United Nations Development Programme

Project Document for nationally implemented projects

financed by the GEF/LDCF/SCCF Trust Funds

| Project title: Strengthening Fiji’s network of Locally Managed Marine Areas (LMMAs) to support globally significant marine biodiversity |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Country: Fiji | Implementing Partner: Fiji Locally Managed Marine Area (FLMMA) Network |  |  |  | Management Arrangements: NGO Implementation Modality |
| UNDAF/Country Program Outcome: Environmental sustainability is strengthened through the improvement of management of energy, natural resources, access to green technology, climate change strategies, conservation of biodiversity, and systems and plans to reduce disasters and risks |  |  |  |  |  |
| UNDP Strategic Plan Output: Output IRRF 1.4.1 Solutions scaled up for sustainable management of natural resources, including sustainable commodities and green and inclusive value chains |  |  |  |  |  |
| UNDP Social and Environmental Screening Category: Moderate |  |  | UNDP Gender Marker: 2 |  |  |
| Atlas Project ID (formerly Award ID): 00116088 |  |  | Atlas Output ID (formerly Project ID): 00113386 |  |  |
| UNDP-GEF PIMS ID number: 5666 |  |  | GEF ID number: 9944 |  |  |
| Planned start date: July 1, 2019 |  |  | Planned end date: June 30, 2023 |  |  |
| PAC meeting date: TBD |  |  |  |  |  |
| Brief project description: The project objective is to strengthen and integrate Locally Managed Marine Areas (LMMAs) into Fiji’s Marine Protected Area (MPA) system through improved institutional and local capacity, management planning and monitoring. Fiji’s globally significant coastal and marine habitats are at risk from multiple threats and declines in coastal fisheries and marine biodiversity have been observed including from nutrient-loading, land-based influences, subsistence and commercial fishing and rising sea surface temperatures. In turn this puts at risk the livelihoods of the Fijian people that depend on these marine resources for sustenance, incomes and the maintenance of their cultural and traditional customs. The project focuses on coastal and marine ecosystems, particularly in the biologically rich Southern Lau seascape, one of the five marine areas in Fiji that are considered to be globally significant based on their uniqueness, endemism and high levels of biological diversity. To achieve the objective, the project has three main strategies or project components as follows: Component 1: Development of a National framework for Marine Protected Area (MPA) system incorporating Locally Managed Protected Areas (LMMAs). This will entail the development of a national MPA policy and implementation plan that provides a road map for the MPA system that integrates LMMAs. It will also update the existing Fiji LMMA (FLMMA) Strategic Plan (2020-2024) to strengthen the use of community-based adaptive management (CBAM) to promote a ridge-to-reef ecosystem-based integrated management approach to LMMAs. Component 2: Enhanced provincial LMMA network balancing resource use and biodiversity conservation. This will be supported by strengthening decentralized provincial governance models and Yaubula Management Support Committees (YMSTS) to provide support to LMMA sites, facilitate integration of village development planning and LMMA management planning in a ridge-to-reef approach, and enhance the capacity of local extension officers to support LMMA management, monitoring and enforcement. Component 3: Project learning, knowledge sharing, communication and M&E. This will help strengthen the existing FLMMA database to align with national and global reporting mechanisms and will operationalize and test it in Southern Lau. It will also ensure that the project is implemented effectively and that knowledge and lessons learned are widely shared with project stakeholders, including the wider public in Fiji, and within the region through existing partnerships with Pacific island countries. |  |  |  |  |  |
| Financing Plan (only cash transferred to UNDP bank account and budgeted under the same GEF project should be included under this section (1), all others should be included under section (2). |  |  |  |  |  |
| GEF Trust Fund |  |  | USD 805,496 |  |  |
| UNDP TRAC resources |  |  | USD 0 |  |  |
| Cash co-financing to be administered by UNDP |  |  | USD 0 |  |  |
| - Total Budget administered by UNDP |  |  | USD 805,496 |  |  |
| Parallel co-financing (all other co-financing that is not cash co-financing administered by UNDP) |  |  |  |  |  |
| Ministry of Waterways and Environment |  |  | USD 400,000 |  |  |
| Ministry of Fisheries |  |  | USD 750,000 (FJD 1,250,000) |  |  |
| Ministry of iTaukei Affairs / iTaukei Affairs Board |  |  | USD 217,077 (FJD 460,204) |  |  |
| Fiji Locally Managed Marine Area (FLMMA) Network |  |  | USD 611,320 (FJD 1,296,000) |  |  |
| Conservation International |  |  | USD 427,000 |  |  |
| WWF |  |  | USD 250,000 |  |  |
| IUCN |  |  | USD 725,277 (FJD 1,537,588) |  |  |
| Pacific Blue Foundation |  |  | USD 47,170 (FJD 100,000) |  |  |
| UNDP |  |  | USD 50,000 |  |  |
| Government |  |  | USD 1,367,077 |  |  |
| Non-Governmental Organizations |  |  | USD 2,110,767 |  |  |
| - Total co-financing |  |  | USD 3,477,844 |  |  |
| - Grand-Total Project Financing (1)+(2) |  |  | USD 4,283,340 |  |  |
| Signatures |  |  |  |  |  |
| Signature: print name below |  | Agreed by Government |  | Date/Month/Year: |  |
| Signature: print name below |  | Agreed by Implementing Partner |  | Date/Month/Year: |  |
| Signature: print name below |  | Agreed by UNDP |  | Date/Month/Year: |  |

# Table of Contents

I.	Table of Contents	3

II.	Development Challenge	6

III.	Strategy	16

IV.	Results and Partnerships	21

V.	Project Management	49

VI.	Project Results Framework	51

VII.	Monitoring and Evaluation (M&E) Plan	55

VIII.	Governance and Management Arrangements	58

IX.	Financial Planning and Management	61

X.	Total Budget and Work Plan	63

XI.	Legal Context	67

XII.	Risk Management	67

XIII.	Annexes	70

Acronymns and Abbreviations

| CBAM | Community based adaptive management |
| --- | --- |
| CBD | Convention on Biological Diversity |
| CI | Conservation International |
| CORAL | Coral Reef Alliance |
| CSO | Civil Society Organization |
| DDC | District Development Council |
| EBSA | Ecologically or Biologically Significant Marine Areas |
| EIA | Environment Impact Assessment |
| FELA | Fiji Environmental Law Association |
| FIMA | Fiji Islands Marine Ecoregion |
| FLMMA | Fiji Locally Managed Marine Area Network |
| FSP | Full Sized Project |
| GEF | Global Environment Facility |
| GEFSEC | Global Environment Facility Secretariat |
| GIZ | German Corporation for International Cooperation |
| GRM | Grievance Redressal Mechanism |
| iQoliqoli | Traditional Fishing grounds |
| iTaukei | Traditional system of laws and governance |
| IUCN | International Union for the Conservation of Nature |
| LMMA | Locally managed marine areas |
| M&E | Monitoring and Evaluation |
| MACBIO | Marine and Coastal Biodiversity and Management in Pacific Island Countries |
| MITA | Ministry of iTaukei Affairs |
| MOEW | Ministry of Environment and Waterways |
| MOF | Ministry of Fisheries |
| MPA | Marine Protected Area |
| MRMDNDM | Ministry of Rural and Maritime Development and Natural Disaster Management |
| MSP | Medium Sized Project |
| NTF | National Trust of Fiji |
| PA | Protected Area |
| PAC | Fiji Protected Area Committee |
| PC | Project Coordinator |
| PCDF | Partners in Community Development Fiji |
| PIF | Project Identification Form |
| PIMS | Project Information Management System |
| PIR | GEF Project Implementation Report |
| PMU | Project Management Unit |
| POPP | Program and Operations Policies and Procedures |
| PPG | Project Preparation Grant |
| SCRUM | Sustainable Coastal Resources Use and Management |
| SDG | Sustainable Development Goals |
| SESP | Social and Environmental Screening Procedures |
| SIDS | Small Island Developing States |
| SIP | Stakeholder Involvement Plan |
| SPC | Secretariat of the Pacific Community |
| SPREP | Secretariat of the Pacific Regional Environment program |
| STAP | GEF Scientific Technical Advisory Panel |
| SUMA | Special Unique Marine Areas |
| Tabu | Seasonal or temporal closure |
| TAB | iTaukei Affairs Board |
| TLFC | Land and Fisheries Commission |
| TOR | Terms of Reference |
| UNDP-CO | UNDP Country Office |
| UNDP-GEF | UNDP Global Environmental Finance Unit |
| USP | University of the South Pacific |
| WCS | Wildlife Conservation Society |
| WIFN | Women in Fisheries Network |
| WWF | World Wildlife Fund |
| YMST | Yaubula Management Support Team |

# Development Challenge

- This project aims to conserve globally significant marine biodiversity in Fiji through the development of a national policy and implementation plan for a marine protected area (MPA) system that integrates locally managed marine areas (LMMAs).

- With 130,450 km2 of archipelagic waters, 45,000 km2 territorial waters and over 322 islands, Fiji hosts a high diversity of marine biodiversity and a wide variety of marine habitats, including estuaries, mangrove wetlands, seagrass, macroalgal assemblages, protected and exposed soft shores, lagoons, coral reefs and slopes.  Fiji has over 1,198 species of fish, 1,056 marine invertebrates and approximately 1,000 coral reefs. The Fijian waters contain some 3.5% of the world’s coral reefs and 9% of the reefs in the Pacific Ocean. Two species of sea turtle nest in Fiji, the green turtle Chelonia mydas and the hawksbill turtle Eretmochelys imbricate. Three species of sea snake breed in Fiji, including two (the amphibian-banded kraits Laticauda colubrine and L. laticauda that breed on land.

- Fiji’s marine biodiversity provides a wealthy natural resource base on which the Fijian economy relies.  There is a particular reliance on inshore and offshore fisheries. About 80% of Fiji’s population lives in coastal areas and are highly dependent upon fish and marine resources for subsistence, especially in remote areas. The indigenous peoples of Fiji – iTaukei Fijians – have a profound connection with the sea, extending from reliance on ocean resources for food and livelihoods to deeply rooted cultural practices that involve the use of marine fauna and flora for ceremonies and celebrations. They also have a rich history of customary laws and practices, including through the stewardship of inshore marine areas. Historically, the use of marine resources within traditional fishing grounds (iQoliqoli) was governed by customary law and informed by traditional ecological knowledge. Traditional conservation mechanisms include tabu (seasonal or temporal closures), the declaration of sacred fishing grounds, and controls over the number of villages allowed to harvest fish, the fishing practices that can be used and the number of fish that can be taken. Reflecting this strong custom, the management of Fiji’s inshore fisheries and coastal ecosystems is guided by a dual governance system that incorporates both a modern legal framework and a traditional iTaukei system of law and governance that is deeply rooted in Fijian culture and customs. There are 410 traditionally managed fishing grounds (385 marine and 25 freshwater iQoliqoli) in Fiji, covering 3.1 million hectares of inshore waters. The resources from these provide livelihoods for approximately 400,000 traditional resource owners in coastal villages.  The rich coastal and marine resources provide a variety of ecological functions that translate directly and indirectly to economic services that have value to local communities and the Fijian economy.  The national annual value of the seven main environmental services from Fiji’s coastal and marine resources range from US$1,146 to US$1.172 million, with subsistence food provision from inshore fisheries and coastal resources valued at US$44.09 million and small-scale inshore commercial fisheries producing a total value of US$7.30 to 26.88 million per year.

- As part of its international efforts to protect its marine resources, Fiji is a signatory to the Convention on Biological Diversity (CBD); through this, Aichi Target 11 aims for 10% of coastal and marine areas to be conserved. In recognition of the importance of protecting the marine environment, the Government of Fiji (at the Small Island Developing States (SIDS) Conference in Mauritius in 2005) committed to the establishment of a network of marine protected areas (MPAs) covering 30% of its territorial waters by 2020. It was the first Pacific nation to do this. This commitment was reaffirmed at the third SIDS meeting in Samoa in 2014, and is reflected in Fiji’s Green Growth Framework. Community-managed marine areas that are built on Fiji’s traditional coastal fishing grounds offer great potential to support the achievement of this target in inshore habitats.

- The concept of locally-managed marine areas (LMMAs) originated in Fiji and has been broadly adopted by local communities and iQoliqoli resource owners. The LMMA approach has empowered local communities to engage in sustainable management of their fishing grounds in a way that reflects traditional customary rights and conserves important fishing stocks. While LMMAs typically have no or limited formal legal protection in Fiji, the traditional management systems under which they operate afford strong protection at the local level. The network has inspired replication in countries across the Pacific and the Indian Ocean. The LMMA approach has been adopted by the Government of Fiji as a key mechanism for sustainable management of inshore coastal fisheries. It also offers the potential for a catalytic expansion of the MPA system through protected areas that provide for both biodiversity conservation and sustainable resource use by local communities (i.e. IUCN PA Category VI), in parallel with the gazettal of large-scale MPAs in offshore areas.

Threats to Marine Resources and Ecosystems

- Poor land use practices: With some of the highest rainfall on the planet, Fiji is endowed with abundant natural water resources, but poor land use practices have resulted in increased soil and nutrient runoff and pollution. These practices include intensification of agriculture without concomitant soil protection, poorly regulated and excessive gravel and boulder extraction, poor logging practices, and poor management of domestic and industrial waste. Poorly managed land-based development and pollution has had serious negative consequences for Fiji’s sensitive coastal ecosystems, including coral reefs and sea grass meadows, affecting their capacity to support local livelihoods. Ecological imbalances from over-fishing are exacerbated by the introduction of modern agricultural practices across the islands, with upland agriculture destabilizing slopes and causing landslides that cause sedimentation on coastal reefs. Further, the increasing use of chemical fertilizers by island communities has stripped soil fertility and increased nutrient blooms on the reefs.

- Global Climate Change impacts: Poorly managed land-based development has made Fiji’s inshore marine habitats more susceptible to changes in climate, including increased ocean temperatures, increased ocean acidification, and more extreme cyclones and tidal events. The root cause of climate change is anthropogenic increases in greenhouse gases.

- Unsustainable fishing practices: Unsustainable fishing practices at commercial and subsistence levels are a significant threat to Fiji’s marine resources. Of the 410 traditionally managed fishing grounds or iQoliqoli, 70 (17%) are considered overexploited and 250 (60%) are fully developed. Overfishing has also led to dramatic declines in important invertebrates such as sea cucumbers and clams, leading to a disruption in species balance that has flow-on effects on ecosystem health. Overfishing, poaching and the use of illegal and destructive fishing equipment (including small mesh nets, fish poisons, dynamite fishing and night scuba fishing) cause problems for inshore areas. Overfishing is caused by increased fishing pressure to meet local seafood and protein needs and to supply (mainly) domestic markets and provide income/livelihoods for rural fisherfolk, coupled with increasingly efficient and destructive fishing techniques. Within the Lau archipelago, overharvesting of invertebrate species, such as sea cucumbers and giant clams, has caused ecological imbalance and an increase in algal cyanobacteria blooms on reefs.  The current rate of extraction of sea cucumbers in Fiji is unsustainable. These practices are further exacerbated by encroachment of offshore fishers (including industrial vessels) into traditional fishing grounds, which contributes to food insecurity and threatens local livelihoods.

- Invasive species: As with many remote islands, invasive species are becoming a major threat to the health of Fiji’s reefs. In localized areas, reefs are impacted by outbreaks of crown of thorns starfish, which can significantly damage coastal health and ecology. Crown of thorns is thought to be one of the main factors contributing to observed changes in coral composition and structure.

- Project conceptual model: The complex web of interacting factors that threaten the globally significant marine biodiversity of Fiji is illustrated in a conceptual model in Figure 1. This indicates the key indirect and direct factors and the points where project intervention can reduce the level of threats and contribute towards the conservation of marine ecosystems, globally threatened species and ecological integrity. The main project intervention strategies are shown as yellow hexagons in Figure 1, and the main elements of these strategies are summarized in the Theory of Change diagram in the following section (Figure 2).

Baseline scenario and associated baseline projects

- On-going government programs and initiatives supported by development partners and NGOs that address the management of coastal and marine ecosystems in Fiji include the following:

- The Green Growth Framework for Fiji: Restoring the Balance in Development that is Sustainable for Our Future 2014 identifies the importance and potential of Fiji’s vast marine ecosystem and recognizes the 30% marine protection target and the establishment of LMMAs as a key step.

- The Government of Fiji made a number of voluntary commitments at the 2017 UN Oceans Conference, which it co-chaired. These commitments included the expansion of large-scale marine managed areas in Fiji (#OceanAction 19904 – Ministry of Fisheries, Ministry of Environment and Waterways) through the development of a legally recognized multiple-use marine spatial plan for Fijian waters by 2018; and a network of integrated terrestrial and marine managed areas across the globally significant Lau seascape, operating under a co-management framework by 2025. Reform of the coastal fisheries sector and the establishment of a national fisheries policy (#OceanAction 19929 – Ministry of Fisheries) will also be completed by 2020, which will enhance the sustainability of coastal fisheries and improve enforcement of fisheries laws. These government actions are bolstered by the Fiji Locally Managed Marine Area (FLMMA) Network voluntary commitment (#OceanAction 21668) to establish an effectively managed and governed network of LMMAs in Fijian communities, covering 100% of Fiji’s iQoliqoli by 2025. Together, these voluntary commitments provide an excellent foundation for this project.

- The lead responsibility for protected area establishment and management in Fiji rests with the Ministry of Environment and Waterways (MOEW). The Ministry is the national focal point for the CBD and has lead responsibility for the implementation and revision of Fiji’s National Biodiversity Strategy and Action Plan (NBSAP). In 2008, the Fiji Protected Area Committee (PAC) was formally established as a technical advisory arm to the National Environment Council, with a mandate that includes supporting the establishment of an adequate and representative national PA system and ensuring the effective management and sustainable financing of that system. The PAC established a Marine Working Group, with inter-agency and CSO membership to complete work on the prioritization of MPAs to achieve the 30% marine protection target. The PAC has endorsed priority marine biodiversity areas of Fiji (the SUMA – special and unique marine areas – a data-driven process supported by the MACBIO project) along with bioregions for Fiji’s entire marine environment. These descriptions of Fiji’s inshore and offshore areas will be a valuable resource for marine spatial planning and designing representative networks of MPAs/LMMAs. The MoEW is also responsible for managing development impacts on coastal areas. The 2011 Integrated Coastal Management Framework of the Republic of Fiji reviews coastal condition and development impacts and provides recommendations (including the development of MPAs) for sustainable coastal resource management (also captured in voluntary commitment #OceanAction19984). The estimated investment of the Ministry in supporting a national MPA network, PAC and sustainable coastal management is over $400,000 over the four-year project period.

- The Ministry of Fisheries (MoF) has responsibility for coastal fisheries management and has a pivotal role in the establishment of MPAs, having the relevant legal mechanisms in both inshore and offshore areas. The MPA Technical Advisory Group was established in 2015 to provide guidance on the establishment of MPAs. It has some overlapping membership with the PAC Marine Working Group, although it operates under its own ToR and work-planning processes. A reform of coastal fisheries management is currently underway, spearheaded by the recent establishment of an Inshore Fisheries Management Division within MoF. The Fiji National Fisheries Policy is currently under development, and MPAs are included in this under draft policy goal 6, which notes the importance of zoning MPAs to enable multi-purpose use for maintenance of community livelihoods. The creation of a 30% MPA network is noted as a cross-cutting issue. National fisheries legislation was recently reviewed and partially replaced by new offshore and aquaculture decrees. To date, six MPAs have been gazetted under Section 9 of the Fisheries Act, including marine reserves in Naiqoro Passage, and Kluva that were gazette in January 2018.The Vatu-i-Ra Marine Reserve is under review and expected to be gazetted shortly. The MoF is also supporting the voluntary commitment to launch the Fiji Whale and Dolphin Action Plan (#OceanAction19959). A number of Important Marine Mammal Areas (IMMAs) in Fiji have been provisionally identified, including migratory routes and calving sites. A systematic survey and inventory of the resource stocks of iQoliqoli is in progress, with approximately half of the 410 customary fishing grounds surveyed to date. The estimated annual investment of the MoF in supporting a national MPA network and LMMA management is $750,000 over the four-year project period; this includes support for LMMA committees, preparation of fisheries management plans for in-shore areas, and support for marketing and storage facilities to enhance local fisher community incomes.

- A critical actor in LMMA management is the Fiji Locally Managed Marine Area (FLMMA) Network, In the Indo-Pacific Region the LMMA Network is a group of practitioners involved in various community-based marine conservation projects. Community management at the LMMA level is coordinated by the FLMMA Network, established in 2001.  FLMMA was registered under the Charitable Trust Act in 2004. FLMMA provides information and resources on LMMAs and community-based adaptive management, and delivers training in project design, monitoring, data management and analysis, fundraising and communications. The FLMMA Strategic Plan 2014-2018 outlines the priorities of FLMMA, which include strengthening village and local capacity and governance; strengthening FLMMA governance by promoting “Yaubula” (i.e. environmental) Ridge to Reef principles for ecosystem-based management across villages; building monitoring capacity for decision making at site and network levels; and promoting the sharing of best practice, effective and scaleable LMMA programs. FLMMA aims to create and support functioning and cohesive community-based, island-based and provincial-based integrated co-management institutions, which will lead the local implementation of conservation and sustainable natural resource management in Fiji by 2020 (#OceanAction 21668). Specifically, under the Conservation International-led Lau Seascape Initiative FLMMA supports: (i) developing strong partnership and programmatic opportunities under the Lau Seascapes Initiative; (ii) contributing to the development of a ten-year strategic vision, resource mobilization plan and implementation plan for the Lau Seascape; and (iii) partnering in the preparation of funding applications for implementation and advancement of the Lau Seascape at the site level. The current budget for the FLMMA Secretariat’s activities is approximately $75,000-150,000 per annum, provided via a range of donors including the MacArthur Foundation and Packard Foundation. This budget does not include funds invested by individual FLMMA partners (see below).  As part of its baseline efforts, FLMMA will spend about $611,320 over the four-year period of the project, to support traditional resource owners in community-based adaptive management (CBAM) of their LMMAs, to provide training in project design, monitoring, data management and analysis, and communications, and to promote best practices.

- The Ministry of iTaukei Affairs oversees Fiji’s 14 Provincial Councils, Roko Tui (Chiefs) and Assistants, and a network of provincial Conservation Officers. It also oversees the Yaubula Management Support Teams (YMSTs) that support the LMMAs, and appoints members of iQoliqoli committees as Fish Wardens. The Ministry invests an estimated $176,000 annually over the four-year period of the project in supporting provincial networks, governance structures and YMSTs at Provincial, Cluster, District and local levels, and in capacity development that in turn supports LMMAs.

- Other key baseline projects and efforts include:

- The Wildlife Conservation Society (WCS) has 16 years of experience building conservation initiatives in Fiji, with a focus on LMMAs, protected areas, reef resilience, catchment management, freshwater fish, land-sea planning, coastal fisheries, and climate and natural disaster vulnerability. WCS is implementing the project District Level Ecosystem Based Management and Coastal Fisheries Management in Fiji, supported by the John D. & Catherine T. Macarthur Foundation and David & Lucille Packard Foundation, with an annual investment of $500-600,000 over the last five years.

- WWF-Pacific is implementing the project Establishing Key Fisheries Management Approaches to Ensure Long Term Sustainability of Fiji’s Globally Significant Great Sea Reef. This project will focus on building and strengthening fisheries and iQoliqoli management in two districts: Mali Island and Dreketi of the Macuata iQoliqoli Cokovata. This work will help demonstrate effective fisheries management and will provide lessons to other LMMA sites in Fiji. WWF is also implementing the NZ Aid-financed Securing food, fisheries and a sustainable seafood future in Fiji project. The project will empower Vanua Levu iQoliqoli communities, build district fisheries management capacity, engage seafood supply chains, enable the hospitality sector to source seafood sustainably, and return economic benefits to iQoliqoli communities. WWF is also supporting the development of comprehensive district-level development plans via its Sustainable Coastal Resource Use Management (SCRUM) Program and will likely spend around $250,000 over the four-year project period.

- The International Union for the Conservation of Nature (IUCN) is implementing the Marine and Coastal Biodiversity Management in Pacific Island Countries (MACBIO) GIZ-International Climate Initiative project. As part of this, IUCN has completed a marine ecosystem service evaluation for Fiji (2015); a marine spatial planning and documentation of best practices for marine resource conservation; a review of legislation, policies, strategies and plans relating to the development of a MPA system; and an MPA typology for Fiji. Consultation on the establishment of the national MPA system has been initiated.  This project will build on the work of IUCN.  As part of the collaborative effort, IUCN will likely spend around $725,277 during the four-year project period to promote the MPA concept and provide geo-spatial support, mapping capabilities and communications.

- Conservation International is actively engaged in the Lau Seascape Initiative, which entails the promotion of an integrated landscape and seascape approach to management of LMMAs. This is helping to build provincial and CSO partner capacity and skills for the integration of land-based activities in LMMA planning, monitoring the effectiveness of conservation and sustainable use of marine resources, and providing professional and technical support to partner agencies working in the Lau seascape. CI expects to spend around $427,000 during the four-year period of the project in the Lau province that will complement and support the GEF investment.

- The Pacific Blue Foundation (PBF), a partner institution within the FLMMA Network, is active in supporting LMMA activities in Fiji. In particular, PBF plan to spend around $47,170 over the four-year period of the project in Southern Lau to support the Lau Seascape Initiative, including working with Provincial actors.

- The Women in Fisheries Network-Fiji (WiFN) works through a network of partners (e.g. women fishers, research and development agencies, technical experts, government agencies and scientists) to support: (i) improving the sustainable use of fisheries resources; (ii) strengthening efforts towards the economic empowerment of women through the development of new business opportunities for women in fisheries; and (iii) strengthening the WiFN-Fiji to improve support and services to fisherwomen, such as capacity development, sustainable fishing practices, and research and development. At the same time, the WiFN-Fiji is developing its in-house capacity to function as a network and to better support its members and women engaged in the fisheries sector. WiFN-Fiji will support the project by providing training support, expertise and tools to enable the improved integration of gender aspects in the project activities.

- The Asian Development Bank-supported Coral Triangle Initiative includes a project on Coastal and Marine Resources Management in the Coral Triangle of the Pacific; this also receives financial support from GEF and the Government of Finland. The project, covering PNG, Solomon Islands, Timor Leste, Fiji and Vanuatu, supports actions to effectively manage and sustainably finance networks of marine managed areas, strengthen integrated watershed and coastal management systems, and demonstrate measures to increase the capacity to adapt to climate change.

- The AFD and FFEM-supported project RESCCUE (Restoration of Ecosystem Services and Adaptation to Climate Change), implemented by the Secretariat of the Pacific Community (SPC), is underway in a number of Pacific countries. Project RESCCUE efforts in Fiji are supported by the University of the South Pacific’s Institute of Applied Science, with Landcare Research, WCS, CI and the Fiji Environmental Law Association. The project is strengthening integrated coastal zone management in Ra and Kadavu provinces, with relevant activities to this project including LMMA support and sustainable fishing practices.

Long-term solution and barriers to be addressed

- Although the programs and projects described in the previous section are supporting the management and conservation of coastal and marine ecosystems in Fiji, there are a number of key deficiencies and barriers to the integrated and effective management of these ecosystems and the ecological, socio-economic and other services they provide. There are three key barriers to unlocking the full potential of LMMAs to contribute to the protection of Fiji’s globally significant marine biodiversity through the national MPA system, as outlined below.

Barrier 1: The current policy and legal framework is uncoordinated and does not offer an appropriate range of tools and guidance for integrating LMMAs within the national MPA system

- A significant weakness of the present policy landscape in Fiji is the absence of a comprehensive national policy for MPA management.  MPA policy comprises multiple policy instruments that support the development and management of MPAs, yet these are fragmented. This is partly due to the multiple government roles in establishing a national MPA system. The Ministry of Environment and Waterways (MoEW) is responsible for coordinating and reporting on Fiji’s protected areas, including MPAs, while the Ministry of Fisheries (MoF) has the legal powers and mechanisms to establish MPAs by gazettal. Multiple actors, centered on the FLMMA Network, offer support to community-based LMMAs.

- The existing legal mechanisms have some notable strengths and weaknesses in terms of the marine environment.  The Fisheries Act 1942 establishes a system for recognizing customary rights to access and use resources within iQoliqoli through a licensing and permitting system, but it has no provisions requiring or enabling the creation of MPAs. Under the Fisheries Regulations (specifically the Marine Reserve Regulations) established under the Fisheries Act, there is some scope for the creation of ad-hoc, site-specific MPAs.  Two marine reserves have been created under the Marine Reserve Regulations, mainly for conserving and protecting sharks and other marine organisms such as coral. However, the low number of MPAs created is reflective of the reluctance of communities and CFROs to have customary LMMAs gazetted.  Although the Offshore Fisheries Management Decree 2012 contains no MPA-specific objectives, it incorporates conservation and long-term sustainable use. Further, it incorporates various principles that may support the development of an effective MPA system, including ensuring long term sustainability of fisheries resources and ensuring the participation of local communities and artisanal fishers in fisheries management. However, it does not define an MPA and contains no provisions with the purpose of designating or managing MPAs. Also, the Decree is not particularly well suited to regulating inshore marine areas, in particular iQoliqoli. On the other hand, informal MPA mechanisms, including tabus and LMMAs, go some way to bridging the gap between customary and modern law, as they combine traditional knowledge and practices with modern scientific and technical expertise in MPA management. LMMAs have effective tools for community-based management of marine resources at the local level, including ‘no-take’ zones enforced by customary law. Although FLMMA’s vision, goals and approach provide some guidance for the development and implementation of LMMAs, these are not legally recognized or legally enforceable; therefore, their effectiveness at achieving ecological outcomes can be at risk. It is expected that meeting the 30% target for marine protection in Fiji will require the adoption and use of a range of mechanisms, both regulatory and customary, yet there is no clear guiding policy or implementation framework for coordination between these. While marine spatial planning is underway through the MACBIO project to identify priority sites for MPA establishment, there is no clearly articulated policy to outline what a MPA network in Fiji will look like and how LMMAs fit within this, nor is there an implementation plan outlining the steps required by different players for achievement of the 30% protection target. Compounding this, there is no accepted government and community-supported definition of a ‘marine protected area’ that aligns to international MPA criteria and that respects traditional customary management and resource use.

- In parallel, there is a lack of appropriate and modern tools and guidance at a site-based level. It is envisaged that LMMAs can make a substantial contribution to Fiji’s MPA system through managed resource-use PA categories, although application of IUCN categories to community-managed MPAs – or parts thereof – is not always straightforward and requires clear guidance and protocols for discussion with local communities. Although only some permanent tabu areas within LMMAs are currently counted as ‘MPAs’ in national reporting, with enhanced management and ecological monitoring there is the potential for many more areas to be included according to the criteria for IUCN PA Category VI (Protected area with sustainable use of natural resources). Currently, nature conservation is not always well integrated into LMMA management processes and protocols. Despite a recent evolution towards ecosystem-based management (e.g. Kubalau District of Vanua Levu) and pilots of enhanced protected LMMA management (e.g. through the UNDP-supported GEF-5 Ridge to Reef project), biodiversity conservation objectives are not yet considered in a broad scale and standardized manner. A 2009 review of over 100 Fijian LMMAs found that in 44% of cases the primary management objective was ‘fisheries management’, ‘conservation’ in 14% of cases, and both of these objectives in 42% of cases. While a process exists for LMMA management planning led by local communities, this does not always consider or integrate biodiversity conservation objectives, nor does it adopt an ecological approach to management, which restricts its potential contribution to the MPA system. The existing Locally-Managed Marine Areas: A guide to supporting Community-Based Adaptive Management (2008) provides a helpful guide to establishing and managing LMMAs but is outdated and weak on ecosystem management. It would be strengthened by more detailed guidance on aspects of management such as MPA design, zoning, monitoring and enforcement.

Barrier 2: Insufficient capacity at national, provincial and local levels to keep pace with the interest in LMMA/MPA establishment and the shift towards ecosystem-based management

- Management effectiveness is highly variable across LMMAs. The establishment of LMMAs, including tabu, in many parts of Fiji has had positive impacts on depleted fishery stocks; however, ensuring viable marine biodiversity and abating threats to conservation requires improved management capacity at national, provincial and local levels. Because the origins of LMMAs are in sustainable resource use and the management of inshore fisheries as a source of livelihoods and protein for coastal communities, there is limited capacity for ecosystem-based management of LMMAs. This is particularly true of the skills and knowledge needed to address the linkages between land and sea-based interactions, which often undermine the condition and sustainability of marine resources in the LMMAs.  The ability to effectively manage such interactions, along with broad-based conservation efforts in the marine areas, can create the ‘enabling conditions’ necessary for effective conservation. To achieve this, new skills and tools are needed.

- While the creation of LMMAs is steadily growing, only some of the LMMAs have functioning management committees and management plans. Further, around 70% of LMMAs are over-exploited. The technical capacity and skills of the FLMMA Network and provincial government staff to enhance the management of existing and new LMMAs has not increased at the same rate that new sites have been established, meaning that the current technical support is spread too thin. Some existing LMMAs have no established management committee or management plan, indicating that there are significant gaps in capacity and knowledge among iQoliqoli owners and provincial extension staff regarding the rules and regulations for establishing LMMA management committees and operational modalities. Where LMMA management plans exist, they are geared to fish production; consequently, the emphasis on ecosystem-based management requires new skills and tools to assess the biological values of the marine environments to enable informed decisions regarding zoning, defining sustainable harvest rates and periods for fish species, and managing threats. There are also geographic gaps in iQoliqoli that have not yet been engaged by the FLMMA Network; the Southern Lau group is one such area. To support enhanced rollout, the FLMMA Network has transitioned from a national advocacy model to one of decentralized provincial support (‘Yaubula’ or Ridge to Reef management, partnering with the Ministry of iTaukei Affairs). However, it is restricted by a lack of capacity among provincial extension officers. In parallel, there is insufficient capacity among national authorities to support extension agencies on MPA management.

- Many communities are engaged and interested in establishing LMMAs but lack technical capacity in LMMA management, ecosystem-based approaches, and monitoring and evaluation. There is also a challenge to effectively bring together modern and customary enforcement approaches for inshore coastal management. There is inadequate capacity and limited training for provincial extension officers and voluntary community Fish Wardens in such areas as managing poaching and compliance with tabu areas to better enhance the effectiveness of customary enforcement.

Barrier 3: Low awareness of the multiple benefits of LMMAs/MPAs, including an understanding of their ecological health and changes in these over time

- The LMMA approach is buoyed by strong awareness and interest at the local level, yet this is largely based on an appreciation of the food security and customary benefits. There is limited awareness of the potential biodiversity benefits of LMMAs and the importance of retaining biodiversity values. Increasing this awareness would support the management of LMMAs for marine biodiversity conservation. Awareness of the LMMA approach and its multiple benefits is still low in some geographic areas, including the biodiverse Lau Group. In parallel, there are few incentives available to encourage communities to integrate biodiversity outcomes and activities within LMMA management.

- Sustainable fishing and conservation benefits of LMMAs continue to emerge, but they have not been systematically documented. Many areas lack monitoring data on ecological status and trends, or information is collected but in a non-standardized fashion. A lot of the site-based data are not transmitted to national authorities for collation and storage, restricting the ability of these authorities to report on progress with MPA establishment and to identify priorities for new LMMAs/MPAs or extra management support. There is also limited capacity for monitoring the effectiveness of LMMAs in securing resource protection, livelihood and conservation benefits. Although a community-based LMMA monitoring system has been developed, this has not yet been rolled out across Fiji. Of the locations where monitoring has been implemented, most have completed only basic monitoring that does not provide information on ecological condition that would enable the monitoring of the longer-term socio-economic, cultural and environmental contributions of LMMAs.

- The GEF investment will promote strengthened policy and institutional frameworks for the establishment and management of marine protected areas (including LMMAs) and will ensure ecosystem-based management that integrates a ridge-to-reef conservation approach into LMMA and MPA plans. This will be achieved by new policy, improved tools and techniques, institutional capacity development, inter-sector collaboration in marine planning approaches, and increased public awareness of the threats to marine biodiversity and ecosystems.

- The direct threats affecting the project target (Fiji’s marine biodiversity) and their relationships with a range of indirect factors (root causes) are illustrated in Figure 1, with entry points for project intervention strategies indicated. The relationship between the barriers and the project intervention logic is further illustrated in the theory of change diagram in Figure 2.

Alignment with national and global priorities

- National Biodiversity Strategy and Action Plan: The GEF project aims to support the establishment of Fiji’s first marine protected area policy, integrate LMMAs, and improve political support and capacity for establishment of an MPA network in Fiji; these are aligned with the Fiji NBSAP (2017-2024). The Implementation Framework (2017-2022) for the NBSAP recognizes the adoption of an ecosystem-based and ridge-to-reef management approach for the management of land and sea resources. The implementation framework is aimed at meeting Fiji’s commitment to establish a 30% representative network of marine protected areas within inshore, archipelagic and offshore waters, to protect marine biodiversity, and to support community, livelihoods and the national economy. Supporting actions address the mapping of priority marine biodiversity areas, finalizing design principles and establishing a system through a range of mechanisms, including gazettal and provincial endorsements. Other relevant actions include establishing clear and effective legal mechanisms and practical institutional and administrative arrangements for PAs; strengthening the national M&E framework for Fiji’s protected areas; enhancing mutually beneficial co-management arrangements; mainstreaming PAs and MPAs across other sectors; developing sustainable financing mechanisms; and strengthening the FLMMA Network and Women in Fisheries Network-Fiji. Recognition of traditional rights to resources is a foundational principle.

- UN Ocean Conference Voluntary Commitments: The proposed project has been developed to dovetail with Government of Fiji, FLMMA Network and other partner Voluntary Commitments made during the recent UN Ocean Conference (refer Baseline Section).

- Sustainable Development Goals and Aichi Targets: The proposed project will support the achievement of the Sustainable Development Goals (SDGs) in Fiji, most notably SDG14 to Conserve and sustainably use the oceans, seas and marine resources for sustainable development; target 14.2 on sustainable management of coastal and marine ecosystems; target 14.5 on coastal and marine protection; and target 14.7 on sustainable use of marine resources by SIDS.  The proposed project will contribute to the following Aichi Targets: Target 6: By 2020, all fish and invertebrate stocks and aquatic plants are managed and harvested sustainably, legally and applying ecosystem based approaches, so that overfishing is avoided, recovery plans and measures are in place for all depleted species, fisheries have no significant adverse impacts on threatened species and vulnerable ecosystems and the impacts of fisheries on stocks, species and ecosystems are within safe ecological limits; and Target 11: By 2020, at least 17 per cent of terrestrial and inland water areas and 10 per cent of coastal and marine areas, especially areas of particular importance for biodiversity and ecosystem services, are conserved through effectively and equitably managed, ecologically representative and well-connected systems of protected areas and other effective area-based conservation measures, and integrated into the wider landscapes and seascapes.

Figure 1: Threats, root causes and barriers to the long-term solution and GEF strategies to address them

# Strategy

- The project objective is to strengthen and integrate Locally Managed Marine Areas (LMMAs) into Fiji’s Marine Protected Area (MPA) system through improved institutional and local capacity, management planning and monitoring. To achieve this objective, the GEF alternative aims to remove the barriers to the long-term solution by strengthening policy, legal and institutional measures for the contribution of LMMAs to the marine protected areas system, and by enhancing provincial capacity for planning, management and monitoring of LMMAs in South Lau. This includes increased management effectiveness of LMMAs to improve conservation of biodiversity and ecosystem services by local communities. The project recognizes the importance of marine and coastal biodiversity to ecological balance, economic and social development, and the fact that this biodiversity underpins the lives and livelihoods of many people who depend on artisanal and inshore fishery activities for local food security and employment; this is particularly the case in areas with limited alternatives.  The project will be implemented over a 4-year period, based on the following principles:

- Supporting and implementing a participatory/consultative bottom-up LMMA planning and implementation approach that focuses on national, provincial, district and community priorities;

- Supporting a decentralized provincial governance model and Yaubula Management Support Committees that provide support to LMMA’s, thereby increasing their potential to become agents of conservation and sustainable marine resources use;

- Strengthening capacities of all stakeholders in effective enhancement of conservation and sustainable use of marine and coastal biodiversity;

- Improving coordination and collaboration between local, district, provincial and national governments;

- Adopting an integrated ecosystem-based ridge-to-reef approach as a strategy for improving the planning and management of the marine seascapes;

- Creating an effective knowledge base that builds on successful lessons and experiences from previous and ongoing programs and projects;

- Ensuring an adaptive management approach that considers ecological, demographic, market, technological and economic factors at land/seascape scales and builds on regular monitoring and evaluation of approaches.

- The project objective will be achieved via three inter-related and complementary strategies (Project Components comprising Outcomes and Outputs) that focus on removing the three key barriers to accomplishing the long-term solution (Figure 1), using the intervention pathways shown in the theory of change diagram (Figure 2). Indicators and assumptions for expected Outcomes under the Components are given in the Project Results Framework. The three Components are:

- Component 1: National framework for Marine Protected Area (MPA) system incorporating Locally Managed Marine Areas (LMMAs)

- Component 2: Enhanced provincial LMMA network balancing resource use and biodiversity conservation

- Component 3:  Project learning, knowledge sharing, communication and M&E

Figure 2: Theory of Change

Project Area

- Southern Lau was selected because it is one of the five marine areas in Fiji considered to be globally significant based on its uniqueness, endemism and high levels of biodiversity.  It is also one of the 26 areas in the Western South Pacific that meet the Convention on Biological Diversity (CBD) criteria for ecologically or biologically significant marine areas (ESBAs).  Located in the southern and far south-eastern regions of Fiji, and straddling the borders of the Tongan EEZ, this area includes seagrass beds, patch and fringing reefs, atolls, barrier reef systems such as the Great Astrolabe Reef, seamounts, deep upwelling slopes, submarine canyons and the Lau Ridge. The waters around the Southern Lau region include important marine foraging areas for Fiji’s sole species of endemic seabird, the critically endangered Fiji petrel (Pseudobulweria macgillivrayi), which is believed to number less than 50 individuals. The area supports high catch rates for tuna—particularly bigeye and albacore—and associated pelagic species. The offshore waters comprise an important migration corridor for great whales, including humpback, sei, minke and sperm, and smaller whale and dolphin species. In nearshore and onshore settings, the islands provide important feeding and nesting areas for hawksbill and green turtles.  The Southern Lau islands are also important for such reef fishes as the endangered humphead wrasse (Cheilinus undulates), bumphead parrotfish (Scarus perrico), vulnerable giant grouper (Epinephelus lanceolatus), and giant sweetlip. They provide important breeding areas for inshore shark species (including IUCN Red List species such as common hammerhead, scalloped hammerhead, giant hammer-head) and the oceanic whitetip, blue and silky sharks. They are also home to four giant clam species, including two that are listed as Vulnerable on the IUCN Red List: the rare ‘devil giant’ or tevoro clam and the smooth or southern giant clam. Over 80 species of shallow-water amphipods (shrimp-like crustaceans) have been described across the Fiji island groups, including the Southern Lau region, 41% of which are endemic. The seamounts south of the Southern Lau islands are relatively intact and are currently not exploited by fisheries or mining interests. Along with canyons and slopes, the seamounts are associated with upwelling and downwelling activities, which support primary productivity within these deep-water areas.

- The Southern Lau region comprises four districts with a total of eight islands, containing 17 villages with a population of around 1,160 individuals. The ratio of men to women is 0.78. The islands covering Southern Lau are divided into two clusters for administrative purposes: the Ono-i-Lau islands and the Vulaga Islands.  The Ono-i-Lau islands cluster includes one district (Ono) and two islands (Ono-i-Lau and Vatoa), with five villages and a population of around 398 individuals. The Vulaga islands cluster includes three districts (Fulaga, Kabara and Moce) with a total of five islands (Fulaga, Ogea, Kabara, Komo and Moce) and 12 villages (Muananicake, Muanaira, Naividamu, Ogea, Naikeleyaga, Udu, Tokalau, Lomati, Namuka I Lau, Komo, Nasau and Korotolu), with a combined population of around 760 individuals.  These two clusters form the two demonstration seascapes for this project for LMMA expansion and enhanced management.

- The Ono-i-Lau islands cluster includes small channels, a lagoon, fore reefs, patch reefs and reef flats.  The reefs are very high in fish diversity and biomass; there are many herbivores, high coral cover, healthy coralline algal cover and several shark species.  The Vulaga Islands cluster is also rich is marine biodiversity. The Moce island, while boosting very high fish diversity, also harbors the spinner dolphin (Stenella longirostris); the connectivity with deep waters makes it potentially an area of high biodiversity.  The Cakau Lekaleka Reef is recognized as a site of national significance for its marine ecosystem, and is known for sharks and aggregations of giant sweetlips, barracuda and groupers.  The Yasaga islands are a huge atoll with a barrier reef, extensive reef systems with several islands, and a sizeable lagoon that has high fish diversity; it is part of a whale migration route and has a large number of boobies nesting on the main island. There is a high diversity of sharks in the lagoon (tiger, silvertip, whitetip, nurse, grey and blacktip) and unique coral assemblages.  The Vulaga and Ogea islands are seabird nesting sites, have marine caves on their coastlines, and are enclosed with fringing and barrier reefs.  Their lagoons have important sea grass beds and are likely to provide foraging grounds for green turtles. Ogea Island has very high fish diversity, good coral cover and manta rays, and is likely to provide spawning grounds for the grouper (Epinephelus fuscoguttatus).  Ogea island is also the home for the endemic Ogea monarch (Mayrornis versicolor), and is classified as an Important Bird Area.

- Additional information on the demonstration area in Southern Lau is included in Annex 12.

Vulaga Islands cluster

Ono-i-Lau islands cluster

FIGURE 3: Map of Fiji showing South Lau project sites (showing the boundary limits of the Lau Province seascape and the two island clusters in Southern Lau, with the Ono-i-Lau islands cluster SUMA at the southern most end and the Vulaga Islands cluster SUMA above it).

Innovation

- Transforming to an ecosystem-based approach to LMMA planning and management will support iQoliqoli resource owners to integrate LMMAs within a broader ridge-to-reef approach. Many of the proposed innovative activities in this project are aimed at reducing threats to marine resources and ecosystems, including improved and sustainable fisheries, improved land-based developments and improved pollution control; these are all highly scalable. This provides an innovative application of ecosystem-based management at multiple scales, while also reflecting iTaukei laws and customary use of marine resources.  The project also aims for the first time to integrate the traditionally community-managed LMMAs into a broader national policy on MPAs, while ensuring that traditional social, cultural and economic practices of local communities in inshore areas are maintained and promoted.

Socio-economic benefits

- Local socio-economic benefits will accrue to the LMMA sites in the Southern Lau seascape.  Such benefits would arise from the reduction of degradation of valuable marine habitats, over-harvesting of marine resources and marine pollution, including from land-based sources. This will be achieved through promotion of an ecosystem-based ridge-to-reef approach in planning and management of LMMAs. The project will take action to strengthen the capacity of YMSTs and LMMA communities, and will provide support for the implementation of LMMA management plans to strengthen the resilience of coastal communities through the development of sustainable livelihoods. While these benefits will be delivered in the Southern Lau seascape, up-scaling of the results through knowledge exchange and use of the project-supported technical manuals and guidelines, has the potential to extend the benefits to other LMMAs in the country and region.

- There are many direct project beneficiaries. First, FLMMA (and NGO partners), provincial staff and YMST members from Lau Province will improve their knowledge and skills in ecosystem-based ridge-to-reef approaches to LMMA management. This will be achieved through the project’s capacity-building program for about 100 trainees (of whom 40% would be likely to be women) and through participation in on-the-ground planning and management of LMMAs. About 1,160 individuals (at least 50% of whom would be women) from the Ono-i-Lau islands and the Vulaga Islands clusters will benefit from improved livelihoods arising from the wise stewardship and sustainable use of marine resources, and from income-generation and value-chain processes. Indirect beneficiaries include those in the remaining three island clusters in the Lau Province, who will benefit from potential scaling-up opportunities that will arise from the improved understanding of provincial staff and YMST members to apply ecosystem-based management.

- Gender mainstreaming will be an important consideration for the successful implementation of the project. While some gender disparities still exist in areas of training opportunities, participation and decision making, in the Southern Lau islands (Annex 7), special measures have been included in the project to incentivise and prioritise women’s engagement, as well as ensure specific programs that benefit women.

# Results and Partnerships

- Expected Results:

- The project is designed to achieve a variety of long-term environmental impacts including establishing the following policy, legal and institutional measures for establishing and managing a MPA network, including LMMAs, in Fiji:

- A national marine protected area policy that integrates Locally Managed Marine Areas;

- An improved regulatory, institutional, planning, management and monitoring framework for locally managed marine areas for the improved conservation and sustainable use of marine resources;

- Improved linkages, governance, capacity and coordination for ecosystem-based planning and management at the national, provincial, district and local levels;

- Improved and sustainable biodiversity-friendly marine and coastal conservation practices; and

- Reduced risks and impacts of unsustainable exploitation of marine resources, including on biodiversity, food security, economics, health and culture.

- The Long-Term Impact (or Global Environmental Benefit) of the project is conservation of marine ecosystems, protection of endemic and threatened species, and improved and sustainable livelihood opportunities for local communities. The project will support enhanced management of 22,000 ha of existing LMMA and establish new LMMAs over 48,000 ha. In particular, through the interventions in the Southern Lau landscape, the project will help improve the status of the critically endangered Fiji petrel, protect the migratory routes of great whales such as humpback, sei, minke and sperm, smaller whale and dolphin species, reef fishes such as the endangered humphead wrasse, bumphead parrotfish and giant grouper, listed as vulnerable by the IUCN, and giant sweetlips. It will protect important breeding areas for inshore shark species. This will be achieved by reduction of direct threats from over-fishing and unsustainable land and coastal developments, and by managing climate change impacts. The project will help to strengthen and integrate LMMAs into Fiji’s MPA system through improved institutional and local capacity, management planning and monitoring. Reduction of direct threats will be achieved under a set of outcomes and associated outputs, which are provided below.

Component 1: National framework for MPA system incorporating LMMAs

Total Cost: US$ 804,500; GEF project grant requested: US$ 174,500; Co-financing: US$ 630,000

Outcome 1: Strengthened policy, legal and institutional framework for contribution of LMMAs to the MPA system

- The key deliverables under Outcome 1 are: National MPA system policy and implementation plan that provide a roadmap for the integration of LMMAs (Output 1.1); FLMMA Strategic Plan updated (2020-2024) (Output 1.2); operational manual or tool-kits that incorporate ecosystem-based approaches for LMMA planning and management (Output 1.3); and strengthened capacity to support MPA/LMMA establishment, management and enforcement (Output 1.4).

Baseline conditions (without GEF project):

- In the absence of GEF funding, the capacity to conserve and sustainably use marine ecosystems will develop slowly and the institutional framework will continue to lack significant capabilities and competencies for co-planning and co-management (between provinces and national levels) of marine natural resources. The development of a comprehensive MPA policy will continue to be slow, leaving a gap in the development of MPA legislation and the management of MPAs. Inconsistency within the Fisheries Act and offshore Decree may not be addressed in a timely fashion and recognition in the formal legal system of voluntary conservation areas like LMMAs may remain unclear. National and Provincial land-based spatial planning policies will not address issues at the seascape level and will likely not integrate biodiversity and ecosystem management into marine development programs. Fiji’s inshore LMMAs will continue to be managed for their fisheries potential at the expense of the ecological values and sustainable use objectives and principles. Land-based development activities will continue, often without an understanding of their inter-relationships with the coastal and marine ecosystems, resulting in a lack of recognition of the economic and social benefits of the marine environment. The existing low capacity for ecological surveys and monitoring of species and habitats, combined with the intense development pressure, will lead to massive loss of biodiversity resources and ecosystem values. Sustainable development will be compromised. Scientific knowledge of biodiversity and ecosystems will be confined to a few agencies and individuals and will remain largely unutilized in the management of the country’s productive marine resources.

Alternative (with GEF project):

- The GEF increment will establish a solid framework (foundational activities) for establishment and management of an MPA system that integrates LMMAs and builds strong coordination between national, provincial, district and local levels. Mechanisms to streamline biodiversity and ecosystem priorities into MPA and LMMA plans will be put in place. Through GEF funding, the project will undertake activities to create Fiji’s MPA policy and institutional and administrative capacity to plan, create and manage MPAs and LMMAs. The intent of the policy is to help maintain the productivity and biodiversity of important and vulnerable marine and coastal areas, including in-shore and off-shore areas, and to facilitate the use of diverse approaches and tools. These tools will include the ecosystem approach, the elimination of destructive fishing practices; the establishment of MPAs consistent with international law and based on scientific information; time/area closures for the protection of nursery, spawning grounds and migratory routes; appropriate coastal land use; a ridge-to-reef planning approach; and the integration of marine and coastal area management into key sectors.

- The FLMMA network will be strengthened and mandated to take greater responsibility and play a central role in the transformation from fisheries-based to ecosystem-based approaches to LMMA planning and management. This will include improving the tools and operational principles for the planning and management of LMMAs and promoting ridge-to-reef approaches in coordination with other key agencies, including the Ministries of Environment and Waterways, Fisheries and iTaukei Affairs. The project will support the development and implementation of an updated Strategic Vision and Action Plan for FLMMA that supports the effective establishment and long-term management of Fiji’s LMMA network, including the ability to effectively engage with key stakeholders (public and private). This Outcome will be achieved through four Outputs.

Output 1.1: National MPA system policy and implementation plan providing roadmap for MPA system integrating LMMAs adopted

- The intent of this Output is to support the development of a national policy and implementation plan aimed at achieving a productive and biologically diverse marine protected area system that provides a roadmap for an MPA system that integrates LMMAs. The Policy will set the national priority actions needed for the establishment of new MPAs and improve the management effectiveness of existing MPAs. It will also promote the integration and improved management of existing and new LMMAs in Fiji, promote their appropriate management, and define the type of interventions needed. To achieve this aim, the project recognizes the need to enhance the consistency between marine and land-based policies and plans and to create a well-managed, ecologically coherent network of MPAs in Fijian waters. The national MPA system policy and implementation plan will set out how policy related to the marine environment fits within the Government’s wider policy framework, what can be achieved by creating an MPA system, how the available tools can be used and how collaboration with various sectoral organizations and interests would be achieved. Importantly, the national policy will provide an overall policy for the management, sustainable use and conservation of marine areas (in-shore and off-shore areas). The policy will also address coordination with management of adjacent coastal and terrestrial lands, given the intrinsic linkage between terrestrial, coastal and marine systems. The process of creating the policy, as well as its existence and provisions, will contribute to national recognition of the importance of conservation of marine and coastal areas, the selection and establishment of an appropriate system of MPAs, and the attainment of sustainable use as a primary goal of management. The integration of LMMAs within the MPS system will need to ensure the protection of Fijian customs and traditions. Therefore the development of the policy and implementation plan will also encompass matters relating to Fijian customs and traditions and customary use and rights over iQoliqoli traditional fishing grounds. It will also consider potential livelihoods-related impacts due to establishment and enhanced management of LMMAs and livelihoods protection and restoration strategies and activities (supporting management of SESP risks, Annex 5).  The establishment of the policy and implementation plan will involve the following indicative activities:

1.1.1.	Hiring of national consultant to facilitate and support the development of MPA policy and implementation plan that integrates LMMAs;

1.1.2.	Engagement of the Protected Area Committee (PAC) Marine Working Group established by the Ministry of Environment and Waterways (MOEW) and the Marine Protected Area Technical Working Group established by the Ministry of Fisheries in the development of MPA policy and implementation plan;

1.1.3. 	Conduct workshops and consultations to reach common consensus on a whole-of-government definition of what constitutes a ‘marine protected area’ that would provide the foundation for strengthening the enabling framework (policy, regulatory and institutional) that is inclusive of LMMAs;

1.1.4.	Based on the above 1.1.3, gather political and public support for national interpretation of a MPA system that reflects international protected area standards and CBD definition of MPAs, along with its alignment within the national context and customary coastal management;

1.1.5.	Through consultations with government, non-government and communities define a legal basis for establishment of different categories of MPAs that recognizes the need for varying degrees of protection and community and industrial resource uses, management categories and zoning typologies.  This will facilitate the defining of a flexible management and zoning approach the enables the integration of LMMAs into the MPA system that ensures the cultural, traditional and food security values that communities attach to their traditional fishing grounds;

1.1.6.	Develop a MPA policy and time-based implementation plan for: (i) comprehensive MPA legislation that recognizes the need for a multiple categories of MPAs; (ii) formal recognition of the voluntary contribution of LMMAs to Fiji’s marine environment obligations; (iii) establishing a comprehensive systems of MPAs for Fiji that preserves representative samples of its rich marine biodiversity and ecosystems that is inclusive of LMMAs; (iv) harmonizing MPA policy with fisheries, environment and iTaukei management (including protection/restoration of livelihoods); (v) establishing clear distinction between MPAs and LMMAs that lie within in-shore areas; (vi) defining mechanisms for integration of MPA implementation plan into the policies and work plans of key sectors and coordinating mechanisms; (vii) development of criteria/guidance for establishing MPAs and LMMAs within in-shore and off-shore areas and institutional arrangements; and (viii) coordination of community interventions within LMMAs to avoid scattered and fragmented actions;

1.1.7.	Finalization and approval of MPA policy and implementation plan; and

1.1.8.	Promote partnership arrangements for linking Fijian’s network of MPAs to regional and global networks, in particular to identify and strengthen collaborative partnerships with other Pacific Island countries and regional networks for wider protection of species and habitat; and sharing of best practices with the international community on tools, techniques and approaches to achieving global marine protected area commitments.

- The project will provide technical support, consultation workshops, dissemination and travel costs to facilitate the development of the national policy and implementation plan for MPAs that builds on the current ten-step process under the MACBIO Project that is being used to assess options for creation of a network of MPAs in the country.

Output 1.2	FLMMA Strategic Plan updated to strengthen multi-sectoral coordination

- FLMMA’s 2014-2018 Strategic Plan presents a vision for achieving a network of vibrant, resilient and empowered communities throughout Fiji to establish a durable system of contiguous LMMAs covering the entirety of Fiji’s inshore fishing area. The FLMMA Strategic Plan recognizes that the creation of a network of contiguous LMMAs will enhance coastal protection from increased storm events and provide enhanced reef resilience to the detrimental effects of climate change. They will also serve to protect Fiji’s marine biodiversity and ensure the long-term viability of Fiji’s vital tourism industry. The Community-Based Adaptive Management approach promoted by the Strategic Plan promotes sustainable use of coastal fisheries resources, the protection of ecosystems and vulnerable species and an increased capacity to manage and adapt to threats.  FLMMA has grown rapidly since its establishment and as of the beginning of the current Strategic Plan Period, FLMMA has established 466 no-take zones (or tabu areas) in 135 iQoliqoli covering 79% of Fiji’s inshore fishery area. Given the experiences and growth in LMMAs over the past five-year period, an updated FLMMA Strategic Plan would help strengthen the use of community-based adaptive management (CBAM) to promote a ridge-to-reef integrated management approach to LMMAs.  It would facilitate the promotion and improved integration of the four FLMMA principles of governance, conservation of biodiversity, socio-economic and spiritual development of the community.  It would help adjust current fisheries management in LMMAs to better address poaching, waste management, sustainable fisheries management and enhance training opportunities that promote integrated management of LMMAs. To facilitate the development of FLMMA’s Strategic Plan (2020-2024), the project will support the following indicative activities:

    - Recruitment of a national consultant to facilitate and coordinate the development of FLMMA’s Strategic Plan (2020-2024);

    - The national consultant coordinates and facilitates consultations (with support from FLMMA Executive Committee) with key stakeholders to assess gaps and opportunities for updating FLMMA current Strategic Plan (2014-2018) based on lessons and experiences of current strategic plan period, and evolving international and regional experiences on planning and management of MPAs and local community marine conservation practices;

    - Conduct of regional and national workshops to build consensus and agreement on strategic approaches for management of LMMAs to ensure ecosystem-based ridge-to-reef approaches that integrates sustainable energy, climate adaptation, income generation, food security, biodiversity conservation and ecosystem and community well-being;

    - Formal agreement between the Protected Area Committee (PAC) Marine Working Group of the Ministry of Environment and Waterways (MOEW), Marine Protected Area Technical Working Group of the Ministry of Fisheries and FLMMA Network on coordination of work plans and programs;

    - FLMMA Network will actively engage with national and provincial governments and NGOs to seek opportunities for integration of LMMA activities within existing programs, plans and budgetary exercises;

    - FLMMA Network and associated NGO partners facilitate identification of new LMMAs and initiation of planning for integrated approaches in LMMAs outside Sothern Lau; and

    - Drafting, approval and dissemination of FLMMA Strategic Plan.

- The project will provide technical consultant support and meeting, workshop, consultations and travel costs associated with the preparation and dissemination of FLMMA’s Strategic Plan (2020-2024).

Output 1.3: New enhanced model LMMA management guidelines and tools that incorporate ecosystem-based ridge-to-reef approaches to LMMA planning and management adopted

- Under this output, the Project will support the preparation of procedures, guidelines and standards to enable and create the conditions to effectively promote the development, planning and implementation of ecosystem-based approaches to the management of LMMAs. Specifically, under this Output, the project will prepare an updated version of the Locally Managed Marine Areas: A guide to supporting community-based adaptive management. This will provide an operational toolkit (or manual) for LMMAs with a focus on management through an ecosystem, resilience-based and integrated ridge-to-reef approach.  The updated operational toolkit/manual will be developed based on lessons learned within and outside of Fiji that can serve as an important means to promote and replicate successful ecosystem-based models of community managed marine resources.  The operational LMMA toolkit/manual will be designed through the following indicative activities:

1.3.1	Hiring of a national consultant to coordinate and facilitate the development of the updated operational manual for LMMAs;

1.3.2.	Consultations to identify key gaps within existing guidelines for identification, establishment, planning, management and enforcement of LMMAs;

1.3.3.	Based on findings of 1.3.2, consultations to enable decisions on strengthened approaches for community-based adaptive management of LMMAs, including in particular the identification, establishment, planning, management and enforcement of LMMAs;

1.3.4.	Based on 1.3.3, the development of step by step guidelines for (i) identification of new LMMAs and their establishment, (ii) zoning and demarcation of LMMA boundaries, (iii) stakeholder assessment and consultations including pursuance and securing FPIC in accordance with the Ministry of iTaukei Affairs (MTA) FPIC Framework; (iv) improved decentralized provincial governance and role of Yaubula Management Support Teams (YMSTs); (v) formation and/or strengthening LMMA committees at each YMST level, (vi) defining roles and responsibilities of different stakeholders in LMMA planning and management; (vii) LMMA planning processes (from village to district to cluster to provincial levels; (viii) design and implementation of different LMMA models (top-down to bottom-up); (ix) Assessment of potential livelihoods impacts and economic displacement associated with LMMA establishment and a standard framework for addressing/managing livelihoods risks including restoration of livelihoods (responding to risks identified in SESP, Annex 5); (x) coordination of land and sea-based planning processes; (xi) implementation of LMMA plans, roles and responsibilities; and (xii) monitoring of LMMA plans and impacts and feedback and adjustment, including improved application of FLMMA LMMA certification program etc.;

1.3.5.	Development and approval of updated community-based adaptive management operational manual; and

1.3.6.	Translation and dissemination of updated operational manual and training for its application.

- The project will provide technical support, consultation workshops, travel, printing and dissemination costs.

Output 1.4: National and provincial agencies capacitated and better able to support MPA/LMMA establishment, management and enforcement

- The GEF increment will support validation of the training needs assessment carried out during the PPG stage and develop and implement a training program at national and provincial level to strengthen the capacity of national and provincial government agencies and non-government agencies and local administrators in MPA/LMMA ridge-to-reef planning and management, enforcement, monitoring and environmental impact assessment. Similarly members of private sector groups (fisheries, tourism, maritime agencies, etc.) will benefit from the program, including the development of skills for the management and sustainable use of marine resources and the reduction of threats on these resources. Training modules and materials will be designed and around 100 national and provincial staff trained by the end of the project through workshops, seminars and field visits to MPAs and LMMAs. The impact of the training will be assessed through interviews and follow-up in the field and assessed through the application of the UNDP Capacity Development Scorecard (Annex 14)at mid-term and end-of-project. The indicative activities to be supported under the output are:

1.4.1	Validation of capacity needs assessment undertaken at PPG stage;

1.4.2.	Identification of capacity and skills training needs and key topics for training.  This in particular, might include (but not restricted to): (i) benefits of ecosystem management versus fisheries management approach; (ii) enhancing governance mechanisms (including role of YMSTs) at different planning levels, (iii) fundamentals of adaptive management; (iv) principles of LMMA planning and integration with land-based activities; (v) strategic choices for integration of biodiversity considerations into their planning and budgeting processes; (vi) demonstrating specific business cases for biodiversity conservation within marine environments; (vii) Application of UNDP safeguards standards including gender mainstreaming, livelihoods impacts and obtaining FPIC; (viii) measurement of LMMA certification effectiveness, etc.; to enable replication outside the Southern Lau area;

1.4.3.	Development of training curriculum and materials (FLMMA);

1.4.4.	Roll out of management training in a trainer development format for national and provincial institutions and non-government institutions covering the topics listed in 1.5.2 and other topics derived from the capacity needs assessment;

1.4.5.	Evaluating the effectiveness of the training programs and its adjustment; and

1.4.6.	Promoting the integration of the training activities within one or more training institutions within the country to ensure its institutionalization.

- To support this process, the project will provide a full-time national project coordinator, national and provincial capacity and skills training and consumables, supplies, travel and operating costs for the duration of the project.

Component 2: Enhanced provincial LMMA network balancing resource use and biodiversity conservation

Total Cost: US$ 2,530,470; GEF project grant requested: US$ 455,800; Co-financing: US$ 2,074,670

Outcome 2: Improved management effectiveness of LMMAs in Southern Lau seascape

Baseline conditions (without GEF project):

- In the absence of GEF funding, the management of existing LMMAs will continue at a basic level with focus on fisheries production rather than on managing these areas to achieve conservation objectives in parallel with resource utilization.  As a consequence, little emphasis would be placed on management for conservation of global biodiversity, migration routes and spawning and feeding grounds of marine species. Technical capacity and resources for LMMA establishment, planning and management will remain low and unable to keep up with community interest in establishing LMMAs.  Provincial government extension staff (forestry, fisheries and agriculture) and conservation officers, fish and forest wardens and community members would remain less informed and have skills to support ecosystem-based LMMA planning and management. Where LMMAs already exist, the awareness of linkages between land and sea-based planning would be limited resulting in poor soil management practices, discharge of domestic and industrial wastes and solid and nutrient runoff that could have negative impacts on sensitive marine habitats and their attendant biodiversity and ecosystem functions. Unsustainable fishing practices are also likely to continue and coordination of land and seascape planning will not be function at a basic level, leading to inconsistent management of LMMAs and management from a site-based perspective rather than ecosystem or ridge-to-reef level.

Alternative (with GEF project):

- Building on the foundational activities under Component 1, the GEF increment will address the challenge of inconsistent management effectiveness and the barrier of low capacity at provincial and local levels in management of LMMAs. It will take place in Lau Province, an area recognized by the Government of Fiji and local Chiefs as the location for an integrated network of co-managed terrestrial and marine protected areas by 2025. It will support LMMAs to form a central component of this integrated framework through strengthening the provincial management model, enhanced management planning that explicitly considers biodiversity conservation, improving community monitoring of LMMA resources including key ecological and livelihood indicators, and providing training in resource use, LMMA management and conservation. On-ground activities supported by GEF funds will be focused on in the South Lau ‘seascape’ – an area that has global biodiversity significance (see Annex 12) and is currently under-represented in the LMMA network.

- To support the transition from site-based to ecosystem-based LMMA management, the project will enhance and capacitate provincial Yaubula Management Support Teams (YMSTs) in Lau Province at the village, island (district), cluster and provincial levels through technical and management support to these community-based governance structures, including for work planning and integration of YMST activities within village integrated development plans, and delivery of communications and outreach. The project will work in two island clusters (Ono-i-Lau islands and the Vulaga Islands clusters) that constitute the Southern Lau seascape, covering 4 districts and 17 villages. With strengthened YMST governance, the project will support the establishment of 13 new LMMAs and strengthen management planning for 7 existing LMMAs across through enhanced protection (IUCN VI) LMMA management plans that integrate biodiversity considerations and strengthen co-management arrangements with iQoliqoli resource owners through support for coordinated implementation of Ridge to Reef actions across each island. In accordance with the government target for all iQoliqoli to become LMMAs by 2025, the full iQoliqoli area of South Lau will be targeted for LMMA establishment (and enhanced management where LMMAs already exist). Targeted training in LMMA management will be rolled out across South Lau to enhance the understanding of management rules and customary enforcement measures, and broaden skills in ecosystem management techniques and restoration techniques.  This Outcome will be achieved through four Outputs.

Output 2.1 Decentralized provincial governance model and Yaubula Management Support Committees operationalized, providing support to LMMA sites across Lau Province.

- The GEF increment will strengthen the capacity of YMSTs to facilitate planning, management, enforcement and monitoring functions at the village, island, cluster and provincial levels.  At the village level, YMSTs will facilitate the preparation of LMMA plans through support for improving consultations with local village communities, provision of outreach and technical support for LMMA planning and implementation.  They also facilitate monitoring effectiveness of LMMA plan implementation and conservation and sustainable resource use outcomes and impacts.  At the island level, the YMSTs will facilitate the integration of land and sector-based planning processes with LMMA planning to ensure that development plans take consideration of land-based impacts on marine ecosystems.  At the cluster level, YMSTs will facilitate training and export of best practices and lessons from the village to the cluster level through its fisheries and forestry extension officers.  At the provincial level, YMSTs will develop and provide the tools and training of staff and resource persons for replication and scaling up of LMMA planning and management approaches, as well as strengthen governance and integration role of YMSTs.  The project will also help strengthen the participation of the provincial sectoral staff in LMMA planning and implementation, improve extension and technical support to LMMAs and help coordinate land and marine based activities at the village, island and provincial levels. This Output will support the following key indicative activities:

2.1.1.	Support the formation of YMSTs where they do not currently exist to support the establishment of new LMMAs where these are absent (in full accordance with MITA FPIC framework) and strengthening of existing LMMAs;

2.1.2.	Strengthen the role of YMSTs in ecosystem-based approaches to LMMA planning and management through preparation of LMMA Operational Manual that defines step-by-step guidelines for LMMA identification, establishment, planning, management and monitoring (covered in Output 1.3);

2.1.3.	Conduct training and skills development programs to improve understanding and application of ecosystem and resilience-based approach, co-management to LMMA planning and management that integrates a ridge-to-reef approach (as defined by LMMA Operational Manual), and application of safeguards including gender mainstreaming, FPIC and livelihoods restoration and actions;

2.1.4.	Provide technical support, equipment, transport facilities and limited operating costs to improve role of YMSTs in planning, management, enforcement and monitoring of LMMAs, including integration of LMMA activities within village development plans and across the individual islands on the basis of ridge-to reef planning approach; and

2.1.5.	Delivery of communication and outreach to facilitate YMSTs role in LMMA planning, management and monitoring (covered in Output 3.1).

Output 2.2 Enhanced ecosystem and resilience-based LMMA management plans developed and implemented for new and existing LMMAs integrating traditional natural resource use with conservation of ecosystems and habitats in a ridge to reef approach

- The intent of this Output is to facilitate the creation of new LMMAs and strengthening of existing LMMAs in two clusters in the Southern Lau seascape. With strengthened YMST governance, the project will support the establishment of 13 new LMMAs covering 48,000 ha and strengthen management planning for 7 existing LMMAs covering 22,000 ha and enhance conservation and livelihoods outcomes for around 1,900 inhabitants. This would entail the development and implementation of enhanced protection (IUCN VI) LMMA management plans for 20 LMMAs that integrate biodiversity considerations and strengthen co-management arrangements with iQoliqoli resource owners. Where current management plans exist, they will be revised and strengthened to incorporate marine conservation objectives and ecological monitoring. To the extent feasible, management actions across the land and seascape will be integrated. The specific activities to be carried out under this Output include:

2.2.1.	Assess the effectiveness of management of existing LMMAs within the Southern Lau seascape, including in particular the conduct of adaptive management planning consultations and workshops at the village level to assess current dependencies on fisheries resources, harvest techniques and volumes, resource status and land based and other related problems, and community constraints to effective management of these LMMAs;

2.2.2.	Consultations with local communities to assess their interest in creation of LMMAs and community management priorities for these new LMMAs (consent obtained in accordance with Ministry of iTaukei Affairs FPIC framework) and completion of initial KAP surveys (designed under Output 3.2, Activity 3.2.2.) for each LMMA as part of the consultation process;

2.2.3.	Training, awareness creation and mobilization of local communities to enable formation of new LMMAs and strengthening management of existing LMMAs;

2.2.4.	Support the preparation of LMMA plans for new LMMAs covering 48,000 hectares and revise management plans for existing LMMAs covering 22,000 hectares that build approaches for promotion of land and seascape planning and management, including due consideration of potential social and environmental risks arising through LMMA establishment and enhanced management;

2.2.5.	Provide technical support, capacity development and investment support for implementation of LMMA plans (staggered through the four years of the project) (also see Output 2.4);

2.2.6.		Train and support participatory monitoring of LMMA plans and outcomes, including institutional, ecological (productivity, status of species and ecosystems, etc.), social aspects (incomes and livelihoods) and cultural aspects;

2.2.8.	Capacity building and awareness creation for implementation of FLMMA’s membership certification program for LMMAs to establish management status that will feed into the national MPA reporting system; and

2.2.10.	Support for a full-time field technical officer to facilitate and oversee the planning and implementation of LMMA activities and help coordination with YMSTs and sector entities.

- The project will provide technical assistance, training, equipment and financial resources to support implementation of the LMMA plans (also see Output 2.4).

Output 2.3	 Provincial extension staff (forestry, fisheries and agriculture) and conservation officers, community fish and forest wardens and community members capacitated and equipped to support LMMA management, monitoring and enforcement

- Targeted training in LMMA management will be rolled out across South Lau to about 100 staff and community members to enhance the understanding of management rules and customary enforcement measures, and broaden skills in ecosystem management techniques and restoration techniques such as Crown of Thorns starfish removal and replanting corals on degraded/dynamited reefs. Training will be focused on the FLMMA Field Technical Officer, Ministry of iTaukei Affairs Conservation Officers and government staff who play a central role in extension, along with YMSTs, provincial fisheries and environment enforcement officers, voluntary community Fish Wardens, and community focal points that can act as champions at a village level. Necessary equipment to support enforcement and monitoring efforts (e.g. canoes, cameras, drones and motor and parts replacement kits, etc.) will be provided. Training and other related expenses are included in the project to support enforcement based on the findings of the surveillance and monitoring efforts. Enforcement activities will happen in parallel with LMMA planning, investments in livelihoods support and ecological restoration under Output 2.4 and linked to specific collective community response actions in terms of monitoring and surveillance findings. Training will also be provided for the FLMMA community-based monitoring system and iQoliqoli resource owners supported to complete the monitoring at LMMA sites. Site-based monitoring will be designed to connect with the enhanced M&E system for MPA reporting established under Output 3.2 and pilot any new approaches developed. Under this Output, the project will support the following indicative activities:

2.3.1.	At the district/cluster level training of local extension staff on YMST governance, management effectiveness monitoring, LMMA planning, ridge-to-reef approach, integrated sustainable fisheries management, zoning practices, monitoring health of ecosystems, integration of conservation outcomes in local planning, screening of LMMA investments, etc.;

2.3.2.	Conduct of community training programs that focus on techniques on baseline survey and monitoring of ecosystem status methodology, conservation planning at LMMA level, climate change impact assessments and adaptation techniques, eco-friendly and sustainable livelihoods, empowerment training, improved harvesting and sustainable techniques, local governance, etc.;

2.3.3.	Train provincial staff in screening processes, tools, guidelines and protocols for integration of biodiversity conservation outcomes, enhancing habitat integrity and management of threats into district and local planning systems, application of safeguards including gender mainstreaming, FPIC and livelihoods restoration;

2.3.4.	Develop new tools and techniques to improve enforcement, including provision of drones to monitor LMMAs, improve enforcement capacity of fish and forestry wardens and improve fish harvest techniques and methods that are more sustainable;

2.3.5.	Support capacity building for undertaking site specific environmental assessments to determine impacts and mitigation of land and sea-based activities on MPA/LMMA ecosystems; and

2.3.5.	Participation of provincial and district staff and community leaders in LMMA planning, implementation and monitoring.

Output 2.4	 Effective community co-management and implementation of LMMA management plans achieving livelihoods improvement, threat reduction, and long-term sustainability of LMMAs

- Community engagement and participation is pivotal for the effective implementation of LMMA management plans, the reduction of threats to biodiversity and the enhancement of local livelihoods. Further, LMMA management plans could introduce management rules that change local community access to marine resources including through establishment of no-take tabu zones. This changed access could result in economic displacement impacts on local communities. Supporting the restoration of these livelihoods is a key part of UNDP safeguards policy and has been built into the design of this project.

- The project will support the implementation of LMMA management plans and livelihoods through the development and deployment of community grants. Based on the ridge-to-reef LMMA planning process, the GEF increment will support activities in each LMMA area and its land-based surroundings for: (i) improved ecosystem-based management of LMMAs; (ii) sustainable fisheries management approaches through appropriate community-management and ecologically-friendly practices; (iii) improved management of upland, coastal, forest and agricultural practices to reduce land-based impacts on marine ecosystems and productivity; and (iv) biodiversity-friendly livelihood and business enterprise development programs, to diversify incomes and improve farm, non-farm and marine productivity. As the project envisages a fully participatory process, project investments are not defined at this juncture, but would evolve during the LMMA planning process (Output 2.2) based on community needs and priorities. Some examples of potential community investments are provided in Table 1.

Table 1: Potential menu of community activities

| Investment Category | Potential Activities |
| --- | --- |
| Marine and Coastal | Mariculture, seaweed farming, giant clam harvest and sea cucumber restocking, mangrove restoration, mud crab farming, sea cucumber and clam farming, pearl farming, fish and prawn farms, etc. |
| Land based activities | Upland forest and land rehabilitation, organic farming, improved agricultural productivity, vegetable farms, Yagona farming, etc. |
| Livelihood | Beekeeping, virgin coconut oil, weaving, crafting, farming, virgin coconut oil production, poultry, sandalwood nurseries, indigenous plant nurseries, local handicrafts (tapa, tanoa/kawa bowls, household decorative ornaments, mats, etc.), small businesses, etc. |

- Grant financing for the LMMA plan investments would be performance-based and designed by ensuring transparency and extensive consultations with the YMSTs and other relevant stakeholders. Grants will be a typical cash for work payments based on the following principles: (i) competitive assessment to select community institutions/beneficiaries; (ii) selection of beneficiaries in accordance with transparent criteria (to be defined early in the project); (iii) upfront payment (percentage of payment to be defined in consultation with stakeholders); and (iv) balance payment on successful completion and verification of work. Based on accountability and transparency principles, grants will be disbursed to LMMA communities based on the following principles: (i) LMMA communities will establish an LMMA executive committee and open a bank account for the receipt of project funding, if not already existing; (ii) the LMMA committee will have established YMST that is directly accountable for the delivery of proposed project activities and production of regular financial statements of expenditure; and (iii) grants to the individual LMMA communities will be in at least 2-3 tranches based on LMMA plans, budget estimates, activities and projected milestones aligned to agreed LMMA plans. While, the LMMA plan investments will be supported under the project, complementary financing will be also sought through provincial, sector and NGO programs to ensure broader financial support and long-term commitment to improving the economic well-being of local communities. The convergence of government resources to support LMMA activities will be sought through the support of Provincial governments and by co-opting YMSTs into LMMA planning and implementation.

- The long-term sustainability of LMMAs will be supported by the identification of sustainable institutional, financing and revenue generation incentives that generate enhanced support for LMMAs. There are currently legal, regulatory and policy constraints to promotion of financing options through tourism such as landing/user fees in Southern Lau. These include regulations relating to tourist access to the islands, security concerns, biosecurity and government control on charging user/landing fees. Additionally there is a lack of incentives for developing tourism because of the remoteness of the islands. This Output will support an initial analysis to understand the constraints to promotion of tourism and how these can be addressed. Following the analysis, the intent is to identify sustainable institutional and financing options in tourism that can be piloted in the Southern Lau seascape. Lessons learned from related activities under the GEF-5 Ridge to Reef Project in Fiji will be used to inform the feasibility assessment and subsequent pilots.

- The project will also evaluate and support the establishment of revolving community funds to support ongoing implementation of LMMA management plans developed by the communities. FLMMA will work towards improving the capacity of local communities to manage such revolving funds, establish governance structures and fund management. FLMMA will also help in facilitating linkages with rural banks and microfinance institutions. This output will support the following indicative activities:

2.4.1.	Develop and roll-out community grants to support LMMA management plan implementation and strengthen livelihoods, sustainable resource use and harvest, value addition and alternative income activities (see Table 1);

2.4.2  Support a feasibility study to assess potential options for ensuring sustainable financing incentives for local community participation in LMMAs. The study will analyze legal and policy barriers to promotion of tourism and other incentives in Southern Lau and options for overcoming them;

2.4.3.	Evaluate the feasibility of establishment of community revolving funds (based on agreed voluntary contributions from community members and non-GEF related funding sources) that will help to financially sustain and expand investments beyond the project period (refer Section V, “Sustainability and Scaling up”);

2.4.4.	Based on the feasibility studies, pilot suitable financial mechanisms in targeted LMMAs;

2.4.5.	Develop a sustainability strategy in the second half of the project based on lessons learned at the field level that will ensure sustainability of outcomes and support upscaling of the ecosystem-based ridge-to-reef planning approach and models tested in Southern Lau; and

2.4.6. Convene FLMMA Annual seminars to cover LMMA-related issues and practices for decision makers and practitioners in Southern Lau.

Component 3: Project learning, knowledge sharing, communication, gender mainstreaming and M&E

Total Cost: US$ 510,000; GEF project grant requested: US$ 102,000; Co-financing: US$ 408,000

Outcome 3:  Lessons learned through knowledge management, monitoring and evaluation, and gender mainstreaming are available to support the implementation of MPAs/LMMAs nationally and internationally.

Baseline conditions (without GEF project)

- While there is strong awareness and interest in LMMAs at local level, yet this is largely likely to continue to be based on food security and customary benefits, rather than on biological or ecosystem considerations. There will still remain limited awareness of potential LMMA biodiversity benefits and the importance of retaining biodiversity values and there will continue to be less support for management of LMMAs for marine biodiversity conservation. Sustainable fishing and conservation benefits of LMMAs will continue to emerge very slowly and monitoring data on ecological status and trends will likely remain weak. Capacity for monitoring the effectiveness of LMMAs at securing resource protection, livelihood and conservation benefits will continue to be low inhibiting options for taking into consideration the economic, cultural and environmental contributions of LMMAs. In addition, gender and other inequities will continue to exist in terms of gaps in information sharing, knowledge, and attitudes in the country. Traditional knowledge while it exist, will likely continue to be guarded and segregated by gender, and while there is effort at sharing knowledge using a modern system of schooling, public media, and traditional face-to-face methods, this is likely to continue to advance at its own slow pace. Significant gaps in understanding of marine habitats, both at the institutional level and at the community level will continue to exist, and impacts of poor exploitation practices, will remain poorly understood. Management of marine-based data will continue to be limited. Without the GEF increment, communications will modernize only slowly and while much information is generated through “projects”, this information is likely to continue to be compartmentalized and not widely shared outside of the close circle of project implementers. Gender inequality relating to knowledge and attitude will continue as many national capacity building and information management efforts in the past decade have focused on monitoring, enforcement, field-work, and these mostly involved men. There will continue to be the lack of gender-disaggregated data, which would make it difficult to evaluate and plan for gender-based improvements. Thus, problems relating to degradation of marine habitats from non-sustainable fisheries and land-based practices will continue without the GEF’s investment in communications.

Alternative (with GEF project):

- Knowledge sharing and dissemination will ensure that project benefits will be expanded nationally and regionally, including through linkages with other South Pacific initiatives as well as shared through GEF’s IW:LEARN and IW:Science. The development of a knowledge management and communication plan is intended to promote meaningful stakeholder awareness, understanding and participation in biodiversity conservation, sustainable marine resource use and alternative livelihood as well as document, disseminate and scale up successful lessons and best practices in marine resource conservation more widely in the country and beyond. This will be accomplished through awareness campaigns, and creation and maintenance of an online public access database and documentation repository. The GEF alternative will enable a gender-equity perspective and analysis of the way that information is prioritized, collected, shared, communicated, and used within the realms of LMMA planning, tourism development, and biodiversity conservation and management, according to the Gender Analysis and Mainstreaming Action Plan (Annex 7). A national awards scheme for LMMA management will be established to recognize communities that excel in conservation of the marine environment and GEF funds will be used to develop an awards scheme that will be held in parallel with the existing annual ‘lessons learned’ meeting coordinated by the FLMMA Network. This Component will be supported by three Outputs:

Output 3.1	 Coordinated institutional approach and protocols for gathering and collating information on MPAs/LMMAs and their management effectiveness

- Under this Output, FLMMA’s information system and knowledge management platform will be strengthened to enable that monitored data is recorded and analyzed for the stakeholders to enhance LMMA planning and management.  The intent is to operationalize and test the FLMMA system in Southern Lau, including for standardizing data collection, input and dissemination so that it can become an effective system that can be applied nationally.  It will enable the sharing of information, management experiences and best practices and later be developed to enable different stakeholders to input and use this system to meet their own requirements. The platform will focus on standardized reporting, inputting and recording of information on critical marine habitats and globally threatened species (status and trends), community management and reporting of LMMA activities that ensure standards are gender and socially inclusive, and ensuring that FLMMA certification standards are highly accessible, usable, and applied uniformly across the country. In addition to this, a public participatory information system to support biodiversity conservation will be established as a platform through the FLMMA network. This will promote and enable the public to report sightings, illegal activities, accidents, by-catches or stranding of marine mammals, etc.

3.1.1.	Recruitment of a national consultant to work to strengthen FLMMA’s information management systems to improve LMMA data management and information sharing. In addition, knowledge products, lessons learned and other project information will also be shared on the system;

3.1.2.	FLMMA Secretariat will establish a small Technical Advisory Committee to advise and guide the national consultant on the upgrade of FLMMA information management system;

3.1.3.	Upgraded information management system will be tested in the Southern Lau seascape;

3.1.4.	Review the use of the upgraded information management system in Year 3 and improve and modify accordingly;

3.1.5.	Following successful testing of the upgraded information management system, expand its use to LMMAs nationally enabling standardized reporting, inputting and recording of information, ensuring standards are gender and socially inclusive, and ensuring that FLMMA certification standards are highly accessible, usable, and applied uniformly across the country; and

3.1.6.	Through a linked public participatory information system, facilitate public (other NGOs, Research Institutions and interested individuals) contribution of data related to sightings of species, illegal activities, best practices, etc.

Output 3.2	Knowledge management, awareness, outreach and communication strategies developed and implemented

- A knowledge management and communication plan will be developed at the beginning of the project (based on Annex 13 - Knowledge Management and Communication Strategy) to achieve the overall goal of creating linkages between the stakeholders from the local, district, provincial and national level, for information, exchange of ideas and implementation of community-based marine conservation and sustainable fisheries and tourism activities. The intent is also to build awareness and generate support amongst policy makers, sector agencies, provincial and local entities and local communities for the conservation of the LMMAs and it’s associated species and marine ecosystems and reduce threats. The knowledge management, outreach and communication plan is intended to ensure that: (i) the project is well understood, accepted, and implemented effectively and equitably; (ii) knowledge and lessons learned from the implementation process of this project are captured, documented and used to improve current and future project practices; (iii) understanding of LMMA planning and management is increased; (iv) knowledge management products are disseminated and used; and (v) local communities have increased awareness of biodiversity conservation and threats to marine resources. In addition, it will help identify promising and good practice ecosystem-based and adaptive mechanism relevant to marine conservation approaches, sustainable fisheries and tourism and help document and disseminate results of best practices to enable up-scaling to other LMMAs in the country and region through the community of practice that the FLMMA Network (and the broader LMMA network) provides. The indicative activities include:

3.2.1.	FLMMA Secretariat reviews existing knowledge management, outreach and communication practices employed in LMMA sites and assess weakness, gaps and measures for strengthening;

3.2.2.	Based on 3.2.1, national consultant to design KAP survey and develop Knowledge Management, Outreach and Communication plan for the project area to ensure regular communication with local stakeholders, and update annually; that (i) the project is well understood, accepted, and implemented effectively and equitably; (ii) knowledge and lessons learned from the implementation process of this project are captured, documented and used to improve current and future project practices; (iii) understanding of LMMA planning and management is increased; (iv) knowledge management products are disseminated and used; and (v) local communities have increased awareness of biodiversity conservation and threats to marine resources.

3.2.3.	Design and implement awareness and outreach programs at community level and at school and educational facilities;

3.2.4.	Prepare at least ten knowledge management products (e.g. best practice notes, videos, posters, brochures, etc.) related to LMMA management;

3.2.5.	Participate in national environmental-related workshops and meeting (and in particular events organized by the national and provincial FLMMA network) to disseminate lessons and experiences of the project to facilitate replication;

3.2.6.	Design and support award and recognition scheme for local action to conserve and sustainably use marine resources, including specific recognition of women in LMMA conservation;

3.2.7	Facilitate dialogue with provincial authorities and other stakeholders in other areas interested in replicating best practices for establishing and managing new and existing LMMAs; and

3.2.8.	Convene	 FLMMA Network national seminar on project outcomes.

Output 3.3	  Gender mainstreaming, safeguards and Monitoring and Evaluation strategies developed and implemented

- Success of the project will be measured through the project’s own Results Framework. Monitoring and evaluation activities will include the regular review and updating of the M&E plan (see Section VII) with indicators, baselines and targets, annual work plans and budgets and the generation of comprehensive monitoring and progress reports. The project will ensure that gender mainstreaming and SESP requirements (Annex 5) are met as an integral part of the project planning, implementation and M&E cycle. The implementation of the gender action plan (Annex 7) is to ensure that a gender and socially inclusive perspective is applied to every set of activities; (ii) awareness on gender and social roles in MPAs/LMMAs informs resulting plans and ensures equitable distribution of benefits; and (iii) information is collected and shared across gender and social divides. Regular Project Steering Committee meetings will enable key stakeholders to be actively involved in a participatory M&E process. Additionally, the project will conduct annual project implementation reviews, and an independent mid-term review and final terminal evaluation to assess progress and achievements, emerging constraints and (at mid-term stage) to formulate possible adaptive management to ensure optimal implementation success. Indicative activities under Output 3.3 include:

3.3.1.	Implementation of gender mainstreaming action plan and evaluating and updating regularly;

3.3.2.	Train FLMMA and YMST staff on gender mainstreaming in LMMA planning and management to enhance the role of women in local decision-making processes, particularly in relation to fisheries and livelihood activities in the LMMAs;

3.3.3.	Regularly evaluate potential social and environmental risks associated with the project, as detailed in the SESP, Annex 5, and ensure appropriate assessment and management measures are defined and implemented in accordance with UNDP policy. Particular attention will be placed on potential livelihood impacts related to Standard 5 on displacement and Standard 6 on indigenous peoples including securing FPIC in accordance with the Ministry of iTaukei Affairs FPIC Framework;

3.3.4. Review and update M&E plan including Results Framework baselines during project inception phase, including GEF-6 Biodiversity Tracking Tool, Programs 1-2;

3.3.5.	Use annual work plan preparation (and annual project reviews/PIRs) as key tools for adaptive management of project activities;

3.3.6.	Conduct Mid-term Review and Terminal Evaluation in line with UNDP/GEF requirements, and incorporate recommendations of MTR into revised project plans (management response) following PSC approval, and monitor their implementation; and

3.3.7.	Publish and disseminate project terminal report.

Partnerships:

- FLMMA is part of an international network of natural resource management practitioners working in Asia and the Pacific, who have joined together to share best practices, lessons learned and to amplify their community voices. The Locally-Managed Marine Area Network consist of a group of practitioners involved in various community-based marine conservation projects around the globe, primarily in the Indo-Pacific, who have joined together to learn how to improve our management efforts.  The Network spans the people and cultures of Southeast Asia, Melanesia, Micronesia, Polynesia and the Americas. Working through LMMA, FLMMA will collaborate across the countries to facilitate the five LMMA objectives of (i) learning about the LMMA approach (through systematic and question-driven monitoring and/or other assessment approaches); (ii) protecting biodiversity at specific sites; (iii) promoting the LMMA approach (and lessons from using it) in the Indo-Pacific and globally; (iv) building capacity for learning and implementation of Community-Based Adaptive Management (CBAM); and (v) developing the policy environment at local, regional, country and international levels to support widespread adoption of LMMAs.

- In Fiji, a partnership arrangement has been forged among a number of NGOs for the Lau Seascape Initiative for (i) developing strong partnership and programmatic opportunities participating under the Lau Seascape Initiative; (ii) Contributing to the development of a ten-year strategic vision, resource mobilization plan and implementation plan for Lau Seascape; and (iii) partnering on preparation of funding applications to secure necessary funds for implementation and advancement of the Lau Seascape at site level. Based on the partnership arrangements as forged by the arrangement and reflected in Table 2, individual NGO partners will implement specific activities related to the project.

Table 2: Partnership Arrangements under Lau Seascape Initiative

| Organization | Roles and Responsibilities under Partnership Agreement |
| --- | --- |
| Conservation International | - Preparation of 10-year strategic vision of Lau Seascape - Strategic conservation programming across the Lau Seascape - Development of integrated Lau Seascape Fundraising and Resource mobilization plan - Shared monitoring and evaluation framework, tools and resources to measure success toward implementation of the Lau seascape - Development of specific fund raising applications to support Lau Seascape - Coordination of technical inputs focused on marine science, fisheries management and local scale marine resource assessment - Coordination of shared lessons and best practices |
| Pacific Blue Foundation | - Engagement with community leaders to develop the Lau Seascape Initiative - Co-facilitating the development of projects - Coordination of input for proposal development in marine sciences, observational technologies, open seas fisheries management and local scale marine science resource assessment |
| FLMMA | - Engagement with community leaders to develop the Lau Seascape Initiative - Connecting and ensuring alignment of activities within the broader FLMMA network. - Facilitating implementation of site-based conservation and strategic community development - Improving capacities of existing and new LMMA sites in Lau |
| University of South Pacific (School of Marine Studies) | - Conducting investigation and studies into priority issues related to conserving, developing and utilizing living and non-living resources to provide information for sound decision making - Engaging local graduate students in advancing a range of opportunities for research, education, training and employment in marine sector - Contributing to sustainable use and governance of the natural resources for the advancement, prosperity and development of the people and for the conservation of the rich biodiversity in the Lau Seascape - Preparing people capable of generating scientific data and information for informed decision making for the welfare of the local people and nature |
| Vatuvara Foundation | - Engaging with privately owned island networks to develop management strategies - Building links for sustainable tourism, local community development and environmental protection to share lessons and experiences - Ensuring alignment of activities and support on sustainable resource conservation and management - Mobilizing and implementing site-based conservation, fostering sustainable livelihoods, youth empowerment, marine conservation awareness and sharing lessons and experiences |
| Coral Reef Alliance | - Advocating and promoting effective management of existing MPAs; - Building awareness and community leader capacity to address environmental stresses and risks; - Building understanding and capacity for compliance, surveillance and enforcement - Facilitating implementation of effective, sustainable financing and local livelihoods to improve conservation outcomes |
| Loving Islands | - Coordinating, mobilizing and assisting to implement strategies that are needed to transform Lau islands to organic regenerative land management systems - Engaging with the empowerment of regenerative economic development that is community owned and operated - Building the capacity of communities to generate sustainable income from the sale of organically produced goods to provide sustained economic growth |

- The FLMMA network that includes representation on its Council of governmental and other NGO partners will collaborate in implementation of the project, including in particular with the Women in Fisheries Network of Fiji to ensure that gender considerations are actively integrated into all aspects of the project.

Risks and Assumptions:  The following (Table 3) are key risks and risk management approaches for the project:

Table 3: Risks and Risk Management Responses

| Risks | Rating | Risk Mitigating Measures |
| --- | --- | --- |
| Risk 1: Increasing pressure on the marine environment and natural resources due to poverty, increase in population, urbanization and economic development. | Moderate I – 3 P -2 | The project aims to continue to bring about transformational change in the mindset of the respective communities through raising awareness on the consequences of unsustainable utilization of marine and fisheries resources. At the same time, the participating LMMAs/community will be made aware of best practices (e.g. tabu, fishing gear restrictions etc.) that both conserve and protect the marine environment and help ensure sustainable economic livelihoods. |
| Risk 2: Lack of political support and community buy-in for marine biodiversity conservation and sustainable fisheries management | Low I -2 P -2 | The proposed project fits very well into the Fiji Government’s commitment to have 30% of marine areas conserved by 2020 and its green growth framework and other relevant sector policies on environment/ NBSAP, fisheries and integrated coastal management and climate change, so high level political support is expected. Alignment to government-endorsed Ocean Conference Voluntary Commitments has been a factor in project design, along with mainstreaming of MPA system incorporating LMMAs across government. |
| SESP Risk 1: Establishment and enhanced management (and enforcement) of LMMAs for biodiversity conservation and sustainable marine resources use may potentially restrict availability, quality of and access to resources for indigenous iTaukei Fijians, within iQoloqoli traditional fishing grounds (i.e. economic displacement). (Principle 1, Question 1,2,3 and 4; Principles 3: Standard 5 Question 5.2 and 5.4; and Standard 6, Question 6.1, 6.2, 6.3, 6.4, 6.5, 6.6, 6.9) | Moderate I = 3 P = 2 | As the vast majority of project stakeholders are iTaukei the Project Document will serve as an Indigenous Peoples Plan and the requirements of the UNDP Indigenous Peoples Plan have been integrated into the project design and individual activities. FPIC has been integrated into the project design (e.g. including training of national, provincial and local extension officers in obtaining FPIC) and the stakeholder engagement plan. FPIC will be pursued and secured in accordance with the Ministry of iTaukei Affairs (MITA) FPIC Framework prior to any activities that could affect the rights, lands territories, resources, traditional livelihoods and/or cultural heritage of iQoliqoli rights owners and local communities. In this project establishment of an LMMA will not take place without the consent of iQoliqoli owners. LMMA communities will then plan and manage their iQoliqoli areas on the basis of their priorities, while ensuring the protection of critically endangered marine species and habitats through mutual agreements related to zoning, demarcation of “tabu” areas, sustainable fishing techniques and harvest rates. The LMMA community may choose to adopt resource use restrictions that impact on local livelihoods in the short-term, where restrictions are considered necessary to protect longer-term livelihoods and environmental sustainability. Livelihoods restoration has been integrated into the project design (e.g. Outputs 1.1, 1.2, 1.3, 2.1, 2.2, 2.3, 2.4). Individual LMMA management plans will outline potential livelihoods impacts and livelihoods restoration and will serve as the livelihood action plan for each LMMA. The project will support the implementation of LMMA management plans. The project will also provide parallel livelihoods support for LMMA communities (alongside support to enhance enforcement of LMMA management rules) to ensure long-term sustainability of livelihoods. The establishment and enhanced management of LMMAs will take place in accordance with the Locally-Managed Marine Areas: A guide for practitioners (2008), which emphasizes community participation and autonomy in managing their marine resources and in declaring tabu and/or restrictions on the take of individual marine species. This guide will be revised with project support (Output 1.3) and these revisions will ensure that MTA policies/processes for FPIC and UNDP SES guidelines for Standards 5 and 6 are captured within it. In inception phase the project will establish a Grievance Response Mechanism (GRM) in accordance with national and local context and agreed approaches for managing grievances from iTaukei communities. The GRM will be included within the Stakeholder Engagement Plan (Annex 6) that will be finalized during the inception phase in discussion with project stakeholders. The FLMMA Field Officer will serve as community focal point and will be given training in application of UNDP SES policy and standards. Training for other stakeholders has been integrated into relevant project activities. |
| SESP Risk 2: FPIC may not always be secured as required across all LMMA sites (Principle 3: Standard 6, Question 6.4) | Moderate I = 4 P = 2 | FPIC has been integrated into the project design (e.g. including training of national, provincial and local extension officers) and the stakeholder engagement plan. FPIC will be pursued and secured in accordance with the Ministry of iTaukei Affairs (MITA) FPIC Framework prior to any activities that could affect the rights, lands territories, resources, traditional livelihoods and/or cultural heritage of iQoliqoli rights owners and local communities. In this project establishment of an LMMA will not take place without the consent of iQoliqoli owners. LMMA communities will then plan and manage their iQoliqoli areas on the basis of their priorities and needs, while ensuring the protection of critically endangered marine species and habitats through mutual agreements related to zoning, demarcation of “tabu’ areas, sustainable fishing techniques and harvest rates. |
| SESP Risk 3: LMMAs could set management rules for restricted/altered access to marine resources that could or are perceived to impact on customary rights to access resources of iQoliqoli traditional fishing grounds (i.e. land/resource rights). (Principle 3, Standard 6, Question 6.3, 6.4) | Moderate I = 3 P = 2 | This risk will be managed via the response detailed for Risk 1. The implementation of the Stakeholder Engagement Plan will ensure wide consultation with and engagement of local communities. Awareness raising and outreach will take place across South Lau, including through YMSTs who have a governance role over the islands. Regular review of SESP and adherence to safeguards requirements is integrated under Output 3.3 of the project. |
| SESP Risk 4: LMMA management decisions could restrict or alter traditional and cultural uses of marine resources that could have impacts (positive or negative) on marine sites considered as cultural sites and/or intangible forms of cultural heritage. (Principle 3, Standard 4; Question 4.1; Standard 6, Question 6.9) | Moderate I = 2 P = 2 | This risk will be managed via the response detailed for Risk 1. Potential site-based risks at individual LMMA sites will be identified and considered during the detailed LMMA management planning process that will be conducted with community (Output 2.2) in accordance with standardized protocols and procedures developed under the project (Output 1.3). Regular review of SESP and adherence to safeguards requirements is integrated under Output 3.3 of the project. |
| SESP Risk 5: Although the LMMA process is community owned and driven, there is possibility that not all affected members of the community, including women, will be involved in the process or participate in / give consent for decisions that could change their access to and use of marine resources. (Principle 2, Question 1, 2, and 4; Principle 3, Standard 6, Question 6.3, 6.4) | Moderate I = 3 P = 2 | A gender analysis has been completed during the PPG (Annex 7). On the basis of the gender analysis, a Gender Mainstreaming Action Plan” (Annex 7) was prepared that ensures that women and vulnerable groups would be consulted and involved in the decision-making process. This action plan would facilitate the integration of the rights, concerns and desires of different user groups and communities into the LMMA management plans developed and implemented. A gender and socially inclusive lens will be applied to every project activity and output to further analyze impacts on the rights of women and vulnerable peoples. Special investments would be planned based on women’s requirements to ensure that they adequately benefit from project investments and activities (e.g. Output 2.2). The use of the monitoring Plan (RAF) will validate gender-disaggregated indicators to access gender dimensions The Stakeholder Engagement Plan will ensure that effective consultation with all segments of the population is undertaken including women. The implementation of the Stakeholder Engagement Plan ensures that the Women in Fisheries network will facilitate participation of women in project decisions and investment. FPIC has been integrated into project design will take place in accordance with Ministry of iTaukei Affairs FPIC framework (see also response for Risk 1 and 2). At start-up of the project, the FLMMA Field Officer in collaboration with YMSTs would be trained on participatory processes and techniques that ensure the participation of vulnerable groups including women, elderly, disabled persons, poorest of the poor, and resource poor people in the planning process. Training programs would be conducted to enhance the capacity of women and vulnerable members to take an active part in the planning and decision-making process at the state level. The YMSTs would monitor and ensure that there is adequate representation of women and disadvantaged members in the decision-making and planning process (Output 2.1; Output 3.3). |
| SESP Risk 6: Project activities to ensure conservation and sustainable use of marine biodiversity could have unintended negative consequences on endangered species or critical habitats if not planned or implemented correctly (including insufficient enforcement of LMMA management rules). (Principle 1; Question 5; Principle 3; Standard 1; Questions 1.1, 1.2, 1.3 and 1.7) | Moderate I = 3 P = 2 | The planning process for LMMA management will entail establishing specific rules and regulations for management of tabu areas and building community capacity for enforcement and management of these areas. The project will use community wardens to monitor and enforce at community-based conservation zones within LMMAs. Project activities will include awareness-raising on these management measures to facilitate voluntary compliance and support for LMMAs. Further, Preparation and implementation of the Stakeholder Engagement Plan and Knowledge Management Plan will help promote awareness towards the key features of LMMA from local to national level, for flow of information and exchange of ideas between iQoloqoli owners. Communities will be provided with capacity development and training to support implementation and monitoring of LMMA management plans to enhance compliance and effective enforcement, ultimately ensuring that management plans are implemented correctly. Project activities will train and equip community members to monitor changes in marine biodiversity and fisheries stock and over use of marine resources to ensure community rules are complied with. |
| SESP Risk 7: There might not be full community support for establishment of LMMAs or management rules including tabu areas that could lead to conflict within community or between neighboring iQoloqoli owners. (Principle 1, Question 8; Principle 3, Standard 6, Question 6.3, 6.4) | Moderate I = 3 P = 2 | The LMMA process is community driven and will seek to engage as many members of community as possible (also see gender risk). The project is targeting, in accordance with the government and FLMMA voluntary commitment, to make all iQoliqoli in South Lau LMMAs. Therefore all iQoliqoli communities will be engaged in awareness and understanding of LMMA process, in line with the project design (Outcome 2). Implementation of the Stakeholder Engagement Plan will support community engagement and awareness by ensuring engagement of local stakeholders. The project will implement awareness activities at island-wide level with YMST to build their support and engagement for disseminating information on LMMAs, as well as offering support to address risks and conflicts between neighboring LMMAs. Securing FPIC will help ensure support and minimize conflict. FPIC has been integrated into project design will take place in accordance with Ministry of iTaukei Affairs FPIC framework (see also response for Risk 1 and 2). Targeted training in LMMA/MPA management will be rolled out across South Lau (Output 2.3) to enhance the understanding of management rules and customary enforcement measures. LMMA communities will be trained and equipped to monitor LMMAs and detect any non-compliance with management rules (see also Risk 6 below). The project will scale up networks of locally managed marine areas to island-wide ecosystem management, including through an important partnership with the Government of Fiji/CI ‘Lau Seascape’ initiative. This initiative across Southern Lau has raised broad awareness and support for LMMA among communities which will support the engagement of local communities in this project and respect for LMMA management rules. |
| SESP Risk 8: Climate change and associated threats to marine environments and fisheries resources (e.g. potentially stronger cyclones, changes in rainfall, sea level rise and coral bleaching, ocean acidification) could threaten project impacts in the longer-term. (Principle 3, Standard 2, Question 2.2) | Moderate I = 2 P = 3 | The project design and strategy will help build the resilience of coastal ecosystems and local communities that depend on them to the impacts of climate change. The project will support an integrated ridge-to reef approach to help reduce stresses from water pollution and sedimentation, and control unsustainable use of marine resources, helping to increase the health of ecosystems and their adaptive capacity to cope with climatic changes. Project activities will help build awareness and capacity of local communities to adapt to such threats in the longer term, including through putting in place standardized community monitoring of marine habitats and resources to identify when ecosystems are changing. |

Social and Environmental Screening

- The Social and Environmental Screening Procedure (SESP) was followed during project preparation, as required by the UNDP SESP Guidance Note. Accordingly, the social and environmental sustainability of project activities is in compliance with the SESP for the project (see Annex 5). The SESP identified eight moderate social and environmental risks for this project that would have potential negative impacts in the absence of safeguards. The following safeguards standards have been triggered: Principle 1: Human Rights; Principle 2: Gender Equality and Women’s Empowerment; Standard 1: Biodiversity Conservation, Standard 2: Climate Change Mitigation and Adaptation; Standard 4: Cultural Heritage; Standard 5: Displacement and Resettlement; Standard 6: Indigenous Peoples. The SESP identifies management measures to respond to these risks and these have been integrated into the detailed design of project activities.

- Project design is built on the principle of ensuring that the predominant iTaukei native Fijian’s cultural, social, economic and political characteristics are maintained. The project will ensure free, prior and informed consent (FPIC) is obtained in accordance with UNDP policy and reflecting national processes such as the Ministry of iTaukei Affairs FPIC Framework. FPIC has been incorporated into the project design and the Stakeholder Engagement Plan. Similarly, livelihoods restoration has been incorporated into the detailed design of project Outputs to ensure that the project activities standardize the identification and assessment of potential livelihood impacts associated with the establishment and enhanced management of LMMAs, and management responses including livelihood restoration. For further information on social and environmental aspects and management measures refer UNDP SESP in Annex 5.

- The FLMMA Project Management Unit in consultation with the respective provincial entities will guide the implementation of the SESP and monitor compliance with the environmental and social norms as identified through the screening process. The Project Management Unit will oversee and evaluate the implementation of the management interventions (including zoning, “set-asides” and “no-take” zones) to assess if social and environment screening has been adequate and if any new risks emerge or escalate in impact and probability at any project sites. Implementation of the SESP and safeguards risks will be monitored each year and reported on as part of the PIR. Implementation of social and environmental mitigation measures will also be monitored by the Project Steering Committee and reported annually, including actions taken. Annually supervision missions will assess the extent to which the risks have been identified and managed.

- In line with UNDP standard procedures, the Project will set up and manage a grievance redress mechanism (GRM) as recommended by UNDP (2014) that would address project affected persons’ (PAP) grievances, complaints, and suggestions. The GRM will be managed and regularly monitored by the PMU/FLMMA and oversight of the Project Steering Committee. The grievance mechanism will be finalized during the inception phase and detailed in the final Stakeholder Engagement Plan (Annex 6).

- Overall, the project is expected to result in positive impacts for marine biodiversity conservation and socio-economic benefits through the greater participation of local communities in MPA/LMMA management processes, sustainable use of marine resources and fisheries and sustainable NRM-based livelihood activities.  Specific efforts will be made while evaluating the condition of resources that will be used in livelihood and value addition to ensure that extraction is permissible within sustainable limits. Harvest of fisheries and marine and coastal products that are currently practiced will follow ecologically friendly and sustainable practices. The project will ensure defining specific areas and harvest rates on the basis of good practice criteria backed by scientific information and close monitoring.

Stakeholder Engagement Plan

- The project included a wide range of consultations during the PPG stage. Initial stakeholder analysis during the PIF stage was followed up with consultation during the PPG stage in terms of the design of the project. During the PPG stage, the stakeholder analysis was updated and elaborated following consultations undertaken by international and national consultants with national and provincial governments addressing both institutional stakeholders in the context of their statutory involvement in the project, and more broadly for non-governmental stakeholders including natural resource dependent communities. An Inception workshop was held on July 20 2018 in Suva followed by a two-day residential workshop at Pacific Harbor, Viti Levu with a number of FLMMA Network members to obtain the perspective on key design aspects of the project as well as local, district, provincial and national institutional and coordination arrangements for implementation of the project. A validation workshop was conducted in November 7, 2018 to reach consensus of design aspects of the project. In addition, FLMMA network conducted two consultative workshops in November 2017 and May 2018 with Provincial Chiefs, NGOS and LMMA representatives to define a Lau Seascape Strategy for establishing sustainable development practices and conservation priorities.  Specifically these meetings focused on key target conservation goals for the Lau Seascape and maintaining the health of the traditional fishing grounds (in particular cultural aspects, food security, local livelihoods, conservation of migratory species, management of land-based activities, etc.) as well as to define strategies for threat reduction. Of particular discussion was on approaches to integrate and coordinate among government and governance levels, natural resources conservation, financial capacity building of LMMA communities, maintaining populations of key species, ecosystem restoration, zonation and MPA establishment, community patrolling, and establishment of conservation milestones to 2020 and beyond. The list of stakeholders and proceedings of inception and validation workshops is provided as Annex 14.

- Roles and responsibilities of main stakeholders of the project are summarized in Table 4 below. The detailed Stakeholder Engagement Plan is provided in Annex 6.

Table 4: Stakeholder Involvement Plan

| Key Stakeholder | Role and responsibilities | Role in the project and involvement mechanism |
| --- | --- | --- |
| - Local Communities and Grassroots Organizations |  |  |
| Yaubula Management Steering Teams (YMSTs) in Lau | Oversees the promotion the sustainable development and utilization of natural resources and to improve coordination of natural resources development partners at provincial level and set common complimentary rather than competitive goals | (Outputs 2.1, 2.2, 2.3 and 2.4) YMSTs will be key partners in the project in Southern Lau and facilitate the integration of land and sector based planning processes with LMMA planning to ensure that development plans take consideration of land-based impacts on near–shore and out-shore ecosystems. At the provincial level, YMSTs will develop and provide the tools and training of staff and resource persons for replication and scaling up of LMMA planning and management approaches, as well as strengthen governance and integration role of YMSTs. At the village level, YMSTS will work with local communities to plan and implement ecosystem-based LMMAs, provide technical support and training to village to implement and monitor such plans. YMSTs will also help coordinate all meetings, awareness and training at community, district and provincial levels on integrated ecosystem-based sustainable management of natural resources in Southern Lau groups. |
| Village Council & District Council | Consist of local communities and government representatives. Meets twice in a year to consult and review development activities and issues in their respect district and communities. | (Output 2.2) Will be an important forum for all key elements of the project. Provide knowledge sharing, planning, implementation and monitoring of the project in target district, cluster, islands and communities in Southern Lau. |
| Local Communities and CBOs | Local communities are custodians and primary users of resources in the LMMAs. They are responsible for management and protection of such resources and its sustainable use The local communities are primary beneficiary of project’s intervention. Local communities both male and female will be consulted during the development of the management plans, with focus on issues related to sustainable & integrated natural resources management. Communities shall be mobilized proactively using sustainable livelihood project to release pressure on natural like marine resource. | (Outputs 2.1, 2.2, 2.3 and 2.4) The local communities are primary beneficiary of project’s intervention. They will be key partners, along with the YMSTs for planning and management of marine resources, particularly in the in-shore areas. YMST and Qoliqoli committees that will be formed and strengthened in Southern Lau will directly plan, manage and monitor the resources of the LMMAs. Local communities will participate in project training in relation to resource use and management. Local communities will participate in implementation of conservation, sustainable natural resources and fisheries management and livelihood initiatives. For implementation of activities terms of references (ToR) will be signed LMMA communities and YMSTs. |
| Students/ school children | As part of the community, they are direct beneficiaries of LMMA resources, but also future decision-makers. They are the best agent for change for any sustainable and natural resources stewardship. | (Output 3.2) They can be involved in the formation of nature clubs and nature study camps and global environmental day celebrations to motivate them to play a better role in biodiversity conservation and dissemination of the message to the local communities. |
| - Relevant Provincial & Government departments |  |  |
| Lau Provincial Office (iTaukei Affairs Board) | Administers village, district and provincial activities and supports development activities within the province, coordinates with sectoral agencies (forestry, fisheries, iTaukei, etc.) in provision of extension service. The office responsible for governance and conservation issues in their respective province. | (Outputs 2.1, 2.2, 2.3 and 2.4) Key partner to coordinate and facilitate the preparation of LMMA plans and monitoring. Provide technical and extension support to LMMA communities and promote the integration of land and marine based planning within the districts and provinces. Assist capacity building activities in the village, islands/cluster, district and province and facilitate the sustaining of programs after project period. |
| Lau Provincial Administrator | Responsible for supervising, implementing and monitoring development projects in all islands and communities, as well as ensuring benefits from development projects are received by local communities. | (Outputs 2.1, 2.2 and 2.4) The Provincial Administrator will be responsible to harmonize interventions with the integrated approach and resolve issues between implementing partners, project proponents and communities, if any, during the project implementation. |
| District Development Committees | Management of the administrative matters of the districts and facilitation of the people through public services using integrated approach. Provincial Administrators Chair the District Development Committees (DDCs). The DDCs will be consulted during preparation of management plans, its approval and other relevant project interventions. They will benefit from advice and training and will be able to use data and experiences generated by the project to improve the economic and social component of their District and Provincial Development plans. | (Outputs 2.2 and 2.4) Key partners to facilitate coordination at district and local levels and ensure convergence of programs and resources in Southern Lau. |
| Ministry of Rural and Maritime Development and National Disaster Management (MRMDNDM) | Responsible for providing sustainable socio-economic development and coordination of preparedness and response to natural disasters. Assists in facilitating implementation of coastal and rural development projects with integrated approach. Oversees provincial system of Divisional Commissioners, Planning Officers and District Administrators. | (Output 2.2) Can play an active part in supporting and facilitating preparedness and response to natural disasters for LMMA communities. |
| Ministry of Fisheries | MoF is the lead Government agency and first point of contact for inshore fisheries and offshore areas. It is legally authorized to establish MPAs; cooperates and is a member of FLMMA. Responsible for fisheries policy development and implementing fisheries legislation (Fisheries Act and Offshore Fisheries Management Decree) to regulate sustainability of and management of different fisheries resources, including surveys of all iQoliqoli (both coastal and freshwater). | (Outputs 1.1, 1.2, 2.2, 2.3 and 2.4) MoF will serve on the Project Board. MOF will participate in the preparation of national MPA policy, FLMMA Strategic Plan and as a key member of the FLMMA Network and will actively engage in the preparation of LMMA plans and provide support through its Fisheries Extension Officers and Fish Wardens to LMMA communities to implement their LMMA management plans. Will support LMMA communities to monitor fish species and populations and impacts. It would also facilitate biological surveys, assist to provide baseline data and take lead in fisheries management and conservation training, as well as support the demarcation of MPA and LMMA at iQoliqoli sites and conflict resolution. |
| Ministry of iTaukei Affairs (MiTA) iTaukei Affairs Board (TAB) iTaukei Lands and Fisheries Commission (TLFC) | Responsibilities include the development, maintenance and promoting policies that provide for the continued good governance and wellbeing of the iTaukei. Included in TLFC’s duties are the surveys of the boundaries and registering ownership of customary fishing rights. MiTA and ITAB have the widest coverage and presence in the rural and catchment areas compared to any other government service. They are represented in all villages and districts and are part of the Yaubula Management Institution and Policy Advisory Committees. | (Outputs 1.1, 1.2, 1.3, 2.1, 2.2, 2.3 and 2.4) Will serve on the Project Board. They will be key players in formulation of MPA policy and implementation plan, FLMMA Strategic Plan, preparation of Operational manual and actively contribute and participate in LMMA planning, implementation and enforcement activities and facilitate surveys of the traditional fishing boundaries and registering the ownership of customary fishing rights. They will be engaged in project via Yaubula Management Institution and Policy Advisory Committees. |
| Fiji Police Force & Fiji Navy Force | They are responsible for law enforcement, security and defense of the country and in particular for policing and enforcement of fisheries regulation and policy all over Fiji. | (Output 2.2) Stationed at Lakeba Island where all government departments for Lau Province are located, they will support documenting and controlling poaching. |
| Department of Environment and Waterways | The mandate of the Department of Environment is to establish environment policies, ensure environmental safeguards in development projects, managing pollution, wastes and hazardous substances; sustainable management of natural resources i.e. soils, water, watersheds, flora and fauna, land use, indigenous ecosystems and human health; air quality monitoring and protection; and focusing on clean industrial production. They are also responsible for overseeing the protection of indigenous ecosystems and biological diversity. Its climate change unit is responsible for promotion of climate change related initiatives. | (Outputs 1.1, 1.2, 1.3 and 1.4) MoEW will chair the Project Board and be part of the Project Technical Working Team. The Ministry will be responsible for oversight and reporting and monitoring project progress to GEF. |
| Tourism department | Promotes tourism at the provincial, district/cluster level and island level in Fiji. | (Outputs 2.2 and 2.4) The Tourism Department will play an active role in supporting local tourism ventures in Southern Lau and facilitate studies to identify opportunities for promotion of tourism related incentives for local communities and provide training for initiation of ecotourism activities |
| - International and national NGOs, Private organizations, and media |  |  |
| FLMMA | Lead implementing NGO and leading conservation organization in the Fiji and the Region in promotion of locally managed marine areas. FLMMA had worked in outer islands in central Lau and other islands in other provinces in Fiji. In Fiji, the FLMMA Network works to promote and encourage the preservation, protection and sustainable use of marine resources in Fiji by the traditional users of marine resources. FLMMA secretariat is based in Suva. | (All Outcomes and Outputs) FLMMA had been involved from the initial project design and will be key executing agency for the project. FLMMA Network will be involved in all aspects of the project. FLMMA Trustee will be part of the project Board and FLMMA’s Executive Committee will be the Steering Committee for the project |
| Conservation International (CI) | CI is a leading international conservation NGO with mission is to protect nature, and its biodiversity, for the benefit of humanity. Country office based in Suva. CI is supporting the Lau Seascape project | (All Outcomes and Outputs) As a member of the FLMMA Network, CI will actively contribute to all aspects of the project. In particular, CI is supporting the Lau Seascape project that will be a close partner of activities in Component 2. They will participate, as part of the FLMMA Network in design and implementation of key conservation project activities. |
| Coral Reef Alliance (CORAL) | CORAL is an international alliance that has adopted a multi-pronged approach to restoring and protecting coral reefs in partnership with the communities living nearest to the reefs. | (Outputs 2.2 and 2.4) Potential partner for developing sustainable business models for MPAs/LMMAs including user-pay systems. Will be consulted during PPG and advise on development of sustainable financing activities. |
| WWF | WWF-Fiji is a member of the WWF International Network, one of the world's independent conservation organizations. Has worked on conservation projects in Southern Lau especially for Ono and Kabara Islands. | (All Outcomes and Outputs) As a member of the FLMMA Network, WWF will actively contribute to all aspects of the project. However, in particular, WWFs experience of conservation education and awareness raising will be utilized in all the project areas under Component 3. They will also be a key partner for information sharing and conservation activities for the project in Southern Lau. |
| Wildlife Conservation Society WCS | WCS has also established multiple-community conservancies and linked them with the provincial government, in some cases providing the platform for community-government coordination. WCS has trained community rangers to protect forests and wildlife. | (All Outcomes and Outputs) As a member of the FLMMA Network, WCS will actively contribute to all aspects of the project. WCS experience of community-based management of natural resources will be utilized in project areas in a collaborative fashion (Component 2). They could also be a key partner for information sharing and conservation activities for the project. |
| The World Conservation Union- IUCN - | IUCN has been quite active in Fiji in implementing conservation concepts and preparation Areas Conservation Strategy. IUCN had developed their own mechanism or Planning Process for MPA sites. | (All Outcomes and Outputs) As a member of the FLMMA Network, WCS will actively contribute to all aspects of the project. The expertise of IUCN will be helpful in the implementation of the project, the use their Ten Steps for MPA implementation can be useful for the project with their other technical expertise could be shared with FLMMA and implementing partners (Output 1.1). |
| Pacific Blue Foundation | Pacific Blue Foundation is a non-profit public benefit charitable trust. Pacific Blue Foundation provides basic research, education, and dissemination of sustainable practices in coastal regions with the ultimate goal of preserving and promoting the biological and cultural diversity of the region. | (Outputs 3.2 and 3.3) Can provide basic research, education, and dissemination of sustainable practices in coastal regions with the ultimate goal of preserving and promoting the biological and cultural diversity of the region. |
| Women in Fisheries Network Fiji | WiFN was set-up as a network of interested scientists, gender and development scholars having a common interest in addressing the involvement of women in the fisheries sector. | (All Outcomes and Outputs) Partner for supporting and guiding the strong participation of women, especially in Lau. They will assist with information dissemination on the role of women in fisheries, sustainable fisheries methods and approaches through lessons learnt. Support sharing of information and tools and concepts that empower women during the project period. The WiFN will provide training support for mainstreaming gender as well as provide oversight for gender related issues |
| Fiji Environmental Law Association (FELA) | FELA’s purpose is to promote the sustainable management of natural resources through law. | (Outputs 1.1 and 2.4) Provide guidance on environmental laws and regulations for implementing agencies and key partner agencies in Southern Lau. |
| National Trust of Fiji (NTF) | NTF is a statutory body funded jointly by the Fiji Government, independent donors and multi-lateral projects to provide for the protection of Fiji’s natural, cultural and national heritage. | (Outputs 3.1 and 3.2) Provides basic research, education, and dissemination of sustainable practices in coastal regions with the ultimate goal of preserving and promoting the biological and cultural diversity of the region. |
| Partners in Community Development Fiji (PCDF) | PCDF aims to promote good governance and gender balance, environmental protection, build capacity and self-reliance in isolated rural communities and promote healthy lifestyles, include reducing stigma attached to mental illness. Has projects on community-based protection of coral reefs | (Output 2.2) Will be consulted on development of project activities and coordination opportunities |
| - Academia |  |  |
| Secretariat of the Pacific Community (SPC) | South Pacific Region’s technical agency with 22 member countries and territories. Will be engaged in PPG discussions (e.g. PPG stakeholder workshops) and consulted on development of project activities and coordination opportunities. | (Outputs 1.4 and 2.3) Will assist in technical training and support information sharing with similar programs in the Pacific region. |
| Secretariat of the Pacific Regional Environment Program (SPREP) | SPREP provides technical and advisory support to Fiji in implementing its National Biodiversity Strategy and Action Plan (NBSAP). | (Output 3.1) Will support sharing of knowledge and best practices in LMMA planning and management through its networks. |
| The University of South Pacific (USP) | University is a leading institution of high creating inter-provincial harmony, providing solutions through research relevant to the national needs, towards transformation of the country into a knowledge-based economy.er learning committed to social development, South Pacific (USP) USP is the region’s premier University with a major campus at Laucala, Suva Fiji, including Institute of Marine Resources (IMR) and Institute of Applied Sciences (IAS). As the region’s largest tertiary education and research organization. It has for over a decade, conducted research in existing and potential FLMMA communities to promote, establish, monitor and promote the spread and sustainability of LMMAs. | (Output 3.3) Engagement of academia and students in monitoring component of the project. Involvement in awareness raising and advocacy campaigns. It would also provide training and capacity building of and conducting collaborative research with FLMMA communities, Government extension staff and NGOs. It will also provide expert scientific input into the design and conduct of baseline and monitoring studies for MPAs. |

Gender Equality and Empowering Women

- Gender integration acknowledge the different roles that women and men play in marine resources planning and management and the need to create opportunities that enhance women’s exposure, networking, knowledge, and skills and give them a platform to share their concerns, needs, and indigenous and other knowledge. Ultimately it facilitates gender responsive policy solutions to promote equitable fisheries activities and improvement of livelihoods. Fisheries conservation and management practices can be a social process in which women and men across various ages, and groups are important actors in helping to conserve, manage, and use natural resource in a sustainable manner.  Annex 7 provides a full discussion of gender analysis and mainstreaming actions.

- To improve the gender roles, the following are considered key opportunities that need to be addressed:

- Improving technologies and investment on value addition and post-harvest technologies for marine products;

- Encouraging women small business entrepreneurs to establish formal networks and associations for marketing, monitoring species, sales and marketing;

- In-depth research and studies to accurately enumerate women’s involvement and contribution to processing, post-harvest, marketing and distribution activities;

- Looking at gender relations in the sector to involve and account for family and other factors;

- Collection of accurate data on fishing participation of men and women in different fisheries sectors;

- Ensuring specific programs that target women and a commitment for ensuring the continuity of such programs;

- Developing innovative marketing and networking to assist communities in rural areas to market their surplus in urban centers where demand is high;

- Strategic involvement of women in education and training that will enable more participation of women, particularly in off-shore fisheries sector;

- Expansion of aquaculture and alternative income generation activities that will relieve pressure on reefs and lagoons;

- Exploring alternatives for credit access, financial loans or assistance; and

- Developing a knowledge management system to build resources for women in fisheries

- Special mechanisms are envisaged under the project to promote the role of women in various activities.  These are reflected in Table 5:

Table 5: Gender Mainstreaming Action Plan

| Gender Mainstreaming Objectives | Gender Mainstreaming Activities | Gender mainstreaming Targets |
| --- | --- | --- |
| To strengthen women based institutions and ensure women’s participation and leadership | Support to strengthen YMST, Village Committee, District & Provincial committees ensuring women participation at all levels | At least 50% of women in the target households are associated with community based institutions and participate in the project initiatives |
| Improve understanding of gender issues, capacity building needs of women and policy issues | Support action to identify the issues related to gender so that capacity building and policy interventions can be planned. | Specific gender related issues and capacity gaps are identified and taken up as a part of the capacity-building of all training and planning process nationally and locally in all the nine islands of the project |
| To enhance capacity, skills and competence of women in technical aspects related to conservation and promotion | Technical training programs, exchange visits and other skills development activities involving women | At least 50% of technical and front-line leaders and women leaders of grassroots institutions/committees are trained in ecosystem-based management approaches Increased economic and social status of women in Southern Lau and target island communities by 15% Annual Yaubula Dau for all Lau group to involve sales of handicrafts mats, tapa, wood carving products that are specifically made by women. |
| To monitor and evaluate women’s participation and their empowerment through the project interventions | Incorporating gender-sensitive indicators and collection of sex-disaggregated data for monitoring and evaluating project results. | Gender disaggregated data included in Results Framework and reported annually in other monitoring and evaluation formats at various levels (progress reports) |
| To provide opportunities for income generation | Design and support for activities that would specifically benefit women | A least 4 activities implemented to target women |
| Reduce drudgery for women | Support for specific programs to reduce burden on women | At least 2 activities implemented to reduce drudgery for women, so that they have more time to participate in decision-making and income generation activities |
| To enhance role of women in implementation of the project | Engaging key local women’s leaders to encourage greater participation of women from local communities. | At least 30% of the development committees engaged in the Village and District Committees are local women. |
| To ensure high participation of women in project activities through innovative communication strategy and methods | Including specific efforts to encourage women’s role in outreach and communication strategy of the project Keeping gender focus in awareness and communication campaigns of the project. | At least 50 % of the communication methods used in the project will be focused towards women |
| Improve women’s role in decision-making | Promote adequate representation and active participation of women decision-making bodies. | Increase in women's role and voice in decision making in planning and management of LMMAs |

South-South and Triangular Cooperation:

- FLMMA is part of the globally recognized network of Locally Managed Marine Areas (LMMA) that is a group of involved in various community-based marine conservation projects around the globe, primarily in the Indo-Pacific, who have joined together to learn how to improve management efforts.  The Network spans the people and cultures of Southeast Asia, Melanesia, Micronesia, Polynesia and the Americas. As part of this global network, FLMMA will work towards and share experiences (Output 3.2) in efforts to (i) protect biodiversity at specific sites; (ii) promote the LMMA approach (and lessons from using it) in the Indo-Pacific and globally; (ii) building capacity for learning and implementation of Community-Based Adaptive Management (CBAM); and (iv) developing policy environment at local, regional, country and international levels to support widespread adoption of LMMAs.  Through this network, FLMMA will share best case studies (Output 3.2), LMMA experiences and tools (Output 1.3) that are to be developed through the project to improve the management of LMMAs, as well as training and lessons sharing events (Output 3.2). In addition, the FLMMA Network in Fiji includes a number of international and national non-government organizations such as IUCN, CI, CORAL, Pacific Blue, WCS, WWF, WiFN, FELA, NTF, PCDF and research and teaching institutions such as USP, SPC and SPREP. Through this alliance, this would enable the sharing of experiences and learning across the networks of these agencies and institutions.

Sustainability and Scaling Up:

- The project has been designed to dovetail with recent Government of Fiji voluntary commitments made at the 2017 UN Oceans Conference, including the Lau Seascape initiative. This alignment will support sustainability beyond the project lifetime, as will the engagement of the FLMMA Network, the key body providing technical support to coastal communities that manage LMMAs and to oversee the implementation of the project.  Ultimately, the community-based management model at the heart of the LMMA approach will in itself support sustainability of project outcomes. The project will build community capacity and the capacity of FLMMA and provincial agencies to support communities, as well as providing incentives for communities to establish LMMAs and strive towards best practice in their management.

- Institutional sustainability will build on and benefit from a number of project actions, including in particular: (i) the FLMMA Executive Committee serving to support dialogue, information flow and decision-making to facilitate the creation and management of LMMAs; (ii) the development of a national policy and implementation plan (Output 1.1) for MPAs in the country that would define measures for integration of LMMAs and site-specific collaborative models for management planning for LMMAs, agreement on targets and indicators for evaluating the effectiveness of LMMAs and the network and arrangements for protection and enforcement mechanisms; (iii) developing and implementing a range of regulations, guidelines and best practices (Output 1.3); for promoting the establishment and management of a LMMA network in the country; (iv) development of a long-term marine biodiversity and ecosystems monitoring program that would be tested in the Southern Lau Seascape (Outputs 3.1 and 3.3) that would provide a framework for replication in other marine LMMAs in the future; and (v) preparation of a Operational Manual and lessons learned guide (Output 1.3) that would serve as the basis for expanding and upscaling the LMMA concept more widely in Fiji. With the strengthening of Fiji’s FLMMA network and provincial and local institutions and authorities to more effectively manage critical marine and coastal ecosystems, and the facilitation and demonstration to show that resources can be applied at scale and sustainably for the benefit of globally important biodiversity and Fiji’s sustainable development. Following the completion of the project, FLMMA and Provincial entities will be empowered and better equipped to exercise their mandates, without requiring further external resources. Communities will gain socio-economically from Fiji’s multi-sectoral efforts to manage marine and coastal zones in support of conservation and sustainable use objectives. By protecting significant biodiversity and reducing the impacts of unsustainable and over-fishing and other destructive land-based activities, the project will contribute to creating a platform for sustainable economic growth, rather than the unsustainable and destructive removal of collective natural resources. By enabling rural communities to gain income from conservation and effective biodiversity management, the project will support Fiji in achieving the Aichi Targets, SDGs and other global initiatives that seek to reduce poverty. Particularly innovative aspects of this project include: (i) the development of a MPA policy (that integrates LMMAs) for the country, when none existsed before; and (ii) the development of capacity to deliver national (Output 1.4) and site level action (Output 2.3) to protect marine and coastal biodiversity in Fiji, bringing together provincial and local actors alongside civil society and local communities to manage biodiversity, reduce resource exploitation and protect ecological functions while minimizing pressures on natural resources.

- To facilitate long-term sustainability of LMMA activities in Fiji, the project will ensure the following:

- Tailored training and capacity-building to strengthen the functionality and capacities of FLMMA (Output 1.4), provincial and local extension staff and community fish and forest wardens and local communities (Output 2.3);

- Establishment of new and strengthened collaborations for comprehensive LMMA planning and management, preparation of National MPA Policy (that integrates LMMAs) and Implementation Plan (Output 1.1), and data management and sharing (Outputs 3.1 and 3.2);

- Outreach and awareness programs (Output 3.2) delivered at national and provincial levels in parallel to build local community and stakeholder support for LMMAs; and

- Development of a sustainability strategy for ongoing community engagement in implementation of LMMA management plans (Output 2.4).

- The project is designed to provide demonstration models for up-scaling in the rest of Fiji. In particular, the capacity building and the development of the operational manual (guidelines and regulations for LMMA planning, management and monitoring) will strongly support up-scaling. By communicating and disseminating project’ results widely will help in generating demand for similar initiatives in the rest of the country. The involvement of different government, provincial and the NGO entities (including in particular, FLMMA) can lead to further up-scaling of the project’s intervention. Improvement in capacity, awareness and regulatory frameworks will ensure post-project sustainability and encourage investments from public and private sector and hence, can contribute to up-scaling.

- The project will introduce a bottom-up participatory planning process by engaging community members and tapping into their local knowledge. The Project support for implementation of LMMA management plans will concurrently seek to develop synergies among provincial development actors and programs with an objective of raising additional investments that will fund and expand models of resource use and alternative livelihood activities within and outside of the targeted LMMAs.  On a national level, best practices from this project could serve for replication in other parts of the country, and across the Pacific and other regions implementing LMMAs. Lessons learned through the project’s on-the-ground and LMMA level interventions in the target ‘model’ LMMAs will be used to promote replication and scaling of the interventions at the national, regional and global levels through knowledge management and dissemination (Component 3). Fiji’s engagement in regional networks, including the FLMMA network in the Pacific through commitment to the international conventions and protocols, as well as by participating in high-level negotiations on regional marine issues, will ensure sharing of the results through monitoring, research, community engagement, and policy making.

# Project Management

Cost efficiency and effectiveness:

- The project has been designed to reflect the most cost-effective approach. A number of strategies were evaluated during the project formulation stage to identify those strategies and activities that demonstrate this cost-effective approach.  The cost-effective approaches that have been applied to the project are the following:

- Defining a holistic approach to project formulation: The project adopts an integrated spatial ecosystem-based approach that connects land, coastal and marine systems and their various interactions to maximize opportunities for synergies, such that selected actions and interventions generate multiple benefits. This is to be accomplished through development and implementation of well-designed conservation actions (LMMAs with defined management zones, including core conservation zones, sustainable use areas, non-consumptive use areas, set-asides or ‘no-take’ areas to facilitate restoration and recovery of marine and coastal habitats), sustainable community resource use and management and livelihood improvement measures in fisheries, tourism, etc. and the improved management of land and coastal-based activities (based on a ridge-to-reef approach).

- Sequencing of activities: Project design and sequencing of project activities ensures that foundational activities are completed first (under Outcome 1), such as (i) establishing functional governance and coordinating mechanisms at the national and provincial levels; (ii) policy and regulatory changes for establishing LMMAs and clarifying institutional responsibilities of LMMA planning, management and oversight; and improved policies and practices that facilitate mainstreaming biodiversity into sector and environmental planning; and (iii) capacity improvements developed to provide the necessary groundwork for later demonstration of integrated ridge-to-reef planning and management in the selected LMMAs under Component 2. The project includes subsequent documentation, dissemination of best practices and trans-boundary collaboration in Outcome 3 to lay the ground work for scaling up of integrated planning and management in LMMAs in the country and feedback mechanisms to influence further policy and legislative changes, as appropriate.

- Improving efficiency, effectiveness and coordination of management and enforcement actions:  The effective, efficient and coordinated use of existing national, provincial, local and NGO (e.g. FLMMA network) capacity and resources (including manpower, budgets, equipment, etc.) based on individual agency mandates. This will ensure that LMMA activities are defined within existing budgetary and institutional constraints that operate in the country and is considered a more cost- effective and sustainable strategy for management of LMMAs, rather than rely on unreliable external funding that cannot be sustained beyond the project period.

- Models to demonstrate benefits:  Project design ensures selectivity in the identification and development of on-the-ground demonstration models (Outcome 2) focusing mainly on trialing of LMMA establishment, integrated planning and management, environmentally sustainable marine and coastal resources use, livelihood best practices, trialing of community-based ecotourism best practices, improved management of land-based activities in the South Lau islands so as to ensure cost-effectiveness in terms of avoiding duplication and ineffective spread of activities.

- Building on existing lessons and best practices: As a measure to ensure cost-effectivity, project design focuses on use of available resource to the extent possible building on the existing LMMA management planning approaches from the region. Rather than hire expensive external consultants, the FLMMA network in collaboration with provincial and local partners will make use of available information and expertise to develop plans that follow the “No Regrets” principle adopted by national policies. This results in plans that have higher levels of participation and buy-in. While they may be simpler than plans drafted by external experts, they would be more likely to be accepted and implemented by local communities.  It would also build and replicate lessons from on-going and other regional initiatives.

- Data management systems: The project will focus on the development of standardized, but simple information collection in a strengthened FLMMA information management system (rather than on costly GIS systems) is also a proven and effective way to collect and share data. The Knowledge Management and Communication Plan will make use of free and widely available forms of communication in the country.

- Co-financing Cost-effectiveness:  The total GEF investment of US$ 805,496 for this project will leverage a minimum of US$ 3,477,844 in cofinancing, a cost-effective ratio of 1:4 with additional associated financing inputs anticipated during project implementation.

Project management:

- The project will operate at the national level in terms of policy development, preparation of guidelines and national capacity development.  The PMU will be located in Suva, and will include a Project Coordinator (GEF-financed), who will be supported by staff of the FLMMA Secretariat, that will include a Technical Advisor, LMMA Coordinator, Finance Officer, Information Technology Officer and Project Officer (all co-financed). In terms of on-the-ground implementation of LMMA actions a Field Officer (GEF-financed) will be recruited by the project and located in Southern Lau. Arrangements for office space in the field will be made through Lao provincial government.  The Field Officer will work closely with the Porvincial Government, YMSTs and fisheries and forestry extension staff.

Agreement on intellectual property rights and use of logo on the project’s deliverables and disclosure of information:

- To accord proper acknowledgement to the GEF for providing grant funding, the GEF logo will appear together with the UNDP logo on all promotional materials, other written materials like publications developed by the project, and project hardware. Any citation on publications regarding projects funded by the GEF will also accord proper acknowledgement to the GEF. Information will be disclosed in accordance with relevant policies notably the UNDP Disclosure Policy and the GEF policy on public involvement.

# Project Results Framework

| This project will contribute to the following Sustainable Development Goal (s): SDG 14: Conserve and sustainably use the oceans, seas and marine resources for sustainable development, notably Target 14.5—By 2020, conserve at least 10 per cent of coastal and marine areas, consistent with national and international law and based on best available scientific information |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| This project will contribute to the following country outcome included in the UNDAF/Country Program Document: Environmental sustainability is strengthened through the improvement of management of energy, natural resources, access to green technology, climate change strategies, conservation of biodiversity, and systems and plans to reduce disasters and risks |  |  |  |  |  |
| This project will be linked to the following output of the UNDP Strategic Plan: Output IRRF 1.4.1 Solutions scaled up for sustainable management of natural resources, including sustainable commodities and green and inclusive value chains |  |  |  |  |  |
|  | Objective and Outcome Indicators | Baseline | Mid-term Target | End of Project Target | Data Collection Methods and Risks and Assumptions |
| Project Objective: To strengthen and integrate Locally Managed Marine Areas (LMMAs) into Fiji’s Marine Protected Area (MPA system) through improved institutional and local capacity, management planning and monitoring | Indicator 1: Area under protection as LMMAs in South Lau seascape (UNDP IRRF 1.4.1) (Total area includes GEF Core Indicator 2.1 – new LMMA and LMMA expansion area only) | 22,000 ha (9,000 ha in Ono-i-Lau cluster; 13,000 ha in Vulaga cluster) | 39,500 ha (17,500 ha LMMA expansion, with 2,500 ha expansion in Ono-i-Lau cluster; and 15,000 ha expansion/new LMMA in Vulaga cluster) | 70,000 ha (48,000 ha LMMA expansion, with 7,000 ha expansion in Ono-i-Lau cluster; and 41,000 ha expansion/new LMMA in Vulaga cluster) | Data Collection Methods: (1) and (2) Management plan documents implementation status reports, Annual work plan completion reports, METTs Assumptions: -The National and Provincial Governments consider it their priority to support integrated planning of its LMMA areas and implement target oriented activities with local communities to improve conservation and sustainable use of such resources. -The Provinces, CBOs, FLMMA and communities would work in close collaboration for preparation of LMMAs management frameworks -Communities provide support for zoning and implementation of conservation related outcomes Risks: -Natural disaster may affect the LMMA conservation and restoration work. -Lack of capacity in government and communities to meet obligations related to project. |
|  | Indicator 2: Management effectiveness of LMMAs in South Lau seascape (METT): (i) Ono-i-Lau LMMA cluster (16,000 ha including 7,000 ha LMMA expansion) a) Ono-i-Lau Island b) Vatoa Island (ii) Vulaga LMMA cluster (54,000 ha including 41,000 ha LMMA expansion and new LMMA) a) Fulaga Island b) Ogea Island c) Kabara Island d) Komo Island e) Moce Island f) Namukailau Island (new LMMA) g) Yagasa Island (new LMMA) h) Navutuiloma Island (new LMMA) i) Vaqava Island (new LMMA) (GEF Core Indicator 2.1 (new LMMAs/LMMA expansion) and 2.2 (existing LMMA area)) | (i) Ono-i-Lau cluster: a) Ono-i-Lau Is: 20 b) Vatoa Is: 15 (ii) Vulaga cluster: a) Fulaga Is: 20 b) Ogea Is: 19 c) Kabara Is: 19 d) Komo Is: 19 e) Moce Is: 19 f) Namukailau Is: 5 g) Yagasa Is: 5 h) Navutuiloma Is: 5 i) Vaqava Is: 5 | At least 30% progress towards final targets: (i) Ono-i-Lau cluster: a) Ono-i-Lau Is: 30 b) Vatoa Is: 25 (ii) Vulaga cluster: a) Fulaga Is: 30 b) Ogea Is: 30 c) Kabara Is: 30 d) Komo Is: 30 e) Moce Is: 30 f) Namukailau Is: 15 g) Yagasa Is: 15 h) Navutuiloma Is: 15 i) Vaqava Is: 15 | (i) Ono-i-Lau cluster: a) Ono-i-Lau Is: 50 b) Vatoa Is: 50 (ii) Vulaga cluster: a) Fulaga Is: 50 b) Ogea Is: 50 c) Kabara Is: 50 d) Komo Is: 50 e) Moce Is: 50 f) Namukailau Is: 40 g) Yagasa Is: 40 h) Navutuiloma Is: 40 i) Vaqava Is: 40 |  |
|  | Indicator 3: Number of direct beneficiaries (percentage of which are women) including people trained and people participating in LMMA management, improved and sustainable marine resources use practices. (GEF Core Indicator 11) | 0 | 230 beneficiaries of which 50% women (115) | At least 1,160 beneficiaries, with at least 50% women (580) | Data Collection Methods: (3) Approved LMMA management plan, Annual plan budget estimates and statement of expenditures. Community survey records, Project records and attendance sheets. Assumptions: -Local communities understand livelihood benefits and ecological security from cooperation with and sustainable management of marine and coastal resources. Thus, they will participate in sustainable management and ecosystem restoration work. Risk: Livelihood benefits from sustainable marine management may be low to give up current unsustainable practices |
| Outcome 1: Strengthened policy, legal and institutional framework for contribution of Locally Managed Marine Areas (LMMAs) to the Marine Protected Area (MPA) system | Indicator 4: Extent to which policy and regulatory frameworks integrate LMMAs into marine protected area system and recognize their contribution to conservation and sustainable use of marine resources | Policies related to MPA system and its integration with LMMAs fragmented and lack clear criteria and institutional responsibilities for planning and management | Consultations and stakeholder workshops underway, including with LMMA communities, to develop MPA policy that has strong political support | National policy for MPAs integrating LMMAs developed and adopted by Government, with clear definition of MPAs and rules and regulations for integration of LMMAs | Data Collection Methods: (4) Government policy approval notice, FLMMA reports, project reports (5) UNDP Capacity Scorecard (6) FLMMA strategic plan and operational manual documents, guidelines, best practices and circulars. Assumption: -The national government will develop appropriate legislative, policy, institutional and technical measures that facilitate integrated landscape to seascape planning and management in a timely manner. -Development strategies and management plans will be officially approved by national and provincial governments with allocation of appropriate staff and funding for implementation -The Province will take active part in developing strategies and implementation using new knowledge and skills provided by the project -Local communities are convinced that spatial planning and mainstreaming ecosystem services and biodiversity into LMMA management is in their long-term interests Risks: -Priorities of provincial government and local communities might shift if development benefits take long to manifest - Plans are developed but not used, particularly by resource users |
|  | Indicator 5: Level of institutional capacities across FLMMA Network to support MPA/LMMA establishment and management (based on UNDP Capacity Development Scorecard) | Limited and thinly spread institutional capacities within FLMMA Network for planning, implementation and monitoring of MPAs/LMMAs that integrate biodiversity conservation as measured by customized UNDP Capacity Development Scorecard with baseline value of 39 | Increase of institutional capacity by 10 points over baseline value = 49 | Increase of institutional capacity by 25 points over baseline value = 64 |  |
|  | Indicator 6: Extent to which LMMAs are planned and managed taking into consideration ecosystem-based management* that recognizes land and sea linkages *Examples of ecosystem-based management includes evidence of the following in LMMA management planning and implementation: (i) Linkages between land actions and seascape and include specific land- based management measures to reduce land-based erosion, pollution, and waste management; (ii) Land based development plans integrate ridge-to-reef approach; (iii) Zoning for different uses with clear guidelines for management of each zone; (iv) Management measures to protect species and ecosystems, including establishing sustainable fishing limits and methods of harvest; (v) Participatory management framework to ensure enforcement and compliance with agreed management measures. | Lack of appropriate and modern tools and guidance on ecosystem-based LMMA management | Tools and guidance for LMMA management that integrates biodiversity conservation and ridge to reef interactions developed and presented to government for approval | Tools and guidance for LMMA management that integrates biodiversity conservation and ridge to reef interactions developed, approved and adopted at LMMA level |  |
| Outcome 2: Improved management effectiveness of LMMAs in Southern Lau seascape | Indicator 7: Contribution of LMMAs to biodiversity conservation in South Lau as measured by changes in: (i) Poaching in LMMAs, measured by monthly records of reported poaching incidents; (ii) Percentage coverage of live coral cover; and (iii) Population/stocks of indicator species of sturgeon fish, snapper and grouper (average abundance across South Lau based on number per 500 square metres). Groupers: Plectropomus spp., Epinepheus spp., Cephalopholis spp. Snappers: Lutjanus spp. Surgeon fish: Acanthurus spp., Ctenocahetus spp. | (i) Average levels of poaching in LMMAs of 6 reports/month (ii) Live coral cover of 53% (iii) Average abundance of indicator species (#/500sqm): Surgeon fish: 232 Snappers: 48 Groupers: 58 (aggregated data for South Lau) | (i) Reduction average monthly records of poaching by 40% (ii) Live coral cover stable (ii) Stocks of key species stable | (i) Reduction average monthly records of poaching by 70% (ii) Live coral cover stable or increasing (ii) Stocks of key species stable or increasing | Data Collection Methods: (7) Biological survey reports, community consultation, poaching records, etc. 7(i) Poaching: Methods include a mix of: (i) direct observation; (ii) indirect observation; (iii) YMST enforcement records; (iv) direct questioning; (v) expert opinion; etc. Data would be collected by the YMSTs and verified by LMMA members. 7(ii) Coral Cover: Assessment is measured belt transects (each 10m x 1m), with a minimum of two transects completed by depth. This coral cover assessment will be undertaken by FLMMA NGO network teams. 7(iii) Population of key species: Reef fish assessment conducted along 4m x 30 m belt transects. A T square marked in 5 cm increments used to gauge fish size. A minimum of 6 transects conducted by each fish diver/site. A roving survey used to assess total diversity and relative abundance of reef fishes at each site. Assessment will be undertaken by FLMMA NGO network teams Assumptions: - Capacity and resources area available to undertake biological surveys in regular intervals -Local communities are convinced that mainstreaming biodiversity into LMMA planning is in their long-term interests and they support such actions Risk: -Communities may not report incidents of poaching or species changes -Climatic events may alter species and ecosystem conditions |
|  | Indicator 8: Number of government and community members applying approaches in ecosystem-based management* of LMMAs with rules and customary enforcement measures *Examples of ecosystem-based management includes evidence of the following in LMMA management planning and implementation: (i) Linkages between land actions and seascape and include specific land- based management measures to reduce land-based erosion, pollution, and waste management; (ii) Land based development plans integrate ridge-to-reef approach; (iii) Zoning for different uses with clear guidelines for management of each zone; (iv) Management measures to protect species and ecosystems, including establishing sustainable fishing limits and methods of harvest; (v) Participatory management framework to ensure enforcement and compliance with agreed management measures; (vi) Clear roles and responsibilities of communities, YMSTs and provincial agency staff. | Limited application of ecosystem based management approaches at LMMA level | At least 25 staff and community members (at least 30% women) trained and applying ecosystem-based approaches to planning and development of LMMA management plans | At least 100 staff and community members (at least 30% women) trained and applying ecosystem-based approaches to planning and development and implementation of LMMA management plans | Data Collection Methods: (8) Training reports, participatory action reports Assumptions: -There is adequate interest and commitment to training and related actions - Trainers adequately skilled to demonstrate the differences between fisheries management and ecosystem management benefits Risks -Biodiversity and ecological services take long to manifest and might not convince communities of the benefits |
| Outcome 3: Lessons learned through knowledge management, monitoring and evaluation, and equitable gender mainstreaming are available to support the implementation of MPAs/LMMAs nationally and internationally | Indicator 9: Level of community and stakeholder awareness of conservation and sustainable use and threats to marine biodiversity (as measured by KAP Survey) | Baseline to be established in Year 1 | At least 20% of participating persons and stakeholders (30% of which are women) have good awareness of conservation, sustainable marine resource use and threat prevention benefits | At least 50% of participating persons (30% of which are women) and stakeholders are aware of value of conservation, sustainable marine resources use and threat prevention benefits | Data Collection Methods: (9) KAP survey reports (see ProDoc Annex 16 for KAP Survey Framework) (10) KM documents, best practice documents, proceedings of dissemination events and implementation reports Assumption: -Stakeholders willing to actively participate in the review process. - -Project management will be able to identify, document and disseminate the best practices -Mid Term Review and End of Project Evaluation of the project will also contribute to identifying the best practices -Best practices on sustainable marine resource management readily available to resource users -Gender and social inclusion plan followed and benefits distributed equitably Risks: -Government priorities may change from due to political pressure from resource users -Actions among the assorted agencies and NGOs remain uncoordinated -Community diversity will be a hindrance to outreach activities |
|  | Indicator 10: Number of knowledge products on conservation and sustainable marine resource management codified and disseminated nationally and internationally | Limited concerted effort exists in promoting knowledge management and best practices | At least 2 knowledge products documented | At least 10 knowledge products on sustainable marine resource use, such as sustainable fisheries practices; LMMA zoning practices; sustainable resource management and fishing, ecosystem-based management, gender mainstreaming, etc., readily available and accessed nationally and internationally |  |

# Monitoring and Evaluation (M&E) Plan

- The project results as outlined in the project results framework will be monitored annually and evaluated periodically during project implementation to ensure the project effectively achieves these results. Supported by Component/Outcome Three:  Knowledge Management, Communication, Gender Mainstreaming and M&E, the project monitoring and evaluation plan will also facilitate learning and ensure knowledge is shared and widely disseminated to support the scaling up and replication of project results.

- Project-level monitoring and evaluation will be undertaken in compliance with UNDP requirements as outlined in the UNDP POPP and UNDP Evaluation Policy. The UNDP Country Office will work with the relevant project stakeholders to ensure UNDP M&E requirements are met in a timely fashion and to high quality standards. Additional mandatory GEF-specific M&E requirements (as outlined below) will be undertaken in accordance with the GEF M&E policy and other relevant GEF policies.

- In addition to these mandatory UNDP and GEF M&E requirements, other M&E activities deemed necessary to support project-level adaptive management will be agreed during the Project Inception Workshop and will be detailed in the Inception Report. This will include the exact role of project target groups and other stakeholders in project M&E activities including the GEF Operational Focal Point and national/regional institutes assigned to undertake project monitoring. The GEF Operational Focal Point will strive to ensure consistency in the approach taken to the GEF-specific M&E requirements (notably the GEF Tracking Tools) across all GEF-financed projects in the country. This could be achieved for example by using one national institute to complete the GEF Tracking Tools for all GEF-financed projects in the country, including projects supported by other GEF Agencies.

M&E Oversight and monitoring responsibilities:

- Project Coordinator:  The Project Coordinator (PC) is responsible for day-to-day project management and regular monitoring of project results and risks, including social and environmental risks. The PC will ensure that all project staff maintain a high level of transparency, responsibility and accountability in M&E and reporting of project results. The PC will inform the Project Board, the UNDP Country Office and the UNDP-GEF RTA of any delays or difficulties as they arise during implementation so that appropriate support and corrective measures can be adopted.

- The PC will develop annual work plans based on the multi-year work plan included in Annex, including annual output targets to support the efficient implementation of the project. The PC will ensure that the standard UNDP and GEF M&E requirements are fulfilled to the highest quality. This includes, but is not limited to, ensuring the results framework indicators are monitored annually in time for evidence-based reporting in the GEF PIR, and that the monitoring of risks and the various plans/strategies developed to support project implementation (e.g. ESMP, gender action plan, stakeholder engagement plan etc.) occur on a regular basis.

- Project Board:  The Project Board will take corrective action as needed to ensure the project achieves the desired results. The Project Board will hold project reviews to assess the performance of the project and appraise the Annual Work Plan for the following year. In the project’s final year, the Project Board will hold an end-of-project review to capture lessons learned and discuss opportunities for scaling up and to highlight project results and lessons learned with relevant audiences. This final review meeting will also discuss the findings outlined in the project terminal evaluation report and the management response.

- Project Implementing Partner:  The Implementing Partner is responsible for providing all required information and data necessary for timely, comprehensive and evidence-based project reporting, including results and financial data, as necessary. The Implementing Partner will strive to ensure project-level M&E is undertaken by national institutes, and is aligned with national systems so that the data used and generated by the project supports national systems.

- UNDP Country Office:  The UNDP Country Office will support the Project Manager as needed, including through annual supervision missions. The annual supervision missions will take place according to the schedule outlined in the annual work plan. Supervision mission reports will be circulated to the project team and Project Board within one month of the mission. The UNDP Country Office will initiate and organize key GEF M&E activities including the annual GEF PIR, and the independent terminal evaluation. The UNDP Country Office will also ensure that the standard UNDP and GEF M&E requirements are fulfilled to the highest quality.

- The UNDP Country Office is responsible for complying with all UNDP project-level M&E requirements as outlined in the UNDP POPP. This includes ensuring the UNDP Quality Assurance Assessment during implementation is undertaken annually; that annual targets at the output level are developed, and monitored and reported using UNDP corporate systems; the regular updating of the ATLAS risk log; and, the updating of the UNDP gender marker on an annual basis based on gender mainstreaming progress reported in the GEF PIR and the UNDP ROAR. Any quality concerns flagged during these M&E activities (e.g. annual GEF PIR quality assessment ratings) must be addressed by the UNDP Country Office and the PC.

- The UNDP Country Office will retain all M&E records for this project for up to seven years after project financial closure to support ex-post evaluations undertaken by the UNDP Independent Evaluation Office (IEO) and/or the GEF Independent Evaluation Office (IEO).

- UNDP-GEF Unit:  Additional M&E and implementation quality assurance and troubleshooting support will be provided by the UNDP-GEF Regional Technical Advisor and the UNDP-GEF Directorate as needed.

- Audit: The project will be audited as per UNDP Financial Regulations and Rules and applicable audit policies on NGO implemented projects.

Additional GEF monitoring and reporting requirements:

- Inception Workshop and Report:  A project inception workshop will be held within two months after the project document has been signed by all relevant parties to, amongst others:

  - Re-orient project stakeholders to the project strategy and discuss any changes in the overall context that influence project strategy and implementation;

  - Discuss the roles and responsibilities of the project team, including reporting and communication lines and conflict resolution mechanisms;

  - Review the results framework and finalize the indicators, means of verification and monitoring plan;

  - Discuss reporting, monitoring and evaluation roles and responsibilities and finalize the M&E budget; identify national/regional institutes to be involved in project-level M&E; discuss the role of the GEF OFP in M&E;

  - Update and review responsibilities for monitoring the various project plans and strategies, including the risk log; SESP, Environmental and Social Management Plan and other safeguard requirements; project grievance mechanisms; the gender strategy; the knowledge management strategy, and other relevant strategies;

  - Review financial reporting procedures and mandatory requirements, and agree on the arrangements for the annual audit; and

  - Plan and schedule Project Board meetings and finalize the first year annual work plan.

- The PC will prepare the inception report no later than one month after the inception workshop. The inception report will be cleared by the UNDP Country Office and the UNDP-GEF Regional Technical Adviser, and will be approved by the Project Board.

- GEF Project Implementation Report (PIR):  The PC, the UNDP Country Office, and the UNDP-GEF Regional Technical Advisor will provide objective input to the annual GEF PIR covering the reporting period July (previous year) to June (current year) for each year of project implementation. The Project Manager will ensure that the indicators included in the project results framework are monitored annually in advance of the PIR submission deadline so that progress can be reported in the PIR. Any environmental and social risks and related management plans will be monitored regularly, and progress will be reported in the PIR.

- The PIR submitted to the GEF will be shared with the Project Board. The UNDP Country Office will coordinate the input of the GEF Operational Focal Point and other stakeholders to the PIR as appropriate. The quality rating of the previous year’s PIR will be used to inform the preparation of the subsequent PIR.

- Lessons learned and knowledge generation:  Results from the project will be disseminated within and beyond the project intervention area through existing information sharing networks and forums. The project will identify and participate, as relevant and appropriate, in scientific, policy-based and/or any other networks, which may be of benefit to the project. The project will identify, analyse and share lessons learned that might be beneficial to the design and implementation of similar projects and disseminate these lessons widely. There will be continuous information exchange between this project and other projects of similar focus in the same country, region and globally.

- GEF Core Indicators:  Relevant GEF Core Indicators will be reported at CEO Endorsement, mid-term and end-of-project.

- Independent Mid-term Review (MTR):  An independent mid-term review process will begin after the second PIR has been submitted to the GEF, and the MTR report will be submitted to the GEF in the same year as the 3rd PIR. The MTR findings and responses outlined in the management response will be incorporated as recommendations for enhanced implementation during the final half of the project’s duration. The terms of reference, the review process and the MTR report will follow the standard templates and guidance prepared by the UNDP IEO for GEF-financed projects available on the UNDP Evaluation Resource Center (ERC). As noted in this guidance, the evaluation will be ‘independent, impartial and rigorous’. The consultants that will be hired to undertake the assignment will be independent from organizations that were involved in designing, executing or advising on the project to be evaluated. The GEF Operational Focal Point and other stakeholders will be involved and consulted during the terminal evaluation process. Additional quality assurance support is available from the UNDP-GEF Directorate. The final MTR report will be available in English and will be cleared by the UNDP Country Office and the UNDP-GEF Regional Technical Adviser, and approved by the Project Board.

- Terminal Evaluation (TE):  An independent terminal evaluation (TE) will take place upon completion of all major project outputs and activities. The terminal evaluation process will begin three months before operational closure of the project allowing the evaluation mission to proceed while the project team is still in place, yet ensuring the project is close enough to completion for the evaluation team to reach conclusions on key aspects such as project sustainability. The PC will remain on contract until the TE report and management response have been finalized. The terms of reference, the evaluation process and the final TE report will follow the standard templates and guidance prepared by the UNDP IEO for GEF-financed projects available on the UNDP Evaluation Resource Center. As noted in this guidance, the evaluation will be ‘independent, impartial and rigorous’. The consultants that will be hired to undertake the assignment will be independent from organizations that were involved in designing, executing or advising on the project to be evaluated. The GEF Operational Focal Point and other stakeholders will be involved and consulted during the terminal evaluation process. Additional quality assurance support is available from the UNDP-GEF Directorate. The final TE report will be cleared by the UNDP Country Office and the UNDP-GEF Regional Technical Adviser, and will be approved by the Project Board.  The TE report will be publically available in English on the UNDP ERC.

- The UNDP Country Office will include the planned project terminal evaluation in the UNDP Country Office evaluation plan, and will upload the final terminal evaluation report in English and the corresponding management response to the UNDP Evaluation Resource Centre (ERC). Once uploaded to the ERC, the UNDP IEO will undertake a quality assessment and validate the findings and ratings in the TE report, and rate the quality of the TE report.  The UNDP IEO assessment report will be sent to the GEF IEO along with the project terminal evaluation report.

- Final Report: The project’s terminal PIR along with the terminal evaluation (TE) report and corresponding management response will serve as the final project report package. The final project report package shall be discussed with the Project Board during an end-of-project review meeting to discuss lesson learned and opportunities for scaling up.

Table 6: Mandatory GEF M&E Requirements and M&E Budget:

| GEF M&E requirements | Primary responsibility | Indicative costs to be charged to the Project Budget (US$) |  | Time frame |
| --- | --- | --- | --- | --- |
|  |  | GEF grant | Co-financing |  |
| Inception Workshop | UNDP Country Office | 3,000 | 5,000 | Within two months of project document signature |
| Inception Report | Project Coordinator | None | None | Within two weeks of inception workshop |
| Standard UNDP monitoring and reporting requirements as outlined in the UNDP POPP | UNDP Country Office | None | None | Quarterly, annually |
| Risk management | Project Coordinator Country Office | None | None | Quarterly, annually |
| Monitoring of indicators in project results framework | Project Coordinator | None | 8,000 | Annually before PIR |
| GEF Project Implementation Report (PIR) | Project Coordinator and UNDP Country Office and UNDP-GEF team | None | None | Annually |
| NIM Audit as per UNDP audit policies | UNDP Country Office | 8,000 | 2,000 | Annually or other frequency as per UNDP Audit policies |
| Lessons learned and knowledge generation | Project Coordinator (plus national consultant) | 6,000 | 2,000 | Annually |
| Monitoring of environmental and social risks, and corresponding management plans as relevant | Project Coordinator UNDP Country Office | 5,000 | 5,000 | On-going |
| Stakeholder Engagement Plan | Project Coordinator UNDP Country Office | None | 5,000 | On-going |
| Gender Action Plan | Project Coordinator UNDP Country Office UNDP GEF team | 6,000 | 5,000 | On-going |
| Addressing environmental and social grievances | Project Coordinator UNDP Country Office | None | 2,000 | On-going |
| Project Board meetings | Project Board UNDP Country Office Project Coordinator | None | 8,000 | At minimum annually (preferably twice a year) |
| Supervision missions | UNDP Country Office | None | 5,000 | Annually |
| Oversight missions | UNDP-GEF team | None34 | 5,000 | Troubleshooting as needed |
| GEF Secretariat learning missions/site visits | UNDP Country Office and Project Coordinator and UNDP-GEF team | None | None | To be determined. |
| Mid-term Evaluation | Project Coordinator | 15,000 | 5,000 | At end Year 2 |
| Terminal GEF Tracking Tool to be updated | Project Coordinator | None | 2,000 | Before terminal evaluation mission takes place |
| Independent Terminal Evaluation (TE) included in UNDP evaluation plan, and management response | UNDP Country Office and Project team and UNDP-GEF team | 28,000 | 10,000 | At least three months before operational closure |
| TOTAL indicative COST: Excluding project team staff time, and UNDP staff and travel expenses |  | 71,000 | 69,000 |  |

# Governance and Management Arrangements

- Roles and responsibilities of the project’s governance mechanism: The project will be implemented following UNDP’s NGO implementation modality, according to the Standard Basic Assistance Agreement between UNDP and the Government of Fiji, and the Country Program.

- The Implementing Partner for this project is the Fiji Locally Managed Marine Areas (FLMMA) Network. The Implementing Partner is responsible and accountable for managing this project, including the monitoring and evaluation of project interventions, achieving project outcomes, and for the effective use of UNDP resources.

- The Implementing Partner is responsible for:

- Approving and signing the multiyear workplan;

- Approving and signing the combined delivery report at the end of the year; and,

- Signing the financial report or the funding authorization and certificate of expenditures.

- The project organisation structure is as follows:

Project Organization Structure

Project Board

Chaired by Permanent Secretary of Ministry of Environment and Waterways: Other members are Permanent Secretaries of Ministries of Fisheries, and iTaukei, and a FLMMA Trustee)

(Chair: Secretary MOCC with Representation from Planning, Finance and from Provincial Wildlife Departments,)

Senior Beneficiary

Ministry of Environment and Waterways

Executive:

FLMMA

Senior Supplier

UNDP

FLMMA Technical Advisory Group and short-term consultants

Three Tier Project

Assurance (country, regional and global)

UNDP Fiji Country Office

Program Officer;

Regional Technical Advisor

Project Management Unit

Project Coordinator (contract) and 
co-financed FLMMA Secretariat Staff (Technical Advisor, Coordinator, Finance Officer, IT Officer)

LMMA villages

Yaubula Management Support Teams

Extension Officers of Fishery, Forestry, Conservation Officers and

Fish and Forest Wardens

Field Officer (contract)

- Project Board:  The Project Board (also called Project Steering Committee) is responsible for making by consensus, management decisions when guidance is required by the Project Coordinator including recommendations for UNDP/Implementing Partner approval of project plans and revisions, and addressing any project level grievances. In order to ensure UNDP’s ultimate accountability, Project Board decisions should be made in accordance with standards that shall ensure management for development results, best value money, fairness, integrity, transparency and effective international competition. In case a consensus cannot be reached within the Board, final decision shall rest with the UNDP Program Coordinator.

- The composition of the Project Board would include the Permanent Secretaries of the Ministries of Environment and Waterways, Fisheries, iTaukei Affairs and Forestry and a Trustee of the FLMMA network. The Project Board will be chaired by the Secretary of the Ministry of Environment and Waterways.  Terms of Reference for Project Board is in Annex 4.  The composition of the Project Board will be subject to confirmation during the project inception period. Observers may be included upon agreement of Board members.

- Specific responsibilities of the Project Board include:

- Provide overall guidance and direction to the project, ensuring it remains within any specified constraints;

- Address project issues as raised by the Project Manager;

- Provide guidance on new project risks, and agree on possible countermeasures and management actions to address specific risks;

- Agree on Project Manager’s tolerances as required;

- Review the project progress, and provide direction and recommendations to ensure that the agreed deliverables are produced satisfactorily according to plans;

- Appraise the annual project implementation report, including the quality assessment rating report; make recommendations for the work plan;

- Provide ad hoc direction and advice for exceptional situations when the project manager’s tolerances are exceeded; and

- Assess and decide to proceed on project changes through appropriate revisions

- Executive: The Executive is FLMMA. The Executive is ultimately responsible for the project, supported by the Senior Beneficiary and Senior Supplier.  The Executive’s role is to ensure that the project is focused throughout its life cycle on achieving its objectives and delivering outputs that will contribute to higher-level outcomes. The executive has to ensure that the project gives value for money, ensuring cost-conscious approach to the project, balancing the demands of beneficiary and suppler.

- Specific Responsibilities (as part of the above responsibilities for the Project Board) is to:

- Ensure that there is a coherent project organization structure and logical set of plans;

- Set tolerances in the AWP and other plans as required for the Project Coordinator;

- Monitor and control the progress of the project at a strategic level;

- Ensure that risks are being tracked and mitigated as effectively as possible;

- Brief relevant stakeholders about project progress; and

- Organize and chair project-related Committee meetings.

- Senior Supplier: The Senior Supplier is an individual or group representing the interests of the parties concerned which provide funding and/or technical expertise to the project (designing, developing, facilitating, procuring, implementing). The Senior Supplier’s primary function within the Board is to provide guidance regarding the technical feasibility of the project. The Senior Supplier role must have the authority to commit or acquire supplier resources required. If necessary, more than one person may be required for this role. Typically, the implementing partner, UNDP and/or donor(s) would be represented under this role. The Senior Suppler is: UNDP.

- Specific Responsibilities (as part of the above responsibilities for the Project Board):

- Make sure that progress towards the outputs remains consistent from the supplier perspective;

- Promote and maintain focus on the expected project output(s) from the point of view of supplier management;

- Ensure that the supplier resources required for the project are made available;

- Contribute supplier opinions on Project Board decisions on whether to implement recommendations on proposed changes;

- Arbitrate on, and ensure resolution of, any supplier priority or resource conflicts.

- Senior Beneficiary: The Senior Beneficiary is the Ministry of Environment and Waterways. The Senior Beneficiary’s primary function within the Board is to ensure the realization of project results from the perspective of project beneficiaries.

- The Senior Beneficiary is responsible for validating the needs and for monitoring that the solution will meet those needs within the constraints of the project. The Senior Beneficiary role monitors progress against targets and quality criteria. This role may require more than one person to cover all the beneficiary interests. For the sake of effectiveness, the role should not be split between too many people.

- Specific Responsibilities (as part of the above responsibilities for the Project Board):

- Prioritize and contribute beneficiaries’ opinions on Project Board decisions on whether to implement recommendations on proposed changes;

- Specification of the Beneficiary’s needs is accurate, complete and unambiguous;

- Implementation of activities at all stages is monitored to ensure that they will meet the beneficiary’s needs and are progressing towards that target;

- Impact of potential changes is evaluated from the beneficiary point of view;

- Risks to the beneficiaries are frequently monitored.

- Project Coordinator: The Project Coordinator has the authority to run the project on a day-to-day basis on behalf of the Project Board within the constraints laid down by the Board. The Project Coordinator is responsible for day-to-day management and decision-making for the project. The Project Coordinator’s prime responsibility is to ensure that the project produces the results specified in the project document, to the required standard of quality and within the specified constraints of time and cost.  The project coordinator will reside in Suva will liaise with the Ministry of Environment and waterways and FLMMA to ensure that the project is managed effectively and cost efficiently.

- The Implementing Partner appoints the Project Coordinator, who is different from the Implementing Partner’s representative in the Project Board.  Specific responsibilities include:

- Provide direction and guidance to project team(s)/ responsible party(ies);

- Liaise with the PSC to assure the overall direction and integrity of the project;

- Identify and obtain any support and advice required for the management, planning and control of the project;

- Responsible for project administration;

- Plan the activities of the project and monitor progress against the project results framework and the approved annual workplan;

- Mobilize personnel, goods and services, training and micro-capital grants to initiative activities, including drafting terms of reference and work specifications, and overseeing all contractors’ work;

- Monitor events as determined in the project monitoring schedule plan/timetable, and update the plan as required;

- Manage requests for the provision of financial resources by UNDP, through advance of funds, direct payments or reimbursement using the fund authorization and certificate of expenditures;

- Monitor financial resources and accounting to ensure the accuracy and reliability of financial reports;

- Be responsible for preparing and submitting financial reports to UNDP on a quarterly basis;

- Manage and monitor the project risks initially identified and submit new risks to the PSC for consideration and decision on possible actions if required; update the status of these risks by maintaining the project risks log;

- Manage and monitor the implementation and reporting of safeguards requirements under the project’s SESP .

- Capture lessons learned during project implementation;

- Prepare the annual workplan for the following year; and update the Atlas Project Management module if external access is made available.

- Prepare the GEF PIR and submit the final report to the PSC;

- Based on the GEF PIR and the PSC review, prepare the AWP for the following year.

- Ensure the mid-term review process is undertaken as per the UNDP guidance, and submit the final MTR report to the PSC.

- Identify follow-on actions and submit them for consideration to the PSC;

- Ensure the terminal evaluation process is undertaken as per the UNDP guidance, and submit the final TE report to the PSC;

- The Project Coordinator will function as part of the existing FLMMA Secretariat, the latter serving as a link between the governance structure of FLMMA to the implementation of activities at the community site (LMMA) level.  The Project Coordinator will receive support from staff of the FLMMA Secretariat for implementation of the project.  This will include the Technical Adviser, FLMMA Coordinator, Finance Officer and Information Technology Officer. The Project Coordinator will work through the Field Officer (recruited through the project) to support the implementation of activities at the Southern Lau seascape level. The implementation of the GEF project would benefit from the technical support and guidance of FLMMA Working Groups, LMMA Councilors and Advisors that serve as a vital link between FLMMA partners and communities in carrying out Activities at the LMMA level.  These include in particular, FLMMA’s Design, Administration and Management (DAM) Working Group; FLMMA’s Learning Working Group, FLMMA’s Sustainability Working Group, FLMMA’s Communications and Awareness Working Group and FLMMA’s Compliance and Enforcement Working Group.

- Field Officer:  The Field Officer will be located in the Southern Lau area.  He/she will work closely with the Project Coordinator and FLMMA Secretariat to oversee the planning, management and supervision of project implementation and evaluation across all components in the Southern Lau seascape, applying administrative and financial procedures as required under the national and UNDP procedures, to assure successful implementation and completion of the project in accordance with the stated outcomes and performance indicators summarized in the Project Results Framework. He/she will be supported through an existing combination of divisional representatives, provincial representatives, provincial conservation officers, site Liaison Officers as well as through the decentralized institutions represented by Yaubula Management Support Teams (YMSTs) in Southern Lau.  Detailed Terms of Reference for the Filed Officer is provided in Annex 4.

- Yaubula Management Support Teams (YMSTs):	The YMSTs will help plan and sustain management activities in established LMMA sites in Southern Lau province and take the lead in setting up iQoliqoli (LMMA) management plans, facilitating the integration of off-shore planning and management with land based development plans to promote an integrated ridge-to-reef management approach, provide technical guidance and support through its sector agency staff, provincial conservation officers and provincial fisheries and forestry extension officers, and facilitate integration of LMMA activities within existing provincial planning and budgeting systems. The Field Officer to be located in the Lau Province will directly liaise with the Provincial Government and YMSTs to facilitate and coordinate the planning, implementation and monitoring of project activities in Southern Lau, drawing in the support of the provincial fishery and forestry extension officers, provincial conservation officer and the respective fish and forest wardens at the local level.

- Project Assurance:  UNDP provides a three – tier supervision, oversight and quality assurance role – funded by the GEF agency fee – involving UNDP staff in Country Offices and at regional and headquarters levels. Project Assurance must be totally independent of the Project Management function. The quality assurance role supports the Project Board and Project Management Unit by carrying out objective and independent project oversight and monitoring functions. This role ensures appropriate project management milestones are managed and completed. The Project Board cannot delegate any of its quality assurance responsibilities to the Project Coordinator.  This project oversight and quality assurance role is covered by the GEF Agency.

- Governance role for project target groups:  The Project Board provides the highest level to engage the project beneficiaries in decision-making, as described above. During implementation, a number of other important governance mechanisms will be established (or strengthened or used) for engaging target groups. These include: (i) the YMSTs at Provincial, Cluster, District and Local levels that will be established/strengthened under Output 2.1 for in Southern Lau to facilitate engagement with stakeholders from provincial staff, communities, researchers and the private sector, the latter to the extent relevant; (ii) the existing FLMMA Network as a mechanism to engage NGO and government partners in the planning and implementation of project activities and dissemination of project results and learning; (iii) FLMMA’s Technical Advisory Groups  such as FLMMA’s Design, Administration and Management (DAM) Working Group; FLMMA’s Learning Working Group, FLMMA’s Sustainability Working Group, FLMMA’s Communications and Awareness Working Group and FLMMA’s Compliance and Enforcement Working Group; and (iv) various task forces, that would be established, as appropriate to support the preparation of MPA policy, FLMMA Strategic Plan, Updated Operations Plan and Information Management.

# Financial Planning and Management

- The total cost of the project is USD 4,283,340. This is financed through a GEF grant of USD 805,496, and USD 3,477,844 in parallel co-financing.  UNDP, as the GEF Implementing Agency, is responsible for the execution of the GEF resources and the cash co-financing transferred to UNDP bank account only.

- Parallel co-financing:  The actual realization of project co-financing will be monitored during the mid-term review and terminal evaluation process and will be reported to the GEF. The planned parallel co-financing will be used as follows:

| Co-financing source | Co-financing amount $ |  |  | Planned Activities/Outputs | Risks | Risk Mitigation Measures |
| --- | --- | --- | --- | --- | --- | --- |
|  | Grant | In-kind | Total |  |  |  |
| Ministry of Environment and Waterways | 400,000 | 0 | 400,000 | Inputs across all Component 1 and 3 | No significant risks | Marine biodiversity conservation is core part of mandate |
| Ministry of Fisheries | 750,000 | 0 | 750,000 | Inputs across all Components, particularly Component 1 and 2 | No significant risks | Marine biodiversity conservation is core part of mandate |
| Ministry of iTaukei Affairs (MiTA) | 217,077 | 0 | 217,077 | Inputs across all Components, particularly Component 2 | No significant risks | Marine biodiversity conservation is core part of mandate |
| FLMMA | 433,962 | 177,358 | 611,320 | Inputs across all Components, | No significant risks | Marine biodiversity conservation is core part of mandate |
| Conservation International | 427,000 | 0 | 427,000 | Inputs across all Components, mainly Component 2 | No significant risks | Marine biodiversity conservation is core part of mandate |
| WWF | 250,000 | 0 | 250,000 | Inputs across all Components | No significant risks | Marine biodiversity conservation is core part of mandate |
| IUCN | 725,277 | 0 | 725,277 | Inputs into all Components, particularly Component 1 | No significant risks | Marine biodiversity conservation is core part of mandate |
| Pacific Blue Foundation (PBF) | 0 | 47,170 | 47,170 | Inputs mainly for Component 2 | No significant risks | Marine biodiversity conservation is core part of mandate |
| UNDP | 50,000 | 0 | 50,000 | Inputs mainly for Project Management | No significant risks | Core part of mandate is supervision and oversight |
|  | 3,253,316 | 224,528 | 3,477,844 |  |  |  |
| Total $ | 3,253,316 | 224,528 | 3,477,844 |  |  |  |

Notes:  Since some co-financing contributions were in local currency (FJ$) an exchange rate of 2.12 was used to convert to US$ for the following contributors: MiTA (FJ$ 115,051/Year); FLMMA (Grant FJ$920,000 and In-kind FJ$376,000); IUCN (FJ$ 384,397/Year) and PBF (FJ$25,000/Year)

- UNDP Direct Project Services as requested by Implementing Partner (if any): The UNDP, as GEF Agency for this project, will provide project management cycle services for the project as defined by the GEF Council. In addition, the IP may request UNDP direct services for specific projects according to its policies and convenience. The UNDP and IP acknowledge and agree that those services are not mandatory, and will be provided only upon request. If requested, the services would follow the UNDP policies on the recovery of direct costs. As is determined by the GEF Council requirements, these service costs will be assigned as Project Management Cost, duly identified in the project budget as Direct Project Costs. Eligible Direct Project Costs should not be charged as a flat percentage. They should be calculated on the basis of estimated actual or transaction based costs and should be charged to the direct project costs account codes: “64397- Services to Project– Staff” and “74596- Services to Project – General Operating Expenses (GOE)”.

- Budget Revision and Tolerance:  As per UNDP requirements outlined in the UNDP POPP, the project board will agree on a budget tolerance level for each plan under the overall annual work plan allowing the project manager to expend up to the tolerance level beyond the approved project budget amount for the year without requiring a revision from the Project Board. Should the following deviations occur, the PC and UNDP Country Office will seek the approval of the UNDP-GEF team to ensure accurate reporting to the GEF: a) Budget re-allocations among components in the project with amounts involving 10% of the total project grant or more; b) Introduction of new budget items/or components that exceed 5% of original GEF allocation.

- Any over expenditure incurred beyond the available GEF grant amount will be absorbed by non-GEF resources (e.g. UNDP TRAC or cash co-financing).

- Refund to GEF:  Should a refund of unspent funds to the GEF be necessary, this will be managed directly by the UNDP-GEF Unit in New York.

- Project Closure:  Project closure will be conducted as per UNDP requirements outlined in the UNDP POPP. On an exceptional basis only, a no-cost extension beyond the initial duration of the project will be sought from in-country UNDP colleagues and then the UNDP-GEF Executive Coordinator.

- Operational completion: The project will be operationally completed when the last UNDP-financed inputs have been provided and the related activities have been completed. This includes the final clearance of the Terminal Evaluation Report (that will be available in English) and the corresponding management response, and the end-of-project review Project Board meeting. The Implementing Partner through a Project Board decision will notify the UNDP Country Office when operational closure has been completed. At this time, the relevant parties will have already agreed and confirmed in writing on the arrangements for the disposal of any equipment that is still the property of UNDP.

- Transfer or disposal of assets: In consultation with the Ministry of Environment and Waterways and the Implementing Partner and other parties of the project, UNDP program manager (UNDP Resident Representative) is responsible for deciding on the transfer or other disposal of assets. Transfer or disposal of assets is recommended to be reviewed and endorsed by the project board following UNDP rules and regulations. Assets may be transferred to the government for project activities managed by a national institution at any time during the life of a project. In all cases of transfer, a transfer document must be prepared and kept on file.

- Financial completion:  The project will be financially closed when the following conditions have been met: a) The project is operationally completed or has been cancelled; b) The Implementing Partner has reported all financial transactions to UNDP; c) UNDP has closed the accounts for the project; d) UNDP and the Implementing Partner have certified a final Combined Delivery Report (which serves as final budget revision).

- The project will be financially completed within 12 months of operational closure or after the date of cancellation. Between operational and financial closure, the implementing partner will identify and settle all financial obligations and prepare a final expenditure report. The UNDP Country Office will send the final signed closure documents including confirmation of final cumulative expenditure and unspent balance to the UNDP-GEF Unit for confirmation before the project will be financially closed in Atlas by the UNDP Country Office.

# Total Budget and Work Plan

| Total Budget and Work Plan |  |  |  |
| --- | --- | --- | --- |
| Atlas Proposal or Award ID: | 00116088 | Atlas Primary Output Project ID: | 00113386 |
| Atlas Proposal or Award Title: | Strengthening Fiji’s network of Locally Managed Marine Areas |  |  |
| Atlas Business Unit | FJI10 |  |  |
| Atlas Primary Output Project Title | Strengthening Fiji’s Network of Locally Managed Marine Areas (LMMAs) to Support Globally Significant Marine Biodiversity |  |  |
| UNDP/GEF PIMS No. | 5666 |  |  |
| Implementing Partner | Fiji Locally Managed Marine Area (FLMMA) Network |  |  |

| GEF Component/Atlas Activity | Responsible Party/ (Atlas Implementing Agent) | Fund ID | Donor Name | Atlas Budgetary Account Code | ATLAS Budget Description | Amount Year 1 (USD) | Amount Year 2 (USD) | Amount Year 3 (USD) | Amount Year 4 (USD) | Total (USD) | See Budget Note: |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| COMPONENT 1: National framework for Marine Protected Area (MPA) system incorporating Locally Managed Protected Areas (LMMAs) | FLMMA | 62000 | GEF | 71300 | Local Consultants | 21,000 | 33,000 | 13,500 | 7,500 | 75,000 | 1 |
|  |  |  |  | 72100 | Contractual services (Companies) | 0 | 0 | 5,000 | 0 | 5,000 | 2 |
|  |  |  |  | 71600 | Travel | 3,000 | 5,000 | 3,000 | 1,000 | 12,000 | 3 |
|  |  |  |  | 75700 | Workshops and Training | 12,500 | 30,000 | 30,000 | 10,000 | 82,500 | 4 |
|  |  |  |  |  | sub-total GEF | 36,500 | 68,000 | 51,500 | 18,500 | 174,500 |  |
|  |  |  |  |  | Total Outcome 1 | 36,500 | 68,000 | 51,500 | 18,500 | 174,500 |  |
| COMPONENT 2: Enhanced provincial LMMA network balancing resource use and biodiversity conservation | FLMMA | 62000 | GEF | 71300 | Local Consultants | 12,500 | 30,500 | 18,500 | 18,500 | 80,000 | 5 |
|  |  |  |  | 75700 | Workshops and Training | 4,800 | 14,700 | 14,700 | 10,800 | 45,000 | 6 |
|  |  |  |  | 71600 | Travel | 9,000 | 16,000 | 16,000 | 11,000 | 52,000 | 7 |
|  |  |  |  | 72200 | Equipment and Furniture (Transportation Vehicles) | 33,400 | 3,200 | 3,800 | 1,200 | 41,600 | 8 |
|  |  |  |  | 72500 | Office Supplies | 3,000 | 3,000 | 3,000 | 3,000 | 12,000 | 9 |
|  |  |  |  | 72600 | Grants | 17,500 | 62,500 | 77,500 | 47,500 | 205,000 | 10 |
|  |  |  |  | 73100 | Rental & Maintenance-Premise | 4,800 | 5,100 | 5,100 | 5,200 | 20,200 | 11 |
|  |  |  |  |  | sub-total GEF | 85,000 | 135,000 | 138,600 | 97,200 | 455,800 |  |
|  |  |  |  |  | Total Outcome 2 | 85,000 | 135,000 | 138,600 | 97,200 | 455,800 |  |
| COMPONENT 3: Project learning, knowledge sharing, communication and M&E | FLMMA | 62000 | GEF | 71200 | International Consultants | 0 | 12,000 | 0 | 23,000 | 35,000 | 12 |
|  |  |  |  | 71300 | Local Consultants | 6,000 | 0 | 3,000 | 3,000 | 12,000 | 13 |
|  |  |  |  | 72200 | Equipment and Furniture | 4,000 | 0 | 0 | 0 | 4,000 | 14 |
|  |  |  |  | 71600 | Travel | 0 | 3,000 | 0 | 5,000 | 8,000 | 15 |
|  |  |  |  | 74200 | Audio Visual&Print Prod Costs | 2,000 | 5,000 | 5,000 | 8,000 | 20,000 | 16 |
|  |  |  |  | 75700 | Training, workshop, meetings | 2,000 | 3,000 | 3,000 | 3,000 | 11,000 | 17 |
|  |  |  |  | 72500 | Office Supplies | 1,000 | 1,000 | 1,000 | 1,000 | 4,000 | 18 |
|  |  |  |  | 74100 | Professional services | 2,000 | 2,000 | 2,000 | 2,000 | 8,000 | 19 |
|  |  |  |  |  | sub-total GEF | 17,000 | 26,000 | 14,000 | 45,000 | 102,000 |  |
|  |  |  |  |  | Total Outcome 3 | 17,000 | 26,000 | 14,000 | 45,000 | 102,000 |  |
| Project Management | FLMMA | 62000 | GEF | 71300 | Local Consultants | 14,500 | 14,500 | 14,500 | 14,500 | 58,000 | 20 |
|  |  |  |  | 71600 | Travel | 1,500 | 1,500 | 1,500 | 1,500 | 6,000 | 21 |
|  |  |  |  | 72500 | Office Supplies | 500 | 500 | 500 | 500 | 2000 | 22 |
|  |  |  |  | 73100 | Rental & Maintenance-Premise | 250 | 250 | 250 | 250 | 1,000 | 23 |
|  |  |  |  | 74500 | Miscellaneous | 200 | 200 | 200 | 119 | 719 | 24 |
|  |  |  |  | 64397/ 74596 | DPC- Services to projects - CO staff | 1,000 | 1,000 | 1,000 | 2,477 | 5,477 | 25 |
|  |  |  |  |  | sub-total | 17,950 | 17,950 | 17,950 | 19,346 | 73,196 |  |
|  |  |  |  |  | Total Management | 17,950 | 17,950 | 17,950 | 19,346 | 73,196 |  |
|  |  |  |  | PROJECT TOTAL |  | 156,450 | 246,950 | 222,050 | 180,046 | 805,496 |  |

| Summary of Funds: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  | Amount Year 1 |  | Amount Year 2 |  | Amount Year 3 |  | Amount Year 4 |  | Total |  |
|  |  |  |  | GEF |  |  | 156,450 |  | 246,950 |  | 222,050 |  | 180,046 |  | 805,496 |  |
|  |  |  |  | UNDP |  |  | 10,000 |  | 10,000 |  | 15,000 |  | 15,000 |  | 50,000 |  |
|  |  |  |  | Government |  |  | 341,770 |  | 341,769 |  | 341,769 |  | 341,769 |  | 1,367,077 |  |
|  |  |  |  | NGO |  |  | 515,192 |  | 515,192 |  | 515,192 |  | 515,191 |  | 2,060,767 |  |
|  |  |  |  | TOTAL |  |  | 1,023,412 |  | 1,113,911 |  | 1,094,011 |  | 1,052,006 |  | 4,283,340 |  |

Budget Notes:

| Budget note number | Comments |
| --- | --- |
| Component 1 |  |
| 1 | Local Consultants: (i) National Consultant to develop MPA policy and implementation plan (Output 1.1) – 12 Staff weeks (SWs) x USD 1,500 = USD 18,000; (ii) National consultant to facilitate development of FLMMA Strategic Plan update (Output 1.2) – 6 SW x USD 1,500 = USD 9,000; (iii) National consultant to develop MPA/LMMA operational manual (Output 1.3)– 12 SW x USD 1,500 = USD 18,000: (vi) part cost for Project Coordinator for provision of technical support to Component 1 activities = 7,500 x 4 years = USD 30,000: TOTAL = USD 75,000 |
| 2 | Contractual Services (Companies):(i) Contractual services for translation and printing of operational manual (200 copies) and video of operational techniques (Output 1.3)– USD 5,000: TOTAL =USD 5,000 |
| 3 | Travel: (i) Travel costs for participants for attending workshops and meetings for policy and FLMMA strategy (Outputs 1.1 and 1.2)– USD 5,000; (ii) travel costs for participants for preparation of operational manual workshops and meetings (Output 1.3) + USD 2,000; (ii) Travel costs for conduct of 3 regional community consultation meetings (Output 1.4) – USD 5,000: TOTAL = USD 12,000 |
| 4 | Workshops and Training: (i) National Workshop costs for preparation of MPA/LMMA policy (Output 1.1)– USD 20,000; (ii) community consultation meetings and costs for preparation of MPA/LMMA policy (Output 1.1), including 3 regional consultation workshops at USD 4,000 each = USD 12,000; (iv) National workshop for FLMMA Strategy plan update (two day) (Output 1.2)– USD 5,000; (iv) community validation workshops for FLMMA strategy update (Output 1.2)– USD 7,500; (v) 4 national and regional workshops for preparation of gender sensitive MPA/LMMA operational manual (Output 1.3)– 4 X USD 5,000 = USD 20,000; (vi) national level training workshops for practitioners at national and provincial level for promoting ecosystem-based planning, gender mainstreaming and monitoring of LMMA effectiveness (Output 1.4) in Years 2, 3 and 4 at USD 5,000/year = USD 15,000; and (vii) launch workshop = USD 3,000: TOTAL = USD 82,500 |
| Component 2 |  |
| 5 | Local Consultants: (i) Field technical officer $12,500 x 4 years = USD 50,000; (ii) national consultant for feasibility study of sustainability options for pilot of incentives for LMMA management (Output 2.4) = 8 SWs x USD 1,500 = USD 12,000: (iii) national consultants for technical support for value addition and livelihood development (Output 2.4)= 12 SWs (4SWs for each of YRs 2,3 and 4) x USD 1,500 = USD 18,000: TOTAL = USD 80,000 |
| 6 | Workshops and Training: (i) National level decentralized YMST leadership training workshops for promoting ecosystem-based planning, gender mainstreaming and monitoring of LMMA effectiveness (Output 2.1) one in Year 2, 3 and 4 = 3 x USD 6,000 = USD 18,000; (ii) Village level planning workshops/consultation for preparation of gender sensitive LMMA management plans (Output 2.2) at 3 consultations in each LMMA at USD 400 each with 4, 6, 6 and 4 LMMAs covered in YRs 1, 2, 3 and 4 respectively = USD 400 x 3 x 20 LMMAs = USD 24,000; (iii) workshops for training in spatial planning /drone applications for district and provincial staff (Output 2.3) = USD 3,000: TOTAL = USD 45,000 |
| 7 | Travel: (i) Travel costs for participation in decentralized YMST leadership training workshops (Output 2.1) with 3 (one each in YRs 2, 3 and 4) x USD 2,000 = USD 6,000; (ii) Travel costs associated with financial sustainability studies (Output 2.4) = USD 10,000; (iii) Travel costs associated with village LMMA planning exercises (Output 2.2) at $1,200/LMMA x 20 = USD 24,000: (iv) travel costs for field technical officer at USD 3,000/Year x 4 = USD 12,000: TOTAL = USD 52,000 |
| 8 | Equipment and Furniture (Transportation Vehicles): Equipment such as (i) small moorings for yachts as part of ecotourism initiatives (subject to feasibility assessment) (Output 2.4) = 20 x USD 240 = USD 4,800; (ii) bays/markers and small equipment (Output 2.2) at USD 240/LMMA x 20 = USD 4,800 (at USD 600, USD 1,200, USD 1,800 and USD 1,200 for YRs 1, 2, 3 and 4 respectively); (iv) drones (including motor and part replacement kits) for survey and monitoring of LMMAs (Output 2.2) at 2 x USD 6,000 x 2 = USD 12,000: (v) boats for field technical officer’s office at USD 10,000 x 2= USD 20,000: TOTAL = USD 41,600 |
| 9 | Office supplies: For field technical officer at USD 3,000/year x 4 = USD 12,000 |
| 10 | Grants: Community grants scheme implemented by FLMMA in accordance with UNDP on-granting facility to FLMMA as grant-making institution. Grants include: (i) Community grants to be issued by FLMMA for implementation of LMMA plans (Output 2.4) = 20 LMMA plans x USD 5,900 = USD 118,000; (ii) Community grants for upland rehabilitation of degraded agricultural lands and sustainable land management (Output 2.4) = 20 x USD 1,600 = USD 32,000; (iii) Community grants for livelihood support (Output 2.4) = 20 x USD 2,000 = USD 40,000; (iv) grant support for value addition investments (Output 2.4) = USD 15,000: TOTAL = USD 205,000 |
| 11 | Rental & Maintenance-Premise: Including (i) fuel for boats for field use (Output 2.2) at USD 250/month x 48 months = USD 12,000; (ii) electricity and related operating cost for field technical officer at USD 170/month x 48 months = USD 8,200: TOTAL = USD 20,200 |
| Component 3 |  |
| 12 | International Consultants: (i) International consultant for conduct of mid-term evaluation (Output 3.3) = USD 12,000; (ii) terminal evaluation (Output 3.3) = USD 23,000: TOTAL: USD 35,000 |
| 13 | Local Consultants: (i) National consultant to design KAP survey and develop communication/KM plan and information management system (Outputs 3.1 and 3.2) = 4 SW x USD 1,500 = USD 6,000; (ii) National consultant to document KM products (Output 3.2)= 4 SW x USD 1,500 = USD 6,000; TOTAL USD 12,000 |
| 14 | Equipment and Furniture: (i) Equipment for establishing data management systems (Output 3.1) at Southern Lau including computer, peripherals and soft ware = USD 4,000 |
| 15 | Travel: Travel costs for mid-term review and terminal evaluation (Output 3.3) = USD 8,000 |
| 16 | Audio-visual and Print: (i) Audio-visual and print production of educational and awareness materials (Output 3.2)= USD 15,000; (ii) printing of KM products = USD 5,000: TOTAL USD 20,000 |
| 17 | Training, Workshop, Meeting: (i) Village meetings to create awareness (Output 3.2)= 20 x 2 x USD 200 = USD 8,000; (ii) workshops for training in data collection and management systems (Output 3.1)= USD 3,000; TOTAL USD 11,000 |
| 18 | Office supplies: For awareness programs (Output 3.2)= USD 1,000 x 4 years = USD 4,000 |
| 19 | Audit = USD 8,000 |
| Project Management |  |
| 20 | Local Consultants: Project Coordinator (part costs) = USD 12,500 x 4 years = USD 50,000; (ii) Administrative and financial assistant support (part-time additional cost to FLMMA Secretariat Finance Officer) at USD 2,000 x 4 years = USD 8,000: TOTAL USD 58,000 |
| 21 | Travel: Travel costs for national project coordinator = USD 1,500 x 4 years = USD 6,000: TOTAL USD 6,000 |
| 22 | Office supplies: USD 500 x 4 years = USD 2,000: TOTAL USD 2,000 |
| 23 | Rental & Maintenance-Premise: USD 250 x 4 years = USD 1,000 |
| 24 | Miscellaneous: (including Bank Charges and incidentals) = approx. USD 200/year = USD 719 |
| 25 | UNDP Direct Project Costs for support to procurement, monitoring and partnership arrangements. DPC charge will follow UNDP-GEF specific guidance on DPC, i.e. services must be itemized and associated costs are calculated on the basis of estimated actual or transaction based costs. = USD 5,477 |

# Legal Context

Option a. Where the country has signed the Standard Basic Assistance Agreement (SBAA)

- This project document shall be the instrument referred to as such in Article 1 of the Standard Basic Assistance Agreement between the Government of Fiji and UNDP, signed on 30 October 1970.  All references in the SBAA to “Executing Agency” shall be deemed to refer to “Implementing Partner.”

- This project will be implemented by FLMMA Network (“Implementing Partner”) in accordance with its financial regulations, rules, practices and procedures only to the extent that they do not contravene the principles of the Financial Regulations and Rules of UNDP. Where the financial governance of an Implementing Partner does not provide the required guidance to ensure best value for money, fairness, integrity, transparency, and effective international competition, the financial governance of UNDP shall apply.

- Any designations on maps or other references employed in this project document do not imply the expression of any opinion whatsoever on the part of UNDP concerning the legal status of any country, territory, city or area or its authorities, or concerning the delimitation of its frontiers or boundaries.

# Risk Management

CSO/NGO/Non-UN or other IGO with no signed SBEAA with UNDP

- Consistent with the Article III of the SBAA, the responsibility for the safety and security of the Implementing Partner and its personnel and property, and of UNDP’s property in the Implementing Partner’s custody, rests with the Implementing Partner.  To this end, the Implementing Partner shall:

- Put in place an appropriate security plan and maintain the security plan, taking into account the security situation in the country where the project is being carried;

- Assume all risks and liabilities related to the Implementing Partner’s security, and the full implementation of the security plan.

- UNDP reserves the right to verify whether such a plan is in place, and to suggest modifications to the plan when necessary. Failure to maintain and implement an appropriate security plan as required hereunder shall be deemed a breach of the Implementing Partner’s obligations under this Project Document and the Project Cooperation Agreement between UNDP and the Implementing Partner.

- The Implementing Partner agrees to undertake all reasonable efforts to ensure that no UNDP funds received pursuant to the Project Document are used to provide support to individuals or entities associated with terrorism and that the recipients of any amounts provided by UNDP hereunder do not appear on the list maintained by the Security Council Committee established pursuant to resolution 1267 (1999). The list can be accessed via http://www.un.org/sc/committees/1267/aq_sanctions_list.shtml.

- Social and environmental sustainability will be enhanced through application of the UNDP Social and Environmental Standards (http://www.undp.org/ses) and related Accountability Mechanism (http://www.undp.org/secu-srm).

- The Implementing Partner shall: (a) conduct project and program-related activities in a manner consistent with the UNDP Social and Environmental Standards, (b) implement any management or mitigation plan prepared for the project or program to comply with such standards, and (c) engage in a constructive and timely manner to address any concerns and complaints raised through the Accountability Mechanism. UNDP will seek to ensure that communities and other project stakeholders are informed of and have access to the Accountability Mechanism.

- All signatories to the Project Document shall cooperate in good faith with any exercise to evaluate any program or project-related commitments or compliance with the UNDP Social and Environmental Standards. This includes providing access to project sites, relevant personnel, information, and documentation.

- The Implementing Partner will take appropriate steps to prevent misuse of funds, fraud or corruption, by its officials, consultants, responsible parties, subcontractors and sub-recipients in implementing the project or using the UNDP funds.  The Implementing Partner will ensure that its financial management, anti-corruption and anti-fraud policies are in place and enforced for all funding received from or through UNDP.

- The requirements of the following documents, then in force at the time of signature of the Project Document, apply to the Implementing Partner: (a) UNDP Policy on Fraud and other Corrupt Practices and (b) UNDP Office of Audit and Investigations Investigation Guidelines. The Implementing Partner agrees to the requirements of the above documents, which are an integral part of this Project Document and are available online at www.undp.org.

- In the event that an investigation is required, UNDP has the obligation to conduct investigations relating to any aspect of UNDP programs and projects. The Implementing Partner shall provide its full cooperation, including making available personnel, relevant documentation, and granting access to the Implementing Partner’s (and its consultants’, responsible parties’, subcontractors‘  and sub-recipients’) premises, for such purposes at reasonable times and on reasonable conditions as may be required for the purpose of an investigation. Should there be a limitation in meeting this obligation, UNDP shall consult with the Implementing Partner to find a solution.

- The Implementing Partner will promptly inform UNDP in case of any incidence of inappropriate use of funds, or credible allegation of fraud or corruption with due confidentiality.

- Where the Implementing Partner becomes aware that a UNDP project or activity, in whole or in part, is the focus of investigation for alleged fraud/corruption, the Implementing Partner will inform the UNDP Resident Representative/Head of Office, who will promptly inform UNDP’s Office of Audit and Investigations (OAI). The Implementing Partner shall provide regular updates to the head of UNDP in the country and OAI of the status of, and actions relating to, such investigation.

- UNDP shall be entitled to a refund from the Implementing Partner of any funds provided that have been used inappropriately, including through fraud or corruption, or otherwise paid other than in accordance with the terms and conditions of the Project Document.  Such amount may be deducted by UNDP from any payment due to the Implementing Partner under this or any other agreement.

- Where such funds have not been refunded to UNDP, the Implementing Partner agrees that donors to UNDP (including the Government) whose funding is the source, in whole or in part, of the funds for the activities under this Project Document, may seek recourse to the Implementing Partner for the recovery of any funds determined by UNDP to have been used inappropriately, including through fraud or corruption, or otherwise paid other than in accordance with the terms and conditions of the Project Document.

- Note:  The term “Project Document” as used in this clause shall be deemed to include any relevant subsidiary agreement further to the Project Document, including those with the Implementing Partner, responsible parties, subcontractors and sub-recipients.

- Each contract issued by the Implementing Partner in connection with this Project Document shall include a provision representing that no fees, gratuities, rebates, gifts, commissions or other payments, other than those shown in the proposal, have been given, received, or promised in connection with the selection process or in contract execution, and that the recipient of funds from the Implementing Partner shall cooperate with any and all investigations and post-payment audits.

- Should UNDP refer to the relevant national authorities for appropriate legal action any alleged wrongdoing relating to the project, the Government will ensure that the relevant national authorities shall actively investigate the same and take appropriate legal action against all individuals found to have participated in the wrongdoing, recover and return any recovered funds to UNDP.

- The Implementing Partner shall ensure that all of its obligations set forth under this section entitled “Risk Management Standard Clauses” are passed on to each responsible party, subcontractor and sub-recipient and that all the clauses under this section entitled “Risk Management” are included, mutatis mutandis, in all sub-contracts or sub-agreements entered into further to this Project Document.

# Annexes

Mandatory Annexes

- Multi year Workplan

- (a) GEF Biodiversity –Tracking Tool at baseline (METT) and (b) Reporting template for GEF-7 indicators

- Overview of technical consultancies/subcontracts

- Terms of Reference for Project Board, PMU Positions, etc.

- UNDP Social and Environmental and Social Screening Template (SESP)

- Stakeholder Engagement Plan

- Gender Analysis and Mainstreaming Action Plan

- UNDP Risk Log

- Results of the capacity assessment of the project implementing partner and HACT micro assessment

- Additional agreements: (i) co-financing letters, (ii) PCA; (iii) calculations for Direct Project Services

- UNDP Project Quality Assurance Report

Other Annexes

- Southern Lau biological and socio-ecological profile

- Knowledge Management and Communications Strategy

- UNDP capacity development scorecard

- PPG consultations documentation

- KAP Survey framework

Biodiversity Clearing House Mechanism Fiji:  https://chmfiji.wordpress.com/about/overview-of-fijis-biodiversity/

WWF. 2004. Setting Priorities for Marine Conservation in the Fiji Islands Marine eco-region

Biodiversity Clearing House Mechanism Fiji: https://chmfiji.wordpress.com/about/overview-of-fijis-biodiversity/

MACBIO. National Marine Ecosystem Services Valuation (2014 figures)

Jupiter, S. and D. Egli. 2010. Ecosystem-based management in Fiji: Successes and challenges after five years of implementation. Journal of Marine Biology 2011 (2011), Article ID 940765.

van Dijken, S. 2017. One the edge: in Lau Islands, some marine species are in trouble. http://stories.conservation.org/on-the-edge.

Bruckner, A.W., Dempsey, A.C., Coward, G., Saul, S., Rauer, E.M., and Heemsoth, A. (2016) Global Reef Expedition: Lau Provunce, Fiji. Final Report. Khaled bin Sultan Living Oceans Foundation, Annapolis, MD

A MACBIO 2016 review identified 14 pieces of national legislation as having high relevance to MPAs and 7 national policies/strategies, with a further 9 pieces of legislation and 5 policies as medium relevance.

Meeting the 30% protection target in hectare terms will require the establishment of large marine managed areas under the Offshore Fisheries Management Decree, yet protection of the diverse range of ecosystems including important mangroves, seagrass beds and inshore reefs will rely upon community-based LMMAs that respect customary resource rights.

Jupiter, S. and D. Egli. 2011. Ecosystem-based management in Fiji: successes and challenges after five years of implementation. Journal of Marine Biology, Volume 2011, Article ID 940765.

Govan, H. et al. 2009. Status and potential of locally-managed marine areas in the South Pacific: meeting nature conservation and sustainable livelihood targets through wide-spread implementation of LMMAs. SPREP/WWF/WorldFish-Reefbase/CRISP

As defined by IUCN in the Guidelines for applying the IUCN Protected Area Management Categories to Marine Protected Areas, spatial areas without a stated primary nature conservation objective cannot be considered as MPAs even if they result in nature conservation benefits.

WWF: 2004.  Setting priorities for Marine Conservation in the Fiji Islands Marine Ecoregion

Secretariat of the Convention on Biological Diversity. 2014 EBSAs: Special places in the world’s oceans, Volume 1: Western South Pacific.

Yamamoto, T., Takahashi, A., Katsumata, N., Sato, K. and Trathan, P.N. 2010. At-sea distribution and behavior of streaked shearwaters (Calonectris leucomelas) during the nonbreeding period. The Auk 127 (4): 871-881.

Tuiwawa, M. and Aalbersberg, W. 2013. Rapid Biological Assessment Survey of Southern Lau, Fiji. Biodiversity Conservation Lessons Learned Technical Series 22. Conservation International Pacific Islands Program, Apia, Samoa.

Meyers, A.A. 1985. Shallow water, coral reefs, and mangrove amphipoda (Gammaridea) of Fiji. Records of the Australian Museum Supplement, 0812-7387.

Flu et al. (2010)

Meo, S. (personal communication)

MACBIO (2018) Biophysically Special Unique Marine Areas of Fiji

Batibasaga, A. Ministry of Fisheries (2016)

MACBIO (2018) Biophysically Special Unique Marine Areas of Fiji

ibid

The monitoring includes both community questionnaires (e.g. covering governance, management and enforcement) and ecological monitoring, taking place at both a basic (Level 1) and advanced (Level 2) level.

As a cost effective maintenance effort, the project will purchase medium cost robust drones with motor replacement, batteries and movable parts kits that are easy to operate with training. FLMMA Project field technical officer, Provincial fisheries and environmental enforcement officers and community fish and forest wardens will be trained to operate these drones.

The role and engagement of women in fisheries in Fiji, Women in Fisheries Network (2014)

The survey sampling questionnaire and methodology will be developed in the first quarter of the first year of the project and measurement taken at baseline, MTR and TE.  Sample villages will be selected in each of the LMMA clusters and Households will be selected using a 25-50% (depending on the number of HHs in the selected villages) random sample in each village. The questionnaire will be developed in consultation with the Ministry of ITaukei Affairs and Women in Fisheries Network.  The survey will cover women's voices in planning in LMMAs, defining zoning and no-take zones, harvest rates, monitoring and fish processing and marketing and access to marketing technologies, access etc.)

See http://www.undp.org/content/undp/en/home/operations/transparency/information_disclosurepolicy/

See https://www.thegef.org/gef/policies_guidelines

See https://www.thegef.org/gef/policies_guidelines

See https://www.thegef.org/gef/gef_agencies

See guidance here:  https://info.undp.org/global/popp/frm/pages/financial-management-and-execution-modalities.aspx

Excluding project team staff time and UNDP staff time and travel expenses.

Includes costs of national and provincial, YMSTs and community training in gender mainstreaming within training workshop costs in Components 1 and 2

The costs of UNDP Country Office and UNDP-GEF Unit’s participation and time are charged to the GEF Agency Fee.

see  https://info.undp.org/global/popp/ppm/Pages/Closing-a-Project.aspx

See https://popp.undp.org/_layouts/15/WopiFrame.aspx?sourcedoc=/UNDP_POPP_DOCUMENT_LIBRARY/Public/PPM_Project%20Management_Closing.docx&action=default.