## Working sheet 2014 (hidden)
Sustainable Land Management in Churia Region Nepal (GEF funded)
Year 1 (CY14) |  |  | Year 2 (CY15) |  | Year 3 (CY16) |  | Total
Budget | Expense | Spending % | Budget | Expense | Budget | Expense | Budget | Expenses | Spending %
381537.5 | 285038.04 | 74.71% | 301292.3733 | 0 | 234601.1987 | 0 | 917431.072 | 285038.04 | 31.07%
Savings from 2014
Exp Jun-Dec | 99253.17
Exp Jan-Jun | 210890.72
Total | 310143.89 | exp reported to HQ | grant and consultancy obligation
Savings | 71393.61 | 285038.04 | 25105.85 | 96499.46
2015 Budget | 397791.8333
Activities transferred to 2015 from 2014
2201 | Obligation Deductable - Grants
| WT47 |  |  |  |  | -10024 | -103.78
| WT81 |  |  |  |  | -388765.62 | -4042.69
| WT82 | [5 empty] | -0.97
| WT83 |  |  |  |  | -1781813 | -18359.25
| WU22 |  |  |  |  | -20800 | -218.99
| Total |  |  |  |  | -2201402.62 | -22725.68
2206/07 | Obligation Deductable - Consultancy
| WU62 |  |  |  |  | -150650 | -1529.91
| WV81 |  |  |  |  | -85000 | -850.26
| Total |  |  |  |  | -235650 | -2380.17
| Total of grants and consultancy | [5 empty] | -25105.85 | reconciled
Note on K9: Author: DSA, communication and monitoring visits; implementing visits For all 4 project sites and implementing partners

## Guidance
Guidance
This template serves two functions: 1) Template for drafting the Annual Work Plan and Budget (AWP&B), based on the full project workplan. The purpose of the AWP&B is to ensure that activities planned for the project year will be successful at meeting the Results Framework targets, and are budgeted correctly. 2) Tracking progress against the Work Plan and Budget and the Results Framework (RF). Formulas are built into the AWP&B and Results Framework tabs to support tracking, and this is based on an average achievement of all activities/RF targets. Progress is rated annually in the Project Progress Report – the Implementation Progress Rating corresponds to AWP&B achievement, while the Development Objective Rating corresponds to achievement against the RF. One should not have over 100% achievement even if the target was exceeded.
Drafting the Annual Work Plan and Budget Output tracking (light orange row in AWP&B tab): Achievement of each output should be monitored over the lifetime of the project. If the activities underneath the output provide sufficient information on whether or not an output was achieved, no separate output target/indicator is required. Only include a target if the output is expected to be achieved for the given project year. Activities: Activities should be developed based on the ProDoc and what is needed to meet the Results Framework targets. Include relevant activities related to the Gender Action Plan and Stakeholder Engagement Plan. Please ensure alignment with the overall project workplan and ensure that the activities are relevant towards achieving the outputs. The outputs then should be relevant to achieving the results in the Results Framework. Targets/Units: Targets should always be numerical. The unit being measured should be included (e.g. # of meetings). Work plan (timing): The time dedicated to a given activity should be noted by project quarter (or, if the team prefers, by month). Budget: The budget can be provided by output or activity, and should be based off of the submitted and approved detailed budget. At the end of the year, budget spent v. activities planned and achieved can be assessed to show variance and alignment in spending and implementation. Budget variances of 5% or more at the total component level (as approved in ProDoc) needs to be approved by the WWF GEF Agency. Project Management Costs (PMC) cannot go over the total amount approved by GEF.
Tracking during Implementation In the AWP&B, progress can be tracked at the end of each project year under the columns labeled “Work Plan Tracking (Column M-P).” In the Results Framework, please track progress against targets in columns "actual" and "% achieved" for each year reported. Note that formulas will need to be adjusted if columns or rows have been added to this template. IP Rating: The project Implementation Progress (IP) rating is determined by averaging the achievement of all activities together in the workplan, rather than taking the average of component averages. Note that even if the project has exceeded an intended target associated with an activity (>100%), the rating will have to be manually adjusted to 100% to not skew the average. If there is a gender target in addition to a total target, both will contribute equally to the level of acheivement. DO Rating: The project Development Objective (DO) rating is determined by averaging the percent achievement of all indicators in the RF. Please note that some indicators have multiple measurements per indicator (e.g. 1 platform established with 200 registered users and 100 KM products) and it is recommended to average the achievement of all measurements taken per indicator (E.g. 1 platform, 100 users and 20 KM products would be 100% + 50% + 20% = 56%). The same would apply for a gender target. The snapshot tab will show a summary of progress again the AWP&B and RF over the life of the project.
Full Project Workplan The annual workplan activities and targets should align with the full project workplan, so please ensure that targets are cumulative through the end of the project and that the full suite of activities are represented. The template may need to be adjusted.
Additional Notes This completed spreadsheet will be submitted for approval of the AWP&B for planning purposes. Once the tracking aspects of the AWP&B and RF are completed, it will also be submitted and annexed to the annual Project Progress Report for reporting purposes. This template was designed for six years and five components, but please adjust this template to fit the realities of this project by inserting additional rows or columns. Please note that there are forumulas already input into the template that will need to be adjusted if you do add rows or columns. The password is Heike to unlock the sheet to input the formulas.

## Snapshot
Project: 9437-Integrated Landscape Management to Secure Nepal’s PAs and Critical Corridors
SNAPSHOT
Annual Work Plan Activity Tracking: Summary | [6 empty] | Results Framework Tracking: Summary
| % achievement | [5 empty] | Year | % average achievement
Component | Y1 | Y2 | Y3 | Y4 | Y5 | Y6
Component 1 | N/A | 30.67% | 26.67% | 45.76% | 50% | 0% | Y1 | N/A
Component 2 | N/A | 20% | 46.07% | 49.34% | 66.88% | 0% | Y2 | 39.63%
Component 3 | N/A | 47.52% | 70% | 57.55% | 68.67% | 0% | Y3 | 67.62%
Component 4 | N/A | 63.08% | 82.5% | 80.46% | 71.63% | 0% | Y4 | 61.84%
Average Activities | N/A | 44.87% | 60.71% | 60.11% | 64.85% | 0% | Y5 | 70.27%
Y6

## Results Framework
RESULTS MEASUREMENT FRAMEWORK
OUTCOME | INDICATOR | DEFINITION | METHOD | WHO | DISSAGREGATION | BASELINE | YR1 July 1, 2020 - June 30, 2021 |  |  | YR2 July 1, 2021 - June 30, 2022 |  |  | YR3 (July 1, 2022 - June 30, 2023) |  |  | YR4 (July 1, 2023 - June 30,2024) |  |  | YR5 (July 1, 2024 - June 30, 2025) |  |  | YR6 (July 1, 2025 - June 30, 2026) |  |  | Assumption
[7 empty] | Target | Actual | % achieved | Target | Actual | % achieved | Target | Actual | % achieved | Target | Actual | % achieved | Target | Actual | % achieved | Target | Actual | % achieved
Project Objective: To promote integrated landscape management to conserve globally significant forests and wildlife
Global Environmental Benefits | Core Indicator 3. Area of land and ecosystems under restoration in hectar | Cumulative in hectar This indicator captures the area of forest and forest land that is undergoing ecological restoration through GEF-funded interventions. The intent is to capture the area in which best practices for ecological restoration are being applied. Measured as hectares undergoing restoration through direct intervention in project intervention areas in targeted TAL buffer zones and corridors | Map/monitor extent of the degraded land being restored and also to indicate the relative state of the area prior to GEF activities. | PMU | Total | 0 |  |  |  | 0 | 72.5 |  | 350 | 336.8 | 71.57% | 1200 | 1122.6 | 64.2% | 2350 | 2011.16 | 82.24% | 4050 | 0 | 0% | Drought and forest fires do not adversely impact habitat restoration outcomes. Through C3 intervention. Break down figures by target area units: BNP BZ, BaNP BZ, Kamdi and Karnali Corridors May require GIS support
| Sub-Indicator 3. 1. Area of degraded agricultural lands under restoration |  |  | PMU | GEF Sub-indicator 3.1: Area of degraded agricultural lands restored (ha) | 0 |  |  |  | 0 | 9.6 |  | 50 | 9.6 | 19.2% | 100 | 9.6 | 9.6% | 150 | 123.18 | 82.12% | 150 |  | 0%
| Sub-Indicator 3. 2. Area of forest and forest land under restoration |  | GIS land cover / habitat classification maps for target areas to calculate baseline and restored areas | PMU | GEF Sub-indicator 3.2: Area of forest and forest land restored (ha) | 0 |  |  |  | 0 | 0 |  | 200 | 191 | 95.5% | 800 | 664 | 83% | 1600 | 1033.48 | 64.59% | 2900 |  | 0%
| Sub-Indicator 3. 3. Area of natural grass and woodlands under restoration |  | see above | PMU | GEF Sub-indicator 3.3: Area of natural grass and shrublands restored (ha) | 0 |  |  |  | 0 | 62.9 |  | 100 | 136.2 | 100% | 300 | 449 | 100% | 600 | 854.5 | 100% | 1000 |  | 0%
| Core Indicator 4: Area of landscapes under improved practices (hectares; excluding protected areas) | Cumulative in hectar | Calculated using GIS; Land use and management plans; Monitoring reports; Field reports | PMU executing partners |  | 0 | 0 | 0 |  | 0 | 0 |  | 500 | 129.18 | 25.84% | 2000 | 1619 | 80.95% | 3000 | 3056.25 | 100% | 233500 | 0 | 0% | Through all components. This indicator applies to all corridors in TAL, which will have updated / improved management plans. In this case, could use the Protected Forest areas as the figure for GEF subindicator 4.1
| Sub-indicator 4.1: Area of landscapes under improved management to benefit biodiversity | This indicator captures the landscape area being managed to benefit biodiversity, but which is not certified. |  |  |  | 0 | 0 |  |  | 0 | [5 empty] | 0 |  |  | 0 |  |  | 229500 |  | 0%
| Sub-indicator 4.3: Area of landscapes under sustainable land management in production systems | This indicator captures the landscape area that is in production (e.g., agriculture, rangeland, and forests) and whose soil, air, and water are managed in a sustainable manner |  |  |  | 0 | 0 |  |  | 0 |  |  | 500 | 129.18 | 25.84% | 2000 | 1619 | 80.95% | 3000 | 3056.25 | 100% | 4000 |  | 0%
| Core Indicator 6: Greenhouse gas emission mitigated Sub-indicator 6.1: Carbon sequestered, or emissions avoided in the AFOLU sector | Carbon sequestration is defined as the process of increasing the carbon content of a reservoir/pool other than the atmosphere (IPCC, 2012). Avoided emissions refers to reduced emissions due to avoided deforestation or forest degradation, sustainable forest management, and improved practices on other land uses such as in agriculture. Through project interventions in TAL. | t/ha/yr calculated using FAO EX-ACT Tool | PMU, executing partners | n/a | 0 | 0 |  |  | 0 | [5 empty] | 500000 | 500955 | 100% |  |  |  | 1270919 |  | 0% | Forest fires do not adversely impact carbon sequestration in project areas
| GEF Core Indicator 11: Number of direct beneficiaries disaggregated by gender as co-benefit of GEF investment | . a) Community members in targeted CFUGs and BZUGs in intervention areas receiving capacity development / training; disaggregated by gender | Cumulative Direct beneficiary: individual who receives targeted support from a given GEF project and/or who uses specific resources that the project maintains or enhances ILM4TAL field project report and database Training reports | M&E Officer-ILM4TA | Women | 0 | 847 | 305 | 100% | 847 | 305 | 100% | 2895 | 4800 | 100% | 3793 | 6197 | 100% | 4141 | 7345 | 100% | 3193 |  | 0%
[5 empty] | Men | 0 | 848 | 2433 | 100% | 848 | 2433 | 100% | 2895 | 4809 | 100% | 3793 | 6241 | 100% | 4141 | 6944 | 100% | 3194 |  | 0%
[5 empty] | Total | 0 | 1695 | 2738 | 100% | 1695 | 2738 | 100% | 5790 | 9609 | 100% | 7586 | 12438 | 100% | 8282 | 14289 | 100% | 6387 |  | 0%
|  | b) Government staff receiving capacity development / training from the project , disaggregated by gender and federal/state/local government | ILM4TAL field project report and database Training reports | M&E Officer-ILM4TA | Women | 0 | 30 |  | 0% | 30 |  | 0% | 38.8 | 33 | 85.05% | 40 | 61 | 100% | 37 | 47 | 100% | 66 |  | 0%
[5 empty] | Men | 0 | 268 |  | 0% | 268 |  | 0% | 349 | 271 | 77.65% | 365 | 424 | 100% | 268 | 454 | 100% | 154 |  | 0%
[5 empty] | Total |  | 298 | 422 | 0% | 298 | 422 | 0% | 387.8 | 304 | 81.35% | 405 | 485 | 100% | 305 | 501 | 100% | 220 | 0 | 0%
[5 empty] | Total ALL beneficiaries | 0 | 1993 | 3160 | 50% | 1993 | 3160 | 50% | 6177.8 | 9913 | 90.68% | 7991 | 12923 | 100% | 8587 | 14790 | 100% | 6607 | 0 | 0%
[5 empty] | Average percent achievement (50% weight on gender) Indicator 11 |  |  |  | 50% |  |  | 50% |  |  | 91.6% |  |  | 100% |  |  | 100% |  |  | 0%
Project Objective achievement: | [8 empty] | 50% |  |  | 50% |  |  | 66.43% |  |  | 78.92% |  |  | 89.34% |  |  | 0%
COMPONENT 1: National capacity and enabling environment for cross-sectoral coordination to promote forest and landscape conservation
Outcome 1.1: Improved inter-sectoral coordination from Federal, State to Local level for sustainable forest management and integrated landscape management | Number of Cross-sectoral coordination mechanisms strengthened and/or newly established and meeting regularly at Federal, State and Local levels # mechanisms at each level Cumulative | Mechanisms will include: Federal, State, District and Municipal coordination committees, etc. (see Output 1.1.1) and will only be counted if meeting regularly (minimum quarterly) Strengthened = Legal/administrative recognition of the coordination body (where necessary); ToR review and improvement; membership to include relevant stakeholders; rules and procedures reviewed to be fit for function; regular meetings held | Percentage of agency staff responsible for ILM coordination functions at federal and state levels (including NBCC, NBCC Subcommittees and State Biodiversity Coordination Committees for States 2,3,5,7 and Karnali) that have participated in project supported training on conservation leadership and ILM related subjects % staff Cumulative | PMU. Executing partners | Federal | 2 | 0 |  |  | 0 |  |  | 0 |  |  | 2 |  | 0% |  |  |  | 2 |  | 0% | Sectoral agencies are willing to cooperate at federal, state and local levels to achieve ILM.
[5 empty] | State | 0 | 0 | 1 |  | 0 | 1 |  | 0 |  |  | 1 | 1 | 100% |  |  |  | 2 |  | 0%
[5 empty] | Local | 2 | 0 |  |  | 0 |  |  | 0 |  |  | 3 |  | 0% |  |  |  | 3 |  | 0%
[5 empty] | Total | 4 | 0 | 1 |  | 0 | 1 |  |  |  |  | 6 | 1 | 16.67% | 0 | 0 |  | 7 | 0 | 0%
Outcome 1.2: Capacity increased for multi-stakeholder and cross-sector landscape and forest planning and management | Percentage of agency staff responsible for ILM coordination functions at federal and state levels (including NBCC, NBCC Subcommittees and State Biodiversity Coordination Committees for States 2,3,5,7 and Karnali) that have participated in project supported training on conservation leadership and ILM related subjects % staff Cumulative | The target group here is all staff participating in biodiversity coordination committees and subcommittees at federal and state agencies. As some of these committees will only be established during project implementation, training can only start after their establishment. Training will also seek to address staff turnover on these committees. | Reports on project training events | PMU | Federal | 0% | 20% |  | 0% | 20% |  | 0% | 50% | 65% | 100% | 70% | 0% | 0% | 90% | 0% | 0% | 100% |  | 0% | Biodiversity coordination committees and subcommittees are established at federal and state levels during the course of project implementation and representatives agree to attend training courses
[5 empty] | State | 0% | 0% |  |  | 0% | [5 empty] | 30% | 0% | 0% | 60% | 0% | 0% | 80% |  | 0%
Component 1 achievement: | [8 empty] | 0% |  |  | 0% |  |  | 100% |  |  | 20% |  |  | 0% |  |  | 0%
COMPONENT 2: Integrated Planning for Protected Area Buffer Zones and Critical Corridors in the Terai Arc Landscape
Outcome 2.1: Improved corridor planning for TAL corridors (Brahmadev, Karnali and Kamdi) | # of TAL corridors assessed for improved community-based natural resource governance status that includes biodiversity conservation # surveys Non-Cumulative | Biodiversity surveys, socio-economic surveys, and local stakeholder consultation for Brahmadev, Karnali, and Kamdi corridors to determine feasibility of appropriate models for community-based natural resource management and strategic framework development, including KBA assessments |  | PMU | # of surveys completed for each corridor | 0 | [6 empty] | 3 | 6 | 100% | 9 | 6 | 66.67% | 9 | 1 | 11.11% |  |  |  | The MoFE, State and local government agencies provide political and financial support for the protection and sustainable management of forest resources in critical corridors
[18 empty] | 86.11% |  |  | 61.25%
Outcome 2.2: Improved participatory planning for sustainable management of in Banke-Bardia complex | No. of CFUGs in Kamdi and Karnali Corridors with updated forest operation plans addressing SFM and biodiversity conservation # CFUGs Cumulative |  |  | PMU, executing partners | Kamdi corridor x out of out of 76 CFUGs have updated FMOPs | 11 | [6 empty] | 20 | 12 | 60% | 30 | 25 | 83.33% | 50 | 25 | 50% | 76 |  | 0%
[5 empty] | Karnali corridor out of 54 CFUGs have updated FMOPs | 0 | [6 empty] | 15 | 12 | 80% | 27 | 24 | 88.89% | 40 | 29 | 72.5% | 54 |  | 0%
100%
| % change in Area Weighted Mean Patch Area (AREA_AM) to determine connectivity of forest cover in targeted corridors | Area Weighted Mean Patch Area (AREA_AM) is the sum across all patches of the corresponding patch value multiplied by the proportional patch area divided by the sum of patch areas (McGarigal et al., 2012). Increase in patch size indicate merger of patches and thus decrease in fragmentation of particular patch type. | Measured by GIS analysis of satellite imagery of forest cover in targeted corridors and PA buffer zones, for sample areas. Programmes such as FRAGSTATS can be used for analysis: https://www.umass.edu/landeco/research/fragstats/fragstats.html | Project GIS staff | Kamdi corridor | 3767.1673 | [9 empty] | 4821 | 5034 | 100% |  |  |  | >5% increase in mean patch size over baseline |  | #VALUE! | Forest fires do not adversely impact forest corridor connectivity
[5 empty] | Karnali corridor | 5687.627 | [9 empty] | 3784 | 5876 | 100% |  |  |  | >5% increase in mean patch size over baseline |  | #VALUE!
Component 2 achievement: | [14 empty] | 80% |  |  | 89.81%
COMPONENT 3: COMPONENT 3: Forest and human-wildlife conflict management for improved conservation of targeted protected area buffer zones and corridors in the Terai Arc Landscape
Outcome 3.1: Strengthen livelihoods and biodiversity conservation through Sustainable forest management practices | ) No. forest fire incidents in targeted corridor / BZ per year % Cumulative | Number of forest fire occurrences detected by remote sensing. See separate sheet for ICIMOD data | ICIMOD forest fire monitoring data | PMU | Kamdi | 74 |  |  |  | 5.8 |  | 0% | 70.3 | 55 | 100% | 5.22 | 7 | 100% | 47 | 5 | 100% | 4.64 |  | 0%
[5 empty] | Karnali | 114 |  |  |  | 5 |  | 0% | 108.3 | 152 | 0% | 4.5 | 8 | 100% | 129 | 3 | 100% | 4 |  | 0%
[5 empty] | Banke | 505 |  |  |  | 20.4 |  | 0% | 479.75 | 15 | 100% | 18.36 | 107 | 100% | 429 | 36 | 100% | 16.32 |  | 0%
[5 empty] | Bardia | 505 |  |  |  | 24.2 |  | 0% | 479.75 | 118 | 100% | 21.78 | 163 | 100% | 429 | 69 | 100% | 19.36 |  | 0%
[5 empty] | Total | 1198 |  |  |  | 55.4 | 0 | 0% | 1138.1 | 340 | 75% | 49.86 | 285 | 100% | 1034 | 113 | 100% | 44.32 | 0 | 0%
| b) % CFUGs managing open grazing out of total number in the targeted corridor / buffer zone | Open grazing: unrestricted grazing of cattle on lands covered by Community Forest, Protected Forest, Protected Area and PA Buffer Zone designations | Surveys of CFUGs in targeted areas | PMU | Kamdi corridor 11 out of out of 76 CFUGs have imposed bans and 50 allow rotational grazing | 65 | [6 empty] | 9.75 | 3 | 30.77% | 16 | 11 | 68.75% | 26 | 18 | 69.23% |  |  |  | The management of grazing is supported by relevant agencies to ensure that livestock herders continue to receive benefits under new grazing management regimes
[5 empty] | Karnali corridor all 54 CFUGs allow grazing | 54 |  |  |  | 54 |  | 0% | 8.1 | 1 | 12.35% | 13 | 7 | 53.85% | 21 | 13 | 61.9%
[5 empty] | Total | 119 |  |  |  | 54 | 0% | 0% | 17.85 | 4 | 21.56% | 29 | 18 | 61.3% | 47 | 31 | 65.57% | 0 | 0 |  | Gender mainstreaming and the rights of indigenous peoples are accepted and supported by federal, state and local government leaders
| a) Women, resident indigenous peoples and marginalized groups empowered for CBNRM in targeted corridors and buffer zones as indicated by: a) Number of womens’, indigenous peoples and Dalit groups established for CBNRM and livelihood activities # communities Non-cumulative | Definitions for indigenous peoples and Dalit follows that used in the Safeguards assessment (see Annex X of ProDoc) |  | Executing partners | Women's group | 0 |  |  |  | 0 |  |  | 5 | 2 | 40% | 10 | 8 | 80% | 10 | 9 | 90% | 10 |  | 0%
[5 empty] | IP groups | 0 |  |  |  | 0 |  |  | 5 | 5 | 100% | 10 | 6 | 60% | 10 | 10 | 100% | 10 |  | 0%
[5 empty] | Dalit groups | 0 |  |  |  | 0 |  |  | 2 | 1 | 50% | 5 | 2 | 40% | 5 | 3 | 60% | 5 |  | 0%
[5 empty] | Total | 0 |  |  |  | 0 | 0 |  | 12 | 8 | 63.33% | 25 | 16 | 60% | 25 | 22 | 83.33% | 25 | 0 | 0%
| b) Number of indigenous peoples and Dalit communities engaged in project CBNRM and livelihood interventions # communities Non-cumulative |  |  |  | IP groups | 0 |  |  |  | 0 |  |  | 5 | 4 | 80% | 10 | 6 | 60% | 10 | 9 | 90% | 10 |  | 0%
[5 empty] | Dalit groups | 0 |  |  |  | 0 |  |  | 2 | 0 | 0% | 5 | 2 | 40% | 5 | 3 | 60% | 5 |  | 0%
[5 empty] | Total | 0 |  |  |  | 0 | 0 |  | 7 | 4 | 40% | 15 | 8 | 50% | 15 | 12 | 75% | 15 | 0 | 0%
| c) Average percentage of female, indigenous and Dalit recipients of project-related loans for community level enterprise and livelihood support % female, IP and dalit recipients of total recipients Non-cumulative | The average should be applied across all communities receiving project-supported revolving loan schemes, allowing for variation in percentages in individual communities (for instance, higher percentages of IP loans are expected in Tharu areas) | Disaggregated by community, then summed and averaged | Executing partners | Female | 0 |  |  |  | 0% |  |  | 60% | 0% | 0% | 60% | 0% | 0% | 60% |  |  | 60% |  | 0%
[5 empty] | IP | 0 |  |  |  | 0% |  |  | 25% | 0% | 0% | 25% | 0% | 0% | 25% |  |  | 25% |  | 0%
[5 empty] | Dalit | 0 |  |  |  | 0% |  |  | 10% | 0% | 0% | 10% | 0% | 0% | 10% |  |  | 10% |  | 0%
[5 empty] | Total | 0 |  |  |  | 0% | 0% |  | 95% | 0% | 0% | 95% | 0% | 0% | 95% |  |  | 95% | 0% | 0%
| d) Average percentage of female, indigenous and Dalit participants in project-related training for CBNRM and livelihood activities % female, IP and dalit recipients of total recipients Non-cumulative | The average should be applied across all communities receiving project-supported revolving loan schemes, allowing for variation in percentages in individual communities (for instance, higher percentages of IP loans are expected in Tharu areas) | Disaggregated by community, then summed and averaged | Executing partners | Female | 0 |  |  |  | 0% |  |  | 60% | 25% | 41.67% | 60% | 50% | 83.33% | 60% | 46% | 76.67% | 60% |  | 0%
[5 empty] | IP | 0 |  |  |  | 0% |  |  | 25% | 45% | 100% | 25% | 36% | 100% | 25% | 39% | 100% | 25% |  | 0%
[5 empty] | Dalit | 0 |  |  |  | 0% |  |  | 10% | 5% | 50% | 10% | 13% | 100% | 10% | 9% | 90% | 10% |  | 0%
[5 empty] | Total | 0 |  |  |  | 0% | 0% |  | 95% | 75% | 63.89% | 95% | 99% | 94.44% | 95% | 94% | 88.89% | 95% | 0% | 0%
Outcome 3.2: Improved management of the human-wildlife conflict | Reduced incidence of HWC in localities where related project activities occur within targeted corridor and PA buffer zone areas | HWC: actions by humans or wildlife that have an adverse effect on the other |  |  | Targeted locations for HWC related activities in PA BZs and Corridors | 194 |  |  |  | 0 | 0 |  | 174 | 165 | 94.83% | 999 | 1684 | 25% | 1811 | 2965 | 100% | 0 | 0 |  | HWC records are systematically collected and maintained by the government
| a) No. livestock taken / year % Cumulative | Definition to follow local government HWC reporting system | Local Government statistics/ reports; and project location-specific reports | M&E Officer-ILM4TAL | a) No. livestock taken / year - to be determined for targeted locations - TBC | 1052 | [6 empty] | 947 | 1097 | 0% | 842 | 1511 | 0% | 736 | 1538 | 0%
| b) Damage to houses/year Area of cropland protected (ha) % Cumulative |  |  |  | b) Damage to houses/year - for targeted locations: 256 Bardia Area of cropland protected (ha) | 87 | [6 empty] | 78 | 49 | 100% | 70 | 83 | 0% | 1000 | 1382 | 100%
| c) Human fatalities and injuries / year % Cumulative |  |  |  | c) Human fatalities and injuries / year - for targeted locations: 5 killed and 3 injured in Bardia | 21 | [6 empty] | 19 | 19 | 100% | 17 | 10 | 100% | 15 | 15 | 100%
| d) Number of wildlife fatalities on national park roads % Cumulative | Wildlife fatalities - number of wild animals killed in road accidents along identified road stretches during set time periods |  |  | No. wild animals killed in road accidents 66 in Bardia and 58 in Banke NPs in FY 2016/17 | 86 | [6 empty] | 77 | 97 | 100% | 70 | 80 | 0% | 60 | 30 | 100%
Outcome 3.3: Enhanced capacities of government agencies and community in curbing illegal wildlife crime | # reported cases of poaching in targeted PA Buffer Zones and Corridors per year by species # cases Non-cumulative | Poaching: illegal killing of wildlife | CBAPU reports, DFO reports | M&E Officer-ILM4TAL | By species and BZ/Corridor | Zero poaching in Banke and Bardiya in Fiscal year 2016/17. No information available for corridors |  |  |  | Systematic reporting of poaching incidents established for targeted BZs/Corridors |  |  | 0 | 0 |  |  |  | 75% |  |  | 25%
[5 empty] | Banke | 0 | [6 empty] | 0 | 2 |  | 0 | 1 | 0% | 0 | 3 | 0%
[5 empty] | Bardia | 0 | [6 empty] | 0 | 0 | 100% | 0 | 0 | 100% | 0 | 2 | 0%
[5 empty] | Kamdi corridor | NA | [6 empty] | 0 | 0 | 100% | 0 | 0 | 100% | 0 | 3 | 0%
[5 empty] | Karnali corridor | NA | [6 empty] | 0 | 1 | 0% | 0 | 0 | 100% | 0 | 0 | 100%
Component 3 achievement: | [11 empty] | 0% |  |  | 55.86% |  |  | 63.81% |  |  | 76.83% |  |  | 0%
COMPONENT 4: Monitoring and evaluation (M&E), knowledge management (KM), and regional coordination
Outcome 4.1: Improved coordination and dialogue on integrated landscape management from the local to national level | Number of stakeholders participating in annual forums (indicates that national, provincial and local stakeholders involved with TAL are informed of progress and participate in discussion of project-related issues) # stakeholders Non-cumulative | Participate: take part in project related meetings and able to freely provide views, excludes project trainings. | Project reports | PMU | Disaggregate stakeholders by gender, level of government, and civil society representation | 0 |  |  |  | 100 | 145 | 100% | 100 | 520 | 100% | 200 | 543 | 100% | 200 | 485 | 100% | 300 | 0 | 0% | Project management staff actively participate in annual reflection workshops and are committed to incorporating M&E data into workplans
[5 empty] | Federal | [8 empty] | 73 |  |  | 28 |  |  | 23
[5 empty] | State | [8 empty] | 16 |  |  | 11 |  |  | 43
[5 empty] | Local | [8 empty] | 43 |  |  | 23 |  |  | 52
[5 empty] | CSOs | [8 empty] | 388 |  |  | 481 |  |  | 367
[5 empty] | Women | [8 empty] | 1479 | [5 empty] | 823
[5 empty] | Men | [8 empty] | 880 | [5 empty] | 1355
| Changes in attitudes on integrated landscape management. % increase in Knowledge, Attitudes, Perception scores | Participant take part in project related mass awareness and capacity buiulding events. | KAP Survey | PMU |  | The % target increase will be set only upon completion of the first Knowledge, Attitude, Practices (KAP) survey. | [12 empty] | 85%
Outcome 4.2: Project monitoring system operates, systematically provides information on progress, and informs adaptive management to ensure results | Number of annual reflection workshops linked to annual stakeholder forums where project management analyses project progress and resource allocation, monitoring result and incorporates adaptive management into work planning. # workshops Non-cumulative |  | Project reports |  |  | 0 |  |  |  | 1 | 6 | 100% | 1 | 2 | 100% | 1 | 2 | 100% | 1 | 1 | 100% | 1 |  | 0%
Outcome 4.3: Project monitoring system operates, systematically provides information on progress, and informs adaptive management to ensure result | a) Number of forums where annual lessons are shared | # forums Non-cumulative | Project reports | PMU |  | 0 |  |  |  | 1 |  | 0% | 2 | 2 | 100% | 2 | 1 | 50% | 1 | 0 | 0% | 2 |  | 0% | Involvement in the design and implementation of project interventions and knowledge sharing on the experiences and expected benefits of ILM practices will result in long-term support for the project and adoption of new knowledge, skills and practices.
| b) Articles on project-related websites (No/year) | # articles Non-cumulative |  |  |  | 0 |  |  |  | 15 | 1 | 6.667% | 15 | 18 | 100% | 15 | 15 | 100% | 15 | 15 | 100% | 15 |  | 0%
| c) Number of radio programs hosted by the project | # radio programs Non-cumulative |  |  |  | 0 |  |  |  | 1 | 1 | 100% | 4 | 0 | 0% | 4 | 4 | 100% | 4 | 12 | 100% | 4 |  | 0%
Component 4 achievement: | [11 empty] | 61.33% |  |  | 80% |  |  | 90% |  |  | 80% |  |  | 0%
|  |  |  | Development Objective |  | Total % achieved |  |  | 25% |  |  | 39.63% |  |  | 67.62% |  |  | 61.84% |  |  | 70.27%
Note on O11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Included new figure with outputs achieved from degrated agricutlural land reclamation with mesh-wire fencing work in BNP BZ and Karnali corridor
Note on N16: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Please advise here, we included target only 10% femal participation as gov. offices in project site only have around 10% female staff in average Reply: Yes, this is correct. We will update this and discuss with GEF Sec.
Note on Q16: Prakash Tiwari: Target set as the previous year understanding
Note on T16: Lenovo: In an avearge, only 12% of the total government staff in project sites are female. So target set accordingly.
Note on Z23: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Project activities will be implemented in coordination with the NBSAP preparation technical/thematic committee, primarily focusing on project intervention sites and project stakeholders. Concurrently, loose forum (e.g., province level biodiversity coordination committee) will be engaged that supports the NBSAP preparation process. Reporting will be done accordingly.
Note on G27: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 311 total federal staff in 2 NP offices
Note on N27: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Cumulative target as per prodoc
Note on O27: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: In FY 2022: BaNP 81 , BNP : 64, FY 2023, BNP : 57 Total staff from federal level in working sites are 311 (BaNP: 107, BNP: 204)
Note on Z27: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Same as above. project activities will be implemented in coordination with the NBSAP preparation technical/thematic committee, primarily focusing on project intervention sites and project stakeholders. Concurrently, loose forum (e.g., province level biodiversity coordination committee) will be engaged that supports the NBSAP preparation process. Reporting will be done accordingly.
Note on G36: Lingertat, Heike: What number is this? Hectars?
Note on Q36: Lingertat, Heike: This has to be translated into a number. Please calculate. I made the calculation for outcome 3.1
Note on R36: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: As suggestions, 2019 Area_AM was taken as a baseline where Kamdi (5075) and Karnali (3984)
Note on G37: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Same as above. Please explain under indicator what number this is.
Note on Q37: Lingertat, Heike: Same as above
Note on R37: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: same as above
Note on B40: Lingertat, Heike: I translated the percentage into the number based on the baseline number to be able to calculaye the results. Please verify that this is correct.
Note on G40: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Baseline updated from ICIMOD fire database 2021 as per recent biodiversity assessment report in 2023
Note on O40: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: achievement reported by DFOs and National Park offices
Note on P40: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: We provided input by deleting formula as the formula does not understand number/Percentage relation
Note on Q40: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Need to set target as per the new baseline
Note on R40: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Fire occurrence data reported by DFOs and National Park Offices using MODIS data
Note on T40: Lenovo: Target set based on the baseline set in 2021
Note on B45: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Add the baseline numbers and targets so that they can be verified.
Note on G45: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Prodoc/RF information in Kamdi and Karnali
Note on O52: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Majority were IPs as project beneficiaries
Note on B55: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Recommended to remove. Budget are being reallocated as per the MTR recommendations, thus, subsidy-based activities contributing indicator recommended to remove.
Note on D55: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Recommended to remove. Budget are being reallocated as per the MTR recommendations, thus, subsidy-based activities contributing indicator recommended to remove.
Note on O59: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 10 Female, 18 IPs and 2 Dalits (Karnali corridor records)
Note on G64: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Based on data maintained by concerned gov. authorities
Note on P64: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Why is this 0%?
Note on S64: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Formula changed, as actual is greater than target then it is 0%
Note on B65: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Recommended to remove this indicator as per the MTR recommendations. Instead of this, suggested to add the indicator “Area of cropland protected (hectares)” to enable better integration and traceability to GEF Core Indicator 4, sub indicator 4.3. The target is set at 2000 ha.
Note on G65: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: BNP+Kamdi+Karnali+BaNP -Based on data reported by concerned authorities -Baseline considered FY78/79 (2022) Reply: Activities implemented for human-wildlife conflict mitigation that support sustainable land management (e.g., mesh wire fencing) will be reported in this indicator.
Note on P65: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: target was 10% but achievement was 43.67 % decrease so it means we achieved 100%
Note on S65: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: same as above
Note on T65: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Target was set to enable better integration and traceability to GEF Core Indicator 4, sub-indicator 4.3.
Note on G66: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Data managed by NP offices and DF offices from previous year
Note on S66: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: same as above
Note on S67: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: same as above
Note on S69: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: If the actual is zero then its 100%, Formula set accordingly
Note on N75: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: in project document it says 100 is target for year 2
Note on R75: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Need to add stakeholder number instead of gender.
Note on F80: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Participants' gender
Note on B82: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: For measuring the effectiveness of capacity building and mass awareness initiatives it is recommended to include indicator under Outcome 4.1.
Note on T82: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Baseline was set based on the KAP survey report. Aggregated value of Knowledge, Attitude, Practice score.

## AWPB Yr 1
Period: Year 1 (July 21 - June 22) (FY 78/79)
| ANNUAL WORK PLAN | [12 empty] | WORK PLAN TRACKING (Tracking at end of project year)
COMPONENT / OUTCOME / OUTPUT | # | ACTIVITIES | Responsible | YEAR X TIMING |  |  |  | BUDGET in USD |  |  | x | UNIT DESCRIPTION | TARGET | # UNIT(S) ACHIEVED | % ACHIEVED BY ACTIVITY (# unit(s) achieved / target) | % ACHIEVED BY OUTCOME | % ACHIEVED BY COMPONENT | BUDGET (actual, by Component)
|  |  |  | Q1 | Q2 | Q3 | Q4 | TA | Programm Funding | Total | if activity is carried over from previous year | # of | [5 empty] | in Rupee | in USD
A. ACTIVITY COSTS | [7 empty] | 0 | 0 | 0 | [7 empty] | 0 | 162126.4
COMPONENT 1: National capacity and enabling environment for cross-sectoral coordination to promote forest and landscape conservation | [7 empty] | 0 | 0 | 0 | [7 empty] | 0 | 8716.83
Outcome 1.1: Improved inter-sectoral coordination from Federal, State to Local level for sustainable forest management and integrated landscape management |  |  |  | Q1 | Q2 | Q3 | Q4 | 0 | 0 | 0 | [7 empty] | 0 | 5891.91
Output 1.1.1 : Cross-sectoral coordination mechanisms established to support integrated landscape management for conservation outcomes at different levels | 1 | 1.1.1.1: Provide support to NBCC committee (ensure gender inclusive team) | [5 empty] | 0 | 0 | 0 | [8 empty] | 0
| 2 | 1.1.1.2 Organize State level Biodiversity Co-ordination Committee (State 2,3,5,7 and Karnali) meetings | [5 empty] | 0 |  | 0 | [8 empty] | 1193.69
| 3 | 1.1.1.3 Provide technical and financial support to State Biodiversity Co-ordination committee | [5 empty] | 0 |  | 0
| 4 | 1.1.1.4 Organize inter-ministerial coordination mechanism for wildlife friendly infrastructure | [5 empty] | 0 |  | 0
| 5 | 1.1.1.5 Organize inter-state coordination (2, 3, Gandaki, 5, Karnali, 7) for implementation of the NBSAP and TAL Strategy | [5 empty] | 0 |  | 0 | [8 empty] | 333.84
| 6 | 1.1.1.6 Carry out cluster meetings with Municipalities | [5 empty] | 0 |  | 0
| 7 | 1.1.1.7 Conduct final review of NBSAP (2014-2020) | [5 empty] | 0 |  | 0
| 8 | 1.1.1.8Provide technical and financial support to WCCB | [5 empty] | 0 |  | 0 | [8 empty] | 2741.76
| 9 | 1.1.1.9 Field program implementation support & coordination | [5 empty] | 0 |  | 0 | [8 empty] | 1622.62
[8 empty] | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  | 0 | 5891.91
Outcome 1.2 Capacity increased for multi-stakeholder and cross-sector landscape and forest planning and management |  |  |  | Q1 | Q2 | Q3 | Q4 | 0 | 0 | 0 | [7 empty] | 0 | 2824.92
Output 1.2.1. Conservation Leadership Training provided | 10 | 1.2.1.1: Conduct training to ILM coordinators for capturing international best practice and applying this to the local context | [5 empty] | 0 |  | 0 |  |  |  | 0
[8 empty] | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  | 0 | 0
Output 1.2.2 Training courses provided on key subjects for integrated landscape management for responsible federal and state government staff | 11 | 1.2.2.1: Conduct training on Biodiversity conservation and monitoring | [5 empty] | 0 | 0 | 0
| 12 | 1.1.2.2: Conduct training on Disaster Risk Management | [5 empty] | 0 |  | 0
| 13 | 1.1.2.3: Orientation on roles and responsibilities for new park staff (senior/game scouts) | [5 empty] | 0 |  | 0 | [8 empty] | 1320.73
| 14 | 1.1.2.4: Orientation on roles and responsibilities for new divisional staff | [5 empty] | 0 |  | 0 | [8 empty] | 1504.19
[8 empty] | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  | 0 | 2824.92
Output 1.2.3 Small grants for innovation in ILM (conservation, natural resource, and landscape management) in TAL corridors and PA buffer zones | 15 | 1.2.3.1:Provide Individual grant (Bachelors and Master's thesis) | [5 empty] | 0 |  | 0
| 16 | 1.1.3.2: Provide Institutional grant to Academic Institutional and CBOs/CSOs | [5 empty] | 0 |  | 0
| 17 | 1.1.3.3: Provide innovation grant to the government agencies (National Park, Forest Division, Research and Training Centre) at state level | [5 empty] | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0% | 0 | 0
Component 2: Integrated Planning for Protected Area Buffer Zones and Critical Corridors in the Terai Arc Landscape | [7 empty] | 0 | 0 | 0 | [7 empty] | 0 | 13925.6
Outcome 2.1: Improved corridor planning for TAL corridors (Brahmadev, Karnali and Kamdi) |  |  |  | Q1 | Q2 | Q3 | Q4 | 0 | 0 | 0 | [7 empty] | 0 | 0
Output 2.1.1 Biodiversity surveys, socio-economic surveys, and local stakeholder consultation for Brahmadev , Karnali, and Kamdi corridors to determine feasibility of appropriate models for community-based natural resource management | 18 | 2.1.1.1: Conduct assessment to update biodiversity inventory and socio-economic status in corridors (incorporating GESI aspect, indigenous people and access restriction information) | [7 empty] | 0
| 19 | 2.1.1.2: Provide technical support to review existing forest encroachment status and response options considering GESI aspect and any necessary safeguards management plans (e.g. IPP or LRP)” | [7 empty] | 0
| 20 | 2.1.1.3: Prepare corridor/bottleneck assessment report with GESI and safeguards integration | [7 empty] | 0
[8 empty] | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  | 0 | 0
Outcome 2.2: Improved participatory planning for sustainable management of in Banke-Bardia complex |  |  |  | Q1 | Q2 | Q3 | Q4 | 0 | 0 | 0 | [7 empty] | 0 | 13925.6
Output 2.2.1: Land uses, biodiversity values, forest carbon, and key threats assessed, mapped, reported and disseminated to identify priority villages and forest areas in the targeted PA buffer zones and corridors | 21 | 2.2.1.1: Conduct participatory assessments in targeted PA buffer zones and corridors to identify priority community and forest areas | [7 empty] | 0 | [8 empty] | 13925.6
| 22 | 2.2.1.2: Conduct resource mapping of CFUGs at corridor level and BZUCs | [7 empty] | 0
| 23 | 2.2.1.3: Carry out consultations at identified communities | [7 empty] | 0
[8 empty] | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  | 0 | 13925.6
Output 2.2.2: Sustainable Forest Management Operational Plans developed or revised for priority forest areas, incorporating the assessment from 2.2.1 | 24 | 2.2.1.1: Provide financial support to develop State forest sector strategies (including Community Forests, Protected Forests and Leash-hold Forest) | [6 empty] | 0 | 0
| 25 | 2.2.1.2: Support CFUGs and BZ CFUGs to develop/revise forest operational plan (GESI aspect is revised/incorporated) | [5 empty] | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  | 0 | 0
COMPONENT 3: Forest and human-wildlife conflict management for improved conservation of targeted protected area buffer zones and corridors in the Terai Arc Landscape | [7 empty] | 0 | 0 | 0 | [7 empty] | 0 | 104858.18
Outcome 3.1: Strengthen livelihoods and biodiversity conservation through Sustainable forest management practices |  |  |  | Q1 | Q2 | Q3 | Q4 | 0 | 0 | 0 | [7 empty] | 0 | 73638.29
Output 3.1.1: Training and tools to local government on SFM | 26 | 3.1.1.1: Prepare Sustainable Forest Management Training (SFM) Manual incorporating GESI | [5 empty] | 0 | 0 | 0
| 27 | 3.1.1.2: Provide "Training of Trainers" (TOT) to Division Forest Offices staff based on SFM Training Manual | [5 empty] | 0 | 0 | 0
| 28 | 3.1.1.3 Establish Forest Management Information system (FMIS) including forest fire management | [5 empty] | 0 |  | 0
| 29 | 3.1.1.4: Support the State Forest Directorate fire reporting system | [5 empty] | 0 |  | 0
| 30 | 3.1.1.5: Support forest fire management through innovative tools and techniques such as leaf litter collection and composting (within targeted sites identified in component 2) | [5 empty] | 0 |  | 0 | [8 empty] | 6673.01
| 31 | 3.1.1.6 Provide multi-year support for nursery to Division forest offices (within targeted sites identified in component 2) | [5 empty] | 0 |  | 0 | [8 empty] | 27243.89
[8 empty] | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  | 0 | 33916.9
Output 3.1.2: Technical support to CFUGs, BZCFUGs and land holders for forest management | 32 | 3.1.2.1: Provide training to CFUGs and BZ CFUGs for forest management implementation (including applied SFM, restoration technique - lined with 3.1.1 | [7 empty] | 0
| 33 | 3.1.2.2: Conduct exchange visits for targeted BZ CFUG members (learning from successful UCs on fund mobilization and HWC management) | [7 empty] | 0
| 34 | 3.1.2.3: Support BZUCs annual meetings for Bardia and Banke NP Buffer Zones (northern side) | [7 empty] | 0
| 35 | 3.1.2.4: Provide coaching on "Governance and Financial management" for CFUGs of corridors and PA Buffer zones | [7 empty] | 0
| 36 | 3.1.2.5: Provide support private forest development (providing seedling, irrigation, fencing) | [7 empty] | 0 | [8 empty] | 8833.81
| 37 | 3.1.2.6: Support to register private forest | [7 empty] | 0
[8 empty] | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  | 0 | 8833.81
Output 3.1.3: Forests and associated habitat in priority buffer zones and corridors managed sustainably | 38 | 3.1.3.1: Create revolving fund to implement forest operational plans in project targeted corridors | [7 empty] | 0
| 39 | 3.1.3.2: Provide financial and technical support to improve livestock management (AI, fodder plant support, feeding trough, vet support, stall improvement) | [7 empty] | 0
| 40 | 3.1.3.3: Provide financial and technical support for management of grassland and wetland in project targeted area | [7 empty] | 0 | [8 empty] | 30271.72
| 41 | 3.1.3.4: Provide financial and technical support for river bank protection in project targeted area | [7 empty] | 0
| 42 | 3.1.3.5: Safeguard plan implementation | [7 empty] | 0 | [8 empty] | 615.86
| 43 | 3.1.3.6: Provide financial and technical support to small scale green enterprises in project targeted area | [7 empty] | 0
| 44 | 3.1.3.7: Provide financial and technical support to develop business plan | [7 empty] | 0
[8 empty] | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  | 0 | 30887.58
Outcome 3.2: Improved management of the human-wildlife conflict |  |  |  | Q1 | Q2 | Q3 | Q4 | 0 | 0 | 0 | [7 empty] | 0 | 19047.02
Output 3.2.1: Pilot method to reduce the wildlife accident in priority sites | 45 | 3.2.1.1: Conduct study on the wildlife traffic accident issue | [7 empty] | 0
| 46 | 3.2.1.2: Install tools/facilities to pilot measures to reduce accidents | [7 empty] | 0
| 47 | 3.2.1.3: Support in operation and monitoring of wildlife related traffic accidents in highway | [7 empty] | 0 | [8 empty] | 2041.38
| 48 | 3.2.1.4: Support to erect fence in both side of Sikta irrigation canal | [7 empty] | 0 | [8 empty] | 9570.88
[8 empty] | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  | 0 | 11612.26
Output 3.2.2: Training and facilities for human wildlife conflict response | 49 | 3.2.2.1: Prepare species-specific guidelines for HWC management | [7 empty] | 0
| 50 | 3.2.2.2: Pictorial manual on Wildlife identification and behavior in Nepali and local dialects | [7 empty] | 0
| 51 | 3.2.2.3: Conduct training on identification and behavior of wild animals to Divisional forest office staff | [7 empty] | 0 | [8 empty] | 3676.93
| 52 | 3.2.2.4: Support Wildlife Rescue center | [7 empty] | 0
| 53 | 3.2.2.5: Support wildlife rescue and handling equipment and training | [7 empty] | 0 | [8 empty] | 3757.83
[8 empty] | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  | 0 | 7434.76
Output 3.2.3: Community based HWC mitigate and preventive action implemented | 54 | 3.2.3.1: Conduct workshop on preventive and curative measures for HWC | [7 empty] | 0
| 55 | 3.2.3.2: Implement measures for HWC based on prepared plans (mentha plantation, biological/virtual fencing) | [7 empty] | 0
| 56 | 3.2.3.3: Support to establish community-based insurance (crop, livestock) scheme | [7 empty] | 0
| 57 | 3.2.3.4: Implement community-based reporting system of HWC incidents | [7 empty] | 0
[8 empty] | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  | 0 | 0
Outcome 3.3: Enhanced capacities of government agencies and community in curbing illegal wildlife crime |  |  |  | Q1 | Q2 | Q3 | Q4 | 0 | 0 | 0 | [7 empty] | 0 | 12172.87
Output 3.3.1: Community Based Anti poaching Units functional in priority areas | 58 | 3.3.1.1: Provide support for field gears to CBAPU members | [7 empty] | 0
| 58 | 3.3.1.2: Provide technical and financial support for skill based training to CBAPU members | [7 empty] | 0
| 59 | 3.3.1.3: Establish revolving fund to initiate green enterprise for CBAPUs member (link to above activities) | [7 empty] | 0
[8 empty] | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  | 0 | 0
Output 3.3.2: Training and operation support to Park staff, rangers on wildlife crime management | 60 | 3.3.2.1: Update training manual on illegal wildlife crime scene management | [7 empty] | 0
| 61 | 3.3.2.2: Conduct training to investigation officers level on Illegal wildlife crime scene management | [7 empty] | 0 | [8 empty] | 2729.32
| 62 | 3.3.2.3: Support Transboundary coordination at local level | [7 empty] | 0 | [8 empty] | 1671.33
| 63 | 3.3.2.4: Field program implementation support & coordination | [7 empty] | 0 | [8 empty] | 7772.22
[8 empty] | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  | 0 | 12172.87
COMPONENT 4: Monitoring and evaluation (M&E), knowledge management (KM), and regional coordination | [7 empty] | 0 | 0 | 0 | [7 empty] | 0 | 34625.79
Outcome 4.1: Improved coordination and dialogue on integrated landscape management from the local to national level |  |  |  | Q1 | Q2 | Q3 | Q4 | 0 | 0 | 0 | [7 empty] | 0 | 28067.85
Output 4.1.1: Information on ILM importance shared among key stakeholders | 64 | 4.1.1.1: Organize monthly dialogue through "Jaibik Chautari" (Biodiversity Platform) at field | [7 empty] | 0 | [8 empty] | 3357.78
| 65 | 4.1.1.2: Organize annual technical thematic discussion session at center | [7 empty] | 0
| 66 | 4.1.1.4: Establish and maintain online Landscape Knowledge Learning Platform (including project website) | [7 empty] | 0 | [8 empty] | 1195.53
[8 empty] | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  | 0 | 4553.31
Output 4.1.2: Mass awareness products on biodiversity conservation and integrated landscape management | 67 | 4.1.2.1: Provide technical and financial support to green/eco-clubs formation and its operation | [7 empty] | 0 | [8 empty] | 14317.15
| 68 | 4.1.2.2: Support annual meetings of green/eco-clubs network at district level | [7 empty] | 0
| 69 | 4.1.2.3: Support special conservation events at local level | [7 empty] | 0 | [8 empty] | 6104.8
| 70 | 4.1.2.4: Sensitize media (print and TV) on integrated landscape management | [7 empty] | 0
| 71 | 4.1.2.5: Support radio program (local dialects) on ILM | [7 empty] | 0 | [8 empty] | 3092.59
[8 empty] | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  | 0 | 23514.54
Outcome 4.2: Project monitoring system operates, systematically provides information on progress, and informs adaptive management to ensure results |  |  |  | Q1 | Q2 | Q3 | Q4 | 0 | 0 | 0 | [7 empty] | 0 | 4982.95
Output 4.2.1: Participatory planning and M&E system | 72 | 4.2.1.1: Organize project inception workshops at Kathmandu and field level | [7 empty] | 0
| 73 | 4.2.1.2: PAC/PEC planning review workshop (Central and Field) | [7 empty] | 0 | [8 empty] | 167.59
| 74 | 4.2.1.3: Conduct periodic (trimester) workplan review and planning sessions | [7 empty] | 0 | [8 empty] | 3167.27
| 75 | 4.2.1.4: Conduct periodic and joint monitoring visits | [7 empty] | 0
| 76 | 4.2.1.5: Conduct Safeguard Monitoring visits | [7 empty] | 0
| 77 | 4.2.1.6: Conduct training on "participatory monitoring and evaluation" to CFUGs and relevant sub-grantees | [7 empty] | 0
| 78 | 4.2.1.7: Capacity building/training of PSU staff (on project management - WWF network standards, report writing and GESI and safeguard) | [7 empty] | 0 | [8 empty] | 1648.09
| 79 | 4.2.1.8: Organize Project Mid-term review workshops with all key stakeholders | [7 empty] | 0
| 80 | 4.9.1.9: Conduct Project Evaluations (Mid-term and terminal evaluation - GEF/SWC) | [7 empty] | 0
| 81 | 4.2.1.10: Annual Financial Audit | [7 empty] | 0
[8 empty] | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  | 0 | 4982.95
Outcome 4.3: Project lessons shared |  |  |  | Q1 | Q2 | Q3 | Q4 | 0 | 0 | 0 | [7 empty] | 0 | 1574.99
Output 4.3.1: Project lessons captured and disseminated to project stakeholders and to other projects and partners | 82 | 4.3.1.1: Documentation on Traditional Knowledge associated to natural resources | [7 empty] | 0
| 83 | 4.3.1.2: Prepare success stories and videos of the project | [6 empty] | 0 | 0
| 84 | 4.3.1.3: Print case studies and periodic project reports | [6 empty] | 0 | 0
| 85 | 4.3.1.4: Provide financial support to participate in national/international scientific forum for field staff | [6 empty] | 0 | 0
| 86 | 4.3.1.5: Provide financial support to publish journal articles | [6 empty] | 0 | 0
| 87 | 4.3.1.6: Field program implementation support & coordination | [7 empty] | 0 | [8 empty] | 1574.99
| 88 | 4.2.1.7: Organize final project lessons sharing workshop | [6 empty] | 0 | 0
[8 empty] | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  | 0 | 1574.99
B. Project Management Costs | [9 empty] | 0 | [7 empty] | 0 | 0
Office and field running costs |  |  |  | Q1 | Q2 | Q3 | Q4 | 0 | 0 | 0 | [7 empty] | 0 | 0
Project Management Unit | 56xx | Insurance, Maintenance, Utility | PMU | [6 empty] | 0
| 56xx | Office Rent | PMU | [6 empty] | 0
| 56xx | Equipment Running Cost | [7 empty] | 0
| 56xx | Vehicle Running Costs (Vehicle Repair) | [7 empty] | 0
| 56xx | Vehicle Running Costs (fuel for office purpose) | [7 empty] | 0
| 56xx | Photocopying | [7 empty] | 0
| 56xx | Postage & Shipping | [7 empty] | 0
| 56xx | Communications (phone, fax, internet) | [7 empty] | 0
| 56xx | Supplies | [7 empty] | 0
| 56xx | Field program implementation support coordination (Staffs travel and Inhouse Meeting) | PMU | [6 empty] | 0
| 56xx | Advertisment/Priniting and Publication | PMU | [6 empty] | 0
| 56xx | Bank charges | PMU | [6 empty] | 0
[8 empty] | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  | 0 | 0
|  | Capital Assets | [5 empty] | 0 | 0 | 0 | [7 empty] | 0 | 0
| 58xx | Scanner | PMU | [6 empty] | 0 |  | Set
| 58xx | LCD Projector with screen (1 for Kathmandu and 2 for Banke Office | PMU | [6 empty] | 0 |  | Set
| 58xx | Camera | [7 empty] | 0 |  | Set
| 58xx | Air Conditioners (3 for Banke Office) | [7 empty] | 0 |  | Set
| 58xx | EPABX system setup | [7 empty] | 0 |  | Set
| 58xx | Power backup system (inverter & battery for Banke Office) | [7 empty] | 0 |  | Set
| 58xx | Desktop Screen (monitor) | [7 empty] | 0 |  | Set
| 58xx | Vault for Kathmandu and Banke Office | [7 empty] | 0 |  | Set
| 58xx | GPS (Banke Office) | [7 empty] | 0 |  | Set
| 58xx | Spiral binding machine | [7 empty] | 0 |  | Set
| 58xx | Air Cooler for Banke Office | [7 empty] | 0 |  | No.
| 58xx | Microwave oven for Kathmandu Office | [7 empty] | 0 |  | No.
| 58xx | Account Software (Activitywise reporting, VMS etc.) | [7 empty] | 0 |  | No
| 58xx | Office 365 insallation, Sofware AMC etc | [7 empty] | 0 |  | times
| 58xx | IT support | [7 empty] | 0 |  | times
| 58xx | Bridger Liscence (annual recurring cost) | PMU | [6 empty] | 0 |  | times
| 58xx | Office and restroom renovation, Kathmandu Office | PMU | [6 empty] | 0 |  | Times
| 58xx | Equipment Motorbike | PMU | [6 empty] | 0 |  | No.
[8 empty] | 0 | 0 | 0 |  |  | 0 |  |  |  |  | 0 | 0
|  | Personnel | [5 empty] | 0 | 0 | 0 | [7 empty] | 0 | 0
| 50xx | Project Coordinator | PMU | [6 empty] | 0
| 50xx | Project Manager | PMU | [6 empty] | 0
| 50xx | Finance and Administration Manager | PMU | [6 empty] | 0
| 50xx | Field Manager | PMU | [6 empty] | 0
| 50xx | Field Program Officer | PMU | [6 empty] | 0
| 50xx | Field Finance/Compliance Officer | PMU | [6 empty] | 0
| 50xx | Field Monitoring, Evaluation and Learning (MEL) Officer | PMU | [6 empty] | 0
| 50xx | Field Finance and Administration Associate | PMU | [6 empty] | 0
| 50xx | Field Program Assistant (4) | PMU | [6 empty] | 0
| 50xx | Front Desk Assistant _KTM | PMU | [6 empty] | 0
| 50xx | Front Desk Assistant _Field | PMU | [6 empty] | 0
| 50xx | Communication Officer (100% ) | PMU | [6 empty] | 0
| 50xx | Field Safeguard and GESI Officer | PMU | [6 empty] | 0
| 50xx | Office Messenger (2) | PMU | [6 empty] | 0
| 50xx | Driver (2) | PMU | [6 empty] | 0
[8 empty] | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  | 0 | 0
GRAND TOTAL (A+B) |  |  |  | YR 1 | [5 empty] | 0 | [7 empty] | 0 | 162126.4
|  |  | Carry-over total (unspent funds from previous year) | [12 empty] | % achieved for activities overall |  | Actual budget for previous project year
|  |  | Request of funds for Upcoming Project Year | [6 empty] | 0
[20 empty] | GL CODE | LMBIS CODE | ACT# NO# | COMPONENT / OUTCOME / OUTPUT/ACTIVITIES | RESPONSIBLE | TIMELINE |  |  |  | UNIT DESCRIPTION | TARGET | UNIT COST | TOTAL BUDGET | Remarks | COMPONENT |  |  |  |  | TOTAL BUDGET | [6 empty] | BUDGET BIFUCATION |  |  | Outcomes
[25 empty] | Q1 | Q2 | Q3 | Q4 | [5 empty] | Com.1 | Com.2 | Com.3 | Com.4 | Mgmt. | Jan-Mar 2021 | Apr-Jun 2021 | Jul-Sep 2021 | Oct-Dec 2021 | Jan-Mar 2022 | Apr-Jun 2022 | TOTAL Budget | TECHNICAL ASSISTANCE | PROGRAM FUNDING | TOTAL
[23 empty] | A. PERSONNEL COSTS |  | 0 | 0 | 0 | 0 |  |  |  | 341694.2045 |  | 58379.8687 | 41832.346 | 133332.8761 | 62713.2273 | 45435.8864 | 56949.0341 | 56949.0341 | 56949.0341 | 56949.0341 | 56949.0341 | 56949.0341 | 341694.2045 | 341694.2045 | 0 | 341694.2045
[20 empty] | 50xx |  |  | Project Coordinator | PMU |  |  |  |  | Mo. | 15 | 2424.5455 | 36368.1818 |  | 18184.0909 | 3636.8182 | 7273.6364 | 1818.4091 | 5455.2273 | 6061.3636 | 6061.3636 | 6061.3636 | 6061.3636 | 6061.3636 | 6061.3636 | 36368.1818 | 36368.1818 | 0 | 36368.1818
[20 empty] | 50xx |  |  | Project Manager | PMU |  |  |  |  | Mo. | 15 | 2239.3636 | 33590.4545 |  | 6718.0909 | 6718.0909 | 11756.6591 | 3359.0455 | 5038.5682 | 5598.4091 | 5598.4091 | 5598.4091 | 5598.4091 | 5598.4091 | 5598.4091 | 33590.4545 | 33590.4545 | 0 | 33590.4545
[20 empty] | 50xx |  |  | Finance and Administration Manager | PMU |  |  |  |  | Mo. | 15 | 1860.4091 | 27906.1364 |  | 3488.267 | 3488.267 | 9767.1477 | 5581.2273 | 5581.2273 | 4651.0227 | 4651.0227 | 4651.0227 | 4651.0227 | 4651.0227 | 4651.0227 | 27906.1364 | 27906.1364 | 0 | 27906.1364
[20 empty] | 50xx |  |  | Field Manager | PMU |  |  |  |  | Mo. | 15 | 1403.1818 | 21047.7273 |  | 3157.1591 | 3157.1591 | 10523.8636 | 4209.5455 | 0 | 3507.9545 | 3507.9545 | 3507.9545 | 3507.9545 | 3507.9545 | 3507.9545 | 21047.7273 | 21047.7273 | 0 | 21047.7273
[20 empty] | 50xx |  |  | Field Program Officer | PMU |  |  |  |  | Mo. | 15 | 1343.0455 | 20145.6818 |  | 2014.5682 | 4029.1364 | 10072.8409 | 4029.1364 | 0 | 3357.6136 | 3357.6136 | 3357.6136 | 3357.6136 | 3357.6136 | 3357.6136 | 20145.6818 | 20145.6818 | 0 | 20145.6818
[20 empty] | 50xx |  |  | Field Finance/Compliance Officer | PMU |  |  |  |  | Mo. | 15 | 1343.0455 | 20145.6818 |  | 2518.2102 | 2518.2102 | 7050.9886 | 4029.1364 | 4029.1364 | 3357.6136 | 3357.6136 | 3357.6136 | 3357.6136 | 3357.6136 | 3357.6136 | 20145.6818 | 20145.6818 | 0 | 20145.6818
[20 empty] | 50xx |  |  | Field Monitoring, Evaluation and Learning (MEL) Officer | PMU |  |  |  |  | Mo. | 15 | 1363.0909 | 20446.3636 |  | 0 | 0 | 0 | 20446.3636 | 0 | 3407.7273 | 3407.7273 | 3407.7273 | 3407.7273 | 3407.7273 | 3407.7273 | 20446.3636 | 20446.3636 | 0 | 20446.3636
[20 empty] | 50xx |  |  | Field Finance and Administration Associate | PMU |  |  |  |  | Mo. | 15 | 1072.4318 | 16086.4773 |  | 2010.8097 | 2010.8097 | 5630.267 | 3217.2955 | 3217.2955 | 2681.0795 | 2681.0795 | 2681.0795 | 2681.0795 | 2681.0795 | 2681.0795 | 16086.4773 | 16086.4773 | 0 | 16086.4773
[20 empty] | 50xx |  |  | Field Program Assistant (4) | PMU |  |  |  |  | Mo. | 15 | 3046.9091 | 45703.6364 |  | 2285.1818 | 4570.3636 | 36562.9091 | 2285.1818 |  | 7617.2727 | 7617.2727 | 7617.2727 | 7617.2727 | 7617.2727 | 7617.2727 | 45703.6364 | 45703.6364 | 0 | 45703.6364
[20 empty] | 50xx |  |  | Front Desk Assistant _KTM | PMU |  |  |  |  | Mo. | 15 | 801.8182 | 12027.2727 |  | 962.1818 | 962.1818 | 2886.5455 | 1202.7273 | 6013.6364 | 2004.5455 | 2004.5455 | 2004.5455 | 2004.5455 | 2004.5455 | 2004.5455 | 12027.2727 | 12027.2727 | 0 | 12027.2727
[20 empty] | 50xx |  |  | Front Desk Assistant _Field | PMU |  |  |  |  | Mo. | 15 | 781.7727 | 11726.5909 |  | 938.1273 | 938.1273 | 2814.3818 | 1172.6591 | 5863.2955 | 1954.4318 | 1954.4318 | 1954.4318 | 1954.4318 | 1954.4318 | 1954.4318 | 11726.5909 | 11726.5909 | 0 | 11726.5909
[20 empty] | 50xx |  |  | Communication Officer (100% ) | PMU |  |  |  |  | Mo. | 15 | 1454.5455 | 21818.1818 |  | 3490.9091 | 3490.9091 | 10472.7273 | 4363.6364 | 0 | 3636.3636 | 3636.3636 | 3636.3636 | 3636.3636 | 3636.3636 | 3636.3636 | 21818.1818 | 21818.1818 | 0 | 21818.1818
[20 empty] | 50xx |  |  | Field Safeguard and GESI Officer | PMU |  |  |  |  | Mo. | 15 | 1545.4545 | 23181.8182 |  | 3477.2727 | 3477.2727 | 11590.9091 | 4636.3636 | 0 | 3863.6364 | 3863.6364 | 3863.6364 | 3863.6364 | 3863.6364 | 3863.6364 | 23181.8182 | 23181.8182 | 0 | 23181.8182
[20 empty] | 50xx |  |  | Office Messenger (2) | PMU |  |  |  |  | Mo. | 15 | 1050 | 15750 |  | 1260 | 1260 | 3780 | 1575 | 7875 | 2625 | 2625 | 2625 | 2625 | 2625 | 2625 | 15750 | 15750 | 0 | 15750
[20 empty] | 50xx |  |  | Driver (2) | PMU |  |  |  |  | Mo. | 15 | 1050 | 15750 |  | 7875 | 1575 | 3150 | 787.5 | 2362.5 | 2625 | 2625 | 2625 | 2625 | 2625 | 2625 | 15750 | 15750 | 0 | 15750
[23 empty] | B. ACTIVITY COST | [8 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on Y185: Narayan K.C.: liNE Ministry Budget Informaiton System
Note on AI193: Author: 120,000/Fulltime

## AWPB Yr 2
Period: Year 2 (July 21 - June 22) (FY 78/79)
| ANNUAL WORK PLAN | [12 empty] | WORK PLAN TRACKING (Tracking at end of project year)
COMPONENT / OUTCOME / OUTPUT | # | ACTIVITIES | Responsible | YEAR X TIMING |  |  |  | BUDGET in USD |  |  | x | UNIT DESCRIPTION | TARGET | # UNIT(S) ACHIEVED | % ACHIEVED BY ACTIVITY (# unit(s) achieved / target) | % ACHIEVED BY OUTCOME | % ACHIEVED BY COMPONENT | BUDGET (actual, by Component)
|  |  |  | Q1 | Q2 | Q3 | Q4 | TA | Programm Funding | Total | if activity is carried over from previous year | # of | [5 empty] | in Rupee | in USD
A. ACTIVITY COSTS | [7 empty] | 9000 | 736909.9091 | 745909.9091 | [7 empty] | 0 | 162126.4
COMPONENT 1: National capacity and enabling environment for cross-sectoral coordination to promote forest and landscape conservation | [7 empty] | 0 | 177864.4545 | 177864.4545 | [7 empty] | 0 | 8716.83
Outcome 1.1: Improved inter-sectoral coordination from Federal, State to Local level for sustainable forest management and integrated landscape management |  |  |  | Q1 | Q2 | Q3 | Q4 | 0 | 42014.4545 | 42014.4545 | [7 empty] | 0 | 5891.91
Output 1.1.1 : Cross-sectoral coordination mechanisms established to support integrated landscape management for conservation outcomes at different levels | 1 | 1.1.1.1: Provide support to NBCC committee (ensure gender inclusive team) | [5 empty] | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0
| 2 | 1.1.1.2 Organize State level Biodiversity Co-ordination Committee (State 2,3,5,7 and Karnali) meetings | [5 empty] | 0 | 4000 | 4000 |  |  | 2 | 1 | 50% |  |  |  | 1193.69
| 3 | 1.1.1.3 Provide technical and financial support to State Biodiversity Co-ordination committee | [5 empty] | 0 | 3000 | 3000 |  |  | 2 | 0 | 0%
| 4 | 1.1.1.4 Organize inter-ministerial coordination mechanism for wildlife friendly infrastructure | [5 empty] | 0 | 3000 | 3000 |  |  | 1 | 0 | 0%
| 5 | 1.1.1.5 Organize inter-state coordination (2, 3, Gandaki, 5, Karnali, 7) for implementation of the NBSAP and TAL Strategy | [5 empty] | 0 | 2000 | 2000 |  |  | 1 | 0 | 0% |  |  |  | 333.84
| 6 | 1.1.1.6 Carry out cluster meetings with Municipalities | [5 empty] | 0 | 5000 | 5000 |  |  | 10 | 1 | 10%
| 7 | 1.1.1.7 Conduct final review of NBSAP (2014-2020) | [5 empty] | 0 | 15969 | 15969 |  |  | 1 | 0 | 0%
| 8 | 1.1.1.8Provide technical and financial support to WCCB | [5 empty] | 0 | 3000 | 3000 |  |  | 2 | 2 | 100% |  |  |  | 2741.76
| 9 | 1.1.1.9 Field program implementation support & coordination | [5 empty] | 0 | 6045.4545 | 6045.4545 |  |  | 1 | 1 | 100% |  |  |  | 1622.62
[8 empty] | 0 | 42014.4545 | 42014.4545 |  |  | 20 | 5 | 32.5% | 32.5% |  | 0 | 5891.91
Outcome 1.2 Capacity increased for multi-stakeholder and cross-sector landscape and forest planning and management |  |  |  | Q1 | Q2 | Q3 | Q4 | 0 | 135850 | 135850 | [7 empty] | 0 | 2824.92
Output 1.2.1. Conservation Leadership Training provided | 10 | 1.2.1.1: Conduct training to ILM coordinators for capturing international best practice and applying this to the local context | [5 empty] | 0 | 12000 | 12000 |  |  | 12 | 0 | 0%
[8 empty] | 0 | 12000 | 12000 |  |  | 12 | 0 | 0% |  |  | 0 | 0
Output 1.2.2 Training courses provided on key subjects for integrated landscape management for responsible federal and state government staff | 11 | 1.2.2.1: Conduct training on Biodiversity conservation and monitoring | [5 empty] | 0 | 0 | 0 |  |  | 0 | 0
| 12 | 1.1.2.2: Conduct training on Disaster Risk Management | [5 empty] | 0 |  | 0 |  |  | 0 | 0
| 13 | 1.1.2.3: Orientation on roles and responsibilities for new park staff (senior/game scouts) | [5 empty] | 0 | 1500 | 1500 |  |  | 1 | 1 | 100% |  |  |  | 1320.73
| 14 | 1.1.2.4: Orientation on roles and responsibilities for new divisional staff | [5 empty] | 0 | 1500 | 1500 |  |  | 1 | 1 | 100% |  |  |  | 1504.19
[8 empty] | 0 | 3000 | 3000 |  |  | 2 | 2 | 100% |  |  | 0 | 2824.92
Output 1.2.3 Small grants for innovation in ILM (conservation, natural resource, and landscape management) in TAL corridors and PA buffer zones | 15 | 1.2.3.1:Provide Individual grant (Bachelors and Master's thesis) | [5 empty] | 0 | 5850 | 5850 |  |  | 9 | 0 | 0%
| 16 | 1.1.3.2: Provide Institutional grant to Academic Institutional and CBOs/CSOs | [5 empty] | 0 | 15000 | 15000 |  |  | 1 | 0 | 0%
| 17 | 1.1.3.3: Provide innovation grant to the government agencies (National Park, Forest Division, Research and Training Centre) at state level | [5 empty] | 0 | 100000 | 100000 |  |  | 2 | 0 | 0%
[8 empty] | 0 | 120850 | 120850 |  |  | 12 | 0 | 0% | 33.33% | 30.67% | 0 | 0
Component 2: Integrated Planning for Protected Area Buffer Zones and Critical Corridors in the Terai Arc Landscape | [7 empty] | 9000 | 53000 | 62000 | [7 empty] | 0 | 13925.6
Outcome 2.1: Improved corridor planning for TAL corridors (Brahmadev, Karnali and Kamdi) |  |  |  | Q1 | Q2 | Q3 | Q4 | 0 | 30000 | 30000 | [7 empty] | 0 | 0
Output 2.1.1 Biodiversity surveys, socio-economic surveys, and local stakeholder consultation for Brahmadev , Karnali, and Kamdi corridors to determine feasibility of appropriate models for community-based natural resource management | 18 | 2.1.1.1: Conduct assessment to update biodiversity inventory and socio-economic status in corridors (incorporating GESI aspect, indigenous people and access restriction information) | [6 empty] | 30000 | 30000 |  |  | 2 | 0 | 0%
| 19 | 2.1.1.2: Provide technical support to review existing forest encroachment status and response options considering GESI aspect and any necessary safeguards management plans (e.g. IPP or LRP)” | [7 empty] | 0 |  |  | 0 | 0
| 20 | 2.1.1.3: Prepare corridor/bottleneck assessment report with GESI and safeguards integration | [7 empty] | 0 |  |  | 0 | 0
[8 empty] | 0 | 30000 | 30000 |  |  | 2 | 0 | 0% | 0% |  | 0 | 0
Outcome 2.2: Improved participatory planning for sustainable management of in Banke-Bardia complex |  |  |  | Q1 | Q2 | Q3 | Q4 | 9000 | 23000 | 32000 | [7 empty] | 0 | 13925.6
Output 2.2.1: Land uses, biodiversity values, forest carbon, and key threats assessed, mapped, reported and disseminated to identify priority villages and forest areas in the targeted PA buffer zones and corridors | 21 | 2.2.1.1: Conduct participatory assessments in targeted PA buffer zones and corridors to identify priority community and forest areas | [6 empty] | 15000 | 15000 |  |  | 1 | 1 | 100% |  |  |  | 13925.6
| 22 | 2.2.1.2: Conduct resource mapping of CFUGs at corridor level and BZUCs | [6 empty] | 5000 | 5000 |  |  | 1 | 0 | 0%
| 23 | 2.2.1.3: Carry out consultations at identified communities | [6 empty] | 3000 | 3000 |  |  | 15 | 0 | 0%
[8 empty] | 0 | 23000 | 23000 |  |  | 17 | 1 | 33.33% |  |  | 0 | 13925.6
Output 2.2.2: Sustainable Forest Management Operational Plans developed or revised for priority forest areas, incorporating the assessment from 2.2.1 | 24 | 2.2.1.1: Provide financial support to develop State forest sector strategies (including Community Forests, Protected Forests and Leash-hold Forest) | [5 empty] | 9000 | 0 | 9000 |  |  | 1 | 0 | 0%
| 25 | 2.2.1.2: Support CFUGs and BZ CFUGs to develop/revise forest operational plan (GESI aspect is revised/incorporated) | [5 empty] | 0 | 0 | 0 |  |  | 0 | 0
[8 empty] | 9000 | 0 | 9000 |  |  | 1 | 0 | 0% | 25% | 20% | 0 | 0
COMPONENT 3: Forest and human-wildlife conflict management for improved conservation of targeted protected area buffer zones and corridors in the Terai Arc Landscape | [7 empty] | 0 | 404454.5455 | 404454.5455 | [7 empty] | 0 | 104858.18
Outcome 3.1: Strengthen livelihoods and biodiversity conservation through Sustainable forest management practices |  |  |  | Q1 | Q2 | Q3 | Q4 | 0 | 183000 | 183000 | [7 empty] | 0 | 73638.29
Output 3.1.1: Training and tools to local government on SFM | 26 | 3.1.1.1: Prepare Sustainable Forest Management Training (SFM) Manual incorporating GESI | [5 empty] | 0 | 0 | 0 |  |  | 0 | 0
| 27 | 3.1.1.2: Provide "Training of Trainers" (TOT) to Division Forest Offices staff based on SFM Training Manual | [5 empty] | 0 | 0 | 0 |  |  | 0 | 0
| 28 | 3.1.1.3 Establish Forest Management Information system (FMIS) including forest fire management | [5 empty] | 0 | 10000 | 10000 |  |  | 1 | 0 | 0%
| 29 | 3.1.1.4: Support the State Forest Directorate fire reporting system | [5 empty] | 0 | 5000 | 5000 |  |  | 1 | 0 | 0%
| 30 | 3.1.1.5: Support forest fire management through innovative tools and techniques such as leaf litter collection and composting (within targeted sites identified in component 2) | [5 empty] | 0 | 8000 | 8000 |  |  | 4 | 4 | 100% |  |  |  | 6673.01
| 31 | 3.1.1.6 Provide multi-year support for nursery to Division forest offices (within targeted sites identified in component 2) | [5 empty] | 0 | 30000 | 30000 |  |  | 1 | 1 | 100% |  |  |  | 27243.89
[8 empty] | 0 | 53000 | 53000 |  |  | 7 | 5 | 50% |  |  | 0 | 33916.9
Output 3.1.2: Technical support to CFUGs, BZCFUGs and land holders for forest management | 32 | 3.1.2.1: Provide training to CFUGs and BZ CFUGs for forest management implementation (including applied SFM, restoration technique - lined with 3.1.1 | [7 empty] | 0 |  |  | 0 | 0
| 33 | 3.1.2.2: Conduct exchange visits for targeted BZ CFUG members (learning from successful UCs on fund mobilization and HWC management) | [7 empty] | 0 |  |  | 0 | 0
| 34 | 3.1.2.3: Support BZUCs annual meetings for Bardia and Banke NP Buffer Zones (northern side) | [7 empty] | 0 |  |  | 0 | 0
| 35 | 3.1.2.4: Provide coaching on "Governance and Financial management" for CFUGs of corridors and PA Buffer zones | [6 empty] | 4000 | 4000 |  |  | 2 | 0 | 0%
| 36 | 3.1.2.5: Provide support private forest development (providing seedling, irrigation, fencing) | [6 empty] | 20000 | 20000 |  |  | 20 | 9.6 | 48% |  |  |  | 8833.81
| 37 | 3.1.2.6: Support to register private forest | [7 empty] | 0 |  |  | 0 | 0
[8 empty] | 0 | 24000 | 24000 |  |  | 22 | 9.6 | 24% |  |  | 0 | 8833.81
Output 3.1.3: Forests and associated habitat in priority buffer zones and corridors managed sustainably | 38 | 3.1.3.1: Create revolving fund to implement forest operational plans in project targeted corridors | [7 empty] | 0 |  |  | 0 | 0
| 39 | 3.1.3.2: Provide financial and technical support to improve livestock management (AI, fodder plant support, feeding trough, vet support, stall improvement) | [6 empty] | 35000 | 35000 |  |  | 140 | 0 | 0%
| 40 | 3.1.3.3: Provide financial and technical support for management of grassland and wetland in project targeted area | [6 empty] | 42000 | 42000 |  |  | 4 | 4 | 100% |  |  |  | 30271.72
| 41 | 3.1.3.4: Provide financial and technical support for river bank protection in project targeted area | [6 empty] | 20000 | 20000 |  |  | 2 | 0 | 0%
| 42 | 3.1.3.5: Safeguard plan implementation | [6 empty] | 9000 | 9000 |  |  | 1 | 1 |  |  |  |  | 615.86
| 43 | 3.1.3.6: Provide financial and technical support to small scale green enterprises in project targeted area | [7 empty] | 0 |  |  | 0 | 0
| 44 | 3.1.3.7: Provide financial and technical support to develop business plan | [7 empty] | 0 |  |  | 0 | 0
[8 empty] | 0 | 106000 | 106000 |  |  | 147 | 5 | 33.33% | 38.67% |  | 0 | 30887.58
Outcome 3.2: Improved management of the human-wildlife conflict |  |  |  | Q1 | Q2 | Q3 | Q4 | 0 | 200500 | 200500 | [7 empty] | 0 | 19047.02
Output 3.2.1: Pilot method to reduce the wildlife accident in priority sites | 45 | 3.2.1.1: Conduct study on the wildlife traffic accident issue | [7 empty] | 0 |  |  | 0 | 0
| 46 | 3.2.1.2: Install tools/facilities to pilot measures to reduce accidents | [6 empty] | 25000 | 25000 |  |  | 1 | 0 | 0%
| 47 | 3.2.1.3: Support in operation and monitoring of wildlife related traffic accidents in highway | [6 empty] | 2500 | 2500 |  |  | 1 | 1 | 100% |  |  |  | 2041.38
| 48 | 3.2.1.4: Support to erect fence in both side of Sikta irrigation canal | [6 empty] | 20000 | 20000 |  |  | 2 | 2 | 100% |  |  |  | 9570.88
[8 empty] | 0 | 47500 | 47500 |  |  | 4 | 3 | 66.67% |  |  | 0 | 11612.26
Output 3.2.2: Training and facilities for human wildlife conflict response | 49 | 3.2.2.1: Prepare species-specific guidelines for HWC management | [7 empty] | 0 |  |  | 0 | 0
| 50 | 3.2.2.2: Pictorial manual on Wildlife identification and behavior in Nepali and local dialects | [6 empty] | 4000 | 4000 |  |  | 1 | 0 | 0%
| 51 | 3.2.2.3: Conduct training on identification and behavior of wild animals to Divisional forest office staff | [6 empty] | 4000 | 4000 |  |  | 1 | 1 | 100% |  |  |  | 3676.93
| 52 | 3.2.2.4: Support Wildlife Rescue center | [6 empty] | 120000 | 120000 |  |  | 1 | 0 | 0%
| 53 | 3.2.2.5: Support wildlife rescue and handling equipment and training | [6 empty] | 5000 | 5000 |  |  | 2 | 2 | 100% |  |  |  | 3757.83
[8 empty] | 0 | 133000 | 133000 |  |  | 5 | 3 | 50% |  |  | 0 | 7434.76
Output 3.2.3: Community based HWC mitigate and preventive action implemented | 54 | 3.2.3.1: Conduct workshop on preventive and curative measures for HWC | [7 empty] | 0 |  |  | 0 | 0
| 55 | 3.2.3.2: Implement measures for HWC based on prepared plans (mentha plantation, biological/virtual fencing) | [6 empty] | 20000 | 20000 |  |  | 4 | 0 | 0%
| 56 | 3.2.3.3: Support to establish community-based insurance (crop, livestock) scheme | [7 empty] | 0 |  |  | 0 | 0
| 57 | 3.2.3.4: Implement community-based reporting system of HWC incidents | [7 empty] | 0 |  |  | 0 | 0
[8 empty] | 0 | 20000 | 20000 |  |  | 4 | 0 | 0% | 50% |  | 0 | 0
Outcome 3.3: Enhanced capacities of government agencies and community in curbing illegal wildlife crime |  |  |  | Q1 | Q2 | Q3 | Q4 | 0 | 20954.5455 | 20954.5455 | [7 empty] | 0 | 12172.87
Output 3.3.1: Community Based Anti poaching Units functional in priority areas | 58 | 3.3.1.1: Provide support for field gears to CBAPU members | [6 empty] | 5000 | 5000 |  |  | 100 | 0 | 0%
| 58 | 3.3.1.2: Provide technical and financial support for skill based training to CBAPU members | [7 empty] | 0 |  |  | 0 | 0
| 59 | 3.3.1.3: Establish revolving fund to initiate green enterprise for CBAPUs member (link to above activities) | [7 empty] | 0 |  |  | 0 | 0
[8 empty] | 0 | 5000 | 5000 |  |  | 100 | 0 | 0% |  |  | 0 | 0
Output 3.3.2: Training and operation support to Park staff, rangers on wildlife crime management | 60 | 3.3.2.1: Update training manual on illegal wildlife crime scene management | [7 empty] | 0 |  |  | 0 | 0
| 61 | 3.3.2.2: Conduct training to investigation officers level on Illegal wildlife crime scene management | [6 empty] | 3000 | 3000 |  |  | 1 | 1 | 100% |  |  |  | 2729.32
| 62 | 3.3.2.3: Support Transboundary coordination at local level | [6 empty] | 4000 | 4000 |  |  | 2 | 1 | 50% |  |  |  | 1671.33
| 63 | 3.3.2.4: Field program implementation support & coordination | [6 empty] | 8954.5455 | 8954.5455 |  |  | 1 | 1 | 100% |  |  |  | 7772.22
[8 empty] | 0 | 15954.5455 | 15954.5455 |  |  | 4 | 3 | 83.33% | 62.5% | 47.52% | 0 | 12172.87
COMPONENT 4: Monitoring and evaluation (M&E), knowledge management (KM), and regional coordination | [7 empty] | 0 | 101590.9091 | 101590.9091 | [7 empty] | 0 | 34625.79
Outcome 4.1: Improved coordination and dialogue on integrated landscape management from the local to national level |  |  |  | Q1 | Q2 | Q3 | Q4 | 0 | 56000 | 56000 | [7 empty] | 0 | 28067.85
Output 4.1.1: Information on ILM importance shared among key stakeholders | 64 | 4.1.1.1: Organize monthly dialogue through "Jaibik Chautari" (Biodiversity Platform) at field | [6 empty] | 8500 | 8500 |  |  | 1 | 1 | 100% |  |  |  | 3357.78
| 65 | 4.1.1.2: Organize annual technical thematic discussion session at center | [6 empty] | 3000 | 3000 |  |  | 1 | 0 | 0%
| 66 | 4.1.1.4: Establish and maintain online Landscape Knowledge Learning Platform (including project website) | [6 empty] | 3000 | 3000 |  |  | 1 | 1 | 100% |  |  |  | 1195.53
[8 empty] | 0 | 14500 | 14500 |  |  | 3 | 2 | 66.67% |  |  | 0 | 4553.31
Output 4.1.2: Mass awareness products on biodiversity conservation and integrated landscape management | 67 | 4.1.2.1: Provide technical and financial support to green/eco-clubs formation and its operation | [6 empty] | 16000 | 16000 |  |  | 8 | 8 | 100% |  |  |  | 14317.15
| 68 | 4.1.2.2: Support annual meetings of green/eco-clubs network at district level | [7 empty] | 0 |  |  | 0 | 0
| 69 | 4.1.2.3: Support special conservation events at local level | [6 empty] | 8000 | 8000 |  |  | 4 | 4 | 100% |  |  |  | 6104.8
| 70 | 4.1.2.4: Sensitize media (print and TV) on integrated landscape management | [7 empty] | 0 |  |  | 0 | 0
| 71 | 4.1.2.5: Support radio program (local dialects) on ILM | [6 empty] | 17500 | 17500 |  |  | 5 | 1 | 20% |  |  |  | 3092.59
[8 empty] | 0 | 41500 | 41500 |  |  | 17 | 13 | 73.33% | 70% |  | 0 | 23514.54
Outcome 4.2: Project monitoring system operates, systematically provides information on progress, and informs adaptive management to ensure results |  |  |  | Q1 | Q2 | Q3 | Q4 | 0 | 30000 | 30000 | [7 empty] | 0 | 4982.95
Output 4.2.1: Participatory planning and M&E system | 72 | 4.2.1.1: Organize project inception workshops at Kathmandu and field level | [7 empty] | 0 |  |  | 0 | 0
| 73 | 4.2.1.2: PAC/PEC planning review workshop (Central and Field) | [6 empty] | 6000 | 6000 |  |  | 3 | 3 | 100% |  |  |  | 167.59
| 74 | 4.2.1.3: Conduct periodic (trimester) workplan review and planning sessions | [6 empty] | 4000 | 4000 |  |  | 2 | 3 | 100% |  |  |  | 3167.27
| 75 | 4.2.1.4: Conduct periodic and joint monitoring visits | [6 empty] | 4000 | 4000 |  |  | 2 | 0 | 0%
| 76 | 4.2.1.5: Conduct Safeguard Monitoring visits | [6 empty] | 4000 | 4000 |  |  | 4 | 0 | 0%
| 77 | 4.2.1.6: Conduct training on "participatory monitoring and evaluation" to CFUGs and relevant sub-grantees | [6 empty] | 0 | 0 |  |  | 0 | 0
| 78 | 4.2.1.7: Capacity building/training of PSU staff (on project management - WWF network standards, report writing and GESI and safeguard) | [6 empty] | 5000 | 5000 |  |  | 1 | 1 | 100% |  |  |  | 1648.09
| 79 | 4.2.1.8: Organize Project Mid-term review workshops with all key stakeholders | [6 empty] | 0 | 0 |  |  | 0 | 0
| 80 | 4.9.1.9: Conduct Project Evaluations (Mid-term and terminal evaluation - GEF/SWC) | [6 empty] | 0 | 0 |  |  | 0 | 0
| 81 | 4.2.1.10: Annual Financial Audit | [6 empty] | 7000 | 7000
[8 empty] | 0 | 30000 | 30000 |  |  | 12 | 7 | 60% | 60% |  | 0 | 4982.95
Outcome 4.3: Project lessons shared |  |  |  | Q1 | Q2 | Q3 | Q4 | 0 | 15590.9091 | 15590.9091 | [7 empty] | 0 | 1574.99
Output 4.3.1: Project lessons captured and disseminated to project stakeholders and to other projects and partners | 82 | 4.3.1.1: Documentation on Traditional Knowledge associated to natural resources | [6 empty] | 10000 | 10000 |  |  | 1 | 0 | 0%
| 83 | 4.3.1.2: Prepare success stories and videos of the project | [6 empty] | 0 | 0 |  |  | 0 | 0
| 84 | 4.3.1.3: Print case studies and periodic project reports | [6 empty] | 0 | 0 |  |  | 0 | 0
| 85 | 4.3.1.4: Provide financial support to participate in national/international scientific forum for field staff | [6 empty] | 0 | 0 |  |  | 0 | 0
| 86 | 4.3.1.5: Provide financial support to publish journal articles | [6 empty] | 0 | 0 |  |  | 0 | 0
| 87 | 4.3.1.6: Field program implementation support & coordination | [6 empty] | 5590.9091 | 5590.9091 |  |  | 1 | 1 | 100% |  |  |  | 1574.99
| 88 | 4.2.1.7: Organize final project lessons sharing workshop | [6 empty] | 0 | 0 |  |  | 0 | 0
[8 empty] | 0 | 15590.9091 | 15590.9091 |  |  | 2 | 1 | 50% | 50% | 63.08% | 0 | 1574.99
B. Project Management Costs | [9 empty] | 389144.2045 | [7 empty] | 0 | 0
Office and field running costs |  |  |  | Q1 | Q2 | Q3 | Q4 | 0 | 47450 | 47450 | [7 empty] | 0 | 0
Project Management Unit | 56xx | Insurance, Maintenance, Utility | PMU | [5 empty] | 7363.6364 | 7363.6364
| 56xx | Office Rent | PMU | [5 empty] | 5836.3636 | 5836.3636
| 56xx | Equipment Running Cost | [6 empty] | 585.4545 | 585.4545
| 56xx | Vehicle Running Costs (Vehicle Repair) | [6 empty] | 5854.5455 | 5854.5455
| 56xx | Vehicle Running Costs (fuel for office purpose) | [6 empty] | 4090.9091 | 4090.9091
| 56xx | Photocopying | [6 empty] | 476.3636 | 476.3636
| 56xx | Postage & Shipping | [6 empty] | 2331.8182 | 2331.8182
| 56xx | Communications (phone, fax, internet) | [6 empty] | 3709.0909 | 3709.0909
| 56xx | Supplies | [6 empty] | 7854.5455 | 7854.5455
| 56xx | Field program implementation support coordination (Staffs travel and Inhouse Meeting) | PMU | [5 empty] | 6272.7273 | 6272.7273
| 56xx | Advertisment/Priniting and Publication | PMU | [5 empty] | 2727.2727 | 2727.2727
| 56xx | Bank charges | PMU | [5 empty] | 347.2727 | 347.2727
[8 empty] | 0 | 47450 | 47450 |  |  | 0 | 0 |  |  |  | 0 | 0
|  | Capital Assets | [5 empty] | 0 | 0 | 0 | [7 empty] | 0 | 0
| 58xx | Scanner | PMU | [6 empty] | 0 |  | Set | 2
| 58xx | LCD Projector with screen (1 for Kathmandu and 2 for Banke Office | PMU | [6 empty] | 0 |  | Set | 3
| 58xx | Camera | [7 empty] | 0 |  | Set | 6
| 58xx | Air Conditioners (3 for Banke Office) | [7 empty] | 0 |  | Set | 3
| 58xx | EPABX system setup | [7 empty] | 0 |  | Set | 2
| 58xx | Power backup system (inverter & battery for Banke Office) | [7 empty] | 0 |  | Set | 1
| 58xx | Desktop Screen (monitor) | [7 empty] | 0 |  | Set | 8
| 58xx | Vault for Kathmandu and Banke Office | [7 empty] | 0 |  | Set | 2
| 58xx | GPS (Banke Office) | [7 empty] | 0 |  | Set | 8
| 58xx | Spiral binding machine | [7 empty] | 0 |  | Set | 2
| 58xx | Air Cooler for Banke Office | [7 empty] | 0 |  | No. | 3
| 58xx | Microwave oven for Kathmandu Office | [7 empty] | 0 |  | No. | 1
| 58xx | Account Software (Activitywise reporting, VMS etc.) | [7 empty] | 0 |  | No | 1
| 58xx | Office 365 insallation, Sofware AMC etc | [7 empty] | 0 |  | times | 1
| 58xx | IT support | [7 empty] | 0 |  | times | 1
| 58xx | Bridger Liscence (annual recurring cost) | PMU | [6 empty] | 0 |  | times | 1
| 58xx | Office and restroom renovation, Kathmandu Office | PMU | [6 empty] | 0 |  | Times | 1
| 58xx | Equipment Motorbike | PMU | [6 empty] | 0 |  | No. | 6
[8 empty] | 0 | 0 | 0 |  |  | 52 |  |  |  |  | 0 | 0
|  | Personnel | [5 empty] | 341694.2045 | 0 | 341694.2045 | [7 empty] | 0 | 0
| 50xx | Project Coordinator | PMU |  |  |  |  | 36368.1818 |  | 36368.1818
| 50xx | Project Manager | PMU |  |  |  |  | 33590.4545 |  | 33590.4545
| 50xx | Finance and Administration Manager | PMU |  |  |  |  | 27906.1364 |  | 27906.1364
| 50xx | Field Manager | PMU |  |  |  |  | 21047.7273 |  | 21047.7273
| 50xx | Field Program Officer | PMU |  |  |  |  | 20145.6818 |  | 20145.6818
| 50xx | Field Finance/Compliance Officer | PMU |  |  |  |  | 20145.6818 |  | 20145.6818
| 50xx | Field Monitoring, Evaluation and Learning (MEL) Officer | PMU |  |  |  |  | 20446.3636 |  | 20446.3636
| 50xx | Field Finance and Administration Associate | PMU |  |  |  |  | 16086.4773 |  | 16086.4773
| 50xx | Field Program Assistant (4) | PMU |  |  |  |  | 45703.6364 |  | 45703.6364
| 50xx | Front Desk Assistant _KTM | PMU |  |  |  |  | 12027.2727 |  | 12027.2727
| 50xx | Front Desk Assistant _Field | PMU |  |  |  |  | 11726.5909 |  | 11726.5909
| 50xx | Communication Officer (100% ) | PMU |  |  |  |  | 21818.1818 |  | 21818.1818
| 50xx | Field Safeguard and GESI Officer | PMU |  |  |  |  | 23181.8182 |  | 23181.8182
| 50xx | Office Messenger (2) | PMU |  |  |  |  | 15750 |  | 15750
| 50xx | Driver (2) | PMU |  |  |  |  | 15750 |  | 15750
[8 empty] | 341694.2045 | 0 | 341694.2045 |  |  | 0 | 0 |  |  |  | 0 | 0
GRAND TOTAL (A+B) |  |  |  | YR 2 | [5 empty] | 1135054.1136 | [7 empty] | 0 | 162126.4
|  |  | Carry-over total (unspent funds from previous year) | [12 empty] | % achieved for activities overall | 44.87% | Actual budget for previous project year
|  |  | Request of funds for Upcoming Project Year | [6 empty] | 1135054.1136
[20 empty] | GL CODE | LMBIS CODE | ACT# NO# | COMPONENT / OUTCOME / OUTPUT/ACTIVITIES | RESPONSIBLE | TIMELINE |  |  |  | UNIT DESCRIPTION | TARGET | UNIT COST | TOTAL BUDGET | Remarks | COMPONENT |  |  |  |  | TOTAL BUDGET | [6 empty] | BUDGET BIFUCATION |  |  | Outcomes
[25 empty] | Q1 | Q2 | Q3 | Q4 | [5 empty] | Com.1 | Com.2 | Com.3 | Com.4 | Mgmt. | Jan-Mar 2021 | Apr-Jun 2021 | Jul-Sep 2021 | Oct-Dec 2021 | Jan-Mar 2022 | Apr-Jun 2022 | TOTAL Budget | TECHNICAL ASSISTANCE | PROGRAM FUNDING | TOTAL
[23 empty] | A. PERSONNEL COSTS |  | 0 | 0 | 0 | 0 |  |  |  | 341694.2045 |  | 58379.8687 | 41832.346 | 133332.8761 | 62713.2273 | 45435.8864 | 56949.0341 | 56949.0341 | 56949.0341 | 56949.0341 | 56949.0341 | 56949.0341 | 341694.2045 | 341694.2045 | 0 | 341694.2045
[20 empty] | 50xx |  |  | Project Coordinator | PMU |  |  |  |  | Mo. | 15 | 2424.5455 | 36368.1818 |  | 18184.0909 | 3636.8182 | 7273.6364 | 1818.4091 | 5455.2273 | 6061.3636 | 6061.3636 | 6061.3636 | 6061.3636 | 6061.3636 | 6061.3636 | 36368.1818 | 36368.1818 | 0 | 36368.1818
[20 empty] | 50xx |  |  | Project Manager | PMU |  |  |  |  | Mo. | 15 | 2239.3636 | 33590.4545 |  | 6718.0909 | 6718.0909 | 11756.6591 | 3359.0455 | 5038.5682 | 5598.4091 | 5598.4091 | 5598.4091 | 5598.4091 | 5598.4091 | 5598.4091 | 33590.4545 | 33590.4545 | 0 | 33590.4545
[20 empty] | 50xx |  |  | Finance and Administration Manager | PMU |  |  |  |  | Mo. | 15 | 1860.4091 | 27906.1364 |  | 3488.267 | 3488.267 | 9767.1477 | 5581.2273 | 5581.2273 | 4651.0227 | 4651.0227 | 4651.0227 | 4651.0227 | 4651.0227 | 4651.0227 | 27906.1364 | 27906.1364 | 0 | 27906.1364
[20 empty] | 50xx |  |  | Field Manager | PMU |  |  |  |  | Mo. | 15 | 1403.1818 | 21047.7273 |  | 3157.1591 | 3157.1591 | 10523.8636 | 4209.5455 | 0 | 3507.9545 | 3507.9545 | 3507.9545 | 3507.9545 | 3507.9545 | 3507.9545 | 21047.7273 | 21047.7273 | 0 | 21047.7273
[20 empty] | 50xx |  |  | Field Program Officer | PMU |  |  |  |  | Mo. | 15 | 1343.0455 | 20145.6818 |  | 2014.5682 | 4029.1364 | 10072.8409 | 4029.1364 | 0 | 3357.6136 | 3357.6136 | 3357.6136 | 3357.6136 | 3357.6136 | 3357.6136 | 20145.6818 | 20145.6818 | 0 | 20145.6818
[20 empty] | 50xx |  |  | Field Finance/Compliance Officer | PMU |  |  |  |  | Mo. | 15 | 1343.0455 | 20145.6818 |  | 2518.2102 | 2518.2102 | 7050.9886 | 4029.1364 | 4029.1364 | 3357.6136 | 3357.6136 | 3357.6136 | 3357.6136 | 3357.6136 | 3357.6136 | 20145.6818 | 20145.6818 | 0 | 20145.6818
[20 empty] | 50xx |  |  | Field Monitoring, Evaluation and Learning (MEL) Officer | PMU |  |  |  |  | Mo. | 15 | 1363.0909 | 20446.3636 |  | 0 | 0 | 0 | 20446.3636 | 0 | 3407.7273 | 3407.7273 | 3407.7273 | 3407.7273 | 3407.7273 | 3407.7273 | 20446.3636 | 20446.3636 | 0 | 20446.3636
[20 empty] | 50xx |  |  | Field Finance and Administration Associate | PMU |  |  |  |  | Mo. | 15 | 1072.4318 | 16086.4773 |  | 2010.8097 | 2010.8097 | 5630.267 | 3217.2955 | 3217.2955 | 2681.0795 | 2681.0795 | 2681.0795 | 2681.0795 | 2681.0795 | 2681.0795 | 16086.4773 | 16086.4773 | 0 | 16086.4773
[20 empty] | 50xx |  |  | Field Program Assistant (4) | PMU |  |  |  |  | Mo. | 15 | 3046.9091 | 45703.6364 |  | 2285.1818 | 4570.3636 | 36562.9091 | 2285.1818 |  | 7617.2727 | 7617.2727 | 7617.2727 | 7617.2727 | 7617.2727 | 7617.2727 | 45703.6364 | 45703.6364 | 0 | 45703.6364
[20 empty] | 50xx |  |  | Front Desk Assistant _KTM | PMU |  |  |  |  | Mo. | 15 | 801.8182 | 12027.2727 |  | 962.1818 | 962.1818 | 2886.5455 | 1202.7273 | 6013.6364 | 2004.5455 | 2004.5455 | 2004.5455 | 2004.5455 | 2004.5455 | 2004.5455 | 12027.2727 | 12027.2727 | 0 | 12027.2727
[20 empty] | 50xx |  |  | Front Desk Assistant _Field | PMU |  |  |  |  | Mo. | 15 | 781.7727 | 11726.5909 |  | 938.1273 | 938.1273 | 2814.3818 | 1172.6591 | 5863.2955 | 1954.4318 | 1954.4318 | 1954.4318 | 1954.4318 | 1954.4318 | 1954.4318 | 11726.5909 | 11726.5909 | 0 | 11726.5909
[20 empty] | 50xx |  |  | Communication Officer (100% ) | PMU |  |  |  |  | Mo. | 15 | 1454.5455 | 21818.1818 |  | 3490.9091 | 3490.9091 | 10472.7273 | 4363.6364 | 0 | 3636.3636 | 3636.3636 | 3636.3636 | 3636.3636 | 3636.3636 | 3636.3636 | 21818.1818 | 21818.1818 | 0 | 21818.1818
[20 empty] | 50xx |  |  | Field Safeguard and GESI Officer | PMU |  |  |  |  | Mo. | 15 | 1545.4545 | 23181.8182 |  | 3477.2727 | 3477.2727 | 11590.9091 | 4636.3636 | 0 | 3863.6364 | 3863.6364 | 3863.6364 | 3863.6364 | 3863.6364 | 3863.6364 | 23181.8182 | 23181.8182 | 0 | 23181.8182
[20 empty] | 50xx |  |  | Office Messenger (2) | PMU |  |  |  |  | Mo. | 15 | 1050 | 15750 |  | 1260 | 1260 | 3780 | 1575 | 7875 | 2625 | 2625 | 2625 | 2625 | 2625 | 2625 | 15750 | 15750 | 0 | 15750
[20 empty] | 50xx |  |  | Driver (2) | PMU |  |  |  |  | Mo. | 15 | 1050 | 15750 |  | 7875 | 1575 | 3150 | 787.5 | 2362.5 | 2625 | 2625 | 2625 | 2625 | 2625 | 2625 | 15750 | 15750 | 0 | 15750
[23 empty] | B. ACTIVITY COST | [8 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on Y185: Narayan K.C.: liNE Ministry Budget Informaiton System
Note on AI193: Author: 120,000/Fulltime

## AWPB Yr 3
Period: Year 3 (July 22 - June 23) (FY 79/80)
| ANNUAL WORK PLAN | [11 empty] | WORK PLAN TRACKING (Tracking at end of project year)
COMPONENT / OUTCOME / OUTPUT | # | ACTIVITIES | Responsible | YEAR X TIMING |  |  |  | BUDGET in USD |  | x | UNIT DESCRIPTION | TARGET | # UNIT(S) ACHIEVED | % ACHIEVED BY ACTIVITY (# unit(s) achieved / target) | % ACHIEVED BY OUTCOME | % ACHIEVED BY COMPONENT | BUDGET (actual, by Component)
|  |  |  | Q1 | Q2 | Q3 | Q4 | Unit Cost | Total | if activity is carried over from previous year | # of | [5 empty] | in Rupee | in USD
A. ACTIVITY COSTS | [8 empty] | 931851.3455 | [7 empty] | 49973731 | 391413.95
COMPONENT 1: National capacity and enabling environment for cross-sectoral coordination to promote forest and landscape conservation | [8 empty] | 219787.1818 | [7 empty] | 2313702 | 18121.83
Outcome 1.1: Improved inter-sectoral coordination from Federal, State to Local level for sustainable forest management and integrated landscape management |  |  |  | Q1 | Q2 | Q3 | Q4 |  | 54150.8182 | [7 empty] | 865757 | 6780.95
Output 1.1.1 : Cross-sectoral coordination mechanisms established to support integrated landscape management for conservation outcomes at different levels | 89 | 1.1.1.1: Provide support to NBCC committee (ensure gender inclusive team) | PMU |  |  |  |  | 1818.1818 | 1818.1818 |  | Event | 1 | 0 | 0% |  |  | 0 | 0
| 90 | 1.1.1.2 Organize State level Biodiversity Co-ordination Committee (State 2,3,5,7 and Karnali) meetings | MoTIFE/MoFESC |  |  |  |  | 1363.6364 | 10909.0909 |  | Meetings | 8 | 0 | 0% |  |  | 0 | 0
| 91 | 1.1.1.3 Provide technical and financial support to State Biodiversity Co-ordination committee | MoTIFE/MoFESC |  |  |  |  | 1363.6364 | 5454.5455 |  | Times | 4 | 0 | 0% |  |  | 0 | 0
| 92 | 1.1.1.4 Organize inter-ministerial coordination mechanism for wildlife friendly infrastructure | PMU |  |  |  |  | 2727.2727 | 2727.2727 |  | Multistakeholder meeting | 1 | 0 | 0% |  |  | 0 | 0
| 93 | 1.1.1.5 Organize inter-state coordination (2, 3, Gandaki, 5, Karnali, 7) for implementation of the NBSAP and TAL Strategy | PMU |  |  |  |  | 1818.1818 | 1818.1818 |  | Workshop | 1 | 0 | 0% |  |  | 0 | 0
| 94 | 1.1.1.6 Carry out cluster meetings with Municipalities | PMU |  |  |  |  | 454.5455 | 4545.4545 |  | Meetings | 10 | 3 | 30% |  |  | 139343 | 1091.39
| 95 | 1.1.1.7 Conduct final review of NBSAP (2014-2020) | PMU |  |  |  |  | 15969 | 15969 |  | Report | 1 | 0 | 0% |  |  | 0 | 0
| 96 | 1.1.1.8Provide technical and financial support to WCCB | BaNP/BNP |  |  |  |  | 1363.6364 | 2727.2727 |  | District cell? | 2 | 2 | 100% |  |  | 298221 | 2335.78
| 97 | 1.1.1.9 Field program implementation support & coordination | PMU |  |  |  |  | 681.8182 | 8181.8182 |  | Month of staff support/ travel | 12 | 12 | 100% |  |  | 428193 | 3353.78
[9 empty] | 54150.8182 |  |  | 40 | 17 | 25.56% | 25.56% |  | 865757 | 6780.95
Outcome 1.2 Capacity increased for multi-stakeholder and cross-sector landscape and forest planning and management |  |  |  | Q1 | Q2 | Q3 | Q4 |  | 165636.3636 | [7 empty] | 1447945 | 11340.88
Output 1.2.1. Conservation Leadership Training provided | 98 | 1.2.1.1: Conduct training to ILM coordinators for capturing international best practice and applying this to the local context | PMU |  |  |  |  | 1000 | 12000 |  | Training | 1 | 0 | 0% |  |  | 0 | 0
[9 empty] | 12000 |  |  | 1 | 0 | 0% |  |  | 0 | 0
Output 1.2.2 Training courses provided on key subjects for integrated landscape management for responsible federal and state government staff | 99 | 1.2.2.1: Conduct training on Biodiversity conservation and monitoring | PMU |  |  |  |  | 4545.4545 | 4545.4545 |  | Training | 1 | 0 | 0% |  |  | 0 | 0
| 100 | 1.1.2.2: Conduct training on Disaster Risk Management | PMU |  |  |  |  | 4545.4545 | 4545.4545 |  | Training | 1 | 0 | 0% |  |  | 0 | 0
| 101 | 1.1.2.3: Orientation on roles and responsibilities for new park staff (senior/game scouts) | BaNP/BNP |  |  |  |  | 909.0909 | 1818.1818 |  | Orientation | 2 | 1 | 50% |  |  | 100000 | 783.24
| 102 | 1.1.2.4: Orientation on roles and responsibilities for new divisional staff | DFO-B/DFO-P |  |  |  |  | 909.0909 | 1818.1818 |  | Orientation | 2 | 2 | 100% |  |  | 200000 | 1566.48
[9 empty] | 12727.2727 |  |  | 6 | 3 | 37.5% |  |  | 300000 | 2349.72
Output 1.2.3 Small grants for innovation in ILM (conservation, natural resource, and landscape management) in TAL corridors and PA buffer zones | 103 | 1.2.3.1:Provide Individual grant (Bachelors and Master's thesis) | PMU |  |  |  |  | 681.8182 | 10909.0909 |  | Training | 16 | 17 | 100% |  |  | 1147945 | 8991.16
| 104 | 1.1.3.2: Provide Institutional grant to Academic Institutional and CBOs/CSOs | PMU |  |  |  |  | 15000 | 30000 |  | grant package | 2 | 0 | 0% |  |  | 0 | 0
| 105 | 1.1.3.3: Provide innovation grant to the government agencies (National Park, Forest Division, Research and Training Centre) at state level | PMU |  |  |  |  | 50000 | 100000 |  | grant package | 2 | 0 | 0% |  |  | 0 | 0
[9 empty] | 140909.0909 |  |  | 20 | 17 | 33.33% | 28.24% | 26.67% | 1147945 | 8991.16
Component 2: Integrated Planning for Protected Area Buffer Zones and Critical Corridors in the Terai Arc Landscape | [8 empty] | 88681.8182 | [7 empty] | 4481524 | 35101.06
Outcome 2.1: Improved corridor planning for TAL corridors (Brahmadev, Karnali and Kamdi) |  |  |  | Q1 | Q2 | Q3 | Q4 |  | 33000 | [7 empty] | 3222890 | 25242.94
Output 2.1.1 Biodiversity surveys, socio-economic surveys, and local stakeholder consultation for Brahmadev , Karnali, and Kamdi corridors to determine feasibility of appropriate models for community-based natural resource management | 106 | 2.1.1.1: Conduct assessment to update biodiversity inventory and socio-economic status in corridors (incorporating GESI aspect, indigenous people and access restriction information) | PMU |  |  |  |  | 15000 | 30000 |  | Study | 2 | 2 | 100% |  |  | 3222890 | 25242.94
| 107 | 2.1.1.2: Provide technical support to review existing forest encroachment status and response options considering GESI aspect and any necessary safeguards management plans (e.g. IPP or LRP)” | PMU | [5 empty] | 0 |  |  | 1 | 0 | 0% |  |  | 0 | 0
| 108 | 2.1.1.3: Prepare corridor/bottleneck assessment report with GESI and safeguards integration | PMU |  |  |  |  | 3000 | 3000 |  | Report | 1 | 0 | 0% |  |  | 0 | 0
[9 empty] | 33000 |  |  | 4 | 2 | 33.33% | 33.33% |  | 3222890 | 25242.94
Outcome 2.2: Improved participatory planning for sustainable management of in Banke-Bardia complex |  |  |  | Q1 | Q2 | Q3 | Q4 |  | 55681.8182 | [7 empty] | 1258634 | 9858.12
Output 2.2.1: Land uses, biodiversity values, forest carbon, and key threats assessed, mapped, reported and disseminated to identify priority villages and forest areas in the targeted PA buffer zones and corridors | 109 | 2.2.1.1: Conduct participatory assessments in targeted PA buffer zones and corridors to identify priority community and forest areas | PMU | [5 empty] | 0 | [7 empty] | 0 | 0
| 110 | 2.2.1.2: Conduct resource mapping of CFUGs at corridor level and BZUCs | PMU |  |  |  |  | 17500 | 17500 |  | Study | 1 | 0 | 0% |  |  | 0 | 0
| 111 | 2.2.1.3: Carry out consultations at identified communities | PMU |  |  |  |  | 136.3636 | 4772.7273 |  | Consultations | 35 | 35 | 100% |  |  | 332400 | 2603.49
| 112 | Dissemination of threats, values, land uses, etc to priority villages and forest areas in the targeted PA buffer zones and corridors | [6 empty] | 0 |  | Orientations |  | 0 |  |  |  | 0 | 0
[9 empty] | 22272.7273 |  |  | 36 | 35 | 50% |  |  | 332400 | 2603.49
Output 2.2.2: Sustainable Forest Management Operational Plans developed or revised for priority forest areas, incorporating the assessment from 2.2.1 | 113 | 2.2.2.1: Provide financial support to develop State forest sector strategies (including Community Forests, Protected Forests and Leash-hold Forest) | MoTIFE/MoFESC |  |  |  |  | 9090.9091 | 18181.8182 |  | Strategy | 2 | 0 | 0% |  |  | 0 | 0
| 114 | 2.2.2.2: Support CFUGs and BZ CFUGs to develop/revise forest operational plan (GESI aspect is revised/incorporated) | DFO |  |  |  |  | 227.2727 | 7954.5455 |  | Support to CFUGs | 35 | 24 | 68.57% |  |  | 675000 | 5286.87
| 115 | 2.2.2.3: Field program implementation support & coordination | PMU |  |  |  |  | 606.0606 | 7272.7273 |  | Month of staff support/ travel | 12 | 12 | 100% |  |  | 251234 | 1967.76
[9 empty] | 33409.0909 |  |  | 49 | 36 | 56.19% | 53.71% | 46.07% | 926234 | 7254.63
COMPONENT 3: Forest and human-wildlife conflict management for improved conservation of targeted protected area buffer zones and corridors in the Terai Arc Landscape | [7 empty] | 0 | 533234.4545 | [7 empty] | 37373958 | 292727.56
Outcome 3.1: Strengthen livelihoods and biodiversity conservation through Sustainable forest management practices |  |  |  | Q1 | Q2 | Q3 | Q4 | 0 | 310436.3636 | [7 empty] | 20465121 | 160290.9
Output 3.1.1: Training and tools to local government on SFM |  | 3.1.1.1: Prepare Sustainable Forest Management Training (SFM) Manual incorporating GESI | [6 empty] | 0 |  | Manual
|  | 3.1.1.2: Provide "Training of Trainers" (TOT) to Division Forest Offices staff based on SFM Training Manual | [6 empty] | 0 |  | Training
| 116 | 3.1.1.3 Establish Forest Management Information system (FMIS) including forest fire management | MoITFE/MoEFSC |  |  |  |  | 14500 | 14500 |  | Support package | 1 | 0 | 0% |  |  | 0 | 0
| 117 | 3.1.1.4: Support the State Forest Directorate fire reporting system | MoITFE/MoEFSC |  |  |  |  | 4545.4545 | 9090.9091 |  | Support Package | 2 | 0 | 0% |  |  | 0 | 0
| 118 | 3.1.1.5: Support forest fire management through innovative tools and techniques such as leaf litter collection and composting (within targeted sites identified in component 2) | BaNP/BNP/DFO-P/DFP-B |  |  |  |  | 2045.4545 | 8181.8182 |  | Support Package | 4 | 4 | 100% |  |  | 896719 | 7023.46
| 119 | 3.1.1.6 Provide multi-year support for nursery to Division forest offices (within targeted sites identified in component 2) | DFO-P/DFP-B |  |  |  |  | 31818.1818 | 63636.3636 |  | No.? | 2 | 2 | 100% |  |  | 4770060 | 37360.99
[9 empty] | 95409.0909 |  |  | 9 | 6 | 50% |  |  | 5666779 | 44384.45
Output 3.1.2: Technical support to CFUGs, BZCFUGs and land holders for forest management | 120 | 3.1.2.3: Support BZUCs annual meetings for Bardia and Banke NP Buffer Zones (northern side) | PMU |  |  |  |  | 181.8182 | 1090.9091 |  | Support to BZUCs | 6 | 7 | 100% |  |  | 89660 | 702.25
| 121 | 3.1.2.4: Provide coaching on "Governance and Financial management" for CFUGs of corridors and PA Buffer zones | PMU |  |  |  |  | 1818.1818 | 1818.1818 |  | Coaching Event | 1 | 1 | 100% |  |  | 11390 | 89.21
| 122 | 3.1.2.5: Provide support private forest development (providing seedling, irrigation, fencing) | DFO/Park |  |  |  |  | 910 | 27300 |  | Ha supported | 30 | 0 | 0% |  |  | 78456 | 614.5
| 123 | 3.1.2.6: Support to register private forest | DFO | [5 empty] | 0 | [7 empty] | 0 | 0
[9 empty] | 30209.0909 |  |  | 37 | 8 | 66.67% |  |  | 179506 | 1405.96
Output 3.1.3: Forests and associated habitat in priority buffer zones and corridors managed sustainably | 124 | 3.1.3.2: Provide financial and technical support to improve livestock management (AI, fodder plant support, feeding trough, vet support, stall improvement) | PMU |  |  |  |  | 227.2727 | 45454.5455 |  | Households supported | 200 | 202 | 100% |  |  | 4957646 | 38830.24
| 125 | 3.1.3.3: Provide financial and technical support for management of grassland and wetland in project targeted area | BaNP/BNP/DFO-P/DFP-B |  |  |  |  | 12727.2727 | 50909.0909 |  | Support Package | 4 | 4 | 100% |  |  | 5436755 | 42582.81
| 126 | 3.1.3.4: Provide financial and technical support for river bank protection in project targeted area | BaNP/BNP/DFO-P/DFP-B |  |  |  |  | 9090.9091 | 45454.5455 |  | Support Package | 5 | 3 | 60% |  |  | 2898496 | 22702.16
| 127 | 3.1.3.5: Safeguard plan implementation | PMU |  |  |  |  | 20000 | 20000 |  | ? | 1 | 1 | 100% |  |  | 1229939 | 9633.37
| 128 | 3.1.3.6: Provide financial and technical support to small scale green enterprises in project targeted area | PMU |  |  |  |  | 18500 | 18500 |  | Support Package | 1 | 1 | 100% |  |  | 96000 | 751.91
| 129 | 3.1.3.7: Provide financial and technical support to develop business plan | PMU |  |  |  |  | 4500 | 4500 |  | Support package | 1 | 0 | 0% |  |  | 0 | 0
[9 empty] | 184818.1818 |  |  | 212 | 211 | 76.67% | 66.15% |  | 14618836 | 114500.49
Outcome 3.2: Improved management of the human-wildlife conflict |  |  |  | Q1 | Q2 | Q3 | Q4 |  | 192318.1818 | [7 empty] | 14372875 | 112574.01
Output 3.2.1: Pilot method to reduce the wildlife accident in priority sites | 130 | 3.2.1.1: Conduct study on the wildlife traffic accident issue | PMU |  |  |  |  | 3000 | 3000 |  | Study | 1 | 1 | 100% |  |  | 326005 | 2553.4
|  | 3.2.1.2: Install tools/facilities to pilot measures to reduce accidents | [6 empty] | 0
| 131 | 3.2.1.3: Support in operation and monitoring of wildlife related traffic accidents in highway | BNP/BaNP |  |  |  |  | 1363.6364 | 2727.2727 |  | Support package | 2 | 2 | 100% |  |  | 299998 | 2349.7
|  | 3.2.1.4: Support to erect fence in both side of Sikta irrigation canal | [6 empty] | 0
[9 empty] | 5727.2727 |  |  | 3 | 3 | 100% |  |  | 626003 | 4903.1
Output 3.2.2: Training and facilities for human wildlife conflict response | 132 | 3.2.2.1: Prepare species-specific guidelines for HWC management | PMU |  |  |  |  | 4545.4545 | 4545.4545 |  | Guideline | 1 | 0 | 0% |  |  | 0 | 0
| 133 | 3.2.2.2: Pictorial manual on Wildlife identification and behavior in Nepali and local dialects | PMU |  |  |  |  | 4500 | 4500 |  | Manual | 1 | 0 | 0% |  |  | 0 | 0
| 134 | 3.2.2.3: Conduct training on identification and behavior of wild animals to Divisional forest office staff | DFO-B/DFO-P |  |  |  |  | 1818.1818 | 3636.3636 |  | Training | 2 | 2 | 100% |  |  | 400000 | 3132.96
| 135 | 3.2.2.4: Support Wildlife Rescue center | Park |  |  |  |  | 109090.9091 | 109090.9091 |  | Construction of rescue center | 1 | 1 | 100% |  |  | 8674669 | 67943.42
| 136 | 3.2.2.5: Support wildlife rescue and handling equipment and training | BaNP/BNP?DFO-B/DFO-P |  |  |  |  | 1931.8182 | 7727.2727 |  | Support Package | 4 | 4 | 100% |  |  | 815221 | 6385.13
[9 empty] | 129500 |  |  | 9 | 7 | 60% |  |  | 9889890 | 77461.51
Output 3.2.3: Community based HWC mitigate and preventive action implemented | 137 | 3.2.3.1: Conduct workshop on preventive and curative measures for HWC | BNP |  |  |  |  | 4545.4545 | 4545.4545 |  | Workshop | 1 | 1 | 100% |  |  | 498000 | 3900.53
| 138 | 3.2.3.2: Implement measures for HWC based on prepared plans (mentha plantation, biological/virtual fencing) | PMU |  |  |  |  | 12000 | 48000 |  | Support package | 4 | 4 | 100% |  |  | 3108982 | 24350.77
|  | 3.2.3.3: Support to establish community-based insurance (crop, livestock) scheme | [6 empty] | 0
| 139 | 3.2.3.4: Implement community-based reporting system of HWC incidents | BNP/DFO-B |  |  |  |  | 2272.7273 | 4545.4545 |  | Support package | 2 | 1 | 50% |  |  | 250000 | 1958.1
[9 empty] | 57090.9091 |  |  | 7 | 6 | 83.33% | 75% |  | 3856982 | 30209.4
Outcome 3.3: Enhanced capacities of government agencies and community in curbing illegal wildlife crime |  |  |  | Q1 | Q2 | Q3 | Q4 |  | 30479.9091 | [7 empty] | 2535962 | 19862.65
Output 3.3.1: Community Based Anti poaching Units functional in priority areas | 140 | 3.3.1.1: Provide support for field gears to CBAPU members | PMU |  |  |  |  | 2727.2727 | 10909.0909 |  | Support package | 4 | 4 | 100% |  |  | 1144168 | 8961.57
|  | 3.3.1.2: Provide technical and financial support for skill based training to CBAPU members | PMU | [5 empty] | 0 |  | Support package
|  | 3.3.1.3: Establish revolving fund to initiate green enterprise for CBAPUs member (link to above activities) | DFO/Park | [5 empty] | 0 |  | Support package
[9 empty] | 10909.0909 |  |  | 4 | 4 | 100% |  |  | 1144168 | 8961.57
Output 3.3.2: Training and operation support to Park staff, rangers on wildlife crime management | 141 | 3.3.2.1: Update training manual on illegal wildlife crime scene management | PMU |  |  |  |  | 4000 | 4000 |  |  | 1 | 0 | 0% |  |  | 0 | 0
| 142 | 3.3.2.2: Conduct training to investigation officers level on Illegal wildlife crime scene management | DFO/Park |  |  |  |  | 2727.2727 | 5454.5455 |  |  | 2 | 2 | 100% |  |  | 600000 | 4699.44
| 143 | 3.3.2.3: Support Transboundary coordination at local level | DFO/Park |  |  |  |  | 1363.6364 | 2727.2727 |  |  | 2 | 1 | 50% |  |  | 199480 | 1562.4
| 144 | 3.3.2.4: Field program implementation support & coordination | PMU |  |  |  |  | 615.75 | 7389 |  |  | 12 | 12 | 100% |  |  | 592314 | 4639.24
[9 empty] | 19570.8182 |  |  | 17 | 15 | 62.5% | 70% | 70% | 1391794 | 10901.08
COMPONENT 4: Monitoring and evaluation (M&E), knowledge management (KM), and regional coordination | [8 empty] | 90147.8909 | [7 empty] | 5804547 | 45463.5
Outcome 4.1: Improved coordination and dialogue on integrated landscape management from the local to national level |  |  |  | Q1 | Q2 | Q3 | Q4 |  | 36318.1818 | [7 empty] | 2997532 | 23477.85
Output 4.1.1: Information on ILM importance shared among key stakeholders | 145 | 4.1.1.1: Organize monthly dialogue through "Jaibik Chautari" (Biodiversity Platform) at field | [5 empty] | 909.0909 | 3636.3636 |  | Monthly meetings? | 4 | 4 | 100% |  |  | 392074 | 3070.88
| 146 | 4.1.1.2: Organize annual technical thematic discussion session at center | [5 empty] | 2727.2727 | 2727.2727 |  | Discussion convened | 1 | 1 | 100% |  |  | 48740 | 381.75
| 147 | 4.1.1.4: Establish and maintain online Landscape Knowledge Learning Platform (including project website) | [5 empty] | 909.0909 | 909.0909 |  | Platform established w/ website | 1 | 1 | 100% |  |  | 97180 | 761.15
[9 empty] | 7272.7273 |  |  | 6 | 6 | 100% |  |  | 537994 | 4213.78
Output 4.1.2: Mass awareness products on biodiversity conservation and integrated landscape management | 148 | 4.1.2.1: Provide technical and financial support to green/eco-clubs formation and its operation | [5 empty] | 1363.6364 | 13636.3636 |  | Eco-clubs supported | 10 | 12 | 100% |  |  | 1446488 | 11329.46
|  | 4.1.2.2: Support annual meetings of green/eco-clubs network at district level | [6 empty] | 0
| 149 | 4.1.2.3: Support special conservation events at local level | [5 empty] | 1818.1818 | 7272.7273 |  | Events | 4 | 4 | 100% |  |  | 727725 | 5699.83
| 150 | 4.1.2.4: Sensitize media (print and TV) on integrated landscape management | [5 empty] | 3636.3636 | 3636.3636 |  | Package? | 1 | 1 | 100% |  |  | 285325 | 2234.78
| 151 | 4.1.2.5: Support radio program (local dialects) on ILM | [5 empty] | 4500 | 4500 |  | Audio programs supported | 1 | 0 | 0% |  |  | 0 | 0
[9 empty] | 29045.4545 |  |  | 16 | 17 | 75% | 85.71% |  | 2459538 | 19264.07
Outcome 4.2: Project monitoring system operates, systematically provides information on progress, and informs adaptive management to ensure results |  |  |  | Q1 | Q2 | Q3 | Q4 |  | 31227.2727 | [7 empty] | 1029528 | 8063.67
Output 4.2.1: Participatory planning and M&E system |  | 4.2.1.1: Organize project inception workshops at Kathmandu and field level | [6 empty] | 0
| 152 | 4.2.1.2: PAC/PEC planning review workshop (Central and Field) | PMU |  |  |  |  | 454.5455 | 2272.7273 |  | workshops | 5 | 1 | 20% |  |  | 34300 | 268.65
| 153 | 4.2.1.3: Conduct periodic (trimester) workplan review and planning sessions | PMU |  |  |  |  | 1818.1818 | 7272.7273 |  | Sessions | 4 | 2 | 50% |  |  | 394231 | 3087.77
| 154 | 4.2.1.4: Conduct periodic and joint monitoring visits | PMU |  |  |  |  | 1818.1818 | 3636.3636 |  | Monitoring visits | 2 | 2 | 100% |  |  | 28680 | 224.63
| 155 | 4.2.1.5: Conduct Safeguard Monitoring visits | PMU |  |  |  |  | 2272.7273 | 4545.4545 |  | Visits | 2 | 1 | 50% |  |  | 41525 | 325.24
| 156 | 4.2.1.6: Conduct training on "participatory monitoring and evaluation" to CFUGs and relevant sub-grantees | PMU |  |  |  |  | 3636.3636 | 3636.3636 |  | Training | 1 | 1 | 100% |  |  | 310639 | 2433.05
| 157 | 4.2.1.7: Capacity building/training of PSU staff (on project management - WWF network standards, report writing and GESI and safeguard) | PMU |  |  |  |  | 3500 | 3500 |  | Training package | 1 | 1 | 100% |  |  | 220153 | 1724.33
|  | 4.2.1.8: Organize Project Mid-term review workshops with all key stakeholders | PMU | [5 empty] | 0
|  | 4.9.1.9: Conduct Project Evaluations (Mid-term and terminal evaluation - GEF/SWC) | PMU | [5 empty] | 0
| 160 | 4.2.1.10: Annual Financial Audit | PMU |  |  |  |  | 6363.6364 | 6363.6364 |  |  | 1 | 1 | 100% |  |  | 0 | 0
[9 empty] | 31227.2727 |  |  | 16 | 9 | 74.29% | 74.29% |  | 1029528 | 8063.67
Outcome 4.3: Project lessons shared |  |  |  | Q1 | Q2 | Q3 | Q4 |  | 22602.4364 | [7 empty] | 1777487 | 13921.98
Output 4.3.1: Project lessons captured and disseminated to project stakeholders and to other projects and partners |  | 4.3.1.1: Documentation on Traditional Knowledge associated to natural resources | PMU | [5 empty] | 0
|  | 4.3.1.2: Prepare success stories and videos of the project | PMU |  |  |  |  | 0 | 0
| 161 | 4.3.1.3: Print case studies and periodic project reports | PMU |  |  |  |  | 4500 | 4500 |  | Package | 1 | 1 | 100% |  |  | 173778 | 1361.1
|  | 4.3.1.4: Provide financial support to participate in national/international scientific forum for field staff | PMU |  |  |  |  | 0 | 0
|  | 4.3.1.5: Provide financial support to publish journal articles | PMU |  |  |  |  | 0 | 0
| 162 | 4.3.1.6: Field program implementation support & coordination | PMU |  |  |  |  | 1508.5364 | 18102.4364 |  | Staff travel and DSA | 12 | 12 | 100% |  |  | 1603709 | 12560.88
|  | 4.2.1.7: Organize final project lessons sharing workshop | PMU |  |  |  |  | 0 | 0
[8 empty] | 6008.5364 | 22602.4364 |  |  | 13 | 13 | 100% | 100% | 82.5% | 1777487 | 13921.98
B. Project Management Costs | [8 empty] | 424143.4091 | [7 empty] | 2641358.3 | 20688.15
Office and field running costs |  |  |  | Q1 | Q2 | Q3 | Q4 |  | 43857.9091 | [7 empty] | 1609588.3 | 12606.93
Project Management Unit | 56xx | Office Utility | PMU |  |  |  |  | 318 | 3816 |  | Months | 12 |  |  |  |  | 38010 | 297.71
| 56xx | Office Maintenance | PMU |  |  |  |  | 91 | 1092 |  |  | 12 |  |  |  |  | 71352 | 558.86
| 56xx | Office Insurance | PMU |  |  |  |  | 1363.6364 | 1363.6364 |  |  | 1 |  |  |  |  | 82343 | 644.94
| 56xx | Office Rent | PMU |  |  |  |  | 182 | 2184 |  | Months | 12 |  |  |  |  | 196087 | 1535.83
| 56xx | Equipment Running Cost | PMU |  |  |  |  | 45 | 540 |  | Months | 12 |  |  |  |  | 0 | 0
| 56xx | Vehicle Running Costs (Vehicle Repair) | PMU |  |  |  |  | 318 | 3816 |  | Months | 12 |  |  |  |  | 226762 | 1776.09
| 56xx | Vehicle Running Costs (fuel for office purpose) | PMU |  |  |  |  | 409 | 4908 |  | Months | 12 |  |  |  |  | 278749 | 2183.27
| 56xx | Photocopying | PMU |  |  |  |  | 22.7273 | 272.7273 |  | Months | 12 |  |  |  |  | 335 | 2.62
| 56xx | Postage & Shipping | PMU |  |  |  |  | 90.9091 | 1090.9091 |  | Months | 12 |  |  |  |  | 27053 | 211.89
| 56xx | Communications (phone, fax, internet) | PMU |  |  |  |  | 318.1818 | 3818.1818 |  | Months | 12 |  |  |  |  | 78339 | 613.58
| 56xx | Supplies | PMU |  |  |  |  | 545.4545 | 6545.4545 |  | Months | 12 |  |  |  |  | 403959 | 3163.97
| 56xx | Field program implementation support coordination (Staffs travel and Inhouse Meeting) | PMU |  |  |  |  | 780.0833 | 9361 |  | LS | 12 |  |  |  |  | 60182 | 471.37
| 56xx | Advertisment/Priniting and Publication | PMU |  |  |  |  | 950 | 4750 |  |  | 5 |  |  |  |  | 146402 | 1146.68
| 56xx | Bank charges | PMU |  |  |  |  | 25 | 300 |  | Months | 12 |  |  |  |  | 15.3 | 0.12
[9 empty] | 43857.9091 |  |  | 150 | 0 |  |  |  | 1609588.3 | 12606.93
|  | Capital Assets | [6 empty] | 21595 | [7 empty] | 1031770 | 8081.22
| 58xx | Cupboard/File Racks ( for Banke and for Kathmandu Office) | PMU |  |  |  |  | 318.1818 | 954.5455 |  | Set | 3 |  |  |  |  | 34000 | 266.3
| 58xx | Office Board/Notice boards etc | PMU |  |  |  |  | 90.9091 | 272.7273 |  | Nos | 3 |  |  |  |  | 0 | 0
| 58xx | Laptop (with dock-in set) | PMU |  |  |  |  | 1000 | 5000 |  | Set | 5 |  |  |  |  | 462799 | 3624.82
| 58xx | Data Backup/Hard Drive | PMU |  |  |  |  | 136.3636 | 545.4545 |  | Set | 4 |  |  |  |  | 44000 | 344.63
| 58xx | CC Camera for Banke Office | PMU |  |  |  |  | 454.5455 | 454.5455 |  | Set | 1 |  |  |  |  | 42155 | 330.17
| 58xx | Printers | PMU |  |  |  |  | 363.6364 | 727.2727 |  | Set | 2 |  |  |  |  | 79500 | 622.68
| 58xx | Office Table | PMU |  |  |  |  | 181.8182 | 727.2727 |  | Set | 4 |  |  |  |  | 0 | 0
| 58xx | Mixture | PMU |  |  |  |  | 72.7273 | 72.7273 |  | Set | 1 |  |  |  |  | 7006 | 54.87
| 58xx | Cameras | PMU |  |  |  |  | 454.5455 | 909.0909 |  | Set | 2 |  |  |  |  | 0 | 0
| 58xx | Revolving Chairs | PMU |  |  |  |  | 109.0909 | 981.8182 |  | Set | 9 |  |  |  |  | 65600 | 513.81
| 58xx | Projector-Portable | PMU |  |  |  |  | 909.0909 | 909.0909 |  | Set | 1 |  |  |  |  | 99800 | 781.67
| 58xx | Projector-Screen | PMU |  |  |  |  | 136.3636 | 272.7273 |  | Set | 2 |  |  |  |  | 16200 | 126.88
| 58xx | Desktop Screen (monitor) | PMU |  |  |  |  | 381.8182 | 1527.2727 |  | Set | 4 |  |  |  |  | 82800 | 648.52
| 58xx | GPS (Banke Office) | PMU |  |  |  |  | 181.8182 | 363.6364 |  | Set | 2 |  |  |  |  | 0 | 0
| 58xx | Account Software (Activitywise reporting, AMC etc.) | PMU |  |  |  |  | 454.5455 | 454.5455 |  | No | 1 |  |  |  |  | 0 | 0
| 58xx | Office 365 insallation, Sofware AMC etc | PMU |  |  |  |  | 1818.1818 | 1818.1818 |  | times | 1 |  |  |  |  | 77910 | 610.22
| 58xx | IT support | PMU |  |  |  |  | 454.5455 | 909.0909 |  | times | 2 |  |  |  |  | 0 | 0
| 58xx | Office and restroom renovation, Kathmandu Office | PMU |  |  |  |  | 4695 | 4695 |  | Times | 1 |  |  |  |  | 20000 | 156.65
[9 empty] | 21595 |  |  | 48 |  |  |  |  | 1031770 | 8081.22
|  | Personnel | [6 empty] | 358690.5
GRAND TOTAL (A+B) |  |  |  | YR 3 |  |  |  |  | 1355994.7545 | [7 empty] | 52615089.3 | 412102.1
|  |  | Carry-over total (unspent funds from previous year) | [10 empty] | % achieved for activities overall | 60.71% |  | Actual budget for previous project year
|  |  | Request of funds for Upcoming Project Year | [5 empty] | 1355994.7545
[19 empty] | GL CODE | LMBIS CODE | ACT# NO# | COMPONENT / OUTCOME / OUTPUT/ACTIVITIES | RESPONSIBLE | TIMELINE |  |  |  | UNIT DESCRIPTION | TARGET | UNIT COST | TOTAL BUDGET | Remarks | COMPONENT |  |  |  |  | TOTAL BUDGET | [6 empty] | BUDGET BIFUCATION |  |  | Outcomes
[24 empty] | Q1 | Q2 | Q3 | Q4 | [5 empty] | Com.1 | Com.2 | Com.3 | Com.4 | Mgmt. | Jan-Mar 2021 | Apr-Jun 2021 | Jul-Sep 2021 | Oct-Dec 2021 | Jan-Mar 2022 | Apr-Jun 2022 | TOTAL Budget | TECHNICAL ASSISTANCE | PROGRAM FUNDING | TOTAL
[22 empty] | A. PERSONNEL COSTS |  | 0 | 0 | 0 | 0 |  |  |  | 341694.2045 |  | 58379.8687 | 41832.346 | 133332.8761 | 62713.2273 | 45435.8864 | 56949.0341 | 56949.0341 | 56949.0341 | 56949.0341 | 56949.0341 | 56949.0341 | 341694.2045 | 341694.2045 | 0 | 341694.2045
[19 empty] | 50xx |  |  | Project Coordinator | PMU |  |  |  |  | Mo. | 15 | 2424.5455 | 36368.1818 |  | 18184.0909 | 3636.8182 | 7273.6364 | 1818.4091 | 5455.2273 | 6061.3636 | 6061.3636 | 6061.3636 | 6061.3636 | 6061.3636 | 6061.3636 | 36368.1818 | 36368.1818 | 0 | 36368.1818
[19 empty] | 50xx |  |  | Project Manager | PMU |  |  |  |  | Mo. | 15 | 2239.3636 | 33590.4545 |  | 6718.0909 | 6718.0909 | 11756.6591 | 3359.0455 | 5038.5682 | 5598.4091 | 5598.4091 | 5598.4091 | 5598.4091 | 5598.4091 | 5598.4091 | 33590.4545 | 33590.4545 | 0 | 33590.4545
[19 empty] | 50xx |  |  | Finance and Administration Manager | PMU |  |  |  |  | Mo. | 15 | 1860.4091 | 27906.1364 |  | 3488.267 | 3488.267 | 9767.1477 | 5581.2273 | 5581.2273 | 4651.0227 | 4651.0227 | 4651.0227 | 4651.0227 | 4651.0227 | 4651.0227 | 27906.1364 | 27906.1364 | 0 | 27906.1364
[19 empty] | 50xx |  |  | Field Manager | PMU |  |  |  |  | Mo. | 15 | 1403.1818 | 21047.7273 |  | 3157.1591 | 3157.1591 | 10523.8636 | 4209.5455 | 0 | 3507.9545 | 3507.9545 | 3507.9545 | 3507.9545 | 3507.9545 | 3507.9545 | 21047.7273 | 21047.7273 | 0 | 21047.7273
[19 empty] | 50xx |  |  | Field Program Officer | PMU |  |  |  |  | Mo. | 15 | 1343.0455 | 20145.6818 |  | 2014.5682 | 4029.1364 | 10072.8409 | 4029.1364 | 0 | 3357.6136 | 3357.6136 | 3357.6136 | 3357.6136 | 3357.6136 | 3357.6136 | 20145.6818 | 20145.6818 | 0 | 20145.6818
[19 empty] | 50xx |  |  | Field Finance/Compliance Officer | PMU |  |  |  |  | Mo. | 15 | 1343.0455 | 20145.6818 |  | 2518.2102 | 2518.2102 | 7050.9886 | 4029.1364 | 4029.1364 | 3357.6136 | 3357.6136 | 3357.6136 | 3357.6136 | 3357.6136 | 3357.6136 | 20145.6818 | 20145.6818 | 0 | 20145.6818
[19 empty] | 50xx |  |  | Field Monitoring, Evaluation and Learning (MEL) Officer | PMU |  |  |  |  | Mo. | 15 | 1363.0909 | 20446.3636 |  | 0 | 0 | 0 | 20446.3636 | 0 | 3407.7273 | 3407.7273 | 3407.7273 | 3407.7273 | 3407.7273 | 3407.7273 | 20446.3636 | 20446.3636 | 0 | 20446.3636
[19 empty] | 50xx |  |  | Field Finance and Administration Associate | PMU |  |  |  |  | Mo. | 15 | 1072.4318 | 16086.4773 |  | 2010.8097 | 2010.8097 | 5630.267 | 3217.2955 | 3217.2955 | 2681.0795 | 2681.0795 | 2681.0795 | 2681.0795 | 2681.0795 | 2681.0795 | 16086.4773 | 16086.4773 | 0 | 16086.4773
[19 empty] | 50xx |  |  | Field Program Assistant (4) | PMU |  |  |  |  | Mo. | 15 | 3046.9091 | 45703.6364 |  | 2285.1818 | 4570.3636 | 36562.9091 | 2285.1818 |  | 7617.2727 | 7617.2727 | 7617.2727 | 7617.2727 | 7617.2727 | 7617.2727 | 45703.6364 | 45703.6364 | 0 | 45703.6364
[19 empty] | 50xx |  |  | Front Desk Assistant _KTM | PMU |  |  |  |  | Mo. | 15 | 801.8182 | 12027.2727 |  | 962.1818 | 962.1818 | 2886.5455 | 1202.7273 | 6013.6364 | 2004.5455 | 2004.5455 | 2004.5455 | 2004.5455 | 2004.5455 | 2004.5455 | 12027.2727 | 12027.2727 | 0 | 12027.2727
[19 empty] | 50xx |  |  | Front Desk Assistant _Field | PMU |  |  |  |  | Mo. | 15 | 781.7727 | 11726.5909 |  | 938.1273 | 938.1273 | 2814.3818 | 1172.6591 | 5863.2955 | 1954.4318 | 1954.4318 | 1954.4318 | 1954.4318 | 1954.4318 | 1954.4318 | 11726.5909 | 11726.5909 | 0 | 11726.5909
[19 empty] | 50xx |  |  | Communication Officer (100% ) | PMU |  |  |  |  | Mo. | 15 | 1454.5455 | 21818.1818 |  | 3490.9091 | 3490.9091 | 10472.7273 | 4363.6364 | 0 | 3636.3636 | 3636.3636 | 3636.3636 | 3636.3636 | 3636.3636 | 3636.3636 | 21818.1818 | 21818.1818 | 0 | 21818.1818
[19 empty] | 50xx |  |  | Field Safeguard and GESI Officer | PMU |  |  |  |  | Mo. | 15 | 1545.4545 | 23181.8182 |  | 3477.2727 | 3477.2727 | 11590.9091 | 4636.3636 | 0 | 3863.6364 | 3863.6364 | 3863.6364 | 3863.6364 | 3863.6364 | 3863.6364 | 23181.8182 | 23181.8182 | 0 | 23181.8182
[19 empty] | 50xx |  |  | Office Messenger (2) | PMU |  |  |  |  | Mo. | 15 | 1050 | 15750 |  | 1260 | 1260 | 3780 | 1575 | 7875 | 2625 | 2625 | 2625 | 2625 | 2625 | 2625 | 15750 | 15750 | 0 | 15750
[19 empty] | 50xx |  |  | Driver (2) | PMU |  |  |  |  | Mo. | 15 | 1050 | 15750 |  | 7875 | 1575 | 3150 | 787.5 | 2362.5 | 2625 | 2625 | 2625 | 2625 | 2625 | 2625 | 15750 | 15750 | 0 | 15750
[22 empty] | B. ACTIVITY COST | [8 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on J19: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: input was wrong ealier it was 1000
Note on M25: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: this does not applicable in IP rating
Note on O33: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: this activity was not in approved AWP&B
Note on X170: Narayan K.C.: liNE Ministry Budget Informaiton System
Note on AH178: Author: 120,000/Fulltime

## AWPB Yr 4
Period: Year 4 (July 23 - June 24) (FY 80/81)
| ANNUAL WORK PLAN | [10 empty] | WORK PLAN TRACKING (Tracking at end of project year) | [5 empty] | Additonal Notes
COMPONENT / OUTCOME / OUTPUT | # | ACTIVITIES | Responsible | YEAR X TIMING |  |  |  | BUDGET in USD | x | UNIT DESCRIPTION | TARGET | # UNIT(S) ACHIEVED | % ACHIEVED BY ACTIVITY (# unit(s) achieved / target) | % ACHIEVED BY OUTCOME | % ACHIEVED BY COMPONENT | BUDGET (actual, by Component) |  |  |  |  | Safeguard issues |  |  |  | Measures | IPPF |  |  |  | GESI intigration
|  |  |  | Q1 | Q2 | Q3 | Q4 | TA | if activity is carried over from previous year | # of | [5 empty] | in Rupee | in USD | Act# | Activity |  | Policy on natural habitat | Policy on involuntary resettlement | Policy on indigenous people | Policy on pest management | Proposed mitigating activities | FPIC needed or not | IP organization direct collaboration possible or not | Livelihood restoration plan | Action to be taken during implementation | Trigger or not | Action points | Additional information
A. ACTIVITY COSTS | [7 empty] | 2446897 | [7 empty] | 0 | 0 | Technical Assistance - WWF GEF Part
COMPONENT 1: National capacity and enabling environment for cross-sectoral coordination to promote forest and landscape conservation | [7 empty] | 352393 | [7 empty] | 0 | 0 | COMPONENT 1: National capacity and enabling environment for cross-sectoral coordination |  |  | COMPONENT 1: National capacity and enabling environment for cross-sectoral coordination
Outcome 1.1: Improved inter-sectoral coordination from Federal, State to Local level for sustainable forest management and integrated landscape management |  |  |  | Q1 | Q2 | Q3 | Q4 | 53752 | [7 empty] | 0 | 0 | Outcome 1.1: Improved inter-sectoral coordination from Federal, State to Local level |  |  | Outcome 1.1: Improved inter-sectoral coordination from Federal, State to Local level
Output 1.1.1 : Cross-sectoral coordination mechanisms established to support integrated landscape management for conservation outcomes at different levels | 162 | 1.1.1.1: Provide support to NBCC committee (ensure gender inclusive team) | MOFE/DOFSC/DNPWC/MITFE/PMU |  |  |  |  | 2344 |  |  | 2 | 0 | 0% |  |  |  |  | 1.1.1.1 | Support includes meeting logistics and office equipment to MoFE, To make unit trackable - PMU will update the workplan during implementation whether it will be meeting logistic support or equipment |  | No | No | No | No | No | No | No | No | No | Yes | 1.Sensitize for inclusive participation during project communication (e.g. regular briefing on GESI perspective) 2. Ensure at least 33% female participants in the coordination mechanism (Representation of women, dalits, ethnic and indigenous peoples (where applicable) 3. Ensure coordination mechanism listens and value the idea, perception and needs of women, dalit, janjati, poor and marginalized people of the community (Do no harm and safeguard women, dalit, janjati and poor adn marginalized people) | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
|  | 1.1.1.2 Organize State level Biodiversity Co-ordination Committee (State 2,3,5,7 and Karnali) meetings | MOFE/DOFSC/DNPWC/MITFE |  |  |  |  | 0 | [9 empty] | 1.1.1.2
| 163 | 1.1.1.3 Provide technical and financial support to State Biodiversity Co-ordination committee | MOFE/DOFSC/DNPWC/MITFE/PMU |  |  |  |  | 19688 |  |  | 12 | 3 | 25% |  |  |  |  | 1.1.1.3 | States (MoEFSC - Sudurpaschim, Lumbini, Madesh , Bagmati, Karnali province) will receive institutional support after formation of province level BCC to enhance understanding and adoption of Integrated Landscape Management |  | No | No | No | No | No | No | No | No | No | Yes | 1.Sensitize for inclusive participation during project communication (e.g. regular briefing on GESI perspective) 2. Ensure at least 33% female participants in the coordination mechanism (Representation of women, dalits, ethnic and indigenous peoples (where applicable) 3. Ensure coordination mechanism listens and value the idea, perception and needs of women, dalit, janjati, poor and marginalized people of the community (Do no harm and safeguard women, dalit, janjati and poor adn marginalized people) | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
| 164 | 1.1.1.4 Organize inter-ministerial coordination mechanism for wildlife friendly infrastructure | MOFE/DOFSC/DNPWC/MITFE/PMU |  |  |  |  | 5469 |  | Meeting | 2 | 0 | 0% |  |  |  |  | 1.1.1.4 | Multistakeholder meeting organized focussing on widlife friendly infrastructure promotion |  | No | No | No | No | No | No | No | No | No | Yes | 1.Sensitize for inclusive participation during project communication (e.g. regular briefing on GESI perspective) 2. Ensure at least 33% female participants in the coordination mechanism (Representation of women, dalits, ethnic and indigenous peoples (where applicable) 3. Ensure coordination mechanism listens and value the idea, perception and needs of women, dalit, janjati, poor and marginalized people of the community (Do no harm and safeguard women, dalit, janjati and poor adn marginalized people) | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
| 165 | 1.1.1.5 Organize inter-state coordination (2, 3, Gandaki, 5, Karnali, 7) for implementation of the NBSAP and TAL Strategy | PMU/DNPWC/MITFE |  |  |  |  | 3594 |  | Meeting | 2 | 0 | 0% |  |  |  |  | 1.1.1.5 | Enhancing inter-state coordination on ILM works through organizing interaction on ILM based on NBSAP and TAL strategy, 1 event of meeting workshop will be organized at province level (Lumbini Province) |  | No | No | No | No | No | No | No | No | No | Yes | 1.Sensitize for inclusive participation during project communication (e.g. regular briefing on GESI perspective) 2. Ensure at least 33% female participants in the coordination mechanism (Representation of women, dalits, ethnic and indigenous peoples (where applicable) 3. Ensure coordination mechanism listens and value the idea, perception and needs of women, dalit, janjati, poor and marginalized people of the community (Do no harm and safeguard women, dalit, janjati and poor adn marginalized people) | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
| 166 | 1.1.1.6 Carry out cluster meetings with Municipalities | PMU/DNPWC/MITFE |  |  |  |  | 7813 |  | Meeting | 20 | 11 | 55% |  |  |  |  | 1.1.1.6 | At least 20 Local governments will be sensitized about importance of ILM and coordinate/faciliate in LG's planning process and will be oriented on TAL and NBSAP strategy |  | No | No | No | No | No | No | No | No | No | Yes | 1.Sensitize for inclusive participation during project communication (e.g. regular briefing on GESI perspective) 2. Ensure at least 33% female participants in the meetings (Representation of women, dalits, ethnic and indigenous peoples (where applicable) 3. Ensure coordination mechanism listens and value the idea, perception and needs of women, dalit, janjati, poor and marginalized people of the community (Do no harm and safeguard women, dalit, janjati and poor adn marginalized people) | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
|  | 1.1.1.7 Conduct final review of NBSAP (2014-2020) | PMU |  |  |  |  | 0 | [9 empty] | 1.1.1.7
| 167 | 1.1.1.8 Provide technical and financial support to WCCB | MOFE/DOFSC/DNPWC/MITFE |  |  |  |  | 5469 |  | District cell | 4 | 4 | 100% |  |  |  |  | 1.1.1.8 | WCCBs (district level) will be strengthend through institutional support |  | No | No | No | No | No | No | No | No | No | Yes | 1.Support women friendly tools 2. Advocacy for inclusive WCCB | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
| 168 | 1.1.1.9 Field program implementation support & coordination | PMU/BaNP/BNP |  |  |  |  | 9375 |  | Month | 12 | 12 | 100% |  |  |  |  | 1.1.1.9 | Package includes cost for project staff's travel cost (Transportation and DSA) to support grantee partners in activity implementation and coordination. Also includes monitoring cost to grantee partners |  | No | No | No | No | No | No | No | No | No | Yes | 1.Sensitize for inclusive participation during project communication (e.g. regular briefing on GESI perspective) 2. Ensure at least 33% female participants in the coordination mechanism (Representation of women, dalits, ethnic and indigenous peoples (where applicable) 3. Ensure coordination mechanism listens and value the idea, perception and needs of women, dalit, janjati, poor and marginalized people of the community (Do no harm and safeguard women, dalit, janjati and poor adn marginalized people) | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
[8 empty] | 53752 |  |  | 54 | 30 | 40% | 40% |  | 0 | 0
Outcome 1.2 Capacity increased for multi-stakeholder and cross-sector landscape and forest planning and management |  |  |  | Q1 | Q2 | Q3 | Q4 | 298641 | [7 empty] | 0 | 0 | Outcome 1.2 Capacity increased for multi-stakeholder and cross-sector landscape and forest planning and management |  |  | Outcome 1.2 Capacity increased for multi-stakeholder and cross-sector landscape and forest planning and management
Output 1.2.1. Conservation Leadership Training provided | 169 | 1.2.1.1: Conduct training to ILM coordinators for capturing international best practice and applying this to the local context | PMU/DNPWC/MITFE |  |  |  |  | 12000 |  | ILM coordinators trained | 12 | 0 | 0% |  |  |  |  | 1.2.1.1 | ILM coordinators working in biodiversity conservation in TAL will be capacited on ILM through international exposures. Capacitated officials are expected to engage to replicate pragmatic approaches and new knowledge in landscape management. |  | No | No | No | No | No | No | No | No | No | Yes | 1.Sensitize for inclusive participation during project communication (e.g. regular briefing on GESI perspective and synergies across all level) 2. Ensure 30% female participation (Representation of women, dalits, ethnic and indigenous peoples) with meaninfgul representation in the decision making process | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
[8 empty] | 12000 |  |  | 12 | 0 | 0% |  |  | 0 | 0
Output 1.2.2 Training courses provided on key subjects for integrated landscape management for responsible federal and state government staff | 170 | 1.2.2.1: Conduct training on Biodiversity conservation and monitoring | PMU |  |  |  |  | 7813 |  | Training | 1 | 0 | 0% |  |  |  |  | 1.2.2.1 | At least 20 government staffs (state and federal staffs) will be given training with 2 training package |  | No | No | No | No | No | No | Yes | No | Yes. ensure meaningful participation of IPs group, women's group and dalit groups in the consultation process with quality representation in decision making process | Yes | 1.Sensitize for inclusive participation during project communication (e.g. regular briefing on GESI perspective and synergies across all level) 2. Ensure 50% female participation (Representation of women, dalits, ethnic and indigenous peoples) with meaninfgul representation in the decision making process 1. The training manual must include GESI component related to conservation, cover GESI sensitive curriculum/topics, positive change in social norms approach in conservation 2. Use participatory training methods 3. Develop pre-test, post-test questionnaire as an integral part of manual | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
| 171 | 1.1.2.2: Conduct training on Disaster Risk Management | PMU |  |  |  |  | 11719 |  | Training | 1 | 0 | 0% |  |  |  |  | 1.2.2.2 | At least 30 government staffs (state and federal staffs) will be given training with 3 training package |  | No | No | No | No | No | No | Yes | No | Yes. ensure meaningful participation of IPs group, women's group and dalit groups in the consultation process with quality representation in decision making process | Yes | 1.Sensitize for inclusive participation during project communication (e.g. regular briefing on GESI perspective and synergies across all level) 2. Ensure 50% female participation (Representation of women, dalits, ethnic and indigenous peoples) with meaninfgul representation in the decision making process 1. The training manual must include GESI component related to conservation, cover GESI sensitive curriculum/topics, positive change in social norms approach in conservation 2. Use participatory training methods 3. Develop pre-test, post-test questionnaire as an integral part of manual | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
| 172 | 1.1.2.3: Orientation on roles and responsibilities for new park staff (senior/game scouts) | BaNP/BNP |  |  |  |  | 2109 |  | Orientation | 2 | 2 | 100% |  |  |  |  | 1.2.2.3 | Training to national park staff on roles and responsibilites. trainee will be identified with inclusive representation |  | No | No | No | No | No | No | No | No | No | Yes | Capacity building on GESI concepts and mainstreaming methodologies | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
| 173 | 1.1.2.4: Orientation on roles and responsibilities for new divisional staff | DFO-B/DFO-P |  |  |  |  | 2109 |  | Orientation | 2 | 2 | 100% |  |  |  |  | 1.2.2.4 | Training package - In coordination with Division Forest officials, trainee will be identified with inclusive representation |  | No | No | No | No | No | No | No | No | No | Yes | Capacity building on GESI concepts and mainstreaming methodologies | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
[8 empty] | 15937 |  |  | 6 | 4 | 50% |  |  | 0 | 0
Output 1.2.3 Small grants for innovation in ILM (conservation, natural resource, and landscape management) in TAL corridors and PA buffer zones | 174 | 1.2.3.1:Provide Individual grant (Bachelors and Master's thesis) | PMU |  |  |  |  | 12891 |  | Grants | 22 | 19 | 86.36% |  |  |  |  | 1.2.3.1 | Capacity Enhancement of research skills and capacity of university students on ILM and enhance broadening of knowledge through possible journal papers, newspaper articles, blogs and thesis reports |  | No | No | No | No | Include Safeguards and GESI research theme | No | Yes; consultation and meaningful participation of IPs should be ensured when applicable | No | Yes. ensure meaningful participation of IPs group, women's group and dalit groups in the consultation process with quality representation in decision making process | Yes | 1. GESI-sensitive selection criteria are used for the selection of Bachelor’s and Master’s degree students 2. Follow participatory method in community consultation processes 3. Ensure 50% female participants (Representation of women, dalits, ethnic and indigenous peoples) with meaningful participation in the decision making processes | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
| 175 | 1.1.3.2: Provide Institutional grant to Academic Institutional and CBOs/CSOs | PMU |  |  |  |  | 58594 |  | Grants | 5 | 1 | 20% |  |  |  |  | 1.2.3.2 | Includes study, action research or scientific research and on the ground interventions as well. However priority will be given to academic institutions in research and extension work related to NRM and biodiversity Conservation in TAL corridors and PA buffer zones that will help address threats and barriers in achieveing overall project objective |  | No | No | No | No | No | No | Yes | No | Yes. ensure meaningful participation of IPs group, women's group and dalit groups in the consultation process with quality representation in decision making process | Yes | 1. GESI-sensitive selection criteria are used for identifying local CBOs/CSOs to provide grants (i.e. ensuring an equal percentage of women-led CBOs/CSOs have access to grants, as much as possible) 2. Ensure 50% female participation (Representation of women, dalits, ethnic and indigenous peoples) with meaningful representation in the decision making processes during capacity enhacement trainings and participations | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
| 176 | 1.1.3.3: Provide innovation grant to the government agencies (National Park, Forest Division, Research and Training Centre) at state level | PMU/DNPWC/MoEFSC |  |  |  |  | 199219 |  | Grants | 3 | 3 | 100% |  |  |  |  | 1.2.3.3 | Include infrastructure, equipments and research (HWC management, species management), study, capacity development training to government officials and scientific research. Priority in TAL area |  | No | No | No | No | No | No | Yes | No | Yes. ensure meaningful participation of IPs group, women's group and dalit groups in the consultation process with quality representation in decision making process | Yes | 1. Ensure at least 33% female participation (Representation of women, dalits, ethnic and indigenous peoples) with meaningful representation in the decision making process in selection of participants (awardees) and conduction of consultation meetings with community | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
[8 empty] | 270704 |  |  | 30 | 23 | 68.79% | 50.8% | 45.76% | 0 | 0
Component 2: Integrated Planning for Protected Area Buffer Zones and Critical Corridors in the Terai Arc Landscape | [7 empty] | 139266 | [7 empty] | 0 | 0 | Component 2: Integrated Planning for Protected Area Buffer Zones and Critical Corridors in the Terai Arc Landscape |  |  | Component 2: Integrated Planning for Protected Area Buffer Zones and Critical Corridors in the Terai Arc Landscape
Outcome 2.1: Improved corridor planning for TAL corridors (Brahmadev, Karnali and Kamdi) |  |  |  | Q1 | Q2 | Q3 | Q4 | 6938 | [7 empty] | 0 | 0 | Outcome 2.1: Improved corridor planning for TAL corridors (Brahmadev, Karnali and Kamdi) |  |  | Outcome 2.1: Improved corridor planning for TAL corridors (Brahmadev, Karnali and Kamdi)
Output 2.1.1 Biodiversity surveys, socio-economic surveys, and local stakeholder consultation for Brahmadev , Karnali, and Kamdi corridors to determine feasibility of appropriate models for community-based natural resource management |  | 2.1.1.1: Conduct assessment to update biodiversity inventory and socio-economic status in corridors (incorporating GESI aspect, indigenous people and access restriction information) | PMU | [14 empty] | 2.1.1.1
| 177 | 2.1.1.2: Provide technical support to review existing forest encroachment status and response options considering GESI aspect and any necessary safeguards management plans (e.g. IPP or LRP)” | BaNP/BNP/ DFO-B/ DFO-P |  |  |  |  | 6938 |  | Assessment | 6 | 5 | 83.33% |  |  |  |  | 2.1.1.2 | Preparation of existing forest encorachment status in BaNPBZ, BNP BZ, Kamdi corridor, Karnali corriodr, Brahmadev Corridor and Dang District report considering GESI aspect and necessary safeguard management aspects |  | Yes | Yes | Yes | No | 1. Ensure Natural Habitat degradation ascpect, IPs socio-economic and access restriction status in the survey design | Yes | Yes | Yes; prepare on the basis of screnning | 1. Consultations with IPs, Womens' Group and Dalits | Yes | 1.Sensitize for inclusive participation during project communication (e.g. regular briefing on GESI perspective) 2. Ensure 50% female participation (Representation of women, dalits, ethnic and indigenous peoples) | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
|  | 2.1.1.3: Prepare corridor/bottleneck assessment report with GESI and safeguards integration | PMU | [14 empty] | 2.1.1.3
[8 empty] | 6938 |  |  | 6 | 5 | 83.33% | 83.33% |  | 0 | 0
Outcome 2.2: Improved participatory planning for sustainable management of in Banke-Bardia complex |  |  |  | Q1 | Q2 | Q3 | Q4 | 68672 | [7 empty] | 0 | 0 | Outcome 2.2: Improved participatory planning for sustainable management of in Banke-Bardia complex |  |  | Outcome 2.2: Improved participatory planning for sustainable management of in Banke-Bardia complex
Output 2.2.1: Land uses, biodiversity values, forest carbon, and key threats assessed, mapped, reported and disseminated to identify priority villages and forest areas in the targeted PA buffer zones and corridors | 178 | 2.2.1.1: Conduct participatory assessments in targeted PA buffer zones and corridors to identify priority community and forest areas | PMU |  |  |  |  | 3828 |  | Assessment | 1 | 1 | 100% |  |  |  |  | 2.2.1.1 | Update assessment report (Prepared on FY 2021) based on year 1 and year 2 implementation status and learning |  | Yes; incorporate the habitat degradation status and patch areas in the assessment | Yes; analyze any access restriction issues | Yes; ensure meaningful participation IPs | No | 1.Ensure habitat degradatio, patch areas identification, access restriction issues 2. Ensure meaningful participation of IPS, women's group and dalit groups | Yes | Yes | Yes; Report any as such requred during the consultative process | Ensure meaningful participation of IPS | Yes | 1.Sensitize for inclusive participation during project communication (e.g. regular briefing on GESI perspective) 2. Ensure at least 50% female participants (Representation of women, dalits, ethnic and indigenous peoples) | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
| 179 | 2.2.1.2: Conduct resource mapping of CFUGs at corridor level and BZUCs | PMU/DNPWC/MITFE |  |  |  |  | 7500 |  | Assessment | 4 | 0 | 0% |  |  |  |  | 2.2.1.2 | Resource mapping with expert supports BaNP BZ, BNP BZ, Kamdi and Karnali corridor |  | Yes | Yes | Yes | No | 1. Ensure issues of IPs, Dalits and Women's group | Yes | Yes | Yes; prepare on the basis of screnning | 1. Consultations with IPs, Womens' Group and Dalits | Yes | 1.Sensitize for inclusive participation during project communication (e.g. regular briefing on GESI perspective) 2. Ensure 50% female participation (Representation of women, dalits, ethnic and indigenous peoples) | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
| 180 | 2.2.1.3: Carry out consultations at identified communities | MOFE/DOFSC/DNPWC/MITFE |  |  |  |  | 14063 |  | Assessment | 60 | 67 | 100% |  |  |  |  | 2.2.1.3 | At least 60 events of consultation meetings and co-ordinaton meetings will be conducted with the identified communities. Based on the forest and community Participatory Assessment Report (updated) to facilitate implementation of project activities including safeguard orientation |  | Yes; discuss on habitat degradation issues | Yes; analyze any access restriction issues and mitigation strategies | Yes; participate IPs in consultation process | No | Yes; on the basis of consultation | Yes | Yes | No | Ensure meaningful participatoin of IPs/ in consultation process and in decision making processs | Yes | 1.Sensitize for inclusive participation during project communication (e.g. regular briefing on GESI perspective) 2. Ensure 50% female participants (Representation of women, dalits, ethnic and indigenous peoples) with meaningful participation in decision making process | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
[8 empty] | 25391 |  |  | 65 | 68 | 66.67% |  |  | 0 | 0
Output 2.2.2: Sustainable Forest Management Operational Plans developed or revised for priority forest areas, incorporating the assessment from 2.2.1 | 181 | 2.2.2.1: Provide financial support to develop State forest sector strategies (including Community Forests, Protected Forests and Leash-hold Forest) | MOFE/DOFSC/DNPWC/MITFE |  |  |  |  | 25781 |  | Stradegy study | 3 | 0 | 0% |  |  |  |  | 2.2.1.1 | Province level forest sector strategy will be prepared keeping integrated landscape approach in consideration (PMU-Madesh, Karnali and Bagmati) |  | Yes; discuss on habitat degradation issues | Yes; analyze any access restriction issues | Yes; participate IPs in consultation process | No | Yes; as per the report | No | Yes | No | No | Yes | 1.Sensitize for inclusive participation during project communication (e.g. regular briefing on GESI perspective) 2. Ensure 50% female participants (Representation of women, dalits, ethnic and indigenous peoples) with meaningful participation in decision making process | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
| 182 | 2.2.2.2: Support CFUGs and BZ CFUGs to develop/revise forest operational plan (GESI aspect is revised/incorporated) | PMU/DNPWC/MITFE |  |  |  |  | 17500 |  | CFUGs meetings | 70 | 25 | 35.71% |  |  |  |  | 2.2.1.2 | Incorporation of GESI aspects in operational plans will be prioritized. |  | Yes; review the natural habitat degradation | Yes; review any access restriction issues in the plan | 1. Yes; ensure meaningful participation of IPs in revision process | No | Explore true collaboration and agreement | Yes | Yes; ensure meaningful participation of Ips | No | Ensure meaningful participatoin of IPs/ in consultation process and in decision making processs with true collaboration adn agreement | Yes | 1.Sensitize for inclusive participation during project communication (e.g. regular briefing on GESI perspective) 2. Ensure 50% female participation (Representation of women, dalits, ethnic and indigenous peoples) with meaningful participation in decision making process | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
[8 empty] | 43281 |  |  | 73 | 25 | 17.86% |  |  | 0 | 0
Output 2.2.3: Strategic framework for corridor management developed and management plans prepared or revised for all seven TAL corridors / protected forests | 178 | 2.2.3.1: Develop a gender and inclusion responsive guideline (GIRD) to prepare management plans of PF/Corridors | PMU |  |  |  |  | 7500 |  | Guidelines | 1 | 0 | 0% |  |  |  |  | 2.2.3.1 | Guideline to be prepared with expert support of Kamdi Corridor |  | Yes; discuss on habitat degradation issues | Yes; analyze any access restriction issues | Yes; participate IPs in consultation process | No | Yes; as per the report | No | Yes | No | No | Yes | 1.Sensitize for inclusive participation during project communication (e.g. regular briefing on GESI perspective) 2. Ensure 50% female participants (Representation of women, dalits, ethnic and indigenous peoples) with meaningful participation in decision making process | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
| 179 | 2.2.3.2: Support to revise PF / Corridor Management Plans through a participatory process | PMU/DNPWC/MITFE |  |  |  |  | 48000 |  | Plans | 4 | 1 | 25% |  |  |  |  | 2.2.3.2 | Prepare corridor management plan with experts' support (Kamdi, Karnali, Brahmhadev, Barandabhar Corridor) |  | Yes; discuss on habitat degradation issues | Yes; analyze any access restriction issues | Yes; participate IPs in consultation process | No | Yes; as per the report | No | Yes | No | No | Yes | 1.Sensitize for inclusive participation during project communication (e.g. regular briefing on GESI perspective) 2. Ensure 50% female participants (Representation of women, dalits, ethnic and indigenous peoples) with meaningful participation in decision making process | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
| 180 | 2.2.3.3: Field program implementation support & coordination | MOFE/DOFSC/DNPWC/MITFE |  |  |  |  | 8156 |  | Months | 12 | 12 | 100% |  |  |  |  | 2.2.3.3 | Package includes cost for project staff's travel and DSA to support grantee partners in activity implementation and coordination. Along with monitoring cost to grantee partners |  | No | No | No | No | No | No | No | No | No | Yes | 1.Sensitize for inclusive participation during project communication (e.g. regular briefing on GESI perspective) 2. Ensure 50% female participation (Representation of women, dalits, ethnic and indigenous peoples) with meaningful participation in decision making process | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
[8 empty] | 63656 |  |  | 17 | 13 | 41.67% | 45.09% | 49.34% | 0 | 0
COMPONENT 3: Forest and human-wildlife conflict management for improved conservation of targeted protected area buffer zones and corridors in the Terai Arc Landscape | [7 empty] | 1701837 | [7 empty] | 0 | 0 | COMPONENT 3: Forest and HWC management for improved conservation of targeted PA buffer zones and corridors in the TAL |  |  | COMPONENT 3: Forest and human-wildlife conflict management for improved conservation of targeted protected area buffer zones and corridors in the Terai Arc Landscape
Outcome 3.1: Strengthen livelihoods and biodiversity conservation through Sustainable forest management practices |  |  |  | Q1 | Q2 | Q3 | Q4 | 1334759.25 | [7 empty] | 0 | 0 | Outcome 3.1: Strengthen livelihoods and biodiversity conservation through Sustainable forest management practices |  |  | Outcome 3.1: Strengthen livelihoods and biodiversity conservation through Sustainable forest management practices
Output 3.1.1: Training and tools to local government on SFM | 181 | 3.1.1.1: Prepare Sustainable Forest Management Training (SFM) Manual incorporating GESI | MOFE/DOFSC/DNPWC/MITFE |  |  |  |  | 5000 |  | Manaul | 1 | 0 | 0% |  |  |  |  | 3.1.1.1 | Prepare SFM training manual with experts support |  | Yes; discuss on habitat degradation issues | Yes; analyze any access restriction issues | Yes; participate IPs in consultation process | No | Yes; as per the report | No | Yes | No | No | Yes | 1.Sensitize for inclusive participation during project communication (e.g. regular briefing on GESI perspective) 2. Ensure 50% female participants (Representation of women, dalits, ethnic and indigenous peoples) with meaningful participation in decision making process | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
| 182 | 3.1.1.2: Provide "Training of Trainers" (TOT) to Division Forest Offices staff based on SFM Training Manual | PMU/DNPWC/MITFE |  |  |  |  | 11250 |  | No of training | 2 | 0 | 0% |  |  |  |  | 3.1.1.2 | Training cost- Lumbini province |  | No | No | No | No | No | No | No | No | No | Yes | a. Ensure GESI component related with the conservation in the manual b. Ensure participatory training methods in the manual 3. Ensure GESI pre-test, post-test questionnaire as a part of manual | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
| 183 | 3.1.1.3 Establish Forest Management Information system (FMIS) including forest fire management | MOFE/DOFSC/DNPWC/MITFE |  |  |  |  | 7813 |  | Support Package | 1 | 0 | 0% |  |  |  |  | 3.1.1.3 | Sudurpaschim province ministry will develop system
|  | 3.1.1.4: Support the State Forest Directorate fire reporting system | MOFE/DOFSC/DNPWC/MITFE | [14 empty] | 3.1.1.4
| 184 | 3.1.1.5: Support forest fire management through innovative tools and techniques such as leaf litter collection and composting (within targeted sites identified in component 2) | MOFE/DOFSC/DNPWC/MITFE |  |  |  |  | 16250 |  | support | 8 | 7 | 87.5% |  |  |  |  | 3.1.1.5 | Sites or CFUGs identified as most vulnerable to forest fire in project sites will be supported with forest fire management tools |  | Yes | No | Yes | No | Explore any collaboration and agreement with Ips for effective tools | Yes | Yes; ensure meaningful participation of IPs | Yes | 1. Ensure meaningful participation of women's, dalit and IPs groups | Yes | 1. Ensure 50% female beneficiaries receiving tools | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
| 185 | 3.1.1.6 Provide multi-year support for nursery to Division forest offices (within targeted sites identified in component 2) | MOFE/DOFSC/DNPWC/MITFE |  |  |  |  | 82031.25 |  | nursery | 3 | 4 | 100% |  |  |  |  | 3.1.1.6 | DFOs will establish a nursery including infrastructures and produce multi-year seedlings to make available to local communities in forest restoration sites, private and agro-forestry promotion sites |  | Yes; ensure selection of quality species suitable for wildlife and biodiversity | No | Yes | Yes | Ensure invasive species are not promoted, and IPs are consulted | Yes | Yes | No | 1. Ensure meaningful participation of women's, dalit and IPs groups | Yes | Ensure 60% female, 20% IPs and 5% dalits as beneficiaries | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
[8 empty] | 122344.25 |  |  | 15 | 11 | 37.5% |  |  | 0 | 0
Output 3.1.2: Technical support to CFUGs, BZCFUGs and land holders for forest management | 186 | 3.1.2.1: Provide training to CFUGs and BZ CFUGs for forest management implementation (including applied SFM, restoration technique - lined with 3.1.1 | PMU/DNPWC/MITFE |  |  |  |  | 12500 |  | training | 8 | 6 | 75% |  |  |  |  | 3.1.2.1 | Training to CFUGs on sustainable forest management and restoration, ensuring equitable access to all members and gender dimensions in training opportunities |  | No | No | No | No | No | No | No | No | 1. Ensure meaningful participation of women's, dalit and IPs groups | Yes | 1.Sensitize for inclusive participation during project communication (e.g. regular briefing on GESI perspective) 2. Ensure 50% female participation (Representation of women, dalits, ethnic and indigenous peoples) | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
| 187 | 3.1.2.2: Conduct exchange visits for targeted BZ CFUG members (learning from successful UCs on fund mobilization and HWC management) | PMU |  |  |  |  | 7500 |  | visits | 2 | 2 | 100% |  |  |  |  | 3.1.2.2 | Exchange visit to TAL Nepal and TAL India for BZUCs/BZCFUG members on HWC management including BZ focal points in National Park offices, ensuring equitable access to all members and gender dimensions in training opportunities |  | No | No | No | No | No | No | Yes; participate NEFIN/FECOFUN in the exchangie visits | No | No | Yes | 1.Sensitize for inclusive participation during project communication (e.g. regular briefing on GESI perspective) 2. Ensure 50% female participation (Representation of women, dalits, ethnic and indigenous peoples) | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
| 188 | 3.1.2.3: Support BZUCs annual meetings for Bardia and Banke NP Buffer Zones (northern side) | PMU/DNPWC/MITFE |  |  |  |  | 1000 |  | BZUCs annual meetings supported | 2 | 2 | 100% |  |  |  |  | 3.1.2.3 | Logistics support for annual meetings of BZUCs |  | No | No | No | No | No | No | No | No | No | Yes | 1.Sensitize for inclusive participation during project communication (e.g. regular briefing on GESI perspective) 2. Ensure 50% female participation (Representation of women, dalits, ethnic and indigenous peoples) | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
| 186 | 3.1.2.4: Provide coaching on "Governance and Financial management" for CFUGs of corridors and PA Buffer zones | PMU/DNPWC/MITFE |  |  |  |  | 4688 |  | coaching sessions | 30 | 19 | 63.33% |  |  |  |  | 3.1.2.4 | Training costs for CFUGs and BZUCs, ensuring equitable access to all members and gender dimensions in training opportunities |  | No | No | No | No | No | No | No | No | No | Yes | 1.Sensitize for inclusive participation during project communication (e.g. regular briefing on GESI perspective) 2. Ensure 50% female participation (Representation of women, dalits, ethnic and indigenous peoples) | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
| 187 | 3.1.2.5: Provide support private forest development (providing seedling, irrigation, fencing) | MOFE/DOFSC/DNPWC/MITFE |  |  |  |  | 132813 |  | Ha | 85 | 0 | 0% |  |  |  |  | 3.1.2.5 | Multi-year seedlings and necessary tools/equipment (solar pumps/hand pumps/barbed wires) supports will be provided to individuals/group for private forest development. Number of beneficiaires (grantees will be identified after community consultations) |  | Yes | No | Yes | Yes | 1. Promote indigenous species plantation 2. Discourage use of pesticides | Yes | Include in half yearly and yearly monitoring trip | No | No | Yes | 1.Sensitize for inclusive participation during project communication (e.g. regular briefing on GESI perspective) 2. Ensure 50% female participation (Representation of women, dalits, ethnic and indigenous peoples) | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
| 188 | 3.1.2.6: Support to register private forest | PMU/DNPWC/MITFE |  |  |  |  | 3125 |  | No of forest | 10 | 0 | 0% |  |  |  |  | 3.1.2.6 | Administration cost support to private forest owners in registration process |  | No | No | Yes | Yes | 1. Promote indigenous species plantation 2. Discourage use of pesticides | No | No | No | No | Yes | Prioritize 50% women's for their ownership in registration | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
[8 empty] | 161626 |  |  | 137 | 29 | 56.39% |  |  | 0 | 0
Output 3.1.3: Forests and associated habitat in priority buffer zones and corridors managed sustainably | 189 | 3.1.3.1: Create revolving fund to implement forest operational plans in project targeted corridors | PMU/DNPWC/MITFE |  |  |  |  | 93750 |  | Support Package | 4 | 0 | 0% |  |  |  |  | 3.1.3.1 | Creation of revolving fund to implement forest operational plans in project targeted corridors and Buffer zones |  | Yes | Yes | Yes | Yes | 1. Promote indigenous species plantation 2. Discourage use of pesticides | Yes; consultation and consent of community people should be ensured | Yes; involve IPsin the consultation meetings | No | Ensure meaningful participation of IPs, Women and dalits | yes | 1.Sensitize for inclusive participation during project communication (e.g. regular briefing on GESI perspective) 2. Ensure 50% female participation (Representation of women, dalits, ethnic and indigenous peoples) | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
| 190 | 3.1.3.2: Provide financial and technical support to improve livestock management (AI, fodder plant support, feeding trough, vet support, stall improvement) | PMU/DNPWC/MITFE |  |  |  |  | 165632 |  | Households | 800 | 806 | 100% |  |  |  |  | 3.1.3.2 | To reduce pressure on wildlife habitat, alternative packages including cement trough, fodder seedlings will be supported to households who are more dependent on forest resources in nearby corridor forest/ buffer zone forest |  | Yes | No | Yes | Yes | Ensure proper consultation and meaningful participation of Ips | Yes | Yes | Yes | 1. Prepare LRP first and then support | Yes | 1. Ensure 60% female, 20% Ips, and 10% dalit beneficiaries for livestock management support | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
| 191 | 3.1.3.3: Provide financial and technical support for management of grassland and wetland in project targeted area | PMU/DNPWC/MITFE |  |  |  |  | 287500 |  | Support Package | 26 | 26 | 100% |  |  |  |  | 3.1.3.3 | Package includes Habitat improvement in BaNP and its buffer zone, BNP and its buffer zone, Kamdi corridors and Karnali corridors (330 Ha. grassland and 26 wetlands) including technical backstopping and monitoring cost to grantee partners. Park offices will prioritize implementation sites in core area of national park and buffer zone |  | Yes | Yes | Yes | No | Conduct screening, categorization | Yes | Yes | Yes | 1. Ensure meaningful participation of IPs, Dalit and women's group 2. Develop LRP | Yes | 1. Ensure 60% female, 20% Ips, and 10% dalit beneficiaries for livestock management support | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
| 192 | 3.1.3.4: Provide financial and technical support for river bank protection in project targeted area | PMU/DNPWC/MITFE |  |  |  |  | 164063 |  | Support Package | 6 | 6 | 100% |  |  |  |  | 3.1.3.4 | Pacckage includes river training works, biological measures to be appliced to control river cutting, construction materials purchase and transporation. Area (forest and agriculture land to be protected/restored after river bank protection to be calculated during details sites identification and implementation plan preparation. |  | Yes | Yes | Yes | No | 1. Ensure wildlife friendly structure | Yes | Yes | Yes | 1. Consent from IPs | Yes | 1.Sensitize for inclusive participation during project communication (e.g. regular briefing on GESI perspective) 2. Ensure 50% female participation (Representation of women, dalits, ethnic and indigenous peoples) | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
| 193 | 3.1.3.5: Safeguard plan implementation | PMU |  |  |  |  | 23438 |  | plan/s | 4 | 4 | 100% |  |  |  |  | 3.1.3.5 | Package includes the support to needy households and communities to safeguard IP&LC rights to natural resources, and local community needs. The activities will be prepared after the community consultation planned in 2.2.1.3. The livelihood restoration plan and IPPF will be key guiding documents to unfold packages. An exposure visit of project stakeholders focusing on social and environmental safeguards and grievance mechanisms will be organized. Capacity development of local people and project stakeholders on grievance mechanism (brochure/ FAQ, training/workshop, display boards) |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Ensure Environmental and Social Safeugards along with GESI polices are adhered as per the document | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
| 194 | 3.1.3.6: Provide financial and technical support to small scale green enterprises in project targeted area | PMU/DNPWC/MITFE |  |  |  |  | 312500 |  | enterprise | 8 | 3 | 37.5% |  |  |  |  | 3.1.3.6 | Package includes support for small infrastructures and capacity development, ensuring gender balance in green enterprise promotion and equitable access to women-led enterprises |  | Yes | No | Yes | Yes | 1. Promote indigenous species | Yes | Yes | No | Preference to highly marginalized community | Yes | 1.Sensitize for inclusive participation during project communication (e.g. regular briefing on GESI perspective) 2. Ensure 50% female participation (Representation of women, dalits, ethnic and indigenous peoples) | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
| 195 | 3.1.3.7: Provide financial and technical support to develop business plan | PMU |  |  |  |  | 3906 |  | plan/s | 5 | 0 | 0% |  |  |  |  | 3.1.3.7 | Technical support with expert members on green enterprises business plan preparation, ensuring gender balance and equitable access to women-led enterprises in training in business planning |  | No | No | Yes | No | Ensure meaningful participation of Ips, dalit and womens group | Yes | Yes | Yes | 1. Involve IPs in business plan preparation | Yes | Ensure at least 60% female, 25% Ips and 10% dalit beneficiaries for project related loans for community level enterprise and livelihood support | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
[8 empty] | 1050789 |  |  | 853 | 845 | 62.5% | 53.52% |  | 0 | 0
Outcome 3.2: Improved management of the human-wildlife conflict |  |  |  | Q1 | Q2 | Q3 | Q4 | 233203 | [7 empty] | 0 | 0 | Outcome 3.2: Improved management of the human-wildlife conflict |  |  | Outcome 3.2: Improved management of the human-wildlife conflict
Output 3.2.1: Pilot method to reduce the wildlife accident in priority sites |  | 3.2.1.1: Conduct study on the wildlife traffic accident issue | PMU |  |  |  |  | 0 | [9 empty] | 3.2.1.1
| 196 | 3.2.1.2: Install tools/facilities to pilot measures to reduce accidents | MOFE/DOFSC/DNPWC/MITFE |  |  |  |  | 27500 |  | Support Package | 1 | 1 | 100% |  |  |  |  | 3.2.1.2 | Package includes technology installment that are effective in Bardia National Park and its buffer zone area |  | No | No | No | No | No | No | Yes | No | 1. Consult with IPs/beneficiaries for possible solutions to reduce the accidents | Yes | Ensure gender friendly tools are installed | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
| 197 | 3.2.1.3: Support in operation and monitoring of wildlife related traffic accidents in highway | MOFE/DOFSC/DNPWC/MITFE |  |  |  |  | 5156 |  | monitoring | 2 | 2 | 100% |  |  |  |  | 3.2.1.3 | Package includes technology, capacity development and monitoring cost |  | No | No | No | No | No | No | No | No | No | Yes | Research on gender perspective accidents in the highway | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
| 198 | 3.2.1.4: Support to erect fence in both side of Sikta irrigation canal | MOFE/DOFSC/DNPWC/MITFE |  |  |  |  | 15422 |  | Support Package | 1 | 1 | 100% |  |  |  |  | 3.2.1.4 | Construction of fence in both side of Sikta irrigation canal |  | Yes | Yes | Yes | No | 1. Support highly marginalized community with livelihood restoration support | Yes | Yes | Yes | 1. Meeting with CFUG/BZUC for FPIC and suitable measures | Yes | 1.Sensitize for inclusive participation during project communication (e.g. regular briefing on GESI perspective) 2. Ensure 50% female participation (Representation of women, dalits, ethnic and indigenous peoples) | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
[8 empty] | 48078 |  |  | 4 | 4 | 100% |  |  | 0 | 0
Output 3.2.2: Training and facilities for human wildlife conflict response | 199 | 3.2.2.1: Prepare species-specific guidelines for HWC management | MOFE/DOFSC/DNPWC/MITFE/PMU |  |  |  |  | 3906 |  | guideline | 1 | 1 | 100% |  |  |  |  | 3.2.2.1 | Focus will be tiger as number of tiger-human incidents increased in project site |  | Yes | No | Yes | No | 1. The guidelines should involve natural habitat, IPs and access restriction issue | Yes | Yes | Yes | Ensure meaningful participation of Ips | Yes | Ensure 50% female participation along with Ips and dalits in the consultation meetings | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
| 200 | 3.2.2.2: Pictorial manual on Wildlife identification and behavior in Nepali and local dialects | MOFE/DOFSC/DNPWC/MITFE/PMU |  |  |  |  | 3906 |  | manual | 1 | 1 | 100% |  |  |  |  | 3.2.2.2 | Manual preparation and printing |  | No | No | No | No | No | No | No | No | No | Yes | Ensure gender friendly dialect | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
| 201 | 3.2.2.3: Conduct training on identification and behavior of wild animals to Divisional forest office staff | MOFE/DOFSC/DNPWC/MITFE/PMU |  |  |  |  | 7813 |  | training | 4 | 2 | 50% |  |  |  |  | 3.2.2.3 | Training package development with curriculam and conduct training to division forest staff |  | No | No | No | No | No | No | No | No | No | Yes | 1.Sensitize for inclusive participation during project communication (e.g. regular briefing on GESI perspective) 2. Ensure at least 30% female participation (Representation of women, dalits, ethnic and indigenous peoples) | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
| 202 | 3.2.2.4: Support Wildlife Rescue center | MOFE/DOFSC/DNPWC/MITFE |  |  |  |  | 10906 |  | Centre | 1 | 1 | 100% |  |  |  |  | 3.2.2.4 | Strengthening of wildlife rescue center in BNP with equipments and facilities |  | No | No | Yes | No | Ensure awareness among nearby communities | Yes | Yes | Yes; on the basis of FPIC | Prepare plan on the basis of consultation with IPs, Dalits and women's group | Yes | 1.Sensitize for inclusive participation during project communication (e.g. regular briefing on GESI perspective) 2. Ensure at least 33% female participation (Representation of women, dalits, ethnic and indigenous peoples) | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
| 203 | 3.2.2.5: Support wildlife rescue and handling equipment and training | MOFE/DOFSC/DNPWC/MITFE |  |  |  |  | 6250 |  | training | 4 | 4 | 100% |  |  |  |  | 3.2.2.5 | Activities includes rescue of wildlife, equipments/tools purchase to handle wildlife and training conduction (if needed) |  | No | No | No | No | No | No | No | No | No | Yes | 1. Ensure 50% female participants in the training 2. Manual should include GESI mainstreaming methodologies | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
[8 empty] | 32781 |  |  | 11 | 9 | 90% |  |  | 0 | 0
Output 3.2.3: Community based HWC mitigate and preventive action implemented | 196 | 3.2.3.1: Conduct workshop on preventive and curative measures for HWC | MOFE/DOFSC/DNPWC/MITFE |  |  |  |  | 7813 |  | workshop | 2 | 1 | 50% |  |  |  |  | 3.2.3.1 | Workshop with relevent stakeholders on preventive and curative measures taking account the knowledge, needs and special considerations of vulnersable groups (including woman) in developing and promoting measures |  | No | No | No | No | No | No | Yes; participate IPs organizations | No | Ensure meaningful participation of Ips | Yes | 1.Sensitize for inclusive participation during project communication (e.g. regular briefing on GESI perspective) 2. Ensure 50% female in the workshop (women, dalits, indigenous people) where applicable 3. GESI concept and mainstreaming methodologies are incorporated in the presentation | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
| 197 | 3.2.3.2: Implement measures for HWC based on prepared plans (mentha plantation, biological/virtual fencing) | PMU/DNPWC/MITFE |  |  |  |  | 78125 |  | Plans | 10 | 10 | 100% |  |  |  |  | 3.2.3.2 | Package includes wildlife deterent plants plantation, green fences, predator proof pen fence, mesh wire /electric fencing and its maintanance, - as per community need and nature of HWC. The detials (sites/interventions) to be finalized based on participatory assessment report followed by community consultation |  | Yes | Yes | Yes | Yes | Ensure no invasive species are used and meaningful consultation with IPs | Yes | Yes | Yes | 1. Meaningful participation of IPs, Womens' Group and Dalits | Yes | 1.Sensitize for inclusive participation during project communication (e.g. regular briefing on GESI perspective) 2. Ensure 60% female, 25% Ips and 10% dalit participation during project -related loans for community level enterprise and livelihood support | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
| 198 | 3.2.3.3: Support to establish community-based insurance (crop, livestock) scheme | PMU/DNPWC/MITFE |  |  |  |  | 62500 |  | Support package | 4 | 1 | 25% |  |  |  |  | 3.2.3.3 | Package includes franction of insurance premium payments through rovolving fund establishment |  | No | No | No | No | No | Yes | Yes | No | 1. Meaningful participation of IPs, Womens' Group and Dalits | Yes | Prioritize Dalit, women's group, and IPs in decision making | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
| 199 | 3.2.3.4: Implement community-based reporting system of HWC incidents | MOFE/DOFSC/DNPWC/MITFE |  |  |  |  | 3906 |  | system | 1 | 0 | 0% |  |  |  |  | 3.2.3.4 | Prepare reporting system and implement with stakeholders support |  | No | No | No | No | No | Yes | Yes | No | 1. Meaningful participation of IPs, Womens' Group and Dalits | Yes | Prioritize Dalit, women's group, and IPs in decision making | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
[8 empty] | 152344 |  |  | 17 | 12 | 43.75% |  |  | 0 | 0
Outcome 3.3: Enhanced capacities of government agencies and community in curbing illegal wildlife crime |  |  |  | Q1 | Q2 | Q3 | Q4 | 133874.75 | [7 empty] | 0 | 0 | Outcome 3.3: Enhanced capacities of government agencies and community in curbing illegal wildlife crime |  |  | Outcome 3.3: Enhanced capacities of government agencies and community in curbing illegal wildlife crime
Output 3.3.1: Community Based Anti poaching Units functional in priority areas | 200 | 3.3.1.1: Provide support for field gears to CBAPU members | PMU/DNPWC/MITFE |  |  |  |  | 31250 |  | CBAPU/s | 100 | 91 | 91% |  |  |  |  | 3.3.1.1 | Basic safety and health equipments to community youth volunteer - CBAPU like torch light, field gears e.g. cap, rain coat/jacket. Cost includes 5 sesitization/ capacity development workshop on biodiversity conservation and environmental and social safeguard and field gears to 100 CBAPUs |  | No | No | No | No | No | No | No | No | No | Yes | Ensure Gender friendly field gears | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
| 201 | 3.3.1.2: Provide technical and financial support for skill based training to CBAPU members | PMU |  |  |  |  | 4500 |  | No of training | 1 | 0 | 0% |  |  |  |  | 3.3.1.2 | Training to CBAPU members |  | No | No | No | No | No | No | No | No | No | Yes | 1. Ensure 50% female participants in the training 2. Manual should include GESI mainstreaming methodologies | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
| 202 | 3.3.1.3: Establish revolving fund to initiate green enterprise for CBAPUs member (link to above activities) | PMU/DNPWC/MITFE |  |  |  |  | 77968.75 |  | Support Package | 2 | 0 | 0% |  |  |  |  | 3.3.1.3 | Revolving fund establishment |  | No | No | No | No | No | No | No | No | No | Yes | 1.Sensitize for inclusive participation during project communication (e.g. regular briefing on GESI perspective) 2. Ensure 60% female, 25% Ips and 10% dalit participation during project -related loans for community level enterprise and livelihood support | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
[8 empty] | 113718.75 |  |  | 103 | 91 | 30.33% |  |  | 0 | 0 | All the activities of output 3.3.1. will contribute to make CBAPU functional. The functionality will be measured based on the periodic reporting.
Output 3.3.2: Training and operation support to Park staff, rangers on wildlife crime management | 203 | 3.3.2.1: Update training manual on illegal wildlife crime scene management | MOFE/DOFSC/DNPWC/MITFE/PMU |  |  |  |  | 3906 |  | Manual | 1 | 0 | 0% |  |  |  |  | 3.3.2.1 | Manual update through experts engagement |  | No | No | No | No | No | No | No | No | No | Yes | Ensure GESI concept and mainstreaming are part of the manual | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
| 204 | 3.3.2.2: Conduct training to investigation officers level on Illegal wildlife crime scene management | MOFE/DOFSC/DNPWC/MITFE |  |  |  |  | 9375 |  | training | 4 | 0 | 0% |  |  |  |  | 3.3.2.2 | Training package developed and training conducted |  | No | No | No | No | Ensure WWF’s Support for Enforcement and Rangers in the training manual | No | No | No | No | Yes | 1.Follow WWF guidance on armed, professional poachers vs community members engaged in livelihood activities 2. Ensure at least 50% female participation (Representation of women, dalits, ethnic and indigenous peoples) | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
| 205 | 3.3.2.3: Support Transboundary coordination at local level | MOFE/DOFSC/DNPWC/MITFE |  |  |  |  | 3125 |  | meeting | 2 | 1 | 50% |  |  |  |  | 3.3.2.3 | 2 transboundary meetings between India and Nepal officials on ILM themes (species protection, HWC management etc) |  | No | No | No | No | No | No | No | No | No | Yes | 1.Sensitize for inclusive participation during project communication (e.g. regular briefing on GESI perspective) 2. Ensure at least 33% female participation (Representation of women, dalits, ethnic and indigenous peoples) | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
| 206 | 3.3.2.4: Field program implementation support & coordination | PMU/DNPWC/MITFE |  |  |  |  | 3750 |  | Month | 12 | 12 | 100% |  |  |  |  | 3.3.2.4 | Package includes cost (for 12 months) for project staff's travela nd DSA to support gratee partners technically in activity implementation and necessary coordination. |  | No | No | No | No | No | No | No | No | No | Yes | 1.Sensitize for inclusive participation during project communication (e.g. regular briefing on GESI perspective) 2. Ensure at least 33% female participation (Representation of women, dalits, ethnic and indigenous peoples) | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
[8 empty] | 20156 |  |  | 19 | 13 | 37.5% | 34.43% | 57.55% | 0 | 0
COMPONENT 4: Monitoring and evaluation (M&E), knowledge management (KM), and regional coordination | [7 empty] | 253401 | [7 empty] | 0 | 0 | COMPONENT 4: Monitoring and evaluation (M&E), knowledge management (KM), and regional coordination |  |  | COMPONENT 4: Monitoring and evaluation (M&E), knowledge management (KM), and regional coordination
Outcome 4.1: Improved coordination and dialogue on integrated landscape management from the local to national level |  |  |  | Q1 | Q2 | Q3 | Q4 | 127188 | [7 empty] | 0 | 0 | Outcome 4.1: Improved coordination and dialogue on integrated landscape management from the local to national level |  |  | Outcome 4.1: Improved coordination and dialogue on integrated landscape management from the local to national level
Output 4.1.1: Information on ILM importance shared among key stakeholders | 204 | 4.1.1.1: Organize monthly dialogue through "Jaibik Chautari" (Biodiversity Platform) at field | MOFE/DOFSC/DNPWC/MITFE/PMU |  |  |  |  | 18750 |  | Dialogue | 48 | 27 | 56.25% |  |  |  |  | 4.1.1.1 | A dialogue will be organized in coordination with local CSOs and government bodies e.g. NBCC, WCCB, TAL working group and conduct thematic discussion e.g. how to manage forest fire in fire season, HWC management and produce media reports/programs. During the implementation, number of stakeholders will be identified and documented to better align with result framework. |  | No | No | No | No | No | No | Yes; ensure representation of IPs organization | No | 1. Ensure quality representation | Yes | 1.Sensitize for inclusive participation during project communication (e.g. regular briefing on GESI perspective) 2. Ensure 50% female participation (Representation of women, dalits, ethnic and indigenous peoples) | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
| 205 | 4.1.1.2: Organize annual technical thematic discussion session at center | MOFE/DOFSC/DNPWC/MITFE/PMU |  |  |  |  | 5469 |  | meeting | 2 | 0 | 0% |  |  |  |  | 4.1.1.2 | Annual discussions among key stakeholders on ILM e.g. wildlife rescue |  | No | No | No | No | No | No | No | No | No | yes | Inclusive team members | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
| 206 | 4.1.1.4: Establish and maintain online Landscape Knowledge Learning Platform (including project website) | PMU |  |  |  |  | 781 |  | platform | 1 | 1 | 100% |  |  |  |  | 4.1.1.3 | Project website maintained and enhanced |  | No | No | No | No | No | No | No | No | No | Yes | Prioritize women's group, dalits, IPs in the learning platform | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
[8 empty] | 25000 |  |  | 51 | 28 | 52.08% |  |  | 0 | 0
Output 4.1.2: Mass awareness products on biodiversity conservation and integrated landscape management | 207 | 4.1.2.1: Provide technical and financial support to green/eco-clubs formation and its operation | PMU/DNPWC/MITFE |  |  |  |  | 58594 |  | No of eco-clubs supported | 30 | 30 | 100% |  |  |  |  | 4.1.2.1 | Capacitate eco-clubs to be part of biodiversity conservation at local level through talent competition, awareness campaign (e.g. mass awareness on waste management/plastic pollution control), small infrastructure like e.g.cycle stand, eco-garden, bio-fencing) |  | No | No | No | No | No | No | No | No | No | Yes | 1. Ensure 50% female in the Eco-club 2. Gender friendly planning and implementation | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
| 208 | 4.1.2.2: Support annual meetings of green/eco-clubs network at district level | PMU |  |  |  |  | 18750 |  | No of meetings | 12 | 8 | 66.67% |  |  |  |  | 4.1.2.2 | Orientation, exposure visits and capacity buidling training/events and meetings with eco-club networks, eco-teachers |  | No | No | Yes | No | Ensure childrens from Ips in the meeting | No | No | No | No | Yes | Ensure 50% female, and representation of Ips, dalits in the eco-club | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
| 209 | 4.1.2.3: Support special conservation events at local level | MOFE/DOFSC/DNPWC/MITFE |  |  |  |  | 13125 |  | event | 8 | 8 | 100% |  |  |  |  | 4.1.2.3 | Technical support to government entities to organize conservation events with multi-stakeholder (Ips, LCs) participation |  | No | No | No | No | No | No | Yes | No | 1. Ensure meaningful participation of IPs in celebrating events | Yes | 1.Sensitize for inclusive participation event celebration (e.g. regular briefing on GESI perspective) 2. Ensure at least 50% female participation (Representation of women, dalits, ethnic and indigenous peoples) | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
| 210 | 4.1.2.4: Sensitize media (print and TV) on integrated landscape management | PMU |  |  |  |  | 3906 |  | media | 1 | 1 | 100% |  |  |  |  | 4.1.2.4 | Organize media visits to sensitize about ILM, ensuring gender and social inclusion (GESI) dimensions during implementation |  | No | No | No | No | No | No | No | No | No | Yes | 1. GESI sensitive information 2. Ensure proper capacity building of the media to disseminate information on the importance of GESI integration in conservation. | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
| 211 | 4.1.2.5: Support radio program (local dialects) on ILM | PMU |  |  |  |  | 7813 |  | radio | 10 | 10 | 100% |  |  |  |  | 4.1.2.5 | Audio-programs development to disseminate information about ILM, ensuring gender and social inclusion (GESI) dimensions during implementation |  | No | No | No | No | No | No | No | No | No | Yes | Initiate radio program with success stories of women's group, dalits, IPs | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
[8 empty] | 102188 |  |  | 61 | 57 | 93.33% | 77.86% |  | 0 | 0
Outcome 4.2: Project monitoring system operates, systematically provides information on progress, and informs adaptive management to ensure results |  |  |  | Q1 | Q2 | Q3 | Q4 | 80275 | [7 empty] | 0 | 0 | Outcome 4.2: Project monitoring system operates, information on progress, and informs adaptive management to ensure results |  |  | Outcome 4.2: Project monitoring system operates, systematically provides information on progress, and informs adaptive management to ensure results
Output 4.2.1: Participatory planning and M&E system |  | 4.1.2.1: Provide technical and financial support to green/eco-clubs formation and its operation | [15 empty] | 4.2.1.1
| 212 | 4.2.1.2: PAC/PEC planning review workshop (Central and Field) | [5 empty] | 2344 |  | Meeting | 5 | 3 | 60% |  |  |  |  | 4.2.1.2 | Meetings as per prodoc |  | No | No | No | No | No | No | No | No | No | Yes | 1.Sensitize for inclusive participation during project communication (e.g. regular briefing on GESI perspective) 2. Ensure 33% female participation (Representation of women, dalits, ethnic and indigenous peoples) | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
| 213 | 4.2.1.3: Conduct periodic (trimester) workplan review and planning sessions | [5 empty] | 14063 |  | Workshop | 6 | 6 | 100% |  |  |  |  | 4.2.1.3 | Workshops to review project progresses/prepare quarterly and annual plan with project team and also with project stakeholders |  | No | No | No | No | No | No | No | No | No | Yes | 1.Sensitize for inclusive participation during project communication (e.g. regular briefing on GESI perspective) 2. Ensure 33% female participation (Representation of women, dalits, ethnic and indigenous peoples) | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
| 214 | 4.2.1.4: Conduct periodic and joint monitoring visits | [5 empty] | 10938 |  | Visits | 7 | 5 | 71.43% |  |  |  |  | 4.2.1.4 | Visits/travel focused on project interventions (outcomes/outputs) |  | No | No | No | No | No | No | Yes; Esure meaningful participation of IPs representative | No | No | Yes | 1.Sensitize for inclusive participation during project communication (e.g. regular briefing on GESI perspective) 2. Ensure 33% female participation (Representation of women, dalits, ethnic and indigenous peoples) | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
| 215 | 4.2.1.5: Conduct Safeguard Monitoring visits | [5 empty] | 1563 |  | Visits | 2 | 1 | 50% |  |  |  |  | 4.2.1.5 | Multi-stakeholders including Ips, LCs, local goverments, project staff, MoFE officials - visit |  | No | No | No | No | No | No | Yes; Esure meaningful participation of IPs representative | No | No | Yes | 1.Sensitize for inclusive participation during project communication (e.g. regular briefing on GESI perspective) 2. Ensure 33% female participation (Representation of women, dalits, ethnic and indigenous peoples) | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
| 216 | 4.2.1.6: Conduct training on "participatory monitoring and evaluation" to CFUGs and relevant sub-grantees | [5 empty] | 12656 |  | Training | 6 | 5 | 83.33% |  |  |  |  | 4.2.1.6 | Training cost (e.g. resource persons, training materials, participant travel, logistics) |  | No | No | No | No | No | No | Yes; Esure meaningful participation of IPs representative | No | No | Yes | 1.Sensitize for inclusive participation during project communication (e.g. regular briefing on GESI perspective) 2. Ensure 33% female participation (Representation of women, dalits, ethnic and indigenous peoples) | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
|  | 4.2.1.7: Capacity building/training of PSU staff (on project management - WWF network standards, report writing and GESI and safeguard) | [5 empty] | 0 |  | Event | [7 empty] | 4.2.1.7 | Event as training package including site visit (exposure) in integrated landscape management practices in other landscapes |  | No | No | No | No | No | No | No | No | No | Yes | 1.Sensitize for inclusive participation during project communication (e.g. regular briefing on GESI perspective) 2. Ensure 33% female participation (Representation of women, dalits, ethnic and indigenous peoples) | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
| 217 | 4.2.1.8: Organize Project Mid-term review workshops with all key stakeholders | [5 empty] | 3711 |  | Workshop | 1 | 1 | 100% |  |  |  |  | 4.2.1.8 | organize a workshop with project stakeholers as requested by Mid-term review team |  | No | No | No | No | No | No | Yes; ensure participation of IPs | No | No | Yes | 1.Sensitize for inclusive participation during project communication (e.g. regular briefing on GESI perspective) 2. Ensure 33% female participation (Representation of women, dalits, ethnic and indigenous peoples) | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
| 218 | 4.9.1.9: Conduct Project Evaluations (Mid-term and terminal evaluation - GEF/SWC) | [5 empty] | 35000 |  | No of evaluation supported | 1 | 1 | 100% |  |  |  |  | 4.2.1.9 | WWF - Technical assistance part |  | No | No | No | No | No | No | Yes; ensure participation of IP representation | No | No | Yes | 1.Sensitize for inclusive participation during project communication (e.g. regular briefing on GESI perspective) 2. Ensure 33% female participation (Representation of women, dalits, ethnic and indigenous peoples) | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
[8 empty] | 80275 |  |  | 28 | 22 | 80.68% | 80.68% |  | 0 | 0
Outcome 4.3: Project lessons shared |  |  |  | Q1 | Q2 | Q3 | Q4 | 45938 | [7 empty] | 0 | 0 | Outcome 4.3: Project lessons shared |  |  | Outcome 4.3: Project lessons shared
Output 4.3.1: Project lessons captured and disseminated to project stakeholders and to other projects and partners |  | 4.3.1.1: Documentation on Traditional Knowledge associated to natural resources | PMU | [14 empty] | 4.3.1.1
| 220 | 4.3.1.2: Prepare success stories and videos of the project | PMU/DNPWC/MITFE |  |  |  |  | 10938 |  | No of stories/videos | 7 | 5 | 71.43% |  |  |  |  | 4.3.1.2 | Prepare 7 short videos and 1 story of the project highlighting project interventions, ensure the GESI dimensions as part of lessons and stories |  | No | Reflect Ips issues and mitigation measures taken into success stories | Reflect Ips issues and mitigation measures taken into success stories | yes; reflect on impacts of discouraging invasive species | Reflect impact of project intervention on IP, dalit and womens | Yes; take consent before story collection and disclose before dissemianation | No | No | No | yes | Ensure proper cpacity building of the media to disseminate information on the importance of GESI integration in conservation | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
| 221 | 4.3.1.3: Print case studies and periodic project reports | PMU |  |  |  |  | 3828 |  | Reports | 1 | 1 | 100% |  |  |  |  | 4.3.1.3 | Cost includes any policy documents review, design and printing support to relevent government organizations |  | No | No | No | No | No | No | No | No | No | yes | Ensure proper cpacity building of the media to disseminate information on the importance of GESI integration in conservation | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
| 222 | 4.3.1.4: Provide financial support to participate in national/international scientific forum for field staff | PMU |  |  |  |  | 3906 |  | Persons supported | 2 | 1 | 50% |  |  |  |  | 4.3.1.4 | Provide support to participate in international scientific forum for ILaM project staff |  | No | No | No | No | No | No | No | No | No | yes | Ensure proper cpacity building of the media to disseminate information on the importance of GESI integration in conservation | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
| 223 | 4.3.1.5: Provide financial support to publish journal articles | PMU |  |  |  |  | 3828 |  | Articles | 1 | 1 | 100% |  |  |  |  | 4.3.1.5 | Provide support to prepare and publish a journal article in ILaM project theme |  | No | No | No | No | No | No | No | No | No | yes | Ensure proper cpacity building of the media to disseminate information on the importance of GESI integration in conservation | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
| 224 | 4.3.1.6: Field program implementation support & coordination | PMU/DNPWC/MITFE |  |  |  |  | 23438 |  | Month | 12 | 12 | 100% |  |  |  |  | 4.3.1.6 | Package includes Staff travel and DSA, coordination meeting with gov. partners, gov staffs travel and communication support, coordination meeting with IPs and local communities, travel cost/transporation and communication support to gov partners for monitoring and technical backstopping |  | No | No | No | No | No | No | No | No | No | yes | Ensure proper cpacity building of the media to disseminate information on the importance of GESI integration in conservation | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
| 225 | 4.2.1.7: Organize final project lessons sharing workshop | PMU | [14 empty] | 4.3.1.7
[8 empty] | 45938 |  |  | 23 | 20 | 84.29% | 84.29% | 80.46% | 0 | 0
B. Project Management Costs | [7 empty] | 271558 | [7 empty] | 0 | 0
Office and field running costs |  |  |  | Q1 | Q2 | Q3 | Q4 | 49034 | [7 empty] | 0 | 0
Project Management Unit | 56xx | Office Utility | PMU |  |  |  |  | 2813 |  | Month | 12
| 56xx | Office and Equipment Maintenance | PMU |  |  |  |  | 938 |  | Month | 12
| 56xx | Office Insurance (including office vehicles) | PMU |  |  |  |  | 1172 |  | Time | 2
| 56xx | Office Rent | PMU |  |  |  |  | 3906 |  | Month | 12
| 56xx | Equipment Running Cost | PMU |  |  |  |  | 469 |  | Month | 12
| 56xx | Vehicle Running Costs (Vehicle Repair) | PMU |  |  |  |  | 3281 |  | Month | 12
| 56xx | Vehicle Running Costs (fuel for office purpose) | PMU |  |  |  |  | 5625 |  | Month | 12
| 56xx | Field Supplies (field gear for project staff) | PMU |  |  |  |  | 1758 |  | Package | 1
| 56xx | Photocopying | PMU |  |  |  |  | 234 |  | Month | 12
| 56xx | Postage & Shipping | PMU |  |  |  |  | 938 |  | Month | 12
| 56xx | Communications (phone, fax, internet) | PMU |  |  |  |  | 2813 |  | Month | 12
| 56xx | Supplies | PMU |  |  |  |  | 7813 |  | Month | 12
| 56xx | Field program implementation support coordination (Staffs travel and Inhouse Meeting) | PMU |  |  |  |  | 7599 |  | Month | 12
| 56xx | Advertisment/Priniting and Publication | PMU |  |  |  |  | 3906 |  | Printing | 5
| 56xx | Bank charges | PMU |  |  |  |  | 300 |  | Month | 12
| 56xx | Annual Audit | PMU |  |  |  |  | 5469 |  | Audit | 1
[8 empty] | 49034 |  |  | 153 | 0 |  |  |  | 0 | 0
|  | Capital Assets | [5 empty] | 15489 | [7 empty] | 0 | 0
| 58xx | Cupboard/File Racks (for Banke office and for Kathmandu Office) | PMU |  |  |  |  | 390 |  | Set | 1
| 58xx | Office Board/Notice boards etc | PMU |  |  |  |  | 0 |  |  | 0
| 58xx | Laptop (with dock-in set) | PMU |  |  |  |  | 3000 |  | No | 3
| 58xx | Data Backup/Hard Drive | PMU |  |  |  |  | 352 |  | No | 3
| 58xx | CC Camera for PMU Office | PMU |  |  |  |  | 390 |  | Set | 1
| 58xx | TV 65" for PMU office (multipurpose uses) | PMU |  |  |  |  | 1172 |  | No | 1
| 58xx | Air conditioner with associated cost (for field office) | PMU |  |  |  |  | 3000 |  | No | 3
| 58xx | Micro-oven (for Banke) | PMU |  |  |  |  | 156 |  | No | 1
| 58xx | Cameras/Binacular | PMU |  |  |  |  | 780 |  | No | 2
| 58xx | Multi-function printer (for Banke) | PMU |  |  |  |  | 391 |  | No | 1
| 58xx | Power back up system (for Banke) | PMU |  |  |  |  | 3906 |  | Set | 1
| 58xx | Projector-Screen | PMU |  |  |  |  | 0 |  |  | 0
| 58xx | Desktop Screen (monitor) | PMU |  |  |  |  | 0 |  |  | 0
| 58xx | GPS (Banke Office) | PMU |  |  |  |  | 0 |  |  | 0
| 58xx | Account Software (Activity-wise reporting, AMC etc.) | PMU |  |  |  |  | 390 |  | Set | 1
| 58xx | Office 365 insallation, Sofware AMC etc | PMU |  |  |  |  | 781 |  | Softwares | 1
| 58xx | IT support | PMU |  |  |  |  | 781 |  | Support | 1
| 58xx | Office and restroom renovation, Kathmandu Office | PMU |  |  |  |  | 0 |  |  | 0
[8 empty] | 15489 |  |  | 20 |  |  |  |  | 0 | 0
|  | Personnel | [5 empty] | 207035
GRAND TOTAL (A+B) |  |  |  | YR 4 |  |  |  | 2718455 | [7 empty] | 0 | 0
|  |  | Carry-over total (unspent funds from previous year) | [10 empty] | % achieved for activities overall | 60.11% | Actual budget for previous project year
Request of funds for Upcoming Project Year
[20 empty] | GL CODE | LMBIS CODE | ACT# NO# | COMPONENT / OUTCOME / OUTPUT/ACTIVITIES | RESPONSIBLE | TIMELINE |  |  |  | UNIT DESCRIPTION | TARGET | UNIT COST | TOTAL BUDGET | Remarks | COMPONENT |  |  |  |  | TOTAL BUDGET | [6 empty] | BUDGET BIFUCATION |  |  | Outcomes
[25 empty] | Q1 | Q2 | Q3 | Q4 | [5 empty] | Com.1 | Com.2 | Com.3 | Com.4 | Mgmt. | Jan-Mar 2021 | Apr-Jun 2021 | Jul-Sep 2021 | Oct-Dec 2021 | Jan-Mar 2022 | Apr-Jun 2022 | TOTAL Budget | TECHNICAL ASSISTANCE | PROGRAM FUNDING | TOTAL
[23 empty] | A. PERSONNEL COSTS |  | 0 | 0 | 0 | 0 |  |  |  | 341694.2045 |  | 58379.8687 | 41832.346 | 133332.8761 | 62713.2273 | 45435.8864 | 56949.0341 | 56949.0341 | 56949.0341 | 56949.0341 | 56949.0341 | 56949.0341 | 341694.2045 | 341694.2045 | 0 | 341694.2045
[20 empty] | 50xx |  |  | Project Coordinator | PMU |  |  |  |  | Mo. | 15 | 2424.5455 | 36368.1818 |  | 18184.0909 | 3636.8182 | 7273.6364 | 1818.4091 | 5455.2273 | 6061.3636 | 6061.3636 | 6061.3636 | 6061.3636 | 6061.3636 | 6061.3636 | 36368.1818 | 36368.1818 | 0 | 36368.1818
[20 empty] | 50xx |  |  | Project Manager | PMU |  |  |  |  | Mo. | 15 | 2239.3636 | 33590.4545 |  | 6718.0909 | 6718.0909 | 11756.6591 | 3359.0455 | 5038.5682 | 5598.4091 | 5598.4091 | 5598.4091 | 5598.4091 | 5598.4091 | 5598.4091 | 33590.4545 | 33590.4545 | 0 | 33590.4545
[20 empty] | 50xx |  |  | Finance and Administration Manager | PMU |  |  |  |  | Mo. | 15 | 1860.4091 | 27906.1364 |  | 3488.267 | 3488.267 | 9767.1477 | 5581.2273 | 5581.2273 | 4651.0227 | 4651.0227 | 4651.0227 | 4651.0227 | 4651.0227 | 4651.0227 | 27906.1364 | 27906.1364 | 0 | 27906.1364
[20 empty] | 50xx |  |  | Field Manager | PMU |  |  |  |  | Mo. | 15 | 1403.1818 | 21047.7273 |  | 3157.1591 | 3157.1591 | 10523.8636 | 4209.5455 | 0 | 3507.9545 | 3507.9545 | 3507.9545 | 3507.9545 | 3507.9545 | 3507.9545 | 21047.7273 | 21047.7273 | 0 | 21047.7273
[20 empty] | 50xx |  |  | Field Program Officer | PMU |  |  |  |  | Mo. | 15 | 1343.0455 | 20145.6818 |  | 2014.5682 | 4029.1364 | 10072.8409 | 4029.1364 | 0 | 3357.6136 | 3357.6136 | 3357.6136 | 3357.6136 | 3357.6136 | 3357.6136 | 20145.6818 | 20145.6818 | 0 | 20145.6818
[20 empty] | 50xx |  |  | Field Finance/Compliance Officer | PMU |  |  |  |  | Mo. | 15 | 1343.0455 | 20145.6818 |  | 2518.2102 | 2518.2102 | 7050.9886 | 4029.1364 | 4029.1364 | 3357.6136 | 3357.6136 | 3357.6136 | 3357.6136 | 3357.6136 | 3357.6136 | 20145.6818 | 20145.6818 | 0 | 20145.6818
[20 empty] | 50xx |  |  | Field Monitoring, Evaluation and Learning (MEL) Officer | PMU |  |  |  |  | Mo. | 15 | 1363.0909 | 20446.3636 |  | 0 | 0 | 0 | 20446.3636 | 0 | 3407.7273 | 3407.7273 | 3407.7273 | 3407.7273 | 3407.7273 | 3407.7273 | 20446.3636 | 20446.3636 | 0 | 20446.3636
[20 empty] | 50xx |  |  | Field Finance and Administration Associate | PMU |  |  |  |  | Mo. | 15 | 1072.4318 | 16086.4773 |  | 2010.8097 | 2010.8097 | 5630.267 | 3217.2955 | 3217.2955 | 2681.0795 | 2681.0795 | 2681.0795 | 2681.0795 | 2681.0795 | 2681.0795 | 16086.4773 | 16086.4773 | 0 | 16086.4773
[20 empty] | 50xx |  |  | Field Program Assistant (4) | PMU |  |  |  |  | Mo. | 15 | 3046.9091 | 45703.6364 |  | 2285.1818 | 4570.3636 | 36562.9091 | 2285.1818 |  | 7617.2727 | 7617.2727 | 7617.2727 | 7617.2727 | 7617.2727 | 7617.2727 | 45703.6364 | 45703.6364 | 0 | 45703.6364
[20 empty] | 50xx |  |  | Front Desk Assistant _KTM | PMU |  |  |  |  | Mo. | 15 | 801.8182 | 12027.2727 |  | 962.1818 | 962.1818 | 2886.5455 | 1202.7273 | 6013.6364 | 2004.5455 | 2004.5455 | 2004.5455 | 2004.5455 | 2004.5455 | 2004.5455 | 12027.2727 | 12027.2727 | 0 | 12027.2727
[20 empty] | 50xx |  |  | Front Desk Assistant _Field | PMU |  |  |  |  | Mo. | 15 | 781.7727 | 11726.5909 |  | 938.1273 | 938.1273 | 2814.3818 | 1172.6591 | 5863.2955 | 1954.4318 | 1954.4318 | 1954.4318 | 1954.4318 | 1954.4318 | 1954.4318 | 11726.5909 | 11726.5909 | 0 | 11726.5909
[20 empty] | 50xx |  |  | Communication Officer (100% ) | PMU |  |  |  |  | Mo. | 15 | 1454.5455 | 21818.1818 |  | 3490.9091 | 3490.9091 | 10472.7273 | 4363.6364 | 0 | 3636.3636 | 3636.3636 | 3636.3636 | 3636.3636 | 3636.3636 | 3636.3636 | 21818.1818 | 21818.1818 | 0 | 21818.1818
[20 empty] | 50xx |  |  | Field Safeguard and GESI Officer | PMU |  |  |  |  | Mo. | 15 | 1545.4545 | 23181.8182 |  | 3477.2727 | 3477.2727 | 11590.9091 | 4636.3636 | 0 | 3863.6364 | 3863.6364 | 3863.6364 | 3863.6364 | 3863.6364 | 3863.6364 | 23181.8182 | 23181.8182 | 0 | 23181.8182
[20 empty] | 50xx |  |  | Office Messenger (2) | PMU |  |  |  |  | Mo. | 15 | 1050 | 15750 |  | 1260 | 1260 | 3780 | 1575 | 7875 | 2625 | 2625 | 2625 | 2625 | 2625 | 2625 | 15750 | 15750 | 0 | 15750
[20 empty] | 50xx |  |  | Driver (2) | PMU |  |  |  |  | Mo. | 15 | 1050 | 15750 |  | 7875 | 1575 | 3150 | 787.5 | 2362.5 | 2625 | 2625 | 2625 | 2625 | 2625 | 2625 | 15750 | 15750 | 0 | 15750
[23 empty] | B. ACTIVITY COST | [8 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on K8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Support is not a unit description. What is the support concretely?
Note on A44: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: New Outcome
Note on C140: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Suggest putting these cost under a component
Note on AG184: Author: 120,000/Fulltime

## AWPB Yr 5
Period: Year 5 (July 1, 24 - June 30, 25) (FY 81/82)
[12 empty] | WORK PLAN TRACKING (Tracking at end of project year) | [5 empty] | Additonal Notes
COMPONENT / OUTCOME / OUTPUT | # | ACTIVITIES | Responsible | YEAR X TIMING |  |  |  | BUDGET in $ | x | UNIT DESCRIPTION | TARGET | # UNIT(S) ACHIEVED | % ACHIEVED BY ACTIVITY (# unit(s) achieved / target) | % ACHIEVED BY OUTCOME | % ACHIEVED BY COMPONENT | BUDGET (actual, by Component) |  |  |  | Safeguard issues |  |  |  | Measures | IPPF |  |  |  | GESI intigration
|  |  |  | Q1 | Q2 | Q3 | Q4 | TA | if activity is carried over from previous year | # of | [5 empty] | in Rupee | in USD | Act# | Activity | Policy on natural habitat | Policy on involuntary resettlement | Policy on indigenous people | Policy on pest management | Proposed mitigating activities | FPIC needed or not | IP organization direct collaboration possible or not | Livelihood restoration plan | Action to be taken during implementation | Trigger or not | Action points | Additional information
A. ACTIVITY COSTS | [7 empty] | 1603776 | [7 empty] | 0 | 0 | Technical Assistance - WWF GEF Part
COMPONENT 1: National capacity and enabling environment for cross-sectoral coordination to promote forest and landscape conservation | [7 empty] | 228973 | [7 empty] | 0 | 0 | COMPONENT 1: National capacity and enabling environment for cross-sectoral coordination |  | COMPONENT 1: National capacity and enabling environment for cross-sectoral coordination
Output 1.1.1 : Cross-sectoral coordination mechanisms established to support integrated landscape management for conservation outcomes at different levels | 1 | 1.1.1.1: Provide support to NBCC committee (ensure gender inclusive team) | MOFE/DOFSC/DNPWC/MITFE/PMU |  |  |  |  | 2344 |  | Support | 2 | 0 | 0% |  |  |  |  | 1.1.1.1 | Support includes meeting logistics and office equipment to MoFE, To make unit trackable - PMU will update the workplan during implementation whether it will be meeting logistic support or equipment | No | No | No | No | No | No | No | No | No | Yes | 1.Sensitize for inclusive participation during project communication (e.g. regular briefing on GESI perspective) 2. Ensure at least 33% female participants in the coordination mechanism (Representation of women, dalits, ethnic and indigenous peoples (where applicable) 3. Ensure coordination mechanism listens and value the idea, perception and needs of women, dalit, janjati, poor and marginalized people of the community (Do no harm and ensure safeguard of women, dalit, janjati, poor and marginalized people during the meeting of coordination mechanism) | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
| 2 | 1.1.1.2 Organize State level Biodiversity Co-ordination Committee (State 2,3,5,7 and Karnali) meetings | MOFE/DOFSC/DNPWC/MITFE |  |  |  |  | 10806 |  | Meeting | 7 | 0 | 0% |  |  |  |  | 1.1.1.2 | Cost includes meetings/workshop logistics | No | No | No | No | No | No | No | No | No | Yes | 1.Sensitize for inclusive participation during project communication (e.g. regular briefing on GESI perspective) 2. Ensure at least 33% female participants in the coordination mechanism (Representation of women, dalits, ethnic and indigenous peoples (where applicable) 3. Ensure coordination mechanism listens and value the idea, perception and needs of women, dalit, janjati, poor and marginalized people of the community (Do no harm and ensure safeguard of women, dalit, janjati, poor and marginalized people during the meeting of coordination mechanism) | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
| 3 | 1.1.1.3 Provide technical and financial support to State Biodiversity Co-ordination committee | MOFE/DOFSC/DNPWC/MITFE/PMU |  |  |  |  | 1641 |  | Support | 1 | 0 | 0% |  |  |  |  | 1.1.1.3 | States (MoEFSC - Sudurpaschim, Lumbini, Madesh , Bagmati, Karnali province) will receive institutional support after formation of province level BCC to enhance understanding and adoption of Integrated Landscape Management | No | No | No | No | No | No | No | No | No | Yes | 1.Sensitize for inclusive participation during project communication (e.g. regular briefing on GESI perspective) 2. Ensure at least 33% female participants in the coordination mechanism (Representation of women, dalits, ethnic and indigenous peoples (where applicable) 3. Ensure coordination mechanism listens and value the idea, perception and needs of women, dalit, janjati, poor and marginalized people of the community (Do no harm and ensure safeguard of women, dalit, janjati, poor and marginalized people during the meeting of coordination mechanism) | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
| 4 | 1.1.1.4 Organize inter-ministerial coordination mechanism for wildlife friendly infrastructure | MOFE/DOFSC/DNPWC/MITFE/PMU |  |  |  |  | 5469 |  | Meeting | 2 | 0 | 0% |  |  |  |  | 1.1.1.4 | Multistakeholder meeting organized focussing on widlife friendly infrastructure promotion | No | No | No | No | No | No | No | No | No | Yes | 1.Sensitize for inclusive participation during project communication (e.g. regular briefing on GESI perspective) 2. Ensure at least 33% female participants in the coordination mechanism (Representation of women, dalits, ethnic and indigenous peoples (where applicable) 3. Ensure coordination mechanism listens and value the idea, perception and needs of women, dalit, janjati, poor and marginalized people of the community (Do no harm and ensure safeguard of women, dalit, janjati, poor and marginalized people during the meeting of coordination mechanism) | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
| 5 | 1.1.1.5 Organize inter-state coordination (2, 3, Gandaki, 5, Karnali, 7) for implementation of the NBSAP and TAL Strategy | PMU/DNPWC/MITFE |  |  |  |  | 5391 |  | Meeting | 3 | 0 | 0% |  |  |  |  | 1.1.1.5 | Enhancing inter-state coordination on ILM works through organizing interaction on ILM based on NBSAP and TAL strategy | No | No | No | No | No | No | No | No | No | Yes | 1.Sensitize for inclusive participation during project communication (e.g. regular briefing on GESI perspective) 2. Ensure at least 33% female participants in the coordination mechanism (Representation of women, dalits, ethnic and indigenous peoples (where applicable) 3. Ensure coordination mechanism listens and value the idea, perception and needs of women, dalit, janjati, poor and marginalized people of the community (Do no harm and ensure safeguard of women, dalit, janjati, poor and marginalized people during the meeting of coordination mechanism) | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
| 6 | 1.1.1.6 Carry out cluster meetings with Municipalities | PMU/DNPWC/MITFE |  |  |  |  | 7813 |  | Meeting | 20 | 15 | 75% |  |  |  |  | 1.1.1.6 | Local governments will be sensitized about importance of ILM and coordinate/faciliate in LG's planning process and will be oriented on TAL and NBSAP strategy | No | No | No | No | No | No | No | No | No | Yes | 1.Sensitize for inclusive participation during project communication (e.g. regular briefing on GESI perspective) 2. Ensure at least 33% female participants in the coordination mechanism (Representation of women, dalits, ethnic and indigenous peoples (where applicable) 3. Ensure coordination mechanism listens and value the idea, perception and needs of women, dalit, janjati, poor and marginalized people of the community (Do no harm and ensure safeguard of women, dalit, janjati, poor and marginalized people during the meeting of coordination mechanism) | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
| 7 | 1.1.1.7 Conduct final review of NBSAP (2014-2020) | PMU |  |  |  |  | 15150 |  | Package | 1 | 1 | 100% |  |  |  |  | 1.1.1.7 | Cost includes consulting services, roll out of NBSAPin project sites (Province and Local level) if approved by Government of Nepal in Project period
| 8 | 1.1.1.8 Provide technical and financial support to WCCB | MOFE/DOFSC/DNPWC/MITFE |  |  |  |  | 2734 |  | District cell | 2 | 3 | 100% |  |  |  |  | 1.1.1.8 | WCCBs (district level) will be strengthend through institutional support | No | No | No | No | No | No | No | No | No | Yes | 1.Support women friendly tools 2. Advocacy for inclusive WCCB | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
| 9 | 1.1.1.9 Field program implementation support & coordination | PMU/BaNP/BNP |  |  |  |  | 9375 |  | Month | 12 | 12 | 100% |  |  |  |  | 1.1.1.9 | Package includes cost for project staff's travel cost (Transportation and DSA) to support grantee partners in activity implementation and coordination. Also includes monitoring cost to grantee partners | No | No | No | No | No | No | No | No | No | Yes | 1.Sensitize for inclusive participation during project communication (e.g. regular briefing on GESI perspective) 2. Ensure at least 33% female participants in the coordination mechanism (Representation of women, dalits, ethnic and indigenous peoples (where applicable) 3. Ensure coordination mechanism listens and value the idea, perception and needs of women, dalit, janjati, poor and marginalized people of the community (Do no harm and ensure safeguard of women, dalit, janjati, poor and marginalized people during the meeting of coordination mechanism) | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
[8 empty] | 60723 |  |  | 50 | 31 | 41.67% | 41.67% |  | 0 | 0
Outcome 1.2 Capacity increased for multi-stakeholder and cross-sector landscape and forest planning and management |  |  |  | Q1 | Q2 | Q3 | Q4 | 168250 | [7 empty] | 0 | 0 | Outcome 1.2 Capacity increased for multi-stakeholder and cross-sector landscape and forest planning and management |  | Outcome 1.2 Capacity increased for multi-stakeholder and cross-sector landscape and forest planning and management
Output 1.2.1. Conservation Leadership Training provided | 10 | 1.2.1.1: Conduct training to ILM coordinators for capturing international best practice on cross-sector landscape and forest planning/management and applying this to the local context | PMU/DNPWC/MITFE |  |  |  |  | 12000 |  | ILM coordinators trained | 1 | 0 | 0% |  |  |  |  | 1.2.1.1 | ILM coordinators working in biodiversity conservation in TAL will be capacited on ILM through international exposures. Capacitated officials are expected to engage to replicate pragmatic approaches and new knowledge in landscape management. | No | No | No | No | No | No | No | No | No | Yes | 1.Sensitize for inclusive participation during project communication (e.g. regular briefing on GESI perspective and synergies across all level) 2. Ensure 30% female participation (Representation of women, dalits, ethnic and indigenous peoples) with meaninfgul representation in the decision making process | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
[8 empty] | 12000 |  |  | 1 | 0 | 0% |  |  | 0 | 0
Output 1.2.2 Training courses provided on key subjects for integrated landscape management for responsible federal and state government staff | 11 | 1.2.2.1: Conduct training on Biodiversity conservation and monitoring | PMU |  |  |  |  | 3906 |  | Training | 1 | 1 | 100% |  |  |  |  | 1.2.2.1 | At least 20 government staffs (state and federal staffs) will be given training with 2 training package | No | No | No | No | No | No | Yes | No | Yes. ensure meaningful participation of IPs group, women's group and dalit groups in the consultation process with quality representation in decision making process | Yes | 1.Sensitize for inclusive participation during project communication (e.g. regular briefing on GESI perspective and synergies across all level) 2. Ensure 50% female participation (Representation of women, dalits, ethnic and indigenous peoples) with meaninfgul representation in the decision making process 3. The training manual must include GESI component related to conservation, cover GESI sensitive curriculum/topics, positive change in social norms approach in conservation 4. Use participatory training methods 5. Develop pre-test, post-test questionnaire as an integral part of manual | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
| 12 | 1.2.2.2: Conduct training on Disaster Risk Management | PMU |  |  |  |  | 7813 |  | Training | 2 | 0 | 0% |  |  |  |  | 1.2.2.2 | At least 30 government staffs (state and federal staffs) will be given training with 2 training package | No | No | No | No | No | No | Yes | No | Yes. ensure meaningful participation of IPs group, women's group and dalit groups in the consultation process with quality representation in decision making process | Yes | 1.Sensitize for inclusive participation during project communication (e.g. regular briefing on GESI perspective and synergies across all level) 2. Ensure 50% female participation (Representation of women, dalits, ethnic and indigenous peoples) with meaninfgul representation in the decision making process 3. The training manual must include GESI component related to conservation, cover GESI sensitive curriculum/topics, positive change in social norms approach in conservation 4. Use participatory training methods 5. Develop pre-test, post-test questionnaire as an integral part of manual | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
| 13 | 1.2.2.3: Orientation on roles and responsibilities for new park staff (senior/game scouts) | BaNP/BNP |  |  |  |  | 3906 |  | Orientation | 4 | 3 | 75% |  |  |  |  | 1.2.2.3 | Training to national park staff on roles and responsibilites. trainee will be identified with inclusive representation | No | No | No | No | No | No | No | No | No | Yes | Capacity building on GESI concepts and mainstreaming methodologies | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
| 14 | 1.2.2.4: Orientation on roles and responsibilities for new divisional staff | DFO-B/DFO-P |  |  |  |  | 3906 |  | Orientation | 4 | 3 | 75% |  |  |  |  | 1.2.2.4 | Training package - In coordination with Division Forest officials, trainee will be identified with inclusive representation | No | No | No | No | No | No | No | No | No | Yes | Capacity building on GESI concepts and mainstreaming methodologies | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
[8 empty] | 19531 |  |  | 11 | 7 | 62.5% |  |  | 0 | 0
Output 1.2.3 Small grants for innovation in ILM (conservation, natural resource, and landscape management) in TAL corridors and PA buffer zones | 15 | 1.2.3.1:Provide Individual grant (Bachelors and Master's thesis) | PMU |  |  |  |  | 11719 |  | Grants | 20 | 15 | 75% |  |  |  |  | 1.2.3.1 | Thesis grant will be provided as per PEC approved guideline | No | No | No | No | Include Safeguards and GESI research theme | No | Yes; consultation and meaningful participation of IPs should be ensured when applicable | No | Yes. ensure meaningful participation of IPs group, women's group and dalit groups in the consultation process with quality representation in decision making process | Yes | 1. GESI-sensitive selection criteria are used for the selection of Bachelor’s and Master’s degree students 2. Follow participatory method in community consultation processes 3. Ensure 50% female participants (Representation of women, dalits, ethnic and indigenous peoples) with meaningful participation in the decision making processes | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
|  | 1.1.3.2: Provide Institutional grant to Academic Institutional and CBOs/CSOs | PMU |  |  |  |  | $- |  | Grants | [7 empty] | 1.2.3.2 | Includes study, action research or scientific research and on the ground interventions as well. However priority will be given to academic institutions in research and extension work related to NRM and biodiversity Conservation in TAL corridors and PA buffer zones that will help address threats and barriers in achieveing overall project objective (10,000 realigned from 1.2.3.2 to 1.2.3.1 ; 21,406 realigned from 1.2.3.2 to 1.2.3.3 - MTR recommendation) | No | No | No | No | No | No | Yes | No | Yes. ensure meaningful participation of IPs group, women's group and dalit groups in the consultation process with quality representation in decision making process | Yes | 1. GESI-sensitive selection criteria are used for identifying local CBOs/CSOs to provide grants (i.e. ensuring an equal percentage of women-led CBOs/CSOs have access to grants, as much as possible) 2. Ensure 50% female participation (Representation of women, dalits, ethnic and indigenous peoples) with meaningful representation in the decision making processes during capacity enhacement trainings and participations | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
| 16 | 1.2.3.3: Provide innovation grant to the government agencies (National Park, Forest Division, Research and Training Centre) at state level | PMU/DNPWC/MoEFSC |  |  |  |  | 125000 |  | Grants | 6 | 6 | 100% |  |  |  |  | 1.2.3.3 | Include infrastructure, equipments and research (HWC management, problem animal-rescue equipment , ecotourism promotion, species management and habitat management), study, capacity development training to government officials and scientific research. Priority in TAL area | No | No | No | No | No | No | Yes | No | Yes. ensure meaningful participation of IPs group, women's group and dalit groups in the consultation process with quality representation in decision making process | Yes | 1. Ensure at least 33% female participation (Representation of women, dalits, ethnic and indigenous peoples) with meaningful representation in the decision making process in selection of participants (awardees) and conduction of consultation meetings with community | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
[8 empty] | 136719 |  |  | 26 | 21 | 87.5% | 60.71% | 50% | 0 | 0
Component 2: Integrated Planning for Protected Area Buffer Zones and Critical Corridors in the Terai Arc Landscape | [7 empty] | 67314 | [7 empty] | 0 | 0 | Component 2: Integrated Planning for Protected Area Buffer Zones and Critical Corridors in the Terai Arc Landscape |  | Component 2: Integrated Planning for Protected Area Buffer Zones and Critical Corridors in the Terai Arc Landscape
Outcome 2.1: Improved corridor planning for TAL corridors (Brahmadev, Karnali and Kamdi) |  |  |  | Q1 | Q2 | Q3 | Q4 | 3000 | [7 empty] | 0 | 0 | Outcome 2.1: Improved corridor planning for TAL corridors (Brahmadev, Karnali and Kamdi) |  | Outcome 2.1: Improved corridor planning for TAL corridors (Brahmadev, Karnali and Kamdi)
Output 2.1.1 Biodiversity surveys, socio-economic surveys, and local stakeholder consultation for Brahmadev , Karnali, and Kamdi corridors to determine feasibility of appropriate models for community-based natural resource management |  | 2.1.1.1: Conduct assessment to update biodiversity inventory and socio-economic status in corridors (incorporating GESI aspect, indigenous people and access restriction information) | PMU |  |  |  |  | $- | [9 empty] | 2.1.1.1 | (4,757 realigned from 2.1.1.1 to 2.2.3.3 after activity completion)
|  | 2.1.1.2: Provide technical support to review existing forest encroachment status and response options considering GESI aspect and any necessary safeguards management plans (e.g. IPP or LRP)” | BaNP/BNP/ DFO-B/ DFO-P |  |  |  |  | $- |  | Assessment | 0 | [6 empty] | 2.1.1.2
| 17 | 2.1.1.3: Prepare corridor/bottleneck assessment report with GESI and safeguards integration | PMU |  |  |  |  | 3000 |  | Assessment | 1 | 0 | 0% |  |  |  |  | 2.1.1.3 | Assessment report preparation cost | Yes | Yes | Yes | No | Yes; Report any as such required during the assessment report preparation process | Yes, ensure meaningful participation of IPs | yes | prepare based on screening | Ensure meaningful participation of IPs, Dalits and women | Yes | 1. Sensitize for inclusive participation 2. Ensure 50% female participation (Representation of women, dalits, ethnic and indigenous peoples) | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
[8 empty] | 3000 |  |  | 1 | 0 | 0% | 0% |  | 0 | 0
Outcome 2.2: Improved participatory planning for sustainable management of in Banke-Bardia complex |  |  |  | Q1 | Q2 | Q3 | Q4 | 34376 | [7 empty] | 0 | 0 | Outcome 2.2: Improved participatory planning for sustainable management of in Banke-Bardia complex |  | Outcome 2.2: Improved participatory planning for sustainable management of in Banke-Bardia complex
Output 2.2.1: Land uses, biodiversity values, forest carbon, and key threats assessed, mapped, reported and disseminated to identify priority villages and forest areas in the targeted PA buffer zones and corridors | 18 | 2.2.1.1: Conduct participatory assessments in targeted PA buffer zones and corridors to identify priority community and forest areas | PMU |  |  |  |  | 6250 |  | Package | 1 | 1 | 100% |  |  |  |  | 2.2.1.1 | Based on learnings from Ilam Project interventions prepared a document on integrated landscape management approach, published and orientation to stakeholders, Cost includes consulting service, printing and workshop | Yes; incorporate the habitat degradation status and patch areas in the assessment | Yes; analyze any access restriction issues | Yes; ensure meaningful participation IPs | No | 1.Ensure habitat degradation, patch areas identification, access restriction issues 2. Ensure meaningful participation of IPS, women's group and dalit groups | Yes | Yes | Yes; Report any as such requred during the consultation process | Ensure meaningful participation of IPS | Yes | 1.Sensitize for inclusive participation during project communication (e.g. regular briefing on GESI perspective) 2. Ensure at least 50% female participants (Representation of women, dalits, ethnic and indigenous peoples) | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
| 19 | 2.2.1.2: Conduct resource mapping of CFUGs at corridor level and BZUCs | PMU/DNPWC/MITFE |  |  |  |  | 14063 |  | Assessment | 6 | 0 | 0% |  |  |  |  | 2.2.1.2 | Resource mapping with expert supports BaNP BZ, BNP BZ, Kamdi and Karnali corridor, Bramhadev corridor | Yes | Yes | Yes | No | 1. Ensure issues of IPs, Dalits and Women's group | Yes | Yes | Yes; prepare on the basis of screnning | 1. Consultations with IPs, Womens' Group and Dalits | Yes | 1.Sensitize for inclusive participation during project communication (e.g. regular briefing on GESI perspective) 2. Ensure 50% female participation (Representation of women, dalits, ethnic and indigenous peoples) | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
| 20 | 2.2.1.3: Carry out consultations at identified communities | MOFE/DOFSC/DNPWC/MITFE |  |  |  |  | 9375 |  | Event | 80 | 105 | 100% |  |  |  |  | 2.2.1.3 | At least 80 events of consultation meetings and co-ordinaton meetings will be conducted with the identified communities. Based on the forest and community Participatory Assessment Report (updated) to facilitate implementation of project activities including program/financial compliance orientation | Yes; discuss on habitat degradation issues | Yes; analyze any access restriction issues and mitigation strategies | Yes; participate IPs in consultation process | No | Yes; on the basis of consultation | Yes | Yes | No | Ensure meaningful participatoin of IPs/ in consultation process and in decision making processs | Yes | 1.Sensitize for inclusive participation during project communication (e.g. regular briefing on GESI perspective) 2. Ensure 50% female participants (Representation of women, dalits, ethnic and indigenous peoples) with meaningful participation in decision making process | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
[8 empty] | 29688 |  |  | 87 | 106 | 66.67% |  |  | 0 | 0
Output 2.2.2: Sustainable Forest Management Operational Plans developed or revised for priority forest areas, incorporating the assessment from 2.2.1 |  | 2.2.2.1: Provide financial support to develop State forest sector strategies (including Community Forests, Protected Forests and Leash-hold Forest) | MOFE/DOFSC/DNPWC/MITFE | [6 empty] | Strategy study | [7 empty] | 2.2.1.1 | (19,219 realigned from 2.2.2.1 to 3.2.3.2 - MTR recommendation)
| 21 | 2.2.2.2: Support CFUGs and BZ CFUGs to develop/revise forest operational plan (GESI aspect is revised/incorporated) | PMU/DNPWC/MITFE |  |  |  |  | 4688 |  | CFUGs | 20 | 7 | 35% |  |  |  |  | 2.2.1.2 | Incorporation of GESI aspects in operational plans will be prioritized. (8,000 realigned from 2.2.2.2 to 3.2.3.2 - MTR recommendation) | Yes; review the natural habitat degradation | Yes; review any access restriction issues in the plan | 1. Yes; ensure meaningful participation of IPs in revision process | No | Explore true collaboration and agreement | Yes | Yes; ensure meaningful participation of Ips | No | Ensure meaningful participation of IPs/ in the consultation process and in decision-making processes with true collaboration and agreement | Yes | 1.Sensitize for inclusive participation during project communication (e.g. regular briefing on GESI perspective) 2. Ensure 50% female participation (Representation of women, dalits, ethnic and indigenous peoples) with meaningful participation in decision making process | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
[8 empty] | 4688 |  |  | 20 | 7 | 35% |  |  | 0 | 0
Output 2.2.3: Strategic framework for corridor management developed and management plans prepared or revised for all seven TAL corridors / protected forests | 22 | 2.2.3.1: Develop a gender and inclusion responsive guideline (GIRD) to prepare management plans of PF/Corridors | PMU/DNPWC/MITFE |  |  |  |  | 7500 |  | Guidelines | 1 | 1 | 100% |  |  |  |  | 2.2.3.1 | Cost includes service providers' cost to prepare GIRD
| 23 | 2.2.3.2: Support to revise PF / Corridor Management Plans through a participatory process | PMU/DNPWC/MITFE |  |  |  |  | 12500 |  | Plans | 1 | 1 | 100% |  |  |  |  | 2.2.3.2 | Cost includes service providers' cost to prepare plan
| 24 | 2.2.3.3: Field program implementation support & coordination | MOFE/DOFSC/DNPWC/MITFE |  |  |  |  | 9938 |  | Months | 12 | 12 | 100% |  |  |  |  | 2.2.3.3 | Package includes cost for project staff's travel and DSA to support grantee partners in activity implementation and coordination. Along with monitoring cost to grantee partners | No | No | No | No | No | No | No | No | No | Yes | 1.Sensitize for inclusive participation during project communication (e.g. regular briefing on GESI perspective) 2. Ensure 50% female participation (Representation of women, dalits, ethnic and indigenous peoples) with meaningful participation in decision making process | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
[8 empty] | 29938 |  |  | 14 | 14 | 100% | 76.43% | 66.88% | 0 | 0
COMPONENT 3: Forest and human-wildlife conflict management for improved conservation of targeted protected area buffer zones and corridors in the Terai Arc Landscape | [7 empty] | 1079775 | [7 empty] | 0 | 0 | COMPONENT 3: Forest and HWC management for improved conservation of targeted PA buffer zones and corridors in the TAL |  | COMPONENT 3: Forest and human-wildlife conflict management for improved conservation of targeted protected area buffer zones and corridors in the Terai Arc Landscape
Outcome 3.1: Strengthen livelihoods and biodiversity conservation through Sustainable forest management practices |  |  |  | Q1 | Q2 | Q3 | Q4 | 585665 | [7 empty] | 0 | 0 | Outcome 3.1: Strengthen livelihoods and biodiversity conservation through Sustainable forest management practices |  | Outcome 3.1: Strengthen livelihoods and biodiversity conservation through Sustainable forest management practices
Output 3.1.1: Training and tools to local government on SFM |  | 3.1.1.1: Prepare Sustainable Forest Management Training (SFM) Manual incorporating GESI | MOFE/DOFSC/DNPWC/MITFE |  |  |  |  | $- |  | Manaul | [7 empty] | 3.1.1.1
Outcome 1.1: Improved inter-sectoral coordination from Federal, State to Local level for sustainable forest management and integrated landscape management |  |  |  | Q1 | Q2 | Q3 | Q4 | 60723 | [7 empty] | 0 | 0 | Outcome 1.1: Improved inter-sectoral coordination from Federal, State to Local level |  | Outcome 1.1: Improved inter-sectoral coordination from Federal, State to Local level
| 25 | 3.1.1.2: Provide "Training of Trainers" (TOT) to Division Forest Offices staff based on SFM Training Manual | PMU/DNPWC/MITFE |  |  |  |  | 11250 |  | No of training | 2 | 0 | 0% |  |  |  |  | 3.1.1.2 | Training cost- Lumbini province, Sudurpaschim Province | No | No | No | No | No | No | No | No | No | Yes | 1. Ensure GESI component related with the conservation in the manual 2. Ensure participatory training methods in the manual 3. Ensure GESI pre-test, post-test questionnaire as a part of manual | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
|  | 3.1.1.3 Establish Forest Management Information system (FMIS) including forest fire management | MOFE/DOFSC/DNPWC/MITFE | [6 empty] | Support Package | [7 empty] | 3.1.1.3 | 21,687 realigned from 3.1.1.3 to 3.1.1.5 - MTR recommendation
|  | 3.1.1.4: Support the State Forest Directorate fire reporting system | MOFE/DOFSC/DNPWC/MITFE |  |  |  |  | $- | [9 empty] | 3.1.1.4 | 25,000 realigned from 3.1.1.4 to 3.1.1.5 - MTR recommendation
| 26 | 3.1.1.5: Support forest fire management through innovative tools and techniques such as leaf litter collection and composting (within targeted sites identified in component 2) | MOFE/DOFSC/DNPWC/MITFE |  |  |  |  | 31250 |  | support | 4 | 4 | 100% |  |  |  |  | 3.1.1.5 | Sites or CFUGs identified as most vulnerable to forest fire in project sites will be supported with forest fire management tools | Yes | No | Yes | No | Explore any collaboration and agreement with Ips for effective tools | Yes | Yes; ensure meaningful participation of IPs | Yes | 1. Ensure meaningful participation of women's, dalit and IPs groups | Yes | 1. Ensure 50% female beneficiaries receiving tools | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
| 27 | 3.1.1.6 Provide multi-year support for nursery to Division forest offices (within targeted sites identified in component 2) including restoration activities in BZ and corridor | MOFE/DOFSC/DNPWC/MITFE |  |  |  |  | 70313 |  | nursery | 6 | 9 | 100% |  |  |  |  | 3.1.1.6 | DFOs will manage nursery including small infrastructures and produce single/ multi-year seedlings to make available to local communities in forest restoration sites, private and agro-forestry promotion sites. 2 lakh seedling production+30 hac restoration (Restoration of public land and community forest through natural regeneration protection and plantation) | Yes; ensure selection of quality species suitable for wildlife and biodiversity | No | Yes | Yes | Ensure invasive species are not promoted, and IPs are consulted | Yes | Yes | No | 1. Ensure meaningful participation of women's, dalit and IPs groups | Yes | Ensure 60% female, 20% IPs and 5% dalits as beneficiaries | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
[8 empty] | 112813 |  |  | 12 | 13 | 66.67% |  |  | 0 | 0
Output 3.1.2: Technical support to CFUGs, BZCFUGs and land holders for forest management | 28 | 3.1.2.1: Provide training to CFUGs and BZ CFUGs for forest management implementation (including applied SFM, restoration technique - lined with 3.1.1 | PMU/DNPWC/MITFE |  |  |  |  | 12500 |  | training | 8 | 12 | 100% |  |  |  |  | 3.1.2.1 | Training to CFUGs on sustainable forest management and restoration, ensuring equitable access to all members and gender dimensions in training opportunities | No | No | No | No | No | No | No | No | 1. Ensure meaningful participation of women's, dalit and IPs groups | Yes | 1.Sensitize for inclusive participation during project communication (e.g. regular briefing on GESI perspective) 2. Ensure 50% female participation (Representation of women, dalits, ethnic and indigenous peoples) | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
|  | 3.1.2.2: Conduct exchange visits for targeted BZ CFUG members (learning from successful UCs on fund mobilization and HWC management) | PMU |  |  |  |  | $- |  | visits | 0 | [6 empty] | 3.1.2.2
| 29 | 3.1.2.3: Support BZUCs annual meetings for Bardia and Banke NP Buffer Zones (northern side) | PMU/DNPWC/MITFE |  |  |  |  | 3281 |  | BZUCs annual meetings supported | 7 | 4 | 57.14% |  |  |  |  | 3.1.2.3 | Logistics support for annual meetings of BZUCs | No | No | No | No | No | No | No | No | No | Yes | 1.Sensitize for inclusive participation during project communication (e.g. regular briefing on GESI perspective) 2. Ensure 50% female participation (Representation of women, dalits, ethnic and indigenous peoples) | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
| 30 | 3.1.2.4: Provide coaching on "Governance and Financial management" for CFUGs of corridors and PA Buffer zones | PMU/DNPWC/MITFE |  |  |  |  | 10156 |  | coaching sessions | 65 | 40 | 61.54% |  |  |  |  | 3.1.2.4 | Training costs for CFUGs and BZUCs, ensuring equitable access to all members and gender dimensions in training opportunities | No | No | No | No | No | No | No | No | No | Yes | 1.Sensitize for inclusive participation during project communication (e.g. regular briefing on GESI perspective) 2. Ensure 50% female participation (Representation of women, dalits, ethnic and indigenous peoples) | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
|  | 3.1.2.5: Provide support private forest development (providing seedling, irrigation, fencing) | MOFE/DOFSC/DNPWC/MITFE |  |  |  |  | $- |  | Ha | [7 empty] | 3.1.2.5 | (20,000 realigned from 3.1.2.5 to 3.1.1.6; 80,000 realigned from 3.1.2.5 to 3.1.3.2 47,739 realigned from 3.1.2.5 to 3.1.3.3; 10,000 realigned 3.1.2.5 from to 3.2.3.2) - MTR recommendation
| 31 | 3.1.2.6: Support to register private forest | PMU/DNPWC/MITFE |  |  |  |  | 625 |  | No of forest | 2 | 23 | 100% |  |  |  |  | 3.1.2.6 | Administration cost support to private forest owners in registration process ( 40,000 realigned from 3.1.2.6 to 3.1.3.3) - MTR recommendation | No | No | Yes | Yes | 1. Promote indigenous species plantation 2. Discourage use of pesticides | No | No | No | No | Yes | Prioritize 50% women's for their ownership in registration | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
[8 empty] | 26562 |  |  | 82 | 79 | 79.67% |  |  | 0 | 0
Output 3.1.3: Forests and associated habitat in priority buffer zones and corridors managed sustainably |  | 3.1.3.1: Create revolving fund to implement forest operational plans in project targeted corridors | PMU/DNPWC/MITFE |  |  |  |  | $- |  | Support Package | [7 empty] | 3.1.3.1 | ( 6,250 realigned from 3.1.3.1 to 3.1.3.2) - MTR recommendation
| 32 | 3.1.3.2: Provide financial and technical support to improve livestock management (AI, fodder plant support, feeding trough, vet support, stall improvement), Including Agroforestry promotion activities | PMU/DNPWC/MITFE |  |  |  |  | 173633 |  | Households | 650 | 1943 | 100% |  |  |  |  | 3.1.3.2 | To reduce pressure on wildlife habitat, alternative packages including cement trough, fodder seedlings will be supported to households who are more dependent on forest resources in nearby corridor forest/ buffer zone forest Agroforestry promotion activities includes fruits and tree plantation with irrigation support in 150 hac (realigned from 3.1.2.5: 39,062) - MTR recommendation | Yes | No | Yes | Yes | Ensure proper consultation and meaningful participation of Ips | Yes | Yes | Yes | 1. Prepare LRP first and then support | Yes | 1. Ensure 60% female, 20% Ips, and 10% dalit beneficiaries for livestock management support | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
| 33 | 3.1.3.3: Provide financial and technical support for management of grassland and wetland in project targeted area | PMU/DNPWC/MITFE |  |  |  |  | 221875 |  | Support Package | 11 | 11 | 100% |  |  |  |  | 3.1.3.3 | Package includes Habitat improvement in BaNP and its buffer zone, BNP and its buffer zone, Kamdi corridors and Karnali corridors (255 Ha. grassland and 18 wetlands) including technical backstopping and monitoring cost to grantee partners. Park offices will prioritize implementation sites in core area of national park and buffer zone realigned from 3.1.3.1: 124,842 - MTR recommendation | Yes | Yes | Yes | No | Conduct screening, categorization | Yes | Yes | On the basis of FPIC | 1. Ensure meaningful participation of IPs, Dalit and women's group 2. Develop LRP as needed | Yes | 1. Ensure 60% female, 20% Ips, and 10% dalit beneficiaries (if LRP) | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
| 34 | 3.1.3.4: Provide financial and technical support for river bank protection in project targeted area | PMU/DNPWC/MITFE |  |  |  |  | 22656 |  | Support Package | 2 | 1 | 50% |  |  |  |  | 3.1.3.4 | Pacckage includes river training works, biological measures to be appliced to control river cutting, construction materials purchase and transporation. Area (forest and agriculture land to be protected/restored after river bank protection to be calculated during details sites identification and implementation plan preparation. | Yes | Yes | Yes | No | 1. Ensure wildlife friendly structure | Yes | Yes | Yes | 1. Consent from IPs | Yes | 1.Sensitize for inclusive participation during project communication (e.g. regular briefing on GESI perspective) 2. Ensure 50% female participation (Representation of women, dalits, ethnic and indigenous peoples) | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
| 35 | 3.1.3.5: Safeguard plan implementation | PMU |  |  |  |  | 23438 |  | plan/s | 4 | 6 | 100% |  |  |  |  | 3.1.3.5 | Package include capacity building training on ESS, GESI, GRM, hoarding board/Pictorial content development on ESS awareness, support women/IPs/dalit group with LIP, exposure visit to CFUG/BZUC members, mitigative safeguard to support Project Affected Peoples | Yes | Yes | Yes | Yes | Yes, Ensure Environmental and Social Safeugards | Yes | Yes | Yes | Yes | Yes | Ensure 60% women, 25% IPs and 10% dalit beneficiaries | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
|  | 3.1.3.6: Provide financial and technical support to small scale green enterprises in project targeted area | PMU/DNPWC/MITFE |  |  |  |  | $- |  | enterprise | [7 empty] | 3.1.3.6 | (93,548 realigned from 3.1.3.6 to 3.2.3.2 ) - MTR recommendation
| 36 | 3.1.3.7: Provide financial and technical support to develop business plan | PMU |  |  |  |  | 4688 |  | plan/s | 6 | 1 | 16.67% |  |  |  |  | 3.1.3.7 | Technical support with expert members on green enterprises business plan preparation, ensuring gender balance and equitable access to women-led enterprises in training in business planning | No | No | Yes | No | Ensure meaningful participation of Ips, dalit and womens group | Yes | Yes | Yes | 1. Involve IPs in business plan preparation | Yes | Ensure at least 60% female, 25% Ips and 10% dalit beneficiaries for project related loans for community level enterprise and livelihood support | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
[8 empty] | 446290 |  |  | 673 | 1962 | 73.33% | 73.78% |  | 0 | 0
Outcome 3.2: Improved management of the human-wildlife conflict |  |  |  | Q1 | Q2 | Q3 | Q4 | 428438 | [7 empty] | 0 | 0 | Outcome 3.2: Improved management of the human-wildlife conflict |  | Outcome 3.2: Improved management of the human-wildlife conflict
Output 3.2.1: Pilot method to reduce the wildlife accident in priority sites |  | 3.2.1.1: Conduct study on the wildlife traffic accident issue | PMU |  |  |  |  | $- | [9 empty] | 3.2.1.1
|  | 3.2.1.2: Install tools/facilities to pilot measures to reduce accidents | MOFE/DOFSC/DNPWC/MITFE |  |  |  |  | $- |  | Support Package | [7 empty] | 3.2.1.2
|  | 3.2.1.3: Support in operation and monitoring of wildlife related traffic accidents in highway | MOFE/DOFSC/DNPWC/MITFE |  |  |  |  | $- |  | monitoring | [7 empty] | 3.2.1.3
|  | 3.2.1.4: Support to erect fence in both side of Sikta irrigation canal | MOFE/DOFSC/DNPWC/MITFE |  |  |  |  | $- |  | Support Package | [7 empty] | 3.2.1.4
[8 empty] | 0 |  |  | 0 | 0 |  |  |  | 0 | 0
Output 3.2.2: Training and facilities for human wildlife conflict response | 37 | 3.2.2.1: Prepare species-specific guidelines for HWC management | MOFE/DOFSC/DNPWC/MITFE/PMU |  |  |  |  | 3906 |  | guideline | 1 | 0 | 0% |  |  |  |  | 3.2.2.1 | Focus will be tiger as number of tiger-human incidents increased in project site | Yes | No | Yes | No | 1. The guidelines should involve natural habitat, IPs and access restriction issue | Yes | Yes | Yes | Ensure meaningful participation of Ips | Yes | Ensure 50% female participation along with Ips and dalits in the consultation meetings | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
| 38 | 3.2.2.2: Pictorial manual on Wildlife identification and behavior in Nepali and local dialects | MOFE/DOFSC/DNPWC/MITFE/PMU |  |  |  |  | 3906 |  | manual | 1 | 1 | 100% |  |  |  |  | 3.2.2.2 | Manual preparation and printing | No | No | No | No | No | No | No | No | No | Yes | Ensure GESI friendly dialect | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
| 39 | 3.2.2.3: Conduct training on identification and behavior of wild animals to Divisional forest office staff | MOFE/DOFSC/DNPWC/MITFE/PMU |  |  |  |  | 6563 |  | training | 4 | 3 | 75% |  |  |  |  | 3.2.2.3 | Training package development with curriculam and conduct training to division forest staff | No | No | No | No | No | No | No | No | No | Yes | 1.Sensitize for inclusive participation during project communication (e.g. regular briefing on GESI perspective) 2. Ensure at least 30% female participation (Representation of women, dalits, ethnic and indigenous peoples) | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
| 40 | 3.2.2.4: Support Wildlife Rescue center | MOFE/DOFSC/DNPWC/MITFE |  |  |  |  | 40625 |  | Centre | 2 | 2 | 100% |  |  |  |  | 3.2.2.4 | Strengthening of wildlife rescue center in BNP and BaNP with equipments and facilities improvement | No | No | Yes | No | Ensure awareness among nearby communities | Yes | Yes | Yes; on the basis of FPIC | Prepare plan on the basis of consultation with IPs, Dalits and women's group | Yes | 1. Sensitize for inclusive participation during project communication (e.g. regular briefing on GESI perspective) 2. Ensure 50% female participation (Representation of women, dalits, ethnic and indigenous peoples) | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
| 41 | 3.2.2.5: Support wildlife rescue and handling equipment and training | MOFE/DOFSC/DNPWC/MITFE |  |  |  |  | 4688 |  | training | 3 | 3 | 100% |  |  |  |  | 3.2.2.5 | Activities includes rescue of wildlife, equipments/tools purchase to handle wildlife and training conduction (if needed) | No | No | No | No | No | No | No | No | No | Yes | 1. Ensure 50% female participants in the training 2. Manual should include GESI mainstreaming methodologies | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
[8 empty] | 59688 |  |  | 11 | 9 | 75% |  |  | 0 | 0
Output 3.2.3: Community based HWC mitigate and preventive action implemented | 42 | 3.2.3.1: Conduct workshop on preventive and curative measures for HWC | MOFE/DOFSC/DNPWC/MITFE |  |  |  |  | 3906 |  | workshop | 1 | 0 | 0% |  |  |  |  | 3.2.3.1 | Workshop with relevent stakeholders on preventive and curative measures taking account the knowledge, needs and special considerations of vulnersable groups (including woman) in developing and promoting measures | No | No | No | No | No | No | Yes; participate IPs organizations | No | Ensure meaningful participation of Ips | Yes | 1.Sensitize for inclusive participation during project communication (e.g. regular briefing on GESI perspective) 2. Ensure 50% female in the workshop (women, dalits, indigenous people) where applicable 3. GESI concept and mainstreaming methodologies are incorporated in the presentation | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
| 43 | 3.2.3.2: Implement measures for HWC based on prepared plans (mentha plantation, biological/virtual fencing) | PMU/DNPWC/MITFE |  |  |  |  | 329688 |  | Plans | 12 | 12 | 100% |  |  |  |  | 3.2.3.2 | Package includes wildlife deterent plants plantation, green fences, predator proof pen fence, mesh wire /electric fencing and its maintanance, - as per community need and nature of HWC. The detials (sites/interventions) to be finalized based on participatory assessment report followed by community consultation Realigned from3.1.3.6 : 156,062 - MTR recommendation | Yes | Yes | Yes | Yes | Ensure no invasive species are used and meaningful consultation with IPs | Yes | Yes | Yes | 1. Meaningful participation of IPs, Womens' Group and Dalits | Yes | 1.Sensitize for inclusive participation during project communication (e.g. regular briefing on GESI perspective) 2. Ensure 60% female, 25% Ips and 10% dalit participation during project -related loans for community level enterprise and livelihood support | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
| 44 | 3.2.3.3: Support to establish community-based insurance (crop, livestock) scheme | PMU/DNPWC/MITFE |  |  |  |  | 31250 |  | Support package | 2 | 0 | 0% |  |  |  |  | 3.2.3.3 | Package includes franction of insurance premium payments through rovolving fund establishment | No | No | No | No | No | Yes | Yes | No | 1. Meaningful participation of IPs, Womens' Group and Dalits | Yes | Prioritize Dalit, women's group, and IPs in decision making | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
| 45 | 3.2.3.4: Implement community-based reporting system of HWC incidents | MOFE/DOFSC/DNPWC/MITFE |  |  |  |  | 3906 |  | system | 1 | 1 | 100% |  |  |  |  | 3.2.3.4 | Prepare reporting system and implement with stakeholders support | No | No | No | No | No | Yes | Yes | No | 1. Meaningful participation of IPs, Womens' Group and Dalits | Yes | Prioritize Dalit, women's group, and IPs in decision making | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
[8 empty] | 368750 |  |  | 16 | 13 | 50% |  |  | 0 | 0
Outcome 3.3: Enhanced capacities of government agencies and community in curbing illegal wildlife crime |  |  |  | Q1 | Q2 | Q3 | Q4 | 65672 | [7 empty] | 0 | 0 | Outcome 3.3: Enhanced capacities of government agencies and community in curbing illegal wildlife crime |  | Outcome 3.3: Enhanced capacities of government agencies and community in curbing illegal wildlife crime
Output 3.3.1: Community Based Anti poaching Units functional in priority areas | 46 | 3.3.1.1: Provide support for field gears to CBAPU members | PMU/DNPWC/MITFE |  |  |  |  | 19531 |  | CBAPU/s | 100 | 100 | 100% |  |  |  |  | 3.3.1.1 | Basic safety and health equipments to community youth volunteer - CBAPU like torch light, field gears e.g. cap, rain coat/jacket. Cost includes 5 sesitization/ capacity development workshop on biodiversity conservation and environmental and social safeguard and field gears to 100 CBAPUs (also includes capacity building through exposer visits and training)) | No | No | No | No | No | No | No | No | No | Yes | Ensure Gender friendly field gears | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
| 47 | 3.3.1.2: Provide technical and financial support for skill based training to CBAPU members | PMU |  |  |  |  | 28125 |  | No of training | 3 | 13 | 100% |  |  |  |  | 3.3.1.2 | Training to CBAPU members | No | No | No | No | No | No | No | No | No | Yes | 1. Ensure 50% female participants in the training 2. Manual should include GESI mainstreaming methodologies | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
|  | 3.3.1.3: Establish revolving fund to initiate green enterprise for CBAPUs member (link to above activities) | PMU/DNPWC/MITFE |  |  |  |  | $- |  | Support Package | [7 empty] | 3.3.1.3 | (32,021 realigned from 3.3.1.3 to 3.3.1.2 - MTR recommendation
[8 empty] | 47656 |  |  | 103 | 113 | 100% |  |  | 0 | 0
Output 3.3.2: Training and operation support to Park staff, rangers on wildlife crime management |  | 3.3.2.1: Update training manual on illegal wildlife crime scene management | MOFE/DOFSC/DNPWC/MITFE/PMU |  |  |  |  | $- |  | Manual | [7 empty] | 3.3.2.1
| 48 | 3.3.2.2: Conduct training to investigation officers level on Illegal wildlife crime scene management | MOFE/DOFSC/DNPWC/MITFE |  |  |  |  | 8672 |  | training | 3 | 0 | 0% |  |  |  |  | 3.3.2.2 | Training package developed and training conducted | No | No | No | No | Ensure WWF’s Support for Enforcement and Rangers in the training manual | No | No | No | No | Yes | 1.Follow WWF guidance on armed, professional poachers vs community members engaged in livelihood activities 2. Ensure at least 50% female participation (Representation of women, dalits, ethnic and indigenous peoples) | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
| 49 | 3.3.2.3: Support Transboundary coordination at local level | MOFE/DOFSC/DNPWC/MITFE |  |  |  |  | 6250 |  | meeting | 4 | 1 | 25% |  |  |  |  | 3.3.2.3 | 2 transboundary meetings between India and Nepal officials on ILM themes (species protection, HWC management etc) | No | No | No | No | No | No | No | No | No | Yes | 1.Sensitize for inclusive participation during project communication (e.g. regular briefing on GESI perspective) 2. Ensure at least 33% female participation (Representation of women, dalits, ethnic and indigenous peoples) | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
| 50 | 3.3.2.4: Field program implementation support & coordination | PMU/DNPWC/MITFE |  |  |  |  | 3094 |  | Month | 12 | 12 | 100% |  |  |  |  | 3.3.2.4 | Package includes cost (for 12 months) for project staff's travela nd DSA to support gratee partners technically in activity implementation and necessary coordination. | No | No | No | No | No | No | No | No | No | Yes | 1.Sensitize for inclusive participation during project communication (e.g. regular briefing on GESI perspective) 2. Ensure at least 33% female participation (Representation of women, dalits, ethnic and indigenous peoples) | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
[8 empty] | 18016 |  |  | 19 | 13 | 41.67% | 65% | 68.67% | 0 | 0
COMPONENT 4: Monitoring and evaluation (M&E), knowledge management (KM), and regional coordination | [7 empty] | 227714 | [7 empty] | 0 | 0 | COMPONENT 4: Monitoring and evaluation (M&E), knowledge management (KM), and regional coordination |  | COMPONENT 4: Monitoring and evaluation (M&E), knowledge management (KM), and regional coordination
Outcome 4.1: Improved coordination and dialogue on integrated landscape management from the local to national level |  |  |  | Q1 | Q2 | Q3 | Q4 | 140234 | [7 empty] | 0 | 0 | Outcome 4.1: Improved coordination and dialogue on integrated landscape management from the local to national level |  | Outcome 4.1: Improved coordination and dialogue on integrated landscape management from the local to national level
Output 4.1.1: Information on ILM importance shared among key stakeholders | 51 | 4.1.1.1: Organize monthly dialogue through "Jaibik Chautari" (Biodiversity Platform) at field | MOFE/DOFSC/DNPWC/MITFE/PMU |  |  |  |  | 14844 |  | Dialogue | 41 | 25 | 60.98% |  |  |  |  | 4.1.1.1 | A dialogue will be organized in coordination with local CSOs and government bodies e.g. NBCC, WCCB, TAL working group and conduct thematic discussion e.g. how to manage forest fire in fire season, HWC management and produce media reports/programs. During the implementation, number of stakeholders will be identified and documented to better align with result framework. Includes one KAP survey to understand changes in Knowledge, Attitude and Practice as recommended by MTR (30,000 realigned from 4.1.1.1 to 4.1.2.1) - MTR recommendation | No | No | No | No | No | No | Yes; ensure representation of IPs organization | No | 1. Ensure quality and inclusive representation | Yes | 1.Sensitize for inclusive participation during project communication (e.g. regular briefing on GESI perspective) 2. Ensure 50% female participation (Representation of women, dalits, ethnic and indigenous peoples) | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
| 52 | 4.1.1.2: Organize annual technical thematic discussion session at center | MOFE/DOFSC/DNPWC/MITFE/PMU |  |  |  |  | 5469 |  | meeting | 2 | 0 | 0% |  |  |  |  | 4.1.1.2 | Annual discussions among key stakeholders on ILM e.g. wildlife rescue | No | No | No | No | No | No | No | No | No | yes | 1.Sensitize for inclusive participation during project communication (e.g. regular briefing on GESI perspective) 2. Ensure 50% female participation (Representation of women, dalits, ethnic and indigenous peoples) | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
| 53 | 4.1.1.3: Establish and maintain online Landscape Knowledge Learning Platform (including project website) | PMU |  |  |  |  | 781 |  | platform | 1 | 0 | 0% |  |  |  |  | 4.1.1.3 | Project website maintained and enhanced (9000 realigned from 4.1.1.3 to 4.1.2.1) - MTR recommendation | No | No | No | No | No | No | No | No | No | Yes | Prioritize women's group, dalits, IPs in the learning platform | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
[8 empty] | 21094 |  |  | 44 | 25 | 20.33% |  |  | 0 | 0
Output 4.1.2: Mass awareness products on biodiversity conservation and integrated landscape management | 54 | 4.1.2.1: Provide technical and financial support to green/eco-clubs formation and its operation | PMU/DNPWC/MITFE |  |  |  |  | 62500 |  | No of eco-clubs supported | 32 | 44 | 100% |  |  |  |  | 4.1.2.1 | Capacitate eco-clubs to be part of biodiversity conservation at local level through talent competition, awareness campaign (e.g. mass awareness on waste management/plastic pollution control), small infrastructure like e.g.cycle stand, eco-garden, bio-fencing) | No | No | No | No | No | No | No | No | No | Yes | 1. Ensure 50% female in the Eco-club 2. Gender friendly planning and implementation | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
| 55 | 4.1.2.2: Support annual meetings of green/eco-clubs network at district level | PMU |  |  |  |  | 18750 |  | No of meetings | 12 | 7 | 58.33% |  |  |  |  | 4.1.2.2 | Orientation, exposure visits and capacity buidling training/events and meetings with eco-club networks, eco-teachers | No | No | Yes | No | Ensure childrens from Ips in the meeting | No | No | No | No | Yes | Ensure 50% female, and representation of Ips, dalits in the eco-club | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
| 56 | 4.1.2.3: Support special conservation events at local level | MOFE/DOFSC/DNPWC/MITFE |  |  |  |  | 16406 |  | event | 10 | 11 | 100% |  |  |  |  | 4.1.2.3 | Technical support to government entities to organize conservation events with multi-stakeholder (Ips, LCs) participation | No | No | No | No | No | No | Yes | No | 1. Ensure meaningful participation of IPs in celebrating events | Yes | 1.Sensitize for inclusive participation event celebration (e.g. regular briefing on GESI perspective) 2. Ensure at least 50% female participation (Representation of women, dalits, ethnic and indigenous peoples) | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
| 57 | 4.1.2.4: Sensitize media (print and TV) on integrated landscape management | PMU |  |  |  |  | 5859 |  | media | 5 | 5 | 100% |  |  |  |  | 4.1.2.4 | Organize media visits to sensitize about ILM, ensuring gender and social inclusion (GESI) dimensions during implementation | No | No | No | No | No | No | No | No | No | Yes | 1. GESI sensitive information 2. Ensure proper capacity building of the media to disseminate information on the importance of GESI integration in conservation. | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
| 58 | 4.1.2.5: Support radio program (local dialects) on ILM | PMU |  |  |  |  | 15625 |  | radio | 20 | 12 | 60% |  |  |  |  | 4.1.2.5 | Audio-programs development to disseminate information about ILM, ensuring gender and social inclusion (GESI) dimensions during implementation | No | No | No | No | No | No | No | No | No | Yes | Initiate radio program with success stories of women's group, dalits, IPs | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
[8 empty] | 119140 |  |  | 79 | 79 | 83.67% | 59.91% |  | 0 | 0
Outcome 4.2: Project monitoring system operates, systematically provides information on progress, and informs adaptive management to ensure results |  |  |  | Q1 | Q2 | Q3 | Q4 | 45339 | [7 empty] | 0 | 0 | Outcome 4.2: Project monitoring system operates, information on progress, and informs adaptive management to ensure results |  | Outcome 4.2: Project monitoring system operates, systematically provides information on progress, and informs adaptive management to ensure results
Output 4.2.1: Participatory planning and M&E system |  | 4.2.1.1 : Organize project inception workshop at Kathmandu and field level | [5 empty] | $- | [9 empty] | 4.2.1.1
| 59 | 4.2.1.2: PAC/PEC planning review workshop (Central and Field) | PMU |  |  |  |  | 2344 |  | Meeting | 5 | 3 | 60% |  |  |  |  | 4.2.1.2 | Meetings as per prodoc | No | No | No | No | No | No | No | No | No | Yes | 1.Sensitize for inclusive participation during project communication (e.g. regular briefing on GESI perspective) 2. Ensure 33% female participation (Representation of women, dalits, ethnic and indigenous peoples) | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
| 60 | 4.2.1.3: Conduct periodic (trimester) workplan review and planning sessions | PMU/DNPWC/MITFE |  |  |  |  | 13281 |  | Workshop | 7 | 12 | 100% |  |  |  |  | 4.2.1.3 | Workshops to review project progresses/prepare quarterly and annual plan with project team and also with project stakeholders | No | No | No | No | No | No | No | No | No | Yes | 1.Sensitize for inclusive participation during project communication (e.g. regular briefing on GESI perspective) 2. Ensure 33% female participation (Representation of women, dalits, ethnic and indigenous peoples) | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
| 61 | 4.2.1.4: Conduct periodic and joint monitoring visits | PMU/DNPWC/MITFE |  |  |  |  | 9375 |  | Visits | 6 | 6 | 100% |  |  |  |  | 4.2.1.4 | Visits/travel focused on project interventions (outcomes/outputs) | No | No | No | No | No | No | Yes; Esure meaningful participation of IPs representative | No | No | Yes | 1.Sensitize for inclusive participation during project communication (e.g. regular briefing on GESI perspective) 2. Ensure 33% female participation (Representation of women, dalits, ethnic and indigenous peoples) | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
| 62 | 4.2.1.5: Conduct Safeguard Monitoring visits | PMU |  |  |  |  | 2344 |  | Visits | 2 | 1 | 50% |  |  |  |  | 4.2.1.5 | Multi-stakeholders including Ips, LCs, local goverments, project staff, MoFE officials - visit | No | No | No | No | No | No | Yes; Esure meaningful participation of IPs representative | No | No | Yes | 1.Sensitize for inclusive participation during project communication (e.g. regular briefing on GESI perspective) 2. Ensure 33% female participation (Representation of women, dalits, ethnic and indigenous peoples) | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
| 63 | 4.2.1.6: Conduct training on "participatory monitoring and evaluation" to CFUGs and relevant sub-grantees | PMU/DNPWC/MITFE |  |  |  |  | 12656 |  | Training | 6 | 7 | 100% |  |  |  |  | 4.2.1.6 | Training cost (e.g. resource persons, training materials, participant travel, logistics) | No | No | No | No | No | No | Yes; Esure meaningful participation of IPs representative | No | No | Yes | 1.Sensitize for inclusive participation during project communication (e.g. regular briefing on GESI perspective) 2. Ensure 50% female participation (Representation of women, dalits, ethnic and indigenous peoples) | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
| 64 | 4.2.1.7: Capacity building/training of PSU staff (on project management - WWF network standards, report writing and GESI and safeguard) | PMU |  |  |  |  | 5339 |  | Event | 1 | 1 | 100% |  |  |  |  | 4.2.1.7 | Event as training package including site visit (exposure) in integrated landscape management practices in other landscapes | No | No | No | No | No | No | No | No | No | Yes | 1.Sensitize for inclusive participation during project communication (e.g. regular briefing on GESI perspective) 2. Ensure 33% female participation (Representation of women, dalits, ethnic and indigenous peoples) | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
|  | 4.2.1.8: Organize Project Mid-term review workshops with all key stakeholders | [5 empty] | $- |  | Workshop | [7 empty] | 4.2.1.8 | organize a workshop with project stakeholers as requested by Mid-term review team (3,713 realigned from 4.2.1.8 to 4.2.1.7; MTR already completed)
|  | 4.2.1.9: Conduct Project Evaluations (Mid-term and terminal evaluation - GEF/SWC) | PMU |  |  |  |  | $- |  | No of evaluation supported | 0 | [6 empty] | 4.2.1.9 | WWF - Technical assistance part
[8 empty] | 45339 |  |  | 27 | 30 | 85% | 85% |  | 0 | 0
Outcome 4.3: Project lessons shared |  |  |  | Q1 | Q2 | Q3 | Q4 | 42141 | [7 empty] | 0 | 0 | Outcome 4.3: Project lessons shared |  | Outcome 4.3: Project lessons shared
Output 4.3.1: Project lessons captured and disseminated to project stakeholders and to other projects and partners |  | 4.3.1.1: Documentation on Traditional Knowledge associated to natural resources | PMU | [14 empty] | 4.3.1.1
| 65 | 4.3.1.2: Prepare success stories and videos of the project | PMU/DNPWC/MITFE |  |  |  |  | 11719 |  | No of stories/videos | 5 | 6 | 100% |  |  |  |  | 4.3.1.2 | Prepare videos and stories of the project highlighting project interventions, ensure the GESI dimensions as part of lessons and stories | No | No | Reflect Ips issues and mitigation measures taken into success stories | yes; reflect on impacts of discouraging invasive species | Reflect impact of project intervention on IP, dalit and womens | Yes; take consent before story collection and disclose before dissemianation | No | No | No | yes | Ensure proper capacity building of the media to disseminate information on the importance of GESI integration in conservation | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
| 66 | 4.3.1.3: Print case studies and periodic project reports | PMU |  |  |  |  | 7656 |  | Reports | 2 | 2 | 100% |  |  |  |  | 4.3.1.3 | Cost includes any policy documents review, design and printing support to relevent government organizations | No | No | No | No | No | No | No | No | No | yes | Ensure proper capacity building of the media to disseminate information on the importance of GESI integration in conservation | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
| 67 | 4.3.1.4: Provide financial support to participate in national/international scientific forum for field staff | PMU |  |  |  |  | 9766 |  | Persons supported | 5 | 0 | 0% |  |  |  |  | 4.3.1.4 | Provide support to participate in international scientific forum for ILaM project staff | No | No | No | No | No | No | No | No | No | yes | Ensure 33% female participation (Representation of women, dalits, ethnic and indigenous peoples) | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
|  | 4.3.1.5: Provide financial support to publish journal articles | PMU | [6 empty] | Articles | [7 empty] | 4.3.1.5 | Provide support to prepare and publish a journal article in ILaM project theme | No | No | No | No | No | No | No | No | No | yes | Ensure disseminate information on the importance of GESI integration in conservation | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
| 68 | 4.3.1.6: Field program implementation support & coordination | PMU/DNPWC/MITFE |  |  |  |  | 13000 |  | Month | 12 | 12 | 100% |  |  |  |  | 4.3.1.6 | Package includes Staff travel and DSA, coordination meeting with gov. partners, gov staffs travel and communication support, coordination meeting with IPs and local communities, travel cost/transporation and communication support to gov partners for monitoring and technical backstopping | No | No | No | No | No | No | No | No | No | yes | Sensitize for inclusive participation during project communication (e.g. regular briefing on GESI perspective) | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
|  | 4.3.1.7: Organize final project lessons sharing workshop | PMU |  |  |  |  | $- | [9 empty] | 4.3.1.7
[8 empty] | 42141 |  |  | 24 | 20 | 75% | 75% | 71.63% | 0 | 0
B. Project Management Costs | [7 empty] | 290563.08 | [7 empty] | 0 | 0
Office and field running costs |  |  |  | Q1 | Q2 | Q3 | Q4 | 58290.88 | [7 empty] | 0 | 0
Project Management Unit | 5645 | Office running cost- Utility | PMU |  |  |  |  | 4218.75 |  | Month | 12
| 5608 | Office & Equipments Maintenance | PMU |  |  |  |  | 1406.25 |  | Month | 12
| 5607 | Office Insurance (Equipment & Vehicles) | PMU |  |  |  |  | 1328.13 |  | Time | 2
| 5605 | Office Rent | PMU |  |  |  |  | 3906.25 |  | Month | 12
| 5616 | Equipment Running Cost | PMU |  |  |  |  | 843.75 |  | Month | 12
| 5701 | Vehicle Running Costs (Vehicle Repair) | PMU |  |  |  |  | 5625 |  | Month | 12
| 5701 | Vehicle Running Costs (fuel for office purpose) | PMU |  |  |  |  | 7500 |  | Month | 12
| 5625 | Photocopying | PMU |  |  |  |  | 656.25 |  | Package | 1
| 5630 | Postage & Shipping | PMU |  |  |  |  | 937.5 |  | Month | 12
| 5655 | Communications (phone, fax, internet) | PMU |  |  |  |  | 3750 |  | Month | 12
| 5650 | Office Supplies | PMU |  |  |  |  | 6562.5 |  | Month | 12
| 5310 | Field program implementation support coordination (Staffs travel and Inhouse Meeting) including Vehicle Hired | PMU |  |  |  |  | 8911.5 |  | Month | 12
| 5405 | Advertisment/Priniting and Publication | PMU |  |  |  |  | 3906.25 |  | Month | 12
| 5660 | Bank charges | PMU |  |  |  |  | 300 |  | Printing | 5
| 5701 | Field gear for project staff | PMU |  |  |  |  | 2970 |  | Month | 12
| 4.2.1.10 | Annual Financial Audit | PMU |  |  |  |  | 5468.75 |  | Audit | 1
[8 empty] | 58290.88 |  |  | 153 | 0 |  |  |  | 0 | 0
|  | Capital Assets | [5 empty] | 7772.2 | [7 empty] | 0 | 0
| 5820 | Cupboard/File Racks ( for Banke or Kathmandu Office) | PMU |  |  |  |  | 546.88 |  | Set | 1
| 5820 | Laptop (with dock-in set) | PMU |  |  |  |  | 2343.75 |  | No | 2
| 5820 | Data Backup/Hard Drive | PMU |  |  |  |  | 234.38 |  | No | 3
| 5820 | CC Camera for PMU Office | PMU |  |  |  |  | $ - |  | No | 3
| 5820 | TV 65'' for PMU Office (Multi-purpose uses) | PMU |  |  |  |  | $ - |  | Set | 1
| 5820 | Air conditioner (for Banke) | PMU |  |  |  |  | $ - |  | No | 1
| 5820 | Other communication equipments | PMU |  |  |  |  | 780 |  | No | 3
| 5820 | Multi-Function Printers (For Banke) | PMU |  |  |  |  | 781.25 |  | No | 1
| 5820 | Power Backup System (for Banke) | PMU |  |  |  |  | $ - |  | No | 2
| 5820 | Account Software (Activity-wise reporting, AMC etc.) | PMU |  |  |  |  | 195.31 |  | No | 1
| 5820 | Office 365 insallation, Sofware AMC etc | PMU |  |  |  |  | 781.25 |  | Set | 1
| 5820 | IT support | PMU |  |  |  |  | 781.25 |  | times | 1
| 5608 | Office Renovation and partation | PMU |  |  |  |  | 781.25 |  | times | 1
| 5820 | Monitor | PMU |  |  |  |  | 546.88 |  | No | 2
[8 empty] | 7772.2 |  |  | 23 |  |  |  |  | 0 | 0
|  | Personnel | [5 empty] | 224500
GRAND TOTAL (A+B) |  |  |  | YR5 |  |  |  | 1894339.08 | [7 empty] | 0 | 0
|  |  | Carry-over total (unspent funds from previous year) | [10 empty] | % achieved for activities overall | 64.85% | Actual budget for previous project year
Request of funds for Upcoming Project Year
Note on C18: McKeehan, Adrienne: Best practice training on what subject? Best practice on cross-sector landscape and forest planning/management (outcome 1.2)
Note on C25: McKeehan, Adrienne: How is the grant process designed, and who do you invite to submit proposals? Is this process gender-inclusive, and what efforts are made to ensure that it is fair and transparent? PMU: Grantee selection criteria is approved by PEC and published in project website as mandated by approved project document section 2.2 PMU invite proposals through public announcements to all perspective university students PMU follows the approved criteria to make the process fair and transparent In year 2, 10 girls were awarded with thesis grant out of 17
Note on A43: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: New Outcome
Note on M55: Lenovo: 5-Nursery Sites/Seedling Production 4- Restoration Sites
Note on M65: Lenovo: Improved Shed Construction: 626 HHs Fodder Distribution: 1317 HHs
Note on C123: McKeehan, Adrienne: Note that when documenting Traditional Knowledge, you must get the consent of the community/people that the knowledge comes from. This includes making it clear to them how this will be shared and who will have access to it. Very good suggestions, we will fully follow your suggestions while implementing
Note on C140: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Suggest putting these cost under a component Reply: we follow approved project document and placed here

## AWPB Yr 6
Period: Year 6 (July 25 - June 26) (FY 82/83)
| ANNUAL WORK PLAN | [10 empty] | WORK PLAN TRACKING (Tracking at end of project year) | [5 empty] | Additonal Notes
COMPONENT / OUTCOME / OUTPUT | # | ACTIVITIES | Responsible | YEAR X TIMING |  |  |  | BUDGET in USD | x | UNIT DESCRIPTION | TARGET | # UNIT(S) ACHIEVED | % ACHIEVED BY ACTIVITY (# unit(s) achieved / target) | % ACHIEVED BY OUTCOME | % ACHIEVED BY COMPONENT | BUDGET (actual, by Component) |  |  |  | Safeguard issues |  |  |  | Measures | IPPF |  |  |  | GESI intigration
|  |  |  | Q1 | Q2 | Q3 | Q4 | TA | if activity is carried over from previous year | # of | [5 empty] | in Rupee | in USD | Act# | Activity | Policy on natural habitat | Policy on involuntary resettlement | Policy on indigenous people | Policy on pest management | Proposed mitigating activities | FPIC needed or not | IP organization direct collaboration possible or not | Livelihood restoration plan | Action to be taken during implementation | Trigger or not | Action points | Additional information
A. ACTIVITY COSTS | [7 empty] | 1537221 | [7 empty] | 0 | 0 | Technical Assistance - WWF GEF Part
COMPONENT 1: National capacity and enabling environment for cross-sectoral coordination to promote forest and landscape conservation | [7 empty] | 359959 | [7 empty] | 0 | 0 | COMPONENT 1: National capacity and enabling environment for cross-sectoral coordination |  | COMPONENT 1: National capacity and enabling environment for cross-sectoral coordination
Outcome 1.1: Improved inter-sectoral coordination from Federal, State to Local level for sustainable forest management and integrated landscape management |  |  |  | Q1 | Q2 | Q3 | Q4 | 48924 | [7 empty] | 0 | 0 | Outcome 1.1: Improved inter-sectoral coordination from Federal, State to Local level |  | Outcome 1.1: Improved inter-sectoral coordination from Federal, State to Local level
Output 1.1.1 : Cross-sectoral coordination mechanisms established to support integrated landscape management for conservation outcomes at different levels | 1 | 1.1.1.1: Provide support to NBCC committee (ensure gender inclusive team) | MOFE/DOFSC/DNPWC/MITFE/PMU |  |  |  |  | 2965 |  | Support | 1 |  | 0% |  |  |  |  | 1.1.1.1 | Support includes meeting logistics and office equipment to MoFE | No | No | No | No | No | No | No | No | No | Yes | 1.Sensitize for inclusive participation during project communication (e.g. regular briefing on GESI perspective) 2. Ensure at least 33% female participants in the coordination mechanism (Representation of women, dalits, ethnic and indigenous peoples (where applicable) 3. Ensure coordination mechanism listens and value the idea, perception and needs of women, dalit, janjati, poor and marginalized people of the community (Do no harm and ensure safeguard of women, dalit, janjati, poor and marginalized people during the meeting of coordination mechanism) | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
| 2 | 1.1.1.2 Organize State level Biodiversity Co-ordination Committee (State 2,3,5,7 and Karnali) meetings | MOFE/DOFSC/DNPWC/MITFE | [14 empty] | 1.1.1.2
| 3 | 1.1.1.3 Provide technical and financial support to State Biodiversity Co-ordination committee | MOFE/DOFSC/DNPWC/MITFE/PMU |  |  |  |  | 11261 |  | Support | 5 |  | 0% |  |  |  |  | 1.1.1.3 | Provinces will receive institutional support after formation of province level BCC or during the preparation of NBSAP and its roll-out to enhance understanding and adoption of Integrated Landscape Management | No | No | No | No | No | No | No | No | No | Yes | 1.Sensitize for inclusive participation during project communication (e.g. regular briefing on GESI perspective) 2. Ensure at least 33% female participants in the coordination mechanism (Representation of women, dalits, ethnic and indigenous peoples (where applicable) 3. Ensure coordination mechanism listens and value the idea, perception and needs of women, dalit, janjati, poor and marginalized people of the community (Do no harm and ensure safeguard of women, dalit, janjati, poor and marginalized people during the meeting of coordination mechanism) | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
| 4 | 1.1.1.4 Organize inter-ministerial coordination mechanism for wildlife friendly infrastructure | MOFE/DOFSC/DNPWC/MITFE/PMU |  |  |  |  | 6923 |  | Meeting | 1 |  | 0% |  |  |  |  | 1.1.1.4 | Multistakeholder meeting organized focussing on widlife friendly infrastructure promotion and also includes necessary support in policy processes e.g. printing, consultation, visits | No | No | No | No | No | No | No | No | No | Yes | 1.Sensitize for inclusive participation during project communication (e.g. regular briefing on GESI perspective) 2. Ensure at least 33% female participants in the coordination mechanism (Representation of women, dalits, ethnic and indigenous peoples (where applicable) 3. Ensure coordination mechanism listens and value the idea, perception and needs of women, dalit, janjati, poor and marginalized people of the community (Do no harm and ensure safeguard of women, dalit, janjati, poor and marginalized people during the meeting of coordination mechanism) | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
| 5 | 1.1.1.5 Organize inter-state coordination (2, 3, Gandaki, 5, Karnali, 7) for implementation of the NBSAP and TAL Strategy | PMU/DNPWC/MITFE |  |  |  |  | 2692 |  | Meeting | 2 |  | 0% |  |  |  |  | 1.1.1.5 | Enhancing inter-state coordination on ILM works through organizing interaction on ILM based on NBSAP and TAL strategy | No | No | No | No | No | No | No | No | No | Yes | 1.Sensitize for inclusive participation during project communication (e.g. regular briefing on GESI perspective) 2. Ensure at least 33% female participants in the coordination mechanism (Representation of women, dalits, ethnic and indigenous peoples (where applicable) 3. Ensure coordination mechanism listens and value the idea, perception and needs of women, dalit, janjati, poor and marginalized people of the community (Do no harm and ensure safeguard of women, dalit, janjati, poor and marginalized people during the meeting of coordination mechanism) | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
| 6 | 1.1.1.6 Carry out cluster meetings with Municipalities | PMU/DNPWC/MITFE |  |  |  |  | 10000 |  | Meeting | 4 |  | 0% |  |  |  |  | 1.1.1.6 | Local governments will be sensitized about importance of ILM and coordinate/faciliate in LG's planning process and will be oriented on TAL and NBSAP strategy. Local governments will be sensitized and made aware about importanace of SFM. Also aligned with project phase out plan sharing meeting | No | No | No | No | No | No | No | No | No | Yes | 1.Sensitize for inclusive participation during project communication (e.g. regular briefing on GESI perspective) 2. Ensure at least 33% female participants in the coordination mechanism (Representation of women, dalits, ethnic and indigenous peoples (where applicable) 3. Ensure coordination mechanism listens and value the idea, perception and needs of women, dalit, janjati, poor and marginalized people of the community (Do no harm and ensure safeguard of women, dalit, janjati, poor and marginalized people during the meeting of coordination mechanism) | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
| 7 | 1.1.1.7 Conduct final review of NBSAP (2014-2020) | PMU/MoFE |  |  |  |  | 3846 |  | Package | 1 |  | 0% |  |  |  |  | 1.1.1.7 | Cost includes print & publication, consulting services, roll out of NBSAP in project sites (Province and Local level) once approved by Government of Nepal in Project period . Costs also include documentation, editing, review and meeting logistics | No | No | No | No | No | No | No | No | No | Yes | 1.Sensitize for inclusive participation during project communication (e.g. regular briefing on GESI perspective) 2. Ensure at least 33% female participants in the coordination mechanism (Representation of women, dalits, ethnic and indigenous peoples (where applicable) 3. Ensure coordination mechanism listens and value the idea, perception and needs of women, dalit, janjati, poor and marginalized people of the community (Do no harm and ensure safeguard of women, dalit, janjati, poor and marginalized people during the meeting of coordination mechanism) | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
| 8 | 1.1.1.8 Provide technical and financial support to WCCB | MOFE/DOFSC/DNPWC/MITFE |  |  |  |  | 3846 |  | District cell | 2 |  | 0% |  |  |  |  | 1.1.1.8 | WCCBs (district level) will be strengthend through institutional support | No | No | No | No | No | No | No | No | No | Yes | 1.Support women friendly tools 2. Advocacy for inclusive WCCB | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
| 9 | 1.1.1.9 Field program implementation support & coordination | PMU/BaNP/BNP |  |  |  |  | 7391 |  | Month | 12 |  | 0% |  |  |  |  | 1.1.1.9 | Package includes cost for project staff's travel cost (Transportation and DSA) to support grantee partners in activity implementation and coordination. Also includes monitoring cost to grantee partners | No | No | No | No | No | No | No | No | No | Yes | 1.Sensitize for inclusive participation during project communication (e.g. regular briefing on GESI perspective) 2. Ensure at least 33% female participants in the coordination mechanism (Representation of women, dalits, ethnic and indigenous peoples (where applicable) 3. Ensure coordination mechanism listens and value the idea, perception and needs of women, dalit, janjati, poor and marginalized people of the community (Do no harm and ensure safeguard of women, dalit, janjati, poor and marginalized people during the meeting of coordination mechanism) | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
[8 empty] | 48924 |  |  | 28 | 0 | 0% | 0% |  | 0 | 0
Outcome 1.2 Capacity increased for multi-stakeholder and cross-sector landscape and forest planning and management |  |  |  | Q1 | Q2 | Q3 | Q4 | 311035 | [7 empty] | 0 | 0 | Outcome 1.2 Capacity increased for multi-stakeholder and cross-sector landscape and forest planning and management |  | Outcome 1.2 Capacity increased for multi-stakeholder and cross-sector landscape and forest planning and management
Output 1.2.1. Conservation Leadership Training provided | 10 | 1.2.1.1: Conduct training to ILM coordinators for capturing international best practice and applying this to the local context | PMU/DNPWC/MITFE |  |  |  |  | 68000 |  | ILM coordinators trained | 12 |  | 0% |  |  |  |  | 1.2.1.1 | ILM coordinators working in biodiversity conservation in TAL will be capacited on ILM through international exposures. Capacitated officials are expected to engage to replicate pragmatic approaches and new knowledge in landscape management and TAL India and Nepal exposure visit for Project staff and officials from grantee partners (Realigned $24000 from 1.1.1.3 and $20000 from 2.2.2.1 based on MTR Recommendations inculding field priority /practices) | No | No | No | No | No | No | No | No | No | Yes | 1.Sensitize for inclusive participation during project communication (e.g. regular briefing on GESI perspective and synergies across all level) 2. Ensure 30% female participation (Representation of women, dalits, ethnic and indigenous peoples) with meaninfgul representation in the decision making process | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
[8 empty] | 68000 |  |  | 12 | 0 | 0% |  |  | 0 | 0
Output 1.2.2 Training courses provided on key subjects for integrated landscape management for responsible federal and state government staff | 11 | 1.2.2.1: Conduct training on Biodiversity conservation and monitoring | PMU |  |  |  |  | 8094 |  | Training | 2 |  | 0% |  |  |  |  | 1.2.2.1 | At least 20 government staffs (state and federal staffs) will be given training with 2 training package | No | No | No | No | No | No | Yes | No | Yes. ensure meaningful participation of IPs group, women's group and dalit groups in the consultation process with quality representation in decision making process | Yes | 1.Sensitize for inclusive participation during project communication (e.g. regular briefing on GESI perspective and synergies across all level) 2. Ensure 50% female participation (Representation of women, dalits, ethnic and indigenous peoples) with meaninfgul representation in the decision making process 3. The training manual must include GESI component related to conservation, cover GESI sensitive curriculum/topics, positive change in social norms approach in conservation 4. Use participatory training methods 5. Develop pre-test, post-test questionnaire as an integral part of manual | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
| 12 | 1.1.2.2: Conduct training on Disaster Risk Management | PMU |  |  |  |  | 4687 |  | Training | 1 |  | 0% |  |  |  |  | 1.2.2.2 | At least 10 government staffs (state and federal staffs) will be given training with1 training package | No | No | No | No | No | No | Yes | No | Yes. ensure meaningful participation of IPs group, women's group and dalit groups in the consultation process with quality representation in decision making process | Yes | 1.Sensitize for inclusive participation during project communication (e.g. regular briefing on GESI perspective and synergies across all level) 2. Ensure 50% female participation (Representation of women, dalits, ethnic and indigenous peoples) with meaninfgul representation in the decision making process 3. The training manual must include GESI component related to conservation, cover GESI sensitive curriculum/topics, positive change in social norms approach in conservation 4. Use participatory training methods 5. Develop pre-test, post-test questionnaire as an integral part of manual | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
| 13 | 1.1.2.3: Orientation on roles and responsibilities for new park staff (senior/game scouts) | BaNP/BNP |  |  |  |  | 3077 |  | Orientation | 2 |  | 0% |  |  |  |  | 1.2.2.3 | Training to national park staff on roles and responsibilites. trainee will be identified with inclusive representation | No | No | No | No | No | No | No | No | No | Yes | Capacity building on GESI concepts and mainstreaming methodologies | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
| 14 | 1.1.2.4: Orientation on roles and responsibilities for new divisional staff | DFO-B/DFO-P |  |  |  |  | 1605 |  | Orientation | 1 |  | 0% |  |  |  |  | 1.2.2.4 | Training package - In coordination with Division Forest officials, trainee will be identified with inclusive representation | No | No | No | No | No | No | No | No | No | Yes | Capacity building on GESI concepts and mainstreaming methodologies | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
[8 empty] | 17463 |  |  | 6 | 0 | 0% |  |  | 0 | 0
Output 1.2.3 Small grants for innovation in ILM (conservation, natural resource, and landscape management) in TAL corridors and PA buffer zones | 15 | 1.2.3.1:Provide Individual grant (Bachelors and Master's thesis) | PMU |  |  |  |  | 7569 |  | Grants | 12 |  | 0% |  |  |  |  | 1.2.3.1 | Thesis grants will be provided as per PEC approved guideline. | No | No | No | No | Include Safeguards and GESI research theme | No | Yes; consultation and meaningful participation of IPs should be ensured when applicable | No | Yes. ensure meaningful participation of IPs group, women's group and dalit groups in the consultation process with quality representation in decision making process | Yes | 1. GESI-sensitive selection criteria are used for the selection of Bachelor’s and Master’s degree students 2. Follow participatory method in community consultation processes 3. Ensure 50% female participants (Representation of women, dalits, ethnic and indigenous peoples) with meaningful participation in the decision making processes | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
| 16 | 1.1.3.2: Provide Institutional grant to Academic Institutional and CBOs/CSOs | PMU |  |  |  |  | 15962 |  | Grants | 4 |  | 0% |  |  |  |  | 1.2.3.2 | Includes study, action research or scientific research and on the ground interventions as well. However priority will be given to academic institutions in research, extension work and capacity development related to NRM and biodiversity Conservation in TAL | No | No | No | No | No | No | Yes | No | Yes. ensure meaningful participation of IPs group, women's group and dalit groups in the consultation process with quality representation in decision making process | Yes | 1. GESI-sensitive selection criteria are used for identifying local CBOs/CSOs to provide grants (i.e. ensuring an equal percentage of women-led CBOs/CSOs have access to grants, as much as possible) 2. Ensure 50% female participation (Representation of women, dalits, ethnic and indigenous peoples) with meaningful representation in the decision making processes during capacity enhacement trainings and participations | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
| 17 | 1.1.3.3: Provide innovation grant to the government agencies (National Park, Forest Division, Research and Training Centre) at state level | PMU/DNPWC/MoEFSC |  |  |  |  | 202041 |  | Grants | 5 |  | 0% |  |  |  |  | 1.2.3.3 | Include infrastructure, equipments and research (HWC management, species management, Forest restoration, problem animal-rescue equipment, agroforestry, promotion for livelihood), study, ecotourism promotion, workshop, capacity development training and saftey field gear to government officials and scientific research across the country. Priority in TAL area (Realigned $ 40000 from 1.2.3.2 based on MTR Recommendations inculding field priority /practices) | No | No | No | No | No | No | Yes | No | Yes. ensure meaningful participation of IPs group, women's group and dalit groups in the consultation process with quality representation in decision making process | Yes | 1. Ensure at least 33% female participation (Representation of women, dalits, ethnic and indigenous peoples) with meaningful representation in the decision making process in selection of participants (awardees) and conduction of consultation meetings with community | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
[8 empty] | 225572 |  |  | 21 | 0 | 0% | 0% | 0% | 0 | 0
Component 2: Integrated Planning for Protected Area Buffer Zones and Critical Corridors in the Terai Arc Landscape | [7 empty] | 34223 | [7 empty] | 0 | 0 | Component 2: Integrated Planning for Protected Area Buffer Zones and Critical Corridors in the Terai Arc Landscape |  | Component 2: Integrated Planning for Protected Area Buffer Zones and Critical Corridors in the Terai Arc Landscape
Outcome 2.1: Improved corridor planning for TAL corridors (Brahmadev, Karnali and Kamdi) |  |  |  | Q1 | Q2 | Q3 | Q4 | 0 | [7 empty] | 0 | 0 | Outcome 2.1: Improved corridor planning for TAL corridors (Brahmadev, Karnali and Kamdi) |  | Outcome 2.1: Improved corridor planning for TAL corridors (Brahmadev, Karnali and Kamdi)
Output 2.1.1 Biodiversity surveys, socio-economic surveys, and local stakeholder consultation for Brahmadev , Karnali, and Kamdi corridors to determine feasibility of appropriate models for community-based natural resource management | 18 | 2.1.1.1: Conduct assessment to update biodiversity inventory and socio-economic status in corridors (incorporating GESI aspect, indigenous people and access restriction information) | PMU | [14 empty] | 2.1.1.1
| 19 | 2.1.1.2: Provide technical support to review existing forest encroachment status and response options considering GESI aspect and any necessary safeguards management plans (e.g. IPP or LRP)” | BaNP/BNP/ DFO-B/ DFO-P | [14 empty] | 2.1.1.2
| 20 | 2.1.1.3: Prepare corridor/bottleneck assessment report with GESI and safeguards integration | PMU | [14 empty] | 2.1.1.3
[8 empty] | 0 |  |  | 0 | 0 |  |  |  | 0 | 0
Outcome 2.2: Improved participatory planning for sustainable management of in Banke-Bardia complex |  |  |  | Q1 | Q2 | Q3 | Q4 | 24627 | [7 empty] | 0 | 0 | Outcome 2.2: Improved participatory planning for sustainable management of in Banke-Bardia complex |  | Outcome 2.2: Improved participatory planning for sustainable management of in Banke-Bardia complex
Output 2.2.1: Land uses, biodiversity values, forest carbon, and key threats assessed, mapped, reported and disseminated to identify priority villages and forest areas in the targeted PA buffer zones and corridors | 21 | 2.2.1.1: Conduct participatory assessments in targeted PA buffer zones and corridors to identify priority community and forest areas | PMU | [14 empty] | 2.2.1.1 |  | Yes; incorporate the habitat degradation status and patch areas in the assessment | Yes; analyze any access restriction issues | Yes; ensure meaningful participation IPs | No | 1.Ensure habitat degradation, patch areas identification, access restriction issues 2. Ensure meaningful participation of IPS, women's group and dalit groups | Yes | Yes | Yes; Report any as such requred during the consultation process | Ensure meaningful participation of IPS | Yes | 1.Sensitize for inclusive participation during project communication (e.g. regular briefing on GESI perspective) 2. Ensure at least 50% female participants (Representation of women, dalits, ethnic and indigenous peoples) | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
| 22 | 2.2.1.2: Conduct resource mapping of CFUGs at corridor level and BZUCs | PMU/DNPWC/MITFE |  |  |  |  | 5000 |  | Assessment | 2 |  | 0% |  |  |  |  | 2.2.1.2 | Resource mapping with expert supports BaNP BZ, BNP BZ, Kamdi and Karnali corridor, including water quality assessment-1, in BNP. Cost also include documentation, editing, review and printing | Yes | Yes | Yes | No | 1. Ensure issues of IPs, Dalits and Women's group | Yes | Yes | Yes; prepare on the basis of screnning | 1. Consultations with IPs, Womens' Group and Dalits | Yes | 1.Sensitize for inclusive participation during project communication (e.g. regular briefing on GESI perspective) 2. Ensure 50% female participation (Representation of women, dalits, ethnic and indigenous peoples) | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
| 23 | 2.2.1.3: Carry out consultations at identified communities | MOFE/DOFSC/DNPWC/MITFE |  |  |  |  | 10000 |  | meetings | 64 |  | 0% |  |  |  |  | 2.2.1.3 | At least 60 events of consultation meetings and co-ordinaton meetings will be conducted with the identified communities. Based on the forest and community Participatory Assessment Report (updated) to facilitate implementation of project activities including safeguard orientation. Also includes Sustainability plan preparation/roll out meeting with stakeholders (Realigned $1986 from 2.1.1.2 and $139 from 2.1.1.1 based on MTR Recommendations inculding field priority /practices) | Yes; discuss on habitat degradation issues | Yes; analyze any access restriction issues and mitigation strategies | Yes; participate IPs in consultation process | No | Yes; on the basis of consultation | Yes | Yes | No | Ensure meaningful participatoin of IPs/ in consultation process and in decision making processs | Yes | 1.Sensitize for inclusive participation during project communication (e.g. regular briefing on GESI perspective) 2. Ensure 50% female participants (Representation of women, dalits, ethnic and indigenous peoples) with meaningful participation in decision making process | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
[8 empty] | 15000 |  |  | 66 | 0 | 0% |  |  | 0 | 0
Output 2.2.2: Sustainable Forest Management Operational Plans developed or revised for priority forest areas, incorporating the assessment from 2.2.1 | 24 | 2.2.2.1: Provide financial support to develop State forest sector strategies (including Community Forests, Protected Forests and Leash-hold Forest) | MOFE/DOFSC/DNPWC/MITFE |  |  |  |  | 5781 |  | Stradegy study | 1 |  | 0% |  |  |  |  | 2.2.1.1 | Cost includes dissemination/roll-out meetings of Forestry sector strategy prepared by MoFE in project sites and TAL and also includes consultation support (if needed) at province level. Costs also include documentation, editing, review and printing, meeting logistics.
| 25 | 2.2.2.2: Support CFUGs and BZ CFUGs to develop/revise forest operational plan (GESI aspect is revised/incorporated) | PMU/DNPWC/MITFE |  |  |  |  | 3846 |  | CFUGs meetings | 12 |  | 0% |  |  |  |  | 2.2.1.2 | Incorporation of GESI aspects in operational plans will be prioritized. | Yes; review the natural habitat degradation | Yes; review any access restriction issues in the plan | 1. Yes; ensure meaningful participation of IPs in revision process | No | Explore true collaboration and agreement | Yes | Yes; ensure meaningful participation of Ips | No | Ensure meaningful participation of IPs/ in the consultation process and in decision-making processes with true collaboration and agreement | Yes | 1.Sensitize for inclusive participation during project communication (e.g. regular briefing on GESI perspective) 2. Ensure 50% female participation (Representation of women, dalits, ethnic and indigenous peoples) with meaningful participation in decision making process | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
[8 empty] | 9627 |  |  | 13 | 0 | 0% |  |  | 0 | 0
Output 2.2.3: Strategic framework for corridor management developed and management plans prepared or revised for all seven TAL corridors / protected forests | 26 | 2.2.3.1: Develop a gender and inclusion responsive guideline (GIRD) to prepare management plans of PF/Corridors | PMU | [14 empty] | 2.2.3.1
| 27 | 2.2.3.2: Support to revise PF / Corridor Management Plans through a participatory process | PMU/DNPWC/MITFE |  |  |  |  | 4248 |  | Plans | 2 |  | 0% |  |  |  |  | 2.2.3.2 | corridor management plan roll-out incuding printing cost. Costs also include documentation, editing, review.
| 28 | 2.2.3.3: Field program implementation support & coordination | MOFE/DOFSC/DNPWC/MITFE |  |  |  |  | 5348 |  | Months | 12 |  | 0% |  |  |  |  | 2.2.3.3 | Package includes cost for project staff's travel and DSA to support grantee partners in activity implementation and coordination. Along with monitoring cost to grantee partners | No | No | No | No | No | No | No | No | No | Yes | 1.Sensitize for inclusive participation during project communication (e.g. regular briefing on GESI perspective) 2. Ensure 50% female participation (Representation of women, dalits, ethnic and indigenous peoples) with meaningful participation in decision making process | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
[8 empty] | 9596 |  |  | 14 | 0 | 0% | 0% | 0% | 0 | 0
COMPONENT 3: Forest and human-wildlife conflict management for improved conservation of targeted protected area buffer zones and corridors in the Terai Arc Landscape | [7 empty] | 953243 | [7 empty] | 0 | 0 | COMPONENT 3: Forest and HWC management for improved conservation of targeted PA buffer zones and corridors in the TAL |  | COMPONENT 3: Forest and human-wildlife conflict management for improved conservation of targeted protected area buffer zones and corridors in the Terai Arc Landscape
Outcome 3.1: Strengthen livelihoods and biodiversity conservation through Sustainable forest management practices |  |  |  | Q1 | Q2 | Q3 | Q4 | 596864 | [7 empty] | 0 | 0 | Outcome 3.1: Strengthen livelihoods and biodiversity conservation through Sustainable forest management practices |  | Outcome 3.1: Strengthen livelihoods and biodiversity conservation through Sustainable forest management practices
Output 3.1.1: Training and tools to local government on SFM | 29 | 3.1.1.1: Prepare Sustainable Forest Management Training (SFM) Manual incorporating GESI | MOFE/DOFSC/DNPWC/MITFE |  |  |  |  | 5000 |  | Manaul | 1 |  | 0% |  |  |  |  | 3.1.1.1 | Cost includes printing cost of manual and expert cost if applicable. Costs also include documentation, editing, review.
| 30 | 3.1.1.2: Provide "Training of Trainers" (TOT) to Division Forest Offices staff based on SFM Training Manual | PMU/DNPWC/MITFE |  |  |  |  | 16852 |  | No of training | 2 |  | 0% |  |  |  |  | 3.1.1.2 | Includes Training Cost province government officials and Local governments will be sensitized and made aware about importance of SFM. | No | No | No | No | No | No | No | No | No | Yes | 1. Ensure GESI component related with the conservation in the manual 2. Ensure participatory training methods in the manual 3. Ensure GESI pre-test, post-test questionnaire as a part of manual | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
| 31 | 3.1.1.3 Establish Forest Management Information system (FMIS) including forest fire management | MOFE/DOFSC/DNPWC/MITFE | [14 empty] | 3.1.1.3
| 32 | 3.1.1.4: Support the State Forest Directorate fire reporting system | MOFE/DOFSC/DNPWC/MITFE | [14 empty] | 3.1.1.4
| 33 | 3.1.1.5: Support forest fire management through innovative tools and techniques such as leaf litter collection and composting (within targeted sites identified in component 2) | MOFE/DOFSC/DNPWC/MITFE |  |  |  |  | 34615 |  | support | 4 |  | 0% |  |  |  |  | 3.1.1.5 | Sites or CFUGs identified as most vulnerable to forest fire in project sites will be supported with forest fire management tools and forest fire management interventions support to DFOs/NPs (Realigned $7813 from 3.1.1.3 based on MTR Recommendations inculding field priority /practices) | Yes | No | Yes | No | Explore any collaboration and agreement with Ips for effective tools | Yes | Yes; ensure meaningful participation of IPs | Yes | 1. Ensure meaningful participation of women's, dalit and IPs groups | Yes | 1. Ensure 50% female beneficiaries receiving tools | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
| 34 | 3.1.1.6 Provide multi-year support for nursery to Division forest offices (within targeted sites identified in component 2) including forest restoration activities in BZ and corridor | MOFE/DOFSC/DNPWC/MITFE |  |  |  |  | 40769 |  | nursery | 4 |  | 0% |  |  |  |  | 3.1.1.6 | Nursery infrastructures strengthening and produce multi-year/single year seedlings to make available to local communities in forest restoration sites, private and agro-forestry promotion site 2.5 lakh seedling production, 172 hac area restoration (Restoration of public land and national forest including ommunity forest through through natural regeneration protection and plantation) following MTR recommendation | Yes; ensure selection of quality species suitable for wildlife and biodiversity | No | Yes | Yes | Ensure invasive species are not promoted, and IPs are consulted | Yes | Yes | No | 1. Ensure meaningful participation of women's, dalit and IPs groups | Yes | Ensure 60% female, 20% IPs and 5% dalits as beneficiaries | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
[8 empty] | 97236 |  |  | 11 | 0 | 0% |  |  | 0 | 0
Output 3.1.2: Technical support to CFUGs, BZCFUGs and land holders for forest management | 35 | 3.1.2.1: Provide training to CFUGs and BZ CFUGs for forest management implementation (including applied SFM, restoration technique - lined with 3.1.1 | PMU/DNPWC/MITFE |  |  |  |  | 119231 |  | training | 2 |  | 0% |  |  |  |  | 3.1.2.1 | Focus on implementation of SFM in block Forest and Community Forest. Training to CFUGs on sustainable forest management and restoration (Realigned $ 46876 from 3.1.3.1 and $ 61538.46 from 3.1.2.5 based on MTR Recommendations inculding field priority /practices) | No | No | No | No | No | No | No | No | 1. Ensure meaningful participation of women's, dalit and IPs groups | Yes | 1.Sensitize for inclusive participation during project communication (e.g. regular briefing on GESI perspective) 2. Ensure 50% female participation (Representation of women, dalits, ethnic and indigenous peoples) | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
| 36 | 3.1.2.2: Conduct exchange visits for targeted BZ CFUG members (learning from successful UCs on fund mobilization and HWC management) | PMU | [14 empty] | 3.1.2.2
| 37 | 3.1.2.3: Support BZUCs annual meetings for Bardia and Banke NP Buffer Zones (northern side) | PMU/DNPWC/MITFE | [14 empty] | 3.1.2.3
| 38 | 3.1.2.4: Provide coaching on "Governance and Financial management" for CFUGs of corridors and PA Buffer zones | PMU/DNPWC/MITFE |  |  |  |  | 7154 |  | coaching sessions | 32 |  | 0% |  |  |  |  | 3.1.2.4 | Training costs for CFUGs and BZUCs, ensuring equitable access to all members and gender dimensions in training opportunities | No | No | No | No | No | No | No | No | No | Yes | 1.Sensitize for inclusive participation during project communication (e.g. regular briefing on GESI perspective) 2. Ensure 50% female participation (Representation of women, dalits, ethnic and indigenous peoples) | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
| 39 | 3.1.2.5: Provide support private forest development (providing seedling, irrigation, fencing) | MOFE/DOFSC/DNPWC/MITFE | [14 empty] | 3.1.2.5
| 40 | 3.1.2.6: Support to register private forest | PMU/DNPWC/MITFE |  |  |  |  | 2000 |  | No of forest | 2 |  | 0% |  |  |  |  | 3.1.2.6 | Administration cost support to private forest owners in registration process | No | No | Yes | Yes | 1. Promote indigenous species plantation 2. Discourage use of pesticides | No | No | No | No | Yes | Prioritize 50% women's for their ownership in registration | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
[8 empty] | 128385 |  |  | 36 | 0 | 0% |  |  | 0 | 0
Output 3.1.3: Forests and associated habitat in priority buffer zones and corridors managed sustainably | 41 | 3.1.3.1: Create revolving fund to implement forest operational plans in project targeted corridors | PMU/DNPWC/MITFE | [14 empty] | 3.1.3.1
| 42 | 3.1.3.2: Provide financial and technical support to improve livestock management (AI, fodder plant support, feeding trough, vet support, stall improvement) including agroforestry promotion activities to reduce grazing pressure | PMU/DNPWC/MITFE |  |  |  |  | 20037 |  | Households | 81 |  | 0% |  |  |  |  | 3.1.3.2 | To reduce pressure on wildlife habitat, alternative packages including cement trough, fodder seedlings will be supported to households who are more dependent on forest resources in nearby corridor forest/ buffer zone forest ultimately contributing to sustainable forest management, including agroforestry promotion activities following MTR recommendation | Yes | No | Yes | Yes | Ensure proper consultation and meaningful participation of Ips | Yes | Yes | Yes | 1. Prepare LRP first and then support | Yes | 1. Ensure 60% female, 20% Ips, and 10% dalit beneficiaries for livestock management support | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
| 43 | 3.1.3.3: Provide financial and technical support for management of grassland and wetland in project targeted area | PMU/DNPWC/MITFE |  |  |  |  | 259231 |  | Support Package | 8 |  | 0% |  |  |  |  | 3.1.3.3 | Package includes Habitat improvement in BaNP and its buffer zone, BNP and its buffer zone, Kamdi corridors and Karnali corridors including technical backstopping and monitoring cost to grantee partners. Park offices will prioritize implementation sites in core area of national park and buffer zone. Improved management within National Parks helps provide essential habitat for diverse wildlife. Since there is a large area available in the project site for restoration, and we need to achieve additional targets, a substantial portion of the budget has been reallocated to this activity (Realigned $13298 from 2.2.3.1, $2692 from 4.1.1.1, $20000 from 2.2.1.2, $14285 from 4.3.1.4, $14962 from 4.3.1.5, $ 2404 from 4.3.1.2, 12591 from 4.2.1.6 , $8000 from 4.1.2.2, $13069 from 4.2.1.3, $2401 from 4.2.1.4, $9122 from 4.2.1.5, $11540 from 3.3.1.1, $10000 from 4.3.1.1, $10000 from 1.2.2.2 $2324 from 3.1.3.7 based on MTR Recommendations inculding field priority /practices) | Yes | Yes | Yes | No | Conduct screening, categorization | Yes | Yes | On the basis of FPIC | 1. Ensure meaningful participation of IPs, Dalit and women's group 2. Develop LRP as needed | Yes | 1. Ensure 60% female, 20% Ips, and 10% dalit beneficiaries (if LRP) | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
| 44 | 3.1.3.4: Provide financial and technical support for river bank protection in project targeted area | PMU/DNPWC/MITFE |  |  |  |  | 64771 |  | Support Package | 2 |  | 0% |  |  |  |  | 3.1.3.4 | Package includes river training works, biological measures to be appliced to control river cutting, construction materials purchase and transporation. Area (forest and agriculture land to be protected/restored after river bank protection to be calculated during details sites identification and implementation plan preparation ( Realigned $ 32189 from 3.1.2.5 Planning Workshop based on MTR Recommendations inculding field priority /practices) | Yes | Yes | Yes | No | 1. Ensure wildlife friendly structure | Yes | Yes | Yes | 1. Consent from IPs | Yes | 1.Sensitize for inclusive participation during project communication (e.g. regular briefing on GESI perspective) 2. Ensure 50% female participation (Representation of women, dalits, ethnic and indigenous peoples) | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
| 45 | 3.1.3.5: Safeguard plan implementation | PMU |  |  |  |  | 17524 |  | plan/s | 4 |  | 0% |  |  |  |  | 3.1.3.5 | Package include capacity building training on ESS, GESI, GRM, hoarding board/Pictorial content development on ESS awareness, support women/IPs/dalit group with LIP, exposure visit to CFUG/BZUC members, mitigative safeguard to support Project Affected Peoples. Costs also include documentation through consulting services, editing, review and printing | Yes | Yes | Yes | Yes | Yes, Ensure Environmental and Social Safeugards | Yes | Yes | Yes | Yes | Yes | Ensure 60% women, 25% IPs and 10% dalit beneficiaries | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
| 46 | 3.1.3.6: Provide financial and technical support to small scale green enterprises in project targeted area | PMU/DNPWC/MITFE |  |  |  |  | 7692 |  | enterprise | 1 |  | 0% |  |  |  |  | 3.1.3.6 | financial and technical support to small scale green enterprises in project targeted area
| 47 | 3.1.3.7: Provide financial and technical support to develop business plan | PMU |  |  |  |  | 1988 |  | plan/s | 1 |  | 0% |  |  |  |  | 3.1.3.7 | Technical support with expert members on green enterprises business plan preparation | No | No | Yes | No | Ensure meaningful participation of Ips, dalit and womens group | Yes | Yes | Yes | 1. Involve IPs in business plan preparation | Yes | Ensure at least 60% female, 25% Ips and 10% dalit beneficiaries for project related loans for community level enterprise and livelihood support | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
[8 empty] | 371243 |  |  | 97 | 0 | 0% | 0% |  | 0 | 0
Outcome 3.2: Improved management of the human-wildlife conflict |  |  |  | Q1 | Q2 | Q3 | Q4 | 306162 | [7 empty] | 0 | 0 | Outcome 3.2: Improved management of the human-wildlife conflict |  | Outcome 3.2: Improved management of the human-wildlife conflict
Output 3.2.1: Pilot method to reduce the wildlife accident in priority sites | 48 | 3.2.1.1: Conduct study on the wildlife traffic accident issue | PMU | [14 empty] | 3.2.1.1
| 49 | 3.2.1.2: Install tools/facilities to pilot measures to reduce accidents | MOFE/DOFSC/DNPWC/MITFE | [14 empty] | 3.2.1.2
| 50 | 3.2.1.3: Support in operation and monitoring of wildlife related traffic accidents in highway | MOFE/DOFSC/DNPWC/MITFE |  |  |  |  | 7692 |  | monitoring | 2 |  | 0% |  |  |  |  | 3.2.1.3 | Package includes technology enhancement, capacity development and monitoring cost (Realigned $447 from 3.2.1.1, $1704 from 3.2.1.2, $ 4437 from 3.2.1.4 based on MTR Recommendations inculding field priority /practices) | No | No | No | No | No | No | Yes; Esure meaningful participation of IPs representative | No | No | Yes |  | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
| 51 | 3.2.1.4: Support to erect fence in both side of Sikta irrigation canal | MOFE/DOFSC/DNPWC/MITFE | [14 empty] | 3.2.1.4
[8 empty] | 7692 |  |  | 2 | 0 | 0% |  |  | 0 | 0
Output 3.2.2: Training and facilities for human wildlife conflict response | 52 | 3.2.2.1: Prepare species-specific guidelines for HWC management | MOFE/DOFSC/DNPWC/MITFE/PMU | [14 empty] | 3.2.2.1
| 53 | 3.2.2.2: Pictorial manual on Wildlife identification and behavior in Nepali and local dialects | MOFE/DOFSC/DNPWC/MITFE/PMU |  |  |  |  | 5047 |  | manual | 1 |  | 0% |  |  |  |  | 3.2.2.2 | Manual preparation, review and printing | No | No | No | No | No | No | No | No | No | Yes | Ensure GESI friendly dialect | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
| 54 | 3.2.2.3: Conduct training on identification and behavior of wild animals to Divisional forest office staff | MOFE/DOFSC/DNPWC/MITFE/PMU |  |  |  |  | 3846 |  | training | 2 |  | 0% |  |  |  |  | 3.2.2.3 | conduct training to division forest staff | No | No | No | No | No | No | No | No | No | Yes | 1.Sensitize for inclusive participation during project communication (e.g. regular briefing on GESI perspective) 2. Ensure at least 30% female participation (Representation of women, dalits, ethnic and indigenous peoples) | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
| 55 | 3.2.2.4: Support Wildlife Rescue center | MOFE/DOFSC/DNPWC/MITFE | [14 empty] | 3.2.2.4
| 56 | 3.2.2.5: Support wildlife rescue and handling equipment and training | MOFE/DOFSC/DNPWC/MITFE |  |  |  |  | 1172 |  | training | 1 |  | 0% |  |  |  |  | 3.2.2.5 | Activities includes rescue of wildlife, equipments/tools purchase to handle wildlife and training conduction (if needed) | No | No | No | No | No | No | No | No | No | Yes | 1. Ensure 50% female participants in the training 2. Manual should include GESI mainstreaming methodologies | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
[8 empty] | 10065 |  |  | 4 | 0 | 0% |  |  | 0 | 0
Output 3.2.3: Community based HWC mitigate and preventive action implemented | 57 | 3.2.3.1: Conduct workshop on preventive and curative measures for HWC | MOFE/DOFSC/DNPWC/MITFE |  |  |  |  | 7877 |  | workshop | 1 |  | 0% |  |  |  |  | 3.2.3.1 | Workshop with relevent stakeholders on preventive and curative measures taking account the knowledge, needs and special considerations of indigenous people in developing and promoting measures | No | No | No | No | No | No | Yes; participate IPs organizations | No | Ensure meaningful participation of Ips | Yes | 1.Sensitize for inclusive participation during project communication (e.g. regular briefing on GESI perspective) 2. Ensure 50% female in the workshop (women, dalits, indigenous people) where applicable 3. GESI concept and mainstreaming methodologies are incorporated in the presentation | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
| 58 | 3.2.3.2: Implement measures for HWC based on prepared plans (mentha plantation, biological/virtual fencing) | PMU/DNPWC/MITFE |  |  |  |  | 276682 |  | Plans | 10 |  | 0% |  |  |  |  | 3.2.3.2 | Package includes wildlife deterent plants plantation, green fences, predator proof pen fence, mesh wire /electric fencing and its maintanance, - as per community need and nature of HWC. The detials (sites/interventions) to be finalized based on participatory assessment report followed by community consultation and information collection from field. Cost also includes cost-benefit analysis of HWC management as recommended by MTR (Realigned $143410 from 3.1.3.6, $66094 from 3.2.3.3, $5628 from 3.3.2.3, $9410 to 4.1.2.1 based on MTR Recommendations inculding field priority /practices) | Yes | Yes | Yes | Yes | Ensure no invasive species are used and meaningful consultation with IPs | Yes | Yes | Yes | 1. Meaningful participation of IPs, Womens' Group and Dalits | Yes | 1.Sensitize for inclusive participation during project communication (e.g. regular briefing on GESI perspective) 2. Ensure 60% female, 25% Ips and 10% dalit participation during project -related loans for community level enterprise and livelihood support | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
| 59 | 3.2.3.3: Support to establish community-based insurance (crop, livestock) scheme | PMU/DNPWC/MITFE | [14 empty] | 3.2.3.3
| 60 | 3.2.3.4: Implement community-based reporting system of HWC incidents | MOFE/DOFSC/DNPWC/MITFE |  |  |  |  | 3846 |  | system | 2 |  | 0% |  |  |  |  | 3.2.3.4 | Prepare reporting system and implement with stakeholders support. It also includes Information collection | No | No | No | No | No | Yes | Yes | No | 1. Meaningful participation of IPs, Womens' Group and Dalits | Yes | Prioritize Dalit, women's group, and IPs in decision making | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
[8 empty] | 288405 |  |  | 13 | 0 | 0% |  |  | 0 | 0
Outcome 3.3: Enhanced capacities of government agencies and community in curbing illegal wildlife crime |  |  |  | Q1 | Q2 | Q3 | Q4 | 50217 | [7 empty] | 0 | 0 | Outcome 3.3: Enhanced capacities of government agencies and community in curbing illegal wildlife crime |  | Outcome 3.3: Enhanced capacities of government agencies and community in curbing illegal wildlife crime
Output 3.3.1: Community Based Anti poaching Units functional in priority areas | 61 | 3.3.1.1: Provide support for field gears to CBAPU members | PMU/DNPWC/MITFE |  |  |  |  | 20000 |  | CBAPU/s | 70 |  | 0% |  |  |  |  | 3.3.1.1 | Basic safety and health equipments to community youth volunteer - CBAPU and protection staff like torch light, field gears e.g. cap, rain coat/jacket. Cost includes sesitization/ capacity development workshop on biodiversity conservation and environmental and social safeguard and field gears to 70 CBAPUs (also includes capacity building through exposer visits and training) | No | No | No | No | No | No | No | No | No | Yes | Ensure Gender friendly field gears | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
| 62 | 3.3.1.2: Provide technical and financial support for skill based training to CBAPU members | PMU | [14 empty] | 3.3.1.2
| 63 | 3.3.1.3: Establish revolving fund to initiate green enterprise for CBAPUs member (link to above activities) | PMU/DNPWC/MITFE | [14 empty] | 3.3.1.3
[8 empty] | 20000 |  |  | 70 | 0 | 0% |  |  | 0 | 0
Output 3.3.2: Training and operation support to Park staff, rangers on wildlife crime management | 64 | 3.3.2.1: Update training manual on illegal wildlife crime scene management | MOFE/DOFSC/DNPWC/MITFE/PMU |  |  |  |  | 4000 |  | Manual | 1 |  | 0% |  |  |  |  | 3.3.2.1 | Manual update through experts engagement and also include printing cost. Costs also include documentation, editing, review and consultation meeting
| 65 | 3.3.2.2: Conduct training to investigation officers level on Illegal wildlife crime scene management | MOFE/DOFSC/DNPWC/MITFE |  |  |  |  | 18050 |  | training | 2 |  | 0% |  |  |  |  | 3.3.2.2 | Training package development and training conducted | No | No | No | No | Ensure WWF’s Support for Enforcement and Rangers in the training manual | No | No | No | No | Yes | 1.Follow WWF guidance on armed, professional poachers vs community members engaged in livelihood activities 2. Ensure at least 50% female participation (Representation of women, dalits, ethnic and indigenous peoples) | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
| 66 | 3.3.2.3: Support Transboundary coordination at local level | MOFE/DOFSC/DNPWC/MITFE |  |  |  |  | 4615 |  | meeting | 3 |  | 0% |  |  |  |  | 3.3.2.3 | Transboundary meetings between India and Nepal officials on ILM themes (species protection, HWC management etc) | No | No | No | No | No | No | No | No | No | Yes | 1.Sensitize for inclusive participation during project communication (e.g. regular briefing on GESI perspective) 2. Ensure at least 33% female participation (Representation of women, dalits, ethnic and indigenous peoples) | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
| 67 | 3.3.2.4: Field program implementation support & coordination | PMU/DNPWC/MITFE |  |  |  |  | 3552 |  | Month | 12 |  | 0% |  |  |  |  | 3.3.2.4 | Package includes cost (for 12 months) for project staff's travela nd DSA to support gratee partners technically in activity implementation and necessary coordination (Realigned $962 from 3.1.2.2, $55 from 3.1.2.3, $889 from 3.2.2.4 based on MTR Recommendations inculding field priority /practices) | No | No | No | No | No | No | No | No | No | Yes | 1.Sensitize for inclusive participation during project communication (e.g. regular briefing on GESI perspective) 2. Ensure at least 33% female participation (Representation of women, dalits, ethnic and indigenous peoples) | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
[8 empty] | 30217 |  |  | 18 | 0 | 0% | 0% | 0% | 0 | 0
COMPONENT 4: Monitoring and evaluation (M&E), knowledge management (KM), and regional coordination | [7 empty] | 189796 | [7 empty] | 0 | 0 | COMPONENT 4: Monitoring and evaluation (M&E), knowledge management (KM), and regional coordination |  | COMPONENT 4: Monitoring and evaluation (M&E), knowledge management (KM), and regional coordination
Outcome 4.1: Improved coordination and dialogue on integrated landscape management from the local to national level |  |  |  | Q1 | Q2 | Q3 | Q4 | 61583 | [7 empty] | 0 | 0 | Outcome 4.1: Improved coordination and dialogue on integrated landscape management from the local to national level |  | Outcome 4.1: Improved coordination and dialogue on integrated landscape management from the local to national level
Output 4.1.1: Information on ILM importance shared among key stakeholders | 68 | 4.1.1.1: Organize monthly dialogue through "Jaibik Chautari" (Biodiversity Platform) at field | MOFE/DOFSC/DNPWC/MITFE/PMU |  |  |  |  | 11613 |  | Dialogue | 5 |  | 0% |  |  |  |  | 4.1.1.1 | A dialogue will be organized in coordination with local CSOs and government bodies e.g. NBCC, WCCB, TAL working group and conduct thematic discussion. During the implementation, number of stakeholders will be identified and documented to better align with result framework. | No | No | No | No | No | No | Yes; ensure representation of IPs organization | No | 1. Ensure quality and inclusive representation | Yes | 1.Sensitize for inclusive participation during project communication (e.g. regular briefing on GESI perspective) 2. Ensure 50% female participation (Representation of women, dalits, ethnic and indigenous peoples) | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
| 69 | 4.1.1.2: Organize annual technical thematic discussion session at center | MOFE/DOFSC/DNPWC/MITFE/PMU |  |  |  |  | 10077 |  | meeting | 1 |  | 0% |  |  |  |  | 4.1.1.2 | Annual discussions among key stakeholders on ILM e.g. wildlife rescue, forest fire and other sues recommended by MoFE | No | No | No | No | No | No | No | No | No | yes | 1.Sensitize for inclusive participation during project communication (e.g. regular briefing on GESI perspective) 2. Ensure 50% female participation (Representation of women, dalits, ethnic and indigenous peoples) | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
| 70 | 4.1.1.4: Establish and maintain online Landscape Knowledge Learning Platform (including project website) | PMU |  |  |  |  | 2080 |  | platform | 1 |  | 0% |  |  |  |  | 4.1.1.3 | Project website maintained and enhanced | No | No | No | No | No | No | No | No | No | Yes | Prioritize women's group, dalits, IPs in the learning platform | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
[8 empty] | 23770 |  |  | 7 | 0 | 0% |  |  | 0 | 0
Output 4.1.2: Mass awareness products on biodiversity conservation and integrated landscape management | 71 | 4.1.2.1: Provide technical and financial support to green/eco-clubs formation and its operation | PMU/DNPWC/MITFE |  |  |  |  | 15384 |  | No of eco-clubs supported | 4 |  | 0% |  |  |  |  | 4.1.2.1 | Capacitate eco-clubs to be part of biodiversity conservation at local level through talent competition, awareness campaign (e.g. mass awareness on waste management/plastic pollution control), small infrastructure like e.g.cycle stand, eco-garden, bio-fencing, waste pit). It includes write shop event. Costs also include documentation, editing, review and printing. | No | No | No | No | No | No | No | No | No | Yes | 1. Ensure 50% female in the Eco-club 2. Gender friendly planning and implementation | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
| 72 | 4.1.2.2: Support annual meetings of green/eco-clubs network at district level | PMU |  |  |  |  | 3846 |  | No of meetings | 2 |  | 0% |  |  |  |  | 4.1.2.2 | Orientation, exposure visits and capacity buidling training/events and meetings with eco-club networks, eco-teachers. It also includes print and publish of Art book and story book & write-shop event. Costs also include documentation, editing, review and printing | No | No | Yes | No | Ensure childrens from Ips in the meeting | No | No | No | No | Yes | Ensure 50% female, and representation of Ips, dalits in the eco-club | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
| 73 | 4.1.2.3: Support special conservation events at local level | MOFE/DOFSC/DNPWC/MITFE |  |  |  |  | 7531 |  | event | 5 |  | 0% |  |  |  |  | 4.1.2.3 | Awareness event celebration through PMU and technical/financial support to government entities to organize conservation events with multi-stakeholder (Ips, LCs) participation including International Womans day (Realigned $1578.85 from 4.1.2.2, $3846 from 4.2.1.2 based on MTR Recommendations inculding field priority /practices) | No | No | No | No | No | No | Yes | No | 1. Ensure meaningful participation of IPs in celebrating events | Yes | 1.Sensitize for inclusive participation event celebration (e.g. regular briefing on GESI perspective) 2. Ensure at least 50% female participation (Representation of women, dalits, ethnic and indigenous peoples) | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
| 74 | 4.1.2.4: Sensitize media (print and TV) on integrated landscape management | PMU |  |  |  |  | 4910 |  | media | 1 |  | 0% |  |  |  |  | 4.1.2.4 | Organize media visits to sensitize about ILM | No | No | No | No | No | No | No | No | No | Yes | 1. GESI sensitive information 2. Ensure proper capacity building of the media to disseminate information on the importance of GESI integration in conservation. | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
| 75 | 4.1.2.5: Support radio program (local dialects) on ILM | PMU |  |  |  |  | 6142 |  | radio | 10 |  | 0% |  |  |  |  | 4.1.2.5 | Audio-programs development to disseminate information about ILM, ensuring gender and social inclusion (GESI) dimensions during implementation and documentation of program outcome | No | No | No | No | No | No | No | No | No | Yes | Initiate radio program with success stories of women's group, dalits, IPs | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
[8 empty] | 37813 |  |  | 22 | 0 | 0% | 0% |  | 0 | 0
Outcome 4.2: Project monitoring system operates, systematically provides information on progress, and informs adaptive management to ensure results |  |  |  | Q1 | Q2 | Q3 | Q4 | 94462 | [7 empty] | 0 | 0 | Outcome 4.2: Project monitoring system operates, information on progress, and informs adaptive management to ensure results |  | Outcome 4.2: Project monitoring system operates, systematically provides information on progress, and informs adaptive management to ensure results
Output 4.2.1: Participatory planning and M&E system | 76 | 4.2.1.1: Organize project inception workshop at Kathmandu and field level/sharing meeting | [5 empty] | 6000 |  | Meeting | 1 |  | 0% |  |  |  |  | 4.2.1.1 | Carried out project results sharing workshop with findings from terminal evaluation align with phase out plan of the project | No | No | No | No | No | No | No | No | No | Yes | 1.Sensitize for inclusive participation during project communication (e.g. regular briefing on GESI perspective) 2. Ensure 33% female participation (Representation of women, dalits, ethnic and indigenous peoples) | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
| 77 | 4.2.1.2: PAC/PEC planning review workshop (Central and Field) | [5 empty] | 11538 |  | Meeting | 5 |  | 0% |  |  |  |  | 4.2.1.2 | Meetings as per prodoc, including PEC/PAC members visits to project sites focussing on PEC/PAC agendas | No | No | No | No | No | No | No | No | No | Yes | 1.Sensitize for inclusive participation during project communication (e.g. regular briefing on GESI perspective) 2. Ensure 33% female participation (Representation of women, dalits, ethnic and indigenous peoples) | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
| 78 | 4.2.1.3: Conduct periodic (trimester) workplan review and planning sessions | [5 empty] | 9231 |  | Workshop | 8 |  | 0% |  |  |  |  | 4.2.1.3 | Workshops to review project progresses/prepare quarterly and annual plan with project team and also with project stakeholders. Costs also include documentation, editing, review and printing. | No | No | No | No | No | No | No | No | No | Yes | 1.Sensitize for inclusive participation during project communication (e.g. regular briefing on GESI perspective) 2. Ensure 33% female participation (Representation of women, dalits, ethnic and indigenous peoples) | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
| 79 | 4.2.1.4: Conduct periodic and joint monitoring visits | [5 empty] | 10000 |  | Visits | 5 |  | 0% |  |  |  |  | 4.2.1.4 | Visits/travel focused on project interventions (outcomes/outputs). Costs also include documentation, editing, review and printing. | No | No | No | No | No | No | Yes; Esure meaningful participation of IPs representative | No | No | Yes | 1.Sensitize for inclusive participation during project communication (e.g. regular briefing on GESI perspective) 2. Ensure 33% female participation (Representation of women, dalits, ethnic and indigenous peoples) | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
| 80 | 4.2.1.5: Conduct Safeguard Monitoring visits | [5 empty] | 3846 |  | Visits | 2 |  | 0% |  |  |  |  | 4.2.1.5 | Multi-stakeholders including Ips, LCs, local goverments, project staff, MoFE officials - visit. Costs also include documentation, editing, review and printing. | No | No | No | No | No | No | Yes; Esure meaningful participation of IPs representative | No | No | Yes | 1.Sensitize for inclusive participation during project communication (e.g. regular briefing on GESI perspective) 2. Ensure 33% female participation (Representation of women, dalits, ethnic and indigenous peoples) | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
| 81 | 4.2.1.6: Conduct training on "participatory monitoring and evaluation" to CFUGs and relevant sub-grantees | [5 empty] | 3847 |  | Training | 1 |  | 0% |  |  |  |  | 4.2.1.6 | Training cost (e.g. resource persons, training materials, participant travel, logistics) | No | No | No | No | No | No | Yes; Esure meaningful participation of IPs representative | No | No | Yes | 1.Sensitize for inclusive participation during project communication (e.g. regular briefing on GESI perspective) 2. Ensure 50% female participation (Representation of women, dalits, ethnic and indigenous peoples) | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
| 82 | 4.2.1.7: Capacity building/training of PSU staff (on project management - WWF network standards, report writing and GESI and safeguard) | [15 empty] | 4.2.1.7 |  | No | No | No | No | No | No | No | No | No | Yes | 1.Sensitize for inclusive participation during project communication (e.g. regular briefing on GESI perspective) 2. Ensure 33% female participation (Representation of women, dalits, ethnic and indigenous peoples) | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
| 83 | 4.2.1.8: Organize Project Mid-term review workshops with all key stakeholders | [15 empty] | 4.2.1.8
| 84 | 4.9.1.9: Conduct Project Evaluations (Mid-term and terminal evaluation - GEF/SWC) | [5 empty] | 50000 |  | No of evaluation supported | 1 |  | 0% |  |  |  |  | 4.2.1.9 | WWF - Technical assistance part
[8 empty] | 94462 |  |  | 23 | 0 | 0% | 0% |  | 0 | 0
Outcome 4.3: Project lessons shared |  |  |  | Q1 | Q2 | Q3 | Q4 | 33751 | [7 empty] | 0 | 0 | Outcome 4.3: Project lessons shared |  | Outcome 4.3: Project lessons shared
Output 4.3.1: Project lessons captured and disseminated to project stakeholders and to other projects and partners | 85 | 4.3.1.1: Documentation on Traditional Knowledge associated to natural resources | PMU | [14 empty] | 4.3.1.1
| 86 | 4.3.1.2: Prepare success stories and videos of the project | PMU/DNPWC/MITFE |  |  |  |  | 15385 |  | No of stories/videos | 1 |  | 0% |  |  |  |  | 4.3.1.2 | Prepare videos and stories of the project highlighting project interventions, ensure the GESI dimensions as part of lessons and stories (Shifted $2404 to 3.1.3.3, It also includes story writng of our working site) | No | No | Reflect Ips issues and mitigation measures taken into success stories | yes; reflect on impacts of discouraging invasive species | Reflect impact of project intervention on IP, dalit and womens | Yes; take consent before story collection and disclose before dissemianation | No | No | No | yes | Ensure proper capacity building of the media to disseminate information on the importance of GESI integration in conservation | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
| 87 | 4.3.1.3: Print case studies and periodic project reports | PMU |  |  |  |  | 8957 |  | Reports | 1 |  | 0% |  |  |  |  | 4.3.1.3 | Cost includes preparing reports any policy documents review, design and printing support in PMU/MOFE/DNPWC/MITFE | No | No | No | No | No | No | No | No | No | yes | Ensure proper capacity building of the media to disseminate information on the importance of GESI integration in conservation | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
| 88 | 4.3.1.4: Provide financial support to participate in national/international scientific forum for field staff | PMU |  |  |  |  | 0 |  | visits | 2 |  | 0% |  |  |  |  | 4.3.1.4 | To be implemented through Technical Assistant through PMU recommendation to capacitate WWF-GEF staff | No | No | No | No | No | No | No | No | No | yes | Ensure 33% female participation (Representation of women, dalits, ethnic and indigenous peoples) | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
| 89 | 4.3.1.5: Provide financial support to publish journal articles | PMU | [14 empty] | 4.3.1.5 |  | No | No | No | No | No | No | No | No | No | yes | Ensure disseminate information on the importance of GESI integration in conservation | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
| 90 | 4.3.1.6: Field program implementation support & coordination | PMU/DNPWC/MITFE |  |  |  |  | 9409 |  | Month | 12 |  | 0% |  |  |  |  | 4.3.1.6 | Package includes Staff travel and DSA, coordination meeting with gov. partners, gov staffs travel and communication support, coordination meeting with IPs and local communities, travel cost/transporation and communication support to gov partners for monitoring and technical backstopping | No | No | No | No | No | No | No | No | No | yes | Sensitize for inclusive participation during project communication (e.g. regular briefing on GESI perspective) | Since the project falls under category "B", the environmental and social safeguards issues does not seem relevant largely in activities under component 1, 2 and 4, however, stakeholders will be regularly sensitized with safeguards and GESI policies/provisions of the ILaM project including process facilitation
| 91 | 4.2.1.7: Organize final project lessons sharing workshop | PMU | [14 empty] | 4.3.1.7
[8 empty] | 33751 |  |  | 16 | 0 | 0% | 0% | 0% | 0 | 0
B. Project Management Costs | [7 empty] | 383825 | [7 empty] | 0 | 0
Office and field running costs |  |  |  | Q1 | Q2 | Q3 | Q4 | 55775 | [7 empty] | 0 | 0
Project Management Unit | 56xx | Office Utility | PMU |  |  |  |  | 5500 |  | Month | 12
| 56xx | Office and Equipment Maintenance | PMU |  |  |  |  | 1500 |  | Month | 12
| 56xx | Office Insurance (including office vehicles) | PMU |  |  |  |  | 1400 |  | Time | 2
| 56xx | Office Rent | PMU |  |  |  |  | 4000 |  | Month | 12
| 56xx | Equipment Running Cost | PMU |  |  |  |  | 900 |  | Month | 12
| 56xx | Vehicle Running Costs (Vehicle Repair) | PMU |  |  |  |  | 3000 |  | Month | 12
| 56xx | Vehicle Running Costs (fuel for office purpose) | PMU |  |  |  |  | 7500 |  | Month | 12
| 56xx | Field Supplies (field gear for project staff) | PMU |  |  |  |  | 2000 |  | Package | 1
| 56xx | Photocopying | PMU |  |  |  |  | 700 |  | Month | 12
| 56xx | Postage & Shipping | PMU |  |  |  |  | 950 |  | Month | 12
| 56xx | Communications (phone, fax, internet) | PMU |  |  |  |  | 2850 |  | Month | 12
| 56xx | Supplies | PMU |  |  |  |  | 7000 |  | Month | 12
| 56xx | Field program implementation support coordination (Staffs travel and Inhouse Meeting) | PMU |  |  |  |  | 10000 |  | Month | 12
| 56xx | Advertisment/Priniting and Publication | PMU |  |  |  |  | 3906 |  | Printing | 1
| 56xx | Bank charges | PMU |  |  |  |  | 100 |  | Month | 12
| 56xx | Annual Audit | PMU |  |  |  |  | 4469 |  | Audit | 1
[8 empty] | 55775 |  |  | 149 | 0 |  |  |  | 0 | 0
|  | Capital Assets | [5 empty] | 43050 | [7 empty] | 0 | 0
| 58xx | Cupboard/File Racks (for Banke office and for Kathmandu Office) | PMU |  |  |  |  | 1500 |  | Set | 2
| 58xx | Office Board/Notice boards etc | PMU
| 58xx | Laptop (with dock-in set) | PMU/DNPWC/MoITFE/MoFE |  |  |  |  | 7500 |  | No | 6
| 58xx | Data Backup/Hard Drive | PMU |  |  |  |  | 475 |  | No | 3
| 58xx | CC Camera for PMU Office | PMU
| 58xx | Camera / Lens | PMU/DNPWC/MoITFE |  |  |  |  | 2500 |  | No | 1
| 58xx | Air conditioner with associated cost (for field office) | PMU
| 58xx | Micro-oven (for Banke) | PMU/DNPWC/MoITFE
| 58xx | Cameras/Binacular | PMU
| 58xx | Multi-function printer | PMU/DNPWC/MoITFE |  |  |  |  | 3000 |  | No | 4
| 58xx | Power back up system (for Banke) | PMU
| 58xx | Projector-Screen | PMU
| 58xx | Desktop Screen (monitor) | PMU
| 58xx | Motorcycle | PMU/DNPWC/MoITFE |  |  |  |  | 22000 |  | No. | 8
| 58xx | Account Software (Activity-wise reporting, AMC etc.) | PMU |  |  |  |  | 775 |  | Set | 1
| 58xx | Office 365 insallation, Sofware AMC etc | PMU |  |  |  |  | 775 |  | Softwares | 3
| 58xx | IT support | PMU |  |  |  |  | 775 |  | Support | 1
| 58xx | Office and restroom renovation, Kathmandu Office | PMU/MoFE/DNPWC/DoFSC/MoITFE |  |  |  |  | 3750 |  | package | 1
[8 empty] | 43050 |  |  | 30 |  |  |  |  | 0 | 0
|  | Personnel cost included in WWF Technical assistance part which also includes monitoring visit with project stakeholders, PMU staff field visit cost as approved by WWF and staff capacity development through national/international scientific forum, project terminal evaluation | [5 empty] | 285000
GRAND TOTAL (A+B) |  |  |  | YR 5 |  |  |  | 1921046 | [7 empty] | 0 | 0
|  |  | Carry-over total (unspent funds from previous year) | [10 empty] | % achieved for activities overall | 0% | Actual budget for previous project year
Request of funds for Upcoming Project Year
Note on A44: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: New Outcome
Note on C140: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Suggest putting these cost under a component
Note on G170: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Heike - in cell I170 the amount should be 285000 US $. Please edit,It is protected cell so we could not edit, thanks

## Full Project Workplan
FULL PROJECT WORKPLAN
Component | Outcome | Output | Activity # | Activities | Who | Timeline (Y1, Y2, Y3, etc.) | Budget (at activity, output, or outcome level)
COMPONENT 1: Enabling environment | Outcome 1.1. Improved inter-sectoral coordination | Output 1.1.1 Cross-sectoral coordination mechanisms established | 1.1.1.1 | Provide support to NBCC committee (ensure gender inclusive team) | MOFE/DOFSC/DNPWC/MITFE
COMPONENT 1: Enabling environment | Outcome 1.1. Improved inter-sectoral coordination | Output 1.1.1 Cross-sectoral coordination mechanisms established | 1.1.1.2 | Organize State level Biodiversity Co-ordination Committee (State 2,3,5,7 and Karnali) meetings | MOFE/DOFSC/DNPWC/MITFE
COMPONENT 1: Enabling environment | Outcome 1.1. Improved inter-sectoral coordination | Output 1.1.1 Cross-sectoral coordination mechanisms established | 1.1.1.3 | Provide technical and financial support to State Biodiversity Co-ordination committee | MOFE/DOFSC/DNPWC/MITFE
COMPONENT 1: Enabling environment | Outcome 1.1. Improved inter-sectoral coordination | Output 1.1.1 Cross-sectoral coordination mechanisms established | 1.1.1.4 | Organize inter-ministerial coordination mechanism for wildlife friendly infrastructure | MOFE/DOFSC/DNPWC/MITFE
COMPONENT 1: Enabling environment | Outcome 1.1. Improved inter-sectoral coordination | Output 1.1.1 Cross-sectoral coordination mechanisms established | 1.1.1.5 | Organize inter-state coordination (2, 3, Gandaki, 5, Karnali, 7) for NBSAP and TAL Strategy | PMU
COMPONENT 1: Enabling environment | Outcome 1.1. Improved inter-sectoral coordination | Output 1.1.1 Cross-sectoral coordination mechanisms established | 1.1.1.6 | Carry out cluster meetings with Municipalities | PMU
COMPONENT 1: Enabling environment | Outcome 1.1. Improved inter-sectoral coordination | Output 1.1.1 Cross-sectoral coordination mechanisms established | 1.1.1.7 | Conduct final review of NBSAP (2014-2020) | PMU
COMPONENT 1: Enabling environment | Outcome 1.1. Improved inter-sectoral coordination | Output 1.1.1 Cross-sectoral coordination mechanisms established | 1.1.1.8 | Provide technical and financial support to WCCB | MOFE/DOFSC/DNPWC/MITFE
COMPONENT 1: Enabling environment | Outcome 1.1. Improved inter-sectoral coordination | Output 1.1.1 Cross-sectoral coordination mechanisms established | 1.1.1.9 | Field program implementation support & coordination | PMU
COMPONENT 1: Enabling environment | Outcome 1.2 Capacity increased | Output 1.2.1 Conservation Leadership Training provided | 1.2.1.1 | Conduct training to ILM coordinators | PMU
COMPONENT 1: Enabling environment | Outcome 1.2 Capacity increased | Output 1.2.2 Training on ILM for federal and state government staff | 1.2.2.1 | Conduct training on Biodiversity conservation and monitoring | PMU
COMPONENT 1: Enabling environment | Outcome 1.2 Capacity increased | Output 1.2.2 Training on ILM for federal and state government staff | 1.2.2.2 | Conduct training on Disaster Risk Management | PMU
COMPONENT 1: Enabling environment | Outcome 1.2 Capacity increased | Output 1.2.2 Training on ILM for federal and state government staff | 1.2.2.3 | Orientation on roles and responsibilities for new park staff (senior/game scouts) | MOFE/DOFSC/DNPWC/MITFE
COMPONENT 1: Enabling environment | Outcome 1.2 Capacity increased | Output 1.2.2 Training on ILM for federal and state government staff | 1.2.2.4 | Orientation on roles and responsibilities for new divisional staff | MOFE/DOFSC/DNPWC/MITFE
COMPONENT 1: Enabling environment | Outcome 1.2 Capacity increased | Output 1.2.3 Small grants for innovation in ILM | 1.2.3.1 | Provide Individual grant (Bachelors and Master's thesis) | PMU
COMPONENT 1: Enabling environment | Outcome 1.2 Capacity increased | Output 1.2.3 Small grants for innovation in ILM | 1.2.3.2 | Provide Institutional grant to Academic Institutional and CBOs/CSOs | PMU
COMPONENT 1: Enabling environment | Outcome 1.2 Capacity increased | Output 1.2.3 Small grants for innovation in ILM | 1.2.3.3 | Provide innovation grant to the government agencies (National Park, Forest Division, Research and Training Centre) at state level | MOFE/DOFSC/DNPWC/MITFE
Component 2: Integrated Planning for Buffer Zones and Critical Corridors in TAL | Outcome 2.1 Corridor planning for TAL corridors (Brahmadev, Karnali and Kamdi) | Output 2.1.1. Biodiversity surveys, socio-economic surveys, and local stakeholder consultation for Brahmadev , Karnali, and Kamdi corridors to determine feasibility of appropriate models for community-based natural resource management | 2.1.1.1 | Conduct assessment to update biodiversity inventory and socio-economic status in corridors (incorporating GESI aspect) | PMU
Component 2: Integrated Planning for Buffer Zones and Critical Corridors in TAL | Outcome 2.1 Corridor planning for TAL corridors (Brahmadev, Karnali and Kamdi) | Output 2.1.1. Biodiversity surveys, socio-economic surveys, and local stakeholder consultation for Brahmadev , Karnali, and Kamdi corridors to determine feasibility of appropriate models for community-based natural resource management | 2.1.1.2 | Provide technical support to review existing forest encroachment status and response options considering GESI aspect | PMU
Component 2: Integrated Planning for Buffer Zones and Critical Corridors in TAL | Outcome 2.1 Corridor planning for TAL corridors (Brahmadev, Karnali and Kamdi) | Output 2.1.1. Biodiversity surveys, socio-economic surveys, and local stakeholder consultation for Brahmadev , Karnali, and Kamdi corridors to determine feasibility of appropriate models for community-based natural resource management | 2.1.1.3 | Prepare corridor/bottleneck assessment report with GESI integration | PMU
Component 2: Integrated Planning for Buffer Zones and Critical Corridors in TAL | Outcome 2.2 : Improved participatory planning for sustainable management of in Banke-Bardia complex | Output 2.2.1: Land uses, biodiversity values, forest carbon, and key threats assessed, mapped, reported and disseminated to identify priority villages and forest areas in the targeted PA buffer zones and corridors | 2.2.1.1 | Conduct participatory assessments in targeted PA buffer zones and corridors to identify priority community and forest areas | MOFE/DOFSC/DNPWC/MITFE
Component 2: Integrated Planning for Buffer Zones and Critical Corridors in TAL | Outcome 2.2 : Improved participatory planning for sustainable management of in Banke-Bardia complex | Output 2.2.1: Land uses, biodiversity values, forest carbon, and key threats assessed, mapped, reported and disseminated to identify priority villages and forest areas in the targeted PA buffer zones and corridors | 2.2.1.2 | Conduct resource mapping of CFUGs at corridor level and BZUCs | MOFE/DOFSC/DNPWC/MITFE
Component 2: Integrated Planning for Buffer Zones and Critical Corridors in TAL | Outcome 2.2 : Improved participatory planning for sustainable management of in Banke-Bardia complex | Output 2.2.1: Land uses, biodiversity values, forest carbon, and key threats assessed, mapped, reported and disseminated to identify priority villages and forest areas in the targeted PA buffer zones and corridors | 2.2.1.3 | Carry out consultations at identified communities | PMU
Component 3: Forest and HWC management in TAL | Outcome 3.1: Strengthen livelihoods and biodiversity conservation through SFM | Output 3.1.1 Training and tools to local government on SFM | 3.1.1.1 | Prepare Sustainable Forest Management Training (SFM) Manual incorporating GESI | MOFE/DOFSC/DNPWC/MITFE
Component 3: Forest and HWC management in TAL | Outcome 3.1: Strengthen livelihoods and biodiversity conservation through SFM | Output 3.1.1 Training and tools to local government on SFM | 3.1.1.2 | Provide "Training of Trainers" (TOT) to Division Forest Offices staff based on SFM Training Manual | PMU
Component 3: Forest and HWC management in TAL | Outcome 3.1: Strengthen livelihoods and biodiversity conservation through SFM | Output 3.1.1 Training and tools to local government on SFM | 3.1.1.3 | Establish Forest Management Information system (FMIS) including forest fire management | MOFE/DOFSC/DNPWC/MITFE
Component 3: Forest and HWC management in TAL | Outcome 3.1: Strengthen livelihoods and biodiversity conservation through SFM | Output 3.1.1 Training and tools to local government on SFM | 3.1.1.4 | Support the State Forest Directorate fire reporting system | MOFE/DOFSC/DNPWC/MITFE
Component 3: Forest and HWC management in TAL | Outcome 3.1: Strengthen livelihoods and biodiversity conservation through SFM | Output 3.1.1 Training and tools to local government on SFM | 3.1.1.5 | Support forest fire management through innovative tools and techniques such as leaf litter collection and composting (within targeted sites identified in component 2) | MOFE/DOFSC/DNPWC/MITFE
Component 3: Forest and HWC management in TAL | Outcome 3.1: Strengthen livelihoods and biodiversity conservation through SFM | Output 3.1.1 Training and tools to local government on SFM | 3.1.1.6 | Provide multi-year support for nursery to Division forest offices (within targeted sites identified in component 2) | MOFE/DOFSC/DNPWC/MITFE
Component 3: Forest and HWC management in TAL | Outcome 3.1: Strengthen livelihoods and biodiversity conservation through SFM | Output 3.1.2: TA to CFUGs, BZCFUGs and land holders for SFM | 3.1.2.1 | Provide training to CFUGs and BZ CFUGs for forest management implementation (including applied SFM, restoration technique - lined with 3.1.1 | PMU
Component 3: Forest and HWC management in TAL | Outcome 3.1: Strengthen livelihoods and biodiversity conservation through SFM | Output 3.1.2: TA to CFUGs, BZCFUGs and land holders for SFM | 3.1.2.2 | Conduct exchange visits for targeted BZ CFUG members (learning from successful UCs on fund mobilization and HWC management) | PMU
Component 3: Forest and HWC management in TAL | Outcome 3.1: Strengthen livelihoods and biodiversity conservation through SFM | Output 3.1.2: TA to CFUGs, BZCFUGs and land holders for SFM | 3.1.2.3 | Support BZUCs annual meetings for Bardia and Banke NP Buffer Zones (northern side) | PMU
Component 3: Forest and HWC management in TAL | Outcome 3.1: Strengthen livelihoods and biodiversity conservation through SFM | Output 3.1.2: TA to CFUGs, BZCFUGs and land holders for SFM | 3.1.2.4 | Provide coaching on "Governance and Financial management" for CFUGs of corridors and PA Buffer zones | PMU
Component 3: Forest and HWC management in TAL | Outcome 3.1: Strengthen livelihoods and biodiversity conservation through SFM | Output 3.1.2: TA to CFUGs, BZCFUGs and land holders for SFM | 3.1.2.5 | Provide support private forest development (providing seedling, irrigation, fencing) | MOFE/DOFSC/DNPWC/MITFE
Component 3: Forest and HWC management in TAL | Outcome 3.1: Strengthen livelihoods and biodiversity conservation through SFM | Output 3.1.2: TA to CFUGs, BZCFUGs and land holders for SFM | 3.1.2.6 | Support to register private forest | PMU
Component 3: Forest and HWC management in TAL | Outcome 3.1: Strengthen livelihoods and biodiversity conservation through SFM | Output 3.1.3 : Priority buffer zones and corridors managed sustainably | 3.1.3.1 | Create revolving fund to implement forest operational plans in project targeted corridors | PMU
Component 3: Forest and HWC management in TAL | Outcome 3.1: Strengthen livelihoods and biodiversity conservation through SFM | Output 3.1.3 : Priority buffer zones and corridors managed sustainably | 3.1.3.2 | Provide financial and technical support to improve livestock management (AI, fodder plant support, feeding trough, vet support, stall improvement) | PMU
Component 3: Forest and HWC management in TAL | Outcome 3.1: Strengthen livelihoods and biodiversity conservation through SFM | Output 3.1.3 : Priority buffer zones and corridors managed sustainably | 3.1.3.3 | Provide financial and technical support for management of grassland and wetland in project targeted area | PMU
Component 3: Forest and HWC management in TAL | Outcome 3.1: Strengthen livelihoods and biodiversity conservation through SFM | Output 3.1.3 : Priority buffer zones and corridors managed sustainably | 3.1.3.4 | Provide financial and technical support for river bank protection in project targeted area | PMU
Component 3: Forest and HWC management in TAL | Outcome 3.1: Strengthen livelihoods and biodiversity conservation through SFM | Output 3.1.3 : Priority buffer zones and corridors managed sustainably | 3.1.3.5 | Safeguard plan implementation | PMU
Component 3: Forest and HWC management in TAL | Outcome 3.1: Strengthen livelihoods and biodiversity conservation through SFM | Output 3.1.3 : Priority buffer zones and corridors managed sustainably | 3.1.3.6 | Provide financial and technical support to small scale green enterprises in project targeted area | PMU
Component 3: Forest and HWC management in TAL | Outcome 3.1: Strengthen livelihoods and biodiversity conservation through SFM | Output 3.1.3 : Priority buffer zones and corridors managed sustainably | 3.1.3.7 | Provide financial and technical support to develop business plan | PMU
Component 3: Forest and HWC management in TAL | Outcome 3.2: Improved HWC management | Output 3.2.1: Pilot method to reduce wildlife accidents in priority sites | 3.2.1.1 | Conduct study on the wildlife traffic accident issue | MOFE/DOFSC/DNPWC/MITFE
Component 3: Forest and HWC management in TAL | Outcome 3.2: Improved HWC management | Output 3.2.1: Pilot method to reduce wildlife accidents in priority sites | 3.2.1.2 | Install tools/facilities to pilot measures to reduce accidents | MOFE/DOFSC/DNPWC/MITFE
Component 3: Forest and HWC management in TAL | Outcome 3.2: Improved HWC management | Output 3.2.1: Pilot method to reduce wildlife accidents in priority sites | 3.2.1.3 | Support in operation and monitoring of wildlife related traffic accidents in highway | MOFE/DOFSC/DNPWC/MITFE
Component 3: Forest and HWC management in TAL | Outcome 3.2: Improved HWC management | Output 3.2.1: Pilot method to reduce wildlife accidents in priority sites | 3.2.1.4 | Support to erect fence on both sides of Sikta irrigation canal | MOFE/DOFSC/DNPWC/MITFE
Component 3: Forest and HWC management in TAL | Outcome 3.2: Improved HWC management | Output 3.2.2: Training and facilities for human wildlife conflict response | 3.2.2.1 | Prepare species-specific guidelines for HWC management | MOFE/DOFSC/DNPWC/MITFE
Component 3: Forest and HWC management in TAL | Outcome 3.2: Improved HWC management | Output 3.2.2: Training and facilities for human wildlife conflict response | 3.2.2.2 | Pictorial manual on Wildlife identification and behavior in Nepali and local dialects | MOFE/DOFSC/DNPWC/MITFE
Component 3: Forest and HWC management in TAL | Outcome 3.2: Improved HWC management | Output 3.2.2: Training and facilities for human wildlife conflict response | 3.2.2.3 | Conduct training on identification and behavior of wild animals to Divisional forest office staff | MOFE/DOFSC/DNPWC/MITFE
Component 3: Forest and HWC management in TAL | Outcome 3.2: Improved HWC management | Output 3.2.2: Training and facilities for human wildlife conflict response | 3.2.2.4 | Support Wildlife Rescue center | MOFE/DOFSC/DNPWC/MITFE
Component 3: Forest and HWC management in TAL | Outcome 3.2: Improved HWC management | Output 3.2.2: Training and facilities for human wildlife conflict response | 3.2.2.5 | Support wildlife rescue and handling equipment and training | MOFE/DOFSC/DNPWC/MITFE
Component 3: Forest and HWC management in TAL | Outcome 3.2: Improved HWC management | Output 3.2.3 : Community-based HWC mitigation and preventive action implemented | 3.2.3.1 | Conduct workshop on preventive and curative measures for HWC | MOFE/DOFSC/DNPWC/MITFE
Component 3: Forest and HWC management in TAL | Outcome 3.2: Improved HWC management | Output 3.2.3 : Community-based HWC mitigation and preventive action implemented | 3.2.3.2 | Implement measures for HWC based on prepared plans (mentha plantation, biological/virtual fencing) | PMU
Component 3: Forest and HWC management in TAL | Outcome 3.2: Improved HWC management | Output 3.2.3 : Community-based HWC mitigation and preventive action implemented | 3.2.3.3 | Support to establish community-based insurance (crop, livestock) scheme | PMU
Component 3: Forest and HWC management in TAL | Outcome 3.2: Improved HWC management | Output 3.2.3 : Community-based HWC mitigation and preventive action implemented | 3.2.3.4 | Implement community-based reporting system of HWC incidents | MOFE/DOFSC/DNPWC/MITFE
Component 3: Forest and HWC management in TAL | Outcome 3.3: Enhanced capacities of government agencies and community in curbing illegal wildlife crime | Output 3.3.1: Community Based Anti-poaching Units functional in priority areas | 3.3.1.1 | Provide support for field gear to CBAPU members | PMU
Component 3: Forest and HWC management in TAL | Outcome 3.3: Enhanced capacities of government agencies and community in curbing illegal wildlife crime | Output 3.3.1: Community Based Anti-poaching Units functional in priority areas | 3.3.1.2 | Provide technical and financial support for skill based training to CBAPU members | PMU
Component 3: Forest and HWC management in TAL | Outcome 3.3: Enhanced capacities of government agencies and community in curbing illegal wildlife crime | Output 3.3.1: Community Based Anti-poaching Units functional in priority areas | 3.3.1.3 | Establish revolving fund to initiate green enterprise for CBAPUs member (link to above activities) | PMU
Component 3: Forest and HWC management in TAL | Outcome 3.3: Enhanced capacities of government agencies and community in curbing illegal wildlife crime | Output 3.3.2: Training and operation support to Park staff, rangers on wildlife crime management | 3.3.2.1 | Update training manual on illegal wildlife crime scene management | MOFE/DOFSC/DNPWC/MITFE
Component 3: Forest and HWC management in TAL | Outcome 3.3: Enhanced capacities of government agencies and community in curbing illegal wildlife crime | Output 3.3.2: Training and operation support to Park staff, rangers on wildlife crime management | 3.3.2.2 | Conduct training to investigation officers level on Illegal wildlife crime scene management | MOFE/DOFSC/DNPWC/MITFE
Component 3: Forest and HWC management in TAL | Outcome 3.3: Enhanced capacities of government agencies and community in curbing illegal wildlife crime | Output 3.3.2: Training and operation support to Park staff, rangers on wildlife crime management | 3.3.2.3 | Support Transboundary coordination at local level | MOFE/DOFSC/DNPWC/MITFE
Component 3: Forest and HWC management in TAL | Outcome 3.3: Enhanced capacities of government agencies and community in curbing illegal wildlife crime | Output 3.3.2: Training and operation support to Park staff, rangers on wildlife crime management | 3.3.2.4 | Field program implementation support & coordination | PMU
COMPONENT 4. KNM and M&E | Outcome 4.1: Improved coordination and dialogue on integrated landscape management from the local to national level | Output 4.1.1: Information on ILM importance shared among key stakeholders | 4.1.1.1 | Organize monthly dialogue through "Jaibik Chautari" (Biodiversity Platform) at field level | MOFE/DOFSC/DNPWC/MITFE
COMPONENT 4. KNM and M&E | Outcome 4.1: Improved coordination and dialogue on integrated landscape management from the local to national level | Output 4.1.1: Information on ILM importance shared among key stakeholders | 4.1.1.2 | Organize annual technical thematic discussion session at center | MOFE/DOFSC/DNPWC/MITFE
COMPONENT 4. KNM and M&E | Outcome 4.1: Improved coordination and dialogue on integrated landscape management from the local to national level | Output 4.1.1: Information on ILM importance shared among key stakeholders | 4.1.1.3 | Establish and maintain online Landscape Knowledge Learning Platform (including project website) | PMU
COMPONENT 4. KNM and M&E | Outcome 4.1: Improved coordination and dialogue on integrated landscape management from the local to national level | Output 4.1.2: Mass awareness products on biodiversity conservation and integrated landscape management | 4.1.2.1 | Provide technical and financial support to green/eco-clubs formation and its operation | PMU
COMPONENT 4. KNM and M&E | Outcome 4.1: Improved coordination and dialogue on integrated landscape management from the local to national level | Output 4.1.2: Mass awareness products on biodiversity conservation and integrated landscape management | 4.1.2.2 | Support annual meetings of green/eco-clubs network at district level | PMU
COMPONENT 4. KNM and M&E | Outcome 4.1: Improved coordination and dialogue on integrated landscape management from the local to national level | Output 4.1.2: Mass awareness products on biodiversity conservation and integrated landscape management | 4.1.2.3 | Support special conservation events at local level | MOFE/DOFSC/DNPWC/MITFE
COMPONENT 4. KNM and M&E | Outcome 4.1: Improved coordination and dialogue on integrated landscape management from the local to national level | Output 4.1.2: Mass awareness products on biodiversity conservation and integrated landscape management | 4.1.2.4 | Sensitize media (print and TV) on integrated landscape management | PMU
COMPONENT 4. KNM and M&E | Outcome 4.1: Improved coordination and dialogue on integrated landscape management from the local to national level | Output 4.1.2: Mass awareness products on biodiversity conservation and integrated landscape management | 4.1.2.5 | Support radio program (local dialects) on ILM | PMU
COMPONENT 4. KNM and M&E | Outcome 4.2: Project Monitoring | Output 4.2.1 Participatory planning and M&E system | 4.2.1.1 | Organize project inception workshops at Kathmandu and field level | PMU
COMPONENT 4. KNM and M&E | Outcome 4.2: Project Monitoring | Output 4.2.1 Participatory planning and M&E system | 4.2.1.2 | PAC/PEC planning review workshop (Central and Field) | PMU
COMPONENT 4. KNM and M&E | Outcome 4.2: Project Monitoring | Output 4.2.1 Participatory planning and M&E system | 4.2.1.3 | Conduct periodic (trimester) workplan review and planning sessions | PMU
COMPONENT 4. KNM and M&E | Outcome 4.2: Project Monitoring | Output 4.2.1 Participatory planning and M&E system | 4.2.1.4 | Conduct periodic and joint monitoring visits | PMU
COMPONENT 4. KNM and M&E | Outcome 4.2: Project Monitoring | Output 4.2.1 Participatory planning and M&E system | 4.2.1.5 | Conduct Safeguard Monitoring visits | PMU
COMPONENT 4. KNM and M&E | Outcome 4.2: Project Monitoring | Output 4.2.1 Participatory planning and M&E system | 4.2.1.6 | Conduct training on "participatory monitoring and evaluation" to CFUGs and relevant sub-grantees | PMU
COMPONENT 4. KNM and M&E | Outcome 4.2: Project Monitoring | Output 4.2.1 Participatory planning and M&E system | 4.2.1.7 | Capacity building/training of PSU staff (on project management - WWF network standards, report writing and GESI and safeguard) | PMU
COMPONENT 4. KNM and M&E | Outcome 4.2: Project Monitoring | Output 4.2.1 Participatory planning and M&E system | 4.2.1.8 | Organize Project Mid-term review workshops with all key stakeholders | PMU
COMPONENT 4. KNM and M&E | Outcome 4.2: Project Monitoring | Output 4.2.1 Participatory planning and M&E system | 4.2.1.9 | Conduct Project Evaluations (Mid-term and terminal evaluation - GEF/SWC) | PMU
COMPONENT 4. KNM and M&E | Outcome 4.2: Project Monitoring | Output 4.2.1 Participatory planning and M&E system | 4.2.1.10 | Annual Financial Audit | PMU
COMPONENT 4. KNM and M&E | Outcome 4.3: Project lessons shared | Output 4.3.1: Lessons captured and disseminated | 4.3.1.1 | Documentation on Traditional Knowledge associated to natural resources | PMU
COMPONENT 4. KNM and M&E | Outcome 4.3: Project lessons shared | Output 4.3.1: Lessons captured and disseminated | 4.3.1.2 | Prepare success stories and videos of the project | PMU
COMPONENT 4. KNM and M&E | Outcome 4.3: Project lessons shared | Output 4.3.1: Lessons captured and disseminated | 4.3.1.3 | Print case studies and periodic project reports | PMU
COMPONENT 4. KNM and M&E | Outcome 4.3: Project lessons shared | Output 4.3.1: Lessons captured and disseminated | 4.3.1.4 | Provide financial support to participate in national/international scientific forum for field staff | PMU
COMPONENT 4. KNM and M&E | Outcome 4.3: Project lessons shared | Output 4.3.1: Lessons captured and disseminated | 4.3.1.5 | Provide financial support to publish journal articles | PMU
COMPONENT 4. KNM and M&E | Outcome 4.3: Project lessons shared | Output 4.3.1: Lessons captured and disseminated | 4.3.1.6 | Field program implementation support & coordination | PMU
COMPONENT 4. KNM and M&E | Outcome 4.3: Project lessons shared | Output 4.3.1: Lessons captured and disseminated | 4.3.1.7 | Organize final project lessons sharing workshop | PMU