
JUSTIFICATION FOR CO-FINANCING BELOW 35% AT MID-TERM REVIEW
Project Title: Promoting Sustainable Land Management (SLM) Through Strengthening Legal and Institutional Framework, Capacity Building and Restoration of Most Vulnerable Mountain Landscapes (GEF 9759)
The co-financing expenditure reported remains the same, below 35%. This is primarily due to delays in the implementation of project activities, which were significantly impacted by several external and institutional factors up to 2023:
The COVID-19 Pandemic caused substantial disruptions in project execution, and stakeholder engagement, which in turn delayed planned co-financed activities. In addition, from the project development until MTR, five ministers for environment have changed (Mr. Bashkim Ameti, Mr. Sadulla Duraki, Mr. Naser Nuredini, Ms. Kaja Shukova and the current minister Mr. Izet Mexhiti), also the changes of the National project team.
The Project Team is working to accelerate implementation and expect increased co-financing in the upcoming reporting period.

