FAO/GLOBAL ENVIRONMENT FACILITY

PROJECT DOCUMENT

| PROJECT TITLE: Contributing to the Integrated Management of Biodiversity in the Pacific Region of Colombia to Build Peace PROJECT CODE: GCP/COL/061/GFF |  |  |  |
| --- | --- | --- | --- |
| COUNTRY: Colombia |  |  |  |
| FINANCING PARTNER: GEFTF |  |  |  |
| FAO / UNIDO Project ID: 638260 (FAO) 160054 (UNIDO) |  | GEF/LDCF/SCCF Project ID: 9441 |  |
| EXECUTING PARTNERS: Ministry of the Environment and Sustainable Development, National Natural Parks, and Pacific SIRAP (IIAP, INVEMAR, CARs) |  |  |  |
| Expected EOD (Starting Date): |  |  |  |
| Expected NTE (End Date): |  |  |  |
| CONTRIBUTION TO FAO’s STRATEGIC FRAMEWORK: | a. Strategic Objective/Organizational Result: Strategic Objective 2. Make agriculture, forestry and fisheries more productive and sustainable. Outputs 20101, 20102, 20202. Strategic Objective 3. Reduce rural poverty. Output 30102 b. Regional Result/Priority Areas: Regional Initiative 3. Sustainable Agriculture and resilient to climate change c. Country Programming Framework Outcome: Priority area 2: Natural resources and governance of forests, land, and water |  |  |
| GEF/LDCF/SCCF Focal Area: Biodiversity, Land Degradation, and Sustainable Forest Management |  |  |  |
| GEF/LDCF/SCCF Strategic Objectives: BD-1, BD-4, LD-3, SFM-1, SFM-2 |  |  |  |
| Environmental and social risk classification (insert √): Low risk (√) Moderate risk High risk |  |  |  |
| Financing Plan: GEF/LDCF/SCCF allocation: Co-financing: Ministry of Environment and Sustainable Development National Natural Park of Colombia Institute of Environmental Research of Pacific Institute of Marine and Coastal Research Departmental Government of Nariño Departmental Government of Chocó Regional Autonomous Corporation of Risaralda Regional Autonomous Corporation of Valle del Cauca Regional Autonomous Corporation of Chocó Regional Autonomous Corporation of Nariño Mayor Communal Council of Alto San Juan Communal Council of the Cacarica River watershed Resguardo of the La Sierpe Community Resguardo of Calle Santa Rosa Communal Council of Bajo Mira and Frontera Corporación Biocomercio Sostenible BIOINNOVA San Cipriano Foundation Patrimono Natural – Biodiversity and Protected Areas Fund United Nations Industrial Development Organization United Nations Food and Agriculture Organization Sub-total co-financing: Total Budget: |  |  | 7.562.558 USD 1,196,757 USD 1,548,715 USD 484,838 USD 147,943 USD 4,719,870 USD 168,845 USD 410,088 USD 5,871,918 USD 3,547,790 USD 6,640,426 USD 170,010 USD 118,748 USD 40,500 USD 157,611 USD 395,926 USD 731,768 USD 108,488 USD 909,643 USD 3,223,765 USD 1,710,000 USD 32,303,649USD 39,866,207USD |
| Executive Summary The project objective is to mainstream the sustainable use and conservation of biodiversity and the provision of ecosystem services that support human welfare and vulnerable landscapes of the Colombia’s Pacific region in view of generating global and local environmental benefits and supporting the peace process. The project will be implemented in five biodiversity conservation and use mosaics (MUCBs) in the Colombian Pacific region, in the departments of Nariño, Cauca, Valle del Cauca, Risaralda, and Chocó, creating conditions for replicating results at the regional and national levels. The Katíos – Caoba, Farallones – Calima, and Cabo Manglares – Gran Familia Awá MUCBs will have full intervention; while the Serranía de los Paraguas – Tatamá and Munchique – Río Saija MUCBs will have partial intervention. The general project strategy is based on conservation mosaics and a green business approach. In the former, this approach will enable the integrated management of a geographical area by implementing actions to reduce ecosystem fragmentation and degradation, as well as building social bridges for the effective management and administration of protected areas (PAs) and complementary conservation strategies (CCSs). The green business approach will allow a linkage of biodiversity-derived products with markets (subnational, national, and international), creating sustainable economic alternatives for the communities and promoting biodiversity conservation and sustainable forest and land management. The project strategy consists of four interrelated components. Component 1 is focused on harmonizing territorial management tools to safeguard the cultural, biological, and ecosystem services diversity of the Colombian Pacific region, and strengthening institutional and community capacities. Component 2 provides support for strengthening governance mechanisms in the PAs and improving their management effectiveness; it also will support voluntary CCSs (primarily those developed by communities) in terms of their regulatory process for their formalization as territorial conservation strategies and their management; together with the declaration of new PAs they will contribute to national conservation goals. Component 3 will support sustainable economic alternatives based on production and/or use of biodiversity-derived products that improve the community’s quality of life; primarily those communities residing in PAs’ buffer zones and that were affected by Colombia’s armed conflict. Finally, Component 4 will support the development of participatory action plans for each MUCB and the implementation of a communication strategy appropriate to the context of each MUCB that enables the dissemination of good practices and knowledge resulting from project implementation. |  |  |  |

SECTION 1 – PROJECT RATIONALE	10

1.1 PROJECT CONTEXT	10

1.2 THE CURRENT SITUATION	28

1.3 THE GEF ALTERNATIVE	44

1.4 LESSONS LEARNED	84

1.5 STRATEGIC ALIGNMENT	86

SECTION 2 – FEASIBILITY	91

2.1 ENVIRONMENTAL & SOCIAL RISK ASSESSMENT	91

2.2 RISK MANAGEMENT	91

SECTION 3 – IMPLEMENTATION AND MANAGEMENT ARRANGEMENTS	93

3.1 INSTITUTIONAL ARRANGEMENTS	93

3.2 IMPLEMENTATION ARRANGEMENTS	93

3.3 PLANNING AND FINANCIAL MANAGEMENT	100

3.4 PROCUREMENT	104

3.5 MONITORING AND REPORTING	105

3.6	EVALUATION PROVISIONS	110

3.7 COMMUNICATION AND VISIBILITY	111

SECTION 4 – SUSTAINABILITY OF RESULTS	112

4.1 SOCIAL SUSTAINABILITY	112

4.2 ENVIRONMENTAL SUSTAINABILITY	113

4.3 FINANCIAL AND ECONOMIC SUSTAINABILITY	114

4.4 SUSTAINABILITY OF CAPACITY DEVELOPMENT	114

4.5 APPROPRIATENESS OF TECHNOLOGIES INTRODUCED and COST/EFFECTIVENESS	115

4.6 INNOVATIVENESS, REPLICATION and SCALE-UP	115

APPENDIX 1: RESULTS FRAMEWORK	117

APPENDIX 2: WORK PLAN	147

APPENDIX 3: PROJECT BUDGET	158

APPENDIX 4: RISK MATRIX	159

APPENDIX 5: ENVIRONMENTAL AND SOCIAL RISK ASSESSMENT	167

APPENDIX 6: ENVIRONMENTAL AND SOCIAL RISK MANAGEMENT PLAN	172

APPENDIX 7. TERMS OF REFERENCE (Indicative)	175

APPENDIX 8. MAPS OF THE PROJECT INTERVENTION AREAS	197

APPENDIX 9. STAKEHOLDER ENGAGEMENT PLAN AND CONSULTATION WITH INDIGENOUS, BLACK, AND RURAL COMMUNITIES	202

APPENDIX 10. DETAILED CARBON CALCULATION	219

APPENDIX 11. METHODOLOGY FOR THE SELECTION OF THE PROJECT INTERVENTION AREAS	222

APPENDIX 12. ANALYSIS OF POTENTIAL BIODIVERSITY-DERIVED PRODUCTS	225

APPENDIX 13. GENDER MAINSTREAMING ROADMAP	238

APPENDIX 14: ENVIRONMENTAL AND SOCIAL MANAGEMENT PLAN (ESMP) UNIDO COMPONENT	253

Acronyms

| ADR | Rural Development Agency (Acronym in Spanish) |
| --- | --- |
| AEMAPPS | Protected Areas Management Effectiveness Tool with Social Participation (Acronym in Spanish) |
| ANLA | National Environmental Licensing Authority (Acronym in Spanish) |
| ART | National Land Agency (Acronym in Spanish) |
| AUNAP | Special Administrative Unit – National Agriculture and Fishing Authority (Acronym in Spanish) |
| AWP/B | Annual Work Plan and Budget |
| BH | Budget Holder |
| CAR | Regional Autonomous Corporation (Acronym in Spanish) |
| CARDER | Regional Autonomous Corporation of Risaralda (Acronym in Spanish) |
| CCS | Complementary Conservation Strategies |
| CDB | Convention on Biological Diversity |
| CDS | Sustainable Development Corporation (Acronym in Spanish) |
| CEPF | Critical Ecosystems Partnership Fund |
| CI | Conservation International |
| CODECHOCÓ | Regional Autonomous Corporation for Sustainable Development of Chocó (Acronym in Spanish) |
| CONPES | National Council of Economic and Social Policy (Acronym in Spanish) |
| CRC | Regional Autonomous Corporation of Cauca (Acronym in Spanish) |
| CORPONARIÑO | Regional Autonomous Corporation of Nariño (Acronym in Spanish) |
| CSNR | Civil Society Natural Reserve |
| CSO | Civil Society Organization |
| CVC | Regional Autonomous Corporation of Valle del Cauca (Acronym in Spanish) |
| DANE | National Statistics Administrative Department (Acronym in Spanish) |
| DNP | National Department of Planning (Acronym in Spanish) |
| DTPA | Territorial Direction – Pacific (Acronym in Spanish) |
| EOT | Territorial Planning Scheme (Acronym in Spanish) |
| ESSPP | Environmental and Social Safeguards Policies and Procedures |
| FAO | Food and Agriculture Organization of the United Nations |
| FEDECACAO | National Federation of Cocoa Growers (Acronym in Spanish) |
| FEDECOCO | National Federation of Coconut Producers, Traders and Small Industries of Colombia (Acronym in Spanish) |
| FEDEGAN | Colombian Federation of Cattle Ranchers (Acronym in Spanish) |
| FEDEMADERAS | National Federation of the Timber Industry (Acronym in Spanish) |
| FEDEPALMA | National Federation of Oil Palm Growers (Acronym in Spanish) |
| FFEM | French Facility for Global Environment |
| FFS | Flora and Fauna Sanctuary |
| FFS | FAO Farmers Field School |
| FLO | Funding Liaison Officer |
| FPIC | Free, Prior and Informed Consent |
| FPMIS | Field Programme Management Information System |
| GDP | Gross Domestic Product |
| GEF | Global Environment Facility |
| GHG | Greenhouse Gas |
| GIBSE | Integral Management of Biodiversity and Ecosystem Services (Acronym in Spanish) |
| GIS | Geographic Information System |
| ha | Hectare(s) |
| IAvH | Alexander Von Humboldt Institute of Research on Biological Resources (Acronym in Spanish) |
| ICA | National Institute of Agriculture and Livestock (Acronym in Spanish) |
| IDEAM | Institute of Hydrology, Meteorology and Environmental Studies (Acronym in Spanish) |
| IIAP | Institute of Environmental Research of the Pacific (Acronym in Spanish) |
| IINB | Initiative to Support Biodiversity Ideas and Businesses (Acronym in Spanish) |
| IMND | Integrated Management National District |
| IMRD | Integrated Management Regional District |
| INCODER | Colombian Institute of Rural Development (Acronym in Spanish) |
| INVEMAR | Institute of Marine and Coastal Research José Benito Vives de Andreis (Acronym in Spanish) |
| INVIMA | National Food and Drug Surveillance Institute (Acronym in Spanish) |
| IUCN | International Union for Conservation of Nature |
| KBA | Key Biodiversity Area |
| km | Kilometer(s) |
| km2 | Square kilometer(s) |
| LCI | Living Conditions Index |
| KOICA | Korea International Cooperation Agency |
| LoA | Letters of Agreement |
| l/s-km2 | Liters per second per square kilometer |
| LTO | Lead Technical Officer |
| m3 | Cubic meter(s) |
| m3/s | Cubic meters per second |
| MADR | Ministry of Agriculture and Rural Development (Acronym in Spanish |
| MADS | Ministry of Environment and Sustainable Development (Acronym in Spanish) |
| MTR | Mid-term review |
| METT | Management Effectiveness Tracking Tool |
| mm | Millimeter(s) |
| Mm3 | Million cubic meters |
| MPI | Multidimensional Poverty Index |
| MUCB | Biodiversity Use and Conservation Mosaic (Acronym in Spanish) |
| MUCBTC | MUCB Technical Committee |
| NDP | National Development Plan |
| NGO | Non-governmental Organization |
| NNP | National Natural Park |
| NPD | National Project Director |
| NPFR | National Protective Forestry Reserve |
| NR | Natural Reserve |
| PA | Protected Area |
| PBO | Peace Building Overview |
| PBOT | Basic Plan for Territorial Planning (Acronym in Spanish) |
| PC | Project Coordinator |
| PDET | Development Programs with Territorial Approach (Acronym in Spanish) |
| PGAR | Regional Environmental Management Plan (Acronym in Spanish) |
| PGS | Participatory Guarantee Systems |
| PIF | Project Identification Form |
| PIR | Project Implementation Report |
| PIU | Project Implementation Unit |
| PNGIBSE | National Policy for Biodiversity and Ecosystem Services Management (Acronym in Spanish) |
| PNN | National Natural Parks of Colombia (Acronym in Spanish) |
| PNNV | National Green Business Plan (Acronym in Spanish) |
| POF | Forest Zoning Plan (Acronym in Spanish) |
| POMIUAC | Planning and Integrated Management Plan of the Coastal Environmental Unit (Acronym in Spanish) |
| POT | Territorial Zoning Plans (Acronym in Spanish) |
| PPG | Project Preparation Grant |
| ppm | Parts per million |
| PPR | Project Progress Report |
| PRAIS | Performance Review and Assessment of Implementation System |
| PRODOC | Project Document |
| PSC | Project Steering Committee |
| PTF | Project Task Force |
| PTP | Productive Transformation Program (Acronym in Spanish) |
| PTT | Project Technical Team |
| REDD+ | Reducing Emissions from Deforestation and Forest Degradation |
| RFPR | Regional Forestry Production Reserve |
| RNP | Regional Natural Park |
| RRI | Integral Rural Reform (Acronym in Spanish) |
| RTC | Regional Technical Committee |
| SAMP | Subsystem of Marine Protected Areas (Acronym in Spanish) |
| SCD | Soil Conservation District |
| SFM | Sustainable Forest Management |
| SIAC | Environmental Information System of Colombia (Acronym in Spanish) |
| SIAT_PC | System of Territorial Environmental Information of the Colombian Pacific Region (Acronym in Spanish) |
| SIDAP | Departmental System of Protected Areas (Acronym in Spanish) |
| SILAP | Local System of Protected Areas (Acronym in Spanish) |
| SINA | National Environmental System (Acronym in Spanish) |
| SINAP | National System of Protected Areas (Acronym in Spanish) |
| SINCHI | Amazonian Institute of Scientific Research (Acronym in Spanish) |
| SIRAP | Regional System of Protected Areas (Acronym in Spanish) |
| SIRAP Pacific | Regional System of Protected Areas of the Pacific (Acronym in Spanish) |
| SLM | Sustainable Land Management |
| SPNN | System of National Natural Parks of Colombia (Acronym in Spanish) |
| SPS | Sustainable Production System |
| TE | Terminal evaluation |
| TORs | Terms of reference |
| UBN | Unsatisfied Basic Needs |
| UEBT | Union for Ethical BioTrade |
| UMAIC | Unit of Information Management and Analysis (Acronym in Spanish) |
| UNDP | United Nations Development Programme |
| UNDSS | United Nations Department of Safety and Security |
| UNFCCC | United Nations Framework Convention on Climate Change |
| UNIDO | United Nations Industrial Development Organization |
| UNREDD+ | United Nations Collaborative Programme on Reducing Emissions from Deforestation and Forest Degradation |
| URT | Land Restitution Unit (Acronym in Spanish) |
| UPRA | Planning Unit of Rural Land, Land Adaptation, and Farming Uses (Acronym in Spanish) |
| USD | USA dollar |
| VOC | Conservation Targets (Acronym in Spanish) |
| WCS | Wildlife Conservation Society |
| WS | Wildlife Sanctuary |
| WWF | World Wide Fund for Nature |
| ZOMAC | Zones Most Affected by the Conflict (Acronym in Spanish) |

# SECTION 1 – PROJECT RATIONALE

## 1.1 PROJECT CONTEXT

1.1.1. National context

Colombia is one of the 17 most biodiverse countries in the world and is home to approximately 15% of the planet’s endemic species. Colombia has 18 ecological regions and 65 different types of ecosystems. Protected areas (PAs) and indigenous territories represent 41% of the country’s territory and contain some of the highest levels of biodiversity in the world. The country’s territory encompasses 2,070,408 square kilometers (km2) and is divided geographically and politically into 32 departments, 1,096 municipalities, 5 districts, and 20 departments; the country’s population is approximately 47 million. Colombia borders five countries by land and 11 countries by sea, and is the only South American country with both Pacific and Atlantic coasts.

The Pacific region of Colombia is a strip of land that forms part of the ecoregional complex of the Chocó-Darién, which is one of the most biodiverse areas of the world, encompassing approximately 17 million hectares (ha). In biogeographic terms, the Colombian Pacific region is located at the intertropical confluence zone between the Pacific Ocean to the west, and the western mountain chain of the Colombian Andes to the east. In the northwest the Pacific region serves as the border between Colombia and Panama; in the northeast, it is the transition zone between the tropical rainforest and dry forest ecosystems; in the west it comprises Pacific Ocean; and in the south it serves as the border between Colombia and Ecuador. In this region, tropical rainforest is predominant and corresponds to the Pacific hydrographic area with annual precipitation levels between 3,000 and 12,000 millimeters (mm) on a wide altitude gradient. Multiple basins are found in this hydrographic area corresponding to the departments of Chocó, Valle del Cauca, Cauca, and Nariño; with average monthly flow values ranging from 2,186 cubic meters per second (m3/s) to 3.35 m3/s. Figure 1 is a map of the Colombian Pacific region (Regional System of Protected Areas [SIRAP, Spanish acronym] Pacific Management Area).

- Figure 1. Colombian Pacific Region (SIRAP Pacific Management Area)

Environmental context

The mountain and coastal areas of the Colombian Pacific region have a predominance of natural ecosystems; this region comprises 17% of the Colombian land mass and contains 8% of the country’s forests. This region is recognized worldwide as a reservoir of great biological and cultural diversity and is part of the Tumbes-Chocó-Magdalena “hot spot.” It is also part of a larger unit known as the Chocó biogeographic region. The high levels of biodiversity are due to a series of conditions that include natural and geological characteristics, geomorphological aspects, climate conditions, and biogeography. The Colombian Pacific region also has large variety of human settlement patterns,,.

This region, along with other hydrographic areas of the country, such as the Amazon and low Cauca areas, has the greatest capacity to retain moisture and maintain water regulation conditions. The hydric output of the Pacific region is the highest in the country and is estimated at 116.2 liters per second per square kilometer (l/s-km2). The Pacific region supplies 283,201 million cubic meters (Mm3) of water, which is 14% of the country’s total water supply.

The types of forest present in the Colombian Pacific region as per the composition of the plant associations are homogeneous and heterogeneous forests. The term homogenous refers to the cativa tree forests, mangroves, natal, and guandal forests. The term heterogeneous refers to the tropical rainforests of the Andean and Sub-Andean zones (17% of the region’s terrestrial ecosystems), basal forests (54%), riparian forests (8%), dry forests (0.2%), and páramos (0.8%), among others.

The Colombian Pacific region has one of the highest levels of endemic plants on the planet: 25% of the flora in this region does not exist anywhere else in the world, a phenomenon that is particularly true for the Anthurium family and related species (Araceae), orchids (Orchidaceae), palms (Cyclanthaceae), and bromeliads (Bromeliaceae). According to data compiled by the GEF project Conservation of Biodiversity in the Chocó Biogeographic Region (1992-1998; GEF ID 366), the Chocó biogeographic region contains 15% of the total plant species described globally for the 36 plant families studied.

Although the regional fauna is not as well known, it is also rich, particularly due to the large volume of terrestrial invertebrates that are as yet unclassified. There are 353 known species of day butterflies of the 3,300 species reported for the Neotropic. Among vertebrates, amphibians are very diverse compared with other Neotropical regions. It is estimated that the Pacific region contains almost 11% of all bird species known in the world and 56% of the Colombian species. The region contains 176 species of mammals, compared with 896 species reported for the Neotropic. It should be noted that many of these species are limited in their distribution and range, are endemic to the region or more specific places, and constitute a resource that has traditionally been used by the inhabitants.

The Colombian Pacific region has a coastline that spans 1,544 kilometers (km), with its coastal and interior area covering 8,455 km2. The region encompasses 359,948 km2 of territorial waters, which correspond to 18% of the national territory. The Pacific region comprises 16 coastal municipalities. In physiographic terms, the Pacific coast has two distinct features: 1.) In the northern region between the border with Panamá and the Corrientes cape, with steep and high-relief coastal areas that are approximately 374 km in length. 2.) In the southern region towards Ecuador the coast is low, alluvial, with floodplains covered with mangroves and a dense drainage network made up of rivers and estuaries; there are some cliffs in Málaga, Buenaventura, and Tumaco bays.

Among the main marine-coastal ecosystems and biotopes characteristic of the region are mangroves (47% of total coastal ecosystems area), coral reefs, beaches (sandy, sandy-muddy, rocky), sea grass prairies, soft bottoms (89% of total marine ecosystems), rocky or steep complexes, coastal estuaries and lagoons, and pelagic areas. These ecosystems are rich in animal and plant species that form the basis of the local economy, provide indigenous communities with the means for their subsistence to supply national and international markets.

The soils of the Colombian Pacific region are typically poor or deficient, and are best fit for forestry activities, and are considered globally unique because of their interaction with salt water, fresh water and the region’s biomass. The degradation processes that these soils are undergoing include compaction, contamination, loss of organic matter, salinization, and desertification. The region is also known for its contribution to mitigate climate change at the local and global levels.

Socioeconomic context

Despite the fact that the Colombian Pacific region is rich in biodiversity and natural resources, the current levels of poverty, social inequality, and marginalization are the highest in the country. The Chocó is the poorest department in the country with a poverty rate of 68.0%, followed by Cauca at 62.1%, Nariño at 47.6%, and Valle del Cauca at 26.9%. This situation becomes even more critical in rural areas, which have high levels of food insecurity and malnutrition that are due to a lack of availability and access to a diversified source of food, particularly for the most vulnerable inhabitants. This region, particularly the Chocó, contributes the lowest per capita income nationally. In 2013, the Chocó contributed only 0.4% of the total Gross Domestic Product (GDP), which is one of the lowest in the country. The five pillars of the regional economy in 2014 were a) social, community, and personal services (34.5%); b) mining and quarries (23.9%); c) agriculture and livestock (13.45%); d) restaurants and hotels (7.5%); and e) construction (5.9%). In terms of business and manufacturing, the region’s contribution was only 1.9% and 1.3%, respectively. The resources and activities practiced within the region (other than extraction) are representative of indigenous and black populations who mainly live in rural areas and consist of fishing, hunting, and small-scale agriculture; these activities do not comprise a significant share of the GDP and are generally not visible at the national level. According to data from the National Statistics Administrative Department (DANE, according to its Spanish acronym), the region rated the highest Multidimensional Poverty Index (MPI) in 2013 (53.8%), constituting more than half of the entire country’s MPI. With regard to the Unsatisfied Basic Needs index (UBN), the Colombian Pacific region rated 65.17%, which is considerably higher than the UBN for the entire country (27.78%); additionally, the Chocó was rated with an UBN at 79.19% (the highest in the region), followed by the Pacific sub-regions of Nariño and Cauca at 77.17 % and 68.47 %, respectively.

In addition, the region’s gold resources have been exploited for more than four centuries. The extracted gold is sent through national or international channels where its value increases; however, none of the capital gains generated are returned to the areas of local extraction/production. The same is true for the exploitation of timber and fishing resources, which has led to the extinction or near extinction of many plant and animal species. This extraction-based economy creates false expectations of wealth and prevents the understanding that these types of use of natural resources are not sustainable and will adversely affect local inhabitants’ food security.

Institutional framework

The National Environmental System of Colombia (SINA, according to its Spanish acronym) was established under Act 99/1993 with the purpose of granting greater authority, resources, and tools for environmental management. SINA integrates the different public, social, and private stakeholders involved in environmental issues to promote a sustainable development model through decentralized, democratic, and participatory environmental management. SINA is led by the Ministry of Environment and Sustainable Development (MADS, according to its Spanish acronym) and includes the National Natural Parks of Colombia (PNN, according to its Spanish acronym) and the National Environmental Licensing Authority (ANLA, according to its Spanish acronym) at the central level. The decentralized level includes the Institute of Hydrology, Meteorology, and Environmental Studies (IDEAM, according to its Spanish acronym), the Institute of Marine and Coastal Research José Benito Vives de Andreis (INVEMAR, according to its Spanish acronym), the Alexander Von Humboldt Institute of Research on Biological Resources (IAvH, according to its Spanish acronym), the Amazonian Institute of Scientific Research (SINCHI, according to its Spanish acronym), and the Institute of Environmental Research of the Pacific (IIAP, according to its Spanish acronym). At the regional level, there are the Regional Autonomous Corporations (CARs, according to its Spanish acronym) and the Sustainable Development Corporations (CDSs, according to its Spanish acronym).

The MADS is the government agency charged with defining the National Environmental Policy to promote the recovery, conservation, protection, planning, management, use and exploitation of renewable natural resources, ensuring sustainable development and the right of all citizens to use and inherit a healthy environment. Areas of focus within the MADS include issues around development of green businesses, soils and forest conservation and management, marine-coastal areas planning and management, conservation and management of biodiversity and strategic ecosystems, sustainable land management (SLM), reduction of greenhouse gas (GHG) emissions, biosphere reserves management, sustainable forest management (SFM), genetic resources, sustainable production alternatives, and policy development.

The PNN is a unit of the MADS with administrative and financial autonomy and national jurisdiction, and which is responsible for administering and managing the System of National Natural Parks (SPNN, according to its Spanish acronym) and coordinating the National System of Protected Areas (SINAP, according to its Spanish acronym). SINAP is: “the set of protected areas, social actors and management strategies and tools that articulate them to contribute as a whole to accomplish the country’s conservation objectives. It includes all the protected areas of public, private or communal governance, and those of national, regional or local management scope”. The management categories for the PAs correspond to public governance at the national and regional levels. They are as follows: 1) PAs within the SPNN, which include national natural parks, wildlife and plant sanctuaries, natural reserves, unique natural areas and park roads; 2) protected forest reserves; 3) regional natural parks; 4) integrated management districts; 5) soil conservation districts; and 6) recreational areas. The categories of private governance correspond to the Natural Reserves of Civil Society (RNSC, according to its Spanish acronym). SINAP is made up of six regional PA subsystems, which include (or may include) thematic subsystems of PAs that can be defined based on a geographic criterion or other criteria. The regional subsystems of PAs are recognized as the set of national, regional and local, public or private PAs existing in the zones determined according to the regionalization established at the country level, and the social and institutional stakeholders and the strategies that integrate them.

The mission of the Ministry of Agriculture and Rural Development (MADR, according to its Spanish acronym) is to develop, coordinate, and evaluate policies that promote the competitive, equitable, and sustainable development of agriculture and livestock, forestry, fishing, and rural development processes using criteria for decentralization, agreement, and participation that contribute to improving the quality of life of the Colombian population. The MADR’s affiliated agencies are the following: the National Agriculture and Livestock Institute (ICA, according to its Spanish acronym); the Land Restitution Unit (URT, according to its Spanish acronym); the Special Administrative Unit – National Agriculture and Fishing Authority (AUNAP); Rural Development Agency (ADR, according to its Spanish acronym); National Land Agency (ART); the Planning Unit of Rural Land, Land Adaptation, and Farming Uses (UPRA, according to its Spanish acronym).

The Departmental Governments are mandated to manage and promote the integral development of all inhabitants through the adoption and execution of plans and programs that foster economic growth and sustainable social development and create the conditions needed for peaceful coexistence, jointly with national, regional, and municipal authorities, and civil society organizations (CSOs). The departments of Chocó, Valle del Cauca, Risaralda, Cauca, and Nariño comprise the project’s intervention area, and their departmental governments are among the project’s stakeholders.

The CARs are the main environmental authorities in their respective regions. CARs are autonomous corporate entities that, because of their characteristics, constitute a similar ecosystem geographically or constitute a geopolitical, biogeographic or hydrogeographic unit, with administrative and financial autonomy and patrimony and legal status, assigned by law to administer issues related to the environment and renewable natural resources and the promotion of their sustainable development according to the MADS legal provisions and policies. The PA’s buffer zones are under the jurisdiction of the CARs, in coordination with the PNN. The departmental PAs are under the jurisdiction of the CARs; for example, if a municipal area is placed under consideration to become part of the SINAP, the respective CAR coordinates with the municipal councils that are responsible for declaring them as such and promotes them to the regional category. Likewise, CARs implement local initiatives addressing the preservation and sustainable use of natural resources, water resources and strategic ecosystems management, and biodiversity conservation. The CARs that are part of this project are as follows: the Regional Autonomous Corporation for the Sustainable Development of the Chocó (CODECHOCÓ, according to its Spanish acronym), the Regional Autonomous Corporation of Valle del Cauca (CVC, according to its Spanish acronym), the Regional Autonomous Corporation of Risaralda (CARDER, according to its Spanish acronym), the Regional Autonomous Corporation of Cauca (CRC, according to its Spanish acronym), and the Regional Autonomous Corporation of Nariño (CORPONARIÑO, according to its Spanish acronym).

SIRAP Pacific is the Regional System of Protected Areas of the Colombian Pacific region that is integrated by six CARs, PNN, IIAP, INVEMAR, representatives of the region’s black and indigenous communities, departmental governments, and nongovernmental organizations (NGOs). Since 2007 it has served to integrate stakeholders, PAs, and CCS in rural and urban areas of the Colombian Pacific region, and has as its main objective the conservation of biodiversity, ecosystem services, nature, and culture within a context that seeks stronger governance and livelihoods of local communities.

Small-, medium-, and large-scale private agriculture and livestock producers are represented by several associations at the national, subnational, and local levels. The Colombian Federation of Cattle Ranchers (FEDEGAN, according to its Spanish acronym) consists of regional and local cattle rancher organizations, as well as other types of entities related to cattle ranching across the country. The National Federation of Oil Palm Growers (FEDEPALMA, according to its Spanish acronym) supports and protects palm growers’ interests and facilitates the competitiveness of the oil palm industry to improve the quality of life in communities involved in production activity. The National Federation of the Timber Industry (FEDEMADERAS, according to its Spanish acronym) represents the country’s forestry, timber, and furniture sector, and brings together the suppliers of goods and services for this sector in the country. FEDEMADERAS also includes reforestation business, developers, manufacturers and sellers of wood furniture and other products, and the black communities that are responsible for forest management. The National Federation of Cocoa Growers (FEDECACAO, according to its Spanish acronym) protects the interests of Colombian cocoa growers by contributing to their integral development; offering commercial, scientific, technological, social, environmental, and cultural products and services; and by implementing rural extension activities with national and international support to allow further development of the cocoa subsector. The National Federation of Coconut Producers, Traders, and Small Industries of Colombia (FEDECOCO, according to its Spanish acronym) protects the collective interests and income of its members, and guides, organizes, fosters, and regulates agricultural development and growth using collaborative and participatory mechanisms, while promoting solidarity and economic, scientific, technological, industrial, environmental, and commercial initiatives by the rural sector through more efficient agricultural industry best practices.

Various NGOs are developing activities related to socioeconomic development and environmental conservation in the Colombian Pacific region, they are as follows: World Wide Fund for Nature (WWF), Wildlife Conservation Society (WCS), Conservation International (CI), Fundación Natura, BIOINNOVA, Sustainable Bio-Commerce Corporation, Serraniagua Corporation, FEDCA, community and indigenous councils, among others.

The black and indigenous peoples form organizations that represent their interests at the national, subnational, and local levels. In the prioritized areas of the project there are 71 communal councils and 58 indigenous councils. The indigenous peoples include the Emberá, Emberá Katío, Emberá Chamí, Emberá Dobida, Eperara Siapidara, Waunan, Kuna Tule, Nasa, Coconuco, Pasto, Kamentsa, Coreguaje, and Awá; they are organized in reservations (resguardos), settlements, or indigenous communities (parcialidades) that are rendered non-prescriptive, cannot be seized, and are unalienable through Acts 89 of 1890, 160 of 1994, Act 21 of 1991, and Act 70 of 1993. They have their own traditional authorities and government units such as cabildos, as well as their own planning instruments such as safeguard plans and life plans.

Blacks are organized into collective territories, which are held with formal land tittles or without land tittles as stated under Act 70 of 1993 that recognizes the black communities’ right to collective ownership of land that they have historically occupying and that has been passed down through traditional practices, and sets forth that the collective entitlement of lands held by each community shall constitute a communal council. The General Assembly is the highest level of the communal councils, which is composed of delegates who represent all local communal councils (two delegates per community are elected in communal assemblies and five per zone are elected in zonal meetings). These communities have ethno-development plans that are used as management and planning instruments and that serve to express their perspectives, interests, and needs for their vision for development that considers environmental conservation and validation of traditional production practices, eradication of poverty, and respect and recognition of their social and cultural values.

Political and legal framework

The Colombian political and legal framework comprises several standards and plans related to biodiversity conservation and SLM. The following are highlighted as relevant to this project.

The National Development Plan 2014-2018: “Everyone for a new country,” has as its foundation peace, equality, and education with a cross-cutting strategy of “green” growth. This strategy envisions using sustainable development to ensure long-term socioeconomic well-being and for resources to provide the environmental goods and services that the country needs. The objectives of this plan are as follows: (i) progress towards sustainable and low-carbon growth; (ii) protect and ensure the sustainable use of the country’s natural capital and improve environmental quality and governance; and (iii) achieve resilient growth and reduce vulnerability against disasters and climate change risks.

The National Planning Department (DNP, acronym in Spanish]), aware of the need to prioritized “green” growth for the country’s development, created the Green Growth Mission, which defines public policy inputs and guidelines to guide the country’s economic development towards green growth in 2030. The objectives of this mission are as follows: (i) promote the country’s economic competitiveness; (ii) protect and ensure the sustainability of the country’s natural capital and ecosystem services; (iii) promote resilient economic growth in the face of natural disasters and climate change; and (iv) ensure social inclusion and well-being. The mission highlights the following sectors that would comprise Colombia’s bio-economy: processed food and beverages, cosmetics and toiletry, and agriculture and cattle-ranching sectors.

The objective of the National Policy for Biodiversity and Ecosystem Services Management in Colombia (PNGIBSE, according to its Spanish acronym; MADS, 2012), is to improve the resilience of the social and ecological systems at the national, regional, local, and cross-border scales, considering scenarios of change and through joint, coordinated, and focused action by the government, the productive sector, and civil society. Within the policy framework the importance of ecosystem services is recognized for their role in ensuring the well-being of the population  through the supply of services, such as food and natural ingredients, medicinal plants, cosmetic products,  water regulation, and cultural support and services (e.g., recreation and tourism).

The three lines of action of the PNGIBSE address biodiversity, economic development and competitiveness, and quality of life, with the objective of mainstreaming biodiversity and ecosystem services into sectoral planning and decision making that will enable the sustainability of production, extraction of natural resources, human settlement and consumption, and improved quality of life at the national, regional, and local levels.

SLM Policy. This policy seeks to promote SLM in Colombia so that the conservation of biodiversity, water, and air are incorporated into land use planning and risk management and contribute towards sustainable development and the well-being of the country’s population. The policy’s action plan highlights the following strategic lines: i) institutional strengthening and harmonization of standards and policies; ii) education, training, and awareness; iii) strengthening of environmental and sectoral planning tools; iv) soil quality monitoring and follow-up; and v) soil conservation, restoration, and sustainable use.

The “Forests, Territories of Life” strategy. The Integrated Strategy for Control of Deforestation and Forest Management is a cross-sectoral policy instrument that highlights the shared responsibility of the different government stakeholders in halting deforestation and land degradation by addressing their root causes and recognizing the strategic importance of these ecosystems within the country’s sociocultural, economic, and environmental contexts; their potential as a development option in the framework for building peace; and their contribution to climate change mitigation and adaptation.

This strategy has five strategic lines of action that encompass integral forest governance and bank on long-term progress towards rural sustainable development that relies upon natural forests, contributes to improved quality of life for rural communities, ensures multiple benefits from standing forests, and contributes towards GHG emissions reduction. The lines of actions are the following: i) sociocultural forest management and public awareness; ii) development of a forest economy and halting the expansion of agriculture; iii) cross-sectoral management of territorial planning and environmental determinants; iv) permanent monitoring and control; and v) creation and strengthening of legal, institutional, and financial capacities.

The National Policy for Sustainable Production and Consumption (2010) seeks to change non-sustainable production and consumption patterns of the different national civil stakeholders, thereby contributing to reducing pollution, conserving resources, favoring the environmental integrity of goods and services, and promoting the sustainable use of biodiversity, as sources of economic competitiveness and quality of life. The four elements governing this policy are as follows: i) environmental sustainability of the country’s natural heritage; ii) business competitiveness; iii) employment generation; and iv) contribution towards creating the institutional and cultural capacities for sustainability by the different stakeholders. The implementation of the policy guidelines identifies production sectors that are recognized as green businesses, such as tourism, ecological food sectors, and products and services from biodiversity, and seeks to generate green business initiatives and strengthen existing ones.

The key actions guiding the development of this strategy are as follows: i) expansion of capacities of networks and incubation and acceleration programs for green business initiatives; ii) strengthening of fairs, expos, and spaces for green business exchanges; iii) creation and articulation of seed capital investment funds for businesses with the potential for success; iv) development of a public information platform for sustainable initiatives (i.e., criteria, programs, portfolios, investments, and sales); and v) articulation of bids for business plans focused on green business initiatives.

The National Competitiveness and Productivity Policy (CONPES 3527, June 2008) has as one of its lines of action environmental sustainability as a factor for competitiveness, and recognizes bio-businesses as an element of competitiveness.

CONPES Document 3680 of 2010, in its Guidelines for Consolidating the National Protected Areas System, states that within the PA system, “the protected areas cannot be considered as isolated units but they shall constitute systems understood as a set of protected areas, social and institutional actors and management strategies and instruments that articulate them, to contribute as a whole to comply with the country’s conservation objectives; policy that at the country’s sphere along with SINAP action plan and SIRAP planning instruments complies with the commitments assumed in the APs work program approved by the Convention on Biological Diversity and in whose framework the APs systems shall have essential attributes as be complete, well connected, ecologically representatives and effectively managed.”

The Policy for the Commercial Development of Biotechnology Based on Sustainable Use of Biodiversity (CONPES 3697, June 2011) seeks to create the economic, technical, institutional, and legal conditions that attract public and private resources for the development of companies and commercial products based on the sustainable use of biodiversity, specifically biological and genetic resources and their derivations. These resources will serve as the basis for new products in several industries such as cosmetics, pharmaceuticals, agri-food, and natural ingredients industries, etc.

The National Green Business Plan (PNNV, 2014) defines the guidelines and tools for planning and decision making to develop and promote the supply and demand for green and sustainable businesses through the implementation of the appropriate tools, incentives, coordination mechanisms, and institutional articulation platform, which will lead to economic growth, employment generation, and natural capital conservation in Colombia. Within the PNNV the following series of tools is recognized for promoting green businesses: economic incentives, tax incentives, promotional expos, eco-design, environmental certification, and green business nodes/windows.

Green businesses are economic initiatives that offer goods and services that generate positive environmental impacts and incorporate best environmental, social, and economic practices that contribute to environmental conservation as natural capital to support territorial development. According to the PNNV classification, there are three green business categories: i) sustainable goods and services derived from biodiversity; ii) industrial eco-products; and iii) carbon markets. The proposed project will be focused on category i), covering three sectors: a) sustainable agro-ecosystems; b) bio-business; and c) environmental restoration.

On July 30, 2014, the national government declared the Pacific region a priority in terms of equity that was manifested through Act 1753 of 2015 (by which the National Development Plan 2014-2018 “Everyone for a new country” was issued). Through Article 185, the fund for developing the “We are all PAZcific” Plan (Plan Todos Somos PAZcífico) was created, administered by the Ministry of Finance and Public Credit and/or the entity or entities defined by it. The objective of this fund is the financing and/or investment in the most urgent needs to promote the integral development of the Pacific region. On November 3, 2015, through CONPES 3847, the council provided a favorable opinion to the government to authorize the “Fund for the Development of the Plan Todos somos PAZcífico,” to seek external public credit operations for up to USD $400 million. The objective of the plan is to close the existing socioeconomic gaps in the Pacific region, based on equal socioeconomic development, the integration of the region with the rest of the country, and environmental sustainability. This will be achieved through the development of five strategic lines of action: i) utilities and urban development; ii) integration and competitiveness; iii) environment, culture, and sustainable production; iv) education, employability, and social mobility; and v) institutional capacity, transparency, and accountability.

The final agreement to end the conflict and build stable and long-lasting peace. “Towards a new Colombian country: Integral Rural Reform.” The Integral Rural Reform (RRI, according to its Spanish acronym) will be the transformative beginning of a rural and agrarian structure in Colombia characterized by equity and democracy, thereby contributing to the end of conflict and the construction of a stable and long-lasting peace. The RRI is focused on improving the quality of life of the rural population, which includes indigenous and black communities, as well as people who live in inter-ethnic and intercultural spaces. The RRI seeks to achieve regional integration, eradication of poverty, promotion of equality, closing of gaps between rural and urban areas, protection of citizens’ rights, and to reenergize the rural areas, specifically the rural-, family-, and community-based economies.

1.1.2 Areas of Intervention

The project will intervene in five Biodiversity Use and Conservation Mosaics (MUCBs, according to its Spanish acronym) in the Colombian Pacific region that were prioritized using a multicriteria analysis approach (Appendix 11). A conservation mosaic is a network of protected areas and complementary landscapes including combinations of national parks, marine and land production areas, landscapes and territories of collective ethnic property. This mosaic approach will allow integrated landscape management through implementation of the four project components in three mosaics (Katíos – Caoba, Farallones – Calima, and Cabo Manglares – Gran Familia Awá) and partial intervention in two mosaics (Serranía de Paraguas – Tatamá and Muchique – Rio Saija). Appendix 8 includes maps of the MUCBs.

The surface cover of the five priority MUCBs represents 19% (2,040,072 ha) of the SIRAP Pacific management area (Figure 2 and Table 1).

- Figure 2. Prioritized MUCBs

- Table 1. MUCBs prioritized by the project

| MUCB Name | Katíos – Caoba | Farallones – Calima | Cabo Manglares – Awa | Serranía Paraguas – Tatamá | Munchique – Río Saija |
| --- | --- | --- | --- | --- | --- |
| Surface Area | 895,994 ha | 572,453 ha | 638,650 ha | 436,388 ha | 250,058 ha |
| Departments | Chocó | Chocó Valle del Cauca | Nariño | Chocó Risaralda Valle del Cauca | Cauca |
| Municipalities | Unguía Acandí Riosucio Carmen del Darién Juradó | San Juan Restrepo Coastal Area Dagua Yocoto La Cumbre Cálima Vijes Buenaventura | Cumbal Ricaurte Mallama Tumaco Barbacoas | El Dovio El Cairo San José del Palmar Tadó Pueblo Rico Mistrató | El Tambo Timbiquí López |
| PA | 13 | 27 | 5 | 34 | 3 |
| Complementary conservation strategies - (CCS) | 31 | 16 | 34 | 12 | 13 |
| Communal Councils | 17 | 28 | 11 | 6 | 7 |
| Indigenous Reserves | 19 | 7 | 24 | 6 | 5 |

Source: SIRAP Pacífico, Dialogos locales. 2018

Katíos – Caoba MUCB.

The Katíos-Caoba MUCB is within the department of Chocó and includes the following five municipalities: Acandí, Unguía, Riosucio, Carmén del Darién, and Juradó. There are 17 indigenous reserves among the Emberá-Katío, Wounana, and Cuna or Tulé ethnic groups, representing 20% of the MUCB area; there are 19 communal councils representing approximately 56% of the MUCB.

The forest cover represents 64% of the MUCB. There are 11 PAs that are part of the SINAP within the MUCB (Table 2).

- Table 2. Protected areas in Katíos – Caoba MUCB

| MUCB | PA category | Name |
| --- | --- | --- |
| Katíos-Caoba | National Natural Park (NNP) | Los Katíos |
|  | Wildlife Sanctuary (WS) | Acandí Playón and Playona |
|  | Regional Natural Park (RNP) | Wetlands of the León and Suriqui Rivers |
|  | National Forestry Protective Reserve – (NFPR) | Darién |
|  |  | León River |
|  | Integrated Management Regional District (IMRD) | La Playona and Loma de la Caleta |
|  |  | Lago Azul –Los Manatíes |
|  | Civil Society Natural Reserve (CSNR) | Aguapanela |
|  |  | Tacarcuna |
|  |  | Amigos del Bosque |
|  |  | Montes de la Esperanza |

Sources: RUNAP, 2017; SIRAP, 2017

This MUCB’s strategic ecosystems include hydrophytic ecosystems, lowland forests, and coastal-marine ecosystems. In addition, there are important plant associations such as arracacha plants, panga trees, mangroves, and cativa trees. As hydrophytic ecosystems the swampy complexes stand out in the municipalities of Riosucio, Unguía, and Carmen del Darién, and in the lower zones at the banks of the Río Atrato. To the west, 27% of the total mangroves in the department of Chocó are found in the municipality of Juradó .

This MUCB presents homogeneous forests with timber-yielding species of high economic value. Additionally, it includes coastal and oceanic landscapes, which provide the means for oceanic transportation. The area is recognized for its potential for interoceanic communication, and there are mega projects proposed for an interoceanic channel and Pan-American Road. It should be noted that there are currently three port areas under construction in the MUCB’s area of influence in the municipalities of Turbo and Necoclí (Antioquia).

The ecological functions of these coastal ecosystems, which include mangroves and swamps, are key to the protection of coastal dynamics as they act as natural filters for land-based runoff, serve as habitat for numerous species, and are critical feeding areas and key areas for fisheries that serve as breeding areas for different species. In addition, they act as carbon sinks, are sources of energy, offer tourism attractions, and contribute to the region’s economic development.

The total population of this area is 62,345, 4,272 of who are from indigenous ethnic groups, and 27,119 of whom correspond to black communities. In terms of the area’s production systems, the main economic activities in Unguía are cattle ranching and agriculture (rice, corn, manioc, yam, and plantain crops). There are also fruit plantations as lemon, papaya, and borojó. In the municipality of Riosucio plantain cultivation is the main agricultural activity and this municipality is the highest producer of plantains in the department of Chocó, above the principal producers in Alto and Medio Baudó, Bojayá, Carmen del Darién, and Quibdó.

In the municipality of Juradó the main economic activity is timber logging that has been developed through unsuitable and inappropriate means. The species that are the most illegally extracted are abarco, cedar, oak, carobro, algarrobo, choibá, bonga, sangregallina, caracolí, and mahogany. Most agricultural activities are for subsistence, and the most prevalent crops are rice, plantain, corn, coconut, and manioc, and fruit crops such as borojó, guava, avocado, chontaduro, and lemon. Traditional fishing is an important economic activity because of the abundance of resources, access, and diversity of species that supplies local markets. A small part of the traditional fishing is commercialized in the interior of the country (Medellín) and in coastal towns such as Bahía Solano and Buenaventura.

The Living Conditions Index (LCI), is generally low for the department of the Chocó (60-70). At the municipal level, Riosucio and Carmen del Darién have the lowest LCI, within a range of <=50. The NBI calculation is within a range of >80 for the municipalities of Carmen del Darién, Juradó, and Riosucio; the range for Acandí is 30.01-50 and 50.01-70 for Unguía:. In the Chocó, the range of health coverage deficiency is between 30-40%.

This region has also experienced armed conflict for more than 20 years. The area has served as a route for arms trafficking because of its proximity to the Panama Canal, and was the rearguard area for insurgent groups attacking in Urabá, Córdoba, and sectors of Antioquia. During many years, navigation along the Río Atrato was interrupted because of the presence of armed groups. Social, political, economic, and cultural unrest derived from the armed conflict has manifested in the displacement of rural peoples, Black, and indigenous populations; marginalization; and, in some cases, environmental damage. According to the report Peace Building Overview (PBO) developed by the Colombian Unit of Information Management and Analysis (UMAIC, according to its Spanish acronym) four municipalities in this MUCB rated high in percentage of exiled or displaced persons in 2016; only Acandí was classified within the medium range.

Farallones – Calima MUCB

The Farallones – Calima MUCB is located in the departments of Valle del Cauca and Chocó and comprises eight municipalities: Yotoco, Vijes, Calima, Restrepo, La Cumbre, Dagua, and Buenaventura in Valle del Cauca, and the municipality of Litoral de San Juan in Chocó. This MUCB includes seven indigenous resguardos and 28 communal councils representing 1% and 35% of the MUCB area, respectively.

The forest-associated land cover represents 76% of the MUCB area. There are 27 PAs that are part of the SINAP in this MUCB, and are listed in Table 3.

- Table 3. Protected areas in the Farallones – Calima MUCB

| MUCB | PA category | Name |
| --- | --- | --- |
| Farallones – Calima | NNP | Farallones de Cali |
|  | NFPR | Río Anchicayá |
|  |  | Río Dagua |
|  | Regional Forestry Production Reserve (RFPR) | Bitaco |
|  | RNP | Páramo El Duende |
|  | IMRD | Subxerophytic Enclave of Atuncela |
|  |  | El Chicál |
|  | Soil Conservation District (SCD) | Cañón de Río Grande |
|  | CSNR | Dinaboy |
|  |  | El Carare II |
|  |  | El Carare |
|  |  | El Progreso |
|  |  | El Tesoro |
|  |  | Esparta |
|  |  | Himalaya |
|  |  | Jurásico |
|  |  | La Esperanza |
|  |  | La Magdalena |
|  |  | La Vega |
|  |  | Masada |
|  |  | Moralba |
|  |  | Los Volcanes |
|  |  | Rondalla |
|  |  | San Antonio |
|  |  | San Rafael |
|  |  | Tierra Blanca 2 |
|  |  | Tierrablanca number 4 |

Source: RUNAP, 2017

This MUCB encompasses strategic ecosystems such as mangroves, rainforest, wetlands, and dry forest. These ecosystems are important for water provision, and the MUCB includes hydrographic subzones with higher water demand in the Pacific region. Other services provided by these ecosystems are timber production, refuge for wildlife species, and tourism.

The population of the eight municipalities conforming the MUCB totals 523,332 persons. 7,816 belong to indigenous ethnic groups and 290,538 are members of black communities. Commerce is the main economic activity in the municipality of Buenaventura and is a key point of distribution of food and supplies in the Colombian Pacific region to municipalities that do not have land transportation systems and whose air transportation system is expensive and intermittent. The tourism sector MUCB has significant economic importance, mainly in the municipality of Calima Darién. Agricultural production consists of coffee, corn, beans, manioc, pineapple, panela cane sugar, chontaduro, borojó, small banana, coconut, and papachina crops. Economic activities also include cattle ranching, timber production, aviculture, and dairy production.

The LCI for the Valle del Cauca municipalities is within the highest range (70.01-80) and for the municipality in Chocó it is in the range of <=50 (DNP, 2005). The NBI is in a range of <=30 for six of the eight MUCB municipalities. The range for Buenaventura is 30.01-50 and 70.01-80 for Litoral de San Juan (DANE, 2010). The percentage of health coverage deficit for both departments is between 30-40%.

The various forms of land occupation by different inhabitants (e.g., community, private business, government, armed groups) have connected immigration and emigration processes with new colonization processes and the armed conflict. With regard to forced displacement, 1,009 persons were reported as having been forcibly displaced from the municipality of Buenaventura in 2011. According to the PBO report developed by UMAIC regarding the range of displaced persons in 2016, only Buenaventura shows a high range, while the other municipalities have a low range.

Cabo Manglares – Awá MUCB

The Cabo Manglares – Gran Familia Awá MUCB is located in the department of Nariño and comprises five municipalities: Mallama, Tumaco, Ricaurte, Barbacoas, and Cumbal. There are 24 indigenous reserves of Awá ethnic groups and 15 communal councils representing 25% and 16% of MUCB area, respectively.

The forest-associated land cover represents 36% of the MUCB area. There are six PAs that are part of the SINAP in this MUCB and are listed in Table 4.

- Table 4. Protected areas in the Cabo Manglares – Gran Familia Awá MUCB

| MUCB | PA category | Name |
| --- | --- | --- |
| Cabo Manglares – Gran Familia Awá | NFPR | La Planada |
|  |  | Río Nembí |
|  | National Integrated Management District (NIMD) | Cabo Manglares – Bajo Mira y Frontera |
|  | CSNR | Biotopo Selva Húmeda |
|  |  | Pueblo Viejo |
|  |  | Tierrablanca número 4 |

Source: RUNAP, 2017

Strategic ecosystems of wetlands (lacustrine and marsh) and mangroves are highlighted within this MUCB. Mangroves provide services for the well-being of humans such as timber for constructing dwellings and bridges and for coal and firewood. These wetlands and mangroves are key sites that provide refuge, habitat, and breeding spaces for hydrobiological species such as shrimps, fish, piangua clam, and others. They serve to regulate the risk of coastal erosion and other natural phenomena; in addition, they contribute to the entire region’s climate regulation services. As regards cultural services, they are sources for ecotourism development.

Ecosystems present in the coastal foothills are mainly located in the municipalities of Ricaurte and Mallama and are associated with rainforest ecosystems. These ecosystems, in combination with other geographic conditions, have fostered the provision of services such as food supply through agriculture, the provision of water, and currently the potential for tourism development with an emphasis on ecotourism and bird-watching; the latter associated with existing local and communal conservation processes.

The population of this MUCB, comprising five municipalities, has a population of 313,914, 49,244 of whom pertain to indigenous ethnic groups and 152,727 of whom are members of black communities. Crops such as palm, cocoa, coconut, naidi, vanilla, borojó, small banana, and panela cane sugar predominate in this MUCB. The MUCB contains production systems with agro-forestry arrangements, such as cocoa with cedar and tangare; other economic activities include tourism (bird-watching), timber extraction (mainly cedar, laurel, guadua, and tangare–copaiba) and mining, with the Barbacoas municipality as the main site for gold extraction in the department of Nariño.

As recorded in 1999, coca crops have encompassed 3,959.32 ha, which corresponds to 1% of the MUCB’s area. In 2016, coca crops covered a record 42,627.38 ha, which is approximately 6% of the MUCB’s area. This illegal activity has restricted the normal development of economic activities in this MUCB; however, because of the implementation of the peace agreements, investments have been reactivated mainly in the town of Tumaco.

The LCI for the municipality of Nariño is in the low range of 60-70; at the municipality level, Ricaurte is highlighted with an index lower than 50. The NBI is generally low for all the MUCB’s municipalities; Cumbal, Mallama, and Tumaco fall within a range of 30-50 and Ricaurte 50-70. With regard to the percentage of health coverage deficit, the department of Nariño scores the lowest, between 20-30%.

This MUCB is one of the areas most affected by the armed conflict, illicit crops, forced displacement, and human settlement in areas that are highly vulnerable environmentally, as well as illegal mineral extraction, illegal timber extraction, and deliberate hydrocarbon spills. These conditions lead to a limited government presence in the MUCB, likely associated with limited physical access to most of the municipalities of Nariño along the Pacific coast, and their geographic, socioeconomic, political, and cultural conditions. According to the PBO report developed by the UMAIC in relation to the range of exiled displaced persons in 2016, the following four MUCB municipalities scored high: Barbacoas, Mallama, Ricaurte, and Tumaco; only Cumbal reported a low range.

Serranía de Paraguas – Tatamá MUCB

The Serranía de Paraguas – Tatamá MUCB is located within the departments of Chocó, Risaralda, and Valle del Cauca. This MUCB includes the following nine municipalities: Tadó, Novita, Sipí, and San José del Palmar in Chocó; Pueblo Rico and Mistrató in Risaralda; and El Cairo, Versalles, and El Dovio in Valle del Cauca. There are two indigenous resguardos of Emberá-Katío and Emberá-Chamí ethnic groups, and six communal councils representing 12% and 18% of the MUCB area, respectively.

The forest cover represents 67% of the MUCB. There are 30 PAs r that are part of the SINAP in this MUCB and are listed in Table 5.

- Table 5. Protected areas in the Serranía de Paraguas – Tatamá MUCB.

| MUCB | PA category | Name |
| --- | --- | --- |
| Tatamá-Serranía de Paraguas | NNP | Tatamá |
|  | PNP | Río Negro |
|  | IMRD | Chuchilla del San Juan |
|  | CSNR | El Recreo |
|  |  | El Retiro |
|  |  | El Provenir |
|  |  | El Laguito |
|  |  | El Cedral |
|  |  | El Arrayan |
|  |  | Dos Quebradas |
|  |  | Bellavista |
|  |  | Altomira |
|  |  | La Esperanza |
|  |  | Peñas Blancas |
|  |  | Patio Bonito |
|  |  | Montevideo |
|  |  | Manga bonita |
|  |  | Manantial |
|  |  | Las Golondrinas |
|  |  | La Vuelta |
|  |  | La Ventura |
|  |  | La Parcela 9 |
|  |  | La Parcela 2 |
|  |  | El Silencio |
|  |  | La Divisa de Guillermo |
|  |  | El Vergel |
|  |  | El Tesoro |
|  |  | La Bretaña |
|  |  | La Paila |
|  |  | La India |
|  |  | La Ilusión |

Sources: RUNAP, 2017; Pacific SIRAP, 2017.

The Serranía de los Paraguas is a mountain complex associated with important ecosystem services for the area; CODECHOCO and CVC share jurisdictions in San José del Palmar in the Chocó and El Cairo in Valle del Cauca. The mountain complex is not associated with any PA, but is part of a process prioritized by the Departmental System of Protected Areas (SIDAP, according to its Spanish acronym) in Valle del Cauca. Currently the Serranía de los Paraguas is prioritized as a conservation area for natural resources that is free from mining and is in undergoing the process of being declared as a PA.

This MUCB comprises nine municipalities and has a total population of 91,462. Of this, 9,637 pertain to indigenous ethnic groups and 22,610 to black communities, representing 12% and 21% of the total population, respectively. At the municipality level, the LCI is within the 50-70 range for all the MUCB municipalities, except for El Dovio, which has a range of 70-80. The NBI is in the range of >80 for Tadó, 50-70 Pueblo Rico and Novita, 30-50 in Mistrató, San José del Palmar and Sipi; and <=30 for the municipalities of El Dovio, El Cairo, and Versalles in Valle del Cauca. Regarding the health coverage deficit, the three departments are in the range of 30-40%.

This MUCB is one of the areas most affected by the armed conflict, has the presence of illicit crops, forced displacement and occupation of areas that are environmentally vulnerable, illicit extraction of minerals, illegal timber extraction, and the intentional dumping of hydrocarbons. These conditions create a situation of low governability, likely associated with the difficultly in accessing the majority of the municipalities on the Pacific coast of Nariño, as well as its geographic, socioeconomic, political, and cultural conditions. Per the PBO report, the municipalities of Tadó, San José del Palmar, and Pueblo Rico were qualified as high in terms of displaced persons in 2016, López and Timbiquí were qualified in the medium-high range, El Dovio and Mistrató in the medium range, and Versalles was qualified in the low range.

Munchique – Río Saija MUCB

The Munchique – Río Saija MUCB is located in the department of Cauca. This MUCB comprises the following three municipalities: Timbiquí, López de Micay, and El Tambo. There are rive indigenous reserves of Emberá Eperara-Sapidará and Emberá-Katío ethnic groups, and seven communal councils representing 22% and 33% of the MUCB’s area, respectively.

The forest cover represents 77% of the MUCB. There are three PAs that are part of the SINAP in this MUCB and are listed in Table 6.

- Table 6. Protected areas in the Munchique- Río Saija MUCB.

| MUCB | PA category | Name |
| --- | --- | --- |
| Munchique – Saija | NNP | Munchique |
|  | CSNR | Valparaíso |
|  |  | De las Aves Mirabilis Swarovsky |

Source: RUNAP, 2017

Per DANE projections for 2017, the total population of the three MUCB municipalities (El Tambo, Timbiquím and López) was 90,261. Of this total, 4,524 pertain to indigenous ethnic groups and 25,104 pertain to black communities, representing 5% and 28% of the MUCB’s population, respectively.

With regard to LCI, at the municipal level Timbiquí is placed the lowest range (<=50), El Tambo and López are in the next highest range of 50-70. The NBI is in the range of 30-50 for López, 50-70 for El Tambo, and 70-80 for Timbiquí. The percentage of health coverage deficit for the department is between 40-50%. According to the PBO report developed by the UMAIC, all the MUCB municipalities rated in the high range for displaced persons in 2016.

## 1.2 THE CURRENT SITUATION

1.2.1 Threats to global environmental benefits

At the regional scale

The PNGIBSE analyzes the direct and indirect drivers of transformation and loss of biodiversity and its ecosystem services in Colombia and the impacts at the national level. The direct drivers of change are identified as: i) changes in land use (terrestrial or aquatic) and ecosystem fragmentation; ii) reduction, loss, or degradation of elements in native ecosystems and agro-ecosystems; iii) invasive species; iv) pollution and contamination; and v) climate change.

Indirect drivers include: i) demographics factors; ii) economic factors (e.g., globalization, trade, markets, and economic policies); iii) sociopolitical factors: (e.g., governance, institutions, and legal framework); iv) science and technology; and v) culture and religion (e.g., beliefs and consumer choices).

Direct drivers

Changes in land use: Deforestation and land degradation are the main processes determining biodiversity loss and ecosystem fragmentation in the Colombian Pacific region. Other impacts relate to the loss of associated ecosystem services, including carbon storage and water supply. Among the causes related to deforestation, the most important refers to changes determined by forest resources exploitation that is illegally and unsustainably carried out in some sectors, the presence of illicit crop cultivation, illegal mineral extraction, and the expansion of agriculture and cattle-ranching. In the region, a total of 383,517 ha wee deforested during 1990-2013, which generated 7,453,574 million tons of CO2eq emissions. According to the trend analysis and the deforestation patterns in Colombia, the average deforestation rate for the Colombian Pacific region is 14,403 ha/year; in 2014 a total of 13,855 ha of forest were lost.

- Forest resources exploitation. Change in the cover of Andean and High-Andean forests and mangroves due to the exploitation of forest resources is considered a deforestation driver, as there are places where it is done in an illegal and unsustainable manner. Forest resources exploitation in the Chocó is concentrated in the municipalities of Medio Baudó, Quibdó, Medio Atrato, Río Iró, Río Quito and Bojayá, Tadó, Carmen del Darién, Riosucio, and Unguía. In Valle del Cauca, although there is still a representative forest cover, overexploitation of forest resources occurs principally in areas close to rivers and estuaries.

The forestry sector is still informal; there is limited use of SFM tools and lack of control of illegal and unsustainable logging to supply. During the period of 2008-2012, the national police seized 1,815,322 cubic meters (m3) of illegally extracted timber, which is equivalent to 14,523 trucks with a carrying capacity of 25-m3 per year. The logging activities are carried out by local communities; particularly by youth and young adults who sell wood at a very low price to intermediaries that supply timber companies and external parties.

- Illicit crop cultivation. Although at the national level there has been a decrease in illicit crops, in recent years, Chocó, Nariño, Valle del Cauca, and Cauca have reported high levels of coca production and land transformation, with Tumaco (Nariño) and El Tambo (Cauca) as the municipalities with the largest coverage of illicit crop cultivation in 2014. As a result, there is greater incidence of chemical runoff into the water sources in these areas. The department of Nariño has the largest area under cultivation in the country (13,177 ha). According to the MADS and the United Nations in Colombia, two types of processes are noted in areas that have been able to reduce the cultivation of illicit crops: i) activities that generate sustainable income, such as cocoa, rubber, and honey production and ecotourism; ii) non-sustainable activities such as logging (deforestation) and/or precious metals extraction, which tend to involve vulnerable populations in areas with weak institutions. Finding alternatives to illicit crops that are profitable enough but that are also sustainable is critical for building peace in the Pacific region.

- Mining. Emissions and dumping related to this activity, in addition to soil degradation and the use of chemicals such as mercury and cyanide, impact ecosystems and their provision of services that is made evident in the alteration of habitat and contamination of water sources. The Chocó is among the departments with the highest level of gold and silver production in the country, at 37% and 24%, respectively; in addition, in the Chocó 195 tons of mercury are used per year in the gold and silver production processes. The freshwater systems that are most affected by mercury runoff include the Quito River and other rivers that lead directly to the San Juan River. A study performed within the framework of GEF project Conservation of Biodiversity in Landscapes Impacted by Mining in the Chocó Biogeographic Region (GEF ID 4916), which was led by WWF and executed jointly with the Universidad de Cartagena and IIAP, showed that the highest concentrations of contaminated sediments were found in the mouth of the Quito River, in the Puné River, and the Atrato River at the town of Buchadó and before the town of San José. The study also demonstrated that concentrations of mercury found in fish exceeded the limit recommended by the World Health Organization of 0.5 parts per million (ppm) in muscle tissue, for the toad catfish (Pseudopimelodus schulzi), driftwood catfish (Ageneiosus pardalis), blue-green knifefish (Sternopygus aequilabiatus), South American catfish (Rhamdia quelen), and wolf fish (Hoplias malabaricus).

- Expansion of agriculture and cattle ranching. Forest clearance happens to make room for crops for food production and pastures for cattle grazing. These land uses are incompatible with the soil carrying capacity, and is worsened by the adoption of inappropriate technologies and unsustainable natural resources practices.

Species loss. The elimination of species occurs due to illegal trafficking of native species associated with the exploitation of forest resources, illegal hunting, and overexploitation of hydrobiological resources. CODECHOCÓ and CORPONARIÑO have highlighted the difficulty they face as environmental authorities in obtaining approval for, execution of, and monitoring the Forest Management Plans. The species of trees that are under the most pressure in the Pacific region are: Sande (Brosimun utile), Sajo (Camnosperma panamensis), Tangare (Carapa guianensis), Sebo (Virola reedii), Peine mono (Apeiba aspera), Machare (Symphonia globulifera), Popa (Couma macrocarpa), Cuángare (Dialyanthera garcilipes), Chaquiro (Goupia glabra), Chanul (Humiriastrum procera), Chachajo (Aniba perutilis), Caimito (Pouteria caimito), Anime (Protium nervosum), Carrá (Huberodendron patinoi), and Cedar (Cedrela odorata). In addition, the red mangrove (Rhizophora mangle) is intensively exploited for the extraction of tannin and currently as square wood. In response to this, the CVC has banned the use of this wood.

Regarding freshwater ecosystems, a study conducted by Universidad Javeriana, IAvH, and WWF (2014), indicated that of the 186 species of freshwater fish inhabiting the Chocó Biogeographic region, 50% are endemic species and 30 species have high commercial value and are highly endangered. These include: bocachico (Prochilodus magdalenae), driftwood catfish (Ageneiosus pardalis), guacucos (Hypostomus hondae), sábalo (Brycon medemi), dentón (Leporinus muyscorum), and catfish (Pseudopimelodus sp.). This threat is mainly associated with overexploitation of hydrobiological resources; illegal trafficking of species; transformation of ecosystems, including alteration of water flows caused by the presence of hydroelectric plants; mining; and deforestation.

According to the Red Books of Threatened Species for Colombia, 157 plant species are threaten (21 are in critical danger, 55 are endangered, and 81 are vulnerable), including plant species such as mahogany (Swietenia macrophylla; globally vulnerable), whose wild population has been subjected to indiscriminate logging as it is considered as one of the best woods in the market; and Choiba (Dipteryx oleifera), of which the whole plant is used from the stalk to the leaves and fruit. This region serves as habitat for animal endemic species that are also globally endangered, such as the black-headed spider monkey (Ateles fusciceps), the Baudó guan (Penelope ortoni) (endangered), the long-wattled umbrella bird (Cephalopterus penduliger) (vulnerable), the colorful puffleg (Eriocnemis mirabilis) (critically endangered), and the Baudó oropendola (Psarocolius cassini) (endangered). There are other species under threat categories including the spectacled bear (Tremarctos ornatus) and the jaguar (Panthera onca). The threats affecting these species include deforestation, habitat fragmentation and transformation, hunting, illegal trade, extraction of timber species, expansion of agriculture and cattle-ranching, and temperature change due to plant cover loss.

Hydrobiological resources such as freshwater fish are overexploited for self-consumption and sale; this phenomenon is most critical in areas affected by the armed conflict where that has been a high demand for these resources. Additionally, overfishing and threats to marine wildlife is common the coastal areas of Acandí and Unguía; these activities are carried out by national and international fishing vessels in restricted areas.

Climate change. Several aspects, including the El Niño Southern Oscillation, determine climate change in the Colombian Pacific region. The effect of this phenomenon is sea level rise in the range of 20, 30 and 40 cm on the coasts of Tumaco and up to 60 cm in Valle del Cauca. In addition, sea temperatures are also rising, reaching 2°C and 3°C above normal in different areas. During the El Niño phenomenon, temperature can increase 2°C or more above normal, while during La Niña phenomenon there is a reduction in water temperatures.

The climate change scenarios for 2040 indicate that main areas in the country experiencing a rise in temperature correspond to the Pacific and Caribbean regions. According to the Third National Communication on Climate Change to the United Nations Framework Convention on Climate Change (UNFCCC), climate change analyzed for each department showed risks related to food security, hydrological resources, and biodiversity (Table 7).

- Table 7. Climate Change Risk by Department.

| Department | Food security risk |  | Hydrological resource risk |  | Biodiversity risk |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | Value | Indicator | Value | Indicator | Value | Indicator |
| Chocó | 34.7% | High | 4.2% | Very High | 10% | High |
| Risaralda | 35.4% | High | 4.4% | Very High | 11% | High and Medium |
| Valle del Cauca | 35.1 | Low and Medium | 4.1% | High | 9.5% | High |
| Cauca | 36.5% | High | 4.3% | Medium and High | 10.9% | High |
| Nariño | 34.8% | Very low | 4.1% | High | 11.6% | High |

Sources: IDEAM, PNUD, MADS; DNP, CANCILLERÍA. 2017.

Indirect drivers

Public policies. The legal economies based on extraction activities influences the change in traditional production systems and constitute a threat to natural communal heritage and biodiversity. This is attributed, among other factors, to public policies that promote extraction economies and rural technification, including mining and agro-industrial monoculture (e.g., oil palm and bananas). The high demand for natural resources alters the cultural and environmental characteristics of natural areas, such as in case of the demand by the construction industry for forest resources in the Chocó,.

Additionally, the population of the Colombian Pacific region lives in impoverished conditions, which is mostly due to ineffective and poor public policies at the local level. This problem is associated, among other factors, with clientelism and the population’s distrust of the political process. In other cases, the conditions of poverty are related to the unsustainable demand for natural resources.

Territorial governance. The different forms of land use and lifestyles in the Colombian Pacific region, obey to the different interests that are prevalent in the area. For example, one of the key characteristics that differentiate the Pacific region from other Colombian regions is the role of black and indigenous populations in land use planning; the Pacific region still depends on traditional methods of property ownership (i.e., ancestral territories) and territorial organization. Generally, black, indigenous, and rural communities have shaped agricultural systems to their mode of subsistence, with the improvement and adaptation of plant and animal species. In contrast, other land uses, are influenced by forms of production and interest that compared with the traditional production systems of the rural groups, represent increased pressure on ecosystems and natural resources. These are market-oriented production systems that include large-scale forest and fish concessions, mining businesses, agroindustrial monocultures, shrimp farms and heart of palm cultivation, hydrocarbon exploitation, and hydroelectric power production. This contrasting scenario does not necessarily results in the equal distribution of the benefits of production among the various stakeholders involved. The least favored populations are those with unsatisfied basic needs who have been immersed for years in an armed conflict and have undergone forced displacement.

Despite the fact that the Colombian Pacific region has significant inequality and high poverty and unemployment levels in comparison with the national average, the prevailing territorial governance models have not successfully integrated biological, socioeconomic, cultural, and political aspects to create models for the sustainable use of natural resources with social welfare and environmental conservation objectives, and that consider the cultural and socioeconomic aspects of the territory.

Armed conflict. Although land and natural resources appropriation has not been the ultimate goal of the armed conflict, this has been a means to achieve social and economic control of the territory, with severe consequences for society and the economy. In addition, there are no estimates of the conflict’s impact on biodiversity and ecosystem services.

The armed conflict is characterized by forcible displacement of populations. During 2015-2017, UMAIC (2017) estimates a population of 54,682 displaced persons in Chocó (of a total of 510,047 inhabitants); there were 71,721 displaced persons from Valle del Cauca (of a population projected in 2017 as 4,708,262); displaced persons in Nariño and Cauca fluctuated between 38,352 and 35,183 (from a total population of 1,787,545 and 1,404,205, respectively). The displacement of communities by armed groups is related to various reasons, including the interest of land appropriation for establishing intensive productive systems as extensive cattle ranching and monocultures of banana/plantain and palm crops, which have led to increased deforestation and land use conflicts. In addition, the armed groups have targeted the electric and oil infrastructure as a way to exert territory pressure and control with severe consequences for water sources and soil quality degradation. For example, as a result of the bombing of the trans-Andean oil pipeline in the Tumaco municipality, a total of 18,131 barrels of oil were spilled in the region for the period 2009-2015. The conflict has been financed by illegal economies such as the cultivation and trade of illicit crops and illegal mining activities that result in deforestation, soil degradation, alteration of hydrological resources, and air pollution.

The implementation of the peace agreement is expected to bring opportunities to mitigate poverty, exclusion, and inequality among communities left marginalized by the armed conflict. However, in the post-agreement period environmental degradation scenarios must also be considered in the event that a sustainable development model is not implemented considering the natural and cultural characteristics of the region, with an approach focused on the equitable distribution of benefits and with the positive harmonization of interests among communities, institutions, and production sectors. According to ONU-Ambiente (2017) if the post-agreement framework is not properly defined and implemented it may bring changes in land use; environmental degradation because of illegal mining; increase of degraded areas needing restoration and environmental remediation; the continuation of illegal extractive economies; and environmental challenges associated with continual displacement of human populations.

Threats to biodiversity in the prioritized MUCBs

Katíos – Caoba MUCB. The main threats to PAs, CCS, and to ecosystem services in this MUCB are presented in Table 8.

- Table 8. Threats identified for Katíos – Caoba MUCB.

| Threats | Direct causes (pressures) | Indirect causes (drivers) |
| --- | --- | --- |
| Ecosystems deforestation and transformation | - Selective logging in Los Katíos PA, mainly in the watershed of Cacarica, Tendal, Tilupo, Peye rivers, along the Río Atrato bank. - Selective logging in the CCSs and the MUCB area in general. - Changes in land use in PAs and the MUCB. - Fires in PAs and the MUCB. - Expansion of the agricultural and cattle-ranching border (in the PA). - Cattle-ranching activity in the northern limit of the Los Katíos PA. - Wetlands drainage (in the PA). - Opening of trails for fishing and logging in the Los Katíos PA. - Soil loss and erosion. - Occupancy (in Bijao sector) in the Los Katíos PA. | - Cultural factors related to limited awareness of the environment. - Cultural erosion. - Lack of productive alternatives. - Sedimentation of watersheds; for example, sediment siltation of the Río León in the Tumaradó swamp. - Armed conflict in the CCS and in the MUCB in general. - Institutional neglect of communities adjacent to the Los Katíos PA. |
| Hydrobiological resources overexploitation | - There is growing pressure on the use of fishing resources in Tumaradó swamps and the Río Atrato, mainly by the black communities of Tumaradó, Puente América, and Puerto Plata and by settlers and rural peoples. - Inappropriate use of fishing instruments and fishing in prohibited areas. | - Lack of production alternatives. - Colonization of the land by outside parties with intent to extract biodiversity that is overexploited. |
| Habitat destruction and species loss | - Hunting of animals and birds that feed the conservation targets [VOC, according to its Spanish acronym): jaguar (Panthera onca) in the Los Katíos PA. - Destruction of VOC species habitat in the PA: Chavarri (Chauna chavarri) (in Los P Katíos PA) due to wetlands desiccation. - Soil loss and erosion in the CCS and MUCB in general. | - Cultural factors related to adopting VOCs as pets. - Colonization by outsiders with extractive purposes associated with biodiversity in the CCS and the MUCB in general. - Institutional neglect of communities adjacent to the protected areas. |
| Pollution | - Inappropriate disposal of solid wastes, runoff of fuel wastes into Los Katíos PA. | - Cultural factors relating to limited awareness about the environment. - Cultural erosion. |

Source: Results of local consultations (workshops), baseline analysis.

Farallones – Calima MUCB. Threats identified in Farallones PA are recognized as critical (Table 9). Although these pressures are not monitored and hence their progress or current status is unknown, 5% of the PA (9,990 ha) is considered under pressure, as per the cover multi-time analysis for 2012.

These pressures have led to socioenvironmental conflicts in the PA relating to land use, occupancy, and property ownership. As a result, actions are being implemented to mitigate the impacts, such as mining control, control points for ecotourism and for occupancy-derived activities.

- Table 9. Threats to the Farallones – Calima MUCB.

| Threats | Direct causes (pressures) | Indirect causes (drivers) |
| --- | --- | --- |
| Ecosystems deforestation and transformation | - Selective logging in the CCS and in the conservation MUCB in general. - Extension of the agricultural border in the CCS and in the conservation MUCB in general. - Inappropriate soil usage in the CCS and in the MUCB in general. - Landslides and mass removal of soil. - Illicit crops in the CCS and in the MUCB in general. - Soil loss. - Timber companies. - Climate change. | - Non-regulated tourism in Farallones PA and the MUCB. - Poor tourism development and organization in the CCS, and the conservation MUCB in general. - Armed conflict. - Lack of resources to implement management tools. - Increased population. - Little consensus with local community stakeholders. - Weak environmental governance. |
| Habitat destruction and species loss | - Inappropriate exploitation of wildlife. - Trafficking of wildlife. | - Limited capacity for surveillance and control |
| Presence of extraction companies | - Presence of hydroelectric plant (sludge management) in the Farallones PA, the CCS, and the MUCB in general. - Non-regulated mining in the Farallones PA. - Timber companies. | - Economic factors (markets and economic policies). - Lack of resources to implement management tools. - Little consensus with local community stakeholders. - Weak environmental governance. |
| Inadequate resources consumption | - Illegal capture of water resources in the CCS and the conservation MUCB in general. - Water shortage in the CCS and the MUCB in general. - Overexploitation of resources. | - Lack of resources to implement management tools. - Little consensus with local community stakeholders. - Weak environmental governance. - Loss of heritage. - Little support for local processes. |
| Pollution and contamination | - Illegal dumping in the Farallones PA. - Fumigation of crops. | - Increase in population. - Sediment contamination in watersheds. |
| Roads and infrastructure | - Species introduction or elimination. - Changes in land cover. | - Lack of resources to implement management tools. - Economic factors (markets and economic policies). |

Sources: Results of local consultations (workshops), baseline analysis.

Cabo Manglares – Gran Familia Awá MUCB. The threats listed in Table 10 are identified for the existing CCS and, in general, for ecosystem services identified in the MUCB.

- Table 10. Threats to the Cabo Manglares – Gran Familia Awá MUCB.

| Threats | Direct causes (pressures) | Indirect causes (drivers) |
| --- | --- | --- |
| Ecosystems deforestation and transformation | - Expansion of the agricultural border. - Erosion. - Unregulated mining. - Climate change. - Forest logging. | - Lack of production alternatives. - Lack of recognition of the CCS by the government. There are no supporting actions to ensure the conservation processes and initiatives dictated in the area’s communal councils. - Lack of guarantee of food sovereignty. - Public order situation. - Lack of government presence. - Invasion by settlers. - Institutional weakness. |
| Inadequate resources consumption | - Natural resources extraction. - Resources misuse. - Unregulated mining - Solid waste. - Overexploitation of resources. | - Intensive exploitation policies. - Lack of government presence. - There are no alternatives proposed by institutions for the fishing communities to reduce pressure on resources. - Little institutional support to develop sustainable tourism. - Lack of appropriate regulations and control policies. |
| Pollution and contamination | - Hydrocarbons spillage. - Industrial-origin dumping. - Fumigation of illicit crops and oil palm crops. | - Institutional weakness. - Lack of appropriate regulations and control policies. |

Source: Results of local consultations (workshops), baseline analysis.

Munchique – Río Saija MUCB. The threats in Table 11 are identified for the existing PAs, CCSs, and in general for ecosystem services identified in this MUCB.

- Table 11. Threats to the Munchique – Río Saija MUCB.

| Threats | Direct causes (pressures) | Indirect causes (drivers) |
| --- | --- | --- |
| Ecosystems deforestation and transformation | - Cattle ranching, agriculture, expansion of illicit crops in the Munchique PA. - Logging, forestry exploitation in the Munchique PA. - Mangrove deforestation. | - Insufficient economic resources for managing the area. - Armed conflict. - Changing guidelines and policies depending on the period of government. |
| Inadequate resources consumption | - Mining in the Munchique PA. - Forestry exploitation in the Munchique PA. | - Insufficient economic resources for managing the area. - Armed conflict. - Changing guidelines and policies depending on the period of government. |
| Pollution and contamination | - Dumping of waste into the Munchique PA. | - Insufficient economic resources for managing the area. - Changing guidelines and policies depending on the period of government. |

Source: Results of local consultations (workshops), baseline analysis.

The Munchique PA has a monitoring program and a research portfolio for the PA; monitoring conducted in the PA indicates that pressures have decreased; however, it also indicates that there has been a loss of land cover. The PA has consolidated its proposal for updating the management plan and is in the process of obtaining approval. Currently, the Strategic Action Plan of the Management Plan has been implemented since the annual operational plan was approved in 2015-2016, and progress has been made in compliance with the plan, as demonstrated through monitoring of the activities and outputs. The strategic objectives have not yet begun to be monitored, as the response indicators have not been defined.

Serranía de Paraguas – Tatamá MUCB. Threats in Table 12 are identified for the PA at national level. The PA has 9,990 ha under pressure as per the land cover multi-time analysis for 2012, equivalent to 5% of the entire PA; of the 11 pressures identified (four within and seven in the buffer zone), seven are qualified as minor, two as moderate (selective logging and illegal water capture) and two are qualified as critical (agriculture, cattle ranching, and mining).

- Table 12. Threats to the Serranía de Paraguas – Tatamá MUCB.

| Threats | Direct causes (pressures) | Indirect causes (drivers) |
| --- | --- | --- |
| Ecosystems deforestation and transformation | - Cattle ranching and agriculture in the Tatamá PA. - Mining in the Tatamá PA. - Hunting and logging in the Tatamá PA, mainly in El Águila and Pueblo Rico. - Changes in land cover. | - Population increase. - Bad agriculture and livestock practices. - National policies, among others, that favor pressure increase from a buffer zone towards the Tatamá PA. - Low governance of the communities. |
| Inadequate resources consumption | - Illegal water capture in the Tatamá PA. - Conflicts due to land use. | - Population increase. - Low governance of the communities. |
| Habitat degradation and species loss | - Cattle ranching and agriculture in the Tatamá PA. - Mining in the Tatamá PA. - Hunting and logging in the Tatamá PA, mainly in El Águila and Pueblo Rico. | - Bad agriculture and livestock practices. - National policies, among others, that favor and increase pressures to the Tatamá PA. - Low governance of the communities. |

Source: Results of local consultations (workshops), baseline analysis.

1.2.2 Baseline initiatives

SIRAP Pacific. The SIRAP Pacific was created as a strategic alliance for biodiversity conservation, including VOCs and the use of biodiversity and the region’s culture. It involves institutional, community, private sector, and environmental organization stakeholders organized in a regional subsystem of PAs. The SIRAP Pacific includes 106 PAs in national and regional conservation categories and public and private governance. The SIRAP Pacific has jurisdiction over a total area of 43,684,777 ha (21.3% in the continental area, 78.61% in coastal and marine areas, and 0.9% are islands). It is a coordinating body for biodiversity management and operates using conservation strategies for PAs. The SIRAP Pacific utilizes a planning instrument to guide its management toward the achievement of regional objectives, particularly for the consolidation of onsite biodiversity conservation based on diverse conservation strategies through a particular PA and other CCSs to strengthen ecosystem services connectivity in the region, thereby contributing to the country’s general conservation objectives (ethnic areas, other protection modalities (Article 111, Act 99 of 1993) and achieving global recognition.

The Productive Transformation Program (PTP]) was created by the Ministry of Commerce, Industry, and Tourism in 2009 to promote industry productivity and competitiveness. Participating companies are supported through projects and investments for improving productive processes in terms of quality, human capital, and productivity.

The National Green Business Plan (PNNV; MADS, 2014) has as its objective to define the guidelines and provide tools for planning and decision making that enable development, promotion, and encouragement of both supply and demand for green and sustainable Businesses in the country, through the implementation of appropriate tools, incentives, institutional coordination and articulation, leading to economic growth, employment generation, and natural capital conservation in Colombia. In the Pacific region, the MADS provides support to a portfolio of 12 green business projects jointly with local communities including community-based tourism, agroforestry systems, added value to non-timber forest products, small-scale fisheries, and sustainable cattle ranching, with a total investment of USD 733,040 over the next 5 years.

Fund for the Plan Todos Somos PAZcífico. With the capacity of seeking external public credit operations for up to USD $400 million it will invest in the development of five strategic lines of action: i) utilities and urban development; ii) connectivity and competitiveness; iii) environment, culture, and sustainable production; iv) education, employability and social mobility; and v) institutional capacity, transparency, and accountability.

The Sustainable Pacific Vision Program is an initiative led by MADS with the objective of reducing the drivers of environmental degradation in the region and promoting local sustainable development based on biodiversity and sub-regional natural and socioeconomic characteristics. The program’s strategy considers land use management and governance as the basis for the sustainable use of the territory and biodiversity conservation (terrestrial and coastal-marine), water resource management and low-carbon sustainable production development, and climate change adaptation and mitigation. The program has prioritized 6 projects that are currently being formulated with an estimated investment of USD $6,634,814.

Instruments contained in the final agreement for ending the conflict and building a stable and long-lasting peace. CONPES 3867 defines the institutional readiness strategy for peace and post-conflict. This strategy defines the programmatic scope of interventions, institutional framework, means of implementation, and the principal financial and operations mechanisms. Other legislative mechanisms for implementing the agreement are the Fast Track, presidential powers for peace, Decree 3886 on payment for environmental services, national plans for integral rural reform, the development of programs for land access and use, and special areas set aside for peace. The special areas idea was developed with the areas that most affected by the conflict in mind, and which are grouped into the areas that are part of the Territory-Focused Development Programs (PDET, according to its Spanish acronym). These areas will have a representative before the House of Representatives from each PDET area. The plan for implementing the peace agreements will be critical, in addition to the areas prioritized for this intervention. Through Decree 1650 of 2017, the municipalities that are located in the territories most affected by the conflict will receive an economic benefit to support businesses operating in these municipalities; they are designated as areas most affected by the conflict (ZOMAC, according to its Spanish acronym]). Of the total 28 municipalities that correspond to the area of project intervention, 21 are in these areas: seven municipalities in the Department of Chocó, five in the Department of Valle del Cauca, four in the Department of Nariño, two in the Department of Risaralda, and three in the Department of Cauca.

The PDETs are planning and management instruments used to implement the sectoral plans and programs within the RRI and the relevant measures established by the Final Peace Agreement with FARC, jointly with the territorial plans. Their purpose is to transform the structure of rural areas through an equal relationship between them and the cities of the prioritized areas, ensuring welfare and good living conditions, and the protection of multiethnic and multicultural wealth. In the project’s area of influence, there are 11 PDET municipalities: Acandí, Carmen del Darién, Riosucio, Unguía, and Litoral del San Juan in the Department of Chocó; Buenaventura in the Department of Valle del Cauca; El Tambo, Gape, and López de Micay in the Department of Cauca; and Tumaco and Barbacoas in the Department of Nariño. For the development of the PDET, a Regional Transformation Action Plan needs to be outlined, which includes the principal projects for the 170 municipalities that have been prioritized for the post-conflict, and which included nine areas in the Colombian Pacific region. At the national level, an investment of one trillion Colombian pesos per year (approximately USD $470,000,000 per year) is estimated for the next 10 years, which will support rural education and health, land use, housing and potable water, economic reactivation, right to food, reconciliation, coexistence and peace, among the most relevant issues for the region. To date in the framework of the PDET there are 1,283 works delivered or under development, with an investment of USD $ 134 billion in 52 municipalities.

Herencia Colombia Program (HeCO) was conceived as a permanent financing program that seeks to protect and ensure the sustainable use of natural capital and improve the quality and governance of the SINAP through the government’s integrated commitment within the framework of a unique agreement and with the total necessary financing, contributing to a lasting peace. The program’s proposed objective is:  “By 2020, conservation and long-term financing is ensured for 20 million hectares, which represents 10% of the country’s territory, through increased coverage, effective management and governability of the National System of Protected Areas of Colombia and other complementary conservation strategies in sustainable landscapes, as spaces for inclusion and building peace, generating opportunities for the well-being and development of humans within the context of climate change”. This commitment is accomplished within the framework of a single agreement and with the financing required to achieve the goals proposed by Herencia Colombia, contributing to a scenario of peace and generating other benefits. The goals to achieve the objective are: i) increased protection of natural capital; ii) effective management, and iii) landscape governance. The Pacific mosaic of the HeCo East program is among those prioritized and is led by an inter-institutional group composed of MADS, PNN, Moore Foundation, WWF, Natural Heritage Fund, WCS, and CI.

The GEF project Implementing the Socio-Ecosystem Connectivity Approach to Conserve and Sustainably Use Biodiversity in the Caribbean Region of Colombia (GEF ID 5288), which is also known as the Bio-Caribbean Connection, has as its main objective to implement a strategy of socio-ecosystem connectivity that includes inter-institutional articulation, territorial planning, social participation with an intercultural vision, effective management of existing PAs, creation of new PAs, and the promotion of sustainable production models.

The Support Program for Production Alliances led by the MADR is aimed at incrementing companies’ competitiveness and improving poor rural communities’ development in a sustainable manner through associations promoted by the private sector. For the period 2016-2018 in the project’s area of influence, the alliances highlighted are coconut in Valle del Cauca and Nariño, cocoa in Nariño and Risaralda, achiote in Chocó, and chontaduro in Risaralda.

Support initiative for biodiversity ideas and business initiatives (IINB). In 2016, the GEF/ United Nations Development Programme (UNDP) Small Grants Program and WWF – Colombia, within the framework of the GEF project Conservation of Biodiversity in Landscapes Impacted by Mining in the Chocó Biogeographic Region (GEF ID 4916), joined together to create the IINB, whose objective is to foster green businesses that sustainably use biodiversity in the Chocó. This process has the participation of local partners as CODECHOCÓ, CORPOURABÁ, IIAP, and BIOINNOVA. IINB received 120 profiles of green ideas and businesses after a public solicitation was made, of which 15 initiatives were selected (10 businesses and 5 business ideas) for non-timber forest products, sustainable agro-systems, and ecotourism, which currently receive financial support for infrastructure, machinery, and equipment; specialized technical support and training in business and organizational strengthening. The GEF-UNDP Small Grants Program declared an investment of USD $740,000 for the selected initiatives for a 12-to-24-month period in 2017 and 2018.

The project Jungle and Ocean Borders for Peace (2017-2020) was developed within the framework of the Fiduciary Fund for Peace with support and financing from the European Union and IIAP in the amount 3.2 million euros provided by the European Union and 800,000 euros by Colombia. The project will provide a better quality of life for 3,000 black and mestizo fishermen and 1,900 farmer families in the municipalities of Bahia Solano, Nuquí, and Juradó, in the northern region of the Chocó.

The Connected Landscapes Program, implemented by the Action Fund, adopts eight projects from the BioREDD+ portfolio. The program’s objective is to support the efforts of Colombia in mitigating and adapting to climate change, avoiding deforestation and degradation of ecosystems and loss biodiversity, and encouraging the country’s sustainable rural development. The program promotes the use of market tools, such as payment for environmental services, to preserve and recover forests and jungles within the Chocó biographic region. Likewise, it promotes the empowerment of the community governance and develops alternatives for conservation and sustainable management of resources, with the goals of 669,488 ha protected, 1,780,016 tons of CO2 emissions avoided annually, 8,325 families benefited, and five lines of production improved: cocoa, coconut, naidí, chontaduro, and fishing.

Local Sustainable Development Program – Budgetary Support. Conducted by PNN – MADS with the support of the European Union, this program seeks to contribute towards building peace in marginalized area of the country affected by its historic conflict by reducing pressures and threats on PAs from extractive and inappropriate uses; articulation of actions and processes with local ethnic group authorities and organizations of peasants and fishers communities representatives; development of a public policy for transforming territorial conflicts in SPNN areas with rural communities, and strengthening and supporting economic initiatives for local development based on a sustainable use model with influence in the national parks of the Colombian Pacific region. The program has a total investment of 20.8 million euros through the mechanism of payment for results and will last until 2019. In the Pacific Region USD $1,548,715 will be invested by the PNN to support project PAs during 2018 and 2019.

United Nations Industrial Development Organization (UNIDO) leads the programs in the region. The first program consists of the development of export consortiums in Valle del Cauca through the Agro-industrial and Cosmetics Project, with an investment of USD $600,000 for 2016-2018. The project is aimed at improving competitiveness and market access to small- and medium-sized companies with export potential in these two sectors. The second program is the Cosmetics Sector Quality Program with an investment of USD $2.7 million for 2015-2018 that seeks for Colombian cosmetic products, particularly those created from natural ingredients, to overcome technical barriers in international markets and improve their capacity to comply with quality and sustainability standards.

The Pacific Region SFM Project is financed by the French Fund for the Environment (FFEM) in the amount of 9.55 million euros and will be implemented by ONF Andina for a duration of 4 years beginning in 2018. The expected challenges, outcomes, and impacts include: i) 250 direct jobs in SFM and 500 indirect jobs, and 125 jobs created in productive chains; ii) forestry planning tools and strategies at the appropriate scale of analysis are consolidated and harmonized to limit the risk of illegal and non-sustainable timber trade; iii) two SFM initiatives operating that ensure legal timber production and articulation with the development of other productive chains; iv) information generation at the local level and through scientific research that facilitates decision making and updating of public policies related to SFM of Colombian rainforests.

The Local Sustainable Development and Governance for Peace Project receives resources from the European Union, the general executor is SINCHI, and the technical coordinators include INVEMAR. The project components are: i) strengthening the Colombian environmental system (SIAC) and information systems of the research institutes; ii) creation of a buffer zone of the PAs of the Vía Parque Isla de Salamanca and Wildlife and Plant sanctuary; ii) Amazonia: municipality of Vistahermosa (Area of Special Management Macarena Norte IMD). CORMACARENA; iii) Pacific: North: Utría NNP, Golfo de Tribugá - Cabo Corrientes and the traditional fishing area; Low and Medium Atrato: Unguía, Carmen del Darién, Riosucio, Communal Councils of Cocomacia, Ascoba, communities of the buffer zone of the Katíos NNP and CODECHOCO. The first component is currently being implemented by IIAP, as one of its technical coordinators, jointly with INVEMAR; during 2019, USD $326,358 will be invested for strengthening the SIAC-PC.

The Critical Ecosystem Partnership Fund (CEPF) is a joint initiative of the French Agency for Development, CI, the European Union, the GEF, the government of Japan, the McArthur Foundation, and the World Bank, whose objective is to provide support through grants to CSOs working in the conservation of KBAs, or hotspots, that are the richest areas on earth in biological terms and the most threatened ones. The strategic investment lines of the CEPF in the hotspot of Tropical Andes are: i) to improve the protection and management of 36 KBAs that are prioritized to generate and maintain local support for conservation and mitigation of the main threats; ii) integrate biodiversity conservation into public policies and development plans of seven corridors to support their sustainable development; iii) promote local stakeholders’ participation and the integration of social and environmental safeguards into infrastructure, mining, and agriculture projects to mitigate potential threats to KBAs; iv) promote and increase opportunities to improve private sector initiatives for biodiversity conservation that benefit the KBAs; v) protect endangered species at the global level; and vi) strengthen capacities of civil society, stakeholders’ alliances, and communications to achieve the conservation outcomes of the CEPF. In Colombia, the CEPF is implemented in concert with the Fondo Patrimonio Natural in two corridors and 10 KBAs, of which at least nine are similar to the project intervention area. For the period of 2016 to 2020, this project will be funded in the amount of USD $503,772.

The departmental governments of Nariño and Chocó within the framework of the Departmental Development Plans, will investment USD $699,885 in restoration of degraded areas, reforestation with native species, sustainable production projects, and management of water resources.

The CARs (CODECHOCÓ, CVC, CARDER and CORPONARIÑO), according to their Action Plans, support activities for the conservation and sustainable use of biodiversity, territorial organization, restoration of degraded areas, and strengthening of green businesses and the SIDAPs; likewise, they contribute to the improvement of forest governance and the promotion of sustainable production practices. The investment planned by the CARs is USD $16,470,221.

1.2.3 Remaining barriers

Despite the efforts of the national government, municipalities, research institutes, civil society, and collective territories, the following barriers to achieving biodiversity conservation and effective land management remain in the Colombian Pacific region:

Barrier 1. Disarticulated planning processes hinder the incorporation of environmental, cultural and productive determinants in the Pacific region.

Within the framework of the territorial planning instruments, the capacities for governance as a function of biodiversity conservation and sustainable use, and ecosystem services in the Colombian Pacific region, the recognized barriers are: i) difficult articulation of territorial planning and environmental management processes; ii) conflicts in the land use that influence the territorial governance and access to ecosystem services; iii) the need to understand and assess the ecosystem services supply and demand; and iv) the need for territorial planning instruments and environmental management tools to be developed through participatory means, with strong inter-institutional-community alliances, and with communities and institutions that are prepared to oversee the effective application of environmental and social determinants that protect biological and cultural diversity.

Currently there are contradictions in the definition of land use among the various territorial planning instruments and disarticulation in the planning process, which make the incorporation of environmental, cultural, and productive use determinants that properly integrate conservation interests with production interests difficult. In the local communities and organizations, the planning and territorial management processes are considered non-participatory, and this is understood as a lack of political will to support production alternatives and protect biological and cultural diversity. In addition, the planning of marine-coastal areas has not been included in the territorial planning, considering its importance for the contribution of ecosystem services to the well-being of human populations.

The harmonization of planning instruments faces a barrier with regard to information. At the regional level, the identification and strategic assessment of ecosystem services is not recognized even when some specific exercises are considered. It is important for the environmental authorities to be able to determine the potential supply of ecosystem services and obtain the necessary data for determining the environmental costs resulting from the impacts of using these services. The lack of knowledge about the reduction of ecosystem services and the lack of understanding as to how it affects the sustainability of territorial development, do not allow the authorities to propose actions for their use in a sustainable manner and that will contribute to improving the living conditions of the communities in the Colombian Pacific region.

The threats identified for natural communal heritage and biodiversity identified include limited and poor institutional abilities to for monitoring and control mechanisms for the conservation of natural resources and associated cultural features. The existing organizational structures for participation and decision-making are weak, and the participation of local communities in the monitoring and control of activities that lead to the deterioration of their environmental and cultural heritage is limited. In general, the participation of directly affected communities has been limited and they play a passive role in coordinating with other stakeholders involved in territorial planning and environmental management processes. The SIRAP Pacific faces difficulties in enabling community participation, flow of information, and decision making among it strategic stakeholders within its organizational and operational structure; principally among the local stakeholders.

Within the current framework of the peace agreements, principally in such regions as Nariño and Chocó, the lack of articulation between governmental entities and communities is notable, which is why their political influence is limited in defining land use and other guidelines for territorial planning that result in the social and environmental recovery of the areas most affected by the conflict. To achieve this articulation, the communities must be strengthened and they must consolidate their own organizational structures for participation corresponding to local and regional assemblies of communal councils and indigenous resguardos, with the objective of promoting citizen participation and renewing knowledge (which is the basis for the system of authority within indigenous groups). According to a survey of citizen participation conducted by the DNP (2016), the percentage of participation in any social organization is just 11% in rural and urban areas, and this percentage is lower for the Pacific sub-regions. In addition, the elements of knowledge and behavior that have regulated uses and practices in black communities and indigenous populations begin to be lost when new generations utilize mass media more than the traditional systems that are based on everyday living and oral tradition.

Barrier 2: Insufficient management and inadequate control and monitoring of the protected areas.

Situations exist that prevent the sustainable management of PAs, which include: a) reduced government authority in areas where illegal groups continue to exist; b) insufficient financial resources for the integrated management of the PAs; and c) limited ability of the PAs officials to exercise monitoring and control.

PAs under different management categories, such as either public or private governance, and with the objectives of either strict protection or restoration and sustainable use, generate indisputable benefits for biodiversity and human communities in their respective regions. However, there are limitations in the maintenance and sustainability of such areas; it is estimated that the financial gap to cover the inter-institutional activities for the operation of the SIRAP Pacific is approximately 85%. PA institutions rely mostly on national budget allocations and inter-institutional cooperation; these sources of financing are insufficient to guarantee the effective management of PAs in the Pacific region. This problem is more serious for regional PAs that depend on fewer resources for their management.

Also, there are weakness in terms of human capacities for the management, monitoring, prevention, control, and surveillance of PAs. The shortage of economic resources and personnel faced by those responsible for the administration of PAs does not allow them to address PAs governance and management needs, which makes it difficult to achieve effective and real compliance with their conservation objectives.

With regard to the CCSs, because they are not part of the SINAP, they are not fully recognized by the central government, which means they cannot be direct beneficiaries of the action proposed by the government. For the recognition of the CCS by the National Government, these must be ecologically characterized and the related information systematized; in addition, their types of governance need to be understood, as well as their management practices and effectiveness, to guarantee their permanence as a conservation strategy. Participatory methodologies must be developed for their management and for their monitoring, in order to generate information that measures the contribution of the CCSs to the strategies and goals of the country’s commitments to international agreements (Aichi, CBD).

The CCS are focused on the management of biodiversity and system services in situ; however, the lack of ability for proper management is evident in both, as well as the need to strengthen the communication channels between the stakeholders that would allow joint technical, financial and participation efforts that contribute to the sustainability of the entities dedicated to biodiversity conservation.

Furthermore, the SIRAP Pacific has not been able to make feasible the participation of strategic stakeholders as part of its organizational and operational structure: local-, departmental-, and subnational-level stakeholders. In particular, financial limitations exist that prevent these stakeholders from participating in an active and consistent manner in the decision-making processes. The challenge is to develop governance and financing provisions in line with the roles and characteristics of the various institutional, community, and social stakeholders.

Barrier 3. Low diversification of production and limited added value to biodiversity products.

Although the Pacific region has the potential to diversify sources of income, illegal timber extraction, mining, illicit crops, and unsustainable farming production continue to be the main sources of income for rural populations. Despite the important effort in developing programs, projects, and initiatives for sustainable production and generation of products and services from the sustainable use of biodiversity, the potential for green businesses in the region is widely underexploited; there are basic production chains with little added value, producers with limited technical knowledge or support, and poorly organized production systems that are disperse and limit the types of products. Traditionally, extension and technical assistance programs, as well as the rural support services, have prioritized farming production systems with little investment in silviculture, agro-silviculture, or production based on biodiversity-derived products.

Regarding biodiversity products, most of the production is hand made and there are no consolidated supply networks to ensure a constant supply. Biodiversity-derived products have traditionally been used for local or family consumption; nevertheless, its commercialization has been more oriented towards the use of raw materials and basic inputs than in transformed products, and has been linked to individuals, production units, or entrepreneurs, 90% of which has been non-formalized. This issue has diminished the value chain since profits are not capitalized.

Although there is a promising national and export-based market for biodiversity-derived products in the sectors of cosmetics, pharmaceuticals, and food, producers rarely participate in these markets. They generally have little knowledge of the markets and their regulations; they do not have marketing abilities or knowledge about the various products; and they have limited access to the market information. In cases where biodiversity-derived products have been taken to the market, private companies have not fulfilled the business agreements made with the communities.

There are community-based initiatives for working with biodiversity-derived products and projects of transformation units have been developed; however, these initiatives are weak with regard to technical aspects, access to the markets, organizational and administrative capacities, logistical and transportation costs, and the need for strengthening viable alternatives for the sustainable use of biodiversity in the territories.

In the new post-conflict scenario, the communities will have the challenge of eliminating unsustainable use practices and reduce disarticulation with government institutions to achieve progress in the sustainable use of the natural capital of the Colombian Pacific region. The opportunities this natural capital provides for peace building implies rethinking the rural context beyond agriculture and livestock, considering the natural heritage, specifically the innovation of the use of biodiversity and ecosystem services as an alternative to diversify rural production, revitalize the economy, and offer a wide horizon of possibilities to strengthen local cultures, validate local knowledge and associated processes, and improve coexistence spaces, among others.

## 1.3 THE GEF ALTERNATIVE

1.3.1 Project strategy

In order to eliminate the barriers mentioned above, the project will develop an integrated strategy based on: i) strengthening the territorial planning and management of the Colombian Pacific region to ensure natural resources sustainable use and sustainable development in the context of peace building and economic growth; ii) improve articulation among different institutional, sectoral, and community interests to promote long-term life strategies and biodiversity conservation, prioritizing post-conflict areas; iii) promote local sustainable development models based on biodiversity and forest sustainable use, incorporating cultural elements and local knowledge to improve communities’ food security and incomes and reduce pressure on strategic ecosystems through forest-derived production and transformation; and iv) enhance SFM mainly in collective territories.

The project implementation will consider two approaches: conservation mosaics and green businesses.

Conservation mosaics. This approach is based on two experiences of projects supported by the GEF in Colombia; the “conservation mosaic approach” and the “socio-ecosystem connectivity approach”.

From an ecological perspective, the conservation mosaic is defined as “networks of protected areas and complementary landscapes including combinations of national parks, marine and land production landscapes and territories of collective ethnic property”. This approach works in two dimensions: on one hand, “definition and implementation of short-term actions (…) to reduce pressures and promote the integrated management of protected areas and buffer zones through conservation and sustainable use measures. The conservation mosaics propose the generation of conditions that contribute to territory consolidation, where conservation and development are coherent and interrelated in the long term” . In the long term, the conservation mosaic approach is based on social and ecological variables, understanding the social agreements as the core management concept and as an actual contribution to the effective and sustainable management of the protected area, this latter understood as part of the territory”. The mosaic conservation model is based on two key concepts: territory approach and ecosystem vision. The mosaic approach conceives the territory as a social construction in a given ecological landscape and, as such, as a dynamic socio-ecological process.

On the other hand, the “socio-ecosystem connectivity approach” introduces the idea of connectivity, defined as the “collective construction of conservation mosaics and the use of inter-cultural dialogue mechanisms and social participation to promote the recovery of ecosystem services through environmental and land use planning, as well as the use of participative management tools among institutions, communities, and productive sectors.”

According to the mosaic approach, the conservation mosaic consolidation requires “consensus on the concept of territory, interaction among the different territory use and management strategies and the way to address local environmental management.”

The mosaic approach will allow an integrated treatment of a defined geographic space where environmentally critical areas are combined in collective territories, PAs, and production landscapes to preserve cultural, biological, and ecosystem services diversity, and generate sustainable economic opportunities that are alternatives to illicit and unsustainable activities—these are the MUCBs. Precisely, this approach allows the participation of social and institutional territorial stakeholders in making decisions that benefit or affect their territory (i.e., it promotes participatory-based territorial management).

Green businesses. The National Green Business Plan (PNNV, according to its Spanish acronym]) defines green and sustainable business as “economic activities offering goods and services that generate positive environmental impacts and incorporate good environmental, social and economic practices focused on the life cycle that contribute to environment conservation as natural capital that supports the territorial development.”

According to the PNNV classification, there are three green business categories: i) sustainable goods and services derived from biodiversity; ii) industrial eco-products; and iii) carbon markets. The project will be focused on category i) covering three sectors: a) sustainable agro-ecosystems; b) bio-commerce; and c) restoration.

Through the green business approach, the project proposes a real and direct connection between farmers and buyers for at least five biodiversity-derived products. This will enable the generation of minimum two benefits: i) minimize risks related to commercial activity in establishing formal agreements between farmers and a commercial partner, and ii) focus the development of biodiversity-derived products on the real accomplishment of specific market quality requirements. This strategy will ensure the application of a value chain approach with real introduction to the market.

Based on these approaches the project considers four components:

Component 1 of the project will support the articulation of territorial management tools at the departmental and municipal levels, including the ethnic perspectives of the territory, sectoral interests, and institutional policies. Additionally, the component will contribute to safeguarding cultural, biological, and ecosystem services diversity in the existing plans and implement monitoring mechanisms for allowable land uses. Likewise, within the SIRAP Pacific framework, the component will enhance the capacities of institutions and inhabitants to improve participation in the decision-making spaces regarding conservation and sustainable use of biological and cultural diversity.

Component 2 of the project will strengthen the governance mechanisms of the PAs as well as improve their management. Voluntary community conservation regulations regarding natural resource use and management will be developed and implemented incorporating the perspective of the indigenous, black communities, and rural populations, and will contribute to their characterization and recognition as conservation areas within the SINAP. Jointly with the declaration of new PAs (also supported by the project), this will contribute to national and international goals for biodiversity conservation and sustainable use.

Sustainable production alternatives will be created through Component 3 based on biodiversity-based production and use with added value and promotion of nature-based tourism, thereby contributing to the creation of sustainable economic alternatives, improving the communities’ quality of life, and building peace in territories affected by the armed conflict.

Component 4 will enable the participatory development of action plans for the MUCBs. This component will systematize and communicate lessons learned and good practices resulting from the project for biodiversity conservation, SLM, and SFM in the Colombian Pacific region; to that end, a communication strategy will be developed appropriate to each MUCB. Finally, as part of this component a project monitoring and evaluation (M&E) plan will be implemented.

1.3.2 Objectives, outcomes, and outputs

Project objective

To mainstream the sustainable use and conservation of biodiversity and the provision of ecosystem services that support human welfare and vulnerable landscapes of the Colombia’s Pacific region in view of generating global and local environmental benefits and supporting the peace process.

Table 13. GEF 7 Core Indicators.

| Project Core Indicators |  | Expected at CEO Endorsement |
| --- | --- | --- |
| 1 | Terrestrial protected areas created or under improved management for conservation and sustainable use (Hectares) | 841,741 |
| 2 | Marine protected areas created or under improved management for conservation and sustainable use (Hectares) | 190,282 |
| 3 | Area of land restored (Hectares) | 1,000 |
| 4 | Area of landscapes under improved practices (excluding protected areas)(Hectares) | 210,193 |
| 5 | Area of marine habitat under improved practices (excluding protected areas) (Hectares) | NA |
|  | Total area under improved management (Hectares) | 1,243,216 |
| 6 | Greenhouse Gas Emissions Mitigated (metric tons of CO2e) | 10,646 |
| 7 | Number of shared water ecosystems (fresh or marine) under new or improved cooperative management | NA |
| 8 | Globally over-exploited marine fisheries moved to more sustainable levels (metric tons) | NA |
| 9 | Reduction, disposal/destruction, phase out, elimination and avoidance of chemicals of global concern and their waste in the environment and in processes, materials and products (metric tons of toxic chemicals reduced) | NA |
| 10 | Reduction, avoidance of emissions of POPs to air from point and non-point sources (grams of toxic equivalent gTEQ) | NA |
| 11 | Number of direct beneficiaries disaggregated by gender as co-benefit of GEF investment | 4,000 (40% women, 60% men) |

The intended goals for the project are:

- 2,793,546 ha with reduction of current and potential pressures caused by changes in land use and forest degradation, as a direct effect of the project.

- 44,084,957 ha (marine area: 34,762,783 ha; continental area: 9,322,174 ha) corresponding to SIRAP Pacific management area with reduction of current and potential pressures due to change in land use and forest degradation, as a direct effect of the project (scaling).

- 210,193 ha of strategic importance for biodiversity conservation outside the PAs that apply guidelines and are managed to be included in the planning instruments under improved management.

- Areas (ha) contributing to socio-ecosystem connectivity in the Colombian Pacific region (the target will be established during the project implementation stage).

Component 1. Institutional strengthening to support conservation and sustainable use in the Pacific region of Colombia.

Outcome 1.1. The territorial and environmental management planning instruments are harmonized with the instruments developed by the black and indigenous peoples to safeguard biological, cultural, and ecosystem services diversity, leading to a general reduction in potential threats from development- oriented activities.

The targets for this outcome are:

a) 44,084,957 ha (marine area: 34,762,783 ha; continental area: 9,322,174 ha) corresponding to the SIRAP Pacific management area (indirect target landscape) of which at least 1,243,216 ha (direct total area).

b) 210,193 hectares of strategic importance for biodiversity conservation outside PAs

Output 1.1.1.  A Diagnosis and Strategic Assessment of the ecosystem services in the Pacific Region.

Output target:

- 4 analyses and strategic assessments of ecosystem services for four MUCBs.

This output will enable the characterization of ecosystem services in the priority MUCBs and knowledge of the different values of the services from the perspective of the various beneficiaries of such services (institutional, sectoral, and academic vision, ethnic cosmovision, etc.), as well as the identification of the ecosystem services that are a priority for human welfare according to each territorial context and the differentiated distribution of services use and access. The ecological, economic, and cultural assessment of ecosystem services and the analysis of services’ interdependencies will be key to understanding the territorial dynamics and making informed decisions.

This ecosystem services assessment approach is based on in the proposed methodology for Integral Assessment of Biodiversity and Ecosystem Services presented by MADS and IAvH, within the PNGIBSE framework. Additionally, it considers the conceptual and methodological development for the multicriteria assessment of ecosystem services implemented by the GEF/FAO/COL/041 project, Implementing the Socio-Ecosystem Connectivity Approach to Conserve and Sustainable Use Biodiversity in the Caribbean Region of Colombia (GEF ID 5288).

Outcomes of the ecosystem services strategic assessment will be inputs to: i) identifying the indicators of biodiversity and ecosystem services monitoring in the project intervention area; ii) identifying threats and opportunities that will complement the exercise of conservation prioritization in the SIRAP Pacific, iii) analyzing the socio-ecosystem connectivity carried out in the MUCBs; iv) analyzing environmental conflicts; v) developing Component 2 outputs, including SIRAP financial strategy, construction of technical guidelines for positioning CCSs, and the PAs’ effective management in terms of monitoring and financing; and vi) contributing to the development of Component 3 outputs, including ecotourism and forest and non-forest products as ecosystem services, and supporting green business initiatives (Outputs 3.1.1 and 3.2.1), market analysis of biodiversity products (Output 3.2.2), and analysis of nature-based tourism initiatives (Output 3.2.3).

The identification and characterization of ecosystem services and the strategic assessment of priority ecosystem services will be performed in the following MUCBs: Katíos–Caoba, Farallones–Calima, Cabo Manglares–Gran Familia Awá, and Munchique–Río Saija.

During the first year of the project, background information and previous exercises in the region and the country will be reviewed to construct a baseline that incorporates ethnic and gender perspectives, lessons learned, conceptual approaches and methodological tools, and the identification of information gaps. This will be done in a participatory way that results in a joint validation with the support of a multidisciplinary team that includes the communities, with participation and effective representation of women, institutions, and academia.

In addition, types of ecosystem services will be characterized and the different values provided by the services will be identified for the various beneficiaries, which incorporate local and regional wisdom and knowledge (e.g., cosmovision of communities, productive, institutional, and academic sectors vision, etc.) through tours and other methods (e.g., spatial analysis with GIS, surveys, interviews, participative mapping, etc.). Based on the identified ecosystem services and considering the services prioritized in the project development, the services to be evaluated will be prioritized.

The strategic assessment of these services, which will begin in the first year of the project and extend into the first half of the second year, will apply methods and tools from various disciplines (that conduct ecological, economic and cultural assessments) so that the different forms of assessment are visible to the services beneficiaries—including women’s participation—as well as their corresponding territorial scales (national, regional, and local).  For the strategic assessment of ecosystem services in the project, the integration and complementarity of biophysical approximations, monetary values, and sociocultural values will be performed (tradeoff analysis).

During the second year, with inputs from the activities carried out in the MUCBs and through workshops and interviews, ecosystem services at regional level will also be identified for the Colombian Pacific region. Progress will be achieved in the strategic assessment of this service at this scale; the progress will be mainly in terms of the ecological and economic assessment and the proposal of cultural assessment integration at this scale.

During the second year, the results of the ecosystem services strategic analysis and assessment will be disseminated to the participants of the process. In the intervention plan for each MUCB (Output 4.1.1), the usefulness and incorporation of the results of the ecosystem services strategic analysis and assessment will be defined according to the particular context and different inputs that this output will provide. During the same year, the corresponding delivery and incorporation of outcomes will be done for the respective project outputs.

Output 1.1.2. Agreed guidelines on harmonization of departmental/municipal territorial plans and Indigenous Peoples’/Black groups’ instruments, with a gender approach.

Output targets:

- 1 Guidelines.

- 24 planning instruments reached.

- 6 pilot areas in MUCBs.

- Gender chapter included.

This output comprises the creation of guidelines for the harmonization exercise of territorial planning and use instruments at the departmental and municipal levels and in collective territories (Black and indigenous peoples), so that: i) conflicts of land use are reduced among the different instruments; ii) an approach of biodiversity and ecosystem services conservation and sustainable use is incorporated; and iii) the planning instruments reflect the local communities needs and expectations within the framework of the differential rights recognized for them.

The guidelines will be developed based on pilot cases in the MUCBs of Katíos–Caoba, Farallones–Calima and Cabo Manglares–Gran Familia Awá (two pilot cases in each MUCB). These guidelines will be defined depending on the instrument to be harmonized, considering that the project seeks to harmonize land use planning and other instruments such as forest zoning and management plans (Output 1.1.4), PA management plans and restoration (Component 2), and green business plans (Component 3).

During the first year of the project, the criteria to prioritize the pilot cases in the selected MUCBs will be defined and applied. The definition of pilot cases prioritizes the departmental and municipal territory planning instruments and the planning instruments of Black and indigenous peoples with whom the work will be carried out. This prioritization will be included in the intervention plan of each MUCB. In addition, a characterization of priority departmental and municipal territory planning instruments will be conducted in terms of their structure, duration, development, or review period, contents, ethnic and gender perspective inclusion, level of complementarity, and other defined variables to assess the current status of the inclusion of elements that safeguard cultural, biological, and ecosystem services diversity, and the existing opportunities, needs, or difficulties for including these elements or guidelines. The characterization of these instruments will include a path for including the socio-ecosystem connectivity approach within the planning instruments of the GEF ID 5288 project implemented by FAO in the Colombian Caribbean.

In the development of this output the environmental determinants and issues established by the CARs will be considered and understood as the guidelines for determining land use planning, which are mandatory for the territorial agencies in developing their planning instruments, with the respective inclusion of PAs, key environmental areas, strategic ecosystems, and other current environmental considerations. This activity will give consideration to these documents in developing the output, and constant communication will be maintained about progress with the corresponding environmental authority. Each CAR will subsequently evaluate the opportunity to include or not include elements from the guidelines to safeguard cultural, biological, and ecosystem services diversity in such documents.

Considering that currently all ethnic groups have internal regulations, but not all of them have administrative and management plans for the natural resources of their titled territories, the project will support the development and/or updating of at least one instrument in each MUCB, where pilot exercises will be conducted that will generate key inputs for its harmonization with the planning instruments. In the first year, the construction process of these instruments will begin in a participatory manner, encouraging Black and indigenous peoples to formulate their own instruments with support from the Project Technical Team (PTT).

Additionally, in the first year, an analysis and evaluation of conflicts among the departmental and municipal territorial planning instruments (POTs/PDOTs) will be conducted regarding the self-determined instruments of black and indigenous peoples, among other instruments such as the respective environmental determinants and issues and the environmental zoning of watersheds, PAs, or CCSs, as the Forest Reserve Areas of Act 2 (1959). This assessment will be carried out to have inputs for the definition of guidelines, to identify the opportunity or difficulty of harmonizing instruments, to identify conflicts among instruments relating to land uses defined in the territory, and to construct the path to be followed.

During the first and second years of the projects, workshops and meetings will be held to jointly define and validate the guidelines for the proper harmonization and incorporation of forest zoning and management plans (Output 1.1.4), PA management plans, restoration plans (Component 2), and green business plans (Component 3) in the territorial planning and environmental management instruments for harmonizing the planning instruments.

These guidelines refer to documents, mapping inputs, and in general, instruments incorporating cultural, biological, and ecosystem services’ diversity and the respect and preservation of traditional knowledge associated with biodiversity management, based on pilot cases and considering a regional approach. To that end, representatives of the local beneficiary communities will actively participate, including the effective participation of women and the active participation of the Ministry of Internal Affairs, among other key participants. In addition to recognizing the self-determined instruments of Black and indigenous peoples as inputs—mainly their environmental zoning—the results of the ecosystem services strategic assessment (Output 1.1.1) will be considered and the work of environmental and social safeguards will be recognized as a precedent in which United Nations agencies as FAO, UN Environment, the MADS, among others, have achieved progress. The national interpretation of environmental and social safeguards will be considered within the framework of the United Nations Collaborative Programme on Reducing Emissions from Deforestation and Forest Degradation (UN-REDD), as well as, in general, the progress regarding the Safeguards Information System from UN Environment. Similarly, progress in this area will be considered within the framework of the GEF/PNUD-WWF project, Conservation of Biodiversity in Landscapes Impacted by Mining in the Choco Biogeographic Region Chocó (GEF ID 4916). For more information regarding the environmental and social safeguards of this project, see Section 2.1.

Finally, during years 3, 4 and 5 of the project, progress will be made in the application of the guidelines developed, with early actions according to the context of each instrument. These actions may be meetings at the national, regional, and local level with persons responsible for formulating the POTs/PDOTs, interinstitutional management, technical support in POT/PDOT formulation and/or review, workshops to strengthen technical capacities, and information gathering.

These guidelines, as in Output 1.1.1, will serve as inputs for the process to define the Territorial Planning Model for the Colombian Pacific region.

Output 1.1.3: A tailor-made and open-access SIAT_PC (integrated with the Environmental Information System of Colombia - SIAC) - strengthened to harmonize the existing planning mechanisms in the Pacific Region.

SIAT-PC is part of SIAC and is recognized as the integrated set of policies, processes, technologies, and stakeholders involved in environmental information management aimed at generating knowledge for informed decision-making, environmental education, and social participation in the Colombian Pacific region. SIAT-PC is an integrator level between the national and local spheres upon which regional processes will be developed. “The SIAT-PC mission is to integrate and enhance knowledge, capacities of entities, groups and persons through a network promoting production, exchange, maintenance and access to relevant, reliable and opportune environmental information that contributes to generate knowledge for territorial environmental planning, life quality improvement and sustainable development of the Colombian Pacific region”. The above, in line with the project’s goal of enhancing the decision-making processes to harmonize land uses in territorial planning and environmental management instruments through training mechanisms, organizational structures for participation, and flow of information, is relevant and hence the support to strengthen the SIAT-PC is defined.

SIAT-PC strengthening is supported by the project Local Sustainable Development and Governance for Peace, with resources of the European Union and whose general executor is SINCHI. The strengthening of institutional capacities through the project to SIAC and its information systems is one of the three components of the project, executed by IIAP jointly with INVEMAR. This support is focused on functional design, system construction and implementation, standardization of mapping information, and data collection and capture; this includes hardware and software supplies for the main center located in Quibdó, and for secondary centers located in IIAP branches in Guapi, Tumaco, and Buenaventura. This output focuses on the training and socialization of the system use and management to 40 community organizations of Black and indigenous peoples and other beneficiaries (47) such as mayoral offices, universities, and CARs in the departments of Chocó, Valle del Cauca, Cauca, and Nariño. These activities began in November 2017 and during 2018 the expectation is to have a SIAT-PC with standard historical geographic information on environmental, ecosystem, socioeconomic, and production issues, as well as communication with the existing national information systems such as SIAC, the decisions support system (SSD-INVEMAR]), marine environmental information system (SIAM-INVEMAR]), among others. Furthermore, a free access software will be available for local communities, organizations, and territorial entities (e.g., CARs and municipalities).

In addition to the strengthening process and recognition of the relevance of this tool to the project objectives, the supplying and equipping of two information centers will be supported in the intervention area of the MUCBs, and communication and training processes will be scaled up to extend access to the system information and use principally with territorial entities and other community organizations.

During the first year, the prioritization of two secondary information centers will be conducted, which will be supported by the project in two MUCBs. During the first and second years, training, supply, and equipment necessary in terms of hardware and software will be carried out.

In the second and third years, alternatives for communication and training will be designed and implemented, focusing on access to regional environmental information, with territorial entities (municipalities), other community organizations, and environmental and sectoral institutions (in at least three pilot cases of Output 1.1.2). During training, subjects as information, data capture mobile systems management, information management protocols, database management, information security and access, software use, and spatial analyses may be considered.

In third, fourth, and fifth years, actions will be designed and implemented for incorporating information allowing the monitoring of priority pilot cases of Output 1.1.2 in SIAT-PC, regarding implementation of guidelines to safeguard cultural, biological, and ecosystem services diversity in the territorial planning and environmental management instruments.

Output 1.1.4: Forest zoning and management plans (POFs) outside the PAs developed, updated, and implemented in a participatory way, promotes socio-ecosystem connectivity at the MUCB level.

Output targets:

- 2 POFs for 65,000 ha,  following MADS guidelines

- 2,000 hectares with forest management plans and support for their implementation

The project will provide support to CORPONARIÑO and CRC in updating their forest zoning plans (POFs), according to the guidelines of the MADS, in addition to the incorporation of the results of the ecosystem services analysis and assessment (Output 1.1.1) to safeguard cultural, biological, and ecosystem services diversity. Support to the POFs will be limited to an area that was previously agreed to with each CAR, whose boundaries could be defined by a watershed, ecosystem, or collective territory.

Additionally, for 2,000 ha in the Katíos–Caobas, Farallones–Calima, and Cabo Manglares–Gran Familia Awá MUCBs, the development and implementation of actions of Forest Management Plans will be supported. During the first year, the criteria to prioritize the sites for intervention will be defined and applied, taking as main inputs the results of the socio-ecosystem connectivity strategy application for identifying sites with the highest connectivity potential, prioritizing the buffer zones of the PAs. This activity will be carried out based on workshops with the various stakeholders, such as environmental authorities and other project partners.

The Forest Management Plans plans will consider the following aspects: i) description of the area, ii) characterization of wildlife and plant species, iii) forest inventory, iv) forest management and silviculture plans, and v) monitoring and evaluation strategy. Their implementation will begin during the second year and will be conducted directly by the beneficiaries. The project will also provide technical support in coordination with the CARs.

Outcome 1.2. Improved stakeholders’ capacity and participation to support the enforcement of harmonized planning and environmental management in the MUCBs..

The intended targets for this outcome are:

- Increase of 15% in the SIRAP Pacific’s management capacity, as measured through the GEF Development Capacity Scorecard.

  - Regional roundtable: 29% (the baseline and targets will be validated at project inception)

  - Regional/local roundtable Katios – Caoba MUCB: x%

  - Regional/local roundtable Farallones – Calima MUCB: x%

  - Regional/local roundtable Cabo Manglares – Gran Familia Awá MUCB: x%

  - Regional/local roundtable Munchique – Río Saija MUCB: x%

  - Regional/local roundtable Serranía de Paraguas – Tatamá MUCB: x%

- Increased capacity of local groups:

  - Assembly CC/CI Katios – Caoba MUCB: x%

  - Assembly CC/RI Farallones – Calima MUCB: x%

  - Assembly CC/RI Cabo Manglares – Gran Familia Awá MUCB: x%

  - Assembly CC/RI Munchique – Río Saija MUCB: x%

  - Assembly CC/RI Serranía de Paraguas – Tatamá MUCB: x%

(Baselines and targets to be defined at project inception)

Output 1.2.1. Six (6) SIRAP Pacific participation and decision-making structures, strengthened and with enhanced capacities to apply harmonized guidelines (see output 1.1.2).

This output will strengthen and make the existing participation and decision-making organizational structures within the SIRAP Pacific framework more operational, based on the SIRAP regional assembly; departmental-level organizational structures such as the SIDAP and regional, sub-regional, and local roundtables; SILAP; and other local processes of biological and cultural diversity conservation (see baseline per MUCB) through the communities’ and institutional representatives’ participation—including the effective participation of women—in technical and decision-making spaces. In addition, this output will improve the quality of the participation by equipping the physical spaces for meetings so that they are decent and appropriate spaces. This output development will be determined by: i) the strategy formulated with SIRAP Pacific to enhance effective information dissemination and socialization, ii) the SIRAP Pacific planning instrument, and iii) the SIRAP Pacific education and training plan developed within this project.

During the first year, organizational structures for participation and decision-making will be prioritized as follows: one per each MUCB (total of five) and one at the regional level. This definition will be included in each MUCB intervention plan as well as the prioritized issues for strengthening capacities.

In addition, in the first year the project will develop jointly with SIRAP Pacific a strategy to enhance the effective information dissemination and socialization from local to regional level and vice versa. Beginning in the second year, it will provide support to the development of this strategy’s priority actions (e.g., communication mechanisms such as flipcharts and infographics; the latter have been used in meetings of SIRAP Pacific) for the participation and decision-making organizational structures in each MUCB and regionally.

To strengthen the prioritized organizational structures of the SIRAP Pacific and in line with objective 3 of its Action Plan, during the first and second years the project will design jointly with SIRAP an Education and Training Plan to strengthen the two-way flow of information among thee structures at the sub-system level by promoting the technical capacities of those who are participating in the organizational structures for decision making. Beginning in the second year, the priority actions from this education and training plan will be implemented. Knowledge will be exchanged and other relevant methods will be conducted in workshops, training courses, or academic courses, and capacities will be strengthened with the participation of communities and institutions and the effective representation of women. These workshops or courses may be conducted inside the MUCB or between MUCBs at least once a year (beginning in the second to the fifth year). Subjects of the training courses will include: SIRAP Pacific (objectives, components, consolidation process of SINAP and SIRAP, participation strategy, etc.), PAs (declaration, management, monitoring and tracking), environmental authorities’ mission and management (roles, competencies, regulatory framework, SINA structure, environmental management challenges, etc.).

Output 1.2.2: Five (5) local community participatory structures, strengthened and with enhanced capacities to comply with harmonized guidelines (see output 1.1.2)

The existing local structures for community participation will be prioritized (as communal councils’ assemblies, indigenous cabildos, CSOs, in addition to communal councils or indigenous resguardos associations), where activities of capacity strengthening, intercultural and intergenerational dialogue spaces are carried out, as well as communities’ effective and qualified participation, and exchanges of experiences. The purpose of this output is to enhance oversight and monitoring of accomplishing the guidelines designed to safeguard cultural, biological, and ecosystem services diversity by harmonizing the territorial and environmental management planning instruments (defined in Output 1.1.2).

During the first year, existing structures for local participation will be prioritized, one per each MUCB (total of five). This activity will be included in each MUCB action plan (Output 4.1.1) with the goal of strengthening capacities for organization, territorial management, administration, and negotiation skills (year 2 of the project).

Beginning in the second year, the project will provide support for conducting local assemblies of the prioritized areas, at least once per year. The objective of this is to enhance organizational capacities, territorial management, administrative capacities, and discussion with the project key stakeholders.

During the first and second years, intercultural and intergenerational dialogue spaces will be designed, and the path to strengthening training and capacities of communities and institutions related to the priority areas in each MUCB will be constructed in a participatory manner.

In the second, third and fourth years, intergenerational dialogue spaces will be developed. These spaces for dialogue, strengthening, training, and exchanges of experience will be held to host information exchange and generational changeover, recognizing the value of senior citizens in the communities, as well as the participation of women and youth, looking to strengthen knowledge transfer. Specially, this activity will highlight respect for and preservation of traditional knowledge associated with biodiversity management, and traditional relationships of communities with their environment as a function of environmental balance and territorial defense. The development of these spaces for knowledge transfer is proposed using a center to educate environmental leaders/agents, and generational changeover with an ethnic and gender perspective that facilitates dialogue and the appropriation of the project’s outcomes. To develop these spaces, development needs will be identified and the requirements will be defined. The subjects to be addressed include the law of origin, ethnic cosmovision, traditional uses and practices, among others.

During the second, third, and fourth years, the training and capacity strengthening path will also be developed according to the priority subjects and the most relevant mechanisms (e.g., certification courses, workshops, etc.). Training subjects will be related to community organization, administrative capacity and for discussion with territorial entities, regulatory context, citizens’ participation mechanisms, monitoring and tracking elements, etc.

In the second year, as part of the process to generate higher capacities at the local level, the provision and improvement of three community participation and meeting spaces such as communal halls or offices (one in each of the three main MUCBs) will be designed and developed jointly with the beneficiary community. These spaces in turn will be used for knowledge exchange, and execution of participatory activities and workshops within the project framework.

During third, fourth, and fifth years, the path for exchanges of experiences will be designed in a participatory way that will define places, participants, budget, mechanisms, methods, time, objectives, commitments, and method for replication. An exchange network will be established to generate the knowledge dialogue among communities and to strengthen the monitoring and tracking of the accomplishment of guidelines designed for safeguarding cultural, biological, and ecosystem services diversity in the territorial and environmental management planning instruments.

Component 2: Integrated management of PAs, buffer zones and CCS.

Outcome 2.1. Reduction of pressures and threats to biodiversity and ecosystem services in 773,420 ha of existing PAs and their buffer zone.

The goals for this outcome are:

- 773,420 ha with reduced pressures and threats to biodiversity and ecosystem services.

- 1,000 ha restored.

- 10,646 tCO2-eq sequestered.

Output 2.1.1: Management plans and governance mechanisms developed and/or adopted include support for the implementation of priority actions in the selected areas.

The project will provide support to seven PAs (five national PAs and two regional PAs) as part of the integrated management of biodiversity in the MUCBs (Table 14).

- Table 14 – Selected PAs

| PA |  | Total Area of PA | Area of PA inside MUCB | Conservation Targets | Ecosystem Services |
| --- | --- | --- | --- | --- | --- |
| National | Los Katíos NNP | 72,000 ha. | 64,768 ha. | Cativo (Prioria copaifera) Jaguar (Panthera onca) Chavarría (Chauna chavarria) Arracacho (Montrichardia arborescens) Bocachico (Prochilodus magdalenae) | There is no characterization of the ecosystems services provided nor is there a strategy to monitor the services it provides; however, its importance is emphasized in water regulation, provision of hydrobiological resources, genetic diversity, climate regulation, and cultural and historic importance. |
|  | Farallones de Cali NNP | 196,430 ha. | 170,014 ha. | Lotic systems Picos Farallones de Cali 4 ecosystems 2 vegetation species 5 bird species Amphibians assemblage Spaces of ethnic community uses | The Farallones NNP de Cali is an important producer of goods and services for the community; it is the source of many rivers and streams, hence it is a strategic area with regard to water supply for the development and competitiveness of the Department of Valle del Cauca and its communities. It offers areas for recreation, contributes to plant and animal species preservation by protecting their habitats, and is of special interest for research. |
|  | Tatamá NNP | 51,900 ha. | 36,204 ha. | Páramo vegetation Andean Orobiome Low Andes Orobiome Magnoliaceae Andean Bear (Tremarctos ornatus) Bansia (Bangsa aureocinta). | This PA protects strategic ecosystems including the Páramo de Tatamá, environmental services such as water provision, important mammal and bird species, forest species, numerous orchid species, which together contribute to climate and water regulation processes, air quality maintenance, carbon storage, regulation of natural systems’ responses to the impact of extreme natural events and their consequences for human populations, maintenance of land for cultivation purposes, and as a site for recreation and tourism services with particular emphasis on tourism related to bird watching. |
|  | Munchique NNP | 46,969 ha | 46,969 ha. | Low rain forest Sub-Andean rain forest Andean rain forest High zone of the San Joaquín river basin Spectacled bear Bird assemblages. | This PA has one of the highest diversity indices of wildlife and plant species, most of them endemic, and harbors different endangered species. It has steep topographical relief with high hydrological wealth that is evident in more than 40 waterfalls and 30 streams and rivers. The ecosystem service that stands out as one of the benefits derived from this PA corresponds to its water supply; it is also recognized for its contribution to climate regulation, as a genetic reservoir and carbon reservoir. |
|  | Cabo Manglares – Bajo Mira y Frontera IMND | 190,282 ha | 190,282 ha. | Landscapes: Río Mira delta. Ecosystems: sea floors, beaches, estuaries, mangroves, native trees. Species: Fishing resources, hydrobiological resources, threatened, endangered, and critically endangered species. Strategic places for developing production activities, fishing areas, sites for collecting Piangua clams (Anadara tuberculosa), and sites for capturing Jaiba (Calinectes spp. and Portunus spp). | This area presents different biophysical and conservation elements such as an area for migratory bird feeding and rest areas, concentrated areas for fishing resources, mangroves and native forests, low-energy beaches, soft rock cliffs, non-carbonated bottoms, turtle nesting areas, estuaries, reefs of Piangua clams, among other biodiversity elements, which together constitute a source for preservation, restoration, knowledge, sustainable use, and recreation services for the communities. |
| Regional | Río Bravo NR | 24,278 ha | 24,278 ha | Rain Forest with high biodiversity (16 amphibian species, 23 reptile species, 57 mammals species) Migratory birds as Reinita naranja (Dendroica fusca) Bat (Tremactos ornatus) | This PA is a forest landscape unit in excellent conservation status that contains a number of waterfalls and diversity of animal and plant species. Ecosystem services include water supply, climate regulation, and services for the development of ecotourism. |
| Regional | Serrania de los Paraguas | 191,561 ha | 191,561 ha | Andean rain forest Andean bear (Tremactos ornatus) and productive landscapes | La Serranía is a conservation priority at the global level: it is a key biodiversity area and an important area for bird conservation. It is part of the Ecoregional Chocó-Darién Complex, which extends from Darién in Panamá to the province of Esmeraldas in Ecuador, and includes the Pacific slope of the tropical Andes hotspot and its corresponding basins in Colombia in Colombia, which drain to the low lands of the Chocó-Darién hotspot. It is part of Alto San Juan Complex (Citará-Tatamá-Paraguas-Duende) and contributes water to three large basins of San Juan river, the fastest flowing river of the South American Pacific region: in the north, Ingará-Tamaná, which drains to San Juan, and Cajón, which drains to Sipí and Carrapatas-Sipí (both rise in La Serranía, join together and drain to the San Juan). |

The project will provide support for actions within the framework for developing the management plan for the Cabo Manglares Bajo Mira IMND, including zoning for regulation of traditional and industrial fisheries in the PA. Consensus on the studies that will factor into the management plan and that will be supported by the project will be achieved jointly with PNN, INVEMAR, and CC. Bajo Mira and Frontera.

For the Katíos, Tatamá, Farallones and Munchique NNPs, the project will support activities to adopt the management plans and strengthen the spaces for consensus to enable effective PA governance, conservation, and protection jointly with the communities. The project will also support the implementation of activities prioritized under the management plan for the regional PAs of Río Bravo Natural Reserve (NR) and Serranía de los Paraguas.

In addition, project resources will be available to support the improved management effectiveness in the selected PAs by identifying and prioritizing the investment needs within the implementation framework of the management plans; the investments could include computer equipment, specialized software, monitoring and laboratory equipment, telecommunications and transportation equipment, facilities improvement, training of officials, and strengthening governance strategies and mechanisms. As such, the variables for which the PAs have low values will be identified through the PAs management effectiveness tool with social participation (AEMAPPS, according to its Spanish acronym]); this assessment will be supplemented by prioritization of investments and consensus meetings with PNN and CVC staff (for regional PAs). Using these inputs, an investment plan will be developed and implemented for the PAs that shall be coordinated, as closely as possible, with the HeCo program. The AEMAPPS results will be used as a guide for scoring the GEF’s PA Management Effectiveness Tracking Tool (METT) at the mid-term and final points of the project.

Output 2.1.2: One financial sustainability strategy designed and implemented for ensuring participation within the SIRAP Pacific framework.

The following three stages are proposed during the first and second years of the project to develop the SIRAP Pacific’s financial strategy and enable the achievement of the objectives and goals established in its Action Plan:

First stage. Analysis of inputs related to the financial gap and financial administrative system. This refers to identifying the financial needs through a costs and benefits analysis. Recommendations will then be provided to improve the financial management by promoting efficiency in resources management to allow long-term planning.

Second stage. Pre-selection and analysis of financial mechanisms and legal framework. The identification and selection of financial mechanisms will focus on conventional options for developing projects so as to have access to governmental and international cooperation resources, non-conventional options such as services to third parties, creation of incentives, and other economic tools. The purpose will be to create a diversified financing stable and safe portfolio. Likewise, within the strategy design framework a review will be conducted of the current legal framework, and legal/institutional recommendations will be provided for the financial consolidation of the SIRAP Pacific.

Third stage. Implementation of actions aimed at generating resources to ensure the implementation of priority actions of SIRAP Pacific’s Action Plan. As part of the financial strategy implementation, a professional will provide support for developing projects, allowing access to resources that ensure, at a minimum, the execution of the SIRAP Pacific’s participation strategy and CCS management.

From the first to the fourth year, project resources will be available to support meetings for dialogue and participation within the SIRAP Pacific, such as the Regional Technical Roundtable, Technical Committee, and General Assembly. At the end of the fourth year, the financing of such spaces will be covered, preferably, with resources generated as a result of the implementation of the financial sustainability strategy.

Output 2.1.3: Forest restoration and soil recovery plans for PAs, buffer zones, connectivity areas, and corridors are developed and implementation is kick-started in a participatory manner.

The project will support the restoration of 1,000 ha of forests and landscapes inside the MUCBs that cover the PAs, buffer zones, and areas contributing to ecosystem connectivity.

As a first step, through the application of the socio-ecosystem connectivity strategy, during the first year a preliminary identification of potential areas of intervention in the MUCBs for land restoration and recovery actions will be carried out; this may be supplemented by onsite verification of sites and current condition of the ecosystem to be restored.

The second step will be the development of land restoration and recovery plans in the prioritized MUCBs, which will be developed in a participative manner with the interested stakeholders (MADS, CARs, PNN, indigenous, black, and rural communities), including women and youth The plans, at a minimum, will include the following: i) identification of sites for restoration; ii) identification of human and/or natural stressors; iii) establishing community and institutional participation agreements; iv) define restoration methods to be used (including traditional knowledge of indigenous, black, and rural peoples); v) species selection; vi) define  activities for land restoration and recovery; and vii) monitoring strategy.

As a third step, beginning in the second year and until the end of the project, land restoration and recovery plans will be implemented through participatory means in the priority MUCBs. Agroforestry will be promoted as one of the many approaches enabling restoration of forests and degraded agricultural land, thereby contributing to landscape restoration in the MUCBs and considering their potential as a tool to improve land productivity, control erosion, and regulate water availability in degraded or less productive land, in addition to helping ecosystem restoration and contributing to biodiversity conservation, adaptation to climate change, and mitigation of its effects. Agroforestry will also offer the communities a wide variety of food and non-food products, thus contributing to food and nutritional security, generating income, improving livelihoods, and reducing rural poverty.

Finally, throughout the process, carbon that has not been emitted by soils and biomass will be calculated through identifying the project additionality. This carbon calculation will be made using methodologies that allow verifying that such actions are effective. A combination of the following methods could be used:

- Direct measurements jointly with the communities

- Data derived from activities

- Models based on the accepted statistical analysis principles, models of stored carbon and coverage increase

- Remote-sensing techniques, flow measurements, and soil sampling (for very large areas)

Last, the methodology selected for carbon calculation will manage the information in a transparent way and ensure access to it to enable improved regulation of execution of the methodology. Moreover, these methodologies shall be relevant, so they will be verified and discussed based upon national or international references that seek to achieve the same objective. They shall contain reliable variables and parameters, which are justified and endorsed by scientific studies preferably using data from officially recognized sources that safeguard accuracy and minimize uncertainty based on reproducible methods.

Outcome 2.2. New PAs and CCSs receive support for management planning and implementation.

The targets for this outcome are:

- 258,603 ha of new PAs under declaration process (three publicly governed PAs).

- 210,193 ha sustainably managed through communal CCSs

Output 2.2.1: Planning and management instruments developed, with priority actions implemented in CCSs, by the forest-dependent communities.

The project will promote and contribute to the development of planning and management instruments for communal CCSs, which respond to the local interests of communities living in the collective territories that are part of each MUCB. This process will highlight the strong link between biodiversity conservation and the worldview, beliefs, and traditions of the black and indigenous peoples living in the territory, and will contribute to the strengthening the role of these collective territories in providing ecological benefits.

During the first year, activities will identify, prioritize, and select the CCSs that will receive the project support within the Katíos–Caoba, Farallones–Calima, and Cabo Manglares–Gran Familia Awá MUCBs. Consensus will be achieved in through workshops with indigenous, Black, and rural communities; meetings with SIRAP Pacific; and through the activities to develop the participatory plans for intervention (Output 4.1.1). The application of the socio-ecosystem connectivity strategy and the CCS baseline by SIRAP Pacific and the results from development workshops held in the MUCBs during the Project Preparation Grant (PPG) phase will serve as inputs for identifying the CCSs in the MUCBs.

First, an activity will be developed for the collection and analysis of planning and management instruments for the CCSs in each MUCB. It shall be noted that such management instruments do not currently exist for most CCSs.

Once the CCSs that will receive support are selected, work agreements will be established with indigenous reserves, communal councils, and rural communities so that they may lead the characterization of the area and develop the planning and management instruments for the CCSs. The project will provide continuous technical support and accompaniment during the entire process to develop these instruments, and will promote a conservation approach based on rights, as well as the fulfillment of Free, Prior and Informed Consent (FPIC).

At the same time, the investment needs to support the implementation of the planning and management instruments will be identified and prioritized. Based on these, the priority investment plan will be drawn up for the CCSs, which will be implemented once it is agreed upon and approved, and activities are prioritized with input from the stakeholders.

Subsequently, and during the project execution, community-based monitoring mechanisms will be implemented in the CCSs that account for conservation progress and/or improvement and biodiversity sustainable use in these areas.

Finally, a document will be written detailing lessons learned from the development of the CCS management instruments of the indigenous, black, and rural peoples, also from the implementation of such management plans and the community monitoring strategies used. This document will serve as a reference for the MADS to develop similar initiatives in other areas of the Colombian Pacific region and in other countries, and it will be disseminated as part of the Component 4 activities.

Output 2.2.2: One technical guideline as support for the regulatory process to formalize the CCSs in the Pacific region considering ethnic/cultural aspects and in line with the national process.

This output will contribute to the national process executed by the MADS jointly with IAvH and with support from the GIZ to establish mechanisms for CCS identification, recognition, and registration for such conservation modalities to be considered in the territorial environmental planning processes and contribute to national and international conservation and sustainable development goals.

During the first year, a regional workshop will be performed to gain consensus on minimum technical requirements for the characterization of indigenous, black, and rural peoples’ voluntary CCSs in the Colombian Pacific region. Subsequently, in each MUCB a pilot exercise will be carried out to characterize the existing community voluntary CCS, taking as the basis the CCS inventory developed by the SIRAP Pacific. The important information to be included in this characterization is area, location, object of conservation value, extension, and management modalities, among others.

During the second and third years, the results of the pilot characterization exercise of the voluntary CCSs in the MUCBs will be submitted during a regional workshop to environmental and community officials (e.g., CARs MADS, IIAP, INVEMAR, PNN). Based on the results of the pilot exercise and the regional workshop, technical guidelines will be developed for characterizing the voluntary CCSs of indigenous, black and rural peoples of the Colombian Pacific region as a contribution to the national CCS process.

Finally, with the minimum technical information gathered for characterization of the CCSs, the project will articulate to SIAC Pacific (Output 1.1.3) one information module related to the CCSs that makes visible and integrates these conservation strategies into the territorial planning and sectoral planning processes that will trigger the consolidation of the CCSs in the entire SIRAP Pacific area of influence.

Output 2.2.3:  Priority areas for conservation are assessed and steps towards their declaration as formal PAs are taken.

The project will support the declaration process of four new PAs of public regional governance, based on SIRAP Pacific conservation priorities. During the first year, the areas identified and proposed during the PPG phase will be validated jointly with SIRAP Pacific. These areas are summarized in Table 15.

- Table 15. Potential areas to be established as PAs.

| MUCB | Potential area | Surface (ha) |
| --- | --- | --- |
| Katios – Caoba | - Relictos de Caoba | 63,686 |
| Serrania de Paraguas – Tatamá | - Serranias de los Paraguas | 191,561 |
| Munchique – Rio Saija | - Calle Santa Rosa | 3,356 |

The validation or selection of new areas will include the development of a spatial analysis that will focus on identifying the priority areas for conservation that contribute to ecosystem connectivity in the MUCB. Once the areas are validated, meetings to obtain consensus with the key stakeholders will be held in each MUCB to identify and implement the needs for support, according to the stage in the declaration process, through contracting with organizations or research/teaching institutions that have experience in this subject.

Component 3. Sustainable production practices as alternatives for local development, biodiversity protection and peace process support.

Outcome 3.1. Biodiversity and ecosystem services are sustainably utilized in forest-based productive systems and generate multiple environmental and socio-economic benefits.

The targets of this outcome are as follows:

- 10,000 ha under sustainable production systems benefiting 1,000 families.

- 40% of SFM initiatives and production systems led by women.

Output 3.1.1: Green Business action plan(s) harmonized and under implementation for fostering and developing diversified production systems are agreed upon and modalities adapted to local conditions, for supporting food security, sustainable livelihoods, landscape-level connectivity and forest rehabilitation.

Output targets:

- 3  green business plans that safeguard cultural, biological, and ecosystem services’ diversity.

- 25 green business initiatives with priority actions supported (in the MUCBs)

The project will promote the incorporation of the results of Output 1.1.1 into the five CARs’ green business plans to safeguard cultural, biological, and ecosystem services diversity within their jurisdictions. At the same time, the departmental plans will be harmonized with the Pacific region’s green business plan.

Furthermore, during the first year, an inventory of green businesses will be developed based on information provided by CARs through their green business initiatives. Subsequently, criteria will be defined for prioritizing business initiatives to be supported with project resources.

Beginning in the second year until the fourth year of the project, priority actions will be implemented to support and strengthen the green business initiatives in each MUCB. Support for 25 initiatives (five initiatives per MUCB) will be considered, based upon the actions defined in their action plans, which will contribute to creating sustainable alternatives for the residents in the MUCBs, improving their livelihoods, promoting socio-ecosystem connectivity, restoring forests, and building peace in the Colombian Pacific region.

Output 3.1.2: SFM initiatives and sustainable production systems implemented incorporating good soil and biodiversity-friendly practices, with gender approach.

Output target:

- 8 plans for SFM initiatives and sustainable production systems as a result of the project

Based on supply plans (Output 3.2.1) and the results of the market analysis and the participatory prioritization of biodiversity products (Output 3.2.2), SFM and sustainable production plans will be designed for each MUCB to improve the living conditions of families, which will also contribute to socio-ecosystem connectivity and the generation of supplies for the added value units (Output 3.2.1).

During the first year of the project, the socio-ecosystem connectivity strategy will be applied to identify the sites with higher connectivity potential in each MUCB, giving priority to the buffer zones of the PAs; this will result in technical elements to select communities participating in sustainable production. Another selection criterion will be the current or potential offer for production and/or use of the biodiversity-derived products identified through Output 3.2.1.

After the sites have been defined and agreed upon, within the framework of the participatory action plans in the MUCBs (Output 4.1.1), surveys will be conducted and participatory workshops will be held to construct a baseline on the current status of the participant families in terms of income and characteristics of production and/or use of biodiversity-derived products (practices, volume, quality, added value processes, trade, sale price, and production destination). Based on this information the sustainable production plans will be developed, considering the following: i) design of agroforestry arrangements, including landscape management tools; ii) land use planning; iii) identification of technological needs and inclusion of the traditional knowledge of back and indigenous peoples; iii) biodiversity conservation and SFM/sustainable use agreements; iv) design of field schools adapted to the context and culture of each MUCB, including a gender and ethnic approach; and v) design of local supply networks articulated to the added-value units (Output 3.2.1).

The sustainable production alternatives will be implemented under the FAO Farmers Field Schools (FFS) methodology and will promote the socio-ecosystem connectivity approach, SFM, and SLM. The FFS core objective will be to strengthen the participants’ capacities, in addition to the exchange of ancestral knowledge articulated with technical knowledge, always seeking economic, social and environmental sustainability based on the “learning by doing” technique. Each FFS is constituted by a maximum of 30 participants for a total of 1,000 beneficiary families, of which 40% will be led by women and will cover 10,000 ha.

As a basic component of the capacity strengthening process for SFM and sustainable production alternatives, the project will develop an initial workshop on “trainer of trainers,” during which local technicians will acquire technical skills and competencies in the production/use of non-timber forest products and management of groups, as well as eco-friendly soil conservation practices. Preferably the technicians will come from the priority MUCBs and will be in charge of implementing the FFSs and providing technical support to each participant family.

Once the training process is completed and the education modules have been implemented through the FFSs, the project will deliver supplies and materials to each participant in order for them to replicate the training process on their property; this will put into practice the knowledge and invigorate the communities with regard to sustainable production/use of non-timber forest products.

At the same time, progress will be made in the implementation of local supply networks whose main function will be focused on ensuring the constant supply of raw materials to the value addition units (Output 3.2.1).

Outcome 3.2. Products and services derived from biodiversity have value added and their value chains duly strengthened.

The targets of this outcome are:

- The annual average income of beneficiary communities is increased in at least 10% for the operation of the biodiversity products value addition units.

- 7 value added units of biodiversity-derived products with technical and management capacities.

- At least 5 biodiversity-derived products with access to formal markets, and fulfilling the requirements for quality, MADS green business criteria, and other standards.

- 4 community-based nature tourism initiatives strengthened that safeguard biological, cultural, and ecosystem services diversity with government and non-government support.

Output 3.2.1: Value addition units of biodiversity-derived products created and strengthened, with technical and management training that safeguard cultural, biological, and ecosystem services’ diversity.

The project will support seven value addition units of biodiversity-derived products in Katíos–Caoba, Farallones–Calima, and Cabo Manglares–Gran Familia Awá MUCBs. Two out of these seven units will be piloted and five existing ones will be strengthened. The units will be adapted and supplied with equipment and technology; furthermore, technical, administrative, and management aspects will be improved with the implementation of protocols for processing products in adherence with quality and sustainability standards. The value addition units are economic alternatives based on biodiversity sustainable use and will contribute to reducing pressure on forests and strategic ecosystems.

During the first year, seven value addition units will be selected and evaluated based on field visits, consultation with indigenous, Black, and rural community representatives, including women. The units will be evaluated in terms of their potential for success in addition to social, environmental, economic, and market aspects. The measurement of success in trading non-timber forest products makes use of criteria from the decision-making system of the World Conservation Monitoring Center of the UNEP, as well as environmental, organizational, and institutional cohesion criteria, and technical and market criteria developed by Corporación Biocomercio Sostenible.

Once the units are selected and evaluated, business plans will be developed and the operational model of the value addition units will be defined. This will contain the following: i) business model, ii) market, iii) product conditions, iv) risk analysis, v) return analysis, vi) economic viability, vii) costs structure, viii) required investments, ix) work capital needed, and x) legal aspects of the operation, among others. Development of the business plan will include the participation of beneficiary community (indigenous, black, and rural communities) representatives, which will include the effective representation and participation of women. The business plans and their associated operational models will be communicated to the communities in understandable. Each value addition unit will define its own business strategy using a fair and equitable distribution approach.

At the end of the first year, a raw products supply plan will be defined, where quality and quantity requirements will be stated in addition to the needs for technical support, materials, and supplies to provide the raw material for the value addition units in terms of quantity and in adherence with quality and sustainability standards. The supply plan will be an input for formulating the sustainable production plans considered in Output 3.1.2, and as part of such plans, beginning in the first year until the fifth year, technical support will be provided to the suppliers’ network of each value addition unit through periodic visits and exchanges of experiences among producers with the network of suppliers of each of value addition unit. The operation of the value addition units is directly related to the Sustainable Production Plans (Output 3.1.2); as long as these are successful, raw materials will be available for the operation of the value addition units.

During the second year, the value addition units will be improved, and equipment will be purchased based on a technical analysis and in accordance with standards of quality and sustainability (Output 3.2.2).

Beginning in the second year until the fifth year, support will be provided for the operation of the value addition units. Processing standards will be developed for each biodiversity-derived product, which include technical and quality specifications considering traditional knowledge of products’ use and transformation, sustainable use of resources, and reuse and recycling of resources. These standards will form the operational basis of the value addition units. In addition, training will be provided for implementing protocols as well as periodic technical support to adjust, calibrate, and improve them. Also, business capacities of beneficiaries will be strengthened through training in accounting, administration, management, and organizational development. The effective representation and participation of women and youth will be considered in training and education, as well as the use of common and understandable language.

Finally, beginning in the third year to the fifth year, a sustainability strategy will be developed and implemented based on updating and adapting each value addition unit, as well as the lessons learned from the process. Management support will be provided to maintain and expand business alliances, continue the operation of the value addition units, access working capital, access credit, and establish links with key stakeholders that strengthen technical, financial, and administrative aspects.

The project will periodically monitor the income generated for participating families as a result of the value addition units’ operation. The increase will be compared against the income identified in the baseline prior to the operation of some value addition units.

Output 3.2.2: Biodiversity-derived products with market access and complying with quality requirements, MADS green business criteria and other standards for market access.

The project will support the value addition units so that their products comply with quality standards, environmental and social requirements, MADS green business criteria, and other standards for accessing the market.

During the PPG stage, three groups of biodiversity products will be prioritized as having potential to use natural ingredients: i) natural colors, ii) oils and fats, and iii) food; these groups are in line with the potential sectors of bio-economy in Colombia where processed food, beverages, cosmetics, hygiene, agriculture and livestock are highlighted. The preselected biodiversity products are described in Table 16 and Appendix 12.

Table 16 Pre-selected biodiversity products.

| Species | Products in the market |
| --- | --- |
| Cocoa (Theobroma cacao) | Oil: it is the fatty component of cocoa. It is also known as Theobroma oil. It is used in the manufacturing of cosmetic and pharmaceutical products. Cake: it is the solid phase of the cocoa liquor. It is used in the elaboration of chocolate; and Powder: the cake can be pulverized and become cocoa powder. Cocoa powder is basically used to provide flavor to a variety of foods (cookies, ice creams, beverages, and cakes, etc). Likewise, it is used in the production of toppings for confectionary and frozen desserts. Cocoa powder is also used in the beverages industry, for example in the preparation of chocolate shakes. |
| Chontaduro (Bactris gasipaes) | Chontaduro in brine, syrup and preserved palm hearts. Products such as flour, marmalade and preserves are locally processed. |
| Coconut (Cocos nucifera) | Coconut, water, oil, flour, butter, chips, dehydrated fruit. Most of them are used in the cosmetic and food industries. |
| Achiote (Bixa orellana) | Medical, dental or cleaning products; insect repellents; specific use for cosmetics or toiletry products, food products or non-alcoholic beverages. |
| Asai (Euterpe oleracea) | Fruit extract: anti-aging agent, antioxidant and nutritive agent; represented in pulp, freeze-dried products, and beverage. Acai seed exfoliant: it has properties as antioxidant, exfoliant, anti-aging agent, vein tonic, and nutritive agent. |
| Borojó (Borojoa patinoi) | Pulps, juice, fresh fruit, candies, preserves, sauces, balsamic-type vinegar, energizing jelly, infusion beverages, liquor, shampoo, hair products and cosmetic products. |
| Jagua (Genipa americana) | Powder with attributes as blue dye, liquor, tattoo henna and gel. |

During the first year, the products will be determined based on a market analysis with a preliminary selection of biodiversity groups and products; current and potential markets will be analyzed, as well as the supply and demand, which will serve as input in the development of sustainable production plans (Output 3.1.2). This will be done jointly with representatives of the beneficiary communities (ethnic and rural), including women, youth, and the elderly, who possess an expansive knowledge of their territory, the supply, availability, and seasonality of the products will be analyzed. Additionally, traditional and technical knowledge about product use, transformation, and value addition will be reviewed. This information will be supplemented with the results of the strategic analysis and evaluation of ecosystem services (Output 1.1.1). Using the analysis of information in a participatory manner, the identified products and their strategic markets will be given priority. The criteria for prioritization developed by the UNIDO and Biointropic in 2016 will be used to select the natural ingredients containing biological, technological, and supply and demand aspects.

For each selected product, quality and sustainability requirements and standards required to gain access to the identified markets will be determined; requirements could be mandatory such as: pesticides residues analysis, heavy metals analysis, natural resources use authorization by environmental authorities, National Food and Drug Surveillance Institute (INVIMA), registration, sanitary standards, conformity analysis certificate, technical datasheets, safety data sheets, dossiers, product datasheets, good manufacturing practices, labeling, etc. They could also be voluntary and include: organic certification, Union for Ethical BioTrade (UEBT), fair trade, good manufacturing practices, organic standards, MADS green business criteria, Participatory Guarantee Systems (PGS), among others, which are implemented to highlight environmental and social attributes and gain access to the identified markets.

In addition, in the first year, activities will be held for technical strengthening of local institutions as part of the quality infrastructure; initially quality infrastructure mapping and assessment will be carried out in each MUCB where value addition units will be supported; subsequently, a training plan will be defined to be executed between the second and fourth years to improve conformity of the selected products and enhance capacities strengthened at the regional level that encourages the creation of new biodiversity products and their access to the market. The training plan will include regional and national events and exchanges.

Beginning in the second year, technical assistance and training will be provided to comply with quality and sustainability requirements. Gaps and principal barriers to access the market will be identified in the value addition units. Through technical assistance, training, education, and quality improvement plans, along with incorporation of the processing protocols (Output 3.2.1), the gaps that are identified will be reduced, and external audits will be supported to gain access to certification and/or verification of the selected quality standards.

Beginning the third year, a business strategy will be implemented for the value addition units that is agreed upon with the beneficiary communities. The business strategy will consider aspects of the business plan, results of the market analysis, and quality standards that are developed. The project will support the beneficiary communities in establishing business contacts, matchmaking forums, delivery of samples, pilot testing of trade and sale, tours, and exchanges with buyers and producers. The strategy will be supplemented with a communications program that highlights the products’ attributes, which are mainly related to their contribution to SFM and SLM, conservation and biodiversity sustainable use in the MUCBs, as well as compliance with the quality requirements.

Output 3.2.3: Community-based nature tourism initiatives strengthened with government and non-government support that safeguard cultural, biological, and ecosystem services’ diversity.

Nature-based tourism constitutes a sustainable use and conservation alternative for the PAs and CCSs of indigenous, Black, and rural peoples inhabiting the priority MUCBs. The project will support four nature-based tourism initiatives through planning tourism development, implementing early actions, and working with government and non-government allies to promote sustainability.

During the first year, an analysis of nature-based tourism initiatives will be performed; four initiatives currently in operation will be selected in the MUCBs with higher identified tourism potential (Katíos–Caoba, Farallones–Calima, and Serranía de Paraguas–Tatamá); Output 1.1.1 will provide information to select the sites and the initiatives to be supported. With the participation of the beneficiary community, which includes women and youth, an evaluation will be performed in terms of supply, tourism services, and infrastructure, as well as an analysis of market, tourist profile, conformity to quality requirements, safety, and environmental and social safeguards.

Also during the first year, tourism development initiatives will be planned. The plan will be developed through participatory means and will include a business model, actions to be developed for improved tourism competitiveness, conformity to quality standards and incorporation of environmental and social safeguards, business strategy for promotion and sales, and training, education, and investment needs.

During the second and fourth years, priority actions will be implemented in the selected tourism initiatives that may include: signposting, adaptation of trails, tourism information points, waste management, tourism activity planning, tourism services improvement (food concessions, transportation, accommodation, garbage management, guides, zoning), promotion, exchange tours, training and education, among others.

Government support (e.g., the Ministry of Commerce, Tourism Promotion Fund, Green Business program, Impulsa MiPyMES, Fondo Emprender SENA) and non-government support (mainly international cooperating agencies) will be sought to develop nature-based tourism initiatives by supporting the beneficiary communities in managing alliances to strengthen the links between communities and the other tourism value chain stakeholders, by promoting sectoral roundtables, participation in meetings, matchmaking forums, and fairs, and relationships with strategic partners, to finance tourism development plan action and promote the sustainability of the initiatives.

Component 4. Knowledge management and project monitoring and evaluation.

Outcome 4.1. Project monitored and evaluated with a results-based management approach, and communication of lessons learned.

The targets of this outcome are:

- 5 action plans for the MUCBs.

- 1 online M&E platform.

- 1 strategy of communication for development implemented.

- Mid-term review (MTR) and terminal evaluation (TE).

Output 4.1.1. Five (5) participatory action plans for the prioritized MUCBs.

During the first six months of project execution, a participatory action plan will be developed for each MUCB. This activity will encompass two stages:

First stage. Development of a methodological proposal to create an agreed-upon vision of the MUCB. This methodology will include participatory workshops and consultations with the territorial stakeholders of each MUCB, including research institutions and representatives of government entities present in the territory, such as mayoral offices and departmental governments, NGOs, communal councils, indigenous reserves, producers’ associations, and environmental and production officials. During this stage, the socio-ecosystem connectivity assessment will also be conducted for each MUCB to identify with greater accuracy the priority sites for executing project activities and outputs that will allow ecosystem connectivity, such as sustainable production systems, SFM, and forest and land restoration.

Second stage. Application of the methodological proposal that will have as a result the intervention plan of each MUCB. The plan will contain: i) priority intervention sites at the project output level; ii) analysis of opportunities and threats; iii) identification, characterization, and capacity evaluation of each potential project executing partner; iv) a work plan for the project execution period (5 years); v) one operational budgetary plan for the first year of the project; and vi) pathway for the participation of indigenous, black, and rural communities present in each MUCB.

The effective participation of traditional authorities, women, and representatives of the local beneficiary communities will be promoted in developing the action plans of the MUCBs, so that they contribute ideas and inputs to define the intervention lines in each MUCB based on their traditional knowledge, political and administrative structure, context, and territorial priorities.

These plans will recognize and respect traditional knowledge and practices and traditional knowledge systems regarding biodiversity conservation and sustainable use under FPIC.

During the first year, consensus on the formalization of the participatory intervention plan will be promoted that will also facilitate the coordinated work of territorial stakeholders and partners for biodiversity conservation and sustainable use in each MUCB. This consensus will produce bilateral participatory agreements with each communal council and indigenous reserve, describing the various products and/or activities of the project in which they are participating.

The particular ethnic and cultural characteristics of indigenous peoples and black communities residing in the intervention MUCBs will be considered in all project actions, through discussion and exchange of technical knowledge and traditional and ancestral knowledge, the full and effective participation of the various communities in project validation, development, implementation, M&E, and respecting their expressions, values, and sociocultural traditions.

Every year at least one participatory assessment will be conducted in each MUCB to update the intervention plan to evaluate the performance in the execution and develop the work and budgetary plan for the following year.

Output 4.1.2. An online M&E platform

During the first year, an online project monitoring platform will be designed and implemented that allows the project technical team to conduct consultations, and receive feedback from the territories on the progress achieved by the project in each MUCB. The platform will be designed so that operationality after the project can be maintained at a low cost and optimal management level. Likewise, the online monitoring and tracking system will enable access to the project partners for them to have updated information about the project performance.

During the first to fifth years the Project Coordinator (PC) will prepare every six months the Project Performance Report (PPR). The PPR includes the biannual monitoring of the project outcomes framework indicating the progress achieved regarding goals of each outcome and output; likewise, it includes the monitoring of risks identified in the risk matrix, as well as those not planned initially, and states the mitigation measures.

At the end of each year the PC, jointly with GEF Project Portfolio Coordinator of FAO Colombia, will prepare the inputs needed for the FAO Lead Technical Officer (LTO) to develop the Project Implementation Report (PIR). The PIR includes annual monitoring of the project outcomes framework stating the progress achieved regarding goals of each outcome and output during the year; it also includes monitoring the risks identified in the risk matrix, as well as those not planned for initially, and states the mitigation measures.

Output 4.1.3: One (1) communication strategy for development implemented

In the first year of the project, a communication strategy will be designed for the local beneficiary communities, institutions, and project stakeholders to be duly informed and in a transparent manner so that they can give and receive information on the project details and progress. In the design of this strategy key elements will be considered, such as the needs for information, communication channels, and the media, as well as communication activities.

The communication strategy will consider the following principles:

- Transparency and access to information

- Good faith and transparency of the participants

- Respect for rights and cultural diversity of local beneficiary communities

- Inclusion and representation

- Effective governability

- Gender equality

- Respect for protocols and traditional dynamics, including the verbal and non-verbal communication standards

- Assurance that all the project-related information is transparent, complete, accessible (be available and accessible to all the actors involved), clear, appropriate and easy to understand for local beneficiary communities.

Communication contents, media, and modalities will be defined respecting the guide provided by the communities, and will be stated in the participatory agreements for each MUCB intervention plan.

For its implementation from the first to the fifth years, communication strategies, media, modalities, and mechanisms for traditional knowledge transfer will be used, as well as those inherent to current trends and technologies. These mechanisms can include:

- Strengthening of local groups for dissemination

- Dialog workshops and forums

- Publications, teaching materials and notebooks in accessible and understandable languages for ethnic groups (preferable in native language).

- Radio broadcasting for reinforcing community radio stations and knowledge networks.

- Documentary photography and video

The teaching and communication tools will be appropriate to the sociocultural context of indigenous, black, and rural communities. They will address the diversity of languages and dialects and verbal and non-verbal communication modalities corresponding to the cultural diversity existing in the MUCBs, in order to facilitate their understanding and promote land restoration and appraisal of traditional indigenous and community names.

The project will document the procedures and results with the local dissemination group and will make them publicly available for replication in the rest of the Colombian Pacific region.

Output 4.1.4: One Mid-term Review (MTR) and one Terminal Evaluation (TE).

Once the project execution is initiated and after 24 months, the mid-term review will be conducted by an external consultant. The consultant will work closely with the Project Technical Team, Project Portfolio Coordinator GEF-FAO Colombia, LTO, and FAO–GEF Unit.

The terminal evaluation (TE) of the project will begin six months before the project execution is finished and will be managed by OED, in consultation with the Project Portfolio Coordinator GEF-FAO Colombia, BH, LTO, and FAO–GEF Coordination Unit. OED will be responsible to develop the terms of reference (TORs) of the TE, with inputs/comments from the project task force, the FAO-GEF Coordination Unit and, when relevant, other stakeholders

1.3.3 Project stakeholders

During full project formulation, the first three steps of the FPIC were completed: 1. Identification of indigenous peoples and black communities and their representatives. 2. Documentation of geographic and demographic information thorugh participatory mapping: workshops were conducted in each prioritized MUCB as well as meetings to inform about the project, collect baseline information, define the project results, and define the project activities. Entities and representatives of indigenous peoples that are part of the Regional Roundtable of the SIRAP Pacific participated in meetings and workshops. 3. Design of a communication plan to disseminate the project results, with local beneficiary communities and parties interested in the project.

The successful implementation of the project will largely depend on the effective communication and coordination with the multiple project stakeholders and the implementation of participatory mechanisms. The key national and sub-national stakeholders include the MADs, PNN), SIRAP Pacific, Regional Autonomous Corporations (CARs; CVC, CODECHOCO, CORPONARIÑO, CRC, CARDER), IIAP, INVEMAR, and Ministry of Agriculture and Rural Development (MADR). At the local level, the most relevant stakeholders are Departmental and Municipal Governments, organizations and communities of indigenous, black, and rural peoples, CSOs, and non-governmental organization (NGOs). The extensive stakeholder consultations and engagement that began during the PPG phase will be continued throughout project implementation. To achieve this the project will make use of several mechanisms, including: a) Project Inception Workshop, where the project will be presented to stakeholders at the national. Subnational, and local levels; b) Project Steering Committee: will be comprised of representatives of the governmental agencies, and special interest groups and will be responsible for approving the annual work plans, participation in the recruitment processes, and provide overall strategic guidance to the project; c) Project Implementation Unit (PIU): responsible for the implementation of the stakeholder engagement plan, communications plan, gender action plan, grievance mechanism, and M&E; d) Communications and Dissemination of Information: the PIU will implement a stakeholders communication plan to ensure communication with all stakeholders using a variety of  methods (meetings, telephone calls, listserv, WhatsApp, etc.),  will hire the services of communication specialists to achieve the objectives of the plan, and will have active knowledge management with the documentation of processes and lessons learned, which will be shared with all stakeholders; e) Local Committees to facilitate local stakeholder participation: will be established in all five MUCBs where field activities will be implemented; f) Gender Action Plan: will secure the involvement of both genders, but especially women who are often marginalized and whose participation in agricultural and natural resource-based activities is low compared to men; g) Grievance Mechanism: will be established and published so that all stakeholders are aware of its existence, allowing the documentation of any potential grievances and ensuring they are addressed in a timely manner; h) Activities, Training, and Engagement Plans: will use a participatory approach that is rights-based and integrates the perspectives of all stakeholders using bottom-up approaches and integrating the different views of local stakeholders and beneficiaries; and i) Decentralized M&E: including meetings with the local committees, interviews with direct beneficiaries, local and national participatory workshops, and meetings with special groups such as women to verify indicators.

The Project Coordinator and the National Project Director (NPD) will have a key role in maintaining fluid and permanent communication about the project with the interested parties at all levels in order to maintain stakeholders’ interest in and commitment to the project during its lifespan. The different decision-making spaces of the project (PSC, Regional Technical Committee, and MUCB Technical Committees) will also serve as vehicles for communication and to increase visibility regarding the project objectives and approaches. Outcome 4.1.3 specifically addresses developing and implementing the communication strategy that will be designed in a participatory way for the local beneficiary communities, project partners, territorial entities, CSOs, and other parties interested in project execution to be duly informed about how the project develops and be able to provide and receive information on the project’s details and progress. The communication activities for project development and visibility will be planned during the first 6 months of the project to ensure participation of interested parties, as well as access to relevant information. The communication strategy will seek participation, dialogue, and improvement of the project outcomes’ visibility. Any specific visibility arrangement requested by the partners will also be considered. A Communications Expert will be hired who will be responsible for developing the project communications strategy at the project outset and coordinating its implementation across all project components. The Communications Expert will work closely with a Geographic Information System (GIS)/M&E Expert on knowledge management and M&E aspects of the project.

| Stakeholder | Role in the project implementation |
| --- | --- |
| Ministry of Environment and Sustainable Development (MADS) | Executing agency of the project and GEF focal point. Main entity responsible for developing the national policy related to environment and renewable natural resources. It also shall establish the guidelines for proper land planning and use. During the project implementation process the MADS will provide expertise on biodiversity conservation and sustainable use, land use, economic tools, and incentives. |
| National Natural Parks of Colombia (PNN) | Project partner. This organization manages the national natural parks of Colombia and coordinates the SINAP. It has extensive experience in working with communities, building consensus, and participating in dialogues through its permanent presence in the territory, in addition to being a conservation leader. The project will provide support for managing the PAs. |
| SIRAP Pacific | Project beneficiary and partner. The SIRAP Pacific constitutes an articulation scenario for linking environmental officials (CARs and PNN), MADS, research institutions (INVEMAR and IIAP), institutional regional stakeholders, and ethnic (indigenous and Black) and rural communities with local conservation processes in the region. The SIRAP Pacific will participate in all of the project’s outcomes and products. |
| BIOINNOVA | BIOINNOVA’s main role is to connect science with traditional knowledge, creating territorial ownership. It works in the following areas: (1) identification of potentialities, product research and development; (2) community innovation and education; (3) implementation of conservation initiatives; (4) development of biodiversity-derived products; and (5) knowledge platform. It has extensive experience in BIO production startups, creation of companies, and successful experiences in creating local development models, valuation proposals, and knowledge transfer. BIOINNOVA will provide support to the execution of project Outcome 3.2. |
| Corporación Biocomercio Sostenible | Its main role in the project is to promote the sustainable use of biodiversity through identifying and prioritizing products, determining key aspects for their development, strengthening producers’ networks, and supporting inclusive market participation. It has wide experience in promissory products identification, supporting the communities in developing business plans, market research, territorial marketing, etc. In addition, Corporación Biocomercio Sostenible will develop activities related to corporate management, environmental services, strengthening of networks, value chains, and consolidation of local innovation at the regional or national scale. The organization will take part in the execution of project Outcome 3.2. |
| Food and Agriculture Organization of the United Nations (FAO) | As per the agreements with the Government of Colombia, FAO will serve as the implementing agency of the project. Additionally, it will help the project in execution of certain areas such as on-the-ground implementation of sustainable production models, production supply, income generation, association, capacities strengthening, and linking to markets, as well as strengthening governance by public entities and local organizations. It will be responsible for project Outcomes 1.1, 1.2, 2.1, 2.2, 3.1, and 4.1. |
| United Nations Industrial Development Organization (UNIDO) | As per the agreements with the Government of Colombia, UNIDO will be one of the project implementing agencies and will carry out some activities based on its expertise in industrial development, agroindustry and value chains, in addition to matters related to development of production protocols, designing plants for product transformation, improved competitiveness and creation of business capacity, increasing capacities for meeting quality standards and market requirements, technical datasheets development, industrial and production knowledge transfer, experts, technical capacities, among others. UNIDO will be responsible for project Outcome 3.2. |
| Ministry of Agriculture and Rural Development (MADR) | The MADR is the national entity in charge of developing, coordinating, and evaluating the policies that promote the competitive, equitable, and sustainable development of agriculture and livestock, forest, fishing and rural development processes, with decentralization, consensus, and participation criteria that contribute to improving the income and quality of life for the Colombian population. It is in charge of Rural Development Programs that incorporate equity, formalization of rural property, and the project Constructing rural business capacities, trust, and opportunity. During project implementation, actions will be articulated in relation to rural development within the framework of programs and projects managed by the MADR. |
| Regional Autonomous Corporations (CARs): CODECHOCÓ CARDER CVC CRC CORPONARIÑO | CARs are legally charged with managing the environmental and renewable resources within their jurisdictions to achieve sustainable use according to MADS guidelines. For this project, CARs are the target of actions to strengthen capacity that will improve their technical and operational capacities so that biodiversity-friendly production systems can be sustainable over time, in addition to strengthening their forest planning and management capacities. During the project, they will play a beneficiary and partner role providing support to all of the outputs. |
| Institute of Environmental Research of Pacific (IIAP) John von Neumann | The IIAP is the SIRAP Pacific technical secretariat and its objective is to conduct and disseminate scientific studies and research related to the biological, social, and ecological situation of the Pacific Coast and Biographic Chocó. During the project, the IIAP will play a significant role in developing Output 1.1.3, as this is a regional node of Colombia SIAT, and in supporting all of the outcomes and results. |
| Institute of Marine and Coast Research José Benito Vives de Andreis (INVEMAR) | INVEMAR is part of the SIRAP Pacific and its roles include conducting basic research and research applied to natural renewable resources, environment and coast and oceanic ecosystems, with emphasis on researching those systems with higher diversity and productivity, such as coastal lagoons, mangroves, rocky reefs, etc. In addition, it issues technical concepts on marine resources conservation and sustainable use. During the project, INVEMAR will participate in actions to be undertaken in Cabo Manglares–Gran Familia Awá MUCB with coastal-marine influence. |
| Mayoral Offices | The mayoral offices are responsible for promoting clean production and biodiversity conservation at the local level, and for land use and planning in the municipalities, in coordination with their technical teams. They will be project beneficiaries and participants in terms of training in biodiversity conservation matters, the harmonization of planning instruments, sustainable production systems, and strengthening of organizational structures for participation. |
| Departmental Governments | The departmental governments lead and coordinate the territorial planning schemes and plans, and guide agriculture and livestock workers. They also define departmental development plans through their Environmental and Economic Development Division. They will be project beneficiaries and partners in all the project outputs with emphasis on Outputs 2.1.2, 3,1.2, 3.2.1, 3.2.2, and 3.2.3. |
| Indigenous Resguardos and Communal Councils | The indigenous (Embera, Wounaan, Katío, Chamí, Tule, and Zenú del Chocó) and black communities constitute relevant stakeholders in project implementation, and they will be direct beneficiaries and partners through the signing of agreements (Letters of Agreement – LoA) and will receive resources to execute the activities within the project framework; they also will participate in all of the project outputs. Project preparation participatory workshops will be conducted in each priority MUCB; during these workshops the Project Identification Form (PIF) approved by the GEF SEC was socialized and feedback received from the communities; in addition, three regional participatory exercises were conducted (inception workshop, collective development, and consensus building) with the participation of representatives from communal councils, indigenous resguardos, and rural communities, ensuring a participatory project design process. The proposed steps for achieving FPIC according to FAOs Handbook are: 1) identify the indigenous peoples concerned and their representatives; 2) document geographic and demographic information thorugh participatory mapping; 3) design a participatory communication plan and carry out iterative discussions to disclose project information; 4) reach consent; 5) conduct participatory monitoring and evaluation of the agreement; and 6) document lessons learned. During the project formulation phase, ethnic groups for each MUCB were identified with an impact on intervention MUCBs and participatory mapping was conducted. Step 3 through 6 will be completed during project implementation. With the development of participatory actions plans a manifestation of FPIC from the black and indigenous peoples that will directly participate in the project will be obtained. Consent from concerned indigenous peoples will be obtained before enacting any relevant activities and the FPIC process will be implemented throughout the project’s life; this is an explicit requirement of the United Nations Declarations on the Rights of Indigenous Peoples that has been incorporated into the FAO Policy on Indigenous and Tribal Peoples, and since 2015 in the FAO Environmental and Social Management Guidelines, the FAO Project cycle, and the UNIDO Environmental and Social Safeguards Policies and Procedures (ESSPP). The FAO Partnerships and Sputh South Cooperation Division (DPS) will provide technical support for the implementation of FPIC. |
| Community Organizations | Second-tier organizations of indigenous and Black communities with influence in the MUCBs, such as the Association of Indigenous Cabildos of Valle del Cauca (ACIVA, according to its Spanish acronym]), the Association of Indigenous Cabildos Waunan, Embera Dóbida, Katío, Chamí and Tule of Department of Chocó (OREWA), the Indigenous United Organization of AWÁ People (UNIPA, according to its Spanish acronym), the Network of Communal Councils of South Pacific (RECOMPAS, according to its Spanish acronym]) that brings together 14 communal councils located on the southern coast of Nariño in the municipalities of Tumaco and Francisco Pizarro, and the Black Communities Process (PCN, according to its Spanish acronym) that brings together black community organizations of the Departments of Nariño, Valle, and Cauca, who are participating in processes related to environmental defense and sustainable development in the Pacific region. During the project these groups will participate depending on their strengthening level in the execution of activities related to Outcomes 2.2, 3.1, and 3.2. |

1.3.4 Stakeholder Engagement Plan

The description of the participation of key stakeholders has been provided in the previous description section of this Project Document; it is also summarized in the Project Implementation Arrangements section. The project will ensure the solid participation of stakeholders during the life of the project execution.

The project has placed emphasis on participation from the design phase, including government agencies, the private sector (the PIU will perform the necessary tasks to facilitate the participation of the private sector), and civil society stakeholders. For example, Outcome 1, which seeks to harmonize the territorial planning and management instruments with the planning instruments developed by the black and indigenous peoples, depends to a large extent on the will of regional and local officials and the private sector to apply guidelines for harmonization of these instruments. The project was designed with the participation of the interested parties, and during the preparation phase various consultations and workshops were held.

During the project development phase, participatory workshops and meetings were held to inform about the project, gather baseline data, and develop the project results framework through a participatory process. Workshops and meetings attended by Project Partners and representatives of ethnic groups that form part of the Regional Technical Roundtable of the SIRAP Pacific. In this way the project has the advantage of having the SIRAP Pacific as the Executing agency, as it is an institution recognized in the area and since 2013 has been consolidating a participatory conservation strategy in the territory with representatives from the ethnic groups.

A stakeholder engagement plan for indigenous, black, and rural communities has been included in the project design (see Appendix 9) to ensure that all relevant ethnic groups and organizations are consulted and participate in the project. This plan will allow full consultation with indigenous peoples to achieve FPIC.

A project governance structure of multiple stakeholders is reflected in Section 3 of this Project Document (see Project Implementation Arrangements). The Project Direction Committee will include representatives from the government and from FAO, and will make project decisions based on consensus of its members (see Section 3.2.3).

1.3.5 Grievance Redress Mechanism

FAO is committed to ensuring that its programs are implemented in accordance with the Organization’s environmental and social obligations. In order to better achieve these goals, and to ensure that beneficiaries of FAO programs have access to an effective and timely mechanism to address their concerns about non-compliance with these obligations, the Organization, in order to supplement measures for receiving, reviewing and acting as appropriate on these concerns at the program management level, has entrusted the Office of the Inspector-General with the mandate to independently review the complaints that cannot be resolved at that level.

FAO will facilitate the resolution of concerns of beneficiaries of FAO programs regarding alleged or potential violations of FAO’s social and environmental commitments. For this purpose, concerns may be communicated in accordance with the eligibility criteria of the Guidelines for Compliance Reviews Following Complaints Related to the Organization’s Environmental and Social Standards, which applies to all FAO programs and projects.

Concerns must be addressed at the closest appropriate level, i.e. at the project management/technical level, and if necessary at the Regional Office level. If a concern or grievance cannot be resolved through consultations and measures at the project management level, a complaint requesting a Compliance Review may be filed with the Office of the Inspector-General (OIG) in accordance with the Guidelines. Program and project managers will have the responsibility to address concerns brought to the attention of the focal point.

The principles to be followed during the complaint resolution process include: impartiality, respect for human rights, including those pertaining to indigenous peoples, compliance of national norms, coherence with the norms, equality, transparency, honesty, and mutual respect.

Project-level grievance mechanism

The project will establish a grievance mechanism at field level to file complaints during project inception phase. Contact information and information on the process to file a complaint will be disclosed in all meetings, workshops and other related events throughout the life of the project. In addition, it is expected that all awareness raising material to be distributed will include the necessary information regarding the contacts and the process for filing grievances.

The project will also be responsible for documenting and reporting as part of the safeguards performance monitoring on any grievances received and how they were addressed.

The mechanism includes the following stages:

- In the instance in which the claimant has the means to directly file the claim, he/she has the right to do so, presenting it directly to the Project Coordination Unit (PCU). The process of filing a complaint will duly consider anonymity as well as any existing traditional or indigenous dispute resolution mechanisms and it will not interfere with the community’s self-governance system.

- The complainant files a complaint through one of the channels of the grievance mechanism. This will be sent to the PC to assess whether the complaint is eligible. The confidentiality of the complaint must be preserved during the process.

- Eligible complaints will be addressed by the Project Advisory Committee (PAC). The PC will be responsible for recording the grievance and how it has been addressed if a resolution was agreed.

- If the situation is too complex, or the complainer does not accept the resolution, the complaint must be sent to a higher level, until a solution or acceptance is reached.

- For every complaint received, a written proof will be sent within ten (10) working days; afterwards, a resolution proposal will be made within thirty (30) working days.

- In compliance with the resolution, the person in charge of dealing with the complaint, may interact with the complainant, or may call for interviews and meetings, to better understand the reasons.

- All complaint received, its response and resolutions, must be duly registered.

Resolution

Upon acceptance a solution by the complainer, a document with the agreement should be signed with the agreement.

| Project Implementation Unit (PIU) | Must respond within 5 working days. |
| --- | --- |
| FAO Representation in Colombia | Anyone in the FAO Representation may receive a complaint and must request proof of receipt. If the case is accepted, the FAO Representative must respond within 5 working days in consultation with FAO's Representation and Project Team. FAO Rappresentative a.i.: Rafael Zavala Rafael.Zavala@fao.org Tel: +57 1 3465101 |
| Project Steering Committee (PSC) | If the case cannot be dealt by the FAO Representative, he/she must send the information to all PSC members and call for a meeting to find a solution. The response must be sent within 5 working days after the meeting of the PSC. |
| FAO Regional Office for Latin America and the Caribbean | Must respond within 5 working days in consultation with FAO's Representation. FAO Representativa: Julio Berdegué RLC-ADG@fao.org; Julio.Berdegue@fao.org Tel: (56 2) 2923 2100 |
| Office of the Inspector General (OIG) | To report possible fraud and bad behavior by fax, confidential: (+39) 06 570 55550 By e-mail: Investigations-hotline@fao.org By confidential hotline: (+ 39) 06 570 52333 |

1.3.6 Expected global environmental and adaptation benefits

The GEF investment will result in the following global environmental benefits:

2,785,452 ha of coastal-marine and terrestrial ecosystems within MUCBs that safeguard biological, cultural, and ecosystem services diversity by harmonizing territorial and environmental management planning instruments.

Improvement of the conservation and management status of strategic ecosystems in the Colombian Pacific region, including:

- 773,420 ha of existing PAs that improve their management effectiveness and strengthen natural resources governance.

- 210,193 ha sustainably managed through the voluntary CCSs of indigenous, black, and rural peoples.

- 258,603 ha corresponding to new PAs as part of SIRAP Pacific conservation priorities.

- 10,000 ha under SFM and production systems contributing to conservation and sustainable use of biodiversity, promoting socio-ecosystem connectivity and generating benefits for human well-being in the communities.

- 1,000 ha under land restoration and recovery process so that they may maintain and/or recover their capacity to generate ecosystem services.

- 10,646 tCO2-eq of carbon sequestered as a result of forest and soil restoration.

The project will also generate global environmental benefits contributing to Aichi targets 1, 2, 5, 7, 11, 15, and 18.

- Table 17. Project contributions to Aichi targets

| Biodiversity Aichi Target | Project output | Selected SMART indicator |
| --- | --- | --- |
| Target 1. By 2020, at the latest, people are aware of the values of biodiversity and the steps they can take to conserve and use it sustainably. | 1.1.3 1.2.1 1.2.2 | 6 organizational structures for participation and decision-making in the SIRAP Pacific are strengthened to safeguard biological, cultural, and ecosystem services diversity. 5 organizational structures for local community participation are strengthened to monitor land use objectives. |
| Target 2. By 2020, at the latest, biodiversity values have been integrated into national and local development and poverty reduction strategies and planning processes and are being incorporated into national accounting, as appropriate, and reporting systems | 1.1.2 1.1.3 3.1.1 | 24 local planning instruments safeguard biological, cultural, and ecosystem services diversity in the Colombian Pacific region. |
| Target 5. By 2020, the rate of loss of all natural habitats, including forests, is at least halved and where feasible brought close to zero, and degradation and fragmentation is significantly reduced. | 2.1.1 2.1.2 2.1.3 2.2.1 2.2.2 2.2.3 3.1.1 3.1.2 3.2.2 | 1,032,023 ha of new and existing PAs that improve their management and conservation status. X ha are managed to contribute to socio-ecosystem connectivity. |
| Target 7. By 2020 areas under agriculture, aquaculture and forestry are managed sustainably, ensuring conservation of biodiversity. | 1.1.3 2.1.3 3.1.1 3.1.2 | 10,000 ha under sustainable production plans (1,000 families, 40% headed by women) |
| Target 11 By 2020, at least 17 per cent of terrestrial and inland water, and 10 per cent of coastal and marine areas, especially areas of particular importance for biodiversity and ecosystem services, are conserved through effectively and equitably managed, ecologically representative and well connected systems of protected areas and other effective area-based conservation measures, and integrated into the wider landscapes and seascapes. | All | 2,614,249 ha in land and 179,297 ha of coastal-marine areas of the MUCB contribute to the sustainable use and conservation of biodiversity in the Colombian Pacific region. |
| Target 15. By 2020, ecosystem resilience and the contribution of biodiversity to carbon stocks has been enhanced, through conservation and restoration, including restoration of at least 15 per cent of degraded ecosystems, thereby contributing to climate change mitigation and adaptation and to combating desertification. | 2.1.3 | 1,000 ha with ecological restoration and recovery. |
| Target 18. By 2020, the traditional knowledge, innovations and practices of indigenous and local communities relevant for the conservation and sustainable use of biodiversity, and their customary use of biological resources, are respected, subject to national legislation and relevant international obligations, and fully integrated and reflected in the implementation of the Convention with the full and effective participation of indigenous and local communities, at all relevant levels. | 2.2.1 2.2.2 3.1.1 3.1.2 3.1.1 3.1.2 | 210,193 ha under voluntary CCS by the indigenous, black communities, and rural peoples. |

## 1.4 LESSONS LEARNED

Lessons learned from previous work by FAO.

FAO has a long history of working in the Colombian Pacific region, as more than 10 years ago it began to implement projects focused on livelihood recovery in communities impacted by the armed conflict and also climate events. The lessons learned include:

- Incorporating the communities and local and national officials into the design process of the project proposal promotes and develops the activities designed to eliminate gaps and strengthen weaknesses identified by them within their territories.

- Alignment of the project objectives with national objectives ensures the committed participation of national institutions in considering the project as an essential element for fulfilling their commitments.

- Design and application of a proper methodology for evaluating livelihoods is indispensable for channeling the risk management actions. This methodology allows the identification of resources that communities have and that can be used in the project actions; their main livelihood sources; and the risks to which they are exposed, not only climate-related risks but also other natural risks. It also identifies institutional and political weaknesses and strengths.

- Establishing agreements with partners and allies in the territory about the project actions is critical for their knowledge, and for linking the different stakeholders. Recognition of traditional knowledge as a fundamental element empowers communities. Likewise, conducting an analysis of the populations (women, youth) helps to design more relevant actions as per their roles within communities and their specific needs.

- The analysis of safety at the beginning of the project’s interventions is important for all areas, as it provides relevant information to avoid problems during the implementation and helps to establish the mitigation measures.

- Permanent articulation between the institutions helps to create valid methodologies for these types of interventions, which are replicable in other areas of the country.

- It is important to involve other agricultural sector institutions that work in matters related to risk management and adaptation to climate change in the country, to articulate actions that have been already proven. This will lead to the creation of networks of learning and shorter adaptation times.

- Efforts should be made to ensure that actions developed with communities within the project framework are institutionalized, avoiding isolated interventions, such that the actions may be articulated to other stakeholders’ efforts in the territory and have continuity; this leads to greater appropriation by the communities and institutions.

- Strengthening professionals’ capacities in the project areas is important for supporting the communities.

- In a country like Colombia, where communities are affected by extreme climate events as well as the armed conflict, it is important to consider both in the analysis to develop actions to reduce risk and take the necessary management measures incorporating both humans and nature.

Lessons learned from other projects executed by UNIDO

UNIDO has led projects focused on promoting sustainable industrial development in the cosmetics sector through its program Quality for the Cosmetics sector Safe+ (developed with the support of the Swiss government, the Productive Transformation Program of the Ministry of Commerce, Industry and Tourism) and the Export Consortiums project in Valle del Cauca in the agro-industry and cosmetic sectors (in alliance with the Korea International Cooperation Agency [KOICA] and the Ministry of Commerce, Industry, and Tourism). Such projects have enabled closing technical gaps to increase the commercial capacity of national cosmetic products generated from biodiversity. The main lessons learned include:

- The project’s implementation shall have a systemic approach with positive impacts at multiple levels; for example in: i) the value chain companies, ii) national institutions relevant to the National Quality System, and iii) quality infrastructure, thereby revitalizing the National Quality System to enhance the competitiveness of the country’s cosmetic sector and contributing to continuing quality improvement actions for the products once the project ends.

- Creating a culture of quality ensures access to new markets for national cosmetic products developed using Colombian biodiversity.

- The theory of change approach implemented by UNIDO ensures that proposed interventions become impacts at the economic, social, and environmental levels, thereby maximizing the outcomes and outputs scope and ensuring sustainability of capacities and competencies created within companies and institutions.

- Empowerment of partners and alliances with local, national, and international entities maximizes outcomes and the efficient use of resources through the creation of value-generating synergies.

- Integrated work with environmental authorities ensures progress in regulating and authorizing the sustainable use of non-timber forest products and their registration process; for example, in cooperation with the environmental authorities registration in China was achieved for the first time for a Colombian cosmetic ingredient derived from biodiversity.

- Articulation of projects beginning at their inception with government institutions, supporting entities, and universities ensures that a group of professionals and business people remains in the region with the technical capacity to continue strengthening actions and reproducing them in new sectors and companies.

- Extraction and generation of added value for cosmetic-use natural ingredients presents significant challenges for the country relating to compliance with national and international requirements and standards. The program, under different supporting lines, has faced this challenge and facilitated the creation of capacities to close quality gaps at different levels.

- In the technical support processes, it is important to count on the participation of the companies’ managers and/or owners, as this generates greater progress and dynamics in developing their work plan.

- The technical support programs may include individual and specialized advisory tools for each beneficiary. In this way capacities have been generated that go beyond the project’s life cycle and are reproducible.

- The continuous technical support, planned and monitored, generates higher value in a small company than financial support to achieve the same goal. With this strategy important results are achieved in the short term in the culture of the organizations, which allows for greater growth.

## 1.5 STRATEGIC ALIGNMENT

1.5.1 Alignment with national development goals and policies

At the national level, the project is in line with the National Development Plan (NDP; 2014.2018) “Everyone for a new country”, with the following strategies:

- Developing a strategy for green growth:

- Objective 1: Preserve and ensure the sustainable use of natural marine and terrestrial capital in the country based on the development of an integrated management component in PAs, buffer zones, and CCSs.

- Objective 2: Protect and ensure the sustainable use of natural capital within a process to consolidate a framework of climate change policy, seeking its integration into environmental, territorial and sectoral planning, and based on the development of the institutional strengthening component to support conservation and sustainable use in the Colombian Pacific region.

- Objective 4: Protection and conservation of territories and ecosystems, climate change mitigation and adaptation, environmental planning, mechanisms for Reducing Emissions from Deforestation and Forest Degradation (REDD+) in ethnic territories, and improve quality and environmental governance based on the development of the institutional strengthening component to support conservation and sustainable use in the Colombian Pacific region.

- Cross-cutting strategy for transformation of rural areas:

Objective 3: Speed up the escape from a cycle of poverty and the extension of middle class through a commitment to the inclusion of rural settlers in production systems, and the development of production and commercial capacities of rural communities based on the strengthening of priority value chains.

Additionally, the project is articulated with the NDP through the following elements of the Pacific region program: socioeconomic development with equity, integration and environmental sustainability, and actions in zones affected by the conflict under schemes of local sustainable development models.

At the local level, the project is articulated with the Development Plans of the five departments and the Actions Plans of the CARs with which it has direct influence:

Department of Chocó. Departmental Development Plan of Chocó (2016-2019) Opportunities for all the sub-regions, through the central theme N.1- Sustainable economic growth with employment, competitiveness, scientific and technological development, and innovation, based on the territory’s biodiversity, and the central theme N.4- Territorial planning and development, environmentally sustainable and according to the economically differentiated vocation of each sub-region.

Department of Cauca. Departmental Development Plan Cauca territory of peace (2016-2019), through the components of environmental conservation and development, economic growth and competitiveness, recovery of the social fabric, and peace, post-conflict, and innovation building.

Department of Nariño. Participatory Plan for Departmental Development Nariño heart of the world (2016-2019), through the following programs: production, transformation and trade in the agriculture and livestock, forest, aquaculture and fishing sectors; territorial governance; environment and tourism in the heart of the world.

Department of Valle del Cauca. Development Plan of Valle del Cauca (2016-2019) El Valle is inside you, through the following programs: food and nutritional security; economic inclusion for equity; institutional synergy in the territory; strategic ecosystems and sustainable biodiversity; integral management of hydrological resources; countryside sustainable and supported transformation; local and sub-regional economic development; Valle del Cauca tourism, biodiversity, multicultural and innovation; productive initiatives; Valle INN- Inclusive and Innovative; programs associated with a regionalization strategy for the municipalities of Valle that are part of the Colombian Pacific region, which is articulated with actions in the other departments with municipalities in this area.

Department of Risaralda. Development Plan (2016-2019) Risaralda green and entrepreneur, through the programs of departmental innovation ecosystems; Innova entrepreneurial; territorial development for peace, post-agreement and competitiveness; Risaralda, green and competitive territory; and territorial planning and regional development.

CARDER. Institutional Action Plan (2016-2019) Risaralda, biodiverse, sustainable, and at peace, through the following programs: territory planning with sustainability; climate change adaptation and mitigation criteria; Risaralda, green, biodiverse, and at peace; sectoral and urban low-carbon environmental management; and Program 6. Good governance for environmental management.

CRC. Action plan (2016-2019) Cauca, environmental territory for peace, through the following programs: regional environmental planning; biodiversity and ecosystem services management; risk and climate change management; environmental management with integrated vision and a differential approach in territories with ethnic and rural groups; and urban, regional and sectoral environmental management.

CODECHOCÓ. Institutional Action Plan (2016-2019) Environmental management with human approach, through the following programs: environmental planning of ecosystems and territories for building peace; institutional and community participatory development for environmental management in a post-conflict and biodiversity sustainable use scenario for the development of the Chocó in a post-conflict scenario.

CVC. Action Plan (2016-2019) Peace facts for nature, through the following programs: integrated management of water resources; territorial development as per its potentialities and limitations; land cover and sustainable use; and the integrated management of biodiversity and ecosystem services.

CORPONARIÑO. Institutional Action Plan (2016-2019): We conserve nature, through the following programs: articulated and integrated environmental planning; integrated management of biodiversity and ecosystem services; water resources management; and promotion of sustainable production and consumption in the production sectors.

1.5.2 Consistency with national communications and reports to the United Nations Convention to Combat Desertification (UNCCD), Convention on Biological Diversity (CBD).

In its 5th report to the CBD, Colombia defined its National Biodiversity Policy in 1994, the current National Policy for the Management of Biodiversity and Ecosystem Services (PNGIBSE) 2012 – 2020, and framed and conceptually guided all environmental management tools (standards, plans, programs, and projects) for biodiversity at the national level. The policy has six strategic lines of action: i) biodiversity conservation and environmental stewardship; ii) biodiversity, governance, and creation of public value; iii) biodiversity, economic development, competitiveness and quality of life; iv) biodiversity, knowledge, technology, and information management; v) biodiversity, risk management, and supply of ecosystem services; and vi) biodiversity, shared responsibility, and global commitments. The project’s objective, outcomes, and outputs are fully aligned with the PNGIBSE strategic lines of action and with the National Biodiversity Strategy and Action Plan. Component 1 of the project contributes to territorial planning strategies, initiatives and actions, and the definition of conceptual and legal frameworks for territorial planning. Component 2 contributes to generating inputs to identify areas for conservation, increase the PAs’ coverage, strengthen the PAs’ conservation through a strategy of conservation mosaics, analyze PAs’ effectiveness, and ecological restoration; Component 3 contributes to developing sustainable production alternatives.

In 2014 Colombia submitted the Performance Review and Assessment of Implementation System (PRAIS) to UNCCD during the 5th reporting cycle, which described the development of a proposal aligned with the National Action Plan’s 10-year strategy. The PRAIS also informed about actions for dissemination, raising awareness of the causes and impacts of desertification, drought, and land degradation, and the application of projects and programs that promote national capacities. These actions are in line with Component 1, Outputs 1.2.1 and 1.2.2, and Component 2, Output 2.1.3 of the project.

1.5.3 Consistency with GEF focal areas

The project is consistent with the following strategic objectives of the Biodiversity (BD), Land Degradation (LD), and SFM focal areas.

BD-4 – Mainstream Biodiversity Conservation and Sustainable Use into Production Landscapes/Seascapes and Sectors; Program 9 – Managing the Human-Biodiversity Interface. Outputs 1.1.1 and 1.1.2 will promote the incorporation of the PAs and CCSs, which provide essential ecosystem services, into the territorial planning instruments. Through Component 3, outputs, strategies, and tools for production and/or use of non-timber forest products will be promoted and implemented in 10,000 ha, as well as the integration of five biodiversity-derived products through seven value addition units. This will all be in line with the green business strategy in the Colombian Pacific region.

BD-1 – Improve Sustainability of Protected Area Systems; Program 1 – Improving Financial Sustainability and Effective Management of the National Ecological Infrastructure. SIRAP Pacific will be strengthened through the design and implementation of a financial sustainability strategy under Output 2.1.3; spaces for participation and decision making will be strengthened in the SIRAP Pacific through Output 1.2.1; and management of the PAs and CCS will be improved in 1,648.791 ha through Outputs 2.1.1, 2.2.1, 2.2.2, and 2.2.3.

LD-3 – Reduce pressures on natural resources by managing competing land uses in broader landscapes; Program 4 – Scaling-up sustainable land management through the Landscape Approach. Through Output 1.1.2, 56 pilot projects to harmonize territorial planning instruments will be carried out, from basic levels such as life plans and ethno-development plans, to municipal and departmental levels to reduce conflicts in land use. Through Output 1.2.2, community-based monitoring networks will be established to safeguard compliance with land uses. In addition, the SLM approach will be incorporated, impacting 10,000 ha through Outputs 2.1.3 and 3.1.2.

SFM-1 – Maintained Forest Resources: Reduce the pressures on high conservation value forests by addressing the drivers of deforestation; Program 1 – Integrated land use planning.

SFM-2 – Enhanced Forest Management: Maintain flows of forest ecosystem services and improve resilience to climate change through SFM; Program 5 – Capacity development for SFM within local communities.

1.5.4 Consistency with FAO and UNIDO strategic framework and objectives

Alignment with FAO strategic framework and objectives.

The project will contribute to the following strategic objectives and corporate outputs:

Strategic Objective 2. Make agriculture, forestry and fisheries more productive and sustainable.

Output 20101. Practices piloted, tested or scaled up by producers, to sustainably increase productivity, address climate change and environmental degradation, through the implementation of forest productive systems generating environmental and socioeconomic benefits.

Output 20102 Capacities of institutions are strengthened to promote the adoption of more integrated and cross-sectoral practices that sustainably increase production, address climate change and environmental degradation, through the implementation of the integrated management component of PAs, buffer zones, and CCSs.

Output 20202 Government and stakeholders’ capacities improved to facilitate cross-sectorial policy dialogue for more integrated strategies in sustainable agriculture, forestry and fisheries, address climate change and environmental degradation, through the development of the institutional strengthening component to support conservation and sustainable use in the Colombian Pacific region.

Strategic Objective 3. Reduce rural poverty.

Output 30102 Strategies, policies, guidelines and programmes to improve the rural poor’s access to, and control over, a set of services, finance, knowledge, technologies, markets and natural resources, including in the context of climate change, through the strengthening of priority value chains.

The project is in line with the FAO Country Programming Framework for Colombia 2015-2019:

Priority area 2: Natural resources and governance of forests, land, and water:

Output 2.1. Programs implemented with multisectoral approach to encourage integral territorial planning processes, natural resources conservation and sustainable and efficient use, provision of ecosystem services, and prevention of agro-environmental conflicts; through the development of the institutional strengthening component to support conservation and sustainable use in the Colombian Pacific region.

Output 2.2. Strengthening of normative frameworks and national, regional and local governance capacities promoting biodiversity and natural resources conservation, sustainable and efficient use; by implementing the integrated management component of PAs, buffer zones, and CCSs.

Output 2.5. Promotion of local initiatives for responsible management of natural resources and biodiversity, and sustainable agricultural production that contribute to reduce poverty and food insecurity, as well as pressure on sensitive environmental ecosystems; through the implementation of forest productive systems generating environmental and socioeconomic benefits.

Priority area 4: Family agriculture and inclusive markets:

Output 4.2: Models of effective productive undertakings developed to strengthen and encourage rural associations, technical capacities and access to markets; through the strengthening of priority value chains.

Regarding FAO Regional Initiatives for Latin America and the Caribbean, the project contributes to:

Regional initiative 3: Sustainable agriculture and resilience to climate change; based on the development of the institutional strengthening component to support conservation and sustainable use in the Colombian Pacific region, as well as the integrated management component of PAs, buffer zones, and CCSs.

Regional initiative 2: A new development for the rural world in Latin America and the Caribbean: fight inequalities and overcome poverty in a sustainable way; based on strengthening the priority value chains and implementation of forest productive systems generating environmental and socioeconomic benefits.

Coherence with UNIDO strategic framework and objectives

The project Component 3 is in line with UNIDO mandate to help countries to achieve inclusive and sustainable industrial development, and the declaration of Lima on “eradication of poverty by an inclusive and sustainable industrial development”.

Likewise, in relation to UNIDO Programmatic Framework (2018-2021), it is in line with the following strategic priorities:

Creation of shared prosperity: promote eradication of poverty and social inclusion; create productive capacities in an inclusive way; and provide more opportunities to all women and men, as well as all social groups, also by alliances with those interested in the industrialization processes.

Environment protection: encourage environmentally sustainable industrial development; create capacities in the institutions and the industrial sectors to achieve industries more respectful with the environment by the efficiency of resources and technologies and cleaner production practices; create industries that respect the environment, including those dedicated to residues management and recycling; and facilitate transition to a circular economy.

On the other hand, the UNIDO Programmatic Framework for Colombia 2015-2019 contains action lines relating to Component 3 including: manage and execute sustainable and inclusive industrial development projects for creating employment with emphasis in regions and groups meta-affected by the conflict within the framework of an eventual post-conflict scenario, promotion of associations in the industrial sector, including the creation and promotion of groups, clusters and consortiums; technical assistance to strengthen the inclusion of micro, small and medium business (MSMEs) in the national and international value chains, and provide support to the MSMEs in the fulfillment of quality standards to gain access to new national and international markets.

# SECTION 2 – FEASIBILITY

## 2.1 ENVIRONMENTAL & SOCIAL RISK ASSESSMENT

During the PPG stage a contextual analysis of environmental and social risks was conducted (encompassing risks from the project as well as risks to the project) in accordance with FAO and UNIDO guidelines: UNIDO Environmental and Social Safeguards Policies and Procedures (ESSPP) and FAO Guidelines for Environmental and Social Risk Management. The analysis results are presented in Appendix 6 (FAO) and Appendix 14 (UNIDO).

According to FAO Guidelines for Environmental and Social Risk Management, this project has been qualified as a moderate risk. The environmental and social safeguards identified for further consideration are the following:

- Presence of indigenous and black peoples in the project implementation areas where the proposed activities will be carried out, which may impose potential risks on such communities. This risk relates to FAO Safeguard 9: Indigenous population and cultural heritage, and UNIDO Safeguard 4: Indigenous population. In Colombia, these safeguards are also applied to black “raizal” and Palenque communities.

- Project implementation in legally constituted PAs and buffer zones (FAO Safeguard 2: biodiversity, ecosystems and natural habitats/UNIDO OS2: natural habitats protection).

- Safeguard on gender equity (FAO Safeguard 8).

A preliminary plan to address these FAO stated safeguards is presented in Appendix 6. This will be developed in greater detail during the project implementation stage.

## 2.2 RISK MANAGEMENT

Risks both from and towards the project have been identified and analyzed during the project preparation stage and mitigation measures have been incorporated into the project design. Appendix 4 summarizes the identified risks as well as their impact levels, likelihood of occurrence, corresponding mitigation measures, and the responsible individuals.

The following eight risks were identified: i) political instability in the country, particularly the Colombian Pacific region, where there are often changes in departmental and municipal administrations; ii) lack of will and participation by territorial entities and local authorities for the proper development of the project activities; iii) the participating entities do not comply with the co-financing commitments; iv) lack of interest and low participation by traditional authorities and representatives of indigenous and black peoples in the project activities; v) low participation of women, senior citizens, and young people; vi) climate change events that can affect conservation areas, production landscapes, and beneficiary local communities; vii) socio-environmental conflicts related to extraction activities and territorial and land conflicts, and viii) events related to the armed conflict situation occurring in the region, such as population displacement, assassination of community leaders, and the presence of illicit crops.

The PSC, the Regional Technical Committee (RTC), and the MUCB Technical Committees (MUCBTCs) will constitute spaces to propose management of these risks and the effective implementation of mitigation measures during the entire project life cycle, which could be adjusted as necessary; likewise, they shall identify, manage, and mitigate any risks not identified during the PPG stage.

The M&E system of the project will monitor the outcome and output indicators, associated risks, and the corresponding mitigation measures. The biannual Project Progress Report (PPR) and the annual Project Implementation Report (PIR) will serve as the main tools for risk monitoring and management. These reports shall contain a chapter on monitoring of risks and mitigation measures that were identified during the PPG stage, and identify new risks with their corresponding mitigation measures, responsible individuals, and intended deadlines.

2.2.1 Risks and mitigation measures

Appendix 4 provides a summary of the identified risks and the proposed mitigation measures.

2.2.2 Analysis of fiduciary risks and mitigation measures (only for OPIM projects)

Not applicable

# SECTION 3 – IMPLEMENTATION AND MANAGEMENT ARRANGEMENTS

## 3.1 INSTITUTIONAL ARRANGEMENTS

The Ministry of Environment and Sustainable Development (MADS) will act as the Executing Entity for the project, in close consultation with other relevant ministries and local governments involved in the field activities. The MADS will have technical and executive responsibility for the project, and FAO will provide technical supervision as a GEF agency.

## 3.2 IMPLEMENTATION ARRANGEMENTS

The Food and Agriculture Organization of the United Nations (FAO) has been selected by the participating country as the GEF Implementing Agency for the proposed project, and as such, will provide project cycle management services as established in the GEF Policy.

The MADS will be responsible for the overall execution of the project and will act as national execution entity.  National co-executing agencies will be designated and will be supported by the PSC and a Project Coordination Unit. The overall responsibility for project execution implies accountability for intended and appropriate use of funds, as well as for timely delivery of inputs and outputs.

MADS will also designate, as part of its co-financing, the National Project Director (NPD), who will be responsible for the execution and coordination of the project, with the following responsibilities:

- Organize and chair PSC meetings.

- Participate in meetings of the RTC and MUCBTCs.

- Regularly supervise the implementation of the project in line with the Project Results Framework, budget, and the annual work plan.

- Requesting FAO the timely disbursementof GEF resources.

- Review and approve the semi-annual and annual progress reports.

One important vehicle for collaboration will be through Letters of Agreement (LoA) that will be developed and signed between FAO and the respective partners. This includes project co-executing entities, such as government institutions, civil society organizations, and academia - if established in the Annual Work Plans approved by the PSC. Funds received under a LoA will be used to execute Project activities in conformity with FAO’s rules and procedures.

3.2.1 FAO’s roles and responsibilities

FAO’s role in the project governance structure

The Food and Agriculture Organization of the United Nations (FAO) will be the GEF Agency responsible for supervision and provision of technical guidance during project implementation. As the GEF Agency, FAO will:

- Administrate funds from GEF in accordance with the rules and procedures of FAO;

- Oversee project implementation in accordance with the project document, work plans, budgets, agreements with co-financiers and the rules and procedures of FAO;

- Provide technical guidance to ensure that appropriate technical quality is applied to all activities concerned;

- Conduct at least one supervision mission per year; and

- Report to the GEF Secretariat and Evaluation Office, through the annual Project Implementation Review, on project progress and provide financial reports to the GEF Trustee.

If requested by the Government involved in the proposed project, the FAO may provide direct project services. The FAO and the participating governments acknowledge and agree that those services are not mandatory, and will be provided only upon written government request. The direct project services would follow FAO policies on the recovery of direct project costs related to GEF funded projects.

In accordance with the present Project Document and the Annual Work Plan and Budget (AWP/B(s)) approved by the PSC, FAO will prepare budget revisions to maintain the budget updated in the financial management system of FAO and will provide this information to the PSC to facilitate the planning and implementation of project activities. In collaboration with the PCU and the PSC, FAO will participate in the planning of contracting and procurement processes. FAO will process due payments for delivery of goods, services and products upon request of the PCU and based on the AWP/B and Procurement Plans that will be annually approved by the PSC.

FAO’s roles in internal organization

The roles and responsibilities of FAO staff are regulated by the FAO Guide to the Project Cycle, Quality for Results, 2017 Annex 4: Roles and responsibilities of the Project Task Force (PTF) Members, and its updates.

The FAO Representative in Colombia will be the Budget Holder (BH) and will be responsible for the management of GEF resources, as applicable. As a first step in the implementation of the project, the FAO Representation in Colombia will establish an interdisciplinary Project Task Force (PTF) within FAO, to guide the implementation of the project.

The PTF is a management and consultative body that integrates the necessary technical qualifications from the FAO relevant units to support the project. The PTF is composed of a Budget Holder, a Lead Technical Officer (LTO), the Funding Liaison Officer (FLO) and one or more technical officers based on FAO Headquarters (HQ Technical Officer).

In consultation with the LTO, the FAO Representative in Colombia will be responsible for timely operational, administrative and financial management of the GEF project resources, as applicable, including in particular: (1) the acquisition of goods and contracting of services for the activities of the project, according to FAO’s rules and procedures, in accordance with the approved AWP/B; (2) process the payments corresponding to delivery of goods, services and technical products in consultation with the PSC; (3) provide six-monthly financial reports including a statement of project expenditures to the PSC; and (4) at least once a year, or more frequently if required, prepare budget revisions for submission to the FAO-GEF Coordination Unit through the Field Programme Management Information System (FPMIS) of FAO.

The FAO Representative in Colombia, in accordance with the PTF, will give its non-objection to the AWP/Bs submitted by the PCU as well as the PPRs. PPRs may be commented by the PTF and should be approved by the LTO before being uploaded by the BH in FPMIS

The Lead Technical Officer (LTO) for the project will be the Policy Officer in the Regional Office for Latin America and the Caribbean – RLC. The role of the LTO is central to FAO’s comparative advantage for projects. The LTO will oversee and carry out technical backstopping to the project implementation. The LTO will support the BH in the implementation and monitoring of the AWP/Bs, including work plan and budget revisions. The LTO is responsible and accountable for providing or obtaining technical clearance of technical inputs and services procured by the Organization.

In addition, the LTO will provide technical backstopping to the PT to ensure the delivery of quality technical outputs. The LTO will coordinate the provision of appropriate technical support from PTF to respond to requests from the PSC. The LTO will be responsible for:

- Review and give no-objection to TORs for consultancies and contracts to be performed under the project, and to CVs and technical proposals short-listed by the PCU for key project positions, goods, minor works, and services to be financed by GEF resources;

- Supported by the FAO Representation in Colombia, review and clear final technical products delivered by consultants and contract holders financed by GEF resources before the final payment can be processed;

- Assist with review and provision of technical comments to draft technical products/reports during project execution;

- Review and approve project progress reports submitted by the GPC, in cooperation with the BH;

- Support the FAO Representative in examining, reviewing and giving no-objection to AWP/B submitted by the GPC, for their approval by the Project Steering Committee;

- Ensure the technical quality of the six-monthly PPRs. The PPRs will be prepared by the GPC, with inputs from the PT. The BH will submit the PPR to the FAO/GEF Coordination Unit for comments, and the LTO for technical clearance. The PPRs will be submitted to the PSC for approval twice a year. The BH will upload the approved PPR to FPMIS.

- Supervise the preparation and ensure the technical quality of the annual PIR. The PIR will be drafted by the GPC, with inputs from the PT. The PIR will be submitted to the BH and the FAO-GEF Coordination Unit for approval and finalization. The FAO/GEF Coordination Unit will submit the PIRs to the GEF Secretariat and the GEF Evaluation Office, as part of the Annual Monitoring Review report of the FAO-GEF portfolio. The LTO must ensure that the GPC and the PT have provided information on the co-financing provided during the year for inclusion in the PIR;

- Conduct annual (or as needed) supervision missions

- Review the TORs for the mid-term review, participate in the mid-term workshop with all key project stakeholders, development of an eventual agreed adjustment plan in project execution approach, and supervise its implementation; and

- Provide comments to the TORs for the terminal evaluation; provide information and share all relevant background documentation with the evaluation team. Participate in the final workshop with all key project stakeholders, as relevant. Contribute to the follow-up to recommendations on how to insure sustainability of project outputs and results after the end of the Project.

The HQ Technical Officer is a member of the PTF, as a mandatory requirement of the FAO Guide to the Project Cycle. The HQ Officer has most relevant technical expertise - within FAO technical departments - related to the thematic of the project. The HQ Technical Officer will provide effective functional advice to the LTO to ensure adherence to FAO corporate technical standards during project implementation, in particular:

- Supports the LTO in monitoring and reporting on implementation of environmental and social commitment plans for moderate risk projects.

- Provides technical backstopping for the project work plan.

- Clears technical reports, contributes to and oversees the quality of Project report (PPRs, PIR).

- May be requested to support the LTO and PTF for implementation and monitoring.

- Will contribute to the overall ToR for the terminal evaluation; review the composition of the evaluation team and support the evaluation function.

The FAO-GEF Coordination Unit will act as Funding Liaison Officer (FLO). The FAO/GEF Coordination Unit will review and prove the PPRs, PIRs, and financial reports, as well as the approved Project Budget and AWP/Bs. This FAO/GEF Coordination Unit will review and provide a rating in the annual PIR(s) and will undertake supervision missions as necessary. The PIRs will be included in the FAO GEF Annual Monitoring Review submitted to GEF by the FAO GEF Coordination Unit. The FAO GEF Coordination Unit will organize and facilitate the mid-term review, the evaluation, and participate (FLO) in the development of corrective actions in the project implementation strategy if needed to mitigate eventual risks affecting the timely and effective implementation of the project. The FAO GEF Coordination Unit will in collaboration with the FAO Finance Division request transfer of project funds from the GEF Trustee based on six-monthly projections of funds needed.

The FAO Financial Division will provide annual Financial Reports to the GEF Trustee and, in collaboration with the FAO-GEF Coordination Unit, request project funds on a six-monthly basis to the GEF Trustee.

c) Rural Development Agency (ADR/MADR) – FAO Alliance. A strategy for building capacities of professionals, technicians, and extension officers in 10 departments (including Chocó, Risaralsa,Cauca, Valle del Cauca, and Nariño, which are all covered under the project proposed herein) who are responsible for designing, implementing, or developing Integral Projects for Agricultural and Rural Development (PIDAR).

3.2.2 Decision-making mechanisms of the project

Project governance, decision-making, and execution will be carried through 3 levels:

- Political level: PSC and RTC

- Coordination level: MUCBTC, one per MUCB (5).

- Operational level: Implementation Unit

Coordination among Government agencies and the Implementing agencies will be achieved through a Project Steering Committee (PSC) which will be co-chaired by MADS. The PSC will provide the necessary guidance and coordination to the project implementation, and will invite members and experts for specific meetings, as needed. The PSC decisions shall be made in line with the approved project document, GEF, FAO and UNIDO guidelines. Additionally, the PSC will be composed of PNN, MADR, SIRAP Pacific, one representative of community councils, one representative of indigenous resguardos, and one CAR in representation of the five CARs, departmental governments of Nariño, Cauca, Valle del Cauca and Chocó, FAO and UNIDO. The PSC Technical Secretary will be the PC. Its main function is to guide the implementation of the project, verify and approve the annual work plans, approve the financial and technical reports, and provide strategic guidance for the project.

The project Regional Technical Committee (RTC) will be organized within the SIRAP Pacific Technical Committee framework and will be constituted by delegates of MADS, PNN, CODECHOCÓ, CARDER, CVC, CRC, CORPONARIÑO, IIAP, INVEMAR, FAO and UNIDO, and the invitation can be extended to departmental governments and representatives of indigenous, black communities, and peasant peoples with influence in the project.

The MUCB Technical Committees (MUCBTCs) will be integrated by MADS, PNN MADR, community councils, and indigenous resguardos participating in the project, INVEMAR, IIAP, FAO, UNIDO, CAR, municipalities, and community and civil society organizations with influence in each MUCB. The composition of each MUCBTC will be defined according to the presence and influence of each entity.

Functions and responsibilities of each decision-making space of the project are detailed in Section 3.2.4. Likewise, an operation protocol of each participation space will be developed in the first 3 months of the project execution. Likewise, terms of reference (TOR) governing the participation of stakeholders on each decision-making level will be developed in the first 3 months of the project execution.

FAO will hire some of the following human resources:

- Professional in participation and ethnic and gender approach (PPEGA)

- Professional in instruments for ecosystem services planning and assessment (PIESPA)

- Professional in PAs and CCSs (PPAsCCSs)

- Professional in Communications (PCM)

- Professional in Sustainable Forest Management (PSFM)

- Professional in Sustainable Production and Soil Management Systems (PSPSMS)

- Other technical experts

- Figure 3. Implementation arrangements

The project PSC will meet once a year. The purpose of the PSC will be to review and approve the planning for the project implementation; it will have the following as its roles and responsibilities: i) review and approve the annual operational and budget plans of the project developed by the PC with inputs generated in each RTC and MUCBTC; ii) approve the annual progress and results reports; iii) approve the final project report; iv) approve the adjustments to the total amounts of budget elements; v) analyze and approve changes in project goals and outcomes; and vi) propose and agree potential modifications to the agreement signed by the implementing agencies and the national government.

The RTC will meet at least twice a year within the SIRAP Pacific Technical Committee framework. The purpose of the RTC will be to provide technical guidelines for the project implementation; it will have the following roles and responsibilities: i) monitor the progress of the activities by analyzing goals achieved and difficulties; ii) review the consolidation of the project operational work plan; iii) monitor the project indicators; iv) monitor the obligations of the project’s physical execution and its execution percentage; v) invite persons because of competency, according to the meeting theme; vi) promote the participation of regional stakeholders in the project activities, and vii) review the annual progress reports.

The MUCBTC will meet before the PSC at least twice a year and it will be convened by the PC, or outside of this schedule when some of the members request it. The MUCBTC will have the following roles: i) monitor the progress of the activities in the project’s four components by analyzing goals achieved and difficulties; ii) review and propose to PSC the budget transfers of the different budget elements; iii) monitor the project indicators; iv) monitor the obligations of the project’s physical execution and its execution percentage; v) review the new TORs for jobs other than the existing ones; vi) invite persons because of competency, according to the meeting theme.

For the execution of the Project activities, the PIU will be established and constituted by a Project Technical Team (PTT), which will be financed by GEF. The main PIU function, following the guidelines and decisions taken by PSC, in close coordination with RTC and MUCBTC and under supervision of the NPD, is to ensure rigorous and effective coordination and execution of the project annual work plans and the intervention plans of each MUCB.

The PIU will be under the general supervision of the NPD and led by the Project Coordinator (PC), who will be in charge of the daily project management and technical supervision, in accordance with FAO standards, procedures, present project document and the work plans agreed upon for each MUCB. The PC will lead the formulation of reports to GEF and technically validate and supervise the reports of consultants and organizations.

The TORs of the PC and the PIU are contained in Appendix 7, which will be updated and adjusted in the first 3 months of the project implementation.

The PIU will be structured as shown below.

- Figure 4. Structure of the PIU.

The Project Coordinator (PC) will be responsible for supervising and guiding PIU. He/she will also be responsible for coordinating activities with all instances linked to the different components of the project, as well as with the partner institutions of the project. He/she will also be in charge of daily project management and technical supervision including: (i) coordinating and closely supervising the execution of project activities, (ii) day-to-day management, (iii) coordination with other related initiatives, (iv) ensure a high level of collaboration between participating institutions and organizations at the national, provincial and local levels; (v) monitor the progress of the project and ensure the timely delivery of inputs and outputs; (vi) implement and manage the project monitoring plan and its communication program.

The Administrative and Financial Assistant will be responsible for the day-to-day financial management of the project, including lifting the contracts and acquiring other necessary supplies according to the approved Project AWP/Bs. He/she will work in close consultation with the PC and project implementing partners, particularly the FAO Representation in the Colombia and the MADS.  The PIU will be based in the city of Cali.

## 3.3 PLANNING AND FINANCIAL MANAGEMENT

#### 3.3.1 Financial plan (by components, outcomes, and co-financiers).

- Table 18. Financial plan (by components, outcomes, and co-financiers).

| Co-financier | Co-financing amount | Component |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | (US$) | 1 | 2 | 3 | 4 | PMC |
| MADS | 1,196,757 |  |  | 1,067,048 | 72,721 | 56,988 |
| PNN | 1,548,715 |  | 1,474,967 |  |  | 73,748 |
| INVEMAR | 147,943 | - | 140,898 | - | - | 7,045 |
| IIAP | 484,838 | 310,797 | 71,807 | 79,146 | - | 23,088 |
| Departmental Government of Nariño | 4,719,870 | 24,889 | 153,541 | 4,311,155 | 5,529 | 224,756 |
| Departmental Government of Chocó | 168,845 | 49,508 | 38,856 | 43,010 | 29,431 | 8,040 |
| CARDER | 410,088 | 375,439 | 8,254 | 4,010 | 2,857 | 19,528 |
| CVC | 5,871,918 | 1,007,203 | 4,031,515 | 553,585 | - | 279,615 |
| CORPONARIÑO | 6,640,426 | 4,317,684 | 1,734,422 | 272,109 |  | 316,211 |
| CODECHOCÓ | 3,547,790 |  | 1,735,375 | 1,643,473 |  | 168,942 |
| Major communal council of Alto San Juan (ASOCASAN) | 170,010 |  | 161,914 |  |  | 8,096 |
| Communal council of Cuenca del Río Cacarica Choco | 118,748 |  | 113,093 |  |  | 5,655 |
| La Sierpe Community Resguardo Calle Santa Rosa Resguardo | 40,500 | 4,762 | 14,286 | 17,142 | 2,381 | 1,929 |
| Communal council of Bajo Mira and Frontera | 157,611 | 50,035 | 50,035 | 50,036 |  | 7,505 |
| Corporación Biocomercio Sostenible (CBS) Colombia | 395,926 | - | - | 377,072 |  | 18,854 |
| BIOINNOVA | 731,768 | - | - | 696,922 | - | 34,846 |
| Fundación San Cipriano | 108,488 | - | 103,322 | - | - | 5,166 |
| Patrimono Natural – Fund for Biodiversity and Protected Areas | 909,643 | - | 794,953 | 71,374 |  | 43,316 |
| UNIDO | 3,223,765 |  |  | 3,070,252 |  | 153,513 |
| FAO | 1,710,000 | 514,286 | 257,143 | 714,285 | 142,857 | 81,429 |
| Subtotal | 32,303,649 | 6,654,603 | 10,884,381 | 12,970,619 | 255,776 | 1,538,270 |
| GEF | 7,562,558 | 1,333,199 | 2,680,399 | 2,874,296 | 314,542 | 360,122 |
| Total | 39,866,206 | 7,987,802 | 13,564,780 | 15,844,915 | 570,318 | 1,898,392 |

- Table 19. Confirmed co-financing sources.

| Sources of co-financing | Co-financier (source) | Type of co-financing | Amount of co-financing ($) |
| --- | --- | --- | --- |
| National Government | Ministry of Environment and Sustainable Development (MADS) | In-kind and cash | 1,196,757 |
| National Government | PNN | In-kind and cash | 1,548,715* |
| Research Institute | IIAP | In-kind | 484,838 |
| Research Institute | INVEMAR | In-kind | 41,143 |
|  |  | Cash | 106,800 |
| Local Government | Departmental Government of Nariño - Environment and Sustainable Development Secretariat | In-kind | 26,227 |
|  |  | Cash | 504,642 |
| Local Government | Departmental Government of Nariño - Agriculture and Rural Development Secretariat | In-kind | 4,189,000 |
| Local Government | Departmental Government of Chocó | In-kind | 72,012 |
|  |  | Cash | 96,833 |
| Local Government | CARDER | In-kind | 274,264 |
|  |  | Cash | 135,824 |
| Local Government | CVC | Cash | 5,871,918 |
| Local Government | CORPONARIÑO | In-kind | 93,429 |
|  |  | Cash | 6,546,997 |
| Local Government | CODECHOCÓ | Cash | 3,547,790 |
| Community organizations- Black communities | Major communal council of del Alto San Juan - ASOCASAN | In-kind | 170,010 |
| Community organizations- Black communities | Communal council of Cuenca del Río Cacarica - Choco | In-kind | 118,748 |
| Community organizations- Black communities | Reservation comunidad La Sierpe Reservation Calle Santa Rosa | In-kind | 40,500 |
| Community organizations- Black communities | Communal council of Bajo Mira and Frontera | In-kind | 157,611 |
| Non-governmental organization | Corporación Biocomercio Sostenible - Colombia | In-kind | 395,926 |
| Non-governmental organization | BIOINNOVA | In-kind | 731,768 |
| Non-governmental organization | Fundación San Cipriano | In-kind | 108,488 |
| Non-governmental organization | Fundacion Patrimonio Natural – Fund for Biodiversity and Protected Areas | Cash | 909,643 |
| GEF Agency | UNIDO | In-kind | 800,000 |
|  |  | Cash | 2,423,765 |
| GEF Agency | FAO | In-kind | 510,000 |
|  |  | Cash | 1,200,000 |
| Total |  |  | 32,303,649 |

*Official Exchange Rate: COP 2,779 = USD 1.00

3.3.2 GEF contribution

GEF resources will be directed to finance the necessary inputs to generate the project outcomes and outputs; these include strengthening the institutional framework and increasing capacities and participation of the stakeholders in the Colombian Pacific region (institutions at the regional, departmental, municipal, and local levels) to safeguard cultural, biological, and ecosystems services diversity, as well as develop and implement a financial sustainability strategy for the SIRAP Pacific. GEF resources will also be used to improve effectiveness of PAs and CCS management and governance, support the declaration of new PAs, and restore forests and land under a socio-ecosystem connectivity strategy, contributing to biological and cultural diversity conservation in the Colombian Pacific region.

GEF resources will also be invested in promoting sustainable production systems (forest and biodiversity-derived products and services) within the value generation and value chains strengthening framework, including technical assistance, training, and support in developing the production units and the commercial process for biodiversity products and nature tourism. The total GEF financing for the project amounts to USD 7,562,558.

3.3.3 Government contribution

MADS, PNN, departmental Governments of Choco, Nariño,and CARs (CODECHOCÓ, CVC, CARDER, CORPONARIÑO) and research centers, IIAP and INVEMAR, will contribute in cash and in-kind. These contributions correspond to actions associated with the activities that each institution implements in the framework of their corresponding plans, programs, and projects.

- Related to Component 1, contributions include actions for planning, environmental and territorial planning, administration and management of continental and coast-marine natural resources, GIS, information models and systems for decision making; institutional strengthening and training, and environmental education.

- Related to Component 2, contributions include actions for formulating and implementing the PAs’ management plans, management of regional PA systems and land protection, creation of new PAs, biodiversity conservation and sustainable use, investments to improve PAs’ management, forest planning and restoration, and joint work with local communities aimed at conserving biodiversity in the PAs and buffer zones.

- Related to Component 3, contributions correspond to promoting actions for SFM, improvement of agriculture and livestock production and productivity, assurance of trade for biodiversity-derived products, and green business promotion and strengthening.

The estimated, cash and in kind, investment is around USD 24,737,190.

3.3.4 FAO Contribution

FAO will provide technical assistance, support, training, and supervision of the project activities execution financed by GEF; it also will support and promote dialogue at local, regional, and national levels for exchanging experiences, transferring knowledge on sustainable production practices, and articulation with regional and national initiatives implemented by FAO, in which the project outcomes and outputs are complemented. FAO co-financing, in cash and in-kind will be USD 1,700,000.

3.3.5 UNIDO Contribution

UNIDO will provide support, technical assistance, training, and supervision for promoting sustainable production alternatives and executing the project Outcome 3.2 activities. Likewise, it will work in coordination with FAO and the project partners to conduct an integral intervention in the MUCBs, it will also promote dialogue among stakeholders and experiences transfer and exchange, and facilitate work methodologies and paths related to agroindustry and value chain matters. UNIDO co-financing, in cash and in kind, will be USD 3,223,765 distributed as follows:

| S. No. | Contribution | Amount (USD) |
| --- | --- | --- |
| 1. | Contributions from other UNIDO technical departments: PTC/TII and PTC/AGR will provide advice on value chain development for biodiversity products and tourism as well as the development quality and other standards compliance capacity building. The international staff placed at UNIDO office in Bogotá will also provide expertise and support monitoring of the project. | 400,000 |
| 2. | Contributions from ongoing non-GEF funded UNIDO projects regarding the network of regional sustainable | 2,023,765 |
| 3. | Contributions from Tools and methodologies developed by UNIDO that are relevant to the project, i.e. UNIDO’s value chain diagnostics, its tool on pro-poor agricultural value chain development, its rural cluster building methodology and its methodology on standards setting and compliance. | 800,000 |
| 4. | Contributions |  |
|  | Total | 3,223,765 |

3.3.6 Other co-financers contribution

Indigenous, black communities and peasant peoples, as well as COs, will provide support to the activities leading to biodiversity conservation and use in the MUCBs through investments to support local utilization initiatives for forest non-timber yielding products and community-based tourism, facilitation of community spaces for participation and training events, local transportation, and community work. The investment will be USD 2,642,694.

3.3.7 Financial management and reporting on GEF resources

Financial management and reporting in relation to the GEF resources will be carried out in accordance with FAO’s rules and procedures, and in accordance with the agreement between FAO, and the GEF Trustee.  On the basis of the activities foreseen in the budget and the project, FAO will undertake all operations for disbursements, procurement and contracting for the total amount of GEF resources upon request of the NPD and the PC.

Financial records. FAO shall maintain a separate account in United States dollars for the Project’s GEF resources showing all income and expenditures. Expenditures incurred in a currency other than United States dollars shall be converted into United States dollars at the United Nations operational rate of exchange on the date of the transaction. FAO shall administer the Project in accordance with its regulations, rules and directives.

Financial reports. FAO shall prepare six-monthly project expenditure accounts and final accounts for the project, showing amount budgeted for the year, amount expended since the beginning of the year, and separately, the un-liquidated obligations as follows:

- Details of project expenditures on outcome-by-outcome basis, reported in budget lines as stated in the project budget of this Project Document.

- Final accounts on completion of the Project on a component-by-component and outcome-by-outcome basis, reported in line with the Project Budget included in this Project Document.

- A final statement of account in line with FAO Oracle Project budget codes, reflecting actual final expenditures under the Project, when all obligations have been liquidated

Financial statements. Within 30 working days of the end of each semester, together FAO shall submit six-monthly statements of expenditure of GEF resources, to present to the RTC and the PSC and included in the PPR. The purpose of the financial statement is to list the expenditures incurred on the project on a six monthly basis compared to the budget, so as to monitor project progress and to reconcile outstanding advances during the six-month period. The financial statement shall contain information that will serve as the basis for a periodic revision of the budget.

The BH will submit the above financial reports for review and monitoring by the LTO and the FAO GEF Coordination Unit. Financial reports for submission to the donor (GEF) will be prepared in accordance with the provisions in the GEF Financial Procedures Agreement and submitted by the FAO Finance Division

Responsibility for cost overruns: The BH shall utilize the GEF project funds in strict compliance with the Project Budget (Appendix 3) and the approved AWP/Bs. The BH can make variations provided that the total allocated for each budgeted project component is not exceeded and the reallocation of funds does not impact the achievement of any project output as per the Project Results Framework (Appendix 1). At least once a year, the BH will submit a budget revision for approval of the LTO and the FAO/GEF Coordination Unit through FPMIS. Cost overruns shall be the sole responsibility of the BH.

Audit: The Project shall be subject to the internal and external auditing procedures provided for in FAO financial regulations, rules and directives and in keeping with the Financial Procedures Agreement between the GEF Trustee and FAO.

The audit regime at FAO consists of an external audit provided by the Auditor-General (or persons exercising an equivalent function) of a member nation appointed by the Governing Bodies of the Organization and reporting directly to them, and an internal audit function headed by the FAO Inspector-General who reports directly to the Director-General. This function operates as an integral part of the Organization under policies established by senior management, and furthermore has a reporting line to the governing bodies. Both functions are required under the Basic Texts of FAO, which establish a framework for the TORs of each. Internal audits of imprest accounts, records, bank reconciliation and asset verification take place at FAO field and liaison offices on a cyclical basis.

## 3.4 PROCUREMENT

At the request of the Government of Colombia, FAO will procure the equipment and services foreseen in the budget (Appendix 3) and the AWP/Bs, in accordance with FAO rules and procedures.

Careful procurement planning is necessary for securing goods, services and works in a timely manner, on a “Best Value for Money” basis, and in accordance with the Rules and Regulations of FAO. It requires analysis of needs and constraints, including forecast of the reasonable timeframe required to execute the procurement process. Procurement and delivery of inputs in technical cooperation projects follow FAO’s rules and regulations for the procurement of supplies, equipment and services (i.e. Manual Sections 502 and 507). Manual Section 502: “Procurement of Goods, Works and Services” establishes the principles and procedures that apply to procurement of all goods, works and services on behalf of the Organization, in all offices and in all locations, with the exception of the procurement actions described in Appendix A – Procurement Not Governed by Manual Section 502. Manual Section 507 establishes the principles and rules that govern the use of Letters of Agreement (LoA) by FAO for the timely acquisition of services from eligible entities in a transparent and impartial manner, taking into consideration economy and efficiency to achieve an optimum combination of expected whole life costs and benefits (“Best Value for Money”).

The PC, jointly with the PTT, will design an annual procurement plan for the primary services and products that will be the basis for the procurement orders during project implementation. The first procurement plan will be updated at project inception. The plan will include a description of the goods, services, and works to be acquired, their estimated budget and the funding source, a timetable for the procurement process, and the proposed procurement method.  When accurate information is not available, the procurement plan will, at the least, contain reasonable projections that will be adjusted, as the information becomes available.

Before commencing procurement, the PC will update the project´s Procurement Plan for approval by the PSC. This plan will be reviewed during the inception workshop and will be approved by FAO. The PC will update the Plan every six months and submit the plan to the NPD, and to FAO for final approval.

## 3.5 MONITORING AND REPORTING

The monitoring and evaluation (M&E) of progress in achieving the results and objectives of the project will be based on targets and indicators in the Project Results Framework (Appendix 1). Project monitoring and the evaluation activities are budgeted at 172,490 USD (see Table 20). Monitoring and evaluation activities will follow FAO, UNIDO, and GEF policies and guidelines for M&E. The M&E online system (Output 4.12) will also facilitate learning and replication of the project’s results and lessons in relation to biodiversity conservation and sustainable use in the priority MUCBs of the Colombian Pacific region.

3.5.1 Oversight and monitoring responsibilities

The monitoring and evaluation roles and responsibilities specifically described in the Monitoring and Evaluation table (see below) will be undertaken through: (i) continuous monitoring and supervision visits by the project coordination unit (PCU); (ii) technical monitoring of the indicators to measure the global benefits by the PCU and the LTO in coordination with the partners; (iii) mid-term review and terminal evaluation (independent consultants and the FAO Evaluation Office); and (iv) monitoring and supervision missions (FAO).

At the beginning of the implementation of the GEF project, the PCU will establish a system to monitor the project’s progress. Participatory mechanisms and methodologies to support the monitoring and evaluation of performance indicators and outputs will be developed, which will contribute to the design the project monitoring platform (Output 4.1.2).

During the project inception workshop (see section 3.5.3 below), the tasks of monitoring and evaluation will include: (i) presentation and explanation (if needed) of the project’s Results Framework with all project stakeholders; (ii) review of monitoring and evaluation indicators and their baselines; (iii) preparation of draft clauses that will be required for inclusion in consultant contracts, to ensure compliance with the monitoring and evaluation reporting functions (if applicable); and (iv) clarification of the division of monitoring and evaluation tasks among the different stakeholders in the project. One of the main products of the workshop will be a detailed monitoring plan, agreed among all the stakeholders and based on the M&E plan that is summarized in section 3.5.4.

The GIS/M&E Expert (see TORs in Appendix 7) will prepare a draft monitoring and evaluation matrix that will be discussed and agreed upon by all stakeholders during the inception workshop. The M&E matrix will be a management tool for the NPD, the PC, and the Project Partners to: i) six-monthly monitor the achievement of output indicators; ii) annually monitor the achievement of outcome indicators; iii) clearly define responsibilities and verification means; iv) select a method to process the indicators and data.

The M&E Plan will be prepared by the GIS/M&E Expert in the three first months of the PY1 and validated with the PSC. The M&E Plan will be based on the M&E Table 20 and the M&E Matrix and will include: i) the updated results framework, with clear indicators per year; ii) updated baseline, if needed, and selected tools for data collection (including sample definition); iii) narrative of the monitoring strategy, including roles and responsibilities for data collection and processing, reporting flows, monitoring matrix, and brief analysis of who, when and how will each indicator be measured; iv) environmental and social risk management plan. Responsibility of project activities may or may not coincide with data collection responsibility; iv) updated implementation arrangements, if needed; v) inclusion of the tracking tool indicators, data collection and monitoring strategy to be included in the mid-term review and terminal evaluation; vi) calendar of evaluation workshops, including self-evaluation techniques.

The day-to-day monitoring of the project’s implementation will be the responsibility of the PC and will be driven by the preparation and implementation of an AWP/B followed up through six-monthly PPRs. The preparation of the AWP/B and six-monthly PPRs will represent the product of a unified planning process between main project stakeholders. As tools for results-based-management (RBM), the AWP/B will identify the actions proposed for the coming project year and provide the necessary details on output and outcome targets to be achieved, and the PPRs will report on the monitoring of the implementation of actions and the achievement of output and outcome targets for each MUCB. Specific inputs to the AWP/B and the PPRs will be prepared based on participatory planning and progress review with all stakeholders and coordinated and facilitated through project planning and progress review workshops. These contributions will be consolidated by the PC in the draft AWP/B and the PPRs.

An annual project progress review and planning meeting should be held with the participation of the project partners in the MUCBs and at the regional level to finalize the AWP/B and the PPRs. Once finalized, the AWP/B and the PPRs will be submitted to the FAO LTO and to for technical clearance, and to the PSC for revision and approval. The AWP/B will be developed in a manner consistent with the Project Results Framework to ensure adequate fulfillment and monitoring of project outputs and outcomes.

Following the approval of the Project, the PY1 AWP/B will be adjusted (either reduced or expanded in time) to synchronize it with the annual reporting calendar. In subsequent years, the AWP/Bs will follow an annual preparation and reporting cycle as specified in section 3.5.3 below.

3.5.2 Indicators and information sources

To monitor project outputs and outcomes including contributions to global environmental benefits, specific indicators have been established in the Project Results Framework (see Appendix 1). The Project Results Framework indicators and means of verification will be applied to monitor both project performance and impact. Following FAO monitoring procedures and progress reporting formats, data collected will be sufficiently detailed that can track specific outputs and outcomes, and flag project risks early on. Output target indicators will be monitored on a six-monthly basis, and outcome target indicators will be monitored on an annual basis, if possible, or as part of the midterm and terminal evaluations.

The project output and outcome indicators have been designed to monitor biophysical and socio-economic impacts and progress in building and consolidating capacities for conservation and sustainable use of biodiversity, socioeconomic connectivity at the MUCB level, integrated management of natural resources and SFM both at the political-legal level as well as at the productive level, among indigenous, black and rural communities that conserve and use the natural resources for their food security, maintenance of ecosystems and cultures, and generation of economic benefits..

The main information sources to support the M&E plan include: i) monitoring systems of SIRAP Pacific, MADS, MADR, CARs, IIAP, INVEMAR, departmental governments and other project stakeholders, ii) participatory workshops to review progress with stakeholders and beneficiaries; iii) on-the-ground monitoring of the implementation of best practices for sustainable production; iv) progress reports prepared by the PC with inputs from the partners, allies and project participants; v) consultancy reports; vi) training reports; vii) midterm evaluation and terminal evaluation; viii) financial reports and budget revisions; ix) PIRs prepared by the FAO LTO and the Technical Officer in the headquarters of UNIDO with the support of the PTT; x) FAO and UNIDO supervision mission reports.

    - Reporting schedule

Specific reports that will be prepared under the monitoring and evaluation program are: (i) Project inception report; (ii) AWP/B; (iii) PPRs); (iv) PIRs; (v) Technical reports; (vi) Co-financing reports; (vii) Terminal Report; and (viii) mid-term review and terminal evaluation reports. In addition, the GEF Core Indicator Worksheet will be duly completed.

Project Inception Report.  An inception workshop will be held in the first 3 months of project implementation. Immediately after the workshop, the PC will prepare a project inception report in consultation with the FAO and UNIDO and other project partners. The report will include a narrative on the institutional roles and responsibilities and coordinating action of project partners, progress to date on project establishment and start-up activities and an update of any changed external conditions that may affect project implementation. It will also include a detailed first year AWP/B and the M&E Matrix (see below). The draft inception report will be circulated to FAO, UNIDO, the RTC, and the PSC for review and comments before its finalization, no later than three months after project start-up. The report will be cleared by the FAO BH, LTO and the FAO/GEF Coordination Unit in addition to the Technical Officer in the headquarters of UNIDO.

Annual Work Plan and Budget(s) (AWP/Bs). The PC will present a draft AWP/B to the PSC no later than the first month of each year. The AWP/B should include detailed activities to be implemented by project outcomes and outputs and divided into monthly timeframes and targets and milestone dates for output and outcome indicators to be achieved during the year. A detailed project budget for the activities to be implemented during the year should also be included together with all monitoring and supervision activities required during the year. The PC will circulate the draft AWP/B to the FAO PTF and the Technical Officer in the headquarters of UNIDO for their comments. The AWP/B will be reviewed by the PSC and the PCU will incorporate any comments. The final AWP/B will be sent to the PSC for approval and to FAO and UNIDO for final no-objection. The BH will upload the AWP/Bs in FPMIS.

Project Progress report (PPR). The PPRs are used to identify constraints, problems or bottlenecks that impede timely implementation and take appropriate remedial action. PPRs will be prepared based on the systematic monitoring of output and outcome indicators identified in the Project Results Framework (Appendix 1), AWP/B and M&E Plan. Each semester the PC will prepare a draft PPR, and will collect and consolidate any comments from the FAO PTF. The PC will submit the final PPRs to the FAO Representative and the UNIDO Representative in Colombia every six months, prior to 10 June (covering the period between January and June) and before 10 December (covering the period between July and December). The July-December report should be accompanied by the updated AWP/B for the following Project Year (PY) for review and no-objection by the FAO PTF. The Budget Holder has the responsibility to coordinate the preparation and finalization of the PPR, in consultation with the PMU, LTO and the FLO. After LTO, BH and FLO clearance, the FLO will ensure that project progress reports are uploaded in FPMIS in a timely manner.

Annual Project Implementation Review (PIR).  The PC, under the supervision of the LTO and BH and in coordination with the national project partners, will prepare a draft annual PIR report covering the period July (the previous year) through June (current year) no later than July 1st every year. The LTO will finalize the PIR and will submit it to the FAO-GEF Coordination Unit for review by July 10th. The FAO-GEF Coordination Unit, the LTO, and the BH will discuss the PIR and the ratings. The LTO is responsible for conducting the final review and providing the technical clearance to the PIR(s). The LTO will submit the final version of the PIR to the FAO-GEF Coordination Unit for final approval. The FAO-GEF Coordination Unit will then submit the PIR(s) to the GEF Secretariat and the GEF Independent Evaluation Office as part of the Annual Monitoring Review of the FAO-GEF portfolio. The PIR will be uploaded to FPMIS by the FAO-GEF Coordination Unit.

Technical reports. The technical reports will be prepared as part of the project outputs and will document and disseminate lessons learned. Drafts of all technical reports must be submitted by the PC to the PSC and the FAO and the UNIDO Representations in Colombia, which in turn will be shared with the FAO LTO and the UNIDO Technical Official for review and approval. Copies of the technical reports will be distributed to the PSC and other project stakeholders, as appropriate. These reports will be uploaded in FAO FPMIS by the BH.

Co-financing reports. The PC will be responsible for collecting the required information and reporting on in-kind and cash co-financing provided by all the project co-financiers and eventual other new partners not foreseen in the Project Document. Every year, the PC will submit the report to the FAO and the UNIDO Representations in Colombia before July 10th covering the period July (the previous year) through June (current year). This information will be used in the PIRs.

Final Report. Within two months prior to the project’s completion date, the PC will submit to the PSC and the FAO Representation in Colombia, a draft final report. The main purpose of the final report is to give guidance to authorities (ministerial or senior government level) on the policy decisions required for the follow-up of the Project, and to provide the donor with information on how the funds were utilized. Therefore, the terminal report is a concise account of the main outputs, outcomes, conclusions and recommendations of the Project, without unnecessary background, narrative or technical details. The target readership consists of persons who are not necessarily technical specialists but who need to understand the policy implications of technical findings and needs for ensuring sustainability of project results. Work is assessed, lessons learned are summarized, and recommendations are expressed in terms of their application to the integrated landscape management in the context of the development priorities at national and departmental levels, as well as in practical execution terms. This report will specifically include the findings of the terminal evaluation as described in section 3.6 below. A project evaluation meeting will be held to discuss the draft final report with the PSC before completion by the PC and approval by the FAO BH, LTO, the Technical Officer in the headquarters of UNIDO, and the FAO-GEF Coordination Unit.

3.5.4 Monitoring and Evaluation summary

Table 20 summarizes the main monitoring and evaluation reports, parties responsible for their publication and time frames.

- Table 20. Summary of the main M&E activities.

| M&E Activity | Responsible parties | Time frame/ Periodicity | Budget |
| --- | --- | --- | --- |
| Inception workshop (workshop report) | PC; FAO-UNIDO (with support from Lead Technical Officer [LTO], Budget Holder and FAO – GEF Coordination Unit) | Within two months of project start up | USD 12,594 |
| Field level impact monitoring | PC, Project partners, Local organizations | Continuous | USD 68,550 (travel, 5% of the PC time, 30 % of the MUCB Technical Coordinator) |
| Project Progress Report (PPR) | PC, with contributions of the project partners and other executing institutions | Six-monthly | USD 6,564 (3% of the PC time) |
| Project Implementation Review (PIR) | PC with support of the Project Technical Team (PTT) and under supervision of FAO Lead Technical Officer (LTO) and the Technical Officer of UNIDO Office; clearance by the FAO/GEF and UNIDO/GEF Coordination Unit(s) | Annual | FAO and UNIDO staff time financed through GEF agency fees, PC and PTT financed through the project budget |
| Co-financing reports | PC with inputs from other co-financiers | Annual | USD 2,188 (1% of the PC time) |
| Technical reports | PC and FAO (LTO, FAO Colombia) UNIDO | According to the project needs | None |
| Mid-term review (MTR) | External Consultant, FAO and UNIDO Offices in Colombia, FAO/GEF Coordination Unit and others | Midway through the project implementation period | USD 20,000 for external consultancy |
| Terminal Workshop (workshop report) | PC and PTT | Prior to the end of the project | USD 12,594 |
| Independent Terminal Evaluation (ITE) | External consultant, FAO Office of Evaluation (OED) in consultation with the project team, including the FAO-GEF and UNIDO-GEF Coordination Unit(s) and other stakeholders | Six months prior to the end of the project | USD 50,000 |
| Terminal Report | PC; FAO (FAO Office in Colombia, LTO, FAO-GEF Coordination Unit, TCR Report Unit), UNIDO | Three months prior to the end of the project | None |

## EVALUATION PROVISIONS

At the end of the first 30 months of the project, the BH will arrange a Mid-Term Review (MTR) in consultation with the PSC, the PCU, the LTO and the FAO-GEF Coordination Unit. The MTR will be conducted to review progress and effectiveness of implementation in terms of achieving project objective, outcomes and outputs. The MTR will allow mid-course corrective actions, if needed.  The MTR will provide a systematic analysis of the information provided under the M&E Plan (see above) with emphasis on the progress in the achievement of expected outcome and output targets against budget expenditures. The MTR will refer to the Project Budget (see Appendix 3) and the approved AWP/Bs. The MTR will contribute to highlight replicable good practices and main problems faced during project implementation and will suggest mitigation actions to be discussed by the PSC, the FAO LTO, the Technical Officer in the headquarters of UNIDO, and the FAO-GEF Coordination Unit.

An independent Final Evaluation (FE) will be carried out six months prior to the terminal report meeting. The FE will aim to identify the project impacts, sustainability of project outcomes and the degree of achievement of long-term results. The FE will also have the purpose of indicating future actions needed to expand on the existing Project in subsequent phases, mainstream and up-scale its products and practices, and disseminate information to management authorities and institutions with responsibilities in the conservation and sustainable use of natural resources in the Colombian Pacific including strategic planning and evaluation tools for ecosystem services, sustainable production systems that include soil conservation and biodiversity-friendly practices and ecosystem conservation, to assure continuity of the processes initiated by the Project.  Both the MTR and FE will pay special attention to outcome indicators and will be aligned with the GEF Core Indicators 1, 3, 4, and 6.

## 3.7 COMMUNICATION AND VISIBILITY

During the PPG stage a line of communication was established at numerous consultation meetings with government organizations, representatives of indigenous, black, and peasant peoples, and other key stakeholders at the national and regional levels. This approach will continue during the implementation stage.

The PC and the NPD will have a key role in maintaining fluid and permanent communication about the project with the interested parties at all levels in order to maintain stakeholders’ interest in and commitment to the project during its lifespan. This will be achieved through bilateral personal communication. The different decision-making spaces of the project (PSC, RTC, and MUCBTC) will also serve as vehicles for communication and to increase visibility regarding the project objectives and approaches.

Communication and knowledge exchange are crucial aspects of the project; they are critical to all outcomes and outputs, so it is important to ensure communication on the project, both internal and external, with differentiated strategies.

Outcome 4.1.3 (see Section 1.3.2) specifically addresses developing and implementing the communication strategy that will be designed in a participatory way for the local beneficiary communities, project partners, territorial entities, CSOs, and other parties interested in project execution to be duly informed about how the project develops and be able to provide and receive information on the project’s details and progress.

The communication activities for project development and visibility will be planned during the first 6 months of the project to ensure participation of interested parties, as well as access to relevant information. The communication strategy will seek participation, dialogue, and improvement of the project outcomes’ visibility. Any specific visibility arrangement requested by the partners will also be considered.

The communication actions to disseminate, raise awareness, and mobilize communities, government, authorities, officers, organizations, and the general community will have as their objective that interested parties are aware and make favorable decisions about the project implementation.

Responsibility for the project activities will be shared among the communication divisions of FAO and UNIDO, and a participatory communication plan will be jointly developed, of which partner and beneficiary communities, local organizations of ethnic and peasant communities in the MUCBs intervention areas, territorial entities partners of the project (departmental governments, mayoralties, CARs, and ministries), and civil society organization will be active part of through a strategy of participatory communication that disseminates the information derived from the project at both the national and territorial levels.

Mechanism for addressing grievances, complaints, and suggestions.

The project will facilitate a redress mechanism within the framework of the FPIC that will address requests for information and will allow the different participating local beneficiary communities and organizations to file complaints, grievances, and suggestions that will be addressed by the project to ensure compliance with the project safeguards and respect for the rights of the communities.

The mechanism to address complaints, grievances, and suggestions will provide information pertinent to the project and will improve and prevent potential conflicts that the project activities may generate. The project will ensure that the beneficiary indigenous, black, and peasant communities are aware of and have access to this mechanism.

This mechanism will be developed using the following steps:

- The complaints, requests, and suggestions will initially be addressed at the technical level. If resolution is possible and they can be addressed at the technical level, no further action is required.

- When the grievance cannot be addressed at the technical level, the affected party shall approach a participation expert and/or the PC, who will receive and document the complaints and requests received in a written report. The expert shall provide a solution with assistance from the ETP, with the proper monitoring of potential related environmental and social risks. The ETP shall also document the related complaints in the respective reports.

- If the indigenous communities expert or the PC cannot address the complaint, he or she shall inform the CTR, who will decide the appropriate course of action. The CTR will communicate verbally or in writing with the persons affected about the actions that will be taken.

- If the affected person considers that the complaint or request has not been adequately addressed, he or she shall notify the CP. Once this communication is received, the PC shall inform the CTR or the CD, who will then decide the steps to take. If it is the case that the CTR or CD cannot resolve the complain, it may require an external resolution or arbitrator such as a Public Defender.

- Finally, the affected party may present his or her complaint or grievance using the FAO Response Mechanism.

# SECTION 4 – SUSTAINABILITY OF RESULTS

## 4.1 SOCIAL SUSTAINABILITY

To achieve social sustainability, the project will employ participatory approaches in identifying the interests, needs, and priorities of both men and women. Men and women will participate in decision-making processes and the sustainable management of biodiversity so that their different roles and responsibilities are considered. The stakeholder engagement process started during full project preparation. The participatory planning processes (Output 4.1.1) will provide continuity and will underline the need to adopt actions and measures that consider the differences and inequalities among certain populations (e.g., indigenous, black, and rural communities) to ensure the protection of their rights. The project will promote actions to strengthen the capacities of indigenous, black, and rural community representatives in the MUCBs to make decisions about biodiversity conservation and sustainable use, and to support traditional mechanisms for participation (e.g., assemblies, councils, etc.). Decision-making spaces within the SIRAP Pacific framework will be supported. The project will also promote the creation of community-based information exchange networks for knowledge-sharing from older community members to the youth, and between communities. By using a participatory approach, the project will adopt mechanisms that promote interest, motivation, and ensure trust, providing a favorable environment for social equality and lead to the elimination of dispositional, physical, communication barriers. In addition, FAO Farmers Field Schools (FFS) methodology will be applied, where possible, to promote knowledge-sharing on traditional biodiversity management. FFS will serve as places to hold meetings and exchange ideas and strengthening social relationships among the MUCBs’ inhabitants.

FAO’s Farmer Field School (FFS) is an approach based on people-centred learning. Participatory methods to create an environment conducive to learning: the participants can exchange knowledge and experience in a risk free setting. Practical field exercises using direct observation, discussion and decision making encourage learning-by­doing. The field is the space where local knowledge and outside scientific insights are tested, validated and integrated, in the context of local ecosystem and socio-economic settings. Community-based problem analysis is the entry point for a FFS group to develop a location specific curriculum. A growing range of technical topics are being addressed through FFS: soil, crop and water management, seeds multiplication and varietal testing, IPM, agropastoralism, aquaculture, agroforestry, nutrition, value chain, and link to markets, etc

## 4.2 ENVIRONMENTAL SUSTAINABILITY

The project activities will contribute directly or indirectly to the environmental sustainability of the project through the following:

- Strengthening integrated landscape management in the Colombian Pacific region through harmonizing territorial planning and management instruments at the departmental and municipal levels, incorporating ethnic perspectives of the territory, sectoral interests, and institutional policies to safeguard cultural, biological, and ecosystem services diversity.

- Supporting the sustainable use of biodiversity and ecosystem services within the framework of the peace-building process, based on sustainable development goals. Environmental governance will be consolidated by strengthening existing participatory structures, as well as implementing monitoring mechanisms of biodiversity mainstreaming and land uses.

- Improving the conservation and management status of regionally and globally important ecosystems by creating new PAs and improving the management of existing PAs.

- Promoting the recognition of CCS by the national government, and their access to technical and financial resources.

- Strengthening of free access SIAC – PC, which will lead to a cohesive landscape planning process.

- Developing forest zoning plans (POFs), forest management plans, and ecological restoration plans outside the PAs to ensure sustainable land management in MUCB priority areas.

- Supporting biodiversity-friendly production and promoting sustainable production systems, market access, livelihoods alternatives, natural resources conservation and sustainable use, increased family income and business development.

- Developing a participatory communication strategy to raise awareness among key stakeholders and decision makers at the national, sub-national, and local levels about the significance of biodiversity and socio-ecosystem connectivity in MUCB.

## 4.3 FINANCIAL AND ECONOMIC SUSTAINABILITY

Financial and economic sustainability will be ensured through the provision of cash and in-kind resources; co-financing by project partners; investments in conservation, restoration, and sustainable production within the framework of institutional action plans; departmental development plans; and territorial zoning plans (POTs). Project partners (PNN, SIRAP, departmental governments and municipalities) will have annual budget allocations designated for activities implemented to safeguarding the diversity of cultural, biological, and ecosystem services. This will cover project actions and in other sectors – both addressed in institutional plans. The design and implementation of the SIRAP Pacific financial sustainability strategy will ensure economic resources needed to host participatory and decision-making spaces.

The project will also contribute to CCS’ financial sustainability through the participatory development of management tools, sustainable use of resources and effective CCS management. The project will promote sustainable production systems that are aimed at conserving and managing ecosystem services in the long-term and improve local livelihoods – including SFM and production plans. These plans will include a strategy for technical support, capacity development, and a store network that will supply value-added units. Outcome 3.2 will focus specifically on (at least) five biodiversity-derived products with access to the market. The compliance with the quality requirements, MADS’ green business criteria and other standards are expected to generate higher income and employment for producer families, while supporting BD sustainable use and conservation. Additionally, community-based nature tourism initiatives will be strengthened through Component 3. This will generate new jobs in targeted communities and supplementary income for local households participating in the project. Eco-tourism actions will also contribute to the long-term conservation and sustainable use of biodiversity

## 4.4 SUSTAINABILITY OF CAPACITY DEVELOPMENT

The project will address capacity development

The project will address the three dimensions of capacity development (CD) identified in FAO’s Approach to Sustainability i) individuals (small-scale farmers, households, female-led households); ii) institutions (departmental and local governments, SIRAP Pacific, CARs, indigenous peoples/black groups structures, networks, associations); and iii) the policy enabling environment (new environmental governance strategy; enhanced institutional capacities through trainings). The interaction between community members and local CSOs, and between CSOs and DAGs will be also addressed.

CD activities will be focused on strengthening the managerial and technical skills of the national and local institutions, producer associations, civil society and local communities. At institutional level, the project will strengthen the SIRAP Pacific structures, the departmental governments, and CSOs to facilitate multi-stakeholder coordination. CD will maximize the institutionality of multiple public and private stakeholders in the design of policies and strategies on sustainable management of natural resources, biotrade, sustainable land management, and forestry. Training and raising awareness among stakeholders will improve the environmental governance in the local context (enabling environment).

At field level, the promotion of best practices will be based on methodologies already used in the country (e.g. farmer field schools, extension, farmer-to-farmer), local knowledge, and collective community work. Training methods and modules will take into account local ethno-cultural knowledge to ensure the mainstreaming of cultural issues in the proposals for plans and strategies, sustainable best practices, and forest conservation and management. Ethno-cultural knowledge will be combined with current technologies to be promoted by the project. Training events (e.g. courses, workshops, tours, and field days) will be timely programmed to ensure the participation of beneficiaries, especially women. In sum, stakeholders’ ownership of best practices will contribute to the sustainability of the acquired capacities. Systematized lessons learned will also contribute to CD sustainability.

## 4.5 APPROPRIATENESS OF TECHNOLOGIES INTRODUCED and COST/EFFECTIVENESS

The technical feasibility of the project is supported by the institutions present in the Colombian Pacific region that have considerable experience in applied research, extension, and transfer of technology adapted to the regional context, such as the CARs, IIAP, and INVEMAR, that will provide a solid foundation for the project initiatives that will be carried out on-the-ground.

The suitability of the technologies that will be supported and promoted by the project is ensured because of the fact that most of them will be based on or constituted by practices identified by the partners and participants themselves, and which have been developed traditionally by the black and indigenous peoples as a response to their particular biophysical and socioeconomic conditions. Added to this is the fact that these production practices are proven and cost effective. These practices include agroforestry systems, reforestation and ecological restoration with native species having high utilization potential. Training methodologies and technical support provided by FAO and UNIDO in Colombia will be used; these are recognized and accepted by both technicians and producers, such as the FFSs.

As a result, the project will place significant emphasis on participatory processes to allow producers to identify causes of failure in past experiences, stressing the transformation of biodiversity-derived products to implement transformation technologies adapted to the Colombian Pacific regional context, as well as plans to transfer technological capacity to ensure the proper management of the value addition units.

## 4.6 INNOVATIVENESS, REPLICATION and SCALE-UP

Project activities will be mainstreamed into public policies and newly created structures at local, regional and national level. This will generate synergies with partners in the short-, medium- and long-term. Output 1.1.2 will build guidelines with high replicability potential in other regions of Colombia facing post-conflict. Interventions targeting the PAs and voluntary CCSs will lead to experiences and lessons learned applicable in the wider SIRAP Pacific area and the National System of Protected Areas (SINAP) framework.

The project will design production and supply plans; develop value-added units in the MUCBs; strengthen technical, administrative, and management capacities; increase market access; and implement green business plans. Component 3 will apply a value chain approach, replicable in other areas of Colombia. Component 3 vision is to promote a sustainable business model that incorporates sustainable biodiversity use and the participation of indigenous, black, and rural peoples, within the entire context of the Colombian Pacific region, adapted to agro-climatic conditions, logistics, and transformed products.

Systematization of the project experiences will be performed jointly with FAO and UNIDO, to promote the lessons learned and serve as replication mechanism.  FAO and UNIDO will also communicate the project outcomes and lessons learned to other projects in the country, Latin America region, and to each agency.

## APPENDIX 1: RESULTS FRAMEWORK

| Results chain | Indicators | Baseline | Mid-term target | Final target | Means of verification | Assumptions | Responsible for data collection |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Objective: To mainstream the sustainable use and conservation of biodiversity and the provision of ecosystem services that support human welfare and vulnerable landscapes of the Colombia’s Pacific region in view of generating global and local environmental benefits and supporting the peace process. | Area (ha) under sustainable management and conservation of biodiversity and ecosystem services as a result of the project. | Zero (0) | Direct (marine and/or terrestrial): 781,064 ha, distributed in continental area: 730,788 ha; and marine-coastal area: 50,276 ha Indirect: SIRAP Pacific management area: 3,243,794 ha, distributed in marine-coastal area: 632,900 ha; and continental area: 2,610,894 ha | Direct (marine and/or terrestrial): 2,793,546 ha distributed in continental areas: 2,614,249 ha; and marine-coastal area: 179,297 ha Indirect: SIRAP Pacific management area: 10,812,647 ha, distributed in marine-coastal area: 2,109,667 ha; and continental area: 8,702,980 ha | Project monitoring reports GEF7 Core Indicators updated at the midterm and end of the project. Project evaluation reports (PIR, mid-term review and terminal evaluation) | Willingness of decision makers to harmonize the territorial and environmental management planning instruments with the planning instruments developed by black and indigenous peoples by incorporating environmental and social safeguards specific to the territory of the MUCBs, and biodiversity and ecosystem services’ sustainable management. Willingness of the black and indigenous peoples to have conservation areas as complementary contributions to biodiversity and ecosystem services conservation. Willingness of landowners and local producers to incorporate environmental sustainability criteria into their productive activities. Optimal sampling. | Project M&E Expert SIRAP Pacific MADS |
|  | Area (ha) of strategic significance for biodiversity conservation outside the PAs that applies the guidelines for harmonization of territorial and environmental management planning instruments, with the planning instruments developed by the black and indigenous peoples to safeguard cultural, biological, and ecosystem services diversity. | Zero (0) | 45,275 ha | 210,193 ha | Project monitoring reports Approval resolutions/ documents (environmental zoning in life plans/ethno-development) Project evaluation reports (PIR, mid-term and final evaluations) | Willingness of the black and indigenous peoples to have conservation areas as complementary contributions to biodiversity conservation and ecosystem services’ maintenance. Willingness of decision makers to harmonize the territorial and environmental management planning instruments with the planning instruments of the black and indigenous peoples. | Project M&E Expert SIRAP |
|  | Area (ha) contributing to socio-ecosystem connectivity in 5 MUCBs. | X (Baseline to be defined at project inception) | X | X (Final target to be defined at project inception) | Field monitoring reports Project evaluation reports (PIR, mid-term and final evaluations) | There are no significant changes in land use/cover affecting the population status of the monitored species. Sampling efforts are optimal. There is environmental variability within the normal range. | Expert in Biodiversity Monitoring GIS Expert CARs SIGAP IAvH |
| Component 1: Institutional strengthening to support pro-conservation and sustainable use in the Pacific region of Colombia |  |  |  |  |  |  |  |
| Outcome 1.1 The territorial and environmental management planning instruments are harmonized with the instruments developed by the black communities and indigenous peoples to safeguard biological, cultural, and ecosystem services diversity, leading to a general reduction in potential threats from development- oriented activities. | a) Project targeted area (hectares – ha) for reducing current and potential pressures from competing land uses and forest degrading land-uses. b) Hectares of strategic importance for biodiversity conservation outside PAs that apply guidelines and are managed to be included in the planning instruments under improved management. |  |  | a) 44,084,957 ha (marine area: 34,762,783 ha; continental area: 9,322,174 ha) corresponding to the SIRAP Pacific management area (indirect target landscape) of which at least 1,243,216 ha (direct total area). b) 210,193 hectares of strategic importance for biodiversity conservation outside PAs | Planning instruments approved GEF-7 Core Indicators updated at midterm and final points of the project. | Willingness of subnational and local authorities and private sector to apply the guidelines for harmonization of territorial and environmental management planning instruments that safeguard cultural, biological, and ecosystem services’ diversity. | Project M&E Expert |
| Output 1.1.1: A Diagnosis and Strategic Assessment of the ecosystem services in the Pacific Region. | Number of analyses and strategic assessments of ecosystem services for four MUCBs. | Zero (0) | 4 (Katios – Caoba, Farallones – Calima, Cabo Manglares – Gran Familia Awá, Muchique – Rió Saija). | 4 (Katios – Caoba, Farallones – Calima, Cabo Manglares – Gran Familia Awá, Muchique – Rió Saija). | Assessment reports Project reports | The project stakeholders recognize the usefulness of the strategic assessment inputs in several project products. Subnational and local authorities recognize the usefulness of the analysis and strategic assessment exercise and will incorporate it into their management practices. | MUCB Coordinators Ecosystem Services Expert MADS SIRAP CARs |
| Output 1.1.2: Agreed guidelines on harmonization of departmental/municipal territorial plans and Indigenous Peoples’/black communities’ instruments, with a gender approach. | # of guidelines # of planning instruments included #of pilot areas Degree of gender mainstreaming | Zero (0) | One (1) guidelines document under development | 1 Guidelines. 24 planning instruments reached. 6 pilot areas in MUCBs. Gender chapter included. | Guidelines for harmonizing instruments that safeguard cultural, biological, and ecosystem services’ biodiversity approved by the authorities. Field reports. Project reports. | Subnational and local authorities adopt the guidelines for harmonizing territorial zoning plans at the departmental and municipal levels with the planning instruments developed by black communities and indigenous peoples to safeguard cultural, biological, and ecosystem services’ diversity. Application of guidelines for harmonizing instruments that safeguard cultural, biological, and ecosystem services’ diversity will be a collective process with communities and institutions providing support. | Project Team Departmental Governments Municipalities SIRAP CARs MADS Ministry of Internal Affairs |
| Output 1.1.3: A tailor-made and open-access SIAT_PC (integrated with the Environmental Information System of Colombia - SIAC) - strengthened to harmonize the existing planning mechanisms in the Pacific Region. | SIAT-PC strengthened | SIAT-PC launched in 2002 | SIAT-PC under strengthening process | SIAT-PC strengthened and integrated into SIAC of SINA | Databases Information platform Reports of the territorial planning system and SIAC | Technical feasibility | Information Systems Expert MADS IIAP |
| Output 1.1.4: Forest zoning and management plans (POFs) outside the PAs developed, updated, and implemented in a participatory way, promotes socio-ecosystem connectivity at the MUCB level. | Number of POFs for 65,000 ha following MADS guidelines | Zero (0) | Zero (0) | Two (2) | POFs documents developed under MADS guidelines. Project reports | CARs and collective territories proximate to the PAs are willing to update the POFs. MADS makes the guidelines available for developing POFs. | Project Team Departmental Governments Municipalities SIRAP CARs |
|  | Area (ha) with forest management plans and with support for their implementation | Zero (0) | 500 ha | 2,000 ha | Forest management plans approved by environmental/ territorial authorities (CARs and one collective territory) Implementation reports | CARs and collective territories proximate to the PAs are willing to develop forest management plans. | Project Team Departmental Governments Municipalities SIRAP CARs |
| Outcome 1.2 Improved stakeholders’ capacity and participation to support the enforcement of harmonized planning and environmental management in the MUCBs | Management capacity measured through the GEF capacity development scorecard. | Capacity in SIRAP Pacific structures: - Regional roundtable: 29% (the baseline and targets will be validated at project inception) -Regional/local roundtable Katios – Caoba MUCB: x% - Regional/local roundtable Farallones – Calima MUCB: x% - Regional/local roundtable Cabo Manglares – Gran Familia Awá MUCB: x% - Regional/local roundtable Munchique – Río Saija MUCB: x% - Regional/local roundtable Serranía de Paraguas – Tatamá MUCB: x% Capacity of local groups: - Assembly CC/CI Katios – Caoba MUCB: x% - Assembly CC/RI Farallones – Calima MUCB: x% - Assembly CC/RI Cabo Manglares – Gran Familia Awá MUCB: x% - Assembly CC/RI Munchique – Río Saija MUCB: x% - Assembly CC/RI Serranía de Paraguas – Tatamá MUCB: x% (Baseline to be defined at project inception) | Capacity in SIRAP Pacific structures: - Regional roundtable: 34% - Regional/local roundtable Katios – Caoba MUCB: x% - Regional/local roundtable Farallones – Calima 2 MUCB: x% - Regional/local roundtable Cabo Manglares – Gran Familia Awá MUCB: x% - Regional/local roundtable Munchique – Río Saija MUCB: x% - Regional/local roundtable Serranía de Paraguas – Tatamá MUCB: x% Capacity of local groups - Assembly CC/CI Katios – Caoba MUCB: x% - Assembly CC/RI Farallones – Calima MUCB: x% - Assembly CC/RI Cabo Manglares – Gran Familia Awá MUCB: x% - Assembly CC/RI Munchique – Río Saija MUCB: x% - Assembly CC/RI Serranía de Paraguas – Tatamá MUCB: x% (Mid-term targets to be defined at project inception) | Capacity in SIRAP Pacific structures: - Regional roundtable: 44% - Regional/local roundtable Katios – Caoba MUCB: x% - Regional/local roundtable Farallones – Calima MUCB: x% - Regional/local roundtable Cabo Manglares – Gran Familia Awá MUCB: x% - Regional/local roundtable Munchique – Río Saija MUCB: x% - Regional/local roundtable Serranía de Paraguas – Tatamá MUCB: x% Capacity of local groups - Assembly CC/CI Katios – Caoba MUCB: x% - Assembly CC/RI Farallones – Calima MUCB: x% - Assembly CC/RI Cabo Manglares – Gran Familia Awá MUCB: x% - Assembly CC/RI Munchique – Río Saija MUCB: x% - Assembly CC/RI Serranía de Paraguas – Tatamá MUCB: x% (Final targets to be defined at project inception) | GEF capacity development scorecard updated at mid-term and final points of the project. Lists of participants in training events and exchange networks. | Sampling efforts are optimal. Beneficiaries apply the additional knowledge acquired. | Project Team and/or specialized consultant |
| Output 1.2.1: Six (6) SIRAP Pacific participation and decision-making structures, strengthened and with enhanced capacities to apply harmonized guidelines (see output 1.1.2). | Number of existing participatory and decision-making structures within the framework of the SIRAP Pacific strengthened through the project. | Zero (0) | Six (6) in process | Six (6) strengthened | Meeting minutes SIRAP Pacific performance and annual reports | There is interest in and commitment to participate. Representatives before the SIRAP Pacific are qualified to represent their communities, and receive information and decisions made within the SIRAP Pacific framework. Representativeness of the various population groups exists, ensuring the inclusion of an ethnic and gender approach in local and regional platforms. | Project Team SIRAP Pacific |
| Output 1.2.2: Five (5) local community participatory structures, strengthened and with enhanced capacities to comply with harmonized guidelines (see 1.1.2) | Number of local participatory structures strengthened for ensuring compliance with guidelines, using a gender-based approach. | Zero (0) | At least five (5) in process | At least five (5) strengthened | Meeting minutes Project reports | There is interest in and commitment to participate. Representativeness of the various population groups exists, ensuring the inclusion of an ethnic and gender approach within the local and regional organizational structures. | Project Team Communities |
| Component 2: Integrated management of PAs, buffer zones and CCS |  |  |  |  |  |  |  |
| Outcome 2.1 Reduction of pressures and threats to biodiversity and ecosystem services in 773,420 ha of existing PAs and their buffer zone. | Management effectiveness of PAs measured by the METT | - Katíos NNP: 66 - Farallones NNP: 74 - Tatamá NNP: 63 - Munchique NNP: 73 - Cabo Manglares Bajo Mira and Frontera IMND:22 - Río BravoNR: Serranía de los Paraguas NR: (Baseline to be defined and refined at project inception) | - Katíos NNP: 71 - Farallones NNP: 79 - Tatamá NNP: 68 - Munchique NNP: 78 - Cabo Manglares Bajo Mira and Frontera IMND: 27 - Río Bravo: - Serranía de los Paraguas NR: (Mid-term targets to be defined and refined at Project inception) | - Katíos NNP: 76 - Farallones NNP: 84 - Tatamá NNP: 73 - Munchique NNP: 83 - Cabo Manglares Bajo Mira and Frontera IMND: 32 - Río Bravo: - Serranía de los Paraguas NR: (Final targets to be defined and refined at Project inception) | METT updated at mid-term and final points of the project Reports analyzing multi-temporal changes in land cover GEF 7 Core Indicators updated | There is interest by the central and municipal governments, local communities, and production sectors to improve PA management and ensure the protection of conservation targets. Effective reduction of pressures on natural forests is achieved. | M&E Expert SIRAP CARs |
| Output 2.1.1: Management plans and governance mechanisms developed and/or adopted include support for the implementation of priority actions in the selected areas. | Number of hectares (ha) under management plans developed and/or adopted with support for the implementation of priority actions. | 0 | 190,282 ha | 773,420 ha | Management plans adopted PAs management reports, including Colombia’s AEMAPPS Project progress reports Official gazette and/or resolution | There is interest from the central, regional, and local governments, civil society, and production sectors to improve PAs’ management. The legal framework remains unchanged; however, changes in policy may occur under a new government. Commitments and agreements for building peace favor project implementation. The policy to reduce deforestation is adopted. The Integral Strategy for the Control of Deforestation and Forest Management is adopted. | Project Team SIRAP CARs Communities PNN |
|  | Number of governance mechanisms under implementation as a result of the project | 0 | At least two (2) under implementation | Five (5) under implementation | Reports on case studies regarding the performance and operation of governance mechanisms in the MUCBs |  | Project Team Governance Specialist PNN SIRAP Pacific |
| Output 2.1.2: One financial sustainability strategy designed and implemented for ensuring participation within the SIRAP Pacific framework | Financial strategy for the SIRAP Pacific action plan | Currently there is no strategy. | Financial strategy for the SIRAP Pacific designed. | Financial strategy for the SIRAP Pacific designed. | Financial strategy document Final strategy implementation reports | Interest of the central and departmental governments, regional environmental authorities, civil society organizations, and black and indigenous communities in financing the PAs’ management at the subnational level. | Project Team SIRAP CARs MADS Civil society Black and indigenous communities |
|  | Level of participation of members of the SIRAP Pacific with resources from the project and as a result of implementing part of the SIRAP financial sustainability strategy. | - General assembly: 0% - Regional Technical Committee: 70% | - General assembly: baseline :60% - Regional Technical Committee: baseline :80% | - General assembly: baseline + 80% - Regional Technical Committee: baseline + 90% | SIRAP Pacific meeting minutes Lists of attendance at meetings SIRAP Pacific management reports | Participation in the SIRAP Pacific is strengthened and positively influences its management. | Project Team SIRAP Pacific |
| Output 2.1.3: Forest restoration and soil recovery plans for PAs, buffer zones, connectivity areas, and corridors are developed and implementation is kick-started in a participatory manner. | Carbon captured (tCO2-eq) through soil ecological restoration and recovery as a result of the project | 0 tCO2-eq | 0 tCO2-eq | 10,646 tCO2-eq | Field and technical reports Updated GEF7 Core Indicators at mid-term and final points of the project | There are no significant changes in land use/land cover. Sampling efforts are optimal. Environmental variability within normal ranges. | SFM/LD Expert (and carbon accounting) |
|  | Area (ha) restored with the project’s support | 0 | 400 ha under restoration | 1,000 ha restored |  |  | SFM/LD Expert |
| Outcome 2.2 New PAs and CCSs receive support for management planning and implementation. | Area (ha) of new PAs under declaration process (three public PAs). | 0 | 3,356 ha | 258,603 ha | Proposals for establishing new PAs Official gazette Updated GEF7 Core Indicators at mid-term and final points of the project | There is willingness among decision- makers to establish new PAs. | Project M&E Expert SIRAP CARs MADS |
|  | Area (ha) sustainably managed through the communal CCS | 0 | 62,268 ha | 210,193 ha | Project monitoring reports Updated GEF-7 Core Indicators at mid-term and final points of the project | There is willingness by the decision makers to incorporate SFM objectives into production landscapes/MUCBs | Project M&E Expert SIRAP CARs MADS Communal Councils Indigenous Reserves |
| Output 2.2.1: Planning and management instruments developed, with priority actions implemented in CCSs, by the forest-dependent communities. | Number of planning and management instruments with early implementation actions in CCSs as a result of the project | Zero (0) | At least two (2) | Five (5) | CCS planning instruments approved by the competent platforms. CCS management reports | Willingness and feasibility exist to support the existing CCSs and the consolidation of new related initiatives | Project Team Communities SIRAP Pacific |
| Output 2.2.2: One Technical guidelines as support for the regulatory process to formalize the CCSs in the Pacific region considering ethnic/cultural aspects and in line with the national process. | Document with technical guidelines as support for regulations to formalize the CCSs in the Pacific region | There are no technical guidelines. | Technical guidelines under development | Document with technical guidelines | Document compiling and analyzing the technical guidelines for formalizing the CCSs Dissemination reports Project reports | Related authorities adopt the guidelines proposed. Continued interest by indigenous peoples | Project Team Communities MADS SIRAP |
| Output 2.2.3: Priority areas for conservation are assessed and steps towards their declaration as formal PAs are taken. | Number of new PAs progressing towards their declaration as a result of the project. | - Regional public governance: Zero (0) | - Regional public governance: Three (3) (Caoba, Serranía de los Paraguas, and Calle Santa Rosa) | - Regional public governance: Three (3) (Caoba, Serranía de los Paraguas, and Calle Santa Rosa) | Technical studies CAR proposals for the declaration of PAs | Political will and social feasibility for establishing new PAs | CARs SIRAP PNN |
| Component 3: Sustainable production practices as alternatives for local development, biodiversity protection and peace process support |  |  |  |  |  |  |  |
| Outcome 3.1 Biodiversity and ecosystem services are sustainably utilized in forest-based productive systems and generate multiple environmental and socio-economic benefits | Area (ha) under sustainable production systems | 0 | At least 3,500 ha | 10,000 ha | Field reports Project reports (PIR, mid-term review and terminal evaluation) | There is willingness by landowners and local producers to incorporate environmental sustainability criteria as part of their productive activities. There are incentives available to implement sustainable production practices. | Project Team Socio-economic Expert |
|  | Proportion of SFM initiatives and production systems led by women. | 0 | 10% | 40% | Results of surveys made available to producers. Project reports (PIR, mid-term and final evaluations) | Gender effectively mainstreamed | Project Team Socio-economic Expert |
| Output 3.1.1: Green Business action plan(s) harmonized and under implementation for fostering and developing diversified production systems are agreed upon and modalities adapted to local conditions, for supporting food security, sustainable livelihoods, landscape-level connectivity and forest rehabilitation | Number of green business plans that safeguard cultural, biological, and ecosystem services’ diversity. | Zero (0) | Three (3): Nariño, Cauca, Risaralda | Three (3): Nariño, Cauca, Risaralda | Green business plans approved by the interested parties Project reports. | Stakeholders are interested in participating. | Project Team Green Markets Expert CARs MADS |
|  | Number of green business initiatives with priority actions supported (in the MUCBs) | Zero (0) | Ten (10) | Twenty five (25) | Implementation reports of green business initiatives Project reports | Stakeholders are interested in participating. | Project Team Green Markets Expert CARs MADS |
| Output 3.1.2: SFM initiatives and sustainable production systems implemented incorporating good soil and biodiversity-friendly practices, with gender approach | Number of plans for SFM initiatives and sustainable production systems as a result of the project | Zero (0) | Eight (8) | Eight (8) | Results of surveys made available to producer families Production plans shared with stakeholders Field reports Project reports | Beneficiaries are interested in participating. Incentives available to implement environmental-friendly production practices. | Project Team SFM and SLM Expert |
| Outcome 3.2 Products and services derived from biodiversity have value added and their value chains duly strengthened. | Annual average income of beneficiary communities, maintained or increased # of value added units of BD-derived products with technical and management capacities #of BD-derived products with access to formal markets, and fulfilling the requirements for quality, MADS green business criteria, and other standards # of community-based nature tourism initiative strengthened | - Average of USD $1,240 per year per family (COP $3,600,000 per year per family) (Baseline to be defined at project inception) | - Average of USD $1,302 per year per family (5% increase) | - At least an average of USD $1,364 per year per family (at least 10% increase) Seven (7) units Five (5) products Four (4) tourism initiatives | Income assessment results Household surveys | Beneficiaries are interested in participating. Incentives available to implement biodiversity-friendly production practices. Stable and multiple markets available. | Project Team Socio-economic Expert |
| Output 3.2.1 Value addition units of biodiversity-derived products created and strengthened, with technical and management training that safeguard cultural, biological, and ecosystem services’ diversity. | Number of value addition units strengthened and created for biodiversity-derived products with technical and management capacity as a result of the project | - Value addition units strengthened: Zero (0) - Value addition units created: Zero (0) | - Five (5) value addition units in the process of strengthening - Two (2) value addition units in the process of being created | Seven (7) value addition units strengthened | Technical and management training plans for value addition units Performance report of value addition units Training documents and tools Lists of attendees at training events | Continuity of the national green business policy Favorable security conditions | Project Team UNIDO Trainers |
| Output 3.2.2: Biodiversity-derived products with market access and/or enhance compliance with quality requirements, MADS green business criteria, and other standards for market access. | Number of biodiversity-derived products with formal market access and complying with quality requirements, green business criteria of MADS and other standards for markets access | Zero (0) | At least two (2) | At least five (5) | Business plans for the five products Progress reports, audits to assess compliance with green business criteria Project reports Business agreements | Markets available Government continues strengthening the infrastructure quality Reduced contamination in project areas | Project Team UNIDO Green Markets Expert CAR |
| Output 3.2.3: Community-based nature tourism initiatives strengthened with government and non-government support that safeguard cultural, biological, and ecosystem services’ diversity. | Number of community-based nature tourism initiatives strengthened that safeguard cultural, biological, and ecosystem services’ diversity. | Zero (0) | Four (4) under development | Four (4) | Nature tourism plans. Social, environmental, and economic feasibility reports Project reports | Social, environmental, and economic feasibility Interest by the government and non-government sectors to support initiatives | Project Team UNIDO SIRAP CARs National Parks MADS |
| Component 4: Knowledge management and project M&E |  |  |  |  |  |  |  |
| Outcome 4.1 Project monitored and evaluated with a results-based management approach, and communication of lessons learned. | Progress made in project implementation | 0% | 35-50% | 100% | PIRs PPRs Mid-term and final evaluation reports | The M&E plan of the project and related actions are implemented. Project executed within the intended time. | FAO-GEF and UNIDO-GEF Coordination Units MADS Team External Evaluators |
| Output 4.1.1. Five participatory action plans for the prioritized MUCBs. | Number of action plans | Zero (0) | Five (5), 1 per MUCB | Five (5), 1 per MUCB | Draft plans Monitoring and follow-up reports | Project actions to be implemented have been identified and prioritized in a participatory manner for each MUCB | Project Team SIRAP |
|  | Number of participation agreements at the MUCB level for the conservation and sustainable use of biodiversity | Zero (0) | Five (5), 1 per MUCB | Five (5), 1 per MUCB | Agreements signed Project monitoring and follow-up reports Project partners’ institutional reports | Willingness at the institutional and collective territories level to implement actions for the conservation and sustainable use of biodiversity | Project Team MUCB Coordinator |
| Output 4.1.2 An online M&E platform | Online monitoring platform | Zero (0) | One (1) online monitoring platform being designed | One (1) online monitoring platform operating | PIR PPRs Online monitoring platform reports | Effective use of the platform by the project and other stakeholders | Project Team FAO UNIDO Implementation Partners |
| Output 4.1.3: One communication strategy for development implemented | Communication strategy | Zero (0) | One (1) communication strategy designed and in early stages of implementation | One (1) communication strategy implemented | Communication strategy reports Project-related publications PPRs | Best practices and lessons learned disseminated in a timely manner at the local, sub-national, national and regional (international) levels | Communication and Knowledge Management Expert FAO UNIDO Implementation Partners |
| Output 4.1.4: One Mid-term Review (MTR) and one Terminal Evaluation (TE) | One Mid-term Review and one Terminal Evaluation | NA | Mid-term Review report | Terminal Evaluation report | Mid-term Review and Terminal Evaluation reports | Mid-term Review and Terminal Evaluation completed according to guidelines of FAO, UNIDO and GEF and within the intended timeframe | FAO- UNIDO-GEF Coordination Unit External Evaluators |

## APPENDIX 2: WORK PLAN

| Outputs | Activities |  | Responsible | Year 1 |  |  |  | Year 2 |  |  |  | Year 3 |  |  |  | Year 4 |  |  |  | Year 5 |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 |
| Component 1: Institutional strengthening to support conservation and sustainable use in the Pacific region of Colombia. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.1.1. A Diagnosis and Strategic Assessment of the ecosystem services in the Pacific Region | 1.1.1.1 | Review and validate previous strategic assessment exercises of ecosystem services. | Project Coordinator (PC), Professional in instruments for strategic planning and assessment of ecosystem services (PISP&AES), Local Technical Supervisor (LTS) | x | x |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 1.1.1.2 | Identify and prioritize the types of ecosystem services | PC, PISP&AES, LTS |  |  | x | x | x |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 1.1.1.3 | Conduct a strategic assessment and analysis of inter-dependencies and synergies among the ecosystem services in the MUCBs. | PC, PISP&AES, |  |  |  | x | x | x |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 1.1.1.4 | Identify and prioritize an ecosystem service for its assessment in the Pacific region. | PC, PISP&AES, LTS |  |  |  | x | x | x |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 1.1.1.5 | Disseminate the results to the process participants. | PC, PISP&AES, LTS |  |  |  |  | x | x |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 1.1.1.6 | Design and implement a strategy to incorporate into the results according to MUCBs action plans. | PC, PISP&AES, LTS |  |  |  |  | x | x | x |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.1.2. Agreed guidelines on harmonization of departmental/municipal territorial plans and Indigenous Peoples’/Black groups’ instruments, with a gender approach. | 1.1.2.1 | Define and apply the criteria to prioritize pilot cases. | PC, PISP&AES, LTS, Professional in participation, ethnicity and gender (PPEG) |  | x |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 1.1.2.2 | Characterize the prioritized territorial planning instruments | PC, PISP&AES, LTS, PPEG |  |  | x | x |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 1.1.2.3 | Formulate and/or update the planning instruments of black and indigenous peoples | PC, PISP&AES, LTS, PPEG |  | x | x | x |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 1.1.2.4 | Analyze the land use conflicts according to the defined guidelines. | PC, PISP&AES, LTS, PPEG, GIS Professional (GISP) |  |  |  | x | x |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 1.1.2.5 | Define and validate in a participative manner the guidelines for the harmonization of territorial and environmental management planning instruments | PC, PISP&AES, LTS, PPEG |  |  |  |  | x | x |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 1.1.2.6 | Progress in the application of the defined guidelines. | PC, PISP&AES, LTS, PPEG |  |  |  |  |  |  | x | x | x | x | x | x | x | x | x | x | x | x |  |  |
| 1.1.3. A tailor-made and open-access SIAT_PC (integrated with the Environmental Information System of Colombia - SIAC) - strengthened to harmonize the existing planning mechanisms in the Pacific Region. | 1.1.3.1 | Establish and adapt the SIAT-PC secondary nodes | PC, PISP&AES, GISP |  | x | x | x | x |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 1.1.3.2 | Design and implement dissemination and training alternatives to access to environmental information | PC, PISP&AES, GISP |  |  |  |  |  | x | x | x | x | x |  |  |  |  |  |  |  |  |  |  |
|  | 1.1.3.3 | Design the information module for monitoring pilot cases of Output 1.1.2 and Output 2.2.2 in the SIAT-PC. | PC, PISP&AES, GISP |  |  |  |  |  | x | x | x | x |  |  |  |  |  |  |  |  |  |  |  |
|  | 1.1.3.4 | Implement actions to incorporate the information for monitoring pilot cases of Output 1.1.2 and Output 2.2.2 into the SIAT-PC. | PC, PISP&AES, GISP |  |  |  |  |  |  |  |  | x | x | x | x | x | x |  |  |  |  |  |  |
| 1.1.4. Forest zoning and management plans outside the PAs developed, updated, and implemented in a participatory way, promotes socio-ecosystem connectivity at the MUCB level. | 1.1.4.1 | Review, adjust and update the POFs selected as per MADS guidelines | PC, GISP LTS, Forest Professional (FP) |  |  | x | x | x | x | x | x |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 1.1.4.2 | Select areas for implementing POFs | PC, GISP LTS, FP |  | x |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 1.1.4.3 | Formulate forest management plans in the MUCBs and prioritize implementation actions. | PC, GISP LTS, FP |  |  | x | x | x | x |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 1.1.4.4 | Implement actions of the prioritized forest management plans. | PC, GISP LTS, FP |  |  |  |  |  |  | x | x | x | x | x | x | x | x | x | x | x | x |  |  |
|  | 1.1.4.5 | Compile local experiences on the application of MADS guidelines and disseminate them | PC, GISP, LTS, FP |  |  |  |  |  |  |  |  |  |  | x | x |  |  |  |  | x | x |  |  |
| 1.2.1. Six (6) SIRAP Pacific participation and decision-making structures, strengthened and with enhanced capacities to apply harmonized guidelines (see 1.1.2). | 1.2.1.1 | Define the participation and decision-making structures within the SIRAP Pacific framework. | PC, PISP&AES, LTS, PPEG |  | x |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 1.2.1.2 | Design the strategy for information dissemination at local and regional level within the SIRAP Pacific framework. | PC, PISP&AES, LTS, PPEG Communications Professional (CP) |  | x | x | x |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 1.2.1.3 | Implement the information dissemination strategy at local and regional level within the SIRAP Pacific framework. | PC, PISP&AES, LTS, PPEG, CP |  |  |  |  |  | x | x |  |  | x | x |  |  | x | x |  |  | x | x |  |
|  | 1.2.1.4 | Design the Training Plan for the SIRAP Pacific | PC, PISP&AES, LTS, PPEG, CP |  |  | x | x | x | x |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 1.2.1.5 | Implement the Training Plan for the SIRAP Pacific | PC, PISP&AES, LTS, PPEG, CP |  |  |  |  |  | x |  |  |  | x |  |  |  | x |  |  |  | x |  |  |
| 1.2.2 Five (5) local community participatory structures, strengthened and with enhanced capacities to comply with harmonized guidelines (see 1.1.2) | 1.2.2.1 | Define and apply the criteria to prioritize the existing regional participatory structures of black and indigenous peoples. | PC, PISP&AES, LTS, PPEG, CP |  | x |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 1.2.2.2 | Support the participation and decision-making structures of the ethnic groups. | PC, PISP&AES, LTS, PPEG, CP |  |  |  |  |  | x |  |  |  | x |  |  |  | x |  |  |  | x |  |  |
|  | 1.2.2.3 | Design routes to train environmental leaders/agents by strengthening capacities and spaces for intergenerational and intercultural dialog. | PC, PISP&AES, LTS, PPEG, CP |  |  |  | x | x | x | x |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 1.2.2.4 | Implement routes to train environmental leaders/agents by strengthening capacities and spaces for intergenerational and intercultural dialog. | PC, PISP&AES, LTS, PPEG, CP |  |  |  |  |  |  |  | x | x | x | x | x | x | x | x | x |  |  |  |  |
|  | 1.2.2.5 | Supply resources and improvement of local community participation spaces | PC, PISP&AES, LTS, PPEG |  |  |  |  |  | x | x | x | x |  |  |  |  |  |  |  |  |  |  |  |
|  | 1.2.2.6 | Design and implement in the route for experiences exchange. | PC, PISP&AES, LTS, PPEG, CP |  |  |  |  |  |  |  |  |  |  |  | x | x | x | x | x | x | x |  |  |
| Component 2: Integrated management of PAs, buffer zones and CCS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.1.1. Management plans and governance mechanisms developed and/or adopted include support for the implementation of priority actions in the selected areas. | 2.1.1.1 | Formulate and/or update the PAs management plans. | PC, PA and CCS Expert (PA&CCSE) |  | X | X | X | X | X | X | X | X |  |  |  |  |  |  |  |  |  |  |  |
|  | 2.1.1.2 | Socialize the management plans. | PC, PA&CCSE |  |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X |  |  |
|  | 2.1.1.3 | Prioritize needs for improving management effectiveness | PC, PA&CCSE |  |  | X | X | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 2.1.1.4 | Identify the needs for strengthening governance mechanisms in the PAs. | PC, PA&CCSE |  |  |  | X | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 2.1.1.5 | Prepare the investment plan for the prioritized PAs and strengthen the governance mechanisms. | PC, PA&CCSE, Administrative and Financial Professional (AFP) |  |  |  |  | X | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 2.1.1.6 | Implement the investment plan. | PC, PA&CCSE, AFP |  |  |  |  |  |  | X | X | X | X | X | X | X | X | X | X | X | X |  |  |
| 2.1.2. One financial sustainability strategy designed and implemented for ensuring participation within the SIRAP Pacific framework | 2.1.2.1 | Design the financial sustainability strategy for the SIRAP Pacific | PC, PA&CCSE |  | X | X | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 2.1.2.2 | Implement the SIRAP Pacific financial sustainability strategy. | PC, PA&CCSE |  |  |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X |  |
|  | 2.1.2.3 | Conduct participation and decision-making spaces for the SIRAP Pacific | PC, AFP |  |  | X | X |  | X |  | X |  | X |  | X |  | X |  | X |  | X |  | X |
| 2.1.3. Forest restoration and soil recovery plans for PAs, buffer zones, connectivity areas, and corridors are developed and implementation is kick-started in a participatory manner. | 2.1.3.1 | Identify sites and define types of intervention to be developed in each prioritized MUCB. | PC, SFM Professional, (SFMP), GISP |  | X | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 2.1.3.2 | Design in a participative way the ecological restoration and soil recovery plans. | PC, SFMP, GISP |  |  | X | X | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 2.1.3.3 | Implement the ecological restoration and soil recovery plans. | PC, SFM Professional, (SFMP), GISP |  |  |  |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X |
| 2.2.1. Planning and management instruments developed, with priority actions implemented in CCSs, by the forest-dependent communities. | 2.2.1.1 | Prioritize and select CCSs in the MUCBs. | PC, PA&CCSE, GISP |  |  | X | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 2.2.1.2 | Formulate planning and management instruments for the CCS. | PC, PA&CCSE |  |  |  | X | X | X | X | X |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 2.2.1.3 | Prioritize the actions to be implemented according to the CCS planning and management instruments. | PC, PA&CCSE |  |  |  |  |  |  | X | X |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 2.2.1.4 | Implement the prioritized actions in the CCSs. | PC, PA&CCSE |  |  |  |  |  |  |  |  | X | X | X | X | X | X | X | X | X | X |  |  |
| 2.2.2. One Technical guidelines as support for the regulatory process to formalize the CCSs in the Pacific region considering ethnic/cultural aspects and in line with the national process. | 2.2.2.1 | Characterize the CCS in prioritized MUCBs. | PC, PA&CCSE, GISP |  | X | X | X | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 2.2.2.2 | Define and apply minimum technical criteria required for CCSs formalization. | PC, PA&CCSE, GISP |  |  |  | X | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 2.2.2.3 | Consolidate and socialize the technical guidelines for the CCSs in Colombian Pacific region. | PC, PA&CCSE |  |  |  |  |  | X | X | X |  |  |  |  |  |  |  |  | X | X |  |  |
| 2.2.3. Priority areas for conservation are assessed and steps towards their declaration as formal PAs are taken. | 2.2.3.1 | Validate the selection of prioritized areas for conservation | PC, PA&CCSE |  | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 2.2.3.2 | Agree on actions to support the declaration process of new PAs | PC, PA&CCSE |  | X | X | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 2.2.3.3 | Implement actions for the declaration of new PAs and the prioritized management activities. | PC, PA&CCSE |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X |  |  |
| Component 3: Sustainable production practices as alternatives for local development, biodiversity protection and peace process support |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.1.1. Green Business action plan(s) harmonized and under implementation for fostering and developing diversified production systems are agreed upon and modalities adapted to local conditions, for supporting food security, sustainable livelihoods, landscape-level connectivity and forest rehabilitation. | 3.1.1.1 | Formulate departmental green business plans for the project intervention MUCBs. | PC |  |  | x | x | x | x |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 3.1.1.2 | Update the guidelines of green business plans to be included in the action plans of CARs | PC |  |  |  |  |  |  |  |  | X | X |  |  |  |  |  |  |  |  |  |  |
|  | 3.1.1.3 | Prioritize green business initiatives. | PC |  |  | x | x |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 3.1.1.4 | Implement the prioritized actions for green business initiatives | PC |  |  |  |  | x | x | x | x | x | x | x | x | x | x | x | x |  |  |  |  |
| 3.1.2. SFM initiatives and sustainable production systems implemented incorporating good soil and biodiversity-friendly practices, with gender approach. | 3.1.2.1 | Implement instruments for the establishment of the baseline. | PC, Sustainable Production Systems Professional (SPSP), M&E Professional, (M&EP) | x | x |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 3.1.2.2 | Characterization of production systems. | PC, SPSP, M&EP |  | X | X | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 3.1.2.3 | Design sustainable production and forest management plans including a technical support strategy and strengthening of abilities and collection networks to supply the value addition units. | PC, SPSP, M&EP |  |  | x | x | x | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 3.1.2.4 | Implementation of sustainable production and forest management plans. | PC, SPSP, M&EP |  |  |  |  | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x |
| 3.2.1. Value addition units of biodiversity-derived products created and strengthened, with technical and management training that safeguard cultural, biological, and ecosystem services’ diversity. | 3.2.1.1 | Select the value addition units to be benefited. | PC, Project Team (PT) UNIDO, Trainers |  | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 3.2.1.2 | Construct the business plan and the operation model for the value addition units. | PC, PT-UNIDO, Trainers |  |  | X | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 3.2.1.3 | Define the quality and quantity requirements of sustainable production and forest management plans. | PC, PT-UNIDO, Trainers |  |  | x | x |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 3.2.1.4 | Design and improve facilities and acquire equipment. | PC, PT-UNIDO, Trainers |  |  |  |  | X | X | X | X | X | X | X | X |  |  |  |  |  |  |  |  |
|  | 3.2.1.5 | Start and support the operation of the value addition units according to the processing protocols. | PC, PT-UNIDO, Trainers |  |  |  |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X |
|  | 3.2.1.6 | Create administrative and management skills. | PC, PT-UNIDO, Trainers |  |  |  |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | x | x |
|  | 3.2.1.7 | Develop and implement the sustainability strategy of the value addition units. | PC, PT-UNIDO |  |  |  |  |  |  | x | x | x | x | x | x | x | x | x | x | x | x | x | x |
| 3.2.2. Biodiversity-derived products with market access and complying with quality requirements, MADS green business criteria, and other standards for market access. | 3.2.2.1 | Determine the products to be promoted | PC, PT-UNIDO | X | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 3.2.2.2 | Establish requirements, quality and sustainability standards to access the identified markets. | PC, PT-UNIDO |  |  | X | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 3.2.2.3 | Strengthen the local institutions that are part of the quality infrastructure. | PC, PT-UNIDO |  |  |  |  | X | X | X | X | X | X | X | X |  |  |  |  |  |  |  |  |
|  | 3.2.2.4 | Provide technical assistance and training to comply with the requirements. | PC, PT-UNIDO |  |  |  |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X |
|  | 3.2.2.5 | Develop and implement the commercial strategy. | PC, PT-UNIDO |  |  |  |  |  |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X |
| 3.2.3. Community-based nature tourism initiatives strengthened with government and non-government support that safeguard cultural, biological, and ecosystem services’ diversity. | 3.2.3.1 | Identify and assess the nature-based tourism initiatives. | PC, PT-UNIDO | x | x |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 3.2.3.2 | Plan the development of tourism for the selected. | PC, PT-UNIDO |  |  | x | x |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 3.2.3.3 | Implement prioritized actions for tourism strengthening. | PC, PT-UNIDO |  |  |  |  | x | x | x | x | x | x | x | x |  |  |  |  |  |  |  |  |
|  | 3.2.3.4 | Leverage government and non-government support for the development of tourism. | PC, PT-UNIDO |  |  |  |  | x | x | x | x | x | x | x | x | x | x | x | x |  |  |  |  |
| Component 4: Knowledge management and project M&E |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 4.1.1. Five (5) participatory action plans for the prioritized MUCBs. | 4.1.1.1 | Design the methodology for the development of action plans. | PC, PPEG, CP | X | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 4.1.1.2 | Prepare participative action plans of each priority MUCB. | PC |  | X | X |  |  |  |  | X |  |  |  | X |  |  |  | X |  |  |  |  |
|  | 4.1.1.3 | Promote the signing of voluntary agreement for biodiversity sustainable use and conservation at MUCB level. | PC |  |  | X | X | X | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 4.1.2. An online M&E platform | 4.1.2.1 | Inception and final project workshops. | PC | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | X |
|  | 4.1.2.2 | Prepare and validate the M&E platform and protocol. | PC, M&EP |  | X | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 4.1.2.3 | Prepare and validate the work plan and annual budget | PC, M&EP | X | X |  | X |  | X |  | X |  | X |  | X |  | X |  | X |  | X |  | X |
|  | 4.1.2.4 | Periodic monitoring and preparation of progress reports (PPR) | PC, M&EP |  | X |  |  |  | X |  |  |  | X |  |  |  | X |  |  |  | X |  |  |
|  | 4.1.2.5 | Prepare annual reports (PIR) | PC, M&EP |  |  |  | X |  |  |  | X |  |  |  | X |  |  |  | X |  |  |  | X |
| 4.1.3. One (1) communication strategy for development implemented. | 4.1.3.1 | Design the communication strategy | PC, CP |  | X | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 4.1.3.2 | Implement the communication strategy | PC, CP |  |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X |
| 4.1.4. One Mid-term Review (MTR) and one Terminal evaluation (TE). | 4.1.4.1 | Mid-term review | PC |  |  |  |  |  |  |  |  |  |  | X | X |  |  |  |  |  |  |  |  |
|  | 4.1.4.2 | Terminal evaluation | PC |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | X | X | X |

## APPENDIX 3: PROJECT BUDGET

## APPENDIX 4: RISK MATRIX

| Description of risk | Impact | Probability of occurrence | Mitigation actions | Responsible party |
| --- | --- | --- | --- | --- |
| POLITICAL RISK |  |  |  |  |
| Political instability: change of government and senior officials’ turnaround in national, regional, and local agencies (ministries, departmental and municipal administrations, and environmental authorities). | The national, regional, and local policies and land use/territorial planning instruments will continue not to be harmonized. Disorganized public actions will deepen environmental degradation. Low participation from national and local authorities in the project. Limited ownership of project outcomes and GEBs. | Medium | The project will keep the representatives from key national authorities (MADS, PNN), sub-national agencies (CARs, SIRAP Pacific), departmental and municipal territorial entities, informed on project progress, achievements, and benefits. Roles and responsibilities during project implementation will be re-validated at inception and monitored on yearly basis. If there is a change of government, the Project Team will re-visit the agreement with the new administration. The key project partners (PNN, CODECHOCO, CARDER, CVC, CRC, CORPONARIÑO, IIAP, INVEMAR, MADS, and the Departmental Governments of Chocó and Nariño) have committed co-financing to materialize their interest in the project. | Project Committees and Coordinator |
| Local authorities show limited interest in the project and reflect a lack of willingness to take part in project activities |  |  | The project will generate participation and discussion spaces with project partners through the Project Steering Committee (PSC), Project Technical Committee (PTC), and MUCB Technical Committees. Local stakeholders will be part of agreements to implement MUCB action plans. They will be periodically reviewed and adjusted to keep up the local interest. |  |
|  |  |  | The project will promote institutional strengthening and will develop capacities of local technical teams and local communities to harmonize planning instruments. This will contribute to maintaining interest in the project at the local level. |  |
|  |  |  | The project will adopt a participatory approach, through SIRAP Pacific structures and other mechanisms. The economic incentives and production alternatives will encourage the participation of municipal authorities in project activities. |  |
| Project co-financiers do not comply with the co-financing commitments. | The project does not achieve the expected impact due to lack of available co-financing as part of the GEF alternative. | Low | The project will keep co-financiers informed regarding their financial commitments to the project. Within the framework of the PSC, matters related to co-financing contributions will be coordinated to ensure these commitments are included in the annual budgetary allocations of the partner entities. The PC will provide advice to the project Executing Partners in reporting in-kind and cash co-financing provided by co-financers and eventually other partners not foreseen in the Project Document. |  |
| SOCIAL RISK |  |  |  |  |
| Lack of interest and low participation by traditional authorities, local communities, and community leaders | Persistence of deforestation problems, changes in land use, habitat fragmentation, unsustainable production practices, and loss of ecosystem services. | Medium | The project includes a Stakeholder Engagement Plan for indigenous, black, and rural communities within the Free, Prior, and Informed Consent (FPIC) framework. The plan implementation will ensure the active participation and local ownership by beneficiary communities, including women, youth, and the elderly. | PC, local authorities, indigenous and black peoples’ representatives, and community leaders |
|  | Local livelihoods are not improved. Socio-economic and environmental benefits are not delivered. Food insecurity and environmental degradation have increased. |  | Project activities are gender-sensitive and have been designed to promote the participation of beneficiary communities in meetings and roundtables, and in workshops to develop capacities. The project will promote the application of sustainable production practices, and access to economic incentives and markets for local biodiversity-based products. New business models are expected to generate an improvement in local living conditions (Component 3). Additionally, the project will strengthen and ensure respect for and recognition of the traditional knowledge systems associated with biodiversity. Traditional authorities, local communities, and community leaders will obtain tangible social, economic, and environmental benefits, which will contribute to promoting interest in the project. |  |
|  | Delay in implementing the project activities. |  | To avoid delays, the PSC, PTC, and MUCB committees will be established at project inception, ensuring the early engagement of project stakeholders, including representatives and leaders of beneficiary black, indigenous, and peasant communities, which will be key to supporting the implementation of activities in the field (i.e., MUCBs). Stakeholders and project partners will be informed on their roles in these committees and the decision-making processes. In line with the project M&E plan, PSC meetings will be held periodically to define the Annual Work Plan and Budget (AWP/B) and review the Project Progress Report (PPR) and PIR, allowing the close monitoring of the implementation of project activities. |  |
|  |  |  | Mechanisms for fair and equitable distribution of project socio-economic and environmental benefits will be defined at inception. Benefits are detailed as follows: organizational strengthening and capacity building of beneficiary local communities, participation strategies, harmonization of life/ethno development plans, support for the CCSs, community-based monitoring of SFM plans, improvement of household incomes through the marketing of biodiversity-derived products and the promotion of eco-tourism initiatives, and improved knowledge-sharing and information access for decision-making). |  |
|  |  |  | The project formulation phase was compliant with initial FPIC requirements. In PY1 agreements will be set and signed with ethnic representatives of local beneficiary communities for implementing the MUCB action plans, in the framework of FPIC. |  |
| Low participation of women, youth, and the elderly. | The situation of invisibility and vulnerability of rural women continues. | Low | The project will apply a gender-sensitive approach and will ensure fair and equitable distribution of project benefits among women and men. The project will enhance participation of organizations of women, youth, and the elderly in decision-making processes, training events, and access to economic incentives. Additionally, as part of the project M&E strategy, gender-based indicators are included to evaluate benefits and collect gender-disaggregated data on gender mainstreaming. Likewise, the project implementation team will include an expert in participation, ethnic and gender approaches as part of the strategy to ensure the active participation of women, youth, and the elderly. |  |
|  | Livelihoods of local communities, particularly women, youth, and the elderly do not improve and social, economic and environmental benefits are not gained, thereby increasing food insecurity and environmental degradation. |  |  |  |
| ENVIRONMENTAL RISK |  |  |  |  |
| The sequence of climate change events affects vital areas for conservation, productive landscapes, and beneficiary communities. | Loss of goods and sustainable production systems developed by the project due to extreme events. Climate change is likely to alter ecosystems that are vital for species production from which natural ingredients are derived, limiting the implementation of sustainable production practices as alternatives for local development, biodiversity protection, and peace process support. | Medium | To reduce the impact of climate change, the project incorporates a socio-ecosystem connectivity approach and activities related to harmonization of planning instruments, PAs and CCSs planning and management, SFM, and sustainable production initiatives. The project activities related to biodiversity conservation include sustainable production practices, forest cover improvement, and native vegetation rehabilitation, which will contribute to increasing resilience to climate change and climate variability. In addition, the project will strengthen and improve the adaptation capacity and social resilience of local communities to climate change by respecting and recognizing their traditional knowledge of biodiversity management and the promotion of sustainable production practices. | PC, local authorities, community leaders, MADS, PNN, CARs Project Directive Committee, Technical Committees |
|  | Climate change variability contributes to biodiversity loss and determines new challenges for communities related to agriculture, natural resources management, and survival. |  |  |  |
| Socio-environmental conflicts: Extraction activities and territorial conflicts. | Delay in the implementation of project activities. | Medium | Output 1.1.1, which is related to analysis and strategic assessment of ecosystem services in the Colombian Pacific region will provide information for identifying socio-environmental conflicts. The project will foster a monitoring system with periodic reports, including identification and tracking of potential socio-environmental conflicts in each MUCB. Potential socio-environmental conflicts will be discussed within the framework of the PSC, PTC, and the committees of each MUCB so that these are considered in the planning and implementation of project activities. |  |
| SECURITY RISK |  |  |  |  |
| Armed conflict, disruption of public order, and problems related to security. | Armed conflict: Presence of illegal armed groups, homicides, threats and murders of community leaders, illicit crops, and mined areas. Conditions of scarce security in many of the project intervention areas may affect the implementation of project activities and the displacement of beneficiaries. | Medium-high | One of the factors for defining and prioritizing the MUCBs was the situation of security and public order. Areas where the main efforts for building peace are concentrated were selected. Likewise, the security criteria will be considered in selecting the areas for implementation of pilot activities and during the Technical Committee meetings of each MUCB. The security measures required by the United Nations system will be applied in such cases. The United Nations Department of Safety and Security (UNDSS) periodically evaluates the risks of the country and the specific risks for those operating in the field, by sharing this information with all the United Nations system agencies. Additionally, the Department of Protection of Citizens’ rights puts an Early Warning System at the disposal of communities and institutions that monitors the risk situations due to the armed conflict. The project will strictly follow the advice of the UNDSS concerning all matters related to security of the United Nations and project staff working on activities involving the locations of offices, movement, and participation of populations in remote areas. | PSC, Technical Committees, Implementing Agencies |
| INSTITUTIONAL RISK |  |  |  |  |
| The institutional post-conflict structure and roles and responsibilities have only recently been defined, which may limit the impact of the project. | The implementation of sustainable production practices as alternatives for local development, biodiversity protection, and consolidation of the peace process in the prioritized MUCBs depends on a solid institutional post-conflict structure at the national and local levels, which was just put into place in 2017. | Low |  | PC, PTT |

## APPENDIX 5: ENVIRONMENTAL AND SOCIAL RISK ASSESSMENT

| Question | YES or NO |
| --- | --- |
| SAFEGUARD 1 NATURAL RESOURCES MANAGEMENT | NO |
| Could this project: |  |
| Result in the degradation (biological or physical) of soils or undermine sustainable land management practices; or |  |
| include the development of a large irrigation scheme, dam construction, use of waste water or affect the quality of water; or |  |
| reduce the adaptive capacity to climate change or increase GHG emissions significantly; or |  |
| result in any changes to existing tenure rights[1] (formal and informal[2]) of individuals, communities or others to land, fishery and forest resources? |  |
| SAFEGUARD 2 BIODIVERSITY, ECOSYSTEMS AND NATURAL HABITATS | NO |
| Would this project be executed in or around protected areas or natural habitats, decrease the biodiversity or alter the ecosystem functionality, use alien species, or use genetic resources? |  |
| SAFEGUARD 3 PLANT GENETIC RESOURCES FOR FOOD AND AGRICULTURE | NO |
| Would this project: |  |
| introduce crops and varieties previously not grown, and/or; |  |
| provide seeds/planting material for cultivation, and/or; |  |
| involve the importing or transfer of seeds and or planting material for cultivation or research and development; |  |
| supply or use modern biotechnologies or their products in crop production, and/or |  |
| establish or manage planted forests? |  |
| SAFEGUARD 4 ANIMAL (LIVESTOCK AND AQUATIC) GENETIC RESOURCES FOR FOOD AND AGRICULTURE | NO |
| Would this project introduce non-native or non-locally adapted species, breeds, genotypes or other genetic material to an area or production system, or modify in any way the surrounding habitat or production system used by existing genetic resources? |  |
| SAFEGUARD 5 PEST AND PESTICIDES MANAGEMENT | NO |
| Could this project: |  |
| result in the direct or indirect procurement, supply or use of pesticides: |  |
| o on crops, livestock, aquaculture, forestry, household; or |  |
| o as seed/crop treatment in field or storage; or |  |
| o through input supply programmes including voucher schemes; or |  |
| o for small demonstration and research purposes; or |  |
| o for strategic stocks (locust) and emergencies; or |  |
| o causing adverse effects to health and/or environment; or |  |
| result in an increased use of pesticides in the project area as a result of production intensification; or |  |
| result in the management or disposal of pesticide waste and pesticide contaminated materials; or |  |
| result in violations of the Code of Conduct? |  |
| SAFEGUARD 6 INVOLUNTARY RESETTLEMENT AND DISPLACEMENT | NO |
| Could this project permanently or temporarily remove people from their homes or means of production/livelihood or restrict their access to their means of livelihood? |  |
| SAFEGUARD 7 DECENT WORK | NO |
| Could this project affect the current or future employment situation of the rural poor, and in particular the labour productivity, employability, labour conditions and rights at work of self-employed rural producers and other rural workers? |  |
| SAFEGUARD 8 GENDER EQUALITY | NO |
| Could this project risk overlooking existing gender inequalities in terms of men’s and women’s participation in decision making and/or their differential access to productive resources, services and markets? |  |
| SAFEGUARD 9 INDIGENOUS PEOPLES AND CULTURAL HERITAGE | YES |
| Would this project: |  |
| have indigenous peoples[4] living outside the project area [5] where activities will take place; or |  |
| have indigenous peoples living in the project area where activities will take place; or |  |
| adversely or seriously affect on indigenous peoples’ rights, lands, natural resources, territories, livelihoods, knowledge, social fabric, traditions, governance systems, and culture or heritage (physical[6] and non-physical or intangible[7]) inside and/or outside the project area; or be located in an area where cultural resources exist? |  |

Safeguard 9 provides guidelines to respect, include, and promote indigenous peoples’ issues in the work of the Organization. The main principles guiding such safeguard are self-determination, respect for traditional knowledge, cultural and traditional practices of indigenous peoples that contribute to sustainable development and Free, Prior and Informed Consent (FPIC). In the same way, this safeguard recognizes the importance of tangible and non-tangible cultural heritage for current and future generations.

These safeguards are aimed at complying with the following objectives: ensure respect for the United Nations Declaration of the Rights of Indigenous Peoples in all the agencies’ projects and programs; promote the right of self-determination and development with identity of the indigenous peoples; ensuring the application of the FPIC; recognizing, respecting and preserving rights, lands, natural resources, livelihoods, knowledge, social fabric, traditions and own government systems; and protect cultural heritage and avoid its alteration, damage or elimination.

Regarding the presence of ethnic groups in the project area, the project will ensure a positive involvement of these groups in the project, will avoid adverse impacts by minimizing and mitigating these effects in agreement with such populations, and will adopt benefits in a culturally sensitive way.

The due FPIC process will be implemented throughout the project life cycle and will promote the participation of local beneficiary communities as per FAO Policy on Indigenous and Tribal Peoples, United Nations Declaration on the Rights of Indigenous Peoples, ILO Convention 169, and it will follow the guidelines of FAO’s Free, Prior, and informed Consent Manual, and UNIDO Annex 6, Practical Guide for OS4 – Indigenous Peoples.

As part of the FPIC process, the project will implement participatory mechanisms and processes to promote participation and appropriation of results by the ethnic beneficiary communities, including women, the youth and the elder during the project formulation, implementation and monitoring and evaluation stages.

During the project formulation stage participative workshops and meetings were held to inform about the project, gather baseline information and define the project results framework in a participative way. This included the participation of Project Partners and the representatives of the ethnic groups that are part of the SIRAP Pacific Regional Roundtable. In this sense, the project has the advantage of having the SIRAP Pacific as Implementing Entity that is an institution with recognition in the area that since 2013 has been consolidating a conservation and participation strategy in the territory jointly with representatives of the ethnic groups.

To ensure that all relevant ethnic groups and organizations are consulted and take part in the project, a stakeholder engagement plan for indigenous, black, and rural communities is included as part of the project design (see Appendix 9) that will enable the extensive consultation of indigenous and black communities to reach consent.

Safeguard 2 aims at avoiding agriculture, livestock, fishing, forest and aquaculture practices that may cause potential negative impacts on biodiversity, ecosystems, ecosystem services or critical habitats; and sustainably managing the ecosystems to maintain the services and benefits they provide.

None of project activities will contribute to deforestation, conversion or degradation of critical habitats or environmentally sensitive areas. On the contrary, one of the strategic objectives of the project is precisely to promote the integrated management of PAs, buffer zones and CCSs mainly through two outcomes:

Outcome 2.1. Reduction of pressures and threats to biodiversity and ecosystem services in 773,420 ha of existing PAs and their buffer zone.

Outcome 2.2. New PAs and CCS receive support for management planning and implementation.

Accordingly, the project will contribute to the integrated management of PAs, buffer zones and CCSs through the activities to be implemented under Component 2 for consolidating governance mechanisms, updating and formulating management plans for of PAs and CCS, supporting the implementation of priority actions in the selected areas, develop a financial sustainability strategy to support the SIRAP Pacific, forest restoration and soil recovery through a participative processes, defining technical guidelines to support the legal process for CCS formalization, and supporting the declaration of new PAs.

Safeguard 8 is based on FAO Policy on Gender Equality and UNIDO strategy on gender equality, which establish a regulatory framework addressed to ensure minimal standards to integrate gender in a cross-cutting manner and interventions mainly addressed to women. Through the project, equal access to production resources, services and markets will be provided as well as to their control. In addition, the participation of women and men in decision making in rural institutions and political processes will be safeguarded, and it will be ensured that all the stakeholders equally benefit from the development interventions, and that inequality is not promoted or perpetuated.

This safeguard recognizes that gender equity is one of the main factors for the sustainability of the interventions in the agriculture and rural development sector.

The project approach will be sensitive to gender issues during its design and implementation by ensuring no discrimination of women or girls and gender equality. It will address the different needs and priorities of women and men promoting the effective participation of women in all the project activities and ensuring equality of opportunities for men and women in the participation and obtaining benefits according to the technical guide for governing land for women and men.

During the formulation of the project, a gender analysis was conducted to ensure that needs and priorities of men and women will be considered during the implementation of the project and to identify potential risks, benefits and impacts in relation to production supplies, resources and services and participation in decision-making. In addition, the project will collect data disaggregated by gender and will record progress regarding gender mainstreaming.

Finally, the project includes a Gender Action Plan for gender mainstreaming into the project and to promote gender equality. This plan includes gender-sensitive indicators in line with the project results framework. The Gender Action Plan is included as Appendix 13 to this Project Document.

## APPENDIX 6: ENVIRONMENTAL AND SOCIAL RISK MANAGEMENT PLAN

| Risk identified | Risk Classification | Risk Description in the project | Mitigation Action (s) | Progress on mitigation action | Indicators |
| --- | --- | --- | --- | --- | --- |
| 2. The project may be implemented within protected areas or buffer zones | Moderate | The project will intervene in five Biodiversity Use and Conservation Mosaics (MUCB) in the Pacific Region of Colombia. Those MCUB have been prioritized by using a multicriteria analysis approach (see Appendix 11). A conservation mosaic is a network of protected areas and complementary landscapes that include national parks, marine and terrestrial production landscapes, and territories of collective ethnic property . This mosaic approach will support integrated landscape management in three mosaics (i)Katíos – Caoba; ii) Farallones – Calima; and iii) Cabo Manglares – Gran Familia Awá), and partial intervention in two mosaics (Serranía de Paraguas – Tatamá and Muchique – Rio Saija). Appendix 8 includes maps of the MUCBs. The project will intervene in 82 protected areas overall. | The project aims to reduce pressures and promote the integrated management of protected areas and buffer zones through conservation and sustainable use measures. Component 2 will support the effective management of protected areas (PAs), buffer zones and complementary conservation strategies (CCSs). In order to do so, planning and management instruments will be developed, and technical guidelines to formalize the CCSs in the Pacific region will be designed. Moreover, priority areas for conservation will be assessed and necessary steps towards their declaration as formal PAs will be taken. |  | • Hectares of marine and terrestrial protected areas created or under improved management for conservation and sustainable use (GEF core indicator) |
| 9. Project activities could take place where indigenous peoples live | Moderate | During full project preparation, 58 indigenous reserves have been identified in the five MUCBs, as belonging to Embera, Embera Katío, Embera Chamí, Embera Dobida, Eperara Siapidara, Waunan, Kuna Tule, Nasa, Coconuco, Pasto, Kamentsa, Coreguaje, and Awá populations. | The project includes a Stakeholder Engagement Plan for indigenous peoples, black communities, and rural communities within the Free, Prior, and Informed Consent (FPIC) framework. The Plan will ensure the active participation and local ownership of beneficiary communities, including women, youth, and the elderly. Furthermore, this Plan foresees that all relevant ethnic groups and organizations are duly consulted and involved in project implementation activities (see Appendix 8). |  | • Number of participatory agreements (with local communities) that involve the communities and their authorities, respecting their institutions and specifying their own variables and indicators for indigenous participation. • Area under voluntary CCS – managed by indigenous peoples, black communities, and rural peoples (hectares) |

## APPENDIX 7. TERMS OF REFERENCE (Indicative)

N.1 National Project Director

The National Project Director is a governmental official assigned to the project part of co-financing, he/she will have the following responsibilities:

- Supervise and guide the PC regarding the policies and priorities within which the project is framed.

- Provide support to the financial management of the project in close collaboration with FAO and UNIDO.

- Supervise the execution of the activities corresponding to the four components of the project in close coordination with the PTT and the representation of FAO and UNIDO in Colombia.

- Review the financial biannual reports Prepared by FAO and UNIDO.

- Request for disbursement to GEF in accordance with the approved AWP/B.

N.2 Project Coordinator (PC)

The PC will act as the leader of the PIU and as Secretary of the PSC and will be responsible overall for planning, daily management, technical supervision and coordination of all project activities, carrying out the following tasks:

- Lead the execution of technical and administrative activities of the project in coordination with the members of FAO-UNIDO Implementation Unit, counting on the technical supervision of the Technical Lead Official (TLO) at the regional Office and the branch of FAO in Rome and UNIDO.

- Supervise, in coordination with the PTT, the execution of the project activities established in the AWP/B.

- Prepare the procurement plan jointly with the project technical and administrative team.

- Provide support to all the actions associated with the selection of the PTT and contracting processes: development of TORs, preparation and review of technical tests, participation in interviews, and support to the elaboration of selection minutes.

- Coordinate and participate in the inception and terminal workshops, annual project progress reviews, and the MUCB workshops with local stakeholders and Project Executing Partners to prepare the Annual Work Plan and Budget (AWP/B), and participative in the development of the action plans of each MUCB, as well as to direct the concurrence of wills for the stakeholders in each MUCB.

- Provide technical supervision and guidance to the Project Executing Partners in implementing project activities.

- Conduct regular field supervision visits and provide on-site guidance to technical staff from Project Executing Partners in the different MUCBs.

- Permanent coordination and communication with the Project Executing Partners staff in the different MUCBs and with Project Executing Partners responsible for the implementation of activities.

- Monitor project risks according to the risk matrix (see Appendix 4) and ensure that mitigation measures are being applied or alternative mitigation measures are in place.

- Ensure that the Socio-Ecosystem Connectivity approach is followed during project implementation.

- Prepare the Project Progress Report (PPR) and the Terminal Report (TR) in coordination with the PTT and UNIDO’s technical team, and submit them to the TLO, the PSC and the Project Technical Committee (PTC) for consideration and review.

- Support the TLO in the preparation of the Annual Project Implementation Review (PIR).

- Advice Project Executing Partners in reporting in-kind and cash co-financing provided by co-financers and eventual other partners not foreseen in the Project Document.

- Plan, organize and participate in meetings of the PSC, the PTC, and MUCBs Committees.

- In coordination with the PSC, the PTC, FAO – UNIDO Evaluation Office, the TLO and the FAO – GEF Coordination Unit, support the organization of the mid-term and terminal evaluations.

- Coordinate the induction of the PTT according to the policies defined by FAO.

- Coordinate with FAO and UNIDO technical teams the design of strategies enabling the execution of planned activities and delivery of project outputs.

- Coordinate the organization and execution of meetings, workshops and other events needed for the normal development of the project activities jointly with UNIDO and other project partners.

- Coordinate the updating and systematization of all the information generated in the execution of the activities.

- Promote gender equality within the PTT complying with the FAO gender policies.

- Coordinate the work plans of the other consultants hired for project implementation and verify the contracted deliverables.

- Make the necessary arrangements to facilitate, through agreements and inter-sectorial partnerships with local and national government sector, including the private sector, the development of the project and the achievement of goals.

- Carry out the audits jointly with the MUCB Supervisor, of the contracts signed for executing the project activities.

- Ensure technical compliance with the targets of the project, based on the monitoring component, M&E.

- Coordinate the implementation of the communication strategy of the project and institutional strengthening activities.

- Frequently communicate to the National Office of FAO Programs the main achievements reached and/or difficulties faced, in case they may alter the scheduled project development.

- Close and end the agreements by complying with the required procedures and processes, such as: inventories, contracts, travel, reports, budget and archive, among others.

N.3 Supervisor of MUCB

The MUCB Supervisor will have the following responsibilities:

- Provide support to the PIU regarding the development of technical and administrative activities in the MUCBs, in articulation with FAO – UNIDO technical team.

- Lead the co-financing management by the project partners in the MUCBs.

- Lead the development of the activities of the PTT in each MUCB and track the execution of the project activities established in the AWP/B.

- Provide support to the elaboration of the contracting plan according to the project needs for each MUCB.

- Support the actions associated with the selection of the PTT and contracting processes: development of TORs and preparation and review of technical tests.

- Support the preparation and execution of the inception and terminal workshops, MUCBs workshops and other participatory events needed to develop the project activities jointly with FAO-UNIDO and other project partners.

- Support the participatory formulation of the action plans for each MUCB and occurrence of wills of each prioritized MUCB.

- Provide technical assistance, permanent information and serve as a guide to the Executing Partners for implementing the project-related activities in the MUCBs.

- Periodically conduct supervision visits in the project implementation areas and provide advice to the Executing partners’ technical staff in the different MUCBs.

- Maintain permanent communication channels with FAO – UNIDO project staff in each MUCBs and with the Executing Partners in charge of the project activities in each area.

- Maintain permanent communication channels with government institutions representatives at regional and local level, CSOs, black and indigenous peoples, and Project Partners within the MUCBs.

- Support the elaboration of periodic reports on the progress of project activities as required by FAO and the GEF (PPR, PIR), as well as the final report as per FAO provisions.

- Support the organization of Directive Committee, Technical Committee and project MUCBs Committee meetings.

- Take part in official activities of FAO when the PC delegates such functions.

- Provide support to the induction of the PTT according to the policies defined by FAO to that end.

- Support the FAO and UNIDO technical team in the design of strategies enabling the execution of planned activities and delivery of project outputs.

- Promote gender equality within the PTT complying with the FAO gender policies.

- Support the PC in coordinating the work plans of the other consultants hired for project implementation and verifying the contracted deliverables.

- Provide support to the necessary arrangements to facilitate, through agreements and inter-sectorial partnerships with local and national government sector, including the private sector, the development of the project and the achievement of goals.

- Ensure technical compliance with the targets of the project, based on the monitoring component, M&E.

- Frequently communicate to PC the main achievements reached and/or difficulties faced, in case they may alter the scheduled project development.

N.4 Professional in Geographic Information Systems – GIS, Monitoring and Evaluation

The GIS/M&E Professional will have the following responsibilities:

- Prepare the AWP/B corresponding to the activities of geographic information management and storage, spatial analysis and identify geographic-related outputs during the year.

- Prepare periodic reports of the activities developed and contribute to the PPR elaboration.

- Consolidate and organize the project base line related to spatial data and cartographic information.

- Identify the requirements of geo-referred data and images from remote sensors as a function of the project products.

- Process geo-referred data and images from remote sensors as a function of the project products.

- Develop requested graphic products to support the delivery of project outputs.

- Prepare jointly with the project technical team the analysis of socio-ecosystem connectivity indicator (considering the methodology stated by the GEF project: GCP/COL/041/GFF), as the project base line for year 1 and in the closing year of the project).

- Prepare the relevant aspects concerning geo-referencing, structuring, storage and analysis of geographic information related to: i) design and implementation of the action plans per MUCB; ii) design and implementation of guidelines for harmonization of territorial and environmental management planning instruments; iii) characterization of the CCSs in the MUCBs; and iv) formulation and implementation of ecological restoration and soil recovery plans.

Additionally, he/she shall provide support to the free access SIAT-PC as an integral part of the strengthened SIAC, through the following:

- Prepare the TORs for strengthening the free access SIAT-PC and as an integral part of SIAC.

- Supervise the strengthening of free access SIAT-PC and as an integral part of SIAC.

In relation to monitoring and tracking the Professional will execute the following activities:

- Design the M&E System in consultation with executing partners and key stakeholders.

- Lead the definition of outcome and impact indicators for each project component keeping coherence and feasibility with the logic framework, the GEF7 Core Indicators, PTPA and project targets. The indicators shall consider economic, social and environmental factors as part of the project sustainability framework.

- Support the systematization and processing of the information generated by the project components to feed the indicators proposed in the GEF project framework.

- Define the methodology for the survey, delivery and processing of information necessary to feed the indicators, considering the use of Information and Communication Technologies, based on the project components and their inclusion in the information system according to FAO and UNIDO guidelines.

- Support the process of baseline feeding in each of the project components.

- Define the mechanisms to generate early warnings on delays and to propose solutions to such project delays.

- Ensure that the GEF 7 Core Indicators for the project-related focal areas are completed at mid-term and final points of the project and before the corresponding evaluations.

- Ensure monitoring of project impacts in terms of gender, including gender-differentiated indicators.

- Submit a detailed work plan specifying the tasks to be carried out, as well as the verification means to be delivered.

- Provide support to the application tools and instruments needed to implement the defined M&E plan for the project.

- Supervise the collection of the project information by the technical teams defined in the M&E plan.

- Analyze the information for each outcome and output to be achieved through the project (base line, survey of advances evaluation, etc.).

- Share the project M&E plan with the PTT.

- In accordance with FAO’s monthly report form, present the project progress based on the defined indicators.

- Ensure that the progress reports are timely delivered by the PTT and review that they are aligned with the defined indicators.

- Review and analyze the monitoring reports related to the accomplishment of the activities carried out by the PTT.

- Carry out the monthly monitoring activities to ensure the accomplishment of the activities planned in the Project Operational Plan.

- Support the PTT in the correct and timely development of the project M&E plan.

- Monthly feed the information system of Representation (AWP progress, report matrix, Gannt verification means, PSIMER, etc.), in order to monitor in a systematical and continuous way the activities carried out, as well as the products and results of the different project outcomes.

- Support the final structuring and refinement of the information generated by the project in the necessary forms and applications.

- Support the elaboration of progress reports for the resources partners, as well as the corresponding biannual and final reports.

- Promote the generation and dissemination of good practices regarding gender according to FAO’s gender equality policy.

- Provide support to the project evaluation by submitting updated information and generating related inputs.

- Take active part in FAO and UNIDO monitoring group meetings.

- Provide the required information on the progress of the project to be submitted in the different committees.

- Archive digitally, and according to the programs area instructions, the means of verification produced by the project.

- Conduct monitoring visits to the MUCBs to assess project progress and performance.

- Undertake any other related duties as required by supervisor.

N.5 Administrative – Financial Professional

The Administrative - Financial Professional will have the following responsibilities:

- Participate in the elaboration of the project procurement plan and provide follow up.

- Plan, implement and adjust the project budget according to its needs and GEF guidelines applicable to the project.

- Keep a detailed control of the project budget execution in Colombian pesos and dollars, updating the budget in a monthly basis considering the United Nations Exchange rates.

- Review and control the project budget records according to FAO available applications and the budget template provided to that purpose.

- Verify and track the incorporation of requests for payment in favor of consultants and suppliers in the budget execution.

- Permanently update in close coordination with the project administrative staff the commitments, requests and payments according to the project operational plan and approved budget.

- Prepare the financial reports required by FAO, counterparts and GEF as per the guidelines established to that purpose.

- Review and control budgetary records of the project in accordance with the available applications, such as: Integrated Management Information System (IMIS), Field Programme Management Information System (FPMIS) and Global Resource Management System (GRMS).

- Conduct the project budget reviews, process the signature before counterparts and ensure they are uploaded to FPMIS.

- Perform, support and/or track the procurement processes for the project according to FAO procedures.

- Monthly prepare the projections for the project expenses requested by FAO.

- Track and monitor expenditures, commitments and availability of project resources.

- Implement administrative and operational procedures according to FAO standards and rules and regulations of the United Nations System.

- Conduct on-field verification and monitoring of the project resources investment, as required.

- Help in and guide the administrative procedures.

- Support, review, and monitor the procurement plans.

- Undertake any other related duties as required by the supervisor.

N.6 Administrative Professional FAO-UNIDO

The Administrative - Logistical Professional will have the following responsibilities:

- Provide project operational and administrative management support.

- Provide support to the execution of the project procurement and contracting plans and monitor them.

- Implement administrative and operational procedures according to FAO standards and rules and regulations of the United Nations System.

- Conduct, support and monitor the procurement processes for the project according to FAO procedures.

- Process the administrative action requests required to prepare contracts, sub-contracts, travel, training, equipment procurement, acquisitions, payment to suppliers among others, according to FAO standards and procedures for implementing GEF projects.

- Provide support to the procurement processes related to the project framework and prepare all related documents jointly with the Project Team.

- Prepare the project procurement requests in the GRMS administrative and financial platform, in the module designed to that purpose.

- Develop the receipt of goods and/or services in the GRMS administrative and financial platform, in the module designed to that purpose by verifying the compliance with the requirements and supports demonstrating the suppliers’ compliance.

- Follow-up the inventories of Expendable and non-Expendable supplies acquired within the project framework.

- Update and control the inventories of furniture and equipment within the project execution framework.

- Advise and guide the technical team in the different project activities and administrative requirements.

- Request the payments of the project and ensure that FAO requirements to that purpose are fulfilled.

- Request the advance payments required by consultants for events, workshops, training, etc.

- Process the requests for national travel (TA and LTA), the arrangements for the corresponding travel, and track and control them.

- Review the legalization of advance payments made to consultants; prepare the LTEC with charge to the project internal team and external collaborators related with the project.

- Review that the legalization of national travel and field travel (MTC) comply with FAO standards.

- Verify that all team members have Security Clearance prior to each mission.

- Support the tracking of documentation related to the delivery of supplies, materials, and tools delivered to the beneficiary communities of the project to ensure they comply with the administrative requirements.

- Provide logistical support to carry out workshops, events and committee meetings related to the project.

- Provide support to the process for call for proposals and selection of staff for the implementation of project activities.

- Support the renewal of staff contracts and matters related to contracts of the project consultants with the guide of the Human Management area.

- On a monthly basis provide support in the elaborating of the consultants’ time sheets as per the approval by the PC.

- Support the PTT by providing training and guidelines of administrative nature.

- Support the review and control of budget records sent by the project according to the available applications as: Integrated Management Information System (IMIS), Field Programme Management Information System (FPMIS) and Global Resource Management System (GRMS), as required.

- Monitor and track the project expenses, commitments, and availability of resources.

- Prepare reports as per the needs of the project and counterparts.

- Administer the petty cash of the project.

- Support the consultants in the on-field missions, as necessary.

- Keep accounting and financial records and control of each activity carried out in the project, maintaining it organized and updated to feed the reports required by FAO within the project execution framework.

- Archive and preserve all the project correspondence, documentation and information in accordance with standards and procedures established by FAO in the project execution.

- Support the PC in the communication and information process at internal and external level.

- Undertake any other related duties as required by the PC.

UNIDO Functions

- Support the National Expert in Biodiversity Products in the project operational and administrative management.

- Process the administrative action requests required to Prepare contracts, sub-contracts, trips, training, equipment procurement, acquisitions, payment to suppliers among others, according to UNIDO standards and procedures.

- Administer and provide support to petty cash management.

- Maintain record and accountancy and financial control of each activity conducted in the project keeping it organized and updated, and provide financial reports the resources under his/her charge, on a monthly basis or the periodicity that UNIDO or GEF require.

- Support the National Expert in Biodiversity Products in preparing administrative progress reports requested to him/her and the annual reports to GEF.

- Archive and keep all the project correspondence, documentation and information according to the established standards and procedures.

- Support the coordination and control of the communication and information process at internal and external levels of the project.

- Support the logistical organization of project events, seminars, workshops and meetings.

- Safeguard the preservation of the activities archive and all the historic documentation.

N.7 Professional in participation and ethnic and gender approach

The Professional in participation and ethnic and gender approach will have the following responsibilities:

- Support the methodological design for formulating the action plans in each MUCB.

- Take active part in the workshops for the participatory development of the action plans in each MUCB.

- Design the participation plan for indigenous, black and rural peoples within the project framework and its corresponding budget.

- Articulate the participation plan to the technical project components (Components 1, 2 and 3) and agree on the activities with the PC and the PTT.

- Support and facilitate the participation agreements with indigenous, black and rural peoples in line with the action plan for each MUCB.

- Support the elaboration of the project communication strategy ensuring the inclusion of black and indigenous peoples’ needs within the project framework.

- Ensure the incorporation of the differential and ethnic approach into the four project components.

- Prepare periodic reports on the activities carried out and contribute to the development the project report.

- Document the lessons learned for each MUCB including work with indigenous and black peoples with ethnic and gender approach.

- Support the periodic M&E of the project by collecting information on variables and participation indicators for ethnic groups, men, women, the youth, and the elder.

- Support and facilitate the incorporation of the gender approach into the action plans for each MUCB.

- Support the organization and development of workshops for consultation with communities and ethnic organizations in line with the participation plan for indigenous, black, and rural peoples.

- Support the development of technical meetings within the project framework.

- Undertake any other related duties as required by the Contract Supervisor.

N.8 Professional in instruments for ecosystem services planning and assessment

The Professional in instruments for ecosystem services planning and assessment will have the following responsibilities:

- Prepare the AWP/B for project Component 1 (Institutional strengthening and planning instruments).

- Prepare periodic reports of the activities implemented and contribute to the development of the PPR.

- Support the periodic M&E of the project by collecting information related to the fulfillment of the project results framework indicators and its means of verification, and identification of lessons learned.

Concerning the definition of guidelines for harmonizing territorial and management planning instruments with the instruments of black and indigenous peoples, he/she will have the following responsibilities:

- Define a proposal of criteria for the prioritization of the pilot cases.

- Characterize the instruments of departmental and municipal territorial planning and the planning instruments of prioritized indigenous and black peoples.

- Prepare the TORs and supervise the formulation and/or updating of the planning instruments of prioritized black and indigenous peoples (life plans/ethno-development), mainly the aspects of natural resources management and administration of these instruments.

- Prepare the TORs for analyzing land use conflicts among the prioritized territorial planning instruments and the participatory definition and validation of guidelines for the harmonization of territorial and environmental management planning instruments with the planning instruments of indigenous and black peoples.

- Coordinate and supervise jointly with the participant entities, the analysis of land use conflicts among the prioritized territorial planning instruments, and the participative definition and validation of guidelines for the harmonization of territorial and environmental management planning instruments with the planning instruments of indigenous and black peoples.

- Coordinate jointly with the participant entities the progress in applying the defined guidelines.

- Provide the necessary feedback to the team responsible for the design and implementation of the information module for monitoring the pilot cases of Output 1.1.2 and Output 2.2.2 in the SIAT-PC.

- Provide support to the implementation of activities for the strengthening of the existing participation and decision-making structures and mechanisms within SIRAP Pacific, including the community participation, for the application of guidelines for harmonizing the territorial and environmental management planning instruments that safeguard cultural, biological and ecosystem services diversity.

Regarding the diagnosis and strategic assessment of socio-ecosystem services, he/she will have the following responsibilities:

- Define the baseline studies, background information, and identification of inputs needed for the diagnosis and strategic assessment of ecosystem services, considering the lessons learned and potential tools of ecological, sociocultural, and monetary valuation for the strategic assessment of ecosystem services. These results will serve as input for the development of the TORs to conduct this assessment.

- Prepare the TORs for the diagnosis and strategic assessment of ecosystem services.

- Supervise, jointly with the PC, the delivery of a diagnosis and strategic assessment of ecosystem services.

- Coordinate, jointly with the corresponding Project Team, the design and implementation of the strategy for incorporating the results of the ecosystem services assessment according to each MUCB action plan.

- Participate in the implementation and participatory activities related to the Component 1 of the project.

- Support and provide advice to other project staff and the PTT on related matters.

N.9 Professional in PAs and CCSs

The Professional in PAs and CCSs will have the following responsibilities:

- Prepare the AWP/B corresponding to the project Component 2 (Integrated management of PAs, buffer zones, and CCSs).

- Prepare periodic reports of the activities implemented and contribute to the development of the PPR.

- Support the periodic M&E of the project by collecting information related to the fulfillment of the project results framework indicators and its means of verification, and identification of lessons learned.

Concerning the development and/or adoption of management plans and governance mechanisms based on the implementation of priority actions in the selected areas, he/she will have the following responsibilities:

- Identify and prioritize, in coordination with the participant entities, the needs to improve management effectiveness (METT, AEMAPPS tool, and consultations) and strengthen the governance mechanisms in the prioritized PAs.

- Prepare and supervise, in coordination with the participant entities, the implementation of the investment plan to improve management effectiveness and strengthen governance mechanisms.

Regarding the design and implementation of the financial sustainability strategy to ensure participation within SIRAP Pacific framework, he/she will have the following responsibilities:

- Prepare the TORs and supervise, in coordination with the participant entities, the design of the financial sustainability strategy of SIRAP Pacific action plan.

- Prepare the TORs and supervise the implementation of priority actions of the financial sustainability strategy.

- Coordinate project support to enhance participatory decision-making according to the SIRAP Pacific internal regulations and work plan.

Regarding the formulation of planning and management instruments with prioritized actions implemented in the CCSs of communities depending on forests, he/she will have the following responsibilities:

- Define the criteria to prioritize and select the CCSs in the MUCBs.

- Prepare the TORs and supervise the formulation of CCS planning and management instruments of black and indigenous peoples, and implementation of prioritized actions.

Regarding the development of technical guidelines to support to the normative process for CCS formalization with ethnic/cultural emphasis for the Colombian Pacific region, and according to the national process, he/she will have the following responsibilities:

- Coordinate the characterization of CCS in the MUCBs.

- Define and develop, in coordination with the participant entities, the identification of minimum technical requirements needed to formalize the CCSs.

- Draft and share, jointly with Project Team and participant entities, the technical guidelines for the formalization of the CCSs the Colombian Pacific region at national level.

Concerning the support to priority areas for conservation under formal declaration process, he/she will have the following responsibilities:

- Validate, jointly with the participant entities, the selection of priority areas for conservation that are subject to declaration as PAs in each priority MUCB.

- Agree with the relevant entities the supporting actions to the declaration of PAs.

- Prepare the TORs and supervise the implementation of the agreed supporting actions for declaring new PAs and implementing the prioritized actions for their management.

In addition, he/she will have the following responsibilities:

- Participate in the implementation and participatory activities related to the Component 2 of the project.

- Support and provide advice to other project staff and the PTT on related matters.

N.10 Professional in Communications

The Professional in Communication will have the following responsibilities:

- Design the project communication and participation strategy that articulates the two agencies, FAO and UNIDO, and the project partners in the MUCBs.

- Prepare the project annual communication plan including the activities proposed to disseminate FAO actions in the region.

- Implement the project of communication strategy in coordination with the two agencies, FAO – UNIDO, MADS, SIRAP Pacific and community and organization partners of the project.

- Supervise the development of communication materials approved in the project communications plan by writing texts, collecting information and photographs, and submitted them for final approval.

- Supervise the development of tools for the project internal communication.

- Coordinate the execution of local, regional, and national events identified in the project communication strategy.

- Draft minutes and systematize the results of participatory events within the framework communication and participation strategy.

- Support the facilitation of local, regional and national events according to the request of the PC.

- Keep permanent communication with the entire FAO/UNIDO Project Team to determine the consulting needs with the project stakeholders.

- Support the elaboration of the project reports to the request of the PC.

- Ensure that the project information published in the FAO and UNIDO web page is updated and according to the activities carried out in the field.

- Publicize the project within the framework of the communication and participation strategy by writing and publishing press releases and developing communication materials.

- Maintain the project photographic archive.

- Promote gender equality by complying with FAO gender policy.

- Provide advice to the project on the development of project-related publications.

N.11 Professional in Sustainable Forest Management

The Professional in SFM will have the following responsibilities:

- Prepare the AWP/B corresponding to the activities of project outputs 1.1.4; 2.1.3; 3.1.1; and 3.1.2 (Components 1, 2, and 3).

- Prepare periodic reports of the activities implemented and contribute to the development of the PPR.

- Support the periodic M&E of the project by collecting information related to the fulfillment of the project results framework indicators and its means of verification, and identification of lessons learned.

Regarding Output 1.1.4 Forest Zoning and Management Plans outside the PAs developed, updated, and implemented in a participatory way, promotes socio-ecosystem connectivity at the MUCB level, he/she will have the following responsibilities:

- Direct the guidelines for updating the forest zoning plans according to MADS guidelines and in line with the CARs.

- Supervise the updating the forest zoning plans according to the work plan defined with the CARs.

- Define the guidelines and criteria for selection of areas where the forest management plans will be developed.

- Select the areas where the forest management plans will be developed.

- Support the participative formulation of forest management plans in the MUCBs and the prioritization of actions to be implemented.

- Draft a document with local experiences in the application of MADS guidelines, and the formulation and implementation of forest management plans in the MUCBs; disseminate the document among key stakeholders in order to contribute to the national policy protocols and instruments.

Regarding Output 2.1.3 Forest restoration and soil recovery plans for PAs, buffer zones, connectivity areas, and corridors, he/she will have the following responsibilities:

- Define guidelines and criteria to identify sites and activities to be implemented in each MUCB in relation to ecological restoration and soil recovery plans in the project PAs, buffer zones, and corridors.

- Design, jointly with the PTT and the Professional of Sustainable Production and Soil Management Systems and in a participative way, the ecological restoration and soil recovery plans.

- Support the implementation of the ecological restoration and soil recovery plans in each MUCB jointly with the PTT and the Professional of Sustainable Production and Soil Management Systems.

Regarding Output 3.1.1 Green Business action plan(s) harmonized and under implementation for fostering and developing diversified production systems are agreed upon and modalities adapted to local conditions, for supporting food security, sustainable livelihoods, landscape-level connectivity and forest rehabilitation, he/she will have the following responsibilities:

- Prepare the TORs for the development of departmental green business plans that safeguard cultural, biological and ecosystem services diversity in coordination with the CARs.

- Supervise the formulation of departmental green business plans according to the work plan defined with CARs.

- Identify the guidelines for green business plans to be included in CARs action plans according to the characteristics of the prioritized MUCBs.

- Define guidelines and criteria to prioritize green business initiatives in the prioritized MUCBs.

- Support and supervise the implementation of actions identified in the green business initiatives in the prioritized MUCBs, in articulation with Output 2.2.

Regarding Output 3.1.2 SFM initiatives and sustainable production systems implemented incorporating good soil and biodiversity-friendly practices, he/she will have the following responsibilities:

- Design the tools for information collection and management to establish the baseline in relation to SFM and sustainable production systems incorporating good soil and biodiversity-friendly practices in the prioritized MUCBs.

- Describe, jointly with the technical team and the Professional of Sustainable Production and Soil Management Systems, the production systems including traditional knowledge, good practices, and high impact activities.

- Design the sustainable production and forest management plans including a strategy for technical support, strengthening capacities, and collection networks for supplying the value addition units.

- Lead the implementation of the project forest management plans for each prioritized MUCB as a strategy in the conservation corridors.

Additional responsibilities:

- Support the periodic M&E of the project by collecting information on related variables and indicators.

- Participate in PIU meetings.

- Support the organization and development of workshops for consultation to ethnic communities and organizations within the implementation framework of the participation plan of ethnic and peasant communities.

- Support the PIU in technical meetings related to the project.

- Coordinate with the UNIDO team for the joint implementation of actions.

- Undertake any other related duties as required by the Contract Supervisor.

N. 12 Professional in Sustainable Production and Soil Management Systems

The Professional in Sustainable Production and Soil Management Systems will have the following responsibilities:

- Prepare the work plan and annual budget corresponding to the activities of the project outputs 1.1.4; 2.1.3; 3.1.1; and 3.1.2 (Components 1, 2 and 3) in close coordination with the Professional in Forest Sustainable Management

- Prepare periodic reports of the activities implemented and contribute to the development of the.

- Support the periodic M&E of the project by collecting information related to the fulfillment of the project results framework indicators and its means of verification, and identification of lessons learned.

Regarding Output 1.1.4 Forest Zoning and Management Plans outside the PAs developed, updated, and implemented in a participatory way, promotes socio-ecosystem connectivity at the MUCB level, he/she will have the following responsibilities:

- Support the process for defining guidelines and criteria to select the areas where the forest management plans will be developed.

- Support the participative formulation of forest management plans in the MUCBs, and the prioritization of the implementation actions, incorporating the soil sustainable management approach.

Regarding Output 2.1.3 Forest restoration and soil recovery plans for PAs, buffer zones, connectivity areas, and corridors, he/she will have the following responsibilities:

- Lead the definition of guidelines and criteria to identify sites and activities to be implemented in each MUCB in relation to ecological restoration and soil recovery plans in the project PAs, buffer zones, and corridors in close collaboration with the Professional in SFM.

- Design, jointly with the PTT and in close collaboration with the Professional in SFM and in a participative way, the ecological restoration and soil recovery plans.

- Lead the implementation of soils recovery plans in each MUCB within the project framework and jointly with the technical team.

- Provide technical guides for the implementation of soil recovery plans in each MUCB to Local Technicians that serves as local liaison and the PTT.

Regarding Output 3.1.1 Green Business action plan(s) harmonized and under implementation for fostering and developing diversified production systems are agreed upon and modalities adapted to local conditions, for supporting food security, sustainable livelihoods, landscape-level connectivity and forest rehabilitation, he/she will have the following responsibilities:

- Prepare the TORs for the development of departmental green business plans that safeguard cultural, biological and ecosystem services diversity in coordination with the CARs.

- Support the definition of guidelines and criteria to prioritize green business initiatives in the prioritized MUCBs considering sustainable production and soil management matters.

- Support and supervise the implementation of actions identified in the green business initiatives in the prioritized MUCBs, in articulation with Output 3.1.2.

Regarding Output 3.1.2 SFM initiatives and sustainable production systems implemented incorporating good soil and biodiversity-friendly practices, he/she will have the following responsibilities:

- Lead the design the tools for information collection and management to establish the baseline in relation to SFM and sustainable production systems incorporating good soil and biodiversity-friendly practices in the prioritized MUCBs in close collaboration with the Professional in SFM.

- Lead the process to describe the production systems including traditional knowledge, good practices, and high impact activities jointly with the PTT for each priority MUCB.

- Design the sustainable production plans in close collaboration with the Professional in SFM, including a strategy for technical support, strengthening capacities, and collection networks for supplying the value addition units.

- Support the implementation of the project forest management plans for each prioritized MUCB and articulate them with the socio-ecosystem connectivity strategy.

Additional responsibilities:

- Participate in PIU meetings.

- Support the organization and development of workshops for consultation to ethnic communities and organizations within the implementation framework of the participation plan of ethnic and peasant communities.

- Support the PIU in technical meetings related to the project.

- Coordinate with the UNIDO team for the joint implementation of actions.

- Undertake any other related duties as required by the Contract Supervisor.

N.13 MUCB Local Technicians (5)

The MUCB Local Technician will have the following responsibilities:

- Support the Professional in SFM in the identification, participative design, and implementation of ecological restoration and soil recovery plans for PAs, buffer zones, connectivity areas, and corridors in the prioritized MUCBs.

- Provide support to the formulation and implementation of management plans and governance mechanisms in the prioritized PAs.

- Assist the Professional in Sustainable Production Systems in describing the production systems including traditional knowledge, good practices, and high impact activities.

- Support to the Professional in Sustainable Production and Soil Management Systems and the project team in designing sustainable production and forest management plans including a strategy for technical support, strengthening capacities, and collection networks for supplying the value addition units.

- Support the start-up of the FFS-SECs (Output 3.1.2,) including training activities according to the agreed work plan, providing teaching materials, and explaining the selected subjects, as well as support to the producers in the implementation of good agriculture and livestock practices.

- Support the implementation of the required forest, agroforestry, and restoration activities.

- Support the implementation of the sustainable production and forest management plans for the prioritized MUCB.

- Support the organization and implementation of training activities for local stakeholders.

- Support the participatory processes for incorporating the socio-ecosystem connectivity approach into the planning instruments.

- Assist the implementation of field activities according to the established work plan for each priority MUCB.

- Call and coordinate meetings, work sessions and training with the project beneficiaries and local institutions, and allies and partners of the project.

- Collect information at the local level as per the consultants needs, including baseline information according to the PC guidelines.

- Support the periodic project M&E by collecting information about variables and indicators as required by the PC.

- Support the organization and development of workshops for consultations with ethnic communities and organizations within the framework of the participation plan of indigenous, black and rural peoples.

- Coordinate with the UNIDO team for the joint implementation of actions.

- Undertake any other related duties as required by the Contract Supervisor.

No. 14 National Expert in Biodiversity Products

The National Expert in Biodiversity Products will lead the implementation and monitoring of Outcome 3.2 - Products and services derived from biodiversity have value added and their value chains duly strengthened; he/she will be responsible for planning, daily management, technical supervision and coordination of all Outcome 3.2 activities by executing the following activities:

- Direct the execution of technical and administrative activities of Outcome 3.2, in collaboration with the PC and those responsible for Outcome 3.1 and Components 1, 2, and 4.

- Prepare the AWP/B for Outcome 3.2.

- Jointly with the PC, coordinate and take part in the inception workshop and annual review of project progress; participate planning workshops with local stakeholders and executing partners for developing the AWP/Bs; participate in the PSC and the PTC meetings.

- Coordinate the review and approval of the TORs for contracting within Outcome 3.2.

- Provide technical assistance and guide to consultants and executing partners for implementing the project-related activities and conduct periodic on-field supervision visits.

- Manage and maintain the relationships with national and local counterparts and beneficiaries.

- Supervise the execution of contracts, sub-contracts and procurement as per the AWP/Bs.

- Supervise the correct execution of the budget.

- Monitor and evaluate the implementation of the AWP/Bs and targets for Outcome 3.2 indicators.

- Prepare the PPR and PIR, and provide inputs for the mid-term and terminal evaluation project evaluations jointly with the Project Team as they relate to Outcome 3.2.

- Support the organization of mid-term and terminal evaluations.

- Maintain permanent communication with the project staff, executing partners and beneficiary communities; develop communication materials and supervise the implementation of the project communication strategy for aspects related to Outcome 3.2.

- Undertake any other related duties as required.

No. 15 MUCB Local Facilitators

The MUCB Local Facilitators will be responsible for supporting the on-field implementation of Outcome 3.1 and 3.2 activities. Particularly, they will execute the following activities:

- Assist and support the value addition units in the correct implementation of the activities described in the different action plans: i) business plan and operation model; ii) plan for upgrading facilities and equipment procurement; iii) program to strengthen administrative and management skills; iv) protocols for processing biodiversity-derived products; v) quality improvement plan; vi) annual operational plan of the value addition unit; vii) supply plan, and viii) commercial strategy.

- Monitor the implementation of plans for strengthening local institutional capacities that and upgrading infrastructure in coordination with the Project Team.

- Periodically visit the value addition units and keep permanent communication with beneficiaries.

- Keep continuous communication with the National Expert in Biodiversity Products and jointly monitor the implementation of actions for strengthening the value addition units.

- Facilitate the on-field activities of the consultants contracted by the project to strengthen the value addition units and local institutions, including the upgrading of infrastructure, to gain access to the market for biodiversity products and promote nature tourism initiatives.

- Organize and coordinate meetings, work sessions, and training with the beneficiaries of the value addition units for biodiversity products, as well as the local institutions, and maintain the beneficiaries informed about the project.

- Collect information at the local level as per the consultants needs, including baseline information related to change in income increase of beneficiaries according to the PTT guidelines.

- Support the establishment of agreements with the project beneficiaries and monitor their implementation.

- Undertake any other related duties as required.

Terms of reference for implementing partners – Bioinnova Corporation

The Bioinnova Corporation will provide support in technical aspects, quality improvement, administrative and management strengthening of the value addition units of the Katíos –Caoba MUCB, as follows:

- Support the consultants in charge of developing, building consensus and socializing the business plans and operation models for the value addition units.

- Analyze the supply of products, quality, availability and seasonality; traditional and technical knowledge of use, transformation and value addition to products for the value addition units in the Katíos-Caoba MUCB.

- Determine the needs for technical support, materials and goods to supply the value addition units of Katíos-Caoba MUCB with the required raw products and under quality and sustainability standards.

- Conduct workshops and roundtables with the beneficiary communities of the value addition units of the Katíos-Caoba MUCB to reach consensus and agree on: i) products to work on; ii) business plan and operation model; iii) plan for upgrading facilities and equipment procurement; iv) program to strengthen administrative and management skills; v) protocols for processing biodiversity-derived products; vi) quality improvement plan; vii) annual operational plan of the value addition unit; viii) supply plan; and ix) commercial strategy. Consensus will be materialized through agreements between beneficiaries and the project.

- Provide technical support and training to the value addition units of the Katíos-Caoba MUCB for implementing the processing protocols.

- Implement a program to strengthen the administrative and management skills of the value addition units.

- Implement technical actions strengthening local institutions that are part of the quality infrastructure.

- Provide technical support and training to assess and comply with quality requirements.

- Conduct periodic meetings with the UNIDO team, the PC, and the Katíos-Caoba MUCB coordinator to agree and inform on actions on the ground and monitor the progress regarding the established targets and outputs.

- Prepare periodic progress reports including supporting information.

- Participate in the PTC as required.

- Contribute to the adaptive management of the project by documenting the experiences in developing initiatives related with biodiversity and knowledge about the territory.

Terms of reference for implementing partners – Corporación Biocomercio Sostenible

The Corporación Biocomercio Sostenible will provide support to strengthen the supply network of the processing units, access to markets for the biodiversity-derived products, and will develop nature tourism initiatives, particularly in Farallones-Calima and Cabo Manglares-Gran Familia Awá MUCBs, with the following activities:

- Conduct the evaluation to select the eight (8) value addition units to be benefited: create two (2) new units and strengthen six (6) existing units.

- Analyze the supply of products, quality, availability and seasonality; traditional and technical knowledge of use, transformation and value addition to products for the value addition units in the Farallones-Calima and Cabo Manglares-Gran Familia Awá MUCBs.

- Prepare and implement a plan for the supply of raw products for the value addition units according to the quality and sustainability standards required to access the markets identified and in coordination with the activities planned under Output 3.1.2.

- Develop in a participative way the business plan and operation model of the value addition units of Farallones-Calima MUCB.

- Conduct workshops and roundtables with the beneficiary communities of the value addition units of the Farallones-Calima and Cabo Manglares-Gran Familia Awá MUCB to reach consensus and agree on: i) products to work on; ii) business plan and operation model; iii) plan for upgrading facilities and equipment procurement; iv) program to strengthen administrative and management skills; v) protocols for processing biodiversity-derived products; vi) quality improvement plan; vii) annual operational plan of the value addition unit; viii) supply plan; and ix) commercial strategy. Consensus will be materialized through agreements between beneficiaries and the project.

- Implement a program to strengthen the administrative and management skills of the value addition units of Farallones-Calima and Cabo Manglares-Gran Familia Awá MUCBs.

- Support the implementation of the commercial strategy through market analysis, commercial contacts identification, samples testing, and participation in fairs related with the products generated in the value addition units.

- Conduct, with support from government and nongovernment entities, the evaluation, planning, and implementation of prioritized activities for nature-based tourism initiatives.

- Conduct periodic meetings with the UNIDO team, the PC, and MUCB coordinators to agree and inform on actions on the ground and monitor the progress regarding the established targets and outputs.

- Prepare periodic progress reports including supporting information.

- Participate in the PTC as required.

- Contribute to the adaptive management of the project by documenting the experiences in developing initiatives related with biodiversity and knowledge about the territory.

## APPENDIX 8. MAPS OF THE PROJECT INTERVENTION AREAS

MUCB Katíos – Caoba

MUCB FARALLONES – CALIMA

MUCB CABO MANGLARES . GRAN FAMILIA AWÁ

MUCB SERRANÍA PARAGUAS - TATAMÁ

MUCB MUNCHIQUE – RÍO SAIJA

## APPENDIX 9. STAKEHOLDER ENGAGEMENT PLAN AND CONSULTATION WITH INDIGENOUS, BLACK, AND RURAL COMMUNITIES

As the project will be implemented in the traditional communities of indigenous, black and rural peoples, it will be designed to ensure conformity with the GEF Principles and Guidelines for Engagement with Indigenous Peoples, social and environmental safeguards for REDD+ in Colombia, and the environmental and social safeguards of the implementation agencies (FAO and UNIDO), which specifically relate to safeguards that respect traditional knowledge and the rights of these communities (FAO Safeguard 9: Indigenous Populations and Cultural Heritage, and UNIDO Safeguard 4: Indigenous Population). In Colombia these safeguards are also applicable to Black, raizal, and palenque communities.

The process of Free, Prior, and Informed Consent (FPIC) for these communities will be applied throughout the project duration in accordance with the FAO Manual for this process. This is a right fully recognized by ILO Convention 169 and the United Nations Declaration on the Rights of Indigenous Peoples, which has been entirely incorporated into the FAO Policy on Indigenous and Tribal Peoples, FAO Environmental and Social Management Guidelines, and UNIDO Environmental and Social Safeguards Policies and Procedures.

The stakeholder engagement plan that has been designed for the project will incorporate a differential approach that is inclusive of ethnic and cultural diversity as a cross-cutting topic during the project development and implementation stages, and that will ensure the rights of indigenous, black, and rural communities in the project’s area of influence. The plan will respect the cultural diversity of these territories and ensure the effective participation of local communities through a participation mechanism that will be applied throughout the project life cycle, ensuring the achievement of the project objectives, the proper development of its activities, and the sustainability of its outcomes.

The project assumes, as strategy for the cross application of its components, that conditions will be created that promote, facilitate, and improve the full and effective participation of indigenous, Black, and rural peoples. This includes the equal participation of men and women in decision-making instances and the implementation of activities that will touch upon their traditional knowledge systems as per the specific cultural attributes of the different populations and territories, thereby ensuring the generation of social, economic and environmental benefits at local level.

Incorporating ethnic or cultural variables or dimensions into plans, projects, instruments, or procedures does not follow a single set of instructions, as there is a broad wealth of diversity among the different communities. The inclusion of such variables will serve to gather specific information from these population groups that will be useful in developing plans, projects, procedures, policies, programs, and activities that consider their different needs and are culturally appropriate to their vision of the territory.

The participation of authorities and representatives from the beneficiary ethnic and rural communities is critical for the decision-making processes and the development of activities that will ensure the communities’ empowerment, autonomy, and governability in their territories according to their life plans/ethno-development framework.

A path to participation for these ethnic and rural communities has been developed, and will be executed in two phases: the first during the project development phase and the second during the project implementation phase.

Project development phase

The following two steps were developed for the project development phase:

FPIC: FPIC is a specific right of indigenous and Black peoples. It is part of human rights and is the universal right to self-determination. FPIC is recognized by the International Labor Organization (ILO) Convention 169, United Nations Declaration on the Rights of Indigenous Peoples (UNDRIP), the Convention on Biological Diversity (CDB), and regulatory provisions on this subject at the national level based on the political constitution, national legislation, and jurisprudence (Sentences of the Constitutional Court) of Colombia.

This process is in line with the fundamental right to prior consultation at the national level that stipulates the obligation to consult these communities whenever works, activities, or projects are to be carried out in their territories, or administrative and legislative measures are to be implemented that may affect them in any way. Prior consultation is an intercultural dialogue intended to ensure real, timely, and effective participation of communities and indigenous peoples in administrative or legislative initiatives that directly affect them, as well as in developing plans and programs that affect them.

The consent allows indigenous peoples’ and black communities to ensure that their priorities and needs are considered, that there is respect for their cultural identity and self-determination. It also allows them to exercise control and manage their territories,  in addition to be well informed about the project issues to make decisions.

FPIC is achieved when a measure, action, or project may affect lands, territories and resources that ethnic peoples customarily have, enabling such groups to provide or deny the consent and negotiate the conditions under which the project will be designed, implemented, monitored, and evaluated. This project will guarantee the due implementation of the FPIC process to ensure the full and effective participation of indigenous communities concerned by  the project and their consent to implement the activities in their territories, minimizing the identified risks related to participation, consent, and interests of ethnic groups in the project, and building relationships based on trust and respect for their traditional knowledge systems.

According to the FAO Manual on FPIC, the consent shall be freely granted with no coercion, intimidation, or manipulation. Similarly,  ‘prior’ refers to a consent that is reached in advance of the implementation of activities, thereby respecting the communities’ own time; and “Informed” relates to the nature of the commitment and the need for providing all relevant information to obtain the consent.

The steps proposed for the FPIC process according to FAO FPIC Manual are: 1) identify the indigenous peoples concerned and their representatives; 2) document geographic and demographic information through participatory mapping; 3) design a participatory communication plan and carry out iterative discussions to disclose project information; 4) reach consent; 5) conduct participatory monitoring and evaluation of the agreement; and 6) document lessons learned.

During the project development stage, the following steps were addressed: identification of indigenous peoples concerned by the project’s  intervention and participatory mapping. Steps 4 to 6 will be performed during the project implementation process.

Identification of ethnic populations having influence in the MUCBs. The project respects and recognizes the cultural and ethnic diversity present in the Colombian Pacific region by identifying the indigenous populations’ territories and black communities’ territories with influence in the project.

The indigenous territories are organized into indigenous reserves, settlements, and “partialities,” which are considered imprescriptible, non-seizable, and unalienable under Acts 89 of 1890, 160 of 1994, 21 of 1991, and 70 of 1993. They have their own traditional authorities and government modalities known as “cabildos,” and their own planning instruments such as internal regulations and life plans  and safeguard plans.

As such, the project recognizes the need to articulate these communities’ life plans as legal planning exercises with territorial planning instruments and plans, as proposed in Output 1.1.2 of Component 1.

During project development in the five MUCBs, 58 indigenous reserves were identified as belonging to Embera, Embera Katío, Embera Chamí, Embera Dobida, Eperara Siapidara, Waunan, Kuna Tule, Nasa, Coconuco, Pasto, Kamentsa, Coreguaje, and Awá populations (see Table 1).

Table 1: Indigenous reserves with influence in the intervention MUCBs

| MUCB | Municipality | Indigenous Resguardos | Ethnic group |
| --- | --- | --- | --- |
| Katíos-Caoba | Juradó | Nussi purru | Embera, Embera Katío, Waunan |
|  |  | Jurado | Embera, Embera Katío, Waunan |
|  | Riosucio | Rio Quiparadó | Embera |
|  |  | Salaqui y Pavarandó | Embera Katío, Waunan |
|  |  | Peranchito | Embera Katío |
|  |  | Perancho | Embera Katío |
|  |  | Yarumal y el Barranco | Embera |
|  |  | Rio la Raya | Embera, Embera Katío |
|  |  | Peña Blanca-rio Truandó | Embera Katío |
|  | Mutata | Chontadural cañero | Embera Katío |
|  | Unguia | Tanela | Kuna Tule, Embera Katío |
|  |  | Arquia | Kuna Tule, Embera |
|  |  | Cuti | Kuna Tule |
|  |  | Eyakera dogibi | Embera Dobida |
|  | Acandí | Chidima tolo | Embera Katío |
|  |  | Pescadito | Embera Katío |
|  | Carmen del Darien | Urada Jiguamiand | Embera, Embera Katío |
| Farallones-Calima | Restrepo | Nabera drua | Embera Chami |
|  |  | Los Niasa | Embera Chami, Nasa, Coconuco |
|  | Dagua | Yu yik kwe | Nasa |
|  | Vijes | Wasiruma | Embera, Embera Chami, Nasa |
|  | Buenaventura | Chonara Huena | Eperara Siapidara |
|  |  | La Delfina | Nasa, Embera Chami |
|  |  | Rio Dagua | Waunan |
| Cabo mangalres-Gran Familia Awá | Tumaco | El Gran Sabalo | Awa, Pasto |
|  |  | La Turbia | Awa |
|  |  | Kejuambi Feliciana | Awa |
|  |  | Chinquirito Mira | Awa |
|  |  | Piguambi Palangala | Awa |
|  |  | Piedra Sellada-q.Tronqueria | Awa |
|  |  | Gran Rosario | Awa |
|  | Barbacoas | Honda Rio Guiza | Awa |
|  |  | Chimbagal | Awa |
|  | Ricaurte | Guadual-Cumbas-Invina-Arrayan | Awa, Pasto |
|  |  | Pialapi Pueblo Viejo | Awa, Pasto, Kamentsa |
|  |  | Cuchilla-Palmar | Awa, Pasto |
|  |  | Awa del Alto Albi | Awa, Pasto, Kamentsa |
|  |  | Cuascuabi-Paldubi | Awa |
|  |  | Cuasbil-la Faldada | Awa |
|  |  | Guambi-Yaslambi | Awa |
|  |  | Pingullos-Sardinero | Awa |
|  |  | Cuaiquer Integrado La Milagrosa | Awa, Nasa, Pasto |
|  |  | Chagui, Chimbuza, Vegas, San Antonio, otros | Awa, Pasto, Kamentsa |
|  |  | Nulpe Medio-Alto Rio San Juan | Awa |
|  |  | Alto Cartagena | Awa, Pasto |
|  |  | Palmar Imbi | Awa |
|  |  | Gualcala | Awa |
| Munchique Río Saija | Timbiquí | Rio Guangui | Eperara Siapidara |
|  |  | Calle Santa Rosa - Rio Saija | Eperara Siapidara, Embera |
|  |  | Infi | Eperara Siapidara, Coreguaje, Nasa |
|  |  | Almorzadero, San Isidro y la Nueva Unión | Eperara siapidara, coreguaje |
|  | López de Micay | Isla del Mono | Eperara siapidara |
| Serranía Paraguas-Tatamá | El Cairo | Doxura | Embera Chami, Yanacona |
|  | Mistrató | Loma de Citabara | Embera Chami |
|  |  | Unificado Chami Río San Juan | Embera |
|  | Pueblo rico | Gito Docabu | Embera Chami, Embera Katío, Embera |
|  | Novita | Sabaletera San Onofre El Tigre Embera, | Embera Katío |
|  | Tadó | Tarena | Embera Chami, Eperara Siapidara, Embera |

Source: Compilation based on the municipal map of indigenous reserves. Scale 1.500.000 IGAC, 2015

The black population is organized into collective territories of black communities that hold legal titles under Act 70 of 1993 and collective occupancy territories without legal titles. Act 70 of 1993 recognizes the black communities’ right to the collective ownership of land that they have been occupying ancestrally and historically, and establishes that to receive the collective entitlement lands, each community shall constitute itself as a communal council.

Black communities have ethno-development plans that are also considered to be management and planning instruments that define their perspectives, interests, and needs for self-development, which responds to their considerations for environmental preservation, conservation, and qualification of their traditional production practices, the eradication of poverty, and respect for and recognition of their social and cultural life.

It is important to note that not all the communal councils have an ethno-development plan; some have a territorial and environmental management plan for joint territory planning with the CARs, as is the case of the Farallones-Calima MUCB communal councils (see Component 1). These plans denote the legal recognition of collective territories and the communities’ full and appropriate access to land and natural resources, enabling a more participatory land management process.

A total of 71 communal councils were identified in the five MUCBs (see Table 2).

Table 2: Communal councils with influence in the intervention MUCBs

| MUCB | Municipality | Communal council |
| --- | --- | --- |
| Katíos-Caoba | Riosucio | Pedeguita and Mancilla |
|  |  | Cacarica River watershed |
|  |  | Salaquí River watershed |
|  |  | La nueva |
|  |  | La Larga River and Turmaradó |
|  |  | Quiparadó River watershed |
|  |  | Vigía de Curbaradó and Santa Rosa de Limón |
|  |  | Clavellino |
|  |  | Midle Truandó |
|  |  | Dos bocas |
|  | Riosucio-Carmen del Darién | Domingodó River |
|  | Riosucio-Carmen del Darien-Belén de Bajirá | Curvaradó Rio |
|  | Carmen del Darién-Belén de Bajirá | Jiguamiandó |
|  | Carmen del Darién | La Madre |
|  |  | Apartadó Buenavista |
|  | Unguia | Major of the Lower Atrato (Cocomaunguía) |
|  |  | Tolo River and southern coastal area (Cocomasur) |
|  | Acandí | Acandí Seco River, el Cedro and Juancho (Cocomaseco) |
|  |  | Acandí River, northern coastal zone |
| Farallones-Calima | Buenaventura | Tapral |
|  |  | Sabaletas |
|  |  | Guaimía |
|  |  | Guadualito |
|  |  | Citronela Dagua River |
|  |  | Lower Potedó |
|  |  | Calle Larga Dagua River |
|  |  | Campo hermoso |
|  |  | Major of the middle and upper Dagua River |
|  |  | San Marcos |
|  |  | Córdoba and San Cipriano |
|  |  | Upper Potedó |
|  |  | Zacarias Dagua River |
|  |  | Limones |
|  |  | Agua clara |
|  |  | La esperanza |
|  |  | Upper Dagua River - Pacifico Cimarrones de Cisneros |
|  |  | Bellavista Anchicayá |
|  |  | Llano bajo |
|  |  | Major of the Anchicayá River watershed |
|  |  | Brazitos and Amazonas |
|  |  | De la Brea |
|  |  | Calima River lowe waterhed |
|  |  | Yurumanguí River |
|  |  | Cajambre River |
|  |  | Caucana |
|  | Dagua | Upper Anchicayá |
|  | Bajo Baudó (Pizarro), El Litoral del San Juán (Docordó), Istmina, Medio San Juan (Andagoya), Nóvita, San José del Palmar | Middle, Lower, and Coastal Zone of the San Juan (ACADESÁN) |
| Cabo Manglares-Gran Familia Awá | Tumaco | Upper Mira and Frontera |
|  |  | Rescate Las Varas |
|  |  | Tablón Salado River |
|  |  | Lower Mira and Frontera |
|  |  | Gualajo River |
|  |  | Imbilpí del Darmen |
|  |  | Rosario River union |
|  |  | Tablón Dulce River |
|  |  | El Recuerdo de Nuestros Ancestros of the Mejicano River |
|  |  | Union of the Chaguí River |
|  | Francisco Pizarro-Tumaco-Olaya Herrera | Del Rio Patía Grande, its branches and the Acapa sound |
| Munchique Río Saija | Timbiquí | San Bernardo Patía Norte River watershed |
|  |  | Lower Saija Cuenca del río |
|  |  | Negros en Acción |
|  |  | Uppoer-southern Saija River |
|  | López de Micay | San Joc Upper Micay River |
|  |  | El playón of the Siguí River |
|  |  | La Mamuncia, middle Micay River |
| Serranía Paraguas-Tatamá | Pueblo rico | Piedras Bachichi |
|  |  | Black community of the Municipality of Pueblo Rico, Risaralda |
|  | Condoto | Major of the Municipality of Condoto and fo the Iró River |
|  | Tadó | Major of the Upper San Juan (ASOCASAN) |
|  | Novita | Major of Nóvita |
|  | Istmina, Nóvita, Sipí y Litroal del San Juán | Middle, lower and coastal zone of the San Juan (ACADESAN) |

Source: Compilation based on the municipal map of black communities’ collective titles. Scale 1.500.000. IGAC 2016

Secondary-level organizations of indigenous and black peoples were identified as having influence in the MUCBs, such as the Association of Indigenous Cabildos of Valle del Cauca (ACIVA); the Association of Indigenous Cabildos Waunan, Embera Dóbida, Katío, Chamí and Tule of Department of Chocó (OREWA); the Indigenous Unit of the AWÁ People (UNIPA); the Network of Communal Councils of the South Pacific (RECOMPAS), comprising 14 communal councils located in the south coast of Nariño in the municipalities of Tumaco and Francisco Pizarro; and the Black Communities Process (PCN), comprising black community organizations of the Departments of Nariño, Valle and Cauca, who are participating in processes related to defense of the environment and sustainable development in the Pacific region.

Participatory mapping. During the development of the Project Document different organizational structures for participation were created with the project partners, organizations, and communities to inform them about the general project scheme, to gather baseline information, reach consensus through a participatory manner to determine the project results framework, and gather their main perceptions of the project.

During these meetings the project promoted the participation of representatives of ethnic groups in the SIRAP Pacific framework, which is means for articulating stakeholders, PAs, and other conservation groups in rural and urban areas of the Colombian Pacific region with the goal of conservation and strengthening self-governance.

Representatives from indigenous and black communities took part in the SIRAP Pacific Regional Roundtable of organizational structures for participation (see Table 3), so that participatory mechanisms already in existence in the region could be enhanced within the institutional and community framework with the support of SIRAP Pacific. In this way the work performed and the experiences derived from this work related to the articulation of PAs and CCSs may be recognized, as well as institutional articulation with the communities, ethnic environmental officials, building of joint agreements, and knowledge about and respect for conservation initiatives among the different cultures.

Table 3 lists the spaces that served as means for consultation, participation, consensus-building, and provision of feedback with the region’s stakeholders who are allies and participants in the project development process. In the dialogs conducted in each MUCB, working roundtables were developed using participatory mapping exercises to gather baseline information related to mapping of stakeholders, ecosystem services, PAs, complementary conservation strategies, forest management, sustainable production initiatives, and biodiversity products that are significant to the local environs.

Table 3. Project participation and consensus spaces

| Event | Location and Date | Objective | Representatives of Communal Councils, Reserves, and other CSOs | Institutional Stakeholders | Attendance List |
| --- | --- | --- | --- | --- | --- |
| Project inception workshop | Bogotá, September 6, 2017 | Technical meeting to kick off the project document development with the goal of appropriation of the objectives, goals of the PIF goals, work plan, and the intended outputs for the project document development stage. |  | PNN, INVEMAR, FAO, UNIDO, MADS, Sustainable Pacific Vision, CBS Colombia | ..\Memorias eventos - proceso formulación\Listas de asistencia - Anexo 8\Lista asistencia taller Bogota 26 Sep 2017.pdf |
| Validation workshop | Cali, October 24, 2017 | Workshop to inform about the project antecedents, as well as results, outputs, and indicators of the project approved profile (PIF), the work plan to develop the project document, the MUCBs proposal, and to reach consensus on joint workspaces within the project development framework. | -Agua Clara Communal Council: Gilberto Montaño -Association of indigenous cabildos of Valle del Cauca Pacific region (ACIVA): Ligio Quiroz | CVC, INVEMAR, PNN, Corponariño, CRC, FAO, UNIDO, MADS, Sustainable Pacific Vision, CBS Colombia, IIAP, FAO, UNIDO | ..\Memorias eventos - proceso formulación\Listas de asistencia - Anexo 8\Lista asistencia taller Cali 24 Oct 2017- GEF Pacifico.pdf |
| Workshop Tatamá-Serranía Paraguas MUCB | November 16, 2017 | Present, socialize, and receive feedback on the project profile; identify input information for the baseline and analysis of the MUCB territorial context; collect key information to introduce, from the local-regional point of view, the approaches and actions to be developed in the MUCB | -Serraniagua: Cesar Franco | CVC, CARDER, PNN, IIAP, FAO | ..\Memorias eventos - proceso formulación\Memorias- Talleres Mosaicos\Memorias_TallerTatama-SerraniaParaguas_17-11-2017.pdf |
| Workshop Katíos Caoba MUCB | Turbo, November 22, 2017 | Present, socialize, and receive feedback on the project profile; identify input information for the baseline and analysis of the MUCB territorial context; collect key information to introduce, from the local-regional point of view, the approaches and actions to be developed in the MUCB | -Cuenca del Río Cacarica Communal Council: Pablo Salazar and Orlando Chochoguiro. -Bajo Cacarica Communal Council: Eulices Ramírez -Vigía de Curbaradó y Santa Rosa de Limón Communal Council: Jairo Mercado Córdoba -Montaño Indigenous Reservation: Ana Rubiela Palacios -Waunan Juin Phubuur Indigenous Community: Ovidio Chucho | BIOINNOVA, PNN, FAO, UNIDO CODECHOCO, | ..\Memorias eventos – proceso formulación\Memorias- Talleres MUCBos\Memorias_TallerKatios-Caoba –Noviembre de 2017.pdf |
| Workshop Cabo Manglares-Gran Familia Awá MUCB | Tumaco, November 27, 2017 | Present, socialize, and receive feedback on the project profile; identify input information for the baseline and analysis of the MUCB territorial context; collect key information to introduce, from the local-regional point of view, the approaches and actions to be developed in the MUCB | -Bajo Mira y Frontera Communal Council: Edwin Grueso (Vice-President), Ricardo Montaño (treasurer), Enrique Garrido Ruiz (spokesperson), Maritza Landázuri (comptroller). --ASOCASAN: Jefferson Quinto | PNN, IIAP, FAO, CORPONARIÑO CBS Colombia, Chocolate Tumaco Foundation, | ..\Memorias eventos - proceso formulación\Memorias- Talleres Mosaicos\Memorias Taller Mosaico Cabo Manglares .pdf |
| Workshop Farallones-Calima MUCB | Buenaventura, November 30, 2017 | Present, socialize, and receive feedback on the project profile; identify input information for the baseline and analysis of the MUCB territorial context; collect key information to introduce, from the local-regional point of view, the approaches and actions to be developed in the MUCB | Agua Clara Communal Council: Gilberto Montaño. -Association of indigenous cabildos of Valle del Cauca pacific region (ACIVA): Ligio Quiroz. | PNN, IIAP, FAO, CBS Colombia, UNIDO, CVC. | ..\Memorias eventos - proceso formulación\Memorias- Talleres Mosaicos\Memorias Taller Farallones-Calima.pdf |
| Meeting Munchique – Rio Saija MUCB | Popayán, December 12, 2017 | Present, socialize, and receive feedback on the project profile; identify input information for the baseline and analysis of the MUCB territorial context; collect key information to introduce, from the local-regional point of view, the approaches and actions to be developed in the MUCB | -Calle Santa Rosa Reservation: Carlos Quiro | PNN, FAO, CRC. | ..\Memorias eventos - proceso formulación\Memorias- Talleres Mosaicos\Memorias_TallerMunchique_12-12-2017.pdf |
| Project Results Framework Workshop | Cali, December 14, 2017 | Participatory development of the Project Results Framework, including SMART indicators | -Agua Clara Communal Council: Gilberto Montaño -Cuenca del río Acandí Seco, El Cedro y Juancho (COCOMASECO) Communal Council: Efraín Ballesteros Santa Cecilia Communal Council: Rocío Bonilla -Cacarica Communal Council: Luis Guillermo Chaverra --ASOCASAN: Jefferson Quinto RECOMPAS: Cesar Quiñones -Bajo Mira y Frontera Communal Council: Oberman Torres -ACIVA- Joaquincito -Reservation: Ligio Quiroz -Wounan Juin Phubuur Indigenous Community: Tilbaro Membache -Calle Santa Rosa Reservation: Carlos Quiro -Serraniagua: Cesar Franco -La Planada Reserve- Awá Reservation: Guillermo Cantillo -San Cipriano Foundation: Lida Riascos -FELCA: Laura Ruíz Florez and Cristian Florez | PNN, IIAP, UAO, INVEMAR, FAO, UNIDO, BIOINNOVA, CBS, MADS, ONF Andina, WWF, CODECHOCO, Visión Pacífico Sostenible, CARDER, Corponariño, Gobernación del Choco, CVC, Gobernación de Nariño. | ..\Memorias eventos - proceso formulación\Listas de asistencia - Anexo 8\Taller MML- Diciembre 14-15 de 2017\Memorias taller Construcción participativa- Dic 2017.pdf |
| Validation and consensus workshop | Cali, April 4-5, 2018 | Technical exercise involving the participation of institutional, community, and CSO stakeholders around validation and consensus of the project-specific actions for the four components and implementation arrangements in each MUCB | Agua Clara Communal Council: Gilberto Montaño Santa Cecilia Communal Council: Rocío Bonilla Cacarica Communal Council: Luis Guillermo Chaverra -ASOCASAN: Jose Aristarco Ríos Bajo Mira y Frontera Communal Council: Paterson Arboleda and Lidoro Hurtado. -ACIVA - Joaquincito Reservation: Ligio Quiroz -Calle Santa Rosa Reservation: Carlos Quiro -Serraniagua: Cesar Franco -La Planada Reserve-Awá Reservation: Guillermo Cantillo - San Cipriano Foundation: Lida Riascos | PNN, IIAP, INVEMAR, FAO, UNIDO, BIOINNOVA, CBS, MADS, CODECHOCO, CARDER, Corponariño, CVC, Departmental government of Chocó. | ..\Memorias eventos - proceso formulación\Listas de asistencia - Anexo 8\Listado asistencia - taller de concertación y validación - proyecto GEF Pacífico- Abril 4y5 de 2018.pdf |

Additionally, with the objective of holding bilateral meetings for project and implementation and co-financing arrangements and managing of contra-accounts resources and articulation with plans, programs, and projects, meetings were held with territorial entities (CARs with the departmental governments of Nariño, Valle del Cauca, and Choco; the mayoral office of Buenaventura; PNN, Sustainable Pacific Vision program; MADS; INVEMAR and IIAP) and ethnic communities (representatives from communal councils of the indigenous reserves and black communities). These meetings enabled more direct relationships among the project partners and clarified the actions to be developed in each MUCB.

Project implementation stage. Implementation of the project actions will ensure respect for peoples’ autonomy to manage their territory and their right to effectively participate in the decision-making processes considering the regulatory framework for protecting the rights of these communities as the FPIC. These actions will consider the use and traditions of each community involved and the respect for their own governance structures and decision making structure. Therefore, it is necessary to generate participation and agreement for each MUCB action plan.

The relevant FPIC steps that are to be carried out at project implementation stage are:

- Communication plan for project development (participatory communication plan);

- Intervention plan for each MUCB designed in a participatory manner;

- Participation agreements with local beneficiary communities for the intervention plan per MUCB with their corresponding feedback and grievance mechanisms;

- Participatory monitoring and evaluation of the participation agreement with local communities;

- Documentation of lessons learned.

Within the project framework, a communication plan will be designed to transparently involve local communities that are beneficiary partners and allies of the project in the implementation process, the project activities, direct and indirect intervention areas, and project progress (Output 4.1.3).

The plan will respect customary protocols and dynamics, including verbal and non-verbal communication standards. All due efforts will be made to ensure that, the plan and all project-related information are transparent, complete, easily accessible (i.e., will be available and accessible for the participating stakeholders), clear, suitable, and easy to understand by local beneficiary communities.

Communication content, media, and modalities will be defined respecting the guidelines provided by the involved communities and will be stated in the participatory agreements for the intervention plan in each MUCB.

The design of the communication plan will employ strategies, means, modalities, and mechanisms for the traditional transmission communication as well as new trends and technologies for disseminating the project information.

The communication actions to disseminate, make aware and move communities, government, authorities, officers, organizations and general community will have as their objective to generate public awareness and interest, so that they may take favorable positions about the project implementation. In addition, the project will establish an effective communication procedure with the representatives of ethnic beneficiary communities throughout the different phases of the project and will conduct effective iterative discussions by agreeing on the place and time for such discussions and transmitting to the communities their right to decide about actions in their territory. The project will document the procedures and outcomes and make them publicly available.

Furthermore, during the implementation stage, the project will implement effective mechanisms of coordination among all the stakeholders participating in the project to achieve the participation of ethnic and local communities in each project stage and in the decision-making processes. To that end, a project Directive Committee, a project Technical Committee, and technical committees per MUCB were created, which will have the representation of institutional partners and representatives of black and indigenous communities. The project implementation unit will supervise the participatory process of local beneficiary communities and will take the operational and administrative responsibility to facilitate stakeholders’ participation, including women, to ensure the appropriation of the project outcomes.

The MUCB action plans will be designed through the participation spaces and mechanisms aimed at effectively incorporating the participation of traditional authorities and representatives of local beneficiary communities. In this way, through their traditional knowledge, political, and administrative structures and territorial context and priorities, they contribute with ideas and inputs to define the intervention lines in each MUCB.

These plans will recognize and respect the wisdom, traditional practices, and traditional knowledge systems of the various peoples and territories of the Pacific region around biodiversity use, management, and conservation. They will also respect sacred places and safeguard that the actions to be implemented do not affect or impose restrictions on their traditional uses and practices. The plans will state how the information exchange and consultations will be conducted using culturally appropriate means.

Within the framework of the plans for intervention, voluntary agreements will be signed with entities participating in the project such as implementation agencies, MADS, PNN, SIRAP Pacific, CARs, research institutions, CSOs, educational institutions, and representatives of local beneficiary communities.

Based on these voluntary agreements, bilateral participation agreements will be reached with each communal council and indigenous reservation wherein the component activities to be implemented will be described.

The project recognizes the traditional authorities and representatives of reserves and communal councils and their own structures and systems to make decisions to reach participatory agreements of ethnic communities in the action plans of each MUCB. The project will contribute to strengthening the traditional authorities or representatives’ capacities to make decisions and conduct the appropriate monitoring of the MUCB intervention plan implementation.

The voluntary agreements with ethnic and local communities shall contain:

- Signatory parties and/or customary practice to seal the agreement

- Summary of the project information and implementation agencies

- Proof of consensus

- Social and environmental benefits for communities in the territory

- Commitments taken by the participant institutions in activities implementation

- Communication agreement

- Mechanism agreed to for feedback, reporting of grievances, and how to address them

- Monitoring and evaluation plan

The activities shall consider the linking of staff appointed directly by the communities to gather information in order to safeguard access to the territory and ensure recognition and respect for communities’ traditions, practices, and dynamics.

Another important issue is the development of competencies and skills of the project operations staff to promote the recognition of ethnic and cultural diversity in these territories by using strategies and methodologies that are suitable to the proposed approach.

Monitoring of the participatory agreements will be conducted by the communities and their authorities, thereby respecting their own organizational modalities and specifying their own variables and indicators for indigenous participation.

All the project actions will consider the ethnic-cultural particularities of indigenous peoples and black communities inhabiting the MUCBs, by promoting dialogue and exchange of technical knowledge and traditional and ancestral knowledge, thereby fostering the full and effective participation of the various communities in the validation, development, implementation, monitoring, and evaluation of the project, and respecting their expressions, values, and sociocultural traditions.

The project will facilitate a grievance mechanism within the FPIC framework to address requests for information and enable the local beneficiary communities and participating entities to submit claims, complaints, and suggestions to ensure the accomplishment of the project safeguards, and respect for the communities’ rights (see Section 3.2.4).

During the final stage of project execution, a document detailing the lessons learned will be generated by which the project learning’s will be communicated in both the development and implementation stages, as well as the processes developed jointly with the communities, and the institutional framework supporting the project execution within the different MUCBs. This document will gather the joint learning of the implementation agencies FAO and UNIDO and their partners in the territory during the project execution.

## APPENDIX 10. DETAILED CARBON CALCULATION

Methods

Estimate of potential carbon stocks in the Pacific forests. To estimate potential carbon reserves in the natural forests of the Pacific, the average biomass estimated by IDEAM (2014) for each type of forest according to the Holdridge life zones classification system was used. Based on this information, the average biomass of the Pacific forest was calculated. Subsequently, the confidence interval for the biomass was estimated, and the lower limit for estimates of potential emissions reduction was used, in order to be conservative. To convert the values of biomass to carbon, a factor of 0.47 was used following national protocols (IDEAM, 2014). Finally, the underground or root biomass was estimated using the pantropical equation developed by Cairns et al. (1997) (BR = exp (-1.085 + 0.9256 ln BA, where BR is the root biomass, BA is the biomass).

Estimate of potential carbon stocks in other land uses. According to IPCC (2006) recommendations, the change in biomass is only estimated for perennial woody crops and pastures. For annual crops, the increase in biomass stocks in a single year is assumed to be equal to biomass losses from harvest and mortality in that year; therefore, there is no net accumulation of carbon stocks in biomass. In this regard, this year, the content of carbon in post-deforestation land use was obtained using a combination of factors from the guide of good practices by the IPCC (2003), and the literature review, using values reported for sites with similar characteristics. In addition, and bearing in mind the lack of information in many cases, the average value was increased by 30 per cent. This is in order not to overestimate emissions from deforestation (Pedroni, 2012).

Estimate of carbon sequestration by restoration activities. To determine the accumulation of carbon, conventionally the average annual increases of carbon (IMA) or growth curves by species/ecosystem are used. Such procedures are considered to be good practices according to the IPCC (IPCC, 2003). For estimates of potential capture from restoration activities in the life zone of very humid tropical forests (bmh-T), a curve was constructed using data from secondary sources regarding storage potential and Mean Annual Increment (Tosi, 1981). The von Bertalanffy model that is found in Equation 1 (von Bertalanffy, 1976) was parametrized, using the method of mathematical approximation.

C = A[1-exp(-bt)] 1/(1-m)		(1)

Where C is carbon (t ha-1), t is time (years) and A, b and m are parameters of the equation. The term exp denotes the exponential operator and A is the asymptote or maximum amount that can reach the body with the progress of time, which controls the maximum rate of growth of the species. This model suggests that the body anabolism rates are proportional to its raised mass elevated to the power 2/3, while catabolism is only proportional to mass. Therefore, the parameter m in the Bertalanffy model is 2/3 (Zeide, 1993). In cases where this model is used, this constant was assumed since it has been observed empirically that this value can estimate conservative asymptotic values, so the iteration process of the other parameters is facilitated and makes the term 1/1-m, and it becomes a constant term c = 3.

Estimate of the emissions derived from the avoidance of deforestation. Estimates of emission reductions are based on lower rates of deforestation in the project area, according to the estimated rate, which in the case of this project is based on historical analyses of deforestation in the Pacific region. As well, the project should consider in its accounts emissions resulting from the implementation of project activities. For these calculations, some equations proposed by the IPCC, which are recommended in the VM0015 methodology of the VCS, were taken as a base given that the draft sustainable forest management would be implemented in areas where deforestation is unplanned.

Outcomes

Estimate of potential carbon stocks in the Pacific forests. The average biomass for the Pacific forests is 280.36 ± 14.11 t ha-1. For these estimates, the value of the lower limit, that is, 266.25 t ha-1 was used; this value is enclosed to that reported in other studies (Quinto & Moreno, 2011), and even in two of the BioREDD projects (Cajambre and Mutatá). Regarding ground biomass, the value obtained was 59.38 t ha-1, for a total biomass of 325.63 t ha-1, corresponding to 561.17 t CO2e ha-1, the value used for estimating the potential for emissions reduction.

Estimate of potential carbon stocks in other land uses

- According to the review and applying the 30 per cent adjustments, carbon content related to other forest cover/land use changes were as follows:

- Forests to Agricultural Areas: 12,88 t CO2e ha-1.

- Forests to Pastures: 7,11 t CO2e ha-1.

- Forests to Shrub Vegetation Areas: 20,12 t CO2e ha-1.

Estimate of carbon sequestration by restoration activities. According to the review, the restoration of one hectare of tropical wet forest (bmh-T), can reach an average annual increase of 4.5 t C ha-1. Thus, one restored hectare could eventually hold around 61.92 t C. That is, if the project restores 1,000 hectares a total of 10.646,27 t CO2e could eventually be captured in the 4 years of restoration implementation, minus the 30 per cent buffer related to risks (natural, financial, etc.).

Estimate of emissions from deforestation avoidance. To estimate the avoided emissions the following assumptions are considered: i) the rate of historical deforestation in the region is about 1 per cent according to IDEAM studies and reports (2011); ii) sustainable forest management activities will result in a 40 per cent reduction during the first 5 years and then 30 per cent for years 5-10 and 30 per cent for years 10-15; iii) taking into account the complexities of the implementation of these activities, a buffer of 30 per cent will be considered, that is, a discount to the reduction potential, based on the potential risks that may arise; iv) the project area was estimated at 602,811 ha; v) only CO2e emission reductions were considered; vi) a 4-year project was considered; and vii) the application of significant amounts of chemical fertilizers was not considered, so no input values of this type are considered. Thus, it was found that the project would have a potential to reduce emissions by avoiding deforestation of 3.590.056,88 t CO2e. It is recommended that once implementation begins, the calculations should be reviewed and updated, considering a prudent time lapse between the submission of this project document and its approval.

Total Emission Reduction: 3.600.703,15 t CO2e. That value included conservation area plus restoration area.

## APPENDIX 11. METHODOLOGY FOR THE SELECTION OF THE PROJECT INTERVENTION AREAS

The objective of the multicriteria analysis was to identify the MUCBs with higher potential to integrally implement the project and achieve favorable results; the multicriteria evaluation was based on five principles:

- Enabling the integration of the four project components;

- Presenting potential and feasibility to achieve the results;

- Availability of baseline information or ease of generating it;

- Allowing assigning values to each criterion;

- Be flexible to enable the inclusion, elimination or modification of criteria or assigned values in subsequent stages.

Based on these principles a priority index was developed with maximum score of 1,000 points grouped into two components: i) potential, and ii) feasibility. The components integrated key criteria for the project, which are shown in the following figure.

A maximum score to be obtained was assigned to each criterion. The component of potential included those criteria directly related to the project objectives regarding key matters such as sustainable production, restoration, and opportunities for conservation  (PAs and CCSs).

| COMPONENT | CRITERIA | DESCRIPTION | SCORE | SOURCE |
| --- | --- | --- | --- | --- |
| POTENTIAL | Deforestation | Deforested surface (% hectares vs total) | 20 | IDEAM, MADS, 2016 |
|  |  | Deforestation sources (cores) |  |  |
|  | Opportunities for conservation | Potential for declaration of new PAs | 20 | SIRAP Pacífico |
|  |  | Presence of complementary conservation strategies CCSs |  |  |
|  | Sustainable production systems | Initiatives associated with green business | 20 | CAR – PNV, PNM 2016 - 2019 |
|  |  | Biodiversity products with use potential |  |  |
|  | SPV Municipalities/Post conflict | Municipalities prioritized by Sustainable Pacific Vision, CONPES 3850 de 2015 and PDET | 10 | Office of the high Post conflict commissioner /Sustainable Pacific Vision program |
|  | Vulnerability |  | 10 |  |

The component of feasibility was focused on evaluating and prioritizing the MUCBs having higher safety and accessibility conditions; in addition to the articulation with other international cooperation initiatives in the MUCBs.

| COMPONENT | CRITERIA | DESCRIPTION | SCORE | SOURCE |
| --- | --- | --- | --- | --- |
| FEASIBILITY | Safety | Number of violent events reported for the municipalities making up each MUCB. | - | NNUU (monitor umaic. Org) |
|  | Access | Access roads/costs | - | Access roads connectivity and proximity to intermediate cities and municipal township/connectivity |
|  | Complementarity with other initiatives or international cooperation projects | Municipalities having international cooperation projects as per the President Agency of International Cooperation of Colombia | 10 | APC. Cooperation projects map GEF |

Therefore, and as an example of score assigning to each criterion, if the MUCB had potential for the creation of new PAs and at the same time it has an CCS, the maximum score achieved is the maximum score for such criteria (20 points), if it only has one of the two options, the score would be 10 and if it does not have any option, the score would be 0. The following table shows the values assigned per MUCB and criterion.

| MUCB / criterion | Deforestation | Opportunities for conservation | Sustainable production systems | SPV Municipalities, Post conflict | Vulnerability | Other projects | Total |
| --- | --- | --- | --- | --- | --- | --- | --- |
| KATIOS-CAOBA | 20 | 20 | 20 | 10 | 10 | 8 | 88 |
| FARALLONES-CALIMA | 15 | 20 | 20 | 4 | 8 | 6 | 73 |
| CABO MANGLARES-LA PLANADA | 20 | 18 | 10 | 7 | 5 | 2 | 72 |
| MUNCHIQUE-FARALLONES | 10 | 20 | 20 | 9 | 4 | 8 | 71 |
| SERRANIA PARAGUAS-TATAMA | 10 | 20 | 20 | 6 | 6 | 7 | 68 |
| UTRIA-BAJO BAUDO | 10 | 20 | 20 | 7 | 5 | 5 | 67 |
| PIEDEMONTE ANDINO PACIFICO | 10 | 16 | 20 | 8 | 4 | 1 | 59 |
| URAMBA-BAHIA MALAGA | 10 | 18 | 5 | 10 | 6 | 10 | 59 |
| SANQUIANGA-GORGONA | 10 | 12 | 10 | 9 | 4 | 1 | 46 |

Finally, by applying the multicriteria evaluation exercise, five of the initially nine proposed MUCBs were prioritized, which were validated during the PPG inception workshop. Likewise, the integrated project intervention was agreed for three MUCBs and partial intervention for two MUCBs as follows:

## APPENDIX 12. ANALYSIS OF POTENTIAL BIODIVERSITY-DERIVED PRODUCTS

Products derived from biodiversity include goods and/or services obtained through the sustainable use of native and/or cultivated biodiversity. These goods include products extracted from the wild and agro-biodiversity crops. Services include nature-based tourism.

The Colombian Pacific region boasts a wide range of biodiversity, a wealth of water resources, and the presence of indigenous groups in an environmentally favored location within the Pacific basin. These characteristics provide great production, environmental, and social potential to be tapped in the region. Despite it being one of the most diverse regions in Colombia, the Pacific region has the highest level of inequality and poverty; directly correlated with this is the deterioration of ecosystems that are the bases of local livelihoods. These conditions, coupled with the vulnerability of ecosystems that are essential for local communities in the face of climate change, highlight the need to promote environmentally friendly production systems so that the region’s inhabitants have better opportunities through alternatives to illegal or environmentally unsustainable activities that will degrade the region’s natural capital.

A study performed within the framework of the GEF project Conservation of Biodiversity in Landscapes Impacted by Mining in the Choco Biogeographic Region analyzed non-timber forest products (NTFPs) that are used in the Pacific region, as well as their relationship with production initiatives and their incorporation into the value chain. There are 53 NTFPs in the region produced under production initiatives that generate different levels of income in the area of study. These products include: achiote, jagua, asaí, mil pesos, chontaduro, coconut, cocoa, borojo, coronilla, badea, tagua, pipilongo, and vanilla, among others.

There are several production initiatives based on biodiversity within the Pacific region; in the project’s area of influence there are 77 production or green business initiatives that are either formal or remain informal, which generate goods and services based on the diversity present in the municipalities of the three main MUCBs (Katíos-Caoba, Farallones – Calima and Cabo Manglares –Gran Familia Awá).

These products are based on the communities’ traditional knowledge and their use for the communities’ subsistence, as well as the establishment and transformation of some products for local and global trading.

Katíos – Caoba MUCB: The initiatives identified were mainly related to cocoa, banana, rice, and manioc. The legal enterprises identified were producers’ associations, communal councils, and indigenous resguardos.

Farallones – Calima MUCB: The p initiatives identified were mainly related to cocoa, naidi, chontaduro, borojó, coconut and small banana; other products were also reported as breadfruit tree, medicinal plants, papachina, pineapple, citric fruit, vanilla, achiote, and organic panela cane sugar.

Cabo Manglares – Gran Familia Awa MUCB: The products reported for this MUCB were mainly cocoa, oil palm trees, naidí, and fruit.

Generally, although there are business initiatives based on biodiversity products use and transformation, there are few transformation and value addition processes. Mostly, the production initiatives identified are small-scale with restrictions to market access and insufficient technical and management capacity.

In general, three large product groups were identified in the MUCBs: colors, oils and fats, and food. There is a fourth group related to medicinal uses which, although it was identified, it was not considered as extensive research and technological efforts are required to have access to the market.

| Oils and fats |  | Food |  | Colors |
| --- | --- | --- | --- | --- |
| Cocoa (Theobroma cacao) |  | Cocoa (Theobroma cacao) |  | Achiote (Bixa orellana) |
| Chontaduro (Bactris gasipaes) |  | Chontaduro (Bactris gasipaes) |  | Jagua (Genipa americana) |
| Coconut (Cocos nucifera) |  | Coconut (Cocos nucifera) |  |  |
| Guerrege (Astrocaryum standleyanum) |  | Vanilla (Vanilla planifolia) |  |  |
| Noli (Elaeis oleífera) |  | Asai (Euterpe oleracea) |  |  |
| Asai (Euterpe oleracea) |  | Borojó (Borojoa patinoi) |  |  |
| Cabecinegro (Manicaria saccifera) |  |  |  |  |
| Don Pedrito (Oenocarpus minor) |  |  |  |  |
| Mil pesos (Oenocarpus bataua) |  |  |  |  |

The identified groups are part of the natural ingredients sector, which can be used in the cosmetics, food, or pharmaceutical industry.

Colors group: In this group three potential species were identified: achiote, chontaduro and jagua. There are some initiatives in Colombian Pacific region for these products, which have experience in transformation experience and, in some cases, periodic trading. However, these initiatives have not had much success because of problems with regulation, supply, and distribution of benefits.

The global trend for colors is to use natural products with no artificial preservatives or other ingredients. This leads to significant demand and the diversification of uses in different industry sectors. Natural colors commonly used in the food industry are: carotenoids that are yellow and are oil-soluble pigments; bell pepper, which is found in red peppers (Capsicum annum); beta-carotene; long turmeric, which is yellow-golden in color; and achiote extract in oils extracted from Bixa orellana. The bixin color corresponds approximately to 70 percent of the natural colors market, and 50 percent of all the natural ingredients that are used in food coloring.

Currently, the extraction processes of colors from plants in the areas of indirect influence of the project’s MUCBs has been led by the companies of cities that buy raw materials from the producers or create joint projects to achieve long-term supply.

Although a market potential has been identified for natural colors at the local level and for export, a business model must be created to be economically feasible and with competitive pricing in comparison with artificial colors, which if developed with a fair trade component established through the joint production with traditional communities, may favor the project’s initiatives.

Oils and fats group: In this group the palm trees of the Pacific region have been identified as potential products, including naidí, coconut, chontaduro, and mil pesos; however, other species such as cocoa are also included.

Colombia is the second country after Malaysia that has the highest diversity of palm tree species, with a total of 252 species divided into 45 genera. Of the 252 species, 161 are reported to have some type of use, demonstrating that this family represents one with the highest use reported (fibers, construction, food, oils, among others). Specifically, for the Colombian Pacific region, a total of 94 palm species are recorded, 16 of which present some degree of threat.

In the study “Uso de las palmas en las tierras bajas del pacífico colombiano” (Ledezma & Galeano, 2014), which was conducted to evaluate traditional knowledge about the use of palm species in the Colombian Pacific region to guide future research and define general use patterns in the region, informational sources were studied that document the traditional uses in this region. Ninety types of use were recorded for 52 species of useful palms in the Pacific region, which equates to 61 percent of palms growing in the region. Uses were grouped into eight use categories and 30 subcategories; the most important use categories were construction, utensils and tools, and as human food. The species with the highest use were Astrocaryum standleyanum, Oenocarpus bataua, Euterpe oleracea, Oenocarpus minor, Cocos nucifera, Attalea cuatrecasana, Iriartea deltoidea, Desmoncus cirrhifer, and Wettinia quinaria.

In the cosmetics sector, natural oils and lipids are used for various purposes such as emollients, as they provide smoothness and flexibility due to moisture retention and the interaction between the skin and the cosmetic lipids; as lubricants and adherents, in addition to gloss and the pigmentation valued as important benefits of using lipids in cosmetic products. Some oils derived from biodiversity also have non-lipid fractions that may contain bioactive elements that benefit skin. These benefits may be very varied and, in general, traditional populations already using these products have traditional knowledge that may be used by the cosmetic industry.

It is important to demonstrate that communities know which products can be feasibly extracted; however, they do not do it because of lack of knowledge in some cases, in others, because of a lack of machinery associated with transformation. However, the main reason is because the market has not demonstrated to them that this can be a segment that reduces the main disadvantage in the areas that are associated with high transportation costs.

The challenge is to make the production chains for these species economically viable in comparison with oils and fats derived from African palm, soy, sunflower, or canola. Plant oils from community-based production chains will be differentiated by socio-environmental features in line with the sustainable strategy of big buying companies, the diversity of industrial uses for their products and by-products, or biotechnological innovation to develop unique active bases and functional ingredients that cannot be found in imported oils.

Food group: The products identified for this group are naidí, chontaduro, coconut, vanilla, achiote, and borojó. This is the most important group for local economy, is mainly used for feeding the families themselves, are exchanged as barter with neighbors, and the surplus is sold without needing to bring them to the market. In general, the people of the community know who extracts these products and at harvest time they search for best and cheapest products. These products can be brought to the market as fresh fruit; however, the production potential in the areas enables people to plan the commercialization of products such as marmalade, juices, preserves, dry fruit, pulp, sweets, etc. There are initiatives that transform borojó into pulp, and for the sale of vanilla in the departments of Chocó and Antioquia for use in ice cream in Bogotá. Chontaduro is transformed into snacks and dehydrated coconut and can be found in several cities in the country.

A critical stage in developing the market for biodiversity-derived food and products is to increase the added value of the Pacific region products. A possible strategy would be specialization to occupy niches in certain markets as there is a growing demand, at least in developed countries, for environmentally and socially suitable products.

Based on the diversity of products found in the Colombian Pacific region and considering their potential for transformation as natural ingredients, particularly for food and cosmetic industries, products have been identified for technical knowledge, INCI or CAS registrations, with data and/or reports about the supply in the project areas of influence, that can be obtained by sustainable extraction from the natural environment or through cultivation, and are linked to initiatives associated with such products.

There are companies in Colombia that are producing and commercializing natural ingredients, including: Neyber, Phithoter Laboratories, Medick Laboratories, Waliwa, Lafarve Laboratories, Tropicoil, Organic evolution, Ecoflora cares, Sanadores ambientales, Green Andina, Bioprocol, ECHZ, Kahai, Asai de Colombia, Tecnas, QyB, Disaromas, Farmaverde, Selva Nevada, Esencialife, among others. To date, three of these ingredients companies are authorized to access genetic resources for their commercial purposes: Ecoflora Cares, Bioprocol, and Cosmos International Ingredients.

In the list of natural ingredients to supply the cosmetics industry through the Colombian market, the following products from seeds, flowers, fruit and pulp and species are highlighted: jagua, achiote, turmeric, sacha inchi, asai, balu, chontaduro, inchi, copoazu, aloe vera, prontoalivio, rosemary, calendula, chamomile, and tropical fruit such as maracuyá, tamarindo, borojó, lulo, among others.

Limitations and potentialities for the identified biodiversity products are as follows:

There a set of problems associated with the development of products of the Pacific region related to production, transformation, transportation, and commercialization. In terms of production, the products are traditionally used for food security and local consumption, so the communities have not considered the need to develop initiatives based on these products; therefore, this has not been seen as an opportunity for a real increase in income. Likewise, the production is made in a traditional way and according to the communities’ knowledge about the species; they do not have technical guidelines or qualified labor in specialized tasks that allow more effective production.

Currently, the groups in the community that have been dedicated to transformation have encountered a series of difficulties that includes the humid conditions in the Pacific region, which make some products’ transformation difficult. In addition, the technical capacity in managing the processing plants that are installed have generated important economic losses, mainly associated with cooperative projects. Although the areas that are the farthest from the municipal townships have the highest diversity of natural extraction and cultivation products, transportation to the processing plants is difficult and expensive.

Even if difficulties in production and transformation are overcome, there is a third group of problems associated with transportation; the principal means of transportation in the Pacific region is river transport, which involves several considerations: first, the possibility of moving products depends significantly on climate factors; second, the cost of fuel in the Pacific region is approximately of $15.000 COP per gallon (USD $5.00 per gallon) in rural zones, equating to 60 percent of extra charges. When this is compared with cities such as Bogotá, Cali, and Medellín, the Pacific region’s competitiveness of products in the market is decreased.

With regard to commercialization, generally the projects involve development from production to commercialization, making important efforts to organize the communities; however, when the communities do not achieve sustainable commercialization processes, they become unmotivated and abandon the effort. In the same way, despite the variety of products associated with the presence of forests in the Pacific region communities, the fact that they are produced in the wild restricts the possibility of bringing them to markets that require a constant supply.

It should be highlighted that the project’s approach focuses on creating economic development models that enable the communities to produce and become suppliers to a transformation plant using a self-sustainable management model and associated market. As such, the project will utilize the lessons learned from other projects carried out in the region and the experience of partners in an effort to minimize risk.

There were some restrictions encountered for the selected species:

- For cocoa, the main difficulties are price fluctuation, low transformation, high transportation cost because of the difficulty in transformation processes; in addition, the lack of INVIMA registration sometimes limits access to the market.

- For asaí or naidí, there are management plans for natural use; however, inventories of natural populations were not found.

- For coconut, the main difficulties are pests and associated diseases, improvisation in transformation, and the lack of technological knowledge to generate added value.

Opportunities associated with the selected species are derived from biological and cultural conditions that transform this region into a territory with huge potential to establish businesses using biodiversity in a sustainable way, contributing not only to improving the life quality of local communities but also to ecosystems conservation. Currently, the region is characterized by cultural diversity as a result of the different inhabitants throughout the territory and the ancestral knowledge associated with biological diversity and their adaptation processes to the natural environment. Their traditional knowledge constitutes a tool for communities to recognize and use natural products existing in the territory, which jointly with the application of guidelines for their sustainable extraction, will contribute to reducing pressure on biological diversity and ecosystems.

Current social and organizational processes are identified in the region through which ethnic groups generate demands through alternative projects for natural resources management.

Development of production initiatives that sustainably use natural products represents an opportunity for the communities to generate income and, therefore, improve the living conditions of the beneficiary families. It is important to emphasize that there are initiatives already in process for the priority species. The project will seek to strengthen these processes so that they become a real source of income through accessing to markets beyond the local scope.

There are also institutional guidelines that favor the implementation of production initiatives around biodiversity sustainable use. This framework includes the National Green Business Plan (PNNV), which is the result of the joint effort by the Ministry of Environment and Sustainable Development (MADS), Regional Autonomous Corporation (CARs), research institutes, producers, and public and private entities related to green business in the country, whose purpose is to define guidelines and provide tools for planning and decision making that promote both supply and demand for green and sustainable businesses in the country.

Likewise, the previous identification of business models with high success rates and potential for replication in the project influence area and in other territories (even at a small scale) supports the development of the component, which is on-the-ground recognition of biodiversity products. Along these lines there is a proposal for product groups associated not only with production but also with cost, research, innovation, and potential markets that serves as a support to the proposal proposed herein during the five years of project duration and beyond.

A summary of commercial uses and products of the selected market species follows.

| Species | Commercial use | Products in the market |
| --- | --- | --- |
| Cocoa (Theobroma cacao) | The most common commercial uses of cocoa are cocoa powder, butter, and liquor, to which health benefits are attributed, highlighting the presence of polyphenols in the grain that are bioactive compounds with antioxidant properties that reduce cancer risk, cardiovascular, and neurodegenerative diseases. | The most common products derived from cocoa in the market are: Butter: it is the fatty component of cocoa. It is also known as Theobroma oil. It is used in the manufacturing of cosmetic and pharmaceutical products. Cake: it is the solid phase of cocoa liquor. It is used in the elaboration of chocolates; and Powder: the cake can be pulverized and become cocoa powder. Cocoa powder is basically used to provide flavor to cookies, ice creams, beverages and cakes. Likewise, it is used in the production of toppings for confectionary and frozen desserts. Cocoa powder is used in the beverages industry, for example in the preparation of chocolate shakes. |
| Chontaduro (Bactris gasipaes) | The fruit is consumed fresh and cooked, its pulp is used for manufacturing flour and preserves, and its bud is used to obtain palm hearts. Its fat is of interest to the cosmetic industry for manufacturing cosmetic bases (Carrillo et al., 2016). | The main product from chontaduro are chontaduro in brine, syrup, and preserved palm hearts. Products such as flour, marmalade, and preserves are developed from artisanal processing (Godoy, Pencue, Ruiz, & Montilla, 2007); however, both direct consumption and processing create big volumes of wastes (husks), whose agroindustry potential has not been evaluated in most cases (Pinzón et al., 2015). These wastes are normally discarded or used for animal feeding (Perea, Martínez, Medina, & Hinestroza, 2013). Other researches refer its use for extracting oil by using pressurized carbon dioxide (Pasquel & Castillo, 2002). |
| Coco | Coconut is traditionally used as food, beverage, and cosmetics through its oil. | Currently in the market the following products are found, among others: coconut water, oil, flour, butter, chips and dehydrated fruit. Most of them are used in the cosmetic and food industries. |
| Achiote (Bixa O orellana) | It is mainly used as food condiment since it is useful to color food. It is also used as raw material for manufacturing cosmetics, repellents, varnishes, tattoos, and for decoloring ceramics and textiles. Oil extracted from seeds is the main source of bixin and norbixin pigments classified as carotenoids. Tea developed with small stems and leaves is used as anti-dysentery, aphrodisiac, and astringent, and to treat skin infections, fever, and hepatitis. Extracts of ethyl alcohol from fruit and leaves have shown in vitro activity against Escherichia coli and Staphylococcus aureus. Adhesive: from the branches a gum is obtained similar to Arabic gum. | In relation to Bixa orellana patents, they are divided into five main categories: medical, dental, or cleaning preparations; microorganisms or enzymes, compositions of them and repellents; new plants or procedures to obtain them; specific use for cosmetics or toilette products, and food products or non-alcoholic beverages. |
| Asai (Euterpe oleracea) | In the Pacific region the species of interest is Euterpe oleracea and its use shall be mainly oriented to the use of the fruit. The fruit is mainly consumed as pulp, from which food functional products such as juices, nectars, dehydrated products, ice creams and snacks are obtained, among others (Carrillo, et al., 2016). The palm bud is used as palm heart and its pulp may be considered to extract pigments; oil from the fruit is used in food, cosmetic and nutraceutical applications (Carrillo, et al., 2016). Seeds are a source of polyunsaturated and saturated fatty acids. | There are various Euterpe oleracea products with International Nomenclature of Cosmetic Ingredients (INCI) code and special certifications. In the food sector (fruit extract that acts as anti-aging, antioxidant, and nutritive agent) it is represented by pulp, freeze-dried products, and beverages. For cosmetic use, ACAI ECO of Provital, Euterpe Oleracea Fruit Extract. Acai Powder by Green Source Organics, Extrapone® Acai, Acai Berry Oil, Neo Actipone® Acai, Acai Pulp Oil, Acai Extract Powder, BioNatural® Acai Powder, acai seed exfoliant, Exfoliant Guaraná + Açaí, Açai Butter–certified Organic, Euterpe oleracea Fruit Extract, which stands out as an antioxidant, exfoliant, anti-aging, vein tonic, protector, restorative, and nutritive agent. |
| Borojó (Borojoa patinoi) | Traditionally, borojó has been conceived as a fruit with aphrodisiac, medicinal, healing and nutritional properties in beverages and pulp. | In the market there are assorted products from borojó: pulp, juice, fresh fruit, candies, preserves, sauces, balsamic-type vinegar, energizing jelly, infusion beverages, liquor, shampoo, hair products, and cosmetic products. |
| Jagua (Genipa americana) | This species is used as wood and natural coloring for food, cosmetics (tattoos, colors for hair), and personal care industries; and as potential use in sunscreens. Additionally the flowers are used for their aromatic properties and to extract essential oils. Fruit is edible when unripe and the fruit pulp can be consumed as preserves and candies. | Jagua is transformed into products as powder with attributes such as blue dye, liquor, tattoo henna, and gel. |

Nature-based tourism

Tourism is a sector that has been growing at the global level. According to statistics from the Colombian Association of Travel Agencies and Tourism (ANATO), the year 2017 was reported as a very positive year for the tourism sector, which became the second highest sector for generating income in the country. Between January and September 2017, USD $4.698 million was generated by the tourism sector, which is an increase of 7.4 percent in relation to the same period in 2016. For Colombia, in 2011, 260,688 tourists’ arrivals were reported for purposes of nature-based tourism, representing 16 percent of the total number of tourists.

The Colombian Pacific region has particular elements that differentiate it from other regions of the country with regard to nature-based tourism; these are as follows: (i) the combination of natural particularities (dense forests, wealth of water resources, coastal areas with strategic ecosystems such as mangroves and oceans that are rich for fishing) and cultural wealth that is principally represented by the presence of the indigenous peoples Embera, Wounaan, Katío, Chamí, Tule, Zenú of Chocó in the north and Awa in the south, and black communities; (ii) the appropriation (ancestral territories) and organizational modalities for territorial management, such as collective property (indigenous resguardos and black communities’ collective territories) managed by cabildos and communal councils that organize the territory according to natural resource use; (iii) the cultural and political concepts of territory that implies an unbreakable relationship between nature and culture, and how these concepts ensure the permanence of the populations.

Sixty-five (65) projects were identified as relating to tourism with influence in the Pacific region, and are focused on the adaptation of roads, tourism infrastructure, tourist ports (Turbo, Capurganá), piers (Guapi, Tatémate, Bahía Solano), tourist villages (Chorí), jettys (Playa del Morro in Tumaco, Boulevard in Valle del Cauca, Quibdó), construction, equip of an auditorium, and walking trails in Utría NNP (Nuquí and Bahía Solano), as well as promotion and competitiveness strategies.

According to information provided by the President’s Office, during January and February 2018 the MINTIC began the execution of projects in the Colombian Pacific region with the development of training activities for developing business plans, education and training, designing of tourism products, development of tourist routes, and a commercialization plan.

Within the MUCBs, the following initiatives, plans, programs, and projects related to nature-based tourism were identified:

Katíos-Caoba MUCB

The number of visitors in 2014 was 12,630, with the goal of 94,421 visitors established for 2020 (MCIT, 2016). The Tourist Development Plan of Chocó 2016-2020 (MCIT, 2016) identifies the following key tourism products: whale watching, bird watching, wildlife and plant species observance, and diving; the goal is for the Chocó to be recognized as a nature-based tourism destination par excellence and to strengthen organized community tourism. The municipality of Acandí has great tourism potential, particularly in the coastal areas (municipal township, communities of Capurganá, Sapzurro, Triganá, and San Antonio). Acandí, Bahía Solano, and Nuquí become the three main tourism destinations in the department. The territory has large landscape scenarios such as Los Katíos NNP and El National Park, which operate ecological tourism, as well as beaches in the Golfo de Urabá coast, wetlands in Unguía and Marriaga, various rivers and streams, hot springs in the township of Balboa, the bat cave in the area of La Gloria, and livestock farms that represent places with unique beauty and that are ideal for relaxing and viewing nature.

Serranías Paraguas Tatamá MUCB

This MUCB has potential for specialized nature-based tourism, specifically related to bird watching and observance of wildlife and plant species. Tatamá NNP is characterized for its excellent conservation status and the presence of an unspoiled paramo, which is a protected area of great scientific interest and an intact natural refuge for many plant and animal species. The park connects to Serranía de los Paraguas and more than 50 civil society private reserves and two community reserves: El Inglés and Galápagos. During the Global Big Day on May 13, 2017, in Serranía de los Paraguas, 105 birds were recorded along one route. Cerro El Inglés is considered the largest natural reserve in Valle del Cauca and has been consolidated as scientific tourist and bird watching destination. In this area the endemic wildlife and species are identified as the Sapito de los Paraguas (Rhinella paragua): an endemic frog of the Colombian western mountain chain and which was discovered just over a decade ago in Cerro El Inglés, and the orchid Lepanthes yubartha.

Farallones – Calima MUCB

The tourism development plan for this MUCB outlines the development of the bird watching tourism product in Valle del Cauca, including the rural area of Buenaventura and the Farallones and Uramba Bahía Malaga NNP. The portfolio of tourism products for this MUCB includes whale watching, bird watching, and observance of wildlife and plant species. In the municipality of Buenaventura, tourist resources and attractions were identified as Alto Anchicayá, the Anchicayá “Néstor Córdoba Camacho” Special Natural Reserve, San Cipriano and Escaleretes rivers Forest Reserve, Málaga cove, among others. Alto Anchicaya is reported as one of the most prominent places for bird watching, characterized by its high rate of endemic bird species. Ornithologists and tourists can enjoy birds as rare as corbatudo (Cephalopterus penduliger) and roadrunner (Neomorphus radiolosus), as well as mixed flocks of multicolor tangaritas. Another area of interest for ecotourism in this MUCB is the San Cipriano Forest Reserve, where studies have been performed to design ecotourism routes The reserve encompasses 2.7 km of scenic viewpoints, a 120-meter-long suspension bridge, resting zones, and bird watching. It is important to mention that department of Valle del Cauca has an adequate transportation infrastructure for commerce and ecotourism: airports, one international sea port, train and a road network, all of which are in good condition.

Munchique – Río Saija MUCB

This MUCB has influence in the Munchique NNP, which is located within the jurisdiction of the municipality of El Tambo. In the park area, the "Wood-wren Munchique" was discovered, which is a bird species described as "new to science" in 2003. It has numerous mountains including Cerro de Munchique, which is 3,012 meters above sea level, therefore the principal ecosystem is the mountain forest.

Cabo Manglares MUCB

The strategic plan for tourism in this department highlights two characteristics of the Pacific area of Nariño: strengthening the tourism product of beach and sun in Nariño and strengthening the tourism product of whale watching. Likewise, the development of the “Route to Sea” is proposed, which is made up of municipalities of Mallama, Ricaurte, Barbacoas, and Tumaco. Municipalities with higher potential to develop products related to nature tourism are Tumaco, Ricaurte, and Barbacoas (Nariño). The municipality of Tumaco has high tourist potential for its wide diversity of geographic, cultural, coastal, maritime and river attractions as the tourist area of El Morro, in addition to many other existing attractions, which with its original beauty and the image of the “Natural Arch” in the center, constitutes a prominent area for tourism in the region. The municipality of Ricaurte has countless tourist, cultural, religious and historical attractions. The most representative location of nature tourism activity is La Planada Natural Reserve, which has infrastructure for providing lodging, restaurants, ecotourism-trained guides, and scientific research on environmental and ecological matters. In 2015, a total of 1,950 visitors entered La Planada NR (Municipal Development Plan, 2016-2019).

Considering the following criteria: i) suitability of the area and community interest; ii) presence of nature tourism initiatives currently operating that are led by or with community-based participation (communal councils, indigenous resguardos, native leaders, local communities, etc.); iii) incorporation into the tourist product of areas with interest for conservation (Important Bird Areas [IBAs], conservation corridors, civil society reserves, regional parks, etc.) and areas of sociocultural interest; and iv) infrastructure and basic tourist plant for operating, the MUCBs with the greatest potential to develop community-based nature tourism are: Katíos-Caoba, Farrallones-Calima and Tatamá; however, it is important to note that the proposed areas may be adjusted during the project implementation process.

## APPENDIX 13. GENDER MAINSTREAMING ROADMAP

The project will contribute to the incorporation of a differential gender approach in order to reduce participation gaps, guarantee women's empowerment and guarantee a fair and equitable distribution of the benefits generated by the project.

The incorporation of a gender perspective in the project is carried out in accordance with the FAO Gender Equity Policy, the UNIDO Gender Policy and the GEF Gender Strategy in order to guarantee equality between men and women in terms of effective participation and decision-making and to promote equity and recognition of women in the conservation, use and management of biodiversity. It is also developed in accordance with FAO safeguard 8 related to gender equity.

The project will also take into account FAO's Technical Guide to support gender-responsive and equitable governance of land tenure. This guide incorporates a gender perspective in order to achieve more equitable participation between men and women in processes and institutions related to land decision-making. It focuses on the concept of equity and the ways in which land administration considers the differences, needs and priorities of men and women. In this way, it offers a set of tools, strategies and actions that contribute to improving gender equity in processes and activities related to land tenure governance.

Gender equity must be incorporated into land governance to ensure that the interests and needs of all people-women and men-are taken into account; and that transparent, consultative and participatory procedures prevail in tenure-related processes and institutions (FAO, 2013, p. 5).

Although women play a fundamental role in the management of natural resources and in the development of productive activities, the conditions under which men and women carry out their activities continue to reflect important gender gaps which are accentuated under conditions of armed conflict. In this sense, the project will have specific actions aimed at reducing gender gaps by strengthening women's effective participation in decision-making, promoting their economic autonomy, strengthening their positions as community leaders and making visible the role that women play in the use, management and conservation of the territory.

1. Gender Analysis

In the following paragraphs gender statistics are presented for the five departments (Chocó, Nariño, Cauca, Valle del Cauca, and Risaralda) where the prioritized MUCBs are located.

Demographics

According to the DANE 2015-2020 population projections, the female population is slightly larger, representing 50.6 percent of the total population. In most of the departments the female population is slightly larger with the exception of Nariño and Cauca. The department with the highest number of women is Valle del Cauca with a percentage equivalent to 51.3%. (Table 1)

Table 1: Population projections by year and sex by department Period 2005-2020

|  | 2005 |  |  | 2010 |  | 2015 |  | 2020 |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Department | total | Women | % women | total | women | total | women | total | women |
| Total national | 42,888,592 | 21,718,757 | 50.6 | 45,508,205 | 23,041,594 | 48,202,617 | 24,390,693 | 50,912,429 | 25,757,335 |
| Chocó | 454,030 | 229,293 | 50.5 | 476,173 | 239,063 | 500,076 | 249,845 | 525,528 | 261,531 |
| Nariño | 1,541,956 | 770,048 | 49.9 | 1,639,569 | 817,146 | 1,744,275 | 868,309 | 1,851,658 | 921,364 |
| Cauca | 1,268,937 | 626,522 | 49.3 | 1,318,983 | 650,705 | 1,379,070 | 680,151 | 1,437,141 | 708,592 |
| Valle del Cauca | 4,161,425 | 2,138,610 | 51.3 | 4,382,939 | 2,256,202 | 4,613,377 | 2,376,741 | 4,852,896 | 2,502,463 |
| Risaralda | 897,509 | 459,141 | 51.1 | 925,105 | 474,196 | 951,945 | 488,200 | 978,182 | 501,773 |

Source: Dane. Population projections by year and sex by department Period 2005-2020

According to the 2005 DANE Census, Colombia has 3.4% of indigenous people and 10.3% of black communities, of whom 49.5% and 50.3% are women, respectively. The majority of the population in these departments are black communities, and women are slightly majority among the population, but slightly minority among the indigenous population. The department with the largest black community and indigenous population is Chocó (Table 2).

Table 2: Composition of ethnic groups by department

|  | Indigenous |  | Black communities |  | Rest |  |
| --- | --- | --- | --- | --- | --- | --- |
| Departments | % total | % women | % total | % women | % total | % women |
| Total national | 3.4 | 49.5 | 10.3 | 50.3 | 84.2 | 51.1 |
| Chocó | 11.4 | 49.4 | 73.6 | 51.3 | 4.7 | 47.4 |
| Nariño | 10.4 | 50.1 | 18.1 | 49.4 | 67.6 | 50.9 |
| Cauca | 21 | 49.1 | 21.6 | 50.8 | 54.9 | 50.4 |
| Valle del Cauca | 0.5 | 50.5 | 26.9 | 51.9 | 71.6 | 52.1 |

Source: CELADE - 2005 CENSUS. Retrieved from Presidency Counseling for Women. Women’s situation in Colombia, Chocó and in the Pacific region - Figures and indicators.

With regard to head of household by sex, Colombia has a sustained increase in female heads of household, with 30% of all households in the country according to the 2005 census. In the department of Chocó the female head of household is 33%, Valle del Cauca 32%, Risaralda 31%, Cauca 28% and Nariño 29%. The Chocó Departmental Development Plan states that Chocó women are the poorest in the country and that Chocó is the second department in Colombia with the most female-headed households. 70% of Chocó households are made up of women and their children, surpassing the national average (Chocó Departmental Development Plan, 2016).

Labor market

Women's economic participation is lower than men's; this situation is more present in rural areas than in urban areas. In 2005, women's economic participation was 46% compared to 54% for men. It is important to highlight that in the Department of Chocó women have one of the lowest economic participation rates in the country with 15%; in Cauca it is 34%, in Valle del Cauca it is 43% and in Nariño it is 46%.

Unemployment affects women more than men. In 2010, the national unemployment rate for women was 15.6%, compared to 9% for men. In all the departments analyzed, the unemployment rate is higher for women than for men. This is due to the fact that, in rural areas, women are traditionally engaged in domestic and family work, and although women also work in productive activities, these activities are rarely recognized and remunerated. In addition, the unemployment gap is significantly greater in the Department of Chocó, where women have a rate of 16.9%, while men have a rate of 5.8%, in Nariño it is 37.8%, Cauca 17.8% and Valle del Cauca 15.5%.

Education

In the last years, illiteracy among the Colombian population has decreased, reaching 8% in 2005. It is important to note that, at the national level, illiteracy among women (8%) is slightly lower than among men (9%). However, in most of the departments analyzed, the illiteracy rate is higher for women than for men. Once again, the department of Chocó has one of the highest illiteracy rates in the country, with 20% against 8% at the national level. Moreover, illiteracy among women is significantly higher than among men, with rates of 22% and 18% respectively (Table 3).

The Colombian population has an educational situation composed of a majority of people with basic, primary and middle education (about 60%), people with secondary education (about 16%) and people with higher education (about 12%).  In this context, women have a lower percentage in basic education than men, with 58.8% and 60.4% respectively. However, women have acquired a higher level of secondary and higher education than men. The department of Chocó has lower illiteracy rates compared to the other departments (Table 3).

Table 3: Level of education of the population aged 15 years old and over by sex, by department 2005

| Department | Men basic | Women basic | Men secondary | Women secondary | Men superior | Women superior |
| --- | --- | --- | --- | --- | --- | --- |
| Chocó | 50.8% | 49.9% | 9.7% | 11.3% | 5.8% | 7.6% |
| Cauca | 68.9% | 65.4% | 11.1% | 12.3% | 10% | 12% |
| Valle del Cauca | 61.5% | 60.5% | 19.4% | 19.7% | 11.5% | 12.6% |
| Nariño | 65.7% | 64% | 11.1% | 12.3% | 6.1% | 7.2% |
| Total national | 60.4% | 58.8% | 15.8% | 16.9% | 11% | 12.7% |

Source: DANE 2005 Census. Retrieved from Presidency Counseling for Women. Women’s situation in Colombia, Chocó and in the Pacific region- Figures and indicators.

Health

Most of the departments located in the Pacific region have a higher fertility rate than the national average, with the exception of the Department of Valle del Cauca.  In the Department of Chocó, the fertility rate is significantly higher than the national average, with 3.3 children per woman of childbearing age. Likewise, the percentage of pregnant women in Chocó and Nariño is higher than the national average (4.3% and 4.5% compared to 3.5% at the national level), for Cauca it is 3.9% and for Valle del Cauca it is 3.1%.

With regard to maternal mortality in 2009, nearly 72 mothers died per 100,000 live births. Most of the departments in the Pacific have maternal mortality rates higher than the national average, with the exception of Valle del Cauca. It should be noted that Chocó and Nariño have the highest maternal mortality rates, with 126% and 122%, respectively, suggesting serious sexual and reproductive health difficulties. For Cauca it is 102.68% and for Valle del Cauca it is 58.24%.

Violence

The national homicide rate is 38.36. The breakdown by sex shows that the homicide rate is significantly higher in men than in women, with 71.2 per 100,000 men and 6.27 per 100,000 women. This behavior is also reproduced in the other analyzed departments. The department of Valle del Cauca has a homicide rate much higher than the national average with 77.6 followed by Cauca with 41.6.

Colombia has a high rate of domestic violence with 196,3 per 100.000 inhabitants. This type of violence affects women much more than men with 302% and 87% respectively per 100.000 inhabitants, which means that 78% of the victims of this type of violence are women. The departments with the highest percentage of domestic violence are Valle del Cauca and Cauca with 254,2 and 237,1 respectively (Table 4).

Table 4: Rate per 1000 inhabitants of domestic violence by sex, by department, 2010

| Department | Total males | Total females | Total | % Female victims of domestic violence |
| --- | --- | --- | --- | --- |
| Chocó | 19.82 | 107.09 | 63.63 | 91.3 |
| Cauca | 61.2 | 237.12 | 147.99 | 89.25 |
| Valle del Cauca | 58.12 | 254.22 | 159.07 | 90.9 |
| Nariño | 40.37 | 150.15 | 95.09 | 90.47 |
| Total | 87.79 | 302.54 | 196.53 | 88.44 |

Source: Description of the Behavior of Homicide. Colombia, 2010 - National Institute of Forensic Medicine and Forensic Sciences. Taken from Presidency Counseling for Women. Situación de las mujeres en Colombia y en Chocó y la región Pacífica-Figures and indicators

The displaced population in Colombia represents around 8.1%. This figure is higher for men than for women with 8.4% and 7.9% respectively. Nariño is the department that has received the highest number of displaced people with 179,718 people, equivalent to 11% of the affected population with respect to the total departmental population. In this regard, it is important to highlight the situation in Chocó with 114,635 displaced persons, equivalent to 24% of the departmental population. In this population, the number of women and men is very similar.

In relation to the displaced population, Chocó and Nariño have the highest numbers of displaced people. In 2010, Chocó had expelled a total of 206,554 people, equivalent to 43.4 of its total departmental population. Nariño expelled a total of 162,488 people in 2010, equivalent to 8% of its departmental population. Among the expelled population, women are slightly in the majority, with a total of 50.5 %.

The gender approach in planning instruments:

Territorial planning plans at the departmental level include a gender perspective. The Development Plan of the Department of Cauca (Development Plan 2016-2019) incorporates a specific gender equality component, which establishes objectives to strengthen institutions, eliminate violence against women and improve social, and community empowerment. The Departmental Development Plan for Chocó 2016-2019 develops a chapter on women, highlighting the general situation of women in the department and the particular situation of indigenous women.

In the same way, some planning instruments of black and indigenous communities include gender considerations in their life/ethno development plans. The Comprehensive Environmental Self-Development Plan of the community councils of Tumaco and Francisco Pizarro (RECOMPAS, 2008) includes a chapter on generational equity and gender, emphasizing the importance of promoting better living conditions for black women and strengthening their abilities for autonomous development and participation in decision-making forums. Its activities include promoting gender equity and women's autonomy, promoting programs and policies aimed at strengthening collective territoriality at the hands of women, supporting environmental quality programs promoted by women in collective territories, and promoting a policy of environmental management and community participation with a gender perspective. For its part, the Life Plan for the indigenous communities of the Awa People includes a chapter on the Awa family and women, aimed at strengthening training processes on the rights of Awa women and girls.

Women's participation during the formulation phase

Throughout the formulation phase of the project some female representatives from community councils and indigenous reservations participated in the participatory forums. Highlighted is the participation of Ana Rubiela Palacios from the indigenous reservation from Montaño with presence in the Katíos Caoba MUCB, Maritza Landázuri from the community council Bajo Mira and Frontera impacting in the of Cabo Manglares Gran Familia Awá MUCB, Rocio Bonilla from the community council of Santa Cecilia, Lida Riascos from the foundation San Cipriano y Laura Ruiz Flórez from the ecological foundation Los Colibríes de Altaquer FELCA, which develops projects on environmental education with local communities of Río Nambí Natural Reserve.

In addition, during the workshop for the participatory construction of the project's results and products framework, a round table was held with representatives of community councils and resguardos in order to gather their perceptions and needs with respect to the components proposed by the project and to collect information related to safeguards, ethnic and gender differential approaches. Despite historical and patriarchal patterns in the relationship with each other, there are more and more exercises and leadership experiences by women that transcend this patriarchal imaginary. In the community council of Yurumanguí there is Dalia's leadership. In the council of the Raposo river it was a woman the one who led the movement against mining. In the major community council of Anchicayá Beatriz leads as councilor, where she has conducted a very important work with women promoting the use of home gardens. In the community councils of Zabaletas, Guaimía, Llano Bajo and Corregimiento 8, women have held positions of legal representatives. In this way, women have gained space for recognition and representation, but it is mainly men who make the decisions.

Some women's organizations that are working on gender issues and promoting leadership and empowerment of women, young people and girls were identified.  It is important to highlight the presence of the Association of Rural, Indigenous and Black Women of Colombia (AMUCIB), which promotes the defense of women's ethnic and territorial rights and fosters the articulation and strengthening of women's productive and social dynamics in their family and community environment.

The AMUCIB, created approximately in 1984, has an impact at the local, departmental and national levels, with an impact in 24 departments. Particularly in the department of Valle del Cauca, this organization has worked with several community councils in the municipalities of Tuluá, Dagua, Jamundí, Palmira, Sevilla, Yumbo, Buenaventura, Zarzal and Calima. In the municipality of Calima this organization has worked on projects led by women for the recovery of traditional seeds and medicinal plant crops in alliance with the Women's Action Fund. In the municipality of Buenaventura, this organization has worked with women from the community councils of Bajo Calima, Zacarías, Calle Larga, Las Palmeras, Mayor de Anchicayá, Alto y Medio Dagua, Citronela, Sabaleta, Vistahermosa, El Triunfo and Esfuerzo 2. In alliance with the Ministry of the Interior of the Valley, it worked on a research project with 187 women to raise broilers.

It is also important to highlight the Ruta Pacífica de las Mujeres that works with approximately 300 women's organizations and 9 regional ones with presence in Chocó, Valle del Cauca, Cauca and Risaralda. It is a feminist movement with political and social action aimed at strengthening the feminist vision of pacifism, non-violence and civil resistance and at promoting transformations in the public and private sectors in favor of women for the construction of peace, social justice and the enforceability of the rights to truth, justice and reparation.  The Ruta Pacífica de las Mujeres regional del Valle del Cauca promotes the peace agenda of the women of the Valle del Cauca.

In addition, the following local women's organizations were identified in the prioritized MUCBs.

Local women’s organizations

| MUCB | Name | Location |
| --- | --- | --- |
| Farallones-Calima | Asociación de mujeres campesinas e indígenas de Buenaventura ANMUCIB | Buenaventura |
| Cabo Manglares-Gran Familia Awá | Mujeres en Acción | Tumaco |
|  | Asochillangua |  |
|  | Escuela de jóvenes |  |
|  | Jóvenes Acapa |  |
|  | Afromubara |  |
|  | ACOP |  |
|  | Asociación Mujeres Emprendedoras de Ricaurte | Ricaurte |
|  | Asociación Mujeres el Porvenir Chambú |  |
| Serranía Paraguas-Tatamá | Red de Mujeres del Pacífico | El Cairo |
|  | Mulan |  |
|  | Mujeres por un Buen Futuro |  |
|  | Mujeres Semillas del Mañana |  |
|  | Camigua |  |
|  | Asomuproplat |  |
| Katios-Caoba | Resguardo Arquia | Unguia |
|  | Grupo de Mujeres de Acandí | Acandí |

The gender dimension of the project responds to a transversal approach in the different components of the project related to institutional strengthening (component 1), integrated management of protected areas and complementary conservation strategies (component 2) and the improvement of their productivity, income and living conditions (component 3).  The project will guarantee and strengthen the representation and effective participation of men and women in the products and activities to be implemented, as well as in the fair and equitable distribution of the benefits generated by the project. It will also contribute to the visibility and recognition of the role that women play in the management, use and management of biodiversity.

Likewise, in the implementation of the activities, the project will promote the participation of young people and older adults, considering that the traditional space for the transmission of knowledge in daily life has been lost due to the abandonment of traditional festivals and meetings, the isolation of older people and the new interests of young people. In addition, many of the latter move to the cities in search of better opportunities, thus losing their connection to land, animals and crops. In addition, traditional festivals and meetings are being abandoned.

Since the project activities can have a differentiated impact on the situation of women, it is important to make visible the existing differences related to work, poverty, family life, health, education, environment, public life and decision-making, as well as to promote equal benefits and opportunities for men and women. It is also important to consider and assess the specific needs and interests of men and women in the development of the project. This knowledge is essential to guarantee women's rights and to comply with project safeguards.

Incorporating a gender approach poses important challenges so that the project will take special care in designing strategies and mechanisms that address ethnic and cultural differences, socioeconomic differences, age and sexual differences present in the territory; guarantee the effective participation of women, including women heads of household in the development of activities and in the spaces for participation and decision-making; and promote fair equity in the distribution of opportunities and benefits.

In the design of the MUCB Action Plans, participatory analyses and field evaluations will be developed to collect information on the interests, needs and priorities of men and women, levels of participation in decision-making and their roles in the sustainable management of ecosystems, so that the intervention plans consider the particularities in relation to the roles and responsibilities that men and women will have in the development of activities according to the actions defined in each of the MUCBs.

Likewise, the project will incorporate into the contracting processes a gender consultancy so that the entire project team, including operators and contractors, can be trained in conceptual frameworks and practical tools to incorporate the gender approach in the development of its components and particularly in the training and capacity building processes.

The project will develop case studies, systematization of experiences and lessons learned on gender equality and women's empowerment in the different components of the project as part of the monitoring plan to make visible the role of women in the sustainable management of Pacific ecosystems.

It is important to note that there are some factors that could limit the effective participation of women in the development of project activities:

- Domestic responsibilities that limit participation

- Participation and predominant roles of men as leaders and decision-makers in relation to the activities carried out in their territories.

- Cultural patterns that inhibit women's participation in productive and community activities.

- Situations of violence against women that influence their lack of participation and interest in community and productive activities

- Isolation and lack of mobilization: Distance between homes and meeting places or difficulties in transportation or travel times.

- Lack of knowledge of the institutional framework that protects women's rights.

However, it is important to point out that there are also opportunities to increase gender equality:

- Recognition of the role and contributions that men and women make in the development of productive systems, forest management and management of protected areas and complementary conservation strategies.

- Recognition of the legal and institutional framework for strengthening women's rights.

- Willingness on the part of indigenous and black community organizations to promote gender equality and strengthen women's participation in self-government structures.

- Recognition and valuation of women's traditional knowledge regarding the use, management and conservation of biodiversity.

- Promotion of interests and capacity building needs for women.

- Coordination with other institutions and organizations working on gender issues.

Women in the Pacific region are highly vulnerable due to high levels of poverty and social exclusion and gender-based violence. The social exclusion of women is particularly relevant in ethnic communities since historically decisions regarding production, transformation, access, opportunities, implementation of local economic development strategies are immersed in a patriarchal culture.

However, it is important to highlight the recognition of the growing leadership power of black women in the Pacific and their potential to generate positive changes in the development of communities.

In the area of influence of the Farallones-Calima MUCB, there are several community process leaders from women who have been able to obtain positions as legal representatives of their community councils, as is the case of Estella Hinestroza from the Sabaletas Community Council; Marcelina Cundumi of the Community Council of San Marcos; Carolina Parra Bustamante of the Community Council of Alto Potedó; Carlina Hinestroza of the Community Council of Limones; Francisca Ordoñez of the Community Council of Brazito Amazonas and Yusmely Valencia of the Community Council of Campo Hermoso. Also, in the Greater Community Council of Anchicayá there is the Cooperative COMUMPENSAR which works in productive processes for women led by Beatriz Mosquera. The San Cipriano Forest Reserve in the municipality of Buenaventura is also led by a woman.

The design of local strategies and access to opportunities for women is a priority to promote gender equality through the project. In order to achieve these objectives, the following priority activities will be included in the Gender Mainstreaming Plan by component (see figure 2).

Figure 2: Gender Mainstreaming Plan

| COMPONENT | OUTPUT | ACTIVITIES | INDICATORS |
| --- | --- | --- | --- |
| Component 1: Institutional strengthening to support conservation and sustainable use in the Pacific region of Colombia | 1.1.1 Diagnosis and strategic assessment of ecosystem services in the Pacific region | Participatory background and baseline review and validation with an ethnic and gender perspective | Mechanism for Incorporating a Gender Perspective in the Diagnosis of Ecosystem Services |
|  |  | Identify, characterize and prioritize the types of ecosystem services and the different ways of valuing them from the different beneficiaries of the services with an ethnic and gender perspective. |  |
|  | 1.1.2. Guidelines for harmonizing territorial plans at the departmental and municipal levels with the planning instruments developed by black and indigenous peoples to safeguard cultural, biological, and ecosystem services’ diversity through pilot projects in the MUCBs. | Characterization of departmental and municipal land-use planning instruments and planning instruments for prioritized black and indigenous peoples, identifying those that incorporate a gender perspective. | Number of planning instruments that include a gender perspective |
|  |  | Formulate and/or update planning instruments specific to ethnic peoples with an impact on the project (life plans/ethno-development) from a gender perspective. | Number of life/ethno-development plans that include a gender focus |
|  |  | Participatory definition and validation of environmental and social safeguards with the participation of representatives of local communities and institutions including the effective participation of women and women's organizations, youth and older adults. | Number of male and female participants |
|  |  | Formulation of guidelines that will allow for the adequate inclusion of environmental and social safeguards, including a gender perspective in the ETPs/UNDPs, and harmonization with the planning instruments for black and indigenous peoples. | Guidelines that incorporate a gender perspective |
|  | 1.1.3. A tailor-made and open-access SIAT_PC, integrated with the Environmental Information System of Colombia (SIAC), is strengthened to harmonize all existing planning mechanisms and frameworks for the Pacific region leading to a cohesive and environmentally- sound planning process detailing prescribed land-uses. | Design and implement dissemination and training alternatives to expand access to environmental information in the region, with territorial entities and other community organizations, including women's organizations. | Number of participating women's organizations |
|  | 1.1.4 Forest Zoning and Management Plans outside the PAs developed, updated, and implemented in a participatory way, promotes socio-ecosystem connectivity at the MUCB level. | Participatory formulation of forest management plans in the MUCBs and prioritization of implementation actions with effective participation of women, youth and older adults. The management plans will make the roles of men and women in forest management visible. | No. of management plans that include a gender perspective |
|  | 1.2.1. Participation and decision-making organizational structures strengthened within the framework of SIRAP Pacific, and enhanced capacity of project stakeholders’ to apply guidelines for harmonizing territorial and environmental management planning instruments that safeguard cultural, biological, and ecosystem services’ diversity in the MUCBs. | Promote the effective participation of women in participation and decision-making bodies within the framework of SIRAP Pacific: one (1) for each MUCB (total 5) and one (1) at the regional level. | Number of male and female participants |
|  | 1.2.2. Local community participatory structures (forming networks for sharing knowledge) strengthened to ensure compliance with guidelines for harmonizing territorial and environmental management planning instruments that safeguard cultural, biological, and ecosystem services’ diversity in the MUCBs. | Supporting ethnic groups' own instances of participation and decision-making, such as general and local assemblies, strengthening knowledge on gender issues to ensure the effective participation of women. | Number of male and female participants |
|  |  | Design training routes for environmental leaders/managers with capacity building and spaces for intercultural and intergenerational dialogue, taking into account the interests and needs for strengthening and training by women, young people and older adults. | Number of men, women, youth and older adults participating |
|  |  | To develop training routes for environmental leaders/managers with capacity building and spaces for intercultural and intergenerational dialogue with the effective participation of women, young people and older adults. |  |
|  |  | Participatory design of the route for the exchange of experiences, including the effective participation of women. |  |
| Component 2: Integrated management of PAs, buffer zones and CCSs | 2.1.1. Management plans and governance mechanisms developed and/or adopted include support for the implementation of priority actions in the selected areas. | Support for the formulation and updating of management plans for five protected areas with the effective participation of women. | Number of female participants |
|  | 2.1.2. Financial sustainability strategy designed and implemented for ensuring participation within the SIRAP Pacific framework. | Realization of legitimate SIRAP participation spaces for the construction of the Sustainability Strategy, including the effective participation of women. |  |
|  | 2.1.3 Forest restoration and soil recovery plans for PAs, buffer zones, connectivity areas, and corridors are developed and implementation is kick-started in a participatory manner. | Implementation of ecological restoration and soil recovery plans with effective participation of women and taking into account their traditional knowledge and knowledge. | No. of forest restoration processes that include a gender perspective |
|  | 2.2.1 Planning and management instruments developed, with priority actions implemented in CCSs, by the forest-dependent communities. | Development of actions to support the participatory construction of planning and management instruments for CCPs with the effective participation of women, young people and older adults. | Number of planning instruments that include a gender perspective and number of female participants |
|  |  | Definition of the governance mechanism for the Complementary Conservation Strategies, including participation mechanisms that guarantee the participation of women. | Mechanisms for the effective participation of women |
|  | 2.2.2. Technical guidelines as support for the regulatory process to formalize the CCSs in the Pacific region considering ethnic/cultural aspects and in line with the national process. | Characterize complementary conservation strategies by identifying the roles that men and women play in relation to the management of these strategies. | CCP characterization documents that include a gender focus |
| Component 3: Sustainable production practices as alternatives for local development, biodiversity protection and peace process support | 3.3.1 Green Business action plan(s) harmonized and under implementation for fostering and developing diversified production systems are agreed upon and modalities adapted to local conditions, for supporting food security, sustainable livelihoods, landscape-level connectivity and forest rehabilitation. | Support the formulation of three green business plans that include social and environmental safeguards and incorporate a gender perspective | No. of green business plans that include a gender perspective |
|  |  | Implementation of early actions in 25 selected initiatives including women-led initiatives. | No. of initiatives led by women |
|  | 3.3. 2 SFM initiatives and sustainable production systems implemented incorporating good soil and biodiversity-friendly practices | Characterization of production systems will identify the roles of men and women in the management of production and forest management systems, women producers' organizations, and women's capacity building needs. | Characterization documents of productive systems that include a gender approach |
|  |  | The activities related to training and technical assistance will take into account the interests and needs for strengthening women in relation to sustainable productive practices. | Number of men and women trained |
|  | 3.2.1. Value addition units of biodiversity-derived products created and strengthened, with technical and management training that safeguard cultural, biological, and ecosystem services’ diversity. | Build the business plan and operating model of the value addition units including the effective participation of women. | Number of male and female participants |
|  |  | Build administrative and management capacities taking into account needs to strengthen the skills and knowledge of women and young people | Number of men and women trained |
|  | 3.2.2. Biodiversity-derived products with market access and complying with quality requirements, MADS green business criteria, and other standards for market access. | Provide technical assistance and training to meet requirements, quality standards and sustainability. Develop criteria to guarantee the participation of women and youth, identify the barriers women face in accessing credit, markets and incentives. | Number of men and women trained |
|  | 3.3.1 Community-based nature tourism initiatives strengthened with government and non-government support that safeguard cultural, biological, and ecosystem services’ diversity. | The activities related to the assessment, planning and implementation of actions for the tourist development will count on the effective participation of women and the youth. | Number of male and female participants |
| Component 4: Knowledge management and project M&E. | 4.1.1. Participatory action plans for the prioritized MUCBs. | The design of MUCB action plans will involve the effective participation of women and take into account their interests, needs and priorities. | Number of male and female participants |
|  |  | The Participation Agreements will include a clause that guarantees respect for women's rights and the equitable distribution of benefits. | At least one clause guaranteeing respect for women's rights and the equitable distribution of benefits is included in 100% of the agreements signed with producers. |
|  | 4.1.2: An online monitoring platform | The project information should collect, compile, analyze and present the information by sex and age in order to have differentiated impacts of the project. | Methodology for collecting information and processing data by sex and age |
|  |  | Gender indicators will be included in the monitoring and evaluation system. | Number of gender indicators included in the system |
|  |  | To develop case studies, systematization of experiences and lessons learned on gender equality and empowerment of women in the different components of the project as part of the monitoring plan that make visible the role of women in the sustainable management of Pacific ecosystems. | At least two publications (case studies or systematizations) during the life of the project that recognize lessons learned and best practices on empowerment, lessons learned from men and women, and activities and products promoted by the project. |
|  | 4.1.3: Communication strategy implemented | Educational, communication and awareness-raising campaigns to promote a culture of gender equality in decision-making spaces, structures, organizations and governance mechanisms. | Number of communication campaigns that include a gender focus |
|  |  | Promote affirmative actions that facilitate access by women and young people to capacity building and technical assistance programs. | Number of affirmative actions to facilitate participation |
|  | 4.1.4: MTR and FE | Include gender criteria in the mid-term and annual outcome evaluation to ensure that gender mainstreaming is monitored in the project. | Number of criteria included in evaluations. |

## APPENDIX 14: ENVIRONMENTAL AND SOCIAL MANAGEMENT PLAN (ESMP) UNIDO COMPONENT

- Project Description

The project objective is to mainstream the sustainable use and conservation of biodiversity and the provision of ecosystem services that support human welfare and vulnerable landscapes of the Colombia’s Pacific region in view of generating global and local environmental benefits and supporting the peace process. The project will be implemented in five biodiversity conservation and use mosaics (MUCBs) in the Colombian Pacific region, in the departments of Nariño, Cauca, Valle del Cauca, Risaralda, and Chocó, creating conditions for replicating results at the regional and national levels. The Katíos – Caoba, Farallones – Calima, and Cabo Manglares – Gran Familia Awá MUCBs will have full intervention; while the Serranía de los Paraguas – Tatamá and Munchique – Río Saija MUCBs will have partial intervention.

- Figure 1. Prioritized MUCBs.

The general project strategy is based on conservation mosaics and a green business approach. In the former, this approach will enable the integrated management of a geographical area by implementing actions to reduce ecosystem fragmentation and degradation, as well as building social bridges for the effective management and administration of protected areas (PAs) and complementary conservation strategies (CCSs). The green business approach will allow a linkage of biodiversity-derived products with markets (subnational, national, and international), creating sustainable economic alternatives for the communities and promoting biodiversity conservation and sustainable forest and land management.

The project strategy consists of four interrelated components. Component 1 is focused on harmonizing territorial management tools to safeguard the cultural, biological, and ecosystem services diversity of the Colombian Pacific region, and strengthening institutional and community capacities. Component 2 provides support for strengthening governance mechanisms in the PAs and improving their management effectiveness; it also will support voluntary CCSs (primarily those developed by communities) in terms of their regulatory process for their formalization as territorial conservation strategies and their management; together with the declaration of new PAs they will contribute to national conservation goals. Component 3 will support sustainable economic alternatives based on production and/or use of biodiversity-derived products that improve the community’s quality of life; primarily those communities residing in PAs’ buffer zones and that were affected by Colombia’s armed conflict. Finally, Component 4 will support the development of participatory action plans for each MUCB and the implementation of a communication strategy appropriate to the context of each MUCB that enables the dissemination of good practices and knowledge resulting from project implementation.

Environmental context

The mountain and coastal areas of the Colombian Pacific region have a predominance of natural ecosystems; this region comprises 17% of the Colombian land mass and contains 8% of the country’s forests. This region is recognized worldwide as a reservoir of great biological and cultural diversity and is part of the Tumbes-Chocó-Magdalena “hot spot.” It is also part of a larger unit known as the Chocó biogeographic region. The high levels of biodiversity are due to a series of conditions that include natural and geological characteristics, geomorphological aspects, climate conditions, and biogeography. The Colombian Pacific region also has large variety of human settlement patterns,,.

This region, along with other hydrographic areas of the country, such as the Amazon and low Cauca areas, has the greatest capacity to retain moisture and maintain water regulation conditions. The hydric output of the Pacific region is the highest in the country and is estimated at 116.2 liters per second per square kilometer (l/s-km2). The Pacific region supplies 283,201 million cubic meters (Mm3) of water, which is 14% of the country’s total water supply.

The types of forest present in the Colombian Pacific region as per the composition of the plant associations are homogeneous and heterogeneous forests. The term homogenous refers to the cativa tree forests, mangroves, natal, and guandal forests. The term heterogeneous refers to the tropical rainforests of the Andean and Sub-Andean zones (17% of the region’s terrestrial ecosystems), basal forests (54%), riparian forests (8%), dry forests (0.2%), and páramos (0.8%), among others.

The Colombian Pacific region has one of the highest levels of endemic plants on the planet: 25% of the flora in this region does not exist anywhere else in the world, a phenomenon that is particularly true for the Anthurium family and related species (Araceae), orchids (Orchidaceae), palms (Cyclanthaceae), and bromeliads (Bromeliaceae). According to data compiled by the GEF project Conservation of Biodiversity in the Chocó Biogeographic Region (1992-1998; GEF ID 366), the Chocó biogeographic region contains 15% of the total plant species described globally for the 36 plant families studied.

Although the regional fauna is not as well known, it is also rich, particularly due to the large volume of terrestrial invertebrates that are as yet unclassified. There are 353 known species of day butterflies of the 3,300 species reported for the Neotropic. Among vertebrates, amphibians are very diverse compared with other Neotropical regions. It is estimated that the Pacific region contains almost 11% of all bird species known in the world and 56% of the Colombian species. The region contains 176 species of mammals, compared with 896 species reported for the Neotropic. It should be noted that many of these species are limited in their distribution and range, are endemic to the region or more specific places, and constitute a resource that has traditionally been used by the inhabitants.

The Colombian Pacific region has a coastline that spans 1,544 kilometers (km), with its coastal and interior area covering 8,455 km2. The region encompasses 359,948 km2 of territorial waters, which correspond to 18% of the national territory. The Pacific region comprises 16 coastal municipalities. In physiographic terms, the Pacific coast has two distinct features: 1.) In the northern region between the border with Panamá and the Corrientes cape, with steep and high-relief coastal areas that are approximately 374 km in length. 2.) In the southern region towards Ecuador the coast is low, alluvial, with floodplains covered with mangroves and a dense drainage network made up of rivers and estuaries; there are some cliffs in Málaga, Buenaventura, and Tumaco bays.

Among the main marine-coastal ecosystems and biotopes characteristic of the region are mangroves (47% of total coastal ecosystems area), coral reefs, beaches (sandy, sandy-muddy, rocky), sea grass prairies, soft bottoms (89% of total marine ecosystems), rocky or steep complexes, coastal estuaries and lagoons, and pelagic areas. These ecosystems are rich in animal and plant species that form the basis of the local economy, and provide indigenous communities with the means for their subsistence to supply national and international markets.

The soils of the Colombian Pacific region are typically poor or deficient, and are best fit for forestry activities, and are considered globally unique because of their interaction with salt water, fresh water and the region’s biomass. The degradation processes that these soils are undergoing include compaction, contamination, loss of organic matter, salinization, and desertification. The region is also known for its contribution to mitigate climate change at the local and global levels.

Socioeconomic context

Despite the fact that the Colombian Pacific region is rich in biodiversity and natural resources, the current levels of poverty, social inequality, and marginalization are the highest in the country. The Chocó is the poorest department in the country with a poverty rate of 68.0%, followed by Cauca at 62.1%, Nariño at 47.6%, and Valle del Cauca at 26.9%. This situation becomes even more critical in rural areas, which have high levels of food insecurity and malnutrition that are due to a lack of availability and access to a diversified source of food, particularly for the most vulnerable inhabitants. This region, particularly the Chocó, contributes the lowest per capita income nationally. In 2013, the Chocó contributed only 0.4% of the total Gross Domestic Product (GDP), which is one of the lowest in the country. The five pillars of the regional economy in 2014 were a) social, community, and personal services (34.5%); b) mining and quarries (23.9%); c) agriculture and livestock (13.45%); d) restaurants and hotels (7.5%); and e) construction (5.9%). In terms of business and manufacturing, the region’s contribution was only 1.9% and 1.3%, respectively. The resources and activities practiced within the region (other than extraction) are representative of indigenous and black populations who mainly live in rural areas and consist of fishing, hunting, and small-scale agriculture; these activities do not comprise a significant share of the GDP and are generally not visible at the national level. According to data from the National Statistics Administrative Department (DANE, according to its Spanish acronym), the region rated the highest Multidimensional Poverty Index (MPI) in 2013 (53.8%), constituting more than half of the entire country’s MPI. With regard to the Unsatisfied Basic Needs index (UBN), the Colombian Pacific region rated 65.17%, which is considerably higher than the UBN for the entire country (27.78%); additionally, the Chocó was rated with an UBN at 79.19% (the highest in the region), followed by the Pacific sub-regions of Nariño and Cauca at 77.17 % and 68.47 %, respectively.

In addition, the region’s gold resources have been exploited for more than four centuries. The extracted gold is sent through national or international channels where its value increases; however, none of the capital gains generated are returned to the areas of local extraction/production. The same is true for the exploitation of timber and fishing resources, which has led to the extinction or near extinction of many plant and animal species. This extraction-based economy creates false expectations of wealth and prevents the understanding that these types of use of natural resources are not sustainable and will adversely affect local inhabitants’ food security.

Environmental & social risk assessment

During the PPG stage a contextual analysis of environmental and social risks was conducted (encompassing risks from the project as well as risks to the project) in accordance with FAO and UNIDO guidelines: UNIDO Environmental and Social Safeguards Policies and Procedures (ESSPP) and FAO Guidelines for Environmental and Social Risk Management. The analysis results are presented in Appendix 5.

According to FAO Guidelines for Environmental and Social Risk Management, this project has been qualified as a moderate risk. The environmental and social safeguards identified for further consideration are the following:

- Presence of indigenous and black peoples in the project implementation areas where the proposed activities will be carried out, which may impose potential risks on such communities. This risk relates to FAO Safeguard 9: Indigenous population and cultural heritage, and UNIDO Safeguard 4: Indigenous population. In Colombia, these safeguards are also applied to black raizal and Palenque communities.

- Project implementation in legally constituted PAs and buffer zones (FAO Safeguard 2: biodiversity, ecosystems and natural habitats/UNIDO OS2: natural habitats protection).

The following five risks were identified: i) the participating entities do not comply with the co-financing commitments; ii) lack of interest and low participation by traditional authorities and representatives of indigenous and black peoples in the project activities; iii) low participation of women, senior citizens, and young people; iv) climate change events that can affect conservation areas, production landscapes, and beneficiary local communities; v) socio-environmental conflicts related to extraction activities and territorial and land conflicts.

- Policy, legal, and administrative framework

During the design and implementation phases, the project will consider the environmental and social safeguards of the National Safeguard System, the traditional Knowledge Policy of the Ministry of Environment and Sustainable Development (MADS) and the safeguard guidelines considered by the implementing agencies (FAO and UNIDO) in order to ensure the respect and guarantee of the rights of local communities, as well as the integrity of the forests and ecosystems where the project actions will be implemented.

The project will take into account the environmental and social safeguards for REDD+  in Colombia defined in the United Nations Framework Convention on Climate Change (UNFCCC) as part of its implementation.  As part of the commitments made during the convention, the country is advancing in the construction and consolidation of a National Safeguard System with the purpose of providing information and monitoring how these safeguards are being respected and addressed in accordance with the national context. The National Safeguard System is part of the Integrated Strategy for Deforestation Control and Forest Management (EICDGB) led by MADS. This strategy aims to contribute to the conservation of forests and their biodiversity, improve the quality of life of local communities that live or depend on forests and improve the sustainability of the activities of the sectors that are related to causes of deforestation. It also recognizes aspects related to land tenure, gender and safeguards with effective participation of ethnic and peasant communities, recognizing the vision and significance of forests for these communities.

As the project will be implemented in the traditional communities of indigenous, black and rural peoples, it will be designed to ensure conformity with the GEF Principles and Guidelines for Engagement with Indigenous Peoples, social and environmental safeguards for REDD+ in Colombia, and the environmental and social safeguards of the implementation agencies (FAO and UNIDO), which specifically relate to safeguards that respect traditional knowledge and the rights of these communities (FAO Safeguard 9: Indigenous Populations and Cultural Heritage, and UNIDO Safeguard 4: Indigenous Population). In Colombia these safeguards are also applicable to Black, raizal, and palenque communities.

The process of Free, Prior, and Informed Consent (FPIC) for these communities will be applied throughout the project in accordance with the FAO Manual for this process. This is a right fully recognized by ILO Convention 169 and the United Nations Declaration on the Rights of Indigenous Peoples, which has been entirely incorporated into the FAO Policy on Indigenous and Tribal Peoples, FAO Environmental and Social Guidelines, and UNIDO Environmental and Social Safeguards Policies and Procedures.

- Environmental and social (E&S) risks and mitigation measures

|  | E&S risks | Mitigating Measure | Technical details of the mitigation technology, process, equipment, design and operating procedures | Location | Timeline, including frequency, start and end date | Responsibility | Cost of Mitigation (If Substantial; to be covered by the GEF grant or non-UNIDO co-financing) |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Risks identified during the PIF preparation and verified during the project preparation (PPG) | Climate change affects areas that are vital to the stability of ecosystems and productive landscapes | Processing plants will be equipped to process a number of different products | Certain processes such as pulping, homogenization, sterilization, etc., can be performed with the same equipment. If necessary applications need to be procured that allow for the change of the process with some new equipment | All processing (value adding) units supported by the project | Throughout the project | UNIDO field operations managers, communities and/or owners of the processing units | Depends on the type of factory design change to be applied |
|  | Unwillingness of local institutions to participate in project activities | From the start of the project communities will be consulted and trained on the development of community-based processing plants | Management and ownership plans will be developed before setting up the processing plants | All processing (value adding) units supported by the project | First 18 month of project | UNIDO field operations managers, communities and/or owners of the processing units | Continuous motivation and training of the communities is factored into the project budget |
|  | Resistance from local communities to participate in the development of productive alternatives proposed in the project because of disagreement from access to genetic resources | Processing plants will be equipped to process a number of different products | If a number of products will not be able to be sources alternative products always exist, some of them without issues of genetic resource exploitation (e.g. cocoa) | All processing (value adding) units supported by the project | First 18 month of project | UNIDO field operations managers, communities and/or owners of the processing units | Continuous motivation and training of the communities is factored into the project budget |
|  | Issues related to security (has recently aggravated) | Coordination with local and national authorities. Working with community based people in the project who become mediators. | Information on latest security status needs to be continuously reviewed. | The entire project region | Throughout the project | The entire project team in coordination with UNSST and the Government | Depends on the type of factory design change to be applied |
| Additional risks identified during the project implementation | Women will not be equally allowed to engage in and benefit from value addition activities | Targeting of particular producer groups in which women engage. Application of gender mainstreaming roadmap. | Trainings and capacity strengthening need to be focused on women capacities and availability | All processing (value adding) units supported by the project | Throughout the project | UNIDO field operations managers, communities and/or owners of the processing units | Additional training and capacity building costs |
|  | Workers at processing plants may not get employed due to lack of skills. | Intensive capacitation with visits to demonstrate good practice | The salary perspective will draw people into operations that are not sufficiently skilled. Clear rules on the basis of capacities need to be set on who engages and who gets paid. | All processing (value adding) units supported by the project | Throughout the project | UNIDO field operations managers, communities and/or owners of the processing units | Additional training and capacity building costs |
|  | Processing plants may contaminate the environment | Application of cleaner production and energy efficient technological solutions as well as waste management plans | The types of processes to be applied are not contamination intensive. Proper management of residues will even provide for more adding value | All processing (value adding) units supported by the project | 2nd year of the project during the plant design process | UNIDO project managers and local food technology consultants | Additional waste treatment equipment |

- Environmental and social sustainability monitoring

The M&E system of the project will monitor the outcome and output indicators, associated risks, and the corresponding mitigation measures. The biannual Project Progress Report (PPR) and the annual Project Implementation Report (PIR) will serve as the main tools for risk monitoring and management. These reports shall contain a chapter on monitoring of risks and mitigation measures that were identified during the PPG stage, and identify new risks with their corresponding mitigation measures, responsible individuals, and intended deadlines. The M&E Plan will be prepared by the GIS/M&E Expert in the three first months of the PY1 and validated with the PSC (Project Steering Committee).

- Capacity development

The PSC, the Regional Technical Committee (RTC), and the MUCB Technical Committees (MUCBTCs) will constitute spaces to propose management of these risks and the effective implementation of mitigation measures during the entire project life cycle, which could be adjusted as necessary; likewise, they shall identify, manage, and mitigate any risks not identified during the PPG stage.

During the implementation phase of the project, once the Steering Committee (SC) of the project, the Regional Technical Committee (RTC) and more specifically the Technical Committees of each MUCB (CTMUCB) are formed, the capacity of its members to carry out follow-up actions to the ESMP could be evaluated.

The participation of authorities and representatives from the beneficiary ethnic and rural communities is critical for the decision-making processes and the development of activities that will ensure the communities’ empowerment, autonomy, and governability in their territories according to their life plans/ethno-development framework.

A path to participation for these ethnic and rural communities has been developed, and will be executed in two phases: the first during the project development phase and the second during the project implementation phase.

Project development phase

Project participation and consensus spaces

| Event | Location and Date | Objective | Representatives of Communal Councils, Reserves, and other CSOs | Institutional Stakeholders | Attendance List |
| --- | --- | --- | --- | --- | --- |
| Project inception workshop | Bogotá, September 6, 2017 | Technical meeting to kick off the project document development with the goal of appropriation of the objectives, goals of the PIF goals, work plan, and the intended outputs for the project document development stage. |  | PNN, INVEMAR, FAO, UNIDO, MADS, Sustainable Pacific Vision, CBS Colombia | ..\Memorias eventos - proceso formulación\Listas de asistencia - Anexo 8\Lista asistencia taller Bogota 26 Sep 2017.pdf |
| Validation workshop | Cali, October 24, 2017 | Workshop to inform about the project antecedents, as well as results, outputs, and indicators of the project approved profile (PIF), the work plan to develop the project document, the MUCBs proposal, and to reach consensus on joint workspaces within the project development framework. | -Agua Clara Communal Council: Gilberto Montaño -Association of indigenous cabildos of Valle del Cauca Pacific region (ACIVA): Ligio Quiroz | CVC, INVEMAR, PNN, CORPONARIÑO, CRC, FAO, UNIDO, MADS, Sustainable Pacific Vision, CBS Colombia, IIAP, FAO, UNIDO | ..\Memorias eventos - proceso formulación\Listas de asistencia - Anexo 8\Lista asistencia taller Cali 24 Oct 2017- GEF Pacifico.pdf |
| Workshop Tatamá-Serranía Paraguas MUCB | November 16, 2017 | Present, socialize, and receive feedback on the project profile; identify input information for the baseline and analysis of the MUCB territorial context; collect key information to introduce, from the local-regional point of view, the approaches and actions to be developed in the MUCB | -Serraniagua: Cesar Franco | CVC, CARDER, PNN, IIAP, FAO | ..\Memorias eventos - proceso formulación\Memorias- Talleres Mosaicos\Memorias_TallerTatama-SerraniaParaguas_17-11-2017.pdf |
| Workshop Katíos Caoba MUCB | Turbo, November 22, 2017 | Present, socialize, and receive feedback on the project profile; identify input information for the baseline and analysis of the MUCB territorial context; collect key information to introduce, from the local-regional point of view, the approaches and actions to be developed in the MUCB | -Cuenca del Río Cacarica Communal Council: Pablo Salazar and Orlando Chochoguiro. -Bajo Cacarica Communal Council: Eulices Ramírez -Vigía de Curbaradó y Santa Rosa de Limón Communal Council: Jairo Mercado Córdoba -Montaño Indigenous Reservation: Ana Rubiela Palacios -Waunan Juin Phubuur Indigenous Community: Ovidio Chucho | BIOINNOVA, PNN, FAO, UNIDO CODECHOCO, | ..\Memorias eventos – proceso formulación\Memorias- Talleres MUCBos\Memorias_TallerKatios-Caoba –Noviembre de 2017.pdf |
| Workshop Cabo Manglares-Gran Familia Awá MUCB | Tumaco, November 27, 2017 | Present, socialize, and receive feedback on the project profile; identify input information for the baseline and analysis of the MUCB territorial context; collect key information to introduce, from the local-regional point of view, the approaches and actions to be developed in the MUCB | -Bajo Mira y Frontera Communal Council: Edwin Grueso (Vice-President), Ricardo Montaño (treasurer), Enrique Garrido Ruiz (spokesperson), Maritza Landázuri (comptroller). --ASOCASAN: Jefferson Quinto | PNN, IIAP, FAO, CORPONARIÑO CBS Colombia, Chocolate Tumaco Foundation, | ..\Memorias eventos - proceso formulación\Memorias- Talleres Mosaicos\Memorias Taller Mosaico Cabo Manglares .pdf |
| Workshop Farallones-Calima MUCB | Buenaventura, November 30, 2017 | Present, socialize, and receive feedback on the project profile; identify input information for the baseline and analysis of the MUCB territorial context; collect key information to introduce, from the local-regional point of view, the approaches and actions to be developed in the MUCB | Agua Clara Communal Council: Gilberto Montaño. -Association of indigenous cabildos of Valle del Cauca pacific region (ACIVA): Ligio Quiroz. | PNN, IIAP, FAO, CBS Colombia, UNIDO, CVC. | ..\Memorias eventos - proceso formulación\Memorias- Talleres Mosaicos\Memorias Taller Farallones-Calima.pdf |
| Meeting Munchique – Rio Saija MUCB | Popayán, December 12, 2017 | Present, socialize, and receive feedback on the project profile; identify input information for the baseline and analysis of the MUCB territorial context; collect key information to introduce, from the local-regional point of view, the approaches and actions to be developed in the MUCB | -Calle Santa Rosa Reservation: Carlos Quiro | PNN, FAO, CRC. | ..\Memorias eventos - proceso formulación\Memorias- Talleres Mosaicos\Memorias_TallerMunchique_12-12-2017.pdf |
| Project Results Framework Workshop | Cali, December 14, 2017 | Participatory development of the Project Results Framework, including SMART indicators | -Agua Clara Communal Council: Gilberto Montaño -Cuenca del río Acandí Seco, El Cedro y Juancho (COCOMASECO) Communal Council: Efraín Ballesteros Santa Cecilia Communal Council: Rocío Bonilla -Cacarica Communal Council: Luis Guillermo Chaverra --ASOCASAN: Jefferson Quinto RECOMPAS: Cesar Quiñones -Bajo Mira y Frontera Communal Council: Oberman Torres -ACIVA- Joaquincito -Reservation: Ligio Quiroz -Wounan Juin Phubuur Indigenous Community: Tilbaro Membache -Calle Santa Rosa Reservation: Carlos Quiro -Serraniagua: Cesar Franco -La Planada Reserve- Awá Reservation: Guillermo Cantillo -San Cipriano Foundation: Lida Riascos -FELCA: Laura Ruíz Florez and Cristian Florez | PNN, IIAP, UAO, INVEMAR, FAO, UNIDO, BIOINNOVA, CBS, MADS, ONF Andina, WWF, CODECHOCO, Visión Pacífico Sostenible, CARDER, CORPONARIÑO, Departmental government of Choco, CVC, Departmental government of Nariño. | ..\Memorias eventos - proceso formulación\Listas de asistencia - Anexo 8\Taller MML- Diciembre 14-15 de 2017\Memorias taller Construcción participativa- Dic 2017.pdf |
| Validation and consensus workshop | Cali, April 4-5, 2018 | Technical exercise involving the participation of institutional, community, and CSO stakeholders around validation and consensus of the project-specific actions for the four components and implementation arrangements in each MUCB | Agua Clara Communal Council: Gilberto Montaño Santa Cecilia Communal Council: Rocío Bonilla Cacarica Communal Council: Luis Guillermo Chaverra -ASOCASAN: Jose Aristarco Ríos Bajo Mira y Frontera Communal Council: Paterson Arboleda and Lidoro Hurtado. -ACIVA - Joaquincito Reservation: Ligio Quiroz -Calle Santa Rosa Reservation: Carlos Quiro -Serraniagua: Cesar Franco -La Planada Reserve-Awá Reservation: Guillermo Cantillo - San Cipriano Foundation: Lida Riascos | PNN, IIAP, INVEMAR, FAO, UNIDO, BIOINNOVA, CBS, MADS, CODECHOCO, CARDER, CORPONARIÑO, CVC, Departmental government of Chocó. | ..\Memorias eventos - proceso formulación\Listas de asistencia - Anexo 8\Listado asistencia - taller de concertación y validación - proyecto GEF Pacífico- Abril 4y5 de 2018.pdf |

Project implementation stage

| Consultation | Purpose | Participants | Lead/Chair | Reporting | Schedule |
| --- | --- | --- | --- | --- | --- |
| Communication plan for project development (participatory) | Within the project framework, a communication plan will be designed to transparently involve local communities that are beneficiary partners and allies of the project in the implementation process, the project activities, direct and indirect intervention areas, and project progress (Output 4.1.3). | Implementation agencies, MADS, PNN, SIRAP Pacific, CARs, research institutions, CSOs, educational institutions, and representatives of local beneficiary communities. | Comunication expert | Communication strategy | Year 1 |
| Intervention plan for each MUCB designed in a participatory manner | To define the intervention lines in each MUCB. The plans will state how the information exchange and consultations will be conducted using culturally appropriate means. | Implementation agencies, MADS, PNN, SIRAP Pacific, CARs, research institutions, CSOs, educational institutions, and representatives of local beneficiary communities. | General coordination and MUCBs technical supervisor | Participatory action plans for the prioritized MUCBs | Year 1 |
| Participation agreements with local beneficiary communities for the intervention plan per MUCB with its corresponding feedback and grievance mechanisms | Within the framework of the plans for intervention, voluntary agreements will be signed with entities participating in the project such as implementation agencies, MADS, PNN, SIRAP Pacific, CARs, research institutions, CSOs, educational institutions, and representatives of local beneficiary communities.. | Implementation agencies, MADS, PNN, SIRAP Pacific, CARs, research institutions, CSOs, educational institutions, and representatives of local beneficiary communities. | General coordination | Consensus on the formalization of the participatory intervention plan will be promoted that will also facilitate the coordinated work of territorial stakeholders and partners for biodiversity conservation and sustainable use in each MUCB | Year 1-2 |
| Participatory monitoring and evaluation of the participation agreement with local communities | The voluntary agreements with ethnic and local communities shall contain: • Signatory parties and/or customary practice to seal the agreement • Summary of the project information and implementation agencies • Proof of consensus • Social and environmental benefits for communities in the territory • Commitments taken by the participant institutions in activities implementation • Communication agreement • Mechanism agreed to for feedback, reporting of grievances, and how to address them • Monitoring and evaluation plan Monitoring of the participatory agreements will be conducted by the communities and their authorities, thereby respecting their own organizational modalities and specifying their own variables and indicators for indigenous participation. | Implementation agencies, MADS, PNN, SIRAP Pacific, CARs, research institutions, CSOs, educational institutions, and representatives of local beneficiary communities. | mosaics technical supervisor | the annual Project Implementation Report (PIR) | Year 1-5 |
| Documentation of lessons learned | During the final stage of project execution, a document detailing the lessons learned will be generated by which the project learning’s will be communicated in both the development and implementation stages, as well as the processes developed jointly with the communities, and the institutional framework supporting the project execution within the different MUCBs | FAO, UNIDO and local partners during project implementation | General coordination | Final Report | Year 5 |

Full intervention refers to the execution of all the project outputs in the MUCBs.

Partial intervention refers to the execution of priority outputs (defined in the participatory workshops conducted during the PPG stage) in the MUCBs.

Casas et al. 1998.

IDEAM, 2014.

According to Gentry (1986), the forests of the Colombian Pacific region are estimated to contain one of the richest plant communities in the world. In the Catalogue of Plants and Lichens of Colombia, of the 24,528 species of vascular plants recorded, 6,052 species are in the Pacific Region (Bernal, R., S.R. Gradstein and M. Celis (eds.), 2015).

Idem.

Ecofondo, 2008.

Playona Loma La Caleta IMRD.

IDEAM, 2014.

The reference area for this calculation is the management scope of SIRAP Pacific: 7,338,028.175 ha of land ecosystems, 1,533,070.525 aquatic ecosystems; cartographic sources: IDEAM 2010-2012.

The reference area for this calculation is the management scope of SIRAP Pacific: 1,533,070525 aquatic ecosystems; cartographic source: IDEAM 2010-2012.

From: GEF6 PIF: GEF, FAO, ONUDI, 2017

Casas et al. 1998.

Ecofondo, 2008.

INVEMAR, 2016.

Idem.

The reference area for this calculation is the management scope of SIRAP Pacific: 453,499.7207 ha coastal ecosystems, 161,1549913 ha marine ecosystems; cartographic source: IDEAM 2010-2012.

From: PIF (GEF-FAO-ONUDI, 2017)

MinCIT, 2015

The term ‘black communities’ is the English translation of the Spanish term “comunidades negras” which is widely utilized in Colombia and it will be used for simplicity throughout the text. The term ‘black communities’ in the Colombian context also include ‘Afro-descendants’ and ‘Afro-Colombians’ communities.

The UBN methodology used to determine, using simple indicators, if the basic needs of the population are met. The groups not reaching a minimum threshold are classified as poor. The indicators selected are: unsuitable housing, overcrowded housing, housing with insufficient utilities, households with high economic dependence, households with school-aged children who do not go to school. (DANE: https://www.dane.gov.co/index.php/estadisticas-por-tema/pobreza-y-condiciones-de-vida/necesidades-basicas-insatisfechas-nbi)

Problemática humanitaria en la región pacífica colombiana. Defensoría Delegada para la Prevención de Riesgos de Violaciones a los Derechos Humanos y DIH. Bogotá. 2016.

Ethos Regional, 1 000 copies, number 11, septiembre – diciembre 2014. Santiago de Cali, Universidad Autónoma de Occidente. Centro Interdisciplinario de Estudios de la Región Pacífico Colombiana, CIER, cier@uao.edu.co

Decree 2372 of 2010.

It is important to note that Decree 2372 of 2010 ruling the SINAP, only includes the regional protected areas subsystems and thematic protected areas subsystems. However, in SINAP dynamics in the country, departmental (SIDAP), municipal (SIMAP) and local (SILAP) systems have been also generated.

Conforme los establece el Decreto 2372 de 2010 (compilado por el Decreto 1076 del 2015 en su artículo 2.2.2.1.6.1.)

The life plans are planning instruments oriented towards the physical and cultural continuance of indigenous peoples, which are based on community dynamics and collective constructions wherein the community carries out self-analysis, identifies their problems, and creates development proposals, programs, and strategies derived from their own point of view. The life plans define the community’s life; their principles are related to their world vision, territoriality, historic memory, spirituality, culture, identity, autonomy, collectivity, and address the peoples’ physical and cultural integrity and continuance (DNP, 2016, page 34).

Act 70 of 1993 estipulates black communities’ rights based on the transitory article 55 of the Political Constitution of 1991. This Act recognizes the collective property of the black communities that have occupied fallow lands in rural zones of the Pacific basin, according to their traditional production practices (DNP, 2016, page. 24).

DNP, 2014.

Bioeconomía y sectores potenciales en Colombia, Biointropic, 2018. Misión de crecimiento verde. Departamento Nacional de Planeación.

MAVDT, 2010

Green business relates to economic activities offering goods and services that generate positive environmental impacts and incorporate good environmental, social, and economic practices focused on the life cycle, which contribute to environment conservation as natural capital that supports the territorial development. According to the PNNV classification, there are three green business categories: i) sustainable goods and services derived from biodiversity; ii) industrial eco-products; and iii) carbon markets. The project will be focused on category i) covering three sectors: a) sustainable agro-ecosystems; b) bio-commerce; and c) restoration.

GEF Project #2551 “Protected Areas Conservation Trust Fund.

CCS are understood as “geographic defined areas, other than PAs, aiming at maintaining and promoting the contribution of nature to society while supporting in situ biodiversity conservation through long-term governance involving one or multiple stakeholders (public, private and/or community).”

CODECHOCÓ, 2016

Idem.

Ecofondo, 2008; INVEMAR, 2016; CODECHOCÓ, 2016.

This figure refers to the sum of total population for the five mosaic municipalities (Acandí, Unguía, Riosucio, Carmén del Darién and Juradó), according to DANE projections up to 2017.

DANE, 2005.

Red ORMED & PNUD, 2013.

Red ORMED & PNUD, 2013

Codechocó, ANIAF, 2011

The LCI quantifies and characterizes the living conditions of poor and non-poor people, covering also the poverty phenomenon by including variables related to housing, utilities and household members, goods ownership, and perception of the head of household or spouse regarding the living conditions at home. (DNP), 2005.

Idem.

DANE, 2010.

DNP.

UMAIC, 2017.

DANE, 2005.

Around 80% of coffee produced in Colombia, and 60% of the country’s international trade leaves by this port.

Municipal development Plan, 2016

Production data for the municipality of Buenaventura, taken from the document on Productive Profile (Red ORMED & PNUD, 2013).

DNP, 2005.

Departamento Administrativo para la Prosperidad Social, 2011.

UMAIC, 2017.

CORPONARIÑO, 2016.

CORPONARIÑO, 2011.

DANE, 2005.

Production data taken from the document of Productive Profile for Tumaco municipality (Red ORMED & PNUD, 2013) and from the Departmental Development Plans for Barbacoas, Ricaurte and Mallama municipalities.

SIMCI/UNODC, 2016.

DNP 2005.

Idem.

UMAIC, 2017.

DANE, 2005.

DNP, 2005.

DANE, 2010.

DNP, 2005.

UMAIC, 2017.

DANE, 2005.

DNP, 2005.

DANE, 2010.

DNP, 2005.

UMAIC, 2017.

Idem.

These direct and indirect movers are recognized as processes affecting biodiversity in its space presence in a specific territory and its manifestations of genes, species and ecosystems (MADS, 2012).

IDEAM, 1990-2013, in: Calderon, et. al, 2016.

IDEAM, 2011.

IDEAM, 2014.

CODECHOCÓ, 2016.

CVC, 2016.

IDEAM press release. November 2014.

GEF6 PIF: GEF, FAO, UNIDO, 2017

Idem.

IDEAM, 2014.

UNODC, 2013.

United Nations System in Colombia and Ministry of Environment and Sustainable Development. September 2014. Environmental considerations for building a stable, lasting and sustainable peace in Colombia territorial - inputs for discussion. Bogotá, DC, Colombia.

GEF6 PIF: GEF, FAO,UNIDO, 2017

MADS, 2012 en IDEAM, 2014.

From: http://gefbiodiversidadymineria.wwf.org.co/mercurio/#1500477952631-973c6389-729f

GEF6 PIF: GEF, FAO, UNIDO, 2017

CORPONARIÑO, 2016.

CVC, 2016.

El Tiempo, 2014.

GEF6 PIF GEF-FAO,UNIDO, 2017.

Idem.

CODECHOCÓ 2016.

Delgado et al., 2008; CORPONARIÑO, 2016; CVC, 2016.

IDEAM, PNUD, MADS; DNP, CANCILLERÍA. 2017.

Idem.

The multidimensional analysis of Vulnerability and Risk due to climate change was based on the main dimensions used in ND-GAIN international study (http://index.nd-gain.org:8080/documents/ nd-gain_technical_document_2015.pdf), adapted to national approaches in sessions with experts. Definition of food security, hydrological resource and biodiversity dimensions is outlined as follows: Food security: Food and nutritional security is defined by the national government in the document Conpes 113 as the sufficient and stable availability of food, access and timely and permanent consumption of them in amount, quality and safety by all people, under conditions allowing their proper biological utilization, to have a healthy and active life. In this case the component of “availability” was prioritized as per denomination of Observatorio de Seguridad Alimentaria y Nutricional de Colombia for manioc, rice, plantain, panela cane sugar, potato, corn, bean, coffee, as well as the associated risks. Hydrological resource: This dimension is aimed at identifying the relationship of the human settlements and the hydrological resource regarding use and availability. The component has as conceptual reference the Estudio Nacional del Agua (IDEAM, 2014). Biodiversity and ecosystem services: This dimension relates the provision ecosystem service to species classified as “of use” in the analysis of endangered species listed in the national red books with threat category (in critical danger, in danger and vulnerable). Under this dimension the change in natural plant cover was modeled for 2040 under the scenario RCP 6.0. (Idem, page 30).

Casas, et. al 19998; DNP, 2016; CODECHOCÓ, 2016.

Andrade, 2013.

Calderón, et. al, 2016.

Fergusson, et al. 2014, en: Calderón, et. al, 2016

Calderón, et. al, 2016; ONU-Ambiente, 2017.

ONU-Ambiente, 2017.

In Katíos a strategic and urgent afforestation project is in course given the current circumstances of accelerated deforestation. The forestry usage needs to be organized in a participative way towards the resource sustainable use, establishment of low impact exploitations, portable sawmills, generation of higher added value to timber-yielding products, identification and use of productive and extractive alternatives, and promote the management ability of communities and their organizations.

Source: GEF6 PIF (GEF-FAO-UNIDO).

Planning instrument that regionalizes and complements the provisions of the SINAP Action Plan.

From: GEF6 PIF: GEF-FAO-ONUDI.

DNP, 2016. CONPES 3687

Idem.

From: http://lasillavacia.com/silla-pacifico/los-pdet-en-el-pacifico-contrarreloj-64349.

MADS, PNN, Moore Foundation, WWF, Natural Patrimony Fund, WCS and CI. 2018. Technical program document (in construction).

Businesses that bet on biodiversity in Chocó. WWF, UNDP; GEF Small Grants Program. 2017

From: https://prezi.com/bebuxncb4wom/ffem-proyecto-manejo-forestal sostenible/?utm_campaign=share&utm_medium=copy

From: https://www.sinchi.org.co/cooperacion.

Idem

This corresponds to goods and/or services obtained from the sustainable use of native and/or cultivated biodiversity. Goods include products extracted from nature and crops cultivated from agro-biodiversity; services include nature-based tourism.

Final consultancy report: PFNM biogeographic Chocó - WWF TX71 agreement. Financing Fund: GEF. Consultant: Mabel Gisela Torres Torres Ph.D. in Biological Sciences. Quibdó, 2016

PNUD, GIZ. Consideraciones ambientales para la construcción de una paz territorial, estable, duradera y sostenible en Colombia, 2014.

Project GEF #2551.

Project GEF #5288.

World Bank. 2006. Project document related to the grant proposal of the Global Environmental Fund (GEF), Project of Fondo Nacional de Áreas Protegidas in Colombia. Report No: 35125 – CO. World Bank, and quoted in Santamaría M., Barona A., Rey N, Orjuela M. y Chaves M.E. 2012 Mosaicos de Conservación. Fondo Patrimonio Natural, Bogotá D.C. Colombia.

Santamaría M., Barona A., Rey N., Orjuela M. y Chaves M.E. 2012 Mosaicos de Conservación. Fondo Patrimonio Natural, Bogotá D.C. Colombia. This publication has been an output of the GEF Mosaic Project.

The way that an approximation of the measurement of the socio-ecosystemic connectivity can be performed. In the case of ecosystems, analysis of the ecological connectivity and functionality related to the PAs and the complementary conservation strategies is suggested. The social component should be directed to an Analysis of Social Networks within said ecosystem connection corridors, identifying the existing relationships between society and the natural areas and the environmental products that comprise them (goods, capital, and information). (Velázquez and Aguilar 2005; Clark 2006). Within the territorial context of the project, this implies integrated articulation with black communities and indigenous peoples who are present in the conservation mosaics.

GEF Project #5288, FAO GEF Project Document, page 49.

PIF-FAO-UNIDO, 2017.

Rincón et.al 2014.

The economic assessment activities performed by the IIAP (2012) will be complementary inputs to this evaluation, based on their methodological contribution and results in the territory, as some of them have been conducted in areas that are part of the mosaics. These include: Páramo del Duende and Tatamá (Tatamá–Serranía de Paraguas Mosaic), the Dagua dry forest (Farallones–Calima Mosaic), Tumaco mangroves (Cabo Manglares–Gran Familia Awa Mosaic), and the Bajo Atrato wetland complex (see baseline by MUCB).

In the spaces for local dialogue (local workshops by mosaic) that were held during the project development stage, the priority ecosystem services in the three main mosaics were: Katíos–Caoba mosaic: subsistence by fishing, cultural identity, physical support: transportation, water supply; Farallones–Calima mosaic: forest-related services: wood, fuel, species habitat and refuge, water supply and tourism; Cabo Manglares–Gran Familia Awa mosaic: water supply, subsistence by fishing, water regulation, forest related-services: wood, fuel, climate regulation, and species habitat and refuge.

Among the methods for the ecological assessment, the ecosystem services mapping tool INVEST (Integrated Valuation of Ecosystem Services and trade-offs) is highlighted through its analysis of: flow of materials, inputs and outputs, ecological integrity, landscape fragmentation, and functional diversity. Based on this, a total economic assessment (Valoración Económica Total [VET, according to its Spanish acronym]) is proposed for articulation of values that transforms all the potential values into one common unit—the monetary unit. The VET is constituted by the (direct and indirect) use and non-use (optional, legacy, existence) values with methods such as productivity change, avoided cost, replacement cost, hedonic prices, contingent assessment, and benefit transfer. In the cultural assessment, methods such as direct observation, interviews, and workshops, plus information from the rest of the assessment exercise will allow the construction of sustainability and welfare social indicators.

Tradeoff is understood as the balance achieved between two opposing features resulting from management and other actions that are not intentional and alter the quantity or quality of an ecosystem service. Tradeoffs may be spatial among beneficiaries or temporary (Rincón et. al 2014).

The aim of output 1.1.2 is to safeguard ecosystem services, cultural and biological diversity

This refers to the territorial zoning plans (POT]), the territorial planning scheme (EOT), or basic plan of territorial zoning (PBOT), and departmental plans for territorial zoning (PDOT).

The management plan of the Integrated Management District Lago Azul Los Manatíes, which is recognized as the ethno-development plan of the Communal Councils of COCOMAUNGUÍA, and the natural resources administration and management plans supported by CVC for the communal councils corresponding to Farallones–Calima conservation mosaic are highlighted. These plans include land use definition through environmental zoning, and support, as necessary, for the definition of parts of the plan that are related to natural resources management and administration instruments.

http://siatpc.iiap.org.co/index.php?page=acerca.

Project outputs: i) strengthening of SIAC and the institutes’ information systems; ii) generation and availability of information on territorial and environmental planning, and iii) biodiversity sustainable use and green businesses. Intervention areas and beneficiaries: i) Caribbean: Ciénaga Grande de Santa Marta (CORPMAG; local communities in the buffer zone of the Vía Parque Isla de Salamanca and Santuario de Flora y Fauna CGSM PAs; ii) Amazoiía: Vistahermosa municipality (DMI Special Management Area Macarena Norte). Cormacarena; iii) Pacific: North: Utría, Golfo de Tribugá–Cabo Corrientes and the traditional fishing area (ZEPA); Bajo and Medio Atrato: Unguía, Carmen del Darién, Riosucio, Communal Councils of Cocomacia, Ascoba, communities in the buffer zone of Katíos NNP. Codechocó (source: https://www.sinchi.org.co/cooperacion).

For this activity the following precedents will be considered: i) the diploma course conducted within the framework of the GEF project Conservation of Biodiversity in Landscapes Impacted by Mining in the Chocó Biogeographic Region; ii) the development of interdisciplinary projects by the Observatory of Ethnic Territories led by Pontificia Universidad Javeriana jointly with the Department of Rural and Regional Development of the Faculty of Environmental and Rural Studies, and which is co-financed by the Spanish Cooperation Agency for Development  (Agencia Española de Cooperación para el Desarrollo [AECID]); this observatory proposes to support the strengthening of the self-governance of ethnic groups with regard to territorial administration and to provide tools contributing to enhance the response capacity of the government to territorial demands by the country’s indigenous and rural communities; iii) the experience of the Fundación Universitaria Claretiana in the Colombian Pacific region, highlighting among its nine Religious Centers the centers located in Quibdó and Tumaco; its undergraduate program includes Social Work and Anthropology, and post-graduate degree in of Social Services Management, among others; iv) the strategy of diploma courses with regional approach developed by the IIAP with institutional support, known as Permanent Institutional Provision of Local Dialogues (Diálogos Locales de Oferta Permanente Institucional [DOPI]).

This amount corresponds to the addition of principal PAs in the conservation mosaics (Farallones NNP, Munchique NNP, Tatamá NNP, Los Katíos NNP, Cabo Manglares IMRD), plus the Río Bravo Natural Reserve in the Farallones–Calima MUCB.

The buffer zones do not correspond to a formally defined polygon, they are associated with the management approach for the PAs, related to the definition of actions in their management plans going beyond their borders and allowing the reduction of pressures on the PA and shaping a buffer function in their areas of influence, and/or territorial planning processes to be carried out by the territorial entities for these areas that will mitigate and prevent disturbances to the PAs, contribute to compensate for the alteration occurring due to the effects of pressures on these areas, harmonize occupancy and territory transformation with conservation objectives of the PAs, and contribute to biophysical elements, cultural elements and values, environmental services conservation, and ecological processes related to the PAs.

Area of the PA under jurisdiction of the CODECHOCÓ.

Forest and landscape restoration is an active process that brings together people to identify, discuss, and implement practices that restore the optimal balance among the agreed-upon ecological, social, and economic benefits of forests and trees in wider land use patterns. (FAO, 2017).

The term agroforestry collectively designates the land use techniques and systems where evergreen woody plants (trees, bushes, palm trees, bamboo, etc.) are intentionally used on the same surface unit that is occupied by crops or animals, with some spatial order or time sequence. In agroforestry systems there are both ecological and economic interactions among the different components. (FAO, 2017).

IPCC 2000

FPIC is a specific right of indigenous and black peoples. This is part of Human Rights and the universal right to self-determination. In addition, FPIC is recognized by the International Labor Organization (ILO) Covenant 169, the United Nations Declaration on Rights of Indigenous Peoples (UNDRIP), the Convention on Biological Diversity (CBD), and normative provisions on this subject at the national level based on the political constitution, national legislation, and jurisprudence (Sentences of the Constitutional Court).

Landscape management tools for biodiversity conservation in rural regions are landscape elements that constitute or improve habitat, increase functional connectivity, or simultaneously accomplish these functions in benefit of native biodiversity. Source: Renjifo, L. M; AristizáBal, S. L; Lozano-Zambrano, F. H; Vargas, W; Vargas, A. M.; RamíRez, D. P. 2009. Diseño de la estrategia de conservación en el paisaje rural (Fase II). 85- 119 p. In: Lozano-Zambrano, F. H. (ed). Herramientas de manejo para la conservación de biodiversidad en paisajes rurales. Instituto de Investigación de Recursos Biológicos Alexander von Humboldt y Corporación Autónoma Regional de Cundinamarca (CAR). Bogotá, D. C., Colombia. 238 p.

The FFS as a training methodology gathers farmers periodically to exchange experiences, using the field as a learning resource where observation, analysis, and discussion take place, and appropriate decisions are made on the sustainable management of a productive system (FAO, 2017).

Corresponds to goods and services obtained from the sustainable use of native and/or cultivated biodiversity. Goods include products extracted from the natural environment and agrobiodiversity crops; services include nature-based tourism.

UNEP World Conservation Monitoring Centre, 2005, Sistema de Apoyo a las Decisiones CEPFOR. Guía del Usuario v 4.0.

Uso de la biodiversidad, una oportunidad para la paz. Guía para para identificar y fortalecer los encadenamientos productivos de bienes y servicios de la naturaleza con potencial de uso. PNUD- Corporación Biocomercio Sostenible-SENA. Bogotá. 2016.

This corresponds to the 12 criteria related to the business economic feasibility, environmental aspects, life cycle approach, social responsibility, communication of attributes, etc., that are evaluated by the MADS and environmental authorities to grade the green business companies at the following levels: initial, basic, intermediate, satisfactory advanced, and ideal.

Bioeconomía y sectores potenciales en Colombia, Biointropic, 2018. Misión de crecimiento verde. Departamento Nacional de Planeación.

It refers to standards associations, mandatory and voluntary technical regulations, certification associations, inspection associations, testing laboratories, and National Metrology Institute that enable the government and consumers to ensure that products in the market comply with minimum quality and sustainability standards.

It is every type of tourism based on nature, where the main motivation is nature observation and appreciation, as well as traditional cultures. (OMT, 2002)  Definition accepted by the government of Colombia.

One list of indigenous reservation and communal councils being part of the biodiversity use and conservation mosaics where the project will be implemented is included in Annex 8.

Compliance Reviews following complaints related to the Organization’s environmental and social standards: http://www.fao.org/aud/42564-03173af392b352dc16b6cec72fa7ab27f.pdf

The surface area will be measured during the project implementation stage.

https://www.unido.org/sites/default/files/2015-01/UNIDO_ENVIRONMENTAL_AND_SOCIAL_SAFEGUARDS_POLICIES_AND_PROCEDURES_0.pdf

http://www.fao.org/3/a-i4413e.pdf

El CD podrá modicarse en el primer año de ejecución con la finalidad lograr una mayor operatvidad del proyecto.

Given that the government does not have enough space in its headquarters in the city of Cali to house the project technical team, an office will be rented.

The PC, the BH, the LTO and the FAO/GEF Coordination Unit should assign ratings to the PIR every year. The ratings can or cannot coincide among the project managers.

http://www.fao.org/capacitydevelopment/the-three-dimensions-of-the-fao-capacity-development-framework/en/20.

Criteria existing within the environmental standards will be considered in addition to validated land use capacity.

Refers to documents, mapping inputs and, in general, instruments that incorporate issues around cultural diversity, biodiversity, and ecosystem services, as well as respect for and preservation of traditional knowledge associated with biodiversity management. The project will recognize as inputs for these guidelines the instruments developed by the black and indigenous populations—mainly in relation to environmental zoning, the results of ecosystem services strategic evaluation—mainly the cultural ecosystem services. In addition, it will consider the work on environmental and social safeguards conducted by United Nations agencies such as FAO, UN Environment, and MADS, among others. The national interpretation of environmental and social safeguards will be reviewed within the UNREDD program framework, and in general, the progress concerning the Safeguard Information System by UN Environment. Likewise, progress made in this matter within the framework of the GEF project Conservation of Biodiversity in Landscapes Impacted by Mining in the Chocó Biogeographic Region (GEF ID 4916) will be considered (refer to the chapter on environmental and social safeguards in the project development framework).

As a reference to obtain an approximate number, the exercise of prioritizing conservation in the SIRAP Pacific was considered. The number of 210,193 ha refers to conservation priorities (whose use is proposed for protection and restoration for conservation) located in at least one Community Council (CC) and one Indigenous Reservation (IR) in each of the priority MUCBs. In the Katíos-Caoba MUCB it refers to a conservation priority area in the Cacarica River CC (41,405 ha), in the Salaquí River CC (14,421 ha) and Salaquí and Pavarandó IR (30,580 ha); in Farallones-Calima MUCB to an area in CC Medio, Bajo and coastal zone of San Juan "ACADESÁN” (20,276 ha), in the CC of Cuenca Baja of the Calima River (5,117 ha) and in the Yu Yic Kwe IR (1,467 ha); in Cabo Manglares-Gran Familia Awá MUCB, an area in the CC Bajo Mira and Frontera (32,867 ha), in El Gran Sabalo IR (8,001 ha) and in La Turbia IR(16,206 ha); in Munchique-Saija River MUCB, an area in the CC of El Playón of the Siguí River (17,043 ha), in the CC of Parte Baja of the Saija River (4,745 ha) and in Calle Santa Rosa Saija River IR (3,356 ha); in Tatamá-Serranía de Paraguas MUCB, an area in the CC Medio, Bajo, and coastal zone of San Juan "ACADESÁN” (2,314 ha) and in the Unificado Chamí of San Juan River IR (12,395 ha).

The “socio-ecosystem connectivity” indicator refers to the methodology used in the GEF project Bio-Caribbean Connection to design the project’s socio-ecosystem connectivity areas. This model conducts a spatial analysis with the following inputs framed within three principles: Principle 1: Key areas for provision of materials (water, wood, food), key areas for species life cycles and regulation of habitat (key species habitat), important areas for cultural enjoyment and cultural identity (areas of cultural and archaeological heritage, ecotourism attractions, and existence value); Principle 2: PAs of SINAP, CCS; Principle 3: areas of territorial stress and territorial alliances.

As a precedent, four exercises are identified for an economic assessment of ecosystem services conducted in the area of the MUCBs: Paramo of Duende and Tatamá (Tatamá-Paraguas MUCB), Dry Forest of Dagua (Farallones-Calima MUCB), Mangroves of Tumaco (Cabo Manglares- Awa MUCB), and Wetland Complex of Bajo Atrato.

The aim of output 1.1.2 is to safeguard ecosystem services, cultural and biological diversity

Area corresponding to a basin selected in the CORPONARIÑO zoning plan, it refers to the Mira river basin (65.000 ha).

Priority participatory structures will be supported within the framework of the SIRAP Pacific operational structure; this structure has platforms that correspond to 4 levels: regional, departmental, sub-regional, and local. One (1) SIRAP Pacific Regional Roundtable (General Assembly and Technical Committee); five (5) Roundtables of Departmental PA Systems  (SIDAP): Risaralda, Nariño, Cauca, Valle del Cauca, and Chocó; two (2) SIDAP Nariño Sub-regional Roundtables: Pacific and Coastal Foothills; one (1) SIDAP Cauca Sub-regional Roundtable: Pacific Roundtable; two (2) SIDAP Valle del Cauca Local Roundtables: East Pacific and West Pacific; five (5) SIDAP Chocó Sub-regional Roundtables: Pacific Coast, Atrato, Baudó, San Juan, and Darién; six (6) Local PAs Systems–SILAP of SIDAP Chocó: San José del Palmar, Acandí, Unguía, Carmen de Atrato, Nuquí, Tadó; Local conservation actions of bio-cultural diversity of Pacific region per department; one (1) Thematic Sub-system of protected marine areas: SAMP (articulated to the SIRAP Pacific and SIRAP Caribbean). In total, there are 71 delegates within these platforms (Vásquez, 2015).

One regional platform will be supported, and five departmental, sub-regional, or local platforms in the MUCBs, one prioritized per MUCB.

One prioritized platform will be supported in each MUCB. Around 140 local participation platforms are estimated among indigenous cabildos’ assemblies, communal councils’ assemblies and regional associations’ assemblies, in addition to local participation platforms of civil society organizations.

Corresponds to Cabo Manglares- Bajo Mira IMND.

For example: The local roundtable of use, occupancy, and ownership of the Munchique NNP, the co-management roundtable that will be created within the management process framework of the new Cabo Manglares IMND, the technical committees of the CVC PAs, among other spaces existing in the framework of PNN use and management agreements.

These data correspond to the addition of hectares covered by the new areas identified for MUCBs, consisting of Relictos de Caoba Juradó (63,686 ha) for Katios – Caoba MUCB, Serranía de los Paraguas (191,561 ha) in Serranía Paraguas – Tatamá MUCB; and Calle Santa Rosa (3,356 ha) in the Munchique – Río Saija MUCB.

The area of 210,193 ha refers to conservation priorities (whose use is proposed for protection and restoration for conservation) located in at least one Community Council (CC) and one Indigenous Reserve (IR) in each MUCB as follows: a) Katíos-Caoba MUCB: Cacarica River CC (41,405 ha), Salaquí River CC (14,421 ha), and Salaquí and Pavarandó IR (30,580 ha); b) Farallones-Calima MUCB: middle, lower, and coastal zone of San Juan "ACADESÁN” CC (20,276 ha), Cuenca Baja of Calima River CC (5,117 ha), and Yu Yic Kwe IR (1,467 ha); c) Cabo Manglares-Gran Familia Awá MUCB: Bajo Mira and Frontera CC (32,867 ha), El Gran Sabalo IR (8,001 ha), and La Turbia IR (16,206 ha); d) Munchique-Saija River MUCB, El Playón of Siguí River CC (17,043 ha), Lower Saija River CC (4,745 ha), and Calle Santa Rosa Saija River IR (3,356 ha); e) Tatamá-Serranía de Paraguas MUCB: middle, lower, and coastal zone of San Juan "ACADESÁN” CC (2,314 ha), and Unificado Chamí of San Juan River IR (1,395 ha).

Three groups of biodiversity products have been identified for natural ingredients: 1) natural colors: achiote, jagua; 2) fats and oils: açai, mil pesos, noli, cocoa, coconut, chontaduro, donpedrito; and 3) Food: cocoa, coconut, borojó, açai, chontaduro, vanilla. All these products have potential for current markets and demands by natural ingredients companies, mainly cosmetics and food.

The aim of output 1.1.2 is to safeguard ecosystem services, cultural and biological diversity

FAO Policy on Indigenous and Tribal Peoples  http://www.fao.org/fileadmin/user_upload/newsroom/docs/FAO_policy.pdf

FAO Policy on Gender Equality http://www.fao.org/docrep/017/i3205e/i3205e.pdf

https://www.unido.org/sites/default/files/2015-10/GC.16_8_S_Gender_Equality_and_Empowerment_of_Women_Strategy__2016-2019_0.pdf

http://www.fao.org/3/a-i3114s.pdf

https://www.thegef.org/sites/default/files/publications/Indigenous_Peoples_Principle_SP.pdf

http://www.fao.org/3/a-i6190e.pdf

http://www.ilo.org/wcmsp5/groups/public/---americas/---ro-lima/documents/publication/wcms_345065.pdf

http://www.un.org/esa/socdev/unpfii/documents/DRIPS_es.pdf

http://www.fao.org/fileadmin/user_upload/newsroom/docs/FAO_policy.pdf

http://www.fao.org/3/a-i4413e.pdf

www.unido.org/sites/default/files/2015- /UNIDO_ENVIRONMENTAL_AND_SOCIAL_SAFEGUARDS_POLICIES_AND_PROCEDURES_0.pdf

The life plans are planning exercises oriented towards the physical and cultural continuity of indigenous peoples, and are characterized based on community dynamics and collective constructions wherein the community members perform self-analysis, identify their problems and create development proposals, programs, and strategies based on their own point of view. These life plans define the community or people, their principals of cosmovision, territoriality, historical memory, spirituality, culture, identity, autonomy, and collectivity (DNP, 2016, page 34).

Act 70 of 1993 develops the black communities’ rights based on the transitory article 55 of the Political Constitution of 1991. This Act recognizes the collective property of the black communities that have occupied fallow lands in the rural areas of the Pacific basin, according to their traditional production practices (DNP, 2016, page. 24).

By conservation of 602,811 ha (new protected areas and complementary conservation strategies).

Pacífico: desarrollo socioeconómico con equidad, integración y sostenibilidad ambiental. DNP.

Caracterización y análisis de Competitividad de la Cadena de Ingredientes Naturales para el Sector Cosmético y Cosméticos Naturales. Swiss contact-Corporación Biocomercio Sostenible.2017.

Cost of fuel in Bogotá $ 8889; Cali $ 8894 and Medellín $ 8839 to January 2018

http://sostenibilidad.semana.com/medio-ambiente/articulo/paraisos-colombianos-para-observar-aves/38824

http://www.fao.org/docrep/017/i3205e/i3205e.pdf

https://www.unido.org/sites/default/files/2015-10/GC.16_8_S_Gender_Equality_and_Empowerment_of_Women_Strategy__2016-2019_0.pdf

https://www.thegef.org/sites/default/files/council-meeting-documents/C.40.10.Rev1_.Safeguards_Policy_Spanish_Translation.Final__1.pdf

http://www.fao.org/3/a-i3114s.pdf

DANE Census 2005. Retrieved from Presidency Counseling for Women. Women’s situation in Colombia, Chocó and in the Pacific region- Figures and indicators.

DANE Great Integrated Survey of households. Retrieved from Presidency Counseling for Women. Women’s situation in Colombia, Chocó and in the Pacific region- Figures and indicators.

Idem

Profamilia-ENDS 2010. Retrieved from Presidency Counseling for Women. Women’s situation in Colombia, Chocó and in the Pacific region- Figures and indicators.

DANE ‐EEVV Maternal Mortality Rate (per 100000 live births). Retrieved from Presidency Counseling for Women. Women’s situation in Colombia, Chocó and in the Pacific region- Figures and indicators.

Description of Homicide Behavior. Colombia, 2010 ‐ National Institute of Legal Medicine and Forensic Sciences. Retrieved from Presidency Counseling for Women. Women’s situation in Colombia, Chocó and in the Pacific region- Figures and indicators.

Acción Social Estadísticas Desplazados y DANE Estimaciones de la Población. Tomado de Consejería presidencia para la mujer. Situación de las mujeres en Colombia  y en Chocó y la región Pacífica-Cifras e indicadores.

Full intervention refers to the execution of all the project outputs in the MUCBs.

Partial intervention refers to the execution of priority outputs (defined in the participatory workshops conducted during the PPG stage) in the MUCBs.

According to Gentry (1986), the forests of the Colombian Pacific region are estimated to contain one of the richest plant communities in the world. In the Catalogue of Plants and Lichens of Colombia, of the 24,528 species of vascular plants recorded, 6,052 species are in the Pacific Region (Bernal, R., S.R. Gradstein and M. Celis (eds.), 2015).

Idem.

Ecofondo, 2008.

Playona Loma La Caleta IMRD.

IDEAM, 2014.

The reference area for this calculation is the management scope of SIRAP Pacific: 7,338,028.2 ha of land ecosystems, and 1,533,070.5 of aquatic ecosystems; cartographic sources: IDEAM 2010-2012.

The reference area for this calculation is the management scope of SIRAP Pacific: 1,533,070.5 of aquatic ecosystems; cartographic source: IDEAM 2010-2012.

From: GEF6 PIF: GEF, FAO, ONUDI, 2017

Casas et al. 1998.

Ecofondo, 2008.

INVEMAR, 2016.

Idem.

The reference area for this calculation is the management scope of SIRAP Pacific: 453,499.7 ha coastal ecosystems, 161,155 ha marine ecosystems; cartographic source: IDEAM 2010-2012.

From: PIF (GEF-FAO-ONUDI, 2017)

MinCIT, 2015

The UBN methodology used to determine, using simple indicators, if the basic needs of the population are met. The groups not reaching a minimum threshold are classified as poor. The indicators selected are: unsuitable housing, overcrowded housing, housing with insufficient utilities, households with high economic dependence, households with school-aged children who do not go to school. (DANE: https://www.dane.gov.co/index.php/estadisticas-por-tema/pobreza-y-condiciones-de-vida/necesidades-basicas-insatisfechas-nbi)

Problemática humanitaria en la región pacífica colombiana. Defensoría Delegada para la Prevención de Riesgos de Violaciones a los Derechos Humanos y DIH. Bogotá. 2016.

Ethos Regional, 1 000 copies, number 11, septiembre – diciembre 2014. Santiago de Cali, Universidad Autónoma de Occidente. Centro Interdisciplinario de Estudios de la Región Pacífico Colombiana, CIER, cier@uao.edu.co

https://www.unido.org/sites/default/files/2015-01/UNIDO_ENVIRONMENTAL_AND_SOCIAL_SAFEGUARDS_POLICIES_AND_PROCEDURES_0.pdf

http://www.fao.org/3/a-i4413e.pdf

REDD+ es la reducción de emisiones causadas por la deforestación, la degradación de los bosques, la conservación y aumento de las reservas de carbón y el manejo forestal sostenible.

https://www.thegef.org/sites/default/files/publications/Indigenous_Peoples_Principle_SP.pdf

http://www.fao.org/3/a-i6190e.pdf

http://www.ilo.org/wcmsp5/groups/public/---americas/---ro-lima/documents/publication/wcms_345065.pdf

http://www.un.org/esa/socdev/unpfii/documents/DRIPS_es.pdf

http://www.fao.org/fileadmin/user_upload/newsroom/docs/FAO_policy.pdf

http://www.fao.org/3/a-i4413e.pdf

www.unido.org/sites/default/files/2015- /UNIDO_ENVIRONMENTAL_AND_SOCIAL_SAFEGUARDS_POLICIES_AND_PROCEDURES_0.pdf