GEF-6 REQUEST FOR PROJECT ENDORSEMENT/APPROVAL

Project Type:

Type of Trust Fund: GEF Trust Fund

For more information about GEF, visit TheGEF.org

part i: project information

| Project Title: Contributing to the integrated management of biodiversity in the Pacific Region of Colombia to build peace |  |  |  |  |
| --- | --- | --- | --- | --- |
| Country(ies): | Colombia | GEF Project ID: |  | 9441 |
| GEF Agency(ies): |  | GEF Agency Project ID: |  | 638260 (FAO) 160054 (UNIDO) |
| Other Executing Partner(s): | Ministry of Environment and Sustainable Development (MADS), National Natural Parks of Colombia (PNN), Regional System of Protected Areas of the Pacific - SIRAP Pacific (IIAP, CARs) | Submission Date: Re-submission Date: |  | 21-Nov-2018 6 March 2019 |
| GEF Focal Area (s): |  | Project Duration (Months) |  | 60 |
| Integrated Approach Pilot | IAP-Cities IAP-Commodities IAP-Food Security |  | Corporate Program: SGP |  |
| Name of Parent Program | N/A (not applicable) | Agency Fee ($) |  | 718,443 |

- Focal Area  Strategy Framework and Other Program Strategies

| ### Focal Area Objectives/Programs | ### Focal Area Outcomes | ### Trust Fund | ### (in $) |  |
| --- | --- | --- | --- | --- |
|  |  |  | ### GEF Project Financing | ### Co-financing |
| BD-4 Program 9 | Outcome 9.1 Increased area of production landscapes and seascapes that integrate conservation and sustainable use of biodiversity into management |  | 2,393,186 | 11,935,127 |
| BD-1 Program 1 | Outcome 1.2: Improved management effectiveness of protected areas. |  | 2,233,274 | 6,225,476 |
| LD-3 Program 4 | Outcome 4.1: SLM mainstreamed in development investments and value chains across multiple scales |  | 711,782 | 3,379,545 |
| SFM-1 Program 1 | Outcome 1: Cross-sector policy and planning approaches at appropriate governance scales, avoid loss of high conservation value forests. |  | 1,067,672 | 4,624,638 |
| SFM-2 Program 5 | Outcome 3: Increased application of good management practices in all forests by relevant government, local community (both women and men) and private sector actors. |  | 1,156,644 | 5,229,400 |
| Total project costs |  |  | 7,562,558 | 31,394,186 |

- Project description summary

| ### Project Objective: To mainstream the sustainable use and conservation of biodiversity and the provision of ecosystem services in vulnerable landscapes of the Colombia’s Pacific region in view of generating global and local environmental benefits and supporting the peace process. |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| ### Project Components/ ### Programs | ### Financing Type | ### Project Outcomes | ### Project Outputs | ### Trust Fund | ### (in $) |  |
|  |  |  |  |  | ### GEF Project Financing | ### Confirmed Co-financing |
| Component 1: Institutional strengthening to support pro conservation and sustainable use in the Pacific region of Colombia. |  | 1.1 The territorial and environmental management planning instruments are harmonized with the instruments developed by the black communities and indigenous peoples to safeguard biological, cultural, and ecosystem services diversity, leading to a general reduction in potential threats from development- oriented activities. Indicators: − Project targeted area (hectares – ha) for reducing current and potential pressures from competing land uses and forest degrading land-uses: 44,084,957 ha (marine area: 34,762,783 ha; continental area: 9,322,174 ha) corresponding to the SIRAP Pacific management area (indirect target landscape) of which at least 1,061,655 ha (direct total area). − 210,193 ha of strategic importance for biodiversity conservation outside PAs that apply guidelines and are managed to be included in the planning instruments under improved management. 1.2 Improved stakeholders’ capacity and participation to support the enforcement of harmonized planning and environmental management in the MUCBs. Outcome 1.2 Indicators: − Increase in the SIRAP Pacific’s management capacities measured through the GEF Development Capacity Scorecard: SIRAP Pacific Technical Regional Roundtable, from 29% to 44%. | 1.1.1 A Diagnosis and Strategic Assessment of the ecosystem services in the Pacific Region. Target Output 1.1.1: Ecosystem services assessed in 4 Biodiversity Use and Conservation Mosaics (MUCBs). 1.1.2 Agreed guidelines on harmonization of departmental/municipal territorial plans and Indigenous Peoples’/black communities’ instruments, with a gender approach. Targets Output 1.1.2: 1 Guidelines. 24 planning instruments reached. 6 pilot areas in MUCBs. Gender chapter included. 1.1.3 A tailor-made and open-access SIAT_PC (integrated with the Environmental Information System of Colombia - SIAC) - strengthened to harmonize the existing planning mechanisms in the Pacific Region. 1.1.4 Forest Zoning and Management Plans outside the PAs developed, updated, and implemented in a participatory way, promotes socio-ecosystem connectivity at the MUCB level. 1.2.1 Six (6) SIRAP Pacific participation and decision-making structures, strengthened and with enhanced capacities to apply harmonized guidelines (see 1.1.2). 1.2.2 Five (5) local community participatory structures, strengthened and with enhanced capacities to comply with harmonized guidelines (see 1.1.2) |  | 1,333,199 | 6,654,641 |
| Component 2: Integrated management of protected areas (PAs), buffer zones and ‘complementary conservation strategies’ (CCSs) . |  | 2.1 Reduction of pressures and threats to biodiversity and ecosystem services in 581,859 ha of existing PAs and their buffer zone. Indicator targets: − Management effectiveness of PAs measured by the METT; a) Katios National Natural Park (NNP): 76; b) Farallones NNP: 77; c) Tatamá NNP: 78; d) Munchique NNP: 78; e) Cabo Manglares Bajo Mira and Frontera Integrated Management National District (IMND): 48; f) Río Bravo RFPR: 50, − 1,000 ha restored. − 10,646 tCO2-eq sequestered. 2.2 New PAs and CCSs receive support for management planning and implementation. Indicators: − 258,603 ha of new PAs under declaration process (three public PAs). − 210,193 ha sustainably managed through communal CCSs. | 2.1.1 Management plans and governance mechanisms developed and/or adopted include support for the implementation of priority actions in the selected areas. 2.1.2 One financial sustainability strategy designed and implemented for ensuring participation within the SIRAP Pacific framework. 2.1.3 Forest restoration and soil recovery plans for PAs, buffer zones, connectivity areas, and corridors are developed and implementation is kick-started in a participatory manner. 2.2.1 Planning and management instruments developed, with priority actions implemented in CCSs, by the forest-dependent communities. 2.2.2 One Technical guidelines as support for the regulatory process to formalize the CCSs in the Pacific region considering ethnic/cultural aspects and in line with the national process. 2.2.3 Priority areas for conservation are assessed and steps towards their declaration as formal PAs are taken. |  | 2,680,399 | 10,089,487 |
| Component 3: Sustainable production practices as alternatives for local development, biodiversity protection and peace process support. |  | 3.1. Biodiversity and ecosystem services are sustainably utilized in forest-based productive systems and generate multiple environmental and socio-economic benefits. Indicators: − 10,000 ha under sustainable production systems benefiting 1,000 families. − 40% of sustainable forest management (SFM) initiatives and production systems led by women. 3.2 Products and services derived from biodiversity have value added and their value chains duly strengthened. Indicators: − The annual average income of beneficiary communities is maintained or increased from USD $1,240 per year per family to USD $1,364 per year per family (at least 10% increase) for the operation of the biodiversity products value-added units. − Seven (7) value-added units of biodiversity-derived products with technical and management capacities. − At least five (5) biodiversity-derived products with access to formal markets, and fulfilling the requirements for quality, MADS green business criteria, and other standards. − Four (4) community-based nature tourism initiatives strengthened that safeguard biological, cultural, and ecosystem services diversity with government and non-government support. | 3.1.1 Green Business action plan(s) harmonized and under implementation for fostering and developing diversified production systems are agreed upon and modalities adapted to local conditions, for supporting food security, sustainable livelihoods, landscape-level connectivity and forest rehabilitation. Target output 3.1.1: 25 green business initiatives with priority actions supported. 3.1.2 SFM initiatives and sustainable production systems implemented incorporating good soil and biodiversity-friendly practices, with gender approach. 3.2.1 Value-added units of biodiversity-derived products created and strengthened, with technical and management training that safeguard cultural, biological, and ecosystem services’ diversity. 3.2.2 Biodiversity-derived products with market access and/or enhanced compliance with quality requirements, MADS green business criteria, and other standards for market access. 3.2.3 Community-based nature tourism initiatives strengthened with government and non-government support that safeguard cultural, biological, and ecosystem services’ diversity. |  | 2,874,296 | 12,899,320 |
| Component 4: Knowledge management and project monitoring and evaluation (M&E). |  | 4.1 Project monitored and evaluated with a results-based management approach, and communication of lessons learned | 4.1.1 Five (5) participatory action plans for the prioritized MUCBs. 4.1.2 An online M&E platform 4.1.3 One (1) communication strategy for development implemented 4.1.4 One Mid-term Review (MTR) and one Terminal Evaluation (TE). |  | 314,542 | 255,777 |
| Subtotal |  |  |  |  | 7,202,436 | 29,899,225 |
| Project Management Cost (PMC) |  |  |  |  | 360,122 | 1,494,961 |
| Total project costs |  |  |  |  | 7,562,558 | 31,394,186 |

- confirmed sources of Co-financing for the project by name and by type

Please include evidence for co-financing for the project with this form.

| Sources of Co-financing | Name of Co-financier | Type of Cofinancing | Amount ($) |
| --- | --- | --- | --- |
| Recipient Government | Ministry of Environment and Sustainable Development (MADS) | In-kind | 1,196,757 |
|  | PNN | In-kind | 1,548,715 |
|  | Institute of Environmental Research of the Pacific (IIAP) | In-kind | 484,838 |
|  | Institute of Marine and Coastal Research José Benito Vives de Andreis (INVEMAR) | In-kind | 41,143 |
|  |  | Cash | 106,800 |
|  | Departmental Government of Nariño | In-kind | 4,215,227 |
|  |  | Cash | 504,823 |
|  | Departmental Government of Chocó | In-kind | 72,012 |
|  |  | Cash | 96,833 |
|  | Regional Autonomous Corporation of Risaralda (CARDER) | In-kind | 274,264 |
|  |  | Cash | 135,824 |
|  | Regional Autonomous Corporation of Valle del Cauca (CVC) | Cash | 5,871,918 |
|  | Regional Autonomous Corporation of Nariño (CORPONARIÑO) | In-kind | 93,429 |
|  |  | Cash | 6,546,997 |
|  | Regional Autonomous Corporation for Sustainable Development of Chocó (CODECHOCÓ) | Cash | 3,547,790 |
|  | Major Communal Council of del Alto San Juan (ASOCASAN) | In-kind | 170,010 |
|  | Communal Council of the Cacarica River Watershed - Chocó | In-kind | 118,748 |
|  | Reservation Comunidad La Sierpe Reservation Calle Santa Rosa | In-kind | 40,500 |
| Beneficiaries | Communal council of Bajo Mira and Frontera | In-kind | 157,611 |
|  | Corporación Biocomercio Sostenible - CBS Colombia | In-kind | 395,926 |
|  | BIOINNOVA | In-kind | 731,768 |
|  | Fundación San Cipriano | In-kind | 108,488 |
|  | UNIDO | In-kind | 800,000 |
|  |  | Cash | 2,423,765 |
|  | FAO | In-kind | 510,000 |
|  |  | Cash | 1,200,000 |
| Total Co-financing |  |  | 31,394,186 |

- Trust Fund  Resources Requested by Agency(ies),  Country(ies) and the Programming of Funds

| GEF Agency | Trust Fund | Country Name/Global | Focal Area | Programming of Funds | (in $) |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | GEF Project Financing (a) | Agency Fee a) (b)2 | Total (c)=a+b |
| FAO | GEFTF | Colombia | Biodiversity | n/a | 2,683,791 | 254,960 | 2,938,751 |
| UNIDO | GEFTF | Colombia | Biodiversity | n/a | 1,942,669 | 184,554 | 2,127,223 |
| FAO | GEFTF | Colombia | Land Degradation | n/a | 711,782 | 67,619 | 779,401 |
| FAO | GEFTF | Colombia | Sustainable Forest Management | SFM | 2,224,316 | 211,310 | 2,435,625 |
| Total Grant Resources |  |  |  |  | 7,562,558 | 718,443 | 8,281,000 |

a ) Refer to the Fee Policy for GEF Partner Agencies

- Project’s Target Contributions to GEF 6 Core Indicators

Update the relevant sub-indicator values for this project using the methodologies indicated in the Core Indicator Worksheet (as used in GEF 7 Endorsement template – Annex E) and aggregating them in the table below. Progress in programming against these targets is updated at mid-term evaluation and at terminal evaluation. Achieved targets will be aggregated and reported any time during the replenishment period. There is no need to complete this table for climate adaptation projects financed solely through LDCF and SCCCF.

| Project Core Indicators |  | Expected at CEO Endorsement |
| --- | --- | --- |
| 1 | Terrestrial protected areas created or under improved management for conservation and sustainable use (Hectares) | 650,180 |
| 2 | Marine protected areas created or under improved management for conservation and sustainable use (Hectares) | 190,282 |
| 3 | Area of land restored (Hectares) | 1,000 |
| 4 | Area of landscapes under improved practices (excluding protected areas)(Hectares) | 220,193 |
| 5 | Area of marine habitat under improved practices (excluding protected areas) (Hectares) | NA |
|  | Total area under improved management (Hectares) | 1,061,655 |
| 6 | Greenhouse Gas Emissions Mitigated (metric tons of CO2e) | 3,600,703 |
| 7 | Number of shared water ecosystems (fresh or marine) under new or improved cooperative management | NA |
| 8 | Globally over-exploited marine fisheries moved to more sustainable levels (metric tons) | NA |
| 9 | Reduction, disposal/destruction, phase out, elimination and avoidance of chemicals of global concern and their waste in the environment and in processes, materials and products (metric tons of toxic chemicals reduced) | NA |
| 10 | Reduction, avoidance of emissions of POPs to air from point and non-point sources (grams of toxic equivalent gTEQ) | NA |
| 11 | Number of direct beneficiaries disaggregated by gender as co-benefit of GEF investment | 4,000 (40% women, 60% men)* |

* 1,000 families (4 members per family) benefiting from the implementation of SFM initiatives and sustainable production systems.

Provide additional explanation on targets, other methodologies used, and other focal area specifics (i.e., Aichi targets in BD) including justification where core indicator targets are not provided.

- Project Taxonomy

Please update the table below for the taxonomic information provided at PIF stage. Use the GEF Taxonomy Worksheet provided in Annex F to find the most relevant keywords/topics/themes that best describe the project.

| Level 1 | Level 2 | Level 3 | Level 4 |
| --- | --- | --- | --- |
| Influencing Models | Strengthen institutional capacity and decision-making |  |  |
| Stakeholders | Indigenous Peoples |  |  |
|  | Private Sector | Financial intermediaries and market facilitators, Individuals/Entrepreneurs |  |
|  | Beneficiaries/ Local Communities/ Civil Society | Community Based Organization, Non-Governmental Organization, |  |
|  | Type of Engagement, | Information Dissemination, Partnership, Consultation, Participation, |  |
|  | Communications | Awareness, Raising Education |  |
| Capacity, Knowledge and Research | Capacity Development |  |  |
|  | Knowledge Generation and Exchange |  |  |
|  | Learning | Theory of Change, Adaptive Management, Indicators to Measure Change |  |
|  | Knowledge and Learning | Knowledge Management, Capacity Development, Learning |  |
|  | Stakeholder Engagement Plan |  |  |
| Gender Equality | Gender mainstreaming | Beneficiaries, Women groups, Sex-disaggregated indicators, Gender-sensitive indicators |  |
|  | Gender results areas | Access and control over natural resources, Participation and leadership, Access to benefits and services, Capacity development, Knowledge generation |  |
| Focal Area/Theme | Biodiversity | Protected Areas and Landscapes | Terrestrial Protected Areas, Coastal and Marine Protected Areas, Productive Landscapes, Community Based Natural Resource Management |
|  |  | Mainstreaming | Tourism, Agriculture & agrobiodiversity, Certification (national standards), Certification (International Standards) |
|  |  | Species | Threatened species |
|  |  | Biomes | Mangroves, Wetlands, Rivers, Tropical Rain Forests, Paramo |
|  |  | Financial and Accounting | Conservation Finance |
|  | Forest | Forest and Landscape Restoration |  |
|  | Land Degradation | Sustainable Land Management | Restoration and Rehabilitation of Degraded Lands, Sustainable Agriculture, Sustainable Forest/Woodland Management |
|  |  | Food Security |  |
| Rio Marker | Climate Change Mitigation 0 Climate Change Adaptation 0 |  |  |

part ii:  project justification

A. describe any changes in alignment with the project design with the original pif

A.1. Project Description. Elaborate on:

1) The global environmental and/or adaptation problems, root causes and barriers that need to be addressed. NA

2) The baseline scenario or any associated baseline projects.

- An update baseline scenario is provided in Section 1.2.2 Baseline Initiatives of the FAO-GEF Project Document.

3) The proposed alternative scenario, GEF focal area strategies, with a brief description of expected outcomes and components of the project.

- The project design is closely aligned with the original PIF. The structure of the project components closely resemble the PIF that was approved by the GEF. A description of the project components is included in Section 1.3.2 (Objectives, Outcomes, and Outputs) of the FAO-GEF Project Document. Minor changes were made to the project’s outputs; however, these do not represent a departure from the project’s strategy as defined originally in the PIF, nor will they have an impact on the funds originally budgeted. These changes are described as follows:

| PIF Outputs (Component 1) | Project Document Outputs (Component 1) |
| --- | --- |
| 1.1.2: Biodiversity, ecosystem services and cultural aspects safeguards mainstreamed in land-use plans through pilot projects in departments and municipalities. | 1.1.2 Agreed guidelines on harmonization of departmental/municipal territorial plans and Indigenous Peoples’/black communities’ instruments , with a gender approach. Component 1 will focus on addressing the existing barriers that prevent the harmonization of government instruments for territorial planning and environmental management with the instruments developed by black communities and indigenous peoples, mainly due to the differences between the types of land uses that are more appropriate from the production, environmental, and sociocultural rural perspectives, and because of the need to include elements in these instruments that safeguard cultural, biological, and ecosystem services’ diversity. Accordingly, this project output was reworded to specify this. |
| 1.1.3: A tailor-made and open-access territorial planning system integrated into the Environmental Information System of Colombia (SIAC) of the National Environmental System (SINA), and strengthened to serve as a “planning umbrella” to harmonize all existing planning mechanisms and frameworks for the Pacific region leading to a cohesive and environmentally- sound planning process detailing prescribed land-uses | 1.1.3 A tailor-made and open-access SIAT_PC (integrated with the Environmental Information System of Colombia - SIAC) - strengthened to harmonize the existing planning mechanisms in the Pacific Region. The output basically remains the same, but was slightly reworded to clarify its scope. |
| Output 1.1.4: Forest Management Plans are developed for high-value biodiversity areas outside of protected areas, infusing strong socio-environmental safeguards into these plans, and their implementation is kick-started with project support, promoting ecological connectivity at the landscape level | 1.1.4 Forest Zoning and Management Plans outside the PAs developed, updated, and implemented in a participatory way, promotes socio-ecosystem connectivity at the MUCB level. In addition to supporting Forest Management Plans that will benefit 2,000 ha, the project will support the updating of two Forest Zoning Plans covering 65,000 ha. |
| Output 1.2.1: Capacity development modules for stakeholders and governance systems established for collaborative land use management, with gender approach | 1.2.1 Six (6) SIRAP Pacific participation and decision-making structures, strengthened and with enhanced capacities to apply harmonized guidelines (see 1.1.2). The output was reworded to indicate that capacity development will also benefit the organizations and members that make up the SIRAP Pacific. |
| Output 1.2.2: Community-based participatory networks established for monitoring and safeguarding compliance with prescribed land-uses, with gender approach. | 1.2.2 Five (5) local community participatory structures, strengthened and with enhanced capacities to comply with harmonized guidelines (see 1.1.2) . The output was reworded to indicate that capacity building at the community level will focus on strengthening the community’s ability to ensure compliance with agreements regarding the harmonization of government instruments for territorial planning and environmental management with the planning instruments developed by local communities. |
| PIF Outputs (Component 2) | Project Document Outputs (Component 2) |
| 2.1.1: Management Plans and governance mechanism for selected forest PAs developed and implemented (410,000 hectares) | 2.1.1 Management plans and governance mechanisms developed and/or adopted include support for the implementation of priority actions in the selected areas. The output basically remains the same; however, the area benefiting from improved PA management increased from 410,000 ha to 581,859 ha. |
| 2.1.2: Strategies for the Financial Sustainability of SIRAP Pacific designed and implemented | 2.1.2 Financial sustainability strategy designed and implemented for ensuring participation within the SIRAP Pacific framework. The output was reworded to indicate that the financial sustainability of the SIRAP Pacific will also ensure the availability of resources to support the participation of the members of the SIRAP Pacific in meetings and assemblies, among other events. |
| 2.1.3: Forest restoration and soil recovery plans for protected areas or buffer zones, connectivity areas and corridors are developed and implementation is kick-started in 2,000 ha (to be fully defined during full project preparation) | 2.1.3 Forest restoration and soil recovery plans for PAs, buffer zones, connectivity areas, and corridors are developed and implementation is kick-started in a participatory manner The output basically remains the same; however, the area to be restored through the project was reduced from 2,000 ha to 1,000 ha following a feasibility analysis conducted during the PPG phase. |
| 2.2.1: Natural resource management plans are prepared and implemented in CCS areas and ICCAs by the forest-dependent communities (300,000 hectares) | 2.2.1 Planning and management instruments developed, with priority actions implemented in CCSs, by the forest-dependent communities The output was reworded to indicate that instead of natural resource management plans, the project will focus on the implementation of planning and management instruments for CCSs only; accordingly, the area benefiting from these actions was reduced from 300,000 ha to 210,193 ha. |
| 2.2.2: Legal feasibility study for ‘Indigenous and Community Conserved Areas’ (ICCAs) leads the way for the incorporation of these areas into an overall conservation strategy for the country (the Pacific Region spearheads this). | 2.2.2 Technical guidelines as support for the regulatory process to formalize the CCSs in the Pacific region considering ethnic/cultural aspects and in line with the national process. The output was reworded to indicate that the project will focus on CCSs rather than ICCAs. The definition of the regulatory process (legal feasibility) will be done as part of the baseline initiatives; accordingly, the project will develop technical guidelines to support this process. |
| Output 2.2.3: Potential new regional PAs with high-value forests are assessed and steps towards their declaration as formal PAs taken (150,000 hectares) | 2.2.3 Priority areas for conservation are assessed and steps towards their declaration as formal PAs are taken The output basically remains the same; however, the area of the new PAs to be created through the project increased from 150,000 ha to 258,603 ha. |
| PIF Outputs (Component 3) | Project Document Outputs (Component 3) |
| 3.1.1: ‘Green Business action plan(s)’ harmonized and under implementation: The location and management frameworks for fostering and developing diversified production systems (among them, agroforestry, industry and services) are agreed upon and modalities adapted to local conditions, for supporting food security, sustainable livelihoods with strong economic linkages, landscape-level connectivity and forest rehabilitation | 3.1.1 Green Business action plan(s) harmonized and under implementation for fostering and developing diversified production systems are agreed upon and modalities adapted to local conditions, for supporting food security, sustainable livelihoods, landscape-level connectivity and forest rehabilitation. The output basically remains the same, the location and management frameworks for fostering and developing diversified production systems and the types of systems to be implemented are specified in the description of output activities. |
| Output 3.1.2: Sustainable production systems implemented incorporating good soil and biodiversity-friendly practices (1000 families, 10,000 hectares) | 3.1.2 SFM initiatives and sustainable production systems implemented incorporating good soil and biodiversity-friendly practices, with gender approach. In addition to sustainable production systems, the project will support the implementation of SFM initiatives; the number of families benefiting (1,000 families) and area covered (10,000 ha) remains the same. |
| 3.2.1: Processing units for forest products have acquired technical and management training. | 3.2.1 Value-added units of biodiversity-derived products created and strengthened, with technical and management training that safeguard cultural, biological, and ecosystem services’ diversity. The output basically remains the same; however, the wording was modified to clarify its scope. |
| 3.2.2: At least 5 biodiversity-derived products with market access and certified by sustainable production standards. | 3.2.2 Biodiversity-derived products with market access and/or enhanced compliance with quality requirements, MADS green business criteria, and other standards for market access. The output was reworded to emphasize that the biodiversity-derived products with market access will comply with national standards; in addition, voluntary certification of quality and sustainability requirements and standards of products may be supported, including organic certification, Union for Ethical BioTrade (UEBT), fair trade, good manufacturing practices, organic standards, and Participatory Guarantee Systems (PGS), among others. |
| 3.2.3: Two (2) sustainable tourism initiatives conceived, planned at the landscape level, their feasibility assessed and tenders launched to attracting private sector investments that will abide by the strongest social-environmental safeguards, given the region’s ecological sensitivity. | Community-based nature tourism initiatives strengthened with government and non-government support that safeguard cultural, biological, and ecosystem services’ diversity. The wording of the output was modified to clarify its scope, and instead of two (2) sustainable tourism initiatives the project will support (4) initiatives. |
| PIF Outputs (Component 4) | Project Document Outputs (Component 4) |
| NA | 4.1.1 Participatory action plans for the prioritized MUCBs. This output was added; participatory action plans for the prioritized MUCBs will be developed and the areas where the activities will be implemented on the ground will be determined through consensus among all the interested parties. |
| 4.1.2: Best practices and lessons learned systematized and disseminated. | 4.1.3 Communication strategy implemented Best practices and lessons learned will be systematized and disseminated as part of the communication strategy for the project. |

4) Incremental/additional cost reasoning and expected contributions from the baseline, the GEFTF and co-financing.

- No changes from PIF. There was an decrease in co-financing (USD3,905,814 )  due to the fact that some of the co-financiers indicated during  the PIF stage  did not confirmed their commitments with the project during the PPG phase, and institutional changes due to the Integral Rural Reform conducted by the national government that resulted in the closure of the Land Consolidation Administrative Unit (indicated in the PIF as co-financier for an amount of USD 4,000,000 USD)

5) Global environmental benefits (GEFTF).

- Although there were no changes to the incremental/additional cost reasoning and approach, there are some slight changes to the global environmental benefits to be delivered:

- The project will strengthen protection and sustainable use of these forest ecosystems, safeguarding, enhancing and generating multiple social and environmental benefits derived from them. These include the maintenance of globally significant biodiversity in 1,032,023 ha, including 258,603 ha of new PAs. In addition, 210,193 ha will be sustainably managed through the CCSs in communal territories. Local and indigenous communities managing these areas will in turn enjoy improved tenure security preserving their associated traditional heritage.

- Due to the focus on the sustainable management of carbon-rich forests, the implementation of the project is also likely to avoid the emission of 3,590,056.88 t CO2-eq  into the atmosphere as avoided deforestation. In addition, through the forest restoration actions initiated by the project (1,000 ha), but likely to reach maturity after the project’s duration, 10,646 tCO2-eq will be sequestered. Estimates of carbon benefits are included in Appendix 10 of the FAO-GEF Project Document.

6) Innovativeness, sustainability and potential for scaling up.

- To achieve social sustainability, the project will employ participatory approaches in identifying the interests, needs, and priorities of both men and women. Men and women will participate in decision-making processes and the sustainable management of biodiversity so that their different roles and responsibilities are considered. The stakeholder engagement process started during full project preparation. The participatory planning processes (Output 4.1.1) will provide continuity and will underline the need to adopt actions and measures that consider the differences and inequalities among certain populations (e.g., indigenous peoples, black communities, and rural communities) to ensure the protection of their rights. The project will promote actions to strengthen the capacities of indigenous, Black communities, and rural community representatives in the MUCBs to make decisions about biodiversity conservation and sustainable use, and to support traditional mechanisms for participation (e.g., assemblies, councils, etc.). Decision-making spaces within the SIRAP Pacific framework will be supported. The project will also promote the creation of community-based information exchange networks for knowledge-sharing from older community members to the youth, and between communities. By using a participatory approach, the project will adopt mechanisms that promote interest, motivation, and ensure trust, providing a favorable environment for social equality and lead to the elimination of dispositional, physical, communication barriers. In addition, FAO Farmers Field Schools (FFS) methodology will be applied, where possible, to promote knowledge-sharing on traditional biodiversity management. FFS will serve as places to hold meetings and exchange ideas and strengthening social relationships among the MUCBs’ inhabitants.

- FAO’s Farmer Field School (FFS) is an approach based on people-centred learning. Participatory methods to create an environment conducive to learning: the participants can exchange knowledge and experience in a risk free setting. Practical field exercises using direct observation, discussion and decision making encourage learning-by­doing. The field is the space where local knowledge and outside scientific insights are tested, validated and integrated, in the context of local ecosystem and socio-economic settings. Community-based problem analysis is the entry point for a FFS group to develop a location specific curriculum. A growing range of technical topics are being addressed through FFS: soil, crop and water management, seeds multiplication and varietal testing, IPM, agropastoralism, aquaculture, agroforestry, nutrition, value chain, and link to markets, etc (http://www.fao.org/farmer-field-schools/overview/en/)

- The project activities will contribute directly or indirectly to the environmental sustainability of the project through the following:

- Strengthening integrated landscape management in the Colombian Pacific region through harmonizing territorial planning and management instruments at the departmental and municipal levels, incorporating ethnic perspectives of the territory, sectoral interests, and institutional policies to safeguard cultural, biological, and ecosystem services diversity.

- Supporting the sustainable use of biodiversity and ecosystem services within the framework of the peace-building process, based on sustainable development goals. Environmental governance will be consolidated by strengthening existing participatory structures, as well as implementing monitoring mechanisms of biodiversity mainstreaming and land uses.

- Improving the conservation and management status of regionally and globally important ecosystems by creating  new PAs and improving the management of existing PAs.

- Promoting the recognition of CCS by the national government, and their access to technical and financial resources.

- Strengthening of free access SIAC – PC , which will lead to a cohesive landscape planning process.

- Developing forest zoning plans (POFs), forest management plans, and ecological restoration plans outside the PAs to ensure sustainable land management in MUCB priority areas.

- Supporting biodiversity-friendly production and promoting sustainable production systems, market access, livelihoods alternatives, natural resources conservation and sustainable use, increased family income and business development.

- Developing a participatory communication strategy to raise awareness among key stakeholders and decision- makers at the national, sub-national, and local levels about the significance of biodiversity and socio-ecosystem connectivity in MUCB.

- Financial and economic sustainability will be ensured through the provision of cash and in-kind resources; co-financing by project partners; investments in conservation, restoration, and sustainable production within the framework of institutional action plans; departmental development plans; and territorial zoning plans (POTs). Project partners (PNN, SIRAP, departmental governments and municipalities) will have annual budget allocations designated for activities implemented to safeguarding the diversity of cultural, biological, and ecosystem services. This will cover project actions and in other sectors – both addressed in institutional plans. The design and implementation of the SIRAP Pacific financial sustainability strategy will ensure economic resources needed to host participatory and decision-making spaces.

- The project will also contribute to CCS’ financial sustainability through the participatory development of management tools, sustainable use of resources and effective CCS management. The project will promote sustainable production systems that are aimed at conserving and managing ecosystem services in the long-term and improve local livelihoods – including SFM  and production plans. These plans will include a strategy for technical support, capacity development, and a store network that will supply value-added units. Outcome 3.2 will focus specifically on (at least) five biodiversity-derived products with access to the market. The compliance with the quality requirements, MADS’ green business criteria and other standards are expected to generate higher income and employment for producer families, while supporting BD sustainable use and conservation. Additionally, community-based nature tourism initiatives will be strengthened through Component 3. This will generate new jobs in targeted communities and supplementary income for local households participating in the project. Eco-tourism actions will also contribute to the long-term conservation and sustainable use of biodiversity.

- The project will address the sustainability of capacity development

- The project will address the three dimensions of capacity development (CD) identified in FAO’s Approach to Sustainability : i) individuals (small-scale farmers, households, female-led households); ii) institutions (departmental and local governments, SIRAP Pacific, CARs, indigenous peoples/black communities structures, networks, associations); and iii) the policy enabling environment (new environmental governance strategy; enhanced institutional capacities through trainings). The interaction between community members and local CSOs, and between CSOs and DAGs will be also addressed.

- CD activities will be focused on strengthening the managerial and technical skills of the national and local institutions, producer associations, civil society and local communities. At institutional level, the project will strengthen the SIRAP Pacific structures, the departmental governments, and CSOs to facilitate multi-stakeholder coordination. CD will maximize the institutionality of multiple public and private stakeholders in the design of policies and strategies on sustainable management of natural resources, biotrade, sustainable land management, and forestry. Training and raising awareness among stakeholders will improve the environmental governance in the local context (enabling environment).

- At field level, the promotion of best practices will be based on methodologies already used in the country (e.g. farmer field schools, extension, farmer-to-farmer), local knowledge, and collective community work. Training methods and modules will take into account local ethno-cultural knowledge to ensure the mainstreaming of cultural issues in the proposals for plans and strategies, sustainable best practices, and forest conservation and management. Ethno-cultural knowledge will be combined with current technologies to be promoted by the project. Training events (e.g. courses, workshops, tours, field days) will be timely programmed to ensure the participation of beneficiaries, especially women. In sum, stakeholders’ ownership of best practices will contribute to the sustainability of the acquired capacities. Systematized lessons learned will also contribute to CD sustainability.

- Potential for scaling up: Project activities will be mainstreamed into public policies and newly created structures at local, regional and national level. This will generate synergies with partners in the short-, medium- and long-term. Output 1.1.2 will build guidelines with high replicability potential in other regions of Colombia facing post-conflict. Interventions targeting the PAs and voluntary CCSs will lead to experiences and lessons learned applicable in the wider SIRAP Pacific area and the National System of Protected Areas (SINAP) framework.

- The project will design production and supply plans; develop value-added units in the MUCBs; strengthen technical, administrative, and management capacities; increase market access; and implement green business plans. Component 3 will apply a value chain approach, replicable in other areas of Colombia and adapted to agro-climatic and logistical conditions, as well as transformed products. By and large the vision of component 3 impose the promotion of a sustainable business model that incorporates sustainable biodiversity use and the participation of indigenous peoples, black communities, and rural people.

- Systematization of the project experiences will be performed jointly with FAO and UNIDO, to promote the lessons learned and serve as replication mechanism.  FAO and UNIDO will also communicate the project outcomes and lessons learned to other projects in the country, Latin America region, and to each agency.

A.2. Child Project? No

A.3.  Stakeholders. Please provide the Stakeholder Engagement Plan or equivalent assessment. Please refer to Appendix 9 of the FAO-GEF Project Document.

In addition, provide a summary on how stakeholders will be consulted in project execution, the means and timing of engagement, how information will be disseminated, and an explanation of any resource requirements throughout the project/program cycle to ensure proper and meaningful stakeholder engagement.

- During full project formulation, the first three steps of the FPIC were completed: 1. Identification of indigenous peoples and black communities and their representatives. 2. Participatory mapping: workshops were conducted in each prioritized MUCB as well as meetings to inform about the project, collect baseline information, define the project results, and define the project activities. Entities and representatives of ethnic groups that are part of the Regional Roundtable of the SIRAP Pacific participated in meetings and workshops. 3. Design of a communication plan to disseminate the project results, with local beneficiary communities and parties interested in the project.

- The successful implementation of the project will largely depend on the effective communication and coordination with the multiple project stakeholders and the implementation of participatory mechanisms. The key national and sub-national stakeholders include the MADs, PNN), SIRAP Pacific, Regional Autonomous Corporations (CARs; CVC, CODECHOCO, CORPONARIÑO, CRC, CARDER), IIAP, INVEMAR, and Ministry of Agriculture and Rural Development (MADR). At the local level, the most relevant stakeholders are Departmental and Municipal Governments, organizations of indigenous peoples, black communities, and rural people, CSOs, and non-governmental organization (NGOs). The extensive stakeholder consultations and engagement that began during the PPG phase will be continued throughout project implementation. To achieve this the project will make use of several mechanisms, including: a) Project Inception Workshop, where the project will be presented to stakeholders at the national. Subnational, and local levels; b) Project Steering Committee: will be comprised of representatives of the governmental agencies, and special interest groups and will be responsible for approving the annual work plans, participation in the recruitment processes, and provide overall strategic guidance to the project; c) Project Implementation Unit (PIU): responsible for the implementation of the stakeholder engagement plan, communications plan, gender action plan, grievance mechanism, and M&E; d) Communications and Dissemination of Information: the PIU will implement a stakeholders communication plan to ensure communication with all stakeholders using a variety of  methods (meetings, telephone calls, listserv, WhatsApp, etc.),  will hire the services of communication specialists to achieve the objectives of the plan, and will have active knowledge management with the documentation of processes and lessons learned, which will be shared with all stakeholders; e) Local Committees to facilitate local stakeholder participation: will be established in all five MUCBs where field activities will be implemented; f) Gender Action Plan: will secure the involvement of both genders, but especially women who are often marginalized and whose participation in agricultural and natural resource-based activities is low compared to men; g) Grievance Mechanism: will be established and published so that all stakeholders are aware of its existence, allowing the documentation of any potential grievances and ensuring they are addressed in a timely manner; h) Activities, Training, and Engagement Plans: will use a participatory approach that is rights-based and integrates the perspectives of all stakeholders using bottom-up approaches and integrating the different views of local stakeholders and beneficiaries; and i) Decentralized M&E: including meetings with the local committees, interviews with direct beneficiaries, local and national participatory workshops, and meetings with special groups such as women to verify indicators.

- The Project Coordinator and the National Project Director (NPD) will have a key role in maintaining fluid and permanent communication about the project with the interested parties at all levels in order to maintain stakeholders’ interest in and commitment to the project during its lifespan. The different decision-making spaces of the project (PSC, Regional Technical Committee, and MUCB Technical Committees) will also serve as vehicles for communication and to increase visibility regarding the project objectives and approaches. Outcome 4.1.3 specifically addresses developing and implementing the communication strategy that will be designed in a participatory way for the local beneficiary communities, project partners, territorial entities, CSOs, and other parties interested in project execution to be duly informed about how the project develops and be able to provide and receive information on the project’s details and progress. The communication activities for project development and visibility will be planned during the first 6 months of the project to ensure participation of interested parties, as well as access to relevant information. The communication strategy will seek participation, dialogue, and improvement of the project outcomes’ visibility. Any specific visibility arrangement requested by the partners will also be considered. A Communications Expert will be hired who will be responsible for developing the project communications strategy at the project outset and coordinating its implementation across all project components. The Communications Expert will work closely with a Geographic Information System (GIS)/M&E Expert on knowledge management and M&E aspects of the project.

Select what role civil society will play in the project:

Consulted only;

Member of Advisory Body; contractor;

Co-financier;

Member of project steering committee or equivalent decision-making body;

Executor or co-executor;

Other (Please explain)

A.4. Gender Equality and Women's Empowerment. Provide the gender analysis or equivalent socio-economic assessment. (Type response here; if available, upload document or provide link) Gender Analysis is included under Appendix 13 of the FAO-GEF Project Document

Does the project expect to include any gender-responsive measures to address gender gaps or promote gender equality and women’s empowerment? (yes  /no) If yes, please upload gender action plan or equivalent here. Gender Action Plan is included in Appendix 13 of the FAO-GEF Project Document

If possible, indicate in which results area(s)  the project is expected to contribute to gender equality:

closing gender gaps in access to and control over natural resources;

improving women’s participation and decision making; and or

generating socio-economic benefits or services for women.

Does the project's results framework or logical framework include gender-sensitive indicators? (yes  /no).

- Five (5) local participatory structures strengthened for ensuring compliance with guidelines, using a gender-based approach.

- 40% of SFM initiatives and production systems led by women.

# A.5 Risk. Elaborate on indicated risks, including climate change, potential social and environmental risks that might prevent the project objectives from being achieved, and, if possible, the proposed measures that address these risks at the time of project implementation.(table format acceptable):

| Description of risk | Impact | Probability of occurrence | Mitigation actions | Responsible party |
| --- | --- | --- | --- | --- |
| POLITICAL RISK |  |  |  |  |
| Political instability: change of government and senior officials’ turnaround in national, regional, and local agencies (ministries, departmental and municipal administrations, and environmental authorities). | The national, regional, and local policies and land use/territorial planning instruments will continue not to be harmonized. Disorganized public actions will deepen environmental degradation. Low participation from national and local authorities in the project. Limited ownership of project outcomes and GEBs. | Medium | The project will keep the representatives from key national authorities (MADS, PNN), sub-national agencies (CARs, SIRAP Pacific), departmental and municipal territorial entities, informed on project progress, achievements, and benefits. Roles and responsibilities during project implementation will be re-validated at inception and monitored on yearly basis. If there is a change of government, the Project Team will re-visit the agreement with the new administration. The key project partners (PNN, CODECHOCO, CARDER, CVC, CRC, CORPONARIÑO, IIAP, INVEMAR, MADS, and the Departmental Governments of Chocó and Nariño) have committed co-financing to materialize their interest in the project. | Project Committees and Project Coordinator (PC) |
| Local authorities show limited interest in the project and reflect a lack of willingness to take part in project activities |  |  | The project will generate participation and discussion spaces with project partners through the Project Steering Committee (PSC), Project Technical Committee (PTC), and MUCB Technical Committees. Local stakeholders will be part of agreements to implement MUCB action plans. They will be periodically reviewed and adjusted to keep up the local interest. |  |
|  |  |  | The project will promote institutional strengthening and will develop capacities of local technical teams and local communities to harmonize planning instruments. This will contribute to maintaining interest in the project at the local level. |  |
|  |  |  | The project will adopt a participatory approach, through SIRAP Pacific structures and other mechanisms. The economic incentives and production alternatives will encourage the participation of municipal authorities in project activities. |  |
| Project co-financiers do not comply with the co-financing commitments. | The project does not achieve the expected impact due to lack of available co-financing as part of the GEF alternative. | Low | The project will keep co-financiers informed regarding their financial commitments to the project. Within the framework of the PSC, matters related to co-financing contributions will be coordinated to ensure these commitments are included in the annual budgetary allocations of the partner entities. The PC will provide advice to the project Executing Partners in reporting in-kind and cash co-financing provided by co-financers and eventually other partners not foreseen in the Project Document. |  |
| SOCIAL RISK |  |  |  |  |
| Lack of interest and low participation by traditional authorities, local communities, and community leaders | Persistence of deforestation problems, changes in land use, habitat fragmentation, unsustainable production practices, and loss of ecosystem services. | Medium | The project includes a Stakeholder Engagement Plan for indigenous peoples, black communities, and rural communities within the Free, Prior, and Informed Consent (FPIC) framework. The plan implementation will ensure the active participation and local ownership by beneficiary communities, including women, youth, and the elderly. | PC, local authorities, indigenous peoples’ and black communities’ representatives, and community leaders |
|  | Local livelihoods are not improved. Socio-economic and environmental benefits are not delivered. Food insecurity and environmental degradation have increased. |  | Project activities are gender-sensitive and have been designed to promote the participation of beneficiary communities in meetings and roundtables, and in workshops to develop capacities. The project will promote the application of sustainable production practices, and access to economic incentives and markets for local biodiversity-based products. New business models are expected to generate an improvement in local living conditions (Component 3). Additionally, the project will strengthen and ensure respect for and recognition of the traditional knowledge systems associated with biodiversity. Traditional authorities, local communities, and community leaders will obtain tangible social, economic, and environmental benefits, which will contribute to promoting interest in the project. |  |
|  | Delay in implementing the project activities. |  | To avoid delays, the PSC, PTC, and MUCB committees will be established at project inception, ensuring the early engagement of project stakeholders, including representatives and leaders of beneficiary black communities, indigenous, and peasant communities, which will be key to supporting the implementation of activities in the field (i.e., MUCBs). Stakeholders and project partners will be informed on their roles in these committees and the decision-making processes. In line with the project M&E plan, PSC meetings will be held periodically to define the Annual Work Plan and Budget (AWP/B) and review the Project Progress Report (PPR) and PIR, allowing the close monitoring of the implementation of project activities. |  |
|  |  |  | Mechanisms for fair and equitable distribution of project socio-economic and environmental benefits will be defined at inception. Benefits are detailed as follows: organizational strengthening and capacity building of beneficiary local communities, participation strategies, harmonization of life/ethno development plans, support for the CCSs, community-based monitoring of SFM plans, improvement of household incomes through the marketing of biodiversity-derived products and the promotion of eco-tourism initiatives, and improved knowledge-sharing and information access for decision-making). |  |
|  |  |  | The project formulation phase was compliant with initial FPIC requirements. In PY1 agreements will be set and signed with ethnic representatives of local beneficiary communities for implementing the MUCB action plans, in the framework of FPIC. |  |
| Low participation of women, youth, and the elderly. | The situation of invisibility and vulnerability of rural women continues. | Low | The project will apply a gender-sensitive approach and will ensure fair and equitable distribution of project benefits among women and men. The project will enhance participation of organizations of women, youth, and the elderly in decision-making processes, training events, and access to economic incentives. Additionally, as part of the project M&E strategy, gender-based indicators are included to evaluate benefits and collect gender-disaggregated data on gender mainstreaming. Likewise, the project implementation team will include an expert in participation, ethnic and gender approaches as part of the strategy to ensure the active participation of women, youth, and the elderly. |  |
|  | Livelihoods of local communities, particularly women, youth, and the elderly do not improve and social, economic and environmental benefits are not gained, thereby increasing food insecurity and environmental degradation. |  |  |  |
| ENVIRONMENTAL RISK |  |  |  |  |
| The sequence of climate change events affects vital areas for conservation, productive landscapes, and beneficiary communities. | Loss of goods and sustainable production systems developed by the project due to extreme events. Climate change is likely to alter ecosystems that are vital for species production from which natural ingredients are derived, limiting the implementation of sustainable production practices as alternatives for local development, biodiversity protection, and peace process support. | Medium | To reduce the impact of climate change, the project incorporates a socio-ecosystem connectivity approach and activities related to harmonization of planning instruments, PAs and CCSs planning and management, SFM, and sustainable production initiatives. The project activities related to biodiversity conservation include sustainable production practices, forest cover improvement, and native vegetation rehabilitation, which will contribute to increasing resilience to climate change and climate variability. In addition, the project will strengthen and improve the adaptation capacity and social resilience of local communities to climate change by respecting and recognizing their traditional knowledge of biodiversity management and the promotion of sustainable production practices. | PC, local authorities, community leaders, MADS, PNN, CARs Project Steering Committee (PSC), Technical Committees |
|  | Climate change variability contributes to biodiversity loss and determines new challenges for communities related to agriculture, natural resources management, and survival. |  |  |  |
| Socio-environmental conflicts: Extraction activities and territorial conflicts. | Delay in the implementation of project activities. | Medium | Output 1.1.1, which is related to analysis and strategic assessment of ecosystem services in the Colombian Pacific region will provide information for identifying socio-environmental conflicts. The project will foster a monitoring system with periodic reports, including identification and tracking of potential socio-environmental conflicts in each MUCB. Potential socio-environmental conflicts will be discussed within the framework of the PSC, PTC, and the committees of each MUCB so that these are considered in the planning and implementation of project activities. |  |
| SECURITY RISK |  |  |  |  |
| Armed conflict, disruption of public order, and problems related to security. | Armed conflict: Presence of illegal armed groups, homicides, threats and murders of community leaders, illicit crops, and mined areas. Conditions of scarce security in many of the project intervention areas may affect the implementation of project activities and the displacement of beneficiaries. | Medium-high | One of the factors for defining and prioritizing the MUCBs was the situation of security and public order. Areas where the main efforts for building peace are concentrated were selected. Likewise, the security criteria will be considered in selecting the areas for implementation of pilot activities and during the Technical Committee meetings of each MUCB. The security measures required by the United Nations system will be applied in such cases. The United Nations Department of Safety and Security (UNDSS) periodically evaluates the risks of the country and the specific risks for those operating in the field, by sharing this information with all the United Nations system agencies. Additionally, the Department of Protection of Citizens’ rights puts an Early Warning System at the disposal of communities and institutions that monitors the risk situations due to the armed conflict. The project will strictly follow the advice of the UNDSS concerning all matters related to security of the United Nations and project staff working on activities involving the locations of offices, movement, and participation of populations in remote areas. | PSC, Technical Committees, Implementing Agencies |
| INSTITUTIONAL RISK |  |  |  |  |
| The institutional post-conflict structure and roles and responsibilities have only recently been defined, which may limit the impact of the project. | The implementation of sustainable production practices as alternatives for local development, biodiversity protection, and consolidation of the peace process in the prioritized MUCBs depends on a solid institutional post-conflict structure at the national and local levels, which was just put into place in 2017. | Low |  | PC, Project Technical Team (PTT) |
| MANAGEMENT RISK |  |  |  |  |
| Lack of an effective implementation from key counterparts, including main implementing agencies (FAO & UNIDO) to reaching the project objectives both at national/regional level, in particular with respect to component 3. | Insufficient production boost meant to be achieved under component 3.1 directly affects activities foreseen under component 3.2. | Medium-high | Based on the technical nature of the collaboration other potential actions would be identified. In case component 3.1 is not able to boost production to a level that renders processing economic and profitable, the processing plants will source alternative products in the region. Additionally, the establishment of a direct channel of communication with the management is envisaged. | PSC, Technical Committees, GEF Implementing Agencies |

A.6. Institutional Arrangement and Coordination. Describe the institutional arrangement for project implementation. Elaborate on the planned coordination with other relevant GEF-financed projects and other initiatives.

Overall institutional arrangements

The Food and Agriculture Organization (FAO) has been selected by the participating country as the lead GEF Implementing Agency, in order to provide project cycle management services as established in the GEF Policy. The United Nations Industrial Development Organization (UNIDO) will complement the intervention, also as GEF Implementing Agency. Within this arrangement, the technical and financial implementation responsibility will be split according to the technical competence of each agency, being FAO responsible for providing oversight, technical backstopping and supervision of the implementation of Project Components 1, 2,  4 and Outcome 3.1, while UNIDO will do the same for Outcome 3.2. Technical support will be provided by both agencies in coordination with government representatives participating in the Project Advisory Committee. FAO’s and UNIDO´s role and responsibilities are described below. All administrative actions will be carried out under the rules and procedures of each GEF Implementing Agency.

The MADS will be responsible for the overall execution of the project and will act as national execution entity. National co-executing agencies will be designated and will be supported by the Project Steering Committee (PSC) and a Project Implementation Unit (PIU). The overall responsibility for project execution implies accountability for intended and appropriate use of funds, as well as for timely delivery of inputs and outputs.

MADS will also designate, as part of its co-financing, the National Project Director (NPD), who will be responsible for the execution and coordination of the project, with the following responsibilities:

- Organize and chair PSC meetings.

- Participate in meetings of the RTC and MUCBTCs.

- Regularly supervise the implementation of the project in line with the Project Results Framework, budget, and the annual work plan.

- Requesting FAO the timely disbursement of GEF resources.

- Review and approve the semi-annual and annual progress reports.

Project governance, decision-making, and execution will be carried through 3 levels:

- Project Steering Committee (PSC)

- Regional Technical Committee (RTC)

- MUCB Technical Committees (MUCBTC), one per MUCB (5)

Coordination among Government agencies and the Implementing agencies will be achieved through a Project Steering Committee (PSC) which will be co-chaired by MADS. The PSC will provide the necessary guidance and coordination to the project implementation, and will invite members and experts for specific meetings, as needed. The PSC decisions shall be made in line with the approved project document, GEF, FAO and UNIDO guidelines. Additionally, The PSC will be composed of PNN, MADR, SIRAP Pacific, one representative of community councils, one representative of indigenous resguardos, and one CAR in representation of the five CARs, departmental governments of Nariño, Cauca, Valle del Cauca and Chocó, FAO and UNIDO. The PSC Technical Secretary will be the PC. Its main function is to guide the implementation of the project, verify and approve the annual work plans, approve the financial and technical reports, and provide strategic guidance for the project.

The project Regional Technical Committee (RTC) will be organized within the SIRAP Pacific Technical Committee framework and will be constituted by delegates of MADS, PNN, CODECHOCÓ, CARDER, CVC, CRC, CORPONARIÑO, IIAP, INVEMAR, FAO and UNIDO, and the invitation can be extended to departmental governments and representatives of indigenous, black communities, and peasant peoples with influence in the project.

The MUCB Technical Committees (MUCBTCs) will be integrated by MADS, PNN MADR, community councils, and indigenous resguardos participating in the project, INVEMAR, IIAP, FAO, UNIDO, CAR, municipalities, and community and civil society organizations with influence in each MUCB. The composition of each MUCBTC will be defined according to the presence and influence of each entity.

Functions and responsibilities of each decision-making level of the project are further detailed in FAO-GEF Project Document, Section 3. Likewise, terms of reference (TOR) governing the participation of stakeholders on each decision-making level will be developed in the first 3 months of the project execution.

The Project Implementation Unit (PIU)

For the execution of the Project activities, the PIU will be established and constituted by a Project Technical Team (PTT), which will be financed by GEF. The main PIU function, following the guidelines and decisions taken by PSC, in close coordination with RTC and MUCBTC and under supervision of the NPD, is to ensure rigorous and effective coordination and execution of the project annual work plans and the intervention plans of each MUCB.

The PIU will be under the general supervision of the NPD and led by the Project Coordinator (PC), who will be in charge of the daily project management and technical supervision, in accordance with FAO and UNIDO standards, procedures, present project document and the work plans agreed upon for each MUCB. The PC will lead the formulation of reports to GEF and technically validate and supervise the reports of consultants and organizations.

The TORs of the PC and the PIU are contained in FAO-GEF Project Document, Appendix 6, which will be updated and adjusted in the first 3 months of the project implementation.

The PIU will be structured as shown below.

Figure 1. Structure of the PIU

The Project Coordinator (PC) will be responsible for supervising and guiding PIU. He/she will also be responsible for coordinating activities with all instances linked to the different components of the project, as well as with the partner institutions of the project. He/she will also be in charge of daily project management and technical supervision of the overall project activities, including: (i) coordinating and closely supervising the execution of project activities with among the project and other Government entities, (ii) day-to-day management, (iii) coordination with other related initiatives, (iv) ensure a high level of collaboration between participating institutions and organizations at the national, provincial and local levels; (v) monitor the progress of the project and ensure the timely delivery of inputs and outputs; (vi) implement and manage the project monitoring plan and its communication program; and (v) report to FAO and UNIDO on project delivery and impact.

The Administrative and Financial Assistant will be responsible for the day-to-day financial management of the project, including lifting the contracts and acquiring other necessary supplies according to the approved project document. He/she will work in close consultation with the PC and project implementing partners, particularly the FAO Representation in  Colombia, UNIDO and the MADS.

The PIU will be complemented by specific technical expertise hired by the guidance of UNIDO or FAO, accordingly to the project requirements.

FAO will hire some of the following human resources:

- Professional in participation and ethnic and gender approach (PPEGA)

- Professional in instruments for ecosystem services planning and assessment (PIESPA)

- Professional in PAs and CCSs (PPAsCCSs)

- Professional in Communications (PCM)

- Professional in Sustainable Forest Management (PSFM)

- Professional in Sustainable Production and Soil Management Systems (PSPSMS)

- Other technical experts

UNIDO will hire some of the following human resources:

- National Expert in Biodiversity Products (NEBP)

- National Quality and Standards Consultant (NQSC)

- National agribusiness consultant (NABC)

- National Market Consultant (NMC)

- Other technical experts

Communication

FAO, UNIDO and GEF logos must be inserted in all the relevant project publications in recognition of the inputs they made to the project. Any citation of the publications related with projects financed by GEF must acknowledge the role played by GEF

FAO institutional arrangements

- FAO Institutional arrangements and project coordination with other initiatives are described in Section 3 – Implementation Management Arrangements of the FAO- GEF Project Document.

UNIDO institutional arrangements

Project Implementation

UNIDO is entrusted by the Government of Colombia and by the GEF with the mandate to implement outcome 3.2 of the project and to achieve its objectives  and outputs within its budget and time frame, as approved in this project document. UNIDO is accountable to the GEF for the funds of this project and will, in close consultation with MADS, implement the project’s outcome 3.2 according to the established UNIDO’s rules and regulations. This means that UNIDO will, jointly with FAO, participate in the execution of Component 3; and in particular, will supervise and provide technical guidance/support for the implementation of activities described in this project, including:

- Administering the funds corresponding to project Outcome 3.2.

- Oversee and monitor the implementation of project activities foreseen under Outcome 3.2, in accordance with the project document, approved work plans, budget, and agreements with co-financers.

- Taking the necessary administrative actions for the provision of resources, supplies, equipment and subcontracting, as deem necessary.

- Reviewing and approving the project progress and financial reports, undertaking and completing the M&E plan, and developing activities aimed at supervising activities foreseen under Outcome 3.2.

- Providing guidance, supervision, technical assistance and leadership, as applicable, to the project.

- Convening meetings for joint coordination with FAO and other key stakeholders to discuss and agree on relevant issues/findings and documenting the lessons learned and/or the way forward agreed.

- Providing the corresponding inputs for Outcome 3.2 to the Lead Agency, including relevant information needed to prepare GEF Annual Monitoring reports.

- and providing financial reports to the Lead Agency, FAO, for developing the PIR.

- Participating in MTR and TE missions, as well as reviewing the draft Mid-Term Review (MTR) and Terminal Evaluation (TE) reports.

- Monitoring the implementation of the social and environmental risks mitigation plan according to UNIDO environmental and social safeguards in relation to the Output 3.2 activities.

UNIDO’s roles in internal organization

The UNIDO Representative in Colombia will be responsible for supervising and facilitating the implementation of Outcome 3.2 and maintaining relationships with national Government and project counterparts.

Two Industrial Development Officers (IDOs) of the Standards and Quality Infrastructure Division (PTC/TII/SQI) and the Rural Entrepreneurship, Youth and Human Security Division (PTC/AGR/RJH), based at the UNIDO HQ, will be the main budget holders responsible for 1) the budget and the administrative, operational, and financial management of resources corresponding to the project Outcome 3.2; 2) procurement of goods and contracting of services for the project activities as per UNIDO standards and procedures, work and budget plan; 3) reviewing and approving financial reports, annual work plans and budget plans, and 4) ensuring implementation of the risks and mitigation plan. They will also monitor and provide technical guidance/support to Outcome 3.1 in coordination with FAO LTO. Full or partial title and ownership of equipment purchased under the Outcome 3.2 may be transferred to national counterparts and/or project beneficiaries during the project implementation as deemed appropriate by the UNIDO IDOs in consultation with the respective project stakeholders.

The Standards and Quality Infrastructure Division provides support to strengthen national and regional quality infrastructure systems to provide quality services, which include advisory on quality policy and good governance strategies, evaluation and modernization of technical regulations regimes, capacity strengthening of national and regional quality systems (i.e. metrology, standardization and accreditation), construction of conformity assessment capacities (testing, inspection, certification, calibration, etc.), and support for small and medium enterprises (SME) to be more competitive and to participate in global value chains, and facilitation of trade (including e-commerce). It also will support the strengthening of authorities and consumers’ associations.

The Rural Entrepreneurship, Youth Employment and Human Security Division provides technical assistance to improve quality of life in rural communities through production activities. The approach ensures through business activities among economically and socially marginalized populations, particularly women and young people, in agriculture and non-agriculture sectors as well as creative industries, that technical and human-undertaken activities are strengthened and joined with opportunities to produce new and improved marketable products. Knowledge and technologies incorporated into rural communities fit in the absorption and innovation capacities of the poorest and most vulnerable segments of the rural societies.

# Additional Information not well elaborated at PIF Stage:

A.7 Benefits. Describe the socioeconomic benefits to be delivered by the project at the national and local levels. How do these benefits translate in supporting the achievement of global environment benefits (GEF Trust Fund) or adaptation benefits (LDCF/SCCF)?

- The project will provide monetary and non-monetary benefits to local stakeholders, including organizations and members of indigenous,  black communities, and rural community members, and local subnational public officials in the Colombian Pacific region, including: a) formulation and/or updating of the planning instruments of black communities and indigenous peoples and their harmonization with local territorial and environmental management planning instruments resulting in improved governance over natural resources and territories; b) formulation of forest zoning management plans in the MUCBs and implementation of SFM actions resulting in improved governance of forest resources and improved income from sustainable forest harvesting and forestry; c) implementation of a training plan for the SIRAP Pacific, improving PAs governance and empowering members; d) strengthening of capacities of community environmental leaders/agents, promotion of intergenerational and intercultural dialogue, and updating/equipping of local community participation venues that strengthen cultural and traditional knowledge values; e) strengthening of governance mechanisms for PAs management; f) implementation of agroforestry systems as a strategy for the restoration of forests and degraded agricultural lands offering the communities a wide variety of food and non-food products, thus contributing to food and nutritional security, generating income, improving livelihoods, and reducing rural poverty; g) implementation of prioritized actions for green business initiatives, enhancing the sustainable livelihoods of indigenous, black communities, and rural community members; and h) implementation of sustainable production and forest management plans, marketing of value-added biodiversity products, and support of community-based nature tourism initiatives, all of which will contribute to increasing the income of the participating households.

- The project will improve the supply of ecosystem services through different actions. The consolidation of PAs and buffer zones will improve habitat conservation and biodiversity on which local communities depend; the restoration of forests and degraded agricultural lands will improve soil productivity, erosion control, and will contribute to the regulation of water availability and quality in degraded or less productive lands; and socio-ecosystem connectivity will build resilience to climate change and contribute to support sustainable production activities. Together, these project actions will contribute to providing a healthier environment for local communities in the five prioritized MUCBs. The project will directly benefit at least 4,000 people (40% women, 60% men).

A.8 Knowledge Management. Elaborate on the knowledge management approach for the project, including, if any, plans for the project to learn from other relevant projects and initiatives (e.g. participate in trainings, conferences, stakeholder exchanges, virtual networks, project twinning) and  plans for the project to assess and document in a user-friendly form (e.g. lessons learned briefs, engaging websites, guidebooks based on experience) and share these experiences and expertise (e.g. participate in community of practices, organize seminars, trainings and conferences) with relevant stakeholders.

- Project Component 4: Knowledge management and project M&E outlines the knowledge management strategy for the project. This strategy includes specific outputs regarding how best practices will be documented and experiences will be shared with other biodiversity initiatives using new and existing information-exchange platforms. This will include: a) an online monitoring platform; and b) a communication strategy. In addition, the results from the project will be disseminated within and beyond the project intervention area through a number of existing FAO and UNIDO information-sharing networks and forums. A description of the knowledge management approach for the project is provided in Section 1.3, The GEF Alternative (Component 4), of the FAO-GEF Project Document.

B. Description of the consistency of the project with:

B.1 Consistency with National Priorities. Describe the consistency of the project with national strategies and plans or reports and assessments under relevant conventions such as NAPAs, NAPs, ASGM NAPs, MIAs, NBSAPs, NCs, TNAs, NCSAs, NIPs, PRSPs, NPFE, BURs, etc.:

- Same as in PIF.

- In addition, the project is also consistent with the objective of the National Policy for Biodiversity and Ecosystem Services Management in Colombia (2012) to improve the resilience of the social and ecological systems at the national, regional, local, and cross-border scales, considering scenarios of change and through joint, coordinated, and focused action by the government, the productive sector, and civil society. Within the policy framework the importance of ecosystem services is recognized for their role in ensuring the well-being of the population  through the supply of services, such as food and natural ingredients, medicinal plants, cosmetic products,  water regulation, and cultural support and services (e.g., recreation and tourism).

- The project is also consistent with the National Action Plan to Combat Desertification and Drought (PAN, 2004) in Colombia, which promotes actions for loss prevention, rehabilitation, and sustainable management of ecosystems affected by land degradation. Specifically, the project’s actions are in line with the PAN’s specific objectives to: a) establish environmental guidelines and measures necessary to prevent, mitigate, halt, and /or combat land degradation; and b) develop and test environmentally sustainable technologies that contribute to the implementation of forestry, agricultural, livestock, and multipurpose activities that contribute to food security and improved quality of life of the communities settled in the areas affected by land degradation.

- In addition, the project is consistent with the National Forest Policy (NFP, 1996) and the National Forestry Development Plan (NFDP, 2000), which promote SFM. The NFP in its strategy for the conservation, recovery, and sustainable use of natural forests, identifies the need to reduce deforestation through the control of the expansion of the agricultural frontier and colonization of natural forested areas, including the use of incentives to promote forest and soil conservation. The NFDP provides the guidelines for the conservation of biodiversity and forest ecosystems, the reduction of deforestation, and the management and sustainable use of forest products by indigenous and local communities, all of which are relevant to the project proposed herein.

C.  Describe the budgeted m &e plan:

| ## M&E Activity | ## Responsible parties | ## Time frame/ Periodicity | ## Budget |
| --- | --- | --- | --- |
| ## Inception workshop (workshop report) | ## PC; FAO- UNIDO (with support from Lead Technical Officer [LTO], Budget Holder and FAO – GEF Coordination Unit) | ## Within two months of project start up | ## USD 12,594 |
| ## Field level impact monitoring | ## PC, Project partners, Local organizations | ## Continuous | ## USD 68,550 (travel, 5% of the PC time, 30 % of the MUCB Technical Coordinator) |
| ## Project Progress Report (PPR) | ## PC, with contributions of the project partners and other executing institutions | ## Six-monthly | ## USD 6,564 (3% of the PC time) |
| ## Project Implementation Review (PIR) | ## PC with support of the Project Technical Team (PTT) and under supervision of FAO Lead Technical Officer (LTO) and the Technical Officer of UNIDO Office; clearance by the FAO/GEF and UNIDO/GEF Coordination Unit(s) | ## Annual | ## FAO and UNIDO staff time financed through GEF agency fees, PC and PTT financed through the project budget |
| ## Co-financing reports | ## PC with inputs from other co-financiers | ## Annual | ## USD 2,188 (1% of the PC time) |
| ## Technical reports | ## PC and FAO (LTO, FAO Colombia) UNIDO | ## According to the project needs | ## None |
| ## Mid-term review (MTR) | ## External Consultant, FAO and UNIDO Offices in Colombia, FAO/GEF Coordination Unit and others | ## Midway through the project implementation period | ## USD 20,000 for external consultancy |
| ## Terminal Workshop (workshop report) | ## PC and PTT | ## Prior to the end of the project | ## USD 12,594 |
| ## Terminal Evaluation (TE) | ## External consultant, FAO Office of Evaluation (OED) in consultation with the project team, including the FAO-GEF and UNIDO-GEF Coordination Unit(s) and other stakeholders | ## Six months prior to the end of the project | ## USD 50,000 |
| ## Terminal Report | ## PC; FAO (FAO Office in Colombia, LTO, FAO-GEF Coordination Unit, TSR Report Unit), UNIDO | ## Three months prior to the end of the project | ## None |

PART iII:  certification by gef partner agency(ies)

- GEF Agency(ies) certification

This request has been prepared in accordance with GEF policies and procedures and meets the GEF criteria for CEO endorsement under GEF-6.

| Agency Coordinator, Agency Name | Signature | Date (MM/dd/yyyy) | Project Contact Person | Telephone | Email Address |
| --- | --- | --- | --- | --- | --- |
| Mr. Philippe R. Scholtès, Managing Director, Programme Development and Technical Cooperation, UNIDO-GEF Focal Point |  |  | Juan Pablo Diaz Castillo, UNIDO Vienna |  | J.DIAZ-CASTILLO@unido.org |
| Alexander Jones Director, CBC |  |  | Gabriel Chavez FAO GEF Project Task Manager, Colombia | +57 1 3905014 | faogef@fao.org Gabriel.chavez@fao.org CBC-Director@fao.org |

ANNEX A:  PROJECT RESULTS FRAMEWORK (either copy and paste here the framework from the Agency document, or provide reference to the page in the project document where the framework could be found).

| Results chain | Indicators | Baseline | Mid-term target | Final target | Means of verification | Assumptions | Responsible for data collection |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Objective: To mainstream the sustainable use and conservation of biodiversity and the provision of ecosystem services that support human welfare and vulnerable landscapes of the Colombia’s Pacific region in view of generating global and local environmental benefits and supporting the peace process |  |  |  |  |  |  |  |
| Component 1: Institutional strengthening to support pro-conservation and sustainable use in the Pacific region of Colombia |  |  |  |  |  |  |  |
| Outcome 1.1 The territorial and environmental management planning instruments are harmonized with the instruments developed by the black communities and indigenous peoples to safeguard biological, cultural, and ecosystem services diversity, leading to a general reduction in potential threats from development- oriented activities. | a) Project targeted area (hectares – ha) for reducing current and potential pressures from competing land uses and forest degrading land-uses. b) Hectares of strategic importance for biodiversity conservation outside PAs that apply guidelines and are managed to be included in the planning instruments under improved management. |  |  | a) 44,084,957 ha (marine area: 34,762,783 ha; continental area: 9,322,174 ha) corresponding to the SIRAP Pacific management area (indirect target landscape) of which at least 1,061,655 ha (direct total area). b) 210,193 hectares of strategic importance for biodiversity conservation outside PAs | Planning instruments approved GEF7 Core Indicators updated at midterm and final points of the project. | Willingness of subnational and local authorities and private sector to apply the guidelines for harmonization of territorial and environmental management planning instruments that safeguard cultural, biological, and ecosystem services’ diversity. | Project M&E Expert |
| Output 1.1.1: A Diagnosis and Strategic Assessment of the ecosystem services in the Pacific Region. | Number of analyses and strategic assessments of ecosystem services for four MUCBs. | Zero (0) | 4 (Katios – Caoba, Farallones – Calima, Cabo Manglares – Gran Familia Awá, Muchique – Rió Saija). | 4 (Katios – Caoba, Farallones – Calima, Cabo Manglares – Gran Familia Awá, Muchique – Rió Saija). | Assessment reports Project reports | The project stakeholders recognize the usefulness of the strategic assessment inputs in several project products. Subnational and local authorities recognize the usefulness of the analysis and strategic assessment exercise and will incorporate it into their management practices. | MUCB Coordinators Ecosystem Services Expert MADS SIRAP CARs |
| Output 1.1.2: Agreed guidelines on harmonization of departmental/municipal territorial plans and Indigenous Peoples’/black communities’ instruments, with a gender approach. | # of guidelines # of planning instruments included #of pilot areas Degree of gender mainstreaming | Zero (0) | One (1) guidelines document under development | 1 Guidelines. 24 planning instruments reached. 6 pilot areas in MUCBs. Gender chapter included. | Guidelines for harmonizing instruments that safeguard cultural, biological, and ecosystem services’ biodiversity approved by the authorities. Field reports. Project reports. | Subnational and local authorities adopt the guidelines for harmonizing territorial zoning plans at the departmental and municipal levels with the planning instruments developed by black communities and indigenous peoples to safeguard cultural, biological, and ecosystem services’ diversity. Application of guidelines for harmonizing instruments that safeguard cultural, biological, and ecosystem services’ diversity will be a collective process with communities and institutions providing support. | Project Team Departmental Governments Municipalities SIRAP CARs MADS Ministry of Internal Affairs |
| Output 1.1.3: A tailor-made and open-access SIAT_PC (integrated with the Environmental Information System of Colombia - SIAC) - strengthened to harmonize the existing planning mechanisms in the Pacific Region. | SIAT-PC strengthened | SIAT-PC launched in 2002 | SIAT-PC under strengthening process | SIAT-PC strengthened and integrated into SIAC of SINA | Databases Information platform Reports of the territorial planning system and SIAC | Technical feasibility | Information Systems Expert MADS IIAP |
| Output 1.1.4: Forest zoning and management plans (POFs) outside the PAs developed, updated, and implemented in a participatory way, promotes socio-ecosystem connectivity at the MUCB level. | Number of POFs for 65,000 ha following MADS guidelines | Zero (0) | Zero (0) | Two (2) | POFs documents developed under MADS guidelines. Project reports | CARs and collective territories proximate to the PAs are willing to update the POFs. MADS makes the guidelines available for developing POFs. | Project Team Departmental Governments Municipalities SIRAP CARs |
|  | Area (ha) with forest management plans and with support for their implementation | Zero (0) | 500 ha | 2,000 ha | Forest management plans approved by environmental/ territorial authorities (CARs and one collective territory) Implementation reports | CARs and collective territories proximate to the PAs are willing to develop forest management plans. | Project Team Departmental Governments Municipalities SIRAP CARs |
| Outcome 1.2 Improved stakeholders’ capacity and participation to support the enforcement of harmonized planning and environmental management in the MUCBs | Increase of the SIRAP Pacific’s management capacities measured through the GEF Development Capacity Scorecard | Capacity in SIRAP Pacific: - Technical Regional Roundtable: 29% (the baseline and targets will be validated at project inception) - | Capacity in SIRAP Pacific: - Technical Regional Roundtable: 34% | Capacity in SIRAP Pacific: - Technical Regional Roundtable: 44% | GEF capacity development scorecard updated at mid-term and final points of the project. Lists of participants in training events and exchange networks. | Sampling efforts are optimal. Beneficiaries apply the additional knowledge acquired. | Project Team and/or specialized consultant |
| Output 1.2.1: Six (6) SIRAP Pacific participation and decision-making structures, strengthened and with enhanced capacities to apply harmonized guidelines (see output 1.1.2). | Number of existing participatory and decision-making structures within the framework of the SIRAP Pacific strengthened through the project. | Zero (0) | Six (6) in process | Six (6) strengthened | Meeting minutes SIRAP Pacific performance and annual reports | There is interest in and commitment to participate. Representatives before the SIRAP Pacific are qualified to represent their communities, and receive information and decisions made within the SIRAP Pacific framework. Representativeness of the various population groups exists, ensuring the inclusion of an ethnic and gender approach in local and regional platforms. | Project Team SIRAP Pacific |
| Output 1.2.2: Five (5) local community participatory structures, strengthened and with enhanced capacities to comply with harmonized guidelines (see 1.1.2) | Number of local participatory structures strengthened for ensuring compliance with guidelines, using a gender-based approach. | Zero (0) | At least five (5) in process | At least five (5) strengthened | Meeting minutes Project reports | There is interest in and commitment to participate. Representativeness of the various population groups exists, ensuring the inclusion of an ethnic and gender approach within the local and regional organizational structures. | Project Team Communities |
| Component 2: Integrated management of PAs, buffer zones and CCS |  |  |  |  |  |  |  |
| Outcome 2.1 Reduction of pressures and threats to biodiversity and ecosystem services in 581,859 ha of existing PAs and their buffer zone. | Management effectiveness of PAs measured by the METT | - Katíos NNP: 66 - Farallones NNP: 67 - Tatamá NNP: 68 - Munchique NNP: 68 - Cabo Manglares Bajo Mira and Frontera IMND:40 - *Río Bravo RFPR: 40 | - Katíos NNP: 71 - Farallones NNP: 72 - Tatamá NNP: 73 - Munchique NNP: 73 - Cabo Manglares Bajo Mira and Frontera IMND: 43 - *Río Bravo RFPR: 45 | - Katíos NNP: 76 - Farallones NNP: 77 - Tatamá NNP: 78 - Munchique NNP: 78 - Cabo Manglares Bajo Mira and Frontera IMND: 48 - *Río Bravo NR: 50 | METT updated at mid-term and final points of the project Reports analyzing multi-temporal changes in land cover GEF 7 Core Indicators updated | There is interest by the central and municipal governments, local communities, and production sectors to improve PA management and ensure the protection of conservation targets. Effective reduction of pressures on natural forests is achieved. | M&E Expert SIRAP CARs |
| Output 2.1.1: Management plans and governance mechanisms developed and/or adopted include support for the implementation of priority actions in the selected areas. | Number of hectares (ha) under management plans developed and/or adopted with support for the implementation of priority actions. | 0 | 190,282 ha | 581,859 ha | Management plans adopted PAs management reports, including Colombia’s AEMAPPS Project progress reports Official gazette and/or resolution | There is interest from the central, regional, and local governments, civil society, and production sectors to improve PA management. The legal framework remains unchanged; however, changes in policy may occur under a new government. Commitments and agreements for building peace favor project implementation. The policy to reduce deforestation is adopted. The Integral Strategy for the Control of Deforestation and Forest Management is adopted. | Project Team SIRAP CARs Communities PNN |
|  | Number of governance mechanisms under implementation as a result of the project | 0 | At least two (2) under implementation | Five (5) under implementation | Reports on case studies regarding the performance and operation of governance mechanisms in the MUCBs |  | Project Team Governance Specialist PNN SIRAP Pacific |
| Output 2.1.2: One financial sustainability strategy designed and implemented for ensuring participation within the SIRAP Pacific framework | Financial strategy for the SIRAP Pacific action plan | Currently there is no strategy. | Financial strategy for the SIRAP Pacific designed. | Financial strategy for the SIRAP Pacific designed. | Financial strategy document Final strategy implementation reports | Interest of the central and departmental governments, regional environmental authorities, civil society organizations, and black and indigenous communities in financing the PAs’ management at the subnational level. | Project Team SIRAP CARs MADS Civil society Black and indigenous communities |
|  | Level of participation of members of the SIRAP Pacific with resources from the project and as a result of implementing part of the SIRAP financial sustainability strategy. | - General assembly: 0% - Regional Technical Committee: 70% - Regional Technical Roundtable: 68% | - General assembly: baseline + 60% - Regional Technical Committee: 80% - Regional Technical Roundtable: baseline 80% | - General assembly: baseline + 80% - Regional Technical Committee: 90% - Regional Technical Roundtable: baseline + 90% | SIRAP Pacific meeting minutes Lists of attendance at meetings SIRAP Pacific management reports | Participation in the SIRAP Pacific is strengthened and positively influences its management. | Project Team SIRAP Pacific |
| Output 2.1.3: Forest restoration and soil recovery plans for PAs, buffer zones, connectivity areas, and corridors are developed and implementation is kick-started in a participatory manner. | Carbon captured (tCO2-eq) through soil ecological restoration and recovery as a result of the project | 0 tCO2-eq | 0 tCO2-eq | 10,646 tCO2-eq | Field and technical reports Updated GEF7 Core Indicators at mid-term and final points of the project | There are no significant changes in land use/land cover. Sampling efforts are optimal. Environmental variability within normal ranges. | SFM/LD Expert (and carbon accounting) |
|  | Area (ha) restored with the project’s support | 0 | 400 ha under restoration | 1,000 ha restored |  |  | SFM/LD Expert |
| Outcome 2.2 New PAs and CCSs receive support for management planning and implementation. | Area (ha) of new PAs under declaration process (three public PAs). | 0 | 3,356 ha | 258,603 ha | Proposals for establishing new PAs Official gazette Updated GEF7 Core Indicators at mid-term and final points of the project | There is willingness among decision- makers to establish new PAs. | Project M&E Expert SIRAP CARs MADS |
|  | Area (ha) sustainably managed through the communal CCS | 0 | 62,268 ha | 210,193 ha | Project monitoring reports Updated GEF7 Core Indicators at mid-term and final points of the project | There is willingness by the decision makers to incorporate SFM objectives into production landscapes/MUCBs | Project M&E Expert SIRAP CARs MADS Communal Councils Indigenous Reserves |
| Output 2.2.1: Planning and management instruments developed, with priority actions implemented in CCSs, by the forest-dependent communities. | Number of planning and management instruments with early implementation actions in CCSs as a result of the project | Zero (0) | At least two (2) | Five (5) | CCS planning instruments approved by the competent platforms. CCS management reports | Willingness and feasibility exist to support the existing CCSs and the consolidation of new related initiatives | Project Team Communities SIRAP Pacific |
| Output 2.2.2: One Technical guidelines as support for the regulatory process to formalize the CCSs in the Pacific region considering ethnic/cultural aspects and in line with the national process. | Document with technical guidelines as support for regulations to formalize the CCSs in the Pacific region | There are no technical guidelines. | Technical guidelines under development | Document with technical guidelines | Document compiling and analyzing the technical guidelines for formalizing the CCSs Dissemination reports Project reports | Related authorities adopt the guidelines proposed. Continued interest by indigenous peoples | Project Team Communities MADS SIRAP |
| Output 2.2.3: Priority areas for conservation are assessed and steps towards their declaration as formal PAs are taken. | Number of new PAs progressing towards their declaration as a result of the project. | - Regional public governance: Zero (0) | - Regional public governance: Three (3) (Caoba, Serranía de los Paraguas, and Calle Santa Rosa) | - Regional public governance: Three (3) (Caoba, Serranía de los Paraguas, and Calle Santa Rosa) | Technical studies CAR proposals for the declaration of PAs | Political will and social feasibility for establishing new PAs | CARs SIRAP PNN |
| Component 3: Sustainable production practices as alternatives for local development, biodiversity protection and peace process support |  |  |  |  |  |  |  |
| Outcome 3.1 Biodiversity and ecosystem services are sustainably utilized in forest-based productive systems and generate multiple environmental and socio-economic benefits | Area (ha) under sustainable production systems | 0 | At least 3,500 ha | 10,000 ha | Field reports Project reports (PIR, mid-term review and terminal evaluation) | There is willingness by landowners and local producers to incorporate environmental sustainability criteria as part of their productive activities. There are incentives available to implement sustainable production practices. | Project Team Socio-economic Expert |
|  | Proportion of SFM initiatives and production systems led by women. | 0 | 10% | 40% | Results of surveys made available to producers. Project reports (PIR, mid-term and terminal evaluations) | Gender effectively mainstreamed | Project Team Socio-economic Expert |
| Output 3.1.1: Green Business action plan(s) harmonized and under implementation for fostering and developing diversified production systems are agreed upon and modalities adapted to local conditions, for supporting food security, sustainable livelihoods, landscape-level connectivity and forest rehabilitation | Number of green business plans that safeguard cultural, biological, and ecosystem services’ diversity. | Zero (0) | Three (3): Nariño, Cauca, Risaralda | Three (3): Nariño, Cauca, Risaralda | Green business plans approved by the interested parties Project reports. | Stakeholders are interested in participating. | Project Team Green Markets Expert CARs MADS |
|  | Number of green business initiatives with priority actions supported (in the MUCBs) | Zero (0) | Ten (10) | Twenty five (25) | Implementation reports of green business initiatives Project reports | Stakeholders are interested in participating. | Project Team Green Markets Expert CARs MADS |
| Output 3.1.2: SFM initiatives and sustainable production systems implemented incorporating good soil and biodiversity-friendly practices, with gender approach | Number of plans for SFM initiatives and sustainable production systems as a result of the project | Zero (0) | Eight (8) | Eight (8) | Results of surveys made available to producer families Production plans shared with stakeholders Field reports Project reports | Beneficiaries are interested in participating. Incentives available to implement environmental-friendly production practices. | Project Team SFM and SLM Expert |
| Outcome 3.2 Products and services derived from biodiversity have value added and their value chains duly strengthened. | Annual average income of beneficiary communities, maintained or increased # of value added units of BD-derived products with technical and management capacities #of BD-derived products with access to formal markets, and fulfilling the requirements for quality, MADS green business criteria, and other standards # of community-based nature tourism initiative strengthened | - Average of USD $1,240 per year per family (COP $3,600,000 per year per family) (Baseline to be defined at project inception) | - Average of USD $1,302 per year per family (5% increase) | - At least an average of USD $1,364 per year per family (at least 10% increase) Seven (7) units Five (5) products Four (4) tourism initiatives | Income assessment results Household surveys | Beneficiaries are interested in participating. Incentives available to implement biodiversity-friendly production practices. Stable and multiple markets available. | Project Team Socio-economic Expert |
| Output 3.2.1 Value addition units of biodiversity-derived products created and strengthened, with technical and management training that safeguard cultural, biological, and ecosystem services’ diversity. | Number of value addition units strengthened and created for biodiversity-derived products with technical and management capacity as a result of the project | - Value addition units strengthened: Zero (0) - Value addition units created: Zero (0) | - Five (5) value addition units in the process of strengthening - Two (2) value addition units in the process of being created | Seven (7) value addition units strengthened | Technical and management training plans for value addition units Performance report of value addition units Training documents and tools Lists of attendees at training events | Continuity of the national green business policy Favorable security conditions | Project Team UNIDO Trainers |
| Output 3.2.2: Biodiversity-derived products with market access and/or enhance compliance with quality requirements, MADS green business criteria, and other standards for market access. | Number of biodiversity-derived products with formal market access and complying with quality requirements, green business criteria of MADS and other standards for markets access | Zero (0) | At least two (2) | At least five (5) | Business plans for the five products Progress reports, audits to assess compliance with green business criteria Project reports Business agreements | Markets available Government continues strengthening the infrastructure quality Reduced contamination in project areas | Project Team UNIDO Green Markets Expert CAR |
| Output 3.2.3: Community-based nature tourism initiatives strengthened with government and non-government support that safeguard cultural, biological, and ecosystem services’ diversity. | Number of community-based nature tourism initiatives strengthened that safeguard cultural, biological, and ecosystem services’ diversity. | Zero (0) | Four (4) under development | Four (4) | Nature tourism plans. Social, environmental, and economic feasibility reports Project reports | Social, environmental, and economic feasibility Interest by the government and non-government sectors to support initiatives | Project Team UNIDO SIRAP CARs National Parks MADS |
| Component 4: Knowledge management and project M&E |  |  |  |  |  |  |  |
| Outcome 4.1 Project monitored and evaluated with a results-based management approach, and communication of lessons learned. | Progress made in project implementation | 0% | 35-50% | 100% | PIRs PPRs Mid-term and terminal evaluation reports | The M&E plan of the project and related actions are implemented. Project executed within the intended time. | FAO-GEF and UNIDO-GEF Coordination Units MADS Team External Evaluators |
| Output 4.1.1. Five participatory action plans for the prioritized MUCBs. | Number of action plans | Zero (0) | Five (5), 1 per MUCB | Five (5), 1 per MUCB | Draft plans Monitoring and follow-up reports | Project actions to be implemented have been identified and prioritized in a participatory manner for each MUCB | Project Team SIRAP |
|  | Number of participation agreements at the MUCB level for the conservation and sustainable use of biodiversity | Zero (0) | Five (5), 1 per MUCB | Five (5), 1 per MUCB | Agreements signed Project monitoring and follow-up reports Project partners’ institutional reports | Willingness at the institutional and collective territories level to implement actions for the conservation and sustainable use of biodiversity | Project Team MUCB Coordinator |
| Output 4.1.2 An online M&E platform | Online monitoring platform | Zero (0) | One (1) online monitoring platform being designed | One (1) online monitoring platform operating | PIR PPRs Online monitoring platform reports | Effective use of the platform by the project and other stakeholders | Project Team FAO UNIDO Implementation Partners |
| Output 4.1.3: One communication strategy for development, implemented | Communication strategy | Zero (0) | One (1) communication strategy designed and in early stages of implementation | One (1) communication strategy implemented | Communication strategy reports Project-related publications PPRs | Best practices and lessons learned disseminated in a timely manner at the local, sub-national, national and regional (international) levels | Communication and Knowledge Management Expert FAO UNIDO Implementation Partners |
| Output 4.1.4: One Mid-term Review (MTR) and one Terminal Evaluation (TE) | One Mid-term Review and one terminal Evaluation | NA | Mid-term Review report | Terminal Evaluation report | Mid-term Review and Terminal Evaluation reports | Mid-term Review and Terminal Evaluation completed according to guidelines of FAO, UNIDO and GEF and within the intended timeframe | FAO-GEF and UNIDO-GEF Coordination Units External Evaluators |

ANNEX B:  RESPONSES TO PROJECT REVIEWS (from GEF Secretariat and GEF Agencies, and Responses to Comments from Council at work program inclusion and the Convention Secretariat and STAP at PIF).

| Reviewer’s comments | Responses | Reference in CEO Endorsement Document (or ProDoc) |
| --- | --- | --- |
| Secretariat Comment at CEO Endorsement (FSP)/Approval (MSP): NA |  |  |
| No comments |  |  |
| STAP Scientific and Technical screening of the Project Identification Form (PIF). Date of screening: May 03, 2017 |  |  |
| 1. The promotion of biodiversity-derived products as the key economic engine to provide incentives for sustainable land management is risky. While developing such products is important in the long term, and certainly to be encouraged, it puts this project at unnecessary risk. By taking on the double challenges of community land governance, and of developing new products, the probability of success of the project will be much reduced. Therefore, the PPG should consider whether improved methods of agronomy or silviculture/agroforestry (e.g. "Conservation Agriculture") might not be a much more effective and much less risky (and less complex) way of providing critical short-term incentives to a project that is already ambitious. Because of the importance of getting Component 2 to work, STAP suggests that Component 3 should be much more conservative (even if less innovative) and rely on improved agronomy. The project could still open the door a little to new bio-products, but should not rely heavily on this. This argument does not apply to ecotourism. Ecotourism is a reliable economic activity, with the caveat that it is not an entry-level activity for communities and will probably be most successful if it involves community–private partnerships, a destination business plan, marketing and scale (see below). | The project addresses the risks of promoting biodiversity-derived products as the key economic engine to provide incentives for sustainable land management by focusing on those products which have been studied thoroughly. Local communities in the five prioritized landscapes currently use well-studied biodiversity-derived products, for which technical support can be provided to ensure their sustainable use and add value, thus increasing the products’ market potential. During the PPG phase, the species used in three groups of products were identified, and a feasibility analysis was conducted to assess their potential for adding value and market access. The following species are used in the products which are part of the project: 1) the natural colorants achiote (Bixa orellana) and jagua (Genipa americana); 2) fats and oils, including açai (Euterpe oleracea), milpesos (Oenocarpus bataua), noli (Elaeis oleífera), cocoa (Theobroma cacao), coconut (Cocos nucifera), chontaduro (Peach-palm) (Bactris gasipaes), and don Pedrito (Oenocarpus minor); and 3) food, such as cocoa, coconut, borojo (Borojoa patinoi), açai, chontaduro, and vanilla (Vanilla planifolia). There is strong market demand for the above-mentioned species/products, particularly from companies producing natural, cosmetic, and food products. Most of these species are associated with the agroforestry and traditional production systems of Colombia’s Pacific coast; the technical knowledge for their cultivation, management, and use is currently available, as is the business know-how regarding product marketability and transformation. The agroforestry arrangements being promoted under the project focus on the use and sale of products such as cocoa, coconut, chontaduro, and açai. In the project area, it is estimated that there are 9 500 ha of cacao, 6 187 ha of coconut, 3 482 ha of chontaduro, and 1 099 ha of açai, among others. The species that are promising, but not yet well known, will not be part of the project as years of research will be required to investigate their agroecology and market potential. - As many as 77 production initiatives or green business ventures have been identified within the project area, which can generate goods and services based on the biodiversity present in the territory. Production and marketing initiatives using biodiversity-based products have in fact taken root throughout the Colombian Pacific region. Best practices and lessons learned from many of these initiatives – with long trajectories – can be incorporated into the project, such as Planeta and Corpocampo with açai, Nathivos and the development of fruit ice cream from the Pacific; Selvaceutica for natural cosmetics; Asocasan for achiote; chocolate from Tumaco; the Community Council ACAPA; and the ProCacao project for cocoa. | FAO-GEF Project Document, 1.3: The GEF Alternative, Component 3, and Appendix 11: Analysis of Potential Biodiversity-Derived Products |
| 2. As noted, the focus on local community stewardship is extremely important. However, more consideration should be given to (1) exactly how participation is operationalized and (2) to internal community governance to avoid elite capture (which is near ubiquitous) and to protect the rights of women and marginal groups to information, benefits and participation in decision-making. Specifically, what will the project do to increase the probability that Ostrom's 8 principles for long-lasting common property regimes are met? | Extensive stakeholder consultations were conducted during the PPG to ensure the participation and engagement of indigenous, black, and rural peoples in the project. A differential approach was incorporated in the design of the stakeholder engagement plan for the systematic inclusion of ethnic and cultural diversity and women’s equality as cross-cutting topics during the project development and implementation stages. This will ensure the participation of all stakeholders in the project’s area of influence, while protecting and respecting the rights of people, including members from indigenous, black, and rural communities, and women. The plan will respect the cultural diversity of these territories, and a participation mechanism will be applied throughout the project’s life cycle to ensure the achievement of the project’s objectives, the proper development of its activities, and the sustainability of its outcomes. A description of the principal participation mechanisms to be used during the project implementation process is provided in Section A.3. Stakeholders. The stakeholder engagement plan is included as Appendix 9 of the FAO-GEF Project Document. In addition, the right to Free, Prior and Informed Consent (FPIC) of these communities will be applied throughout the project in accordance with the FAO Manual for this process and Colombian laws (Act 89 of 1890, Act 160 of 1994, Act 21 of 1991, and Act 70 of 1993). FPIC is a right which is fully recognized by the International Labour Organization (ILO) under Convention 169 – the Indigenous and Tribal Peoples Convention, 1989 – and the United Nations Declaration on the Rights of Indigenous Peoples (UNDRIP); this right has been fully incorporated into the FAO Policy on Indigenous and Tribal Peoples, FAO Environmental and Social Guidelines, as well as UNIDO Environmental and Social Safeguards Policies and Procedures (ESSPP). Other aspects to be considered and respected during the project implementation process include the traditional authorities and government units of black and indigenous peoples, such as cabildos (indigenous peoples) and communal councils (black communities). These peoples have their own territories with common property rights recognized by law, including resguardos in the case of indigenous peoples, and collective territories in the case of the black communities. Through traditional authorities and government units of black and indigenous peoples, property rights are rendered non-prescriptive, cannot be seized, and are unalienable, while planning instruments – land-use planning and life plans – are safeguarded. This is consistent with Ostrom’s eight principles for long-lasting common property regimes. | Section A.3. Stakeholders FAO-GEF Project Document, Appendix 9: Stakeholder Engagement Plan and Consultation with Indigenous Peoples, Black Communities, and Rural Communities |
| 3. The risks identified in this PIF are not comprehensive. First, while the importance of local communities is central to this project, there needs to be more specific information on how "participation" will occur, and governance implications including issues of gender equity and marginalized groups within communities. Second, as mentioned above, the development of new biodiversity-derived products, value-chains and manufacturing plants is a complex issue, and is risky within the scope and budget of a 5-year project. Ecotourism has good markets. However, it is a complex business that depends on brand, marketing, scale and access (roads, airports). A few isolated community camps/ventures will probably fail. However, a business plan that develops a destination, and encourages community-private partnerships, has a much higher likelihood of success. Using this logic, the PIF might seek to develop a tourism business plan, which may well suggest that a certain number of leisure activities are necessary to cross a tourism-viability tipping point, rather than prescribing the development of two ventures. Similarly, the social, technical and economic challenges of how to "recover degraded areas" and of "economic alternatives to improve livelihoods" are significant and challenging. As above, achieving them within the scope and budget of a 5-year project is risky, especially if the PIF/PPG does not include a specific social/technical/financial assessment of what these generic terms mean. Finally, one of the explicitly stated objectives of this project is to support and build peace in post-war Colombia, with the underlying assumption in Component 3 that "providing alternative economic activities for returning populations will promote peace." While this may be true, current and past events indicate that the relationship is not at all simple or straightforward, e.g. South Sudan. Therefore, STAP recommends that project managers make an effort to learn lessons from post-conflict states and consult with expert organizations, such as the Environmental Law Institute and UN Environment's Expert Group on Environment, Conflict and Peacebuilding, which has just signed an agreement to work in post-conflict Colombia. See http://www.unep.org/newscentre/un-environment-will-support-environmental-recovery-and-peacebuilding- post-conflict-development. | The project risks were updated during the PPG phase and are described in more detail in Section A.5, Risk. In addition, an environmental and social risk assessment was conducted in accordance with FAO and UNIDO guidelines: UNIDO Environmental and Social Safeguards Policies and Procedures (ESSPP) and FAO Guidelines for Environmental and Social Risk Management. The results of the analysis are presented in Appendix 5 of the FAO-GEF Project Document. Risk was identified regarding the low participation of women, youth, and the elderly. As a result, mitigation measures – in accordance with GEF and FAO guidelines – have been put in place, incorporating a gender approach into the project’s final design to ensure the fair and equitable distribution of project benefits among women and men. As part of the project’s monitoring and evaluation strategy (M&E), gender-based indicators are included to evaluate benefits and collect gender disaggregated data, thus facilitating the assessment of progress regarding gender mainstreaming. Likewise, the project implementation team includes an expert in participatory, ethnic and gender approaches, who will ensure the active participation of women, youth, and the elderly in the project. The project will not only enhance the participation of women, youth, and the elderly in decision-making processes and training events, but it will also increase their access to economic incentives. For example, stakeholders will have control of and equal access to production resources, services, and markets. The participation of women and men in decision-making in rural institutions and political processes will be safeguarded, as will the equitable distribution of benefits from development interventions. The Gender Safeguard will ensure that inequality is not promoted or perpetuated, as it is based on the FAO Policy on Gender Equality and UNIDO Strategy on Gender Equality, which establish a regulatory framework to ensure minimal standards for integrating gender in a cross-cutting manner. This safeguard recognizes that gender equity is essential to the sustainability of interventions in the agriculture and rural development sectors. The project also includes a Gender Action Plan (included in Section A.4, Gender Equality and Women's Empowerment), which will further contribute to ensuring women’s participation in the project. During the PPG phase, an analysis was conducted on the feasibility of supporting nature-based tourism in the project. According to the results of this analysis, the project will support the following: a) an assessment of tourism products, services and infrastructure, and an analysis of the environment in terms of the market, tourist profile, compliance with quality requirements, safety and security, and environmental and social safeguards; b) a definition of the potential tourism business, including the business model, the actions to be developed to improve tourism competitiveness, compliance with quality standards and the incorporation of social and environmental safeguards, a commercial strategy for advertising and marketing, assessing training and delivering training, and investment; c) the implementation of prioritized actions to strengthen nature-based tourism initiatives, such as establishing tourist information points, waste management, and tourist activities, improving and demarcating nature trails, improving tourist services (e.g. food, transportation, and lodging), promoting nature-based tourism services, exchanging knowledge and experiences, and training and education; d) the pursuit of government and private support for the development of nature-based tourism initiatives; and e) technical support for beneficiary communities, which will strengthen the links between communities and other stakeholders in the tourism value chain through the promotion of sector and business roundtables, participation in fairs, and strategic partnerships, and help finance sustainable tourism development plans. During the PPG phase, 67 nature-based tourism initiatives were identified in the prioritized landscapes (i.e. MUCBs); four of which will be selected and strengthened through management planning and government and private support. The four initiatives will be selected using the following criteria: 1) the suitability of the area and community interest; 2) the presence of operational, nature-based tourism initiatives, which are led by or with community-based participation (e.g. communal councils, indigenous resguardos, native leaders, and local communities); 3) the potential for tourism products which can incorporate conservation-related areas of interest – such as Important Bird and Biodiversity Areas (IBAs), conservation corridors, civil society reserves, regional parks – and areas of sociocultural interest; and 4) the availability of infrastructure and basic tourist facilities. The MUCBs with the greatest potential to develop community-based nature tourism are Katíos-Caoba, Farrallones-Calima, and Tatamá; however, it is important to note that the proposed areas may be adjusted during the project implementation process. The recovery and restoration of degraded areas will be part of the project’s socio-ecosystem connectivity approach. This approach introduces the idea of connectivity as the collective construction of conservation mosaics, using inter-cultural dialogue mechanisms and social participation to promote the recovery of ecosystem services through environmental and land use planning, as well as the use of participatory management tools among institutions, communities, and production sectors. The recovery and restoration of degraded areas will include three steps. The first step in Year 1 is to identify areas for land restoration and recovery, including onsite verification and assessment of the conditions of the areas/ecosystem to be restored. The second step in Year 1 is to develop restoration and recovery plans in the priority MUCBs with stakeholder participation (i.e. MADS, CARs, PNN, indigenous, black, and rural communities), including women and youth. These restoration and recovery plans, at a minimum, will be clearly defined and include the following: a) the identification of sites for restoration; b) the identification of human and/or natural stressors; c) the establishment of community and institutional participation agreements; d) the restoration methods to be used (including traditional knowledge of indigenous, black, and rural peoples); e) the selection of species; f) the activities for land restoration and recovery; and g) a monitoring strategy. The third step, from Year 2 until the end of the project, is to implement land restoration and recovery activities, and promote agroforestry as one of the approaches to be used. The recovery and restoration of degraded areas will be in line with the restoration efforts carried out by the local environmental authorities (CARs), as part of their regular programming. To further bolster the development of economic alternatives for improved livelihoods in the time foreseen for the project (5 years), a strategy has been laid out, which focuses on improving the technical, administrative, and management capacities of stakeholders, and developing the necessary infrastructure to facilitate the marketability of biodiversity-derived products – with their added value and compliance with quality standards. There are three phases in the strategy. First, during Year 1, the value-added units for biodiversity-derived products will be selected, a market analysis will be conducted, the requirements for quality standards and sustainability for each product will be defined, and the business model will be developed in a participatory way. Second, during Years 2, 3 and 4, the facilities and equipment of the value-added units will be designed and improved, training programmes will be implemented, and technical support will be provided for the operation of the value-added units to ensure compliance with quality standards and sustainability requirements. The implementation phase for the commercial strategy for production will start in Year 3, including commercial trials, establishing contacts, marketing, and product commercialization. Third, during Years 4 and 5, the commercial strategy will continue and will be improved as needed, and a sustainability strategy of the value-adding units will be put into place. During the formulation of the project, lessons learned from the implementation of the peace process were reviewed for Guatemala and El Salvador, especially with regard to the implementation of alternative economic activities in rural areas. Lessons learned from Guatemala indicated that the main obstacles to the effective implementation of the socio-economic agreement were the lack of political will and the lack of support from the business sector. In addition, unfulfilled agreements related to land tenure are among the leading causes of social unrest in the country. The misappropriation of lands is widespread – by landowners, the military, and more recently by drug traffickers – as is the misappropriation of concessions to transnational companies for mining exploitation. In El Salvador, the implementation of the peace agreement was also slow due to a lack of political will, and only recently has progress been made in the implementation of economic and social aspects of the agreement. Progress has in fact been made in many areas: securing land tenure rights; strengthening the agricultural sector and improving productivity to supply domestic markets; restructuring social programmes to reduce poverty and social exclusion; and restructuring economic policies aimed at transforming production processes for the benefit of the micro, small, and medium producers; and in environmental sustainability, among others. In Colombia, as part of the implementation of the final peace agreement, the “Policy of Integral Agrarian Development, Towards a new rural Colombia: Integral Rural Reform” (RRI), was developed for the transformation of the countryside, and to create the necessary conditions to improve the well-being of the rural population. The RRI is focused on improving the quality of life of the rural population, which includes indigenous and black communities. Among other things, it seeks to strengthen the rural family economy, through integration with local and national markets and different incentives to improve productivity. Conversely, the Colombia in Peace Fund (CONPES 3850) was established as an initiative to enhance inter-institutional coordination. This Peace Fund is aimed at maximizing the environmental, economic, and social benefits of peace through the promotion of sustainable rural development, the conservation of biodiversity, and the fight against climate change, all within a framework that strengthens the rule of law. As part of its strategy for the use of forests and biodiversity, CONPES 3850 will support efforts to establish and consolidate value chains for different products through the sustainable use of biodiversity (e.g. timber and non-timber forest products). This includes technical assistance, facilitating access to markets, technology, and compliance with sanitary and quality requirements, among others. The project is consistent with the RRI and the CONPES 3850 document, in particular through Component 3, noting that the Colombian peace process and the final agreement was the result of a 3-year process of consultations. These consultations incorporated the lessons learned from experiences in Guatemala and El Salvador, thereby increasing the likelihood that alternative economic activities would be identified for local populations. | A.4. Gender Equality and Women's Empowerment Section A.5 Risk. FAO-GEF Project Document, Appendix 5: Environmental and Social Assessment; Appendix 6: Environmental and Social Risk Management Plan; Appendix 12: Analysis of Potential Biodiversity-Derived Products |
| Canada’s comments |  |  |
| This project is aligned with national priorities, primarily the National Development Plan 2014–2018, Colombia’s commitments under the Convention of Biological Diversity, the Biodiversity Action Plan, the National Green Business Plan and the Somos PaZcifico Program. It also complements other activities undertaken by state institutions, NGOs and several donors. We encourage coordination with these efforts and with government programs. | Thank you for your suggestion. The project is aligned with all of the initiatives listed. Also, representatives of these initiatives – from the government, NGOs, and private donors – were consulted during the PPG phase; they also participated in project events, such as the Inception Workshop, Results Framework Workshop, and Validation Workshop. | B.1 Consistency with National Priorities FAO-GEF Project Document, Section 1.2 The Current Situation, 1.2.2 Baseline initiatives |
| The project has the potential of contributing to the implementation of the peace agreement, primarily in the rural development chapter, as well as sustainable livelihoods for displaced populations who return to their territories, indigenous and afro-Colombian communities and possibly demobilized combatants. However, the presence of illegal armed actors and illicit economic activities may put pressure on the project’s beneficiaries and partners. Are there mitigation measures in place to address this? | One of the factors considered for defining and prioritizing the MUCBs was the situation of security and public order. The areas selected represent where the main efforts for the consolidation of peace are found. Likewise, the security criteria will be considered when selecting the areas for pilot activities, and during the Technical Committee meetings of each MUCB. The security measures required by the United Nations system will be applied in such cases. The United Nations Department of Safety and Security (UNDSS) periodically evaluates the risks of the country and the specific risks for those operating in the field. This information is then shared with all the United Nations system agencies. Additionally, with the aid of the Department of Protection of Citizens’ rights Early Warning System, communities and institutions can monitor conflict-related risks. The project will strictly follow the advice of the UNDSS concerning all matters related to the security of the United Nations and the project staff working on activities involving office locations, movement, and the participation of populations in remote areas. | Section A.5 Risk. |
| Additional information on FAO’s and UNIDO’s experience in this type of programming and capacity to implement the project in the region, including support from the different partners listed in the project proposal is requested. | FAO’s work in Colombia focuses on the following areas: - Fighting food insecurity and malnutrition. - Incorporating a human rights perspective into policy frameworks and policies. - Encouraging the participation of civil society in capacity building within the cycle of policies on food and nutrition security. - Managing natural resources and the governance of forests, land, and water. - Promoting social and technological innovation for sustainable food systems to reduce urban-rural gaps. - Promoting public policies aimed at the social and economic inclusion of family farming. - Managing risks and rehabilitating livelihoods, generating resilience in vulnerable communities. In addition, within the framework of the Peace Agreement between the Government of Colombia and the Revolutionary Armed Forces of Colombia ‒ People’s Army (FARC) – FAO has designed a strategy called Estrategia de Acompañamiento de FAO a la Implementación del Acuerdo de Paz en Colombia. This strategy defines the concrete objectives to implement what was established in the 2015‒2019 Country Programming Framework. Within this framework, the FAO Resilience Programme emphasizes all aspects related to resilience building as the main strategy in post-conflict scenarios and areas where natural disasters are recurrent. FAO is currently implementing a number of related initiatives in Colombia: a) The GEF Project: Implementing the Socio-Ecosystem Connectivity Approach to Conserve and Sustainable Use Biodiversity in the Caribbean Region of Colombia (GEF ID 5288). Also known as the Bio-Caribbean Connection, its objective is to implement a strategy of socio-ecosystem connectivity, which includes inter-institutional articulation, territorial planning, social participation with an intercultural vision, the effective management of existing protected areas (PAs), the creation of new PAs, and the promotion of sustainable production models. This project is being executed in association with MADS, MADR, SIRAP Caribe, PNN, CARs (CVS, CARDIQUE, CODECHOCO, CORPOURABA, and CARSUCRE), and government departments. This Project covers one of the proposed MUCBs (Katios-Caoba). b) Forestería comunitaria, un modelo que le apuesta a la defensa de los bosques. This initiative – jointly implemented by the Colombian Ministry of Environment and Sustainable Development and the European Union – is part of the national strategy to manage the country's forests and counteract deforestation. Community forestry provides people with a viable economic alternative: it helps conserve forests, improves the livelihoods of local communities, reduces deforestation, promotes the conservation of ecosystems, and strengthens local social capital. c) The Rural Development Agency (ADR/MADR) – FAO Alliance. This strategy focuses on building the capacities of professionals, technicians, and extension officers in ten departments (including Chocó, Risaralda, Cauca, Valle del Cauca, and Nariño), all of which are covered under the project proposed herein. 10 Colombian departments are responsible for designing, implementing, or developing Integral Projects for Agricultural and Rural Development (PIDAR). UNIDO has been promoting the implementation of sustainable production alternatives that meet environmental and quality standards. For example, cleaner, small-scale gold extraction technologies were introduced in the Colombian Pacific region – in the department of Chocó and Antioquia (Rio San Juan) – through UNIDO’s Global Mercury-2 Project (GMP-2). In addition, UNIDO is promoting the development of export consortia for the agro-industry and for natural cosmetics through the project "Development of Export Consortia in the Valle del Cauca Region of Colombia in the agro-industry and cosmetic sectors.” To further boost the natural cosmetics and agro-industry sectors’ competitiveness and presence on the international market, a partnership has been formed with the Korea International Cooperation Agency (KOICA), and Colombia's Ministry of Commerce, Industry, and Tourism (MINCIT). This partnership is also aimed at improving employment possibilities for local people. The eight consortia supported through the project are related to the cosmetics and food sectors, which use biodiversity-derived products, such as chontaduro. Additionally, through the implementation of the Safe+ Program, UNIDO actively promotes the increased competitiveness of Colombian natural ingredients from biodiversity in the Pacific region. The Safe+ Program also ensures the fulfilment of technical and quality requirements for export: increasing local companies’ access to international markets, testing laboratories, calibration laboratories, inspection organizations, certification organizations, suppliers of reference materials, and proficiency testing providers. By providing technical support to the value chain of natural ingredients, the country’s quality infrastructure is reinforced, and the entire national quality system is strengthened for the cosmetic sector. With UNIDO’s support for the aforementioned sectors, key stakeholders can be identified, with whom market alliances can be developed for the biodiversity-derived products supported through the project. The management and support processes carried out by UNIDO in the region have been developed in coordination with the MADS (office of international affairs), municipal and departmental governments, IIAP, and CODECHOCO. All of these programmes are executed from the UNIDO office, located in the city of Cali (department of Valle del Cauca), allowing coverage of the entire Colombian Pacific region. | FAO-GEF Project Document, Section 3. Implementation and Management Arrangements |
| We would like to see a more robust gender analysis conducted prior to final approval and more information on the innovative approaches to forestry management, biotrade and productive practices. | The project includes a Gender Analysis and Gender Action Plan, both of which were developed during the PPG. In addition, the project’s results framework includes gender-sensitive indicators. Please refer to Section A.4, Gender Equality and Women's Empowerment, of this CEO Endorsement Request for details. Forestry management plans will be designed for each MUCB, considering supply needs. Surveys will be conducted, and participatory workshops will be held to construct a baseline of the current status of the families participating in SFM initiatives, in terms of income and characteristics of forestry production. Baseline information will be used in the development of sustainable production, considering the following: a) design of agroforestry arrangements, including the use of landscape management tools (forestry elements that constitute or improve habitat and increase functional connectivity); b) land-use planning; c) identification of technological needs and inclusion of the traditional knowledge of black and indigenous peoples; d) biodiversity conservation and SFM agreements; and e) design of field schools adapted to the context and culture of each MUCB, including a gender and ethnic approach. Training will be delivered as a basic component of the capacity strengthening process for SFM. Information regarding biotrade and production practices is included in the response to the previous STAP Comment 1, and in the response to Germany Comment 1 found below. Also, more detailed information is included in the description of activities related to project Component 3 (Outputs 3.2.1 and 3.2.2). | A.4. Gender Equality and Women's Empowerment FAO-GEF Project Document, 1.3 The GEF Alternative, Component 3. FAO-GEF Project Document, Appendix 13 |
| Germany’s comments |  |  |
| The full proposal should clearly identify the challenges of fulfilling basic parameters (such as production in sufficient quantity and quality) prior to discussing the import substitution of foreign products. | Support for biodiversity products and services (Component 3) focuses mainly on regional and national markets. Being without a stable supply of quality local products, the country is a net importer of natural ingredients. To ensure production capacity, the project takes two key elements into account: 1) The focus will be on products that have crops grown in the project prioritized areas (MUCBs), and for which there is sufficient technical information and expertise – in terms of crop production, use, and transformation. 2) Technical support will be provided for sustainable production systems covering 10 000 hectares, and a raw material supply plan will be developed to ensure the availability of raw material for the value-added units. To ensure quality, the project will provide permanent technical support to the value-added units and will develop product improvement plans to comply with market quality requirements. UNIDO has extensive experience in this regard, which has been developed through the implementation of the aforementioned Safe+ Program and Export Consortia projects. Also, during the PPG phase, UNIDO consulted with more than ten national companies, which develop products from Colombian natural ingredients, mainly in the cosmetic and food sectors. These companies recommended focusing on the products that have potential for establishing commercial agreements, and can be supplied in the required quantities and with the market quality requirements. These recommendations were taken into account during the selection process of biodiversity-derived products to be supported by the project; they will also be considered in the development of production and marketing plans for each product. | FAO-GEF Project Document, 1.3 The GEF Alternative, Component 3. |
| Indicators of project Component 1 (Institutional strengthening to support the mainstreaming of biodiversity conservation and sustainable use in the Pacific region of Colombia) should have a stronger focus on results, that is on implementation and monitoring of plans rather than on the planning itself. While first approaches are described under outcome 1.2., Germany suggests that these should become a primary focus of component 1 in the final project proposal. | Component 1 will focus on addressing the existing barriers that prevent the harmonization of government instruments for territorial planning and environmental management with the instruments developed by black and indigenous peoples. These barriers are mainly due to different land-use perspectives (production, environmental, sociocultural and rural perspectives); therefore, measures need to be taken to safeguard cultural and biological diversity, as well as ecosystem services. Component 1 also focuses on strengthening the capacities of key stakeholders at the local level – such as SIRAP Pacific, CARs, and local communities – so that they may better implement and monitor the enhanced instruments for territorial planning and environmental management. This enabling environment will be conducive to directly reducing current and potential pressures from competing and forest-degrading land uses in at least 1,061,655 hectares within PAs, and to the improved management of 210 193 hectares outside the PAs – in areas which are of strategic importance for biodiversity conservation. Components 2 and 3 include the guidelines for the application of the instruments for territorial planning and environmental management in five prioritized landscapes – MUCBs – in the Colombian Pacific region. | Part I: Project Information, B. Project Description Summary |
| With regard to the partners outlined in the PIF, the institutional post-conflict architecture has only recently been adjusted and a coordinating authority has been put in place with the Alta Consejeria para el Posconflicto, Derechos Humanos y Seguridad – ACP. The Institute for Rural Development (Instituto Colombiano de Desarrollo Rural – INCODER), a subordinate agency of the Ministry of Agriculture has been dissolved and three new national entities have been created (Agencia Nacional de Tierra – ANT, Agencia Nacional de Desarrollo Rural – ADR, Agencia Nacional de Renovación del Territorio – ART). Additionally a High Commission for Landuse- Planning has been established (Consejo superior del orden del suelo rural). The exact assignment of responsibilities between these and already existing institutions is still under discussion. These imponderabilities should be considered within the risks. | As suggested, the newly defined institutional post-conflict structure, roles and responsibilities constitute a project risk. However, the institutional post-conflict structure has been operational since 2017, and the roles of key agencies have been defined, including the following: a) Alta Consejeria para el Posconflicto, which includes four main units: - Dirección para el Posconflicto; - Dirección para la Acción Integral contra Minas Antipersonal - Descontamina Colombia; - Dirección para la Sustitución de Cultivos Ilícito; and - Dirección de Inversión Privada para el Posconflicto. b) Patrimonio Autónomo Fondo Colombia en Paz PA-FCP, through which the financial resources for the implementation of the Peace Agreement will be made available. In relation to the rural agricultural sector, the following have been established: - Development Programs with Territorial Approach (PDETs), with the objective of transforming the structure of rural areas through an equal relationship between cities and the areas where the PDETs will be implemented. - Agencia Nacional de Tierras (ANT), which will be charged with the titling of lands and unoccupied lands to producers and rural families. - Agencia Nacional de Renovación del Territorio (ART), which is charged with assisting the development of the so-called "post-conflict municipalities", and is responsible for advancing comprehensive rural reform. - Agencia Nacional de Desarrollo Rural (ADR), whose function is to support the execution of comprehensive plans and projects for agricultural and rural development, with a territorial or associative approach. | Section A.5 Risk. |
| With regard to the potential biodiversity products mentioned in the Annex, Germany encourages to ensure that access and benefit sharing (ABS) relevance is checked with the national ABS focal point or with the ABS Competent National Authority. | The project includes access to Genetic Resources and Fair and Equitable Sharing of the Benefits derived from its use (ABS) in a broad sense. Work will be done on the aggregate value of existing products – mainly those with natural ingredients or food products – as part of the strategy to mainstream biodiversity conservation and sustainable use into production landscapes (GEF Biodiversity Focal Area Objective 4, Program 9). For the distribution of benefits during the first months of project execution, the business model of each value-added unit will be structured to include aspects related to community participation and benefit distribution. In fact, one of the main stakes of the project is exactly find innovative mechanisms to provide so that the populations have incentives to conserve natural resources and to leverage the benefits of a more sustainable management. The project will include the following groups of products: 1) the natural colorants achiote (Bixa orellana) and jagua (Genipa americana); 2) fats and oils, including açai (Euterpe oleracea), milpesos (Oenocarpus bataua), noli (Elaeis oleífera), cocoa (Theobroma cacao), coconut (Cocos nucifera), chontaduro (peach-palm) (Bactris gasipaes), and don Pedrito (Oenocarpus minor); and 3) food, such as cocoa, coconut, borojo (Borojoa patinoi), açai chontaduro, and vanilla (Vanilla planifolia). Consultations were held with the technical offices of the MADS (Green Businesses, Forests and International Affairs Office), to discuss sustainable production initiatives, which are prioritized for the Colombian Pacific area by the MADS. During the first months of the project, the execution of the five products to be generated will be determined. The product possibilities include achiote powder, palm oil, fine and aroma cocoa, cocoa powder, cocoa butter, chontaduro oil, chontaduro foods, coconut oil, coconut pulp, azai extract, and others. As suggested, during the PPG phase, the MADS genetic resources expert group (Forest Management, Biodiversity, and Ecosystem Services Unit/ABS National Focal Point), was consulted regarding research and commercial contracts to access genetic resources and their derived products at the national level. The expert group identified an initiative for the commercialization of the pulp of Genipa americana to obtain dye, as well as bioprospecting and the development of natural ingredients for the cosmetic, pharmaceutical, and hygiene products industries. Consultations were also made concerning the application of the Nagoya Protocol for commercial access to a product derived from the American genipa; these consultations were led by the United Nations Development Programme (UNDP), and Fondo Acción – a Colombian non-profit private foundation that was established in 2000 pursuant to a bilateral agreement between Colombia and the United States within the framework of the Initiative for the Americas. The following lessons learned regarding the regulatory, institutional, social, and economic context were considered: - It is beneficial to work with products that can be grown and extracted from their natural environment, and to work with species with which the environmental authorities already have experience in granting use permits. - The exploration of local and national markets is a lengthy process, as is compliance with international market requirements. - It is important to work hand in hand with the MADS and the environmental authorities, as there are still many regulatory gaps. - Local communities must be actively involved in the process, and long-lasting, clear communication channels are needed to promote a culture of entrepreneurship. | FAO-GEF Project Document, 1.3 The GEF Alternative, Component 3. |

Annex C:  status of implementation of project preparation activities and the use of funds

A.  Provide detailed funding amount of the PPG activities financing status in the table below:

| PPG Grant Approved at PIF: 200,000 |  |  |  |
| --- | --- | --- | --- |
| Project Preparation Activities Implemented | GEF/LDCF/SCCF Amount ($) |  |  |
|  | Budgeted Amount | Amount Spent to date | Amount Committed |
| FAO |  |  |  |
| Project formulation preparatory actions | 3,706 | 1,779 |  |
| Dialogues with national and local actors | 34,365 | 45,645 |  |
| Actors mapping and analysis, co-financing, related initiatives | 10,127 | 8,958 |  |
| Design of Component 1 | 20,284 | 19,382 |  |
| Design of Component 2 | 20,284 | 16,843 |  |
| Design of Component 3 | 5,101 | 2,788 |  |
| Design of Component 4 | 2,628 | 3,097 |  |
| Social and environment analysis risk and mitigation plan | 14,108 | 12,895 |  |
| UNIDO |  |  |  |
| Information review, project design and budget | 37,546 | 21,670 | 15,092 |
| Analysis of environmental challenges in the region | 8,118 | 8,118 |  |
| Study on biodiversity product potential | 10,000 | 10,000 |  |
| Verification on biodiversity potential | 13,000 | 13,000 |  |
| Verification of potential biodiversity products to be developed with local communities | 1,734 | 1,734 |  |
| Design of UNIDO Outcome 3.2 and coordination with FAO | 12,000 | 12,000 |  |
| Translation of final document into English | 7,000 | 7,000 |  |
| Total | 200,000 | 184,908 | 15,092 |

annex D:  calendar  of expected reflows (if non-grant instrument is used)

Provide a calendar of expected reflows to the GEF/LDCF/SCCF Trust Funds or to your Agency (and/or revolving fund that will be set up)

NA

Annex E: GEF 7 Core Indicator Worksheet

| Core Indicator 1 | Terrestrial protected areas created or under improved management for conservation and sustainable use |  |  |  |  |  |  |  |  |  |  |  |  |  |  | (Hectares) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  | Hectares (1.1+1.2) |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  | Expected |  |  |  |  |  |  | Achieved |  |  |
|  |  |  |  |  |  |  | PIF stage |  |  |  | Endorsement |  |  | MTR |  | TE |
|  |  |  |  |  |  |  | 560,000 |  |  |  | 650,180 |  |  |  |  |  |
| Indicator 1.1 | Terrestrial protected areas newly created |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Name of Protected Area | WDPA ID | IUCN category |  |  |  |  |  | Hectares |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  | Expected |  |  |  |  |  |  | Achieved |  |
|  |  |  |  |  |  |  |  | PIF stage |  |  | Endorsement |  |  |  | MTR | TE |
| Relictos de Caoba | TBD | TBD |  |  |  |  |  | n/a |  |  | 63,686 |  |  |  |  |  |
| Serranias de los Paraguas | TBD | TBD |  |  |  |  |  | n/a |  |  | 191,561 |  |  |  |  |  |
| Calle Santa Rosa | TBD | TBD |  |  |  |  |  | n/a |  |  | 3,356 |  |  |  |  |  |
|  |  | Sum |  |  |  |  |  | 150,000 |  |  | 258,603 |  |  |  |  |  |
| Indicator 1.2 | Terrestrial protected areas under improved management effectiveness |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Name of Protected Area | WDPA ID | IUCN category |  | Hectares |  |  |  | METT Score |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  | Baseline |  |  |  |  |  |  | Achieved |  |
|  |  |  |  |  |  |  |  |  |  |  | Endorsement |  |  |  | MTR | TE |
| Los Katíos National Park | 61610 |  | 72,000 |  |  |  |  |  |  |  | 66 |  |  |  |  |  |
| Los Farallones de Cali Natural National Park | 138 |  | 196,430 |  |  |  |  |  |  |  | 67 |  |  |  |  |  |
| Tatamá Natural National Park | 13966 |  | 51,900 |  |  |  |  |  |  |  | 68 |  |  |  |  |  |
| Munchique Natural National Park | 146 |  | 46,969 |  |  |  |  |  |  |  | 68 |  |  |  |  |  |
| Rio Bravo Regional Forest Protectress Reserve | Unknown |  | 24,278 |  |  |  |  |  |  |  | 40 |  |  |  |  |  |
| Core Indicator 2 | Marine protected areas created or under improved management for conservation and sustainable use |  |  |  |  |  |  |  |  |  |  |  |  |  |  | (Hectares) |
|  |  |  |  |  |  | Hectares (2.1+2.2) |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  | Expected |  |  |  |  |  |  | Achieved |  |  |  |
|  |  |  |  |  |  | PIF stage |  |  | Endorsement |  |  |  | MTR |  |  | TE |
|  |  |  |  |  |  | Unknown |  |  | 190,282 |  |  |  |  |  |  |  |
| Indicator 2.1 | Marine protected areas newly created |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Name of Protected Area | WDPA ID | IUCN category |  |  |  |  |  | Hectares |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  | Expected |  |  |  |  |  |  | Achieved |  |
|  |  |  |  |  |  |  |  | PIF stage |  |  | Endorsement |  |  |  | MTR | TE |
|  |  |  |  |  |  |  |  | n/a |  |  | n/a |  |  |  |  |  |
|  |  | Sum |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Indicator 2.2 | Marine protected areas under improved management effectiveness |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Name of Protected Area | WDPA ID | IUCN category |  |  | Hectares |  |  | METT Score (Scale 1-3) |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  | Baseline |  |  |  |  |  |  | Achieved |  |
|  |  |  |  |  |  |  |  | PIF stage |  |  | Endorsement |  |  |  | MTR | TE |
| Cabo Manglares Bajo Mira y Frontera | 555636091 | Not Reported |  |  | 190,282 |  |  | n/a |  |  | 40 |  |  |  |  |  |
|  |  | Sum |  |  | 190,282 |  |  |  |  |  |  |  |  |  |  |  |
| Core Indicator 3 | Area of land restored |  |  |  |  |  |  |  |  |  |  |  |  |  |  | (Hectares) |
|  |  |  |  |  |  |  | Hectares (3.1+3.2+3.3+3.4) |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  | Expected |  |  |  |  |  | Achieved |  |  |  |
|  |  |  |  |  |  |  | PIF stage |  |  |  | Endorsement |  | MTR |  |  | TE |
|  |  |  |  |  |  |  | 2,000 |  |  |  | 1,000 |  |  |  |  |  |
| Indicator 3.1 | Area of degraded agricultural land restored |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  | Hectares |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  | Expected |  |  |  |  |  |  | Achieved |  |
|  |  |  |  |  |  |  |  | PIF stage |  |  | Endorsement |  |  |  | MTR | TE |
|  |  |  |  |  |  |  |  | n/a |  |  | n/a |  |  |  |  |  |
| Indicator 3.2 | Area of forest and forest land restored |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  | Hectares |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  | Expected |  |  |  |  |  |  | Achieved |  |
|  |  |  |  |  |  |  |  | PIF stage |  |  | Endorsement |  |  |  | MTR | TE |
|  |  |  |  |  |  |  |  | 2,000 |  |  | 1,000 |  |  |  |  |  |
| Indicator 3.3 | Area of natural grass and shrublands restored |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  | Hectares |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  | Expected |  |  |  |  |  |  | Achieved |  |
|  |  |  |  |  |  |  |  | PIF stage |  |  | Endorsement |  |  |  | MTR | TE |
|  |  |  |  |  |  |  |  | n/a |  |  | n/a |  |  |  |  |  |
| Indicator 3.4 | Area of wetlands (including estuaries, mangroves) restored |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  | Hectares |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  | Expected |  |  |  |  |  |  | Achieved |  |
|  |  |  |  |  |  |  |  | PIF stage |  |  | Endorsement |  |  |  | MTR | TE |
|  |  |  |  |  |  |  |  | n/a |  |  | n/a |  |  |  |  |  |
| Core Indicator 4 | Area of landscapes under improved practices (hectares; excluding protected areas) |  |  |  |  |  |  |  |  |  |  |  |  |  |  | (Hectares) |
|  |  |  |  |  |  |  | Hectares (4.1+4.2+4.3+4.4) |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  | Expected |  |  |  |  |  | Expected |  |  |  |
|  |  |  |  |  |  |  | PIF stage |  |  |  | Endorsement |  | MTR |  |  | TE |
|  |  |  |  |  |  |  | 310,000 |  |  |  | 220,193 |  |  |  |  |  |
| Indicator 4.1 | Area of landscapes under improved management to benefit biodiversity |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  | Hectares |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  | Expected |  |  |  |  |  |  | Achieved |  |
|  |  |  |  |  |  |  |  | PIF stage |  |  | Endorsement |  |  |  | MTR | TE |
|  |  |  |  |  |  |  |  | 300,000 |  |  | 210,193 |  |  |  |  |  |
| Indicator 4.2 | Area of landscapes that meet national or international third-party certification that incorporates biodiversity considerations |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Third party certification(s): |  |  |  |  |  |  |  | Hectares |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  | Expected |  |  |  |  |  |  | Achieved |  |
|  |  |  |  |  |  |  |  | PIF stage |  |  | Endorsement |  |  |  | MTR | TE |
|  |  |  |  |  |  |  |  | n/a |  |  | TBD |  |  |  |  |  |
| Indicator 4.3 | Area of landscapes under sustainable land management in production systems |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  | Hectares |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  | Expected |  |  |  |  |  |  | Achieved |  |
|  |  |  |  |  |  |  |  | PIF stage |  |  | Endorsement |  |  |  | MTR | TE |
|  |  |  |  |  |  |  |  | 10,000 |  |  | 10,000 |  |  |  |  |  |
| Indicator 4.4 | Area of High Conservation Value Forest (HCVF) loss avoided |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  | Hectares |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  | Expected |  |  |  |  |  |  | Achieved |  |
|  |  |  |  |  |  |  |  | PIF stage |  |  | Endorsement |  |  |  | MTR | TE |
|  |  |  |  |  |  |  |  | n/a |  |  | n/a |  |  |  |  |  |
| Core Indicator 6 | Greenhouse gas emission mitigated |  |  |  |  |  |  |  |  |  |  |  |  |  |  | (Tons) |
|  |  |  |  |  |  |  |  | Tons (6.1+6.2) |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  | Entered |  |  |  | Entered |  |  |  |  |
|  |  |  |  |  |  |  |  | PIF stage |  | Endorsement |  | MTR |  |  |  | TE |
|  | Expected CO2e (direct) |  |  |  |  |  |  | 2,701,280 |  | 3,600,703 |  |  |  |  |  |  |
|  | Expected CO2e (indirect) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Indicator 6.1 | Carbon sequestered or emissions avoided in the AFOLU sector |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  | Tons |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  | Entered |  |  |  |  |  |  | Entered |  |
|  |  |  |  |  |  |  |  | PIF stage |  |  | Endorsement |  |  |  | MTR | TE |
|  | Expected CO2e (direct) |  |  |  |  |  |  | 21,293 |  |  | 10,646 |  |  |  |  |  |
|  | Expected CO2e (indirect) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Anticipated Year |  |  |  |  |  |  | 2023 |  |  | 2023 |  |  |  |  |  |
| Indicator 6.2 | Emissions avoided |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  | Hectares |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  | Expected |  |  |  |  |  |  | Achieved |  |
|  |  |  |  |  |  |  |  | PIF stage |  |  | Endorsement |  |  |  | MTR | TE |
|  | Expected CO2e (direct) |  |  |  |  |  |  | 2,679,987 |  |  | 3,590,057 |  |  |  |  |  |
|  | Expected CO2e (indirect) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Anticipated Year |  |  |  |  |  |  | 2023 |  |  | 2023 |  |  |  |  |  |
| Indicator 6.3 | Energy saved |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  | MJ |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  | Expected |  |  |  |  |  |  | Achieved |  |
|  |  |  |  |  |  |  |  | PIF stage |  |  | Endorsement |  |  |  | MTR | TE |
|  |  |  |  |  |  |  |  | n/a |  |  | n/a |  |  |  |  |  |
| Indicator 6.4 | Increase in installed renewable energy capacity per technology |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Technology |  |  |  |  |  | Capacity (MW) |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  | Expected |  |  |  |  |  |  | Achieved |  |
|  |  |  |  |  |  |  |  | PIF stage |  |  | Endorsement |  |  |  | MTR | TE |
|  |  |  |  |  |  |  |  | n/a |  |  | n/a |  |  |  |  |  |
| Core Indicator 11 | Number of direct beneficiaries disaggregated by gender as co-benefit of GEF investment |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 4,000 (40% women, 60% men) |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Number Achieved |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | MTR | TE |
|  |  |  |  |  |  |  |  |  |  |  | Female |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  | Male |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  | Total |  |  |  |  |  |

Annex F: GEF Project Taxonomy Worksheet

| Level 1 | Level 2 | Level 3 | Level 4 |
| --- | --- | --- | --- |
| Influencing models |  |  |  |
|  | Transform policy and regulatory environments |  |  |
|  | Strengthen institutional capacity and decision-making |  |  |
|  | Convene multi-stakeholder alliances |  |  |
|  | Demonstrate innovative approaches |  |  |
|  | Deploy innovative financial instruments |  |  |
| Stakeholders |  |  |  |
|  | Indigenous Peoples |  |  |
|  | Private Sector |  |  |
|  |  | Capital providers |  |
|  |  | Financial intermediaries and market facilitators |  |
|  |  | Large corporations |  |
|  |  | SMEs |  |
|  |  | Individuals/Entrepreneurs |  |
|  |  | Non-Grant Pilot |  |
|  |  | Project Reflow |  |
|  | Beneficiaries |  |  |
|  | Local Communities |  |  |
|  | Civil Society |  |  |
|  |  | Community Based Organization |  |
|  |  | Non-Governmental Organization |  |
|  |  | Academia |  |
|  |  | Trade Unions and Workers Unions |  |
|  | Type of Engagement |  |  |
|  |  | Information Dissemination |  |
|  |  | Partnership |  |
|  |  | Consultation |  |
|  |  | Participation |  |
|  | Communications |  |  |
|  |  | Awareness Raising |  |
|  |  | Education |  |
|  |  | Public Campaigns |  |
|  |  | Behavior Change |  |
| Capacity, Knowledge and Research |  |  |  |
|  | Enabling Activities |  |  |
|  | Capacity Development |  |  |
|  | Knowledge Generation and Exchange |  |  |
|  | Targeted Research |  |  |
|  | Learning |  |  |
|  |  | Theory of Change |  |
|  |  | Adaptive Management |  |
|  |  | Indicators to Measure Change |  |
|  | Innovation |  |  |
|  | Knowledge and Learning |  |  |
|  |  | Knowledge Management |  |
|  |  | Innovation |  |
|  |  | Capacity Development |  |
|  |  | Learning |  |
|  | Stakeholder Engagement Plan |  |  |
| Gender Equality |  |  |  |
|  | Gender Mainstreaming |  |  |
|  |  | Beneficiaries |  |
|  |  | Women groups |  |
|  |  | Sex-disaggregated indicators |  |
|  |  | Gender-sensitive indicators |  |
|  | Gender results areas |  |  |
|  |  | Access and control over natural resources |  |
|  |  | Participation and leadership |  |
|  |  | Access to benefits and services |  |
|  |  | Capacity development |  |
|  |  | Awareness raising |  |
|  |  | Knowledge generation |  |
| Focal Areas/Theme |  |  |  |
|  | Integrated Programs |  |  |
|  |  | Commodity Supply Chains (Good Growth Partnership) |  |
|  |  |  | Sustainable Commodities Production |
|  |  |  | Deforestation-free Sourcing |
|  |  |  | Financial Screening Tools |
|  |  |  | High Conservation Value Forests |
|  |  |  | High Carbon Stocks Forests |
|  |  |  | Soybean Supply Chain |
|  |  |  | Oil Palm Supply Chain |
|  |  |  | Beef Supply Chain |
|  |  |  | Smallholder Farmers |
|  |  |  | Adaptive Management |
|  |  | Food Security in Sub-Sahara Africa |  |
|  |  |  | Resilience (climate and shocks) |
|  |  |  | Sustainable Production Systems |
|  |  |  | Agroecosystems |
|  |  |  | Land and Soil Health |
|  |  |  | Diversified Farming |
|  |  |  | Integrated Land and Water Management |
|  |  |  | Smallholder Farming |
|  |  |  | Small and Medium Enterprises |
|  |  |  | Crop Genetic Diversity |
|  |  |  | Food Value Chains |
|  |  |  | Gender Dimensions |
|  |  |  | Multi-stakeholder Platforms |
|  |  | Food Systems, Land Use and Restoration |  |
|  |  |  | Sustainable Food Systems |
|  |  |  | Landscape Restoration |
|  |  |  | Sustainable Commodity Production |
|  |  |  | Comprehensive Land Use Planning |
|  |  |  | Integrated Landscapes |
|  |  |  | Food Value Chains |
|  |  |  | Deforestation-free Sourcing |
|  |  |  | Smallholder Farmers |
|  |  | Sustainable Cities |  |
|  |  |  | Integrated urban planning |
|  |  |  | Urban sustainability framework |
|  |  |  | Transport and Mobility |
|  |  |  | Buildings |
|  |  |  | Municipal waste management |
|  |  |  | Green space |
|  |  |  | Urban Biodiversity |
|  |  |  | Urban Food Systems |
|  |  |  | Energy efficiency |
|  |  |  | Municipal Financing |
|  |  |  | Global Platform for Sustainable Cities |
|  |  |  | Urban Resilience |
|  | Biodiversity |  |  |
|  |  | Protected Areas and Landscapes |  |
|  |  |  | Terrestrial Protected Areas |
|  |  |  | Coastal and Marine Protected Areas |
|  |  |  | Productive Landscapes |
|  |  |  | Productive Seascapes |
|  |  |  | Community Based Natural Resource Management |
|  |  | Mainstreaming |  |
|  |  |  | Extractive Industries (oil, gas, mining) |
|  |  |  | Forestry (Including HCVF and REDD+) |
|  |  |  | Tourism |
|  |  |  | Agriculture & agrobiodiversity |
|  |  |  | Fisheries |
|  |  |  | Infrastructure |
|  |  |  | Certification (National Standards) |
|  |  |  | Certification (International Standards) |
|  |  | Species |  |
|  |  |  | Illegal Wildlife Trade |
|  |  |  | Threatened Species |
|  |  |  | Wildlife for Sustainable Development |
|  |  |  | Crop Wild Relatives |
|  |  |  | Plant Genetic Resources |
|  |  |  | Animal Genetic Resources |
|  |  |  | Livestock Wild Relatives |
|  |  |  | Invasive Alien Species (IAS) |
|  |  | Biomes |  |
|  |  |  | Mangroves |
|  |  |  | Coral Reefs |
|  |  |  | Sea Grasses |
|  |  |  | Wetlands |
|  |  |  | Rivers |
|  |  |  | Lakes |
|  |  |  | Tropical Rain Forests |
|  |  |  | Tropical Dry Forests |
|  |  |  | Temperate Forests |
|  |  |  | Grasslands |
|  |  |  | Paramo |
|  |  |  | Desert |
|  |  | Financial and Accounting |  |
|  |  |  | Payment for Ecosystem Services |
|  |  |  | Natural Capital Assessment and Accounting |
|  |  |  | Conservation Trust Funds |
|  |  |  | Conservation Finance |
|  |  | Supplementary Protocol to the CBD |  |
|  |  |  | Biosafety |
|  |  |  | Access to Genetic Resources Benefit Sharing |
|  | Forests |  |  |
|  |  | Forest and Landscape Restoration |  |
|  |  |  | REDD/REDD+ |
|  |  | Forest |  |
|  |  |  | Amazon |
|  |  |  | Congo |
|  |  |  | Drylands |
|  | Land Degradation |  |  |
|  |  | Sustainable Land Management |  |
|  |  |  | Restoration and Rehabilitation of Degraded Lands |
|  |  |  | Ecosystem Approach |
|  |  |  | Integrated and Cross-sectoral approach |
|  |  |  | Community-Based NRM |
|  |  |  | Sustainable Livelihoods |
|  |  |  | Income Generating Activities |
|  |  |  | Sustainable Agriculture |
|  |  |  | Sustainable Pasture Management |
|  |  |  | Sustainable Forest/Woodland Management |
|  |  |  | Improved Soil and Water Management Techniques |
|  |  |  | Sustainable Fire Management |
|  |  |  | Drought Mitigation/Early Warning |
|  |  | Land Degradation Neutrality |  |
|  |  |  | Land Productivity |
|  |  |  | Land Cover and Land cover change |
|  |  |  | Carbon stocks above or below ground |
|  |  | Food Security |  |
|  | International Waters |  |  |
|  |  | Ship |  |
|  |  | Coastal |  |
|  |  | Freshwater |  |
|  |  |  | Aquifer |
|  |  |  | River Basin |
|  |  |  | Lake Basin |
|  |  | Learning |  |
|  |  | Fisheries |  |
|  |  | Persistent toxic substances |  |
|  |  | SIDS : Small Island Dev States |  |
|  |  | Targeted Research |  |
|  |  | Pollution |  |
|  |  |  | Persistent toxic substances |
|  |  |  | Plastics |
|  |  |  | Nutrient pollution from all sectors except wastewater |
|  |  |  | Nutrient pollution from Wastewater |
|  |  | Transboundary Diagnostic Analysis and Strategic Action Plan preparation |  |
|  |  | Strategic Action Plan Implementation |  |
|  |  | Areas Beyond National Jurisdiction |  |
|  |  | Large Marine Ecosystems |  |
|  |  | Private Sector |  |
|  |  | Aquaculture |  |
|  |  | Marine Protected Area |  |
|  |  | Biomes |  |
|  |  |  | Mangrove |
|  |  |  | Coral Reefs |
|  |  |  | Seagrasses |
|  |  |  | Polar Ecosystems |
|  |  |  | Constructed Wetlands |
|  | Chemicals and Waste |  |  |
|  |  | Mercury |  |
|  |  | Artisanal and Scale Gold Mining |  |
|  |  | Coal Fired Power Plants |  |
|  |  | Coal Fired Industrial Boilers |  |
|  |  | Cement |  |
|  |  | Non-Ferrous Metals Production |  |
|  |  | Ozone |  |
|  |  | Persistent Organic Pollutants |  |
|  |  | Unintentional Persistent Organic Pollutants |  |
|  |  | Sound Management of chemicals and Waste |  |
|  |  | Waste Management |  |
|  |  |  | Hazardous Waste Management |
|  |  |  | Industrial Waste |
|  |  |  | e-Waste |
|  |  | Emissions |  |
|  |  | Disposal |  |
|  |  | New Persistent Organic Pollutants |  |
|  |  | Polychlorinated Biphenyls |  |
|  |  | Plastics |  |
|  |  | Eco-Efficiency |  |
|  |  | Pesticides |  |
|  |  | DDT - Vector Management |  |
|  |  | DDT - Other |  |
|  |  | Industrial Emissions |  |
|  |  | Open Burning |  |
|  |  | Best Available Technology / Best Environmental Practices |  |
|  |  | Green Chemistry |  |
|  | Climate Change |  |  |
|  |  | Climate Change Adaptation |  |
|  |  |  | Climate Finance |
|  |  |  | Least Developed Countries |
|  |  |  | Small Island Developing States |
|  |  |  | Disaster Risk Management |
|  |  |  | Sea-level rise |
|  |  |  | Climate Resilience |
|  |  |  | Climate information |
|  |  |  | Ecosystem-based Adaptation |
|  |  |  | Adaptation Tech Transfer |
|  |  |  | National Adaptation Programme of Action |
|  |  |  | National Adaptation Plan |
|  |  |  | Mainstreaming Adaptation |
|  |  |  | Private Sector |
|  |  |  | Innovation |
|  |  |  | Complementarity |
|  |  |  | Community-based Adaptation |
|  |  |  | Livelihoods |
|  |  | Climate Change Mitigation |  |
|  |  |  | Agriculture, Forestry, and other Land Use |
|  |  |  | Energy Efficiency |
|  |  |  | Sustainable Urban Systems and Transport |
|  |  |  | Technology Transfer |
|  |  |  | Renewable Energy |
|  |  |  | Financing |
|  |  |  | Enabling Activities |
|  |  | Technology Transfer |  |
|  |  |  | Poznan Strategic Programme on Technology Transfer |
|  |  |  | Climate Technology Centre & Network (CTCN) |
|  |  |  | Endogenous technology |
|  |  |  | Technology Needs Assessment |
|  |  |  | Adaptation Tech Transfer |
|  |  | United Nations Framework on Climate Change |  |
|  |  |  | Nationally Determined Contribution |
|  |  |  | Paris Agreement |
|  |  |  | Sustainable Development Goals |
|  |  | Climate Finance (Rio Markers) |  |
|  |  |  | Climate Change Mitigation 1 |
|  |  |  | Climate Change Mitigation 2 |
|  |  |  | Climate Change Adaptation 1 |
|  |  |  | Climate Change Adaptation 2 |

Project ID number remains the same as the assigned PIF number.

When completing Table A, refer to the excerpts on GEF 6 Results Frameworks for GETF, LDCF and SCCF.

Financing type can be either investment or technical assistance.

‘The term ‘black communities’ is the English translation of the Spanish term “comunidades negras” which is widely utilized in Colombia and it will be used for simplicity throughout the text. The term ‘black communities’ in the Colombian context also include ‘Afro-descendants’ and ‘Afro-Colombians’ communities.

The aim of output 1.1.2 is to safeguard ecosystem services, cultural and biological diversity

Translation of ‘estrategias complementarias de conservación’, which include the establishment of areas that are not formal protected areas, but function as such. It may e.g. include stewardship approaches, but also modalities of area protection and management that correspond to what is internationally termed as ‘Indigenous and Community Conserved Areas’ (ICCAs). These areas are not currently under the jurisdiction of any environmental authority in Colombia.

For GEF Project Financing up to $2 million, PMC could be up to10% of the subtotal;  above $2 million, PMC could be up to 5% of the subtotal.  PMC should be charged proportionately to focal areas based on focal area project financing amount in Table D below.

For questions A.1 –A.7 in Part II, if there are no changes since PIF , no need to respond, please enter “NA” after the respective question.

For biodiversity projects, in addition to explaining the project’s consistency with the biodiversity focal area strategy, objectives 
   and programs, please also describe which Aichi Target(s) the project will directly contribute to achieving..

http://www.fao.org/capacitydevelopment/the-three-dimensions-of-the-fao-capacity-development-framework/en/20.

GEF policies encompass all managed trust funds, namely: GEFTF, LDCF, and SCCF

As a precedent, four exercises are identified for an economic assessment of ecosystem services conducted in the area of the MUCBs: Paramo of Duende and Tatamá (Tatamá-Paraguas MUCB), Dry Forest of Dagua (Farallones-Calima MUCB), Mangroves of Tumaco (Cabo Manglares- Awa MUCB), and Wetland Complex of Bajo Atrato.

The aim of output 1.1.2 is to safeguard ecosystem services, cultural and biological diversity

Area corresponding to a basin selected in the CORPONARIÑO zoning plan, it refers to the Mira river basin (65.000 ha).

Priority participatory structures will be supported within the framework of the SIRAP Pacific operational structure; this structure has platforms that correspond to 4 levels: regional, departmental, sub-regional, and local. One (1) SIRAP Pacific Regional Roundtable (General Assembly and Technical Committee); five (5) Roundtables of Departmental PA Systems  (SIDAP): Risaralda, Nariño, Cauca, Valle del Cauca, and Chocó; two (2) SIDAP Nariño Sub-regional Roundtables: Pacific and Coastal Foothills; one (1) SIDAP Cauca Sub-regional Roundtable: Pacific Roundtable; two (2) SIDAP Valle del Cauca Local Roundtables: East Pacific and West Pacific; five (5) SIDAP Chocó Sub-regional Roundtables: Pacific Coast, Atrato, Baudó, San Juan, and Darién; six (6) Local PAs Systems–SILAP of SIDAP Chocó: San José del Palmar, Acandí, Unguía, Carmen de Atrato, Nuquí, Tadó; Local conservation actions of bio-cultural diversity of Pacific region per department; one (1) Thematic Sub-system of protected marine areas: SAMP (articulated to the SIRAP Pacific and SIRAP Caribbean). In total, there are 71 delegates within these platforms (Vásquez, 2015).

One regional platform will be supported, and five departmental, sub-regional, or local platforms in the MUCBs, one prioritized per MUCB.

One prioritized platform will be supported in each MUCB. Around 140 local participation platforms are estimated among indigenous cabildos’ assemblies, communal councils’ assemblies and regional associations’ assemblies, in addition to local participation platforms of civil society organizations.

Corresponds to Cabo Manglares- Bajo Mira IMND.

For example: The local roundtable of use, occupancy, and ownership of the Munchique NNP, the co-management roundtable that will be created within the management process framework of the new Cabo Manglares IMND, the technical committees of the CVC PAs, among other spaces existing in the framework of PNN use and management agreements.

These data correspond to the addition of hectares covered by the new areas identified for MUCBs, consisting of Relictos de Caoba Juradó (63,686 ha) for Katios – Caoba MUCB, Serranía de los Paraguas (191,561 ha) in Serranía Paraguas – Tatamá MUCB; and Calle Santa Rosa (3,356 ha) in the Munchique – Río Saija MUCB.

The area of 210,193 ha refers to conservation priorities (whose use is proposed for protection and restoration for conservation) located in at least one Community Council (CC) and one Indigenous Reserve (IR) in each MUCB as follows: a) Katíos-Caoba MUCB: Cacarica River CC (41,405 ha), Salaquí River CC (14,421 ha), and Salaquí and Pavarandó IR (30,580 ha); b) Farallones-Calima MUCB: middle, lower, and coastal zone of San Juan "ACADESÁN” CC (20,276 ha), Cuenca Baja of Calima River CC (5,117 ha), and Yu Yic Kwe IR (1,467 ha); c) Cabo Manglares-Gran Familia Awá MUCB: Bajo Mira and Frontera CC (32,867 ha), El Gran Sabalo IR (8,001 ha), and La Turbia IR (16,206 ha); d) Munchique-Saija River MUCB, El Playón of Siguí River CC (17,043 ha), Lower Saija River CC (4,745 ha), and Calle Santa Rosa Saija River IR (3,356 ha); e) Tatamá-Serranía de Paraguas MUCB: middle, lower, and coastal zone of San Juan "ACADESÁN” CC (2,314 ha), and Unificado Chamí of San Juan River IR (1,395 ha).

Three groups of biodiversity products have been identified for natural ingredients: 1) natural colors: achiote, jagua; 2) fats and oils: azaí, mil pesos, noli, cocoa, coconut, chontaduro, donpedrito; and 3) Food: cocoa, coconut, borojó, azaí, chontaduro, vanilla. All these products have potential for current markets and demands by natural ingredients companies, mainly cosmetics and food.

If at CEO Endorsement, the PPG activities have not been completed and there is a balance of unspent fund, Agencies can continue to undertake the activities up to one year of project start.  No later than one year from start of project implementation, Agencies should report this table to the GEF Secretariat on the completion of PPG activities and the amount spent for the activities.  Agencies should also report closing of PPG to Trustee in its Quarterly Report.