Project Implementation Report

Project title: The Restoration Initiative (TRI) Myanmar, Reversing forest degradation and deforestation and restoring forested landscapes through local multi-stakeholder management

Programme: ARO

Project Manager: Mr. Bo Sann

Global thematic programme:  Global Forest Programme

PIR Date: April 2021

Actual Agency Approval date: 3 July 2018

Fiscal year: 2020-21

Implementation status: Under implementation

Development objective rating: Moderately satisfactory

Implementation progress rating: Unsatisfactory

Risk rating: Substantial risk

Actual implementation start date: 15 October 2018

First disbursement date: 30 September 2018

Expected mid-term review date: June 2021

Expected closing date: February 2025

Cumulative disbursement as of 28 February 2021 ($): 386,093

Expected financial closure / terminal financial report date: February 2026

Information on Progress, challenges and outcomes on project implementation activities:

Progress

Component 1: Policy Development and Integration

The Project activities have been started although there were challenges related to signing the implementing agreement with the Forest Department in Myanmar, and due to COVID-19 restrictions. Progress includes completing the project launch in March 2019 with full participation of the government of Myanmar, and ROAM assessment workshops at regional and local (Township) levels involving 361 participants and resulting in the identification of 29 priority areas for FLR covering 291,841 hectares.  The project has also supported the Myanmar Restoration and Rehabilitation Programme (MRRP), and advocating for FLR and ROAM concepts to be included as National priorities in policy dialogues. In addition, the Project has advocated for the formation of a National Working Group on Forest and Landscape Restoration. The Project is aiming to support the implementation of Chatthin Wildlife Sanctuary Management Plan that has been developed by the Friends of Wildlife (FoW) organisation. Zaloung Taung Wildlife Sanctuary has also been identified for support and a ROAM assessment will be completed for the sanctuary. The Project has made preparations for Payment for Ecosystem Services (PES) activities, including the selection of the target watershed, development of a ToR for the feasibility assessment, and developing maps for the watershed.

Component 2: Implementation of Restoration Programs and Complementary Initiatives

Restoration interventions in target FLR areas have been proposed by Forest Department at township level. The proposed interventions include restoration of commercial teak plantations, assisted natural regeneration, establishment of village-level nurseries, seedling distribution to active community forest (CF) user groups, patrolling for forest governance, support to implementation of CF management plan, etc. However, field implementation of these proposed interventions is delayed and have not yet commenced. The coup d’état on 1 February 2021 is another constraint because communities are cautious of engaging with the government in place after the coup.  The regional carbon balance workshop, previously scheduled for 25-29 May 2020, and with support from the TRI Global programme, was postponed due to the Covid-19 pandemic.  When held, this workshop will include a comprehensive training on the FAO developed carbon balance tool EX-ACT so that PMU can measure and estimate GHG emission mitigated due to project implementation. Regarding project beneficiaries to date, a total of 432 men and women have directly benefited from the project through increased knowledge of ROAM and FLR during project inception workshop, regional workshop and township level ROAM workshops.

Component 3: Institutions, Finance, and Upscaling

ROAM workshops have been completed and attended by participants from 43 national organizations. A regional ROAM assessment workshop, was completed on 22-23 May 2019 in Monywa with 80 participants attending.  The participants were from a range of different government departments including Forestry, Agriculture, Mining, Fisheries, Myanmar Timber Enterprise, and civil society organizations. Six township level ROAM workshops have also been completed in September/October 2019. A total of 296 participants attended the series of workshops, including regional and national parliamentarians, government staff from different departments (General Administration Department, Planning, Agriculture, Forestry, Irrigation, Rural Development) and representatives from NGOs, private sector and communities. For finance and upscaling, the PMU has started working on 2 proposals: Payment for Ecosystem Services project and a Green Climate Fund (GCF) Project Preparation Facility proposal in collaboration with ICRAF (World Agroforestry Centre).

Component 4: Knowledge, Partnerships, Monitoring and Assessment

The Project has produced project flyer and two posters in Myanmar and English language.  These have been used at events.  A case study on Community Forestry, Yinkhe Reserved Forest, was produced for the Global TRI year review newsletter in 2019. Based on group discussions during township ROAM workshops, a report on the identification of important NTFPs has been prepared. A cost-benefit analysis of restoration interventions has also been completed. The ROAM handbooks (20 English version and 100 Myanmar version) have been distributed to Forest Rangers at the three FD stations during the regional ROAM assessment workshop and during the fieldtrips.

Project monitoring  and reporting

The Monitoring and Knowledge Management Specialist was hired in mid 2020. The monitoring and evaluation (M&E) framework has been completed including evaluation criteria and target indicators. The 1st Project Supervision Mission was completed during 3-4 December 2020, utilising a ‘virtual’ format. In the subsequent Aide Memoire the IUCN Mission Team made crucial recommendations on project implementation to date, work planning, monitoring and evaluation, Environmental and Social Management System planning and execution, financial progress, and procurement. All PIRs and bi-annual reports have been submitted on time.

Challenges

| Issue/Challenge | Comments/Solutions |
| --- | --- |
| Military coup, On 1 February 2021, the Myanmar military overthrew the civilian government. Mass protests have been ongoing throughout the country since then. The political and operational situation in Myanmar continues to be dynamic and progressively more unstable. Increasingly forceful responses from the military government towards participants in the Civil Disobedience Movement (CDM). | - The coup has completely disrupted planned activities. - More than 3000 staff from Forest Department (FD) have joined the CDM and many other FD staff are not working. Only the Director General and some of the higher officials are on duty at the FD. - A Risk Management/Contingency Plan has been developed by PMU covering the period from March to August 2021. - Partnership meeting between PMU, MERN and TNC was held on 9 March to discuss the coup and implications on the TRI Project. - The PMU is developing options to restructure the execution of the project to suit the current context in Myanmar. |
| Implementing Agreement (IA) between IUCN (GEF Agency) and Forest Department (FD) was significantly delayed. This has resulted in delays to project execution. Implementation of FLR activities are dependent on being timed with the ideal season for planting and delays in completing the agreement with the FD has subsequently now delayed the beginning of most of these activities to 2022. | - The IA was signed on the 4th of February 2021. - After the military coup, communication with FD has been difficult to maintain. - The National Project Director (NPD) from the FD has. The former NPD, Mr. Soe Myint Oo, was retired and replaced by Mr. U Pe Chit, as Director, Watershed Management Division and current NPD for the project. - PMU requested (17 March) FD to organize virtual meetings with FD at district and township levels to discuss possible FLR implementation in 2021. |
| COVID 19 has continued to delay execution. | - After a peak in cases between September 2020 – January 2021 the number of new cases has stablished in Myanmar to a maximum of around two dozen new cases reported each day. However, it is noteworthy that many health workers are participating the CDM and there are limited efforts to currently manage the pandemic response in the country, so actual number of cases may be much higher due to a lack of testing. - The PMU continues to monitor the situation. |
| Execution not synchronized. Execution of some project activities started in early 2019 and led by IUCN at the request of the FD. However the agreement with the FD was not finalized till February 2021. This has resulted in activities being not well synchronized. The delay in completing this agreement has resulted in the drawdown of funds allocated to key project personnel. This may result in budget for PMU personnel being spent before all project activities have been completed. | - A meeting was held between the PMU and FD on the 28 January 2021 to discuss overall execution. The PMU presented a revised workplan, revised budget and staffing plan for the remining time of the TRI Myanmar Project. The revised workplan and budget plan will be discussed in 1st meeting of the Project Steering Committee, currently postponed due the coup. |
| The location of the PMU office has not been resolved. The PMU continues to work out of the IUCN country office in Nay Pyi Taw. As per the project document and previous discussion the PMU office was to be location Katha Township. The FD has proposed the office location be moved to Kawlin Township and to construct a new building in the Kawlin FD staff residential compound. It is critical that the PMU establish and office in the project target area as soon as possible. | - Currently not possible to establish the PMU office outside Nay Pyi Taw due to the security situation related to the coup. Several PMU staff have moved to work from home for security reasons. - The office location was discussed in meetings between PMU and FD. It was agreed that FD should send a request letter to IUCN (GEF Agency) outlining the rationale for changing the location of the PMU office from Katha to Kawlin township, and what, if any, are implications for operations to support project execution and the budget. - The PMU office location should be approved in at the 1st meeting of the PSC, currently postponed due the coup. |

Information on Progress, challenges and outcomes on stakeholder engagement (based on the description of the Stakeholder engagement plan included at CEO Endorsement/Approval):

Stakeholders at different levels have been engaged in all project activities to date.  For example, about 432 participants from government, civil society, academia, and the private sector had attended to the national, regional and township level ROAM assessment workshops. In these regional and local workshops, 29 FLR areas had been demarcated on the map with the active participation of the participants so that restoration opportunities could have been identified. During several field visits to the project sites, PMU had communicated with different stakeholders (government staff, local community, private sector, explaining and consulting about the prospects of project implementation. In January 2021, PMU has drafted the grievance mechanism related to implementation of project activities on the ground.

Information on Progress on gender-responsive measures as documented at CEO Endorsement/Approval in the gender action plan or equivalent:

| Issue/Challenge | Comments/Solutions |
| --- | --- |
| Because of the delay in implementation of the project the gender equality and gender action plan have not yet been drafted. This work is part of the ToR for MERN who will implement the livelihood support to the TRI Myanmar Project | - As part of the services provided to the TRI Myanmar Project, MERN should ensure the equal participation of women in all activities. MERN will also be responsible for conduction a gender analysis. |

Knowledge activities / products (when applicable), as outlined in knowledge management approved at CEO Endorsement / Approval:

The regional and local ROAM workshops included sessions explaining FLR and ROAM concepts and advocating for FLR and ROAM concepts to be included as National priorities in policy dialogues.  All participants responded positively and appreciated the value of learning more about FLR and ROAM. During the workshop evaluations 85% of respondents indicated that their knowledge had increased and what they learnt would be useful in their day to day job. Prior to the launch of the project, fliers and posters in both English and Burmese were developed to raise awareness by describing the TRI Myanmar Project and ROAM process. These knowledge materials have been used during the regional and local ROAM workshops. The project developed detailed maps of the 6 target Townships using satellite imagery and GIS. These maps were then used during the ROAM workshops to help determine and delineate target FLR areas. Based on discussions during the workshops and farmer interviews during field visits, the Project has published report on cost-benefit analysis of six restoration interventions and has done report on identification of important NTFP for local livelihoods in Sagaing region. Additionally, 11 participants from FD, TNC, IUCN and UFES (University of Forestry and Environmental Science) attended three international TRI exchanges events held in Rome, China, Kenya. The TRI partner, TNC has advocated FD for the formation of a National Working Group on Forest and Landscape Restoration for providing strategic guidance on FLR implementation.

| Product/Activity | Comments/Solutions |
| --- | --- |
| Cost-Benefit Analysis of Forest Restoration Interventions in Sagaing Region | - Published 16 March 2021. - https://www.iucn.org/news/myanmar/202103/cost-benefit-analysis-forest-restoration-interventions-sagaing-region-myanmar |
| EX-ACT toolkit webinar | - PMU participated in the launch of the new version of the FAO carbon balance tool, EX-ACT on the 12 January 2021. |
| Forest Resource Assessment for Sagaing Region | - PMU produced the forest resource assessment for the whole of Sagaing Region in January 2021. |
| Case study for TRI Year in Review | - PMU prepared a case study for the Global TRI in Year Review 2020. |
| Landscape Finance Workshop | - PMU participated in the FAO organized Landscape Finance workshop for 3 days, 3-5 March. |
| Mekong-US Partnership Dialogue | - On 19 to 26 March 2021, the virtual dialogue was organized by the Stimson Center and the International Union for the Conservation of Nature. During the Dialogue, M&E and Knowledge Management Specialist participated and presented the cost-benefit analysis of forest restoration interventions in Sagaing. |
| Township FLR Plans and Strategies preparations | - PMU have prepared maps that will be used in each of the Township FLR Plan and Strategy. The following maps have been produced so far: - Overview map of each Township with the location of each selected FLR area (6 maps). - Township Ecosystem Maps (6 maps) - Township, Primary Forest Map (6) - Map over each of the 29 FLR areas (29 maps) |

ESMS implementation update:

Restoration activities have not yet started and therefore ESMS have not been implemented. The overall impacts being expected to be largely positive as improved ecosystem services are expected to lead to improved livelihoods. The project has been classified as a moderate risk project. ROAM planning process have been implemented and reflects a strong congruence with the main ESMS elements. A significant part of the analytical work carried out during ROAM ensure meeting substantial and procedural ESMS requirements.

| Issue/Challenge | Comments/Solutions |
| --- | --- |
| ESMS training for project stakeholders have been planned for April 2021. This training will be organized as a virtual event. | - Training will be organized by IUCN HQ. Participants from FD, TNC, MERN and PMU will attend. - Due to the coup, this activity will be postponed. - The PMU has drafted an ESMS assessment form for project implementation. The form will be discussed, updated and applied after consultations with partners such as TNC, MERN, FD. |

Budget showing advancement (USD) to 28 February 2021:

| Component | Budget | Expenditure |  |  |  | Total expenditure | Balance |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | 2018 | 2019 | 2020 | 2021 |  |  |
| Component 1 - Policy Development and Integration | 560,289 | 7,962 | 113,013 | 45,139 | 2,498 | 168,612 | 391,678 |
| Component 2 - Implementation of Restoration Programs and Complimentary Initiatives | 1,186,007 | - | 43,344 | 49,644 | 10,432 | 103,420 | 1,082,587 |
| Component 3 - Institutions, Finance and Upscaling | 419,699 | - | - | 38,301 | 5,498 | 43,799 | 375,899 |
| Component 4 - Knowledge, Partnerships, Monitoring and Assessment | 352,643 | - | 19,480 | 17,753 | 6,258 | 43,491 | 309,151 |
| Project Management Costs | 133,655 | - | 7,844 | 17,107 | 1,819 | 26,770 | 106,885 |
| Total | 2,652,293 | 7,962 | 183,680 | 67,944 | 26,507 | 386,093 | 2,266,200 |

Highly satisfactory, satisfactory, unsatisfactory, not rated, unknown, marginally satisfactory, marginally unsatisfactory, highly unsatisfactory.

High risk, substantial, moderate risk, low risk