## Table of Contents
FAO-GEF Project Implementation Report
2025 – Revised Template
Period covered: 1 July 2024 to 30 June 2025
Table of Contents
1. BASIC PROJECT DATA
2. PROGRESS TOWARDS ACHIEVING PROJECT OBJECTIVE(S) (DEVELOPMENT OBJECTIVE)
3. IMPLEMENTATION PROGRESS (IP)
4. SUMMARY ON PROGRESS AND CHALLENGES
5.ENVIRONMENTAL AND SOCIAL SAFEGUARDS (ESS):RISKS FROM THE PROJECT
6. RISKS TO THE PROJECT
7. FOLLOW-UP ON MID-TERM REVIEW OR SUPERVISION MISSION
8. MINOR PROJECT AMENDMENTS
9. STAKEHOLDERS' ENGAGEMENT
10. GENDER MAINSTREAMING
11. KNOWLEDGE MANAGEMENT ACTIVITIES
12. INDIGENOUS PEOPLES AND LOCAL COMMUNITIES INVOLVEMENT
13. CO-FINANCING TABLE
14. GEO LOCATION INFORMATION
Annex. Monitoring Area-based GEF Core Indicator Commitments and Progress with FERM
IMPORTANT DISCLAIMER:
The final version of this PIR will be submitted to the GEF Secretariat.
The report will then be publicly available on the GEF website (click here).
Sensitive information should be submitted in Annex to be uploaded separately.
In such cases, please contact faogef-pir-support@fao.org for guidance.

## 1. Basic project data
1. Basic Project Data
General Information
Region: | Near East and North Africa (RNE)
Country(ies): | Algeria
Project Title: | Integrated management of forests and biodiversity for sustainable development in the Biban mountain range
FAO Project Symbol: | GCP/ALG/002/GFF
GEF ID: | 10170
Type of Trust Fund(s): | GFF
GEF Focal Area(s): | Multi Focal Area (Biodiversity, Land Degradation)
Project Executing Partners: | The National Observatory for the Environment and Sustainable Development (ONEDD) of the Ministry of Environment and Quality of Life (MEQL)
Initial project duration (years): | 4 years
Project Dates
GEF CEO Endorsement Date: | 2021-12-08
Actual Agency Approval Date | 2021-06-18
Project Implementation Start Date/EOD: | 2022-08-01
First Disbursement Date | 2025-02-28
Planned Project End Date/NTE1: | 2026-07-31
Revised project implementation End date (if approved)2: | 2028-08-31
Actual Completion Date: | N/A
Expected Financial Closure Date: | 2029-08-31
Funding
GEF Grant Amount (USD): | 3297260
Total GEF grant delivery (as of June 30, 2025 (USD): | 492643.1
Total Co-financing amount (USD)3: | 29220460
Total estimated co-financing materialized as of June 30, 2025: | 0
M & E Milestones
Date of Last Project Steering Committee (PSC) Meeting: | May 28th 2025
Expected Mid-term Review date5: | 2025-11-16
Actual Mid-term review date (if already completed): | N/A
Expected Terminal Evaluation Date6: | 2028-02-28
Overall ratings
Overall rating of progress towards achieving objectives/outcomes (cumulative): | Highly Unsatisfactory (HU)
Overall implementation progess rating: | Highly Unsatisfactory (HU)
Overall risk rating: | Moderate
Status
Implementation Status (1st PIR, 2nd PIR, etc. Final PIR): | 1st PIR
1 Date that was originally foreseen at the project’s operationalization and indicated in FPMIS. 2 If NTE extension has been requested and approved by the FAO-GEF Coordination Unit. 3 This is the total amount of co-financing as included in the CEO Document/Project Document. 4 Please refer to the Section 13 of this report where updated co-financing estimates are requested and indicate the total co-financing amount materialized. 5 The Mid-Term Review (MTR) should take place after the 2nd PIR, around half-point between EOD and NTE. The MTR report in English should be submitted to the GEF Secretariat within 4 years of the CEO Endorsement date. 6 The Terminal Evaluation date should be discussed with OED 6 months before the project’s NTE date.
Project Contacts
Contact | Name, Title, Division/Institution |  | E-mail
Project Coordinator (PC) | Karim Arab, DG ONEDD |  | arabkarim3@gmail.com
Budget Holder (BH) | Irina Kouplevatskaya - Buttoud |  | Irina.Buttoud@fao.org
GEF Operational Focal Point (GEF OFP) | Mr. Karim Baba |  | karimbaba1964@gmail.com
Lead Technical Officer (LTO) | Fidaa Haddad (FAORNE) |  | Fidaa.Haddad@fao.org
GEF Technical Officer (GTO) | Anika Seggel |  | Anika.Seggel@fao.org
Key Project Management Unit Personnel
Please indicate the composition of the PMU as per the Terms of Reference in the ProDoc. If any new position was establised during the project implementation, please insert it accordingly.
Position planned (as per ProDoc) | Position filled (Yes/No) | Start date, Name, Contact |  | Comments
National Project Coordinator | No |  |  | Second call for applications for the three positions was launched on July 29, the first being unsuccessful. At the same time, the FAO is revising the salary scale, taking into account that the proposed honorarium in the document does not correspond to current UN salary scale, and does not attract suitable candidates.
Financial and Administrative Assistant | No
Field Assistant | No

## _Calc (hidden)
Rating text | Score
Highly Unsatisfactory (HU) | 1
Unsatisfactory (U) | 2
Moderately Unsatisfactory (MU) | 3
Moderately Satisfactory (MS) | 4
Satisfactory (S) | 5
Highly Satisfactory (HS) | 6
Unknown | 0
Not Rated | 0
for DevScore
|  | Person | PM/Coord | Budget Holder | LTO | GEF OFP | GTO
|  | Weight % | 20 | 25 | 25 | 0 | 30
For ImpScore
|  | Person | PM/Coord | LTO | GEF OFP | GTO
|  | Weight % | 25 | 35 | 0 | 40
Once you've filled in 2. Progress towards outcomes & 3. Implementation Progress
Please double click and press enter on Cells D20 and D21 |  | 1
1

## Countries (hidden)
Select Country
Afghanistan
Åland Islands
Albania
Algeria
American Samoa
Andorra
Angola
Anguilla
Antarctica
Antigua and Barbuda
Argentina
Armenia
Aruba
Australia
Austria
Azerbaijan
Bahamas
Bahrain
Bangladesh
Barbados
Belarus
Belgium
Belize
Benin
Bermuda
Bhutan
Bolivia (Plurinational State of)
Bonaire, Sint Eustatius and Saba
Bosnia and Herzegovina
Botswana
Bouvet Island
Brazil
British Indian Ocean Territory
British Virgin Islands
Brunei Darussalam
Bulgaria
Burkina Faso
Burundi
Cabo Verde
Cambodia
Cameroon
Canada
Cayman Islands
Central African Republic
Chad
Chile
China
China, Hong Kong Special Administrative Region
China, Macao Special Administrative Region
Christmas Island
Cocos (Keeling) Islands
Colombia
Comoros
Congo
Cook Islands
Costa Rica
Côte d’Ivoire
Croatia
Cuba
Curaçao
Cyprus
Czechia
Democratic People's Republic of Korea
Democratic Republic of the Congo
Denmark
Djibouti
Dominica
Dominican Republic
Ecuador
Egypt
El Salvador
Equatorial Guinea
Eritrea
Estonia
Eswatini
Ethiopia
Falkland Islands (Malvinas)
Faroe Islands
Fiji
Finland
France
French Guiana
French Polynesia
French Southern Territories
Gabon
Gambia
Georgia
Germany
Ghana
Gibraltar
Greece
Greenland
Grenada
Guadeloupe
Guam
Guatemala
Guernsey
Guinea
Guinea-Bissau
Guyana
Haiti
Heard Island and McDonald Islands
Holy See
Honduras
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Isle of Man
Israel
Italy
Jamaica
Japan
Jersey
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People's Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Martinique
Mauritania
Mauritius
Mayotte
Mexico
Micronesia (Federated States of)
Monaco
Mongolia
Montenegro
Montserrat
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands (Kingdom of the)
New Caledonia
New Zealand
Nicaragua
Niger
Nigeria
Niue
Norfolk Island
North Macedonia
Northern Mariana Islands
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Pitcairn
Poland
Portugal
Puerto Rico
Qatar
Republic of Korea
Republic of Moldova
Réunion
Romania
Russian Federation
Rwanda
Saint Barthélemy
Saint Helena
Saint Kitts and Nevis
Saint Lucia
Saint Martin (French Part)
Saint Pierre and Miquelon
Saint Vincent and the Grenadines
Sint Eustatius and Saba
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Sint Maarten (Dutch part)
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
South Georgia and the South Sandwich Islands
South Sudan
Spain
Sri Lanka
State of Palestine
Sudan
Suriname
Svalbard and Jan Mayen Islands
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
Timor-Leste
Togo
Tokelau
Tonga
Trinidad and Tobago
Tunisia
Türkiye
Turkmenistan
Turks and Caicos Islands
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States Minor Outlying Islands
United States of America
United States Virgin Islands
Uruguay
Uzbekistan
Vanuatu
Venezuela (Bolivarian Republic of)
Viet Nam
Wallis and Futuna Islands
Western Sahara
Yemen
Zambia
Zimbabwe

## TypeofTrustFund (hidden)
Type of Trust Fund
Capacity-building Initiative for Transparency (CBIT)
Global Biodiversity Framework Fund (GBFF)
Global Environment Facility Trust Fund (GFF)
Least Developed Countries Fund (LDCF)
Special Climate Change Fund (SCCF)
Small Grants Program (SGP)

## FocalArea (hidden)
Focal Area
Multi Focal Area
Biodiversity
Chemicals and Waste
Chemicals/PoPs
Climate Change
Climate Change Adaptation
Climate Change Mitigation
International Waters
Land Degradation

## 2. Progress towards outcomes
2. Progress towards Achieving Project Objective(s) (Development objective)
(All inputs in this section should be cumulative from project start, not annual)
Please indicate the project’s main progress towards achieving its objective(s) and the cumulative level of achievement of each outcome since the start of project implementation.
Project or Development Objective | Outcomes | Outcome indicators | Baseline | Mid-term Target | End-of-project Target | Cumulative progress level at 30 June 2025 | % of cumulative progress | Progress rating
Component 1: Biodiversity and land management planning, policy strengthening and financial capacity building for Sustainable Forest and Land Management in the Biban mountain range | Outcome 1 | Number of government staff disaggregated by gender from the central to the local level trained on integrated land-use planning, inventories and biodiversity assessments, and value assessments Number of integrated PCDs that address biodiversity and land degradation concerns developed and implementation initiated Number of Protected Areas under development |  |  | 150 government staff including 50% of women Two integrated PCDs that address biodiversity and land degradation concerns One Protected Area under development | No progress | 0% | Activities pending the establishment of the project management unit,
| Outcome 1.1: Biodiversity conservation and sustainable land management are integrated into communal development plans and budgeted for in Ighil Ali and Teniet En Nasr communes | Indicator 1: Number of government staff disaggregated by gender from the central to the local level trained on integrated land-use planning, inventories and biodiversity assessments, and value assessments Number of integrated PCDs that address biodiversity and land degradation concerns developed and implementation initiated Number of Protected Areas under development |  |  | Target 1: 150 government staff including 50 percent of women | No progress | 0% | Activities pending the establishment of the project management unit,
|  | Indicator 2: Number of integrated PCDs that address biodiversity and land degradation concerns developed and implementation initiated |  |  | Target 2: Two integrated PCDs that address biodiversity and land degradation concerns | No progress | 0% | Activities pending the establishment of the project management unit,
|  | Indicator 3: Number of Protected Areas under development |  |  | Target 3: One Protected Area under development | No progress | 0% | Activities pending the establishment of the project management unit,
Component 2: Adoption of sustainable sources of income that contribute to conserving biodiversity and reversing land degradation by local resource users in the targeted communes.mountain range | Outcome 1
| Outcome 2.1: Nature-based sustainable businesses in Ighil Ali and Teniet En Nasr communes are developed and are directly contributing to the conservation of biodiversity, forest ecosystems and land | Indicator: Number of sustainable MSMEs generating profit established disaggregated by women and youth |  |  | Target: at least 20 MSMEs established in each commune | No progress | 0% | Activities pending the establishment of the project management unit,
Component 3 : Outscaling and upscaling of successful interventions across the Biban mountain range resource users in the targeted communes.mountain range | Outcome 3.1 : Sustainable land management and biodiversity conservation integrated in development planning across the Biban mountain range | Indicator 1: Number of policy document drafted, policy recommendations developed to integrate biodiversity and ecosystems’ considerations |  |  | Target 1: At least three policy document drafted or policy recommendations developed | No progress | 0% | Activities pending the establishment of the project management unit,
|  | Indicator 2: Additional private and public resources mobilized for the upscaling of sustainable land management and biodiversity conservation practices in other communes of the Biban mountain range |  |  |  | No progress | 0%
| Outcome 3.2: Project monitored, results captured and lessons learned widely disseminated. | Indicator: Number of sustainable MSMEs generating profit established disaggregated by women and youth |  |  | Target: at least 20 MSMEs established in each commune | No progress | 0%
Average Cumulative progress toward outcomes (%) | Time elapsed since project start/EOD vs Planned Project End Date | % of delivery
0% | 77.74% | 14.94%
Development Objective (DO) Ratings, and Overall Assessment
Please note that the overall DO ratings should be substantiated by evidence and progress reported above. The ratings and comments should reflect the overall progress of results since project start
| FY2025 Development Objective rating¹ | Project Manager/ Coordinator | Budget Holder | Lead Technical Officer13 | GEF Operational Focal Point | GEF Technical Officer (GTO)
|  | Unsatisfactory (U) | Highly Unsatisfactory (HU) | Unsatisfactory (U) |  | Highly Unsatisfactory (HU)
| Comments/reasons¹² justifying the ratings for FY2025 and any changes (positive or negative) in the ratings since the previous reporting period | One of the main challenges has been the recruitment of the Project Management Unit (PMU). Salary levels applied in Algeria in 2024–2025 are significantly higher than those foreseen in the project document at the design stage. Consequently, the first round of vacancy announcements did not attract suitable candidates, leading to the launch of a second call. While a positive milestone was the official launch of the project in May, it unfortunately took place without an established PMU. | For the time being the biggest progress is the operationalisation of the OPIM partner and formal launching of the project in presence of the Minister of Environement. Due to institutional changes the launching of the project was delayed. Recruitment of the project management unit is another challenge: salary rates applied in Algeria in 2024-2025 are considerably higher than rates foreseen in the project document during the project design stage. As a result the first round of vacacies annoucement was not successful. A seoncd VA was launched. | The main challenge has been operationalising OPIM and building capacity to review, discuss, and implement project components on the ground. While the project was officially launched in May, delays in PMU recruitment limited early implementation. OPIM’s engagement remains critical for effective on-the-ground project execution and capacity strengthening. |  | A budget revision is pending, which apparently prevents the OP from further implementing. This must urgently be adressed by OP and the CO.
Measures to address MS, MU, U and HU ratings on Section 2 above
Outcome |  | Action(s) to be taken |  | By whom? |  | By When?
Outcome 1.1 |  | Salary scale review and budget revision Establishment of the management unit Accelerated consumption of the first tranche transferred to ONEDD Request for the second tranche Finalization of the terms of reference for the various expert assessments |  | FAO/ONEDD |  | 2025-09-01
Outcome 2.1 |  | Idem |  | FAO/ONEDD |  | 2025-09-01
Outcome 2.2 |  | Idem |  | FAO/ONEDD |  | 2025-09-01
Outcome3.1 |  | Idem |  | FAO/ONEDD |  | 2025-10-01
Ouctome 3.2 |  | Idem |  | FAO/ONEDD |  | 2025-09-01
7 Some indicators may not identify mid-term targets at the design stage (refer to approved results framework) therefore this column should only be filled when relevant. 8 Use GEF Secretariat required six-point scale system: Highly Satisfactory (HS), Satisfactory (S), Moderately Satisfactory (MS), Moderately Unsatisfactory (MU), Unsatisfactory (U), and Highly Unsatisfactory (HU).

## 3. Implementation Progress
3. Implementation Progress (IP)
(Please indicate progress achieved during this FY as per the Implementation Plan/Annual Workplan)
Outcomes and outputs | Indicators (as per the logical framework) | Main achievements in the last 12 months (please DO NOT repeat results reported in previous year PIR) |  |  | Describe any variance 9 in delivering outputs
Outcome 1.
Output 1.1 |  | The ToR of the project management unit have been adapted and agreed with the OPA, a first VA issued. All candidates desisted due to the unappealling rate. A second VA is currently open. Meanwhile a reevaluation of the scale is being made.
Output 1.2 |  | None
Output 1.3 |  | None
Output 1.4 |  | None
Output 1.5 |  | None
Output 1.6 |  | None
None
Output 2.1 |  | None
Output 2.2 |  | None
Output 2.3 |  | None
Output 2.4 |  | None
Output 2.5 |  | None
Output 2.6 |  | None
None
Output 3.1 |  | None
Output 3.2 |  | None
Output 3.3 |  | None
Output 3.4 |  | None
Output 3.5 |  | None
Output 3.6 |  | None
Implementation Progress (IP) , and Overall Assessment
Please note that the overall IP ratings should be substantiated by evidence and progress reported above. The ratings and comments shoud reflect the overall progress of results during the fiscal year (July 1 2024, to June 30, 2025)
| Project Manager/ Coordinator | Lead Technical Officer | Budget Holder | GEF Operational Focal Point (OFP) | GEF Technical Officer (GTO)
FY2025 Implementation Objective rating10 | Unsatisfactory (U) | Unsatisfactory (U) | Highly Unsatisfactory (HU) |  | Highly Satisfactory (HS)
Comments/reasons justifying the ratings for FY2025 and any changes (positive or negative) in the ratings since the previous reporting period | One of the main challenges has been the recruitment of the Project Management Unit (PMU). Salary levels applied in Algeria in 2024–2025 are significantly higher than those foreseen in the project document at the design stage. Consequently, the first round of vacancy announcements did not attract suitable candidates, leading to the launch of a second call. While a positive milestone was the official launch of the project in May, it unfortunately took place without an established PMU. | The main challenge has been operationalising OPIM and building capacity to review, discuss, and implement project components on the ground. While the project was officially launched in May, delays in PMU recruitment limited early implementation. OPIM’s engagement remains critical for effective on-the-ground project execution and capacity strengthening. | For the time being the biggest progress is the operationalisation of the OPIM partner and formal launching of the project in presence of the Minister of Environement. Due to institutional changes the launching of the project was delayed. Recruitment of the project management unit is another challenge: salary rates applied in Algeria in 2024-2025 are considerably higher than rates foreseen in the project document during the project design stage. As a result the first round of vacacies annoucement was not successful. A seoncd VA was launched. | Comments | A budget revision is pending and must urgently be adressed by the CO and OP, to ensure smooth implemenattion during next reporting cycle.
9 Variance refers to the difference between the expected and actual progress at the time of reporting. 10 Implementation Progress Rating – A rating of the extent to which the implementation of a project’s components and activities is in compliance with the projects approved implementation plan.

## 4. Summary_Progress & Challenge
4. Summary on progress and challenges
Please provide a summary paragraph on project implementation progress consistent with the information reported in section 2 and 3 of the PIR (Max 400 words) (This section will be uploaded to the GEF portal)
1) The OPA document as proposed by the FAO required the clarification of many operationalization-related questions hence a delay of more than a year, during which the FAO and the Government were engaged in an active concertation process to reach an agreement and move towards implementation. 2) The signing ceremony of the OPA document in the presence of the Minister of the Environment and Renewable Energies took place on October 24th, 2024. At this event, the Minister reaffirmed the strong interest of the Government for this project, and the members of the steering committee took part and each presented a communication. 3) The ONEDD established a comission specific for this project, including the directors of the diverse departments, very aware of the project.
Please provide a summary paragraph on challenges of project implementation consistent with the information reported in section 2 and 3 of the PIR (Max 400 words) (This section will be uploaded to the GEF portal)
The project was delayed in its start due to the formulation of the OPA until to reach a form acceptable and its validation. - With the OPA document having been signed, further delays have occurred due to a ministerial reshuffle and the subsquent changes . - The proposed salary rates for the Management Unit falls short of the candidates' and the government's expectations, especially taking in consideration the gap with international consultancies. - A second call for applications has been launched and the salary scale has been revised upwards to enable the management unit to be set
Implementation of Exit Strategy
Has the project developed an Exit Strategy? If yes, please describe the progress to implement it. | Yes: - Support mission from the FEM division in February and working session with project managers at ONEDD in the presence of the FAO Representation, - Several working sessions organized by the FAO Representation and ONEDD in the presence of the Ministry of the Environment and the Ministry of Foreign Affairs. This resulted in the establishment of a task force to support the management unit (once installed) and the coordination of the project with ONEDD. - Second call for applications to constitute the management unit, with integration of the entrepreneurial card (which will fit better the consultant status) and upward revision of the salary scale
How is the project enhancing institutional capacities to foster country ownership for more durable / sustained results? | Several working meetings to present and facilitate the implementation of project activities Continued support from the FAO team in project implementation, including fund transfer requests, recruitment, procurment, communication, and organization of the launch workshop

## 5. ESS Risk
5. Environmental and Social Safeguards (ESS): risks from the project
Initial ESS Risk Classification (at CEO Endorsement/Approval Stage) | Moderate
New environmental and social risks. | one
Progress made towards implementing the Enivronmental and Social Management Plan (ESMP) (only for Moderate and High Risk Projects) | On hold
Grievance Redress Mechanism (GRM) | Will be put in place at the project effective launch.

## 6. Risks to the Project
6. Risks to the Project
The following table summarizes risks identified in the Project Document and reflects also any new risks identified during the project implementation.
| Type of risk |  | Risk rating11 | Identified in the ProDoc Y/N | Description of Risk | Mitigation measure implemented
1 | Political |  | High | Yes | Security issues undermine efforts to develop sustainable activities (notably ecotourism). | Tourism is the main economic activities supported by the project that may be affected by insecurity. If the security situation deteriorates, over the short-medium term the emphasis will be placed on other economic activities that are less affected by insecurity. However, this is a low risk because security has improved greatly in recent years and the government is committed to maintaining security.
2 | Institutional |  | Moderate | Yes | Decreased project ownership and support from governmental agencies | ME and other key ministries, and Wilaya and Communes government agencies are currently very supportive of the project. To maintain this support, they will continue to be fully involved in the project preparation and in the project implementation and management. The project design takes into consideration the need to achieve results in the short-term in order to demonstrate the relevance of the project objectives, results, and activities to local and national governmental agencies. The alignment of the project with national strategies and policies is also a strong warrant of government commitment in the project.
3 | Environmental |  | Moderate | Yes | Climate change may lead to increased threats to forest, through fire, pests, diseases and changing climatic conditions (temperature, precipitation). | Current and future climate conditions will be taken into account when designing the on-the-ground interventions as it is a condition for the sustainability of the project inputs. As an example of this integration of climate resilience in the project, a key selection criteria for the species to be promoted by the project will be their resilience to current and future climate scenarios based on the latest information available.
4 | Environmental |  | Moderate | Yes | Fires occur in the intervention sites and hinder the success of the SLM and SFM interventions | The fire risk will be systematically assessed as part of the selection process for the SLM, SFM and Value Chains strengthening interventions, to exclude interventions with high risks where efficient mitigation measures cannot be identified
5 | Social |  | Moderate |  | Low involvement and participation of local institutions in planning and monitoring mechanisms. | Local authorities such as the Walis and their advisors, the APCs, the DGF, Social Development Agencies among others have provided continuous support during the PPG phase to organise field visits and consultations, and provide required information for the project design. They also participated actively to the two workshops organised. Their engagement in the project will be maintained by keeping them informed on the progress of the project’s validation process until the start of the implementation, and supporting multi-stakeholder and participatory processes for the development and coordination of project activities. Local authorities will be strongly involved in every step of the project and their capacity will be built. The anchoring of the project interventions on existing local development planning processes through the PCDs will further secure their involvement. Finally, because of the project alignment with the national policy framework, the project interventions fall under the mandate of local authorities in each relevant sector. This should strongly contribute to the maintenance of the commitment throughout the project.
6 | Environmental |  | Moderate | Yes | Overexploitation of NTFPs as a result of Value Chains strengthening interventions | NTFPs’ Value Chains development will be supported by the inventories and assessments that will inform sustainable harvesting rates. Thereafter, harvesting permits will be defined and allocated on demand. The capacity of DGF in monitoring permits will be increased. Involvement of local populations in monitoring will also be increased. The certification systems to be implemented as part of Value Chain strengthening will include environmental certifications and will increase the financial value of the products which is expected to further encourage the compliance to harvesting rates. The monitoring interventions linked to these certification schemes will further encourage sustainable harvesting rates to be followed. Awareness-raising interventions will also be implemented to prevent environmental degradation.
7 | Economic |  | Moderate | Yes | Agricultural and urban encroachment as a result of increased population size due to the creation of income opportunities | The integrated PCDs to be developed in a participatory manner under the project will clearly identify the different land-use zones and development zones for each land-use category. Local authorities’ capacity to monitor these plans and local populations’ involvement in monitoring will be enhanced. Increased economic value attributed to natural ecosystems are a result of the assessments undertaken as part of Component 1 and corresponding knowledge-sharing and awareness-raising interventions will further encourage environmental protection.
Project overall risk rating (Low, Moderate, Substantial or High):
FY2024 rating | FY2025 rating | Comments/reason for the rating for FY2025 and any changes (positive or negative) in the rating since the previous reporting period
Moderate | Moderate | The ESM Unit has reviewed the project activities and reclassified the project to moderate-risk. The ESM Unit recommends to prepare an Environmental and Social Management Plan (ESMP), send it for clearance once ready, and upload it under “Documentation” in FPMIS.
11 Risk ratings means a rating of the overall risk of factors internal or external to the project which may affect implementation or prospects for achieving project objectives. Risk of projects should be rated on the following scale: Low, Moderate, Substantial or High.

## 7. Follow-up on Mid-term review
7. Follow-up on Mid-term review or supervision mission
If the project had an MTR or a supervision mission in 2024, please report on how the recommendations were implemented during this fiscal year as indicated in the Management Response or in the supervision mission report.
MTR or supervision mission recommendations | Measures implemented during this Fiscal Year
Recommendation 1:
Recommendation 2:
Recommendation 3:
Recommendation …
Recommendation…

## 8. Minor project amendments
8. Minor project amendments
Minor amendments are changes to the design or implementation that do not have significant impact on the project objectives or scope, or an increase of the GEF project financing up to 5% as described in Annex 9 of the GEF Project and Program Cycle Policy Guidelines 12. Please describe any minor changes that the project has made under the relevant category or categories and provide supporting documents as an annex to this report if available. (This section will be uploaded to the GEF Portal)
Category of change | Provide a description of the change | Indicate the timing of the change | Approved by
Results framework | No
Components and cost | No
Institutional and implementation arrangements | No
Financial management | No
Implementation schedule | No
Executing Entity | No
Executing Entity Category | No
Minor project objective change | No
Safeguards | No
Risk analysis | No
Increase of GEF project financing up to 5% | No
Co-financing | No
Location of project activity | No
Other minor project amendment (define) | No
12 GEF Council meeting documents, guidelines, project and program cycle policy 2020 update

## 9. Stakeholders' Engagement
9. Stakeholders' Engagement
Please report on progress, challeges, and outcomes on stakeholder engagement (based on the description of the Stakeholder Engagement Plan) included at CEO Endorsement/Approval during this reporting period. (This section will be uploaded to the GEF Portal)
Profile | Stakeholder name | Type of partnership | Progress, results & Challenges on Stakeholder's Engagement
None

## 10. Gender Mainstreaming
10. Gender Mainstreaming
Information on Progress on Gender-responsive measures as documented at CEO Endorsement/Approval in the gender action plan or equivalent (when applicable) during this reporting period. (This section will be uploaded to the GEF Portal)
Category | Yes/No | Briefly describe progress and results achieved during this reporting period.
a. Closing gender gaps in access to and control overal natural resources |  | None
b. Improving women's participation and decision making |  | None
c. generating socio-economic benefits or services for women |  | None
Any other good practices on gender |  | None

## 11. Knowledge Management
11. Knowledge and Learning Activities
Knowledge activities/products (when applicable), as outlined in Knowledge Management (and Learning) Approach approved at CEO Endorsement/Approval, during this reporting period. (This section will be uploaded to the GEF Portal)
Knowledge management and Learning (KML): Does the project have a KML strategy? | Yes
If YES, what is the implementation progress? In your answer, please describe how the project is fostering knowledge sharing and learning among stakeholders at national and sub-national level. | Initiated following the organization of the launch workshop during which the main actors, notably the representatives of the local communities of the two pilot zones, attended
If NO, how does the project identify, collect and document good practices?
Please list good practices, including key-technical and/or institutional innovations, from the project thus far. | Not yet
Communication strategy: Does the project have a communication strategy? | No
Please provide a brief overview of the communications successes and challenges this fiscal year.
Human-interest story: Please share a human-interest story from your project, focusing on how the project has helped to improve people's livelihoods while contributing to achieving the expected Global Environmental Benefits. Please indicate any Socio-economic Co-benefits that were generated by the project. Include at least one beneficiary quote and perspective, and please also include related photos and photo credits.
Please provide links to related website, social media account
Please provide a list of publications, leaflets, video materials, newsletters, or other communications assets publised on the web, if any.
Please indicate the Communication and/or knowledge management focal point's name and contact detais.

## 12. Indigenous & Local Involve.
12. Indigenous Peoples and Local Communites Involvement
Are Indigenous Peoples and local communities involved in the project (as per the approved Project Document)? If yes, please briefly explain.
If applicable, please describe the process and current status of on-going/completed, legitimate consultations to obtain Free, Prior and Informed Consent (FPIC) with the indigenous communities. For local communities, the participatory approach of the project was implemented throughout the PPG phase. Local populations have first been consulted at the very beginning of the process and have therefore been able to contribute actively to the development of the Bibans project. The interest of the local populations in the project is evident as 1,284 project proposals were submitted by the populations to the project design team. Local authorities and civil society representatives have provided continuous support to the project design through assisting local populations in formulating their projects and gathering their proposals, supporting the field visits and consultations undertaken by the PPG experts, and participating actively to the workshops. To further ensure the buy-in of local populations and based on the experience from previous programmes, a financial counterpart will be requested to benefit from the project. Do indigenous peoples and/or local communities have an active partcipation in the project activities? If yes, briefly describe how.

## 13. Co-Financing Table
13. Co-Financing Table
Sources of Co-financing | Name of Co-financer | Type of Co-financing | Amount Confirmed at CEO endorsement/approval (in USD) | Actual Amount Materialized at 30 June 2025 (in USD)
Gouvernement national et local | Ministère des finances | Investissement public | 29220460
Total |  | Total | 29220460 | 0
Please explain any significant changes in project co-financing since CEO Endorsement/Approval, or differences between the pledged and materialized co-financing amounts.
GEF CoFinancing Guidelines 2018

## 14. GEO Location
14. Geo Location Information
This section should be completed ONLY by projects with 1st PIR and in case the geographic coverage of project activities has changed since last reporting period. This information is required by GEF Secretariat in GEF Portal
Are there any changes in the geographic coverage of the project activities since the last PIR report? |  |  |  | No
Location Name | Latitude | Longitude | Geo Name ID |  | Location & Activity Description*
Ighil Ali | 36.3177 | 4.5195
Téniet En Nasr | 36.2167 | 4.5833

## Annex
Annex. Monitoring Area-based GEF Core Indicator Commitments and Progress with FERM
The Framework for Ecosystem Restoration Monitoring (FERM), developed by FAO, is the official monitoring platform for tracking global progress and disseminating good practices for the UN Decade of Ecosystem Restoration. The FERM can serve as an integrated GIS-based platform, providing GEF staff and all relevant stakeholders the chance to display the progress of committed versus achieved land under restoration or under improved management for conservation and sustainable use, along with clear results such as the percentage of project achievement. Having a common tracking and monitoring platform allows users to comprehensively assess and report on project progress. A user-friendly dashboard showcasing project results gives stakeholders a clear understanding of the extent to which project targets have been achieved. Projects with area-based GEF Core Indicators (GEF Core Indicators 1-5 and LDCF Core Indicator 2) are encouraged to register in the FERM platform.
Useful links:
• FERM website
• FERM User Guide (PDF)
• FERM YouTube channel
• Email Carmen Morales
26 It also supports countries in reporting areas under restoration for the Kunming-Montreal GBF Target 2 (areas under restoration) for which FAO is the custodian agency.