GEF - PROJECT IMPLEMENTATION REPORT (PIR)

Document Generated by: CCA TM

At: 2025-08-07 04:42:21

# Table of contents

1 PROJECT IDENTIFICATION

1.1 Project Details

1.2 Project Description

1.3 Project Contacts

2 Overview of Project Status

2.1 UNEP PoW & UN

2.2. GEF Core and Sub Indicators

2.3. Implementation Status and Risks

2.4 Co Finance

2.5. Stakeholder

2.6. Gender

2.7. ESSM

2.8. KM/Learning

Reflows

2.9. Stories

3 Performance

3.1 Rating of progress towards achieving the project outcomes

3.2 Rating of progress implementation towards delivery of outputs (Implementation Progress)

4 Risks

4.1 Table A. Project management Risk

4.2 Table B. Risk-log

4.3 Table C. Outstanding Moderate, Significant, and High risks

5 Amendment - GeoSpatial

5.1 Table A: Listing of all Minor Amendment (TM)

5.2 Table B: History of project revisions and/or extensions (TM)

UNEP GEF PIR Fiscal Year 2025

Reporting from 1 July 2024 to 30 June 2025

# 1 PROJECT IDENTIFICATION

## 1.1 Project Details

| GEF ID: 10926 | Umoja WBS: |
| --- | --- |
| SMA IPMR ID: | Grant ID:S1-32LDL-000065 |
| Project Short Title: Improved livelihood in Tuvalu |  |
| Project Title: Ecosystem based adaptation for improved livelihood in Tuvalu |  |
| Duration months planned: | 60 |
| Duration months age: | 19 |
| Project Type: | FSP |
| Parent Programme if child project: | None |
| Project Scope: | National |
| Region: | Asia Pacific |
| Countries: | Tuvalu |
| GEF Focal Area(s): | Climate Change Adaptation |
| GEF financing amount: | $ 4,416,210.00 |
| Co-financing amount: | $ 14,116,674.00 |
| Date of CEO Endorsement/Approval: | 2023-11-01 |
| UNEP Project Approval Date: | 2024-02-22 |
| Start of Implementation (PCA entering into force): | 2024-02-22 |
| Date of Inception Workshop, if available: | 2024-08-28 |
| Date of First Disbursement: | 2024-07-19 |
| Total disbursement as of 30 June 2025: | $ 500,000.00 |
| Total expenditure as of 30 June: | $ 0 (commitments) |
| Midterm undertaken?: | n/a |
| Actual Mid-Term Date, if taken: |  |
| Expected Mid-Term Date, if not taken: | 2027-05-02 |
| Completion Date Planned - Original PCA: | 2024-05-02 |
| Completion Date Revised - Current PCA: | 2029-07-19 |
| Expected Terminal Evaluation Date: | 2029-03-19 |
| Expected Financial Closure Date: | 2030-01-19 |

## 1.2 Project Description

## 1.3 Project Contacts

| Division(s) Implementing the project | Climate Change Division |
| --- | --- |
| Name of co-implementing Agency | n.a. |
| Executing Agency (ies) | Climate Change Department, Ministry of Finance |
| names of Other Project Partners |  |
| UNEP Portfolio Manager(s) | Jessica Troni |
| UNEP Task Manager(s) | Bunchingiv Bazartseren |
| UNEP Budget/Finance Officer | Priscillah Kaara |
| UNEP Support Assistants | Catherine Goreti Okoch/Ruth Mutinda |
| Manager/Representative | Mervina Paueli |
| Project Manager | Senita Felemiti |
| Finance Manager | Kelesi Sikela |
| Communications Lead, if relevant | n.a. |

# 2 Overview of Project Status

## 2.1 UNEP PoW & UN

| UNEP Current Subprogramme(s): | Climate Action Sub-programme |
| --- | --- |
| UNEP previous Subprogramme(s): |  |
| PoW Indicator(s): | Climate Action: i.. Number of national, subnational and private-sector actors that adopt climate change mitigation and/or adaptation and disaster risk reduction strategies and policies with UNEP support ii) Amounts provided and mobilized in $ per year in relation to the continued existing collective mobilization goal of the $100 billion commitment through to 2025 with UNEP support iv. Positive shift in public opinion, attitudes and actions in support of climate action as a result of UNEP action Nature: (i) Number of national or subnational entities that, with UNEP support, adopt integrated approaches to address environmental and social issues and/or tools for valuing, monitoring and sustainably managing biodiversity. |
| UNSDCF/UNDAF linkages |  |
| Link to relevant SDG Goals | - Goal 1: End poverty in all its forms everywhere - Goal 2: End hunger, achieve food security and improved nutrition and promote sustainable agriculture - Goal 5: Achieve gender equality and empower all women and girls - Goal 6: Ensure availability and sustainable management of water and sanitation for all - Goal 13: Limit and adapt to climate change. - Goal 14: Conserve and sustainably use the oceans, seas and marine resources for sustainable development - Goal 15: Protect, restore and promote sustainable use of terrestrial ecosystems, sustainably manage forests, combat desertification, and halt and reverse land degradation and halt biodiversity loss |
| Link to relevant SDG Targets: | - 1.1 By 2030, eradicate extreme poverty for all people everywhere, currently measured as people living on less than $1.25 a day - 1.5 By 2030, build the resilience of the poor and those in vulnerable situations and reduce their exposure and vulnerability to climate-related extreme events and other economic, social and environmental shocks and disasters - 2.1 By 2030, end hunger and ensure access by all people, in particular the poor and people in vulnerable situations, including infants, to safe, nutritious and sufficient food all year round - 2.3 By 2030, double the agricultural productivity and incomes of small-scale food producers, in particular women, indigenous peoples, family farmers, pastoralists and fishers, including through secure and equal access to land, other productive resources and inputs, knowledge, financial services, markets and opportunities for value addition and non-farm employment - 2.4 By 2030, ensure sustainable food production systems and implement resilient agricultural practices that increase productivity and production, that help maintain ecosystems, that strengthen capacity for adaptation to climate change, extreme weather, drought, flooding and other disasters and that progressively improve land and soil quality - 5.1 End all forms of discrimination against all women and girls everywhere - 5.5 Ensure women's full and effective participation and equal opportunities for leadership at all levels of decision-making in political, economic and public life - 6.4 By 2030, substantially increase water-use efficiency across all sectors and ensure sustainable withdrawals and supply of freshwater to address water scarcity and substantially reduce the number of people suffering from water scarcity - 6.6 By 2020, protect and restore water-related ecosystems, including mountains, forests, wetlands, rivers, aquifers and lakes - 13.3 Improve education, awareness-raising and human and institutional capacity on climate change mitigation, adaptation, impact reduction and early warning - 13.b Promote mechanisms for raising capacity for effective climate change-related planning and management in least developed countries and small island developing States, including focusing on women, youth and local and marginalized communities - 14.2 By 2020, sustainably manage and protect marine and coastal ecosystems to avoid significant adverse impacts, including by strengthening their resilience, and take action for their restoration in order to achieve healthy and productive oceans - Target 14.5 By 2020, conserve at least 10 per cent of coastal and marine areas, consistent with national and international law and based on the best available scientific information - 15.1 By 2020, ensure the conservation, restoration and sustainable use of terrestrial and inland freshwater ecosystems and their services, in particular forests, wetlands, mountains and drylands, in line with obligations under international agreements - 15.5 Take urgent and significant action to reduce the degradation of natural habitats, halt the loss of biodiversity and, by 2020, protect and prevent the extinction of threatened species - 15.9 By 2020, integrate ecosystem and biodiversity values into national and local planning, development processes, poverty reduction strategies and accounts |

## 2.2. GEF Core and Sub Indicators

GEF core or sub indicators targeted by the project as defined at CEO Endorsement/Approval, as well as results

|  | Targets - Expected Value |  |  |  |
| --- | --- | --- | --- | --- |
| Indicators | Mid-term | End-of-project | Total Target | Materialized to date |
| 1. Total number of direct beneficiaries | Total: 2,200 (1,100 males, 1,100 females) | Total: 4,300 (2,150 males, 2,150 females) | Total: 4,300 (2,150 males, 2,150 females) | Not materialized. The implementation has not fully started by the end of the reporting period. |
| 2. Area of land managed for climate resilience (ha) | 260 ha | 567 ha | 567 ha | Not materialized. The implementation has not fully started by the end of the reporting period. |
| 3. Total number of policies/plans that will mainstream climate resilience | 2 | 4 | 4 | Not materialized. The implementation has not fully started by the end of the reporting period. |
| 4. Total number of people trained. | Total: 2,200 (1,100 males, 1,100 females) | Total: 4,300 (2,150 males, 2,150 females) | Total: 4,300 (2,150 males, 2,150 females) | Not materialized. The implementation has not fully started by the end of the reporting period. |

Implementation Status 2025: This is the first PIR.

## 2.3. Implementation Status and Risks

|  | PIR# | Rating towards outcomes (section 3.1) | Rating towards outputs (section 3.2) | Risk rating (section 4.2) |
| --- | --- | --- | --- | --- |
| FY 2025 | 1st PIR | MU | MU | M |
| FY 2024 |  |  |  |  |
| FY 2023 |  |  |  |  |
| FY 2022 |  |  |  |  |
| FY 2021 |  |  |  |  |
| FY 2020 |  |  |  |  |
| FY 2019 |  |  |  |  |
| FY 2018 |  |  |  |  |
| FY 2017 |  |  |  |  |
| FY 2016 |  |  |  |  |
| FY 2015 |  |  |  |  |

Progress: Information on progress outcomes of project implementation activities:

There has been a very limited progress since the project inception workshop, due to the delay in forming the Project Management Unit (PMU). The project was officially launched on 29 August, 2024, in Funafuti, Tuvalu. The one-day event held at the Kilogafou Tausoalima in Funafuti, Tuvalu. A total of 39 participants attended the launch, including representatives of the island communities on the capital from Nanumea, Nanumaga, Nukufetau, Funafuti, and Vaitupu;, relevant stakeholder government offices, NGOs, CSOs, as well as Climate Change Department and UNEP. The Inception workshop report is attached to this report. The key PMU personnel, namely the Project Coordinator and Admin, Finance and Procurement officer have been hired by end of Q2 2025 and the recruitment of the remining PMU personnel is underway. Momentum is expected to be gained from the Q3 2025. The baseline study is commissioned in Q2 2025, the in-country mission is undertaken and is expected to be finalized by end October 2025.

Challenges: Information on challenges of project implementation activities:

- Institutional change: While formalizing the legal instrument between Government and UNEP, restructuring took place in the Government resulting in change of the host Ministry. This has caused a certain level of delay. Also establishment of Climate Change Division within UNEP has caused a slight delay in formalizing the legal instrument.

- Limited labor market in Tuvalu. This has been the key challenge and the main cause of delay in project implementation. To hire PMU personnel, the key positions have been announced four times, due to small population of Tuvalu and a limited number of qualified personnel. The two key positions are filled towards the end of the reporting period. To address this challenge, jointly with Government, UNEP explored an option to sub-contract the project implementation to a local NGO. Unfortunately, this has proven unfeasible as well.

## 2.4 Co Finance

| Planned Co-finance: | $ 14,116,674 |
| --- | --- |
| Actual to date: |  |
| Progress | Justify progress in terms of materialization of expected co-finance. State any relevant challenges: As the project struggled to establish Project |

## 2.5. Stakeholder

| Date of project steering committee meeting | 2025-12-01 |
| --- | --- |
| Stakeholder engagement (will be uploaded to GEF Portal) | We plan to organize the PSC meeting within Q4 2025 or Q1 2026. This is primarily due to the fact that it has taken very long to fill in the Project Management UNT (PMU) positions. |

## 2.6. Gender

| Does the project have a gender action plan? | Yes. |
| --- | --- |
| Gender mainstreaming (will be uploaded to GEF Portal): | It is already uploaded as Appendix 17 of the Project document. |

## 2.7. ESSM

| Moderate/High risk projects (in terms of Environmental and social safeguards) | Was the project classified as moderate/high risk CEO Endorsement/Approval Stage? Yes. It is rated as Moderate risk. If yes, what specific safeguard risks were identified in the SRIF/ESERN? SS 2: Climate Change and Disaster Risks SS 6: Displacement and Involuntary Resettlement SS 7: Indigenous Peoples |
| --- | --- |
| New social and/or environmental risks | Have any new social and/or environmental risks been identified during the reporting period? No. If yes, describe the new risks or changes? |
| Complaints and grievances related to social and/or environmental impacts | Has the project received complaints related to social and/or environmental impacts (actual or potential) during the reporting period? No. If yes, please describe the complaint(s) or grievance(s) in detail, including the status, significance, who was involved and what actions were taken? |
| Environmental and social safeguards management | Of the eight Safeguard Standards, five triggered a low-risk significance, and three triggered a moderate-risk significance. As the project implementation has not started in full swing, implementation of Environmental and Social Management Plan has not yet started. |

## 2.8. KM/Learning

| Knowledge activities and products | Project factsheet at https://wedocs.unep.org/handle/20.500.11822/45899;jsessionid=80FB2E8A46CDB27CA12E390AFDBCECDB |
| --- | --- |
| Main learning during the period |  |

## Reflows

| Reflows (for NGIs only) |  |
| --- | --- |

## 2.9. Stories

| Stories to be shared | n.a. |
| --- | --- |

# 3 Performance

## 3.1 Rating of progress towards achieving the project outcomes

| Project Objective and Outcomes | Indicator | Baseline level | Mid-Term Target or Milestones | End of Project Target | Progress as of current period(numeric, percentage, or binary entry only) | Summary by the EA of attainment of the indicator & target as of 30 June | Progress rating |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Objective: To reduce vulnerability to climate change through adaptive agricultural practices and ecosystem management in Tuvalu. Outcome 1.1: Restoration and increased resilience of 13 ha of agricultural systems on 8 islands against the impacts of climate change and salt-water intrusion through innovative land management and agricultural practices. | Indicator 1: Number of direct project beneficiaries disaggregated by gender | 0 | Total: 2,200 (1,100 males, 1,100 females) | Total: 4,300 (2,150 males, 2,150 females) | 0 | The project implementation has been delayed due to the slow process to set-up the project implementation unit (PMU) and limited labor market in Tuvalu. | MU |
|  | Indicator 2: Area of coastal and forest ecosystems restored or placed under improved conservation. | 0 | 260 ha | 520 ha | 0 | The project implementation has been delayed due to the slow process to set-up the PMU and limited labor market in Tuvalu. | MU |
|  | Indicator 3: Number of raised concrete beds and accompanying irrigation systems introduced to 8 islands by the proposed project. | 0 | 100 raised concrete beds and accompanying rainwater harvesting tanks and irrigations systems | 449 raised concrete beds and accompanying rainwater harvesting tanks and irrigations systems | 0 | The project implementation has been delayed due to the slow process to set-up the PMU and limited labor market in Tuvalu. | MU |
|  | Indicator 4: Percentage increase in crop production from introduced climate-resilient practices | 0 | 10% increase in crop production from climate-resilient practices introduced to raised concrete beds as well as within and surrounding active pulaka pits | 30% increase in crop production from climate-resilient practices introduced to raised concrete beds as well as within and surrounding active pulaka pits | 0 | The project implementation has been delayed due to the slow process to set-up the PMU and limited labor market in Tuvalu. | MU |
|  | Indicator 5: Number of community training workshops held by community training groups. | 0 | At least 24 training workshops across all 8 target islands, consisting of 3 workshops per island over 1.5 years. | At least 64 training workshops across all 8 target islands, consisting of 2 workshops per island per year over 4 years. | 0 | The project implementation has been delayed due to the slow process to set-up the PMU and limited labor market in Tuvalu. | MU |
| Outcome 1.2: Groundwater infiltration and flood-risk reduction services improved on 8 islands through SLM practices that include the restoration and conservation of degraded atoll ecosystems. | Indicator 6: Number of hectares of marine area declared a LMMA under the project | 0 | 52 ha | 104 ha | 0 | The project implementation has been delayed due to the slow process to set-up the PMU and limited labor market in Tuvalu. | MU |
|  | Indicator 7: Number of recipients with an additional or enhanced livelihood option by including training programmes with pre- and post- training surveys to assess the participants understanding of the livelihood options. | 0 | 400 (200 male, 200 female) with new or enhanced livelihood option | 800 (400 male, 400 female) with new or enhanced livelihood option | 0 | The project implementation has been delayed due to the slow process to set-up the PMU and limited labor market in Tuvalu. | MU |
| Outcome 2.1. Institutional uptake of EbA enhanced through policy revisions and capacity building among core government staff, professionals and community representatives. | Indicator 8: Number of policies and plans revised to incorporate SLM, EbA and climate-resilient agricultural approaches | 0 | 1 sub-national plan under the Public Works Department | 4 policies and plans, including 1 sub-national plan under the Public Works Department and 3 national policies or plans. | 0 | The project implementation has been delayed due to the slow process to set-up the PMU and limited labor market in Tuvalu. | MU |
|  | Indicator 9: Change in capacity perception index for government officials to integrate EbA, climate-resilient practice and SLM into policies and plans. | To be determined at beginning of project implementation | Change in capacity perception index by at least 1 point | Change in capacity perception index by at least 3 points | 0 | The project implementation has been delayed due to the slow process to set-up the PMU and limited labor market in Tuvalu. | MU |
| Outcome 2.2: Develop and implement strategic action plans for streamlining EbA national policy and planning frameworks. | Indicator 10: Change in score for the implementation of SLM, EbA and climate-resilient agriculture principles mainstreamed into policies and plans | To be determined at beginning of project implementation | Change in score of at least 1 | Change in score of at least 3 | 0 | The project implementation has been delayed due to the slow process to set-up the PMU and limited labor market in Tuvalu. |  |
| Outcome 2.3: Uptake of EbA and climate-resilient agriculture practices enhanced through multi-level stakeholder decision-making programmes, knowledge management and awareness-raising regarding CCA. | Indicator 11: Percentage of the population with improved awareness of climate change impacts and climate change adaptation using EbA and climate-resilient agriculture | To be determined at beginning of project implementation | At least 20% of the population | At least 50% of the population | 0 | The project implementation has been delayed due to the slow process to set-up the PMU and limited labor market in Tuvalu. |  |

## 3.2 Rating of progress implementation towards delivery of outputs (Implementation Progress)

| Component/Outcome | Output/Activity | Expected completion date | Implementation status as of previous reporting period (%) | Implementation status as of current reporting period (%) | Progress rating justification, description of challenges faced and explanations for any delay | Progress Rating |
| --- | --- | --- | --- | --- | --- | --- |
| 1.1: Restoration and increased resilience of 13 ha of agricultural systems on 8 islands against the impacts of climate change and salt-water intrusion through innovative land management and agricultural practices. | Output 1.1.1. National pulaka pit health and groundwater assessment undertaken on all 8 target islands. |  | - | 0 | The project implementation has been delayed due to the slow process to set-up the PMU and limited labor market in Tuvalu. Baseline assessment is commissioned. | MU |
|  | Output 1.1.2: 449 raised concrete beds introduced to 8 target islands to upscale the climate proofing project. |  | - | 0 | The project implementation has been delayed due to the slow process to set-up the PMU and limited labor market in Tuvalu. Baseline assessment is commissioned. | MU |
|  | Output 1.1.3. Alternative irrigation strategies, including drip irrigation, rooftop rainwater harvesting and water tanks installed to facilitate water supply to 449 raised concrete beds introduced on each of the 8 target islands. |  | - | 0 | The project implementation has been delayed due to the slow process to set-up the PMU and limited labor market in Tuvalu. Baseline assessment is commissioned. | MU |
|  | Output 1.1.4: Diversified cropping strategies introduced to 449 raised concrete beds and pulaka pits to promote the use of climate-resilient crops. |  | - | 0 | The project implementation has been delayed due to the slow process to set-up the PMU and limited labor market in Tuvalu. Baseline assessment is commissioned. | MU |
|  | Output 1.1.5. 8 community training groups — including representatives from women’s groups — established around target sites to generate knowledge of appropriate methodologies and upscale best practices of adaptation strategies among stakeholders. |  | - | 0 | The project implementation has been delayed due to the slow process to set-up the PMU and limited labor market in Tuvalu. Baseline assessment is commissioned. | MU |
| 2.1. Institutional uptake of EbA enhanced through policy revisions and capacity building among core government staff, professionals and community representatives. | Output 2.1.1: Revisions made to 3 national policies and procedures relevant to EbA, water and agriculture to align with the GoT’s broader sustainability indicators, streamline funding for adaptation priorities and facilitate coordination between government agencies. |  | - | 0 | The project implementation has been delayed due to the slow process to set-up the PMU and limited labor market in Tuvalu. Baseline assessment is commissioned. | MU |
|  | Output 2.1.2: Training conducted for 100 government officials, with a focus on technical officers, coastal adaptation management professionals, gender experts, representatives from women’s groups and community representatives on the integration of EbA, climate-resilient agriculture and SLM principles into policies and planning at both national and community levels. |  | - | 0 | The project implementation has been delayed due to the slow process to set-up the PMU and limited labor market in Tuvalu. Baseline assessment is commissioned. | MU |
| 2.2: Develop and implement strategic action plans for streamlining EbA national policy and planning frameworks. | Output 2.2.1: Guidance Note for compliance monitoring and implementation of EbA policy recommendations prepared under Output 2.1.1. |  | - | 0 | The project implementation has been delayed due to the slow process to set-up the PMU and limited labor market in Tuvalu. Baseline assessment is commissioned. | MU |
|  | Output 2.2.2: Land-use zoning plan developed to enable EbA, climate-resilient agriculture and SLM under existing land tenure systems. |  | - | 0 | The project implementation has been delayed due to the slow process to set-up the PMU and limited labor market in Tuvalu. Baseline assessment is commissioned. | MU |
| Outcome 2.3: Uptake of EbA and climate-resilient agriculture practices enhanced through multi-level stakeholder decision-making programmes, knowledge management and awareness-raising regarding CCA. | Output 2.3.1: Gender-responsive best-practice guidelines developed and disseminated to raise awareness and facilitate replication and upscaling of EbA, climate-resilient agricultural and land management practices. |  | - | 0 | The project implementation has been delayed due to the slow process to set-up the PMU and limited labor market in Tuvalu. Baseline assessment is commissioned. | MU |
|  | Output 2.3.2: A gender-responsive knowledge management and communication strategy developed for integrating EbA best practices and lessons learned into planning and policy. |  | - | 0 | The project implementation has been delayed due to the slow process to set-up the PMU and limited labor market in Tuvalu. Baseline assessment is commissioned. | MU |
|  | Output 2.3.3: Continuous training and gender-responsive knowledge generation programmes for public sector officials developed using the results of the direct capacity building of technical officers in Output 2.1.2. |  | - | 0 | The project implementation has been delayed due to the slow process to set-up the PMU and limited labor market in Tuvalu. Baseline assessment is commissioned. | MU |

The Task Manager will decide on the relevant level of disaggregation (i.e. either at the output or activity level).

# 4 Risks

## 4.1 Table A. Project management Risk

Please refer to the Risk Help Sheet for more details on rating

| Risk Factor | EA Rating | TM Rating |
| --- | --- | --- |
| 1 Management structure - Roles and responsibilities | Low | Low |
| 2 Governance structure - Oversight | Moderate | Moderate |
| 3 Implementation schedule | Substantial | Substantial |
| 4 Budget | Moderate | Moderate |
| 5 Financial Management | Low | Low |
| 6 Reporting | Moderate | Moderate |
| 7 Capacity to deliver | Moderate | Moderate |

If any of the risk factors is rated a Moderate or higher, please include it in Table B below

## 4.2 Table B. Risk-log

Implementation Status (Current PIR)

Insert ALL the risks identified either at CEO endorsement (inc. safeguards screening), previous/current PIRs, and MTRs. Use the last line to propose a suggested consolidated rating.

| Risks | Risk affecting: Outcome / outputs | CEO ED | PIR 1 | PIR 2 | PIR 3 | PIR 4 | PIR 5 | Current PIR | Δ | Justification |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Environmental | Extreme weather events (such as droughts, TCs and floods) at project sites may damage or destroy EbA activities implemented through the project. | M | M |  |  |  |  |  |  | Rating not changed as the implementation has not fully started. |
| Social | Women may be restricted from participating in community consultations and decision-making processes during project implementation, leading to project maladaptation | M | M |  |  |  |  |  |  | Rating not changed as the implementation has not fully started. |
| Social | National or regional restrictions due to a national or global disease outbreaks may cause project delays. | L | L |  |  |  |  |  |  | Rating not changed as the implementation has not fully started |
| Social | High staff turnover in the government departments and implementing agencies. | L | L |  |  |  |  |  |  | Rating not changed as the implementation has not fully started |
| Environmental | Land-tenure arrangements proposed by the project for the conservation of ecological buffer zones may restrict access to resources, affect customary land rights and create some level of economic displacement. | M | M |  |  |  |  |  |  | Rating not changed as the implementation has not fully started |
| Social | Limited community ownership of project activities and interventions post-project implementation. | M | M |  |  |  |  |  |  | Rating not changed as the implementation has not fully started |
| Social | Limited technical, on-the-ground expertise for implementing project interventions. | L | M |  |  |  |  |  |  | It has taken several rounds of announcements to fill-in PMU positions. The country’s labor market is found extremely limited. |
| Social | High cost of transportation. | M | M |  |  |  |  |  |  | Rating not changed as the implementation has not fully started |

## 4.3 Table C. Outstanding Moderate, Significant, and High risks

Additional mitigation measures for the next periods

| Risk | Actions decided during the previous reporting instance (PIRt-1, MTR, etc.) | Actions effectively undertaken this reporting period | What | When | By Whom |
| --- | --- | --- | --- | --- | --- |
| Extreme weather events (such as droughts, TCs and floods) at project sites may damage or destroy EbA activities implemented through the project. | Implementation has not fully started |  |  |  |  |
| Women may be restricted from participating in community consultations and decision-making processes during project implementation, leading to project maladaptation | Implementation has not fully started |  |  |  |  |
| Land-tenure arrangements proposed by the project for the conservation of ecological buffer zones may restrict access to resources, affect customary land rights and create some level of economic displacement. | Implementation has not fully started |  |  |  |  |
| Limited community ownership of project activities and interventions post-project implementation. | Implementation has not fully started |  |  |  |  |
| Limited technical, on-the-ground expertise for implementing project interventions. |  | UNEP has agreed to a level of increase in salary scales, which may require a budget revision and also attempted to bring in a local NGO to take the implementation. | Reflect increased PMU salary scales through a budget revision. xx | Q4 2025 or Q1 2026, after this is approved by the PSC first meeting. | UNEP |
| High cost of transportation. | Implementation has not fully started |  |  |  |  |

High Risk (H): There is a probability of greater than 75% that assumptions may fail to hold or materialize, and/or the project may face high risks. Significant Risk (S): There is a probability of     between 51% and 75% that assumptions may fail to hold and/or the project may face substantial risks. Moderate Risk (M): There is a probability of between 26% and 50% that assumptions may     fail to hold or materialize, and/or the project may face only modest risks. Low Risk (L): There is a probability of up to 25% that assumptions may fail to hold or materialize, and/or the project may     face only modest risks.

# 5 Amendment - GeoSpatial

Project Minor Amendments

Minor amendments are changes to the project design or implementation that do not have significant impact on the project objectives or scope, or an increase of the GEF project financing up to         5% as described in Annex 9 of the Project and Program Cycle Policy Guidelines.Please tick each category for which a change occurred in the fiscal year of reporting and provide a description of         the change that occurred in the textbox. You may attach supporting document as appropriate

## 5.1 Table A: Listing of all Minor Amendment (TM)

| Minor Amendments | Changes |
| --- | --- |
| Results Framework: | No |
| Components and Cost: | No |
| Institutional and implementation arrangements: | No |
| Financial Management: | No |
| Implementation Schedule: | No |
| Executing Entity: | No |
| Executing Entity Category: | No |
| Minor project objective change: | No |
| Safeguards: | No |
| Risk analysis: | No |
| Increase of GEF financing up to 5%: | No |
| Location of project activity: | No |
| Other: |  |

Minor amendments:

Minor amendment may be needed to reflect the latest market rates for the PMU remuneration, which ahs been found below the market rate, although those has been established based on the UN salary scales at the time.

## 5.2 Table B: History of project revisions and/or extensions (TM)

| Version | Type | Signed/Approved by UNEP | Entry Into Force (last signature Date) | Agreement Expiry Date | Main changes introduced in this revision |
| --- | --- | --- | --- | --- | --- |
| None. |  |  |  |  |  |

GEO Location Information:

The Location Name, Latitude and Longitude are required fields insofar as an Agency chooses to enter a project location under the set format. The Geo Name ID is required in instances where         the location is not exact, such as in the case of a city, as opposed to the exact site of a physical infrastructure. The Location & Activity Description fields are optional. Project longitude and         latitude must follow the Decimal Degrees WGS84 format and Agencies are encouraged to use at least four decimal points for greater accuracy. Users may add as many locations as         appropriate. Web mapping applications such as OpenStreetMap or GeoNames use this format. Consider using a conversion tool as needed, such as: https://coordinates-converter.com Please         see the Geocoding User Guide by clicking here

| Location Name | Latitude | Longitude | GEO Name ID | Location Description | Activity Description |
| --- | --- | --- | --- | --- | --- |
| None. |  |  |  |  |  |

Please provide any further geo-referenced information and map where the project interventions is taking place as appropriate. *

[Annex any linked geospatial file]

Geolocations are unchanged, subject to the finalization of baseline study.

The score ranges from 1 to 5 and is ranked as: 1) no capacity built; 2) initial awareness raised; 3) substantial training in the practical application of the concepts; 4) knowledge effectively transferred and tested; and 5) demonstratable ability to apply or disseminate knowledge.

The score ranges from 1 to 5 and is ranked as: 1) no implementation of SLM, EbA or climate-resilient agriculture principles mainstreamed into policy; 2) limited implementation of SLM, EbA or climate-resilient agriculture principles mainstreamed into policy; 3) moderate implementation of SLM, EbA or climate-resilient agriculture principles mainstreamed into policy; 4) SLM, EbA or climate-resilient agriculture principles mainstreamed into policy has mostly been implemented and enforced; and 5) all SLM, EbA or climate-resilient agriculture principles mainstreamed into policy have been fully enforced.

Based on global experience of project delays resulting from travel restrictions and quarantine.

Based on risks and lessons learned from the R2R Project and NAPA.

Based on stakeholder engagements and risks identified under the R2R Project.

Based on risks and lessons learned from the R2R Project, Building Capacity and Mainstreaming Sustainable Land Management in Tuvalu, NAPA and COSPPAC.

Based on risks and lessons learned from the R2R Project, Building Capacity and Mainstreaming Sustainable Land Management in Tuvalu and Pacific Adaptation to Climate Change.

Based on stakeholder engagements.

Based on stakeholder engagements and risks identified under the R2R Project.

Based on risks and lessons learned from the R2R Project, Building Capacity and Mainstreaming Sustainable Land Management in Tuvalu, NAPA and COSPPAC.

Based on risks and lessons learned from the R2R Project, Building Capacity and Mainstreaming Sustainable Land Management in Tuvalu and Pacific Adaptation to Climate Change.

Based on stakeholder engagements.