# ANNEX A: PROJECT RESULTS FRAMEWORK

| Objective/ Component/Outcome | Indicator | Baseline | Mid-term Target | End of Project target | Source of Information | Risks and assumptions |
| --- | --- | --- | --- | --- | --- | --- |
| Objective: Improve sustainability of the national protected area (PA) system through increasing PA management effectiveness and mainstreaming PA valuation results into conservation of globally significant biodiversity in China. | - Component1: PA management strengthening - Component2: PA system financial sustainability improving Component 3: Knowledge management, sharing and communications and M&E | Management and planning based on weak evidence and motivated only by income generation; funding haphazard, unsustainable and funds often misspent; Knowledge and information sharing restricted | The accoplishment rate of component 1,2 and 3 reaches 70%,20% and 40% respectively according to the workplan attached in the Endorsement Request appendix. | Management decisions sound and transparent; Funding adequate and sustained; Knowledge and data sharing standard practice |  | Assumptions: The government remains committed to strengthening the PA system and to an incremental growth in the funding allocation to finance the PA network. The government continues to be committed to providing eco-compensations. Risks: Mainstreaming biodiversity and PAs into sectoral development policies will be hindered by poor inter-agency coordination, lack of incentives for other sectors and poor enforcement of agreed priorities, plans and regulations. |
| Component1: PA management strengthening |  |  |  |  |  |  |
| Outcome 1.1 : Evidence-based systematic PA management system strengthened | Outputs: 1.1.1 Design and initiate mandatory basic reporting standard for Chinese nature reserve system and recommend it as a supervision procedure for national nature reserves 1.1.2 Full review of threats to nature reserve and development of standards for mainstreaming sustainability into the existing evaluating management performance 1.1.3 Develop an independent supervisory support system for nature reserve management in China 1.1.4 Establish a database and roster of conservation and biodiversity experts and agencies |  |  |  |  |  |
|  | The number of nature reserves using the mandatory basic reporting standard via MEE | Diverse sporadic reporting to different mother agencies. No central reporting to MEE | At least 80 | At least 200 | Existed standards and flow of data from different PAs. | Assumptions: MEE remains the authorized Clearing House Mechanism (CHM) for CBD in China |
|  | The development of the standards for mainstreaming sustainability into the existing management performance evaluation and adoption by MEE | Threats have been identified in non-systematic and unquantified reviews | The standards are developed after it is sent to experts for comments | The standards are adopted by MEE | Data sharing/reporting agreements with other agencies available Published reports | Assumptions: Other PA management agencies recognise the value of pooling data and agree to cooperate. |
|  | The development of the system and the number of users (the environmental departments at all levels and PAs within the Chinese supervisory system) for the system | No standard assessment system in place. | The system is developed after review of comments from experts | At least 20 provincial EPBs And 100 national nature reserves | Data sharing platform Assessment form designed Revised performance scoring forms | Assumptions: PA reforms will include extending supervisory role of MEE Risks: Central government attention to PA reform and environmental issues is weakened by new development priorities |
|  | Establishment and application of the database and roster The number of approved experts, female expert proportion and dissemination scale | No agreements for cooperation in place Experts identified as informal personal contacts only | The database is established levels. Roster of at least 300 approved experts established 35% of the female experts included in the roster | The database is disseminated to at least 400 nature reserves at various levels via six Inspection Bureaux and provincial EPB s, | Rosters of approved expertise in other professional fields | - Risks: - Different agencies do not wish to cooperate - Funding channel to provide support services not extended after project termination |
| Component 2 PA system financial sustainability improving |  |  |  |  |  |  |
| Outcome 2.1: PA system financial sustainability enhancing through improved PA valuation result mainstreaming, funding use evaluation and funding source broadening methods | Outputs 2.1 Development and standardization of indicators and methods for the valuation of PAs at national level and submitting the results to support the MEE supervision process. 2.2 Valuation of major types of PAs 2.3 Development of funding use effectiveness scorecard for use in PA management supervision, performance assessment and evaluating funding requests 2.4 Development of model PA business engaging approach to allow PAs to better negotiate appropriate funding from multiple sources based on their evaluation results and potential. |  |  |  |  |  |
|  | The development and application of valuation methods | No standardized methods or indicators available | The standardized methods and indicators for valuation are developed and reviewed by experts | The standardized indicators and methods are approved by experts MEE adopt the developed methods in ecological supervision | A variety of methodologies from different valuation systems | Assumptions: - Government continues its policy of improving environmental protection and willingness to pay eco-compensation |
|  | The valuation | Not included in current performance appraisal | N/A | At least 3 types of PA valuation results are achieved | Baseline survey and GIS data | Assumptions: - Government continues its policy of improving environmental protection and willingness to pay eco-compensation |
|  | The development and acceptance of the newly developed fund effectiveness scorecard | Not included in current performance appraisal | N/A | The scorecard is used by at least 5 national nature reserves | Audited financial reports of PAs | Assumptions: The individual PA institutions willing to cooperate in valuation studies and willing to make open financial details. Risks: Coordination of child projects and this support project may prove difficult. |
|  | The number of companies or institutions from the private sector and charities for business engaging approaches trainings | No business engaging approaches | N/A | At least 30 | The needs and requirements from private sectors | Assumptions: Information to support the planning and management of the PAs is made available by government and institutional data holders |
| Component 3: Knowledge management,sharing and communications and M&E |  |  |  |  |  |  |
| Outcome 3.1: Knowledge management, sharing and communications through achievement dissemination, exchanges and awareness-raising | Outputs 3.1.1 Compile best practices guidelines for PA management improvement in China 3.1.2 Assist the programme in development of e-learning and academic training courses to deliver these best practices to PA managers, officials and practitioners 3.1.3 Capacity building and achievement dissemination |  |  |  |  |  |
|  | The number of best practices compiled | International best practice guidelines only available in English and not always suitable to Chinese conditions | At least 2 topics of best practices are accomplished in draft version | 6 topics of the best practices accomplished | The achieved outputs from outcome 1&2 | Assumptions: Different PA management authorities willing to pool data e-learning certificates recognised and contribute to staff advancements and performance assessment Risks: Interdepartmental differences hinder smooth cooperation. Departments send unsuitable personnel to attend important international meetings who either lack technical knowledge for constructive participation or lack authority to represent China' viewpoints. MEE unable to sustain funding of these initiatives after project termination |
|  | The number of trainees and modules Thefemale proportion | The number of specialised training base available is limited The access of e-courses available is limited | 200 trainees participated in the training programme At least 2 e-learning modules available 35% of female trainees | 500 trainees in total At least five e-learning modules available 35% of female trainees | Feedbacks from E-learning courses on web. Feedback forms of 500 stakeholders received training under project |  |
|  | The number of influenced stakeholders | N/A | Achievements are disseminated to at least 20 institutions/organizations and relevant stakeholders. | Achievements are disseminated to at least 50 institutions, organizations and relevant stakeholders. | The achieved results by the project. |  |
| Outcome 3.2 : Monitoring, evaluation and progress review. | Outputs 3.2.1 Undertake continuous monitoring and periodic progress reviews on project execution and the overall project management and associated effectiveness evaluation. |  |  |  |  |  |
|  | The delivery of M&E reports and conduct of mid-term review and final evaluation |  | The timely delivery of high-quality inception report, semi-annual progress reports, progress monitoring reports, project implementation review, supervision mission and supervision reports, monitoring report and mid-term review conducted according to the workplan | The timely delivery of high-quality inception report, semi-annual progress reports, progress monitoring reports, project implementation review, supervision mission and supervision reports, monitoring report and terminal report. Final evaluation conducted according to workplan | GEF and FECO rules | Risks: The inception report, project implementation reviews, semi-annual report, mid-term review and final evaluation are not developed in high quality. The mid-term review and final evaluation are not conducted in time |