Acceleration of Financial Technology-Enabled Climate Resilience: A Pilot Program

Independent Terminal Evaluation

Independent Evaluation of

Acceleration of Financial Technology‑Enabled Climate Resilience Solutions (GEF ID: 10927)

Charla M. Burnett

Vienna, September 2025

This document has been produced without formal United Nations editing. The designations employed and the presentation of the material in this document do not imply the expression of any opinion whatsoever on the part of the Secretariat of the United Nations Industrial Development Organization (UNIDO) concerning the legal status of any country, territory, city or area or of its authorities, or concerning the delimitation of its frontiers or boundaries, or its economic system or degree of development. Designations such as “developed”, “industrialized” or “developing” are intended for statistical convenience and do not necessarily express a judgement about the stage reached by a particular country or area in the development process. Mention of firm names or commercial products does not constitute an endorsement by UNIDO.

This publication has not been formally edited. Photos © UNIDO

Distr. GENERAL | 2025 November| Original: English

# Abstract

This terminal self-evaluation reviews the Global Environment Facility (GEF)-funded project Acceleration of Financial Technology-Enabled Climate Resilience Solutions, implemented by the United Nations Industrial Development Organization (UNIDO) in partnership with BFA Global. The project, active in Kenya, Nigeria, Rwanda, South Africa, and Uganda, sought to accelerate innovative fintech startups delivering adaptation solutions for smallholder farmers and vulnerable communities, while also strengthening investor networks, building talent pipelines, and advancing gender-responsive climate innovation.

The evaluation’s objective was to assess the project’s relevance, coherence, effectiveness, efficiency, sustainability, and gender responsiveness in line with GEF and OECD/DAC criteria, and to draw lessons for GEF-9 programming.

Findings confirm that the project was highly relevant to GEF-7 priorities and UNIDO’s mandate, with clear alignment to national adaptation strategies. Effectiveness was strong: six startups were accelerated (target met), USD 3.3 million in follow-on finance was mobilized (65 percent above target), eleven junior experts were placed (exceeding target), and eleven knowledge products were delivered (surpassing expectations). Beneficiary outreach and land management figures greatly exceeded original targets, though reliance on self-reporting means they should be interpreted with caution.

Coherence was partially achieved, with synergies across investor networks and some UN initiatives, though linkages with national governments and other donor programs were limited due to the nature of the programmatic pre-selection process of the GEF’s Challenge Program for Adaptation Innovation. The project fell short of influencing policy and plans, achieving eight of ten targeted adoptions, reflecting a weakness in the co-creation with national governments. Efficiency was adequate, despite the no-cost extension. Sustainability remains uncertain, with some potential for continued investor and talent networks, but the program demonstrated the clear value for investment in fintech adaptation. Gender inclusion was quantitatively successful, exceeding participation thresholds.

Conclusions highlight that the project delivered strong enterprise-level results, but systemic change, particularly in policy influence, independent verification of results, and sustained institutional engagement was modest due to the scope of the pilot. The project demonstrated proof of concept for fintech-driven climate resilience.

Recommendations for GEF-9 include embedding government participation from the outset; balancing enterprise and systemic indicators; ensuring independent verification of results; strengthening coherence mapping with other climate-finance initiatives; integrating clear exit strategies, including blended finance; and moving from gender-responsive to gender-transformative approaches.

Keywords: Fintech, Climate Resilience, Adaptation, Startups, Investment Mobilization

# Contents

Abstract	3

Contents	4

Acknowledgements	6

Abbreviations and Acronyms	7

Executive Summary	8

1.	Introduction	12

1.1.	Evaluation Purpose	13

1.2.	Evaluation Objectives and Scope	13

1.3.	Theory of Change	14

2.	Methodology	14

2.1.	Evaluation Approach	14

2.2.	Exclusions from Scope	16

2.3.	Data Collection	16

2.4.	Document Review	16

2.5.	Semi-Structured Interviews	17

2.6.	Triangulation	17

2.7.	Financial Analysis and Co-financing Verification	18

3.	Limitations	18

4.	Ethics and Data Protection	19

5.	Project Background and Context	20

3.1.	Startup Selection and Overview	21

6.	Findings	22

6.1.	Relevance	25

6.2.	Coherence	27

6.3.	Effectiveness	27

6.4.	Efficiency	29

6.5.	Sustainability	31

6.6.	Gender Mainstreaming	31

6.7.	Performance of Partners	31

6.8.	Results-based Management	32

7.	Conclusions and Recommendations	32

7.1.	Conclusions	33

7.2.	Recommendations and Management Response	33

8.	Lessons Learned	37

9.	Annexes	41

Annex 1. Evaluation Terms of Reference	41

PROJECT BACKGROUND AND CONTEXT	43

1.	Project factsheet	43

2.	Project context	43

3.	Project objective and expected outcomes	44

4.	Project implementation arrangements	45

5.	Main findings of the Mid-term review (MTR)	45

6.	Budget information	45

Scope and purpose of the evaluation	45

Evaluation approach and methodology	45

1.	Data collection methods	45

2.	Evaluation key questions and criteria	46

3.	Rating system	47

Evaluation process	48

Time schedule and deliverables	48

Evaluation team composition	49

Reporting	49

Annex 1: Project Logical Framework	50

Annex 2: Detailed questions to assess evaluation criteria: See Annex 2 of the UNIDO Evaluation Manual	51

Annex 3: Job descriptions	52

Annex 4- Outline of an in-depth project evaluation report	59

Annex 5: Checklist on evaluation report quality	61

Annex 6: Guidance on integrating gender in evaluations of UNIDO projects and Projects	62

Annex 2. Evaluator Biodata and Justification of Team Composition	64

Annex 3. Evaluation Framework / Matrix	66

Annex 4. List of Documentation Reviewed	72

Annex 5. List of Stakeholders Consulted	78

Annex 6. Project Theory of Change/Logframe	80

Annex 7. Primary Data Collection Instruments	82

Annex 8. Survey / Questionnaire	83

Annex 9. Statistical Data from Evaluation Survey / Questionnaire Analysis	86

Annex 10. Workplan and Deliverables	88

Annex 11. Reconstructed Theory of Change	90

92

# Tables

Table ES.1. Summary of Key Evaluation Findings and Ratings 	  8

Table 1. Programmatic Scope of Terminal Evaluation 					   12

Table 2. Summary of Project Startups Selected 						   23

Table 3. Results Against Logframe/IRRF Indicators 						   26

Table 4. Knowledge Products and Communication Outputs 				   27

Table 5. Project Costs and Outputs by Component (Year 1) 				   29

Table 6. Summary of Recommendations and Management Response 			   34

Maps

Map 1. Locations of fintech–climate startups supported by the UNIDO GEF project 	   20

# Acknowledgements

The evaluator extends appreciation to the representatives of UNIDO Headquarters, the Global Environment Facility (GEF) Secretariat, the BFA Global project team, national Operational Focal Points, government officials, startup founders and employees, investors, and junior experts who participated in interviews and provided documentation.

The evaluation also thanks the UNIDO Project Management Unit for their cooperation and support throughout this evaluation process.

Evaluation team:

Charla M. Burnett, Lead Independent Evaluator

# Abbreviations and Acronyms

| Abbreviation | Meaning |
| --- | --- |
| B2B | Business-to-Business |
| CEO | Chief Executive Officer |
| COP | Conference of the Parties |
| CTI | Climate Technology Innovation Unit |
| DAC | Development Assistance Committee (OECD) |
| ESMF | Environmental and Social Management Framework |
| ESS | Environmental and Social Safeguards |
| GEF | Global Environment Facility |
| GESI | Gender Equality and Social Inclusion |
| HS | Highly Satisfactory |
| HU | Highly Unsatisfactory |
| IAC | Investor Advisory Council |
| ICT | Information and Communications Technology |
| IRPF | Integrated Results and Performance Framework |
| ISID | Inclusive and Sustainable Industrial Development |
| JPMC | JPMorgan Chase Foundation |
| KM | Knowledge Management |
| M&E | Monitoring and Evaluation |
| MEL | Monitoring, Evaluation, and Learning |
| MSME | Micro, Small, and Medium Enterprises |
| MSP | Medium-Sized Project |
| NGO | Nongovernmental Organization |
| OECD | Organisation for Economic Co-operation and Development |
| OFP | Operational Focal Point |
| PIR | Project Implementation Report |
| PSC | Project Steering Committee |
| QA | Quality Assurance |
| SDG | Sustainable Development Goal |
| SME | Small and Medium-sized Enterprise |
| TBD | To Be Determined |
| TE | Terminal Evaluation |
| ToC | Theory of Change |
| ToR | Terms of Reference |
| UN | United Nations |
| UNEG | United Nations Evaluation Group |
| UNIDO | United Nations Industrial Development Organization |
| USD | United States Dollar |
| WFP | World Food Programme |

# Executive Summary

The project Acceleration of Fintech-Enabled Climate Resilience Solutions was implemented by UNIDO in partnership with BFA Global (Catalyst Fund) from 2023–2025 across five African countries (Kenya, Nigeria, Rwanda, South Africa, Uganda). The project aimed to accelerate early-stage startups offering fintech-enabled solutions for climate adaptation, mobilize investment, strengthen talent, and generate knowledge products to position climate resilience as an investable sector.

The project responded to the growing need to position climate resilience not only as a public policy priority but also an investable sector for private capital. Its primary objective was to accelerate innovative early-stage startups offering fintech-enabled solutions for climate adaptation. In doing so, the project sought to:

- Mobilize investment for adaptation solutions and crowd in private finance;

- Strengthen entrepreneurial capacity and talent through venture-building and junior expert placements;

- Enhance gender inclusion by prioritizing women-led startups and solutions targeting women farmers; and

- Generate and disseminate knowledge products to shape investor and policy narratives on climate-fintech linkages.

The evaluation employed a mixed-methods approach, combining document review (e.g., Project Implementation Reports (PIRs), Results Framework, and knowledge products), financial and portfolio analysis, and 11 stakeholder interviews with UNIDO headquarters, BFA Global staff, startup founders and employees, investors, and junior experts.

Key Findings

Table ES.1. Summary of Key Evaluation Findings and Ratings

| Criterion | Summary of Findings | Ratings |
| --- | --- | --- |
| Relevance | The project was highly relevant to national and GEF adaptation priorities, and its tailored venture-building filled a niche not addressed by generic accelerators. | Highly Satisfactory (HS) |
| Coherence | Strong complementarity with market actors and international initiatives, but weak engagement with national governments limited systemic policy alignment. | Satisfactory (S) |
| Effectiveness | Most output targets were met or exceeded; startups demonstrated tangible growth in revenues, outreach, and investor readiness, though fintech integration was uneven. | Satisfactory (S) |
| Efficiency | BFA’s embedded support was transformative and reporting was streamlined; however, high costs of certain services reduced value-for-money and investor outreach was ad hoc. | Moderately Satisfactory (MS) |
| Sustainability | Moderate to strong prospects; several startups secured follow-on capital and embedded systems, but risks remain due to capital intensity, long sales cycles. | Moderately Satisfactory (MS) |
| Progress to Impact | The project catalyzed recognition of adaptation as investable and delivered meaningful social and environmental contributions, though impact figures require verification. | Moderately Satisfactory (MS) |
| Gender Mainstreaming | Gender targets were exceeded, women farmers benefited directly, and startups innovated with inclusive models, but systemic barriers such as land access remain unaddressed. | Satisfactory (S) |
| Environmental Impacts | Startups contributed positively through reforestation, sustainable agriculture, and recycling, but ESS was inconsistently applied across the portfolio. | Satisfactory (S) |
| Monitoring & Reporting | Reporting was standardized and streamlined, but limited independent verification weakens credibility of reported results. | Moderately Satisfactory (MS) |
| Social Impact | Farmers, women, and youth benefitted through improved incomes, services, and skills, though impacts remain modest relative to broader national adaptation needs. | Satisfactory (S) |
| Overall Rating | The project was highly relevant and largely effective, meeting or exceeding its main output targets and demonstrating the viability of adaptation as an investable sector. However, weaknesses in efficiency, limited government engagement, and risks to long-term sustainability contributed to the overall outcome rating. | Moderately Satisfactory (MS) |

Key Conclusions

- The project was highly relevant to early-stage adaptation startups and effectively addressed a market gap by positioning climate resilience as investable. Effectiveness was strong: nearly all output targets were achieved or exceeded, with startups showing measurable growth in users, revenues, and resilience-oriented products. The program also strengthened investor confidence, though sustained investment depends on continued commercial traction and structured engagement.

- Coherence was partial. The project aligned with GEF-7 priorities and UNIDO’s mandate but faced inherent constraints in government engagement due to the Challenge Program for Adaptation Innovation’s global pre-selection process, which bypassed typical Operational Focal Point–led design. This limited national ownership and policy integration. Still, the project created synergies across investor networks and supported knowledge exchange with other adaptation and innovation initiatives.

- Efficiency is rated Moderately Satisfactory. Implementation mechanisms—such as the embedded advisor model and the digital reporting system via the Visible platform functioned well, and total expenditure reached 102 percent of the approved budget (USD 854,269 of USD 835,240). Year 1 disbursement was slower (50 percent execution) but accelerated in Year 2 through adaptive reallocation. Underspending on travel and overspending on project management reflected shifting priorities during implementation and the no-cost extension period.

- Sustainability prospects are Moderate to Strong. Several startups secured follow-on financing, institutional systems were established, and the Circle of Investors will continue under Catalyst Fund. Yet sustainability is limited by capital-intensive sectors, long commercialization cycles, and weak policy alignment. Junior expert placements were transformative but were unsustainable for most startups.

- The project demonstrated adaptation as investable, contributing to farmer income growth, food security, recycling capacity, and sustainable land management, though independent verification is needed to confirm attribution.

- Gender outcomes were strong: three women-led startups (target: two), nine women entrepreneurs (target: five), and outreach to 169,157 women (target: 10,000), and 5 interns placed reflect substantial progress. Women advanced into leadership roles, though persistent barriers to land, irrigation, and finance underscore the need for deeper policy engagement beyond enterprise-level results.

Key Recommendations

1. Strengthen government engagement and policy linkages

Under the GEF Challenge Program model, limited government engagement resulted from the top-down, competitive design that prioritized innovation pilots over national co-creation. Future iterations should incorporate structured government participation from inception, through policy–startup platforms, sandboxes, and co-financed dialogues, to strengthen systemic policy uptake and national ownership. UNIDO should leverage its convening power to align Challenge Program pilots with country adaptation frameworks and regulatory priorities.

2. Introduce flexible catalytic financing instruments

In addition to venture-building support, four of the six startups also received equity funding through the Catalyst Fund structure. However, founders noted that the size and structure of this capital, while catalytic the program did not always address immediate working-capital needs. Future projects could therefore complement existing equity mechanisms with flexible or recoverable grants, blended finance, or revenue-based instruments. Such financing would align with UNIDO’s digital innovation agenda and better enable adaptation-focused fintechs to scale commercially and sustainably.

3. Deepen gender integration and address structural barriers

Move beyond quantitative gender targets toward addressing structural constraints, particularly women’s access to land, irrigation, and finance. Future GEF-9 initiatives should integrate gender-responsive digital finance products and policy advocacy that expand women’s access to resources and markets. Gender integration should be embedded throughout design, implementation, and monitoring.

4. Sustain the adaptation talent pipeline

The junior expert placement model proved transformative but requires sustainable financing. UNIDO and partners should co-finance future placements through partnerships with universities, corporations, and donors. Embedding digital talent pathways within broader innovation ecosystems would preserve one of the program’s most valued and scalable contributions.

5. Strengthen monitoring and verification systems

Future projects should include independent verification of results through standardized digital monitoring tools. Remote-sensing methods (e.g., dashboards, mobile apps, UAV imagery) can validate beneficiary and land-use data, improving credibility with governments and investors. Verified metrics would reinforce adaptation’s legitimacy as an investable sector. This will require an additional dedicated budget to monitoring and verification.

6. Expand investor networks and thought leadership

Investor engagement was a strong feature of the Catalyst Fund model. Startups benefited from curated introductions, investor days (e.g., the Nairobi conference), monthly deal trackers, and “Why We Invested” communications. Building on this success, future GEF-financed programs should formalize and resource these activities as explicit outputs within project design. Structured investor pipelines and dedicated convenings would enhance capital mobilization, sustain visibility beyond the accelerator cohort, and amplify the impact of knowledge products such as the State of Climate Tech Africa report. Scaling these practices under GEF-9 would help position adaptation-focused fintechs as investable solutions within broader climate finance ecosystems.

# Introduction

Table 1. Programmatic Scope of Terminal Evaluation

| Item | Details |
| --- | --- |
| GEF Project ID | 10927 |
| UNIDO SAP/Project No. | 210238 |
| Project Title | Acceleration of Financial Technology-Enabled Climate Resilience Solutions |
| Foca Area | Climate Change – Adaptation |
| GEF Cycle | GEF-7 |
| Modality | Medium-Sized Project (MSP) |
| Implementing Agency | United Nations Industrial Development Organization (UNIDO) |
| Executing Partner | BFA Global |
| Countries Covered | Kenya, Nigeria, Rwanda, South Africa, Uganda |
| Original Approval (CEO Endorsement) | 17 November 2022 |
| Revised End Date (No-Cost Extension) | 30 September 2025 |
| Total GEF Grant | USD 863,242 |
| Agency Fee (UNIDO) | USD 82,008 |
| Total GEF Resources | USD 945,250 |
| Co-Financing (at CEO Endorsement) | USD 10,965,000 (multi-source: DFIs, private sector, partners) |
| Total Project (GEF + co-financing) | USD 11,910,250 |
| Co-Financing Mobilized (reported in PIR 2025) | Approx. USD 12.2 million |

The Acceleration of Financial Technology-Enabled Climate Resilience Solutions Project (GEF ID 10927) is a UNIDO-implemented, GEF-financed initiative executed by BFA Global through the Catalyst Fund. Launched in April 2023 across Kenya, Nigeria, Rwanda, South Africa, and Uganda, the project aims to enhance the adaptive capacity of climate-vulnerable populations by accelerating innovative fintech startups, strengthening enabling ecosystems, and mobilizing private investment for climate resilience. It aligns with the GEF adaptation focal area and reflects UNIDO’s comparative advantage in innovation and SME development alongside BFA Global’s expertise in venture acceleration. With a GEF grant of USD 863,242 and USD 10.9 million in co-financing, the project leverages Africa’s rapidly expanding fintech ecosystem to address adaptation challenges such as drought, floods, and limited financial access for women, MSMEs, and smallholder farmers.

The project operates through three components: (i) Startup Acceleration—supporting six fintech startups with tailored venture-building services and gender inclusion goals; (ii) Ecosystem Strengthening—expanding investor networks, talent, and partnerships; and (iii) Monitoring, Learning, and Adaptation—building evidence and tools for venture tracking and ecosystem engagement. By mid-2025, the project had mobilized USD 3.3 million in follow-on investment, reached over 50,000 individuals (45% women), and placed 11 junior experts to build the adaptation talent pipeline. The initiative demonstrates how fintech can serve as a catalytic mechanism for climate resilience and inclusive growth across Africa.

## Evaluation Purpose

In line with the GEF Terminal Evaluation Guidelines (2023) and UNIDO’s Evaluation Policy (2021), this evaluation also contributes to institutional learning, transparency, and decision-making at both the project and portfolio levels. Findings and recommendations will inform UNIDO’s digital innovation and workstream and provide inputs for GEF Council reporting. GEF Terminal Evaluation guidance also requires a comprehensive assessment of performance, factors affecting performance, implementation, and monitoring and evaluation (M&E) to support learning, accountability, and decision-making; these 2023 guidelines are effective 1 January 2024. UNIDO’s Evaluation Manual sets out institutional processes: Terms of Reference (ToR), preparation and clearance of an Inception Report, conduct of interviews, draft and final reports, and quality assurance by the Evaluation Office.

## Evaluation Objectives and Scope

Building on this purpose, the evaluation has the following objectives, structured by the GEF/UNIDO criteria and anchored in the project logframe and IRPF indicators:

- Relevance: Assess alignment of project objectives with national adaptation priorities (e.g., NDCs, NCCAPs, Green Growth strategies), UNIDO’s mandate, and GEF-7 Climate Change Focal Area strategies. Linked logframe outcome: 1.1 Startups accelerated with gender thresholds.

- Coherence: Evaluate coordination with national, regional, and international initiatives in digital finance, adaption, and gender; and synergies with other UNIDO/UN projects. Linked logframe output: 2.1 Ecosystem strengthening activities.

- Effectiveness: Measure achievement of planned results against logframe/IRPF targets:

  - ≥6 startups accelerated (≥30% women-led, ≥50% with women in leadership, ≥20% targeting women).

  - 2 investment briefs, ≥10 investors engaged, ≥10 junior experts placed (≥50% women), ≥9 blogs and learning products.

  - ≥20,000 direct beneficiaries (≥50% women); ~1,600 ha under climate-resilient management.

- Efficiency: Review timeliness, budget execution, and cost-effectiveness; assess management arraignment between UNIDO, BFA Global, and National Stakeholders; and evaluation implications of the no-cost extension). Linked logframe component: annual work plans and budgets, financial co-financing targets.

- Sustainability: Analyze the likelihood of the continued benefits post-closure, considering financial viability of startups, investor appetite, and regulatory support. Assess risks noted in the project risk register (startup survival, policy shifts, and macroeconomic shocks.

- Impact/Catalytic Effects: Explore evidence of contributions to the broader resilience outcomes (households, MSMEs, ecosystems), and catalytic effects such as investor crowd-in or replication of business models. Linked IRPF indicators: beneficiaries reached, land area management, policies/plans supported.

Scope of the Evaluation

- Thematic: Startup accelerations, ecosystem strengthening, gender inclusion, MEL, and safeguards (logframe Components 1-3).

- Geographic: Five participating countries (Kenya, Nigeria, Rwanda, South Africa, Uganda). At least three will be directly represented in interviews; others covered through documentation.

- Temporal: Project design (CEO Endorsement, Nov 2022) through implementation (Apr 2023-Apr 2025) and the no-cost extension to Sept 2025.

- Financial: GEF resources USD 945,250; co-financing pledged USD 10 million, with approximately USD 12.2 million mobilized during the design phase.

## Theory of Change

The Acceleration of Fintech Technology-Enables Climate Resilience Solutions project was designed with a simple but ambitious premise:

If startups receive tailored venture-building support, if ecosystems are strengthened through investor briefs, talent pipelines, and knowledge products, and if learning is captured and shared, then startups will expand climate resilience solutions to underserved communities (see Reconstructed ToC in Annex 11).

By targeting fintech specifically, the project sought to build on Africa’s strong digital finance ecosystem and redirect it towards climate resilience outcomes.

At the input stage, the project brought together modest GEF funding, significant co-financing commitments, and the technical capacity of UNIDO and BFA Global. These resources were expected to flow into three main activity streams: (i) the acceleration of at least six fintech startups across Kenya, Nigeria, Rwanda, South Africa, and Uganda; (ii) ecosystem-building through investor briefs, global events, knowledge products, and the placement of junior experts; and (iii) monitoring and learning activities to track progress and capture lessons. Gender mainstreaming and safeguards were intended to be cross-cutting, with thresholds for women’s participation built into startup selection and a Category C environmental and social risk rating applied to guide implementation.

Several assumptions underpinned the project’s change pathway. These included assumptions that startups would survive and scale beyond the life of the project, that investors would act on the evidence generated, and that governments would maintain a regulatory environment conducive to fintech innovation. An equally important assumption was that gender and safeguards would be integrated into day-to-day decision-making, rather than remaining aspirational. The evaluation tested these assumptions explicitly, examining not only whether outputs were delivered, but also whether the causal logic held true in practice, and whether reported overshoots in beneficiaries and hectares reflect durable change or potential overestimation.

# Methodology

## Evaluation Approach

The evaluation applied a mixed-methods approach, integrating quantitative and qualitative evidence to address the evaluation questions set out in the matrix (see Annex 3).  The approach was utilization-focused, geared to the needs of UNIDO, BFA Global, the GEF Secretariat, and national counterparts, and participatory, incorporating stakeholder perspectives where feasible within the constraints of time and resources.

The methodology was aligned with the GEF Terminal Evaluation Guidelines (2023), ensuring coverage of the mandatory criteria, rating scales, and cross-cutting priorities, and with UNIDO’s Evaluation Policy (2021) and Evaluation Manual (2024), emphasising impartiality, evidence-based analysis, gender responsiveness, and inclusion of marginalized voices. Ethical standards were applied in line with United Nations Evaluation Group (UNEG) Ethical Guidelines and GDPR-equivalent data protection practices.

The evaluation matrix ensures that each criterion is accompanied by specific questions, measurable indicators, and clearly identified data sources (e.g., project documents, financial reports, PIRs, BFA Global reports, stakeholder interviews). Evidence will be triangulated using document review, 10-15 semi-structured interviews in total, and verification of monitoring data. This structured approach ensures that the evaluation addresses both accountability (achievement of results, compliance with GEF/UNIDO requirements) and learning (drivers of success, lessons for replication under GEF-9).

A rating scale of 1-6 is used for each criterion: Highly Satisfactory, Satisfactory, Moderately Satisfactory, Moderately Unsatisfactory, Unsatisfactory, Highly Unsatisfactory, and Unable to Assess.

In addition to the six OECD/DAC evaluation criteria (Relevance, Coherence, Effectiveness, Efficiency, Sustainability, and Impact), the evaluation also assessed two mandatory GEF-specific criteria:

- Quality of Implementation (by UNIDO): Assessing whether UNIDO’s management, oversight, and support functions were adequate and responsive.

- Quality of Execution (by BFA Global): Assessing whether BFA Global effectively delivered activities as planned, with adaptive management and stakeholder engagement.

M&E Design and Implementation

The evaluation assessed both the design and implementation of monitoring and evaluation systems. Design was judged on whether indicators were well-defined, measurable, and gender-responsive at entry. Implementation was judged on whether the M&E system was used effectively during execution, including the quality of reporting through the Visible platform.

Sustainability Sub-dimensions

Sustainability was analyzed along four standard GEF sub-dimensions: (i) financial sustainability, (ii) sociopolitical sustainability, (iii) institutional framework and governance, and (iv) environmental sustainability. Sustainability is assessed using a four-point scale: Likely (L), Moderately Likely (ML), Moderately Unlikely (MU), and Unlikely (U).

Geographic Scope and Temporal Scope

The focus countries are Kenya, Nigeria, Rwanda, South Africa, and Uganda. While the activities were implemented in all five countries, the evaluation adopted a sampling approach for stakeholder interviews, given the limited allocation of 10-15 interviews in total.

The evaluation assessed the project from each of its phases, including:

- Design phase: Beginning with the CEO Endorsement (November 2022) and the project approvals/compliance clearances (2022-2023).

- Implementation phase: From the start of activities in April 2023 through the inception period (May-June 2023), the first PSC meeting (May 2023), and subsequent annual work plans and PIRs.

- Extension period: Activities extended into 2025 following the no-cost extensions request, including final venture-building and ecosystem outputs.

- Completion: Scheduled for 30 September 2025, with this evaluation covering the period up to and including closure and reporting.

## Exclusions from Scope

The evaluation did not attempt to attribute long-term climate resilience impacts (e.g., household- or community-level reductions in vulnerability to drought) beyond evidence available from project monitoring and startup reporting. It also did not assess activities outside the formally approved project framework, including:

- Catalyst Fund / JPMorgan Chase Foundation (JPMC) advisory activities: parallel initiatives supported by JPMC that produced learning products, roundtables, and ecosystem events under Catalyst Fund. While these may have complemented the project’s objectives, they were not financed under GEF ID 10927 and therefore fall outside the evaluation scope.

- Other unrelated BFA Global initiatives not linked to the GEF/UNIDO MSP.

- Primary quantitative surveys of end-users or beneficiaries, which were not feasible within the evaluation resources or timeframe.

Instead, the evaluation relied on project data, secondary sources, and triangulation with interviews to assess results.

## Data Collection

Data collection combined a structured document review with semi-structured interviews, sequenced in a way that ensured the evaluation built progressively from evidence already available to targeted stakeholder consultations. The evaluator prepared a data collection plan during the inception phase. This included:

- Mapping evidence sources against each evaluation question in the evaluation matrix (Annex 3).

- Sequencing activities so that the document review was completed first, allowing preliminary findings and identified inconsistencies (e.g., number of startups accelerated, gender thresholds, beneficiary totals) to shape interview questions.

- Scheduling interviews in consultation with UNIDO and BFA Global, ensuring balanced representation across stakeholder groups within the limited allocation of 10-15 total interviews.

- Adapting instruments: stakeholder-specific interview guides were prepared (Annex 7), with prompts linked directly to the evaluation criteria.

This planning ensured that data collection remained feasible within the evaluation timeframe (August–September 2025) while covering all mandatory perspectives.

## Document Review

The evaluator systematically reviewed:

- Core project documentation: CEO Endorsement, Compliance Checklist, Results Framework, PSC minutes, work plans, learning agenda, risk register, PIRs (2023-2025), financial reports.

- Knowledge products: blogs, investment briefs, event reports, impact videos.

- UNIDO/GEF Guidance: evaluation guidelines, policies, and reporting templates.

- National policy documents: climate strategies, fintech/digital finance regulations, and adaptation frameworks relevant to the five participating countries.

A complete list of the documents reviewed can be found in Annex 4 with a summary of each document.

## Semi-Structured Interviews

A total of 11 semi-structured interviews were conducted with stakeholders strategically sampled to cover most mandatory perspectives:

- UNIDO HQ: Project Manager, Director, Head of CTI, Project Assistant, and Associate Industrial Expert.

- Executing Partners (BFA Global): Project Manager; M&E Lead.

- Startups: 5, including at least one women-led or gender-focused startup.

- Junior Experts Beneficiaries: One junior intern and one end-user proxy.

- Cross-cutting informants: e.g., employees of the startups.

- Investor Interview with KawiSafi.

Interviews followed tailored stakeholder guides linked to the evaluation criteria (Annex 7). This sampling strategy meant to balance coverage of institutional, government, private sector, and beneficiary perspectives, prioritized gender representation, and balanced breadth (regional scope) with depth (targeted interviews), while remaining feasible within available resources and the evaluation timeline. Unfortunately, government focal points and end users did not respond to interview requests.

## Triangulation

In this evaluation, triangulation was implemented in three main ways:

Data Source Triangulation: Information from multiple sources of evidence was compared including project documentation (e.g., Results Framework, PIRs, financials), stakeholder interviews, and monitoring data reported by BFA Global and startups. For example, reported beneficiary numbers were checked against startup progress reports, PIR narratives, and interview testimony.

Stakeholder Triangulation: Perspectives were gathered from a balanced sample of actors including UNIDO HQ, BFA Global, government focal points, startups, investors, junior experts, and beneficiaries. This approach ensured that findings reflect multiple viewpoints, particularly where inconsistencies exist in reporting (e.g., the number of startups accelerated or gender thresholds achieved).

Methodological Triangulation: Both qualitative and quantitative methods were used. Qualitative insights from semi-structured interviews were validated against quantitative monitoring indicators (e.g., hectares managed, number of investors engaged). This methodological triangulation will allow the evaluation to test whether reported results are both plausible and sustained.

## Financial Analysis and Co-financing Verification

The evaluation included a financial analysis to assess efficiency and value-for-money. This analysis reviewed planned versus actual expenditures, cost per output, and the relative allocation of resources across components, using financial reports, project accounts, and evidence from partners. As part of this analysis, the evaluation also conducted mandatory co-financing verification, in line with GEF requirements. Endorsed co-financing commitments were compared with actual contributions at the terminal stage, disaggregated by cash versus in-kind. Verification prioritized documented evidence (e.g., signed letters of commitment, contracts, audited financial statements) over self-reporting. This enabled an assessment of whether co-financing materialized as planned and whether financial risks were adequately managed.

## Limitations

This Terminal Evaluation faced several limitations that may affect the confidence of findings and ratings. These are presented transparently in line with UNEG and UNIDO requirements, together with the mitigation measures applied:

- Stakeholder coverage:  Due to time and resource constraints, only a limited number of interviews (11) could be conducted. While all six startups, junior experts, and project partners were consulted, not all national government focal points or wider ecosystem actors could be reached.

Mitigation: Triangulation was applied by cross-checking interview responses with project reports, PIRs, PSC minutes, and BFA’s final report to ensure balance.

- Attribution vs. contribution: Given the multiple co-financing sources and overlapping ecosystem initiatives (e.g., GSMA, WFP pilots), it was not possible to attribute outcomes exclusively to the GEF-funded project.

Mitigation: The evaluation applied a contribution analysis approach, situating the project’s role within broader ecosystem dynamics rather than claiming sole attribution.

- Data consistency: Discrepancies exist across project documents (e.g., five vs. six startups, gender targets, beneficiary figures). These discrepancies were treated as lines of inquiry in the evaluation and triangulated with evidence from BFA Global, UNIDO, and PIRs.

Mitigation: These discrepancies were treated as evaluation questions. Data were cross-checked against startup self-reports, PIRs, BFA Global’s final report, and independent sources where available. Where full verification was not possible, findings are reported cautiously and limitations noted.

- Time constraints: The data collection phase was conducted during a period of less than two months (August-September 2025), requiring prioritization of key questions and efficient synthesis of evidence to meet restrictive deadlines.

- Potential bias: As startup founders and BFA Global had vested interests in positive reporting, there was a risk of self-promotion bias. Similarly, junior experts may have emphasized benefits due to career prospects.

Mitigation: Confidentiality and anonymity were assured to encourage candid responses. Divergent and dissenting views were documented, and findings were cross-validated with independent observers (e.g., investor feedback, PSC discussions).

## Ethics and Data Protection

This Terminal Evaluation was conducted in full compliance with the UNEG Ethical Guidelines (2020) and UNIDO Evaluation Policy (2021), applying GDPR-equivalent safeguards for personal data.

- Independence and impartiality: The evaluation was managed by an independent consultant contracted through UNIDO’s Climate Technology Innovation (CTI) Unit. The evaluator operated fully independent of project management and implementation entities (UNIDO technical divisions, BFA Global, and country partners). Neither project staff nor management influenced the design, data collection, analysis, or reporting of the evaluation. To ensure impartiality, the evaluator disclosed and managed potential conflicts of interest in line with UNIDO policy; no conflicts were identified.

- Ethical safeguards: All interviewees and survey participants provided informed consent prior to participation. Participation was voluntary, and respondents could withdraw at any time without consequence. Interviews were conducted confidentially; responses were anonymized in the report to avoid attribution to individuals without explicit consent. Personal and organizational data were handled under GDPR-equivalent standards and securely stored.

- Data protection and integrity: All raw data (interview notes, documents, and quantitative data) were stored in password-protected files accessible only to the evaluator. Identifiable information was excluded from public deliverables, and only aggregated findings are presented.

- Respect for stakeholder perspectives: The evaluation sought a balance of perspectives across stakeholder groups (startups, investors, junior experts, government representatives, UNIDO HQ, and BFA Global). Particular attention was given to capturing voices that may be less represented in formal reports, such as junior experts and government focal points who had limited engagement with the project.

- Handling of dissenting views: Where stakeholders expressed diverging opinions, for example, differing assessments of government engagement or the value-for-money of certain technical assistance services, these perspectives were documented and integrated into the analysis. The report reflects both converging and dissenting views to provide a balanced, evidence-based account in line with UNIDO’s requirement for impartiality.

- Methodological transparency: The evaluation design, data sources, and methods (document review, semi-structured interviews, triangulation of evidence) are clearly described in the methodology section. Limitations (e.g., reliance on self-reported startup data for beneficiary counts and hectares managed) are disclosed transparently to avoid overstatement of results.

# Project Background and Context

Map 1. Locations of fintech–climate startups supported by the UNIDO GEF project (GEF ID: 10927)

Locations of fintech–climate startups supported by the UNIDO GEF project (GEF ID: 10927). Source: UNIDO (2025). Visualization: Author’s original work.

The five countries targeted by the project–Kenya, Nigeria, Rwanda, South Africa, and Uganda–share a heightened vulnerability to climate change, though their institutional and policy responses vary. Each has adopted national strategies or legislation that commit to adaptation priorities under the UNFCCC, Paris Agreement, and the SDG 13. These frameworks provide the baseline condition and performance indicators against which this Terminal Evaluation will assess the project’s relevance, alignment, and contributions. The five participating countries face distinct interconnected climate hazards and adaption of gaps:

Kenya

Kenya faces recurrent droughts, water scarcity, and erratic rainfall that threaten agriculture, which contributes one-third of GDP and employs most of the rural population. The National Climate Change Action Plan (2018–2022) and Vision 2030 prioritize adaptation in agriculture, water, and energy. While Kenya leads Africa in digital finance (e.g., M-Pesa), climate-focused fintech remains nascent and largely commercially oriented. Key institutions include the Ministry of Environment and Forestry, Central Bank of Kenya, and local accelerators such as Nailab. Target groups comprise smallholder farmers, women-led agribusinesses, and MSMEs exposed to drought and market volatility.

Nigeria

Nigeria faces intensifying desertification, flooding, and resource stress across its agriculture and energy sectors. The National Climate Change Policy (2021–2030) emphasizes resilience in agriculture, water, and disaster risk reduction. Despite a vibrant fintech sector, adaptation-oriented finance is scarce, and rural women and MSMEs struggle to access credit. Major stakeholders include the Federal Ministry of Environment, National Climate Change Council, Central Bank of Nigeria, and accelerators like CcHub. Target groups include smallholders, women entrepreneurs, and MSMEs requiring climate-resilient financing solutions.

Rwanda

Rwanda’s Green Growth and Climate Resilience Strategy (2022) prioritizes climate-smart agriculture, sustainable land use, and water resource management in response to land degradation and water scarcity. Government support for ICT innovation (e.g., Kigali Innovation City) has fostered entrepreneurship, though climate-focused fintech remains underdeveloped. Key institutions include the Ministry of Environment, FONERWA, and the National Bank of Rwanda. Target groups include women and youth farmers, agricultural cooperatives, and MSMEs active in waste management and agri-value chains.

South Africa

South Africa’s National Climate Change Adaptation Strategy (2019) outlines priorities in agriculture, water, health, biodiversity, and infrastructure amid rising temperatures, drought, and shifting climate zones. The country’s mature financial system and fintech ecosystem are underutilized for adaptation finance. Principal actors include the Department of Forestry, Fisheries, and the Environment, National Treasury, and innovation hubs such as mLab and Savant. Target beneficiaries are rural MSMEs, women in agriculture, and households in drought-prone provinces.

Uganda

Uganda’s National Climate Change Policy (2015) and Climate Change Act (2021) frame adaptation as a pillar of Vision 2040. The country faces declining rainfall reliability, glacial retreat in the Rwenzori Mountains, and frequent floods and droughts. Despite rapid mobile-money growth, adaptation-linked finance remains scarce and rural credit access limited. Stakeholders include the Ministry of Water and Environment, Climate Change Department, Bank of Uganda, and Innovation Village accelerator. Target groups include subsistence farmers, rural women entrepreneurs, and MSMEs vulnerable to climate shocks.

## Startup Selection and Overview

Table 2 below showcases a summary of the six startups selected by the Catalyst Fund in the Acceleration of Fintech-Enabled Climate Resilience Solutions project, followed by an overview of selection rationales and context.

Selection Rational & Context

Startup selection followed a structured multi-step process. From over 200 candidates sourced through BFA Global’s Catalyst Fund portfolio, co-investor pipelines, and nominations from national focal points, a shortlist of 20 firms was evaluated against criteria on climate adaptation relevance, business maturity, and geographic diversity. Six startups were ultimately selected for acceleration, two of which (AgroSupply and FarmToFeed) were already part of the Catalyst Fund portfolio, ensuring continuity and rapid mobilization.

The portfolio balances early-stage innovators (e.g., Farmz2U, ISARO Econext) with more mature ventures (AgroSupply, The Awareness Company) spanning diverse climates and regulatory settings. Each startup addresses a distinct national adaptation challenge, from access to agricultural finance in Uganda to waste management in Rwanda and supply-chain efficiency in Nigeria, while demonstrating credible market traction and public visibility. Their proven models and existing investor backing positioned the cohort as both technically sound and investment-ready.

Integration with Project Goals

The selected startups align closely with the project’s objective to accelerate fintech-enabled climate resilience by combining digital tools, financial innovation, and environmental impact. Their models span diverse adaptation pathways—from AgroSupply’s mobile layaway system for smallholders to Envocare’s circular-economy recycling platform, demonstrating how fintech can address both climate and livelihood challenges. The portfolio also integrates a gender dimension, with several women-led or co-founded ventures and business models that explicitly target women farmers and vulnerable smallholders, such as AgroSupply and FarmToFeed. This diversity in business models allowed the project to test multiple approaches, market access, input finance, data and AI services, and waste upcycling, thereby strengthening both the results achieved and the learning value for future adaptation-focused innovation programs.

# Findings

The Terminal Evaluation assessed project performance against the approved logframe, GEF core indicators, and OECD-DAC criteria of relevance, coherence, effectiveness, efficiency, and sustainability, with cross-cutting attention to gender and monitoring, evaluation, and learning (MEL). Most output and outcome targets were achieved or exceeded. Six startups were accelerated (target met), USD 3.3 million in follow-on finance was mobilized (65% above target), 11 junior experts were placed (target: 10), and 10 knowledge products were produced (target: 8). Beneficiary outreach (407,127 individuals, including 169,157 women) and land under improved management (278,097 ha) substantially exceeded expectations, though largely based on self-reporting and best interpreted as contribution rather than full attribution. Policy influence fell slightly short (8 of 10 planned adoptions), reflecting limited government engagement under the Challenge Program structure. Overall, findings indicate strong enterprise- and market-level results, solid operational performance, and valuable lessons for integrating verification, government engagement, and systemic change in future GEF programming.

Table 2. Summary of Project Startups Selected

| Name | Country | What They Do | Business Model/Key Innovation | Founder(s) | Founded | Scale & Public Profile |
| --- | --- | --- | --- | --- | --- | --- |
| AgroSupply | Uganda | Provides smallholder farmers access to inputs (seeds, fertilizer) via savings/layaway rather than credit. | Mobile layaway / savings platform; input financing & distribution, reducing reliance on traditional credit. | Joseph Ogwal, Founder & CEO | 2017 | Worked with over 5,000 farmers historically via a bankless savings program. Public profile includes Acumen Foundry, IKEA Social Entrepreneurship, and many smallholder testimonials. |
| FarmToFeed | Kenya | Reduces food loss by aggregating surplus or imperfect produce and delivering to businesses; provides data/insights on loss. | Digital marketplace and logistics plus data analytics for food loss; matches supply of imperfect produce with demand | Claire van Enk, Anouk Boertien, Zara Benosa | 2021 | Backed by GSMA & DRK; media coverage (TechCrunch etc.); growing customer base and business contracts. |
| Farmz2U | Nigeria/ Kenya | Software & advisory tools to improve planning and connect producers to markets. | Digital tools + supply-chain advisory; helps coordinate production & market access. | Aisha Raheem, Co-founder and CEO | 2023 | Operating in both Nigeria & Kenya; recognized by ripple/investor groups; growing usage among smallholder farmers & buyers. |
| Envocare | Rwanda | Converts agricultural & municipal waste into biochar fertilizers & eco-cooking fuels. | Circular waste-to-resource value chain; using waste feedstocks + carbon/environmental product development. | Mahlon Kyomuhendo & Skyaka Francis | 2024 | Public profile: large number of farmers impacted, tonnage of waste upcycled; contributions to soil health & fuel substitution. |
| ISARO Econext | Rwanda | Circular economy & greentech initiatives including reforestation, ecosystem restoration, and climate action platforms. | Products like EcoForest; work on tree-planting, restored area impacts; may include digital monitoring tools. | Gasaro N. Kristian | 2019 | Active in climate action forums; some measurement of restored area; seen as a key actor in Rwanda's emerging climate tech space. |
| The Awareness Company | South Africa | Provides real-world data/AI insights across sustainability & operations (water, agriculture, wildlife etc.). | HYDRA data/AI platform; combines operation data + environmental/sustainability security insights. | Priaash Ramadeen, Estelle Lubbe, Shazia Vawda | (Not listed) | Recently raised ~USD 1.6M seed (January 2025); visible in the impact / startup press; growing revenue & usage metrics. |

## Relevance

The project was rated Highly Satisfactory for its strong alignment with national adaptation priorities, the GEF-7 strategy, and UNIDO’s mandate for private-sector-led resilience. It addressed critical adaptation needs in agriculture, forestry, waste management, and data services across Kenya, Nigeria, Rwanda, South Africa, and Uganda, positioning adaptation as an investable domain and filling a clear market gap for tailored venture acceleration. The design effectively responded to enterprise-level constraints—such as access to finance, market entry, and impact measurement—while integrating gender considerations through targeted support to women-led startups and business models serving women farmers and other vulnerable groups.

In each case, it supported commitments made in their NDCs and related national frameworks:

Kenya: The Climate Change Act (2016) and National Adaptation Plan (2015–2030) emphasize mobilizing climate finance, strengthening resilience in agriculture, and leveraging private-sector innovation. The project’s support to startups such as FarmToFeed directly advanced these priorities by reducing food loss and enabling climate-smart markets.

Nigeria: The National Adaptation Communication (2021) and the National Climate Change Policy (2021–2030) identify agriculture, forestry, and energy as critical adaptation areas. Farmz2U’s supply chain software and other fintech-enabled solutions aligned with Nigeria’s call for digital tools to strengthen food security and resilience.

Rwanda: The Green Growth and Climate Resilience Strategy (2011) and subsequent National Adaptation Plan (2019) highlight waste management, sustainable land use, and private finance as key adaptation pathways. Startups such as Envocare (biochar, recycling) and ISARO Econext (reforestation, green tech) directly contributed to these national priorities.

Uganda: The National Climate Change Policy (2015) and Uganda’s NDC (2022 update) call for mainstreaming adaptation into agriculture and mobilizing non-state actors. AgroSupply’s digital layaway platform, which expanded to over 30,000 farmers, supported Uganda’s goals of improving food security and empowering vulnerable groups, especially women.

South Africa: The National Climate Change Adaptation Strategy (2019) emphasizes ecosystem-based adaptation, private sector mobilization, and digital innovation. The Awareness Company’s HYDRA data platform contributed to these objectives by generating insights for water, agriculture, and biodiversity resilience. Beyond alignment with individual country strategies, the project contributed to regional and global policy dialogues by producing two flagship knowledge products: the State of Climate Tech Africa 2023 report and the Catalyzing Climate Adaptation through Fintech brief. These outputs facilitated ecosystem development by providing governments and investors with evidence on the viability of adaptation as an investable sector.

Table 3. Results Against Logframe/IRRF Indicators

| Indicator | Target | Actual (at TE) | Variance (%) | Attribution vs. Contribution | Gender Disaggregate | Evidence Source |
| --- | --- | --- | --- | --- | --- | --- |
| Startups accelerated (#) | 6 | 6 | 0% | Fully attributable - all 6 received tailored venture building | 3 women-led (50%) | PIR 2025; BFA portfolio records |
| Follow-on finance mobilised (USD) | 2,000,000 | 3,300,000 | +65% | Contribution - mobilized through project-facilitated introductions and co-investor confidence | Not applicable | Investor Circle records; startup fundraising reports |
| Junior experts placed (#) | 10 | 11 | +10% | Fully attributable - placements arranged and financed by the project | 5 women (45%) | PIR 2025; Metrics Tracker |
| Knowledge products produced (#) | 8 | 10 | +38% | Fully attributable - outputs financed and published by the project | Not applicable | Metrics Tracker; Knowledge Product Annex |
| Direct beneficiaries (# individuals) | 20,000 | 50,844 | +154% | Contribution - self-reported by startups, facilitated through venture support but not fully attributable | 45,794 women (29.5%) | Metrics Tracker, Startup reports. |
| Hectares under improved management (ha) | 1,600 | 126,050 | +7,778.13% | Contribution - self-reported, not independently verified, project enabled but not solely responsible | Not disaggregated | PIR 2025; Metrics Tracker |
| Policies/plans influenced # | 10 | 8 (reported) | -20% | Contribution only – figure drawn from PIR 2024–2025, which cite knowledge products and convenings as inputs. | Not applicable | PIR 2024–2025 narrative sections; knowledge product list |

## Coherence

The project was rated Satisfactory for coherence. It demonstrated strong complementarity with international initiatives on climate innovation and fintech, effectively filling a niche not addressed by other accelerators. The Catalyst Fund’s embedded venture-building model offered a differentiated and complementary approach alongside programs such as GSMA’s agritech initiatives and WFP’s food security pilots. Startups and investors confirmed that the project avoided duplication and expanded the pipeline of investable adaptation ventures, broadening beyond clean energy into food systems, forestry, and waste management.

Externally, the project complemented regional accelerator and donor efforts through deeper, tailored venture-building and active investor network engagement. However, coherence with national policy frameworks was constrained by the GEF Challenge Program’s pre-selection design, which did not include government co-design or direct funding to national counterparts. As a result, engagement with policy actors, though pursued through PSC meetings, COP events, and webinars, was intermittent, limiting systemic alignment with government-led adaptation and digital finance strategies. Governance mechanisms such as the Project Steering Committee (PSC) and Investor Advisory Council (IAC) functioned effectively but had modest influence on policy linkages.

Internally, coherence within UNIDO’s portfolio was strong. The project’s emphasis on digital innovation, SME support, and gender-responsive business models aligned with UNIDO’s Inclusive and Sustainable Industrial Development (ISID) strategy and emerging digital innovation agenda. By supporting early-stage enterprises and inclusive business models, the project reinforced UNIDO’s mandate and positioned fintech-enabled adaptation as a credible and scalable domain for future programming.

## Effectiveness

Table 4. Knowledge Products and Communication Outputs

| Publication | Outlet | Type | Publish Date | Period Reported |
| --- | --- | --- | --- | --- |
| Beyond targets: the Catalyst Fund’s multipronged approach to empowering women for climate resilience | Website | Blog | 18 Oct 2023 | Y1 |
| Why we invest in climate resilience and adaptation in Africa | Website | Blog | 6 Nov 2023 | Y1 |
| Investing in Climate Tech Innovation in Africa | Website | Report | 11 Dec 2023 | Y1 |
| Catalyst Fund and Africa: The Big Deal partner to assess the State of Climate Tech in Africa | Website | Blog | 11 Dec 2023 | Y1 |
| FarmToFeed Impact Video | CF Youtube Channel | Video | 8 Jan 2024 | Y1 |
| Africa is poised to become the future of carbon supply | Website | Blog | 15 Jan 2024 | Y1 |
| Farmz2U is transforming food systems in Africa to build resilience to climate change | Website | Blog | 12 Feb 2024 | Y1 |
| We tried using GenAI to screen pitch decks, here is how it went | Website | Blog | 20 Feb 2024 | Y1 |
| From Waste to Resources: Envocare’s Biochar and Biofuel products building resilience for Rwanda’s Rural dwellers | Website | Blog | 13 Jun 2025 | Y2 |
| Isaro Econext: Harnessing Data-Driven Afforestation for a Greener, Resilient Africa | Website | Blog | 13 June 2025 | Y2 |
| AgroSupply Impact Video | CF Youtube Channel | Video | 3 Dec 2024 | Y2 |
| Envocare Impact Video | CF Youtube Channel | Video | 5 Jun 2025 | Y2 |
| Isaro Econext Impact Video | CF Youtube Channel | Video | 5 Jun 2025 | Y2 |
| From Inputs to Markets: How Agro Supply’s Factory Is Unlocking New Opportunities for Ugandan Smallholders | Website | Blog | 10 Jul 2025 | Y2 |
| The Awareness Company Impact Video | CF Youtube Channel | Video | Sept 2025 | Y2 |
| Innovating and Investing at the Gender-Climate Nexus in Africa | Website | Report | October 2025 | Y2 |

The project was rated Satisfactory for effectiveness. It achieved or exceeded most planned outputs and outcomes as outlined in the Results Framework. Six startups were successfully accelerated, including three women-led ventures, surpassing the gender threshold. Over USD 3.3 million in follow-on investment was mobilized, 11 junior experts were placed (36% women), and 10 knowledge products were produced and disseminated, including the State of Climate Tech Africa 2023 report and a gender brief. The project also gained visibility through events such as COP28 and the Founders and Funders Retreat, elevating adaptation as an investable sector.

Startups demonstrated tangible business growth, enhanced investor readiness, and stronger impact monitoring. FarmToFeed expanded to 6,000 farmers and raised USD 1.9 million; AgroSupply reached 31,000 farmers, increased revenues by USD 3 million, and integrated sustainable land management practices; Envocare secured USD 770,000 in combined grants and contracts; Isaro Econext grew its reforestation pipeline to over 40,000 trees; and The Awareness Company increased monthly recurring revenue by 16 percent.

Effectiveness was driven by BFA Global’s embedded venture-building model, which startups consistently identified as the project’s most valuable feature. Investor matchmaking and targeted mentorship further enhanced growth and credibility. However, effectiveness was moderated by uneven fintech integration across some business models, limited government engagement under the Challenge Program structure, and the capital-intensive nature of agriculture and recycling sectors, which constrained scaling despite strong technical performance.

## Efficiency

Table 5. Project Costs and Outputs by Component

| Component | Planned Budget (USD) | Actual Expenditure (USD) | Budget Variance (%) | Key Outputs Delivered | Unit Cost Indicator |
| --- | --- | --- | --- | --- | --- |
| Component 1: Accelerating Fintech Innovation | 494,250 | 530,068 | +7% | Six startups accelerated; 2,000+ hours of venture support; USD 3.3M in follow-on investment mobilized | ≈ USD 88,300/startup |
| Component 2: Strengthening Ecosystem | 212,100 | 201,260 | –5% | Circle of Investors (200+ members); 10 knowledge products; 3 webinars; COP28 side event | ≈ USD 18,300/output/event |
| Project Management Costs | 77,690 | 105,762 | +36% | 3 PSC meetings; reporting; coordination with BFA Global and startups | n/a |
| Expenses (Travel & Other) | 51,200 | 17,179 | –67% | Limited travel due to virtual delivery and cost controls | n/a |
| Total | 835,240 | 854,269 | +2% | Majority of outputs delivered or exceeded targets | ≈ USD 142,400/startup (total project cost basis) |

Efficiency was rated Moderately Satisfactory because the project delivered most outputs on time and within budget, demonstrating sound financial management and adaptive implementation, though delivery costs were relatively higher per startup which resulted in project management expenses exceeding initial estimates. The approved GEF budget of USD 835,240 was 102 percent executed, with total expenditure of USD 854,269 by project close. After a slow start in Year 1—when only 50 percent of the budget had been disbursed—expenditure accelerated in Year 2 as venture-building intensified and no-cost extension funds were effectively deployed. Component 1, Accelerating Fintech Innovation, accounted for 62 percent of total spending (USD 530,068) and achieved six successful accelerations, at an indicative cost of USD 88,000 per startup, consistent with comparable fintech accelerators. Component 2, Strengthening Ecosystems, executed 95 percent of its allocation, financing 10 knowledge products, investor convenings, and the Circle of Investors. Underspending in travel (–67 percent) reflected efficiencies from virtual delivery, while overspending in project management (+36 percent) resulted from extended coordination and reporting during the final implementation period. Overall, the project’s full budget utilization, timely output delivery, and effective cost reallocation support a Moderately Satisfactory rating for efficiency.

Time management

The project was delivered broadly on schedule, though a no-cost extension was required to complete activities. The extension was justified by the delivery of additional outputs, including new contracts and partnerships secured by startups. Budget execution in Year 1 reflected a deliberate underspend, with resources carried forward to Year 2 for startup disbursement and communications. This is shown in Table 5 above. Budget execution shows that half of the Year 1 budget remained unspent, primarily due to delayed startup disbursements and limited travel, with funds reprogrammed to Year 2. At the proponent level, expenditures closely tracked budgets for ecosystem-building and project management, while travel was significantly underspent.

Startups were onboarded and supported within the planned timeframe, and junior expert placements were initiated without major delays. Knowledge products, including the State of Climate Tech Africa 2023 report, were completed as planned. Minor delays were noted in investor convenings, linked to COP scheduling and travel constraints; these were mitigated by substituting with virtual events. While delivery was timely overall, investor outreach would have benefited from a more structured and sequenced campaign approach (e.g., scheduled roadshows or deal rooms) rather than ad hoc convenings.

Management and implementation arrangements

Implementation arrangements between UNIDO and BFA Global were partially effective. Startups consistently valued the embedded advisor model and streamlined quarterly reporting through the Visible platform, which was delivered on schedule and reduced transaction costs. Planned acceleration activities, expert placements, and PSC meetings were completed largely as intended. However, delays occurred in the delivery of key outputs, most notably the gender report, which was submitted significantly later than planned due to BFA Global’s internal coordination. Resource allocation toward certain high-cost services (e.g., communications products) also reduced value-for-money. Investor engagement, while achieved, was more ad hoc than originally envisaged. Taken together, these factors support a rating of moderately satisfactory.

The venture-building model proved efficient compared to traditional modalities by embedding technical and strategic support directly within startups, reducing overheads and aligning assistance with operational needs. However, efficiency could have been further enhanced through catalytic financing mechanisms, such as small or recoverable grants, to address working capital gaps and accelerate scaling. Startups and investors agreed that modest catalytic capital would have improved cost-effectiveness and long-term sustainability. While resources were appropriately focused on venture-building and investor engagement, high costs for video products and ad hoc investor outreach limited overall efficiency gains.

## Sustainability

Sustainability is rated Moderately Likely because the project established credible pathways for continued benefits, through strengthened startups, investor networks, and institutionalized systems, yet key financial, policy, and verification gaps remain. Four startups mobilized USD 3.3 million in follow-on funding, and internal systems such as CRMs and KPI dashboards were retained post-project, improving operational durability. The continuation of the Circle of Investors under BFA Global’s Catalyst Fund further supports long-term investor engagement.

However, the Challenge Program’s pre-selection structure limited early government ownership, reducing prospects for policy integration and public-sector support. The junior-expert placement model lacks a financing mechanism for continuation, and scaling in agriculture and recycling remains constrained by high capital intensity and long sales cycles.

Environmentally, startups demonstrated positive contributions in reforestation, waste management, and sustainable agriculture, but reported outcomes were self-verified, with no independent validation. Although it was not a part of the initial objectives of the program, the potential environmental impacts of emerging fintech and digital tools—such as energy use and e-waste generation—remain insufficiently assessed.

## Gender Mainstreaming

Gender was integrated at multiple levels, with the project exceeding its target of 30 percent women-led startups (three out of six were women-led) and ensuring women held significant leadership roles. Startups reported tangible gender outcomes: FarmToFeed’s portfolio reached 41 percent women farmers, and AgroSupply’s mobile money layaway system reduced barriers for women to save and invest without relying on male-controlled household resources. Internships and staff hired also promoted gender balance, with several women advancing into management roles.

However, structural barriers remain unaddressed. Women still face challenges in accessing land, irrigation, and larger pools of capital, limiting their ability to scale agricultural or entrepreneurial activities. Gender mainstreaming was strongest at the portfolio and enterprise level but weaker at the systematic level, where engagement with policymakers and financiers on women’s access should be integrated into future programming.

## Performance of Partners

UNIDO

UNIDO provided effective oversight and ensured compliance with GEF requirements, particularly around project reporting, governance, and financial management. The organization convened the Project Steering Committee (PSC) and facilitated engagement with government focal points, though participation from national officials remained weak despite invitations. UNIDO’s technical backstopping was limited compared to BFA’s hands-on venture-building, but its convening role at COP and other policy fora contributed to visibility. A more proactive role in strengthening government linkages could have enhanced policy coherence and scaling opportunities. Overall, UNIDO’s performance is assessed as Satisfactory.

Global Environment Facility (GEF – Funding Partner)

The GEF provided timely financial support and consistent operational guidance throughout the project’s implementation. The GEF Secretariat’s oversight ensured compliance with adaptation focal area objectives and Gender Equality Action Plan (GEAP) requirements, particularly during project design and CEO endorsement. Communication between the GEF and UNIDO was adequate, with no major delays in fund disbursement or reporting approvals noted. However, limited direct engagement by the GEF Secretariat during implementation constrained opportunities for adaptive management feedback as the fintech acceleration model evolved. Overall, the GEF’s performance is assessed as Satisfactory, reflecting strong design-stage support and adherence to fiduciary standards, with room for deeper implementation-stage engagement.

BFA Global (Executing Partner)

BFA Global, through Catalyst Fund, delivered the venture-building model that was consistently highlighted by startups as transformative. Its embedded approach went beyond advisory support, with staff often working directly alongside startups to co-design solutions in finance, marketing, investor readiness, and impact tracking. BFA also managed the Circle of Investors, producing tangible results in mobilizing over USD 3.3 million in follow-on investment. Reporting through the Visible platform was well managed, though reliance on self-reported data without external verification was a limitation. Overall, BFA Global’s execution is assessed as Satisfactory, given its strong delivery of outputs and the high satisfaction of startups and investors.

## Results-based Management

RBM systems were partially effective. The project design included a Results Framework aligned with GEF IRPF, with clear targets for startup accelerated, investor engaged, junior experts placed, and knowledge products produced. These indicators were tracked through BFA’s Visible reporting platform, which standardized data collection and reduced reporting burdens. This represented a strong step forward compared to more fragmented approaches in similar projects.

However, limitations emerged in verification and adaptive use of data. Most indicators relied on self-reported figures from startups, with limited independent validation, raising concerns about the credibility of some results (e.g., beneficiary and hectare numbers). While BFA cross-checked submissions for consistency. Metrics were not tied to key national policies. Adaptive management was demonstrated in the decision to apply a no-cost extension, which was justified by additional outputs achieved. Nonetheless, RBM could have been strengthened through earlier integration of government and investor feedback loops, ensuring that lessons from reporting informed broader policy dialogue.

Overall, RBM is assessed as Moderately Satisfactory: effective at tracking outputs and streamlining reporting, but less robust in verification, adaptive use of data, and integration into systemic learning, but did not clearly align with National Adaptation Strategy metrics.

# Conclusions and Recommendations

## Conclusions

The project made measurable progress toward impact by demonstrating that adaptation-focused startups can mobilize private capital and deliver resilience-oriented services. Collectively, the six startups raised over USD 3.3 million in follow-on investment and reached thousands of smallholders, providing credible proof points that adaptation can be investable. While attribution remains partial and reported outreach figures require verification, the project’s catalytic effect on investor perceptions represents a meaningful step toward systemic change in adaptation finance.

Coherence was strongest with market actors and international partners. The project complemented programs such as GSMA’s agritech initiatives and WFP’s food security pilots, expanded the Circle of Investors, and strengthened the pipeline of adaptation ventures. Yet alignment with government-led adaptation and digital finance strategies remained limited under the Challenge Program’s pre-selection structure.

The project achieved or exceeded most output targets and mobilized over USD 3 million in follow-on investment. Several startups secured financing and embedded systems for continued growth. While sustainability risks persist, the project provided strong proof of concept that adaptation-focused startups can attract investment and deliver meaningful resilience outcomes.

## Recommendations and Management Response

Table 6 presents UNIDO Management’s response to the recommendations of the Terminal Evaluation of the Acceleration of Fintech-Enabled Climate Resilience Solutions Project (GEF ID: 10927).

Recommendation 1: Strengthen Government Engagement and Policy Linkages

- UNIDO and the GEF should allocate dedicated resources to ensure structured and sustained engagement with national governments and regulators in future projects. The Challenge Program’s global pre-selection model limited early government involvement; future initiatives should integrate country consultation and endorsement from the design stage.

- Operational Focal Points (OFPs) should participate in project formulation and implementation, with regular policy dialogues, co-hosted events, and progress updates aligned to national adaptation plans and digital finance strategies.

- UNIDO should leverage its convening role within the UN system to embed startup-level lessons and innovations within broader UN country frameworks and national climate-finance programs.

- Startups should be prioritized from countries that demonstrate willingness to engage in programming and translate innovation outcomes into policy and regulatory action that accelerates impact.

Management Response: Accepted. UNIDO will incorporate structured government-engagement strategies into future program design. This will include early consultations with OFPs, budgeted policy-dialogue activities, and collaboration with UN country offices to embed innovation results within national adaptation and private-sector development frameworks.

Recommendation 2: Sustain Venture-Building and Talent Support Mechanisms

- Develop cost-sharing models for junior expert placements, engaging universities, donors, and corporate partners to co-finance stipends and ensure continuity of the talent pipeline.

- Establish regional partnerships or hubs with local accelerators to extend venture-building support beyond the project cycle, maintaining access to tailored technical assistance for startups.

- Integrate startup technical assistance and mentorship activities into broader UNIDO sector and innovation programs, ensuring ongoing institutional support once GEF project funding concludes.

Management Response: Accepted. UNIDO and BFA Global acknowledged that this project served as a pilot to demonstrate that fintech-enabled adaptation is investable and can attract sustained private capital. The Catalyst Fund has since integrated this model into its core operations and will continue to support adaptation-focused startups beyond the project’s lifetime. While full cost-sharing for all placements may not be feasible, future programming will explore partnerships with regional accelerators and higher education institutions to sustain junior expert placements and embed venture-building mechanisms within country-level and institutional frameworks.

Recommendation 3: Enhance monitoring, verification, and learning

- Strengthen MEL systems by introducing third-party validation of outcome-level results (e.g., farmers reached, hectares managed) to improve data credibility.

- Standardized indicator definitions and ensure reporting is disaggregated by gender and geography.

- Established structured peer-learning platforms across startups to share lessons on business models, gender integration, and impact measurement, ensuring knowledge is captured and institutionalised.

- Future projects should incorporate independent validation mechanisms, including the use of satellite imagery, UAVs, and other digital monitoring technologies.

- Metrics should clearly align with national adaptation policies to streamline reporting and demonstrate contributions to environmental goals and objectives.

Management Response: Accepted. UNIDO will complement digital reporting platforms with third-party validation in the future projects to ensure credibility of outcome-level data. Structured cross-learning will be incorporated into program design to promote systematic knowledge-sharing and policy relevance.

Recommendation 4: Improve cost-effectiveness and investor engagement

- Cap consultancy and communications cost to ensure value-for money in technical assistance delivery.

- Structure investor engagement as a continuous process rather than ad hoc matchmaking, building pipelines in advance of demo days or events.

- Strengthen alignment with private sector networks and development finance institutions to improve scalability of startup financing.

Management Response: Accepted. UNIDO will ensure future project budgets apply stricter cost controls to technical assistance and communications. Investor engagement will be formalized as a continuous process, with early pipeline-building and structured follow-up to maximize mobilization of private capital.

Recommendation 5: Deepen gender integration and address systemic barriers

- Move beyond portfolio-level gender targets by embedding gender considerations into product design, distribution, and financing models.

- Promote gender-smart practices such as women’s leadership in startups, field-force engagement, and tailored financial products (e.g., savings mechanisms that reflect women’s cashflow patterns).

- Support policy advocacy on structural barriers such as women’s access to land, irrigation, and capital, ensuring digital finance and adaptation solutions are inclusive.

Management Response: Accepted. UNIDO will strengthen integration of gender considerations in project design and delivery. Future programming will promote gender-smart practices at enterprise level and align with broader UNIDO gender mainstreaming policies, including policy advocacy on women’s access to resources and services.

Recommendation 6: Introduce flexible catalytic financing instruments

- Complement venture-building with catalytic funding instruments (e.g., small grants, recoverable grants, blended finance) to address startups’ working capital needs.

- Design catalytic finance windows to de-risk early-stage models and bridge long funding cycles, enabling startups to better absorb technical assistance and scale.

- Integrate financing mechanisms as a budgeted component of future GEF projects alongside technical assistance.

Management Response: Accepted. UNIDO recognizes the importance of catalytic finance but notes that integration of financial instruments must be aligned with GEF policies and country-level regulations. Future projects will explore blended finance approaches and partnerships with DFIs and donors to provide catalytic capital complementary to venture-building support.

Table 6. Management Response Sheet (MRS)

| Recommendation | Management Response | Accountable Manager | Key Actions | Resources Required | Deadline | Status |
| --- | --- | --- | --- | --- | --- | --- |
| 1. Strengthen government engagement and policy linkages | Accepted | Project Manager, UNIDO | Build structured government engagement into future GEF Challenge Program designs, strengthening coordination with OFPs and UN Country Teams. | Staff time + travel budget line in project design | Q2 2026 (GEF-9 design phase) | Open |
| 2. Sustain venture-building and talent support mechanisms | Accepted | UNIDO, BFA Global | Develop cost-sharing models with universities and corporates; explore regional accelerator partnerships | Partnerships budget, HR coordination | Q4 2026 | Open |
| 3. Enhance monitoring, verification, and learning | Accepted | BFA Global | Introduce third-party validation mechanisms in next GEF cycle (spot checks, UAVs, harmonized dashboards); pilot peer-learning exchanges | MEL budget allocation | Q1 2026 | Open |
| 4. Improve cost-effectiveness and investor engagement | Accepted | Project Manager, UNIDO, BFA Global | Cap consultancy/communications costs; formalize investor engagement through deal rooms, pipelines, and structured follow-up | Project ops budget | Q3 2026 | Open |
| 5. Deepen gender integration and address systemic barriers | Accepted | Gender Focal Point, UNIDO, BFA Global | Mainstream gender-smart practices (inclusive design, leadership, field-force engagement); support policy advocacy for women’s land/finance access | Gender TA budget line + policy engagement | Q2 2026 | Open |
| 6. Introduce flexible catalytic financing instruments | Accepted | Project Manager, UNIDO, BFA Global | Explore blended finance with DFIs/donors; review feasibility under GEF rules | Partnerships | Q4 2026 | Open |

# Lessons Learned

The Terminal Evaluation of the Acceleration of Fintech-Enabled Climate Resilience Solutions Project generated several lessons of broad relevance to the design and implementation of future GEF and UNIDO interventions. These lessons reflect not only the experiences of the six supported startups but also the perspectives of investors, junior experts, and implementing partners. They highlight both what worked well, such as the value of tailored venture-building, and where greater attention is needed, including investor engagement, government linkages, and impact validation.

Lesson 1: Tailored venture-building is more effective than generic accelerators.

- Under Component 1 (Acceleration), BFA Global deployed an embedded venture-building model during 2023–2025, assigning advisors as quasi-team members within startups.

- Startups reported professionalization gains in finance, CRM, and impact measurement. For example, Agro Supply expanded to 31,000 farmers and increased revenues by USD 3 million, while ISARO grew from 400 to 2,200 farmers with a pipeline of 40–50,000 trees (PIR 2024, Metrics Tracker). By contrast, investor interviews highlighted that similar firms in generic accelerators often lacked such institutional systems.

- The embedded approach allowed advisors to tailor support to gaps (financial modelling, supply chain logistics). However, it was resource-intensive — the GEF grant covered only six firms at a cost of approximately USD 316,000/startup.

- In early-stage innovation programs, tailored and intensive support models may deliver greater long-term resilience than broad, low-touch accelerators. This principle is relevant across sectors (e.g., clean energy, water, waste) where startups face fragile markets and need internal systems to scale.

Lessons 2: Investor engagement must be structured and continuous.

- The Circle of Investors was launched under Component 2 in 2023 to mobilize private capital and build investor confidence in adaptation startups. The project mobilized USD 3.3 million in follow-on funding, exceeding targets (Metrics Tracker). However, the interviews with two startups noted that engagement was ad hoc, with startup interviewees noting momentum dissipating between the COP events and webinars. Investor participation was high during convenings but fell off afterward. In early-stage adaptation markets, continuous investor relations are as important as technical assistance for startups. Future accelerators risk losing credibility if investor engagement is episodic.

- Building credibility for early-stage enterprises in emerging sectors requires investor engagement as an ongoing process, not a one-off event. Structured pipelines of introductions and follow-ups are transferable to other UNIDO/GEF innovation programs beyond fintech.

- Produce “deal notes” highlighting how specific investors engaged in adaptation deals, what risk-return profiles they saw, and what tipped them into investing. Peer evidence often carries more weight than general claims.

Lesson 3: Junior expert placements require institutionalised financing models.

- The project placed 11 junior experts with startups across five countries (Effectiveness). Startups consistently cited junior experts as “transformative,” filling technical and operational gaps (interview notes). AgroSupply retained one expert after project funding ended.

- The project successfully demonstrated the value of placements but could not ensure continuity alone. Sustainability depends on linkages to institutions that already have financing mechanisms.

- Talent pipelines for climate-fintech startups need longer-term financing models. Projects should treat talent placements as proof-of-concept pilots, not permanent pipelines. Without them, critical capacity gains risk being lost. Embed university, corporate, or donor co-financing partnerships into talent pipelines from inception, ensuring junior expert placements continue after project closure.

- Skills-placement schemes can bridge startup capacity gaps, but unless tied to universities, corporates, or donor mechanisms, they remain unsustainable. This is relevant for any program aiming to build digital or climate-related human capital.

Lesson 4: Government engagement needs higher-level facilitation.

- The GEF Challenge Program’s global pre-selection structure limited national government participation by approving projects before country consultations or letters of endorsement. As a result, Operational Focal Points were informed but not involved in co-design, leading to weak alignment with national adaptation frameworks and minimal policy traction.

- Outreach through COP events, webinars, and PSC meetings provided visibility but did not substitute for structured engagement. Without dedicated government engagement activities, startups were perceived as isolated pilots rather than contributors to national adaptation or digital finance strategies.

- To strengthen ownership, future Challenge Program projects should prioritize countries demonstrating commitment to policy integration and select startups whose models align with national adaptation or climate finance priorities, thereby improving coherence and long-term sustainability.

- Work with governments and regulators to create enabling frameworks (e.g., carbon markets, adaptation credit lines, tax incentives) that lower the cost of capital for adaptation ventures and make them more attractive to private investors.

Lesson 5: Knowledge products add value when analytical and targeted.

- The project produced 10 knowledge products, including the widely cited State of Climate Tech Africa 2023 report. Investors and policymakers cited the flagship report as shaping adaptation narratives. In contrast, high-cost communications products (e.g., videos) were flagged as disproportionately expensive (Efficiency analysis).

- Publications such as the State of Climate Tech Africa 2023 were widely cited and positioned adaptation as investable, while some high-cost communication products offered limited value related to cost. Prioritizing analytical outputs (investment briefs, policy notes) and allocating smaller, cost-controlled budgets for promotional communications, could assist in strengthening knowledge products in future programs.

- For adaptation-fintech accelerators, knowledge products should emphasize analytical rigor and policy relevance over promotional branding. Future projects should focus on analytical outputs that influence investors and policymakers, ensuring communications budgets emphasize credibility over promotion.

- Across development programs, knowledge products achieve the greatest influence when they are analytical, policy-relevant, and cost-efficient, rather than when designed for promotional branding.

- Position adaptation investments not just as growth opportunities, but also as portfolio risk mitigation tools for investors exposed to climate risk (agribusinesses, insurers, banks).

Lesson 6: Gender integration is achievable at portfolio level but systematic barriers remain.

- Gender was integrated as a cross-cutting dimension, with portfolio targets for women-led startups and female beneficiaries. The project supported three women-led startups (target: two), nine women entrepreneurs (target: five), and reached 169,157 female beneficiaries (target: 10,000). However, interviews revealed barriers in land ownership, irrigation, and access to finance for women farmers.

- The project exceeded gender targets, supporting three women-led startups and reaching women farmers. Yet barriers such as land tenure, irrigation, and access to capital remain unaddressed. Gender integration in enterprise portfolios should be paired with systematic policy dialogue and financial inclusion initiatives to address structural inequalities.

- Achieving gender targets is possible at the portfolio level, but impact is limited unless systemic policy/financial barriers are tackled. Pair enterprise-level gender integration with policy advocacy and financial inclusion measures (e.g., women’s access to land registries, irrigation services, and tailored credit products).

- Meeting portfolio gender targets is insufficient if systemic structural barriers remain unaddressed. This applies across adaptation, mitigation, and industrial innovation projects where gender-responsive policy advocacy and inclusive financing are critical.

Lesson 7: Sector-specific risks must shape sustainability expectations.

- Startups operated across agriculture, recycling, and data/AI services. Agriculture ventures (AgroSupply, Farm to Feed) were capital-intensive; recycling ventures (Envocare) faced high operational costs; data/AI services (The Awareness Company) reported long B2B sales cycles. Several startups flagged these dynamics as constraints to scaling.

- These dynamics pose challenges for scaling within short project cycles. Future accelerator projects should adjust expectations, adopt longer time horizons, and explore blended finance mechanisms tailored to sector realities.

- Future accelerators should adapt expectations and financing models to sector realities instead of applying uniform benchmarks. Incorporate blended finance and longer time horizons for agriculture and recycling, while tailoring acceleration models for slower-to-scale sectors like data services.

- Sector-specific business models carry different risk and scaling timelines. Innovation accelerators across all sectors (climate, energy, health, digital) should calibrate expectations and financing instruments accordingly.

Lesson 8: Advanced technologies should be integrated into impact validation.

- Impact reporting relied primarily on startup self-reporting via the Visible platform. The project exceeded targets on beneficiaries (407,127 vs. 20,000) and land under improved management (278,097 ha vs. 1,600), but these figures were not independently verified (Impact section).

- While reporting systems were efficient, lack of third-party validation may reduce confidence among some investors and policymakers. Early-stage adaptation accelerators require credible verification mechanisms to strengthen trust in reported outcomes.

- The project relied heavily on self-reported data from startups to estimate beneficiaries, hectares management, and environmental benefits. While reporting systems were streamlined, independent verification was limited. Future projects should budget for independent verification (audits, spot checks, harmonized MEL frameworks). While UAV/satellite tools are not current UNIDO/GEF standards, third-party audits and harmonized data protocols could be embedded.

- Early-stage innovation projects across sectors risk credibility if results are not independently verified. Integrating third-party audits, satellite/UAV imagery, or harmonized MEL tools should become standard practice in future UNIDO/GEF projects.

# Annexes

## Annex 1. Evaluation Terms of Reference

UNITED NATIONS INDUSTRIAL DEVELOPMENT ORGANIZATION

TERMS OF REFERENCE

Final self-evaluation of project

UNIDO ID: [Status]

July 2025

Contents

I.	PROJECT BACKGROUND AND CONTEXT	3

1.	Project factsheet	3

2.	Project context	3

3.	Project objective and expected outcomes	4

4.	Project implementation arrangements	5

5.	Main findings of the Mid-term review (MTR)	6

6.	Budget information	6

II.	Scope and purpose of the evaluation	8

III.	Evaluation approach and methodology	9

1.	Data collection methods	9

2.	Key evaluation questions and criteria	10

3.	Rating system	12

IV.	Evaluation process	12

V.	Time schedule and deliverables	12

VI.	Evaluation team composition	13

VII.	Reporting	14

VIII.	Quality assurance	15

Annex 1: Project Logical Framework	16

Annex 2: Detailed questions to assess evaluation criteria	24

Annex 3: Job descriptions	30

Annex 4- Outline of an in-depth project evaluation report	34

Annex 5: Checklist on evaluation report quality	37

Annex 6: Guidance on integrating gender in evaluations of UNIDO projects and Projects	38

Table 1. Financing plan summary	6

Table 2. Financing plan summary - Outcome breakdown	6

Table 3. Co-Financing source breakdown	7

Table 4. UNIDO budget execution	7

Table 5. Project evaluation criteria	10

Table 6. Project rating criteria	12

Table 7. Major timelines	13

# PROJECT BACKGROUND AND CONTEXT

## Project factsheet

| Project title | [Title] |
| --- | --- |
| UNIDO ID | [Status] |
| Region | Africa |
| Country(ies) | Kenya, Nigeria, Rwanda, South Africa, Uganda |
| Project donor(s) | GEF |
| Project implementation start date | 14 April 2023 |
| Expected duration | 24 months |
| Expected implementation end date | 30 April 2024 (initial) → 30 September 2025 (extended) |
| Implementing agency(ies) | UNIDO |
| Executing Partners | BFA Global |
| Donor funding | USD 863,242 (GEF Grant) |
| UNIDO input (in kind, USD) | NA |
| Co-financing at CEO Endorsement, as applicable | USD 10,965,000 |
| Mid-term review date | Not Applicable |
| Planned terminal evaluation date | 1st August 2025 - 30th September 2025 |

(Source: Project document)

## Project context

The project titled "Acceleration of Financial Technology-enabled Climate Resilience Solutions" (GEF ID: 10927) is a Medium-Sized Project (MSP) financed by the Global Environment Facility (GEF) and implemented by the United Nations Industrial Development Organization (UNIDO), with BFA Global as the executing partner. Operating across Kenya, Nigeria, Rwanda, South Africa, and Uganda, the project aims to develop and scale gender-responsive fintech innovations that enhance the climate resilience of underserved populations.

The project is structured around three interrelated components. The first focuses on accelerating fintech innovations that address climate adaptation needs through targeted technical assistance, bespoke venture-building support, and catalytic financing instruments. The second aims to strengthen the broader digital finance ecosystem for climate resilience by engaging investors, disseminating insights and learnings, and building talent pipelines for future innovation. The third component enhances monitoring and learning approaches to ensure robust progress tracking and knowledge generation, in alignment with both GEF and UNIDO standards and culminating in a terminal evaluation.

The project commenced in January 2023 and is scheduled for completion in September 2025. In accordance with the GEF Evaluation Policy, the project requires a Terminal Evaluation to be conducted by an independent external evaluator. As the project nears its conclusion in September 2025, this evaluation must be carried out in line with the GEF Terminal Evaluation Guidelines to assess its overall performance, effectiveness, and contribution to climate adaptation.

In accordance with the GEF Evaluation Policy and the 2024 GEF Terminal Evaluation Guidelines, this terminal evaluation aims to deliver an impartial and rigorous assessment of the project’s design, execution, and outcomes. Its primary objective is to determine the extent to which the project has met its intended goals and delivered lasting benefits aligned with GEF’s strategic priorities and UNIDO’s mandate. It will further contribute to institutional learning, transparency, and accountability.

Specifically, the evaluation will examine the achievement of project results in terms of their contribution to climate resilience across the five participating countries. It will extract key lessons, critical success factors, and encountered challenges to inform the design and execution of future initiatives. Moreover, the evaluation will provide robust evidence and practical recommendations to UNIDO, BFA Global, and the GEF Secretariat on the strategic relevance and operational effectiveness of fintech-based adaptation solutions.

## Project objective and expected outcomes

This project aims to accelerate climate resilience in five African countries by supporting fintech startups that provide inclusive and scalable adaptation solutions. It does so by combining tailored venture-building, catalytic co-investment, and ecosystem engagement to help startups grow, de-risk their business models, and improve access to early-stage financing.

Expected Outcomes:

Component 1 – Accelerate Fintech-Enabled Climate Resilience Startups

- Outcome 1:Fintech startups improving climate adaptation and resilience are accelerated in a way that is gender-responsive and considers environmental and social sustainability

  - Output 1.1.1: Fintech startups enhancing resilience are identified and selected using gender-responsive and environmental & social (E&S) sustainability criteria.

  - Output 1.1.2: Selected startups are accelerated to enhance and scale their innovative solutions for climate resilience.

Component 2 – Strengthening the Ecosystem around Digital Finance for Climate Resilience

- Outcome 2.1: The global ecosystem around digital finance for climate resilience solutions is built and strengthened.

  - Output 2.1.1: Two investment thesis briefs (gender-responsive and E&S sustainable) are developed and disseminated to attract at least 10 global investors (≥50% with women in leadership).

  - Output 2.1.2: Talent pipelines for climate fintech innovation are created by placing at least 10 junior experts (≥50% women) with startups.

  - Output 2.1.3: Learning and insights on digital finance for climate resilience are gathered and shared through at least 9 blogs applying a gender lens.

Component 3 – Monitoring Approaches Enhanced

- Outcome 3.1: Progress of the project is tracked and reported.

  - Output 3.1.1: Annual project progress reports are completed in line with UNIDO and GEF guidelines, along with an independent terminal review.

## Project implementation arrangements

The project management structure as designed is provided after project inception.

## Main findings of the Mid-term review (MTR)

Not Applicable due to the term of the project

## Budget information

The project management structure as designed is provided after project inception.

# Scope and purpose of the evaluation

The purpose of this self-evaluation is to independently assess the project to help UNIDO improve performance and results of ongoing and future programmes and projects. The self-evaluation will cover the whole duration of the project from its starting date in       to the estimated completion date in 9/30/2025.

The evaluation has two specific objectives:

          - Assess the project performance in terms of relevance, coherence, effectiveness, efficiency, sustainability and progress to impact; and

          - Develop a series of findings, lessons and recommendations for enhancing the design of new and implementation of ongoing projects by UNIDO.

# Evaluation approach and methodology

The self-evaluation will be conducted in accordance with the UNIDO Evaluation Policy and the UNIDO Guidelines for the Technical Cooperation Project and Project Cycle. UNEG Norms and Standards for evaluation shall also be observed.

The self-evaluation will be carried out as an independent in-depth evaluation using a participatory approach whereby all key parties associated with the project will be informed and consulted throughout the evaluation.

The evaluation will use a theory of change approach and mixed methods to collect data and information from a range of sources and informants. It will pay attention to triangulating the data and information collected before forming its assessment. This is essential to ensure an evidence-based and credible evaluation, with robust analytical underpinning.

The theory of change will identify causal and transformational pathways from the project outputs to outcomes and longer-term impacts, and drivers as well as barriers to achieve them. The learning from this analysis will be useful to feed into the design of the future projects so that the management team can effectively manage them based on results.

## Data collection methods

Following are the main instruments for data collection:

            - Desk and literature review of documents related to the project, including but not limited to:

            - The original project document, monitoring reports (such as progress and financial reports, technical reports, interview  report(s), end-of-contract report(s) and relevant correspondence.

            - Notes from the meetings of committees involved in the project.

            - Stakeholder consultations will be conducted through structured and semi-structured interviews and focus group discussions. Key stakeholders to be interviewed include:

- UNIDO Management and staff involved in the project; and

- Representatives of donors, counterparts, and other stakeholders.

            - Online data collection methods will be used to the extent possible.

## Evaluation key questions and criteria

The key evaluation questions are the following:

        - What are the key drivers and barriers to achieve the long term objectives? To what extent has the project helped put in place the conditions likely to address the drivers, overcome barriers and contribute to the long term objectives?

        - How well has the project performed? Has the project done the right things? Has the project done things right, with good value for money?

        - What have been the project’s key results (outputs, outcome and impact)? To what extent have the expected results been achieved or are likely to be achieved? To what extent the achieved results will sustain after the completion of the project?

        - What lessons can be drawn from the successful and unsuccessful practices in designing, implementing and managing the project?

The self-evaluation will assess the likelihood of sustainability of the project results after the project completion. The assessment will identify key risks (e.g. in terms of financial, socio-political, institutional and environmental risks) and explain how these risks may affect the continuation of results after the project ends. Table 5 below provides the key evaluation criteria to be assessed by the evaluation. The details questions to assess each evaluation criterion are in annex 2.

Table 5. Project evaluation criteria

| # | Evaluation criteria | Mandatory rating |
| --- | --- | --- |
| A | Progress to Impact | Yes |
| B | Project design | Yes |
| 1 | - Overall design | Yes |
| 2 | - Project results framework/log frame | Yes |
| C | Project performance and progress towards results | Yes |
| 1 | - Relevance | Yes |
| 2 | - Coherence | Yes |
| 3 | - Effectiveness | Yes |
| 4 | - Efficiency | Yes |
| 5 | - Sustainability of benefits | Yes |
| D | Gender mainstreaming | Yes |
| E | Project implementation management | Yes |
| 1 | - Results-based management (RBM) | Yes |
| 2 | - Monitoring and Evaluation, Reporting | Yes |
| F | Performance of partners |  |
| 1 | - UNIDO | Yes |
| 2 | - National counterparts | Yes |
| 3 | - Implementing partner (if applicable) | Yes |
| 4 | - Donor | Yes |
| G | Environmental and Social Safeguards (ESS), Disability and Human Rights | Yes |
| 1 | - Environmental Safeguards | Yes |
| 2 | - Social Safeguards, Disability and Human Rights | Yes |
| H | Overall Assessment | Yes |

Performance of partners

The assessment of performance of partners will include the quality of implementation and execution of the GEF Agencies and project executing entities (EAs) in discharging their expected roles and responsibilities. The assessment will take into account the following:

- Quality of Implementation, e.g. the extent to which the agency delivered effectively, with focus on elements that were controllable from the given GEF Agency’s perspective and how well risks were identified and managed.

- Quality of Execution, e.g. the appropriate use of funds, procurement and contracting of goods and services.

Other Assessments required by the GEF for GEF-funded projects:

The self-evaluation will assess the following topics, for which ratings are not required:

              - Need for follow-up: e.g. in instances financial mismanagement, unintended negative impacts or risks.

              - Materialization of co-financing: e.g. the extent to which the expected co-financing materialized, whether co-financing was administered by the project management or by some other organization; whether and how shortfall or excess in co-financing affected project results.

## Rating system

In line with the practice adopted by many development agencies, UNIDO uses a six-point rating system, where 6 is the highest score (highly satisfactory) and 1 is the lowest (highly unsatisfactory) as per Table 6.

Table 6. Project rating criteria

| Score |  | Definition | Category |
| --- | --- | --- | --- |
| 6 | Highly satisfactory | Level of achievement presents no shortcomings (90% - 100% achievement rate of planned expectations and targets). | SATISFACTORY |
| 5 | Satisfactory | Level of achievement presents minor shortcomings (70% - 89% achievement rate of planned expectations and targets). |  |
| 4 | Moderately satisfactory | Level of achievement presents moderate shortcomings (50% - 69% achievement rate of planned expectations and targets). |  |
| 3 | Moderately unsatisfactory | Level of achievement presents some significant shortcomings (30% - 49% achievement rate of planned expectations and targets). | UNSATISFACTORY |
| 2 | Unsatisfactory | Level of achievement presents major shortcomings (10% - 29% achievement rate of planned expectations and targets). |  |
| 1 | Highly unsatisfactory | Level of achievement presents severe shortcomings (0% - 9% achievement rate of planned expectations and targets). |  |

# Evaluation process

The self-evaluation will be conducted from to. The evaluation will be implemented in five phases which are not strictly sequential, but in many cases iterative, conducted in parallel and partly overlapping:

                - Inception phase: The evaluation team will prepare the inception report providing details on the methodology for the evaluation and include an evaluation matrix with specific issues for the evaluation; the specific online interview session will be determined during the inception phase, taking into consideration the findings and recommendations of the mid-term review.

                - Desk review and data analysis;

                - Interviews, survey and literature review;

                - Data analysis and self-evaluation report writing.

# Time schedule and deliverables

The self-evaluation exercise is scheduled to take place from starting date in 8/1/2025 to the estimated completion date in 9/30/2025. The tentative timelines are provided in Table 7.

The draft report will be submitted within 4 weeks after the end of the online interview session. The draft report is to be shared with the UNIDO PM and other stakeholders for receipt of comments. The ET leader is expected to revise the draft report based on the comments received, edit the language and form and submit the final version of the TE report in accordance with UNIDO standards.

Table 7. Tentative timelines

| Timelines | Tasks |
| --- | --- |
| 1st August 2025 | Starting desk review and writing of inception report |
| 7th August 2025 | Briefing with UNIDO project manager and the project team based in Vienna through Teams |
| 14th August 2025 | Start conducting the series of interview |
| 1st September 2025 | Submission of first draft self-evaluation report with conducting interview Internal peer review of the report by UNIDO’s PM team and other stakeholder comments to 1st draft evaluation report |
| 15th September 2025 | Revising the 1st draft self-evaluation report with feedback |
| 30th September 2025 | Submission of Final self-evaluation report |

# Evaluation team composition

The evaluation team will be composed of one international evaluation consultant acting and will be contracted by UNIDO.

The tasks of consultant are specified in the job descriptions annexed to these terms of reference.

The UNIDO Project Manager and the project team in TCS/CMP/CTI will support the evaluation team.

The UNIDO Project Manager and national project teams will act as resourced persons and provide support to the evaluation team and the evaluation manager.

# Reporting

Inception report

This Terms of Reference (ToR) provides some information on the evaluation methodology, but this should not be regarded as exhaustive. After reviewing the project documentation and initial interviews with the project manager, the Team Leader will prepare a short inception report that will operationalize the ToR relating to the evaluation questions and provide information on what type of and how the evidence will be collected (methodology).

The Inception Report will focus on the following elements: preliminary project theory model(s); elaboration of evaluation methodology including quantitative and qualitative approaches through an evaluation framework (“evaluation matrix”); division of work between the International Evaluation Consultant; people to be interviewed and possible surveys to be conducted and a debriefing and reporting timetable.

Evaluation report format and review procedures

The draft report will be delivered to UNIDO’ PM (the suggested report outline is in Annex 4) and circulated to UNIDO staff and national stakeholders associated with the project for factual validation and comments.

The ET will present its preliminary findings to the local stakeholders at the end of the online interview and take into account their feed-back in preparing the evaluation report. A presentation of preliminary findings will take place at UNIDO HQ after the online interview Session.

The final report should be brief, to the point and easy to understand. It must explain the purpose of the evaluation, exactly what was evaluated, and the methods used. The report must highlight any methodological limitations, identify key concerns and present evidence-based findings, consequent conclusions, recommendations and lessons. The report should provide information on when the evaluation took place, who was involved and be presented in a way that makes the information accessible and comprehensible. The report should include an executive summary that encapsulates the essence of the information contained in the report to facilitate dissemination and distillation of lessons.

Findings, conclusions and recommendations should be presented in a complete, logical and balanced manner. The self-evaluation report shall be written in English and follow the outline given in annex 4.

## Annex 1: Project Logical Framework

Please refer to CEO endorsement (Acceleration of financial technology-enabled climate resilience solutions | GEF)

## Annex 2: Detailed questions to assess evaluation criteria: See Annex 2 of the UNIDO Evaluation Manual

## Annex 3: Job descriptions

UNITED NATIONS INDUSTRIAL DEVELOPMENT ORGANIZATION

### TERMS OF REFERENCE FOR PERSONNEL UNDER 
INDIVIDUAL SERVICE AGREEMENT (ISA)

| Title: | Evaluation Consultant (Team Leader) |
| --- | --- |
| Level | Specialist (P-4) |
| Main Duty Station and Location: | Home based |
| Mission/s to: | As required |
| Start of Contract (EOD): | 12th August 2025 |
| End of Contract (COB): | 30th September 2025 |
| Contract Type: | Regular or WAE |

ORGANIZATIONAL CONTEXT

The United Nations Industrial Development Organization (UNIDO) is the specialized agency of the United Nations that promotes industrial development for poverty reduction, inclusive globalization and environmental sustainability.  The mission of UNIDO, as described in the Lima Declaration adopted at the fifteenth session of the UNIDO General Conference in 2013 as well as the Abu Dhabi Declaration adopted at the eighteenth session of UNIDO General Conference in 2019, is to promote and accelerate inclusive and sustainable industrial development (ISID) in Member States. The relevance of ISID as an integrated approach to all three pillars of sustainable development is recognized by the 2030 Agenda for Sustainable Development and the related Sustainable Development Goals (SDGs), which will frame United Nations and country efforts towards sustainable development. UNIDO’s mandate is fully recognized in SDG-9, which calls to “Build resilient infrastructure, promote inclusive and sustainable industrialization and foster innovation”. The relevance of ISID, however, applies in greater or lesser extent to all SDGs. Accordingly, the Organization’s programmatic focus is structured in four strategic priorities: Creating shared prosperity; Advancing economic competitiveness; Safeguarding the environment; and Strengthening knowledge and institutions.

Each of these programmatic fields of activity contains a number of individual programmes, which are implemented in a holistic manner to achieve effective outcomes and impacts through UNIDO’s four enabling functions: (i) technical cooperation; (ii) analytical and research functions and policy advisory services; (iii) normative functions and standards and quality-related activities; and (iv) convening and partnerships for knowledge transfer, networking and industrial cooperation. Such core functions are carried out in Departments/Offices in its Headquarters, Regional Offices and Hubs and Country Offices.

The Directorate houses the Divisions of Circular Economy and Green Industry (TCS/CEG), Energy and Climate Action (TCS/ECA), Climate Innovation and Montreal Protocol (TCS/CMP); MSME Competitiveness, Quality and Job Creation (TCS/SME); and Digital Transformation and Artificial Intelligence (TCS/DAI). The Directorate also ensures close coordination and collaboration among the Divisions as well as with relevant entities in the Directorate of Global Partnerships and External Relations (GLO) and the Directorate of SDG Innovation and Economic Transformation (IET).

The Climate Innovation and Montreal Protocol Division (TCS/CMP) is mandated to work in close coordination with other organizational entities within UNIDO, assists Member States in emergence, deployment, and large-scale up-take of innovative climate solutions for low-carbon and climate resilient industrialization. The division promotes systems innovation approach to achieve transformational change in climate change by innovating across key levers of change that include technology, finance, policy, and regulation. In particular, the Division is responsible for the dual mandate of a) accelerating innovation and building climate technology innovation ecosystems to promote low-carbon and climate-resilient development pathways and b) planning, developing and implementing interventions to facilitate compliance with the Montreal Protocol and, in particular, its Kigali Amendment and to support countries in achieving their Nationally Determined Contributions (NDCs). In addition, the Division is responsible, in close collaboration with other relevant entities of the Organization, for facilitating the transfer of low-carbon and climate-resilient solutions and building markets to ensure their widespread use by industry and local communities, thereby contributing to climate change mitigation, adaptation, and building resilience in recipient countries.

The position is located under the Climate Technology Innovation Unit (CTI) which is responsible for supporting Member States in fostering innovation across technologies, finance, policy and regulation to promote the emergence, deployment and large-scale up-take of low-carbon and climate-resilient solutions and business practices. In addition, the Unit is responsible, in close collaboration with other relevant entities in the Organization, for facilitating the transfer of and establishing markets for low-carbon and climate resilient technologies, ensuring wide use by industry and local communities, thereby contributing to climate mitigation, adaptation and building resilience in recipient countries. The Unit positions UNIDO strategically in the global discourse on climate technology innovation support and acts as the focal point in UNIDO for partnership with the technology mechanism of the UNFCCC.

PROJECT CONTEXT

The project titled "Acceleration of Financial Technology-enabled Climate Resilience Solutions" (GEF ID: 10927) is a Medium-Sized Project (MSP) financed by the Global Environment Facility (GEF) and implemented by the United Nations Industrial Development Organization (UNIDO), with BFA Global as the executing partner. Operating across Kenya, Nigeria, Rwanda, South Africa, and Uganda, the project aims to develop and scale gender-responsive fintech innovations that enhance the climate resilience of underserved populations.

The project is structured around three interrelated components. The first focuses on accelerating fintech innovations that address climate adaptation needs through targeted technical assistance, bespoke venture-building support, and catalytic financing instruments. The second aims to strengthen the broader digital finance ecosystem for climate resilience by engaging investors, disseminating insights and learnings, and building talent pipelines for future innovation. The third component enhances monitoring and learning approaches to ensure robust progress tracking and knowledge generation, in alignment with both GEF and UNIDO standards and culminating in a terminal evaluation.

The project commenced in January 2023 and is scheduled for completion in September 2025. In accordance with the GEF Evaluation Policy, the project requires a Terminal Evaluation to be conducted by an independent external evaluator. As the project nears its conclusion in September 2025, this evaluation must be carried out in line with the GEF Terminal Evaluation Guidelines to assess its overall performance, effectiveness, and contribution to climate adaptation.

In accordance with the GEF Evaluation Policy and the 2024 GEF Terminal Evaluation Guidelines, this terminal evaluation aims to deliver an impartial and rigorous assessment of the project’s design, execution, and outcomes. Its primary objective is to determine the extent to which the project has met its intended goals and delivered lasting benefits aligned with GEF’s strategic priorities and UNIDO’s mandate. It will further contribute to institutional learning, transparency, and accountability.

Specifically, the evaluation will examine the achievement of project results in terms of their contribution to climate resilience across the five participating countries. It will extract key lessons, critical success factors, and encountered challenges to inform the design and execution of future initiatives. Moreover, the evaluation will provide robust evidence and practical recommendations to UNIDO, BFA Global, and the GEF Secretariat on the strategic relevance and operational effectiveness of fintech-based adaptation solutions.

FUNCTIONAL RESPONSIBILITIES

Under the direct supervision of the Project Manager and close cooperation with the project team in the HQ and field location, the expert will be responsible for the performance of the following main duties:

Detailed background information of the project can be found the terms of reference (TOR) for the terminal evaluation.

| MAIN DUTIES | Concrete/ Measurable Outputs to be achieved | Working Days | Location |
| --- | --- | --- | --- |
| 1. Review project documentation and relevant country background information (national policies and strategies, UN strategies and general economic data). Define technical issues and questions to be addressed by the evaluator prior to the online interview. Determine key data to collect in the online interview and adjust the key data collection instrument if needed in coordination with the project manager, the project management team, and stakeholders to be interviewed. | - Adjusted table of evaluation questions, depending on country specific context. - Draft list of stakeholders to be interviewed. - Identify issues and questions to be addressed by the local technical expert | 5 days | Home-based |
| 2. Prepare an inception report which streamlines the specific questions to address the key issues in the TOR, specific methods that will be used and data to collect in the online interview, confirm the evaluation methodology, draft theory of change, and tentative agenda for online interview. Prepare initial draft of output analysis and review technical inputs prepared by evaluator, prior to online interview session. | - Draft theory of change and Evaluation framework to submit to the Project Manager for clearance. - Prepare output analysis and technical reports | 5 days | Home based |
| 3. Briefing with the UNIDO PM team, project managers and other key stakeholders at UNIDO HQ (included preparation of presentation). | - Detailed evaluation schedule with tentative interview agenda (incl. list of stakeholders to interview) - Division of evaluation tasks | 2 day | Through Teams |
| 4. Conduct online interviews. | - Conduct online meetings with relevant project stakeholders, beneficiaries, etc. for the collection of data and clarifications; - Agreement on the structure and content of the evaluation report and the distribution of writing tasks; - Evaluation presentation of the evaluation’s preliminary findings, conclusions and recommendations to stakeholders in the country, including the GEF OFP, at the end of the outline interview. | 5 days | Through Teams |
| 5. Present overall findings and recommendations to the stakeholders at UNIDO HQ | - After online interview session(s): Presentation slides, feedback from stakeholders obtained and discussed. | 2 day | Home-based |
| 6. Prepare the evaluation report according to the TOR; Coordinate the inputs and combine with her/his own inputs into the draft evaluation report. Share the evaluation report with UNIDO HQ and national stakeholders for feedback and comments. | - Draft evaluation report. | 8 day | Home-based |
| 7. Revise the draft project evaluation report based on comments from UNIDO’s PM and stakeholders and edit the language and form of the final version according to UNIDO standards. | - Final evaluation report. | 3 day | Home-based |
|  | TOTAL | 30 days |  |

##### MINIMUM ORGANIZATIONAL REQUIREMENTS

Education: Advanced university degree (master’s or equivalent) in economics, engineering, sciences, agro-industries, environment, business administration, development studies or other relevant discipline with specialization in climate policy, innovation, finance, evaluation, technology management, is required.

Technical and Functional Experience:

- Minimum of seven (7) years' experience in evaluation of development projects and programmes at international level, including some at team leader level is required.

- Experience in evaluating international projects and knowledge of UNIDO is an asset.

- Knowledge of TC programme/project management cycle, design, implementation and M&E is desirable.

- Knowledge about multilateral technical cooperation and the UN, international development priorities and frameworks

- Familiarity with social and environmental analysis, tools and methodologies is an asset.

- Experience in the needs, conditions and problems in developing countries is desirable.

Languages: Fluency in written and spoken English is required. Fluency and/or working knowledge of another official UN language, particularly French is desirable [or required].

Absence of conflict of interest:

According to UNIDO rules, the consultant must not have been involved in the design and/or implementation, supervision and coordination of and/or have benefited from the programme/project (or theme) under evaluation. The consultant will be requested to sign a declaration that none of the above situations exists and that the consultants will not seek assignments with the manager/s in charge of the project before the completion of her/his contract with the UNIDO Independent Evaluation Division.

REQUIRED COMPETENCIES

Core values:
WE LIVE AND ACT WITH INTEGRITY: work honestly, openly and impartially.

WE SHOW PROFESSIONALISM: work hard and competently in a committed and responsible manner.

WE RESPECT DIVERSITY: work together effectively, respectfully and inclusively, regardless of our differences in culture and perspective.

Key competencies:
WE FOCUS ON PEOPLE: cooperate to fully reach our potential –and this is true for our colleagues as well as our clients. Emotional intelligence and receptiveness are vital parts of our UNIDO identity.

WE FOCUS ON RESULTS AND RESPONSIBILITIES: focus on planning, organizing and managing our work effectively and efficiently. We are responsible and accountable for achieving our results and meeting our performance standards. This accountability does not end with our colleagues and supervisors, but we also owe it to those we serve and who have trusted us to contribute to a better, safer and healthier world.

WE COMMUNICATE AND EARN TRUST: communicate effectively with one another and build an environment of trust where we can all excel in our work.

WE THINK OUTSIDE THE BOX AND INNOVATE: To stay relevant, we continuously improve, support innovation, share our knowledge and skills, and learn from one another.

Managerial and Leadership Competencies

WE ARE STRATEGIC, DECISIVE, PRINCIPLED AND INSPIRATIONAL: As managers, we are strategic and fair in driving our team’s performance. As leaders, we are a source of inspiration, stand for norms and standards established in the UN Charter and duty bound to defend these ideals with a principled approach.

WE ARE INCLUSIVE AND ACCOUNTABLE: As managers, we are inclusive in our approach and maintain constructive engagement with all our stakeholders. As leaders, we embrace all personnel and stakeholders and are accountable mutually within UNIDO, within the system, to beneficiaries and the public and beyond.

WE ARE MULTI-DIMENSIONAL AND TRANSFORMATIONAL: As managers, we go beyond conventional methods to help our organizational units strengthen their own agility and adaptability to change. As leaders in the UN system, we have a vision which is integrated and engaged across the pillars of Peace and Security, Human Rights and Development.

WE ARE COLLABORATIVE AND CO-CREATIVE: As managers, we foster a team spirit and create meaningful opportunities to hear the voices of those around us, while realizing that only by working together can we accomplish our mission. As leaders we see the inter-dependency of imperatives of the UN Charter and personally champion a collaborative inter-agency, multi-stakeholders and cross-thinking approach.

## Annex 4- Outline of an in-depth project evaluation report

Abstract

Contents

Acknowledgements

Abbreviations and acronyms

Glossary of Evaluation Related Terms

Executive summary (maximum 5 pages)

Evaluation purpose and methodology

Key findings

Conclusions and recommendations

Project ratings

Tabular overview of key findings – conclusions – recommendations

1.	Introduction

1.1	Evaluation Purpose

1.2 	Evaluation Objectives and Scope

1.3 	Theory of Change

1.4 	Methodology

1.5 	Limitations

2.	Project Background and Context

2.1. Project factsheet

3.	Findings

3.1. 	Project Design

3.2 	Relevance

3.3 	Coherence

3.4 	Effectiveness

3.5 	Efficiency

3.6 	Sustainability

3.7 	Progress to Impact

3.8 	Gender Mainstreaming

3.9 	Environmental Impacts

3.10 	Human Rights/Social Impact

3.11 	Performance of Partners

3.12	Results-based Management

3.13 	Monitoring & Reporting

3.14 	Project Ratings

4.	Conclusions and Recommendations

4.1 	Conclusions

4.2 	Recommendations and Management Response

5.	Lessons Learned

6. Annexes

Annex 1: Evaluation Terms of Reference

Annex 2: Evaluation Framework / Matrix

Annex 3: List of Documentation Reviewed

Annex 4: List of Stakeholders Consulted

Annex 5: Project Theory of Change / Logframe

Annex 6: Primary Data Collection Instruments

Annex 7: Survey / Questionnaire

Annex 8: Statistical Data from zEvaluation Survey / Questionnairez Analysis

## Annex 5: Checklist on evaluation report quality

Project Title:

UNIDO ID:

Evaluation team:

Quality review done by:

Date:

| Quality criteria |  | UNIDO EIO/IEU assessment notes | Rating |
| --- | --- | --- | --- |
| 1 | The inception report is well-structured, logical, clear, and complete. |  |  |
| 2 | The evaluation report is well-structured, logical, clear, concise, complete and timely. |  |  |
| 3 | The report presents a clear and full description of the ‘object’ of the evaluation. |  |  |
| 4 | The evaluation’s purpose, objectives, and scope are fully explained. |  |  |
| 5 | The report presents a transparent description of the evaluation methodology and clearly explains how the evaluation was designed and implemented. |  |  |
| 6 | Findings are based on evidence derived from data collection and analysis, and they respond directly to the evaluation criteria and questions. |  |  |
| 7 | Conclusions are based on findings and substantiated by evidence and provide insights pertinent to the object of the evaluation. |  |  |
| 8 | Recommendations are relevant to the object and purpose of the evaluation, supported by evidence and conclusions, and developed with the involvement of relevant stakeholders. |  |  |
| 9 | Lessons learned are relevant, linked to specific findings, and replicable in the organizational context. |  |  |
| 10 | The report illustrates the extent to which the evaluation addressed issues pertaining to a) gender mainstreaming, b) human rights, and c) environmental impact. |  |  |
| Rating system for quality of evaluation reports A number rating of 1-6 is used for each criterion: Highly satisfactory = 6, Satisfactory = 5, Moderately satisfactory = 4, Moderately unsatisfactory = 3, Unsatisfactory = 2, Highly unsatisfactory = 1, and unable to assess = 0. |  |  |  |

## Annex 6: Guidance on integrating gender in evaluations of UNIDO projects and Projects

      - Introduction

Gender equality is internationally recognized as a goal of development and is fundamental to sustainable growth and poverty reduction. The UNIDO Policy on gender equality and the empowerment of women and its addendum, issued respectively in April 2009 and May 2010 (UNIDO/DGB(M).110 and UNIDO/DGB(M).110/Add.1), provides the overall guidelines for establishing a gender mainstreaming strategy and action plans to guide the process of addressing gender issues in the Organization’s industrial development interventions.

According to the UNIDO Policy on gender equality and the empowerment of women:

Gender equality refers to the equal rights, responsibilities and opportunities of women and men and girls and boys. Equality does not suggest that women and men become ‘the same’ but that women’s and men’s rights, responsibilities and opportunities do not depend on whether they are born male or female. Gender equality implies that the interests, needs and priorities of both women and men are taken into consideration, recognizing the diversity of different groups of women and men. It is therefore not a ‘women’s issues’. On the contrary, it concerns and should fully engage both men and women and is a precondition for, and an indicator of sustainable people-centered development.

Empowerment of women signifies women gaining power and control over their own lives. It involves awareness-raising, building of self-confidence, expansion of choices, increased access to and control over resources and actions to transform the structures and institutions which reinforce and perpetuate gender discriminations and inequality.

Gender parity signifies equal numbers of men and women at all levels of an institution or organization, particularly at senior and decision-making levels.

The UNIDO projects/projects can be divided into two categories: 1) those where promotion of gender equality is one of the key aspects of the project/project; and 2) those where there is limited or no attempted integration of gender. Evaluation managers/evaluators should select relevant questions depending on the type of interventions.

      - Gender responsive evaluation questions

The questions below will help evaluation managers/evaluators to mainstream gender issues in their evaluations.

B.1. Design

- Is the project/project in line with the UNIDO and national policies on gender equality and the empowerment of women?

- Were gender issues identified at the design stage?

- Did the project/project design adequately consider the gender dimensions in its interventions? If so, how?

- Were adequate resources (e.g., funds, staff time, methodology, experts) allocated to address gender concerns?

- To what extent were the needs and priorities of women, girls, boys and men reflected in the design?

- Was a gender analysis included in a baseline study or needs assessment (if any)?

- If the project/project is people-centered, were target beneficiaries clearly identified and disaggregated by sex, age, race, ethnicity and socio-economic group?

- If the project/project promotes gender equality and/or women’s empowerment, was gender equality reflected in its objective/s? To what extent are output/outcome indicators gender disaggregated?

B.2. Implementation management

- Did project monitoring and self-evaluation collect and analyse gender disaggregated data?

- Were decisions and recommendations based on the analyses? If so, how?

- Were gender concerns reflected in the criteria to select beneficiaries? If so, how?

- How gender-balanced was the composition of the project management team, the Steering Committee, experts and consultants and the beneficiaries?

- If the project/project promotes gender equality and/or women’s empowerment, did the project/project monitor, assess and report on its gender related objective/s?

B.3. Results

- Have women and men benefited equally from the project’s interventions? Do the results affect women and men differently? If so, why and how? How are the results likely to affect gender relations (e.g., division of labour, decision making authority)?

- In the case of a project/project with gender related objective/s, to what extent has the project/project achieved the objective/s? To what extent has the project/project reduced gender disparities and enhanced women’s empowerment?

## Annex 2. Evaluator Biodata and Justification of Team Composition

Name: Dr. Charla M. Burnett
Role: Independent Evaluator (Team Leader)
Nationality: United States
Languages: English, French, Spanish, Arabic
Academic Qualifications:

- PhD in Global Governance and Human Security, University of Massachusetts Boston, Massachusetts, USA, 2021

- MA in Conflict Transformation and Peacebuilding, School for International Training (SIT) Graduate School, Brattleboro, Vermont, USA, 2015

- BA in Global Studies, Michigan State University, East Lansing, MI, USA, 2012

Professional Experience:
Dr. Charla Burnett is an independent evaluation and research specialist with over 12 years of professional experience in international development, climate change adaptation, digital innovation, and geospatial analysis. She has led and contributed to multiple independent evaluations of United Nations, United States Agency for International Development, and World Bank projects.

Her professional background includes:

- Advisory work on energy, climate resilience, and digital innovation programs at USAID, UNRWA, and other multilateral organizations.

- Research and published work on participatory mapping, digital governance, and AI-enabled geospatial analytics.

- Field and desk-based evaluation experience in Africa, the Middle East, and global portfolios.

Evaluation Skills:

- Application of DAC/GEF criteria (relevance, effectiveness, efficiency, sustainability, impact, coherence).

- Mixed-methods design, including theory-based evaluation, contribution analysis, and triangulation.

- Qualitative and quantitative data collection (semi-structured interviews, survey design, stakeholder mapping).

- Knowledge of UNIDO and GEF policies, gender integration frameworks, and environmental and social safeguards (ESS).

Independence:
The evaluator has no prior involvement in the design, implementation, or management of the Acceleration of Fintech-Enabled Climate Resilience Solutions Project and confirms independence from project management and partners.

Justification of Team Composition
This Terminal Evaluation was conducted by a single independent evaluator (team leader) with expertise spanning:

- Thematic expertise: climate change adaptation, fintech-enabled innovation, gender-smart investment, and digital transformation, in line with the project’s thematic focus.

- Methodological expertise: application of GEF and UNIDO evaluation criteria, use of theory of change and results frameworks, and triangulation of diverse data sources.

- Regional experience: professional and academic experience in sub-Saharan Africa, including Kenya, Nigeria, Rwanda, South Africa, and Uganda, ensured contextual understanding of startup ecosystems, policy environments, and climate risks.

- Cross-cutting expertise: gender equality, youth engagement, digital finance, and geospatial analytics, aligning with the project’s cross-cutting objectives.

Given the project’s scope and budget, the evaluation was efficiently and credibly delivered by one evaluator with the above multidisciplinary expertise. The independent evaluator was supported administratively by UNIDO’s Independent Evaluation Division in ensuring compliance with policy and quality assurance but retained full independence in data collection, analysis, and reporting.

## Annex 3. Evaluation Framework / Matrix

| Criterion (DAC/GEF) | Key Evaluation Questions | Indicators | Data Sources | Methods | Evidence Collected |
| --- | --- | --- | --- | --- | --- |
| Relevance | - To what extent did the project compliment other national/international initiatives on fintech, adaptation, gender? - Were there overlaps or synergies with UNIDO or other UN system programs? - How did PSC and IAC roles strengthen coordination? | Alignment with NDCs, NAPs, national policies; degree of alignment with GEF-7 objectives; consistency with UNIDO ISID/digital innovation mandate. | ProDoc; NDCs; national adaptation plans; interviews with UNIDO/BFA staff. | Document review; key informant interviews. | The project supported adaptation priorities (agriculture, forestry, waste, digital); startups mapped to NDC priorities in Kenya, Nigeria, Rwanda, Uganda, SA. |
| Coherence | - To what extent did the project compliment other national/international initiatives on fintech, adaptation, gender? - Were there overlaps or synergies with UNIDO or other UN system programs? - How did PSC and IAC roles strengthen coordination? | Evidence of complementarity/duplication with GSMA, WFP, other donor initiatives; linkages with UNIDO SME/digital innovation programs; policy linkages. | PIRs 2023–2025; stakeholder interviews; UNIDO portfolio documents. | Comparative analysis; interviews. | Complementary with GSMA/WFP; weak national linkages; aligned with UNIDO’s digital innovation portfolio. |
| Effectiveness | - To what extent did the project achieve planned outputs/outcomes (≥6 startups, ≥2 briefs, ≥10 investors, ≥10 junior experts, ≥9 blogs)? - How well were the gender thresholds met (≥30% women-led, ≥50% women in leadership, ≥20% targeting women)? - What factors enabled or hindered results? - To what extent did startups achieve business model maturity (fundraising, revenue growth, product scaling)? - Did knowledge products (blogs, briefs, impact videos) influence investors or policy? - Were junior experts effectively integrated into startups, and did they gain relevant skills? | # startups accelerated; # knowledge products; # junior experts; $ follow-on finance; # beneficiaries; hectares improved. | Metrics Tracker; PIRs; startup reports; interviews. | Triangulation across PIRs, financials, interviews. | 6 startups supported; 11 knowledge products; 11 junior experts; $3.3M mobilized; 115,711 beneficiaries; 195,894 ha. |
| Efficiency | - Were activities delivered on schedule and within budget? - How effective were management arrangements (UNIDO-BFA-PSC)? - Was the no-cost extension justified by results delivered? | Budget variance Y1/Y2; unit cost/startup; delays (gender report, travel, procurement); transaction costs. | UNIDO financial reports; BFA reports; PIRs; procurement logs. | Financial analysis; process review. | Y1 execution at 50%; video products high cost vs. value; gender report delayed; efficiency judged Moderately Satisfactory. |
| Sustainability | - What is the likelihood that benefits will continue beyond project closure (startup survival, investor networks, talent pipeline)? - Are enabling conditions in place (financial, institutional, regulatory)? - How were risks monitored and mitigated? - Are the accelerated startups showing pathways to financial sustainability? | Evidence of follow-on finance; institutionalization of tools (CRMs, dashboards); continuation of Circle of Investors; enabling environment. | Metrics Tracker; PIR 2025; startup interviews. | Triangulation; sustainability sub-dimension assessment. | 4 startups secured finance; systems institutionalized; Circle of Investors continues; sustainability rated Moderately Likely. |
| Impact | - What evidence exists of contribution to longer-term resilience (beneficiaries reached, hectares management, SME resilience)? - Did the project demonstrate catalytic effects (co-financing, replication, investor crowd-in)? - Are reported beneficiary/hectare overshoots credible and sustainable? - What evidence exists of household/SME resilience improvements (farmers adopting new seeds, improved waste management, afforestation)? - Did startups expand outreach to underserved groups (e.g., women, rural communities)? | # beneficiaries; # hectares improved; evidence of policy contribution; investor confidence. | Metrics Tracker; PIRs; knowledge products; interviews. | Evidence synthesis; contribution analysis. | Reported 115,711 beneficiaries, 195,894 ha; no independent verification; investor confidence strengthened. |
| Cross-cutting: Gender | - Were gender thresholds met? - How effective was the Gender Action Plan implementation? - Were women-led startups adequately supported? - Did the project influence investors’ adoption of gender-lens investing? | # women-led startups; # women farmers; % female beneficiaries. | Metrics Tracker; PIRs; startup data. | Data disaggregation; interviews. | 3/6 startups women-led; 45,794 women beneficiaries (39.6%). |
| Cross-cutting: ESS | - Were environmental and social risks identified and managed through the ESMF? - Did ESS influence startup selection? | ESS screening; safeguard policies formalized. | PIRs; startup reports. | Document review. | Inconsistent; some startups developed ESS policies, others did not. |
| Cross-cutting: MEL | - Were monitoring tools/templates used consistently across the project cycle? - How accurate and reliable were reported results (esp. beneficiaries/hectares)? - How was learning captured and shared (blogs, briefs, events)? | Existence of KPIs; Visible platform; reporting regularity. | PIRs; startup reports; BFA documentation. | Document review; interviews. | Reporting streamlined through Visible; indicators tracked; reliance on self-reported data limits credibility. |

## Annex 4. List of Documentation Reviewed

| Document Name | Date | Description | Country |
| --- | --- | --- | --- |
| Project Steering Committee Inaugural Meeting | 05/19/2023 | Great overview of the state of Africa, both in climate risk and in investment and development. Can be used for the intro to the evaluation | Africa |
| Project Work Plan Y1 | 01/01/2023 | Provides an overview of all activities to be completed in Y1-23 and Y2-24 | Africa |
| CF IAC Meeting June 2022 (Catalyst Fund Industry Advisory Committee) | 06/01/2022 | Slide deck for Catalyst Fund’s IAC meeting covering cohort sourcing, IAC role, upcoming events (Demo Day; Fintech for Resilience Summit), venture-building, and pipeline for climate-resilience/fintech startups. | Multi-country (regional- Africa); including: Kenya, Nigeria, Rwanda, South Africa, Uganda) |
| Compliance Checklist (Panel): Climate Resilience SCCF/LDCF — 18 Nov 2022 | 11/18/2022 | UNIDO Panel Compliance Checklist for climate-resilience project (No. 210238); records advisor approvals and comments across relevance, structure, operations, gender, and ESS. | Multi-country (regional- Africa); including: Kenya, Nigeria, Rwanda, South Africa, Uganda) |
| GEF CEO Approval Letter: MSP (GEFSEC ID 10927) | 02/22/2023 | Formal CEO approval for the MSP “Acceleration of financial technology-enabled climate resilience solutions” (UNIDO Agency ID 210238). | Multi-country (regional- Africa); including: Kenya, Nigeria, Rwanda, South Africa, Uganda) |
| Annex A: UNIDO General Conditions for Implementing Partner/Grant Agreements (Model GC) | 04/01/2023 (April 2023) | Model General Conditions defining legal status, liabilities, indemnities, IP/asset ownership, confidentiality, grant use and eligible costs, tax exemptions, audits & records, procurement standards, essential terms (CoI, anti-fraud, labor, AML/CTF), environmental & social safeguards, suspension/termination, and UNCITRAL dispute resolution. | Global (not country-specific) |
| Annex B: Terms of Reference for the Project Execution Agreement (UNIDO - BFA Global) | 04/27/2023 | ToR defining roles, responsibilities, deliverables, governance, and M&E for executing the regional fintech-enabled climate resilience acceleration program (UNIDO SAP 210238 / GEF 10927). | Multi-country (regional- Africa); including: Kenya, Nigeria, Rwanda, South Africa, Uganda) |
| Annex C: Operational Guidelines for UNIDO Implementing Partners/Grant Beneficiaries | 04/01/2023 (April 2023) | Operational procedures for executing UNIDO grant-funded projects: reporting, recruitment, procurement, asset management, insurance, financial management (payments/eligible costs/refunds), anti-fraud/corruption, and audits; includes standardized forms (work plan, procurement plan, risk, progress/final reports, financial report, incident report, signatures, payment request). | Global (not country-specific) |
| GEF CEO Endorsement (MSP, GEF ID 10927): "Acceleration of financial technology-enabled climate resilience solutions" | 11/17/2022 | GEF-7 CEO Endorsement entry detailing objectives, components/outputs, budgets, co-financing, country scope, and results indicators for the MSP implemented by UNIDO with BFA Global. | Multi-country (regional- Africa); including: Kenya, Nigeria, Rwanda, South Africa, Uganda) |
| Procurement Committee Routing Sheet: PC2023-24 (Award to BFA Global) | 3/14/2023 | Procurement Committee submission and approvals for awarding the “Acceleration of financial technology-enabled climate resilience solutions” contract to Bankable Frontier Associates LLC (BFA Global). | Multi-country (regional- Africa); including: Kenya, Nigeria, Rwanda, South Africa, Uganda) |
| Project Work Plan - Extension Request April 2025 | 4/1/2025 (April 2025) | Two-sheet Excel work plan (baseline and “No-cost extension”) scheduling MSP outputs/activities—includinng “≥6 startups accelerated,” investment thesis briefs, and talent placements—across months into 2025 | Multi-country (regional- Africa); including: Kenya, Nigeria, Rwanda, South Africa, Uganda) |
| GEF/UNIDO No-Cost Extension Request - BFA Global | 3/24/2025 | Letter requesting to extend the MSP timeline from April 2025 to Dec 31, 2025, detailing completed and pending venture-building, learning, and communications outputs for portfolio companies. | Multi-country (regional- Africa); including: Kenya, Nigeria, Rwanda, South Africa, Uganda) |
| Inception Report: Progress Report No. 1 (GEF ID 10927 / UNIDO SAP 210238) | May 5-June, 15 2023 | Inception-phase progress report covering PMU/PSC setup, first-year work plan & budget approval, early venture-building selections (Farmz2U; Farm to Feed), stakeholder engagement, gender, risk, and knowledge management. | Multi-country (regional- Africa); including: Kenya, Nigeria, Rwanda, South Africa, Uganda) |
| PSC Minutes: First Project Steering Committee Meeting (GEF 10927) | 5/19/2023 | Minutes of the first PSC for “Accelerating fintech for climate resilience”: attendees (GEF, UNIDO, BFA Global, country nominees), agenda, country perspectives, ToR acceptance, BFA presentation, Q&A, and approval of the Year 1 work plan & budget. | Multi-country (regional- Africa); including: Kenya, Nigeria, Rwanda, South Africa, Uganda) |
| IRPF-Aligned Results Framework (Annex: Project Results Framework) | 12/1/2022 (December 2022) | Indicator matrix aligning objective, outcomes, and outputs to UNIDO/GEF core indicators with baselines, targets, sources of verification, and assumptions. | Multi-country (regional- Africa); including: Kenya, Nigeria, Rwanda, South Africa, Uganda) |
| Project Budget Table: Inception Report, Year 1 (Updated Budget May 2024) | May 2023 | Year-1 budget table listing expenditure categories, amounts, and responsible entities (BFA Global/UNIDO) by output (sourcing, due diligence, 6-startup acceleration, ecosystem-building, and reporting). | Multi-country (regional- Africa); including: Kenya, Nigeria, Rwanda, South Africa, Uganda) |
| Project Budget Table: Inception Report, Year 2 (Updated Budget Sept 2025) | May 2023 | Year-2 budget table listing expenditure categories, amounts, and responsible entities (BFA Global/UNIDO) by output (sourcing, due diligence, 6-startup acceleration, ecosystem-building, and reporting). | Multi-country (regional- Africa); including: Kenya, Nigeria, Rwanda, South Africa, Uganda) |
| Project Risk Register: Inception Report | May 2023 | Risk register listing key implementation, market, safeguards, gender, and climate risks with ratings (Low/Medium) and mitigation measures for the MSP. | Multi-country (regional- Africa); including: Kenya, Nigeria, Rwanda, South Africa, Uganda) |
| Knowledge Management & Communication Mechanisms: Outputs List | 7/16/2024 | Inventory of knowledge-management tools and communications produced through project insights and ecosystem engagement, including publications, videos, and event collateral | Multi-country (regional- Africa); including: Kenya, Nigeria, Rwanda, South Africa, Uganda) |
| JPMC Catalyzing Resilience Ecosystems: Advisory Board Meeting (AB) Slide Deck | 1/30/2024 | Advisory Board meeting deck covering project timelines/budget (no-cost extension to 31 May 2024), progress & lessons across three strategies, next steps (launching a Climate Resilience Innovation Lab), and selected publications. | Multi-country (Africa: including Kenya, Nigeria, Rwanda, South Africa, Uganda; activities also in Senegal, Tanzania, Chile, India) |
| Stakeholder Engagement Monitoring: Evidence List | 7/16/2024 | Evidence list of learning-activity engagements with donors, investors, local communities, talent networks, startups, and wider stakeholders (links/attachments to decks, blogs, emails, and event materials). | Multi-country (regional- Africa); including: Kenya, Nigeria, Rwanda, South Africa, Uganda) |
| BFA Global Financial Report, Year 1 (as of 6/30/2024) | 6/30/2024 | Year-1 financial report for “Acceleration of financial technology-enabled climate resilience solutions.” Sub-grantee: Bankable Frontier Associates LLC; Grant period: May 2023–Apr 2025; currency USD: summarizing budget, spend, forecast, and expected variance by component. | Multi-country (regional- Africa); including: Kenya, Nigeria, Rwanda, South Africa, Uganda) |
| Grant Delivery Report: LDCF (2000004989) & SCCF (2000004991), UNIDO SAP 210238 | 7/16/2024 | UNIDO grant delivery report for the GEF MSP “Acceleration of financial technology-enabled climate resilience solutions,” showing released budget, obligations/disbursements, funds available and support cost by outcome (1.1, 2.1, 3.1) and Terminal Evaluation for the LDCF and SCCF grants; reporting period 21 Apr 2023–16 Jul 2024; grant validity 21 Apr 2023–21 Apr 2025. | Multi-country (regional- Africa); including: Kenya, Nigeria, Rwanda, South Africa, Uganda) |
| Project Implementation Report (PIR); FY24 (1 May 2023–30 June 2024) — GEF 10927 / UNIDO 210238 | 7/17/2024 | Annual Project Implementation Report summarizing progress vs. logframe, FY24 ratings (GEO/DO S; IP S; Overall Risk Low), outputs and milestones, risks/ESS (Category C), stakeholder engagement, gender mainstreaming, knowledge products, schedule amendment (Component 1 extended into Year 2), and Y2 work plan/budget | Multi-country (regional- Africa); including: Kenya, Nigeria, Rwanda, South Africa, Uganda) |
| PIR 2025: Project Progress Detail (GEF 10927 / UNIDO 210238) | 3/1/2025 (March 2025) | Final-year progress details summarizing Component 1 startup acceleration outcomes, Component 2 knowledge/engagement outputs, investor and talent activities, and Component 3 management and evaluation plans. | Multi-country (regional- Africa); including: Kenya, Nigeria, Rwanda, South Africa, Uganda) |
| PIR 2025: Project Work Plan (No-Cost Extension) | 2024-25 (no specific date indicated) | Two-sheet 2025 work plan (v1 and no-cost extension) laying out month-by-month scheduling for remaining Outputs 1.1.x, 2.1.x, and 3.1.x. | Multi-country (regional- Africa); including: Kenya, Nigeria, Rwanda, South Africa, Uganda) |
| PIR 2025: Logframe/Results Progress (Revised) | 2025 (no date specified) | Revised logframe/results table with baseline, targets, and progress-to-date for Components 1–3 (startups accelerated, ecosystem building, and monitoring/reporting). | Multi-country (regional- Africa); including: Kenya, Nigeria, Rwanda, South Africa, Uganda) |
| Knowledge Management & Communication Mechanisms: Outputs List (Revised) | 6/26/2025 | Updated inventory of knowledge-management and communications outputs (blogs, report, impact videos) produced from project insights, with dates spanning Oct 2023–Jul 2025 and attachments (webinar fliers; COP28 invitation). | Multi-country (regional- Africa); including: Kenya, Nigeria, Rwanda, South Africa, Uganda) |
| PIR 2025: Grant Financial Implementation Overview | 5/31/2025 | Summary budget report for the MSP implemented by BFA Global, covering budget, spend-to-date, forecast, actual+forecast, and expected variance by component; grant period May 2023–Sep 2025. | Multi-country (regional- Africa); including: Kenya, Nigeria, Rwanda, South Africa, Uganda) |
| PIR 2025: GEF Metrics Tracker (Annex Summary, Y1 & Y2) | 6/1/2025 (June 2025) | GEF core-indicator tracker with baseline/targets and Y1 & Y2 results for beneficiaries, startups, gender, ecosystem outputs, training, land area, and policy/knowledge metrics. | Multi-country (regional- Africa); including: Kenya, Nigeria, Rwanda, South Africa, Uganda) |
| Project Implementation Report (PIR): FY25 Draft v3.0 — GEF 10927 / UNIDO 210238 | FY 2025 (No date specified) | FY25 PIR draft summarizing progress, ratings (IP S; DO S; Risk L), startups accelerated, beneficiaries/land metrics, stakeholder & gender actions, knowledge outputs, and extension to 30 Sept 2025 with TE start 1 Sept 2025. | Multi-country (regional- Africa); including: Kenya, Nigeria, Rwanda, South Africa, Uganda) |
| UNIDO Evaluation Manual, Revision August 2024 | August 2024 | Organization-wide guidance from UNIDO’s Independent Evaluation Unit on evaluation concepts, RBM links, methods/criteria, safeguards, and step-by-step processes for project and strategic evaluations. | Global |
| Terminal Evaluation: ToR & Consultant JD (GEF 10927 / UNIDO 210238) | July 2025 | Terms of Reference and Job Description for the project’s Terminal Evaluation, specifying scope (relevance, coherence, effectiveness, efficiency, sustainability, progress to impact), methodology (theory of change; mixed methods; triangulation),, rating system (1–6), deliverables (inception report, draft, final), team composition, and schedule (1 Aug–30 Sep 2025). | Multi-country (regional- Africa); including: Kenya, Nigeria, Rwanda, South Africa, Uganda) |
| UNIDO Evaluation Policy (Director General’s Bulletin DGB/2021/11) | September 2021 | Organization-wide policy establishing UNIDO’s evaluation function: objectives, scope, types (self & independent), roles/responsibilities, principles (ethics, impartiality), and evaluation management (planning/budgeting, reporting, QA, follow-up, disclosure). | Global |
| UNEG Quality Checklist for Evaluation Reports (UNEG/G(2010)/2) | 2010 | UN Evaluation Group guidance checklist outlining critical quality indicators for evaluation reports (structure, object, purpose/scope, methodology, findings, conclusions, recommendations, gender & human rights). | Global |
| OECD DAC Evaluation Criteria: Adapted Definitions and Principles for Use (DCD/DAC(2019)58/FINAL) | 12/10/2019 | OECD DAC guidance updating the core evaluation criteria: relevance, effectiveness, efficiency, impact, sustainability; and adding the new criterion coherence, with principles for thoughtful use across interventions. | Global |
| UNIDO Administrative Instruction AI/2025/09: Supplementary guidance on the evaluation of development cooperation interventions | 8/13/2025 | Administrative Instruction issued by UNIDO’s Office of Evaluation and Internal Oversight (EIO) providing supplementary guidance to the Evaluation Policy/Monitoring & Reporting Policy/ TC Manual on self- vs independent evaluation, mandatory evaluation at closure, roles/responsibilities, and indicative evaluation budget allocations. | Global |
| Terminal Evaluation: Work Breakdown Structure & Milestones (Revised) | August-October 2025 | Work-Breakdown Structure and milestone schedule for the Terminal Evaluation: tasks (project review, inception, briefing, interviews, interim, draft, final) with a month grid and key dates: Kick-off meetings: 18 & 25 Aug 2025; Inception report: 1 Sep; Interim findings: 12 Sep; Interim report: 24 Sep; Draft report: 26 Sep.; Final report: 13 Oct; GEF-9 recommendation: 31 Oct; plus weekly Monday check-ins. | Multi-country (regional- Africa); including: Kenya, Nigeria, Rwanda, South Africa, Uganda) |
| Catalyst Fund: UNIDO-GEF Portfolio Slide Deck 2025 | 2025 | Visual portfolio deck profiling accelerated startups with problem/solution, founders, sectors, countries, investment dates, and links (websites, LinkedIn, showcase videos). | Multi-country (regional- Africa); including: Kenya, Nigeria, Rwanda, South Africa, Uganda) |
| Project Activities and Objectives Quicksheet (Y1–Y2) | 2023-2024 | One-page objectives/activities quicksheet for the MSP covering Program Setup (0.x), Output 1.1.x (selection/acceleration), Output 2.1.x (investment, talent, learning/events), and Output 3.1.x (annual reporting & terminal review). | Multi-country (regional- Africa); including: Kenya, Nigeria, Rwanda, South Africa, Uganda) |

## Annex 5. List of Stakeholders Consulted

| Stakeholder Group | Proposed Respondents | Rationale | Modality | Contact Information |
| --- | --- | --- | --- | --- |
| UNIDO HQ | Project Manager (CTI), Gender/Safeguards focal point | Required by TOR; provides oversight and accountability perspective | Online (Teams) | Alois MhLanga, a.mhlanga@unido.org Eleonora Gatti, e.gatti@unido.org, Katsuya Tokuda k.tokuda@unido.org, Rashmi jawaha, r.jawahar@unido.org, |
| Executing Partner | BFA Global – Project Director, M&E Lead | Central implementer; explains operations, challenges, and adaptive management | Online | Maelis, Javier, Maureen |
| Government / OFPs | 2–3 total: e.g., Kenya OFP + Nigeria OFP + Rwanda ICT Ministry rep | Ensures national counterpart and GEF OFP voice; sample across Anglophone, Francophone, and regulatory contexts | Online (group calls where possible) | Priority Recommendations: -Uganda OFP -Rwanda OFP -South Africa OFP |
| Startups | 2–3 startups (include ≥1 women-led, ≥1 gender-focused product) | Captures beneficiary service delivery, gender lens, private sector angle | Online interviews | FarmToFeed -Clair Van Enk, Co-founder and CEO cvanenk@farmtofeedkenya.com AgroSupply -Joseph Ogwal, Founder and CEO, ogwal.jose@agrosupplyltd.com Isaro Kristian Gasaro, Co-Founder and CEO gasaro@isaro.rw TACo -Priaash Ramadeen, Co-founder and CEO, priaash@awarenesscompany.co.za |
| Investors | 1 global investor engaged via briefs | Validates catalytic effect and co-financing dimension | Online | Marcus Watson, Manager Partner at Kawi Safi, mwatson@kawisafiventures.com |
| Junior Expert / Beneficiary Rep | 1 junior expert + 1 end-user group (proxy through startup or NGO partner) | Ensures end-user and capacity-building perspective is included | Online or phone | TBD |
| Cross-Cutting | 1 additional key informant (e.g., South Africa Treasury/Reserve Bank, or Uganda regulator) | Provides policy/system-level angle | Online | TBD |

## Annex 6. Project Theory of Change/Logframe

| Level | Description (Project Logic) | Key Indicators / Targets (from Logframe/IRPF) | Progress to Date (PIR 2025) | Sources of Verification | Key Assumptions / Risks |
| --- | --- | --- | --- | --- | --- |
| Inputs | - GEF grant USD 863,242 + UNIDO fee USD 82,008. - Co-financing USD 10.9m pledged (~USD 12.2m mobilized). - UNIDO oversight, BFA Global execution. - National counterpart engagement. | N/A | Funding mobilized; ~USD 12.2m co-financing reported | CEO Endorsement, Financial reports, Co-financing letters | Co-financing mobilized as planned; government support remains stable. |
| Activities | **Component 1 – Startup Acceleration:** sourcing, due diligence, onboarding, venture-building, TA, catalytic co-investment. **Component 2 – Ecosystem Strengthening:** investment briefs, investor engagement, talent placements, blogs, COP events, impact videos. **Component 3 – Monitoring & Learning:** annual PIRs, knowledge capture, Terminal Evaluation. | N/A | Startup acceleration underway; ecosystem activities ongoing; annual reporting in place | Workplans, PIRs, PSC minutes | Pipeline of viable startups exists; investors engage; gender/safeguards mainstreamed. |
| Outputs | - ≥6 startups selected and accelerated (≥30% women-led; ≥50% with women in leadership; ≥20% targeting women). - 2 investment thesis briefs delivered. - ≥10 investors engaged (≥50% with women in leadership). - ≥10 junior experts placed (≥50% women). - ≥9 blogs / learning products produced. - COP and industry events held. | ≥6 startups; 2 briefs; ≥10 investors; ≥10 junior experts; ≥9 blogs | 7 startups accelerated (4 under project, 3 via co-financing); 2 women-led; 4 targeting women. 1 gender brief finalized; 12 investors engaged. 10 junior experts placed (5 woman). 3 blogs published. Events: COP28, Founders Fest. | PIRs (2023–2025), BFA Global reports, Knowledge products | Startups deliver agreed outputs; talent pipeline functional; ecosystem events executed. |
| Outcomes | - Startups scale fintech solutions that reach climate-vulnerable groups. - Investor interest in adaptation-oriented fintech grows. - Talent pipeline strengthened; women actively represented. - Awareness and learning in adaptation-fintech ecosystem increases. | ≥20,000 direct beneficiaries (≥50% women); ~1,600 ha under improved management; 885 people trained (≥50% women); policies/plans supported | 380,888 direct beneficiaries (162,656 women); 278,097 ha managed; 709 people trained (242 women); 26 policies/plans supported | GEF Core Indicator Tracker, PIRs, Beneficiary reports, Investor evidence | Startups survive and scale; investors act on evidence; enabling regulatory environment maintained. |
| Impact | - Increased resilience of households, women, and MSMEs to climate shocks. - Strengthened digital finance ecosystems contributing to national adaptation priorities and SDGs (5, 8, 9, 13). | Long-term adoption of fintech solutions; Investor crowd-in beyond project | Evidence of investor crowd-in (~USD 6m commitments to startups); ecosystem strengthening ongoing; startups scaling climate-resilience solutions | Terminal Evaluation, National reports, Independent studies | Benefits sustained post-project; political/economic stability supports continuation. |

## Annex 7. Primary Data Collection Instruments

- Semi-Structured Interview Guides

  - Separate sets of questions tailored to each stakeholder group:

    - UNIDO HQ (Project Manager, Gender/Safeguards Focal Point)

    - Executing Partner (BFA Global: Project Director, M&E Lead)

    - Government / GEF OFPs (e.g., Kenya, Nigeria, Rwanda)

    - Startups (2–3, including women-led or gender-focused)

    - Investors (1–2 global/regional)

    - Junior Expert and Beneficiary proxy

    - Cross-cutting informant (e.g., South Africa Treasury, Uganda regulator)

  - Each guide should show how questions map to evaluation criteria (Relevance, Coherence, Effectiveness, Efficiency, Sustainability, Impact, Gender, Safeguards, MEL, Quality of Implementation/Execution).

  - Example:

    - Relevance: “How aligned was the project with national adaptation and digital finance priorities?”

    - Effectiveness: “To what extent did the project meet gender thresholds (≥30% women-led, ≥50% leadership, ≥20% targeting women clients)?”

    - Sustainability: “What factors will determine whether startups continue to scale post-project?”

- Interview Consent Script

  - Short statement used before interviews, covering:

    - Purpose of the evaluation

    - Voluntary nature of participation

    - Confidentiality/anonymization

    - Use of information (for evaluation only, no attribution without consent)

- Document Review Protocol / Document Matrix

  - A simple table used during desk review showing:

    - Document name

    - Evaluation criteria addressed

    - Key evidence extracted

    - Notes on inconsistencies (e.g., 5 vs ≥6 startups)

- Co-Financing Verification Template

  - A small matrix to compare:

    - Pledged co-financing (by source)

    - Reported actual (cash / in-kind)

    - Evidence source (letters, contracts, reports)

    - Notes on variance

## Annex 8. Survey / Questionnaire

UNIDO HQ (Project Manager, CTI + Gender/Safeguards focal point)

Purpose: Oversight, accountability, alignment with UNIDO/GEF standards.

Relevance & Coherence - How did the project align with UNIDO’s mandate and GEF-7 priorities on climate resilience? - Were there synergies or overlaps with other UNIDO/UN system initiatives in Africa? Effectiveness - Did the project meet its main outputs (≥6 startups, gender thresholds, 2 investment briefs, talent placements, blogs/events)? - How did UNIDO assess and validate reported results (esp. overshoot on beneficiaries/hectares)? Efficiency - How effective was collaboration between UNIDO HQ, BFA Global, and PSC? - Were resources allocated and monitored efficiently (considering no-cost extension)? Sustainability - What measures are in place to ensure results (startup growth, investor networks, gender inclusion) will continue beyond the GEF project? - How did UNIDO monitor environmental and social safeguards (ESS)? Cross-cutting - How did UNIDO assess gender marker 2A compliance and the Gender Action Plan? - What lessons should UNIDO take forward for GEF-9 programming?

Executing Partner (BFA Global – Project Director, M&E Lead)

Purpose: Implementation, adaptive management, reporting.

Relevance & Coherence - How were startups sourced and selected? Why 5 vs. 6 vs. 7 (including co-financed startups)? - How was gender considered in selection (≥30% women-led, ≥50% leadership)? Effectiveness - What outputs were achieved? Where did you fall short (e.g., gender thresholds, briefs)? - How do you explain the large overshoot in beneficiaries and hectares compared to targets? Efficiency - How did you track implementation against monthly/annual work plans? - Were any M&E tools/templates developed and applied consistently? Sustainability - What is the likelihood that startups continue scaling beyond project funding? - How are investor networks and talent placements being sustained? Cross-cutting - How did you integrate gender, ESS, and safeguards into venture-building? - What lessons have you documented internally for replication?

Government / GEF Operational Focal Points (Kenya, Nigeria, Rwanda)

Purpose: National ownership, policy alignment, stakeholder perspective.

Relevance & Coherence - How relevant was the project to your national climate and digital finance priorities? - Did it complement or overlap with other initiatives in your country? Effectiveness - Were you consulted in startup selection or PSC decisions? - How do you view the project’s impact on local ecosystems (regulation, market development)? Efficiency - Did reporting mechanisms (PSC, briefings) keep you informed and engaged? - Were government expectations met within the project timeframe? Sustainability - Do you expect the supported startups to continue growing and benefiting communities? - What regulatory or institutional factors could enable or block sustainability? Cross-cutting - How satisfied are you with the project’s gender and safeguards mainstreaming? - Would you recommend scaling this model nationally or regionally?

Startups (2–3, incl. ≥1 women-led)

Purpose: Capture private-sector beneficiary perspective.

Relevance & Coherence - Why did you join the program? Was the support relevant to your needs? - Did project goals align with your business model and target communities? Effectiveness - What specific venture-building or investment-readiness support did you receive? - How did the project contribute to your growth (funding raised, users reached, hectares managed)? Efficiency - Was support timely, accessible, and cost-effective? - How burdensome were reporting and M&E requirements? Sustainability - Do you expect to sustain/scale these solutions after project closure? - What are the main risks to your continued growth? Cross-cutting - Did the project help address gender inclusion (as a women-led company, or in your services)? - How did safeguards (ESS, social/environmental) affect your operations?

Investors (1 global investor engaged via briefs)

Purpose: Validate catalytic impact, co-financing.

Relevance & Coherence - Did the investment briefs/engagement events change how you view climate adaptation opportunities? - How well did the project complement your existing portfolio strategy? Effectiveness - Did you invest in or build stronger ties with the startups? - How did the project facilitate meaningful investor/startup matchmaking? Efficiency - Was investor outreach and communication well organized? - What could have been done to make investment opportunities more compelling? Sustainability - Are you likely to continue engaging with these startups beyond the project? - What would sustain investor appetite for fintech-for-resilience in Africa?

Junior Expert / Beneficiary Representative

Purpose: Capture end-user and human-capacity building experience.

Relevance & Coherence - Why did you join as a junior expert / partner user group? - Was the placement/support relevant to your career or community needs? Effectiveness - What skills or knowledge did you gain? - How has the project changed your ability to contribute to climate resilience? Efficiency - Was the placement/support well organized and adequately resourced? Sustainability - Do you see opportunities to continue applying what you learned? - How has your participation influenced your career trajectory / community resilience? Cross-cutting - Were gender and inclusion issues adequately addressed in your experience?

Cross-Cutting Key Informant (e.g., SA Treasury/Reserve Bank, Uganda regulator)

Purpose: Provide policy/system-level perspective.

Relevance & Coherence - How does fintech-enabled resilience align with national policy or regulatory frameworks? - Did this project add value to the existing national/regional ecosystem? Effectiveness - What observable changes (if any) have you seen in fintech regulation, investment, or climate resilience awareness? Efficiency - Was government engagement through PSC or other mechanisms effective? Sustainability - Do you see pathways to institutionalize or scale up project outcomes nationally? Cross-cutting - What role do you think gender-responsive policies should play in sustaining these outcomes?

## Annex 9. Statistical Data from Evaluation Survey / Questionnaire Analysis

As part of the Terminal Evaluation of the Acceleration of Fintech-Enabled Climate Resilience Solutions Project (GEF ID: 10927), questionnaires and semi-structured interviews were conducted with key stakeholder groups, including startups, junior experts, investors, government representatives, UNIDO staff, and BFA Global. While the evaluation did not deploy a large-scale quantitative survey, structured questions were applied consistently across respondent groups to allow for aggregation of responses and analysis.

1. Respondent Groups and Coverage

| Stakeholder Group | Targeted | Interviewed / Completed | % Response |
| --- | --- | --- | --- |
| Startups (founders/teams) | 5 | 5 | 100% |
| Junior experts | 1 | 1 | 100% |
| Gender Beneficiary | 1 | 1 | 100% |
| Investors (Circle of Investors) | 1 | 1 | 100% |
| Government representatives | 3 | 0 | 0% |
| UNIDO HQ staff | 3 | 3 | 100% |
| BFA Global staff | 3 | 3 | 100% |
| Total Interviews | 17 | 14 | 83% |

2. Aggregated Findings

Relevance:

- 100% of startups rated the support as “highly relevant” to their business needs.

- Investor noted that knowledge products (e.g., State of Climate Tech Africa 2023) improved their understanding of climate adaptation investability.

- Government representatives did not participate in the terminal evaluation.

Effectiveness:

- 5 of 6 startups confirmed venture-building was transformative for professionalization (finance, CRM, impact dashboards).

- Junior reported their placements had a “substantial impact” on startup operations.

Efficiency:

- 2 of the 5 startups interviewed flagged some TA activities (e.g., video production) as high-cost relative to value.

- UNIDO and BFA staff confirmed that biweekly check-ins improved efficiency, though procurement delays increased transaction costs.

Sustainability:

- 4 of 6 startups secured follow-on funding; amounts ranged from USD 179,000 (Farmz2U) to USD 2.6M (Farm to Feed).

- Investor stated they were “likely to continue engagement” with startups post-project.

- 2 out of 6 startups were concerned about sustainability.

Cross-cutting (Gender and Innovation):

- 3 women-led startups were supported, exceeding the target of 2.

- 75% of startups indicated gender targets helped raise visibility, but systemic barriers (land, irrigation, finance) remain unaddressed.

- Investors and startups agreed fintech elements were valuable but not sufficient; blended models (fintech + agri/AI/waste-to-value) were necessary.

## Annex 10. Workplan and Deliverables

| Phase | Dates | Tasks / Activities | Lead Responsibility | Outputs / Deliverables |
| --- | --- | --- | --- | --- |
| 1. Preparation & Document Review | 20–26 Aug 2025 | Review core documents: CEO Endorsement, Results Framework, PSC minutes, inception reports, work plans (2023–2025), PIRs, financial reports, knowledge outputs. Identify inconsistencies and draft preliminary findings. | Evaluator (Burnett) + Delegated support | Evidence tables; adjusted evaluation questions; stakeholder list |
| 2. Inception Report | 27 Aug – 1 Sept 2025 | Draft inception report (sections 1–7) including ToC, evaluation matrix, stakeholder plan, methodology, and timeline. Submit to the UNIDO Evaluation Office for clearance. | Evaluator | Draft Inception Report (1 Sept 2025) |
| 3. UNIDO Briefing & Interview Scheduling | 2–5 Sept 2025 | Virtual briefing with UNIDO PM team; present ToC, evaluation matrix, consultation plan. Finalize interview schedule with BFA Global and OFPs. | Evaluator (leads) + Support (logistics) | Briefing slide deck; interview calendar |
| 4. Data Collection – Interviews | 8–12 Sept 2025 | Conduct 10–15 semi-structured interviews (UNIDO HQ, BFA Global, OFPs, startups, investor, junior expert, policy informant). Delegated staff support note-taking. | Evaluator (leads) + Delegated support (notes) | Interview transcripts/notes; emerging findings |
| 5. Data Analysis & Drafting | 13–25 Sept 2025 | Synthesize evidence by criterion; triangulate findings from docs and interviews; apply GEF rating scales. Draft evaluation report (delegated drafts document-based sections; evaluator drafts conclusions & recommendations). | Evaluator (leads) + Support (first drafts, annexes) | Draft Terminal Evaluation Report |
| 6. Submission of Draft Report | 26 Sept 2025 | Submit Draft Terminal Evaluation Report to UNIDO Evaluation Office for review and circulation. | Evaluator | Draft Report (26 Sept 2025) |
| 7. Presentation of Findings | 15 Oct 2025 | Virtual presentation to UNIDO HQ, BFA Global, OFPs, and stakeholders. Include preliminary ratings, lessons, and recommendations (plus GEF-9 policy relevance). | Evaluator | Findings presentation deck (15 Oct 2025) |
| 8. Revision & Finalization | 16 Oct – 14 Nov 2025 | Revise draft report based on feedback from UNIDO, BFA Global, and country stakeholders. Strengthen recommendations and finalize annexes (ToR, matrix, interview list, docs reviewed). | Evaluator (leads) + Support (editing, formatting) | Final Terminal Evaluation Report |
| 9. Submission of Final Report | 15 Nov 2025 | Submit final report to UNIDO Evaluation Office for quality assurance and upload to GEF portal. | Evaluator | Final Report (15 Nov 2025) |

## Annex 11. Reconstructed Theory of Change

-Reduced vulnerability of climate-affected populations
-Contribution to GEF-7 climate resilience objectives

Outcomes

Outputs

Impact

Activities

Inputs

Increased resilience of 407,000+ beneficiaries

Assumptions, enablers

-﻿﻿Enhanced private-sector capacity
-﻿﻿More inclusive ecosystem

﻿﻿278,000 ha under improved management

-Scaled climate resilience solutions
-﻿﻿Improved investor readiness

-Gender integration in business models
﻿﻿-Emerging talent pipeline

﻿Strengthened operational systems

Assumptions, enablers

-Scaled climate resilience solutions

-Improved investor readiness

-Gender integration in business models

-Emerging Talent Pipelines

-Strengthened operational systems

Assumptions, enablers

Startup Acceleration: Six startups supported with tailored venture-building.

Talent Development: 11 junior experts placed to strengthen startup operations.

Investor Engagement: Circle of Investors expanded; demo days and curated introductions.

Assumptions, enablers

Knowledge Products: 11 reports/briefs produced, incl. State of Climate Tech Africa 2023

Management & Governance: PSC meetings, Visible platform reporting, UNIDO–BFA coordination.

Venture-building Technical

Junior Expert Placements

Investor Matchmaking

Assumptions, enablers

Knowledge Products

Government Engagement

Investor confidence in adaptation startups increases.

Capital mobilized for scaling early-stage ventures.

Curated introductions between startups and investors were facilitated, with 52 direct matches made, contributing to the mobilization of USD 3.3 million in follow-on funding across four startups. Investor convenings were organized through demo days, COP side events, and webinars, which showcased startups and improved investor awareness of adaptation as an investable sector. Investor-facing knowledge briefs and investment theses were published and disseminated, enhancing the credibility.

Startups professionalize operations and systems.

Ventures demonstrate improved investor readiness.

Gender targets lead to systemic inclusion. Follow-on funding cycles are long but can be bridged with catalytic finance. Ecosystem initiatives are complementary.

Partnerships with universities and donors enable talent pipeline continuation.

ACTIVITIES

SHORT TERM

OUTCOMES

OUTPUTS

Junior experts filled gaps in areas such as product redesign, CFO-level financial management, farmer engagement, and marketing support. Several placements were retained beyond the project period, demonstrating proof-of-concept for talent pipeline approaches to support green jobs. Startups reported that junior experts were “transformative,” significantly improving organizational efficiency.

Component 1: Acceleration (Venture-Building)

Sourcing and selecting 6 startups across Kenya, Nigeria, Rwanda, South Africa, and Uganda. Delivering embedded venture-building technical assistance (finance, CRM, impact dashboards, supply chains). Providing sector-specific mentorship and peer learning across startups. Supporting startups in professionalization (financial modelling, investor readiness, product redesign).

Component 2: Investor and Ecosystem Engagement

Establishing and growing the Circle of Investors (200+ members, 79% with women in leadership). Organizing curated introductions, demo days, deal rooms, and COP side events. Publishing investor-facing briefs and investment theses. Convening webinars and ecosystem dialogues with policymakers and investors.

Component 3: Talent Development

Recruiting, training, and placing 11 junior experts with startups. Embedding junior experts into operational and technical roles (marketing, finance, farmer outreach, product redesign). Providing professional development and mentoring for junior experts. Testing the model as a talent pipeline for future climate-fintech ecosystems.

Knowledge products and thought leadership position adaptation as investable. Digital tools (Visible platform, dashboards) streamline reporting and investor readiness.

Investor networks (Circle of Investors, DFIs, ecosystem partners) expand access to capital.

ENABLERS

Startups have capacity to absorb TA and institutionalize systems. Policymakers are open to engaging with innovation and aligning with national plans.

ASSUMPTIONS

Resilience strengthened among vulnerable farmers and communities (improved food security, reduced climate risk).

Land management improved, with hundreds of thousands of hectares under more sustainable practices.

Private-sector capacity expanded for delivering climate adaptation solutions at scale.

Gender inclusion advanced through women-led startups, women farmers reached, and women in leadership within investor networks.

Adaptation recognized as investable, attracting greater DFI and private capital into early-stage ventures.

Contribution to GEF-7 goals on climate resilience, innovation, and systemic ecosystem strengthening.

Policymakers and investors access credible evidence.

Adaptation positioned as an investable sector.

Six early-stage climate–fintech startups (three women-led) were sourced and selected through a transparent process across Kenya, Nigeria, Rwanda, South Africa, and Uganda. Each startup received tailored venture-building support, including the embedding of advisors who worked as quasi-team members to strengthen financial modelling, CRM systems, impact dashboards, and supply-chain logistics. Startups institutionalized new operational systems, such as digital dashboards, financial management platforms.

IMPACTS

Component 4: Knowledge Products and Thought Leadership

Producing 11 knowledge products, including:

-Disseminating findings via events, social media (14,000+ impressions), and DFI networks.

-Positioning climate adaptation as an investable sector through thought leadership.

A total of 11 knowledge products were produced and disseminated, including the flagship State of Climate Tech in Africa 2023 report, which received 14,000+ impressions. A Gender–Climate Nexus Brief was developed, categorizing startups into “gender aware,” “gender accommodating,” and “gender transformative,” and informing future gender integration strategies.

Startups address critical capacity gaps.

Junior experts gain climate–fintech experience.

Vienna International Centre

Wagramerstr. 5, P.O. Box 300,

A-1400 Vienna, Austria

+43 1 26026-0

www.unido.org

evaluation@unido.org

Data to be validated by the Consultant

UNIDO. (2015). Director General’s Bulletin: Evaluation Policy (UNIDO/DGB/(M).98/Rev.1)

UNIDO. (2006). Director-General’s Administrative Instruction No. 17/Rev.1: Guidelines for the Technical Cooperation Programme and Project Cycle (DGAI.17/Rev.1, 24 August 2006)

The evaluator will be provided with a Guide on how to prepare an evaluation inception report prepared by the UNIDO ODG/EVQ/IEV.