UN Environment GEF PIR Fiscal Year 2019

- July 2018 to 30 June 2019)

| - Identification |  |  | GEF ID: 4020 | Umoja no.: P1-33GFL-001304 |  |
| --- | --- | --- | --- | --- | --- |
| Project Number + Project Title |  |  | Market Policy and legislative development for mainstreaming sustainable management of marine and coastal ecosystems in Lebanon |  |  |
| Duration months | Planned |  | 36 |  |  |
|  | Extension(s) |  | n/a |  | n/a |
| Division(s) Implementing the project |  |  | Ecosystems Division, UN Environment, Kenya |  |  |
| Name of co-implementing Agency |  |  | N/A |  |  |
| Executing Agency(ies) |  |  | Current PCA holder: The International Union for the Conservation of Nature, Regional office for West Asia First PCA holder: Ministry of Environment, Lebanon |  |  |
| Names of Other Project Partners |  |  | Other partners: University of Balamand, CNRS, TCNR, PINR and MORES |  |  |
| Project Type |  |  | Medium Size Project |  |  |
| Project Scope |  |  | National |  |  |
| Region (delete as appropriate) |  |  | West Asia |  |  |
| Names of Beneficiary Countries |  |  | Lebanon |  |  |
| Programme of Work |  |  | PoW 2018-19, Subprogramme 3 – healthy and productive ecosystems |  |  |
| GEF Focal Area(s) |  |  | Biodiversity |  |  |
| UNDAF linkages |  |  | UNSF 2017 – 2020 (Core Priority 3) |  |  |
| Link to relevant SDG target(s) and SDG indicator(s) |  |  | SDG 14: Life below water |  |  |
| GEF financing amount |  |  | Total: $ 950,000 For the Second PCA: 654,265.50 US $ |  |  |
| Co-financing amount |  |  | Total: 1,423,000 US$ By IUCN: 325,000 US $ |  |  |
| Date of CEO Endorsement |  |  | 2/11/2010 |  |  |
| Start of Implementation |  |  | 1/11/2013 For the 2nd PCA/ IUCN: 20/1/2018 |  |  |
| Date of first disbursement |  |  | 20/3/2013 For 2nd PCA: 20/2/2018 |  |  |
| Total disbursement as of 30 June |  |  | Total (IUCN & MoEnv): 445,735 USD 2nd PCA (IUCN): 150,000 USD |  |  |
| Total expenditure as of 30 June |  |  | Total (MoEnv & IUCN): 473,654 USD 2nd PCA (IUCN): 177,920 USD (status of March 2019) |  |  |
| Expected Mid-Term Date |  |  | 30.10.2019 |  |  |
| Completion Date |  | Planned | 31/12/2020 |  |  |
|  |  | Revised |  |  |  |
| Expected Terminal Evaluation Date |  |  | 30.6.2021 |  |  |
| Expected Financial Closure Date |  |  | 30.11.2021 |  |  |

- OVERVIEW OF PROJECT STATUS

| UN Environment Subprogramme(s) PoW 2018-19 Subprogramme 3: Healthy and productive ecosystems | Specify the relevant Expected Accomplishment(s) & Indicator(s) EA a) The health and productivity of marine, freshwater and terrestrial ecosystems are institutionalized in education, monitoring and cross-sector and transboundary collaboration frameworks at the national and international levels. Indicators: (ii) Increase in the number of countries and transboundary collaboration frameworks that demonstrate enhanced knowledge of the value and role of ecosystem services. iii) Increase in the number of countries and groups of countries that improve their cross-sector and transboundary collaboration frameworks for marine and terrestrial ecosystem management EA b) Policymakers in the public and private sectors test the inclusion of the health and productivity of ecosystems in economic decision-making Indicator: (i) Increase the in number of public sector institutions that test the incorporation of the health and productivity of marine and terrestrial ecosystems in economic decision-making |
| --- | --- |
| - The project is enhancing knowledge base and understanding of coastal and marine bird species in Lebanon: their importance, identification and geographic distribution with expert recommendations for their conservation. - The project is currently preparing guidelines on mainstreaming biodiversity conservation in the EIA process for development projects affecting marine and coastal ecosystems, and a checklist for the inspection and monitoring of necessary environmental mitigation measures related to biodiversity conservation and protection, which will directly contribute to strengthening the policy and regulatory framework for mainstreaming biodiversity in Lebanon. - The Project has produced a Monitoring Protocol for Marine Invasive Alien Species (lAS), supported with a capacity building program and with the suitable recommended measures to prevent and control lAS. - The project has also produced fact sheets on the marine IAS in Lebanon which will enhance the knowledge base of a wide range of stakeholders about the IAS. - The project is contributing to EA (b) indicator (i) through a capacity building program which is targeting different types of stakeholders from (Ministry of Environment staff, relevant ministries, academics and research institutions and the general public). The project introduced the concept of Red Listing to the research community concerned with the marine and coastal biodiversity, The project introduced the concept of protected area management effectiveness to stakeholders involved in coastal protected area management, the project contributed in increasing the awareness of the importance of marine birds, and of the impact of IAS on the marine environment. |  |

For all GEF 6 and later projects:

| GEF Core Indicators | Indicative expected Results |
| --- | --- |
|  | Indicative expected Results |
| N/A, GEF4 project |  |

| Planned linkages with UNDAF | This project is a GEF 4 project which was prepared and designed prior to the issue and release of the current United Nations Strategic Framework for Lebanon UNSF 2017 – 2020. However, we see that the project strongly contributes to this framework, especially to Core Priority 3, which states that “Lebanon reduces poverty and promotes sustainable development while addressing immediate needs in a human rights/gender sensitive manner”. This priority area entails that the UN will pursue a ‘dual-track’ approach that focuses both on mitigating the impact of the Syrian conflict and addressing pre-existing structural constraints. UN support to address these socio-economic challenges will be provided in three areas. These consist of strengthening productive capacities and generating inclusive growth, improving equitable access and delivery of social services, and promoting environmental protection and effective natural resource management. The project contributes to this core priority area as it is directly promoting the sustainable management of marine and coastal ecosystems through: a. mainstreaming of marine and coastal biodiversity in the legislative framework; b. enhancing the knowledge base on threats to marine biodiversity like IAS and hotspots of marine and coastal biodiversity; c. Provide a data base for decision makers, research community and general public on marine and costal biodiversity in Lebanon; and d. Produce awareness material like factsheets, booklets for different types of stakeholders on marine and coastal biodiversity. |
| --- | --- |

| Planned contribution to relevant SDG target(s) and SDG indicator(s) | The project contributes to SDG 14: life under water, target 2. 14.2.1 Proportion of national Exclusive Economic Zones managed using ecosystem-based approaches. The project contribution towards this target includes: - Enhanced awareness and capacity of local institutions related to on the identification of marine invasive species, which are a major threat to marine and coastal ecosystems in Lebanon. - Enhanced management of coastal area by enhancing the awareness of marine birds, their identification, importance and geographic distribution. - Enhancing the awareness of local communities of the threatened and endangered species through a training program on the Red listing of marine species. - Enhancing the capacity towards effective management of marine protected areas, through training on protected area management effectiveness. |
| --- | --- |

| Implementation Status | FY 2014 | FY 2015 | FY 2016 | FY 2017 | FY 2018 | FY 2019 |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  | 1st PIR | 2nd PIR | 3rd PIR | 4th PIR |

| Development Objective Rating FY | FY 2014 | FY 2015 | FY 2016 | FY 2017 | FY 2018 | FY 2019 |
| --- | --- | --- | --- | --- | --- | --- |
|  | unknown | unknown | MS | MU | MS | S |

| Implementation Progress Rating | FY 2014 | FY 2015 | FY 2016 | FY 2017 | FY 2018 | FY 2019 |
| --- | --- | --- | --- | --- | --- | --- |
|  | unknown | unknown | MS | MU | MS | S |
| Project implementation Progress: - Training on the Assessment of the Management Effectiveness of Protected Areas in Lebanon. Objective: Train the management teams of the Marine Protected Areas MPAs in Lebanon to use the Management Effectiveness Tracking Tool in order to measure MPAs performance and progress and to develop accordingly an operational manual to enhance their performance and effectiveness. -Workshop date: 11 - 13 October 2018 Workshop Location: Byblos, Lebanon Name of consultant: Imen Meliane, WCPA Regional Vice Chair for North Africa, West Asia and middle East - Development of a Monitoring Protocol for Marine Invasive Alien Species (lAS), specially adopted for Lebanese Coastal and Marine Environment, supported with a capacity building program and with the suitable recommended measures to prevent and control lAS, and awareness material (fact sheets on marine invasive species). Two training workshops parallel to the development of the protocol on marine invasive species were conducted: - 1st workshp on IAS: - Objective: Train main diving clubs and users of ports in Lebanon on early detection and reporting of IAS - Workshop date: 26 - 27 October 2018 - Workshop Location: Tyre, Lebnon - 2nd Workshop on IAS: - Objective: Train officials, experts and managers in national institutions on IAS evaluation and monitoring techniques. - Workshop date: 9 - 10 November 2018 - Workshop Location: Beit Al Madina, Tyre – Lebanon - Consultant: Nancy Sayar and Michel Bariche. - Assessment study related to coastal and marine birds of Lebanon: Objectives of the study: - Elaboration of a detailed updated list of the marine sea birds of Lebanon based on literature review, in addition to field visits. - Development of detailed factsheets for the most significant coastal and marine bird species in Lebanon. - Preparation of draft recommendations for adoption by the relevant national authorities, and recommendations specific for fishermen and general public. - Conduct a National awareness workshop - National Awareness Workshop objective: To raise awareness about the coastal and marine birds of Lebanon and to disseminate the outputs of the factsheets and awareness materials activities and measures to protect the coastal and marine species Workshop Date: 11 March 2019 Workshop Location: Beirut – Lebanon Consultant: Dr. Ghassan Jaradi, Private Consultant - IUCN Red List Training Workshop Objective: Training marine experts from public and private sector to build capacities on how to use IUCN Red List categories and criteria towards a national red list of threatened species in Lebanon with focus on marine species. Workshop Date: 13- 14 June 2019 Workshop Location: Byblos- Lebanon Consultant: Catherine Numa, IUCN Species Programme coordinator, IUCN- MED - Study of coastal and marine birds of Lebanon “An Atlas of Distribution” Objective: The objectives of this activity is to develop an Atlas of distribution for the coastal and marine bird species in Lebanon, which will contribute in achieving the following: - Enhancing and increasing the availability and access to spatial data that could support the decision- making process related to mainstreaming the conservation of marine and coastal biodiversity into the coastal zone planning and management - Contributing to feeding the project online data base with data and maps on the distributions of marine bird species with importance for conservation - Elaborating maps, in an Atlas, illustrating where and why birds are most under threat, and what is being done to protect them - Examine key factors influencing the spatial distribution of birds along the Lebanese coast - Conduct a national workshop to raise awareness about the coastal and marine birds of Lebanon and to disseminate the output of this activity (The Atlas of distribution and species accounts) Consultant: Ghassan Jaradi Status: Contractual arrangements complete, and the assignment is in progress. 5- Guidelines on mainstreaming biodiversity conservation in the EIA process for development projects affecting marine and coastal ecosystems, and a checklist for the inspection and monitoring of necessary environmental mitigation measures related to biodiversity conservation and protection. Objectives: The purpose of this assignment is to enhance the mechanisms for protecting priority coastal areas by enhancing the EIA legal frame work and licensing procedures and enhancing the capacity to mainstream biodiversity and sustainable management in EIA’s related to projects with potential impacts on coastal biodiversity Status: Assignment TOR prepared, RFP released, bid analysis and consultant selection complete. Contractual arrangements with the selected consultant are underway. - Assessment of Climate Change Impact on Lebanon coastal zone Objectives: - Conduct a literature review on the vulnerability of marine biodiversity and ecosystems in Lebanon to climate change, including the review of Lebanon’s second and third national communication to UNFCCC and the NBSAP. - Identify knowledge gaps for the full assessment of the vulnerability of the marine biodiversity and ecosystems to climate change, including meteorological data. - Identify, through experts’ meetings, necessary policy measures and adaptation mechanisms and actions for the increase of resilience of Lebanon’s marine biodiversity and ecosystems to climate change, and Identify institutional and policy and capacity building challenges for minimizing the risk posed by climate change to marine biodiversity and ecosystems. - Identify one marine biodiversity hotspot area and conduct site specific adaptation analysis that encompasses environmental aspects of species and ecosystems but also socio economic aspects of the fishing communities that depend on them. - Taking into consideration the national context, develop comprehensive site specific adaptation plans that comprise prioritized actions, list of related needed resources, allocated responsibilities and timeline, and good practices examples from the Mediterranean region supported by local and national stakeholder consultations. - Provide information that is required to produce a draft Handbook or brochure for raising public awareness about the impact of climate change on the coastal zone of Lebanon. - Conduct a consultation workshop to validate the finding of this assessment study. Status: TOR of the assignment reviewed and updated, negotiations with the University of the Balamand are on- going to finalize the contractual arrangements to conduct this assignment. Challenges: A number of challenges are facing the implementation of the project activities: - The project was designed and approved in 2010, including the activities and budget allocation. We are trying to adapt the activities to the current needs of the Lebanese Ministry of Environment but we face the challenge of insufficient budget allocation for a number of consultancies. - Some consultancies require very specific expertise which could be hard to find in Lebanon, or restricted to a limited number of experts. This recurrently leads to raise the cost of project activities compared to what was expected in the original design of the project. |  |  |  |  |  |  |

| Risk Rating |  | FY 2014 | FY 2015 | FY 2016 | FY 2017 | FY 2018 | FY 2019- |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | e.g. L | L | H | M | M to L |
|  | The project has undergone a major change in its management set up to overcome the challenges reported in the 2017 PIR. The major change was that The Ministry of Environment asked IUCN to handle the execution of the project through a PCA signed between UN Environment and IUCN-ROWA, which was signed and brought to implementation on 20/1/2018. Although this is largely a positive move to push towards the effective implementation of the project activities considering IUCN status as an international organization with access to large repository of experts in all fields related to biodiversity conservation , and well established procurements policies, systems and procedures which advance could advance the implementation of the project activities, there are still a number of risks that may influence the effective implementation of project activities: - The project document was finalized and approved in 2010, which is 9 years from now. And a major risk for implementation is to check the validity of project deliverables in the light of the current emerging needs of the Ministry of Environment. To avoid the risk of invalidity of project activities, IUCN keeps close coordination with the Lebanese Ministry of Environment and other stakeholders and seeks to adapt project activities to the current actual needs of the Ministry of Environment, within the original framework of the project document. - As the project was designed in 2010, the project budget allocated for a number of activities is found hardly sufficient to accomplish the ambitious deliverables set by the project document due to the time lapse between project design and current implementation. - Access and availability to data still poses a risk to the implementation of some of the project activities. We are working to lower the rank of this work from medium to low through the engagement of relevant academics in project activities, acquiring experts in the field to be engaged in project activities. |  |  |  |  |  |  |

| Stakeholder engagement | The project activities involved active participation of different types of stakeholders from government, Ngo and academic institutions. Each project activity carried out within the current reporting period was designed to target certain types of stakeholders. Below are examples on the type if engagement of the different types of stakeholders: - Strategic partners and government: these are mainly responsible for shaping land use and land management strategies, environmental laws, bylaws and regulations affecting marine and coastal biodiversity. These were involved in project training workshops concerned with raising awareness on monitoring marine invasive species (The 2nd IAS workshop), workshop to present the results of the studies on coastal and marine birds (1 workshop), PA management effectiveness (1 Workshop). - Academic and research institutions: Representatives from the research community and academic institutions in Lebanon are invited to project workshops as their scientific input and recommendations are important for the project. One of the project workshops (The IUCN’s Red Listing training workshop) was mainly targeting this group of stakeholders. The workshop introduced the process of red listing to the research community and institutions related to marine and costal environment in Lebanon. - Private sector: The private sector, namely the diving clubs and users of the port were targeted in the awareness workshop on the early detection of marine IAS in Lebanon. IUCN has also addressed all private companies that are licensed to practice EIA in Lebanon and shared the RFP for the consultancy “Guidelines on mainstreaming biodiversity conservation in the EIA process for development projects affecting marine and coastal ecosystems, and a checklist for the inspection and monitoring of necessary environmental mitigation measures related to biodiversity conservation and protection”. The findings of this consultancy will also be shared and discussed with the EIA practitioners in Lebanon (mainly private companies). They will also have the chance to contribute and give feedback during the consultation workshop planned towards the end of this assignment. - Public (NGO’s local communities, etc): The general public and local communities are targeted by being invited to awareness workshops. One of the IAS workshops targeted the general public and users of the Ports. (the 1st IAS workshop). Another way to engage the general public is through sharing the publications and fact sheets and other forms of awareness material produced by the project. They are also engaged through social-media platforms that promote the project activities like IUCN’s social media platforms that keep the general public updated and engaged in the project activities. Other types of stakeholder engagement: The project management is trying to adapt the project activities to the current needs of the Ministry of Environment to the extent possible in the light of the rime lapse between project design and implementation. IUCN, and through the focal point at the Ministry of Environment conducted thorough consultation during the preparation of the TOR’s of the project consultancies. The project focal point at the Ministry of Environment consulted the EIA division regarding the draft TOR for the Consultancy “Guidelines on mainstreaming biodiversity conservation in the EIA process for development projects affecting marine and coastal ecosystems, and a checklist for the inspection and monitoring of necessary environmental mitigation measures related to biodiversity conservation and protection”. Their feedback was integrated in the final TOR and RFP to make sure that the findings of this consultancy will serve the current mainstreaming needs and will be usable by the Ministry and the EIA practitioners. Challenges: The main challenge for stakeholder engagement related to try to accommodate the needs of the different groups with conflicting interests and priority. A challenge that is being addressed by seeking proper design of events and segregating workshops based on the objectives and target groups as we did with the two IAS workshops. |
| --- | --- |

| Gender mainstreaming | The project seeks to achieve gender balance through the implementation of its activities. Project workshops, training programs and events have large contribution and participation from female experts. For example, female participants constitute around/ more than 35% of the participants in most project workshops. For consultancy services delivered through the project, we tried to encourage and seek female experts, whenever applicable to deliver project consultancies. For example, during the FY 2019 2 training workshops were conducted by female experts (The Red list and the IAS). The IAS consultancy was also coordinated by a female expert. |
| --- | --- |

| Knowledge activities and products | The project has developed the following knowledge products: - Developing and designing an educational booklet on birds of Lebanon for kids - Assessment study and a factsheet on the marine birds of Lebanon in English Language translated into Arabic. (Click Here) - Producing a factsheet on the marine invasive alien species in Lebanon, translated into Arabic. (English & Arabic version) - Field manual for monitoring invasive alien species in the marine environment of Lebanon (English & Arabic version) |
| --- | --- |

| Stories to be shared |  |
| --- | --- |

- RATING PROJECT PERFORMANCE AND RISK

Based on inputs by the Project Manager, the UNEP Task Manager will make an overall assessment and provide ratings of:

- Progress towards achieving the project Results(s)- see section 3.1

- Implementation progress – see section 3.2

Section 3.3 on Risk should be first completed by the Project Manager. The UNEP Task Manager will subsequently enter his/her own ratings in the appropriate column.

  - 3.1	Rating of progress towards achieving the project Results(s)

| Project objective and Outcomes | Indicator | Baseline level | Mid-Term Target or Milestones | End of Project Target | Observations/ justification on rating | Progress rating |
| --- | --- | --- | --- | --- | --- | --- |
| Objective: Sustainable Management of Marine and Coastal Biodiversity and Habitats through Policy and Legislative Development and Mainstreaming in Lebanon | 1. Policy and regulatory frameworks governing sectors outside the environment sector incorporate measures to conserve and sustainably use biodiversity | Policy and regulatory frameworks governing sectors outside the environment sector do not include measures to conserve and sustainably use biodiversity. | Conservation policy reports are prepared and publicized Recommendations of law enforcement mechanisms are prepared and communicated to stakeholders. | Scenarios for incorporation of BD priorities into national plans are developed and communicated to relevant authorities. | -Lebanon issued Decree No.42 of 2017- Division of marine waters subject to the jurisdiction of the Lebanese State into blocks. The Decree provides for a buffer zone where petroleum activities are not allowed except with a decree issued by the Council of Ministers. The buffer zone extends along the borders of the Lebanese coast from the far north to the far south. -Preparation of guidelines on mainstreaming biodiversity conservation in the EIA process for development projects affecting marine and coastal ecosystems is in process. | S |
|  | 2. Nationally adopted measures for the implementation of the SAP-BIO, ICZM protocol, CC adaptation and CBD. | SAP-BIO dated 2002 and needs revision ICZM protocol was ratified in 2014 and requests a law and strategy CC adaption/ UNFCCC needs revision | SAP BIO update ICZM law and strategy drafted CC impact and adaptation measured | CC adaptation measures are adopted by key stakeholders | The 2002 report of the SAP-BIO project is updated. The project contributes to the update of two marine Protected area management plans. An assessment of CC impact on the coastal area of Lebanon with recommendations on adaptation measures is in process. | MS |
|  | 3. Reduced threats to globally important BD through established sustainable use practices and cooperation agreements at various scales | The Ministry of Environment‘s agenda towards the establishment of a network of protected areas. Efforts to achieve one of H2020 targets related to this project which consists of promoting sustainable management of the sea and coastal zones and taking urgent action to put an end to the degradation of coastal zones by “bringing at least 10% of the marine and coastal surface under some form of Protection”. | Marine and coastal BD priorities and key sites are identified. Raising awareness of stakeholders about marine and coastal BD. | Sustainable development and management plans are developed for 2 pilot sites. | 5 training workshops to enhance awareness and access to knowledge on the key issues like: PA management effectiveness, monitoring of IAS, marine and coastal birds, & Red listing of marine species. Designation files for declaring deep sea protected areas are prepared. The project contributed to the update of the management plan of two MPAs. | S |
| Outcome 1: 1.1. Adoption of legal, policy and institutional reforms and changes of practices for improved marine and coastal BD management and improved capacity of national institutions, incl. harmonization of national plans on agreed priorities. | 1. The number of policy documents, legal decrees and regulations (adopted or in process of adoption) that incorporate measures to improve the sustainable use and management of marine and coastal BD. | Very limited inclusion of CZM into sectoral plans, policies and decrees | Policy reports are developed and publicized. Recommendations of law enforcement mechanisms are developed and communicated to stakeholders Priorities of marine and coastal BD are identified and communicated to stakeholders. Existing policies and legislations reviewed. Gaps in existing policies and legislations identified General level of compliance with the current legislation in Lebanon is assessed Root causes of non-compliance assessed and the real problems in non-compliance identified. The measures adopted in Lebanon identified and evaluated, within the framework of regional conventions | Targeted policy and legal instruments show measurable increase in including CZM objectives. | Draft law and ICZM proposal submitted to the cabinet. ICAM reviewed, an ICZM strategy was drafted with consultation with stakeholders. Guidelines on mainstreaming biodiversity conservation in the EIA process for development projects affecting marine and coastal ecosystems, and a checklist for the inspection and monitoring of necessary environmental mitigation measures related to biodiversity conservation and protection are in progress. | S |
|  | 2. The number of institutions and corresponding personnel trained on marine priorities and legal gaps/reforms. | No Training and capacity building programs on CZM |  | Training and capacity programs are developed and implemented in 3 national institutions. | 5 training workshops conducted on marine priorities targeting different stakeholders (MoEnv, Government institutions, research and academic institutions) |  |
| 1.2. Coastal zone planning and management advanced for Lebanon by integrating BD protection, incl. CC adaptation measures, | 1. Number of coastal zone management plans that include BD monitoring and CC adaptation measures. | Very limited knowledge on species status and decline in the identified BD hot spots. No CC adaptation measures included in CZM. Few marine and coastal BD management plans. | Monitoring program for important species in BD hot spots is established. Key sites are identified. Identification of the necessary tools to integrate of protection. mechanisms into CZM plans. Identification of CC impacts and adaptation measures. | BD monitoring program is integrated into CZM plans 2 pilot sites have established procedures Measurable increase in identified priority areas and CZM plans. CC adaptation measures are induced in CZM plans. | TOR’s prepared, and Contractual arrangements with the University of the Balamand are in process for assessment of CC impact on the coastal area of Lebanon incl. adaptation measures. Preparation of EIA guidelines mentioned above will also contribute to this outcome. | S |
| 1.3. Sustainable financing mechanism developed for the protection of marine and coastal BD. | Number of financing mechanisms for CZM | No financing mechanisms | Identification of BD economic values and stakeholders needs. | Economic valuation for marine and coastal BD established Mechanisms for sustainable financing developed | Draft TOR prepared for the Economic valuation and will be released in October. | S |
| Outcome 2: 2.1. Enhanced coordination among relevant sectors | 1. The number of sectors participating in the established inter-ministerial committee | Weak or no coordination and involvement of key sectoral agencies in CZM | Inter-ministerial committee is established. | All targeted government entities are actively engaged in inter-ministerial committee | Relevant stakeholders are identified and actively engaged in the project and implementation. The project plan to prepare for the inter-ministerial committee is communicated with the Ministry of Environment. It is delayed due to the political situation Stakeholders’ registry updated after each workshop and activity. | S |
| 2.2. Stakeholder engagement, public involvement, participation and awareness raising initiatives are developed and implemented. | Level of awareness among stakeholder groups | Little awareness about marine and coastal BD | Initiatives for raising awareness are formulated | Measurably improved awareness on CZM issues among stakeholders | TOR’s for a consultancy related to Guidance on awareness and measuring level of improvement in stakeholder awareness will be finalized in October 2019. | S |
|  | The number of different stakeholder groups participating in project activities | Poor stakeholder involvement | Coordination established with national and international partners in BD | All identified stakeholder groups participate in project activities. Project reports, maps and awareness materials are widely available to target groups. | Stakeholders are engaged in project activities, including the American universities, CNRS , MPA managers and others. Several knowledge output are developed (mentioned in the relevant section) and communicated with relevant target groups. The project database is used by the ministry and stakeholders for the management and costal decisions. |  |
| 2.3. More effective networking for information sharing, enhanced intra- and inter-regional knowledge sharing and learning for long-term marine and coastal BD protection and exchange of best practices and lessons learned established with other relevant regional initiatives (i.e. SP for the MedLME) | The number of regional and international exchanges carried out. | No website related to marine BD in Lebanon. No documentation of best practices and lessons learned. | Networking mechanism. Stakeholders are aware of the project’s activities and outputs | The network of national and international partners is successfully established. Project’s website is published. | At least 20 meetings were conducting with different regional partners. Network of MPAs created in Lebanon with clear TORs and the first meeting conducted. Communication with Panorama Solutions Platform established as a means for communicating solutions related to marine BD. Plans for an exchange visit on ICZM next Spring were discussed with MoEnv. IUCN-ROWA incorporated a page on the project with updates on Project activities in addition to promoting the project activities on IUCN social media platforms. The project will also be represented in IUCN’s Regional Conservation Forum in September, 2019 with display of the fact sheets on marine birds and marine IAS | S |
| Outcome 3: 3.1. Environmental assessments and integration of results from related initiatives allow data/information gaps on the status of marine and coastal BD to be filled for the national implementation of SAP-BIO, CBD, ICZM protocol for the protection of marine and coastal BD | Number of assessments and survey on marine and coastal BD | No systematic assessment on marine and coastal BD | Establish a database of existing data on marine and coastal BD and increase accessibility to it | Full survey and complete database for marine and coastal BD in Lebanon. | IAS assessment is conducted and a protocol for monitoring IAS. A full survey was accomplished. Around 900 items (publications, articles, maps…) were collected and later classified. The classification was adopted after communication with stakeholders, experts and the MoEnv. SAP BIO updated. A study on coastal and marine birds conducted with fact sheets produced in both Arabic and English. | S |
| 3.2. Adaptation to CC measures identified for specific climate change impacts on marine BD (i.e. invasive species from Red Sea and migration of native species). | Coastal zone management reflects suggestions from 2nd national communication report to the UNFCCC. | No systematic incorporation of CC adaptation. |  | At least two adaptation measures for the protection of marine BD from SNC report identified and implemented | TOR’s for the consultancy prepared, and contractual arrangements with the University of the Balamand are in process. | S |
| 3.3. Incorporating results of this, past and ongoing initiatives into a detailed status report of the marine and coastal environment, to be widely disseminated | Number of institutions and stakeholder groups to which national marine and coastal status report is disseminated | 2002 SAP-BIO report |  | The 2002 SAP-BIO report is updated. All targeted stakeholder groups received national status report | The 2002 SAP-BIO report is updated. All targeted stakeholder groups received national status report | S |
| Outcome 4: 4.1. Unified database incorporating all past and present marine and coastal biodiversity projects/initiatives developed and maintained, disseminated to and used by a wide range of stakeholders | Database established and operating | No database |  | Database is centralized at MoE | GIS database framework is designed to be the base for the full GIS database. Coordination with CNRS was finalised in order to partner with OLIFE project in a unified biodiversity database for Lebanon. Stakeholders were involved in the discussions. A consultancy to prepare an Atlas for marine birds with GIS data, shapefile format is ongoing. These maps will feed the database and expected to be ready by October, 2019. |  |
| 4.2. Development and implementation of a monitoring program (including process, stress reduction and environmental status indicators) for the long term tracking of marine and coastal biodiversity | Monitoring plan adopted. | No monitoring plan in place. No project plan and long term tracking indicators in place. No training |  | A monitoring plan and long term tracking indicators are set by Y3. | - A Framework for monitoring programme is designed | S |
|  | The number of experts trained on monitoring process. | No training on monitoring process. |  | Experts in at least 3 national institutions are trained on monitoring plan and tools. | A training on monitoring and early detection of marine IAS was conducted |  |

Overall rating of project progress towards meeting project Result(s)

| FY2018 rating [previous] | FY2019 rating [current] | Justification of the current FY rating and explanation of reasons for change (positive or negative) since previous reporting periods. |
| --- | --- | --- |
| MS | S | Project implementation during the reporting period has greatly improved and benefitted from a change in the execution partner – IUCN’s West Asia Regional Office took over this role by the end of January 2018. Capacity development programmes at institutional levels were conducted for the agreed upon marine conservation priorities, including on IAS, and the project provided substantive input to the updating of MPA management plans. The big time-lapse between project design and current implementation (about 9 years) still hampers implementation, though. With regard to its objectives, the project facilitated the issuing of a decree (No 42/2017) providing for a buffer zone where petroleum activities are not allowed except with a decree issued by the Council of Ministers and a draft law and ICZM proposal were submitted to cabinet. The preparation of guidelines on mainstreaming biodiversity conservation in the EIA process for development projects affecting marine and coastal ecosystems is in process (indicator 1). The project further updated the 2002 SAP-BIO reports, supported the update of 2 MPA management plans, conducted a full IAS assessment, established an IAS monitoring protocol, and a CC impact assessment on the Lebanese coastal area with recommendations for adaptation measures is under way (indicator 2). The project further conducted a set of training workshops for government and research institutions on PA management, IAS monitoring, marine and coastal birds and red listing of marine species, and prepared designation files for protecting two deep sea areas (indicator 3). |

Risks to the delivery of results

The second column should be completed by the Project Manager and the third column should summarize the recommendations that the Project Manager and Task Manager have agreed upon to address the problem/risk.  Projects should complete only the relevant sections and are free to add/delete problems/risks.  This section should inform the risk rating in section 3.3.

| Problems/risks identified | Description of the problem/risk | Agreed recommended actions |
| --- | --- | --- |
| on achieving targets | - Time lapse between project design and approval in 2010 and current time (9 years) so that some activities are perceived currently not valid by the MoEnv. - Budgets allocated for some activities are considered underestimated compared to the current costs so some activities need to be narrowed in scope. - Achieving project targets requires strong political will to adopt policies, change regulations and this is a critical issue for Lebanon where there was no government for years. - The change of project management several times during the course of project, and the transfer of the project execution from MoEnv to IUCN and the handover process is one of the challenges that the management is trying overcome for the successful implementation of the project activities. | PM: Actively seek to prioritize project activities together with main stakeholders. TM: Support budget re-allocations to the extent possible |
| on stakeholder engagement | Stakeholder engagement is generally considered satisfactory; however the general political situation in Lebanon could affect the active participation of all stakeholders. |  |
| on gender actions | The project does not have an issue with gender actions. Gender balance is considered in all project activities, and there is strong contribution of females in all project activities as consultants, trainers and participants. |  |
| on safeguards |  |  |
| on delivering GEF Core Indicators |  |  |
| on delivering of PoW EA |  |  |
| on sustainability of results | The sustainability of results depends on the formal adoption of the project deliverables, reports and guidelines. This largely depends on the weight of the MoEnv and the political will in general to mainstream biodiversity in all sectors related to the coastal zone management. | PM: Pay particular attention to engage with all relevant ministerial and political decision makers for dissemination of project findings and recommendations |
| others |  |  |

3.2	Rating of progress implementation towards delivery of outputs

| Outputs | Expected delivery date | Implement-ation status as of 30 June 2018 | Implement-ation status as of 30 June 2019) | Progress rating justification | Progress rating |
| --- | --- | --- | --- | --- | --- |
| Output 1.1.1: Identification of legal, policy and institutional gaps and policy reforms drafted for marine and coastal BD protection. |  |  |  |  |  |
| Activity 1.1.1.1: Review the existing policies and legislations related to the protection of marine and coastal areas in Lebanon including biodiversity issues, in terms of appropriateness and effectiveness | 30/10/2014 | 100% | 100% | Completed during the MoEnv execution phase/ 1st PCA | S |
| Activity 1.1.1.2: Establish coordination with the MoA, particularly with the Department of Fisheries Resources. | 30/10/2014 | 100% | 100% | Completed during the MoEnv execution phase/ 1st PCA | S |
| Activity 1.1.1.3: Identify the gaps in existing policies and legislation related to marine and coastal biodiversity based on the report of the SELDAS project. | 30/10/2014 | 100% | 100% | Completed during the MoEnv execution phase/ 1st PCA | S |
| Activity 1.1.1.4: Identify and evaluate the measures adopted in Lebanon within the framework of regional conventions, or other MEAs to which Lebanon is a party. Review and update the draft strategy on ICAM developed in 2003 under the CAMP project (or any legal text that MoE and the project see necessary according to the recommendations of the activity 7 stated above). | 12/2/2015 | 100% | 100% | Completed during the MoEnv execution phase/ 1st PCA | S |
| Activity 1.1.1.5: Assess the general level of compliance with the current legislation in Lebanon. | 27/11/2014 | 100% | 100% | Completed during the MoEnv execution phase/ 1st PCA | S |
| Activity 1.1.1.6: Analyze the root causes of non-compliance and identify the real problems in non-compliance scenarios. | 27/11/2014 | 100% | 100% | Completed during the MoEnv execution phase/ 1st PCA | S |
| Activity 1.1.1.7: Provide support for the development of practical and appropriate guidelines for policies on marine and coastal biodiversity conservation and sustainable management. | 27/11/2014 | 100% | 100% | Completed during the MoEnv execution phase/ 1st PCA | S |
| Activity 1.1.1.8: Prepare and publicize policy reports on marine conservation aspects. |  |  | 100% | Completed during the MoEnv execution phase/ 1st PCA | S |
| Activity 1.1.1.9: Coordinate with all governmental bodies and ministries to prepare a healthy atmosphere for the good understanding and uptake of the prepared policy guidelines and for the realization of the urgent need of enforcement and implementation of the already existing ones. | 27/11/2014 | 100% | 100% | Completed during the MoEnv execution phase/ 1st PCA | S |
| Activity 1.1.1.10: Coordinate with the MoIM and encourage the setup of a national police body for the conservation and protection of marine and coastal areas in Lebanon. | 31/01/2015 | 100% | 100% | Completed during the MoEnv execution phase/ 1st PCA | S |
| Activity 1.1.1.11: Develop recommendations for law enforcement mechanisms in consultation with local communities and the MoIM. | 31/01/2015 | 100% | 100% | Completed during the MoEnv execution phase/ 1st PCA | S |
| Activity 1.1.1.12: Organize a workshop to communicate the results of activities associated to output 1.1.1 to relevant stakeholders. | 19/3/2015 | 100% | 100% | Completed during the MoEnv execution phase/ 1st PCA | S |
| Output 1. 1.2: Training and capacity programme developed and implemented for min. 3 national institutions |  |  |  | Capacity building programme has been approved in the steering committee workshop to be in this year on: invasive species and management effectiveness, and Red listing of marine species. | S |
| Activity 1.1.2.1: Identify the priorities for marine and coastal biodiversity conservation in Lebanon. | 30/12/2018 | 0% | 80 % | Priorities identified through consultation workshop and meetings with partners, and based on guidance from MoEnv | S |
| Activity 1.1.2.2: Communicate these priorities to stakeholders and achieve agreement on them through proper consultations. | 30/12/2018 | 0% | 70% | These priorities are communicated through consultation meetings and other forms of communication | S |
| Activity 1.1.2.3: Develop a local authority capacity building program and conduct training for at least three national institutions i.e. the MoA, MoPWT and the MoT on the agreed marine conservation priorities and the importance and implementation of identified legal reforms under output 1.1.1. | 1/03/2019 | 0% | 80 % | 5 training workshops were conducted in the reporting period: - PA management effectiveness - IAS (2 workshops, one of them targeting national institutions including MOA) - Workshop on assessment - related to marine birds. - IUCN Red listing of marine species. - Mainstreaming marine biodiversity conservation in the EIA process is planned during Oct-Nov, 2019 | S |
| Activity 1.1.2.4: Provide support for national institutions to prepare for the implementation of necessary legal reforms. | 1/12/2019 | 0% | 30 % | The expected completion date extended to Dec 2019. Part of this is addressed in three consultancy which are currently in progress: - Preparation of Atlas for marine birds will include policy recommendations. - The CC adaptation will include potential mitigation measures and policy recommendations. - EIA guidelines consultancy will include policy recommendations. | S |
| Output 1. 1.3: Integration of agreed protection priorities into national plans | 1/12/2019 | 0% | 0% | The completion date extended to Dec 2019 | N/A |
| Activity 1.1.3.1: Coordinate and consult with key stakeholders to set the ground, especially with governmental institutions for harmonization of conservation priorities with national plans and programs. | 1/12/2019 | 0% | 0 % | The completion date extended to Dec 2019 | N/A |
| Activity 1.1.3.2: Develop, with each involved governmental institution, scenarios how to best incorporate BD conservation priorities into the respective sectoral policy processes (i.e. jointly define appropriate entry points) | 1/12/2019 | 0% | 0% | The completion date extended to Dec 2019 | N/A |
| Output 1. 2.1: legal and administrative procedures developed for the protection of 2 identified sites |  |  |  |  |  |
| Activity 1.2.1.1: Identify key sites for marine and coastal protected areas in Lebanon that harbor representative and well-conserved habitats and that are needed to protect endangered species. | 16/6/2014 | 100% | 100% | Completed during the MoEnv execution phase/ 1st PCA | S |
| Activity 1.2.1.2: Identify the legal, administrative and decision-support tools needed for the integration of marine and coastal zone management into the management plans of 2 identified pilot sites of the potential identified MPAs | 30/6/2014 | 100% | 100% | Completed during the MoEnv execution phase/ 1st PCA | S |
| Activity 1.2.1.3: Prepare suitable and sustainable development and management plans of the two identified pilot sites. (2 first draft management plans, one for each site; including zoning and habitat mapping.) | 25/8/2014 | 100% | 100% | Completed during the MoEnv execution phase/ 1st PCA | S |
| Activity 1.2.1.4: Coordinate with relevant governmental bodies and stakeholders to agree on identified areas and adopt the prepared development and management plans. | 2/12/2014 | 100% | 100% | Completed during the MoEnv execution phase/ 1st PCA | S |
| Output 1.2.2: Coastal priority areas and mechanisms for their protection agreed and included in plans for coastal zone management |  |  |  |  |  |
| Activity 1.2.2.1: Identify the legal, administrative and decision-support tools needed for the integration of coastal zone protection mechanisms into coastal zone management plans. | 31/12/2018 | 0% | 30% | All the legal framework to manage the costal zone area in Lebanon has been reviewed. | S |
| Activity 1.2.1.2: Organize a workshop to consult with all stakeholders about the identified tools and prepare a healthy environment for their adoption. | 31/12/2018 | 0% | 20% | This workshop will be organised in the 4th quarter of 201, however, consultations are ongoing with this regards. We prefer to have this workshop when we have initial results from the three ongoing consultancies (EIA, CC impact on coastal area, and Atlas of marine birds) which could be useful for the discussion |  |
| Activity 1.2.2.3: Coordinate with relevant governmental bodies and stakeholders to agree on and adopt the prepared conservation mechanisms and management plans and thus including them into plans of coastal zone management. | 1/12/2019 | 0% | 0% | Completion date extended to Dec 2019 | NA |
| Activity 1.2.2.4: Support and conduct environmental impact assessment (EIA) of development including commercial and land-based activities on marine ecosystems, including the reviewing of current licensing and permissions procedures and mechanisms. | 1/10/2020 | 0% | 20% | Guidelines on mainstreaming biodiversity conservation in the EIA process for development projects affecting marine and coastal ecosystems, and a checklist for the inspection and monitoring of necessary environmental mitigation measures related to biodiversity conservation and protection are in progress. TOR prepared, RFP launched, Bid analysis complete, and selection of a consultant and contractual arrangements are in process. | N/A |
| Output 1.2.3: Coastal zone planning includes adaptation measures for the protection of BD from CC |  |  |  |  |  |
| Activity 1.2.3.1: Identify the impacts of climate change on marine and coastal biodiversity in Lebanon. | 31/12/2019 | 0% | 25% | TOR finalized with MoEnv, and contractual arrangements with the University of the Balamand are in process. Task team has already started the literature review part of the consultancy. | N/A |
| Activity 1.2.3.2: Identify the adaptation measures to tackle the identified impacts. | 31/12/2019 | 0% | 20% | Completion date extended to Dec 2019. This is part of the consultancy covered in 1.2.3.1 |  |
| Activity 1.2.3.3: Coordinate with concerned governmental institutions and other stakeholders to have their feedback and to set the ground for the integration the climate change adaptation measures into national plans for marine biodiversity conservation | 31/12/2020 | 0% | 10% | Completion date extended to Dec 2019. This is part of the consultancy covered in 1.2.3.1 | N/A |
| Output 1.3.1: Economic valuation of coastal and marine BD, along with analysis of most cost-effective and sustainable potential initiatives, finance mechanisms, tools and technologies for the protection of marine and coastal BD. | 31/12/2020 |  |  |  | N/A |
| Activity 1.3.1.1: Identify the total economic value of marine and coastal biodiversity in Lebanon including direct and indirect values, option values and non-use existence values. | 30/06/2019 | 0% | 5% | Completion date extended to Dec 2019. Draft TOR’s prepared. | N/A |
| Activity 1.3.1.2: Assess the current marine resources use, including activities that are generating income in and around existing and recommended protected areas. | 30/06/2019 | 0% | 5% | Completion date extended to Dec 2019. Draft TOR’s prepared. | N/A |
| Activity 1.3.1.3: Identify the needs of key stakeholders related to marine and coastal biodiversity conservation and sustainable management. | 3l/12/2019 | 0% | 5% | Completion date extended to Dec 2019. Draft TOR’s prepared. | N/A |
| Activity 1.3.1.4: Identify the initiatives that are of highest cost-effectiveness and sustainability potential to determine which measures, at the lowest possible cost, will lead to the protection and conservation of marine and coastal biodiversity in Lebanon. | 30/03/2020 | 0% | 5% | Completion date extended to Dec 2019. Draft TOR’s prepared. | N/A |
| Activity 1.3.1.5: Identify and develop potential sustainable financing mechanisms for the sustainable management of marine and coastal biodiversity including activities for sustainable management of marine and coastal protected areas. | 31/12/2020 | 0% | 5% | Completion date extended to Dec 2019. Draft TOR’s prepared. | N/A |
| Activity 1.3.1.6: Develop management plans and guidelines for marine eco-tourism activities. | 31/12/2020 | 0% | 0% | Completion date extended to Dec 2019 | N/A |
| Output 2.1.1: The establishment of an Inter-ministerial committee incl. all key sectors (agriculture, urban, industry, tourism etc.) and the private sector who will be fully participating in the project activities. | 31/12/2014 | 100% | 100% | Completed during the MoEnv execution phase/ 1st PCA | S |
| Activity 2.1.1.1: Coordinate with concerned governmental institutions and establish an inter-ministerial committee including representatives of key sectors and the private sector. | 31/12/2013 | 100% | 100% | Completed during the MoEnv execution phase/ 1st PCA | S |
| Activity 2.1.1.2: Support MoE in establishing objectives and procedures for the inter-ministerial committee | 31/12/2013 | 100% | 100% | Completed during the MoEnv execution phase/ 1st PCA | S |
| Output 2.2.1: Stakeholders identified and fully participating in project activities | 31/12/2016 | 50% | 50% |  | S |
| Activity 2.2.1.1: Identify key stakeholders for marine and coastal biodiversity in Lebanon. | 30/6/2014 | 100% | 100% | Completed during the MoEnv execution phase/ 1st PCA | S |
| Activity 2.2.1.2: Formulate and implement initiatives to raise awareness about marine and coastal biodiversity in Lebanon, its conservation measures and the project activities and results. | 31/12/2020 | 10% | 70% | - Meetings conducted with stakeholders and partners to discuss the initiative and what could be done. - Part of the workshops held to communicate the project deliverables aimed to raise awareness (IAS two workshops, workshop on the assessment of marine and coastal birds). - The production of a booklet on marine birds for school kids, the IAS and marine birds fact sheets. | S |
| Output 2.2.2: Partnership with other complementary projects to exchange results and best practices | 31/12/2019 |  |  |  | N/A |
| Activity 2.2.2.1: Engage with similar projects being implemented in Lebanon and in the region. | 31/3/2019 | 40% | 50% | This is an ongoing activity related to networking and we think that it should be extended to the end of 2020. | S |
| Activity 2.2.2.2: Collaborate with them and initiate partnership on relevant activities. Agree and develop joint results when possible. | 31/3/2017 | 20% | 30% | Communication and preapproval with UNDP and Palm island protected area to plan some joint activities which will be conducted in 2019 | S |
| Output 2.2.3: Network of international and national partners dealing with BD protection, network of universities, NGOs etc. are engaged in a dialogue on exchange of best practices and lessons learned via regular meeting and web-based discussion forum | 31/12/2019 |  |  |  | S |
| Activity 2.2.3.1: Coordinate with national and international partners dealing with BD protection and engage in a dialogue for exchange of experiences and lessons via regular meetings or web-based discussion forum | 31/12/2019 | 50% | 60% | - Regular meeting conducted with national and international partners. - Universities and research institutions invited to project workshops (Red Listing, etc). - Communication is established with the Panorama Solutions initiative to promote and exchange solutions related to marine and coastal BD conservation and management. We think that this should be ongoing and the deadline should be extended to 31/12/2020 | S |
| Output 2.3.1: Identified relevant institutions, organizations and public sector informed of project’s aims and results through communication strategy | 30/6/2017 |  |  |  | N/A |
| Activity 2.3.1.1: Coordinate with key stakeholders and with relevant international institutions and establish networking mechanisms including internet based mechanisms, oriented publications, regular meetings and workshops to exchange information and protocols. | 30/12/2019 | 0% | 20% | - Communication is established with the Panorama Solutions initiative to promote and exchange solutions related to marine and coastal BD conservation and management. Completion date extended to Dec 2019. -Communication regarding a planned conference to be held in Lebanon jointly with the Blue Solutions Project to offer the opportunity for regional/ international networking. | N/A |
| Activity 2.3.1.2: Develop and maintain a register of experts and consultants on marine and coastal biodiversity research, conservation and management. | 31/3/2015 | 100 % | 100 % | Completed during the MoEnv execution phase/ 1st PCA | S |
| Activity 2.3.1.1: Maintain regular consultation with key stakeholders involved in the project activities. Keep all relevant institutions, organizations, public and private sectors well informed about the project’s aims, activities and results through a communication strategy. | 30/6/2017 | 100 % | 100 % | Completed during the MoEnv execution phase/ 1st PCA | S |
| Output 2.3.2: Web-based platform and project site in place for the dissemination of reports, maps and awareness materials. | 31/12/2016 |  |  |  | N/A |
| Activity 2.3.2.1: Establish a web–based platform and a project site and include all reports, maps and awareness materials for dissemination. | 31/12/2019 | 20% | 30% | Marine map layers created in coordination with the ministry GIS unit. The consultancy for the preparation of an Atlas for marine birds is on-going, this will provide GIS maps and data on the distribution and abundance of marine birds for the online database. | S |
| Output 3.1.1: Baseline database on existing data for marine species, marine habitats and ecological areas. | Dec 2014 |  |  |  | N/A |
| Activity 3.1.1.1: Identify and locate existing data on marine and coastal BD. | 12/1/2015 | 100% | 100% | Completed during the MoEnv execution phase/ 1st PCA | S |
| Activity 3.1.1.2: Establish registry and database for the identified data. | 23/3/2015 | 100% | 100% |  | S |
| Activity 3.1.1.3: Increase the availability and access to this data | 31/12/2020 | 0% | 0% | Expected completion extended to be in 2020 | N/A |
| Output 3.1.2: Topographic maps, habitat maps, sea floor maps, species maps and sensitivity maps are developed for all identified priority areas | 30/6/2020 |  |  |  | N/A |
| Activity 3.1.2.1: Conduct a full survey to have sea floor maps, topographic maps, habitat maps, species maps and sensitivity maps for priority sites. | 30/11/2020 | 50% | 50% | Expected to start in the fourth quarter of 2019. Part of the data will be available through the consultancy “Atlas of Marine birds”, which will identify birds distribution and abundance spatially. | N/A |
| Activity 3.1.2.2: Include these maps in the established database (in 3.1.1.2) and publish them on the project’s website. | 30/12/2020 | 0% | 0% | expected completion extended to 2020. Part of the data will be available through the consultancy “Atlas of Marine birds” , which will identify birds distribution and abundance spatially. | N/A |
| Output 3.2.1: The process of the second National Communication is completed and assisted through the analysis of impacts and definition of adaptation measures for the protection of marine and coastal BD from CC. | 31/12/2016 | 0% |  |  | N/A |
| Activity 3.2.1.1: Coordinate with stakeholders and inform them on the UNFCCC national communication process. | 30/10/2020 | 0% | 10% | Expected completion extended to 2020. This will be covered through the CC consultancy which is on-going. Contractual arrangements are in progress with the University of the Balamand. Task team has already started the literature review part. | N/A |
| Activity 3.2.1.2: Analyse CC impacts in each of the involved sectors and for each stakeholder group. | 30/10/2020 | 0% | 10% | expected completion extended to 2020. This will be covered through the CC consultancy which is on-going. Contractual arrangements are in progress with the University of the Balamand. Task team has already started the literature review part. | N/A |
| Activity 3.2.1.3: Develop scenarios for CC adaptation measures in each sector and stakeholder group. | 30/10/2020 | 0% | 10% | expected completion extended to 2020. This will be covered through the CC consultancy which is on-going. Contractual arrangements are in progress with the University of the Balamand. Task team has already started the literature review part. |  |
| Output 3.3.1: Final report on the status of marine and coastal BD in Lebanon (updating of 2002 SAP, BIO National Report) is widely disseminated | 10/05/2020 |  |  |  | N/A |
| Activity 3.3.1.1: Gather all data and information collected and prepared via this project and other relevant ones and develop a final report on the marine and coastal biodiversity in Lebanon. | 5/4/2016 | 100% | 100% | Completed during the MoEnv execution phase/ 1st PCA | S |
| Activity 3.3.1.2: Update the 2002 report of the SAP-BIO project. | 10/5/2016 | 100% | 100% | Completed during the MoEnv execution phase/ 1st PCA | S |
| Activity 3.3.1.3: Make these reports easily accessible to stakeholders and ensure their wide dissemination. | 10/5/2020 | 50% | 60% | On-going. | N/A |
| Output 4.1.1: Database with different user and viewer interfaces accessible for public, private and academic institutions and centralized at MOE, incl. GIS maps. | 30/6/2019 |  |  |  | N/A |
| Activity 4.1.1.1: Conduct survey on different data and accessibility needs for various stakeholder groups. | 23/3/2015 | 100% | 100% | Completed during the MoEnv execution phase/ 1st PCA | S |
| Activity 4.1.1.2: Develop tools and materials for local stakeholders without access to electronic media. | 30/06/2019 | 0% | 70% | Expected completion extended to end of 2019. Produced a booklet on marine birds for kids in Arabic language. Marine birds fact sheets, and IAS fact sheets produced in English and translated into Arabic. The Arabic versions are designed and reviewed and will be printed by September , 2019. Project brochures are being drafted. | S |
| Activity 4.1.1.3: Establish a database for marine and coastal biodiversity in Lebanon in the MoE and provide easy access to information to key stakeholders on the national, regional and international levels. | 31/12/2019 | 50% | 50% | It is expected to start by the end 2019, and completed in 2020. Part of the work was done through the 1st PCA by MoEnv. | N/A |
| Output 4.2.1: Marine BD monitoring plan adopted, incl. legal and administrative documents, mechanism for the sustainable financing, administration and management of the monitoring programme | 30/6/2016 | 80% |  | Further follow up work is required to complete this task | N/A |
| Activity 4.2.1.1: Establish adequate monitoring techniques and develop standard monitoring protocols for implementation by the appropriate agencies and stakeholders. | 9/4/2016 | 100% | 100% | Completed during the MoEnv execution phase/ 1st PCA | S |
| Activity 4.2.1.2: Promote the adequate monitoring tools and survey of the effectiveness of marine and coastal protected areas. | 9/4/2016 | 100% | 100% | Completed during the MoEnv execution phase/ 1st PCA | S |
| Activity 4.2.1.3: Coordinate with relevant stakeholders to ensure proper and smooth monitoring implementation processes. | 9/4/2016 | 100% | 100% | Completed during the MoEnv execution phase/ 1st PCA | S |
| Activity 4.2.1.4: Evaluate, at the national and regional levels, the effectiveness of the adopted policy and legislative measures in Lebanon and refine them when necessary. | 30/03/2019 | 50% | 50% | It is expected to start by the end of 2019 | N/A |
| Output 4.2.2: Indicators for long-term tracking of Lebanon’s implementation of the CBD, SAP-BIO, ICZM protocol | 31/12/2020 |  |  | Expected to start in 2020. | N/A |
| Activity 4.2.2.1: Identify and develop adequate biological and socio-economic indicators to assess the long term proper implementation of the CBD, SAP-BIO, ICZM protocol and CC adaptation and to evaluate the effectiveness of the adopted management measures via this project. | 31/06/2019 | 0% | 10% | Expected completion extended to 2020. Part of the work is covered through the CC consultancy. | N/A |
| Activity 4.2.2.2: Form a working group to elaborate and validate the set of identified indicators and to select the useful and applicable ones in Lebanon. | 30/06/2020 | 0% | 0% | expected completion extended to 2019 | N/A |
| Activity 4.2.2.3: Convene a workshop to communicate the selected indicators and their objectives to key stakeholders to be able to adopt them. | 30/07/2020 | 0% | 0% | expected completion extended to 2020 | N/A |
| Activity 4.2.2.4: Adopt the agreed indicators, establish a report about them and publish it. | 30/11/2020 | 0% | 0% | expected completion extended to 2020 | N/A |
| Output 4.2.3: Training of experts in national institutions on monitoring | 21/6/2015 |  |  |  | N/A |
| Activity 4.2.3.1: Conduct survey on monitoring and evaluation training needs and requirements. | 9/4/2016 | 100% | 100% | Completed during the MoEnv execution phase/ 1st PCA | S |
| Activity 4.2.3.2: Develop appropriate training tools and materials for different stakeholder groups | 9/4/2016 | 100% | 100% | Completed during the MoEnv execution phase/ 1st PCA | S |
| Activity 4.2.3.3: Organize workshops to train officials, experts and managers in national institutions on evaluation and monitoring issues. | 30/10/2020 | 0% | 70% | Training on Protected Area Management effectiveness. Training on IAS monitoring and early detection | S |
| Activity 4.3.3.4: Establish monitoring program for the identified BD hot spots, through an ongoing survey of one or two representative species for each important habitat at different time intervals. | 30/10/2019 | 0% | 30% | Monitoring invasive species along the Lebanese cost started. We think the completion dtae should be extended to Q1 2020. | N/A |

Overall project implementation progress

| FY2018 rating [previous] | FY2019 rating [current] | Justification of the current rating and explanation of reasons for change (positive or negative) since previous reporting periods. |
| --- | --- | --- |
| MS | S | Implementation progress accelerated considerably, including re-organization and prioritization of activities to be more aligned to current needs and requirements, taking into account political will, priorities and overall political climate in Lebanon |

Risks in implementation

This section should be completed by the Project Manager and summarize implementation risks (e.g. procurement delays, reputational risks etc).

The first column should be completed by the Project Manager and the second column should summarize the recommendations that the Project Manager and Task Manager have agreed upon to address the problem/risk.  This section should inform the risk rating in section 3.3.

| Problems/risks identified | Agreed recommended actions | By whom | When |
| --- | --- | --- | --- |
| Time lapse between project design and approval in 2010 and current time (9 years) so that some activities are perceived currently not valid by the MoEnv. | Actively seek to prioritize project activities together with main stakeholders. Support budget re-allocations flexibly to the extent possible | PM TM | Continuously Continuously |
| Lack and limited national expertise required to accomplish the required project consultancies. Project budget does not allow to acquire international experts to perform the tasks |  |  |  |
| Procurement delays because of limited expertise, so validity and eligibility checks should take place | Improve project oversight | PM & TM | Ongoing basis |
| The change of project management, and the transfer of project execution from MoEnv and IUCN is resulting in extra consultation between IUCN and MoEnv to assure validity and consensus in recruiting project consultants, and implementation of activities |  |  |  |

3.3. Risk Rating

| Risk | Mitigation at CEO approval | Mitigation at implementation | Rank |
| --- | --- | --- | --- |
| Climate Change Impacts: Climate change can impact the project, among others through storms, floods and rise in sea temperature. It can be predicted that the highest vulnerability is where there are unstable and uncontrolled land-based activities and coastal modifications | The project will make available information on climate change and its impacts on marine biodiversity in Lebanon a part of the activities on information dissemination and capacity building. Other measures will be promoted also such as the reduction of infringement on coastlines, control of land-use in the coastal areas, taking forceful preventive measures for on-going activities deleterious to the coastline, or devising economic and social incentives. Climate change risk data will be assessed and recommendations be incorporated in project activities, so as to lower overall pressures on marine ecosystems and to strengthen its resilience to climate change impacts, being assumed at the medium level | The project is started to establish a better understanding of Climate Change impact on the coastal area of Lebanon through the consultancy service which is in progress. The consultancy will also include the recommendation of CC adaptation measures and policy recommendations whenever valid. | CEO: M |
|  |  |  | TM: M |
|  |  |  | PM: M |
| Political will to mainstream coastal and marine biodiversity priorities into national plans and programs: The potential of the proposed legal and legislative reforms and other recommendations to conserve marine and coastal biodiversity in Lebanon depends largely on their mainstreaming into national plans and programs and thus the main issue here is the willingness of the relevant ministries and governmental bodies to adapt and change their development plans. | Coordination and consultation with relevant ministries will create a healthy atmosphere for broad ownership of the project and its implementation, which will contribute to mitigating this risk, which is considered at medium level. The project activities, in this regard, aim at complying with the Lebanese government commitments to marine and coastal biodiversity conservation through CBD and UNFCCC and other regional and international protocols and programs. | The project seeks continuous consultation with stakeholders, and tries to adapt the project activities to the actual current needs of MoEnv within the framework of the project. TOR’s for consultancies are prepared with active consultation with relevant government departments. | CEO: M |
|  |  |  | TM: M |
|  |  |  | PM: M |
| Insufficient capacities to mainstream biodiversity into national plans and programs: In addition to political will, the capacities of sectoral ministries and departments to properly incorporate project results and recommendations into their planning and activity frameworks is considered another risk at medium level. | The core components of the project aim at reducing critical knowledge barriers and at providing capacity development to stimulate an active uptake of suggested measures into policy making and implementation. Explanation of the economic values and benefits in addition to the establishment of economically sustainable management plans which will also help mitigating this risk. Additionally, training sessions and media campaigns will help address this risk also | The project seeks to remove knowledge barriers and make data on the importance of costal and marine biodiversity, threats, and mitigation measures available to the public and decision makers in several accessible formats. Each study or survey provides policy recommendations that address the relevant sector. Knowledge outputs and the establishment of a database are also enhance access to data and decision support, thus enhancing capacities to mainstream biodiversity into national plans. | CEO: M |
|  |  |  | TM: M to L |
|  |  |  | PM: L |
| Scaling-up and replication of project approach | To ensure that the Lebanese lessons and approaches are relevant and useful in other contexts or regional countries, the project will establish partnerships with other projects being implemented in the region to share results and best practices. Since the existing SAP-BIO already provides a useful platform for regional cooperation, this risk is considered as low. | Partnerships, and networking with similar projects, initiatives, and institutions of similar scope of work are contributing to keep this as low risk. | CEO: L |
|  |  |  | TM: L |
|  |  |  | PM: L |
| Political and economic instability: This risk relates to the political/economic instability and differences over policy implementation in the country and in the region. | The project’s strategy for minimizing the risk is to work with the key actors of the different governmental bodies and make them aware of the benefits of developing long-term internal policies to foster sustainable management of marine and coastal biodiversity. Another issue to be tackled by this project is to improve living conditions and income at local level within sustainable activities that do not contradict the sustainable management and use of marine and coastal resources. These activities will permit mitigating the economic instability and will even permit to offer alternative economic incentives through conservation and protection measures. | The project will develop economic valuation of ecosystem services related to marine and coastal biodiversity (draft TOR’s prepared), which will enhance the understanding of the importance of sustaining these services while maximising the economic benefits. | CEO: M |
|  |  |  | TM: M |
|  |  |  | PM: M |
| Lack of interest of the project’s beneficiaries in the long term. | This risk will be tackled by incorporating local communities’ interests and perceptions into project activities; by actively involving them into project execution measures; both environmental and economic, as well as by disseminating the project’s lessons and recommendations in locally appropriate formats. | This risk is kept as minimum through the mitigation measures reported at CEO endorsement , like participatory approach in the design of project consultancies, and sharing knowledge outputs and lessons learned. | CEO: L |
|  |  |  | TM: L |
|  |  |  | PM: L |
| Lack of continuity of political will and commitments | The project will initiate regular coordination and consultation with all governmental sectors. In addition, there is a commitment that the Lebanese government has towards the conservation of its biodiversity through international conventions and protocols. However, even if the project can contribute to a strengthened and continued commitment by different governmental agencies, it has only limited influence on the provision of governmental funding for sustaining such a commitment. | The project is keeping regular consultation with concerned government sectors. The project is considering the needs of the government regarding its commitments to international conventions. Still part of this remains unpredictable due to the political situation in Lebanon. | CEO: M to H |
|  |  |  | TM: M to H |
|  |  |  | PM: M to H |
| Low conservation impact from project activities | The project will establish a monitoring and evaluation program to ensure compliance with sustainable management principles for short and long term purposes. In addition, the project will be implemented in coordination with other similar projects in the region; therefore, this risk is considered as low. | The project has started to introduce the concept of long term monitoring to relevant authorities, for example, the IAS monitoring protocol and training on the early detection and monitoring of IAS is an example. | CEO: L |
|  |  |  | TM: L |
|  |  |  | PM: L |
| Stakeholders participation | The project will address this risk by regular meetings, consultations and close coordination and follow ups with all stakeholders. | Stakeholder participation is on-going through the course of the project. Stakeholder’s current needs are taken into consideration during the development of TOR’s. They are targeted in the workshops when the findings of consultancies are presented, their feedback is integrated. | CEO: L to M |
|  |  |  | TM: L |
|  |  |  | PM: L |
| Overall Risk Rating Project Manager |  |  | M to L |
| Overall Risk Rating Task Manager |  |  | M to L |

| FY2018 rating [previous] | FY2019 rating [current] | Justification of the current risk rating and explanation of reasons for change (positive or negative) since previous reporting periods. |
| --- | --- | --- |
| M | M to L | The project has taken measures to keep the risk between medium to low by mainly the following: - Active stakeholder participation. - Adapting the activities and consultancies to the current needs of the government. - Enhancing the understanding and removing knowledge barriers concerned to climate risks, understanding of the value of marine ecosystems. - Networking, coordination and capitalization. |

High Risk (H): There is a probability of greater than 75% that assumptions may fail to hold or materialize, and/or the project may face high risks. 
Substantial Risk (S): There is a probability of between 51% and 75% that assumptions may fail to hold and/or the project may face substantial risks. 
Modest Risk (M): There is a probability of between 26% and 50% that assumptions may fail to hold or materialize, and/or the project may face only modest risks. 
Low Risk (L): There is a probability of up to 25% that assumptions may fail to hold or materialize, and/or the project may face only modest risks.

Annexes and/or Links:

- Project Steering Committee Minutes of the year reported

- Risk Factor Table form previous template

Risks Factor Table

There are two tables to assess and address risk: the first “risk factor table” to describe and rate risk factors; the second “top risk mitigation plan” should indicate what measures/action will be taken with respect to risks rated Substantial or High and who is responsible to for it.

High Risk (H): There is a probability of greater than 75% that assumptions may fail to hold or materialize, and/or the project may face high risks. 
Substantial Risk (S): There is a probability of between 51% and 75% that assumptions may fail to hold and/or the project may face substantial risks. 
Modest Risk (M): There is a probability of between 26% and 50% that assumptions may fail to hold or materialize, and/or the project may face only modest risks. 
Low Risk (L): There is a probability of up to 25% that assumptions may fail to hold or materialize, and/or the project may face only modest risks.

RISK FACTOR TABLE

Project Managers will use this table to summarize risks identified in the Project Document and reflect also any new risks identified in the course of project implementation. The Notes column should be used to provide additional details concerning manifestation of the risk in your specific project, as relevant. The “Notes” column has one section for the Project Manager (PM) and one for the UNEP Task Manager (TM). If the generic risk factors and indicators in the table are not relevant to the project rows should be added. The UNEP Task Manager should provide ratings in the right hand column reflecting his/her own assessment of project risks.

|  |  |  |  | Project Manager Rating |  |  |  |  |  | Notes | Task Manager Rating |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Risk Factor | Indicator of Low Risk | Indicator of Medium Risk | Indicator of High Risk | Low | Medium | Substantial | High | Not Applicable | To be determined |  | Low | Medium | Substantial | High | Not Applicable | To be determined |
| INTERNAL RISK |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Project management |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Management structure [Roles and responsibilities] | Stable with roles and responsibilities clearly defined and understood | Individuals understand their own role but are unsure of responsibilities of others | Unclear responsibilities or overlapping functions which lead to management problems | X |  |  |  |  |  | PM : There’s an agreement on the roles but the transition of project execution from MoEnv to IUCN adds another level of intensive communication and coordination requirements to implement and lead activities with consensus | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: Agreed. PM team to continue constantly involving MoEnv and core partners |  |  |  |  |  |  |
| Governance structure [oversight] | Steering Committee and/or other project bodies meet periodically and provide effective direction/inputs | Body(ies) meets periodically but guidance/input provided to project is inadequate. TOR unclear | Members lack commitment Committee/body does not fulfil its TOR | X |  |  |  |  |  | PM : Steering committee provides guidance and feedback for the project implemmentation | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: Agreed |  |  |  |  |  |  |
| Internal communications | Fluid and cordial | Communication process deficient although relationships between team members are good | Lack of adequate communication between team members leading to deterioration of relationships and resentment | X |  |  |  |  |  | PM: Active direct communication between the project management team and MoEnv focal point | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: Agreed |  |  |  |  |  |  |
| Work flow | Project progressing according to work plan | Some changes in project work plan but without major effect on overall timetable | Major delays or changes in work plan or method of implementation |  | X |  |  |  |  | PM: Some adjustments to the timetable of work plan are required but without major impact on the overall work plan |  | X |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: Agreed |  |  |  |  |  |  |
| Co-financing | Co-financing is secured and payments are received on time | Is secured but payments are slow and bureaucratic | A substantial part of pledged co-financing may not materialize |  | X |  |  |  |  | PM: Delays in finalizing the audit with the ministry of Env are affecting the payments of IUCN ROWA which are executing the project currently |  | X |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: Needs to be reported |  |  |  |  |  |  |
| Budget | Activities are progressing within planned budget | Minor budget reallocation needed | Reallocation between budget lines exceeding 30% of original budget | X |  |  |  |  |  | PM: IUCN is trying to adapt activities to the current budget but minor changes could be needed by the end of 2019 |  | X |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: Changes will be required |  |  |  |  |  |  |
| Financial management | Funds are correctly managed and transparently accounted for | Financial reporting slow or deficient | Serious financial reporting problems or indication of mismanagement of funds | X |  |  |  |  |  | PM: Funds are managed according to the allocated budget with transparency | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: Agreed |  |  |  |  |  |  |
| Reporting | Substantive reports are presented in a timely manner and are complete and accurate with a good analysis of project progress and implementation issues | Reports are complete and accurate but often delayed or lack critical analysis of progress and implementation issues | Serious concerns about quality and timeliness of project reporting | X |  |  |  |  |  | PM: IUCN complies with the reporting requirements of UN Environemnt | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: Agreed |  |  |  |  |  |  |
| Stakeholder engagement | Stakeholder analysis done and positive feedback from critical stakeholders and partners | Consultation and participation process seems strong but misses some groups or relevant partners | Symptoms of conflict with critical stakeholders or evidence of apathy and lack of interest from partners or other stakeholders | X |  |  |  |  |  | PM: IUCN involves stakeholders and adapts the activities to the current needs and situation within the framework of the project | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: Agreed |  |  |  |  |  |  |
| External communications | Evidence that stakeholders, practitioners and/or the general public understand project and are regularly updated on progress | Communications efforts are taking place but not yet evidence that message is successfully transmitted | Project existence is not known beyond implementation partners or misunderstandings concerning objectives and activities evident | X |  |  |  |  |  | PM: Project stakeholders are actively involved in the project , and regular updates and news about project activities are communicated and interacted with on social media | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: Agreed |  |  |  |  |  |  |
| Short term/long term balance | Project is addressing short term needs and achieving results with a long term perspective, particularly sustainability and replicability | Project is interested in the short term with little understanding of or interest in the long term | Longer term issues are deliberately ignored or neglected | X |  |  |  |  |  | PM: Balance is being achieved to the most achievable extent | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: Re-prioritization might still be required due to the time lapse between design and current implementation` |  |  |  |  |  |  |
| Science and technological issues | Project based on sound science and well established technologies | Project testing approaches, methods or technologies but based on sound analysis of options and risks | Many scientific and /or technological uncertainties | X |  |  |  |  |  | PM: IUCN ROWA is using the best experts from iucn commissions to implement the project which is focusing on science and technology. | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: Agreed |  |  |  |  |  |  |
| Political influences | Project decisions and choices are not particularly politically driven | Signs that some project decisions are politically motivated | Project is subject to a variety of political influences that may jeopardize project objectives | X |  |  |  |  |  | PM: The project is not driven by political agenda | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: Agreed |  |  |  |  |  |  |
| Other, please specify. Add rows as necessary |  |  |  |  |  |  |  |  |  | PM: |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: |  |  |  |  |  |  |

|  |  |  |  | Project Manager Rating |  |  |  |  |  | Notes | Task Manager Rating |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Risk Factor | Indicator of Low Risk | Indicator of Medium Risk | Indicator of High Risk | Low | Medium | Substantial | High | Not Applicable | To be determined |  | Low | Medium | Substantial | High | Not Applicable | To be determined |
| EXTERNAL RISK |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Project context |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Political stability | Political context is stable and safe | Political context is unstable but predictable and not a threat to project implementation | Very disruptive and volatile |  | X |  |  |  |  | PM: There is still a margin of political instability and political conditions are unpredictable |  | X |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: Agreed |  |  |  |  |  |  |
| Environmental conditions | Project area is not affected by severe weather events or major environmental stress factors | Project area is subject to more or less predictable disasters or changes | Project area has very harsh environmental conditions |  | X |  |  |  |  | PM: Project area is subject to a predictable events so far |  | X |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: Project aims to mitigate environmental stressors |  |  |  |  |  |  |
| Social, cultural and economic factors | There are no evident social, cultural and/or economic issues that may affect project performance and results | Social or economic issues or changes pose challenges to project implementation but mitigation strategies have been developed | Project is highly sensitive to economic fluctuations, to social issues or cultural barriers | X |  |  |  |  |  | PM: No evident social, cultural and/or economic issues | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: Agreed |  |  |  |  |  |  |
| Capacity issues | Sound technical and managerial capacity of institutions and other project partners | Weaknesses exist but have been identified and actions is taken to build the necessary capacity | Capacity is very low at all levels and partners require constant support and technical assistance | X |  |  |  |  |  | PM: Capacity development and enhancement is needed however it is considered imporiving | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: Project focuses on addressing the most eminent capacity gaps |  |  |  |  |  |  |
| Others, please specify |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

If there is a significant (over 50% of risk factors) discrepancy between Project Manager and Task Manager rating, an explanation by the Task Manager should be provided below

TOP RISK MITIGATION PLAN

Rank – importance of risk Risk Statement – potential problem (condition and consequence) Action to take – action planned/taken to handle the risk Who – person(s) responsible for the action Date – date by which action needs to be or was completed

| Rank | Risk Statement |  | Action to Take | Who | Date |
| --- | --- | --- | --- | --- | --- |
|  | Condition | Consequence |  |  |  |

Project overall risk rating (Low, Medium, Substantial or High) (Please include PIR risk ratings for all prior periods, add columns as necessary):

| FY2017 rating | FY2018 rating | FY2019 rating | Comments/narrative justifying the current FY rating and any changes (positive or negative) in the rating since the previous reporting period |
| --- | --- | --- | --- |
| High | Medium | Medium to Low | The risk rating is assessed to be improving during the course of the project for the following reasons: - IUCN has established the project team which is working closely with the MoEnv - Active stakeholder participation during the implementation of project activities - Adapting the project activities to the current needs of the MoEnv and concerned stakeholders which is enhancing the validity and ownership of project activities |
|  |  |  | If a risk mitigation plan had been presented for a previous period or as a result of the Mid-Term Review/Evaluation please report on progress or results of its implementation |

For joint projects and where applicable ratings should also be discussed with the Task Manager of co-implementing agency.

Some projects are adopting/planning to adopt milestones for tracking the achievement of outcomes. Add the corresponding milestones in this column when applicable to inform the rating. Milestones are optional and may substitute for Mid-Term Target.

Use GEF Secretariat required six-point scale system: Highly Satisfactory (HS), Satisfactory (S), Marginally Satisfactory (MS), Marginally Unsatisfactory (MU), Unsatisfactory (U), and Highly Unsatisfactory (HU).

Add rows if your objective has more than 3 outcome indicators. Same applies for the number of outcomes.

Outputs as described in the project logframe or in any updated project revision.

As per latest workplan (latest project revision)

Implementation may be assessed by qualitative assessments, percentage of delivery, and/or budget expenditure (planned and actually spent).  The 2018 assessment should be copied from previous PIR.

To be provided by the UNEP Task Manager

Use GEF Secretariat required six-point scale system: Highly Satisfactory (HS), Satisfactory (S), Marginally Satisfactory (MS), Marginally Unsatisfactory (MU), Unsatisfactory (U), and Highly Unsatisfactory (HU)

Only for Substantial to High risk.