GEF-6 REQUEST FOR PROJECT ENDORSEMENT/APPROVAL

Project Type:

Type of Trust Fund:

part i: project information

| Project Title: Supporting Mainstreamed Achievement of Roadmap Targets on Energy in Nauru (SMARTEN) |  |  |  |
| --- | --- | --- | --- |
| Country(ies): | Nauru | GEF Project ID: | 9974 |
| GEF Agency(ies): | UNDP | GEF Agency Project ID: | PIMS 6188 |
| Project Executing Entity(s): | In Nauru: Department of Commerce, Industries and Environment (DCIE) | Submission Date: Resubmission Date: Resubmission Date: | 25 Nov 2019 4 Feb 2020 7 July 2020 |
| GEF Focal Area (s): | Climate Change | Expected Implementation Start | 1 April 2020 |
|  |  | Expected Completion Date | 30 April 2024 |
| Name of Parent Program | N/A | Parent Program ID: | N/A |

- Focal/Non-Focal Area Elements

| ### Programming Directions | ### Focal Area Outcomes | ### Trust Fund | ### (in $) |  |
| --- | --- | --- | --- | --- |
|  |  |  | ### GEF Project Financing | ### Confirmed Co-financing |
| CCM-1-1: Promote timely development, demonstration and financing of low carbon technologies and mitigation options | Accelerated adoption of innovative technologies and management practices for GHG emission reduction and carbon sequestration | GEFTF | 3,302,968 | 22,765,000 |
| Total Project Costs |  |  | 3,302,968 | 22,765,000 |

- Project Description Summary

| ### Project Objective: Enabling the increased applications of feasible RE and EE technologies for supporting socio-economic development in Nauru in accord with the country’s energy roadmap targets |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| ### Project Components/ ### Programs | ### Type | ### Project Outcomes | ### Project Outputs | ### Trust Fund | ### (in $) |  |
|  |  |  |  |  | ### GEF Project Financing | ### Confirmed Co-financing |
| 1: Energy Policy & Regulatory Framework Strengthening | TA | 1: Enforcement of approved policies and rules and regulations on the widespread application of cost-effective RE and EE technologies for energy production and use | 1.1: Formulated, approved and enforced policy and regulatory instruments (standards, policies and implementing rules and regulations) on the application of RE & EE technologies in the energy and energy end use sectors 1.2: Revised and updated energy policy framework (NEPF) , National Energy balance (NEB) and roadmap (NERM) and policies and regulations to achieve NERM targets, inclusive of 10-12 trained DCIE, MoF-PAD, NBoS personnel on M&E of NERM RE & EE targets. 1.3: Approved and implemented fully budgeted national energy plan, inclusive of 18-20 trained DCIE, MoF-PAD, NBos, NUC, RONPHOS personnel and members of district communities and private enterprises on energy planning and financing in the supply and demand sectors. | GEFTF | 78,684 | 541,000 |
| 2: Supporting RE & EE Initiatives | TA | 2.1: Cohesive institutional mechanisms for facilitating widespread application of RE & EE technologies in the country | 2.1.1: Well-coordinated planned and implemented RE/EE Projects of the GoN, private sector and communities 2.1.2: Approved and implemented energy-integrated development projects in the end-use sectors including the mining industry and the regional processing centers, inclusive of 18-20 trained DCIE, MoF, NBoS, DoT, RONPHOS, Eigigu, and RPC personnel on energy integrated development planning & RE/EE technologies. 2.1.3: Established and operational institutional framework that supports the implementation of low carbon (EE & RE) development policies, standards and IRRs. | GEFTF | 77,200 | 531,000 |
|  | INV | 2.2: Adequate amounts of financial resources available for RE/EE Technology application projects in the country | 2.2.1: Feasible financial support schemes for RE & EE technologies application projects in the energy end-use sectors, inclusive of the implementation arrangements, and procedures for financial assistance application process; as well as 20+ trained people from women and youth-led and operated small businesses on RE&EE business and investment opportunities and financing. 2.2.2: De-risked RE-based power generation and grid stability projects, grid-connected or decentralized RE-based energy generation at the district level, inclusive of business plans for the GoN and private sector to facilitate financing and implementation; as well as 12-15 trained DCIE, MoF-PAD, NUC, and RONPHOS personnel on financing and economic aspects of RE and EE. | GEFTF | 430,000 | 2,956,000 |
| 3: Promotion of RE & EE Technologies Applications | TA | 3: Improved confidence in, and application of, RE & EE technologies | 3.1: Documented reports on of the demos results and performance 3.2: Approved implementation designs and plans for the replication and/or scale up of the demos, inclusive of (a) 15-18 trained people from DCIE, DoT, NUC, Eigigu, and local service providers on the design, engineering and installation of RE & EE technologies in the energy and energy end-use sectors; and, (b) 12-15 trained DCIE, MoF-PAD, DoT, NBoS, NUC, and Eigigu personnel on the development and preparation of bankable project proposals. 3.3: Established and operational energy audit system covering all energy end-use sectors, inclusive of 6-8 trained DCIE, and MoF-PAD personnel on conducting energy audits. | GEFTF | 228,100 | 1,568,000 |
|  | INV |  | 3.4: Completed engineering designs and implementation plans of RE & EE demos in the energy and energy end-use sector, inclusive of 10 trained NUC personnel on operation and maintenance of battery storage systems and utility practices with RE for data collection analysis and real time control. 3.5: Implemented and operational RE & EE technologies application demos, inclusive of 4 trained DoT, DWS, and local community people on the operation and maintenance of a mini solar powered treated water production and desalination system; and, 2 trained people on the operation and maintenance of hybrid electric bus and charging station. | GEFTF | 2,174,400 | 14,950,000 |
| 4: Improvement of Energy Sector Capacity | TA | 4: Improved awareness and capacity of the GoN, private sector and communities about cost-effective application of RE and EE technologies and practices | 4.1: Regularly conducted capacity development program on sustainable energy and low carbon development; continuing program on the promotion and awareness enhancement on integrated sustainable energy development; inclusive of 18-20 trained DCIE, MoF-PAD, and NUC personnel, and community leaders on sustainable energy and low carbon development. 4.2: Established and operational information sharing system for the promotion and dissemination of knowledge on all aspects of sustainable energy and low carbon development, inclusive of 10-12 trained DCIE, MoF-PAD, and NUC personnel on the operation and maintenance of an information sharing system. 4.3: Established and operational energy supply and consumption monitoring & reporting and database system, inclusive of 10-12 trained DCIE, MoF-PAD, and NUC personnel on the operation and maintenance of an energy database and an energy monitoring and reporting system. | GEFTF | 157,300 | 1,081,000 |
| Subtotal |  |  |  |  | 3,145,684 | 21,627,000 |
| Project Management Cost (PMC) |  |  |  | GEFTF | 157,284 | 1,138,000 |
| Total Project Costs |  |  |  | GEFTF | 3,302,968 | 22,765,000 |

For multi-trust fund projects, provide the total amount of PMC in Table B, and indicate the split of PMC among the different trust funds here: (N/A)

- Confirmed Sources of Co-financing for the Project by Name and by Type

Please include evidence for co-financing for the project with this form.

| Sources of Co-financing | Name of Co-financier | Type of Co-financing | Investment Mobilized | Amount ($) |
| --- | --- | --- | --- | --- |
| Recipient Country Government | Department of Commerce, Industry and Environment (DCIE) |  |  | 585,000 |
|  | Nauru Utilities Corporation (NUC) |  |  | 22,080,000 |
| GEF Agency | United Nations Development Programme (UNDP) |  |  | 100,000 |
| Total Co-financing |  |  |  | 22,765,000 |

- Trust Fund  Resources Requested by Agency(ies),  Country(ies), Focal Area and the Programming of Funds

| GEF Agency | Trust Fund | Country Name/Global | Focal Area | Programming of Funds | (in $) |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | GEF Project Financing (a) | Agency Fee (b) | Total (c) = a+b |
|  |  | Nauru |  |  | 3,302,968 | 313,782 | 3,616,750 |
| Total GEF Resources |  |  |  |  | 3,302,968 | 313,782 | 3,616,750 |

- Does the project include a “non-grant” instrument?

(If non-grant instruments are used, provide in Annex D an indicative calendar of expected reflows to your Agency  and to the GEF/LDCF/SCCF Trust Fund). N/A

- Project’s Target Contributions to GEF 7 Core Indicators

Update the relevant sub-indicator values for this project using the methodologies indicated in the Core Indicator Worksheet provided in Annex H and aggregating them in the table below. Progress in programming against these targets is updated at mid-term evaluation and at terminal evaluation. Achieved targets will be aggregated and reported any time during the replenishment period. There is no need to complete this table for climate adaptation projects financed solely through LDCF and SCCCF.

| Project Core Indicators |  | Expected at CEO Endorsement |
| --- | --- | --- |
| 6 | Greenhouse Gas Emissions Mitigated (Million metric tons of CO2e) | 1.049 |
| 11 | Number of direct beneficiaries disaggregated by gender as co-benefit of GEF investment | 817 Women 817 Men |

- Project Taxonomy

Please update the table below for the taxonomic information provided at PIF stage. Use the GEF Taxonomy Worksheet provided in Annex I to find the most relevant keywords/topics/themes that best describe the project.

| Level 1 | Level 2 | Level 3 | Level 4 |
| --- | --- | --- | --- |
| Influencing models | Transform policy and regulatory environments |  |  |
|  | Strengthen institutional capacity and decision-making |  |  |
| Stakeholders | Indigenous Peoples |  |  |
|  | Private Sector | Financial intermediaries and market facilitators |  |
|  |  | Individuals/Entrepreneurs |  |
|  | Beneficiaries |  |  |
|  | Local Communities |  |  |
|  | Civil Society | Community Based Organization |  |
|  | Type of Engagement | Information Dissemination |  |
|  |  | Consultation |  |
|  |  | Participation |  |
|  | Communications | Awareness Raising |  |
|  |  | Public Campaigns |  |
| Capacity, Knowledge and Research | Enabling Activities |  |  |
|  | Capacity Development |  |  |
|  | Knowledge Generation and Exchange |  |  |
|  | Innovation |  |  |
|  | Knowledge and Learning | Knowledge Management |  |
|  |  | Capacity Development |  |
|  | Stakeholder Engagement Plan |  |  |
| Gender Equality | Gender results areas | Participation and leadership |  |
|  |  | Awareness raising |  |
| Focal Areas/Theme | Climate Change | Climate Change Mitigation | Energy Efficiency |
|  |  |  | Renewable Energy |
|  |  | Climate Finance (Rio Markers) | Climate Change Mitigation 1 |

part ii:  project justification

Describe any Changes in Alignment with the Project Design with the Original PIF

1a. Project Description.

1a.1) Global environmental problems, root causes and barriers that need to be addressed (systems description)

This section remains largely the same as in the PIF document, there are only few changes, which are explained in the table below:

| GEF-Approved PIF | - Project Document | - Changes |
| --- | --- | --- |
| Diesel GenSets fuel efficiency: 3.48 kWh/Lt of diesel | Diesel GenSets fuel efficiency: - 3.74 kWh/Lt of diesel | - NUC has made significant progress in achieving its ambitious 4.1 kWh/Lt of diesel target for 2020. |
| 2020 Electricity demand estimate: 50 GWh | 2020 Electricity demand estimate: 41.9 GWh | - The estimate has been recently revised downwards during the feasibility study development for the 6.0 MWac ADB solar PV system to take into consideration that RONPHOS secondary mining is not currently viable, and that there will be only 1 Refugee Processing Centre operating, out of the three operating now. |
| Electricity price for Commercial sector: AUD 0.50/kWh | Electricity price for Commercial sector: AUD 0.70/kWh | - NUC decided to align the electricity price for the commercial sector with the Industrial and Government tariff. |

1a.2) Baseline scenario and any associated baseline projects

The following previously identified baseline projects/activities in the GEF-approved PIF are no longer included in the Project Document because these are either already completed or are expected to be completed before the implementation of the SMARTEN project, and therefore replaced with appropriate ongoing and soon-to-be implemented projects. Please refer to Table G-2 in Annex G for the main results/impacts of these completed baseline projects and activities. Nevertheless, It is important to remark that the relevant outcomes and results of these completed, or about to be completed projects, have been considered in the design of the SMARTEN activities. For example, the design of specific investment and technical assistance activities in the project considered the level of RE-based power generation from the completed EU/MFAT-financed solar PV system project and build on it. Moreover, the specific activities on grid stability are also based on the results of the project on the upgrading of the transmission lines of the national electric grid.

The following are additional ongoing, planned and budgeted projects/activities that were further identified during the project development (PPG) phase: (a) the 6.0 MWac (6.9 MWdc) ADB ground-mounted solar PV power system with battery energy storage system; (b) the CTCN Sustainable Land Transport for Nauru; (c) Water Tanks procurement and installation for the 14 districts; (d) the High EE Household Appliances Financing Scheme; and (e) the Nauru Energy Efficiency on the Demand Side (NEEDS) Initiative.

1a.3) Proposed alternative scenario with a brief description of expected outcomes and components of the project

Please refer to Table G-1 of Annex G of this document.

1a.4) Alignment with GEF focal area and/or Impact Program strategies: N/A

1a.5) Incremental/additional cost reasoning and expected contributions from the baseline, the GEFTF, LDCF, SCCF, and co-financing: N/A

1a.6) Global environmental benefits (GEFTF) and/or adaptation benefits (LDCF/SCCF): N/A

1a.7) Innovativeness, sustainability and potential for scaling up: N/A

1b. Project Map and Geo-Coordinates. Please provide geo-referenced information and map where the project interventions will take place.

## Map of Nauru:

## Spatial Coordinates (DCIE): Latitude: 0.5407732 S	     -	Longitude: 166.240574 E

# 1c. Child Project?  NO

2. Stakeholders. Please provide the Stakeholder Engagement Plan or equivalent assessment.

See Annex 4 of the Project Document.

In addition, provide a summary on how stakeholders will be consulted in project execution, the means and timing of engagement, how information will be disseminated, and an explanation of any resource requirements throughout the project/program cycle to ensure proper and meaningful stakeholder engagement.

The designated implementing partner of the SMARTEN project, and therefore the main stakeholder, is the Department of Commerce, Industry and Environment (DCIE). Therefore, the DCIE will assume a leadership role throughout the whole project implementation phase providing guidance and supervision. It will be responsible for communication and coordination with the office of the national GEF OFP and UNDP, it will liaise with villages during implementation of the demo projects, and it will maintain information about RE and EE technologies and measures and divulge it to the general public. Lastly, the DCIE will provide data inputs on plans and programs of the country concerning the energy provision in the projects of the government.

Two important project stakeholders are: (1) the Nauru Utilities Corporation (NUC), will be engaged for the entire duration of SMARTEN and will have a crucial role in the implementation, operation and maintenance of the “Storage of excess solar PV generated electricity in desalinated water” demo. NUC management will also provide data and information to the implementation management team; and, (2) the Ministry of Finance (MoF) will also participate for the entire project implementation phase and will play a crucial role in developing approving and enforcing fiscal/financing incentives to promote RE/EE, and will provide energy and financial information (MoF is in charge of fossil fuels purchase for the entire country). The MoF will also support DCIE in the implementation of the high EE technologies financing scheme. Other key stakeholders that will be engaged during SMARTEN implementation are the: a) Department of Transportation; b) Nauru Bureau of Statistics; and c) Vital Energy Corporation.

The project also involves Community Leaders, both at the district and at the village level, civil society organization such as the Women’s Group, and private sector entities. Indigenous people will be involved through the various village and district leaders, especially during the implementation of the project demos and the awareness raising initiatives.

Select what role civil society will play in the project:

Consulted only.

Member of Advisory Body; contractor.

Co-financier.

Member of project steering committee or equivalent decision-making body.

Executor or co-executor.

Other (Please explain)

3. Gender Equality and Women's Empowerment. Provide the gender analysis or equivalent socio-economic assessment.

A Gender Analysis Report will be submitted separately

Does the project expect to include any gender-responsive measures to address gender gaps or promote gender equality and women’s empowerment? (yes  /no) If yes, please upload gender action plan or equivalent here.

If possible, indicate in which results area(s)  the project is expected to contribute to gender equality:

Closing gender gaps in access to and control over natural resources;

Improving women’s participation and decision making; and or

Generating socio-economic benefits or services for women.

Does the project's results framework or logical framework include gender-sensitive indicators? (yes  /no)

# 4. Private Sector Engagement. Elaborate on the private sector’s engagement in the project, if any.

The GoN has expressed its intention to encourage and stimulate investments from the private sector in the energy sector to integrate the investments from international donors. Due to the remoteness, small economy size and lack of financial institutions that would facilitate the transfer and management of funds, it is very unlikely that foreign investors would finance energy projects in Nauru, unless they have some ties with the country. In the recent past, there have been few investments from the private sector, essentially in the installation of rooftop solar PV systems, mostly grid-connected. For this reason, several SMARTEN activities are designed to attract and favor the participation of the private sector in RE/EE initiatives. This will be achieved by removing the two main existing barriers to a widespread involvement of the private sector. The first is the lack of knowledge of the financial, technical and environmental advantages of RE/EE technologies and measures. This barrier will be removed by designing and conducting several capacity building activities and awareness raising initiatives. The second is the limited available financial resources. To remove this barrier, several financial and fiscal incentives will be established, approved and enforced; furthermore, a very attractive financing scheme for high EE appliances and solar PV panels will be established and supported, to circumvent the lack of financial institutions. The aim of SMARTEN is, by removing the existing barriers, to lay the foundation so that the involvement of the private sector in sustainable energy and low carbon development can continue well past the completion of the project implementation stage, and can be possibly expanded to some of the demos that will be implemented under SMARTEN, such as hybrid and electric vehicles, and mini grids of solar powered water purification and reticulation systems.

# 5. Risks.

During the preparation of the PIF several potential risks that could prevent the achievement of the project objective and outcomes were identified and proper measures to prevent and alleviate their impact on the project were proposed. During the project preparation phase, and more precisely during the Micro HACT assessment of SCIE, the implementing partner, new risks have been highlighted and added to the Risk Log. The design of the SMARTEN project incorporated the suggested risk mitigation measures. As per standard UNDP requirements, the Project Manager will monitor risks quarterly and report on the status of risks to the UNDP Country Office. The UNDP Country Office will record progress in the UNDP ATLAS risk log. Risks will be reported as critical when the impact and probability are high (i.e. when impact is rated as 5, and when impact is rated as 4 and probability is rated at 3 or higher). Management responses to critical risks will also be reported to the GEF in the annual PIR. Refer to Annex 5 of the SMARTEN Project Document.

6. Institutional Arrangement and Coordination. Describe the institutional arrangement for project implementation. Elaborate on the planned coordination with other relevant GEF-financed projects and other initiatives.

The project will be implemented following UNDP’s national implementation modality, per the Standard Basis Assistance Agreement between UNDP and the Government of Nauru, and the Country Programme. The Implementing Partner for this project is the Department of Commerce, Industry and Environment (DCIE). The Implementing Partner is the entity to which the UNDP Administrator has entrusted the implementation of UNDP assistance specified in this signed project document along with the assumption of full responsibility and accountability for the effective use of UNDP resources and the delivery of outputs, as set forth in this document.

The SMARTEN Project will be governed by a Project Board (PB). This board will be made up of representatives from DCIE, MoF-PAD, DoT, NBoS, NUC, RONPHOS, and invited representatives from beneficiary groups such as civil society and local communities, as may be relevant or applicable, and the UNDP-Fiji Multi-Country Office (MCO). The Project Board is responsible for taking corrective action as needed to ensure the project achieves the desired results. In order to ensure UNDP’s ultimate accountability, Project Board decisions should be made in accordance with standards that shall ensure management for development results, best value money, fairness, integrity, transparency and effective international competition. In case consensus cannot be reached within the Board, the UNDP Resident Representative (or their designate) will mediate to find consensus and, if this cannot be found, will take the final decision to ensure project implementation is not unduly delayed.

The DCIE will establish a Project Management Unit (PMU) based in the DCIE headquarter and recruit its personnel for the management of project activities. The PMU will be headed by a Project Manager (PM) who has the authority to run the project on a day-to-day basis on behalf of the Implementing Partner within the constraints laid down by the Project Board. The Implementing Partner appoints the Project Manager, who must be different from the Implementing Partner’s representative in the Project Board. The Project Manager’s primary responsibility is to ensure that the project produces the results specified in the project document, to the required standard of quality and within the specified constraints of time and cost. The Project Manager will inform the Project Board and the Project Assurance roles of any delays or difficulties as they arise during implementation so that appropriate support and corrective measures can be adopted. The Project Manager will remain on contract until the Terminal Evaluation report and the corresponding management response have been finalized and the required tasks for operational closure and transfer of assets are fully completed. Fig. 1 shows a schematic of the Project Organization Structure.

# 7. Consistency with National Priorities.

The proposed project is consistent with the country’s National Energy Policy Framework (NEPF), National Sustainable Development Strategy 2005-2025 (NSDS) and is meant to facilitate the realization of the 2020 RE and EE targets of the country as stated in its NDC. It is also in line with the country’s Second National Communications to the UNFCCC, particularly in specific actions and policies related to EE and RE applications in supporting economic and social development. Specifically, the project is in accord with the country’s Nauru Energy Road Map (NERM) that aims to achieve the following targets by 2020: (1) 50% renewable energy-based electricity generation; and, (2) 30% energy efficiency improvement in the end use sectors (commercial, government and residential). In that regard, the project is expected to contribute to achieving the national energy saving and climate change mitigation targets.

Project Management Unit:

Project Manager (Implementing Partner); Project Implementation and Monitoring Officer; Project Finance and Administrative Officer; National Project Director

Project Board

Development Partners:

MoF-PAD; DoT; NBoS; NUC; RONPHOS, UNDP PO

Project Executive:

Department of Commerce, Industry and Environment (DCIE)

Beneficiary Representatives:

Community Leaders (Districts and Villages)

Project Assurance:

UNDP Pacific Office in Fiji Programme Officer

Project Support (e.g. Project team):

Chief Technical Advisor; Component Coordinators

Fig. 1: Project Organization Structure

National and International Experts and Consultants

Local Technical Experts and Service Providers; Community Leaders; and NGOs

NUC Personnel; RONPHOS Personnel

Project Management Unit:

Project Manager (Implementing Partner); Project Implementation and Monitoring Officer; Project Finance and Administrative Officer; National Project Director

Project Board

Development Partners:

MoF-PAD; DoT; NBoS; NUC; RONPHOS, UNDP PO

Project Executive:

Department of Commerce, Industry and Environment (DCIE)

Beneficiary Representatives:

Community Leaders (Districts and Villages)

Project Assurance:

UNDP Pacific Office in Fiji Programme Officer

Project Support (e.g. Project team):

Chief Technical Advisor; Component Coordinators

Fig. 1: Project Organization Structure

National and International Experts and Consultants

Local Technical Experts and Service Providers; Community Leaders; and NGOs

NUC Personnel; RONPHOS Personnel

8. Knowledge Management.

The low level of capacity and limitations of the country in the planning, design, and sustainable implementation of low carbon development strategies and measures, as well as in EE & RE technology application projects, warrant a focus approach for knowledge management (KM). In this regard, the KM system that will be employed in the project will consists of the conduct of training courses for specific personnel in the DCIE, and in the energy and utilities sector (i.e., NUC and Vital Energy), as well as for national community councils in the different districts of the country. There will be special mentoring sessions for specific group of staff who will be carrying out the operations and maintenance of the various demo/pilot installations that are part of the project. The mentored staff will make up the cadre of in-house experts in the DCIE, DoT, and NUC (and Vital Energy). The information sharing system that will be established and operationalized under this project will also be for the promotion and dissemination of knowledge on low carbon development (including the application of standardized RE-based power generation and distribution systems) within and outside of the country. Moreover, as part of the design, establishment and operationalization of an energy supply and consumption monitoring and reporting, database development and maintenance will be carried out. This aspect of knowledge management, which involve the drawing on information from a wide variety of sources, will be implemented, not only for the country’s energy planning but also to achieve an organized usage of knowledge about the energy situation in the country.

Additional details of the SMARTEN Project’s knowledge management plan are presented in Annex F.

9. Monitoring and Evaluation. Describe the budgeted M & E plan.

To track the successful completion of the project activities and delivery of the intended outputs, the continuous monitoring of project components and activities towards achieving the expected outcome and outputs will be done. This will be carried out in line with the UNDP-GEF monitoring and evaluation (M&E) system. A formal M&E Plan will be adopted during the project inception corresponding to a full-scale project to track the activities and contributions of the activities by all the project partners, in terms of both in-cash and in-kind co-financing contributions to augment the GEF funds. These M&E findings will be reported on in the project’s two in-depth independent reviews during the mid-term and towards the end of the project.

The table below shows the project’s M&E Plan. The M&E will be conducted at multiple levels. At the most basic level, the project manager will be responsible for tracking project indicators and preparing quarterly reports and initial drafts of annual project reports. The project manager will also carry out site visits to the project demos to monitor their progress. The PB will meet at least once every six months to monitor and evaluate project progress, taking actions as necessary. In addition, a mid-term review will be conducted after about two years of implementation and a terminal evaluation as the project is nearing its close. These evaluations will be carried out by parties who have not previously been involved with the project. The project’s M&E plan and indicators will be finalized at the time of inception.

| Monitoring and Evaluation Plan and Budget |  |  |  |
| --- | --- | --- | --- |
| GEF M&E requirements | Responsible Parties | Indicative costs (US$) | Time frame |
| Inception Workshop | Implementing Partner (DCIE) Project Manager | 10,000 | Within 60 days of CEO endorsement of this project. Cannot be charged to GEF Fee. |
| Inception Report | Project Manager | 5,000 | Within 90 days of CEO endorsement of this project. Cannot be charged to GEF Fee. |
| Monitoring of indicators in project results framework | Project Manager will oversee national institutions/agencies charged with collecting results data. | 4,000 per year | Annually prior to GEF PIR. This will include GEF core indicators. Cannot be charged to GEF Fee. |
| GEF Project Implementation Report (PIR) | Regional Technical Advisor UNDP Country Office Project Manager | None | Annually typically between June-August |
| Monitoring all risks (Atlas risk log) | Project Manager | 2,500 per year | On-going. Cannot be charged to GEF Fee. |
| Monitoring of social and environmental safeguard screening | Project Safeguards Officer | 2,500 per year | On-going. Cannot be charged to GEF Fee. |
| Monitoring of stakeholder engagement plan | Project Stakeholder Engagement Officer | 2,500 per year | On-going. Cannot be charged to GEF Fee. |
| Monitoring of gender action plan | Project Gender Officer | 2,500 per year | On-going. Cannot be charged to GEF Fee. |
| Project Board Meetings | Implementing Partner (DCIE) Project Manager | 2,000 per year | Annually. Cannot be charged to GEF Fee. |
| Reports of Project Board Meetings | Implementing Partner (DCIE) Project Manager | None | Annually. Cannot be charged to GEF Fee. |
| Lessons learned and knowledge generation | Project Manager | 4,000 per year | Annually. Cannot be charged to GEF Fee. |
| Supervision missions | UNDP Country Office | None | Annually |
| Oversight missions | UNDP-GEF RTA and UNDP-GEF Directorate | None | Troubleshooting as needed |
| Mid-term GEF and/or LDCF/SCCF Core indicators and METT or other required Tracking Tools | Implementing Partner (DCIE, NUC, MoF-PAD, NBoS, Community Leaders) Project Manager | 10,000 | Before mid-term review mission takes place. Cannot be charged to GEF Fee. |
| Independent Mid-term Review (MTR) and management response | UNDP Evaluation Specialists and independent evaluation consultants. | 30,000 | Between 2nd and 3rd PIR Only oversight can be charged to the GEF Fee. |
| Terminal GEF and/or LDCF/SCCF Core indicators and METT or other required Tracking Tools | Implementing Partner (DCIE) Project Manager | 10,000 | Before terminal evaluation mission takes place Cannot be charged to GEF Fee. |
| Independent Terminal Evaluation (TE) and management response | UNDP Evaluation Specialists and independent evaluation consultants. | 30,000 | At least three months before operational closure Only oversight can be charged to the GEF Fee. |
| Translation of MTR and TE reports into English | UNDP Country Office | None | Cannot be charged to GEF Fee. |
| TOTAL indicative COST Excluding oversight/project assurance costs. |  | 175,000 |  |

10. Benefits.

The successful implementation of SMARTEN will allow Nauru to achieve all three energy targets, which will provide benefits to the entire populations in three different aspects: (1) environmentally, since burning less fossil fuels will allow to reduce the emissions of GHG and particulate matter; (2) financially, because the large solar PV systems and the improved EE will lower the costs of electricity; and (3) security, with more indigenous energy generation, the country will be less exposed to delayed deliveries and sudden fossil fuels prices increase. The financing scheme for energy efficient appliances and rooftop solar PV systems will be accessible to households and small businesses, allowing them to receive a significant rebate on the purchase of these technologies. Similarly, the electricity storage system in desalinated water and the hybrid bus for public transportation will provide more reliable clean water resource while reducing electricity prices and an alternative to private vehicles, especially useful for those who do not own one. Lastly, the Mini solar powered treated water production and distribution system demo will directly benefit the community in which it will be installed is. However, indirectly this demo will benefit the entire population, by paving the road to scale-up and replication projects, for which there is large potential, since Nauru does not have a water reticulation system in place.

Since the main essence of the proposed project is the reduction of diesel fuel oil-based power generation in the country, the global environmental benefits of the proposed GEF project would mainly come from GHG emission reductions (tons CO2) from fossil fuel substitutions in electricity generation, and other energy end-uses particularly in using available feasible RE resources. Sustainable energy initiatives that would lead to the improvement of the specific energy consumption of energy end use sectors through improved energy utilization efficiency will also contribute to this. In summary, the GHG emissions reductions would come from: (1) Direct emission reductions from completed sustainable energy and low carbon technology application demonstrations and replications; and, (2) Indirect emission reductions from follow-up sustainable energy and low carbon (RE and EE) technology application projects in the country as influenced by this proposed GEF project. Further environmental benefits will derive from the improvement in energy efficiency as well as a transition from diesel and gasoline cars to hybrid and electric vehicles.

PART IV: Annexes

Annex A: Project Results Framework

| This project will contribute to the following Sustainable Development Goal (s): SDG 7: “Ensure access to affordable, reliable, sustainable and modern energy for all”; SDG 13: “Take urgent action to combat climate change and its impacts by regulating emissions and promoting developments in renewable energy”; |  |  |  |  |
| --- | --- | --- | --- | --- |
| This project will contribute to the following country outcome (UNDAF/CPD, RPD, GPD): UN Pacific Strategy 2018-2022: Outcome 1 – Climate Change, Disaster Resilience and Environmental Protection; UNDP Sub-Regional Programme Document 2018-2022: Outcome 1 – By year 2022, people and ecosystems in the Pacific are more resilient to the impacts of climate change, climate variability and disasters; and environmental protection is strengthened. |  |  |  |  |
|  | Objective and Outcome Indicators | Baseline | Mid-term Target | End of Project Target |
| Project Objective: Enabling the increased applications of feasible RE and EE technologies for supporting socio-economic development in Nauru in accord with the country’s energy roadmap targets | Cumulative GHG emission reduction from fossil fuel utilization in the electricity sector, tons CO2 | 0 | 15,867 | 43,858 |
|  | Cumulative reduction in fossil fuel consumption due to implemented RE and EE technology projects as influenced by the project interventions, toe | 0 | 5,048 | 13,955 |
|  | % RE electricity production | 3.0% | 45.3% | 47.4% |
|  | No. of individuals that are gainfully employed in new jobs created due to the application of RE and EE technologies in the country: Direct: * Male: * Female Indirect: * Male * Female: | 0 0 0 0 0 | 12 4 4 2 2 | 36 12 12 6 6 |
| Component 1: | Energy Policy & Regulatory Framework Strengthening |  |  |  |
| Outcome 1: Enforcement of approved policies and rules and regulations on the widespread application of cost-effective RE and EE technologies for energy production and use | % planned NERM 2018-2020, and revisions, activities that are implemented | 0% | 30% | 95% |
|  | No. of planned energy-integrated socio-economic development activities (e.g., in the districts) that feature RE and EE technology applications | 0 | 1 | 3 |
|  | No. of new policies and regulations drafted, approved and implemented to cover the changing RE/EE sector | 0 | 2 | 3 |
| Outputs to achieve Outcome 1 | Output 1.1: Formulated, approved and enforced policy and regulatory instruments (standards, policies and implementing rules and regulations) on the application of RE & EE technologies in the energy and energy end use sectors Output 1.2: Revised and updated energy policy framework (NEPF) , National Energy balance (NEB) and roadmap (NERM) and policies and regulations to achieve NERM targets Output 1.3: Approved and implemented fully budgeted national energy plan |  |  |  |
| Component 2: | Supporting RE & EE Initiatives |  |  |  |
| Outcome 2.1: Cohesive institutional mechanisms for facilitating widespread application of RE & EE technologies in the country | No. of GoN agencies/entities that coordinate with the DCIE their energy-related plans and activities | 0 | 3 | 3 |
|  | No. of districts that coordinate with the DCIE the planning and implementation of the energy-related activities of the communities and private sector entities within their area | 0 | 3 | 8 |
|  | No. of jointly-implemented projects or collaborative initiatives carried out by the DCIE with other GoN entities (e.g., NUC, RONPHOS), private sector and public on sustainable energy and low carbon development | 0 | 2 | 5 |
| Outputs to achieve Outcome 2.1 | Output 2.1.1: Well-coordinated planned and implemented RE/EE Projects of the GoN, private sector and communities Output 2.1.2: Approved and implemented energy-integrated development projects in the end-use sectors including the mining industry and the regional processing centers Output 2.1.3: Established and operational institutional framework that supports the implementation of low carbon (EE & RE) development policies, standards and IRRs |  |  |  |
| Outcome 2.2: Adequate amounts of financial resources available for RE/EE Technology application projects in the country | No. of RE and EE financial schemes, as well as fiscal and financial incentives, developed and adopted for supporting RE and EE initiatives in the country | 0 | 2 | 2 |
|  | No. of women-led/owned and youth group operated businesses that benefited from the financing schemes, and fiscal and financial incentives | 0 | 1 | 4 |
|  | No. of EE and RE technology projects financed either through the adopted financing scheme, and fiscal and financial incentives; or by private sector investment | 0 | 3 | 8 |
| Outputs to achieve Outcome 2.2 | Output 2.2.1: Feasible financial support schemes for RE & EE technologies application projects in the energy end-use sectors, inclusive of the implementation arrangements, and procedures for financial assistance application process Output 2.2.2: De-risked RE-based power generation and grid stability projects, grid-connected or decentralized RE-based energy generation at the district level, inclusive of business plans for the GoN and private sector to facilitate financing and implementation |  |  |  |
| Component 3: | Promotion of RE & EE Technologies Applications |  |  |  |
| Outcome 3: Improved confidence in, and application of, RE & EE technologies | No. of replication and scale-up RE and EE technology projects planned and implemented by the GoN to achieve the NERM targets | 0 | 2 | 5 |
|  | Cumulative amount of energy savings from the successfully installed and operational demonstration RE and EE technology application projects, ktoe | 0 | 66.1 | 200.0 |
|  | No. of RE and EE technologies application projects designed and financed by the private sector for implementation as influenced by the results and outcomes of the demonstrations implemented under the project | 0 | 1 | 5 |
| Outputs to achieve Outcome 3 | Output 3.1: Completed engineering designs and implementation plans of the identified demonstrations of RE & EE technologies applications in the energy generation and end-use sectors Output 3.2: Documented and disseminated reports about the energy performance and impact assessments of implemented demonstrations Output 3.3: Approved implementation designs and plans for the replication and/or scale up of demonstrated RE & EE technologies applications Output 3.4: Established and operational energy audit system covering all energy end-use sectors Output 3.5: Implemented and operational RE & EE technologies application demos |  |  |  |
| Component 4: | Improvement of Energy Sector Capacity |  |  |  |
| Outcome 4: Improved awareness and capacity of the GoN, private sector and communities about cost-effective application of RE and EE technologies and practices | No. of RE and EE technology application projects designed, implemented and maintained by NUC and district communities | 0 | 2 | 6 |
|  | No. of sustainable energy projects implemented by the private sector and district communities with funding sourced from the private sector and other development partners | 0 | 1 | 3 |
|  | No. of consumers/users in the energy end-use sectors that are utilizing EE appliances and RE-based energy generating and consuming equipment | 0 | 350 | 1,390 |
| Outputs to achieve Outcome 4 | Output 4.1: Regularly conducted capacity development program on sustainable energy and low carbon development; continuing program on the promotion and awareness enhancement on integrated sustainable energy development Output 4.2: Established and operational information sharing system for the promotion and dissemination of knowledge on all aspects of sustainable energy and low carbon development Output 4.3: Established and operational energy supply and consumption monitoring & reporting and database system |  |  |  |

Annex B: Response to Project Reviews (from GEF Secretariat and GEF Agencies, and Responses to Comments from Council at work program inclusion, and responses to comments from the Convention Secretariat and STAP at PIF).

Exhibit B.1: Responses to GEFSec Comments (19 June 2020)

| Comment & Response |  | Reference |
| --- | --- | --- |
| 12. Is CEO endorsement recommended? |  |  |
| Comment: Audits are ineligible items under M&E. Response: The Financial Audit activity has been removed from M&E Plan and Budget table. The budget for this project management activity is as designed is covered under the project management cost. | ProDoc: Sec. VI, p. 55, TBWP p. 67 |  |
| Comment: Although all the sources of co-financing indicated in the Portal come with co-financiers’ letters, there seems to be a disconnect between what is in the Portal and the confirmed financing sources in the Project Document. The Project Document (see snapshot) refers to ADB, Gov’t of New Zealand and CTCN as major sources of co-financing – the info has to be consistent across the documents and Portal. Please check Table C and Table VIII carefully to find out the inconsistency and revise them. Response: The project co-financing comes from the Department of Commerce, Industries and Environment (DCIE), Nauru Utilities Corporation (NUC), and the UNDP. The GoNZ-funded project (NEEDS Initiative) and the CTCN-funded project (Sustainable Land Transport for Nauru) are both under the DCIE. The GON-funded project (Water Tanks Procurement) is also under the DCIE. These baseline projects of the DCIE are part and parcel of the SMARTEN Project, and their collective available budgets (US$ 585,000) is part of the co-financing from DCIE. The ADB-funded project (Solar Expansion Plan) and the existing Low Carbon Fund are both under the NUC. These are also subsumed into the SMARTEN Project as baseline projects. Their collective available budgets (US$ 22.08 million) is part of the co-financing from NUC. The rest of the co-financing (US$ 100,000) is from UNDP. The table in question, which is on the confirmed co-financing (ProDoc, pp. 62-63) has been corrected to show the details of the co-financing as described above. Co-financing source; Co-financing type; Co-financing amount (US$); Planned Co-financing Activities/Outputs; Risks; Risk Mitigation Measures. DCIE; Grant; 250,000; Water Tanks Procurement: As part of the government (DCIE) efforts to strengthen its water security, water tanks will be procured and distributed to all districts; Government (DCIE) diverts funds to other uses; Facilitate through government procurement system as national priority. Grant; 320,000; NEEDS Initiative: GoNZ-MFAT is providing technical assistance to the DCIE to select the most promising EE projects and measures from an existing shortlist that will enable Nauru to improve its EE; The technical assistance is currently being provided and there are no identified risks to prevent its completion; N/A. Grant; 15,000; Sustainable Land Transport for Nauru: CTCN is supporting the DCIE in the assessment of the transport sector in Nauru with the objective to reduce the reliance on fossil fuels for the land transportation; The donor changes its priorities or delays the disbursement of the funds; Support the DCIE in liaising with CTCN to secure the budget. NUC; Grant; 80,000; Low Carbon Fund: This is an existing financial scheme operated and managed by the NUC to financially support the purchase of energy efficient appliances (washing machines and fridges) by households; The scheme will not be completed because energy and cost savings are not clearly quantified to the general public; Informative campaign to show the energy and cost advantages of RE/EE technologies is readily organized as part of SMARTEN. Grant; 22,000,000; Solar Expansion Plan: This is an ADB-funded project of the NUC involving the installation and operation of a 6.0 MWac solar PV system supported by a 2.5MWh/5.0MW battery energy storage system, which will allow Nauru to get close to its 50% electricity from RE target; Project may get delayed if the propaedeutic ground preparation stage conducted by the NUC incur in some hiccups; There is no identified direct risk or mitigation measure for ADB, but it refers to the GoN (NUC) portion of the project. UNDP; Grant; 100,000; Project management and M&E; None; N/A. Total; 22,765,000. Grant; 22,765,000. In-Kind; 0. | ProDoc: Sec. VIII, pp. 62-63 |  |

Exhibit B.2: Responses to GEFSec Comments (6 March 2020)

| Comment & Response | Reference |
| --- | --- |
| 1. If there are any changes from that presented in the PIF, have justifications been provided? |  |
| Comment: Not at this time. Per the response of the Agency, lots of new renewable energy and energy efficiency activities were financed and will be financed by other parties such as the ADB and the EU. Please use a table to show each of these activities, funding amounts and their outputs or impacts in the country. Then, justify the revisions or changes of the current GEF project activities. Please also indicate why the Agency did not know these project activities at the PIF stage for a small country with less than 12,000 people. In the new version of the CEO ER document, please highlight in color the revisions of the document. Response: Just for clarity, the project proponents and the GEF Agency are aware that currently there are no EU funded projects that are ongoing or planned for Nauru. In the recent past, the EU has co-financed the installation of a 1 MWp solar PV farm (in partnership with NZ MFAT) and the construction of a high voltage transmission system through the middle of the island to connect to the national grid the new solar PV power generation installations (i.e., the EU/MFAT project, and the planned ADB solar PV project) and the new loads, which are the new prison and the Refugee Processing Centres. These two donor-funded projects only included some hands-on training of local technicians on the installation, operation and maintenance of the equipment installed. As already explained in the responses to the previous round of GEFSec comments, and clarified on Page 5 of the CERDoc, some of the projects that were originally identified during the PIF stage as baseline for the proposed SMARTEN Project have either been already completed or will be completed before the beginning of the implementation phase of this project. It is important to remark that the relevant outcomes and results of these completed, or about to be completed projects, have been considered in the design of the SMARTEN Project activities. Please refer to Table G-2 (Annex G) of the CEO Endorsement Request (CER) Document for the summary of the results/impacts of the completed baseline projects/activities. Some of the previously identified baseline projects have been replaced by new projects that will contribute to the achievement of the objective of the SMARTEN Project. Among these are the projects on the installation of a solar PV system by the ADB; setting up of new water tanks in all 14 districts by the GON; and supporting a sustainable land transport system in Nauru by the Climate Technology Centre & Network (CTCN). These new baseline projects are also in line with the aim of facilitating the use of feasible renewable energy (RE) and energy efficiency (EE) technologies for supporting socio-economic development in Nauru and are also in line with the achievement of the country’s energy roadmap (NERM) targets. The reason why these projects were not included the list of baseline projects in the PIF is because they have only been announced, and funds secured, during the project preparation stage. | CERDoc: Part II, Sec. 1a.2, pp. 5-6 CERDoc: Annex G, Table G-2 ProDoc: Table 1, Part II, pp. 13-14; ProDoc: Part VIII, pp. 63-64 |
| 2. Is the project structure/ design appropriate to achieve the expected outcomes and outputs? |  |
| Comment: Not at this time. Training or capacity building for local government and industrial stakeholders is a means of, but not a goal of delivering global environment benefits. Please focus on investment in tangible technologies in this GEF project. Response: The project proponents understand that capacity development is among the means of removing specific barriers, and once such barriers are removed will bring about the global environment benefits that are expected from this proposed project. Hence, this project is designed with the idea that capacity development as the contributors to the realization of the project goal. As it has been designed, the project focuses on the removal of barriers and to do that involves investment in tangible technologies that will bring about the achievement of the RE and EE targets of Nauru under its energy road map, but also bring about global environmental benefits. The investment activities and demonstrations of the project have a combined budget of US$ 2,604,400 (including detailed demo design), or 83% of the total GEF funding. | ProDoc: Part IV, pp. 22-37. ProDoc: Part IX; Budget Notes, pp. 68-70 CERDoc: Part B, pp. 1-3 |
| Comment: 1. The listed 13 training activities need to be justified. Why does the country need so many training activities given that the ADB and the EU have done so many projects on ground? Please justify the additional value of the GEF training. Please justify why the GEF should always support face-to-face meetings for training, why not use virtual programs for the training. Response: The proposed training programs have been designed based on the needs and gaps that emerged during stakeholder consultations with the members of the project development team. Nauru has very limited in-house expertise regarding the various aspects of RE and EE technology regulation and implementation, as also evidenced by the result of the Micro HACT assessment. This required the design of several training programs spanning from policy and regulations to finance and institutional mechanisms, as well as from awareness raising to technology installation, operation and maintenance. The proposed training programs have been designed to complement, and not overlap, the training activities that will be carried on as part of the ADB project. As mentioned in the response above, EU did not provide training programs and currently there are none scheduled. Experience and lesson learned from other GEF projects implemented in the Pacific region SIDS have shown that in-person training have been more successful that online programs. |  |
| Comment: 2. Please articulate the training materials and trainers for the training program. Response: As already shown in the responses to the first round of GEFSec comments, the majority of the proposed training programs will range from US$ 6,000 to US$ 8,000, while those in the US$ 12,000-15,000 range will be delivered into two cycles. These training programs are relatively inexpensive and only require the procurement of international specialists and the preparation of some printouts to facilitate the trainees. The most expensive training is for 4 local technicians on how to operate and maintain the equipment that will be acquired as part of the demos. However, the cost for these training activities is part of the procurement and installation of the equipment and systems of each demo. The higher cost of this training activity is because the technicians will be trained overseas, because the training will require actual hands-on experience. Such training is cheaper to organize at the vendors’ facilities rather than shipping trainers and the required training units to Nauru. | Supplemental Annex, p. 23 & p. 25. |
| Comment: 3. Please justify why not use one training program session for all government agencies. Response: While there might be some trainees that will participate in more than just one training program, due to the vast range of subjects covered several trainers will be required to conduct all 13 training programs. In addition, as indicated in the Multi-Year Work Plan of the ProDoc, the timing of all training programs does not coincide since some activities are propaedeutic to the training programs, while these are in turn preparatory to other activities. Finally, owing it to the large number and variety of topics covered in the programs it would be too difficult to effectively deliver them all at once, and obtain effective capacity development results. |  |
| Comment: 4. Please redesign Table B into three components: 1. Policy development, training and capacity building. Please put all training and capacity building in this component. 2. Capital investment. Please use at least 80% of GEF grant in this component. The GEF investment should be in the area that has not been invested by the ADB and the EU. Response: As explained in the responses to the first round of GEFSec comments, Component 2 of the proposed SMARTEN project already merges the strengthening of Institutional framework and the improvements in Financial Resources for RE/EE technologies, two areas that in the logical framework analysis (LFA) that was conducted to come up with the project results framework, are in separate components, as is in similar UNDP-GEF funded projects in the Pacific (e.g., Niue: AREAN, Vanuatu: BRANTV). The essence of the project’s log frame will be significantly affected, and its clarity lost if the project components are organized by types of activities, as opposed to by areas of interventions (i.e., each component focusing on the removal of a major type of barrier). As designed, based on the project Log Frame, there are already two Investment Components, for a combined budget of US$ 2,604,400, or 83% of the GEF grant (excluding the Project Management Costs). | CERDoc: Part I, Sec B, pp 1-3 ProDoc: Part IV, pp. 22-37. |
| Comment: 5. Please design Component 3 to ensure that GEF's project will be implemented without distraction, and that the GEF project impacts will be sustainable after the GEF project implementation is over. For example, with this component implementation, the government will be able to really ensure and monitor the mainstream of renewable energy and energy efficiency in the country's energy development strategy, policy and investment. Response: Delivering an appropriate range of training programs, as designed in the proposed project, to build local capacity will also address another sensible concern raised by the reviewer, guarantee sustainability past the implementation phase of SMARTEN by strengthening the capacity of the relevant government ministries and departments, as well as of the national utility. |  |
| 3. Is the financing adequate and does the project demonstrate a cost-effective approach to meet the project objective? |  |
| Comment: Not at this time. From the CEO RE document, the PM of the GEF cannot see any "increased applications of feasible RE and EE technologies" that is highlighted in the objective of the project by the Agency. Also the agency used a wrong method to justify the cost-effectiveness of the current project. GEBs of GEF CCM projects, namely CO2 emission reductions, are not for emission trading. The costs of unit reduction of CO2 in GEF projects should not be used to compare that in any CO2 trading market. Please look at the GEF or UNDP CCM project portfolio and compare the cost-effectiveness of CO2 emission reduction of this project against the average of any of the portfolios. Response: First of all, it is important to take into consideration that with the completion of the ADB solar PV project, Nauru will generate nearly 50% of its electricity needs from solar PV systems. After the ADB project is completed, the electricity that will be generated during daytime with the solar PV panels will be larger than the power demand during the same period of time. Since ADB deems too expensive to store the electricity in batteries it will only provide half an hour batteries for grid stabilization and as a result the excess electricity that the ADB project will generate during peak sun hours will be curtailed. Adding more RE for electricity generation, which in Nauru means more PV (because solar thermal for power generation is not suited for SIDS in the Pacific, there is no sufficient wind near the equator, OTEC is too expensive, and there are no hydro resources), would mean adding power generation during the day time when there is already overcapacity and all the electricity generated would need to be stored. That is why our efforts have concentrated on a technology that would allow storing the electricity generated by the ADB solar PV system that would have been curtailed. The designed demos and investment type activities will introduce in Nauru several RE and EE technologies, specifically: - The RE/EE financing scheme supports the adoption of high EE appliances and the implementation of small rooftop PV systems. - A water desalination unit used as an electricity storage system to recover the electricity curtailed by the ADB solar PV system, which will also serve another great need for Nauru, which is additional water desalination capacity. Furthermore, due to the modularity of these units, they can be easily replicated and scaled up in the future, as discussed in the Supplemental Annex file, pp.19-20. - The mini solar powered water production and distribution system for a community includes solar pumps, as well as solar PV panels and batteries to operate the water treatment unit and the distribution system. - The hybrid diesel-electric bus with a charging station will introduce an environmentally friendly public transportation system. The project proponents do not mean to imply the trading of the CO2 emission reductions nor the establishment of a CO2 trading market in Nauru but are just using the price that the market gives to the removal of 1 ton of CO2 emissions as a benchmark against which to compare the unit abatement cost (UAC) in Nauru. Indeed, SMARTEN should be compared with other UNDP-GEF projects in SIDSs in the Pacific region, which are similarly small and far from large developed countries and therefore requiring very high freight costs as well as high costs to bring on-site technical experts for the project implementation. The unit abatement cost (UAC) for the SMARTEN Project, i.e., GEF grant per ton CO2 emission reduction, of approximately US$ 3.15/ton CO2, compares favorably to the average US$ 6.0/ton CO2; i.e., GEF$ per total lifetime GHG ER (direct + indirect) of full-sized projects UNDP-GEF CCM projects in the Pacific region. Considering both the GEF grant of US$ 3.30 million and the co-financing of US$ 22.77 million, and the overall GHG emission reduction (direct + indirect), the resulting UAC is US$ 24.85/ton CO2, which is lower than the average total cost (GEF + co-financing) per total lifetime GHG ER (direct + indirect) of US$ 42/ton CO2 of UNDP-GEF CCM projects in the region. | Supplemental Annex file: pp. 18-26 |
| 4. Does the project take into account potential major risks, including the consequences of climate change, and describes sufficient risk response measures? (e.g., measures to enhance climate resilience) |  |
| Comment: After the project is redesigned, please address again the possible impact of climate change on the capital investment or on the tangible equipment that will be installed by the GEF financing in this project. Response: Based on the responses in the previous comments above, the project proponents believe that the project design is in complete agreement with the concept as presented in the GEF-approved PIF and the project Log Frame. Hence, the risks and their analyses are the same included in the Risk Log table on pp. 40-44 of the ProDoc. | ProDoc: Part IV, pp. 40-44 |
| 6. Are relevant tracking tools completed? |  |
| Comment: One more question please. Has the agency or the country considered this following fact? Nauru has a total of less than 11,000 people now. More than half of them will have been able to access renewable energy after the ADB and the EU programs are over, per the response of the agency. Can the agency and the country use the GEF grant and the co-financing grants (totaling $26 million) to provide zero-carbon electricity or energy to the rest 50% of the 11,000 people. Please address this question with evidence. Response: It is important to clarify that Nauru has a single national electric grid that reaches practically 100% of the population. Hence, everyone has access to the grid. The ADB solar PV system will be integrated into that grid. Once that project is completed, approximately 50% of the electricity generation will come from solar PV systems, with the balance coming from diesel generators. Therefore it is not correct to state that about 50% of the population will receive electricity from solar PV and the balance from diesel, but the correct statement is that about 50% of the electricity that each and every Nauruan consumes will be generated with solar PV systems and the remainder with diesel generators. While the project proponents agree with the reviewer that the cost of the ADB project is quite high, it should be noted that the project proponents have no control over it. Furthermore, the design of the ADB project is based on providing enough PV panels to the existing installations to achieve 50% electricity generation from RE (one of the targets set by the government of Nauru in its energy roadmap), which ADB estimated to be US$ 22M. Therefore, if the costs estimates, which were performed by an Australian consulting firm, would have been lower, ADB would have allocated a lower budget and not provided more solar PV panels. It is also important to remark that the sizing of the ADB solar PV farm has been based on generating 50% of the estimated electricity demand with solar PV systems. However, the demand curve during the sun hours does not match the generation curve. The generation capacity is larger than demand, and not enough electricity storage is provided, because storage was estimated to be too expensive. Because of this design choice, during days with a clear sky, a portion of the ADB solar PV power generation capacity is curtailed. In other words a portion of the PV panels are disconnected during peak hours. This means that less than 50% of the electricity consumed comes from RE (please refer to the Supplemental Annex file, Part 3, pp. 13-15). | Supplemental Annex file: Part 3, pp. 13-15 |
| 10. Does the project have descriptions of a knowledge management plan? |  |
| Comment: Not completed at this time. For the total number of trainees (163-186 people), please divide them into two groups: (1) Critical group, without face-to-face training, this project will fail: (2) not so important group. For it, a virtual training program is enough. Response: The project proponents, based on their experience with previous capacity development activities in the country strongly recommend the much effective training programs as designed, i.e., involving face-to-face training sessions instead of online training. It is also important to highlight that additional stakeholder consultations, held during the preparation of this round of responses to the latest comments from the GEFSec, have indicated that their preference would be for conducting face-to-face training programs. The proposed budget for most training activities is already very thin (in the US$ 6-8k range) and there won’t really be budget savings if anything, by changing the designed training activities to online courses. The project proponents also want to point out that, excluding the overseas training of the technicians that will operate and maintain the demos, the combined budget for the remaining 12 training programs is only US$ 111,000, or 3.5% of the total GEF grant (excluding the Project Management Cost). | Part IX; Budget Notes, pp. 68-70 |
| Comment: Please re-write the pages 43-44 per the following sub-sections: (1) an overview of existing lessons and best practice that inform the project concept; (2) plans to learn from relevant projects, programs, initiatives & evaluations; (3) proposed processes to capture, assess and document info, lessons, best practice & expertise generated during implementation; (4) proposed tools and methods for knowledge exchange, learning & collaboration; (5) proposed knowledge outputs to be produced and shared with stakeholders; (6) a discussion on how knowledge and learning will contribute to overall project/program impact and sustainability plans for strategic communications. Response: The additional information requested by the reviewer and based on the suggested sub-sections have been provided in the Knowledge Management section of the CEO Endorsement Request Document. | CERDoc: Part II, Sec. 8; and, Annex F |
| 11. Has the Agency adequately responded to comments at the PIF stage from: |  |
| GEFSEC: Not completed at this time. At the PIF stage, the PM commented the following: |  |
| Comment: Supplemental Annex File Annex B p. 17 presented the ADB project as the baseline of this GEF project (The ADB will installed 6 MW renewable energy for 50% of the country residents). But it does not show any thing about the RE energy capacity to be developed or installed by the GEF project. Please provide this information. Please put this information in Table B of the CEO ER document. Response: The project proponents emphasize that the baseline ADB solar PV system (6 MW) will not serve only 50% of the country residents, but that system will enable about 50% of the electricity production in the country to be derived from renewable energy sources (i.e., solar energy). Since the electricity produced from that system is injected into the country’s main and only grid, everyone in the country has access to that solar energy-derived electricity. Under the SMARTEN project, the GEF grant is used to finance 2 investment type activities and 3 demos (please see the Supplemental Annex file, pp 17-26): The first investment type activity is for guaranteeing a much-improved grid-connected solar PV system building on the ADB solar PV project. The improvement involves filling a major gap in that baseline activity. The baseline ADB solar PV project only provides a battery (half hour capacity) as a tool for grid stabilization. Such is deemed insufficient by the international grid system specialist member of the project development team. The consulting firm hired by ADB confirmed that there wasn’t a thorough grid stabilization analysis conducted, as it can be verified in the design documents prepared for the ADB project. The incremental investment type activities that will be implemented are to facilitate the full utilization of the electricity produced by the ADB solar PV system and enabling the stable operation of the national grid when the ADB solar PV system is integrated into it. Figure 1, on page 13 of the Supplemental Annex file, shows the average daily electricity demand in 2022 (when the ADB project is expected to be fully operational), which is relatively flat compared to other countries with just a slight peak during the daytime. Figure 2, on page 15 of the Supplemental Annex file, shows the mismatch between the same average demand curve and the average daily electricity generation curve. This figure visually shows the excess generation capacity. Even in the most conservative option, which assumes that batteries are only charged when there is overcapacity, there is a substantial amount of power generation capacity that needs to be curtailed. For grid stability, it might be a preferred choice to charge the batteries first thing in the morning, to have electricity storage available to compensate for a potential sudden drop in PV power generation capacity. The project development team estimates, based on the average daily demand and generation curves, that the amount of electricity curtailed is 1,140 MWh/year. Considering that according to GHD estimates, which are very aggressive, the ADB solar PV farm can generate at full capacity (without curtailment) 12,450 MWh in 2022, the first full year of operation. In that case, the curtailed electricity represents about 9.1% of the total electricity generation potential or, in power generation capacity terms, it would be equivalent to reducing the power installed to about 5.45 MWp. An extremely important conclusion that can be drawn by analyzing Figure 2 is that any additional solar PV installation would be useless, unless enough storage capacity is added concomitantly. The second investment type activity, which is a RE/EE financing scheme, is designed to address the financial barriers as well as to facilitate the achievement of the 30% EE target set by the government in its energy roadmap, and for which there are no sufficient efforts done. The scheme will allow installing 25 5-kWp rooftop solar PV systems and hundreds of high EE appliances. As it is shown on page 19 of the Supplemental Annex file, the scheme is expected to reduce the annual GHG emissions by 895 tCO2, which is the same result that would be achieved by installing and operating a 700 kWp solar PV system. By adopting the same logic to the three demos, the annual reduction of GHG emissions would amount to an incremental 200 kWp solar PV system, which based on the calculations in “Footnote #1” would cost about US$ 1.8 million minimum. In terms of GHG emission reductions, SMARTEN would achieve the same results that would be achieved by installing an incremental 900 kWp solar PV system, which based on the calculations in “Footnote #1” would cost about US$ 8.1 million minimum. In addition, there are the tangible benefits of improved grid stability from the first investment type activity, hundreds of thousands liters of desalinated water produced, a desalinated water generation and distribution mini-grid system for a small community, an energy efficient and environment friendly mean of public transportation, and deployment of hundreds of high EE appliances facilitated by the RE/EE financing scheme. | Supplemental Annex file: Annex B, pp. 13, 15, and 17-26 |
| GEF Council: |  |
| Comment: Not at this time. The Agency has not effectively addressed the comments of the Council members. Please see the comments of the PM above. Please revise the project components per the above comments. Please use the GEF grant and the co-financing grants to do installation of renewable energy technologies in the country as the ADB is doing. There is little necessity for RE energy technology demonstrations since the ADB and the EU are massively installing renewable energy technologies in the country to supply renewable energy for 50% of the residents. The Agency needs to make best use of the GEF grant and government grant co-financing to supply the remainder 50% of residents with renewable energy . Response: In the responses immediately above this, the project proponents have addressed the comments of the council members explaining why Nauru has reached a stage where additional installation of solar PV systems is not cost-effective (please refer to “Footnote #1”), and for this reason the project development team, following the information gathered during stakeholder consultations, have designed a combination of power and non-power applications of solar energy in Nauru, which ultimately contribute to the achievement of the RE and EE targets set in the NERM. Unless a considerably cheaper electricity storage technology is demonstrated and deployed in Nauru, there is no financial convenience in installing more PV system. While pumped hydro storage seems to be a potential option, but this technology needs to be assessed in a complex environment such as Nauru, because of the topside limestone pinnacles covering the majority of the soil and the fact that the highest point of the island is only about 60-70 meters above the sea level. |  |
| 12. Is CEO endorsement recommended? |  |
| Comment: Not at this time. The Country needs more tangible investment than financial scheme. With the GEF $3.3 million grant and the cash co-financing $22.76 million of the national government, the GEF project should be able to finance enough equipment for the remainder of 5,500 (50% of 11,000) people so that they will use renewable energy. The PM cannot figure out why the agency needs $4,727 per person ($26 million divided by 5,500 people) to develop a financing scheme for these people. The $4,727 per person is more than enough for them to harness renewable energy. In short, the project design is not cost-effective. Response: As can be gleaned from the Supplemental Annex, it is not only the RE/EE financial scheme that comprise the tangible investments that will be implemented under the proposed project. It is important again to take note that the baseline ADB solar PV project will allow achieving nearly 50% of electricity generation from RE sources. Since there is only a single national electric grid, this will serve everybody. In other words, every Nauruan will use electricity that is generated 50% from RE and the balance from diesel. Adding more RE capacity means to generate more electricity during a period of the day for which there is already overcapacity, which is impractical and expensive. Therefore, what is needed to supplement the baseline ADB project is an electricity storage system, which will be done in the project through desalinated water. The excess electricity from the baseline ADB project will be used to produce more desalinated water that will be distributed to water users in the country. This innovative energy storage scheme practically also provide additional water desalination capacity for the country. Furthermore, regardless of the considerations on the cost-effectiveness of the baseline project, i.e., ADB solar PV system, although the project proponents are in full agreement with the reviewer that such project is not cost-effective, they and the project development team have no control and authority on how the budget of that project is determined and spent. Even though the cost-effectiveness of the ADB solar PV system cannot be improved by the project proponents, the outputs of the baseline ADB project can, and will, be significantly optimized thanks to the design of the SMARTEN incremental activities. Specifically, the implementation of the “Enhanced Solar PV Power Generation and Distribution System” (Investment Type activity #1 on pp 17-18 of the Supplemental Annex file) will allow a much more stable and reliable operation of the Nauru national electric grid. Additionally, the installation of the “Storage of Excess Solar PV Generated Electricity in Desalinated Water” demo (pp 20-21 of the Supplemental Annex file), a significant portion of the curtailed electricity will be recovered. Such demo can be easily scaled-up by NUC, since additional water desalination capacity will have to be added that can utilize the portion of curtailed electricity not recovered through SMARTEN. The viability of both this incremental activities is also shown by the positive IRRs for the investment type activity (20.2%) and the demo 1 (28.3%). The project proponents believe that the best benchmark would be to determine the cost per ton of CO2 removed considering only the GEF grant, which would give us approximately US$ 3.01/tCO2 (or US$ 3.17/tCO2 including the Project Management Cost), since there is no way to control whatever the ADB has budgeted for its solar PV project in the country. This value compares to the average cost per ton of CO2 removed in other UNDP-GEF CCM projects in Pacific, i.e., (GEF US$ 6.00/ton CO2), and specifically to similar full size projects in other SIDSs in the Pacific region that are of the same circumstances as Nauru, namely: remoteness, small population (which does not allow for any significant scale-up), limited indigenous RE resources and limited local technical expertise. Finally, as mentioned in a previous response, the financing scheme has been designed to meet a specific stakeholders’ request, to support the government efforts in achieving 30% energy efficiency improvements, one of the 3 targets set in the Nauru Energy Road Map (NERM). | Supplemental Annex file: Annex B, pp. 17-18, and 20-21 |

Exhibit B.3: Responses to GEFSec Comments (23 December 2019)

| Comment & Response | Reference |
| --- | --- |
| 1. If there are any changes from that presented in the PIF, have justifications been provided? |  |
| Comment: Not at this time. Please justify why the significant changes in baseline scenario listed on page 5 do not significantly affect the design of the project outputs and outcomes listed in Annex E on pages 43-45. Response: As mentioned on Page 5 of the CEO Endorsement Request Document (CERDoc), some of the projects that were originally identified as baseline for the SMARTEN activities have either been already completed or will be completed before the beginning of the implementation phase of the SMARTEN Project. It is important to remark that the relevant outcomes and results of these completed, or about to be completed projects, have been considered in the design of the SMARTEN activities. Among these that were considered in the design of the SMARTEN activities are the EU/MFAT-financed solar PV system that is expected to contribute to the achievement of the 50% Renewable Energy (RE)-based electricity generation target, and the project on upgrading the transmission lines connecting both the ADB-, and the EU/MFAT-funded solar PV systems to the national electric grid. For example, the design of specific investment and technical assistance activities in the project considered the level of RE-based power generation from the completed EU/MFAT-financed solar PV system project and build on it. Moreover, the specific activities on grid stability are also based on the results of the project on the upgrading of the transmission lines of the national electric grid. Some of the previously identified baseline projects have been replaced by new projects that will contribute to the achievement of the objective of the SMARTEN Project. Among these are, the projects on the installation of a solar farm by the ADB; setting up of new water tanks in all 14 districts by the GON; and, supporting a sustainable land transport system in Nauru by the Climate Technology Centre & Network (CTCN). These new baseline projects are also in line with the aim of facilitating the use of feasible RE and Energy Efficiency (EE) technologies for supporting socio-economic development in Nauru and are also in line with the achievement of the country’s energy roadmap (NERM) targets. | CERDoc: Part II, Sec. 1a.2, pp. 5-6 |
| 2. Is the project structure/ design appropriate to achieve the expected outcomes and outputs? |  |
| Comment: Not at this time. Components 2 and 4 are in institutional capacity development, please merge them and save some GEF grant budget for capital investments in RE and EE in Component 3. Please indicate in which forms to develop local capacities, such as workshops, seminars, publications, TA training programs, or any others. Please indicate the targeted groups of the trainees, number of people, and number of workshops etc. Please elaborate how to evaluate the effectiveness of the capacity development and institutional supports for new RE and EE initiatives. Response: The project proponents agree with the reviewer about the convenience of merging components to optimize the use of financial resources by grouping activities together, especially for training programs and capacity building. In fact, Component 2 of the proposed SMARTEN project already merges the strengthening of Institutional Framework and the improvement in Financial Resources for RE/EE technologies, two areas that have been often kept in separate components in similar GEF funded projects. On the other hand, while Component 4 is also a TA component, the contents of the training programs cannot be easily and conveniently grouped with those in Component 2. However, it is the opinion of the project proponents that merging the two components together would create a quite complex and unmanageable set of activities without gaining any substantial financial benefit. The large majority of capacity building will be done through the design and implementation in training programs designed ad-hoc. In addition, there will be few awareness raising actions that will require some printed materials and publications. List of Training Programs: - Activity 1.2.3 of ProDoc (Page 22): 10-12 trainees from Department of Commerce, Industry and Environment (DCIE); Ministry of Finance – Planning and Aid Division (MoF-PAD); and Nauru Bureau of Statistics (NBoS). Cost: US$ 6,000 (see Budget Note #4). - Activity 1.3.2 of ProDoc (Page 23): 18-20 trainees from DCIE; MoF-PAD; NBos; Nauru Utilities Corporation (NUC); Republic Of Nauru Phosphate (RONPHOS); and members district communities and private enterprises. Cost: US$ 8,000 (see Budget Note #4). - Activity 2.1.2.2 of ProDoc (Page 25): 18-20 trainees from DCIE; MoF; NBos; Department of Transport (DoT); RONPHOS; Eigigu; and Refugees Processing Centres (RPCs). Cost: US$ 12,000 for two cycles of training (see Budget Note #9). - Activity 2.2.1.4 of ProDoc (Page 27): 20+ trainees from women and youth-led and operated small businesses. Cost: US$ 8,000 (see Budget Note #15). - Activity 2.2.2.3 of ProDoc (Page 28): 12-15 trainees from DCIE; MoF-PAD; NUC; RONPHOS. Cost: US$ 8,000 (see Budget Note #15). - Activity 3.1.7 of ProDoc (Page 30): 10 trainees from NUC. Cost: US$ 15,000 for two cycles of training (see Budget Note #22). - Activity 3.3.2 of ProDoc (Page 31): 15-18 trainees from DCIE; DoT; NUC; Eigigu; and locals service providers. Cost: US$ 12,000 (due to the large amount of information covered, the training program can be divided into two cycles) (see Budget Note #22). - Activity 3.3.3 of ProDoc (Page 31): 12-15 trainees from DCIE; MoF-PAD; DoT; NBoS; NUC; and Eigigu. Cost: US$ 12,000 (see Budget Note #22). - Activity 3.4.2 of ProDoc (Page 32): 6-8 trainees from DCIE; and MoF-PAD. Cost: US$ 12,000 for two cycles of training (see Budget Note #22). - Activity 3.5.1 of ProDoc (Page 33): 4 trainees from DoT; Dept of Water and Sanitation; and local community. Cost: US$ 21,000 for two trainees overseas to learn how to operate and maintain the mini solar powered treated water production and desalination system; and US$ 15,000 for two trainees overseas to learn how to operate and maintain the hybrid bus and the charging station (see Budget Note #22). - Activity 4.1.2 of ProDoc (Page 35): 18-20 trainees from DCIE; MoF-PAD; NUC; and community leaders. Cost: US$ 6,000 (see Budget Note #29). - Activity 4.2.2 of ProDoc (Page 36): 10-12 trainees from DCIE; MoF-PAD; and NUC. Cost: US$ 6,000 (see Budget Note #29). - Activity 4.3.3 of ProDoc (Page 37): 10-12 trainees from DCIE; MoF-PAD; and NUC. Cost: US$ 6,000 (see Budget Note #29). The effectiveness of the training programs will be evaluated by preparing tests that will assess the level of knowledge and competence achieved regarding the subjects covered during the training activities. For example, the training program in Activity 3.5.1, which refers to hands-on experience on operation and maintenance of the demo technologies, the evaluation of the training activities will include practical experience and it will be organized as part of the training activities overseas. | ProDoc: Part IV, pp. 22-37. Part IX; Budget Notes, pp. 68-70 |
| Comment: In output 3.5, please articulate where the demos to take place, which RE and EE technologies to use, how many MW to install, how many MWh electricity to save, whom to involve, which private stakeholders to engage, etc. Response: The detailed descriptions of the investment type activities and demonstrations that include all the data and information requested by the reviewer are already provided as part of the Supplemental Annexes to the SMARTEN Project proposal submission, more specifically as Annex B of the Supplemental Annex file. | Supplemental Annex File: Annex B; p. 17 |
| 3. Is the financing adequate and does the project demonstrate a cost-effective approach to meet the project objective? |  |
| Comment: Not at this time. The financing is adequate, but the project does not demonstrate a cost-effective approach to meeting the project objective. The project aims at mitigating 1.049 million tonnes of CO2, including both direct and consequential emission reductions from RE technologies, while the total budget of the project reaches $26 million. In other words, it needs $3.15 GEF grant and $21.8 co-financing to mitigate one tonne of CO2, which is high in the GEF CCM portfolio. Response: The aim (objective) of the project is enabling the increased applications of feasible RE and EE technologies for supporting socio-economic development in Nauru in accord with the country’s energy roadmap targets. From the successful implementation of the planned project activities, delivery of project outputs and realization of the project outcomes, a total lifetime incremental amount of 1.049 million tonnes of CO2 emissions (direct and consequential) will be realized. The project proponents agree that the project costs might seem high. However, one should take into account that the implementation costs of RE/EE technologies in general, including solar PV systems, in remote locations such as the small island state of Nauru, are always significantly higher than in other larger developing countries. This is due to high transactions costs involved, not only due to the high freight and insurance costs, maintenance costs (in terms of spare parts), but also because these technologies very often require technical expertise that is not available locally, and a crew of specialists has to be flown in for the engineering and installation. In addition, it should be pointed out that the unit abatement cost (UAC), i.e., GEF grant per ton CO2 emission reduction, of approximately US$ 3.15/ton CO2 removed, is significantly lower than the current carbon prices in existing carbon exchanges like the European Emission Allowances (EUA Spot Price = US$ 26.74/ton CO2, Ref: Climate Daily News: 27 January 2020; https://www.factorco2.com). Please note that the 1.049 million CO2 emission reduction is incremental to what the country may reduce if they only implement their baseline (business-as-usual) initiatives to reduce GHG emissions without GEF support. Considering both the GEF grant of US$ 3.30 million and the co-financing of US$ 22.77 million, and the overall GHG emission reduction (baseline and incremental), the resulting UAC is US$ 24.85/ton CO2, which is still lower than the 27 January 2020 EUA Spot Price of US$ 26.74/ton CO2. | Supplemental Annex File: Annex B; p. 17 |
| Comment: Please reduce budget in TA components and increase that in capital investment in EE or waste management and make the project more cost-effective. Please account carbon emission reductions from EE technologies which are generally more cost-effective than RE technologies. Response: The project proponents agree with the suggestion of the reviewer to reduce the TA budget to increase the investment portion, as well as with the point that EE technologies are in general more cost-effective than RE technologies. In fact, based on the financial analysis performed for the two investment type activities and for the three demonstrations, as shown in Annex B of the Supplemental Annex file, the Internal Rate of Return (IRR), and consequently the Net Present Value (NPV), is highest for the RE/EE Financing Scheme at about 50%. For this reason, US$ 100,000 from the TA budget has been moved to the RE/EE Financial Scheme, which is now budgeted at US$ 350,000 (inclusive of expenses for the detailed design, promotion, and operationalization of the scheme). By increasing the funds for the RE/EE Financing Scheme, the number of beneficiaries has increased from 950 up to 1,390. | Supplemental Annex File: Annex B; p. 17 ProDoc: Part IX - Budget Notes; pp. 65-71 |
| 6. Are relevant tracking tools completed? |  |
| Comment: Yes. But the carbon emission mitigation amount is very small. The unit (million tonnes of CO2) also needs to be entered in the GEF Portal. Response: While the total GHG emission reduction is small in absolute terms, this is very significant in the context of a small island developing state like Nauru, a 21 km2 island nation with a population of less than 13,000. In fact, the total GHG emissions in Nauru was only 57,000 tons of CO2, in 2014, equivalent to 0.0002% of the overall global CO2 emissions. The data on GHG emission reduction as stated in Part I (Sec F) and Annex G (GEF 7 Core Indicator Worksheet) of the CEO ER Document have been entered in the GEF Portal. | ProDoc: Part II, p. 9 |
| 10. Does the project have descriptions of a knowledge management plan? |  |
| Comment: Not completed at this time. In the KM section, please elaborate the number of government trainees (DCIE) and the power utility (NUC and Vital Energy). These number should be shown in Table B as well. Response: The response to “Comment #2” above gives a detailed breakdown of the number of trainees expected for each training programs that will be organized and conducted during the SMARTEN implementation stage. Based on the information provided in that response, the total number of participants in all training programs will be in the range of 163-186. The relevant numbers are also stated in Part I, Sec. B of the CERDoc | Response to Comment #2 of this document |
| Comment: In the KM section, please add more information on: 1. an overview of existing lessons and best practice that inform the project concept; 2. plans to learn from relevant projects, programs, initiatives & evaluations; 3. proposed processes to capture, assess and document info, lessons, best practice & expertise generated during implementation; 4. proposed tools and methods for knowledge exchange, learning & collaboration; 5. proposed knowledge outputs to be produced and shared with stakeholders; and 6. a discussion on how knowledge and learning will contribute to overall project/program impact and sustainability plans for strategic communications Response: Additional information requested by the reviewer have been provided in the Knowledge Management section of the CEO Endorsement Request Document. | CERDoc: Annex F, pp. 43-44 |
| 11. Has the Agency adequately responded to comments at the PIF stage from: |  |
| GEFSEC: Not completed at this time. At the PIF stage, the PM commented the following: |  |
| Comment: "In the CEO ER stage, please clearly indicate the capacities, expenditures, locations, and beneficiaries of the demonstration investments. Please add one more component: M&E. More co-financing from the private sector is needed to enlarge the ratio of co-financing." Response: Information about the capacities, budgets and locations of the demonstrations and investment type activities are provided in Annex B of the Supplemental Annex file. The beneficiaries have been specified in the Core Indicator 11, where a footnote also specifies a breakdown for each demo. M&E is part and parcel of each of the project component. The costs for independent M&E (mid-term review and terminal evaluation) are covered in the Project Management Costs. The total co-financing for this project is actually much higher than that indicated at the PIF stage. It went up from US$ 13,354,400 (per the GEF-approved PIF) to US$ 22,765,000, an increase of over 70%. The Co-financing ratio is approximately 7:1, which is considerably high for a small island developing state like Nauru and is in line with the ambition for the co-financing ratio of at least 7:1 for the overall GEF portfolio. Financial resources from the private sector will be leveraged through the RE/EE Financing Scheme. As explained in Annex B of the Supplemental Annex File, the financing scheme will only cover at most 30% of the investment (or 25% in case the participant does not trade in an old appliance). The participants to the scheme, primarily small businesses and households, will be responsible for covering the balance of 70% (or 75% if there is no trade-in). Assuming that all participants will trade in an old appliance, which represents the case for the lowest financial disbursement from the participants, the total private sector investment is calculated at US$ 674,000 (detailed calculations are included in the aforementioned Annex B of the Supplemental Annex file). | Supplemental Annex File: Annex B; p. 17 ProDoc: M&E Plan and Budget, p. 54 CERDoc, p. 10 CERDOC: Part I, Secs. B & C |
| Comment: The capacities, expenditures, locations, and beneficiaries of the demonstration investments have not been elaborated in the CEO RE document, they are shown in Table B. Response: The information requested that are provided in Annex B of the Supplemental Annex file were tabulated and the resulting table is now included in the CEO ER Document as another annex (Annex E). Moreover, it is the understanding that the last phrase “they are shown in Table B.” meant that these data be presented in Part I, Sec B of the CERDoc. Hence, these data have now been included in the table in Sec B. | CERDoc: Annex E; p. 42. Supplemental Annex File: Annex B; p. 17 |
| GEF Council: Not completed at this time. |  |
| Comment: In its Comment 1, France requires tangible investment in demo. Please provide details in capital investment for the demo sub-project. Also please see the PM's comments above on Component 3. Response: As mentioned in the “After PPG Stage” response to the first comment of the French GEF Council Member, the investment portion of the SMARTEN project is the large majority of the requested GEF grant; specifically: - Under Component 2.2, US$ 350,000 will be used to finance the RE/EE financing scheme. This budget has been increased from the original US$ 250,000 budget, following the suggestion of the reviewer on increasing the investment portion of the project. - Under Component 3, US$ 1,915,000 will be used for the demos and the investment type activities. (see Budget Note #20 on the ProDoc, Page 69 and Annex B of the Supplemental Annex document). In addition there is a US$ 36,000 budget for the training on these demos. - Under Component 3 there is also a US$ 15,000 budget for the equipment to conduct energy audits. - Under Components 3 and 4 there is a combined US$ 37,000 budget for the acquisition of several software packages. - Finally, under Component 3 there is a budget of approximately US$ 200,000 for the detailed designs of all demos and the investment type activity, which is an integral investment for the demonstrations. In total, out of the US$ 3.15 million GEF grant (excluding the Project Management Costs), the investment portion in actual hardware and software products amounts to US$ 2.31 million, or 73% of the requested grant. This portion increases to US$ 2.55 million, or 81% of the investment, if designs of the demos and investment type activities and the training on the O&M of the demos are included. | Supplemental Annex File: Annex B; p. 17 ProDoc: Part IX, Budget Notes, pp. 67-70 CERDoc: Annex B, Exhibit B.1 |
| Comment: In the first comment, Germany requires the project to effectively mobilize private investment. The Agency' did not address the comment satisfactorily. The project can indeed engage the private companies or individual households in solar PV, small wind power installations, and EE technology investment. While finalizing the INV component for this project, please take into account engaging the private sector in capital investment. Response: The design of the RE/EE financing scheme is meant to attract funds from the private sector for investment in small scale solar PV systems and the purchase of high energy efficiency appliances and equipment. Regrettably, small wind power installations are not an option for Nauru, given its position very close to the equator, which is not optimal for wind as it has been demonstrated by a year-long SPREP data collection in 2010 – for a more detailed discussion of potential RE sources please refer to Annex A, pages 15-16 of the Supplemental Annex file). Following the suggestion of the reviewer, the total budget allocated for the RE/EE financing scheme has been increased to US$ 350,000 up from the previous US$ 250,000 budget (40% increase). In addition, as explained in the response to the first comment of the German GEF Council Member, Nauru does not currently have a banking/finance system in place, following the phosphate industry collapse. The banking/finance system will be re-established in the next 2-3 years by the GoN with the support of ADB. When this task will be accomplished, similar financing schemes can be replicated through a normal loan product portfolio. Lastly, the SMARTEN activities devoted to the establishment of a supporting financial framework, together with fiscal/financial incentives, will spur investments from the local private sector, which has very limited financial resources, and it will also attract investments from expats and foreign investors. As reported by the Nauru Utilities Corporation (NUC) which also keeps track of RE installations (specifically rooftop PV systems) in the private sector, to date there are a total of 9 solar PV installations for a combined 385 kWp. These are: - 3 relatively large rooftop installations on a department store, an apartment complex and a warehouse all owned by a private investor, Capelle and Partner, (combined 357 kWp); - 5 rooftop installations on private households (combined 23 kWp); and, - 1 rooftop installation on a hotel (5kWp). | Supplemental Annex File: Annex B; p. 17. Annex A; pp. 15-16 CERDoc: Annex B, Exhibit B.2 |
| 12. Is CEO endorsement recommended? |  |
| Comment: Not at this time. Please address the comments above. Response: The project proponents have adequately addressed the comments. They look forward to the CEO endorsement of this project. |  |
| Comment: Please consider tangible energy efficiency and/or waste management investment in the project which will make the project innovative and cost-effective. Response: Energy efficiency is among the focus of the investment type activities of the SMARTEN Project. The promotion of, and the facilitation of the widespread practice of, EE in the country are among the interventions of the project. Part of the intervention is the design and implementation of a RE/EE Financing Scheme that will financially support the purchase and utilization of energy efficient appliances/equipment by households and small businesses. Per Annex B of the Supplemental Annex file, such tangible EE intervention is a cost-effective investment for the project, with an Internal Rate of Return (IRR) of over 50%. Note that following the reviewer comments on increasing the investment portion of the GEF grant, the budget allocated to this financing scheme has been increased by US$ 100,000 to a total of US$ 350,000. Activities to improve demand side energy efficiency comprise mostly of changes to behavior and appliance/equipment. As such improving energy efficiency is seen as the most environmentally friendly activity as it largely does not require new infrastructure. However, where appliance/equipment replacement is envisioned in order to move towards more efficient technologies/models, obsolete equipment and other associated waste must be properly managed and disposed of in an environmentally friendly manner. In this regard, the activities on the design and implementation of the RE/EE Financing scheme also include those to address the disposal and management of the replaced old appliances and potentially hazardous waste materials from such decommissioned or disposed items. | Supplemental Annex File: Annex B; pp. 19-20. |
| Comment: Please also notice the following policy statement: As the agency knows, the implementation and execution roles on GEF projects are meant to be separate per policy and guideline. The GEFSEC will analyze any requests for dual role playing by an agency at the time of CEO endorsement and only approve those cases that it deems warranted on an “exceptional” basis. We strongly encourage the agency to look at third party options as a preferred way forward. We also strongly encourage the agency to discuss any and all options for execution that do not include the government with the GEFSEC early in the PPG phase. The technical clearance of this PIF in no way endorses any alternative execution arrangement. Response: The project proponents understand that UNDP, as the GEF Agency for this proposed project, will not execute any of the SMARTEN project activities. All project activities will be nationally implemented by the project’s implementing partner, which is the Department of Commerce, Industry and Environment (DCIE) on behalf of the Government of Nauru. The detailed description of the project implementation arrangement is described in Part VII: Governance and Management Arrangements on page 56 of the SMARTEN ProDoc. | ProDoc: Sec. VII; p. 56 |

Exhibit B.4: Responses to GEF Council Member (France) Comments on PIF

| Comment | Response |
| --- | --- |
| Here is a project which is almost composed of Technical Assistance only. There is a component with equipment supply but not a lot of details are provided (my understanding is that it includes feasibility, design, assessment even if a pilot is mentioned). | While in terms of the number of components (3 out of 4) the project is comprised of technical assistance activities, bulk of the GEF funding (80%) is on investment type activities. These activities include the design, engineering, installation and operation of demonstration RE technologies applications in the country’s energy generation and end-use sectors. Before PPG Stage: As stated in the PIF, the actual line-up of RE technology applications for the demonstrations will be established during project design and preparation (PPG) stage. Nonetheless, based on initial assessments, the demos may include applications of RE technologies for RE-based energy systems such as solar PV power generation system with battery energy storage system; solar PV-based distributed generation facilities (e.g., district level decentralized RE-based power generation financed and commercially operated by a private sector entity); and non-power applications such as community-owned and operated decentralized solar PV water desalination systems, solar PV water pumping and distribution systems; applications of solar PV powered appliances; and, waste-to-energy schemes. For EE demos, the initially identified technology applications include EE lighting and air conditioning systems in government, commercial and residential buildings, EE community infrastructures, EE street lighting, etc. The actual demo sites and RE/EE technologies that will be featured will be determined and confirmed during the PPG stage. After PPG Stage: Component 3, which includes the investment type activities, accounts for USD 2.5 M out of the USD 3.3 M grant requested from GEF. As rightfully pointed out by the reviewer, this component also includes feasibility studies as well as design, engineering and implementation plans for the installation of the selected RE/EE demos, which are crucial steps to guarantee the successful implementation of the demos. The total investment for the actual equipment is USD 1.915 million. In addition to this significant budget, under Component 2 there is a budget of USD 350,000 for a financing scheme to promote RE and EE technologies, which will be spent on EE appliances and solar home systems for small domestic and commercial applications. This budget is a 40% increase US$ from the original US$ 250,000 budget, following the suggestion of the reviewer on increasing the investment portion of the project. Other investment type costs items include USD 37,000 for software and IT equipment to be used in Components 3 and 4 activities; USD 15,000 for energy audit equipment; and approximately US$ 200,000 for the detailed designs of all demos and the investment type activities. In total, out of the US$ 3.15 million GEF grant (excluding the Project Management Costs), the investment portion in actual hardware and software products amounts to US$ 2.31 million, or 73% of the requested grant. This portion increases to US$ 2.55 million, or 81% of the investment, if designs of the demos and investment type activities and the training on the O&M of the demos are included. For a detailed description of all the expenses, please refer to the Budget Notes in Chapter IX of the ProDoc. |
| But we recommend that, in the project, the electricity grid management issue should be further developed (including the management of an energy mix which would include an important part of intermittent renewable energy production), under a “Smart Grid” perspective, together with the Demand-Side Management issue. The latter is important in view of non-energy efficient equipment and behavior inherited from the period 1970-1990. | Before PPG Stage: As stated in the PIF, the project will involve interventions that will enable the establishment of grid-connected and/or decentralized RE-based energy systems in the country, and for improving the energy efficiency in the electricity end use sectors as ways of achieving RE and EE targets that were set in the Nauru Energy Road Map (NERM). The most recent activities of the Nauru Utilities Corporation (NUC) involved the installation of solar PV power systems including storage to maintain grid stability and decrease the generation requirement during the day and evening peaks. Based on findings during the PIF development stage, the potential improvements to the NUC grid will be on enhancing system grid stability; improvement in the SCADA system; design and installation of additional inverters, batteries and smart systems for network power flow analysis, load monitoring, load growth forecasting, and optimum dispatch. The demo district solar PV power system will also be designed based on “smart grid” principles. Feasible and applicable DSM activities will also be included in the project, building on the GON’s plans for improving energy efficiency in the country, including the introduction of appliance energy labelling and MEPS. The proposed project will, among others, assist the government in facilitating the nationwide EE improvement program, as well as in designing and implementing government-funded financing schemes for low income households in the purchase of EE appliances and solar home systems. After PPG Stage: The GoN has a set target, in its Nauru Energy Road Map, of achieving 50% of electricity generation from renewable sources. The only available and viable renewable energy source in Nauru is solar energy, and the intermittent nature of this energy source makes the electric grid extremely vulnerable to instability. The upcoming ADB 6.0 MWac solar PV system, a baseline project for the SMARTEN activities, will bring Nauru close to the 50% target, and will be designed with a battery energy storage system that will provide only half an hour buffer in case of sudden decline of solar energy enough to turn on the diesel generators. A crucial contribution of SMARTEN will be the design and implementation of several grid stability measures, for which the expertise of a grid specialist has been retained during the PPG stage. These activities include a thorough dynamic grid stability study, the upgrade of the SCADA system, the establishment of procedures for optimal load dispatch under normal operations as well as procedures in case of grid fault, etc. The proposed measures will actually allow a stable operation of the grid even in the event that the 50% electricity from RE target will be surpassed, which has been indicated by the GoN as the next step (a detailed description of all the equipment and measures that will be procured and implemented under SMARTEN are in Chapter IV of the ProDoc, Outputs 3.1 and 3.5). Once completed the 6.0 MWac project, there will be over capacity during sun-peak hours, which ADB will simply solve by curtailing the excess capacity. One of the demos designed under SMARTEN will have a double purpose: (1) recover and store in desalinated water a portion of the excess capacity; and (2) provide DSM by shifting the load towards daytime when a surplus of power generation capacity is available. In fact, differently from many other countries Nauru has the need to shift demand from night time to day time (time-of-use incentives will also be established to favor this load shifting towards daytime); since for security reasons NUC has water desalination generation overcapacity, which will increase even further in the near future, it can apply DSM by generating desalinated water when excess electricity is available. Lastly, there are also activities designed to improve EE towards the target of 30% energy use reduction in the residential, commercial, industrial and government sectors, which will help Nauru to significantly save energy and financial resources, with significant environmental benefits. |
| Finally, more information should be provided in the final project document on Investment activities which will be financed by NUC and on the way they will be articulated with the GEF supported activities. | Before PPG Stage: This will be among the tasks that will be carried out during the PPG stage. By understanding very well the details of the country’s investment activities in the energy sector (to be carried out by the NUC) it is possible to determine what will be the incremental features that can be incorporated on these to augment/supplement or enhance the realization and the magnitude of energy savings and global environmental benefits that these will bring about. After PPG Stage: Since the time when the PIF was prepared the investment plans of NUC have substantially changes thanks to the USD 22 M grant from ADB to install a 6.0 MWac (6.9 MWdc) solar PV field that will bring Nauru very close to the 50% electricity from RE target. ADB has already completed a feasibility study and prepared a detailed solar expansion plan (both documents have been prepared by GHD, one of the world’s leading engineering consulting firms). The GoN funded site preparation activities are ongoing and the new PV installation is scheduled to be commissioned in 2022. |

Exhibit B.5: Responses to GEF Council Member (Germany) Comments on PIF

| Comment | Response |
| --- | --- |
| Although the project proposal elaborates on financial barriers, the actions proposed do not provide a comprehensive approach to remove identified barriers. Especially, the proposal does not conceive the effective mobilisation of private climate finance sufficiently. Germany suggests clearly identifying potential national and international partners from the private and financial sector for project implementation. After all, a stronger inclusion of non-governmental actors could add valuable input to overcome the identified challenges. | Before PPG Stage: The proposed project envisions that adequate amounts of financial resources will become available for RE/EE Technology application projects in the country. Hence, the project will involve interventions that will provide supporting mechanisms, institutional and financial, for RE and EE initiatives. It should be noted that following the collapse of country’s phosphate mining industry, Nauru was left with a substantial amount of debt held by foreign creditors, which led to the bankruptcy of the entire financial sector. The result of this that currently there is no banking or financial system, nor a banking regulatory and supervisory framework in place in the country. However, efforts are underway with support from ADB to establish a framework, the results of which are expected in the medium term. Nauru currently has only one bank - Bendigo Bank, an Australian bank that has operated in the country since 2015 under Australian banking regulations. However, Bendigo Bank currently only offers banking and financial transactions without offering any loan or credit products. Nonetheless, during the PPG stage, the Department of Commerce, Industry and Environment (DCIE) and the project development team (PDT) will work with other development partners in Nauru in coming up with complementary efforts to support the GON in efforts to realize the achievement of the country’s energy roadmap targets. The objective is to align at an early stage, energy sector multi-lateral/bilateral donor and development bank interventions with national priorities and ensure synergy of actions and eliminate possible duplication between development agencies. After PPG Stage: In response to the suggestion from Germany, the project has been designed to include activities that will address the financial barriers that hinder the people of Nauru in the application of RE and EE technologies. Among these are the: - Establishment of a conducive legal regime with independent regulation as well as financing and risk management frameworks for the increased role for the private sector in the implementation of sustainable energy projects in Nauru. - Development of a business and institutional framework for private sector investment and financing for RE and EE projects in the country - Development of sustainable financial support schemes including implementation modalities and processes for RE & EE technologies application projects and criteria to support women and youth led businesses - Establishment of a financing scheme for households and small business owners to purchase high energy efficiency appliances and small renewable energy powered electricity generation system (primarily solar PV panels). Due to the small size of Nauru it is not easy to attract foreign investments; however there have been investments made by expats, with one private investor very active in the installation of relatively large rooftop solar PV installations on his privately-owned hotel, warehouse and supermarket. The establishment of a supportive financial framework, together with fiscal/financial incentives and the establishment of a financing scheme will spur private investments from the private sector and potentially attract more foreign funds, especially from expats. Furthermore, it is envisioned that with the assistance of the ADB to the GoN regarding the re-establishment of the banking and finance system (expected in the next 2-3 years), the proposed project interventions will enable Bendigo and other banks to also replicate similar financing schemes through the normal loan product portfolio. |
| The project demonstrates potential for scale-up and market transformation; yet this requires engagement of a broader set of actors. Hence, to speed up the transition process, a stronger focus on co-operation with international stakeholders should be given consideration in the project implementation process. The respective roles of potential partners and institutions should be outlined. For example, the NDC Pacific Regional Hub provides an excellent opportunity to exchange with other Pacific countries on issues related to technology application and capacity building. | The project proponent (DCIE) and the PDT are aware of the limited capacity in the country to implement the various activities that are stated in the Nauru Energy Road Map (NERM). In that regard, apart from the capacity development activities that will be carried out under the proposed project, the DCIE will work together with other partners in the Pacific region in the implementation of the project activities, particularly those that are also working in Nauru. Inasmuch as the NERM targets are also the country’s NDC targets, it would also be helpful to consider working with the planned NDC Pacific Regional Hub for support in the implementation of the country’s NERM targets. After PPG Stage: The project activities have been designed to collectively contribute to the facilitation of the increased applications of feasible renewable energy and energy efficiency technologies for supporting socio-economic development in Nauru. These are all in accord with the country’s NERM and NDC targets. Hence, the implementation of these project activities will make use of the appropriate resource inputs that can be sourced both in the country and in the region. Obviously, regional organizations in the Pacific that have been working on energy projects in the country will be considered. Among these includes the SPC, SPREP, and PCREEE, as well as the ADB, GIZ, and GGGI. Since both the UNDP and GIZ were involved in the development and implementation of the NERM activities, regarding the implementation of the SMARTEN’s NERM/NDC-related activities, the DCIE will also consult and coordinate with regional entities like the Pacific NDC Hub for possible technical assistance. It is expected that this entity, together with the assistance provided by the UNDP under its Climate Promise, will also be able to provide technical assistance in the enhancement and implementation of the country’s NERM/NDC activities. Finally, for the design, organization and conduction of training programs and for capacity building, an assessment of similar activities already successfully implemented in other PICs will be performed as a preliminary step. |

Exhibit B.6: Responses to GEF Council Member (United States of America) Comments on PIF

| Comment | Response |
| --- | --- |
| The U.S. encourages the project team to consult and involve the Pacific Center for Renewable Energy and Energy Efficiency (PCREEE) and the Pacific Power Association (PPA) in planning and implementation of this project. The involvement of both groups is likely to expand capacity and contribute to effective replication and project scale-up. | UNDP and the SMARTEN project development team (PDT) are aware of the limited capacity of the DCIE and NUC to implement the various activities in the Nauru Energy Road Map (NERM). In that regard, apart from the capacity development activities that will be carried out under the proposed project, the DCIE will work together with other partners in the Pacific region in the implementation of the project activities such as those that are also working on energy in Nauru like the PCREEE. Since the project involves power generation activities by a Pacific Power Association (PPA) member – NUC, it would also be helpful to coordinate and partner with the PPA particularly in the sharing/dissemination of the outputs of the project to other PPA member utilities, not only for information sharing purposes but also promoting similar type of RE-based power generation and distribution system, and electricity storage strategy in other Pacific Island Countries, and possibly other Small Island Developing States. |

Exhibit B.7: Responses to STAP Review of PIF

Note: Based on the PIF screening, STAP’s advisory response to the GEF Secretariat and GEF Agency is Concur.

| Comment | Response |
| --- | --- |
| 1. The aim is to support renewable energy (RE) projects and improved energy efficiency (EE) through policies to help meet the energy supply and demand targets as outlined in the Nauru Energy Road Map (NERM) as set by the government of this very small nation. | Agree in a way. The project aim is to enable the increased applications of feasible RE and EE technologies for supporting socio-economic development in Nauru in accord with the country’s energy roadmap targets. |
| 2. Demonstrations of RE electricity generation and EE projects are planned that will use around three-quarters of the total funding sought, most of which will be as co-financing through the state-owned Nauru Utilities Corporation with power generation development supported by the governments of Australia, New Zealand and UAE. | The designed project includes a demonstration on RE-electricity power generation (solar power PV systems) integrated into an existing power grid, supplemented with system features that will enable grid stability and electricity storage systems. The underlying baseline activities for this demo are the ADB/AusAid and NZMFAT solar PV power generation projects of the country’s state-owned utility, NUC. |
| 3. Total investment sought to improve grid reliability, increase capacity and to reduce dependence on imported diesel-fuelled generation plant equates to around USD 1660 per capita. The recent installation of two new 2.8 MW diesel gensets funded by AusAid and ADB will produce greenhouse gases for many years to come. The reason for this investment decision, given the urgent need to reduce emissions globally, is not known. It was probably based on economic cost analysis alone with no value included for the CO2 released. Consequently, the NUC target to reach 50% generation from renewables by 2020 is now highly unlikely to be met. | The recently installed ADB/AusAid funded 2x2.8 MW diesel gensets were for the improvement of the level of energy service in Nauru. This provided reliable base-load power for the NUC, allowing it to retire the older gensets. It was to address the reliability and efficiency shortcomings in Nauru’s current diesel generation equipment to improve service reliability and mitigate the risk of catastrophic failure of the NUC’s power generation. Such installation has been assessed as effective due to the role the gensets play in securing baseload electricity generation, paving the way for introducing more solar capacity into Nauru’s energy mix. The ADB 6.0 MW solar PV power generation system (including 2.5 MWh battery storage) is designed to achieve the NERM’s 50% electricity from RE sources target by 2025. Based on the electricity production estimates, the maximum power generation capability of this system will allow the achievement of about 40% of electricity from RE. Spurred by the success of, and facilitative and enabling environment that will be created by, the SMARTEN Project, it is estimated that by 2025, an additional 1.5 MW solar PV system would have been installed thereby achieving the 50% target. NUC has already indicated that additional solar PV systems projects are being studied and planned for implementation by 2025. |
| 4. Renewable electricity, mostly solar PV, currently has a low share of total generation (~3-4%) and is expected to rise only slowly without further external investment. Strengthening of policies and measures to encourage RE development, together with creating greater awareness of the potential by government and the private sector, will be needed if the 50% target is eventually to be met within a decade or more. | Agree. The SMARTEN Project is comprised, among others, of barrier removal activities that will address the policy/regulatory and institutional barriers to the widespread application of RE and EE technologies. Such activities are designed to deliver outputs that will collectively help realize: (a) Enforcement of approved policies and rules and regulations on the widespread application of cost-effective RE and EE technologies for energy production and use; and, (b) Cohesive institutional mechanisms for facilitating widespread application of RE & EE technologies in the country. |
| 5. Several RE and EE projects exist, and others are planned within the NERM. However, this baseline is inadequate to meet the government targets and additional projects will need to be supported, (through this GEF project for example), in order to remove barriers to uptake such as by building local expertise and capacity. | Agree. Accordingly, the SMARTEN Project also includes a component on the Improvement of Energy Sector Capacity. The activities include, among others the development of the local capacity to support RE & EE projects. Collectively, the outputs that will be delivered under such project component will lead to improved awareness and capacity of the GoN, private sector and communities about cost-effective application of RE and EE technologies and practices. |
| 6. Innovative ways to "smarten" the grid through decentralised generation and incentivising private sector involvement are commendable. The many opportunities for EE potential have been identified, and a PV powered desalination plant is planned to be built as a demonstration. | Among the proposed demonstrations of the project is a “Mini solar powered treated water production and distribution system”. This will showcase the viable commercial operation of a community-based solar water pump system with purification and reticulation system. Indirectly this demo will benefit the entire population, by paving the road to scale-up and replication projects, for which there is large potential, since Nauru does not have a water reticulation system in place. |
| 7. The assessment of 5.1 MW new solar PV capacity to be installed if around 25% renewable generation is to be achieved in the alternative scenario by end of project (footnote 20) assumes a capacity factor of around 20% which is acceptable for this location. | Agree. The average net capacity factor based on the sun irradiance value is typically 0.20-0.23. The ADB 6 MW solar PV system is designed on the following assumption: 1st year full operation 2022; 3% efficiency decline in year 2, and 0.65% efficiency decline from year 3 to year 25. |
| 8. The greenhouse gas mitigation claims for this GEF project of around 1 Mt CO2-eq exclude any emissions reductions resulting from EE projects. They equate to around USD 16/t avoided (including both GEF funding and co-financing) which is acceptable given that investment in EE projects should also give an improvement. | Agree. The estimated total amount of GHG emission reduction is comprised of direct and consequential GHG emission reductions from the RE interventions that will be implemented. This estimate does not include the GHG emission reductions from activities that will focus on improving energy efficiency in the end-use sectors. |
| Further General Comment: The project is not particularly innovative but builds on earlier investments in RE and EE projects. The need to consider grid stability at the proposed higher levels of variable generation in either national or decentralised systems will need careful analysis on how best to reduce peak demand loads and the need for possible investment in energy storage. It is assumed the potential for wind power or bioenergy generation (e.g. using biogas) have been evaluated based on resources available and that solar has the lowest cost-effective potential. If not, then a more balanced generation system using solar, wind and bioenergy resources should be assessed. | The project will address the potential grid instability problems that may happen when there is an increased integration of solar energy-produced electricity from the new solar PV power generation systems that will be installed (e.g., from the ADB-funded 6 MW solar PV power generation project). To address this, the following grid stabilization interventions will be carried out under the project: - Upgrading of the electrical HV component and communication/electrical infrastructure in the NUC grid system. - Implementation of the recommendations from the grid system protection study focusing on the entire grid system with the new RE-based power generation systems and the Battery Energy Storage Systems. - Demonstration of the monitoring, operation of the SCADA system with entire grid system, diesel generators, BESS system and RE-based power generation units. - Implementation of an integrated RE generation forecasting tool to the SCADA system to perform day-ahead planning of the load dispatch planning and support the reliability and operational procedures; and, - Demonstration of the monitoring, operation and performance of the RE-generation forecasting tool to support with day-ahead planning. The ADB solar PV system has been sized and designed for minimum average electricity generation cost (diesel and solar mix). The lowest electricity price is achieved when 6.0 MW solar-based power generation capacity is added to the grid with no battery storage. Nonetheless, a 2.5 MWh battery system is included in the ADB solar PV system to have some grid stability capabilities. Based on the estimated system peak load of about 5.7 MW, the battery storage is sized to provide approximately 30 minutes buffer to place the diesel gensets online, in case the PV power generation suddenly declines due to climate conditions. During sunny days, the solar PV generation capacity in Nauru will be about 2.3 MW higher than the average peak demand, which means that in just over an hour the battery bank will be fully charged. Because of the limited storage capacity, and there are no significant load-shifting measures being implemented due to the relatively flat electricity demand profile, with a slight peak demand occurring during daytime, the mismatch between solar PV electricity generation and electricity demand will cause excess solar energy-based electricity production. Since there is not enough electricity storage capacity, the solution proposed by ADB is to curtail part of the electricity generation capacity by disconnecting a portion of the PV system when there is overcapacity. It is estimated that, even with the assumption of daily charging of the battery bank, about 1,150 MWh/year of electricity production will be curtailed. One of several innovations that will be featured under the SMARTEN Project is the storage of the excess solar PV electricity production through the production of desalinated water. |

Exhibit B.8: Responses to GEFSec Comments (9 February 2018)

| Comment & Response | Reference |
| --- | --- |
| 2. Is the project consistent with the recipient country’s national strategies and plans or reports and assessments under relevant conventions? |  |
| Comment: Not completed at this time. Pages 6-7 are not clear on how the proposed GEF project will contribute to the NDCs and the NERM of the country. In its NDCs to the UNFCCC, the government of Nauru stated the following: "The key mitigation intervention is to replace a substantial part of the existing diesel generation with a large-scale grid connected solar photovoltaic (PV) system which would assist in reducing the emissions from fossil fuels. Concurrent to the above there needs to be put in place extensive demand side energy management improvements which will complement the PV installation. The demand management improvements are expected to reduce emissions by bringing down diesel consumption further." In addition, the NERM of Nauru has its specific targets: "by 2020, 50% of grid electricity (will be) supplied from RE sources" Please present two scenarios in two Tables: (1) without the GEF project, projection of investment and operations of diesel power generation facilities, RE power generation facilities, demand side management investment and penetration/ deployment of EE technologies; and (2) with the GEF project, projection of investment and operations of diesel power generation facilities, RE power generation facilities, and demand side management facilities and EE technology penetration/deployment. Then, estimate how much (in percentage) the GEF project will contribute to the target of replacing diesel power generation with solar PV and EE technologies. Response: Case A: No SMARTEN Project The following is the investment plan of the Nauru Utilities Corporation (NUC) from 2015 to 2020 in solar PV installations to meet the 50% target: Year; % Total Power Generation; Annual Solar PV Power Generation, MWh; Annual Installed Solar PV Power Generation Capacity, MW; Cumulative Installed Solar PV Power Generation Capacity, MW; Required Annual Investment, US$ million. 2015; 1.7; 684.0; 0.5; 0.5; 1.4. 2016; 5.0; 2,735.8; 1.5; 2.0; 4.3. 2017; 15.0; 10,276.9; 5.4; 7.3; 15.8. 2018; 25.0; 19,452.6; 6.6; 13.9; 19.3. 2019; 35.0; 28,188.9; 6.2; 20.1; 18.4. 2020; 50.0; 40,144.9; 8.5; 28.6; 25.1. Source: NUC Strategic Plan 2015-2020 (Investment figures converted to USD from original AUD) However, the NUC has limited funds for the installation of new solar PV power generation systems. The planned allocations till 2020 can support the installation of only about 6 MW by 2020. This involve the installation of solar PV plant including storage to maintain grid stability and decrease the generation requirement during the day and evening peak. The country must tap other potential sources of finance for meeting its 50% RE electricity target. Based on the NERM Review in 2017, the following are the GON’s investment plan for the period 2018-2020 for the power sector and RE-based power generation, and in promoting and implementing DSM and energy efficiency initiatives: Planned NERM Activities; Required Budget, US$ ‘000. Power Sector. Upgrade assets; 5,624. Improve planning and management; 505. Improve supply-side energy efficiency; 646. Move toward full recovery of operation and maintenance costs; 441. Develop and safeguard NUC staff; 114. Total; 7,330. Renewable Energy. Phased implementation of large-scale solar PV (up to 8.5 MWp); 38,095. Investigation and implementation of other renewable energy resources; 904. Build in-country capacity to operate and maintain solar PV systems; 46. Total; 39,045. Demand Side Management & Energy Efficiency. Data collection and analysis for preparation for DSM implementation; 152. Implementation of demand side energy efficiency; 255. Introduction of appliance energy labelling and MEPS; 129. Total; 536. Source: Review of the NERM 2014 – 2020 (Investment figures converted to USD from original AUD) It should be emphasized that the GON still must source additional funding to meet the required budget for their planned NERM activities. For example, the proposed budget for new solar PV power generation system is yet to be fully sourced since the GON is not able to provide this completely. Note also that this amounts only to 45% of the estimated investment cost for installing the required total solar PV capacity to achieve the 50% RE electricity target. With the current trend of uptake of installed solar PV power generation assets, it is very unlikely that the NERM target will be achieved in the next 10 to 12 years. By 2020, the estimated % contribution of RE-generated electricity to the country’s power generation mix would only be about 9.3%. Case B: With SMARTEN Project Considering the current situation in the country wherein there are significant delays in the implementation of the NUC’s strategic plan, and that of the planned NERM activities, the GON endeavors to identify, evaluate and adequately address the reasons for this, apart from the rather obvious limited funds that are available from the government coffers. With the aim of being more sustainable in the production and provision of electricity to its citizens, and gradually reducing reliance on donor funding, the GON endeavors to explore and consider other funding sources for the full implementation of its NERM. While donor funds are expected, the GON intends to tap the private sector (local and foreign) in investing in RE-based power generation projects, from which their collective power generation will count towards the achievement of the 50% RE electricity target. Based on the NUC Monthly Reports 2017 and the NERM Review the following is the forecast adjusted plan for the achievement of the set %RE electricity target: Year; % Total Power Generation; Annual Solar PV Power Generation, MWh; Annual Installed Solar PV Power Generation Capacity, MW; Cumulative Installed Solar PV Power Generation Capacity, MW; Required Annual Investment, US$ million. 2017; 3.3; 1,769.7; 1.0; 1.0; 3.0. 2018; 5; 3,152.6; 0.8; 1.8; 2.4. 2019; 9.5; 6,788.2; 2.1; 3.9; 6.2. 2020; 13; 9,728.5; 1.7; 5.6; 5.0. 2021; 19.5; 15,348.3; 3.2; 8.9; 9.5. 2022; 25.5; 21,436.5; 3.5; 12.4; 10.3. 2023; 33; 29,424.0; 4.6; 17.0; 13.5. 2024; 41; 38,557.3; 5.3; 22.3; 15.3. 2025; 50; 49,364.2; 6.2; 28.5; 18.1. To realize the above investment plan for the achievement of the NERM target, there must be actions to take to facilitate this. With the identification and thorough understanding of the barriers/issues/constraints that are hindering such enabling environment, the GON would be able to implement appropriate actions to remove such hindrances. The NERM Review 2017 presented the status of the NERM activities as of November 2017. While the estimated investment cost is available, the data about the available investment for the 2018-2020 period is not available. However, based on discussions with the Department of Commerce, Industry and Environment (DCIE), which is in-charge of energy matters in the country, and with the NUC, a level best estimate of the available investment for all NERM sectors is shown in the table below, along with the estimated incremental funding from the GEF for enabling the increased applications of feasible RE and EE technologies for supporting socio-economic development in Nauru in accord with the NERM, as proposed in the SMARTEN Project. Sector; Estimated Available Investment, US$ '000; Proposed GEF Funding, US$ '000; Potential GEF-funded Incremental Activities. Power; 2,500; 196; Demos on enhanced solar PV-powered water desalination units in NUC and in pilot districts; Improvements in SCADA system and for enhanced system grid stability;. Renewable Energy; 12,475; 2,500; Design, engineering and financing of feasible RE-based power generation systems; district level decentralized RE-based power generation financed and commercially operated by a private sector entity; Community-owned and operated non-power applications of solar energy (e.g., water supply). Demand Side and Energy Efficiency; 268; 300; GON-funded financing schemes for low income households in the purchase of EE appliances and solar home systems.. Institutional Strengthening and Capacity Building; 248; 150; Piloting in selected districts of specific policies and strategies for the application of RE and EE techniques, measures and practices; Application of integrated energy planning techniques.. Petroleum; 162; 0; Not directly covered in SMARTEN Project. Transport; 125; 0; Not directly covered in SMARTEN Project. Total; 15,778; 3,146. The proposed project is aimed at facilitating the achievement of the NERM target through the removal of barriers. Through this project, an alternative scenario that would enhance the pace of solar PV installations in the country, will be facilitated and enable the country to achieve its %RE electricity target by 2025. The chart below illustrates the comparison of the pathway towards the achievement of the NERM target in the baseline (business-as-usual) and alternative scenarios. By end of the proposed SMARTEN Project (2022), the level of contribution of RE-generated electricity in the country’s power generation mix would be halfway through in achieving the NERM target (25.5%) compared to the 15% RE electricity level under the business-as-usual scenario. Since there are limited number of entities that are currently working on the NERM, it would be fair to conclude that most of this 10.5 percentage points improvement in %RE electricity can be attributed to the GEF project. A more thorough analysis of the baseline and alternative scenario trends and attributions to the proposed GEF project will be carried out during the project design and development stage. | PIF: Part II, Sec. 1.1, 9th & 10th Paras, p. 6 PIF: Part II, Sec 1.2, 2nd & 3rd Paras, p. 9 PIF: Part II, Sec. 1.3, 1st & 2nd Paras, p. 10 PIF: Part II, Sec. 1.3, 8th Para, p. 13 PIF: Part II, Sec. 1.3, 9th Para, p. 14 PIF: Part II, Sec. 1.3, Last Para, p. 15 |
| 3. Does the PIF sufficiently indicate the drivers of global environmental degradation, issues of sustainability, market transformation, scaling, and innovation? |  |
| Comment: Not completed at this time. Please address the comments in Box 2 and revise the PIF accordingly. Then, revise the PIF regarding the following issues: 1.the drivers of global environmental degradation, 2. sustainability, 3. market transformation, 4. scaling, and 5. Innovation. Response: Drivers of global environmental degradation: Although the small country of Nauru contributes very low levels of CO2eq emissions (0.0002 % of global emissions in 2014), it endeavors to play its part in addressing the threat of global warming. This is despite being saddled by serious economic challenges. The local infrastructure, including power generation, drinking water and health services, have been adversely affected in recent years by the decline in income from the once thriving phosphate industry, which is Nauru’s major lifeline revenue source. With fewer prospects in the phosphate industry, and with its limited natural resources, Nauru must find other alternative revenue sources to support its economic development, while meeting also its commitment to mitigating climate change. Nauru is dependent on imports for almost everything that are consumed in the country. Among these imports is fossil fuel, which is required in supporting the country’s economy, as well as the livelihoods, health and well-being of its citizens. Bulk of the country’s GHG emissions are from the consumption of fossil fuel in power generation and transport. Through the optimal use of its indigenous renewable energy resource (mainly solar energy) and implementing energy efficiency measures, the country will be able to reduce fossil fuel consumption in electricity generation. The efficient use of electricity in the end-use sectors will also contribute to the reduction in electricity demand and consequently reduce fossil fuel imports. However, with the dwindling income from its phosphate mining industry, it would be tough for this small developing country to fully and expeditiously meet these actions. Because of this, the country cannot be expected to mitigate out of its own resources and would need international assistance. The increased operations of the Australian-operated Refugee Processing Centers (RPCs), while contributing much needed income to the country, also increased the demand for fossil fuels for the operation of their diesel power generation units and transport vehicles. This translates to increased GHG emissions from these additional energy demands. Innovation: Achieving the %RE electricity target does not mean that this will only be realized through the installation of RE-based power generation facilities in NUC. Decentralized RE-based energy systems (e.g., solar PV power desalination units in districts) will also be contributing to that, and so is the widespread practice of energy efficiency in the end-use sectors. These will bring about reduced electricity demand, which indirectly help make the 50% RE electricity target easier to achieve. The planning, funding and actual deployment of decentralized RE-based energy systems and large-scale EE technology applications in the country can be optimally carried out through energy-integrated development planning, which in the Nauruan context, is a new approach. Presently, the electricity and water supply infrastructure planning in the country are mainly the purview of the NUC. However, if the involvement of the end-users (e.g., financing from the private sector and communities) in the successful implementation of the NERM is encouraged, a clearer and more holistic development planning that takes into consideration the energy and environmental impacts of all development plans and actions, is required. This is among the innovations that the proposed project will be bringing into the country. Part and parcel of this approach is the promotion of community-based and private sector-financed and commercial business operated energy service provision. This novel approach is aimed at achieving the objectives of the NERM. Such approach is innovative in the sense that presently, the policies and regulations that will facilitate community-based, private sector-financed RE-based electricity systems, as well as energy-integrated development planning are non-existent. Again, in the context of Nauru, another innovation is the initiative to improve the availability/access to financial resources (local and foreign) for financing RE and EE projects, through the development of financing schemes and other financial instruments that consider the current limitations, arrangements and programs of the GON for financially supporting socio-economic development. The project will involve interventions that will enable the establishment of grid-connected and/or decentralized RE-based energy systems in the country, and for improving the energy efficiency in the electricity end use sectors as ways of achieving RE and EE targets in the NERM. Sustainability: The proposed project involves, among others, the showcasing of the application of feasible energy generation and energy efficiency technologies, along with enabling activities that will facilitate the smooth and sustained operation of these demonstrations. Each of the interventions that involve the planning, design, engineering, installation, operation and maintenance of RE-based energy generation systems, will be supported by appropriate schemes that will sustain their continuous operation, thereby realizing the expected energy savings and associated GHG emission reductions. For example, business plans for the operation of grid-connected, and decentralized solar PV power generation systems, or community-based solar PV-powered water desalination systems will be prepared and implemented to ensure sustainability. The necessary enabling conditions that will encourage/motivate interested investors to actively and continuously participate in the development of the country’s electricity sector will be developed, implemented and sustained. To facilitate sustainability of these actions, the appropriate supportive policies/regulations and institutional mechanisms will be developed, adopted, and enforced, thereby ensuring the expected follow through from the stakeholders. And this follow through will be in terms of the increased interest in investing in and implementing EE & RE technology applications in the country. To facilitate financial support for future RE & EE efforts, the project team will coordinate with the relevant GON agency(ies) on the optimal compliance with the country’s financial reform program to catalyze new investments in EE & RE technology applications. The appropriate actions to facilitate sustainability of the policies, regulations, and institutional frameworks that will be established and enforced/implemented will be determined during the project preparation stage of this proposed project. Potential for Scaling-up: The installation and operation of new solar PV energy generation systems either for electricity production or for non-power applications (e.g., water desalination, water pumping) are intended to demonstrate their benefits, viability and cost-effectiveness so that these can be replicated by others (e.g., private sector entity, community or household) or scaled-up. The successful demonstration of the application of RE & EE technologies (for power and non-power applications) in this proposed project can be expanded or replicated in the other districts of the country if the enabling conditions (in terms of policies, regulations and incentives) are there and are sustained. For example, a successful demo on solar PV water desalination and water distribution in one district, can potentially be expanded (e.g., addition of another unit) to include also the people in the adjacent district. Furthermore, best practices that will come out from the interventions that will be carried out in the project can also be shared with other PICs and SIDS with similar circumstances as Nauru. Market transformation: The awareness raising activities of the proposed project for influencing and effecting a change in the attitude of the energy end-users in the country towards the application of more energy conserving and environment-friendly techniques and practices are expected to gradually transform the country’s energy market. The demonstrations on the application of energy efficient household appliances (e.g., air conditioners, freezers/refrigerators), and feasible and cost-effective solar PV powered systems (e.g., water desalination units, solar water heaters, solar home systems) will further supplement this transformation effort. The successful implementation of these two approaches and supported by applicable policies and regulations and institutional mechanisms will help transform the appliance market into something that only promote and sell EE appliances/equipment. Furthermore, the enabling environment (e.g., support policies, institutional and financing mechanisms, enhanced technical capacity and data/information) that will be created by the proposed project is expected to bring in the necessary additional investments from other sources of financing from within the country (e.g., government, private sector, communities) or from interested foreign investors thereby continuously effecting the market transformation. The continuous enforcement of suitable policies and regulations, for example on tariffs for RE-generated electricity will also help in the sustained transformation of the country’s energy market. | PIF: Part II, Sec. 1.1, 2nd & 3rd Paras, pp. 4 & 5. PIF : Part II, Sec. 1.6, 1st Para, pp. 16 & 17. PIF: Part II, Sec. 1.6, 2nd Para, p. 17 PIF: Part II, Sec. 1.6, 3rd Para, p. 17 PIF: Part II, Sec. 1.6, 4th Para, p. 18. |
| 4. Is the project designed with sound incremental reasoning? |  |
| Comment: Not completed at this time. Please see the comments in Boxes 2 and 3. Response: Please refer to the above responses to Questions 2 & 3. |  |
| 5. Are the components in Table B sound and sufficiently clear and appropriate to achieve project objectives and the GEBs? |  |
| Comment: Not completed yet. The Agency revised the PIF according to the comments of the GEF SEC, but the more work needs to be done. Please articulate (1) what kind of RE technologies, solar PV, or wind or biomass power will be invested in the sub-component of INV; (2) the targeted amounts of renewable power installation in MW for the demonstration; (3) possible locations and beneficiaries of the demonstration investments. Response: - As presented in the PIF, for purposes of the demonstration of the RE technology applications, based on initial assessments, the demos may include applications of RE technologies for RE-based energy systems such as solar PV power generation system with battery energy storage system; solar PV-based distributed generation facilities (e.g., district level decentralized RE-based power generation financed and commercially operated by a private sector entity); and non-power applications such as community-owned and operated decentralized solar PV water desalination systems, solar PV water pumping and distribution systems; applications of solar PV powered appliances; and, waste-to-energy schemes. The actual line-up of RE technology applications for the demonstrations will be established during project design and preparation (PPG) stage. After PPG Stage: While the ADB solar PV system will not allow Nauru to fully achieve its 50% electricity from RE target, considering that the only viable renewable energy source in Nauru is solar energy, the idea of installing another solar PV system was discarded because if did not have any innovative component and would have not demonstrated anything new. Similarly, although needed, providing additional battery storage would have not had any innovative aspect and it would have used a very expensive technology that should be only used for small application or when alternatives are not available. Therefore, the following technologies, some new to all Pacific islands and others new to Nauru have been chosen: - A water desalination system to store the excess power capacity of the ADB solar PV system. This demo not only shows a novel application for water desalination, but also serves a double purpose: (1) recover a portion of the otherwise curtailed excess power generation capacity; and (2) augment the water desalination capacity, a major need for Nauru, which is currently trying to raise the required funds to upgrade its water desalination capacity. - A hybrid diesel-electric bus that also has a twofold purpose: (1) facilitate the establishment of a public transportation system, currently non-existent in Nauru; and (2) showcase a new technology to incentivize (together with the establishment of actual financial incentives) the local population to adopt fuel efficient vehicles such as hybrid and electric vehicles even for private transportation (i.e., cars and motorbikes). - A mini solar powered treated water production and distribution system. Although comprised of all technologies already used in Nauru, this demo will enable the establishment of a water reticulation system, while providing desalinated water to an extremely vulnerable community of 120 people. - At the PIF development stage, the estimated incremental budget is expected to facilitate the installation of an aggregate 5 MW of additional solar PV power generation capacity by end of project (as compared to the baseline scenario). Note that the other demos are targeted for non-power applications of solar energy, and for EE technology applications (e.g., lighting and air conditioning systems in government, commercial and residential buildings, including EE community infrastructures, EE street lighting, etc.). After PPG Stage: During PPG stage it was estimated that the incremental SMARTEN activities will facilitate the aggregate installation of over 6.0 MWac of additional solar PV power generation capacity. - The following is a tentative list of potential demo sites of the project. The actual demo sites and the RE technology that will be featured will be determined and confirmed during the project design and preparation (PPG) stage. Possible locations are the following: (1) NUC designated areas for solar PV power generation; (2) GON-owned hotel – in-house solar PV power generation system; (2) GON-owned and private commercial shopping centers – solar PV air conditioning; (4) NUC – solar PV-powered water desalination; (5) Districts (to be evaluated) – solar powered water desalination and water distribution system; decentralized solar PV power generation and distribution. After PPG Stage: The actual sites for the implementation of the demos have been identified and they are respectively: - The Meneng district is the site for the water desalination system to store the excess power capacity. NUC is already developing in Meneng its water desalination expansion project and using the same site will allow SMARTEN to take advantage of the existent infrastructure (e.g., water pumps, piping system, and water tanks). - The hybrid diesel-electric will be managed by the Department of Transportation and the route will cover the entire circumference of the island, while the battery charging station can be located at the DoT headquarter where trained personnel can provide proper maintenance of the charging station as well as the spare battery (training will be provided as part of the demo). - Lastly, for the mini solar powered treated water production and distribution system, the site is extremely important, especially to use this demo to also support the most vulnerable community. The demo site has been identified and it is a 3-block complex of housing units within the “Location” community. | PIF: Footnotes 4 & 19 Annex A. PIF: Footnote 20 See also Annex A |
| 8. Is the PIF being recommended for clearance and PPG (if additional amount beyond the norm) justified? |  |
| Comment: Not completed at this time. The PM would like to thank the project developer for making efforts to revise the PIF. But more efforts are needed to proceed the project. Please address comments in Boxes 2, 3, 4 and 5. Response: The project proponents have adequately addressed the comments raised. In that regard, they look forward to the CEO approval of the proposed PIF. |  |

Exhibit B.9: Responses to GEFSec Comments (16 January 2018)

| Comment & Response | Reference |
| --- | --- |
| 2. Is the project consistent with the recipient country’s national strategies and plans or reports and assessments under relevant conventions? |  |
| Comment: Not completed at this time. Please articulate the country's long-term energy and climate change mitigation goal and plan and then justify this project is consistent with them. For example, the agency needs to expand para 3 on page 6 about the country's NDCs and justify how this project will help the country to achieve the goals of the NDCs. This should apply for other national government planning and strategies as well. Response: The referred paragraph (PIF, p.6, para 3) states that the country’s efforts toward achieving its set RE and EE targets, as per its NDC and its National Energy Road Map (NERM), are hindered by many barriers. The succeeding paragraphs in p.6 describe these barriers. It should be noted in the country’s NDC that the main mitigation contribution is, among others, to achieve the outcomes and targets under the NERM. The stated project objective is the enabling of the increased applications of feasible renewable energy and energy efficiency technologies for supporting socio-economic development in Nauru in accord with the country’s energy roadmap targets. The intended enabling actions involve the removal of the barriers, i.e., the hindrances to achieving the country’s RE and EE targets as set in the NERM. Without addressing the removal of these barriers, these 2020 RE and EE targets will not be realized. The NERM is currently under implementation. As of end 2017, some activities were already completed, others are ongoing and there are still that are yet to be started. While the design of the NERM may have considered some of the barriers to RE and EE implementation in the country, not all aspects of such barriers and other underlying issues (e.g., limited institutional capacity, limited capacity on energy-integrated development planning and national energy planning, limited knowhow in other non-power RE applications, etc.) were considered. These aspects and other limitations/constraints are addressed in the proposed project. Moreover, in line with the NSDS, which is also the basis of the country’s NDC, the proposed project will also address priority actions that will work towards the realization of the goals in the NSDS, as well as those in sectoral plans and strategies in regards climate change. Among these are enabling and demonstration activities that address water security and energy security, that will contribute to the improvement of the welfare and well-being of the Nauruans. For example, Component 3 of the project include activities to demonstrate the application (design, engineering, installation, and commercial operation) of RE-based water desalination, storage and distribution (through a water reticulation system) and decentralized RE-based power generation in selected districts. These demonstrations will enable not only the Nauru Utility Corporation (NUC) to improve their current power generation and water production and distribution business, but also enable interested private sector entities and district communities to invest in such RE-based energy applications, thereby contributing to the RE and EE targets of the country. | PIF: Part II, Sec 1.1, pp. 6-7 |
| 3. Does the PIF sufficiently indicate the drivers of global environmental degradation, issues of sustainability, market transformation, scaling, and innovation? |  |
| Comment: Not completed at this time. The project is full of TAs, not really investment. The total budget of the project is over $16.6 million. In 2017, the worldwide average capital investment for solar PV was about $1388/kW. This number will continue going down in 2018-2022. In other words, the total investment of the GEF project will be able to help install more than 12 MW solar PV in the country during the project implementation period. This is equivalent to installing more than 1.2 kW of solar PV generation capacity for every person given that the country has about 10,000 people. The PM recommends that the agency use majority of the project funding to install tangible solar PV technologies rather than in TAs. This can be done with the existing on-going baseline projects indicated on page 8. With that, the agency can easily address the following issues: 1.the drivers of global environmental degradation, 2. sustainability, 3. market transformation, 4. scaling, and 5. Innovation. Response: The barrier removal activities would require necessary TA. The scope of the TA would obviously be dependent on the nature and magnitude or extent of the barriers to be removed. The NERM activities are mainly not intended for removing barriers, although some of them when successfully completed can contribute to, or pave the way to, the removal of some specific barriers. Where possible and feasible, the project will build on the ongoing and yet-to-be implemented NERM activities. The enhancements of the NERM activities to enable barrier removal would require the implementation of TAs. Even to convince and enable the private sector to become interested in venturing into investing in RE and EE technologies project would require TA. The baseline activities of the project, i.e., those that the country will be doing even without the GEF assistance is a combination of investment and enabling activities. The investment activities entail the installation of about 6.0 MW solar PV power systems till year 2020. The amount of investment is cumulative until such time that the target 50% RE electricity generation is achieved. Initially that was targeted to be achieved by 2020 but is now most likely to be realized by 2025. The Nauru Utility Corporation’s Strategic Plan (2015-2020) is based on a forecast that there will be additional annual electricity consumption of about 49 GWh, which translates into an increase in load demand from the current 4.5 MW to 12.8 MW by 2020. The large growth is mainly due to the connection of off-grid demand such as that of the phosphate plant (RONPhos) and the refugee processing center (and RPC) to the grid. Hence, a solar PV system capacity/capita metric may not provide a practical gauge of the cost-effectiveness of the proposed project. Based on the NUC Strategic Plan, if 50% of the annual electricity production is to be through solar PVs, this would require a total installed solar PV system capacity of 28.6 MW. Currently, the total installed capacity in the country is only about 750 kW (including grid connected units in government and private buildings). Under the baseline scenario, by 2020 the total installed capacity would only be about 6 MW. The country must tap other potential sources of finance for meeting its 50% RE electricity target, and the TA and investment activities are intended to encourage these other potential sources (communities, private sector, and foreign investors). Moreover, the proposed investment activities in the project are not just meant for utility scale solar PV power generation. There will also be investment activities for the demonstration of RE and EE technology applications that include applications of RE technologies for RE-based energy systems such as solar PV-based distributed generation facilities; and non-power applications such as decentralized solar PV water desalination systems, solar PV water pumping and distribution systems; and waste-to-energy schemes. There will also be investment activities for the demonstration of EE technology applications in lighting and air conditioning systems government, commercial and residential buildings, including community infrastructures such as clinics/hospitals, water supply and distribution systems, trade and industry operations, including refrigeration, water system loss management, energy efficient solid waste management, application of EE street lighting technologies, and demand side management in selected government and commercial buildings. All these will require TA activities in their design, engineering, planning, and capacity building (in the operation, maintenance and monitoring) particularly for the new RE/EE technology applications. The proposed investment activities, which not only focus on commercially and community-operated RE-based energy generation for power and non-power applications; and the technical assistance type activities that would facilitate the: (1) proper design, engineering, installation, operation and maintenance of such systems; and, (2) continuous implementation of the enabling conditions that will influence and support the replication of such system, are part and parcel of the energy-integrated development planning approach that the proposed project will promote. This, in the Nauruan context is innovative in the sense that presently, the policies and regulations that will facilitate community-based, private sector-financed RE-based electricity systems, as well as energy-integrated development planning are non-existent. In addressing its climate change mitigation targets (as per the NDC and NERM), the country has embarked on utilizing RE to reduce GHG emissions from one of the major sources of GHG in the country – the energy sector. This proposed GEF project will enhance the baseline efforts of the country by supporting the establishment of the required enabling environment (e.g., support policies, institutional and financing mechanisms, enhanced technical capacity and data/information) that will bring in the necessary additional investments from other sources of financing from within the country (e.g., government, private sector, communities) or from interested foreign investors. |  |
| 4. Is the project designed with sound incremental reasoning? |  |
| Comment: Not completed at this time. Please see the comments in Box 3. Response: Please refer to the above responses to Question 3. |  |
| 5. Are the components in Table B sound and sufficiently clear and appropriate to achieve project objectives and the GEBs? |  |
| Comment: Not completed at this time. The INV sub-component in Component 3 is a TA. Please focus on capital investment in solar PV technologies, not TAs. Response: As presented in the PIF, Component 3 is comprised on both TA and investment activities. Based on the proposed GEF budget, the investment activities account for 12% of the total component budget. The investment activities are mainly on the (a) design and engineering (b) implementation (installation and operation) of the demonstrations. The potential demonstrations in pilot districts/communities are stated in the PIF. The required TA activities are mainly to enable the planning and preparation, and the cost-effective and proper design and engineering of the RE and EE technology application demonstrations, as well as the annual evaluation of the energy performance and impacts of each demonstration, publication and dissemination of energy performance and impact reports; and, preparation of designs and implementation plans for the scale-up and/or replication of the demonstrations. The PIF shows that 55% of the total component budget is for Investment activities, with about ⅔ of the total component co-financing amount also allocated for investment activities. Considering the implied comment on the component budget allocations for TA and investment activities, the project proponents revisited the ongoing and yet-to-be implemented NERM activities to determine the possible adjustment in the TA and Investment budget spread. The proposed order-of-magnitude adjustment will match the percentage allocation of the total component co-financing. In this case, about 75% of the GEF budget for all components is allocated to Component 3. About 89% of the Component 3 GEF budget is for investment, and 11% is for TA activities. | PIF: Part II, Sec. 1.3, Comp. 3 PIF: Part I, Sec. B |
| 6. Are socio-economic aspects, including relevant gender elements, indigenous people, and CSOs considered? |  |
| Comment: Not completed at this time. Please address how this project is related to indigenous people and CSOs. Response: As mentioned in the PIF, the project development team will be working with relevant NGOs, communities (National Community Councils) and social/civic groups (e.g., churches) in the identification and analysis of barriers to the application of RE/EE technologies in community development, the design of the barrier removal activities of the project, and in the organization, design and preparation of the relevant activities in the project demonstration and replication activities. The citizens of Nauru are the indigenous people of the country and will be the partners and beneficiaries in the implementation of the proposed project. Unlike in other countries where there may be special indigenous people to consider, the Nauruans are indigenous to their country. | PIF: Part II, Sec. 2, p. 17 |
| 8. Is the PIF being recommended for clearance and PPG (if additional amount beyond the norm) justified? |  |
| Comment: Not completed at this time. Please address comments in Boxes: 2, 3, 4, 5, and 6. Response: The project proponents have adequately addressed the comments raised. In that regard, they look forward to the CEO approval of the proposed PIF. |  |

Annex C: Status of Utilization of Project Preparation Grant (PPG) - Provide detailed funding amount of the PPG activities financing status in the table below:

| PPG Grant Approved at PIF: US$ 150,000 |  |  |  |  |
| --- | --- | --- | --- | --- |
| Project Preparation Activities |  | GETF/LDCF/SCCF Amount ($) |  |  |
| GEF Outcome/Atlas Activities | Input Resources | Budgeted Amount (US$) | Amount Spent To date (US$) | Amount Committed (US$) |
| Design and development of the UNDP-GEF project: Supporting Mainstreamed Achievement of Roadmap Targets on Energy in Nauru (SMARTEN) | International Consultants | 112,000 | 95,000 | 17,000 |
|  | Local Consultants | 9,000 | 17,000 | 0 |
|  | Travel | 12,000 | 5,500 | 6,500 |
|  | Contractual Services - Companies | 6,000 | 0 | 0 |
|  | Miscellaneous Expenses | 1,000 | 590 |  |
|  | Trainings | 10,000 | 3,600 | 4,810 |
| Total |  | 150,000 | 121,690 | 28,310 |

If at CEO Endorsement, the PPG activities have not been completed and there is a balance of unspent fund, Agencies can continue to undertake the activities up to one year of CEO Endorsement/approval date. No later than one year from CEO endorsement/approval date. Agencies should report closing of PPG to Trustee in its Quarterly Report.

Annex D: Calendar of Expected Reflows (if non-grant instrument is used)

Provide a calendar of expected reflows to the GEF/LDCF/SCCF Trust Funds or to your Agency (and/or revolving fund that will be set up): N/A

Annex E: Summary of Demonstrations

NOTE: This is in response to GEFSec Comment on capacities, expenditures, locations, and beneficiaries of the demonstration investments.

| Activity | Capacity | Expenditure | Location | Beneficiaries | Reference |
| --- | --- | --- | --- | --- | --- |
| Investment 1: Enhanced Generation & Distribution System | 6 MWac Solar PV field - Equipment to reliably operate the solar field | GEF Expenditure: US$ 320,000 Co-financing: US$ 22,000,000 | NUC headquarter and ADB Solar PV Farm | Nauru Utilities Corporation (NUC) and NUC customers | Annex B – Supplemental Annex Doc – Pages 17-18 |
| Investment 2: RE/EE Financing Scheme | 25 solar PV systems (5 kWp each) 210 refrigerators 210 freezers 170 washing machines 160 A/C 615 sets of 10 LED light bulbs | GEF Expenditure: US$ 350,000 Co-financing: US$ 80,000 | DCIE, MoF, and Bendigo Bank Offices | 970 Households 420 SMEs (equivalent to 1,390 participants) | Annex B – Supplemental Annex Doc – Pages 18-19 |
| Demo 1: Storage and use of Excess Electricity from ADB solar field | 480,000 L/day reverse osmosis (RO) water desalination system | GEF Expenditure: US$ 1,020,000 Co-financing: US$ 22,000,000 | Meneng District | 920 people (@ 6 hr./day operation, 130 lits/day/pax) | Annex B – Supplemental Annex Doc – Pages 20-21 |
| Demo 2: Mini treated water production & distribution system | 15,600 L/day RO water desalination system – includes PV panels; battery bank; water pump; water tank; piping; spares; freight; and training | GEF Expenditure: US$ 301,000 Co-financing: US$ 250,000 | A 3-block housing complex in “The Location” | 120 people in demo community | Annex B – Supplemental Annex Doc – Page 21-24 |
| Demo 3: Hybrid diesel-electric bus for public transport | 1 mid-sized bus – includes charging station; spare battery; other spares; freight; and training | GEF Expenditure: US$ 310,000 Co-financing: US$ 15,000 | The whole island and DoT headquarter | 40,800 passengers/yr @ 15 pass./trip; 8 trips/day; and 340 days/yr. | Annex B – Supplemental Annex Doc – Page 24-26 |

Annex F: Knowledge Management Plan

Overview of existing lessons and best practice that inform the project concept:

Despite the previous donor-funded projects that were implemented in Nauru, the overall results in terms of sustainable improvements in capacity have been mixed, at best. Based on the discussions with the project proponent (DCIE) and a number of project stakeholders, the GEF Agency (UNDP) determined during the PIF development stage the approaches to capacity development and knowledge management that were implemented in the country. While many of the donor agencies such as the ADB, AusAID, NZAID), and the WB have incorporated capacity development in the projects that they have supported, the stakeholders felt that these have provided benefits mainly during the time the projects were implemented. The country needs more effective and sustainable capacity development and supplemented with a good knowledge management system. The increased interest in capacity development and knowledge management in recent years somehow reflects an acknowledgment of the shortcomings in the previous development assistance in the country. This situation led to suggestions from the DCIE to incorporate capacity development interventions in the planned SMARTEN Project that will involve approaches that are more systematic and integrated, and which focus more on the country’s ownership and achievement of sustainable results. This includes capacity building focusing on policy, procedures, personnel, organizations, institutions, and supporting environment required to effectively deliver development outcomes. Moreover, to contribute to sustaining the developed capacity, supplemental activities will be included to create and support an integrated knowledge management system in the country on energy and environment.

Plans to learn from relevant projects, programs, initiatives & evaluations:

In the design of the SMARTEN Project, the project development team had consulted not only the stakeholders but also from donor agencies, UN agencies (including UNDP) and the regional organizations e.g., SPC, SPREP, PIFS regarding lessons learned on capacity development from the projects that they have supported and implemented in Nauru, as well as in the other Pacific Island Countries. This include lessons learned from the training activities that were part of the energy and climate change projects that were implemented in Nauru, as well as in climate change adaptation, and socio-economic development projects in the country. Apart from sharing, and learning from, the results and experiences gained from the project implementation, the knowledge management plan of the project shall include activities of learning from the other energy and environment projects in the country and from other PICs. These include key data/information in the field of energy, relevant information on lessons learnt and best practice in project implementation from previous ongoing UNDP and UNDP-GEF projects in the country, as well as in other PICs. These include the Enabling the Implementation of the Nauru Energy Road Map (NERM) Project and to some extent the Implementing a “Ridge to Reef” Approach to Protect Biodiversity and Ecosystem Functions in Nauru (R2R Nauru) Project.

Proposed processes to capture, assess  and document info, lessons, best practice & expertise generated during implementation:

A plan for information gathering (e.g., field visits) on the results of implemented project activities, including those from the identified parallel baseline projects/programs/activities will be developed as part of the project implementation and monitoring plans. The assimilation, processing, reporting and dissemination of the project results to the relevant target audiences and beneficiaries will be integrated into the information sharing system that will be developed in Component 4 of the project. The various project activities will produce useful information, and these can only be useful when made easily available and accessible. The SMARTEN PMU in collaboration with the DCIE and other GON agencies, NGO’s and community stakeholders will provide professional (international and local) support to a nationwide dissemination of knowledge products that the project will produce particularly regarding RE and EE measures and techniques that are expected to be widely applied and practiced. Information gathered and stored within the Information Sharing System that will be housed in DCIE will provide the information that is to be reviewed and if required edited to develop practical, user friendly media publications that highlight key energy supply and utilization issues and how these are being addressed in the country. Interaction with local communities to define and articulate methods of information exchange will be an important attribute to the successful delivery of this initiative.

Proposed tools and methods for knowledge exchange, learning & collaboration:

Among the tools and processes that will be used for the knowledge management cum information sharing system is the development and management of a user friendly easily accessible information sharing system on all aspects of sustainable energy and low carbon development for the promotion and dissemination of knowledge. In addition, an energy data banking system will also be established to collect and store all energy supply and consumption information, including monitoring and reporting activities as well as status of advancement of the NERM achievements. These 2 systems are essential sources of data/information that continuously support the knowledge management objective of the project. Both systems will be housed and operated and maintained by DCIE. Part of the strategy for the knowledge management plan is collaboration and direct partnerships with key stakeholders in the country (e.g., NUC, Vital Energy Corporation, Bendigo Bank) and other regional organizations in the Pacific (e.g., UNDP, SPC, SPREP, PPA and PCREEE) to access and obtain pertinent data and information from related activities that they implement, as well as sustainable energy and low carbon development data or promotional products (e.g. video, posters) that they have.

Proposed knowledge outputs to be produced and shared with stakeholders:

Key information and knowledge products (such as media articles, blogs, press releases, social media tweets, posts, etc.) will be developed from the following project outputs:

- Formulated, approved and enforced policy and regulatory instruments (standards, policies and implementing rules and regulations) on the application of RE & EE technologies in the energy and energy end use sectors.

- Revised and updated energy policy framework (NEPF), National Energy balance (NEB) and roadmap (NERM) and policies and regulations to achieve NERM targets.

- Completed and approved national energy plans and budgets that are fully implemented and enforced.

- Established and operational institutional framework that supports the implementation of low carbon (EE & RE) development policies, standards and IRRs.

- Feasible financial support schemes for RE & EE technologies application projects in the energy end-use sectors, inclusive of the implementation arrangements, and procedures for financial assistance application process.

- Derisked RE-based power generation and grid stability projects, grid-connected or decentralized RE-based energy generation at the district level, inclusive of business plans for the GoN and private sector to facilitate financing and implementation.

- Completed engineering designs and implementation plans of RE & EE demos in the energy and energy end-use sector and documented reports on of the demos results and performance.

- Approved implementation designs and plans for the replication and/or scale up of the demos.

- Established and operative energy audit system covering all energy end-use sectors.

- Implemented and operational feasible RE & EE technologies application demos.

- Regularly conducted capacity development program on sustainable energy and low carbon development, continuing program on the promotion and awareness enhancement on integrated sustainable energy development.

- Operational information sharing system for the promotion and dissemination of knowledge on all aspects of sustainable energy and low carbon development; as well as an energy supply and consumption monitoring & reporting system and data banking.

How knowledge and learning will contribute to overall project/program impact and sustainability plans for strategic communications.

Knowledge management and dissemination is a critical aspect of the Nauru SMARTEN Project. To be successful, the project will need to (1) generate the knowledge that Nauru needs to get to the next level in the application of RE&EE technologies, and (2) ensure that this knowledge reaches a broad range of persons and is available for them to access on an ongoing basis. Thus, within the project activities are interwoven the knowledge management plan of creating critical information, documenting this information, and ensuring both in the near term and long term that key groups in society both know about this information and can access it as needed. As part of the information sharing and dissemination aspects of the project, communicating the results of sound feasibility and design engineering studies for RE and EE technology application demonstrations will be used for decision making in the operation, maintenance and sustainability of these, and provide information to help convince communities about the showcased technology applications and other proposed RE and EE measures.

The project’s knowledge management plan is essential in achieving the improved awareness and capacity of the GoN, private sector and communities about cost-effective application of RE and EE technologies and practices, which is one of the key outcomes for achieving the SMARTEN Project objective. The essential components of the plan (e.g., energy data banking system, information sharing system) will be used for energy planning and for the formulation of sustainable energy and low carbon development policies and regulations. It will also be useful to international donors, implementing partners and consultants when designing and implementing energy related projects for Nauru. The implementation of the envisioned plan will improve awareness, communications, and education and ensure that the experiences and results of the SMARTEN Project are properly captured and disseminated to in-country stakeholders as well as project partners, including UNDP and GEF. The proper management of knowledge will require transparent and timely sharing of data, and other information through proper communication.

Annex G: Changes from the PIF

This annex shows how the detailed project design corresponds to the PIF and provides details of changes. The table below shows the comparison of the outcomes and output statements in the PIF to that in the ProDoc. The main change concerns one of the Outputs, which was splint in two for clarity. The other changes made are mainly on the reorganization and restructuring of the outputs, and in some cases, additional outputs were included to enhance the achievement of the component outcome. Overall, in each of the project components, the changes in some of the original output statements did not alter the theme and overall substance of the expected outcome in each project component. For the cases in which changes are significant, rationale is given. In each case, changes are explained, correspondence between PIF outputs and ProDoc outputs (if there are changes) are highlighted, and justification for changes is provided.

Table G-1: Changes from the PIF

| - Expected Outcomes/Outputs |  | - Rationale for Change in PIF Outcomes/Outputs in the ProDoc |
| --- | --- | --- |
| GEF-Approved PIF | - Project Document |  |
| Outcome 1 | - Same | - N/A |
| Output 1.1: Formulated and approved standards, policies and implementing rules and regulations (IRRs) on the application of RE & EE technologies in the energy and energy end use sectors. | - Output 1.1: Formulated, approved and enforced policy and regulatory instruments (standards, policies and implementing rules and regulations) on the application of RE & EE technologies in the energy and energy end use sectors. | - Output 1.1 has been slightly rephrased to add clarity and especially to specify that SMARTEN will also support the enforcement of the approved policy and regulatory instruments. |
| Output 1.2: Enforced policies on the promotion and support for the implementation of action plans to achieve the RE and EE targets of the updated Nauru Energy Road Map (NERM). Output 1.3: Revised and updated National Energy Policy Framework (NEPF), inclusive of updated national energy balance and action plans. | - Output 1.2: Revised and updated energy policy framework (NEPF) , National Energy balance (NEB) and roadmap (NERM) and policies and regulations to achieve NERM targets. | - Outputs 1.2 and 1.3 in the PIF were merged to form Output 1.2 of the ProDoc. Since the NERM is based on the NEPF, during the preparation of the project document it was noted that there is a strong overlap between these activities, and it is more efficient to carry them out together. |
| Output 1.4: Completed energy-integrated development planning at the national level. | - Output 1.3: Approved and implemented fully budgeted national energy plan. | - Since Outputs 1.2 and 1.3 from the PIF were merged, Output 1.4 from the PIF has been relabeled Output 1.3 in the ProDoc, and it has been also rephrased to add clarity. |
| Outcome 2: Improved institutional and financial mechanisms in the integrated planning and implementation of RE & EE technologies for energy generation and utilization. | - Outcome 2.1: Cohesive institutional mechanisms for facilitating widespread application of RE & EE technologies in the country. - Outcome 2.2: Adequate amounts of financial resources available for RE/EE Technology application projects in the country | - Outcome 2 from the PIF has been split into Outcome 2.1 and Outcome 2.2 in the ProDoc. During the Logical Framework Analysis (LFA) workshop held in Nauru, the participant stakeholders, by consensus suggested a clear separation of the institutional and the financial aspects of the outcome statement to better design the activities that will deliver the necessary outputs that will collectively bring about each of them. |
| --- | - Output 2.1.1: Well-coordinated planned and implemented RE/EE Projects of the GoN, private sector and communities | - After splitting the original Outcome 2 statement into Outcomes 2.1 & 2.2, Output 2.1.1 is added since it is necessary to help bring about Outcome 2.1. |
| Output 2.1: Established and operational institutional framework that supports the implementation of low carbon (EE & RE) development policies, standards and IRRs. | - Label changed to Output 2.1.3 | - Output 2.1 from the PIF was simply renamed Output 2.1.3 in the ProDoc. |
| Output 2.2: Completed study of the feasible financial support schemes for RE & EE technologies application projects in the energy end-use sectors, inclusive of the implementation arrangements, and procedures for financial assistance application process. | - Output 2.2.1: Feasible financial support schemes for RE & EE technologies application projects in the energy end-use sectors, inclusive of the implementation arrangements, and procedures for financial assistance application process. | - Output 2.2 from the PIF was relabeled Output 2.2.1 in the ProDoc. Furthermore the output statement has been slightly rephrased to highlight that is about actual designed financing schemes. |
| Output 2.3: Completed study on the derisking of RE-based power generation and grid stability initiatives of the state utility, and grid-connected or decentralized RE-based energy generation at the district level, inclusive of business plans based on the derisking study for the GON and private sector to facilitate financing and implementation of feasible RE and EE technologies applications. | - Output 2.2.2: Derisked RE-based power generation and grid stability projects, grid-connected or decentralized RE-based energy generation at the district level, inclusive of business plans for the GoN and private sector to facilitate financing and implementation. | - Output 2.3 from the PIF was relabeled Output 2.2.2 in the ProDoc. Furthermore the output has been rephrased for brevity and clarity. |
| Output 2.4: Approved and implemented energy-integrated development projects in the end-use sectors including the mining industry and the regional processing centers. | - Label changed to Output 2.1.2 |  |
| Outcome 3: | - Same | - N/A |
| Output 3.2.1: Completed engineering designs and implementation plans of the identified demonstrations of RE & EE technologies applications in the energy generation and end-use sectors. | - Label changed to Output 3.1 |  |
| Output 3.1.2: Documented and disseminated reports about the energy performance and impact assessments of implemented demonstrations. | - Label changed to Output 3.2 |  |
| Output 3.1.3: Approved implementation plans and project designs for the replication and/or scale up of demonstrated RE & EE technologies applications. | - Output 3.3: Approved implementation designs and plans for the replication and/or scale up of demonstrated RE & EE technologies applications. | - Output 3.1.3 from the PIF was labeled Output 3.3 in the ProDoc. Furthermore the output statement was slightly rephrased for clarity. |
| --- | - Output 3.4: Established and operational energy audit system covering all energy end-use sectors. | - Output 3.4 has been added to the ProDoc. Since several large electricity consumers will be added to the national grid, in the effort to improve EE it is important that the DCIE acquires in-house skills to conduct energy audits of large consumers. |
| Output 3.2.2: Implemented and operational RE & EE technologies application demonstrations. | - Label changed to Output 3.5 |  |
| Output 3.1.1: Completed feasibility analyses of RE and EE technologies applications in the energy generation and energy end-use sectors in Nauru. | - Removed | - Output 3.1.1 from the PIF was removed because the feasibility analysis of RE/EE technologies has been included as part of the activities under the new Output 3.1 |
| Outcome 4: | - Same: | - N/A |
| Output 4.1: Completed capacity development program for government officials and authorities, and the private sector on energy-integrated development planning, including RE and EE technology applications. Output 4.4: Continuing program on the promotion and awareness enhancement on integrated sustainable energy development for Nauruans. | - Output 4.1: Regularly conducted capacity development program on sustainable energy and low carbon development; continuing program on the promotion and awareness enhancement on integrated sustainable energy development. | - Outputs 4.1 and 4.4 in the PIF were merged because these are both on capacity building in various aspects of sustainable energy and low carbon development. |

Table G-2 below shows the list of previously identified (during the PIF development stage) baseline projects and activities. These were no longer considered in the SMARTEN Project design and have been replaced with ongoing and soon-to-be implemented projects that are relevant as baseline for the project. These are either already completed or are expected to be completed before the implementation of the SMARTEN project.

Table 6-2: Completed Initially Identified Baseline Projects/Activities

| Baseline Project/Activity | Funder | Results/Impacts |
| --- | --- | --- |
| Power generation assets upgrading | ADB | Nauru Utilities Corporation (NUC) has made significant progress in upgrading its power plant assets and facilities. It also has upgraded its grid network to accommodate new solar PV installations that will be integrated into the grid (e.g., new 6 MW solar PV farm to be funded by ADB). NUC has made significant progress in achieving its ambitious 4.1 kWh/Lt of diesel target for 2020. |
| Improvement of supply-side efficiency (focusing on water production and supply) | ADB | Water production facilities improvements at NUC have been made contributing to significant progress in improving NUC’s financial management leading to the minimization of its annual subsidy from the Government. Additional funding becomes available from the Government for the installation of central water tanks in the different districts of the country. |
| Fossil fuel reduction and alternative fuel utilization | GoN | Fuel handling facilities improvements have been made at NUC contributing to significant progress in improving financial management of NUC that led to the minimization of its annual subsidy from the Government. Regarding the alternative fuel study, it was found out that there is limited interest in LPG or bioenergy from stakeholders. |
| Nauru Energy Initiative | EU and NZMFAT | Completed installation and integration into the national power grid of a 1 MW solar PV farm, including the construction of a high voltage transmission system through the middle of the island to connect to the national grid the new solar PV power generation installations. This is to be followed by the planned 6 MW solar PV project funded by the ADB. |
| Capacity building on the operation and maintenance of solar PV power systems | EU and NZMFAT | Instead of capacity building, the review of International and Pacific Island Region Technical Standards on Solar PV Power was done, and the Draft Nauru Solar PV Technical Standards was developed. The NUC is expecting that its technical and power plant personnel will receive solar PV training in future solar PV projects like SMARTEN. |
| Energy efficiency standards and labeling program | GoN | A set of national mandatory minimum energy performance standards (MEPS) and labeling scheme for appliances in Nauru have been developed. |
| Improvement of energy sector governance and accountability | CTIF | The Energy Unit of the DCIE was formally established in July 2017. The Energy Unit consists of a Director, Climate Change and Energy and an Energy Officer. As part of the Enabling the Implementation of the Nauru Energy Road Map project, a project manager (based at DCIE) began work based in September 2017. |
| Establishment of energy sector policies, regulations and legislation | ADB | Completed Legislative Gap Analysis of the energy sector, and review of the draft NUC Power System Rules and Regulations of 2012; Developed draft NUC Regulations, which are much broader than originally planned residential PV regulations only, and these de facto include a full Grid Code, i.e., regulations, technical provisions and specifications for NUC day-to-day operations, and NUC customers’ obligations. |
| Facilitation of the development of local skills base for the energy sector | GoN | No activities for developing local skills for the energy sector. Instead, technical assistance and training/support to attend international events to the Energy Unit provided. Also, 400 hard copies of updated NERM 2018 – 2020 published and distributed, including various promotional material produced and distributed. |
| Promotion of partnership with private sector in energy development. | ADB | Establishment of an economically efficient, secure and safe National Fuel Terminal and fuel supply under the private sector entity – Vital Energy |

Annex H: GEF 7 Core Indicator Worksheet

| Core Indicator 6 | Greenhouse gas emission mitigated |  |  |  |  |  | (Metric tons of CO₂e ) |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Expected metric tons of CO₂e (6.1+6.2) |  |  |  |  |  |
|  |  | PIF stage | Endorsement |  | MTR |  | TE |
|  | Expected CO2e (direct) | 1.029 million tCO2e | 0.350 million tCO2e |  |  |  |  |
|  | Expected CO2e (indirect) |  | 0.699 million tCO2e |  |  |  |  |
| Indicator 6.1 | Carbon sequestered or emissions avoided in the AFOLU sector |  |  |  |  |  |  |
|  |  | Expected metric tons of CO₂e |  |  |  |  |  |
|  |  | PIF stage |  | Endorsement |  | MTR | TE |
|  | Expected CO2e (direct) | N/A |  | N/A |  | N/A | N/A |
|  | Expected CO2e (indirect) | N/A |  | N/A |  | N/A | N/A |
|  | Anticipated start year of accounting | N/A |  | N/A |  | N/A | N/A |
|  | Duration of accounting | N/A |  | N/A |  | N/A | N/A |
| Indicator 6.2 | Emissions avoided Outside AFOLU |  |  |  |  |  |  |
|  |  | Expected metric tons of CO₂e |  |  |  |  |  |
|  |  | Expected |  |  |  | Achieved |  |
|  |  | PIF stage |  | Endorsement |  | MTR | TE |
|  | Expected CO2e (direct) | 1.029 million tCO2e |  | 0.350 million tCO2e |  |  |  |
|  | Expected CO2e (indirect) |  |  | 0.699 million tCO2e |  |  |  |
|  | Anticipated start year of accounting |  |  | 2020 |  |  |  |
|  | Duration of accounting |  |  | Until 2050 |  |  |  |
| Indicator 6.3 | Energy saved |  |  |  |  |  |  |
|  |  | MJ |  |  |  |  |  |
|  |  | Expected |  |  |  | Achieved |  |
|  |  | PIF stage |  | Endorsement |  | MTR | TE |
|  |  |  |  | 6.53x108 |  |  |  |
| Indicator 6.4 | Increase in installed renewable energy capacity per technology |  |  |  |  |  |  |
|  | Technology | Capacity (MW) |  |  |  |  |  |
|  |  | Expected |  |  |  | Achieved |  |
|  |  | PIF stage |  | Endorsement |  | MTR | TE |
|  |  |  |  | 6.9 MWdc |  |  |  |
| Core Indicator 11 | Number of direct beneficiaries disaggregated by gender as co-benefit of GEF investment |  |  |  |  |  | (Number) |
|  |  | Number |  |  |  |  |  |
|  |  | Expected |  |  |  | Achieved |  |
|  |  | PIF stage |  | Endorsement |  | MTR | TE |
|  | Female |  |  | 817 |  |  |  |
|  | Male |  |  | 817 |  |  |  |
|  | Total |  |  | 1,634 |  |  |  |

Annex I: GEF Project Taxonomy Worksheet

| Level 1 | Level 2 | Level 3 | Level 4 |
| --- | --- | --- | --- |
| Influencing models |  |  |  |
|  | Transform policy and regulatory environments |  |  |
|  | Strengthen institutional capacity and decision-making |  |  |
|  | Convene multi-stakeholder alliances |  |  |
|  | Demonstrate innovative approaches |  |  |
|  | Deploy innovative financial instruments |  |  |
| Stakeholders |  |  |  |
|  | Indigenous Peoples |  |  |
|  | Private Sector |  |  |
|  |  | Capital providers |  |
|  |  | Financial intermediaries and market facilitators |  |
|  |  | Large corporations |  |
|  |  | SMEs |  |
|  |  | Individuals/Entrepreneurs |  |
|  |  | Non-Grant Pilot |  |
|  |  | Project Reflow |  |
|  | Beneficiaries |  |  |
|  | Local Communities |  |  |
|  | Civil Society |  |  |
|  |  | Community Based Organization |  |
|  |  | Non-Governmental Organization |  |
|  |  | Academia |  |
|  |  | Trade Unions and Workers Unions |  |
|  | Type of Engagement |  |  |
|  |  | Information Dissemination |  |
|  |  | Partnership |  |
|  |  | Consultation |  |
|  |  | Participation |  |
|  | Communications |  |  |
|  |  | Awareness Raising |  |
|  |  | Education |  |
|  |  | Public Campaigns |  |
|  |  | Behavior Change |  |
| Capacity, Knowledge and Research |  |  |  |
|  | Enabling Activities |  |  |
|  | Capacity Development |  |  |
|  | Knowledge Generation and Exchange |  |  |
|  | Targeted Research |  |  |
|  | Learning |  |  |
|  |  | Theory of Change |  |
|  |  | Adaptive Management |  |
|  |  | Indicators to Measure Change |  |
|  | Innovation |  |  |
|  | Knowledge and Learning |  |  |
|  |  | Knowledge Management |  |
|  |  | Innovation |  |
|  |  | Capacity Development |  |
|  |  | Learning |  |
|  | Stakeholder Engagement Plan |  |  |
| Gender Equality |  |  |  |
|  | Gender Mainstreaming |  |  |
|  |  | Beneficiaries |  |
|  |  | Women groups |  |
|  |  | Sex-disaggregated indicators |  |
|  |  | Gender-sensitive indicators |  |
|  | Gender results areas |  |  |
|  |  | Access and control over natural resources |  |
|  |  | Participation and leadership |  |
|  |  | Access to benefits and services |  |
|  |  | Capacity development |  |
|  |  | Awareness raising |  |
|  |  | Knowledge generation |  |
| Focal Areas/Theme |  |  |  |
|  | Integrated Programs |  |  |
|  |  | Commodity Supply Chains (Good Growth Partnership) |  |
|  |  |  | Sustainable Commodities Production |
|  |  |  | Deforestation-free Sourcing |
|  |  |  | Financial Screening Tools |
|  |  |  | High Conservation Value Forests |
|  |  |  | High Carbon Stocks Forests |
|  |  |  | Soybean Supply Chain |
|  |  |  | Oil Palm Supply Chain |
|  |  |  | Beef Supply Chain |
|  |  |  | Smallholder Farmers |
|  |  |  | Adaptive Management |
|  |  | Food Security in Sub-Sahara Africa |  |
|  |  |  | Resilience (climate and shocks) |
|  |  |  | Sustainable Production Systems |
|  |  |  | Agroecosystems |
|  |  |  | Land and Soil Health |
|  |  |  | Diversified Farming |
|  |  |  | Integrated Land and Water Management |
|  |  |  | Smallholder Farming |
|  |  |  | Small and Medium Enterprises |
|  |  |  | Crop Genetic Diversity |
|  |  |  | Food Value Chains |
|  |  |  | Gender Dimensions |
|  |  |  | Multi-stakeholder Platforms |
|  |  | Food Systems, Land Use and Restoration |  |
|  |  |  | Sustainable Food Systems |
|  |  |  | Landscape Restoration |
|  |  |  | Sustainable Commodity Production |
|  |  |  | Comprehensive Land Use Planning |
|  |  |  | Integrated Landscapes |
|  |  |  | Food Value Chains |
|  |  |  | Deforestation-free Sourcing |
|  |  |  | Smallholder Farmers |
|  |  | Sustainable Cities |  |
|  |  |  | Integrated urban planning |
|  |  |  | Urban sustainability framework |
|  |  |  | Transport and Mobility |
|  |  |  | Buildings |
|  |  |  | Municipal waste management |
|  |  |  | Green space |
|  |  |  | Urban Biodiversity |
|  |  |  | Urban Food Systems |
|  |  |  | Energy efficiency |
|  |  |  | Municipal Financing |
|  |  |  | Global Platform for Sustainable Cities |
|  |  |  | Urban Resilience |
|  | Biodiversity |  |  |
|  |  | Protected Areas and Landscapes |  |
|  |  |  | Terrestrial Protected Areas |
|  |  |  | Coastal and Marine Protected Areas |
|  |  |  | Productive Landscapes |
|  |  |  | Productive Seascapes |
|  |  |  | Community Based Natural Resource Management |
|  |  | Mainstreaming |  |
|  |  |  | Extractive Industries (oil, gas, mining) |
|  |  |  | Forestry (Including HCVF and REDD+) |
|  |  |  | Tourism |
|  |  |  | Agriculture & agrobiodiversity |
|  |  |  | Fisheries |
|  |  |  | Infrastructure |
|  |  |  | Certification (National Standards) |
|  |  |  | Certification (International Standards) |
|  |  | Species |  |
|  |  |  | Illegal Wildlife Trade |
|  |  |  | Threatened Species |
|  |  |  | Wildlife for Sustainable Development |
|  |  |  | Crop Wild Relatives |
|  |  |  | Plant Genetic Resources |
|  |  |  | Animal Genetic Resources |
|  |  |  | Livestock Wild Relatives |
|  |  |  | Invasive Alien Species (IAS) |
|  |  | Biomes |  |
|  |  |  | Mangroves |
|  |  |  | Coral Reefs |
|  |  |  | Sea Grasses |
|  |  |  | Wetlands |
|  |  |  | Rivers |
|  |  |  | Lakes |
|  |  |  | Tropical Rain Forests |
|  |  |  | Tropical Dry Forests |
|  |  |  | Temperate Forests |
|  |  |  | Grasslands |
|  |  |  | Paramo |
|  |  |  | Desert |
|  |  | Financial and Accounting |  |
|  |  |  | Payment for Ecosystem Services |
|  |  |  | Natural Capital Assessment and Accounting |
|  |  |  | Conservation Trust Funds |
|  |  |  | Conservation Finance |
|  |  | Supplementary Protocol to the CBD |  |
|  |  |  | Biosafety |
|  |  |  | Access to Genetic Resources Benefit Sharing |
|  | Forests |  |  |
|  |  | Forest and Landscape Restoration |  |
|  |  |  | REDD/REDD+ |
|  |  | Forest |  |
|  |  |  | Amazon |
|  |  |  | Congo |
|  |  |  | Drylands |
|  | Land Degradation |  |  |
|  |  | Sustainable Land Management |  |
|  |  |  | Restoration and Rehabilitation of Degraded Lands |
|  |  |  | Ecosystem Approach |
|  |  |  | Integrated and Cross-sectoral approach |
|  |  |  | Community-Based NRM |
|  |  |  | Sustainable Livelihoods |
|  |  |  | Income Generating Activities |
|  |  |  | Sustainable Agriculture |
|  |  |  | Sustainable Pasture Management |
|  |  |  | Sustainable Forest/Woodland Management |
|  |  |  | Improved Soil and Water Management Techniques |
|  |  |  | Sustainable Fire Management |
|  |  |  | Drought Mitigation/Early Warning |
|  |  | Land Degradation Neutrality |  |
|  |  |  | Land Productivity |
|  |  |  | Land Cover and Land cover change |
|  |  |  | Carbon stocks above or below ground |
|  |  | Food Security |  |
|  | International Waters |  |  |
|  |  | Ship |  |
|  |  | Coastal |  |
|  |  | Freshwater |  |
|  |  |  | Aquifer |
|  |  |  | River Basin |
|  |  |  | Lake Basin |
|  |  | Learning |  |
|  |  | Fisheries |  |
|  |  | Persistent toxic substances |  |
|  |  | SIDS : Small Island Dev States |  |
|  |  | Targeted Research |  |
|  |  | Pollution |  |
|  |  |  | Persistent toxic substances |
|  |  |  | Plastics |
|  |  |  | Nutrient pollution from all sectors except wastewater |
|  |  |  | Nutrient pollution from Wastewater |
|  |  | Transboundary Diagnostic Analysis and Strategic Action Plan preparation |  |
|  |  | Strategic Action Plan Implementation |  |
|  |  | Areas Beyond National Jurisdiction |  |
|  |  | Large Marine Ecosystems |  |
|  |  | Private Sector |  |
|  |  | Aquaculture |  |
|  |  | Marine Protected Area |  |
|  |  | Biomes |  |
|  |  |  | Mangrove |
|  |  |  | Coral Reefs |
|  |  |  | Seagrasses |
|  |  |  | Polar Ecosystems |
|  |  |  | Constructed Wetlands |
|  | Chemicals and Waste |  |  |
|  |  | Mercury |  |
|  |  | Artisanal and Scale Gold Mining |  |
|  |  | Coal Fired Power Plants |  |
|  |  | Coal Fired Industrial Boilers |  |
|  |  | Cement |  |
|  |  | Non-Ferrous Metals Production |  |
|  |  | Ozone |  |
|  |  | Persistent Organic Pollutants |  |
|  |  | Unintentional Persistent Organic Pollutants |  |
|  |  | Sound Management of chemicals and Waste |  |
|  |  | Waste Management |  |
|  |  |  | Hazardous Waste Management |
|  |  |  | Industrial Waste |
|  |  |  | e-Waste |
|  |  | Emissions |  |
|  |  | Disposal |  |
|  |  | New Persistent Organic Pollutants |  |
|  |  | Polychlorinated Biphenyls |  |
|  |  | Plastics |  |
|  |  | Eco-Efficiency |  |
|  |  | Pesticides |  |
|  |  | DDT - Vector Management |  |
|  |  | DDT - Other |  |
|  |  | Industrial Emissions |  |
|  |  | Open Burning |  |
|  |  | Best Available Technology / Best Environmental Practices |  |
|  |  | Green Chemistry |  |
|  | Climate Change |  |  |
|  |  | Climate Change Adaptation |  |
|  |  |  | Climate Finance |
|  |  |  | Least Developed Countries |
|  |  |  | Small Island Developing States |
|  |  |  | Disaster Risk Management |
|  |  |  | Sea-level rise |
|  |  |  | Climate Resilience |
|  |  |  | Climate information |
|  |  |  | Ecosystem-based Adaptation |
|  |  |  | Adaptation Tech Transfer |
|  |  |  | National Adaptation Programme of Action |
|  |  |  | National Adaptation Plan |
|  |  |  | Mainstreaming Adaptation |
|  |  |  | Private Sector |
|  |  |  | Innovation |
|  |  |  | Complementarity |
|  |  |  | Community-based Adaptation |
|  |  |  | Livelihoods |
|  |  | Climate Change Mitigation |  |
|  |  |  | Agriculture, Forestry, and other Land Use |
|  |  |  | Energy Efficiency |
|  |  |  | Sustainable Urban Systems and Transport |
|  |  |  | Technology Transfer |
|  |  |  | Renewable Energy |
|  |  |  | Financing |
|  |  |  | Enabling Activities |
|  |  | Technology Transfer |  |
|  |  |  | Poznan Strategic Programme on Technology Transfer |
|  |  |  | Climate Technology Centre & Network (CTCN) |
|  |  |  | Endogenous technology |
|  |  |  | Technology Needs Assessment |
|  |  |  | Adaptation Tech Transfer |
|  |  | United Nations Framework on Climate Change |  |
|  |  |  | Nationally Determined Contribution |
|  |  |  | Paris Agreement |
|  |  |  | Sustainable Development Goals |
|  |  | Climate Finance (Rio Markers) |  |
|  |  |  | Climate Change Mitigation 1 |
|  |  |  | Climate Change Mitigation 2 |
|  |  |  | Climate Change Adaptation 1 |
|  |  |  | Climate Change Adaptation 2 |

https://www.google.com/maps/place/Parliament+House/@-0.5407732,166.9240574,11597m/data=!3m1!1e3!4m13!1m7!3m6!1s0x0:0x0!2zMMKwMzEnMjIuMCJTIDE2NsKwNTUnNTMuNCJF!3b1!8m2!3d-0.522778!4d166.9315033!3m4!1s0x6f7d1e803a23b4d3:0xf468cd0e9a3ab39c!8m2!3d-0.5470631!4d166.9170199?hl=en

Example: 1 kWp ground-mounted PV installation in Nauru, based on ADB estimates, would generate nearly 6 kWh/day. This means that for each kWp of solar PV panels installed, 6 kWh of battery storage should be added. Considering that the lifespan of a battery bank is about one third of a solar PV system, over the lifetime of the PV system the battery bank has to be replaced 3 times. Therefore, at the current costs for Nauru using the ADB project as a reference, 1 kWp of ground mounted solar PV system (including ground preparation) costs about US$ 3,800. To be conservative, let’s assume here that the installment of 1 kWp of solar PV panels can be done for US$ 3,000.

The cost of batteries for 1 kWh of storage capacity in Nauru, using the cost per kWh for the ADB battery bank, is about US$ 1,280. Again, to be conservative, let’s assume a cost for the battery of US$ 1,000/kWh, and since 6 kWh of battery storage would be needed per kWp of PV installed (based on the average daily sun-hours), that would give a total cost for 6 kWh of battery capacity needed per each kWp of solar PV installed, of US$ 6,000. Therefore, each additional kWp of solar PV system installed in Nauru including the battery bank, since the daytime demand is already fully met as shown in Figure 2 of the Supplemental Annex file, would cost US$ 9,000 (this without taking into consideration that over the lifetime of the PV panels, the battery bank has to be re-purchased two more times). If one would want to install just 1 MWp of additional PV generation capacity, including the required 6 MWh of battery storage capacity, it would require a conservative upfront disbursement of US$ 9.0 M (it could be as high as US$ 11-12 M, plus the two re-purchases of the battery banks).

This is average GEF$ per total lifetime GHG ER (direct + indirect) of full-sized projects. The average total cost (GEF + co-financing) per total lifetime GHG ER (direct + indirect) is US$ 42/ton CO2.

Multiple types of intermittent energy sources, for example solar + wind, make the grid inherently more stable, since they can partially compensate each other.

The goal of NUC is to have at least twice the needed water desalination capacity, split 50/50 on each side of the island to guarantee water supply even in case of severe weather events, which historically have never hit the island on both sides at the same time.

The excess power generation capacity is curtailed for economic reasons, since ADB calculations show that is cheaper to curtail it than store the electricity in batteries.

“The Location” is a housing compound built in the Denigomodu district to house the expatriate, mostly from Tuvalu and Kiribati, who worked for NPC. After the 2002 collapse of the phosphate mining industry, the expatriates moved out and Nauruans have occupied the houses.

Nauru’s NDC hinges on its National Sustainable Development Strategy (NSDS) 2005 – 2025 (revised in 2009), Nauru Energy Road Map (NERM) 2014-2020, The Second National Communication (SNC) to the UNFCCC (submitted in 2015), and the Republic of Nauru Climate Change Adaptation and Disaster Risk Management Framework (RONAdapt).

These targets are: (a) 50% of grid electricity supplied from renewable energy sources by 2020; and, (b) 30% improvement in energy efficiency in the residential, commercial and government sectors by 2020.

The quoted unit average worldwide investment cost (US$/kW) for solar PV system is for utility scale system (crystalline and thin film). While it is recognized that the investment cost for such utility scale system has been on a downtrend, the realistic unit investment cost is relatively higher in SIDS like Nauru. For example, the unit installed cost of recent solar PV power generation system installations in American Samoa and Cook Islands is more than double this current average unit cost. Also, the systems that will also be promoted under the project will include solar PV systems for residences, rooftops (commercial & industrial) and community-based systems. The investment cost for these types of solar PV systems are more than double than that of the utility scale systems (Ref: Lazard’s Levelized Cost of Electricity Analysis, Ver. 11.0, November 2017).

This includes both Direct and Indirect

This includes both Direct and Indirect

It is estimated that the Mini solar powered water desalination and distribution system will directly benefit 120 persons (60 for each gender); the bus will provide a mean of transportation for a minimum of 100 persons (50 for each gender); SMARTEN is expected to directly create 24 new positions (12 women and 12 men); and finally it has been assesses that the financing scheme will benefit 1,390 Nauruans (50% women and 50% men).