United Nations Development Programme

Project Document

| Project title: Sustainable Finance of Papua New Guinea’s Protected Area Network |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Country: Independent State of Papua New Guinea | Implementing Partner: Conservation & Environmental Protection Authority (CEPA) |  |  |  | Management Arrangements: National Implementation Modality (NIM) |
| UNDAF/Country Programme Outcome: Sub-Outcome 3.3: By 2022, people, particularly marginalized and vulnerable, are empowered to manage climatic risks, develop community resilience and generate development opportunities from protection of land, forests and marine resources |  |  |  |  |  |
| UNDP Strategic Plan Output: Output 2.4.1: Gender-responsive legal and regulatory frameworks, policies and institutions strengthened, and solutions adopted, to address conservation, sustainable use and equitable benefit sharing of natural resources, in line with international conventions and national legislation. |  |  |  |  |  |
| UNDP Social and Environmental Screening Category: Moderate Risk |  |  | UNDP Gender Marker: 2 |  |  |
| Atlas Project ID/Award ID number: 00086294 |  |  | Atlas Output ID/Project ID number: 00093582 |  |  |
| UNDP-GEF PIMS ID number: 5507 |  |  | GEF ID number: 9536 |  |  |
| Planned start date: 01 September 2018 |  |  | Planned end date: 31 August 2025 (84 months) |  |  |
| LPAC date: June 2018 (planned) |  |  |  |  |  |
| Brief project description: The project, Sustainable Finance of Papua New Guinea’s Protected Area Network, will extend Government of PNG’s ability to fulfil its protected area mandate and implement the Protected Area Policy: (i) secure stable and long-term financial resources for the management of protected areas across the country; (ii) ensure that these financial resources are allocated to contribute to improving effectiveness of the management of the protected areas across the country; and (iii) ensure that they are managed cost-effectively and efficiently with respect to their conservation and other complementary development objectives. In recognition of this need, the project will assist with the development of a diversified mix of conventional and innovative funding sources and consolidate revenues to finance the ongoing costs of establishing and managing protected areas, and assist the Government to establish a Biodiversity Fund – that will be built on a secure, accountable and transparent financial mechanism, for receiving, administering and disbursing funds. The project will, therefore, result in a system that will provide catalytic and long-term financial support that will lead to stable ecosystems (both within and outside of protected areas), coupled with the social transformations to make that happen (including transforming institutions to become supporters/facilitators of that process, and the establishment of long-term partnerships). |  |  |  |  |  |
| Financing Plan |  |  |  |  |  |
| GEF Trust Fund |  |  | USD 11,311,915 |  |  |
| UNDP TRAC resources |  |  | USD 228,326 |  |  |
| - Total Budget administered by UNDP |  |  | USD 11,540,241 |  |  |
| Parallel co-financing (all other co-financing that is not cash co-financing administered by UNDP) |  |  |  |  |  |
| Government of PNG |  |  | USD20,000,000 |  |  |
| Barrick Niugini Ltd/Porgera Joint Venture |  |  | USD 600,000 |  |  |
| Walindi Plantation Resort |  |  | USD 350,000 |  |  |
| Mahonia na Dari |  |  | USD 120,000 |  |  |
| FORCERT |  |  | USD 1,000,000 |  |  |
| WCS |  |  | USD 1,000,000 |  |  |
| Binatang Research Centre |  |  | USD 1,730,000 |  |  |
| Yus Conservation Area/Woodland Park Zoo |  |  | USD 3,760,000 |  |  |
| WB/UNDP Forest Carbon Partnership Facility 2 |  |  | USD 5,000,000 |  |  |
| Government of Australia (DFAT) |  |  | USD 15,337,423 |  |  |
| New Britain Palm Oil Limited |  |  | USD 1,235,500 |  |  |
| - Total co-financing |  |  | USD 50,132,923 |  |  |
| - Grand-Total Project Financing (1)+(2) |  |  | USD 61,673,164 |  |  |
| Signatures |  |  |  |  |  |
| Signature: print name below |  | Agreed by Government |  | Date/Month/Year: |  |
| Signature: print name below |  | Agreed by Implementing Partner |  | Date/Month/Year: |  |
| Signature: print name below |  | Agreed by UNDP |  | Date/Month/Year: |  |

# Table of Contents

I.	Table of Contents	3

II.	Development Challenge	6

III.	Strategy	17

IV.	Results and Partnerships	27

V.	Project Management	63

VI.	Project Results Framework	66

VII.	Monitoring and Evaluation (M&E) Plan	71

VIII.	Governance and Management Arrangements	76

IX.	Financial Planning and Management	83

X.	Total Budget and Work Plan	87

XI.	Legal Context	95

XII.	Risk Management	95

XIII.	Annexes	97

Annex A:  Multi Year Work Plan	98

Annex B:  GEF Tracking Tool at baseline	101

Annex C: Overview of Technical Consultancies and Contracts	102

Annex D: Terms of Reference	107

Annex E: List of Protected Areas in PNG	115

Annex F: List of people consulted over the course of the PPG process	118

Annex G: Process of selecting pilot sites.	126

Annex H: A proposal to develop a “METT for PNG”	131

Annex I: UNDP Social and Environmental Screening Procedure and plans as needed	133

Annex J: Stakeholder Engagement Plan	134

Annex K: Gender Analysis and Action Plan	138

Annex L: Additional Maps	146

Annex M: UNDP Risk Log	147

Annex N: Results of the capacity assessment of the project implementing partner and HACT micro assessment	151

Annex O: Capacity Scorecard Assessments for key government institutions	152

Acronyms, Abbreviations and Glossary

| AWP | Annual Work Plan |
| --- | --- |
| CEPA | Conservation and Environmental Protection Authority |
| CEPF | Critical Ecosystems Partnership Fund |
| CI | Conservation International |
| CSO | Civil Society Organisation |
| CSR | Corporate Social Responsibility |
| DEC | Department of Environment and Conservation |
| DFAT | Department of Foreign Affairs and Trade (of the Government of Australia) |
| DPS | Direct Project Services |
| EOP | End of Project |
| ERC | (UNDP) Evaluation Resource Centre |
| FMA | Forest Management Areas |
| FPIC | Free, Prior, Informed Consent |
| FSP | Full Sized Project |
| GDP | Gross Domestic Product |
| GEB | Global Environmental Benefits |
| GEF | Global Environment Facility |
| GEF OFP | GEF Operational Focal Point |
| GEFSEC | Global Environment Facility Secretariat |
| GoPNG | Government of PNG |
| HCS | High Carbon Stock |
| HCV | High Conservation Value |
| IEO | (GEF / UNDP) Independent Evaluation Office |
| (I)NGO | (International) Non-Governmental Organisation |
| IP | (Project) Implementing Partner |
| KfW | Derived from Kreditanstalt für Wiederaufbau, KfW is the German Development Bank |
| KPIs | Key Performance Indicators |
| LLG | Local Level Government |
| LMMA | Locally Managed Marine Area |
| METT | Management Effectiveness Tracking Tool |
| MHL | Mainland Holdings Ltd |
| MOECCC | Ministry of Environment, Conservation and Climate Change |
| MPA | Marine Protected Area |
| MPTF | UN Multi-Partner Trust Fund |
| MTR | Mid Term Review |
| NEC | National Executive Council |
| NIM | National Implementation Modality (of project) |
| PA | Protected Area |
| PB | Project Board |
| PIF | Project Identification Form |
| PIR | GEF Project Implementation Report |
| PIU | Project Implementation Unit |
| PNG | Papua New Guinea |
| PNGK | PNG kina (local currency) with USD 1 = PNGK 3.2 (March 2017) |
| PNG LNG | PNG Liquid Natural Gas |
| POPP | Programme and Operations Policies and Procedures |
| POPP | (UNDP) Programme and Operations Policies and Procedures |
| PPG | Project Preparation Grant |
| PRODOC | Project Document |
| Protected Area Management | As used throughout this project document, see Box 1 |
| REDD+ | Reducing Emissions from Deforestation and forest Degradation + |
| ROAR | (UNDP) Results Oriented Annual Report |
| RP | Responsible Party |
| RPA | Responsible Party Agreement |
| RSPO | Roundtable for Sustainable Palm Oil |
| SABL | Special Agriculture and Business Leases |
| SDG | Sustainable Development Goals |
| SES | Social and Environmental Screening |
| SSTrC | South-South and Triangular Cooperation |
| STAP | GEF Scientific Technical Advisory Panel |
| SWMI | Sepik Wetland Management Initiative |
| TA | Technical Assistance |
| TE | Terminal Evaluation |
| TNC | The Nature Conservancy |
| UNDP | United Nations Development Programme |
| UNDP RR | UNDP Resident Representative |
| UNDP-CO | UNDP Country Office |
| UNDP-GEF | UNDP Global Environmental Finance Unit |
| UNDP-GEF RTA | UNDP-GEF Regional Technical Advisor |
| UNDP-GEF SGP | UNDP-GEF Small Grants Program |
| WCS | Wildlife Conservation Society |
| WMA | Wildlife Management Area |
| WWF | World Wild Fund for Nature |

# Development Challenge

- An emerging country in transition.  The Independent State of Papua New Guinea (of 452,860km2) is found in Melanesia, which, in turn, is a sub-region of Oceania. The current human population is 7.9 million and growing rapidly: 54% of the population is estimated to be under the age of 24.  The average human density is 17.1 people/km2 and 87% of the population is rural.

- The country’s formal economy is dominated by two sectors. The minerals and energy extraction sector contributes most to export earnings and Gross Domestic Product. This means that national income is strongly influenced by commodity prices, leading to strong GDP growth from 2003-2011 (averaging 5.7% annually) but slower growth since 2015 (down to an estimated 2.1% in 2017). The agricultural, forestry, and fishing sector engages most of the labour force who work in the formal sector, some in plantations and commercial fishing.  However, the greater majority of the population is engaged in the informal sector on small holdings on customary land – coupled with harvesting of natural resources. As a result, it is estimated that 80-85% of the population work and live in subsistence farming and fishing, with only a small portion of their livelihoods earned through the cash economy. These people are, therefore, totally reliant on the productivity of their environment.

- Demands on the country’s financial and management resources are very high, exacerbated by the lack of transport infrastructure - with the geography as a profound barrier: precipitous mountainous terrain and scattered islands make servicing difficult and expensive.  Service delivery is complicated by poor capacity in administration and financial stewardship. People’s access to economic development, health services and education is largely determined by their location, with the remote rural people having least opportunities for social mobility. Only 13% of rural people have attained secondary education, compared with 25% of urban people. The literacy rate ranges from 59% in rural areas to 86% in urban areas. The gender gap in literacy is also more obvious in rural areas, where 46% of women cannot read or write, compared to 33% of men. Rural people are also vulnerable to natural disasters, and to the effects of climate change, such as sea level rise, droughts, floods, storms and fire.

- What is most interesting is that with provision of basic services and aspects that lead to improved well-being, the people who are the customary owners of much of the natural wealth of the country are willing custodians of that wealth.

- A custodian of globally significant biodiversity. While PNG is struggling to provide its growing population with basic services, it is endowed with exceptional natural values. The rich biodiversity of the country is founded on a number of different factors.  The biogeography of Papua New Guinea (PNG) is characterised by a number of key features: i) it is found to the east of Wallace’s line (although there are both floral and faunal elements – mainly plants and invertebrates as well as volant mammals and birds – that have crossed this line), ii) the vast island of New Guinea (which is the largest and highest tropical island on earth and which has the third largest contiguous area of humid forest in the world) is the northern extension of the Indo-Australian tectonic plate  and iii) it includes a number of island arcs (including New Britain, New Ireland, Bougainville, the Admiralty Islands – with these three sets of islands sometimes grouped into the Bismarck Archipelago, the Trobriand Islands and the Louisiade Archipelago) that were never connected to the island of New Guinea. The result is that PNG, as a nation state, sits at the confluence of three biotas: there are avian, mammalian, floral and invertebrate affinities with Malesia, floral, mammalian, reptilian and invertebrate affiliates with the Australian biota, and species that are characteristic of the Pacific biota.  When that is coupled with (large and small scale) isolation associated with tectonic activity (with associated uplift), erosion into deep valleys and a humid climate, the result is a species-rich, diverse biota with a high degree of endemism.  The numbers are staggering: estimates for the number of vascular plants in the country go as high as 25,000 species of which 60% are estimated to be endemic (to an area slightly larger than the nation state of PNG – therefore, including the entirety of the island of New Guinea).  In some groups, endemism is even higher – for example, an estimated 90% of angiosperms are endemic.  The diversity and endemism extends through virtually all the represented faunal and floral groups: examples could be equally drawn from mammals (over 200 regionally endemic species), birds (42% regionally endemic), reptiles, amphibians (with 77% of frogs endemic to PNG alone).  However, many species are under threat: the IUCN Red List for PNG includes 33 critically endangered species, 56 endangered, 373 vulnerable and 289 near threatened.

- As a part of the third largest tropical forests in the world, the forests of Papua New Guinea (covering 280,000km2) are important for regulating the global climate, they store a significant amount of carbon (for example, the Kamula Doso area encompasses 7,900km2 and stores an estimated 480 million tonnes of carbon), maintain the quality of water and preserve soil stability.  The value of the ecosystems of Papua New Guinea is accentuated by their integrity (relative to other degraded systems across the globe).

- PNG also has over 2.4 million km2 of ocean that, in turn, includes over 7,000km2 of coral reefs and 4,200km2 of diverse mangrove forest.  The reefs are part of the Coral Triangle (the area with the highest global levels of marine biodiversity) – including the Bismarck Sea, the Milne Bay Area and Southeast Papua.  There are an estimated 2,800 species of fish in PNG’s waters.

- The global significance of biodiversity of the area is widely recognised (although being a nation state that sits at the confluence of three biotas, it shares this international recognition with its neighbours).  For example, the island of New Guinea is recognised as a Wilderness area by Conservation International (CI), and the Bismarck Archipelago, the Trobriand Islands and the Louisiade Archipelago are included in the East Melanesian Islands Biodiversity Hotspot.  PNG is also identified by CI as being one of 17 “megadiverse” countries in the world.

- A rural population dependent on natural resources.  Human populations mirror the diversity of other species.  Once the island was colonized by humans some 40-50,000 years ago, people inhabited virtually every habitat across the islands but thereafter, once established, groups remained in relative isolation for long periods of time.  As with speciation of the fauna and flora, this has resulted in cultural diversification – this is perhaps best illustrated by the estimated 850 languages that are spoken across the country.

- The rural communities are organised into clan-based structures: these structures are the primary resource owners with 97% of the land and adjacent coastal areas being owned under customary law.  Therefore, in addition to the ownership of resources associated with terrestrial areas, the clan structures also own and have customary rights over access to and use of resources associated with coastal and marine areas (usually associated with mangroves, sea grass beds and near-reefs).

- There has also been a long agrarian history in the area, with evidence that agricultural production started between 7,000 – 10,000 years ago.  Plant domestication took place on the island of New Guinea, including crops such as taro Colocasia esculenta, banana Musa spp., sago Metroxylon sagu, sugar cane Saccharum officinarum and yam Dioscorea spp.. Food production (still primarily based on these crops) for more than 75% of the households in the country takes place in shifting ‘gardens’.  When human populations are at low densities, this shifting agriculture increases (some measures of) biodiversity – and communities have demonstrated knowledge of the need for fallow periods of at least 30 years before the land can be re-cleared and re-planted.  However, rural human populations have diverse livelihood strategies and are not dependent on the ‘gardens’ alone.  Indeed, the people are dependent on natural resources.  Studies have demonstrated that terrestrial, arboreal and marine fauna constitute the principal sources of protein and fats to sustain the rural population (with an estimated 4-8 million vertebrate animals captured on an annual basis), and an estimated 1,035 plants species being used for a variety of purposes (including, for example, house construction and roofing, furniture, mats and basket production).  In coastal communities a wide variety of seafood, including fish, molluscs, and turtles are harvested. Currently, coral reef ecosystems in PNG are being exploited by small-scale artisanal and subsistence fishers, who use a range of techniques (including modern tools that are unsustainable) to harvest reef and reef-associated fish.  In addition, the natural resources provide an important safety net when crops fail and when natural disasters strike – something that is expected to become more frequent under climate change scenarios.

- Finally, the forests (and occasionally but more rarely reefs) lie at the heart of the spiritual aspects of rural Papua New Guineans’ lives.  This is primarily expressed through the many sacred sites identified by any given clan and there are stands within the forests in which men are not allowed to hunt and which women are not allowed to visit.  For other people – such as the Kaulong people (a small group of people living in the Kandrian District of West New Britain), the forest is home to spirits which may be capricious and dangerous.

- Thus, on an international scale, PNG’s people – primarily the customary landowners – are custodians of critical natural wealth. The challenge is how the world can support PNG’s people to progress their social and economic well-being without irretrievable loss of this natural wealth

- Threats to biodiversity, ecosystem services and ecological processes.  The current human population is 7.9 million and growing rapidly: 54% of the population is estimated to be under the age of 24.  The average human density is 17.1 people/km2 and 87% of the population is rural.  With the expansion of logging and industrial scale monocultures (see below), the area in which people live has become limited; when this is coupled with increases in the human populations, the impacts of shifting agriculture and clearance of habitat have also increased (as the fallow periods have shortened), and this is a trend that will not change for the foreseeable future: approximately two-thirds of PNG’s forests are within a day’s walk of a rapidly growing village.

- Over 50% (or 140,000km2) of PNG’s forests lie within the 298 logging concessions (for map, see Figure 3 in Annex M).  By 2014, an estimated 0.49% of the forests of PNG were being lost to industrial logging on an annual basis.  This appeared to be a deceleration of the rate at which forests are being degraded (in the period from 2002 – 2014 compared with the period 1972 – 2002).  That is not to say that exploitation is not expanding: between 2002 – 2014, a total of 4.1% of the forest was cleared or logged, and 7,705km2 of previously unlogged forest was degraded through logging.  The rate of forest loss in the most accessible forests is still occurring at a higher rate (7.3% being cleared in the period from 2002 – 2014).  Moreover, many of the concessions are being repeat-harvested within the legal cutting cycle of 35 years – with evidence of some repeated harvesting within 15 years and some areas have been harvested three times within a 20-year period.

- Of particular concern for the future of PNG’s forests in the last decade has been the allocation of 3.8 million hectares of rainforest in Special Agriculture and Business Leases, which would allow for their future deforestation. Some of these leases are over locations identified as being of very high priority for conservation, including over proposed World Heritage Sites. In 2016, the PNG Government committed to cancel all SABLs, but this has yet to occur. Under current legislation, Wildlife Management Areas are not immune from development options. Large-scale open pit mining for minerals such as gold and copper have also resulted in both direct impacts from forest clearing (including for infrastructure, access roads and associated support) as well as incidences of marine and riverine pollution from the runoff of tailings.

- In addition to logging, forests are being converted to industrial scale agricultural monocultures – especially for palm oil Elaeis guineensis production.  This has been done under the auspices of a government initiative that allocates Special Agriculture and Business Leases (SABLs) that allow for clear-felling of areas for agricultural development; a total of 38,000 km2 have been allocated under SABLs (for map, see Figure 4 in Annex M).  While the intention has been for agricultural development, SABLs have also permitted logging companies to circumvent the country’s forestry laws such that between 2002 – 2014, 2,047km2 within SABLs was logged or cleared with no agricultural development once the logging had taken place.  In addition, there are substantial overlaps between the SABLs and the logging concessions (e.g., the three Kamula Doso logging blocks are encompassed within three SABLs).

Figure 1. Illustrating the deforestation and forest degradation, 1972-2014. Figure from Bryan & Shearman, 2015

- Forest fires are also increasing – exacerbated by climate change (which seems to be lifting the inversion layer which, in turn, leads to drying of forests at lower altitudes) and El Niño events (with associated droughts), logging and road building (with their edge effects and accumulation of dead material).  In the period from 2002-2014, a total of 81,819 fires were detected with evidence that the majority were started by people (because of their proximity to human habitation).  Degraded forest is also susceptible to invasive species (e.g., Eichornia crassipes, Piper aduncum or Spathodea campanulata are some relatively common invasive species – among many, many others).  Finally, while deforestation and forest degradation contributes to climate change, so too does climate change threaten the forests of PNG: there is an obvious linkage between climatic patterns and the growth, health and persistence of forests.

- PNG is highly vulnerable to the impacts of climate change: maximum temperatures in PNG have increased at a rate of about 0.11°C per decade, sea levels have risen by about 7mm per year since 1993, and the level of ocean acidification has been slowly increasing. The Government of PNG through the Climate Change and Development Authority lists nine major impacts of climate change in PNG: coastal flooding and sea level rise; inland flooding; food insecurity caused by crop failures due to droughts and inland frosts; climate change-induced migration; damage to coral reefs; malaria and vector borne diseases; water and sanitation; and landslides. Rural subsistence communities in PNG are particularly vulnerable to climate change impacts due to their direct dependence on natural resources and a reliable climate and their limited capacity to adapt. Changes in species distribution have already been recorded, with wildlife in montane areas will be particularly vulnerable to extinction.

Figure 2. The coverage of extractive (logging, mining, oil and gas) licenses and concessions, and SABLs across Papua New Guinea showing the degree to which they overlap. (Figure adapted and reproduced with permission; Shearman, 2013).

- In the marine environment, primary threats have been identified as population growth (especially in coastal areas); development activities (in coastal and upstream areas) and related impacts including increased runoff and habitat fragmentation and degradation; overexploitation of resources, particularly fisheries resources; pollution, especially related to runoff from inland mining activities and poor land management practices, and debris and sewage; and impacts of climate change, including potential disruption of oceanographic processes, changes in species distribution, changes in water temperature and salinity, sea level rise and saltwater intrusion into groundwater.

- In summary, then, there is a trend for expansion of logging into all available unlogged forests, repeated and unsustainable harvest in already logged forests, and, ultimately, clearance of forests for agricultural production (especially oil palm).  All this exacerbates the risk of fire and the spread of invasive species.  This is a pattern that has been seen in Malaysia and Indonesia in the past decades.

- Further to these threats, other extractive industries (mining, and oil and gas) also present threats, both from forest clearance (for infrastructure) and pollution (especially into water systems from the tailings).

- Indeed, an examination of the degree to which extractive industries (logging, mining, and oil and gas) licenses and concessions (and Special Agricultural Business Licenses, SABLs) overlap elegantly illustrates an effective “land grab”, and the absence of coordination and ethical, meaningful land planning as these industries seek to ensure that all possible land (and marine areas) is claimed for exploitation (see Figure 22).  This is occurring despite the customary ownership of the land by local communities that is enshrined in the constitution; there has been a negligible level of consultation with the customary owners of the land when drawing up these licenses and concessions.

- A policy response.  The Government of PNG is meeting this challenge in its legislative and policy framework. At the highest level, the PNG constitution includes as one of its five goals: “Natural resources and environment: natural resources and environment to be conserved and used for the collective benefit of us all, and be replenished for the benefit of future generations.”

- The national vision, launched in November 2009, is: “Papua New Guinea will be a Smart, Wise, Vibrant and Happy Country by 2050”. The PNG Vision 2050 maps out the country’s development initiatives for a 40-year period from 2010 to 2050, and is premised on the mutually reinforcing roles of economic growth, human development and environmental management. One of the seven pillars of Vision 2050, a number are particularly pertinent to this project:

  - Human Capital Development, Gender, Youth and People Empowerment

  - Institutional Development and Service Delivery

  - Environment Sustainability and Climate Change

  - Spiritual, Cultural and Community Development

  - Strategic planning, integration and control

- The National Strategy for Responsible Sustainable Development for PNG (StaRS) promotes cost-effective and resource efficient ways of responsible sustainable development and call for a “paradigm shift” towards a green economy. The strategy recognises the natural capital elements that have the potential to become the growth drivers in the future.

- To complement these high-level plans, the government has developed other significant policies that recognise the importance of the environment and of sustainable resource use while improving social and economic mobility, including:

  - Newly launched third successive Medium Term Development Plan 2018-2022

  - National Population Policy 2015-2024

  - National Climate Compatible Development Management Policy 2014

  - Policy on Protected Areas 2014 (to be discussed below) and

  - PNG Marine Program on Coral Reefs, Fisheries and Food Security 2010-2013 (new version currently in draft).

- In addition and pertinently, the government – through CEPA and with the support of the UNDP-GEF-4 project – has developed and approved a Protected Areas Policy (2014).  This will be discussed below.

- However, to date, there is a profound policy-implementation challenge and the government has struggled to implement PNG’s policy framework to prevent a significant decline in biodiversity and ecosystem services.

- Protected areas: part of the development solution.  In the majority of countries around the world, one key response to equivalent threats, and loss of biodiversity, the erosion of ecosystem services and the degradation of ecological processes is to establish a system of protected areas.  Protected areas in PNG are primarily community owned and managed, and the national concept of protected areas is strongly rooted in PNG cultural and tenure arrangements. These areas provide a critical opportunity for the PNG people to maintain and sustainably use the values of the country’s natural wealth, to prevent irretrievable loss of ecosystem services and biodiversity, and to work towards a sustainable future. While they cannot be the whole solution to biodiversity loss, they form the core of the strategy for biodiversity conservation and sustainable development. In Papua New Guinea, 4.1% of the land area and less than 1% of the marine areas now fall within “recognised” protected areas.  This is well below the CBD targets that are envisaged by this time.

- Protected areas in some form have a long history in PNG. Customary landowners recognise many areas of land and sea as “tambu” – areas of special spiritual significance. “Over thousands of years, communities all over PNG have been conserving nature for cultural and spiritual reasons, while pursuing traditional livelihoods in these landscapes and seascapes”. PNG has 59 protected areas covering 2.14 million ha (Figure3 & Annex E).

- While a number of protected area planning exercises have been carried out – primarily on the basis of identifying the key biodiversity areas in the country – there is a disconnect between these planning processes and the realities on the ground.  The whole concept of “conservation”, with its focus on rare or endemic biodiversity, is alien to the greater majority of people in the country primarily because the concept of resource limitation is alien – because the country is so rich and productive.  This is not to say that humans have not had an impact on certain resources; rather, resources are harvested to local extirpation (or at least to a point to which harvesting it is no longer viable) but other resources are so abundant that the consequences of exhausting any one resource has little impact on people’s livelihoods.

Figure 3: Growth of protected area system in PNG

- Through the 1990s and 2000s, the GEF and many of the larger international NGOs implemented programmes that were based on “traditional” conservation approaches or “mantras”: identifying the key biodiversity areas, approaching communities and encouraging the establishment of protected areas (most often Wildlife Management Areas, WMAs or Locally Managed Marine Areas, LMMAs), often on the principle of actual or potential resource limitation. Many of the actors present in earlier decades have now either withdrawn from PNG or are active in other projects but do not focus on protected areas, due to a shift in priorities at the international level. Some projects were not successful, while others appeared to be progressing well until support was suddenly withdrawn, before local communities had the capacity to take on the responsibility. There are, however, a few exceptions, such as in the Yus Conservation Area, when the conservationists arrive at the very moment when a specific resource is becoming depleted (in that case, the Matschie’s tree kangaroo, Dendrolagus matschiei which was being hunted by local people) – thereby offering an opportunity to drive the establishment of the protected area on the basis of said resource depletion.

- The “traditional” conservation narrative is also significantly gender biased, with a focus on a male perspective.  Thus, in contrast to the male perspective, women generally acknowledge that there is indeed some limitation on access and decision making over resources.  However, this is often pertaining to clean water or firewood – thus, not the rare, endemic biodiversity that is the traditional focus of conservation organisations.

- In addition to the programmes carried out by the international NGOs, the extractive industries have also gone through the process of working with communities that live in the areas adjacent (or nearby) their areas of operation – or using the Conservation Needs Assessments (as described above) as the basis on which to build protected areas.  The processes carried out in the Headlands of the Strickland and in the Kaijende Highlands (with the support of Barrick/Porgera Joint Venture), and Lake Kutubu WMA and Lower Kikori (with the support of PNG LNG) are the best examples of this.

- In contrast to this backdrop, the process of land acquisition either by logging companies or industrial agriculturists (in effect, oil palm) are perceived to be a direct threat by local communities and people are seeking some form of legal protection for their land – including the establishment of protected areas. This suggests another narrative may be more successful in the process of establishing protected areas across the country.

- Such dichotomies have made it challenging for both state and non-state actors to identify the most parsimonious strategy to develop the country’s protected area system. The de facto situation is that, despite the number of planning exercises, there has been no coherent process yet to establish protected areas in the country. The National Protected Area System is in the initial stages of its establishment with support from the UNDP-GEF-4 project. Supportive of the customary land ownership enshrined in the constitution, the NPAS is tailored to adopt the different types of protected areas that have emerged in PNG – ranging from past planning processes with international NGOs catalysing WMAs or LMMAs, to affiliations to extractive industries as part of their offsetting or corporate social responsibility efforts, to individual efforts most often linked with single or multiple species.

- There is an emergent trend related to the alternative narrative: communities are forming partnerships with local NGOs in an effort to find some form of legal protection over their land against land ‘acquisition’ or actual grabbing by loggers and agro-industrialist, using protected areas as the legal vehicle for doing this.  Many of these processes are based on acknowledging and valuing the depth of traditional ecological knowledge, and empowering the people to bring traditional knowledge and the formal protected area thinking together to create a functional system of protected areas that is culturally and contextually appropriate. Based on the results of the nationwide assessment on the management effectiveness of protected areas, management of most protected areas is community-based and supported only by volunteer labour. By functioning at the grassroots levels, these processes are proving successful and empowering. While most of the customary landowners were keen to be involved and to remain as primary stewards of the protected areas, they recognised that this could not be done without assistance and called for a greater government involvement.

- Within this picture sits the Conservation and Environmental Protection Authority (CEPA, formerly the Department of Environment and Conservation, DEC).  CEPA was formed through the CEPA Act (2014).  The Act does not refer directly to CEPA’s mandate with regard to protected areas; instead, it refers to existing “environmental conservation laws and policy directions”, most specifically the Conservation Areas Act (Chapter 362) of 1978, and the Environment Act of 2000.  In Part II, Section 8 of the Act, the “functions” are described, including:

  - “To do all things necessary for the conservation and protection of the environment in accordance with the environmental conservation laws and any policy directions of the Minister and the National Executive Council; and

  - “To co-ordinate with provincial and local-level governments and sub-national authorities to foster, manage and monitor environmental conservation strategies and programmes in the country; and

  - [Pertinently, for this project] “To impose and receive rents, fees, charges and bonds in respect of its functions under any environmental conservation law, including but not limited to providing services related to the approval and issue of environment permits and the investigation and audit of activities under the Environment Act 2000; and

  - “To promote Papua New Guinea's laws, regulations and policies relating to conservation and environment matters within the country and overseas; and

  - “To give advice to the Minister and maintain dialogue with other government agencies on environmental conservation laws and policies”

- Since the formation of CEPA, with the support of the UNDP-GEF-4 project, a Protected Areas Policy has been produced. This lays out a progressive and ambitious vision for protected areas of the country – and for CEPA, which it asserts is “the lead agency for protected areas in PNG, setting the standards, providing overview and support, and coordinating the complex array of activities … ensuring that Protected Areas are managed as an effective and cohesive network”.  It describes very clearly CEPA’s mandate that takes on the lead responsibility with the establishment and management of national protected areas while instituting governance arrangements at subnational levels where provincial and Local Level Governments, communities and even private companies to declare and gazetted protected areas.

- Indeed, as is relatively common among protected area authorities in developing economies, despite years of “capacity development” and despite its “upgrade” from a “department” to an “authority”, little has changed in CEPA. The UNDP-GEF-5 project is specifically working on institutional strengthening of the CEPA’s Sustainable Environment Programme (SEP) that also looks at negotiating overlapping concessions and licenses with other resource sectors to support the local communities and NGOs in their efforts to establish protected areas.

- In terms of protected areas, across the country, (currently) CEPA recognises the existence of 59 protected areas (see Annex E).  The greater majority of the PAs across the country fall within land under customary ownership; some of these are being developed and/or being managed in partnership with a non-state actor; many others exist primarily on paper with no actual management or activities taking place. The list of “recognised” protected areas in PNG also suggests that there are numerous other areas which could be recognised as being protected; these are the areas that exist with the integrity of their biodiversity, ecosystem service and ecological processes remaining intact. These include i) areas simply valued by local peoples for the natural resources that they provide, ii) areas that are held sacred by local peoples, iii) areas that are simply inaccessible – by virtue of the geography in which they are found, and iv) areas protected by local peoples for any other reason. In addition to this list, there are areas that are set aside by those industries as either part of an offset (as part of their efforts to fulfil their corporate social responsibilities) or as part of their commitments (usually associated with a certification process, the best example of which is the Roundtable for Sustainable Palm Oil, RSPO, which requires oil palm producers to set aside areas of high conservation value, HCV, or high carbon stock, HCS) or requirements (e.g., Forest Management Areas, FMAs, are required to set aside a minimum of 10% of their license area as conservation areas).

- However, protected areas across the country neither have insufficient and unreliable funding nor do they generate revenue.  This is recognized in much of the literature and, indeed, the Mama Graun Conservation Trust Fund was established as part of the WB/CI/GEF project “Forestry and Conservation Project” in recognition of this.  The Yus Conservation Area has established its own Endowment Fund to assist with sustainable financing of the area.

- The limitation of funding was also recognised at the site level. In an exercise to determine the management effectiveness of the protected areas across the country, 83% of protected areas states that the current budget was an issue and 91% stated that there was no budget security. This is corroborated with the data collected during the PPG process: 40 of a total of 59 protected areas are known not to receive any budget whatsoever. Indeed, only one, the Yus Conservation Area, has a transparent expenditure (for the last five years) and projected budget (for the coming five years).

- Funding limitation is also recognized in the PA Policy. Indeed, one (of the five) pillars of the policy is dedicated to “sustainable and equitable financing for protected areas”. Two key objectives are identified in the policy to achieve the vision of “sustainable and equitable financing for protected areas”: i) to develop and implement a Biodiversity Trust Fund, and ii) to develop small grants programs for the establishment and management of protected areas.  The achievement of these key objectives has, in addition and with support from the UNDP-GEF-4 project, been built into the Protected Areas Policy Implementation Plan (PAIP, 2018-2028).  This GEF-6 project has been designed to these two objectives: indeed, this is the primary scope of the project – with the overarching aim of building sustainable protected areas, especially in terrestrial and marine areas that belong to the communities.  However, to put these things in place without building the institution will only lead to inefficient management and ineffective use of funds. As such, the project will also be investing in the processes of building confidence in the institutions’ accountability and transparency mechanisms beyond refute while ensuring that national government plays central role in the capitalization and consolidation of revenues for protected areas with support from UNDP and other partners.

- In addition, with a few notable exceptions, there are no revenue streams being generated by protected areas (see Table 1). In the majority of the cases, the revenue that is being generated within any given protected area is generally not being used for its management – although in a few cases it may arguably be being used for protection of the site (primarily by excluding other people from the site).  Almost without exception, there is no (indicated in Table 1 there are few data available for many sites) and, in many cases, the beneficiaries (especially at the individual or family level) do not see the need to generate or share revenue for the benefit of the protected area as a whole.  In addition, even in the country’s most lucrative tourism site – the Kokoda Trail (which falls under the Kokoda Initiative, jointly financed by the Governments of PNG and Australia), analysis suggests that the envisaged sustainable income streams from ‘trekking activities’ will not generate sufficient income to support in any meaningful way the conservation and sustainable use of the Interim Protection Zone (IPZ) around the Trail.

Table 1. Some examples (but not an exhaustive list) of protected areas that are generating some form of revenue; there are no data for the majority of PAs

| Area | Source of revenue | Amount/yr. (5-year average) | Used for |
| --- | --- | --- | --- |
| Kimbe Bay (specifically Kaula Island) | Diving & other tourism | K15/person K 20,000/year | Fees transferred to clan to protect site |
| Individual clan areas in Sepik Wetlands | Sale of crocodile eggs | K153,603 (total for all eggs harvested; average over period 2013-2017) | Individual/family/clan use |
| Hunstein Range WMA | Guest house and bird watching | Birdwatching K15/person Guesthouse K50/person | Individual use |
| The Kikori River Basin (with four WMAs), and Lake Kutubu | Support from PNG LNG | USD 1.8 million/year | Support to PAs, including surveys, capacity development |
| Yus Conservation Area | Endowment Trust Fund | USD 103,000 (2018 budget) | Yus Conservation Area Program costs |
|  | Donor funding | USD 500,000 – 750,000 |  |
| Kaijende Highlands | REDD+ | - | Used for “carbon sequestration and biodiversity conservation” |
|  | Support from Barrick/Porgera Joint Venture | K220,000/year (since 2005) |  |
| Headwaters of the Strickland | REDD+ | - |  |
|  | Support from Barrick/Porgera Joint Venture | K165,000/year (since 2005) |  |
| Wanag WMA | Research fees and research-related employment | K110,000/year | Individual use/Protecting site |
|  | Donor funding | K100,000/year | Local school |
| Kokoda Memorial Park | Tourist fees DFAT support | USD 750,000/yr | To Kokoda Track Authority (including two LLGs) |
| Kokoda Hisorical (Track) Reserve | Tourist fees DFAT support |  |  |

- By working to build sustainability – and, in particular, sustainable financing of the protected areas of the country – this project will contribute to prevent the degradation of the country’s biological resources (including biodiversity, ecosystem services and ecological processes).  As such, the proposed project will be relevant to the development of PNG as highlighted in the policy and strategy documents described above.  Building on the experience of GEF 4 & 5, CEPA intends to establish a policy and initial national system for the mitigation of impacts on biodiversity in PNG. This includes an investigation on biodiversity offset as a stable revenue stream. The proposed project also will contribute directly to the achievement of a number of different strategic goals and targets of the country’s NBSAP.  Given the absolute global importance of the country’s biodiversity, ecosystem services and ecological processes, this project will, similarly, be making a significant contribution (with an associated legacy) to global environmental issues.

- The project will have other, broader political implications for the country. This project is being viewed as a high profile project for the GEF for a number of different reasons, including: the interest of the Minister of Environment to form a Biodiversity Fund. Thus, there is an opportunity (but also a pressure and responsibility) to ensure that the project not only works but is very successful. The success of the project, in turn, will bring political leverage for the Government of PNG.

- The project will also make contributions to meeting the objectives of the Sustainable Development Goals (SDGs) as follows: Goal 1 Ending poverty: the project will work in a number of ways to reduce poverty, specifically through community engagement, by making the realities of the customary ownership of the land at the heart of the protected area system of the country, and improving the wellbeing of people that choose to establish protected areas within the land for which they are responsible; Goal 5: Gender equality: by supporting women to take leading roles in the management of the protected areas, on account of their greater awareness and direct interest in protection and subsequently, resulting from empowerment, addressing/preventing high levels of GBV; Goal 13 Take urgent action to combat climate change and its impacts through improved protection and management of forest and marine resources; Goal 14 Life below water through improved management of marine protected areas; and Goal 15 Life on land: through the improved management of terrestrial protected areas.

# Strategy

- The Long-Term Solution. The proposed project is seeking to implement solutions that will overcome the root causes to the threats to biodiversity, ecosystem services and ecological processes, and also to overcome the barriers to an effectively managed protected area system in the country, as described above, and to achieve the project’s objective: To reduce the funding gap for Papua New Guinea’s protected areas in order to improve their management effectiveness, and livelihoods of their communal landowners.

- The objective will be achieved through the implementation of three project components.  Component 1: Enabling conditions for improving the sustainability of the protected area system.  This component will focus principally on i) ensuring a clear understanding among relevant institutions of their specific roles in protected area management, including how they are financed and ii) building the capacity and governance systems within those organisations that have a specific mandate and/or role and responsibility in the management of protected areas, as well as among local communities as land owners and land users.  Component 2: Establishment, operationalisation and mobilization of funding for a Biodiversity Fund.  This component will focus on the establishment of the Biodiversity Fund for PNG and, will assist with the establishment of mechanisms to manage and consolidate funds for exclusive use across the PA system in PNG including the necessary documentation and governance structures associated with this.  Component 3: Enhanced management capacity and financial sustainability of individual protected areas. This component focuses on testing, piloting and learning – specifically i) testing mechanisms to deliver funds from the Biodiversity Fund to selected protected areas, ii) piloting mechanisms (including through loans) that will catalyse (or consolidate) revenue in a small number of sites such that the revenue, once accrued, will be re-invested into the management of those sites (or used to cross-subsidise other sites across the protected area system) and iii) learning from the diverse practices that are being implemented by various partner organisations across the country.  This third component will also lead to lessons being learned from the project via active participation of all stakeholder groups in the project design and implementation.  The information and data from M&E will be made available nationally and internationally to facilitate sustainable financing of the PA system across the country (and elsewhere in the world).

- Baseline scenario.  As would be expected, the project was developed in an environment in which there are a number of actors with ongoing programs and projects. Indeed, the project is built strongly on the lessons learned from the two ongoing UNDP-GEF protected areas projects (as described in the Partnerships tables of Section IV) – both the successes that these projects have achieved to date as well as the barriers and issues that the projects have faced.  Despite these ongoing programs and projects, in the absence of the GEF-6 funding it would be expected that: i) the government institutions involved in protected areas in the country would remain very limited in their ability to deliver the Protected Area Policy and will remain unable to fulfil their mandates, roles and responsibilities – thereby leading to the further decline of the PA system as a whole, ii) capacities and governance systems of the key stakeholders and partners, including customary landowners, would remain low and inappropriate for the demands of the protected area system of the country, iii) the protected area system would continue to be chronically underfunded, with some (but not all) protected areas succumbing to the (short term) temptations presented by the extractive industries or commercial agriculture enterprises (as has already happened), iv) protected area management effectiveness will, at best, remain at same (with the exception of those area that continue to receive sustained external support) and v) there would be no capacity to reach the Aichi targets for coverage of land and water and representation of key ecosystems in the protected area system.  In addition, the existing gender power imbalance would persist – which, in and of itself, would lead to further degradation of the natural resources and integrity of ecosystems.  In short, the GEF funding will catalyse significant change (or, in the parlance of GEF, there is significant incremental reasoning for the project).

- Indeed, in a recent assessment of the protected areas of the country, the current funding baselines for protected areas across the country, and the capacities to administer and improve revenue streams for protected areas are well below the levels required to ensure that the protected areas can effectively serve their long-term function of protecting biodiversity. The financial situation of protected areas is precarious, and those that do receive funding (of which the greater majority do not), they are highly dependent on sporadic, project-based support from development partners, donor agencies and NGOs. Given the current weak levels of regular and reliable financial support for protected areas, long-term financing to cover the basic operating costs of the protected areas in PNG is an important barrier to conserving these areas of globally critical biodiversity. The three key weaknesses in the system are: i) insufficient and unreliable revenue streams; ii) lack of capacity to secure and manage financial resources; and iii) a clear framework for investment in this sector.

- Theory of Change.  The components, as identified above, are designed to overcome the barriers through the achievement of outcomes. There are a number of assumptions that are associated with the achievement of the outcomes (see Table 2).

Table 2.  The project’s Theory of Change

| Outputs | Outcomes | Impacts and GEBs | Assumptions |
| --- | --- | --- | --- |
| Objective: To reduce the funding gap for Papua New Guinea’s protected areas in order to improve their management effectiveness, and livelihoods of their communal landowners |  | The improved management effectiveness of protected areas – with secured biodiversity, ecosystem services and ecological processes | There is clear understanding and implementation of mandates – within the limitations of the PNG context |
| Component 1: Enabling conditions for improving the sustainability of the protected area system |  |  |  |
| Initially, an institutional analysis of all organisations involved will be carried out to gain a better understanding of the roles, responsibilities and mandates of the organisations and where the potential for partnerships lie (Output 1.1). A business plan for the protected area system of PNG will be developed and implemented (Output 1.2). Finally, on the basis of the above, appropriate governance structures and capacity of partner organisations will be developed (Output 1.3). | The improved capacity and establishment and implementation of systems and structure resulting from analysis of the space and needs of the organisations involved or implications in protected area management, will lead to a better managed and more financially sustainable protected area system (Outcome One) as well as improvements in the management effectiveness of protected areas (Objective Outcome). | The improved management effectiveness of protected areas will lead to the recovery of the populations of those species that are specifically hunted and/or plants (and plant products) sustainably harvested and the integrity of ecosystems retained (long-term impact and GEB). | Institutional functionality does not impede the effective management of protected areas. Therefore, CEPA fulfils its role as a facilitator and supporter of partner organisations and communities involved in protected area and natural resource management. Cooperation and collaboration among all organisations (at all levels) will be mutually beneficial for all involved. The government will provide sufficient human and financial resources to effective support for the protected area system and the partners Financial resources that are made available are used only for intended purposes. |
| Component 2: Establishment, operationalisation and mobilization of funding for a Biodiversity Fund |  |  |  |
| The Biodiversity Fund is established according to best international practices to ensure transparency, accountability and security. A fund raising/resource mobilisation strategy to capitalise the Biodiversity Fund is developed and implemented – leading to contributions to the Fund (Output 2.3). | The establishment and operationalisation of the Biodiversity Fund (Outcome Two) will ensure secure, long-term funding for the protected area system of PNG while also reducing the funding gap required for effective management of protected areas within the system (Outcome Objective). | As above, the improved management effectiveness of protected areas will lead to the recovery of the populations of those species that are targeted for harvest and the integrity of ecosystems retained (long-term impact and GEB). | The Biodiversity Fund is independent of political interests. The fund raising/resource mobilisation is successful and guaranteed for an adequate period. The funding streams from the Biodiversity Fund become available across the protected area system for the partners (including NGOs and communities) who are the owners of the protected areas and are directly involved in protected area management. |
| Component 3: Enhanced management capacity and financial sustainability of individual protected areas |  |  |  |
| This component focuses on testing, piloting, demonstrating and learning – specifically testing mechanisms to deliver funds from the Biodiversity Fund to selected protected areas (Output 3.1); piloting mechanisms that will catalyse (or consolidate) revenue in a small number of sites such that that revenue will be re-invested into the management of those sites and possibly other sites (Output 3.2); and learning from the diverse practices that are being implemented by various partner organisations across the country (Output 3.3). National and international stakeholders will participate in the project M&E, and lessons learned from the implementation will be systemized (Output 3.4) | Mechanisms for improving the management and financial sustainability of selected protected areas will be tested and piloted. A participatory and gender balanced approach in M&E and a strong lesson learning system will allow effective adaptation of systems to provide funding to protected areas (and the partners involved in their management) and community based natural resource management (Outcome Three). Successful mechanisms will be implemented across the country and at an international level by other projects (Objective Outcome) | Through the learning, upscaling and replication, the project results will be strengthened leading to more secure and better managed protected areas (Mid-Term Impact) and restoration of fauna and flora populations and ecosystems (Long-Term Impact) | Other stakeholders have interest to learn from lessons and successful practices developed by the project The stakeholders involved in the pilots and tests come to a consensus understanding regarding the outcome of the pilots and tests |

- The project is taking the approach of building from the ground up (with the participation of the provincial, district and LLGs) – rather than adopting a top-down approach (which has been previously unsuccessful in the context of PNG) – although it acts within a national framework with full participation of CEPA.  The consensus among stakeholders is that a bottom-up approach – working with and through the land-owners and users, and local partners – is the only way in which the project will be successful in achieving its outcomes and objective in the context of PNG.

- The project strategy is developed on the basis of i) a thorough analysis of the context and situation in PNG, ii) consultation with a broad swathe of stakeholders – including extensive consultations with local communities, peoples and land-owners and users in the vicinity of the sites that will be targeted by the project. This includes the stakeholders and institutions involved in the implementation of the two ongoing UNDP-GEF projects.  Other projects and organisations that were consulted over the PPG period include WCS, TNC, WWF, the Treasury, the Provincial Governments (in East Sepik, Madang and West New Britain provinces), selected Local Level Governments (LLGs) in the vicinity of the sites targeted by the project (see Annex F for a list of the people consulted over the course of the PPG process). The PPG also included an initial stakeholder workshop and then a “pre-validation” workshop in which comments and feedback was given on a draft of the project document.

- In addition, the strategy is drawn from other PA sustainable financing initiatives that have been and are ongoing across the globe. The strategy also recognises that sustainable financing of Protected Areas in PNG will always require a level of funding support from both the government of PNG and international sources (to maintain/increase the Biodiversity Fund), in line with the global benefits of the biodiversity protection in PNG, for which the local community owners of the land in PNG cannot exclusively be held responsible.

- Selected project areas.  The project’s objective is to achieve sustainable financing of the protected areas of the country – using the Biodiversity Fund as the principal mechanism to do this. Over the project’s life (as part of Outcome Three, as described in the following section), two processes that include selected protected areas in the country will be implemented.

- The first process will be to trial the mechanism for delivering funds from the Biodiversity Fund to the protected areas (Output 3.1). This will be an inclusive process; being inclusive will be a fundamental principle of the Biodiversity Fund. Over the project’s life, therefore, funding from the Biodiversity Fund will be trialled in both those areas that are relatively well capacitated (in that their capacity has already been built through existing partnerships) as well as working out how to deliver funding to the less capacitated areas.  Therefore, for example, there has been significant investment in the Strickland Headwaters and Kaijende Highlands (through a partnership with Barrick/Porgera Joint Venture), the Kikori River Basin (with four WMAs) and Lake Kutubu (through a partnership with PNG LNG), the Yus Conservation Area (which has been developed in partnership with Woodland Park Zoo), the Torricelli Conservation Area (proposed, though a partnership with the Tenkile Conservation Alliance), the Wanang Conservation Area (with the current partnership with the NG Binatang Research Center and the Steamships Company) and the Varirata National Park (through investments by JICA and the UNDP-GEF-5 project).  Important areas such as the newly created Managalas Conservation Area will be important to support, as well as the significant areas in the west of the country (Tonda and Maza WMAs).  Other smaller community-conservation areas include those in which the UNDP-GEF-4 project has invested funds and support with a range of different partners. Thus, the mechanism to deliver funding to protected areas will be tested in these areas – as per the criteria in the Biodiversity Fund’s Operational Manual (see Output 2.2 and Box 1); however, this will not offset the funding from these existing supporters or partners – indeed, provision of funding from the Biodiversity Fund will be conditional on demonstrated maintenance of the support from the original partners and supporters.

- The second process will be to invest in a small number of protected areas with the specific objective of catalysing a revenue-generating mechanism, and that this revenue will, thereafter, be used within the given protected area (Output 3.2). The project will work in three pilot sites: the sites were specifically selected because there is a significant potential for the sites to generate revenue – or there was an already existing revenue stream - which needs to be harnessed for protected area management (for definition of which, see Box 1).  They are: i) the Sepik Wetlands, ii) Mt Wilhelm National Park and the surrounding community-owned areas, and iii) Kimbe Bay.  In addition, once the processes in these three selected sites are underway, the project (and the Biodiversity Fund, once operational) shall continue to invest in other protected areas to catalyse further streams of revenue. In some areas, the role of the project (and, ultimately, the Biodiversity Fund) is to facilitate and mediate among stakeholders and users of the ecosystem services being provided by protected areas such that those users agree to pay for the use of the ecosystem services (thereby fulfilling a payment for ecosystem services scheme).

Box 1. Defining protected area management. Throughout this document, the term “protected area management” is used to define activities that are carried out in any given area and which may be funded by either the project or the Biodiversity Fund or both. However, the Biodiversity Fund will be inclusive, offering the possibility of funding to all protected areas in any stage of its development; in doing so, there is recognition of a number of key points: i) that what is defined as “protected area management” in one area will not be equal or equivalent to “protected area management” in any other area, ii) that the protected area system of PNG spans areas that are managed by the state (although concessioning areas owned/managed by the state should be considered – see Output 1.2) as well as the majority that are owned and managed by the communities, iii) that the communities are turning to protected areas as a legal mechanism to protect their land and resources (from all the forces that threatens the land and resources thereon) even though the primary motivation for establishing a protected area is not necessarily biodiversity conservation, iv) that it is for each protected area to define the strategy (with targeted objectives and outcomes) and activities that will lead to achievement of those objectives and outcomes – and, in community managed areas – these may include sustainable livelihood options, sustainable land use planning, delivery of social services with linkages to the Ward and LLG Development Planning processes (and, indeed, “traditional” protected area management practices such as boundary demarcation, community scouts or rangers who “enforce” regulations, the establishment of management committees – all may be counterproductive if not damaging in these circumstances).

Figure 4. A map illustrating the Sepik Wetlands - indicating the Upper, Middle and Lower Sepik areas.

- The Sepik Wetlands.  The Sepik Wetlands cover an area of 2.4 million ha and are associated with the Sepik river as it meanders across a broad floodplain towards the sea.  There are numerous communities that live within the wetland – including along the river itself.  The wetlands and river are of importance in terms of biodiversity (although relatively little has been done to identify the biodiversity of the area) and ecosystem services (with the local communities being wholly dependent on natural resources for their livelihoods and well-being – as well as for transport).  The system is threatened by i) climate change – with impacts on water levels, vegetation and ecosystem services; ii) the Frieda River Mine in the watershed of the Sepik river – the feasibility studies for which are completed and have been submitted to the GoPNG and which has all the potential and real impacts associated with such a project; iii) upstream logging operations – which not only denude the upstream watershed but also use the Sepik river itself for transport; iv) the long-term impacts of introduced fish species – which have led to significant negative impacts on the vegetation (and especially the floating mats within the wetlands) and to indigenous fish populations, v) unsustainable harvesting of crocodile egg for individual benefit, and vi) other impacts such as population growth among the peoples living within the wetlands.  From the perspective of the project, there in one protected area – the Hunstein Range WMA – associated with the Sepik wetlands – but it abuts onto the south of the wetland.  However, although the area is going through the process of being recognised as a Ramsar site, currently, there is no protected area within the wetland.  This means that the project will work to establish a mosaic of community-managed protected areas through the wetland.  In terms of financial sustainability, the area has two mechanisms for generating revenue that can be used for the management of the protected areas – as well as bolstering the livelihoods of the people living in the area. Both of these mechanisms currently exist – but there are significant issues with them (most associated with governance and gender issues that extends to gender-based violence).  First, there is tourism – which is primarily associated with the annual Crocodile (or pukpuk) Festival and the guesthouse in Wagu (associated with the Hunstein Range WMA).  Second, there is an elegant linkage (or chain) between the harvest of crocodile eggs (and, to a lesser extent, live crocodiles) by peoples living in the Sepik wetland, and the production and sale of high-end leather products.  There are also other natural resources (including, for example, raw tree bark and shrubs - “massoy” and “eaglewood”) that are harvested for trade in various markets; however, the value-chain analysis and value-addition for these other resources has not been carried out.

- Mt Wilhelm National Park. Mt Wilhelm is the highest peak in PNG, ascending to 4,509m asl.  The area above approximately 3,200m asl is protected as a national park (Mt Wilhelm National Park) with the lower reaches of the massive falling under customary ownership.  As with the Sepik Wetlands, there is the potential for demonstrating two mechanisms for generating revenue.  As above, the first is tourism associated with the trekking and climbing of the peak of Mt Wilhelm itself (predominantly within the existing National Park), but tourism is currently limited by poor access and facilities.  The second builds on the success of the financing mechanism for the Wanang MWA: using research fees and support for research projects including logistics, locally trained paraecologists, and baseline biological data.  The proposal emerges from the Binatang Research Centre (BRC) with the intention to build a research programme to explore the ecological cline from 200m asl to the summit of My Wilhelm (at 4,509m asl).  The transect to explore this cline is already established but investment is necessary for some infrastructure and local expertise (Para ecologists) to facilitate the research.  This will, thereafter, pave the way for researchers to visit and work in the area – and pay research fees which will then contribute to the protection and management of the area.  Part of the work will also include the establishment of community-owned conservation areas that will protect the areas surrounding the transect; these community conservation areas will abut to the national park – thereby creating a contiguous, large protected area.

Figure 5. The nominal area for Mt Wilhelm National Park; this map does not illustrate the adjacent area that would be adjoined to the national park.

- Kimbe Bay. Kimbe Bay lies on the northern side of the island of New Britain (and, probably more by a quirk of history rather than by design, off the province of West New Britain).  It is part of the Coral Triangle and is known to harbour more than 400 species of hard coral and an estimated 900 species of fish.  Although many of the local communities have some relationship with marine resources – and some communities are more dependent than others (e.g., the people living on islands have fewer alternatives and are, therefore, more dependent on marine resources) – the people are less dependent today than would be otherwise expected.

Figure 6. Kimbe Bay, indicating the proposed boundary of the protected area - but also indicating the existing LMMAs and other terrestrial protected areas.

- As with all of the Sepik Wetlands and Mt Wilhelm, there are two potential financial mechanisms that may be demonstrated within the Kimbe Bay area.  The first is tourism.  This is already well established but the realistic, de facto situation is that tourism in Kimbe Bay has protected only Kaula Island – which is a tiny part of this ecosystem.  The remainder of the area remains largely unprotected (with the exception of those areas that are protected by default in that they are either inaccessible or they remain unknown) – even though there are 14 LMMAs across the bay (although the LMMAs are generally confined to inshore reefs and adjacent shore features including patches of mangroves) but they are not being managed.  The second (potential) revenue generating mechanism is research – in the same way as the BRC has been generating finance for the Wanang WMA and is proposing that research fees be the principal mechanism for financing the community conservation areas that abut to Mt Wilhelm National Park.  However, despite the fact that Kimbe Bay has been a focus for research for the past two decades, unlike the philosophy and approach of the BRC, the research institutions have not contributed financially to the protection of the area.

Table 3: Summary of biodiversity information of targeted PA pilot sites including KBA criteria.

| No. | Site | Site description | Key biodiversity values | Area (Ha.) | IBA criteria | KBA criteria |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Sepik Wetlands | The Sepik Wetlands is associated with the Sepik river as it meanders across a broad floodplain towards the Bismark sea. This site is going through the process of being recognized as a Ramsar and World Heritage Site. It has one protected area – the Hunstein Range WMA (220,000 ha) is associated with the Sepik wetlands. | Sepik River Basin is home to a number of rare and endemic globally threatened species including Papuan eagle (Harpyopsis novaeguineae) Goodfellow's tree-kangaroo (Dendrolagus goodfellowi), grizzled tree-kangaroo (Dendrolagus inustus) and Tenkile (Dendrolagus scottae) are found commonly in the forest. One of most valuable timber species on the island of New Guinea is Kauri pine (Agathis labillardierei) and also includes the type locality of the Klinki pine (Araucaria hunsteinii), largest of the world's Araucarias. This area contains two Global 200 eco-regions, three endemic bird areas, three centers of plant diversity, and only survey site for the saltwater crocodile (Crocodylus porosus LC) under CITES. | 2.4 million hectares (targeting 1.5 million ha only) | A1, A2, A3 | A1, B1, B2, B3 |
| 2 | Kimbe Bay | Kimbe Bay is part of the Bismarck Sea under the Coral Triangle Initiative. There are 14 Locally Managed Marine Areas across the bay (although the LMMAs that are generally confined to inshore reefs and adjacent shore features including patches of mangroves. | Kimbe Bay is in the Coral Triangle biodiversity hotspot and has the greatest species richness of fishes (ca. 1600 species in PNG) in the Pacific. It harbors more than 60% of coral species found in the Indo Pacific region, home to the Sperm whale (Physeter macrocepahlues), listed as Vulnerable (A1d) on the IUCN Red List and reproductive area for the killer whale (Orcinus orca). It is also observed as the feeding ground for four marine species of elasmobranchs scalloped-hammerhead shark, Sphyrna lewini; grey reef shark, Carcharhinus amblyrhynchos; manta ray, Manta birostris; and blue-spotted ray, Dasyatis kuhlii) and four species of fin-fish (yellow-fin tuna, Thunnus albacares; big-eye tuna, Thunnus obesus; IndoPacific sailfish, Istiophorus platypterus; and sunfish, Mola mola); and common bottlenose dolphin (Tursiops truncatus), Indo-Pacific bottlenose dolphin (Tursiops aduncus), pantropical spotted dolphin (Stenella attenuata), Risso’s dolphin (Grampus griseus), short-finned pilot whale (Globicephala macrorhynchus), and Cuvier’s beaked whale (Ziphius cavirostris). | 1.33 million hectares | A1 | A1 |
| 3 | Mount Wilhelm- Wanang WMA (Bismark Range Transect) | Mt. Wilhelm (4509 m asl.) is the highest peak of Papua New Guinea. It is part of the Central Cordillera running over thousand kilometers accross the island of New Guinea. Uplifted during the collision between Australian and Pacific tectonic plates, it is one of the great tropical mountain ranges, harbouring exceptional biodiversity. Mt. Wilhelm massif harbours a complete elevation range of undisturbed rainforests from lowlands at 200 m asl. to treeline at 3700 m asl. The transect comprises eight stations spaced from 200 to 3700 masl. at regular elevational increments of 500 m. It is 41 km long. A series of community conservation areas to be established adjacent to the Mt Wilhelm National Park. | Mt Wilhelm, together with adjacent but geologically younger Finisterre Mts., belongs among the world’s seven regions with the highest plant diversity. With the number of plant species per 10,000 km2 compared to the top category (>5,000 species). Mt. Wilhelm transect harbours a large proportion of the overall biodiversity found in Papua New Guinea, including 52% of PNG bat species, 51% of the mainland PNG bird species, 46% of NG Ficus species, 27% of PNG butterfly species, and 15% of PNG frog species | 817 ha plus the additional adjacent areas | A1, A2, A3 | A1, B1, B2, B3 |
| Total |  |  |  | 2.831 million ha |  |  |

- The project aims to build on the previous proposal for a protected area (of 1.33 million ha) that encompasses the entirety of Kimbe Bay.

Table 4. The selected pilot sites (Output 3.2).

| Area | Protected Area | Targeted area (ha) | Potential Financing Mechanisms |
| --- | --- | --- | --- |
| Sepik Wetlands | To be established over the project’s life as a mosaic of discrete community conservation areas that will, ultimately, coalesce to form a larger protected area encompassing the entire Sepik Wetlands | 1.5 million ha | 1. Tourism – currently this is focused on the Crocodile (or pukpuk) Festival and the small guesthouse in Wagu but there is potential for further tourism development 2. The harvest of crocodile eggs (and a limited number of live crocodiles) 3. The harvest of a number of other natural resources (including, for example, massoia derived from the bark of the Massoia tree Cryptocaria massoia and eaglewood or ghara) In addition, there may be other possibilities such as PES (for example, contributions/fee structures from upstream users – e.g., the Frieda mine – who impact the Sepik Wetlands). |
| Mt Wilhelm & surrounds | A series of community conservation areas to be established adjacent to the Mt Wilhelm National Park | 817ha plus the additional adjacent areas | 1. Tourism – currently this is focused on trekking and climbing Mt Wilhelm. 2. Research – building on the experiences of the BRC in the Wanang WMA, research along the ecological cline (from 200m – 4,509m asl). Instead of directly taxing researchers, research initiative will be encouraged to support capacity building of budding researchers, creating jobs for local community members. In addition, there may be other possibilities such as PES (specifically watershed protection) provided by conservation areas in the area, and for measured/sustainable harvesting of plants with medical properties and other commercial/food value. |
| Kimbe Bay | Focused on the larger marine area (previous proposed by TNC) but including the established (and yet to be established) LMMAs and other unrecognised protected areas and zones (e.g., Kaula Island) | 1.33 million ha | 1. Tourism – building on the existing tourism (primarily diving but also sport fishing) but there is potential for further tourism development |

# Results and Partnerships

- Expected Results.  The section above describes the strategy and theory of change. The long-term goals – and hence the long-term impacts or global environmental benefits (GEB) – to which the project will contribute (in a 10-15-year timeframe are:

  - The population of rare and endemic globally threated flora and fauna specie in the KBAs of Sepik Wetlands are maintained at the current level or increased through increased level of protection. These include: Papuan eagle (Harpyopsis novaeguineae) Goodfellow's tree-kangaroo (Dendrolagus goodfellowi), grizzled tree-kangaroo (Dendrolagus inustus) and Tenkile (Dendrolagus scottae).

  - The integrity of the ecological cline of Mt Wilhelm and surrounding areas (from 200 – 4,500m asl) remains intact, providing ecosystem services and protecting biodiversity that includes 52% of PNG’s bat species, 51% of PNG’s mainland bird species, 46% of NG’s focus species, 27% of butterfly species and 15% of PNG’s frog species.

  - The ecosystems of Kimbe Bay are retained in healthy condition, with an increase in biomass of target and indicator fish species (1600 species including vulnerable species such as Sperm Whale (Physeter macrocepahlues)), and coral (more than 60%), seagrass and mangrove where they have been reduced, degraded or lost; the system will be better able to adapt to climate change as a result.

  - A Biodiversity Fund is fully constituted, operationally functional, and strategically focused on delivering long-term funding to support the establishment and management of the protected area system in PNG: i) the total annual replenishment of the Biodiversity Fund from multiple recurrent income sources reaches at Year 4 more than US$1.5m per annum; and ii) the sinking portion of the Biodiversity Fund attracts at least US$12m for earmarked project-based grants.

  - The Financial sustainability of the PA system in PNG increased from the baseline of 9% to 58% (derived from the Obj. 1. Section III Part III of the Financial Scorecard).

  - The average METT scores of the three new designated protected areas increase to at least 20% higher than the baseline; and

  - The number of individuals [of whom 65% are women and youth] living in rural villages in and around PAs who directly benefit from the Biodiversity Fund exceeds a cumulative total of 1,200 [780 of whom are women and youth] by EOP; improved socio-economic status allows people to adapt to climate change.

- The project will contribute in the mid-term (5-10 years) to the above long-term impacts by reducing threats to ecosystems (depicted as midterm impacts in the Theory of Change): Increased and more sustainable financing, decreased unsustainable use of natural resources.  Threat reduction will, in run, be achieved through the following objective level outcomes:

  - Improved protection of key ecosystems (EOP target: significant increases in management effectiveness in the three selected pilot PAs as measured using the (proposed adaption of the) METT (see Annex H) from the baseline; and over 1.5 million ha of terrestrial (Sepik Wetlands and Mt Wilhelm) and over 1.33 million ha of marine habitat (Kimbe Bay) under improved natural resource management) – equating to increased PA coverage (2.83 million ha); overall improved ability to adapt to climate change

  - Demonstrable implementation of the PA Policy and regulations, and the PA Bill (once enacted)

  - Institutional transformation leads to improved effectiveness and efficiency, with improved transparency, accountability, governance and M&E systems.

- The objective level outcomes will, in turn, be achieved during the project’s lifetime through three outcomes (seven years):

  - Outcome One: Improved enabling conditions deliver a better managed and more financially sustainable protected area system, as indicated by:

    - Actors (both state and non-state) are demonstrably fulfilling their roles, responsibilities and mandates with respect to protected area management and financing;

    - A business plan for the protected area system of PNG is being implemented and, as a result, the funds being expended per year has grown by 75% above the baseline level as measured by the Financial Sustainability Scorecard;

    - Key actors have appropriate governance and management structures in place, and capacity has been developed such that protected area management effectiveness has quantifiably increased as demonstrated by the Capacity Development Scorecard.

  - Outcome Two: A Biodiversity Fund for Papua New Guinea established and operationalised, as indicated by:

    - The Biodiversity Fund is operationalised as a sinking fund consisting of: USD 5 million initial capital from GoPNG, at least USD 1.5 million annual revenue from recurrent income sources enabled by innovative GoPNG fiscal instruments, at least USD 1 million through the fund raising/resource mobilisation strategy, and GEF funds (USD 2.7 million) disbursed as  grants via proposals approved by the Biodiversity Fund secretariat

    - The overall funding gap, as measured by the Financial Sustainability Scorecard, has shrunk from the baseline of USD 2.12 million/annum to USD 0.6 million/annum by the EOP.

    - At least 12 protected areas across the protected area system of PNG are receiving funds from the Biodiversity Fund, partly as grants and partly as loans when local revenue is expected as a result of the investments made

  - Outcome Three: Mechanisms for improving management and financial sustainability of selected protected areas tested and piloted to improve knowledge and learning, as indicated by:

    - Revenue streams from at least three protected areas are being demonstrably used for management (including protection of the area) and longer turn revenue generation

    - Five project lessons learned by the project through participatory M&E are used in other conservation projects such that they are working to finance protected areas sustainably and promote community-based natural resource management nationally and internationally

    - At least ten national and international organisations and academic institutions participate in the project’s M&E and related research (thereby contributing to dissemination of the lessons learned and enhancing revenue generation for the PA management and the communities’ livelihoods, based on unique local opportunities and sustainably marketable local products)

- To ensure achievement of above Outcomes the project will deliver following key Outputs (project products and services):

Outcome One: Improved enabling conditions deliver a better managed and more financially sustainable protected area system

- This component will focus on i) ensuring a clear understanding among relevant institutions and organisations of their specific roles in protected area management, including how they are financed, ii) developing a business plan for the protected area system of the country, and iii) building the capacity and governance systems within those organisations that have a specific mandate and/or role and responsibility in the management of protected areas – relative to their specific mandate and needs.

Output 1.1: A better understanding of the roles and responsibilities of each organisation, institution and sectors of society involved in PA management and PA financing is achieved

- The mandate of the various organisations – particularly the government entities – with respect to the protected areas of the country is not clear (see Section II). This is because of the rather unique nature of the customary land tenure system within the country – with the majority of protected areas being owned (and in principle managed) by local communities. The closest government structures to these customary owners of the land are the wards and LLGs.  As a result, there is a need to ensure that each organisation is clear about their mandate, with their roles and responsibilities within the sector.

- The project will carry out a participatory and facilitated assessment, and mapping of the institutions and organisations that are involved in protected area management and financing to determine the roles and responsibilities of the institutions and organisations (see overview of technical consultancies in Annex C).  The principle of this work is to put the protected areas at the heart of the system and to determine how the different state and non-state partners can serve them to ensure that they achieve their targeted conservation and livelihood/well-being outcomes.  In the case of CEPA, the work will also include determining how best it may be structured to fulfil its identified roles and responsibilities – including i) their mandated role in collecting fines and imposing sanctions in cases of violations of environmental laws and regulations (particularly with respect to protected areas and with respect to violations by extractive and agro-industry parties) and ii) legal support for communities against threats from developers – including other government agencies.  Thus, there is a need to shift CEPA’s role of being the facilitator and support provider to the actors that work at the level of the protected areas.

- The other key set of organisations to include in the assessment and mapping are the Wards and Local Level Governments (LLGs) – as these really operate at the level of the protected areas and the community owners of the land – and how they need to be supported by the Provincial Governments in order to support the protected areas.  Finally, there is a need to include – and hence understand – the roles that different sectors of society at the grassroots or community level have in natural resource management and, by extension, in protected area management. This includes different age groups, different genders, different ethnic or clan structures.

- This work will be transformative. The result will be a clear understanding and mapping of all organisations’ roles and responsibilities with respect to protected area management and financing; the mapping will also include how different genders and ages are included in the system (including within the government and non-state actors).  The stakeholders will be better equipped to understand their capacity development needs because they will understand where their capacity is limited with respect to those roles and responsibilities. The institutional mapping process will also identify the gaps within the system and, as a result, it will determine which organisations are best positioned to fill those gaps. One noticeable gap, for example, is the absence of legal support that CEPA should be providing to stakeholders involved in either existing or potential protected area.

- There will be a focus on CEPA’s roles and responsibilities – including the terms of reference/job descriptions and performance evaluation processes for all staff.  Again, the project aims to be transformative – to transition CEPA from being an organisation that wishes to enforce to one that is supportive and provides services to its constituents and clients.  The example given above – providing legal support and services such as conflict mediation to the land owners and land users, including legal protection from extractive and commercial agricultural industries – is a good illustration of this.  Other aspects of CEPA’s support and services that they should be providing include facilitating and coordinating, and ensuring that there is no duplication of effort. The same applies to the Wards and LLGs who operate at the level of the protected areas themselves (as they are in a position to represent the expressed, urgent needs of communities with respect to basic social services, including quality education, health care and family planning that are not being provided adequately – thereby hampering sustainable development and maintenance of protected areas).

- Once the mandate mapping is complete, within CEPA and the LLGs, the process will also map out the roles, responsibilities and expectations of each of the employees – and what they are expected to do on a day-by-day basis – relative to the human and financial capacity of those organisations.

- The work will be positioned firmly in the socio-political and economic realities of PNG; it will be firmly positioned within the social realities of PNG – explicitly acknowledging that the communities are the principal land owners and land users, and that, as a result, they have a pivotal role to play in the management of protected areas.

- The work will also recognise and identify the partnerships that will be needed for the effective and efficient management of protected areas.

- The work will be overseen by the Project Manager – working together with a team that will be contracted to carry out the analysis.  Finally, the team associated with this work will also be contracted (within the same contract) to carry out the capacity development work indicated below (see Output 1.3).

Output 1.2: A business plan for the PA system of PNG is developed and initial implementation supported

- Building on the analysis of the institutional and organisational space, and building on the achievements of the current UNDP-GEF-4 and GEF-5 projects, the project will work with stakeholders and partners to develop – and fund the initial implementation – of a business plan for the PA system of PNG.  This will be a medium-term business plan (5 year) with a shorter term (three year) action plan and associated one-year workplans. Given the proposed length of the project, it is envisaged that one five-year business planning cycle will be complete and the subsequent five-year business plan developed and implementation commenced before the project is closed.

- The business plan will build on the financial data collected over the course of the PPG process (including the financial gaps that have been identified). There will be two aspects of the business plan: i) a detailed analysis that identifies the financial requirements for the existing (and projected expansion of the) protected area system, and the realistic funding needs for effective management of the system (both existing and expanded within the projected five-year period of the business plan) and quantifies the funding gaps; and ii) a detailed analysis of viable revenue-generating options for protected areas (linked, in part, to the pilots, demonstrations and case-studies in this project – see Outcome 3). The business plan will focus on generating revenues from both conventional (e.g., budgetary allocations, overseas development assistance, user fees) and innovative sources.

- From the outset, the business plan will make the business case for an increase in government funding of protected areas (and see also Output 2.3); this will build on the 10-year PA Policy Implementation Plan which seeks to secure government financing of PNGK 20 million; and this is partially fulfilled in the co-financing pledges that the government has made for the project. The business plan will also consider aspects such as branding the protected area system, and developing related marketing and communication materials and media as part of the process to build the business case.  This is on the basis that there are no protected area systems in the world that are not dependent, at least to some extent, on the state budget and in some countries, the state entirely supports the protected area system.  Thus, working with national state organisations – and primarily CEPA – the project will work i) to advocate for an incremental increase of state budget allocations for the protected area system; and ii) to secure annual state budget allocations from the Public Investment Program (PIP) for the protected area system.

- While noting that Papua New Guinea is far from “conventional” in terms of its protected area system (see Section II), the “conventional” sources that may be explored include building on the tourism activities that already exist and for which some form of user fees are applied (e.g., recreational diving, sport fishing, bird watching, hiking, cultural tourism in various places in the country – including in all three of the principal demonstration sites, see Output 3.2 – and one of the outputs here, within the overall Business Plan, will be a tourism and recreational strategy and action plan for the protected area system), the efficacy of introducing user fees, and tourism and recreational concessions in protected areas will be reviewed.  Pricing strategies for products, services and facilities to be provided in/by protected areas will be proposed – noting that this also extends to ecosystem services other than tourism as well (e.g., watershed protection, provision of clean water, etc.).

- The business plan will build on the biodiversity offset mechanism (that is currently being developed with UNDP-GEF 4 & 5 support). In addition, any relevant information such as valuation studies or benefit-cost analysis for site-specific protected areas as well as the forthcoming National Biodiversity Strategy and Action Plan and the Sixth National Report to the UN Convention on Biodiversity that will be completed in December 2018 will also inform the development of the Business Plan.

- The business plan will also explore the possibility of developing concessions and contracts – both within protected areas but also for the management of entire protected areas. This is akin to the sub-contracting of management that happens elsewhere in the world (for example, the contracts under which African Parks works in a number of different countries in Africa).  However, this may be applicable only to those protected areas managed by CEPA and, in the context of PNG, may not be applicable to the community-owned and managed protected areas.

- With the exception of those protected areas that are managed by the state (and especially CEPA), the development of revenue generating systems in (community-owned) protected areas will be, by their very nature, done on a case-by-case and individual protected area basis. The revenue-generating systems are likely to be very different in different areas (and may range from tourism, the products of sustainable agriculture, to harvested natural resources). These are likely to be linked to the development plan for any given community-owned protected area – which should indicate how the revenue generated may be used at a community (and thus not only individual) level (e.g., for the development of social services, the development of sustainable livelihood options, the development of sustainable land use plans – and how these are linked to the LLG Development Plans and District Development Plans).  When considering the business cases within community-owned protected areas, the business plan will be sensitive and responsive to different groups within society – but especially those people that are marginalised as a result of the androcentric and youth-age discriminatory culture dominating almost every community within the country.

- The project overall, will ensure that the environment is enabling to allow all protected areas to develop and implement whichever revenue generating mechanism is appropriate and best (e.g., by facilitating the ongoing development of the enabling legislative, regulatory and policy frameworks – see Output 2.1)

- The innovative sources that will be explored in detail – to determine their technical and legal feasibility – include (but are not limited to):

  - Biodiversity offsets from large-scale developments for expanding, and improving the management of, the protected area system, building on the existing examples in the country – see Section II but expanded to target medium- to large-scale oil and gas, and mining developments and activities; oil palm plantations and their set aside of HCV and HCS; and, in principle, this could be expanded to other developments as well;

  - Payment for Ecosystem Services (PES) – building on the studies that have already been carried out and the relationships that have already been established with PNG Power (by the GEF-4 and GEF-5 projects), the potential and feasibility for PES schemes (including REDD+) will be determined and expanding to Eda Ranu and, potentially, other public services (e.g., targeted ecosystem services will include flood protection, water catchment supply, soil protection, coastal erosion protection and hydro-electric power) provided by protected areas;

  - Environmental fees, taxes and fines – a portion of which should be earmarked for protected area management (for example, a round log tax from logging operations that is mentioned in the draft PA Bill);

  - Environmental branding and certification schemes (with the potential for sustainable management/fair trade product taxes) for products linked to protected areas (e.g., building on the example provided by the coffee harvested from the Yus Conservation Area and expanded to targeted products such as eaglewood, coffee, vanilla, bird eye chili and sea cucumber).  Indeed, the project will be directly supporting this process with the existing system of exporting saltwater crocodile skins from the Sepik Wetlands (see Output 3.2)

  - Contracting the management of protected areas to third parties (as suggested above).

  - Providing conserved ecosystems as basis for biological research, supported by locally trained field technicians, field accommodation and lab space, and – on the government level - mechanisms for research and export permits could be another such mechanism; already tested in Wanang but still innovative in PNG and internationally. However, this approach should not be seen as means of increasing revenue stream by ‘taxing’ researchers, instead to support capacity building of young researchers on globally unique or important ecosystems, and alternatively create job opportunities for local community members by facilitating research initiatives and establishing rules.

- The business plan will, therefore, provide the overall strategic direction (with associated goals, objectives, outcomes and targets) and guidance to improving the financial sustainability of the protected area system. It will also act as mechanism for standardising and coordinating the funding efforts, and aligning the performance accountability within the scope of each institution and organisation (as described under the institutional analysis under Output 1.1).  It will also be linked to and in synergy with the fund raising and resource mobilisation for the Biodiversity Fund (see Output 2.3).

- The aim will be to produce the business plan within the first 18 months of the project implementation. The development of the Business Plan will be led and facilitated by the project’s Chief Technical Officer (CTO). This will be developed in an inclusive and participatory way. Similarly, it will be adopted by consensus by those stakeholders who have been involved in its development. Once adopted, the project will support the initial implementation of the business plan, again led by the CTO and, as such, the implementation of the business plan will be interlinked with the development of the business plan. Throughout the process of development of the business plan and through its subsequent implementation, the project’s role will be to facilitate the consultation and negotiations with counterpart government institutions, agencies and organisations as well as non-state actors – thereby facilitating, in turn, the ongoing development of the enabling legislative, regulatory and policy frameworks for these innovative sources to be realised, and for the targets within the business plan to be achieved.

- Finally, the project will support an independent review of the business plan and its implementation at the end of five years – with the aim of developing the second edition of the Business Plan before the end of the project.

Output 1.3: The capacity of relevant organisations and institutions developed to deliver improved protected area management and governance, transparency and accountability, and financial management across the country

- Having first analysed and mapped the institutional and organisational space, and identified the roles and responsibilities of all people at the different levels and in both governmental and non-state organisations (Output 1.1), and identified the capacity needs within the business plan for the protected areas (Output 1.2), and as an iterative and adaptive process as a result of the testing, piloting and learning processes of Outcome Three, the project will be in a position to develop the capacity of the project partners.

- There are a number of fundamental aspects to this process:

  - The capacity development process will target all the stakeholders and project partners (including those involved in Outcome Three): thus, the community land-owners and land users will be specifically targeted for capacity development under this Output – especially during the process when they receive grants and/or loans from the Biodiversity Fund.

  - At the level of the protected areas, the people (and especially the communities that are owners and users of the land and resources – with their partners) will need to develop their capacity to design, manage and implement revenue generating as well as environmental protection activities and projects, and developing their skills and capacities to handle fair (gender and age) distribution of tasks, management/protection roles, and benefits sharing.

  - The capacity development process will be tailored according to the analyses indicated above (Outputs 1.1 and 1.2).  As such, it will be pragmatic and efficient, and it will be responsive to the actual needs of the organisations involved  in protected area management, and build on to some of the capacity development initiatives under the ongoing GEF-5 project

  - Financial management capabilities will be developed, as needed and as identified in the above processes – thus, including: financial support services, staffing, equipment, communications infrastructure, systems and skills development. Where warranted, this will extend to developing institutional and individual capacities in: a) financial policies and procedures; b) medium-term financial and business planning; c) annual budgeting; d) financial controls (including: budget and budgetary control; books of account; accounting process; revenue process; purchasing and expenditure process; fixed asset management process; stock management process; payroll management process; bank account management; financial reporting; internal controls and audit; risk management and procurement); e) accounting systems; f) financial reporting and auditing, and g) detecting and combatting corruption and embezzlement. For some targeted financial and administrative staff, this will include a skills development and training program, including: professional short-courses; professional mentoring; inter-institutional exchange programs; and part-time studies.  Ultimately, this will ensure that the protected areas and their partners are in compliance with the requirements and regulations of the IPA, IRC and/or any other government department.

  - Where organizational restructuring is required, the project will support this process, especially within CEPA (as determined through the process in Output 1.1).

  - Finally, because governance is a fundamental aspect of protected area management, the project will emphasise developing and implementation of governance systems with all the project partners – including the need for systems that lead to transparency and accountability.

- As noted in the MTR of the GEF-4 project (and in Leverington et al. 2017), there is a challenge with the use of the METT in PNG – especially in community-owned and managed areas. The MTR of the GEF-4 project recommended amendment of the METT to something that was more appropriate for the context of PNG. What was done by Leverington et al. (2017) to this end was extremely valuable – but they tried to stay true to the original METT and by doing so, the adapted METT did not include a number of parameters and factors that are critically important for the success of community conservation areas.

- In response, the project will develop and institutionalise an innovative METT in the first year of the project that would be wholly appropriate for the community-owned areas across the country and which would include parameters and factors such as measures of natural resource management effectiveness, enterprise, security, socio-economic development and well-being, access to services, gender, capacity and governance (as well as many of the aspects included by Leverington et al., 2017).  These measures of governance will be specifically adapted from other community-based governance measures (as developed in other countries) and incorporated into an adapted “METT for PNG” (See Annex H). One specific example to refer is from a UNDP-GEF project in Brazil where they have developed a modified METT for use with indigenous territories

- The adapted “METT for PNG” will be used for all protected areas supported within this project as well as those supported by the Biodiversity Fund.  This, then, is an opportunity to develop something that is unique, designed specifically for the context of PNG, innovative and has significant scale-up potential in community conservation areas across the globe.

- As indicated above, the contract of the team that will carry out the institutional and organisational analysis (under Output 1.1) will, under the same contract and in concert with the Project Manager, carry out this capacity development work. Both the MTR and TE for the project will review evidence of improved capacity and how trainings and any other capacity development processes are actually being used on a regular basis. This will be primarily for the actors at the protected area level including CEPA.

Outcome Two: A Biodiversity Fund for Papua New Guinea established and operationalised

- The strategic focus of Component Two is to catalyse the establishment, capitalisation and operationalisation of the Biodiversity Fund for PNG. The aim of the Biodiversity Fund is to contribute to conservation of biodiversity within Papua New Guinea while contributing to the livelihoods and well-being of people living within and surrounding protected areas across the country. The Fund will do this by contributing to the financial sustainability and effective management of the protected area system of Papua New Guinea (noting the specific use of “protected area management” in this context – see Box 1).  As such, the Fund will: i) reduce the funding gap required for the protected area system of the country, ii) provide long-term and stable funding for management and expansion of protected areas, iii) contribute in a sustainable way to the livelihoods and well-being of people living within and surrounding state-managed protected areas, and to those communities who are land owners and users of all other protected areas, and iv) contribute to the establishment of a PNG Biodiversity Survey (including the training of national post-graduate students).

- The establishment of the Biodiversity Fund will draw off lessons and best practices, both from within PNG and also from around the globe. As indicated above (see Section II), this is not the first time that PNG has set out to establish a conservation/biodiversity fund: previous efforts included the establishment of the Mama Graun Conservation Trust Fund. There have been other efforts to build trust funds in other sectors in PNG – ranging for example, from a Sovereign Wealth Fund to the Fund established as a result of the Ok Tedi mine disaster, as well as trust funds for the education, health and infrastructure sectors. There have been successes and failures and there are number of lessons that can be and have been derived from these processes. All key stakeholders who have been consulted stipulated that the Biodiversity Fund should be built on two fundamental principles: i) it is immune from political interference, and ii) it is secure from embezzlement or corruption. One of the lessons from the 2001 – 2006 WB/GEF Forestry and Conservation Project was that “projects in difficult governance environments … benefit from formal assessment of … commitment using some form of social mapping”.  At the level of the communities living in rural areas across the country, there is a strong desire to seek legal protection for their land and resources in the face of exploitation pressures from logging and industrial agriculture as well as other extractive industries (specifically oil and gas, and mining).

- Furthermore, on the basis of international best practice for Conservation Trust Funds, the Biodiversity Fund should be an independent entity. The establishment of the fund and its governance arrangements – along with fund operations – will conform to the Practice Standards for Conservation Trust Funds (Spergel & Mikitin, 2013) and align with key recommendations of the GEF for the effective establishment of national trust funds. In addition, while undertaking the work on establishing the BF, UNDP and project team will reach out Caribbean Biodiversity Fund and Micronesia Conservation Trust where both the organizations have significant experience in the SIDS context.

- The Biodiversity Fund will be underpinned by a number of key aspects, including (but not limited to):

  - The Fund is being established in the knowledge that a fully functional, successful fund and protected area funding mechanism would bring significant recognition to Papua New Guinea, and transfer political capital and leverage to the Government of PNG on national and international stages.

  - The objective is to have a secure, accountable and transparent funding mechanism.

  - All people associated with the oversight, administration, management, implementation and/or operation of the fund must declare all conflicts of interest and sign a code of conduct that governs these aspects of the Fund.

  - The monies of the Fund as applicable will be invested in “ethical” investments in line with GEF and UNDP standards: these are investments that will not in any way lead to any form of environmental degradation, social stress and/or hardship either within Papua New Guinea or elsewhere in the world.  This means that the funds will not be invested in the following sectors (to which others may be added): fossil fuels, arms, industries exploiting child or slave labour, industrial agriculture with a demonstrated negative impact on the environment.

  - The Biodiversity Fund will finance the establishment and management of key protected areas in Papua New Guinea such as associated areas in the Sepik Wetlands, Mt Wilhelm and Kimbe Bay. Key activities are intended to support processes that will build upon existing conservation and management activities while developing or upscaling sustainable revenue generating activities within and surrounding areas. Engendering community-based natural resource management will also be considered for support. This may include population surveys to ensure sustainable offtakes, strengthening traditional management systems (i.e. no take zones, rotational use) to mainstream biodiversity friendly practices in natural resources management, monitoring the impacts of use and improving enforcement of management plans. This will focus on non-timber forest products, cash crops, and offtakes of wildlife where sustainability can be assured with effective conservation measures are in place. The Biodiversity Fund, however, will not cover salaries and entitlements of community partners and management committees nor support the preparation and application process of community groups to be a registered Integrated Land Group. These aspects shall be defined in detail in the Fund’s Strategic Plan and Operational Manual which will be developed in inclusive and participatory ways and approved by the Steering Committee.

  - The Fund will also hold donors and benefactors to the same ethical standards, and where necessary, donations will be turned away if the source of the fund/s is/are found to be unethical. All donations will also be free from leverage or influence on the Fund.

  - The Fund will be inclusive and equitable. It recognises the diversity of Papua New Guinea and that the majority of land is under customary ownership. It recognises that the majority of the people it will benefit do not have the capacity to fill complicated forms and templates that are often associated with such funds and the Fund will be designed specifically to take this into account and will accept the high transaction costs that this confers on to the Fund. It recognises that the majority of land owners and land users have chosen to form protected areas on their land not only because of the biodiversity or conservation value but also because they seek legal protection over their land.  It recognises that these people want to protect their land for the ecosystem services it provides them, and for its cultural values.  As such, the Biodiversity Fund recognises that it will fund activities that build governance and equitability, socio-economic development and improve well-being, including, where possible, improving access to social services.

  - The Fund recognises the diversity of people that make up communities and the issues surrounding the androcentric nature of the majority of Papua New Guinean communities. The Fund also recognises the role that different segments of society play in natural resource use and management.  As such, the Fund will prioritise those areas in which gender equality is promoted, in which youth are given opportunities to thrive in a changing world, and in which gender-based violence is countered.

  - In the spirit of inclusion and equitability, the development of the Fund’s guiding documents, including a full version of the principles and strategy of the Fund, and the Operational Manual (which will include the policies and rules of procedure of the Fund) will be conducted in a participatory and inclusive manner.

  - There will be a participatory review of the governance structures and constitution (including the policies, rules of procedure and strategic plan) of the Fund every four years during the first 12 years of the Biodiversity Fund’s life, and this may be extended to every eight years in perpetuity thereafter.

- The project will focus on the logical sequence of establishing the Fund by putting in place the different structures as well as governing documents (Outputs 2.1 and 2.2), development and implementation of a resource mobilisation/fund raising strategy (Output 2.3) and support the government ownership role to capitalize, operationalise and manage the Fund.

Output 2.1: The Biodiversity Fund’s governing and operational structures are established

- In principle, the legal establishment of the Biodiversity Fund comes through the enactment of the PA Bill.  In order to facilitate the establishment of the Biodiversity Fund – especially legal aspects – the project will carry out a review of the existing policies and legislation (including the status of the PA Bill and its regulations) to ensure that everything is aligned to enable the operationalisation of the Biodiversity Fund – as well as the ability to collect taxes, levies and fees for replenishment of the Biodiversity Fund and/or for protected area management and/or the legislative requirements for some of the revenue generating mechanisms that will be incorporated into the business plan that will be developed under the project (see Output 1.2).  As such, the review will be undertaken during the process to establish the Biodiversity Fund and while the Business Planning process is underway.

- This work will be undertaken by a person or team with sufficient legal capacity and who will be hired specifically for this task (see overview of technical consultancies in Annex C). The outputs of the work will not simply be a report with recommendations for the amendments that are necessary, but the people involved in this work will have to work with the relevant stakeholders and organisations to prepare all the amendments that may be necessary such that they are ready for submission to the NEC for final approval.

- The project will then put in place the different structures together with the documents that are necessary to govern the Fund and each of those structures (including their responsibilities, management functions, composition and relations to each other) – necessary to operate and administer the Fund by Year 3. These include: i) the Steering Committee; the Secretariat; the Administrator; and the Investment Manager. Over and above these four fundamental bodies, there may be an additional Advisory Body.

- The project’s Project Board (see Section VIII) have additional responsibilities (over that of usual UNDP-GEF PBs) and it will guide and oversee the process of legal establishment of the Biodiversity Fund and the constitution of the Fund’s governing bodies and structures. The governing documents for the Biodiversity Fund will include the Articles of Incorporation.

- Biodiversity Fund Steering Committee. The Steering Committee is the Fund’s highest governing body. It is constituted within Papua New Guinea and is the decision-making body for the Fund.  As such, the Steering Committee facilitates donor coordination and funding, ensures overall coordination, sets the fund’s strategic direction through the Fund’s Strategic Plan (which will include the Fund’s priorities and theory of change, and all decisions by the Steering Committee will be taken with these in mind; the Strategic Plan will also articulate the Fund’s targets regarding resource mobilisation, which, in turn, will be linked to the Resource Mobilisation Plan). The Steering Committee also oversees the inter-agency efforts for implementation, makes resource allocation decisions and is responsible for reviewing and revising the fund’s performance.

- The Fund’s Articles of Incorporation will specify the composition of, and level of expertise required in, the Steering Committee (including, for example, people with legal and financial expertise, and representation of the beneficiary groups); the process of selection and/or appointment of Steering Committee members; establishing the terms of office of Steering Committee members; developing policies on Steering Committee meetings (regularity, minutes, decision-making processes; quorum, conflict resolution, fiduciary responsibilities, etc.).  However, following best international practices, at least 50% of the Steering Committee should be drawn from non-state actors (private companies in which the state has an equity interest should be considered as state members of the Steering Committee and, therefore, not to be included in the >50% of “non-state actors”). In addition, reviews have indicated that conservation trust funds with greater independence from government are more transparent and effective in achieving biodiversity conservation goals, less influenced by short-term political considerations, and more successful in attracting contributions from donors and from the private sector.]

- In addition, global best practice indicates that other important factors that will contribute to the Biodiversity Fund’s success and independent status include: i) the chairperson of the board should not be a government official; ii) the fund’s office should not be physically located inside a government ministry; iii) non-governmental members of the board should not be chosen or appointed by a government; and iv) the Steering Committee should have at least one high-level government representative to ensure that fund’s activities are linked to national biodiversity conservation action plans and policies, and to ensure government support for the Biodiversity Fund.

- In order to protect against the possibility that the Steering Committee decided to close the Fund and use the liquidated assets for uses of their own interest, the Fund will adhere to the principle (which will be included into the Articles of Incorporation) that it can only be closed under specific circumstances, such as: i) permission to explore the feasibility and possibility of closing the Biodiversity Fund will be sought among all its constituents (with constituents being defined as all those people of voting age living within or adjacent to every protected area within the country and all the people and organisations who have made gifts or donations to the Fund) and the Steering Committee will only secure the go ahead to carry out this work if a super-majority (defined as being more than 75% of the constituents) agree to this course of action; ii) the results of the exploration are presented to all constituents; the presentation will include a full exploration of different scenarios including what should be done in order to keep the Fund operational as well as what will happen to all the assets if the Fund were to be closed; iii) permission would be granted to the Steering Committee to close the Fund if a super-majority (of greater than or equal to 75%) of the constituents agree that this is the only remaining course of action; and iv) on closure, the Steering Committee disburses the assets in the way proposed above with full transparency and accountability to its constituents.

Figure 7. The structure of the Biodiversity Fund

- Once formed, the Steering Committee, with the support of the project and the Secretariat, will develop the Fund’s Strategic Plan (which includes funding priorities taking into consideration the Fund’s objectives and theory of change) and the Operational Manual for the Biodiversity Fund (see Output 2.2).

- The Steering Committee will be bound to the rules of procedure set out in the Fund’s Operational Manual (see Output 2.2), including, for example, that each of the members of the Steering Committee will be asked to sign a legally binding declaration of Conflict of Interest and Code of Conduct.

- Advisory Board. The Steering Committee will be able to call on external advisers as and when desired or needed in order to assist them with the decision-making processes and with the governance of the Fund.  This may take the form of an Advisory Board, as required (and during the process of establishing the Biodiversity Fund, the need for an Advisory Board will be determined). If an Advisory Board is constituted, i) it will not have decision-making or voting powers within the Steering Committee and it will be comprised of legal, financial, institutional, governance, environmental and social/gender advisors, and ii) the process of selection and appointment of advisory committee members; and developing policies for the advisory committee/s (terms of reference, record of meetings, decision-making processes, etc.) will be included in the Fund’s Articles of Incorporation.

- Technical Secretariat.  The Secretariat will comprise a professional fund management team (envisaged to be a maximum of four people) that will be recruited following a Request for Proposals. The Secretariat shall provide technical and administrative support to the Steering Committee and will be responsible for the day-to-day operations of the fund. This will include the appraisal of project proposals (including guaranteeing relevancy and quality, and social and environmental screening), coordination, report consolidation, monitoring and evaluation – as described in the Fund’s Operational Manual. The Secretariat may from time to time draw on UNDP for support as necessary. The Operational Manual will, in turn, be codified by the Secretariat for approval by the Steering Committee. The Operational Manual will also include the Fund’s policies and rules of procedure.

- In partnership with the Fund Administrator (see below), the Secretariat will also develop the Fund’s resource mobilization strategy for approval by the Steering Committee and will engage, as necessary, with contributing partners.

- The Secretariat will also ensure the monitoring of the implemented activities and operational risks, and submit consolidated periodic results-based progress reports to the Steering Committee (see “Reporting, Monitoring and Evaluation” below).

- Some of the functions of the Secretariat may be delegated to UNDP and/or contracted to third parties – including aspects such as developing proposals and mentoring low capacity groups or organisations, project/ programme appraisal, and monitoring and evaluation.  This would result in the increased independence of such activities.

- Once it has been constituted, the Secretariat will be based in a dedicated Fund Office; this will be an independent office – following international best practice on Conservation Trust Funds.  GEF funds will, therefore, be used to cover their associated establishment and operating costs for the life of the project - including procurement and installation of key equipment and communications infrastructure necessary to support the administrative and financial management functions of this professional management team.

- Fund Administration.  The design of the Fund will be supported by the UNDP Multi-Partner Trust Fund Office. The MPTFO operates (in more than 110 countries, including PNG) under pre-cleared, standing legal contractual arrangements with over 120 donors – including the majority of bilateral and multilateral donors as well as other philanthropists and benefactors. The MPTFO has been identified to provide technical support for a number of strategic reasons, including: i) it would help navigate the complex legal processes that are usually associated with establishing trust funds, ii) it has a proven track record of delivering in a secure, transparent and accountable way, and iii) it has proven connections and existing agreements with the majority of the multi- and bilateral donors and private philanthropists (thereby expediting the fund transfer process). Critically, using the MPTFO in this way would allow the Fund to be established quickly; this is critical to the project’s success, primarily because operationalisation, testing and learning – coupled with building governance systems and developing capacity – are all slower and, more complicated processes.

- As a service provider it will assist the government with the establishment of the Trust Fund shell. The project will create the requisite Trust Fund structure for the government to use, while the PNG government will take responsibility for operationalizing and capitalizing the Trust Fund. MPTFO has done this before with several Trust Funds where they have established a Trust Fund shell for a fee but do not commit to operationalize or monitor it.

- The Government and Steering Committee will contract an independent and reputable institution to be the “Trustee” of the Fund.  The key functions of the Fund Administrator will be to assist CEPA in its early administration, including receiving and administering contributions, consolidation of revenues from different sources, transferring funds to the recipient entities (as per the Steering Committee’s decisions) as well as financial and performance reporting.

- With the support of the Secretariat, the Fund Administrator will assist in administering all legal arrangements with Recipient Organizations and contributions from donors during the initial phase of the project. Building on the experience of a successful Trust Fund within the Department of Transport and Infrastructure, the independent service provider will place a financial comptroller to mentor at least 3-4 dedicated staff of CEPA from the early years of administering the Fund until the project ends.

- The Fund Administrator will further assist in establishing a publicly-accessible online platform for the Biodiversity Fund.  This specifically adds transparency and visibility – as transactions (both inward and outgoing) can be viewed in real time.  The online platform will also support resource mobilization efforts as the Fund will be brought to the attention of potential partners.  In addition, on the basis of the recipients’ annual reports and financial statements, the Fund Administrator will also assist the Secretariat initially to prepare annual consolidated narrative and financial reports to submit to each of the Fund's Contributors and to the Steering Committee.  These reports will also be publicly available on the online platform.

- Fund Investment.  An Investment Manager will be identified through a call for proposals. The investment manager will be an independent organization responsible to invest the fund assets in line with "ethical” investment rules as indicated above; the Investment Manager will receive monies and transfer the returns on the fund at a mutually agreed cost. The Investment Manager will advise the Steering Committee on Fund design and investment portfolio (while following the underlying principles of the Fund).

- The funds will be structured as a sinking fund, with the design of the fund being reviewed every four years in order to provide opportunity for adaptive management of the fund structure and operation. In summary, the review will include analysis and review of the Fund’s financial architecture relative to the degree to which it is capitalised.  The design of the fund will take into account its level of capitalisation at the time of the review and decisions will be made regarding: i) the proportion of the sinking fund that will be invested, ii) how the interest and other revenue streams can be developed, iii) how to manage the revenues that are being accrued within the protected area system within PNG, and iv) whether amendments to the investment portfolio should be made on the basis of the Fund’s principles (as described above).  The result will be an Investment Strategy that will be forwarded to the Steering Committee for approval and adoption. The Investment Manager will, therefore, invest the funds according to the approved Investment Strategy which will be reviewed from time to time to ensure relevance.

Output 2.2: The Biodiversity Fund’s strategic and operational frameworks are developed

- The project, together with the Secretariat, Steering Committee, UNDP and the Fund Administrator with MPTFO will undertake an inclusive and consultative process to develop the documents necessary to operationalise the Fund.  These include: i) the Fund Risk Management Strategy, ii) the Strategic Plan, and iii) the Operational Manual.

- In the event that disagreement arises in the administration of the Fund, the UNDP Resident Representative, as a neutral party, will arbitrate.

- Strategic Plan. The Strategic Plan will cover a 10-year period and define aspects such as the Fund’s Objectives, Theory of Change – and as a consequence, funding priorities.

- Risk Management. The project, in liaison with the Secretariat and the Fund Administrator, will develop a Fund Risk Management Strategy with the explicit aim to accelerate delivery and increase fund impact, ensure that fund operations ‘do no harm’ and verify that funds are used for their intended purpose, and improve risk management capacity of national institutions. In this way, a common understanding of the risk context and the possible mitigation measures will be developed. The development of the Risk Management Strategy will include a participatory and inclusive assessment of risk, with the associated mechanisms to reduce and better manage risks.  Overall, the Fund’s Risk Management Strategy will develop a shared understanding of risks faced by the Fund, including i) defining risk appetite or tolerance, ii) identifying known risk and risk-holders, iii) establishing the Fund's policies regarding identified risks (for incorporation into the policy section of the Operational Manual), iv) determining risk treatment through measures of mitigation or adaptation, and v) establishing information strategies and common messages about the risks.

- Operational Manual. In terms of developing the systems for operationalising the Biodiversity Fund and building systems for working with beneficiaries, the systems and processes that were previously developed by other actors – and most pertinently, the Mama Graun Conservation Trust Fund and the UNDP-GEF SGP – will be adapted for use. The project will also seek best international practices on which to build its systems and process (as will be codified in the Operational Manual).

- In terms of target beneficiaries, the Fund will be inclusive, especially in view of the nature of the protected area system that is predominantly owned by communities. There will be specific costs to being inclusive, with high transaction costs for working with those communities with low capacity to deal with the complexities of applying for funding, managing and expending funding to produce results, and reporting those results and accounting for expenditure. This, however, is the cost of business and the Biodiversity Fund will, in response, will be deliberative and iterative, and work through international or/or local NGOs and CBOs.

- The capacity of a small number of partner organisations (local NGOs or CBOs) will be specifically built to work with the Secretariat to mentor, build capacity, and work with communities and LLG partners at the level of the protected areas; this will, ultimately, reduce the transaction costs.

- These systems will all be codified into the Operational Manual. The Operational Manual will also include the Biodiversity Fund’s principles, policies and rules of procedure. The rules of procedure, in turn, will include how the various governance bodies are constituted and the composition of, and level of expertise required in, the structures; how members will be selected on the basis of ensuring representation of the key stakeholders; establishing the terms of office of board members; developing policies on board meetings (regularity, minutes, decision-making processes; quorum, conflict resolution, fiduciary responsibilities, etc.); the rules of procedure for each of the Biodiversity Fund’s structures – including the Steering Committee for which: i) decisions will be made by consensus, and ii) decisions will be made on the basis of the Fund’s principles, purpose and Theory of Change) iii) the various formats for application for funding, reporting and accounting, including eligibility criteria; iv) the project funding cycle (see Box 2), v) the monitoring and evaluation framework (see below); vi) the formats for Declaration of Conflicts of Interest and Code of Conduct – specifically for the members of the Steering Committee, Secretariat and Advisory Board; and vii) the investment principles and strategy, and how the corpus of the Trust Fund should be managed.

BOX 2: PROJECT CYCLE Development of projects: Each eligible recipient organizations may submit proposals to the Steering Committee, after a call for proposal process. The Secretariat is responsible to develop calls-for-proposals and once they are approved by the Steering Committee, the Secretariat will communicate the call for proposals with all potential grantees (noting that the majority of potential grantees do not necessarily have access to the internet and some do not have access to a mobile phone network). The grantees then prepare their proposals – with the support of the Secretariat and/or other parts so as to build the ability of all grantees to manage the application process. All projects must: i) align the key expected results and indicators with the strategic objectives of the Fund, ii) demonstrate that proposed activities have been developed in consultation with beneficiaries, iii) contain detailed budgets and workplans, a risk analysis, proposed executing partners and geographical scope, and iv) include satisfactory environmental and social safeguards. Assessment of Proposals: The Secretariat conducts a systematic, comprehensive assessment of the project proposals (possibly with the support of a third party). Where the proposals need further strengthening, the Secretariat and/or other partners will work with the grantees to strengthen the proposal(s) – noting this is not a competition but an inclusive process to contribute to the financial sustainability and management of protected areas across the country. Approval of projects: Once the assessment is finalized, the Secretariat submits a recommendation to the Steering Committee for review and approval. On approval, the Secretariat will sign the contract with the grantee(s). Project implementation: Once the contract is signed, disbursement of funds can commence. On approval from the Steering Committee, the Fund Administrator will make the fund disbursements direct to the recipient organisations. Disbursements will occur on a quarterly basis, with a rolling one-quarter float. The subsequent quarter’s budget will be disbursed on satisfactory receipt of the previous quarter’s accountability and reporting. Reporting. Aside from the quarterly accountability and reports, the recipients will also submit annual reports and financial statements using a common format designed for the Fund (that will be substantially linked to measuring the management effectiveness of the area using a “METT for PNG)”. At the end of a project’s life, a final narrative report and financial statement will be submitted using the same format. The reports must exhibit results based on evidence. The responsibilities related to reporting are gathered and detailed in the legal agreements signed between the recipient organization and the UNDP/Fund Administrator.

- Monitoring and evaluation. Monitoring and evaluation will be conducted by the Secretariat, with periodic independent monitoring and evaluation by a third party. The periodic independent M&E will assess the progress of the Fund towards achievement of its objectives and outcomes, with audits of the recipients’ use of funds. The objective of evaluations is to analyse the Fund's performance, and will provide specific recommendations to the Steering Committee regarding the underlying theory of change, including its revision if deemed necessary.

- The Secretariat will include an M&E specialist who will consolidate all the results and information received from the recipients through a result-based management system. This system will gather performance data at the level of outcomes and outputs, linking program-related and financial result indicators to enable the evaluation of both efficiency and effectiveness of the Fund.

- Review. There will be a review of the governance structures and constitution of the BF every four years and, therefore, the first review of the governance structures, constitutional and operational documents will occur during the project’s life and be supported by the project. Indeed, on the basis that every stakeholder, without exception, recommended it, the project will be longer than originally proposed in the PIF.  This will also allow the impacts of the Fund to be evaluated after this project has been completed. It will also provide sufficient time for the processes dictated by the Operational Manual to be tried and tested, and adapted through an iterative review process to become sufficiently robust and equitable within the context of Papua New Guinea.

Output 2.3: A fund raising/resource mobilization strategy for the Biodiversity Fund is developed and implemented

- The project, in concert with the Biodiversity Fund, will assist in developing a fundraising strategy – the Resource Mobilisation Strategy – the aim of which will be to solicit significant contributions to the Biodiversity Fund from a variety of donors, including multi- and bilateral donors and ODA, the private sector, private philanthropists and NGOs.

- The fundraising strategy will be developed in tandem with the Business Plan for the protected area system (see Output 1.2) recognising that their aims are somewhat different. The CTO, who will lead the development of the Business Plan, will also be involved in the development of the Biodiversity Fund’s fund raising strategy and, as such, the fundraising strategy will take account of the Business Plan objective to generate sufficient revenues and will cross-subsidize the protected area system – or, more pertinently, consolidate revenues that can continue to replenish the Biodiversity Fund on a year-by-year basis.

- There is also an opportunity to use the Biodiversity Fund as the mechanism to administer support pledged to the PNG government for the implementation of the PNG Protected Areas Policy.

- The implementation of the fund-raising strategy will be funded by the project and carried out by a team specifically recruited to do so. The strategy will include a number of different processes:

  - The fund-raising team, with the assistance of the project, will support donor management processes including: i) targeting potential donors – including those from the community in PNG – by preparing detailed project proposals, ii) liaising with different funders, and iii) building working partnerships with funding agencies/ institutions.

  - As a country with vast stored carbon and carbon sequestration processes, there is significant potential to mobilise REDD+ and other carbon financing. However, the feasibility of this needs to be determined – in part by closely watching the progress of other people in securing carbon finance (see Output 3.3).

  - The fund-raising team will also explore all other innovative mechanisms for generating resources for the Biodiversity Fund. For example, Debt for Nature Swaps, could be explored as a mechanism to capitalise the Biodiversity Fund.

  - The fund-raising team will also determine the feasibility of including taxes, levies and revenue streams from other sources as mechanisms to replenish the Biodiversity Fund – including biodiversity offsets, green taxes (e.g., a round-log tax as has been suggested in the PA Bill) and payment for ecosystem services (especially in those situations in which the users are private or semi-autonomous organisations such as PNG Power or Eda Ranu – and other water suppliers around the country).  Ultimately, how these funds will be managed will be decided and written into the fund design; as stated above, this will be reviewed every four years.

  - In addition, on reaching a suitable agreement, other funding mechanisms that have been established or are in the process of being established (e.g., the USAID funding for protected areas) will be amalgamated into the Biodiversity Fund (see Partnerships section, below); where it is not possible to do this, synergies and complementarity will be ensured.  It is also expected that BF will collaborate and draw lessons from UNDP-GEF SGP from its grant making process to community-level natural resource management and/or protected area management.

Outcome Three: Mechanisms for improving management and financial sustainability of selected protected areas tested and piloted to improve knowledge, learning and practice

- This component focuses on testing, piloting, demonstrating and learning – specifically: i) testing mechanisms to deliver funds from the Biodiversity  Fund to protected areas – thus, operationalisation of the Biodiversity Fund (Output 3.1), ii) piloting mechanisms that will catalyse or consolidate revenue in a small number of sites, such that revenue will be re-invested into the management of those sites or used to cross-subsidise other sites across the protected area system, ideally through the provision of loans (Output 3.2) and iii) learning from the diverse practices that are being implemented by various partner organisations across the country (Outputs 3.3 and 3.4).  These final two outputs will also lead to lessons being learned from the project via active participation of all stakeholder groups in the project activities’ design, implementation, and monitoring and evaluation.  The information and data from M&E will be made available nationally and internationally to facilitate sustainable financing of the PA system across the country.

- For each of the recipients under Outputs 3.1 and 3.2, the project and Secretariat of the Biodiversity Fund and other partners involved in the process will provide additional technical support that will include: assistance with the fund application process, awarding the funds, negotiating and agreeing on the contracts associated with the funding, and mentoring through the life of the funding period. In addition, there will be independent field evaluations, and financial and technical auditing.

- It should be noted that in the majority of the project document, but particularly in this section, “protected areas” refers to the organisations and people that are associated with any given protected area. Thus, this could include: the land-owners and land-users, protected area management committees, and other state or non-state actors that are working specifically for the effective management of the given protected area.  The project recognises, too, that there are many “protected areas” beyond those that are officially recognised by CEPA; in principle, the Biodiversity Fund will also make funding available to all (subject to agreement on the Fund’s priorities, theory of change and strategy).

Output 3.1: Mechanisms to deliver funds to protected areas and for participatory natural resource management tested

- Funds will be delivered to protected areas from the Biodiversity Fund once it has received initial capitalization and the architecture and governance of the fund have been established. The initial capitalization will include a minimum investment of: a) USD 5 million initial capital from GoPNG and b) at least USD 1.5 million annual revenue from recurrent income sources enabled by innovative GoPNG fiscal instruments. In addition, it is expected that implementation of the fund raising/resource mobilisation strategy will result in additional capitalization of at least USD 250,000 by mid-term and USD 1 million by the end of the project. GEF funds amounting to USD 2.7 million will be disbursed through low value grants in support of PA management, capacity development, sustainable livelihood and revenue generating activities, etc.

- The mechanism for disbursement of GEF funds will be through grants (utilizing the UNDP micro-capital grants policy) to CBOs. The $2.7 million in the project budget would be disbursed through UNDP and the Project Board would decide (on a programmatic basis) the selection of grant beneficiaries; UNDP would sign grant agreements with each grant recipient. The funds for the grants would be released by the UNDP CO in tranches which would be drawn down from the project budget as individual grant agreements are signed and grants are disbursed. The full $2.7 million would be disbursed by the end of the project with results through a series of individual grants; and any remaining balance would be returned to GEF.

- This output will test the funding mechanisms of the Biodiversity Fund – particularly the mechanisms described under Output 2.2. The specific aim here is to test the systems of the Biodiversity Fund (as defined under Output 2.2) such that by the end of the project, it has demonstrated how the system may function efficiently and effectively – together with the mechanisms of adaptive management. In other words, it is highly unlikely that the system, as developed under Output 2.2, that is put into place from the outset will be perfect; there must be a mechanism through which the system can adapt and change.  By the end of the project, it is expected that the second edition of the Biodiversity Fund’s operational manual will have been produced as a direct result of the monitoring, evaluation and amendment during the project’s life.

- In addition, the Biodiversity Fund will assist protected areas in all stages of their development (which will be codified in the Biodiversity Fund’s Operational Manual and the Fund’s strategy, funding priorities and theory of change – as developed under Output 2.2): thus, whether i) a protected area in the early stage of its development requires assistance (including legal assistance) to become established and recognised, ii) capacity development (including legal literacy) is necessary to build governance and management systems of an established protected area, iii) a protected area simply requires assistance to cover some of the recurrent costs of management, or iv) a protected area requires an injection of capital to cover the investment costs of some form of development (that may subsequently generate revenue for the protected area).

- Many of the protected areas across the country have a need for capital investment and operational funding.  However, there is a need to be practical in the initial stages of the Biodiversity Fund’s life when the systems are being tested. As such, guided by the Biodiversity Fund’s Operational Manual and Strategy, the funding delivery mechanism will be tested in as many protected areas and with as many communities involved in natural resource management as is feasible. For the sake of practicality and feasibility, the initial rounds of funding will be limited to five areas per funding cycle, with each funding cycle expected to last four years and with a new group of protected areas joining the scheme per year (covering a total of 20 PAs for each cycle). The results of this process will be monitored carefully to ensure that there is adequate learning and those lessons are used to further adapt the operations manual for all future rounds of funding.

- Over the project’s life, fund delivery by the Biodiversity Fund will be trialled in both those areas that are relatively well capacitated (in that their capacity has already been built through existing partnerships) as well as working out how to deliver funding to the less capacitated areas. Therefore, for example, there has been significant investment in the Strickland Headwaters and Kaijende Highlands (through a partnership with Barrick/Porgera Joint Venture), the Kikori River Basin (with four WMAs) and Lake Kutubu (through a partnership with PNG LNG), the Yus Conservation Area (which has been developed in partnership with Woodland Park Zoo), the Torricelli Conservation Area (proposed, though a partnership with the Tenkile Conservation Alliance), the Wanang Conservation Area (with the current partnership with the NG Binatang Research Center and the Steamships Company) and the Varirata National Park (through investments by JICA and the UNDP-GEF-5 project).  Important areas such as the newly created Managalas Conservation Area will be important to support, as well as the significant areas in the west of the country (Tonda and Maza WMAs). Other smaller community-conservation areas include those in which the UNDP-GEF-4 project has invested funds and support (with a number of different partners). Thus, the mechanism to deliver funding to protected areas will be tested in these areas – as per the criteria in the Biodiversity Fund’s Operational Manual (see Output 2.2 and Box 1); however, this will not offset the funding from these existing supporters or partners – indeed, provision of funding from the Biodiversity Fund will be conditional on demonstrated maintenance of the support from the original partners and supporters.

Output 3.2: Mechanisms to catalyse (or consolidate) revenue streams to deliver funds to selected protected areas tested

- One of the important aspects of building sustainable financing of protected areas is their ability to generate revenue and that this revenue is then used to contribute towards the management and maintenance costs of the protected area, and possibly even to contribute towards the management of other sites.

- This aspect of the project will work through selected partners (see Table 4) in three areas with the aim of catalysing (where they do not currently exist) or consolidating (where they currently exist) revenue streams, and that some portion of the revenue streams is then used to contribute towards the costs of managing the protected area.  The three areas (as described in Section III) are: i) the Sepik Wetlands, ii) the Mt Wilhelm assemblage of protected areas, and iii) Kimbe Bay.  The process will include developing and implementing a proposal/workplan for developing the revenue generating activities, with associated feasibility and risk analyses and social and environmental impact assessments.

- In addition, the process will also include negotiating natural resource management agreements with the customary land owners and implementing a process that will lead to the establishment of protected areas in each of the areas (to be a mosaic of protected areas in the Sepik Wetlands, at least one area in the vicinity of Mt Wilhelm that abuts the Mt Wilhelm National Park, and a sub-marine conservation deed for Kimbe Bay).  Each of the steps (including the revenue generating schemes, the natural resource agreements and the roles and responsibilities surrounding the conservation deeds and their implementation) will ensure gender- and age-inclusivity, that there is no abuse of power, and that fair and equitable management structures and governance systems are put in place.

- The areas are also extensive (Sepik Wetlands: 1.5 million ha; Mt Wilhelm covering the ecological cline from 200m asl to 3,200 m asl; and Kimbe Bay: 2.53 million ha) and include the communities living in these areas.  The project together with the project partners will, therefore, adopt an ecosystem approach in these areas; this will include consideration of climate change in site management planning and assessments.

- Lessons learnt in the implementation of these income-generating opportunities will enable an objective assessment of the feasibility and viability (affordability, practicality and efficiency) of introducing revenue generating mechanisms in other protected areas or across the entire protected area system. It is envisaged that a portion of the net income from GEF-supported activities under this output may be allocated to the sinking portion of the Fund for re-investment directly back into the conservation management of the protected areas generating these income streams.

Table 5. The specific activities that will be funded in each of the selected protected areas

| Area (and partners) | Activities to be carried out |
| --- | --- |
| Sepik Wetlands (SWMI, Mainland Holdings Ltd, Ramsar, CEPA; an organisation such as FORCERT and/or with PNG Centre for Locally Managed Areas – to improve the functionality and governance in SWMI; EU-funded programmes; Provincial Government, LLGs). | - Improve capacity, governance, transparency and accountability of SWMI. Because of the low capacity and dysfunctionality of SWMI, it is likely that they will need significant support to improve their governance, transparency and accountability – this could either be done through a new partner, or the re-engagement of WWF, or through a greater commitment by Mainland Holdings (with the latter option probably being the optimum solution). - Identify contextually appropriate community-conservation areas (in terms of size, ownership, natural resources that they harbour); negotiate meaningful natural resource management agreements within those areas; sign agreements with the owners and users of those areas; build capacity of the people to manage those areas; ensure legal protection of those areas (using appropriate tools such as conservation deeds); Build a mosaic of community-conservation areas all protected by appropriate tools such as conservation deeds across the Sepik Wetlands - Build on and consolidate the existing system of harvesting crocodile eggs (with their transport to Mainland Holdings in Lae and ultimate transformation into high-end, luxury products), including: i) ensuring that the annual nest count surveys are carried out (paid for by CEPA, having carried out a reassessment of the fee structures that Mainland Holdings pays to CEPA such that the fees cover these costs), ii) ensure traceability of all eggs and skins from the person in the Sepik Wetlands who harvests the eggs to the high-end luxury product - Support data collection, development of management plans and technical assessment required for or after the designation of Ramsar site. - Conduct a climate change vulnerability assessment to inform management and investment planning - Produce a business plan for the Sepik Wetlands that includes all aspects of financial sustainability and socio-economic development, taking into account climate change adaptation needs - Carry out value chain analyses for the other natural resources that are being harvested from the area to determine the feasibility of on-site value addition and establishing transparent, accountable and traceable supply routes. - Carry out an assessment of how to improve tourism within the Sepik Wetlands and the adjacent Hunstein Range WMA; contribute to the implementation of a resulting tourism development plan - Work with other donors (e.g., EU) to put in place “mobile money” systems such that people are not vulnerable to insecurity associated with transporting large sums of money. - Work with LLGs to mainstream environment and biodiversity into LLGs development plans while delivering social services, including training health workers and teachers drawn from the local communities. - Provide micro-loans to stakeholders in any sector (but especially tourism and natural resource harvesting) as long as it i) leads to a demonstrable increase in the livelihoods and well-being of those people involved, ii) it is demonstrably gender and age positive and iii) it will demonstrably lead to improved environmental conditions. - Negotiate and implement fee structure for all vessels using the Sepik river for commercial transport – especially for transport of logs - Secure a PES agreement with the Frieda mine and upstream loggers to offset all potential and real impacts on the Sepik Wetlands |
| Mt Wilhelm Conservation Area (Provincial Government, LLGs, New Guinea Binatang Research Centre, WCS – with the BRC taking a lead in the areas adjacent to the national park and WCS taking a lead in the areas within the NP) | - Work with the New Guinea Binatang Research Centre to put in place the infrastructure necessary to attract researchers to the environmental cline from 200m asl to the peak of Mt Wilhelm. - Work with the New Guinea Binatang Research Centre to produce the biodiversity knowledge base (using biodiversity surveys and ecological research) and local expertise (training locally recruited personnel, from field assistants through paraecologists to university-level and even PhD level researchers) to increase the attraction of the area for research and its ability to support such research - Conduct a climate change vulnerability assessment to inform management and investment planning - Carry out an assessment of how to improve tourism within and surrounding the Mt Wilhelm conservation area; contribute to the implementation of a resulting tourism development plan - Work with LLGs to mainstream environment and biodiversity into LLGs development plans while delivering social services, including training health workers and teachers drawn from the local communities. - Identify contextually appropriate community-conservation areas (in terms of size, ownership, natural resources that they harbour); negotiate meaningful natural resource management agreements within those areas; sign agreements with the owners and users of those areas; build capacity of the people to manage those areas; ensure legal protection of those areas (using appropriate tools such as conservation deeds) - Negotiate an agreement between those people and organisations that are involved in the management of the Mt Wilhelm National Park and the adjacent communities such that there are strong synergies between the adjacent areas - Produce a business plan for Mt Wilhelm that includes all aspects of financial sustainability and socio-economic development, including climate change adaptation considerations - Work with LLGs to improve delivery of social services, including training health workers and teachers drawn from the local communities. - Secure PES agreements for i) carbon storage and sequestration across the area, ii) watershed protection. - Carry out value chain analyses for the other natural resources that are being harvested from the area to determine the feasibility of on-site value addition and establishing transparent, accountable and traceable supply routes. |
| Kimbe Bay (Walindi Plantation Resort, Mahonia na Dari, Liamo Reef Resort, WNB Provincial Government, LLGs, LMMAs, TNC, JCU and other research organisations, NBPOL, HPOL; overall implementation may be done by an organisation such as FORCERT with PNG Centre for Locally Managed Areas). | - Seek protection of Kimbe Bay on the basis of an appropriate conservation deed - Produce a business plan for Kimbe Bay conservation area(s) that includes all aspects of financial sustainability and socio-economic development including climate change adaptation considerations - Conduct a climate change vulnerability assessment to inform management and investment planningNegotiate with research organisations to determine fee structures that are both affordable and make meaningful financial contributions to the management of Kimbe Bay - Negotiate with tourism organisations to determine whether there are any fees structures and/or financial mechanisms that could contribute to fund the management costs of Kimbe Bay; Carry out an assessment of how to improve tourism within Kimbe Bay – thereby assisting in the development of the ecotourism aspirations and products to help establish Kimbe Bay as a priority area within the Coral Triangle and the Pacific; contribute to the implementation of a resulting tourism development plan - Manage the expectations of the LMMAs; overhauling the LMMAs to something meaningful for the context of Kimbe Bay; support the emerging coordination mechanism for the LMMAs in Kimbe Bay; change attitudes of people (using MND) and ensuring that these groups assume their responsibilities, forged through the establishment of natural resource use and management agreements - Work with the West New Britain government to build partnership that lead to meaningful and effective management of all resources within Kimbe Bay - Work with LLGs to improve delivery of social services, including training health workers and teachers drawn from the local communities. - Build partnerships with New Britain Palm Oil Ltd and Hargy Palm Oil Ltd to ensure their contribution to the conservation of Kimbe Bay (including ensuring their commitment to i) not expanding the coverage of palm oil, ii) carrying out forest rehabilitation, iii) testing run-off water from the palm oil plantations for use of chemical inputs that pollute Kimbe Bay – and securing payments for damages, iv) ensuring their continued support for community palm oil schemes. - Carry out value chain analyses for the other natural resources that are being harvested from the area to determine the feasibility of on-site value addition and establishing transparent, accountable and traceable supply routes. - The conservation zone will require annual monitoring to assess water quality, coral cover, species richness, dead coral, indicator species (e.g. COTS), fish species (including commercial & recreational target species), and local community/individual attitudes (interviews). There is no effective baseline for these things (there are some data but they may not be consistent and only cover selected areas of the conservation zone). It will also be necessary to monitor land clearing activities, pollution and waste, coverage of palm oil and fertiliser use on land as these all affect what happens in the Bay. |

Output 3.3 In a learning process, the diverse practices that are being implemented by various partner organisations across the country will be documented and the lessons learned from them will be disseminated

- There are a number of ongoing efforts both to build capacity among protected areas in the country, but also, in a few places, efforts to generate some form of revenue (e.g., the Porgera Joint Venture is exploring the possibilities of securing REDD+ funding to contribute to the long-term financing and hence management of the areas in which they have been investing – specifically the Strickland Headwaters and Kaijende Highlands, or the Yus Conservation Area with an endowment fund dedicated to the area). In addition, in at least one instance, the revenue is being used to protect the area (see Table 1). In these areas, there may not be a need for the project to invest GEF funds either to improve the likelihood that revenue-generating mechanism is implemented or even to build capacity of the partners that are working to protect and manage areas.

- Instead, the project’s role in these areas is to work with partners to document (through case studies) and thereafter disseminate the lessons learned from the case studies, such that the good practices can be replicated across the protected area system. The project will, therefore, convene a seminar every two years throughout its life; this will bring all the partners involved in protected area management in the country together. At these seminars, the case studies will present the mechanisms being used to achieve financial sustainability and to build capacity, and to achieve the dual and linked goals of achieving biodiversity protection and justly distributed improvement of the well-being of the land owners and users in their diverse roles as women, men, young and old, ethnic minority, etc.

- This does not preclude these areas from receiving funding from the Biodiversity Fund, once it has been established. Indeed, these well capacitated areas may well act as pilots for disbursement of the first rounds of funding, as described in Output 3.1, to test the mechanism for disbursing funds.

Output 3.4: Lessons learned by the project through participatory M&E are used for overall knowledge management, enhancing synergies, sharing experiences and learning

- There is a strong emphasis in Outcome 3 on testing, piloting, demonstrating and learning.  The activities in all three components will be monitored (see also Section VII on the M&E framework). The project team and partners will monitor the implementation of all activities that are undertaken. In other words, when the project undertakes any activity, the implementation and results of that activity will be monitored with reference to the baseline established at the start of the project. This will lead to the project team and partners making conscious decisions about the activities that are undertaken – questioning why the activity is necessary, what will be the intended result or impact, and how the result or impact should be demonstrated through monitoring processes. This will also include those activities that are undertaken adaptively.

- The project will also monitor the use of the outputs of the project – including, for example, the results of the institutional analysis and planning process (Output 1.1), the business plan (Output 1.2), the constitution of the Biodiversity Fund (Output 2.1).

- In addition, the project will support direct surveys to demonstrate the results of the project, as necessary. For example, the project will support aerial surveys of crocodile populations (including nest counts) in the Sepik wetlands at the beginning, at the MTR stage and at the EOP.

- Throughout the M&E processes, relevant stakeholders will be involved – with six aims: i) to build their capacity to carry out such baseline surveys and M&E processes, ii) to demonstrate the value of the results to them, iii) to ensure gender and age-group balance in M&E processes, iv) to transfer a degree of ownership and responsibility to them, v) to ensure adaptive management of the project as it proceeds, and vi) to demonstrate the value of well-planned (and implemented) projects. The stakeholders that are most obviously involved in the M&E processes are the members of the PB (both voting members and observers – see Section VIII). Whenever possible, the project will invite other people to the PB meetings, especially when there are aspects relevant to them being discussed. In all other cases, when M&E processes are being carried out, stakeholders will be involved to the degree that is practicable. Furthermore, during the MTR and TE of the project, stakeholders will be consulted adequately.

- The project team will share the lessons learned from the project – focusing on sharing case studies, recommendations and methodologies – and inviting feedback from similar experience elsewhere.  The emphasis will be to share lessons nationally and regionally (Asia-Pacific).

- Lessons will be shared using the following platforms: i) the project website that will be established especially for this purpose, and ii) conferences, symposia, roundtables and workshops that will be carried out expressly for sharing the information and lessons. Indeed, the project will organise and fund an annual forum on the protected areas of the country: these will provide an ideal forum for sharing experiences and practices.

- One of the key objectives of the information sharing will be to demonstrate the value of conservation (protected areas and natural resource management in particular) in concert with owner-community livelihood improvement as win-win opportunity to a variety of targeted local, sub-national and national audiences, and to build confidence in the value of long-term planning – using the project’s successes as examples.

- Partnerships. The project is keenly aware that partnerships are pivotal both to the success of the project and to the long-term sustainability and impacts within the biodiversity conservation sector in Papua New Guinea; this will be confirmed in the analysis that will be carried out under Output 1.1. The project will, therefore, collaborate with a number of on-going projects and programmes within the country with the objective of leveraging results and funding, and avoiding duplications. The collaborations will also allow for lessons and best practices to be shared and, therefore, to increase the overall positive impact on biodiversity in PNG.

Table 6. Proposed partnerships and synergies for the project

| Project/Programme | Synergies and/or relationship with project |
| --- | --- |
| Ministry of Environment, Conservation and Climate Change | The project falls under the Ministry of Environment, Conservation and Climate Change, and as indicated above, the inclusion of the establishment of the Biodiversity Fund within the project was partly as a result of the personal request of the Minister of Environment, Conservation & Climate Change. |
| Conservation and Environment Protection Authority (CEPA) | CEPA is the agency for the protected areas at the central level of government. As discussed in Section II, CEPA has a role and responsibility within the protected area system – although this is not well defined; in response, CEPA’s mandate will be defined under Output 1.2. CEPA’s capacity to fulfil its mandate will then be built under Output 1.3. |
| LLGs, Districts and Provincial Governments | These administrative units, especially in the vicinity of the sites that will be funded under Outputs 3.1 and 3.2 are critically important for the success of the project. This is especially the case with the LLGs that operate at the level of the communities that are the principal owners and users of the land. The LLGs (as well as other levels), have development planning processes into which the protected areas – as well as funding provided by the project and the Biodiversity Fund – should be factored. |
| GEF-4 project | The UNDP-GEF-4 project (Community-based Forest and Coastal Conservation and Resource Management in PNG) is designed primarily to ensure that community-conserved forest areas are integrated into the national PA system, increasing the national PA estate by at least 1,000,000ha of IUCN Category VI-equivalent protected areas. The implementation of this project document will help to develop effective natural resource management and financing systems for community conservation areas in Papua New Guinea. The project will work on the following key components in order to succeed with the implementation and execution of the project: 1) Enabling national environment for a community-based sustainable national system of Protected Areas (PAs) containing globally and nationally significant biodiversity; 2) Identification and establishment of new PAs in the country; 3) Undertaking Conservation Area (CA) management planning and signing partnership agreements with communities; and 4) Providing capacity development and support for implementation of CA Management Plans. By strengthening revenue streams to support community-based conservation, the project should also be contributing to sustainable financing of PA systems. In other words, there are overlaps with the GEF-4 project and this GEF-6 project will assume the responsibility for the majority (but not all) the sustainable financing issues. |
| GEF-5 project | The UNDP-GEF-5 project (R2R Strengthening the Management Effectiveness of the National System of Protected Areas) aims to operationalise the protected area policy as well as support the institutional transition from the former DEC to CEPA. The project will also strengthen the links between central government’s policy and institutional systems with PAs that are being established by community landowners and conservation partners in key biodiversity areas throughout the country. The project has two components, i) to support management capabilities of the PNG State, strengthening policies relating to PA management, building capacity, implementing training programs and working to ensure effective management of Varirata NP, and ii) to support two other conservation areas (Yus CA and the proposed Torricelli CA) |
| USAID programme | Towards the end of 2018, it is anticipated that a new USAID programme will commence in PNG, with three strategic approaches to address the threats to biodiversity: i) strengthening capacity for environmental decision making, ii) provision of legal and policy education and training, and iii) integrated land use planning. At present, the shape of the programme remains unknown but it is likely to be a competitive small grants program, with grants awarded to local community groups or other CBOs. In other words, there are significant synergies with this GEF-6 project and, indeed, duplications must be avoided. |
| WCS | Establishment and sustainable financing of MPA and LMMAs - Donor: Blue Action Fund - Project objective: Establishment and implementation of MPAs; Improvement of coastal livelihoods in fisheries-dependent communities; Consensus building around identified legal and institutional pathways to operationalize sustainable financing of MPAs and LMMAs (building on Fiji’s experience) - Project site in PNG: Kavieng District, New Ireland Province; - Project period: mid 2018-2021 - Budget for PNG: $1 million |
|  | Sustainable Wildlife Management Project - Donor: European Union - Project objective in PNG: sustainable wildlife management through improved customary management - Project site in PNG: around Mt Wilhelm (building on an ongoing project funded by the Darwin Initiative) - Project period: mid 2018-2023 - Budget for PNG: $2 million |
| Mahonia na Dari Research and Conservation Centre | MND Marine Environment Education Program (MEEP) has been working for 21 years and visits about 12,000 people annually (8000 school children, 4000 community members) around all Kimbe Bay coastal districts, conducting Intensive MEEP programs to four Kimbe Bay High Schools covering about 100 students and sometimes their teachers; it also conducts two Teacher Training workshops (one at Madang Primary School Teacher Training College) for 30-40 primary school teachers and has day visits by about 350 students per year. It has an annual budget of K150,000 -K200,000 |
| Walindi Plantation Resort | As indicated in Section II, the Walindi Plantation Resort in Kimbe Bay has a relationship with the clans that own Kaula Island. This relationship has been developed on the basis on taxing tourists (and predominantly scuba divers) for visiting the islands and the reefs around the island and paying the clan these fees. However, the Kaula Island is not part of the formal protected area system; it was not even formed as an LMMA – nonetheless, it functions as the best protected area within the entire Kimbe Bay at present. This will, therefore, be used as a basis on which to build the Kimbe Bay Conservation Area – with Walindi Plantation Resort being a partner and stakeholder in demonstrating how this can be scaled-up across the entire bay. |
| Yus Conservation Area | Yus Conservation Area is the single protected area in the country for which there are good financial data. Yus also has developed its own Endowment Trust Fund – which, therefore, provides lessons for the functionality of the Biodiversity Fund as it is being established and as it is operationalised. The area will also be used as one of the pioneers for trialling the Biodiversity Fund disbursement under Output 3.1. |
| Mainland Holdings Ltd (MHL) | Mainland Holdings Ltd is a key to the success and future of the Sepik Wetlands area. MHL has been operating in the area for a number of years, buying crocodile eggs from local communities. These are then incubated in their crocodile farm in Lae before the crocodiles are slaughtered and the skins exported. MHL has also built a relationship with SWMI in an attempt to improve the sustainability of the system and chain. MHP will remain an important partner in the development of the Sepik Wetlands. |
| Sepik Wetlands Management Initiative (SWMI) | The Sepik Wetlands Management Initiative (SWMI) was established by WWF in an effort to improve the management of the harvesting of natural resources in the Sepik Wetlands – with a focus on the crocodile populations. With removal of the support by WWF, the governance of SWMI (together with CEPA’s representatives in the area) has significantly deteriorated – although support for SWMI has continued primarily through the UNDP-GEF SGP. Nonetheless, SWMI represents an important partner in the area and the project will work with them to build their capacity and improve governance. |
| New Guinea Binatang Research Centre (BRC) | NG Binatang Research Center is one of the leaders in biodiversity research and postgraduate student training in PNG, developing the concept of funding rainforest conservation areas through logistical and professional support of local and international research. This concept has been applied in the Wanang Conservation Area (conserving lowland rainforest) and is being planned for the Mt Wilhelm with elevation rainforest gradient from 200 to 3700 m asl., which is also focal area of the present proposal. The research-based funding model, its application in Mt Wilhelm, and the BRC’s ability to build local and national capacity in biodiversity research represent important synergies with the current project. As a result, the BRC is an important partner for the project. |
| CEPF | The CEPF has an ongoing programme covering the East Melanesian Islands Biodiversity Hotspot – which includes the Bismarck and Louisade Archipelagos and the Trobriand Islands of PNG. The CEPF provides small grants to non-state actors – most often civil society organisations. The value of the CEPF investment is USD 9 million over a period from 2013 – 2021 and there are significant synergies and lessons to be learned from the CEPF investment in the region. |
| Mama Graun Conservation Trust Fund | As discussed above, Mama Graun was established during the Ci/WB/GEF Forestry and Conservation project and was capitalised with a USD 10 million grant from the GEF. Even on early closure of the project, Mama Graun continued to operate and built systems for delivering funds to communities across the country. These systems are well thought out and valid and will be adopted (and adapted, as necessary) by the Biodiversity Fund for their systems. |
| PNG LNG | PNG LNG is a joint venture that includes at least six different co-venturers – including ExxonMobil. PNG LNG has a Biodiversity Offset Program which aims to strengthen existing Protected Areas as well as create new ones. PNG LNG’s target is to enhance or create 50,000 hectares of conserved land in three elevation zones (Montane, Mid-montane and Lowland areas). In addition to creating Protected Areas, the Offset Program provides technical capacity building at community and national level to help ensure sustainable conservation as well as a program in conservation planning for the Kikori River Basin. The project will learn from the practices that are put into place by PNG LNG (under Output 3.3) and use the protected area with which the PNG LNG is engaging as testing areas for delivery of funding from the Biodiversity Fund (under Output 3.1). |
| TNC | TNC has been active in PNG since 1993. From the perspective of the project, it has invested heavily in Kimbe Bay – including establishing the LMMAs across the Bay. The success of the LMMAs is open to question; however, TNC bring experience and expertise to the equation. |
| James Cook University, Australia | JCU has been conducting research on the coral reefs of Kimbe Bay since 1996 – with two ongoing, long-term projects. The first of these has been monitoring the benthic cover, fish abundance and species diversity on 14 reefs annually since 1996. The reefs monitored include 8 inshore reefs that have been closed to all fishing and collecting since 1999, and results show that marine reserves have been beneficial for a number of Surgeonfish species that are targeted by local fishers. The second long-term project, which started in 2004, has been examining patterns of reef fish dispersal and connectivity among reefs, focussing on the Orange clownfish and Vagabond butterflyfish. There have been numerous shorter-term projects, including 26 PhD student projects and 30 Masters/BSc Honours student projects on a wide range of topics, with a focus on the effects of habitat structure on coral reef fishes. There has been a JCU resident PhD researcher staying at Mahonia Na Dari for extended periods since 1998. Part of this voluntary role involves communicating results of JCU research with the local communities of Kimbe Bay, as well as visitors to the area, and assisting Mahonia Na Dari staff with environmental education programs. The results of the research have been published in the international scientific literature. In other words, the work has had a significant impact across the scientific world. However, despite this, JCU has not contributed to the financial sustainability of any conservation work that may be underway in Kimbe Bay – and this stands in stark contrast to the model being implemented by the Binatang Research Centre in both Wanang and, in the future, in Mt Wilhelm. |
| WWF | WWF was pivotal in starting work in the Sepik Wetlands and establishing SWMI. While they have subsequently withdrawn from the area, their history in the region remains interesting and informative. |
| Barrick/Porgera Joint Venture | As with the PNG LNG, Barrick/Porgera Joint Venture has been providing support to the Headwaters of the Strickland and the Kaijende Highlands protected areas. As with the areas supported by the PNG LNG, the project will learn from the practices that are put into place by Barrick – especially the success of securing REDD+ funding (under Output 3.3) and use the protected areas as testing areas for delivery of funding from the Biodiversity Fund (under Output 3.1). |
| FORCERT, CELCOR, BRG | These three civil society organisations represent key opportunities in PNG and have the potential to assume significant roles within the project. The organisations have different and complementary roles – but each has a significant connection and understanding of community development and community processes. The Project Implementation Unit should look to these three organisations to support the implementation of different aspects of the project, including establishing protected areas and working with communities. |

- Risks and Assumptions.  As per standard UNDP requirements, the Project Manager will monitor risks quarterly and report on the status of risks to the UNDP Country Office (UNDP-CO). The  CO will record progress in the UNDP ATLAS risk log.  Risks will be reported as critical when the impact and probablity are high (i.e. when impact is rated as 5, and when impact is rated as 4 and probability is rated at 3 or higher). Management responses to critical risks will also be reported to the GEF in the annual PIR.

- A number of risks were identified in the PIF; these have been updated during the PPG phase. The project has specifically been designed to overcome the principal risks – in particular those associated with the management and implementation of the project.

- There are three primary risks associated with the project – all of which have been described above (see Section II and IV).

- First, there are issues associated with the mandate of institutions and organisations that are either involved in the protected areas of PNG. The purpose of Output 1.1 is to examine the protected area system to determine its needs for institutional and organisational support (including key aspects such as the legal and financial support that protected areas need) and to align the mandates of the institutions and organisations to the realities of the PNG context. While this seems simple and logical enough, there are significant risks here. The current perceptions in CEPA are built on models from elsewhere – all of which are not applicable in whole for the PNG context. As stated in this document, the PNG context is unique – which obviously calls for a unique solution. The challenge is made more profound because it demands two things from CEPA: i) to act as a facilitator and provider of services to the protected areas, and ii) to stand up to other branches and agencies of government that may be seeking to exploit the resources that may be harboured within the protected areas – and thus, CEPA needs to provide legal support to the protected areas.

- Second, the project will be implemented under UNDP’s Nationally Implemented Modalities (NIM) with UNDP providing Support Services (as described in Section VIII).  In effect, that means that UNDP manages the project on a day-to-day basis – with government oversight through the Project Board. The project transfers specific responsibilities to the Head of the Environment, Climate Change and Disaster Risk Management Portfolio at the UNDP-CO. These responsibilities need to be fully assumed.

- The final main risk is that the Biodiversity Fund is insufficiently capitalised. The project has responded to this risk by allocating significant budget to fund raising/resource mobilisation – but this is still no guarantee that the Biodiversity Fund will be adequately capitalised. For example, one of the vagaries is that KfW is not present or active in PNG; an unfortunate circumstance because KfW has been one of the most generous donors to conservation trust funds in the world.

Table 7: Project risks, updated during the PPG phase

| Description | Type | Impact & Probability | Mitigation Measures | Owner |
| --- | --- | --- | --- | --- |
| Risk 1: The government does not allocate adequate resources (both human and financial) in response to the result from the project’s incremental processes and impacts. This project will build capacity of government agencies, hence will demand a higher (or additive) level of resource allocation from the government during and following the project implementation. | Financial and organizational | Probability: 4 Impact: 3 HIGH | The project will strive to increase resource allocation from the government to the protected area system, both through the business plan (Output 1.2) as well as the fund-raising/resource mobilisation strategy (Output 2.3) including establishment of government led recurring revenue streams for the Fund. The capitalization of the Biodiversity Fund using GEF funds will only take place once specified milestones have been reached, including the provision of Government cofinancing and the establishment of recurrent funding mechanisms. The government has committed 5 million cash cofinancing and 15 million parallel cofinancing in support of project implementation. UNDP will track the delivery of this cofinancing through its reporting systems and ensure that it is fully realized. In addition, a fundraising strategy will be developed and implemented, including: i) targeting potential donors by preparing detailed project proposals, ii) liaising with different funders, and iii) building working partnerships with funding agencies/ institutions; reviewing the potential to mobilise REDD+ and other carbon financing as well as other innovative mechanisms for generating resources for the Biodiversity Fund. For example, Debt for Nature Swaps; determining the feasibility of including taxes, levies and revenue streams from other sources – including biodiversity offset, green taxes (e.g., a round-log tax as has been suggested in the PA Bill) and payment for ecosystem services from hydropower schemes. | GoPNG, UNDP-CO |
| Risk 2: Limited institutional capacity, mandate, roles and responsibilities leading to limited institutional functionality, even with capacity development efforts Institutional issues and institutional functionality (CEPA, provincial governments, UNDP-CO) could undermine the project’s ability to be implemented in an effective and efficient way; it may also impact the management effectiveness of protected areas. This would undermine the impacts that the project might have. | Organizational | Probability: 3 Impact: 3 MODERATE | UNDP has policies and procedures relating to Its National Implementation Modality (NIM) of project implementation that provide safeguards against inadequate implementation capacity and the risks of mismanagement. Consequently, during the PPG, a capacity assessment of the project implementing partner (CEPA) and HACT micro assessment were conducted in order to ensure that adequate capacity exists to support project implementation (see Annex O). This project will receive full UNDP CO support to NIM meaning that there will not be any cash transfer to the government because of the level of risk rating (HACT Assessment). PIU will be recruited by UNDP which will consist of Chief Technical Officer; Project Manager; Safeguards Officer, Finance. In addition, capacity development scorecard baselines have been assessed during PPG for key provincial government partners (see Annex P). The project will address relevant capacity limitations by defining the mandates and carrying out an institutional mapping exercise (Output 1.1) and systematically building capacity based on the result of that exercise (Output 1.3). The management arrangements and feasibility analysis make proposals to streamline and improve the project management and implementation efficiencies. | UNDP-CO; UNDP-GEF RTA |
| Risk 3: Project implementation may be afflicted by mismanagement and corruption, based on the experience of similar previous projects (e.g. the Mama Graun Conservation Trust Fund) | Organizational | Probability: 1 Impact: 4 MODERATE | The project has been designed with numerous measures to ensure its effectiveness and efficiency, and the governance arrangements are such that the project will be implemented in a transparent and accountable way (see Section VIII Governance and Management Arrangements). These measures include: an unusually strong role of the UNDP CO in hosting the PMU and directly managing the disbursement and accounting of GEF funds; strong counter-corruption measures specified in Section XII Risk Management, including a requirement that the Implementing Partner will ensure that its financial management, anti-corruption and anti-fraud policies are in place and enforced for all funding received from or through UNDP. Regarding Outcome 2, Biodiversity Fund should be built on two fundamental principles: i) they are immune from political interference and ii) they are secure from embezzlement or corruption. One of the lessons from the 2001 – 2006 WB/GEF Forestry and Conservation Project was that “projects in difficult governance environments … benefit from formal assessment of … commitment using some form of social mapping”. In this case, the key stakeholders are community groups owning/using and protecting their own communal lands. | UNDP-CO |
| Risk 4: The Biodiversity Fund is insufficiently capitalized. While in the short- (5 years) to medium-term (10-15 years) this risk would have limited impact, in the long-term, inadequate capitalisation of the Biodiversity Fund would result in the system backsliding to the present status within a maximum of ten years. This would undermine the sustainability of the project’s processes and impacts. | Financial | Probability: 2 Impact: 4 MODERATE | The project supports development and implementation of both a business plan for the protected area system (Output 1.2) and a fund-raising/resource mobilisation strategy that will be specifically designed to leverage funding for the Biodiversity Fund (Output 2.3). The project will support establishment of recurring revenue streams to the Fund using government’s fiscal instruments. In addition, the use of the transparent and accountable UN Multi-Partner Trust Fund (MPTF) and other reputable entities as necessary as a vehicle for designing the Biodiversity Fund will build trust. | UNDP-CO; UNDP-GEF RTA; UNDP-GEF Directorate; MPTFO |
| Risk 5: PA Bill not approved leaving significant legislative gap in PA system The PA bill is still pending approval by the NEC and, therefore, presents a risk to the project. | Political | Probability: 2 Impact: 4 MODERATE | The GEF-4 project that is under implementation will continue to support the process aiming for the approval of the PA Bill. Once implementation starts on this project, the situation will be (re)assessed (as part of Output 2.1) and it will be mitigated as best as possible. | GoPNG, UNDP-CO |
| Risk 6: “land grabbing” and corrupt practices leads to loss of protected areas. Even with the legal protection offered by the constitution, land grabbing pose serious threats to PA in the country. | Political/ organisational | Probability: 2 Impact: 4 MODERATE | The additional legal protection offered by protected areas (through conservation deeds) will deter such ‘land grabs’ to occur. Indeed, the exercise to identify mandates will demonstrate the need for CEPA to provide legal services to protected area owners and managers to counter such land grabs (under Output 1.1). | CEPA; Ministry of Environment and Climate Change |
| Risk 7: Major natural and climate induced disasters including other environmental risks – may affect the implementation and results of project initiatives. Besides the likely impacts of Climate Change, PNG is also susceptible to other natural disasters (including earthquakes, volcanoes and, to a lesser extent, tsunamis, drought and floods). At a local level, the impacts of any one of these factors could be significant, both on the livelihoods of the people in the disaster area but also on the natural environment. | Environmental | Probability: 3 Impact: 3 MODERATE | The project will put in place strategies to mainstream environmental and climate risks into the overall project interventions so that mitigation measures are well thought through during the planning process, as follows. By contributing to the financial sustainability of the PA system and defining the roles and building capacities of organisations with respect to PAs, the project will strengthen their management effectiveness including climate change adaptation being integrated into PA management planning processes. By adopting ecosystem-based approaches, the project is also contributing by expanding the protected area system by over 2.83 million ha and increasing the representation of two ecosystems that are currently under-represented within the system. The UNDP CO and government IP through the PMU and PSC will also ensure close alignment of the project with their climate change programmes and projects. | Ministry of Environment and Climate Change; UNDP-CO, Project Team |
| Risks from Social and Environmental Screening Procedure (Annex I) |  |  |  |  |
| Risk 1: Not all community members (disadvantaged groups, vulnerable, minorities, poor, women) might be fully engaged in decision that affect their land, culture and rights The risk relates to: Right holders i/e community groups not being able to claim their rights due to their own limited knowledge/ capacity/power; Duty bearers (namely CEPA, provincial departments and local level government) do not meet their obligations to deliver adequate services/legal protection, etc. to the communities engaged in existing or to be established Protected Areas e.g. against illegal occupation; Referred to SESP Attachment 1: Principle 1, 5; Principle 1, 6; Principle 3/standard 5, 5.4; Principle 3/standard 6 6.1 & 6.2; Principle 3/standard 6, 6.5; Principle 3/standard 6, 6.8. | Environmental and Social | I = 4 P = 2 MODERATE | Before the project’s inception, further assessments of all environmental and social risks will be undertaken and the required management plan(s) will be prepared, and then applied during project implementation. Risk management measures include: The project will support CEPA, provincial governments, district administrations and LLGs in adequately understanding their mandate, roles and responsibilities with respect to community-owned protected areas (Output 1.1) and subsequently acting upon that, e.g., with respect to legal protection against land grabbing. The project will also build the capacity of CEPA and these other state actors such that they can fulfil their described mandates, roles and responsibilities (Output 1.3). Under Output 3.1, there will be active demonstration of how this is best done. Stakeholder analysis and consultation was carried at the national, local level government, NGOs, private sectors and communities were carried during the project formulation (Annex F). A stakeholder engagement plan (Annex J) was prepared clearly outlining the mechanisms to facilitate engagement and participation of different levels of stakeholders in the project implementation. Budget for Social and Environmental Safeguards Officer (SESO) has been built into the project to monitor and manage social and environmental risks during implementation. | Safeguards Officer, Project Manager |
| Risk 2: Unequal/unfair distribution of benefits from the use of Traditional Knowledge (eg. Non-timber forest produce, use of genetic resources by companies, etc.). Referred to SESP Attachment 1: Principle 3/standard 4, question 4.2; Principle 3/standard 6, Question 6.9 | Environmental and Social | I=3 P=2 MODERATE | To be assessed further, before project inception. Project activities all relate to the establishment and improved management of Protected Areas on community owned land, specifically designed to benefit the community and protect community interests, and the sustainable protection of ‘critical habitats and/or environmentally sensitive areas’. CEPA is obliged to provide the legal protection, and technical protection to register the PA (as determined under Output 1.1 with capacity built in Output 1.3). Under Output 3.2, the project will identify community-conservation areas; negotiate meaningful natural resource management agreements; sign agreements with the owners and users of those areas; carry out value chain analyses for the other natural resources that are being harvested from the area to determine the feasibility of on-site value addition and establishing transparent, accountable and traceable supply routes. | Project Manager & Safegurads Officer |
| Risk 3: Project outcomes and interventions will be vulnerable to potential impacts of climate change and other natural disasters Referred to SESP Attachment 1: Principle 3/standard 2, Question 2.2; Principle 3/standard 3, Question 3.5 | Environmental | I=3 P=3 MODERATE | To be assessed further, before project inception Risk management measures include: The project will mainstream CC and DRR into the overall planning process of the project interventions. For instance, the project will adopt an ecosystem-based approach in its pilot areas – which will allow for adaptation to climate change. Communities and project areas that are affected by destructive logging activities will be provided the platform to seek justice (through NGOs and CBOs that support community rights; e.g. CELCOR). Budget for Social and Environmental Safeguards Officer (SESO) has been built into the project to monitor and manage social and environmental risks during implementation. | Safeguards Officer and Project Manager |
| Risk 4: Many women/leaders shared their gender equality and other concerns and proposed actively addressing/eliminating GBV and promoting women leadership roles. Referred to SESP Attachment 1: Principle 2, Question 3 | Social | I=3 P=2 MODERATE | To be assessed further, before project inception. The project has well elaborated gender and power strategy (see Section IV of the project document) with various mechanisms to work towards addressing GBV and promoting women leadership roles among the communities. Gender analysis has been completed and a Gender Action Plan prepared (Annex K) | Project Manager |
| Risk 5: The ecosystem and habitants could be damaged by uncontrolled tourism and harvesting if not done sustainably or best practices are not followed. Referred to SESP Attachment 1: Principle 3/standard 1, Question 1.2; Principle 3/standard 1, Question 1.7; Principle 3/standard 1, Question 1.9 | Environmental and social | I=2 P=2 LOW | Project will provide education and awareness to communities seeking to take in tourist (e.g. through eco-tourism) on importance of quality/safe tourist facilities; hospitality courses and general awareness on importance (and handling potential risks) of tourists visiting communities and on value of the cross-cultural exchanges that will influence the young generation’s future. Tourism best practices will be shared at the annual PA forums. Tourism companies/operators will be subject to codes of conduct. | Safeguards Officer and Project Manager |
| Risk 6: community groups protecting their rightful control over their natural resources may be exposed to threats of actual violence by logging/ mining companies and others wanting to gain access and control over these lands as has been shown. Referred to SESP Attachment 1: Principle 1, Question 8 | Environmental and social | I=4 P=2 MODERATE | To be assessed further, before project inception. Risk management measures include: The stakeholder consultation and assessment undertaken during the project formulation (including the lessons from the on-going GEF-4 project) recognizes the primary motivation of the communities to establish protected areas within the land and marine areas is to seek robust legal protection over their land. The project has been designed to be inclusive both in the design and the during implementation. The purpose of the institutional analysis (Output 1.1) is to ensure that the mandates of institutions and organisations involved in the protected areas of the country match the actual needs; this is done in the acknowledgement that over 90% of the protected areas are owned by local communities. The risk should be offset by the support of the project (through legal support and building capacity; Outputs 1.1, 1.3, 3.1 and 3.2). Once established and gazetted as Protected Area (or under a conservation deed – providing legal protection for the land), the government is obliged to provide the protection required against abuse, violence or dispossession. The stakeholder engagement plan (Annex J) has been prepared and it outlines the mechanisms to facilitate engagement and participation of communities including other stakeholders in the project implementation. | Safeguards Officer and Project Manager |

- The UNDP Social and Environmental Screening Procedure (SESP; included as Annex I of the UNDP Project Document) was finalized during the project preparation as required by UNDP’s Social and Environmental Standards (SES). The SESP identified a total of six risks of which one has been assessed as low significance and five as moderate significance. Therefore, overall SESP risk categorization for the project is ‘Moderate’. Notably, Standard 6 on Indigenous Peoples, among other SES Principles/Standards, has been triggered with a moderate risk because the project activities will take place on the lands of indigenous communities. Given the nature of the project and the country context, and in accordance with UNDP’s SES and the requirements associated with the triggered SES Principles/Standards, further assessment of the environmental and social risks will be undertaken for this moderate risk project before the project inception. This assessment will identify and be used to develop the required management measures/plans that will be undertaken during project implementation, including but not limited to: (i) the completion of further, potentially ongoing/iterative assessments; and (ii) the development of the appropriate management plan(s), as identified by the assessments (e.g. an Environmental and Social Management Plan (ESMP), or stand-alone management plans). All project activities contributing to these risks will not commence until the assessments have been completed and the management plan(s) have been approved and put in place. The development of the assessment and management plans will involve public consultation and public disclosure. Free, Prior and Informed Consent (FPIC) will be applied for all activities involving indigenous, disadvantaged, vulnerable and minority groups, including but not limited to the implementation of the management plan(s); the project-specific FPIC requirements will be documented in and implemented based on the subsequent management plan(s). As will be described in the management plan(s), a project-level Grievance Redress Mechanism (GRM) will be established during the first year of project implementation. The implementation of the management plan(s) will be overseen by the Safeguards Officer/ Project Manager and monitored throughout the duration of the project.

- Stakeholder Engagement Plan.  A large number of stakeholders were engaged and consulted over the course of the PPG phase (see Annex F).

- The project will be implemented on the principle that little will be achieved in isolation and as such whenever and wherever possible, the project activities will be implemented through partnerships and/or in collaboration with other actors, with the primary stakeholders, i.e., landowners/users (equally shared between women and men, young and older) supported to take maximum ownership of all processes. This is described in detail in the Stakeholder Engagement Plan (Annex J). There will be a number of key mechanisms through which this will function.  For example, the Project Board (PB) will be an inclusive forum and will offer an opportunity for state and non-state actors to provide oversight to the project (Section VIII and the draft TOR of the PB in Annex D). At a local level, the project will collaborate with all relevant actors.

- Gender equality and empowering women. Most rural communities in PNG do not suffer from food insecurity, shelter problems or poverty: nature’s abundance provides for most of their basic food items, cooking fuel, water and house construction materials. Sale of marketable produce (from gardens, fishing, hunting or – more recent- commercial farming activities) generally covers primary cash needs, although school fees for secondary education of both boys and girls are mentioned as increasingly problematic. Available food is shared equally between members of families, without discriminating according to sex.

- While the basic livelihood provision is fairly good for men and women alike, it became strikingly clear from literature, the visits and the overall assessment in preparation of the proposal, that local cultural traditions, colonial administrative heritage and particularly androcentric and patriarchal notions of male and senior age entitlements and hence dominance, not just determine division of labour between women and men, but in fact seriously restrict the social position and decision making power of women (and to a great extent of young people) in matters of daily life and planning for the future at personal, household and community levels.

- Though variations exist between communities and regions in terms of the (formal) position of women (e.g. in matrilineal communities), and their levels of financial autonomy, social status, decisions about planning their family (fertility control/reproduction) and control over the use of productive assets, the general conclusion is that the position of women in PNG is (nearly) always secondary to men; that women suffer from male dominance in all respects and that many women are subjected to serious (domestic) physical as well as sexual violence, often related to abuse of home brewed and – more recent home-distilled – alcohol. Women are almost exclusively responsible for managing the household affairs in terms of food preparation, fuel and water collection, rearing and caring for children, while also highly involved in food production in the gardens and with fishing, when living in coastal areas.

- With variations between communities and regions, many women in rural areas are organised in social groupings often through their participation in church related groups, much more so than their male partners in the communities. Formal community leadership, however, is generally in the hands of men only.

- Starting from the late seventies, a number of INGOs have promoted environmental protection through the establishment and (when possible) registration of conservation areas (WMAs and LMMAs), with foreign funds made available for equipment e.g. boats as well as fuel, stipends, etc. Some extracting industries have also invested in different forms of environmental protection as part of their CSR policies. Overall planning and environmental analysis and visioning was usually done by the staff of the INGOs. Community groups were established for the implementation of such environmental protection plans. At the community level, decision making was usually in the hands of management committees of elder men (including local chiefs and other established authorities), with only occasionally a few women members. For as long as funding continued, these WMA and LMMA committees existed and various protective activities were undertaken, but with little involvement of women or young (f/m) people. Most of the funded activities related directly to environmental (and specifically biodiversity) protection, with generally little attention for other (immediate or long term) needs that communities, and within them women, men, youth and ethnic minorities might have. Reportedly, there was hardly a sense of ownership of the selected activities by the communities: receiving the payments and equipment was the major driving force, to be involved and do the work required.

- The visits and assessments also show that men generally do not report serious changes in their natural surroundings, impacting their lives and hence they rarely express the need to protect their environment. With the increase of commercial activities, like oil palm cultivation, or employment in the oil palm and other industries, their reliance on access to fertile fishing or hunting grounds, or forest land for gardens has reduced, as part of their (male) needs and wants are now met by cash income.

- Women on the other hand, spoke of changes in the environment affecting them directly through decrease in the (easy) availability of fuel wood and roofing material, availability and access to clean and safe drinking water, as well as reduction of space for gardens to grow staple food, fruits and vegetables. With oil palm trees often planted in erstwhile vegetable gardens, the diet in many communities has changed as well. Increasingly fresh staple food, vegetables, fruits and fresh fish are replaced by industrially produced and often imported canned or packaged foods (which are often beyond their expiry/sell-by date). Reduced fresh food intake is likely to negatively affect personal health, which is already reported in some areas.

- Young people’s ambitions vary, in relation to their levels of education, opportunities for (self-) employment, proximity to urban areas and related transport and the strength of their cultural ties to the traditional community life. In many rural and remote communities, young boys (both unmarried and newly married) find little opportunities for (paid) work and hence many are idle at their parents’ homes. In many communities they reportedly engage in home brewing and distilling of alcohol for consumption and selling, for which they may even demand (and sometimes with violence) the little cash their wives or parents may have. Young and newly married girls are generally occupied in household activities and when land is available, food gardening and fishing.

- Some young people, both boys and girls, are conscious about the environmental changes and deterioration: they see the need for protection, but also feel that their voices are rarely heard by the older generation leadership.

- Mainstreaming gender.  More than only mainstreaming gender, the project needs to become gender transformative to ensure long term sustainability.

- In view of the felt needs of women (fuel, roofing material, clean water, food gardens, small fishes, and their management roles) and their deeper felt urgency and hence ownership of initiatives to protect their surroundings and address negative environmental changes, the project will pro-actively engage women in the choice, design and management of the project activities in their settings. Success and sustainability of any community development activity lies with the level of ownership, commitment and responsibilities taken for such activities by the community members concerned and hence, given their understanding of the urgency, it is foreseen that in many of the activities and activity management of the project women should be in the lead. Because some young people (male and female) show a long-term interest as well, their potential and practical roles need to be assessed as well in the start-up phase of the different project activities, looking at how they can be adequately heard and involved in planning and decision making.

- Gender power relations, and patriarchal traditions do not change overnight and hence, activity design meetings will also need to involve and convince traditional male leadership to obtain their support for the activities to be undertaken as in the long run the whole community will benefit.

- The more recognition and support for the active role of women in (some of) the environmental protection and livelihood activities undertaken can be raised, the greater the scope for the project to go beyond only gender mainstreaming during the project’s life and actually contribute towards gender transformative action: recognition for the role women play, gender-balanced sharing of planning, implementing and managing of the protective activities, rather than women only following male instructions in line with traditional androcentric practices. Once stronger organised and vocal, and concretely involved in project management, women are likely to also start addressing other issues of male dominance, control and (sexual) violence. An active role by young people, male and female, with dreams and aspirations that often differ from the traditional elder male dominance, may enhance a positive social change process. If adequately guided and trained, young men and women can help to reduce physical and gender-based violence and thereby contribute to a more conducive and cooperative community life that is likely to address environmental protection because it is recognised as a common need.

- Such change processes require strong civil society support in the bottom-up organising and planning phases. But it will also require government services actually getting delivered to the communities: quality (hence context-adequate) education, delivery of required reproductive and other health services, credit/rural banking and marketing opportunities, and adequate and affordable means of communication.

- Whereas the minimal requirement of any new development project should be ‘do no harm’, hence not being gender-negative and increasing inequalities, or gender blind, the proposed environmental protection project provides a crucial and indispensable development opportunity. It will aim to move towards gender- and age-transformative action, as a sustainable win-win situation for everyone. In the planned project life of only seven years, this may not be totally achieved, but the processes and structures put in place are planned to at least carry the ingredients towards gender transformation and hence gender justice, which is beneficial to all.

- One of the crucial elements for this to happen, is for women and young people to also play an active role in the monitoring and evaluation processes of this project. What changes, brought about by project activities, do they consider sustainable improvements in their life? What are the indicators they want to use, to monitor progress towards the desired changes? In the start-up phase of the project, therefore, all concerned and particularly women and young people (f/m) will need to be trained and guided in formulating their own baseline, setting short and longer-term goals, as well as monitoring mechanisms to measure progress and address problems. The ultimate financial sustainability of protected areas will greatly depend on the level of acceptance of responsibility for adequate management and handling of community owned land, which in turn will relate to the opportunities of women, men and young people of the communities to equally benefit from such protection.

Table 8: Proposed gender mainstreaming actions for project implementation

| Outcome/ Output | Gender Mainstreaming Actions |
| --- | --- |
| Component 1: Developing the enabling conditions for improving the sustainability of the protected area system |  |
| Output 1.1 Better understanding and acknowledgment of potential active role of women and young people (F/M/T) in environmental protection, based on their higher awareness and expressed interests | Proactive inclusion of local women and women organizations and young peoples and their organisations in working groups and committees involved in 1) the baseline surveys and 2) subsequently in the development and 3) implementation of PA Management Plans; Gender Mainstreaming will be addressed in the PA MPs. For monitoring purposes all participants of the management planning will be disaggregated by gender and age in the reporting documents. The management plans are expected to lead to the development of PA gender and age balanced Management Committees; such committees will therefore be comprised of at least 65% women and young people |
| Component 2: Establishment, operationalisation and mobilization of funding for a Biodiversity Fund |  |
| Output 2.3: Sources of Biodiversity Fund | Both sourcing and investment of capital for the Biodiversity Fund are bound by ethical banking principles: hence, must exclude capital/investments from/for activities that: 1) (potentially) contribute to, perpetuate or condone gender inequalities, and discrimination on the basis of gender and age 2) (potentially) contribute to negative effects on biodiversity and sustainable environmental protection (which disproportionally negatively affect women and girls) 3) (potentially) contribute to arms, drugs and sex industries, including trafficking in humans, (which disproportionally negatively affect women and girls). |
| Component 3: Strengthen the management capacity and financial sustainability of individual protected areas |  |
| Output 3.1: Active role of women and young people | Funding from the Biodiversity Fund for activities in the (prospective) protected areas will include rules and conditions that guarantee equal access to, and control over funding received for activities planned by women’s group and young people. Women and young people and their organised groups are encouraged, supported and capacitated (by qualified local and national CSOs to take up active roles in the management (planning, implementation, oversight) and contributions to financial sustainability of the (potential) protected areas |
| Output 3.1 and 3.2: Addressing GBV as condition | With prevailing high levels of Gender Based Violence (GBV) and domestic violence seriously violating the rights of (primarily) women and girls, but also of boys and men and thereby hindering sustainable development of communities and effective environmental protection, no support (financial of otherwise) will be provided to communities of (potential) protected area, unless there is commitment and practical action by the community to address these violations. Communities willing to address and terminate GBV and domestic violence will be given support by relevant CSOs in order to qualify for financial and other support for their (potential) protected area |
| Output 3.1 and 3.2: income generation for livelihood and financial sustainability | Women’s and young people’s groups will be encouraged and supported (with knowledge, training and investment capital) to undertake economic activities that generate income for livelihood development, support economic independence, while also benefitting sustainable financing of biodiversity and environmental protection, by maximising locally added value to sustainable harvesting and processing of commercially valuable plant species prior to selling. |
| Output 3.3 and 3.4: Learning best practice | While the majority of Outcome Three relates to piloting, testing and learning, Outputs 3.3 and 3.4 are specifically about learning – and this will include learning best practices regarding gender and age inclusion across protected areas in the country. The annual protected area forums that are planned and budgeted provide an ideal forum for sharing experiences and practices. |

- South-South and Triangular Cooperation (SSTrC). The proposed project will draw off and contribute to the SSTrC in the following ways: Sustainable development pathways. The best (and worst) experiences of the project will be shared on the internet via the project’s website. Similarly, the project will draw off the best experiences in other countries going through similar processes: there are many examples of Biodiversity/Protected Area/Conservation Funds around the globe – and the project team, with the support of the UNDP-GEF team in Bangkok, will explicitly seek to learn from good practices (where things have worked well) such that these learnings may be put into practice in the Biodiversity Fund that will be established under this project. The South Pacific Regional Environmental Programme’s (SPREP) regional program on Biodiversity and Invasive species and the Pacific Community (SPC) could both benefit from and contribute to this initiative and will be included in regional coordination efforts, including on AIS issues.

- In addition, while community-based activities have been the focus of work in PNG for many years, it is evident that there could be benefits from drawing and learning off other examples of community-based protected areas (e.g., the Northern Rangelands Trust in Northern Kenya, see http://www.nrt-kenya.org in which, as with the land tenure system in PNG, there is communal ownership of the land) or of community-based natural resource management (e.g., the Participatory Forest Management systems developed in Ethiopia, which are specifically designed to manage people’s access to and use of natural resources – while transferring the responsibility of managing those resources to the people following an extended period of negotiation, agreement and capacity development). Obviously, the process of learning and applying lessons from other models requires analytical thinking and determination of relevance; PNG’s situation is comparable in many ways but unique in others and a simple copy-cat process will almost definitely fail.

- Sustainability and Scaling Up: The project will invest considerable resources to increase the likelihood of sustainability of the processes that it establishes and the results that it will have. The project will take into account various aspects of sustainability – including financial, socio-political, institutional and governance, and environmental sustainability.

- This project is specifically designed to build systems that will contribute to the sustainability of the protected area system of the country. More particularly, the project will be building financial sustainability; this will hinge primarily on the establishment and functionality of the Biodiversity Fund. However, the project will not only focus on financial sustainability, but it is also expected to have other profound impacts which, in turn, will also lead to sustainability within the system.

- First, the analysis of the mandates of all the organisations involved  in protected area management will lead to clear understanding of each organisations’ roles and responsibilities (Output 1.1): a better understanding will lead to a better managed and more sustainable institutional system.

- Second, there will be a strong emphasis on developing capacity throughout the project (Output 1.3 and throughout Outcome 3); improved capacity is pivotal to sustainable institutional and socio-political systems.

- Third, the project, uniquely, recognises the ownership of the majority of the protected areas of the country (i.e., that the majority of the protected areas are owned by communities) and that the management of the protected areas is inextricably linked to the well-being of those communities. It has been stated in various places in this project document that “biodiversity conservation” is not the primary objective of the people and until their primary concerns are addressed, “biodiversity conservation” will remain a secondary or tertiary concern. It should be noted that this is “biodiversity conservation” as a goal in and of itself; the people are wholly dependent on natural resources and as such, sustainable management and use of natural resources is a primary goal of the local communities. The project also recognises that the well-being of those communities (and their diverse categories and interest groups) is not just linked to having (both environmentally and financially) successful livelihood strategies but also that overcoming gender inequality and other power issues (including gender-based violence) is fundamentally important to sustainability of the system as a whole – and especially to socio-economic sustainability.

- In addition to these project-specific activities, the standard measure to improve the likelihood of sustainability will be applied. Therefore, for example, the likelihood of financial sustainability will be enhanced at each stage of the project’s implementation. The PIU will consider the financial implications of each of the activities and processes that are being implemented.  The PIU will consider which institution is involved in the continuation (and replication or upscaling) of the processes beyond the life of the project.  The PIU will implement all processes in partnership with the involved institutions and work to garner commitments from those institutions such that the likelihood that they will continue beyond the life of the project will be increased. Many of the assumptions identified in the project’s results frameworks pivot on aspects of financial sustainability and uptake by different institutions – especially government partners. The project’s approach will be inclusive and participatory, transferring ownership and responsibility where possible.

- Upscaling. The Biodiversity Fund will be constructed in such a way that it is inclusive; therefore, while initially (and over the life of the project) only a limited number of protected areas will receive funding from the Biodiversity Fund, it will be designed in such a way that it will, eventually, fund all the protected areas in the country, as needed. Thus, the financial mechanism will be up-scaled across the protected area system within the country.

- Upscaling and replication requires monitoring and evaluation, learning processes and dissemination of those lessons and that information. Outcome Three Is specifically designed to ensure that monitoring and evaluation and participatory learning processes are fully integrated into the project. In addition, the project has a detailed M&E system (Section VII); the M&E will be carried out in a participatory way and the information that it generates will be made available nationally, regionally and globally to all relevant stakeholders and, where possible and pertinent, extend invitations to relevant stakeholders to attend trainings and other capacity development processes.

# Project Management

- Cost efficiency and effectiveness:  The project will use a number of different strategies to ensure cost efficiency and to ensure effective attainment of results, including (but not limited to) the following:

- First, the project will use standard UNDP rules for procurement; these are specifically designed to optimise value for money.  All activities to be carried out in any given year will be included in the Annual Work Plan, which will be discussed and approved by the Project Board to ensure that proposed actions are relevant and necessary. When the activities are to be implemented and project outputs monitored and evaluated, cost-effectiveness will be taken into account but will not compromise the quality of the outputs. When hiring third party consultants or contractors, the project will follow a standard recruitment and advertising process to have at least three competitors for each contract. Selection will be based on qualifications, proven technical experience and financial proposal, to ensure hiring the best consultant (individual or organization) for an optimal price. Economy fares will be applied for necessary air and road travel, and appropriate lodging facilities will be provided to the project staff ensuring staff safety and cost-effectiveness. Similarly, the project will follow a tendering process for equipment purchase and any printing/publishing that accounts for more than USD 10,000, comparing at least three vendors. In case there is a single vendor only for any activity, appropriate official norms will be followed to obtain approval from UNDP and GEF. Expenses will be accounted for according to UNDP rules and in line with the GEF policy.

- UNDP-CO has hired a P5 Programme Coordinator to oversee the Biodiversity, Climate Change and Risk Disaster Management Portfolio.  In addition: i) the Project Manager and the Project APFO (Administration, procurement and Finance Officers) will receive specific training on UNDP rules, regulations and procedures, and ii) project partners, on receiving funding from the project (or the Biodiversity Fund), will also receive training on the specific expectations regarding administering the grant, including reporting and accounting.

- As indicated in the section on Governance and Management Arrangements (see Section VIII), a number of strategies have been put in place specifically to improve the efficiency and effectiveness of the project’s implementation, including to ensure the functionality and effectiveness of the Project Board (PB) – again, on the basis of lessons learned from previous and ongoing UNDP-GEF projects in the country.

- Second, the project will be working with all the relevant stakeholders within PNG through partnerships and collaborations (some of which will be codified within MoU; see Section IV) thereby reducing the risk of duplication and redundancy. In addition, the partnerships and collaborations will also ensure complementarity of the work.  Thus, for example, the USAID is planning to implement a small grants programme for protected areas (thus, similar to Output 3.1 in this project). If these pieces of work are not carried out with a high degree of synergy – or even, as proposed under Output 2.1, to amalgamate these into a single funding mechanism – there will be duplication, confusion and scope for inefficiencies, misuse of available funding, or for over-burdening/over-financing of popular and easily marketable community activities.

- Third, the project has been designed by drawing off best practices in protected area sustainable financing from across the globe.

- Fourth, the feasibility of all activities has been carefully analysed, including the investments in the three pilot areas – thus, supporting the principle of value for money. In order to reduce transaction costs of funding local communities with low capacity, the project (and Biodiversity Fund) will work through local service providers and civil society organisations; this will also increase the sense of ownership among local communities.

- Finally, the project’s budgets have been carefully prepared for all investments; where tools and technologies are being introduced, the most recent developments are being used – and further developments will be tried and tested during the project’s life.

- Project Management.  As indicated below (Section VIII Governance and Management Arrangements), the day to day implementation of the project will be carried out by a Project Implementation Unit (PIU) that will be formed by the UNDP.

- The project should strive for further cost effectiveness with the other GEF projects as well as other conservation programmes that are being implemented by UNDP (and even other organisations) – including, for example, the CEPF, the forthcoming USAID programme – as well as other closely related programmes in other focal areas (e.g., climate change). The shared resources could include: the rental facilities, utilities, vehicles and personnel that can be pooled (e.g., PA/communications, gender/social, M&E, administration /finance / procurement).

- As described above (see Section IV), the project will be active in numerous sites across the country. Through the Biodiversity Fund, the project will test delivery of funds to a number of different protected areas across the country (Output 3.1). The project will also provide funding in an attempt to catalyse revenue-generating mechanisms in three sites (initially) under Output 3.2. Finally, the project will monitor various activities that are occurring across the protected area system as a whole to learn from successes (and failures, if they should occur) under Output 3.3. However, in all these efforts across the protected area system, the project will work through selected partners – and the project itself will not open physical project offices.

- Other aspects of partnerships have been addressed above (see Section IV – Results and Partnerships).

- Agreement on intellectual property rights and use of logo on the project’s deliverables and disclosure of information:  In order to accord proper acknowledgement to the GEF for providing grant funding, the GEF logo will appear together with the UNDP logo on all promotional materials, other written materials like publications developed by the project, and project hardware. Any citation in publications regarding projects funded by the GEF will also accord proper acknowledgement to the GEF. Information will be disclosed in accordance with relevant policies notably the UNDP Disclosure Policy and the GEF policy on public involvement.

# Project Results Framework

This project will contribute to the following Sustainable Development Goal (s): - Goal 1: End poverty in all its forms everywhere; - Goal 2: End hunger, achieve food security and improved nutrition and promote sustainable agriculture - Goal 13: Take urgent action to combat climate change and its impacts - Goal 14: Conserve and sustainably use the oceans, seas and marine resources for sustainable development - Goal 15: Protect, restore and promote sustainable use of terrestrial ecosystems, sustainably manage forests, combat desertification, and halt and reverse land degradation and halt biodiversity loss - Target 1.4: By 2030, ensure that all men and women, in particular the poor and the vulnerable, have equal rights to economic resources, as well as access to basic services, ownership and control over land and other forms of property, inheritance, natural resources, appropriate new technology and financial services, including microfinance - Target 2.4: By 2030, ensure sustainable food production systems and implement resilient agricultural practices that increase productivity and production, that help maintain ecosystems, that strengthen capacity for adaptation to climate change, extreme weather, drought, flooding and other disasters and that progressively improve land and soil quality - Target 13.2: Integrate climate change measures into national policies, strategies and planning - Target 14.5: By 2020, conserve at least 10 per cent of coastal and marine areas, consistent with national and international law and based on the best available scientific information - Target 15.1: By 2020, ensure the conservation, restoration and sustainable use of terrestrial and inland freshwater ecosystems and their services, in particular forests, wetlands, mountains and drylands, in line with obligations under international agreements

This project will contribute to the following country outcome included in the UNDAF/Country Programme Document: Sub-Outcome 3.3: By 2022, people, particularly marginalized and vulnerable, are empowered to manage climatic risks, develop community resilience and generate development opportunities from protection of land, forests and marine resources

This project will be linked to the following output of the UNDP Strategic Plan: Output 2.4.1: Gender-responsive legal and regulatory frameworks, policies and institutions strengthened, and solutions adopted, to address conservation, sustainable use and equitable benefit sharing of natural resources, in line with international conventions and national legislation. Output Indicators from the UNDP Strategic Plan Integrated Results and Resources Framework: - Natural resources that are managed under a sustainable use, conservation, access and benefit sharing regime: (a) area of land and marine habitat under protection (ha); (b) area of existing protected area under improved management (ha); (c) area under sustainable forest management (ha); (e) Biodiversity - Number of countries with gender-responsive measures in place for conservation, sustainable use, and equitable access to and benefit sharing of natural resources, biodiversity and ecosystems: a) Policy frameworks; b) legal and regulatory frameworks; c) institutional frameworks; d) financing frameworks.

|  | Objective and Outcome Indicators | Baseline | Mid-term Target | End of Project Target | Data Collection Methods and Risks/Assumptions |
| --- | --- | --- | --- | --- | --- |
| Project Objective: To reduce the funding gap for Papua New Guinea’s protected areas in order to improve their management effectiveness, and livelihoods of their communal landowners | Indicator 1: Area of land and marine habitat recognised by CEPA (within the database of protected areas) as being within protected areas (ha) | 2.125 million ha | 3.5 million ha | 4.5 million ha | Data Collection Methods: As measured by CEPA’s database on protected areas. Assumed that the demonstration sites (Sepik Wetlands, Mt Wilhelm and Kimbe Bay) that are not currently designed as protected areas become designated over the life of the project |
|  | Indicator 2: Improvement in the management effectiveness of protected areas score for sites receiving support from the Biodiversity Fund | All 57 gazetted PAs assessed using METT: 64% has little or no progress, 24% with some progress and high concerns, 5% with good progress and some concern, and 7% in very good state | At least 5 protected areas identified to receive support from the Biodiversity Fund once it is operational | METT score for 5-12 protected areas receiving direct financial support from the Biodiversity Fund improves by at least 10% over baseline per 2 years of support | Data Collection Methods: PAs assessed at the national and individual sites at end of project using GEF 6 METT – covering those areas that receive direct financial support from the Biodiversity Fund once this is operational. Note: the new ‘METT for PNG’ will be developed in parallel but not used for project M&E. Risks/Assumptions Assumes that delivery of funding from the Biodiversity Fund (which will start during the first half of the project) will lead to improved management. |
|  | indicator 3: Number of direct project beneficiaries, of which >65% are women and youth | 0 | At least 500 people (65% women and youth) | 1,200 people (>65% women & youth) | Data Collection Methods: These are beneficiaries in the targeted protected areas (under Output 3.1 and 3.2); at the project’s midterm, it is unlikely that there will be significant impacts (because of the time taken to establish the Biodiversity Fund and negotiate with communities in other areas under Output 3.2). The majority of the people are in the Sepik Wetlands with others in Mt Wilhelm and Kimbe Bay. The numbers will be reported by project partners. This represents a conservative estimate of the number of beneficiaries |
| Component/Outcome 1: Enabling conditions deliver a better managed and more financially sustainable protected area system | Indicator 4: Status of institutional mapping and mandates with respect to protected area management | Score = 2/6 Roles and responsibilities among different actors with respect to protected area management and financing is unclear and mandates remain unfulfilled | Score = 3/6 All involved actors sign an agreement to the produced institutional map to demonstrate that they are aware of their roles, responsibilities and mandates with respect to protected area management and financing | Score = 5/6 Actors are demonstrably fulfilling their roles, responsibilities and mandates with respect to protected area management and financing | Data Collection Methods: For this indicator, the score will be derived from the following: i) mandate for CEPA is mentioned in the legislation and policies, ii) mandate for CEPA is mentioned in the legislation and policies through specific legislation and policies (see Section II), iii) mandates and institutional mapping including CEPA, other state and non-state actors are agreed, signed by stakeholders and partners, and published, iv) the state and non-state actors are working to fulfil their mandates – including allocation of budgets and development of workplans, v) the state and non-state actors are implementing the workplans, and vi) the implementation of the workplans is being transparently and accountably reported and monitored. Risks/Assumptions: Government agencies – and especially CEPA – is open to institutional analyses and mapping, and to accept the outcome of such a mapping exercise Actors have sufficient capacity by EOP to fulfil their roles, responsibilities and mandates. |
|  | Indicator 5: Financial Scorecard (derived from Obj. 1. Section III Part III of the Sustainable Financing Tracking Tool) and projected number of years for which funding is secure | 9%; 3 years | 53%; 5 years | 58%; >12 years | Risks/Assumptions: The PA Business Plan (Output 1.2) is successfully implemented. The emphasis of the Biodiversity Fund is to increase stability and predictability of funding over the long-term, while reducing the funding gap. Thus, the achievement of this indicator assumes that the Biodiversity Fund is successfully established and capitalised. |
|  | Indicator 6: Capacity of organisations as measured using the Capacity and Competency Scorecard | CEPA: 38% West New Britain Provincial Government: 44% East Sepik Provincial Government: 23% Simbu Provincial Government: 20% | CEPA: 70% West New Britain Provincial Government: 54% East Sepik Provincial Government: 33% Simbu Provincial Government: 30% | CEPA: 85% West New Britain Provincial Government: 64% East Sepik Provincial Government: 43% Simbu Provincial Government: 40% | Risks/Assumptions: Commitment of government officers, PA managers, rangers and others consistency apply knowledge, skills and competencies in their day-to-day work Relevant stakeholders build consensus and cooperation among each other to strengthen collaboration at all levels |
| Outcome 2: A Biodiversity Fund for Papua New Guinea established and operationalised | Indicator 7: Biodiversity Fund structure and governance in place as indicated by: - Governing and operational structures – including the Steering Committee and Technical Secretariat – are in place with their associated governing documents; the strategic and operational documents have been developed and approved. - Biodiversity Fund is delivering funds to protected areas – as per Output 3.1 – and the use of these funds is being monitored and reported. | Biodiversity Fund does not exist | Biodiversity Fund fully established with functional sustainable recurring revenue sources | Biodiversity Fund fully functional | Risks/Assumptions: Multi- and bilateral donors, and non-state organisations and philanthropists are willing to contribute to the Biodiversity Fund |
|  | Indicator 8. Biodiversity Fund operationalisation through a sinking fund consisting of: - USD 5 million initial capital from GoPNG - At least USD 1.5 million annual revenue from recurrent income sources enabled by innovative GoPNG fiscal instruments (USD 1 million by mid-term) - GEF grant funds (USD 2.7 million) disbursed as grants via proposals approved by the Biodiversity Fund secretariat in support of PA management, sustainable livelihood and revenue generating, etc. activities, - At least USD 1 million additional capitalization through successful implementation of the fund raising/resource mobilisation strategy | Biodiversity Fund does not exist | a) USD 5 million initial capital received from GoPNG b) At least USD 1 million annual revenue from recurrent income sources enabled by innovative GoPNG fiscal instruments c) GEF funds (USD 2.7 million) released for disbursement as grants through the Biodiversity Fund in support of PA management, sustainable livelihood and revenue generating activities d) At least USD 250,000 additional capitalization through implementation of the fund raising/resource mobilisation strategy | a) USD 5 million initial capital from GoPNG b) At least USD 1.5 million annual revenue from recurrent income sources enabled by innovative GoPNG fiscal instruments c) GEF grant funds (USD 2.7 million) fully disbursed through Biodiversity Fund in support of PA management, sustainable livelihood and revenue generating activities d) At least USD 1 million aadditional capitalization through implementation of the fund raising/resource mobilisation strategy | Risks/Assumptions The emphasis of the Biodiversity Fund is to increase stability and predictability of funding over the long-term, while reducing the funding gap. Thus, the achievement of this indicator assumes that the Biodiversity Fund is successfully established and capitalised; The sinking portion of the Biodiversity Fund has grown and continues to be operational. Other sources could include green tax, biodiversity offset, linkage of protected area to climate funding, among others |
| Outcome 3: Enhanced management and financial sustainability of selected protected areas tested and piloted to improve knowledge, learning and practice | Indicator 9: Number of protected areas accessing funding from Biodiversity Fund | 0 | Funds being delivered to at least five protected areas across the country | Funds being delivered to at least 12 protected areas across the country | Risks/Assumptions: The delivery of funds to protected areas is dependent on their absorptive capacity and the protected areas will have to satisfy the criteria before funding can be delivered. |
|  | Indicator 10: Protected area management effectiveness | METT scores of selected PAs: Kimbe Bay: 32.4 Sepik Wetlands: 36 Mt. Wilhelm- Wanang: 43 | METT scores of selected PAs increase by 10% above baseline | METT scores of selected PAs increase by 20% above baseline | Risks/Assumptions: The demonstration sites that are not currently designated as protected areas become designated over the life of the project |
|  | Indicator 11: The generation and use of revenue streams for protected area management in the three selected protected areas (Sepik Wetlands, Mt Wilhelm and Kimbe Bay) | Kimbe Bay: K20,000/year Sepik Wetlands: K153,603/year Mt Wilhelm: K0/year Little or no revenue that is being generated is being used for protected area management in selected protected areas | ≥ USD 50,000 per individual PA | Exceeds USD 100,000 per annum | Risks/Assumptions: This assumes that i) the demonstration protected areas (under Output 3.2) are designated as protected areas and ii) that the stakeholders and beneficiaries agree to use revenues for protected area management (including protection). |
|  | Indicator 12: Gender responsive linkages between sustainable financing of protected areas and environmental protection, and well-being of communities as measured by: - Increased annual income of individuals (disaggregated by gender and age) from the number of environmentally and socially sustainable opportunities that have been identified and established (e.g. income from employment; business and entrepreneurial opportunities; increased production of food; sale of services; sale of products; etc.) - Number of communities with natural resource management agreements – that include water and fuelwood (specifically safe, protected and nearby sources of water and fuelwood) – that are developed and implemented. - Number of communities with agreed measures to address/halt GBV and age-discrimination | No linkages of individual or community livelihood improvements to sustainable financing and protection of biodiversity and environment; no active role of women and young people The baseline for these parameters will be established in each of the targeted protected areas on signing a funding agreement with either the project or the Biodiversity Fund (Outputs 3.1 and 3.2) | Active role of women and young people as individuals and groups in starting up income generation linked to environmental protection and its financing; measurable and meaningful improvements from baseline: - Average annual income of individuals (disaggregated by gender and age) increased by 20% from baseline - Seven communities with natural resource management agreements (n = 3 in Sepik Wetlands, n = 1 in Mt Wilhelm and n= 3 in Kimbe Bay) - Seven communities with agreed measures to address/halt GBV and age-discrimination (n = 3 in Sepik Wetlands, n = 1 in Mt Wilhelm and n= 3 in Kimbe Bay) | Successful income generating activities that equally benefit women, men and young people as individuals, families and/or community, simultaneously contributing to financially and physical sustainability of protected area - Average annual income of individuals (disaggregated by gender and age) increased by 40% from baseline - Eleven communities with natural resource management agreements (n = 5 in Sepik Wetlands, n = 1 in Mt Wilhelm and n= 5 in Kimbe Bay) - Eleven communities with agreed measures to address/halt GBV and age-discrimination (n = 5 in Sepik Wetlands, n = 1 in Mt Wilhelm and n= 5 in Kimbe Bay) | Risks/Assumptions: Gender and age power inequalities, male dominance and prevailing GBV and its causes/triggers have been addressed / are being addressed successfully |
|  | Indicator 13: Number of lessons (identified and disseminated by the project) used in development and implementation of other protected areas | 0 | 2 | 5 | Risks/Assumptions: Other stakeholders are interested in the lessons learned by this project |

# Monitoring and Evaluation (M&E) Plan

- The project results as outlined in the project results framework will be monitored annually and evaluated periodically during project implementation to ensure the project effectively achieves these results.  Component/Outcome Three is explicitly designed to facilitate learning and to ensure that knowledge is shared and widely disseminated to support the scaling up and replication of project results; this will be supported by the project’s monitoring and evaluation plan.

- Project-level monitoring and evaluation will be undertaken in compliance with UNDP requirements as outlined in the UNDP POPP and UNDP Evaluation Policy. The UNDP Country Office will work with the relevant project stakeholders to ensure UNDP M&E requirements are met in a timely fashion and to high quality standards. Additional mandatory GEF-specific M&E requirements (as outlined below) will be undertaken in accordance with the GEF M&E policy and other relevant GEF policies.

- In addition to these mandatory UNDP and GEF M&E requirements, other M&E activities deemed necessary to support project-level adaptive management will be agreed during the Project Inception Workshop and will be detailed in the Inception Report. This will include the exact role of project target groups (with respect to participatory baseline development as well as progress indicator formulation and its subsequent monitoring) and other stakeholders in project M&E activities including the GEF Operational Focal Point and national/regional institutes assigned to undertake project monitoring. The GEF Operational Focal Point will strive to ensure consistency in the approach taken to the GEF-specific M&E requirements (notably the GEF Tracking Tools) across all GEF-financed projects in the country. This could be achieved for example by using one national institute to complete the GEF Tracking Tools for all GEF-financed projects in the country, including projects supported by other GEF Agencies.

M&E Oversight and monitoring responsibilities:

- Project Manager:  The Project Manager is responsible for day-to-day project management and regular monitoring of project results and risks, including social and environmental risks; the social and environmental risk monitoring will also be carried out by the Social and Environmental Safeguards Officer (SESO). The Project Manager will ensure that all project staff maintain a high level of transparency, responsibility and accountability (including accountability to the project target groups in the – prospective – protected areas) in M&E and reporting of project results. The Project Manager will inform the Project Board, UNDP Country Office, and the UNDP-GEF RTA of any delays or difficulties as they arise during implementation so that appropriate support and corrective measures can be adopted.

- The Project Manager will develop annual work plans based on the multi-year work plan (Annex A), including annual output targets to support the efficient implementation of the project. The Project Manager will ensure that the standard UNDP and GEF M&E requirements are fulfilled to the highest quality. This includes, but is not limited to, ensuring the results framework indicators are monitored annually in time for evidence-based reporting in the GEF PIR, and that the monitoring of risks and the various plans/strategies developed to support project implementation (e.g. gender strategy, KM strategy etc.) occur on a regular basis.

- Project Board:  The Project Board will take corrective action as needed to ensure the project achieves the desired results. The Project Board will hold project reviews to assess the performance of the project and appraise the Annual Work Plan for the following year. In the project’s final year, the Project Board will hold an end-of-project review to capture lessons learned and discuss opportunities for scaling up and to highlight project results and lessons learned with relevant audiences. This final review meeting will also discuss the findings outlined in the project terminal evaluation report and the management response.

- Project Implementing Partner in conjunction with the Project Implementation Unit: The Implementing Partner and the PIU are responsible for providing any and all required information and data necessary for timely, comprehensive and evidence-based project reporting, including results and financial data, as necessary and appropriate. The Implementing Partner and PIU will strive to ensure project-level M&E is undertaken by national institutes, and is aligned with national systems so that the data used by and generated by the project supports national systems.

- UNDP Country Office:  The UNDP-CO (and specifically the Head of the Environment, Climate Change and Risk Disaster Management Portfolio) will support the Project Manager as needed, including through annual supervision missions. The annual supervision missions will take place according to the schedule outlined in the annual work plan. Supervision mission reports will be circulated to the project team and Project Board within one month of the mission.  The UNDP-CO will initiate and organize key GEF M&E activities including the annual GEF PIR, the independent mid-term review and the independent terminal evaluation. The UNDP-CO will also ensure that the standard UNDP and GEF M&E requirements are fulfilled to the highest quality.

- The UNDP-CO is responsible for complying with all UNDP project-level M&E requirements as outlined in the UNDP POPP. This includes ensuring the UNDP Quality Assurance Assessment during implementation is undertaken annually; that annual targets at the output level are developed, and monitored and reported using UNDP corporate systems; the regular updating of the ATLAS risk log; and, the updating of the UNDP gender on an annual basis based on gender mainstreaming progress reported in the GEF PIR and the UNDP ROAR. Any quality concerns flagged during these M&E activities (e.g. annual GEF PIR quality assessment ratings) must be addressed by the UNDP-CO and the Project Manager.

- The UNDP-CO will retain all M&E records for this project for up to seven years after project financial closure in order to support ex-post evaluations undertaken by the UNDP Independent Evaluation Office (IEO) and/or the GEF Independent Evaluation Office (IEO).  In addition, any of the donors to the Biodiversity Fund may request a third-party evaluation and/or audit if deemed necessary.

- UNDP-GEF Unit:  Additional M&E and implementation quality assurance and troubleshooting support will be provided by the UNDP-GEF Regional Technical Advisor and the UNDP-GEF Directorate as needed.

- Audit: The project will be audited according to UNDP Financial Regulations and Rules and applicable audit policies on NIM implemented projects.

- Additional GEF monitoring and reporting requirements:

- Inception Workshop and Report:  A project inception workshop will be held within one month of the establishment of the PIU [including the recruitment of the Project Manager, the Administrative, Procurement and Financial Officer (APFO) and the Chief Technical Officer (CTO)]; this should be within two months after the project document has been signed by all relevant parties to, amongst others:

  - Re-orient project stakeholders to the project strategy and discuss any changes in the overall context that influence project strategy and implementation;

  - Discuss the roles and responsibilities of the project team, including reporting and communication lines and conflict resolution mechanisms;

  - Review the results framework and finalize the indicators, means of verification and monitoring plan;

  - Discuss reporting, monitoring and evaluation roles and responsibilities and finalize the M&E budget; identify national/regional institutes to be involved in project-level M&E; discuss the role of the GEF OFP in M&E;

  - Update and review responsibilities for monitoring the various project plans and strategies, including the risk log; Environmental and Social Management Plan and other safeguard requirements; the gender strategy; the knowledge management strategy, and other relevant strategies;

  - Review financial reporting procedures and mandatory requirements, and agree on the arrangements for the annual audit; and

  - Plan and schedule Project Board meetings and finalize the first year annual work plan.

- The Project Manager will prepare and submit the inception report no later than one month after the inception workshop. The inception report will be cleared by the UNDP-CO and the UNDP-GEF Regional Technical Adviser, and will be approved by the Project Board.

- GEF Project Implementation Report (PIR):  The Project Manager, the UNDP-CO, and the UNDP-GEF Regional Technical Advisor will provide objective input to the annual GEF PIR covering the reporting period July (previous year) to June (current year) for each year of project implementation. The Project Manager will ensure that the indicators included in the project results framework are monitored annually in advance of the PIR submission deadline so that progress can be reported in the PIR. Any environmental and social risks and related management plans will be monitored regularly, and progress will be reported in the PIR.

- The PIR submitted to the GEF will be shared with the Project Board. The UNDP-CO will coordinate the input of the GEF Operational Focal Point and other stakeholders to the PIR as appropriate. The quality rating of the previous year’s PIR will be used to inform the preparation of the subsequent PIR.

- Lessons learned and knowledge generation:  Results from the project will be disseminated within and beyond the project intervention area through existing information sharing networks and forums. The project will identify and participate, as relevant and appropriate, in scientific, policy-based and/or any other networks, which may be of benefit to the project. The project will identify, analyse and share lessons learned that might be beneficial to the design and implementation of similar projects and disseminate these lessons widely. There will be continuous information exchange between this project and other projects of similar focus in the same country, region and globally.

- GEF Focal Area Tracking Tools:  The following GEF Tracking Tools will be used to monitor global environmental benefit results: i) GEF-6 METT and, a new METT for PNG will be developed as a trial for national use; ii) the Capacity Development Scorecard (using the baseline data collected by the GEF-5 project) and iii) the Financial Sustainability Scorecard. The baseline/CEO Endorsement GEF Focal Area Tracking Tools – submitted as Annex B to this project document – will be updated by the Project Manager and shared with the mid-term review and terminal evaluation consultants before the required review/evaluation missions take place. The updated GEF Tracking Tools will be submitted to the GEF along with the completed Mid-term Review report and Terminal Evaluation report.

- Independent Mid-term Review (MTR):  An independent mid-term review process will begin after the second PIR has been submitted to the GEF, and the MTR report will be submitted to the GEF in the same year as the third PIR. The MTR findings and responses outlined in the management response will be incorporated as recommendations for enhanced implementation during the final half of the project’s duration. The terms of reference, the review process and the MTR report will follow the standard templates and guidance prepared by the UNDP IEO for GEF-financed projects available on the UNDP Evaluation Resource Center (ERC). As noted in this guidance, the evaluation will be ‘independent, impartial and rigorous’. The consultants that will be hired to undertake the assignment will be independent from organizations that were involved in designing, executing or advising on the project to be evaluated. The GEF Operational Focal Point and other stakeholders will be involved and consulted during the terminal evaluation process. Additional quality assurance support is available from the UNDP-GEF Directorate. The final MTR report will be available in English and will be cleared by the UNDP-CO and the UNDP-GEF Regional Technical Adviser, and approved by the Project Board.

- Terminal Evaluation (TE):  An independent terminal evaluation (TE) will take place upon completion of all major project outputs and activities. The terminal evaluation process will begin three months before operational closure of the project allowing the evaluation mission to proceed while the project team is still in place, yet ensuring the project is close enough to completion for the evaluation team to reach conclusions on key aspects such as project sustainability. The Project Manager will remain on contract until the TE report and management response have been finalized. The terms of reference, the evaluation process and the final TE report will follow the standard templates and guidance prepared by the UNDP IEO for GEF-financed projects available on the UNDP Evaluation Resource Center. As noted in this guidance, the evaluation will be ‘independent, impartial and rigorous’. The consultants that will be hired to undertake the assignment will be independent from organizations that were involved in designing, executing or advising on the project to be evaluated. The GEF Operational Focal Point and other stakeholders will be involved and consulted during the terminal evaluation process. Additional quality assurance support is available from the UNDP-GEF Directorate. The final TE report will be cleared by the UNDP-CO and the UNDP-GEF Regional Technical Adviser, and will be approved by the Project Board.  The TE report will be publicly available in English on the UNDP ERC.

- The UNDP-CO will include the planned project terminal evaluation in the UNDP-CO evaluation plan, and will upload the final terminal evaluation report in English and the corresponding management response to the UNDP Evaluation Resource Centre (ERC). Once uploaded to the ERC, the UNDP IEO will undertake a quality assessment and validate the findings and ratings in the TE report, and rate the quality of the TE report.  The UNDP IEO assessment report will be sent to the GEF IEO along with the project terminal evaluation report.

- Additional aspects of the MTR and TE.  In addition to the standard terms of reference for the MTR, and to some extent the TE, the MTR (and TE) consultants will have additional responsibilities:

  - There should be a demonstrable improvement in the capacity, efficiency and effectiveness within the stakeholders involved in protected area management and financing (Outcomes One and Three).  Both the MTR and TE for the project will be looking for evidence of improved capacity and how trainings and any other capacity development processes are actually being used on a regular basis.

  - Furthermore, there is an expectation that all contractors and consultants to include a demonstrable transfer of skills and knowledge such that at the MTR and TE, the project will be in a position to demonstrate how those skills and that knowledge are actually being used at the midpoint and end of the project’s life.

  - Project Assurance will be carried out by the person heading the Environment, Climate Change and Disaster Risk Management Portfolio within the UNDP-CO (see Section VIII); the Project Assurance role and the success of the project will be included into his/her Terms of Reference and Key Performance Indicators (KPIs) to ensure adequate oversight of the project; the MTR should seek documentary evidence that has been done if there are any issues with the transparent, accountable, efficient and effective implementation of the project.

  - If, during the project’s MTR, the project’s ratings are anything less than “satisfactory”, the MTR consultant(s) should work to understand where the barriers lie. If they lie within the governance and management arrangements, changes to these arrangements should be considered – especially if they are deemed to be UNDP’s responsibility. The MTR should recommend adaptive measures and course corrections if the project is not performing as desired.

  - The MTR will check the composition of the PB and ensure that the Senior Beneficiaries are adequately and sufficient representative, and that they are fulfilling their primary role of ensuring the realization of project results from the perspective of project beneficiaries, including the women, men and young people of the communities that own and live from the land and waters to be sustainably protected through this project.

  - This project document makes a number of different proposals for cost-sharing to improve cost effectiveness (see sections V and VIII); the MTR should examine in detail how cost effectiveness is being achieved.

- Final Report: The project’s terminal PIR along with the terminal evaluation (TE) report and corresponding management response will serve as the final project report package. The final project report package shall be discussed with the Project Board during an end-of-project review meeting to discuss lessons learned and opportunities for scaling up.

Table 9: GEF M&E Requirements and M&E Budget

| GEF M&E requirements | Primary responsibility | Indicative costs to be charged to the Project Budget (US$) |  | Time frame |
| --- | --- | --- | --- | --- |
|  |  | GEF grant | Co-financing |  |
| Inception Workshop | UNDP-CO | 15,000 | 10,000 | Within two months of the project document signature |
| Inception Workshop Report | Project Manager | None | None | Within one month after the inception workshop |
| Standard UNDP Monitoring and Reporting Requirements as outlined in UNDP POPP | UNDP Country Office | None | None | Quarterly, Annually |
| Risk management | Project Manager Country Office | None | None | Quarterly, Annually |
| Monitoring of indicators in project results framework | Project Manager | 16,000 (4,000/ year) | 15,000 (5,000/year) | Annually |
| GEF Project Implementation Report (PIR) | Project Manager, Country Office and UNDP-GEF Team | None |  | Annually |
| NIM Audit as per UNDP audit policies | UNDP-CO | 35,000 (3,000-5000/year) | 20,000 | Annually |
| Lessons learned and knowledge generation | Project Manager | 126,000 (18,000/year) | 0 | Annually |
| Monitoring of environmental and social risks, and corresponding management plans as relevant | Project Manager, SESO, UNDP-CO | None | 20,000 | On-going |
| Addressing environmental and social grievances | Project Manager, SESO, UNDP-CO, BPPS as needed | None | 5000 | Costs associated with missions, workshops, BPPS expertise etc. |
| Project Board meetings | Project Board, UNDP-CO, PM | 90,000 (15,000/ year) | 0 | At minimum, twice annually |
| Supervision missions | UNDP-CO | None | 25,000 | Annually |
| Oversight missions | UNDP-GEF team | None | 0 | Troubleshooting as needed |
| GEF Secretariat learning missions/site visits | UNDP-CO and Project Manager and UNDP-GEF team | None | 0 | To be determined |
| Mid-term GEF Tracking Tool to be updated | Project Manager | 10,000 | 0 | Before mid-term review mission takes place. |
| Independent Mid-term Review (MTR) and management response | UNDP-CO and Project team and UNDP-GEF team | 50,000 | 10,000 | Between 2nd and 3rd PIR. |
| Terminal GEF Tracking Tool to be updated | Project Manager | 10,000 | 5,000 | Before terminal evaluation mission takes place |
| Independent Terminal Evaluation (TE) included in UNDP evaluation plan, and management response | UNDP-CO and Project team and UNDP-GEF team | 60,000 | 5,000 | At least three months before operational closure |
| TOTAL indicative COST (3-5% of GEF grant) |  | 412,000 | 115,000 |  |

# Governance and Management Arrangements

- It should be stated that there are profound expectations in this project among the stakeholders in the country as with other GEF investments in the country. The GEF provides the most significant investments in biodiversity conservation in PNG at present including government expenditure.

- This project will be implemented by the Government with full support of the UNDP, ensuring transparency, accountability, efficiency and effectiveness. This means:

  - When working with partners and contractors, the UNDP-CO (as the entity implementing and managing the on a day-to-day basis) will provide training on mutual expectations regarding processes, efficiencies, reporting and accountability with tips and strategies for how efficiencies and effectiveness can be optimised.

  - The Project Board will be inclusive, transparent and accountable. As such, it will be comprised of voting members but be open to non-voting observers.

  - Project Assurance will be carried out, as is usual in UNDP-GEF projects, by the person heading the Environment, Climate Change and Disaster Risk Management Portfolio within the UNDP-CO. However, the Project Assurance role and the success of the project will be included into his/her Terms of Reference and Key Performance Indicators (KPIs) to ensure adequate oversight of the project (and the MTR should seek documentary evidence that has been done if there are any issues with the transparent, accountable, efficient and effective implementation of the project).

  - In order to facilitate project oversight, and monitoring and evaluation, the project’s M&E budget is adequately provisioned (3.64% of the GEF grant).

  - If, at the project’s midterm review, the project’s ratings are anything less than “satisfactory”, the midterm review consultant(s) should work to understand where the barriers lie.  If they lie within the governance and management arrangements, changes to these arrangements should be considered – especially if they are deemed to be UNDP’s responsibility, and recommend adaptive measures and course corrections.

  - The project will include a dispute resolution mechanism and a confidential whistle-blower mechanism; the dispute mechanism will be chaired by the UNDP Resident Representative.

- In addition to these innovative approaches, the proposed project will also focus on building capacity of the project partners – including of CEPA – to fulfil their mandates (as identified and described under Output 1.1): indeed, this is the purpose of Outcomes One and Three.  However, it will not focus on building the capacity of the project partners to implement GEF projects!

- Beyond these measures (all of which are designed to improve project oversight and hence management), there are a number of factors beyond the control of the project. As a consequence, these factors present risks to the success of the project (see Section IV).

- The project will be implemented over a period of up to seven years (thus, a total maximum of 84 months) and the project will commence once the PRODOC has been signed by the UNDP and the Chair of the Board of the Conservation and Environmental Protection Authority (CEPA). The additional time (relative to the 60 months proposed in the PIF) will allow UNDP and the project partners to start up the project in an effective way. This will enable the Project Implementation Unit to be established with recruited project staff.  It will then allow the project partners to collect baseline METT data, actively involving women and men as well as young people of the communities concerned in this collection in a participatory way to enhance their ownership of the data collected as baseline. It will also allow the Biodiversity Fund to be established and for the systems of fund delivery to be fully tested such that, with adaptive management, there will be iterative amendments and improvements over the project’s life.  It will also allow for the second edition of the Business Plan to be developed (after the first five-year plan is completely implemented).

- Roles and responsibilities of the project’s governance mechanism. The project will be implemented following UNDP’s national implementation modality (NIM), according to the Standard Basic Assistance Agreement between UNDP and the Government of Papua New Guinea, and the Country Programme. The Implementing Partner for this project is the Conservation and Environmental Protection Authority (CEPA) under the Ministry of Environment, Conservation and Climate Change (MOECCC). The Implementing Partner is responsible and accountable for managing and evaluation of project interventions, achieving project outcomes and for the effective use of UNDP and GEF resource. The Implementing Partner will also appoint a National Project Director.  This will be a high-ranking official – the Director of the Sustainable Environment Program; s/he will Chair the PB and be responsible for ensuring that it meets at least twice a year. S/he is expected to dedicate 15% of his/her time to the project and be in continual close communication and liaison with the Project Manager. The project will be implemented with UNDP Support Services. This means that:

  - UNDP will recruit and form a Project Implementation Unit (PIU) responsible for the day-to-day management and implementation of the project, as described below.

  - The UNDP Support Services will include i) identification and recruitment of project personnel for the PIU, and ii) procurement of goods and services.

  - The procurement and recruitment processes will follow UNDP rules and regulations.

  - The UNDP-CO (and PIU) undertakes transactions from requisition through to disbursement on behalf of the project with no cash transferred to the implementing partner IP (i.e CEPA). The implementing partner has programmatic oversight, however, through its position as Chair of the Project Board (Figure 8). The project organization structure is as follows:

Figure 8. The project's governance and management structure

- The Project Board (also called Project Steering Committee) is the body with ultimate responsibility for the efficient and effective implementation of the project.  As such, it will be held to account for the delivery of the project. Therefore, it will ensure that the project’s process of implementation and the achievement of its objective and outcomes are highly professional, streamlined, effective and efficient.  The PB will ensure that the project maintains the highest levels of transparency and accountability; and it will ensure cooperation and collaboration among project partners.

- The Project Board has the key responsibility to ensure that the project remains relevant to the communities that own, use and hence - to a great extent - depend on the Protected Area lands and waters for their sustenance and survival.

- The PB will also ensure that the project remains relevant to national development objectives and strategies; to the UNDP policies and strategies; to the GEF’s focal areas. The PB will ensure that the processes that the project has put into place and the impacts that the project has are sustainable. The PB will promote learning, feedback and knowledge sharing on the results and lessons learned from the project and its partners as a basis for decision-making on and, if necessary adaptation of, policies, strategies, programme management and projects, and to improve knowledge and performance.

- The PB will be responsible for approving the project’s annual workplans and budgets (including fund allocations, budgets and projects, and the financial coordination mechanisms) – and these will be developed in synchrony and synergy with other programmes and projects (including those of CEPF, USAID, DFAT, and other GEF and GCF initiatives in the country), as well as with CEPA’s own budget and allocations related to the selected protected areas, to prevent funding overlap or substitution. It will also be responsible to examine the expenditure, ensuring efficient use of the project’s budget relative to the project lifetime.

- The PB will meet after the Inception Workshop (to approve the first year’s annual workplan and budget) and, thereafter, a minimum of two times a year.

- The National Project Director – who will also Chair the PB – will be responsible for calling for PB meetings and, with the support of the Project Manager, putting together the agenda for the meetings. However, if the PB is not meeting frequently enough, any member of the PB can propose a PB meeting. The Project Manager will be responsible for drafting the minutes, including agreed action points, of the PB meetings and circulating them within no more than one week following the PB meetings. The minutes from the previous PB meeting will be approved at the start of the meeting that follows that meeting, with a check on the follow-up given to agreed action points.

- The PB will be responsible for making, by consensus, project management decisions, when guidance is required by the Project Manager, including recommendations for UNDP/Implementing Partner approval of project plans and revisions, and addressing any project level grievances. In order to ensure UNDP’s ultimate accountability, Project Board decisions should be made in accordance with standards that shall ensure management for development results, best value for money, fairness, integrity, transparency, preventing harm to the invovled commuities, and effective international competition. In case a consensus cannot be reached within the Board, final decision shall rest with the Head of the Environment, Climate Change and Disaster Risk Management Portfolio in the UNDP-CO.

- Specific responsibilities of the Project Board include (and the draft TOR for the Project Board are contained in Annex D):

  - Provide overall guidance and direction to the project, ensuring it remains within any specified constraints;

  - Address project issues as raised by the project manager;

  - Provide guidance on new project risks, and agree on possible mitigation or countermeasures and management actions to address specific risks;

  - Agree on project manager’s tolerances as required;

  - Review the project progress, and provide direction and recommendations to ensure that the agreed deliverables are produced satisfactorily according to plans or adapted and altered is deemed necessary;

  - Appraise the annual project implementation report, including the quality assessment rating report; make recommendations for the workplan;

  - Provide ad hoc direction and advice for exceptional situations when the project manager’s tolerances are exceeded;

  - Assess and decide to proceed on project changes through appropriate revisions.

  - Approving and signing the multiyear workplan;

  - Approving and signing the combined delivery report at the end of the year; and,

  - Signing the financial report or the funding authorization and certificate of expenditures.

- The Project Board includes:

- Executive: The Executive represents ownership of the project and who will chair the Project Board.  The Executive is the Director of the Sustainable Environment Program of CEPA.  The Executive is ultimately responsible for the project, supported by the Senior Beneficiary and Senior Supplier (see below). The Executive’s role is to ensure that the project is focused throughout its life cycle on achieving its objectives and delivering outputs that will contribute to higher level outcomes. The Executive has to ensure that the project gives value for money, ensuring a cost-conscious approach to the project, balancing the demands of beneficiary and supplier. His/her specific responsibilities: (as part of the above responsibilities for the Project Board) include:

  - Ensure that there is a coherent project organisation structure and logical set of plans;

  - Set tolerances in the AWP and other plans as required for the Project Manager;

  - Monitor and control the progress of the project at a strategic level;

  - Ensure that risks are being tracked and mitigated as effectively as possible;

  - Brief relevant stakeholders about project progress;

  - Organise and chair Project Board meetings.

- Senior Suppliers: The Senior Supplier is an individual or group representing the interests of the parties concerned which provide funding and/or technical expertise to the project (designing, developing, facilitating, procuring, implementing). The Senior Supplier’s primary function within the Board is to provide guidance regarding the technical feasibility of the project. The Senior Supplier role must have the authority to commit or acquire supplier resources required. If necessary, more than one person may be required for this role. Typically, the implementing partner, UNDP and/or donor(s) would be represented under this role. The Senior Suppliers are: UNDP, the MPTFO or other reputable entities and the project co-financiers. On the PB, they will be represented by the UNDP Deputy Resident Representative/CO Programme Manager (i.e Head of the Environment, Climate Change and Disaster Risk Management Portfolio). Other PB members representing Senior Suppliers include:

  - Representatives from the Ministry of Planning & Monitoring, and the Treasury

  - A representative from the service provider serving as Fund Administrator (when available)

  - An appropriate high-level representative from the bilateral donor and ODA community as part of the process of ensuring visibility on the project and the establishment (and need for capitalisation) of the Biodiversity Fund, and

  - Representative(s) of other organisations (state and non-state) that provide relevant technical assistance (TA) specifically to the communities concerned. These are the people representing the interests of the parties concerned which provide funding and/or technical expertise to the project (designing, developing, facilitating, procuring, implementing).

- Specific responsibilities (as part of the above responsibilities for the Project Board) include:

  - Make sure that progress towards the outputs remains consistent from the supplier perspective;

  - Promote and maintain focus on the expected project output(s) from the point of view of supplier management;

  - Ensure that the supplier resources and expertise required for the project are made available;

  - Contribute supplier opinions on Project Board decisions on whether to implement recommendations on proposed changes;

  - Arbitrate on, and ensure resolution of, any supplier priority or resource conflicts.

- Senior Beneficiaries: The Senior Beneficiary is an individual or group of individuals representing the interests of those who will ultimately benefit from the project. Thus, the Senior Beneficiaries’ function within the Board is to ensure the realization of project results from the perspective of project beneficiaries, including the women, men and young people of the communities that own and live from the land and waters to be sustainably protected through this project.  The Senior Beneficaries will be drawn from people who are uniquely dedicated to conservation of the environment in PNG and who can amplify the interests of the communities (land owners and land users) on the PB (including representatives from academic organisations, civil society and non-governmental organisations that are actively working on protected area issues in the country, representatives from financial and legal institutions, representatives from the private sector tourism industry – especially those with some form of relationship with the project, representatives working for sustainability departments from private sector organisations that are committed to global standards of responsibility and sutainability).

- The Senior Beneficiaries are responsible for validating the needs and for monitoring that the solution will meet those needs within the constraints of the project. The Senior Beneficiaries’ role is to monitor progress against targets and quality criteria.  Their specific responsibilities (as part of the above responsibilities for the Project Board) include:

  - Prioritize and contribute beneficiaries’ opinions on Project Board decisions on whether to implement recommendations on proposed changes;

  - Check whether specification of the Beneficiary’s needs is accurate, complete and unambiguous;

  - Monitor implementation of activities at all stages is monitored to ensure that they will meet the beneficiary’s needs (which are different for women, men and young people) and are progressing towards that target;

  - Impact of potential changes is evaluated from the beneficiary point of view;

  - Risks to the beneficiaries are frequently monitored.

- Attendance of the PB meetings will be monitored and attendance rates of the delegated people is expected to be no less than 80%.

- In addition, the aim of the PB has to be inclusive, transparent and accountable, and, as such, PB meetings will be open to the public and observers will be welcome. The observers may include state and non-state actors, the private sector, NGOs, CBOs and protected area community representatives; however, observers will not be voting members of the PB.  While observers will not have the right to vote in PB meetings, they do have the right to call for a PB meeting if there has not been a PB meeting for over nine months in any given period through the project’s life.

- Finally, as stated above, if, during the project’s midterm review, the project’s ratings are anything less than “satisfactory”, the midterm review consultant(s) should work to understand where the barriers lie.  If they lie within the governance and management arrangements, changes to these arrangements should be considered – especially if they are deemed to be UNDP’s responsibility, and recommend adaptive measures and course corrections to address the barriers.

- UNDP Direct Project Services (DPS) as requested by Government: The UNDP, as GEF Agency for this project, will provide project management cycle services for the project as defined by the GEF Council. In addition, the Government of Papua New Guinea may request UNDP direct services for specific projects, according to its policies and convenience.  The UNDP and Government of Papua New Guinea acknowledge and agree that those services are not mandatory, and will be provided only upon Government request. If requested, the services would follow the UNDP policies on the recovery of direct costs. These services (and their costs) are specified in the Letter of Agreement (TBD). As is determined by the GEF Council requirements, these service costs will be assigned as Project Management Cost, duly identified in the project budget as Direct Project Costs. Eligible Direct Project Costs should not be charged as a flat percentage. They should be calculated on the basis of estimated actual or transaction based costs and should be charged to the direct project costs account codes: “64397- Services to projects – CO staff” and “74596 – Services to projects – GOE for CO”.

- As such, UNDP will form a Project Implementation Unit (PIU), including appointing a Project Manager.  The Project Manager has the authority to run the project on a day-to-day basis on behalf of the Implementing Partner within the constraints laid down by the Board. The Project Manager is responsible for day-to-day management and decision-making for the project. The Project Manager’s prime responsibility is to ensure that the project produces the results specified in the project document, to the required standard of quality and within the specified constraints of time and cost.  The Project Manager will have both project management and technical functions (see Annex D for draft TOR) and those functions will include the following specific responsibilities:

  - Provide direction and guidance to contractors and project partners;

  - Liaise with the Project Board to assure the overall direction and integrity of the project;

  - Identify and obtain any support and advice required for the management, planning and control of the project;

  - Responsible for project administration;

  - Plan the activities of the project and monitor progress against the project results framework and the approved annual workplan;

  - Mobilize personnel, goods and services, training and micro-capital grants to initiative activities, including drafting terms of reference and work specifications, and overseeing all contractors’ work;

  - Monitor events as determined in the project monitoring schedule plan/timetable, and update the plan as required;

  - Manage requests for the provision of financial resources from UNDP, through advance of funds, direct payments or reimbursement using the fund authorization and certificate of expenditures;

  - Monitor financial resources and accounting to ensure the accuracy and reliability of financial reports;

  - Be responsible for preparing and submitting financial reports to the PB and UNDP on a quarterly basis;

  - Manage and monitor the project risks initially identified and submit new risks to the project board for consideration and decision on possible actions if required; update the status of these risks by maintaining the project risks log;

  - Capture lessons learned during project implementation;

  - Prepare the annual workplan for the following year; and update the Atlas Project Management module if external access is made available.

  - Prepare the GEF PIR and submit the final report to the Project Board;

  - Based on the GEF PIR and the Project Board review, prepare the AWP for the following year.

  - Ensure the mid-term review process is undertaken as per the UNDP guidance, and submit the final MTR report to the Project Board.

  - Identify follow-on actions and submit them for consideration to the Project Board;

  - Ensure the terminal evaluation process is undertaken as per the UNDP guidance, and submit the final TE report to the Project Board;

- In addition to the Project Manager, the PIU will include an Administrative, Procurement & Financial Officer (APFO) to support the Project Manager. The APFO will also have some technical obligations in the project – particularly with reference to building capacity and systems for outstanding financial planning and management among partner organisations.

- The project will also recruit a Chief Technical Officer (CTO).  This is a specifically technical position – with specific reference to business planning, resource mobilisation, and financial planning, systems and capacity building. The CTO will not substitute the Project Manager in terms of project management.  Indeed, the CTO will have the specific responsibility to develop the Business Plan (Output 1.2) – but in an inclusive, participatory and deliberative way with the involvement of stakeholders.  The CTO will also be involved in the resource mobilisation for the Biodiversity Fund, guiding the process of developing the Biodiversity Fund’s fund raising/resource mobilisation strategies (Output 2.3).  Finally, the CTO will be involved in the process to catalyse revenues in the selected pilot sites (Output 3.2).  In addition, the CTO will be involved other aspects of the project, as necessary (see Annex D for draft TOR).

- Finally, the project will recruit a Social and Environmental Safeguards Officer (SESO). This position is essential given the nature of the protected areas of PNG – the majority of which are owned and managed by indigenous communities living within and surrounding the protected areas. The SESO will ensure that the highest standards are achieved in all protected areas with respect to social and environmental standards – including the gender, age and power issues – in line with the management plan(s) to be developed for the project.

- The PIU will prepare annual workplans and budgets in consultation with project partners for approval by the Project Board.  In addition, the PIU will be responsible for the preparation of all project reports including the project’s Inception Report and the Project Implementation Reports (PIR) (see Section VII). The PIU will also be responsible for contracting consultants, partner organisations and/or contractual service companies that will be engaged to carry out the different aspects of the specific output of project; these aspects will be agreed in the annual workplans and budgets that will be approved by the PB (as necessary and as required, see budget notes in Section X).  In addition, the PIU may sub-contract other partners to implement different components or sub-components of the project.  This is especially important in Output 3.2 in the three pilot sites; Responsible Party(ies) will be selected to implement the project’s work in the three sites (see Table 4).  In the selection of the Responsible Parties, the bidding parties will have to demonstrate how they will be deemed trustworthy by and downward accountable to the communities as well as upward accountable to the government, UNDP and the GEF. Indeed, bids that include a consortium – coupling the project management expertise and a strong civil society organisation, such that project management (including financial management, procurement and reporting) and social and gender content is adequately addressed from the outset of the project – will be encouraged.

- As indicated in Section V, the PIU will be housed within the UNDP-CO. The project should strive for further cost effectiveness with the other GEF projects as well as other biodiversity programmes that are being implemented by UNDP (and even other organisations) – including, for example, the forthcoming USAID programme – as well as other closely related programmes in other focal areas (e.g., climate change) – with shared resources including (but not limited to): utilities, vehicles and project personnel that can be pooled (e.g., gender/social, administration/ finance/ procurement).

- The functions of the PIU will end when the final project terminal evaluation report and corresponding management response, and other documentation required by the GEF and UNDP, has been completed and submitted to UNDP (including operational closure of the project).

- The project assurance: UNDP provides a three – tier supervision, oversight and quality assurance role – funded by the GEF agency fee – involving UNDP staff in Country Offices and at regional and headquarters levels. Project Assurance must be totally independent of the Project Management function. The quality assurance role supports the Project Board and Project Implementation Unit by carrying out objective and independent project oversight and monitoring functions. This role ensures appropriate project management milestones are managed and completed. The Project Board cannot delegate any of its quality assurance responsibilities to the Project Manager. This project oversight and quality assurance role is covered by the GEF Agency.

- As part of the project assurance role, UNDP will be responsible to provide training (possibly through a contracted organisation) for all project partners. The training will include the rationale that underpins the bureaucratic processes involved with provision of quarterly tranches, the need for accounting and reporting, and the processes, templates and forms involved with all those things.

# Financial Planning and Management

- The total cost of the project is USD 61,673,164. This is financed through a GEF grant of USD 11,311,915 and co-financing of 50,361,249 which represents USD 228,326 in cash co-financing to be administered by UNDP; USD 5 million in cash co-financing from the Government of PNG into the TF; and USD 45,132,923 in parallel co-financing. The co-financing is slightly higher than the total amount indicated in the PIF of USD 49,540,000. UNDP, as the GEF Implementing Agency, is responsible for the execution of the GEF resources and the cash co-financing transferred to UNDP bank account only.

- Parallel co-financing: The actual realization of project co-financing will be monitored during the mid-term review and terminal evaluation process and will be reported to the GEF. The planned parallel co-financing will be used as follows:

Table 10: Co-financing from government and partners

| Co-financing source | Co-financing type | Co-financing amount | Planned Activities/Outputs | Risks | Risk Mitigation Measures |
| --- | --- | --- | --- | --- | --- |
| Government of PNG | In kind | 15,000,000 | The government’s contributions will be through developing capacity (Output 1.3) and working to support communities in the sites (Outputs 3.1 and 3.2) | No risk |  |
| Government of PNG | Grant | 5,000,000 | Government’s contribution to the Biodiversity Fund | The government’s contribution to the Biodiversity Fund will be made available by Year 4 of the project because of the current fiscal situation. | The UNDP-CO will continually engage the government throughout the project (over and above the government’s engagement in the PB) to ensure that the government do go through with the pledged contribution. |
| Walindi Plantation Resort | Grant | 350,000 | Working with communities in Kimbe Bay; tourism development (Outputs 3.2, 3.3) | No risk |  |
| UNDP TRAC | Grant | 228,326 | Cash for support to cover project management costs | No risk |  |
| UNDP (Forest Carbon Partnership Facility 2) | Grant | 5,000,000 | Strengthen environmental protection, policies and regulations; support conservation efforts to secure sustainable financing to improve the management and protection of PNG’s forests. |  |  |
| Barrick (N) Ltd | In-kind | 600,000 | Working with the proposed Kaijende Highlands and Headlands of Strickland; trialling REDD+ as mechanism for sustainable financing of PAs (Outputs 3.1., 3.3) | No risk |  |
| New Guinea Binatang Research Centre | Grant | 1,730,000 | Demonstration of mechanism to generate revenue and employment in Pas (Output 3.2) | No risk |  |
| FORCERT | Grant | 1,000,000 | Working with communities through sustainable land and resource use and community action planning processes; support for village-based enterprises; contribute to sustainability of PAs and natural resource management in the country. | No risk |  |
| WCS | Grant | 1,000,000 | Activities in Mt Wilhelm areas (one of the project’s pilot sites (Output 3.2) | No risk |  |
| Mahonia na Dari | Grant | 120,000 | Activities in Kimbe Bay (Output 3.2) | No risk |  |
| Woodland Park Zoo | Grant | 1,740,000 | Demonstration of financing mechanisms in the Yus Conservation Area (Outputs 3.1, 3.3) | No risk |  |
| Woodland Park Zoo | In-kind | 2,020,000 |  |  |  |
| Government of Australia (DFAT) | Grant | 15,337,423 | Promote improved policy settings; direct support to communities for conservation efforts. | No risk |  |
| New Britain Palm Oil Limited | Grant | 1,235,500 | Focuses on the Popondetta plains and the Managalas Plateau – recently gazetted PA; develop mechanisms to contribute to the sustainable financing of the conservation work for QABB (Queen Alexandra’s Birdwing Butterfly) and its natural ecosystems. | No risk |  |
| Total |  | 50,361,249 |  |  |  |

- Budget Revision and Tolerance:  As per UNDP requirements outlined in the UNDP POPP, the project board will agree on a budget tolerance level for each plan under the overall annual work plan allowing the project manager to expend up to the tolerance level beyond the approved project budget amount for the year without requiring a revision from the Project Board. Should the following deviations occur, the Project Manager and UNDP-CO will seek the approval of the UNDP-GEF team to ensure accurate reporting to the GEF: a) Budget re-allocations among components in the project with amounts involving 10% of the total project grant or more; b) Introduction of new budget items/or components that exceed 5% of original GEF allocation.

- Any over expenditure incurred beyond the available GEF grant amount will be absorbed by non-GEF resources (e.g. UNDP TRAC or cash co-financing).

- Refund to GEF:  Should a refund of unspent funds to the GEF be necessary, this will be managed directly by the UNDP-GEF Unit in New York.

- Project Closure:  Project closure will be conducted as per UNDP requirements outlined in the UNDP POPP. On an exceptional basis only, a no-cost extension beyond the initial duration of the project will be sought from UNDP CO and then the UNDP-GEF Executive Coordinator.

- Operational completion: The project will be operationally completed when the last UNDP-financed inputs have been provided and the related activities have been completed. This includes the final clearance of the Terminal Evaluation Report (that will be available in English) and the corresponding management response, and the end-of-project review Project Board meeting. The Implementing Partner through a Project Board decision will notify the UNDP-CO when operational closure has been completed. At this time, the relevant parties will have already agreed and confirmed in writing on the arrangements for the disposal of any equipment that is still the property of UNDP.

- Transfer or disposal of assets: In consultation with the NIM Implementing Partner and other parties of the project, UNDP programme manager (UNDP Resident Representative) is responsible for deciding on the transfer or other disposal of assets. Transfer or disposal of assets is recommended to be reviewed and endorsed by the project board following UNDP rules and regulations. Assets may be transferred to the government for project activities managed by a national institution at any time during the life of a project. In all cases of transfer, a transfer document must be prepared and kept on file.

- Financial completion:  The project will be financially closed when the following conditions have been met: a) The project is operationally completed or has been cancelled; b) The Implementing Partner has reported all financial transactions to UNDP; c) UNDP has closed the accounts for the project; d) UNDP and the Implementing Partner have certified a final Combined Delivery Report (which serves as final budget revision).

- The project will be financially completed within 12 months of operational closure or after the date of cancellation. Between operational and financial closure, the implementing partner will identify and settle all financial obligations and prepare a final expenditure report. The UNDP-CO will send the final signed closure documents including confirmation of final cumulative expenditure and unspent balance to the UNDP-GEF Unit for confirmation before the project will be financially closed in Atlas by the UNDP-CO.

# Total Budget and Work Plan

| Total Budget and Work Plan |  |  |  |
| --- | --- | --- | --- |
| Atlas Proposal or Award ID: | 00086294 | Atlas Primary Output Project ID: | 00093582 |
| Atlas Proposal or Award Title: | Biodiversity Conservation, Sustainable Financing |
| Atlas Business Unit | PNG10 |  |  |
| Atlas Primary Output Project Title | Sustainable Finance of Papua New Guinea’s Protected Area Network |  |  |
| UNDP-GEF PIMS No. | 5507 |  |  |
| Implementing Partner | CEPA (with Support Services being provided by UNDP through a PIU) |  |  |

| GEF Component/ Atlas Activity | (Atlas Implementing Agent) | Fund ID | Donor Name | Atlas Budgetary Account Code | ATLAS Budget Description | Amount Year 1 (USD) | Amount Year 2 (USD) | Amount Year 3 (USD) | Amount Year 4 (USD) | Amount Year 5 (USD) | Amount Year 6 (USD) | Amount Year 7 (USD) | Total (USD) | Budget Note |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| COMPONENT/OUTCOME 1 | UNDP (PIU) | 62000 | GEF TF | 61300 | Salary and Post Adj – IP Staff | 108,000 | 108,000 | 108,000 | 108,000 | 108,000 | 108,000 | 108,000 | 756,000 | 1 |
|  |  |  |  | 71400 | Contractual Services - Individual | 4,506 | 4,506 | 4,506 | 4,506 | 4,506 | 4,506 | 4,506 | 31,542 | 2 |
|  |  |  |  | 71400 | Contractual Services - Individual | 7,087 | 7,087 | 7,087 | 7,087 | 7,087 | 7,087 | 7,087 | 49,609 | 3 |
|  |  |  |  | 71400 | Contractual Services - Individual | 13,517 | 13,517 | 13,517 | 13,517 | 13,517 | 13,517 | 13,517 | 94,619 | 4 |
|  |  |  |  | 71600 | Travel | 0 | 15,000 | 18,890 | 20,000 | 20,000 | 20,000 | 20,000 | 113,890 | 5 |
|  |  |  |  | 72100 | Contractual Services-Companies | 40,000 | 40,000 | 0 | 0 | 0 | 0 | 0 | 80,000 | 6 |
|  |  |  |  | 72100 | Contractual Services-Companies | 45,000 | 0 | 0 | 0 | 0 | 0 | 0 | 45,000 | 7 |
|  |  |  |  | 72100 | Contractual Services-Companies | 0 | 50,000 | 50,000 | 50,000 | 50,000 | 50,000 | 50,000 | 300,000 | 8 |
|  |  |  |  | 74200 | Printing and Publication | 0 | 0 | 7,000 | 0 | 0 | 7,000 | 0 | 14,000 | 9 |
|  |  |  |  | 75700 | Training, Workshops and Confer | 30,000 | 60,000 | 60,000 | 20,000 | 0 | 0 | 20,000 | 190,000 | 10 |
|  |  |  |  | 75700 | Training, Workshops and Confer | 0 | 0 | 97,672 | 0 | 0 | 0 | 0 | 97,672 | 11 |
|  |  |  |  |  | Total Outcome 1 | 248,110 | 298,110 | 366,672 | 223,110 | 203,110 | 210,110 | 223,110 | 1,772,332 |  |
| COMPONENT/OUTCOME 2 | UNDP (PIU) | 62000 | GEF TF | 61300 | Salary and Post Adj – IP Staff | 81,000 | 81,000 | 81,000 | 81,000 | 81,000 | 81,000 | 81,000 | 567,000 | 12 |
|  |  |  |  | 71400 | Contractual Services - Individual | 7,931 | 7,931 | 9,011 | 9,011 | 9,011 | 9,011 | 9,011 | 60,917 | 13 |
|  |  |  |  | 71600 | Travel | 10,000 | 20,000 | 0 | 0 | 10,000 | 0 | 0 | 40,000 | 14 |
|  |  |  |  | 72100 | Contractual Services-Companies | 45,000 | 110,000 | 120,000 | 0 | 0 | 0 | 120,000 | 395,000 | 15 |
|  |  |  |  | 72100 | Contractual Services-Companies | 0 | 450,000 | 450,000 | 300,000 | 200,000 | 100,000 | 50,000 | 1,550,000 | 16 |
|  |  |  |  | 72100 | Contractual Services-Companies | 0 | 205,000 | 120,000 | 120,000 | 0 | 0 | 0 | 445,000 | 17 |
|  |  |  |  | 72200 | Equipment and furniture | 0 | 25,000 | 0 | 0 | 0 | 0 | 0 | 25,000 | 18 |
|  |  |  |  | 72500 | Supplies | 0 | 2,520 | 2,520 | 2,520 | 2,520 | 2,520 | 2,520 | 15,120 | 19 |
|  |  |  |  | 72800 | IT Equipment | 0 | 25,000 | 0 | 0 | 0 | 0 | 0 | 25,000 | 20 |
|  |  |  |  | 73100 | Rental & Maintenance - Premises | 0 | 36,000 | 36,000 | 30,000 | 24,000 | 18,000 | 12,000 | 156,000 | 21 |
|  |  |  |  | 74200 | Printing and Publication | 0 | 6,500 | 6,500 | 0 | 0 | 6,500 | 0 | 19,500 | 22 |
|  |  |  |  | 75700 | Training, Workshops and Confer | 25,000 | 75,000 | 50,000 | 0 | 0 | 0 | 0 | 150,000 | 23 |
|  |  |  |  |  | Total Outcome 2 | 168,931 | 1,043,951 | 875,031 | 542,531 | 326,531 | 217,031 | 274,531 | 3,448,537 |  |
| COMPONENT/OUTCOME 3 | UNDP (PIU)/Project partners (TBD) | 62000 | GEF TF | 61300 | Salary and Post Adj – IP Staff | 81,000 | 81,000 | 81,000 | 81,000 | 81,000 | 81,000 | 81,000 | 567,000 | 24 |
|  |  |  |  | 71200 | International Consultants | 0 | 0 | 36,000 | 0 | 0 | 0 | 30,000 | 66,000 | 25 |
|  |  |  |  | 71300 | National Consultants | 0 | 0 | 24,000 | 0 | 0 | 0 | 20,000 | 44,000 | 26 |
|  |  |  |  | 71400 | Contractual Services - Individual | 4,507 | 4,507 | 4,507 | 4,507 | 4,507 | 4,507 | 4,507 | 31,549 | 27 |
|  |  |  |  | 71400 | Contractual Services - Individual | 7,087 | 7,087 | 7,087 | 7,087 | 7,087 | 7,087 | 7,087 | 49,609 | 28 |
|  |  |  |  | 71400 | Contractual Services - Individual | 36,000 | 36,000 | 36,000 | 36,000 | 36,000 | 36,000 | 37,703 | 253,703 | 29 |
|  |  |  |  | 71600 | Travel | 0 | 0 | 10,000 | 0 | 0 | 0 | 6,522 | 16,522 | 30 |
|  |  |  |  | 72400 | Audio Visual & Print Production Costs | 7,000 | 7,000 | 7,000 | 7,000 | 7,000 | 7,000 | 7,000 | 49,000 | 31 |
|  |  |  |  | 72600 | Grants | 0 | 250,000 | 600,000 | 440,000 | 200,000 | 0 | 0 | 1,490,000 | 32 |
|  |  |  |  | 72600 | Grants | 0 | 0 | 300,000 | 500,000 | 750,000 | 750,000 | 400,000 | 2,700,000 | 33 |
|  |  |  |  | 75700 | Training, Workshops and Confer | 30,000 | 30,000 | 30,000 | 30,000 | 30,000 | 30,000 | 30,000 | 210,000 | 34 |
|  |  |  |  | 75700 | Training, Workshops and Confer | 25,000 | 0 | 0 | 25,000 | 0 | 0 | 25,000 | 75,000 | 35 |
|  |  |  |  |  | Total Outcome 3 | 190,594 | 415,594 | 1,135,594 | 1,130,594 | 1,115,594 | 915,594 | 648,819 | 5,552,383 |  |
| Project Management Cost | UNDP (PIU) | 62000 | GEF TF | 71400 | Contractual Services - Individual | 20,000 | 20,000 | 20,000 | 20,000 | 20,000 | 20,000 | 20,000 | 140,000 | 36 |
|  |  |  |  | 71400 | Contractual Services - Individual | 8,000 | 8,000 | 8,000 | 8,000 | 8,000 | 8,000 | 8,000 | 56,000 | 37 |
|  |  |  |  | 71600 | Travel | 11,000 | 14,984 | 11,000 | 11,000 | 11,000 | 11,000 | 11,000 | 80,984 | 38 |
|  |  |  |  | 72200 | Equipment & furniture | 20,000 | 0 | 0 | 0 | 0 | 0 | 0 | 20,000 | 39 |
|  |  |  |  | 72500 | Supplies | 2,500 | 2,500 | 2,500 | 2,500 | 2,500 | 2,500 | 2,500 | 17,500 | 40 |
|  |  |  |  | 72800 | IT Equipment | 21,179 | 0 | 0 | 0 | 0 | 0 | 0 | 21,179 | 41 |
|  |  |  |  | 74100 | Professional Services | 5,000 | 5,000 | 5,000 | 5,000 | 5,000 | 5,000 | 5,000 | 35,000 | 42 |
|  |  |  |  | 74596 | Services to projects - GOE for CO | 18,000 | 18,000 | 18,000 | 18,000 | 18,000 | 18,000 | 18,000 | 126,000 | 43 |
|  |  |  |  | 75700 | Training, Workshops and Confer | 6,000 | 6,000 | 6,000 | 6,000 | 6,000 | 6,000 | 6,000 | 42,000 | 44 |
|  |  |  |  |  | GEF Total (Project Management) | 111,679 | 74,484 | 70,500 | 70,500 | 70,500 | 70,500 | 70,500 | 538,663 |  |
|  | UNDP (PIU) | 04000 | UNDP TRAC | 71400 | Contractual Services - Individual | 13,517 | 13,517 | 13,517 | 13,517 | 13,517 | 13,517 | 13,517 | 94,619 | 45 |
|  |  |  |  | 71400 | Contractual Services - Individual | 12,402 | 12,402 | 12,402 | 12,402 | 12,402 | 12,402 | 12,402 | 86,814 | 46 |
|  |  |  |  | 71600 | Travel | 6,699 | 6,699 | 6,699 | 6,699 | 6,699 | 6,699 | 6,699 | 46,893 | 47 |
|  |  |  |  |  | UNDP TRAC Total (Project Management) | 32,618 | 32,618 | 32,618 | 32,618 | 32,618 | 32,618 | 32,618 | 228,326 |  |
|  |  |  |  | Total Project Management |  | 144,297 | 107,102 | 103,118 | 103,118 | 103,118 | 103,118 | 103,118 | 766,989 |  |
|  |  |  |  | GEFTF TOTAL |  | 719,314 | 1,832,139 | 2,447,797 | 1,966,735 | 1,715,735 | 1,413,235 | 1,216,960 | 11,311,915 |  |
|  |  |  |  | PROJECT TOTAL |  | 751,932 | 1,864,757 | 2,480,415 | 1,999,353 | 1,748,353 | 1,445,853 | 1,249,578 | 11,540,241 |  |

Summary of Funds (USD)

| Source of funds | YR1 | YR2 | YR3 | YR4 | YR5 | YR6 | YR7 | TOTAL |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| GEF | 719,314 | 1,832,139 | 2,447,797 | 1,966,735 | 1,715,735 | 1,413,235 | 1,216,960 | 11,311,915 |
| UNDP | 32,618 | 32,618 | 32,618 | 32,618 | 32,618 | 32,618 | 32,618 | 228,326 |
| Govt. of PNG | 2,857,143 | 2,857,143 | 2,857,143 | 2,857,143 | 2,857,143 | 2,857,143 | 2,857,142 | 20,000,000 |
| Walindi Plantation Resort | 50,000 | 50,000 | 50,000 | 50,000 | 50,000 | 50,000 | 50,000 | 350,000 |
| Barrick (N) Ltd | 80,000 | 80,000 | 80,000 | 80,000 | 80,000 | 80,000 | 120,000 | 600,000 |
| New Guinea Binatang Research Centre | 242,000 | 248,000 | 248,000 | 248,000 | 248,000 | 248,000 | 248,000 | 1,730,000 |
| FORCERT | 140,000 | 140,000 | 140,000 | 160,000 | 140,000 | 140,000 | 140,000 | 1,000,000 |
| WCS | 140,000 | 140,000 | 140,000 | 160,000 | 140,000 | 140,000 | 140,000 | 1,000,000 |
| Mahonia na Dari | 15,000 | 15,000 | 15,000 | 30,000 | 15,000 | 15,000 | 15,000 | 120,000 |
| Woodland Park Zoo | 500,000 | 500,000 | 530,000 | 730,000 | 500,000 | 500,000 | 500,000 | 3,760,000 |
| DFAT | 2,191,060 | 2,191,060 | 2,191,060 | 2,191,060 | 2,191,061 | 2,191,061 | 2,191,061 | 15,337,423 |
| Forest Carbon Partnership Facility 2 (WB/UNDP) | 700,000 | 700,000 | 700,000 | 800,000 | 700,000 | 700,000 | 700,000 | 5,000,000 |
| New Britain Palm Oil | 200,500 | 200,000 | 195,000 | 160,000 | 160,000 | 160,000 | 160,000 | 1,235,500 |
| TOTAL | 7,867,635 | 8,985,960 | 9,626,618 | 9,465,556 | 8,829,557 | 8,527,057 | 8,370,781 | 61,673,164 |

Budget Notes

| Component 1 |  |
| --- | --- |
| 1 | International staff - partial cost of Chief Technical Officer (equivalent international P4 position) for 7 years.; the partial costs are linked to the time (40%) that s/he is expected to spend on Outcome 1 as described in the draft TOR: the TOR include various technical aspects relating to financial sustainability within the protected area system of PNG, including leading the development of the Business Plan (Output 1.2) and capacity development of various partners regarding financial management and legal literacy (Output 1.3). Total USD 756,000. |
| 2 | Contracting services; partial cost of Project Manager; Project Manager TOR includes technical aspects of institution building and capacity development - Has technical functions thus is costed across outcomes (costs at 10% in Outcome 1) Total USD 31,542. |
| 3 | Contracting services; partial cost of Administrative, Procurement and Financial Officer; TOR includes technical aspects of capacity development in financial and accounting matters with partners (Output 1.3) thus 20% costed in Outcome 1. Total USD 49,609. |
| 4 | Contracting services; partial cost (30% - associated with social and environmental aspects of institutional analysis, and building capacity – especially to take into account the gender and power issues) of Social & Environmental Safeguards Officer; has technical functions on some outputs (Output 1.1, 1.3, 2.2, 3.1, 3.2 and 3.3) thus costed in technical sections. Total USD 94,619 |
| 5 | Travel costs (estimated partly on basis of costs for PPG mission into the field; including accommodation @ USD 120/night, flights @ USD 200/flight, vehicle @ USD 200/day and plane hire @ USD 2,500/hour (7 pax) associated with developing capacity (Outputs 1.3) Total USD 113,890. |
| 6 | Contracting services for an institutional analysis and mapping of institutions and organisations involved in protected area management (Output 1.1), and developing capacity and mentoring (especially CEPA's) on basis of analysis and mapping @ USD 80,000 (Output 1.3) – thus, one company to do both. The cost is a lump sum figure that includes international travel (for any international consultants associated with bids), visas, terminal expenses, insurance, a portion of the in-country travel, accommodation, DSA |
| 7 | Contracting services for development of the "METT for PNG" (Output 1.3 and Annex H) - with a focus on the community conservation areas (thus, those protected areas owned and managed by customary owners and users of the land @ USD 45,000. The cost is a lump sum figure that includes international travel (for any international consultants associated with bids), visas, terminal expenses, insurance, a portion of the in-country travel, accommodation, DSA |
| 8 | Contracting service to a small number of key organisations following UNDP Financial rules and regulations (to be identified - but probably to include FORCERT, PNG Centre for Locally Managed Areas, WCS, BRC and others to be identified) to work in partnerships at a local level (including in pilot sites of Output 3.1 and 3.2) to build capacity and mentor local communities - including land owners and users, LLG and district administrations, wards (Output 1.3). Total USD 300,000 |
| 9 | Web publishing and the design, printing, binding and circulation of the business plan (under Output 1.2) Total USD 14,000 |
| 10 | Costs of participatory workshops and consultative meetings associated with i) the institutional analysis - including participatory mapping process and participatory reviews of the implementation and application of the results of the analysis (Output 1.1), ii) the development of the Business Plan (Output 1.2), and iii) training and capacity development, including covering the costs of participatory and consultative workshops and meetings to develop the "METT for PNG" (Output 1.3). Workshops costs include the costs of travel and accommodation for invitees. On average, a workshop with 40 participants in PNG costs in the vicinity of USD 20,000. In order to improve cost effectiveness, some of the workshops across the project will be run back-to-back because many of the participants are the same. Total USD 190,000. |
| 11 | South-south and Triangular Cooperation: study tour for 12 selected representatives (e.g., from CEPA, facilitator organisations and representatives from key communities involved in protected area management) to learn from best practice of community-conservation protected area governance, management and financing (Output 1.3). The budget includes an estimate for flights, visas, accommodation, for participants. Total USD 97,672 |
| Component 2 |  |
| 12 | International staff - partial cost of Chief Technical Officer (equivalent international P4 position); the partial costs are linked to the time (30%) that s/he is expected to spend on Outcome 2 as described in the draft TOR: the TOR include various technical aspects relating to financial sustainability within the protected area system of PNG, including backstopping the development and implementation of the fund raising/resource mobilisation strategy for the Biodiversity Fund (Output 2.3) Total USD 567,000. |
| 13 | Contracting services; partial cost (20% - linked to the satisfactory incorporation of social and environmental safeguards into the policies and strategies of the Biodiversity Fund) of Social & Environmental Safeguards Officer; has technical functions on some outputs (Output 1.1, 1.3, 2.2, 3.1, 3.2 and 3.3) thus costed in technical sections. Total USD 60,917. |
| 14 | Travel costs associated with MPTF and other service provider representatives travelling to Port Moresby for discussions regarding establishment of the Biodiversity Fund (Output 2.1 and 2.2), to sign agreements and to work on development of Fund Raining Strategy (Output 2,.3). The estimates include costs of travel, visas, accommodation and DSA. Total USD 40,000. |
| 15 | Contracting services to facilitate establishment of governing, administration and management structures, and all associated documentation (through inclusive, participatory process) for Biodiversity Fund including governing documents, strategic and operational planning documents - which will also include legal analysis for establishment of Biodiversity Fund - building on the PA Bill (which includes the provision for legal establishment of the Biodiversity Fund); developing regulations for approval under the PA Bill (once enacted). @ USD 395,000; Outputs 2.1 and 2.2. The cost is a lump sum figure that includes international travel (for any international consultants associated with bids), visas, terminal expenses, insurance, a portion of the in-country travel, accommodation, DSA |
| 16 | Contracting the services of the Technical Secretariat (the Fund management team) to manage day-to-day implementation of the Biodiversity Fund (Output 2.1); once the Biodiversity Fund has been established, the costs of the Technical Secretariat will be progressively transferred from the project to the BF overheads; Total USD 1,550,000. |
| 17 | Contracting services for development and support to implementation of fund-raising strategy for the Biodiversity Fund including its review @ US$ 445,000 (Output 1.3). Once the Biodiversity Fund has been established, a portion of the interest from the initial capital will be used to continue to the fund raising - until such time as the Biodiversity Fund is sufficiently capitalised. |
| 18 | Equipment and furniture for Technical Secretariat: office furniture. Total USD 25,000. |
| 19 | Office supplies, paper, cartridges and other consumables including mobile phone plan for Technical Secretariat. Total USD 15,120. |
| 20 | IT Equipment for Technical Secretariat: laptops (up to US$ 1,500 per computer), unit printer-scanner-copier (up to US$ 3,500), communication equipment such as wifi router, cell phones (US$ 200 per unit). Total USD 25,000. |
| 21 | Rental for office space to establish Biodiversity Fund's office to accommodate the Technical Secretariat @ USD 36,000/year (although if there is an option to purchase an office, this option will be explored). The Biodiversity Fund Office must be independent of both UNDP and CEPA - as per best global practices for Conservation Trust Funds. once the Biodiversity Fund has been established, the costs of the rental will be progressively transferred from the project to the BF overheads. Total USD 156,000. |
| 22 | Web publishing and the design, printing, binding and circulation of the material associated with the fund-raising strategy for the Biodiversity Fund (Output 2.3) @ USD 19,500 |
| 23 | Costs of participatory workshops and consultative meetings associated with developing the Biodiversity Fund governing structures (Outputs 2.1 and 2.2), and to leverage and socialize documentation for the Biodiversity Fund (@USD 25,000/workshop). Workshops costs include the costs of travel and accommodation for invitees. Total USD 150,000. |
| Component 3 |  |
| 24 | International staff - partial cost of Chief Technical Officer (equivalent international P4 position); the partial costs are linked to the time (30%) that s/he is expected to spend on Outcome 3 as described in the draft TOR: the TOR include various technical aspects relating to financial sustainability within the protected area system of PNG, including technical assistance to the pilot sites and catalysing the revenue generating systems (Output 3.2). Total USD 567,000. |
| 25 | International mid-term evaluation consultant (12 weeks @ $3,000/week) and an international final evaluation consultant (10 weeks @ $3,000/week). Total USD 66,000. |
| 26 | National mid-term evaluation consultant (12 weeks @ $2,000/week) and a national final evaluation consultant (10 weeks @ $2,000/week). Total USD 44,000. |
| 27 | Contracting services; partial cost of Project Manager; Project Manager TOR includes technical aspects of institution building and capacity development - Has technical functions thus can be costed across outcomes (costs at 10% in Outcome 3). Total USD 31,549 |
| 28 | Contracting services; partial cost of Administrative, Procurement and Financial Officer; TOR includes technical aspects of capacity development in financial matters with partners (Output 1.3) thus 25% costed in Outcome 1 - Has some technical functions (Output 1.3, and in Output 3.1 and 3.2) thus 20% in Outcome 3. Total USD 49,609. |
| 29 | Contracting services; partial cost (30% - linked to the social and environmental safeguards associated with the pilot sites – Output 3.1 and 3.2 as well as assimilating lessons from across the protected area system in the country – Output 3.3) of Social & Environmental Safeguards Officer; has technical functions on some outputs thus costed in technical sections. Total USD 253,703. |
| 30 | Travel costs associated with the MTR and TE processes. Total USD 16,522. |
| 31 | Documentation of the proceedings from the annual protected area forums as well as other lessons learned through M&E processes for electronic dissemination @ USD 7,000/year (see above) (Outputs 3.3 and 3.4). Total USD 49,000. |
| 32 | Grants for LLGs/CBOs/NGOs in the three pilot sites (Sepik Wetlands, Mt Wilhelm and Kimbe Bay) to support processes that will lead to sustainable revenue generating activities; (Output 3.2, 3.3, 3.4, 1.2). The estimated total investments/allocations for the three sites are USD 420,000, USD 620,000 and USD 450,000 respectively on the basis that the process will be more expensive in Mt Wilhelm associated with the research infrastructure that is necessary in that area. This will be managed as part of the sinking fund. Total USD 1,490,000. The use of grants shall follow UNDP micro-capital grant policy. |
| 33 | Grants to be provided through the Biodiversity Fund (sinking fund) to CSOs/NGOs, LLGs & Communities, in order to test the efficacy of the fund. Grants will be disbursed following the UNDP micro-capital grant policy for pilot sites to initiate operationalisation and test granting processes under the Biodiversity Fund (Outputs 3.1 and 3.2). Total USD 2,700,000. |
| 34 | Annual forums for protected areas - to learn lessons from Outputs 1.1, 1.3, 3.1, 3,2 and 3.3 (as well as other protected areas programs that are ongoing in the country - e.g., other GEF projects and the USAID program). A broad range of stakeholders will be invited to share methodologies, experiences and lessons (such meetings could be followed by PB meetings). The proceedings of these forums will be published for electronic dissemination (see below). The forum costs include the costs of travel and accommodation of the invitees. In order to improve cost effectiveness, some of the workshops across the project will be run back-to-back because many of the participants are the same. In addition, on an annual basis, the project team will seek sponsors to support these meetings. In addition, where the lessons from other projects and/or programs are being shared, cost-sharing will be encouraged. Total USD 210,000. |
| 35 | To cover the costs of the Project Inception Workshop, and meetings and consultative workshops associated with the Midterm Review and Terminal Evaluation. Total USD 75,000. |
| PMC |  |
| 36 | Contracting services; partial cost of Project Manager; Project Manager TOR includes technical aspects of institution building and capacity development - Has technical functions thus can be costed across outcomes (costs at 80% in PMC - 50% costed to the GEF). Total USD 140,000 |
| 37 | Contracting services; partial cost (25%) of Administrative, Procurement and Financial Officer. Total USD 56,000 |
| 38 | Partial costs (66%) for additional travel budget for PIU (especially Project Manager and SESO) for site visits Total USD 80,984 |
| 39 | Procurement of equipment and office furniture for PIU. Total USD 20,000. |
| 40 | Office supplies, paper, cartridges and other consumables including mobile plan; and car maintenance and fuel. Total USD 17,500 |
| 41 | Laptops (up to US$ 1,500 per computer), 1 unit printer-scanner-copier (up to US$ 3,500), communication equipment such as Wi-Fi routers and satellite phones (@ US$ 1,179) for PIU. Total USD21,179 |
| 42 | Covering the costs of annual financial audits for the project. Total USD 35,000. |
| 43 | UNDP Direct Project Costs –Total USD 126,000, cover services for payment processing, recruitment of project personnel, procurement of goods and services, organization of training, travel arrangement, and other administration. Details of services and associated costs will be documented in Letter of agreement and submitted at DOA issuance stage |
| 44 | Covering the costs of the Project Board meetings (@ USD 3,000/meeting with 2 meetings/year - including the accommodation and travel for the members of the PB). Total USD 42,000. |
| 45 | Contracting services; partial cost of Project Manager; Project Manager TOR includes technical aspects of institution building and capacity development - Has technical functions thus can be costed across outcomes (costs at 80% in PMC - 30% costed to the UNDP). Total USD 94,619. |
| 46 | Contracting services; partial cost (35%) of Administrative, Procurement and Financial Officer. Total USD 86,814. |
| 47 | Partial costs (37%) for additional travel budget for PIU (especially Project Manager and SESO) for site visits. Total USD 46,893. |

# Legal Context

- This project document shall be the instrument referred to as such in Article 1 of the Standard Basic Assistance Agreement between the Government of Papua New Guinea and UNDP, signed in 1981.   All references in the SBAA to “Executing Agency” shall be deemed to refer to “Implementing Partner.”

- This project will be implemented by the Conservation and Environmental Protection Authority (CEPA, the “Implementing Partner”) with Support Services being provided by UNDP – including the day-to-day implementation of the project - in accordance with UNDP’s financial regulations, rules, practices and procedures.  The financial governance of UNDP shall be applied to provide the required guidance to ensure best value for money, fairness, integrity, transparency, and effective international competition.

- Any designations on maps or other references employed in this project document do not imply the expression of any opinion whatsoever on the part of UNDP concerning the legal status of any country, territory, city or area or its authorities, or concerning the delimitation of its frontiers or boundaries.

# Risk Management

- Government Entity (NIM).  Consistent with the Article III of the SBAA, the responsibility for the safety and security of the Implementing Partner and its personnel and property, and of UNDP’s property in the Implementing Partner’s custody, rests with the Implementing Partner. To this end, the Implementing Partner shall:

  - put in place an appropriate security plan and maintain the security plan, taking into account the security situation in the country where the project is being carried;

  - assume all risks and liabilities related to the Implementing Partner’s security, and the full implementation of the security plan.

- UNDP reserves the right to verify whether such a plan is in place, and to suggest modifications to the plan when necessary. Failure to maintain and implement an appropriate security plan as required hereunder shall be deemed a breach of the Implementing Partner’s obligations under this Project Document.

- The Implementing Partner agrees to undertake all reasonable efforts to ensure that no UNDP funds received pursuant to the Project Document are used to provide support to individuals or entities associated with terrorism and that the recipients of any amounts provided by UNDP hereunder do not appear on the list maintained by the Security Council Committee established pursuant to resolution 1267 (1999). The list can be accessed via http://www.un.org/sc/committees/1267/aq_sanctions_list.shtml.

- Social and environmental sustainability will be enhanced through application of the UNDP Social and Environmental Standards (http://www.undp.org/ses) and related Accountability Mechanism (http://www.undp.org/secu-srm).

- The Implementing Partner shall: (a) conduct project and programme-related activities in a manner consistent with the UNDP Social and Environmental Standards, (b) implement any management or mitigation plan prepared for the project or programme to comply with such standards, and (c) engage in a constructive and timely manner to address any concerns and complaints raised through the Accountability Mechanism. UNDP will seek to ensure that communities and other project stakeholders are informed of and have access to the Accountability Mechanism.

- All signatories to the Project Document shall cooperate in good faith with any exercise to evaluate any programme or project-related commitments or compliance with the UNDP Social and Environmental Standards. This includes providing access to project sites, relevant personnel, information, and documentation.

- The Implementing Partner will take appropriate steps to prevent misuse of funds, fraud or corruption, by its officials, consultants, responsible parties, subcontractors and sub-recipients in implementing the project or using UNDP funds.  The Implementing Partner will ensure that its financial management, anti-corruption and anti-fraud policies are in place and enforced for all funding received from or through UNDP.

- The requirements of the following documents, then in force at the time of signature of the Project Document, apply to the Implementing Partner: (a) UNDP Policy on Fraud and other Corrupt Practices and (b) UNDP Office of Audit and Investigations Investigation Guidelines. The Implementing Partner agrees to the requirements of the above documents, which are an integral part of this Project Document and are available online at www.undp.org.

- In the event that an investigation is required, UNDP has the obligation to conduct investigations relating to any aspect of UNDP projects and programmes. The Implementing Partner shall provide its full cooperation, including making available personnel, relevant documentation, and granting access to the Implementing Partner’s (and its consultants’, responsible parties’, subcontractors’ and sub-recipients’) premises, for such purposes at reasonable times and on reasonable conditions as may be required for the purpose of an investigation. Should there be a limitation in meeting this obligation, UNDP shall consult with the Implementing Partner to find a solution.

- The signatories to this Project Document will promptly inform one another in case of any incidence of inappropriate use of funds, or credible allegation of fraud or corruption with due confidentiality.

- Where the Implementing Partner becomes aware that a UNDP project or activity, in whole or in part, is the focus of investigation for alleged fraud/corruption, the Implementing Partner will inform the UNDP Resident Representative/Head of Office, who will promptly inform UNDP’s Office of Audit and Investigations (OAI). The Implementing Partner shall provide regular updates to the head of UNDP in the country and OAI of the status of, and actions relating to, such investigation.

- UNDP shall be entitled to a refund from the Implementing Partner of any funds provided that have been used inappropriately, including through fraud or corruption, or otherwise paid other than in accordance with the terms and conditions of the Project Document.  Such amount may be deducted by UNDP from any payment due to the Implementing Partner under this or any other agreement.

- Where such funds have not been refunded to UNDP, the Implementing Partner agrees that donors to UNDP (including the Government) whose funding is the source, in whole or in part, of the funds for the activities under this Project Document, may seek recourse to the Implementing Partner for the recovery of any funds determined by UNDP to have been used inappropriately, including through fraud or corruption, or otherwise paid other than in accordance with the terms and conditions of the Project Document.

- Note:  The term “Project Document” as used in this clause shall be deemed to include any relevant subsidiary agreement further to the Project Document, including those with responsible parties, subcontractors and sub-recipients.

- Each contract issued by the Implementing Partner in connection with this Project Document shall include a provision representing that no fees, gratuities, rebates, gifts, commissions or other payments, other than those shown in the proposal, have been given, received, or promised in connection with the selection process or in contract execution, and that the recipient of funds from the Implementing Partner shall cooperate with any and all investigations and post-payment audits.

- Should UNDP refer to the relevant national authorities for appropriate legal action any alleged wrongdoing relating to the project, the Government will ensure that the relevant national authorities shall actively investigate the same and take appropriate legal action against all individuals found to have participated in the wrongdoing, recover and return any recovered funds to UNDP.

- The Implementing Partner shall ensure that all of its obligations set forth under this section entitled “Risk Management” are passed on to each responsible party, subcontractor and sub-recipient and that all the clauses under this section entitled “Risk Management Standard Clauses” are included, mutatis mutandis, in all sub-contracts or sub-agreements entered into further to this Project Document.

# Annexes

Annex A:  Multi Year Work Plan	98

Annex B:  GEF Tracking Tool at baseline	101

Annex C: Overview of Technical Consultancies and Contracts	102

Annex D: Terms of Reference	107

Annex E: List of Protected Areas in PNG	115

Annex F: List of people consulted over the course of the PPG process	118

Annex G: Process of selecting pilot sites.	126

Annex H: A proposal to develop a “METT for PNG”	131

Annex I: UNDP Social and Environmental Screening Procedure and plans as needed	133

Annex J: Stakeholder Engagement Plan	133

Annex K: Gender Analysis and Action Plan	138

Annex L: Additional Maps	146

Annex M: UNDP Risk Log	147

Annex N: Results of the capacity assessment of the project implementing partner and HACT micro assessment	151

Annex O: Capacity Scorecard Assessments for key government institutions	152

## Annex A:  Multi Year Work Plan

|  |  |  | YR1 |  |  |  | YR2 |  |  |  | YR3 |  |  |  | YR4 |  |  |  | YR5 |  |  |  | YR6 |  |  |  | YR7 |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Output | Activity | Responsible Party | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 |
| Project start-up | Finalise tender for staff for PIU (specifically PM and APFO); advertise; receive and evaluate applications; offer contracts | UNDP-CO, CEPA | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Contract negotiations; sign contract | UNDP-CO | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Orient PIU team | UNDP-CO | X | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | National Inception workshop | PIU |  | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Identify partners for different components | PIU, UNDP-CO, CEPA |  | X | X |  |  |  |  |  |  |  |  |  |  | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Gender mainstreaming | Monitoring and follow-up of gender mainstreaming effectiveness | PIU |  |  |  |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X |
| M&E | Review of results framework and indicators | PIU |  |  |  | X |  | X |  |  |  | X |  | X | X | X |  |  |  | X |  |  |  | X |  |  |  | X | X | X |
|  | Measurement of indicators | PIU, partners |  |  | X | X |  | X |  |  |  | X |  | X | X | X |  |  |  | X |  |  |  | X |  |  |  | X | X | X |
|  | Mid-term review | UNDP-CO |  |  |  |  |  |  |  |  |  |  |  |  | X | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Final evaluation | UNDP-CO |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | X | X |
| Project closure | Negotiation of details of exit/sustainability strategy | PIU/UNDP-CO |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | X | X |  |  |  |
|  | Review/feedback workshop | PIU, UNDP-CO |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | X |
|  | Administrative closure | UNDP-CO |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | X |
| Outcome 1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 1.1 Institutional analysis and mapping | Contracted institutional analysis and mapping | PIU, contractor |  |  |  | X | X | X | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 1.2 Business planning | Business plan developed and implemented | PIU, contractor |  |  |  |  |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X |
| Output 1.3 Capacity development | CEPA capacity development | PIU, CEPA, Contractors |  |  |  |  |  |  |  | X | X | X |  |  |  |  | X |  |  |  | X |  |  |  | X |  |  | X | X |  |
|  | Capacity development, selected partners and local communities | PIU, partners |  |  |  |  |  |  |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X |
| Outcome 2 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 2.1: Establishing Biodiversity Fund | Development of governing documents for Biodiversity Fund | PIU, PB |  |  |  |  | X | X | X | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Contracted review of policies and legislation | PIU, Contractor |  |  |  | X | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Recruitment of Secretariat | PIU, BFSC |  |  |  |  |  | X | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Establishment of Biodiversity Fund office | PIU, BFSC |  |  |  |  |  |  | X | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Sign agreement with MPTF | PIU, UNDP-CO, MPTF |  |  |  |  |  |  | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Recruitment of Investment Manager | BFSC, |  |  |  |  |  |  |  | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 2.2 Biodiversity Fund’s strategic and operational framework | Development of strategic and operational documents | BFSC, PIU, BFTS, Contractor |  |  |  |  |  |  | X | X | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 2.3: Fund raising/ resource mobilisation | Development of fund raising strategy | PIU, BFSC, BFTS, Contractor |  |  |  |  |  |  |  | X | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Implementation of fund raising strategy | PIU, BFSC, Contractor, BFTS |  |  |  |  |  |  |  |  |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X |
| Outcome 3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 3.1 Testing fund delivery systems | Making grants/loans to protected areas | PIU, BFTS, partners |  |  |  |  |  |  |  |  |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X |
| Output 3.2 Piloting mechanisms to catalyse revenue streams | Sepik Wetlands | PIU, BFTS, BFSC, partners |  |  |  |  |  |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X |
|  | Mt Wilhelm |  |  |  |  |  |  |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X |
|  | Kimbe Bay |  |  |  |  |  |  |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X |
| Output 3.3 M&E, learning | Learning lessons from ongoing practices | PIU, BFTS, partners |  |  |  |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X |
|  | Disseminating lessons and information across partners |  |  |  |  |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X |
|  | Annual PA forum |  |  |  |  | X |  |  |  | X |  |  |  | X |  |  |  | X |  |  |  | X |  |  |  | X |  |  |  | X |

## Annex B:  GEF Tracking Tool at baseline

| Capacity Scorecard for CEPA | As developed by the GEF-5 project. See Annex O. |
| --- | --- |
| METT | See Annex H |
| Financial Scorecard | Attached. However, there are significant shortcomings to the Financial Scorecard for two principal reasons: First, the data for the protected areas and protected area system in the country is very poor – this is true even of CEPA and the few areas for which CEPA has the mandate to managed (although, as indicated in Annex E, the majority of these are nominally managed by CEPA). There are good data for only one protected area in the country: this is the Yus Conservation Area (see worksheet in the Financial Scorecard) – both for projected budgets (basic and optimal) and for past expenditure. Second and conversely, the current situation is that the greater majority of protected areas in the country simply do not have any budget of any kind. In addition, the projected estimated budgets for the protected areas across the country (also see worksheet in the Financial Scorecard) are flawed by many assumptions that they make (e.g., that there is a need for ‘traditional’ PA management systems – including management committees and patrols – despite the flaws that have been demonstrated of such management systems among the community-owned and used areas across PNG (see Section II). In conclusion, the Financial Scorecard – especially the estimates of basic and optimal funding needs, as well as current budgets and expenditure, is of limited value. Indeed, as with the proposed “METT for PNG” (see Annex H), a similar unique tool should be developed for PNG on the basis that the GEF’s Financial Scorecard is full of assumptions that do not apply to the unique nature of Papua New Guinea’s protected areas. |

## Annex C: Overview of Technical Consultancies and Contracts

The majority of the technical consultancies, listed below, will be for companies or teams of people.  Bids will be evaluated on the basis of a number of criteria, including (but not limited to): i) the proposed composition of the team, ii) the relevance of the organisation’s experience to working in the sector and on similar projects and their capacity – documented as part of their bid – to manage the processes foreseen in the implementation of such a project, iii) the relevance of the organisation’s experience to working in the context of PNG, iv) a micro-capacity assessment of the bidding organisations, and v) the opportunities that are presented to well-qualified PNG nationals on the team.  The bidding parties will also have to demonstrate how they will be deemed trustworthy by and downward accountable to the communities as well as upward accountable to the government, UNDP and the GEF. Indeed, bids that include a consortium – coupling the required technical expertise and strong social and gender content (that may be effected through bids that include a strong civil society organisation), such that social and gender content is adequately addressed from the outset of the project, will be encouraged.  Furthermore, there is an expectation that all contractors and consultants to include a demonstrable transfer of skills and knowledge such that at the MTR and TE, the project will be in a position to demonstrate how those skills and that knowledge is actually being used at the midpoint and end of the project’s life.

| Consultant | Time input |
| --- | --- |
| Institutional Analysis and Mapping |  |
| The mandate of the various organisations – particularly the government entities – with respect to the protected areas of the country is not clear. This is primarily because of the rather unique nature of PNG and the customary land tenure system within the country – and the institutions have not been built in response to the unique nature of the environment and society. As a result, there is a need to ensure that each organisation is clear about their mandate, with their roles and responsibilities within the sector. Under Output 1.1, there will be a participatory and facilitated assessment and mapping of the institutions and organisations that are involved in protected area management and financing to determine the roles and responsibilities of the institutions and organisations. In the case of CEPA, the work will also include determining how best it may be structured to fulfil its identified roles and responsibilities – including their mandated role in collecting fines and imposing sanctions in cases of violations of environmental laws and regulations (particularly with respect to protected areas and with respect to violations by extractive and agro-industry parties), as well as providing legal protection of communities from ‘land-grabbing’ processes. The other key set of organisations are the Wards and Local Level Governments (LLGs) – as these really operate at the level of the protected areas and the community owners of the land – and how they need to be supported by the Provincial Governments. There is also a need to understand the roles of different sectors of society – at the grassroots or community level – have in natural resource management and, by extension, in protected area management. This includes different age groups, different genders, different ethnic or clan structures. This work will be transformative. The result will be a clear understanding and mapping of all organisations’ roles and responsibilities with respect to protected area management and financing; the mapping will also include how different genders and ages are included in the system (including within the government and non-state actors). The stakeholders will be better equipped to understand their capacity development needs because they will understand where their capacity is limited with respect to those roles and responsibilities. The institutional mapping process will also identify the gaps within the system and, as a result, it will determine which organisations are best positioned to fill those gaps. One gap was the absence of legal support that CEPA was providing to stakeholders involved in either existing or potential protected area: there is a profound need for CEPA to fulfil this role. There will be a focus on CEPA’s roles and responsibilities. Again, the project aims to be transformative – to transition CEPA from being an organisation that wishes to enforce to one that is supportive and provides services to its constituents and clients. The example given above – providing legal support and services such as conflict mediation to the land owners and land users, including legal protection from extractive and commercial agricultural industries – is a good illustration of this. Other aspects of CEPA’s support and services that they should be providing include facilitating and coordinating, and ensuring that there is no duplication of effort. The same applies to the Wards and LLGs who operate at the level of the protected areas themselves (as they are in a position to represent the expressed, urgent needs of communities with respect to basic social services, including quality education, health care and family planning that are not being provided adequately – thereby hampering sustainable development and maintenance of protected areas). Once the mandate mapping is complete, within CEPA and the LLGs, the process will also map out the roles, responsibilities and expectations of each of the employees – and what they are expected to do on a day-by-day basis – relative to the human and financial capacity of those organisations. The work will be positioned firmly in the socio-political and economic realities of PNG; at the time of the PPG, there were various stakeholders who stated that, in effect, the country was “bankrupt”. The work will also be firmly positioned within the social realities of PNG – explicitly acknowledging that the communities are the principal land owners and land users, and that, as a result, they have a pivotal role to play in the management of protected areas. The work will also identify the partnerships that will be needed for the effective and efficient management of protected areas. Finally, the team contracted to carry out this work will also be contracted (possibly within the same contract) to carry out the capacity development work (under Output 1.3) and having the final payments for the contract(s) withheld until there is a demonstrable improvement in the capacity, efficiency and effectiveness within the stakeholders involved in protected area management and financing. |  |
| Development of “METT for PNG” |  |
| See Annex H |  |
| Legislative Review |  |
| As indicated in Output 2.1, in principle, the legal establishment of the Biodiversity Fund comes through the enactment of the PA Bill. Indeed, the PPG process took place at a time when the PA Bill was going through the process to be approved by the NEC. In addition, some of the regulations associated with the Bill were also in the process of being developed. However, while stakeholders are positive that it will be enacted, there were uncertainties and the regulations may not provide all the necessary aspects for implementation and achievement of this project’s outcomes and objective – including, for example, securing public benefit status for the Biodiversity Fund for tax exemption purposes and any other aspects of the legal establishment of the Biodiversity Fund. As a consequence and in order to facilitate the establishment of the Biodiversity Fund, the project will carry out a review of the existing policies and legislation to ensure that everything is aligned to enable the operationalisation of the Biodiversity Fund – as well as the ability to collect taxes, levies and fees for replenishment of the Biodiversity Fund and/or for protected area management and/or the legislative requirements for some of the revenue generating mechanisms that will be incorporated into the business plan that will be developed under the project (see Output 1.2). As such, the review will be undertaken during the process to establish the Biodiversity Fund and while the Business Planning process is underway. This work will be undertaken by a person or team with sufficient legal capacity and who will be hired specifically for this task. The outputs of the work will not simply be a report with recommendations for the amendments that are necessary, but the people involved in this work will have to work with the relevant stakeholders and organisations to prepare all the amendments that may be necessary such that they are ready for submission to the NEC for final approval. Indeed, these people will be held to account for the work and final payments will be withheld until the drafted amendments have been submitted to the NEC. |  |
| Development of documentation for Biodiversity Fund |  |
| As part of the process to establish and operationalise the Biodviersity Fund, the guiding and governance documents will need to be prepared. This will be done in an inclusive and participatory way, with key stakeholders included and involved in the process to develop the documents. Once developed, the documents will be submitted to the Biodiversity Fund’s Steering Committee (which, for the first two years of the Biodiversity Fund’s life will be the project’s Project Board) for approval. The documents will include: The Operational Manual – that will, in turn, include: i) the roles and responsibilities of the different structures and bodies assoicated with the Biodiversity Fund – including, the Steering Committee, the Secretariat, the Fund Administrator , the Investment Manager, the Advisory Board, ii) the policies, rules of procedure, and principles to which the Biodiversity Fund will adhere (including, for example, that Steering Committee decisions will be made by consensus, and that decisions will be made on the basis of the Fund’s principles, purpose and Theory of Change), iii) the processes by which the Steering Committee and Secretariat will be selected on the basis of expected composition and expertise, and the terms of office, iv) the policies for board meetings (regularity, minutes, decision-making processes; quorum, conflict resolution, fiduciary responsibilities), v) the Conflict of Interest declaration and Code of Conduct for Steering Committee members, vi) the templates for all documents required for the project cycle (including budgets, activity proposals, capacity development requirements, socio-economic development needs, reporting and accountability, etc.). The Fund’s Strategic Plan – which will include the Fund’s priorities and theory of change, and the targets regarding resource mobilisation, which, in turn, will be linked to the Resource Mobilisation Plan The draft agreement between the Biodiversity Fund and the service provider. The Fund’s Risk Management Strategy (that will similarly be linked to the Operational Manual, the Fund’s Strategic Plan and the Fund’s Investment Strategy). [It should be noted that the fund’s i) fund raising/resource mobilisation plan (see below) and ii) investment strategy and design will be developed seperately – with the investment strategy and design being developed by the Fund Administrator and the Investment Manager for submission to the Steering Committee for approval.] |  |
| Development and implementation of the Biodiversity Fund’s fund raising/resource mobilisation plan |  |
| Further from the above work, the project will contract a person or organisation to develop and implement a fund raising/resource mobilisation plan for the Biodiversity Fund (Output 2.3). The aim of the Resource Mobilisation Plan will be to solicit significant contributions to the Biodiversity Fund from a variety of donors, including multi- and bilateral donors, the private sector, and private philanthropists. The fund-raising strategy will be developed in tandem with the business plan for the protected area system of the country (see Output 1.2) recognising that their aims are somewhat different. Nonetheless, the fund-raising strategy will be developed cognisant that one of the objectives of the business plan for the protected area system of PNG that will be developed by the project will be to generate sufficient revenues such that it can cross-subsidize the protected area system – or, more pertinently, the revenues can continue to replenish the Biodiversity Fund on a year-by-year basis. The implementation of the fund-raising strategy will be funded by the project and carried out by a team specifically recruited to do so; the MPTFO will also contribute to the successful development of the strategy as needed. The strategy will include a number of different processes: The fund-raising team, with the assistance of the project, will support donor management processes including i) targeting potential donors – including those from the community in PNG – by preparing detailed project proposals such as for the Green Climate Fund, ii) liaising with different funders, and iii) building working partnerships with funding agencies/ institutions. As a country with vast stored carbon and carbon sequestration processes, there is significant potential to mobilise REDD+ and other carbon financing. However, the feasibility of this needs to be determined – in part by closely watching the progress of other people in securing carbon finance (see Output 3.3). The fund-raising team will also explore all other innovative mechanisms for generating resources for the Biodiversity Fund. For example, none of the stakeholders in PNG had even heard of Debt for Nature swaps; these could be explored as a mechanism to capitalise the Biodiversity Fund. The fund-raising team will also determine the feasibility of including taxes, levies and revenue streams from other sources – including green taxes (e.g., a round-log tax as has been suggested in the PA Bill) and payment for ecosystem services (especially in those situations in which the users are private or semi-autonomous organisations such as PNG Power or Eda Ranu – and other water suppliers around the country) – as mechanisms to replenish the Biodiversity Fund. It is possible (although initially very unlikely) that the protected area system itself will generate sufficient revenues such that it can cross-subsidize other areas within the protected area system – or, possibly, the revenues can continue to replenish the Biodiversity Fund on a year-by-year basis. Ultimately, how these funds will be managed will be decided and written into the fund design; as stated above, this will be reviewed every four years. In addition, on reaching a suitable agreement, other funding mechanisms that have been established or are in the process of being established (e.g., the USAID funding for protected areas) will be amalgamated into the Biodiversity Fund (for more, see Partnerships in Section IV); where it is not possible to do this, synergies and complementarity will be ensured. It is also expected that all funding that would otherwise be allocated through the UNDP-GEF SGP to community-level natural resource management and/or protected area management will be managed through the Biodiversity Fund. In other words, a significant portion of the UNDP-GEF SGP funds will be subsumed into the Biodiversity Fund. The fund raising/resource mobilisation contract may, in part, be based on commission for successfully raised funds (at least this may apply to funds raised from certain sources of funding). |  |
| Secretariat for Biodiversity Fund |  |
| The Secretariat of the Biodiversity Fund will be comprised of a professional fund management team (envisaged to be a maximum of four people) that will be recruited following a Request for Proposals. The Secretariat shall provide technical and administrative support to the Steering Committee and will be responsible for the day-to-day operations of the fund. This will include the appraisal of project proposals (including guaranteeing relevancy and quality, and social and environmental screening), coordination, report consolidation, monitoring and evaluation – as described in the Fund’s Operational Manual. Following the first edition of the Operational Manual (see above), all future editions of the Operational Manual will be codified by the Secretariat for the approval by the Steering Committee. The Secretariat will also work with contractors on the Fund’s resource mobilization strategy and engages with contributing partners. The Secretariat will also provide technical advice, quality control and coordination of meetings. It ensures the monitoring of the implemented activities and operational risks and submits consolidated periodic results-based progress reports to the Steering Committee. Some of the functions of the Secretariat may be delegated and/or contracted to third parties – including aspects such as working with and mentoring low capacity groups or organisations, project/programme appraisal, and monitoring and evaluation (as this would result in an increased independence of such activities). |  |
| Investment Manager |  |
| An Investment Manager will be identified through a call for proposals. The investment manager will be an independent organization responsible to invest the fund assets; the Investment Manager will work under a contract with the Fund Administrator and will receive monies and transfer the returns on the fund at a mutually agreed cost. Together with the Fund Administrator, the Investment Manager will advise the Steering Committee on Fund design and investment portfolio (while following the underlying principles of the Fund), with the design of the fund being reviewed every four years. The review will include analysis and review of the Fund’s results framework and financial architecture relative to the degree to which it is capitalised. The design of the fund will take into account its level of capitalisation at the time of the review and decisions will be made regarding: i) the proportion of the sinking fund that will be invested fund, ii) how the interest from the sinking Fund will be managed, iii) how to manage the revenues that are being accrued within the protected area system within PNG, and iv) whether amendments to the investment portfolio should be made on the basis of the Fund’s principles (as described above). The result will be an Investment Strategy that will be forwarded to the Steering Committee for approval and adoption. The Investment Manager will, therefore, invest the funds according to the approved Investment Strategy. |  |
| Pilot sites |  |
| Under Output 3.2, the project will seek partners to implement the projects activities, with the aim of achieving the project’s outputs, outcomes and impacts, in three sites (initially). The selection will in most cases be a direct selection (because the partner organisation is working in the area and is the logical organisation to implement the project’s activities) but the partner will still remain accountable to the project. Once the partner(s) have been selected, they will be offered a contract (under a Responsible Party agreement); the contract will be linked to a grant and to the activities described in Output 3.2 under Section IV. |  |
| Sepik Wetlands (grant) |  |
| In the Sepik Wetlands, a partner organisation will be sought to work with SWMI; SWMI simply does not have the capacity to implement the project activities in the Sepik Wetlands and there are serious questions regarding their governance (in tandem with the CEPA representative in the area). It is possible that an organisation such as FORCERT or BRG may be persuaded to work with SWMI to improve governance and practices and work towards achieving the project’s objectives. |  |
| Mt Wilhelm Conservation Area (grant) |  |
| There are two organisations that will, ideally, work together to achieve the project’s objectives in the Mt Wilhelm area: these are the New Guinea Binatang Research Centre and the Wildlife Conservation Society. |  |
| Kimbe Bay (grant) |  |
| A consortium of organisations may partner with the project in Kimbe Bay; it is possible that FORCERT – with their base in Kimbe town – may take the lead on some of the work but this may be done with other partners such as TNC (that has a long history of working in Kimbe Bay) and JCU (that has a long history of carrying out research in Kimbe Bay). There may be roles for other organisations such as Mahonia na Dari – although the practical work of the project falls outside of the core business of Mahonia na Dari. |  |

## Annex D: Terms of Reference

- Project Board

The Project Board will ensure adequate guidance, oversight and integration of project activities. The PB is the body with ultimate responsibility for the efficient and effective implementation of the project.  As such, it will ensure that the project’s process of implementation and the achievement of its objective and outcomes are highly professional, streamlined, effective and efficient.  The PB will ensure that the project maintains the highest levels of transparency and accountability; and it will ensure cooperation and collaboration among project partners.  It will ensure that the project remains relevant to the national development objectives and strategies; to the UNDP policies and strategies; to the GEF’s focal areas; and in particular to the communities that own, use and hence - to a great extent - depend on the Protected Area lands and waters for their sustenance and survival.  The PB ensures that the processes that the project has put into place and the impacts that the project has are sustainable.  The PB will promote learning, feedback and knowledge sharing on the results and lessons learned from the project and its partners as a basis for decision-making on and, if necessary adaptation of, policies, strategies, programme management and projects, and to improve knowledge and performance

- The PB shall provide strategic advice to the Project Implementation Unit (PIU) for the implementation of project activities to ensure broader integration of the project activities within the national development goals of poverty reduction and sustainable development objectives

The PB will meet after the Inception Workshop (to approve the first year’s annual workplan and budget) and, thereafter, a minimum of two times a year.  With the assistance of the PIU, the chairperson of the PB will convene Project Board meetings. The Project Manager (PM) will participate in the PB and provide the Secretariat to the Board, with other PIU staff joining on demand and invitation.  The Project Manager will therefore be responsible for drafting the minutes, including agreed action points, of the PB meetings and circulating them within no more than one week following the PB meetings.  The minutes from the previous PB meeting will be approved at the start of the meeting that follows that meeting, with a check on the follow-up given to agreed action points.

The PB will be responsible for making, by consensus, project management decisions, when guidance is required by the Project Manager, including recommendations for UNDP/Implementing Partner approval of project plans and revisions, and addressing any project level grievances. In order to ensure UNDP’s ultimate accountability, Project Board decisions should be made in accordance with standards that shall ensure management for development results, best value for money, fairness, integrity, transparency, preventing harm to the invovled commuities, and effective international competition. In case a consensus cannot be reached within the Board, final decision shall rest with the Head of the Environment, Climate Change and Disaster Risk Management Portfolio in the UNDP-CO.

The Project Board will have the following main objectives, roles and responsibilities:

- To approve the project’s annual workplans and budgets (including fund allocations, budgets and projects, and the financial coordination mechanisms) – and these will be developed in synchrony and synergy with other programmes and projects, as well as with CEPA’s own budget and allocations related to the selected protected areas, to prevent funding overlap or substitution.

- To be responsible to examine the expenditure, ensuring efficient use of the project’s budget relative to the project lifetime.

- To represent national interests in the planning and development to ensure improvement of economic, environmental and social outcomes as a result of this project.

- To monitor project implementation in terms of effectiveness and timeliness of inputs and in terms of the success of project activities in the field.

- To provide strategic guidance and direction to the project, ensuring it remains within any specified constraints

- To provide strategic guidance and direction to the Project Implementation Unit.

- To oversee and provide policy guidance to project activities, ensure activities address the project objectives outcomes and outputs.

- To provide a forum for ensuring an integrated approach to project activities.

- To ensure coordination between the project and other ongoing activities in the country

- To perform advocacy role that promotes the role of Protected Areas as well as building support for protecting natural resources.

- To address project issues as raised by the project manager;

- To provide guidance on new project risks, and agree on possible mitigation or countermeasures and management actions to address specific risks;

- To agree on project manager’s tolerances as required;

- To review the project progress, and provide direction and recommendations to ensure that the agreed deliverables are produced satisfactorily according to plans or adapted and altered is deemed necessary;

- To appraise the annual project implementation report, including the quality assessment rating report; make recommendations for the workplan;

- To provide ad hoc direction and advice for exceptional situations when the project manager’s tolerances are exceeded;

- To assess and decide to proceed on project changes through appropriate revisions.

- To approve and sign the multiyear workplan, and the combined delivery report at the end of the year; and,

- To sign the financial report or the funding authorization and certificate of expenditures.

- Project Implementation Unit (PIU)

The PIU will be formed by the UNDP (including the recruitment of the PIU staff).  The UNDP – through the PIU – will be responsible for the implementation of this project, including achievement of its objective, outcomes and delivery of its outputs.  The UNDP’s responsibilities thus include the mobilization of all project inputs, recruitment and supervision of project staff, consultants and sub-contractors. Generally, the UNDP will be responsible for meeting government obligations under the project (under the NIM with UNDP Support Services modality). The PIU will perform a liaison role with the Government, UNDP and other UN Agencies, NGOs and project partners, and maintain close collaboration with other donor agencies providing co-financing.

Duties and Responsibilities

- Managing the implementation of all components and outputs of this project

- Monitoring and evaluation of project interventions

- Ensuring effective use of GEF resources

- Delivering the project objective, outcomes and outputs

- Ensuring demonstrable, effective and efficient achievement of the targets in the PRF (see Section VI)

- Prepare annual workplans and budgets for approval by the Project Board

- Prepare all project reports including the project’s Inception Report and the Project Implementation Reports (PIR) (see Section VII)

- Contracting consultants, partner organisations and/or contractual service companies that will be engaged to carry out the different aspects of the project, as necessary and as required.

- Sub-contracting other partners to implement different components or sub-components of the project

The functions of the PIU will end when the final project terminal evaluation report and corresponding management response, and other documentation required by the GEF and UNDP, has been completed and submitted to UNDP (including operational closure of the project).

- National Project Director

The National Project Director (NPD) is the Director of the Sustainable Environment Program; s/he will Chair the PB, responsible for ensuring that it meets at least twice a year (see section on Project Board, above).  S/he is expected to dedicate 15% of his/her time to the project and be in continual close communication and liaison with the Project Manager.  S/he will be accountable to the CEPA and UNDP for the achievement of project objectives and results. The time spent by the NPD on project business will be financed through national government funds (as project co-financing).

Duties and Responsibilities

- Serve as Chair and a member of the Project Board.

- Supervise compliance with objectives, activities, results, and all fundamental aspects of project execution as specified in the project document.

- Supervise compliance of project implementation with CEPA policies, procedures and ensure consistency with national plans and strategies.

- Facilitate coordination with other organizations and institutions that will conduct related conservation activities for the protected area system

- Participate in project evaluation, testing, and monitoring missions.

- Coordinate with national governmental representatives on legal and financial aspects of project activities.

- Coordinate and supervise government staff inputs to project implementation.

- Coordinate, oversee and report on government cofinancing inputs to project implementation.

- Project Manager (full time)

The Project Manager (PM), will be a nationally or internationally recruited expert selected based on an open competitive process managed by the UNDP. He/she will be responsible for the overall management of the project, including the mobilization of all project inputs, supervision over project staff, consultants and sub-contractors. The PM will report to the line manager in the UNDP in close consultation with the Director General of CEPA and the UNDP RR (or duly designated UNDP officer) for all of the project’s substantive and administrative issues. From the strategic point of view of the project, the PM will report on a periodic basis to the Project Board. Generally, the PM will be responsible for meeting government obligations under the project, under the project execution modality. He/she will perform a liaison role with the Government, UNDP and other UN Agencies, NGOs and project partners, and maintain close collaboration with other donor agencies providing co-financing. The Project Manager will also play a technical function in addition to the project management functions.

Duties and Responsibilities

- Manage the PIU

- The Project Manager will have a technical role in Component One – in terms of backstopping the institutional analysis and capacity building processes of all institutions and organisations involved in protected area management.

- Supervise and coordinate the production of project outputs, as per the project document, including ensuring technical quality and compatibility of the outputs with the objectives of the project;

- Mobilize all project inputs in accordance with UNDP procedures for nationally executed projects;

- Supervise and coordinate the work, including technical aspects, of all implementing partners, project staff, consultants and sub-contractors;

- Coordinate the recruitment and selection of project personnel and contractors as needed, especially with a view to the large infrastructure investments made by this project;

- Ensure that gender is mainstreamed into operational plans, as well as markers are reported on as part of regular reporting;

- Prepare and revise project work and financial plans, as required by the PB, CEPA and UNDP;

- Liaise with UNDP, CEPA, relevant government agencies, and all project partners, including donor organizations and NGOs for effective coordination of all project activities;

- Facilitate administrative backstopping and provide technical backstopping to subcontractors and activities supported by the Project;

- Oversee and ensure timely submission – and ensure adequate quality – of the Inception Report, Combined Project Implementation Review/Annual Project Report (PIR/APR), Technical reports, quarterly financial reports, and other reports as may be required by UNDP, GEF, EWCA and other oversight agencies;

- Disseminate project reports and respond to queries from concerned stakeholders;

- Report progress of project to the Project Board, and ensure the fulfilment of PB directives.

- Oversee the exchange and sharing of experiences and lessons learned with relevant actors nationally and internationally;

- Address key communication need and support the development and implementation of a project communication plan;

- Ensures the timely and effective implementation of all components of the project;

- Carry regular, announced and unannounced inspections of all sites and the activities of the project site management units.

Qualifications

- A post-graduate university degree (MSc/MPhil or PhD) in Natural Resources Management, Conservation or Protected Areas Management, related fields, Environmental Sciences, or related fields of expertise

- At least 10 years of experience in natural resource management;

- At least 10 years of project/program management experience;

- Working experiences with relevant ministries and national institutions is a plus, but not a requirement;

- Technical knowledge and experience with building institutions and capacity building among a broad range of stakeholders.

- Ability to effectively coordinate a large, multi-stakeholder project;

- Ability to administer budgets, train and work effectively with counterpart staff at all levels and with all groups involved in the project;

- Strong drafting, presentation and reporting skills;

- Strong computer skills, in particular mastery of all applications of the MS Office package and internet search;

- Strong knowledge about Papua New Guinea’s political and socio-economic context;

- Excellent writing communication skills in English, and good verbal Tok Pisin communication

- Chief Technical Officer (full time)

This is a specifically technical position – with specific reference to business planning, resource mobilisation, and financial planning, systems and capacity building.  The CTO will not substitute the Project Manager in terms of project management.  Indeed, the CTO will have the specific responsibility to develop the Business Plan (Output 1.2) – but in an inclusive, participatory and deliberative way with the involvement of stakeholders.  The CTO will work on capacity development of various partners regarding financial management and legal literacy (Output 1.3).  The CTO will also be involved in the resource mobilisation for the Biodiversity Fund, guiding the process of developing the Biodiversity Fund’s fund raising/resource mobilisation strategies (Output 2.3).  Finally, the CTO will be involved in the process to catalyse revenues in the selected pilot sites (Output 3.2).  In addition, the CTO will be involved other aspects of the project, as necessary.  Indeed, s/he will render technical support to the Project Manager and project staff, and both state and non-state actors. The CTO will coordinate the provision of the required technical inputs, reviewing and preparing Terms of Reference, and reviewing the outputs of consultants and other sub-contractors.

The CTO will be an outstanding and experienced national or international brought in at a P4 level.

Duties and Responsibilities

- Provide technical and strategic assistance for project activities, including planning;

- Develop the Business Plan (Output 1.2) in an inclusive, participatory and deliberative way with the involvement of stakeholders. S/he will be required to facilitate all meetings and workshops required for the development of the Business Plan, including deliberative consultations.  S/he will then be required to draft the Business Plan and finalise it for approval once it has been reviewed.  S/he will then coordinate the implementation of the Business Plan with the aim of achieving all of its goals and objectives.  Towards the end of the project, following the first five years of the Business Plan’s implementation, s/he will then review the Business Plan in an inclusive, participatory and deliberative way with the involvement of stakeholders and develop the second edition of the Business Plan before the end of the project.

- Provide support to the Project Manager, CEPA staff and other government counterparts in the areas of project management and planning, management of site activities, monitoring, and impact assessment;

- Ensure that the institutional assessment and analysis (Output 1.1) is done in an inclusive, participatory and deliberative way with the involvement of stakeholders – and that the emerging roles and responsibilities are appropriate for the nature of the protected areas of PNG.  In other words, CEPA should provide a supportive and facilitation role for protected areas, with specific legal support to counter all illegal encroachment into the areas.

- Work with all actors to build the capacity of the people, institutions and organisations involved  in protected area management – such that there is a demonstrative increase in capacity;

- Work with the other members of the project team to develop Terms of Reference for consultants and sub-contractors, and assist in the selection and recruitment process;

- Ensure the technical aspects of the work of all consultants and sub-contractors is of the highest standard;

- Assist the Project Manager in the preparation and revision of the Annual Work Plans and other documents and reports associated with the project;

- Work with the Project Manager on the preparation of the periodic Status Report when called for by the National Project Director;

- Assist the Project Manager in the preparation of the Combined Project Implementation Review/Annual Project Report (PIR/APR), inception report, technical reports, quarterly financial reports for submission to UNDP, the GEF, other donors and Government Departments, as required;

- Assist in mobilizing staff and consultants in the conduct of a mid-term project evaluation, and in undertaking revisions in the implementation program and strategy based on evaluation results;

- Assist the Project Manager in liaison work with project partners, donor organizations, NGOs and other groups to ensure effective coordination of project activities;

- Document lessons from project implementation and make recommendations to the Project Board for more effective implementation and coordination of project activities; and

- Perform other tasks as may be requested by the National Project Director, Project Manager, Project Board and other project partners.

Qualifications

- Tertiary university education (MSc or PhD) with expertise in the area of Environmental Economics, Business Planning associated to the environmental sector (and, if possible, protected areas in particular), or related fields of expertise;

- At least 12 years of professional experience

- International level experience would be an added bonus;

- Awareness of institutional change management would be desirable

- Strong skills in monitoring and evaluation and experience in implementing projects with both financial and environmental aspects;

- Previous experience with GEF projects in the region would be desirable

- Ability to work in and with a large, multidisciplinary team of experts and consultants;

- Be an effective negotiator with excellent oral and presentation skills;

- Excellent writing skills in English.

- Administrative, Procurement and Financial Officer (full-time – but could be a shared resource with other projects/programmes)

The Project Administrative, Procurement & Financial Officer (APFO) will be a national professional recruited by the UNDP on the basis of an open competitive process managed by the UNDP. S/he shall be responsible for the overall financial management and administration of the project, under the supervision of the PM.

In addition, the APFO will have a technical role with respect to the capacity development among partner organisations (under Output 1.3).  The APFO will also have a pivotal role in working with the contracted organisation that has the responsibility to develop the Business Plan.

Duties and Responsibilities:

- Assist the Project Manager in day-to-day management and oversight of project activities;

- Assist the PM in matters related to M&E and knowledge resources management;

- Assist in the preparation of progress reports;

- Ensure all project documentation (progress reports, consulting and other technical reports, minutes of meetings, etc.) are properly maintained in hard and electronic copies in an efficient and readily accessible filing system, for when required by PB, UNDP, project consultants and other PIU staff;

- Provide PIU-related administrative and logistical assistance.

- Keep records of project funds and expenditures, and ensure all project-related financial documentation are well maintained and readily available when required by the Project Manager;

- Review project expenditures and ensure that project funds are used in compliance with the Project Document and UNDP financial rules and procedures;

- Provide necessary financial information as and when required for project management decisions;

- Provide necessary financial information during project audit(s);

- Review annual budgets and project expenditure reports, and notify the Project Manager if there are any discrepancies or issues;

- Consolidate financial progress reports submitted by the responsible parties for implementation of project activities;

- Liaise and follow up with the responsible parties for implementation of project activities in matters related to project funds and financial progress reports.

- Facilitate auditing and financial controls with respect to the Project;

- Ensure that all procurements and disbursements are carried out in accordance with the UNDP/GEF and Government of Papua New Guinea’s requirements, which requires familiarity with the financial management procedures;

- Implementation of procurement related to the large infrastructure investments to be made under this project, in particular;

- Ensure that project-related disbursements are carried out in a timely and efficient manner;

- Ensure the smooth flow of funds to enable the timely implementation of project activities amongst the various implementation partners, including the timely replenishment of the project account;

- Compile the quarterly and annual financial reports in a timely manner, with a focus on the financial delivery of the project;

- Prepare a monthly project bank reconciliation;

- Maintain a logical and comprehensive record of financial transactions, with supporting documentation, for reference and audit purposes;

- Provide the necessary assistance and documentation for the statutory audit of annual financial statements;

- Perform all other duties as requested by the PM;

- Perform any other duty relevant to the assignment.

With respect to Procurement for the UNDP-GEF-supported Project

- Prepare and implement procurement strategies, plans and, where applicable, procedures, including sourcing strategies and e-procurement tools and procurement plans, based on the during the PPG phase developed infrastructure and procurement plans and guidance, and in line with existing procedures within the implementation partners.

- Ensure that all procurement activities under the UNDP-supported project are implemented in full compliance of procurement activities applicable.

- Elaboration and implementation of cost saving and cost reduction strategies.

- Implementation of a well-functioning strategic procurement processes, from sourcing strategy, tendering, supplier selection and evaluation, quality management, customer relationship management, to performance measurement.

- Implements and guidance to, contracts management and administration strategy within the project, constantly guided by legal framework of the organization and assessing/minimizing all forms of risks in procurement.

- Evaluate offers and make recommendations for the finalization of purchases and the award of contracts; analyse and evaluate commodity tender results;

- Managing reporting requirements to Project Management on delivery of procurement services.

Qualifications

- At least a Bachelor’s Degree in Business Administration;

- Knowledge of accounting policies and principles;

- At least five (5) years’ work experience in administration, of which at least one year was closely related to support of project / program activities;

- Capable of working fairly independently;

- Excellent organizational skills;

- Excellent inter-personal skills and the ability to establish and maintain effective working relations with people;

- Excellent communication skills (oral and written); in English

- Good computer skills and proficiency in standard computer applications (MS Word, MS Excel, etc.).

- Social and Environmental Safeguards Officer (full-time – but could be a shared resource with other projects/programmes)

Under the overall supervision and guidance of the Project Manager, the Project Social and Environmental Safeguards Officer (SESO) will have the responsibility for the implementation of the risk management plan(s), Gender Action Plan and Stakeholder Participation Plan. This will be a primarily technical role, with roles in the following: i) ensuring gender and power issues are taken into account during the capacity development processes under Output 1.3; ii) ensuring that gender and power issues are built into the Biodiversity Fund’s governance and management structures, and into the Fund’s governance, strategic and operational documents, and, most importantly, iii) ensuring that the implemented activities in the pilot sites and trial processes across protected areas in the country at the very least cause no harm and at best have a positive impact on all members and structures of the different societies with whom the project and Biodiversity Fund is working, in line with the project’s social and environmental risk management plan(s).

The SESO will work closely with the PM and FAA on related aspects of project implementation, reporting, monitoring, evaluation and communication. Specific responsibilities will include:

- Develop a project communications strategy / plan, incorporate it with the annual work plans and update it annually in consultation with project stakeholders; coordinate its implementation

- Coordinate the implementation of knowledge management outputs of the project;

- Coordinate and oversee the implementation of public awareness activities across all project components;

- Contribute to the design and maintenance of the project website/webpages and ensure it is up-to-date and dynamic;

- Facilitate learning and sharing of knowledge and experiences relevant to the project;

- Monitor progress in implementation of the project Gender Action Plan ensuring that targets are fully met and the reporting requirements are fulfilled;

- Oversee/develop/coordinate implementation of all gender-related work;

- Review the stakeholder participation plan and Gender Action Plan annually, and update and revise as necessary;

- Ensure reporting, monitoring and evaluation fully address the gender issues of the project;

- Monitor progress in development/implementation of the project risk management plan(s) (e.g. ESMP/ESMF), ensuring that UNDPs SES policy is fully met and the reporting requirements are fulfilled;

- Oversee/develop/coordinate implementation of all safeguard related plans, including the project-level Grievance Redress Mechanism;

- Ensure social and environmental grievances are managed effectively and transparently;

- Review the SESP annually, and update and revise corresponding risk log; mitigation/management plans as necessary;

- Ensure full disclosure with concerned stakeholders;

- Ensure environmental and social risks are identified, avoided, mitigated and managed throughout project implementation;

The SESO will be recruited based on the following qualifications:

- Bachelor’s degree in gender studies, gender and development, environment, sustainable development or closely related area.

- Demonstrated understanding of issues related to gender and sustainable development; at least 5 years of practical working experience in gender mainstreaming, women’s empowerment and sustainable development in relevant Country/Region/Area of Work;

- Proven experience in gender issues in Country/Region/Area of Work

- Previous experience with UN projects will be a definite asset;

- Demonstrated understanding of the links between sustainable development, social and gender issues;

- Experience in gender responsive capacity building;

- Experience with project development and results-based management methodologies is highly desired/required;

- Excellent analytical, writing, advocacy, presentation, and communications skills.

- Excellent language skills in English (writing, speaking and reading) and in local languages.

- Very good inter-personal skills

## Annex E: List of Protected Areas in PNG

[Note: proposed protected areas appear in italics]

| PA Name | Province | Size (ha) | Land-ownership | Management | Partners |
| --- | --- | --- | --- | --- | --- |
| Varirata National Park | Central | 1,068 | State and customary | CEPA | CEPA, JICA, GEF-5 |
| Headwaters of the Strickland | Hela | >200,000 | Customary | Community | Barrick/Porgera Joint Venture |
| Kaijende Highlands | Enga | 120,000 | Customary | Community | Barrick/Porgera Joint Venture |
| Bagiai WMA | Madang | 13,760.00 | Customary | Community |  |
| Baiyer River Sanctuary | Western Highlands | 741.00 | State | Nominally CEPA | Provincial and Local Government and the local Member for Parliament |
| Balek Wildlife Sanctuary | Madang | 470.00 | State | Nominally CEPA | Madang Provincial Government and the Tourism Bureau of Madang Province |
| Baniara Island | Milne Bay | 200.00 | Customary | Customary |  |
| Cape Wom Memorial Park | East Sepik | 165.42 | State and customary | Provincial Government | Provincial Government |
| Crown Island Wildlife Sanctuary | Madang | 58969 | Customary | Nominally CEPA |  |
| Crater Mountain WMA | Eastern-Madang- Simbu-Gulf | 270000 | Customary | Customary | Research Conservation Foundation |
| Garu WMA | West New Britain | 8,700.00 | Customary | Customary | UNDP/GEF-4 |
| Hombareta WMA | Oro | 130.00 | Customary | Customary | Oro provincial government |
| Horse Shoe Reef | Central | 395.90 | Customary | Customary | JICA |
| Hunstein Range WMA | East Sepik | 220000 | Customary | Customary | WWF |
| Iomare WMA | Central | 3,827.00 | Customary | Customary |  |
| Jimi (Ruti) Valley National Park | Western Highlands | 4,180.00 | State | Nominally CEPA | Provincial Government |
| Kamiali WMA | Morobe | 47,413.00 | Customary | Customary |  |
| Kavakuna Caves WMA | East New Britain | ~ <300 | Customary | Customary | UNDP/GEF-4 |
| Klampun WMA | East New Britain | 5,200.00 | Customary | Customary | UNDP/GEF-4 |
| Kokoda Memorial Park | Central | - | State | National Museum/ customary | Kokoda initiative |
| Kokoda Historic (Track) Reserve | Oro-Central | - | Customary | National Museum/ Customary | Kokoda iniative |
| Lake Lavu WMA | Milne Bay | 2,640.00 | Customary | Customary |  |
| Lake Kutubu WMA | Southern Highlands | 4,924.00 | Customary | Customary | WWF, Exxon Mobil, Chevron Nugini |
| Laugum Marine WMA | Madang | 72.95 | Customary | Customary | WWF and Madang provincial government |
| Libano-Arisai WMA | Southern Highlands | 3,964.00 | Customary | Customary | WWF and CDI |
| Libano-Hose WMA | Sothern Highlands | 7,736.00 | Customary | Customary | WWF and CDI |
| Lihir Island | New Ireland | 1,980.00 | Customary | Provincial Government | Provincial government and Lihir gold mine |
| Loroko National Park | West New Britain | 100.00 | State | Nominally CEPA |  |
| Managalas CA | Oro | 360,000 | Customary | Customary | Partnership with Melanesians |
| Maza WMA | Western | 184230 | Customary | Customary |  |
| Mc Adams National Park | Morobe | 1,821.00 | State | Nominally CEPA |  |
| Moitaka Wildlife Sanctuary | National Capital District | 42.00 | State | Nominally CEPA | Moitaka is not functioning and serving its purpose |
| Mojirau WMA | East Sepik | 5,079.00 | Customary | Customary |  |
| Mt Gahavisuka Provincial Park | Eastern Highlands | 77.40 | State | Provincial Government | Provincial government |
| Mt Kaindi WMA | Morobe | 1,502.00 | Customary | Customary |  |
| Mt Susu Natural Reserve | Morobe | 260.00 | Customary and state | Nominally CEPA |  |
| Mt Wilhelm National Park | Simbu | 817.00 | State | Nominally CEPA | Investment promotion authority, Provincial Government |
| Namanatabu Reserves | Central | 29.00 | State | Nominally CEPA |  |
| Nanuk Island District Park | East New Britain | 12.00 | State | District Administration |  |
| Ndrolowa WMA | Manus | 5,850.00 | Customary | Customary |  |
| Neiru (Aird Hills) WMA | Gulf | 3.98 | Customary | Customary |  |
| Nusareng WMA | Morobe | 22.23 | Customary | Customary |  |
| Oi Mada Waa WMA | Milne Bay | 22840 | Customary | Customary |  |
| Paga Hill Scenic Reserve | National Capital District | 13.12 | State | Nominally CEPA | The Scenic Reserve has been destroyed through development |
| Pirung Eight Islands WMA | North Solomons | 43200 | Customary | Customary |  |
| Pokili WMA | West New Britain | 9,840.00 | Customary | Customary | UNDP, provincial government |
| Ranba WMA | Madang | 41922 | Customary | Customary |  |
| Ranba Wildlife Sanctuary | Madang | 15,724.00 | State | Nominally CEPA |  |
| Sawataitai WMA | Milne Bay | 700.00 | Customary | Customary |  |
| Tab Island WMA | Madang | 984 | Customary | Customary | WWF and Madang provincial government |
| Sulamesi WMA | Southern Highlands | 70 159 | Customary | Customary | WWF and CDI |
| Tabad WMA | Madang | 16.20 | Customary | Customary | WWF UNDP(GEF) |
| Sinub Island Marine WMA | Madang | 11.80 | Customary | Customary | WWF UNDP (GEF) |
| Talele Island Natural Reserve | East New Britain Province | 12 | State | Nominally CEPA |  |
| Siwi Utame WMA | Southern Highlands | 12540 | Customary | Customary |  |
| Tavalo WMA | East New Britain Pro | 1155 | Customary | Customary |  |
| Wewak Memorial Park | Wewak | 1.9 | State | Provincial Government |  |
| Zo-oimaga WMA | NCD | 1510. | Customary | Customary |  |
| Yus CA | Morobe | 75000 | Customary | Customary | CEPA, UNDP, US based NGO |
| Tonda | Western Province | 590000 | Customary | Customary |  |

# Annex F: List of people consulted over the course of the PPG process

Attendees of PPG Inception and Consultative Workshop, most of whom were consulted on a one-to-one basis during the first mission to PNG (see Table below)

| Name | Position | Organisation |
| --- | --- | --- |
| Peniamina Leavai | Senior Policy & Finance Advisor | USAID Contractor - Climate Ready Project |
| Warren Jano |  | CEPA/UNDP |
| Rose Raka Koyama | Acting Deputy Secretary (Policy) | DNPM |
| Noel Gisawo | Project Officer - Inaina WMA | Partners with Melanesians Inc. |
| Thomas Waika | Project Assistant | UNDP |
| Ms. Kay Kalim | Director - Sustainable Environment Programs | CEPA |
| Gwen Maru | Programme Officer - Environment & Energy | UNDP |
| Mark Nizette | Kokoda Initiative Advisor | CEPA |
| Peter Bosip | Executive Director | CELCOR Inc |
| Haro Setae | Acting Director - Community Benefit Fund | NGCB |
| Andy Hetra | Coordinator - EIS & Permitting | TOTAL Exp PNG Limited |
| Lovelyn Ungere | Snr Project Officer - Agriculture & Natural Resources | CIMC |
| Peter Dam | Technical Advisor | FORCERT |
| Steven Magil | National Coordinator | Papua New Guinea Forest Certification Incorporated |
| Lester Seri | Environmentalist | Self-Employed |
| Alois Jewkihau | Policy Officer | PNG FA |
| John Songi | Project Officer | Partners with Melanesians Inc. |
| Melinda Waipo | GEF 5 Officer | UNDP |
| James Sabi | Manager - Terrestrial Eco-systems | CEPA |
| Evengelyn Kove | Rainforest Literacy Coordinator | PWM |
| Jim Thomas | CEO | Tenkile Conservation Alliance |
| Yasap Popoitai | GEF 4 Team | CEPA/UNDP |
| Benny B.Popoitai |  | BPNG |
| Rufus Mahuru | Program Manager | PWM Inc |
| Paul Lokani | Executive Director | PNG Mama Graun Conservation Trust Fund |
| Dr Francesca Dem | Research Supervisor/Deputy Director | New Guinea Binatang Research Centre |
| Zola Sangga | National Country Coordinator | Critical Ecosystem Partnership Fund/IUCN |
| Saina Jeffery Philyara | Kikori Project Officer | WWF |
| Tashi Dorji | Regional Technical Specialist | UNDP - Bangkok Regional Hub |
| Carolyn Kumul |  | CEPA/UNDP |
| Charlie Ross | Environment Manager | Barrick (Niugini) Limited |
| Laura Ann Dresser | Environment Regulatory Supervisor | Exxon Mobil PNG |
| Dr. Jane Mogina | Biodiversity Lead | Exxon Mobil PNG |
| Jerry Farehu | Snr Environment Advisor | Exxon Mobil PNG |
| Jacinta Mimigari | Project Officer - Collingwood Bay Project | PWM |
| Anthony K. Yauieb | Director | Alle PNG Ltd |
| Raymon Joshua | Project Coordinator | OISCA - ARM |
| Maxine Anjiga | Executive Director | PNG Centre for Locally Managed Areas Inc |
| Modi Pontio | Observer |  |

People met and consulted on a one-to-one basis during the first mission to PNG

| Date | Person consulted | Affiliation |
| --- | --- | --- |
| Tuesday 16 May 2017 | Kay Kalim, Head SEP James Sabi, Terrestrial systems Michael Bongro | CEPA |
| Wednesday 17 May | Paul Lokani | Mama Graun Trust Fund |
|  | Rebecca Asigau | CELCOR |
|  | Rufus Mahuru & Team (9 people) | Partners with Melanesia (PWM) |
|  | Dr Ambrose Bernier Dr Nathan Whitmore | WCS-PNG |
| Friday 19 May | Paul Barker | Internal National Affairs |
|  | Mark Nizette, Advisor | Kokoda Initiative |
|  | Lester Seri | Collingwood Bay Landowner |
| Monday 22 May | Charlie Ross, Environment Manager | Barrick Gold - A presentation on 2 proposed conservation areas – Kaijende Highlands and Strickland Headwaters – and the support provided to these areas by Barrick |
|  | Zola Sangga | Critical Ecosystem Partnership Fund (CEPF) |
| Tuesday 23 May | Hideki Imai Team from JICA (2 people) and representatives from CEPA | CEPA-JICA |
|  | Peniamina Leavai Harry Gubala | USAID – Climate Ready Project & CCDA |
|  | Mr Benny Popoitai | Bank of PNG Financial Analysis & Supervision Unit (FASU) – PNG’s Financial Intelligence Unit |
|  | Phil Shearman | UPNG Remote Sensing Centre, University of Papua New Guinea |
| Wednesday 24 May | Anthony Yauieb | Consultant & former Deputy Secretary of Dept of Treasury involved in the Sovereign Wealth Fund |
|  | Kay Kalim, Head SEP James Sabi, Terrestrial systems Michael Bongro | CEPA debrief |
|  | Lawrence Stephens | Melanesian Trustee Services Ltd/Pacific Balanced Fund; TIPNG |
|  | Maxine Anjiga | PNG Centre for Locally Managed Areas Inc (PNGCLMA) |
| Thursday 25 May | Dennis Vidmar Laura Dresser Dr Jane Mogina Jerry Fareho | PNGLNG Operators - ExxonMobil PNG |
|  | Juliana Kubak | Former A/Sec Dept of National Planning & Monitoring (insight to govt budget planning mechanisms for co-financing) |
|  | Brian Brunton | AEL & PA Bill advisor |

People met and consulted during the second mission to PNG

| Date | Name | Affiliation | Place |
| --- | --- | --- | --- |
| 28 Aug 2017 | Priscilla Hokoi | PNG FA (ESP Administration) | Wewak |
| 28 Aug 2017 | Richard Kali | Provincial Forest Officer | Wewak |
| 29 Aug 2017 | Florence Parinjo | President, Wewak District Council of Women | Wewak |
| 29 Aug 2017 | Christine Ati | Wewak District Council of Women, Yawasoro | Wewak |
| 30 Aug 2017 | Moses Wamsari | Wagu Village, Hunstein Range WMA Chairman | Ambunti |
|  | Donald Wanshu | Biaka Village, youth representative |  |
|  | Stella Komap | Wasku Village, Women Rep |  |
|  | Paul Komap | Ward member, Ward 19 |  |
|  | Joseph Kolhuni | Ward member, Ward 18 |  |
|  | Schola Joseph | Ward 18 Women Rep |  |
|  | Hennik Anskar | President, Ambunti District Council of Women |  |
|  | Meggy Amasai | Member, Ambunti District Council of Women |  |
|  | Hilda Waipeli Linda Nawi Jonathan Gowep Basari Jeremiah Wana Jerry Wana Benny Gowep | SWMI staff |  |
|  | Albert Nawi | Ward 1 Member |  |
|  | Simon Kula Issca Begawi Mathew Yafei (chairman) | Wagu Village – Hunstein (Behinomo) WMA Committee – Yigai, Wagu and Gahom villages are part of the WMA |  |
| 31 Aug | Caleb the old man Jenny La Kenny Julie Wamnai Evelyn Wafai Rosa Kenny Christina Sadi | Wagu Villagers at meeting | Wagu Village Along the Hunstein River |
| 31 Aug | Sakias Biko Joshua Nasio James Riso Alex Gudara Timothy Boren Kevin Yam Lukas Mason Mark Nabi Robert Boren Kenny Sanabi Samuel Morien Luke Yam Peter Nasio Glenda Yam Selina Alex Norin Charles Robina Biko Elsi Luke Veronica Martin Glenes Joshua Peter Max Joshua Nick Morien Aneth Philip Priscilla Yam Magreth Andrew Jona Wakmok Steven Gudara Genesis Gudara Jack Wakwau Philip Mason Esther Jack Ambros Joshua Gloria Job | Swagap Village | Swagap Village along the Sepik River |
| 01 - 02 Sept | Albert Nawi Jerry Wana Benny Gowep Hennick Anskar Maggie Amosoi Mrs Albert Nawi Alois Mataos | Councillor, Ambunti Urban Ward 1 SWMI SWMI Women activist Women activist Community member Sepik Croc Festival initiator – Chairman of the Wewak Chamber of Commerce & Chairman of the Tourism Industry Association | Ambunti & Wewak |
|  | Raymond Wungen | District Administrator, CEO: Angoram District Administration | Ambunti |
|  | Hon. Salio Waipo | MP, Angoram | Wewak |
| 02 Sept | Alan Bird Chris Bais | Governor – ESP EO to ESP Governor | Wewak |
| 3 Sept | Vojtech Novotny Francesca Dam & Team (10 people) | Director Deputy Director BRC | Nagada Bay – BRC HQ |
| 4 Sept | Frank Sopla | Forester, Madang Provincial Admin | Madang |
|  | Kafuri Yaro Rebecca Samuel | PNG Program Manager, WWF-PNG Coastal Marine Project Officer, WWF | Madang |
|  | Lilo Massing | Horizon T3000 – Austrian Organisation for Development Coorperation | Madang |
| 5 Sept | Philip Damen Saldon Yabi Mulapa Samson Marava Saldon Pithiea Jorry Anna Mokoi Philip Kamal Philip Waim Daniel Timothy Philip Ananias Kamam John Timothy Timon Niton Lanson Kamam Amos Airam Stanley Philip Japi Rope Cathy Waim Estha Jorry Clarah Philip Arron Sam Grace Jorry Miss Sivi Andrew Sapma Jonah Philip Aisaik Saldon Eunice Jonah Dolis Samuel Ana Jolly Pitias Sazu Joyce Philip Hilda Christopa Pain Ray Saulas Hukem | Wanang Leader | Wanang village 5 villages: Wanang, Kungi, Well, Palimun & Munge |
| 6th Sept | Joanne Arek & Team Imason Bekue Oniel Beibi Alice Stanley Relson Heni Dembis | Madang Culture & Tourism Bureau Manager | Madang |
|  | Taddy Sabai Hirin Dau Joe Kasa Francis Wadui Francis Sanna Kondrad Dong Lilly Dong Chris Mol Benny Wadui John Duadak Wolfy Duadak Frankey Duadak Francisca Duadak Adolf Sakau Levi Kubulau Maksil Mot Adolf Loman Wendy Bau Clarista Sinub Simon Deb (Sek) | Tabad WMA Siaman Tabad Tabad –Councillor Sinub WMA Sinub WMA Comm. Sinub WMA Sinub WMA Women Sinub WMA Sinub WMA Laugum WMA Laugum Laugum Laugum women Laugum WMA Malmal Malmal Malmal Laugum Laugum Kananani C/leader | Riwo village |
| 7th Sept | Daniel Aloi | Provincial Administrator, Madang Province GM, Madang Resort | Madang |
|  | David Thomas Tamloneg Tabb Rodney Tabb Paul Zabe Francis Morris Victor Tabb Gokly Kalim Oscar Tabb Mereg Willy | Tabb Chairman Vice Secretary Treasurer Komiti Komiti Komiti Komiti | Tab WMA Community 2 clans – 200-300 pp (Waifur/Mizim) |
| 8th Sept | Peter Miller | Programme Manager, MND | Kimbe |
| 9th Sept | Michael Huri Gabriel Bakani Josepha Bakani Miriam Giru | Chairman Secretary of LMMA Community member Kobongane LMMA (Kilu village) | Kulungit LMMA |
| 10 Sept | John Lagea Turia Beno Beno Macko Robin Saeke Herman Saeg Gervasius Gabu William Saeke George G Demas Saeke Joe Lobao Robert Kailoa Regina Luke Josephine Nono Brigit Nono Philip Taupili | Isunawa LMMA farmer Chairman farmer farmer Vice Chairman Farmer Lolobau Leader | Bialla – Baea Isunawa LMMA Lolobau LMMA |
| 11 Sept | Kaiwa Joe Jacob Sade Kaukia Peter Albert Saeke Angus Tokaien Peter ad Freddy Vili Maria Lagea Alois Koki Vincent Lagea William Malisa Clement Laia John Saeke Teddy Male Peter Gavuli Alois Kouki Valtrude Tokolo Francisca Gavuli Gethrude Lobao Gethrude Uba Mathilda Appa Vulolo Georgina Gisela Vulolo Albetha Namo Benedictha B Francisca Bitai Maria Vule |  | Baea proposed LMMA |
|  | Ron Tavalakol Helen Toirima Ps Michael Zanere Boas Matitiliu Mary Ekonia Tutu Waria Jacob Gavuli Patrick Teiga | Vice Pres ENLLG Ewasse LMMA Ewasse Chairman Bubu included Lands ENLLG Admin ENLLG Village Court Insp, ENLLG Tavur Lodge Tavur Lodge | East Nakanai LLG Office Tavur Lodge Kimbe |
| 12 Sept | Mr. V. Kapae & spouse Mathias' Son A young man John Herebubu Papa Hulabaka Theo Gorivo A young woman Another young man |  | Papavulabaka & Makasili LMMA communities |
|  | William Hosea | Provincial Administrator, WNB | Kimbe |
|  | Riccard Reimann | Owner, Liamo Resort, Kimbe; Baia Fishing Lodge | Kimbe |
| 13 Sept | Eric Langelet | Mainland Holdings – Crocodile | Lae |
|  | Lisa Dabek Mikal Nolan Joel Glick | YUS Conservation Area | Lae |
| 14 Sept – 15 Sept | Cecelie Benjamin Max Benjamin Chyne Benjamin Liz Cotterell Peter Miller | Walindi Plantation Resort Walindi Dive Centre Mahonia na Dari | Kimbe |
|  | Cosmas Makamet | FORCERT | Kimbe |
| 18 Sept | David Peter | SWMI POM | Port Moresby |
|  | Kirsty Laird (Partner), Navancca Eyres (Manager) Julian Eko (Supervisor) | Deloittes Tomatsu |  |
|  | Tracy Viennings & Emily Fajardo | UNDP-CO |  |
| 19 Sept | Cornelius Soagal Charlotte Moore | OSL Biodiversity management Lead | PoM |
|  | Ruth George Nelson, Earom Iru, Martin Teine, Martin Kondo, Stephanie Huasi | Dept of Treasury |  |
|  | Zola Sangga | CEPF |  |
|  | Charlie Ross & Dr Bill Thomas | Barrick Gold – PJV Forest Stewards |  |
| 20 Sept | Gwen Sissiou Mirzohaydar Isoev Peter Katapa Sam Moko | CCDA/UNDP REDD+ | PoM |
|  | Dennis Vidmar Dr Jane Mogina Jerry Fareho | ExxonMobil PNG |  |
|  | Brian Brunton | AEL |  |
| 21 Sept | Maxine Anjiga | PNGCLMA | PoM |
|  | Robert Schlenther | German Honorary Consulate to PNG |  |
|  | Musje Werror | OTML Deputy CEO |  |
|  | Anthony Yauieb | Treasury Advisor |  |
| 22 Sept | Douveri Henao | Digicel Foundation Chairman & EO for PNG/Aust Business Council | PoM |
|  | Dilu Mugawa Michael Bongro | CEPA DMD & PIU Director |  |
|  | Jane Mogina | EMPNG Biodiversity |  |
|  | Tracy Viennings | UNDP CO |  |
|  | Brian Brunton | AEL & PA Bill advisor |  |

LIST OF PARTICIPANTS - SUSTAINABLE FINANCING OF PROTECTED AREAS OF PNG PROJECT VALIDATION WORKSHOP 29 NOV 2017

| Names | Designation | Organisation |
| --- | --- | --- |
| Warren Jano |  | CEPA/UNDP |
| Thomas Waika | Project Assistant | UNDP |
| Ms. Kay Kalim | Director - Sustainable Environment Programs | CEPA |
| Gwen Maru | Programme Officer - Environment & Energy | UNDP |
| Lovelyn Ungere | Snr Project Officer - Agriculture & Natural Resources | CIMC |
| James Sabi | Manager - Terrestrial Eco-systems | CEPA |
| Jim Thomas | CEO | Tenkile Conservation Alliance |
| Jean Thomas | COO | TCA |
| Yasap Popoitai | GEF 4 Team | CEPA/UNDP |
| Zola Sangga | National Country Coordinator | Critical Ecosystem Partnership Fund/IUCN |
| Jerry Fareho | Snr Environment Advisor | Exxon Mobil PNG |
| Titus Tsigese | Environment Officer | PNG Power |
| Ambrose Brenier PhD | Country Director | WCS |
| Elizabeth Cotterell | Dive Manager | Walindi Plantation Resort |
| Mary Theresa Boni | Snr Program Officer | INA |
| Marjorie Warisaiho | Community Legal Education Coordinator | CELCOR |
| Dr Francesca Dem | Research Supervisor/Deputy Director | New Guinea Binatang Research Centre |
| Salape Tulai | Research Technician | New Guinea Binatang Research Centre |
| Alfred Mani | Research Technician | New Guinea Binatang Research Centre |
| Navannca Eyres | Manager – Consulting Services | Deloitte Touche Tohmatsu PNG |
| Brian Brunton | Legal Consultant | Alotau Environment Ltd |
| Jerry Wana | Manager | Sepik Wetlands Management Initiative (SWMI) |
| Betty Wong |  | SWMI PoM |
| Mr Somei Jonda | MND resident Marine Biologist & Education officer | Mahonia Na Dari |
| Desmond Vaghelo | Environment & Forest Officer | West New Britain Provincial Admin |
| Mirzohaydar Isoev | CTA, FCPF REDD+ Readiness Project | UNDP |
| Ruth George Nelson | A/AS-Risk & Strategic Management | Dept of Treasury |
| Jessie Pile | Manager, Environment | OTML |
| James Sabi | Manager, TEM | CEPA –SEP Division |
| David Peter | PNG Ports | SWMI |
| Emily Fajardo | GEF 4 CbFCCRM Program Analyst | UNDP –GEF |

Other people consulted during the third mission to PNG

| Person | Affiliation |
| --- | --- |
| Brian Brunton | AEL & PA Bill advisor |
| Natalie Moxham | Leanganook Yarn |
| Guy Dutson Robin Mitchell | The Biodiversity Consultancy (hired to develop offset policy for PNG) |
| Allen Allison, PhD | Bishop Museum (consultant for GEF-4 and GEF-5 projects) |
| Jim Thomas | Director, Tenkile Conservation Alliance |

## Annex G: Process of selecting pilot sites.

Criteria for Selecting Pilot Sites

Following a series of consultations with the Conservation and Environmental Protection Authority (CEPA), the following criteria were applied for the selection of the pilot sites.  There was a single, overriding criterion (or principle) that is necessary for all pilot sites:

Each of the pilot sites requires some investment that will catalyse a site-based system that generates income for the protected area.

The site-based income (or revenue) generating system could include one (or more) of the following revenue generating mechanisms (with examples of how this might function):

- Payment for Ecosystem Services (PES) – this could be linked to companies such as Power PNG Ltd or Eda Ramu paying for the protection of the watershed that provides water (either for hydroelectric systems or for water supply systems)

- REDD + (and other carbon finance mechanisms) – it should be noted that this is primarily a mechanism for mitigating climate change through reducing net emissions of greenhouse gases although in principle REDD+ also allows for conservation of carbon stocks.

- Tourism – in which fees, taxes and agreements lead to the generation of revenue

- Site-based offsetting – in which residual adverse biodiversity impacts are compensated through measurable conservation outcomes (including the establishment and management of protected areas)

- Management agreements or concessions – in which the management (and responsibility for financing) of a given protected area is transferred often to a private sector organization.

- Specific site-level tax rebates – tax rebates may be granted to private sector organisations for provision of financing to a protected area.

Aside from this one fundamental criterion, the selection of pilot sites should include the following essential criteria:

- The area(s) are key biodiversity areas - this could be coupled with areas with significant ecosystem services or ecological processes.

- The investment necessary to catalyse the site-based system for generating income is readily identified and calculated

- The protected area is either already established or is close to being established – thereby preventing the need for significant time investments to secure, for example, Free Prior Informed Consent (FPIC) with associated letters of consent from landowners and land users.

- There is scope for carrying out work to enhance the well-being and livelihoods of people living within and/or surrounding the protected area.

Finally, the selection of pilot sites should include the following desirable criteria:

- The areas are relatively accessible – thus, the costs of working in the area are less prohibitive

- If the sites are to be gazetted over the lifetime of the project (noting first the third bullet of the essential criteria), they should contribute to the overall coverage of the protected area system.

Brief from CEPA on site selection (see following pages)

## Annex H: A proposal to develop a “METT for PNG”

PNG’s protected areas are relatively unique - related primarily to the customary ownership of land within the country that, in turn, means that the majority of protected areas are owned by communities.  This means that protected area management and evaluation mechanisms and methodologies that are applicable elsewhere in the world are either less applicable in PNG or, in some cases, not only inapplicable but wholly inappropriate.  This is the case with the METT that is usually used for GEF protected areas projects (hereafter the “original METT”).

The original METT was designed for protected area systems in which the state owned the greater majority - if not all - protected areas (as is the case in the majority of the rest of the world) and those protected areas were often IUCN Cat II PAs.  When such tools are applied in community-owned and managed protected areas there may be a number of negative results and impacts – and the use of the original METT has already been demonstrated to be not only ineffective but also damaging within the context of community-owned protected areas in PNG.  For example, the language used in the tool can lead to creating expectations; if the expectations are not fulfilled, people become disgruntled and, in the context of PNG, in which there is a choice (with the extractive industries or industrial agriculture), people may embrace those alternatives.  This has, apparently, already happened once in PNG - as a direct result of application of the original METT.

The original METT not only is inapplicable because of the language it uses and the expectations that it creates but there are a number of fundamental aspects of protected area management that are either inadequately included or they are not included whatsoever.  A good example of this is the measurement and monitoring of governance (and elsewhere, for example, the International Institute for Environment and Development (IIED) is currently developing a specific tool for monitoring governance among community-owned and management protected areas in northern Kenya).  And yet, despite its importance) especially within the context of community-owned protected areas), good governance is inadequately included in the original METT.  Other key elements of community-owned and managed protected area management include (but are not limited to) governance, enterprise, security, socio-economic development, access to services, gender; these are all of which are critical to the success of community-owned protected areas.

In recognition of its inapplicability to community-owned protected areas across most places elsewhere in the world, the original METT is simply not used as the tool for monitoring management effectiveness.

Concerns regarding the use of the METT (hereafter termed as the “original METT”) in PNG have been raised on a number of occasions but most recently as part of the UNDP-GEF-4 project.  As a result of this, within the GEF-4 project, the METT was amended to adapt it to PNG’s unique circumstances (hereafter termed as the “amended METT”) – while attempting to stay true to the “original” METT; this was, in turn, based on the fieldwork carried out by a team from SPREP to assess the management effectiveness of the protected areas of the country and resulted in the following report:

Fiona Leverington, Ann Peterson, Gregory Peterson, 2017, Methodology for assessment of protected area management effectiveness in Papua New Guinea’s Protected Areas, SPREP, Apia, Samoa

This was an extremely useful and valuable process – and brings with it many lessons.  However, there is a need to build on the foundations laid by Leverington et al. (2017) and develop a tool that is wholly appropriate and meaningful for monitoring the management effectiveness of community-owned protected areas in PNG, ensuring that it measures all the aspects that are critically important to their success.  Such a tool would, thereafter, be relevant for all community-owned protected areas supported by the GEF-6 project and the Biodiversity Fund.  Indeed, it would be the tool for the monitoring of management effectiveness of community-owned protected areas in PNG ad infinitum.  This proposal, therefore, is for a participatory process that would include the engagement and inclusion of a small number of key stakeholders (a METT Working Group) to develop such a tool and securing the endorsement of a broad range of stakeholders for the resulting tool.  The process would involve five steps:

  - A desk review of the different models that exist across the globe for monitoring the management effectiveness of community-owned and managed protected areas.  The work will determine all the aspects of protected area management (including governance, enterprise, security, socio-economic development, access to services, gender inclusion) that need to be assessed within the context of PNG and develop a draft proposal for a METT for PNG - with options for each of the different aspects.

  - A meeting of the METT Working Group to develop a proposed METT for PNG.  This would be a facilitated process that would examine the proposed tool and require agreement on: i) the different aspects/components that should be incorporated into a METT for PNG; ii) the best language to use to elicit information from the stakeholders/community-owners (i.e., ensuring that expectations would not be created or built through the process), and iii) the best and most cost-effective mechanism for applying the METT for PNG.

  - Finalising the proposed METT for PNG on the basis of the above two steps and holding a broad stakeholder workshop to validate the final METT for PNG.

  - Testing the application of the METT for PNG in the protected areas targeted through the GEF project that are currently underway in PNG and through partner organisations in the country.

  - Reviewing the METT for PNG following its initial application across the protected areas in the country and adjusting it, as necessary.

The final tool would be applicable in the context of PNG – including as the key mechanism for determining the impact of the Biodiversity Fund – but it would also have the potential to be adapted and used elsewhere in the world in those circumstances in which communities had ownership of and/or management responsibilities for protected areas.

## Annex I: 	UNDP Social and Environmental Screening Procedure and plans as needed

-See separate file-

## Annex J: Stakeholder Engagement Plan

1. Information dissemination, consultation, and similar activities that took place during the PPG

Throughout the project's development, close contact was maintained with stakeholders at the national and local levels. Numerous consultations occurred with all of the above stakeholders to discuss different aspects of project design. This included:

- As series of consultations with national public institutions and multilateral agencies and entities – notably CEPA, the Treasury, the Provincial Governments, and representatives from the Bank of Papua New Guinea, USAID, DFAT, ExxonMobil, Barrick/Porgera Joint Venture and UNDP – to solicit information on the current project baseline, consult on proposed project interventions and confirm the political, administrative, operational and financial commitment of project partners (including securing co-financing commitments) (see Annex F);

- A series of consultative field visits and meetings with local communities and the relevant responsible institutions in the project’s target areas (including visits to the Sepik Wetlands, various sites in the vicinity of Madang including the Wanang area, and Kimbe Bay). These field visits and meetings sought to assess the local challenges in situ, and consultatively identify prospective solutions (see also Annex F);

- Two consultative consolidated workshops with representatives of all key local, national and international organizations and NGOs in order to solicit information, and present the project and identify opportunities for synergies and collaboration.  This included a “pre-validation” workshop to present the detailed project outputs, activities, budgets and implementation arrangements to all stakeholders, including all key government agencies and institutions, development partners, NGOs and other civil society partners; and

- Iterative circulation of the project documentation for review and comments.

2. Approach to stakeholder participation

The project’s approach to stakeholder involvement and participation during project implementation is premised on the principles outlined in the table below.

| Principle | Stakeholder participation will: |
| --- | --- |
| Value Adding | be an essential means of adding value to the project |
| Inclusivity | include all relevant stakeholders |
| Accessibility and Access | be accessible and promote access to the process |
| Transparency | be based on transparency and fair access to information; main provisions of the project’s plans and results will be published in local mass-media |
| Fairness | ensure that all stakeholders are treated in a fair and unbiased way |
| Accountability | be based on a commitment to accountability by all stakeholders |
| Constructive | Seek to manage conflict and promote the public interest |
| Redressing | Seek to redress inequity and injustice |
| Capacitating | Seek to develop the capacity of all stakeholders |
| Needs Based | be based on the needs of all stakeholders |
| Flexible | be flexibly designed and implemented |
| Rational and Coordinated | be rationally planned and coordinated, and not be ad hoc |
| Excellence | be subject to ongoing reflection and improvement |

3. Stakeholder involvement plan

The project’s design incorporates several features to ensure ongoing and effective stakeholder participation in the project’s implementation. The mechanisms to facilitate involvement and active participation of different stakeholder in project implementation will comprise a number of different elements:

(i) Project inception workshop to enable stakeholder awareness of the start of project implementation

Once the PIU team has been recruited and once the baseline data have been collected, the project will be launched by a multi-stakeholder workshop. This workshop will provide an opportunity to provide all stakeholders with the most updated information on the project and the project work plan. It will also establish a basis for further consultation as the project’s implementation commences.

The inception workshop will address a number of key issues including: assist all partners to fully understand and take ownership of the project; detail the roles, support services and complementary responsibilities of UNDP, the PIU, CEPA, the civil society organisations that are a key to each protected area’s success, provincial government institutions, LLGs and development partners regarding the implementation of project activities; and discuss the roles, functions, and responsibilities within the project structure, including reporting and communication lines, and conflict resolution mechanisms.

The workshop will also be a forum to: review the project budget; finalize the first annual work plan as well as review and agree on the indicators, targets and their means of verification, and recheck assumptions and risks; provide a detailed overview of reporting, monitoring and evaluation (M&E) requirements; and plan and schedule project meetings for the PB.

(ii) Constitution of the PB to ensure representation of stakeholder interests in project

A Project Board (PB) will be constituted to ensure broad representation of all key interests throughout the project’s implementation. The representation, and broad draft TOR, of the PB are further described in Section VIII of the Project Document (with further details of the PB’s draft TOR in Annex D).  As is noted in Section VIII, the PB will be inclusive, transparent and accountable, and, as such, it will be open to the public and observers will be welcome.  The observers may include state and non-state actors, the private sector, NGOs, CBOs and protected area community representatives – however, they will not be voting members of the PB.  While observers will not have the right to vote in PB meetings, they do have the right to call for a PB meeting if there has not been a PB meeting for over nine months in any given period through the project’s life.

(iii) Establishment of a Project Implementation Unit to oversee stakeholder engagement processes during project

The Project Implementation Unit (PIU) - comprising a Project Manager (PM), Financial and APFO and Technical Adviser(s) - will take direct operational and administrative responsibility for facilitating stakeholder involvement and ensuring local ownership of the project and its results. The PM and FAA will be located in Port Moresby to ensure coordination among key stakeholder organizations at the national level during the project period.  The project will work directly through local partners in each of the project’s targeted areas to ensure closer working relationships with local stakeholders and communities.

The PIU will also include a Social and Environmental Safeguards Officer (SESO) who’s specific job will be to ensure stakeholder engagement and participation in project processes (see Annex D for her/his Terms of Reference).

(iv) Project communications to facilitate ongoing awareness of project

The project will develop, implement and maintain a communications strategy to ensure that all stakeholders are informed on an ongoing basis about: the project’s objectives; the projects activities; overall project progress; and the opportunities for involvement in various aspects of the project’s implementation. This strategy will ensure the use of communication techniques and approaches that appropriate to the local contexts such as appropriate languages (and especially tok pisin) and other skills that enhance communication effectiveness. The project will develop and maintain a web-based platform for sharing and disseminating project information; this will be coupled with the Biodiversity Fund’s website once it has been established.

(v) Stakeholder consultation and participation in project implementation

The project aims to be inclusive and participatory in all aspects of its implementation:

- Output 1.1 – the process to understand the roles and responsibilities of all of the organisations and institutions will, by its very nature, be participatory involving all of the people from those institutions and organisations.  Indeed, this will be done in such a way that people from those institutions and organisations take ownership of their mandates such that they seek to fulfil those mandates once the exercise is complete.

- Output 1.2 – the process to develop the Business Plan will similarly be carried out in a fully inclusive and participatory way – to understand the complementarity with other parallel process that are underway in the country and to seek innovative opportunities.  In addition, securing long-term support from the government is central to the Business Plan and their involvement in the process will be critically important.

- Output 1.3 – building capacity among the institutions and organisations is, by its nature, inclusive and participatory.

- Outcome 2 – this focuses on the establishment, capitalisation and operationalisation of the Biodiversity Fund.  The process to develop the documentation for the Biodiversity Fund will be participatory and inclusive – especially because its constituents are the communities that own the land across the country.  Therefore, at each step of the documents’ development, there will be consultation and the draft and final versions of the documents will be presented at broad stakeholder meetings.

- Output 3.1 – this will pilot the delivery of funds from the Biodiversity Fund to the protected areas across the country.  While at the beginning of the process, only a small number of pilot areas will be targeted, this is expected to significantly expand by the end of the project.  Again, by its very nature, this process is inclusive.  The project will ensure that at the site level, this is done in an inclusive way.  In addition, the project will be defining and promoting “protected area management” in a new way (see Box 1) – the very nature of which is putting the livelihoods and well-being of the communities who live within and surrounding the protected areas at the heart of protected area management (and moving away from the ‘traditional’ approaches to protected area management).

- Output 3.2 – this section of the project focuses on the three targeted areas.  The work in these areas will be done through partners that are either already active in the area or will be selected because of their participatory and engagement approaches.  The work will take place at a grassroots level – and aspects such as gender (as described in the project’s gender strategy (see Section IV and in Annex I) will be centrally important.

- Output 3.3 and 3.4 – both outputs are about learning, and monitoring and evaluation.  There will be a strong emphasis on participatory approaches in the learning and monitoring and evaluation (see also Section VII).

A participatory approach will be adopted to facilitate the continued involvement of local stakeholders including the vulnerable and marginalized members of the community (including women, youth and elderly) and institutions in the implementation of the project activities within the targeted areas. Wherever possible, opportunities will be created to train and employ local residents living in the vicinity of the selected protected areas.

(vi) Capacity building

The majority of project activities are strategically focused on building the capacity - at the systemic, institutional and individual level - in order to ensure sustainability of initial project investments. Significant GEF resources are directed at building the capacities of inter alia: the local administrations (LLGs), the local community and people living in the vicinity of the protected areas, and their partners. Wherever possible, the project will also seek to build the capacity of local communities (e.g. local community groups and vulnerable and marginalized segments) to enable them to actively participate in project activities. The project will, wherever possible, use the services and facilities of existing local training and skills development institutions.

4. Coordination with other related initiatives

In Section IV, there is a thorough exploration of project partners, synergies and potential partnerships that are either already formed through the PPG process or will be engendered through the project’s implementation.

In addition, the project will overlap with the GEF-4 and GEF-5 projects that will be being implemented during the project’s early years and, as a consequence, there are many opportunities for sharing experiences and adapting the project on the basis of lessons learned through all these other projects.

There are also complementary programmes being carried out by the CEPF and USAID; the project will establish close contact with both programmes and ensure that synergies are maintained (without duplication) and that lessons are shared and in order to identify and develop opportunities for ongoing collaboration.

Similarly, the project will work with all partners as identified in the partnerships analysis (see Table 5 of the project document).  As such, the project will seek to develop collaborative agreements with key partners (notably FORCERT, MHL, SWMI, WCS, BRC and a suite of partners in Kimbe Bay). The project will, within the framework of these collaborative agreement/s, then assist in reimbursing the costs of NGOs in the direct implementation of activities that fall directly within the ambit of the project outputs.  All of these organisations will be invite to be observers of the PB.

## Annex K: Gender Analysis and Action Plan

- Rationale for the Social and Environmental Screening (SES)

- To maximise the scope for achieving the SDGs’ desired outcomes, all programmes funded by or through UNDP must contribute to social and environmental sustainability. Therefore “Programmes and Projects (must) adhere to the objectives and requirements of the SES, which are to: (i) strengthen the social and environmental outcomes of Programmes and Projects; (ii) avoid adverse impacts to people and the environment; (iii) minimize, mitigate, and manage adverse impacts where avoidance is not possible; (iv) strengthen UNDP and partner capacities for managing social and environmental risks; and (v) ensure full and effective stakeholder engagement, including through a mechanism to respond to complaints from project-affected people.” (quoted from UNDP “Environmental and Social Screening Procedure” Version March 2016).

- As part of the SES, gender (and other) power relations are analysed and conditions to address gender and other inequalities are formulated:

- No sustainable development can be achieved without gender justice and equality;

- Everyone is gendered: women, men, youth (f/m/t) and hence the gender analysis addresses all positions;

- Protection of the environment without serving the interest of the people (women, men, youth, elderly in their various positions) living on, and from the land to be protected is not sustainable.

- Methodology and approach

- To collect the data required for this SES, which includes a gender power analysis, the following activities were undertaken:

- A literature review, covering the issues to be addressed by the project as well as issues pertaining to the socio-economic, assets’ control and (gender) power position of different sections of the communities in the proposed geographical areas;

- Meetings with CEPA and relevant PNG government departments and financial institutions; (I)NGOs; CSOs and research institutes involved in, or having an interest in environmental protection, biodiversity as well as socio-economic developments and rights of (mostly) rural communities;

- Meetings with relevant private sector parties, already engaged in environmental protection activities and its funding, to learn from their experiences;

- Meetings with funding agencies and INGOs already engaged in financing environmental protection, potentially interested to be co-financers of the project to be developed;

- A stakeholder Inception workshop on 18 May 2017 in Port Moresby, discussing basic problems to be addressed by the project; potential solutions, risks and obstacles, as well as the nature of information to be collected during field visits;

- Design of selection criteria for potential pilot areas for the project to be developed, based on which CEPA made a preliminary site selection;

- Visits to proposed pilot areas in Sepik, Madang/Wanang and Kimbe areas, as well as a visit to Lae, to meet with Provincial and LLG officials, NGOs, research institutes and private sector parties and, most importantly, to collect primary data among communities through meetings with local leaders and Focus Group Discussions with women, men and young people, both together and separately. These meetings were meant to learn not only about their differentiated socio-economic and gender power positions, environmental issues, concerns and changes observed, their development opportunities, but also about their dreams, desires, and their interest to actively engage in furthering environmental protection, through the establishment of Protected Areas, for their own long term socio-economic benefits as well as the maintenance of the biodiversity of PNG.

- Project validation workshop with key stakeholders on 29 November 2017 in Port Moresby, discussing and checking field findings re gender and social power issues.

- Context analysis

- There are a few striking differences between the environmental protection context of Papua New Guinea and many other countries in development to which GEF makes financial contributions for sustainable environmental protection.

- Though PNG does not rank high on the standard global GDP listing (119th out of 190 countries in 2017), particularly in rural areas most communities in all their diversities, including women and young people, generally do not suffer (sustained) food insecurity or problems of building and maintaining adequate shelters for their families. There are indications, however, that global climate change may increase the number of climate refugees, for whom such/ this erstwhile security no longer exists.

- Approximately 95% of all the land in PNG belongs to communities and not to the state. Barring a few state parks, the land and water areas already registered, demarcated and proposed to be registered or potentially available as “Protected Areas” legally belong to communities (whether under control of these communities or under control of other parties/industries, through long term leases or illegal occupation). The new project will therefore primarily relate to those communities.

- Whereas the natural wealth, abundance and diversity of animal and plant species in most such (potential) protected areas is evidently deteriorating, it still appears very abundant as the changes are relatively slow and hence most people in the communities are not very conscious or worried about such deterioration and hence not easily inclined to undertake efforts costing time, energy and money protecting their environment. Through increased alternative sources of cash income, moreover, food and income particularly of men depend less on their own natural resources than it did before and hence a deterioration does not instantly affect their lives.

- Gender power issues: the distinct positions of women and men

- Papua New Guinea is known for its great diversity of peoples, cultures, traditions and languages. Historical geographical origins, as well as present geographical contexts (living on different islands, in different altitudes of mountain ranges or in coastal areas, as well as diverse modes of production) have influenced cultural traditions, practices, habits, as well as changes, maintenance or reinforcement of such traditions and practices in the communities. Notwithstanding such great historical diversity, including a small number of communities following matrilineal heritage practices, the commonly adhered to patriarchal norms and values, the traditional cultural ones as well as those introduced in colonial times, greatly determine and maintain the social position of women and girls as subordinate to men, both in public and in private spheres, throughout the country.

- Most rural communities in PNG do not suffer from food insecurity, shelter problems or poverty: nature’s abundance provides for most of their basic food items, cooking fuel, water and house construction materials. Sale of marketable produce (from gardens, fishing, hunting or – more recent- commercial farming activities, or sometimes cash income from employment) generally covers primary cash needs, although school fees for secondary school education of both boys and girls are mentioned as increasingly problematic. Available food is shared equally between members of families, without discriminating according to sex. Similarly, no sex-based discrimination was mentioned with respect to spending money on school fees.

- While the basic livelihood provision is fairly good for men and women alike, it was strikingly clear from the literature study as well as from the community focus group discussions and the overall assessment in preparation of the proposal, that local cultural traditions, colonial administrative heritage and particularly patriarchal notions of male and senior age dominance, not merely determine division of labour between women and men in favour of men, but also seriously restrict the social position and decision making power of women - and to a great extent of young people - in matters of daily life and planning for the future at personal, household and community levels.

- Though variations exist among communities and regions in terms of the position of women and their levels of financial autonomy, social status and control over the use of productive assets, the general conclusion is that the position of women in PNG is (nearly) always secondary to men; that women suffer from male dominance in all respects and that many women are subjected to serious (domestic) physical as well as sexual violence.

- Socio-economic position of women and men in the communities

- Women are almost exclusively responsible for managing the household affairs in terms of food preparation, fuel and water collection, rearing and caring for children, while also highly involved in food production in the ‘gardens’ (swidden cultivation) and with fishing, when living in coastal areas.

- With variations between communities and regions, many women in rural areas are organised in social groupings, often through their participation in church related groups, much more so than their male partners in the communities. Formal community leadership is generally in the hands of men only, though sometimes a wife of a community leader can be seen as leader and automatically given the responsibility to organise and lead women in the community. Hence the position of women in society can be influenced by their husbands social, economic and leadership status.

- Hunting, clearing of land for new gardens, fishing by boat and the main construction work on a new house has traditionally been the work of men. Employment in the oil palm industry, and other formal employment outside the community is also usually limited to men.

- With reduced fishing by boat in many locations and less opportunities for hunting and other such traditional male work, many men sit idle at home, while waiting for their wives to serve them.

- Gender Based Violence: more than an individual mishap

- Violence Against Women (VAW) and more general, Gender Based Violence (GBV), is not a new phenomenon in PNG, but from (verbal) accounts it appears to have seriously increased in recent years. A range of different causes are mentioned particularly by women in the communities as well as by other stakeholders and experts, referring to old traditions but also to recent (social and economic) changes in the communities and the PNG society at large.

- An often-mentioned cause of such violence is the notion of ‘male entitlement’, resulting from toxic masculine interpretations (‘woman is owned by man’) of the tradition of paying a bride price to the community at the time of marriage. But the (amount of the) bride price as such is also mentioned as easily triggering GBV.

- One of the triggers for the use of GBV is the excessive use of drugs and alcohol (which is often consumed ‘on credit’). Alcohol, commercially produced or locally brewed from available fruits, has been around for many years, but the level of home-brewed and - more recent home distilled – alcohol has fast increased. Particularly young boys, sitting idle at home - in absence of education/schooling opportunities, jobs or gainful activities-, are easily tempted to engage in “steaming”, the term used for distilling alcohol. Their strong alcohol is sold within the community as well as to outsiders and provides them cash needed for fashionable clothing, mobile phones and phone airtime. The cash they require to buy the ingredients that are not available in the community (e.g. sugar and yeast) is often forcibly taken from their mother or wife.

It was noted that sometimes also young women help their partners of brothers in the brewing and distilling process as it earns them some cash income. Increasing numbers of young women also drink.

- Levels of literacy and education in general are low and life-skills education, including communication and anger management skills, are generally absent (only occasionally provided through church or Women’s Council groups or civil society organisations, e.g. Eastern Highlands Family Voice).

- Comprehensive sexuality education is virtually absent and hence awareness about family planning and contraception is minimal. As a result (also caused by the increasing absence of reproductive health care and supplies) the family size in many rural areas has increased, leading to more stress in the families.

- Men, using their dominant position, often insist on having a son and in case there are only daughters, their wives feel obliged to give in, even if they prefer not to have more children. Husbands will easily use the threat of marrying another woman, in case the wife does not give in to the man’s sexual desires and wanting more children. Many women prefer less children.

- Many women fear their husbands and cultural traditions do not give much space to women to voice her own opinion: men decide, women need to oblige.

- In some areas, however, women are becoming more vocal and will not accept all men say. This happens particularly when women have had some education, have their own income and are organised through church- or NGO-organised or women’s council groups. But voicing their views easily leads to increased domestic violence as men want to keep their level of control (often under peer pressure by other men).

- Particularly when men are frustrated - no gainful employment, reduced local production to sell, hence ‘failing’ as traditional breadwinner and thus as ‘a man’ (according to their upbringing) - they often use violence to show or reconfirm their dominant power position as their skills to communicate in other ways within the household are limited.

- Other reported triggers for men to feel insecure and frustrated resulting in violence are the level of nepotism and corruption as well as the effects of wantokism.

- For other men, it is their access to money and changing lifestyle - without taking responsibility for the family needs - that induces the use of violence, particularly in the case of extra marital relations.

- In East Sepik polygamy is increasing (men often using their ‘barren wives’ as excuse) easily leading to domestic conflicts and violence as the first wife has no say in such second marriage.

- Different expressions of modernity, new lifestyles, higher needs for cash and a clash of older and younger generations’ thinking - influenced by using social media -  are often seen as triggering conflicts and violence.

- Many children grow up in families where men control their children and partner by instilling fear and using violence. Boys that have witnessed their father using violence against their mother to get something (done) easily see and adopt that as normal behaviour, while girls in such situations learn to accept the violence and oblige.

- Because the traditional social practices of ‘hunting’ rape perpetrators or ridiculing a man, who uses violence against his wife, have faded away in many communities and there is hardly any law enforcement response to such violence (and hence little reporting), men mostly get away with their continuous use of domestic and gender based violence, condoned by their peers.

- It is also noted by many professionals that PNG laws on domestic violence (as well as sorcery, leading to violence) urgently require updating, to be able to address GBV effectively.

- GBV, abuse and rape of women is also prevalent in the settings of the extracting industries: mostly without any repercussions for the perpetrators or adequate support for the survivors.

- Not all men are violent, but because there is a culture of violence, condoning the use of violence is common, making many men ‘bystander’ to GBV, rather than actively stopping and preventing it. Peer pressure among men to condone violence, makes it difficult for men to start addressing abuse, rape and other forms of gender violence.

- Unless acknowledged and addressed, the gender based power difference and notably the wide-spread prevalence of GBV, is a structural hindrance in the effective design and sustainable implementation of any development project, also and perhaps specifically in the organisation of community based environmental protection.

Support for GEF-6 project activities at community level will be conditioned by eliminating and preventing GBV. Community groups, unwilling/unsuccessful in addressing and preventing GBV will be excluded from financial support. Community groups lacking necessary skills, but willing to address GBV, however, can be trained and supported in their process to eliminate/prevent GBV.

- Age power issues: the position of young people

- Traditionally, young people -boys and girls- have little say in matters that concern the community at large or for that matter in family affairs. At home the father and at community level the traditional leaders, primarily men, only occasionally a woman, decide.

- Because of the changes in mobility and contacts, influenced by using mobile phones and social media (where there is mobile phone coverage) the position, views and aspirations of young people, particularly boys, is changing. Depending on the ease of contact with the world outside their own community or village, young boys and to some lesser extent girls, develop different views on their cultural tradition and values than their parents hold. This often leads to generational conflicts, in which parents do not know how to ‘manage’ their adolescent children, and adolescents at the same time feel ignored by their parents. Marriage age has gone down in recent years, reportedly from - on average - 25 to as low as 14.

- Young people’s aspirations and ambitions vary, in relation to their own levels of education, opportunities for (self-) employment, proximity to urban areas and related transport, and strength of their cultural ties to the community. In many rural and remote communities, young boys (both unmarried and newly married) find little opportunities for (paid) work and hence many sit idle at their parents’ homes. In absence of parental guidance, or adequate education or other forms of social education, young boys, as mentioned above, may easily engage in home brewing and distilling of alcohol for their own consumption and selling (to earn some income), subsequently contributing to abusive alcohol consumption, GBV and sexual abuse. As a result, there is an increase in unwanted teenage pregnancies, occasionally leading to underage marriage. Many pregnant young girls, however, return home and get socially isolated.

- Different from young boys, freely roaming around or sitting idle at home, most young and newly married girls are occupied in household activities and when land is available, food gardening and fishing. Mothers often prefer their daughters to go to school as they recognise the value of educated girls in their future lives.

- Some young people, both boys and girls, are conscious about the environmental changes and deterioration; they see the need for protection, but also feel that their voices are rarely heard by the older generation leadership.

- Development issues in rural communities

- Though basic food and shelter needs are covered reasonably well in most rural communities, some other development needs are no longer met. Whereas many rural communities have facilities for elementary and primary education, the recruitment and particularly retaining of teachers has become a severe problem. Many communities do not have teachers from their own communities and hence need to employ teachers from outside the community. Payment of salaries and provisions for the schools by the government has become a problem and hence many schools are no longer in use as there are no teachers. Externally recruited teachers may also leave their job because of the remoteness of the community. In one situation a teacher left because the level of alcohol abuse in the community was extremely high and none of the parents or community leaders were prepared to address the issue.

- There were also reports about teachers being abusive and thereby not providing a conducive learning context.

- Similar to the situation in the field of education, many rural health centres do not have trained staff, equipment or (adequate) medical supplies, because the government is no longer providing the funds for that, leaving large segments of the rural population in need of general health care as well as reproductive health- and maternity care. No family planning education is provided, nor are contraceptives available for those families wanting to space or prevent (further) pregnancies. Compared to other countries in the Pacific/Oceania region, the population growth in PNG is high (estimated to be 2.07 in 2017 by worldpopulationreview.com, but women in the communities visited reported much higher figures), resulting in hardship in the families concerned as well as fast increasing pressure on the environment.

- PNG moreover has “the highest incidence of HIV/AIDS in the Pacific and meets the criteria for a generalized HIV/AIDS epidemic. The leading cause of death is malaria, which affected about 1.7 million people in 2003 alone” (source: http://worldpopulationreview.com).

- Many communities lack adequate access to safe drinking water sources, aggravated by the fast increase of the population. Limited road infrastructure and absence of affordable means for water transport limit access by the communities to markets, supplies, larger healthcare facilities and higher education, and vice versa, for such service providers and government officials to the communities. Many communities still do not have any, or only very limited access to mobile phone coverage to the world outside their own community.

- In absence of adequate transport infrastructure and facilities, local food production in access of local needs is hardly marketed outside.

- Environmental awareness and protective action

- The visits to the communities, WMAs and LMMAs revealed that men generally did not report fundamental changes in their natural surroundings that have impacted their lives. As a result, men generally did not express the need or urgency to protect their environment. The reasons for that appear to be threefold: 1. Environmental changes, including reduced presence or disappearance of fish and wildlife species happen through slow processes. 2. With the increase of commercial activities, like oil palm cultivation, or employment in the oil palm and other industries, their reliance on access to fertile fishing or hunting grounds, or forest land for gardens has reduced, as part of their needs are now met by cash income. 3. Men are rarely in full charge of collecting drinking water or cooking fuel, hence they do not notice the changes easily.

- Women on the other hand, spoke of changes in the environment affecting them directly through decrease in the (easy) availability of fuel wood, availability and access to clean and safe drinking water, as well as either reduction of space for gardens to grow staple food, fruits and vegetables, or returning to the same garden areas after too short a period for it to regenerate its fertility. Fast population growth as well as use of garden land for oil palm were mentioned as the causes.

- With oil palm trees often planted in erstwhile vegetable gardens, the diet in many communities has changed as well. Increasingly fresh staple food, vegetables, fruits and fresh fish are replaced by industrially produced and often imported canned or packaged foods. Reduced fresh food intake is likely to negatively affect personal health, which is already reported in some areas.

- In focus group discussions women as well as men are shared their views that much of the environmental degradation (erosion, water pollution, reduction of land available for gardens) were caused by loggers, violating existing laws and community land rights, but they felt unable to stop them and when tried, unsuccessful in raising these issues with the relevant authorities. Similarly, many women and youth realised that communities were not adequately protecting their fishing grounds against external intrusion and hence there is increasing theft of stock. But there was also awareness that sometimes members of their own communities were to be blamed as they give in too easily and prefer illicit cash earning by harvesting crocodile eggs, sea cucumbers beyond sustainable numbers or by uprooting entire massoy (local shrub species), eaglewood and other valuable trees and shrubs for quick sales to traders from West Papua and elsewhere to produce commercially lucrative fragrances and other products.

- In some proposed pilot locations there was fear among community members for the impact that proposed - but not fully started - mining will have on their habitat, wildlife and fish stock because of proposed (and sometimes already started) road construction and related erosion and pollution.

- Environmental protection to date: focus on the environment, not on community needs

- Starting from the late seventies, several INGOs have promoted environmental protection through the establishment and (when possible) registration of conservation areas (WMAs and LMMAs). Foreign funds were made available for the procurement and running of equipment e.g. boats, fuel, staff stipends, etc. Some extracting industries have also invested in different forms of environmental protection as part of their CSR policies.

- Overall planning and environmental analysis and visioning for these ‘protected areas’ was usually done by the staff of the INGOs. Community groups, mostly consisting of men, were established for the implementation of the environmental protection plans. At community level, decision making was usually in the hands of management committees of elder men (including local chiefs and other established authorities), with only occasionally a few women members.

- For as long as funding continued, these WMA and LMMA committees existed and various protective activities were undertaken, but with little involvement of women or young (f/m/t) people. Most of the funded activities related directly to environmental protection, with generally little attention for other (immediate or long term) needs that communities have. Reportedly, there was hardly a sense of ownership of the selected activities by the communities: receiving the payments and equipment was the major driving force, to be involved in such projects. When the (I)NGOs no longer received funding and terminated their investments, payments and often even their (office) presence, many such environmental protection activities seized operation, and hence: protection stopped.

- Many women in the suggested pilot areas visited were conscious of the failing management of the earlier projects and felt that they as women in the communities - sometimes already organised in groups through their church, an NGO or as local women’s council) - could manage environment conservation areas very well.

- It must be noted that there are also a sizable number of old Protected Areas in PNG (whether formally registered as such or not) that have continued protecting their land areas without any government or NGO support. These communities are motivated to protect their natural environment because they are aware of the need as well as the benefits they derive from such protection.

- Potential role of women and youth in effective environmental protection

- In view of the felt needs of women (fuel, clean water, food gardens, small fishes and related management roles) and their deeper felt urgency and hence potential sense of ownership of initiatives to protect their surroundings and address negative environmental changes, the project will pro-actively engage women in the choice, design and management of the project activities in their setting.

In the GEF-6 project 65% of the positions in committees, set up to plan and manage PAs, will be reserved for women and youth

- Success and sustainability of any development activity lies with the level of ownership, commitment and responsibilities taken for activities by community members concerned. Given their understanding of the urgency, it is foreseen that in many of the activities and activity management women will be in the lead.

- Because (some) young people (m/f/t) showed clear interest in environmental protection as well, their joblessness and sitting idle at home could change if they are adequately heard and involved in planning, decision making and implementing of environment protection activities as well, transforming their often-negative social position in the community to a positive role of engagement and action. Their potential and practical roles will be assessed as well in the start-up phase of the different project activities.

- Andro-centrism and patriarchal power relations, traditions and practices do not change overnight and hence, design meetings in the start-up phase will involve the traditional male leadership in support for the activities to be undertaken, as in the long run the whole community will benefit.

- The more recognition and support can be generated for the active role of women in (some of) the environmental protection and livelihood activities planned, the greater the scope for the project to go beyond only gender mainstreaming during the project’s life and actually contribute towards gender transformative action: recognition of the important roles women play, gender-balanced sharing of planning, implementing and managing of the protective activities, rather than women only following male instructions.

- Once stronger organised and vocal, and concretely involved in project management, women will be supported, along with men and f/m/t youth, to also address other issues of the gender and generation inequalities: male dominance and (sexual) violence. An active role by young people (m/f/t), with dreams and aspirations that often differ from the traditional elder male dominance, is likely to enhance a positive social change process. If adequately guided and trained, young women and men can help reducing physical and gender-based violence and thereby contribute to a more conducive and cooperative community life.

- Such change processes require strong civil society support in the bottom-up organising and planning phases. But it will also require government services being delivered to the communities: quality (hence context-adequate) education, delivery of required reproductive and other health services, credit/rural banking and marketing opportunities, and adequate and affordable communication infrastructure (mobile coverage, roads, boats).

- Whereas the minimal requirement of any new development project should be ‘do no harm’, hence not being gender-negative and increasing inequalities, or gender blind, the GEF-6 project provides a crucial and indispensable development opportunity, contributing to gender transformative action. It will aim to move towards gender- and age-transformative action, as a sustainable win-win situation for everyone. In the planned project life of only seven years, this may not be totally achieved, but the processes and structures put in place are planned to create, practice, experience and subsequently carry forward the ingredients towards gender transformation and hence gender justice, beneficial to all.

- One of the crucial elements for this, is for women and young people to also play an active role in the monitoring and evaluation processes of the project. What changes, brought about by project activities, do they consider sustainable improvements in their lives? What are the indicators they want to use, to monitor progress towards the desired changes?

- In the start-up phase of the project, all concerned and particularly women and young people (f/m/t) will be trained and guided in formulating their own baseline (covering livelihood issues, gender and age power issues, environment), setting short and longer-term goals, as well as monitoring mechanisms and indicators to measure progress and address problems. The ultimate financial sustainability of protected areas depends greatly on the level of acceptance of responsibility for the management and handling of community owned land and water areas, which in turn will relate to the opportunities of women, men and young people of the communities to equally benefit from such protection and improve their lives.

As a result of the PPG process for this project, there was a shift in focus of the project from that of the PIF (which was very state-centric) to one that puts the people and the community-owned protected areas at the heart of the project (and the protected area system - as they should be)! As a consequence, the project, as a whole, has been designed to counter social and environmental threats; in other words, the actions to mitigate social and environmental risks have woven into the fabric of the project. The shift also brought the project in line with the comments that had been received from the perceptive and prescient STAP review and GEF Council comments. The degree to which this is achieved, of course, depends on the project being implemented in an effective and efficient way; the project has also been designed to increase the likelihood of this happening – including ensuring that the PIU includes a Social and Environmental Safeguards Officer (SESO).

## Annex L: Additional Maps

Figure 3. The existing logging concessions in PNG. Figure from Bryan & Shearman, 2015

Figure 4. The SABLs across the country. Figure from Bryan & Shearman, 2015

## Annex M: UNDP Risk Log

| # | Type | Date Identified | Description | Review or Completion Date | Comment or Management Response | Critical or Completion Flag |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Organizational | 13 March 2018 | Limited institutional capacity, mandate, roles and responsibilities leading to limited institutional functionality, even with capacity development efforts |  | Status: Stable Probability: 3 Impact: 3 Countermeasures: The project is addressing this issue – particularly as it relates to protected area management and financing (Output 1.1 and 1.3); the management arrangements and feasibility analysis make proposals to streamline and improve the project management and implementation efficiencies (see above and Section VIII). Owner: UNDP (Regional and CO) | MODERATE |
| 2 | Organizational | 13 March 2018 | Project implementation may be afflicted by mismanagement and corruption, based on the experience of similar previous projects (e.g. the Mama Graun Conservation Trust Fund) |  | Status: None with respect to current GEF projects Probability: 1 Impact: 4 Countermeasure: the project has been designed with numerous measures to ensure the effectiveness and efficiency of the project (see Section VIII Governance and Management Arrangements). The key stakeholders are community groups owning/using and protecting their own communal land, rather than government institutions/staff with no stake in success. Owner: UNDP-CO | MODERATE |
| 3 | Financial | 13 March 2018 | The Biodiversity Fund is insufficiently capitalised |  | Status: N/A Probability: 2 Impact: 4 Countermeasure: The project supports development and implementation of both a business plan for the protected area system (Output 1.2) and a fund-raising/resource mobilisation strategy (Output 2.3); in addition, the use of the transparent and accountable as a vehicle for the Biodiversity Fund will build trust. Overall, the risk should be mitigated. Owner: UNDP | MODERATE |
| 4 | Financial and organisational | 13 March 2018 | The government does not allocate adequate resources (both human and financial) in response to the additive processes that result from the project’s incremental impacts |  | Status: The government’s allocation to the protected area system has remained stable Probability: 4 Impact: 3 Countermeasure: The project is targeting the government to increase the allocation to the protected area system, both through the business plan (Output 1.2) as well as the fund-raising/resource mobilisation strategy (Output 2.3). However, the government’s response remains unpredictable. Owner: Govt. of PNG, UNDP-CO | HIGH |
| 5 | Political | 13 March 2018 | PA Bill not approved leaving significant legislative gap in PA system |  | Status: Risk remains Probability: 2 Impact: 4 Countermeasure: The GEF-4 project that is still underway will continue to lobby for the approval of the PA Bill. Once implementation starts on this project, the situation will be (re)assessed (as part of Output 2.1) and it will be mitigated as best as possible. Owner: Govt. of PNG, UNDP-CO | MODERATE |
| 6 | Political/ organisational | 13 March 2018 | “land grabbing” and corrupt practices leads to loss of protected areas. |  | Probability: 2 Impact: 4 The additional legal protection offered by protected areas (through conservation deeds) will deter such ‘land grabs’ to occur. Indeed, the exercise to identify mandates will demonstrate the need for CEPA to provide legal services to protected area owners and managers to counter such land grabs (under Output 1.1). | MODERATE |
| 7 | Environmental | 13 March 2018 | Major natural and climate induced disasters including other environmental risks – may affect the implementation and results of project initiatives. |  | Status: Increasing Probability: 3 Impact: 3 Countermeasure: Although over the life of the project, the impact of climate change is estimated to be moderate, the project is putting in place strategies that should mitigate the impacts of climate change (both through the increased effectiveness of protected area management). However, the project will have to take care to ensure, for example, that local communities (and their use of natural resources) remain adaptable in the face of climate change. Owner: Minister of Conservation, Environment and Climate Change; UNDP-CO | MODERATE |

## Annex N: Results of the capacity assessment of the project implementing partner and HACT micro assessment

-See separate file-

## Annex O: Capacity Scorecard Assessments for key government institutions

This section includes the Capacity Scorecard Assessments for the West New Britain, East Sepik and Simbu Provincial Governments

1- Capacity Score for the Provincial Government of West New Britain

| Strategic Area of Support | Target for CD | Outcomes | Outcome Indicators (Scorecard) | Initial Evaluation | Evaluative Comments |
| --- | --- | --- | --- | --- | --- |
| 1. Capacity to conceptualize and formulate policies, legislations, strategies and programs |  |  |  |  |  |
|  | Systemic | The protected area agenda is being effectively championed / driven forward | 0 -- There is essentially no protected area agenda; 1 -- There are some persons or institutions actively pursuing a protected area agenda but they have little effect or influence; 2 -- There are a number of protected area champions that drive the protected area agenda, but more is needed; 3 -- There are an adequate number of able "champions" and "leaders" effectively driving forwards a protected area agenda | 2 |  |
|  | Systemic | There is a strong and clear legal mandate for the establishment and management of protected areas | 0 -- There is no legal framework for protected areas; 1 -- There is a partial legal framework for protected areas but it has many inadequacies; 2 – There is a reasonable legal framework for protected areas but it has a few weaknesses and gaps; 3 -- There is a strong and clear legal mandate for the establishment and management of protected areas | 2 | There is only a draft policy and is still to be formalized. |
|  | Institutional | There is an institution responsible for protected areas able to strategize and plan (this is 2 issues - needs separating, 1 Systemic, 2 institutional) | 0 -- Protected area institutions have no plans or strategies; 1 -- Protected area institutions do have strategies and plans, but these are old and no longer up to date or were prepared in a totally top-down fashion; 2 -- Protected area institutions have some sort of mechanism to update their strategies and plans, but this is irregular or is done in a largely top-down fashion without proper consultation; 3 – Protected area institutions have relevant, participatorily prepared, regularly updated strategies and plans | 1 |  |
| 2. Capacity to implement policies, legislation, strategies and programs |  |  |  |  |  |
|  | Systemic | There are adequate skills for protected area planning and management | 0 -- There is a general lack of planning and management skills; 1-- Some skills exist but in largely insufficient quantities to guarantee effective planning and management; 2 -- Necessary skills for effective protected area management and planning do exist but are stretched and not easily available; 3 -- Adequate quantities of the full range of skills necessary for effective protected area planning and management are easily available | 1 | Provincial Environment Officer with PA planning and management skill who assist existing and proposed protected areas in the province supported by GEF4. |
|  | Systemic | There are protected area systems | 0 -- No or very few protected areas exist and they cover only a small portion of the habitats and ecosystems; 1 -- Protected area system is patchy both in number and geographical coverage and has many gaps in terms of representativeness; 2 -- Protected area system is covering a reasonably representative sample of the major habitats and ecosystems, but still presents some gaps and not all elements are of viable size; 3 -- The protected areas include viable representative examples of all the major habitats and ecosystems of appropriate geographical scale | 2 | Several protected area work within the province such as Pokili and Garu WMA, LLMAs in Kimbe Bay, among others. |
|  | Systemic | There is a fully transparent oversight authority for the protected areas institutions | 0 -- There is no oversight at all of protected area institutions; 1 -- There is some oversight, but only indirectly and in a non-transparent manner; 2 -- There is a reasonable oversight mechanism in place providing for regular review but lacks in transparency (e.g. is not independent, or is internalized); 3 -- There is a fully transparent oversight authority for the protected areas institutions | 1 |  |
|  | Institutional | Protected area institutions are effectively led | 0 -- Protected area institutions have a total lack of leadership; 1 -- Protected area institutions exist but leadership is weak and provides little guidance; 2 -- Some protected area institutions have reasonably strong leadership but there is still need for improvement; 3 -- Protected area institutions are effectively led | 2 | Provincial Environment Officer expecting additional human resource (3 additional staff) to support protected area work in the province. |
|  | Institutional | Protected areas have regularly updated, participatorily prepared, comprehensive management plans | 0 -- Protected areas have no management plans; 1 -- Some protected areas have up-to-date management plans but they are typically not comprehensive and were not participatorily prepared; 2 -- Most Protected Areas have management plans though some are old, not participatorily prepared or are less than comprehensive; 3 -- Every protected area has a regularly updated, participatorily prepared, comprehensive management plan | 2 |  |
|  | Institutional | Human resources are well qualified and motivated | 0 -- Human resources are poorly qualified and unmotivated; 1 -- Human resources qualification is spotty, with some well qualified, but many only poorly and in general unmotivated; 2 -- HR in general reasonably qualified, but many lack in motivation, or those that are motivated are not sufficiently qualified; 3 -- Human resources are well qualified and motivated. | 1 | 3 more staff will assist the Provincial Environment Officer funded by GEF4 |
|  | Institutional | Management plans are implemented in a timely manner effectively achieving their objectives | 0 -- There is very little implementation of management plans; 1 -- Management plans are poorly implemented and their objectives are rarely met; 2 -- Management plans are usually implemented in a timely manner, though delays typically occur and some objectives are not met; 3 -- Management plans are implemented in a timely manner effectively achieving their objectives | 1 |  |
|  | Institutional | Protected area institutions are able to adequately mobilize sufficient quantity of funding, human and material resources to effectively implement their mandate | 0 -- Protected area institutions typically are severely underfunded and have no capacity to mobilize sufficient resources; 1 -- Protected area institutions have some funding and are able to mobilize some human and material resources but not enough to effectively implement their mandate; 2 -- Protected area institutions have reasonable capacity to mobilize funding or other resources but not always in sufficient quantities for fully effective implementation of their mandate; 3 -- Protected area institutions are able to adequately mobilize sufficient quantity of funding, human and material resources to effectively implement their mandate | 1 | Needs funding and resources. |
|  | Institutional | Protected area institutions are effectively managed, efficiently deploying their human, financial and other resources to the best effect | 0 -- While the protected area institution exists it has no management; 1 -- Institutional management is largely ineffective and does not deploy efficiently the resources at its disposal; 2 -- The institution is reasonably managed, but not always in a fully effective manner and at times does not deploy its resources in the most efficient way; 3 -- The protected area institution is effectively managed, efficiently deploying its human, financial and other resources to the best effect | 1 |  |
|  | Institutional | Protected area institutions are highly transparent, fully audited, and publicly accountable | 0 -- Protected area institutions totally non-transparent, not being held accountable and not audited; 1 – Protected area institutions are not transparent but are occasionally audited without being held publicly accountable; 2 -- Protected area institutions are regularly audited and there is a fair degree of public accountability but the system is not fully transparent; 3 -- The Protected area institutions are highly transparent, fully audited, and publicly accountable | 1 | Provincial Government provided minimal support for the operational cost of protected areas. |
|  | Institutional | There are legally designated protected area institutions with the authority to carry out their mandate | 0 -- There is no lead institution or agency with a clear mandate or responsibility for protected areas; 1 -- There are one or more institutions or agencies dealing with protected areas but roles and responsibilities are unclear and there are gaps and overlaps in the arrangements; 2 -- There are one or more institutions or agencies dealing with protected areas, the responsibilities of each are fairly clearly defined, but there are still some gaps and overlaps; 3 -- Protected Area institutions have clear legal and institutional mandates and the necessary authority to carry this out | 1 |  |
|  | Institutional | Protected areas are effectively protected | 0 -- No enforcement of regulations is taking place; 1 -- Some enforcement of regulations but largely ineffective and external threats remain active; 2 -- Protected area regulations are regularly enforced but are not fully effective and external threats are reduced but not eliminated; 3 -- Protected Area regulations are highly effectively enforced and all external threats are negated | 2 | Protected areas (Pokili and Garu WMAs) receives support from the private sector to conduct field monitoring |
|  | Individual | Individuals are able to advance and develop professionally | 0 -- No career tracks are developed and no training opportunities are provided; 1 -- Career tracks are weak and training possibilities are few and not managed transparently; 2 -- Clear career tracks developed and training available; HR management however has inadequate performance measurement system; 3 -- Individuals are able to advance and develop professionally | 1 |  |
|  | Individual | Individuals are appropriately skilled for their jobs | 0 -- Skills of individuals do not match job requirements; 1 -- Individuals have some or poor skills for their jobs; 2 -- Individuals are reasonably skilled but could further improve for optimum match with job requirement; 3 -- Individuals are appropriately skilled for their jobs | 1 |  |
|  | Individual | Individuals are highly motivated | 0 -- No motivation at all; 1 -- Motivation uneven, some are but most are not; 2 -- Many individuals are motivated but not all; 3 -- Individuals are highly motivated | 1 |  |
|  | Individual | There are appropriate systems of training, mentoring, and learning in place to maintain a continuous flow of new staff | 0 -- No mechanisms exist; 1 -- Some mechanisms exist but unable to develop enough and unable to provide the full range of skills needed; 2 -- Mechanisms generally exist to develop skilled professionals, but either not enough of them or unable to cover the full range of skills required; 3 -- There are mechanisms for developing adequate numbers of the full range of highly skilled protected area professionals | 1 |  |
| 3. Capacity to engage and build consensus among all stakeholders |  |  |  |  |  |
|  | Systemic | Protected areas have the political commitment they require | 0 -- There is no political will at all, or worse, the prevailing political will runs counter to the interests of protected areas; 1 -- Some political will exists, but is not strong enough to make a difference; 2 -- Reasonable political will exists, but is not always strong enough to fully support protected areas; 3 -- There are very high levels of political will to support protected areas | 2 | With political support from the Deputy Provincial Administration. WNBPA signed MOA with CEPA to co-finance GEF 4 activities in the province. |
|  | Systemic | Protected areas have the public support they require | 0 -- The public has little interest in protected areas and there is no significant lobby for protected areas; 1 -- There is limited support for protected areas; 2 -- There is general public support for protected areas and there are various lobby groups such as environmental NGO's strongly pushing them; 3 -- There is tremendous public support in the country for protected areas | 1 |  |
|  | Institutional | Protected area institutions are mission oriented | 0 -- Institutional mission not defined; 1 -- Institutional mission poorly defined and generally not known and internalized at all levels; 2 -- Institutional mission well defined and internalized but not fully embraced; 3 – Institutional missions are fully internalized and embraced | 1 |  |
|  | Institutional | Protected area institutions can establish the partnerships needed to achieve their objectives | 0 -- Protected area institutions operate in isolation; 1 -- Some partnerships in place but significant gaps and existing partnerships achieve little; 2 -- Many partnerships in place with a wide range of agencies, NGOs etc, but there are some gaps, partnerships are not always effective and do not always enable efficient achievement of objectives; 3 -- Protected area institutions establish effective partnerships with other agencies and institutions, including provincial and local governments, NGO's and the private sector to enable achievement of objectives in an efficient and effective manner | 2 | WNBPA has a good working relationship with UNDP and CEPA |
|  | Individual | Individuals carry appropriate values, integrity and attitudes | 0 -- Individuals carry negative attitude; 1 -- Some individuals have notion of appropriate attitudes and display integrity, but most don't; 2 -- Many individuals carry appropriate values and integrity, but not all; 3 -- Individuals carry appropriate values, integrity and attitudes | 1 |  |
| 4. Capacity to mobilize information and knowledge |  |  |  |  |  |
|  | Systemic | Protected area institutions have the information they need to develop and monitor strategies and action plans for the management of the protected area system | 0 -- Information is virtually lacking; 1 -- Some information exists, but is of poor quality, is of limited usefulness, or is very difficult to access; 2 -- Much information is easily available and mostly of good quality, but there remain some gaps in quality, coverage and availability; 3 -- Protected area institutions have the information they need to develop and monitor strategies and action plans for the management of the protected area system | 1 |  |
|  | Institutional | Protected area institutions have the information needed to do their work | 0 -- Information is virtually lacking; 1 -- Some information exists, but is of poor quality and of limited usefulness and difficult to access; 2 -- Much information is readily available, mostly of good quality, but there remain some gaps both in quality and quantity; 3 -- Adequate quantities of high quality up to date information for protected area planning, management and monitoring is widely and easily available | 1 |  |
|  | Individual | Individuals working with protected areas work effectively together as a team | 0 -- Individuals work in isolation and don't interact; 1 -- Individuals interact in limited way and sometimes in teams but this is rarely effective and functional; 2 -- Individuals interact regularly and form teams, but this is not always fully effective or functional; 3 -- Individuals interact effectively and form functional teams | 2 | Provincial Environment Officer overworked to cover the entire province including ODA projects such as GEF/UNDP, TNC/CSIRO, WWF, IOM, among others. |
| 5. Capacity to monitor, evaluate, report and learn |  |  |  |  |  |
|  | Systemic | Protected area policy is continually reviewed and updated | 0 -- There is no policy or it is old and not reviewed regularly; 1 -- Policy is only reviewed at irregular intervals; 2 -- Policy is reviewed regularly but not annually; 3 -- National protected areas policy is reviewed annually | 1 | Policy endorsed by NEC |
|  | Systemic | Society monitors the state of protected areas | 0 -- There is no dialogue at all; 1 -- There is some dialogue going on, but not in the wider public and restricted to specialized circles; 2 -- There is a reasonably open public dialogue going on but certain issues remain taboo; 3 -- There is an open and transparent public dialogue about the state of the protected areas | 1 | Through Partners’ Meeting under UNDP/GEF project |
|  | Institutional | Institutions are highly adaptive, responding effectively and immediately to change | 0 -- Institutions resist change; 1 -- Institutions do change but only very slowly; 2 -- Institutions tend to adapt in response to change but not always very effectively or with some delay; 3 -- Institutions are highly adaptive, responding effectively and immediately to change | 2 | To undergo planned restructuring to separate Environment and Climate Change with Forestry |
|  | Institutional | Institutions have effective internal mechanisms for monitoring, evaluation, reporting and learning | 0 -- There are no mechanisms for monitoring, evaluation, reporting or learning; 1 -- There are some mechanisms for monitoring, evaluation, reporting and learning but they are limited and weak; 2 -- Reasonable mechanisms for monitoring, evaluation, reporting and learning are in place but are not as strong or comprehensive as they could be; 3 -- Institutions have effective internal mechanisms for monitoring, evaluation, reporting and learning | 1 |  |
|  | Individual | Individuals are adaptive and continue to learn | 0 -- There is no measurement of performance or adaptive feedback; 1 -- Performance is irregularly and poorly measured and there is little use of feedback; 2 -- There is significant measurement of performance and some feedback but this is not as thorough or comprehensive as it might be; 3 -- Performance is effectively measured and adaptive feedback utilized | 1 |  |
|  |  |  | TOTAL Score (%) | 42 out of 96 (44%) |  |

2- Capacity Score for the Provincial Government of East Sepik

| Strategic Area of Support | Target for CD | Outcomes | Outcome Indicators (Scorecard) | Initial Evaluation | Evaluative Comments |
| --- | --- | --- | --- | --- | --- |
| 1. Capacity to conceptualize and formulate policies, legislations, strategies and programs |  |  |  |  |  |
|  | Systemic | The protected area agenda is being effectively championed / driven forward | 0 -- There is essentially no protected area agenda; 1 -- There are some persons or institutions actively pursuing a protected area agenda but they have little effect or influence; 2 -- There are a number of protected area champions that drive the protected area agenda, but more is needed; 3 -- There are an adequate number of able "champions" and "leaders" effectively driving forwards a protected area agenda | 1 |  |
|  | Systemic | There is a strong and clear legal mandate for the establishment and management of protected areas | 0 – There is no legal framework for protected areas; 1 – There is a partial legal framework for protected areas but it has many inadequacies; 2 – There is a reasonable legal framework for protected areas but it has a few weaknesses and gaps; 3 – There is a strong and clear legal mandate for the establishment and management of protected areas | 0 | Draft PA policy has not been formalized as yet. |
|  | Institutional | There is an institution responsible for protected areas able to strategize and plan (this is 2 issues - needs separating, 1 Systemic, 2 institutional) | 0 -- Protected area institutions have no plans or strategies; 1 -- Protected area institutions do have strategies and plans, but these are old and no longer up to date or were prepared in a totally top-down fashion; 2 -- Protected area institutions have some sort of mechanism to update their strategies and plans, but this is irregular or is done in a largely top-down fashion without proper consultation; 3 – Protected area institutions have relevant, participatorily prepared, regularly updated strategies and plans | 1 1 |  |
| 2. Capacity to implement policies, legislation, strategies and programs |  |  |  |  |  |
|  | Systemic | There are adequate skills for protected area planning and management | 0 -- There is a general lack of planning and management skills; 1-- Some skills exist but in largely insufficient quantities to guarantee effective planning and management; 2 -- Necessary skills for effective protected area management and planning do exist but are stretched and not easily available; 3 -- Adequate quantities of the full range of skills necessary for effective protected area planning and management are easily available | 1 | Provincial Officer has been involved with CEPA and CCDA since 2013. Still need more capacity development. |
|  | Systemic | There are protected area systems | 0 -- No or very few protected area exist and they cover only a small portion of the habitats and ecosystems; 1 -- Protected area system is patchy both in number and geographical coverage and has many gaps in terms of representativeness; 2 -- Protected area system is covering a reasonably representative sample of the major habitats and ecosystems, but still presents some gaps and not all elements are of viable size; 3 -- The protected areas include viable representative examples of all the major habitats and ecosystems of appropriate geographical scale | 1 |  |
|  | Systemic | There is a fully transparent oversight authority for the protected areas institutions | 0 -- There is no oversight at all of protected area institutions; 1 -- There is some oversight, but only indirectly and in a non-transparent manner; 2 -- There is a reasonable oversight mechanism in place providing for regular review but lacks in transparency (e.g. is not independent, or is internalized); 3 -- There is a fully transparent oversight authority for the protected areas institutions | 0 | Provincial Government is not explicitly mandated to provide oversight of PAs. |
|  | Institutional | Protected area institutions are effectively led | 0 -- Protected area institutions have a total lack of leadership; 1 -- Protected area institutions exist but leadership is weak and provides little guidance; 2 -- Some protected area institutions have reasonably strong leadership but there is still need for improvement; 3 -- Protected area institutions are effectively led | 0 | Provincial Government is not explicitly mandated to provide oversight of PAs. |
|  | Institutional | Protected areas have regularly updated, participatorily prepared, comprehensive management plans | 0 – Protected areas have no management plans; 1 – Some protected areas have up-to-date management plans but they are typically not comprehensive and were not participatorily prepared; 2 – Most Protected Areas have management plans though some are old, not participatorily prepared or are less than comprehensive; 3 – Every protected area has a regularly updated, participatorily prepared, comprehensive management plan | 0 |  |
|  | Institutional | Human resources are well qualified and motivated | 0 -- Human resources are poorly qualified and unmotivated; 1 -- Human resources qualification is spotty, with some well qualified, but many only poorly and in general unmotivated; 2 -- HR in general reasonably qualified, but many lack in motivation, or those that are motivated are not sufficiently qualified; 3 -- Human resources are well qualified and motivated. | 1 | Provincial Government HR has not catered for needed environment conservation staffs. |
|  | Institutional | Management plans are implemented in a timely manner effectively achieving their objectives | 0 -- There is very little implementation of management plans; 1 -- Management plans are poorly implemented and their objectives are rarely met; 2 -- Management plans are usually implemented in a timely manner, though delays typically occur and some objectives are not met; 3 -- Management plans are implemented in a timely manner effectively achieving their objectives | 1 | There are plans done annually but funding is needed for effective implementation of these Provincial Government work plans. |
|  | Institutional | Protected area institutions are able to adequately mobilize sufficient quantity of funding, human and material resources to effectively implement their mandate | 0 -- Protected area institutions typically are severely underfunded and have no capacity to mobilize sufficient resources; 1 -- Protected area institutions have some funding and are able to mobilize some human and material resources but not enough to effectively implement their mandate; 2 -- Protected area institutions have reasonable capacity to mobilize funding or other resources but not always in sufficient quantities for fully effective implementation of their mandate; 3 -- Protected area institutions are able to adequately mobilize sufficient quantity of funding, human and material resources to effectively implement their mandate | 0 | Provincial Officer needs additional capacity. |
|  | Institutional | Protected area institutions are effectively managed, efficiently deploying their human, financial and other resources to the best effect | 0 -- While the protected area institution exists it has no management; 1 -- Institutional management is largely ineffective and does not deploy efficiently the resources at its disposal; 2 -- The institution is reasonably managed, but not always in a fully effective manner and at times does not deploy its resources in the most efficient way; 3 -- The protected area institution is effectively managed, efficiently deploying its human, financial and other resources to the best effect | 1 | Provincial Officer needs additional staffs and funding to implement planned activities. |
|  | Institutional | Protected area institutions are highly transparent, fully audited, and publicly accountable | 0 -- Protected area institutions totally non-transparent, not being held accountable and not audited; 1 – Protected area institutions are not transparent but are occasionally audited without being held publicly accountable; 2 -- Protected area institutions are regularly audited and there is a fair degree of public accountability but the system is not fully transparent; 3 -- The Protected area institutions are highly transparent, fully audited, and publicly accountable | 0 |  |
|  | Institutional | There are legally designated protected area institutions with the authority to carry out their mandate | 0 -- There is no lead institution or agency with a clear mandate or responsibility for protected areas; 1 -- There are one or more institutions or agencies dealing with protected areas but roles and responsibilities are unclear and there are gaps and overlaps in the arrangements; 2 -- There are one or more institutions or agencies dealing with protected areas, the responsibilities of each are fairly clearly defined, but there are still some gaps and overlaps; 3 -- Protected Area institutions have clear legal and institutional mandates and the necessary authority to carry this out | 0 | Provincial Government is not explicitly mandated to provide oversight of PAs. |
|  | Institutional | Protected areas are effectively protected | 0 -- No enforcement of regulations is taking place; 1 -- Some enforcement of regulations but largely ineffective and external threats remain active; 2 -- Protected area regulations are regularly enforced but are not fully effective and external threats are reduced but not eliminated; 3 -- Protected Area regulations are highly effectively enforced and all external threats are negated | 1 |  |
|  | Individual | Individuals are able to advance and develop professionally | 0 -- No career tracks are developed and no training opportunities are provided; 1 -- Career tracks are weak and training possibilities are few and not managed transparently; 2 -- Clear career tracks developed and training available; HR management however has inadequate performance measurement system; 3 -- Individuals are able to advance and develop professionally | 1 | Provincial Government HR has not catered for Environment Conservation staff positions. |
|  | Individual | Individuals are appropriately skilled for their jobs | 0 -- Skills of individuals do not match job requirements; 1 -- Individuals have some or poor skills for their jobs; 2 -- Individuals are reasonably skilled but could further improve for optimum match with job requirement; 3 -- Individuals are appropriately skilled for their jobs | 0 |  |
|  | Individual | Individuals are highly motivated | 0 -- No motivation at all; 1 -- Motivation uneven, some are but most are not; 2 -- Many individuals are motivated but not all; 3 -- Individuals are highly motivated | 0 | There is only one Provincial Officer with many responsibilities. |
|  | Individual | There are appropriate systems of training, mentoring, and learning in place to maintain a continuous flow of new staff | 0 -- No mechanisms exist; 1 -- Some mechanisms exist but unable to develop enough and unable to provide the full range of skills needed; 2 -- Mechanisms generally exist to develop skilled professionals, but either not enough of them or unable to cover the full range of skills required; 3 -- There are mechanisms for developing adequate numbers of the full range of highly skilled protected area professionals | 1 |  |
| 3. Capacity to engage and build consensus among all stakeholders |  |  |  |  |  |
|  | Systemic | Protected areas have the political commitment they require | 0 -- There is no political will at all, or worse, the prevailing political will runs counter to the interests of protected areas; 1 -- Some political will exists, but is not strong enough to make a difference; 2 -- Reasonable political will exists, but is not always strong enough to fully support protected areas; 3 -- There are very high levels of political will to support protected areas | 1 | Governor of East Sepik, Grand Chief Sir Michael Somare has made commitments to ensuring that there is protection of the natural environment. No funding has been given as yet. |
|  | Systemic | Protected areas have the public support they require | 0 -- The public has little interest in protected areas and there is no significant lobby for protected areas; 1 -- There is limited support for protected areas; 2 -- There is general public support for protected areas and there are various lobby groups such as environmental NGO's strongly pushing them; 3 -- There is tremendous public support in the country for protected areas | 1 | PA support comes from people within the PAs and surrounding communities. |
|  | Institutional | Protected area institutions are mission oriented | 0 -- Institutional mission not defined; 1 -- Institutional mission poorly defined and generally not known and internalized at all levels; 2 -- Institutional mission well defined and internalized but not fully embraced; 3 – Institutional missions are fully internalized and embraced | 0 | Provincial Officer has Environment and Conservation as one of his responsibilities. |
|  | Institutional | Protected area institutions can establish the partnerships needed to achieve their objectives | 0 – Protected area institutions operate in isolation; 1 – Some partnerships in place but significant gaps and existing partnerships achieve little; 2 – Many partnerships in place with a wide range of agencies, NGOs etc, but there are some gaps, partnerships are not always effective and do not always enable efficient achievement of objectives; 3 – Protected area institutions establish effective partnerships with other agencies and institutions, including provincial and local governments, NGO’s and the private sector to enable achievement of objectives in an efficient and effective manner | 1 | CEPA and CCDA (Office of Climate Change) has included the Provincial Government since 2013. |
|  | Individual | Individuals carry appropriate values, integrity and attitudes | 0 -- Individuals carry negative attitude; 1 -- Some individuals have notion of appropriate attitudes and display integrity, but most don't; 2 -- Many individuals carry appropriate values and integrity, but not all; 3 -- Individuals carry appropriate values, integrity and attitudes | 1 |  |
| 4. Capacity to mobilize information and knowledge |  |  |  |  |  |
|  | Systemic | Protected area institutions have the information they need to develop and monitor strategies and action plans for the management of the protected area system | 0 -- Information is virtually lacking; 1 -- Some information exists, but is of poor quality, is of limited usefulness, or is very difficult to access; 2 -- Much information is easily available and mostly of good quality, but there remain some gaps in quality, coverage and availability; 3 -- Protected area institutions have the information they need to develop and monitor strategies and action plans for the management of the protected area system | 1 | Provincial Officer has limited information on the PAs in the Province. He has no information on the Torricelli Mountain Range. |
|  | Institutional | Protected area institutions have the information needed to do their work | 0 -- Information is virtually lacking; 1 -- Some information exists, but is of poor quality and of limited usefulness and difficult to access; 2 -- Much information is readily available, mostly of good quality, but there remain some gaps both in quality and quantity; 3 -- Adequate quantities of high quality up to date information for protected area planning, management and monitoring is widely and easily available | 1 | Provincial Officer has limited information on the PAs in the Province. He has no information on the Torricelli Mountain Range. |
|  | Individual | Individuals working with protected areas work effectively together as a team | 0 -- Individuals work in isolation and don't interact; 1 -- Individuals interact in limited way and sometimes in teams but this is rarely effective and functional; 2 -- Individuals interact regularly and form teams, but this is not always fully effective or functional; 3 -- Individuals interact effectively and form functional teams | 1 | CEPA and CCDA has involved the Provincial Officer since 2013. Prior to that there was no team work. |
| 5. Capacity to monitor, evaluate, report and learn |  |  |  |  |  |
|  | Systemic | Protected area policy is continually reviewed and updated | 0 – There is no policy or it is old and not reviewed regularly; 1 – Policy is only reviewed at irregular intervals; 2 – Policy is reviewed regularly but not annually; 3 – National protected areas policy is reviewed annually | 0 | Draft PA Policy has not been formalized as yet. |
|  | Systemic | Society monitors the state of protected areas | 0 -- There is no dialogue at all; 1 -- There is some dialogue going on, but not in the wider public and restricted to specialized circles; 2 -- There is a reasonably open public dialogue going on but certain issues remain taboo; 3 -- There is an open and transparent public dialogue about the state of the protected areas | 1 |  |
|  | Institutional | Institutions are highly adaptive, responding effectively and immediately to change | 0 -- Institutions resist change; 1 -- Institutions do change but only very slowly; 2 -- Institutions tend to adapt in response to change but not always very effectively or with some delay; 3 -- Institutions are highly adaptive, responding effectively and immediately to change | 1 |  |
|  | Institutional | Institutions have effective internal mechanisms for monitoring, evaluation, reporting and learning | 0 -- There are no mechanisms for monitoring, evaluation, reporting or learning; 1 -- There are some mechanisms for monitoring, evaluation, reporting and learning but they are limited and weak; 2 -- Reasonable mechanisms for monitoring, evaluation, reporting and learning are in place but are not as strong or comprehensive as they could be; 3 -- Institutions have effective internal mechanisms for monitoring, evaluation, reporting and learning | 1 | Provincial Government has their own monitoring and evaluation mechanisms but these are not effective due to funding difficulty. |
|  | Individual | Individuals are adaptive and continue to learn | 0 -- There is no measurement of performance or adaptive feedback; 1 -- Performance is irregularly and poorly measured and there is little use of feedback; 2 -- There is significant measurement of performance and some feedback but this is not as thorough or comprehensive as it might be; 3 -- Performance is effectively measured and adaptive feedback utilized | 1 |  |
|  |  |  | TOTAL Score (%) | 22 out of 96 (23%) |  |

3- Capacity Score for the Provincial Government of Simbu

| Strategic Area of Support | Target for CD | Outcomes | Outcome Indicators (Scorecard) | Initial Evaluation | Evaluative Comments |
| --- | --- | --- | --- | --- | --- |
| 1. Capacity to conceptualize and formulate policies, legislations, strategies and programs |  |  |  |  |  |
|  | Systemic | The protected area agenda is being effectively championed / driven forward | 0 -- There is essentially no protected area agenda; 1 -- There are some persons or institutions actively pursuing a protected area agenda but they have little effect or influence; 2 -- There are a number of protected area champions that drive the protected area agenda, but more is needed; 3 -- There are an adequate number of able "champions" and "leaders" effectively driving forwards a protected area agenda | 1 |  |
|  | Systemic | There is a strong and clear legal mandate for the establishment and management of protected areas | 0 -- There is no legal framework for protected areas; 1 -- There is a partial legal framework for protected areas but it has many inadequacies; 2 – There is a reasonable legal framework for protected areas but it has a few weaknesses and gaps; 3 -- There is a strong and clear legal mandate for the establishment and management of protected areas | 0 |  |
|  | Institutional | There is an institution responsible for protected areas able to strategize and plan (this is 2 issues - needs separating, 1 Systemic, 2 institutional) | 0 -- Protected area institutions have no plans or strategies; 1 -- Protected area institutions do have strategies and plans, but these are old and no longer up to date or were prepared in a totally top-down fashion; 2 -- Protected area institutions have some sort of mechanism to update their strategies and plans, but this is irregular or is done in a largely top-down fashion without proper consultation; 3 – Protected area institutions have relevant, participatorily prepared, regularly updated strategies and plans | 1 |  |
| 2. Capacity to implement policies, legislation, strategies and programs |  |  |  |  |  |
|  | Systemic | There are adequate skills for protected area planning and management | 0 -- There is a general lack of planning and management skills; 1-- Some skills exist but in largely insufficient quantities to guarantee effective planning and management; 2 -- Necessary skills for effective protected area management and planning do exist but are stretched and not easily available; 3 -- Adequate quantities of the full range of skills necessary for effective protected area planning and management are easily available | 0 | There is no officer responsible for environment conservation in the Province. |
|  | Systemic | There are protected area systems | 0 -- No or very few protected areas exist and they cover only a small portion of the habitats and ecosystems; 1 -- Protected area system is patchy both in number and geographical coverage and has many gaps in terms of representativeness; 2 -- Protected area system is covering a reasonably representative sample of the major habitats and ecosystems, but still presents some gaps and not all elements are of viable size; 3 -- The protected areas include viable representative examples of all the major habitats and ecosystems of appropriate geographical scale | 1 | Negative experience with Crater Mountain |
|  | Systemic | There is a fully transparent oversight authority for the protected areas institutions | 0 -- There is no oversight at all of protected area institutions; 1 -- There is some oversight, but only indirectly and in a non-transparent manner; 2 -- There is a reasonable oversight mechanism in place providing for regular review but lacks in transparency (e.g. is not independent, or is internalized); 3 -- There is a fully transparent oversight authority for the protected areas institutions | 0 | There is no officer responsible for PAs within the province |
|  | Institutional | Protected area institutions are effectively led | 0 -- Protected area institutions have a total lack of leadership; 1 -- Protected area institutions exist but leadership is weak and provides little guidance; 2 -- Some protected area institutions have reasonably strong leadership but there is still need for improvement; 3 -- Protected area institutions are effectively led | 0 |  |
|  | Institutional | Protected areas have regularly updated, participatorily prepared, comprehensive management plans | 0 -- Protected areas have no management plans; 1 -- Some protected areas have up-to-date management plans but they are typically not comprehensive and were not participatorily prepared; 2 -- Most Protected Areas have management plans though some are old, not participatorily prepared or are less than comprehensive; 3 -- Every protected area has a regularly updated, participatorily prepared, comprehensive management plan | 0 | There is no officer at present with environment conservation responsibilities. |
|  | Institutional | Human resources are well qualified and motivated | 0 -- Human resources are poorly qualified and unmotivated; 1 -- Human resources qualification is spotty, with some well qualified, but many only poorly and in general unmotivated; 2 -- HR in general reasonably qualified, but many lack in motivation, or those that are motivated are not sufficiently qualified; 3 -- Human resources are well qualified and motivated. | 1 |  |
|  | Institutional | Management plans are implemented in a timely manner effectively achieving their objectives | 0 -- There is very little implementation of management plans; 1 -- Management plans are poorly implemented and their objectives are rarely met; 2 -- Management plans are usually implemented in a timely manner, though delays typically occur and some objectives are not met; 3 -- Management plans are implemented in a timely manner effectively achieving their objectives | 0 | There is no officer at present with environment conservation responsibilities. |
|  | Institutional | Protected area institutions are able to adequately mobilize sufficient quantity of funding, human and material resources to effectively implement their mandate | 0 -- Protected area institutions typically are severely underfunded and have no capacity to mobilize sufficient resources; 1 -- Protected area institutions have some funding and are able to mobilize some human and material resources but not enough to effectively implement their mandate; 2 -- Protected area institutions have reasonable capacity to mobilize funding or other resources but not always in sufficient quantities for fully effective implementation of their mandate; 3 -- Protected area institutions are able to adequately mobilize sufficient quantity of funding, human and material resources to effectively implement their mandate | 1 |  |
|  | Institutional | Protected area institutions are effectively managed, efficiently deploying their human, financial and other resources to the best effect | 0 -- While the protected area institution exists it has no management; 1 -- Institutional management is largely ineffective and does not deploy efficiently the resources at its disposal; 2 -- The institution is reasonably managed, but not always in a fully effective manner and at times does not deploy its resources in the most efficient way; 3 -- The protected area institution is effectively managed, efficiently deploying its human, financial and other resources to the best effect | 1 |  |
|  | Institutional | Protected area institutions are highly transparent, fully audited, and publicly accountable | 0 -- Protected area institutions totally non-transparent, not being held accountable and not audited; 1 – Protected area institutions are not transparent but are occasionally audited without being held publicly accountable; 2 -- Protected area institutions are regularly audited and there is a fair degree of public accountability but the system is not fully transparent; 3 -- The Protected area institutions are highly transparent, fully audited, and publicly accountable | 0 |  |
|  | Institutional | There are legally designated protected area institutions with the authority to carry out their mandate | 0 -- There is no lead institution or agency with a clear mandate or responsibility for protected areas; 1 -- There are one or more institutions or agencies dealing with protected areas but roles and responsibilities are unclear and there are gaps and overlaps in the arrangements; 2 -- There are one or more institutions or agencies dealing with protected areas, the responsibilities of each are fairly clearly defined, but there are still some gaps and overlaps; 3 -- Protected Area institutions have clear legal and institutional mandates and the necessary authority to carry this out | 1 | CEPA is the lead agency for PAs but they have not worked in the Province |
|  | Institutional | Protected areas are effectively protected | 0 -- No enforcement of regulations is taking place; 1 -- Some enforcement of regulations but largely ineffective and external threats remain active; 2 -- Protected area regulations are regularly enforced but are not fully effective and external threats are reduced but not eliminated; 3 -- Protected Area regulations are highly effectively enforced and all external threats are negated | 1 |  |
|  | Individual | Individuals are able to advance and develop professionally | 0 -- No career tracks are developed and no training opportunities are provided; 1 -- Career tracks are weak and training possibilities are few and not managed transparently; 2 -- Clear career tracks developed and training available; HR management however has inadequate performance measurement system; 3 -- Individuals are able to advance and develop professionally | 0 | There is no Provincial Officer with Environment Conservation responsibilities at present. |
|  | Individual | Individuals are appropriately skilled for their jobs | 0 – Skills of individuals do not match job requirements; 1 – Individuals have some or poor skills for their jobs; 2 – Individuals are reasonably skilled but could further improve for optimum match with job requirement; 3 – Individuals are appropriately skilled for their jobs | 0 | There is no Provincial Officer with Environment Conservation responsibilities at present. |
|  | Individual | Individuals are highly motivated | 0 – No motivation at all; 1 – Motivation uneven, some are but most are not; 2 – Many individuals are motivated but not all; 3 – Individuals are highly motivated | 1 |  |
|  | Individual | There are appropriate systems of training, mentoring, and learning in place to maintain a continuous flow of new staff | 0 – No mechanisms exist; 1 – Some mechanisms exist but unable to develop enough and unable to provide the full range of skills needed; 2 – Mechanisms generally exist to develop skilled professionals, but either not enough of them or unable to cover the full range of skills required; 3 – There are mechanisms for developing adequate numbers of the full range of highly skilled protected area professionals | 1 |  |
| 3. Capacity to engage and build consensus among all stakeholders |  |  |  |  |  |
|  | Systemic | Protected areas have the political commitment they require | 0 – There is no political will at all, or worse, the prevailing political will runs counter to the interests of protected areas; 1 – Some political will exists, but is not strong enough to make a difference; 2 – Reasonable political will exists, but is not always strong enough to fully support protected areas; 3 – There are very high levels of political will to support protected areas | 1 | There is some political will but more needs to be done to assist Mt. Wilhelm and Crater Mountain |
|  | Systemic | Protected areas have the public support they require | 0 -- The public has little interest in protected areas and there is no significant lobby for protected areas; 1 -- There is limited support for protected areas; 2 -- There is general public support for protected areas and there are various lobby groups such as environmental NGO's strongly pushing them; 3 -- There is tremendous public support in the country for protected areas | 1 |  |
|  | Institutional | Protected area institutions are mission oriented | 0 – Institutional mission not defined; 1 – Institutional mission poorly defined and generally not known and internalized at all levels; 2 – Institutional mission well defined and internalized but not fully embraced; 3 – Institutional missions are fully internalized and embraced | 0 | Nothing as yet from the Provincial Government. |
|  | Institutional | Protected area institutions can establish the partnerships needed to achieve their objectives | 0 -- Protected area institutions operate in isolation; 1 -- Some partnerships in place but significant gaps and existing partnerships achieve little; 2 -- Many partnerships in place with a wide range of agencies, NGOs etc, but there are some gaps, partnerships are not always effective and do not always enable efficient achievement of objectives; 3 -- Protected area institutions establish effective partnerships with other agencies and institutions, including provincial and local governments, NGO's and the private sector to enable achievement of objectives in an efficient and effective manner | 1 | Work is led by NGOs |
|  | Individual | Individuals carry appropriate values, integrity and attitudes | 0 -- Individuals carry negative attitude; 1 -- Some individuals have notion of appropriate attitudes and display integrity, but most don't; 2 -- Many individuals carry appropriate values and integrity, but not all; 3 -- Individuals carry appropriate values, integrity and attitudes | 1 |  |
| 4. Capacity to mobilize information and knowledge |  |  |  |  |  |
|  | Systemic | Protected area institutions have the information they need to develop and monitor strategies and action plans for the management of the protected area system | 0 -- Information is virtually lacking; 1 -- Some information exists, but is of poor quality, is of limited usefulness, or is very difficult to access; 2 -- Much information is easily available and mostly of good quality, but there remain some gaps in quality, coverage and availability; 3 -- Protected area institutions have the information they need to develop and monitor strategies and action plans for the management of the protected area system | 1 | Information on PAs within the province with NGOs. |
|  | Institutional | Protected area institutions have the information needed to do their work | 0 -- Information is virtually lacking; 1 -- Some information exists, but is of poor quality and of limited usefulness and difficult to access; 2 -- Much information is readily available, mostly of good quality, but there remain some gaps both in quality and quantity; 3 -- Adequate quantities of high quality up to date information for protected area planning, management and monitoring is widely and easily available | 1 | Provincial Government does not have the needed PA information to do their work. |
|  | Individual | Individuals working with protected areas work effectively together as a team | 0 -- Individuals work in isolation and don't interact; 1 -- Individuals interact in limited way and sometimes in teams but this is rarely effective and functional; 2 -- Individuals interact regularly and form teams, but this is not always fully effective or functional; 3 -- Individuals interact effectively and form functional teams | 1 | CEPA and UNDP may be working with Provincial team. |
| 5. Capacity to monitor, evaluate, report and learn |  |  |  |  |  |
|  | Systemic | Protected area policy is continually reviewed and updated | 0 -- There is no policy or it is old and not reviewed regularly; 1 -- Policy is only reviewed at irregular intervals; 2 -- Policy is reviewed regularly but not annually; 3 -- National protected areas policy is reviewed annually | 0 | Draft PA Policy has not been formalized as yet. |
|  | Systemic | Society monitors the state of protected areas | 0 -- There is no dialogue at all; 1 -- There is some dialogue going on, but not in the wider public and restricted to specialized circles; 2 -- There is a reasonably open public dialogue going on but certain issues remain taboo; 3 -- There is an open and transparent public dialogue about the state of the protected areas | 1 |  |
|  | Institutional | Institutions are highly adaptive, responding effectively and immediately to change | 0 -- Institutions resist change; 1 -- Institutions do change but only very slowly; 2 -- Institutions tend to adapt in response to change but not always very effectively or with some delay; 3 -- Institutions are highly adaptive, responding effectively and immediately to change | 1 |  |
|  | Institutional | Institutions have effective internal mechanisms for monitoring, evaluation, reporting and learning | 0 -- There are no mechanisms for monitoring, evaluation, reporting or learning; 1 -- There are some mechanisms for monitoring, evaluation, reporting and learning but they are limited and weak; 2 -- Reasonable mechanisms for monitoring, evaluation, reporting and learning are in place but are not as strong or comprehensive as they could be; 3 -- Institutions have effective internal mechanisms for monitoring, evaluation, reporting and learning | 0 |  |
|  | Individual | Individuals are adaptive and continue to learn | 0 -- There is no measurement of performance or adaptive feedback; 1 -- Performance is irregularly and poorly measured and there is little use of feedback; 2 -- There is significant measurement of performance and some feedback but this is not as thorough or comprehensive as it might be; 3 -- Performance is effectively measured and adaptive feedback utilized | 0 | There is no Provincial Officer with PA responsibilities. |
|  |  |  | TOTAL Score (%) | 19 out of 96 (20%) |  |

This estimate is derived from the 2011 estimate of 7.06 million coupled with estimated population growth rates; with estimated 2016 population from World Bank. (2018) Data - Papua New Guinea, http://databank.worldbank.org/data/reports.aspx?source=2&country=PNG,  Accessed 26/1/2017.

National Statistical Office PNG. (2015) 2009-2010 Papua New Guinea houshold income and expenditure survey, summary tables. National Statistical Office PNG,, Port Moresby.

World Bank Group. (2017) Papua New Guinea Economic Update December  2017: Reinforcing Resilience. World Bank Group.

For example, health statistics are sobering even though PNG spends more than other comparative countries on health. While the situation is improving steadily, the rates of child malnutrition are among the highest in the world. Only 53% of births have a skilled attendant, and 57 babies in every 1000 die before their fifth birthday Ibid.

National Statistical Office PNG. (2015) 2009-2010 Papua New Guinea houshold income and expenditure survey, summary tables. National Statistical Office PNG,, Port Moresby.

Allison A. & Tallowin O. (2015) Occurrence and Status of Papua New Guinea Vertebrates. In: The State of the Forests of Papua New Guinea 2014: Measuring change over the period 2002-2014 (eds J. E. Bryan and P. L. Shearman). University of Papua New Guinea, Port Moresby

IUCN Species Survival Commission. (2017) The IUCN Red List of Threatened Species. Version 2016-3, www.iucnredlist.org,  Accessed 30 /1/2017.

It is interesting to note that New Guinea is not listed as a Vavilov Centre of Crop Diversity – primarily because Nikolai Vavilov carried out much of his work before much scientific exploration had been carried out on the island of New Guinea.

Commonly described elsewhere as slash-and-burn or shifting agriculture

Mack & West, 2005

This estimate is derived from the 2011 estimate of 7.06 million coupled with estimated population growth rates

Though allocated for agriculture, this areas are firstly a focus of logging and clearing. Bryan J.; Shearman P.; Aoro G.; Wavine F. & Zerry J. (2015) The current state of PNG’s forests and changes between 2002 & 2014. In: The State of the Forests of Papua New Guinea 2014: Measuring change over the period 2002-2014 (eds J. E. Bryan and P. L. Shearman). University of Papua New Guinea, Port Moresby.

The new Protected Areas Bill will not permit developments of plantations or mining, so any existing leases may need to be surrendered or purchased by the government. This process will occur during a five-year transition phase.

In 2016, the PNG Government committed to cancel all SABLs, but this has yet to occur.

Makareiva, A.K. & V.G. Gorshkov (2015) Large-scale climatic significance of Papua New Guinea forests. In The State of the Forests of Papua New Guinea: Measuring change over period 2002-2014 (eds. J.E. Bryan & P.L. Shearman). University of Papua New Guinea, Port Moresby, Papua New Guinea.

Government of Papua New Guinea. (2016) Intended Nationally Determined Contribution (INDC) Under the United Nations Framework Convention on Climate Change -agreed to become the NDC.

Butler J. R. A.; Skewes T.; Mitchell D.; Pontio M. & Hills T. (2014) Stakeholder perceptions of ecosystem service declines in Milne Bay, Papua New Guinea: Is human population a more critical driver than climate change? Marine Policy 46, 1-14.

Freeman B. G. & Class Freeman A. M. (2014) Rapid upslope shifts in New Guinean birds illustrate strong distributional responses of tropical montane species to global warming. Proceedings of the National Academy of Sciences 111, 4490-4.  10.1073/pnas.1318190111.

Government of Papua New Guinea. (2015) National Marine Conservation Assessment for Papua New Guinea Conservation and Environment Protection Authority.

Department of National Planning and Monitoring. (2014) National Strategy for Responsible Sustainable Development for Papua New Guinea. 2nd edition. Department of National Planning and Monitoring, Government of Papua New Guinea.

Government of Papua New Guinea. (2010) PNG Marine Program on Coral Reefs, Fisheries and Food Security 2010 – 2013. Coral Triangle Initiative.

Indeed, in GEF’s own GEF-6 Programming Directions, there is acknowledgement that the establishment and management of protected area systems across the globe has arguably been the GEF’s greatest achievements.

Independent State of Papua New Guinea. (2014) Papua New Guinea Policy on Protected Areas.  (ed Conservation and Environment Protection Authority), Waigani, National Capital District, Papua New Guinea.

Most importantly, Alcorn, J.B. & Beehler, B.M. (1993) Papua New Guinea Conservation Needs Assessment (two volumes). Government of Papua New Guinea (Department of Environment and Conservation) & The Biodiversity Support Program, Washington D.C.; Nix, H. et al. (2000) The BioRap Toolbox - A national study of biodiversity assessment and planning for Papua New Guinea. Australian National University, Canberra, Australia.  More recent studies include examples such as Allison, A. and O. Tallowin (2015) Distribution, Diversity and Conservation Status of the Biota of New Britain; Adams V. M.; Tulloch V. J. & Possingham H. P. (2017) Land-sea conservation assessment for Papua New Guinea. A report on the work undertaken to fulfil the terms of the project Review and Integration of the Terrestrial and Marine Program of Works on Protected Areas. University of Queensland, PNG Conservation and Environment Protection Authority, Government of Papua New Guinea. (2015) National Marine Conservation Assessment for Papua New Guinea Conservation and Environment Protection Authority, Lipsett-Moore G.; Game E.; Peterson N.; Saxon E.; Sheppard S.; Allison A.; Michael J.; Singadan R.; Sabi J.; Kula G. & Gwaibo R. (2010) Interim National Terrestrial Conservation Assessment for Papua New Guinea: Protecting Biodiversity in a Changing Climate. In: Pacific Island Countries Report No. 1/2010. Papua New Guinea Department of Environment and Conservation, The Nature Conservancy, UNDP

This is with the exception of catastrophic events – such as floods or droughts – that lead to loss of crops or assets; climate change may exacerbate such events, both in terms of frequency but also intensity.  During such periods, people’s dependence on natural resources increases.

On the contrary, it is likely, however, that there are nutritional limitations and environmental health issues among groups of people in the country; these factors remain beyond the scope of the current project although future projects may take such factors into account.  In addition, the perception that resource conservation is of a lesser import may simply be fueled by the people’s perception that they have more important and pressing needs (including, for example, access to good healthcare and education).

Source: Compiled from the CEPA database on protected areas Conservation and Environment Protection Authority. (2017) Database of protected areas. Port Moresby.

Source: Leverington F.; Peterson A. & Peterson G. (2017) Papua New Guinea Management Effectiveness Evaluation of Protected Areas. SPREP/ CEPA/UNDP, Samoa.

Conservation and Environmental Protection Authority Act 2014, No. 9 of 2014, Certified on 30 May 2014.

But most authors also suggest that it also refers to other laws, including: Fauna Protection Act 1966 (Amended 1974,1976), Crocodile (Trade Protection) Act 1973, International Trade of Endangered Species (Fauna & Flora) Act 1978 (Amended 2003)

Of the functions described in the Act, these are the most pertinent, as they relate (albeit obliquely) to protected areas.

Independent State of Papua New Guinea, (2014), Papua New Guinea Policy on Protected Areas. Conservation & Environment Protection Authority, October 2014, Waigani, National Capital District, Papua New Guinea

See Appendix 3 (on pg 76) of the Policy.

Through the PPG process, it was apparent that the country was effectively bankrupt – salaries are not being paid, budgets are not being fulfilled; CEPA moved offices during the PPG process for non-payment of rent.

The CI/WB/GEF project included a GEF grant of USD 17 million of which USD 10 million was allocated to capitalise the Mama Graun Conservation Trust Fund.  The project was closed on 04 October 2006 (thus, two years early) as a result of embezzlement and corruption.  The initial funds to capitalise Mama Graun have now long been exhausted. Since this time, Mama Graun no longer acts as a “Trust Fund” but rather as an NGO, relying, on an annual basis, on raising funds and dispersing or using those funds for a series of projects.

Leverington F.; Peterson A. & Peterson G. (2017) Papua New Guinea Management Effectiveness Evaluation of Protected Areas. SPREP/ CEPA/UNDP, Samoa

See worksheets associated with the Finance Scorecard Tracking Tool.

Specifically, the project will contribute to the achievement of all six goals of the NBSAP, under the goals, the project will contribute to two (of three) Priority 1 programmes (Financial and Technical Resources, and Human Capacities) and Access and Benefit Sharing, and in situ biodiversity conservation (Priority 2), Research and Information Sharing (Priority 3) – and to a lesser extent to Priority 4 and the final priority (on monitoring and evaluation.

Fiona Leverington, Ann Peterson, Gregory Peterson, 2017, Methodology for assessment of protected area management effectiveness in Papua New Guinea’s Protected Areas, SPREP, Apia, Samoa

For example, see Adams, V., V. Tulloch & H. Possingham (2016) Land-sea conservation assessment for Papua New Guinea, 2016. University of Queensland; Allison, A. & O. Tallowin (2015) Distribution, Diversity and Conservation Status of the Biota of New Britain; Faith, D. P., Margules, C. R. and Walker, P. A., (2001) A biodiversity conservation plan for Papua New Guinea based on biodiversity trade-offs analysis. Pacific Conservation Biology 6: 304-324; Swartzendruber, J.F. (1993) Papua New Guinea Conservation Needs Assessment Synopsis Report. Biodiversity Support Program (USAID, WWF, TNC, WRI) and DEC; McCallum, R. & Sekhran, N. (1997) Race for the rainforest: Evaluating Lessons from an Integrated Conservation and Development "Experiment" in New Ireland, Papua New Guinea. PNG Biodiversity Conservation and Resource Management Programme

The two ongoing UNDP-GEF projects are the GEF-5 project “R2R Strengthening Management Effectiveness of the National System of Protected Areas” and the GEF-4 project “PAS: Community-Based Forest and Coastal Conservation and Resource Management in PNG”

Held on 17 May 2017; see Annex F for a list of the participants.

Held on 29 November 2017, see Annex F for a list of the participants.

The sites were selected on the basis of a series of meetings: i) six sites were selected and listed in the PIF, ii) following the commencement of the PPG process, a further two sites were added to make a long list of eight sites.  On 29 May 2017, the PPG consultants provided a list of criteria by which the pilot sites were to be selected from the long list – including the key criterion that “Each of the pilot sites requires some investment that will catalyse a site-based system that generates income for the protected area”.  On 11 July 2017 and as a result of a series of meetings held in CEPA, three sites were selected for initial investment by the project.  See Annex G for the documentation of the process.

Indeed, it is for these reasons that the METT is not feasible for the majority of protected areas in PNG.

However, the project will focus on the core area of the Sepik Wetlands – and area of 1.5 million ha – essentially the area inhabited by the saltwater crocodile (Crocodylus porosus) – thus, the middle and upper Sepik; in the longer term, the lower Sepik would become involved and included.

See the impacts of the Ok Tedi mine disaster for potential impacts – when an estimated two billion tons of untreated mining waste spilled into the Ok Tedi river; the real impacts include the planned development of a hydroelectric dam.

The establishment of protected areas is a complicated process because the spatial scales over which natural resource use and management occurs differs depending on any given resource being considered.  For example, women collect fuelwood from a discrete area, but they also collect water from communal sources; crocodile eggs are harvested from a different area, but no less well defined or discrete.  In short, the areas and natural resources found therein will define the scale of the protected areas.  The establishment of protected areas (as community conservation areas) should occur at a scale defined by the people themselves through an inclusive and participatory process.  This will result in a mosaic of protected areas which, ultimately, will cover the entirety of the Sepik Wetlands.

See http://baloun.entu.cas.cz/png/mtwilhelm/

This is primarily as a result of the success of the community oil palm scheme (which are essentially oil palm outgrowers schemes) – meaning that local people that live in the coastal areas of Kimbe Bay are much less dependent on natural resources (see Koczberski, G. et al. (2006) Village-based marine resource use and rural livelihoods in Kimbe Bay, West New Britain, Papua New Guinea. Report prepared for The Nature Conservancy. TNC Pacific Island Countries Report No. 5/06. 128pp).

The LMMAs were established between 2006 – 2009 under the guidance of TNC.  However, as described in Section II, they were established on the basis of the concept of diminishing resources, which, for various reasons, was of a lesser concern to the people involved and, as a result, they were not embraced.  There is an initiative to revive the LMMAs with the formation of a new coordination body

See, for example, https://mahonianadari.org/research/research-conducted/ and https://www.jcu.edu.au/courses-and-study/courses/master-of-science-in-marine-biology-and-ecology

This is written in full acknowledgement of the contribution of knowledge and information, some of which is world-class and some of which has had global implications. Nonetheless, there has been no financial contribution (e.g., in the form of research fees akin to those collected by the BRC for the Wanang WMA).

Global IBA Criteria: http://datazone.birdlife.org/site/ibacritglob [Note: informally assessed against the full criteria: A1-Globally threatened species; A2 – Restricted-range species; A3- Biome-restricted species; A4-Congregations;

Global KBA criteria: www.keybiodiversityareas.org [Note: informally assessed against the following criteria: A1 Threatened biodiversity; B Geographically restricted biodiversity]

There is a little confusion in the literature regarding the actual identity of the plant involved with at least two plants with the common (or local) name of massoi or massoia (Cryptocaria massoia and Cinnamomum xanthoneuron); massoi bark has also been confused with lawang bark.

Noting that i) eaglewood or gaharu (called agarwood elsewhere) refers to Aquilaria spp. and that all Aquilaria spp. are listed on CITES Appendix II and ii) in its purest form per unit weight, it is one of the most expensive natural raw matierals in the world with an estimated USD 6-8 million annual market at present.

Using a METT that has specifically been adapted for use in PNG – the “METT for PNG”.  In recognition that the use of the ‘original’ METT in PNG was both inappropriate and damaging, a first attempt to amend it was undertaken under the GEF-4 project in PNG.  However, many issues linger even in this adapted METT and further adaptation is necessary (see Output 1.3 and Annex H).

Such an inclusive and participatory piece of work – to assess and map the mandates of the institutions and organizations involved in protected area management has not and will not be carried out under the ongoing GEF-4 or GEF-5 projects.

The Project Manager’s TOR has technical functions relating to institution building and capacity development (see Annex D). S/he will be expected to spend 10% of his/her time on Output 1.1 and 1.3.

The pricing strategies are usually dependent on the following parameters: cost recovery; market rate; willingness to pay; re-investment in improving the facilities and their management; and demand management

See https://www.african-parks.org

A capacity assessment has been undertaken and based on the results of the CA, project interventions have focused on improving practical skills on project and financial management for non-government and community-based organization. A systematic approach on capacity development is currently implemented under GEF5 - a PNG Competence Register based on the recommended IUCN format (Appleton 2017) to facilitate the professionalization of protected area management within CEPA/Sustainable Environment Program wing and to enhance the competence of its staff and key stakeholders to provide effective planning and management of PNG’s PAs. Training sessions revolved around 3 broad competencies: a) planning, management and administration; b) applied protected area management; and c) general personal competences.

This also should be considered in the context in which the original METT was developed – which was for state-centric protected area systems in which the majority of protected areas were state owned and IUCN Cat II. It was not developed for community conservation areas.  This is the reason that few, if any, of the community conservation areas in the world are using the METT as their tool to measure management effectiveness.

This also would not be the first time that the METT would be adapted for unique circumstances.  For example, WWF-Russia went through the process of adapting the METT for the special circumstances of zapovedniks (or IUCN Cat I Strict Nature Areas) for use in ex-Soviet Republics including the Russian Federation.

Leverington et al., Pers. comm.

METT ILs GEF Indigenous.doc

https://undpgefpims.org/project-attachment?projectId=3600

This may be on the basis of existing proposals and partnership that include CEPA, UPNG, the Lae Herbarium, the New Guinea Binatang Research Centre – as well as external partners such as Bishops Museum and James Cook University.

For example, GEF evaluation of experience with conservation trust funds (1998).

The PPG process took place at a time when the PA Bill was going through the process to be approved by the NEC. In addition, some of the regulations associated with the Bill were also in the process of being developed.  However, while stakeholders are positive that it will be enacted, there were uncertainties and the regulations may not provide all the necessary aspects for implementation and achievement of this project’s outcomes and objective – including, for example, securing public benefit status for the Biodiversity Fund for tax exemption purposes and any other aspects of the legal establishment of the Biodiversity Fund.

Conservation Finance Alliance. 2008. Rapid Review of Conservation Trust Funds.

See Spergel & Mikitin (2013) Practice Standards for Conservation Trust Funds.

The MPTF manages a portfolio of over USD 9.3 billion and is also managing a number of other Funds for conservation – examples include the Central African Forest Initiative (with a value of USD 84.4 million see http://mptf.undp.org/factsheet/fund/AFI00), UN REDD Programme Fund (with a value of approximately USD 290 million, see http://mptf.undp.org/factsheet/fund/CCF00), the UN REDD Viet Nam Phase II MPTF (with a value of over USD 26.4 million, see http://mptf.undp.org/factsheet/fund/VNM00), the DRC Fonds National REDD+ (with a value of USD 120 million, see http://mptf.undp.org/factsheet/fund/3CD00), and the Joint Program Promoting Gender-Responsive Approaches to Natural Resource Management for Peacebuilding (with a value of USD 554,000, see http://mptf.undp.org/factsheet/fund/JXD00).  The MPTF also already manages the PNG UN Trust Fund – a Fund with a value of USD 93.6 million (see http://mptf.undp.org/factsheet/fund/PG100) – and as such, there is a precedent for the use of the MPTF as a vehicle in the country.

This only makes sense if the capitalization of the Trust Fund is of a sufficient value to pay for their costs as a custodian of the TF, which is not yet the case here.

This will be done by, where possible, building on the documents that already exist – e.g., those used by the Mama Graun Conservation Trust Fund.

See Annex H for details.

The majority of potential donors and benefactors stated that not only would they, in principle, be happy to contribute to the fund but, indeed, that it would be a matter of principle to do so.

Given the current fiscal situation of the government after the devastating earthquake of 26 February 2018, the government will not be able to frontload its contribution to the Fund. Instead, the cash contribution is expected to come through by the 4th year of the project when the ground works are completed and the Fund has been established with support from MPTFO and other independent entities as necessary.

See the Sustainable Finance Tracking Tool.

It is interesting to recognize that the CEPF’s programme in the East Melanesian Islands Hotspot is for eight years – rather than the usual five-year investment.  This vindicates the decision by the PPG team to extend the GEF-6 project’s duration from the original five years to the currently proposed seven years.

It has been reflected in both the STAP and the GEF Council reviews of the PIF.

KfW – derived from Kreditanstalt für Wiederaufbau is the German Development Bank.

See https://www.farmafrica.org/ethiopia/making-forests-pay and https://www.farmafrica.org/downloads/farm-africas-approach-on-pfm.pdf

See http://www.undp.org/content/undp/en/home/operations/transparency/information_disclosurepolicy/

See https://www.thegef.org/gef/policies_guidelines

Integrated Results and Resources Framework of the UNDP Strategic Plan, 2018-21 (draft 23 October 2017).

Baseline, mid-term and end of project target levels must be expressed in the same neutral unit of analysis as the corresponding indicator. Baseline is the current/original status or condition and need to be quantified. The baseline must be established before the project document is submitted to the GEF for final approval. The baseline values will be used to measure the success of the project through implementation monitoring and evaluation.

Target is the change in the baseline value that will be achieved by the mid-term review and then again by the terminal evaluation.

Data collection methods should outline specific tools used to collect data and additional information as necessary to support monitoring. The PIR cannot be used as a source of verification.

The scoring system here has been adapted from the Mainstreaming Biodiversity Tracking Tool (GEF 6 Objective 4, Program 9)

Represent the average METT scores for 5 LMMAs in Kimbe Bay

See https://www.thegef.org/gef/policies_guidelines

See https://www.thegef.org/gef/gef_agencies

See guidance here:  https://info.undp.org/global/popp/frm/pages/financial-management-and-execution-modalities.aspx

Excluding project team staff time and UNDP staff time and travel expenses.

The costs of UNDP Country Office and UNDP-GEF Unit’s participation and time are charged to the GEF Agency Fee.

This should be a two-way relationship, with UNDP making commitments to ensure outstanding communication with partners and to ensure that there are no unjustifiable bureaucratic delays to processes.

By making the UNDP RR as the Chair of the dispute mechanism, it will ensure that s/he is always aware of the issues facing the project and in order to minimize the demand on this person’s busy schedule, the project team will have to work to minimize the number of disputes – thus, ensuring effective implementation of the project.

At every stakeholder meeting during the PPG process (including the two workshops in Port Moresby), the stakeholders unanimously requested a longer project – in acknowledgement of the slow nature of PNG and the fact that it does, actually, take longer to get things done.  In addition, both the GEF-4 project and GEF-5 projects had rocky start-up processes.

Using the newly developed METT for PNG (see Output 1.3)

The PPG process included soliciting opinions from key stakeholders to determine who they thought should sit on the PB in order to fulfil the role of Senior Beneficiaries. The following people were suggested and they should be considered (while acknowledging that this is a two-way relationship and that some of these people may not wish to participate even if asked): i) David Mowbray, UPNG, ii) Michael Koisen, Tisa Savings, iii) Benny Popoitai from Bank of PNG, iv) Anthony Yauieb, member of the PNG Institute of Directors, v) Dr Eric Kwa, Constitutional & Law Reform Commission, vi) Effrey Dademo, Program Manager, Act Now, vii) Brian Brunton, independent, viii) Patricia Kila, independent, ix) Ian Orrell, New Britain Palm Oil Limited, x) The Project Managers of other GEF project in the country, xi) The Country Directors, WCS and TNC, xii) A representative from Walindi Plantation Resort (to represent private sector tourism industry), xiii) Dr Francesca Dam, Deputy Head of the New Guinea Binatang Research Centre, and xiv) Representatives from civil society organisations (FORCERT, CELCOR).  The MTR will check the composition of the PB and ensure that the Senior Beneficiaries are adequately and sufficiently representated and that they are fulfilling their primary role of ensuring the realization of project results from the perspective of project beneficiaries, including the women, men and young people of the communities that own and live from the land and waters to be sustainably protected through this project.

see  https://info.undp.org/global/popp/ppm/Pages/Closing-a-Project.aspx

See https://popp.undp.org/_layouts/15/WopiFrame.aspx?sourcedoc=/UNDP_POPP_DOCUMENT_LIBRARY/Public/PPM_Project%20Management_Closing.docx&action=default.

Note that some of these mechanisms may also function at the protected area system level – for example, through contribution to a system-level trust fund.

There have been a number of different assessments of the biodiversity of PNG – although the majority have focused on terrestrial diversity (vs. marine biodiversity).  These should be used as the basis for making the decisions.

There have not been any nationwide assessments of the ecosystem services or ecological processes.