# Strengthening Resilience of Agricultural Lands and Forests in Dominica in the Aftermath of Hurricane Maria

GEF Secretariat Review for Full Sized Project

Basic Information

GEF ID

9978

Countries

Dominica

Project Title

Strengthening Resilience of Agricultural Lands and Forests in Dominica in the Aftermath of Hurricane Maria

GEF Agency(ies)

UNEP

Agency ID

GEF Focal Area(s)

Land Degradation

Program Manager

PIF

CEO Endorsement

Project Design and Financing

1. If there are any changes from that presented in the PIF, have justifications been provided?

Secretariat Comment at CEO Endorsement

Thank you for the submission of the CEO ER.

2/27/2019

Yes

Response to Secretariat comments

2. Is the project structure/ design appropriate to achieve the expected outcomes and outputs?

Secretariat Comment at CEO Endorsement

2/27/2019: Not fully

a) Please confirm that the total number of hectares to be improved is 750 ha (500 ha restored and 250 ha under improved land management). If so, please ensure consistency in the results data for Table B and Section 4, Table 2.

b) We understand that a total of 2,000 inhabitants will benefit from the project. Please indicate in Table B how many farmers will benefit.

c) We understand the post-Hurricane context and the importance of immediate actions on the ground. However, we recommend to give more importance on sustainability aspects on several actions.

- For instance, how will soil and water conservation measures, tree holding stations, and nurseries (output 1.1.2) be maintained  once the project will have ended, as it seems that these activities are new for farmers. Is a tangible arrangement (MoU?) possible?

- Similar question about sustainability and maintenance of the natural resources data management system?

d) Output 3.1.1: can you clarify the contents of the proposed Programme for Institutional Strengthening?

4/18/2019:

Cleared

Response to Secretariat comments

a)            Yes. The total number of hectares to be improved is 750 ha (Output 1.1.3: 500 ha Land degradation processes halted and land areas stabilized for reforestation restored and, Output 2.1.2: 250 of degraded agricultural lands converted into farms that employ resilient and sustainable farming practices).  This is included and made clearer in Table B.

b)  Out of the 2,000 residents that will be directly influenced by the project, 300 – 400 are engaged in farming operating over 60 to 100 farms (info from the Ministry of Agriculture, Extension Services).  The number of farmers to be engaged has been included in Table B.

c) Personnel of the Government of Dominica through its Extension Services (Departments of Agriculture and Forestry), stakeholders and farmers will be exposed to silvicultural and other reforestation techniques that will benefit farmers/community stakeholders post-project with expectation that they will continue to apply those techniques, contributing to sustainability.  In addition, resources will be allocated from the Government’s regular budget to support continuation and expansion of these activities post-project. Inclusions made under Output 1.1.2 narrative on page 18.

The concept of an MOU, or appropriate commitment agreement will in fact be necessary between the Forestry department and the various farmer stakeholders, including the Central Regional Farmers group and the Dominica Essential Oil and Spices Cooperative Society Limited, to ensure that a proper maintenance regimen is put in place during the early growth stage of the plantings.  Inclusion made under Output 1.1.2 narrative on page 18.

With respect to the natural resources data management system, which is essentially a GIS-based natural resources data management system, will be housed at the Dept of Forestry but linked to the Government’s GIS department at the Ministry of Planning where it will form part of the suite of GIS info collected from the GEF 6 SLM project and this project. Further, this body of work will be linked to the work currently being carried out by PISLM on Land Degradation Neutrality and a joint PISLM/FAO, sub-regional, project called SOILCARE.  Inclusion within the second paragraph under Output 1.1.4 narrative on page 19.

d) Clarification on the proposed Programme for Institutional Strengthening under Output 3.1.1.

Inclusion within the third paragraph under Output 3.1.1 narrative on page 22:

The Institution Strengthening Programme comprises the following components:

·         Training of personnel in the Departments of Agriculture and Forestry in reforestation and climate smart agricultural techniques. In this regard, particular emphasis will be placed on enhancing the skills and knowledge-base of the Extension Services of both the Agriculture and Forestry departments, thereby equipping them with the tools to provide support to farmers during and beyond the duration of the project. Additionally, the Extension Division of the Ministry of Agriculture has indicated its intent to incorporate the training material to be delivered under the project as an integral part of its annual training curricula for farmers in the future.

·         Training of farmers in reforestation and climate smart agricultural approaches, tools and methods.

·         Training of Farming Producer Organizations such as Central Region Farmers Group and the Dominica Organic Agricultural Movement (DOAM), in particular its members who are directly involved in organic agriculture and the members of the Dominica Essential Oil and Spices Cooperative Society Limited (DEOSC).  .

3. Is the financing adequate and does the project demonstrate a cost-effective approach to meet the project objective?

Secretariat Comment at CEO Endorsement

2/27/2019

We note similarities in the budget with the #9667 project and have then the same questions about the budget:

- The level of resources assigned to the project team is a concern: it is the project component presenting the higher costs, also questioning the sustainability of the approach: Are the different positions "National Project Coordinator", "Chief Technical Advisor", "PISLM oversight Officer", "Administrative office" justified? Please, confirm that the different positions will be occupied by different people. Please, provide a rationale to justify 36 months of Chief Technical Officer paid by the project, but not located in Dominica. It was a concern for the #9967, and is still true for this project. Please clarify the need for the PISLM Oversight Officer? Based on the information provided the tasks of the Oversight Officer can be performed by the Project Coordinator. The additional savings can then be allocated towards field-based interventions.

- We have difficulties to understand such budget assigned to publications and reporting ($79,000). We recommend to significantly decrease it and increase the budget for field-based interventions. Explanations for such costs will be welcome.

4/18/2019:

Cleared

Response to Secretariat comments

-          In follow-on discussions with officials from the Ministry of Environment it was determined that the following positions are necessary: Project Manager, Administrative Officer and PISLM Oversight Officer.   Agreed that the function of the Chief Technical Advisor can be rolled into the job of the Project Manager and the CTA position has now been excluded.  It should be noted that the positions will be filled by the existing persons from the GEF 6 SLM project.  Changes to page 31; also Appendix 3: Terms of Reference / Job Descriptions

-          Justification for the PISLM Oversight Officer: This role evolved out of Annex H: Implementing Arrangement. As such, as was the case in GEF 6 SLM Project, an office within PISLM was created to focus on this remit. The PISLM Oversight Officer is of critical importance both from a policy and accountability standpoint. From a policy standpoint this officer will deal directly with the Minister and the Permanent Secretary of the Ministries of the Environment and Agriculture when necessary, with other Ministers and Permanent Secretaries of other Ministries whose activities are aligned to this project. Further, this Officer will also provide project oversight responsibility for ensuring that the relevant issues with respect to the project which need strategic decisions of the Cabinet of the Government of Dominica are dealt with and, will provide or cause to be provided technical backstopping to the Project Management Unit and the Project Manager where necessary.

-          Agreed, reduced budget assigned to publications and reporting; from $79,000 to $30,000. Key publications will be based on “Climate Change…..Plan”, best practice manuals, information flyers, video production and video blogs.  The $49,000 from the publications and reporting, budget line 5201 were re-allocated to budget line 4202-Equipment and materials for forest restoration to bring the total to $449,000. Changes made to Annex F1 and Appendix 2: Procurement Plan.

-          The resources allocated for the Chief Technical Advisor, under budget line 1102 ($90,000) were transferred to budget line 2301- ‘Sub-contract with community organizations’ to bring this total to $190,000. This will further ensure that community involvement is entrenched into the project so as ensuring a greater chance of sustainability. Changes made to Annex F1 and Appendix 2: Procurement Plan

4. Does the project take into account potential major risks, including the consequences of climate change, and describes sufficient risk response measures? (e.g., measures to enhance climate resilience)

Secretariat Comment at CEO Endorsement

2/27/2019

Yes

Response to Secretariat comments

5. Is co-financing confirmed and evidence provided?

Secretariat Comment at CEO Endorsement

2/27/2019

We note that the government will try to access additional co-financing throughout project implementation.

Response to Secretariat comments

In the aftermath of Hurricane Maria, the country suffered considerably. Government is however committed to providing co-financing to the project, particularly in-kind contributions. The Government through its Ministry of Environment is presently reaching out to other institutions such as the Caribbean Development Bank (CDB) for co-financing.

6. Are relevant tracking tools completed?

Secretariat Comment at CEO Endorsement

2/27/2019

N/A. Core indicators completed.

5/15/2019:

The GEF RBM team has recommended the following:

On Indicators please consider moving the 500 ha under 3.1 to (degraded ag lands restored) to 3.2 (forest lands restored).  Given that the project is targeting forest areas damaged by Hurricane Maria.  Also please consider moving the 250 ha under 4.1 (landscape under improved management practices to benefit biodiversity) to 4.3 (Area of landscapes under sustainable land management in production systems).

Please adjust the indicators accordingly. Please also ensure any uploaded documents are also aligned.

Response to Secretariat comments

The recommendations provided by the GEF secretariat has been adopted and relevant changes made in the project document

7. Only for Non-Grant Instrument: Has a reflow calendar been presented?

Secretariat Comment at CEO Endorsement

2/27/2019

N/A

Response to Secretariat comments

8. Is the project coordinated with other related initiatives and national/regional plans in the country or in the region?

Secretariat Comment at CEO Endorsement

2/27/2019:

Not fully.

While the project is fully aligned with national and regional plans, we recognize a few similarities with the GEF 6 SLM project (#9667) which was recently approved. Please provide further details in the project description (Section 3) on how the two projects will collaborate and not duplicate efforts related to the following actions/components:

- the project areas- we note both projects are working in the Corona community;

- monitoring protocols;

- national public awareness campaigns on similar topics. Please justify the need to for two separate campaigns;

- training on GIS and SLM/sustainable agriculture;

- knowledge products on SLM and sustainable agriculture.

4/18/2019:

Cleared

Response to Secretariat comments

i.              How the two projects will collaborate and not duplicate efforts in similar locations

The activities under this project will not be duplicative to the GEF 6 SLM project; rather will provide significant synergies and opportunities for deepened collaboration on enhancing the resilience-building aspects for the benefit of stakeholders in the farming community. To note, in the GEF 6 SLM project, activities in Corona include:

-          Assistance to farmers to better practice sustainable land management in diversified crop production

-          Collaboration by the Corona farming community within a 21 ha demonstration farm in the Woodford Hill area

-           Receipt by farmers of Corona of a package of SLM approaches and technologies developed under Output 2.1.1 and their participation in capacity building activities under Output 2.1.2, G-GAP certification.

These suite of activities, listed above, will lay the foundation for the activities proposed in this project, particularly taking into consideration the catastrophic impacts of Hurricane Maria. As such, the following ‘value-added’ activities envisioned in this project that will include Corona area farmers will include:

-          re-enforcement of the sustainable agriculture practices to ensure resilience.

-          The conduct of a market analysis to determine which crops/products have the most commercial potential (building on the G-GAP capacity building carried out in GEF 6 SLM)

-          Provision of technical support to small farmers to implement new production practices, processing methodologies and commercialization of products.  Inclusion made in narrative under A6. Coordination paragraph 2, pages 31-32

ii.       training on GIS and SLM/monitoring protocols/sustainable agriculture

In the GEF 6 SLM project the GIS aspects will build the capacity of the various ministerial departments in using GIS, as outlined in output 1.1.2.  This project will contribute to enhanced capacity in decision making for improved forest resource and ecosystem assessments and management.  The project will strengthen the existing Geonode land mapping / data information system managed by the Physical Planning Department and rely on expertise of the newly trained officers in the generation of relevant forestry-related datasets and associated capabilities to utilize the data for decision making.    Inclusion made in narrative under Output 1.1.4 paragraphs 3,4, page 19; page 33

iii.            Need for public awareness campaigns and knowledge products

The project will augment the work of the GEF 6 SLM project which looks at LD in a more general awareness-raising context; in this project the focus will be more on creating awareness of the vulnerabilities brought about by impacts of LD on agriculture and how to bolster resilience in these systems, based on ecosystem service approaches. Compared to the SLM project, this project will heighten awareness of LD and climate change on forest ecosystems and the role of the community in the management and governance of Forestry in Dominica.  New knowledge products for forestry-related decision will be created.  Inclusions made in the narrative under Output 3.1.3, page 23; also under section A8, page 34.

9. Does the project include a budgeted M&E Plan that monitors and measures results with indicators and targets?

Secretariat Comment at CEO Endorsement

2/27/2019

Yes

Response to Secretariat comments

10. Does the project have descriptions of a knowledge management plan?

Secretariat Comment at CEO Endorsement

2/27/2019

Yes.

However please see additional comments in Question 8 above.

4/18/2019:

Cleared

Response to Secretariat comments

Agency Responses

11. Has the Agency adequately responded to comments at the PIF stage from:

GEFSEC

Secretariat Comment at CEO Endorsement

2/27/2019

Yes

Response to Secretariat comments

STAP

Secretariat Comment at CEO Endorsement

2/27/2019

N/A

Response to Secretariat comments

GEF Council

Secretariat Comment at CEO Endorsement

2/27/2019

N/A

Response to Secretariat comments

Convention Secretariat

Secretariat Comment at CEO Endorsement

2/27/2019

N/A

Response to Secretariat comments

Recommendation

12. Is CEO endorsement recommended?

Secretariat Comment at CEO Endorsement

2/27/2019

The project cannot be recommended for CEO approval yet. Please address the comments above.

4/18/2019:

We have received the uploaded document with the Agency responses to the Review Comments, however as a part of our internal processing we require the responses to be entered into the Portal prior to project clearance.   Please enter the comments.

4/29/2019:

We note that the uploaded CEO ER has a completed Taxonomy which does not match the Taxonomy entered in the portal. Additionally the portal Taxonomy has included key words that may not apply to this project, such as - Plastics, DDT - Other, DDT - Vector Management, Ozone, Polychlorinated Biphenyls, New Persistent Organic Pollutants, Uninentional Persistent Organic Pollutants, Sound Management of chemicals and waste, Artisanal and Scale Gold Mining, Coal Fired Industrial Boilers, Coal Fired Power Plants, Cement, Non Ferrous Metals Production, Industrial Emissions, Open Burning, Green Chemistry, Disposal, Hazardous Waste Management, Industrial Waste, eWaste

Please adjust.

5/6/2019:

Cleared. The Taxonomy has been adjusted.

5/15/2019:

Not at this time. Please make the adjustment on the indicators as indicated in Question 6.

Response to Secretariat comments

Noted. Agency responses to the Review Comments have been entered.

Review Dates

|  | Response to Secretariat comments |  |
| --- | --- | --- |
| First Review |  |  |
| Additional Review (as necessary) |  |  |
| Additional Review (as necessary) |  |  |
| Additional Review (as necessary) |  |  |
| Additional Review (as necessary) |  |  |