| Core Indicator 3 | Area of land restored |  |  |  |  | (Hectares) |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Hectares (3.1+3.2+3.3+3.4) |  |  |  |
|  |  |  | Expected |  | Achieved |  |
|  |  |  | PIF stage | Endorsement | MTR | TE |
|  |  |  |  | 60,000 | 3,081,100 | 4,298,252 |
| Indicator 3.1 | Area of degraded agricultural land restored |  |  |  |  |  |
|  |  |  | Hectares |  |  |  |
|  |  |  | Expected |  | Achieved |  |
|  |  |  | PIF stage | Endorsement | MTR | TE |
| Degraded Land characterisation, technical feasibility of water harvesting areas and development of plans of rehabilitation |  |  |  | 60,000 | 1,753,380 | 2,456,144 |
| Indicator 3.3 | Area of natural grass and shrublands restored |  |  |  |  |  |
|  |  |  | Hectares |  |  |  |
|  |  |  | Expected |  | Achieved |  |
|  |  |  | PIF stage | Endorsement | MTR | TE |
| Description of biodiversity and indentification and communication of BMP |  |  |  | 60,000 | 1,327,720 | 1,842,108 |

| Core Indicator 4 | Area of landscapes under improved practices (hectares; excluding protected areas) |  |  |  |  | (Hectares) |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Hectares (4.1+4.2+4.3+4.4) |  |  |  |
|  |  |  | Expected |  | Expected |  |
|  |  |  | PIF stage | Endorsement | MTR | TE |
|  |  |  |  | 15,000 | 104,380 | 106,140 |
| Indicator 4.3 | Area of landscapes under sustainable land management in production systems |  |  |  |  |  |
|  |  |  | Hectares |  |  |  |
|  |  |  | Expected |  | Achieved |  |
|  |  |  | PIF stage | Endorsement | MTR | TE |
| Works of soil protection against water erosion, Rehabilitation of 4 khettaras, Rehabilitation of 14 water canals, 12 Solar energy woks for water pumping |  |  |  |  | 4,380 | 6,140 |
| 3 Water points works in pastoral lands |  |  |  |  | 100,000 | 100,000 |

| Core Indicator 6 | Greenhouse gas emission mitigated |  |  |  |  |  |  | (Metric tons of CO₂e ) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Expected metric tons of CO₂e (6.1+6.2) |  |  |  |  |  |
|  |  |  | PIF stage | Endorsement |  | MTR |  | TE * |
|  | Expected CO2e (direct) |  | 150,000 | 150,000 |  | 269,543 |  | 751,170 |
|  | Expected CO2e (indirect) |  |  |  |  |  |  | 1,517,740 |
| Indicator 6.1 | Carbon sequestered or emissions avoided in the AFOLU sector |  |  |  |  |  |  |  |
|  |  |  | Expected metric tons of CO₂e |  |  |  |  |  |
|  |  |  | PIF stage |  | Endorsement |  | MTR | TE |
|  | Expected CO2e (direct) |  | 150,000 |  | 150,000 |  | 269,543 | 751,170 |
|  | Expected CO2e (indirect) |  |  |  |  |  |  | 1,517,740 |
|  | Anticipated start year of accounting |  | 2022 |  | 2022 |  | 2022 | 2022 |
|  | Duration of accounting |  | 20 |  | 20 |  | 20 | 36 |
| Core Indicator 11 | Number of direct beneficiaries disaggregated by gender as co-benefit of GEF investment |  |  |  |  |  |  | (Number) |
|  |  |  | Number |  |  |  |  |  |
|  |  |  | Expected |  |  |  | Achieved |  |
|  |  |  | PIF stage |  | Endorsement |  | MTR | TE |
|  |  | Female |  |  | 30% |  | 23600 | 75,010 |
|  |  | Male |  |  |  |  | 20427 | 62,280 |
|  |  | Total |  |  |  |  | 43027 | 137,290 |

* Estimated value.