WWF GEF Agency

Project Implementation Report

ECOSYSTEM APPROACH TO FISHERIES MANAGEMENT (EAFM) IN EASTERN INDONESIA (FISHERIES MANAGEMENT AREA (FMA) - 715,717 & 718), COMPONENTS A, B, AND D

(GEF PROJECT ID 9129)

Project Report information:

| Report Author(s) | Dr. Adipati Rahmat Gumelar, Heike Lingertat |
| --- | --- |
| Report Completion Date | August 14th, 2025 |

| 1. General Information | PIR Submission Date | September 10, 2025 |
| --- | --- | --- |
|  | Agency Approval Date | WWF: 12/20/19 CI: 05/04/2017 |
|  | Fiscal Year | 2025 |
|  | Implementation Status (1st PIR, 2nd PIR, Final PIR) | 6th PIR |
| 2. Current Year Ratings | Overall DO rating | HS |
|  | Overall IP rating | S |
|  | Overall Risk rating | M |
| 3. Key dates | Actual Implementation Start Date | WWF: 05/04/2021 CI: 03/15/2018 |
|  | First Disbursement Date | WWF: 08/12/20 CI:03/15/2018 |
|  | Expected Mid-Term Review Date | WWF: 7/1/23 |
|  | Expected Completion Date | CI: technically closed on 05/20/22, and last PIR was in 2022 WWF: 12/31/26 |
|  | Expected Financial Closure | WWF: 6/30/27 |
|  | Actual Completion Date | CI: on 05/20/22 |
| 4. BUDGET | Total Project Budget | WWF: USD6.893.0832 of USD10,183,486 (GEFTF) |
|  | Total GEF disbursement (USD) through June 30 of the FY for project that has been in implementation for at least 1 FY (Please indicate amounts under GEF Trust Fund, LDCF, and SCCF) | USD 4,666,141.21 (WWF with Rekam) $2,672,418 (CI) Total: USD 7,338,559.21 USD 7,338,559.21 ( includes CI, US and Rekam) |
|  | Committed co-financing | 38,057,193 |
|  | Materialized Co-finance | 11,666,751 |

PMU Contact information:

| Project Position | Name | E-mail |
| --- | --- | --- |
| Project Manager | Dr. Adipati Rahmat Gumelar | adipatirahmat@gmail.com |
| M&E Officer | Ahadar Tuhuteru, S.Pi, M.Si | ahdar.79@gmail.com |
| F&A Officer | Yoppy Endano, SE, MM | yoppy.hii@gmail.com |
| Safeguards Specialist | Faridatun Amalia Hasanah, S.Tr.Pi.,MP | faridatunamalia25@gmail.com |
| Finance Assistant | Muhammad Firmansyah, S.Ag | Syah2790@gmail.com |
| Creative Media Assistant | Marsha Maritza, S.Pi | mrshmaritza@gmail.com |
| Project Secretary | Nuranti Anarkhis., S.Pi., M.P | nurantianarkhis22@gmail.com |

WWF GEF Contact information:

| Project Position | Name | E-mail |
| --- | --- | --- |
| Project Manager | Heike Lingertat | Heike.Lingertat@wwfus.org |
| Safeguards Specialist | Adrienne McKeehan | Adrienne.McKeehan@wwfus.org |
| Gender Specialist | Nathalie Simoneau | Nathalie.Simoneau@wwfus.org |

Instructions:

The WWF GEF Project Manager is responsible for completing the PIR in coordination with the Project Management Unit. It may be necessary to consult with other experts for current data (e.g. Safeguards, Gender, RBM, etc). Please include the following annexed documents:

- Completed Tracking Tool with Results Framework and Annual Work Plan and Budget Tracking (for project year)

- Tracking tools (eg. METT), if applicable

- Knowledge Management products (if links were not provided in the section directly)

- Other supporting documents: meeting minutes, stakeholder consultation, photos, maps, reports, etc.

### Ratings

Fill in all ratings based on the Rating Scale provided in Annex I.

|  | Year 1 (FY19) | Year 2 (FY20) | Year 3 (CY21) | Year 4 (CY22) | Year 5 (CY23) | Year 6 (CY24) | Year 7 (CY25) |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Development Objective WWF | N/A | S | U | S | S | HS |  |
| Development Objective CI | S | S | HS | N/A | N/A | N/A | N/A |
| Implementation Progress WWF | N/A | U | MU | MS | MS | S |  |
| Implementation Progress CI | N/A | S | HS | N/A | N/A | N/A | N/A |
| Risk WWF | N/A | L | M | M | M | M |  |
| Risk CI | L | L | L | N/A | N/A | N/A | N/A |

Justification for Current Year Ratings:

In summary, the CFI Indonesia project achieved commendable results throughout 2024, reflecting significant progress and impact. The Year 5 Development Objective rating for the project is Highly Satisfactory and reflects meeting 100% of indicator targets for the year. While the CI GEF component of the project underwent technical close-out in May 2022 (as reported in the PIR for FY22/Year 3), this PIR reflects the fourth year of implementation for the WWF GEF component. The Implementation Progress is also rated Satisfactory, with 99% of workplan activities completed in alignment with the indicator targets for the reporting period. This marks a 22% improvement over last year’s performance which is due to strong engagement of MMAF and the local government. This success reflects the dedicated efforts of the Project Management Unit (PMU) and the Ministry of Marine Affairs and Fisheries (MMAF), supported by strategic guidance from the WWF-US GEF Agency. The project risk rating remains Modest, primarily due to the uncertain impact of the new fisheries policy and ongoing personnel changes within the Project Management Unit (PMU) and Steering Committee. According to MMAF regulations, an acting Director General (DG) may serve for a maximum of eight months before a permanent appointment is required. Continued changes in the DG of Capture Fisheries have affected the Project Steering Committee, as well as the roles of the National Project Coordinator (NPC) and Technical Coordinator (TC). To mitigate this risk, the PMU and the broader CFI Indonesia team have drawn lessons from past transitions and plan to proactively engage with the incoming DG as early as possible.

### Progress, Challenges, and Outcomes on Project Implementation

(Based on Outcomes, Challenges, and Safeguards sections of the Progress Report)

Describe the key outcomes and impacts achieved as well as any challenges during the previous 12 months, using the AWP&B and Results Framework as a reference. Please report by component if feasible. Beginning in 2024, with approval from the WWF-US GEF Agency, the CFI project expanded its scope to actively support priority programs of the MMAF. This adjustment was necessary due to the original project design, developed in 2015, which no longer fully aligned with the Ministry’s current vision and mission. As a result, CFI Indonesia now incorporates MMAF’s priority programs to ensure that project outcomes are consistent with the expectations of the Minister and relevant stakeholders. Component A. Implementing Enabling Condition for EAFM in FMA 715, 717, and 718 Flying Fish Fishery Management Plan: Under Sub-Component A.1, CFI facilitated the finalization of two pending Fisheries Management Plans (FMPs) for FMAs 715 and 718. These plans are developed under national regulatory frameworks and provide comprehensive guidance for managing Fisheries Management Areas (FMAs). Compared to regional instruments such as Governor’s Regulations or Action Plans, FMPs offer more robust data integration, standardized processes, and inclusive stakeholder engagement. Due to the GEF project, the development of FMPs now integrates safeguard and gender-related issues, and the representation of minority, local, and Indigenous communities. This marks a significant achievement in gender mainstreaming and the empowerment of Indigenous Peoples. The Collaborative Fisheries Initiative (CFI) has been recognized by the Gender Working Group within the Ministry of Marine Affairs and Fisheries (MMAF) for its effective approach to gender integration. As a result, the MMAF plans to replicate the CFI’s gender mainstreaming strategy within future FMPs and adopt it as a best practice. With the completion of these two FMPs, all FMPs for CFI’s activity locations have now been established. CFI also pioneered the implementation of the Sasi Co-management concept, strengthening indigenous coastal communities’ conservation efforts through the OECM (Other Effective Area-Based Conservation Measures) framework. This initiative, launched in Kilitay, Menarbu, and Ohoirenan, has been well received, including by the GEF Operational Focal Point, and stands out as the only OECM initiative among GEF projects in Indonesia. Under Sub-Component A.2, CFI successfully collected data on mangrove crab populations across three FMAs, engaging universities as research partners (data collection) to ensure scientific rigor and local capacity building. In Sub-Component A.3, the project completed two key studies: one supporting the establishment of a Regional Public Service Agency for conservation area management in Ur Pulau (FMA 718), and another exploring a Payment for Ecosystem Services (PES) scheme in the same region. Sub-Component A.4 continued to focus on enhancing stakeholder capacity, particularly among local communities and government institutions. A notable achievement was the introduction to fuel-efficient engines in Southeast Maluku, representing an environmentally friendly technological innovation that is accessible and practical for fishing communities. Component B: Implementing EAFM Tools to support EAFM in FMA 715, 717 and 718 Progress Toward Marine Conservation: The primary achievement under Component B was the successful establishment of the new South Buru Marine Protected Area (MPA) in FMA 715. This milestone was achieved through collaboration with the Maluku Provincial Fisheries and Maritime Affairs Agency and academic institutions. The MPA was formalized through Maluku Governor Decree No. 1957 of 2024, which designated 1,031,665.13 hectares of regional conservation areas across four regencies: Buru Waters, Buru Regency: 57,594.12 ha South Buru Waters, South Buru Regency: 87,570.95 ha East Seram Waters, East Seram Regency: 199,500.06 ha Teon Nila Serua Waters, Central Maluku Regency: 687,000 ha The project supported the establishment of the MPA by facilitating a series of integrated ecological and socio-economic evaluations. Between August 25 and September 3, 2024, CFI supported the Maluku Province Marine and Fisheries Agency in conducting a socio-economic survey to assess community livelihoods and resource use. This was followed by an ecological survey led by IPB from September 18 to October 20, 2024, which evaluated the condition of mangrove, seagrass, and coral reef ecosystems, and assessed the presence and nesting potential of sea turtles, with a focus on leatherback turtles. To ensure inclusive planning, Public Consultation I was held at the village level from November 7–8, 2024, and Public Consultation II at the district level on November 19, 2024. The formal designation of a new conservation area on Southern Buru Island, identified as a critical migration route for leatherback turtles, is scheduled for completion in 2025. The proposed area spans approximately 35,000 hectares and will be managed under a co-management framework involving local communities, provincial authorities, and conservation partners. Key targets include: Legal designation of the MPA by Q4 2025 Development of a participatory management plan by Q2 2026 Baseline biodiversity monitoring completed by Q1 2026 Capacity building for 50 local stakeholders in MPA governance and enforcement These efforts aim to enhance marine biodiversity conservation, support sustainable fisheries, and strengthen climate resilience in the region. CFI has successfully completed the Ecosystem Approach to Fisheries Management (EAFM) assessments for all three Fisheries Management Areas (FMAs): 715, 717, and 718. For FMA 715, the assessment was conducted in collaboration with the Local Champion (LC) EAFM team at the University of Pattimura. For FMA 717, CFI partnered with the LC EAFM team at the University of Papua. In addition, CFI, together with the National Research and Innovation Agency (BRIN) and the Directorate of Small Islands Utilization, facilitated the recognition of Indigenous Peoples' Sasi Areas as Conservation Area Reserves under the Other Effective Area-Based Conservation Measures (OECM) framework. This recognition was achieved through the Sasi Co-management model in the following locations: Kataloka (FMA 715), Menarbu (FMA 717), Ohoirenan (FMA 718) CFI Indonesia has made significant strides in improving coastal community resilience and sustainable marine resource management across multiple provinces, including East Seram, Ambon, South Manokwari, Biak, Wondama, Kaimana, and Southeast Maluku. Empowering Village-Owned Small Businesses: A core focus of CFI has been the development of village-owned small businesses, particularly those led by women’s groups. Through targeted training and facilitation, these groups have received support in product development, branding, intellectual property rights, health and halal certification, and marketing. CFI also facilitated Memorandums of Understanding (MoUs) with modern retail outlets to expand market access. As a result of these interventions, women's group incomes increased by 193% by the end of 2024. The success of the Sasi Label model, a community-based business system, has been particularly noteworthy. It led to the formation of 58 business groups, producing 1,927 processed food products and 1,737 eco-print items, all certified and market ready. Supporting Small-Scale Fishers: CFI continued to support male fishers by facilitating the issuance of small passes and fishing vessel registration certificates (TDKP)—key prerequisites for obtaining fish catching and transport permits. Fishers also benefited from practical training in: Boat engine repair, GPS and net maintenance, use of collapsible traps and crab banks, fuel-saving technologies, proper fish handling and certification, and building capacity for young fishers. To enhance safety and employability, CFI strengthened the role of the Ambon Fisheries Training and Extension Center by delivering Basic Safety Training (BST) in line with IMO-STCW standards. In 2024, three BST sessions were conducted, reaching 149 participants, 40% of whom were women. Impressively, 78% of trained youth secured employment, including on international vessels. Despite facing logistical challenges—particularly adverse weather in remote coastal areas—and limited physical infrastructure and capital support, CFI Indonesia leveraged strong partnerships to overcome these barriers. For example: In Southeast Maluku, the Fisheries Office constructed a dock, the Village Government built a production house, and local banks provided micro-business credit. These collaborative efforts have been widely recognized by community groups and government stakeholders, who have praised CFI Indonesia’s positive impact on livelihoods, governance, and marine conservation. Component D. Implementing KM, M&E for Sustainable Coastal Fisheries in FMA 715, 717 and 718 Component D of the CFI Indonesia program is centered on knowledge management, monitoring and evaluation, and the dissemination of best practices. The Project Management Unit (PMU) has played a key role in ensuring that lessons learned and field-level insights are systematically captured and shared with stakeholders at all levels. D.1 – Monitoring, Evaluation, and Community Empowerment. CFI has prioritized the evaluation of this years implemented activities and their impacts across project sites. A notable focus has been on promoting community-based fisheries data collection, particularly through the use of logbooks by small-scale fishers. In areas such as Tual, Morotai, and Central Maluku, fishers trained in electronic log-booking now routinely record and report their catch data to local Fishing Ports and Fisheries Agencies. This has significantly improved the quality and consistency of fisheries data. In 2024, CFI also launched a Community Champions initiative, selecting 12 women fishers from 12 regencies based on their leadership, enthusiasm, and commitment during training sessions. These champions such as Sri Fanny Mony (Southeast Maluku), Sinta (Ambon), and Joy (Kaimana) have become key advocates for CFI’s mission. They have participated in EAFM trainings, represented their communities at strategic events, and showcased their products at exhibitions. Their role is expected to grow as they help sustain CFI’s legacy beyond the project’s conclusion by sharing their stories and mentoring others. D.2 – Data Systems and Decision Support Tools. To support evidence-based decision-making, CFI developed a Fish Resource Dashboard for the Ministry of Marine Affairs and Fisheries (MMAF). This tool enables users to access and analyze data on small pelagic species, snapper, and grouper, collected through CFI-supported initiatives such as the Buru Island expedition. The dashboard integrates ecological data (e.g., coral reefs, seagrass, mangroves) and social data (e.g., fishers and indigenous communities), and has directly supported the planning of a new conservation area in South Buru, particularly for the protection of leatherback turtle migration routes. D.3 – Dissemination and Scientific Engagement. CFI has actively disseminated its findings through Information, Education, and Communication (IEC) campaigns. A highlight was the September 2024 exhibition held alongside the International Symposium on Small-Scale Fisheries (ISOSS) in Ambon. This event provided a platform for CFI to present research outputs, including studies on Other Effective Area-Based Conservation Measures (OECMs) and indigenous knowledge systems. CFI also premiered three documentaries produced in 2024, offering compelling visual narratives of its work and impact. Major Challenges The implementation of the 2024 Annual Work Plan and Budget (AWPB) faced notable challenges, primarily stemming from bureaucratic delays. A change in the Chair of the Project Steering Committee (PSC) early in the year disrupted the approval process, requiring the AWPB to be revised to align with the evolving priorities of the Ministry of Marine Affairs and Fisheries (KKP). As CFI Indonesia is institutionally affiliated with the Ministry of Marine Affairs and Fisheries (MMAF), its activities must adhere to the ministry’s administrative protocols. This dependency created a bottleneck, delaying formal approval until March 2024 and pushing the start of implementation to mid-May. The compressed timeline significantly impacted planning, execution, and monitoring efforts. Activities had to be fast-tracked, often under suboptimal conditions, which placed pressure on field teams and limited opportunities for adaptive management. Despite these constraints, the PMU successfully negotiated the inclusion of two new activity titles and ensured that several components of the AWPB were realigned with MMAF’s strategic programs—an achievement that ultimately enabled the project to move forward. Major Strengths A key factor enabling the project’s performance in 2024 was the strong, transparent, and adaptive coordination between the Project Management Unit (PMU) and its counterparts within MMAF, including the National Project Coordinator (NPC) and Technical Committee (TC). The PMU’s commitment to clear communication and accountability, particularly in financial and administrative reporting, earned formal recognition from both the Auditor and Inspector 2 of the Inspectorate General. This transparency helped build institutional trust and ensured compliance with oversight requirements. Additionally, the Planning Bureau of the Secretariat General commended the PMU’s collaborative approach, noting that it significantly improved the efficiency of activity coordination and minimized procedural errors across the project.

### Progress, Challenges, and Outcomes of Stakeholder Engagement

### (Based on Stakeholder Engagement Plan (SEP) or equivalent included in the ProDoc)

Summarize progress, challenges, and/or outcomes of stakeholder engagement, including strategies taken to ensure gender and social inclusion. Please report for each group of stakeholders (e.g. Ips, LCs, local government, etc). identified in the SEP or equivalent plus any other group identified during implementation. As a project embedded within the Ministry of Marine Affairs and Fisheries (MMAF), CFI Indonesia operates within a complex bureaucratic framework that demands consistent coordination and alignment with national priorities. While this structure presents challenges, particularly in navigating administrative processes, the project has made significant progress in strengthening collaboration with key units. Coordination between the Project Management Unit (PMU) and the Executing Agency—specifically the Directorate of Fish Resource Management—has been well-established. The PMU also maintains strong working relationships with the MMAF Secretariat General, including the Planning Bureau, Cooperation and Foreign Relations Bureau, Legal Bureau, and the Auditor. Notably, the Planning Bureau upgraded CFI Indonesia’s status from “red” to “green,” recognizing the project as a model for effective project management within MMAF. However, a persistent challenge has been the frequent turnover of leadership within MMAF’s CFI management structure. In 2024 alone, the Project Steering Committee changed three times (from Zaini to Agus Hermawan to Lotharia Latif), while the National Project Coordinator and Technical Coordinator each changed once. These transitions often slowed project momentum due to the time required for new appointees to familiarize themselves with CFI’s objectives, processes, and progress. Local Government Level: At the local level, CFI Indonesia maintains strong relationships with provincial and district governments. However, challenges occasionally arise when Regency Fisheries Offices lack the technical or administrative capacity to implement activities or manage financial reporting in accordance with CFI standards. In such cases, the PMU coordinates with the Auditor and, when necessary, reassigns responsibilities to more capable partners or implements activities directly to ensure quality and accountability. Academic and Learning Centers: CFI Indonesia collaborates extensively with universities and EAFM Learning Centers across multiple Fishery Management Areas (WPPs). Rather than relying on a single institution per region, CFI engages multiple academic partners to optimize data collection and research. This approach not only enhances the quality of outputs but also reduces operational costs by leveraging local expertise and proximity to field sites. Community Engagement: CFI Indonesia is widely recognized at the community level, particularly through the Champion Initiative launched in 2024. This program identifies and trains outstanding individuals—primarily women—from each regency to serve as local ambassadors of CFI’s mission. A total of 19 champions have received training in EAFM, participated in exhibitions, and represented their communities at national and international events. These champions are expected to play a key role in sustaining CFI’s legacy beyond the project’s duration. CFI also promotes inclusive participation, actively engaging men, women, persons with disabilities, and widows in its programs. This inclusive approach ensures that all community members have the opportunity to contribute to and benefit from local development and business initiatives. Indigenous Communities: CFI Indonesia recognizes the distinction between indigenous peoples and indigenous law communities; the latter being formally acknowledged through government decrees. In collaboration with the Directorate of P3K, CFI has facilitated the designation of three indigenous law communities in Kilitay, Menarbu, and Ohoirenan. The project also works with other indigenous groups seeking support, including those in Gorom, Aisandami, and Watkidat, to strengthen their rights, visibility, and participation in marine resource management.

### Information on Progress on Gender-Responsive Measures

### (As documented in the ProDoc, Results Framework, the Gender Action Plan or Equivalent)

Please provide the completion dates for: the gender assessment or analysis and gender mainstreaming strategy/action plan (GEF-7). Advancing Gender Equality and Social Inclusion in Coastal Fisheries: Indonesia’s coastal fisheries sector has long grappled with structural inequalities, particularly in the recognition and inclusion of women and other vulnerable groups. Although women play a vital role across the fisheries value chain—from processing and marketing to post-harvest activities—their contributions often go formally unrecognized. Limited access to technical training, business ownership, legal documentation, and market opportunities has left women, widows, the elderly, persons with disabilities, and indigenous communities economically and socially marginalized. In response, the CFI Indonesia Project has actively promoted a more equitable and inclusive approach to coastal resource governance. The project made significant strides in mainstreaming gender equality and social inclusion principles into community-based fisheries management. Inclusive Capacity Building and Economic Empowerment: A total of 1,637 women participated in livelihood skills training through 37 activities, including eco-print production, fisheries product processing, and micro-entrepreneurship. Simultaneously, 3,522 male fishers were engaged in 35 technical trainings, covering boat engine repair, Basic Safety Training certification, and data-driven marine resource management. This balanced approach reflects the project’s commitment to inclusive participation and equitable access to resources. As a result, over 30 Joint Business Groups (KUB) led by women were formed across 12 villages, with more than 200 active members. These groups now manage their businesses independently and have received support to formalize their operations. CFI facilitated the issuance of Business Identification Numbers, Home Food Industry Licenses, FDA certifications, and Intellectual Property Rights for more than 10 women-led enterprises, strengthening their access to sustainable markets. Product Innovation and Market Linkages: The project-supported women groups have produced 1,927 processed fishery products—including shredded fish, nuggets, crackers, fish sticks, and seafood sauces—and 1,737 eco-printed items, such as bags, fabrics, and clothing. These products not only generate new income streams for coastal households but also celebrate local culture and creativity. To expand market access, CFI brokered eight Memorandums of Understanding (MoUs) with regional retail partners, including GOTA Supermarket Langgur, Frish Mart Ambon, PT. Angkasa Pura I Ambon, and outlets at Pattimura Airport and Hotel Santika Premiere. These partnerships have enabled community products to reach broader audiences, including travelers and urban consumers. Transformative Learning and Leadership: A key milestone was the Community Development Training held at Pendopo Kembang Kopi, Malang, attended by 17 Champions (8 women, 7 men) from various project sites. Initially hesitant to speak, women participants became increasingly confident through interactive facilitation and a live-in approach. By the end of the training, they were actively voicing community needs and positioning themselves as local leaders in fisheries governance and marine conservation. Economically, the impact has been substantial. The combined income of assisted groups rose from $2,586 in 2023 to $7,584 in 2024, marking a 193.3% increase. This growth underscores the power of inclusive empowerment, legal recognition, and market access to drive tangible change in coastal communities. National Recognition and Replication: The success of CFI’s gender and inclusion model has attracted national attention. It has been showcased at high-profile events such as the IndoFisheries Exhibition at the Jakarta Convention Center, the launch of the Measured Fishing Program in Tual, and various ministerial visits. Replication efforts are already underway in areas like Tangerang and Morotai, signaling the model’s scalability and relevance. Partner Training and Gender Action Plan Implementation: To ensure sustainability, CFI has embedded gender action plan implementation into its coordination and training processes. Socialization of gender principles occurs at every activity, and the PMU regularly convenes coordination meetings with central and regional governments and community stakeholders to monitor progress. Gender-disaggregated data is consistently recorded and evaluated. Importantly, the project has fostered a cultural shift: men now actively support women-focused initiatives, recognizing their value to community development. This collaborative spirit has strengthened the foundation for long-term gender equity in coastal resource governance.

### Knowledge Activities / Products

### (When Applicable, as Outlined in Knowledge Management Approach in the ProDoc)

Please summarize progress on the implementation of the project’s KM approach approved at CEO endorsement/ Approval. One of the work specifications in the GEF 6 CFI Indonesia (EAFM) project is knowledge management and monitoring and evaluation (KM & MNE). This specification is largely accommodated in Component D, which implements knowledge management, monitoring, and evaluation for sustainable coastal fisheries in the FMA. Component D includes a platform built for project monitoring, evaluation, reporting, and knowledge management, which encourages data exchange, communication of lessons learned, and adaptive management. Results are monitored by continuously recording and analyzing project implementation. To implement Component D, a platform is needed to accommodate knowledge and lessons learned from the EAFM project, which can also serve as a medium for collaboration between stakeholders involved in EAFM-based fisheries management. Currently, the EAFM project has a well-managed web-based information center at www.cfi-indonesia.id. In addition to these primary communication channels, the PMU team also utilizes other social media platforms such as WhatsApp, Instagram, YouTube, Facebook, and Twitter. The number of visitors to the CFI Indonesia news portal and YouTube channel has increased annually. This year, the highest number of news visitors to the website www.cfi-indonesia.id reached over 1,600, and the CFI Indonesia YouTube channel @CFIGEF6 (https://www.youtube.com/@CFIGEF6) reached over 900. Meanwhile, the Instagram account (https://www.instagram.com/cfigef6?igsh=MWJnZ2w4azJrbHNoeg==) has over 9,000 followers, with the highest number of visitors reaching over 1,000. Furthermore, GEF-6 also collaborates with the social media channels of the Ministry of Maritime Affairs and Fisheries and the Directorate General of Capture Fisheries. For example, information shared through the MMAF YouTube channel and on the MMAF TV channel (Neptune TV) includes a video about women fishermen filmed in Coa, Kaimana, West Papua. Similarly, local media outlets in Maluku and West Papua published news about GEF 6 activities in both locations. For example, the Ecoprint Product Making activity in Aisandami, Wondama Bay, was also publicized on the Wondama Bay Communication and Information Technology (KOMINFO) YouTube channel. Similarly, the Kaimana Fisheries Service, the West Papua Province Maritime Affairs and Fisheries Service, the Southeast Maluku Fisheries Service, the East Seram Regency Fisheries Service, and the Maluku Province Maritime Affairs and Fisheries Service publicized their activities through YouTube channels, Facebook, and online news portals (websites). In addition to YouTube channels, Instagram has also become a platform for up-to-date information in this digital era. The GEF-6 Instagram has also collaborated with the Public Relations Department of the Directorate General of Capture Fisheries, for example, in sharing information related to the GEF-6 International Seminar, among other things. List knowledge activities/products (including links) developed during this project year. Activity; # Knowledge Management Activities. CFI Indonesia: Year 2024 Report; # https://drive.google.com/file/d/1fhMxoioa8OlQQyDljORKJGZlrIFzwa4f/view?usp=sharing. CFI Indonesia: Re-convene ARM 2024 and Prepared AWPB 2025, Involving Women Champions from 6 Coastal Districts; # https://cfi-indonesia.id/blog/cfi-indonesia-gelar-kembali-arm-2024-dan-penyusunan-awpb-2025-ikut-sertakan-champion-perempuan-pesisir-6-kabupaten/ # https://kkp.go.id/djpt/kkp-ajak-gef-6-perluas-kerja-sama-ekonomi-biru-oVNX/detail.html # https://www.antaranews.com/berita/4525801/kkp-ajak-gef-6-perluas-kerja-sama-ekonomi-biru#google_vignette. Technical Guidance on the Application of Fuel-Saving Technology for Fishing Fleets; # https://cfi-indonesia.id/blog/cfi-indonesia-bimbingan-teknis-penerapan-teknologi-alat-penghemat-bbm-untuk-armada-penangkapan/ # https://cfi-indonesia.id/blog/cfi-indonesia-technical-guidance-on-the-application-of-fuel-saving-device-technology-for-fishing-fleets/ # https://www.youtube.com/watch?v=LbtBa9jfiwI. KKP Collaborates with Southeast Maluku Regency Fisheries Office to Improve Capacity and Skills of 13 Small-Scale Fishers Groups (Volume 2); # https://cfi-indonesia.id/blog/cfi-indonesia-kkp-gandeng-dinas-perikanan-kabupaten-maluku-tenggara-tingkatkan-ketrampilan-nelayan-kecil-(jilid-2)/. MMAF Holds Socialization of Fishing Logbook in Pasanea Village, Central Maluku; # https://www.salawaku.com/daerah/kkp-gelar-sosialisasi-logbook-penangkapan-ikan-di-desa-pasanea-maluku-tengah.html. Fishing Vessel Seaworthiness Certificate (SKKP) Activity in Mandala Village, Jayapura - Supporting the Safety and Operational Standards of Fishermen; # https://cfi-indonesia.id/blog/cfi-indonesia-kegiatan-gerai-penerbitan-sertifikat-kelaikan-kapal-perikanan-(skkp)-di-kampung-mandala,-jayapura-mendukung-keselamatan-dan-standar-operasional-nelayan/. Together with Maluku Provincial Office of Marine Affairs and Fisheries, Facilitating the Draft Governor Regulation (Ranpergub) on the Sea Turtle Regional Action Plan (RAD Penyu) at the Ministry of Home Affairs to Ensure Alignment with National Regulations; # https://cfi-indonesia.id/blog/cfi-indonesia-bersama-dkp-maluku-laksanakan-fasilitasi-ranpergub-rad-penyu-di-kemendagri-guna-memastikan-kesesuaian-regulasi-nasional/ # https://www.youtube.com/watch?v=M6CqhrZWfKA. Facilitation of Fisheries Stock Assessment in Fisheries Management Areas (WPP) 715, 717, and 718; # https://cfi-indonesia.id/blog/cfi-indonesia-fasilitasi-kajian-stok-perikanan-di-wilayah-pengelolaan-perikanan-(wpp)-715,-717-dan-718/. Unveiling the Coastal and Fisheries Ecosystem Conditions of Southern Buru Island to Support Marine Protected Area Designation through the Faculty of Fisheries and Marine Science (FPIK) IPB University Expedition; # https://cfi-indonesia.id/blog/cfi-indonesia-menguak-kondisi-ekosistem-pesisir-dan-perikanan-pulau-buru-bagian-selatan-dukung-pencadangan-kawasan-konservasi-melalui-ekspedisi-fpik-ipb-university/ # https://www.ipb.ac.id/news/index/2024/10/ekspedisi-himiteka-ix-ipb-university-mengungkap-spesies-langka-penyu-di-pulau-buru/ # https://korpusipb.com/advertorial/ekspedisi-himasper-kembara-moloku-rhizossia-bersatu-selamatkan-laut-maluku/ # https://www.ipb.ac.id/news/index/2024/10/ekspedisi-himiteka-ix-ipb-university-mengungkap-spesies-langka-penyu-di-pulau-buru/ # https://www.youtube.com/watch?v=j1PPkDlqHDo. MMAF Disseminates the Results of Identification and Mapping of the Indigenous Community of Negeri Kiltay in East Seram; # https://cfi-indonesia.id/blog/cfi-indonesia-kkp-diseminasi-hasil-identifikasi-dan-pemetaan-masyarakat-adat-negeri-kiltay-di-seram-bagian-timur/ # https://www.youtube.com/watch?v=fUmDfFjPu7A. CFI Indonesia: Conducting a Bio-ecological Study of Mangrove Crabs in Fisheries Management Areas (WPPNRI) 715, 717, and 718; # https://cfi-indonesia.id/blog/cfi-indonesia-melaksanakan-kajian-bioekologi-kepiting-bakau-di-wppnri-715,-717,-dan-718/ # https://www.youtube.com/watch?v=_d9hTqbSf4E. CFI Indonesia: Ecoprint Batik Making Training for Fisherwomen in East Seram Regency; # https://cfi-indonesia.id/blog/cfi-indonesia-pelatihan-pembuatan-batik-ecoprint-bagi-wanita-nelayan-di-kabupaten-seram-bagian-timur/ # https://www.youtube.com/watch?v=TGqdUP5yII0. Facilitation of Knowledge Management System for Fisheries Enumerators and Extension Officers in Fisheries Management Areas (WPPNRI) 715, 717, and 718; # https://cfi-indonesia.id/blog/cfi-indonesia-fasilitasi-sistem-manajemen-pengetahuan-bagi-para-enumerator-penyuluh-perikanan-di-wppnri-715,-717-dan-718/. CFI Indonesia : Promoting Small-Scale Fishers’ Empowerment, MMAF and Southeast Maluku Fisheries Office Facilitate the Issuance of Small Vessel Registration Documents for Small-Scale Fishers; # https://cfi-indonesia.id/blog/cfi-indonesia-dorong-pemberdayaan-nelayan-kecil,-kkp-dan-dinas-perikanan-maluku-tenggara-fasilitasi-penerbitan-dokumen-pas-kecil-bagi-nelayan-kecil/. CFI-Indonesia : Together with the Raja Ampat Regency Fisheries Office, Training Fishers to Repair Outboard Motors; # https://cfi-indonesia.id/blog/cfi-indonesia-bersama-dinas-perikanan-raja-ampat-latih-nelayan-perbaiki-motor-tempal/ # https://www.youtube.com/watch?v=Gz0BtL7QoC8. MMAF Facilitates Assistance in Drafting the Regent Regulation on the Recognition of the Indigenous Community of Ohoi Ohoirenan – Southeast Maluku; # https://cfi-indonesia.id/blog/cfi-indonesia-kkp-mendamping-percepatan-penetapan-masyarakat-hukum-adat-ohoi-ohoirenan-maluku-tenggara/. Survey of Sasi Fisheries Resources in Windesi District, Teluk Wondama Regency; https://cfi-indonesia.id/blog/cfi-indonesia-survey-sumberdaya-perikanan-sasi-distrik-windesi-kabupaten-teluk-wondama/. The Issuance of Minister of Marine Affairs and Fisheries Regulation No. 76/2024, Governing the Improved Management of Flying Fish Fisheries; # https://cfi-indonesia.id/blog/cfi-indonesia-terbitnya-peraturan-menteri-kelautan-dan-perikanan-nomor-76-tahun-2024,-mengatur-pengelolaan-perikanan-ikan-terbang-lebih-baik/ # https://www.youtube.com/watch?v=cbsY61PCw8o. Together with the East Seram Fisheries Office, Holding Basic Diving Training for Civil Servants and Community Monitoring Groups; # https://cfi-indonesia.id/blog/cfi-indonesia-bersama-dinas-perikanan-sbt-gelar-pelatihan-selam-dasar-bagi-asn-dan-kelompok-masyarakat-pengawas/. MMAF, Through PPN Ternate, Holds a Coordination Meeting on the Fisheries Management Unit (UPP) of Fisheries Management Area of the Republic of Indonesia (WPPNRI) 717; # https://cfi-indonesia.id/blog/cfi-indonesia-kkp-melaui-ppn-ternate-gelar-kegiatan-rapat-rapat-koordinasi-unit-pengelolaan-perikanan-wilayah-pengelolaan-perikanan-negara-republik-indonesia-(upp-wppnri)-717/. MMAF Encourages the Acceleration of the Recognition of the Indigenous Community (MHA) of Ohoirenan, Southeast Maluku Regency; # https://cfi-indonesia.id/blog/cfi-indonesia-kkp-dorong-percepatan-pengesahan-mha-ohoi-ohoirenan-kabupaten-maluku-tenggara/ # https://www.youtube.com/watch?v=OarRbPh2c7Y. Together with Marine and Fisheries Polytechnic – Maluku Campus, Facilitating Basic Safety Training (BST) Certification for 30 Participants from Southeast Maluku Regency, Maluku Province (Batch III); # https://cfi-indonesia.id/blog/cfi-indonesia-bersama-poltek-kp-kampus-maluku,-fasilitasi-sertifikasi-bst-bagi-30-peserta-dari-kabupaten-maluku-tenggara,-provinsi-maluku/ # https://www.youtube.com/watch?v=VWQxoP0q6M8&t=52s. Strengthening the Community Monitoring Groups (Pokmaswas) Capacity, MMAF and Maluku Fisheries Office Hold Institutional Training of Trainers in Ohoi Watkidat, Southeast Maluku; # https://cfi-indonesia.id/blog/cfi-indonesia-perkuat-kapasitas-pokmaswas,-kkp-dan-dkp-maluku-gelar-training-for-trainers-kelembagaan-di-ohoi-watkidat,-maluku-tenggara/. Laha Village, Ambon, Wins Third Place in the 2024 Indonesian Tourism Village Award; # https://cfi-indonesia.id/blog/cfi-indonesia-desa-laha,-ambon,-raih-juara-ketiga-dalam-ajang-anugerah-desa-wisata-indonesia-2024/ # https://cfi-indonesia.id/blog/cfi-indonesia-laha-village,-ambon,-wins-third-place-in-the-indonesian-tourism-village-award-2024/. Joint Research with the Faculty of Fisheries and Marine Science, University of Papua Assessing the Application of EAFM in Snapper and Grouper Fisheries Management in Aisandami, Wondama Bay; # https://cfi-indonesia.id/blog/gef-6-cfi-indonesia-riset-bersama-fpik-universitas-papua-mengkaji-penerapan-eafm-dalam-pengelolaan-perikanan-kakap-dan-kerapu-di-aisandami,-teluk-wondama/. CFI Indonesia : In Support of the Documentation for the Proposed South Buru Marine Protected Area, MMAF and the Maluku Fisheries Office Conduct a Socio-Economic Survey; # https://cfi-indonesia.id/blog/cfi-indonesia-guna-melengkapi-dokumen-pengusulan-calon-kawasan-konservasi-buru-selatan,-kkp-dan-dkp-maluku-gelar-survey-sosial-ekonomi/. Together with the Maluku Fisheries Office, Holding the Second Public Consultation on Prospective Conservation Areas in the Waters of Kepala Madan, South Buru Regency; # https://cfi-indonesia.id/blog/cfi-indonesia-bersama-dkp-maluku-gelar-konsultasi-publik-ii-calon-kawasan-konservasi-di-perairan-kepala-madan-kabupaten-buru-selatan/. MMAF Implements Capacity and Skills Development Program for Traditional Fishers in Teluk Wondama Regency; # https://cfi-indonesia.id/blog/cfi-indonesia-kkp-melaksanakan-kegiatan-peningkatkan-kapasitas-dan-keterampilan-nelayan-tradisional-kabupaten-teluk-wondama/ # https://www.youtube.com/watch?v=q1emnlodE_A&t=605s. Strengthening and Implementation of Community-Based EAFM for Women Fishers in Ambon; # https://cfi-indonesia.id/blog/cfi-indonesia-penguatan-dan-penerapan-community-based-eafm-bagi-wanita-nelayan-di-ambon/. Together with IPB University and Pattimura University, Holding the International Seminar ISOSS 2024 – Encourage Marine Innovation for a Sustainable Future; # https://cfi-indonesia.id/blog/cfi-indonesia-bersama-ipb-university-dan-universitas-pattimura-gelar-seminar-internasional-isoss-2024-dorong-inovasi-kelautan-untuk-masa-depan-berkelanjutan/ # https://www.ipb.ac.id/news/index/2024/11/seminar-internasional-isoss-ipb-university-di-ambon-tekankan-pentingnya-keberlanjutan-laut/. WWF GEF Agency Visit to Ensure the Results of CFI Indonesia’s Work; # https://cfi-indonesia.id/blog/kunjungan-www-gef-agency-memastikan-hasil-hasil-kerja-cfi-indonesia/ # https://www.instagram.com/p/DFW8mGSB_bc/ # https://www.instagram.com/p/DE6YR39hQta/. CFI Indonesia : In Collaboration with Padjadjaran University, Training the Community of Teluk Wondama to Develop Integrated Coastal Ecotourism; # https://cfi-indonesia.id/blog/cfi-indonesia-bersama-universitas-padjajaran-melatih-masyarakat-teluk-wondama-mengembangkan-ekowisata-pesisir-terpadu/ # https://www.youtube.com/watch?v=Ln36WDGBzA0. CFI Indonesia Attends Global Partnership Consultation In Roma; # https://cfi-indonesia.id/blog/cfi-indonesia-attends-global-partnership-consultation-in-roma/ https://cfi-indonesia.id/blog/cfi-indonesia-menghadiri-global-partnership-consultation-di-roma/. CFI Indonesia Participates in the 10th International Water Conference in Montevideo, Uruguay; # https://cfi-indonesia.id/blog/cfi-indonesia-turut-berpartisipasi-dalam-acara-international-water-conference-ke-10-di-montevideo,-urugua/. Supporting Measured Fishing Policy (PIT), GEF-6 CFI Indonesia Facilitates Technical Guidance for Enumerators of the Fisheries Port Information Center; # https://cfi-indonesia.id/blog/dukung-pit,-gef-6-cfi-indonesia-fasilitasi-bimbingan-teknis-enumerator-pusat-informasi-pelabuhan-perikanan/. Whale Shark Data Collection in Kaimana; https://cfi-indonesia.id/blog/cfi-indonesia-pendataan-dan-kajian-bioekologi-populasi-hiu-paus/ https://klikpapua.com/papua-barat/kaimana/sekda-kaimana-ajak-warga-lindungi-hiu-paus-dari-ancaman-sampah-plastik.html https://klikpapua.com/papua-barat/kaimana/dkp-kaimana-bahas-strategi-konservasi-hiu-paus-untuk-jaga-ekosistem-laut.html https://www.rri.co.id/kaimana/daerah/1032241/pentingnya-perlindungan-hiu-paus-dkp-gelar-fgd-di-kaimana https://www.facebook.com/share/p/3Zh9gzVP5pLpc3PS/ https://www.facebook.com/share/p/XBUjmr5bCLvbNUW6/ https://www.instagram.com/p/DD8j-t5BswF/?img_index=1 https://www.instagram.com/p/DFCIvnEqBSy/. GEF 6 CFI Indonesia Facilitating EAFM Training for Fisheries Management Planners in Fisheries Management Area 715, 717, and 718; # https://cfi-indonesia.id/blog/gef-6-cfi-indonesia-fasilitasi-pelatihan-eafm-perencana-pengelolaan-perikanan-wpp-715,-717-dan-718/ # https://www.youtube.com/watch?v=QQST9_aemVk. GEF 6 Participates In The International Event Indo Fisheries 2024 Expo & Forum; # https://cfi-indonesia.id/blog/gef-6-participates-in-the-international-event-indo-fisheries-2024-expo-and-forum/ # https://www.instagram.com/reel/C-P3pbVSS3W/?igsh=MXMzeWRocDh4NnRyeQ==. GEF 6 CFI Indonesia : Support the National Seminar on Marine and Fisheries in Mataram In Order To Achieve Sustainable Marine Resource Management; # https://cfi-indonesia.id/blog/gef-6-cfi-indonesia-dukung-seminar-nasional-kelautan-dan-perikanan-ii-di-mataram-dalam-rangka-menuju-pengelolaan-sumber-daya-laut-berkelanjutan/ # https://cfi-indonesia.id/blog/gef-6-cfi-indonesia-support-national-seminar-on-marine-and-fisheries-ii-in-mataram-in-order-to-achieve-sustainable-marine-resource-management/. GEF 6 CFI Indonesia: Together With Marine and Fisheries Polytechnic – Maluku Facilitate Basic Certification Of BST For 55 Participants From East Seram Regency, Maluku Province (Volume 2); # https://cfi-indonesia.id/blog/gef-6-cfi-indonesia-bersama-poltek-kp-maluku-fasilitasi-sertifikasi-dasar-bst-bagi-55-peserta-dari-kabupaten-seram-bagian-timur,-provinsi-maluku-(jilid-2)/ # https://www.youtube.com/watch?v=VWQxoP0q6M8 # https://cfi-indonesia.id/blog/gef-6-cfi-indonesia-together-with-poltek-kp-maluku-facilitate-basic-certification-of-bst-for-55-participants-from-east-seram-regency,-maluku-province-(volume-2)/. GEF-6 : MMAF Continues to Strengthen the Capacity and Skills of Traditional Fishers in East Seram Regency; https://cfi-indonesia.id/blog/gef-6-kkp-kembali-meningkatkan-kapasitas-dan-keterampilan-nelayan-tradisional-kabupaten-sbt/ # https://www.youtube.com/watch?v=AlYLUrTmqwc. GEF 6 CFI Indonesia: MMAF Improves Again The Capacity And Skills Of Traditional Fishermen In The SBT District; # https://cfi-indonesia.id/blog/gef-6-cfi-indenesia-kkp-improves-again-the-capacity-and-skills-of-traditional-fishermen-in-the-sbt-district/. GEF 6 CFI Indonesia : Support Laha To Enter The Top 50 Best Tourist Villages In The 2024 Adwi Event; # https://cfi-indonesia.id/blog/gef-6-cfi-indonesia-turut-dukung-laha-masuk-50-besar-desa-wisata-terbaik-ajang-adwi-2024/ # https://cfi-indonesia.id/blog/gef-6-cfi-indonesia-support-laha-to-enter-the-top-50-best-tourist-villages-in-the-2024-adwi-event/. Ecoprint Batik Training in Kaimana; https://www.rri.co.id/kaimana/lain-lain/987368/owner-zie-batik-semarang-berharap-kaimana-jadi-ikon-ecoprint https://www.rri.co.id/kaimana/lain-lain/987267/pelatihan-ecoprint-berdayakan-perempuan-nelayan-pesisir-kaimana https://www.rri.co.id/kaimana/lain-lain/987939/freddy-thie-pelatihan-usaha-wanita-nelayan-berlanjut-ke-pemasara https://youtu.be/41kuZtM_XcQ?si=6AlTEqlxUk8GGxnN. GEF 6 CFI Indonesia : Mangrove Crab Bioecology Data Collection; # https://cfi-indonesia.id/blog/gef-6-cfi-indonesia-pengumpulan-data-bioekologi-kepiting-bakau/ # https://www.youtube.com/watch?v=_d9hTqbSf4E # https://cfi-indonesia.id/blog/gef-6-cfi-indonesia-mangrove-crab-bioecology-data-collection/ # https://www.instagram.com/p/DFjjgFVB5Te/?img_index=1. GEF 6 CFI Indonesia : Together With Semarang Fishing Training and Research Center (BBPI Semarang) Apply Crab Folding Bubu Fishing Gear Technology Crab Folding Bubu In East Seram District (FMA 715); # https://cfi-indonesia.id/blog/gef-6-cfi-indonesia-bersama-bbpi-semarang-terapkan-teknologi-alat-penangkapan-ikan-bubu-lipat-kepiting-bubu-lipat-kepiting-di-kabupaten-seram-bagian-timur-(wpp-715)/ # https://www.youtube.com/watch?v=egHuxRqOH3o&t=632s # https://cfi-indonesia.id/blog/gef-6-cfi-indonesia-together-with-bbpi-semarang-apply-crab-folding-bubu-fishing-gear-technology-crab-folding-bubu-in-east-seram-district-(fma-715)/. BBI/BBWI Exhibition; https://infobaru.co.id/2024/08/23/dorong-usaha-kecil-perikanan-pesisir-gef-6-cfi-gelar-talkshow-di-ambon/ https://ambon.tribunnews.com/2024/08/24/talkshow-gef-6-cfi-di-ambon-jadi-momen-dorong-usaha-kecil-perikanan-pesisir#google_vignette https://ambon.antaranews.com/berita/226635/fasilitas-lingkungan-global-cfi-ikuti-puncak-bbi-bbwi-kkp-di-ambon # https://www.youtube.com/watch?v=EMy1AhGvX04&t=25s. Coastal Women of Ambon Seize Ecoprint Batik Business Opportunities While Preserving the Environment and Natural Sustainability; # https://cfi-indonesia.id/blog/perempuan-pesisir-kota-ambon-menangkap-peluang-bisnis-batik-ecoprint-tetap-memuliakan-lingkungan-dan-kelestarian-alam/ https://gemanusantara.net/2024/08/16/perempuan-negeri-laha-ikut-pelatihan-pembuatan-batik-ecoprint-dengan-teknik-mengkukus/. Technical Guidance on Certification and Marketing of Processed Fishery Products (Ambon, August 21, 2024); https://web.facebook.com/100013607026503/ posts/1951856898611192/?mibextid= NTRm0r7WZyOdZZsz&_rdc=1&_rdr. Processed Fishery Product Diversification Activity; https://kaimananews.com/gef-6-wwf-gandeng-dinas-perikanan-kaimana-gelar-kegiatan-diversifikasi-usaha-wanita-nelayan/ https://web.facebook.com/reel/518747190488171. GEF 6 CFI Indonesia : Together with Marine and Fisheries Polytechnic Maluku, Facilitating Basic Safety Training (BST) Certification for 55 Participants from East Seram Regency, Maluku Province (Batch 2); https://cfi-indonesia.id/blog/gef-6-cfi-indonesia-bersama-poltek-kp-maluku-fasilitasi-sertifikasi-dasar-bst-bagi-55-peserta-dari-kabupaten-seram-bagian-timur,-provinsi-maluku-(jilid-2)/. GEF 6 CFI Indonesia : Joint Research with BRIN Reveals the Potential of Local Marine Resource Utilization and Sustainable Fisheries in Kei Kecil Conservation Area, Southeast Maluku; # https://cfi-indonesia.id/blog/gef-6-cfi-indonesia-riset-bersama-brin-ungkap-potensi-pemanfaatan-sdl-dan-perikanan-berkelanjutan-di-kawasan-konservasi-kei-kecil,-maluku-tenggara/ # https://www.youtube.com/watch?v=EETQM-qSMEw&t=77s. GEF 6 CFI Indonesia: Facilitation of Sasi in Werka Waters, Southeast Maluku, as an OECM; # https://cfi-indonesia.id/blog/gef-6-cfi-inonesia-fasilitasi-sasi-di-perairan-werka-(wpp-714)-maluku-tenggara-sebagai-oecm/ # https://www.instagram.com/reel/C98W5iDSjd-/ ?igsh=MXYwZGF4dTI1NnJvaQ==. GEF 6 CFI Indonesia : Southeast Maluku Regional Secretary Inaugurates 15 Capture Fisheries Joint Business Groups (KUB) and Continues to Promote Institutional Capacity Building for Small-Scale Fishers; # https://cfi-indonesia.id/blog/gef-6-cfi-indonesia-sinergi-kkp-dan-dinas-perikanan-maluku-tenggara-dorong-peningkatan-kapasitas-kelembagaan-nelayan-kecil/. Blue Economy KKP: GEF-6 CFI Indonesia Supports Marine Plastic Waste Clean-Up Action in Raja Ampat Regency; # https://cfi-indonesia.id/blog/blue-economy-kkp-gef-6-cfi-indonesia-dukung-aksi-bersih-sampah-plastik-laut-di-kabupaten-raja-ampat/ https://www.rri.co.id/daerah/847960/nelayan-kampung-saporkren-belajar-mengolah-sampah https://rajaampatnews.com/wujudkan-laut-raja-ampat-yang-bersih-kkp-dan-pemda-sosialisasikan-penanganan-sampah-bagi-warga-saporkren/ https://web.facebook.com/reel/518747190488171 # https://www.instagram.com/reel/C9zeMDNSjvf/ ?igsh=MWgxZGd3c2FlMjZvdA==. GEF-6 : MMAF Continues to Strengthen the Capacity and Skills of Traditional Fishers in East Seram Regency; # https://cfi-indonesia.id/blog/gef-6-kkp-kembali-meningkatkan-kapasitas-dan-keterampilan-nelayan-tradisional-kabupaten-sbt/ # https://www.youtube.com/watch?v=AlYLUrTmqwc. GEF 6 : Nusantara Fishing Port (PPN) TernateCollaborates with Fishermen in Morotai Island Regency to Implement E-Pit Application-Based E-Logbook Filling Practice; # https://cfi-indonesia.id/blog/gef-6-ppn-ternate-mempraktekan-pengisian-e-logbook-dengan-aplikiasi-e-pit-di-kabupaten-pulau-morotai/ # https://www.instagram.com/reel/C-Ab6mkSHlf/ ?igsh=MTVhaHE2MjBwYjlvNw==. GEF 6: Socialization of Good Fish Handling Practices (CPIB) Onboard Vessels in Morotai Regency; # https://cfi-indonesia.id/blog/gef-6-sosialisasi-cara-penanganan-ikan-yang-baik-(cpib)-di-atas-kapal,-di-kabupaten-pulau-morotai/. GEF-6 Participates in the International Event Indo Fisheries 2024 Expo & Forum; # https://cfi-indonesia.id/blog/gef-6-berpartispasi-di-ajang-internasional-indo-fisheries-2024-expo-and-forum/. Through the GEF-6 CFI Indonesia Program, MMAF Reviews the Fisheries Management Plans (RPP) for Fisheries Management Areas (WPPNRI) 715 and 717; # https://cfi-indonesia.id/blog/lewat-program-gef-6-cfi-indonesia-kkp-kembali-mereviu-rpp-wppnri-715-dan-717/. Capacity Building for Kaimana Fishers’ Institutional Management; https://youtu.be/PIX3K6eweJI?si=18lJ4izIxdDEHX9h # https://www.youtube.com/watch?v=NgOd18OWLSk&t=277s. GEF 6 : Empowering Business Actors to Support the Sustainability of the Fisheries Sector in Southeast Maluku Regency; # https://cfi-indonesia.id/blog/pemberdayaan-pelaku-usaha-untuk-mendukung-keberlanjutan-sektor-perikanan-di-kabupaten-maluku-tenggara/. GEF 6 : MMAF Collaborates with Kaimana Fisheries Office to Hold Business Diversification Program for Women Fishers (Batch 2); # https://cfi-indonesia.id/blog/gef-6-kkp-gandeng-dinas-perikanan-kaimana-gelar-kegiatan-diversifikasi-usaha-wanita-nelayan-(jilid-2)/. GEF 6: Together with the West Papua Fisheries Office, Provide BPJS Employment Protection to Protect Fishers in South Manokwari; # https://cfi-indonesia.id/blog/gef-6-bersama-dkp-papua-barat-lindungi-nelayan-di-mansel-dengan-bpjs-ketenagakerjaan/ https://papuabarat.tribunnews.com/2024/06/27/dkp-papua-barat-lindungi-nelayan-di-mansel-dengan-bpjs-ketenagakerjaan https://youtu.be/u1EWOSdQLds?si=vx3ASWZ4vtiZpAoa # https://www.youtube.com/watch?v=r4p-4baH_Rk&t=9s. GEF 6: In Collaboration with the Maluku Provincial Fisheries Office, Continuing the Marking of Fishing Vessels in East Seram Regency; # https://cfi-indonesia.id/blog/gef-6-bersama-dkp-provinsi-maluku-melanjutkan-fasilitasi-penandaan-kapal-perikanan-di-kabupaten-sbt/. Through the GEF 6 CFI Indonesia Program, the East Seram Women's Group Develops Roa Chili Sauce Products and Promotes Licensing Management; # https://cfi-indonesia.id/blog/melalui-program-gef-6-cfi-indonesia-kelompok-perempuan-seram-timur-kembangkan-prodak-sambal-roa-dan-dorong-pengurusan-perijinannya/. Through the GEF-6 CFI Indonesia Program, the East Seram Fisheries Office Assists Its Small-Scale Fishers with Fishing Vessel Registration Certificate (TDKP); # https://cfi-indonesia.id/blog/melalui-program-gef-6-cfi-indonesia-giliran-dinas-perikanan-seram-bagian-timur-bantu-tdkp-nelayan-kecilnya/. GEF 6 : Seaweed Diversification Training as an Alternative to Boost Livelihoods in Southeast Maluku (Batch II); # https://cfi-indonesia.id/blog/gef-6-pelatihan-diversifikasi-rumput-laut-sebagai-alternatif-peningkatan-ekonomi-masyarakat-pesisir-maluku-tenggara-(jilid-ii)/. GEF-6: MMAF and Maluku Fisheries Office Conduct Socialization on Fishing Vessel Registration and Marking in Maluku; # https://cfi-indonesia.id/blog/gef-6-kkp-bersama-dkp-maluku-sosialisasi-pendaftaran-dan-penandaan-kapal-perikanan-di-maluku/. Technical Guidance on the Adoption of CCRF and EAFM Indicators; # https://www.instagram.com/reel/C9bzX4OSqTz/?igsh= MW55MWFhYXk2eTIxMQ==. GEF-6 CFI Indonesia Program Creates Significant Impact for Coastal Communities; # https://cfi-indonesia.id/blog/progam-gef-6-cfi-indoensia-berdampak-signifikan-bagi-masyarakat-pesisir/. Minister of Marine Affairs and Fisheries Launches Measured Fishing Modeling in Tual; # https://cfi-indonesia.id/blog/menteri-kelautan-dan-perikanan-lauching-modelling-penangkapan-ikan-terukur-di-kota-tual/. MMAF Conducts Public Consultation on Flying Fish Fisheries Management Plan (RPP); # https://cfi-indonesia.id/blog/kkp-gelar-konsultasi-publik-rpp-ikan-terbang/. GEF 6: Promoting Southeast Maluku’s Icon through Eco-Friendly and High-Value Ecoprint; # https://cfi-indonesia.id/blog/gef-6-menggagas-ikon-maluku-tenggara-melalui-ecoprint-ramah-lingkungan-dan-bernilai-tinggi/ https://malraterkini.com/tingkatkan-pendapatan-nelayan-di-maluku-tenggara-dilatih-ecoprint/ https://youtu.be/-wUFTCzQb64. Gef-6 : Facilitating the MoU on Marketing of Processed Fishery Products by MSMEs in Southeast Maluku; # https://cfi-indonesia.id/blog/gef-6-fasilitasi-mou-marketing-produk-olahan-perikanan-umk-maluku-tenggara/ # https://www.youtube.com/watch?v=uDL6kXvUQhk. Revenue Sharing and Non-Tax State Revenue (PNBP) for Sustainable Fisheries; # https://cfi-indonesia.id/blog/dana-bagi-hasil-dan-pnpb-untuk-perikanan-yang-berkelanjutan/. Training on Hull Repair, Net Repair, and GPS Utilization in Watkidat, Southeast Maluku; # https://www.youtube.com/watch?v=CjKYQt9P1Hk. MMAF Encourages Acceleration of Upstream–Downstream Business Cooperation in Capture Fisheries in Tual; # https://cfi-indonesia.id/blog/*kkp-dorong-percepatan-pelaksanaan-kerja-sama-hulu-hilir-bisnis-perikanan-tangkap-di-kota-tual*/. Gender Mainstreaming (PUG) Program in the Ministry of Marine Affairs and Fisheries (MMAF).; # https://www.youtube.com/watch?v=tLw9p8Hn6vo&t=10s. GEF-6 CFI Indonesia Participates in the 2024 Integrated Technical Working Meeting of MMAF; # https://cfi-indonesia.id/blog/gef-6-cfi-indonesia-ikut-berpartidpasi-di-rakernis-terpadu-kkp-tahun-2024/ # https://www.instagram.com/reel/C4M-ejKPMoZ/?igsh=NDc1c2FoY3huZW92 # https://www.youtube.com/watch?v=jZvtrOMZlH8. GEF 6 : Nusantara Fishing Port (PPN) Ternate Holds Coordination Meeting of the Fisheries Management Unit (UPP) for Fisheries Management Area of Indonesia (WPPNRI) 717; # https://cfi-indonesia.id/blog/gef-6-ppn-ternate-gelar-rapat-koordinasi-unit-pengelola-perikanan-wppnri-717/. Komnas Kajiskan Strengthens Synergy to Advance MMAF’s Blue Economy Priorities; # https://cfi-indonesia.id/blog/sinergitas-komnas-kajiskan-wujudkkan-program-prioritas-kkp-blue-economy/. Hawear: The Local Tradition of the Kei People in Preserving Nature; # https://cfi-indonesia.id/blog/hawear-budaya-lokal-orang-kei-menjaga-alamnya/. MMAF Participates Drafting the WTO Fisheries Subsidies Agreement; # https://cfi-indonesia.id/blog/kkp-ikut-penyusunan-teks-fisheries-subsidies-agreement-wto/. Wave Conqueror Woman Video; # https://www.youtube.com/watch?v=aC9OkCX0bow&t=245s. MMAF Holds GEF-6 PSC Meeting to Approve the 2024 AWPB and Finalize the GA Addendum; # https://cfi-indonesia.id/blog/kkp-gelar-psc-meeting-gef-6-sahkan-awpb-2024-dan-finaliasi-amanden-ga/. Identification of the Indigenous Community in Ohoirenan, Southeast Maluku; # https://www.youtube.com/watch?v= WNB8RPGveg4&t=3s. GEF-6 : Identification of the Indigenous Community of Negeri Kiltay, East Seram Regency, Maluku; # https://www.youtube.com/watch?v=obBbVcK3xog. Whale shark in Kaimana; # https://www.youtube.com/watch?v=ew7VS1Xzg9E. # INDONESIA HEBAT : TEMUKAN PENYU RAKSASA, PENYU BELIMBING ADA DI PULAU BURU, TERANCAM PUNAH; # https://www.youtube.com/watch?v=M6CqhrZWfKA. # BIJAK MENGELOLA IKAN TERBANG UNTUK ANAK CUCU KITA; # https://www.youtube.com/watch?v=cbsY61PCw8o. A total of more than 100 news items, including press releases, videos, and photos of the activities, were disseminated. Some of the publications included press releases in local online media and on the GEF 6 website (www.cfi-indonesia.id), and photos and videos released on YouTube and Instagram. The materials and links to the activity publications can be found in Appendix 1.

### Reflows (for NGIs only)

Note: This field is not publicly disclosed.

Please attach the actual reflow (both cumulative, and reflow in the current year), the potential reflows, and other relevant information, including the quarterly investor reports and/or presentations materials the Executing Agencies provide to GEF Agencies. Select the disclosure level based on each document’s confidentiality. Please provide an explanation for any deviations between projected and actual reflows, along with any updates to reflow projections. Include any relevant changes to the project, events, or notifications received from Executing Agencies that may adversely affect future reflows

### Adaptive Management

Please check all applicable modifications made to the project during this reporting period noting a description of the change, justification for the change and the date of No-Objection given by the WWF GEF Agency. If not applicable, please leave blank. Please see guidance on definitions and procedures for Major and Minor Amendments. Note: it is recommended that all changes be discussed in advance with the GEF Program Manager. Category of change; Description of the change; Justification; Date of No-Objection by WWF GEF. Major Amendments. ☐Project Scope. ☐ Project Objective. ☐>5% Increase in financing. Minor Amendments. ☐ Results framework; CFI project extended the Results Framework to support priority programs of the MMAF. It includes now two newly created MPA and; This adjustment was necessary due to the original project design, developed in 2015, which no longer fully aligned with the Ministry’s current vision and mission. As a result, CFI Indonesia now incorporates MMAF’s priority programs to ensure that project outcomes are consistent with the expectations of the Minister and relevant stakeholders.; January 30, 2024. ☐ Components and cost. ☐Institutional and implementation arrangements. ☒Financial management. ☐Implementation schedule. ☐ Executing Entity. ☐Executing Entity Category. ☐Minor project objective change. ☐ Safeguards. ☐ Risk analysis. ☐ Increase of GEF project financing up to 5%. ☐ Co-financing. ☐ Location of project activity. ☐ Other: <fill in>. For any proposed or anticipated changes to the project this coming year, please describe below what those changes would be (e.g., in the workplan or results framework) and provide justification. Note: It may be helpful to reference project lessons, challenges, strengths and/or the project theory of change. Best practices The Project Document states that CFI Indonesia's objective is to contribute to coastal fisheries in FMA 715, 717, and 718 by providing sustainable environmental, social, and economic benefits and demonstrating an effective, integrated, sustainable, and replicable coastal fisheries management model characterized by good governance and effective incentives. The word "replicable" is crucial here, meaning that the project must be designed so that each activity does not stand alone but is interconnected with each other, creating component outcomes. In this case, the interconnectedness between these activities can become a learning process that generates best practices that can be replicated in other regions, even other countries. Sasi Label and Sasi Co-Management are two best practices from CFI Indonesia that have been recognized by the Ministry of Marine Affairs and Fisheries and other countries. Therefore, going forward, a Theory of Change needs to be developed with the aim of creating a learning process to create these best practices by design.

### Geolocation Information

Please provide a location name, latitude and longitude for key locations of GEF-financed activities. Depending on the scope of the project, it may only be necessary to provide geolocation of the capital city. The format should be in Decimal Degrees WGS84 format only – e.g. not degrees, minutes or seconds. Please use ‘-‘ instead of ‘S’ and avoid inserting ‘°’). As an alternative, you may enter a GEOname ID for locations of GEF-financed activities under this project. Location and activity description is optional. Maps or shapefiles are recommended, but optional. Please use this Guide for additional details. Location Name; Latitude; Longitude; Geo Name ID; Location & Activity Description (Optional). Kilitay; -3.892282; 130.910769; East Seram - Sasi Label & Sasi Co-Management. Laha; -3.713076; 128.099158; Ambon – Alternative Livelihood. Menarbu; -2.401161; 134.563340; Wondama Bay - Sasi Label & Sasi Co-Management. Aisandami; -2.488666; 134.541245; Wondama Bay - Sasi Label. Arguni Atas; -3.075250; 133.861667; Kaimana – Alternatif Lifelihood. Waho; -3.426573; 133.568555; Kaimana - Sasi Label. Padarni; -0.858752; 134.070442; Manokwari – Alternative Livelihood.

Appendix 1. List of knowledge activities/products

| No | Activities | Link |
| --- | --- | --- |
|  | CFI Indonesia: Re-organizes ARM 2024 and Prepares AWPB 2025, Involving Coastal Women Champions from 6 Regencies | https://cfi-indonesia.id/blog/cfi-indonesia-gelar-kembali-arm-2024-dan-penyusunan-awpb-2025-ikut-sertakan-champion-perempuan-pesisir-6-kabupaten/ https://kkp.go.id/djpt/kkp-ajak-gef-6-perluas-kerja-sama-ekonomi-biru-oVNX/detail.html https://www.antaranews.com/berita/4525801/kkp-ajak-gef-6-perluas-kerja-sama-ekonomi-biru#google_vignette |
|  | Technical Guidance on the Application of Fuel-Saving Technology for Fishing Fleets | https://cfi-indonesia.id/blog/cfi-indonesia-bimbingan-teknis-penerapan-teknologi-alat-penghemat-bbm-untuk-armada-penangkapan/ https://cfi-indonesia.id/blog/cfi-indonesia-technical-guidance-on-the-application-of-fuel-saving-device-technology-for-fishing-fleets/ https://www.youtube.com/watch?v=LbtBa9jfiwI |
|  | The Ministry of Marine Affairs and Fisheries (KKP) Partners with the Southeast Maluku Regency Fisheries Office to Improve the Capacity and Skills of 13 Small-Scale Fishermen's Cooperatives (KUB) (Part 2) | https://cfi-indonesia.id/blog/cfi-indonesia-kkp-gandeng-dinas-perikanan-kabupaten-maluku-tenggara-tingkatkan-ketrampilan-nelayan-kecil-(jilid-2)/ |
|  | The Ministry of Marine Affairs and Fisheries Holds Fishing Logbook Socialization in Pasanea Village, Central Maluku | https://www.salawaku.com/daerah/kkp-gelar-sosialisasi-logbook-penangkapan-ikan-di-desa-pasanea-maluku-tengah.html |
|  | Fishing Vessel Seaworthiness Certificate (SKKP) Issuance Booth in Mandala Village, Jayapura - Supporting Fishermen's Safety and Operational Standards | https://cfi-indonesia.id/blog/cfi-indonesia-kegiatan-gerai-penerbitan-sertifikat-kelaikan-kapal-perikanan-(skkp)-di-kampung-mandala,-jayapura-mendukung-keselamatan-dan-standar-operasional-nelayan/ |
|  | Together with the Maluku Fisheries Office, Facilitates the Draft Governor's Regulation on Turtle Fishing at the Ministry of Home Affairs to Ensure Compliance with National Regulations | https://cfi-indonesia.id/blog/cfi-indonesia-bersama-dkp-maluku-laksanakan-fasilitasi-ranpergub-rad-penyu-di-kemendagri-guna-memastikan-kesesuaian-regulasi-nasional/ https://www.youtube.com/watch?v=M6CqhrZWfKA |
|  | Fishery Stock Assessment Facilitation in Fisheries Management Areas (WPP) 715, 717, and 718 | https://cfi-indonesia.id/blog/cfi-indonesia-fasilitasi-kajian-stok-perikanan-di-wilayah-pengelolaan-perikanan-(wpp)-715,-717-dan-718/ |
|  | Uncovering the Condition of the Coastal Ecosystem and Fisheries of Southern Buru Island Supporting Conservation Area Designation Through an Expedition by the Faculty of Fisheries and Marine Sciences (FPIK) of IPB University | https://cfi-indonesia.id/blog/cfi-indonesia-menguak-kondisi-ekosistem-pesisir-dan-perikanan-pulau-buru-bagian-selatan-dukung-pencadangan-kawasan-konservasi-melalui-ekspedisi-fpik-ipb-university/ https://www.ipb.ac.id/news/index/2024/10/ekspedisi-himiteka-ix-ipb-university-mengungkap-spesies-langka-penyu-di-pulau-buru/ https://korpusipb.com/advertorial/ekspedisi-himasper-kembara-moloku-rhizossia-bersatu-selamatkan-laut-maluku/ https://www.ipb.ac.id/news/index/2024/10/ekspedisi-himiteka-ix-ipb-university-mengungkap-spesies-langka-penyu-di-pulau-buru/ https://www.youtube.com/watch?v=j1PPkDlqHDo |
|  | Ministry of Marine Affairs and Fisheries Disseminates Identification and Mapping Results of the Negeri Kiltay Indigenous Community in East Seram | https://cfi-indonesia.id/blog/cfi-indonesia-kkp-diseminasi-hasil-identifikasi-dan-pemetaan-masyarakat-adat-negeri-kiltay-di-seram-bagian-timur/ https://www.youtube.com/watch?v=fUmDfFjPu7A |
|  | CFI Indonesia: Conducting a Bioecological Study of Mud Crabs in the 715, 717, and 718 Fisheries Management Areas | https://cfi-indonesia.id/blog/cfi-indonesia-melaksanakan-kajian-bioekologi-kepiting-bakau-di-wppnri-715,-717,-dan-718/ https://www.youtube.com/watch?v=_d9hTqbSf4E |
|  | CFI Indonesia: Ecoprint Batik Training for Fisherwomen in East Seram Regency | https://cfi-indonesia.id/blog/cfi-indonesia-pelatihan-pembuatan-batik-ecoprint-bagi-wanita-nelayan-di-kabupaten-seram-bagian-timur/ https://www.youtube.com/watch?v=TGqdUP5yII0 |
|  | Facilitating a Knowledge Management System for Enumerators and Fisheries Extension Workers in the 715, 717, and 718 Fisheries Management Areas | https://cfi-indonesia.id/blog/cfi-indonesia-fasilitasi-sistem-manajemen-pengetahuan-bagi-para-enumerator-penyuluh-perikanan-di-wppnri-715,-717-dan-718/ |
|  | CFI Indonesia: Encouraging the Empowerment of Small-Scale Fishermen, Ministry of Marine Affairs and Fisheries and the Southeast Maluku Fisheries Service Facilitate the Issuance of Small-Scale Pass Documents for Small-Scale Fishermen | https://cfi-indonesia.id/blog/cfi-indonesia-dorong-pemberdayaan-nelayan-kecil,-kkp-dan-dinas-perikanan-maluku-tenggara-fasilitasi-penerbitan-dokumen-pas-kecil-bagi-nelayan-kecil/ |
|  | CFI-Indonesia: Together with the Raja Ampat Fisheries Service, Train Fishermen to Repair Boat Motor | https://cfi-indonesia.id/blog/cfi-indonesia-bersama-dinas-perikanan-raja-ampat-latih-nelayan-perbaiki-motor-tempal/ https://www.youtube.com/watch?v=Gz0BtL7QoC8 |
|  | Ministry of Marine Affairs and Fisheries Facilitates Assistance in the Drafting of a Regent's Regulation Establishing the Ohoi Ohoirenan Indigenous Community in Southeast Maluku | https://cfi-indonesia.id/blog/cfi-indonesia-kkp-mendamping-percepatan-penetapan-masyarakat-hukum-adat-ohoi-ohoirenan-maluku-tenggara/ |
|  | Survey Sasi Fishery Resources in Windesi District, Teluk Wondama Regency | https://cfi-indonesia.id/blog/cfi-indonesia-survey-sumberdaya-perikanan-sasi-distrik-windesi-kabupaten-teluk-wondama/ |
|  | Issuance of Minister of Maritime Affairs and Fisheries Regulation No. 76 of 2024, Regulating Better Management of Flying Fish Fisheries | https://cfi-indonesia.id/blog/cfi-indonesia-terbitnya-peraturan-menteri-kelautan-dan-perikanan-nomor-76-tahun-2024,-mengatur-pengelolaan-perikanan-ikan-terbang-lebih-baik/ https://www.youtube.com/watch?v=cbsY61PCw8o |
|  | Together with the Fisheries Service, SBT Holds Basic Diving Training for Civil Servants and Community Supervisory Groups | https://cfi-indonesia.id/blog/cfi-indonesia-bersama-dinas-perikanan-sbt-gelar-pelatihan-selam-dasar-bagi-asn-dan-kelompok-masyarakat-pengawas/ |
|  | The Ministry of Maritime Affairs and Fisheries, Through the Ternate PPN, Holds a Coordination Meeting of the UPP WPPNRI 717 | https://cfi-indonesia.id/blog/cfi-indonesia-kkp-melaui-ppn-ternate-gelar-kegiatan-rapat-rapat-koordinasi-unit-pengelolaan-perikanan-wilayah-pengelolaan-perikanan-negara-republik-indonesia-(upp-wppnri)-717/ |
|  | The Ministry of Maritime Affairs and Fisheries Encourages Acceleration of MHA Ohoirenan Ratification in Southeast Maluku Regency | https://cfi-indonesia.id/blog/cfi-indonesia-kkp-dorong-percepatan-pengesahan-mha-ohoi-ohoirenan-kabupaten-maluku-tenggara/ https://www.youtube.com/watch?v=OarRbPh2c7Y |
|  | Together with Poltek KP Kampus Maluku, Facilitates BST Certification for 30 Participants from Southeast Maluku Regency, Maluku Province (Volume III) | https://cfi-indonesia.id/blog/cfi-indonesia-bersama-poltek-kp-kampus-maluku,-fasilitasi-sertifikasi-bst-bagi-30-peserta-dari-kabupaten-maluku-tenggara,-provinsi-maluku/ https://www.youtube.com/watch?v=VWQxoP0q6M8&t=52s |
|  | To Strengthen the Capacity of Community Development Groups (Pokmaswas), the Ministry of Maritime Affairs and Fisheries (KKP) and the Maluku DKP Hold Institutional Training for Trainers in Ohoi Watkidat, Southeast Maluku | https://cfi-indonesia.id/blog/cfi-indonesia-perkuat-kapasitas-pokmaswas,-kkp-dan-dkp-maluku-gelar-training-for-trainers-kelembagaan-di-ohoi-watkidat,-maluku-tenggara/ |
|  | Laha Village, Ambon, Wins Third Place in the 2024 Indonesian Tourism Village Award | https://cfi-indonesia.id/blog/cfi-indonesia-desa-laha,-ambon,-raih-juara-ketiga-dalam-ajang-anugerah-desa-wisata-indonesia-2024/ https://cfi-indonesia.id/blog/cfi-indonesia-laha-village,-ambon,-wins-third-place-in-the-indonesian-tourism-village-award-2024/ |
|  | Joint Research with the Faculty of Fisheries and Marine Sciences, University of Papua, Examines the Implementation of EAFM in Snapper and Snapper Fisheries Management Grouper in Aisandami, Wondama Bay | https://cfi-indonesia.id/blog/gef-6-cfi-indonesia-riset-bersama-fpik-universitas-papua-mengkaji-penerapan-eafm-dalam-pengelolaan-perikanan-kakap-dan-kerapu-di-aisandami,-teluk-wondama/ |
|  | CFI Indonesia: To Complete the Proposed Documents for the South Buru Conservation Area, the Ministry of Marine Affairs and Fisheries (KKP) and the Maluku Department of Marine Affairs and Fisheries (DKP) Conduct a Socio-Economic Survey | https://cfi-indonesia.id/blog/cfi-indonesia-guna-melengkapi-dokumen-pengusulan-calon-kawasan-konservasi-buru-selatan,-kkp-dan-dkp-maluku-gelar-survey-sosial-ekonomi/ |
|  | Together with the Maluku Department of Marine Affairs and Fisheries, they Hold the Second Public Consultation for the Prospective Conservation Area in the Kepala Madan Waters of South Buru Regency | https://cfi-indonesia.id/blog/cfi-indonesia-bersama-dkp-maluku-gelar-konsultasi-publik-ii-calon-kawasan-konservasi-di-perairan-kepala-madan-kabupaten-buru-selatan/ |
|  | KKP Conducts Capacity and Skills Improvement Activities for Traditional Fishermen in Wondama Bay Regency | https://cfi-indonesia.id/blog/cfi-indonesia-kkp-melaksanakan-kegiatan-peningkatkan-kapasitas-dan-keterampilan-nelayan-tradisional-kabupaten-teluk-wondama/ https://www.youtube.com/watch?v=q1emnlodE_A&t=605s |
|  | Strengthening and Implementing Community-Based EAFM for Women Fishermen in Ambon | https://cfi-indonesia.id/blog/cfi-indonesia-penguatan-dan-penerapan-community-based-eafm-bagi-wanita-nelayan-di-ambon/ |
|  | Together with IPB University and Pattimura University, they Hold the ISOSS 2024 International Seminar - Encouraging Marine Innovation for a Sustainable Future | https://cfi-indonesia.id/blog/cfi-indonesia-bersama-ipb-university-dan-universitas-pattimura-gelar-seminar-internasional-isoss-2024-dorong-inovasi-kelautan-untuk-masa-depan-berkelanjutan/ https://www.ipb.ac.id/news/index/2024/11/seminar-internasional-isoss-ipb-university-di-ambon-tekankan-pentingnya-keberlanjutan-laut/ |
|  | GEF Agency's WWW Visit Ensures CFI Indonesia's Work Results | https://cfi-indonesia.id/blog/kunjungan-www-gef-agency-memastikan-hasil-hasil-kerja-cfi-indonesia/ https://www.instagram.com/p/DFW8mGSB_bc/ https://www.instagram.com/p/DE6YR39hQta/ |
|  | CFI Indonesia: Together with Padjajaran University, they Train the Wondama Bay Community to Develop Integrated Coastal Ecotourism | https://cfi-indonesia.id/blog/cfi-indonesia-bersama-universitas-padjajaran-melatih-masyarakat-teluk-wondama-mengembangkan-ekowisata-pesisir-terpadu/ https://www.youtube.com/watch?v=Ln36WDGBzA0 |
|  | CFI Indonesia Attends Global Partnership Consultation in Rome | https://cfi-indonesia.id/blog/cfi-indonesia-attends-global-partnership-consultation-in-roma/ |
|  | CFI Indonesia Participates in the International Water Conference 10th in Montevideo, Uruguay | https://cfi-indonesia.id/blog/cfi-indonesia-turut-berpartisipasi-dalam-acara-international-water-conference-ke-10-di-montevideo,-urugua/ |
|  | GEF 6 CFI Indonesia Facilitates Technical Guidance for Enumerators at the Fisheries Port Information Center in Support of PIT | https://cfi-indonesia.id/blog/dukung-pit,-gef-6-cfi-indonesia-fasilitasi-bimbingan-teknis-enumerator-pusat-informasi-pelabuhan-perikanan/ |
|  | Kaimana Whale Shark Data Collection | https://cfi-indonesia.id/blog/cfi-indonesia-pendataan-dan-kajian-bioekologi-populasi-hiu-paus/ https://klikpapua.com/papua-barat/kaimana/sekda-kaimana-ajak-warga-lindungi-hiu-paus-dari-ancaman-sampah-plastik.html https://klikpapua.com/papua-barat/kaimana/dkp-kaimana-bahas-strategi-konservasi-hiu-paus-untuk-jaga-ekosistem-laut.html https://www.rri.co.id/kaimana/daerah/1032241/pentingnya-perlindungan-hiu-paus-dkp-gelar-fgd-di-kaimana https://www.facebook.com/share/p/3Zh9gzVP5pLpc3PS/ https://www.facebook.com/share/p/XBUjmr5bCLvbNUW6/ https://www.instagram.com/p/DD8j-t5BswF/?img_index=1 https://www.instagram.com/p/DFCIvnEqBSy/ |
|  | GEF 6 CFI Indonesia: Facilitates EAFM Training for Fisheries Management Planners in WPP 715, 717, and 718 | https://cfi-indonesia.id/blog/gef-6-cfi-indonesia-fasilitasi-pelatihan-eafm-perencana-pengelolaan-perikanan-wpp-715,-717-dan-718/ https://www.youtube.com/watch?v=QQST9_aemVk |
|  | GEF 6 Participates in the International Event Indo Fisheries 2024 Expo & Forum | https://cfi-indonesia.id/blog/gef-6-participates-in-the-international-event-indo-fisheries-2024-expo-and-forum/ https://www.instagram.com/reel/C-P3pbVSS3W/?igsh=MXMzeWRocDh4NnRyeQ== |
|  | GEF 6 CFI Indonesia: Supports the National Seminar on Marine Affairs and Fisheries in Mataram to Achieve Sustainable Marine Resource Management | https://cfi-indonesia.id/blog/gef-6-cfi-indonesia-dukung-seminar-nasional-kelautan-dan-perikanan-ii-di-mataram-dalam-rangka-menuju-pengelolaan-sumber-daya-laut-berkelanjutan/ https://cfi-indonesia.id/blog/gef-6-cfi-indonesia-support-national-seminar-on-marine-and-fisheries-ii-in-mataram-in-order-to-achieve-sustainable-marine-resource-management/ |
|  | GEF 6 CFI Indonesia: Together with Poltek KP Maluku, Facilitates Basic BST Certification for 55 Participants from East Seram Regency, Maluku Province (Volume 2) GEF 6 CFI Indonesia: Together with Poltek KP Maluku Facilitates Basic Certification of BST for 55 Participants from East Seram Regency, Maluku Province (Volume 2) | https://cfi-indonesia.id/blog/gef-6-cfi-indonesia-bersama-poltek-kp-maluku-fasilitasi-sertifikasi-dasar-bst-bagi-55-peserta-dari-kabupaten-seram-bagian-timur,-provinsi-maluku-(jilid-2)/ https://www.youtube.com/watch?v=VWQxoP0q6M8 https://cfi-indonesia.id/blog/gef-6-cfi-indonesia-together-with-poltek-kp-maluku-facilitate-basic-certification-of-bst-for-55-participants-from-east-seram-regency,-maluku-province-(volume-2)/ |
|  | GEF-6: Ministry of Marine Affairs and Fisheries (KKP) Again Improves the Capacity and Skills of Traditional Fishermen in SBT Regency | https://cfi-indonesia.id/blog/gef-6-kkp-kembali-meningkatkan-kapasitas-dan-keterampilan-nelayan-tradisional-kabupaten-sbt/ https://www.youtube.com/watch?v=AlYLUrTmqwc |
|  | GEF 6 CFI Indonesia: KKP Again Improves the Capacity and Skills of Traditional Fishermen in the SBT District | https://cfi-indonesia.id/blog/gef-6-cfi-indenesia-kkp-improves-again-the-capacity-and-skills-of-traditional-fishermen-in-the-sbt-district/ |
|  | GEF 6 CFI Indonesia: Supports Laha's Adwi 2024 Tourism Village Ranking | https://cfi-indonesia.id/blog/gef-6-cfi-indonesia-turut-dukung-laha-masuk-50-besar-desa-wisata-terbaik-ajang-adwi-2024/ https://cfi-indonesia.id/blog/gef-6-cfi-indonesia-support-laha-to-enter-the-top-50-best-tourist-villages-in-the-2024-adwi-event/ |
|  | Ecoprint Batik Training in Kaimana | https://www.rri.co.id/kaimana/lain-lain/987368/owner-zie-batik-semarang-berharap-kaimana-jadi-ikon-ecoprint https://www.rri.co.id/kaimana/lain-lain/987267/pelatihan-ecoprint-berdayakan-perempuan-nelayan-pesisir-kaimana https://www.rri.co.id/kaimana/lain-lain/987939/freddy-thie-pelatihan-usaha-wanita-nelayan-berlanjut-ke-pemasara https://youtu.be/41kuZtM_XcQ?si=6AlTEqlxUk8GGxnN |
|  | GEF 6 CFI Indonesia: Mangrove Crab Bioecology Data Collection | https://cfi-indonesia.id/blog/gef-6-cfi-indonesia-pengumpulan-data-bioekologi-kepiting-bakau/ https://www.youtube.com/watch?v=_d9hTqbSf4E https://cfi-indonesia.id/blog/gef-6-cfi-indonesia-mangrove-crab-bioecology-data-collection/ https://www.instagram.com/p/DFjjgFVB5Te/?img_index=1 |
|  | Technical Guidance for Certification and Marketing of Processed Fishery Products (Ambon, August 21, 2024) | https://web.facebook.com/100013607026503/ posts/1951856898611192/?mibextid= NTRm0r7WZyOdZZsz&_rdc=1&_rdr |
|  | Processed Product Diversification Activity | https://kaimananews.com/gef-6-wwf-gandeng-dinas-perikanan-kaimana-gelar-kegiatan-diversifikasi-usaha-wanita-nelayan/ https://web.facebook.com/reel/518747190488171 |
|  | GEF 6 CFI Indonesia: Collaborating with Poltek Kp Maluku, Facilitates Basic BST Certification for 55 Participants from East Seram Regency, Maluku Province (Volume 2) | https://cfi-indonesia.id/blog/gef-6-cfi-indonesia-bersama-poltek-kp-maluku-fasilitasi-sertifikasi-dasar-bst-bagi-55-peserta-dari-kabupaten-seram-bagian-timur,-provinsi-maluku-(jilid-2)/ |
|  | GEF 6 CFI Indonesia: Joint Research with BRIN Reveals Potential for Sustainable Fisheries and Sustainable Fisheries in the Kei Kecil Conservation Area, Southeast Maluku | https://cfi-indonesia.id/blog/gef-6-cfi-indonesia-riset-bersama-brin-ungkap-potensi-pemanfaatan-sdl-dan-perikanan-berkelanjutan-di-kawasan-konservasi-kei-kecil,-maluku-tenggara/ https://www.youtube.com/watch?v=EETQM-qSMEw&t=77s |
|  | GEF 6 CFI Indonesia: Facilitating Sasi in Werka Waters, Southeast Maluku as an OECM | https://cfi-indonesia.id/blog/gef-6-cfi-inonesia-fasilitasi-sasi-di-perairan-werka-(wpp-714)-maluku-tenggara-sebagai-oecm/ https://www.instagram.com/reel/C98W5iDSjd-/ ?igsh=MXYwZGF4dTI1NnJvaQ== |
|  | GEF 6 CFI Indonesia: Southeast Maluku Regional Secretary Inaugurates 15 Capture Fisheries Units and Continues to Encourage Institutional Capacity Building for Small-Scale Fishermen | https://cfi-indonesia.id/blog/gef-6-cfi-indonesia-sinergi-kkp-dan-dinas-perikanan-maluku-tenggara-dorong-peningkatan-kapasitas-kelembagaan-nelayan-kecil/ |
|  | KKP Blue Economy: GEF 6 CFI Indonesia Supports Marine Plastic Debris Clean-Up in Raja Ampat Regency | https://cfi-indonesia.id/blog/blue-economy-kkp-gef-6-cfi-indonesia-dukung-aksi-bersih-sampah-plastik-laut-di-kabupaten-raja-ampat/ https://www.rri.co.id/daerah/847960/nelayan-kampung-saporkren-belajar-mengolah-sampah https://rajaampatnews.com/wujudkan-laut-raja-ampat-yang-bersih-kkp-dan-pemda-sosialisasikan-penanganan-sampah-bagi-warga-saporkren/ https://web.facebook.com/reel/518747190488171 https://www.instagram.com/reel/C9zeMDNSjvf/ ?igsh=MWgxZGd3c2FlMjZvdA== |
|  | GEF-6: KKP Again Enhances the Capacity and Skills of Traditional Fishermen in SBT Regency | https://cfi-indonesia.id/blog/gef-6-kkp-kembali-meningkatkan-kapasitas-dan-keterampilan-nelayan-tradisional-kabupaten-sbt/ https://www.youtube.com/watch?v=AlYLUrTmqwc |
|  | GEF 6: Ternate PPN and Morotai Island Regency Fishermen Practice Filling Out E-Logbooks Based on the E-Pit Application | https://cfi-indonesia.id/blog/gef-6-ppn-ternate-mempraktekan-pengisian-e-logbook-dengan-aplikiasi-e-pit-di-kabupaten-pulau-morotai/ https://www.instagram.com/reel/C-Ab6mkSHlf/ ?igsh=MTVhaHE2MjBwYjlvNw== |
|  | GEF 6: Socialization of Good Fish Handling Practices (CPIB) on Board Vessels in Morotai Island Regency | https://cfi-indonesia.id/blog/gef-6-sosialisasi-cara-penanganan-ikan-yang-baik-(cpib)-di-atas-kapal,-di-kabupaten-pulau-morotai/ |
|  | GEF 6 Participates in the International Indo Fisheries 2024 Expo & Forum | https://cfi-indonesia.id/blog/gef-6-berpartispasi-di-ajang-internasional-indo-fisheries-2024-expo-and-forum/ |
|  | Through the GEF 6 CFI Indonesia Program, the Ministry of Marine Affairs and Fisheries (KKP) Re-Reviews the Draft Regulations on Fisheries Management (RPP) for Fishermen in Indonesia (WPPNRI) 715 and 717 | https://cfi-indonesia.id/blog/lewat-program-gef-6-cfi-indonesia-kkp-kembali-mereviu-rpp-wppnri-715-dan-717/ |
|  | Increasing the Institutional Management Capacity of Fishermen in Kaimana | https://youtu.be/PIX3K6eweJI?si=18lJ4izIxdDEHX9h https://www.youtube.com/watch?v=NgOd18OWLSk&t=277s |
|  | GEF 6: Empowering Business Actors to Support the Sustainability of the Fisheries Sector in Southeast Maluku Regency | https://cfi-indonesia.id/blog/pemberdayaan-pelaku-usaha-untuk-mendukung-keberlanjutan-sektor-perikanan-di-kabupaten-maluku-tenggara/ |
|  | GEF 6: KKP Collaborates with the Kaimana Fisheries Service to Hold a Business Diversification Activity for Women Fishermen (Volume 2) | https://cfi-indonesia.id/blog/gef-6-kkp-gandeng-dinas-perikanan-kaimana-gelar-kegiatan-diversifikasi-usaha-wanita-nelayan-(jilid-2)/ |
|  | GEF 6: Together with the West Papua Marine Affairs and Fisheries Department, Protect Fishermen in Mansel with BPJS Employment | https://cfi-indonesia.id/blog/gef-6-bersama-dkp-papua-barat-lindungi-nelayan-di-mansel-dengan-bpjs-ketenagakerjaan/ https://papuabarat.tribunnews.com/2024/06/27/dkp-papua-barat-lindungi-nelayan-di-mansel-dengan-bpjs-ketenagakerjaan https://youtu.be/u1EWOSdQLds?si=vx3ASWZ4vtiZpAoa https://www.youtube.com/watch?v=r4p-4baH_Rk&t=9s |
|  | GEF 6: Together with the Maluku Province Marine Affairs and Fisheries Department, Continue Vessel Marking Fisheries in SBT Regency | https://cfi-indonesia.id/blog/gef-6-bersama-dkp-provinsi-maluku-melanjutkan-fasilitasi-penandaan-kapal-perikanan-di-kabupaten-sbt/ |
|  | Through the GEF 6 CFI Indonesia Program, the East Seram Women's Group Develops Roa Chili Sauce Products and Promotes Permit Processing | https://cfi-indonesia.id/blog/melalui-program-gef-6-cfi-indonesia-kelompok-perempuan-seram-timur-kembangkan-prodak-sambal-roa-dan-dorong-pengurusan-perijinannya/ |
|  | Through the GEF 6 CFI Indonesia Program, it's the East Seram Fisheries Service's Turn to Assist its Small-Scale Fishermen | https://cfi-indonesia.id/blog/melalui-program-gef-6-cfi-indonesia-giliran-dinas-perikanan-seram-bagian-timur-bantu-tdkp-nelayan-kecilnya/ |
|  | GEF 6: Seaweed Diversification Training as an Alternative to Improve the Economy of Coastal Communities in Southeast Maluku (Volume II) | https://cfi-indonesia.id/blog/gef-6-pelatihan-diversifikasi-rumput-laut-sebagai-alternatif-peningkatan-ekonomi-masyarakat-pesisir-maluku-tenggara-(jilid-ii)/ |
|  | GEF 6: Ministry of Marine Affairs and Fisheries (KKP) and Maluku Ministry of Marine Affairs and Fisheries (DKP) Promote Fishing Vessel Registration and Marking in Maluku | https://cfi-indonesia.id/blog/gef-6-kkp-bersama-dkp-maluku-sosialisasi-pendaftaran-dan-penandaan-kapal-perikanan-di-maluku/ |
|  | Technical Guidance on Adopting CCRF and EAFM Indicators | https://www.instagram.com/reel/C9bzX4OSqTz/?igsh= MW55MWFhYXk2eTIxMQ== |
|  | GEF 6 CFI Indonesia Program Has a Significant Impact on Coastal Communities | https://cfi-indonesia.id/blog/progam-gef-6-cfi-indoensia-berdampak-signifikan-bagi-masyarakat-pesisir/ |
|  | Minister of Maritime Affairs and Fisheries Launches Modeling for Measured Fishing Capture in Tual City | https://cfi-indonesia.id/blog/menteri-kelautan-dan-perikanan-lauching-modelling-penangkapan-ikan-terukur-di-kota-tual/ |
|  | KKP Holds Public Consultation on the Flying Fish Draft Regulation (RPP) | https://cfi-indonesia.id/blog/kkp-gelar-konsultasi-publik-rpp-ikan-terbang/ |
|  | GEF 6: Developing an Icon of Southeast Maluku Through Environmentally Friendly and High-Value Ecoprinting | https://cfi-indonesia.id/blog/gef-6-menggagas-ikon-maluku-tenggara-melalui-ecoprint-ramah-lingkungan-dan-bernilai-tinggi/ https://malraterkini.com/tingkatkan-pendapatan-nelayan-di-maluku-tenggara-dilatih-ecoprint/ https://youtu.be/-wUFTCzQb64 |
|  | GEF-6: Facilitating a Marketing MoU for Processed Fishery Products for MSMEs Southeast Maluku | https://cfi-indonesia.id/blog/gef-6-fasilitasi-mou-marketing-produk-olahan-perikanan-umk-maluku-tenggara/ https://www.youtube.com/watch?v=uDL6kXvUQhk |
|  | Revenue Sharing Funds and Non-Tax State Revenue for Sustainable Fisheries | https://cfi-indonesia.id/blog/dana-bagi-hasil-dan-pnpb-untuk-perikanan-yang-berkelanjutan/ |
|  | Southeast Maluku Student Council Training on Kasko Repair, Net Repair, and GPS Use | https://www.youtube.com/watch?v=CjKYQt9P1Hk |
|  | KKP Encourages Accelerated Implementation of Upstream and Downstream Capture Fisheries Business Cooperation in Tual City | https://cfi-indonesia.id/blog/*kkp-dorong-percepatan-pelaksanaan-kerja-sama-hulu-hilir-bisnis-perikanan-tangkap-di-kota-tual*/ |
|  | PUG KKP | https://www.youtube.com/watch?v=tLw9p8Hn6vo&t=10s |
|  | GEF 6 CFI Indonesia Participates in the 2024 KKP Integrated Working Meeting | https://cfi-indonesia.id/blog/gef-6-cfi-indonesia-ikut-berpartidpasi-di-rakernis-terpadu-kkp-tahun-2024/ https://www.instagram.com/reel/C4M-ejKPMoZ/?igsh=NDc1c2FoY3huZW92 https://www.youtube.com/watch?v=jZvtrOMZlH8 |
|  | GEF 6: Ternate PPN Holds Coordination Meeting with the Fisheries Management Unit of the Indonesian Fisheries Authority (WPPNRI717) | https://cfi-indonesia.id/blog/gef-6-ppn-ternate-gelar-rapat-koordinasi-unit-pengelola-perikanan-wppnri-717/ |
|  | Komnas Kajiskan Synergy to Realize the KKP Blue Economy Priority Program | https://cfi-indonesia.id/blog/sinergitas-komnas-kajiskan-wujudkkan-program-prioritas-kkp-blue-economy/ |
|  | Hawear Local Culture of the Kei People Protects Their Nature | https://cfi-indonesia.id/blog/hawear-budaya-lokal-orang-kei-menjaga-alamnya/ |
|  | KKP Participates in Drafting the Text of the WTO Fisheries Subsidies Agreement | https://cfi-indonesia.id/blog/kkp-ikut-penyusunan-teks-fisheries-subsidies-agreement-wto/ |
|  | Video of Women Conquering the Waves | https://www.youtube.com/watch?v=aC9OkCX0bow&t=245s |
|  | KKP Holds PSC Meeting GEF 6 to Ratify the 2024 Awpb & Finalize the Addendum | https://cfi-indonesia.id/blog/kkp-gelar-psc-meeting-gef-6-sahkan-awpb-2024-dan-finaliasi-amanden-ga/ |
|  | Identification of Indigenous Communities in Ohoirenan, Southeast Maluku | https://www.youtube.com/watch?v= WNB8RPGveg4&t=3s |
|  | GEF-6: Identification of Indigenous Communities in the Country Kiltay, East Seram Regency, Maluku | https://www.youtube.com/watch?v=obBbVcK3xog |

Start date is grant agreement signature or soft start.

As specified in the CEO Approval/ Endorsement or subsequent revision.

Should be no more than 12 Months after the expected closing date. Please keep current.

Date of Submission of Final PIR (when operations are complete).

Total GEF disbursement defined as amount of project budget spent by the Executing Agency, as a total from project start until June 30 of reporting FY.