Project Document

# Section 1: Project Identification

1.1	Project title:				Advancing Conservation in the Eastern Caribbean

1.2	Project number:			9979

PMS:  01482

1.3	Project type: 				MSP

1.4	Trust Fund:				GEF

1.5	Strategic objectives: 			GEF 6 BD 4, Programme 9 & BD 1 Programme 1

1.6	UNEP priority: 			Biodiversity

1.7	Geographical scope:			Caribbean

1.8	Mode of execution:			External

1.9	Project executing organization:	Conservation Council of Nations (CCN)

1.10	Duration of project:			36 months

Commencing: July 1, 2019

Technical completion: June 30, 2022

1.11	Validity of legal instrument:		48 months

    - Cost of project 					US$			%

| Total Cost of the Project Cost to the GEF Trust Fund | 4,051,700 1,866,700 | 100 46.5 |
| --- | --- | --- |
| Co-financing |  |  |
| Cash |  |  |
| Conservation Council of Nations | 510,000 | 12.5 |
| ICCF Conservation Council | 325,000 | 8 |
| Sub-total | 835,000 | 20.5 |
| In-kind |  |  |
| Conservation Council of Nations | 1,350,000 | 33 |
| Sub-total | 1,350,000 | 33 |
| Co-financing Total | 2,185,000 | 53.5 |

1.13	Project summary

Biological diversity has been referred to as the “web of life,” necessary to sustain human lives and livelihoods. Despite the fact that biodiversity directly impacts all human life, we continue to utilize 25% more natural resources than the planet can sustain. Biodiversity loss is jeopardizing not only wildlife but also clean air and water, health, and food security.

A recent World Wildlife Fund (WWF) report states that humanity has wiped out 60% of mammals, birds, fish, and reptiles since 1970. Islands are recognized as having exceptionally high numbers of endemic species, with 15% of bird, reptile, and plant species on only 3% of the world’s land area.

The Caribbean islands and adjacent marine waters have been identified as a biodiversity hotspot: a region with exceptional concentration of endemic species that is experiencing exceptional habitat loss. The area is home to 11,000 plant species, 72 of which are found only in this region, as well as large numbers of animal species endemic to the ecosystem, including amphibians, reptiles, birds, and mammals (mostly bats). Species endemic to the hotspot represent 2.6 percent of the world’s plant species and 3.5 percent of the world’s vertebrate species. Much of this biodiversity is threatened by a range of factors, including urbanization, population growth, and other human activity. UN Environment reported in 2010 that almost two-thirds of the Caribbean coral reefs were threatened by coastal urbanization, sedimentation, contamination by toxic substances, water acidification, and overfishing.

The Conservation Council of Nations (CCN) was founded in 2011, building upon the strong institutional ICCF model in the United States. It is supporting the formation of legislative conservation caucuses in parliaments in Africa, Asia, and Latin America, which bring together conservation-minded legislators to seek solutions to issues of natural resource management. CCN now supports legislative conservation caucuses in 14 countries, and a number of caucuses are being built in other nations globally.

Building on this momentum, in the Caribbean region, Component 1 of this project will build effective policymaking infrastructure and political will by creating the “architecture” needed for policy change, specifically the required mechanisms, relationships, and willingness among policymakers to take steps to mitigate biodiversity loss and address other conservation challenges. The intended outcome is to create new legislative “conservation caucuses” comprised of legislators from four countries (Antigua and Barbuda, Dominica, Grenada, and Saint Lucia) with increased capacity and willingness to assess and address conservation challenges at high levels of government. The project will further leverage CCN’s experience, ICCF’s relationships, and the expertise of partners and stakeholders to focus legislative conservation caucus attention and energy on putting in place the laws, policies, and regulations needed to address the targeted nations’ conservation challenges.  The project will also increase high-level commitment to—and greater capacity for—harmonization of conservation policies, laws, and practices among participating Caribbean nations.

Under Component 2 of this project, CCN’s International Conservation Corps Program deploys top-level conservation professionals from the U.S. and Canada to effectively assist developing countries around the world in order to fill gaps in capacity to accomplish real-world on-the-ground priorities, and to help develop overseas capacity for self-reliance. International Conservation Corps professionals are veterans of U.S. and Canadian government agencies, such as the U.S. National Park Service, Parks Canada, U.S. Forest Service, U.S. Fish and Wildlife Service, and others. Current and recent work includes projects in the Bahamas, China, Colombia, Haiti, Jamaica, Kenya, Mongolia, Peru, Thailand, St. Kitts & Nevis, and St. Vincent.

CCN proposes to conduct a series of field missions of International Conservation Corps personnel to specific protected areas within the target countries to improve management plans of the designated areas (Codrington Lagoon National Park in Antigua and Barbuda, Cabrits National Park (and adjacent marine reserve) in Dominica, Grand Anse Marine Protected Area (MPA) in Grenada, and the Iyanola National Park proposed in Saint Lucia). These personnel will then work in consultation with the respective national agencies to develop management, education, and outreach plans for the designated protected areas.

Table of Contents

Section 1: Project Identification	1

Acronyms and Abbreviations	6

Section 2: Background and Situation Analysis (Baseline Course of Action)	8

2.1	Background and Context	8

2.2	Global Significance	11

2.3	Threats, Root Causes and Barrier Analysis	15

2.4	Institutional, Sectoral and Policy Context	24

2.5	Stakeholder Mapping and Analysis	30

2.6	Baseline Analysis and Gaps	35

2.7	Linkages with Other GEF and Non-GEF Interventions	39

Section 3: Intervention Strategy (Alternative)	46

3.1	Project Rationale, Policy Conformity and Expected Global Environmental Benefits		46

3.2	Project Goal and Objective	47

3.3	Project Components and Expected Results	48

3.4	Intervention Logic and Key Assumptions	56

3.5	Risk Analysis and Risk Management Measures	57

3.6	Consistency with National Priorities or Plans	60

3.7	Incremental Cost Reasoning	63

3.8	Sustainability	64

3.9	Replication	66

3.10	Public Awareness, Communications and Mainstreaming Strategy	66

3.11	Environmental and Social Safeguards	67

Section 4: Institutional Framework and Implementation Arrangements	67

Section 5: Stakeholder Participation	69

Section 6: Monitoring and Evaluation Plan	74

Section 7: Project Financing and Budget	77

7.1	Overall Project Budget	77

7.2	Project Co- financing	77

7.3	Project Cost- Effectiveness	78

Appendices Table of Contents	79

Appendix 3:	Incremental Cost Analysis	80

Appendix 4:  Project Results Framework	84

Appendix 5: Workplan and Timetable	89

Appendix 7: Costed M&E plan	95

Appendix 8: Reporting Requirements	96

Annex 11	96

Appendix 9:	Consultant Costs	97

Appendix 10: Decision-making Flowchart and Organogram	98

Appendix 11: Terms of Reference	99

Appendix 12: Co-financing commitment letters from project partners	115

Appendix 13: Draft Procurement Plan	116

Appendix 14: Management Effectiveness Tracking Tools	119

Appendix 15: UNEP Environmental, Social and Economic Review Note (ESERN)	120

Appendix 16: Theory of Change	120

Appendix 17: Endorsement letters of GEF National Focal Points	129

Appendix 18: Project Taxonomy	129

Appendix 19: Core Indicators	129

## Acronyms and Abbreviations

| CARICOM | Caribbean Community |
| --- | --- |
| CBD | Convention on Biological Diversity |
| CBF | Caribbean Biodiversity Fund |
| CBI | Citizenship by Investment |
| CCI | Caribbean Challenge Initiative |
| CCN | Conservation Council of Nations |
| CLME | Caribbean and North Brazil Shelf Large Marine Ecosystems |
| CLNP | Codrington Lagoon National Park |
| CNP | Cabrits National Park |
| COP | Conference of Parties |
| CREAD | Climate Resilience Execution Agency for Dominica |
| CRFM | Caribbean Regional Fisheries Mechanism |
| CRS | Common Reporting Standard |
| EAF | Ecosystem Approach to Fisheries |
| EBM | Ecosystem-Based Management |
| ELI | Environmental Law Institute |
| GEB | Global Environmental Benefit |
| GEF | Global Environment Facility |
| GLISPA | Global Island Partnership |
| IUCN | International Union for the Conservation of Nature |
| IUU | Illegal, Unreported, Unregulated Fishing |
| IWCAM | Integrating Watershed and Coastal Area Management |
| IWEco | Integrating Water, Land and Ecosystems Management in Caribbean Small Island Developing States |
| MMA | Marine Management Area |
| MPA | Marine Protected Area |
| MSDF | Multi-Country Sustainable Development Framework |
| NBSAP | National Biodiversity Strategy and Action Plan |
| NCSA | National Capacity Self Assessment |
| OAS | Organization of American States |
| OECD | Organization for Economic Cooperation and Development |
| OECS | Organisation of Eastern Caribbean States |
| PA | Protected Area |
| SAP | Strategic Action Plan |
| SIDS | Small Island Developing States |
| TNC | The Nature Conservancy |
| UN | United Nations |
| UNDP | United Nations Development Programme |
| USAID | United States Agency for International Development |
| WWF | World Wildlife Fund |

# Section 2: Background and Situation Analysis (Baseline Course of Action)

## 2.1	Background and Context

- The Caribbean Islands Biodiversity Hotspot, covers almost 4 million square kilometers that contains 30 different nations and territories, providing valuable genetic and species varieties to the world. Some threats to biodiversity and the barriers to combat them are similar on various Caribbean islands, and some others are more specific to particular countries. CCN proposes to build and foster political will in four countries in the Eastern Caribbean to address conservation challenges that have been identified in the region. The countries and specific areas in which CCN proposes to work are Codrington Lagoon National Park in Antigua and Barbuda, Cabrits National Park (and marine reserve) in Dominica, Grand Anse Marine Protected Area (MPA) in Grenada, and the Iyanola National Park proposed in Saint Lucia.

- From the regional perspective, shortcoming with respect to investing in conservation of biodiversity and natural resources is the main issue, which is also shared with most other countries in the developing world. This shortfall has been partially met through international assistance, but the lack of secure domestic support leaves conservation subject to the grant cycle and fashions in international assistance. Published research indicates that up to 90% of conservation funding in developing world countries comes from foreign sources. Conservation in the target countries will not be secure until it includes a larger share of domestic support. Such support is more likely and more sustainable when there is a genuine element of economic development that benefits local people in the plans for protected areas (typically stressing tourism).

- Project efforts under the grant will stress engagement with private-sector investors and with NGOs having experience in working with communities, for example on marine resources and artisanal fisheries. Through the experience of CCN, building legislative conservation caucuses and fostering political will in both Africa and Latin America, we have found that engaging legislators on these issues helps to coalesce action around conservation challenges, and this is often a key component that must be addressed for sustainable conservation solutions.

- The participating countries are all signatories to the Convention on Biological Diversity and have proclaimed extensive networks of protected areas (PAs) and reserves, but the level of actual protection at many of these PAs remains challenging, as do public access and sustainable benefits to local people. The urgency of other immediate priority human needs (especially food, education, health, transport, and infrastructure) has meant countries, even when well intentioned, consistently under-invest in conservation. Such tendencies have led to substantial problems of environmental degradation and loss of biodiversity, and to a broad deterioration in the natural goods sustainably provided for human use. To the extent that active, managed conservation is carried out, there is a tendency to depend to a high degree upon international support. Government documents including national strategies and National Biodiversity Strategy and Action Plans (NBSAPs) from the participating countries all acknowledge these challenges.

- Antigua and Barbuda has eight protected areas between its two sister islands (six in Antigua and two in Codrington Lagoon). As of 2014 the country had undertaken to complete a Systems Plan for Protected Areas, but has not yet finalized the plan. The management authority of Antigua and Barbuda’s Protected Areas varies depending on the area, with the National Parks Authority managing the National Parks, the Fisheries Division managing MMAs and MPAs, and the Barbuda Council managing Codrington Lagoon National Park on Barbuda Island. While conservation remains a top priority for bureaucratic government agencies, especially those managing the protected areas and the Department of Environment, anecdotal evidence suggests that legislators prioritize natural disaster resilience and development over biodiversity conservation issues, creating a disconnect within government on the passage and implementation of policy.

- Antigua and Barbuda’s Codrington Lagoon is an area measuring 3,600 hectares on Barbuda Island that encompasses vast wetlands, seagrass, algae, and coastal marine ecosystems, including the Magnificent Frigatebird Sanctuary. Designated nationally in 2005 as a National Park under the management authority of Barbuda National Parks, the International Union for the Conservation of Nature (IUCN) has classified it as a “Protected Area with Sustainable Use of Natural Resources,” defined as, “generally large, with most of the area in a natural condition, where a proportion is under sustainable natural resource management and where low-level non-industrial use of natural resources compatible with nature conservation is seen as one of the main aims of the area.” In 2006, the site was also added to the List of Wetlands of International Importance under the Ramsar Convention, an intergovernmental treaty that provides a framework for national action and international cooperation for the conservation and wise use of wetlands and their resources.

- Dominica, known colloquially as the “Nature Island,” measures only 47km by 22km at its widest point. Dominica’s national Protected Areas systems consists of seven protected areas: three national parks, two forest reserves, one marine reserve, and one water catchment. Notably, one of the National Parks - Cabrits National Park - has both a marine and terrestrial component. The management of Protected Areas is divided, with the Forestry Division housing the National Parks Authority and responsible for the management of National Parks, and the Fisheries Division managing the MPA and marine component of National Parks. The Government of Dominica has demonstrated commitment to biodiversity conservation through ratifying the United Nations Convention on Biological Diversity in 1994 and submitting a National Biodiversity Strategy and Actions Plan in 2001. Hurricane Maria in 2017, however, severely impacted the priority of biodiversity conservation in Dominica, with most national and political attention being instead devoted to resilience and economic development in recent years. Cabrits National Park in Dominica encompasses a peninsula and the surrounding marine environment on Dominica’s Northwest coast, about 2 kilometers from the nearest town of Portsmouth; it contains 531 hectares of marine environment of coral reefs and seagrass beds, and 35 hectares of swamp wetlands, including mangroves, swamp forest, and marshlands. The park and marine reserve is most known for its coral reef biodiversity, Hawksbill and Leatherback sea-turtle nesting sites, and its mangrove wetlands, but also for its UNESCO World Heritage Site, Fort Shirley, considered Dominica’s most significant historical site, and the location of the famous revolt of the 8th West India Regiment in 1802, when African slave soldiers took over the garrison for three days in protest over conditions there and the fear of being sent to work in the canefields; notably, this event resulted in all slave soldiers in the British Empire being made free in 1807. Marine mammals such as dolphins and sperm whales can also be seen in its waters most times of the year, particularly due to a resident pod of sperm whales offshore, contributing to Dominica’s reputation as the “whale watching capital of the Caribbean”.

- Grenada’s three main islands, Grenada, Carriacou, and Petit Martinique, cover 348 sq km and a 121 km coastline. Grenada has a large system of protected areas that are in various stages of official designation. While only seven protected areas have been designated by legislation, other areas of consideration include five terrestrial sites and one marine site that are awaiting finalization, three “heritage sites” that are under active management and considered Protected Areas but not formally designated, ten tourism sites that are under active management and considered Protected Areas but not formally designated, and thirteen areas of interest that have been identified for consideration under future land use planning. Grenada ratified the CBD in 1994 and implemented its National Environmental Action Plan. A draft Protected Areas System Plan was completed by OAS in 1988 that recommended 27 sites on Grenada and 16 sites on Carriacou for designation in a combination of protected area categories. In 2009, a new Protected Areas System Plan based on the 1988 plan was created for Grenada in order to meet Grenada’s 2006 Declaration commitment to conserve at least 25% of Grenada’s near shore marine environments and terrestrial environments by 2020 as a means to contribute to the sustainable livelihoods for its people and to contribute to protection of the world’s biodiversity. Legislation in Grenada provides for the creation of a Director of National Parks, but because only one National Park is currently designated, no such Director has been appointed and instead designated and proposed Protected Areas are under the management authority of the Ministry of Agriculture, including the Department of Forestry and National Parks, Department of Fisheries, Ministry of Tourism, and Grenada Board of Tourism. This overlap of authority has created numerous challenges in the management of Grenada’s Protected Areas and has been addressed as a concern by the Protected Areas System Plan. Grand Anse MPA is a marine protected sea- and landscape on Grenada’s Southwest coast that covers a total of 1,965 hectares encompassing coral reefs, coastal areas, and a fish sanctuary. The area hosts numerous recreational activities and waterfront hotels, as well as local populations that rely upon the park’s resources for livelihood, particularly fishermen. At the time of its designation in January 2017, the area and its iconic Grand Anse Beach hosted over 100 visitors and up to 140 yachts per day.

- Saint Lucia’s “mountainous landscapes and tropical location” has enabled a variety of biologically diverse creatures to thrive. Saint Lucia’s Protected Areas system currently has twelve forest reserves and twenty-four protected forests, two wildlife reserves, twenty-four marine reserves, two local fisheries management areas, two environmental protection areas, one World Heritage Site, two RAMSAR sites, and twenty-six national trust sites. While Saint Lucia’s government is party to a number of international agreements - it ratified the CBD in 1992, the Ramsar Convention on Wetlands in 1971, the World Heritage Convention in 1972, the Convention for the Protection and Development of the Marine Environment in the Wider Caribbean Region (Cartagena Convention) in 1983 - it has not adopted a systematic approach to protected areas management. The Protected Areas System Plan of 2009 built upon a 1992 Protected Areas System Plan, proposing an additional two National Parks, four Protected Landscapes, three MMA, and nine nature reserves to supplement and complete the existing designations. Both the 1992 and 2009 Systems Plans has been referenced and utilized by numerous agencies, but not officially adopted by the Government of Saint Lucia, and the resultant land management within the island is quite weak. Management Authority of Protected Areas is not clearly defined in Saint Lucia, though the Ministry of Agriculture, Lands, Forestry and Fisheries houses many of the divisions with suggested responsibility by the Systems Plan of 2009, in addition to the Ministry for Physical Planning and Ministry for Sustainable Development.  A swath of land covering 5090 hectares of dry forest, mangroves, coastline, and coral reefs on Saint Lucia's East Coast, and last remaining undeveloped coastline, has been proposed under the name Iyanola National Park by the Systems Plans for Protected Areas in St. Lucia first in 1992 and again in 2009 in order to protect the high amounts of biodiversity in the area. The proposed park includes three other proposed protected landscapes and areas, including Fond D’or Protected Landscape, Grand Anse National Park, and Esperance Protected Landscape. It is also proposed to overlap with and include the East Coast Marine Management Area (MMA), which extends along the Eastern coast of the country, including important coral reefs, white sand bays, and mangrove forests.

## 2.2	Global Significance

- Islands are recognized as having exceptionally high numbers of endemic species, with 15% of bird, reptile, and plant species on only 3% of the world’s land area. The conservation significance of islands is highlighted by global analyses showing that 67% of the centres of marine endemism and 70% of coral reef hotspots are centred on islands. Caribbean biodiversity is described by the Critical Ecosystem Partnership Fund as a hotspot that supports a wealth of biodiversity within its diverse ecosystems. It includes about 11,000 plant species, of which 72 percent are endemics. For vertebrates, high proportions of endemic species characterize the herpetofauna (100 percent of 189 amphibian species and 95 percent of 520 reptile species), likely due to their low dispersal rates, in contrast to the more mobile birds (26 percent of 564 species) and mammals (74 percent of 69 species, most of which are bats). Species endemic to the hotspot represent 2.6 percent of the world’s 300,000 plant species, and 3.5 percent of the world’s 27,298 vertebrate species.

- Changes to biodiversity can have dire consequences for society and the world, including reduced food, fuel, structural materials, medicine, or genetic resources. Loss of species can drastically change community compositions and alter entire ecosystem processes that are crucial to human survival. The impacts of these losses can be wide-ranging and costly. For example, in the Caribbean, the high biodiversity in coral reefs is critical as a barrier to tropical storms and hurricanes, which can cause immense damage to the islands. The loss of these critical ecosystems would represent a loss for all of humanity.

- Like many nations in the Caribbean, the archipelagic state of Antigua and Barbuda is seen as a biodiversity hotspot with a high level of endemism. Anthropogenic activities, originally for agriculture and now for tourism, have greatly threatened the biodiversity of the islands. Much of the habitats were originally cleared for the cultivation of sugarcane and cotton. The array of habitats, including wetlands, beach and coral reef ecosystems, as well as extensive watershed systems, marine ecosystems of coral reefs and seagrass beds, host a variety of rare flora and fauna. Specifically, the islands host the largest frigatebird (Fregata magnificens) nesting ground in the Caribbean. The Codrington Lagoon National Park area contains a great biodiversity of bird, reptile, and fish species, most notably including breeding sites of the frigatebird, two endemic species of anolis, Hawksbill, Green, and Leatherback sea turtles, and red footed tortoises (G. carbonaria). The National Park hosts important resources, including an important lobster fishery, coral reefs, and the largest frigatebird colony in the Caribbean, and the site accounts for approximately 60% of the Barbudan economy. Major threats to the park reflect threats to the biodiversity of the country as a whole, including overfishing, solid waste disposal, and land degradation.

Codrington Lagoon National Park, Barbuda

(Source: protectedplanet.net)

- Dominica has incredible global biodiversity significance, hosting some 155 families, 672 genera and 1,226 species of vascular plants, with a number of plant species considered endemic to the island. Cabrits National Park encompasses a peninsula and the surrounding marine environment on Dominica’s Northwest coast, about 2 kilometers from the nearest town of Portsmouth; it contains 531 hectares of marine environment of coral reefs and seagrass beds, and 35 hectares of swamp wetlands, including mangroves, swamp forest, and marshlands.

Cabrits National Park (and marine reserve), Dominica

(Source: protectedplanet.net)

- Grenada’s three main islands, Grenada, Carriacou, and Petit Martinique, cover 348 sq km and a 121 km coastline. The ecosystems of mangrove swamps, coral reefs, seagrass beds, beaches, lagoons, dry woodlands, and cactus shrub host “233 marine species, 69 marine/brackish water species, and several species of seabirds as well as 17 freshwater species on the main island.” Grenada’s existing terrestrial protected areas cover over 2200 hectares and protect significant altitude forest environments, critical dove habitat, and Amerindian cultural resources. The island’s Amerindian heritage includes Crown land at Pearls, formally designated as a protected area due to its cultural and heritage resources. The Ministry of Tourism also supports several colonial heritage sites, including Fort Frederick, Fort George, and Fort Matthew. The biodiversity of Grenada’s coral reefs is significant to international tourism, particularly that of yacht and cruise ship moorings.

Grand Anse MPA, Grenada

(Source: protectedplanet.net)

- Even though Saint Lucia is only 616 sq km, this small island hosts 1,300 plant species, 160 birds, 250 reef fish and 50 coral species. The proposed Iyanola National Park is crucial to protecting not only the last remaining expanse of undeveloped coastline in Saint Lucia, but also the survival of rare and endemic species, including the Iyanola sea turtle and iguana, which share important breeding and nesting sites on the beaches of the National Park. The dry forests provide important resources for local populations, as well as habitats for pollinators. Together with the mangrove stands and coral reefs, these terrains provide protection against soil erosion and increase resilience to hurricanes. The Grand Anse coastline within the park is home to fifty-three species of birds, seven of which are endemic. It contains thirteen rare plant species, four of which are believed to be endemic, and is the site of the only nesting ground for the masked duck in Saint Lucia, as well as the most important nesting ground of Leatherback and Iyanola sea turtles.  The Fond D’or proposed protected landscape also contains cultural and historical significance, with architectural remnants from the colonial age and artifacts that date back to the Amerindian tribes that once inhabited the area located at the interpretation center and Museum.

Proposed Iyanola National Park, Saint Lucia

(Source: Haffey, David. “A Systems Plan for Protected Areas in St. Lucia” OECS Protected Areas and Associated Livelihoods Project. December 2009)

## 2.3	Threats, Root Causes and Barrier Analysis

- Broadly, the main threats to the conservation of biodiversity in small islands development states (SIDS) and in particular in the Caribbean include, among others: increasing social inequality, inadequate agricultural models, Illegal, Unreported and Unregulated (IUU) fishing, land-based pollution of marine areas, weak law enforcement and policy adherence, and insufficient funds for protection and management. In the four project countries, the main threats to biodiversity conservation are water pollution, coastal erosion from inappropriate development and/or deforestation, overfishing, and natural disasters. The root causes vary depending on the country, but can often be traced back to lack of political will to monitor and enforce management of Protected Areas, insufficient budgets and staffing, and rapid, unsustainable development, especially related to tourism.

Antigua and Barbuda: Codrington Lagoon National Park

Overfishing and loss of marine/coastal habitat:

- Overfishing is one of the main causes of biodiversity loss in Antigua and Barbuda. Seagrass beds that provide food for fish and turtles and also function as nurseries for young conch, spiny lobsters, shrimp and a variety of fish are being destroyed. Coral reefs are in poor condition, stressed by high sedimentation, and activities like overfishing, destruction by the anchoring of boats, improper placement of fish traps, garbage, breakage by recreational diving, and the release of partly treated sewage from coastal holiday developments directly into the sea. The destruction of nesting and foraging habitats through coastal construction, sand mining, pollution, and overfishing has threatened sea turtles as well. The regulatory mechanisms, though effectively enhanced with the enactment of the new Fisheries Act and its accompanying regulations, are undermined by the lack of capacity to enforce these laws. In addition, Antigua and Barbuda authorities note the need to, “Adopt measures to prevent overfishing including a ban on other destructive fishing gear not covered by the Fisheries regulations.”

- Overfishing is a specific concern for Codrington Lagoon. The lobster fisheries industry in Barbuda is extremely important to the livelihood of the population, and the overexploitation of this resource could be economically devastating to the island. According to the National Park’s management plan, export-oriented lobster fishing on Barbuda’s reefs makes up 40% of Barbuda’s Island Domestic Product, and this resource is shared with fishing vessels from Antigua and Guadeloupe. A biodiversity assessment conducted by OECS in 2008 found low populations of parrotfish and Nassau Groupers in the park relative to the rest of the Caribbean. Coral cover is also extremely low in the park, which is believed to be an indirect effect of overfishing. Seagrass, an important marine ecosystem for numerous species and natural filter for sedimentation, has suffered propeller scars from fishing boats, which can take years to adequately recover. In an important step forward, the Barbuda Council adopted new oceans management legislation in 2014, permanently banning parrot-fish catching and temporarily banning fishing in the National Park; however, the Environmental Law Institute (ELI) points out major gaps in enforcement and regulation of the bans, encouraging the management authority to work with its sister authority on Barbuda and the Ministry with authority for national parks to update current national park regulations to improve protection, management, and enforcement and to ensure that the regulations accommodate the particular needs of the Codrington Lagoon National Park. A study of environmental laws by the Environmental Law Institute identified serious shortcomings in the fisheries laws for Barbuda. Barbuda was massively damaged in 2017 by Hurricane Irma, and it is likely that in an iterative dialogue about project activity in Antigua and Barbuda, a large element of recovery work will be identified and implemented.

Water pollution:

- Water pollution from sewage runoff, agro-chemical runoff, and boat pollution continues to be a threat to coastal and marine ecosystems. Fortunately, some of the damage has been mitigated by the implementation of the Pesticides and Toxic Chemicals Act. The Pesticides Control Board manages pesticide use, but there are still gaps in effective management such as the lack of effective disposal of obsolete chemicals and hazardous waste. Antigua and Barbuda has taken steps to monitor the degree of pollution in its waters through its monthly monitoring of water quality in Falmouth and English Harbour. The Environmental Unit, in conjunction with the Fisheries Division Laboratory at Point Wharf, seeks to identify the sources of the pollution and limit them to tolerable levels for the vulnerable marine ecosystems within the harbor. In accordance with the Aichi targets, Antigua and Barbuda have set a national target that “by 2020 pollution, including from excess nutrients within specific demonstration areas,” will be brought to levels that are “not detrimental to ecosystem function and biodiversity.”

- The proximity of Barbuda’s 1,400 residents in Codrington Village, within the limits of Codrington Lagoon National Park, could present serious water pollution damage if not properly managed. Despite the small population, threats of water pollution already exist. The lagoon is bordered by mangrove stands where solid waste and sewage pumping from septic tanks are dumped, and the Antigua Public Utilities Authority (APUA) energy plant on the shoreline is a continual source of oil pollution and fuel leakage. These effects are compounded especially after heavy rains. ELI asserts that new regulations by the Ministry with National Parks Authority may be required to address conflicts between the 2012 regulations and the needs of the CLNP and Barbuda community, and such opportunities could be taken in drafting an implementation plan for the 2009-2019 management plan.

Loss of habitat and deforestation:

- Significant areas of habitat have been lost in the country, primarily through the subdivision of lands for housing, tourism development, agriculture, and the mining and dredging of sand. Development activities have often meant the clearing of natural vegetation; planting of ornamental trees, shrubs, and grass for lawns and golf courses; filling-in of forests / mangrove areas for marina developments and mosquito control; and construction of new roads to give access to areas previously difficult to access. Mangroves function as nurseries, breeding grounds, and habitats for both marine and terrestrial wildlife, and provide protection from environmental shocks, but they are being destroyed for coastal development, especially development associated with the tourism sector. In the 1980s, there was an estimated 4,900 ha of mangroves in the twin island state, however estimates from photos taken in 2004 indicated that only 902 ha remained in Antigua and 807 ha remained in Barbuda.

- In Barbuda, the sustainable use and protection of the Codrington Lagoon and its mangroves are critical to its biodiversity, particularly the conservation of the Frigatebird Sanctuary and nursery areas for commercially significant species such as the spiny lobster, yet, until recently, there has been very little active management of these areas. Mangroves provide an excellent system of water filtration, specifically important in the “352 ha fringe mangrove of Codrington Lagoon,” as approximately 50% of the fishing industry for Barbuda depends on the lagoon. Application of the Forestry Act in Barbuda overlaps substantially with that provided by the Barbuda Land Act, according to ELI analyses. Each act prohibits unpermitted timber harvesting, including mangroves, and resultantly determining which law takes precedence will be incidental to mangrove protection efforts. The Barbuda Land Act is more recent than the Forestry Act and explicitly authorizes the Council to regulate forestry in Barbuda without oversight from the Cabinet, implying its precedence and the authority of the Council.

Dominica: Cabrits National Park

- Cabrits National Park (and associated marine reserve) faces many threats, primarily to its wetlands and reefs from hurricanes, land-based pollution, illegal dumping in wetlands, impacts of cruise ship and yacht tourism, and illegal harvesting.

Overfishing:

- The high levels of poverty in Dominica create a reliance on fish stocks for livelihood. This, coupled with ineffective management of fisheries, has resulted in overexploited fish stocks, declining white sea urchins, and severely threatened corals. The NBSAP notes that the main threats to marine and aquatic biodiversity include “negative impacts of ghost fishing and inappropriate fishing gear such as nets with inappropriate mesh size.” Fortunately, the Fisheries Department, authorized by the Fisheries Act No. 11 of 1987, has taken some steps to successfully mitigate these issues including, “the formation of fisheries cooperatives at community level that allow for education exchanges, technology transfer and financial support, provision of appropriate gear to fishers, using fishermen to police the behavior of others, discouraging the use of ghost fishing (fish pots that are frequently lost), and providing training to relatives and friends of fishers to effectively utilize all of their catch.” According to the NBSAP, this legislation is “functional with need of revision,” and the proposed project would create a forum to discuss the necessary revisions.

- Additionally, the implementation of the Fisheries Industry Census serves as a positive step to inform decision making. Spear-fishing from members of outside communities that target larger fish remains a problem in Cabrits; this type of activity not only reduces the number of fish in the area, but also degrades the coral over time. Sea turtle populations have rebounded due to efforts by the Dominica Sea Turtle Conservation, a local NGO that, “has trained over seventy five persons over the past three years to do beach monitoring in protection of turtles, their eggs and their hatchlings.” Due to the aforementioned strategies and others, in recent years the status of marine turtles, sea grasses, and coastal pelagic resources has improved. Despite laws against harvesting within the National Park, within the mangrove forests of the Cabrits peninsula, local populations have reduced crab populations which are a local delicacy, through overharvesting.

Water pollution:

- The NBSAP intends to “seek agreement among farmers to regulate pesticide use in support of the Organic Island concept,” although it notes that the “aerial application of pesticide may render organic farming impossible.” The government plans on modernizing this sector for it to become globally competitive and ensure food security and employment, so it is essential that the agricultural policies and procedures do not degrade the marine biodiversity. Attempts to mitigate water pollution were made by the Marine Pollution Management Bill of 1999, but the NBSAP laments that the legislation is “not well enforced.” In accordance with the Aichi targets, the NBSAP has set a National Target that, “by 2020, pollution, including from excess nutrient, has been brought to levels that are not detrimental to ecosystem function and biodiversity.”

- Clear water is crucial to reefs, which require sunlight to thrive; water clarity has been particularly impacted in Toucarie Bay and Douglas Point South by sediment loading and the discharge of both solid and liquid waste from cruise ships and yacht boats. In the 1980's one major municipal solid waste disposal site for Portsmouth was located within the wetlands of the park, and although this dumping was discontinued and the activity made illegal, locals still use this area to dump old vehicles and appliances. This can be extremely detrimental to the health of reefs and the many important species that make their habitats in them.

Deforestation:

- The clearance of natural forest areas over the past several decades due to the expansion of housing, roads, and agriculture has reduced forest cover. Overall, forest cover on the island, which ranges from dry scrub woodland on the west coast to lush, tropical rain forest in the interior, declined eight percent between 1990 and 2005, mainly due to the expansion of agriculture and housing. Large storm events (notably Hurricane David in 1978, as well as several hurricanes and tropical storms in the past 10 years) have also significantly damaged natural forests. Hurricane Maria in September 2017 has had an even greater impact, especially through the amount of forestland degraded or destroyed in the storm, estimated by remote sensing to be at approximately 19%, hence we anticipate that dialogue with local authorities and parliamentarians will lead to the identification and implementation of elements of disaster recovery in the project work.

Grenada - Grand Anse MPA

Overfishing:

- Overfishing in Grenada is one of the greatest threats to biodiversity. Recognizing the importance of sustainable fishing, Grenada has taken some measures to create a more sustainable industry. First, the Fishery (Amendment) Regulations of 1996 and 2001, and the Fisheries (Marine Protected Areas) of 2001, provide for habitat protection of both spawning and foraging habitats. The police, the coast guard, and the fishery officers conduct joint enforcement. The efficacy of enforcement must be good as, “compliance within the pelagic fishery is fairly high.” There is a data gap from the Grenada fisheries as there is insufficient data on the populations of smaller pelagic and broader issues including social, environmental, and economic impacts. Coastal fisheries of Latin America and the Caribbean note the need for an “integrated coastal management policy” to help resolve the frequent user conflicts that arise such as yachts getting in the way of inshore pelagic fishers’ seines. Currently only line fishing is permitted in one area of the Grand Anse MPA, but this remains an issue for a coalition of fishermen, the Grand Anse Fishers Association, for whom the Grenadian government is trying to find alternative sources of livelihood.  Moreover, anecdotal evidence suggests that illegal fishing continues within the protected area boundaries.

Water pollution:

- Water pollution from agro-runoff and sewage is one of the main threats to the marine and coastal biodiversity in the country. Agro-chemical runoff is of particular importance as the latest “census indicated that approximately 75% of the total land area is under some form of agriculture.” Grenada is aware of this issue and has conducted awareness workshops with farmers on minimizing the “dependence of polluting pests,” although the lack of enforcement is noted as an ongoing issue. The NBSAP notes the need to “Embark on sustainable agricultural production systems including restricted use of inorganic fertilizers insecticides and pesticides, genetically modified organisms, introduction of alien species, managing nutrient discharge and pollution, combating soil erosion and land degradation and safeguarding genetic diversity.”

Deforestation:

- Grenada’s mangroves have been decimated by anthropogenic and environmental shocks. For example, 90% of the country’s mangrove forests were destroyed during Hurricane Ivan and more recently, mangroves continue to be threatened by deforestation for coastal development and “unsustainable harvesting for charcoal production.” It is estimated that 3.4 sq km of mangroves remain in Grenada, some of which are protected under the national parks in Levera in the northeast. Fortunately, the Grenada Fund for Conservation, in conjunction with Deutsche Gesellschaft für Internationale Zusammenarbeit, began the RECCOMM pilot project in 2015 to “rehabilitate the mangroves for protection against the adverse effects of climate change such as storm surges and sea-level rise.” The project has also worked to raise awareness with locals, especially in the Telescope Big Bay Area, on the importance of mangroves, as their involvement is necessary to the project’s success.

Coastal Erosion:

- The development of Grand Anse tourism and history of sand mining have dramatically eroded the coast over time. Cambers et al found that Grand Anse was eroding at an average rate of 0-4 m/year between 1951 and 1970, and 0-7 m/year between 1971 and 1974, and measurements indicate that this trend is continuing to increase with increased development and plastic solid waste disposal in the MPA. Although sand mining has become illegal in the area, its effects have compromised the marine habitats,  contributing to salt water intrusion of nearby agricultural lands and well water contamination. Rebuilding after hurricanes Ivan and Emily has also been completed with weak planning and enforcement in many cases, flouting Environmental Impact Assessment (EIA) compliance and dumping waste in wetlands or areas outside of designated landfills.

Saint Lucia - Iyanola National Park

Overfishing:

- Lack of data on the reef health off Saint Lucia’s Eastern coast is a major limiting factor to enforcing policies in this area. While no specific reef data has been taken off the Atlantic coast, Saint Lucia’s Coral Reef Report Card notes that harvested species in the area include parrotfish, angelfish, triggerfish, spiny lobster, conch and white sea urchin. Overfishing threatens the island’s reefs as herbivorous fish, such as the parrotfish, remove algae from coral reefs, allowing coral recruits to take hold, and their removal has dire consequences for the coral. Legislation for the successful management of fisheries has been enacted, such as the Fisheries Act 1984 and Fisheries Regulation 1994, but according to the National Environmental Summary, “these are outdated but currently being revised by the Fisheries Department with the aim of updating them to reflect current trends in fisheries. The Fisheries Management Plan which is a general plan adopted from the regional Fisheries Master plan but is too general to be effective.” Little data has been gathered on artisanal fishing off the Eastern coast, but it has been recorded that species such as lobster, conch, and sea eggs are harvested there, and that many of the local communities rely on subsistence fishing for livelihood support. Sea turtles and their eggs are also illegally harvested, primarily for consumption or shells, despite laws against disturbing sea turtle nests or harvesting sea turtles under a specific weight requirement.

Livestock Grazing:

- Due to the decline in banana production, some of the land previously used in agroforestry now supports livestock rearing, especially pigs. In the proposed Iyanola National Park, fishing and agriculture dominate the economic activities of local communities, and the rearing of livestock is the least sustainable agricultural practice of the area. Unfortunately, this activity has led to a growing problem of fecal contamination of the river systems. Regulations for livestock waste disposal exist but are “hardly enforced.” The Water and Sewerage Act 1999 concerns the control of the sewage system, but provides no treatment standards, resulting in only crude primary treatment prior to disposal through an outfall in the harbor.” Policy provisions and projects are in place to help mitigate pollution issues. For example, Saint Lucia ratified the Land Based Sources of Pollution Protocol within the Cartagena Convention in 2008, has created standards for the implementation of the protocol, and a pilot project was implemented in 2010 to “ascertain the type of pollutants and their sources” with the aim to eventually “test the effectiveness of the water quality standards.” Moreover, this practice contributes to deforestation for grazing lands, contributing to soil degradation and erosion. This can be costly during rainy seasons by increasing the likelihood of landslides, and hurricane seasons, when the absence of vegetative buffers to hurricanes can intensify effects on local communities and the environment.

Deforestation:

- Between 1990 and 2010, Saint Lucia lost forests at an average of 150 ha or 0.34% per year. Most of the forest remaining is secondary, disturbed, and fragmented, having been modified by grazing, planting of exotic species, and cutting for charcoal. The majority of forest types are situated outside of the reserves, almost entirely in areas that lack formal protection, and dry deciduous seasonal forests are widespread but degraded and vulnerable. This is incredibly threatening to the proposed Iyanola National Park, which includes important and limited dry forest ecosystems, as well as mangrove forests by the coast. Deforestation trends have been somewhat offset by the return of land formerly under banana cultivation to secondary forest, however these forests are less diverse, provide less habitat for endangered species, and are also under threat of fragmentation and encroachment. Furthermore, some land formerly under banana cultivation, especially in the Iyanola area, has been converted to other forms of mono-cropping, livestock grazing, or is being sold for real estate. Notably, three large privately owned estates exist within the proposed boundaries of the Park, all of which have pursued or still pursue agriculture and the clearing of forest for crop growth.

Barriers to Progress in Defending Biodiversity, and How the Components of the Project Would Help:

- The obstacles to effective protection of biodiversity are in large measure common among the Caribbean countries and indeed among developing countries globally. Some examples are: shortcomings in national policy and legal frameworks for natural resources access and utilization, lack of political will among the local political elites to address such shortcomings, inefficient enforcement of these regulatory frameworks, limited collaboration and learning from best practices across borders, inappropriate technical capacity incentives for responsible resource utilization, insufficient funding for management of PA/MPA, etc. The values of biodiversity are often distributed and longer-term whereas the economic benefits of converting or abusing habitat are relatively prompt and concentrated. There exists an inevitable tension between competing goals. The process of resolving such tensions in a manner that serves the best interests of the natural and human environments is usually neither simple nor easy, as witnessed by the fact that these issues persist even in rich countries. But a key step toward good solutions is to foster enhanced political will for conservation among persons and institutions that have actual power to affect outcomes.

- Inadequate Effective Management of Protected Areas (to be addressed by components 1 and 2): Many conservation areas have now been legally classified and demarcated but still lack adequate long-term management capacity and funding to ensure that biodiversity is protected. While each of the four target countries has a Protected Areas Systems Plan, the adoption and successful implementation of said plans varies due to overlapping management authority, lack of enforcement powers, low technical training for staff, and lack of designated budget allocation for Protected Areas. Creating legislative conservation caucuses within legislatures will raise awareness amongst lawmakers of gaps in existing policies to effectively manage protected areas, and the guidance of the International Conservation Corps will enhance the technical capacity of managing authorities to effectively monitor and enforce existing legal frameworks.

- Existing domestic investment is frequently insufficient to address to effectively manage PA/MPA systems (to be addressed by component 1): Protected areas in the region are largely managed by governments, however there has also been significant outside investment from private NGOs, the GEF, and other international multilateral agencies. To ensure adequate personnel, benefits, operations, and infrastructure, additional domestic funding will be needed to bring management effectiveness up to a standard, consolidated level that ensures each PA receives the investment required by its management plan, without excessive dependence on international grant cycles. Political will is needed to ensure that governments commit more funds for the management of protected areas; briefings and field visits create a platform of engagement that allows otherwise disconnected stakeholders to share ideas and establish a situational baseline and common goals.

- National policies, laws, and regulations do not anticipate ongoing changes to tourism, population, and resource demand (to be addressed by components 1 and 2). The PA systems in many Caribbean countries do not have plans that accurately reflect the reality on the ground in terms of needs, exiting capacities (equipment and staff), proper definition of activities and priorities, etc. The ongoing development of tourism and resorts in several of the countries is expected to increase the impact of tourism and pressures for development, while rising populations and demand for resources are also expected to contribute to pressures on land management and resource allocation. This future growth needs to be accounted for in legislation and management plans for Protected Areas management. Resources and opportunities to discuss these important issues are limited for decision makers. The most efficient means of adopting such changes is one informed by regional and global best practices, through exposure to events such as expert briefings, workshops, and guided field visits.

- Overexploitation of resources and unsustainable practices related to the need of local people to access resources for their livelihoods (to be addressed by components 1 and 2). Most legislators do not acknowledge the importance of biodiversity conservation to future access to resources for livelihoods, even when the impact of biodiversity on industries such as fishing and tourism is apparent, because the global scale of this problem can be deemed too daunting and removed from the constituency for a legislator to tackle, or may not be deemed profitable enough for his or her attention. Briefings by experts and legislative conservation caucus activities with local stakeholders will raise awareness of the importance of biodiversity conservation to sustainable livelihoods. Moreover, the International Conservation Corps will provide the training and guidance to increase technical capacity of Protected Areas management to reduce unsustainable resource use in Protected Areas and increase the overall value and profitability of the areas.

## 2.4	Institutional, Sectoral and Policy Context

- The parliamentary system of governance is similar in Antigua and Barbuda, Dominica, Grenada, and Saint Lucia where the House of Representatives or House of Assembly is responsible for introducing legislation, while the Senate, reviews and gives assent to proposed legislation.  Bills require a two-thirds majority to pass. For all target countries, the consolidated budget is controlled by appropriations, passed each year in accordance with the provisions under the national constitutions (Constitution of Antigua and Barbuda 1981, Dominica 1978, Grenada 1973, and Saint Lucia 1978). Conservation caucuses with substantial membership will be vehicles for bolstering political ambitions and commitments to conservation legislation on the national agenda. The project endeavors to assist with advancing governance through models of bi-partisan parliamentarian engagement that has been demonstrated to add value in other countries to the process of consensus-forming in moving legislation and regulations forward.  The process is complementary and facilitatory and will build on current initiatives rather than execute outside of existing structures.

Policy Gaps

- While all of the target countries have created legal frameworks for the protection of natural areas, many are infeasible for stakeholders to follow, reducing their overall effectiveness. In the policy implementation stage, this often takes the form of unclear or disputed boundaries of the protected area; local populations that live in the protected area or stakeholders whose livelihood depends on the use of natural resources within its boundaries are often inadequately addressed in the legal frameworks or left out entirely. This is especially prevalent with areas that include marine resources that are a crucial resource to local populations and deeply ingrained within their cultures. The infeasibility of their compliance ultimately leads to either the failure of the policy implementation or the economic and cultural subversion of the local population.

Lack of Institutional Capacity

- An unfortunate number of policies applying to protected areas in the target countries are rendered ineffective due to weak or overlapping management. Sharing the management of a protected area between institutions is common, usually between the forestry, fishery, and/or parks divisions, as is the case with Saint Lucia, but sometimes even between two different islands, as is the case in Antigua & Barbuda. Overlapping authority is rarely delineated clearly, and the collaboration of multiple authorities is regularly hindered by poor or inefficient communication. This results in inconsistent enforcement operating on a case-by-case basis, or in failure to enforce policies completely. Streamlining management authority and legal frameworks can improve the implementation and enforcement of policy.

Limited Resources

- Many of the Eastern Caribbean countries are developing island nations that face the increasing threat of climate change, particularly in the form of devastating hurricanes that have wracked the region in recent years. Most of the aid funding that comes in is earmarked for development initiatives such as infrastructure, climate resilience, and disaster relief to help these nations prepare for and recover from these natural disasters. This means that very little is left over for sustainable management of protected areas, or for research and development into the biodiversity in protected areas or the role that biodiversity plays in national and regional socioeconomics. Without up-to-date information on the ecological biodiversity and importance of protected areas, it can be difficult both to secure funding and to create policies to adequately protect those crucial resources. Moreover, most legislators want to use these areas to maximize economic returns, often looking to development and tourism opportunities that can be detrimental to preserving biodiversity.

Needs in Target Countries to Enhance Biodiversity Protection

- Investment in research and development of protected areas in order to more effectively set policies and secure funding

- Reevaluation of legal frameworks to close gaps and streamline management authority

- Capacity building with management agencies to facilitate communication and collaboration on the enforcement of policies

- Increased participation and input of stakeholders in the designation and management of protected areas

Current Policies

Antigua & Barbuda

- National Parks in Antigua & Barbuda are authorized under the National Parks Act of 1984. The Act does not specify the required purpose of a National Park but provides for the establishment of parks, which currently include parks containing marine areas—most notably the Codrington Lagoon National Park in Barbuda. The National Parks Act does not specify what activities are regulated in National Parks. However, in 2012 the government issued National Park Regulations providing a variety of restrictions in National Parks. Among other provisions, these regulations require permits to use public land or property or conduct certain activities in a park, allow the National Parks Authority to designate restricted or prohibited areas, and prohibit or regulate specific activities in a park (e.g., boating, dogs, fires). Importantly, the National Parks Act does not include specific provisions granting enforcement powers in National Parks, limiting its effectiveness. Similarly, the Physical Planning Act lacks specific provisions granting enforcement authority related to Environmental Protection Areas. As a result, enforcement in these areas requires reliance on authority granted by other laws. Violation of the National Parks regulations may result in penalties up to EC$5,000 and/or six months’ imprisonment.

- Codrington Lagoon is located on the island of Barbuda, one of the two islands that comprise Antigua and Barbuda.  The Codrington Lagoon National Park Management Plan of 2009-2019 states that the park’s purpose is to “protect the biodiversity and productivity of the Codrington Lagoon wetland complex, the East coast cliff environments, and adjacent near shore marine areas by maintaining their natural ecological structure and processes, while at the same time promoting sustainable tourism, fisheries, recreation, and educational activities”. Moreover, because the Park is located on Barbuda Island, the management and development authority has been delegated officially to the Barbuda Council. The two islands are historically at odds over land development in Barbuda, with the Barbudan people’s communal land ownership (an ingrained anti-developmental relationship between the Barbudan people and their land) regularly clashing with the central Antiguan government’s desire for development. The Barbuda Land Act protects their communal land ownership by requiring any major development project (defined as any project over $5.4 million) proposed in Barbuda to be supported by the majority of citizens in order for a land lease to be granted, and this communal land ownership includes the National Park. Prime Minister Gaston Browne has long expressed interest in moving to a private land ownership system that is largely opposed by Barbudans. The evacuation of Barbudans to Antigua following Hurricane Irma in September 2017, which destroyed 90% of the homes on the island, and the central government’s initiative to rebuild on Barbuda have raised concerns over the transparency of the development on the island and compliance with the 2007 Barbuda Land Act.

Dominica

- Cabrits National Park is established under the National Parks and Protected Areas Act of 1975 (amended in 1986 and 1990.) Under the Act, National Parks are designated for the purpose of preserving the natural beauty, including flora and fauna, creating a recreational area, commemorating an historic event of national importance, or preserving any historical landmark or any area or object of historic, prehistoric, archaeological, or scientific importance. They are under the authority of the Minister of National Parks, who has the power to designate and change the boundaries of National Parks. The Act establishes a Director of National Parks, responsible for all hiring and staff, and a National Parks Advisory Council that consists of the Director and four other members that are appointed with the task of advising the Minister of the management of the parks. The Law outlines regulated activities in parks, and places enforcement powers with park wardens or police officers, who have powers of interrogation, search and seizure, and arrest. Other relevant existing legislation includes the Beach Control Act of 1986, which places any water-based construction of docks etc. under the Ministry of Works Authority, and the Fisheries Act of 1987, which places all aquatic animals, including coral, under the authority of the Fisheries Division.

- Like many other Caribbean nations, Dominica has been severely affected by hurricanes in recent years. Dominica is rated by the “Commonwealth Vulnerability Index” as having the sixth (out of 111 countries evaluated) most vulnerable economy (to external shocks and natural hazards) in the world, and the most vulnerable in the Caribbean. According to the World Bank, Dominica suffered damages estimated at $1.3 billion, or 224 percent of the nation’s gross domestic product, during Hurricane Maria in September 2017; the storm had a huge impact on the island’s GDP, including a 55 million USD cost to the agriculture industry and 20 million USD to tourism. After Hurricane Maria, Dominica created a Climate Resilience Execution Agency (CREAD) which is working with international agency consultations to determine and implement best practices to increase infrastructural resilience.  Grants have been awarded to the nation towards these efforts; the CBD in partnership with the EU and DFID provided US$127,000 for a project to complete energy audits of fifteen major buildings in Roseau, to help modernize infrastructure and recommend more cost-effective energy measures for development purposes.

- Both Dominica and Saint Lucia have actively pursued a liberal CBI (citizen by investment) scheme to attract foreign wealth and investment in the islands; however, the program resulted in the Organization for Economic Cooperation and Development (OECD) placing them and four other OECS countries on a “blacklist” for thwarting international efforts to reduce tax evasion and posing a high risk to their Common Reporting Standard (CRS). For Dominica, this is mostly due to the scheme’s loose requirements for residency time on the island. Under the scheme, the government has allowed development of resorts and real estate projects to attract such investments, such as the Kempinski Resort on Cabrits National Park, which requires a minimum investment of just 200,000 USD for Dominican citizenship.

Grenada

- Grenada’s MPA regulations define an MPA as “an area declared as such by the Minister by order under” [the Fisheries] Act and “may be a marine park, a marine reserve, a marine sanctuary or a marine historical site or a combination of any of those.” In practice, an MPA will often contain multiple types of these area designations to serve particular purposes. In addition to different area designations in MPAs, the Regulations create an administrative body (the MPA Authority) and authorize it to designate different zones within an MPA. Certain types of activities are permitted in each of these zones; for example, access zones, aquatic sports zones, and fishing zones may be designated. In an area like Grand Anse MPA, this can lead to confusion due to the many tourist and recreational uses of the area.

- The MPA Regulations contain additional general prohibitions on a variety of activities. Stricter restrictions on activities apply in marine reserves and sanctuaries within MPAs. In particular, access is regulated differently for each type of MPA area designation, ranging from open access to marine parks to prohibitions on entry except for research purposes in marine sanctuaries. Orders by of the Minister or the Authority establishing specific zones within an MPA may also further regulate particular activities within those zones.

- Currently, the Fisheries Minister, as the leading MPA authority, does not have the legal authority to delegate management authority of specific MPAs to other bodies or groups, as would be required for a co-management agreement.  The MPA Regulations authorize the appointment of marine park wardens with enforcement powers in MPAs. Police officers and fisheries officers may also enforce in MPAs using their general enforcement powers as well as the special powers of marine park wardens. Marine park wardens are authorized to seize items and arrest anyone committing an offence against the MPA Regulations, but the regulations do not explicitly authorize them to stop, board, or search vessels or require production of licenses, except that wardens have the power to require production of a permit for and records relating to operating a dive or charter vessel. The Fisheries Act does not explicitly authorize fisheries officers to make arrests, but marine park wardens are authorized to arrest any person committing an offence in an MPA. Commission of an offence against the MPA Regulations is punishable by an EC$10,000 fine and imprisonment for 6 months. Continuing offences may result in further fines of up to EC$200 per day. Under the MPA Regulations, courts may order forfeiture of any item used in the commission of the offence other than vessels and vehicles. Courts may also order payment of the costs of restoration and repair of damage caused by a defendant to an MPA. The MPA regulations also apply the provisions of the Fisheries Act requiring forfeiture of fish, proceeds, and illegal substances.

- Grenada recently passed a Non-Biodegradable Waste Control Act to regulate the use of non-biodegradable products with a view to reducing the negative environmental impacts of inevitable disposal of the products and improving the health of the people of the State of Grenada. The Act bans the importation of styrofoam, sanctions sales on styrofoam, and enacts a complete embargo on its use. The act also bans all single-use plastics such as shopping bags, cutlery, plates, straws and cups by February 1, 2019.

Saint Lucia

- The Iyanola National Park is as yet undesignated, although it contains other PAs with both marine and terrestrial components. Management authority for protected areas in Saint Lucia is divided between the Fisheries Division, Forestry Division and the Department of Sustainable Development, depending on the type of area, its designation, and the policy in question. This results in the lack of a clear authority for the management of National Parks that include marine, forest, and wetland ecosystems. Saint Lucia only has one existing declared National Park, and therefore there is a dearth of experience within government agencies in managing this type of Protected Area.

- Marine Reserves in Saint Lucia are authorized by the Fisheries Act of 1984. Human activity is prohibited in Marine Reserves unless the relevant Minister or his/her delegate gives written permission authorizing such activity for statutorily enumerated purposes (e.g., proper management of the reserve). Use of Marine Reserves is allowed only with written permission from the relevant Minister or his delegate, who can authorize a specific set of uses if they are consistent with the purposes of the reserve or proper management of the reserve. The Minister can designate authorised fisheries officers, who may at any time, without a warrant, stop, board, and search fishing vessels; require production of and examine licences; and require production of and examine nets and other gear. When they have reasonable grounds to suspect an offence, authorised officers may further enter and search premises other than dwellings; take samples of fish; seize vessels, stores, cargo, and gear; seize fish; and seize explosives, poisons, and other noxious substances.

- The Fisheries Act does not explicitly authorize fisheries officers to make arrests, but it provides that seized vessels be taken to the nearest port and detained there pending outcome of the case. The master of a vessel is liable for any offence against the Fisheries Act committed by any person onboard or employed on the vessel. The Act also provides a presumption that when a vessel has been involved in illegal activity, any fish found aboard was caught illegally. When a charge involves an activity that requires permission, the defendant bears the burden of proving that he or she held the requisite license, permit, or authority at the time of the charged offence. Fishing or attempting to fish, taking or destroying flora or fauna other than fish, disturbing or altering the natural environment in any way, or erecting buildings in a Marine Reserve without written permission is an offence liable for up to EC$5,000. Obstructing, assaulting, or threatening an officer who is enforcing the Fisheries Act is liable for up to EC$5,000 and/or up to 2 years in prison.

- The Fisheries Act limits the authority of the Minister to promulgate regulations relating to penalties by limiting the fines to EC$5,000. Any person who contravenes or fails to comply with the Fisheries Regulations is liable on summary conviction to a fine not exceeding EC$5,000, unless otherwise provided for in the Act.  The Minister may compound an offence and may order the return of seized articles if the person who committed the offence pays the government “a sum of money not exceeding the maximum fine specified for that offence.” A court may order vessels, gear, and nets to be forfeited, and must order fish and noxious substances to be forfeited. Conducting activities that are likely to damage a National Conservation Authority Protected Area is an offence subject to a fine of EC$500 or to imprisonment for three months or both; Court may order the convicted person to pay compensation in satisfaction of the damage.

- Protected areas are authorized by the National Conservation Authority Act of 1999. The Act authorizes the Minister responsible for the Authority to declare an area of land or water as a protected area to preserve or enhance the area’s natural beauty, flora, or fauna; create a recreational area or park; or create a marine park, though the NCA has never performed this function. The National Conservation Authority Act authorizes the Authority to employ persons as rangers or wardens. Such persons may arrest, without a warrant, a person who commits an offence against the Act, and such persons may seek assistance from members of the Police Force, who must provide assistance. Authority rangers and wardens are not explicitly granted powers of search or seizure, except that an employee of the Authority or a police officer may request production of a business licence. Like Dominica, Saint Lucia has also adopted a loose Citizenship by Investment (CBI) scheme that the OECD has deemed threatening to international efforts to thwart tax evasion.

## Stakeholder Mapping and Analysis

- Legislators and parliamentarians that may be interested in forming a legislative conservation caucus have been determined based on current or previous roles in relevant ministries. From this initial analysis contact will be made and the caucus effort will grow organically from those initial contacts and through events and meetings during the project.

- Lead partner agencies in each country were substantially relied upon to represent the institutional and stakeholder climate within the public sector during project design, but additional engagement will need to occur during the project inception phase to make connections with a variety of crucial stakeholders in both the public and private sectors.

The outlook for private-sector consultations points to possible roles and responsibilities mainly around soliciting joint cooperation and gaining two-way feedback on ease of doing business based on ecosystem services assets in the protected areas and serving as an informational vehicle for opportunities in sustainable development to the government entities.

- The OECS Secretariat has been made aware of the project and will be included as a stakeholder starting with inception workshops as a pathway for inclusion of the project within the purview of the OECS Council of Ministers of Environmental Sustainability.

- Antigua and Barbuda: In Antigua and Barbuda, the Department of Environment will be a key government partner agency to the project, as it houses the positions most directly linked to the management and oversight of Protected Areas, including coordination with the Manager of Codrington Lagoon National Park. The project will coordinate with the staff to provide enhanced training on a variety of topics to enhance technical capacity to monitor and enforce management policies. Moreover, the Department of Environment will benefit from increased access to legislators via the legislative conservation caucus created under Component 1. Ten legislators have been identified as potential caucus members based on previous or current Ministry positions related to environment, tourism, and/or agriculture. Of these, one is a senator, and one is a woman. Eight of the identified legislators represent the majority party, ABLP, with one representing the minority party, UPP, and one representing the Barbuda People’s Movement, which will be an incredibly important stakeholder for any projects in Codrington Lagoon. The Barbuda Council will also be an important stakeholder when it comes to Component 2 of the project, in regards to an implementation plan for Codrington Lagoon National Park; this council is the overall management authority of the Park, and therefore any action will require extensive participation by council members. A Stakeholder Committee outlined by the Management Plan of 2009-2019 also identifies the following associations and organizations that represent important perspectives on the National Park: the Fisheries Office of Barbuda; Planning Office of Barbuda; Environment Division of Antigua & Barbuda; Small Businesses Association; Sea Taxis Association; Land Taxis Association; Fishermen Association; Lobster Exporters Association.

- There are many private tourism companies in Antigua that could be potential partners due to their stake in healthy coral reefs and several in Barbuda, whose participation may vary based on recovery from recent hurricanes. Because of the Frigate Bird Sanctuary in Codrington Lagoon, international birding societies are likely to be willing partners as well. The Antigua Hotel and Tourism Association (AHTA) is made up of private stakeholders including airlines (LIAT) and banks associated as members, and therefore will be an important stakeholder to engage for the caucus and include in stakeholder forums, especially in regards to sustainable development of tourism.

Table 1: Antigua & Barbuda Tour Companies

| Company | Contact | About |
| --- | --- | --- |
| Adventure Antigua | Antigua Adventures, Box W1669, St. John´s, Antigua & Barbuda Phone: +1 268-726-6355 | Provides ecotourism through education of conservation activism, crew and staff are active volunteers with the Antigua Sea Turtle Project with research and educational efforts and assisting with sea turtle nesting sites. The team also helps in recording whale and dolphin sightings to promote optimal marine mammal watching, as well as sea turtle and marine mammal rescues. |
| Tropical Adventures Antigua | P.O. Box 301 Lower Redcliffe Street, St. Johns, Antigua, West Indies Phone: +1 (268) 480-1225, Email: reservations@tropadantigua.com | Offers various land and sea safari tours through rainforests, snorkeling in coral reefs, eco-kayaking. However, they do not advertise conservation on their website. |
| Indigo Divers | Box JH155, Jolly Harbour Commercial Centre, St. Mary’s, Antigua and Barbuda Phone: +1 268-562-3483 | Provides guided daytime and night dive tours of coral reefs off the coast of Southwest Antigua. |
| Catch the Cat Private Sailing Charters | P.O. Box 209, Jolly Harbour Phone: +1 268 - 464-7113, Email: info@catchthecatantigua.com | Provides small private sail tours in areas including northwestern bays and southwestern reefs. The company provides snorkeling opportunities but does not discuss ecotourism or sustainability. |
| Caribbean Helicopters | Main Office & Heliport: VC Bird International Airport, Runway 10, P.O. Box 2008, St. John’s, Antigua Phone: +1 (268) 460-5900; Email: reservations@caribbeanhelicopters.com | Provides aerial tours through Antigua’s beaches, reefs, coastline, and Montserrat Volcano. Website provides no information about conservation interests. |
| Stingray City Antigua, LLC | Stingray City (Antigua) Ltd, Seaton’s Village, P.O. Box W816St. John’s, Antigua Phone: 268 - 562- 7297; email: stingray@candw.ag | Provides 5-minute speed boat ride to Antigua’s offshore island to a pool with stingrays; not enclosed giving hands-on interaction with the animals. Snorkeling amongst the reef and fish after the tour is also included. No other sustainability information provided on website. |

- Dominica: In Dominica, the main the key government partner agency is the Forestry Division, which houses the Director of National Parks and is responsible for managing the majority of Protected Areas within Dominica. Partnerships with both the Fisheries Division and Forestry Division will help resolve discrepancies between management objectives and practices by creating opportunities for collaboration and best practice sharing, while enhancing access of both agencies to legislators via the legislative conservation caucus to be created under component 1. Ten legislators have been identified in Dominica as being potential caucus members due to their current or previous roles in relevant ministries or their stated goals for their constituents. Of those, five are from the Dominica Labour Party, and five are from the United Workers Party, making for a potentially balanced caucus.

- There are a few tourism companies that may be relevant stakeholders due to their reliance upon Cabrits tourism and healthy reefs for their livelihood, though much ecotourism in Dominica is centered on rainforests and geothermal sites in the island’s interior. Two new resort development projects in Cabrits National Park, the Kempinksi Resort and the Moroccan Hotel, will likely be valuable partners and stakeholders in the area’s conservation, as they will be responsible for increased tourism to the National Park. Other local stakeholders would include fishing associations, water taxi associations, and water sport tour operators. Influential community leaders and advisors involved with the inscription of the Morne Trois Piton National Park as a UNESCO world heritage site will be engaged in advisory roles.

Table 2: Dominica Tour Companies

| Company | Contact | About |
| --- | --- | --- |
| Dominica Untouchable Tours | Whoamen Road, Calibishie, Dominica. West Indies Office Phone: 1 - 767-445-8271, Cell Phone: 1-767-245-3089 Email: untouchabletours@yahoo.com | Provides educational ecotours of Dominica’s untouched ecosystems discussing conservation issues that have impacted the island |
| Rainforest Riding | Bell Hall, Portsmouth, Dominica Phone: 1-767-265-7386, 1-767-445-3619; Email: rainforestriding@yahoo.com | Offers horseback rides through nature trails along the beach, rainforests, and national parks. |
| JC Ocean Adventures | Cabrits National Park, Dominica +1 767-295-0757 | Scuba diving and snorkeling trips from Cabrits National Park, Portsmouth. |
| Keepin it Real | Portsmouth, Dominica +1 767-225-765 | An ecotour operator, including paddle boarding, kayaking, snorkeling, and water sport rentals |
| Cabrits Dive Center | Lizard Trail ¦ Picard Estate, Portsmouth, Dominica +1 767-617-4077 | Cabrits Dive Centre is Dominica's only PADI 5 Star Dive Centre of Dominica, specializing in individual and small group diving principally to the stay over tourist and yachting community. |
| Island Dive Operations | Purple Turtle Beach, Portsmouth, Dominica +1 767-277-5673 | Education, Research, Exploration and Adventure Diving -Focusing on small groups |

- Grenada: The key government partner agency in Grenada will be the Department of Fisheries, which is responsible for managing all MPAs and MMAs in Grenada. The approval of this Department will be necessary in identifying a potential co-managing entity and approving a co-management agreement for Grand Anse MPA. For the legislative conservation caucus, potential members have been identified in Grenada based on current or previous roles in relevant ministries, including several women and representatives from both the House of Representatives and the Senate.  A notable political consideration in Grenada is that one party (the New National Party) holds every seat in the House, but a multi-party caucus could still be formed if members of the Senate representing other parties were to join.

- Private tourism companies will certainly be important stakeholders for a project in Grand Anse, considering the economic benefits that tourism already provides the area, and their probable interest in having a say in the co-management agreement; there are several conservation-minded diving and snorkeling companies that have a vested interest in protecting the reefs that support their businesses. At the time of Grand Anse’s declaration as an MPA, an advisory stakeholder committee was established that included the Hotel Association, water taxi association, dive association, and fisheries association. The Grenada Hotel & Tourism Association has significant vested interest in the Grand Anse area, hence the project intends to actively engage these important association members within the coalition of stakeholders co-managing the MPA, most notably private-sector representatives.

Table 3: Grenada Private Tourism Companies

| Company | Contact | About |
| --- | --- | --- |
| Dive Grenada | Dive Grenada P.O. Box 771 St. George’s, Grenada, W.I Phone: 1-473-444-1092, 1-473-414-6229 (cell), email: info@divegrenada.com | Boutique dive shop that offers snorkel and dive tours. Recognized for Marine Conservation and Environmental Credentials with the 2015 Blue Green matters Sustainability Award of Excellence. Works with the Fisheries Division of Grenada and received approval to design, develop and fund the first purpose-build artificial reef in Grenada with the Grande Anse Reef Regeneration Project (GARRP). |
| Eco Dive, Grenada Blue | Coyaba Beach Resort (headquarters), Grand Anse Beach & Port Louis Marina (satellite office) St. George’s, Grenada Phone: 1-437-444-7777; Email: ecodivegrenada@gmail.com | Local owned and operated dive shop with full-time marine biologists that educate, monitor and protect tropical reef and coastal ecosystems. Work with Project Raise funds through Project Aware to protect marine environments worldwide. Recent projects: shark and ray conservation campaign, invasive species awareness and education programme for the Caribbean Lionfish, recycling program, and most recent International Coastal Clean-up and clean-up dive on Grand Anse Beach. |
| Lumbadive | General Delivery, Carriacou, Grenada, West Indies Phone: 473-443-8566 (office), 473-457-4539 (mobile) Email: dive@lumbadive.com | Provide scuba diving to 35 different sites, and express care and love for the ocean and environment. Participate in ocean cleanups and local/international ocean projects including: lionfish hunting, paying back to the community using plastic to make trash cans, sea turtle salvage and tagging, the Indian Sea Urchin Program. |
| Scuba Tech Dive Center Grenada | The Calabash Hotel L’Anse aux Epines St. George’s, Grenada W.I. Phone: 1-473-439-4346; Email:info@scubatech-grenada.com | Offers diving tours on reefs and wreck sites |
| Aquanauts Grenada LTD | P.O. Box 1264 St. George’s Grenada W.I Phone: 473-444-1126, Email:sales@aquanautsgrenada.com | Offers dive tours to 30 reef and 15 wreck sites in Grenada |
| Caribbean Horizons/ McIntyre Bros LTD | True Blue, PO Box 70, St. George’s, Grenada, West Indies Phone: 473-444-1555; email: info@caribbeanhorizons.com | Large tourism company offering transportation, land and sea tours to local business attractions, hikes, botanical garden, spice and rum distillery stations. |

- Saint Lucia: The key government partner agency in Saint Lucia will be the Ministry of Sustainable Development, which is responsible for managing all multilateral organizational grants, but other department partners will also be necessary, including the National Conservation Authority and the Ministry of Agriculture, Lands, Forestry, and Fisheries. The project will create lines of dialogue between these agencies to improve the management of Protected Areas, and specifically to create a streamlined management plan for the proposed Iyanola National Park. The participation of legislators will also be crucial to the project’s success. Saint Lucia has numerous potential legislative conservation caucus members based on current or previous membership in relevant ministries, as well as stakeholder constituencies, and come from both the United Workers Party (UWP) and Saint Lucia Labour Party (SLP).

- There are many potential partnerships in private tourism companies operating in Saint Lucia; many take an interest in conservation and community development, and some even offer tours of local fishing communities; these companies would likely be very interested in being part of the management planning process for the proposed Iyanola National Park. Saint Lucia's Hotel and Tourism Association's (SLHTA) vision is to be the premier private sector tourism organization in St. Lucia, providing sound and dynamic leadership for its members, functioning as the principal intermediary for tourism service providers, and, creating an influential lobby on tourism development issues.” Given its role, it will be a useful private-sector linkage for the caucus, especially through its environmental committee. Nonprofits that work in mangrove and sea turtle conservation, such as the Desbarras Sea Turtle Watching Group (DSTWG) and the Saint Lucia Heritage Programme, may also be interested stakeholders. The private landowners of the three large estates within the boundaries of the proposed National Park will also be large stakeholders whose cooperation and agreement will be necessary if the designation of the National Park is to pass.

Table 4: Saint Lucia Private Tourism Companies

| Company | Contact | About |
| --- | --- | --- |
| Real St. Lucia Tours | Phone: 1-758-717-8604 | Recognizes themselves to have an impact on the well-being of community, guides, island and customers. Works towards research and contributes to causes that would generate the most impact mainly towards schools and children. |
| Eco Adventures St. Lucia Tours & Taxi | Phone: 758-7188398, +1-758-716-8396; Email:jahrod.alcindor@stluciaecoadventures.com\ | Advertises as eco-tour company with tours of nature sites, waterfalls, volcano visits, rainforest hikes, birdwatching, and World Heritage Site visits. |
| St. Lucia Travel and Tours | Micoud Highway, Vieux Fort, St. Lucia Phone: 1-758-716-8598, Email: info@stlucia-travel.com | Offers tours to small fishing villages, town of rum factory and banana plantation, botanical gardens, volcano springs. |
| Discover Soufriere, St. Lucia | Soufriere, St. Lucia Phone: 758-489-7077 Email: charles@discoversoufriere.com | Offers various tours including ziplining through rainforest, whale watching, visiting coastal fishing communities, waterfall/botanical garden with knowledgeable guides able to provide information on the sites. |
| Cox & Company Limited | PO Box 88 Castries, Gros Islet Hwy, Choc, St. Lucia Phone: 1-758-456-5000; Email:info@coxcoltd.com | Offers tours including: visit of heritage sites displaying wide variety of flora and fauna and local traditions, dolphin and whale watching, canopy adventure tours, local village visits, and a cocoa production site. |
| Lucian Style Experience | 11 Reduit Beach Drive PO BOX RB2596 Rodney Bay, Saint Lucia WI Phone: 758-452-8300 | Similar to Cox & Co: Offers tours including: visit of heritage sites displaying wide variety of flora and fauna and local traditions, dolphin and whale watching, canopy adventure tours, local village visits, bird watching, deep sea fishing, and a cocoa production site. |

## 2.6	Baseline Analysis and Gaps

- Countries identified for this project are part of the Convention on Biological Diversity and have proclaimed extensive networks of PAs and reserves; however, actual protection at many of these “protected” areas is underdeveloped and underfunded. Public access, sustainable benefits to local people, parks capacity and infrastructure, organization, and visibility (public awareness) are often lacking. Many countries, despite having good intentions, under-invest in conservation because other immediate priority human needs take precedence. This is particularly true in areas affected by recent devastating hurricanes that have crippled and, in some cases, completely wiped out vital infrastructure. To the extent that active, managed conservation is carried out, there is a tendency to depend to a high degree upon international support. A 2004 World Resources Institute study estimated that between 350 million USD and 870 million USD could be lost annually between 2015 and 2050 due to declining fish stocks, reduced tourism, loss of shoreline protection, and coral reef degradation throughout the region.

- In Antigua and Barbuda, for example, parks have been designated, but the NBSAP notes the need to “establish the necessary policy and legal framework to facilitate the management and sustainable use and protection of the country’s biodiversity.” Environmental Protection Areas are authorized by 2003/2004 legislation that “places emphasis on protected areas and the establishment of a trust fund for the management of these areas.” Specifically, in the North East Marine Management Area, “The Environmental Awareness Group and Antiguan Government are protecting biodiversity through marine management, fisheries regulations, educational programs and community outreach.” Additionally, the Barbuda MMA (Marine Managed Area) contains the “largest seascape of mangroves-seagrass-corals in Eastern Caribbean.” These are discussed in more detail below.

- In 2018, the Government of Antigua and Barbuda’s provided funds totaling 3,514,908 USD to the Environment Division of the Ministry of Environment and Health, as well as 1,537,155 USD to the Fisheries Division and 504,998 USD to the Barbuda Administrative and General Services within the Ministry of Agriculture, Lands, Fisheries, and Barbuda Affairs budget. Relevant GEF-approved projects for Antigua and Barbuda include: Monitoring and Assessment of MEA Implementation and Environmental Trends in Antigua and Barbuda (UNDP); Sustainable Pathways – Protected Areas and Renewable Energy (UN Environment); and Developing a Strategic Approach to Sustainable Land Management (GEF Secretariat). The CEO endorsement of the project “Antigua and Barbuda the Path 2020” was approved by the GEF in late 2018 and will also have an impact in protected areas. Other conservation organizations working in Antigua and Barbuda include The Nature Conservancy (Marine Protection Campaign; “This Is Who We Are” Campaign); Fauna & Flora International; and the Waitt Institute.

Codrington Lagoon National Park currently operates based on a management plan for the 2009-2019 period. This plan allows for a coalition of stakeholders approved by the Barbuda Council to manage the park, including the Barbuda Council, the Fisheries Office of Barbuda, the Planning Office of Barbuda, the Environment Division of Antigua & Barbuda, the Small Businesses Association, the Sea Taxis Association, the Land Taxis Association, the Fishermen Association, and the Lobster Exporters Association.. According to the Management Plan, “The Committee is active and dedicated, but lacks technical capacity with respect to national park management.” The Park Manager oversees the work of four rangers that constitute the entire park staff. While the authorities and stakeholders are happy with the goals and strategies outlined 2009-2019 management plan, a need for an implementation plan was expressed. There are several issues that an implementation plan could address: the overlapping authority of national and local laws is an area that has not yet been finalized; the committee of stakeholders is not officially gazetted, and therefore strategies for engagement and group collaboration in management have been identified as a need. Additionally, the monitoring and enforcement of National Park regulations within the Park could be improved to enhance the technical capacity of rangers and park management. In regards to overlapping authority, several laws, especially regarding forestry, have local and national provisions that could be in conflict, raising the need for more clear delineation of authority. In regards to enhancing the enforcement of regulations, provisions could be made to reduce development within the park and monitor and regulate fishing within the park to avoid exploiting the important resources that the lagoon provides to the region.

- In Dominica, several protected areas have been established. In addition, terrestrial and marine sites are proposed for protection but are not formally designated. PAs fall primarily under the responsibility of the Division of Forestry, Wildlife, and National Parks, and the Fisheries Division, Ministry of Agriculture and Fisheries. There are two major sources of funding for the management of PAs: governmental budgets and self-generated funds. Dominica’s PAs have traditionally been funded from the government treasury and given low priority, as they were seen to have little to contribute to the national development process. Annual budgets are often just enough to keep only basic management structures in place, and capital budgets are insufficient to prevent depreciation and decay of PA infrastructure. Relevant GEF-approved projects for Dominica include: Supporting Sustainable Ecosystems by Strengthening the Effectiveness of Dominica’s Protected Areas System (UNDP); Sustainable Financing and Management of Eastern Caribbean Marine Ecosystems (The World Bank); and Sustainable Land Management in the Commonwealth of Dominica (UN Environment). The proposed project “Strengthening resilience in the Morne Trois Pitons National Park in the aftermath of Hurricane Maria through participatory forest rehabilitation / restoration, sustainable land management practices, and the development of livelihood options,” which will also target activities in the protected area of the Morne Trois Pitons, is currently under development. The Nature Conservancy is also active in Dominica through its Marine Protection Campaign and “This Is Who We Are” Campaign.

- Although Cabrits National Park was designated in 1975 under the National Parks and Protected Areas Act, its management effectiveness has been restricted by funding limitations and overlapping authorities. The Park has a management plan dating back to 1986 that provides for basic management strategies and development concepts, and has been supplemented by subsequent livelihood plans conducted in 2010. The Park has a small staff and collects entrance fees, and the recently restored Historic Fort Shirley has the capacity to host large events, such as weddings, and has been rented for such occasions in the past. According to the livelihood plan, park management expenditures at Cabrits National Park in 2010 “totalled some $50,000, primarily for two grounds maintenance workers controlling vegetation and for a cleaner for the visitor centre and a warden/receptionist to authorize visitor site passes”, creating approximately 14 full-time livelihoods for the terrestrial component management Notably the 1986 management plan did not provide for marine component management in the Park, and while a marine management plan was proposed in 2007 it remains under consideration by the Division of Forestry, Wilderness, and National Parks, and is considered a ‘working plan’ at this point in time.  Wetland boundaries are well defined and studied in CNP, but there is some ambiguity surrounding the marine boundaries, which may not be obvious to non-park authorities. Regarding the designation of a cruise ship berth and dock in Douglas Bay, an ongoing dispute over management between the Port Authority and the National Parks Division has prevented significant monitoring and enforcement of regulations in the park. Furthermore, local fishermen have objected to the boundaries that exist based on traditional fishing sites and maintenance of their livelihood

- Grenada’s environmental policy and legislation, while existent, need to be reviewed and updated per the NBSAP. The NBSAP noted a “lack of enforcement of relevant laws and regulations,” caused in part by a need for skilled human capital. A wider variety of stakeholders also need to be engaged in decision making. There are three main players in protected area management: the Ministry of Tourism, the Department of Forestry, and the Department of Fisheries. Currently, the estimated combined budget from these institutions in PA-related activities is 4 Million USD over the project period. Relevant GEF-approved projects for Grenada include: Sustainable Financing and Management of Eastern Caribbean Marine Ecosystems (The World Bank); Implementing a “Ridge to Reef” Approach to Protecting Biodiversity and Ecosystem Functions within and around Protected Areas (UNDP); and others. TNC is also working on-the-ground in Grenada through its Marine Protection Campaign, “This Is Who We Are” Campaign, and “At the Water’s Edge” Mangrove Replanting Initiative.

- Within the Grand Anse MPA, anecdotal evidence supports the NBSAP’s identification of a gap between legal frameworks and enforcement. This gap is attributed in part to small community sizes that discourage conflict between wardens and fishermen, as well as inconsistent compliance by tourism companies to pay the entrance fees for visitors to the MPA. Some illegal fishing is still reported within the MPA, as well.

- In partnership with UN Environment and the GEF, Saint Lucia created the NBSAP, adopted in 2000. The plan outlined the vision for a collaborative, cross-sector approach to successful resource and biodiversity management, citing the need for “improved coordination of policies and activities relevant to, or impacting on, biological diversity, as many of the problems currently observed result from the fragmentation of policy instruments and from the absence of effective coordination among actors, and there is need to establish effective partnerships among governmental and non-governmental partners.” The NBSAP notes that the “legal instruments for the conservation and management of publicly owned resources appear generally adequate.” Laws have allowed for the creation of 20 MPAs in Saint Lucia, and the country has detailed management plans for parks in place, though the NBSAP notes need for training activities aimed at governmental agencies, notably in the area of protected area management. Saint Lucia ́s estimated investment in protected areas is 500,000 USD to 750,0000 USD per year. This is composed of government budget and also fees such as those coming from yachting, diving, and snorkeling amongst others. Relevant GEF-approved projects for Saint Lucia include: Iyanola - Natural Resource Management of the NE Coast (UN Environment); Sustainable Financing and Management of Eastern Caribbean Marine Ecosystems (The World Bank); and Developing Organizational Capacity for Ecosystem Stewardship and Livelihoods in Caribbean Small-Scale Fisheries (StewardFish) (FAO). The project “Integrated Ecosystem Management and Restoration of Forests on the South East Coast of Saint Lucia” was approved by the GEF and will also have an impact in protected areas.

- Saint Lucia’s Iyanola National Park has been proposed but not yet finalized and designated by law, and major gaps in policy include unclear management authorities for Protected Areas, and conflicts with landowners in the designation and management of the National Park. The proposal that exists includes extensive terrestrial and marine areas, which include several local subsistence-level communities, and three major privately owned estates; conservation objectives are not commonly supported by local communities in Saint Lucia and the Fisheries Act and National Preserve Act both strictly regulate use of resources within designated areas, which could become a source of contention for these communities that survive mainly through fishing and livestock grazing. Existing consultation with stakeholders through other projects has mentioned the interest in these communities in alternative livelihoods, but indifference to designation of a National Park. The area itself poses challenges to its management; for example, it encompasses twelve offshore islands that are in separate MMAs, which will require clear legal delineation of regulations and enforcement, as well as mangrove forests, for which authority designation is unclear between the Forestry and Fisheries divisions. The terrestrial area currently has poor infrastructure, limiting access to its interior, and very little economic importance vis a vis tourism, which may also pose challenges to enforcement policies. An interim management plan is being prepared for the entire region under an existing GEF project, but does not have the endorsement of parliamentarians or an expected finish date. Such a plan could be an important step towards an umbrella management plan for the proposed National Park.

## 2.7	Linkages with Other GEF and Non-GEF Interventions

Lessons learned from a) the GEF/World Bank Project “Caribbean Regional Oceanscape Project,” b) the GEF/UN Environment “Integrating Watershed and Coastal Area Management (IWCAM) in the Small Island Developing States of the Caribbean” project, and c) the GEF/World Bank “OECS Protected Areas and Associated Sustainable Livelihoods” project will be reviewed and will be shared and disseminated as appropriate during the current project. These projects, completed over the past decade, sought to: a) strengthen capacity for ocean governance and coastal and marine geospatial planning in selected Caribbean countries; b) assist participating countries in improving their watershed and coastal zone management practices in support of sustainable development (including coastal area management and biodiversity; tourism development; protection of water supplies; land-based sources of pollution; etc.); and c) contribute to the economic development of the Small Island Development States (SIDS) of the Organization of Eastern Caribbean States (OECS) region through (i) the strengthening of existing and the creation of new protected areas; and (ii) providing environmentally sustainable economic opportunities for communities living in the surrounding areas.

- The inclusion of UN Environment on the Project Steering Committee will ensure that coordination with a range of GEF-funded projects completed, under implementation, or planned will be duly considered in the strategic planning of interventions for the current project. The project will engage with relevant UN teams at both national and regional levels, taking cognizance of the UNDAF, during the inception phase to avoid duplication of project strategy and build on complementary actions by these agencies in the countries.

- The project contributes to achieving the GEF-6 Biodiversity Strategy as follows: BD 1: Improve sustainability of protected area systems: Program 1: improving Financial sustainability and effective management of the national ecological infrastructure and BD 4: Mainstream biodiversity conservation and sustainable use into production landscapes/seascapes and sectors: Programme 9: Managing the Human-Biodiversity Interface (further discussed in paragraph 3.1 below). It also supports the GEF’s continuing focus on sustainable development for SIDS.

- Additionally, it supports achievement of several of the UN Sustainable Development Goals, particularly SDG 14: Life Below Water: Conserve and sustainably use the oceans, seas and marine resources for sustainable development; and SDG 15: Life on Land: Protect, restore and promote sustainable use of terrestrial ecosystems, sustainably manage forests, combat desertification, and halt and reverse land degradation and halt biodiversity loss. The project also contributes to SDG 5: Achieve gender equality and empower all women and girls through expanding leadership opportunities in conservation governance to women and SDG 8: Promote sustained, inclusive and sustainable economic growth, full and productive employment and decent work for all  by seeking to expand livelihood opportunities in protected areas management for key protected area sites.

- The UN Environment Regional Office for Latin America and the Caribbean will support the promotion and integration of the outcomes from this project in the Caribbean 2017-2021 United Nations Multi-Country Sustainable Development Framework (MSDF) (2030 Caribbean), as well as provide a platform for dissemination of results, and provision of technical support to countries.

- Project contributions to Priority Area 4 (A Sustainable and Resilient Caribbean) of the UNMSDF will primarily relate to the following goals: i) strengthen institutional and community resilience at both regional and national levels, in terms of natural resources management; the protection and sustainable use of terrestrial, coastal and marine ecosystems; renewable energy systems; and inclusive and sustainable societies, and ii) inclusive and sustainable solutions adopted for the conservation, restoration, and use of ecosystems and natural resources.

- The project contributes to the goals of the Caribbean Environment Program (CEP), particularly to the Protocol on Specially Protected Areas and Wildlife (SPAW). The SPAW Protocol is dedicated to protecting the coastal regions and marine biodiversity with a specific focus on “Marine Protected Areas and Wildlife, Threatened and Endangered Marine Species, and Marine and Coastal Ecosystems.”  The project will directly contribute to the four programme elements of the SPAW Protocol; (i) Strengthening and Management of Protected Areas in the Wider Caribbean Region, (ii) Development of Guidelines for the Management of Protected Areas and Species, (iii) Conservation of Threatened and Endangered Species and (iv) Conservation and Sustainable Use of Marine and Coastal Ecosystems.  It should be noted that while Antigua & Barbuda and Saint Lucia have ratified the Protocol, Dominica and Grenada remain engaged through the wider ambit of the CEP and contribute actively to the pursual of the strategic elements of the Protocol.  Achievements under the SPAW Protocol include the advancement of the Global Coral Reef Monitoring Network, a memorandum of understanding with Sargasso Sea Commission and the Caribbean Regional Fisheries Mechanism, and a sub-project with the Meso-American Reef Fund. Component 2 of the project, which aims to enhance technical capacity of protected areas management, including marine protected areas and marine components of national parks, directly benefits this goal.

- The project is fully consistent with UNEP’s Programme of Work (and budget) for the 2018‒2019 biennium where it is closely aligned to Subprogramme 3 ‘Healthy and productive ecosystems’ under which countries are supported to increasingly manage marine, freshwater and terrestrial ecosystems through an integrated approach that enables them to maintain and restore biodiversity, ecosystems’ long-term functioning and supply of ecosystem goods and services.  Relevant expected accomplishments of the sub-programme to this project are that (i) the health and productivity of marine, freshwater and terrestrial ecosystems are institutionalized in education, monitoring and  cross-sector and transboundary collaboration frameworks  at the national and international levels, and (ii)  policymakers in the public and private sectors test the inclusion of the health and productivity of ecosystems in economic decision-making.  The potential legislative outcomes from Component 1 of the project will promote ecotourism and sustainable fisheries practices, and also place additional information and data in policymakers’ hands through briefing events and stakeholder engagement. Component 2 will enhance government capacity to manage biodiversity within protected areas, including through mobilizing government funds and resources towards enhanced management frameworks and technical capacity in protected areas with significant levels of biodiversity.

- At the national and regional level, this project has commonalities with a number of GEF and non-GEF interventions, and the CCN team will reach out to representatives of each of these projects to engage in dialogue, seek collaboration, and initiate sharing of knowledge and best practices. These programs include the following:

Regional:

- Catalyzing Implementation of the Strategic Action Programme for the Sustainable Management of Shared Living Marine Resources in the Caribbean and North Brazil Shelf Large Marine Ecosystems (CLME+): This UNDP/GEF Project (GEF ID 5542; 2015-2019) is a 5-year project that specifically aims at facilitating the implementation of the 10-year politically endorsed Strategic Action Programme for the Sustainable Management of the Shared Living Marine Resources of the Caribbean and North Brazil Shelf Large Marine Ecosystems (CLME+ SAP). The project seeks to achieve this by facilitating ecosystem-based management/an ecosystem approach to fisheries (EBM/EAF) within the CLME+ region, in such a way that a sustainable and climate resilient provision of goods and services from the region’s living marine resources can be secured. Participating countries include Antigua and Barbuda, Dominica, Grenada, and Saint Lucia, among others.

- Integrating Water, Land and Ecosystems Management in Caribbean Small Island Developing States (IWEco): This 5-year GEF/UNEP/UNDP project aims to contribute to the preservation of Caribbean ecosystems that are of global significance and the sustainability of livelihoods through the application of existing proven technologies and approaches that are appropriate for SIDS through improved fresh and coastal water resources management, sustainable land management, and sustainable forest management that also seek to enhance resilience of socio-ecological systems to the impacts of climate change. Participating countries include Antigua & Barbuda, Grenada, and Saint Lucia.

- Developing Organizational Capacity for Ecosystem Stewardship and Livelihoods in Caribbean Small-Scale Fisheries (StewardFish): This GEF/FAO project seeks to support the implementation of strategies 1, 2, 3 and sub-strategies 1.4, 1.5, 2.7, 2.8, 3.7 of the Caribbean and North Brazil Shelf (CLME+) SAP in Caribbean Regional Fisheries Mechanism (CRFM) Member States by empowering fisherfolk throughout fisheries value chains, and to upkeep their engagement in resource management, decision-making, and sustainable livelihoods, with strengthened institutional support at all levels. Participating countries include Antigua and Barbuda and Saint Lucia, among others.

- Advancing the Nagoya Protocol in Countries of the Caribbean Region: This GEF/UN Environment project seeks to raise awareness of the Nagoya Protocol on Access to Genetic Resources and the Fair and Equitable Sharing of Benefits Arising from their Utilization. This 2016-2019 project covers eight countries, including Antigua and Barbuda, Grenada, and Saint Lucia, among others.

- Caribbean Challenge Initiative (CCI)/Caribbean Biodiversity Fund (CBF): The Caribbean Challenge Initiative (CCI) is an historic conservation initiative that brings together governments, companies, and partners to accelerate action on conservation in the Caribbean. Together, the 9 participating countries and territories have committed to conserve at least 20% of nearshore and coastal environments in marine protected areas by 2020 with the help of private- and public-sector partners. The Caribbean Biodiversity Fund has been established to support achievement of the CCI commitments by 2020. Partners include 8 island nations — Bahamas; Dominican Republic; Jamaica; Saint Vincent and Grenadines; Saint Lucia; Grenada; Antigua and Barbuda; Saint Kitts and Nevis. It is sponsored by the private sector and country governments. The Caribbean Biodiversity Fund is currently supported by the German Development Bank, GEF, and The Nature Conservancy. CCI private-sector partners include several CCN partners, such as The Moore Foundation, UNDP, UN Environment, World Bank, etc. It should be noted that while Antigua & Barbuda and Dominica are not participating countries in this initiative, members of the legislative caucuses assembled under this project will be exposed to complementary activities of the Caribbean Challenge Initiative/Caribbean Biodiversity Fund.  The project will seek out opportunities for synergies between the two initiatives in implementation

- Cartagena Convention: The Convention for the Protection and Development of the Marine Environment in the Wider Caribbean Region (WCR), or Cartagena Convention, is a regional legal agreement for the protection of the Caribbean Sea. It is supported by the Protocol Concerning Co-operation in Combating Oil Spills in the Wider Caribbean Region; the Protocol Concerning Specially Protected Areas and Wildlife (SPAW) in the Wider Caribbean Region; and the Protocol Concerning Pollution from Land-Based Sources and Activities. The Convention seeks to prevent, reduce, and control marine pollution from a variety of sources, including ships, dumping, sea-bed activities, airborne sources, and land-based sources and activities.

- The SPAW Protocol seeks to "Take the necessary measures to protect, preserve and manage in a sustainable way: areas that require protection to safeguard their special value, and threatened or endangered species of flora and fauna." Program elements include: Strengthening and Management of Protected Areas in the Wider Caribbean Region; Development of Guidelines for the Management of Protected Areas and Species; Conservation of Threatened and Endangered Species; and Conservation and Sustainable Use of Marine and Coastal Ecosystems.

- The Protocol Concerning Pollution from Land-Based Sources and Activities includes regional effluent limitations for domestic wastewater (sewage) and requires the development of plans to address agricultural non-point sources of pollution.

- The Protocol Concerning Co-operation and Development in Combating Oil Spills in the Wider Caribbean Region (the Oil Spills Protocol) seeks to “Strengthen national and regional preparedness and response capacity of the nations and territories of the region and Facilitate co-operation and mutual assistance in cases of emergency to prevent and control major oil spill incidents.”

- The Nature Conservancy Regional Programs: The Nature Conservancy works in Antigua and Barbuda, Dominica, Saint Lucia, and Grenada (among others) to grow the capacity of the Eastern Caribbean people to preserve the natural beauty and resources of their islands. The Conservancy works with local governments and partners to identify priority sites for establishing new MMAs and to ensure new and existing protected areas are effectively managed. The Conservancy provides critical support to Eastern Caribbean countries to secure the funding, resources, data, and management strategies needed to achieve their marine conservation goals. Five countries have established national conservation trust funds, with the help of the Conservancy and partners, which steer long-term funding to the most urgent conservation initiatives in each country. The Conservancy also works with governments on debt-for-nature swaps. Efforts include: restoring corals, restoring mangroves, making communities more resilient by restoring natural protective features of coastal ecosystems, using cutting-edge data to develop habitat maps of nearshore and coastal environments, engaging local communities to raise awareness of the need to protect and conserve the marine resources on which they depend, and providing mentorship and training in areas such as protected area monitoring, fisheries management, and disaster preparedness.

- Caribbean Community Climate Change Centre (CCCCC) Regional Programs: The Centre coordinates the Caribbean region’s response to managing and adapting to climate change and provides climate change-related policy advice and guidelines to CARICOM Member States through the CARICOM Secretariat. Services provided by the Centre include providing information for decision-making through an information clearinghouse, climate modeling, threat identification/early warning, Lidar surveys, project development and support (the CCCCC is an Accredited Regional Implementing Entity (RIE) to the UNFCCC Green Climate Fund and functions as an executing agency for various development partner and national government initiatives), training on climate-related issues, consultancy services and joint venture services.

- The GEF Caribbean Fund for Wastewater Management (GEF-CReW) is a four-year project that began in 2011. It was funded by the Global Environment Facility (GEF) and implemented by the Inter-American Development Bank (IDB) and the United Nations Environment Programme (UNEP) involving thirteen countries, including Antigua and Barbuda and Saint Lucia. The project had five Components: Investment and innovative financing, Reforms for Wastewater Management, Communication, Outreach & Training, Monitoring and Evaluation, and Project Management, with responsibility shared between the Implementing Agencies, the Inter-American Development Bank (IDB) and the United Nations Environment Programme (UNEP). A second phase of the project is under consideration to build on the lessons from the first project.   The threats posed by untreated wastewater to the marine environment of the Caribbean Sea and its sensitive and economically valuable ecosystems is the is underlying driver which is highly relevant to this project.

- Other Regional Programs: Other entities working to support sustainable development and environmental conservation in the region include the Caribbean Development Bank, the Caribbean Sustainable Economic Development Network, CARICOM, and the Organization of Eastern Caribbean States (OECS), among others.

National:

Antigua and Barbuda:

- GEF Agencies: GEF agencies with projects in Antigua and Barbuda include the GEF Secretariat, UNDP, and UN Environment.

- Blue Halo Barbuda: The Barbuda government has, with the assistance of the Waitt Institute, voluntarily adopted sustainable and comprehensive ocean and coastal management and no-fish zones around the island. This project, 'Blue Halo Barbuda,' involved developing and implementing sustainable ocean policies focused on marine spatial planning, sanctuary zones, and fisheries regulations. The Waitt Institute continues to work closely with the government and people of Barbuda to support implementation of these regulations. This includes setting up a long-term scientific monitoring program, training local staff in marine ecology and field research techniques, recommending enforcement approaches, providing needed equipment, and working with schools to develop an ocean education curriculum.

- The Path to 2020: This GEF-funded and UNEP-implemented project aims to implement Objective 1 of Antigua and Barbuda’s National Biodiversity Strategy and Action Plan (2014 – 2025): A national system, including protected areas, for the management and conservation of biodiversity conservation is developed and established. By strengthening institutional coordination for protected areas, supporting legal frameworks, and blending local co-investment with international financing, this project will position Antigua and Barbuda to tap into global opportunities in conservation investments. The project has three main components:  i. Strengthening regulations, institutions and financing mechanisms for the national Protected Areas System; ii. Expansion of protected areas in support of species conservation; iii. Pilot livelihood financing mechanisms that support conservation and sustainable use of biodiversity and plant genetic resources in the newly designated Shekerley Mountain Management Area.

- Sustainable Pathways-Protected Areas and Renewable Energy (SPPARE): This GEF-funded and UNEP-implemented project responds to the financial constraints of government to meet the estimated operational costs of the biodiversity rich Protected Areas and forest systems of Antigua and Barbuda through formalizing agreements with the Sustainable Island Resource Framework Fund (SIRF) to increase revenue for Protected Areas systems, pilot installation of renewable energies, improved management effectiveness of financially sustainable pilot protected areas, and restoration of surrounding watershed forests to improve water management and hydro energy storage.

Dominica:

- The World Bank: The World Bank has an “Emergency Agricultural Livelihoods and Climate Resilience Project” in Dominica that seeks to restore agricultural livelihoods and enhance climate resilience of farmers and fisher folk affected by 2017’s Hurricane Maria. Its components include restoration of agriculture through cropping systems, livestock and fisheries systems, and agribusiness capabilities, restoration of infrastructure in Agriculture, Livestock, and Forestry and institutional strengthening of the Ministry of Agriculture and Fisheries (MAF.)

- Food and Agriculture Organization (FAO): Under its Special Fund for Emergency and Rehabilitation Activities- Agricultural Input Response Capacity, FAO is working with the Ministry of Agriculture and Fisheries in Dominica to restore the fisheries sector. Belgium funded the $100,000 USD project on agricultural recovery after Hurricane Maria’s decimation in 2017, with its objective to protect food security of vulnerable fisher folk affected by the Hurricane through the distribution of equipment and repairs to vessels.

- GEF Agencies: GEF agencies with projects in Dominica include UNDP and UN Environment.

- Sustainable Land Management in the Commonwealth of Dominica: This GEF-funded and UNEP-implemented project seeks to establish landscape level planning, and information and coordination frameworks to support sustainable agriculture and sustainable watershed management in Dominica. Its two components are to enable a ‘whole island’ landscape framework to plan, monitor and adapt land management and to reduce the effects of land degradation on ecosystem services through sustainable land management.

Grenada:

- The Nature Conservancy: The Nature Conservancy has a number of on-the-ground projects in Grenada. It helped establish Grenada’s first coral nurseries and trained local youth to maintain them, building both local expertise and employment opportunities; it is assisting fishing communities that have seen severe flooding and erosion with mangrove planting and restoration work; and its scientists have installed engineered reef structures in  Grenada, using community labor and local materials, that reduce wave  energy and protect the coast from  storm impact, while hosting coral, fish, and other species. This pilot project can serve as a model for protecting coastal communities around the Caribbean.

- Implementing a “Ridge to Reef” Approach to Protecting Biodiversity and Ecosystem functions within and around Protected Areas in Grenada: This GEF/UNEP project aims to ensure that biodiversity and ecosystems functions within and around marine and terrestrial PAs in Grenada are better protected from threats through the adoption of an integrated “Ridge to Reef” approach that increases PA management effectiveness and applies targeted sustainable land (and coastal sea) management practices, while ensuring ecosystems resilience to climate change. Implemented by the Grenadian government, this project is expected to conclude in December 2019.

- GEF Climate Resilient Agriculture for Integrated Landscape Management.  This UNDP-implemented project focuses on biodiversity and land degradation aims to operationalize integrated agroecosystem management through mainstreaming biodiversity conservation in the production landscape and increasing resilience of agricultural system.  This project will have alignment with the intended project outcomes of strengthened systemic and institutional capacity for promoting SLM through cross-sectoral collaboration for land use planning and management, the operationalization of five integrated watershed management plans and the development of a training system for integrated natural resource management.

- Global Island Partnership (GLISPA): Led by the Presidents of Palau and Seychelles, the Prime Minister of Grenada, and the Premier of the British Virgin Islands, the Global Island Partnership promotes action to build resilient and sustainable island communities by inspiring leadership, catalyzing commitments, and facilitating collaboration. It is a partnership for all islands, regardless of size or political status, to take greater action to conserve and sustainably utilize invaluable island natural resources that support people, culture, and livelihoods around the world. Partners include Conservation International, GEF, and UNDP, among many others.

- Conserving 25% of Grenada's nearshore marine environment and the sustainable development of its coastline by 2020 is a commitment by the Government to be underpinned by fully functioning sustainable finance mechanisms that will provide long-term and reliable funding to conserve and sustainably manage the marine and coastal resources and the environment. Partners include the Government of Grenada, The Nature Conservancy, among many others.

- GEF Agencies: GEF agencies with projects in Grenada include The World Bank and UNDP.

Saint Lucia:

- Increase Saint Lucia's Capacity to Monitor MEA Implementation and Sustainable Development: This GEF/UNEP project seeks to strengthen institutional capacity for the implementation and monitoring of international conventions as a follow-up to the National Capacity Self Assessment (NCSA) of Saint Lucia and to better integrate environmental concerns, and the value of ecosystems, into its broader development frameworks.

- The Nature Conservancy Mangrove Restoration Project: TNC is working with partners to train communities and governments to restore Ma’ Kôté, the largest mangrove forest in Saint Lucia and the Eastern Caribbean—in addition to planting mangrove seedlings to restore mangroves throughout other islands. Like reefs, these mangroves will help protect coastlines from flooding and erosion, as well as support fisheries production.

- Iyanola-Natural Resource Management of the NE Coast (GEF and UNEP): This project approved in 2013 aims to increase the management effectiveness and sustainable use of the North East Coast’s natural resource base to generate multiple global environmental benefits. The area it covers extends beyond the boundaries of the proposed Iyanola National park and notable achievements of the project to date include a baseline inventory of fauna and flora, finalized Land Use Plan for the region, a biodiversity, livelihoods and needs assessment, and a preparation of ecosystems services valuation that is in process and awaiting final results. One major consultancy of the project involves an interim management plan for the region, from which Component two of this project would build upon.

- GEF Agencies: GEF agencies with projects in Saint Lucia include the GEF Secretariat, the World Bank, UNDP, and UN Environment.

# Section 3: Intervention Strategy (Alternative)

## 3.1	Project Rationale, Policy Conformity and Expected Global Environmental Benefits

- The Conservation Council of Nations will support the countries of Antigua and Barbuda, Dominica, Grenada, and Saint Lucia to establish legislative “conservation caucuses,” which are communities of legislators organized around a shared commitment to seek solutions to natural resource management challenges. This project will foster increased capacity and willingness among these legislative bodies to assess and address conservation challenges, leveraging CCN’s experience, ICCF’s relationships, and the expertise of partners and stakeholders to focus caucus attention and energy on putting in place the laws, policies, and regulations needed to address the targeted nations’ conservation challenges. In addition to driving the conservation agenda within their own nations, caucus members will work with one another to harmonize policies, laws, and practices among participating Caribbean nations.

- This tried and tested innovative approach has been successfully applied by CCN in other developing countries throughout Africa and Latin America, through assistance from the GEF, guided by the experiences of the bipartisan U.S. Congressional International Conservation Caucus and U.S. Congressional Oceans Caucus.

- The new and enhanced laws, regulations, and policies, as well as improved management of protected areas, generated through this project will generate environmental benefits extending to the greater good of the economy, progress, and many other realms and will help to safeguard globally significant biodiversity.

- Common threats to biodiversity and sustainable management of the marine protected areas in the Eastern Caribbean are overfishing, deforestation, and pollution. All are essentially resource management issues which impact both the citizens of each country and the natural environment. By building awareness and capacity in the legislatures, one of the goals of this project is to raise awareness of the impacts of these issues and provide experts to advise on international best practices to help confront these conservation challenges.

- The awareness and capacity built through briefings, workshops, field visits, and regional interactions created as part of the outputs in this program are designed to significantly raise levels of knowledge and engagement about key issues, including not only direct threats to biodiversity but also the need to mainstream conservation in landscapes with other issues including employment, public access, local land rights especially of indigenous peoples, and effects of changes upon women. This increased awareness will occur among political elites who have actual ability to affect these trends for the better.

- The proposed project is consistent with the following goals of the GEF-6 Biodiversity Strategy:

- BD 1: Improve sustainability of protected area systems: By building political will and capacity of policymakers to develop improved policy and legislation to address the region’s conservation challenges, this project will support greater national-level ability to manage protected areas and, if possible, increased financial support for protected area management. It will provide a forum for exploration of possibilities for/feasibility of expanding the protected area estate of target countries and greater knowledge and sophistication about long-term support using public-private partnerships. The on-the-ground work of CCN’s International Conservation Corps will enhance institutional capacity to manage protected areas such that they achieve their conservation objectives.

- BD 4: Mainstream biodiversity conservation and sustainable use into production landscapes/seascapes and sectors: Protected areas are essential to conservation and sustainable use of biodiversity; however, they are often located in mixed-use land- and seascapes, and their resources may be needed to provide for human needs. The GEF is working to support policies, strategies, and practices that engage the public and private sectors to conserve and sustainably use biodiversity. The legislative conservation caucuses formed as part of this project will provide ideal fora for policymaker engagement and education on this topic, creating venues for a broader national dialogue extending beyond legislators and traditional park officials, to include all significant stakeholders, which over time can lead to major policy reforms that better balance conservation of biodiversity and other natural resources with the necessities of national economic development. In addition, protected area management plans and strategies facilitated by the International Conservation Corps will be key to formalizing conservation and sustainable use mainstreaming within specific protected areas.

- The project specifically is: (i) relevant to the objectives of GEF’s biodiversity strategy; (ii) in support of priorities identified by the Conference of Parties (COP) of  the CBD; (iii) highly likely to have a broad and positive impact on biodiversity; (iv) targeting potential for replication; (v) delivering global demonstration value; and (vi) contributing to global conservation knowledge. This project will address biodiversity conservation by increasing capacity, improving governance, and raising critical awareness.

- The proposed project will deliver global environmental benefits (GEBs) through enhanced awareness and capacity, which will promulgate national-level interventions (policy instruments or fiscal reforms) that link biodiversity valuation, with development planning which integrates sustainable consideration of ecosystem services.  GEBs will be targeted to have a positive impact on areas of high global biodiversity value, e.g., PAs.  A long-term weakness of conservation efforts in the region has been the lack of a strong domestic constituency for conservation. Constituencies for the over-use and abuse of the environment are often, by contrast, immediately powerful because they deliver short-term profits or convenience. Conservation funding has also been excessively dependent on donated resources from international bodies.  This leaves conservation excessively dependent upon the grant cycle and fashions in giving.  The creation of legislative conservation caucuses, and their support by a conservation council made up in large part of tourism-related businesses, will create for the first time a regional center for political will to stand up to the exploiters and abusers on behalf of the long-term interests of the countries in a healthy, attractive, and sustainable environment. The work of the International Conservation Corps will also increase biodiversity conservation by building the capacity of protected area managers to implement policies and legislation and to better balance the needs of the ecosystems they manage with the services they provide.

## 3.2	Project Goal and Objective

- The objective of this project is to support biodiversity conservation in the Antigua and Barbuda, Dominica, Grenada, and Saint Lucia through enhanced political will and capacity building for improved management of marine protected areas (MPAs), marine management areas (MMAs), and protected areas (PAs). The project will provide parliamentarians in select countries with knowledge, expertise, and capacity to formulate and implement sound conservation policies and programs and will improve capacity of MPA, MMA, and PA managers through shared expertise and mentoring.  The project was designed based on the theory of change depicted in Appendix 16.

- In each of the countries the project will focus on management enhancement of key biodiversity areas and protected areas of high biodiversity importance.  The sites are the Codrington Lagoon National Park (Barbuda), the Cabrits National Park and marine area (Dominica), the Grand Anse Marine Protected Area (Grenada) and the Iyanola National Park (Saint Lucia).  Of these, the Barbuda Codrington Lagoon National Park and Iyanola National Park are designated Key Biodiversity Areas.

- The Cabrits National Park and marine area, while not currently formally designated a KBA, harbors critically important biodiversity in its marine environment, with the predominant features being extensive and diverse coral reefs, dominated by a variety of soft corals, sponges and hard corals and sea grass ecosystems, and important nest sites for Hawksbill and Leatherback turtles.  The area is also frequented by various whale species.  The marine area is an important reef fishery for the town of Portsmouth and environs, and there has been a long-recognized need for protection of the biological diversity, enhancement of fisheries management practice, preservation of cultural assets (wrecks) and maintenance of recreational and tourism services.

- The Grand Anse Marine Protected Area is a designated Marine Protected Area / Protected Land and Seascape (since 2018).  It is an important biodiversity area harboring diverse coral reefs and a fish sanctuary.  Studies from 2015 show that the coral reefs in the Grand Anse Reef Complex are above the Caribbean average, however fish biomass are below the Caribbean average, particularly for economically and ecologically important species (snapper, grouper, parrotfish and surgeonfish). A reef health index reference based on a number of indicator species surveyed indicates “very good” reef condition due to low fleshy macroalgal cover and “critical” in the case of commercial fish species due to low biomass values.

## 3.3	Project Components and Expected Results

Component 1. Build and enhance political will for conservation

- This component will create the “architecture” needed for policy change, specifically the required mechanisms, relationships, and willingness among policymakers to take steps toward conservation of key biodiversity resources. The intended outcome is to create new legislative conservation caucuses with increased capacity and willingness to assess and address biodiversity challenges at high levels of government.

- This component also aims to build strategic partnerships and enhance buy-in with key private-sector and non-governmental partners that are heavily reliant on the resources within these parks and protected areas, notably hotel properties, dive-shops, tour operators and user associations.  These stakeholders have critical roles in support of the legislators in terms of their recognized contributions to business opportunities linked to the strengthening of economic sustainability of the protected areas under Component 2.

- Component 1 draws on CCN’s and ICCF’s best practices for creating political will and increasing capacity for conservation, and will showcase the legislative conservation caucus model, which has been implemented successfully in more than a dozen developing nations such as Kenya, Colombia, Malawi, and others, through assistance from the GEF, based on the experiences of the U.S. Congressional International Conservation Caucus.

- Policymakers are largely influenced by political ambition and by the actions, impressions, and recognition of their colleagues; in this sense building a legislative conservation caucus is similar to managing a campaign. To create each caucus, CCN will build relationships within legislative bodies in the targeted countries, identify and select a few strong leaders, and organize opportunities and mechanisms to bring policymakers together so that the caucus model can be “pitched and sold” utilizing the influence of their peers and a momentum of support. As such, it is critically important that national counterparts have active leading roles; this is envisaged for the champions from the legislatures who are expected to be in the forefront of agenda-setting and policy-making for conservation. CCN will then build an organization around this group of policymakers, bringing in public- and private-sector partners to empower the caucus with sound information and give them the tools to convince a wider following that the policies they are pursuing are beneficial to their constituencies and the nation. CCN will also involve caucus members in interactions with legislators from other nations, demonstrating how important these policies are to a wide body and providing opportunities for recognition regionally and internationally. This is a proven process that has been effective within legislative bodies around the world. It also promotes longevity; as policymakers receive recognition for their work, they and their peers are motivated to continue and expand this work.

- From the experience gained in launching conservation caucuses, CCN has learned the importance of focusing on all sectors of society, not just parliament. In replicating the CCN caucus-building model in other countries, the intent is to build support “block by block” among the corporate, government, and civil society sectors, not just within the legislature. CCN understands the benefit of involving those who are considered part of the problem as well as those trying to solve the problem.  It was further learned that parliamentarians respond with more interest and involvement when they see immediately that the stakeholder groups they represent are also interested in the caucus. This broader approach takes caucus-building beyond a legislative exercise and creates real possibility for collaboration and learning.

Outcomes: The planned outcomes for Component 1 are:

Outcome 1.1 Self-sustaining legislative conservation caucuses support conservation of key biodiversity resources through enhanced political will; and

Outcome 1.2 Enhanced cooperation between the legislative members and stakeholders in their respective countries is promoted by broader knowledge of the conservation challenges in the Eastern Caribbean and best practices (i.e., legislators take leadership to propose and adopt new legislation).

Outputs: Planned outputs include:

1.1.1 Multiparty legislative conservation caucuses of legislators including structure and functioning for Antigua and Barbuda, Dominica, Grenada, and Saint Lucia defined and submitted to legislators for approval

- The project will create multiparty legislative conservation caucuses of legislators from Antigua and Barbuda, Dominica, Grenada, and Saint Lucia. Country selection was based on consultations carried out during the project preparation phase with policy, technical, private-sector and other stakeholders, who affirmed strong national stakeholder interest in the project and willingness to embrace this innovative approach, as well as recognition of the gaps in political will and capacity to address these gaps in these countries. The caucuses will provide a forum for legislators to identify conservation priorities, become educated on topics related to these priorities, share ideas, seek consensus, and develop strategies, policies, legislation, and/or regulations to address prioritized conservation challenges. Caucus activities will be supported by key private sector and non-governmental partners, who will provide education, expertise, and resources. Activities in these targeted countries will build upon relationships begun during the project preparation period and will include:

- Identification of potential caucus members with attention to gender equity ;

- Dissemination of information about CCN and operational models of existing caucuses worldwide to potential caucus members, along with invitations to participate in recruitment activities and join the caucuses;

- Recruitment of initial caucus members via national outreach activities;

- Continuous engagement of caucus members in their contributions to national conservation agendas through a variety of mechanisms including verbal and electronic communication, in-person meetings with CCN staff, briefings and other engagement with public-private stakeholders

- Tracking of caucus membership numbers and representation throughout the course of the project by means of gender-disaggregated caucus rosters.

Once these steps have been completed and legislative conservation caucuses established, the architecture will be in place to enable the completion of Outputs 1.1.2 through 1.2.3, described below, including development of strategic partnerships, prioritization of conservation challenges, education on topics related to these priorities, collaboration & consensus building, and development of new or enhanced policies, legislation, and/or regulations to address prioritized conservation challenges.

- Extra attention will be given to ensure that women have high levels of representation in legislative conservation caucuses, especially in the leadership of caucuses. According to a recent UN report (2015,)  CARICOM countries have a total of 163 senators, 36 of whom are women (22.1%); and a total of 539 lower house parliamentarians, 76 of whom are women (14.8%). All countries besides Grenada and Guyana fall below the 30% women’s representation to which they have committed; caucuses are an important vehicle facilitating the political representation of women, and though the international conservation caucus would not be inherently focused on gender issues, it would provide an important channel to support women’s livelihoods and agency over environmental issues. Thus far, six female representatives have already been identified as potential stakeholders given their involvement or experience in environmental, fisheries, agricultural, tourism, or otherwise related ministries.  The aim is that each caucus would have one female co-chair to support women’s leadership in conservation issues.

1.1.2  A regional secretariat to support the legislative conservation caucuses

The project will create a regional secretariat to be based in one of the four countries to support all four national caucuses. As the parliaments in the four target countries are quite small, the caucuses are anticipated to be relatively small compared to other conservation caucuses CCN has supported in other parts of the globe. Having four local project (staff) members; one for each caucus, would be an excessive and costly investment of training time, salaries, etc. when the job of the secretariat would not constitute a full-time position in each individual country. Therefore, a regionally-based individual project team member has been deemed to be a sounder investment for the project, considering the proximity of the islands and the common functioning of parliamentary legislation power across the four nations. Internationally based staff assigned to the project will engage regularly with caucus members and stakeholders throughout the project.

- Activities will include:

- Establishment of the secretariat office;

- Incorporation/registration of the secretariat with local host government, as required;

- Hiring of local staff to support the caucuses under the supervision of CCN’s U.S.-based staff.

- Engagement with local staff to develop private-sector funding, partnerships, and infrastructure from connected stakeholders that will enable the secretariat to become self-sustaining by the end of this project. Caucus work beyond the scope of the project would potentially be funded through a variety of mechanisms including general funding provided by partnerships begun during the project.

1.1.3	Strategic partnerships with key private-sector and non-governmental partners, to support the activities of the caucuses submitted to national authorities for approval

- The project will also build stakeholder communities within the civil society and corporate sectors. Stakeholders will be identified based on interest or investment in natural resources and biodiversity of the islands, to focus on tourism and hotels associations, but also extend to corporations and civil society organizations. Activities will include:

- Identification of key local stakeholders for engagement;

- Arrangement of stakeholder meetings to discuss the legislative conservation caucuses and how they can become involved.  This includes attending project activities such as educational briefings and workshops, sharing expertise with caucus members through direct participation in project activities, engaging with other partners to exchange knowledge and expertise, providing financial and potentially other resources to support caucus activities among others.

- Inclusion of stakeholders in legislative conservation caucus events as participants in forums, expert panelists in briefings, and guides or participants in field visits.

1.2.1	Portfolio of conservation priorities created with the legislative conservation caucus

- The project team will consult with legislative conservation caucus members and other policy leaders within each country to identify, assess, and prioritize current conservation challenges in order to lay the groundwork for activities under Output 1.2.3, described below.

1.2.2	Legislative conservation caucus members are exposed to expertise and advice from conservation stakeholders through workshops, dialogues, briefings, and field visits

- The project will conduct programs and events to expose legislative members to expertise and advice from conservation stakeholders so that policymakers are empowered to address the priorities identified in Output 1.2.1. Based on an analysis of campaign platforms, party manifestos, and speeches, the issues that seem to be most important to legislators in the region include reducing vulnerabilities of communities to climate change and associated extreme weather events through strengthening resilience of the natural environment, and development of sustainable tourism and agriculture that also maximizes economic benefits.  This output will include the following activities:

- Creation of opportunities for legislative members to take stock of the opportunities and needs in their countries’ conservation systems and policies by means of workshops, dialogues, briefings, and field visits;

- Development of informational briefings (issue oriented, nonpartisan) in consultation with CCN corporate and NGO partners engaged in relevant activities;

- Hosting of briefings showcasing biodiversity conservation issues, projects, cutting-edge research, and/or best practices;

- Completion of follow-up activities and dissemination of program outputs electronically to broaden the reach of the programs.

1.2.3	New legislation, policies, guidance and support as necessary provided on demand to support requests by Members

- Building upon momentum from Outputs 1.2.1 and 1.2.2, this project will provide technical expertise, through working sessions, educational briefings, and/or mentorship exchanges, to help legislators address identified needs. Activities will include:

- Assistance provided to legislative conservation caucus members in the development of legislative/policy goals as requested;

- In collaboration with partners, delivery of expertise and understanding to caucus leaders, as requested, to assist them in the development of language in drafting of new legislation, policies, etc.;

- Engagement of private-sector and non-governmental stakeholders to encourage their political support for proposed new legislation/ amendments/regulations;

- Provision of support to caucus leadership by providing educational materials to legislative conservation caucuses relating to the issues;

- Provision of educational materials to the executive relating to the issues addressed by the legislation and the need in order to ensure buy-in by the Executive for approval of the new policy/legislation/regulation;

- Dissemination of updates on this process to a wide network of legislators and others around the world to educate and inspire other legislators to take similar actions.

Component 2. Capacity building (through technical support of the International Conservation Corps program) to support the management of protected areas, marine protected areas, and marine management areas

This component will build the capacity needed to support the management of Protected Areas through the provision of technical support by International Conservation Corps experts. Building capacity in small island developing states toward long-term sustainability in management of protected areas must be built within a broad-based approach that engages stakeholders beyond the usual government agencies typically charged with natural resource management, hence the approach adopted in this project geared at enhancing parliamentary influence and engagement.  This is extended to private sector engagement to further build collective implementation capacity.   The project intends to rely on, and augment existing in-country capacity building efforts with already mainstreamed initiatives and relevant projects.  This component will include training workshops for staff and stakeholders in association with the development of the protected area management plans.

Given the predisposition of Caribbean small island developing states to the ravages posed by natural disasters, most notably hurricanes, particularly in light of the recent passage of destructive storms in the participating countries, provisions for disaster resilience-building will be taken into consideration in the management plans.  These management (and business) plans will include special contingency plans that incorporate business continuity considerations in disaster aftermath, data and archival back-up and remote storage, asset rehabilitation and recovery among others.  The influence of the caucuses will be levered to address the environmental consequences of natural disasters and continue moving towards the overall objective of promoting biodiversity conservation in the face of climate change in the targeted countries of the Eastern Caribbean.

- In each of the four countries, government officials have expressed interest in obtaining support for achieving the objectives of protected areas. Most of the countries have some degree of legislation or management pertaining to the protected areas, but with significant gaps in authority designation, legal frameworks, enforcement, and budgeting.

- The International Conservation Corps consists of volunteer experts in the management of natural resources, and is therefore uniquely positioned to identify the areas where PA goals are thwarted by management gaps. Through field missions to each site during which the legislative conservation caucus members will meet with stakeholders that live and work firsthand in the protected areas, the International Conservation Corps will be able to identify and quantify the effect of these management gaps. They will then serve as advisors to standardize and implement the necessary changes to improve the management of natural resources in these protected areas.

- The major outcome of this component will be the formalized versions of these changes and subsequent implementation. The focus areas for each country vary depending on their current status and needs; in Antigua and Barbuda’s Codrington Lagoon National Park, an implementation plan will be developed from the existing management plan and focused on bridging gaps in the monitoring and enforcement of the current 2009-2019 management plan. In Dominica, a site-level business plan will be implemented to complement existing biophysical, management, and livelihood plans as a way to increase the financial independence and sustainability of Cabrits National Park. In Grenada, a co-management plan will be prepared and initiated between a third-party coalition stakeholder group and the Fisheries Division to improve the preservation of resources in Grand Anse MPA.  In Saint Lucia, the interim management plan for the Iyanola Region being drafted under the ongoing GEF-funded project “Iyanola - Natural resource management of the NE Coast” will be built upon to create a formal management plan for the proposed National Park with the partnership of International Conservation Corps volunteer experts.

Outcome: The planned outcome for Component 2 is:

Outcome 2.1 Improved biodiversity conservation in protected areas through better management of PAs, MMAs, and MPAs, and other enhancements such as signage plans, community engagement practices, and co-management agreements, based on best appropriate practices and legal structures and enforcement.

Outputs: Planned outputs include:

2.1.1   	An Implementation plan to facilitate and improve upon the 2009-2019 management plan in Barbuda’s Codrington Lagoon National Park developed and submitted for approval.

- The International Conservation Corps team will work toward developing an implementation plan for the Codrington Lagoon National Park in Barbuda for the 2019-2029 period based on the 2009-2019 management plan, through stakeholder consultations. In the recent aftermath of Hurricanes Irma and Jose (of the 2017 hurricane season) information on the health of the reefs, mangroves, and frigatebird colonies in the park remains unclear.  An initial mission to the island will allow the International Conservation Corps Team to meet with stakeholders ranging from Codrington residents to active nonprofits, to tourist operations and representatives from the Barbuda Council and Stakeholder Committee to assess the current situation and determine the effectiveness of the existing management plan.

Subsequent missions will involve providing advice and guidance to the Barbuda Council in facilitating the implementation of the 2009 - 2019 management plan. The focus will be addressing current shortcomings in monitoring and enforcement of the management plan, and drafting a solutions-based plan to bridge the gaps. Based on consultations with Park management, the current management plan covers key strategies and responsible entities for the area’s effective management, but lacks clear directives to facilitate implementation. Once these gaps are filled, ICC members will not just produce a formalized plan for continued use, but also provide technical capacity training for staff and Park managers. The plan will have a financing component for the sustainability of its provisions, to include a budget decided on in stakeholder meetings with the Department of Environment. The project will ensure that necessary safeguards are put in place for maintaining traditional access rights to the protected area as part of the implementation plan.  Activities will include:

- Field visits to collect baseline information during which International Conservation Corps will meet with stakeholders, including tourist operators, fishermen, Codrington Village residents, staff, and Barbuda Council members.  Interview procedures will identify current shortcomings in management plan, current implementation status, and needs for technical capacity training

- Development of an implementation plan (for the management plan) through meetings with the National Parks Authority, the Barbuda Council, and the Department of Environment, during which any amendments to management plan would be decided. Subsequent workshops will develop implementation plan in a way that supports goals of management plan, including provisions for streamlining of authority and maintaining traditional access rights

- Provision of guidance to Park management on implementation of the plan via workshops with Park employees, briefings for Park authorities, and the implementation of training workshops for Park staff based on needs identified in Phase 1

2.1.2   	A business plan in accordance with biophysical plan, management plan, & livelihood plan to increase self-sustainability of Cabrits National Park in Dominica developed and submitted for approval

- Cabrits National Park in Dominica has a management plan, a biophysical plan, and a livelihood plan but lacks a comprehensive business plan to effectively manage resource allocation in the Park. Funding for Protected Areas in Dominica either comes from the government treasury or self-generated funds; however, there are no historical records or financial data on trends or sources of funding. Despite the large number of visiting boats that dock in Douglas and Toucarie Bays, there is no comprehensive system of collecting fees for the use of the natural resources and any self-generated funds are reportedly extremely low. Treasury-allocated funding is also reportedly low, allowing for little more than paying the salaries of the existing seven staff members. Members of the International Conservation Corps team will meet with stakeholders in the initial phase of this component and gather baseline information regarding sources of funding and general allocation of resources, and develop a business plan for the most sustainable allocation of resources.

- ICC members will assist Park management officials in the development of a comprehensive business plan, to include a marketing study and marketing plan along with a financial plan, in accordance with the biophysical, management, and livelihood plans. The major output will be a formalized system of recording financial information, identification of business opportunities and revenue streams, marketing and pro-forma projections for the Park, and a budget of allocations with a timeline for regular updating. The goal is for the business plan, when implemented, to help put the Park on a more stable financial footing through identification of current and potential revenue sources and how funding is being, and may be allocated to support operations.  This will further inform the creation of a strategy to reduce dependence on outside funding sources, while independently maintaining the Park’s programs and biodiversity. Part of the budget will be earmarked for research within the National Park to increase knowledge of its biodiversity and inform management of any changes that require timely action. Activities will include:

- Initial meeting with relevant stakeholders, including park management officials, hotel and tourism associations in order to identify current modes and amounts of funding, quantify expenditures and projected costs, and prioritize operational management areas that would benefit from increased allocation of resources

- Development of a business plan that includes a market study, market plan, and financial plan.  Specifically this will entail:

  - Identification of revenue streams including venue rental, concessions, events and recreation fees from mooring and other visitor services in keeping with the purpose of the Park,  establishment of a system of financial record-keeping, and publishing of a budget of allocations with timeline for updating

- Facilitation of implementation with park employees by holding briefings on financial record keeping and workshops on enforcement of rent collection.

2.1.3   	A co-management agreement between Fisheries Division and third-party coalition of managers to improve legal frameworks on natural resource management in the Grand Anse MPA of Grenada drafted and submitted to the competent authorities for signature

- While the Grand Anse MPA has a management plan, there is no implementation or effective enforcement, due to a complete lack of funding and staff to execute the mandate in the plan.  Further, the spatial boundaries of the MPA remain undefined to stakeholders. The Government of Grenada has voiced interest in the establishment of a co-management agreement between the designated MPA Authority (the Fisheries Department) and a third party manager, comprised of a coalition of vested stakeholders, to strengthen management of the MPA through improved implementation of the management plan. While the current legislation that would provide statutory allowance for the Fisheries Minister to delegate management authority to a third party is currently under review, such delegation is already being practiced in other instances; an example being the Gouyave Marine Protected Area, where a co-management agreement between the Fishers Association and the Fisheries Division is in effect. In the case of the Grand Anse MPA, CCN will facilitate the initiation of an appropriate co-management agreement by convening the relevant stakeholders, facilitating the development of an appropriate co-management framework and formulating the co-managing entity. This co-managing entity would perform identified functions in keeping with the area’s management plan, and also would serve as a representative coalition of stakeholders’ interests in the area.

- In this role, the International Conservation Corps will conduct on-site dialogues with the Fisheries Division and relevant Grand Anse MPA stakeholders to discuss potential co-management options.  The International Conservation Corps will support and facilitate necessary stakeholder discussions toward the emergence of an effective coalition group of stakeholders willing to act as third party management for the MPA. Activities will include:

- Development of a co-management policy and agreement based on stakeholder consensus;

- Drafting a co-management policy and agreement drawing on models and templates of other such agreements in the country, the region and perhaps from the global level;

- Foster establishment of a group of stakeholders to serve as a third-party co-management coalition by working with the Fisheries Division and multiple MPA stakeholders, to include the fishers association, hotel association, and dive association;

- If the co-management agreement is approved within the project timeline, the International Conservation Corps will assist in monitoring and evaluating its initial implementation.

2.1.4   	A Protected Areas management plan for the proposed Iyanola National Park in Saint Lucia that builds upon the interim regional land use management plan drafted by a consultancy group for an ongoing GEF project in the region drafted and submitted for approval

- The Iyanola National Park has yet to be designated, but the proposed boundaries contain several proposed Protected Areas and landscapes, including Grande Anse National Park, Esperance Protected Landscape, and Fond D’Or Protected Landscape. The government of Saint Lucia has expressed an interest in receiving additional support in developing a management plan for the National Park to supplement the interim management plan for the entire region that is currently under development. This is in keeping with the 2009 Protected Areas Systems Plan, the goal of which is to guide the use, management, development and administration of land resources in Saint Lucia in order to optimize the contribution of land to sustainable development. At the PPG Validation Workshop, consultants of the ongoing GEF Iyanola Project explained the broad scope of land use plans being developed for the Iyanola region and requested the support of International Conservation Corps experts in partnering with relevant authorities and stakeholders to develop a Protected Areas management plan for Iyanola National Park from the interim (wider area) regional management plan. This effort is expected to commence in the second year of the grant, at which time the ongoing GEF project, which designates the area to be considered for the proposed National Park, will be complete. While the Park has not yet been designated, the formalization of a management plan could spur policy-makers to move forward with the designation of the Park, or at least be implemented on an agency-by-agency basis for its various provisions.

- The International Conservation Corps experts will meet with the National Conservation Authority, Forestry and Fisheries Ministries and consultants working on the interim management plan for the Iyanola Region. Based on the interim regional management plan and designation of area described in the ongoing GEF Iyanola project, the International Conservation Corps volunteers will assist Saint Lucian authorities in drafting and formalizing a management plan for Iyanola National Park which builds upon existing frameworks, such as the Land Use Plan, Ecosystems Services Valuation plan, biodiversity livelihoods and needs assessment, and interim regional management plan. The major output will be the aforementioned management plan, as well as subsequent briefings and workshops to enhance its implementation. The management plan will include a budget section to provide for the Park’s continued maintenance and the plan’s sustained implementation. Activities will include:

- In-field meetings and consultations between International Conservation Corps members and stakeholders in the vicinity of the proposed National Park will be held to allow for continued information collection, needs analysis, stakeholder mapping and review of the interim management plan in the context of how it will inform the development of the National Park management plan. Stakeholders, particularly the local communities, landowners, consultants, and government agencies, will provide input and feedback on the existing interim plan.

- Workshops will be held with stakeholders and relevant ministries to draft the plan, to include contracting to a mapping company for maps of the National Park.

## 3.4	Intervention Logic and Key Assumptions

- Biodiversity protection at many of the parks and PAs in the Caribbean region remains challenging, as do public access and sustainable benefits to local people. The urgency of other immediate human needs has led countries to consistently under-invest in conservation. These tendencies have led to substantial problems of environmental degradation and loss of biodiversity, and of a broad deterioration in the natural goods sustainably provided to human use. To the extent that active, managed conservation is carried out, there is a tendency to depend to a high degree upon international support. In addition, management and other plans for PAs, MPAs, and MMAs are often nonexistent; where such plans do exist in the region, effective implementation is often lacking.

- The proposed project will address several of the currently missing enabling conditions to address these biodiversity challenges:

- Lack of awareness and prioritization at the decision-making level;

- Inadequate national policy and legal frameworks for natural resource access and utilization;

- Limited collaboration among Caribbean countries;

- Weak technical capacity and incentives for sustainable resource utilization;

- Insufficient funding for management of PAs, MPAs, and MMAs;

- Inadequate or lacking management and other plans for PAs, MPAs, and MMAs.

- The legislative conservation caucus model, which has been successfully implemented, with GEF support, in developing countries such as Kenya, Colombia, etc., offers an innovative approach that goes a step beyond current approaches. The enabling conditions to be established by this intervention will facilitate and support further actions such as strategic planning and capacity enhancement within policymaking bodies and national agencies of target countries through cross-sectoral collaboration. They will also support greater collaboration among Eastern Caribbean countries. Project efforts can further provide impetus for preparation of protected area management plans for other PAs, MPAs, and MMAs in the target nations, and commitment for corresponding budgets for their implementation. This intervention will push for the strengthening of cooperation within and between national agencies and relevant international organizations, such as other caucus groups, and to mobilize political support for environmental law enhancement, harmonization, and streamlining at national and regional levels.

- The following assumptions are part of the intervention logic of the project:

- The legislative conservation caucus approach will be appropriately tailored and applied, with correct context, to Caribbean SIDS;

- The value of the legislative conservation caucus approach will be recognized and promoted by policymakers, with political buy-in and participation;

- Key private-sector stakeholders will recognize the value of the approach and are willing to support the development of project outputs;

- Stakeholders will generally be willing to participate in project activities;

- PA management goals for the target locations are well articulated so that project interventions are appropriately crafted and delivered;

- Partners and collaborators are responsive in project implementation;

- Project resources are deployed in an efficient manner.

## 3.5	Risk Analysis and Risk Management Measures

- The following table summarizes the information about possible risks and associated risk mitigation strategies that have been identified for the project.

Table 5: Risk Analysis and Risk Management

| Risk | Level | Mitigation Strategy |
| --- | --- | --- |
| Lack of buy-in from legislators | M | Legislative Conservation Caucus leaders will be encouraged and supported through GEF-funded activities to develop a conservation agenda broader than that proposed by the project, to reflect national and regional concerns and priorities. The strategy hinges on translating and appropriately adapting successful caucus experiences gained in developing countries. For example, the Colombian caucus played an instrumental role in passing the Minamata convention in 2013; Peru’s caucus recently pushed legislation to ban single-use plastic bags; and Kenya’s caucus was responsible for critical amendments that were made to existing legislation in Wildlife and Conservation Management Act of 2013. Legislators will be actively recruited and attracted to caucus activism by the nature of the events, especially field visits. Such visits have been shown to increase cooperation between caucus members, increase their awareness of biodiversity and other conservation issues, and increase the priority of conservation agendas in existing caucuses. |
| Inability of legislators to form legislative conservation caucus | M | In countries with less functional or very small legislatures, CCN will identify and engage with key leaders, heads of state, ministers, and other high-level policy makers who can commit to and enact appropriate legislation in concert with legislative conservation caucuses. The caucus mechanism and structure is highly flexible by nature, and adaptable to local circumstances and preferences. |
| Turnover in legislatures due to election cycles | M | Establish legislative conservation caucuses with the strength and numbers to ensure longevity across political election cycles. Participation “emeritus” of ex-legislators has been shown to be highly useful, so an electoral loss need not necessarily end the usefulness of a Member. |
| Drafted/proposed legislation is not passed into law | H | Recognizing possible challenges in gaining the full legislative and/or policy transformation during the course of the project, measures will be sought to ensure that robust political commitments are realized and foundational legal, regulatory and policy proposals are made with full stakeholder consultation under the aegis of the conservation caucuses as a basis to enhance sustainability of the investments of the project. Project activities seek to tap into the collective expertise of CCN’s extensive partnerships to inform and justify needed policy changes, drawing on experiences gained in other developing countries. Caucus-building and/or executive-level engagement activities are expected to create the necessary political will, momentum, and leadership for change toward adoption of transformative legislation and policy instruments. |
| Legal land tenure disputes | M | In two of the four countries, land rights and land tenure disputes have the potential to delay progress in Component 2 of the project. In Barbuda, on-going land tenure issues in terms of ownership and institutional authority could present challenges in land management-related aspects in the development of the management plan for Codrington Lagoon National Park. This issue is connected to the land tenure system that has been historically in place in Barbuda where the lands are communally owned by the families inhabiting the island. In the aftermath of Hurricane Irma (2017) the issue of regularization of tenure was brought to the fore, in the context of encouraging investments to rebuild the island which included the possibility of external investments. There was some apprehension among residents that a new land management regime would disrupt present and future land entitlements and could impinge on the management proposal for lands associated with the national park. It should be underscored that the project does not seek to create a new management regime that will cause adjustment to traditional access rights or land tenure arrangements; rather, it will develop an implementation plan that will operationalize the existing management plan that has been in place since 2009, which local residents had accepted as it was a consultative process. Additionally, the bulk of the lands associated with the national park are wetlands hence this should not be a significant issue as concerns the geographic integrity of the park. To further mitigate risks that may include access and use rights, the International Conservation Corps team will consult extensively with the Barbuda Council, as well as Barbudan civil society groups to avoid potential rights infringement through the development of the implementation plan. Moreover, the Conservation Caucus will encourage members from both the Barbuda Council as well as the Parliament to join the caucus; this approach has received support during consultations in the PPG validation workshops. In Saint Lucia, private ownership of the large estates within the proposed Iyanola National Park and challenges to solicit owners’ engagement has averted the designation of the National Park in the past; this has the potential to delay or challenge the process of developing a Management Plan for the National Park under Component 2. The project will therefore closely engage with the land owners to solicit their buy-in and foster appropriate co-management arrangements within the scope of the management plan. This will enhance the ability of individual government agencies to implement their jurisdictional responsibilities under the plan, even in the event where non-designation status is maintained. Moreover, in conjunction with the creation of a conservation caucus and enhanced platforms of engagement for legislators on conservation issues, the project as a whole is anticipated to assist the National Park’s eventual designation. The region-level land use plan being developed under the ongoing GEF Iyanola project will be an important input to this project, and the gains realized with negotiations with land owners under that project are expected to positively contribute to moving the agenda forward. |
| Caucuses disintegrate after conclusion of the project | L | This risk is designated as “Low” because of precedent examples of self-sustaining caucuses, the natural structure of governance, and the activities of the regional secretariat. There have been other conservation caucuses supported by CCN (such as in Botswana and Namibia, for example) that have continued their activities and commitments after the conclusion of their project and wind-down of continued funding for specific activities. However, engagement by CCN staff still continues. This is supported by natural governance structures of regular turnover and therefore consistent recruitment and renewed engagement that self-propels under the leadership of a few in Parliament. Fundraising and seeking diversified supplemental funding during and after the project’s conclusion will be one task for the local CCN staff that will also help secure continuation of the caucus work after the conclusion of the project. |
| Conflict and variance in opinion by way of cultural norms and expectations | L | There is a potential for conflict and variance in opinion by way of cultural norms and expectations. The risk is deemed to be Low due to leadership of caucus members in setting agendas, organizing role of the regional secretariat, and level of experience of involved staff at CCN and the International Conservation Corps. |
| Natural Disasters (mainly hurricane impact) | M | Given that Caribbean small island developing states (SIDS) are predisposed to the risk of natural disasters, especially hurricanes and have the potential to disrupt project implementation, mitigation measures that will be put in place. These measures will include an implementation contingency plan that will be formulated as part of the inception activities at project start-up. This will be mainly in the form of making allowances for rephasing activities depending on the severity of an event where stakeholders may be otherwise engaged in recovery efforts where attention may be diverted from project implementation actions. |

## Consistency with National Priorities or Plans

- The target audience of key decision makers at the national level will ensure that the project approach is consistent with national priorities and plans. Target countries will specifically be supported in reviewing their country NBSAPs to inform their participation in project activities and in support of CBD and other multilateral environmental agreements and relevant conventions.

Antigua and Barbuda

- Antigua and Barbuda ratified the Convention on Biological Diversity in April 1993 and drafted its initial NBSAP for implementation in 2011. It has created an updated version to reflect emerging biodiversity concerns and the Aichi targets that went into effect in 2014 (NBSAP). While parks have been designated, the NBSAP notes the need to, “establish the necessary policy and legal framework to facilitate the management and sustainable use and protection of the country’s biodiversity”. The proposed project will assist in this endeavor.  2017 Hurricane damage to Barbuda will be a factor.

- Under the NBSAP for Antigua and Barbuda, a great emphasis is placed upon capacity development, environmental monitoring, evaluation and institutional management and implementation as strategies in the protection of the nation’s biodiversity. The report specifically names one of its main goals as, “the achievement of an integrated, coordinated and inter-sectoral approach to biodiversity policy planning and management.” This aligns perfectly with the goals and strategies of Component 1 of this project, which are to enhance political will through the foundation of legislative conservation caucuses in parliament, enhanced by the involvement of stakeholders and informational activities hosted by CCN.  Moreover, the Component 2 outcome of a Codrington Lagoon National Park Management Plan further supports Antigua and Barbuda’s capacity-building by improving institutional management of the National Park, in keeping with its national priorities.

- The 2015-2020 National Action Plan (NAP) for Antigua and Barbuda emphasizes land degradation, desertification, and drought as national priorities for management in Antigua and Barbuda. Notably, it underscores the significance of Codrington Lagoon National Park within the report, stating that the reliance of more than 60% of Barbuda’s economy on the fishing industry “indicates the critical importance attached to the preservation of the vegetation and the coastline for Barbuda.” The goals of Component 2 support the preservation of this area and Antigua and Barbuda’s national priorities through guidance towards a management plan that will consider the significance of the coastline, especially the management of the National Park’s mangrove forests and the potential pollution and development from nearby Codrington Village.

Dominica

- On July 4th 1994, the Government of Dominica ratified the United Nations Convention on Biological Diversity.” In 2001, it demonstrated its commitment to biodiversity management with the preparation, approval, and submission to the CBD of its NBSAP. And in December 2014, it reevaluated the NBSAP to address new threats and to align biodiversity management with the Aichi targets. In addition, a number of pieces of legislation have been proposed, but are still waiting the approval including the Proposed Protected Area System Plan and Climate Change, Evolving Environment and Natural Resource Bill (NBSAP p.30). The NBSAP laments that “there is a number of weak, outdated, and sometimes overlapping pieces of legislation that affect the sustainability of biodiversity” (NBSAP p. 9). In addition, “the NGO community complains of exclusion from the decision-making process and limited access to financing and technical information” (NBSAP, p.26). Human capacity constraint also prohibits NGOs from capitalizing on decision making opportunities when they occur (NBSAP p.26). The NBSAP notes that even with environmental legislation and a land use plan, Dominica still faces the ongoing challenge of the lack of “human and financial resources to enforce legislation” (NBSAP). Damage from the 2017 hurricane will further complicate efforts.  The current project will provide a forum for discussion of these important issues, and will support the countries in sharing experiences and knowledge through south-south and north-south cooperation in order to find suitable options for addressing the problems faced.

- Dominica’s NAP confirms Dominica’s commitment to engaging public and private sectors to develop sustainably and advance the protected areas management system, and outlines the major threats and areas of improvement to protect the islands’ biodiversity. It specifically points out budget constraints, weak legislative frameworks in the absence of integrated development processes, and the conception that “biodiversity is not a big money earner” as threats to sustainability in the country. Both components of the proposed project address these threats; the legislative conservation caucus would increase integration in development, and input of stakeholders would help strengthen legislative frameworks for conservation by creating a platform for conservation policy dialogue. Additionally, the implementation of a successful business management plan for Cabrits National Park would help change the notion that biodiversity is not lucrative, as well as relieve some of the budget constraints in managing protected areas.

- Dominica’s 2001 -2005 NBSAP was not fully implemented, and the country did not reach its 2010 Biodiversity targets due primarily to financial, technical, and human limitations. The goals of the 2015-2020 NBSAP, therefore, are to develop national strategies, plans or programs for the conservation and sustainable use of biological diversity and integrate, as far as possible and where appropriate, the conservation and sustainable use of biological diversity into relevant sectoral or cross-sectoral plans, programs, and policies. One of its main strategies in doing so is to strengthen the effectiveness of the protected areas system, and it specifically mentions developing and implementing a protected area systems plan with allocated financial resources. Component 2 of the proposed project aligns perfectly by creating a business plan for a protected area that could inform policy on other protected areas in the country, as well.  In keeping with national strategies, this plan would involve the input of key stakeholders, and include provisions for integration with institutional, administrative and budgeting processes. Objective 4 of the NBSAP aims to share knowledge in direct development policy with the population on the importance of biodiversity to wealth; the project goals align with this by creating opportunities for political leaders to become informed and in turn help raise awareness among their constituents.

Grenada

- While Grenada does have some beneficial environmental legislation in place, the NBSAP notes the need to “review and update policy, legislative institutional and governance frameworks for biodiversity management” and notes that the legislative priorities include “national parks and protected areas, physical planning and development control, climate change, forestry and fisheries” (NBSAP p.25). In accordance with the Aichi targets, it also notes the need for, “integration, mainstreaming and linkages of biodiversity conservation and sustainable use established across all decision making levels” (Aichi Target 2, NBSAP p.23). Grenada prepared and submitted its first NBSAP in 2000 in light of the 2010 Global Biodiversity Strategy and revised its plan to account for emerging biodiversity issues for 2016-2020. The NBSAP laments the “lack of enforcement of relevant laws and regulations,” that is partially caused by a need for skilled human capital. Through the legislative conservation caucus, this project will provide the forum for discussion of important topics for the country, such as the need for enforcement of relevant laws, which is expected to result in support from the stakeholders and decision-makers in charge of this.

- Grenada’s 2017-2021 National Action Plan goals include improving management and conservation of protected areas and other key ecosystems areas, as well as building the institutional, professional, and technical capacity for integrated coastal zone management (PoAs 5 and 6). It specifically mentions the management and conservation of protected areas and other key ecosystems, protecting and sustainably managing 20% of Grenada’s marine, coastal, and terrestrial ecosystems by 2021, and establishing a Coastal Zone management unit by 2020. The proposed project in Grand Anse MPA directly supports these two objectives in both Components. Component 1 establishes a legislative conservation caucus in Grenada’s parliament, with the engagement of stakeholders at regular informational briefings and workshops, which will serve to strengthen the institutional capacity for coastal zone management through stakeholder engagement and policy. Component 2 introduces a co-management agreement to bolster the technical management of Grand Anse MPA, which according to the NAP has the greatest total land (206,100m2) and beach loss (54,500 m2) due to sea-level rise (SLR), making this an important target area. This component will improve technical capacity for integrated coastal zone management through the guidance and training of an experienced co-manager, in keeping with the objectives and strategies outlined in the NAP.

- Moreover, the proposed project parallels closely Grenada’s 2016-2020 NBSAP lessons learned and strategic priorities, which both emphasize the importance of political leadership and commitment to biodiversity, stakeholder involvement, and enhanced national capacity for sustainable use of resources, with priority placed upon a coastal zone management policy. This aligns perfectly with the goals and strategies of Component 1 of this project, which are to enhance political will through the foundation of a legislative conservation caucus in parliament, enhanced by the involvement of stakeholders and informational activities hosted by CCN.  Moreover, the Component 2 outcome of a co-management agreement for Grand Anse MPA further supports Grenada’s capacity-building by improving institutional management of the marine and coastal zone, in keeping with its national priorities.

Saint Lucia

- St. Lucia outlined the actions and policies necessary for successful resource management in the NBSAP, adopted in 2000. The plan recognizes the importance and far-reaching consequences of biodiversity. The plan outlined the vision for a collaborative and cross-sector approach to successful resource and biodiversity management stating that, “there is need for improved coordination of policies and activities relevant to, or impacting on, biological diversity, as many of the problems currently observed result from the fragmentation of policy instruments and from the absence of effective coordination among actors, and there is need to establish effective partnerships among governmental and non-governmental partners”.). The legislative conservation caucus will facilitate discussion of the issue of fragmented policy instruments and will support the country in identifying alternatives to solve this problem.

- One of the main objectives of Saint Lucia’s 2008-2018 NBSAP is improved institutional framework and coordinating mechanisms for biodiversity management supported by appropriate legislative and regulatory systems; moreover, it mentions the need for a greater value placed upon biodiversity by government in legislation. This aligns with the project proposal’s first component, which establishes a legislative conservation caucus to champion conservation policies, as well as holds activities to inform and strengthen that caucus. According to the report, to date no institutional arrangements have been supported by appropriate legislation to establish a coordinating mechanism for environmental management, and one strategy to do so is to implement a program approach to management that strengthens stakeholder input; the proposed project would hold various activities to create platforms for major stakeholders to discuss and inform policy at the national level, in keeping with this strategy.

- Another main strategy outlined in the report for consideration is use of an Integrated Development Planning (IDP) approach, since such an approach to biodiversity management would cut across sectors and agencies, and to establish a national biodiversity management authority to implement the NBSAP; this aligns with Component 2, which works with this entity to create an overall management plan for the East Coast National Park that takes into account the other individual management plans for protected areas within the park. This integration helps Saint Lucia reach its goal of integrated national management of biodiversity.

## 3.7	Incremental Cost Reasoning

Baseline scenario:

- The baseline scenario for this project is one where the threats to biodiversity in the participating countries are related to unsustainable use of resources (i.e., overfishing, sand mining), lack of updated legislation that can capture the actual challenges, expansion of the tourism sector decoupled from environmental aspects, pollution, deforestation, and lack of enforcement of existing regulations, amongst others. Participating PAs, MPAs, and MMAs lack sufficient management and/or other plans to effectively meet the biodiversity challenges with which they are faced.

- In the absence of GEF support, the countries will continue to face the same challenges, as they will continue to lack updated legislation and enforcement. Additionally, PAs, MPAs, and MMAs will not receive on-the-ground technical support of volunteer international parks experts and will continue to lack adequate management, financial, and other plans. They will therefore continue to be unable to address and overcome their conservation challenges. By addressing conservation governance and on-the-ground management challenges, the proposed initiative will complement previous and ongoing interventions in biodiversity conservation and valuation.

The alternative scenario:

- This project´s contribution is to bring about the creation and strengthening of active legislative conservation caucuses including respected and powerful legislative Members, willing to raise the profile of conservation as a national issue through engagement with the respective Executive Branches, private partners, and the general public. Those activities will progressively increase support for protection of biodiversity and natural resources, while also improving the efficiency by which available funds serve their conservation goals.

- This project will provide a more informed view within the governance structure of how to sustainably manage the human-biodiversity interface, through a strengthened neutral arena for dialogue for conservation issues that transcend political barriers.  By targeting specific sites of globally significant biodiversity, the proposed project will deliver multiple conservation outcomes, and through the work of the legislative conservation caucuses it will mainstream biodiversity and sustainable development with positive economic benefits through enhanced awareness, technical support, and strengthening of links between legislators and operative branches in the respective countries. It is expected that these efforts will also eventually contribute to a broader understanding and integration of biodiversity and ecosystem services valuation into policy making by integrating expertise from the public-private partnerships.  The contribution of the proposed project is to influence policy and fiscal reforms through this lens, with tangible reforms through informed and effected policy instruments and lasting awareness and capacity strengthening created through the momentum of caucus building.

- The project will also contribute directly to the conservation of biodiversity in PAs, MPAs, and MMAs by providing expertise necessary for the development of new and/or strengthened management and other plans. This will result in positive economic benefits generated through increased tourism and greater balance between the needs of the ecosystems and the services they provide.

## 3.8	Sustainability

- In CCN’s previous projects to establish legislative conservation caucuses, CCN expressed its firm commitment to continue its work in supporting existing caucuses and helping to establish new ones and has succeeded in leveraging additional financial support to sustain the most active caucuses, notably Colombia and Kenya. The independent evaluation of the first project noted as “Likely” the sustainability of the established caucuses. CCN is committed to continuing this work with or without additional GEF funding. CCN has been successful in mobilizing financial support from the private sector; these funds will be used to support core costs and an agenda of educational programs. Furthermore, governments are providing in-kind co-financing by their participation across all the components of previous caucus efforts. Previously, in some caucuses, there was a high turnover after national elections, for example in Kenya. However, the Kenya model demonstrated a situation where the functions and benefits of a strong secretariat are evident: to cultivate strong and deep caucus leadership, work with caucus leaders to plan for succession, conduct ongoing recruitment of new members, and provide continuity in programming. The Kenyan caucus continues to be successful in mobilizing additional financing from the private sector and grant-making organizations.

- As existing legislative conservation caucuses are strengthened numerically and representationally, the likelihood of sustainability of these caucuses continues to increase as well. As a new paradigm for conservation, the caucuses have forged new forms of cooperation, building multi-partisan collaboration around issues of conservation and natural resource management.  The replicability of the model depends on the following factors:

- Interest of legislators and relative strength of the legislature;

- Receptivity of the executive branch to the caucuses and willingness to support the caucuses;

- Potential for mobilizing all relevant stakeholders, especially the stakeholder groups that are represented by the key legislators involved;

- Potential for secretariat support on the ground;

- Capacity for CCN to engage at higher political levels;

- Potential to transform the caucuses into a platform for collaboration and learning;

- Opportunity on the ground to cultivate interest among more individuals from a wider variety of committees and sectors;

- Opportunity to work with influential parliamentarians and to seek their buy-in first.

- The independent evaluation found that the legislative conservation caucus model has the potential to catalyze replication, considering the interest of legislators, the receptivity of the executive branch, the engagement of civil society, and the impact that has been generated thus far by successful caucuses.  CCN has made considerable efforts to engage both the large conservation NGOs and representatives from the private sector. They have been engaged in the CCN brain trust and have been actively involved with many of the caucuses.

- Based on CCN’s stakeholder surveys and observations during the previous projects, we know that new legislative conservation caucuses have several requirements to become sustainable financially and institutionally:

- Support must be built from a large stakeholder group including from the corporate, government, and civil society sectors. This approach has two benefits for sustainability: it builds stakeholder support and interest that helps keep legislators engaged and accountable, and it creates a base of financial support for a secretariat for the legislative conservation caucus. In each country, the project will cultivate a constituent/stakeholder group as a key part of the caucus-building process.

- A coordinating body (“secretariat”) is needed to provide the appropriate level of day-to-day support and overall, long-term coordination and engagement with legislative conservation caucus leadership and partners. In Colombia and Kenya, for example, CCN has created affiliate foundations with local staff.

- A sustainability assessment in Kenya specifically indicated the following measures as advisable to make legislative conservation caucuses more effective and sustainable:

- put in place rules for operations of the caucus such as those for “friendship groups”;

- create awareness among members from different parties;

- have a reliable and reputable local CCN contact in country; and

- use and follow institutional structures and internal procedures during establishment of the caucus to ensure internal support, ease of approval, and sustainability.

- To assist legislative conservation caucuses in continuing or expanding activities in the future, respondents cited the need to: establish collaborative links within the caucus, continue to build capacity, have a local base, have the private sector participate or establish local partnerships, and establish other links not necessary with the parliamentary - private sector.

- In sum, the resources and structures that would best benefit a legislative conservation caucus in order to ensure future sustainability included: financial resources; an established secretariat; capacity building; private-sector partnership; and establishment of rules and procedures governing the caucus in place in the assembly.

- Beyond the formation of legislative conservation caucuses, this project will also ensure sustainability through the long-term effects of new/amended laws, policies, and regulations as well as overall improved knowledge and understanding of legislators regarding the negative impacts of biodiversity loss. In addition, linkages between this project and numerous projects of partner organizations will facilitate the development of relationships and networks that will lead to continued sharing of knowledge and best practices beyond the term of this project. For example, the sharing of information regarding key stakeholders in the Grand Anse MPA with the Ridge to Reef project will enhance the prospects of organizing a co-management entity for the MPA. In Saint Lucia, coordination with consultants working on the regional interim management plan for the Iyanola region will support and strengthen International Conservation Corps efforts to finalize a management plan for Iyanola National Park. International Conservation Corps experience in the region will also support its efforts in Component 2 in each of the four countries.

- This project will also build cooperation between nations. Agreements/commitments resulting from this project, and relationships built among nations, will bring about changes that will endure beyond the scope of this project. Through communication amongst and between legislative conservation caucuses established through the project, the members will have the opportunity to share information, challenges, and best practices.

- The activities of the International Conservation Corps in executing this project will generate new and improved management and other plans for PAs, MPAs, and MMAs. These plans will continue to benefit these areas long after the completion of the project and have the potential to serve as models for other PAs, MPAs, and/or MMAs.

## 3.9	Replication

- Replication is a key consideration in CCN projects, and the design of this project promotes replication. The target countries in this project will benefit from the creation of legislative conservation caucuses built following the successful model of the U.S. Congressional International Conservation Caucus and a number of other caucuses around the globe. This model, which provides the infrastructure for effective policymaking and creation of political will, may be replicated in other countries around the world following the same steps utilized in this process. The policies enacted under this project may also serve as models for other nations that wish to prioritize biodiversity within their own policy agendas, specifically in other countries in the Caribbean that may face similar challenges to these four Eastern Caribbean countries.

- Resources made available to target countries within this project will also gain recognition as resources that may be utilized by other interested nations. Through regional workshops and conferences, nations beyond the four target nations of this project may also have the opportunity to take part in educational programs, build networks and relationships, and be encouraged/motivated by the project.  Stakeholders who participate in program activities will also carry back their newly gained capacity, together with tools and methodologies made available to them through the CCN.  Management and other plans for PAs, MPAs, and MMAs developed as part of this project may also serve as models for replication nationally, regionally, and internationally.

## 3.10	Public Awareness, Communications and Mainstreaming Strategy

- To grow awareness and engender replication efforts, CCN will broadly disseminate results of the project’s approach together with the tools and materials developed for its execution.  Materials and modules on particular themes can be made available for key groups, including the conservation community. Through CCN’s website, interested parties will be able to access materials and information about the project. For example, all CCN educational briefings and programs will be captured electronically; videos will be made available online through the CCN website, and information about these programs, including how to access video footage, will be disseminated to CCN’s extensive network of email subscribers, including policymakers of CCN member nations The project team will be complemented by CCN communications experts who have rich experience in awareness building through networks to maximize exposure of project products. CCN’s communications experts will electronically communicate project updates on a regular basis to its extensive network of email subscribers. CCN will work broadly with the press and media channels at large.

The project will ensure that during its SC meetings, there is a space for discussion particularly on lessons learned, best practices and communication strategies. Communication efforts will be assisted by the fact that many project activities are already planned to use virtual technologies from the Internet. The project´s communication approach will also be sensitive to gender and socio-cultural issues, ensuring that all parties are well represented; this is expected to empower them to take actions for BD conservation based on their particular skills and needs.

## 3.11	Environmental and Social Safeguards

- The project is expected to create positive environmental and social impacts in the target countries and surrounding region (in terms of biodiversity and habitat preservation, economic development, increased tourism revenues, etc.).  In accordance with UNEP’s Policy on Environmental and Social Safeguards, safeguard measures are considered in the design and will be applied during the course of implementation.

- Furthermore, the project will ensure inclusiveness of both men and women in project formulation and implementation and will involve multi-racial and multi-ethnic stakeholder groups. The project itself is designed to be inclusive of all stakeholders, political parties, socio-economic groups, etc. in order to ensure that the effects of the project are far reaching and that project results are sustainable.

- Local communities (and where relevant, indigenous people thereof) will be greatly affected by the outcomes of this project in terms of improved economies, revenues, stability, and other factors; similarly, the cooperation and involvement of local communities is key to the success of this project. Because of the important role of communities within this project, CCN will ensure that community leaders have the opportunity and are encouraged to participate in project activities and engage with other stakeholders.

- The project will be consistent with UN Environment and GEF gender policies. Women will also play a key role in this project at many levels: parliamentary, stakeholder, etc. Some of the most prominent figures in existing conservation caucuses (co-chairs and Ministers) are, in fact, women, and CCN will be proactive to ensure their inclusion in all activities. It should be noted that gender considerations do not exclusively take into account issues related to women, but rather the dynamic of communities including men’s issues, as well as consideration of vulnerable groups.

- The project will generate gender data and input gender dimensions as concerns participation and empowerment, influence in shaping the legislative conservation caucuses, transforming benefit to local stakeholders, etc. Gender considerations will be taken into account in information/communication by formulating messages specifically tailored to female and male audiences. Disaggregated gendered impacts of increased income generation will be tracked as part of the M&E for the project. Additionally, the project management/steering committee will be gender balanced.

# Section 4: Institutional Framework and Implementation Arrangements

- UN Environment is acting as the GEF Implementing Agency.  CCN, as the Executing Agency, will provide overall management and oversight of the Project from its headquarters in Washington, DC.  A Project Steering Committee will be comprised of representatives from the project countries (either the GEF Focal Point or an appointee) and a designee from UN Environment. CCN’s management role (led by the Project Coordinator) will be to review quarterly work programs; administer, oversee, and implement all project activities; provide financial management; monitor project implementation and outcomes; and ensure that the project is delivered on time and on budget. Project stakeholders, including parliamentarians, Ministers, and other high-level decision makers; implementing agency representatives; local communities; and CCN partners in target countries and the region—will also be consulted throughout the course of the project for their insight and feedback on project activities.

- The Project Steering Committee (PSC) will be comprised of CCN (the Project Executing Agency), UN Environment (the Project Implementing Agency), and representatives from each of the four involved countries to be either the GEF Operational Focal point or their designee. The key partner agencies identified are as follows: in Antigua and Barbuda, the Department of Environment and Barbuda Council; in Dominica, the Department of Forestry; in Grenada the Fisheries Division; in Saint Lucia the Ministry of Sustainable Development. This steering committee represents the interests of multiple parties in achieving the goals of the project, which is to advance conservation agendas at the identification of country leaders in four countries of the Eastern Caribbean.

- CCN will build upon its extensive, diverse network of CCN and ICCF partner organizations to add value to country/regional initiatives. CCN will involve both local representatives on the ground and overall management of these organizations to invite their input and expertise, as well as their participation in CCN programs, in order to ensure the highest quality programs. CCN’s strength is working at the very highest levels of government, engaging policymakers in a top-down approach. For many of the roles, existing CCN staff will be allocated proportionally to work on this project; for example, the Project Coordinator, Senior Policy Advisor, Senior Political Advisor, International Conservation Corps Director, Technical Writer, and Communications Officer are all current CCN employees based in CCN’s headquarters in Washington, D.C. and will devote a portion of their time to this project, as needed. There will be two Program Officers for this project; one based in Washington, DC and the other recruited and based in the Caribbean in one of the project countries, to be determined prior to project inception.   The Program Officer based in the Caribbean will be responsible for managing the Regional Secretariat for the legislative conservation caucus, and thus serve as a crucial link between in-country events and partners, and the communications and management structures in Washington DC. Terms of Reference for the CCN staff for this project are provided in Appendix 11.

- The International Conservation Corps, in carrying out Component 2 of the project, will be responsible for coordinating with local stakeholders and implementing partners on the ground, including local NGOs, and government agencies, as well as civil society organizations. Through interviews and meetings with such stakeholders to establish baseline situations of management of protected areas, the International Conservation Corps can then subsequently assist in the improvement of management plans and provide technical capacity training for enhanced implementation.

Figure 1: Project Institutional Frame

# Section 5: Stakeholder Participation

CCN unites policymakers, businesses, NGOs, and governments – providing a vital link between natural resource management and sustainable economic development. The project’s design and planned implementation are premised on outreach to key stakeholders which together can effect change. At the national level, the following activities will take place with wide stakeholder participation:

- National-level roundtables/workshops of stakeholders, policymakers, and/or conservation groups to discuss biodiversity policy

- Briefings for legislative conservation caucus members showcasing biodiversity conservation issues, projects, cutting-edge research, and/or best practices

- Members of Parliament will form legislative conservation caucuses, in which members from multiple parties will cooperate towards collaboratively-identified conservation objectives. CCN will then build an organization around this group of policymakers, bringing in public- and private-sector partners to empower the caucus with sound information and give them the tools to convince a wider following that the policies they are pursuing are beneficial to their constituencies and the nation. CCN will also involve caucus members in interactions with legislators from other nations, demonstrating how important these policies are to a wide body and providing opportunities for recognition regionally and internationally. This is a proven process that has been effective within legislative bodies around the world. It also promotes longevity; as policymakers receive recognition for their work, they and their peers are motivated to continue and expand this work.

- The main points of contact and closest partners for Component 2 will be members of the agencies or division responsible for implementing the protected area management plan, co-management agreement, or business plan as the case may be. Other ministries will also provide input and support to the drafting process and in stakeholder meetings, and will likely have specific roles in the implementation of the project outputs, as well. The key government agency partners identified in each country are as follows: in Antigua and Barbuda, the Department of Environment and the Barbuda Council; in Dominica, the Forestry Division; in Grenada, the Department of Fisheries; and in Saint Lucia, the Department of Sustainable Development.

- Because of their important management role over protected areas and MPAs, the International Conservation Corps teams work extensively with PA/MPA authorities in key government partner agencies in the formation updating of management plans, business plans, and co-management agreements in the four Eastern Caribbean countries. The PA/MPA staff will additionally participate in briefings and workshops mostly in phase three of most Component 2 activity plans, to benefit from additional information and practice on implementation strategies of PA/MPA management plans. The key government partner agency for each country is identified in more detail below.

- Civil society organizations, NGOs, and tourism companies will be important participants in the project by helping to educate and raise awareness of legislators to the impact of conservation issues on local people and businesses, as well as participating in consultations for the drafting of management/implementation/business plans for Protected Areas. Civil society members are often most affected by current and future land use, and as the constituents of legislative conservation caucus members, will drive many of the pressures placed on the caucus members. Civil society organizations, such as fishermen’s or farmer’s associations will be included in stakeholder meetings with conservation caucus members to provide insight into how conservation issues are faced by constituents and local individuals. They will also be consulted in drafting management/implementation/business plans for the Protected Area sites identified in component 2 for each country. NGOs are important stakeholders because of their proximity to the issues and people they effect on the ground. They often have important insight into the barriers and gaps in policy implementation and baseline status of environmental concerns and therefore their input will be especially valuable both as recipients and contributors in dialogues, briefings, and workshops of both Components 1 and 2. Tourism companies are important potential partners in the caucus model because their livelihood and businesses depend to a great extent upon the preservation of natural resources and biodiversity. This incentive makes them more likely to help drive political will towards stronger policy action, as well as relay important information about the economic role that biodiversity plays within the country. Tourism companies will therefore be approached to participate in briefings and field activities for the caucus, to help raise legislator awareness to on-the-ground situations. Relevant tourist companies operating in protected area sites identified in component 2 for each country will also be consulted in drafting management/implementation/business plans.

Table 6: Key stakeholders

| Stakeholders | Current Mandates / Responsibilities | Roles in Project Implementation |
| --- | --- | --- |
| Conservation Council of Nations (CCN) | CCN is a global network of policymakers engaged in conservation discussions, on-the-ground capacity building and public-private partnerships to elevate the importance of biodiversity conservation on national and regional agendas. | CCN is the implementation agency for the project, and will be responsible for the management of the regional secretariat for the support of the legislative conservation caucuses, as well as the planning and reporting of legislative conservation caucus events and field missions. |
| Members of Parliament | Parliaments are relatively small in these four countries, and MPs are elected by one constituency that they represent by a majority vote. Members of Parliament are beholden to their constituents, and many have campaigned upon the promise of economic development, educational improvement, and climate resilience. Members from majority parties are often given cabinet positions in specific ministries for which sectors they are responsible. The most relevant ministries include Ministry of Tourism, Environment, Agriculture, and Fisheries. | Members of Parliament will form legislative conservation caucuses on international conservation, in which members from multiple parties will cooperate towards collaboratively-identified conservation objectives. CCN will then build an organization around this group of policymakers, bringing in public- and private-sector partners to empower the caucus with sound information and give them the tools to convince a wider following that the policies they are pursuing are beneficial to their constituencies and the nation. CCN will also involve caucus members in interactions with legislators from other nations, demonstrating how important these policies are to a wide body and providing opportunities for recognition regionally and internationally. This is a proven process that has been effective within legislative bodies around the world. It also promotes longevity; as policymakers receive recognition for their work, they and their peers are motivated to continue and expand this work. |
| Department of Environment Antigua and Barbuda | Responsible for National Park management in Antigua and Barbuda | The main point of contact and closest partner for Component 2.1.1, in which officials will be included in consultation and creation of an implementation plan for Codrington Lagoon National Park. Staff will benefit from training workshops |
| Barbuda Council Antigua and Barbuda | Current Managing authority of Codrington Lagoon National Park | An important point of contact and partner for Component 2.1.1 with which International Conservation Corps. Volunteers will conduct training for technical capacity enhancement |
| Department of Forestry in Dominica | Houses the Director of National Parks and responsible for National Parks management in Dominica | The main point of contact and closest partner for Component 2.1.2, in which officials will be included in consultation, market study, drafting, and implementation of a business plan for Cabrits National Park. Staff will benefit from briefings and training workshops. |
| Fisheries Division in Grenada | Responsible for MPA management in Grenada | The main point of contact and closest partner for Component 2.1.3, in which officials will be included in consultation and passage of a co-management agreement for Grand Anse MPA. |
| Ministry of Sustainable Development Saint Lucia | Responsible for leading the process of sustainable development through promotion of environmental management and participatory approach to government | The main point of contact and closest partner for Component 2.1.4, in which officials will be included in consultation and passage of a National Park Management Plan for proposed Iyanola National Park |
| Grenada and Carriacou Scuba Diving Association of Dive Shops | Organizes the scuba diving shops and tourism operations in Grenada and Carriacou, including those on Grand Anse MPA and contributes many visitors to the MPA | Will participate in briefings and field activities for the legislative conservation caucus, and to help raise legislator awareness regarding on-the-ground situations and the importance of biodiversity to the tourism sector |
| Environmental Awareness Group (EAG) | Antiguan-based nonprofit that aims to raise awareness and value of natural resources and promote their sustainable management | Will be a participant in stakeholder forums for legislative conservation caucus in Antigua and Barbuda to provide nonprofit perspective on conservation issues and agenda items |
| Hotel properties (in all target countries, with emphasis on those in close geographic proximity and/or those with vested interests) | Provide accommodations and tourism opportunities in the protected areas | Property management will be consulted about potential for sustainable tourism opportunities in the protected areas, as well as solicited to participate in briefings and stakeholder forums to raise legislator awareness to hotelier perspectives and importance of biodiversity to tourism sector. To be engaged during inception workshops and over the course of project implementation |
| Other private sector (tour operators, dive shops, commercial retailers) | Tour and dive shop operators offer scuba/snorkeling and other nature-based experiences in conjunction with hotels and other commercial retailers in and around the protected areas. | Will participate in briefings and field activities for the caucus, and to help raise legislator awareness regarding on-the-ground situations and the importance of biodiversity to the tourism sector. |
| St. Lucia Network of Rural Women Producers | Group of eighty women involved mainly in agro-processing and farming. There are four clusters, including in Babonneau and Micoud located within the proposed Iyanola National Park | The network will be consulted in drafting the National Park Management Plan, as well as invited to stakeholder forums and briefings of legislators on the importance of natural resource management to local livelihoods, especially for women. |
| Gouyave Fishermen Cooperative Society Limited | Association of fishermen in the Gouyave Marine Protected Area of Grenada that organize around fishers’ rights | The Cooperative will be consulted in drafting the co-management agreement for the management of Grand Anse Marine Protected Area and invited to stakeholder forums to raise legislator awareness to the importance of biodiversity to livelihoods of fishermen in Grenada |
| Dominica Conservation Association (DCA) | Nonprofit based in Dominica that promotes the judicious management and development of Dominica’s natural, cultural, and economic resources | CCN will seek the organization’s input in dialogues, briefings, and workshops to inform legislators on important identified conservation issues and raise legislative awareness on the importance of biodiversity |
| Grenada Fund for Conservation (GFC) | Nonprofit NGO with the aim of helping promote and protect Grenada’s environment by working in partnership with local, regional and international conservation agencies, including legislative changes | CCN will seek the organization’s input in dialogues, briefings, and workshops to inform legislators on important identified conservation issues and raise legislative awareness on the importance of biodiversity |
| Nonprofit and community groups in target countries that are recognized ‘forefront stewards’ of the resource | Community organizations and nonprofits focused on environmental conservation and biodiversity protected agendas that complement the project. | Will be consulted in regards to Component 2 outcomes, as well as invited to stakeholder forums and briefings of legislators on importance of biodiversity to local livelihoods. |
| Civil Society | In each country, the natural resources are important to the general population as a source of livelihood, especially in areas that include marine and forest components. Civil society members such as fishermen, market owners, and farmers are an integral part of land management, and therefore important stakeholders in conservation policies that affect their livelihoods. | Civil society members are the ones most affected by current and future potential land use, and as the constituents of legislative conservation caucus members, will drive many of the pressures placed on the caucus members. Civil society organizations, such as fishermen’s or farmer’s associations, will be included in stakeholder meetings with conservation caucus members to provide insight into on-the-ground situations. They will also be consulted in drafting management / implementation / business plans for the Protected Area sites identified in component 2 for each country |

# Section 6: Monitoring and Evaluation Plan

- The project will follow UNEP standard monitoring, reporting and evaluation processes and procedures with substantive and financial project reporting requirements. Reporting requirements and templates are an integral part of the UNEP legal instrument to be signed by the executing agency and UNEP.

- The project M&E plan is consistent with the GEF Monitoring and Evaluation policy. The Project Results Framework presented in Appendix 4 includes SMART indicators for each expected outcome as well as mid-term and end-of-project targets. These indicators along with the key deliverables and benchmarks included in Appendix 6 will be the main tools for assessing project implementation progress and whether project results are being achieved. The means of verification and the costs associated with obtaining the information to track the indicators are summarized in Appendix 6. Other M&E related costs are also presented in the Costed M&E Plan and are fully integrated in the overall project budget.

- The M&E plan will be reviewed and revised as necessary during the project inception workshop to ensure project stakeholders understand their roles and responsibilities vis-à-vis project monitoring and evaluation. Indicators and their means of verification may also be fine-tuned at the inception workshop. Day-to-day project monitoring is the responsibility of the project management team but other project partners will have responsibilities to collect specific information to track the indicators. It is the responsibility of the Project Manager to inform UNEP of any delays or difficulties faced during implementation so that the appropriate support or corrective measures can be adopted in a timely fashion.

- The project Steering Committee will receive periodic reports on progress and will make recommendations to UNEP concerning the need to revise any aspects of the Results Framework or the M&E plan. Project oversight to ensure that the project meets UNEP and GEF policies and procedures is the responsibility to the Task Manager in UNEP-GEF. The Task Manager will also review the quality of draft project outputs, provide feedback to the project partners, and establish peer review procedures to ensure adequate quality of scientific and technical outputs and publications.

- Project supervision will take an adaptive management approach. The Task Manager will develop a project supervision plan at the inception of the project which will be communicated to the project partners during the inception workshop. The emphasis of the Task Manager supervision will be on outcome monitoring but without neglecting project financial management and implementation monitoring.  Progress vis-à-vis delivering the agreed project global environmental benefits will be assessed with the Steering Committee at agreed intervals. Project risks and assumptions will be regularly monitored both by project partners and UNEP. Risk assessment and rating is an integral part of the Project Implementation Review (PIR). The quality of project monitoring and evaluation will also be reviewed and rated as part of the PIR. Key financial parameters will be monitored quarterly to ensure cost-effective use of financial resources.

- In-line with UNEP Evaluation Policy and the GEF’s Monitoring and Evaluation Policy the project will be subject to a Terminal Evaluation and, additionally, a Mid-Term Review will be commissioned and launched by the Project Manager before the project reaches its mid-point if deemed necessary after discussion with the Evaluation Office. The possibility of a Mid-Term Evaluation will be discussed with the Evaluation Office.

- The Evaluation Office will be responsible for the Terminal Evaluation (TE) and will liaise with the Task Manager and Executing Agency(ies) throughout the process.  The TE will provide an independent assessment of project performance (in terms of relevance, effectiveness and efficiency), and determine the likelihood of impact and sustainability. It will have two primary purposes: (i) to provide evidence of results to meet accountability requirements, and (ii) to promote learning, feedback, and knowledge sharing through results and lessons learned among UNEP, the GEF, executing partners and other stakeholders. The direct costs of the evaluation will be charged against the project evaluation budget.  The Terminal Evaluation will be initiated no earlier than six months prior to the operational completion of project activities and, if a follow-on phase of the project is envisaged, should be completed prior to completion of the project and the submission of the follow-on proposal. Terminal Evaluations must be initiated no later than six months after operational completion.

- The draft TE report will be sent by the Evaluation Office to project stakeholders for comment. Formal comments on the report will be shared by the Evaluation Office in an open and transparent manner. The project performance will be assessed against standard evaluation criteria using a six point rating scheme. The final determination of project ratings will be made by the Evaluation Office when the report is finalised and further reviewed by the GEF Independent Evaluation Office upon submission.  The evaluation report will be publically disclosed and may be followed by a recommendation compliance.

- The Management Effectiveness Tracking Tools (METT) is attached as Appendix 14. This will be updated at mid-term and at the end of the project and will be made available to the GEF Secretariat along with the project PIR report. As mentioned above the mid-term and terminal evaluation will verify the information of the tracking tool.

# Section 7: Project Financing and Budget

## 7.1	Overall Project Budget

- The overall project budget of this project is US$4,051,700. Costs to the GEF Trust Fund amount to US$1,866,700 as presented in Appendix 1.

Table 7: Summary GEF budget for project implementation by Year

| Components | Amount Requested from GEF (USD) |
| --- | --- |
| Year 1 | 656,378 |
| Year 2 | 605,661 |
| Year 3 | 604,661 |
| Totals | 1,866,700 |

Table 8: Summary GEF budget for project implementation by Component

| Components | Amount Requested from GEF (USD) |
| --- | --- |
| Component 1 | 820,309 |
| Component 2 | 696,691 |
| Monitoring & Evaluation | 180,000 |
| Project Management | 169,700 |
| Totals | 1,866,700 |

## 7.2	Project Co- financing

- US$2,185,000 is provided in the form of co-financing, as detailed in Appendix 2. Co-financing secured during the lifetime of the project will be reported throughout implementation.

Table 9: Cofinance

| Conservation Council of Nations | Cash | 510,000 |
| --- | --- | --- |
| Conservation Council of Nations | In-Kind | 1,350,000 |
| ICCF Conservation Council | Cash | 325,000 |
| Total |  | 2,185,000 |

Table 10: Cofinance

| Component 1 | 658,215 |
| --- | --- |
| Component 2 | 1,301,785 |
| M&E | 25,000 |
| Project Management | 200,000 |
| Total | 2,185,000 |

## 7.3	Project Cost- Effectiveness

- Human capital empowerment is a critical component of cost-effective capacity building. Transferring and connecting existing capacity and knowledge directly to build human capital is a direct approach.

- The expected outcomes and outputs under each project component consider cost-effective activities to achieve them, including the use of low-cost International Conservation Corps experts, particularly taking into consideration the following: (i) complementarity with previous and ongoing GEF-funded projects in the Caribbean, (ii) expected improvement of the capacity of targeted Protected Areas to produce ecosystem services more efficiently through improved management, business, and implementation plans; and (iii) reversal of the "business-as-usual" approach, which until now has been responsible for accelerated growth of costs of environmental degradation in the targeted countries. Without intervention, millions of dollars will be lost annually due to declining fish stocks, reduced tourism, loss of shoreline protection, and coral reef degradation throughout the region. This project will generate outcomes and outputs that will significantly reduce this loss.

- Additionally, this project will help to reduce dependence of the targeted countries on foreign assistance by building private-sector commitment to provide funding for biodiversity conservation (by demonstrating the value proposition and return on investment); by increasing legislative support within target countries to provide funding at the national level; and by overall increasing the amount of revenues and/or preventing revenue loss through improved capacity among policymakers, park/protected area managers, etc. leading to resilient and profitable marine ecosystems. The multiple co-benefits for health, the economy, and society further exemplify the cost-effectiveness of this project.

# Appendices Table of Contents

Appendix 1:	Budget by project components and UN Environment budget lines (attached Excel file)

Appendix 2:	Co-financing by source and UN Environment budget lines (attached Excel file)

Appendix 3:	Incremental cost analysis

Appendix 4:	Results Framework

Appendix 5:	Workplan and timetable

Appendix 6:	Key deliverables and benchmarks

Appendix 7:	Costed M&E plan

Appendix 8:	Summary of reporting requirements and responsibilities

Appendix 9:	Consultant Costs

Appendix 10: 	Decision-Making Flowchart

Appendix 11:	Terms of Reference

Appendix 12:	Co-financing commitment letters from project partners

Appendix 13: 	Draft Procurement Plan

Appendix 14:	Management Effectiveness Tracking Tools

Appendix 15:	UN Environment Environmental and Social Safeguards

Appendix 16:	Theory of Change

Appendix 17:	Endorsement letters of GEF National Focal Points

Appendix 18: Project Taxonomy

Appendix 19: Core Indicators

## Appendix 3:	Incremental Cost Analysis

The incremental costs and benefits of the proposed project are summarized in the following incremental cost matrix. The incremental cost of the project, USD$4,051,700, is required to achieve the project’s global environmental benefits. Of this amount USD$1,866,700 (representing 46.5%) is being requested from GEF. The remaining amount of USD$2,185,000 (53.5%) of the total cost will come from national and international partners. The figure includes both in-kind and cash contributions.

| COMPONENT | Baseline (B) (excluding PM and M&E costs) | Alternative (A) (excluding PM and M&E costs) | Increment (A-B) (excluding PM and M&E costs) |
| --- | --- | --- | --- |
| Component 1: Build and enhance political will for conservation |  |  |  |
| Outcome 1.1: Self-sustaining legislative conservation caucuses support conservation of key biodiversity resources through enhanced political will | No legislative conservation caucuses currently exist in the targeted countries. Without GEF support, no new legislative conservation caucuses will be established, and thus legislators in the targeted countries will not have the necessary increased political will to support conservation of key biodiversity resources. Additionally, no new strategic partnerships will be established. | The legislative conservation caucus model will be implemented in the four target countries. Strategic partnerships will be established to support caucus activities and provide expertise Four new legislative conservation caucuses will be formed. This will result in greater capacity and willingness to assess and address biodiversity conservation challenges at high levels of government. 3-5 strategic partnerships established to support caucus activities and provide appropriate expertise to members | Total Cost to GEF: $820,309 Co-Financing: $658,215 |
| Output 1.1.1 Multiparty legislative conservation caucuses of legislators including structure and functioning for Antigua and Barbuda, Dominica, Grenada, and Saint Lucia defined and submitted to legislators for approval |  |  |  |
| Output 1.1.2 A regional secretariat to support the legislative conservation caucuses |  |  |  |
| Output 1.1.3 Strategic partnerships with key private-sector and non-governmental partners, to support the activities of the caucuses submitted to national authorities for approval |  |  |  |
| Outcome 1.2: Enhanced cooperation between the legislative members and stakeholders in their respective countries is promoted by broader knowledge of the conservation challenges in Antigua and Barbuda, Dominica, Grenada, and Saint Lucia and best practices (i.e., legislators take leadership to propose and adopt new legislation). | The four target countries currently lack significant cooperation between legislators and Executive Branch agencies due to low understanding of the conservation challenges in Antigua and Barbuda, Dominica, Grenada, and Saint Lucia and best practices. Without GEF support, there will be low prioritization of biodiversity conservation on legislative agendas and low engagement in building cooperation at all levels of government in the countries. National support for legislative, policy, and/or regulatory change will remain low, and no significant new biodiversity conservation laws, regulations, or policies will be enacted or amended in the target countries. | With GEF support, there will be increased prioritization of biodiversity conservation on legislative conservation caucus agendas and cooperation between Executive Branch agencies and legislators. National support for legislative, policy, and/or regulatory change will increase (as measured by caucus activities and agenda reviews). The legislative branch will develop the consensus and expertise to achieve passage and enactment of new legislation. 20 briefings will be held, with media created for each. Each legislative conservation caucus will have a conservation agenda to guide its actions |  |
| Output 1.2.1 Portfolio of conservation priorities created with the legislative conservation caucus |  |  |  |
| Output 1.2.2 Legislative members are exposed to expertise and advice from conservation stakeholders through workshops, dialogues, briefings, and field visits (20 total activities) |  |  |  |
| Output 2.1.1: An Implementation plan to facilitate and improve upon the 2009-2019 management plan in Barbuda’s Codrington Lagoon National Park developed and submitted for approval |  |  |  |
| Output 2.1.2: A business plan in accordance with biophysical plan, management plan, & livelihood plan to increase self-sustainability of Cabrits National Park in Dominica developed and submitted for approval |  |  |  |
| Output 2.1.3: A co-management agreement between Fisheries Division and third-party coalition of managers to improve legal frameworks on natural resource management in the Grand Anse MPA of Grenada drafted and submitted to the competent authorities for signature | Biodiversity conservation efforts in target countries are inadequate due to a need for better management of PAs, MMAs, and MPAs as well as other enhancements such as signage plans, community engagement practices, and willingness-to-pay studies, based on best appropriate practices and legal structures and enforcement. Without GEF support, PAs, MMAs, and MPAs will continue to lack optimal management and other enhancements. With GEF support, there will be improved biodiversity conservation in protected areas through better management of PAs, MMAs, and MPAs as well as enhancements such as signage plans, community engagement practices, and willingness-to-pay studies, based on best appropriate practices and legal structures and enforcement. This will include: - Establishment of an implementation plan for Codrington Lagoon National Park in Barbuda - Establishment of a business plan for Cabrits National Park in Dominica - Establishment of a co-management agreement between the fisheries sector and third-party manager to improve the legal framework around Grand Anse MPA in Grenada - Establishment of a Protected Areas management plan for proposed Iyanola National Park in St. Lucia To achieve this, field visits will be made by members of the International Conservation Corps team to Field mission by International Conservation Corps to Codrington Lagoon National Park, Cabrits National Park, Grand Anse MPA, and Iyanola National Park. | Improved biodiversity conservation in protected areas. Better management of PAs, MMAs, and MPAs and other enhancements such as signage plans, community engagement practices, and willingness-to-pay studies, based on best appropriate practices and legal structures and enforcement. Management plan for Codrington Lagoon National Park in Barbuda. Financial plan for Cabrits National Park in Dominica. Co-management agreement between the fisheries sector and third-party manager to improve the legal framework around Grand Anse MPA in Grenada. Park-wide management plan for Iyanola National Park in St. Lucia. | Total Cost to GEF: $696,691 Co-Financing: $1,301,785 |
| Output 2.1.1: An Implementation plan to facilitate and improve upon the 2009-2019 management plan in Barbuda’s Codrington Lagoon National Park developed and submitted for approval |  |  |  |
| Output 2.1.2: A business plan in accordance with biophysical plan, management plan, & livelihood plan to increase self-sustainability of Cabrits National Park in Dominica developed and submitted for approval |  |  |  |
| Output 2.1.3: A co-management agreement between Fisheries Division and third-party coalition of managers to improve legal frameworks on natural resource management in the Grand Anse MPA of Grenada drafted and submitted to the competent authorities for signature |  |  |  |
| Output 2.1.4: A Protected Areas management plan for the proposed Iyanola National Park in Saint Lucia that builds upon the interim regional land use management plan drafted by a consultancy group for an ongoing GEF project in the region drafted and submitted for approval |  |  |  |
| COST BASELINE | COST ALTERNATIVE | GEF: $1,866,700 |  |
|  |  | Co-financing: $2,185,000 |  |
| TOTAL: $ 0 | TOTAL: $4,051,700 | TOTAL: $4,051,700 |  |

## Appendix 4:  Project Results Framework

| Outcomes | Indicators | Baseline | Mid-term Targets | End of Project Targets | Means of Verification |
| --- | --- | --- | --- | --- | --- |
| Project Objective: To support biodiversity conservation in Antigua and Barbuda, Dominica, Grenada, and St. Lucia through enhanced political will and capacity building for improved management of marine protected areas (MPAs), marine management areas (MMAs) and protected areas (PAs) |  |  |  |  |  |
| Component 1: Build and enhance political will for conservation |  |  |  |  |  |
| Outcome 1.1: Self-sustaining legislative conservation caucuses support conservation of key biodiversity resources through enhanced political will | % of overall legislative body participating in legislative conservation caucus events in each country | No caucuses established, no membership – 0% participation | Legislative conservation Caucuses established in each country with at least 13% participation in each country | Legislative conservation Caucuses established in each country with at least 25% participation in each country | Caucus charters / agreements Caucus Membership Roster In-country staff contracted to facilitate caucus activities and communication |
|  | # of legislative conservation caucuses formalized across all countries | No caucuses formalized | 2 caucuses formalized | 4 caucuses formalized |  |
|  | # of strategic partnerships initiated to improve conservation of key biodiversity resources in the project countries | No established strategic partnerships supporting caucus members | At least 3 Strategic partnerships | 5-7 strategic partnerships established with private-sector stakeholders through which these partners will participate in and support caucus activities and provide appropriate expertise to members |  |
|  | # of proposed policies, laws or regulations supporting biodiversity conservation by legislative conservation caucus members across all countries | No policies, laws, or regulations developed and proposed by caucus members | At least 2 proposed policies, laws and/or regulations supporting biodiversity conservation by caucus members | 4 proposed policies, laws and/or regulations supporting biodiversity conservation by caucus members |  |
|  | % of women participation in the legislative conservation caucus in each country | No participation | % participation in the caucus is equivalent to % of women in the legislative body | % participation in the caucus is equivalent to % of women in the legislative body |  |
|  | # of women in leadership positions in the legislative conservation caucuses in each country | No leadership established | At least 2 women in caucus leadership positions | At least 4 women in caucus leadership positions |  |
| Outcome 1.2: Enhanced cooperation between the legislative members and stakeholders in their respective countries is promoted by broader knowledge of the conservation challenges in Antigua and Barbuda, Dominica, Grenada, and Saint Lucia and best practices (i.e., legislators take leadership to propose and adopt new legislation). | # of Educational Briefings and Workshops held for stakeholders across all countries | 0 Educational Briefings or workshops held | At least 8 briefings held | Host 20 briefings total, Year 1 - 1 per country, Year 2 - 2 per country, Year 3, 2 per country | Caucus agendas Communication between caucuses on common challenges and sharing of best practices Educational Briefings and Workshops New legislation or policies |
|  | # of conservation agendas developed by legislative conservation caucus across all countries (conservation issues acknowledged by legislators and of interest to engage upon via briefings, workshops, or legislative discussions) | No agendas developed | At least 1 draft conservation agenda created and under discussion | 4 conservation agendas; one for each caucus to guide its actions, including priorities, goals and an action plan for passing new policies, laws, and regulations |  |
|  | # of documents or media products to share among legislative conservation caucuses in the region and made publicly available (shared through email and other social media (Twitter, Facebook, etc.), articles on internationalconservation.org, and video recordings shared on YouTube and/or local media coverage). | No documents or media products to share discussions of best practices | At least 8 documents or media products and made publicly available | At least 20 documents or media products created made publicly available throughout the region |  |
| Outputs under Component 1 Output 1.1.1: Multiparty legislative conservation caucuses of legislators including structure and functioning for Antigua and Barbuda, Dominica, Grenada, and Saint Lucia defined and submitted to legislators for approval Output 1.1.2: A local secretariat to support the legislative conservation caucuses Output 1.1.3: Strategic partnerships with key private-sector and non-governmental partners, to support the activities of the caucuses submitted to national authorities for approval Output 1.2.1: Portfolio of conservation priorities created with the legislative conservation caucus Output 1.2.2: Legislative members are exposed to expertise and advice from conservation stakeholders through workshops, dialogues, briefings, and field Output 1.2.3: New legislation, policies, guidance and support as necessary provided on demand to support requests by Members |  |  |  |  |  |
| Component 2: Capacity building (through technical support of the International Conservation Corps program) to support the management of protected areas, marine protected areas, and marine management areas |  |  |  |  |  |
| Outcome 2.1: Improved biodiversity conservation in protected areas through better management of Protected Areas, Marine Protected Areas, and Marine Management Areas, and other enhancements such as signage plans, community engagement practices, and co-management agreements, based on best appropriate practices and legal structures and enforcement. | Management capacity of targeted protected areas, as measured using the METT - Codrington Lagoon NP - Cabrits NP - Grand Anse MPA - Iyanola NP | Baseline METT Scores (Appendix 14) - Codrington Lagoon NP - 48 - Cabrits NP - 40 - Grand Anse MPA – 32 - Iyanola NP - 30 | Mid Term METT Scores - Codrington Lagoon NP - 56 - Cabrits NP - 54 - Grand Anse MPA - 42 - Iyanola NP - 35 | End of Project METT Scores - Codrington Lagoon NP - 67 - Cabrits NP - 70 - Grand Anse MPA - 61 - Iyanola NP - 46 | METT documents |
|  | Number of Implementation plans for Codrington Lagoon National Park in Barbuda | Management plan (2009-2019) exists but not operationalized | 1 draft Implementation Plan | 1 Implementation Plan produced | Implementation plan for Codrington Lagoon National Park in Barbuda Business plan for Cabrits National Park in Dominica Co-management agreement between the Fisheries Division and third-party manager to improve the legal framework around Grand Anse MPA in Grenada Park management plan for Iyanola National Park in St. Lucia Meeting reports and attendance rolls |
|  | Number of business plans/market studies for Cabrits National Park in Dominica | No business plans established, no market studies conducted | 1 market study conducted | 1 business plan produced; one market study conducted |  |
|  | Number of Co-management agreements between the Fisheries Division and third-party manager for the Grande Anse MPA in Grenada | No co-management plans in place, no co-management entities in existence; Fisheries Minister does not have legislative power to delegate authority | 1 draft co-management agreement; at least 1 co-management partner entity under consideration | 1 co-management plan signed between the Fisheries Division and partner entity under delegation of authority by the Minister of Fisheries |  |
|  | Number of targeted management plans for proposed Iyanola National Park in Saint Lucia | No management plan exists; an interim regional management plan is being developed under a separate GEF project | 1 draft management plan for National Park, based on an interim (wider area) regional management plan established | 1 Management plan produced |  |
|  | Number of major community stakeholder engagements per project country contributing to conservation actions promoted by the project (includes outreach and participation of local women’s cooperatives or organizations) | Existing stakeholder engagement between communities and Protected areas continues | At least 4 stakeholder engagement opportunities | At least 8 stakeholder engagement opportunities |  |
| Outputs under Component 2 Output 2.1.1: An Implementation plan to facilitate and improve upon the 2009-2019 management plan in Barbuda’s Codrington Lagoon National Park developed and submitted for approval. Output 2.1.2: A business plan in accordance with biophysical plan, management plan, & livelihood plan to increase self-sustainability of Cabrits National Park in Dominica developed and submitted for approval Output 2.1.3: A co-management agreement between Fisheries Division and third-party coalition of managers to improve legal frameworks on natural resource management in the Grand Anse MPA of Grenada drafted and submitted to the competent authorities for signature Output 2.1.4: A Protected Areas management plan for the proposed Iyanola National Park in Saint Lucia that builds upon the interim regional land use management plan drafted by a consultancy group for an ongoing GEF project in the region drafted and submitted for approval |  |  |  |  |  |

## Appendix 5: Workplan and Timetable

|  | Year 1 |  |  |  | Year 2 |  |  |  | Year 3 |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Activity | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 |  |
| Component 1: Build and enhance political will for conservation |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Outcome 1.1: Self-sustaining legislative conservation caucuses support conservation of key biodiversity resources through enhanced political will. |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 1.1.1: Multiparty legislative conservation caucuses of legislators including structure and functioning for Antigua and Barbuda, Dominica, Grenada, and Saint Lucia defined and submitted to legislators for approval |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1. Recruit, inform, orient and mentor potential members to the legislative conservation caucus model |  | x | x |  |  |  |  |  |  |  |  |  |  |
| 2. Creation of legislative conservation Caucus roster to track membership and activity |  |  | x |  | x |  | x |  | x |  | x |  |  |
| Output 1.1.2: A regional secretariat to support the legislative conservation caucuses |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1. Establish local office & register with government | x | x | x | x |  |  |  |  |  |  |  |  |  |
| 2. Hire and train local staff as needed | x | x | x |  |  |  |  |  |  |  |  |  |  |
| Output 1.1.3: Strategic partnerships with key private-sector and non-governmental partners, to support the activities of the caucuses submitted to national authorities for approval |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1. Identify potential stakeholders | x | x | x | x | x | x | x |  |  |  |  |  |  |
| 2. Conduct outreach and meetings with stakeholders to discuss and commit to involvement |  | x | x | x | x | x | x | x | x | x |  |  |  |
| 3. Host stakeholder events to recruit partners |  |  | x |  | x |  | x |  | x |  | x |  |  |
| Outcome 1.2: Enhanced cooperation between the legislative members and stakeholders in their respective countries is promoted by broader knowledge of the conservation challenges in Antigua and Barbuda, Dominica, Grenada, and Saint Lucia and best practices (i.e., legislators take leadership to propose and adopt new legislation). |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 1.2.1: Portfolio of conservation priorities created with the legislative conservation caucus |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1. Consultations with legislative conservation caucus members to identify, assess, and prioritize current conservation challenges | x | x |  |  | x |  |  |  | x |  |  |  |  |
| Output 1.2.2: Legislative conservation caucus members are exposed to expertise and advice from conservation stakeholders through workshops, dialogues, briefings, and field visits (20 total activities) |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1. Hold workshops, dialogues, briefings, and field visits to provide opportunities for members to discuss policies and showcasing biodiversity conservation issues, projects, cutting-edge research, and/or best practices; |  |  | x | x | x | x | x | x | x | x | x |  |  |
| 2. Conduct follow-up activities with all participants, and disseminate program outputs electronically to broaden the reach of the programs. |  |  |  | x |  | x |  | x |  | x |  | x |  |
| Output 1.2.3: New legislation, policies, guidance and support as necessary provided on demand to support requests by Members |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1. Provide expertise to legislative conservation caucus leadership, policymakers, partners, and other stakeholders in development of legislative/policy goals in each country; | x | x |  |  | x | x |  |  | x | x |  |  |  |
| 2. Provide legal expertise partners, to legislative conservation caucus leaders in drafting proposed legislation/amendments/ regulations; |  | x | x | x |  | x | x | x |  | x | x | x |  |
| 3. Engage stakeholders to encourage support for proposed new legislation/ amendments/regulations; |  |  | x | x |  |  | x | x |  |  | x | x |  |
| 4. Present proposed legislation/amendments/regulations to the larger legislative conservation caucus: provide educational materials to these bodies relating to the issues addressed by the legislation; |  |  | x | x |  |  | x | x |  |  | x | x |  |
| 5. Provide updates on the process to wider networks of legislators around the world to solicit support for efforts under this project and to educate and inspire other legislators to take similar actions. |  | x |  | x |  | x |  | x |  | x |  | x |  |
| Component 2: Capacity building (through technical support of the International Conservation Corps program) to support the management of protected areas, marine protected areas, and marine management areas |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Outcome 2.1: Improved biodiversity conservation in protected areas through better management of PAs, MMAs, and MPAs, and other enhancements such as signage plans, community engagement practices, and co-management agreements, based on best appropriate practices and legal structures and enforcement |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 2.1.1: An Implementation plan to facilitate and improve upon the 2009-2019 management plan in Barbuda’s Codrington Lagoon National Park developed and submitted for approval |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1. Members of International Conservation Corps team engage stakeholders to discuss current management plan, implementation needs, plan out work and assess progress |  | x |  | x |  | x |  |  |  |  |  |  |  |
| 2. Planning/design workshops to update management plan and develop the implementation plan |  |  |  |  |  | x |  | x |  | x |  |  |  |
| 3. Development of Implementation Plan |  |  |  |  | x | x | x | x | x | x | x | x |  |
| 4. Final wider stakeholder workshop for presentation and adoption of Implementation Plan |  |  |  |  |  |  |  |  |  |  |  | x |  |
| Output 2.1.2 A business plan in accordance with biophysical plan, management plan, & livelihood plan to increase self-sustainability of Cabrits National Park in Dominica developed and submitted for approval |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1. Members of International Conservation Corps team engage with stakeholders associated with Cabrits National Park for detailed needs assessment and work planning |  |  | x |  |  |  |  |  |  |  |  |  |  |
| 2. Meetings between International Conservation Corps team and with stakeholders to discuss business plan (including market study, market plan, and financial plan) for Cabrits in accordance with the biophysical plan, management plan, and livelihood plan. |  | x |  | x | x |  | x |  |  |  |  |  |  |
| 3. Workshops for stakeholder input to business plan development, validation and implementation |  |  |  |  |  |  |  | x |  | x |  | x |  |
| 4. Development of business plan |  |  |  | x | x | x | x | x | x | x | x |  |  |
| Output 2.1.3: A co-management agreement between Fisheries Division and third-party coalition of managers to improve legal frameworks on natural resource management in the Grand Anse MPA of Grenada drafted and submitted to the competent authorities for signature |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1. Members of International Conservation Corps team engage with relevant stakeholders at the Grand Anse MPA to initiate work, plan and assess progress | x |  | x |  | x |  | x |  | x |  | x |  |  |
| 2. Meetings between International Conservation Corps team and fisheries sector stakeholders to propose draft co-management agreements | x |  | x |  | x |  | x |  | x |  | x |  |  |
| 3. Development of co-management agreement |  | x | x | x | x | x |  |  |  |  |  |  |  |
| 4. Meeting with stakeholders in Grand Anse MPA to establish a co-managing stakeholder association | x |  | x |  | x |  | x |  | x |  | x |  |  |
| 5. Workshops to develop and adopt co-management agreement |  |  |  |  |  |  |  | x |  | x |  | x |  |
| Output 2.1.4: A Protected Areas management plan for the proposed Iyanola National Park in Saint Lucia that builds upon the interim regional land use management plan drafted by a consultancy group for an ongoing GEF project in the region drafted and submitted for approval |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1. Members of International Conservation Corps team engage with relevant stakeholders associated with Iyanola National Park to discuss needs and scope of work |  |  |  |  |  |  |  | x |  | x |  | x |  |
| 2. Meetings between International Conservation Corps team with and stakeholders to discuss interim management plans for park areas and an overarching plan for the National Park |  |  |  |  |  |  |  | x |  | x |  | x |  |
| 3. Development of Protected Areas Management Plan |  |  |  |  |  |  |  | x | x | x | x | x |  |
| 4. Workshops for stakeholder input to Protected Areas management plan for Proposed National Park based on designated area in ongoing GEF Iyanola project. |  |  |  |  |  |  |  | x |  | x |  | x |  |

Appendix 6: Key Deliverables and Benchmarks

| Outcomes/Outputs | Key Deliverables | Benchmarks |
| --- | --- | --- |
| Component 1: Build and enhance political will for conservation Outcome 1.1: Self-sustaining legislative conservation caucuses support conservation of key biodiversity resources through enhanced political will Outcome 1.2: Enhanced cooperation between the legislative members and stakeholders in their respective countries is promoted by broader knowledge of the conservation challenges in Antigua and Barbuda, Dominica, Grenada, and Saint Lucia and best practices (i.e., legislators take leadership to propose and adopt new legislation). |  |  |
| Outputs/milestones Output 1.1.1: Multiparty legislative conservation caucuses of legislators including structure and functioning for Antigua and Barbuda, Dominica, Grenada, and Saint Lucia defined and submitted to legislators for approval | - Legislative conservation caucus charters/agreements - Legislative conservation caucus Membership Roster | PY1-PY3: Legislative conservation caucuses established in all four target countries PY1-PY2: Determine appropriate benchmarks for legislative conservation caucus membership by end of PY3 |
| Output 1.1.2: A regional secretariat to support the legislative conservation caucuses and definition of caucus operation modalities | - Registration with government - In-country staff contracted to facilitate legislative conservation caucus activities and communication | PY1-PY2: Regional secretariat is registered with relevant government PY1-PY2: In-country staff contracted |
| Output 1.1.3: Strategic partnerships with key private-sector and non-governmental partners, to support the activities of the caucuses submitted to national authorities for approval | Stakeholder commitment to be involved | PY1-PY3: 5 partnerships created |
| Output 1.2.1: Portfolio of conservation priorities created with the legislative conservation caucus | Legislative Conservation Caucus agendas Communication between caucuses on common challenges and sharing of best practices | PY1-PY3: Agendas developed by each caucus PY1-PY3: 4 exchanges between caucuses |
| Output 1.2.2: Legislative members are exposed to expertise and advice from conservation stakeholders through workshops, dialogues, briefings, and field visits (20 total activities) | Educational Briefings and Workshops | PY1-PY3: 20 educational briefings and workshops |
| Output 1.2.3: New legislation, policies, guidance and support as necessary provided on demand to support requests by Members | Proposed legislation or policies | PY1-PY3: 1 new piece of legislation or policy drafted in each country |
| Component 2: Capacity building (through technical support of the International Conservation Corps program) to support the management of protected areas, marine protected areas, and marine management areas Outcome 2.1: Improved biodiversity conservation in protected areas through better management of PAs, MMAs, and MPAs, and other enhancements such as signage plans, community engagement practices, and co-management agreements, based on best appropriate practices and legal structures and enforcement. |  |  |
| Outputs/milestones Output 2.1.1: An Implementation plan to facilitate and improve upon the 2009-2019 management plan in Barbuda’s Codrington Lagoon National Park developed and submitted for approval. | Implementation plan for Codrington Lagoon National Park in Barbuda | PY1-PY2: Field mission by International Conservation Corps to Codrington Lagoon National Park PY1-PY3: Implementation plan for Codrington Lagoon National Park developed |
| Output 2.1.2: A business plan in accordance with biophysical plan, management plan, & livelihood plan to increase self-sustainability of Cabrits National Park in Dominica developed and submitted for approval | Business plan for Cabrits National Park in Dominica | PY1-PY2: Field mission by International Conservation Corps to Cabrits National Park PY1-PY3: Business plan for Cabrits National Park developed |
| - Output 2.1.3: A co-management agreement between Fisheries Division and third-party coalition of managers to improve legal frameworks on natural resource management in the Grand Anse MPA of Grenada drafted and submitted to the competent authorities for signature | Co-management agreement between the fisheries sector and third-party coalition of stakeholders to improve management of Grand Anse MPA in Grenada | PY1-PY2: Field mission by International Conservation Corps to Grand Anse MPA PY1-PY3: Co-management agreement developed between the fisheries sector and third-party manager to improve the legal coalition of stakeholders around Grand Anse MPA in Grenada |
| Output 2.1.4: A Protected Areas management plan for the proposed Iyanola National Park in Saint Lucia that builds upon the interim regional land use management plan drafted by a consultancy group for an ongoing GEF project in the region drafted and submitted for approval | Protected Areas management plan for proposed Iyanola National Park in St. Lucia | PY1-PY2: Field mission by International Conservation Corps to Iyanola National Park PY1-PY3: Protected Areas management plan for proposed Iyanola National Park developed |

## Appendix 7: Costed M&E plan

The indicative Monitoring and Evaluation Work Plan is provided in the table below.

| Type of M&E Activity | Responsible Parties | GEF Budget (USD) |  | Co-finance (USD) |  | Time Frame |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Inception Workshop and report | - Project Coordinator and Project Steering Committee | 30,000 |  | 12,000 |  | Within first 3 months of project start-up |  |
| Measurement of project indicators (outcome, progress and performance indicators, GEF tracking tools) including baseline data collection | - Project Coordinator | 45,000 |  | 5,000 |  | Outcome indicators: start, mid, and end of project Progress/performance indicators: annually |  |
| Semi-annual Progress / Operational reports to UN Environment | - Project Coordinator |  |  |  |  | Within 1 month of the end of reporting period; i.e., on or before 31 Jan. and 31 Jul. |  |
| Project Steering Committee (PSC) meetings + advisory technical group | - CCN, GEFSEC, UNEP, country representatives | 10,000 |  | 8,000 |  | Once a year minimum, planned for quarterly |  |
| Reports of PSC meetings | - Project Coordinator |  |  |  |  | Annually |  |
| Project Implementation Review (PIR) | - Project Coordinator, UNEP Task Manager |  |  |  |  | Annually, part of reporting routine |  |
| Mid Term Review/ Evaluation | - Project Coordinator, UNEP Task Manager | 25,000 |  |  |  | At mid-point of project implementation (*Note: If a Mid-Term review is not required for this MSP, these resources will be applied to the Terminal Evaluation) |  |
| Terminal Evaluation | - UNEP Evaluation Office with Project Coordinator, UNEP Task Manager and PSC | 40,000 |  |  |  | Within 6 months of end of project implementation |  |
| Financial Audits | - CCN | 20,000 |  |  |  | Annually |  |
| Project Final Report | - Project Coordinator | 10,000 |  |  |  | Within 2 months of the project completion date |  |
| Co-financing report | - Project Coordinator |  |  |  |  | Within 1 month of the PIR reporting period; i.e., on or before 31 July |  |
| Publication of Lessons Learnt and other project documents | - Project Coordinator |  |  |  |  | Annually, part of Semi-annual reports & Project Final Report |  |
| Total M&E Plan cost |  |  | 180,000 |  | 25,000 |  |  |  |

## Appendix 8: Reporting Requirements

| Reporting requirements | Due date | Format appended to legal instrument as | Responsibility of |
| --- | --- | --- | --- |
| Procurement plan (goods and services) | 2 weeks before project inception meeting | N/A | Project Coordinator |
| Inception Report | 1 month after project inception meeting | N/A | Project Coordinator |
| Expenditure report accompanied by explanatory notes | Quarterly on or before 30 April, 31 July, 31 October, 31 January | # Annex 11 | Project Coordinator |
| Cash Advance request and details of anticipated disbursements | Quarterly or when required | Annex 7B | Project Coordinator |
| Progress report | Half-yearly on or before 31 January | Annex 8 | Project Coordinator |
| Audited report for expenditures for year ending 31 December | Yearly on or before 30 June | N/A | CCN |
| Inventory of non-expendable equipment | Yearly on or before 31 January | Annex 6 | Project Coordinator |
| Co-financing report | Yearly on or before 31 July | Annex 12 | Project Coordinator |
| Project implementation review (PIR) report | Yearly on or before 31 August | Annex 9 | Project Coordinator, PSC Members, UNEP Task Manager |
| Minutes of steering committee meetings | Yearly (or as relevant) | N/A | Project Coordinator |
| Mission reports and “aide memoire” for executing agency | Within 2 weeks of return | N/A | Project Coordinator |
| Final report | 2 months of project completion date | Annex 10 | Project Coordinator |
| Final inventory of non-expendable equipment |  | Annex 9 | Project Coordinator |
| Equipment transfer letter |  | Annex 10 | Project Coordinator |
| Final expenditure statement | 3 months of project completion date | Annex 11 | Project Coordinator |
| Mid-term review or Mid-term evaluation | Midway through project | N/A | Project Coordinator |
| Final audited report for expenditures of project | 6 months of project completion date | N/A | CCN |
| Independent terminal evaluation report | 6 months of project completion date | Appendix 9 to Annex 1 |  |

## Appendix 9:	Consultant Costs

| Consultant | Activities | Related Project Outputs | Consultant Type* | # of Days | Rate (US$/day) | Total (US$) |
| --- | --- | --- | --- | --- | --- | --- |
| None |  |  |  |  |  |  |
| Total |  |  |  |  |  |  |

* IC = International Consultant; LC = Local Consultant

Consultant Costs Summary

| Consultant | # Days | Total Cost |
| --- | --- | --- |
| Consultant 1 |  |  |
| Consultant 2 |  |  |
| Consultant 3 |  |  |
| Consultant 4 |  |  |
| Consultant 5 |  |  |
| Total |  |  |

## Appendix 10: Decision-making Flowchart and Organogram

## Appendix 11: Terms of Reference

Overview of Staff

|  |  |  |  | Budget |  |
| --- | --- | --- | --- | --- | --- |
| Title | Reports to | Terms | Location | GEF | Co-Fin. |
| Project Coordinator | PSC | Full-time, 36 months | Washington | 140,000 [20,000 under PMC; 120,000 under activities] | 65,000 |
| Senior Political Advisor | Project Coordinator | Part-time -35%, 36 months | Washington | 180,000 | 100,000 |
| Senior Policy Advisor | Project Coordinator | Part-time -55%, 36 months | Washington | 135,000 | 50,000 |
| ICC Director | Project Coordinator | Part time – 15%, 36 months | Washington | 45,000 | 45,000 |
| Program Officer – Caribbean | Project Coordinator | Full-time, 36 months | Caribbean | 120,000 | 0 |
| Project Officer - Administration | Project Coordinator | Part time -33%, 36 months | Washington | 55,233 [27,700 under PMC; 27,533 under activities] | 0 |
| Communications Officer | Project Coordinator | Part Time-33%, 36 months | Washington | 90,000 | 30,000 |
| Technical Writer | Project Coordinator | Part time - 25%, 36 months | Washington | 60,000 | 45,000 |
| Additional Staff support – Program Officers | Project Coordinator | Part time, as needed | Washington, Bogota Office | 0 | 200,000 |
| Conservation Corps Experts | ICC Director | As projects dictate | Caribbean | 0 | 900,000 |
| Total |  |  |  | 825,233 | 1,435,000 |

| TITLE: | Project Coordinator |
| --- | --- |
| REPORTS TO: | Project Steering Committee |
| POSITION DESCRIPTION / MAIN ROLES AND RESPONSIBILITIES: |  |
| Reporting to the Project Steering Committee, the Project Coordinator will be the day-to-day coordinator of all project activities as outlined in the Project Document, including the following. - Management supervision of the project including oversight responsibility for all project staff. Specific key tasks include (by output) include: - Oversee process for recruitment, advising, orienting and mentoring potential members to the legislative conservation caucus model and support organization of outreach and meetings and recruitment drives for stakeholders and make technical/policy inputs as required (Outputs 1.1.1; 1.1.3); - Establish local office registration with host government; hire and train local staff as needed (Output 1.1.2); - Support organization of consultations dialogues, briefings, and field visits with legislative conservation caucus members to identify, assess, and prioritize current conservation challenges, showcasing biodiversity conservation issues, projects, cutting-edge research, and/or best practices and disseminate program outputs (Output 1.2.2); - Facilitate work of CCN team members in providing expertise to legislative conservation caucus leadership, policymakers, partners, and other stakeholders in development of legislative/policy goals in each country (Output 1.2.3); - Facilitate sustained engagement of stakeholders in support of proposed legislation/ amendments/regulations and organize relevant fora to present proposed legislation/amendments/regulations and provide updates on the process to wider networks of legislators around the world (Output 1.2.3); - Facilitate engagement of ICC team with local stakeholders in development/re-drafting of the Protected Areas implementation/management plans for Barbuda’s Codrington Lagoon National Park, Cabrits National Park (Dominica), Grand Anse MPA (Grenada) and Iyanola National Park (Saint Lucia) and contribute technical inputs as required (Outputs 2.1.1 to 4). - Event Planning, Preparation, Implementation, and Follow-up - Liaise with project partners to facilitate their involvement in project activities, including subject-matter expertise and resources - Perform activities relating to the scheduling, preparation, implementation, and follow-up for all project briefings and events - Liaise with appropriate GEF/UNEP representatives during the process of program development and implementation - Information and communication strategy - Develop updates and convey relevant information to the communications team - Coordinate with technical writer on all printed/web-based products to coordinate writing support, as necessary, and to ensure that products are properly edited/proofread before printing or disseminating electronically - Travel Planning - Conduct all activities related to travel planning for CCN project team members and others Liaison with Project Steering Committee Maintain regular communication with GEF/UNEP representatives and Project Steering Committee, especially the UNEP Task Manager, to provide project updates, seek input, and ensure that the project continues to meet expectations Monitoring and Evaluation Assume primary responsibility for tracking programs and activities, financial transactions, budget/expenses, and progress/measurable impact in accordance with the Monitoring and Evaluation (M&E) component for the project Reporting Ensure that all activity and budget reporting is conducted on time in accordance with the Project Document Workplan and Timetable |  |
| QUALIFICATIONS AND EXPERIENCE: |  |
| The Project Coordinator must have experience managing large projects, including overseeing project teams, managing complex budgets, interacting with oversight personnel or committees, and demonstrating adaptive management when necessary. Familiarity with the Caribbean is preferred, as is experience working with high-level policymakers and/or judicial representatives. Other required skills include: Education and Training - Fluent in English with exceptional writing and editing skills; Additional language proficiency desirable. - A university degree and 3+ years of experience in project management. - Experience or knowledge of non-profits a plus. Team Leadership Skills - Must work well as a leader of a multi-cultural, inter-disciplinary, multi-lingual, global team; - Proven, professional abilities and technical skills in managing complex multi-cultural operations and teams. Project Management Skills - Experience in working with international project teams; - Strong project management skills to plan, organize, coordinate and control the implementation of several projects simultaneously; - Demonstrated project management experience and ability to manage deadlines and budgets. |  |
| TERMS AND CONDITIONS: |  |
| - The position is based in Washington, DC, USA. · - 36-month contract - Full time - The job may require periodic international travel. |  |

| TITLE: | Senior Political Advisor |
| --- | --- |
| REPORTS TO: | Project Coordinator |
| POSITION DESCRIPTION / MAIN ROLES AND RESPONSIBILITIES: |  |
| Reporting to the Project Coordinator, the Senior Political Advisor will be involved in the day-today project activities as outlined in the Project Document, including the following. Provide Guidance for Activities of Project Staff Provide guidance and expertise to all project staff, as requested by the Project Coordinator. Activities include: - Network with embassies, international parliaments, and other stakeholders and other technical responsibilities. Specific tasks include (under relevant outputs): - Reach out to diplomatic and political representatives of targeted nations to solicit lead political champions for the legislative conservation caucuses, including orientation and mentorship potential caucus members (Output 1.1.1); - Contribute to design of operational modalities of the legislative conservation caucuses (Output 1.1.1); - Provide high-level political/policy advice and guidance to senior policy makers and prospective legislative conservation caucus members and stakeholders to assess, prioritize and offer practical policy and legislative-based options to current conservation challenges based on experiences with other global caucuses (Output 1.1.3); - Share global policy expertise at workshops, dialogues, briefings, and field visits to showcase cutting-edge policy research, and/or best practices (Output 1.2.2); - Provide policy guidance drawing on global experiences in building caucus support toward development/re-drafting of the protected areas implementation/management plans for Barbuda’s Codrington Lagoon National Park, Cabrits National Park (Dominica), Grand Anse MPA (Grenada) and Iyanola National Park (Saint Lucia) (Outputs 2.1.1 to 4); Maintain communications at the highest levels of government in targeted nations to share and gather information and ensure optimal engagement and cooperation. - Event Planning, Preparation, Implementation, and Follow-up - Provide guidance in the design of events and briefings, including content, format and participants - Liaise with project partners to facilitate their involvement in project activities, including subject-matter expertise and resources - Ensure participation of U.S. and donor nation policymakers in project activities as appropriate |  |
| QUALIFICATIONS AND EXPERIENCE: |  |
| The Senior Political Advisor must have extensive experience designing and managing large projects, programs, briefings, and events. Familiarity with working with high-level policymakers internationally is vital. Other required skills include: Education and Training - Fluent in English with exceptional writing and editing skills. - 10+ years of experience in conservation and international relations. - Experience or knowledge of non-profits. Team Leadership Skills - Must work well as a key player in a multi-cultural, inter-disciplinary, multi-lingual, global team. |  |
| TERMS AND CONDITIONS: |  |
| - The position is based in Washington, DC, USA. · - 36-month contract - Part-time consultant - The job will require international travel |  |

| TITLE: | Senior Policy Advisor |
| --- | --- |
| REPORTS TO: | Project Coordinator |
| POSITION DESCRIPTION / MAIN ROLES AND RESPONSIBILITIES: |  |
| Reporting to the Project Coordinator, the Senior Policy Advisor will provide policy analysis and guidance to shape the project activities. Provide Guidance for Activities of Project Staff Provide policy guidance and expertise to project staff as applicable, as requested by the Project Coordinator. - Reach out to and build relationships with diplomatic and political representatives of targeted nations to engage in discussions and education on biodiversity conservation policy. Specific tasks include (under relevant outputs): - Design the legislative conservation caucus model in consultation with national and regional stakeholders (Output 1.1.1); - Develop capacity building tools based on experience-sharing from other global caucuses for local stakeholders, legal drafters legislators, parliamentarians (Output 1.1.2); - Contribute policy and technical inputs to outreach activities for stakeholders to gain commitment and engagement (Output 1.1.3); - Support consultations in development of the conservation priority portfolio with legislative conservation caucus members to identify, assess, and prioritize conservation challenges (Output 1.2.1); - Provide policy and technical guidance to caucus members and stakeholders in various fora including workshops, dialogues, briefings, and field visits showcasing cutting-edge research, and best practices (Output 1.2.2); - Provide expertise to legislative conservation caucus leadership, policymakers, partners, and other stakeholders in development of legislative/policy goals in each country (Output 1.2.3); - Provide legal/technical and policy guidance and assist in preparation as appropriate, proposed legislative and regulatory amendments to support of work legislative drafters, legislative conservation caucus leaders and other partners (Output 1.2.3); - Lead consultations with stakeholders on needs assessment and work planning in upgrade of management plans for Barbuda’s Codrington Lagoon National Park, Cabrits National Park (Dominica), Grand Anse MPA (Grenada) and Iyanola National Park (Saint Lucia) Outputs 2.1.1 to 4; - Lead the inputs to drafting and /or re-drafting of the Protected Areas implementation/management plans for Barbuda’s Codrington Lagoon National Park, Cabrits National Park (Dominica), Grand Anse MPA (Grenada) and Iyanola National Park (Saint Lucia) (Outputs 2.1.1 to 4); Maintain communications at the highest levels of government in targeted nations to share and gather information on biodiversity conservation policy. - Event Planning, Preparation, Implementation, and Follow-up - Provide guidance in the design of events and briefings, including content, format and participants, with respect to biodiversity conservation policy - Conduct educational programs as outlined in the Project Document Policy Analysis and Guidance Oversee and conduct in-depth analysis of biodiversity conservation policy in targeted nations and utilize expertise to shape policymaking discussions. |  |
| QUALIFICATIONS AND EXPERIENCE: |  |
| The Senior Policy Advisor must have extensive experience in international conservation policy analysis and development. Familiarity with building and sustaining caucuses is essential, as is experience working with high-level policymakers in the U.S. and internationally. Other required skills include: Education and Training ● Fluent in English. - 5+ years of experience in conservation and international relations. - Experience or knowledge of non-profits. Team Leadership Skills Must work well as a key player in a multi-cultural, inter-disciplinary, multi-lingual, global team. |  |
| TERMS AND CONDITIONS: |  |
| - The position is based in Washington, DC, USA. · - 36-month contract - Part time - The job will require extensive international travel. |  |

| TITLE: | International Conservation Corps Director |
| --- | --- |
| REPORTS TO: | Project Coordinator |
| POSITION DESCRIPTION / MAIN ROLES AND RESPONSIBILITIES: |  |
| Reporting to the Project Coordinator, the International Conservation Corps Director will oversee the day-to-day project activities of the International Conservation Corps volunteers, with particular emphasis on the following. - Liaise with stakeholders; specific tasks: - At the request of the Senior Political Advisor and/or the Project Coordinator, support the recruitment, engagement and mentorship process for potential members to the legislative conservation caucus (Output 1.1.1); - At the request of the Senior Political Advisor and/or the Project Coordinator, engage in consultations with legislative conservation caucus members to identify, assess, and prioritize current conservation challenges and contribute to modalities for operation of the caucuses (Output 1.2.2); - At the request of the Senior Political Advisor and/or the Project Coordinator, engage with stakeholders from the public and private sectors to support work of the conservation caucuses; - Work with managers of targeted PAs, MPAs, and MMAs to identify challenges to be addressed and develop action plans; - Provide updates on the process to wider networks of legislators around the world to solicit support for efforts under this project and to educate and inspire other legislators to take similar actions (Output 1.2.3); - Assume a lead role in planning and preparation of all International Conservation Corps activities, including regular communication with PA/MPA/MMA staff - Direct the program officers to implement the logistics and other required coordination to complete tasks associated with component 2 of the project. Monitoring and evaluation - Assist Project Coordinator in tracking programs and activities and financial transactions Reporting - Assist Project Coordinator in preparing activity and budget reporting |  |
| QUALIFICATIONS AND EXPERIENCE: |  |
| The International Conservation Corps Director must possess the following skills: Education and Training - Fluent in English; additional language proficiency desirable. - A university degree and 10+ years of experience in protected area management. - Experience or knowledge of non-profits. - International project experience. Team Partnership Skills - Must work well as a member of a multi-cultural, inter-disciplinary, multi-lingual, global team - Proven, professional abilities and technical skills in working with complex multi-cultural operations and teams - Willingness to help with a variety of programs and tasks - Well organized and self-motivated - Excellent organizational, interpersonal, and communication skills - Ability to manage multiple, competing priorities and projects, and meet deadlines ● Strong attention to detail - Proven ability to work with a team, but capable of working independently |  |
| TERMS AND CONDITIONS: |  |
| - The position is based in Washington, DC, USA, but the job will require frequent travel to the Caribbean - 36-month contract - Part Time |  |

| TITLE: | Program Officer (Caribbean) |
| --- | --- |
| REPORTS TO: | Project Coordinator |
| POSITION DESCRIPTION / MAIN ROLES AND RESPONSIBILITIES: |  |
| Reporting to the Project Coordinator, the Program Officer (Caribbean) will execute on-the-ground project activities with the Caribbean region, including the following. - Technical execution of project activities to include: - Ensure representatives of targeted nations are invited and encouraged to participate in CCN briefings and programs; - Assist in planning and preparation of all caucus-building activities, as directed by the Project Coordinator; - Support recruitment and orientation of potential members to the legislative conservation caucus model (Output 1.1.1); - Support creation of legislative conservation caucus roster (Output 1.1.1); - Support registration process with host government and establishment of the local office (Output 1.1.2); - Support identification of core stakeholders (Output 1.1.3); - Support organization and/or lead outreach and meetings and recruitment drives with stakeholders and contribute technical/policy inputs as required (Output 1.1.3); - Support and or/lead organization of consultations dialogues, briefings, and field visits with legislative conservation caucus members (Output 1.2.2); - Disseminate program outputs electronically to broaden the reach of the programs (Output 1.2.2); - Facilitate the work of team members in providing expertise to legislative conservation caucus leadership, policymakers, partners, and other stakeholders in development of legislative/policy goals in each country (Output 1.2.3); - Support development and provision of educational materials relating to the issues addressed by the legislation (Output 1.2.3); - Facilitate engagement of ICC team with local stakeholders in development/re-drafting of the Protected Areas implementation/management plans for Barbuda’s Codrington Lagoon National Park, Cabrits National Park (Dominica), Grand Anse MPA (Grenada) and Iyanola National Park (Saint Lucia) (Outputs 2.1.1 to 4). - Event Planning, Preparation, Implementation, and Follow-up - Liaise with project partners based in the Caribbean to facilitate their involvement in project activities, including subject-matter expertise and resources - Perform activities relating to the scheduling, preparation, implementation, and follow-up for all project briefings and events - Liaise with appropriate GEF/UNEP representatives in the Caribbean during the process of program development and implementation - Information and communication strategy - Provide relevant information to the communications team - Coordinate with technical writer on all printed/web-based products to coordinate writing support, as necessary, and to ensure that products are properly edited/proofread before printing or disseminating electronically - Travel Planning - Assist the with activities related to travel planning for CCN project team members and others as directed by the Project Coordinator Monitoring and evaluation - Provide information and documentation as required to the Project Coordinator to assist in tracking programs and activities and financial transactions Reporting - Assist Project Coordinator in preparing activity and budget reporting |  |
| QUALIFICATIONS AND EXPERIENCE: |  |
| The Program Officer (Caribbean) must possess the following skills: Education and Training - Fluent in English; proficiency in other languages spoken in target countries strongly preferred. - A university degree and 1-2 years of experience. - Experience or knowledge of non-profits a plus. Team Partnership Skills - Must work well as a member of a multi-cultural, inter-disciplinary, multi-lingual, global team - Proven, professional abilities and technical skills in working with complex multi-cultural operations and teams - Willingness to help with a variety of programs and tasks ● Excellent manners - Well organized and self-motivated - Excellent organizational, interpersonal, and communication skills - Ability to manage multiple, competing priorities and projects, and meet deadlines - Strong attention to detail - Proven ability to work with a team, but capable of working independently |  |
| TERMS AND CONDITIONS: |  |
| - The position is based in the Caribbean and may require frequent travel within the region - 36-month contract - ● Full time |  |

| TITLE: | Project Officer - Administration (Washington, DC) |
| --- | --- |
| REPORTS TO: | Project Coordinator |
| POSITION DESCRIPTION / MAIN ROLES AND RESPONSIBILITIES: |  |
| Reporting to the Project Coordinator, the Project Officer will conduct day-to-day project activities, including the following. - Network with embassies and international parliaments - Ensure that representatives of targeted nations are invited and encouraged to participate in CCN briefings and programs - Legislative Conservation Caucus Building: Assist in planning and preparation of all caucus-building activities, as directed by the Project Coordinator - Event Planning, Preparation, Implementation, and Follow-up - Liaise with project partners to facilitate their involvement in project activities, including subject-matter expertise and resources - Perform activities relating to the scheduling, preparation, implementation, and follow-up for all project briefings and events - Liaise with appropriate GEF/UNEP representatives during the process of program development and implementation - Information and communication strategy - Develop updates and relevant information to the communications team - Coordinate with technical writer on all printed/web-based products to coordinate writing support, as necessary, and to ensure that products are properly edited/proofread before printing or disseminating electronically - Travel Planning - Conduct all activities related to travel planning for CCN project team members and others as directed by the Project Coordinator Monitoring and evaluation - Assist Project Coordinator in tracking programs and activities and financial transactions Reporting - Assist Project Coordinator in preparing activity and budget reporting QUALIFICATIONS AND EXPERIENCE: The Project Officer must possess the following skills: Education and Training - Fluent in English; additional language proficiency desirable. - A university degree and 1-2 years of experience. - Experience or knowledge of non-profits a plus. Team Partnership Skills - Must work well as a member of a multi-cultural, inter-disciplinary, multi-lingual, global team; - Proven, professional abilities and technical skills in working with complex multi-cultural operations and teams. - Willingness to help with a variety of programs and tasks ● Excellent manners - Well organized and self-motivated - Excellent organizational, interpersonal, and communication skills - Ability to manage multiple, competing priorities and projects, and meet deadlines ● Strong attention to detail - Ability to be polite and assertive simultaneously on the phone - Proven ability to work with a team, but capable of working independently TERMS AND CONDITIONS: - The position is based in Washington, DC, USA, but the job may require frequent travel to the Caribbean - 36-month contract - Part time |  |

| TITLE: | Communications Officer |
| --- | --- |
| REPORTS TO: | Project Coordinator |
| POSITION DESCRIPTION / MAIN ROLES AND RESPONSIBILITIES: Reporting to the Project Coordinator, the Communications Officer (CO) will be the day-to-day coordinator of all project communication efforts. Establish and Maintain the project website - Maintain and regularly update the CCN website. This might also entail maintaining direct contact with staff from the legislative conservation caucuses to encourage contributions and update the website on a regular basis; - Website management will entail the set-up and operation of news-alerts, internet forum and discussion groups, intranet, e-newsletter, etc. (with news on, e.g., training packages, events and programs, and other key project outputs), etc. as outlined in the project document; - Develop and maintain lists for e-distribution. Contribute to the development of project communication materials & inputs The CO will be responsible for all communications materials to be developed by the project, and will work very closely with the Project Coordinator, Program Officers, and Technical Writer at all stages including: planning, content development, lay-out design and dissemination. Some communication materials and activities may include: - Q&A on the project; - List of relevant upcoming meetings/events to enable the project to have its own events at the margins; - Other inputs for semi-annual consolidated progress report with respect to the communications component of the project, as required; - Newsletters; - Provide comments and inputs to all CCN-related press releases developed by other partners in relation to the formation of the legislative conservation Caucuses; - Produce public relations materials, edit and layout reports and other promotional material, and assist with planning, publicizing, and carrying out special events; - Act as Communication Focal Point for the project including management of press and other media inquiries; - Learn about ICCF and CCN guidelines for information management; - Maintain contacts with key information units at UNEP and GEF secretariat; - Guide development of video and other material; - Produce and regularly update promotional materials e.g., reports, brochures, folders, etc. Other - Develop messaging for the project with the project team to ensure that all project materials have consistent messaging and branding; - Identify key audiences for the project and always ensure that material developed for the different audience group targets their specific needs; - Attend conventions, seminars, workshops to present the project as and when required; - Approach NGOs about distribution of project material, newsletters and stories to their mailing lists; - Compile press and general web coverage overviews; - Collate project-related press and general website coverage for inclusion in project consolidated reports. GEF and UNEP Branding The principles of the GEF Branding Strategy and UNEP Communications Strategy will be integrated into all materials developed through and by the project. The Communications Officer will ensure that material developed through the project follows the guidance laid out in the branding and communications strategies of the GEF and UNEP. |  |
| QUALIFICATIONS AND EXPERIENCE: The Communications Officer must possess strong communications experience and be able to demonstrate the following key competencies: Education and Training - Fluent in English with exceptional writing and editing skills; Additional language proficiency desirable. - A university degree and 2+ years of experience in communications. - Experience in creating newsletters, print and on-line and other communication materials. Relevant experience and high-level competence in the use of information technology, including developing and maintaining websites and web-based systems, plus some experience writing for websites. - Experience or knowledge of non-profits a plus. - Highly developed writing skills and demonstrated competence in copywriting and media release writing. Team Membership Skills - Must work well as a member of a multi-cultural, inter-disciplinary, multi-lingual, global team; - Proven, professional abilities and technical skills in managing complex multi-cultural operations and teams. Project Management Skills - Experience in working with international project teams; - Strong project management skills to plan, organize, coordinate and control the implementation of several projects simultaneously; - Demonstrated project management experience and ability to manage deadlines. Communication and Interpersonal Skills - The CO will be required to represent the project professionally both within the organization and to external stakeholders and audiences; - Excellent verbal and written communication skills to effectively present strategies. - Excellent interpersonal skills and ability to communicate with stakeholders from varying social contexts. |  |
| TERMS AND CONDITIONS: |  |
| - The position is based in Washington, DC, USA. · - 36-month contract - Part time |  |

| TITLE: | Technical Writer |
| --- | --- |
| REPORTS TO: | Project Coordinator |
| POSITION DESCRIPTION / MAIN ROLES AND RESPONSIBILITIES: |  |
| Reporting to the Project Coordinator, the Technical Writer will be responsible for oversight of all project reporting and written communications. Contribute to the development of written project communication materials The Technical Writer will contribute to the development of all communications materials produced by the project, and will work very closely with the Project Coordinator, Program Officers, and Communications Officer at all stages including: planning, research, content development, writing, and proofreading. Some communication materials and activities may include: - Newsletters; - CCN-related press releases developed by other partners in relation to the formation of the Legislative Conservation Caucuses; - Video scripting and other material content; - Promotional/public relations materials including reports, brochures, folders, etc.; - Project reports and other deliverables. Ensure the quality of all written materials The Technical Writer will be responsible for review of all communications and written materials developed by the project. This will include the following tasks: - Ensure compliance with ICCF and CCN guidelines for written materials and information management; - Ensure compliance with GEF/UNEP guidelines for written materials; - Proofread all written materials for spelling, grammar, style, and consistency. Other - Develop messaging for the project with the project team to ensure that all project materials have consistent messaging and branding. GEF and UNEP Branding The principles of the GEF Branding Strategy and UNEP Communications Strategy will be integrated into all materials developed through and by the project. The Technical Writer will ensure that material developed through the project follows the guidance laid out in the branding and communications strategies of the GEF and UNEP. |  |
| QUALIFICATIONS AND EXPERIENCE: |  |
| The Technical Writer must possess strong writing and communications experience and be able to demonstrate the following key competencies: Education and Training - Fluent in English with exceptional writing, proofreading, and editing skills; additional language proficiency desirable. - A university degree and 5+ years of experience in writing and communications. - Relevant experience and high-level proficiency in creating print and on-line communication materials. - Experience in the use of information technology, including developing and maintaining websites and web-based systems, plus experience writing for websites. - Experience or knowledge of non-profits a plus. - Highly developed writing skills and demonstrated competence in copywriting and media release writing. Team Membership Skills - Must work well as a member of a multi-cultural, inter-disciplinary, multi-lingual, global team; - Proven, professional abilities and technical skills in managing complex multi-cultural operations and teams. Project Management Skills - Experience in working with international project teams; - Strong project management skills to plan, organize, coordinate and control the implementation of several projects simultaneously; - Demonstrated project management experience and ability to manage deadlines. Communication and Interpersonal Skills - Excellent verbal and written communication skills. - Ability to communicate effectively with stakeholders from varying social contexts. |  |
| TERMS AND CONDITIONS: |  |
| - The position is based in Washington, DC, USA. · - 36-month contract - Part time |  |

## Appendix 12: Co-financing commitment letters from project partners

Appended as a PDF.

## Appendix 13: Draft Procurement Plan

| UNEP Budget Line |  | List of Goods and Services required | Budget | Year {Note 1} | Brief description of anticipated procurement process {Note 2} |
| --- | --- | --- | --- | --- | --- |
| 10 | Personnel Component |  |  |  |  |
| 1100 | Project Personnel |  |  |  |  |
| 1101 | Project Coordinator |  | 140,000 | Y1 | Hiring process to be procured from existing CCN Staff who have demonstrated the expertise to carry out roles and responsibilities |
| 1102 | Senior Political Adviser |  | 180,000 | Y1 | Hiring process to be procured from existing CCN Staff who have demonstrated the expertise to carry out roles and responsibilities |
| 1103 | Program Officer (in country) |  | 120,000 | Y1 | Hiring to be conducted in the first 3-4 months of project |
| 1104 | Project Officer - Administration – DC based |  | 55,233 | Y1 | Hiring process to be procured from existing CCN Staff who have demonstrated the expertise to carry out roles and responsibilities |
| 1105 | Conservation Corps Director |  | 45,000 | Y1 | Hiring process to be procured from existing CCN Staff who have demonstrated the expertise to carry out roles and responsibilities |
| 1106 | Senior Policy Adviser |  | 135,000 | Y1 | Hiring process to be procured from existing CCN Staff who have demonstrated the expertise to carry out roles and responsibilities |
| 1107 | Communications Officer |  | 90,000 | Y1 | Hiring process to be procured from existing CCN Staff who have demonstrated the expertise to carry out roles and responsibilities |
| 1108 | Technical Writer |  | 60,000 | Y1 | Hiring process to be procured from existing CCN Staff who have demonstrated the expertise to carry out roles and responsibilities |
| 1200 | Consultants |  |  |  |  |
| 1201 | none |  |  |  |  |
| 1601 | Staff Travel and Transport | Flights, local transportation (taxis, car service), hotel, M&IE | 170,000 | Y1, Y2, Y3 as needed | Travel logistics to be determined by programming needs. Prices to be determined for best rates with reasonable travel length. Costs to be submitted and approved by Project Coordinator |
| 2100 | Sub-contracts (MOUs/LOAs for cooperating agencies) |  |  |  |  |
| 2201 | none |  |  |  |  |
| 2201 |  |  |  |  |  |
| 2300 | Sub-contracts to private firms |  |  |  |  |
| 2301 | none |  |  |  |  |
| 2301 |  |  |  |  |  |
| 30 | Training Component |  |  |  |  |
| 3200 | Group Training |  |  |  |  |
| 3201 | Training |  | 85,000 | Y1, Y2, Y3 as needed | Programmatic expenses related to meetings to develop the stakeholder and policymaker network. Budget to be monitored and approved by the project coordinator. Primarily to be used by the Project Officers and Senior advisors for meetings and costs associated with support of the legislative conservation caucuses. |
| 3301 | Meetings/Conferences |  | 573,467 | Y1, Y2, Y3 as needed | Programmatic Expenses. Includes Briefing and forum activities with legislative conservation caucuses Includes event costs including venue, meals and related travel expenses for caucus members and other stakeholders to travel and attend the relevant activities |
| 4200 | Non-expendable equipment |  |  |  |  |
| 4201 | none |  |  |  |  |
| 4202 |  |  |  |  |  |
| 50 | Miscellaneous Component |  |  |  |  |
| 5201 | Publications, Translations, Dissemination and reporting costs |  | 38,000 | Y1, Y2, Y3 as needed | Costs associated to publishing and producing documents for programming requirements. To be approved by the Project Coordinator |
| 5202 | Audit Reports |  | 20,000 | Y1, Y2, Y3 | Costs associated to audit to be conducted. Will use similar Auditor to previous projects which has this established rate |
| 5301 | Communications (Tel, fax, email, etc.) |  | 36,000 | Y1, Y2, Y3 as needed | Costs for telecommunications, electronic communication services, long-distance calling to be billed directly for programmatic costs |
| 5302 | Others |  | 18,000 | Y1, Y2, Y3 as needed | Contingency costs for implementing programming. |
| 5303 | Tech Support and Evaluation |  | 65,000 | Y3 | Costs associated to monitoring and evaluation and reporting |
|  | GRAND TOTAL |  | 1,866,700 |  |  |

Note 1 - Year when goods/services will be procured

Note 2 - Based on your organisation’s procurement procedures, and in compliance with UNEP rules and procedures, briefly explain how the service provider/consultant/vendor will be selected

Key Procurement Requirements:

The following areas have been identified by the CCN as the main procurement requirements. All other activities will be internally procured.

·         Project Staff

·         Direct program costs, including travel, program materials, venues, meals, accommodations, etc.

Procurement Plan:

Project Personnel:

Upon confirmation of project approval, advertisements will be placed in appropriate media seeking applications for those positions not filled by current CCN staff or contractors.

In the recruitment of all senior project personnel, consultants and contractors, a selection panel consisting of representatives from CCN and UNEP shall conduct the evaluation of the candidates, and based on the recommendations of the panel, CCN shall issue contracts, the terms and conditions of which shall be cleared by the panel. Draft terms of reference (subject to refinement during the inception phase) for the respective senior personnel to be recruited are as set out in Appendix 11.

Any personnel changes during the course of the project will be determined by the Project Coordinator in consultation with the Senior Advisor and UNEP.

Direct Program Costs

“Direct program costs” refers to all direct expenses incurred with the planning, implementation, and follow-up of project programs, briefings, and events. These costs will include necessary travel, program materials, venues, meals, accommodations, printing expenses, etc. CCN is committed to ensuring that the most cost-effective solutions are sought for its activities that are appropriate to the participants and the event requirements.

- Procurements of goods and services which exceed the threshold of $5,000 must be made on a competitive basis, and a written justification must be included in the file in cases where the lowest bid is not accepted.

- Sole source procurements, meaning procurements in excess of the small purchase threshold of $5,000 without a competitive process, must be justified in writing and the documentation maintained on file.

- Sole source procurements for transactions in excess of $50,000 require the prior approval of UNEP.

- Staff shall not participate in the selection, award, or administration of a procurement action if a real or apparent conflict of interest would be involved.

## Appendix 14: Management Effectiveness Tracking Tools

Appended as an excel file.

## Appendix 15: UNEP Environmental, Social and Economic Review Note (ESERN)

| I. | Project |
| --- | --- |

| Identification | GEF Project ID: 9979 |
| --- | --- |
| Project Title | Advancing Conservation in the Eastern Caribbean |
| Managing Division |  |
| Type/Location | Regional |
| Region | Latin America/Caribbean |
| List Countries | Antigua and Barbuda, Dominica, Grenada, St. Lucia |
| Project Description | To support biodiversity conservation in four Eastern Caribbean countries (Antigua and Barbuda, Dominica, Grenada, and St. Lucia) through enhanced political will and capacity building for improved management of marine protected areas (MPAs), marine management areas (MMAs) and protected areas (PAs). |
| Estimated duration of project: | 36 months |
| Estimated cost of the project: | GEF Grant: 1,866,700 Co-finance: 2,185,000 |

Environmental Social and Economic Screening Determination

|  | A. Summary of the Safeguard Risks Triggered |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Safeguard Standard Triggered by the Project | Impact of Risk (1-5) | Probability of Risk (1-5) | Significance of risk (L,M,H) |  |
|  | SS 1: Biodiversity, natural habitat and Sustainable Management of Living Resources | 2 | 1 | L |  |
|  | SS 2: Resource Efficiency, Pollution Prevention and Management of Chemicals and Wastes | 1 | 1 | L |  |
|  | SS 3: Safety of Dams | 1 | 1 | L |  |

1 Refer to UNEP Environment, Social and Economic Sustainability (ESES): Implementation Guidance Note to assign values to the Impact of Risk and the Probability of Risk to determine the overall significance of Risk (Low, Moderate or High).

|  | SS 4: Involuntary resettlement | 3 | 1 | L |  |
| --- | --- | --- | --- | --- | --- |
|  | SS 5: Indigenous peoples | 1 | 1 | L |  |
|  | SS 6: Labor and working conditions | 1 | 1 | L |  |
|  | SS 7: Cultural Heritage | 1 | 1 | L |  |
|  | SS 8: Gender equity | 1 | 1 | L |  |
|  | SS 9: Economic Sustainability | 1 | 1 | L |  |
|  | Additional Safeguard questions for projects seeking GCF-funding (Section IV) | NA | NA | NA |  |
|  | - ESE Screening Decision2 (Refer to the UNEP ESES Framework (Chapter 2) and the UNEP’s ESES Guidelines.) Low risk; x; Moderate risk; High risk; Additional information required. - Development of ESE Review Note and Screening Decision: Prepared by: Name: Olivia Blanchette Date: 24 Mar 2019 Safeguard Advisor: Name: Yunae Yi Date: 09 Aug. 2019 Project Manager: Name: Christopher Cox Date: 09 Aug 2019 |  |
| - Recommended further action from the Safeguard Advisor: The project seems to be in the low risk Category. The project is committed to respect local land tenure rights in the project countries. The project committed to develop an implementation plan of the existing land management plans of the countries. We recommend close monitoring and communication of the related matters with the local communities throughout the project implementation. |  |  |  |  |  |

2

Low risk: Negative impacts negligible: no further study or impact management required.

Moderate risk: Potential negative impacts, but less significant; few if any impacts irreversible; impact amenable to management using standard mitigation measures; limited environmental or social analysis may be required to develop an ESEMP. Straightforward application of good practice may be sufficient without additional study.

High risk: Potential for significant negative impacts, possibly irreversible, ESEA including a full impact assessment may be required, followed by an effective safeguard management plan.

ESES Principle and Safeguard checklist

(Section III and IV should be retained in UNEP)

Precautionary Approach

The project will take precautionary measures even if some cause and effect relationships are not fully established scientifically and there is risk of causing harm to the people or to the environment.

Human Rights Principle

The project will make an effort to include any potentially affected stakeholders, in particular vulnerable and marginalized groups; from the decision making process that may affect them.

The project will respond to any significant concerns or disputes raised during the stakeholder engagement process.

The project will make an effort to avoid inequitable or discriminatory negative impacts on the quality of and access to resources or basic services, on affected populations, particularly people living in poverty or marginalized or excluded individuals or groups.3

| Screening checklist | Y/N/ Maybe | Comment |
| --- | --- | --- |
| Safeguard Standard 1: Biodiversity, natural habitat and Sustainable Management of Living Resources |  |  |
| Will the proposed project support directly or indirectly any activities that significantly convert or degrade biodiversity and habitat including modified habitat, natural habitat and critical natural habitat? | N | Not anticipated. On the contrary, project activities are designed to improve habitats and ecosystems. |
| Will the proposed project likely convert or degrade habitats that are legally protected? | N | Not anticipated. On the contrary, project activities are designed to improve legally protected habitats. |
| Will the proposed project likely convert or degrade habitats that are officially proposed for protection? (e.g.; National Park, Nature Conservancy, | N | Not anticipated. On the contrary, project activities are designed to improve habitats officially proposed for protection. |

3 Prohibited grounds of discrimination include race, ethnicity, gender, age, language, disability, sexual orientation, religion, political or other opinion, national or social or geographical origin, property, birth or other status including as an indigenous person or as a member of a minority. References to “women and men” or similar is understood to include women and men, boys and girls, and other groups discriminated against based on their gender identities, such as transgender people and transsexuals.

| Screening checklist | Y/N/ Maybe | Comment |
| --- | --- | --- |
| Indigenous Community Conserved Area, (ICCA); etc.) |  |  |
| Will the proposed project likely convert or degrade habitats that are identified by authoritative sources for their high conservation and biodiversity value? | N | Not anticipated. On the contrary, the project activities are designed to improve habitats identified as having high conservation/biodiversity value. |
| Will the proposed project likely convert or degrade habitats that are recognized- including by authoritative sources and /or the national and local government entity, as protected and conserved by traditional local communities? | N | Not anticipated. |
| Will the proposed project approach possibly not be legally permitted or inconsistent with any officially recognized management plans for the area? | N | Not anticipated. |
| Will the proposed project activities result in soils deterioration and land degradation? | N | On the contrary, the project activities are designed to improve biodiversity and ecosystems |
| Will the proposed project interventions cause any changes to the quality or quantity of water in rivers, ponds, lakes or other wetlands? | N | Project activities are designed to contribute to conservation of ecosystems; therefore, any impacts will be positive. |
| Will the proposed project possibly introduce or utilize any invasive alien species of flora and fauna, whether accidental or intentional? | N | Not anticipated. |
| Safeguard Standard 2: Resource Efficiency, Pollution Prevention and Management of Chemicals and Wastes |  |  |
| Will the proposed project likely result in the significant release of pollutants to air, water or soil? | N | Not anticipated. |
| Will the proposed project likely consume or cause significant consumption of water, energy or other resources through its own footprint or through the boundary of influence of the activity? | N | Not anticipated. |
| Will the proposed project likely cause significant generation of Green House Gas (GHG) emissions during and/or after the project? | N | Not anticipated. |
| Will the proposed project likely generate wastes, including hazardous waste that cannot be reused, recycled or disposed in an environmentally sound and safe manner? | N | Not anticipated. |
| Will the proposed project use, cause the use of, or manage the use of, storage and disposal of hazardous chemicals, including pesticides? | N | Not anticipated. |
| Will the proposed project involve the manufacturing, trade, release and/or use of hazardous materials subject to international action bans or phase-outs, such as DDT, PCBs and other chemicals listed in international conventions such as the Stockholm Convention on Persistent Organic Pollutants or the Montreal Protocol? | N | Not anticipated. |
| Screening checklist | Y/N/ Maybe | Comment |
| Will the proposed project require the procurement of chemical pesticides that is not a component of integrated pest management (IPM) or integrated vector management (IVM) approaches? | N | Not anticipated. |
| Will the proposed project require inclusion of chemical pesticides that are included in IPM or IVM but high in human toxicity? | N | Not anticipated. |
| Will the proposed project have difficulty in abiding to FAO’s International Code of Conduct in terms of handling, storage, application and disposal of pesticides? | N | Not anticipated. |
| Will the proposed project potentially expose the public to hazardous materials and substances and pose potentially serious risk to human health and the environment? | N | Not anticipated. |
| Safeguard Standard 3: Safety of Dams |  |  |
| Will the proposed project involve constructing a new dam(s)? | N | Not anticipated. |
| Will the proposed project involve rehabilitating an existing dam(s)? | N | Not anticipated. |
| Will the proposed project activities involve dam safety operations? | N | Not anticipated. |
| Safeguard Standard 4: Involuntary resettlement |  |  |
| Will the proposed project likely involve full or partial physical displacement or relocation of people? | N | Not anticipated. |
| Will the proposed project involve involuntary restrictions on land use that deny a community the use of resources to which they have traditional or recognizable use rights? | Maybe | As a consequence of improved decision-making on implementation of NBSAPs to improve biodiversity and ecosystems. |

| Screening checklist | Y/N/ Maybe | Comment |
| --- | --- | --- |
| Will the proposed project likely cause restrictions on access to land or use of resources that are sources of livelihood? | Maybe | As a consequence of improved decision-making on implementation of NBSAPs to improve biodiversity and ecosystems. |
| Will the proposed project likely cause or involve temporary/permanent loss of land? | N | Not anticipated. |
| Will the proposed project likely cause or involve economic displacements affecting their crops, businesses, income generation sources and assets? | N | Not anticipated |
| Will the proposed project likely cause or involve forced eviction? | N | Not anticipated. |
| Will the proposed project likely affect land tenure arrangements, including communal and/or customary/traditional land tenure patterns negatively? | N | Not anticipated. |
| Safeguard Standard 5: Indigenous peoples |  |  |
| Will indigenous peoples be present in the proposed project area or area of influence? | N | Not anticipated. |
| Will the proposed project be located on lands and territories claimed by indigenous peoples? | N | Not anticipated. |
| Will the proposed project likely affect livelihoods of indigenous peoples negatively through affecting the rights, lands and territories claimed by them? | N | Not anticipated. |
| Will the proposed project involve the utilization and/or commercial development of natural resources on lands and territories claimed by indigenous peoples? | N | Not anticipated. |
| Will the project negatively affect the development priorities of indigenous peoples defined by them? | N | Not anticipated. |
| Will the project potentially affect the traditional livelihoods, physical and cultural survival of indigenous peoples? | N | Not anticipated. |
| Will the project potentially affect the Cultural Heritage of indigenous peoples, including through the commercialization or use of their traditional knowledge and practices? | N | Not anticipated. |
| Safeguard Standard 6: Labor and working conditions |  |  |
| Will the proposed project involve the use of forced labor and child labor? | N | Not anticipated. |
| Will the proposed project cause the increase of local or regional un- employment? | N | Not anticipated. |

| Screening checklist | Y/N/ Maybe | Comment |
| --- | --- | --- |
| Safeguard Standard 7: Cultural Heritage |  |  |
| Will the proposed project potentially have negative impact on objects with historical, cultural, artistic, traditional or religious values and archeological sites that are internationally recognized or legally protected? | N | Not anticipated. |
| Will the proposed project rely on or profit from tangible cultural heritage (e.g., tourism)? | N | Not anticipated. |
| Will the proposed project involve land clearing or excavation with the possibility of encountering previously undetected tangible cultural heritage? | N | Not anticipated. |
| Will the proposed project involve in land clearing or excavation? | N | Not anticipated. |
| Safeguard Standard 8: Gender equity |  |  |
| Will the proposed project likely have inequitable negative impacts on gender equality and/or the situation of women and girls? | N | Not anticipated. |
| Will the proposed project potentially discriminate against women or other groups based on gender, especially regarding participation in the design and implementation or access to opportunities and benefits? | N | No. On the contrary project activities are designed to enhance the role of women in natural resources management and the sharing of benefits from conservation |
| Will the proposed project have impacts that could negatively affect women’s and men’s ability to use, develop and protect natural resources, taking into account different roles and positions of women and men in accessing environmental goods and services? | N | Not anticipated. |
| Safeguard Standard 9: Economic Sustainability |  |  |
| Will the proposed project likely bring immediate or short-term net gain to the local communities or countries at the risk of generating long-term economic burden (e.g., agriculture for food vs. biofuel; mangrove vs. co+mmercial shrimp farm in terms of fishing, forest products and protection, etc.)? | N | Not anticipated. |
| Will the proposed project likely bring unequal economic benefits to a limited subset of the target group? | N | Not anticipated. |

Additional Safeguard Questions for Projects seeking GCF-funding

| Community Health, Safety, and Security |  |  |  |
| --- | --- | --- | --- |
| Will there be potential risks and negative impacts to the health and safety of the Affected Communities during the project life-cycle? | N |  |  |
| Will the proposed project involve design, construction, operation and decommissioning of the structural elements such as new buildings or structures? | N |  |  |
| Will the proposed project involve constructing new buildings or structures that will be accessed by public? | N |  |  |
| Will the proposed project possibly cause direct or indirect health-related risks and impacts to the Affected Communities due to the diminution or degradation of natural resources, and ecosystem services? | N |  |  |
| Will the proposed project activities potentially cause community exposure to health issues such as water- born, water-based, water-related, vector-borne diseases, and communicable diseases? | N |  |  |
| In case of an emergency event, will the project team, including partners, have the capacity to respond together with relevant local and national authorities? | N |  |  |
| Will the proposed project need to retain workers to provide security to safeguard its personnel and property? | N |  |  |
| Labor and Supply Chain |  |  |  |
| Will UNEP or the implementing/executing partner(s) involve suppliers of goods and services who may have high risk of significant safety issues related to their own workers? | N |  |  |

Appendix 16: Theory of Change

## Appendix 17:	Endorsement letters of GEF National Focal Points

Appended as PDF

## Appendix 18: Project Taxonomy

Appended as PDF

## Appendix 19: Core Indicators

Appended as PDF

Appendix 20: Validation Workshop Report

Appended as PDF

Critical Ecosystem Partnership Fund. “Caribbean Islands Biodiversity Hotspot Ecosystem Profile Summary.” https://www.cepf.net/sites/default/files/caribbean_ep_summary.pdf

For further background, see The Global Review of Protected Area Budgets and Staff produced by WCMC (https://www.cbd.int/financial/expenditure/g-spendingglobal-wcmc.pdf).

Convention on Biological Diversity (CBD) “Action Plan for Implementing the Programme of Work for Protected Areas of the Convention on Biological Diversity: Antigua and Barbuda” April 2012. https://www.cbd.int/doc/world/ag/ag-nbsap-powpa-en.pdf

Gore-Francis, Janil. “Antigua and Barbuda: SIDS 2014 Prepatory Progress Report (July 2013)” United Nations Sustainable Development https://sustainabledevelopment.un.org/content/documents/1049240Antigua%20and%20Barbuda%20final.pdf

IUCN, Protected Area Categories, website. https://www.iucn.org/theme/protected-areas/about/protected-areas-categories/category-vi-protected-area-sustainable-use-natural-resources.

Codrington Lagoon National Park Management Plan 2009-2019

Dominica National Biodiversity Strategy and Action Plan (NBSAP) 2014-2020 December 2014. Prepared by Ministry of Environment, Natural Resources, Physical Planning and Fisheries. https://sustainabledevelopment.un.org/content/documents/1446dominica.pdf

Ecoengineering Caribbean Limited, “Cabrits National Park (Marine Component) Site Report, Dominica: report No. 11/2007”. Environmental and Socio-economic Studies for OPAAL Demonstration Sites.  July, 2007. http://parkscaribbean.net/wp-content/uploads/2013/11/Cabrits%20National%20Park%20(Marine)-Environmental%20and%20Socio-economic%20Study%20(2007).pdf

United Nations Educational Scientific and Cultural Organization (UNESCO). “Fort Shirley” 5/02/2015. web. https://whc.unesco.org/en/tentativelists/6020/

Dominica News Online, January 14th, 2013. Web. http://dominicanewsonline.com/news/homepage/news/tourism-publicity/dominica-the-whale-watching-capital-of-the-caribbean/

Turner, Mel. “Grenada Protected Area System Plan Part I: Identification and Designation of Protected Areas.” July 2009. Pg. 13

Turner, Mel. “Grenada Protected Area System Plan Part I: Identification and Designation of Protected Areas.” July 2009. Pg. 21.

Grenada Declaration at Eighth Meeting of the Conference of Parties of the Convention on Biological Diversity (COP 8) 2006.

Turner, Mel. “Grenada Protected Area System Plan Part II: Legislation, Institutional Organization, Management Planning, Financing, Capacity Development and Training.” July 2009. Pg. 9 https://www.oas.org/dsd/IABIN/Component1/ReefFix/Grenada%20Book/SystemsPlan2/Grenada%20IFT%20Supportdoc.pdf

Turner, Mel. “Grenada Protected Area System Plan Part II: Legislation, Institutional Organization, Management Planning, Financing, Capacity Development and Training.” July 2009. Pg. 10 https://www.oas.org/dsd/IABIN/Component1/ReefFix/Grenada%20Book/SystemsPlan2/Grenada%20IFT%20Supportdoc.pdf

Constantine, Sherry, The Nature Conservancy, “Grenada Launches its newest marine protected area- Grand Anse” Caribbean Biodiversity Fund, https://www.caribbeanbiodiversityfund.org/en/cbf-news-events/news/56-grenada-launches-its-newest-marine-protected-area-grand-anse .

Haffey, David. “A Systems Plan for Protected Areas in St. Lucia” OECS Protected Areas and Associated Livelihoods Project. Appendix 3. December 2009. https://www.cbd.int/doc/pa/tools/A%20Systems%20Plan%20for%20Protected%20Areas%20in%20Saint%20Lucia.pdf

Haffey, David. “A Systems Plan for Protected Areas in St. Lucia” OECS Protected Areas and Associated Livelihoods Project. Appendix 3. December 2009. https://www.cbd.int/doc/pa/tools/A%20Systems%20Plan%20for%20Protected%20Areas%20in%20Saint%20Lucia.pdf

Organization of Eastern Caribbean States (OECS) Secretariat Environment and Sustainable Development (ESDU) Protecting the Eastern Caribbean Region's Biodiversity Project (PERB). "Biodiversity Inventory and Status Assessment Report for the proposed Wallings Forest Protected Area (Antigua) and the Codrington Lagoon National Park (Barbuda)". November 2008. http://www.irf.org/wp-content/uploads/2015/10/Wallings-CodringtonBiodiversitySurvey_Antigua_2008.pdf

Codrington Lagoon National Park Management Plan 2009-2019

Dr. Janil Gore Francis, “CBD, Fourth National Report Antigua and Barbuda”, March 2010. https://www.cbd.int/doc/world/ag/ag-nr-04-en.pdf

Dominica’s 5th National Biodiversity Report to the Convention on Biological Diversity (CBD) 2014. https://www.cbd.int/doc/world/dm/dm-nr-05-en.pdf

Ecoengineering Caribbean Limited, “Cabrits National Park (Marine Component) Site Report, Dominica: report No. 11/2007”. Environmental and Socio-economic Studies for OPAAL Demonstration Sites.  July, 2007. http://parkscaribbean.net/wp-content/uploads/2013/11/Cabrits%20National%20Park%20(Marine)-Environmental%20and%20Socio-economic%20Study%20(2007).pdf

Convention on Biological Diversity (CBD) Country Profile Grenada. Webpage Accessed 1/4/2019.  https://www.cbd.int/countries/profile/default.shtml?country=gd

Turner, Mel. “Grenada Protected Area System Plan Part I: Identification and Designation of Protected Areas.” July 2009. Pg. 13.

Commonwealth Secretariat Economic and Legal Section. “OECS Development of an Eastern Caribbean Regional Ocean Policy Discussion Document.” August 2012. Pg. 12 https://www.oecs.org/ogu-resources/oecs-development-of-an-eastern-caribbean-regional-ocean-policy/viewdocument.

National Biodiversity Strategy and Action Plan (NBSAP), Antigua and Barbuda, p.13

National Biodiversity Strategy and Action Plan (NBSAP), Antigua and Barbuda, p.13

National Biodiversity Strategy and Action Plan (NBSAP), Antigua and Barbuda, p. 42

Codrington Lagoon National Park Management Plan 2009-2019

Ruttenberg, B., Caselle, J. E., Estep, A. J., Johnson, A. E., Marhaver, K. L., Richter, L. J., … Cannon, A. (2018). Ecological assessment of the marine ecosystems of Barbuda, West Indies: Using rapid scientific assessment to inform ocean zoning and fisheries management. PLoS ONE, 13(1), 1–20. https://doi-org.proxy1.library.jhu.edu/10.1371/journal.pone.0189355

Ruttenberg, B., Caselle, J. E., Estep, A. J., Johnson, A. E., Marhaver, K. L., Richter, L. J., … Cannon, A. (2018). Ecological assessment of the marine ecosystems of Barbuda, West Indies: Using rapid scientific assessment to inform ocean zoning and fisheries management. PLoS ONE, 13(1), 1–20. https://doi-org.proxy1.library.jhu.edu/10.1371/journal.pone.0189355

Porder D. Read, Mengerink, Kathryn.  "Sustainable Fisheries & Coastal Zoning in Barbuda: Legal & Institutional Assessment of Authorities and Approaches." Environmental Law Institute. May 2014.

National Biodiversity Strategy and Action Plan (NBSAP), Antigua and Barbuda, p. 14

National Biodiversity Strategy and Action Plan (NBSAP), Antigua and Barbuda, p. 35, description on p.43

Organization of Eastern Caribbean States (OECS) Secretariat Environment and Sustainable Development (ESDU) Protecting the Eastern Caribbean Region's Biodiversity Project (PERB). "Biodiversity Inventory and Status Assessment Report for the proposed Wallings Forest Protected Area (Antigua) and the Codrington Lagoon National Park (Barbuda)". November 2008.  pp. 68 http://www.irf.org/wp-content/uploads/2015/10/Wallings-CodringtonBiodiversitySurvey_Antigua_2008.pdf

National Biodiversity Strategy and Action Plan (NBSAP), Antigua and Barbuda, p. 10

National Biodiversity Strategy and Action Plan (NBSAP), Antigua and Barbuda, p. 13

National Biodiversity Strategy and Action Plan (NBSAP), Antigua and Barbuda, p. 10

Dr. Janil Gore Francis, “CBD, Fourth National Report Antigua and Barbuda”, March 2010. https://www.cbd.int/doc/world/ag/ag-nr-04-en.pdf

Environmental Law Institute, “Sustainable Fisheries and Coastal Zoning in Barbuda” May 2014. http://eli-ocean.org/wp-content/blogs.dir/7/files/Barbuda-BHI-Legal-Framework-Report-ELI.pdf

The Nature Conservancy. Coral Reef Report Card: Dominica. 2016 https://www.issuelab.org/resource/commonwealth-of-dominica-coral-reef-report-card-2016.html

Dominica National Biodiversity Strategy and Action Plan (NBSAP) 2014-2020 December 2014. Prepared by Ministry of Environment, Natural Resources, Physical Planning and Fisheries. https://sustainabledevelopment.un.org/content/documents/1446dominica.pdf

Dominica National Biodiversity Strategy and Action Plan (NBSAP) 2014-2020 December 2014. Prepared by Ministry of Environment, Natural Resources, Physical Planning and Fisheries. https://sustainabledevelopment.un.org/content/documents/1446dominica.pdf

Dominica National Biodiversity Strategy and Action Plan (NBSAP) 2014-2020 December 2014. Prepared by Ministry of Environment, Natural Resources, Physical Planning and Fisheries. p. 28 https://sustainabledevelopment.un.org/content/documents/1446dominica.pdf

Esprit, Agnes “Socio-Economic Monitoring at The Cabrits National Park (Marine Component), Commonwealth of Dominica” Climate resilient eastern caribbean marine managed areas network (ecmman) project. 2018. http://www.socmon.org/upload/documents/ECMMAN%20SocMon%20Cabrits%20Report_FINAL_27%20Feb%202018.pdf

Dominica National Biodiversity Strategy and Action Plan (NBSAP) 2014-2020 December 2014. Prepared by Ministry of Environment, Natural Resources, Physical Planning and Fisheries. p. 18 https://sustainabledevelopment.un.org/content/documents/1446dominica.pdf p. 38

Dominica National Biodiversity Strategy and Action Plan (NBSAP) 2014-2020 December 2014. Prepared by Ministry of Environment, Natural Resources, Physical Planning and Fisheries. https://sustainabledevelopment.un.org/content/documents/1446dominica.pdf

Dominica National Biodiversity Strategy and Action Plan (NBSAP) 2014-2020 December 2014. Prepared by Ministry of Environment, Natural Resources, Physical Planning and Fisheries. p. 28 https://sustainabledevelopment.un.org/content/documents/1446dominica.pdf

Dominica National Biodiversity Strategy and Action Plan (NBSAP) 2014-2020 December 2014. Prepared by Ministry of Environment, Natural Resources, Physical Planning and Fisheries. p. 43 https://sustainabledevelopment.un.org/content/documents/1446dominica.pdf

Ecoengineering Caribbean Limited, “Cabrits National Park (Marine Component) Site Report, Dominica: report No. 11/2007”. Environmental and Socio-economic Studies for OPAAL Demonstration Sites.  July, 2007. http://parkscaribbean.net/wp-content/uploads/2013/11/Cabrits%20National%20Park%20(Marine)-Environmental%20and%20Socio-economic%20Study%20(2007).pdf

Rainforest Cover, Mongabay webpage https://rainforests.mongabay.com/deforestation/archive/Dominica.htm

Hu, Tonggai and Smith, Ronald B. “The Impact of Hurricane Maria on the Vegetation of

Dominica and Puerto Rico Using Multispectral Remote Sensing” Remote Sensing Vol. 10(6):827 · May 2018. Web. file:///C:/Users/oblan/Downloads/TheImpactofHurricaneMariaontheVegetationofDominicaandPuertoRicoUsingMultispectralRemoteSensing.pdf

Salas, Silvia. “Coastal Fisheries of Latin America and the Caribbean.” FAO Fisheries and Aquaculture Technical Paper 544. Rome, 2011. ISBN 978-92-5-106722-2. p. 226.Web.  http://www.fao.org/3/a-i1926e.pdf

Salas, Silvia. “Coastal Fisheries of Latin America and the Caribbean.” FAO Fisheries and Aquaculture Technical Paper 544. Rome, 2011. ISBN 978-92-5-106722-2. p. 226.Web.  http://www.fao.org/3/a-i1926e.pdf

Salas, Silvia. “Coastal Fisheries of Latin America and the Caribbean.” FAO Fisheries and Aquaculture Technical Paper 544. Rome, 2011. ISBN 978-92-5-106722-2. p. 226.Web.  http://www.fao.org/3/a-i1926e.pdf

Salas, Silvia. “Coastal Fisheries of Latin America and the Caribbean.” FAO Fisheries and Aquaculture Technical Paper 544. Rome, 2011. ISBN 978-92-5-106722-2. p. 226.Web.  http://www.fao.org/3/a-i1926e.pdf

Constantine, Sherry, The Nature Conservancy, “Grenada Launches its newest marine protected area- Grand Anse” Caribbean Biodiversity Fund, https://www.caribbeanbiodiversityfund.org/en/cbf-news-events/news/56-grenada-launches-its-newest-marine-protected-area-grand-anse .

Convention on Biological Diversity, Country Profile Grenada. Webpage accessed 1/4/2019 https://www.cbd.int/countries/profile/default.shtml?country=gd

National Biodiversity Strategy and Action Plan (NBSAP), Grenada p.14

National Biodiversity Strategy and Action Plan (NBSAP), Grenada p. 32

National Biodiversity Strategy and Action Plan (NBSAP), Grenada

Grenada Fund for Conservation, http://www.grenadafundforconservation.org/reccomm

Convention on Biological Diversity, Country Profile Grenada. Webpage accessed 1/4/2019 https://www.cbd.int/countries/profile/default.shtml?country=gd

Convention on Biological Diversity, Country Profile Grenada. Webpage accessed 1/4/2019 https://www.cbd.int/countries/profile/default.shtml?country=gd

Grenada Fund for Conservation, http://www.grenadafundforconservation.org/reccomm

Grenada Fund for Conservation, http://www.grenadafundforconservation.org/reccomm

Richard M. Huber, Richard Meganck, The management challenge of Grand Anse Beach erosion, Grenada, West Indies, Ocean and Shoreline Management, Volume 13, Issue 2, 1990, Pages 99-109, ISSN 0951-8312, https://doi.org/10.1016/0951-8312(90)90042-G. (http://www.sciencedirect.com/science/article/pii/095183129090042G)

Singh, Asha. Saint Lucia National Environmental Summary (NES) 2010. UNEP. p. 10 http://www.pnuma.org/publicaciones/Final%20NES%20-%20St%20Lucia-2010-%20edited.pdf

FAO, “Fisheries Resources Report 2016: St. Lucia Queen Conch fishery” Web.  http://firms.fao.org/firms/fishery/975/en

World Bank Global Environment Facility (GEF). “Iyanola Natural Resource Management off the North East Coast: Appendix 15: Project stakeholder and participation plan” p. 15 https://www.thegef.org/sites/default/files/project_documents/11-7-14_-_Appendix_14.pdf

FAO, “Report on the Lobsters Fisheries of St. Lucia” Table 1. Web. http://www.fao.org/docrep/006/y4931b/y4931b0i.htm

“First CITES Wider Caribbean Hawksbill Turtle Dialogue Meeting, Mexico City, Mexico”, 15-17 May, 2001. National Report for St. Lucia. Web. http://life.bio.sunysb.edu/~spgp/Fall%202002/Marine%20Management%20Areas%20for%20the%20Protection%20of%20Marine%20Turtles.pdf

St. Lucia National Trust. “Illegal sea turtle harvesting in Vieux Fort under investigation” St Lucia News Online. September 5, 2018. https://www.stlucianewsonline.com/illegal-sea-turtle-harvesting-within-the-pointe-sable-environmental-protection-area-in-vieux-fort/

Government of St. Lucia, Department of Finance Resources. National vision Plan Northeast Quadrant. p. 77-107. December 15, 2009. Web.  file:///C:/Users/oblan/Downloads/NationalVisionPlan_NorthEastQuadrant_77-106%20(1).pdf

Singh, Asha. Saint Lucia National Environmental Summary (NES) 2010. UNEP. p. 4 http://www.pnuma.org/publicaciones/Final%20NES%20-%20St%20Lucia-2010-%20edited.pdf

Singh, Asha. Saint Lucia National Environmental Summary (NES) 2010. UNEP. http://www.pnuma.org/publicaciones/Final%20NES%20-%20St%20Lucia-2010-%20edited.pdf

Singh, Asha. Saint Lucia National Environmental Summary (NES) 2010. UNEP. p. 4 http://www.pnuma.org/publicaciones/Final%20NES%20-%20St%20Lucia-2010-%20edited.pdf

Singh, Asha. Saint Lucia National Environmental Summary (NES) 2010. UNEP. p. 8 http://www.pnuma.org/publicaciones/Final%20NES%20-%20St%20Lucia-2010-%20edited.pdf

Forest Cover: Saint Lucia, Mongabay web page. https://rainforests.mongabay.com/deforestation/2000/Saint_Lucia.htm

Daltry, Jennifer. “Biodiversity Assessment of Saint Lucia’s Forests, with Management Recommendations Technical Report 10” 2009.  Presented to the European Commission and Banana Industry Trust. https://propark.ro/images/uploads/file/publicatii/Daltry%202009%20Biodiversity%20Assessment%20Saint%20Lucia.pdf

Porder D. Read, Mengerink, Kathryn.  "Sustainable Fisheries & Coastal Zoning in Barbuda: Legal & Institutional Assessment of Authorities and Approaches." Environmental Law Institute. May 2014

Government of Antigua and Barbuda, National Parks Act 1984. Text.  http://laws.gov.ag/acts/chapters/cap-290.pdf

Codrington Lagoon National Park Management Plan 2009-2019

Government of Antigua and Barbuda, Barbuda Land Act 2007. Text. http://laws.gov.ag/acts/2007/a2007-23.pdf

Porder D. Read, Mengerink, Kathryn.  "Sustainable Fisheries & Coastal Zoning in Barbuda: Legal & Institutional Assessment of Authorities and Approaches." Environmental Law Institute. May 2014

Gross Matt. “After Hurricane Maria’s devastation, can Dominica be a destination again?” The New York Times. March 19, 2018. https://www.nytimes.com/2018/03/19/travel/dominica-hurricane-maria-recovery.html

Tomaso Ferrando. “‘Land grab’ on hurricane-hit Barbuda could leave the island almost entirely owned by banks”. The Conversation. May 31, 2018.

Commonwealth of Dominica. National Parks and Protected Areas Act 1975 Chapters 42:02 http://www.dominica.gov.dm/laws/chapters/chap42-02.pdf

Commonwealth Secretariat (2000), "Constructing the Commonwealth Vulnerability Index", in A Commonwealth Vulnerability Index for Developing Countries: The Position of Small States, Commonwealth Secretariat, London, https://doi.org/10.14217/9781848597167-3-en.

CARICOM. Post-Disaster Needs Assessment Hurricane Maria September 18, 2017: A Report by the Government

of the Commonwealth of Dominica

CARICOM. Post-Disaster Needs Assessment Hurricane Maria September 18, 2017: A Report by the Government

of the Commonwealth of Dominica

“CDB, EU and UK to Help Dominica Make Public Buildings More Energy Efficient” Caribbean 360. November 2, 2018

Government of the Commonwealth of Dominica. Investment options: real estate. Web. https://cbiu.gov.dm/real-estate/

Government of Grenada. Fisheries (Marine Protected Areas) Regulations. SRO 78 of 2001

Environmental Law Institute. “Legal Frameworks for MPA Enforcement in the Caribbean: Challenges and Opportunities.” February 2015.

Government of Grenada Information Service “Styrofoam Importation Ban to come into effect on September 1” August 29, 2018.

Government of Grenada Information Service “Styrofoam Importation Ban to come into effect on September 1” August 29, 2018.

All section information referenced from:  Environmental Law Institute. “Legal Frameworks for MPA Enforcement in the Caribbean: Challenges and Opportunities.” February 2015.

Organization for Economic Cooperation and Development (OECD). “Public comments received on misuse of residence by investment (RBI) schemes to circumvent the common reporting Standard.” April 17, 2018.

Antigua & Barbuda Coral Reef Report Card 2016.

Antigua & Barbuda Coral Reef Report Card 2016.

Antigua and Barbuda 2018 Budget Speech. Pg. 189. https://ab.gov.ag/pdf/budget/budget_speech_2018.pdf

Antigua and Barbuda 2018 Budget Speech. Pg. 175. https://ab.gov.ag/pdf/budget/budget_speech_2018.pdf

Antigua and Barbuda 2018 Budget Speech. Pg. 189. https://ab.gov.ag/pdf/budget/budget_speech_2018.pdf.

Management Plan Codrington Lagoon National Park 2009-2019.

Management Plan Codrington Lagoon National Park 2009-2019. Pg. 25

OPAAL Project, “SOCIO-ECONOMIC EVALUATION of the EXISTING AND PROPOSED LIVELIHOODS SUB-PROJECT CABRITS NATIONAL PARK, COMMONWEALTH of DOMINICA” April 2010. pg. 44

OPAAL Project, “SOCIO-ECONOMIC EVALUATION of the EXISTING AND PROPOSED LIVELIHOODS SUB-PROJECT CABRITS NATIONAL PARK, COMMONWEALTH of DOMINICA” April 2010. pg. 44

Grenada NBSAP.

NBSAP, p. 8.

NBSAP, p. 22.

http://www.cep.unep.org/cartagena-convention

http://www.cep.unep.org/cartagena-convention/spaw-protocol

http://www.cep.unep.org/cartagena-convention/lbs-protocol/protocol-concerning-pollution-from-land-based-sources-and-activities

http://www.cep.unep.org/cartagena-convention/oil-spills-protocol

https://www.caribbeanclimate.bz/

http://www.bb.undp.org/content/barbados/en/home/projects/ridge-to-reef-grenada.html

OECS (2007), Environmental and Socio-Economic Studies For OPAAL Demonstration Sites Cabrits National Park (Marine Component) Site Report, Dominica. http://parkscaribbean.net/wp-content/uploads/2013/11/Cabrits%20National%20Park%20(Marine)-Environmental%20and%20Socio-economic%20Study%20(2007).pdf

Grenada Fisheries Division (2017) Socio-economic monitoring in adjacent communities of the Grand Anse Marine Protected Area, ECMMAN Project http://www.socmon.org/upload/documents/ECMMAN%20SocMon%20Grand%20Anse%20Report_27%20Dec%202017.pdf

UNDP (2015). Where are the women? A Study of Women, Politics, Parliaments and Equality in the CARICOM Countries. Table 4 pp 25, https://iknowpolitics.org/sites/default/files/jm_where_are_the_women_caricom.pdf

The “ongoing GEF Iyanola Project” in this section refers to “Iyanola- Natural Resource Management of the NE Coast” GEF Project ID:5057

Antigua and Barbuda NBSAP, p. 2.

2015-2020 National Action Plan for Antigua and Barbuda, p. 21.

Dominica’s National Action Plan, p. 10.

Dominica’s National Action Plan, p. 48.

Dominica NBSAP, p. 18.

Dominica NBSAP, p. 31.

Grenada NBSAP, chapter 4, table 3

The “ongoing GEF Iyanola Project” in this section refers to “Iyanola- Natural Resource Management of the NE Coast” GEF Project ID:5057

The “ongoing GEF Iyanola Project” in this section refers to “Iyanola- Natural Resource Management of the NE Coast” GEF Project ID:5057

“Integrated Pest Management (IPM) means the careful consideration of all available pest control techniques and subsequent integration of appropriate measures that discourage the development of pest populations and keep pesticides and other interventions to levels that are economically justified and reduce or minimize risks to human health and the environment. IPM emphasizes the growth of a healthy crop with the least possible disruption to agro-ecosystems and encourages natural pest control mechanisms http://www.fao.org/agriculture/crops/thematic-sitemap/theme/pests/ipm/en/

"IVM is a rational decision-making process for the optimal use of resources for vector control. The approach seeks to improve the efficacy, cost-effectiveness, ecological soundness and sustainability of disease-vector control. The ultimate goal is to prevent the transmission of vector-borne diseases such as malaria, dengue, Japanese encephalitis, leishmaniasis, schistosomiasis and Chagas disease." (http://www.who.int/neglected_diseases/vector_ecology/ivm_concept/en/)

Find more information from http://www.fao.org/fileadmin/templates/agphome/documents/Pests_Pesticides/Code/CODE_2014Sep_ENG.pdf

Refer to the Toolkit for the application of the UNEP Indigenous Peoples Policy Guidance for further information.