# Appendix 10: Terms of Reference

National Project Coordinator (NPC)

Project: Meeting the Challenge of 2020 in The Bahamas

Post title: National Project Coordinator

Duration: 60 months

Duty station: New Providence (BEST Commission)

Expected Outcomes and Deliverables

The Project Coordinator’s main duties and responsibilities are to:

- Act as secretary to the PSC;

- Coordinate, manage and monitor the implementation of the GEF 2020 Project conducted by the local and international experts, consultants, subcontractors and cooperating partners; this includes planning, initiating and managing national project activities according to the project document and the procedures in the official UNEP Operational Guidelines;

- Organize Project Steering Committee meetings;

- Prepare detailed workplan and budget under the guidance of the PSC;

- Ensure effective communication with the relevant authorities, institutions and Government departments in close collaboration with the Project Steering Committee;

- Acting as the technical focal point for national stakeholders and broaden national stakeholder base where relevant, e.g. by organizing national stakeholder consultations and facilitating national stakeholder meetings;

- Assist Technical Consultant for Ecosystem Zoning Plans with stakeholder mapping exercise to identify stakeholders and their patterns of use in each of the 5 target areas of the project;

- Work with the Technical Consultant for Ecosystem Zoning Plans and marine protected area managers (BNT) in the stakeholder engagement exercises to ensure data and knowledge from stakeholders are incorporated into the zoning plans for the 5 target areas;

- Foster, establish and maintain links with other related national and international programmes and initiatives;

- Identification of additional national co-finance as the FSP develops;

- Prepare and oversee the development of Terms of Reference for FSP components, Targeted MPA Site Teams, other consultants and experts;

- Organize, contract and manage the consultants and experts, and supervise their performance;

- Coordinate and oversee the preparation of the outputs of the GEF 2020 Project;

- Manage the FSP finance, oversee overall resource allocation and where relevant submit proposals for budget revisions to the PSC and UNEP;

- Manage the overall FSP ensuring that all the activities are carried out on time and within budget to achieve the stated outputs;

- Coordinate the work of all stakeholders under the guidance of the NEA and the PSC and in consultation with the UNEP Task Manager;

- Ensure that information is available to the PSC about all Government, private and public sector activities, which impact on GEF 2020 Project; and

- Prepare and submit to UNEP and the PSC, regular progress and financial reports

Reporting structure

The NPC will report to the NEA on a daily basis. The Coordinator will serve as the secretary and provide support to the PSC.

Qualifications

Education

University degree or equivalent qualification in an environmental science, environmental planning or related field. A Master’s degree is preferred.

Required Skills

- Team player who possesses excellent organisational skills;

- Excellent written and oral communication skills;

- Computer literacy with familiarity with Microsoft Office Suite; and

- Strong swimmer, certified SCUBA diver and comfortable in and around boats would be assets.

Experience

- Experience in undertaking similar assignments, preferably with experience in The Bahamas;

- Experience  with stakeholder engagement and mapping; and

- Familiarity with multilateral environmental agreements, including CBD and UNFCCC would be an asset.

Languages

Fluency in English is required.

National Executing Agency (NEA)

The National Executing Agency (NEA), in addition to other duties given to it by the National Government, will:

- Establish the Project Steering Committee (PSC);

- Appoint a full-time National Project Coordinator (NPC), taking into account the sustainability of activities related to the GEF 2020 Project;

- Provide the necessary scientific, technical, financial and administrative support to the work of the PSC, working in close cooperation with relevant government agencies, the scientific community and the public and private sectors;

- Ensure that regular reports, financial accounts, and requests are submitted to UNEP;

- Review all documentation to ensure that these are consonant with National Government policies and procedures.

Project Steering Committee

The Project Steering Committee (PSC) will work together as a team on management of the National Project and meet at least on a quarterly basis with the following duties:

- Develop a common understanding of what is needed to implement the GEF 2020 Project;

- Oversee the execution of project activities;

- Approve the detailed workplan and budget produced by the NPC;

- Mobilize necessary expertise, as needed for the proper execution of the GEF 2020 Project outputs;

- Provide overall policy advice on the implementation of the FSP;

- Review and advise on the main outputs of the GEF 2020 Project;

- Assist in mobilizing available data and ensure a constant information flow between all concerned parties;

- Allow for effective communication and decision-making between the National Project Coordinator and other actors;

- Ensure that the environmental policy of the Government is fully reflected in the GEF 2020 Project documentation;

- Review and approve the GEF 2020 Project outputs and documents.

On an annual basis, the PSC will meet with all executing partners including UN Environment, BNT and IICA to fulfil steering mechanism responsibilities including: oversight of project implementation, monitoring of project progress, strategic and policy guidance and to review and approve annual work plans and budgets.

Technical Consultant (Ecosystem Zoning Plans)

Project: Meeting the Challenge of 2020 in The Bahamas

Post title: Technical Consultant

Duration: 3 months

Duty station: Home-based

Expected Outcomes and Deliverables

The Technical Consultant’s main duties and responsibilities are to develop and finalise ecosystem-wide zoning plans for the five (5) target areas under the GEF 2020 Project and include;

- Review all available information, existing spatial data, and potential holders/sources of data for the 5-target areas

- Stakeholder mapping exercise to identify stakeholders and their patterns of use in each of the 5 target areas

- Conduct a skills gap assessment of MPA management agencies as it relates to zoning

- Work with the marine protected area managers (BNT) in the stakeholder engagement exercises to ensure data and knowledge from stakeholders are incorporated into the zoning plan

- Develop a series of maps for each of the target areas (including biological resources, stakeholder usage, land use, and zones (protected areas boundaries, zoning categories, etc)

- Develop zoning plan for each of the 5 target areas

- Work closely with the consultant responsible for the development of the spatially-based decision support system (SDSS) to ensure data and knowledge from the zoning plan process is standardized and incorporated into the SDSS (e.g. imagery, metadatabases, etc).

Reporting structure

The Technical Consultant will report to the NPC and the NEA.

Qualifications

Education

A minimum Master’s Degree in the field of Urban and Regional Planning, Geographic Information Systems, Environmental Planning, Land-use Planning, Environmental Sciences, or similar field for the lead consultant ii. Evidence of the ability to develop GIS based spatial plans

Required Skills

- The consultant shall have excellent spatial planning, analytical, report writing and communication skills, and excellent knowledge of English.

- The consultant will be expected to collaborate with national, regional and international institution/individuals involved in the GEF 2020 project.

- The consultant will also be required to lead and participate in workshops and seminars with key stakeholders during the consultancy.

- The consultant will at a minimum be required to lead the Inception Workshop and Validation Workshop and participate in at least two other workshops with stakeholders.

Experience

- The Lead Consultant shall have minimum 15 years of professional experience in the field of Physical/Spatial/Land-use planning and a sound track record of at least 10 successfully completed Zoning Plans or Spatial/Land-use Plans, out of which s/he shall have been the lead consultant or lead expert in a minimum of 5 (to be clearly stated in the CV provide evidence of such).

- The Consultant should demonstrate capacity to develop GIS based Spatial and Land Use Plans by attaching copies of Zoning Plans.

- Previous experience/knowledge in incorporation/mainstreaming of MPA, Climate Change issues in the development of Spatial Plans or Zoning Plans shall be considered an advantage.

- Familiarity with The Bahamas is desirable.

Language

Fluency in English is required.

Conservation Finance Specialist

Project: Meeting the Challenge of 2020 in The Bahamas

Post title: Conservation Finance Specialist

Duration: 9-12 months

Duty station: Home-based

Expected Outcomes and Deliverables

The consultant will be responsible for Outputs 2.2.1 under the project document, relating to business plan development and increased financial sustainability and cost reduction at two target MPAs - Lucayan National Park and Moriah Harbour National Park.

The conservation finance expert will support the project team and liaise with other national consultants and project partners, in the following specific activities:

- Do the financial sustainability scorecard for BNT as the baseline assessment

- Conduct a WTP survey of visitors to Grand Bahama to collect data on

- Visitor preferences on facilities and infrastructure (to help prioritize future investments)

- Visitor WTP for entrance fees to Lucayan with planned infrastructure

- Visitor WTP for entrance fees under potential future investment scenarios e.g. Lucayan village, video on caves, watersports rentals etc.

- WTP for other MPAs on Grand Bahama

- Data on visitor spending in Grand Bahama, on eco-tourism related activities and MPA visitation.

- In consultation with a team including the MPA on-site staff, board member (where applicable), local partners and a staff member from the managing organization, use the draft business plan for Lucayan National Park to develop a full business plan for this park.  This would include an economic impact analysis, a functional analysis of expected costs under different scenarios (including necessary spending related to other critical aspects of effectiveness e.g. monitoring, threat mitigation, enforcement) a marketing plan and additional work to develop the financial plan with associated sustainable financial mechanisms

- In consultation with a team including the MPA on-site staff, board member (where applicable), local partners and a staff member from the managing organization, write a draft business plan for Moriah Harbour National Park, with the content detailed in the project document, including a market analysis, economic impact analysis, functional area analysis, cost reduction strategies, financing plan and marketing plan.

Expected Deliverables

- Score for financial scorecard for BNT (1 week)

- Survey report for visitors to Grand Bahama (1 month)

- Business Plan for Lucayan National Park (3-4 months)

- Business Plan for Moriah Harbour National Park (4-6 months)

Reporting structure

The Conservation Finance Specialist will report to the NPC and the NEA.

Required Skills and Qualifications

The minimum key skills and expertise of the consultant shall cover the following:

Competencies

- Good interpersonal and team skills, to respond positively to critical feedback, and a consensus-oriented approach to work.

- Full computer literate

- Familiar with conservation finance in the region

- Excellent English writing and communication skills

- Ability to work in complex, multi-stakeholder project environments

- Demonstrates integrity by modeling UN’s values and ethical standards

- Promotes the vision, mission and strategic goals of the UNDP

- Displays cultural, gender, race, religion, nationality and age sensitivity and adaptability

- Treats all people fairly without favouritism

- Fulfils all obligations to gender sensitivity and zero tolerance for sexual harassment

Education

- Graduate level degree in environmental economics, conservation finance or related subject

Experience

- Experience with contingent valuation and/or choice modelling to measure values associated with environmental recreation and associated econometric analysis

- Proven experience with conservation finance planning and protected area business planning

- Past working experience with key national stakeholders to undertake projects related to protected areas is preferred

- Past working experience conducting surveys in the Bahamas preferred

- Familiarity with Bahamian MPAs preferred

- Ability to conduct research and analysis with strong synthesis and reporting skills

Languages

Fluency in English is required.

Renewable Energy Consultant

Project: Meeting the Challenge of 2020 in The Bahamas

Post title: Renewable Energy Consultant

Duration: 24 – 32 months

Duty station: New Providence

The Renewable Energy Consultant’s main duties and responsibilities are to:

- Direct RE/EE Component activities in accordance with project plans

- Ensure key deliverables of the project are met on a timely basis

- Ensure project risks and potential delays are identified and mitigated

- Regularly reports on project activities, so that the extent to which the project is achieving its objectives are known

- Ensure relevant key stakeholders are informed of project activities

- Ensure project resources are used effectively and efficiently

- Responsible for managing the activities of all sub-contracted works under the RE/EE component of the project

- Responsible for coordinating the activities of all RE/EE consultants assigned to the project

Reporting structure

The Renewable Energy Consultant will report to the National Project Coordinator

Qualifications

Education

- Minimum of Undergraduate degree in energy or energy management related discipline

- Advanced Degree in Energy or Energy Management Discipline preferable

- Project Management Professional Certification would be an asset

Required Skills

- Excellent project management skills

- Very good report writing

- Very good cost control and budgeting skills

- Very good communication and report writing skills

- Ability to resolve team conflicts and possess good problem-solving skills

Experience

- Experience in managing/executing projects for international donor agencies

- Experience with working with government and non-government agencies

- Experience with managing or executing Renewable Energy and Energy Efficiency Projects

- Experience in preparing Greenhouse Gas Inventories would be an asset

Languages

Fluency in English is required.

Knowledge Management Specialist

Project: Meeting the Challenge of 2020 in The Bahamas

Post title: Knowledge Management Specialist

Duration: 60 months

Duty station: New Providence

To be developed at Project Inception.

Species Monitoring and Conservation Plan Specialist

Project: Meeting the Challenge of 2020 in The Bahamas

Post title: Renewable Energy Consultant

Duration: 24 months

Duty station: New Providence

To be developed at Project Inception