Project Document

# Section 1: Project Identification

1.1	Project title:	Meeting the Challenge of 2020 in The Bahamas

1.2	Project number:			GEF ID: 9791

PMS: 01569

1.3	Project type: 				FSP

1.4	Trust Fund:				GEF

1.5	Strategic objectives:

GEF strategic long-term objective:	Improve sustainability of protected areas, reduce threats to biodiversity, and mainstream conservation and sustainable use of biodiversity into production landscapes and seascapes. Demonstrate mitigation options with systemic impacts.

Strategic programme for GEF 6:	GEF-6 - Biodiversity Programme 1: Improving financial sustainability and effective management of the national ecological infrastructure; Biodiversity Programme 4: Prevention, control and management of Invasive Alien Species; Biodiversity Programme 9: Managing the human-biodiversity interface; and Climate Change Mitigation Programme 1: Promote timely development, demonstration and financing of low-carbon technologies and mitigation options.

1.6	UNEP priority: 			Ecosystem Management, Climate Change

1.7	Geographical scope:			Bahamas

1.8	Mode of execution:			External

1.9	Project executing organization:	BEST Commission, Department of Marine

Resources, Inter-American Institute for

Cooperation on Agriculture, Bahamas National

Trust

1.10	Duration of project:			60 months

Commencing:	September 2019

Completion:	August 2024

    - Cost of project 					US$				%

| Cost to the GEF Trust Fund | 6,243,004 | 34.27 |
| --- | --- | --- |
| Co-financing | 11,972,306 | 65.73 |
| Cash |  |  |
| Ministry of Environment & Housing | 2,5000,000 | 13.72 |
| The Nature Conservancy | 603,000 | 3.31 |
| Bahamas National Trust | 3,816,307 | 20.95 |
| Perry Institute for Marine Science | 300,000 | 1.65 |
| Shedd Aquarium | 1,695,500 | 9.31 |
| Sub-total | 8,914,807 | 48.94 |
| In-kind |  |  |
| Ministry of Environment & Housing | 500,000 | 2.74 |
| The Nature Conservancy | 3,000 | 0.02 |
| Caribbean Biodiversity Fund | 50,000 | 0.27 |
| Bahamas National Trust | 1,111,529 | 6.10 |
| Perry Institute for Marine Science | 1,000,000 | 5.49 |
| Shedd Aquarium | 392,970 | 2.16 |
| Sub-total | 3,057,499 | 16.79 |
| Total | 18,215,310 | 100 |

    - Project summary

The main issues the Meeting the Challenge of 2020 in The Bahamas Project or ‘Challenge of 2020 Project’ for short seeks to address include the following:

- Low management effectiveness in legally declared protected areas. Many protected areas lack management plans, infrastructure and capacity to achieve conservation goals;

- Lack of integration of protected areas into broader landscape planning which leads to increased pressures on these areas and the ecosystem services they provide; and

- Threats to protected areas including invasive alien species, habitat degradation, and pollution from agricultural farms that border the protected areas.

The targeted project sites were identified through key stakeholder consultations as well as review of national reports, including 2012 Master Plan for the Bahamas National Protected Area System, 2009 Rapid Assessment and Prioritization for Protected Area Management, Ecological Gap Analyses completed in 2014 and 2017, and 20 x 20 Marine Protection Plan.

These sites are:

  - Andros West Side National Park (AWSNP)

  - Bonefish Pond National Park (BPNP)

  - Exuma Cays Land and Sea Park (ECLSP)

  - Lucayan National Park (LNP)

  - Moriah Harbour Cay National Park (MHCNP)

These sites are national parks which are managed by the Bahamas National Trust (BNT).

These five sites were selected for:

- Their strong biodiversity value.

- The ecosystem services they provide.

- Their high visibility and potential for project activities to change human behaviours.

- Ecological connectivity in the case of ECLSP and MHCNP.

The project is of a five (5) year duration, beginning September 2019 and ending August 2024. The objective of the project is to strengthen management of marine protected areas (MPAs) and to integrate MPAs into broader landscape planning in order to reduce pressures on ecosystem services and biodiversity from competing resource uses.

The project’s components are:

- Integrated Natural Resource Management systems for marine protected areas and adjacent landscapes and seascapes;

- Effective protected area management; and

- Marine protected area (MPA) management integrated with sustainable development in the broader landscape and seascape.

Component 1 on Integrated Natural Resource Management (INRM) will result in development of a spatially-based decision support system populated with data on protected areas which will be made available for use in cross-sectoral planning and management as well as in policy and regulatory development. Ecosystem zoning plans will also be developed for all five sites as a means to assist in planning, not just for the protected areas, but larger ecosystems which MPAs are representative of.

Component 2 on effective protected area management will result in greater participation of local communities in the management of LNP and MHCNP through the establishment of protected area advisory boards. Management plans will be updated for AWSNP, ECLSP and MHCNP and developed for BPNP and LNP. Targeted implementation activities, inclusive of provision of infrastructure, staffing and equipment, will also be completed under this component for all 5 MPAs. Species conservation and monitoring plans will be developed and implemented for AWSNP, ECLSP, LNP, and MHCNP. Renewable energy installations and energy efficiency measures will be implemented as pilots at BPNP, ECLSP and LNP.

Component 3 on MPA management integration will involve removal of IAS impacting BPNP and LNP and restoration of degraded ecosystems of at least 100 hectares. This component will also involve engagement with farmers with agricultural lands bordering MPAs in an effort to reduce the use and impact of chemicals on sensitive biodiversity and water resources. Engagement of community organizations and schools in monitoring and restoration activities will be achieved through adoption schemes at AWSNP and BPNP.

Key partners in the project are the Bahamas Environment, Science and Technology (BEST) Commission, the Bahamas National Trust (BNT), and the Inter-American Institute for Cooperation on Agriculture (IICA).

Table of Contents

Section 1: Project Identification	1

Acronyms and Abbreviations	8

Section 2: Background and Situation Analysis (Baseline)	10

2.1 Background and context	10

2.2 Targeted Project Sites	15

2.3 Global significance	18

2.4 Threats, root causes and barrier analysis	20

2.4.1 Threats	20

2.4.2 Barrier analysis	25

2.5 Institutional, sectoral and policy context	27

2.5.1 Multilateral Environmental Agreements	27

2.5.2 National Policies, Plans and Institutional Arrangements	28

2.6 Stakeholder mapping and analysis	32

2.7 Baseline analysis and gaps	35

2.7.1 Baseline for Spatially-based Decision Support System	36

2.7.2 Baseline for Business Plans	37

2.7.3 Baseline for Renewable Energy	40

2.8 Linkages with other GEF and non-GEF interventions	41

Section 3: Intervention Strategy (Alternative)	44

3.1 Project rationale, policy conformity and expected global environmental benefits	44

3.2 Project goal and objectives	47

3.3 Project components, activities and expected results	48

3.4 Intervention logic and key assumptions	65

3.5 Risk analysis and risk management measures	67

3.6 Consistency with national priorities and plans	69

3.7 Incremental cost reasoning	72

3.7.1 Business as usual scenario	72

3.7.2 Incremental reasoning	72

3.8 Sustainability	74

3.9 Replication	75

3.10 Public awareness, communications and mainstreaming strategy	76

3.11 Environmental and social safeguards	76

Section 4: Institutional Framework and Implementation Arrangements	77

Section 5: Stakeholder Participation	79

Section 6: Monitoring and Evaluation Plan	80

Section 7: Project Financing and Budget	83

7.1 Overall project budget	83

7.2 Project co-financing	83

7.3 Project cost-effectiveness	83

References	85

Appendix 1: Budget by project components and UNEP budget lines	86

Appendix 2: Co-financing by source and UNEP budget lines	86

Appendix 3: Incremental cost analysis	86

Appendix 4: Results Framework	86

Appendix 5: Workplan and Timetable	86

Appendix 6: Key deliverables and benchmarks	86

Appendix 7: Costed M&E Plan	86

Appendix 8: Summary of reporting requirements and responsibilities	86

Appendix 9: Consultant Costs	86

Appendix 10: Terms of Reference	86

Appendix 11: Co-financing commitment letters from project partners	86

Appendix 12: Endorsement letter of GEF National Focal Point	86

Appendix 13: Draft procurement plan	86

Appendix 14: Management Effectiveness Tracking Tool	87

Appendix 15: UNEP Environmental and Social Safeguards	87

Appendix 16: Theory of Change	87

Annex A:  Details on Targeted Project Sites	87

Annex B1:  Technical Report: Spatially-based Decision Support System	87

Annex B2:  Technical Report: Ecosystem-wide Zoning Plans	87

Annex C:   Meeting the Challenge of 2020 in The Bahamas. Conservation Finance Report	87

Annex D:  Renewable Energy & Energy Efficiency Report	87

Maps, Figures and Tables

Map 1: The Islands of The Bahamas	10

Table 1: Demographics of Project Islands	12

Map 2: Targeted Project Sites	13

Table 2: Summary of Targeted Project Sites	16

Table 3: Global designations of Targeted Project Sites	19

Table 4: Threats to Targeted Project Sites	21

Table 5: MEAs that The Bahamas is signatory to	27

Table 7: Key Stakeholder Involvement	33

Table 8: Estimated Costs for Targeted Project Sites and Centralized Costs for BNT	38

Table 9: Summary of Sources of Financial Information for Targeted Project Sites	39

Figure 1: Proposed PA Advisory Board within the BNT organizational structure	52

Table 10: MPA Needs	54

Table 11: Priority Species and Proposed Monitoring and Conservation Management Activities	58

Table 12: Risks and Mitigation Strategy	67

Figure 2: Project implementation arrangements	79

Table 13: Summary GEF budget for project implementation by Year	83

Table 14: Summary GEF budget for project implementation by Component	83

Table 15: Project Co-financing	83

# Acronyms and Abbreviations

| AGRRA | Atlantic and Gulf Rapid Reef Assessment |
| --- | --- |
| ANCAT | Andros Conservancy and Trust |
| AWSNP | Andros West Side National Park |
| BEST BNGIS | Bahamas Environment, Science and Technology Commission Bahamas National Geographic Information Systems Centre |
| BNPAS | Bahamas National Protected Area System |
| BNT | Bahamas National Trust |
| BPAF | Bahamas Protected Areas Fund |
| BPNP | Bonefish Pond National Park |
| BREEF | Bahamas Reef Environment Educational Foundation |
| CBD | Convention on Biological Diversity |
| CTO | Caribbean Tourism Organization |
| DBEF-PS | Dry Broadleaf Evergreen Formations - Palm Shrublands |
| DEHS | Department of Environmental Health Services |
| DMR | Department of Marine Resources |
| ECLSP | Exuma Cays Land and Sea Park |
| EEZ | Exclusive Economic Zone |
| FIES | Food Insecurity Experience Scale |
| FNC | First National Communication |
| FSP | Full-Sized Project |
| EOU GEB | Evaluation and Oversight Unit Global Environmental Benefit |
| GAP | Good Agricultural Practices |
| GEF | Global Environment Facility |
| GIS | Geographic Information Systems |
| GOB | Government of The Bahamas |
| IA | Implementing Agency |
| IAS IBA | Invasive Alien Species Important Bird Area |
| IDB IICA | Inter-American Development Bank Inter-American Institute for Cooperation on Agriculture |
| INDC | Intended Nationally Determined Contribution |
| INRM | Integrated Natural Resource Management |
| IPCC | Inter-governmental Panel on Climate Change |
| IWEco KBA | Integrating Land, Water and Ecosystem Management Key Biodiversity Area |
| LNP | Lucayan National Park |
| MEA | Multilateral Environmental Agreement |
| METT | Management Effectiveness Tracking Tool |
| MHCNP | Moriah Harbour Cay National Park |
| MoT | Ministry of Tourism |
| MPA | Marine Protected Area |
| MSP | Medium-Sized Project |
| NBSAP | National Biodiversity Strategy and Action Plan |
| NCC | National Coordinating Committee |
| NCSA | National Capacity Needs Self-Assessment |
| NEA | National Executing Agency |
| NEMAP | National Environmental Management and Action Plan |
| NGO | Non-Governmental Organization |
| NHSA | Nature’s Hope for Southern Andros |
| NISP | National Implementation Support Programme |
| NISS | National Invasive Species Strategy |
| NPC | National Project Coordinator |
| PIF | Project Identification Form |
| PIR | Project Implementation Review |
| PoWPA | Programme of Work on Protected Areas |
| PPG | Project Preparation Grant |
| PSC | Project Steering Committee |
| PST | Project Site Team |
| PW | Pine Woodlands |
| RAPPAM | Rapid Assessment and Prioritization of Protected Area Management |
| Ramsar Convention | Convention on Wetlands of International Importance especially as Waterfowl Habitat |
| REA | Rapid Ecological Assessment |
| SIDS | Small Island Developing States |
| SNC | Second National Communication |
| SPAW | Specially Protected Areas and Wildlife Protocol under the Cartagena Convention |
| SWOT | Strengths, Weaknesses, Opportunities, and Threats |
| TNC | The Nature Conservancy |
| TM | Task Manager |
| UB | University of The Bahamas |
| UNCCD | United Nations Convention to Combat Desertification and Drought |
| UNEP | United Nations Environment Programme |
| UNFCCC | United Nations Framework Convention on Climate Change |

# Section 2: Background and Situation Analysis (Baseline)

## 2.1 Background and context

- The Bahamas can be found between the southeastern shores of the United States and the northern shores of Cuba. The Bahamian archipelago extends 2,000 km, from Grand Bahama in the north to Inagua in the south, covering 100,000 square miles (259,000 square kilometers) (see Map1). Included in this area are more than 700 islands and 2,500 cays.

#### Map 1: The Islands of The Bahamas

- The archipelago consists of several submerged plateaux, including the Great Bahama Bank and Little Bahama Bank. These are separated by deep oceanic troughs, including the Tongue of the Ocean and Providence Channel. The islands of The Bahamas are the exposed portions of the banks and are formed from limestone created from the skeletal remains of the vast amount of marine plant and animal life inhabiting the shallow water over millions of years.

- The landscapes of the islands are a mixture of rolling hills, ridges, flat rockland and extensive wetlands. Rainfall has produced solution holes of various sizes in the limestone rock. These karst geological features are referred to ‘banana holes’ as soil deposits in them are used by farmers to plant banana trees. Larger-scale solution holes are referred to as blue holes and are usually a part of extensive subsurface cavern systems. Soils in The Bahamas are thin and often absent, except under forest cover.

- All freshwater in The Bahamas, comes from rainfall that is in dynamic transit to the ocean. It has been estimated that freshwater underlies only some 5% of the total land area of The Bahamas. The physical geology or hydrogeology of The Bahamas, and its water resources, are directly linked, as the country has no true rivers. The Bahamas, along with many of the Caribbean islands, ranks among the most water scarce Small Island Developing States (SIDS) in the world. Rainfall varies by season as well as by island. During the winter months, which are considered the dry season, monthly rainfall averages 48.8 mm. The wet season occurs during the summer months with a monthly rainfall average of 180 mm. Annual average rainfall ranges from 1,496 mm in High Rock, Grand Bahama in the north to 693 mm in Matthew Town, Inagua in the south. Surface water in The Bahamas includes tidal creeks, wetlands, marsh areas, brackish ponds, salt ponds, and blue holes. There are no rivers or streams in the country.

- The distinct environment of The Bahamas gives rise to numerous irreplaceable habitats and species, including vast expanses of Caribbean pine forest, tidal flats with thriving bonefish populations, extensive barrier reefs, the highest concentration of blue holes in the Western Hemisphere, and critical fish nursery habitat believed to contribute significantly to fisheries stocks throughout the Caribbean region. The insularity and extensive carbonate shelf with productive coral reefs and other habitats, plus a large area of coastal wetlands, especially mangrove forests, contribute to the abundance and diversity of fish. Rare, critically endangered, and endemic species can also be found in The Bahamas including the Bahama parrot, several species of Rock iguana, Kirtland’s warbler, West Indian flamingo, Hutia, Smalltooth sawfish, Queen conch, and Loggerhead, Hawksbill, and Green turtles.

- Important, and easily-recognized, Bahamian ecosystems include — but are not limited to — the following:

- Pine woodland (forest) – northern islands

- Coppice – central and southern islands

- Wetlands – may be allocated amongst five categories: mangrove swamps and marshes, beach vegetation, swashes, pine forests/barrens, broad-leaf coppice. Mangroves are dominated by one or more species of mangrove (Avicennia, Laguncularia and Rhizophora,).

- Seagrass beds – dominated by turtle grass (Thalassia testudinum)

- Coral Reefs – of great significance in terms of Bahamian biodiversity

- Other shallow water marine habitats – rock and unvegetated sediments

- Caves, sinkholes and blue holes

- Approximately 30 of the over 700 islands are inhabited. The population of The Bahamas was estimated to be approximately 295,000 in 2000, growing at a rate of just over 1%. By 2010, The Department of Statistics recorded that the population growth increased to approximately 351,471 persons in The Bahamas.  The population change figure increased by approximately 50,000 since the 2000 census.

- Project activities will occur in marine protected areas on the islands of Andros, Berry Islands, Exuma, Grand Bahama, and New Providence. Table 1 below provides an overview of the demographics for each of these islands (Bahamas Census, 2010).

#### Table 1: Demographics of Project Islands

| Island | Population | Population Density (person per square mile) |
| --- | --- | --- |
| Andros | 7,490 | 3.3 |
| Exuma (including cays) | 6,928 | 61.9 |
| Grand Bahama | 51,368 | 96.9 |
| New Providence | 246,329 | 3,079.1 |

Source: Department of Statistics, (2010). Bahamas Census Report 2010.

- Project activities will be focused in the marine protected areas (MPAs) identified below (see Map 2). More information on each site is provided in section 2.2.

- Between 2015 and 2017, it is estimated that The Bahamas sustained US$678 million in damages from hurricanes. During the 2017, Hurricane Irma impacted the islands of Ragged Island, Andros, Bimini and Grand Bahama, resulting in estimated damage of US$135 million. In 2016, Hurricane Matthew impacted several islands, including New Providence, with damage estimates of US$438 million. In 2015, Hurricane Joaquin resulted in a estimated US$100 million in damages, particularly for the island of Long Island. The 2018 hurricane seasons was quiet for The Bahamas with no islands negatively impacted by hurricanes or tropical storms.

- Because of The Bahamas’ geographic configuration, the protection of the ocean is of considerable importance as more than 90% of the archipelago is ocean – either coastal or marine environment. Most of the country’s biodiversity is found in coastal waters, inclusive of migratory fish and marine mammals.  Key economic sectors – tourism and fisheries – are reliant on the health of coastal ecosystems, inclusive of beaches, mangroves, seagrass beds and sand flats.

- Currently the economy is still recovering from the effects of the 2008 recession. Due its heavy reliance on tourism, the country is vulnerable to changes in the global economy. The 2017 assessment by the Central Bank of The Bahamas showed very mild growth of the economy. The country’s GDP was US$12.16 billion in 2017 with tourism accounting for more than 50 per cent, financial services about 20 per cent and the balance spread among retail and wholesale trade, fishing, light manufacturing and agriculture. The Bahamian tourism infrastructure supports approximately 1.5 million stopover visitors and 3.5 million cruise visitors annually. Just under 50% of the labour force is directly employed in tourism. When one adds persons indirectly employed, this increases to 70%.

#### Map 2: Targeted Project Sites

- The fisheries sector plays an important role in the Bahamian economy in terms of foreign currency earnings, food supply and employment. The commercial fisheries sector supplies 31 kg/capita/year of fish and fishery products to the population, generates some US$80 million annually in export earnings and provides full-time employment to 9,300 commercial fishers and thousands of jobs more in recreational fisheries, vessel maintenance, fish processing, retail and trade. The fishing fleet is characterized as small-scale and counts approximately 4,000 fishing vessels ranging in length from 3 meters to 30 meters, but generally less than 7 meter in length. The total commercial fisheries production in 2015 was estimated at nearly 12,000 tonnes. The total production has fluctuated in recent years. Fluctuations are largely caused by the variations in landings of spiny lobster, which were nearly 10,000 tonnes in 2010 and 2012 and around 6,500 tonnes in 2015. Spiny lobster stocks in The Bahamas are being fully exploited, while conch, snappers and groupers are, like in the rest of the Caribbean, under heavy fishing pressure and some stocks are probably overexploited. The major threats to the marine fisheries resources are coastal zone development, boat and diver damage to the reef, over-harvesting of commercial species and disturbance to sensitive sites.

- The recreational and sport fisheries subsector of the fisheries sector is also very important to the country contributes an estimated US$500+ million annually to the national economy through related expenditures by tourists and provides employment for some 18,000 Bahamians. The recreational and sport fisheries target game fish, such as marlins and sailfishes, as well as bone fish.

- Approximately 90% of the available agricultural land is owned by the government and leased to farmers. Of the 95,000 ha of arable land in the country, only 7,650 ha is under cultivation, with two very distinct systems of agricultural production: mechanized methods in the northern islands that receive more rainfall and have large underground freshwater reserves; and shifting cultivation in the central and southern islands that are characterized by subsistence farming. More than 5,000 acres of agricultural land in The Bahamas are used for citrus production. Major crops for export are grapefruit, limes, avocados, papaya, okras and pineapples. The soils in the country are generally poor in terms of nutrient availability and water holding capacity, so farmers rely on heavy inputs of chemical fertilizer.

- Coastal populations and indeed the entire country, is highly vulnerable to sea level rise, storm surges, flooding, pollution and coastal erosion. The entire Bahamas due to its size and topography is vulnerable to the impacts of climate change. Increased development along coastlines tends to increase coastal erosion and therefore vulnerability of populations. Yet coastal development is one of the primary income generators of the country, and therefore this dichotomy had engendered conflicting approaches to management of coastal resources. Most of the critical infrastructure in the country (e.g. ports, roads, power stations) is found in vulnerable coastal areas.

- The overall poverty rate in The Bahamas is 12.5 %. New Providence and Grand Bahama present a similar or lower poverty rates (respectively 12.4% and 9.4%) whereas Family Islands have a higher rate (17.2%). Hence, poverty rates are higher in rural communities. However, the total number of poor people in the population is higher in New Providence and Grand Bahama than in the rest of the Family Islands.

## 2.2 Targeted Project Sites

- The targeted project sites were identified through key stakeholder consultations as well as review of national reports, including 2012 Master Plan for the Bahamas National Protected Area System, 2009 Rapid Assessment and Prioritization for Protected Area Management, Ecological Gap Analyses completed in 2014 and 2017 and 20 x 20 Marine Protection Plan.

- These sites are:

  - Andros West Side National Park (AWSNP)

  - Exuma Cays Land and Sea Park (ECLSP)

  - Lucayan National Park (LNP)

  - Moriah Harbour Cay National Park

  - Bonefish Pond National Park

These five sites are national parks which are managed by the Bahamas National Trust (BNT).

- These sites were selected for the following reasons:

- Their designation as areas of high biodiversity value, e.g. Key Biodiversity Areas (KBA) and/or Important Bird Areas (IBA);

- The ecosystem services they provide;

- Their high visibility and potential for project activities to change human behaviours;

- Ecological connectivity in the case of ECLSP and MHCNP.

After concerns expressed by stakeholders during the Inception Meeting about sites identified in the Project Identification Form (PIF), a site selection meeting was held in December 2018 to confirm the priority sites for project interventions. During that meeting, stakeholders agreed that the following changes to targeted sites would be the best approach for identified priorities in MPA management - Conception Island National Park would be removed and Joulter Cays National Park would be replaced by Moriah Harbour Cay National Park. Based on the high biological significance of BPNP and MHCNP (refer to Annex A), the Bahamas National Trust is completing the application process for KBA designation in collaboration with Birdlife International. These sites meet many of KBA criteria including threatened biodiversity and ecological integrity.

- Table 2 below provides a summary of information about each site that underpins the basis for site selection. More detailed information, including boundary maps, are included in Annex A.

#### Table 2: Summary of Targeted Project Sites

| Site | Type | Location | Size (in hectares) | Managing Agency | Description/basis for site selection |
| --- | --- | --- | --- | --- | --- |
| Andros West Side National Park (AWSNP) | National Park | Andros | 607,028 | BNT | Vast area of coastal mangrove habitat that is an important nursery area for many commercially and ecologically important species (Queen conch, Spiny lobster and many fish) and endangered species, such as the Andros Rock Iguana and the Smalltooth Sawfish. It is also a very important bonefishing area and is utilized by many bird species. |
| Exuma Cays Land and Sea Park (ECLSP) | National Park | Exuma | 70,494 | BNT | Protects extensive marine and terrestrial ecosystems, including mangrove, corals, sand flats and coppice forest that support the protection of many commercially and ecologically important species throughout their entire life history (such as groupers, snappers, grunts, sharks and sea turtles). It protects the living fossils (stromatolites), living relatives of some of the oldest known species. The park protects a number of bird species (e.g. Audubon's Shearwaters, White-tailed tropic birds) and the Rock Iguanas. |
| Lucayan National Park (LNP) | National Park | Grand Bahama | 784 | BNT | Contains one of the longest charted underwater cave systems in the world; a unique system of elevated walkways through the last intact mangrove wetland on the southern shore of Grand Bahama; a magnificently wide unspoiled beach showcasing the tallest sand dunes on the island; and a wealth of flora and fauna. This park exhibits all of the Bahamian vegetative zones, including pine forests and mangrove habitats; the latter serve as nursery habitats for important commercially and ecologically important species, along with corals that protect the southern shorelines of Grand Bahama |

| Moriah Harbour Cay National Park (MHCNP) | National Park | Exuma | 9,240 | BNT | Encompasses pristine beaches, sand dunes, mangrove creeks, and sea grass beds. A variety of bird life nests here, including the Gull-billed and Least terns, nighthawks, plovers, oyster catchers and a resident pair of ospreys. The mangroves are a vital nursery for juvenile crabs, Spiny lobster, Queen conch, Gray snappers, Yellowtails and groupers. Landward, palmettos, buttonwoods, bay cedar, and sea oats work in concert, providing stability, nutrients and beauty to the ecosystem. It is an example of the Bahamian coastal zone. |
| --- | --- | --- | --- | --- | --- |
| Bonefish Pond National Park (BPNP) | National Park | New Providence | 500 | BNT | Protects one of the only intact mangrove wetlands on New Providence, the most densely populated Bahamian island. The park protects important nursery habitat for commercially important species, and protects important buffer systems on the southern portion of New Providence which has been shown to be extremely vulnerable to the impacts of climate change. |

## 2.3 Global significance

- The Bahamas is a part of the Caribbean Islands biodiversity hotspot. Insularity and an extensive shelf with productive coral reefs and other habitats, plus a large area of coastal wetlands, especially mangrove forests, contribute to the abundance and diversity of fish in The Bahamas. In this regard, The Bahamas has greater biodiversity abundance and diversity than the entire insular Caribbean. On a global scale, the coral reefs of The Bahamas comprise about 5% of the world’s total coral reef systems.

- Correll and Correll (1982) report that nearly nine percent (121 taxa) of plant species found in The Bahamas are endemic. Over 1,350 species of flowering plants and ferns have been described, representing approximately 660 genera and 144 families.

- The submarine cavern systems of The Bahamas formed in the last Ice Age are found on all the major islands. They represent the largest unexplored and uncatalogued ecosystem in The Bahamas, uniquely linked to the confluence of the fresh, brackish and saline waters.

- While the Bahama Banks were dry land, they were exposed to the atmosphere where the limestone was subjected to chemical weathering that created the karst topography that the islands are famous for today (BNT, 2014).  The now largely submerged limestone banks that comprise the Bahamian archipelago are riddled with karst features, such as sinks, blue holes, fracture caves and solution caves known to be among the most extensive in the world. These karst features hold hydrological, archaeological, paleontological and biological treasures found nowhere else in the world, including stromatolites - rare prehistoric calcareous layers of lime-secreting bacteria that are trapped with sand and sediment and produce high amounts of oxygen.

- The shallow bank waters, mangrove wetlands, and tidal creeks provide critical spawning and nursery habitat for numerous ecologically and economically important marine species including Nassau grouper (Epinephelus striatus), snapper (Family Lutjanidae), tarpon (Megalops atlanticus), bonefish (Albula vulpes), turtles (Hawksbill (Eretmochelys imbricata), Green (Chelonia mydas), and Loggerhead (Caretta caretta), several species of shark, including Great hammerhead (Sphyrna mokarran), Bull (Carcharhinus leucas) and Nurse (Ginglymostoma cirratum), Caribbean spiny lobster (Panulirus argus) and a variety of other marine invertebrates.

- The Little Bahama Bank is also well recognized for its seabird populations.  The chain of cays extending west from Abaco Island forming the northern extent of the Bank is proposed as an Important Bird Area (IBA) for its breeding populations of Bridled Terns (Sterna anaethetus), Least Terns (Sterna antillarum) and Roseate Terns (Sterna dougallii) (Birdlife International, 2013).  In addition, Sale Cay and Little Sale Cay in the north-central Bank area is recognized as a high priority for conservation and protection in the Master Plan for the National Protected Areas System, for its high value for breeding seabirds (Moultrie, 2012).  The Bank is also an important staging area for migrating populations of a variety of seabirds, including species of herons, egrets, ibis and spoonbills.

- Globally significant designations for each targeted project site are provided below in Table 3. Applications are in development by the Bahamas National Trust in collaboration with Birdlife International for Bonefish Pond and Moriah Harbour Cay National Parks to be designated as Key Biodiversity Areas (KBAs). It is expected that the review process will be completed and KBA designation will be granted to both sites by the end of 2019. These sites meet many of KBA criteria including threatened biodiversity and ecological integrity. Globally significant species found in each park including the endangered Bahama Swallow (Tachycineta cyaneolviridis) in BPNP and critically endangered Elkhorn coral (Acropora palmata). endangered Boulder Star coral (Orbicella annularis) and endangered Nassau Grouper (Epinephelus striatus) in MHCNP.

#### Table 3: Global designations of Targeted Project Sites

| Site | Designation | Description |
| --- | --- | --- |
| Andros West Side National Park | IUCN category VI – Managed Resource Protected Area; an area managed as IUCN category Ia – Sensitive Zone | The west coast of Andros is important habitat for 3 species of sea turtles - Green turtles (Chelonia mydas), Loggerheads (Caretta caretta), and Hawksbills (Eretmochelys imbricata). The sea turtle populations observed in this protected area are significant in The Bahamas and may be of regional significance in the Greater Caribbean. The Andros rock iguana (Cyclura cychlura cychlura) is endemic to Andros Island and is listed by IUCN as endangered. The sensitive zone within the Park is to be managed in order to limit human visitation. |
|  | Key Biodiversity Area | 10 breeding females of Smalltooth sawfish (Pristis pectinata). |
| Exuma Cays Land and Sea Park (ECLSP) | IUCN category II – National Park | Protects extensive marine and terrestrial ecosystems, including mangrove, corals, sand flats and coppice forest. |
|  | Important Bird Area (BS 020) | ECLSP supports a globally significant population of White-tailed tropicbird (Phaethon lepturus) primarily located on the eastern cliffs of Shroud Cay, and the northern cliffs of Warderick Wells. The breeding population of Audubon’s shearwater (Puffinus lherminieri) on Long Rock (also called Long Cay) is regionally important, as are the breeding Least terns (Sterna antillarum), primarily on Warderick Wells. The mangroves support a range of waterbirds, and the restricted-range Bahama mockingbird (Mimus gundlachii) and Thick-billed vireo (Vireo crassirostris) occur in the shrubland. |
|  | GLORES Award | The Global Ocean Refuge System (GLORES) is a Marine Conservation Institute initiative working to build a global network of effective marine protected areas to save ocean wildlife. ECLSP received the award as a blue park in 2018. |
|  | Key Biodiversity Area | Supports globally significant population of White-tailed tropicbird and regionally important breeding population of Audubon’s shearwater. |
| Lucayan National Park (LNP) | IUCN category III -Natural Monument or Feature | Contains one of the longest charted underwater cave systems in the world. |
|  | Important Bird Area (BS 001) | LNP supports 3 restricted range birds – Thick-billed Vireo (Vireo crassirostris), Bahama Swallow (Tachycineta cyaneovifidis) and Olive-capped Warbler (Dendroica piyophila) |
|  | Key Biodiversity Area | Provides habitat for globally significant bird species outlined under IBA designation. |
| Moriah Harbour Cay National Park | IUCN category VI – Managed Resource Protected Area | MHCNP showcases ecologically diverse habitats; sand flats, tidal creeks, lagoons, mangroves, coral reefs, rocky and sandy shorelines, sand dunes, blue holes, and coastal plant communities. It also encompasses important areas for spawning, nursery, nesting, and migration of marine and terrestrial species, such as Queen conch, Spiny lobster, bonefish, and White-crowned pigeon. |
| Bonefish Pond National Park | IUCN category VI – Managed Resource Protected Area | This is an area containing predominantly unmodified natural systems, managed to ensure long-term protection and maintenance of biological diversity, while also providing a sustainable flow of natural products and services to meet community needs. |

## 2.4 Threats, root causes and barrier analysis

### 2.4.1 Threats

- Threats to biodiversity in The Bahamas can be broadly classified as:

  - Natural – biological invasions, disease and natural sedimentation;

  - Human – overfishing, non-compatible development and pollution

  - Climate – storms, sea level rise, coral bleaching and global climate change

- Climate change and its impacts threaten all of the targeted project sites. Hurricanes of increased intensity due to warmer oceans can negatively impact habitats, particularly those that are already subject to degradation, as well as coastal infrastructure. Ocean acidification and sea temperature rise pose significant risk to coral reefs.

- Additional threats to targeted project sites are detailed in Table 4 below.

#### Table 4: Threats to Targeted Project Sites

| Site | Threat Type | Threat Description |
| --- | --- | --- |
| Andros West Side National Park | Natural | Invasive species impacts (from free-ranging dogs and cats, and feral pigs), including direct predation, habitat community modification, habitat degradation. |
|  | Human | Over-exploitation of commercially important fishery resources, particularly Queen conch and Nassau grouper. Unregulated sportfishing. Unregulated tourism development. Illegal commercial fishing. Illegal hunting of Andros rock iguana. |
| Exuma Cays Land and Sea Park | Natural | Invasive species impacts notably from Australian pine in terms of plant community and habitat modification/ degradation. |
|  | Human | Incompatible development inclusive of land clearing, dredging and construction. Sedimentation. Eutrophication. Recreational tourism poor practice (including from yachting); impacts include anchor damage, prop scars, groundings, and wildlife disturbance. Poaching. |
| Lucayan National Park | Natural | Invasive species impacts notably from Australian pine, Paperbark tree, and raccoons in terms of plant community and habitat modification/ degradation. |
|  | Human | Development incompatible with the cave system. Incompatible development next to the park. Impacts from cave divers. Wildlife disturbance by tourists (e.g. feeding). |
| Moriah Harbour Cay National Park | Natural | Invasive species impacts, from Australian pine and Red lionfish. In the case of the Australian Pine it is in terms of plant (and habitat) community modification. In the case of the lionfish impacts are in the context of predation and decimation of native fish communities |
|  | Human | Incompatible development, which can be sources of sedimentation and nutrient pollution. Boat groundings and sunken vessels. Anchor damage. Commercial fishing of spawning populations. |
| Bonefish Pond National Park | Natural | Invasive species impacts from Australian pine, Hawaiian inkberry, and Brazilian pepper in terms of plant (and habitat) community modification |
|  | Human | Shoreline and coastal development that can impact watershed and hydrology, inclusive of mangrove removal and dredging. Over-exploitation of fisheries resources. Eutrophication with nutrient discharge from vessels, homes, farms and businesses. Pollution into marine waters including illegal dumping of household trash and toxic substances (e.g. used engine oil). |

- Invasive species have been identified as a key threat to biodiversity globally. In The Bahamas, invasive species that pose threats to native biodiversity were identified in the 2003 and 2013 National Invasive Species Strategy (NISS). Over the past several years, a significant threat to marine species has entered the Bahamian waters in the form of the Lionfish (Pterois volitans). The numbers of lionfish have increased from 2, initially sighted in 2006, to tens of thousands throughout the Bahamian archipelago by 2009.  The lionfish is likely to have an impact not only on native biodiversity, but also on fisheries. Researchers have confirmed that these fish are feeding on commercially important juvenile and adult fish species such as the Nassau grouper (Epinephelus striatus) and it is feared that they are impacting other species as well as coral reefs through their predation of herbivores that keep the reefs free of algae. A previous GEF project on achieving a sustainable protected area system focused specifically on lionfish as an invasive and there is a Lionfish management strategy currently being implemented by the Department of Marine Resources and NGOs, such as BREEF and Friends of the Environment. The species selected for the project have been known to be particularly disastrous for indigenous plant communities and dependent fauna.  The Australian Pine (Casuarina equisetifolia) creates monocultures, causes erosion of beach dune systems, produces allelopathic compounds, and increases hurricane damage.  The Brazilian Pepper (Schinus terebinthifolius) outcompetes native vegetation to create monocultures, can cause contact dermatitis and inflammation in humans, and fruits can cause paralyzing effects on birds and grazing animals.  The Hawaiian inkberry (Scaevola taccada) displaces native coastal vegetation and causes dune destabilization. The Paperbark Tree (Melaleuca quinquenervia) alters the water table, destroys wetland habitat, and displaces native plants and animals.  These are the reasons that these species have been targeted in the Bahamas National Invasive Species Strategy (NISS) and control measures are considered of highest importance as outlined in the NBSAP for The Bahamas. This project will address control of the invasive plants within the boundaries of Lucayan National Park and Bonefish Pond National Park.

- Marine biodiversity in The Bahamas is likely threatened by tourism activities at the same scale as is estimated for other tourism regions.  Tourism has a huge economic influence in the Bahamas considering that in 2018, 6.6 million tourists visited the country.  Although to date there is no data on pollution emissions from cruise ships in Bahamian waters, it is assumed that there is some level of risk to marine ecosystems given the high volume of shipping traffic.  This is against the background that cruise ships are estimated to contribute 77% of all marine pollution worldwide. On a single voyage, a large cruise ship produces an average of 794,850 litres of sewage, 3.785 million litres of greywater, 568 litres of hazardous waste, and 8 tonnes of garbage (Wind Rose Network, 2019).  There is also risk from pollution by leisure craft also in terms of sewage, bilge oil and other waste streams.   Localized stresses on coral reefs include sewage runoff from hotels lacking proper wastewater treatment, tourism impacts such as diver damage, and destruction and/or alteration of coastal habitats for hotel and marina development. Development conflict in respect of competing tourism interest continues to be a growing issue in the country.  For example, when the Chub Cay Club and Marina (Berry Islands) was bought by a new developer, a request was made to the Government to move the boundaries of the Reserve further away from the development and to allow recreational fishing from land. Recreational fishing was granted, but boundaries of South Berry Islands Marine Reserve have not been moved.

- Northern rock iguanas are being hunted in Andros West Side National Park, which can be devastating for this endangered species. Unregulated fishing is occurring in Moriah Harbour Cay National Park.

- As a Small Island Developing State, The Bahamas has a low relief relative to mean sea level. It is threatened by the adverse impacts of climate change, including sea level rise, increasing sea surface temperatures, inundation, storm surges, the increase in the intensity and frequency of tropical processes, climate variability, and changing weather patterns. Climate-related changes in habitat include coral bleaching as a result of increasing sea surface temperatures, rising sea levels, and coastal erosion. Impacts on the marine environment specifically, will be felt across ecosystems like coral reefs, seagrass beds and mangroves due to changes in sea level. With changes to these ecosystems, we may also see changes in populations of marine and terrestrial organisms that are dependent on these ecosystems for the various services they provide.

- The islands of The Bahamas are confronted with dangerous hazards from hurricanes and the associated consequences, such as storm surges and flooding. These consequences cause the salinization of soils, which destroys crops and delays the planting season. They may also negatively impact freshwater resources. In 2004, Hurricanes Frances and Jeanne, in addition to destroying properties valued over US$200 million, severely compromised the freshwater reserves in Andros as well as in Grand Bahama. The aquifers were inundated with salt water from the storm surges associated with these hurricanes. This resulted in water shortages in Nassau, as over 50% of the New Providence potable water at the time were supplied by the freshwater wellfields on Andros. Most freshwater in New Providence is now produced through reverse osmosis.

- Other negative impacts from severe storms include leaching of chemical fertilizers from flooded soils and salt intrusion of agricultural lands. Pine forests are also affected by salt intrusion. Salt intrusion exasperates conditions of forest floors during the dry season. The forests essentially become dry, and sometimes scorched. This, in turn, raises the risk of forest fires. In March 2017, fire which began in coppice areas spread over a vast area, impacting business, homes and even the New Providence landfill. Due to the hazards to human health from fires at the landfill, several families were evacuated from homes affected by the emissions. Impacts on bird populations in the Caribbean from hurricanes include mortality from exposure to hurricane-force winds, storm surges and displacement; birds can also be impacted indirectly through loss of food supplies and nests (Wiley and Wunderle, 1993).

- Historically, agricultural practices involved slash-and-burn, inadequate crop rotation and intensive tillage of the soil. Some present-day practices are still of environmental concern. Those impacting adversely on agricultural lands include the mixing of chemicals close to wells, open trench wells for irrigation, open application of fertilizers to the ground and the indiscriminate application of fertilizers.

- There are also several environmental considerations associated with commercial farming.  Commercial farming involves large-scale water consumption. As a result of the mismanagement of various factors, such as frequency of rainfall versus irrigation scheduling and water extraction versus recharge rate, has contributed to land degradation, and as a consequence, loss of agricultural productivity.

- One of the competing factors for efficient land management has been increasing physical development, particularly touristic and commercial in nature. The land development has often led to exacerbated erosion, loss of agricultural productivity, deforestation, and deteriorating water quality, for both the marine environment and freshwater resources.

- The Bahamas faces the following key challenges related to biodiversity, particularly as they relate to meeting its commitments under the Convention on Biological Diversity:

- The depletion of Bahamian ecosystems and species: The Convention stresses conservation of the total portfolio of biological diversity to maintain the structure and function of ecosystems. Many Bahamian ecosystems and species are already depleted and under threat of further degradation and /or endangerment for example coral reefs, pinelands, and iguanas.

- The depletion of Bahamian natural resources: The Convention stresses sustainability of resource use. Many Bahamian resources are already depleted, for example, several species of commercial fish, and valuable coppice forest species, and are under threat of further degradation.

- The damage or fragmentation of natural habitats: Wildlife and fish habitats such as those provided by pine forests and coral reefs, respectively, are damaged or fragmented by economic development occurring on land and in or near water.

- The introduction of invasive alien species to The Bahamas, accidentally or intentionally, threatens the survival of native species.

### 2.4.2 Barrier analysis

Barrier 1: Lack of framework for promoting sustainable development at site level in The Bahamas islands (to be addressed by Component 1):

- A key barrier for ensuring the sustainability of current and future developments and the protection of ecosystems in the Bahamian islands is the lack of an integrated natural resource management framework among the key responsible agencies at the site level. Planning and implementation of development are carried out on a piecemeal basis. There is limited to no consideration of the ecological sensitivity of certain habitats and the need to find solutions benefitting ecosystem resilience, climate change and conservation of biodiversity as well as development. Land and natural resource management agencies have limited capacity and information to integrate biodiversity and sustainable land management (SLM) into their work. Also, while the development of the islands can and should capitalize from the capacity of these different entities, the lack of an overarching framework for consultation on the use of land, seascapes and associated resources at a local level contributes to the accelerated fragmentation and degradation of various ecosystems. The project will seek to overcome this barrier through the development of a spatially-based decision support system for INRM that can be utilized by land and natural resource management agencies. Development of ecosystem-wide zoning plans at select sites will also serve as models for expanding management to wider landscapes and seascapes.

Barrier 2: Lack of successful models of individual MPAs that overcome financial and capacity constraints through targeted investment & insufficient knowledge of what Renewable Energy (RE) can offer for MPA management effectiveness (to be addressed by Component 2):

- With the past and continual expansion of the protected area system in The Bahamas, supported by the concluded GEF Marine Protected Areas project and the ongoing The Nature Conservancy (TNC) project “Realizing the 2020 Goal”, there is a need to ensure that expansion of the protected area estate will be accompanied by strengthened operational management of new protected areas. Without addressing this aspect, there is a legitimate concern that an expanded national protected area system will be made up primarily of ‘paper parks’ – with no improvement in management and therefore continued loss of threatened species and ecosystem services to local communities. For example, financial constraints mean that participation of local communities and the general public in protected area management is limited to irregular/impromptu meetings. A key lesson from these initiatives was the need to strengthen mechanisms to achieve local community involvement; an option is the establishment of PA advisory boards. These boards would be regularly involved in the PA management and integrated into the organizational structure of BNT as a model for sustained community involvement. This concept of advisory boards has been incorporated as a component of this GEF 2020 Challenge project.

- BNT is constrained, both financially and in terms of human resources. This capacity constraint is amplified as the Bahamas National Protected Area System is expanded. While initial steps towards financial sustainability have been made with the establishment of the Bahamas Protected Area Fund (BPAF) in 2016, there is a significant financial gap to be filled and several mechanisms will need to be utilized to achieve full financial sustainability, Therefore, there is a need to showcase how selected protected areas, through upfront infrastructure investment and capacity building, can become effectively managed and in the long-term be financially sustainable. Issues such as dependency on fossil fuel for energy production, lack of pioneering projects in renewable energy (RE), lack of knowledge on the benefits of RE and lack of investment in RE, are factors limiting the country´s transition to greener solutions (such as renewable energies and energy efficient measures). In the particular case of MPAs, energy needs are only partially met and heavily reliant on diesel fueled generators. The retrofitting with renewable energies of selected facilities in protected areas is expected to add to the financial sustainability of the parks and serve as a model for future interventions towards a more effective and innovative management of protected areas.

- There is also the need to address the MPA’s financial sustainability in terms of income generation and cost management at the site level, within the framework of formal PA business planning processes for newly created MPA sites. In this way, the project approach will deliver a package of revenues and cost savings that will increase the financial sustainability of MPAs and provide a model for the national PA system.

- Another important aspect of management effectiveness is confirming that conservation goals of a protected area are being achieved. Species conservation and monitoring presently occurs in a haphazard manner, relies heavily on external experts and is hampered by lack of funding. The project will seek to establish and implement species conservation and monitoring plans for five of the targeted MPAs. The intent is that lessons learned through the project will enable such plans to be scaled up across the national PA system.

Barrier 3: Lack of capacity and inadequate experience in INRM at the local site level (to be addressed by Components 1 and 3):

- Obstacles to integrated natural resource management revealed through the capacity assessment completed during the PPG phase include:

- Fragmented approach to natural resource management

- Data availability/access, quality, and quantity

- Lack of financial resources needed for purchasing and training

- Access to necessary and up to date tools, software, and equipment

- High cost of investment for GIS software, platforms, and support

- The Bahamas does not have operational “on-the-ground” examples of integrated natural resource management at the local level. Without access to know-how, proven through demonstration, government decision-makers and resource users do not have the tools and knowledge to necessary address land degradation and make the important connections between degradation and numerous social, economic and environmental impacts and costs.

- There is a critical need to infuse new approaches into the management system – focusing on the sectors and stakeholders that are driving land degradation. This need includes three aspects:

- showcasing the rehabilitation of degraded land and establishing cost efficiencies for such rehabilitation – to be achieved through project component on IAS and ecosystem restoration;

- showcasing that particular changes to production sector practices can have beneficial outcomes both for the production sector (development) and to other land uses (conservation) – to be achieved through the project intervention in the agricultural sector targeting farms neighbouring MPAs; and

- involving communities and schools in INRM to promote education and custodianship of wider coastal landscapes – to be achieved through the pilot adoption schemes at two of the targeted MPAs.

## 2.5 Institutional, sectoral and policy context

### 2.5.1 Multilateral Environmental Agreements

- The Bahamas is signatory to several multilateral environmental agreements (MEAs). These are outlined in Table 5 below.

#### Table 5: MEAs that The Bahamas is signatory to

| United Nations Programmes and Funds |  |
| --- | --- |
| Convention on Biological Diversity (CBD) | Party |
| Cartagena Protocol on Biosafety | Party |
| United Nations Framework Convention on Climate Change (UNFCCC) | Party |
| Kyoto Protocol | Party |
| Cartagena Convention for the Protection and Development of the Marine Environment in the Wider Caribbean Region | Party |
| Oil Spills Protocol | Party |
| Land-based Sources of Marine Pollution Protocol (LBS) | Party |
| Specially Protected Areas and Wildlife Protocol (SPAW) | Party |
| Convention on International Trade in Endangered Species of Flora and Fauna (CITES) | Party |
| United Nations Convention on Combating Desertification and Drought (UNCCD) | Party |
| UN Specialised Agencies and Related Organizations |  |
| Food and Agriculture Organisation (FAO): International Plant Protection Convention | Party |
| FAO Code of Conduct for Responsible Fisheries | Member |
| International Maritime Organisation (IMO): United Nations Convention on Law of the Sea (UNCLOS) | Party |
| UN Fish Stocks Agreement (Convention and Management of Straddling Fish Stocks and Highly Migratory Fish Stocks) | Party |
| IMO International Convention for the Control and Management of Ships’ Ballast Water and Sediments (GloBallast) | Project partner |
| World Health Organization (WHO): International Health Regulations | Party |
| International Civil Aviation Organization (ICAO): Resolution A33-18 Preventing the Introduction of Invasive Alien Species | Party |
| Ramsar Convention (Convention on Wetlands of International Importance especially as Waterfowl Habitat) | Party |
| World Trade Organization (WTO) Agreement on the Application of Sanitary and Phytosanitary Measures (SPS Agreement) | WTO Observer |
| Other Relevant Memberships |  |
| Association of Caribbean States (ACS) | Member |
| Alliance of Small Island States (AOSIS) | Member |
| Caribbean Community (CARICOM) | Member |
| Caribbean Tourism Organization (CTO) | Member |

### 2.5.2 National Policies, Plans and Institutional Arrangements

- The following are policy and institutional responses and priority interventions by the lead national agencies in biodiversity and climate change that have been deemed of priority in The Bahamas.

- Biodiversity:  The lead agencies are the Ministry of Environment and Housing through the Bahamas Environment, Science and Technology (BEST) Commission, the Department of Marine Resources, and the Bahamas National Trust (BNT).

- The Ministry of Environment and Housing’s areas of responsibilities with respect to biodiversity include protection, conservation and management of the environment generally, reefs and blue holes, and forestry management. The agencies under the portfolio of the Ministry include the Bahamas Environment, Science and Technology (BEST) Commission, the Department of Environmental Health Services (DEHS), Forestry Unit, Bahamas National Geographic and Information Systems (BNGIS) Centre, and the Department of Housing. There is no enabling legislation that creates the Ministry as a statutory authority. Its legislative mandate is provided through statutes inclusive of the Environmental Health Services Act, Forestry Act, Wild Animals Protection Act and Wild Birds Protection Act.

- The BEST Commission, formed by a directive from the Chief of State in 1994, has in effect been the country’s environmental agency since 1995. BEST, a division of the Ministry of the Environment and Housing, is responsible for developing the Government of The Bahamas’ (GOB) environmental and natural resource management policies. As mandated, the BEST Commission is responsible for the administration of the EIA process, overseeing the technical review of EIAs, coordinating the public review of EIAs, and providing advice to Cabinet for consideration in their decision-making process. BEST is also the lead agency in ensuring that the GOB implements its requirements under the various international Conventions on environmental matters, such as biodiversity, climate change, wetlands, and land degradation. In this role, BEST establishes committees, drawing on appropriate staff from different government agencies, for promoting actions to implement the specific requirements of the various conventions. To date, committees have been established on wetlands, climate change and biodiversity.

- The Department of Marine Resources (DMR) is responsible for the management and development of fishery resources as well as the promotion of the growth of fisheries under the principles of sustainable use and integrated management. The Fisheries Resources (Jurisdiction & Conservation) Act 1977 establishes the Exclusive Fishery Zone (EFZ). It reflects concern with respect to conservation and management of the marine environment and its resources. It also recognizes traditional fishing rights and provides for the declaration of protected marine areas, known as marine reserves, and regulation of the fishing industry. The Department issues a number of permits and licenses in its role as manager of fisheries resources. These permits and licenses are for commercial fishing, sportfishing, use of compressors and scientific research. DMR is also tasked with enforcement of Fisheries Regulations, Marine Mammal Regulations and the Seafood Processing and Inspection Regulations. It is also the agency responsible for managing marine reserves.

- Bahamas National Geographic and Information Systems (BNGIS) Centre is responsible for spatial data for the Government of The Bahamas. Their current spatial maps provide information on subdivisions, streets, oil exploration sites, and maritime boundaries.

- Financial support for these Government programmes on biodiversity as mentioned in paragraphs 53 through 56 is from a mix of national and externally-financed sources.

- The Bahamas National Trust (BNT) was established by an Act of Parliament in 1959, which makes it unique in the NGO community. It represents a unique collaboration of governmental, private sector and scientific interests dedicated to the conservation of the natural and historic resources of The Bahamas for the enjoyment and benefit of the Bahamian people. The major mandate of the Trust is management of the National Parks System of The Bahamas. The Bahamas National Trust Act of 1959 gives the Trust the power to create by-laws to be in effect in the protected areas it establishes. These areas are of environmental, historical and/or cultural importance. The Act was amended in 2010. The Trust has a mix of sources including an endowment fund, user fee system, membership fees, international grants and a small subvention from the Government.

- The Bahamas Protected Area Fund (BPAF) is a national conservation trust fund established by an Act of Parliament in 2014. The Fund is a corporate body with a Board of Directors. It is devoted to helping ensure that Bahamian protected areas will have a dedicated sustainable source of revenue for activities such as employing staff, galvanizing local community support, and monitoring ecosystem health. It has been initially capitalized with US$2 million from The Bahamas Government and US$500,000 from GEF under the previous MPA project. The Fund is in the process of negotiating its partnership agreement with the Caribbean Biodiversity Fund (CBF) so that it can access funds available from other donors, including The Nature Conservancy. US$5 Million has been set aside for drawdowns from the CBF to The Bahamas once the agreement is signed.

- Climate Change: The lead agencies include the Ministry of Environment and Housing, the BEST Commission, the Department of Meteorology, and the National Emergency Management Agency (NEMA).

- The Ministry of Environment and Housing is the National Designated Authority for the Green Climate Fund (GCF). In this role, it has recently completed a readiness project to develop a Country Strategic Framework inclusive of a pipeline of climate change projects to be submitted to the GCF. The project also involved training of staff members from various Government agencies in modalities for accessing the GCF.

- The BEST Commission serves as the Focal Point for the United Nations Framework Convention on Climate Change (UNFCCC). In this role, it has led national efforts to complete all reporting obligations under the Convention, including the First and Second National Communications. It is currently developing the Third National Communication. BEST has also developed the National Adaptation Policy and advised the GOB on various policy decisions related to climate change and its impacts.

- The Department of Meteorology is responsible for weather forecasting for the country. The national hurricane watch and warning system is managed by this Department. They also host historical climatological data for The Bahamas and have developed several climate change models for the country, including PRECIS and SLOSH. The Department has developed a storm surge atlas for some of the islands in the country. Members of the Department have also served on the International Panel for Climate Change (IPCC) and have contributed to reports from the Panel.

- The National Emergency Management Agency (NEMA) serves as a coordinating agency for all natural, man-made, and technological hazards. The Agency was formed under the 2006 Disaster Preparedness and Response Act. Its main focus is to reduce the loss of life and the destruction of property within the Commonwealth of The Bahamas, by ensuring that there are adequate mitigation plans, community preparedness, public information and recovery coordination mechanisms to minimize the impact and recover from the various hazards. These hazards include hurricanes and associated storm surge.

- Financial support for these programmes on climate change as mentioned in paragraphs 61 through 64 is from a mix of national and externally-financed sources.

- Agencies that do not have a biodiversity or climate change mandate, but will be important to engage in the project include the Ministry of Tourism. As identified previously, the tourism sector has significantly impacted the natural environment in negative ways. The Ministry has for many decades promoted mass tourism, focusing its efforts on attracting quantities of tourists rather than quality of tourists. It offers significant concessions to the cruise ship industry and large development projects, providing many services for free (e.g. waste collection, advertising) rather than a means to generate revenue. The Ministry drafted a Sustainable Tourism Policy in 1994, but that policy has not been put into action.

## 2.6 Stakeholder mapping and analysis

- Stakeholders analysis for the project was completed and is represented below in Table 6.

Table 6: Stakeholder Analysis

| WHO | WHY |  |  |  |
| --- | --- | --- | --- | --- |
|  | Interest | Influence | Expertise | Affected |
| Public Sector |  |  |  |  |
| BEST Commission | 3 | 3 | 3 | 3 |
| University of The Bahamas | 1 | 2 | 2 | 1 |
| Department of Agriculture | 1 | 2 | 2 | 2 |
| Department of Marine Resources | 1 | 2 | 3 | 3 |
| Department of Meteorology | 2 | 2 | 3 | 2 |
| Department of Forestry | 3 | 2 | 3 | 2 |
| Ministry of the Environment and Housing | 3 | 3 | 3 | 3 |
| Ministry of Finance | 1 | 3 | 1 | 1 |
| Ministry of Tourism | 1 | 3 | 1 | 2 |
| Ministry of Works and Urban Development | 1 | 3 | 2 | 1 |
| Royal Bahamas Defence Force (RBDF) | 1 | 2 | 2 | 2 |
| Bahamas Power & Light (BPL) | 2 | 3 | 3 | 2 |
| Non-Governmental Organizations |  |  |  |  |
| Bahamas National Trust (BNT) | 3 | 3 | 3 | 3 |
| Bahamas Reef Environment Educational Foundation (BREEF) | 3 | 2 | 2 | 3 |
| Caribbean Biodiversity Fund (CBF) | 3 | 2 | 2 | 2 |
| Inter-American Institute for Cooperation on Agriculture (IICA) | 3 | 3 | 3 | 2 |
| The Nature Conservancy (TNC) | 3 | 2 | 3 | 3 |
| Private Sector |  |  |  |  |
| Grand Bahama Port Authority | 2 | 3 | 2 | 2 |
| Grand Bahama Power | 2 | 3 | 3 | 2 |
| Members of the Public |  |  |  |  |
| Local Government Councils (Andros, Exuma, Berry Islands and Grand Bahama) | 1 | 3 | 1 | 3 |
| Residents of North & South Andros | 2 | 3 | 1 | 3 |
| Residents of Georgetown, Exuma | 2 | 3 | 1 | 3 |
| Residents of Chub Cay, Berry Islands | 1 | 3 | 1 | 3 |
| Residents of Freeport, Grand Bahama | 3 | 3 | 1 | 3 |
| Residents of New Providence | 3 | 3 | 1 | 3 |

- Based on the results of the stakeholder analysis, key stakeholders, their roles and project activities they should be involved in are identified below in Table 7. All other stakeholders identified in Table 7 will be consulted throughout the project on various project activities as needed.

#### Table 7: Key Stakeholder Involvement

| Stakeholders | Role | Involvement in Project |
| --- | --- | --- |
| BEST Commission, Ministry of Housing and Environment | Lead overall Executing Agency and co-financier | Involvement in project steering committee. Liaison agency with UNEP and GEF as Operational Focal Point. Lead agency on liaison with residents of New Providence. |
| Bahamas National Trust (BNT) | Partner executing agency and co-financier | Involvement in project steering committee. Project management on a day-to-day basis, guiding all project interventions in national parks. Lead agency on liaison with residents of Andros and Grand Bahama. |
| Inter-American Institute for Cooperation on Agriculture (IICA) | Partner executing agency and co-financier | Involvement in project steering committee. Project management on a day-to-day basis, guiding all project interventions on farms. Lead agency on liaison with farming community. |
| Ministry of Environment and Housing | Consultative partner and co-financier | Financial oversight. Liaison with high levels of Government (such as Cabinet). Expert advice on climate change and renewable energy. |
| Department of Forestry | Consultative partner | Expert advice on ecosystem monitoring and engagement with production sectors. |
| Ministry of Tourism | Consultative partner | Advice on tourism development plans for The Bahamas. Engagement on incorporation of project outputs into planning and development mechanism of the Ministry of Tourism. |
| Bahamas Power & Light (BPL) | Consultative partner | Expert advice on energy conservation and renewable energy Participation in energy-related project interventions. |
| Grand Bahama Power Company | Consultative partner | Expert advice on energy conservation and renewable energy Participation in energy-related project interventions. |
| The Nature Conservancy Bahamas Office | Consultative partner and co-financier | Expert advice on conservation matters. Participation in conservation-related project interventions. |
| Bahamas Reef Environment Educational Foundation (BREEF) | Consultative partner | Expert advice on marine and education matters. Participation in marine- and education-related project interventions. |
| Residents of Andros (North & South), Exuma (Georgetown), Berry islands (Chub Cay), Grand Bahama (Freeport) and New Providence | Stakeholders | Involvement in all project interventions on their respective islands, including PA management advisory boards, management plan development, species conservation and monitoring, and MPA adoption schemes. Beneficiaries of the project through skills gained from project training activities and ecosystem services provided by MPAs. |
| Local Government Councils in Andros, Exuma, Berry Islands and Grand Bahama | Stakeholders | Involvement in all project interventions on their respective islands, including management plan development, species conservation and monitoring, and MPA adoption schemes. |
| Farming community | Stakeholders | Involvement in project interventions related to reducing the use of agricultural chemicals. Beneficiaries of the project through skills and increased awareness about chemicals and safer alternatives gained from project training activities. |
| Ministry of Works and Urban Development (MOWUD) | Stakeholders | Involvement in project interventions related to RE and EE. |
| Caribbean Biodiversity Fund (CBF) | Consultative & co-financier | Expert advice on conservation matters, particularly as it relates to business planning and sustainable finance. |

## 2.7 Baseline analysis and gaps

- Baseline information about each targeted project site was detailed in section 2.2. Recommendations related to gaps from Rapid Ecological Assessments (REAs) and other surveys of the sites are outlined below:

- Andros West Side National Park – Protected area planning should focus on species management, habitat protection and water quality protection. Protection should include prohibition of direct habitat impacts and alterations of freshwater flow patterns. Maintaining freshwater flow and tidal movements are essential for ensuring the AWSNP ecosystem will continue to function as a nursery system. Continued research into the biophysical characterization of west Andros is needed. More detailed mapping in the southwest and transitional brackish areas are recommended. Several species-specific surveys are needed (e.g. Smalltooth sawfish and bonefish). A monitoring station should be established for tides and documenting long-term sea level rise. A monitoring and evaluation programme should be established to assess the impact that protection is having on habitats, natural resources and human use of the area. An ecosystem approach is needed to ensure bonefish life cycle is protected. Control of feral hogs is vital to protection of iguana populations. Bonefish guides should be involved in data collection on flamingo and marine turtle populations.

- Exuma Cays Land and Sea Park – Utilization of sustainable energy and building standards is a priority in expansion of infrastructure at the Park. Invasive species removal and relocation plan needs to occur. A research and monitoring programme for natural communities needs to be developed. A data management system is needed for natural and cultural resource data. A system needs to be established for measuring, evaluating and mitigating visitor impacts.

- Lucayan National Park – A monitoring programme needs to be developed to expand the baseline inventory of terrestrial and marine habitats and species, and to track management effectiveness. A carrying capacity study should be conducted to aid in visitor management at the Park. A survey of the cave system is needed. A GIS database should be developed of natural and cultural resources in the Park. A business plan needs to be developed for the Park aimed at raising funds to finance management plan goals and objectives. The volunteer programme needs to be revised to assist with park management in a number of areas, including scientific research and conservation of natural resources.

- Moriah Harbour Cay National Park – A regional branch should be developed to support on-the-ground management of the Park and aid in advancing sustainable financing. Overall improvement in management effectiveness, including infrastructure, development of an ecosystem zoning plan, staffing and education and awareness activities in local community.

- Bonefish Pond National Park – There needs to be ecosystem-based zoning to protect important nursery functions provided by the Park. Mangrove restoration can improve the nursery function of the Park, increase biodiversity, aesthetics and improve buffering function during storms and hurricanes.

- This Challenge of 2020 Project will complement the following active programs and projects being implemented by the Bahamas National Trust in target MPAs:

- Andros West Side National Park – A feasibility assessment has been completed on the restoration of a creek in the park.

- Exuma Cays Land and Sea Park – Aspects of the business plan are being implemented.

- Lucayan National Park – IAS removal and control for Australian pine has begun on the shoreline.

- Moriah Harbour Cay National Park – Implementation of aspects of the management plan have included installation of mooring buoys and signage.

- Bonefish Pond National Park – There has been restoration of approximately 0.8 ha (2 acres) of mangroves inclusive of planting of seedlings.

### 2.7.1 Baseline for Spatially-based Decision Support System

- The Bahamas has lagged behind the global trend but has experienced a rise in spatially related data in the past decade. The establishment of the Bahamas National Geographic Information System (BNGIS) Centre has assisted in this regard. The use of Global Positioning Systems (GPS), aerial and satellite imagery, and remote sensing has increased nationally, but a lack of available data is still an obstacle to integrated management and sound decision-making based.

- Despite the availability of spatially related data, access to data has been a particular challenge across the archipelago. Many critical datasets still exist in hard-copy format, including land use/ownership maps and climate-related data. Some data exist in electronic format, but are not available in georeferenced formats and cannot be incorporated into spatial analysis. These include census and demographic data and some fisheries data.

- ﻿There has been widespread development of desktop or personal computer systems at the global level, as more user-friendly and standardized interfaces have entered mainstream. While the variety and number of GIS and SDSS consumers have increased worldwide, this has not been the case in The Bahamas. Many organizations in The Bahamas recognize the potential of using spatial data and software for managing and mapping purposes, and for addressing analytical questions. Some lack the resources or political will to take advantage of the technologies, while others experience social, policy, and other barriers to adopting new technologies. Those that do have the capacity are often limited by data availability and access.

- There are several challenges in identifying a SDSS for the BNPAS. Firstly, the system needs to meet the needs of a diverse user group, within multiple government and non-governmental organisations responsible for protected areas (PA), and each with differing mandates, levels of data availability, usage and needs. Natural resource management in The Bahamas has followed a fragmented approach which strongly influences decision-making processes. These processes are not optimal because of fragmentation of knowledge and data between agencies responsible for biodiversity. This fragmentation requires an integrated solution that is systematic, collection and managing data from multiple sources, one that has social and political buy-in to make it a success.

- Interviews with stakeholders identified generally what capacity exists within institutions, which entities need capacity developed, and how a solution like the proposed SDSS can benefit and address capacity needs.  Of the institutions engaged, the majority have low to partial capacity as it relates to access to and data and information on natural resources or MPAs, mapping, and GIS. Some organisations have sufficient capacity to execute their mandates and missions, and others have no capacity. There is little information available for the target sites identified in the PPG, highlighting a critical need for a central information system in the form of a SDSS.

### 2.7.2 Baseline for Business Plans

- A business plan is a “strategic way to plan and communicate the financial future of a PA”. They are an opportunity to formalize responsibilities, balance competing needs, make an MPA self-sufficient and increase management effectiveness. The business planning process helps strategic planning, by helping to make informed decisions about MPA costs and needs and how to allocate resources to best meet the protected area’s goals, and to target particular programs which help to achieve MPA objectives for additional funds and staff.

- In The Bahamas, there have been three (3) significant analyses done at a system level which estimated funding needs, financing gaps and developed sources of funding for protected areas themselves or their management bodies. These are outlined below in the order they were undertaken.

- Sustainable Finance Plan for Bahamas National Protected Area System (Higgins, 2008) A Sustainable Finance Plan was completed in 2008 for the entire national PA system and also for BNT.  It included an overview of the PA system, a financial gap analysis based on a needs assessment for improved PA management, a market analysis of goods and services from natural resources, and an analysis of potential sustainable financing mechanisms (SFMs).  This Sustainable Finance Plan included a 10-year action plan as an annex which outlined financial and management actions necessary for each year, including viable funding mechanisms.  Out of the recommendations from this plan, the Bahamas Protected Area Fund (BPAF) was established. Overall, the Sustainable Finance Plan identifies a need for $13.1 million and a gap of $7.1 million.  The 2008 Sustainable Finance Plan and the subsequent update, the 2017 Sustainable Financing for the Bahamas Protected Area System make the case for national-level harmonization of user fees for the PA system in the country and different but complementary efforts at various sites across the archipelago under the umbrella of a national framework.

- BNT cost verification study (MacLeod, 2016) - In 2016, the Inter-American Development Bank (IDB) commissioned a cost verification study to estimate capital and annual operating needs for BNT managed parks for optimal level of management (following a financial audit in 2015).  The study showed that BNT needed to increase its annual budget to effectively manage 32 national parks from $4.5 million to $10 million after an investment of $25 million.  This analysis informs the business plan.  These projections were reviewed and compared to 2015 audited financial statements and reviewed in the context of business and management plans and validated with the help of an external construction expert to validate the estimated costs. Some of the estimated costs identified through the 2016 study are described below in Table 8.

#### Table 8: Estimated Costs for Targeted Project Sites and Centralized Costs for BNT

(taken from MacLeod, 2016)

| MPA | Staff Needs | Annual operations costs | Investment needs |
| --- | --- | --- | --- |
| Andros West Side | 5 | $870,000 | $2.54 million |
| ECLSP | 7 | $683,000 | $4.21 million |
| Moriah Harbour Cay | 4 | $233,000 | $421,000 |
| Lucayan NP | 5 | $371,000 | $1.69 million |
| Bonefish Pond NP | 4 | $306,000 | $1.24 million |
| Centralized costs for BNT | Staff Needs | Annual operations costs | Investment needs |
| Parks department | 7 | $295,000 | $75,000 |
| Science | 11 | $372,000 | $103,000 |
| Education | 8 | $980,000 | $50,000 |
| Support staff | 25 | $1.97 million | $5 million |

- Report on Sustainable Financing for the Bahamas Protected Area System (Blue Earth, 2017) - The report established a financial gap analysis for two scenarios - under the status quo and for effective management. It also identified ways to reduce the gap and potential revenue options, although the authors state that there is considerable uncertainty related to future funding.  Costs per acre were calculated for areas with good data and then extrapolated to areas without data and potential future parks.

- PA management bodies currently derive funds from a variety of sources in the amount of B$8.3 million; this does not include in-kind funding from partners. It is estimated that this funding may increase to $15.4 million by 2027.  Expected costs per acre under status quo are about $8.6 million ($0.02- $2.13 per acre) and expected to increase to $35.4 million in 2027.  Effective management needs were estimated to be $18.8 million currently ($4.79 – $6.59 per acre), increasing to more than $155 million in 2027. This is presented in the context of the $900 million in benefits from the PA system estimated by NatCap based on tourism, coastal protection and spiny lobster nurseries (rising to $5 billion if carbon sequestration is included).  Given current funding, the financial gap is $10.5 million currently and projected to be $140 million in 2027 and is presented for each agency. The gap increases in years when new MPAs are expected to be implemented and is greatest for BNT, due to numerous MPAs expected to be implemented over the next decade. The report also outlines cost sharing or saving measures developed with stakeholder consultations.

- For the 5 targeted project sites, there is a disparity in the extent and comprehensiveness of management and business planning, including the development of budget requirements and potential sustainable finance mechanisms (Table 9).  See Annex C for further information as well as annotated bibliographies for each document.

#### Table 9: Summary of Sources of Financial Information for Targeted Project Sites

| Site | Year of Management Plan Publication | Source of Operational and investment cost requirements | Source and extent of SFM development and implementation | Business Plan development (year published |
| --- | --- | --- | --- | --- |
| AWSNP | 2013 | Investment and operations costs over 10 years for each program in management plan and cost verification report | Island-wide ideas from Hargreaves-Allen, 2010, but undeveloped | None |
| ECLSP | 2006 | In cost verification report and business plan | In business plan, partly implemented | Business Plan (2012) |
| LNP | 2009 | In cost verification report and business plan | In draft business plan but not implemented | Draft business plan (2017) |
| MHCNP | 2019 | Estimates from cost verification report used in management plan | 4 SFM ideas outlined in management plan | None |
| BPNP | 2015 | Basic costs in management plan and more detail in cost verification report | 4 SFM ideas outlined in management plan | None |

- The two parks for which business plans will be developed have very limited funding available currently. Moriah Harbor Cay has not had any funds available to date for active management. It has recently benefitted from two grants.  In 2018, the Oceans 5 project provided a one-off payment of $20,000 for the development of a management plan, including stakeholder consultations.  In 2019, a $30,000 grant has been awarded by the National Fish and Wildlife Foundation (NFWF) to improve park demarcation, increase awareness of park benefits, and increase community engagement. Lucayan National Park had a budget of $151,000 in 2018 of which half comes from on-site revenues; these are mainly entrance fees (79%) but also donations, memberships, events and merchandise sales.  Revenues were used to fund staff (38%) and very limited activities to support tourist visitation.  On-site revenue collection at both parks would assist in generating funds for on-going management.

### 2.7.3 Baseline for Renewable Energy

- The introduction of renewable energy and energy efficiency options within the Bahamas National Protected Area System is closely aligned with the country’s National Energy Policy goals. Goal 3 of the Bahamas National Energy Policy 2013-2033 outlines the Government’s strategy as it relates to energy alternative programs:

“The Bahamas will become a world leader in the development and implementation of sustainable energy opportunities and continuously pursue a wide range of well-researched and regulated, environmentally sensitive and sustainable energy programs, built upon the geographical, climatic and economic strengths.”

- The abovementioned goal promotes sustainable energy, with due consideration for reliable well-researched alternative energy options, that preserve and protect the environment, combat climate change, and enhance economic viability. The goal of increasing the percentage of renewables in the energy mix to 30% by 2030 for The Bahamas is a formidable task. However, the increased promotion of and dependence on renewable energy will lessen the environmental impact, reduce the national carbon footprint and reduce greenhouse gas emissions.

- Renewable Energy Potential - Technical Considerations:

In estimating the potential of renewable energy for power generation, only RE technologies presently mature and generally feasible under the conditions of targeted project sites have been considered. The following strategies within MPAs were explored:

- Solar power - The high solar irradiation is favorable for generating power with Photovoltaic (PV) power plants. PV can also be integrated into buildings or on green-field applications.

- Wind power - The wind regime for the entire Bahamas is generally uniform with prevailing eastern winds all year round.

- Ocean energy – The three potential sources of ocean energy being considered are wave energy, tidal energy and ocean thermal.

- Bio-Energy - This utilizes energy crops to provide fuels for power plants. Three common species that qualify for cultivation as solid biofuels in The Bahamas are sugar cane, bamboo and pine trees. Taking into consideration the ecological disadvantages of growing sugar cane and the technological restrictions, it is not recommended to grow sugar cane as solid biofuel feedstock near to Protected Areas.

## 2.8 Linkages with other GEF and non-GEF interventions

- The project’s components align with the components of the forthcoming GEF funded UNEP implemented project entitled “Implementing Integrated Land, Water and Wastewater Management in The Bahamas” (Bahamas IWEco Project) which will be running concurrently.  These components are:

  - Maintenance of ecosystem health through biodiversity inventory, watershed management plan, restoration methodology, restoration of East Grand Bahama ecosystem and sustainable livelihoods in ecotourism production sector;

  - Strengthening of national environmental monitoring and evaluation systems through development of a monitoring and evaluation methodology, standards for ecotourism production sector and standards for the fisheries production sector;

  - Strengthening of the enabling environment in support of policy, legislative and institutional reforms and increase of capacity for sustainable natural resource management; and

  - Enhancing knowledge exchange, best practices, replication and stakeholder involvement in natural resource management. Coordination on this component of IWEco and the Challenge of 2020 project would benefit both projects.

Under the IWEco project, The Bahamas will become a part of the regional network established under the Regional IWEco project and benefit from tools developed under the regional project.

- The Bahamas has been identified as a project site for Phase 2 of Blue Finance on Financial and Legal Arrangements.  The intent is to engage Blue Finance as an international partner.  An invitation will be extended to engage the team with responsibility for the Caribbean region to participate as appropriate in providing technical guidance and facilitate innovative mobilization of resources to fund PA management in the country.

- The Bahamas Protected project which runs from 2016 to 2019, is a partnership between BNT, Bahamas Reef Environment Educational Foundation (BREEF), and The Nature Conservancy (TNC) with funding from Oceans 5. It has enabled a number of interventions in marine protected areas in The Bahamas. The project seeks to achieve the following outcomes:

  - Identify priority areas for protection and design a new set of MPAs that will bring The Bahamas to its 20% goal;

  - Increase the effective management of the entire network of MPAs in The Bahamas. This outcome aligns with the Challenge of 2020 project outcome to improve management effectiveness (Outcome 2.1);

  - Support effective management of MPAs into the future through dedicated, reliable funding; and

  - Strengthen public awareness and support for MPAs.

- The Challenge of 2020 Project will be carried out in close coordination with the ongoing GEF funded project in the Bahamas portfolio - “Pine Islands - Forest/Mangrove Innovation and Integration”.  The Pine Islands project seeks to integrate biodiversity values, ecosystem services values and precepts of sustainable forest management and land-use into enhanced land-use planning in The Bahamas. Its components include establishment of a forestry assessment and monitoring system, establishment of a National Forestry Estate and development of the concept of multi-functional conservation for coastal communities. Synergies occur with the 2020 project in the following areas:

- Monitoring system development – while the Pine Island project focuses on forestry, the 2020 project looks to expand monitoring to an ecosystem level in MPAs as well as engaging local communities in monitoring. The partner agencies, including the BEST Commission, Bahamas National Trust and Department of Forestry have already agreed to coordinate activities in development of the monitoring system to ensure the objectives of both projects are met.

- Mainstreaming biodiversity conservation and sustainable use into production sectors – the Pine Islands project is seeking to do this through forestry and the 2020 project through land use planning and agriculture. Sharing of information as well as lessons learned will be important and beneficial to both projects as they seek to achieve these particular objectives.

- A recently concluded GEF-financed Marine Protected Areas project concluded with the successful establishment of the Bahamas Protected Areas Fund (BPAF), strengthening and substantially expanding the country’s MPA network (including through pilot demonstration projects) and developing an effective monitoring and evaluation regime. The project ultimately gazetted 3 million hectares of new protected areas and marine reserves, exceeding the target of 10% (2.5 million hectares) coverage of the marine environment.  The project also established a monitoring and evaluation protocol in consultation with international scientist networks. Monitoring capacity was substantively increased through the training of 5 Reef Check local instructors, and a total of 53 persons trained under the project with 75 total Eco Divers in The Bahamas. The Atlantic Gulf Rapid Reef Assessment (AGRRA) has 3 local instructors and 27 trained individuals. The following new gazettements of marine protected areas and reserves were effected under this project:

- In Abaco: The Marls of Abaco National Park; East Abaco Creeks National Park ; Cross Harbour National Park South Abaco Blue Holes National Park; East Abaco Creeks-The Bight; East Abaco Creek – Snake Cays; East Abaco Creek – Cherokee; and South Abaco Blue Holes National Park

- In Crooked Island / Acklins: Southeast Bahamas Marine Managed Area; Bight of Acklins National Park

- In Andros: Andros Green Cay National Park; The Joulter Cays National Park; and The Cay Sal Marine Managed Area

- In Grand Bahama: The North Shore  - The Gap National Park; East Grand Bahamas National Park; Hogsty Reef Protected Area; Lucayan National Park Expansion; and Peterson Cay National Park expansion (All Grand Bahama Parks exclude Grand Bahama Development Company holdings)

- In Mayaguana: Booby Cay National Park

- In New Providence: Southwest New Providence Marine Managed Area; and Perpall Tract National Park

- In Great Exuma: Moriah Harbour Cay National Park expansion.

- The project is also aligned with the 2005 GEF-funded National Capacity Needs Self-Assessment (NCSA) Project which identified and prioritized the most critical needs for implementing the four key international environmental Conventions related to biodiversity, climate change, land degradation and wetlands (see UNEP GEF Funded project - http://www.unep.org/dgef/Portals/43/publications/file.2005-09-23(3).pdf). The NCSA report provides recommendations on how the country can enhance its capacity to meet these commitments under the Conventions. The successes of this proposed project may assist the country in revisiting the NCSA and related National Environmental Management and Action Plan (NEMAP) to determine how these may be updated since some time has passed since their development.

- Under the Cartagena Convention, the project aligns with the SPAW Protocol through its focus on protected areas, particularly as it relates to ecosystem zoning plans and species monitoring and conservation plans. The project also aligns with the LBS Protocol with its focus on reducing the negative environmental impacts from chemical fertilizer use on farms neighbouring target MPA sites.

# Section 3: Intervention Strategy (Alternative)

## 3.1 Project rationale, policy conformity and expected global environmental benefits

- The project is fully consistent and designed to deliver global environmental benefits (GEBs) under the following GEF Focal Areas:

- Biodiversity: Maintaining globally significant biodiversity and the ecosystem goods and services that are provided to Bahamian society; and

- Climate Change: Support to enable a transformational shift in the Bahamas National Protected Area System towards a low-emission and resilient development path.

- On a global scale, the coral reefs of The Bahamas comprise about 5% of the world’s total coral reef systems. ECLSP is primarily composed of five different reef types - patch, channel, windward hardbottom, and fringing. Channel reefs, as the name suggests, are located within the cuts or tidal channels separating the various islands. The size of the channel reefs within ECLSP vary considerably from less than 1 ha to well over 3 ha. These reefs serve as major conduits between Exuma Sound and shallow water habitats for juvenile grouper and Queen conch. 843 corals, representing 30 species, were observed on the offshore fringing reef of LNP. Three (3) of these coral species are listed as either Critically Endangered or Vulnerable - Staghorn coral (Acropora cervicornis), Elkhorn coral (Acropora palmate) and Pillar coral (Dendrogyracylindrus) (IUCN Red List, 2012).

- Global environmental benefits will be quantified and monitored using some of the 2013 Aichi Passport indicators. The project aligns with Aichi Biodiversity Targets 1, 5, 9 and 11 as outlined below and all target timelines are for the end of the project in 2024:

- Target 1 - Residents of neighbouring communities to the targeted project sites will be aware of the values of biodiversity in the MPAs and the steps they can take to conserve and sustainably use it;

- Target 5 - The rate of loss of natural habitats in the targeted project MPA, Lucayan National Park, will be at least halved and degradation and fragmentation significantly reduced;

- Target 9 - Invasive alien species and pathways affecting targeted project MPAs, Lucayan National Park and Bonefish Pond National Park, will be identified and prioritized, priority species will be controlled or eradicated, and measures will be in place to manage pathways to prevent their introduction and establishment;

- Target 11 – The government of The Bahamas, through the Bahamas 2020 Declaration committed at least 10% of the terrestrial, inland water, coastal and marine areas of the targeted project MPAs, Lucayan National Park, Exuma Cays Land and Sea Park and South Berry Islands Marine Reserve, to be conserved as effectively and equitably managed, ecologically representative and well-connected systems, as a part of the Bahamas National Protected Area System (it should be underscored that while the project contributes to this target, its attainment falls beyond the scope of the project given the anticipated legislative and political process that will ensue).

- Each target will be monitored using the relevant indicators in the 2013 Aichi Passport to track progress as follows:

- Target 1 – The Biodiversity Barometer will be used to survey awareness of the residents of neighbouring communities in Andros, Berry Islands, Exuma, Grand Bahama, and New Providence pre- and post-project with at least 1,000 respondents per survey;

- Target 5 – Atlantic and Gulf Rapid Reef Assessment (AGRRA) indicator will be used to assess the reefs within targeted project MPAs pre- and post-project;

- Target 9 – Trends in distribution and populations of invasive alien species, specifically Australian pine and Paperbark tree will be determined;

- Target 11 - A spatially-based decision support system for integrated natural resource management (INRM) will be developed by the end of the project for use in cross-sectoral landscape planning and management as well as policy and regulatory development. Management effectiveness will be measured using the METT for Lucayan National Park, Exuma Cays Land and Sea Park and South Berry Islands Marine Reserve.

- The Management Effectiveness Tracking Tool (METT) is a PA management effectiveness evaluation tool used in over 2,500 PAs in about 127 countries globally. It consists of a datasheet of key information on the PA and an assessment form of 30 questions. METTs for all five (5) project sites have been completed during the PPG phase to establish the baseline for management effectiveness. These scores are projected to improve through project implementation as is reflected in the Results Framework (see Appendix 4).

- Adherence to these GEF strategic objectives will also assist the country in implementing the Sustainable Development Goals (SDGs), namely:

- Goal 8 – Promote sustained, inclusive and sustainable economic growth, full and productive employment and decent work for all through achievement of Target 8.4 on improving progressively, through 2030, global resource efficiency in consumption and production and endeavour to decouple economic growth from environmental degradation, in accordance with the 10-year framework of programmes on sustainable consumption and production and Target 8.9 on devising and implementing policies to promote sustainable tourism that creates jobs and promote local culture and products by 2030.

- Goal 9 – Build resilient infrastructure, promote inclusive and sustainable industrialization and foster innovation through achievement of Target 9.4 for upgrading infrastructure and retrofit industries to make them sustainable, with increased resource-use efficiency and greater adoption of clean and environmentally sound technologies and industrial processes, with all countries taking action in accordance with their respective capabilities by 2030.

- Goal 11 - Make cities and human settlements inclusive, safe, resilient and sustainable through achievement of Target 11.4 on strengthening efforts to protect and safeguard the world’s cultural and natural heritage.

- Goal 12 – Ensure sustainable consumption and production patterns through achievement of Target 12.3 on achieving the sustainable management and efficient use of natural resources by 2030 and Target 12.10 on developing and implementing tools to monitor sustainable development impacts for sustainable tourism that creates jobs and promotes local culture and products.

- Goal 13 – Take urgent action to combat climate change and its impacts through achievement of Target 13.1 on strengthening resilience and adaptive capacity to climate-related hazards and natural disasters in all countries, Target 13.2 on integrating climate change measures into national policies, strategies and planning, and Target 13.5 on promoting mechanisms for raising capacity for effective climate change-related planning and management in least developed countries and small island developing States, including focusing on women, youth and local and marginalized communities.

- Goal 14 – Conserve and sustainably use the oceans, seas and marine resources for sustainable development through achievement of Target 14.2 to sustainably manage and protect marine and coastal ecosystems to avoid significant adverse impacts, including by strengthening their resilience, and take action for their restoration in order to achieve healthy and productive oceans by 2020 and Target 14.7 on increasing the economic benefits to Small Island developing States and least developed countries from the sustainable use of marine resources, including through sustainable management of fisheries, aquaculture and tourism by 2030.

- Goal 15 – Protect, restore and promote sustainable use of terrestrial ecosystems, sustainably manage forests, combat desertification, and halt and reverse land degradation and halt biodiversity loss through achievement of Target 15.1 on ensuring the conservation, restoration and sustainable use of terrestrial and inland freshwater ecosystems and their services, in particular forests, wetlands, mountains and drylands, in line with obligations under international agreements by 2020.

- The project will create an enabling environment within the Bahamas National Protected Area System (BNPAS) for integrated landscape management across agriculture, ecotourism, fisheries, construction and conservation sectors. The integrated landscape management practices will be adopted by Government agencies and NGOs that work in the area as well as other islands in The Bahamas. The project is intended to produce a successful model of integrated landscape and seascape management that the Government of The Bahamas will replicate across the archipelago. The model can also be shared with other Small Island Developing States regionally and globally.

## 3.2 Project goal and objectives

- The primary goals of the project are:

- To mainstream Integrated Natural Resource Management systems in the management of marine protected areas and adjacent land/seascapes;

- To foster improved and more effective protected areas management approaches in five priority MPAs through demonstration and application of management and technology innovation; and

- To better integrate sustainable development considerations in MPA management through strengthened community engagement and enhanced custodianship across broader land and seascapes.

- The project objective is for the management of Marine Protected Areas (MPAs) in The Bahamas to be strengthened and integrated into broader landscape planning in order to reduce pressures on ecosystem services and biodiversity from competing resource uses.

## 3.3 Project components, activities and expected results

Component 1: Integrated Natural Resource Management systems for marine protected areas and adjacent land/seascapes

- This component will consist of two outcomes - (1) better effective planning for conservation and sustainable development in areas encompassing MPAs, and (2) development of an integrated natural resource management (INRM) framework which supports the reduction of pressures on biodiversity from competing land uses in the wider landscape.

Outcome 1.1: Better effective planning for conservation and sustainable development in areas encompassing MPAs

Output 1.1.1: Spatially-based decision support systems for INRM are available for use in cross-sectoral landscape planning & management and in policy and regulatory development

- The project will address a key barrier related to the fragmented approach to natural resource management on the islands of The Bahamas that is linked to the fact that information management and processes to share information among stakeholders for coherent and informed decision making is not currently done in an efficient manner.  The project intends to contribute to this significant challenge through the development of, and installation of a spatially-based decision support system (SDSS) making framework that serves the range of stakeholders that are concerned with natural resource management which takes into account broader sea/land planning. Through use of such a SDSS, resource management decisions, particularly related to maintenance of the value of ecosystems services to economic development will be strengthened based on enhanced capabilities to:

- Establish baseline references against which biodiversity loss and alterations can be monitored over time;

- Capture and make available improved information on protected area boundaries, species occurrences, and habitat/ecosystem types and locations;

- Audit environmental impacts due to development by relevant national authorities; and

- Carry out assessments for infrastructure development, tourism and resource extraction projects.

- The SDSS will be built around a multi-user geographic information system (GIS) at its core, drawing on the powerful capabilities of this tool, allowing users to map and analyze spatial relations associated with multiple features and variables that occupy geographical spaces of interest.  The system will be designed to appropriately control access and specify permissions for users within institutions and the general public and ensure privacy and controlled data sharing between entities.  Specifically, the SDSS will allow users to:

- Carry out spatial relational analyses based on multiple-criteria evaluations to generate decision scenarios taking into account biodiversity assets;

- Upload and archive spatial data acquired along with metadata within a centralized and inter-connected data hubs to facilitate enhanced access to users;

- Rapidly search, visualize, and map biodiversity data using satellite imagery and data captured via other means;

- Easily import and export data using popular formats;

- Create maps and other spatial outputs to disseminate to stakeholders;

- Access international biodiversity data sources specific to The Bahamas through a common data portal.

- The SDSS will have three basic components:

  - Data acquisition and integration tools

  - Data management system that allows for powerful, flexible and efficient data archive, curation and analysis

  - Data visualization and decision-support tools

- In terms of contributions to improved decision making and management of marine protected areas in the Bahamas the SDSS will:

- allow users to access spatial data on inter-alia species populations, protected area habitat and ecosystem status, spatial locations and extents, biogeographical regions, elevations and bathymetries, and coastal and marine sensitivities, abstracted from historic studies, field exercises/studies, and potentially ground-truthed where practical;

- contribute toward a single, national biodiversity database and data layer storage solution that can be that can be accessed by Government and non-Government institutions;

- provide access to scientifically sound information about conservation and sustainable development, and serve data for reporting requirements of the various multi-lateral environmental agreements to which The Bahamas is signatory;

- increase local capacity to use and apply the results of geospatial tools in planning;

- enhance institutional capacity and increased data integration among multiple scientific research institutions; and

- increase overall in-country capacity to collect, manage, validate, summarize, and disseminate biodiversity data.

- An evaluation exercise to determine the host agency for the SDSS based on nine key criteria was carried out on three agencies with mandates most closely related to natural resource management; the BEST Commission, the Bahamas National GIS Centre, and the BNT.  The evaluation revealed that the BEST Commission was most suited to be the host institution based on the quantitative and qualitative assessment of the Commission’s overall mandate, its capacity, willingness to support the project activity, and its ability to sustain the SDSS in perpetuity. The assessment was also underpinned by consultations with stakeholders, interviews with the Commission staff, a self-evaluation, and final evaluation conducted during the project development phase. Furthermore, BEST is the progenitor of all GEF activities and GEF funded reports and projects, which requires BEST to meet substantial data and reporting requirements. Beyond national budget allocations, grants pursued by BEST can allow for flexibility in allocation of funds toward enhancements of the SDSS beyond the life of the project.

- It is envisioned that the SDSS will be utilized by a broad spectrum of local, national, and international stakeholders in the public and private sector, civil society, and the general public. Interest in the biodiversity data and analysis capability of the SDSS will attract users in academia, technical, administrative, policy and decision-making roles from institutions that have mandates related to biodiversity, conservation, protected area management, scientific research, environment, land use, capital works, development and decision-makers.  Training opportunities to effectively use the SDSS and build capacities among users will be made available within the scope of the project.

- More details on contributor and user institutions and data types to be handled by the SDSS are contained in Annex B.

Outcome 1.2: Development of an integrated natural resource management (INRM) framework which supports the reduction of pressures on biodiversity from competing land uses in the wider landscape

Output 1.2.1: Ecosystem-wide Zoning Plans developed and approved for areas encompassing 5 target MPAs

- Comprehensive zoning plans will be developed for all five sites under the project.  These zoning plans will provide clearly defined and spatially explicit definitions for MPAs. Zoning can assist decision-makers with protected and management of natural resources. It allows for participatory planning with a wide spectrum of stakeholders and requires an integrated and inter-disciplinary approach to planning. It will address the issue of conflicts among different users and their uses of the area, conflicts between users and the marine environment, and the negative impacts both have on MPAs and their ability to provide ecosystem services. Having a zoning plan in place will also allow decision-makers to be proactive by planning necessary actions and shaping actions that can lead to more desirable futures. Ultimately, the zoning plans will be adopted and implemented by the Bahamas National Trust.

- The zoning plans will be developed in parallel with the development of the SDSS and will form part of the suite of data products that is integrated within the SDSS.  The zoning plans will incorporate knowledge of the spatial distribution of marine resources as well as indications of how the areas under the plan jurisdiction are being used, any special patterns of use that exist, and the conservation status of the areas. Knowledge of the environmental features and the existing conditions of the resources within and adjacent to MPAs will entail the use of relevant assessment tools depending on the nature, size and distribution of the marine resources.

- Extensive stakeholder consultations and engagement in the planning process will be facilitated by the project and will include, but not limited to, the Bahamas National Trust and Bahamas National Geographic Information Systems (BNGIS) Centre.

Component 2: Effective Protected Area Management

- This component has four outcomes; (i) improved PA management effectiveness, (ii) increased financial sustainability in two of the PAs, (iii) stable population numbers of priority species, and (iv) reduced carbon emissions from infrastructure in protected areas.

Outcome 2.1: Improved PA management effectiveness at 5 MPA sites: Moriah Harbour Cay National Park, Lucayan National Park, Exuma Cays Land and Sea Park, Andros West Side National Park and Bonefish Pond National Park

Output 2.1.1: PA Management Advisory Boards for recently established MPAs (Moriah Harbour Cay National Park and Lucayan National Park) established and provided with operational capacity

- The focus of this output is to strengthen community involvement and build a sense of ownership for improving park management capacity. Participatory PA Management Advisory Boards will be established for each of the two MPAs - Lucayan National Park and Moriah Harbour Cay National Parks, which are managed by the Bahamas National Trust (BNT).  The project will contribute to establishment of the Advisory Boards at each site, including development of the management structure that will include elements such as legal context, constitution and rules of procedures, stakeholder representation and scope of work/terms of reference.  Key management activities that PA Advisory Boards are envisioned to be involved in include resolution of user conflicts and visitor management.

- Within the organizational structure of BNT (see Figure 1), Advisory Boards would fall under the Parks Division which is responsible for the implementation of management plans. Recommended Board members for LNP are one representative from each of the stakeholder groupings; tour companies, Grand Bahama Taxi Union, hotels, the Ministry of Tourism, East Grand Bahama Local Government, the Grand Bahama Development Company and the Grand Bahama Port Authority. Recommended Board members for MHCNP include one representative from each of the stakeholder groupings; the local Government, Exuma Foundation, Elizabeth Harbour Conservation Partnership, the Ministry of Tourism, tour guides, Yachters Association, and Department of Marine Resources.  It is anticipated that the Chair of each Board be selected by Board members and BNT would function as the Secretary to the Board and provide technical support. The project will facilitate gender parity in representation on the boards.

- The project will contribute to the development of Terms of Reference for the Boards at the start of the project, along with further definition of the operating modalities. Figure 1 illustrates a proposed structure of the PA Advisory Board.

#### Figure 1: Proposed PA Advisory Board within the BNT organizational structure

- The project will support capacity building for board members to enable them to guide the management planning process and to define and achieve long-term park management goals. Training for Board members will be focused on:

  - Understanding the MPAs they are responsible for, including boundaries, representative species and habitats, conservation goals, as well as BNT organizational structure and legal mandate;

  - Resolution of conflicts between MPA users;

  - Stakeholder engagement;

  - Communications (e.g. messaging and storytelling); and

  - Fundraising.

- The project also will develop and implement a community awareness and education campaign for LNP and MHCNP. Each campaign will include general information about the specific park (e.g. boundaries, bylaws, uses, role of the Board, how persons can be involved). There is value in highlighting the existence of the Board and how persons can communicate with Board members. Priorities for each park over the next 5 years could be highlighted as well.

Output 2.1.2: Management Plans developed / updated and under implementation at 5 MPA sites

- The project will contribute to the updating and strengthening of implementation modalities of existing management plans prepared for the five MPA sites.  Revision and updating of these plans will take into account the evolving threats from within the MPAs as well as those coming from adjacent areas, in addition to defining a strategy for infrastructure management operations within the protected areas to become carbon-neutral.

- The project will contribute to the completion of the management plans for Bonefish Pond National Park (BPNP) and Lucayan National Park (LNP), neither of which currently have a management plan. The Exuma Cays Land and Sea Park (ECLSP) management plan will be updated under the project as it is more than 10 years old. Implementation of priority activities will occur in all five targeted project sites.

- Priority activities for implementation for each PA as identified by the Bahamas National Trust are as follows:

  - AWSNP – Enhance enforcement of park bye-laws, establishment of management zones as identified in the 2013 management plan, and outreach to park users;

  - BPNP – Establishment of management zones as identified in the management plan to be developed and outreach to park users;

  - ECLSP – Enhance enforcement of park bye-laws;

  - LNP – Establish visitation carrying capacity assessment in consideration that the proposed Carnival Cruise Port development will mean greater influxes of tourists to the park; and

  - MHCNP – Establishment of a user fee collection system.

Output 2.1.3: Infrastructure established and staff deployed and capacitated at 5 MPA sites

- The project will support the establishment of critical MPA infrastructure, including offices, staff quarters, visitor facilities, and docking facilities, with a preference for installing “green infrastructure”, inclusive of renewable energy systems (per Output 2.4.1) and energy efficient appliances and lighting, with low environmental impacts and to attain carbon neutrality for BPNP, ECLSP, and LNP. Infrastructure, staffing, equipment and training needs specifically identified for funding by the project for each PA are listed in Table 10.

- The parks suffer from a lack of financing and infrastructure. For example, Lucayan National Park has only one toilet and limited tourist educational materials.  Moriah Harbour Cay National Park has no infrastructure currently, although there is funding for a gazebo on Stocking Island to provide shade to support educational visits from schools.  If tourist facilities are developed, there is potential for significant revenue to be raised from entrance fees, merchandise sales and concessions.  These revenues could help to make the MPAs self-sufficient and generate funds needed for other management activities, such as outreach and education, monitoring, enforcement and threat reduction. Current budgets are insufficient to undertake these critical management activities.

#### Table 10: MPA Needs

| Site | Infrastructure | Staffing | Equipment | Training |
| --- | --- | --- | --- | --- |
| AWSNP | - Small visitor centre/kiosk (25’ x 25’) - Mooring buoys (15) - Demarcation buoys (20) - Landmarkers - Signage – standard park, interpretive & regulatory | 1 warden | - 28-ft Pontoon - 4x4 Pickup truck | Standard warden training which will be done in-house by BNT. There will also be some on-site training. Training will include: - Orientation on BNT National Parks (boundaries and conservation goals) - BNT Act and bylaws for various parks - Park policies and procedures Joint enforcement training activities with DMR, RBDF and RBPF will be explored; training would include: - Boarding and search - Arrest and detention - Developing case files - Chain of custody and securing evidence |
| BPNP | - Restrooms (standalone) - Visitor centre/small office (20’ x 20’) - Signage - Demarcation buoys (4) | 1 Warden | - 4x4 Pickup truck - 18-ft Pontoon |  |
| ECLSP | - Small outposts – 1 in the north (20’ x 20’ structure with 1 room and 1 bathroom) and 1 in the south (40’ x 60’ visitor centre with 37-gallon water catchment system) | 1 warden | - Drones for surveillance (2) |  |
| LNP | - Paved parking lot with solar lighting - Small fee collection kiosk - Restroom with small concession area | 1 warden |  |  |
| MHCNP | - Foot-trail system established on Stocking Island – ¼ mile loop trail to gazebo and access to interior pond - Visitor centre/small office - Mooring buoys (10 to 15) | 1 warden | - 28-ft boat with trailer - 4x4 Pickup truck - Drones for surveillance (2) - Digital tablet for SMART data collection and surveillance (1) |  |

Outcome 2.2: Increased financial sustainability of the Moriah Harbour Cay and Lucayan National Parks

Output 2.2.1: Business Plans developed and under implementation for Moriah Harbour Cay and Lucayan National Parks

- To support the sustainable operations of the Moriah Harbour Cay National Park (MHCNP) and Lucayan National Park (LNP), the project will undertake a complete cost analysis for the operations of these newly designated MPAs, conduct a feasibility assessment for the potential use of new user fees at the sites, and develop MPA business plans for operating the two MPAs.

- These national parks were selected based on consultations with project partners owing to that fact that the sites are easily accessible by visitors and have high visitation rates.  LNP, where there are currently 25,000 visitors a year, is also particularly likely to have greatly increased visitation in the future, with at least one major cruise ship terminal being developed near the park.  This port is anticipated to be able to accommodate two mega cruise ships at the same time, and expected to bring in an additional 1 million visitors a year to Grand Bahama as well as increasing Bahamian visitation through support of employment.  MHCNP could also generate significant visitor numbers given development of tourist facilities.

- Business plans developed for these two sites will focus on the key elements that will include descriptions of the economic, ecological and physical resources of the MPAs, market, economic and functional area analyses of required investments and recurrent expenditures under minimum sustainable management and optimal level of required funds.  The plans will also consider cost reduction strategies such as volume purchases and preventative maintenance of equipment.  Financing plans will be prepared to look at potential sustainable financing mechanisms (SFMs) and prioritise, based on agreed criteria such as social acceptability, technical feasibility and expected returns.  This will also include details for implementation steps and timelines of these SFMs.  Finally, marketing plans will be prepared which include information such as feasibility of potential services offered and pricing, promotion strategies, alliances and partnerships.   More detailed information about research and requirements for activities under this component are provided in Annex C.

- The project intervention will be done against the backdrop that application of uniform ‘national-level’ fees to support MPA management is unlikely to be suitable in the Bahamas, as political acceptability and accountability has been problematic.  Institution of tariffs and fees at national level usually require legislation changes and can be expensive to implement and enforce, unless they are tagged onto existing fees to minimize the costs of collection, registration, and general administration. There is also a history of national fees such as the environmental levy on imports, going into consolidated government funds with challenges for recovery for investment in resource conservation.  Institution of local fee (on-site) systems are preferable as they are more likely to be directly to cover MPA costs; they are more easily administered, understood, and acceptable to visitors compared to general taxes and fees (as they are location and use specific), can be used to control visitor numbers as necessary and do not need central government approval (Blackwell et al., 2013).

- Investment in infrastructure and concurrent development of business plans at these two sites provides an opportunity to help them become financially self-sufficient.  Currently both parks are limited by a lack of adequate infrastructure, which is linked to the fact that financial management and cost-recovery measures are not in place to allow for needed investments and their maintenance. LNP has only one toilet and limited tourist educational materials. Moriah Harbour Cay has no infrastructure currently, although there is funding for a gazebo on Stocking Island to provide shade to support educational visits from schools.

- Should proper service amenities be installed based on proper market analysis, an adequate fee structure along with supportive financial controls, there is potential to significantly grow revenue from entrance fees, merchandise sales and concessions that would help to generate funds needed for other management activities such as outreach and education, monitoring, enforcement and threat reduction. The correct price and type of user fees implemented at both sites will be informed by contingent valuation studies administered to visitors as part of this project.

- For the LNP, a fee structure could be based on revenue components that may include general admission, fees to view exhibits and shows, rental fees for use of equipment such as boats and facilities (such as campsites), licenses and permits for activities, such as fishing or kayaking and special service fees such as tank refills, transport and guide services.

- For MHCNP, mooring and anchorage fees can be established once moorings have been installed and vehicles purchased.  The project will contribute to the development of an on-line payment system which uses AIS (Affiliated Interactive Services), although this cannot be solely relied on due to likely mixed levels of voluntary compliance.  In addition, diving fees will be established through dive operators, who collect fees and then pass them onto the park, to reduce collection costs. Concessions could be explored with kayaking tour companies and fees from fishing guides, but there may not be enough visitors to cover transaction costs.  The Elizabeth Harbour Grant Partnership will be considered as a source of revenue.  Finally, since several of the large resorts, such as Sandals, have expressed an interest in supporting the park, a voluntary surcharge on hotel bills should be explored. This would collect a small fee, which is added onto the resort bill, of perhaps $2.  The use of these funds would be explained and tourists could opt out of paying these fees, which would increase acceptability to the resorts.  The resorts would then forward these funds to the park.

- For LNP, there exists substantial information in terms of cost estimates for necessary investments in infrastructure as well as estimates of recurrent management costs.  A draft business plan was developed back in 2017 which also contains useful information as to substitute sites, cost-saving measures and potential partners in terms of tourist operators.

Outcome 2.3: Stable population numbers of the priority species in targeted project sites

Output 2.3.1: Species Conservation and Monitoring Plans developed and priority actions (e.g. monitoring) under implementation for priority species at 5 MPA sites - Andros West Side, Lucayan, and Moriah Harbour Cay National Parks, South Berry Islands and Exuma Jewfish Cay Marine Reserves

- The project will develop a conservation and monitoring plan and associated conservation management activities for priority species at each of the five target MPAs.  The species of conservation interest are (i) Small-toothed sawfish, (ii) Velvet Sponge, (iii) Nassau Grouper, (iv) Staghorn coral, (v) Bonefish, (vi) Elkhorn coral, (vii) Spiny lobster and (viii) Queen conch.   Table 11 lists the key monitoring and proposed conservation management activities for the priority species for the five MPAs.

- These activities will be carried out in cooperation with Perry Marine Institute, Shedd Aquarium and other partners under overall supervision of the Bahamas National Trust.   The data collected will be fed into the Spatial Decision Support System developed under Component 1.

#### Table 11: Priority Species and Proposed Monitoring and Conservation Management Activities

| Site & Species | Monitoring | Conservation |
| --- | --- | --- |
| AWSNP (a) Small-toothed sawfish (b) Velvet Sponge | (a) Monitoring of sawfish numbers and movements of the species will be done by tagging large juvenile and adult small-tooth sawfish using satellite transmitters (Wildlife Computers), and acoustic transmitters and receivers. The Relative Abundance Index (RAI) will also be determined using fishery-independent surveys which is important for detecting minute changes in population size. Genetics will also be used to monitor genetic diversity and connectivity with the US population and historically caught sawfish (old rostrums in museums and hung in marinas). (b) Velvet sponge is the species of most concern for conservation. Monitoring activities will be done for all commercially important species for densities, population demographics and diversity will be monitored using modified AGRRA methodologies and monitoring growth of sponges in different areas around William’s Island, Middle Bight/South Bight and southern parts of the AWSNP | (a) Education and outreach activities on the sawfish will be conducted to raise awareness of the species and lobby the government for protections specific to the species. (b) If Velvet Sponge is in fact found as has been reported by some spongers, samples will be taken to confirm identity, some will be taken to nursery sites to grow on, and later transported throughout the park. |
| ECLSP Nassau Grouper | Densities will be determined using AGRRA surveying; some groupers will be tagged using acoustic accelerometer tags for bioenergetics research; blood/fin clips will also be collected for genetic samples; and size class distribution will be determined using stereo video survey equipment. | There will be education and outreach activities lobbying for improved management which may include changes in the minimum size for legal harvest and potentially an extension to the closed season. |
| LNP (a) Staghorn coral | (a) Distribution, densities and health of Staghorn coral will be monitored using AGRRA coral and benthic surveys, including the survival or remnant colonies of naturally occurring populations and restoration sites. | (a) Staghorn coral fragments will be collected and grown in nurseries within the park and later transplanted out. Genetics of naturally occurring and out planted colonies will be determined to assess genetic diversity in the area. Populations will be monitored during spawning time to determine if populations are reproducing in LNP |
| MHCNP Elkhorn coral | Distribution, densities and health of Elkhorn coral will be monitored using AGRRA coral and benthic surveys. | Coral fragments will be collected and grown in nurseries within the park and later transplanted out. Genetics of naturally occurring and outplanted colonies will be determined to assess genetic diversity in the area. Populations will be monitored during spawning time to determine if populations are reproducing in MHCNP |
| BPNP Spiny lobster | Collectors will be installed at certain locations throughout the Park (to compare to recruitment assessments conducted in the area as early as 2003). These collectors will monitor the number of juvenile spiny lobsters that are settling in the MPA monthly and indicate productivity of the protected area. Surveys of juvenile lobsters and benthic habitats in natural and restored areas (using modified AGRRA surveys) will also be conducted in areas within the park to assess suitable nursery habitats and examine stock recruit relationships for the area. | The evaluation of nursery habitat and lobster recruitment to restoration areas will help guide restoration efforts in other mangrove systems within MPAs in The Bahamas. |

Outcome 2.4: 2,105,539 tCO2-eq emissions from buildings in protected areas are reduced (indirect and direct impacts)

Output 2.4.1: 3 carbon neutral Marine Protected Area facilities (photovoltaic substitute for diesel generators (minimum 1,052,769.6 tCO2-equivalent direct emission reduction over 15 years) for the ECLSP´s visitors centre, Lucayan visitors centre, and Bonefish Pond´s visitors centre

- The project will seek to demonstrate via pilot installations at three sites, the social, environmental and economic feasibility of climate change mitigation through implementing innovative carbon-neutral solutions that will contribute to the effective management of marine protected areas and to reduce risks associated with the use of diesel to power facilities. Diesel is typically held in bulk storage and transferred across the marine environments to other islands for daily use; this repeated transfer processes poses a high oil-spill risk to sensitive protected area environments. The project will contribute to the installation of signage and promotion of project interventions on social media that will help create awareness among citizens and visitors alike and promote the vision of the protected area system in its drive toward more ‘green’ sustainable options.  The project will carefully document the contributions from the RE installations in the reporting of results related to CO2 emissions aversion; this information will also be available to the national stakeholders engaged in the project.  The pilots will serve as models to be scaled up to other facilities within the protected areas and across the country.

- A set of technological options to reduce reliance on diesel fuel will therefore be considered, that includes solar PV systems, energy efficient lighting (LED-based), improved windows and insulation, green roofing, and use of vegetation to aid cooling.  The following describes the proposed system installations for each of the 3 sites.

- ECLSP - For a peak daily consumption of 220 kWh, it is proposed that 100 per cent of the daily demand for the property is supplied, with any excess feeding back to charge batteries. It is proposed that install 2 Solar PV systems be installed as follows:

- A 3.6kW system to service the Welcome Centre, RBDF Outpost, Visitor Recreation Centre along with solar pathway and energy-efficient appliances and lighting. The diesel generator backup will only be utilized in emergency situations or to replenish batteries due to poor weather conditions.

- A 25kW system to service the main building (Peggy Hall) and new building, including watermaker, maintenance workshop and research area. Similar to previous system, the diesel generator backup will only be utilized in emergency situations or to replenish batteries due to poor weather conditions.

- LNP - For a peak daily consumption of 14.6 kW, it is proposed that 100 per cent of the daily demand is supplied for the property, with excess output feeding back to the power grid. A 3.6kW Solar PV system is therefore proposed, along with solar pathway and parking lot lighting, and energy-efficient appliances and lighting. The main supply from the Grand Bahama Power Company would serve as backup only to avoid need for diesel backup.

- BPNP – A 6.6kW system to service the Welcome Centre, and Electric Vehicle Charging Station (EVCS) is proposed, as well as parking lot solar lighting and solar-powered surveillance equipment. The system will include a 10kW inverter (dc to ac), solar panels, and racking system.

- Over the course of the project, consumption audits will be carried out quarterly and reported as part of the operational reports from the national park management.  The estimated carbon emission reductions will be quantified.

Component 3: MPA management integrated with sustainable development in the broader land/seascape

- This component aims to significantly engage local communities that derive direct economic benefits, in enhanced environmental stewardship of the MPAs and surrounding areas, through contributions to on-ground actions that reduce degradation and deepened appreciation of the environment.

Outcome 3.1: Enhanced provision and appreciation by neighbouring communities of the services from ecosystems in MPAs and surrounding areas as a result of (i) rehabilitation of degraded land, (ii) changes in production sector practices leading to both development and conservation objectives and (iii) fostering long-term custodianship of MPA ecosystems by communities.

Output 3.1.1: Reduced impacts from adjacent areas on MPAs through Invasive Alien Species (IAS) management and ecosystem restoration

- The project will focus on the restoration of sensitive landscapes, critical areas for maintenance of ecosystem services within the Bonefish Pond National Park and the Lucayan National Park, that have become overrun with invasive alien species.  These are areas adjacent to MPAs, particularly within the land-sea interface, with a focus on strengthening ecosystem resiliency.  The main invasives targeted for removal and control include the Australian Pine (Casuarina equisetifolia), Brazilian Pepper (Schinus terebinthifolius), Hawaiian inkberry (Scaevola taccada) and the Paperbark Tree (Melaleuca quinquenervia).  These were the priority invasive plants identified for these two project sites under the threat assessment (see Section 2.4.1). These species are also targeted in the 2003 and 2013 Bahamas National Invasive Species Strategy (NISS) and control measures are considered of highest importance as outlined in the NBSAP for The Bahamas.

- In the Bonefish Pond National Park, the project will undertake invasive species removal and control as well as restoration activities over at least 10 ha of mangroves.  The work will be done in association with the Forestry Unit as well as participants in the adoption scheme (see Output 3.1.3).  Anticipated activities will include:

- Eradicating the Australian Pine and controlling Brazilian Pepper;

- Restoration, inclusive of removal of heavy metals (copper and iron burnt cables), marine litter, garbage and construction waste;

- Enrichment planting of Red and Black mangroves along the northwest and southern boundaries of the park and areas where debris removal has occurred.  On the northern boundary of the park, there will also be restoration of Silver buttonwood;

- Signage displaying infographics will be installed to educate park visitors about the invasive removal and ecosystem restoration effort.

- Activities at Lucayan National Park will involve restoration of sand dune habitat through reestablishment of native species along the entire park boundary, inclusive of adjacent areas over approximately 90 ha. The project will include control of invasives, notably the Australian Pine and Paperbark Tree.   The work will be done by the Trust.

- The interventions will be guided by the 2003 Green Sweep Manual for IAS removal that was developed in tandem with the 2003 National Invasive Species Policy and Strategy.

- To ensure sustainability of these actions (i.e. IAS management and ecosystem restoration), the project will address the main causes of the problem that include lack of awareness about invasives and their pathways, and lack of regulations to require landowners to remove invasive plants from their property.  In this regard, signage displaying infographics will be installed along with community awareness activities (e.g. school talks, outreach at local plant nurseries). The control of IAS is no doubt an intensive and long-term process that requires commitment from many stakeholders, notably those who are in most direct contact and have influence over landscape management, such as BNT.  It is for this reason that the project intends to assist in building the capacity of stakeholders with 3 outputs under Component 3 related to community engagement.  With this investment under the project, it is expected that commitment among stakeholders will be strengthened. It is also expected that national agencies including BEST, BNT, Forestry Unit and Department of Agriculture will continue to support longer-term efforts to enhance likelihood of success.  It should be underscored that the project will foster a co-management approach between support agencies and the community, recognizing that engagement in IAS control will likely not be driven solely by revenue generation factors that may otherwise incentivize the process.

Output 3.1.2: Reduce impacts of agriculture and pollution in productive landscapes on ecosystem services and biodiversity in MPAs

- The project will support the promotion and adoption of good agricultural practices (GAPs) to help reduce the adverse impacts of land degradation and pollution of the environment with focus on AWSNP and BPNP on the islands of Andros and New Providence.  A key focus will be on integrated pest management in reducing chemical loadings to the environment.  The aim will be to encourage reduced reliance on agro-chemicals, and their safer use where required, adoption of more environmentally-friendly approaches to soil and water conservation that include establishment/refurbishment of drainage on farms and incorporation of practices to increase organic matter in the soil.

- The main activities will be centered around the building of technical capacities of farmers, technicians and extension officers, to jointly design and implement best practices through theoretical and practical training sessions, and on-farm demonstrations.  To develop a relevant and effective training and capacity building GAP programme, it will need to be informed by farmer identification, evaluation of their current farming practices and farm types (e.g. livestock), along with fertilization, pest and disease treatment measures, in terms of the type and frequency of chemical applications.  The project anticipates the participation of between 60 and 80 farmers cultivating holdings within 100 hectares over an estimated 1,618 hectares (4,000 acres). Farming plots on New Providence and Andros range in size from 1 acre to 200 acres.  Over the course of the project, the quantities and frequency of agro-chemicals applied in-field will be monitored in terms of the Treatment Frequency Index or TFI which is the number of times farmers use spray or other chemical application measures on their fields on average over the course of the year, along with the extent of implementation of improved practices.

- Important stakeholders will include livestock and crop farmers on the islands of Andros and New Providence, Extension Officers with the Department of Agriculture (DoA), Department of Marine Resources, Bahamas Agriculture and Marine Science Institute (BAMSI), Department of Environmental Health Services (DEHS), BEST Commission, Bahamas Agricultural Health and Food Safety Authority (BAHFSA) and the Department of Public Health.

- This activity will be led by the Inter-American Institute for Cooperation on Agriculture (IICA). As the specialized agency of the Inter-American System for agriculture, IICA supports the efforts of the Member States, including The Bahamas, to achieve agricultural development and rural well-being. The Institute’s 76-year history, physical presence in each country, and coordination role for many of the regional articulation mechanisms in the region gives it an unparalleled understanding of the challenges faced by the agricultural sector as well as the solutions that are effective. IICA has been operating in The Bahamas since 1998 and provides strong technical assistance to both the government and private sector.

Output 3.1.3: Pilot communities and/or schools are supporting management of two MPAs (“adoption schemes”)

- Fostering community stewardship is vital to the sustainability of marine protected areas. As an archipelago, The Bahamas’ infrastructure and other support needs for managing MPAs cannot be the responsibility of a single entity given resource constraints and the spatially distributed nature of natural resource assets over a large geographic space. To assist in the effectiveness of lead national organizations, like BNT, they need to be supported by local communities in their efforts.

- In collaboration with MPA staff, the project will help establish community support groups and provide support to strengthen existing youth environmental programmes in schools in closest proximity to AWSNP and BPNP.   The primary aim of community engagement will be two-fold; (i) to enable them to assist through citizen science approaches in species and habitat monitoring and in ecosystem restoration techniques under the guide of the Bahamas National Trust to contribute to the pool of knowledge on ecosystem status and implementation of community-based management interventions and (ii) fostering the communal-level adoption of protected areas to as to deepen the sense of environmental stewardship over resources that are being used by the community.

- The community-based species and habitat monitoring effort will entail community members assisting with monitoring activities outlined in Table 11 under Output 2.3.1. Community members will be trained in species identification, simple survey methodologies (e.g. line transects) and how to record sightings   Training will be provided by BNT in collaboration with the Perry Institute for Marine Science (PIMS).

- The main community stakeholders to be engaged at each site include:

- AWSNP – flyfishing lodge owners, guides and interns from the Bahamas Agriculture and Marine Sciences Institute (BAMSI);

- BPNP – Bahamas National Trust Collegiate Chapter at the University of the Bahamas (UB); the Collegiate Chapter will assist with outreach to neighbouring high schools, namely Anatole Rodgers Senior High School, CV Bethel Senior High School and Bahamas Academy.

- The Bahamas National Trust Collegiate chapter was established in 2016 to support national park programs and projects through involving local university students in training opportunities, educational activities and field experiences with the Bahamas National Trust. It currently operates at two tertiary institutions - UB in New Providence and BAMSI in Andros. The members of the Chapter have benefited from previous field training activities; this along with their studies majoring in natural sciences makes them an ideal group to participate in the project’s adoption schemes for Andros West Side and Bonefish Pond National Parks.

- The adoption scheme will be effected at Andros West Side and Bonefish Pond National Parks and will seek to build community buy-in and support for conservation and park management activities.  Engaging local stakeholders as trainees and participants in these “adoption schemes” will strengthen ownership of the programme by the continuity. It is expected that local stakeholders, and key partner organisations, including the BNT, TNC and the University of the Bahamas (UB) will also play a key role in the scaling up the results of this output, facilitating implementation of similar “adoption schemes” at other protected areas. Lessons from this initial experience will be documented and serve as important instruments in the scaling-up of community adoption schemes.

## 3.4 Intervention logic and key assumptions

- The project aims to conduct innovative activities on Integrated Natural Resource Management (INRM), MPA management planning, and piloting of community models for sustainable land management and renewable energies that can be scaled up to other islands in The Bahamas.

- Project interventions will enable The Bahamas to overcome barriers related to lack of an integrated natural resource management framework among the key responsible agencies at the site level, lack of successful models of individual MPAs that overcome financial and capacity constraints through targeted investment and insufficient knowledge of what Renewable Energy (RE) can offer for MPA management effectiveness, and lack of capacity and inadequate experience in INRM at the local site level.

- As a result of interventions, project outcomes will include:

  - Better effective planning for conservation and sustainable development in areas encompassing MPAs;

  - Reduction of pressures on biodiversity from competing land uses in the wider landscape informed by an INRM framework ;

  - Improved management effectiveness at five MPA sites;

  - Increased financial sustainability for Lucayan and Moriah Harbour Cay National Parks;

  - Stable population numbers for priority species in five MPA sites;

  - Reduction in emissions from buildings in protected areas; and

  - Enhanced provision and appreciation of ecosystem services in MPAs and surrounding areas by neighbouring communities.

- Through project interventions, MPAs will be taken into consideration into broader planning frameworks with INRM becoming a part of national planning and development. Management of MPAs will also be strengthened with enhanced conservation capacity created through project activities. There will be wider stakeholder engagement in MPA management, resulting in reduced ecosystem stressors. The intended overall impact of the project will be reduced pressures on and reduced degradation of ecosystem assets and services within MPAs in The Bahamas.

- A number of assumptions are made:

  - Required mechanisms to foster inter-agency participation are established early in the project implementation.

- National agencies actively participate in the design and development of the SDSS, i.e. share data and contribute to data-sharing protocols and commit to use the system. A mainstreaming process is established and incorporated within national decision-making framework. The project will trigger the process to develop a supportive regulatory environment for SDSS.

- Full support for zoning plan development will be provided by top-level decision-making levels of government. The public and other stakeholders will recognize the value of the zoning plans, which will be regarded as key to a sustainable development pathway for the country.

- Research agencies and support institutions participate in the assessment activities for the target species. Systems for data capture are mainstreamed in participating agencies. There will also be community participation in provision of data.

- There will be active participation and commitment of partners in the design, constitution and operation of PA Advisory Boards to attain improved PA management effectiveness.

- There will be full stakeholder participation in the development and upgrade of management plans for protected areas. National agencies will fully participate in critical species assessment and commit to conservation plans.

- Infrastructure procurements are facilitated in a cost-effective and timely manner. RE investments are effectively managed so as to achieve carbon neutrality goals for targeted MPAs.

- Local community and other MPA users are fully supportive of recommendations for proposed new fee structures determined for the parks, recognizing value toward maintenance and management. There is also high-level political support for this.

- Restoration activities are supported by the local communities. There is full participation in execution of on-the-ground interventions and community members commit to changes in behaviors to reduce degradation of the environment.

- Stakeholders will be able to benefit from capacity building activities developed through the project, such as their involvement in the species conservation and monitoring programme and community adoption schemes.

- National agencies, both public and non-profit, will utilize the project outputs to improve ecosystem health in the communities and islands where they work. These agencies will commit to replication of the lessons learned and successes so that the benefits may spread far beyond the targeted MPAs.

## 3.5 Risk analysis and risk management measures

- The possible risks to the project along with mitigation measures to be taken are described below in Table 12.

#### Table 12: Risks and Mitigation Strategy

| RISK |  | Risk Mitigation Strategy |
| --- | --- | --- |
| Challenges in coordination and timely action among key national stakeholders | Low/ Medium | Several of the key stakeholders are already engaged through the National Implementation Support Partnership (NISP) for the Programme of Work on Protected Areas (PoWPA), namely BEST, BNT, DMR and TNC. Regular meetings of the Project Steering Committee and participation in project activities will also aid in coordination and timely action by key stakeholders. |
| Political elections result in changed commitments to the Caribbean Challenge and/or the management of marine protected areas | Low / Medium | The project is designed to involve multiple agencies and sectors in a consultative preparatory phase, so that the project interventions are non-partisan and widely accepted. Multiple agencies and sectors will also be involved in the implementation of the project. |
| Climate change variability: A major natural disaster (such as a hurricane) strikes The Bahamas during the project, with negative impacts on MPA infrastructure, species / habitat health, etc. | Medium | The project attempts to manage this risk by supporting activities to improve climate change resiliency and reduce vulnerability to natural disasters in the MPA system and buffer zones. This is particularly true for the planned restoration interventions in Bonefish Pond and Lucayan National Parks. In the event of a major disaster occurring during the course of the project implementation, depending on assessments (under the co-financing commitments by partners), adaptive management measures will be taken in consultation with the national partners and the implementing agency to ensure that core outcomes are realized. |
| Insufficient sources of long-term finance to maintain sustainable management of project interventions | Low | The project will enhance the financial sustainability of the national protected area system by seeking to operationalize new SFMs (e.g. user fees) in addition to those already provided through the Bahamas Protected Ares Fund (BPAF) and associated drawdown of the Caribbean Biodiversity Fund (CBF. The project will strongly support the development of business plans and cost-saving strategies for targeted project sites that can be replicated across the PA system. |
| Recommendations of the ecosystem zoning plans meet difficulties in being enforced. | Medium | To mitigate the risk that zoning plans will not be implemented, a wide consultation process will precede the finalization of the plans. The Government of The Bahamas fully backs development of these zoning plans, and acknowledges the need to incorporate the use of EIA into zoning plans and consultation processes preceding the allocation of land near MPAs for development purposes. |
| Project implementation does not keep pace with anticipated workplan | Medium | One responsibility of the National Executing Agency (i.e. BEST), National Project Coordinator and Project Steering Committee is to ensure adherence to the workplan to assist project partners in overcoming challenges or delays that may impact the workplan. Timely and regular communication of the organizations and individuals involved in the project management structure will ensure that delays are not prolonged due to inaction. |
| National agencies, both public and non-profit, do not utilize project outputs to improve ecosystem health in communities and islands where they work. There is no commitment to replicate lessons learned and successes. | Low | Key agencies, both public and non-profit, have already made a commitment to work as partners for implementation of the project, including making co-financing commitments. The Master Plan for the Bahamas National Protected Area System has already been endorsed nationally and this project serves to implement components of that Plan. Agencies involved have been working to implement the Master Plan since it was endorsed in 2012. |
| There is no high-level political or local community support for proposed MPA new fee structure. | Low | The Government has demonstrated its support for sustainable financing of protected areas through enactment of the Bahamas Protected Area Fund Act legislation and financing of this Fund. It is unlikely that their support will not continue for sustainable financing mechanisms. Local communities will be engaged through PA Advisory Boards and public outreach activities in development of fees and their role in sustaining PAs. |
| Stakeholder participation in project interventions is low. | Low | Project interventions have been designed to engage as many stakeholders as possible, including PA Advisory Boards, adoption schemes, habitat restoration and ecosystem monitoring. Having these opportunities for engagement through the project will ensure stakeholders play an active role in implementation and will continue to support PAs after the project is complete. |

## 3.6 Consistency with national priorities and plans

- The Bahamas signed the Convention on Biological Diversity (CBD) on the 12th of June, 1992, and ratified it on the 2nd of September, 1993. The Bahamas developed its National Biodiversity Strategies and Action Plan (NBSAP) in 1999. The NBSAP identified the following activities as priorities for action to achieve implementation of the CBD:

- National Consultative Process was to determine the specifics of which species, ecosystems and locations are targeted for conservation activities and to create an awareness among citizens and residents of The Bahamas of the value of biodiversity to the economy and to societal well-being, and of their individual and collective responsibilities under the CBD;

- Preparation of bioregional guidelines, position papers and policy statements with respect to bioregions, major ecosystems, and critical species in The Bahamas and the role of the agriculture, fisheries and forestry sectors in conservation biodiversity;

- Planning for a system of national parks and protected areas;

- Development of monitoring and evaluation methodologies; and

- Protection or rehabilitation of threatened or degraded ecosystems and of threatened species.

- Over the past 26 years, action has been taken on all of these, but efforts will need to continue as the tasks are significant. Additionally, progress has been made on biodiversity issues not addressed in the NBSAP, inclusive of invasive alien species (IAS) management and sustainable financing for protected areas. Full details of the country profile and the NBSAP are available at the convention website at http://www.cbd.int/countries/default.shtml?country=bs. Additional biodiversity issues faced by the country include access and benefit-sharing, biosecurity (biosafety), and protection of traditional knowledge.

- The Bahamas National Invasive Species Strategy (NISS) was developed in 2003 and involved an assessment of the mechanisms existing in The Bahamas to address the invasive species issue while enabling increased public awareness and involvement in the process. Key strategic actions recommended by the NISS include development of an IAS database, training in IAS identification and handling for border control officers, legislative reform to enable specific actions on IAS, monitoring of key sites and priority species for eradication and control. The NISS also includes the National Invasive Species Policy and Codes of Conduct for the Government and other key sectors of Bahamian society, such as farms, pet stores, zoos and aquaria. The 2003 NISS was revised in 2013. The 2013 NISS includes an implementation plan spanning 10 years that includes a number of strategic actions such as reducing the threat of introductions via recreational boating and fishing and developing a monitoring system for priority sites including the targeted project sites. The 2013 Strategy will be followed during the project for any invasive species identified within the project site with invasive alien species management being included in any management plans developed for targeted project sites.

- The proposed project will contribute to the achievement of key biodiversity conservation targets outlined in the 4th National Report to the CBD, including to:

- Restore, maintain or reduce the decline of populations of species of selected taxonomic groups;

- Pathways for major potential invasive alien species controlled;

- Maintain and enhance resilience of components of biodiversity to adapt to climate change; and

- Reduce pollution and its impacts on biodiversity.

- The project is also aligned with the National Fisheries Strategic Plan. The Plan speaks to the need for public education and outreach with respect to marine resources. The project activities align with the overall vision for the fisheries sector – a vibrant fishing sector based on a healthy ecosystem developed for the benefit of current and future generations of Bahamians through ecologically sustainable practices, adequate data collection, research, management and enforcement.

- The project is consistent with the 2005 National Wetlands Policy which has a goal to conserve, restore and manage wetlands wisely in conjunction with sustainable development practices. The policy outlines strategies for managing the wetlands, education, awareness and training, ensuring sound scientific basis for management, building partnerships and international actions.

- According to The Bahamas 2015 Second National Communication on Climate Change, electricity generation and the transportation sector are the two most significant sources of greenhouse gas emissions. Whilst The Bahamas’ contribution to global greenhouse gas emissions is fairly negligible, its vulnerability to climate change is very high, and increasing. The Bahamas’ vulnerabilities are due to and exacerbated by the island’s location, topography, limited resources and economic dependence on primary production and the tourism industry. Changes in the frequency and intensity of extreme weather and climate events, such as heavy rainfall, strong winds, drought and high sea temperatures and levels, have been experienced and documented. These and other events have claimed lives, caused severe damage to infrastructure and other economic assets and adversely impacted livelihoods. These changes and their adverse consequences are projected to escalate in the near and longer terms, with negative impacts on the economy, health and safety, and food and water security.

- In recognition of the above, The Bahamas has indicated in their Intended Nationally Determined Contribution (INDC), communicated to the UNFCCC on November 17, 2015, that the country is expected to adapt to the impacts of climate change while at the same time pursuing a low-carbon pathway in conformity to growing international and public pressure for environmentally friendly development that reduces their “carbon footprint” and exposure to climate change, while also increasing energy security. Regarding adaptation, the proposed project is aligned to the INDC as adaptation measures for the specific sectors are mentioned as follows:

- Agriculture, livestock development and fisheries sector: Formulate and implement strategies and measures which will help to enhance food security and sustainable food production;

- Coastal and Marine Resources and Fisheries sector: Adopt short-, medium-, and long-term measures to protect coastlines and increase the resilience of coastal ecosystems, enforcement of setbacks, and restoration of coastal wetlands; and

- Energy sector: Promote the use of less carbon intensive fuels.

- Under mitigation measures, the INDC states the following in line with the project: “The electricity and transport sectors are the main usage sectors of fossil fuels in the country and the electricity demand is expected to increase in the medium term. Accordingly, the Government has defined the policy framework for a low carbon development plan through the National Energy Policy, that sets a target to achieve a minimum of 30% renewables in the country energy mix by 2030 and will allow for a 10% Residential Energy Self Generation Programme within the year. This comprehensive programme of efficiency improvement and energy diversification will allow The Bahamas to provide high-quality, affordable, environmentally-friendly energy and to reduce the amounts of imported oil that the country uses. Energy diversification will involve moving from a high dependence on petroleum to increase the contribution of other sources, such as renewable energy from solar, ocean and wind. Indeed, The Bahamas is well positioned to tap local renewable energy resources such as wind and sun.” and “Results of a mangrove ecosystem study on one Pine Island (Andros) indicate that approximately 5,661,077 tCO2eg may be removed from the atmosphere through the proper management of the ecosystem. Proper management will improve the functionality of our mangrove ecosystems and increase their carbon sink ability.”

- The Bahamas has formalised a National Energy Policy since 2013 that sets targets inclusive of the following:

- Achieve a minimum of 30% renewables in the country’s energy mix by 2030;

- Join the Carbon War Room “Ten Island Challenge” to deploy 20 MW of utility scale PV installations;

- Amend legislation to promote the use of alternative sources of energy and grid-tie connected systems.

- The project is also consistent with the Bahamas National Environmental Policy, National Environmental Management and Action Plan, and Bahamas 2020 Declaration (a commitment under the CBD Programme of Work on Protected Areas).

## 3.7 Incremental cost reasoning

- Without the GEF incremental intervention, the baseline as described above can be expected to follow the business-as-usual scenario or worsen. The proposed project will assist The Bahamas to fulfill obligations under the CBD, including Aichi targets, as well as objectives of its NBSAP, particularly as it related to development of monitoring and evaluation methodologies and protection or rehabilitation of threatened or degraded ecosystems and of threatened species.

- It will result in improvement of globally significant and critical ecosystems in the country, development of a model of integrated natural resource management that can be replicated across the country as well as to other SIDS, and increased capacity for its citizens, particularly resource managers. It is anticipated that the project will empower non-Governmental organizations, like the Bahamas National Trust, and local communities, to develop and execute similar project interventions in the country.

### 3.7.1 Business as usual scenario

- If the project does not occur, current practices that impair ecosystem health will continue including:

- Continued unsustainable exploitation of species as a result of poor practices as well as a lack of knowledge of species and habitats including distribution, abundance and health;

- Uniformed decision making by Central Government, Local Government, natural resource managers and local communities due to a lack of knowledge about the value of habitats through the ecosystems they provide and why this value needs to be protected, and in some cases, restored;

- Perceptions of protected areas as threats to livelihoods, leading to limited cooperation in their management; this is due to a lack of understanding of the benefits of protected areas and that not all protected areas are no-take zones, leading to suspicion and hostility when new areas are declared; and

- Limited national capacity to provide expertise necessary for ecosystem monitoring and valuation as well as for design of restoration activities.

### 3.7.2 Incremental reasoning

- Project interventions will enable the country to address the current practices that serve as barriers to achieving ecosystem health. Anticipated incremental benefits will include a decision support system which will provide relevant information to decision-makers and the BEST Commission as well as other agencies in land and sea use planning. This will ensure that land use decisions are made based on the best available information increasing the possibility that decisions will have duel conservation and development impact and that The Bahamas will move closer towards developing sustainably. With this information, zoning plans will be developed that will maximise the development and conservation benefits and allocated appropriate land/sea uses to the zones. These plans will inform MPA management plans as well as development plans in areas outside MPAs, increasing the possibility of the implementation of such plans.

- Additional support to existing local investments and efforts in the form of this GEF project will increase the management effectiveness of MPAs, which are significant for ecosystem services and as biodiversity habitat. In addition, expansion of business planning and the fee system to newly designated protected areas will generate more resources for MPA management, and therefore natural resources under these areas will have a better opportunity to be protected. The retrofitting of buildings and provision of renewable energy sources of selected facilities in protected areas are expected to add to the financial sustainability of the parks and serve as a model for future interventions towards a more effective and innovative management of protected areas.

- The analysis and restoration of productive landscapes interfaced with seascapes will offer the country possibilities to better adapt to challenges, such as climate change. In addition, the involvement of communities through demonstration pilots will support the management system of key coastal landscapes found in protected areas. This will serve as a model for future interventions and could be scaled-up.

- Emphasis will be placed on advancing gender mainstreaming within policy and capacity building in support of all the components.  Gender audits and targeted analyses to ascertain derived benefits by stakeholders will be conducted, along with training that will strengthen gender-equitable access to spatially-based decision support system, tools for managing protected areas and associated ecosystem services, and other benefits derived from project implementation. Gender data will be collected during Biodiversity Barometer survey as well as at all stakeholder meetings and training sessions. Equitable gender representation will be sought for PA Advisory Boards and adoption schemes. The project through the partners, will foster gender balance in establishment of these governance bodies whereby it is anticipated that gender considerations will filter through management regimes of protected areas in The Bahamas.  The aim will be to encourage increased empowerment among women to step more prominently into the role of protected area management.  Existing partner organizations and community-based organizations with strong gender-based agendas will be encouraged to participate in protected area management and support the process, such as the Department of Gender and Family Affairs, as well as to enable project outcomes to be carried forward in their work.  The Department is currently developing a policy on gender equality and equity for endorsement by Cabinet before the end of 2019; the policy contains commitments on increasing participation of women in national development with respect to the environment and sustainable development. It should be noted that access to capacity building opportunities within the project will be designed so at to promote equity. While men tend to dominate the agricultural sector, Bahamian women that farm have formed their own farmers’ association, Bahamas Network of Rural Women Producers (BAHNROP), which will be involved in Component 3 activities related to good agricultural practices (GAP).

## 3.8 Sustainability

- The project will result in development of an SDSS to facilitate INRM to support future decision making with respect to natural resource management and development. Users of the SDSS will have access to spatial data not previously available which should lead to decision-making that is transparent and based on sound science. The SDSS can also result in development of a user community that not only shares data, but also shares their research and lessons learned to benefit others in the community. The intent is that the SDSS will foster not only improved decision-making, but also more collaborative efforts.

- Development of the ecosystem zoning plans will contribute to national zoning protocols with natural resource management integrated into land use planning moving forward. Marine spatial planning is particularly significant in a country with a significant portion of its tourism based in the marine environment.

- The financial analyses and piloting of renewable energy interventions will provide guidance on the business potential of RE options and energy efficient applications, growing the availability of such solutions and thereby growing the overall sustainability of carbon neutral electricity supply in The Bahamas.

- The project will assist in establishing a participatory PA Management Advisory Board for each of the two new MPAs, which work will definitely contribute to the sustainability of the project results and interventions in the areas (i.e. the implementation of the management plans). The project will also develop and implement a community awareness and education campaign, which combined with community participation in decision-making through the PA Management Advisory Board, will strengthen community involvement and build a sense of ownership for improving park management capacity in the future.

- The business plans and financing strategies developed during the project will provide guidance on implementation of sustainable finance mechanisms to sustain the MPAs as well as cost-saving measures in PA management.

## 3.9 Replication

- Alternative measures such as renewable energies proposed by the project will have a high possibility of replication since they fall within the national priorities as they will tackle a current problem and deliver global environmental benefits. Further, the project will make the case that most if not all renewable energy and energy efficient applications there are cost savings influencing both main and remote island inhabitants to make the shift to carbon neutral options.

- Business planning for the two MPA sites will involve establishing a process of developing a business plan and a standardized structure and content, as well as developing sustainable finance mechanisms, which could be replicated across other MPAs.  This research and experience would reduce the cost and time needed for future business plan and sustainable finance development at other sites.  For example, through using standardized structure and content, from recommendations which would apply to other MPAs and by providing templates for agreements with universities for research or concessions with partners for revenue generation.  Sustainable financing implementation would also provide invaluable experience as to what revenue raising mechanisms are most feasible, practical and generate the most income for MPAs in The Bahamas.  Key recommendations from the 2008 Sustainable Finance Plan and 2017 update to  be realized in the project are development of a user fee system that can be extended to all protected areas, and development of a varying rate schedule covering entrance and activity fees, based on the location of each park, visitor demand and staffing requirements.  This project intends to actualize a modular approach at the national level in roll-out, targeting the PAs that have significant visitor development potential and have significant conservation and protection value. Due consideration is given to less profitable parks in the wider schemes of PA management in the country under the national framework from the completed national studies and their recommendations, including centralizing of revenue generated so that less profitable parks can receive consistent or sustained annual allocations.

- Coordinating arrangements for the project will ensure that opportunities for scaling up all facets of the project outcomes are taken up through mechanisms, such as the National Implementation Support Partnership, which is focused on implementation of the Programme of Work on Protected Areas (PoWPA) and will be involved in project implementation. In addition, the BEST Commission as the national environmental agency for The Bahamas works throughout the country and can use its role within government to facilitate scaling up the successes of the project throughout the country. The project also will involve other national agencies, such as the Bahamas National Trust responsible for all national parks; the Trust can facilitate scaling up activities throughout the country.

## 3.10 Public awareness, communications and mainstreaming strategy

- Public awareness and communication are integral to the FSP. Residents of neighbouring communities to targeted MPAs will be involved in several project activities (including the PA Advisory Boards and adoption schemes) and information about the project will be shared on project partners’ websites on a regular basis. The project will utilize various social media tools to provide regular updates to the public on project activities. Installation of signage and promotion of project interventions on social media will help to create awareness among citizens and visitors alike and promote the vision of the protected area system in its drive toward more ‘green’ sustainable options.

- Additional tools for achieving increased awareness and communications will include:

- Regular communication and meetings with Project Steering Committee representatives and those stakeholders involved in implementation of project components;

- Reporting to key agencies, including Ministry of the Environment and Housing and Ministry of Finance;

- Public availability of project deliverables including decision support system, training modules and the like; and

- Community meetings and school presentations, particularly for updates on demonstration activities and presentations on deliverables once completed.

- One of the primary opportunities for sharing of lessons learned will be through the Cartagena Convention Secretariat, particularly within the scope of the Specially Protected Areas and Wildlife (SPAW) Protocol in its meetings of the Contracting Parties (COP) under the Intergovernmental Meetings of the Cartagena Convention. The Bahamas is also in the process of reactivating its Clearing House Mechanism for biodiversity which will provide another opportunity to share lessons learned internationally, particularly with Parties to the Convention on Biological Diversity. The Caribbean Biodiversity Fund (CBF) regional meeting will enable The Bahamas to share project accomplishments and lessons learned with other Caribbean countries.

## 3.11 Environmental and social safeguards

- A screening of potential environmental and social impacts of project activities was undertaken during the PPG phase. The results of this screening are detailed in Appendix 15. No adverse impacts as a result of the execution of project activities were identified.

# Section 4: Institutional Framework and Implementation Arrangements

- The same agencies that will be involved in the project are responsible for management of natural resources and protected areas across the archipelago, namely the Ministry of the Environment and Housing and its entities, and the Bahamas National Trust. The capacity gained by these agencies through the project can be utilized for integrated natural resource management on other Bahamian islands where these agencies are active.

- The BEST Commission will serve as the National Executing Agency, and the Inter-American Institute for Cooperation on Agriculture (IICA), and Bahamas National Trust (BNT) as partner executing agencies. The BEST Commission, IICA, and BNT will serve as the Project Steering Committee (PSC) and will meet on a monthly basis.  Additional key partners, such as Bahamas Power & Light, Department of Marine Resources (DMR), The Nature Conservancy (Bahamas Office) and Bahamas Reef Environment Educational Foundation (BREEF), are envisioned to be involved in planning and execution of specific project components.  The residents of communities neighbouring the targeted project sites will be involved in all project interventions at the respective project sites. Additional project partners from the private sector, Local Government and civil society organizations can be enjoined on an as needed basis for project information sharing and review purposes.

- At the national level, BEST as the National Executing Agency (NEA), will be responsible for the implementation of the project in accordance with the components outlined in Section 3 of this document. UNEP, as the GEF Implementing Agency (IA), will be responsible for overall project supervision to ensure consistency with GEF and UNEP policies and procedures, and will provide guidance on linkages with related UNEP and GEF funded activities.

- BEST, as the NEA, will cooperate with UNEP so as to allow the organization to fulfill its responsibility as IA accountable to the GEF. To this end, free access to all relevant information will be provided by BEST. The NEA will also establish a Project Steering Committee (PSC) and appoint a National Project Coordinator (NPC). In conjunction with the NPC, BEST will establish reporting guidelines for all partners and specialists and ensure that they submit quality reports. The NEA and NPC will collaborate to prepare biannual progress reports, quarterly financial reports and annual summary progress reports for UNEP.

- Specifically, the duties of the UNEP as the Implementing Agency (IA) will include:

- Provide consistent and regular project oversight to ensure the achievement of project objectives

- Liaise between the project and the GEF Secretariat,

- Ensure that both GEF and UN Environment policy requirements and standards are applied to and are met (reporting obligations, technical, fiduciary, M&E)

- Ensure timely disbursement/sub-allotment of funds, based on the agreed legal documents

- Approve budget revision, certify fund availability and transfer funds

- Organize mid- and end-term evaluations and audit

- Provide technical support and assessment of the execution of the project

- Provide guidance if requested to main TORs/MOUs and subcontracts issued by the project

- Follow-up with NEA for progress, equipment, financial and audit reports

Certify project operational completion

- The duties of the BEST Commission as the National Executing Agency (NEA) will include:

- Establish the Project Steering Committee (PSC);

- Appoint a full-time National Project Coordinator (NPC), taking into account the sustainability of activities related to the GEF 2020 Project;

- Provide the necessary scientific, technical, financial and administrative support to the work of the PSC, working in close cooperation with relevant government agencies, the scientific community and the public and private sectors;

- Ensure that regular reports, financial accounts, and requests are submitted to UNEP;

- Review all documentation to ensure that these are consonant with National Government policies and procedures.

- The PSC will be responsible for managing the execution of project activities, inclusive of reviewing and advising on the main outputs of the project, ensuring that the environmental policy of the Government is fully reflected in the project, ensuring effective communication and decision-making, and assisting with mobilization of expertise as needed or proper execution of the project outputs. On a quarterly basis, the PSC will meet with all executing partners including BNT and IICA to fulfill steering mechanism responsibilities including: oversight of project implementation, monitoring of project progress, strategic and policy guidance and to review and approve annual work plans and budgets. A complete list of responsibilities of the PSC can be found in Appendix 10.

- The NPC will be responsible for coordinating, managing and monitoring the implementation of the project conducted by the local and international experts, consultants, subcontractors and cooperating partners. The NPC will also coordinate and oversee the preparation of the outputs of the project, manage the project budget, oversee overall resource allocation, and where relevant, submit proposals for budget revisions to the PSC and UNEP. Detailed responsibilities of the NPC are listed in Appendix 10.

- The implementation arrangements are presented below in Figure 9.

Inter-American Institute for Cooperation on Agriculture

UNEP

National Executing Agency

BEST Commission

National Project Steering Committee

National Project Coordinator

Bahamas National Trust

Targeted MPA Site Teams

Consultants

Expert Advisors

#### Figure 2: Project implementation arrangements (NOTE: The constitution of the PSC will be elaborated at project inception (to include private sector representation and community representation)

- Targeted MPA Site Teams will be comprised of staff from BNT.  Consultants and experts will also be managed by the NPC. Experts will include those specialists in their fields within PSC organizations who will be available to offer expert advice without having to be contracted to do so.

# Section 5: Stakeholder Participation

- The main stakeholders are the groups listed in Section 2.6. They include Government agencies, non-Governmental organizations and the private sector. All stakeholders were involved in the project design and will be involved in project implementation with the BEST Commission, Inter-American Institute for Cooperation on Agriculture and Bahamas National Trust as the most active.

- A number of participatory activities were undertaken during the PPG phase of the project to enable design of the project and collection of baseline data for the project:

- Stakeholder meetings to review and validate project components;

- Assessments completed by Spatial Planner, RE Specialist, Conservation Finance Specialist and Project Design Expert to develop baseline data for the project and the targeted MPAs;

- Stakeholder meetings for review of co-financing needs and options; and

- Stakeholder consultation on pilot demonstration design and costing, including selection of biological and socioeconomic indicators.

- Key stakeholders actively participated in providing inputs to the formulation of the project, agreeing on the national organizational structure for project implementation and also the budgetary requirements for successful implementation of the project activities. Additional co-finance both in kind and in cash was sought to support FSP activities.

- The overall implementation and execution arrangements for the FSP were developed in consultation with stakeholders for effective coordination of project activities at the national level as well as to enable involvement of regional and international experts.

- Stakeholders will continue to be involved in the project through the implementation phase through various outputs (e.g. PA Advisory Boards and adoption schemes) as well as mechanisms for stakeholder engagements such as public meetings, media appearances by project partners, community activities and awareness campaigns.

# Section 6: Monitoring and Evaluation Plan

- The project will follow UNEP standard monitoring, reporting and evaluation processes and procedures. Substantive and financial project reporting requirements are summarized in Appendix 8 of the project document. Reporting requirements and templates are an integral part of the UNEP legal instrument to be signed by the executing agency and UNEP.

- The project M&E plan is consistent with the GEF Monitoring and Evaluation policy. The Project Results Framework presented in Appendix 4 includes SMART indicators for each expected outcome as well as mid-term and end-of-project targets. These indicators along with the key deliverables and benchmarks included in Appendix 6 will be the main tools for assessing project implementation progress and whether project results are being achieved. The means of verification and the costs associated with obtaining the information to track the indicators are summarized in Appendix 7. Other M&E related costs are also presented in the Costed M&E Plan and are fully integrated in the overall project budget.

- The M&E plan will be reviewed and revised as necessary during the project inception workshop to ensure project stakeholders understand their roles and responsibilities vis-à-vis project monitoring and evaluation. Indicators and their means of verification may also be fine-tuned at the inception workshop. Day-to-day project monitoring is the responsibility of the project management team, but other project partners will have responsibilities to collect specific information to track the indicators. It is the responsibility of the National Project Coordinator to inform UNEP of any delays or difficulties faced during implementation so that the appropriate support or corrective measures can be adopted in a timely fashion.

- The Project Steering Committee will receive periodic reports on progress and will make recommendations to UNEP concerning the need to revise any aspects of the Results Framework or the M&E plan. Project oversight to ensure that the project meets UNEP and GEF policies and procedures is the responsibility to the Task Manager in UNEP-GEF. The Task Manager will also review the quality of draft project outputs, provide feedback to the project partners, and establish peer review procedures to ensure adequate quality of scientific and technical outputs and publications.

- Project supervision will take an adaptive management approach. The Task Manager will develop a project supervision plan at the inception of the project which will be communicated to the project partners during the inception workshop. The emphasis of the Task Manager supervision will be on outcome monitoring but without neglecting project financial management and implementation monitoring. Progress vis-à-vis delivering the agreed project global environmental benefits will be assessed with the Project Steering Committee at annual intervals. Project risks and assumptions will be regularly monitored both by project partners and UNEP. Risk assessment and rating is an integral part of the Project Implementation Review (PIR). The quality of project monitoring and evaluation will also be reviewed and rated as part of the PIR. Key financial parameters will be monitored quarterly to ensure cost-effective use of financial resources.

- In-line with UNEP Evaluation Policy and the GEF’s Monitoring and Evaluation Policy the project will be subject to a Terminal Evaluation and, additionally, a Mid-Term Review will be commissioned and launched by the Project Manager in the third quarter of 2021 as indicated in the project milestones. The possibility of a Mid-Term Evaluation will be discussed with the Evaluation Office. The review will include all parameters recommended by the GEF Evaluation Office for terminal evaluations and will verify information gathered through the GEF tracking tools, as relevant. The review will be carried out using a participatory approach whereby parties that may benefit or be affected by the project will be consulted. Such parties were identified during the stakeholder analysis (see section 5 of the project document). The Project Steering Committee will participate in the mid-term review and develop a management response to the evaluation recommendations along with an implementation plan. It is the responsibility of the UNEP Task Manager to monitor whether the agreed recommendations are being implemented.

- The Evaluation Office will be responsible for the Terminal Evaluation (TE) and will liaise with the Task Manager and Executing Agency(ies) throughout the process.  The TE will provide an independent assessment of project performance (in terms of relevance, effectiveness and efficiency), and determine the likelihood of impact and sustainability. It will have two primary purposes: (i) to provide evidence of results to meet accountability requirements, and (ii) to promote learning, feedback, and knowledge sharing through results and lessons learned among UNEP, the GEF, executing partners and other stakeholders. The direct costs of the evaluation will be charged against the project evaluation budget.  The Terminal Evaluation will be initiated no earlier than six months prior to the operational completion of project activities and, if a follow-on phase of the project is envisaged, should be completed prior to completion of the project and the submission of the follow-on proposal.  The draft TE report will be sent by the Evaluation Office to project stakeholders for comment. Formal comments on the report will be shared by the Evaluation Office in an open and transparent manner. The project performance will be assessed against standard evaluation criteria using a six-point rating scheme. The final determination of project ratings will be made by the Evaluation Office when the report is finalised and further reviewed by the GEF Independent Evaluation Office upon submission.  The evaluation report will be publicly disclosed and may be followed by a recommendation compliance process. The standard terms of reference for the terminal evaluation are included in Appendix 10. These will be adjusted to the special needs of the project.

- The GEF tracking tools are attached as Appendix 14. These will be updated at mid-term and at the end of the project and will be made available to the GEF Secretariat along with the project PIR report. As mentioned above the mid-term and terminal evaluation will verify the information of the tracking tool.

# Section 7: Project Financing and Budget

- The overall project budget is presented in detail in Appendix 1 (Budget by project components and UNEP budget lines) and Appendix 2 (Co-financing by source and UNEP budget lines).

## 7.1 Overall project budget

#### Table 13: Summary GEF budget for project implementation by Year

| Years | Amount Requested from GEF (USD) |
| --- | --- |
| Year 1 | 1,872,582 |
| Year 2 | 2,005,269 |
| Year 3 | 1,581,831 |
| Year 4 | 444,255 |
| Year 5 | 339,067 |
| Total | 6,243,004 |

#### Table 14: Summary GEF budget for project implementation by Component

| Components | Amount Requested from GEF (USD) |
| --- | --- |
| Component 1 | 1,281,000 |
| Component 2 | 4,249,618 |
| Component 3 | 319,600 |
| Monitoring & Evaluation | 95,500 |
| Project Management | 297,286 |
| Total | 6,243,004 |

## 7.2 Project co-financing

#### Table 15: Project Co-financing

| Co-Financing Partners | Amount (USD) |
| --- | --- |
| Ministry of the Environment & Housing | 3,000,000 |
| The Nature Conservancy | 606,000 |
| Caribbean Biodiversity Fund | 50,000 |
| Bahamas National Trust | 4.927,836 |
| Perry Institute for Marine Science | 1,300,000 |
| Shedd Aquarium | 2,088,470 |
| Total | 11,972,306 |

## 7.3 Project cost-effectiveness

- The cost-effectiveness of the project is achieved through project interventions that enable the targeted project sites to become more financially stable. For example, infrastructure, such as visitor centres, kiosks and mooring buoys, will enable the collection of user fees. Installation of renewable energy systems, solar lighting and energy-efficient appliances will assist in reducing costs of power generation which is currently occurring using diesel fuel.

- Partners have already been identified through the PPG phase and have committed cash and in-kind resources to maximize GEF funding available for the various project interventions. For example, the Shedd Aquarium has committed co-finance of its research vessel which will be utilized for species monitoring activities in the targeted project sites.

- Cost-effectiveness will also be demonstrated through the project’s ability to leverage additional resources for biodiversity and integrated natural resource management as partnerships are built with the various sectors and stakeholders, including the Inter-American Institute for Cooperation on Agriculture, Ministry of Tourism, the BNGIS Centre and the Ministry of Works.

# References

Acevedo-Rodríguez, P. and Strong, M. T. (2012). Catalogue of seed plants of the West Indies. Smithsonian Contributions to Botany, 1-1192.

AGRRA. Atlantic and Gulf Rapid Reef Assessment [Online]. University of Miami. Available: http://www.agrra.org/ [Accessed 14th February 2019].

Areces-Mallea, A. (1999). A Guide to Caribbean Vegetation Types Classification Systems and Descriptions.

BEST Commission. (2001). Bahamas Environmental Handbook. Nassau: Media Enterprises.

Blackwell, B. D., Brumbaugh, D. R., & Dahlgren, C. P. (2013). Sustainable Finance Analysis for the South Berry Islands Marine Reserve. The Nature Conservancy, Nassau, The Bahamas.

Blue Earth Consultants (2017). Final report: Sustainable Financing for the Bahamas Protected Area System.  The Nature Conservancy, Nassau, The Bahamas.

Correll, D. S. and Correll, H. B. (1982). Flora of the Bahama archipelago. J. Cramer.

Hallett, B. (2006). Birds of the Bahamas and the Turks and Caicos Islands. Macmillan Publications Limited.

Higgins, J. (2008). Sustainable Finance Plans for Effective Management of the Bahamas National System of Protected Areas.  Bahamas National Trust and The Nature Conservancy, Nassau, The Bahamas.

MacLeod, P. (2016). Cost Verification for an Effectively Managed National Parks System In The Bahamas.  Bahamas National Trust, Nassau, The Bahamas.

Moultrie, S. 2012.  Exuma Cays Land and Sea park (ECLSP) Business Plan.  HD Wells, Nassau, The Bahamas.

Pinder, C. 2017.  Draft Business Plan for the Grand Bahama Parks.  Bahamas National Trust, Nassau, The Bahamas.

Sibley, D. (2003). Sibley field guide to birds of eastern North America. Alfred A. Knopf.

Valentine-Rose, L., Layman, C. A., Arrington, D. A. and Rypel, A. L. (2007). Habitat fragmentation decreases fish secondary production in Bahamian tidal creeks. Bulletin of Marine Science, 80, 863-877.

Wiley, J and Wunderle, J.M. (1993). The effects of hurricanes on birds, with special reference to Caribbean islands. Bird Conservation International. 3(04), 319-349.

# Appendix 1: Budget by project components and UNEP budget lines

See attached Excel spreadsheet

# Appendix 2: Co-financing by source and UNEP budget lines

See attached Excel spreadsheet

# Appendix 3: Incremental cost analysis

Attached

# Appendix 4: Results Framework

Attached

# Appendix 5: Workplan and Timetable

Attached

# Appendix 6: Key deliverables and benchmarks

Attached

# Appendix 7: Costed M&E Plan

Attached

# Appendix 8: Summary of reporting requirements and responsibilities

Attached

# Appendix 9: Consultant Costs

Attached

# Appendix 10: Terms of Reference

Attached

# Appendix 11: Co-financing commitment letters from project partners

Attached

# Appendix 12: Endorsement letter of GEF National Focal Point

Attached

# Appendix 13: Draft procurement plan

Attached

# Appendix 14: Management Effectiveness Tracking Tool

Attached Excel Spreadsheets

# Appendix 15: UNEP Environmental and Social Safeguards

Attached

# Appendix 16: Theory of Change

Attached

# Annex A:  Details on Targeted Project Sites

Attached

# Annex B1:  Technical Report: Spatially-based Decision Support System

Attached

# Annex B2:  Technical Report: Ecosystem-wide Zoning Plans

Attached

# Annex C:   Meeting the Challenge of 2020 in The Bahamas. Conservation Finance Report

Attached

# Annex D:  Renewable Energy & Energy Efficiency Report

Attached

Scale: 1 – Low, 2 – Medium, 3 - High

Two regional branches exist as voluntary committees under the Bahamas National Trust; they are responsible for local management of the park, similar to PA Advisory Boards proposed under the project.

Zones identified under the 2013 Management Plan for Andros West Side include (1) Conservation zone,

(2) Sensitive resource zone, (3) Backcountry camping zone, (4) Day use zone, and (5) Park administration/visitor services zone (in communities neighbouring the Park).

Commercially important sponge species – Velvet sponge (Hippospongia gossypina), Hardhead sponge (Spongia Barbara dura), Grass sponge (Spongia tubilifera), and Wool sponge (Hippospongia lachne).

Estimate – to be confirmed during PPG