January 2023

# Disclaimer

This report has been prepared by an independent consultant and is a product of the Evaluation Office of UNEP. The findings and conclusions expressed herein do not necessarily reflect the views of Member States or the UN Environment Senior Management.

# Acknowledgements

This Mid Term Review (MTR) report was prepared for UNEP by John Kazembe – as an independent Consultant, who expresses sincere gratitude to all persons who contributed to the review process as listed in Annex 2. The Consultant thanks the field team comprising Dr Daniel Sikawa, Alice Kammwamba and Phoebe Kawawa who tirelessly assisted in data collection. Sincere gratitude is conveyed upon the Project Management Unit especially Mphatso Martha Kalemba and Dr. Lillian Chimphepo for their support in the review process. Their availability for consultations demonstrated their total commitment to the project. The Consultant hopes that the findings, conclusions, lessons learned and recommendations contained in this report will contribute to the successful completion of the next phase and to the continuous improvement in the execution of the project.

UNEP acknowledges the contribution of John Kazembe as Consultant. John Kazembe – holds a PhD in Ecology with immense applications in understanding socio-ecological dynamics for prescription of sound conservation strategies. Working as a Senior Lecturer in Lilongwe University of Agriculture and Natural Resources, under the Department of Environmental Sciences, John Kazembe offers quality consulting services in ecological project planning, environment, conservation, and biodiversity in addition to climate change and sustainable development. John Kazembe comes from a practical background of working with the Department of National Parks and Wildlife – initially served as a Research Officer for the Lengwe National Park (1996-1997) and subsequently as a Management Officer for Liwonde National Park (1998-2002). As a Research Officer, John Kazembe was responsible for monitoring of wildlife populations and habitats informing management decisions. While working as a management officer, the main responsibility involved law enforcement and administration of the park. John Kazembe is endowed with expertise in environmental policy analysis, project design and evaluation, training, and capacity development (Annex 5).

# Abbreviations

BWG				Biocontrol Working Group

CABI				Centre for Agriculture and Biosciences International

CBD				Convention on Biological Diversity

CU				Coordination Unit

DNPW				Department of National Parks and Wildlife

EAD				Environmental Affairs Department

ERRD 				Early Rapid Response and Detection

ESMP				Environmental and Social Management Plans

ESS				Environmental and Social Safeguards

GEF				Global Environmental Facility

IAS				Invasive Alien Species

MEPA				Malawi Environmental Protection Authority

MMCT				Mulanje Mountain Conservation Trust

MMFR     			Mulanje Mountain Forest Reserve

MTR				Mid Term Review

MTS				Mid-Term Strategy

NBSAP				National Biodiversity Strategy and Action Plan

NEAs				National Executing Agencies

NHBGM			National Herbarium and Botanical Gardens of Malawi

NISSAP	National Invasive Alien Species Strategy and Action Plan

NNP				Nyika National Parks

PAs				Protected Areas

PIR				Programme Implementation Review

POW				Programme of Work

ProDoc			Project Document

PSC				Project Steering Committee

UNEP				UN Environment Programme

MCFW				Malawi College of Forestry and Wildlife

FGDs				Focus Group Discussions

KIIs				Key Informant Interviews

# LIST OF TABLES

Table 1: Description of the Project Outcomes And corresponding  Outputs	2

Table 2: Output 1 Progress On National Framework For The Cross-Sectoral Management Of IAS Operational And Supporting Long-Term Development Planning.	8

Table 3: Output 2 Progress On Evidence Base Established And Communicated For IAS Prevention And Management In And Around PAs.	9

Table 4: Output 3 Progress On Two Revised Protected Area Management Plans Including Strategies And Budgets For IAS Prevention And Control.	9

Table 5: Output 4 Progress On Tested Management Plans For Four IAS, Including IAS Control And Habitat Restoration In Two PAs.	10

Table 6: Output 5 Progress On Capacity Of 80 Pa Staff Improved And Applied In The Identification And Management Of IAS.	10

Table 7: Output 6 Progress On Biocontrol Working Group Established And Operational Leading To The Introduction Of Three Host Specific And Damaging Biocontrol Agents.	11

Table 8: Output 7 Progress On Invaded Rangeland (100 Ha Total) In Buffer Zones/Agro-Ecosystems Of Two Adjoining Pa’s Cleared And Restored (Native Trees) Through Enhanced Partnerships Between Pa Staff And Farmer Communities, Including The Training Of 100 Farmers On IAS Identification And Management.	11

Table 9: Output 8 Progress On Sustainable Farming Practices Such As Farmer Managed Natural Regeneration, Conservation Agriculture, Including Crop Rotation, Crop Integration And Cover Cropping Adopted And Promoted By 50 Households As A Result Of Training And Demonstration Trials.	11

Table 10: Output 9 Progress On Communication Strategy And Outreach Campaigns Including Use Of Media, Workshops And Meetings Targeting Government Officials, Pa Staff And Affected Communities.	12

Table 11: Output 10 & 11Progress On National Information Sharing Procedures Including The Development Of A Guide On Identification And Management Of Invasive Plant Species In Malawi.	12

Table 12: Outcome 1 Progress On National IAS Policy And Improved National Capacity And Coordination Amongst Different Government Agencies And The Private Sector.	13

Table 13: Progress on Outcome 2 on Reduced IAS impacts in two PAs resulting in enhanced conservation outcomes for endangered or threatened species.	14

Table 14:  Outcome 3 progress  on  reduced IAS impacts in adjoining agro-ecosystems of MMFR and NNP contributing to improved livelihoods and biodiversity conservation.	15

Table 15: Outcome 4 progress on learnt  learnt, documented and disseminated and awareness programs established to facilitate replication and broader adoption in the Malawi PA system.	15

Table 16: Midterm Expenditure Statement	17

Table 17: Summary Of The Review Findings	21

GEF-6 PROJECT IDENTIFICATION FORM (PIF)

Project type: Medium-size Project

Type Of Trust Fund: GEF Trust Fund

For more information about GEF, visit TheGEF.org

|  |  |  | GEF ID.: 9539 | Umoja no.: GFL-11207-14AC0003-SB-010123 |  |
| --- | --- | --- | --- | --- | --- |
| Project Title |  |  | Enhancing sustainability of Protected Area systems in Malawi, and stabilizing agro-production in adjoining areas through improved IAS management |  |  |
| Duration months | Planned |  | 60 months |  |  |
|  | Extension(s) |  | Not yet decided |  |  |
| Division(s) Implementing the project |  |  | UN Environment Programme Ecosystems Division GEF Biodiversity and Land Degradation Unit Biodiversity and Land Branch |  |  |
| Name of co-implementing Agency |  |  | None |  |  |
| Executing Agency(ies) |  |  | Environmental Affairs Department in the Ministry of Natural Resources and Climate Change |  |  |
| Names of Other Project Partners |  |  | Department of Forestry, Department of National Parks and Wildlife, Lilongwe Wildlife Trust, Wildlife and Environmental Society of Malawi (WESM), Malawi College of Forestry and Wildlife, Mulanje Mountain Conservation Trust (MMCT), Peace Parks Foundation (PPF), Forestry Research Institute of Malawi (FRIM), Department of Museums and Monuments, National Herbarium and Botanical Gardens of Malawi (NHBGM), Department of Agricultural Research Services (DARS), Department of Land Resources Conservation, University of Malawi (Chancellor College), District Councils (Mulanje, Phalombe, Rumphi), CABI, Lilongwe Wildlife Trust (LWT) and Total Land Care |  |  |
| Project Type |  |  | Medium Sized Project |  |  |
| Project Scope |  |  | National |  |  |
| Region |  |  | Africa |  |  |
| Countries |  |  | Malawi |  |  |
| Programme of Work |  |  | Healthy and Productive Ecosystems, 2020-2021 |  |  |
| GEF Focal Area(s) |  |  | Biodiversity |  |  |
| UNSDCF / UNDAF linkages |  |  | The project actively contributes to 2 of the pillars identified in Malawi UNDAF; pillar 1 and 3. |  |  |
| Link to relevant SDG target(s) and SDG indicator(s) |  |  | The Project links with the following: i. Target 15.8 under Goal 15 which encourages countries to “introduce measures to prevent the introduction and significantly reduce the impact of invasive alien species on land and water ecosystems and control or eradicate the priority species.” ii. SDG 2 zero hunger – Agriculture ecosystems- (2.1.2, 2.3.1, 2.3.2 and 2.4.1) iii. SDG 6 – impact on water quality (6.5.1 and 6.6.1) iv. SDG 15- Life on Land (15.1.1, 15.1.2, 15.2.1,15.3.1, 15.4.1, 15.4.2, 15.5.1, 15.8.1 and 15.9.1) |  |  |
| GEF financing amount |  |  | US$ 1,502,511 |  |  |
| Co-financing amount |  |  | US$ 5,164,147 |  |  |
| Date of CEO Endorsement |  |  | 15 March, 2018 |  |  |
| Start of Implementation |  |  | 15 May 2018 |  |  |
| Date of first disbursement |  |  | 10 July 2018 |  |  |
| Total disbursement as of 30 June 2021 |  |  | US$ 914,231.75 |  |  |
| Total expenditure as of 30 June 2022 |  |  | US$ 812,098.00 |  |  |
| Expected Mid-Term Review Date |  |  | March to June, 2022 (yet very delayed and ongoing) |  |  |
| Completion Date |  | Planned | 31 May, 2023 |  |  |
|  |  | Revised | Not yet decided |  |  |
| Expected Terminal Evaluation Date |  |  | April to July, 2023 |  |  |
| Expected Financial Closure Date |  |  | December, 2023 |  |  |

# Contents

Disclaimer	ii

Acknowledgements	iii

Abbreviations	iv

LIST OF TABLES	v

Contents	vii

EXECUTIVE SUMMARY	viii

1.	INTRODUCTION	1

1.1.	Project Overview	1

1.2.	Aim, Objectives And Scope Of The MTR	3

3.	REVIEW METHODS	4

1.3.	Desk Review	4

1.4.	Individual Interviews	4

1.5.	Focus Group Discussions	4

4.	REVIEW FINDINGS	5

4.1.	Strategic Relevance	5

4.2.	Gender Responsiveness	6

4.3.	Environmental And Social Safeguards	7

4.4.	Effectiveness – Delivery Of Outputs And Achievement Of Outcomes	8

4.4.1.	Delivery of Outputs	8

4.4.2.	Achievement of Immediate Outcomes	12

4.5.	Financial Management	16

4.6.	Efficiency	17

4.7.	Factors and Processes Affecting Project Performance	18

4.7.1.	Project management	18

4.7.2.	Participation and country – driven processes	18

4.7.3.	Participation and public awareness	18

4.8.	Knowledge Management	18

4.9.	Sustainability	19

4.9.1.	Financial Sustainability	19

4.9.2.	Socio-Economic Risks to Sustainability	19

4.9.3.	Environmental Risks to Sustainability	20

4.10.	Monitoring and Reporting	20

5.	CONCLUSIONS AND RECOMMENDATIONS	21

5.1.	Conclusions	21

5.2.	Recommendations	23

Annex 1 - List of Consulted Individuals	24

Annex 2 – Summarised Terms Of Reference Of The Mid-Term Review For Malawi Invasive Alien Species Management Project In Malawi.	25

ANNEX 3 – DATA COLLECTION TOOL FOR THE MTR	30

Annex 4 – A List Of Stakeholders Who Attended A Validation Workshop	45

Annex 5 – Consultant Abbreviated Curriculum Vitae	46

# EXECUTIVE SUMMARY

- This MTR report provides information for fine-tuning workplans, budgets and implementation arrangements in the second half of the project, as well as introducing mechanisms towards improving project approaches and impacts, based on the project progress and the performance against the outcome indicators as specified in the ProDoc. The MTR was informed by outcomes of an inception meeting followed by a desk review and field visits to the two PAs, meeting site coordinators, beneficiaries of the project and other implementing organizations such as the District Forest Officers (DFOs), local farmers, NGOs, the Total Land Care in Rumphi and those involved in IAS management activities. Key Informant Interviews (KIIs) and Focus Group Discussions (FGDs) were part of the field meetings. To evaluate progress mid-way project implementation, the UNEP/GEF eight criteria are imposed on many aspects of the project.

- Overall Finding: Despite some challenges, the Project has made varying degrees of progress across areas of outcomes, but the overall progress can be invariably rated as Satisfactory, and that some areas need additional time for improvement to ensure attainment of the end-of-project targets for greater impacts.

- Strategic Relevance:  The project strategy is relevant with regards to both global and local contexts. The project has clear linkage to sub-programme 4 of GEF-6, the UN Environment Sub-programme(s) on Health and Productive Ecosystems (2020-2021), and the GEF-7 Biodiversity Strategy. Implementation is progressing consistent with UNEP’s Medium-Term Strategy (2022 – 2025), and the programme of work (POW) and budget (2022–2023) which also focus on responding planetary crises - biodiversity and nature loss, among others. In addition, the IAS project address the Malawi NBSAP and the Strategy for Managing Invasive Species in Africa (2021-2030). The participation of UNEP and CABI is ensuring the maintenance of linkages to the overall GEF-6 subprogram with sound technical attention. The strategic relevance is thus rated Highly Satisfactory (HS).

- Gender mainstreaming:  The project factored gender  considerations under each of the three project components. For example, the cost-benefit analysis of three ‘conflict’ species under Component 1 will assess gender-specific impacts and costs, and the role of women in their management and control of IAS through agricultural practices. The recruitment of students for training to undertake the studies considered 1 female and 2 males. Overall progress on gender integration reveals low participation of women, although exception is noted under Component 3 which achieved almost 58% participation. As for, the training of PA staff in identification of IAS only 25% (29 women 57 men) was reported.  It was observed that, large number of PA staff are men (89%). This limits the pool of women who could have participated in training sessions. Unfortunately, even in labour related activities, women directly working in the two PAs constitute only 14%, but then this was attributed to the harsh terrain and working environment that necessitate absence from homes for days which obviously does not favor women. All awareness activities have engaged women to the level of 40%. On a technical level, the MTR established that the Project Coordinator, and the Chair of the PSC are both ladies. Deliberate effort has been made to bring a lady as an Environmental, Social and Gender expert. Rating is Moderately Unsatisfactory (MU).

- Environmental and Social safeguards:  The MTR confirms that gender as much as ESS were both considered in the project design. Women participation was integrated across the three components, but implementation was inadequate. Less than 40% of the target for women participation was missed at the time of MTR. On ESS, the PIU prepared an Environmental and Social Management Plans (ESMP). The field mission did not confirm availability of the ESMPs although the PIU suggested that it is only implementation that has been limited. Contrary, MTR raises concerns over, the lack of health and safety precautions, unavailability of HIV and AIDS awareness materials, absence of site grievance redress committees, littering inside PAs, among other issues. To be more proactive, formation of site-specific committees should be encouraged. Consideration for ESS and gender is thus Moderately Unsatisfactory (MU) and urgent response is required.

- Effectiveness: The MTR examined progress over output delivery, attainment of direct outcomes and likelihood of impact under this criterion. Results confirm movement towards the right direction although delays overturn attainment of greater effectiveness.  Interestingly, all the four outcomes and 11 outputs are delivered within the provisions of the log-frame. Notably, at the time of project inception, Malawi did not have an IAS policy. The development of the NISSAP has culminated into its adoption as a comprehensive national IAS instrument. Progressively, the Project is bringing together various stakeholders in management of IAS in the country through the national and local project committees. MEPA has also established a national coordination unit to collaborate and coordinate among different Government agencies, the private sector, and NGOs. Ongoing activities are promising to have impact in reduction of the IAS impacts in and around PAs. However, the Project requires more time to achieve Component 3 on Knowledge Management, for field trials to generate conclusive results as planned. The table below summarizes progress on outputs in need of attention.

- Outputs 1 & 4 are the only ones with progress of activities within or below the completion level of 50% while the rest of the outputs (Nine outputs are way above 50% and some have reached 100%). The emergency of COVID19 which limited travel of the International Advisor, limited technical capacity of staff undertaking field trials. Overall, the MTR finds that the achievement of output-level results is Satisfactory based on recognizing of the need for more time than the planned period of project completion.

| Output | Progress on Activity |
| --- | --- |
| Output 1: National framework for the cross-sectoral management of IAS operational and supporting long-term development planning | Activity 4: Identify high risk pathways, especially those for PA’s. At the time of the MTR, this activity was rated a progress of 50%. Activity 4 activity is on course and will conclude within the project period. Activity 5: Strengthen National IAS Risk Analysis procedures and develop RA systems for PA’s. Preparatory work such as training workshop on RA and Review of existing RA Procedures. The PIR at midterm progress rated this at 40%. More technical guidance may be required to expedite progress. |
| Output 4: Tested management plans for four IAS, including IAS control and habitat restoration in two PA’s | Activity 11: Species targeted for management trials and methodologies agreed. Activity 11 has made reasonable progress. However, the results of field trials remain inconclusive due to technical errors associated with data collection. More time may be required to allow for field trials to meet expected standards. Capacity among staff may be required to continue undertaking this the field trials as required. |

- Financial Management: The MTR found that, the rate of spending is consistent with the project’s period of implementation. Delays have been observed against the agreed workplan and the delivery of some outputs including this MTR report, the slow procurement procedures and more. Consultations with UNEP suggested that financial reporting has been consistent and to adequate standards. The MTR confirms that financial management structures and processes were adequately set before the start of the project and are followed in the implementation process. There was a procurement plan in place at the onset of the project but existing procurement procedures are too bureaucratic. In terms of co-financing, at the time of the review (June 2022) the total co-financing received was $3,815,909. This has increased compared to the $1,386,538 of June 2020. This is against the planned co-financing of US$ 5,164,147. Thus, the review established that co-financing arrangement is working beyond expectation but delays in procurement has implications in the overall project performance. Hence, the rating is Moderately Satisfactory.

- Sustainability: Sustainability of the project was scrutinized on financial and economic, socio-economic, and environmental dimensions.  The findings reveal areas of uncertainty for sustainability although preliminary observation suggest movement towards the right direction.

- Economic and Financial Sustainability: The MTR field mission has established that, IAS have gained attraction from both NGOs and the private sector having long-term interests in watershed conservation and biodiversity. There is likelihood of financial and economic resources being available once the GEF assistance ends. However, these stakeholders depend on donor support as well as their business environment which are often characterized by many uncertainties. The level of revenue generation in the two PAs is currently unreliable. Hence, the MTR rates the financial and economic component of sustainability as Moderately Likely.   The MTR does not find potential political or social risks that may jeopardize sustainability of project outcomes.  On the contrary, FGDs suggested that the level of project acceptance has progressively increased among the adjoining PA communities. Although government funding in PAs is limited, the integration of IAS activities into PA Management Plans is the right direction. The Communication and Outreach Strategy, and its implementation is expected to increase the level of awareness of IAS. However, it is not clear as regards to documentation of lessons learned on a continuous basis. The integration of IAS into college curriculum targeting mid-career professionals working in PAs is a healthy intervention for sustainability. However, socio-economic change takes time and demands dedication of resources which PAs have been grappling to meet, hence Moderately Likely.

- Environmental Risks to Sustainability: Successful restoration of IAS impacted areas is has been observed during the field missions. But continuity of success is contingent upon comprehensive understanding of additional environmental determinants. Observation in the field saw the engagement of labouers in firebreak making and the MTR affirms that, this will enhance outcomes and results, so far achieved in restoration. However, in the long-term, civic education programme around PAs on the dangers of uncontrolled fire will be required besides undertaking prescribed fire operations to reduce potential impacts in the event its occurrence. Replanting of indigenous species  in MMFR will require understanding favorable climate as well.  Studies to guide successful ways of restoration on the mountain are required given that some replanted Mulanje Cedar trees are dying, and field discussions attributed this to the combined effects climatic changes and other unknown environmental risks. The rating for environmental sustainability is Moderately Likely considering observed environmental uncertainties.

- Efficiency: The project management display strong evidence of satisfactory technical and financial oversight. CABI has been ensuring quality of outputs while UNEP and EAD are efficiently managing a large group of project partners ensuring timely delivery despite stringent procurement procedures. The MTR has also gathered evidence suggesting the use of effective means to achieve project results, such as the use of country partners for co-financing and engagement of NGOs with valued added and comparative advantage in working with local contexts. NGOs are used to disseminate information reaching multiple local communities beyond those living adjacent PAs. Local consultants are used as they are relatively familiar with local contexts, yet at the same time, they are inexpensive. This component is rated Satisfactory.

- Stakeholder engagement: Strong partnerships have been observed in this project. EAD is working with various partners such as the BWB, DNPW, PPF, CCFW, the LUANAR, MZUNI and many more. The IAS project advances a country driven approach as a critical pathway to support response to IAS threats in PAs. Malawi developed a NBSAP which recognizes IAS as one of the major threats to biodiversity loss and the project addresses IAS as one of the NBSAP priority activities.  The involvement of stakeholders has also emerged in co-financing activities and public awareness, thereby contributing to the progress so far.

- The study established that, the project has lagged behind in terms of indicators on restoration of degraded areas although removal of IAS has progressed to the extent of overachieved.

| Indicator | Expected values at |  | FY2021 |
| --- | --- | --- | --- |
|  | Mid-term | End-of-project |  |
| Indicator 1.2: Terrestrial protected areas under improved management effectiveness METT scores) on 385,000 ha of 2 PAs, including 150ha inside the PAs cleared and restored of IAS: |  |  |  |
| - Mulanje Mountain Forest Reserve | 64 | 67 | 70 |
| - Nyika National Park | 66 | 69 | 72 |
| Area of land restored |  |  |  |
| Indicator 3.1: Area of degraded agricultural land restored (farmland cleared of IAS) |  | 100 ha | 0 |
| Indicator 3.2: Area of forest and forest land restored (IAS removed inside the two PAs) |  | 50 ha | 1,179 |
| Indicator 3.3: Area of natural grass and shrublands restored (adjoining rangeland enhanced forest cover) |  | 150 ha | 0 |
| Indicator 11: Number of direct beneficiaries disaggregated by gender as co-benefit of GEF investment | 125 (40% women.) | 230 (40% women) | Not recorded yet. |

- Summary, Recommendations and Lessons Learned: The project was designed to enhance sustainability of protected areas systems in Malawi, and stabilizing agro-production in adjoining areas through improved IAS management. The three components of the project are implemented with significant progress made so far to achieve the outcomes within the planned timeframe. Interviews with PIU backed by evidence from reports suggest that collaboration among partners was relatively efficient and effective in delivering project activities. Effective communication within and around PAs facilitated the sharing of knowledge and expertise between project partners. The international expert from CABI played a significant role in guiding the PIU on technical matters otherwise would have been difficult for the PAs as frontrunners. A summary of the findings and rating of project performance is displayed below.

| Criterion | Overall Rating |
| --- | --- |
| A. Strategic Relevance | Highly Satisfactory |
| 1. Alignment to MTS and POW and the GEF strategic priorities | Highly Satisfactory |
| 2. Relevance to regional, sub-regional and national environmental priorities | Highly Satisfactory |
| B. Effectiveness | Satisfactory |
| 1. Delivery of outputs | Satisfactory |
| 2. Achievement of direct outcomes | Satisfactory |
| 3. Likelihood of impact, where appropriate/feasible | Likely |
| C. Financial Management | Satisfactory |
| 1.Rate of spend | Satisfactory |
| 2.Quality and consistency of financial reporting | Satisfactory |
| D. Efficiency | Satisfactory |
| E. Monitoring and Reporting | Satisfactory |
| 1. Monitoring design and implementation | Satisfactory |
| 2.Project reporting | Satisfactory |
| F. Sustainability | Moderately Likely |
| I. Factors Affecting Performance |  |
| 1. Preparation and readiness | Satisfactory |
| 2. Quality of project management and supervision | Satisfactory |
| 3. Stakeholder participation and cooperation | Highly Satisfactory |
| 4. Responsiveness to human rights and gender equity | Moderately Unsatisfactory |
| 5. Country ownership and drivenness | Satisfactory |
| 6. Communication and public awareness | Highly Satisfactory |
| Overall project rating | Satisfactory |

Recommendation 1: The level of progress made so far in response to ESS site issues remain is a concern raised by the MTR and calls for urgent attention. Engage environmental and social safeguard expert to intermittently provide independent monitoring of ESMP implementation.

Recommendation 2: The MTR confirms that gender has been integrated across the three project components but the level of progress in implementation is below the midterm target.  The project should make deliberate efforts to increase the level of women participation in the remaining part of the project.

Recommendation 3: The design of the project should imbed activities to increase awareness among workers about gender-based violence and the dangers of STIs and HIV/AIDS and distribute condoms and IEC materials on STIs and HIV/AIDS especially those working for in PAs while away from their families.

Recommendation 4: UNEP-GEF should consider extension of the project to a period of six (6) months based on observation made in the PIR backed by outcome 3 analysis of this MTR and perspectives of some stakeholders.

Recommendation 5: During implementation, Malawi has experienced socio-economic changes including the devaluation of the local currency, the scarcity of foreign currency, the scarcity and rising costs of fuel and gas and the emergency of the COVID19 pandemic. These have negatively affected the efficient and effective delivery of the project. In line with recommendation 4 and economic changes that have affected Malawi’s economy, UNEP-GEF should consider revision of the project budget to cater for activities which will cover the six (6) months period.

Recommendation 6: The research on cost-benefit analysis of priority IAS envisages demonstrating the long-term policy direction in dealing with the problem of conflicts of interest relating to invasive alien plants that have commercial value. Notwithstanding, it is not clear as regards the subsequent steps after the three studies have been concluded. The project should add a policy dialogue as one of the outputs/activities to start sharing results with policy and decisionmakers in decision-making about the targeted IASs.

- Lesson 1: Active engagement of stakeholders in dealing with IAS allowed for effective collaboration which resulted in creating a common ground of understanding of the problem and taking shared responsibilities for action. E.g., the PIU is working with the Blantyre Water Board, CARD, MMFR and MMCT of which each of these organizations has its role to play for a common goal, yet all from a background of varied interests. In addition, the partnership among UNEP has resulted in cost-effective and efficient program delivery and demonstrated effective collaboration and coordination among UN agencies and a valuable model for future program delivery within biodiversity conservation.

- Lesson 2: Strong coordination leadership is an important success factor in the implementation of the project so far. For the EAD as a coordinator, despite this being the first IAS project to coordinate exhibited clear direction coupled with enthusiasm and visionary character that propels the process despite internal bureaucratic and procurement challenges. This project has built  the country capacity and allowed ownership and room for sustainability within the department. Most projects coordinated by others somehow get disconnected from the system.

- Lesson 3: For sustainability, effective planning and implementation of IAS project requires strong involvement of the private sector, and civil society, including community-based and youth organizations with clearly defined roles and translated into implementable activities. This was observed throughout the project processes.

- Progress and Challenges

- The project implementation is on course, and this is despite some challenges such as limited technical capacity of field staff who needed close supervision. The COVID19 pandemic denied the opportunity for the close supervision field resulting in some technical errors which may require more time to rectify.

- Activity 2 under Output 2 has made progress although students have met challenges of limited academic supervisory support which delayed the timely delivery of the theses.

- The PIU has challenges of timely reporting which must receive attention as required. While some issues can be reported on a regular basis, others require prompt attention.

- The MTR raises gender imbalances and Environmental and Social Safeguards as main challenges rocking greater achievement at the project midterm implementation. The direct beneficiaries are both men and women although the number women is generally less than the MTR target of 40%. This is an inherent complexity.

# INTRODUCTION

## Project Overview

- The UN Environment Programme (UNEP) and the Global Environmental Facility (GEF) provided funding to support a project titled ‘Enhancing Sustainability of Protected Area systems in Malawi, and stabilizing agro-production in adjoining areas through improved IAS management’. Its total budget is USD 6,666,658 of which USD 5,164,147 is co-financing – from the Environmental Affairs Department (EAD), CABI, Peace Parks Foundation, Mulanje Mountain Conservation Trust and other national partners, and USD 1,502,511 financed through a GEF grant. The objective of the Project is to prevent new invasions and reduce the current impacts of invasive alien species (IAS) in protected areas (PAs) and adjoining agro-ecosystems in Malawi.

- The project responds to IAS as one of the biggest threats to biodiversity and livelihoods in Malawi. Globally, IAS are invading and threatening a range of habitats, as well as, indirectly, the livelihoods of millions of people depending on natural ecosystems for food, commodities, and energy security. Malawi implements the project in line with Article 8 (h) of the Convention on Biodiversity (CBD), aiming at enhancing the capacity of Malawi to manage IAS, especially in two PAs and their surrounding agro ecosystems, by strengthening existing national and PA specific frameworks for the prevention and management.

- In consideration of complexities involved in managing alien species in terms of the control of a diversity of their pathways and the diverse interests of players in IAS, the Project employed a multi–sectoral approach, undertaking interventions in identification and management of high-risk pathways to prevent further introduction and spread, on one hand, and biocontrol of the worst IAS, on the other hand. The Project therefore has the objectives to (i) establish national framework and capacity to enhance IAS management in protected areas and associated agroecosystems (ii) strengthen on-the-ground IAS management in existing PAs through invasive species control and habitat restoration, as well as in adjoining agro-ecosystems through sustainable farming for improved welfare, and to (iii) improve knowledge management and broader adoption of developed strategies in Malawi PAs.

- To ensure successful implementation, the Project strategically brought in international cooperation for expertise that would see the development of best practices for the management of selected IAS. In addition, the project has been investing in raising public awareness of the serious issues of IAS nationally with the objective to increase the willingness and levels of core government funding to IAS management. The project has several priorities and establishes an integrated workplan at site and national levels to meet some of the GEF policy objectives by (i) establishing national policy and institutional framework (ii) national capacity building and institutional support (iii) developing expertise on the prevention, control and management of priority IAS in protected areas (iv) implementing national information, monitoring and awareness programmes.

- The Project envisages generating some global benefits including contributions to: (i) reduce the loss of biodiversity and maintain the quality of protected habitats in the PA system of Malawi by initially focusing on two PA’s, Nyika NP (NNP) and Mulanje Mountain Forest Reserve (MMFR), and (ii) reduce the negative impacts of IAS on local livelihoods and the economy of Malawi. IAS management activities in agroecosystem areas adjoining.

Table 1: Description of the Project Outcomes And corresponding  Outputs

Outcome 1: Strengthened national IAS policy and improved national capacity and coordination. Output 1.1: National framework for the cross-sectoral management of IAS operational and supporting long-term development planning. Output 1.2: Evidence base established and communicated for IAS prevention and management in and around PAs.

Outcome 2: Reduced IAS impacts in two selected protected areas resulting in enhanced conservation outcomes for endangered and threatened species. Output 2.1: Two revised PA Management Plans including strategies and budgets for IAS prevention and Control. Output 2.2: Tested management plans for four IAS, including IAS control and habitat restoration in two PAs. Output 2.3: Capacity of 80 PA staff improved and applied in the identification and management of IAS. Output 2.4: Biocontrol Working Group (BWG) established and operational leading to the introduction of three host specific and damaging biocontrol agents.

Outcome 3: Reduced IAS impacts in adjoining agro- ecosystems of two selected protected areas contributing to improved livelihoods and biodiversity conservation Output 3.1: Invaded rangeland (100 ha total) in buffer zones/agro-ecosystems of two adjoining PA’s cleared and restored (native trees) through enhanced partnerships between PA staff and farmer communities, including the training of 100 farmers on IAS identification and management. Output 3.2: Sustainable farming practices such as Farmer Managed Natural Regeneration (FMNR), Conservation Agriculture (CA), including crop rotation, crop integration and cover cropping adopted and promoted among 50 households because of training and demonstration trials.

Outcome 4: Lessons learnt, documented, and disseminated and awareness programs established to facilitate replication and broader adoption in the Malawi PA system. Output 4.1: Communication strategy and outreach campaigns including use of media, workshops and meetings targeting government officials, PA staff and affected communities. Output 4.2: National information sharing procedures including the development of a Guide on identification and management of invasive plant species in Malawi Output 4.3: Establish and implement Monitoring and Evaluation Plan.

- The two and some PAs are implementing a shared workplan comprising activities such as (i) the development of National Invasive Species Strategy and Action Plan (NISSAP) (ii) improving coordination and cross-sectoral management at a national and local level (iii) identifying and managing IAS pathways (IAS being introduced into PAs and adjoining agroecosystems) (iv) improving prevention and EDRR mechanisms (v)  managing invasive plants within two PAs and surrounding agroecosystems (include the development of best management practices for selected IAS); and  (vi) building capacity and creating awareness about the threats and management of IAS.

- The project implementation has a management structure working at three different levels with respective roles:

- As a key project partner, the UN Environment is the Implementing Agency (IA) through the UN Environment Office with GEF undertaking the role of funding. The UN Environment has responsibility for ensuring that GEF policies and criteria are adhered to and that project objectives are met and expected outcomes achieved in an efficient and effective manner. The UN Environment project Task Manager is based in the UN Environment Asia Pacific Regional Office in Bangkok, Thailand and responsible for project supervision on behalf of the GEF Executive Coordinator - Director, Division of Global Environment Facility Coordination, UN Environment. UN Environment ensures timelines, quality, and fiduciary standards in project delivery are met at all times.

- CABI is another important Executing Agency (EA) partner. CABI’s African office in Nairobi functions as the project's technical advisor, responsible for review of outputs and ensuring that they are in accordance with the objectives and activities outlined in the ProDoc.

- A PSC was established in Malawi to provide governance and oversight and strategic guidance for the project, as well as enable the exchange of best practices, and lessons from related IAS projects. The NPSC is responsible for overseeing and approving annual workplans and budgets, solving issues and other strategic decisions. Membership include representation from the academia, government ministries and departments and the civil society organizations, the National Executing Agencies (NEA) via National Project Coordinator (NPC), serving as secretariate.

## Aim, Objectives And Scope Of The MTR

- MTR was undertaken as a procedural requirement like any UNEP-GEF funded Project. It was commissioned to provide information for fine-tuning of workplans, budgets and implementation arrangements for the second half of the project, as well as introducing mechanisms towards improving project approaches and impacts, based on a review of project progress as well as the project performance against the outcome indicators as specified in the Project Document.

- This MTR is part of the responsibility of the UNEP Task Manager – in collaboration with the Malawi government as a national executing agency (NEA) for an independent and transparent consultation process involving all key stakeholder groups. The findings and recommendations will be reviewed and endorsed by the PSC, and subsequently taken over and addressed by the NEAs and its main Project Partners in various project sites.

- The MTR’s main goal is to evaluate progress to date using indicators as a benchmark and rating project impacts/performance based on standardized criteria. Improvement will involve possible fine-tuning of work plans for the second half of the project and improving project approaches and optimizing implementation arrangements, to achieve all this, the MTR assesses, amongst other things the:

  - effectiveness and efficiency of project management and supervision of project activities; production of planned outputs and milestones, in terms of quantity, quality, usefulness and timeliness.

  - project performance in achieving project objectives and outcomes.

  - project performance against quantified criteria.

  - project progress against available and spent budget (GEF & co-finance).

  - sustainability and replicability of project achievement towards outputs and outcomes to date. Compliance with environment, social and economic safeguards, as well as gender.

- The MTR report was instituted to (i) make recommendation on how to continue and improve project implementation during the second half of the project (ii) corroborate and/or recommend any specific redirection of program activities (iii) verify or change key outputs, deliverables, and activity benchmarks (iv) confirm or change the log-frame, including indicators and targets (v) advise on project institutional arrangements (vi) advise  on project approaches towards stakeholder groups and other beneficiaries (vi) propose any needed approaches to better achieve project objective and outcomes. The questions for the review to address are described under Annex 2.

# REVIEW METHODS

- The MTR process employed a participatory approach involving close commitment with the Project Management Unit (PMU), government counterparts (the GEF and UNEP Operational Focal Points), and CABI. Through this approach, the MTR used both primary and secondary sources of information and data. Primary data was collected directly from key stakeholders through interviews, questionnaires, checklists, focus group discussions and direct observation techniques. Secondary data was obtained various literature sources through desk review. The following are the details of data collection methods and instruments:

## Desk Review

- The desk review examined documents from project site coordinators from both the NNP and the MMFR, in addition to documents from the EAD. The documents were analyzed for secondary data and information. Some of the documents reviewed include Project Document, Environmental and Social Management Plans (ESMP) report, All Project Implementation Reports (PIR’s), Quarterly progress reports and work plans of the various implementation task teams, Audit reports, Finalized GEF focal area Tracking Tools at CEO endorsement besides one done last year, Oversight mission reports, all monitoring reports prepared by the project, Financial and Administration guidelines used by Project Team. The MTR constantly referred to the following key documents: Project operational guidelines, manuals and systems, Minutes of the 3 PSC  and other meetings (i.e., Technical Committee meetings) and Project site location maps.

## Individual Interviews

- Semi-structured questions were targeted at 20 individuals who beneficiaries and implementers of the project. Out of 20 individuals, 18 were able to respond and give feedback to the questionnaire.  The questions aimed at obtaining both qualitative and quantitative data through face-to-face and virtual consultations using “semi-structured interviews” with a key set of questions in a conversational format (see Annex 3 – the questionnaire that was used in the field). Triangulation of results, i.e., comparing information from different sources, such as documentation and interviews, or interviews on the same subject with different stakeholders, was used to corroborate or check the reliability of evidence. Key stakeholders that were interviewed included the following amongst others: Staff of PMU, UN Environment Task Manager, , Representatives of the EAD, Some Project’s Steering Committee (PSC) members and Various Project Beneficiaries (within project sites) and other government agencies representatives. The organizations consulted include MMFR, NNP, Chongoni Forestry and Wildlife College,  MMCT, National Forest Institute, Department of National Parks and Wildlife, Total Land Care, and the EAD.

## Focus Group Discussions

- FGDs were used to guide our discussion meetings with beneficiaries of the two project sites to obtain their perspectives on the impact of the project on the community. Of great interest to this project was the level of their participation, any experiences in gender related issues, the benefits accrued from the project and further expectations from the project to expand the benefits on long-term investment horizon.  Annex 2 displays the list and categories of stakeholders and communities consulted.

# REVIEW FINDINGS

- To meet UNEP and GEF requirements, the findings are presented in this section assessed with respect to a minimum set of criteria in six categories: (i) Strategic Relevance; (ii) Progress towards results, which includes the assessment of outputs, achieved, effectiveness and likelihood of impact; (ii) Sustainability and replication; (iv) Efficiency; (v) Factors and processes affecting programme performance including: preparation and readiness; implementation and management; stakeholder participation and public awareness; country ownership and driven-ness; financial planning and management; UNEP and supervision and backstopping; and programme monitoring and evaluation; and (vi) Complementarity with the GEF & UNEP strategies and programmes.

## Strategic Relevance

- The MTR confirms the relevance of the project design with regards to the global and local contexts. The desk review found a proper consideration of linkages of the project aims and objectives to ongoing initiatives and this is maintained throughout the project implementation. The participation of UNEP and CABI is ensuring maintenance of the linkages to the overall GEF-6 subprogram and ensuring sound technical attention, respectively. The project aligns with sub-programme 4 of GEF-6 on prevention, control, and management of IAS. It is also relevant to the UN Environment Sub-programme(s) – Health and Productive Ecosystems (2020-2021), and the GEF-7 Biodiversity Strategy which aim to maintain globally significant biodiversity in landscapes and seascapes. Implementational progress is on course with UNEP’s Medium-Term Strategy (2022 – 2025), and the programme of work (POW) and budget for 2022–2023 which focus on responding planetary crises - biodiversity and nature loss, among others.

- The Project directly and indirectly addresses many of the SDGs. It directly addresses the following: (i) Target 15.8 under Goal 15 which encourages countries to “introduce measures to prevent the introduction and significantly reduce the impact of IAS on land and water ecosystems and control or eradicate the priority species.” (ii) SDG 2 zero hunger – Agriculture ecosystems - (2.1.2, 2.3.1, 2.3.2 and 2.4.1) (iii) SDG 6 – impact on water quality (6.5.1 and 6.6.1) (iv) SDG 15- Life on Land (15.1.1, 15.1.2, 15.2.1,15.3.1, 15.4.1, 15.4.2, 15.5.1, 15.8.1 and 15.9.1). No explicit statement of relevance within the regional context was made throughout the project document. However, the MTR deskwork observed that the project design augured with the recently adopted African strategic approach to management of invasive species whose objective is to effectively guide and coordinate actions at the continental, regional and national levels towards prevention and eradication of invasive species. The strategy is intended to secure instruments required for surveillance, predictive modelling, forecasting, monitoring/surveillance, and governance structures, among others.

- The Project exploits synergy with ongoing national initiatives in management of IAS. For example, it links with Malawi’s National Biodiversity Strategies and Action Plan (NBSAP) which supports the Aichi Biodiversity: Target 9: By 2020, IAS and pathways are identified and prioritized, priority species are controlled or eradicated, and measures are in place to manage pathways to prevent their introduction and establishment. The project also supports achievement of targets outlined in the Global Strategy for Plant Conservation 2011-2020, including “Effective plans in place to prevent new biological invasions and to manage important areas that are invaded for plant diversity” and to priorities identified in the International Plant Protection Convention (IPPC).  Moreover, the project has also integrated IAS in the revised Environmental and Social Impact Assessment  guidelines and new the revised regulations including  the forestry  landscape restoration programme.

- The Malawi Growth and Development Strategy (MGD III) is aligned with the SDGs, thus rendering the project relevant to the MGD III and the SDGs across a section of goals as follows:

- The project offers short to long-term economic and employment opportunities for various groups of people such as local consultants and the local communities. The promotion and adoption of sustainable farming practices is expected to improve productivity in agroecosystems with the possibility of surplus for household income. The project is promoting sustainable farming practices such as conservation agriculture, crop rotation and integrated pest management to reduce the impact of IAS on food production for increased yields and reducing input costs. Farmers with IAS invaded farms have been identified and are undergoing training on sustainable farming practices. These practices will be widely marketed and hopefully adopted by other landowners.

- Pinus patula and Acacia mernsii species have high water requirements. By removing and eradicating these species from the water catchments, the project will be contributing to water resources management and management of water catchment ecosystems which are important for hydro-electricity generation and water supply for industry, irrigation and domestic uses.

- The Project is contributing to the maintenance of the forest area in MMFR and NNP. The project is also maintaining the quality of biodiversity by reducing the dominance of IAS and enhancing indigenous species richness and abundance thereby securing wildlife habitat quality. Most important, the project is contributing to enhancing the protecting the Mulanje Cedar from becoming extinct by freeing up land for restoration. There is collaboration with local and international institutions (e.g. NHBGM, CABI) in capacity building in management of IAS. The project is also enhancing local policy coherence through establishment and strengthening of coordination mechanisms. The project is also strengthening the planning tools through development and use of National Invasive Species Strategy and Action Plan (NISSAP), Communication and Outreach Strategy, monitoring and evaluation plans. Rating: Highly Satisfactory (HS).

## Gender Responsiveness

- The UNEP/GEF commit to the integration of gender equality and equity in all its policies, programmes and projects and within its institutional structures. Gender sensitive policies and practices for prevention, management, and control of IAS, which take account of how men and women are differently impacted, to improve their access to information and their ability to adopt technology to control and manage invasive species is advocated.  CABI advocates for evidence generation on gender in invasive species work, including an understanding of the underlying gender-based constraints affecting women’s ability to access and use technologies to prevent, control and manage invasive species and solutions to inform policy and programming.  The review examined the level of gender integration cross the project activities. It was established that, the project document explicitly considered gender issues under each of the three project components. The document cites an example where the cost-benefit analysis of three ‘conflict’ species under Component 1 will assess gender-specific impacts, costs and the role of women in their management and control of IAS through agricultural practices. The recruitment of students to undertake the studies also considered gender although in favor of male students 91 female 2 males, representing 30% female).

- Under Component 2 on strengthening of IAS management, the project document’s proposition was to include supporting community participation, and a communication and outreach to those living in and around PAs targeting not only community leaders but also women and women’s groups. This approach envisaged extending the national awareness programs under Component 3, ensuring that the whole community learns which plants are invasive, how to manage them, and how to reduce the negative impacts and prevent the spread of IAS. The document recognizes that targeting women is key to the control of IAS weeds in agricultural landscapes, as women are typically responsible for weeding and their constant presence in the fields makes them likely to identify IAS more quickly than others in the community. At the same time, IAS control plans developed by the project account for the potential burden that could be placed on women if they become responsible for IAS control activities.

- Gender was mainstreamed across the three components of the project. Overall progress on gender integration reveals low participation of women, although exception is noted under Component 3 which achieved almost 58% participation. As for, the training of PA staff in identification of IAS only 25% (29 women 57 men) was reported.  It was observed that, large number of PA staff are men (89%). This limits the pool of women who could have participated in training sessions. Unfortunately, even in labour related activities, women directly working in the two PAs constitute only 14%, but then this was attributed to the harsh terrain and working environment that necessitate absence from homes for days which obviously does not favor women. All awareness activities have engaged women to the level of 40%. On a technical level, the MTR established that the Project Coordinator, and the Chair of the PSC are both ladies. Deliberate effort has been made to bring a lady as an Environmental, Social and Gender expert. Rating is Moderately Unsatisfactory (MU).

## Environmental And Social Safeguards

- On ESS, the project was deemed to have low environmental and social risks. However, the MTR observed that due to long distances between workers homes and the sites where they work in eradication of IAS, they often spend weeks while on the mountains. This is a recipe for gender violence and spread of HIV and AIDS. Unfortunately, implementation has been a challenge despite that mitigation and precautionary measures were  prescribed. In this case, campaign messages should have been used to ensure at least awareness for prevention. Besides the messages, condoms should have been placed where workers could easily be accessing including toilets or indeed distributing them among those in need. To eliminate or offset potential other adverse environmental and social impacts, or to reduce them to acceptable levels; and the actions were framed in two separate Environmental and Social Management Plans (ESMPs). Unfortunately, the ESMPs have not been made available at the two project sites at least at the time of the consultations for this MTR. Several concerns were observed during the field missions:

- Workers Health and Safety: Workers on the two sites were operating with either limited Personal Protection Equipment (PPEs) or without. The two project sites did not have enough face masks, work suits and helmets etc. consultations with the PIU suggested that these were bought but enforcement to use them has been perhaps limited. At Chambe in MMFR as well as Chilinde in NNP, men and women work away their homes for many days. When asked if women face any forms of gender-based violence, they did not confirm. However, the work environment is susceptible to the spread HIV and AIDS. The FGDs noted the lack of HIV and AIDS messages as well as inaccessibility of condoms.

- Waste management: The continuous presence of workers in both PAs implies increased generation of waste around their accommodation and surrounding areas. littering was observed in both PAs. Both the FGDs and FGDs learnt that the workers did not receive the required awareness about the need to take care of the environment within the PAs. The preparation of ESMPs is just one step that needed resources for implementation.

- Social Issues: The FGDs revealed that the Project workers are paid below the minimum wage requirement, and this is despite complaints lodged to the authorities. Upon triangulation of this information with piu, the review found that the workers are paid different co-financiers such that the wages could be at variance and that workers would always want higher pay. In addition to getting low wages, casual workers have been paid late which is very demotivating. The problem of addressing social issues highlighted here is contingent upon the establishment of a proper Grievance Redress Mechanism (GRM). The Project was properly aligned with existing local government GRMs under the National Social Support Program. Each district around the two PAs District has a Grievance Redress Committee (GRC) at both the District Level and Traditional Area level. The IAS project was properly introduced at District and Traditional area level and its interventions are monitored by Local Grievance Redress Structure. Nevertheless, the need for GRM at site level was necessary as the workers within PAs do not have easy access to the established structures. Rating is Moderately Unsatisfactory (MU).

## Effectiveness – Delivery Of Outputs And Achievement Of Outcomes

- Effectiveness is assessed in terms of delivery of outputs, achievement of direct outcomes and likelihood of impact although this level (mid-point) more emphasis is placed on performance at the output and outcome levels. Analysis based on datasets provided in the ProDoc, project work plans, GEF Tracking Tools, and PIRs, and verified during the MTR mission.

### Delivery of Outputs

Table 2: Output 1 Progress On National Framework For The Cross-Sectoral Management Of IAS Operational And Supporting Long-Term Development Planning.

| Output 1 Activities | Expected delivery date | June 2019 | June 2020 | June 2022 | Summary of findings | Progress Rating |
| --- | --- | --- | --- | --- | --- | --- |
| Activity 1.1: Establish a national IAS Coordination Unit (CU) | Sept 2019 | 50% | 70% | 70% | EAD coordinating IAS activities at national level and included in MEPA strategic plan in addition to local coordination. | S |
| Activity 1.2: Establish a National Steering Committee (NSC) | May 2019 | 100% | 100% | 100% | NSC established in May 2019 and remains functional although meetings are sporadic. | HS |
| Activity 3: Develop NISSAP | July 2020 | 0% | 25% | 100% | NISSAP developed and approved. Activities integrated in MEPA Strategic Plan. | MS |
| Activity 4: Identify high risk pathways. | Sept 2018 | 0% | 0% | 60% | A consultant was recruited, and work commenced. | MS |
| Activity 5: Strengthen National IAS Risk Analysis procedures and develop RA systems for PA’s | July 2020 | 0% | 0% | 50% | TORs are under development. First Training workshop on PRA conducted involving other sectors including crops, fisheries, forestry, wildlife and sectors tasked to identify priority species for their sectors for a practical PRA exercise. | MS |
| Activity 6: EDRR systems established, especially for PA’s and Adjoining agro ecosystems. | July 2020 | 0% | 0% | 65% | A consultant was recruited, and work commenced. | MS |

- A fresh scrutiny of Table 2 reveals that all activities should have been done latest by July 2020. Unfortunately, some activities are carried over to 2022. The lower rating is influenced by factors such as the COVID19, delayed procurement procedures and lower participation of women under Activity 6. The overall rating on Output 1 is Moderately Satisfactory.

Table 3: Output 2 Progress On Evidence Base Established And Communicated For IAS Prevention And Management In And Around PAs.

| Output 2 Activities | June 2019 | June 2020 | June 2022 | Summary of findings | Progress Rating |
| --- | --- | --- | --- | --- | --- |
| Activity 2.1: Produce a national inventory on presence and distribution of priority invasive plants in National Parks and four Wildlife Reserves | April 2020 | 95% | 100% | Inventory was developed and list of species circulated and was endorsed by stakeholders. It is now under dissemination | HS |
| Activity2.2: Undertake cost-benefit analysis of three “Conflict” species and produce reports | Dec 2021 | 50% | 70% | Studies on the costs and benefit of three IAS, including ‘conflict’ species, present in agro-ecosystems adjoining PA’s undertaken are underway. The students are at varying levels of progress. Two MSc students are towards the end and 1 MSc student is still underway. | MS |

- The MTR found that the national inventory on IAS was timely produced by the National Herbarium and Botanical Gardens (NHBG) in conjunction with CABI.  The MTR verified through the NHBG website. This output should be made available to stakeholders as the next step. Activity 2 has made progress although students have met challenges of limited academic supervisory support which delayed the timely delivery of the theses. The rating for Output is Moderately Satisfactory considering that delivery was delayed and that the theses may not be released as outputs within the next three months and further results may not be communicated to the intended audience within time.

Table 4: Output 3 Progress On Two Revised Protected Area Management Plans Including Strategies And Budgets For IAS Prevention And Control.

| Output 3 Activities | Expected delivery date | June 2019 | June 2020 | June 2022 | Progress rating |
| --- | --- | --- | --- | --- | --- |
| Activity 3.1:Two revised PA Management Plans including strategies and budgets for IAS prevention and control | January 2019 | 40% | 60% | As of June 2022, on 50 %. was achieved. MMFR revised. | MS |

- The development of the two Management Plans is contingent on results of the field trials to inform the details of the plans. The trials have made progress although due to the COVID19, the Technical Advisor could not travel to Malawi to guide the field teams. Some technical errors have been made and the trials remain inconclusive. In September 2022 the project produced TORs to engage consultants to develop species-based management plans but delayed by the Technical Advisor. Considering that, only MMFR has revised its plan and that NNP has not yet done so, the delivery date of 2019 has been missed. This was a planning oversight. Further consultations reveal that all the Management plans were supposed to be revised in 2022 after the the field trials have concluded. MMFR was already revising its plan, so the project took advantage  to include IAS. But we will have to revise that section again based on the outcomes of the studies. The MTR rates effectiveness on this out at Moderately Satisfactory.

Table 5: Output 4 Progress On Tested Management Plans For Four IAS, Including IAS Control And Habitat Restoration In Two PAs.

| Output 4 Activities | Expected delivery date | June 2019 | June 2020 | June 2022 | Progress rating |
| --- | --- | --- | --- | --- | --- |
| Activity 4.1: Species targeted for management trials and methodologies agreed | September 2022 | 7% | 95% | Species are now targeted, and the methods are yet to be agreed upon as the field trials have not yet generated conclusive results. | S |
| Activity 4.2: Pilot sites established through effective partnerships | June 2019 | 100% | 100% | By June 2020 all sites had been established and all relevant partners were identified and signed commitment letters. | HS |

- Output 4 has been delivered within time despite some challenges including limited technical capacity of field staff who needed close supervision. The COVID19 pandemic denied the opportunity for the close supervision resulting in some technical errors which require more time to rectify. The overall rating is Moderately Satisfactory considering that more work is required to conclude Activity 4.1.

Table 6: Output 5 Progress On Capacity Of 80 Pa Staff Improved And Applied In The Identification And Management Of IAS.

| Output 5 Activities | Expected delivery date | June 2019 | June 2020 | June 2022 | Progress rating |
| --- | --- | --- | --- | --- | --- |
| Activity 13: Develop and conduct training programs on the identification and management of invasive plants targeting PA staff. | December 2021 | 60% | 100% | Training sessions conducted at MCFW targeting 76 PA staff and 4 management staff. A module on Invasive Alien Species has been developed for use in courses at Malawi college of forestry and wildlife. | S |

- This output has achieved the target. However, the field missions established that, a total of 76 staff were trained out of which 19 were women while 57 were men. This gender imbalance is inherently within the institutions from the time of recruitment which affected achievement of gender balance. Considering the delayed delivery (Table 6) and that the problem of gender inequality was beyond the mandate of the training, the MTR rated effectiveness of delivery of output as Satisfactory.

Table 7: Output 6 Progress On Biocontrol Working Group Established And Operational Leading To The Introduction Of Three Host Specific And Damaging Biocontrol Agents.

| Output 6 Activities | Expected delivery date | June 2019 | June 2020 | June 2022 | Progress rating |
| --- | --- | --- | --- | --- | --- |
| Activity 6.1: Establish a Biocontrol Working Group | June 2020 | 100% | 100% | The Biocontrol Working Group has been established and is operational. | HS |
| Activity 6.2: Identify target species and potential biocontrol agents | December 2021 | 40% | 60% | Target species proposed and potential targets and agents have been identified for the control of Mimosa diplotricha, Opuntia stricta, and Pistia stratiotes and import permits have been issued. Risk assessments were done and approved. The only thing remaining is the shipment of the agents. | S |

- The Project has now established the BWG, and it is also operational. The agents have been identified but at the time of the MTR they were not yet introduced. The overall rating of progress is Satisfactory considering that the requirement of Output 6 is the introduction of the agents which has not been achieved yet.

Table 8: Output 7 Progress On Invaded Rangeland (100 Ha Total) In Buffer Zones/Agro-Ecosystems Of Two Adjoining Pa’s Cleared And Restored (Native Trees) Through Enhanced Partnerships Between Pa Staff And Farmer Communities, Including The Training Of 100 Farmers On IAS Identification And Management.

| Output 7 Activities | Expected delivery date | June 2019 | June 2020 | June 2022 | Progress rating |
| --- | --- | --- | --- | --- | --- |
| Activity 7.1: Develop and conduct training programs on IAS identification and management | June 2022 | 30% | 100% | 110 Farmers have been trained and 100 ha of farmlands identified in farming communities around MMFR and NNP. 47.1 ha has so far been cleared of IAS in the ha identified. | HS |
| Activity 7.2: Local IAS coordination Units Established | June 2019 | 100% | 100% | Local Technical Committees identified and established at site level for NNP and MMFR. TORs for the Site Technical Committees also developed. Local leaders and representatives of PA staff were identified. Area Development Committee meetings conducted. Quarterly including with PA staff present The project is working with local organisations including the Concerned Citizens for the Protection of Mulanje Mountain, Nyika Vwaza Association and many others. | HS |
| Activity 18: Invaded areas cleared and restored using native trees | October 2022 | 30% | 60% | 111 ha area restored with native trees whilst 47.1 ha cleared of IAS on farm lands. | HS |

Table 9: Output 8 Progress On Sustainable Farming Practices Such As Farmer Managed Natural Regeneration, Conservation Agriculture, Including Crop Rotation, Crop Integration And Cover Cropping Adopted And Promoted By 50 Households As A Result Of Training And Demonstration Trials.

| Output 8 Activities | Expected delivery date | June 2019 | June 2020 | June 2022 | Progress rating |
| --- | --- | --- | --- | --- | --- |
| Activity 8.1: Develop and conduct training programs on sustainable farming practices. | December 2022 | 30% | 100% | 110 farmers (60 in Mulanje and 50 in Rumphi) trained and programmes have been developed on different approaches. Framers have been divided based on approaches preferred by them. | HS |
| Activity 8.2: Implementation of sustainable farming practices | Dec 2022 | 15% | 80% | 110 farmers implementing sustainable farming practices in their farmlands, beyond the target of 100. | HS |

- Output 8 (Table 9) is fundamental to this project on two accounts. First it demonstrates the benefit of dealing IAS from both a conservation and livelihood perspective. Second, it deals with one of the primary beneficiaries who are smallholder farmers, the majority who are women.  The delivery of Output 8 is Highly Satisfactory with 58% women benefiting achieving beyond the target of 40%.

Table 10: Output 9 Progress On Communication Strategy And Outreach Campaigns Including Use Of Media, Workshops And Meetings Targeting Government Officials, Pa Staff And Affected Communities.

| Output 9 Activities | Expected delivery date | June 2019 | June 2020 | June 2022 | Progress rating |
| --- | --- | --- | --- | --- | --- |
| Activity 9.1: Develop Communication strategy and undertake comprehensive local and targeted national awareness campaign | June 2021 | 50% | 60% | 100 %. Communication strategy developed and under implementation. The Lilongwe Wildlife Trust and the Wildlife and Environmental Society of Malawi are leading in development of awareness materials and undertaking of national and local awareness activities based on the communication strategy. Other state media houses being engaged through commemoration of environment days, press briefings, news articles, TV programmes and general awareness activities. | S |

- Output 9 has been delivered by the time of the MTR. The engagement of NGOs in the dissemination of the Communication Strategy is an important direction for sustainability. The need for streamlining the communication strategy to target the PAs and surrounding communities has been echoed during KIIs. The MTR rates the level of achievement of this this output as Satisfactory.

Table 11: Output 10 & 11Progress On National Information Sharing Procedures Including The Development Of A Guide On Identification And Management Of Invasive Plant Species In Malawi.

| Output 10 & 11 Activities | Expected delivery date | June 2019 | June 2020 | June 2022 | Progress rating |
| --- | --- | --- | --- | --- | --- |
| Activity 22: Produce invasive alien plant Field Guide | June 2020 | 95% | 100% | As at 30 June 2020 the Field Guide was developed by CABI, and adopted; yet large delay towards its planned printing of book copies. | HS |
| Output 11: Establish and implement Monitoring and Evaluation Plan |  |  |  |  |  |
| Activity 23: Develop M&E plan, indicators and baseline | December 2021 | 100% | 100% | M&E Plan developed and used. | HS |

- Outputs 10 & 11 have been delivered within time although during KIIs a complaint was launched regarding the remaining stage of printing the Guide. Delays are associated with the procurement procedures. The rating is Highly Satisfactory for both as outputs.

### Achievement of Immediate Outcomes

- Under this subsection on effectiveness, the assessment examines the direction of progress based on specific indicators of the immediate outcomes. The MTR reveals varying degree of progress across the four outcome areas.

Table 12: Outcome 1 Progress On National IAS Policy And Improved National Capacity And Coordination Amongst Different Government Agencies And The Private Sector.

| Indicator | Baseline level | Progress Rating |
| --- | --- | --- |
| Indicator 1.1: Level of implementation of the NISSAP in and around PAs. | No strategic policy on IAS management. | Some of NISSAP’s proposed activities are funded by MEPA. The MMFR has integrated NISSAP activities into routine work and being implemented. The Shire Valley Transformation Phase 2 and Drylands Landscape Restoration Project has taken up some of the NISSAP activities. Achievement of this outcome is rated Satisfactory. While the likelihood of Impacts is Likely given the role the private sector and NGOs are playing. |
| Indicator 1.2: Levels of coordination /cooperation between various stakeholder groups like local communities, private sector and Government agencies in the management of IAS | No or little coordination between various agencies with regard to the management of IAS | Level of coordination has started improving. PSC and Technical Committees are functional at the project and PA level. MEPA has subsumed national mandate for coordination of IAS issues by setting up a CU with officers assigned for IAS in the Draft Functional Review. MEPA has also integrated IAS objectives in its strategic plan drawing from the NISSAP. Considering that the CU is not yet operational due to staffing shortage, achievement of this outcome is Moderately Satisfactory, and the Likelihood of Impact is Likely. |
| Indicator 1.3: High risk pathways and most damaging species, incorporated in at least one modified or new national policy and/or PA Management Plans and operations. | No information on high-risk pathways or a prioritized list of IAS threatening PAs. | NISSAP contains a section on risk pathway analysis at a national scale. A study was commissioned, and preliminary synthesis of information is available on PRA focusing on PA level. The rating is Satisfactory, and Likelihood of impact is Likely. |
| Indicator 1.4: Results of CBA of selected priority IAS, including ‘conflict’ species present in agro-ecosystems adjoining PAs, leading to positive change, allocations, safeguards or policy, to reduce or prevent promotion and further spread. | No evaluations have been undertaken on the costs and benefits of some highly invasive agro-forestry species such as Acacia mearnsii, Pinus patula, and Prosopis juliflora | Three MSc Students from LUANAR and Mzuzu University (2 males, 1 female) undertaking studies. Two of the students have already submitted their second drafts for comments and incorporating the comments for a third or final draft based on response. One student still collecting his data. Given that this outcome entails a change the likelihood of impact in the immediate term is Moderately Unlikely. |
| Indicator 1.5: Presence and distribution of invasive and potentially invasive plants detailed for five NP’s (including NNP), four Wildlife Reserves, and MMFR, to enable risk analysis and control. | No detailed information on presence and distribution of all AS and potentially invasive plant species in these PAs. Only pines and bracken . | Information has been synthesized of all invasive and potentially invasive plants in selected PAs. A National Invasive Species Inventory report and Field Guide were developed completed and adopted. The MTR rates this outcome Satisfactory and the likelihood of impact is Likely. |

Table 13: Progress on Outcome 2 on Reduced IAS impacts in two PAs resulting in enhanced conservation outcomes for endangered or threatened species.

| Indicator | Baseline level | Progress at MTR |
| --- | --- | --- |
| Indicator 2.1: PA management effectiveness enhanced on IAS prevention and management in two PAs (strategies, budgets, control and restoration). | No IAS management strategies and budgets included in PA management plans and operations for Mulanje FR and Nyika NP. METT score of 61 for Mulanje Mountain FR and 63 for Nyika NP | Reviewed MMFR Integrated Management plan and IAS issues incorporated. Increased support from stakeholders e.g. NGOs, communities, Forestry Research Institute and BWB, Blantyre District Council, and MMCT. Trials met some technical hiccups and finalisation of the trials means the revision of the plan may start later start. Preliminary METT scores for both PAs have been calculated and resulted in 72 for NNP and 70 for MMFR. This well above targets of 66 for NNP and 64 for MMFR. Highly Satisfactory. |
| Indicator 2.2: Enhanced IAS management planning and capacity in pilot PAs leading to on-the-ground implementation. | Two pilot sites (MMFR and NNP) confirmed. No ecosystem management plans available focusing on IAS. Control practices have been applied for a few species but there is too little information available on best IAS management practices | All trials but one concluded and control practices have been tested and determined in terms of efficacy and desired result in both PA’s. However, more time will be required to meet some technical standards of the trials. About 549.84 ha cleared in NNP and MMFR. Exceeding 150 ha target. \Trial reports developed and PA staff trained on outcomes of the trials (hands on). GEF TT scores have increased significantly. Highly Satisfactory and the Likelihood Of Impact Is Highly Likely. |
| Indicator 2.3: Changes in skills of PA staff in IAS identification and management applied to their conservation work | PA staff have little knowledge in IAS identification and management. Baseline capacity/ knowledge levels determined at project inception | The training of 76 PA staff and 4 management staff in IAS (25% of PA staff were women). ie 19 women and 57 men has increased knowledge and skills in IAS identification. About 30 staff are engaged in identification of IAS removal, and supervision activities. Rating is Satisfactory and Impact is Likely. |
| Indicator 2.3: Biocontrol programs supported | Little to no awareness as to biological control with no agents for terrestrial weeds released in the past 50 years. Baseline awareness levels on biocontrol determined in PY1, as part of the overall awareness baseline assessment. | Risk assessments were conducted and approvals made for release of 3 biological control agents. IAS biological control working group was established and operational in 2020-2021. High priority target species were identified and applications approved for their control. The rating satisfactory and the likelihood of impact is Likely. |

Table 14:  Outcome 3 progress  on  reduced IAS impacts in adjoining agro-ecosystems of MMFR and NNP contributing to improved livelihoods and biodiversity conservation.

| Indicator | Baseline level | Summary of Progress at MTR |
| --- | --- | --- |
| Indicator 3.1: Collaboration between PA managers and adjoining communities improved | Little to no collaboration/cooperation between PA staff and communities on IAS managements | PA representatives are working with NGO’s and extension workers with farmers on management of IAS in adjoining agroecosystems. They meet quarterly for joint trainings and monitoring. Local IAS management plans developed and species of priority concern identified. |
| Indicator 3.3: Knowledge on IAS management and adoption of sustainable farming practices for weed/IAS management by farmers | Areas around two PAs (Mount Mulanje FR and Nyika NP) identified during PPG. Farmers have little to no knowledge on IAS identification, management and sustainable farming practices. No effective management plans available for many IAS in adjoining agro-ecosystems (rangelands and croplands). Continued deforestation and land degradation | 50-ha in Mulanje and 50-ha in Rumphi under sustainable farming practices with 60 farmers in Mulanje and 50 farmers in Rumphi as direct beneficiaries. About 47 ha cleared of IAS and about 111 ha restored with native tree cover. Sustainable farming practices adopted by 110 farmers in Nyika and Mulanje. About 110 farmers have been trained in IAS identification, sustainable land practices including Farm managed natural regeneration 58% are women. This is above MT target of 40%. The rating is Highly Satisfactory, and Likelihood of Impact is Highly Likely. |

Table 15: Outcome 4 progress on learnt  learnt, documented and disseminated and awareness programs established to facilitate replication and broader adoption in the Malawi PA system.

| Indicator | Baseline level | Summary of Progress at MTR |
| --- | --- | --- |
| Indicator 4.1: PA staff and adjacent communities’ awareness increased through project communications. | - PA staff have limited knowledge beyond awareness of the major invasive species - Baseline IAS awareness levels of PA staff and communities living adjacent to Mount Mulanje FR and Nyika NP set at Inception (PY1) | Baseline awareness surveys were conducted and final survey will be conducted towards the end of the project final draft of IAS Communication Strategy developed and now final review. Communities and stakeholders have been reached with IAS information through radio, TV newspaper and community consultation meetings strategy developed and under implementation (development of awareness materials, awareness activities, dissemination of IAS messages etc.). Over 3,000 community members have been reached with IAS messages through extension services, workshops awareness meetings and more others through radio and TV. The general public reached through radio, TV, newspapers, commemoration of biodiversity and environment days, press briefing by ministers and higher officials among others. |
| Indicator 4.2: IAS control pilots reducing the spread and impact of IAS to (i) PA target area, and (ii) the agro-ecosystems. | Baseline biodiversity levels will be quantified at project inception. METT scores of 61 for Mount Mulanje FR and 63 for Nyika NP | Baseline biodiversity levels were quantified and final have been quantified for end of trials evaluation. M&E plan was developed and tracking tools are used for data collection from implementation entities. |

## Financial Management

- The MTR confirms that financial management structures and processes were adequately set before the start of the project and were followed in the implementation processes. There was a procurement plan in place at the onset of the project but existing procedures in government are too slow to match the project implementation. The UN administrative standards are so far followed although procurement procedures under the implementing agency, the EAD have derailed progress.

- In terms of co-financing, at the time of the review (June 2022) the total co-financing received was $3,815,909. This has increased compared to the $1,386,538 of June 2020. This is against the planned co-financing of US$ 5,164,147. Thus, the review established that co-financing arrangement is working beyond expectation.  The BWB as well as the Malawi – Zambia Transfrontier Conservation project have both contributed funds towards removal and restoration of Chambe Basin in the MMFR and NNP, respectively. The Malawi Environment Protection Authority is undertaking some activities proposed in the NISSAP.

- The MCFW provided accommodation and lodging for participants during training sessions. Non-governmental organizations including CARD, Lilongwe Wildlife Trust, Wildlife and Environment Society of Malawi and Total Land Care gave support in conducting awareness campaigns around PAs. Government institutions such as Forest Research Institute of Malawi, EAD, Department of Forestry, the Department of National Parks and Wildlife co-finance through provision of personnel, offices and vehicles. Co-financing information provided seems adequate. Co-financing information provided seems to indicate a very effective resource mobilization effort However the information provided does not indicate the sources of the financing reported. The evaluation The PIR reports and interviews with the project team confirmed that there was effective communication within the project team, and this includes the Fund Management Officers. The MTR has not seen the full project expenditures from EAD. The reports submitted to UNEP deemed were adequate.

Table 16: Midterm Expenditure Statement

| Project implementation period: |  | From: | 30-Aug-18 |  |
| --- | --- | --- | --- | --- |
| Reporting period: |  | To | Jun-22 |  |
| UNEP Budget Line |  | GEF-approved budget | Actual expenditures incurred* | Cumulative unspent balance to-date |
|  |  | Total project budget | Cumulative expenditures to-date |  |
|  |  | A | I=C+H | J=A-I |
| 1100 | Project personnel | - | - | - |
| 1200 | Consultants | 317,687 | 150,152 | 167,535 |
| 1300 | Administrative support | - | - | - |
| 1600 | Travel on official business | 162,100 | 86,970 | 75,130 |
| 2100 | Sub-contracts (co-operating agencies and government) | 733,512 | 459,527 | 273,985 |
| 2200 | Sub-contracts (commercial service providers) | - | - | - |
| 3200 | Group training | 50,000 | 31,545 | 18,455 |
| 3300 | Meetings/Conferences | 33,992 | 26,866 | 7,126 |
| 4100 | Expendable equipment | 4,616 | 3,217 | 1,399 |
| 4200 | Non-expendable equipment | 37,604 | 21,499 | 16,105 |
| 4300 | Premises | - | - | - |
| 5100 | Operation and maintenance of equipment | - | - s | - |
| 5200 | Reporting costs | 86,000 | 20,636 | 65,364 |
| 5300 | Sundry | 5,000 | 4,886 | 114 |
| 5400 | Hospitality and entertainment | - | - | - |
| 5500 | Monitoring and Evaluation | 72,000 | 6,800 | 65,200 |
| 5900 |  |  | - | - |
| GRAND TOTAL |  | 1,502,511 | 812,098.06 | 690,412.94 |

## Efficiency

- In general, efficiencies were either built into project design or have been realised through the use of proven models such as Training of Trainers (ToT) which allowed the project to roll-out activities to a wider stakeholder group. The project also took advantage of existing meetings and information platforms to create awareness. The use of partnerships contributed to both effectiveness and efficiency. The key inefficiency identified was slow project start-up for a variety of reasons, including lateness in project approvals and other administrative delays, including the late appointment of UNEP’s technical specialist. This was the case because it was a single sourcing which demands seeking a no objection from the ODPP

## Factors and Processes Affecting Project Performance

### Project management

- The project has established both national and local structures such as the PSC and local steering committees at the two sites which comprise members from various stakeholders including NGOs, academia, government departments, the private sector, and local communities. There is also a technical committee comprising the private sector (Blantyre Water Board) who are a key player for MMFR activities.  Several meetings have been held with BWB and Traditional Authorities in Mulanje and relevant local groups. They are playing various roles meant to enhance cooperation in future activities. Strong partnerships have been observed in this project. EAD is working with various partners such as the BWB, DNPW, PPF, CCFW, the LUANAR, MZUNI and many more. Collaboration with these partners is based on what each one of them contribute to the implementation of the project. While commending on the partnerships established so far, the frequency of meetings especially, the national steering committee has been limited.  Records indicate only three meetings conducted during the first half of the project implementation. The three meetings took place in Dowa, Lilongwe and Salima, respectively. The plan was to have one meeting  per year because they could not allow the PSC to increase the project budget line on project management. This is a challenge, Consultations suggested that the outbreak of the COVID19 coupled with limited project funding could not allow for frequent meetings which could otherwise increase coordination activities consolidate gains made from the project so far

### Participation and country – driven processes

- The IAS project advances a country driven approach as a critical pathway to support response to IAS threats in PAs. Malawi developed a NBSAP which recognizes IAS as one of the major threats to biodiversity loss and the project addresses IAS as one of the NBSAP priority activities. in addition, the project is receiving support rendered from different departments and organizations which already work with the two PAs which also have mobilization upon realization of the impacts of IAS in their respective sectors. Both local and national government stakeholders support the objectives of the project.

### Participation and public awareness

- They involvement of stakeholder has seen arrangements for co-financing emerging and public awareness contributed to the progress towards achievement of project objectives.  The problem of IAS is widespread in adjoining areas of our PAs. Although awareness campaigns have reached far, there limitations to reach beyond the surround communities. The long-term approach will require embedding awareness activities into existing PAs education and outreach activities.

## Knowledge Management

- Component 3 of the project is solely pursued to improve knowledge management and broader adoption of developed strategies in PAs. Through our inspection combined with the KIIs, the MTR established that activities under this component have made progressing in generating some important knowledge products. for example, two MSc students are in the final stages of defending their theses on cost-benefit analysis of selected invasive plants. results from these studies are expected to inform decisions on the management of the species in and around PAs. While stakeholders raised quality issues regarding the studies, the MTR confirms this to be a good starting point given the limited baseline number of IAS studies and awareness in the country.

- In addition to the studies, the project has also produced the NISSAP which also raises critical knowledge issues and proposed studies to understand IAS in the country. The MCFW has developed IAS Training Module and the college has also an integrated IAS content into existing curriculum. From a practical view, the project has produced an IAS Field Guide, a Communication Strategy, Newspaper articles, awareness materials (banners, calendars, jingles) among others. There have been several programs on TV, radio, local newspapers that have been aired on the project including community radios. The MTR part of deskwork has revealed that, the project collaborated with other conservation programmes to disseminate IAS messages to International Border and Customs staff in Malawi through a workshop. In summary, the MTR has inspected availability of the following knowledge products (i) Two draft theses on Cost-Benefit Analysis of IAS (ii) The National Invasive Species Strategy and Action Plan (iii) Introductory Module on IAS (iv) Preliminary Reports on IAS field Trials (v) Invasive Alien Species Field guide (vi) National IAS Communication Strategy.

## Sustainability

- The purpose of reviewing the sustainability of the project during is to set the stage for the Terminal Evaluation, during which sustainability will be rated by each of the four GEF categories of sustainability (financial, socio-economic, institutional framework and governance, and environmental). Sustainability is generally considered to be the likelihood of continued benefits after the project ends. Consequently, the assessment of sustainability considers the risks that are likely to affect the continuation of project outcomes.

### Financial Sustainability

- The IAS project gained attraction and attention of both NGOs and the Private Sector. For example, the BWB has taken an active role in IAS management through co-financing. Similarly, the Malawi-Zambia Trans frontier Conservation Project and the Peace Parks Foundation (PPF) are also funding some activities in NNP, including payment of labour for the removal of self-sown pine. Both the BWB and PPF have long-term interests in watershed conservation and biodiversity conservation, respectively. Hence, there is high likelihood of financial and economic resources being available once the GEF assistance ends.  To create an enabling environment for continued financing the two PAs should explore the possibility of establishment of financial and economic instruments and mechanisms to ensure the ongoing flow of benefits once the GEF assistance ends (i.e., from the public and private sectors, income generating activities, and market transformations to promote the project’s objectives).

### Socio-Economic Risks to Sustainability

- The removal of Pinus patuala initially raised public outcry. However, through consultations and campaigns, the level of awareness has increased so far. The MTR does not find potential political or social risk that may jeopardize sustainability of project outcomes.  On the contrary, findings based on the FGDs suggested that the level of project acceptance has been increasing among the PA adjoining communities. There is also a sense of ownership of the project among stakeholders by the EAD which has institutionalized the NISSAP and the private sector which is co-financing IAS activities. Although government resources in PAs are limited, the integration of IAS activities into PA Management Plans is the right direction for long-term sustainability.

- The development of the Communication and Outreach Strategy, and subsequently its implementation is expected to extend awareness of IAS project aims and objectives. While the strategy has been criticized of being too ambitious, it has a good starting point to facilitate collective action through established institutional structures. For example, MEPA has now an established National Coordination Unit which will be dealing with all activities pertaining IAS at country level. The recruitment of staff to handle administrative aspects of the unit will see the long-term attention to IAS in the country.   While the project has made strides to raise awareness and engaging stakeholders, it is not clear as regards to documentation of lessons learned being documented on a continual basis. However, there is an established website which could be utilized to achieve this.  In terms of capacity building, the MTR has established that the project has influenced the MCFW to integrate IAS into their curriculum and implementation of the curriculum has begun. The curriculum targets the mid-career professionals who work in forest and national parks. This is an important intervention for sustainability.

### Environmental Risks to Sustainability

- Successful restoration of IAS impacted areas depends on both technical skills as much as environmental factors. Fruitful replanting of Mulanje Cedar on MMFR is contingent on favorable climate as well as fire management.  Observation in the field saw the engagement of labouers in firebreak making. This will enhance outcomes and results, so far achieved. However, in the long-term, civic education activities around the PAs on the dangers of uncontrolled fire will be required besides undertaking prescribed fire operations to reduce potential impacts in the event of its occurrence. Rating: Moderately Likely (ML)

## Monitoring and Reporting

- The MTR noted that supervision requires taking an adaptive management as stipulated in the ProDoc. Risk assessment and rating is an integral part of the PIR which the MTR confirmed in the PIR. Similarly, the quality of project M&E was reviewed and rated as part of the PIR. Key financial parameters are monitored quarterly to ensure cost effective use of financial resources. The project noted that the emergency of the COVID19 pandemic led to changes in the mode of operations. For example, PSC meetings were sometimes conducted virtually.  Similarly, the scheduled trainings could not proceed due to the COVID19 pandemic, but this does not appear in the PIR or indeed any formal communication documents. However, there were also issues such as the slow procurement procedures which required prompt reporting but did not receive much attention. The PIU has challenges of timely report which must receive attention as required. While some issues can be reported on a regular basis, others require prompt attention.

# CONCLUSIONS AND RECOMMENDATIONS

- The MTR was commissioned to provide information for fine-tuning of workplans, budgets and implementation arrangements for the second half of the project, as well as introducing mechanisms towards improving project approaches and impacts, based on a review of project progress besides the project performance against the outcome indicators as specified in the ProDoc. The overall findings and performance of the Project are concluded in this section and recommendations are made for improvement where performance has lagged.

## Conclusions

- The Project has made varying degrees of progress across the four areas of outcomes, but the overall progress can be invariably rated as Satisfactory while some areas need more time for improvement to ensure attainment the end-of-project target (Table 16). Significant progress has been registered under Outcome 1 concerning strengthened national IAS policy and improved national capacity and coordination amongst different government agencies and the private sector to respond to existing and new IAS problems.

Table 17: Summary Of The Review Findings

| Criterion | Overall Rating |
| --- | --- |
| A. Strategic Relevance | Highly Satisfactory |
| 1. Alignment to MTS and POW and the GEF strategic priorities | Highly Satisfactory |
| 2. Relevance to regional, sub-regional and national environmental priorities | Highly Satisfactory |
| B. Effectiveness | Satisfactory |
| 1. Delivery of outputs | Satisfactory |
| 2. Achievement of direct outcomes | Satisfactory |
| 3. Likelihood of impact, where appropriate/feasible | Likely |
| C. Financial Management | Satisfactory |
| 1.Rate of spend | Satisfactory |
| 2.Quality and consistency of financial reporting | Satisfactory |
| D. Efficiency | Satisfactory |
| E. Monitoring and Reporting | Satisfactory |
| 1. Monitoring design and implementation | Satisfactory |
| 2.Project reporting | Satisfactory |
| F. Sustainability | Moderately Likely |
| I. Factors Affecting Performance |  |
| 1. Preparation and readiness | Satisfactory |
| 2. Quality of project management and supervision | Satisfactory |
| 3. Stakeholder participation and cooperation | Highly Satisfactory |
| 4. Responsiveness to human rights and gender equity | Moderately Unsatisfactory |
| 5. Country ownership and drivenness | Satisfactory |
| 6. Communication and public awareness | Highly Satisfactory |
| Overall project rating | Satisfactory |

- Under Outcome 1.1. the project is to realize strengthened national IAS policy and improved national capacity and coordination amongst different government agencies and the private sector to respond to existing and new invasive species problems throughout Malawi, with a focus on protected areas and their adjoining agro- ecosystems. The project has developed a NISSAP as a national framework for the cross-sectoral management of IAS operational and supporting long-term development planning. The NISSAP also contains some strategies for PAs to undertake. A CU within MEPA has been created and implementation is ongoing.  There is ample evidence to conclude that, capacity is being enhanced and that sectors concerned with biodiversity and IAS are beginning to work together as coordinated through structures established by the Project. Progress has also been made in terms of generating evidence base for informing policy and supporting IAS prevention and management in and around PAs. At the time of the review, two students out of three had almost completed their MSc research on cost-benefit analysis of priority IAS. Findings of these studies are envisaged demonstrating the long-term policy direction in dealing with the problem of conflicts of interest relating to invasive alien plants that have commercial value. Notwithstanding, it is not clear as regards the subsequent steps after the three studies have been concluded. A policy dialogue will be an ideal underrating to start influencing policies and decisions. to make use of the findings.

- Capacity building in form of training a target of 80 PA staff in identification and management of IAS has made tremendous progress although it was challenging to meet the target for gender balance as planned. PA staffing is generally skewed towards males and, thus the gender imbalance is inherent within the institutions responsible for PA management. Processes to establish the Biocontrol BWG have culminated although the introduction of three host specific and damaging biocontrol agents has not yet been concluded. n terms of achievement of end-of-project GEF core indicators, including (i) area of degraded agricultural land restored, (iii) area of forest and forest land restored (IAS removed inside the two PAs and (iv) area of natural grass and shrublands restored, the MTR established that, the achievement so far has surpassed the targets. It is expected that by the end of the project more will have been achieved.

- On communication, the Project has developed a Communication and Outreach strategy. Several NGOs such as WESM, Total Land Care are using it in disseminating messages through campaigns in media, workshops and meetings (targeting government officials, PA staff and affected communities). In addition, the MTR has confirmed the development of a Guide on identification and management of invasive plant species in Malawi. However, the copies are waiting printing. As regards, M &E, the Project has developed an M&E program although there is no evidence to suggest IAS monitoring capacity building among PA’s and their agro-ecosystems.

- The findings demonstrate that the GEF additionality, including global environment benefits, through the Project activities, outputs and reporting are being resailed.  The removal of IAS in both PAs and the restoration of degraded areas such as the replanting of Mulanje Cedar are contributing to he expected global benefits of this project include contributions to reducing the loss of biodiversity and reducing the negative impacts of IAS on national economies and local livelihoods.

- The MTR raises gender imbalances and Environmental and Social Safeguards as main challenges rocking greater achievement at the midterm of project implementation. The direct beneficiaries are both men and women although the number women is generally less than the MTR target of 40%. It is unlikely that without increasing deliberate efforts to encourage participation of women, the target will remain below the target of 40%.  The MTR has established progress made on promotion of ssustainable farming practices such as Farmer Managed Natural Regeneration (FMNR), Conservation Agriculture (CA), including crop rotation, crop integration and cover cropping adopted and promoted by more than 50 households because of training and demonstration trials. This component has overachieved the gender equity as data indicate a 58% achievement. As for the ESS, the MTR found that, the project design is rigorous enough but there lacks evidence of implementation of the ESMP. The Project has not created awareness of HIV and AIDS among workers, littering and negligence in use of PPEs are among the main issues of concern.

## Recommendations

- Recommendation 1: The level of progress made so far in response to ESS site issues remain is a concern raised by the MTR and calls for urgent attention. Engage environmental and social safeguard expert to intermittently provide independent monitoring of ESMP implementation.

- Recommendation 2: The MTR confirms that gender has been integrated across the three project components but the level of progress in implementation is below the midterm target.  The project should make deliberate efforts to increase the level of women participation in the remaining part of the project.

- Recommendation 3: The design of the project should imbed activities to increase awareness among workers and surrounding villages about gender-based violence and the dangers of STIs and HIV/AIDS and distribute condoms and IEC materials on STIs and HIV/AIDS.

- Recommendation 4: UNEP-GEF should consider extension of the project to a period of six (6) months based on observation made in the PIR backed by outcome 3 analysis of this MTR and perspectives of some stakeholders.

- Recommendation 5: During implementation, Malawi has experienced socio-economic changes including the devaluation of the local currency, the scarcity of foreign, the rising costs of gas and the emergency of the COVID19 pandemic. These have negatively affected the efficient and effective delivery of the project. In line with recommendation 4 and economic changes that have affected Malawi’s economy, UNEP-GEF should consider revision of the project budget to cater for activities which will cover the six (6) months period. Should the budget be revised, more money should be allocated on the studies since they already exhausted the allocated resources.

- Recommendation 6: The Technical Advisor should expedite some of his activities including the field trials and the development of the species-based management plans, among others.

- Lesson 1: Active engagement of stakeholders in dealing with IAS allowed for effective collaboration which resulted in creating a common ground of understanding of the problem and taking shared responsibilities for action. E.g., the PIU is working with the Blantyre Water Board, CARD, MMFR and MMCT of which each of these organizations has its role to play for a common goal, yet all from a background of varied interests. In addition, the partnership among UN agencies has resulted in cost-effective and efficient program delivery and demonstrated effective collaboration and coordination among UN agencies and a valuable model for future program delivery within biodiversity conservation.

- Lesson 2: Strong coordination leadership is an important success factor in the implementation of the project so far. For the EAD as a coordinator, despite this being the first IAS project to coordinate exhibited has clear direction coupled with enthusiasm and visionary character that propels the process despite internal bureaucratic and procurement challenges.

- Lesson 3: For sustainability, effective planning and implementation of IAS project requires strong involvement of the private sector, and civil society, including community-based and youth organizations with clearly defined roles and translated into implementable activities.

# Annex 1 - List of Consulted Individuals

| NAME | Designation |
| --- | --- |
| Edson Sichali | Research Officer (NNP) |
| George Ngumayo | Project Coordinator, TFC |
| Mphatso Kalemba | Project Coordinator (EAD) |
| Max Zieren | UNEP Task Manager |
| Dr. Lilian Chimphepo | M&E Coordinator |
| Eric Mbingwani | Project Site Coordinator (District Forestry Officer, Mulanje) |
| Gift Nyirenda | Local Technical Committee Chair (Rumphi)District Forestry Officer Rumphi |
| CARD OLESI | NGO-Mulanje |
| Ibrahim Mitole | MMCT |
| Chipiliro Kapichi | MMFR Officer |
| Viva Kagunya | Total Land Care |
| Jones Sibale | Nyika National Park |
| William Nkhazi | Training Beneficiary |
| Gift Lucky Ntambo | Training Beneficiary |
| Gift Nyirenda | Training Beneficiary |
| Anthony Chikwemba | Site Coordinator (Nyika) |
| Dr. Arne Wit | Project Technical Advisor |
| Dan Ndalowa | Forestry Trainer- Malawi College of Forestry and Wildlife |
| Nakhonyo Village, T/A Mkanda, Likhubula, Mulanje District |  |
| Ivory Kaliati | Community member |
| Robert Patrick | Community member |
| Albert Wale | Community member |
| Radson Mpondo | Community member |
| Chitsanzo Suwedi | Community member |
| Pitman Jarson | Community member |
| Bright Mpawa | Community member |
| Luka Tikhiwa | Community member |
| Elizabeth Henderson | Community member |
| Oliver Chinomba | Community member |
| Donata Baluwa | Community member |
| Grace Mandeya | Community member |
| Melisy Nikisi | Community member |
| Anne Kalulu | Community member |

# Annex 2 – Summarised Terms Of Reference Of The Mid-Term Review For Malawi Invasive Alien Species Management Project In Malawi.

Background

The UNEP/GEF funded ‘Enhancing sustainability of Protected Area systems in Malawi, and stabilizing agro-production in adjoining areas through improved IAS management’. With a total budget of USD 6,666,658 of which USD 5,164,147 is co-financing – mainly from Environmental Affairs Department, CABI, Peace Parks Foundation, Mulanje Mountain Conservation Trust and other national partners, and USD 1,502,511 financed through a GEF grant. The project objective is to prevent new invasions and reduce the current impacts of invasive alien species (IAS) in protected areas and adjoining agro-ecosystems in Malawi. IAS are one of the biggest threats to biodiversity and livelihoods. In Malawi IAS are adversely affecting locally and globally significant biodiversity, and are invading and threatening a range of habitats, as well as, indirectly, the livelihoods of millions of people depending on natural ecosystems for food, commodities and energy security. Malawi has recognized the need to implement Article 8 (h) of the CBD to mitigate the threats of IAS. This GEF project aims to enhance the capacity of Malawi to manage IAS, especially in protected areas and surrounding agro-ecosystems, by strengthening existing national and protected area specific frameworks for the prevention and management of IAS. A multi-sector approach, targeting the identification and management of high risk pathways to prevent the introduction and further spread of IAS and biocontrol of the worst IAS is being employed. The project seeks to (1) establish national framework and capacity to enhance IAS management in protected areas and associated agro-ecosystems (2) strengthen on-the-ground IAS management in existing protected areas through invasive species control and habitat restoration, as well as in adjoining agro-ecosystems through sustainable farming for improved welfare, and to (3) improve knowledge management and broader adoption of developed strategies in Malawi protected areas. International cooperation has brought in expertise to develop best practices for the management of selected invasive species. The project is also investing in raising awareness of IAS nationally which will be one of the most important means to increase the willingness and levels of core government funding to IAS management, all of which are rather low in the two target sites. By addressing the following priorities and establishing an integrated work plan at site and national levels, the project will meet several GEF policy objectives: Establishing national policy and institutional frameworks; National capacity building and institutional support; Developing expertise on the prevention, control and management of priority IAS in protected areas; Implementing national information, monitoring and awareness programmes. Targeted global benefits of this project include contributions firstly to reduce the loss of biodiversity and maintain the quality of protected habitats in the PA system of Malawi by initially focusing on two PA’s, Nyika NP (NNP) and Mount Mulanje FR (MMFR), and secondly, as an indirect benefit by reducing the negative impacts of IAS on local livelihoods and the economy of Malawi. IAS management activities in agri-ecosystem areas adjoining these PA’s will also reduce potential future threats of IAS present there that may invade these PAs, threatening biodiversity and increasing future PA management costs. Based on numerous studies from around the world it is obvious that invasive plants have a dramatic impact on biodiversity. By managing invasive plants that are already present in NNP and MMFR and surrounding agro-ecosystems the project will contribute significantly to biodiversity conservation. Communities will also benefit from the project’s IAS management interventions, as IAS have a significant impact on the goods and services provided by ecosystems. By addressing IAS management among communities living in areas adjacent to PA’s, the project also will reduce negative IAS impacts on the protected areas themselves, both by removing IAS populations that might spread into PAs, and by protecting agricultural production from negative IAS impacts and thereby reducing the reliance of rural communities on resources within PAs. Project interventions will also reduce pesticide use, one of the biggest contributors to biodiversity loss in agro-ecosystems. Reduce pesticide use will improve water quality and risks associated with their use to human and livestock health In order to address these issues and contribute to biodiversity within and adjacent to these Protected Areas and reduce pressures on them from adjoining agro-ecosystems, the project has developed a National Invasive Species Strategy and Action Plan, improving coordination and cross-sectoral management at a national and local level (especially between PA staff/management and adjoining communities as IAS cannot be managed in isolation); identify and manage IAS pathways (IAS being introduced into PAs and adjoining agro-ecosystems); improve prevention and EDRR mechanisms (include the use of Pest Risk Assessments); manage invasive plants within two PAs and surrounding agro-ecosystems (include the development of best management practices for selected IAS); and built capacity and create awareness about the threats and management of IAS. Full details are found in the formally endorsed UNEP/GEF Project Document which is an integral part of this MTR consultancy. Although the project initiation workshop was held on 10 July, 2018 activities were only initiated in early 2019 As such the project to undertake a midterm review (MTR) latest by late-2021, for which an independent evaluation consultant is to be selected and contracted. GEF procedures necessitate the execution of a project MTR on all Projects. The MTR has as a main goal the fine-tuning of work plans, budgets and implementation arrangements for the second half of the project, as well as introducing mechanisms towards improving project approaches and impacts, based on a review of project progress as well as the project performance against the outcome indicators as specified in the Project Document. MTRs are considered an integral part of GEF projects and the responsibility of the UNEP Task Manager – in collaboration with the project executing agencies and should be based on an independent and transparent consultation process involving all key stakeholder groups. MTR findings and recommendations will be reviewed and endorsed by the Project Steering Committee (PSC), and subsequently taken over and addressed by the NEAs (Environmental Affairs Department, Department of Forestry and Department of National Parks and Wildlife) and its main Project Partners in various project sites.

Objective: The MTR has as a main goal the evaluation of progress to date using the indicators as a benchmark for project progress, rating project impacts/performance based on standardized criteria, possible fine-tuning of work plans for the second half of the project, improving project approaches and optimizing implementation arrangements, based on a review of progress on execution as well as the achievement of project indicators as specified in the Project Document. The review will assess, amongst other things: - The effectiveness and efficiency of project management and supervision of project activities; - The production of planned outputs and milestones, in terms of quantity, quality, usefulness and timeliness; - Project performance in achieving project objectives and outcomes; - Project performance against quantified criteria; - Project progress against available and spent budget (GEF & co-finance); - Sustainability and replicability of project achievement towards outputs and outcomes to date - Compliance with environment, social and economic safeguards, as well as a gender Based on this: - The Consultant and his/her team shall make recommendation on how to continue and improve project implementation during the second half of the project; - Confirm and/or recommend any specific redirecting of program activities; - Confirm or change key outputs, deliverables and activity benchmarks; - Confirm or change the logframe, including indicators and targets; - Advise on project institutional arrangements; - Advise on project approaches towards stakeholder groups and other beneficiaries; - Suggest any needed approaches to better achieve project objective and outcomes. The MTR consultant shall prepare a short Inception Report during the first two weeks of the assignment, on the MTR process, timing and deliverables, as well as adoption of the UNEP MTR report format. Various Tools are available from UNEP with regards the approach, criteria and formats for a MTR – it is advised that the MTR consultant studies these materials prior to conducting the review. The MTR consultant shall conduct in-depth review of secondary data, conduct interviews as well as conduct field visits to project site(s) to compile, capture and evaluate project information and prepare the consolidated MTR Review Report. The consolidated MTR report shall also provide a summary review of the GEF project approach and methods used during the first years towards achieving the project objectives and outcomes. The review shall also highlight lessons learned and/or best practice features for expansion, the replication in Malawi and strengthening of the GEF project portfolio, in particular. The review of sustainability and replicability of the project will be an integral part of this. Deliverables and Verifiable Indicators - Inception report & work plan prepared and approved by UNEP and the lead NEA (Environmental Affairs Department). - Field visits conducted to a representative selection of the project sites and project field intervention. - Inclusiveness in sampling project stakeholders through review meetings, carefully structured questionnaires, skype/phone interviews, face to face meetings or other ways, involving targeted protected area staff, farmer groups, local and national government, private sector where applicable, and related science institutions, as well as project management and GEF and co-finance partners, to assess project progress, performance and related review aspects, - Presentation of summary findings and recommendations at the next Project Steering Committee meeting – provisionally planned for early April 2022, likely through a physical meeting or hybrid format based on the Covid situation. - Consolidated MTR Report, including recommendations and action plan for implementation. First Draft ready by 15 February 2022 for a 10 days review by project management, project steering committee, and key project partners, GEF focal point, and UNEP; and final version to be submitted to UNEP 15 April 2022 (or earlier if possible). - Consultancy completion report (max 3 pages) to be submitted to UNEP by 30 April 2022. Methods of the review - Desk review of project documents, outputs, national and Project Steering Committee minutes, half-yearly progress reports, annual Project Implementation Reports (PIR), consultant- and sub-contractors technical reports and deliverables, and the UNEP/GEF Project Document; - Review of GEF tracking tools, including data at midterm (to be completed by the GEF project EA prior to the MTR); - Expenditures reports against expected cash-flow, including on co-finance delivery; - Review of public communication activities, publications, media support, websites, etc; - Review of major sub-contracts and their deliverables; review of local partnerships; - Field visits to a good representative sample of pilot sites, farms and related programs; - Face-to-face and e-mail/phone/skype interviews of selected project implementers and stakeholders including a selection from: - Project Management Unit (Environmental Affairs Department in Lilongwe) - UNEP TM (meet virtually) suggested to meet prior to the assessments in Malawi - Members of Project Steering Committees - Lead government agencies including Department of National Parks, Forestry Department, Malawi College of Forestry and Wildlife, National Herbarium and Botanical Gardens their related units; - CABI - Total Land Care, Lilongwe Wildlife Trust, CARD Mulanje Mountain Conservation Trust, Peace Parks Foundation and relevant NGOs partners, - Farmers and Farmers’ Organizations - Other government, institutions and individuals involved in the project Evaluations will be quantified and summarized in the Consolidated MTR Report, following UNEP GEF evaluation criteria, as attached in Annex 1 to this ToR. Detailed tasks for the MTR Consultant - Lead, conduct and report on the MTR; - Ensure a consultative review process is used; - In close consultation with the PMU and the UNEP Task Manager, prepare an Inception report and Work plan during the first two weeks of assignment; - Use the Project Framework/Logframe tracking form, assess compliance with ‘Key Deliverables and Benchmarks’, and the capacity score card to assess project progress, performance and impact as against agreed indicators & targets at midterm; - Review all available project documents, outputs and other deliverables for the project; - Review the GEF-Tracking Tools applicable such midterm performance against baseline; - Compile and review co-finance delivery, as against the project plan ; - Review progress, GEF expenditure to date, as against the cash flow prediction in the project document; - Conduct fact finding as well as field site visits to Malawi , including a selection of at least 1 of the targeted protected areas and at least 1 of the adjoining agro-ecosystems of Nyika National Park and Mulanje Mountain Forest Reserve - Consult with key persons, stakeholder groups and organizations through meetings, interviews, e-mail or phone, on project progress and performance; - Determine the likelihood of sustainability and replicability of current outputs and the anticipated situation after completion of the project (continued delivery of services and benefits; long-term institutional capacity; support from key stakeholders; financial sustainability); - Capture issues and suggest possible mitigation measures on problems related to: project implementation, project approach, institutional aspects, stakeholder issues, financing, sustainability and replicability of project impacts; - Focus on key project issues and problems and prepare recommendations for implementation; - Capture lessons and best practices; - Assess overall project progress and performance to date; using the standardized criteria and rating; - Provide a summary review of the approach and methods used to date in achieving the project objectives and outcomes. Recommend any modifications or changes; - Prepare the Consolidated MTR Report, including Summary of Key Findings, Recommendations and Action Plan (what, by who, by when completed) for follow up by the project during the remainder of the project (see Annex 2 for guidance on table of Contents for the MTR Report); - Present key findings and recommendations at the Project Steering Committee meeting for endorsement - Whilsst beinbg under contract with the NEA, the MTR consultant will coordinate with and be responsible to the project PMU, and report to the UNEP Task Manager. Specific key review questions on technical aspects (for guidance): - Strengthened national IAS policy and improved national capacity and coordination amongst different government agencies and the private sector to respond to existing and new invasive species problems throughout Malawi, with a focus on protected areas and their adjoining agro-ecosystems. - National framework for the cross-sectoral management of IAS operational and supporting long-term development planning. - Evidence base informing policy and supporting IAS prevention and management in and around PA’s - Two revised PA Management Plans including strategies and budgets for IAS prevention and control - Tested management plans for four IAS, including IAS control and habitat restoration in two PA’s - Capacity of 80 PA staff improved and applied in the identification and management of IAS - Biocontrol Working Group (BWG) established and operational leading to the introduction of three host specific and damaging biocontrol agents - Level of progress made towards End-of-project GEF Core Indicators (see PIR reports): Indicator 3.1: Area of degraded agricultural land restored (farmland cleared of IAS) - 100 ha; Indicator 3.2: Area of forest and forest land restored (IAS removed inside the two PAs) - 50 ha; and Indicator 3.3: Area of natural grass and shrublands restored (adjoining rangeland enhanced forest cover) - 150 ha. - Indicator 11: Number of direct beneficiaries disaggregated by gender as co-benefit of GEF investment – Midterm 125 (40% women) and End-of-Project 230 (40% women) - Invaded rangelands (100 ha total) in buffer zones/agro-ecosystems of two adjoining PA’s cleared and restored (native trees) through enhanced partnerships between PA staff and farmer communities, including the training of 100 farmers on IAS identification and management - Sustainable farming practices such as Farmer Managed Natural Regeneration (FMNR), Conservation Agriculture (CA), including crop rotation, crop integration and cover cropping adopted and promoted by 50 households as a result of training and demonstration trials - Communication strategy and outreach campaigns including used of media, workshops and meetings (targeting government officials, PA staff and affected communities) - National information sharing procedures including the development of a Guide on identification and management of invasive plant species in Malawi - Project M&E program, evidence of IAS monitoring capacity built and implemented in PA’s and their agro-ecosystems - Is the project clear with regards achieving GEF additionality, including global environment benefits, through its activities, outputs and reporting; - Level of integration of gender in both project management, technical interventions, knowledge sharing, budgeting as well as project monitoring; - Does the project communicate its approach, successes and best practice adequately, both nationally in Malawi or abroad? Specific key review questions on project management, financing and administration: - How well and timely does PMU consult, inform and report to UNEP as GEF IA; - Has the project succeeded in establishing adequate project management and reporting capacity and procedures, including those related to an international-funded project; - Is the project using its GEF resources wisely and responsibly; - Is the M&E system quantified enough and have gaps in e.g. baseline and indicators been amended during the first year(s) of the project; - Is co-financing and related partnership effectively integrated in project budgeting for project activities and deliverables; - Is the project transparent, fair and effective (for attaining maximum project performance) in information sharing, reporting, budgeting and decision making?

# ANNEX 3 – DATA COLLECTION TOOL FOR THE MTR

# Enhancing sustainability of Protected Area systems in Malawi, and stabilizing agro-production in adjoining areas through improved IAS management

MIDTERM REVIEW

# KEY INFORMANT INTERVIEW GUIDE

INTRODUCTION

The UNEP/GEF is funding a project ‘Enhancing sustainability of Protected Area systems in Malawi, and stabilizing agro-production in adjoining areas through improved IAS management’. The project objective is to prevent new invasions and reduce the current impacts of invasive alien species (IAS) in protected areas and adjoining agro-ecosystems. Time has come to reflect on progress made this far in implementation of the project.

I would like to request your time to respond a few questions intended to generate information for Midterm Review of the Project.

Name:……………………………………………………………………………………………………………………………..

Phone:…………………………………………………………………………………………………………………………….

Email:………………………………………………………………………………………………………………………………

SECTION A– SPECIFIC KEY REVIEW QUESTIONS ON TECHNICAL ASPECTS

Q1. 	What has the project done so far to strengthen and improve the following:

- National IAS policy?.......................................................................................................................................................................................................................................................................................................................................................................................................................................................................................................... ................................................................................................................................................................................................................................................................................................................................................

................................................................................................................................................................................................................................................................................................................................................

- National capacity and coordination among different government agencies and private sectors focusing on Protected Areas (PAs)?..................................................................................................................................................................................................................................................................................................................................................................................................................................................................................................................................................................................................................................................................................................................................................................................................................................................................................................................................................................................................................................

........................................................................................................................................................................................................................................................................................................................................................................................................................................................................................................................

Q2. 	What kind of national framework has been developed so far for the cross-sectoral 	management of IAS in the country? Can I have the draft?

…………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………

Q3. 	Is there a supporting long-term development planning for the management of IAS? 	Is it operational? Explain how it works?

…………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………

Q4. 	What kind of studies have been conducted to generate evidence base informing 	policy and supporting IAS prevention and management in and around PA’s? Please 	list down the studies:

…………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………

……………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………

Q5. 	Apart from those listed above, are there other sources of evidence established by 	the project to inform policy and management of IAS around PAs? Please explain.

………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………….

…………………………………………………………………………………………………………………………………

Q6. 	Has the Management Plan including strategies for Nyika/Mountain Forest 	Reserve been revised?  If not, why and when will this be done?

………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………….

Q7.  Are there developed and tested management plans for four IAS, including IAS control and habitat restoration for Nyika/MMFR? Please show me.

………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………….

Q8.	How many staff have been trained so far to improve their capacity and are 	applying the skills and knowledge in the identification and management of IAS?  	Please show me training reports or similar documents to support this.

………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………….

………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………….

Q9.	Has the project established Biocontrol Working Group (BWG)? Is it 	working?

………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………….

………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………….

Q10.	How much area (ha) of:

- the degraded agricultural land been restored (farmland cleared).

- the forest and forest land restored (IAS removed inside the two PAs).  and

- the natural grass and shrublands restored (adjoining rangeland enhanced forest cover).

Q11.	How many people have directly benefited directly as co-benefit of GEF investment 	– Midterm?  How many of the beneficiaries are women and how many are men?

………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………….

Invaded rangelands (100 ha total) in buffer zones/agro-ecosystems of two adjoining PA’s cleared and restored (native trees) through enhanced partnerships between PA staff and farmer communities, including the training of 100 farmers on IAS identification and management.

Q12.	Mention any kinds of partnerships that have been developed so far to clear 	invaded rangelands (100 ha total) in buffer zones/agro-ecosystem of cleared and 	restored (native trees).

Q13.	How many farmers have been trained on IAS identification and management 	around Nyika/MMFR?  Explain more about the nature of training. How many were 	men and how many were women?

………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………….

………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………….

Q13. 	How many farmers have been trained in Sustainable farming practices such as 	Farmer Managed Natural Regeneration (FMNR), Conservation Agriculture (CA), 	including crop rotation, crop integration and cover cropping adopted and 	promoted?  How many were men and how many were women? Explain more 	about this training.

…………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………

Has a communication strategy been developed? Show me a copy of the same?

How many outreach campaigns including used of media, workshops and meetings (targeting government officials, PA staff and affected communities) been conducted so far? Is there any proof of the same to show? How many were men and how many were women?

Have National information sharing procedures including the development of a Guide on identification and management of invasive plant species in Malawi been completed? Please show me documentation.

What kind of activities have been undertaken to build capacity for Project M&E of the program? Where is evidence to support this claim?

Is the project clear with regards achieving GEF additionality, including global environment benefits, through its activities, outputs and reporting;

Level of integration of gender in both project management, technical interventions, knowledge sharing, budgeting as well as project monitoring;

Does the project communicate its approach, successes and best practice adequately, both nationally in Malawi or abroad?

SECTION B – SPECIFIC KEY REVIEW QUESTIONS ON PROJECT MANAGEMENT, FINANCING AND ADMINISTRATION

- Provide me with your quarterly and annual reports prepared to the UNEP and GEF IA. How timely are the reports?

Examine the timing of reporting for evidence of timely reporting

- What kind of challenges have you been meeting in terms of reporting to UNEP and GEF?

- Seek explanation from the PMU

- Probe the details

- Has the project succeeded in establishing adequate project management and reporting capacity and procedures, including those related to an international-funded project?  Explain please how this has been achieved.

- Is the project using its GEF resources wisely and responsibly;

- Has there been an M&E system? Is it quantified enough and have gaps in e.g. baseline and indicators been amended during the first year(s) of the project?

Please indicate the co-financing and related partnership in project budgeting for project activities and deliverables.

A. Co-financing

| Co financing (Type/ Source) | IA own Financing (mill US$) |  | Multilatéral Agences (Non-GEF) (mill US$) |  | Bi-laterals Donors (mill US$) |  | Central Government (mill US$) |  | Private Sector (mill US$) |  | NGOs (mill US$) |  | Other Sources* (mill US$) |  | Total Co-Financing (mill US$) |  | Total Disbursement (mill US$) |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Proposed | Actual | Proposed | Actual | Proposed | Actual | Proposed | Actual | Proposed | Actual | Proposed | Actual | Proposed | Actual | Proposed | Actual | Proposed | Actual |
| Grant |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Credits |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Loans |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Equity |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| In-kind |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Non-grant Instruments* |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Other Types* |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| TOTAL |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

- Is the project transparent, fair and effective (for attaining maximum project performance) in information sharing, reporting, budgeting and decision making?

Check the following:

- Compliance with governing laws of procurement……………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………….............................................................................................................................................................................................................................................................................................................................................................................................................................................................................................................................................................

- Budget reports

................................................................................................................................................................................................................................................................................................................................................................................................................................................................................................................................................................................................................................................................................................................................................................

- Financial and non-financial disclosures

........................................................................................................................................................................................................................................................................................................................................................................................................................................................................................................................................................................

- Auditing

.................................................................................................................................................................................................................................................................................................................................................................................................................................................................................................................................................................................................................................

Enhancing Sustainability of Protected Area Systems in Malawi, and Stabilizing Agro-production in Adjoining Areas Through  Improved Invasive Alien Species  Management

FIELD REPORT FOR PREPERATION OF THE MTR REPORT

Enhancing Sustainability of Protected Area Systems in Malawi, and Stabilizing Agro-production in Adjoining Areas Through  Improved Invasive Alien Species  Management

FIELD REPORT FOR PREPERATION OF THE MTR REPORT

INTRODUCTION

This document is a Field Mission Report based on interviews and direct observations conducted  to verify the project progress in NNP and MMFR.  The field research was conducted following the desk research that the consultant undertook.  The consultant embarked on field missions  to achieve the following objectives: (i) To observe the existence of any available strengths and weaknesses of the current initiatives in IAS management against project goals, objectives and outcomes. (ii) To interact with the key stakeholders on the ground with the aim of generating their perspectives on the project progress (iv) Conduct further consultations with smallholder farmers and stakeholders around NNP  and MMFR.

NNP FIELD MISSION

NNP is in the northern part of Malawi, and within the park lies a plateau above 1800 m that forms the core of the Nyika National Park.  The plateau covers an area of over 1800 km rich in biodiversity and ecosystem services. However, there are several significant threats to this biodiversity which originated from Invasive Alien Species (IAS). The most problematic species in this regard are the Pine Pinus patula, Black wattle Acacia mearnsii, bracken fern and Rubus. They are difficult to eradicate owing to long lived seeds in the soil like Black Wattle and Rubus.

The field mission learnt that there has been a high impact of these IAS on a variety indigenous species including farms for surrounding villages of NNP which now bring a situation of food insecurity due to low harvest for their crops.  Interviews with the Project Site Coordinator suggested that a number of activities supported by KFW and GEF Medium-sized project have taken place which includes the joint baseline surveys where experimental plots were established for Black Watttle, Rubus, pine and blacken fern. Other stakeholders supporting these experiments include the  of forestry and the Environmental Affairs Department These experimental plots are aimed at finding out the best management practice to be adopted to control these IAS on Nyika Plateau.

Treatment that these species are being subjected to includes; physical removal (uprooting, cutting), chemical application and cultural control or a combination of these, in the form of demonstration trials. It has taken 2-3 years of experimental time. Experimental sites were identified in these protected areas to test different approaches for controlling and managing IAS to identify the most appropriate and effective intervention that can be adopted at national level. Depending on targeted species, trials compared the efficacy of manual removal of the rootstock or hand pulling versus cut-stump (herbicide application to the cut-stump) or scrape and paint treatments.

Black wattle – experiments on black wattle included uprooting, slashing, chemical application, and cutting.  Areas were demarcated into 5 x 5m quadrats. application of a chemical called Turbordor was done in some selected quadrats and other quadrats underwent ring barking treatment and the chemical was applied around the tree.

Rubus – All plants in randomly selected treatment plots were physically removed using the tree popper ensuring that the rootstock is removed to prevent the plant from re-growing. Removed plants were stacked outside of the plots. Chemicals known as Impala and Performer were applied at the Rubus transect. Last year monitoring was done to see the effectiveness of the chemicals. It was found that chemicals are one hundred percent effective because all Rubus plants which were applied with chemicals were found dead.

Pine (Pinus Patula) – This is one of the most dominant invasive alien species that is found in Nyika National Park. Among other effects, pine displaces indigenous vegetation found in Nyika hence the need to physically remove pine. The project of physically removing pine started in January 2021. They have mechanically managed to remove more than 70 hectors of pine.

Figure 1: Experimental Plot for Pinus patula

Black wattle – In the observations of Black wattle, it was evidenced and reported that two experimental set-ups were done in areas invaded by Acacia merssii in Nyika National Park. The first experimental setup involved manual removal of A. merssii plants by uprooting and removal by cutting. Hoes were used to dig and remove black wattle stumps/roots that cannot be uprooted by tree popper. They have managed to remove 4 hectors under experimental. These are aimed at assessing biodiversity recovery after some observation time. The second experimental design was designed to assess the effect of chemicals and cutting on the A. merssii plants.

Figure 2: Black wattle plot after chemical application

Bracken fern (Pteridium Aquilinum) – This is the most dominating invasive indigenous species, and it has existed in abundance around Nyika Plateau including the surrounding farms. In the case of bracken fern, the treatments used are slashing, lime application and uprooting. There are two sites for Bracken Fern that were identified and different treatments were randomly applied.  These treatments include cutting/slashing, uprooting, and lime application, and some plots were left untouched as controls. Insect traps were also used to identify the biodiversity of the insects around the area.  These traps were done by setting test tubes in the center of each quadrat.

Hand removed plants were dried and then burnt, with the ash being used for K-enrichment of soils in adjoining crop lands. Lime is applied to neutralise the soil so that they should create a conducive environment for the growth of black fern. Eco-imazapyr, performer and forester were applied. Performer and forester were mixed and applied in five selected quadrats in each plot. Eco-imazapyr was also applied in five other selected quadrats in each plot. So far 2 hectares of bracken fern has been removed.

Figure 3: Treated plot of Blacken fern

The work of dealing with these IAS requires training for both officers and communities on the ground. Capacity building is one of the tools that will enhance successful implementation of the trials and practices after recommending the best option.  – The IAS program has conducted 1 training which involved less than 10 people all being men working at Nyika National Park.  The training took place at Chongoni Forest as an exchange visit.

Focus Group Discussions were one of the activities prioritized during the verification visit – Having done discussions with the project coordinator, the consultant engaged community members in a focus group discussion to establish their experience and how the IAS has affected them.  Upon request, the site coordinator representative Mr. Sibale organized community members around Nyika Plateau who are also laborers working on the IAS project.

The Park has employed about 30 unskilled laborers and 10 of them are women.  During the focus group discussion, the laborers revealed that they work from morning to 12noon and receive K2000 per day. This is above the average wage. They complained that K2000 is not enough compared to the type of work that they are involved in.  the work includes ring bulking, uprooting, slushing, and chemical application.  The surrounding communities are heavily affected by blacken fern to the extent that it has affected their seasonal harvest by half it was quantified that before blacken fern they used to harvest about 60 bags but now they harvest 30 bags from the same land. Despite all the efforts to remove blacken fern by using hoes and applying round-up in their fields, blacken fern has proven so stubborn and aggressively multiplying so widely.  This has reduced the cultivation land leading to a reduction of harvest and infertility of soils.  Apart from the laborers benefiting from peace works from the project, it is unfortunate that the affected community members who are not employed have not received any training on how to deal with blacken fern affecting their farms.  It is also hard for the laborers to transfer the knowledge to other community members let alone practice on their farms because they spend most of their time at the workplace.

Figure 4: Focus group discussion with unskilled labourers in Nyika Plateau

Challenges – Apart from low wages the laborers complained of the following challenges:

- There are no first aid kits to help them in terms of accidents

- Capacity building is not provided

- The project hasn’t offered any training or awareness on social issues such as HIV

- Insufficient working materials such as panga knives, gumboots, work suits, and raincoats.

- Lack of necessary equipment such as flat files. Flat files are used for sharpening pangas.

- Despite getting low wages, casual workers have always been paid late which is very demotivating.

Some of the challenges that NNP is facing are:

- Growth of animal feed has reduced due to blacken fern creating a food insecurity situation for animals.

- Most areas are affected by fire breaking especially the main stand.

- Lack of working equipment like chainsaws most of them worn out due to unskilled laborer usage.

- Lack of support from the government in terms of resources.

- Government funds are not adequate they rely on project funds

- There is not enough accommodation for workers which limits the employment of more human resources

- Lack of training for farmers

MMFR FIELD MISSION

Having visited NNP, the consultant took a step further to execute another field of research in Mulanje Mountain.  At Mulanje mountain, the main IAS are Mexican pine (pinus patula), Himalayan raspberry (Rubus ellipticus), Bracken fern (Pteridium aquilinum), and American foxglove (Digitalis purpurea).  These IAS have transformed habitats and displaced native plants.  Just like in Nyika National Park, trials to come up with the best solution to eradicate these IAS are in progress.

Capacity building through trainings has also been done on extension workers, forest guards and forest assistance.  However, these trainings did not extend to labourers and other community members. The only benefit the community is getting is the pieces of works and knowledge on invasive species. The target villages are not part of the labourers. Labourers get on the site training to remove. What I am getting is that we should also target the trainings to the labourers.

Focus group discussions were conducted to establish the engagement of community members in the project of eradicating these IAS.  6 women from Nakhonyo Village, T/A Mkanda, Likhubula were engaged in these FGDs and explained that their involvement is through peace works.  They are contracted to weed on the natural trees, slush and uproot blacken fern and remove pine through cutting.   It was discussed that the cutting of pine is not effective because the pine keeps on regenerating rather it needs to be uprooted. Each worker is allocated 0.5 acres and is paid K2000 per day which is the minimum wage.  They are oriented on which plants are referred to as IAS and no training are provided. They normally go up the mountains and stay there for 5 days or more.  Food is not provided they source their own food throughout the whole stay up the mountain. It becomes difficult because they must take loans from friends to buy food to sustain them up the mountain considering the low wages they get.

Safety is not granted once they meet an accident, they take care of themselves, and they are not provided with work suits. But this is an issue of the PPEs being inadequate Situations become extremely difficult in winter because there is snow on the mountain, and they have inadequate shoes or warm clothes.  They freeze as they get to the mountain and survive on fire upon arrival and the whole stay.  No protective measures are provided.

On one occasion they were made to work for 4 days and got paid only for K3000 for the work of K8000 but this was perhaps not to so with the project.  This affected the involved community members because they had to borrow money to survive in terms of food for the days, they were working only to be paid fewer days.  They did not manage to pay the loan and had to find other ways of repaying the loan.  It was revealed that the officer illegally had the other money for his personal use. The issue is still under investigation and the laborers were promised to have their money back once the investigations are done.

Figure 5: Focus group discussion with community ladies in Mulanje

Gender dynamics:  Reports form the focus group discussions revealed that the process of employing labourers ensures that gender is being mainstreamed. Men and women are equally considered for the peace work. However, social awareness is not provided i.e trainings about HIV and AIDS, distribution of condoms e.t.c.

Members present

- Elizabeth Henderson

- Oliver Chinomba

- Grace Mandeya

- Donata Baluwa

- Anne Kalulu

- Melisy Nikisi

The second fgd was with men who benefits from the forest through wood collection. Malawi –Wood Energy Project of the World Bank that was implemented during 1980-1993 which among its objectives aimed at increasing fuelwood production through tree planting by establishing a limited number of Government plantations of pine trees in ecologically fragile areas such as Mulanje mountain. Blantyre Water Board (BWB) also planted 19 500 pine trees in 2017 in Chambe Basin on Mulanje Mountain in fulfilment of an agreement made with the locals to replenish the mountain before taping water from it.

Invasive Alien Species project activities.

The arrangement was to remove pine trees and the project was to find alternative livelihoods to the communities. Most of the pine that was removed by the current project was the one planted by Blantyre water board and most of them were still young trees, however, the process of cutting at soil level was not appropriate because observation have shown that they are regenerating.

Furthermore, the communities were not consulted on conception of the project, and neither the consulted on the implementation of the project, consequently, were not made aware. Meetings for awareness were conducted but may not have reached other areas which is normal given limited resources.

Benefits from the IAS project

- Pine provided wood for timber and provided revenue much better than cedar because cider was over protected

- Tourism is a major benefit especially birds

- The tree cover in Mulanje mountain induces good rainfall around the mountain

- The indigenous trees in Mulanje provide source of traditional medicine

Suggestions to improve project activities

- The communities must be empowered and given responsibilities with sufficient funding. Allow the communities to conduct awareness campaigns on their own.

- The project, besides removing pine, must also consider removing Mkanda Nkhuku and Tambala plants/trees.

- The pine is regenerating and the project must consider uprooting the pine and not using the method of cutting at soil level.

- Project activities were not completed. It was planned and budgeted for 3 months but people worked for only 21 days.

- Mulanje Mountain must be cleared of any pine and NOT PLANT ANY TREE to allow Mulanje cedar do natural regeneration.

- The removed pine should be offered to communities for sale. The current method of burning them was observed to contact water downstream when the ashes get washed by rainwater. But this refers to a previous  project by the MMCT.

Safety Issues

- The project never provided any work suits etc

- The project areas has huge pits dug by the Mining Co. for Bauxite, and during the exercise of cutting pine tree, some people fell into the pits and got injured and there was not any compensation, neither any medical treatment given to them.

- There was no need for provision of protectants like condoms during the exercise because climbing the mountain and the intensity of the work left people without any extra energy for other social activities

Capacity Building: The project never provided any training on Invasive Alien Species and social in terms of HIV and AIDS as well as distribution of condoms to the community especially those employed as unskilled labourers etc.

Project Impact

- The communities identified reducing agricultural yields as the main threat followed by competition with medicinal plants and firewood.

- Communities expected to be provided with alternative livelihoods, however, communities were never considered.

- The communities were paid MK2000 per day for the job of clearing pine on the Mountain, however, cost of meals per day was almost MK2000 and therefore, the project did not benefit the communities financially

- Project implementation did not have prior consultations with communities.

Activities outside Mulanje Mountain

- There was a project that aimed at removed some alien plants outside Mulanje mountain.

- Pine trees are being planted and managed outside the mountain.

General issues arose after cutting the pine trees

- Observations showed that some of the pines are regenerating because they needed to uproot the entire root system rather than cutting at soils level.

- The team suggested that Government must plan to remove not only pine but also Tambala and Nkanda nkhuku because they are also invasive.

- Mulanje Conservation Trust (MCT) took over management of the Mulanje after the wood energy project. The communities indicated that MCT needed to provide sufficient awareness on the removal of pine both on the Mulanje Mountain and in the communities surrounding the mountain.

- Conservation of Mulanje cedar was observed to be interfered by Political interventions when Traders were provided with permit to cut Mulanje cedar with an objective of removing overgrown cedar. In the process, communities took advantage and begun stealing the cedar to the point of almost eradicating the Mulanje cedar.

- Springtone Ltd was provided with permit to mine Bauxite on Mulanje mountain in 2012, however, communities observed that the mining activities threatened conservation of Mulanje Mountain and therefore communities removed the company through violence.

Way forward

Treatments that will effectively control invasive species targeted and contribute to increasing species diversity will be recommended for adoption at the national level for controlling and managing IAS. Once the best management practices have been identified, they will then be implemented across a wider area including the affected community members. The FGDs and KIIs made the following recommendations:

- Employing additional laborers and training them accordingly.

- Salary increments for ground laborers-the current salary is K2000.00 per day

- There is a need for chemicals to remove the blacken ferns. But this is not working sufficiently.

- There is also a need for community training and awareness on how to remove blacken ferns and other IAS available.

- Purchase working materials such as gloves, gumboots, coats, work suits to protect them.

- The project should provide food for the workers during working hours especially in Mulanje. The project of removing IAS should continue until all have been eradicated.

# Annex 4 – A List Of Stakeholders Who Attended A Validation Workshop

# Annex 5 – Consultant Abbreviated Curriculum Vitae

Expertise: Understanding Dynamics of Natural and Agro-ecological Systems through modelling

Qualification: MSc-Tropical Resource Ecology, PhD-Production Systems Analysis

Table 1: Education Qualifications and Relevant Experience

| Duration | Qualification | Specialisation or Subjects | University |
| --- | --- | --- | --- |
| 2007 – 2010 | PhD | Socio – Ecological Systems Analysis | University of Cape Town, Cape Town |
| 1999 – 2000 | MSc | Environment and Tropical Resources Ecology | University of Zimbabwe, Harare |
| 1990 – 1994 | BSc | Physics/Mathematics | University of Malawi |

2019-2020: Impact Evaluation of Participatory Integrated Climate Services for Agriculture (PICSA) Under Saving Lives and Protecting Agriculture-Based Livelihoods in Malawi: Scaling Up the Use of Modernized Climate Information and Early Warning Systems (M-Climes) Project.

2020-2026: National Coordinator and Principal Investigator: National Ecosystem Assessment for Malawi.

2013: Technical Team member – National Coordination Unit for the Development of a  		Management Plan for Dzalanyama Forest Reserve

2013: Team Leader - A study for rehabilitation of the Lilongwe River Catchment and 		 subsequent implementation of the project.

2019-2020: Team leader – development of a national Strategy on Invasive Alien Species and Action Plan (NISSAP).

2013: A consultancy for the development of Climate Smart Agriculture Training Manual for 		Frontline Staff in the 	Ministry of Agriculture and Food Security

2012: Facilitator for a Mid-Career Training course on Agricultural Innovation Systems – Introduction to Agricultural Systems and performance Evaluation Sub-modules modules

2012:   Facilitator Training on Climate Change Impacts and adaptation. A project funded by the 		UNDP through FAO

2012:    Development of a training manual for climate change: A project funded by the UNDP 		through FAO.

2011:   Capacity Building in Agricultural Innovation System - A Stakeholder Demand Analysis  	for RUFORAM /Bunda College project

2007:	Team Leader - Training Needs Assessment for the Livestock Sector in the SADC Region 			– Project funded by ILRI for the SADC region

2005: 	Team member - Development of a Training Manual for the District Development System 		for Local Government in Malawi

MOST RECENT PUBLICATIONS

Kazembe, JA. 2010. Modelling the Influence of Rainfall Variability and different Grazing systems on the spatial Temporal Dynamics of Semi-arid Rangelands. PhD Thesis. University of Cape Town.

Kazembe, JA. 2009. Population dynamics of nyala (Tragelaphus angasii) and impala (Aepyceros) in Lengwe National Park, Malawi. Afr. J. Ecol., 48: 265–268.

Kazembe, JA. 2014.  “Why are wetlands floristically homogeneous, yet highly productive?” African Journal of Science and Research.  (3)2:25-33.

Kazembe, JA, Richardson, FD & H Laure (in Press). Modelling the Spatio-temporal Dynamics and Productivity of Semi-arid rangelands. Agricultural Systems.

Sitima, J & JA. Kazembe (2013). Changing the way a university teaches and acts beyond its walls; LUANAR’s experience In: Ochola Washington, Willem Heemskerk, Mariana Wongtshowski (Eds.) 2013. Changing Agricultural education from within: lessons and challenges from GO4IT programme. RUFORUM, KIT Publishers.

Heemskerk, W, E Kamau-Mbuthia, G Karubanga and J. Kazembe (2013). How have lecturers and universities Changed? In: Ochola Washington, Willem Heemskerk, Mariana Wongtshowski (Eds.) 2013. Changing Agricultural education from within: lessons and challenges from GO4IT programme. RUFORUM, KIT Publishers.

https://dx.doi.org/10.1079/CABICOMM-62-8140