| - GENERAL PROJECT INFORMATION |  |
| --- | --- |
| Country | Tanzania |
| Region | ESA |
| Grant Title | Food-IAP: Reversing Land Degradation Trends and Increasing Food Security in Degraded Ecosystems of Semi-arid Areas of Central Tanzania |
| Associated GEF Programme or Framework | The Integrated Approach Pilot (IAP) programme on Fostering Sustainability and Resilience for Food Security in Sub Sahara Africa (IAP-FS), GEF 6 |
| Grant Type (select one from GEF Trust Fund, LDCF, SCCF) | GEF TF |
| Reference numbers |  |
| PIR Number (1st, 2nd,3rd,4th, Final) | 3rd |
| GEF ID Number | 9132 |
| GEF Focal Area and Programme |  |
| GEF Focal Area | Multi-focal area |
| GEF OP or SP | Fostering Sustainability and Resilience for Food Security in Sub Saharan Africa IAP |
| Critical milestones |  |
| GEF approval date (CEO endorsement) | 01/06/2017 |
| IFAD approval date | 06/06/2017 |
| Actual implementation start date | 18/07/2017 |
| First disbursement date | 29 November 2017 |
| Expected/actual Mid-Term Evaluation date | 12-26 July 2021 ( tbc) |
| Expected project completion date | 30 September 2022 |
| Expected financial closure date (6 months after effective completion) | 31 March 2023 |
| Grant Financing (USD) |  |
| Cumulative disbursement as of 15 April 2021 of the reporting fiscal year ($) | 2,325,027 |

| - CONTRIBUTIONS TO INNOVATION and LESSONS LEARNED Please briefly illustrate current and emerging initiatives – if applicable |  |  |
| --- | --- | --- |
| 1. Information on Progress, challenges and outcomes on project implementation activities | - Progress since the FY20 update. Component 1: Institutional capacity building for sustainable land management and biodiversity conservation at landscape level Mainland Village Land Use Plans (VLUPs). Nzega, Mkalama and Magu districts supported the targeted villages in preparing the documentation for the issuing of Certificates of Customary Right of Occupancy (CCROs) for individual homesteads, crop and pasture land based on the VLUPs. A total of 2190 individual lands have been surveyed (700 in Nzega, 610 in Mkalama and 880 in Magu) based on which 956 CCROs are ready to be issued. Micheweni. The shehia land-use planning process has started for eight Shehia Land Use Plans (SLUP) with training and participation of eight Shehia Land Use Planning Committees (SLUPCs) and four new Shehia Natural Resource Management Committees complementing the four already existing. The LC-Zanzibar and Micheweni district staff were supported by the National Land Use Plan Commission (NLUPC) in the training and assisted the SLUPCs in developing their plans. Component 2: Up-scaling of sustainable and climate smart agriculture, land, water and The elaborated Community Action Plans (CAPs) resulting from the VLUPs propose solutions to land use and NRM challenges. In addition, 2850 individuals were trained on natural resources management through joint land use planning governance and conserving water, woodland and rangeland resources. Seventy-two FFS and NRM groups have so far been established in the five districts with 1671 members (918 males and 753 females of which 615 are youth). Recognising the high demand for access to water in all the CAPs, the support for establishing Community-Based Water Supply Organizations CBWSOs and investing in water infrastructures have been prioritized. For Micheweni district it is important that a water resources assessment report is developed for the shehias as part of their SLUP process. The Ministry of Water (MoW) has been working with the villages and the four mainland districts on detailed feasibility studies for the water investments identified in the water resources assessments done as part of their VLUP processes. The infrastructures include rehabilitation and construction of new charcoal dams, small river dams, and boreholes. The detailed studies for the water infrastructures have started in February 2021 and will be finalized by May 2021. Component 3: Monitoring and assessment Assessments and studies to inform component 2 interventions. The MoU with ICRAF-Tanzania for the land degradation surveillance framework, as well as the MoU with the National Carbon Monitoring Centre for carbon monitoring (Ex-ACT) are about to be signed. The collected and analysed data will be key for adjusting FFS curricula and conservation and sustainable use interventions. The contract for the consultancy services to undertake socio-economic and market analysis in every district was signed and data collection is undergoing. These analyses will be crucial for output 3.1 (income generation and improved market outlets). - Challenges. The project progress was hindered by the suspension of the project for a period of one year between July 2019 to July 2020. The suspension was due to changes in administrative regulations pertaining to the financing agreement of the project. On 29th of July 2019, IFAD received a letter from the acting PS of the VPO requesting an amendment to the finance agreement changing the name of the recipient signatory from the VPO to the Ministry of Finance and Planning. The Government decided that no further expenditures should be done from the project account until the amendment could be signed effectively putting the project on hold. IFAD prepared the requested amendment and submitted it for the governments’ consideration in October 2019. In July 2020, IFAD received a letter from the Ministry of Finance and Planning “approving the continuation of the GEF project Implementation” and confirmed that the financing was valid. During the suspension, districts were only able to progress on activities they could finance by their own co-financing. In addition, when the project resumed in July 2020, the meetings with the local communities were challenged by the COVID-19 pandemic. However, as recommended by the Tanzania Ministry of Health, the District Facilitation Teams have promoted preventive measures including social distancing and hand washing. During the last supervision mission held in December 2020, it was agreed that the PCU will develop a plan and budget for a no extension scenario, with the original completion date of September 2022. The plan focuses on priority actions to guarantee the project will still have significant impacts by its completion date. Proposed activities include: - Issuing of the remaining CCROs for individual land and the one CCRO for the Hadzabe communal land; - Investments in water-works with positive feasibility studies, prioritizing rehabilitation of existing dams and boreholes where sufficient groundwater resources are available and strengthening of CBWSOs and catchment conservation; - FFS for integrated climate smart agroforestry systems using conservation agriculture practices and integrating multiple use trees and fodder crops; and - Where possible (and time allows), support FFS groups in forming producer groups for improved commercialization of produce from their systems. The plan was finalised on the 25 March 2021 and received a No Objection from IFAD. - Adaptive measures and actions. Monitoring and Evaluation. Taking into consideration the remaining project period, instead of the MIS-based M&E system, the project will further develop its simple standardized MS-excel based system. This system will facilitate quarterly update on all indicators, improving the quality of progress reports, and consolidate all project achievements to ensure evidence on project outcomes is available. An IFAD M&E specialist will also build the capacity of both PCU and District Facilitation Teams (DTFs) in understanding the definitions of indicators and how to monitor so as to improve project effectiveness. |
| 2. Information on progress, challenge and outcomes regarding engagement of stakeholders in the projects/program based on the description included in the Stakeholders Engagement Plan or equivalent documentation submitted at CEO Endorsement/Approval | Despite the one-year suspension, from July 2019 to July 2020, the project team strived to achieve interventions related to the finalisation of VLUPs. The VLUP process was carried out by the project team in collaboration with NLUPC, the district and VPO/PCU in order to encourage participation of various communities and groups at the district and village levels. Women and youth actively participate in the discussions on VLUPs and the minority group (Hadzabe people) are involved in the VLUPC. One strength and major achievement of the project remains the strengthening of the institutional framework and settings through the establishment of VLUPs (which involved various stakeholders including the villagers, the VLUPCs District councils, Land Commission of Zanzibar, NLUPC, Ministry of Lands, and local authorities. The stakeholder engagement is most likely to improve land management, secure customary rights, and solve land-use conflicts, thus generating benefits to the target groups and the society in targeted districts. District focal points have established linkages with other donor-funded activities and community based initiatives. |
| 3. Information on progress on gender-responsive measures and my intermediate gender result areas as documented at CEO Endorsement/Approval including gender-sensitive indicators contained in the project results framework or gender action plan or equivalent | The project has now hired a consultant to conduct gender training on gender sensitive approaches in land use planning and agro-pastoral development at landscape level. The objective of this training is to strengthen the Project Coordination Unit, District Facilitation Teams, village natural resource management committees and farmer field school participants’ capacities on carrying out activities that actively contribute to reduce gender gaps and enhance gender equality and equity within the project target areas. |
| 4. Progress on the implementation of the project’s KM approach approved at CEO Endorsement/Approval | KM and visibility products that the project has reported are;- the development of brochures to introduce project areas; video clips of the project that have been disseminated in various media platforms; and a total of 5 television segments have been aired in national and local television stations. For communication, the project has a shared WhatsApp group between officers of the VPO and the PCU. During the last supervision mission, IFAD recommended to develop a clear KM action plan in order to provide a clear timeline, responsibilities, and accountability on KM activities. The project has several experiences that could be disseminated more widely through knowledge products such as the successful land-use planning process and resolution of long standing conflicts and the inclusion of the Hadzabe people in the multiple tribe village of Munguli. This success is an opportunity for the project to produce lessons learnt and knowledge management products on such innovative approach. |

| GEF - OVERALL PROJECT RATINGS Please indicate overall rate for IP , DO and Risk following tables 1 and 2 below |  |
| --- | --- |
| Implementation Progress (IP) Based on progress made for the given reporting period (HS/S/MS/MU/U or HU) | MS |
| Development Progress (DO) Based on the likelihood that by the end of the project, implementation will achieve its stated objectives (HS/S/MS/MU/U or HU) | MS |
| Risk Based on the overall risk of factors internal or external to the project which may affect implementation or prospects for achieving project objectives (H/S/M o L) | M |

| Table 1 IIMPLEMENTATION PROGRESS AND DEVELOPMENT OBJECTIVE - RATING CRITERIA |  |  |
| --- | --- | --- |
|  | IMPLEMENTATION PROGRESS (IP) | DEVELOPMENT OBJECTIVE (DO) |
| Highly Satisfactory (HS): | Implementation of all components is in substantial compliance with the original/formally revised implementation plan for the project. The project can be presented as “good practice”. | Project is expected to achieve or exceed all its major global environmental objectives, and yield substantial global environmental benefits, without major shortcomings. The project can be presented as “good practice |
| Satisfactory (S): | Implementation of most components is in substantial compliance with the original/formally revised plan except for only a few that is subject to remedial action. | Project is expected to achieve most of its major global environmental objectives, and yield satisfactory global environmental benefits, with only minor shortcomings. |
| Marginally Satisfactory (MS): | Implementation of some components is in substantial compliance with the original/formally revised plan with some components requiring remedial action. | Project is expected to achieve most of its major relevant objectives but with either significant shortcomings or modest overall relevance. Project is expected not to achieve some of its major global environmental objectives or yield some of the expected global environment benefits. |
| Marginally Unsatisfactory (MU): | Implementation of some components is not in substantial compliance with the original/formally revised plan with most components requiring remedial action | Project is expected to achieve of its major global environmental objectives with major shortcomings or is expected to achieve only some of its major global environmental objectives. |
| Unsatisfactory (U): | Implementation of most components is not in substantial compliance with the original/formally revised plan. | Project is expected not to achieve most of its major global environment objectives or to yield any satisfactory global environmental benefits. |
| Highly Unsatisfactory (HU): | Implementation of none of the components is in substantial compliance with the original/formally revised plan. | The project has failed to achieve, and is not expected to achieve, any of its major global environment objectives with no worthwhile benefits. |

| Table 2 RISK RATING CRITERIA |  |
| --- | --- |
| High Risk (H) | There is a probability of greater than 75% that assumptions may fail to hold or materialize, and/or the project may face high risks. |
| Substantial Risk (S) | There is a probability of between 51% and 75% that assumptions may fail to hold and/or the project may face substantial risks. |
| Modest Risk (M) | There is a probability of between 26% and 50% that assumptions may fail to hold or materialize, and/ or the project may face only modest risks |
| Lowest Risk (L) | There is a probability of up to 25% that assumptions may fail to hold or materialize, and/ or the project may face only modest risks. |

| MEASURING PERFORMANCE Please briefly provide narrative justification for the previous GEF Overall Project Ratings |  |
| --- | --- |
| Implementation Progress (IP) Achievements and impact to date – if applicable | Component 1 on Institutional capacity building for sustainable land management and biodiversity conservation at landscape level. - A total of 2190 individual lands have been surveyed (700 in Nzega, 610 in Mkalama and 880 in Magu) based on which 956 Certificate of Customary Right of Occupancy (CCROs) are ready to be issued. - 15 Village Land Use Plans (VLUPs) in the four mainland districts were agreed, physically demarcated on the ground, and submitted to the National Land Use Plan Commission (NLUPC). Hence, the output 1.2 on Governance instruments in place to support integrated landscape management and Sustainable Land management (SLM) target has also been fully achieved expecting an overachievement with the finalization of the SLUPs in Micheweni. - With 8 Joint village Land Use planning Committees (JVLUPC) established, the outcome 1 indicator (Number of functioning inter-village NRM committees supported) has been fully achieved. Despite the delays in the launch of Shehias Land Use Plans (SLUPs), the output 1.1 (number of district staff, village staff and community members trained) has been fully attained. The project has successfully trained in VLUP processes 47 district staff (against a target of 50), 161 village staff (against a target of 5 per village, 75), and 2848 community members (against a target of 3000) of which 862 (30.2%) are women and 890 (31.2%) are youth. - The project has successful supported the resolution of the land-use conflict in the Munguli village in Mkalama district with the Hadzabe hunter-gatherers, the Ratatoga pastoralists, and the Sukuma agro-pastoralists finally agreeing on their VLUPs. The Plan includes a forest conservation area that will be reserved for the Hadzabe hunting and gathering reducing the high vulnerability of their culture and way of life. Component 2: Up-scaling of sustainable and climate smart agriculture, land, water and pastoral management systems - Seventy-two FFS and NRM groups have so far been established in the five districts with 1671 members (918 male and 753 female of which 615 are youth). The FFS focus on four main areas: crop farming using conservation and climate smart practices; rangeland and livestock management; NRM groups for forest management and environmental rehabilitation; and Community-Based Water Supply Organizations (CBWSO). - The component 2 will implement priority interventions identified in the Community Action Plans (CAPs) produced as part of the VLUPs processes. CAPs include investments, management actions and capacity building around resources management and production activities. - Under the MoUs signed with the Food and Agriculture Organisation (FAO), Sokoine University of Agriculture (SUA) and Tanzania Trees Seed Agency (TTSA), refresher training of trainers in the FFS approach have been conducted with the participation of 38 staff from line ministries and the five districts. The existing FFS curricula have been tailored to the needs of the target villages and FFS manuals have been developed by experts from Sokoine and FAO. Some additional training of district staff is still needed before the FFS can be rolled out. - Recognizing the high demand for access to water in all the CAPs, the support for establishing CBWSOs and investing in water infrastructures have been prioritized. The feasibility study for drilling boreholes and constructing and rehabilitating small dams and charcoal dams has been done. Feasibility report for drilling boreholes have been completed. However, feasibility reports for the construction of new and rehabilitation of small dams and charcoal dams will be completed after the soil sample analysis. |
| Recommendations to improve IP | - Based on the last supervision mission recommendations, the PCU has developed a plan and budget for a no extension scenario (completion date Sept. 2022) refocusing on priority actions to secure the project will still have significant impacts by its completion date. Proposed activities include: - Issuing of the remaining CCROs for individual land and the one CCRO for the Hadzabe communal land. - Investments in water-works with positive feasibility studies, prioritizing rehabilitation of existing dams and boreholes where sufficient groundwater resources are available and strengthening of CBWSOs and catchment conservation. - FFS for integrated climate smart agroforestry systems using conservation agriculture practices and integrating multiple use trees and fodder crops. - Where possible (and time allows), support FFS groups in forming producer groups for improved commercialization of produce from their systems. |
| Development Progress (DO) Achievements and impact to date – if applicable | The project’s goal and development objective are to improve food and nutrition security in the targeted villages and reverse land degradation trends in semi-arid areas in Tanzania through sustainable land and water management (SLWM) and ecosystem-based adaptation. Based on the National Adaptation Plan (NAP), the design of the project identified overgrazing, deforestation and inadequate land use plans as the main drivers of land degradation. The project has adopted a landscape approach, where participatory village land use planning were conducted within newly established inter-village natural resources management committees. VLUPs have revived and strengthened customary and local institutions for resources governance and management. The VLUPs resulted in the issuance of CCROs as well as the CAPs. The priorities in the CAPs developed based on the participatory VLUP process clearly shows the relevance of the project design in terms of the needs of the participating villages to tackle unsustainable agricultural production and livestock management practices, degradation of catchments, increasingly unreliable rainfall patterns, scarcity of water and energy sources and limited capacity for environmental management. With the participatory development of the 15 VLUPs and their CAPs proposing solutions to land use and NRM challenges, important capacities have been built for 2850 village people for improving their management of natural resources through joint land use governance and conserving water, woodland and rangeland resources. The implementation of the CAPs through water investments and FFS, NRM groups and CBWSO is going to be crucial for also achieving the expected impacts on reversing degradation trends and improving ecosystem services in the landscapes. |
| Recommendations to improve DO | Based on the findings of the CAPs, the project will prioritize the investments in: i) catchment conservation; ii) rainwater harvesting, and other water infrastructure rehabilitation or construction; iii) climate smart agricultural production including agroforestry systems; and iv) rehabilitation of rangelands. During the supervision mission held in December 2020, it was also agreed that district focal point and service providers will assess proven and locally tested practices in terms of assisted natural regeneration, collection and broadcasting of seeds from native grass and shrub species or planting of tree seedlings of multiple use trees that shall be promoted in each site. The project is currently on its final stages of finalising an MOU with International Centre for Research on Agroforestry (ICRAF) Tanzania to conduct baseline study and regular assessment on biodiversity, carbon benefits, soil quality, water availability and land degradation. The Land Degradation Surveillance Framework (LDSF) is designed for landscape-level assessments of ecosystem health, including soil condition, vegetation condition, trends and diversity, land degradation status, carbon assessments and infiltration capacity. In addition, ICRAF and PCU must assess how best LDSF activities can be domesticated and institutionalized within the relevant Ministry in order to enhance sustainability. These discussions will inform the development of the project's exit strategy. These tools will serve as decision support for the landscape level NRM through the inter-village committees and land-use plans. They will also allow for reporting on the achieved global environmental benefits (GEBs) of the project. The project’s core strategy is to invest in farmers’ capacities to produce more sustainably through improved management of natural resources and ecosystem-based adaptation. However, given the status of land degradation in the semi-arid lands of Tanzania, the long lasting impacts will only be achieved if the underlying prevailing institutional barriers (including in particular the inadequacy of land-use planning, resources governance and supporting assessment and knowledge management systems) are eradicated. Because the project aims at upscaling good practices for long-term sustainability and resilience of food production by reducing land degradation and biodiversity loss, recovering natural vegetation and increasing soil carbon, these long-term benefits cannot be attained within a 5 years project lifespan. However, the project is promoting technologies for rapid uptake that will enable smallholder farmers to increase their food production quickly for visible impact and as reserves in case of climate shocks. In addition, to ensure the adoption of sustainable practices, the project is promoting improved incentive systems such as creation of small enterprises and producer groups, FFS, collaborative management of agro-pastoral spaces, farmer-based extension, as well as landscape based land use planning which will upscale investments in ecosystem approaches. |
| Risk level List key risks and measures implemented to resolve it | The project was on hold from July 2019 to July 2020, with its account not operating from September 2019 to July 2020, the limited implementation of activities planned in Annual Work Plan and Budget (AWPB) 2019-20 has significantly limited project progress for component 2 and 3 and further delayed the achievement of most project outcomes, the development objective and goal. Hence, with support from IFAD Project Delivery Team (PDT) the project has developed a plan and budget for a no extension scenario (completion date Sept. 2022, see attached appendix 1) refocusing on priority actions to ensure that the project will still have significant impacts by its original completion date. |
| Recommendations to reduce risk level | Given the delays encountered with project implementation, both PCU and IFAD Tanzania Country Office have elaborated a joint catch up plan to speed up project implementation and ensure that the project will achieve its objectives and goal. This plan is monitored through a weekly virtual catch up meeting to assess progress and tackle potential obstacles. At the MTR mission planned in June 2021, the PCU and PDT will evaluate the projects’ achievements and assess a possible extension which will allow the project to meet its development objective and enhance the prospect of sustainability. |

Appendix 1: LDFS NO EXTENSION SCENARIO IN SUMMARY

- Background

From 30th November to 04th December 2020, the International Fund for Agricultural Development (IFAD) together with the Vice-President's Office (VPO) conducted a joint implementation support mission for the project: Reversing Land Degradation Trends and Increasing Food Security in Degraded Ecosystems in Semi-arid Areas of Tanzania (LDFS). The objectives of the mission among others were to provide technical recommendations where needed; and develop an action plan for all prioritized activities and assign responsibilities.

One of the key mission agreements was to prepare plans and budget of two scenarios that will be a plan and budget for one-year extension to make up for the lost time due to project being on hold from September 2019 to July, 2020 with new completion date September, 2023 and second scenario of no extension plan and budget with completion date September, 2022. The PCU has prepared both scenarios with following explanation for No extension scenario.

- SCENARIO - NO EXTENSION SCENARIO:

The No Extension Plan and Budget scenario for the project starting from July, 2021 to September, 2022 includes all priority activities as discussed and agreed in the Aide-Memoire and the other few project activities.

The main refocused activities to be undertaken can be as follows:

- To complete the villages and shehia land use planning for issuing of the remaining Certificate of Customary Right of Occupancy (CCROs);

This activity will be implemented by District Land Office in collaboration with National Land Use Planning Commission. The team will also include Participatory Land Use Management (PLUM) and Village Land Use Management (VLUM) teams. The VPO and PCU will oversee the implementation of the activity.

In Land Use Planning processes to issue Certificate of Customary Right of Occupancy (CCROs) is part of Village Land Administration in the step five (5) which includes demarcation, survey and register private lands and prepare and issue CCROs.

The LDFS Project conducted Village land use planning processes up step five (5) that implies to continue with investments of activities such as CSA and CA in the land with legal status. However, this activity preceding to the final step (6) of Village Land Use Planning and Consolidation. The outcome of step five will enhance easier implementation of step 6 like preparation of Sustainable Management of different sectors such as forest management plan for the Hadzabe Community in Mkalama district which is underway. The PCU has therefore included issuing of CCROs in the budget to let the possibility of the final step (6) to be implemented by different sectors/actors sustainably for the benefit of the entire community.

Certificate of Customary Right of Occupancy (CCROs) is a sustainable way of completely solving the problem of land conflict between farmers thus encourage farmers interest in investing long term investments such as Conservation agriculture (CA) and Climate Smart Agriculture (CSA) as in Farmers Field School (FFS) on rainwater harvesting and micro catchment management as well as beekeeping in apiaries (catchment areas), tree planting, infrastructures like charcoal dam, small dam and bore holes water.

For sustainability purposes, the sense of ownership of Certificate of Customary Right of Occupancy (CCROs) will encourage the farmers to manage the investments (i.e. CSA, CA and IGAs) banked on the secured land. This implies the value addition of land with assurance of legal right of land ownership which empower individuals to access loans from the Financial Institutions like Banks.

The previous CCROs were prepared for few beneficiaries for one or two villages per district in the project site. Therefore, the remaining CCROs will be issued to the Munguli village (300) in Mkalama district and Haubi and Mafia villages (150) each for Kondoa district within the project landscape level.

To ensure sustainability, the activity will be under the District Land Office within the district in collaboration with PLUM and VLUM teams by operationalization, regular monitoring and by-laws enforcement of land use plans.

Generally, there is a link between CCROs with CSA, CA, afforestation, catchment, agroforestry and all investment banked on land thus Sustainable Land Management (SLM) attained under good integration of activities.

The table below show the initial number of beneficiaries and associated cost vs the revised number of beneficiaries and associated cost for CCROs

| Activity indicator | Initial target | Associated cost | Revised target | Associated cost | Additional cost |
| --- | --- | --- | --- | --- | --- |
| Number of CCROs issued | 2,100 | TZS 84,000,000 (USD 35,972.76) | 2,700 | TZS 108,000,000 (USD 46,250.70) | TZS 24,000,000 (USD 10,277.93) |

- Investment in Water by drilling boreholes, construct new and rehabilitate small dams and charcoal dams, conservation of water catchments and establishment of Community Based Water Supply Organizations (CBWSOs);

The feasibility study for drilling boreholes and construct and rehabilitate small dams and charcoal dams has been done. Feasibility report for drilling boreholes have been completed. However, feasibility report for construction of new and rehabilitation of small dams and charcoal dams will be complete after soil sample analysis. It is expected to drill 33 boreholes in Nzega, Magu, Mkalama and Kondoa.

Each village (15 villages) will drill one production well and monitoring well (this one will be used to monitor the groundwater flow dynamic and quality in that aquifer).

On other hand the project expected to construct new and rehabilitate 6 small dams and 7 charcoal dams in Nzega, Magu and Mkalama. The identification of water sources and feasibility study for water investment in Michweni will be done after completion of land use planning of eight Shehia and is expected to be finalized by May, 2021.

The activity will be under the District Councils in collaboration with Rural Water Supply and Sanitation Agency (RUWASA). RUWASA, which is under the Ministry of Water will provide technical backstopping on water investments within the district council. The Ministry of Water and Water Board Offices will oversee the activity implementation through close supervision in Tanzania Mainland. In Zanzibar particular in Micheweni the activity will be done by Zanzibar Water Authority with technical support from Ministry of Water and Water Board Office Mainland.

The sustainability of the water source from the geophysical studies and secondary data review show that ground water in that area is sustainable. In the case of depending on water harvest instead of drilling of borehole in a particular area, this may result because the morphology and terrain of the area does not favor the construction of dam/charcoal dam infrastructure so the only solution is to use groundwater.

Regarding the issue of assurance of getting water, the percentage of success is more than 75%, but the exact amount of water will be known after drilling, all the stages of geophysical exploration were followed and the next stage is to drill the exploration borehole (pilot boreholes) and this stage will assist us to develop production well and inform the design.

Also, the sustainability of the activity will be through the establishment of CBWSOs for management of each water investment facility within the locality. The CBWSOs will also be responsible for catchment protection to safeguard the water sources. The recharge area will be demarcated, protected and conserved.

The CBWSOs will have the roles to monitor, maintain and collect water fees and charges from the community water users. The fees will be used for repairs and maintenance of water investments supported by the project after phasing out of the project. This will be guided by Guidelines of Establishment and Registration of Community Based Water Supply and Sanitation Organizations of 2019 and Manuals.

Based on feasibility study conducted for dams and ground water sources, some of the ground water sources identified are far from people’s residence. Thus, additional investment in water was required to shorten the distance for water supply. Also, in order to improve management of water investments, the number of CBWSOs in five districts has increased from 27 to 54. The increase in number of CBWSOs has contributed to increased investment in water as reflected in the refocused budget.

Table below show project beneficiaries for water investments

| Activity indicator | Initial target | Associated cost | Revised target | Associated cost | Additional cost |
| --- | --- | --- | --- | --- | --- |
| Total infrastructures (33) boreholes, 6 small dams, 7 charcoal dams and 5 rainwater harvesting facilities) for FFS on ran water harvesting and micro catchment management. | 3,000 | TZS (USD) 2,030,000 | 8,622 (Excluding Micheweni | TZS (USD ) 2,709,628 | TZS (USD ) 679,628 |

- Farmer Field School (FFS) for conservation agriculture and climate smart agriculture;

FFS encourage reducing supervision of Extension Services Staff by delegating powers to selected model farmers in different thematic areas in line with project objectives and goals. Ongoing decentralization of activities will induce farmer’s self-dependence in undertaking CA and CSA as part of their daily practices in the diversity of crops suitable and tolerant to their environment. Model farmers will become trainers to the fellow farmers within their locality thus speed up the rate of adoption to many farmers within a short period of time. This will result into cost reduction and building farmers’ capacity unlike the previous approach of endless Farmers Training and Visit (T and V).

Mainstreaming of FFS in the project thematic areas (i.e. CA and CSA and Rain water harvesting) is a way of strengthening the existing framework under the Climate Smart Agriculture Guideline (May 2017). This will ensure sustainability of the established FFS.

The increase of CSA beneficiaries will not increase the budget because the FFS will not be conducted in the planned period of four years but only two years, thus associated costs of materials, workshop and Consultancy not fully utilized.

Table show the project beneficiaries for CSA

| Activity indicator | Initial target | Associated cost | Revised target | Associated cost | Additional cost |
| --- | --- | --- | --- | --- | --- |
| Number of farmers adopting CSA | 3,000 | N/A | 7,868 | N/A | N/A |

When deciding on the focused activities, the PCU take consideration of the Land Use Planning report of 2019 total area of the pasture land set aside for Nzega, Kondoa, Magu and Mkalama is 4,317.09 hectares which was the area targeted for FFS rangeland. It is important to include activities in tree nursery and woodland management as well as Rangeland management proposed to be retained so as to achieve the Project goal and objectives. Production of agroforestry species (i.e. multipurpose tree seedlings) in the tree nursery established will also add value of rangeland by improvement of pasture (fodder) through planting of agroforestry tree seedlings such as Leucaena leucocephala, Calliandra calothyrsus and Faidherbia albida. Implementation of these activities will favour high production of livestock in rangeland and zero grazing while reversing land degradation by fully utilizing the area (4,317.09 ha) set aside for rangeland.

- Support the development small business to link with the socio-economic and market analysis study and training.

This activity will be implemented by district councils and coordinated by departments of community development within the district councils.

This will be supported and guided by socio economic and market analysis study report findings and capacity building for facilitators of small business producer groups. The report will highlight the opportunities of small producer groups in each district.

There is existing structure within the district councils which supports women, youth and people with disabilities groups by providing 10% of district councils’ own source revenue every financial year as soft loans. These are guided by Local Government Finance Act 1982 and Credit Management Regulation 2019 as per government notice No. 286 of 5th April 2019 and are coordinated by the Community Development Departments within the district councils. Similarly, the established producer groups under the project will follow the existing structure.

- In this scenario the project plans to spend a total of USD 6,023,430 for the remaining project period as follows; In Feb. 21 – June 21 USD 1,191,859, July 21 – June 22 USD 4,336,252, and July 22 – September 22 USD 495,316.

New CCROs added are 600 whereas 300 are from Kondoa district in Mafai and Haubi villages, which previously were not registered to qualify for issuing CCROs and 300 from Mkalama district Munguli village where as more project investment are located in Munguli village, these include 3 boreholes and the proposed Hadzabe Community Forest Reserve. On the otherhandmore, livestock keepers and farmers are based in Munguli village that require CCROs for sustainability of these resources and project goal. From the table above the number of beneficiaries has increased from 3000 initial target with associated cost of 2,030,000 USD up to 8,622 beneficiaries with associated cost of 2,709,628 USD revised target with additional cost of 679,628 USD. Thus, less expensive for the new 600 CCROs because of the fact that other land use processes   from step 1 to  4 (i.e. demarcation of land use) have already been done including building land register Offices and set of some stationaries which reduces cost of additional CCRO for Mkalama district in Munguli village.

- Some of activities have been retained for the No Extension Scenario

- FFS in tree nursery and woodland management. The sub activities which will be retained are:

- To identify multiple- use tree species to be used for the different land use production and conservation activities.

- To facilitate and subcontract School environmental clubs/Youth/ CB0s, Private groups for the establishment and management of tree nurseries and Seedlings distribution.

- To facilitate capacity building on the use of identified improved cooking stoves (Consultant - Wood Consumption Survey and Training to institutions and households in the targeted villages).

- To identify and sensitize Institutions on energy efficient cooking stoves and accessories (Forester, Environment, DFP and CDO), and

- To promote the use of available fuels (rice husks, wood fuel, saw dusts, maize cobs) in efficient cooking stoves (Procurement and distribution of Cooking Stoves and Cooks to public institutions and sampled households of VLUM, VNRCs and VGT members)

- Participatory Forest Resources Assessment (PFRA) and prepare sustainable proposed Village Land Forest (VLFRs) management plans

- Boundary marking by installation of beacons to the proposed VLFRs for the management of the woodland

- FFS in rangeland management. The sub activities which will be retained are:

- To procure materials and equipment for zero grazing, Ngitiri management, pasture conservation, hay making and storage, animal husbandry and others for established FFS on sustainable rangeland management.

- Boundary marking by establishment of live fencing (agroforestry tree and sisal planting) and beacons installation in rangeland.

- To undertake participatory resources assessment and prepare sustainable rangeland management plans.

- Monitoring of carbon by EX-ACT. This activity will be retained as planned to be implemented by National Carbon Monitoring Center to undertake monitoring and evaluation (Baseline and End review) by using Ex-Ante Carbon Balance tool (Ex-ACT) as reflected in refocusing activities within the budget ceiling of 45,112 USD.

- To facilitate ICRAF to conduct baseline and end line study of biophysical, carbon benefits, soil quality, water availability, land degradation and site follow up for each district will be retained by costing 250,000 USD as planned within the ceiling of the refocusing budget.

- Major activities which have been excluded in this scenario are as follows:

- FFS in tree nursery and woodland management. The sub activities which will be dropped are:

- To facilitate capacity building for FFS on tree nurseries and sustainable woodland management

- To undertake enrichment planting in open degraded woodland

- To encourage natural regeneration/copping for value addition of woodland.

- To promote production, processing and marketing of Non-Timber Forest Products (such as beekeeping, fruit canning, edible insects (mopane) mushroom.

- To engage district council team on supporting the demarcation process for the proposed or declared reserved areas (i.e. VLF’s).

- FFS in rangeland management. The sub activities which will be dropped are:

- To conduct capacity building to FFS groups on sustainable rangeland management

- To establish traditional in-situ-fodder conservation systems and pasture management.

- To sensitize the use of residual crops for improvement of rangeland using molasses and Urea fertilizer.

Select from: Biodiversity; Climate Change; Land Degradation; International Waters; Chemicals and Waste; Impact Programs

Operational Priority or Strategic Priority

If necessary, please expand to 1 or 2 additional pages.

As per GEF- SEC Results Based Management Reporting Guidelines for GEF Trust Fund and LDCF/SCCF https://www.thegef.org/sites/default/files/documents/AMR%20Reporting%20Guidelines%20-%202012.pdf

If necessary, please expand to1 or 2 additional pages.