Integrated Landscape Management Gambia Project (INLAMAG)

[The Government of The Gambia]

[2000001065 GRIPS ID]

[27th February 2026]

## Table of Contents

Table of Contents	2

List of acronyms	3

Background	4

Overall implementation progress	5

Implementation arrangements	18

Monitoring and evaluation	19

Financial and fiduciary management	21

Main findings and conclusions	21

Annexes/Appendices	25

Annex 1:	Project logframe updated by MTR

Annex 2:	AWPB 2024 - 2025 physical progress report

Annex 3: 	INLAMAG GEF7 core indicators updated by MTR

Annex 4:	Mission terms of reference, field schedule and list of key persons met

## List of acronyms

| AICRM | Africa Integrated Climate Risk Management Programme |
| --- | --- |
| ANR | Assisted Natural Regeneration |
| AWPB | Annual Work Plan and Budget |
| CRR | Central River Region |
| DLS | Department of Livestock Services |
| DoF | Department of Forestry |
| DPWM | Department of Parks & Wildlife Management |
| ESMPs | Environment and Social Management Plans |
| GALS | Gender Action Learning |
| GCF | Green Climate Fund |
| GEF | Global Environment Facility |
| GoTG | Government of The Gambia |
| GRM | Grievance Redress Mechanism |
| IFAD | International Fund for Agricultural Development |
| INLAMAG | Integrated Landscape Management Gambia |
| IPs | Implementing Partners |
| LDN | Land Degradation Neutrality |
| LRR | Lower River Region |
| MIS | Management Information System |
| MoALFS | Ministry of Agriculture, Livestock & Food Security |
| MoU | Memorandum of Understanding |
| MTR | Mid-Term Review |
| NBR | North Bank Region |
| NEA | National Environment Agency |
| NEMA | National Agricultural Land and Water Management Development Project |
| PSU | Project Support Unit |
| ROOTS | Resilience of Organizations for Transformation of Smallholder Agriculture Project |
| SECAP | Social Environment and Climate Assessment Procedures |
| SLM | Sustainable Land Management |
| SRI | System of Rice Intensification |
| URR | Upper River Region |
| WCR | West Coast Region |
| USD | United State Dollars |

## Background

| Name of grant | Integrated Landscape Management Gambia Project |
| --- | --- |
| Name of recipient | The Government of the Gambia |
| Goal, objectives and target group(s) | Objective: To create an enabling environment for an integrated landscape approach in support of sustainable land management and land degradation neutrality implementation in The Gambia. Target groups: 80% women, 25% youths and 10% PWD |
| Target country(ies) | Republic of The Gambia |
| Date of grant approval | 11 July 2022 |
| Date of grant effectiveness | 9 January 2023 |
| Completion date | 31 August 2027 |
| Value of IFAD-funded grant (in US$) | 4,708,582 (Global Environment Facility) |
| Amount disbursed to date (in US$) | 821,438 |
| Total financing, including co-financing (in US$) | 33,909,682 |

## Overall implementation progress

Likelihood of achieving the development objective

- The Integrated Landscape Management Gambia (INLAMAG) project, funded by the Global Environment Facility (GEF) under its seventh replenishment cycle, co-finances the Resilience of Organizations for Transformation of Smallholder Agriculture Project (ROOTS) also known as the baseline investment. INLAMAG was approved by the GEF in July 2022, the Financing Agreement was signed in January 2023 and the first disbursement was received at the project level in October 2023.

- INLAMAG’s development objective is “to create an enabling environment for an integrated landscape approach in support of Sustainable Land Management (SLM) and Land Degradation Neutrality (LDN) implementation in The Gambia”. Despite a slow start-up in 2024, INLAMAG implementation gained momentum during 2025 with more interventions being rolled out in the project area. INLAMAG will thus likely achieve its development outcomes if implementation is maintained at the same pace and with coverage of more areas to reach LDN targets and Global Environment Benefits (GEBs). To date, INLAMAG has restored 10,949 ha (91.2% of target) of degraded agricultural land and brought 1,858 ha (5.1% of target) of agricultural landscapes under improved practices, through the delivery of the following outputs:

- 746 ha (99% of Mid Term Review (MTR) target and 50% of Life of Project (LoP) target) of area under three Integrated Water and Soil Management practices, namely smart valleys, system of rice intensification (SRI) and use of organic compost in production systems. The practices are undertaken by 176 (25% of LoP target) households from the communities of Yalal, Bintang, Berefet, Manduar, and Suwareh Kunda.

- 6,034 ha (161% of MTR target and 80.4% against a project end target of 7,500 ha) of land under improved bushfire management. More areas are planned to be sustainably managed in 2026.

- 18 ha (3.6% of MTR target and 2% against a target of 1,000 ha) of woodlots have either been established or existing ones enriched in all 11 project districts and more are planned to be established in 2026.

- 4,915 ha (218% of MTR target and 109% of LoP target) of degraded agricultural production landscapes have been rehabilitated through assisted natural regeneration and enrichment planting in wildlife parks and other protected areas surrounding agricultural lands.  An additional 7,000 ha under gazetted forest parks around agricultural productive landscapes is planned to be rehabilitated and restored in the remaining period of implementation as well as establishment of fodder trees in the rangelands in order to reclaim more area under Agro-silvopastoral practices.

- 1,000 (200% of MTR target and 100% against a project target of 1,000 stoves) jambar energy cooking stoves have been distributed among vulnerable households to improve efficiency in energy consumption.

- 964 ha (39% of MTR target and 19% against a target of 5,000ha) of land under agroforestry and sustainable and diversified cropping systems developed through establishment of agroforestry around vegetable and rice gardens. More will be covered through interventions at institutional and community levels.

- 130 ha (13% of MTR target and 7% against a target of 2,000 ha) of land under Integrated Crop-Livestock Systems to optimize the uses of crop and livestock resources established through seeding of rangelands and grazing areas with improved and indigenous pasture seed varieties.

- Some outputs may take time before they are translated into tangible outcomes. However, overall, the likelihood of achieving the development objectives remains high.

Outreach

- The INLAMAG Project employs a robust, multi-level engagement system that integrates community mobilization, institutional coordination, and targeted technical support to ensure broad-based participation in landscape restoration. This structured approach has successfully reached approximately 9,846 direct beneficiaries across all initial intervention zones. Through sensitization campaigns, household consultations, and participatory planning, the project rapidly mobilized farming communities. This grassroots dialogue was instrumental in identifying priority restoration sites and selecting context-appropriate tree species for agroforestry and Assisted Natural Regeneration (ANR). These efforts have achieved blanket coverage of all gardens and rice fields within the 11 pilot districts across the three target regions. Community engagement has directly accelerated on-ground outcomes, leading to the validation of 1,000 hectares for agroforestry and the mobilization of 30 communities for pasture development, resulting in 130 hectares of established community pasture to date.

- Going forward, the project will extend its activities to the remaining districts within the three regions being covered, West Coast, North Bank and Lower River. To enhance impact and ensure quality, the agroforestry target has been strategically recalibrated to 3,000 hectares, allowing for more rigorous monitoring and survival-rate verification. Restoration work is being integrated across the landscape, including enrichment planting in former National Agricultural Land and Water Management Development Project (NEMA) sites and protected areas, which complement widespread ANR activities.

- A critical component of the engagement strategy has been fortifying community-based fire management. Training and the provision of firefighting equipment to 61 community forest committees have enabled local groups to proactively manage 6,034 ha against bushfires, substantially reducing ecological and livelihood risks. Parallel initiatives focused on household energy efficiency, guided by national vulnerability data, led to the distribution of 1,000 improved jambar stoves to the most vulnerable households.

- Institutionally, the project maintains strong, continuous collaboration with key government agencies - including the Departments of Forestry, Livestock Services, Agriculture, Parks and Wildlife Management, and the National Environment Agency (NEA). This is operationalized through joint field missions and technical planning, ensuring alignment and amplifying impact across components like enrichment planting (now covering 4,915 ha in forest parks), woodlot expansion, and SLM.

- Gender sensitive outreach is integrated throughout implementation in line with ROOTS’ targeting approach complemented by the ongoing Gender Action Learning System (GALS) rollout in 25 INLAMAG/ROOTS communities. Overall, INLAMAG’s integrated strategy - spanning from household consultation to high-level institutional partnership - is designed to reinforce community ownership, foster inclusive participation, and secure the long-term sustainability of landscape restoration efforts.

Summary analysis of the updated log frame

- The foundation of INLAMAGs monitoring and evaluation system is the logframe. Based on the progress made against key performance indicators at MTR, some logframe targets are proposed to be revised to align with the broader objectives of contributing to the country’s LDN and GEB targets.

- The following changes have been proposed to the INLAMAG logframe:

- Increase the target of the area of land under improved bushfire management from 7,500 to 10,000 ha.

- Reduce the area under woodlots from 1,000 ha 500 ha.

- Reduce the target for Greenhouse Gas Emissions Mitigated from 2,936,362 to 10% of the national target.

- Reduce the area under agroforestry and sustainable and diversified cropping systems from 5,000 to 3,000 ha.

- Area under Agro-silvopastoral practices increased from 4,500 to 16,500 ha

- Other targets have been maintained. These include the following:

- Maintain the target of jambar energy saving cooking stoves to 1000. Activities to build local capacity for manufacturing the stoves will be incorporated in the 2026 AWPB.

- 2,000 ha of land under integrated Crop-Livestock Systems

- 15,000 ha rehabilitated through participatory soil, land and watershed management activities. The contract for development of Wet-Season Valley Water Control Cascaded Dykes and Micro-Catchments Runoffs Control Dykes was signed in April 2025 and construction is expected to commence at the end of the production season.

- 1,500 ha as area under Integrated Water and Soil Management practices.

AWPB 2024-2025 Execution

- INLAMAG implementation started in 2024 and gained momentum in 2025. The average implementation rate for activities planned during the 2025 financial year is 63%, with varying performances across components i.e. Component 1 - 60%, Component 2 -58%, Component 3 - 72% and Component 4 - 0%.

- Under component 1, the major activities implemented fully during 2025 include the drafting of the capacity development plan, gap assessment for additional infrastructure at Gambia SONGHAI Center, engagement of a contractor to undertake the civil works at SONGHAI Center, establishment of four farmer field school demonstrations with the participation of 116 farmers (109 females and  7 Males) and mapping and collection of georeferenced data in all 248 sites where the project is currently being implemented.  Activities not undertaken but planned include: (i) Stakeholder workshop for validation of the capacity development plan, (ii) Production, printing and dissemination of the final capacity development plan, and (iii) development of the maps/polygons and regional land use management plans.

- Under component 2, the project completed implementation of the following planned activities in 2025: (i) engaged International Technical Assistance to support the development of Smart valley in rice fields, (ii) development of Smart valleys for rice production for three communities namely Badumeh Koto in LRR, Suwareh Kunda in NBR and Farabanta in WCR, (iii) construction of four chambers in community vegetable gardens,  benefitting 666 beneficiaries (M 30, F 636, Y 279 and PwD 3), (iv) conducting of training on agrochemical handling and application to rice SRI intervention communities, (v) Provision of assorted production inputs to support SRI interventions in 24 selected rice fields, covering 730ha, and benefiting 1,555 farmers ( M 209 , F1349, Y 59 ,PwD 0) and (vi) identification and selection of five communities and benefitting them with 18 ha of woodlots through planting of 1,800 seedlings of Gmelina and 1,900 seedlings of Eucalyptus. The project was not able to carry out sensitisation and awareness campaigns on environmental sustainability and ecosystem conservation to additional potential communities and their eventual identification and selection to participate in the activities.

- Under component 3, the project planned and carried out the following activities during 2025: (i) sensitisation and awareness campaigns on integration of agroforestry in farming activities, (ii) Identification and selection of 25 communities to benefit from the agroforestry interventions, (iii) Provision of 41,000 assorted seedlings to the selected communities to establish 730 ha of agroforestry in vegetable and rice gardens, (iv) Facilitation of the signing of commitment letters for the securing of land for the development of the pastures and sustainable management of the rangelands for 30 communities, (v) seeding of 130 ha with improved pasture seeds for 20 of the 30 communities, (vi) recruitment of the contractor for the construction of the Wet-Season Valley Water Control Cascaded Dykes and for the construction of the Micro-Catchments Runoffs Control Dykes. The civil works are, however, yet to commence as these can only be undertaken at the end of the production season.

- No activities were planned to be carried out under component 4. These will be prioritized in 2026.

- The mission noted poor identification and description of activities as a major impediment in ensuring adequate monitoring and ensuring that intended activities are fully delivered and implemented within time. Hence the need to improve the description of the annual planned activities, providing sufficient details clearly identifying them and ensuring that there is clear linkage to expected performance targets for the project.

Component 1: Enabling environment for SLM and LDN mainstreaming and implementation

- Component 1 is designed to create an enabling environment for effective mainstreaming and implementation of SLM and LDN in The Gambia. This means developing policies, institutional arrangements, planning frameworks and capacity that support integrated landscape management rather than isolated site-based interventions.

- Expected outputs include the development of integrated watershed and landscape management plans, mainstreaming of SLM and LDN principles into national and sectoral policies, and the establishment of functional governance and coordination mechanisms across implementing institutions. The Project Support Unit (PSU) is further expected to deliver capacity-building and knowledge management initiatives, stakeholder engagement and participatory planning processes, and a monitoring and reporting framework to track land degradation and restoration outcomes.

- A consultant is currently developing an Institutional Capacity Development Plan and will subsequently cascade the acquired knowledge and skills to relevant stakeholders. These efforts represent key milestones in strengthening institutional and human resource capacities required to mainstream and effectively implement SLM and LDN initiatives.

Component 2: Implementation of integrated landscape planning and management to reduce land degradation and achieve LDN

- Under Component 2, the project targets the promotion of Integrated Water and Soil Management practices across 1,500 hectares of land area, rehabilitation of 12,000 ha of degraded agricultural landscapes through ANR and 7,500 ha of land having improved bushfire management. It is also expected that 4,500 ha of land are established with woodlots using multipurpose tree species as well as an establishment of 1,000 ha community woodlots integrated into the sustainable wood and biomass energy supply chain to strengthen sustainable biomass and community forestry management. A framework agreement was signed with the Department of Forestry (DoF), Department of Livestock Services (DLS) and Department of Parks and Wildlife Management (DPWM) for the implementation of key interventions, including Agroforestry, Community-led tree planting, Woodlot Establishment, and ANR of trees.

- Assisted Natural Regeneration of trees: 61 communities have been sensitized and supported to implement ANR activities within designated community forests. Currently, 6,034 ha (161% of MTR target) are under bushfire management. To strengthen protection efforts, firefighting equipment - including bicycles, rakes, fire beaters, buckets and cutlasses - has been distributed to all participating communities. The ANR interventions have contributed to strengthening community forest protection, reducing bushfire risks and enhancing natural regeneration. Field visits during the mission confirmed a strong sense of community ownership and participation among beneficiary groups. Communities anticipate improved rainfall patterns, increased tree cover, and availability of firewood as positive outcomes from protecting the forest. The provision of firefighting equipment has notably reduced the time and labour required for fire belt construction. However, the effectiveness of community fire management committees remains limited and requires further capacity support. Given the positive results achieved, the mission recommends expanding the ANR target by at least 2,000 hectares to sustain progress, extend fire management to unserved districts and strengthen the functionality and capacity of community fire management committees.

- Community-led tree planting: Tree planting activities were carried out across 30 communities in the three target regions, covering a total of 4,915 ha (82% of MTR target) with 45,030 trees planted. The main species introduced include Eucalyptus (Eucalyptus spp.), Cashew (Anacardium occidentale), Mango (Mangifera indica), Lemon (Citrus limon), and Gmelina (Gmelina arborea), as enrichment planting in protected areas contributing to reforestation, livelihood enhancement and ecosystem restoration efforts. To achieve the 12,000-ha project target for the rehabilitation of degraded landscapes, the mission engaged with DoF to identify forest parks requiring targeted restoration through ANR and enrichment planting. It was agreed to cover approximately 8,000 ha across priority sites, including NBR (3,860 ha in 8 parks), LRR (1,677 ha in 3 parks), and WCR (1,683 ha in 2 parks). These areas will form the basis for accelerated implementation toward meeting the remaining project target.

- Woodlot establishment: To date, the project has undertaken enrichment planting across 15.5 hectares of existing community woodlots and established an additional 2.5 hectares of new sites. Implementation of the woodlot activities has, however, faced challenges due to insufficient budget allocation, particularly for the establishment of fencing infrastructure required to safeguard seedlings from livestock damage. As a result, the project prioritized enrichment planting within former NEMA project fenced woodlot sites, leveraging existing protection measures to enhance tree survival. With the exhaustion of fenced NEMA project sites, it is recommended that the project adopt tree species less prone to livestock browsing, such as Eucalyptus and Neem, and revise the woodlot target from 1,000 to 500 ha for realistic implementation within the available budget. The revised approach should prioritize communities with at least 10 hectares of land and extend support to institutions with a minimum of 3 ha suitable for woodlot development.

- As part of the project targets, a total of 4,500 ha of land is also earmarked for the establishment of woodlots using multipurpose and agro-silvopastoral tree species. The activity, which was previously inadvertently captured under the community-led tree planting target, will be implemented by the Department of Livestock Services (DLS) across 11 districts, with a focus on nursery establishment, transplanting and propagation of fodder trees. This intervention aims to enhance sustainable livestock feed production, improve soil fertility and contribute to climate-resilient land management.

- Integrated Water and Soil Management Promotion: Implementation of these activities is yet to commence, as they were only introduced recently during the ROOTS project restructuring. The Smart Valley approach and the System of Rice Intensification (SRI) will be prioritised across the 11 project districts.

| Agreed Actions | Responsibility | Deadline | Status |
| --- | --- | --- | --- |
| Component 2 |  |  |  |  |
| ANR implementation Expand coverage of implementation of ANR activities within designated community forests by an additional 2,000 hectares, focusing on unserved districts. | DoF | March/2026 | Agreed |
| Strengthening Forest Committees Strengthen the functionality and capacity of community fire management committees | DoF | March/2026 | Agreed |
| Enrichment planting in forest parks Undertake enrichment planting in identified forest parks covering 8,000 hectares (5,000 ha 2026; 3000 in 2027) across NBR, LRR, and WCR. | DoF | June/2026 | Agreed |

Component 3: Promote SLM for Climate-Resilient and low emission agriculture for improved agricultural, rangeland and pastoral management

- Component 3 aims to improve agricultural productivity and livelihoods while restoring and conserving the landscape, reducing land degradation, and supporting long-term ecological balance across rural communities. Key activities include the integration of agroforestry and multipurpose tree planting within farmlands to enhance resilience, diversify production and restore degraded lands; the establishment and rehabilitation of rangelands and pastures; and the adoption of climate-smart agricultural practices such as improved soil and water management, conservation agriculture, and integrated crop-livestock systems.

- Community agroforestry and diversified cropping systems: The agroforestry undertaken by the project involves the planting of lime and orange seedlings along the periphery of gardens as live fence, while moringa were planted inside the garden to improve the soil condition and supplement household nutrition. In total, 234 hectares were established in 2024 across 11 districts in NBR, LRR and WCR and an estimated 730 hectares in 2025 under the rice field buffer-zone tree planting interventions. Approximately 47,000 seedlings were planted across 64 community gardens. Survival rate assessments conducted in 2024 in the gardens indicated 85% survival for lime, 21% for moringa, and 60% for sweet orange. To address losses, seedling replacement exercises were undertaken at affected sites to ensure continued progress toward project targets. In 2025, 18,595 seedlings were distributed and planted as a buffer zoning along the boundary of 23 rice fields with valuable tree species such as Eucalyptus, Gmelina arborea, Cashew, and Khaya senegalensis. Survival assessments are yet to be conducted. The mission recommends that this be done at the end of the dry season (May 2026).

- Communities recognize the importance of trees for soil protection, microclimate improvement, shade and windbreaks and in some cases, as a barrier against salt intrusion. Field visits to the vegetable gardens revealed high seedling mortality due to poor land preparation practices (slash-and-burn practices), termites attack, and poor maintenance, exacerbated by seasonal use of gardens. Lime and moringa adoption remain low, and DoF support has been limited to establishment with minimal monitoring and backstopping. To improve survival and scaling of agroforestry practices, additional training of nurturing of trees will be required for the communities, while technical backstopping needs to be strengthened.

- Given the constraints within the original 11 project districts, the target area is proposed to be reduced to 3,000 ha and implementation extended to additional districts in LRR (5), NBR (2), and WCR (4), including schools and mixed farming centers.

- Live fencing and buffer-zone planting around rice fields will continue, while incentives can be offered to groups achieving the highest survival rates. In subsequent planting cycles, the department should ensure planting before the dry season and conduct post-dry-season surveys to assess survival rates of trees planted in buffer zones. To address bushfire challenges during land preparation, the project should strengthen collaboration with Agricultural Extension Officers to continue sensitizing farmers in beneficiary districts.

- Rangeland establishment and management: The project has signed an MOU with DLS to lead the establishment of a 2,000 ha of community-managed rangeland under Integrated Crop- Livestock Systems. With a target of 600 ha for the first year (2025), DLS was able to establish only 130 ha across 24 INLAMAG intervention communities. Pasture species introduced in the rangeland include Panicum maximum (Guinea grass), Pennisetum purpureum (Napier grass) and Brachiaria brizantha (Brachiria grass). Available reports show that community mobilization and sensitization activities were carried out across WCR, LRR and NBR (30 participants per region) to raise awareness on sustainable rangeland management and pasture improvement. Farmers increasingly recognize the importance of pasture in supporting livestock feed and reducing grazing pressure on forests. Despite community enthusiasm, implementation delays and weak technical guidance reduced effectiveness. Late seed delivery (mostly in August) missing the optimal planting period (June-July) resulted in poor growth rate in multiple sites. The mission further observed limited consultation particularly where seed variety selection was often done without community input, as well as limited technical supervision or extension support during establishment phase.

- To achieve the project targets, DLS agreed to target 100 communities in 2026 and 2027, each with an estimated 20 hectares available for intervention. This ambitious plan will require additional regional-level equipment, including power tillers and ploughs to ensure timely land preparation and seeding. Technical backstopping on pasture establishment and management will be prioritized during the remaining implementation period to ensure sustainability and productivity gains.

- Jambar cooking stoves distribution to households: A total of 1,000 clean cooking and energy efficient stoves to promote sustainable energy use, reduce deforestation and improve household health have been distributed across the three regions. Five vulnerable communities in LRR received 78 stoves; 14 vulnerable communities in WCR received 303 stoves, while 619 stoves were distributed to 22 vulnerable communities in NBR. This achievement (100% of target) represents a major milestone in enhancing climate-smart and gender-responsive energy access, with strong community acceptance. Beneficiaries visited report reduced fuel use, less smoke exposure and reduced cooking time compared to traditional stoves. Beneficiaries expressed appreciation for the convenience, fuel savings and the easing household workloads when using the stove. Notwithstanding its benefits, some beneficiaries find the stove too high or incompatible with large cooking pots, requiring further assessment for technical adjustment. An assessment on the use and effectiveness of the stove, recommended in previous missions is yet to be undertaken. Moving forward, technical support for local production of improved stoves is recommended to enhance sustainability, accessibility and affordability.

| Agreed Actions | Responsibility | Deadline | Status |
| --- | --- | --- | --- |
| Component 3 |  |  |  |
| Technical backstopping for agroforestry Strengthen technical backstopping to ensure seedling survival and the scaling-up of agroforestry practices | DOF and Extension officers | Continuous | Agreed |
| Survival rate assessment Conduct post-dry-season survey to assess survival rates of planted trees/ pasture species | DOF/DLS | May, 2026 | Agreed |
| Jambar cooking stove Provide technical support for local production of improved stoves to enhance sustainability, accessibility and affordability. | PSU | March, 2026 | Agreed |

Component 4: Monitoring the Project Contribution to LDN

- Component 4 seeks to monitor, evaluate and report on the project’s progress toward achieving LDN, as well as broader SLM and integrated landscape management objectives. An LDN Information Hub will be established and operationalised as a mechanism for sharing and disseminating lessons learned to the target groups, along with a Knowledge Management Hub serving as a repository and mechanism to support and enable the dissemination of lessons learned to stakeholders. The mission noted that this is yet to be undertaken. The mission is concerned that LDN targets are contributed to by various institutions and hence the need for prioritisation of the undertaking. The mission thus encourages prioritisation and budgeting for initial dialogue meetings towards setting up the hub, within the 2026 AWPB.

- In addition to the LDN hub, the project is currently finalising georeferenced data collection for sites already reached with interventions and upgrading the Management Information System to ensure that there is efficient monitoring of the field activities and related targets towards improving the GEBs. To achieve this, the project has engaged the DoF to lead this exercise, expected to be completed by December 2025. The project should continue to follow up with the DoF to ensure timely completion of the task and ensure that geo-referenced data are collected upfront for all new intervention sites to strengthen monitoring and reporting accuracy.

- Further, INLAMAG investments have mostly been carried out at community level with communities exhibiting strong levels of commitment to participate in the activities. The community monitoring structures have however not been integrated with the project monitoring system. As recommended under the M&E section, project management is encouraged to prioritise the integration of participatory community monitoring approaches by developing and rolling out simple tools for use by the communities to enhance ownership and empowerment of the communities.

| Agreed Actions | Responsibility | Deadline | Status |
| --- | --- | --- | --- |
| Component 4 |  |  |  |
| Geo-referenced data of interventions Complete the geo-referencing of all existing INLAMAG intervention sites and ensure a systematic collection of geo-referenced baseline data for all new sites. | PSU/DoF | December 2025/Continuous | Agreed |

Targeting

- INLAMAG successfully aligns with the ROOTS targeting strategy, ensuring coherent beneficiary selection that reflects national priorities. By applying clear indicators related to poverty, vulnerability, remoteness, and productive infrastructure quality across 11 districts in the three regions, the project has effectively reached 9,846 people in communities most affected by land degradation and climate change risks. This systematic geographic and socioeconomic targeting has yielded substantial environmental and resilience results, including the validation of 1,000 ha for agroforestry, support for restoration and ANR activities, the distribution of firefighting equipment enabling communities to manage 6,034 against a 7,500-ha target, and the distribution of 1,000 improved Jambar stoves. These interventions have successfully prioritized and reached vulnerable households, women, youth and remote communities.

- However, a critical gap in monitoring limits the ability to fully assess the inclusivity of these outcomes. While ROOTS maintains comprehensive gender- and disability-disaggregated data collection, INLAMAG has not yet fully implemented this practice. Establishing robust disaggregated data systems - capturing not just participation but also benefits received and leadership roles held by different demographic groups -would significantly enhance monitoring capabilities. This would enable more precise, adaptive, and inclusive targeting, ensuring that the project’s reach translates into equitable benefits and that no groups are inadvertently marginalized within the supported communities.

- Furthermore, the project faces inherent challenges in engaging persons with disabilities (PWDs) in its core, physically demanding forest-based activities. The rigorous nature of bushfire management, ANR work, and forest park operations presents substantial accessibility and safety limitations, which can act as a barrier to participation. This reality underscores the importance of proactively developing adapted and innovative participation pathways. Rather than a one-size-fits-all approach, inclusion could be facilitated by creating specialized roles aligned with the project's objectives. For instance, PWDs could be engaged in nursery management, seedling propagation, data collection for community monitoring initiatives, or in leadership and coordination positions within producer groups and forest management committees. Developing these alternative pathways is essential for facilitating genuine and safe inclusion. It ensures that the project's restoration objectives are met without compromising participant wellbeing, while also upholding the principle of leaving no one behind in building community resilience.

| Agreed Actions | Responsibility | Deadline | Status |
| --- | --- | --- | --- |
| Targeting |  |  |  |
| Disaggregated Data Collect disaggregated data for youth and PWD | M&E Officer | Immediate | Agreed |
| Persons with Disabilities Develop pathways and participation opportunities for persons with disabilities- such as nursery management and community monitoring | Social Inclusion Officer/Environment and Climate Officer | March 2026 | Agreed |

Gender and social inclusion

- INLAMAG's gender and social inclusion framework operates in close alignment with the ROOTS Gender Action Plan, implementing targeted approaches that prioritize women (80%), youth (25%), and persons with disabilities (5%). The project's outreach has successfully engaged beneficiaries to date, with women comprising 8, 467 (86%) of these participants, demonstrating a strong commitment to reaching populations most vulnerable to land degradation and climate change impacts.

- ROOTS targets women and youth engaged in rice and vegetable value chains as its main beneficiaries. To fulfill its gender-transformative approach, the project has been using the GALS methodology, rolled out in conjunction with literacy/numeracy training modules in numerous intervention sites. These trainings have been generally well received, with beneficiaries reporting more balance in household relationships and improved women's empowerment. INLAMAG has established a joint implementation platform with ROOTS for delivering the GALS methodology, though current rollout remains concentrated primarily in ROOTS-supported communities, including 25 sites that overlap with INLAMAG's operational areas. A notable success has emerged from the introduction of agroforestry practices in household gardens, particularly through nutrient-rich species like moringa. Women participants reported significant benefits including improved household nutrition and supplemental income generation through both consumption and sale of surplus production.

- To enhance the project's transformative potential, strategic expansion of GALS methodology to INLAMAG-specific communities across all 11 districts would ensure equitable access to empowerment tools, household negotiation frameworks, and participatory planning approaches for all vulnerable groups. Concurrently, strengthening women's institutional engagement through targeted placement on community forestry committees, complemented by specialized training and leadership development programs, will amplify their influence in forest governance structures. These coordinated efforts - combining household-level empowerment with strengthened institutional participation - will foster more accountable, inclusive, and sustainable landscape management outcomes while solidifying community ownership of restoration initiatives.

- This comprehensive approach recognizes that meaningful gender transformation requires both individual capacity building and structural reform, ensuring that women and other vulnerable groups benefit equally from and contribute actively to SLM interventions across INLAMAG's implementation landscape.

| Agreed Actions | Responsibility | Deadline | Status |
| --- | --- | --- | --- |
| Gender and Women Empowerment |  |  |  |
| GALS Extend the GALS to INLAMAG only communities | Social Inclusion officer | Continuous | Agreed |
| Forest Committees Ensure that women are meaningfully represented and trained within community forestry committees with clear sensitization on their roles and leadership | Social Inclusion officer | Continuous | Agreed |

- Social Environment and Climate Assessment Procedures (SECAP)

- The SECAP is operationalised in the ROOTS-INLAMAG. The SECAP related studies are undertaken on a rolling basis in the vegetable gardens and rice fields where the project intervenes. The Environment and Social Management Plans (ESMPs) that are developed are implemented by the communities. SECAP activities are included in the AWPB and the Procurement Plan. SECAP training has been provided for 328 community members in 146 sites. However, awareness and implementation of ESMPs remain limited across communities the mission visited. As more sites are incorporated in the project, the screening criteria should be applied and the necessary risk mitigation measures implemented. A grievance redress mechanism (GRM) has been elaborated for ROOTS, and this is applied to all INLAMAG intervention sites. While local structures (councils of elders, group by-laws, community committees) exist for conflict resolution, there is little understanding of formal GRM procedures or ESMP requirements of the project. The PSU should strengthen sensitization and training on ESMP and GRM implementation for unserved communities and newly targeted communities, integrate environmental compliance into regular monitoring visits, and promote environmentally friendly land preparation practices.

- Communities are increasingly aware of climate change effects, linking agroforestry and reforestation to rainfall improvement and ecosystem balance. Farmers view tree planting as a long-term adaptation measure to improve microclimatic conditions. However, burning during land preparation and incidence of bushfires remains widespread and undermines reforestation gains. Fire management and sensitization need strengthening.

| Agreed Actions | Responsibility | Deadline | Status |
| --- | --- | --- | --- |
| Awareness and implementation of SECAP Provide targeted training on ESMP and GRM procedures for unserved and newly targeted communities. | PSU/NEA | March, 2026 | Agreed |
| SECAP Monitoring Integrate environmental compliance checks into routine monitoring and leveraging local governance structures to support conflict resolution and safeguard adherence. | PSU/NEA | Continuous | Agreed |

Innovation

- Introduction of Nutrition-Rich Crops in Agroforestry Gardens: INALAMAG has introduced nutrient-rich crops such as moringa, lime, and orange within community agroforestry gardens to supplement household nutrition and improve dietary diversity. This innovation not only enhances food security but also promotes climate-resilient farming systems, as these crops, particularly the moringa improve soil fertility, provide shade, and generate additional income opportunities for women and youth engaged in vegetable production.

- Use of Gender-Transformative Tools (GALS) with Climate Change Awareness:
The project applies GALS to promote inclusive participation and empower women in decision-making while integrating climate change awareness into the training process. This innovation ensures that gender equality is mainstreamed alongside climate change adaptation, enabling households and communities to adopt more equitable SLM practices.

- Introduction of Smart Valley and SRI Approaches: The adoption of Smart Valley and SRI techniques, even though yet to commence represents a major shift toward water-efficient, soil-conserving and high-yield rice production systems. These methods enhance productivity while reducing water use and environmental degradation, supporting climate-resilient agriculture across project districts. The innovation aligns with INLAMAG’s goal of promoting sustainable land and water management practices for improved livelihoods and food security.

Partnerships and policy

- Stakeholder engagement under INLAMAG builds on the ROOTS project. The project maintains continuous engagement with DoF, DLS, DoA, DPWM and NEA through joint field missions, technical assessments and planning sessions. The project holds annual consultative forums for national, regional, and community stakeholders to share knowledge, review performance, and plan for the year ahead. Policy dialogue forums address issues affecting project implementation. The AWPB is prepared through a bottom-up participatory process, with regional consultations validating priorities with implementing partners, finalized by the PSU, and submitted to the National Steering Committee for approval before IFAD’s no objection.

- Under INLAMAG, DoF is responsible for rehabilitating degraded landscapes, including 12,000 ha through ANR, 7,500 ha under improved bushfire management, integrating 1,000 ha of woodlots into sustainable energy supply chains, and promoting agroforestry on 5,000 ha. DPWM is tasked with rehabilitating and restoring 4,500 ha of degraded agricultural landscapes through ANR using locally adapted species. The DLS is responsible for implementing all pasture farming activities, including developing 2,000 ha under integrated crop-livestock systems to optimize the use of crop and livestock resources.

Knowledge management and Communication

- Knowledge management and communication in the project have mainly focused on sensitizing the communities and creating awareness and visibility about project interventions. Branding materials have been produced and shared among stakeholders to create awareness about the interventions. Further, the mission observed several signboards that have been erected at various road points and within the community to identify interventions promoted in the project area. The mission appreciates this initiative but notes that it could be done more efficiently, especially in future project districts by consolidating these into a single, and more coherent signboard that presents all interventions collectively.

- The mission noted from field visits that communities have received well some interventions promoted in the project area and that these have had significant impacts on the lives of the beneficiaries. Two such specific interventions include: i) the jambar cooking stoves distributed to vulnerable households. The stoves have reduced firewood use, eased women’s workload, improved fuel efficiency and shortened cooking times; and ii) the use of Moringa as an agroforestry tree within the vegetable gardens accessed by women, especially in Bassick and Yallal Tankonjala communities. The use of moringa has enhanced household nutrition and boosted beneficiaries’ incomes. These and many more success stories should be documented and disseminated to expand the use and deepen the impact of such interventions in other locations in the country.

- The design of INLAMAG included development of an open-access knowledge platform for landscape planning systems to facilitate land-use decision making, targeting, partnerships, research and resource mobilization. This, however, is yet to be prioritized and undertaken.  The mission was however informed that a web-based land cover statistics platform covering the area under community forests, Wildlife Parks and rice fields was developed in collaboration with FAO with ROOTS funding. The operationalisation and webhosting of the platform is delayed due to limited funding to DoF, which is expected to be the host department of the platform. If operationalised, the platform would enable access to some of the key information necessary for land use planning and decision making. Hence the need to prioritise and budget for this activity in the 2026 AWPB.

| Action | Responsibility | Due date | Status |
| --- | --- | --- | --- |
| Document Success stories Document and disseminate success stories on the Jambar cooking stoves and the benefits of Moringa in agroforestry | ROOTS KMO | June 2026 | Agreed |
| Provide budget for Land cover platform Prioritize and budget for the operationalization of the web-based land cover statistics platform, developed under partnership with FAO. | DoF | March 2026 | Agreed |
| Efficient sensitization and awareness creation Consolidate information on project interventions onto one signboard for sites at community level to minimize wastage | ROOTS KMO | Immediate and continuous | Agreed |

Scaling up and sustainability

- The implementation of INLAMAG has demonstrated promising results in rehabilitating degraded landscapes, promoting agroforestry, establishing woodlots, and enhancing community capacity in SLM. Seedling survival, although challenged by bushfires, wrong timing transplanting and seasonal abandonment, shows the potential for climate-resilient agroforestry practices when supported by adequate technical backstopping and community engagement. The awareness of the linkages between tree planting, rainfall improvement and ecosystem balance, provides a strong foundation for scaling up interventions.

- To ensure sustainability, it is critical to institutionalize community-based fire management, strengthen environmental and social safeguards implementation and integrate monitoring and feedback mechanisms into routine project operations. The capacity built among extension workers, women’s associations, and community groups can be leveraged to replicate agroforestry, woodlot development, and pasture management in additional districts. Incentive schemes for high survival rates, continued technical support, and alignment with local governance structures further enhance long-term adoption. Scaling up should also focus on replicating best practices in newly targeted districts, promoting local production of improved seedlings and improved cooking stoves, and linking project interventions to broader national climate change adaptation and SLM strategies to maximize impact beyond the project lifespan.

Lessons learned and implementation issues

- Sourcing and distribution of seedlings – the quality control during the reception of seedlings has been effective and communities appreciated the support that was provided by the Forestry officers. Suppliers should be encouraged to source seedlings within the regions to reduce the transportation times. Sourcing from community nurseries where available should also be encouraged.

- Nurturing of seedlings – in the agro-forestry activities in the gardens the women usually allocate seedlings among themselves and include a fine for seedlings that do not survive. While this seems to provide some incentives early on, there are still neglected seedlings a few months after planting. An incentive can be provided to communities to reward the best performing community in each region with a need that they have expressed for support.

- Planting timing for the pastures – in the fields visited during the mission, earlier planted rangelands where pasture had been transplanted were performing better than the late planted areas where seed was sown. Given the limited material for transplanting, early land preparation and sowing of the pasture lands should be prioritised in 2026. Communities should also be supervised during the planting times to make effective use of resources.

- Institutional support for the Implementing Partners (IPs) – While DPWM and DoF have some earmarked institutional support this is not the case for DLS. Logistical support is provided to all IPs but the mobility challenges continue to hamper the timely implementation of activities including monitoring and follow-up. The planning at regional level needs to be strengthened to overcome some of the challenges. Institutional support will also be considered for DLS in cognisance of the support that will be provided through the Green Climate Fund Africa Integrated Climate Risk Management (AICRM) financing.

- Fencing of woodlots and pastures – Communities continue to request the fencing of woodlots and pastures after planting to protect them from livestock and improve the survival rates. While the rationale behind this is well understood, the project resources are not sufficient to provide fencing for all communities. Alternatives have to be sought such as planting trees that livestock does not prefer and requesting the community to fence the areas using local materials as part of their contribution.

## Implementation arrangements

Project Management and Coordination

- The INLAMAG interventions are coordinated by the ROOTS PSU at the central level and the three Regional Coordination Units in the implementation area. The technical coordination of the activities is led by the Climate Change and Natural Resources Management Officer who works in close collaboration with the focal points from DoF, DLS and DPWM. At the regional level the implementation of the activities is done by the ROOTS Field Assistants, and the technical officers form the IPs. The overall oversight for implementation is provided by the Department of Agriculture (DoA) and the NEA through the ROOTS National Steering Committee.

- The coordination at the central level among the PSU and IPs is effective. The planning and scheduling in each region, however, requires some strengthening among the ROOTS Field Assistants and the DoF, DLS and DPWM Technical Officers. Currently technical officers seem to focus on the activity level and the appreciation of the envisaged objectives that their investments contribute towards and rationale of the activities seem unclear. The IPs provide inputs into the AWPB and the Procurement Plan and are provided with institutional support particularly for the logistics to facilitate implementation of their activities. The planning and information flows at the regional level requires strengthening to ensure the Regional Coordinators are always aware of the activities being undertaken by the IPs in a timely manner. This will promote collaboration and facilitate the monitoring of the activities, so they effectively contribute to the project objectives.

- The INLAMAG activities are incorporated into the ROOTS AWPB. This project management tool needs to be more effectively utilized in the follow-up of the activity implementation and related results in each region and district.

| Agreed Actions | Responsibility | Deadline | Status |
| --- | --- | --- | --- |
| AWPB |  |  |  |
| Review and update the 2026 AWPB to include any missing activities related to expected results but not yet included. | ROOTS M & E Officer | December 2025 | Agreed |

## Monitoring and evaluation

- The foundation of the INLAMAG M&E system is the results framework that contains a set of indicators that enable assessment of progress towards the development objective and goal.

- The project’s M&E system relies on data from ROOTS field assistants and regional officers of key implementing partners (DoF, DLS, DPWM), supervised by Regional Coordinators and consolidated by the PSU M&E Officer. Data collection combines electronic tools (Kobo Toolbox) and manual methods. Community leaders (Alkalos), the village development and forest management committees as well as the community gardens management committees also contribute to field-level monitoring.

- To efficiently manage data collection and day-to-day monitoring of field activities, the ROOTS MIS has been upgraded to integrate INLAMAG and AICRM monitoring. The upgrade is expected to be finalised by December and the system becomes operational.

- Geo-referenced data collection has been undertaken across all 248 project sites. Data analysis is ongoing, and development of maps is expected to be carried out before the end of February 2026.  These maps, in addition to being referenced for land use development activities, will also be a key input in monitoring progress of activities carried out in the project area as well as changes within the landscape attributed to the interventions implemented. Hence the need to fast track the ongoing data analysis.

- Despite progress made under the M&E setup, weaknesses remain. These include the following:

          - Baseline assessments: The mission noted that comprehensive site-specific baseline bio-physical and socio-economic assessments are not systematically carried out prior to carrying out interventions. The lack of such data weakens the basis for attribution and attrition of observed changes within the landscape to the interventions carried out by the project. A retrospective data collection exercise for geo-referenced data was commissioned and has been completed in all 248 project locations where interventions have already been undertaken. Data analysis is ongoing to eventually produce the polygons for the three regions.  Data from the exercise will enable the project to get detailed information on the areas covered and reached with interventions to-date. In addition, the project is encouraged to prioritise such assessments to be carried out prior to and after interventions being carried out. Such assessments would also enable the project implementers to accurately target interventions in areas that would most bring about impact in improved landscape characteristics and on livelihoods of the participating beneficiaries.

          - Data Management: While the project has upgraded the existing MIS to include monitoring of INALAMAG and AICRM activities, the interim data management arrangements in place do not facilitate accurate data quality checks to ensure that consistent information is consolidated at PSU level for reporting to stakeholders. Hence the need to expedite the use of the MIS in addition to strengthening regular data quality checks by the Regional Coordinators and the PSU M&E officer.

          - Weak results focus and misinterpretation of GEF indicators: Implementation of the INLAMAG has experienced challenges in interpretation of expected results and how some interventions are linked to the GEF core indicators that the project is contributing to. As a result, some activities have been implemented, outputs have been delivered and reported against indicators that they are not well aligned to. Clarifications were provided by the mission and going forward, project management will need to ensure that implementation of interventions should be well aligned to the expected results they contribute to.

          - Limited participatory community monitoring: The mission noted strong commitment and enthusiasm among the communities where the project is being implemented. These however have not been formerly engaged in the systematic monitoring of the interventions including collecting some of the monitoring data.  limited community involvement in participatory monitoring. The mission encourages project management to strengthen systematic involvement of communities in monitoring of implementation at their respective levels and including providing them with basic templates for paper-based data collection.

          - Inadequate or poor sequencing of interventions:  The mission noted that some key training activities that would be carried out prior to field interventions are yet to be conducted but planned to be carried out during 2026. Such trainings such as pre-season trainings on timely planting, monitoring of tree survival, good agricultural practices, among others, would help the communities to appreciate their involvement in the project and especially their contribution to the expected results. These requisite trainings should ideally be undertaken before inputs delivery. The consequence of inadequate sequencing of activities and prior trainings is reflected in the quality of results delivered. Hence the need for project management to ensure that there is proper sequencing of activities.

          - The M&E officer in the ROOTS PSU coordinates the M & E activities of INLAMAG with support from the ROOTS Regional Coordinators and Field technical assistants based within the three project regions namely NBR, WCR and LRR. The officer also liaises with staff of IPs on monitoring aspects of implementation led by them.  While this is the ideal situation, the reality is different, as the different officers end up not devoting adequate attention to monitoring of INLAMAG results, thereby compromising their quality.  The mission recommends strengthening regional coordination and monitoring of project interventions by either instituting monthly progress review meetings and other possible means. In addition, the project should prioritise recruitment of a dedicated M&E Assistant to support monitoring and follow-up of INLAMAG activities and improve the quality of results.

| Actions – M&E | Responsibility | Deadline | Status |
| --- | --- | --- | --- |
| Strengthen Result-based M&E Strengthen data analysis and linkage of results to implementation by setting milestone targets and regularly monitoring them to facilitate tracking of progress towards outcomes, GEBs and LDN. | ROOTS M&E Officer | Immediate and Continuous | Agreed |
| Promote participatory and responsive M&E Strengthen involvement of community structures in project monitoring by developing tools to be used at that level. | ROOTS M&E Officer | Immediate and Continuous | Agreed |
| Strengthen Regional Coordination and Monitoring Establish strong coordination mechanisms among the IPs to minimise overlaps in data collected since the project deals with the same communities for various activities under each IP. Prioritise data quality assessments at by Roots Regional Coordinators to minimise gaps and inconsistences in data reported. | ROOTS M&E Officer | Immediate and Continuous | Agreed |
| Efficient and quality data collection Develop and roll out tools to guide field level data collection. Establish monitorable milestones and targets for the interventions implemented by the project as some outcomes will take a long time before they are reached. Ensure the tools are aligned to the milestone targets | ROOTS M & E Officer | March 2026 | Agreed |
| Carry out site specific baseline assessments Prioritise baseline data assessments prior to undertaking implementation of activities in each of the selected project sites to facilitate adequate assessment of progress towards reaching expected outcomes | ROOTS M&E Officer and IPs | Immediate and Continuous | Agreed |
| Recruitment of an M&E Assistant Recruit an M&E Assistant to support M&E implementation | ROOT PSU | March 2026 | Agreed |

## Financial and fiduciary management

- The fiduciary functions of INLAMAG are undertaken by the ROOTS fiduciary team led by a Financial Controller. The team includes two Accountants and a Procurement Assistant. The Procurement Officer is currently being recruited following the resignation of the former officer.

- The current financial execution for INLAMAG based on the 2025 AWPB is 59.47% with USD 605,836 spent out of the budgeted USD 1,018,725. Overall, the financial execution is 17.44% with USD 821,438 spent out of the total budget of USD 4,708,582.

- Extension

- The current completion date for INLAMAG is 31 August 2027. However, given the delayed start of activities an extension of four months is recommended to bring the completion date to 31 December 2027 to align with the request for extension of ROOTS, which at the time of the INLAMAG MTR is being processed.

## Main findings and conclusions

- INLAMAG is on track to achieve its development objective of creating an enabling environment for SLM and LDN in The Gambia. Significant interventions have been implemented despite a delayed start, with most activities showing positive outcomes toward landscape rehabilitation and community engagement.

- The project has so far reached approximately 9,846 direct beneficiaries, which exceeds the INLAMAG target of 9,608 (103% achievement), with 86% women, reflecting strong gender inclusivity. However, full inclusion of persons with disabilities and operationalization of disaggregated data collection remain as a gap.

- A total of 746 ha (99% of the MTR target) has been placed under Integrated Water and Soil Management practices—smart valleys, SRI, and organic compost use—benefiting 176 households across several communities. About 6,034 ha (161% of MTR target) are now under improved bushfire management, with additional areas planned for 2026. Eighteen hectares of woodlots (3.6% of MTR target) have been established or enriched across all 11 project districts, while 4,915 ha (218% of MTR target) of degraded agricultural landscapes have been rehabilitated through ANR, with another 7,000 hectares targeted for restoration. In addition, 1,000 energy-efficient jambar stoves (200% of MTR target) were distributed to vulnerable households, and 964 ha (39% of MTR target) were developed under agroforestry and diversified cropping systems. Finally, 130 ha (13% of MTR target) of land have been placed under integrated crop-livestock systems through the reseeding of rangelands with improved and indigenous pasture species.

- Communities are actively engaged in forest protection, agroforestry, rangeland management and energy-saving interventions, fostering local ownership of restoration outcomes. Technical support for extension officers and community groups remains critical.

- While bushfire management has improved through the project efforts, the effectiveness of community fire management committees remains limited. Provision of firefighting equipment has reduced labour needs, but additional capacity-building is required.

- The implementation of woodlot establishment faces constraints due to insufficient budget allocation in the project document and requires prioritizing resilient species and institutional/fenced sites.

- Agroforestry awareness is high; notwithstanding, seedling mortality is a challenge due to bushfires, termites and seasonal abandonment of project gardens. Continued technical support is essential for improved survival rates.

- The distributed Jambar stoves have improved energy efficiency, reduced smoke exposure and eased workloads for women.

- Participatory monitoring, data quality, results linkage and baseline assessments currently have weaknesses. Integrating community monitoring and setting milestone targets is needed.

- SECAP training has been conducted but awareness and implementation of ESMPs and the GRM are limited. Environmental compliance requires reinforcement.

- Sustainability depends on institutionalizing fire management, promoting local seedling and stove production, integrating monitoring, and strengthening technical backstopping. Scaling up should leverage community capacity, incentive schemes and link interventions to national SLM, LDN and climate change adaptation strategies.

- Coordination among the PSU and regional units is generally effective, though planning at regional levels requires strengthening. Timely information flow is essential for regional planning and coordination and facilitates the monitoring of the activities, so they effectively contribute to the project objectives. Performance of IPs requires improvement.

- Key mission agreements

- Assisted Natural Regeneration: Given the positive results achieved, it is recommended that the ANR target is increased by at least 2,000 ha to sustain progress, extend fire management to unserved districts and strengthen the functionality and capacity of community fire management committees.

- Community-led tree planting: To accelerate implementation toward meeting the remaining project target, the mission agreed to cover approximately 8,000 ha across priority sites, in NBR (3,860 ha in 8 parks), LRR (1,677 ha in 3 parks), and WCR (1,683 ha in 2 parks).

- Woodlot Establishment: With the exhaustion of fenced NEMA project sites, it is recommended that the project adopt tree species less prone to livestock browsing and revise the woodlot target from 1,000 ha to 500 ha for realistic implementation within the available budget. The revised approach should prioritize communities with at least 10 ha of land and extend support to institutions with a minimum of 3 ha suitable for woodlot development.

- Community Agroforestry and Diversified cropping systems: To improve survival and scaling of agroforestry practices, additional training will be required, while technical backstopping needs to be strengthened. Given constraints of available intervention areas within the original 11 districts, the target area is proposed to be reduced to 3,000 ha (from 5,000ha) and implementation extended to additional districts in LRR (5), NBR (2), and WCR (4), including schools and mixed farming centers. Live fencing and buffer-zone planting around rice fields will continue, while incentives can be offered to groups achieving the highest survival rates. In subsequent planting cycles, the department should ensure planting during the optimal period for establishment before the dry season and conduct post-dry-season surveys to assess survival rates of trees planted in buffer zones.

- Women representation in Forest Committees: Ensure that women are meaningfully represented and trained within community forestry committees with clear sensitization on their roles and leadership.

- Rangeland establishment and management: To achieve the project targets (2,000ha), the mission agreed to target 100 communities across the three regions in 2026 and 2027, each with an estimated 20 hectares available for intervention. Technical backstopping on pasture establishment and management will be prioritized during the remaining implementation period to ensure sustainability and productivity gains.

- Jambar Cooking Stoves Distribution to Households: Technical support for local production of improved stoves is recommended to enhance sustainability, accessibility and affordability. The success stories from the use of the jambar stoves should be documented and disseminated to expand the use and deepen the impact of such interventions in other locations in the country.

- Targeting: While ROOTS systematically collects gender and disability-disaggregated data, INLAMAG has not yet fully operationalized this practice. Adopting disaggregated data collection will strengthen monitoring and ensure more inclusive targeting.

- Gender and social inclusion: To deepen gender-transformative impact, extend GALS to INLAMAG-only communities, ensuring that all women and vulnerable groups across the targeted districts have equal access to planning, empowerment and negotiation tools.

- Targeting Persons with Disabilities: The project should develop pathways and participation opportunities for persons with disabilities - such as nursery management and community monitoring.

- Strengthen Results-based M&E: The project should strengthen data analysis and linkage of results to implementation. Milestone targets should be set and regularly monitored to facilitate tracking of progress towards outcomes.

- Promote participatory and responsive M&E: The project should strengthen involvement of community structures in project monitoring by empowering them and developing tools to be used at that level. The project should further establish strong coordination mechanisms among the IPs to minimise overlaps in data collection.

- Carry out site specific baseline assessments: The project should prioritise baseline data assessments prior to undertaking implementation of activities in each of the selected project sites to facilitate adequate assessment of progress towards reaching expected outcomes.

- M&E capacities: The project should recruit a dedicated Monitoring and Evaluation Assistant in charge of monitoring and follow up of INLAMAG activities.

- Extension: A four-month extension to December 2027 is recommended to align with ROOTS completion and recover delayed implementation time resulting from the delayed start-up.

## Annexes/Appendices

Annex 1:	Project logframe updated by MTR (Also see separate Excel file)

Annex 2:	AWPB 2024 - 2025 physical progress report

| Code | Description | Unit of Measure | FY 2025 AWPB (As At 02.12.2025) |  |  | Cumulative |  |  | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Component/Output/ Activities/Inputs |  | AWPB Target | Actual | % Achieved | Appraisal Target | Actual | % Appraisal Achieved |  |
| Component 1: Enabling environment for SLM and LDN mainstreaming and implementation (LD2.5) |  |  |  |  |  |  |  |  |  |
| Outcome 1: 1.1 Enhanced institutional capacities across sectors and governance and coordination mechanisms for SLM and LDN mainstreaming in place |  |  |  |  |  |  |  |  |  |
| Output 1.1.1: | One (1) Institutional Capacity Development Plan and program, including at least 4 training programs (participatory land-use planning, collaborative decision making, multistakeholder approaches, SLM, LDN) for 4,200 beneficiaries; 10 Farmers Field School (FFS), one vocational education center (Songhai Centre) (with at least 50% of participants being women) |  |  |  |  |  |  |  |  |
| Output Indicator 1.1.1: | Institutional Capacity Development Plan developed and operationalised | Number | 1 | 0 | 0.0% | 1 | 0 | 0.0% | CDP draft plan currently under review |
| Activities |  |  |  |  |  |  |  |  |  |
| Activity 1.1.1.1 | Engage consultant to develop the Capacity Development Plan | Number | 1 | 1 | 100% |  |  |  | Consultant engaged in second quarter (April -June) |
| Activity 1.1.1.2 | Draft CDP | Number | 1 | 1 | 100% |  |  |  | Draft CDP developed and submitted by the consultant to the PSU in September 2025. Draft currently under review |
| Activity 1.1.1.3 | Organise workshop for validation of the capacity development Plan through a workshop | Workshop report | 1 | 0 | 0% |  |  |  | Workshop is planned for December 2025 |
| Activity 1.1.1.4 | Produce and Print CDP | Plan | 1 | 0 | 0% |  |  |  | Plan will be printed upon validation and finalisation |
| Activity 1.1.1.5 | Carried out Gap assessment for additional infrastructure at Gambia SONGHAI Center | Assessment report | 1 | 1 | 100% |  |  |  | Assessment done, report finalised and BOQ estimates made in preparation for construction (this activity is directly funded from the ROOTS budget. |
| Activity 1.1.1.6 | Recruit private contractor for the development of additional infrastructures at Gambia SONGHAI center | Contract | 1 | 1 | 100% |  |  |  | Contractor engaged -BALA construction and Engineering Company. Site handover done in November 2025 |
| Activity 1.1.1.7 | Establish FFS | Number | 4 | 4 | 100% |  |  |  | Four ROOTS demo FFS gardens (Berefet & Bintang in WCR; Manduar in LRR; Yalal Tnkonjala in NBR). Demo activities include composting and GAPs demo plots. 116 (107 females & 7 Males) are participating FFS |
| Output 1.1.2: | One (1) open-access knowledge platform for landscape planning system developed for land-use decision making, targeting, partnerships, research and resource mobilization |  |  |  |  |  |  |  |  |
| Output Indicator 1.1.2: | Open-access knowledge platform |  |  |  | 0% | 1 | 0 | 0.0% | A web-based land cover statistics platform covering the area under community forests, Wildlife Parks and rice fields was developed in collaboration with FAO with ROOTS funding. The operationalisation and web-hosting of the platform is delayed due to limited funding to Department of Forestry. The budget for this activity will be prioritised in 2026 AWPB |
| Output 1.1.3 | 1.1.3 One (1) land use management plan is developed in cooperation with relevant national and international partners, leading to its effective implementation in support of SLM and LDN |  |  |  |  |  |  |  |  |
| Output Indicator 1.1.3.1: | Land use Management plan Developed | Number |  |  |  | 1 | 0 | 00% | This activity will be initiated in 2026 |
|  | Activities |  |  |  |  |  |  |  |  |
| Activity 1.1.3.1.1 | Carry out mapping of interventions implemented in the project | Number of interventions mapped | 248 | 248 | 100% |  |  |  | Collection of georeferenced data is completed in all 248 sites. Data analysis is ongoing |
| Activity 1.1.3.1.2 | Develop maps/polygons for the interventions | Maps | 248 | 0 | 0% |  |  |  | Development of the map awaits the completion of the data analysis exercise that is currently ongoing |
| Activity 1.1.3.1.3 | Develop Regional Land use management Plans | Plans | 3 | 0 | 0% |  |  |  | Plans await the finalisation of the mapping exercise |
| Component 2: Implementation of Integrated landscape planning and management to reduce land degradation (LD1.4) |  |  |  |  |  |  |  |  |  |
| Outcome 2.1 Improved, coordinated and collaborative management of Landscape (12,000 ha of degraded productive landscapes in 11 districts, contributing 11% to 109 000 ha LDN national target while bringing 14,500 ha under improved management enhancing their ecological integrity and ensuring better agricultural production and livelihoods. |  |  |  |  |  |  |  |  |  |
| Output 2.1.1.1: | Five (5) Integrated Water and Soil Management practices are promoted by 700 households through dikes, and Conservation Agriculture, including the promotion of system of rice intensification (1,500 ha) |  |  |  |  |  |  |  |  |
| Output Indicator 2.1.1.1 | Integrated Water and Soil Management practices promoted | Practices | 5 | 3 | 60% | 5 | 3 | 60% | Three practices are currently being practiced i.e smart valley, SRI and composting. |
| Output Indicator 2.1.1.2 | Area under Integrated Water and Soil Management practices | Ha | 750 | 746 | 99.5% | 1,500 | 746 | 49.7% | Yalal 5ha , Bintang 5Ha , Berefet 5ha , manduar 5ha, 730 under rice |
| Output Indicator 2.1.1.3 | Number of Households participating in the promotion of integrated soil and water management practices | Households | 200 | 176 | 88% | 700 | 176 | 25% | Community of Suwareh Kunda benefitted from both SRI and smart valley within the INLAMAG project area |
|  | Activities for 2025 |  |  |  |  |  |  |  |  |
| Activity 2.1.1.1.1 | Engaged International Technical Assistance to support the development Smart valley in rice fields | Consultancy | 1 | 1 | 100% |  |  |  | ROOTS partnered with AfriRice to develop smart valleys. |
| Activity 2.1.1.1.2 | Develop Smart valleys for rice production in selected locations. | Ha | 1 | 1 | 100% |  |  |  | Three communities namely: Badumeh Koto in LRR, Suwareh Kunda in NBR and Farabanta in WCR. 60 beneficiaries from Suwareh Kunda (1ha) within the INLAMAG project area benefitted from this intervention. |
| Activity 2.1.1.1.3 | Construct Compost Chambers in selected community gardens | Number of compost chambers | 4 | 4 | 100% |  |  |  | Four chambers were constructed benefitting 666 beneficiaries (M 30, F636, Y 279 and PwD 3) in INLAMAG project area. |
| Activity 2.1.1.1.4 | Conduct training on agrochemical handling and application to rice SRI intervention communities | People trained | 48 | 48 | 100% |  |  |  | The training was given to two representatives selected from 24 SRI FFS in INLAMAG project area. FFS representatives are expected to cascade the training to fellow farmers. |
| Activity 2.1.1.1.5 | Provide assorted production inputs to support SRI interventions in selected rice fields. | SRI fields | 24 | 24 | 100% |  |  |  | Assorted inputs were distributed to 24 rice fields within the INLAMAG project area under SRI initiatives covering 730ha, benefiting 1,555 farmers ( M 209 , F1349, Y 59 ,PwD 0) |
| Output 2.1.2 | 12,000 ha of degraded agricultural production landscapes are rehabilitated and restored through assisted natural regeneration focusing on locally adapted species and- Improved bushfire management (7,500 ha); woodlots using multipurpose tree species, agro- silvopastoral multipurpose tree species, agro-silvo-pastoral practices (4,500 ha) for LDN implementation |  |  |  |  |  |  |  |  |
| Output Indicator 2.1.2.1 | Area of Degraded Agriculture production landscape rehabilitated and restored through ANR, and bush fire management | Ha | 7,500 | 0 | 0% | 7,500 | 6,034 | 80.4% | The project distributed assorted firefighting tools and equipment to 61 communities for the management of community forest bush fires in 2024. |
| Output Indicator 2.1.2.2 | Area under Agro-silvopastoral practices | ha | 4500 | 4915 | 109% | 4500 | 4915 | 109% | Establishment of fodder trees is planned to be undertaken during 2026. However, during FY 2025, enrichment planting was prioritised with selected parks and wildlife areas surrounding agricultural lands |
| Activities for 2025 |  |  |  |  |  |  |  |  |  |
| Activity 2.1.2.1.1 | Carry out sensitisation and awareness campaigns on environmental sustainability and ecosystem conservation to potential communities | Number of communities | 50 | 0 | 0% |  |  |  |  |
| Activity 2.1.2.1.2 | Identify and select community forest management committees | Number of committees | 50 | 0 | 0% |  |  |  |  |
| Activity 2.1.2.1.3 | Provide assorted fire management tools and equipment to selected communities | Number of communities | 50 | 0 | 0% |  |  |  |  |
| Activity 2.1.2.2.1 | Sensitize communities on sustainable use of the rangelands | Number of communities | 50 | 0 | 0% |  |  |  |  |
| Activity 2.1.2.2.2 | Identify and select communities to be support with fodder tree seedlings for ANR in rangelands | Number of communities | 50 | 0 | 0% |  |  |  |  |
| Activity 2.1.2.2.3 | Provide assorted fodder tree seedlings for over-sowing of the rangelands | Ha | 1500 | 0 | 0% |  |  |  |  |
| Activity 2.1.2.2.4 | Facilitate enrichment planting in selected wildlife parks | Ha | 4500 | 4915 | 109% |  |  |  |  |
| Output 2.1.3: | 1,000 ha of woodlots are integrated into the sustainable wood and biomass energy supply chain leading to improved community forestry and indigenous community conservation management |  |  |  |  |  |  |  |  |
| Output Indicator 2.1.3 | Area established under woodlots | Ha | 18 | 18 | 100% | 1000 | 18 | 1.8% | The budget was not adequate to cover establishment of new woodlots. So the intervention was then focused on enriching existing fenced woodlots established under the erstwhile NEMA-Chosso project |
| Activities for 2025 |  |  |  |  |  |  |  |  |  |
| Activity 2.1.3.1 | Identify and select communities to benefit from woodlots establishment in line with established criteria | Number of committees | 5 | 5 | 100% |  |  |  | Selection was targeted at existing NEMA-Chosso project sites to ensure the woodlots are well protected |
| Activity 2.1.3.2 | Establish community woodlots for selected communities | Ha | 18 | 18 | 100% |  |  |  | 18 ha of woodlots with 1800 seedlings of Gmelina and 1,900 seedlings of Eucalyptus in five communities |
| Output 2.1.4: | Community monitoring system for soil erosion and vegetation cover is established using the 3 project-level indicators (land cover change, land productivity and SOC) and inform the open-access knowledge platform: |  |  |  |  |  |  |  |  |
| Output Indicator 2.1.4 | Community Monitoring System | System |  |  |  | 1 | 0 | 0% | The community monitoring system is yet to be established |
| Component 3: Promotion of SLM for Climate- Smart Agriculture for improved agricultural, rangeland and Pastoral management (LD1.1) |  |  |  |  |  |  |  |  |  |
| Outcome 3.1 | 3.1 Improved agricultural, rangeland and pastoral management practices |  |  |  |  |  |  |  |  |
| Output 3.1.1 | 5,000 ha of land under agroforestry and sustainable and diversified cropping systems. |  |  |  |  |  |  |  |  |
| Output Indicator 3.1.1 | Land under Agroforestry and sustainable and diversified cropping systems | Ha | 713 | 730 | 102.3% | 5000 | 964 | 14.6% | Agroforestry initiatives undertaken across 63 community gardens in 2024 and 25 rice fields n 2025 |
|  | Activities |  |  |  |  |  |  |  |  |
| Activity 3.1.1.1 | Carry out sensitisation and awareness campaigns on integration of agroforestry in farming activities | Number of campaigns | 4 | 4 | 100% |  |  |  | Campaigns done on a quarterly basis |
| Activity 3.1.1.2 | Identify and select communities to benefit from the agroforestry interventions | Number of communities | 25 | 25 | 100% |  |  |  |  |
| Activity 3.1.1.3 | Provide assorted seedlings to the selected communities to establish the agroforestry | Number of seedlings | 41000 | 41000 | 100% |  |  |  | Seedlings were distributed for the establishment of 730 Ha of agroforestry in rice gardens |
| Output 3.1.2. | 2,000 ha of land under Integrated Crop-Livestock Systems to optimize the uses of crop and livestock resources |  |  |  |  |  |  |  |  |
| Output indicator 3.1.2 | Land under integrated Crop-Livestock Systems | Ha | 600 | 130 | 21.7% | 2000 | 130 | 6.5% | Procurement of the seeds was delayed delaying the establishment of the area. |
|  | Activities |  |  |  |  |  |  |  |  |
| Activity 3.1.2.1 | Carry out sensitisation and community engagement activities | Number of sensitization campaigns | 3 | 3 | 100% |  |  |  | The campaigns were planned for each of the regions |
| Activity 3.1.2.2 | Facilitate signing of commitment letters for the securing of land for the development of the pastures and sustainable management of the rangelands | Number of Letters | 30 | 30 | 100% |  |  |  | Commitment letters were signed for each of 30 communities |
| Activity 3.1.2.3 | Over-sow rangelands with pastures | Ha | 600 | 130 | 21.7% |  |  |  | The area under rangelands was established for 20 out of 30 communities. Other communities delayed preparing their respective areas as committed |
| Output 3.1.3. | Participatory SLM plan developed on 15,000 ha (mixing different techniques such as soil bunds, stone lines, etc. to reduce water runoff and soil erosion in productive agricultural land, including watershed management. |  |  |  |  |  |  |  |  |
| Output indicator 3.1.3 | Area developed rehabilitation through participatory soil, land and water shed management activities | Ha | 388 | 0 | 0% | 15000 | 0 | 0% | The contract for development of Wet-Season Valley Water Control Cascaded Dykes and Micro-Catchments Runoffs Control Dykes was signed in April 2025 but due to limited funding, and the ongoing production season the activities have delayed to start. |
|  | Activities for 2025 |  |  |  |  |  |  |  |  |
| Activity 3.1.3.1 | Recruit contractor for the construction of the Wet-Season Valley Water Control Cascaded Dykes | Contract | 1 | 1 | 100% |  |  |  | Contractor identified and site handed over April 2025 |
| Activity 3.1.3.2 | Carry out civil works on the Wet-Season Valley Water Control Cascaded Dykes | Ha | 45 | 0 | 0% |  |  |  | Contractor mobilised, but works are yet to commence because the production season was still on. Works will start at the end of the productions season. |
| Activity 3.1.3.3 | Recruit contractor for the construction of the Micro-Catchments Runoffs Control Dykes | Contract | 1 | 1 | 100% |  |  |  | Contractor identified and is the same for construction of the wet season valley water control dykes |
| Activity 3.1.3.4 | Carry out civil works on the Micro-Catchments Runoffs Control Dykes | Ha | 343 | 0 | 0% |  |  |  | Civil works will be carried out at the ed of the production season |
| Output 3.1.4 | 1,000 Jambar cooking stoves distributed to 1,000 households to reduce the use of charcoal and fuelwoods which contribute to soil erosion and general land degradation, with 80% beneficiaries being women |  |  |  |  |  |  |  |  |
| Output indicator 3.1.4 | Cooking stoves distributed to households | Number of stoves |  |  |  | 1000 | 1000 | 100% | The stoves were distributed I 2024 to only vulnerable female beneficiaries |
| Output 3.1.5. | Communities (7), 50 women associations and technical services,150 extension services workers in 11 districts capacity is enhanced on SLM for climate resilient and low emission agriculture leading to improved agricultural, agroforestry and livestock production: |  |  |  |  |  |  |  |  |
| Output Indicator 3.1.5.1 | Associations capacity built | Number of associations | 25 | 3 | 12% | 50 | 3 | 6% | Manduar, Bintang, and Berefet community associations have been supported within the INLAMAG region |
| Output Indicator 3.1.5.2 | Extension services workers capacity built | Number of extension workers |  |  |  | 150 | 0 | 0% | No activities have been planned in 2025. |
| Component 4: | Monitoring the Project’s Contribution to LDN |  |  |  |  |  |  |  |  |
| Outcome 4.1 | Enhanced monitoring and evaluation of land cover changes, land productivity and soil organic carbon carried out in line with project-level indicators in contribution to national LDN agenda |  |  |  |  |  |  |  |  |
| Output 4.1.1 1 | (One) monitoring plan established and agreed upon by key stakeholders, including an interpretation modality for the changes in land cover (positive, negative, stable) are established and agreed upon. |  |  |  |  |  |  |  |  |
| Output Indicator 4.1.1.1 | Monitoring Plan Established | Plan |  |  |  | 1 | 0 | 0% | The Monitoring Plan is yet to be developed. Activities to bring together stakeholders to agree on monitorable indicators is planned for 2026 |
| Output 4.1.2 1 | (One) LDN information hub operationalized as a mechanism for sharing and verification of monitoring data, including the dissemination of lessons learned to target audience: |  |  |  |  |  |  |  |  |
| Output Indicator 4.1.2.1 | LDN Information Hub established and operational | Hub |  |  |  | 1 | 0 | 0% | LDN hub not yet established pending clarification of agency to lead the exercise |

Annex 3: 	INLAMAG GEF7 core indicators updated by MTR

| - Core Indicator | Ha (Expected at PIF) | Ha (Expected at CEO Endorsement) | Ha (Achieved at MTR) | Ha (Proposed end Targets at MTR) |
| --- | --- | --- | --- | --- |
| Total Area | 32,000 | 48,500 | 12,807 | 48,500 |
| Indicator 3 Area of land restored | 10000 | 12000 | 10,949 | 26,500 |
| Indicator 3.1 Area of degraded agricultural land restored | 10000 | 12000 | 10,949 | 26,500 |
| Indicator 4 Area of landscapes under improved practices (hectares; excluding protected areas) | 22000 | 36500 | 1858 | 22,000 |
| Indicator 4.3 Area of landscapes under sustainable land management in production systems | 22000 | 36500 | 1858 | 22,000 |
| Indicator 6 Greenhouse Gas Emissions Mitigated | 0 | 2936362 | NA |  |
| Expected metric tons of CO2e (direct) | 0 | 2936362 | NA | 10% of Gambia National Target |
| Indicator 11 Number of direct beneficiaries disaggregated by gender as co-benefit of GEF investment | 15200 | 9608 | 9846 | 15200 |
| Female | 9041 | 5715 | 8468 | 9041 |
| Male | 6159 | 3893 | 1378 | 6159 |

Annex 4:	Mission terms of Reference, field schedule and list of key persons met

Background, Mission Objectives, Team Composition and Terms of Reference

Basic Project Data

| Executing agency | Ministry of Agriculture |
| --- | --- |
| Donor (s) | IFAD, GOTG, GEF grant, AFD grant, GCF, (AICRM) grant |
| Project ID | 2000001065 |
| Total Project Cost (USD) | US$ 80 million |
| Gambia Government Contribution (USD) | US$ 5.41 million |
| Beneficiaries’ contribution | US$ 6.25 million |
| Date of Approval | 11th December 2019 |
| Date of Financing Agreement Signature | 27th December 2019 |
| Date of Loan Effectiveness | 16th January 2020 for disbursement of FIPS 1st March 2020 Entry into Force |
| Actual date of first disbursement | 21st December 2020 |
| 1st Additional financing | US$ 11,93 million Approved in Sept. 2023 |
| 2nd Additional financing | US$ 18.91 million Approved in Dec. 2024 |
| Project Implementation period | Initial Completion date: 31st March 2026 Proposed completion date: 31st March 2027 |
| Project Outreach Target | 40,000 households |

GEF

| Executing agency | Ministry of Agriculture |
| --- | --- |
| Donor (s) | GEF grant |
| Project ID (GEF ID Number) | 10572 |
| Total Project Cost (USD) | 4,708,582.00 |
| Date of Loan Effectiveness | 9th January 2022 |
| Actual date of first disbursement | 4th October 2023 |
| Project Implementation period | Proposed completion date: 31 August 2027 |

Mission Composition

| Name | Specialization |
| --- | --- |
| Ms. Ann Turinayo | Country Director and Mission leader |
| Ms Paxina Chileshe | Lead Regional Climate and Environment Specialist and Technical Lead |
| Dr. Edmund Kyei Akoto-Danso | Environment and Climate Expert |
| Ms Grace Nakanjakko | M&E and Knowledge management expert |
| Ms Couro Kane | Social inclusion and targeting expert |
| Mr. Marone Mbaye | Support Officer and M&E expert |

ROOTS

The Resilience of Organizations for Transformation of Smallholder Agriculture Project (ROOTS) was approved by the IFAD Board on 11 December 2019, entered into force on 01 March 2020; the project is expected to be completed by March 2026. IFAD and The Government of The Gambia (GoTG) launched officially the ROOTS project in February 2021.

The total project cost is US$ 80 million for the benefit of The Gambia, mainly the rural farmers women and youth. ROOTS is co-financed by IFAD, GEF, AFD, GCF, the GoTG and the beneficiary farmers.

The country is one of the most vulnerable countries to climate change because of its geographical location, characterized by high dependence on rain-fed agriculture and severe salt-water intrusion in the lowland’s floodplain. The goal of ROOTS is to improve food security, nutrition and resilience of smallholder farmers to climate change in The Gambia. The Project Development Objective (PDO) is to increase agricultural productivity and access to markets for enhanced food security and nutrition, and increased resilience of family farms and farmers’ organizations. ROOTS project will support the building and scaling up of the resilience and adaptive capacity of farmers’ organizations (FOs), including youth and women’s organizations, cooperatives and small and medium-sized enterprises (SMEs), along with agricultural and water resource management practices, water infrastructure (micro-catchments, run-off control dykes and causeways) and irrigation systems using renewable energy.

The target group of ROOTS is mainly smallholder farmers, micro-entrepreneurs, poor rural youth and women. The direct beneficiaries of the project are 40,000 households or about 320,000 people (i.e. approximately 10 per cent of the country’s total population); 80 per cent of the direct beneficiaries are women and 25 per cent are youth and persons with disabilities, due to targeted rice and vegetable value chains ROOTS is implemented in five regions of The Gambia: Central River Region (CRR), North Bank Region (NBR), Lower River Region (LRR), Upper River Region (UPR) and West Coast Region (WCR). The project’s interventions will cover 39 districts across these five regions.

ROOTS activities are organized in three components:

Component 1. Agricultural productivity and adaptation to climate change: - This component aims to build the resilience of FOs to climate change through enhanced and sustainable access to natural resources and agricultural services. The objective of this component is pursued through 2 sub-components: (i) infrastructure development and management for rice and horticulture; and (ii) agricultural services provision.

The expected outcome is “Improved smallholder farmers' productivity through the adoption of sustainable and climate-resilient and nutrition-sensitive technologies and practices”. Under sub-component 1.1, the Project will: (i) consolidate 1,300ha of existing poorly performing tidal irrigation and develop 2,800ha of new tidal irrigation on existing agricultural lands (average size per community land between 25 and 75ha); (ii) develop 200ha new wet-season valley water control cascaded dykes; (iii) develop 800ha new micro- catchments runoff control dykes; (iv) establish and strengthen Water User Management Units; and (v) upgrade 20km of causeways to access 800ha rice-growing swampy areas. In addition, the Project will upgrade 40 vegetable gardens and develop 30 new ones. Around the production sites, ecosystem preservation activities such as the rehabilitation of 1,300ha of mangroves and 1,400ha of community forests will be financed. Sub- component 1.2 will support (i) the access to various agricultural services (extension, input provision, financial education) with the focus on the promotion of Farmers’ Field Schools for rice and vegetables; (ii) the emergence of 240 youth-led businesses that will mainly focus on the provision of services to the value chains; and (iii) capacity development of grassroots farmers’ organizations (FOs) so that they develop services for their members

Component 2. Access to markets comprises two sub-components focusing on value chain and market linkages (2.1) and support business ideas of the 4Ps (public-private producer partnerships). The outcome of this component is “inclusive commercial partnerships between strengthened FOs and buyers through public-private producers’ partnerships”. Sub-component 2.1 will focus on value chain and market linkages. It will finance: (i) agricultural value-chain interaction platforms (AVIPs) -- one rice AVIP and one vegetable AVIP will be established in each region targeted by the project with key value- chain stakeholders (producers, processors, traders, transporters) and the voice-based market information system introduced by NEMA will be scaled-up; (ii) capacity development of the National Coordinating Organization for Farmer Association in The Gambia (NACOFAG) as well as the national commodity organizations of food processors, rice and vegetable growers; and (iii) the construction of markets and roads. Sub- component 2.2 will support business ideas of 4Ps, particularly those focused on post- harvest and value-addition elements. The Project will ensure that:(i) FOs and SMEs prepare high-quality business plans; and (ii) matching grant resources are efficiently mobilized and utilized. As a pilot, and after the mid-term review, matching grant funds will be blended with potential private capital from the Gambian diaspora; and (iii) post- investment business support is available to sustain the 4Ps, through linking the SMEs to specialized business development services, including certification and food safety standards.

Component 3. Project management, institutional development, and citizen engagement. The objective is to facilitate: (i) efficient coordination and monitoring and evaluation of project activities; (ii) knowledge management, communication, and learning;

(iii) stakeholder awareness and participation through timely and transparent communication of results and consistent citizen engagement; and (iv) policy dialogue and South-South and Triangular Cooperation.

ROOTS has had four supervision missions, eight follow-up and Implementation Support Missions, and a Mid Term Review mission in April 2024.

The ROOTS Project rural development initiative is co-financed by GEF’s Least Developed Countries Fund (LDCF) through the Integrated Landscape Management Gambia (INLAMAG) Project and GCF through the Agricultural Irrigation and Climate Resilience Mechanism (AICRM), alongside IFAD, AFD, OFID, national government, and beneficiaries.

INALAMAG

The INLAMAG project, funded by the Global Environment Facility (GEF) under its seventh replenishment cycle, forms a key component of the ROOTS initiative. Intervention of this project focuses on 11 districts across three agricultural regions: the West Coast Region (5 districts), North Bank Region (5 districts), and Lower River Region (1 district). Like ROOTS, the project aims to benefit predominantly female beneficiaries, with 80 percent of direct beneficiaries expected to be women, along with 25 percent youth and 10 percent individuals with disabilities. It operates across the following components:

Component 1. Enabling environment for SLM and LDN mainstreaming and implementation. Activities include the development of an Institutional Capacity Development Plan and Program; an open-access knowledge platform for landscape planning systems and a land use management plan.

Component 2. Implementation of integrated landscape planning and management to reduce land degradation and achieve LDN target. Under Component 2 of the GEF co-financing, five (5) Integrated Water and Soil Management practices are targeted to be promoted; 12,000ha of degraded agricultural production landscapes are to be rehabilitated and restored through ANR. It is also expected that 1,000ha of woodlots are integrated into the sustainable wood and biomass energy supply chain leading to improved community forestry and indigenous community conservation management.

Component 3. Promote SLM for Climate-Resilient and low emission agriculture for improved agricultural, rangeland and pastoral management. Under Component 3, the project will promote Sustainable Land Management (SLM) practices that support climate-smart agriculture, improved rangeland and pastoral systems. These interventions aim to enhance agricultural productivity and ecosystem health while addressing the socio- economic needs of vulnerable populations. By restoring degraded land and optimizing resource use, the project will contribute to improved livelihoods and resilience in communities most affected by climate change and land degradation.

Component 4. Monitoring the Project Contribution to LDN. Focuses on monitoring and verifying the project’s contribution to the country’s Land Degradation Neutrality (LDN) targets to assess the level of achievement. One monitoring Plan is expected to be established and agreed upon by key stakeholders. Similarly, one information hub is expected to be operationalized as a mechanism for sharing and verification of monitoring data, including the dissemination of lessons learned to target audience.

The INLAMAG Project experienced delays in the receipt of GEF funding, which in turn led to setbacks in the timely implementation of planned activities. These funding delays affected the scheduling of key project components, including capacity building, land-use planning, and field-level Sustainable Land Management (SLM) interventions.

Objectives of the MTR mission:

The primary objective of the Mid-Term Review (MTR) is to assess the Project’s overall performance over the past three years in relation to its expected goals and development objectives, identify challenges faced by the Project Support Unit (PSU), and recommend practical solutions.

The MTR will: (i) review ROOTS INAMLAG project’s overall progress in physical and financial implementation; ii) review the progress of the implementation of recommendations from the earlier missions; iii) review the progress on the 2025 AWPB as well as the current disbursements; iv) assess ROOTS INAMLAG approach and strategy;

(v) assess the level of project implementation against outputs and outcomes MTR targets;

(vi) refocus priorities, if necessary, to better achieve project’s objectives, to enhance and sustain outcomes and impacts; (vii) re-examine the basic assumptions and the risk factors identified during the design of the Project, and if necessary, make the necessary readjustments; (viii) assess the various achievements in terms of relevance, effectiveness, efficiency and sustainability; (ix) highlight the constraints and lessons learned to lead to recommendations likely to better guarantee the achievement of the expected results at the end of the project.

While review and assessment will be an important part of the MTR, a forward-looking approach will be adopted based on the key lessons learned from the implementation to date. The MTR will also provide implementation support and guidance to the PMU and partner agencies as appropriate.

The MTR mission team will have seven working days and a weekend in the country. A kickoff meeting will be organized at the central level before departing for field visits. Working sessions will be organized with the PMU, before and after the field visit to discuss progress of implementation as per the AWPB, review the results as reflected in the M&E system, discuss challenges and opportunities for improvement, and review the draft work plan and budget for 2026 as will have already been prepared by the project team. A technical pre-wrap-up meeting shall be held with the PMU to discuss the findings, conclusions and recommendations of the mission, and an aide memoire will be prepared for signature with the government authorities. The draft MTR report will also be discussed with the project team.

Mission Composition and responsibilities

The mission team is composed of (i) Country Director and mission leader, Ms. Ann Turinayo; (ii) Lead Regional Climate and Environment Specialist and Technical Lead, Ms Paxina Chileshe; (iii) Environment and Climate Change Specialist, Dr. Edmund Kyei Akoto-Danso; (iv) M&E and Knowledge management experts, Ms Grace Nakanjakko; (v) Mr Marone Mbaye, Support Officer; and (vii) Social inclusion and targeting expert, Ms Couro Wane.

Ms Ann Turinayo, Country Director and mission leader,

As Mission Leader, she will facilitate the mission and ensure overall coordination and quality control of deliverables. She will lead the COSOP Annual Review meeting and the kick-off meeting and debriefings with the mission and will take part in meetings with the government and partners. She will review the project management aspects and provide the relevant recommendations for that relevant section of the report. She will be responsible for ensuring the consistency of the mission's recommendations. She will check the quality of the mid-term review mission's aide-memoire and final report, which must meet IFAD's quality requirements.

Ms Paxina Chileshe, Lead Regional Climate and Environment Specialist and Mission Technical Lead,

The mission technical lead will lead the mission team in all technical discussions, report writing, finalization and presentation to stakeholders and will coordinate field activities. In particular, she will perform the following tasks: Assess the overall implementation strategy and their pertinence to meet the project goals; Assess progress against the 2025 AWPB and progress since inception, under each component and subcomponent; - Exchange with project partners and service providers and assess their effectiveness; - Assess the performance of the project support unit, in terms of effectiveness and efficiency; - Analyse the projects’ exit strategies and propose better solutions, if needed; Assess the level of implementation of agreed actions from past supervisions and implementation support missions; Identify actual and potential/emerging operational problems, and propose solutions for corrective measures or improvements to be made; - Prepare the AM and the MTR mission reports (including their annexes), with the contribution of the mission team members; - Present the results of the mission with the project team and national counterparts.

Dr. Edmund Kyei Akoto-Danso, Environment and Climate Change Expert,

The consultant will work closely with the Country Director and the mission technical lead and assess the overall structure of the project. He will assess all the aspects of the project on climate and environment and will take stock of the extent to which Integrated Water and Soil Management practices and Sustainable Land Management (SLM) practices have been integrated into the AWPB and implementation process of the ROOTS. He will (a) review overall performance on mainstreaming environment and climate change aspects in project activities that have already commenced, specifically the relevance and coherence of these within the larger investment; (b) review performance of the PSU and implementing partners on all activities that are being financed by ROOTS INLAMAG projects; (c) identify and assess key challenges in adopting sustainable and climate- resilient practices by beneficiaries of the ROOTS INLAMAG project; (d) assess whether infrastructure designs and construction/rehabilitation have been sufficiently climate- proofed; (e) ascertain the possible environmental impact of the project and verify quality of the mitigating measures; (f) review adherence to SECAP and coordinate the updating of the IPRM; (g) assess partnership between the project and partners involved in implementing GEF funds in terms of relevance and value addition to climate change adaptation; and (h) provide contributions to the AM and the MTR report.

Ms Grace Nakanjakko, M&E and Knowledge management expert

The M&E and Knowledge Management Expert will conduct a comprehensive assessment of the M&E systems of the ROOTS project. This will include a review of the clarity, logic, and coherence of the M&E arrangements and assigned responsibilities. Based on the findings, she will provide recommendations to strengthen the M&E systems to ensure effective and comprehensive reporting on the ROOTS INLAMAG project indicators. Specifically, the consultant will (a) review overall progress in implementing Project M&E and KM activities against AWPB, and agreed actions since the last supervision; (b) assess the M&E system and provide recommendations to further strengthen the analytical and M&E capacity of the relevant Project staff; (c) with specific reference to results monitoring, work with the ROOTS project M&E team to assess the physical implementation progress of the project measured against the logical framework targets; (d) review the usage of M&E data to inform project management and enhance communication and visibility of project activities and provide feedback for improvement; (e) address the cross-cutting issues such as targeting to the vulnerable groups, women participation, gender sensibility and partnership; (f) assess knowledge management activities and use of innovation for learning, and recommend specific capacity strengthening needs (if any) (g) discuss and examine with team members and the involved implementing agencies the effectiveness of the institutional arrangements for monitoring and evaluation, and provide advice on any improvement that will enhance the M&E management and knowledge management; (h) assist the Project in preparing the 2026 AWPB based on the recommendations from the MTR; and (h) contribute to the Aide Memoire and the MTR reports, including relevant appendices;

Mr. Mbaye Marone, Support Officer and M&E expert

He will, as part of the GEF mission and together with the M&E consultant: a) assess the functionality of the Monitoring and Evaluation (M&E) system and the linkages between ROOTS and GEF indicators and the consolidated logframe; b) review the capacity of implementing partners to collect, process, analyze, and communicate data related to GEF activities. Ensure that all actors are effectively involved at each stage (data collection, processing, analysis, etc.) and evaluate their respective capacities; c) work closely with the M&E Officer to address all pending issues identified in previous mission recommendations; d) formulate key recommendations to strengthen the programme’s performance in monitoring and evaluation; d) contribute to the drafting of the MTR mission aide-mémoire and the project MTR report, in line with the Mission Leader’s guidance and recommendations.

Ms. Couro Kane Wane, Social inclusion expert,

She will Facilitate coordination and exchanges among mission team members, supporting the IFAD team during the field mission. She will review the project's gender and social inclusion activities to determine the progress of implementation with regard to the AWPB, and the recommendations of previous missions. She will be responsible for: reviewing ROOTs systems to assess the allocated human resources, data collection and reporting systems within the broader M&E framework adapted to integrate social inclusion activities. She will: Assess the overall targeting strategy of the project; Contribute to the discussion around INAMLAG and ROOTS, resources; Review the level of implementation of IFAD mainstreaming themes (gender, youth, nutrition) in the implementation of ROOTS and propose measures to improve performance; make sure that the recommendations of all previous missions are duly considered; and Contribute to the drafting of the aide-memoire and reports. Specifically, she will review the social inclusion thematic areas as follows: Gender and Youth: i) assess the reach of beneficiaries, including women, men and youth (disaggregated into men and women); ii) review the progress of youth integration and assess whether project resources and services are delivered in a manner that meets the needs of youth, women and persons with disabilities; assess the quality of adoption of project activities by project groups and identify challenges faced by groups in the process;

iii) assess the level and quality of women's participation in project activities; iv) assess the progress of youth integration and improvement of youth objectives; v) assess the progress and results of the implementation of the strategy on persons with disabilities; vi) assess the relevance of project interventions to meet the needs of target beneficiaries, the extent to which the project addresses the needs of specific vulnerable groups; (vii) Assess the implementation of innovative approaches to address the three strategic objectives of IFAD’s Gender Policy and the root causes of gender inequalities and women’s empowerment (including prevailing social norms, attitudes and behaviors, discrimination and social systems) to ensure equal access for women and youth to productive assets and services, as well as to employment and climate resilience and market opportunities and make recommendations for improvement. Nutrition: (i) assess the implementation of nutrition-sensitive activities, including approaches used, targeting and results achieved;

(ii) review project documentation - progress reports, baselines and aide- memoires from previous supervision and support missions to see if nutrition-related recommendations have been followed; (iii) assess the progress and quality of implementation of planned nutrition-related activities (e.g., training materials, participation, technologies, tools);

(iv) assess whether nutrition-related actions/interventions are included in the annual work plan and budget. Targeting: i) review the adequacy of targeting criteria to reach all groups in the project areas; ii) assess whether program interventions reach the groups most vulnerable to malnutrition in accordance with the tools developed; iii) assess the outreach to beneficiaries; iv) review progress in implementing a cross-cutting targeting strategy; v) review the quality of targeting and outreach, the level of gender integration and the quality of participation of women and young people in relation to the objectives of the 2025 AWPB and the progress made.

Schedule of the mission:

The mission agenda, including field visits itinerary, will be provided before the beginning of the mission and will be discussed and finalized during the initial briefing meeting.

Officials from the Government (Ministry of Agriculture / National Environment Agency) and the implementing partners representatives and beneficiaries’ representatives will participate fully in the mission. Depending on their areas of expertise, they will be co-responsible for the mission's objectives.

| Official launch of the mission, and presentation by the team of the progress made by the project | 24 November 2025 |
| --- | --- |
| Meeting with partners/ field visit | 25 November 2025 |
| Field visit to project sites | 26 November 2025 |
| Engagement with PSU | 27 November 2025 |
| Drafting of the mission report | 28 - 30 November |
| Exchanges with the PSU on the draft report | 1 December 2025 |
| Finalization of report and technical wrap up | 2 December 2025 |

Documentation prepared for the mission team:

  - Implementation support mission reports

  - Previous Supervision mission reports

  - Steering Committee reports

  - ROOTS PDR

  - GEF CEO Endorsement Report

  - Progress reports for ROOTS, AFD, GEF and AICRM

  - COSTABs

  - Financing Agreements

  - LTBs

  - 2025 AWPB & PP

  - M&E data and logframe

  - Financial and Audit reports

  - Implementing partners reports

Mission schedule:

| Day | Date | Time | Activity |
| --- | --- | --- | --- |
| Monday | 24 November 2025 | 10h00-15h00 | Presentation of progress made by the project (at the project office) Meeting with NEA at 3:30pm |
| Tuesday | 25 November 2025 | All Day | Field visits to project sites. See below schedule |
| Wednesday | 26 November 2025 | All Day | Field visits to project sites. See below schedule |
| Thursday | 27 November 2025 |  | Field visits to project sites. See below schedule |
| Fri |  |  | De-briefing meeting of field visit and partner engagement. Invite all Implementing Partners under GEF |
| Fri. – Sunday | 28 – 30 November | All Day | Drafting of the mission report |
| Monday | 1 December 2025 | 09h00-14h00 | Exchanges with the PSU on the draft report |
| Tuesday | 2 December 2025 | 10h00-12h00 | Finalization of report and technical wrap up |

FIELD VISIT – GEF MIDTERM REVIEW

(25th November - 27th November 2025)

| No. | Date and Time | Region | Activity | Responsibility | Location | Intervention type |
| --- | --- | --- | --- | --- | --- | --- |
| Day 1 Day 2 | Tuesday 25th November 2025 8:00 – 10:30a.m. | WCR | Travel from PSU to Berefet and meeting with the community | ROOTS | Berefet | - ANR Firefighting equipment’s - Agroforestry for Rice - Agroforestry in gardens |
|  | 10:30-12:00 |  | Travel from Berefet to Karani | ROOTS | Karanni | - Agroforestry for Rice |
|  | 12:00 – 1:30 p.m. |  | Travel from Karani to Kambong and meeting with the community | ROOTS | Kambong | - Pasture and Rangeland |
|  | 1:30 – 3:00pm. |  | Travel from Kambong to Kansambou and meeting with the community | ROOTS | Kansambou | - Woodlot |
|  | 4:00-4:30pm |  | Night stop in Soma END OF DAY ONE |  |  |  |  |
|  | Wednesday 26th November 7:30-10:30 am | LRR | Travel from Soma to Misira and discussion with the community | ROOTS | Misira | - Agroforestry in gardens - ANR equipment - Pasture and Rangeland |
|  | 10:30-12:00pm |  | Travel from Misira to Janneh Kunda and meeting with the community | ROOTS | Janneh Kunda | - Agroforestry for rice - Cooking stoves |
|  | 12:00-1:30pm |  | Travel from Janneh Kunda to Manar community | ROOTS | Manar | - Pasture and Rangelands |
|  | 1:30 – 5:00pm |  | Travel from Manar community to Bissick | ROOT |  | - Agroforestry Garden - ANR - Firefighting |
|  | 5:00pm – 5:30pm |  | Travel from Bissick to Farafenni NBR |  |  |  |
|  |  |  | Farafenni NBR END OF DAY 2 |  |  |  |  |
| Day 3 | Thursday 27th November 8:00-10:30 |  | Travel from Farafenni to Suwareh Kunda and meeting with the community | ROOTS | Suwareh kunda | - Agroforestry in the Rice field - ANR Enrichment Planting |
|  | 10:30- 12:30 |  | Travel from Suwareh Kunda to Jerikaw Wollof | ROOTS | Jerkaw Woolf | - Woodlots - Cooking stoves |
|  | 12:30 – 2:00 |  | Travel from Jerikaw Wollof to Yella Tankoajella | ROOTS | Yella Tankoajella |  |
|  | 2:00-5:00PM | Departure To Banjul |  |  |  |  |  |
|  |  | End of the Field Mission |  |  |  |  |  |  |

ROOTS GEF MIDTERM REVIEW MISSION FIELD VISIT- ATTENDANCE LIST

IFAD – PSU- IPs

| Name | Institution |
| --- | --- |
| Ms. Paxina Chileshe (Team Lead) Dr. Edmund Kyei Akoto-Danso (Environment & CC Consultant) Ms. Couro Kane (Gender and S.I Consultant) Ms. Grace Nakanjako (M&E Consultant) Mr. Mbaye Marone (Support Officer, M&E Consultant | IFAD |
| Mr. Mamour Alieu Jagne (PD) Mr Alhagi Janneh ( FC) Mr Katim Touray (IAO) Mr Buba Saidy (M&EO) Mr Demba Sanyang (RC) Ms Elizabet Mendy (RC) Mr Paul Mendy (PO) Mr. Ousman Touray Dr. Boubacarr Barry ( IT) Mr Lamin S Darboe ( Head Comp1) Mr Ba Sadi Gassama ( W&I) Dr. Fatou Bojang (ENRO) Ms Aminata Sanyang (APD) Ms Matida Komma ( Gender O) | PSU |
| Mr. Allabatu Jatta | DLS |
| Babanding Sanyang | DoF |
| Amie Touray | DPWM |

Field Visit, 26th and 27th November

|  | Site Manar Region: LRR 26th November 2025 |  |
| --- | --- | --- |
|  | Name | Contact |
| 1 | Lamin Fatty | 2901908 |
| 2 | Amadou Sowe | 7134659 |
| 3 | Sheikh Yakub Fatty | 7068401 |
| 4 | Mustapha Fatty |  |
| 5 | Abdoucadiry Manneh | 55191488 |
| 6 | Seidai Conteh | 7516920 |
| 7 | Amadou Touray | 2703310 |
| 8 | Lamin Camara | 2981619 |
| 9 | Abdoucadiry Fatty | 7993941 |
| 10 | Amadou Koniteh | 2090089 |
| 11 | Ismeila Samateh | 7030524 |
| 12 | Alagie Koniteh | 6316291 |
| 13 | Ousman Njie |  |
| 14 | MomodouLamin Conteh | 2533937 |
| 15 | Alhagie Ousman Camara | 7008456 |
| 16 | Alhagie Foday Sonko | 2412148 |
| 17 | Lamin Darboe | 7425661 |
| 18 | Saikou Dumbeyai | 5077780 |
| 19 | Modou Lamin Camara | 2104284 |
| 20 | Sainey Samateh | 2973044 |
| 21 | Makong Ceesay |  |
| 22 | Galoj Jawo | 2741581 |
| 23 | Yakuba Touray | 3618065 |
| 24 | Salifu Saidy | 2077296 |
| 25 | Fatoumata Fatty | 2157510 |
| 26 | Maimuna Fatty | 2122861 |
| 27 | Fatou Dibba | 5210741 |
| 28 | Aminata Darboe |  |
| 29 | Zainabou Fatty | 4127926 |
| 30 | Mariama Camara | 7777867 |
| 31 | Omar Fatty | 2848805 |
| 32 | Habibatou Hydara | 7687136 |
| 33 | Isa Hydara |  |
| 34 | Tida Janneh |  |
| 35 | Binta Kanyi |  |
| 36 | Nyimanding Jarju | 2172771 |
| 37 | Kaddy Bass | 7688408 |
| 38 | Hawa Njie | 3359908 |
|  | Village: Janneh Kunda Region: LRR Reporting period: 26th November 2025 |  |
| 39 | Bora Bajinka | 3639104 |
| 40 | Nyikass Janneh | 3088372 |
| 41 | Ousman Manjang | 5225632 |
| 42 | Felejie Samateh | 3088290 |
| 43 | Aminata Kanteh | 3851708 |
| 44 | Lamin Manjang | 3045716 |
| 45 | Nyimansatou Jarju | 5351046 |
| 46 | Yakuba Jobarteh | 3621211 |
| 47 | Omar Sanyang |  |
| 48 | Fatou Samateh | 3441324 |
| 49 | Mai Demba | 3858704 |
| 50 | Fansainey Bajinka | 3851122 |
| 51 | Mariatou Janneh | 3547538 |
| 52 | Mama Marong | 3088283 |
| 53 | Nyimanding Janneh |  |
| 54 | Kaka Camara |  |
| 55 | Jalika Janneh | 3088296 |
| 56 | Natoma Gibba | 5968016 |
| 57 | Awa Bajo | 5020709 |
| 58 | Halima nama Janneh | 3358906 |
| 59 | Kaddy Janneh | 3534663 |
| 60 | Kaddy Ceesay | 5126064 |
| 61 | Halima Janneh | 3257989 |
| 62 | Binta Kanteh | 3809691 |
| 63 | Ensa Janneh | 5447117 |
| 64 | Kalifa Manjang |  |
| 65 | Mama Bajinka | 3217700 |
| 66 | Yaya So Janneh | 3073359 |
| 67 | Nyimanding Manjang | 3443221 |
| 68 | Adama Samateh | 3088139 |
| 69 | Mai Janneh |  |
| 70 | Nyima Sanyang | 5311739 |
| 71 | Aminata Bajinka | 3283948 |
| 72 | Mamanding Janneh | 3255736 |
| 73 | Kujai Kanteh | 3715884 |
| 74 | Kaddy Janneh | 3041523 |
| 75 | Mariama Kinteh | 5438952 |
| 76 | Marong Jammeh | 3184901 |
| 77 | Binta Sanyang | 3259749 |
| 78 | Zakaria Janneh | 5446802 |
| 79 | Babucarr Jadama | 3851115 |
| 80 | Dona Sanyang | 3441029 |
| 81 | Ndey Kambi | 5323562 |
| 82 | Fanta Manjang | 3452277 |
| 83 | Awa Samateh | 3088379 |
| 84 | Buba Janneh |  |
| 85 | Mariama Ceesay | 5340414 |
| 86 | Mama Janneh | 3010174 |
| 87 | Awa Jallow | 3732245 |
| 88 | Felejie Janneh |  |
| 89 | Sally Fofana |  |
| 90 | Nyimanding Janneh | 5581307 |
| 91 | Isatou Bajinka | 5681308 |
| 92 | Jung Janneh | 3915591 |
| 93 | Mai Manjang | 3301731 |
| 94 | Jai Jobarteh | 5903632 |
| 95 | Jainaba Marong | 3078611 |
| 96 | Sanna Manjang | 3255696 |
| 97 | Isatou Janneh |  |
| 98 | Nyimanding Sanyang | 5891846 |
| 99 | Isatoun Camara | 3602846 |
| 100 | Fatou Manneh | 3047471 |
| 101 | Musa Janneh | 5581307 |
| 102 | Mbajai Janneh | 5043575 |
| 103 | Fatou Manjang | 3088379 |
| 104 | Sutaring Kanteh | 3020264 |
| 105 | Jalla Janneh | 5340414 |
| 106 | Mamadou Kanteh |  |
| 107 | Jariatou Janneh |  |
| Berefet Village Foni Berefet District |  |  |
| 108 | Karafanding Badjie | 7174479 |
| 109 | FatouSanyang |  |
| 110 | Nyima Badjie | 2900356 |
| 111 | Amie Krubally | 2670588 |
| 112 | Bintou Njie |  |
| 113 | Mariama Manneh |  |
| 114 | Binta Badjie |  |
| 115 | Sunkary Tamba | 7315909 |
| 116 | Isatou Kanteh |  |
| 117 | Jainaba Giteh |  |
| 118 | Nyakassi Manneh | 2230779 |
| 119 | Fatou Gibba |  |
| 120 | Isatou Jadama |  |
| 121 | Fatou Jammeh |  |
| 122 | Nyiminding Bayo |  |
| 123 | Mariama Sanyang | 7644432 |
| 124 | Jainaba Saho | 7991173 |
| 125 | Dorbally Jaiteh | 7732243 |
| 126 | Jainaba Colley | 2266298 |
| 127 | Amie Jarjou |  |
| 128 | Fatou Badjie | 2468839 |
| 129 | Binta Badjie | 2272852 |
| 130 | Jainaba Badjie |  |
| 131 | Nyanya Sanyang | 4091908 |
| 132 | Fatou Camara | 2906376 |
| 133 | Fatou Jammeh |  |
| 134 | Nato Saho | 4082714 |
| 135 | Majula Sanyang | 2886009 |
| 136 | Jaitehnding Sayang |  |
| 137 | Arokey Ceesay | 2741076 |
| 138 | Abdou Keiteh | 4531000 |
| 139 | Bakary Gassama | 3965259 |
| 140 | Binta Bajo | 7236126 |
| 141 | Fatou Sanyang | 2294108 |
| 142 | Jankey Marong | 7468714 |
| 143 | Fatou Njie | 2410123 |
| 144 | Abie Sima | 4570010 |
| Berefet Cluster Forest Intervention type: ANR Fire Fighting Equipments |  |  |
| 145 | Malang Colley | 7400735 |
| 146 | Sainey Sanneh | 4032555 |
| 147 | Jatou Gibba | 7247884 |
| 148 | Nyassi Badjie | 7095599 |
| 149 | Sarjo Sanyang | 7093956 |
| 150 | Abdoulie Senghore | 2126445 |
| 151 | Landing Jammeh | 7554687 |
| 152 | John Mendy | 3183777 |
| 153 | Kebba Kebbeh | 2660572 |
| 154 | Fabakary Kassama | 2827578 |
| 155 | Abdou Krubally | 2602526 |
| 156 | Abdou Keita | 4531000 |
| 157 | Bakary Gassama | 3965259 |
| 158 | Amie Manneh | 2158177 |
| 159 | Isatou Jobarteh | 7154648 |
| 160 | Louis Mendy | 7280950 |
|  | Village Foni Bintang Karanai Intervention type: Agroforestry RICE |  |
| 161 | Fanta Sanneh | 2354663 |
| 162 | Amie Sanyang | 7803623 |
| 163 | Fatou Gibba |  |
| 164 | Abie Bojang | 7092665 |
| 165 | Ismaila Jarjou | 7714676 |
| 166 | Yaya Kujabi | 2536984 |
| 167 | Jarrie Jarjou | 7018255 |
| 168 | Abdou Sanneh | 2976736 |
| 169 | Matida Bojang |  |
| 170 | Nyima Badjie |  |
|  | Kambong Village Foni Kansala Intervention type: Pasture and Range land |  |
| 171 | Kemo Badjie | 2324118 |
| 172 | Alo Sallah | 3958032 |
| 173 | Bakary Bojang | 3571436 |
| 174 | Hawa Jammeh | 6368528 |
| 175 | Lala Jammeh | 2257467 |
| 176 | Adama Jarjou | 2495326 |
| 177 | Kulaymata Badjie | 3861475 |
| 178 | Metta Jarjou | 7588995 |
| 179 | Siabatou Jarjou | 2316152 |
| 180 | Fatou Sanyang | 2590380 |
| 181 | Rohey Badjie | 6872760 |
| 182 | Tarko Sowe | 7919740 |
| 183 | Hawa Jatta | 2762435 |
| 184 | Tumbule Bojang | 2344357 |
| 185 | Ensa Bojang | 2046054 |
| 186 | Kaddy Bojang | 5097694 |
| 187 | Abdou Ceesay | 3543453 |
| 188 | Fatou Badjie | 7030705 |
| 189 | Ramatoulie Jammeh | 2348488 |
| 190 | Kissa Badjie |  |
| 191 | Ida Sanneh | 6034683 |
| 192 | Sally Badjie | 7010316 |
| 193 | Amie Bojang | 2455864 |
| 194 | Tarko S Sowe |  |
| 195 | Fatou Bakary Badjie | 7357464 |
|  | Kansambou Village Foni Jarrol District |  |
| 196 | Malaphy Sambou |  |
| 197 | Kuba Sambou |  |
| 198 | Dodou Sambou |  |
| 199 | Bakary Sambou |  |
| 200 | Buba Sambou |  |
| 201 | Dodou Sambou |  |
| 202 | Bakary Sambou |  |
| 203 | Buba Sambou |  |
| 204 | Musa Sambou |  |
| 205 | Alhagie Sambou |  |
| 206 | Yorro Jomma |  |
| 207 | Landing Sambou |  |
| 208 | Dembou Sambou |  |
| 209 | Kaddyba Sambou |  |
| 210 | Awa Kambi |  |
| 211 | Fanta Jomma |  |
| 212 | Mboge Manga |  |
| 213 | Fanta Barjo |  |
| 214 | Sally Jandi |  |
| 215 | Fatou Sambou |  |
| 216 | Fatoumata Touray |  |
| 217 | Fula Musa Sambou |  |
| 218 | Manyima Sambou |  |
| 219 | Ado Manneh |  |
| 220 | Sireh Jomma |  |
| 221 | Sally Jomma |  |
| 222 | Sebbo Jomma |  |
| 223 | Isatou Sambou |  |
| 224 | Sarjo Sambou |  |
| 225 | Mam Jarra Manga |  |
| 226 | Bambi Manga |  |
| 227 | Sebo Sambou |  |
| 228 | Sariba Sambou |  |
| 229 | Naffi Sambou |  |
| 230 | Serreh Sambou |  |
| 231 | Jainaba Kombo |  |
| 232 | Sebo Darboe |  |
| 233 | Hawa Sambou |  |
| 234 | Metta Manjang |  |
| 235 | Mariama Manneh |  |
| 236 | Kumba Sowe |  |
| 237 | Fatima Sambou |  |
| 238 | Abubacarr Sambou |  |
| 239 | Mariama Sebo Manneh |  |
| 240 | Alhagie Sambou |  |
| 241 | Jalika Sambou |  |
| 242 | Jatou Sambou |  |
| 243 | Buba Sambou |  |
| 244 | Nfamara Sambou |  |
| 245 | Kunta Jomma |  |
| 246 | Mariama Jomma |  |
| 247 | Abdou Jomma |  |

26.6% of end target of 48,500Ha.

Representing 10% (91.3% of target) of the Gambia LDN target of 109,000Ha

Includes Area of Degraded Agriculture production landscape rehabilitated and restored through ANR, and bush fire management and Area under Agro-silvopastoral practices

Includes 10,000Ha of area of Degraded Agriculture production landscape rehabilitated and restored through ANR, and bush fire management and 16,500 of area under Agro-silvopastoral practices

Includes Area under Integrated Water and Soil Management practices, Area established under woodlots, Land under Agroforestry and sustainable and diversified cropping systems and Land under integrated Crop-Livestock Systems

- Includes 15000Ha of area under Integrated Water and Soil Management practices, 3000Ha of area established under woodlots, 500Ha of land under Agroforestry and sustainable and diversified cropping systems, 2000Ha of land under integrated Crop-Livestock Systems and 1500Ha as area under Integrated Water and Soil Management practices

Data Not Available