GEF-6 REQUEST FOR PROJECT ENDORSEMENT/APPROVAL

Project Type:

Type of Trust Fund:

For more information about GEF, visit TheGEF.org

part i: project information

| Project Title: Integrated management of production landscapes to deliver multiple global environmental benefits |  |  |  |  |
| --- | --- | --- | --- | --- |
| Country(ies): | Belize | GEF Project ID: |  | 9796 |
| GEF Agency(ies): | UNDP | GEF Agency Project ID: |  | 6015 |
| Other Executing Partner(s): | Ministry of Agriculture, Fisheries, Forestry, the Environment and Sustainable Development (MAFFESD) | Submission Date: |  | May 29, 2019 |
| GEF Focal Area (s): | Multi-focal Areas | Project Duration (Months) |  | 60 |
| Integrated Approach Pilot | IAP-Cities IAP-Commodities IAP-Food Security |  | Corporate Program: SGP |  |
| Name of Parent Program | n/a | Agency Fee ($) |  | 485,348 |

- Focal Area  Strategy Framework and Other Program Strategies

| ### Focal Area Objectives/Programs | ### Focal Area Outcomes | ### Trust Fund | ### (in $) |  |
| --- | --- | --- | --- | --- |
|  |  |  | ### GEF Project Financing* | ### Co-financing |
|  | Outcome 9.1 Increased area of production landscapes and seascapes that integrate conservation and sustainable use of biodiversity into management. |  | 3,434,254 | 15,872,354 |
|  | Outcome 1.1: Improved agricultural, rangeland and pastoral Management Outcome 1.2: Functionality and cover of agro-ecosystems maintained |  | 418,670 418,669 | 1,936,805 1,936,805 |
|  | Outcome 3.2: Integrated landscape management practices adopted by local communities based on gender sensitive needs |  | 837,340 | 3,873,610 |
| Total project costs |  |  | 5,108,933 | 23,619,574 |

*Applying the STAR flexibility mechanism of GEF-6, resources for a total of $1,780,339 USD of CC STAR allocation were transferred to the BD and LD focal areas for the FSP as follows: $890,169 USD were channeled to BD and $890,170 USD were transferred to LD, inclusive of the corresponding contributions to Project Management Cost. Thus, for the FSP a total amount of $3,434,254 USD of BD resources and a total amount of $1,674,679 USD of LD resources were allocated. Amounts including fees are shown in Table D. In addition, resources for a total of $46,145 USD were also being channeled to the BD and LD focal areas for the PPG as follows: $23,073 USD was channeled to BD and $23,072 USD was channeled to LD. Thus, for the PPG a total amount of $89,014 USD of BD resources and a total amount of $43,406 USD of LD resources were allocated. Amounts including fees are shown in Table E. There is no space in the portal template to accommodate these footnotes / comments

- Project description summary

| ### Project Objective: To mainstream biodiversity conservation and sustainable land/water management into production landscapes in Belize |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| ### Project Components/ ### Programs | ### Financing Type | ### Project Outcomes | ### Project Outputs | ### Trust Fund | ### (in $) |  |
|  |  |  |  |  | ### GEF Project Financing | ### Confirmed Co-financing |
| 1. Enabling environment (policies, financial mechanisms, and institutional capacities) for delivering multiple global environmental benefits (GEBs) through the sustainable management of production landscapes |  | Strengthened governance and financial structure for the conservation of biodiversity and ecosystem services through sustainable land (SLM)/water management in production landscapes including: a) National Lands Act updated; National Utilization Act updated; Environmental Impact Assessment (EIA) Regulations updated; d) National Integrated Water Resources (NIWR) Act updated; Fiscal Incentive Act updated; Integrated Water Resources Management Policy drafted. b. 30% increase in government and private funding aligned to support sustainable production in priority sectors (agriculture, tourism, forestry, and urban development and industry. Increased ability of the government to implement strategies for conservation and SLM/water management in production landscapes through: a. Increased capacity of staff of key agencies to promote biodiversity conservation, integrated watershed management, SLM, and building resilience to climate change as measured through GEF/UNDP Capacity Development Scorecard: i) Department of Environment/MAFFESD: from 37% to 67%. ii) Hydrology Unit/Ministry of Natural Resources (MNR): from 38% to 68%. iii) Department of Fisheries/MAFFESD: from 7% to 37%. iv) University of Belize-Natural Resource Management: from 63% to 93%. v) Sustainable Development Unit/MAFFESD: from 47% to 77%. vi) Department of Agriculture/MAFFESD: from 44% to 74%. vii) Lands and Survey Department/MNR: from 35% to 65%. viii) MNR Policy Unit: from 33% to 63%. ix) Department of Rural Development/ Ministry of Labour, Local Government and Rural Development (MLLGRD): from 58% to 88%. | 1.1. Revised and harmonized policies and legislation for riparian forest protection and management (National Lands Act and National Lands Utilization Act), water management and irrigation (National Integrated Water Resources Act), environmental management, river discharges, and water quality (Environmental Impact Assessment Regulations under the Environmental Protection Act, NIWR Act and Fiscal Incentives Act) and integrated management of watersheds (Integrated Watershed Management Policy) results in: a. Clarification of agencies jurisdictions/ mandates regarding integrated watershed management. b. National coordinating framework for integrated watershed management defined and enabled. c. Protocols for inter-institutional coordination to enforce norms and establish penalties related to the clearing of riparian forests, discharges to water bodies, illegal water withdrawal, and mining in rivers. 1.2. Improved monitoring and enforcement of legislation. 1.3. Diversified financial incentives developed and established through a participatory process (including women, indigenous peoples, and other vulnerable groups) to implement biodiversity-friendly production practices and sustainable water management and use strategies. 1.4. Expanded information management systems (e.g., hydrology, agriculture (BAIMS, GSMU, etc.), includes mechanisms and protocols such as databases and online map viewer for data gathering, access and information sharing between institutions to strengthen biodiversity conservation, land/water resource management, and sustainable agricultural management. 1.5. Multi-tiered training program to build (public, communities, and private) in biodiversity conservation, integrated watershed management, SLM, and building resilience to climate change. |  | 1,071,700 BD: 720,518 LD: 351,182 | 1,898,533 |
| 2. Delivering multiple GEBs through sustainable production and improved value chains for key agricultural and forest products from the Belize River watershed |  | Multiple GEBs achieved through: a. 4,500 hectares (ha) of landscape management tools (i.e., biological micro-corridors, agroforestry, forest enrichment, live fences, windbreaks, and hedges) that promote connectivity and biodiversity conservation. b. Density of key indicator species maintained in riparian zones/forest patches/corridors in production lands and protected areas: i) Jaguar (Panthera onca): 6-7 individuals/100 km2 (data for the Belize Central Corridor) ii) white-lipped peccary (Tayasu peccary): 1 individual/km2; iii) Howler monkey (Alouatta pigra): 32 individuals/km2 (Community Baboon Sanctuary, Belize River Valley) iv) Tapir (Tapirus bairdii): population study currently underway (preliminary estimate: 8 individuals / 10 km2) (Species densities to be verified during the project inception phase) c. 750 ha of riparian forests restored. d. 300 ha of groundwater recharge areas restored. Increased area of agriculture and forest production under sustainable practices: a. 30,500 ha of landscapes under sustainable agriculture with biodiversity benefits. b. 15,000 ha of landscapes under sustainable land management in production systems. Accessible markets for producers implementing sustainable practices including: a. Three (3) products with enhanced value chains placed in markets: Cohune Oil Production (small scale); Livestock (small and medium-sized farmers); and Sugar Cane (small and medium-sized farmers; and large-scale farms). b. Increase in 40% of farmers /producers’ net income (differentiated by gender) from sustainable products (cohune oil, livestock, and sugarcane) with enhanced value chains placed in markets by project end. (Net income of at least 80% of participating farmers [male/ female] documented at project inception [year 1]). | 2.1. Landscape management tools used in priority areas for biodiversity conservation. a. Conservation agreements with participating producers/farmers used for establishing landscape management tools (i.e., biological micro-corridors, agroforestry, forest enrichment, live fences, windbreaks, and hedges). b. Rehabilitation and management strategies for riparian forests implemented alongside programme for participatory soil management to reduce erosion and improve water quality. c. Improved forest monitoring system for enhanced land-use change monitoring within the BRW. 2.2. Water Master Plan for the BRW developed through a participatory process allows integrated management for sustainable land and water resources use: a. Critical groundwater recharge areas identified and mapped and delineated based on extent, quantity, and quality, recharge rate, etc. b. Baseline study of supply and demand and the quality of hydrological resources supports decision making to allocate water for sustainable production and irrigation. c. Optimized hydrological monitoring network (meteorological stations, wells, flow and stage gauges, etc.) provides data for sustainable water management and designing protection measures including flood and drought forecasting. d. Operationalization of funding strategy developed and mechanisms for implementation defined, including collection of fees for water use, for the development and implementation of Water Resource Master Plan and Water Quality Control Plan jointly between the NIWRA/MNR, DOE, and water users, following a water use data analysis. 2.3. At least two incentives (e.g., annual per-hectare payments in return for maintaining forest cover, state-funded results-based payments designed with environmental and socioeconomic targets, carbon sequestration certification) to promote sustainable agriculture and forest production piloted. 2.4. Gender responsive extension work program; to include training for small and large producers, including women and vulnerable groups, to implement sustainable production, post-production and livelihood practices; delivered through a capable Extension Service of the Department of Agriculture, the University of Belize, Galen University, and UNDP's Green Commodities Programme improves production, enhances value chains for key products, and builds awareness among small-scale and large-scale producers about markets for sustainable products. 2.5. Business management capacity of producers (including women) to implement sustainable practices improved through targeted training and technical support for agrobusiness development and private and cooperative support services. 2.6. Awareness program for producers, technicians, and government officials in the production sector (agriculture, tourism, forestry, and urban development and industry) informs and builds capacity to sustain and maintain the environmental and socioeconomic benefits of sustainable production practices and the availability of financial incentives and on-going programs to facilitate implementation. 2.7. Participatory monitoring program assesses the delivery of GEBs: biodiversity conservation and integrated watershed management to improve hydrological functions and services for agro-ecosystem productivity. 2.8 Micro-granting scheme with provides direct incentives/ investments to local communities participating in riparian restoration, conservation agreements and sustainable production. |  | 3,444,950 BD: 2,316,370LD: 1,128,580 | 19,978,039 |
| 3. Knowledge Management and Learning |  | Best practices and lessons are accessed and applied in other production landscapes and watersheds in the country and internationally indicated by: Ten (10) documents on successful farmers’ and community experiences, and practices about integrating SLM and biodiversity conservation practices, and gender mainstreaming in the BRW are disseminated in-country and internationally | 3.1. Gender sensitive/ gender responsive programmes/ activities promoted through project frameworks. 3.2. Experiences, best practices, and lessons learned about biodiversity conservation and SLM/water management in production landscapes captured, systematized and made available through various platforms for public and private stakeholders for use in other production landscapes and watersheds in the country, informing future projects and strategies. |  | 349,001 BD: 233,831 LD: 115,170 | 618,260 |
| Subtotal |  |  |  |  | 4,865,651 | 22,494,832 |
| Project Management Cost (PMC) (BD: 163,536; LD: 79,747) |  |  |  |  | 243,282 | 1,124,742 |
| Total project costs |  |  |  |  | 5,108,933 | 23,619,574 |

- confirmed sources of Co-financing for the project by name and by type

Please include evidence for co-financing for the project with this form.

| Sources of Co-financing | Name of Co-financier | Type of Cofinancing | Amount ($) |
| --- | --- | --- | --- |
|  | Ministry of Natural Resources |  | 324,000 |
|  | Ministry of Natural Resources |  | 224,000 |
|  | Ministry of Agriculture, Fisheries, Forestry, the Environment and Sustainable Development |  | 1,955,000 |
|  | Friends for Conservation and Development |  | 345,000 |
|  | UNDP |  | 75,000 |
|  | UNDP |  | 500,000 |
|  | UNDP /Green Climate Fund |  | 3,900,000 |
|  | University of Belize Environment Research Institute |  | 296,574 |
|  | University of Belize Environment Research Institute |  | 1,000,000 |
|  | Santander Sugar Group |  | 15,000,000 |
| Total Co-financing |  |  | 23,619,574 |

- Trust Fund  Resources Requested by Agency(ies),  Country(ies) and the Programming of Funds

| GEF Agency | Trust Fund | Country Name/Global | Focal Area | Programming of Funds | (in $) |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | GEF Project Financing (a) | Agency Fee a) (b)2 | Total (c)=a+b |
|  |  | Belize |  |  | 3,434,254 | 326,254 | 3,760,508 |
|  |  | Belize |  |  | 1,674,679 | 159,094 | 1,833,773 |
| Total Grant Resources |  |  |  |  | 5,108,933 | 485,348 | 5,594,281 |

a ) Refer to the Fee Policy for GEF Partner Agencies

- Project’s Target Contributions to GEF 6 Core Indicators

| Project Core Indicators |  | Expected at CEO Endorsement |
| --- | --- | --- |
| 3 | Area of land restored (Hectares) | 1,050* |
| 4 | Area of landscapes under improved practices (excluding protected areas)(Hectares) | 50,000** |
|  | Total area under improved management (Hectares) | 50,000 |
| 11 | Number of direct beneficiaries disaggregated by gender as co-benefit of GEF investment | 1,700 (women: 450; men: 1,250)*** |

* Indicator 3:  750 ha of riparian forest restore and 300 ha of wetlands/groundwater recharge areas restored in the BRW.

** Indicator 4: 4,500 ha of landscape management tools (i.e., biological micro-corridors, agroforestry, forest enrichment, live fences, windbreaks, and hedges) that promote connectivity and biodiversity conservation; 30,500 ha of landscapes under sustainable agriculture with biodiversity benefits; and 15,000 ha of landscapes under sustainable land management in production systems.

*** The both 2011 and 2018 agriculture census indicates women making up approximately 20% of the agriculture sector. The project targets women in those activities where they are most prominently represented e.g. post harvest operations. While the project expects equal representation of women in actions related to education and awareness, community led programmes such as community monitoring, community led rehabilitation efforts; the project is cognizant as to the numbers of women engaged in production systems. It is the intention of the project to ensure aggressive targeting of female producers; however, the project is unable to commit to the expansion of women producers. The project can commit to the participation of women in associated roles within the agriculture sector.

- Project Taxonomy

| Level 1 | Level 2 | Level 3 | Level 4 |
| --- | --- | --- | --- |
| Influencing Models | Transform policy and regulatory environments |  |  |
|  | Strengthen institutional capacity and decision-making |  |  |
| Stakeholders | Indigenous Peoples |  |  |
|  | Private Sector | Individuals/Entrepreneurs |  |
|  | Beneficiaries/ Local Communities/ Civil Society | Community Based Organization, Non-Governmental Organization, Academia |  |
|  | Type of Engagement, | Information, Dissemination, Consultation, Participation, |  |
|  | Communications | Awareness Raising, Education, Public Campaigns, Behavior Change |  |
| Capacity, Knowledge and Research | Capacity Development |  |  |
|  | Knowledge Generation and Exchange |  |  |
|  | Learning | Theory of Change, Adaptive Management, Indicators to Measure Change |  |
|  | Knowledge and Learning | Knowledge Management, Capacity Development, Learning |  |
|  | Stakeholder Engagement Plan |  |  |
| Gender Equality | Gender mainstreaming | Beneficiaries, Women groups, Sex-disaggregated indicators, Gender-sensitive indicators |  |
|  | Gender results areas | Access to benefits and services, capacity development, awareness raising knowledge generation |  |
| Focal Area/Theme | Biodiversity | Mainstreaming | Tourism, Agriculture & agrobiodiversity, Infrastructure |
|  |  | Species | Threatened species |
|  |  | Biomes | Wetlands, rivers, tropical rain forests |
|  |  | Financial and accounting | Conservation finance |
|  | Land Degradation | Sustainable Land Management | Restoration and Rehabilitation of Degraded Lands, Ecosystem Approach, Integrated and Cross-sectoral approach, Sustainable Agriculture, Sustainable Pasture Management, Improved Soil and Water Management Techniques, Drought Mitigation/Early Warning |
| Rio Marker | Climate Change Mitigation 0 Climate Change Adaptation 1 |  |  |

part ii:  project justification

A. describe any changes in alignment with the project design with the original pif

A.1. Project Description.

1) The global environmental and/or adaptation problems, root causes and barriers that need to be addressed. N/A

2) The baseline scenario or any associated baseline projects.

- In addition to the baseline scenario identified in the PIF, Belize will be implementing the Resilient Rural Belize (Be-Resilient) Green Climate Fund Project (2019-2025) with a total investment of USD $20 million to be partially financed through a loan from the International Fund for Agricultural Development (IFAD). The objective of this project is to build overall resilience to climate change by adopting new or improved climate-resilient practices, increasing and diversifying agricultural production, and facilitating access to commercial market chains for the off-take of surplus production. Five of the 23 communities across the country to be targeted by this investment are in the middle portions of the Belize River watershed (BRW), where the project proposed herein will be implemented (i.e., Valley of Peace, Buena Vista, La Gracia, San Antonio, and Seven Miles).

- The updated baseline scenario also includes the recent publication of the BRW Management Plan. This effort by the University of Belize in association with the World Wildlife Fund is the first of its kind in Belize and serves as a model for much-needed future watershed management. This initiative took a multidisciplinary approach in collecting and consolidating data pertaining to the BRW. Through scientific research, stakeholder consultations, and community engagement, a sustainable management plan was prepared identifying long-term monitoring programs and projects to bolster conservation and restoration actions and policies to protect the BRW and its resources. The project proposed herein will contribute to the implementation of the BRW Management Plan.

3) The proposed alternative scenario, GEF focal area strategies, with a brief description of expected outcomes and components of the project.

- The project design is closely aligned to the original PIF. The structure of the project components closely resembles the PIF approved by the GEF. A description of the project components is provided in Section V: Results and Partnerships of the GEF-UNDP Project Document. In addition, some changes were made to the project’s outputs, which do not represent a departure from the project’s strategy as defined originally in the PIF nor will they have an impact on the funds originally budgeted. These changes are described as follows:

| PIF Outputs (Component 1) | Project Document Outputs (Component 1) |
| --- | --- |
| 1.1. Revised and harmonized policies and legislation for riparian forest protection (National Land Utilization Act), forest management (Forest Act), water management and irrigation (National Integrated Water Resources Act), river sand mining (Environmental and Safety Regulations under the Mines and Minerals Act), environmental management, river discharges, and water quality (Environmental Protection Act) | 1.1. Revised and harmonized policies and legislation for riparian forest protection and management (National Lands Act and National Lands Utilization Act), water management and irrigation (National Integrated Water Resources Act), environmental management, river discharges, and water quality (Environmental Impact Assessment Regulations under the Environmental Protection Act, NIWR Act and Fiscal Incentives Act) and integrated management of watersheds (Integrated Watershed Management Policy). This project output was reworded to indicate the actual policies and legislation where investments will be focused, based on feasibility assessments and consultations with key stakeholders conducted during the final project design. |
| 1.1(d). Improved monitoring and enforcement of legislation and policy governing land use and land use conflicts, including staff trained and equipped in the Lands and Surveys Department | 1.2. Improved monitoring and enforcement of legislation This output was originally included in the PIF as part of Output 1.1. It is now included as a stand-alone output, given the relevance of monitoring and enforcement for safeguarding the BRW ecosystems and ecosystem services. Monitoring and enforcement functions were expanded beyond the Lands and Surveys Department/Ministry of Natural Resources (MNR) to include the Ministry of Agriculture, Fisheries, Forestry, the Environment ,and Sustainable Development (MAFFESD) and local communities through collaborative planning and joint implementation. |
| 1.3. Expanded information management system under the National Integrated Water Resources Authority (NIWRA)/Land information Center, Ministry of Natural Resources, includes mechanisms and protocols such as databases and online map viewer for data gathering, access and information sharing between institutions to strengthen biodiversity conservation, land/water resource management, and sustainable agricultural management. | 1.4. Expanded information management systems (e.g., hydrology, agriculture (BAIMS, GSMU, etc.), includes mechanisms and protocols such as databases and online map viewer for data gathering, access and information sharing between institutions to strengthen biodiversity conservation, land/water resource management, and sustainable agricultural management. The scope of the information management systems to be supported through the project was expanded beyond NIWRA (water resources management) to include the MAFFESD for the generation of environmental and agroecological information to support biodiversity conservation, land/water resource management, and sustainable agricultural management. |
| 1.4. Training program at the national level to build institutional capacities (public and private) in biodiversity conservation, integrated watershed management, SLM, and building resilience to climate change. | 1.5. Multi-tiered training program to build (public, communities, and private) in biodiversity conservation, integrated watershed management, SLM, and building resilience to climate change. The scope of the output was expanded so that the training program will have a technical/national level component targeting decision-makers, financial institutions, and extension officers and technicians/agronomists from large farms, as well as a local/operational-level component targeting landowners and farmers (including women), as well as community groups, etc. |
| 1.5. Operationalization of a funding strategy, including collection of fees for water use, for the development and implementation of Water Resource Master Plans and Water Quality Control Plans jointly between the NIWRA/MNR and water users. | This output was moved to Component 2 and will focus only on the BRW. Lessons learned from implementation will inform decision-makers about the operationalization of a funding strategy to support Water Resource Master Plans and Water Quality Control Plans in other watersheds in the future. |
| 1.6. Awareness program for producers, technicians, and government officials in the production sector (agriculture, tourism, forestry, and urban development and industry) informs about the environmental and socioeconomic benefits of sustainable production practices and the availability of financial incentives to facilitate implementation. | This output was moved to Component 2 and will focus only on the BRW as it is more in line with the activities planned under this component. |
| PIF Outputs (Component 2) | Project Document Outputs (Component 2) |
| 2.1. Landscape management tools used in priority areas for biodiversity conservation, including: a. Conservation agreements with participating producers/farmers used for establishing landscape management tools (i.e., biological micro-corridors, agroforestry, forest enrichment, live fences, windbreaks, and hedges). b. At least five nurseries of endemic and native plants established. | 2.1. Landscape management tools used in priority areas for biodiversity conservation. a. Conservation agreements with participating producers/farmers used for establishing landscape management tools (i.e., biological micro-corridors, agroforestry, forest enrichment, live fences, windbreaks, and hedges). b. Rehabilitation and management strategies for riparian forests implemented alongside programme for participatory soil management to reduce erosion and improve water quality. c. Improved forest monitoring system for enhanced land-use change monitoring within the BRW. As part of this output, the project will also implement a riparian forest restoration strategy and a Forest Protection Strategy for the project area. The riparian strategy will establish riparian management zones within the watershed and provide guidance and approaches to rehabilitation within prioritized zones, thereby contributing to building ecosystem connectivity. The Forest Protection Strategy will provide effective guidance for monitoring and protection of the remaining areas of forest stands, specifically targeting priority areas that have incomplete protection by promoting better implementation and enforcement of existing laws and ensuring that development planning considers conservation, landholding, forestry, local community and the broader public interest. Nurseries will be established to support the implementation of LMTs and restoration actions, and will be operated by participating communities and institutions. |
| 2.2. Water Master Plan for the Belize River watershed developed through a participatory process allows integrated management for sustainable land and water resources use: a. Rehabilitation and management strategies for riparian forests implemented based on a baseline study of stresses and degree of damage to these forests conducted during the PPG phase. b. Critical groundwater recharge areas identified and mapped and delineated based on extent, quantity, and quality, recharge rate, etc. c. Optimized hydrological monitoring network (meteorological stations, wells, flow and stage gauges, etc.) provides data for sustainable water management and designing protection measures including flood and drought forecasting. d. Program for participatory soil management to reduce erosion and improve water quality. | 2.2. Water Master Plan for the BRW developed through a participatory process allows integrated management for sustainable land and water resources use: a. Critical groundwater recharge areas identified and mapped and delineated based on extent, quantity, and quality, recharge rate, etc. b. Baseline study of supply and demand and the quality of hydrological resources supports decision making to allocate water for sustainable production and irrigation. c. Optimized hydrological monitoring network (meteorological stations, wells, flow and stage gauges, etc.) provides data for sustainable water management and designing protection measures including flood and drought forecasting. d. Operationalization of funding strategy developed and mechanisms for implementation defined, including collection of fees for water use, for the development and implementation of Water Resource Master Plan and Water Quality Control Plan jointly between the NIWRA/MNR, DOE, and water users, following a water use data analysis. The baseline study of supply and demand and the quality of hydrological resources was originally a stand-alone output but was moved to this output as it is directly related to the development of the BRW Water Master Plan. The program for participatory soil management to reduce erosion and improve water quality is now included as part of the riparian forest restoration strategy under Output 1.1. The operationalization of a funding strategy and mechanisms for implementation were originally an output in Component 1 but were moved to Component 2, focusing solely on the BRW. Lessons learned from implementation will inform decision-makers about the operationalization of a funding strategy to support Water Resource Master Plans and Water Quality Control Plans in other watersheds in the future. |
| 2.3. Baseline study of supply and demand and the quality of hydrological resources supports decision making to allocate water for sustainable production and irrigation. | This is not included as a stand-alone output; it is now included as part of Output 2.2. |
| 2.5. Updated land tenure records and land use change assessment in participating farms assist the piloting of incentives mechanism. | The output is not included in the final project design. |
| 2.6. Training program for small and large producers, including women and vulnerable groups, to implement sustainable production practices. | This output was merged with Output 2.7; please see below. |
| 2.7. Extension work program through the Extension Service of the Department of Agriculture and the University of Belize improves production, enhances value chains for key products, and builds awareness among small-scale and large-scale producers about markets for sustainable products. | 2.4. Gender responsive extension work program; to include training for small and large producers, including women and vulnerable groups, to implement sustainable production, post-production and livelihood practices; delivered through a capable Extension Service of the Department of Agriculture, the University of Belize, Galen University, and UNDP's Green Commodities Programme improves production, enhances value chains for key products, and builds awareness among small-scale and large-scale producers about markets for sustainable products. This output was reworded to highlight the fact that the extension work program will be gender responsive and will include the original Output 2.6. Also, in addition to the Extension Service of the Department of Agriculture and the University of Belize, Galen University and UNDP’s Green Commodities Programme were included as project partners who will contribute to delivering this output based on their experiences in promoting sustainable development in Belize and working with smallholder farmers and other stakeholders to strengthen agricultural commodity production and supply chains, as well as improve farmers’ competitiveness in the markets. |
| 2.8. Business management capacity of producers (including women) to implement sustainable practices improved through targeted training and technical support (business plan development, accounting, financing, and marketing). | 2.5. Business management capacity of producers (including women) to implement sustainable practices improved through targeted training and technical support for agrobusiness development and private and cooperative support services. This output was reworded to indicate that support for producers (including women) will include private and cooperative support services as part of the primary objective of building the capacities of producers and processors to maintain sustainable systems, while improving their profitability and managing their businesses. |
| Not included in Component 2. | 2.7. Participatory monitoring program assesses the delivery of GEBs: biodiversity conservation and integrated watershed management to improve hydrological functions and services for agro-ecosystem productivity. Originally included in Component 3, this output was moved to Component 2 to support a participatory monitoring program. |
|  | 2.8 Micro-granting scheme with provides direct incentives/ investments to local communities participating in riparian restoration, conservation agreements and sustainable production. This output was included to indicate the mechanism by which the project will fund Community Smart Growth Projects within the BRW (i.e., projects that protect the environment while supporting the generation of benefits for watershed residents). |
| PIF Outputs (Component 3) | Project Document Outputs (Component 3) |
| 3.1. Participatory monitoring program assesses the delivery of GEBs: biodiversity conservation and integrated watershed management to improve hydrological functions and services for agro-ecosystem productivity. | This output was moved to Component 2, which will deliver the GEBs of the project. Monitoring and evaluation of the project, as described in Section C of this CEO Endorsement Request, will be implemented as part of Component 3 (Output 3.2). |
| Not included. | 3.1. Gender sensitive/ gender responsive programmes/ activities promoted through project frameworks. This output was included to ensure effective gender mainstreaming, including implementation of the Gender Action Plan, which is provided in A.4., Gender Equality and Women’s Empowerment, of this CEO Endorsement Request. |

4) Incremental/additional cost reasoning and expected contributions from the baseline, the GEFTF, LDCF, SCCF,  and co-financing.

- Total co-financing increased from USD $15,076,600 to USD $23,619,574. The additional co-financing will be invested by the Santander Sugar Group to support activities related to Outcome 2.2: Increased area of agriculture and forest production under sustainable practices, within Santander managed areas in the Belize River Watershed.

5) Global environmental benefits (GEFTF).

- Although there were no changes to the incremental/additional cost reasoning and approach, there was a change to the GEBs to be delivered. In particular, there was an increase from 500 ha to 1.050 ha in the area of land restored. In addition, the area of landscapes under improved practices (excluding protected areas) was revised. During the PIF stage, the entire area of the BRW was considered, including protected areas. The change was made from 606,684 ha to 50,000 ha, including 4,500 ha of landscape management tools (i.e., biological micro-corridors, agroforestry, forest enrichment, live fences, windbreaks, and hedges). The target of rehabilitating at least 50% of key groundwater recharge areas was modified to 300 ha of groundwater recharge areas/wetlands restored. This new goal was determined based on an assessment for the identification, protection, and recovery of groundwater recharge areas conducted during the final formulation process and in response to STAP’s comment to clarify how the target was defined during the PIF stage.

6) Innovativeness, sustainability and potential for scaling up.

- An updated description of the project’s innovativeness, sustainability, and potential for scaling-up is included in Section V. Results and Partnerships (Sustainability and Scaling-Up) of the GEF-UNDP Project Document.

A.2. Child Project?  If this is a child project under a program, describe how the components contribute to the overall program impact.

No.

A.3.  Stakeholders. Please provide the Stakeholder Engagement Plan or equivalent assessment. Please refer to Annex F of the GEF-UNDP Project Document.

- The successful implementation of the project will largely depend on the effective communication and coordination with the multiple project stakeholders, and the implementation of mechanisms to ensure the participation of these stakeholders. The key national and sub-national stakeholders include the Ministry of Natural Resources (MNR); the Ministry of Agriculture, Fisheries, Forestry, the Environment, and Sustainable Development (MAFFESD); the Ministry of Rural Development; the Ministry of Economic Development; the National Integrated Water Resources Authority (NIWRA); and Friends for Conservation and Development (FCD), among others. At the local level, the most relevant stakeholders are small-, medium-, and large-scale farmers, producers’ associations, women’s groups, and local communities; they are the primary beneficiaries of the project as they will participate in the key project activities. The extensive stakeholder consultations and engagement that began during the PPG phase will be continued throughout project implementation. To achieve this, the project will make use of several mechanisms, including: a) Project Inception Workshop: the project will be presented to both direct stakeholders and the public; b) Project Board: comprised of representatives of the government agencies,  the private sector, and academia, it will be responsible for approving the work plans, participating in the recruitment processes, and providing overall strategic guidance to the project; c) Project Management Unit (PMU): responsible for the implementation of the stakeholder engagement plan, communications plan, gender action plan, grievance redress mechanisms, and M&E; d) Communication and Dissemination of Information: the PMU will implement the Stakeholder Engagement Plan and ensure communication with all stakeholders through a variety of  methods (meetings, listserv, webpage, social media, etc.); the project will hire the services of a Communications/Knowledge Consultant to undertake a systematization of the project’s experience at the mid-point and at the end of the project to ensure its dissemination; e) Governance role for project target groups: project target groups will be represented on the Project Board as well as be engaged through Technical Advisory Groups (TAG); TAG members bring unique knowledge and skills, which complement the knowledge and skills of the formal board in order to more effectively direct interventions within the project; f) Gender Action Plan: will secure the involvement of both genders, especially women and youth; a Gender Expert/Advisor will be hired to review and update the implementation of the Gender Action Plan; g) Grievance Mechanism: this will be established and published so that all stakeholders are aware of its existence, documenting any potential grievances and ensuring they are addressed in a timely manner; h) Activities, Training, and Engagement Plans: these will employ a participatory approach that is rights-based and integrates the perspectives of all stakeholders using bottom-up approaches and integrating the different views of local stakeholders and beneficiaries; and i) Decentralized M&E: this will include meetings with the project target groups, interviews with direct beneficiaries, and meetings with special groups such as women to verify indicators.

Select what role civil society will play in the project:

Consulted only;

Member of Advisory Body; contractor;

Co-financier;

Member of project steering committee or equivalent decision-making body;

Executor or co-executor;

Other (Please explain)

A.4. Gender Equality and Women's Empowerment. Provide the gender analysis or equivalent socio-economic assessment. (Type response here; if available, upload document or provide link)

Does the project expect to include any gender-responsive measures to address gender gaps or promote gender equality and women’s empowerment? (yes  /no)

| Component/Activities | Indicators | Target | Budget (USD)* | Responsible institution | Period of Implementation |
| --- | --- | --- | --- | --- | --- |
| Outcome 1: Component 1: Enabling environment (policies, financial mechanisms, and institutional capacities) for delivering multiple global environmental benefits (GEBs) through the sustainable management of production landscapes |  |  |  |  |  |
| - Recognize women as key watershed stakeholders (Readiness) - Include women and youth from the BRW productive landscape in the drafting and implementation of a Water Management Plan for this project region. - Build the capacity of women and men to enable inclusive decision-making and informed consent - Ensure that women’s representation on project management decision making bodies in this project isn’t limited to nominal position - Establish and support actions to strengthen capacities of women, men, and youth beneficiaries to participate in watershed management - Strongly encourage and promote the collection of sex-disaggregated data throughout the project process, and the use of gender analyses to inform key policy and strategy documents - Apply safeguards to ensure women’s rights are included in subsequent changes to laws, policies and strategies enabled by the project - Promote the equal participation of men, women, and other marginalized groups in the development of the Belize River Watershed Integrated Management Plan. - Train staff from the project’s Executing Agency and their partners in strategy, conceptual frameworks, and practical tools for implementing the focus on gender. | - Percent of women on: Policy harmonization committees | At least 35% | 277,000 | MAFFESD, MNR, PMU | 2019 – 2024 |
|  | - Percent of BRW Task force participating in meetings or events related to governance in PAs, corridors, water, forests, and land are women. | At least 35% |  |  |  |
|  | - Increase in participation of women as leaders, including indigenous women, in leadership positions of the structures, organizations, and platforms of governance in the PAs, corridors, water, forests, and land. | 50% |  |  |  |
| Component 2: Delivering multiple GEBs through sustainable production and improved value chains for key agricultural and forest products from the Belize River watershed |  |  |  |  |  |
| - Enable full and effective consultation and participation of women and men in all stages of component planning and delivery - Provide women and men with equal access to information regarding all aspects of projects - Involve women in all monitoring, reporting and verification (MRV) and Monitoring and Evaluation (M&E) activities, and provide the necessary tools and knowledge needed for women to engage meaningfully. - Female and male producers, including youth have consistent access to community-based training that promote biodiversity conservation, integrated watershed management, SLM, and resilience building to climate change. - Strengthen the incorporation of the gender focus to improve women’s participation in commodity value chains and sustainable production systems. - Strengthen existing extension support and services to design and deliver gender-sensitive information to both female and male farmers. - Agriculture field school curriculum expanded to include traditional “female” crops - Ensure that women have the option to participate in all types of formal and non-formal training and education, in order to increase their technical capacity to engage in project activities. - Ensure micro-grant criteria allows for the equitable distribution of benefits; paying special attention to cultures and traditional practices that entrench inequality and could exclude women from engaging the mechanism - Incorporate gender focus into all training, educational, and awareness-raising processes associated with project implementation. - Facilitate the contributions of women, male and female youth in the design and implementation of community-based monitoring systems for water resource, biodiversity, and land use. | - No. of male and female producers who receive technical assistance/and or training. | 450 | 724,500 | MAFFESD, PMU | 2019 – 2024 |
|  | - Proportion of educational and training actions that include information about the importance of equal participation of men and women in managing the production landscapes. | 100% |  |  |  |
|  | - No. of conservation agreements that reflects a clause that addresses the rights of women, including indigenous women, and the equal distribution of benefits. | At least one |  |  |  |
|  | - Percent of the micro-grant or other types of incentives that promote the sustainable management of their farms and production processes and/or contribute to the connectivity and management of the corridors are given to women and youth beneficiaries. | At least 40% |  |  |  |
|  | - Percent of business plans and strategies written for women owned enterprises | 50% |  |  |  |
|  | - Percent of women farmers who receive technical support from the project and adopt more sustainable production techniques and practices for managing landscapes. | At least 35% |  |  |  |
| Component 3: Knowledge Management and Learning |  |  |  |  |  |
| - Maintain a registry of participation disaggregated by gender and ethnicity for training, education, and awareness-raising events, farms, families benefiting from other services under this project output. - Develop and disseminate communication materials that incorporate gender perspectives which informs the wider public about the environmental and socioeconomic benefits of sustainable production practices at household, community, and societal levels. - Support communities of practice among all stakeholders, including men and women in the BRW. - Design and implement sustainable production landscape management field internships programs for senior, female and male graduate students at the University of Belize. - Establish a gender-balanced research teams from the Faculty of Science and Technology conduct research on natural resource management, production practices and water quality in the BRW. - Organize, coordinate and launch research seminars on at least one (1) of the key aspects of the BRW productive landscape (biodiversity, land management, water quality, recharge areas, policy implementation, livelihood, etc.) which have implications for male and female producers. - Conduct community level research complete with sex disaggregated baseline data and socio-economic information that provides for a comprehensive profile of each community benefitting from an incentive project. | - No. of knowledge products produced, which addresses gender dynamics within the BRW | At least three (3) | 461,000 | MAFFESD, PMU | 2019 – 2024 |
|  | - Percent of project communications that reflect gender perspectives | 100% |  |  |  |
|  | - Percent of research fellowship benefiting female youths | 50% |  |  |  |

EXPECTED ACCOMPLISHMENTS:

EA1: Enhanced inclusion and representation of women and youth in the governance and management mechanisms for the BRW.

EA2: Female and male producers, including youth have consistent access to community-based training that promote biodiversity conservation, integrated watershed management, SLM, and resilience building to climate change.

EA3: Males and females in the BRW are aware of and publicly articulating the benefits of sustainable production practices on biodiversity, land and water resources.

EA4: Male and female producers in the BRW have the capacities to contribute to knowledge, data and information generation that inform sustainable production practices, and the maintenance of global environmental benefits in the BRW.

EA5: Male and female producers are incentivized to implement sustainable, and environmentally friendly production practices.

Budget

| Item | Consolidated Associated Cost** (USD) |
| --- | --- |
| EA1 | 32,000 |
| EA2 | 245,000 |
| EA3 | 397,500 |
| EA4 | 327,000 |
| EA5 | 371,000 |
| Monitoring and Evaluation | 90,000 |
| Total | 1,469,500 |

** Supporting Activity Cost is as represented within the project Total Budget and Workplan in the GEF-UNDP Project Document.

If possible, indicate in which results area(s)  the project is expected to contribute to gender equality:

closing gender gaps in access to and control over natural resources;

improving women’s participation and decision making; and or

generating socio-economic benefits or services for women.

Does the project's results framework or logical framework include gender-sensitive indicators? (yes  /no)

- # of direct project beneficiaries disaggregated by gender.

- Farmers /producers’ net income (differentiated by gender) from sustainable products (cohune oil, livestock, and sugarcane) with enhanced value chains placed in markets by project end.

A.5 Risk. Elaborate on indicated risks, including climate change, potential social and environmental risks that might prevent the project objectives from being achieved, and, if possible, the proposed measures that address these risks at the time of project implementation.(table format acceptable).

- An updated description of the project’s risk is included in Annex H: UNDP Risk Log of the GEF-UNDP Project Document.

A.6. Institutional Arrangement and Coordination. Describe the institutional arrangement for project implementation. Elaborate on the planned coordination with other relevant GEF-financed projects and other initiatives.

- Institutional arrangements are described in Section IX: Governance and Management Arrangements of the GEF-UNDP Project Document. In addition, an updated description of the coordination with other relevant GEF-financed and other initiatives in included in Section V. Results and Partnerships of the GEF-UNDP Project Document.

# Additional Information not well elaborated at PIF Stage:

A.7 Benefits. Describe the socioeconomic benefits to be delivered by the project at the national and local levels. How do these benefits translate in supporting the achievement of global environment benefits (GEF Trust Fund) or adaptation benefits (LDCF/SCCF)?

- The project will ensure the direct, free, and equal participation of all national and local stakeholders in the planning and implementation of measures that will result in strengthened connectivity between KBAs and production landscapes in the BRW and sustainable production practices, at the same time generating social and economic benefits. At the local level, the project will provide monetary and non-monetary benefits equally to the local stakeholders independently of their conditions, and will result in the following: a) increase in the income of small- and medium-scale farmers, including women and indigenous peoples, resulting from the implementation of landscape management tools including agroforestry and agricultural production practices, and from the use of economic incentives (e.g., Fair Trade mechanisms, ecotourism certification, and carbon credits); b) improved value chains for key agricultural and forest products (sugarcane, livestock, and cohune oil) with access to markets for producers implementing sustainable practices; c) access to plant material through community and/or government-operated nurseries for the implementation of agroforestry, soil stabilization along river banks, and rehabilitation of degraded lands; and e) empowerment of local communities through their direct participation in planning, implementation, and monitoring of environmental protection and management actions in the BRW. In addition, the project will train local community members, small- and large- scale farmers, and women’s groups, among other civil society organizations, so that they become the principal facilitators and decision-makers for biodiversity conservation in production landscapes, SLM, and IWRM in the BRW. The project will directly benefit 1,700 people (1,250 men and 450 women).

A.8 Knowledge Management.

- Project Component 3: Knowledge Management and Learning (Section V: Results and Partnerships of the GEF-UNDP Project Document) outlines the knowledge management strategy to promote learning through participatory processes, as well to enhance community stewardship as awareness of the project activities for mainstreaming biodiversity into production landscapes, enhancing ecosystem connectivity, promoting SLM, sustainable production practices, and gender mainstreaming. This strategy includes specific activities on how best practices will be documented and experiences will be shared with stakeholders. a key best practice in the management of landscapes/watershed would be to provide opportunities for all stakeholders/rights-holders to make meaningful inputs in planning, monitoring and overall oversight of activities in the area. To this end, each year the project team will plan and undertake an annual congress to discuss issues in the watershed, document challenges, ad share experience. Knowledge and best production practices will also be shared with similar projects in the LAC region that are part of UNDP-GEF Regional Coordination Unit (RCU) project portfolio (e.g., Colombia, Costa Rica, Grenada, Guatemala, Honduras, and Panama), initiatives outside of the GEF partnership, and through networks such as the Conference of the Parties of the CBD, the Panorama Portal “Solutions for a Healthy Planet”, and Good Growth Partnership (the latter with support from the UNDP's Green Commodities Programme)

- The project will also share information with IW projects regarding water management strategies through the GEF’s IW:LEARN program. This may include projects such as GEF ID 10172 Towards the Transboundary Integrated Water Resource Management (IWRM) of the Sixaola River Basin shared by Costa Rica and Panama, and GEF ID 9246 Integrated Environmental Management of the Río Motagua Watershed (Honduras and Guatemala).

- In addition, the project will build synergies with IICA so that lessons learned regarding sustainable agriculture are shared through platforms such as: a) IICA Play, an open access and innovative platform designed to access knowledge by making technical and educational content and other information related to crop production and livestock farming available to producers, researchers, students, and young professionals; and b) Warriors – the brainchild – IICA, an online discussion forum that provides a platform to raise awareness and demonstrate the pivotal role of rural women in global food production, as well as to assist in empowering them and improving their socioeconomic conditions.

B. Description of the consistency of the project with:

B.1 Consistency with National Priorities. Describe the consistency of the project with national strategies and plans or reports and assessments under relevant conventions such as NAPAs, NAPs, ASGM NAPs, MIAs, NBSAPs, NCs, TNAs, NCSAs, NIPs, PRSPs, NPFE, BURs, etc.:

- Belize is party member of the Convention on Biological Diversity (CBD), ratified on March 3, 1994. The project is consistent with the National Biodiversity Strategy and Action Plan (NBSAP) (2016-2020), which is based on Belize’s commitment to the conservation and sustainable development of national biodiversity. The NBSAP includes the following goals: 1. Mainstream biodiversity by fostering an understanding and appreciation of biodiversity, its benefits and values at all levels of society. The project will contribute to this goal by enabling the conditions (policies, financial mechanisms, and institutional capacities) for mainstreaming biodiversity into the country’s production lands, and more specifically mainstreaming biodiversity into production lands in the BRW through the implementation of landscape management tools used in priority areas for biodiversity conservation and promoting sustainable agriculture and forest production. 2. Reduce pressures and promoting the sustainable use of biodiversity and the supply of ecosystem services. The project will contribute to this goal by reducing existing threats to biodiversity in the BRW, including addressing deforestation and degradation of riparian forests, implementing sustainable agriculture practices that reduce the use of agrochemicals and control erosion, protecting against agricultural runoff that affects freshwater and costal ecosystems, and building strong partnerships between government agencies for improved enforcement of regulations regarding forests and water resources conservation. 3. Maintain and strengthen functional ecosystems and viable populations of Belize’s biodiversity including a landscape approach and building resilience to climate change. The project will contribute to strengthening functional ecosystems, particularly broadleaf forests and riparian forests, by promoting their conservation and sustainable use in production lands, which will lead to more stable and resilient ecosystems. In addition, by creating micro corridors and restoring degraded riparian forests, the project will contribute to providing enhanced habitat for populations of species of global and local importance and promoting connectivity between forest patches in production lands and protected areas. This will serve to improve the resilience of these species to climate change through increased mobility and by providing refuge against temperature changes and tropical storms, which in the past two decades have increased in frequency and have significantly affected the country. 4. Strengthen the provision of ecosystem services, ecosystem-based management, and the equitable sharing of benefits from biodiversity. The project will contribute to the conservation of forests in the Maya Mountains Massif, which are vital for providing water in the BRW, maintaining soil productivity, controlling erosion and sedimentation, stabilizing rivers banks, and building carbon stocks. In addition, it will contribute to ecosystem-based management by implementing a landscape conservation strategy wherein forest and freshwater ecosystems will be managed sustainably in the production lands surrounding protected areas and KBAs. Finally, the project will contribute to the equitable sharing of benefits from biodiversity by promoting sustainable forest production and forest conservation equally among landowners and local community members, including women and indigenous peoples.

- Belize is also party member of the UNCCD, ratified on July 23, 1998. Belize’s First National Action Programme (NAP) of the United Nations Convention to Combat Desertification is currently being drafted. Although the final draft of the NAP has not yet been made public, we had access to a brief summary of it. The project will address causes of land degradation in Belize as outlined in the NAP, such as: a) deforestation with direct risk of erosion, soil structure deterioration, and loss of soil productivity; b) non-sustainable farming, including farming on steep slopes, which leads to increased use and dependence of fertilizers, erosion, and further soil degradation as well as reduced water quality through runoff; c) livestock over-grazing, which leads to soil compaction, erosion, leaching of nutrients, and paves the way for invasive weeds; and d) logging, which promotes soil erosion and creates access to illegal farming through the construction of access roads.

- The project will be aligned with Belize’s National Action Programme (NAP)/UNCCD currently under development and which will identify factors contributing to desertification and the development of practical measures to combat desertification and mitigate the effects of drought. The project is also aligned with the Nationally Determined Contribution (NDC) under the United Nations Framework Convention on Climate Change (UNCCC), and which has among its priorities to design and implement an integrated water resources management (IWRM) programme in watersheds; enhance protection of water catchment (including groundwater resources); develop water conservancy management systems; conduct water resource assessment (especially groundwater); develop flood controls and drought monitoring; strengthen the human resource capacity in the water sector and strengthen the compliance monitoring capacity of staff; undertake water policy reform; adopt better soil and water management agricultural practices; and maintain and restore healthy forest ecosystems by sustainable forest management, increasing afforestation and reforestation in order to increase the resilience of human communities. The project will address all these priorities, particularly in the Belize River watershed and the production landscapes within, which have been prioritized for project implementation. In addition, the project responds to the National Climate Change Policy, Strategy and Action Plan (NCCPSAP), 2015-2020, which provides policy guidance for the development of an appropriate administrative and legislative framework, in coordination with other sectoral policies, for a low-carbon development path for the country. In addition, the NCCPSAP also seeks to encourage the development of the country’s NDC and to communicate it to the UNFCCC.

- In addition, the project is consistent with the Growth and Sustainable Development Strategy (2016–2019). The Strategy adopts an integrated, systemic approach and encompasses medium-term economic development, poverty reduction and longer- term sustainable development issues. This planning document also provides detailed guidance on priorities and on specific actions to be taken during the planning period, including actions that contribute to longer term development objectives beyond 2019. Similarly, the project is consistent with The National Development Framework for Belize: Horizon 2030, which has as one of mains components the responsible stewardship of the environment integrating environmental sustainability into development planning, including planning for climate change and its effects.

- Finally, the project is also coherent with Belize’s Rural-Area Based Development Strategy, which aims to make rural areas a more attractive place to live and work in and where people can find a better life by providing them with the means to generate their own development, to adapt to new economic circumstances, and to be valued as they deserve to by all of society. It also has the goal of promoting the participation of the private production sector and of civil society in general through leadership training for the integrated and sustainable management of rural territories.

C.  Describe the budgeted m &e plan:  The budgeted M&E plan is included in Section VIII: Monitoring and Evaluation (M&E) Plan of the GEF-UNDP Project Document.

PART iII:  certification by gef partner agency(ies)

- GEF Agency(ies) certification

This request has been prepared in accordance with GEF policies and procedures and meets the GEF criteria for CEO endorsement under GEF-6.

| Agency Coordinator, Agency Name | Signature | Date (MM/dd/yyyy) | Project Contact Person | Telephone | Email Address |
| --- | --- | --- | --- | --- | --- |
| Pradeep Kurukulasuriya, United Nations Development Programme |  | 05/29/2019 | Santiago Carrizosa, Senior Technical Advisor, EBD | +507 302-4510 | Santiago.carrizosa@undp.org |

- GEF_CEOENDR_60

ANNEX A:  PROJECT RESULTS FRAMEWORK (either copy and paste here the framework from the Agency document, or provide reference to the page in the project document where the framework could be found).

| This project will contribute to the following Sustainable Development Goal (s): Goal 1 – End poverty in all its forms everywhere; Goal 5 – Achieve gender equality and empower all women and girls; Goal 6 – Ensure access to water and sanitation for all; Goal 8 – Decent work and economic growth; and Goal 15 – Sustainably manage forests, combat desertification, halt and reverse land degradation, halt biodiversity loss. |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| This project will contribute to the following country outcome included in the UNDAF/Country Programme Document (United Nations Multi-Country Sustainable Development Framework in the Caribbean): Inclusive and sustainable solutions adopted for the conservation, restoration and use of ecosystems and natural resources. |  |  |  |  |  |
| This project will be linked to the following output of the UNDP Strategic Plan: Output 1.3: Solutions developed at national and sub-national levels for sustainable management of natural resources, ecosystem services, chemicals and waste. |  |  |  |  |  |
|  | Objective and Outcome Indicators | Baseline | Mid-term Target | End of Project Target | Data Collection Methods and Risks/Assumptions |
| Project Objective: To mainstream biodiversity conservation and sustainable land/water management into production landscapes in Belize | Indicator 1 (GEF7 Core Indicator 4): Area (hectares) of landscapes under improved practices (sum of Indicators 6, 9, and 10 below) | 0 ha | 27,250 ha | 50,000 ha | Updated GEF7 Core Indicator 4 Project technical reports |
|  |  |  |  |  | Risks: Project team fails to engage stakeholders to adopt improved practices Assumptions: Interest from the central government, private sectors and farmers in biodiversity conservation and sustainable land/water management |
|  | Indicator 2 (GEF7 Core Indicator 11): Number of direct beneficiaries disaggregated by gender as co-benefit of GEF investment | 0 | Male: 350 Female: 150 | Male: 1,250 Female: 450 | Farmer and household surveys/interviews (unstructured and/or semi structured) Updated Gender Action Plan Updated GEF7 Core Indicator 11 |
|  |  |  |  |  | Risks: Landowners are reluctant to incorporate SLM and biodiversity conservation objectives in production landscapes Assumptions: Government officials and farmers and producer organization in the prioritized watershed will be actively engaged in SLM and biodiversity conservation activities. |
| Component 1: Enabling environment (policies, financial mechanisms, and institutional capacities) for delivering multiple global environmental benefits (GEBs) through the sustainable management of production landscapes Outcome 1.1: Strengthened governance and financial structure for the conservation of biodiversity and ecosystem services through sustainable land (SLM)/water management in production landscapes Outcome 1.2: Increased ability of the government to implement strategies for conservation and SLM/water management in production landscapes | Indicator 3: Number of updated and drafted laws and policies | # 0 | # 2 # - Draft revisions of: a) EIA Regulations; and b) NIWR Act | 6 - Laws and policies updated: a) National Lands Act; b) National Utilization Act; c) EIA Regulations ; d) NIWR Act; e) Fiscal Incentive Act) - Integrated Water Resources Management Policy drafted | Document content analysis Drafts of update legislation Official gazette Draft of policies Final Policy endorsed by Cabinet |
|  |  |  |  |  | Risks: Project team and Implementing Partner fail to engage key project partners Assumptions: Continued political will to strengthen strengthened governance biodiversity and ecosystem services through SLM/water management in production landscapes |
|  | Indicator 4: Change in government and private funding aligned to support sustainable production in priority sectors (agriculture, tourism, forestry, and urban development and industry) | - GOB: US$25.32 million (BZ$51 million) - Private sector: US$56.37 million (BZ$113.5 million) | - GOB: US$29.311 million USD (BZ$58.65 million) (increase by 15%) - Private sector: US$61.74 million (BZ$124.3 million) (increase by 6%) | - GOB: US$32.91 million (BZ$66.3 million) (increase by 30%) - Private sector: US$65.31 million (BZ$131.5 million) (increase by 14%) | Government budgets and accounts Private sector budgets and accounts |
|  |  |  |  |  | Risks: Target to may not be achieved because of decreasing national budgets and unstable markets Assumptions: There is interest by the Government and the private sector to investment in SLM/water management |
|  | Indicator 5: Change in the capacity of key agencies to promote biodiversity conservation, integrated watershed management, SLM, and building resilience to climate change as measured through GEF/UNDP Capacity Development Scorecard. | Department of Environment/MAFFESD: 37% Hydrology Unit/MNR: 38% Department of Forestry/MAFFESD: 44% Department of Fisheries/MAFFESD: 7% University of Belize (UB)-Natural Resource Management: 63% Sustainable Development Unit/MAFFESD: 47% Department of Agriculture/MAFFESD: 44% Lands and Survey Department/MNR: 35% MNR Policy Unit: 33% Department of Rural Development/MLLGRD: 58% | Department of Environment/ MAFFESD: 52% Hydrology Unit/MNR: 53% Department of Forestry/MAFFESD: 59% Department of Fisheries: 22% UB-Natural Resource Management/MAFFESD: 78% Sustainable Development Unit: 62% Department of Agriculture/MAFFESD: 59% Lands and Survey Department/MNR: 50% MNR Policy Unit: 48% Department of Rural Development MLLGRD: 73% | Department of Environment/ MAFFESD: 67% Hydrology Unit/MNR: 68% Department of Forestry/MAFFESD: 74% Department of Fisheries/MAFFESD: 37% UB-Natural Resource Management: 93% Sustainable Development Unit/MAFFESD: 77% Department of Agriculture/MAFFESD: 74% Lands and Survey Department/MNR: 65% MNR Policy Unit: 63% Department of Rural Development MLLGRD: 88% | Results of reapplied Capacity Development Scorecard: focal group interviews |
|  |  |  |  |  | Risks: Knowledge drain and implementation capacity constraints at government due to the staffing limitations Project team and Implementing Partner fail to engage key project partners Assumptions: Continued political will to strengthen governance of biodiversity and ecosystem services through SLM/water management in production landscapes |
| Outputs: 1.1. Revised and harmonized policies and legislation for riparian forest protection and management (National Lands Act and National Lands Utilization Act), water management and irrigation (National Integrated Water Resources Act), environmental management, river discharges, and water quality (Environmental Impact Assessment Regulations under the Environmental Protection Act, NIWR Act and Fiscal Incentives Act) and integrated management of watersheds (Integrated Watershed Management Policy) results in: a. Clarification of agencies jurisdictions/ mandates regarding integrated watershed management. b. National coordinating framework for integrated watershed management defined and enabled. c. Protocols for inter-institutional coordination to enforce norms and establish penalties related to the clearing of riparian forests, discharges to water bodies, illegal water withdrawal, and mining in rivers. 1.2. Improved monitoring and enforcement of legislation. 1.3. Diversified financial incentives developed and established through a participatory process (including women, indigenous peoples, and other vulnerable groups) to implement biodiversity-friendly production practices and sustainable water management and use strategies. 1.4. Expanded information management systems (e.g., hydrology, agriculture (BAIMS, GSMU, etc.), includes mechanisms and protocols such as databases and online map viewer for data gathering, access and information sharing between institutions to strengthen biodiversity conservation, land/water resource management, and sustainable agricultural management. 1.5. Multi-tiered training program to build (public, communities, and private) in biodiversity conservation, integrated watershed management, SLM, and building resilience to climate change. |  |  |  |  |  |
| Component 2: Delivering multiple GEBs through sustainable production and improved value chains for key agricultural and forest products from the Belize River watershed Outcome 2.1: Multiple GEBs delivered Outcome 2.2: Increased area of agriculture and forest production under sustainable practices Outcome 2.3: Accessible markets for producers implementing sustainable practices | Indicator 6 (GEF7 Core Indicator 4.1): Area (ha) of landscape management tools that promote connectivity and biodiversity conservation. | 0 | 2,250 ha | 4,500 ha (landscape management tools; i.e., biological micro-corridors, agroforestry, forest enrichment, live fences, windbreaks, and hedges) | Field reports/field verification Project reports Updated GEF7 Core Indicator 4.1 |
|  |  |  |  |  | Risks: Extreme climatic events and hazards (e.g. hurricanes, tropical storms, prolonged drought) jeopardize the measures introduced Assumptions: Sampling efforts are optimal |
|  | Indicator 7: Population densities of key indicator species jaguar [Panthera onca], white-lipped peccary [Tayasu peccary]), Black howler monkey [Alouatta pigra], tapir [Tapirus bairdii] in riparian zones/forest patches/corridors in production lands and KBAs | Jaguar [Panthera onca]: 6-7 individuals/100 km2 (data for the Belize Central Corridor) White-lipped peccary (Tayasu peccary): 1.09 individuals/km2 Howler monkey (Alouatta pigra): 32 individuals/km2 (Community Baboon Sanctuary, Belize River Valley) Tapir (Tapirus bairdii): population study currently underway (suggested estimate: 8 individuals / 10 km2) (Species densities to be verified during the project inception phase) | Maintained levels of density | Maintained levels of density | Transect surveys/visual counts, spot mapping, camera trapping Field reports Project reports |
|  |  |  |  |  | Risks: Landowners/farmers are reluctant to adopt best management practices that favor biodiversity Assumptions: Environmental/climate variability within normal range. Sampling efforts are optimal |
|  | Indicator 8 (GEF7 Core Indicator 3): Area (ha) of land restored | Riparian forests: 0 ha Groundwater recharge areas: 0 ha | Riparian forests: 250ha Groundwater recharge areas: 100 ha | Riparian forests: 750 ha Groundwater recharge areas: 300 ha | Field/plot surveys Project reports Updated GEF7 Core Indicator 3 |
|  |  |  |  |  | Risks: Increase in riparian forest protection not achieved Assumptions: Interest among landowners and authorities to protect riparian zones |
|  | Indicator 9 (GEF7 Core Indicator 4.1): Area of landscapes under sustainable agriculture with biodiversity benefits | 0 ha | 10,675 ha | 30,500 ha | Field and farmer/plot surveys Updated GEF7 Core Indicator 4.1 |
|  |  |  |  |  | Risks: Changes to the use of lands and resources Assumptions: There is willingness by farmers to incorporate environmental sustainability criteria as part of their production activities. Environmental/climate variability within normal range. Sampling efforts are optimal |
|  | Indicator 10 (GEF7 Core Indicator 4.3): Area of landscapes under sustainable land management in production systems | 0 ha | 5,250 ha | 15,000 ha | Field and farmer/plots surveys Updated GEF7 Core Indicator 4.3 |
|  |  |  |  |  | Risks: Changes to the use of lands and resources Assumptions: There is willingness by farmers to incorporate environmental sustainability criteria as part of their production activities |
|  | Indicator 11: Number of products with enhanced value chains placed in markets. | 0 | 3 under development - Cohune Oil Production (small scale): training and technical assistance provided for sustainable production, adding value to products, and marketing - Livestock (small and medium-sized farmers): training and technical assistance provided for sustainable production and marketing - Sugar Cane (small and medium-sized farmers; and large scale/Santander Farms): training and technical assistance provided for sustainable production and marketing | 3 - Cohune Oil production (small scale) with new products developed (e.g., body oils and soaps) and products sold into at least one export market - Sustainable Livestock products (small-scale producers) and products sold into at least one national or export market - Sustainable Sugar Cane (small and medium-sized farmers; and large scale/Santander Farms) and product sold into at least one export market | Field reports Belize Agriculture Information Management System (BAIMS) Reports Business agreements/sale receipts (document analysis) |
|  |  |  |  |  | Risks: Limited benefits for the producers who adopted environmentally friendly practices Assumptions: Markets available |
|  | Indicator 12: Farmers /producers’ net income (differentiated by gender) from sustainable products (cohune oil, livestock, and sugarcane) with enhanced value chains placed in markets by project end. | Net Income men: $ X Net income women: $ X Net income of at least 80% of participating farmers (male/ female) documented at project inception (year 1) | Net Income men: $X + 20% Net income women: $X + 20% Participating farmers show at least 20% increase based on year 1 estimate. | Net Income men: $X + 40% Net income women: $X + 40% Participating farmers show at least 40% increase based on year 1 estimate. | Belize Agriculture Information Management System (BAIMS) Reports Updated Gender Action Plan Household surveys/interviews (unstructured and/or semi structured) |
|  |  |  |  |  | Risks: Limited benefits for the producers who adopted environmentally friendly practices Women participation is hindered by social and cultural preferences for women to maintain household. Assumptions: Markets available. Females and males willing to adopt improved practices Proposed practices are cost-effective. Propose practices have low barrier for uptake, especially among female farmers. |
| Outputs: 2.1. Landscape management tools used in priority areas for biodiversity conservation. a. Conservation agreements with participating producers/farmers used for establishing landscape management tools (i.e., biological micro-corridors, agroforestry, forest enrichment, live fences, windbreaks, and hedges). b. Rehabilitation and management strategies for riparian forests implemented alongside programme for participatory soil management to reduce erosion and improve water quality. c. Improved forest monitoring system for enhanced land-use change monitoring within the BRW. 2.2. Water Master Plan for the BRW developed through a participatory process allows integrated management for sustainable land and water resources use: a. Critical groundwater recharge areas identified and mapped and delineated based on extent, quantity, and quality, recharge rate, etc. b. Baseline study of supply and demand and the quality of hydrological resources supports decision making to allocate water for sustainable production and irrigation. c. Optimized hydrological monitoring network (meteorological stations, wells, flow and stage gauges, etc.) provides data for sustainable water management and designing protection measures including flood and drought forecasting. d. Operationalization of funding strategy developed and mechanisms for implementation defined, including collection of fees for water use, for the development and implementation of Water Resource Master Plan and Water Quality Control Plan jointly between the NIWRA/MNR, DOE, and water users, following a water use data analysis. 2.3. At least two incentives (e.g., annual per-hectare payments in return for maintaining forest cover, state-funded results-based payments designed with environmental and socioeconomic targets, carbon sequestration certification) to promote sustainable agriculture and forest production piloted. 2.4. Gender responsive extension work program; to include training for small and large producers, including women and vulnerable groups, to implement sustainable production, post-production and livelihood practices; delivered through a capable Extension Service of the Department of Agriculture, the University of Belize, Galen University, and UNDP's Green Commodities Programme improves production, enhances value chains for key products, and builds awareness among small-scale and large-scale producers about markets for sustainable products. 2.5. Business management capacity of producers (including women) to implement sustainable practices improved through targeted training and technical support for agrobusiness development and private and cooperative support services. 2.6. Awareness program for producers, technicians, and government officials in the production sector (agriculture, tourism, forestry, and urban development and industry) informs and builds capacity to sustain and maintain the environmental and socioeconomic benefits of sustainable production practices and the availability of financial incentives and on-going programs to facilitate implementation. 2.7. Participatory monitoring program assesses the delivery of GEBs: biodiversity conservation and integrated watershed management to improve hydrological functions and services for agro-ecosystem productivity. 2.8 Micro-granting scheme with provides direct incentives/ investments to local communities participating in riparian restoration, conservation agreements and sustainable production. |  |  |  |  |  |
| Component 3: Knowledge Management and Learning Outcome 3.1: Best practices and lessons are accessed and applied in other production landscapes and watersheds in the country and internationally. | Indicator 13: Number of documents on successful farmers’ and community experiences, and practices about integrating SLM and biodiversity conservation practices, and gender mainstreaming in the BRW are disseminated in-country and internationally | 0 | 5 | 10 | Applied community-based Research Reports Visual and other documentation of environmentally appropriate production practices Annual Community of Practice Proceedings and Reports Monitoring reports Documented project-specific lessons learned |
|  |  |  |  |  | Risks: NA Assumptions: Wide-ranging and timely dissemination of project results and lessons learned. Communities supportive and willing to participate in research and knowledge production. |
| Outputs: 3.1. Gender sensitive/ gender responsive programmes/ activities promoted through project frameworks. 3.2. Experiences, best practices, and lessons learned about biodiversity conservation and SLM/water management in production landscapes captured, systematized and made available through various platforms for public and private stakeholders for use in other production landscapes and watersheds in the country, informing future projects and strategies |  |  |  |  |  |

ANNEX B:  RESPONSES TO PROJECT REVIEWS (from GEF Secretariat and GEF Agencies, and Responses to Comments from Council at work program inclusion and the Convention Secretariat and STAP at PIF).

| Reviewer’s comments | Responses |  |  | Reference in CEO Endorsement Document |
| --- | --- | --- | --- | --- |
| Secretariat Comment at CEO Endorsement (FSP)/Approval (MSP): June 2, 2017 |  |  |  |  |
| 5. Are the components in Table B sound and sufficiently clear and appropriate to achieve project objectives and the GEBs? During PPG, it will remain important that as a primarily biodiversity project - the results, activities and justification keeps global biodiversity benefits in mind. For example, a payments for ecosystem services program should provide benefits for activities with biodiversity impact not simply groundwater recharge. This could take place through the location of farms in corridors or PA buffer zones, types of activities supported, etc. Please also include a map of the project areas and KBAs (as there are a number in the region). | As suggested, the project site prioritization was done considering how activities at the farm level will contribute to biodiversity conservation, in particular enhancing connectivity between PAs/KBAs through the implementation of landscape management tools (i.e., biological micro-corridors, agroforestry, forest enrichment, live fences, windbreaks, and hedges) and improve habitat for key wide-ranging species (e.g., the jaguar, the Central American tapir, and the white-lipped peccary). In addition, the project will support sustainable production systems to reduce pressures to riparian forest (deforestation) and freshwater ecosystems (pollution of rivers and wetlands). To support these efforts, financial incentives such as Fair Trade mechanisms, ecotourism certification, and carbon credits will be made available. As suggested, a map of the KBAs in the BRW is included in Annex N: Target Landscape Description, of the GEF-UNDP Project Document. The project will project focus on the area in the Middle BRW portion of the Lower BRW. The project will contribute to building connectivity between KBAs such as the Rio Bravo Conservation and Management Area, the Maya Mountain Massif, and the Crooked Tree and associated wetlands. |  | GEF-UNDP Project Document, Annex N: Target Landscape Description |  |
| STAP Scientific and Technical screening of the Project Identification Form (PIF). Date of screening: May 14, 2017 |  |  |  |  |
| 1. STAP notes some bold expectations under Component 1 with regards to proposed changes in governance structures, government agency mandates, programming, policies, and legislation. This part of the project relies heavily on the collaboration and continued engagement of multiple government agencies, and the project proponents should be ready to mitigate the risks associated with a failure to achieve these deliverables. |  | The risk of not achieving the policy and institutional reforms proposed has been incorporated into the project’s risk management strategy. The project was designed with the active involvement of government agencies who will participate of the proposed reform. An inter-agency cooperation will be promoted through the project, including the signing of a agreement between the MNR and MAFFESD that will allow for joint programming, resource-sharing, information exchange, etc. Representatives from the different government agencies involved in the project will be invited to participate in the Project Board to facilitate cooperation, decision making, and project follow-up. The UNDP Country Office will periodically assess progress in mitigating this risk as the UNDP ATLAS risk log. | GEF-UNDP Project Document, Annex H: UNDP Risk Log |  |
| 2. It will be important to substantiate various targets presented in the PIF without any justification (e.g. Outcome 2(e) and paragraph 31: how was the 20% erosion reduction value from a participatory program for sustainable soil management derived, and how will it be monitored? Similarly, Outcome 2(d) and paragraph 31: how was the target to rehabilitate at least 50% of key recharge areas determined, and is it feasible?). |  | The 20% erosion reduction value from a participatory program for sustainable soil management has been removed from the final project design due to the complexity of targeting this goal. Instead, the project will focus on reducing the rate of bank failure within the middle and lower sections of the BRW. This was identified as a related problem that resulted from poor land/farm management during the baseline studies that were conducted as part of the PPG phase. The target to rehabilitate at least 50% of key groundwater recharge areas was modified to 300 ha of groundwater recharge areas/wetlands restored. This new goal was determined based on an assessment for the identification, protection, and recovery of groundwater recharge areas that was conducted during the final formulation process. | CEO Endorsement Request: Table B; Annex E: GEF 7 Core Indicator Worksheet |  |
| 3. More detail is required on the strategy to identify and promote suitable SLM practices to manage erosion and enhance productivity of agricultural land. The World Overview of Conservation Approaches and Technologies WOCAT is a useful resource: WOCAT manages a global database on SLM approaches and technologies, which is recommended by the UNCCD. Further information about the database can be found at: https://qcat.wocat.net/en/wocat/ |  | The process of identifying SLM approaches and measures was conducted through a participatory process in which multiple farmers were consulted about existing land use practices and needs. In addition, best practices from past and ongoing initiatives were identified. The implementation of best SLM practices in Belize has the following common characteristics: a) Inclusiveness – include all stakeholders in the landscape or watershed rather than only the poor farmers in the target areas; b) Preventative versus restorative measure – preventative measures are generally more effective and cost-efficient than curative activities, especially when these are based on land use capacity and income-generating potential; c) Rights and values of resource users – farmers and resource users should be recognized as having the capacity of deciding what is good for them in the light of their resources, priorities, and values, thus every opportunity should be given for them to build on such; and d) Prioritization of sites for intervention – efforts should be made in areas that have common threats to the landscape/watershed, where the chances of success are high and can be cost-effective and where the impact (sustainability) will be apparent. Suitable SLM practices to manage erosion and enhance the productivity of agricultural land that will be promoted by the project are the following: a) Development of a manual on SLM – this manual will establish guidelines, standards based on different land use types, approaches to monitoring, etc., and will be developed using a participatory process. The guidelines will reflect the fact that as SLM can lead to increased productivity and income generation, such as in the livestock sector, this can also become a perverse incentive (i.e., leading to more clearing of land). b) Capacity building: local capacity-building workshops will be held in the targeted areas for multiple stakeholders. Exchange field visits both locally and regionally (Central America) will be undertaken. Locally, in the Maya Mountain North Forest Reserve where the Ya’axché Conservation Trust has been working with farmers to reduce forest and land degradation through organic agroforestry. Regionally, visits will be undertaken to Centro Agronómico Tropical de Investigación y Enseñanza (CATIE) in Costa Rica to observe work being done in managing livestock as part of wider agro-ecological agriculture and/or to the Fundación Hondureña de Investación Agrícola (FHIA). c) Integrate SLM into livestock farms to deliver GEBs and on-farm benefits such as reduced erosion and productivity. This will include incorporating shade trees (e.g., Bay Cedar [Guazuma umifolia] and Red Ramon [Trophis racemosa]) and fodder banks; d) Use of multi-layered green fencing. e) Establishment of Organic Agroforestry Pilots, including various mixed cropping systems (e.g., coconut [Cocos nucifera] with cashew [Anacardium occidentale], and soursop [Annona muricata] with oranges [Citrus sinensis], and possibly cacao [Theobroma cacao], which is commonly used in southern Belize where it is cultivated as an under-story crop). f) Climate-smart vegetable production for SLM. g) Designing of a sustainable production programme incorporating the following elements: i) integrated pest management, ii) a bio-fertilizer programme, e.g. use of bokashi composting, and ii) use of cover crops as indicated above. h) Formulation, negotiation, and signing of voluntary Conservation and Sustainable Production Agreements with farmers to implement SLM practices. | GEF-UNDP Project Document, Section V: Results and Partnership. |  |
| 4. STAP welcomes a formal component on knowledge management and learning. However, at this stage, the component appears particularly weak and significantly more thought should be given in developing it. STAP encourages the project developers to consult its ongoing advice on Knowledge Management to the GEF at http://www.stapgef.org/knowledge-management-gef as well as some of the knowledge management tools that are currently recommended – see, for example http://www.knowledge-management- tools.net/knowledge-management-systems.html. |  | Thank you for suggesting these Knowledge Management resources for GEF interventions. The project Knowledge Management strategy includes the use of platforms such as networks such as the Conference of the Parties of the CBD, the Panorama Portal “Solutions for a Healthy Planet,” and Good Growth Partnership (the latter with support from the UNDP's Green Commodities Programme). In addition, south-south knowledge exchange will be promoted with cooperation from the other countries in the region that are implementing similar initiatives—for example Colombia, Costa Rica, Grenada, Guatemala, Honduras, and Panamá. South-south exchanges will also be promoted as part of the multi-tiered training program to be implemented under Component 1. Also, synergies and opportunities for learning from experiences gained within and outside of the GEF partnership will be promoted; the related projects are indicated in the UNDP Project Document. In addition, a key best practice in the management of landscapes/watersheds would be to provide opportunities for all stakeholders/rights-holders to provide meaningful inputs in the planning, monitoring, and overall oversight of activities in the area. To this end, each year the project team will plan and undertake an annual conference to discuss issues in the watershed, document challenges, etc. The project’s Knowledge Management strategy also focuses on systematization as a way to document project experiences and lessons learned for sharing with project stakeholders and others. The project Knowledge Management strategy will be implemented through Component 3. | GEF-UNDP Project Document, Section V: Results and Partnership. |  |
| Comments submitted by council members on the GEF November 2017 Work Program |  |  |  |  |
| Germany |  |  |  |  |
| The proposal is very ambitious in terms of its objectives, it tries to combine many goals in a difficult area where human pressure on the environment is quite high. We suggest further sharpening the focus on biodiversity outcomes and if possible adjusting the level of ambition of objectives, indicators and co-funding |  | Although the overall structure of the project components remains the same, during the final project design, changes were made to some of the project outputs and indicators based on baseline and feasibility assessments. These changes can be observed in Table B and Section A/A.1. A.1. Project Description/3) The proposed alternative scenario, GEF focal area strategies, with a brief description of expected outcomes and components of the project, of this CEO Endorsement Request. Regarding the co-financing, please refer to Table C: Confirmed Sources of Co-Financing for the Project by Name and by Type. | CEO Endorsement Request: Table B and Section A/A.1. A.1. Project Description/3) The proposed alternative scenario, GEF focal area strategies, with a brief description of expected outcomes and components of the project; Table C: Confirmed Sources of Co-Financing for the Project by Name and by Type. |  |
| The projects wants to promote products (sugarcane, banana) with large-scale agricultural producers with enhanced value chain benefits in markets. However, the large-scale agribusiness has been a main driver of deforestation in Belize and is the highest threat to the conservation of the Belize Central Corridor (together with the deforestation in and outside protected areas by small-scale farmers). We ask the final proposal to elaborate clearly how the support of agroindustrial production as lined out in the proposal (“value chains”) would avoid further deforestation and ensure positive biodiversity impacts. |  | The project will engage large farms (e.g., Santander Farms Ltd., Big Falls, etc.) through the following outputs: − Outputs 1.3 and 2.3: The application of financial incentive mechanisms that will serve as the vehicle for large producers within the landscape to incentivized then to effectively engage in sustainable production practices and watershed management. − Output 2.1: The large farms within the landscape are targeted to participate in conservation agreements for the purpose of setting aside or protecting minimally disturbed priority areas, as well as participate in practices that encourage restoration, effective water management, protection of micro-corridor systems, and an improved forest monitoring system for changes in land use within the Belize River Watershed (BRW). As mentioned in paragraph 61 of the UNDP-GEF Project Document, the use of conservation agreements to engage large private-sector holdings such as Santander Farms Ltd. and Big Falls farms is critical for maintaining corridor connectivity and ecosystem functionality within the BRW. The White-Water Lagoon and its surroundings, which was determined to be an ecologically sensitive area encompassing approximately 121 ha, is owned by Santander Farms Ltd. The Big Falls Farm comprises three parcels of land totaling 14,569 ha and is integral for the maintenance of corridor connectivity within the Belize Wester Biological corridor. The project provides the opportunity to work with the landowners to place the forested areas under some type of easement or trust that allows only sustainable usage. In addition, large farming systems are also associated with contributing small farms; as such, the large farms will assist in promoting the adoption of best practices among its contributing farms. The project will support best sugar cane production practices, which may include improved water management for irrigation; organic fertilization, including using leftover sugar cane straw as ground cover; and reduced use of agrochemicals. In addition, owners of sugar cane farms supported by the project will implement activities that result in the conservation and rehabilitation of riparian forests and other ecologically sensitive areas (i.e., water recharge areas), thereby contributing to maintaining and enhancing ecosystem connectivity, providing biodiversity habitat, reducing soil erosion, and improving surface water and groundwater quality. These best practices will be documented and disseminated as part of the knowledge management plan under Component 3. This will include sharing information with the Ministry of Agriculture, Fisheries, Forestry, Environment, and Sustainable Development (MAFFESD) and famers’ associations such as Orange Walk and the Corozal Cane Farmers Association, both of which represent many of the 5,300 cane farmers that produce sugar cane in northern Belize. The durability of interventions such as tree planting and setting aside of steep slopes will be ensured by framing these efforts within a national strategy for riparian forest restoration and protection. Currently this strategy is framed within the national framework for resource management. As such, the Forestry Department will be strengthened to execute its mandate for the protection and restoration of forests in the country. The project supports the emplacement of key elements of programme sustainability, such as establishing community and national nurseries, as well as supporting efforts to engage communities in decentralized efforts for protection. It should be noted that the commitments referenced in the project are expected to be legally binding, as the government of Belize has agreed to formally adopt these as tools for effective resource management. Conservation agreements will be legislated through amendments to the regulations, which enable the existing Forest Act and the Environmental Protection Act. | GEF-UNDP Project Document, Section V: Results and Partnership. |  |
| Germany also highly recommends including a more detailed overview of the impressive amount of co-funding from Belize. It is of fundamental importance to ensure that resources reserved for the proposed project do not constrain the effective implementation of ongoing conservation efforts |  | A breakdown of the confirmed co-financing is presented in Table C of this CEO Endorsement. Copies of the co-financing are included as part of the submission package to the GEF, where it is specified how the co-financing will be used. In addition, as part of the financial planning and management of the project, the UNDP Country Office will monitor the co-financing contributions to the project to ensure the proposed project does not constrain the effective implementation of ongoing conservation efforts, among other risks. | CEO Endorsement. Table C: Confirmed Sources of Co-Financing for the Project by Name and by Type. Copy Cofinancing letters. GEF-UNDP Project Document, Section X: Financial Planning and Management |  |
| Furthermore, Germany recommends building on the experiences and seeking cooperation with development partners such as GIZ who has been working in the area in the past 6 years. The final proposal should elaborate how cooperation with these actors is envisaged. |  | Meetings were held with Mr. Jan Meerman, Technical Advisor, Biodiversity Monitoring and Climate Change in the Selva Maya Region (GIZ). Synergies were built between the GIZ project and the project proposed herein. | GEF-UNDP Project Document, Section V: Results and Partnership; Annex L: List of people consulted during project development |  |
| Secretariat Comment at CEO Endorsement/Approval: July 11, 2019 |  |  |  |  |
| Is the project structure/ design appropriate to achieve the expected outcomes and outputs? No, the project is well structured overall. However, it would be good to have some more information on how the project will be engaging large farms (related to Germany's comment). Many of the activities seem to be tailored to small holders. Also, sugar is not usually identified as a crop for sustainability activities. How will the project work on it and how will lessons be documented? It would also be helpful to have more information how the project will ensure the durability of interventions such as tree planting and setting aside of steep slopes. By creating agreements that may not have continuity, there can be an issue that activities previously done for no external benefit become something farmers will only do when they receive a benefit. |  | The project will engage large farms (e.g., Santander, Big Falls, etc.) through the following outputs: - Outputs 1.3 and 2.3: The application of financial incentive mechanisms that will serve as the vehicle for large producers within the landscape to incentivized then to effectively engage in sustainable production practices and watershed management. - Output 2.1: The large farms within the landscape are targeted to participate in conservation agreements for the purpose of setting aside or protecting minimally disturbed priority areas, as well as participate in practices that encourage restoration, effective water management, protection of micro-corridor systems, and an improved forest monitoring system for changes in land use within the Belize River Watershed (BRW). As mentioned in paragraph 61 of the UNDP-GEF Project Document, the use of conservation agreements to engage large private-sector holdings such as Santander Farms Ltd. and Big Falls farms is critical for maintaining corridor connectivity and ecosystem functionality within the BRW. The White-Water Lagoon and its surroundings, which was determined to be an ecologically sensitive area encompassing approximately 121 ha, is owned by Santander Farms Ltd. The Big Falls Farm comprises three parcels of land totaling 14,569 ha and is integral for the maintenance of corridor connectivity within the Belize Wester Biological corridor. The project provides the opportunity to work with the landowners to place the forested areas under some type of easement or trust that allows only sustainable usage. In addition, large farming systems are also associated with contributing small farms; as such, the large farms will assist in promoting the adoption of best practices among its contributing farms. The project will support best sugar cane production practices, which may include improved water management for irrigation; organic fertilization, including using leftover sugar cane straw as ground cover; and reduced use of agrochemicals. In addition, owners of sugar cane farms supported by the project will implement activities that result in the conservation and rehabilitation of riparian forests and other ecologically sensitive areas (i.e., water recharge areas), thereby contributing to maintaining and enhancing ecosystem connectivity, providing biodiversity habitat, reducing soil erosion, and improving surface water and groundwater quality. These best practices will be documented and disseminated as part of the knowledge management plan under Component 3. This will include sharing information with the Ministry of Agriculture, Fisheries, Forestry, Environment, and Sustainable Development (MAFFESD) and famers’ associations such as Orange Walk and the Corozal Cane Farmers Association, both of which represent many of the 5,300 cane farmers that produce sugar cane in northern Belize. The durability of interventions such as tree planting and setting aside of steep slopes will be ensured by framing these efforts within a national strategy for riparian forest restoration and protection. Currently this strategy is framed within the national framework for resource management. As such, the Forestry Department will be strengthened to execute its mandate for the protection and restoration of forests in the country. The project supports the emplacement of key elements of programme sustainability, such as establishing community and national nurseries, as well as supporting efforts to engage communities in decentralized efforts for protection. It should be noted that the commitments referenced in the project are expected to be legally binding, as the government of Belize has agreed to formally adopt these as tools for effective resource management. Conservation agreements will be legislated through amendments to the regulations, which enable the existing Forest Act and the Environmental Protection Act. | - Annex B: Responses to Project Reviews, Comments Germany - UNDP-GEF Project Document, V. Results and Partnerships |  |
| Is co-financing confirmed and evidence provided? No. The figures for the cofinancing from University of Belize are incorrect |  | Co-financing has been confirmed; total co-financing increased from USD $15,076,600 to USD $23,619,574. The additional co-financing will be invested by the Santander Sugar Group to support activities related to Outcome 2.2: Increased area of agriculture and forest production under sustainable practices, within Santander managed areas in the Belize River Watershed. The figures for the cofinancing from the University of Belize were corrected as suggested; they now indicate a total of USD $1,296,574. | C.CONFIRMED SOURCES OF CO-FINANCING FOR THE PROJECT BY NAME AND BY TYPE |  |
| Are relevant tracking tools completed? Yes. However, please provide a justification for the Rio Marker of 1 on CCA. |  | The justification for the Rio Marker of 1 on CCA is due to the following: - Through Output 1.2, the project will support the optimization of the hydrological monitoring network (e.g., meteorological stations, wells, flow and stage gauges, etc.), as well as provide related data for sustainable water management and the design of protection measures including flood and drought forecasting within the BRW. - Through Output 1.5, the project will provide training to multiple stakeholders at the national and local levels, which will focus on information sharing, stakeholder engagement, and building core capacities for resilience to climate change, among other environmental benefits. - Through Output 2.2, the project will develop a Water Master Plan for the BRW, which relies on climatological information though an optimized hydrological network capable of providing data for sustainable water management. The project will also support designing protection measures, including flood and drought forecasting within the BRW. Through Output 2.5, the project will improve the business management capacities of producers (including women) to implement sustainable production, including climate-smart agricultural practices. | - UNDP-GEF Project Document, V. Results and Partnerships |  |
| Does the project include a budgeted M&E Plan that monitors and measures results with indicators and targets? Yes. However, please provide justification for why women are only approximately a quarter of beneficiaries. |  | The both 2011 and 2018 agriculture census indicates women making up approximately 20% of the agriculture sector. The project targets women in those activities where they are most prominently represented e.g. post harvest operations. While the project expects equal representation of women in actions related to education and awareness, community led programmes such as community monitoring, community led rehabilitation efforts; the project is cognizant as to the numbers of women engaged in production systems. It is the intention of the project to ensure aggressive targeting of female producers; however, the project is unable to commit to the expansion of women producers. The project can commit to the participation of women in associated roles within the agriculture sector. | Table E.PROJECT’S TARGET CONTRIBUTIONS TO GEF 6 CORE INDICATORS |  |
| Does the project have descriptions of a knowledge management plan? Yes, it would be good to coordinate with IW projects on water management strategies and IICA on sustainable agriculture to help share lessons learned and inform project activities. |  | As suggested, the project will share information with IW projects regarding water management strategies through the GEF’s IW:LEARN program. This may include projects such as GEF ID 10172 Towards the Transboundary Integrated Water Resource Management (IWRM) of the Sixaola River Basin shared by Costa Rica and Panama, and GEF ID 9246 Integrated Environmental Management of the Río Motagua Watershed (Honduras and Guatemala). In addition, the project will build synergies with IICA so that lessons learned regarding sustainable agriculture are shared through platforms such as: a) IICA Play, an open access and innovative platform designed to access knowledge by making technical and educational content and other information related to crop production and livestock farming available to producers, researchers, students, and young professionals; and b) Warriors – the brainchild – IICA, an online discussion forum that provides a platform to raise awareness and demonstrate the pivotal role of rural women in global food production, as well as to assist in empowering them and improving their socioeconomic conditions. | - PART II: PROJECT JUSTIFICATION, A.8 Knowledge Management - UNDP-GEF Project Document, V. Results and Partnerships |  |

Annex C:  status of implementation of project preparation activities and the use of funds

A.  Provide detailed funding amount of the PPG activities financing status in the table below:

| PPG Grant Approved at PIF: 132,420 |  |  |  |
| --- | --- | --- | --- |
| Project Preparation Activities Implemented | GEF/LDCF/SCCF Amount ($) |  |  |
|  | Budgeted Amount | Amount Spent To date | Amount Committed |
| Project preparation grant to finalize the project: Integrated management of production landscapes to deliver multiple global environmental benefits | 132,420 | 96,880 | 35,540 |
| Total | 132,420 | 96,880 | 35,540 |

annex D:  calendar  of expected reflows (if non-grant instrument is used)

Provide a calendar of expected reflows to the GEF/LDCF/SCCF Trust Funds or to your Agency (and/or revolving fund that will be set up)

N/A

Annex E: GEF 7 Core Indicator Worksheet

Core Indicator 3: Area of land restored (hectares)

| Ha (expected at PIF) | Ha (expected at CEO Endorsement) | Ha (achieved at MTR) | Ha (achieved at TE) |
| --- | --- | --- | --- |
| 500 | 1,050 |  |  |

Figure at a given stage must be the sum of all figures reported under the four sub-indicators (3.1, 3.2, 3.3 and 3.4) for that stage.

3.1 Area of degraded agricultural lands restored

| Ha (expected at PIF) | Ha (expected at CEO Endorsement) | Ha (achieved at MTR) | Ha (achieved at TE) |
| --- | --- | --- | --- |
| n/a | n/a |  |  |

3.2 Area of forest and forest land restored

| Ha (expected at PIF) | Ha (expected at CEO Endorsement) | Ha (achieved at MTR) | Ha (achieved at TE) |
| --- | --- | --- | --- |
| 500 | 750 |  |  |

3.3 Area of natural grass and shrublands restored

| Ha (expected at PIF) | Ha (expected at CEO Endorsement) | Ha (achieved at MTR) | Ha (achieved at TE) |
| --- | --- | --- | --- |
| n/a |  |  |  |

3.4 Area of wetlands (including estuaries and mangroves) restored

| Ha (expected at PIF) | Ha (expected at CEO Endorsement) | Ha (achieved at MTR) | Ha (achieved at TE) |
| --- | --- | --- | --- |
| n/a | 300 |  |  |

Core Indicator 4: Area of landscapes under improved practices (hectares; excluding protected areas)

| Ha (expected at PIF) | Ha (expected at CEO Endorsement) | Ha (achieved at MTR) | Ha (achieved at TE) |
| --- | --- | --- | --- |
| n/a | 50,000 |  |  |

Figure at a given stage must be the sum of all figures reported under the four sub-indicators (4.1, 4.2, 4.3 and 4.4) for that stage.

4.1 Area of landscapes under improved management to benefit biodiversity (qualitative assessment, noncertified)

| Ha (expected at PIF) | Qualitative description at PIF | Ha (expected at CEO Endorsement) | Qualitative description at CEO ER | Ha (achieved at MTR) | Qualitative description at MTR | Ha (achieved at TE) | Qualitative description at TE |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 606,684 | Area of the BRW, which includes protected areas | 35,000 | Area of agriculture and forest production under sustainable practices in the BRW (does not include protected areas); and area of landscape management tools that promote connectivity and biodiversity conservation. |  |  |  |  |

Add rows as needed.

4.2 Area of landscapes that meet national or international third-party certification and that incorporates biodiversity considerations

| Ha (expected at PIF) | Type of Certification at PIF | Ha (expected at CEO Endorsement) | Type of Certification at CEO ER | Ha (achieved at MTR) | Type of Certification at MTR | Ha (achieved at TE) | Type of Certification at TE |
| --- | --- | --- | --- | --- | --- | --- | --- |
| n/a | n/a | n/a | n/a |  |  |  |  |

Add rows as needed.

4.3 Area of landscapes under sustainable land management in production systems

| Ha (expected at PIF) | Description of Management Practices at PIF | Ha (expected at CEO Endorsement) | Description of Management Practices at CEO ER | Ha (achieved at MTR) | Description of Management Practices at MTR | Ha (achieved at TE) | Description of Management Practices at TE |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 15,000 | Sustainable land management in agriculture and forest production systems | 15,000 | Sustainable land management in agriculture and forest production systems |  |  |  |  |

Add rows as needed.

4.4 Area of High Conservation Value forest loss avoided

| Total Ha (expected at PIF) | Total Ha (expected at CEO Endorsement) | Total Ha (achieved at MTR) | Total Ha (achieved at TE) |
| --- | --- | --- | --- |
| n/a |  |  |  |

Figure at a given stage must be the sum of all individual PAs reported in the next table, for that stage.

| Name of HCVF | Ha (expected at PIF) | Counterfactual at PIF | Ha (expected at CEO Endorsement) | Counterfactual at CEO ER | Ha (achieved at MTR) | Ha (achieved at TE) |
| --- | --- | --- | --- | --- | --- | --- |
| n/a |  |  |  |  |  |  |

Add rows as needed.

Core Indicator 11. Number of direct beneficiaries disaggregated by gender as co-benefit of GEF investment

|  | Total number (expected at PIF) | Total number (expected at CEO Endorsement) | Total number (achieved at MTR) | Total number (achieved at TE) |
| --- | --- | --- | --- | --- |
| Women | n/a | 450 |  |  |
| Men | n/a | 1,250 |  |  |
| Total | n/a | 1,700 |  |  |

Annex F: GEF Project Taxonomy Worksheet

| Level 1 | Level 2 | Level 3 | Level 4 |
| --- | --- | --- | --- |
| Influencing models |  |  |  |
|  | Transform policy and regulatory environments |  |  |
|  | Strengthen institutional capacity and decision-making |  |  |
|  | Convene multi-stakeholder alliances |  |  |
|  | Demonstrate innovative approaches |  |  |
|  | Deploy innovative financial instruments |  |  |
| Stakeholders |  |  |  |
|  | Indigenous Peoples |  |  |
|  | Private Sector |  |  |
|  |  | Capital providers |  |
|  |  | Financial intermediaries and market facilitators |  |
|  |  | Large corporations |  |
|  |  | SMEs |  |
|  |  | Individuals/Entrepreneurs |  |
|  |  | Non-Grant Pilot |  |
|  |  | Project Reflow |  |
|  | Beneficiaries |  |  |
|  | Local Communities |  |  |
|  | Civil Society |  |  |
|  |  | Community Based Organization |  |
|  |  | Non-Governmental Organization |  |
|  |  | Academia |  |
|  |  | Trade Unions and Workers Unions |  |
|  | Type of Engagement |  |  |
|  |  | Information Dissemination |  |
|  |  | Partnership |  |
|  |  | Consultation |  |
|  |  | Participation |  |
|  | Communications |  |  |
|  |  | Awareness Raising |  |
|  |  | Education |  |
|  |  | Public Campaigns |  |
|  |  | Behavior Change |  |
| Capacity, Knowledge and Research |  |  |  |
|  | Enabling Activities |  |  |
|  | Capacity Development |  |  |
|  | Knowledge Generation | Workshop |  |
|  | Knowledge Exchange | Peer-to-peer, field visit |  |
|  | Targeted Research |  |  |
|  | Learning |  |  |
|  |  | Theory of Change |  |
|  |  | Adaptive Management |  |
|  |  | Indicators to Measure Change |  |
|  | Innovation |  |  |
|  | Knowledge and Learning |  |  |
|  |  | Knowledge Management |  |
|  |  | Innovation |  |
|  |  | Capacity Development |  |
|  |  | Learning |  |
|  | Stakeholder Engagement Plan |  |  |
| Gender Equality |  |  |  |
|  | Gender Mainstreaming |  |  |
|  |  | Beneficiaries |  |
|  |  | Women groups |  |
|  |  | Sex-disaggregated indicators |  |
|  |  | Gender-sensitive indicators |  |
|  | Gender results areas |  |  |
|  |  | Access and control over natural resources |  |
|  |  | Participation and leadership |  |
|  |  | Access to benefits and services |  |
|  |  | Capacity development |  |
|  |  | Awareness raising |  |
|  |  | Knowledge generation |  |
| Focal Areas/Theme |  |  |  |
|  | Biodiversity |  |  |
|  |  | Protected Areas and Landscapes |  |
|  |  |  | Terrestrial Protected Areas |
|  |  |  | Coastal and Marine Protected Areas |
|  |  |  | Productive Landscapes |
|  |  |  | Productive Seascapes |
|  |  |  | Community Based Natural Resource Management |
|  |  | Mainstreaming |  |
|  |  |  | Extractive Industries (oil, gas, mining) |
|  |  |  | Forestry (Including HCVF and REDD+) |
|  |  |  | Tourism |
|  |  |  | Agriculture & agrobiodiversity |
|  |  |  | Fisheries |
|  |  |  | Infrastructure |
|  |  |  | Certification (National Standards) |
|  |  |  | Certification (International Standards) |
|  |  | Species |  |
|  |  |  | Illegal Wildlife Trade |
|  |  |  | Threatened Species |
|  |  |  | Wildlife for Sustainable Development |
|  |  |  | Crop Wild Relatives |
|  |  |  | Plant Genetic Resources |
|  |  |  | Animal Genetic Resources |
|  |  |  | Livestock Wild Relatives |
|  |  |  | Invasive Alien Species (IAS) |
|  |  | Biomes |  |
|  |  |  | Mangroves |
|  |  |  | Coral Reefs |
|  |  |  | Sea Grasses |
|  |  |  | Wetlands |
|  |  |  | Rivers |
|  |  |  | Lakes |
|  |  |  | Tropical Rain Forests |
|  |  |  | Tropical Dry Forests |
|  |  |  | Temperate Forests |
|  |  |  | Grasslands |
|  |  |  | Paramo |
|  |  |  | Desert |
|  |  | Financial and Accounting |  |
|  |  |  | Payment for Ecosystem Services |
|  |  |  | Natural Capital Assessment and Accounting |
|  |  |  | Conservation Trust Funds |
|  |  |  | Conservation Finance |
|  |  | Supplementary Protocol to the CBD |  |
|  |  |  | Biosafety |
|  |  |  | Access to Genetic Resources Benefit Sharing |
|  | Land Degradation |  |  |
|  |  | Sustainable Land Management |  |
|  |  |  | Restoration and Rehabilitation of Degraded Lands |
|  |  |  | Ecosystem Approach |
|  |  |  | Integrated and Cross-sectoral approach |
|  |  |  | Community-Based NRM |
|  |  |  | Sustainable Livelihoods |
|  |  |  | Income Generating Activities |
|  |  |  | Sustainable Agriculture |
|  |  |  | Sustainable Pasture Management |
|  |  |  | Sustainable Forest/Woodland Management |
|  |  |  | Improved Soil and Water Management Techniques |
|  |  |  | Sustainable Fire Management |
|  |  |  | Drought Mitigation/Early Warning |
|  |  | Land Degradation Neutrality |  |
|  |  |  | Land Productivity |
|  |  |  | Land Cover and Land cover change |
|  |  |  | Carbon stocks above or below ground |
|  |  | Food Security |  |
|  | Climate Change |  |  |
|  |  | Climate Change Adaptation |  |
|  |  |  | Climate Finance |
|  |  |  | Least Developed Countries |
|  |  |  | Small Island Developing States |
|  |  |  | Disaster Risk Management |
|  |  |  | Sea-level rise |
|  |  |  | Climate Resilience |
|  |  |  | Climate information |
|  |  |  | Ecosystem-based Adaptation |
|  |  |  | Adaptation Tech Transfer |
|  |  |  | National Adaptation Programme of Action |
|  |  |  | National Adaptation Plan |
|  |  |  | Mainstreaming Adaptation |
|  |  |  | Private Sector |
|  |  |  | Innovation |
|  |  |  | Complementarity |
|  |  |  | Community-based Adaptation |
|  |  |  | Livelihoods |
|  |  | Climate Change Mitigation |  |
|  |  |  | Agriculture, Forestry, and other Land Use |
|  |  |  | Energy Efficiency |
|  |  |  | Sustainable Urban Systems and Transport |
|  |  |  | Technology Transfer |
|  |  |  | Renewable Energy |
|  |  |  | Financing |
|  |  |  | Enabling Activities |
|  |  | Technology Transfer |  |
|  |  |  | Poznan Strategic Programme on Technology Transfer |
|  |  |  | Climate Technology Centre & Network (CTCN) |
|  |  |  | Endogenous technology |
|  |  |  | Technology Needs Assessment |
|  |  |  | Adaptation Tech Transfer |
|  |  | United Nations Framework on Climate Change |  |
|  |  |  | Nationally Determined Contribution |
|  |  |  | Paris Agreement |
|  |  |  | Sustainable Development Goals |
|  |  | Climate Finance (Rio Markers) |  |
|  |  |  | Climate Change Mitigation 0 |
|  |  |  | Climate Change Mitigation 1 |
|  |  |  | Climate Change Mitigation 2 |
|  |  |  | Climate Change Adaptation 1 |
|  |  |  | Climate Change Adaptation 2 |

Project ID number remains the same as the assigned PIF number.

When completing Table A, refer to the excerpts on GEF 6 Results Frameworks for GETF, LDCF and SCCF.

Financing type can be either investment or technical assistance.

For GEF Project Financing up to $2 million, PMC could be up to10% of the subtotal;  above $2 million, PMC could be up to 5% of the subtotal.  PMC should be charged proportionately to focal areas based on focal area project financing amount in Table D below.

For questions A.1 –A.7 in Part II, if there are no changes since PIF , no need to respond, please enter “NA” after the respective question.

For biodiversity projects, in addition to explaining the project’s consistency with the biodiversity focal area strategy, objectives 
   and programs, please also describe which Aichi Target(s) the project will directly contribute to achieving..

GEF policies encompass all managed trust funds, namely: GEFTF, LDCF, and SCCF

If at CEO Endorsement, the PPG activities have not been completed and there is a balance of unspent fund, Agencies can continue to undertake the activities up to one year of project start.  No later than one year from start of project implementation, Agencies should report this table to the GEF Secretariat on the completion of PPG activities and the amount spent for the activities.  Agencies should also report closing of PPG to Trustee in its Quarterly Report.