M

# GOVERNMENT OF ANGOLA

FAO GEF PROJECT DOCUMENT

| Project Title: | Sustainable Land Management in target landscapes of Central Angola (Gestão Sustentável de Terras em paisagens seleccionadas da Região Central de Angola -ZAEC-) |
| --- | --- |
| Project symbol: | GCP /ANG/055/GFF |
| Recipient Country(ies): | Angola |
| Executing partner(s): | Ministry of Environment (MINAMB - Ministério do Ambiente) |
| Expected EOD (Starting Date): | October 2019 |
| Expected NTE (End Date): | October 2023 |
| Contribution to FAO’s Strategic Framework: (Indicate as appropriate) | FAO Strategic Objective/Organizational Outcome: Objective #2: Make agriculture, forestry and fisheries more productive and sustainable. / Org. Outcome 2.1: Countries adopted practices to increase productivity sustainably while addressing climate change and environmental degradation in agriculture, forestry and fisheries. Country Outcome(s) UNDAF: Strategic Area of Intervention 3: Sustainable and Inclusive Economic Development. Outcome 3.1: Inclusive Growth, Economic Diversification, Production and Job Creation Outcome 3.2: Environmental Sustainability, Climatic Change and reduction of Risks Disasters. Country Programming Framework(s) Output(s): Priority area 1, Strengthening smallholder farming productivity and competiveness to reduce Food Insecurity. Outcome 1.1. Priority area 2, Sustainable Management of Natural Resources for mitigation and adaptation of climate change impacts. Outcome 2.1. Priority area 3, Institutional Capacity Building. Outcome 3.2 Regional Initiative/Priority Area: Integrated Management of Agricultural Landscapes in Africa / Generating and sharing knowledge and Capacity Building. |
| Contribution to GEF TF Focal Area Strategic Objectives and Programs: | LD1 - Program 1 [Agro-ecosystems / Agroecological intensification] LD3 - Program 4 [Integrated Landscapes / Scaling-up Sustainable Land Management through Landscape Approach] |
| Environmental and Social Risk Classification | low risk [x] |
| Gender Marker | G0 G1 G2a [x] G2b |
| Total Budget: | TOTAL: USD GEF: 2,639,726 USD TOTAL Co-financing: 15,000,000 USD |
| Executive Summary Land degradation is a serious threat to ecosystem services and livelihoods in Angola. Yet, in the current post-conflict era, there have been very few attempts to systematically address it. The extent of land degradation across the national territory, and its impacts on the rural economy – including its growth potential – are yet to be assessed, along with further impacts on food security. In the meantime, land use is changing rapidly in various parts of the country and mostly in an unregulated fashion. In the rural zones, most land-use change is caused by shifting cultivation, overgrazing and the unsustainable use of fire across the landscapes. A legal and policy framework is in place in Angola for developing and enforcing land-use plans in different geographical and jurisdictional settings. However, there are many gaps in the practical application of these frameworks. Technological and capacity barriers need to be overcome before plans, tools and stakeholder consultation mechanisms can be applied for halting and reversing land degradation, thereby avoiding the associated loss of ecosystem services. Another set of barriers relates to access to finance for sustainable land management (SLM), in which the general context of the agricultural economy is relevant. Investing in Angola’s agricultural sector can potentially help the Angolan economy reduce its dependency on both the oil sector and food imports – and taking action towards it has been prioritized by government in its National Development Plan for the period 2018-2022. Investing in the family farming segment, more specifically, could in addition contribute to food security and help fight rural poverty. Beyond the general fragility of the country’s financial system, not geared for the segment of family farmers, principles of SLM are not yet part of the decision-making processes that lead to investments in the agricultural sector or to rational land-use allocation in different contexts. The Central Plateau of Angola, which has its heartland in Huambo Province and extends into parts of the neighboring provinces of Benguela, Bié and Cuanza Sul, is an ideal testing ground for solutions for both assessing and addressing the issue of land degradation through land-use practices. According to a recent survey taken as part of the Land Degradation Neutrality Target Setting Program (LDN-TSP), ecosystem services are declining in 5 out of the 11 municipalities in Huambo Province and in 5 out of 6 non-coastal municipalities in Benguela. In spite of the severity of land degradation in the region, the causes of land degradation are not well known among land-users and technical practitioners within the agricultural sector. In addition, rural land use planning is practically non-existing. Municipal-level spatial plans exist but focus only on urban areas. There have been some attempts at characterizing landscapes in terms of agroecological features and ideal land uses (including crop suitability) with a view to improving land productivity and informing the attribution of land rights (including the concession of agricultural lands), but these have never materialized into outputs that are useful for local land-use aiming at the sustainable improvement of rural livelihoods. The Centre of Tropical Ecology and Climate Change (CETAC), under the Ministry of Environment (MINAMB), is centrally located in Huambo City also closely located to academic institutions which conduct research and offer training in related environmental fields -- in particular the Faculdade de Ciências Agrárias (FCA) and the Instituto de Investigação Agronómica (IIA). CETAC is slated to constitute the pivot of a national network of Agroecological Centers (AECs). If adequately capacitated through investment, by the government and other initiatives (including this project), CETAC has the long-term potential to become a country-level hub in domain of Agroecological Zoning (AEZ) and planning for Sustainable Land Management (SLM), thus capable of promoting SLM nationwide as a core strategy for improving land productivity, safeguarding long-term food security and halting the loss of ecosystem services due to land degradation. The practical integration of AEZ products in local spatial planning for SLM and local agricultural and other land-use practices will be operationalized through the national network of Agroecological Centers and the Agro-Pastoral and Farmer Field Schools (AP/FFSs), an approach that has proved successful in Angola, but which needs to be improved and upscaled. This FAO-GEF project will develop the approach to this long-term vision in regard to a restricted focus zone, i.e., a Wider Landscape in the provinces of Huambo and Benguela. Along the above-mentioned relevance of these landscapes for land degradation and the proximity to CETAC to one of the four AECs in Angola (Chipipa), there is a growing network of AP/FFSs in Huambo and Benguela and neighboring provinces, which are already delivering community-level extension services on a regular basis with the support from both government and a series of international projects set on upscaling the approach. This creates opportunities, which the project will seize, for actively engaging land users in local spatial planning of SLM based on AEZ and adopting SLM practices on the ground. By learning from previous GEF SLM projects and working synergistically with existing ones, this project will build on a solid baseline of relevant investments and implement its strategy in close collaboration with related initiatives. The project focus zone will function as a national SLM ‘upscalable lab’, aimed at demonstrating a ‘nested (or multi-scale) approach’ to spatial planning and land-use management. From ‘micro' to ‘macro’, the multiple and nested scales will encompass the farm-level, selected communes, the municipalities that nest these communes and the Wider Landscape within two provinces of Huambo and Benguela. More specifically, there is a need to address pressures on natural resources from competing land uses, both across the broader landscape and locally. In order to achieve this, CETAC, the AECs and rural extension services through the AP/FFSs will need to overcome institutional and individual capacity barriers and work together, helping local decision makers and land users understand the stakes implied in landscape-level management at different levels. The project’s objective is to reverse negative land degradation trends in selected landscapes in Central Angola by combining sustainable and rational approaches to planning, decision-making and land-use management with participatory approaches to build the capacity of local stakeholders. Interventions are foreseen in three main fronts: Under Component 1, the project will build national capacity for land-use management through Agroecological Zoning (AEZ), by strengthening CETAC’s GIS and spatial planning capabilities. It will develop within the Center a dedicated spatial planning unit with focus on SLM, including by engaging 6-12 young professionals (post-graduate level) though a Job Shadowing program, with strong encouragement towards female candidacies. By developing and applying a unique geographically nested, fine-scale and integrated decision-support system (DSS), CETAC’s AEZ Unit will deliver on-demand services to planners, investors and land-use decision makers at various levels. It will also help Angola to dynamically monitor Land Degradation Neutrality (LDN) parameters across the country. Through this project, the AEZ system will specifically target Benguela and Huambo Provinces. The project will also develop plans for scaling-up the system’s reach and scope, and for integrating more features into it, expanding the range of services, users and contributors. In the process, CETAC’s capacity to sustain the AEZ Unit will be considered and enhanced. Under Component 2, the project will support the integration of SLM into rational decision-making pertaining to land-use management, both at the municipal/commune level and at the local level (i.e. village/community). In selected demonstration landscapes, the project will work with municipal and communal authorities, as well as local communities on topics such as sustainable land-use allocation, crop suitability, fire prevention, integrated soil fertility management, as well as other SLM techniques and science-based approaches. It will target both agricultural and pastoral land uses, making use of agroecological data and tailored AEZ products developed by CETAC’s specialized AEZ Unit. Its goals are to monitor, prevent and, where needed, reverse the process of land degradation on the ground, aiming at meeting LDN targets by project end, thereby demonstrating the effectiveness of AEZ-based SLM in delivering LDN. For the purpose, local stakeholders will be involved in a process of negotiating territorial agreements through participatory methodologies (e.g. GreeNTD). The process will form the basis for preparing local SLM plans, which will be validated by municipalities and incorporated in the Angolan land-use planning system. The implementation of the local SLM plans will be promoted and mediated by farmer field schools and agropastoral field schools (FFS/APFS) and the AEC in Chipipa within the targeted communities (demo sites) in three demonstration landscapes. In addition, the project will deliver a comprehensive training program targeting at least 30 FFS/APFS master trainers active in the Central Plateau region and focusing on SLM and AEZ. In this way, pressures on natural resources are expected to be directly and indirectly attenuated and land productivity improved within approximately 429,000 ha – corresponding to the demo landscapes – and indirectly, within the Wider Landscape, comprising approximately 6.1 million ha. The project’s Component 3 will focus on identifying and developing suitable options for SLM finance and on improving national capacity for mobilizing resources to be invested in SLM. This will include both carrying out and disseminating among key decision makers targeted economic analysis of the cost of land degradation in the provinces of Huambo and Benguela. The aim is to bring financial awareness and leverage, as well as to expand the scale of actions needed for restoring/rehabilitating land in that part of the country. Both mainstream and innovative finance options for SLM will be assessed, explored and probed. Enabling actions for operationalizing the most promising mechanisms in selected local communities within demonstration landscapes will ensue. The resident rural population within the project’s Wider Landscape totals approximately 1.5 million people within rural communes (1.1 million in Huambo and 450 thousand in the Benguela part of the landscape). They will indirectly benefit from the Project through the work under Component 1 (AEZ studies). Direct targets for the number of beneficiaries within demonstration landscapes were estimated at approximately 1,500 engaged farmers and agro-pastoral land users, of whom at least 40% will be women. |  |

# CONTENTS

SECTION 1 – RELEVANCE	10

1.1) PROJECT CONTEXT	10

1.1.1 The National Context	10

1.1.2 Project intervention areas	23

1.2) THE CURRENT SITUATION	29

1.2.1 Main Environmental Threats	29

1.2.2 Baseline Initiatives	37

1.2.3 Remaining Barriers to be addresses	47

1.3) THE GEF ALTERNATIVE	51

1.3.1 Project Strategy	51

1.3.2 Project Objectives, Outcomes and Outputs	69

Component 1) Agroecological zoning (AEZ) integrated planning	69

Component 2) Sustainable Land Management in target landscapes	77

Component 3) Economic and financial leverage approaches to SLM	85

Component 4) Knowledge management, monitoring and evaluation	88

1.3.3 Project Assumptions	89

1.3.4 The global Environmental Benefits	90

1.3.5 The Socio-economic Benefits	93

1.4) STAKEHOLDER CONSULTATION AND ENGAGEMENT	94

1.4.1 Project Stakeholders	94

1.4.2 Stakeholder Engagement Process and Mechanism	96

1.4.3 Stakeholder Engagement	97

1.4.4 Grievance Mechanism	101

1.4.5 Disclosure	103

1.4.6 Partnerships	103

1.5) ALIGNMENT AND STRATEGIC FIT	103

The National Development Plan (PDN) 2018-2022	104

Agricultural Sector Mid-Term Plan (PMPSA) 2018-2022	106

Land Degradation Neutrality Target Setting Program (LDN-TSP)	106

National Action Program to Combat Desertification (PANCOD)	107

Angola’s Spatial Planning System	107

Alignment with FAO’s Strategic Objectives and Programs	108

Alignment with relevant GEF-6 Focal Area Strategies	109

1.6) COMPARATIVE ADVANTAGES	109

1.7) KNOWLEDGE MANAGEMENT AND COMMUNICATION	110

1.7.1 Knowledge Sharing	110

1.7.2 Lessons Learned	111

1.7.3 Communication	119

SECTION 2 – FEASIBILITY	120

2.1) IMPLEMENTATION ARRANGEMENTS	120

2.1.1 Institutional Framework and Coordination	120

2.1.2 Government Inputs	130

2.1.3 Resource Partner Inputs	130

2.1.4 FAO Inputs	132

2.2) RISK MANAGEMENT	132

2.2.1 Potential Risks to the Project	132

2.2.2 Environmental and Social Risks from the Project	133

2.3) MONITORING, PERFORMANCE ASSESSMENT AND REPORTING	133

2.3.1 Monitoring Arrangements	133

2.3.2 Reporting	133

2.4) EVALUATION PROVISIONS	136

2.5) FINANCIAL MANAGEMENT AND REPORTING	137

SECTION 3 - SUSTAINABILITY	139

3.1) CAPACITY DEVELOPMENT	139

3.2) FINANCIAL AND ECONOMIC SUSTAINABILITY	139

3.3) ENVIRONMENTAL SUSTAINABILITY	140

3.4) INNOVATION AND SCALE UP	140

3.4.1 Innovativeness	140

3.4.2 Potential for Scaling Up	141

3.5) DECENT RURAL EMPLOYMENT	141

3.6) GENDER EQUALITY	142

The Gender Action Plan	144

3.7) INDIGENOUS PEOPLES	145

APPENDICES (Standard FAO GEF)	150

Appendix I) Logical Framework Matrix	150

Appendix II) Stakeholder Engagement Matrix	159

1) Stakeholder Consultation	159

2) Grievance Mechanism	160

3) Disclosure (currently not applicable)	160

Appendix III) Work Plan	161

Appendix IV) Budget	166

Appendix V) Risk Management	166

Section A: Risks to the Project	166

Section B: Environmental and Social Risks from the Project	168

Appendix VI) Terms of Reference	172

TORs for PMU – Core Project Team	172

Other TORs: Evaluation, Consultancies and other Service Provision Needs	183

Annexes (Additional – Project Specific)	185

Annex A. PRODOC Atlas (separate file)	185

Annex B. Tracking Tool	186

Annex C. Bibliography	191

Annex D. OFP Letter dated 25 September 2019 on implementation arrangements	194

Annex D. OFP Letter dated 25 September 2019 on implementation arrangements                              197

# TABLES, FIGURES AND BOXES

Table 1. The Wider Landscape: Overview of the resident rural population per municipality	25

Table 2. Selected LD3 – Program 4 Tracking Tool Questions (TT-Qs) applied to demo landscapes	27

Table 3. Baseline Finance: List with Descriptions and Co-financing from Baseline ($M)	39

Table 4. Baseline Finance ($M), Leveraged ($M) and Total Co-financing ($): Overview per Source and Component	42

Table 5. Governmental investment baseline from the National Development Plan (PDN) 2018-2022	43

Table 6. Projected Public Investments from the PDN: OGE Baseline summary per Component and Project Year (PY)	45

Table 7. Incremental Cost Reasoning	62

Table 8. Proposed Products that the AEZ Unit will focus on	74

Table 9. Project assumptions per Component	90

Table 10. GEF Outcome Monitoring & Indicators	93

Table 11. Project stakeholders and their role in project implementation	95

Table 12. Organization and Enabling Environment Capacity Needs Assessment	98

Table 13. Brief analysis of stakeholder profile and stats, plus gender notes	99

Table 14. Overview of numbers for the communities consulted during PPG (Aug/Sep 2018)	100

Table 15. Alignment of the Project with the agenda of the National Development Plan (PDN) 2018-2022	105

Table 16. Relevant past and on-going projects, including GEF funded (synergies, collaboration and lessons)	113

Table 17. Lessons drawn from the application of the FFS approach in Angola FFS	117

Table 18. Further information about the general composition of the AEZ Technical Unit and PMU	128

Table 19. Proposed Letters of Agreement	129

Table 20. Proposed Synergy Partnerships (prospective MoUs or other applicable arrangements)	129

Table 21. M&E Framework	136

Table 22. Gender entry points for monitoring during project implementation	146

Table 23. Screening for the need of FPIC during PPG and project implementation	149

Table 24. Risk Assessment: Overall rating is ‘Low’	167

Table 25. Specific E&S Risk Assessment: Overall rating is ‘Low’ / Compliant	169

Table 26. Summary results from the Project Environmental and Social (E&S) Screening Checklist	172

Table 27. Reference checklist used in the CNA with reference to sourcing of GIS data for AEZ	189

Table 28. Bibliographical sources mentioned in the PRODOC	193

Figure 1. United Nations Map of Angola showing the Project’s Focus Zone	9

Figure 2. Graph on cereal production and productivity in Angola over the years (1961-2015)	11

Figure 3. Central Plateau and other agroecological zones	13

Figure 4. Structure of GDP and of employment per sector in Angola	16

Figure 5. Main activities of rural households according to agricultural sub-sectors (%)	16

Figure 6. Field pictures: Epandi-1’s FFS at Selimbondue, Alto Hama Commune, Huambo Province	20

Figure 7. The Focus Zone and the Wider Landscape within the national geographical context	24

Figure 8. Project landscapes in context: The Wider and Demo Landscapes plus Municipalities	26

Figure 9. Proximate and underlying driving forces of LD (not context-specific)	31

Figure 10. Dominant drivers for tree cover loss in the Project Zone according to global sources	32

Figure 11. Record of active fires in Project Zone according to the global sources	33

Figure 12. Tree cover loss statistics for Huambo and Benguela according to GFW	34

Figure 13. Land Productivity Dynamics in Angola according to the global sources	35

Figure 14. Evolution of State Budget for agriculture (in US$ at market rates)	47

Figure 15. Logical Structure of the General Project Design	53

Figure 16. A Summary of the Project’s Theory of Change	59

Figure 17. Actors and Stakeholders of Component 1	76

Figure 18. Relations between target scales, products and clients of AEZ Unit	77

Figure 19. Main Information flows in the implementation of Component 2	80

Figure 20. Diagram with the implementation arrangement	130

Box 1. Options for municipal and local level spatial and land-use planning	22

Box 2. The tiered nested approach to spatial planning and landscape-level management for SLM	29

Box 3. Three tiers within the nested approach to landscape level management applied in the project	30

Box 4. Baseline of Finances and Co-finance for SLM	47

Box 5. Notes on SLM entry points into the national system of spatial planning and extension	82

Box 6. On the training program for land-use decision making at community-level	85

Box 7. Reference to useful environmental datasets containing publicly available data and information	191

Box 8. Suggested reading by STAP and spatial planning, Considerations and Cross-reference	192

# ACRONYMS

| ADRA | Action for Rural Development and Environment, Angolan NGO |
| --- | --- |
| AEC | Agroecological Center |
| APFS | Agro-Pastoral Field School (Escolas de Campo Agropastoral – also ‘ECAP’ in Portuguese) |
| AWP/B | Annual Work Plan and Budget |
| BaU | Business as usual |
| BH | Budget holder |
| CAC | Councils of Hearing and Social Concertation (Conselhos de Ascultação e Concertação Social) |
| CBD | Convention on Biological Diversity |
| CBOs | Community-Based Organizations |
| CC | Climate Change |
| CETAC | Centre of Tropical Ecology and Climate Change |
| CMA | Multisectoral Commission for the Environment (Comissão Multisectorial para o Ambiente) |
| COSPE | Cooperation for Development of Emerging Countries, Italian NGO |
| CPF | FAO Country Program Framework |
| CTA | Chief Technical Advisor |
| ECA / ECAP | Farmer Field School / Agropastoral Field Schools (Escola de Campo / Escola de Campo Agropastoral) |
| ECONET | Ecosystem Observation and Monitoring Network (GEO Econet), FAO |
| ECP | Strategy for Fighting against Poverty |
| EDA | Agricultural Development Station |
| ELISA | Energy and Livelihoods Solutions for Angola, a UNDP GEF SLM capacity building project |
| ENSAN | National Food Security and Nutrition Strategy |
| FAO | Food and Agriculture Organization of the United Nations |
| FAS | Fundo de Apoio - Social Support Fund |
| FCA | Faculdade de Ciências Agrárias |
| FE | Final Evaluation |
| FFS | Farmer Field Schools (Escolas de Campo – also ‘ECA’ and ‘ECAP’ in Portuguese) |
| FPMIS | FAO Field Program Management Information System (project database) |
| GABAC | Office for Climate Change |
| GAEZ | FAO’s initiative ‘Global Agro-Ecological Zones’ |
| GEB | Global Environmental Benefits |
| GEF | Global Environment Facility |
| GEPE | Office for Planning and Statistics of MINAGRIF |
| GFW | Global Forest Watch |
| GIS | Geographic Information System |
| GLIPHA | Global Livestock Production and Health Atlas |
| GoA | Government of Angola |
| GPS | Global Positioning System |
| GSA | Office for Food Security - Gabinete de Segurança Alimentar, under MINAGRIF |
| HDI | Human Development Index |
| IDA | Agricultural Development Institute |
| IDF | Institute for Forestry Development |
| IGCA | Geodesic Cadastral Institute of Angola - Instituto Geográfico e Cadastral de Angola |
| IGETI | Improving Gender Equality in Territorial Issues |
| IIA | Institute for Agronomic Research |
| IIV | Veterinary Research Institute |
| INAMET | National Institute for Meteorology - Instituto Nacional de Meteorologia |
| INOTU | National Institute for Territorial Planning and Urban Development |
| INRM | Integrated natural resource management |
| ISV | Institute of Veterinary Services |
| LD | Land Degradation |
| LOA | Letter of Agreement |
| LPSC | Local Program Steering Committee |
| LTO | Lead Technical Officers |
| LTU | Lead Technical Unit |
| MAT | Ministry of Territorial Administration |
| MINAGRIF | Ministry of Agriculture and Forestry |
| MINAMB | Ministry of Environment |
| MINOTH | Ministry of Spatial Planning and Housing |
| MOSAP | Market Oriented Smallholder Agriculture Project |
| NAPA | National Adaptation Program of Action |
| NBSAP | National Biodiversity Strategy and Action Plan |
| NEMP | National Environmental Management Plan |
| NGO | Non-Governmental Organization |
| NPC | National Project Coordinator |
| NPP | Net Primary Production |
| NRM | Natural Resources Management |
| PAPEFSA | Program to Support the Livestock Sector Family from Southern Angola |
| PDMPSA | National Medium-term Development Plan for the Agrarian Sector |
| PIR | Project Implementation Review |
| PMIDRCP | Integrated Municipal Program for Rural Development and Combat Against Poverty |
| PDN | National Development Program (Programa de Desenvolvimento Nacional) |
| PNTD | Participatory Negotiated Territorial Development |
| PSC | Project Steering Committee |
| SLM | Sustainable Land Management (Gestão Sustentável de Terras – GST) |
| SV | Veterinary Service |
| STAP | The GEF’s Scientific and Technical Advisory Panel |
| TCI | Investment Centre Division |
| TCP | FAO’s Technical Cooperation Program |
| TOR | Terms of Reference |
| UNCCD | United Nations Convention to Combat Desertification |
| UNDAF | United Development Assistance Framework/ United Nations Assistance Framework for Angola |

Figure 1. United Nations Map of Angola showing the Project’s Focus Zone

# SECTION 1 – RELEVANCE

## 1.1) PROJECT CONTEXT

### 1.1.1 The National Context

#### General Context of Land Degradation in Angola

The Republic of Angola is the third largest country in sub–Saharan Africa with an area of 1,246,700 km2. Angola is located in the southern part of the African continent and is bordered in the north and east by the Republic of Congo and the Democratic Republic of Congo, in the east by the Republic of Zambia, in the South by the Republic of Namibia and in the west by the Atlantic Ocean. Angola’s administrative division comprises of 18 provinces (see Figure 1). Mount Morro de Moco in Huambo Province is the country’s highest point with an elevation of 2,620 m. The climate is tropical to sub-tropical, featuring warm and humid summers and mild and dry winters. Rich in water resources, with more than a dozen major river basins crossing its territory, Angola also displays a broad range of vegetation and soil types. Angola’s terrestrial ecosystems range from the desert biome of the southwest, through arid savannas of the south, shifting to extensive miombo woodlands in the southeast and in the Central Plateau, and to the rainforests of Cabinda, Zaire and other northern provinces. Both climate and vegetation are influenced by altitude, longitude and the direct and indirect effects of the Atlantic Ocean on geophysical parameters. (See PRODOC Atlas in Annex A for an illustration of the geophysical context).

In terms of natural resources, Angola is certainly a rich country. These resources include notably oil, gas and minerals, as well as land, water and varied ecosystems. Yet, in Angola’s post war context, the majority of its people, which currently tally more than 29.2 million, are yet to benefit from the country’s natural bounty. Most of the residents in the rural areas of Angola still face significant challenges linked to poverty, low levels of literacy, reliance on subsistence agriculture and limited access to social services. Also, the poor state of the road network and limited investments in agricultural productivity are major constraining factors, vis-à-vis the potential of the rural economy.

In the current post-conflict recovery era, the Government of Angola made it a priority to expand the importance of the agricultural sector, not least also as a growth alternative to the oil dependency. New investments, bound to come to fruition in the upcoming decade, will certainly help towards this goal, with several new programs being mobilized by the government to that effect. Increased investment in the agricultural sector may change conditions in the rural areas in different ways. The quest towards mainstreaming principles and measures of sustainable land management (SLM) into the modernization efforts of the agricultural sector in Angola represent a complex challenge and a key motivation behind this project’s idea.

Agroecology and the SLM challenge. Agroecology is influenced by all factors mentioned further up – from the geophysical parameters of the country to the drivers of land-use patterns. It may also include considerations on the impacts and feasibility of investments in different rural economy segments, considering local market conditions. The in-depth study of agroecology can help determine the outcome in terms of land productivity and land-use suitability for any given ‘terrestrial spatial unit’ (a piece of land, a landscape, an administrative unit, etc.). It also helps shed light into the sustainability of the current and future use of land, while also providing ‘perspective’ regarding the role and the importance of ecosystem services across landscapes and the interactions between different land uses within these. At different scales and by targeting different audiences, products based on agroecological information can be a powerful tool for the sustainable allocation of land and the management of its use.

Currently, there is very little knowledge about agroecological conditions in Angola. E.g., FAO estimates that 47.6% of the land surface in Angola (59 million ha) is ‘agricultural land’, which is significant, even though only a fraction of this land is arable or cultivated under permanent crops. Other geophysical parameters also point out to an untapped potential for developing the agricultural sector. At the same time, statistics on Angola’s agricultural production and productivity display erratic patterns over the years and a rather modest growth in spite of the potential (see Figure 2). In reality, little is known about Angola’s actual agroecological potential, especially when zooming into a specific geographical area. This potential may be larger than estimated, or smaller, e.g. due land degradation. Regardless, without appropriate measures, it is difficult for a provincial or municipal government to make sound decisions about land-allocation and investment in the agrarian sector.

Figure 2. Graph on cereal production and productivity in Angola over the years (1961-2015)

Source: FAOSTATS, FAO Statistical Data, Angola, Indicators, Production: http://www.fao.org/faostat/en/#country/7.

On the one hand, the historical patterns shown in Figure 2 can be attributed to the lasting impacts of the more than two-decade-long civil war, which ended in 2002 – and there is certainly room for improvement in agricultural statistics in Angola. On the other, it is important to take into account how today’s technology can benefit the agricultural sector and also Angola’s investment power. Because the factors of production change, measures of agroecological potential are always dynamic. Still, the current performance of the agricultural sector, from a production and productivity points of view (with cereal production representing a central aspect of it), is sub-optimal. It is also notable that Angola relies heavily on food imports to meet its consumption needs and that many of these needs are not fully met, as illustrated by a suite of food security indicators for the country.

While factors such as topography and climate are a given and influence the outcome of agricultural performance, other issues can, to a great extent, be attributed to decision-making processes regarding land use. Understanding these patterns, the drivers behind them and their consequences is therefore crucial for a more sustainable development within the agricultural sector in Angola. These principles are also underscored by key policies and plans – in particular the National Medium-term Development Plan for the Agrarian Sector (PDMPSA), 2018-2022, where the vision and targets for the sector’s future, taking environmental issues into account, are outlined.

Project Scope. In the above-presented context, land degradation at the landscape level is a direct result from poor decision-making regarding land use and natural resource management (NRM). And although the agricultural sector in Angola suffers from several systemic constraints that lie outside the scope of this project, issues of decision-making regarding land use and NRM can be addressed through the careful prioritization of capacity building actions, the selection of a meaningful target landscapes, tools, approaches and ‘entry points’, and not least also by carving out strategic partnerships.

Land degradation is indeed a serious threat to ecosystem services and livelihoods in Angola, but in its current post-conflict era, there have been to date very few attempts to systematically address it. Also, the extent of land degradation across the national territory, and its impacts on the rural economy – including its growth potential – are yet to be properly assessed and solutions that prime sustainable land management (SLM) yet to be devised. This project proposes to be a contribution in this respect, working with tools and indicators such as Agroecological Zoning (AEZ) and Land Degradation Neutrality (LDN).

Demographics. According to the General Census of 2014, the first one conducted after national independence, Angola’s resident population was in that year 25.7 million inhabitants, 65% of whom was under 24 years of age. The average age of Angolans is 20.6 years. Hence, any solution for Angola’s many problems must include young people in order to build on the demographic dividend that this represents. Angola also continues to have one of the highest fertility rates in the world (with an average of 5.9 children per woman over the period 2010-2015), surpassing the average in Sub-Saharan Africa (5.1) and well above the average in countries of low human development (4.6), resulting in projections of high rates of natural growth.

The 2014 Census also revealed that demographic patterns in Angola are highly asymmetrical, with vast regions of the country displaying very low population density. According to published Census results, only 37% of the total population live in rural zones, while the remainder 63% in urban ones. The latter has a strong concentration in the province of Luanda and surroundings. The Province of Luanda alone, with 6.9 million inhabitants, harbors more than a quarter of the country's population. After Luanda, the most populated provinces are: Huíla, with 2.5 million (10%), Benguela, with 2.2 million (9%) and Huambo, with 2 million (8%).

A recent household-level survey, carried out by the Government of Angola (GoA) in 2016 and with national coverage, indicated that, in average and across all zones, the two poorest types of household in Angola make up 60% of the total population. Assessments dating from 2008 pointed out to 58% of the rural population being considered poor, as opposed to 5.1% in urban ones. Since the economy has been facing recession for the past 2-3 years, due to relatively low oil prices, poverty in the rural areas is likely aggravating. Women, who make up 53% of the population in rural households in Angola, are even more vulnerable to the economic downturn.

The Project’s Focus Zone. The project’s core geographic focus is on the Central Plateau region, and more specifically on two provinces – Huambo and Benguela. The Central Plateau region of Angola has its heartland in Huambo Province and extends into parts of the neighboring provinces of Benguela, Bié and Cuanza Sul. Although the Central Plateau is an important part of Angola’s geography, it has loosely defined borders, which vary according to source, and no jurisdictional status as a ‘region’ from a governmental administration point of view. Adjacent agroecological zones may include the Center-West Transition Zone and the agro-pastoral Quilengues (as shown in Figure 3):

Figure 3. Central Plateau and other agroecological zones

Note: Refer to Annex A PRODOC Atlas for the bigger picture.

For the sake of definitions, the Project’s Focus Zone encompasses: (i) the rural communes of all the municipalities in Huambo Province and (ii) the non-coastal municipalities of Benguela Province that make up a range of surrounding landscapes vis-à-vis the Central Plateau. These landscapes, located in the interior of the country, include both agricultural lands (primarily in Huambo) and rangeland (primarily in Benguela). The area is vast (it covers 6.1 million ha, which corresponds to approximately 80% of the surface area of Huambo and Benguela Provinces together). Yet, given the nature of Component 1 activities, the large size of the landscape is suitable for agroecological studies. For work on the ground, a much smaller local surface has been selected on a demonstrative basis. (More details in section 1.1.2 Project intervention areas).

The Central Plateau and surrounding landscapes, described above as the ‘Project’s Focus Zone’, is a particularly good case-study for understanding land degradation in Angola and devising solutions to it, due to the following reasons:

- The interior zones of Benguela Province and the hilly landscapes of Huambo Province encompass the sources of chiefly important river basins. The terrain type, combined with its hydrography, may favor soil erosion, if not adequately managed;

- Land in the Central Plateau has been under intense agricultural use for several decades;

- The Central Plateau zone displays the highest population density in the country after the capital (see PRODOC Atlas in Annex A);

- Pressure on land-based ecosystem services from agricultural expansion is currently intensifying;

- There have been limited investments towards recovering agricultural productivity during the post-conflict period.

The Project’s Focus Zone is a macro-landscape, i.e. ‘The Wider Landscape’, upon which analyses of agroecology and LDN can apply. It is home to some 2.9 million people, half of whom live in rural communes. More specifically, the resident rural population of the Project’s Focus Zone sums approximately 1.5 million people within rural communes (1.1 million in Huambo and 450 thousand in the Benguela part of the landscape) and they may indirectly benefit from the Project. Direct targets for number of beneficiaries and ‘demo landscapes’ are otherwise discussed and presented in Table 1 in section 1.1.2.

It has to be considered that the Project will have an impact at the national level:(1) When supporting the LDN monitoring, the data collected and processed by the AEZ Unit will be more detailed for Huambo and Benguela “The Wider landscape”, however information and human capacities will also serve as base for the rest of the provinces in the country (2) The AEZ Unit will be able to offer Agroecological zoning for the entire country  for example when providing (and selling) products on demand to others (private sector, other projects , etc.), (3) Component 3 will also have a national scope. Technicians from MINAMB will be trained on resource mobilisation at national level, capacities for costs of LD assessment, will be created at national level (although at finer scale in the two targeted provinces).

According to a recent LDN Assessment, ecosystem services are in decline in several parts of the Central Plateau landscapes, in particular in the southern and northwest Huambo and in the interior of Benguela Province. In fact, in 9 out of the 17 municipalities included in the Project’s Focus Zone, LDN trends are either negative or mixed (positive and negative). In spite of the severity of land degradation in the Central Plateau region, there have not been any effective attempts to apply spatial planning tools for managing land use, and even less so for assessing the landscape’s agroecological potential as a decision-support system towards improving land productivity.

Development patterns & the economy. Since the end of the conflict, Angola has experienced an extraordinary social and economic recovery which has resulted in the rehabilitation and construction of schools, hospitals, health centers and clinics, roads and bridges, a gradual increase of agricultural, livestock and fisheries production, not to mention the construction sector itself, the country’s most dynamic sector. In more than ten years of stability, Angola achieved a thriving economy and one of the fastest rates of growth, with an average growth rate in real GDP of 11.6 %. Angola’s Human Development Index (HDI) reached 0,533 in 2015, having been as low as 0,390 in 2000. The country is now ranked as 150th among 188 countries. The 2014 Census estimates the life expectancy at birth of an Angolan at 60.29 years for 2014, being 57.6 years for men and 63 years for women.

Angola is currently the second largest crude oil producer in Africa, with a production output of 1.6 million barrels per day (bpd) in 2017, compared with the first in Africa, Nigeria, with a current output of 1.9 million bpd. Second to oil, diamonds are Angola’s main export product. Angola’s underground is also rich in other mineral resources like iron ores, phosphate deposits and large reserves of marble, granite, and quartz. Particularly in the last decade, the oil sector has exerted a decisive influence on the process of growth of the Angolan economy, both by the impact of its volatility and by still being the essential source of tax revenues, exports and foreign exchange entering the country.  The volatility of oil production is a threat to the sustainable development of the Angolan economy. Oil represents about one third of its GDP and over 95% of its exports, and the sharp and prolonged decline in its price since mid-2014 had a significant impact on Angola's economy.

The ensuing economic crisis underscored the need to diversify the Angolan economy and reduce its dependency on oil revenues, not least also because Angola still faces important food security challenges, in spite of recent progress towards SDGs. For example, according to FAO’s most recent flagship global publication on ‘The State of Food Security and Nutrition’, the prevalence of stunting in children under 5 has actually increased in Angola (from 29.2 in 2012 to 37.6 in 2017), while within the last decade, the prevalence of undernourishment in the total population was basically cut by half (was 54.8 in 2004-06 and fell to 23.9 in the 2015-17 period). The same publication also alerted to the relative vulnerability of the Angolan agricultural systems to climatic shocks (e.g. the country is prone to dry spells and low rainfall and its production and/or yields were classified as ‘climate-sensitive’).

According to Angola’s Medium-Term Development Plan for the Agrarian Sector 2018-2022 (PMPSA 2018-22), the agricultural sector only represents about 12.5 % of the Angolan GDP (Figure 4). In an effort to diversify the economy away from oil proceeds, the agenda of the Government of Angola holds as a central priority the exploitation of the country’s agricultural potential as part of a broad economic development strategy for the current post-conflict recovery era. As in most African countries, increasing agricultural productivity in Angola is not just about creating incentives for a struggling agricultural sector, but more fundamentally about food security and poverty alleviation. This implies addressing the more systemic issues that slow down growth, while ensuring that this growth is sustainable and more equitable than what it has been in the past.

The agricultural sector. In order to put the development context of the agricultural sector into perspective, two aspects need to be pondered: First, the Angolan economy has been severely disrupted by the prolonged armed conflict, which lasted from 1975 to 2002 with interludes. The impact of the conflict still affects the country’s agroecological potential and should not be underestimated. Secondly, it is also worth remembering that Angola was until 1975 self-sufficient in all key food crops except wheat. Agricultural exports accounted for nearly 60% of total exports, which were composed of coffee (48%), sisal (5%) maize (2%), and a number of other agricultural products including bananas, tobacco, cotton, beans, sugar, palm oil and rice. Those production systems collapsed with the war and the current systems yield of a fraction of the historical ones.

At the same time, in terms of occupation, agriculture remains the main economic activity for most of the Angolan population. According to the PMPSA 18-22, agriculture, livestock and forestry absorb about 44% of the total employed population (Figure 4). Although this is a large proportion of the employed population, the mentioned statistics did not include subsistence farmers. Data from 2014 Census compiled for Huambo Province reports e.g. that 70.2% of the population is self-employed in Agriculture.

Because production is insufficient, Angola heavily relies on food imports (80%) to meet its needs. In 2017, about 35% of all imports were agricultural and food products. At present, only 5.7% of Angola’s 575,900 km2 of agricultural land (almost half of the land surface) is being used. Agricultural production is predominantly a family-based activity for millions of smallholder subsistence farmers in at least 2.5 million households across the country. They plant an average of 1.4-1.7 hectares per family on two or more parcels of land.

The total planted area has increased slightly every year and it may have reached 5.7 million hectares by 2017. Agricultural production is mostly rainfed and the main growing season spans from September to December in most of the country. The large majority of the agricultural households are engaged in grain production (Figure 5) stressing the predominance of subsistence family farming as the core segment of the agricultural sector.

Figure 4. Structure of GDP and of employment per sector in Angola

| Sources: PMPSA 18-22 (MINPLAN); Banco Nacional de Angola. | Source: PMPSA 18-22 (MINPLAN) |
| --- | --- |

Figure 5. Main activities of rural households according to agricultural sub-sectors (%)

Source: INE (2014) Population Census (also in PMPSA 18-22). The term ‘cereacultura’ here refers to the cultivation of grains such as maize, rice, pearl millet and sorghum.

Currently, despite enormous potential to increase both the amount of area under cultivation and crop yields and, given the diverse mosaic of agro-climatic conditions across several provinces, agriculture, livestock-rearing and forestry make up a relatively small contribution to the economy. More importantly, the sector is not able to feed the country. According to FAO, food imports ($2,707 million) contrast starkly with food exports ($19 million).

The PMPSA 18-22 summarizes the current situation of the sector as characterized by a deficit in the supply of both agricultural, livestock and forestry products. The insufficient mechanization and automation of the various production processes is also a factor inhibiting the development of the sector. Finally, even though family farmers could represent a fairly large market to the financial sector, the PMPSA 18-22 also points out that ‘agriculture and fisheries’ only mobilized 8% of the credit awarded to private sector entities in 2015.

#### Policies, strategies, institutional and legal framework context

##### Institutional Framework

National Level. Regarding land-use management in rural areas—and specifically for the target intervention areas described further down, where neither mining nor oil exploration are significantly at play — three sets of central government entities are particularly important:

- (1) The Ministry of Environment (MINAMB) has a mandate for developing and implementing environmental policies, including the management of protected areas. MINAMB was created in 2008 and is responsible for the coordination, development, implementation, and monitoring of environmental policies, particularly in the areas of biodiversity, environmental technologies, impact assessment and prevention and environmental education. These responsibilities are distributed throughout its central executive services: The National Directorate for Environment, the National Directorate for Biodiversity, the National Directorate for Environmental Impact Assessment and Prevention, the National Directorate for Environmental Technologies and Standards and the Office for Climate Change (GABAC). In 2010 MINAMB established a support advisory body, the Multisectoral Commission for the Environment (CMA) to coordinate and streamline activities that are targeting the protection and sustainable use of natural resources in the country. The CMA’s objective is to promote dialogue between government departments, academic institutions, scientific research and civil society ensuring public participation in environmental management. The National Committee on Climate Change and Biodiversity, coordinated by MINAMB, was created to harmonize programs and policies for the implementation of the National Strategy on Climate Change and Biodiversity preservation; to enable the necessary conditions for the implementation of the National Plan against Climate Change, to develop a National Plan for investments integrating issues related to climate change, and to create centers of excellence in order to carry out research on natural disasters and provide a systematic observation and investigation on climate. GABAC is also the focal point for the global LDN Process, involving all concerned stakeholders.

As the main executing partner, a central player for this project is GABAC is part of the executive services of MINAMB in charge of the National Program for Climate Change and the integration of policies for sustainability in terms of reducing emissions through programs and projects to compensate for GEE emissions.

The Centre of Tropical Ecology and Climate Change (CETAC) is one of MINAMB’s subsidiary institutions. Its core mandate is research (State-driven) and focused on the Central Plateau of Angola. CETAC's current research focus is 75% in Huambo and 25% in the rest of the Central Plateau. They have a nascent GIS lab in a dedicated room with basic equipment (a desktop computer and a plotter.

- (2) The Ministry of Agriculture and Forestry (MINAGRIF), which not only defines agricultural policies but, is also responsible for managing forest reserves through the Institute for Forestry Development (IDF), the rural Land Cadaster through the Office of Rural Land Management and the national efforts towards greater food security through the Office for Food Security (GSA). Various technical institutes are associated with MINAGRIF, such as (a) Agricultural Research Unit (IIA), (b) Veterinary Research Unit (IIV), (c) Institute of Agrarian Development (IDA); (d) Institute of Forestry Development (IDF); and (e) Institute of Veterinary Services (ISV). Especially important for this project, the IDA has a mandate for providing extension services and support to small farmers.

- (3) The Ministry of Territorial Administration (MAT) and The Ministry of Spatial Planning and Housing (MINOTH) have a central role in statutory commissions responsible for land use and spatial planning (“ordenamento do territorio”). MINOTH’s National Institute for Territorial Planning and Urban Development (INOTU) and the Geodesic and Cartographic Institute of Angola (IGCA) both provide technical services linked to the delimitation of land tenure and cadastral registration.

Provincial Level. At the provincial level these four above-listed ministries have provincial directorates. The most relevant for the land-use management include the Provincial Directorate for Environment under MINAMB, responsible for the execution of environmental policies at provincial level; and the Spatial Planning and Urban Development (DPOTUA) under MINOTH, tasked with the management of spatial planning, urban development and housing within each province. The Provincial Directorate for Agriculture and Rural Development (DPADR) under MINAGRIF is responsible for agricultural affairs and represented at the provincial level through its associated Department of Agrarian Development, the Department of Forestry Development, Department of Rural Planning, and the Department of Fisheries and Veterinarian Services. The IDA is also represented at provincial level.

Local (Municipalities and Communes). According to Angolan legislation (D.L. no. 2/07), local administrations have autonomy to manage local land use and competences in the licensing procedures to grant legalization claims both collectively from communities and also from individual citizens. In the development of the country’s planning system, municipalities have the duty to develop municipal planning instruments in the form of Municipal Master Plans (PDM) and Rural Land-Use Plans (POR), among other less relevant types of plans (discussed in more detail further down in Box 1).

Municipalities have, in addition to the Municipal Administrator and a Deputy Municipal Administrator, a technical team with the usual technical competences and a CACS (Council for Social Consultation and Concertation). The same structure is replicated at the level of the commune. The CACS usually include community authorities (the sobas), local associations and NGOs, religious authorities, people of social and economic importance, and companies, among others. Working through municipal or communal administration to support the CACS to play a pro-active role in land-use management. Currently under public consultation, there is a legislative reform planned for the way municipalities function politically, in which the biggest change is that municipal administrators will be democratically elected instead of appointed by provincial authorities. A “Commune Secretary” (replacing the current “Commune Administrator”) will still be appointed by the head of the municipality. Under this reform, the CACS will be replaced by the Municipal Councils. This process will be implemented progressively in a phased approach from 2020 onwards, but the changes that it will bring will not substantially affect the implementation of this project, although it should foresee any adaptations needed in terms of institutional fit.

Figure 6. Field pictures: Epandi-1’s FFS at Selimbondue, Alto Hama Commune, Huambo Province

The EDAs (Stations for Agrarian Development) are IDA’s operational arms in each municipality. Their mandate is to deliver and coordinate extension services within each municipality. They have been a key player in the farmer field schools and agropastoral field schools (FFS/APFS) approach by providing and coordinating facilitators who train the master trainers responsible for the FFSs in rural communities. The EDAs often supervise similar structures at communal level, the CDAs (Agrarian Development Centers).

Rural Communities. The traditional administrative authorities of villages or communities are the “sobas”, who inherit the position or, in some cases, are appointed by the Commune Administrator after consulting the community elders. Decisions and deliberations take place at the “Jango” (shown in top-right picture in Figure 6), a community council that traditionally included only the village elders, but which has recently become more flexible and open to the participation of women and other community members.

##### Legal Framework, Policies and Strategies

Four pieces of legislation are especially relevant in the context of SLM in Angola:

- The Land Law (Law 9/04 of 25th November) and applicable Regulations of 2007 on land concessions (58/07) regulates the general principles on land rights and defines the framework for accessing land, including the criteria for obtaining concessions. In particular, it regulates property rights, rural community rights, natural resources’ use and protection measures, land expropriation, land concession, territorial planning, land classification, and registration procedures. Relevant to the topic of land degradation, it establishes that land-use allocation and management must be executed in a way that does not compromise the regeneration capacities of fertile land and the maintenance of the respective production capacity.

- The Presidential Decree 216/11 establishes the National Policy for Land Concession Rights. It specifies the general basis of the National Policy for Land Concession Rights, defining the mechanisms for accessing, using and exploitation lands, taking into consideration that the access to land is a fundamental for reconstruction, construction and socio-economic development of the country. It applies for agricultural, urban, mining and touristic lands.

- The Planning and Urbanism Law (Law 3/04 of 25th June) regulates the general principles on land, territorial and urban planning. In particular, the Law rules on: land and territorial planning, land classification, and registration procedures. Moreover, the Law indicates the competent authorities and their related functions. In this context, it attributes to the State the duty to organize the territory, with local authorities being obliged to intervene in areas under their jurisdiction, and rural communities having the power to participate in actions related to the organization and preparation of territorial plans. Inhabitants have a right to information about the content of and alterations to the plans, both in the publicizing stage of projects and after their publication. The principles guiding State interventions are: environmental protection; rational use of natural resources; sustainability and public participation.

- The Agrarian Development Law (Law 15/05 of 7th December) provides the basic legislation for agriculture development. The law provides the development goals and rules on farmers and agricultural organizations. Particular attention is given to the agricultural markets as well as the modernization and rationalization of agricultural structures. This law includes forestry as part of agriculture and it integrates the sustainable development principle and environmental considerations explicitly. The law aims to foster the rational use of natural resources in order to achieve a sustained and sustainable increase in productivity, having as fundamental principles the protection of the soil’s productive capacity (respect for regeneration), the preservation of the availability and quality of water resources, and the conservation of the biodiversity associated with the flora and the fauna. The law assigns the State with the responsibility of supporting the development of activities associated with agricultural exploration, especially in rural areas or specific ecosystems. This implies the need for climate change adaptation activities.

Spatial planning is particularly relevant for the scope of this project, to the extent that it proposes to devise practical strategies for how AEZ can contribute to land-use management for SLM at the landscape-level, with decision making support systems (DSS) at the heart of its strategy. In this light, a baseline analysis of how the Angolan system has been structured and effectively works at the local level is instructive. This is presented in Box 1.

Box 1. Options for municipal and local level spatial and land-use planning

According to articles #31, #32 and #33 of the “Spatial Planning Law” LOTU (3/04), there are different types of municipal plans. Those that are relevant to SLM in rural areas are: - Municipal Master Plan (PDM – or Plano Director Municipal), covering the whole of the municipal territory with a dual function because it regulates both urban and rural areas. PDMs have generic strategic guidelines with the purpose of eradicating territorial asymmetries between the urban and rural areas of the municipality, taking into account national and regional options that have an impact on the municipal area. - Environmental Land-Use Plan (POA – or Plano de Ordenamento Ambiental), which is a regulatory plan that lays out the land use and the rules for the protection of natural and environmental assets as well as the rules governing land use in natural reserves. - Rural Land-Use Plan (POR – or Plano de Ordenamento Rural), also a regulatory plan that establishes the rules of occupation and use of the rural areas of the municipal territory. They also set out the models for the preservation and evolution of spatial, natural and human organization, namely, potential areas of mineral exploration, the qualification of agricultural land according to their suitability or types of crop, as well as other assets, including economic, natural, landscape and social aspects of rural territorial spaces, in order to provide better living conditions for citizens. The SLM plans proposed in this project would fit in this category. In an official report* about the progress of the development of territorial plans, there was a total of 205 plans in development or already approved. Of these, 5% were Provincial-Level Spatial Plans (PPOT), 27% were PDMs and 62% were urbanization plans (PU). The PORs (Rural Land-Use Plans) have so far failed to materialize as a functional tool for spatial planning in rural areas.

[*] Refer to: Ministério do Urbanismo e Habitação, Relatório de Identificação e Diagnóstico dos Planos Territoriais, 2013.

In terms of national policies, plans and strategies with relevance for land degradation and SLM, these can be summed in the following list:

##### National plans and strategies

- Angola Development Strategy for 2000 - 2025. The objectives of the Government's Long-Term Strategy entitled ‘Angola Visão 2025’ are to eradicate famine and poverty (therefore giving importance to production sector such as agriculture), natural resource protection, and halting natural resources misuse. The project is more specifically aligned with the objective “to guarantee the sustainable use of the environment, natural resources, and to fight desertification”.

- National Development Plan 2018-2022 (PDN). The PDN for the period 2018-2022 is the second medium-term planning exercise carried out under the National Planning System in force, following the PDN 2013-2017, and aims to promote of the Country's socio-economic and territorial development. The PDN is a prospective and multiannual strategic plan covering the national, sectoral and provincial levels of planning and implements the country's long-term strategic development options as set out in the long-term Angola Development Strategy for 2000 – 2025. Some of the programs in the PDN are closely related to the scope and objectives of this project. Refer to Section 1.5 for more detail on the PDN and its most relevant programs.

- The National LDN Process (2015-2030). Aligned with the global process – and program – of voluntary LDN target setting, Angola has in 2018 adopted the Program for the Definition of Voluntary Goals of Neutral Land Degradation as an effective vehicle to accelerate the implementation of the UNCCD. The main stated goal is to “Achieve by 2030 land degradation neutrality, as compared with the 2015 levels of degradation.” Eight quantifiable targets were established, and several measures proposed. This project will contribute to the achievement of the targets and to the national LDN Process it in different ways (see section 1.5 more specifically).

- National Adaptation Program of Action (NAPA, 2011). Angola submitted its NAPA to the UNFCCC in 2011, the project is aligned with the following priorities set out by Angola: (9) Soil erosion control through organic methods, and (10) Diversify crops to less climate sensitive cultures, the use of locally adapted varieties. Along with the objective to “Strengthening the national capacity in Angolan specialties in the area of vulnerability and adaptation to climate change, thereby guaranteeing a favorable environment for implementing the UNFCCC”.

- Strategy to Combat Poverty (ECP, 2009). The ECP Strategy, approved by Resolution 9/04 of 4 June, includes the reinforcement of agricultural production as one of the key constraints to food security, as well as environmental considerations in accordance with the Millennium Objectives relating to climate change.

- National Strategy for Food and Nutritional Security (ENSAN, 2009). The strategy sets a range of specific objectives to reduce vulnerability to food insecurity by increasing and diversifying agricultural production and productivity in a sustainable manner; ensuring availability and sustainability of food supply chains; improving food accessibility; improving basic health, education and sanitation to minimize levels of malnutrition; establishing and implementing early warning and monitoring systems; and protecting public health by ensuring food safety and drinking water.

##### Sectoral policies, plans and programs:

- Agricultural Sector Mid-term Development Plan 2018 – 2022 (PDMPSA, 2018). The plan seeks to overcome the serious deficit of the sector’s offer in the internal market and modernize production processes, currently inadequate to compete in global markets. The PDMPSA is perfectly aligned with the objectives of this LD project, in that it recognizes the pressing need for “the creation of conditions at the central (capital) and local level (areas of agrarian activity) for the rigorous production of data which, after treatment, would become important agricultural statistical information” as “a reliable basis for drawing up coherent plans, projects and work programs”.

- Integrated Municipal Program for Rural Development and Combating Poverty (PMIDRCP, 2010). The major objective of the PIDRLP is to quickly overcome the economic dependence on the oil and mining sectors by developing the agricultural sector and by pursuing the fighting against poverty, the eradication of food insecurity and agricultural intensification. The program is aimed at improving the food security and nutrition of smallholder farmers. The 2019 state budget proposed for this program 652 million kwanzas (around 2 million US$) but there is another related program “Local Development and Fight Against Poverty” with 91,113 million kwanzas (around 30 million US$) to this program.

- National Action Plan on Food Security and Nutrition (PASAN). The Strategy recognizes the right to food as fundamental and aims to create conditions to guarantee that every Angolan citizen has lasting food security, reducing the level of inequality in income distribution and structurally reducing extreme poverty.

- The National Environmental Management Plan for 2012-2017. Establishes key priorities for the conservation and sustainable use of natural resources and thus supports the mainstreaming of sustainable land management practices into sector policies.

- National Strategy for Climate Change 2018-30 is under development and it is slated to include the agricultural sector and family farmers as potential agents for positive change.

- National plan for preparation, contingencies, response and recovery from calamities and natural disasters. The general objective of the National Plan for Preparation, Contingencies and Response is to define the lines of force that guide a suitable and concerted response, the conditions and the essential means to minimize the adverse effects of serious accident or catastrophe that affects the Angolan population.

This background framework is complemented by the ongoing and planned projects and initiatives that form the project’s baseline (financial and technical). It is described further down in section 3.2 Baseline Initiatives.

### 1.1.2 Project intervention areas

The Project’s Focus Zone (shown below in perspective): The Central Plateau of Angola, which has its heartland in Huambo Province and extends into parts of the neighboring provinces of Benguela, Bié and Cuanza Sul, is a “hotspot” for both assessing and addressing on the ground the issue of land degradation.

Figure 7. The Focus Zone and the Wider Landscape within the national geographical context

Note: Refer to Annex A PRODOC Atlas for higher resolutions imagery.

Huambo and Benguela Provinces. For different reasons, both the two provinces are especially important in the context of land degradation. In addition, other factors justify their selection as the geographical focus of this SLM project. The Central Plateau is of immense ecological importance for biodiversity, agriculture and natural resource management in Angola – not least also due to the fact that it is the source of Angola’s major water basins. Major rivers such as the Okavango, Cunene and Queve originate in Huambo province, where its catchments also contribute to rivers such as the Cubango and Cuanza. Preserving the ecological quality and volume of these watercourses at their head is of extreme importance for their function as ecological corridors and the ecosystem services provided by these rivers. In Huambo the vegetation types are predominantly associated to Miombo forests.

The project’s Component 1 will contribute to building capacity, structures and resources at national level regarding the AEZ, environmental monitoring and using products related to these for decision making support. In the development phase of CETAC’s spatial planning capabilities, the focus will be on two provinces: Huambo and Benguela. Component 2 and, in part, Component 3 will be exclusively implemented in these provinces.

Within Huambo and Benguela, a Wider Landscape, covering 6.1 million ha, has been selected as the specific target for land degradation monitoring activities and AEZ.

‘The Wider Landscape’ will therefore function as the indirect target for SLM, whereas the ‘demo landscapes’ will be the direct target.

Table 1. The Wider Landscape: Overview of the resident rural population per municipality

| Total count = 17 | Municipalities within the Wider Landscape (indirect SLM targets) | Surface area of municipalities concerned (ha) | # of Communes within municipality | TOTAL rural population (2014 Census) | of which women (~52%) |
| --- | --- | --- | --- | --- | --- |
|  | Huambo (all municipalities) | 3,415,559 | 37 | 1,056,356 | 556,633 |
| 1 | Bailundo | 721,448 | 5 | 217,711 | 115,243 |
| 2 | Caála | 438,036 | 4 | 128,290 | 66,936 |
| 3 | Catchiungo | 287,465 | 3 | 68,531 | 36,050 |
| 4 | Ecunha | 148,592 | 2 | 43,173 | 22,795 |
| 5 | Huambo | 297,886 | 3 | 278,080 | 145,164 |
| 6 | Londuimbale | 263,220 | 5 | 79,571 | 42,747 |
| 7 | Longonjo | 241,937 | 4 | 53,209 | 28,017 |
| 8 | Mungo | 305,070 | 2 | 57,188 | 30,564 |
| 9 | Tchikala-Tcholohanga | 435,116 | 4 | 82,905 | 43,966 |
| 10 | Tchinjenje | 106,985 | 2 | 16,899 | 8,941 |
| 11 | Ukuma | 169,805 | 3 | 30,799 | 16,211 |
|  | Benguela (non-coastal municipalities) | 2,721,405 | 7 | 412,852 | 219,578 |
| 1 | Balombo | 274,796 | 1 | 39,728 | 21,078 |
| 2 | Bocoio | 580,694 | 1 | 61,778 | 32,972 |
| 3 | Caimbambo | 352,958 | 1 | 80,715 | 42,655 |
| 4 | Chongorói | 621,002 | 2 | 32,590 | 17,282 |
| 5 | Cubal | 443,489 | 1 | 115,172 | 61,349 |
| 6 | Ganda | 448,467 | 1 | 89,867 | 47,956 |
|  | TOTAL | 6,136,964 | 44 | 1,469,208 | 776,211 |

Source: INE 2014 Population Census; GIS data managed by PPG Team.

Figure 8. Project landscapes in context: The Wider and Demo Landscapes plus Municipalities

Note: Refer to Annex A PRODOC Atlas for higher resolutions imagery.

For the demonstrative integration of AEZ-based SLM in planning and decision-making, this project has selected specific areas of intervention located in Huambo and Benguela Provinces called demonstration landscapes (or demo landscapes), and within which the work on the ground will be developed under Component 2. The three selected demo landscapes comprise: (1) the communes of Alto Hama, in the municipality of Londuimbali; (2) the rural commune of Bailundo in the municipality with the same name; and (3) the commune of Chongoroi in the municipality with same name. The communes of Alto Hama and Bailundo are in Huambo Province and Chongoroi is in Benguela Province. The three selected demo landscapes have a combined approximate productive landscape of some 410,000 hectares, thus divided: site 1 with 57,000 hectares; site 2 with 269,000 ha and site 3 with 84,000 ha (more exact numbers in  Table 2). As of 2014 the selected communes respectively harbored a rural population of: (site 1) 9,000; (site 2) 25,000 (site 3) 50,000 – totaling 84,000 people and with an average of 53% women among them.

All three demo landscapes are located within the sub-humid agroecological zone of Angola, but it is much more arid in Chongoroi than the other two. Alto Hama and Bailundo display altitudes of 1400 - 1700 m, whereas Chongoroi reaches altitudes of 748 - 850 m, a factor that influences climate, land use and erosion risks, differentiating these landscapes. The matter is discussed in the PRODOC Atlas through maps (Annex A). Land uses vary across the landscape in a gradient, and as shown in Figure 8. The break-down of the most relevant land uses per site, and the severity of land degradation within them, are displayed in Table 2.

Table 2. Selected LD3 – Program 4 Tracking Tool Questions (TT-Qs) applied to demo landscapes

LD3 – SLM, PROGRAM 4) TRACKING TOOL QUESTIONS [TT-Qs] Applied to Demo Landscapes *

| [TT-Q 1.] Agroecological context | Demo Landscape [1] Alto Hama Commune (Agricultural) |  | Demo Landscape [2] Chongoroi Commune (Rangelands) |  | Demo Landscape [3] Bailundo Commune (Agricultural) |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Characterization of area in which project is located & of the Land Degradation Problem | [TT-Q 1.b.] Production Systems with break-down | [TT-Q 1.c.] Extent of land degradation in production systems ** | [TT-Q 1.b.] Production Systems with break-down | [TT-Q 1.c.] Extent of land degradation in production systems ** | [TT-Q 1.b.] Production Systems with break-down | [TT-Q 1.c.] Extent of land degradation in production systems ** |
|  | ha | % | ha | % | ha | % |
| i. 'Agriculture' | 37,510 | 26% | 56,100 | 27% | 31,299 | 57% |
| ii. Rangeland | 0 | 0% | 77,892 | 41% | 8,411 | 0% |
| iii. Pastoral | 2,853 | 0% | 16,000 | 40% | 2,726 | 0% |
| iv. Forestry | 9,825 | 13% | 54,500 | 58% | 10,934 | 10% |
| v. Mixed Systems | 6,867 | 63% | 64,040 | 45% | 30,742 | 70% |
| TOTAL (= 409,699 ha productive landscapes) *** | 57,055 | 27% | 268,532 | 42% | 84,112 | 48% |

Notes:

*	Refer to PRODOC Atlas in Annex A for maps that illustrate the above and more details in the Tracking Tool submitted separately. LD3 Program 4 refers to LD3 – SLM in wider landscapes (integrated management). The general goal of LD3 programs is to reduce pressures on natural resources by managing competing land uses in broader landscapes, which is in line with the project’s objective. The break-down per production system are estimates based on available data and visual interpretation of satellite imagery. Under ‘productive systems’, areas that were classified as ‘iv. Forestry’ includes habitats that may be best suited for ‘forest protection’ or ‘conservation of ecosystem services’—as opposed to ‘production forests’ or ‘forestry’ land uses, strictly speaking. They were included in the targets for demo site, so that AEZ exercises that are slated to be carried out during project implementation would determine their optimal use.

**	The areas considered "degraded" were based on an existing LDN data obtained using the Trends Earth plugin. The guidance framework contained in the knowledge portal of the United Nations Convention to Combat Desertification (UNCCD) was actively used in the above-mentioned assessment. (http://knowledge.unccd.int). A keystone publication on the subject that was consulted includes Orr, B. et al. 2017. "Scientific Conceptual Framework for LDN").

***	Beyond the targeted productive landscapes, which corresponds to 93%, 35% and 97% of the total surface of the three respective communes of Alto Hama, Chongoroi and Bailundo, the communes also encompass areas classified as ‘non-productive’, and which are not targeted by the project. Thy include urban, industrial, bare rocks areas plus others not suitable for production. It would also have included protected areas, but none are found within demo landscapes.

The most important criteria for selecting the above-mentioned demo landscapes were: (1) the confirmed presence of active FFS/APFSs, and hereunder the level of advancement within their implementation cycle; and (2) the potential for generating global environmental benefits (GEB), i.e.  the potential for the project to work directly with the concerned communities within the demo landscapes, and within them establishing demo sites at micro-landscape level for community management and SLM planning. In this manner, the communities would be protagonists in the process of adopting SLM plans and practices (discussed in more detail in the description of Component 2). Other criteria for selecting demo landscapes were also considered: e.g. the degree of maturity of the FFSs’ development in Londuimbali and Bailundo, and the status of soil erosion within these communes, which is a proxy indicator of the severity of land degradation at the landscape level, accessibility and participation during PPG consultations.

Together, the demo landscapes also represent samples of the different agroecological conditions within Central Angola (see PRODOC Atlas in Annex A). For example, at the landscape’s micro-level, looking at fine-scale maps with focus on the areas where demo villages are located and surrounding landscapes, all of which are areas managed by these communities, there is a varied mosaic of land uses. These include spots where land degradation is moderate to severe—and land needs to be restored—as well as areas where land is fertile and ecosystem services flow, where conservative land use would be prescribed. And there are yet areas where a preventive approach to land degradation would be bound to show results. Resolving what is prescribed for each different site, landscape or spot is something that the project will do within demo landscapes

The combination of the above-mentioned criteria and conditions provide the best option for working with communities that are being assisted by active extension services, and, through the work of the project, generate global environmental benefits by changing land-use practices on the ground towards SLM. Local stakeholders, including members of the communal and municipal governments, were consulted on the project and manifested a strong interest in it.

Finally, because of the dynamic nature of the implementation cycle of AP/FFSs, which then reflects on their ‘level of advancement’, the project will have the flexibility of adjusting the selection of the specific communities it will work with within the demo landscapes.

While there are many ‘considerations’ and 'entry points’ with respect to in the application of spatial planning and decision-making tools for managing landscapes or land uses for SLM, an explanation on how the project will handle and integrate the different scales, a ‘nested approach’ to landscape level management is proposed. It resembles the ‘scheme of Matryoshka’ dolls, where one fits inside the other and are affiliated with each other, but they can also be used as ‘stand-alone’. See the following content further down for explanations:

Box 2. The tiered nested approach to spatial planning and landscape-level management for SLM

Box 3. Three tiers within the nested approach to landscape level management applied in the project

Through a nested approach, the pursuit of SLM in Angola will be able to benefit from a multi-criteria logic and priority setting methods which can be embedded into AEZ exercises, as the national capacity for spatial planning expands. Further applications may include multiple scales and with multiple entry points, including beyond the project and according to needs.

Box 2. The tiered nested approach to spatial planning and landscape-level management for SLM

| The tree to four nested scales (or levels) that apply to the project in its strategy, as follows: |  |
| --- | --- |
| Schematic illustration of interactions and interrelations among ecological and jurisdictional scales in a nested approach to landscape-level management |  |
| Source for the above figures (except for the inverted pyramid): Minang, P. A., Duguma, L. A., Alemagi, D., & van Noordwijk, M. (2015). Scale considerations in landscape approaches. In Minang, P. A., van Noordwijk, M., Freeman, O. E., Mbow, C., de Leeuw, J., & Catacutan, D. (Eds.) Climate-Smart Landscapes: Multifunctionality in Practice, 121-133. Nairobi, Kenya: World Agroforestry Centre (ICRAF). |  |

Box 3. Three tiers within the nested approach to landscape level management applied in the project

| From Theory to Practice: Planning & Land-use Management Practices at the ‘Wider Landscape’, ‘macro’ and ‘micro’ levels |  |  |
| --- | --- | --- |
| Level ❶ | Level ❷ | Level ❸ / ④ |

## 1.2) THE CURRENT SITUATION

### 1.2.1 Main Environmental Threats

#### Threats, root causes and drivers

The causes and the extent of land degradation. Various generic causes of land degradation are presented in Figure 9 along with the most common drivers behind them. In Angola, the single most important proximate cause of land degradation is linked to agricultural activities and, more specifically, to the prevalent practices in the agricultural sector.

At the level of landscapes in both Huambo and Benguela Provinces, three types of land-use practices, under the ‘agricultural activities’ broad category, referred to in the mentioned figure, impact the stock, as well as the flow of ecosystem services, leading thereby to land degradation:

- (i) shifting cultivation, where increased competition for land is now making this land use unsustainable;

- (ii) overgrazing, which affects the fragile balance of the more arid rangelands, and

- (iii) the excessive use of fire across landscapes, resulting in significant loss of above ground biomass, and whose stocks may or may not seasonally recover, depending on local circumstances.

Figure 9. Proximate and underlying driving forces of LD (not context-specific)

Source: Adapted from Geist and Lambin (2004) by Davies et al., 2015 [Davies J., Ogali C., Laban P. and Metternicht G., 2015. Homing in on the Range: Enabling Investments for Sustainable Land Management. Technical Brief 29/01/2015. Nairobi: IUCN and CEM. Vi+23p].

In the grasslands and woodlands of Huambo and Benguela Provinces, land-use change is primarily driven by shifting cultivation (See Figure 10). This type of practice is a widely spread land use, it takes place in areas that are either native or secondary forest/woodland and which are converted into croplands on a rotational basis, in arable that is increasingly scarce and marginal. In the drylands and rangelands of Benguela province, pastoral land use, rather than shifting cultivation, is the most prominent agricultural activity. In those areas, when the livestock grazing pressure exceeds certain thresholds, it becomes overgrazing. In addition, fire is extensively used across the landscapes in the two provinces, primarily for facilitating land-use change. The current extent, intensity and frequency of these fires exceed, by several orders of magnitude, the natural fire cycle for the landscape, creating pressure on natural resources. In fact, 2018 became a peak year for fires both in Huambo and Benguela. (See Figure 11 further down).

Root causes and land-use change dynamics. The above-presented land-use patterns within the Project’s Focus Zone have a historical reason. At the beginning of the 20th century, when the caravans of the rubber trade ended, and the Portuguese occupied the Central Plateau, men started to participate in agriculture.  Previously, it was an activity almost exclusively practiced by women (men cultivated only the ‘ochumbo’ – the small field around the dwelling.) Men became farmers, and rapidly adopted strategies aimed at marketing their produce. This new type of agriculture required more land, and ploughing with animal traction, which had been introduced by Protestant missionaries in the 1930s and made such expansion possible. Demographic pressure and increased European settlement reduced the length of fallow periods of shifting cultivation systems, which were likely sustainable in the absence of increased pressure. Previous points of balance were ignored and, overtime, increased pressure resulted in the destruction of native woodlands in favor or crop production, increasing thereby the risk of soil erosion. These processes combined ended up reducing soil fertility, eventually affecting production volumes and productivity per unit area.

Figure 10. Dominant drivers for tree cover loss in the Project Zone according to global sources

Note: Refer PRODOC Atlas in Annex A for higher resolution imagery.

Figure 11. Record of active fires in Project Zone according to the global sources

Note: Refer PRODOC Atlas in Annex A for higher resolution imagery.

Currently, the principal cropping system in Huambo still relies on a system that regularly incorporates unconverted natural land into cropland through the use of fire (termed the ‘slash-and-burn’ technique). Across the tropics, fire is actively used by farmers as a means of recovering soil fertility and preparing the land for other uses. In Angola, and in the Central Plateau in particular, fire is also used in the landscapes that surround the villages for hunting or extracting honey. Clearing grasslands by preventively setting fire to dry grasses also serves to create landscape visibility around the villages, and thereby reducing the risk of predators or elephants eventually attacking human settlements. Furthermore, controlled fire may also be used in the end of the dry season as a way of preventing more destructive wildfires.

At the landscape level, practices such as the preventive and active use of fire, as well as shifting cultivation are widespread and prevail. If used moderately, and in a timely and controlled fashion, such practices are not necessarily a major threat to landscape integrity, but in certain settings they may be. The critical factor is though ‘population pressure’ – and hereunder including the demographic, economic and technological factors mentioned in Figure 9.

These factors, which are the direct drivers of land degradation in Angola, will determine the effective access by land users to either arable land or pasture, depending on ‘land suitability’. Land and pasture are becoming increasingly scarce in the Huambo-Benguela axe. As a result, the long fallow period required for recovering land productivity is not respected. Across large landscapes and over the years, soils will invariably become degraded, if the natural vegetation cover repeatedly loses biomass. This loss can be quantified, along with visible processes such as top soil loss (erosion). Both tree cover loss (shown in Figure 12 is a proxy) measurements of soil organic carbon are proxies for monitoring land degradation process linked to loss of top soil, of biodiversity and ecosystem services, and of land productivity altogether.

Figure 12. Tree cover loss statistics for Huambo and Benguela according to GFW

Source: Global Forest Watch Dashboard, Angola Data for regions ‘Benguela’ and ‘Huambo’, retrieved on 15 Oct 2018. Note: Refer PRODOC Atlas in Annex A for maps and more details and the above figures in higher resolution.

Across Angola – including in the Project’s Focus Zone – the pressure for accessing land and for using natural resources has increased significantly in the past 18 years, to the point that the customary practices, which may have kept ‘land in balance’ in previous decades, are now unsustainable. This is illustrated by LDN readings, which for Angola show a general picture of concern (see PRODOC Atlas in Annex A).

Core LDN parameter across the Project’s Focus Zone also point out to opportunities for recovering land productivity and achieving ‘neutrality’ vis-à-vis land degradation if unsustainable practices at farm, village and commune level can be addressed, and if enforcement of sustainable land use can be applied and enforced e.g. at municipal, rural zone and even at the province levels. (see e.g. Figure 13 further down, where land productivity is displayed. In various landscapes across Huambo, this parameter is improving.)

Figure 13. Land Productivity Dynamics in Angola according to the global sources

Source: “Definition of the Land Degradation Neutrality Voluntary National Targets (LDN-TSP)” .Ministry of Environment. November 2018

Quantification through global assessments. Angola is only beginning to properly assess the impacts of widespread land-use change nationally. According to PPG surveys, there are no comprehensive national systems for monitoring deforestation and forest degradation, which could provide accurate information on the issue of land cover and land cover change, as well as carbon stocks.

However, by drawing from Global Forest Watch (GFW) assessments, it is notable that between 2001 and 2014 Angola lost some 1.7 million ha of forest coverage (calculated at min. 30% canopy cover). This implies an average of 120,000 ha per year, amounting to 3.4% of the total baseline of forest cover as of 2000, raising concerns about the rate of deforestation in Angola, in particular because of the accelerating trend. A cursory analysis of forest cover loss from GFW clearly shows that deforestation is a serious problem, not just across the country, but also in the Central Plateau (report reproduced in PRODOC Atlas in Annex A and derived from it):

- ln 2010, Angola had 43.6 million hectares of tree cover, extending over 35% of its land area.

- From 2001 to 2017, Angola lost 2.45 million hectares of tree cover, equivalent to a 5.6% decrease since 2000 and 167Mt of CO₂ emissions.

- ln 2017 alone, which was the ‘peak year’ in the mentioned series, Angola lost approximately 280,000 hectares of tree cover, equivalent to 18.3Mt of C02 of emissions.

- Nine provinces were responsible for 55% of all tree cover loss between 2001 and 2017: Cunene had the most relative tree cover loss at 19% compared to an average per province of 6.9%, followed by Huambo with a 16%-share. Benguela is number 4 among those, with 11%, and after number 3, Huila, which contributed with 15% of all tree cover loss in Angola in the reporting period.

Based on GFW data, it can be concluded that unsustainable land-use practices leading to tree cover loss across the landscapes are threatening ecosystem services at a significant rate. These trends can be quantified (see Figure 12). It is also notable that these threats have been unequally spread within Huambo and Benguela Provinces respectively. Figures are slightly higher in Huambo than in Benguela: tree cover loss was 16% in the former during 2001-2017 at 30% canopy cover, as opposed to 11% in the latter. Yet, the threats to ecosystem services linked to land-use change, fire and soil overuse are equally serious in both provinces. The differences are discussed in the PRODOC Atlas in Annex A where more details are provided.

On-farm dynamics (micro-landscapes). Loss of land productivity affects croplands, and therefore farmers, in many different ways. In both the targeted provinces, Huambo and Benguela, the already low crop productivity is declining in several municipalities due to deteriorating soil fertility. Smallholders are generally risk averse and they will need to assess options for intensifying production systems, since additional fertile land is not available for maintaining the traditional shifting cultivation and slash-and-burn practices.

Intensifying production methods generally include the application of fertilizers and irrigation in in commercial agriculture or, in the context of agroecology, the application of methods like crop rotation or alternation with nitrogen-fixing plants.

Given that 60% of rural households in Angola are either poor or very poor, the costs of obtaining improvements in productivity are prohibitive to the large majority of small farmer in Angola. They have very limited access to extension services, market information and modern agricultural inputs. Literacy rates are also lower in rural areas and lower among women (as seen in section 1.1). Hence, a major challenge for them in terms of achieving SLM at farm-level, is finding ways to produce enough food for local food-security while preventing land degradation.

Even amongst farming households that are food-secure, a broad range of issues constrain potential market-oriented production: e.g. limited scientific knowledge on land features and its potential, as well as on the range of possible techniques for improving productivity, adjusting land suitability. Another constraint is limited marketing experience, lack of household resources to buy seeds and inputs, limited skills to engage in alternative off-farm occupations. In the absence of viable credit programs, very few smallholders have the means needed to purchase even small amounts of the required inputs.

Competition between small-holders and commercial farmers is on the increase, with potential conflicts being exacerbated by an apparent scarcity of available land with tenure rights adequately asserted. Even more importantly, the potential for orienting agricultural production towards markets in a sustainable manner is limited by loss of soil fertility and thus efforts towards market production need to be combined with the generalized adoption of SLM. This is particularly the case in agricultural areas surrounding urban centers, where urban sprawl and intense demand for agricultural produce exacerbate tensions between competing land uses.

According to the comprehensive environmental baseline assessment conducted by the consultancy firm Angola Alliance in 2003, most soils in Huambo – and in the Central Plateau and surrounding landscapes more generally – are degraded, particularly in the areas where people have converged in recent years. The situation was already worrying at the beginning of the 1970s, and the concentration of population in certain areas have exacerbated the situation. Recent studies indicate serious lack of phosphorus and micronutrients.

On the other hand, water erosion has been intense in these areas, often producing very visible damage to the landscape in the form of ravines. At the landscape level, unsustainable land use practices affect farm dynamics in a rather visible way (with reference to the ‘micro-landscapes’). The removal of the vegetation cover often leads to accelerated runoff in key drainage areas that are left exposed and vulnerable to intense rainfall, resulting in gullies and eventually ravines that can be very difficult to repair. Several farmers, as well as and herdsmen/women consulted at visited sites during the PPG confirmed the above trend from their perspective.

Less visible but equally serious, are the subtle changes in soil structure and loss of nutrients that occur in bare soil that is exposed to water runoff. This alternation between drought periods and resulting weakened vegetation and intense periods of precipitation is a self-reinforcing vicious cycle of land degradation in these provinces.

#### Specific Drivers behind the Causes of LD in the Project’s Focus Zone

The specific dynamics of land degradation in the Central Plateau are complex, they happen at different levels (the wider, macro and micro-landscapes) and they are closely linked to the sustained quality of soils, the availability of water, as well as the agricultural techniques applied.

Land-use systems in the Project’s Focus Zone are varied and it is possible to observe the co-existence of subsistence agriculture practiced by small-holders side-by-side with increasing presence of modern agricultural enterprises targeting commodity production. Driven by demand, this type of land use aims at supplying remote markets either in other parts of the country or abroad. These practices increase competition for land across the landscape and function as driver of land degradation.

Geographically outside the Central Plateau, Chongoroi’s rural economy is more or less equally divided between agricultural and pastoral activities, being the Northern tip of Angola Southwest transhumance routes. According to the RETESA project, in these rangelands, a situation of equilibrium in their management of rangelands can be disturbed by shifts of climatic conditions and/or competition for land. When the rains are plentiful, there is a tendency towards growth in the livestock population, to the extent that palatable grasses become available. When these are diminished, sustaining the high stock numbers will either require more land or increased mobility – or else, it will result in overgrazing and in the degradation of land as a consequence. Furthermore, commercial cattle ranchers encroach upon traditional grazing lands and cattle corridors are being closed. Finally, increased aridity in lands that are marginally suitable to agricultural production is also resulting in less edible pasture and adding further constrains. This can either be a natural phenomenon or man-made. In highly arid areas, where only purely pastoralist systems can persist— land use is mostly ‘self-governed’ and follows the traditions of the local tribes that have occupied the area for centuries. Generally, land degradation is less of a problem in those areas, which seem to be in equilibrium but, in reality, the status and trends are not well studied.

Another driver of land degradation relates to low capacity of the governance systems to address the adverse effects of land degradation. Local officials responsible for land-use management have limited knowledge of SLM techniques, few incentives for adopting improved practices and limited extension services to support their efforts. In addition, government authorities who are responsible for planning have limited capacity for cross-sectoral coordination, limited access to GIS and AEZ products (and limited capacity to use them when they do have them), and inadequate capacity to provide technical and economic incentives for the widespread uptake of SLM practices.

The basic model that summarizes the driving forces of land degradation was presented in the diagram in Figure 9, which includes direct and indirect causes of land degradation, and where the latter are the drivers behind the process. They include: demographic, economic, technological and climatic factors. For this project, all of the above-mentioned drivers apply, but to different degrees, as validated by ‘land degradation driver analysis’ contained in the 2013 PANCOD, even though the mentioned national plan does not use the same framework as in Figure 9. The PANCOD points out to the following main causes of land degradation and desertification in Angola: farming practices, fire-based hunting, deforestation and bushfires. The main degradation types are soil erosion, declining biomass productivity, degradation of soil properties (chemical, physical, and biological), and loss of vegetative cover due to fires and forest clearing for charcoal production and agricultural or pasture conversion.

In turn, land degradation and desertification processes are perceived by local stakeholders as having the following direct causes (i.e. pressures): unsustainable agricultural management, deforestation and unsustainable use of forests, overgrazing in rangelands areas, pollution from mining and lack of rehabilitation of mining areas, and climate change. Socio-economic pressures (indirect causes or drivers) include low level of awareness by both the farmers/herders and local leaders on the economic benefits of soil protection and investments, the degraded state of agricultural equipment and infrastructure (e.g. warehouses, silos, water points), and poverty. All of these are aggravated by the poor provision of extension services.

### 1.2.2 Baseline Initiatives

Various projects and programs compose the baseline for this project, to the extent that they are well aligned with the Project’s objective and can provide a platform for collaboration, technical integration and co-financing. Such initiatives are implemented by the government, academic and research institutions, and local and international partners, including NGOs and FAO. Some are supported through development cooperation. The private sector is also investing in geo-referenced data generation for land-use management in Angola, as well as agricultural development.

The next table (Table 3)  provides, a comprehensive assessment of the baseline finance, while Table 4, further down, a quick overview of the baseline / co-financing calculus. Yet further down, in Table 5, the details of governmental programs that compose the baseline investment from Angola’s Central Budget (OGE) is outlined.  Finally, and overview and details on both past and on-going projects, including GEF-funded, and which are relevant to land degradation in the proposed Project Focus Zone, are included in Table 16, noting that although important, the latter group of interventions do not constitute a financial baseline of the project.

Table 3. Baseline Finance: List with Descriptions and Co-financing from Baseline ($M)

| # | Acronym | Baseline Project / Program / Initiative | Objective / Focus Area / Relevance to the Project | Duration | Relevance for the project's Comp. | Baseline estimates $ million | Co-financing from baseline $M |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | PDN OGE MINAMB, Climate change | PDN relevant programs allocated through the Central Budget (OGE) MINAMB (DNB e INBAC) / PDN Program # 2.4.1: Climate Change; source: Government of Angola | Governmental investment baseline from the National Development Plan (PDN) 2018-2022, referring to a baseline contribution from MINAMB (DNB e INBAC), resources assigned through OGE for PDN Program # 2.4.1: Climate Change, at 2,775 Million Kwanzas in 2019, equiv. to $9.25M, at a 100% relevance (see note on project indicator for Component 3 at the end of this table). The extrapolated amount considered as baseline from PDN Program # 2.4.1 for the period 2019-2022 is $25.9M. (Refer to Table 5 for further details and the break-down per Component and year.) Part of the Project’s co-financing from MINANB comes from this baseline investment, as of the last column in this table (see a summary in Table 4). | 2019-2022 | 1,2,3 | 25.9 | 8.0 |
| 2 | PDN OGE MINAGRIF, Agricultural Production | PDN relevant programs allocated through the Central Budget (OGE) MINAGRIF / PDN Program # 2.3.2: Promoting Agricultural Production; source: Government of Angola | Governmental investment baseline from the National Development Plan (PDN) 2018-2022, referring to a baseline contribution from MINAGRIF, resources assigned through OGE for PDN Program # 2.3.2: Promoting Agricultural Production, at 31,620 Million Kwanzas in 2019, equiv. to $105.4M, at a 5% relevance. The extrapolated amount considered as baseline from PDN Program # 2.3.2 for the period 2019-2022 is $14.8M (Refer to Table 5 for further details and the break-down per Component and year.) Part of the Project’s co-financing from MINAGRIF comes from this baseline investment, as of the last column in this table (see a summary in Table 4). | 2019-2022 | 2,3 | 14.76 | 3.0 |
| 3 | PDN OGE MINAGRIF (DNF), Forests | PDN relevant programs allocated through the Central Budget (OGE) MINAGRIF (DNF) / PDN Program # 2.3.4: Promoting the Sustainable Use and Management of Forest Resources; source: Government of Angola | Governmental investment baseline from the National Development Plan (PDN) 2018-2022, referring to a baseline contribution from MINAGRIF (DNF), resources assigned through OGE for PDN Program # 2.3.4: Promoting the Sustainable Use and Management of Forest Resources, at 572 Million Kwanzas in 2019, equiv. to $1.9M, at a 25% relevance. The extrapolated amount considered as baseline from PDN Program # 2.3.4 for the period 2019-2022 is $1.6M. (Refer to Table 5 for further details and the break-down per Component and year.) Part of the Project’s co-financing from MINAGRIF comes from this baseline investment, as of the last column in this table (see a summary in Table 4). | 2019-2022 | 1 | 1.6 | 1.5 |
| 4 | OGE CETAC under MINAMB, recurrent institutional budget | Central Budget (OGE) institutional allocations, source: Government of Angola | CETAC – The Centre of Tropical Ecology and Climate Change, where an approximate annual budget for CETAC's running costs was assessed at $842,571 in 2019. Extrapolated for the project's duration, a total baseline amount of $2.53M was considered, of which $1.5M will serve as co-financing to the project. An additional, non-baseline amount for CETAC also contributes to co-financing, in-kind, at $0.5 million, as stated in MINAMB's letter of co-financing. | 2019-2022 | 1,2,3 | 2.53 | 1.5 |
| 5 | WB PDAC/CADP | WB Angola Program in Angola on Agriculture (PDAC/CADP) | WB Angola - Angola: Commercial Agriculture Development Project – (P159052) has been recently signed. The program aims to promote commercial agriculture development, increasing production and employment within selected value chains, in targeted areas in Angola – total is $230 million, of which at least $21,1 million is directly relevant to the project and was accounted for as baseline finance. The overall objective of the PDAC/CADP is to promote the sustainable transformation of subsistence agriculture to a commercial orientation, with the aim of achieving food security in the country. The Project is being implemented in Huambo, Bie and Malange Provinces. Program components include: Farmer Field Schools, good practices on agriculture systems, processing and access to markets in an inclusive way. FAO has a role in supporting implementation of certain aspects. There are good prospects of linking the work of scaling up the Field Schools (Component 2) and strengthening the results together with partner agency IFAD, which works nationally under the FAO representation in Luanda. | from 2017 (end date t.b.d.) | 1,2,3 | 21.0 | - |
| 5 | IFAD SREP | IFAD -SREP - Smallholder Resilience Enhancement Project (pipeline, no amount yet defined) | Project SREP's objective is to enhance agricultural productivity and resilience of households affected by climate change by developing the adaptive capacity of farmers, support service providers and policy makers to better manage the production landscape. It will be implemented in the Provinces of Benguela, Bengo, Kwanza Norte, Uíge, Zaire, Cunene and Namibe. The Project is particularly relevant because it also adopts the landscape approach with MINAGRIF's IDA playing a key role. Depending on the agreed funding source and modality, the project may or may not represent co-financing to the FAO GEF Project. The Project's budget can reach $100M. For the purposes of baseline calculations, an amount of $12M was considered for now. | 2019-2025 | 1, 2, 3 | 12.0 | - |
| 6 | IFAD-FAO ARP | IFAD FAO ARP - Agricultural Recovery Project | With focus on Rural Development, Project ARP has been signed in 2017 for $7.6M. Its objective is to contribute to improved food and nutrition security and targeted communities; restore productive assets and capacity of households affected by recurrent droughts. It is being implemented in Benguela Project (Chongoroi, hence highly relevant for this FAO-GEF Project), as well as Cunene, Huíla Provinces. The project will focus on supporting smallholder farmers that have lost their agricultural production capacity by promoting sustainable farming practices and climate smart agricultural technologies adapted to local conditions. It will also improve information systems for food security and animal health surveillance, introduce proper rangeland management systems and promote livestock-based livelihood diversification activities as part of a "building back better" strategy. ARP will intervene in three southwestern provinces: Benguela, Cunene and Huila. About 8,000 households, 30 per cent headed by women, and 30 per cent including youth, will be reached. | 2018-2025 | 2, 3 | 7.6 | - |
| 7 | AFDB Agric Value Chains | AfDB Project Support to Angola's Sustainable Development and Growth - 'Angolan agriculture value chains development project' (pipeline, indicative budget $168M) | AFDB Agric Value Chains Project will be implemented in 16 out of 18 Provinces in Angola. It will be a comprehensive sustainable growth program, with focus on developing staple foods value chains, including cassava, vegetables, soybean, flour, livestock and others. Project Components are: 1. Value chains development; 2. Infrastructure; 3. Project management. The AFDB Agric Value Chains Project is relevant to the objective of the GEF FAO Project to the extent that rapid development of the agricultural sector across the country through investment can have negative impacts on ecosystem services, e.g. through unplanned land clearances, unless sound and evidence-based policies focusing on land-use change can be put in place. The FAO GEF will contribute to this goal. Hence, the potential for cooperation through all three components of the FAO GEF Project should be explored early on and partnerships sought. For the purposes of calculations, an amount of $12M was considered as baseline on an interim basis. Likely duration is 5-6 years. | 2019-on (end date t.b.d.) | 1, 2, 3 | 12.0 | - |
| 8 | Three Misc Progr (other) | Other miscellaneous programs, with approx. amounts and duration -------- | NOTE: A baseline amount could not be estimated due to insufficient data, but it was assumed as $1M each, as a token amount for calculation purposes only): ------------ | 2018-2022 (circa) | 1,2,3 | [as below] | - |
| 8a | Misc Progr (a) | AFD Small-Grants | AFD - French Development Cooperation Program, which foresees a funding mechanism for small grants (approx. $10k) and focuses on agricultural value chains. | [as above] | 2 | 1.0 | - |
| 8b | Misc Progr (b) | NL DSS Project | Two Dutch Embassy Programs, one (10b-i) focusing on support to Netherlands-based companies that can contribute to DSS in land-use management and agriculture, with a budget of up to EUR 3M (~$3.45M), and another one (10b-ii) focusing on financing mechanisms for the sector -- both are highly relevant for the FAO GEF Project and partnerships should be sought as a priority. | [as above] | 1 | 1.0 | - |
| 8c | Misc Progr (c) | SASSCAL-CETAC Project | Operating in five SADC countries and with support from the EU and the German Federal Ministry of Education and Research, the work of a regional NGO SASSCAL (Southern African Science Service Centre for Climate Change and Adaptive Land Management) is beginning a cooperation program to be harbored by CETAC with focus on GIS and big-data analysis. Also, this program is highly relevant for the FAO GEF Project and partnerships should be sought as a priority. The list of national higher education institutions that cooperate with SASSCAL is significant. | [as above] | 1 | 1.0 | - |
| . |  |  |  |  | Baseline - TOTAL | 100.4 | 14.0 |

Notes: For rows 1, 2 and 3, refer to Table 5 for details. Amounts were converted to USD at 300 AOZ/USD and spread over the relevant and project duration.

Note on row 1: According to the PDN, an amount equivalent to $9.25M in 2019 has been planned invested in under the PND Program # 2.4.1: Climate Change. For the purposes of this project, it represents a ‘target for public investment in SLM’. In 2014/16, a similar public investment was approximately $4.8M per year, as assessed at PIF stage. Between 2016 and 2016, the PDN was formulated and the baseline from that Program estimated at $26M for the Project’s 4 years, which yields an average of $6.5M per annum for the 2019-2022 period. However, PDN investments bear uncertainties. E.g. the extent to which public investments will realize will depend on the economic scenario and its USD converted amount is subject currency variability. This may have implications for the establishment of indicator baselines for the project’s Component 3, which is proposed updated during inception. For now, a lower figure of $4.8M (2014/2016) was considered as the point of departure for the mentioned relevant indicator on public investment.

Table 4. Baseline Finance ($M), Leveraged ($M) and Total Co-financing ($): Overview per Source and Component

| # | BASELINE [B] Short Title / Acronym (refer to details in Table 3) – amounts in $ millions | Duration | Relevance for the project's Components | C1) AEZ ($M) | C2) SLM ($M) | C3) Fin ($M) | BASELINE TOTAL ($M) * | => Of which, Co-financing from baseline per source $M ¦ [B”] |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | PDN OGE MINAMB, Climate change | 2019-2022 | 1,2,3 | 8.6 | 8.6 | 8.6 | 25.9 | 8.0 |
| 2 | PDN OGE MINAGRIF, Agricultural Production | 2019-2022 | 2,3 |  | 7.4 | 7.4 | 14.8 | 3.0 |
| 3 | PDN OGE MINAGRIF (DNF),Forests | 2019-2022 | 1 | 1.6 |  |  | 1.6 | 1.5 |
| 4 | OGE CETAC under MINAMB, recurrent institutional budget | 2019-2022 | 1,2,3 | 1.3 | 0.6 | 0.6 | 2.5 | 1.5 |
| 5 | WB PDAC/CADP - Program in Angola on Agriculture | from 2017 (end date t.b.d.) | 1,2,3 | 7.0 | 7.0 | 7.0 | 21.0 | _ |
| 6 | IFAD SREP - Smallholder Resilience Enhancement Project | 2019-2025 | 1, 2, 3 | 4.0 | 4.0 | 4.0 | 12.0 | _ |
| 7 | IFAD-FAO ARP - Agricultural Recovery Project | 2018-2025 | 2, 3 |  | 3.8 | 3.8 | 7.6 | _ |
| 8 | AFDB Agric Value Chains – Support to Sust. Dev. & Growth | 2019-on (end date t.b.d.) | 1, 2, 3 | 4.0 | 4.0 | 4.0 | 12.0 | _ |
| 9a | Other Programs: AFD Small-Grants | 2019-2022 | 2 |  | 1.0 |  | 1.0 | _ |
| 9b | Other Programs: NL DSS and Rural Fin Projects | 2019-2022 | 1,3 | 0.5 |  | 0.5 | 1.0 | _ |
| 9c | Other Programs: SASSCAL-CETAC Project | 2019-2022 | 1 | 1.0 |  |  | 1.0 | _ |
|  |  | [B] TOTAL BASELINE | TOTAL | 28.0 | 36.4 | 35.9 | 100.4 | 14.0 |
|  | [B”] CO-FINANCING FROM BASELINE PER COMPONENT ($M) |  | TOTAL | 4.4 | 5.2 | 4.4 | 14.0 | * Baseline net of co-financing (100.4 – 14.0) = $86.4M |
|  | CO-FINANCING LEVERAGED [X] (i.e. would not be invested, was it not for the project) | Duration | Comp | C1) AEZ ($M) | C2) SLM ($M) | C3) Fin ($M) | PMC ($M) | TOTAL Leveraged Co-financing above the baseline $M ¦ [X] |
| 10 | CETAC availing premises to the project | 2019-2023 | 1,2,3, PMC | 0.0 | 0.0 | 0.0 | 0.5 | 0.5 |
| 13 | FAO (in-kind) | 2018-2024 | PMC | 0.0 | 0.0 | 0.0 | 0.5 | 0.5 |
|  | [X] LEVERAGED CO-FINANCING ($M) |  | TOTAL | 0.0 | 0.0 | 0.0 | 1.0 | 1.0 |
|  | TOTAL PROJECT CO-FINANCING [B”] + [X] Name of Co-financier | Note on source | Type (GEF typology, new) * | C1) AEZ ($) | C2) SLM ($) | C3) Fin ($) | PMC ($) | TOTAL ($) [B”] + [X] |
|  | MINAMB, GABAC | Baseline 1 | Public Investment | 2,400,000 | 3,200,000 | 2,400,000 | 0 | 8,000,000 |
|  | MINAMB, CETAC | Baseline 4 | In-kind | 500,000 | 500,000 | 500,000 | 0 | 1,500,000 |
|  | MINAMB, CETAC | No baseline / leverage | Public Investment | 0 | 0 | 0 | 500,000 | 500,000 |
|  | MINAGRIF | Baseline 2 and 3 | Public Investment | 1,500,000 | 1,500,000 | 1,500,000 | 0 | 4,500,000 |
|  | FAO | Contribution | In-kind | 0 | 0 | 0 | 500,000 | 500,000 |
|  | [B”] + [X] TOTAL PROJECT CO-FINANCING ($) |  | TOTAL | 4,400,000 | 5,200,000 | 4,400,000 | 1,000,000 | 15,000,000 |

* Note: The classification of co-financing herein follows the GEF’s guidelines. Co-financing from government in the case of this project will remain managed by government, as these are public investment funds assigned to specific entities, the details of which are provided in Table 3 and Table 5.

#### Contribution from the General State Budget (OGE)

Table 5. Governmental investment baseline from the National Development Plan (PDN) 2018-2022

| Objectives under the different policies and programs | Targets | Priority Actions / Note on financial baseline relevance and calculus for selected public investments * | Owner | Budget allocations for 2019 (as published) * | “Fit” with the Project’s Components * |
| --- | --- | --- | --- | --- | --- |
| XII. ENVIRONMENTAL SUSTAINABILITY POLICY Program # 2.4.1: Climate Change |  |  |  |  |  |
| 3: Reinforce the fight against drought and desertification, in particular by establishing institutional mechanisms for coordination, participation and action between different sectors | Target 3.4: Mapping of Zones with Land Degradation in all provinces by 2022 | - Establish a land-use mapping mechanism to allow monitoring of land-use including, for environmental management purposes, identification of land degradation and desertification zones. This mechanism will make it possible to identify measures to address land degradation factors, including measurable, verifiable and time-bound targets, based on the UNCCD and SDG indicators related to Target 15.3. This exercise will be triggered, phased, nationally in provincial increments; - Map areas of land degradation; - Formulate and implement strategies for control of desertification at the local level and guidelines for designing and reviewing policies and measures to support the sustainable development of areas susceptible or affected by drought or desertification; - Implementing long-term integrated measures and strategies in the affected areas, based on increased land productivity, rehabilitation, conservation and sustainable management of land resources, including the establishment of tree nurseries (fodder and fruit trees) for land rehabilitation purposes. 100% of this program is considered a relevant financial baseline for the project. The USD amount was extrapolated for the project’s duration (2019-2022), with future investments discounted, resulting in appox. $25.9M for the project duration. Of these, $8M is slated to contribute as co-financing from MINAMB on account of Program # 2.4.1. | MINAMB (DNB and INBAC) | 2,775 Million Kwanzas in 2019 equiv. to approx. $9.25M | C1 / C2 / C3 |
| XI: PROMOTION OF PRODUCTION, IMPORT SUBSTITUTION AND EXPORT DIVERSIFICATION Program # 2.3.2: Promoting Agricultural Production |  |  |  |  |  |
| 1: To promote agricultural activity with a view to increasing the production of basic food products for consumption, both on family farms and on farms 2: Increase production of industrial crops and yield 3: Support agricultural production of family farmers by increasing the availability and improved access to inputs and increasing the capacity of rural extension and development services | Targets 1.1 to 2.4: Substantial increases in agricultural production Target 3.5: By 2022, the number of Farmer Field Schools (ECA's [FFS]) increased 61% over 2017 Target 3.6: By 2022, the number of Demonstration Fields increases 35% compared to 2017 Target 3.7: By 2022, the number of Agrarian Development Stations (EDAs) increases 100% over 2017; | - Promoting agronomic research; - Provide technical support to farmers through ’DA's and ’CA's (the latter do not necessarily require the construction of root infrastructures) so as to enable them to properly integrate the use of inputs, increase productivity and, consequently, the income of the households; - Correct soils with dolomitic limestone to reduce soil acidity and prepare soil for increasing areas; - Support the structuring, expansion and operation of the rural commercial network; - Promoting access to credit and insurance for agricultural and livestock activities with credit institutions and insurers under more attractive conditions; and - Mapping and registering family and business farms and creating a bank of arable land available for investment, creating conditions for the improvement of land management. 5% of this program is considered a relevant financial baseline for the project. The USD amount was extrapolated for the project’s duration (2019-2022), with future investments discounted, resulting in appox. $14.8M for the project duration. Of these, $3M is slated to contribute as co-financing from MINAGRIF on account of Program # 2.3.2. | MINAGRIF | 31,620 Million Kwanzas in 2019 equiv. to approx. $105.4M | C2 / C2 / C3 |
| XI: PROMOTION OF PRODUCTION, IMPORT SUBSTITUTION AND EXPORT DIVERSIFICATION Program # 2.3.4: Promoting the Sustainable Use and Management of Forest Resources |  |  |  |  |  |
| 1: Promotion of the use and management of forest resources, in particular of timber resources and of forest vegetation | Target 1.5: At 2022, the planted area increases by 1054% over 2017 | - Complete the National Forest Inventory; - Establish forest plantations and polygons; - Introduce the Forest Certification Process; - Concession of available areas to stakeholders for forest settlement and restocking; - Conduct studies on the phenomena of desertification and reforestation. 30% of this program is considered a relevant financial baseline for the project. The USD amount was extrapolated for the project’s duration (2019-2022), with future investments discounted, resulting in appox. $1.6M for the project duration. Of these, $1.5M is slated to contribute as co-financing from MINAGRIF on account of Program # 2.3.4. | MINAGRIF (DNF) | 572 Million Kwanzas in 2019 equiv. to approx. $1.9M | C2 / C3 |

* Note: Refer to Table 6 for the full explanations behind the extrapolations, and for the estimated break-downs per year and per component which applied to this project baseline.

Table 6. Projected Public Investments from the PDN: OGE Baseline summary per Component and Project Year (PY)

|  | OGE baseline amounts (current, extrapolated and estimated): Planned PDN public investments supporting the project for its duration) | MINAMB (DNB e INBAC) / PDN Program # 2.4.1: Climate Change | MINAGRIF / PDN Program # 2.3.2: Promoting Agric Production | MINAGRIF (DNF) / PDN Program # 2.3.4: Promoting the Sustainable Use and Mgt of Forest Resources | TOTAL PDN OGE |
| --- | --- | --- | --- | --- | --- |
| a | OGE allocations for 2019 in Million Kwanzas – i.e. 1 year only, basis for extrapolations | 2,775 Million Kwanzas | 31,620 Million Kwanzas | 572 Million Kwanzas | 34,967 Million Kwanzas |
| b | Above amounts for 2019 converted to USD (in $M) (converted at 300 AOZ/USD, using late 2018 exchange rates) | $9.25 M | $105.4 M | $1.9 M | $116.6 M |
| c | Relevance for the project (notional, and as endorsed by the GoA based on priority actions listed in Table 5) | 100% | 5% | 30% | 36% |
| b*c * 70% | Extrapolated total amounts from OGE that contribute to the project’s baseline, rounded-off and discounted for the period 2019-2022 (in $M) * | $25.9 M | $14.8 M | $1.6 M | $42.3 M |
|  | OGE BASELINE AMOUNTS: approximate spread for the relevant public investments for the expected duration of the project (ref. to Table 4 rows, in $M) | [1] PDN OGE MINAMB, Climate change | [2] PDN OGE MINAGRIF, Agricultural Production | [3] PDN OGE MINAGRIF (DNF), Forests | Sub-totals estimated and rounded-off ($M) |
|  | PY1 (2018) [pre-PDN year] | 0.0 | 0.0 | 0.0 | 0.0 |
|  | PY1 (2019) [expected project start] | 9.3 | 5.3 | 0.6 | 15.1 |
|  | PY2 (2020) | 8.3 | 4.7 | 0.5 | 13.6 |
|  | PY3 (2021) | 5.6 | 3.2 | 0.3 | 9.1 |
|  | PY3 (2022) | 2.8 | 1.6 | 0.2 | 4.5 |
|  | PY3 (2023) [year beyond PND, yet to be allocated] | - | - | - | - |
| Approx. | TOTAL OGE BASELINE AMOUNTS break-down per component (in $M) | 25.9 | 14.8 | 1.6 | 42.3 |
|  | Component 1 | 8.6 |  | 1.6 | 10.2 |
|  | Component 2 | 8.6 | 7.4 |  | 16.0 |
|  | Component 3 | 8.6 | 7.4 |  | 16.0 |

* Note on the baseline extrapolation calculus and the ‘discount coefficient’ that applied to it: 2019 was assumed as the ‘base year’ for estimating the amounts of public investments allocated through OGE to the three relevant programs and had served as the project’s baseline (row a). Amounts were converted from kwanzas (AOZ) at a 300 AOZ/USD rate (row b). The currency conversion was based on the end 2018 approximate exchange rate. Because the AOZ currency is volatile vis-à-vis the USD, and because medium-term public investments are generally subject to risks of non-realization, a future discount rate of 70% was applied when estimating the total baseline over the PDN’s 4-year duration (2019-2022) (refer to the green row in the first part of the table). The relative relevance of each program’s baseline also applied when estimating the total baseline (row c). Different programs were considered to have different degrees of relevant to the project. For the total OGE contribution the relevance ratio is 36%. Totals per Program were spread over the project’s duration according to notional criteria (light yellow rows in the second part of the table), and per Component according to relevance vis-à-vis the focus of these programs, described in Table 5 (blue rows in the last part of the table).

Figure 14. Evolution of State Budget for agriculture (in US$ at market rates)

Box 4. Baseline of Finances and Co-finance for SLM

Focus on OGE

The State budget has shrunken since 2014 as a result of the global drop in oil prices. This problem was compounded by the devaluation of the national currency and by the fact that the amounts actually disbursed are often considerably below the budgeted value. Agriculture, that has consistently received a modest part of the state budget, was particularly affected. Never having received much attention by the public policy agenda, funding for SLM was surely affected by this trend. Figure 14 illustrates the evolution referred to above. At the same time, international sources of funding for agriculture and natural resources management have supported important projects that benefited Huambo province and parts of Benguela. The World Bank, the French Development Agency, the European Union and the African Development Bank provided credits and donations for a set of projects that included components of SLM. Most of these projects need information to support decision making (climate, soils and other contextual conditions. They are potential “clients” of an AEZ system and the related environment monitoring services. Regarding the Baseline for Component 3: The Ministry of Environment created an Environment Fund which, however, is not being used to support SLM initiatives. For that purpose, this fund would need considerable changes such as creating a specific focal area for SLM and developing a governance structure involving different stakeholders. Some rural development and agriculture projects promoted community rotating funds with diverse levels of success. These rotating funds, that are also being promoted by SADPC (MOSAP II), are a way of allowing local associations to have the capacity to provide loans to their associates. In an environment of almost no credit services or other financial services, these local funds offer an opportunity for future financial services focused on SLM. There is practically no private sector investment in SLM. Some private companies operating in various sectors — such as commercial agriculture, forest plantations, seedling nurseries, beekeeping, quarries, construction, charcoal production, the harvest and commercialization of wild fruit, fish arming and tourism — are currently managed unsustainably but would have the potential to contribute to LDN if they were to incorporate SLM principles. An ongoing pilot initiative to promote agritourism through birdwatching is likely to well adaptable for specific emphasis on the promotion of SLM, and a few agribusiness projects have expressed interest in improving their environmental sustainability.

[*] This operation is working in the processing of other species as well.

### 1.2.3 Remaining Barriers to be addresses

The Current ‘Baseline Scenario’ points out to a strong commitment from the government and partners towards supporting SLM actions in different ways, both directly and indirectly. However, there are visible gaps in the status quo. In the baseline scenario, land degradation will continue to be a visible and serious problem in Angola, but it will remain poorly quantified and assessed. Capacity for SLM on the ground will remain limited and the central region of Angola will face increasing threats to ecosystem services linked to biodiversity, soil, water and carbon. Land will continue to be managed largely in an unsustainable way, even though short-term increases in productivity are possible with certain techniques that may not be fully adequate from an agroecological point of view. Furthermore, the economics of land degradation in Angola will not be specifically assessed, missing out on opportunities to leverage funding for addressing the tall challenges of land restoration and rehabilitation. These represent major gaps that are linked to the project’s baseline. The GEF intervention is needed to consistently address these gaps, discussed herein.

Three barriers stand in the way of realizing the long-term goals outlined in government policies that relate to SLM and which could potentially general both national and global environmental benefits for land-based ecosystem services.

#### Barrier #1

In Angola, the systemic, institutional and individual capacity for complex and geo-based data handling is limited.

As a concept, SLM is still relatively new to Angola. Notably, the country reported for the first time to the UNCCD in 2013 through the PANCOD. At the same time, the GoA took this as an opportunity to officially endorse the PANCOD as a strategy and action program through a Presidential Decree. The PANCOD points out to major deficiencies in the knowledge base for SLM. Most vegetation and soil maps dated back to the 1970’s. No new comprehensive exercise along those lines had been carried out since.

Notwithstanding, there have been a few isolated initiatives for mapping land use and agroecological data, with some of these related to the preparation of Municipal Master Plans (PDMs). As of 2013, at least 53 PDMs had been prepared or were under preparation throughout the country. While this is a commendable progress for a country that had only a few years earlier achieved lasting peace, there are challenges.

More specifically, national efforts towards developing an initial framework for spatial planning in Angola gave top priority to urban areas and regarded rural areas as secondary. This has meant that PDMs have generally only included detailed planning for the urban areas of municipalities. This would not have been problematic if the PDM had been complemented by Environmental Spatial Plans (POAs) and Rural Land-Use Plans (PORs) as foreseen in the country’s spatial planning framework, However, the two latter types of plans (POAs and PORs) have not been produced in Angola in any systematic form. In addition, the few initiatives that have taken place in this context, such as the “Biophysical Characterization of the Municipality of Londuimbali”, have not built on one another and have not been integrated in a common database system.

More importantly, efforts relevant to AEZ have not been translated in products adapted to the needs of decision-making and thus have failed to provide a systematic support to decision-making related to land-use allocation and management. In addition, there is abundant GIS data from global sources relevant to AEZ but which have never been integrated and translated into scale-specific products that are adapted to the needs of Angolan land-use management. The LDN-TSP is being implemented by the Angolan government but has been primarily reliant on default data that is still too broadly scaled for an accurate assessment of land degradation and appropriate responses through SLM (see subsection Supportive Approaches and Tools, item d, under Section 1.3.1 for a description of the LDN-TSP). In the context of the on-going LDN-TSP, voluntary specific LDN targets and strategies were presented by the GoA and validated by stakeholders in November 2018, but the GoA will still require support to effectively implement and monitor LDN technical measures and targets, thereby implementing the overall strategy adopted at national level for LDN.

The main problem is thus twofold: 1. there are important gaps in baseline AEZ-related data; 2. Geo-based data that does exist has not been integrated in a centralized database and zoning system accessible to decision makers and other stakeholders and has not translated to adapted products to support decision-making for land-use management. The two aspects can be boiled down to a problem of technical capacity to collect, produce and use the data for an AEZ analysis and its products in the context of land-use management. The piecemeal initiatives in mapping agroecological data that have taken place have usually been carried out by consulting firms hired for the purpose of producing such products, but without incorporating strategies for building national/local knowledge and technical capacity in the subject matter. This pattern is analogous to the situation of spatial plans produced so far as described under Barrier # 2.

Exacerbated by the context of a country overcoming a long-lasting armed conflict, national capacity in general is departing from a low baseline of available education opportunities at all levels—primary, secondary and tertiary—and for the latter, encompassing various subject matters that would be useful in realizing SLM solutions.

Clearly, building national capacity for managing and fully exploiting big-data applications cannot be acquired from one day to another. At the same time, within the mining and oil industry, the techniques, applications and geo-based datasets are state-of-the-art. However, because holding this data and running these applications may constitute a business advantage for oil and mining companies, they tend not to share, not even piecemeal. Although some of the data could, in theory, be of use to the agricultural or environment sector (e.g. soils, contour, vegetation cover), there have been no initiatives towards sharing them for the public good. Finding common ground in defining the scope of a truly national agroecological zoning system, its ramifications and subsidiary applications, requires careful but close negotiation and collaboration with MINAGRIF, as well as other sectors – and last but not least also the mining and oil sectors.

This crucial barrier is not sufficiently addressed by current baseline initiatives. In fact, it represents a fundamental limitation not only to the success of the current and planned projects, but also to the core governmental agenda for the sustainable development of the market-oriented agricultural sector. Theoretically, practically any initiative or project related to agriculture and the management of land use could benefit substantially from an adequate strategy to address this barrier.

#### Barrier #2

At the local level, capacity for land-use allocation/management and the application on the ground of tools and concepts relating to AEZ, SLM and LDN has significant gaps.

Historically, land-use allocation for agriculture in Angola has followed the path of least resistance until land started to become scarce, inaccessible or degraded. Planning its allocation did not seem necessary during the early days of colonization. Rather, land users occupied productive landscapes with the impression that land and associated resources were almost “endless”. Once a large exporter of coffee, cotton, sisal, sugar cane, bananas and tobacco, Angola’s agricultural sector suffered widespread destruction during the conflict and has not fully recovered since. Before the war, the country was self-sufficient in all food crops except wheat. The exodus of Portuguese settlers after independence and the ensuing civil war that ravaged the country meant the loss of technical capacity and infrastructure destruction, cutting production areas from markets. This is being gradually addressed through recent infrastructural investments. An added challenge has been the large-scale population displacement in rural areas and the legacy of land mines and unexploded devices (as many as 10 million) – a matter that is a limiting factor for a sustainable development within the agricultural sector, but which is being dealt with through various demining and social inclusion interventions.

In today’s Angola, managing and allocating land is much more complex than it has been historically. It means not only re-learning agricultural techniques once mastered, as well as new ones, but in particular it means allocating land in a rational, participatory and equitable manner. The legal frameworks for managing land and associated resources is being developed, but there is still limited practical experience in applying it.

In this context an important centerpiece is the 2004 Spatial Planning Law (LOTU). The LOTU legal package can be a powerful vehicle for promoting SLM on the ground, but for which the GoA currently lacks support in implementing and enforcing it in rural areas. The LOTU framework foresees national, provincial and municipal plans. Municipal plans should include, besides the municipal master plan (PDM), an Environmental Spatial Plan and a Rural Land-Use Plans (see section 1.1.1 for more details).

Huambo does have a provincial plan for the environment, and as in the case of the Benguela province, most of its municipalities are now equipped with PDMs. SLM planning for practical purposes should occur at the local level, being the municipal level the best entry point for SLM planning in Angola. Not having the necessary scale and precision for land-use management, national and provincial land-use planning is mostly of strategic nature and therefore SLM planning needs to be incorporated at municipal level. Finalized PDM’s in Angola, however, have not been complemented by Environmental and Rural Land-Use Plans, and have focused mostly on the urban centers and respective connectivity. For the above-mentioned reasons, the implementation of the LOTU has yet to systematically address the preparation of Rural Land-Use Plans.

Another important reason of this has been the complex dimensions of land tenure in Angola which is now in the process of being improved by other initiatives. Yet another reason is the lack of functional capacity by Angola administrations to conduct the necessary preparation processes. This capacity gap pertains not only to the use agroecological and GIS data, as in barrier # 1, but it also pertains to the core subject matter of land-use plans. More specifically, the capacities needed should focus on: (i) helping groups of stakeholders at various levels make informed decisions on the optimal land use across landscapes of varied scale – and in the case of this project, land uses that pursue SLM as a goal – and (ii) taking into account the complexities of involving all relevant stakeholder in negotiation processes.

In the case of the plans produced so far, this barrier has led to the systematic hiring of consulting firms to produce such plans, which leads to a proliferation of unintegrated piecemeal products, which were prepared with a rather low level of involvement of local actors in their preparation. This approach does not necessarily improve national capacity for spatial planning or implementation of SLM at the level of landscapes, with particular reference to the capacity of Angolan administrations to use spatial planning products in their tasks linked to environmental governance. In addition, there are no formal mechanisms in place for building this capacity.

This creates an unfortunate situation where the different initiatives leave behind products that are not only poorly (if at all) integrated with each other, but which fail to deliver practical contributions to how land use is actually managed at the different administrative tiers, thus heavily limiting the development gains of not only those initiatives directly related to rural land-use planning and management, but also of those related to agriculture in general. This indicates a clear need for planning processes that build capacity by involving local stakeholders and which are based on negotiated local agreements that are able to provide some assurance of ownership by those that are most directly involved (and affected) during the actual implementation of such plans.

This last point leads to another important gap. In addition to the dimension of planning, the lack of capacity for SLM relates also to the actual and practical uptake of SLM principles and measures on the ground. Land managers and land users face many challenges linked to productivity and the dynamics of land allocation at the local level, and local governments are ill-equipped to provide adequate extension services. At the same time, the few existing extension services that specifically focus on SLM practices are not yet anywhere near sufficient to deliver the scale of dissemination that is pressingly needed in Angola.

AP/FFSs in Angola have proved to be a promising extension strategy in various projects (piloted mostly by FAO), and the approach is increasingly accepted and embraced by donors, NGOs and the government. Their current geographical coverage is still limited, but it is currently slated to be expanded through the work of various projects. Some are being implemented or planned for the near future. The AP/FFS approach seems, at this point, to be the most appropriate and promising vehicle for disseminating SLM in Angola.

However, before a massive scale-up of FFS/APFSs for SLM can take place, effective mechanisms for adapting the approach to the promotion of SLM based on agroecological zoning need to be devised and tested – an aspect that is currently missing from baseline initiatives. More specifically, the AP/FFS approach needs to be adapted so as to effectively integrate SLM with accurate agroecological data in the form of concrete socially accepted practices at the local level. Local approaches to building the capacity of local farmers and agro-pastoralists lack both adaptability and some form of standardization that needs to be tailored to local agroecological conditions and socioeconomic specificities. For this to occur, the AP/FFS approach lacks useful agroecological data and also zoning, preferably within the framework of land-use plans that result from, and are based on, collectively negotiated and agreed land-use arrangements. The participatory aspect of such agreements is essential to provide reasonable assurance of the feasibility and ownership of realistic land-use options adapted to the culture and needs of specific communities.

#### Barrier #3

Institutional capacity, stakeholder roles and, financial leverage impede the scaling up of SLM approaches.

Well preserved ecosystems (and respective services) hold value for conservation and other purposes without the need for deriving economic gains from it. Nonetheless, there is an objective need for economic and financial analyses for underpinning decision-making in land-use allocation. Currently, such assessments have not been carried out at scale in Angola, missing out major opportunities of investment in SLM. Under the auspices of the UNCCD, a number of countries are realizing the potential leverage of impact investment geared towards SLM under the LDN initiative. Angola is yet to reform its financial sector to more fully participate in those and other initiatives that can potentially bring home the much-needed finance to restore and rehabilitate landscapes.

Access to finance is a serious hindrance to commercial agricultural development. Notwithstanding the high credit growth from 2004 to 2014 (going from 5 % to 22 % of GDP), the share of credit going to agriculture has remained very low at less than 5 % of overall credit provided. Additionally, despite the general increase in access to finance over the five years between 2010 and 2014, there has been a clear urban/rural divide in access, with Luanda accounting for the bulk of financial sector outreach. Despite the existence of some lines of credit for agriculture, credit options in the sector are very limited. A few attempts to introduce public credits for small farmers have generally proved unsuccessful. The enabling environment for promoting SLM finance tailored for smallholders (including agriculture insurance, warehouse receipts, equipment leasing, moveable collateral registry) is yet to be developed.

The situation of specific SLM financing mechanisms has even wider gaps. There is a very limited pool or resources immediately available for SLM and there are no stable and reliable mechanisms to fund SLM. This can be attributed to three separate problems:

(i) The state budget is allocating insufficient resources to SLM

The 2014/15 General State Budget (OGE) earmarked a mere $6 M in 2016 for SLM-related initiatives – and 2016 was a peak year in terms of government revenue mobilization and expenditure. This situation is only now beginning to improve (with reference to Table 5). Yet, the inadequate response from the state budget to land degradation results from the fact that SLM is not seen as an important priority when compared to other pressing problems such as rural poverty and lack of basic services in a governance culture where short-term solutions are systematically preferred over longer-term strategies. This aspect is compounded by a general lack of consistent advocacy for natural resource management and environmental sustainability. In Angola, even among development activists, environmental protection is often perceived as secondary to the resolution of the most severe social problems. This discourse fails to recognize that any sustainable strategy to curb poverty has to involve a dimension of SLM. Furthermore, the Angolan economy is under crisis, burdening the state budget with multiple sectoral pressures which, in combination with the above, does not favor the argument for more generous budget allocations for SLM.

(ii) There is limited use of existing international sources of funding for SLM

The limited use of existing international sources for SLM funding results from three problems: (i) no one is adequately monitoring and engaging those sources, (ii) there is limited capacity to design high quality project proposals to tap into those resources and (iii) there is a trust deficit in the capacity to properly manage funds.

(iii) Insufficient private initiatives in SLM and natural resource management

There are practically no private sector initiatives investing in SLM- or NRM-related businesses that could sustainably mobilize and generate resources for SLM. This can be attributed to a lack of financial mechanisms to support this type of businesses and to limited technical and managerial capacity among entrepreneurs, government administrations and other stakeholders to actively engage in these investment opportunities.

## 1.3) THE GEF ALTERNATIVE

### 1.3.1 Project Strategy

Illustrated by Figure 15 below, the project strategy rests on three pillars of intervention that are interconnected in a logical structure.

In its approach to the uptake and dissemination of AEZ-based SLM, this project embodies the principle of learning by doing. It “does” and part of that “doing” involves people that thereby learn and are capacitated through their involvement. This dimension of capacitation is present in all three components and in most of the project’s “outputs”.

Figure 15. Logical Structure of the General Project Design

Component 1 will deal with the production of a centralized national AEZ-based decision support. This involves compiling and integrating already existing agroecological and land-use data. Several past initiatives and projects in this domain have produced a substantial volume of studies, plans, maps and agroecological data. However, these have rarely been integrated with one another and hardly played a systematic role in informing decision-making. It will also involve identifying missing data gaps and filling such gaps with complementary GIS global sources and strategic data collection. The resulting layers of these sources are to be integrated into a single national system, which will be multi-scale and nested in its conception, and therefore also ‘multiple-use’. The respective databases and AEZ products will be made available for professionals involved or interested in AEZ in Angola and other relevant stakeholders, thus establishing the AEZ unit at CETAC as a national hub for AEZ in Angola. The component also foresees that comprehensive analysis and maps are developed for the Provinces of Huambo and Benguela as priority AEZ exercise, in view of the interventions under component 2. Component outputs are structured so as to integrate a dimension of capacity-building in the respective activities.

Component 2 relates to the application of the data produced and/or made accessible by Component 1 in the targeted areas. The term “application” herein implies its incorporation into the existing decision-making structures so as to produce social agreements and participatory sustainable land management (SLM) plans that are informed by AEZ. Based on these SLM plans, willing local beneficiaries who are members of AP/FFSs within demonstration landscapes, of whom at least 40% will be women, will be assisted by the project towards the adoption and integration of SLM practices at the micro-landscape level in local land-use management. Linked to this process of preparation and implementation of local SLM plans, the professionals involved in extension services, local /municipal land-use management and the AP/FFS approach in targeted areas will be progressively capacitated by a training program focused on SLM.

Component 3 will focus on identifying and developing suitable options for financing SLM initiatives and on improving national capacity for leveraging resources from multiple sources to be invested in SLM. Along with an economic assessment of the cost of land degradation in the Provinces of Huambo and Benguela, identified finance options will include financial mechanisms for local initiatives related to SLM, targeting first and foremost local beneficiaries in demonstration landscapes.

The implementation of the project takes a three-tiered approach in terms of geographical scale and entry points for spatial planning and land-use management for SLM. These are: the wider landscape, macro-landscapes and, within these, a collection of micro-landscapes. These three tiers correspond roughly to the administrative levels of (i) province, (ii) municipality / commune and (iii) village/community. Across all of these scales, landscapes can be drawn and SLM challenges addressed with the help of decision-support tools and products that are level-appropriate. The AEZ system will be sufficiently robust to supply all of these tiers with information, data and advice that are both level-appropriate and audience-appropriate. Whether and how AEZ applications will be developed for different levels will depend, by and large, on the demand for services.

Through these different geo-spatial scales, between administrative jurisdictions, relevant biophysical features and also across different economic sub-sectors, the project’s strategy (and success) is based on inter-institutional collaboration. It therefore lays much emphasis on the importance of processes and integration. In this light, the project has been designed to sustain a feasible approach that facilitates the cooperation between entities, which should later result in sustainable land-use governance.

#### Supportive approaches and tools

The project’s implementation strategy is based on the application of multiple technical and methodological frameworks (AEZ, AP/FFSs GreeNTD and LDN), and for which FAO’s technical assistance plays a pivotal role. These frameworks have their own methodological approaches which will be carefully adapted to the situation ground and integrated to the proposed strategy in a coherent way, allowing them to reinforce the pursuit of SLM goals by maximizing the impact of technical assistance in tandem with investment concurrent investments on the ground. These investments have been duly identified, described and their impact assessed in section 1.2.2 further up (Baseline Initiatives) and in section ‘Technical Integration with relevant projects’ further down. Here is a brief overview of the supportive approaches and tools.

##### a) FAO’s Agroecological Zoning: FAO AEZ

The purpose of zoning, as carried out for rural land-use planning, is to separate areas with similar sets of potentials and constraints for development. Specific programs can then be formulated to provide the most effective support to each zone. Agroecological zoning (AEZ), as applied in FAO studies, defines zones on the basis of combinations of soil, landform and climatic characteristics. The particular parameters used in the definition focus attention on the climatic and edaphic requirements of crops and on the management systems under which the crops are grown. Each zone has a similar combination of constraints and potentials for land use and serves as a focus for the targeting of recommendations designed to improve the existing land-use situation, either through increasing production or by limiting land degradation. When combined with an inventory of land use, expressed as land utilization types and their specific ecological requirements, zoning can then be used as the basis of a methodology for land resource appraisal. The addition of further layers of information, on such factors as land tenure, land availability, nutritional requirements of human and livestock populations, infrastructure and costs and prices, has enabled the development of more advanced applications in natural resource analysis and land-use planning.

AEZ can be regarded as a set of core applications, leading to an assessment of land suitability and potential productivity, and a further set of advanced or peripheral applications, which can be built on the inventories and results of the core AEZ studies. Outputs of core applications include maps showing agroecological zones and land suitability, and quantitative estimates on potential crop areas, yields and production. Such information provides the basis for advanced applications such as land degradation assessment, livestock productivity modelling, population support capacity assessment and land-use optimization modelling. Before applying the procedures of AEZ, the potential user should have a good appreciation of the underlying concepts, so that the potential uses and limitations of the methodology are understood. The essential elements of the core applications of AEZ comprise: land resource inventor; inventory of land utilization types and crop requirements; land suitability evaluation, including: potential maximum yield calculation, matching of constraints and requirements. The methodology and the input variables of AEZ are scale-independent. However, the level of detail to which such factors as soils, climate and land utilization types are defined may vary according to the map scale and the objectives of the study.

##### b) Agro-Pastoral Field Schools and Farmer Field Schools: AP/FFS

The AP/FFS approach is particularly valuable for integrating knowledge in a local agro-ecosystem specific context, and for mobilizing farmers and pastoralists in the dissemination of new technologies and practices across the AP/FFS groups and networks. AP/FFS are flexible since they directly respond to local demands or issues. They are based on an “experiential learning cycle” (with a minimum duration of one and half-year, during which farmers’ groups are followed and supported on a weekly basis), where farmer groups are gathered at regular intervals to go through a pre-determined number of AP/FFS sessions in the fields /grazing lands to identify a problem, consider different options for problem solving and implement the best option. The method of interaction is informal and based on field observations and group discussions, as well as simple experiments, drawings, models, fables and other tools. The experimental, learning-by-doing approach facilitates the adaptation of the promoted technologies to local agroecological contexts. Farmers participating in AP/FFS gain organizational skills, knowledge and practical skills that carry over beyond the end of the project. Moreover, due to the comprehensive planning processes, they can define the critical broader challenges faced in their livelihoods, as well as strategies to mitigate them. The AP/FFS process is guided by a dual systematic problem-solution identification process that guides consequent actions, thus setting a solid base for sustainability. The AP/FFS approach is therefore considered vital entry point for upscaling specific practices like sustainable land management or climate smart agriculture throughout targeted intervention areas.

##### c) Green Negotiated Territorial Development: GreeNTD

The GreeNTD is a people centered, process-oriented socioecological approach to territorial development. It is based on the active engagement of multiple stakeholders with the purpose of fostering a progressive consensus (Socio-Ecological Territorial Agreement - SETA) leading towards a holistic, multiscale and negotiated vision. The active inclusion of all actors in territorial development interventions is crucial for sustainable development, because it allows recognizing the key role that each of the stakeholders plays, existing power asymmetries within communities, households and institutions, and how they influence people’s capacity to play an active role in development and be assured that they are heard.

In this sense, GreeNTD aims to explore: i) how men and women, ethnic minorities or marginalized people are differentially engaged as socio-economic agents; ii) which are the institutions promoted by such coalitions; iii) how those institutions (including historically constructed informal rules and social norms) differentially affect men and women and minorities in the access and use of assets; iv) which are the differential development outcomes between various groups of stakeholders, (e.g. gender, ethnicity, age, socio-economic class, caste), and how they are influenced by spiritual-cultural perceptions of their roles within their territories. Focusing on understanding the differentiated roles, responsibilities and relations, and how these are managed, the GreeNTD assists development actors to promote gender equality in access and management of land and other natural resources. A negotiated, rights-based and gender sensitive approach characterizes the GreeNTD, making it more comprehensive and adapted to a rapidly changing international context; its proper use fosters the resilience of the local communities and their sustainable development.

##### d) Land Degradation Neutrality: LDN (and LDN Target Setting Program: LDN TSP)

The concept of land degradation neutrality (LDN) emerged from the UN Conference on Sustainable Development (Rio+20) in 2012 to respond to an immediate challenge: intensifying the production of food, fuel and fiber to meet future demand without further degrading finite land resources. In other words, LDN envisions a world where human activity has a neutral, or even positive, impact on the land. LDN has since been embedded in the broader framework of the Sustainable Development Goals (SDGs) and as a follow-up, the UNCCD Secretariat launched the Land Degradation Neutrality project in 2015 as part of the broader 2030 Agenda for Sustainable Development:

- Establishing a structured dialogue between government, science, business and civil society communities on land degradation challenges, priorities and opportunities for immediate action;

- Identifying the gaps and synergies within the National Action Programs, while considering LDN as a key strategic goal;

- Formulating the appropriate spatial scales and set of indicators that reflect the circumstances and capacity of individual countries, and setting voluntary targets to achieve LDN; and

- Implementing strategies at the community/landscape levels on a pilot basis to evaluate policies and practices that aim to achieve LDN by 2030.

In 2014/15, 14 countries supported by the UNCCD embarked in the LDN pilot project to implement the LDN target setting approach. The lessons from the pilot project are now being used to guide and offer practical solutions for decision makers, country stakeholders and development partners engaging in the LDN target setting program (LDN TSP). The LDN TSP is assisting countries in making the LDN concept a reality by 2030, by providing practical tools and guidance for the establishment of voluntary LDN targets, accelerating the implementation of transformative programs and projects, with positive changes. Currently, more than 100 countries are participating in the LDN TSP, Angola among them. In 2016, the LDN Fund was launched as an impact investment fund blending resources from the public, private and philanthropic sectors in support of achieving LDN through sustainable land management and land restoration projects undertaken by the private sector worldwide. The LDN TSP is defined as having four building blocks: 1. Leveraging LDN, 2. Assessing LDN, 3. Setting LDN targets and associated measures and 4. Achieving LDN.

For this process, the aspect of land degradation indicators is essential. An assessment of the current status, trends and drivers of land degradation is needed to set sound LDN targets, make decisions on potential interventions, forecast changes in land-based natural capital and track progress. Along an examination of the local context and the direct and indirect drivers of land degradation in particular, the assessment uses a set of three indicators that reflect land-based natural capital and its associated ecosystem services:

- land cover

- land productivity (metric: net primary productivity)

- carbon stocks above and below ground (metric: soil organic carbon)

These indicators are part of a set of six progress indicators used by the UNCCD to track progress in the implementation of the Convention through national reporting. They have also been recommended as sub-indicators for the global UNCCD indicator 15.3.1, “Proportion of land that is degraded over total land area”, adopted to measure progress toward the SDG target 15.3 and are intended to reduce the reporting burden on country Parties. The indicators monitor changes in different yet highly relevant ways. Land cover provides a first indication of a reduction or increase in vegetation, habitat fragmentation and land conversion. Land productivity offers an indication of ecosystem health and sharpens the focus on ecosystem services. Soil organic carbon denotes overall soil quality. These indicators may be enhanced and complemented by other relevant national (or sub-national) indicators, in order to obtain an even more accurate picture of the current status and progress made.

In the context of the on-going LDN-TSP, and with the general LDN goal of “achieving neutral land degradation by 2030 compared to degradation levels for 2015”, the GoA adopted in November 2018 the following specific LDN targets for avoiding, minimizing and reversing soil degradation:

- Reduction of marked land degradation by around 50% compared to the reference year (2015) for land where agriculture is currently practiced;

- Restoration of 50% of ecosystems currently degraded by unsustainable land use practices;

- 30% increase of soil organic carbon content (SOC) in all land classes and halving (0.4%) the current rate of deforestation throughout the country;

- Reinforcing information, education and awareness-raising on good land-use practices including those linked to sustainable agriculture-conservation for 80% of rural households;

- 30% increase in water availability in deprived areas of the transhumance triangle (Cunene, Huíla and Namibe);

- Reduction of 25% of livestock in areas with a strong tradition of livestock production;

- 18% increase of the total area of conservation areas, covering the country’s different ecoregions / biomes;

- Reduction of greenhouse gas emissions by 50%.

In light of the specific strategies for achieving these targets, which have been formally adopted by the GoA, the baseline analysis has identified that support for effectively implementing and monitoring LDN technical measures and targets is needed. This will be addressed by the project under its Component 1 and as described further down.

The way these frameworks interact can be thus summarized: Products of AEZ and other related spatial analysis, as well as raw data organized in catalogues are compiled to facilitate and promote SLM. Clear agroecological zones will be integrated in decision-support tools to guide the participatory negotiation of social agreements at various governance tiers through the GreeNTD approach and formalized as SLM plans. The implementation of these plans and associated practices will be supported and disseminated through the extensionist approach of AP/FFSs. The AEZ products will also be tailored to data needs of the assessments of the LDN TSP, thus giving special emphasis to the adequate development of the LDN indicators and going beyond their basic requirements whenever possible. The local SLM plans will also guide application of the funding mechanisms for SLM-related investments contemplated by the project’s third component.

#### The Project’s Theory of Change (TOC)

The project’s ToC is summarized in Figure 16.

Figure 16. A Summary of the Project’s Theory of Change

The project’s three technical outcomes (#1, 2 and 3) encompass a strategic combination of feasible solutions that have been respectively identified under barriers analysis (section 1.2.3), whose themes relate respectively to: (1) Governance; (2) Capacity; and (3) Finance.

Under these, the project’s outputs contribute to the combined operationalization of the conceptual and methodological frameworks slated to achieve the mentioned outcomes, which had been described in section 1.3.2 further down. Outputs constitute hence a series piecemeal solution, strategically designed to maximize the project’s cost effectiveness.

Together, these piecemeal solutions point out to a broader long-term solution, relating the problem of tackling land degradation in Angola. Under ideal conditions, implementing the project’s outputs and realizing the project’s expected outcomes equates to achieving its objective – and contributing thereby to realizing the proposed long-term solution, which is formulated as an aspirational goal and relates closely to the project objective, but with a higher ambition level, as follows:

The Project’s Long-Term Solution: Pressures on natural resources from competing land uses are addressed, both across the wider landscape in Central Angola and locally, through a nested and multi-scale and participatory approach to spatial planning and integration of SLM into prevalent agricultural practices.

In order to effectively contribute to realizing feasible solutions, which are closely related to the project’s outputs, it is necessary to address, not the causes of land degradation in Angola’s central region, but its drivers behind them. While environmentally harmful land-use practices that involve shifting cultivation, overgrazing and fire—all under the umbrella of ‘agricultural activities’—have been identified as the most direct and predominant driver behind land-use change in the region, causal analysis pointed out to a different set of factors as the likely root cause, which lead to the description of the project’s barriers.

In the case of this project, the actual drivers behind the problems are related to technical, institutional and financial capacity, and constitute the contextual barriers. The three main barriers to achieving the long-term solution relate to the following (barrier statements in Figure 16 and full descriptions in section 1.2.3):

Barrier #1. Capacity for complex and geo-based data handling.

- Barrier #2. Sustainable Land Management in target landscapes;

Barrier #3. Financial leverage for SLM

The barrier analysis pointed out to solutions, that were then formulated as project components:

- Component 1. Agroecological zoning (AEZ) integrated planning;

- Component 2. Sustainable Land Management in target landscapes;

- Component 3. Economic and financial leverage approaches to SLM.

There is, additionally, a set of baseline (and related) projects, programs and initiatives that underpin the project’s incremental reasons and justification. They are an essential part of the project’s strategy and create an enabling environment for solutions that will overcome the barriers. Therefore, in order to overcome the barriers to the project’s objective, the project strategy will carefully consider the baseline situation in the context of land degradation. As described in relation to Barriers #1 and #2, a major problem in Angola is the lack of integration and continuity of SLM focused initiatives. The project will pay particular emphasis on tying loose ends and building on past initiatives. There is e.g. a substantial volume of relevant agroecological data produced by different initiatives – data that has not been integrated into a useful and integrated AEZ system. Most importantly, it has not been put to practical use in guiding land-use management in rural areas (see sections 1.1.1 and  section 1.2.3). Such resources will be integrated and complemented with global data sources and data collection on the ground. More broadly, the project will build on the lessons and successes of past initiatives and contribute to the integration of AEZ-based SLM in the preparation of rural land-use plans (already foreseen in Angola’s system of spatial planning), rooting the preparation and implementation of such plans in associated social negotiation processes and agreements.

Central to the rationale of a GEF project, project components are designed to complement ongoing projects and initiatives to accrue global environmental benefits from the project that would otherwise not be created. Various projects are relevant in terms of their technical integration and have been described. Such initiatives are funded both from government and multilateral partners and yet some (non-baseline) from GEF. The project’s fit with the financial and technical baseline is laid out in relevant sub-sections.

The baseline represents also the status quo, or the context in which the project is being designed – and for this project the topic of land degradation in Central Plateau of Angola was the main focus. The analysis focused on land-use / spatial planning gaps, sectoral drivers and the needs for introducing, practical land-use management experiences to different administrative tiers, as well as bringing ‘scale’ to feasible solutions that that the project proposes to realize through its strategy.

For the project strategy to be sound, its Theory of Change needs to adequately draw the linkages between identified drivers, the barriers and the solutions. These linkages are summarized in Figure 16. To add to the analysis, these solutions need to undergo a stakeholder consultation and analysis (section 1.4), which is an important part of the context), as well as a risk and feasibility assessment (Section 2), so as to determine their viability.

These (viability/feasibility) assessments have been carried out during PPG stage. The design of the project framework includes a strong causal link between the projects’ outputs and its outcomes, e.g. the general aim of creating an AEZ-based decision support system for MINAMB (through Outputs 1.1 through 1.4) serves the improvement of the national capacity for SLM, and more specifically: (i) sustainable land-use planning and (ii) rational decision-making on sustainable land allocation and management (Outcome 1.0). Without it, it would be difficult to reverse negative land degradation trends (the subject matter of the project objective), either nationally or in Central Angola. Similar analogies can be drawn for the remaining components.

#### Incremental cost analysis

Table 7. Incremental Cost Reasoning

| Current Baseline (B) | Alternative (A) | Global environmental benefits (A – B) |
| --- | --- | --- |
| In the business-as-usual (BAU) scenario, competing land uses across broad landscapes (e.g. extending the agricultural frontier into forest lands, extractive industry destroying forests, urbanization of rural areas) has become a norm in post-conflict Angola, with no specific mechanism for negotiating the stakes for ecosystem services and biophysical resources such as biodiversity, soil, water and carbon. A legal and policy framework is in place in Angola for developing and enforcing land-use plans in different geographical and jurisdictional settings. However, there are many gaps in the practical application of these frameworks, including technological and capacity barriers. In the meantime, land degradation trends continue to threaten ecosystem services and rural livelihoods, in particular in the Central Angola. Within the Wider Landscape selected by the project for Central Angola, increased competition among conflicting land uses contribute to the loss of vegetative cover, exacerbates erosion and results in the loss of biomass and biodiversity. According to a recent Land Degradation Neutrality (LDN) assessment supported by FAO, ecosystem services are currently in decline in 5 out of the 11 municipalities of Huambo Province, and in 5 out of the 6 non-coastal municipalities in Benguela – all of which are included in the Wider Landscape. At this scale, land degradation negatively impacts the rural economy and its growth potential to the extent that it decreases land productivity, eventually impacting food security and the basis for rural livelihoods. The long-term sustainability of agricultural practices, with negative consequences for the provision of ecosystem services in these landscapes and the socio-economic development of rural communities. | In the alternative scenario, the project will contribute towards the development and scaling up of sustainable and rational approaches to planning, decision-making and land-use stabilization in selected landscapes of Central Angola. It will combine these efforts with the integration of science-based agroecological approaches as through the capacitation of local stakeholders. In the development phase of CETAC’s spatial planning capabilities, (establishing a dedicated Agroecological Zoning (AEZ) unit within the Centre), the focus will be on two provinces: Huambo and Benguela. Component 2 and, in part, Component 3 will be exclusively implemented in these provinces. The project will contribute to building capacity, structures and resources at national level regarding the AEZ, environmental monitoring and using products related to these for decision- making support. More specifically, the reduction of pressures on natural resources from competing land uses, by addressing on the one hand the needs for analysis and measurements across the Wider Landscape in Central Angola, and on the other, by working locally and on the ground with land users, practitioners, and local decision makers. The project will achieve its global objective of contributing to stabilizing land use and reverse negative land degradation trends in selected municipalities of Central Angola by integrating science-based agroecological data as a support tool for participatory SLM planning and implementation through the capacitation of local stakeholders. - At least 100 beneficiaries will benefit from a SLM training program, comprising of: civil servants, AP/FFS master trainers, EDA / IDA technicians, of which at least 20% women. - At least 10 SLM plans will be prepared, directly involving the participation of 450 people of approximately 15 communities in GreeNTD sessions, 50% of which women. - Direct beneficiaries within demo landscapes were estimated at approximately 1,500 engaged farmers and agro-pastoral land users, of whom at least 40% will be women. - Approximately 1.5 million people within rural communes (1.1 million in Huambo and 450 thousand in the Benguela part of the landscape) will indirectly benefit from the project through the work under Component 1 (AEZ studies), corresponding to the total resident rural population within the project’s Wider Landscape. | Applying the Landscape Approach, the project will deliver GEBs by turning science-based agroecological data into a powerful support tool, as well as a mechanism, for planning and implementing SLM at scale across varied landscapes. In terms of scale considerations in the landscape approach, the project will combine ground-level data collection and participatory land-use management with remotely sensed data. It will thereby become an example of land-use management for SLM that operates with multiple-scales and involves multiple-stakeholders in the process. The scales will include: - A Wider Landscape within Huambo and Benguela provinces, located within a sub-humid agroecological zone in the Central Angola and covering approx. 6.1 million-ha. The Wider Landscape is the project’s a broad target for demonstrating SLM results through AEZ, encompassing rural communes within Huambo province and within the 6 non-coastal municipalities in Benguela province. - Demonstration landscapes with a combined surface of approx. 400,000 ha of multi-use landscapes (calculated as 409,699 with break-down shown in Table 2). Demo landscapes are located in selected communes of the municipalities of Londuimbali, Bailundo and Chongoroi, and within which land degradation trends will be monitored and SLM plans developed and implemented. - Demo sites, which are targets at micro-landscape level for agroecological intensification within demo landscapes which cover a total 11,000 to 14,000 ha (rounded off). The estimated area corresponds to approximately 10% of agricultural lands in the Alto Hama and Bailundo demo landscapes, plus 10% of identified rangelands within the Chongoroi demo site (calculated surface is 6,881 ha of agricultural lands, plus 7,800 ha of rangelands, totaling up to 14,670 ha) Agroecological data will be retrieved, collected, collated generated and analyzed within CETAC’s AEZ Decision Support System (DSS), geared towards implementing SLM within the landscapes and at different scales and tiers. The AEZ system will be tailored to the needs of local decision makers and/or stakeholders concerned with land-use management within a wide multi-use landscape in Central Angola. Within the upper tiers of multi-use landscapes in Huambo and Benguela Provinces (wider, macro and micro), the project will, on the one hand, influence planners, land users, local communities and investors to adopt and integrate landscape-level management practices, e.g. through the application of AEZ methods and products, in collaboration with three municipal governments and for communes within them, not least also through collaboration with rural development projects through which FAO’s FFS approach is being implemented. On the other, the project will in the lower tiers directly contribute to attenuating pressures on natural resources and improve the productivity of land within demo landscapes and in demo sites. Direct SLM targets apply to the 400,000 ha of demo landscapes and the support mechanism that the AEZ system represents to the Wider Landscape. Status and trends of land cover and carbon storage capacity of plants and soils will be maintained (as opposed to decreasing) in the next few years, measured as follows: - Vegetative cover: land uses maintained stable within selected demo sites, focusing on on-farm dynamics at the village level within the 3 demo landscapes, the rural communes of Alto Hama, Chongoroi and Bailundo. Together they have a total land surface of at least 400,000 ha of production systems. An estimated target for land-use stabilization within demo sites will reach up to 14,000 ha (in total and rounded down). - Carbon sequestration: relevant parameters remotely monitored in 6.1 million hectares (plus prescribed ground-truthing in areas to be defined), more specifically: (i) Above ground biomass is maintained, with +/-10% fluctuations due to natural climatic variability, at approximately: 41.1 Tons CO2 e/ Ha for Alto Hama 40.8 Tons CO2 e/ Ha for Bailundo 80.2 Tons CO2 e/ Ha for Chongorói ================================= 54.0 Tons CO2 e/ Ha mean for the three combined (ii) Soil Carbon is maintained: ~72.6 Tons CO2 e/ Ha (averages) |
| Without the GEF Project... BASELINE [B] [B] = [B’] + [B”] BASELINE FINANCE ($M), INCLUDING CO-FINANCING FROM BASELINE [B”] [B]; [B"]. C1) AEZ; $28.0; , of which = co-financing from baseline =>; $4.40. C2) SLM; $36.4; $5.2. C3) Fin; $35.9; $4.4. TOTAL ~; $104.4; $14.0. | With the GEF Project... THE ALTERNATIVE [A] [A] = [GEF] + [B] + [X] THE GEF PROJECT with its FULL BASELINE ($M) GEF + BASELINE [B] + LEVERAGED CO-FINANCING [X] [GEF]; +[B]; +[X]; = [A]. C1) AEZ; $1.2; $28.0; $0.000; $29.20. C2) SLM; $0.7; $36.4; $0.000; $37.15. C3) Fin; $0.5; $35.9; $0.000; $36.42. M&E + PMC); $0.1; $0.0; $1.000; $1.13. TOTAL ~; $2.514; $100.4; $1.000; $103.899. | The cost of generating GEBs... THE INCREMENT [C] [C] = [A] – [B’] or.... [GEF] + [B"] + [X] GEF PLUS THE TOTAL CO-FINANCING ($M) [GEF]; +[B"] + [X]; [C]. C1) AEZ; $1.202; $4.40; $5.602. C2) SLM; $0.707; $5.20; $5.907. C3) Fin; $0.479; $4.40; $4.879. M&E + PMC); $0.127; $1.00; $1.127. TOTAL ~; $2.514; $15.000; $17.514. |
| C.① In the business-as-usual (BAU) scenario, the capacity of Angolan authorities, in particular of MINAMB and MINAGRIF, to carry out AEZ or other geo-data intensive analyses for handling spatial planning tools and analysis is limited. National capacity is insufficient to conduct the respective processes and there are no effective capacitation mechanisms to develop such capacity in an integrated and centralized framework. - Knowledge and data on the key parameters for monitoring land degradation have not yet been mastered, despite current related initiatives like the LDN-TSP. - There have been mapping, zoning, and planning initiatives that have not been integrated with one another and have not been put to use by land-use management; and - There are no centralized AEZ-related databases at national level that can accessed and used by relevant stakeholders, including public authorities and the private sector. | C.① The project will build national capacity for analysing the country’s agricultural potential by setting up a system of Agroecological Zoning (AEZ), delivering a science based and interactive system, including open-access interfaces to be used in rational decision-making on land allocation and in the monitoring of land degradation. The scope of AEZ system will encompass the entire national territory, giving priority to AEZ products tailored for the project intervention areas. By the end of the project it is expected that: - A group of national professionals is qualified to run the AEZ system semi-autonomously and replicate the training they received during the project with other professionals; - Previous assessments are integrated in a centralized database with new agroecological data and are used to produce specific AEZ products for different land-use planning initiatives; - The centralized AEZ database produced by the project (and respective products) will be accessible by relevant national stakeholders (including public authorities and the private sector) and AEZ professionals and students across the country through an AEZ online platform; | C.① Improved institutional capacity for spatial planning, land-use management and monitoring, with CETAC, under GABAC’s supervision, creating an AEZ-SLM support mechanism. CETAC becomes a new regional centre of excellence in the field of agroecology, establishing a unique niche for its AEZ Unit, in network with other similar centres of excellence and local Agroecological Centres. By project end, CETAC will be capable of - providing a national institutional support mechanism for measuring and promoting SLM in Wider Landscapes and therefore linking up Angola with other countries in the fight against land degradation. - CETAC expands its GIS analysis and DSS capabilities and sustainably maintains an AEZ unit beyond the project's end. The AEZ support mechanism is consolidated, includes 3 demonstration landscapes, with 10 SLM plans delivered and continued integration of SLM practices through FFSs/APFs through targeted capacity building. |
| C.② Decisions that affect the outcome for land use and natural resources are made without a good understanding of agroecological zones and of their optimal management requirements so as to prevent and reverse land degradation. Within project landscapes, pressure on natural resources is on the increase and land-use change follows an opportunistic pattern. Except in very few instances and with limited scope (e.g. through the completed GEF RETESA and the UNDP GEF projects on LD), land-use planning in rural areas is practically non-existing and land users and managers lack the capacity to apply and disseminate SLM. Several factors contribute to this: - Together with the lack of accessible and useful AEZ products, there is not sufficient national capacity to produce quality and practice-oriented local level land-use management plans for rural areas, especially if such plans are to be based on AEZ products and prepared through participatory and negotiated community-based processes. - The AP/FFS approach has proven to be an effective extension service in Angola, but its potential for promoting the uptake of SLM remains limited without the local SLM plans based on AEZ products and prepared through participatory and negotiated community-based processes that greatly increase community acceptance and ownership. | C.② The project will deliver SLM on the ground, and thereby decrease pressures on natural resources putting land in selected landscapes into a path of restoration/rehabilitation. This will be achieved through participatory land-use planning and enforcement, combined with capacity building in communities already served by a network of AP/FFSs. The project will demonstrate through practical experiences how land use can be sustainably managed on the basis of AEZ products and SLM plans resulting from collective agreements. These local efforts will be supported by the AP/FFS approach. By the end of the project it is expected that: - IDA/EDA extension services, FFS facilitators and the communal/municipal technicians (civil servants) of project intervention areas are capacitated to use AEZ products and SLM plans that have been prepared through the GreeNTD methodology (also based on AEZ products) to guide community-level SLM, with high degree of local ownership and effectiveness for halting and reversing land degradation. - Supported by the infrastructure and capacitation program of the Agroecological Center in Chipipa, EDA extensionists, communal and municipal technicians and AP/FFS master trainers of the targeted municipalities are capable of replicating the approach in other communities. | C.② Multi-stakeholder landscape level planning and management (through GreenTD) involving both public and private sectors to inform decision-making on integrated management of ecosystem services. Measurable global environmental benefits in the targeted project area (3 demo landscapes): - Vegetative cover (natural & cultivated cover such as forest, shrubs, herbaceous, incl. crops) stabilized i.e. maintained in 11,000 to 14,000 ha of agricultural landscapes (surface areas are estimates to be refined during project inception) - 54.0 Tons CO2 e/ Ha of above ground biomass and 72.6 Tons CO2 e/ Ha of soil carbon maintained (biomass and soil carbon loss stabilized) |
| C.③ Despite the growing body of evidence about the costs of land degradation – and the benefits of SLM, there is a very limited pool or resources immediately available for SLM and there are no stable and reliable mechanisms to fund SLM. This can be attributed to three separate problems: i) The state budget is allocating insufficient resources to SLM State budget has shrunk since 2014, as a result of the drop in oil prices. This problem was compounded by the devaluation of the national currency and by the fact that the amounts actually disbursed are often considerably below the budgeted value. Agriculture, that has consistently received a modest part of the state budget, was particularly affected. Funding for SLM was surely affected as a result and given the fact that it is not regarded as a priority in the public policy agenda. ii) There is limited use of existing international sources of funding for SLM Only a small fraction existing international funding sources for SLM is currently being used for SLM initiatives [how much being used], taking little advantage of available funding opportunities. The limited use of existing international sources for SLM funding results from three problems: (i) no one is adequately monitoring and engaging those sources, (ii) there is limited capacity to design high quality project proposals to tap into those resources and (iii) there is a trust deficit in the capacity to properly manage funds. iii) Insufficient private initiatives in SLM and natural resource management There is almost no private sector investment in SLM. Some value chains with a potential to contribute to SLM, such as beekeeping, are managed unsustainably. | C.③ The project’s third component will focus on increasing the amount of resources invested in SLM through identifying relevant sources and developing suitable options for SLM finance and on improving national capacity for mobilizing, investing and managing funds for SLM. This will include financial leverage and scale-up of actions needed for restoring/rehabilitating degraded land, through evidence from economic analyses on the cost of land degradation, and the potential benefits from its restoration in the Provinces of Huambo and Benguela. - Evidence of the costs of land degradation will be produced and disseminated among key decision makers, to increase the amounts allocated by the state budget and by private investment to SLM. - Adequate management of those resources are a key factor to guarantee their expansion and sustainability. With that efficiency in mind the project will operationalize both mainstream and innovative finance options for SLM in the targeted municipalities, in parallel to a capacity-building program for mobilizing financial resources, fundraising campaigns and support to the formulation of SLM projects. In practice all these will booster community-based SLM finance, public-private partnerships and targeted matching grants designed and established to channel funds from various funding sources. - As the practical element of this strategy, local businesses related with potential to contribute to SLM are funded and promoted through the selected financial mechanisms. Targeted sectors and activities may include, seedling nurseries, beekeeping, the harvest and commercialization of wild fruit, fish arming and tourism. will develop relevant partnerships and ensure the integration of SLM compatible practices and the ‘trickle-down’ of resources for SLM and land restoration (in particular to communities), complementing the efforts towards Land Degradation Neutrality (LDN) developed under the other components. The project will attempt to develop relevant partnerships and ensure the ‘trickle-down’ of resources for SLM and land restoration. | C.③ Increased finance for SLM (+10% from baseline), including from innovative market and financing mechanisms that provide incentives SLM approaches, both at the local and at the landscape level. |

#### Technical Integration with relevant projects

There are five initiatives that are especially important for the project’s implementation in terms of technical integration, especially given the focus the project’s core strategy to maximize its impact through the integration of often one-off and siloed initiatives.

##### Land Degradation Neutrality - Target Setting Program (LDN-TSP) and other related projects

With respect to the setting up of the ‘data nexus’ relevant for the broader LDN process, there is room for relevant technical integration frameworks facilitated by this project and involving the LDN-TSP. The AEZ-based decision support system foreseen by this project is considered strategic for providing accurate and up-to-date for monitoring LDN indicators towards the objectives of the LDN-TSP. The AEZ system foresees the integration of national data sources and also data collection initiatives, going much further in terms of data richness than most of the countries participating in the TSP, who mostly merely rely on the collation of default data. In addition, the LDN indicators and targets would also become the benchmark framework for any land degradation-related initiatives in Angola. Refer in addition to Box 5 for information on the potential contribution of a GEF7 project for Angola to the LDN agenda.

Box 5. Linkages to the new GEF’s Impact Program on Drylands

A new GEF-7 FAO child project was approved for Angola under the GEF’s Impact Program titled ‘IP SFM DRYLANDS’. The child projects title is: ‘Land and natural resource degradation neutrality and community vulnerability reduction in selected Miombo and Mopane Ecoregions of Angola (Okavango and Cunene River Basin)’ The new project will promote sustainable and resilient land use practices across productive landscapes in the Miombo and Mopane ecoregions of Angola. A focus on Okavango and Cunene river basins and on Land Degradation Neutrality (LDN) principles are part and parcel of the project’s objective. Three technical components are foreseen: (1) Effective governance support on SLM and SFM in the targeted Miombo and Mopane landscape; (2) Scaling up SLM and SFM best practices at landscape level and with a transboundary focus; and (3) Effective knowledge management, monitoring and evaluation. Collaboration will be sought on the ground and through the participation of CETAC, once the AEZ Unit is fully functional, to assist with assessments and AEZ analysis, which include LDN but is not restricted to it. Overall AEZ results will be substantial building blocks for integrated landscape planning (by taking climate projections and suitable land use opportunities into account). Moreover, the dryland intervention will benefit from the work developed in both demo sites and demo landscapes – i.e. with regards to ‘upscaling’ – as well as ‘outscaling’ – evidence-based best SLM practices. Both projects will pioneer such approaches in Angola.

##### SADCP ("MOSAP II")

SADCP (also known as "MOSAP II") - Smallholder Agriculture Development and Commercialization Project of the WB, was approved in 2016 and counts on a budget of $70M. Its objective is to increase smallholder productivity, production and marketing for selected crops. It is being implemented in Huambo, Malange and Bié Provinces, with MINAGRIF playing a key role. Components include: 1. Capacity building and institutional development; 2. Support for increased production and commercialization; 3. Project management. Under the SADCP Project, the capacity of smallholder farmers and farmers’ organizations will be strengthened in all critical aspects related to agriculture by using and scaling up the FFS approach. Over a 5-year period, project SADCP will operationalize approximately 5,000 FFSs is three Provinces, with 30 participants each, and through the ‘multiplier mechanism’ of FFFs, it will aim at training about 150 000 smallholders spread over 80 communes in 26 municipalities. SADCP will also train master trainers and FFS facilitators, and its FFS training cycle will be similar to that of MOSAP I. Project SADCP is relevant for this FAO GEF Project because Component 2 will, in the case of Huambo province, operate in FFSs sustained by SADCP.

##### ICE-SLM

Under a related GEF project – namely the AfDB/GEF funded project “Integrating Climate Change into Environment and Sustainable Land Management Practices” (ICE- SLM - GEF ID 5231) – the second component is implemented by FAO and it has CETAC as the focal institution. The ICE-SLM Project will activate the four Agroecological Centers (AECs) by using them as a platform for stakeholders to exchange and learn about SLM and climate change by testing innovative participative methods of SLM that meet people’s needs and contribute to global benefits in terms of land and forest management. Should the actual timeline of implementation of the ICE- SLM project allow, this GEF-LD project will fit in this process by using one of the AECs as an antenna for receiving and collecting AEZ data under Output 1.5, and also for hosting a training program for capacitating extension professionals involved under Output 2.3. In close contact with the AEZ team and the AEC technical supervisor, the AEC director in Chipipa will play an active role in coordinating these activities. Should this proposed articulation prove impossible due to delay or cancellation of the ICE-SLM, alternative solutions will need to be devised prior to or during project implementation. Possible arrangements that do not rely on the project ICE-SLM are suggested below in section 1.3.2.

##### Provincial Agro-Zoning in Huambo

There was recently an ad-hoc inter-institutional commission created by the provincial governor that included representatives of IGCA, IDA, the Directorate of Agriculture and the Department of Urban Planning. The military and police provided the helicopters for the aerial survey. The initiative managed to map a rough zoning of what is registered in the cadaster and of what is arable or not. The available resources did not allow doing more (i.e. collection of more data and cross-data analysis) and the project had to be suspended. The second phase of this initiative foresees direct cooperation with MINAMB. In this context, FCA is cooperating with Wageningen University on GIS & remote sensing (which includes the development of an operational GIS room) and with Cordoba University on sustainable charcoal production. About 18 staff members are in the 2nd stage of a training program by a network of Lusophone universities that selected agroecology and food security as a focus for cooperation. The expected zoning for the Central Plateau should distinguish between areas suitable for agroecology, livestock and monocultural agribusiness. As the initiative is still occurring, it is recommended that it is integrated in the present GEF LD project, providing the initiative with a more structured and integrated framework, whilst using the results of this survey to directly feed into the databases of the AEZ system.

##### IRCEA - Increasing climate resilience into Agricultural and agro- pastoral systems through soil fertility management in key productive and vulnerable areas using the farmer Field Schools approach

This GEF-funded FAO project (GEF ID 5432) focuses on strengthening local capacity in the agro-meteorological sector by providing training and scaling up SLM practices through a network of FFSs in Huambo, Bié and Malanje Provinces. The chain of FFS will be strengthened and expanded (e.g. to Huila Province). This project will also focus (among others) on training smallholders in SLM practices and expanding the FFS network. This will be achieved through: (i) mainstreaming Climate Change Adaptation (CCA) into agricultural and environmental sector policies, programs and practices; and (ii) capacity building and promotion of CCA through soil fertility and SLM practices using the FFS approach. The project strategy is built on three main components. The first is to strengthen knowledge and understanding of climate change vulnerability and adaptation. The second is scaling up of improved CCA/SLM practices through FFS. The third is mainstreaming CCA into agricultural and environmental sector policies and programs.

In case of Huambo, IRCEA will mostly dovetail with project SADCP’ FFSs by adding the extra dimension of CCA. It will provide technical support and expertise through updated FFS curricula focusing on: i) improving soil fertility and integrated nutrient management through agroecological practices (including specialized trainings); ii) providing training and curricula on agroecology and environmental practices related to soil conservation, rational use of water, fertilizers, integrated nutrient management and promoting integrated pest management. Given that this GEF LD project takes a similar approach in Huambo in relation to SLM (including the development of local land-use plans in communities served by FFSs) and there is significant overlap in the mentioned themes to be targeted by IRCEA’s FFSs, the interventions of both projects need to be carefully articulated for effective complementarity and cost efficiency.

### 1.3.2 Project Objectives, Outcomes and Outputs

#### Project objective

“To reverse negative land degradation trends in selected landscapes in Central Angola by combining sustainable and rational approaches to planning, decision-making and land-use management with participatory approaches to build the capacity of local stakeholders.”

Three technical components are foreseen under the project. They synergistically combine actions towards the project’s objective. A fourth M&E component supports the first three.

### Component 1) Agroecological zoning (AEZ) integrated planning

Work under Component 1 aims at supporting Angola in building capacity for collecting, generating, analyzing and managing geospatial datasets for the purpose of carrying out AEZ, assessing and monitoring Land Degradation across the country, as well as status and trends of ecosystem services. The AEZ Unit will be hosted in Centre of Tropical Ecology and Climate Change (CETAC), making it a key beneficiary institution and a recipient of focused capacity building efforts of international caliber.

Yet, given the Center’s relatively low capacity baseline, CETAC is expected to create, in the process, several useful collaborative relationships to realize the strategic goal of hosting a unique and service-oriented national geospatial unit, dedicated to AEZ and of servicing potential clients at multiple scales and in multiple sectors. Such clients may include any public or private initiative related to agricultural production or environmental management. On a more immediate level, the AEZ Unit is expected to support the LDN-TSP currently being implemented by the Angolan government. This project will be highly instrumental in creating some of the necessary enabling conditions for the success of the LDN strategy, particularly in setting up the data nexus for all other initiatives that can framed within the broader LDN process. Indicator and targets for the interventions in demo sites under Component 2 include those defined thought the LDN-TSP, thereby going beyond their monitoring and testing the effectiveness of AEZ-based SLM in achieving LDN specific targets.

The above implies that CETAC will need to engage with partner entities, other projects or local initiatives, not least to continuously assess project stakeholders and bridge CETAC’s capacity gap.

The outcomes of AEZ spatial analysis will be a key product that CETAC will produce and make available in a user-friendly manner through a WebGIS Decision Support System, which the project will help create. Once established and tested, the AEZ spatial will be a powerful tool for sustainable land use and management at different levels of decision-making.

AEZ can be regarded as a set of core applications, leading to an assessment of land suitability and potential crops productivity, and a further set of advanced applications that address specific country needs, which can be built on the inventories and results of the core AEZ studies. Outputs of core applications include geospatial datasets showing agroecological zones and land suitability for different combinations of crops, input levels and water supply, and quantitative estimates on potential crop areas, yields and production.

AEZ analysis can incorporate various additional data such as e.g. economic assessments, demographic and statistical information and can serve as an excellent baseline for further complex analysis. Component 1 combines AEZ with analysis and ‘environmental monitoring’ i.e. monitoring of LDN indicators and of ecosystem services in order to provide differently tailored products supporting land-use decision-making at its various levels and scales. The foreseen extensive training will secure the self-sustainability of the introduced framework. The project is expected to actively tap into -- and contribute to -- the growing body of knowledge being developed through the UNCCD’s he Science-Policy Interface, which can be accessed through the UNCCD’s knowledge portal (http://knowledge.unccd.int), including the foundational publication on the topic Orr, B. et al. 2017. "Scientific Conceptual Framework for LDN").

This project also encompasses the initial phase of developing and consolidating a robust Decision Support System (DSS) on land-use management in Angola, which the project will help build. More specifically, the project is initially slated to support the application of AEZ products to SLM planning and field-level SLM in targeted areas of the Provinces of Huambo and Benguela under the project’s Component 2. This system will incorporate already existing and newly collected data and in consequence generate products for the national territory as a whole, or for other provinces outside the two pilot provinces.

However, given the limited funding available to this project and the needs for yielding targeted products under the project’s Component 2, the work under Component 1 will give priority to AEZ products that are useful for the latter, in particular during the project’s two first years. Priority will also be given to handling national data that has been produced through previous projects and existing initiatives, as well as to retrieving globally available data worth applying according to scale, thematic details and expected use. As the AEZ system is developed and becomes robust, and as it establishes a niche for governmental services, it will be possible to collect, collate, analyze data for other provinces, providing thereby services to stakeholders in those provinces. Probing the needs for services, combined with a thorough Capacity Needs Assessment, has been carried out under the PPG and its engagement is recommended.

#### Outcome under Component 1

Outcome 1.0) Improved national capacity for: (i) carrying out AEZ, (ii) monitoring land degradation at national scale and (iii) generating products of spatial analysis in formats useful for SLM

In order to realize Outcome 1, the project will focus its efforts into developing within CETAC a dedicated spatial planning unit – the AEZ Unit -- with focus on SLM, including by engaging 6-12 young professionals (post-graduate level) though a Job Shadowing program, with strong encouragement towards applications from women.

By developing and applying a geographically nested, fine-scale and integrated decision-support system (DSS), CETAC’s AEZ Unit will deliver on-demand services to planners, investors and land-use decision makers at various levels. It is envisaged that the core task of the AEZ Unit is to carry out agroecological zoning studies, generating products of spatial analysis in formats useful for sustainable land use planning. Results from Component 1 will also help Angola to dynamically monitor land degradation neutrality (LDN) parameters and support the implementation of Angola’s LDN targets (as part of the land use planning process) across the country, with reference to Target 3.4 under Program # 2.4.1: Climate Change and Policy 12 on ‘Environmental Sustainability’ under the National Development Plan (PDN).

Additionally, as the unit becomes improves its capacity for GIS and spatial planning, it will also incorporate climate change aspects and related matters into its scope of work. It will deal with at various ‘scales’ -- from macro to micro, and with reference to the tree to four nested scales (or levels) and the tiered nested approach to spatial planning and landscape-level management for SLM. Through this project, the AEZ system will specifically target Benguela and Huambo Provinces, but it will serve for various classes of users.

The project will also develop plans for scaling-up the system’s reach and scope, and for integrating more features into it, expanding the range of services, users and contributors. In the process, CETAC’s capacity to sustain the AEZ Unit will be considered and enhanced.

#### Outputs under Component 1

Output 1.1	AEZ Unit: A service-oriented national data analysis and technical unit dedicated to agroecological zoning (AEZ) and LDN-related geospatial analysis is created at CETAC

Output 1.1. will establish a technical team responsible for carrying out the Agroecological Zoning, accordingly to FAO’s methodology, in the area of the project’s Wider Landscape. The technical unit, henceforth designated as “AEZ Unit”, includes GIS/AEZ experts (on soil, climate, water, agriculture) directly responsible for setting up and running the AEZ system, but also experts in SLM, agro-economy and SLM finance responsible for conducting activities under Components 2 and 3.

The AEZ Unit will be hosted in Centre of Tropical Ecology and Climate Change (CETAC). CETAC is an important institute under MINAMB, directly managed by GABAC and has been in operation since 2012. The Centre is tasked with conducting environmental research and monitoring at national level. Although currently its capacity is not sufficient, MINAMB has developed medium-term plans for developing and progressively capacitating CETAC so it can effectively fulfil its mandate of being a central piece of the MINAMB’s environmental governance system. Given the project’s geographical scope, CETAC was identified as the entity that is best prepared in terms of both infrastructure and projected role/mandate to host the AEZ Unit and subsequently serve as a hub for national experts.

GIS experts with the support of trainees, selected CETAC’s staff members and the partners’ technical assistance, will be responsible primarily for carrying out all rolling tasks for Component 1 for the duration of the project. They will be involved in training activities and contribute to development and maintenance of the DSS. With regards to Component 1, the SLM experts will share the responsibility in ensuring that products generated by the Unit (e.g. maps, manuals, guidelines, a management interface, a user-friendly platform) are adjusted to the needs of their users and thus adequate to be employed by the national administrations and stakeholders for the decision-making processes.

Output 1.2	AEZ Services: CETAC is progressively capacitated to (i) serve as a hub for AEZ experts, including by leveraging at least 2 strategic partnerships, and (ii) maintain the provision of AEZ services to at least 3 national entities/clients beyond the project’s lifetime

In order to achieve the goal of improving CETAC’s capacity to ensure sustainability in the flow of services provided by the Unit after project’s end, young talent will be involved in the Unit’s activities according to the principle of learning-by-doing and ultimately prepared to maintain the Unit semi-independently. More specifically, a Job Shadowing Program will be launched and through it, six young professionals (trainees), of which ideally at least two women, will be recruited. These persons can potentially join the Unit after project’s end. The trainees will be ‘paired’ with six members of CETAC’s staff. As the technical experts interact with and incrementally integrate the trainees and professionals working at CETAC in their activities, they will progressively delegate responsibilities according to the developed capacities.

In addition to the Job Shadowing Program, the AEZ Unit will develop and deliver a training program, dedicated to capacitating CETAC’s professionals, in collaboration with experts from the Faculdade de Ciências Agrárias (FCA) and the Instituto de Investigação Agronómica (IIA). Depending on partnerships to be firmed up under Output 1.2, the Unit will ideally engage at least two experts seconded by the academia. This would function as a form of on-demand technical assistance according to specific needs. The training program will be divided into thematic modules and delivered during pre-scheduled working sessions. This element of training and capacity building is a central part of the project’s strategy, and crucial for the project’s long-term sustainability. From the onset, plans will be made for a sustainable hand-over of the infrastructures, equipment and data to MINAMB by project end, but in particular of the capacity (know-how), so the investment can have an impact and be sustainably maintained beyond the project’s lifetime.

An important aspect of capacitating CETAC to play a central role as a national hub and the national institution of reference for AEZ across Angola, will be the establishment and maintenance of a network of professionals involved in AEZ, LDN and ecosystem monitoring at national level. Two institutions will be involved at project inception, given their role in producing knowledge and training professionals in the agricultural sector: FCA and IIA. FCA is developing a GIS unit with the support of University of Wageningen and IIA has an agreement with project SADCP to cooperate on soil sciences the development of technology packages for small farmers. Both initiatives will establish an organic relationship with the AEZ Unit. A LoA will be signed with these organizations and ad-hoc work and training sessions will be scheduled between AEZ Unit members and professionals from those organizations according to the needs, but within the pre-agreed thematic scope. Additionally, the Unit will develop two further partnerships until project end.

Operating mostly remotely via internet, the network will include professionals from academic institutions, governmental entities and NGOs across the country. They will be identified and reached through systematic outreach performed by Unit members. Close collaboration with FAO CBDS Unit is foreseen in under outputs 1.2., 1.3. and 1.4.

Output 1.3	LDN monitoring: AEZ Unit provides services on monitoring of land degradation and of ecosystem services within an area of 6.1 M ha i.e. the project’s Wider Landscape

Based on the data obtained and analysis carried out for the AEZ exercise, and whenever possible collecting data for the entire territory of Angola, the Unit will be systematically carrying out the following “environmental monitoring” activities:

- Spatiotemporal assessment of Land Degradation through monitoring of LDN indicators: (i) land cover and land cover change, (ii) land productivity and suitability, and (iii) carbon stock above and below ground and identification of LD hotspots;

- Monitoring of other LD-related measures, such as soil erosion, disruption of biological cycles, nutrient depletion, soil pH, as well as key ecosystem services and climatic conditions for agriculture through proxies such as precipitation levels, number of rainy days, monthly maximum and minimum temperature, humidity, etc.

Overall, the AEZ Unit is expected to broaden the analysis whenever data and funding availability allows, ideally to the entire national territory. The UNCCD’s scientific conceptual framework for LDN is developing and it will be applied. Guidance on it can be freely accessed through the UNCCD’s knowledge portal and the project will actively use this guidance for the purpose. Exchanges between the Project and the UNCCD’s Science-Policy Interface are also encouraged in this framework.

This analysis will complement outcomes of the AEZ-based decision support system. It will aim primarily at reaching farmers with dynamic information regarding changes in climatic conditions, land degradation levels, etc., useful for shorter-term decision-making i.e. used by farmers in planning their farming activities.

The assessment of land degradation will contribute to the ongoing country-level process of LDN, funded by the UNCCD’s Global Mechanism and implemented by MINAMB’s GABAC in Angola. The assessment of LD will be based on the work undertaken so far by the LDN process and then closely collaborate with the initiative in order to work out a systematic way of monitoring and quantifying Land Degradation hotspots and areas where vulnerability to land degradation is increasing or where potential impacts are particularly harmful for ecosystem services and/or socioeconomic activities. As mentioned before, the products described here will also be available to other projects funded by WB, IFAD, ADF, AfDB or others, as a paid service.

Wherever possible, different land monitoring tools will be used, particularly in line with other initiatives present in the country, i.e. the TCPF project and the LDN initiative. These tools will include Collect Earth – a tool developed within the Open Foris Initiative hosted by FAO and dedicated to data collection though Google Earth. It is important that Collect Earth is included among the selected WebGIS tools to ensure alignment with the LDN initiative in Angola and other land degradation assessments being carried out in FAO projects, which are also employing Collect Earth. The monitoring activities will be developed in coordination with the National Institute for Meteorology (INAMET) and the Office for Food Security (GSA). These institutions are going to be consulted and are expected to participate in data provision. A LoA will be drafted for this purpose.

Output 1.4	AEZ System: The AEZ-based fine-scale WebGIS decision support system (DSS) for SLM, LD and ecosystem services monitoring is developed, covering 6.1 M ha (the Wider Landscape), providing relevant products and creating a framework for the project’s national up-scaling

The envisaged DSS will handle fine-scale data and produce reports and maps with a focus on sustainable land-use planning, ecosystems management and agricultural productivity and suitability. The scope and type of products that are foreseen prepared by AEZ Unit are listed below:

Table 8. Proposed Products that the AEZ Unit will focus on

| Products | Notes |
| --- | --- |
| Raw geo-based data | Currently diffused, they will be searched, solicited, obtained and sorted; and thereafter organized, concatenated and availed to system’s clients in a Geocatalog, as a priority activity. |
| Maps of varied types and scales | Maps of medium (province, municipality) to large scales (e.g. area of specific communities in the municipalities selected by the project), and different levels of generalization, presenting Agroecological suitability and economic performance of farming systems, combined with information regarding LD status (LDN indicators) and dynamic climatic and soil information (particularly for large-scale maps). Maps for AEZ will cover the soil, terrain, climate and land use characteristics and suitability. Current condition of cropping systems should be evaluated against possible alternative most suitable crops. They should also include different types of management applied at the finer possible level. |
| Guidelines | Two main types of guidelines are required: - For the purpose of long-term decision making - development of SLM plans: providing selection of solution packs, taking into consideration various farming techniques and other income-generating activities. - For the purpose of short-term decision-making: of practical and technical character, adjusted to the scale of individual farmer and aligned with SLM plans. These guidelines will include more of ‘dynamic’ information to support day-to-day farming activities on the need basis. All guidelines will be prepared by the AEZ Unit. |
| Miscellaneous | Custom-made assessments for specific areas and commercial clients to be produced directly by the AEZ Unit and to be charged for. |

Considering the different scales of services that will be rendered by the AEZ Unit and the current global trend to freely provide GIS information through World Wide Web platforms, most of the foreseen products will be generated by users through WebGIS DSS, operated and maintained by the AEZ Unit. For this output as well, the AEZ Unit is expected to broaden the analysis whenever data and funding availability allows, ideally to the entire national territory.

See Figure 17 and Figure 18 further down for an illustration of how the products relate to different clients/beneficiaries, different scales of decision-making and how they will be indicatively delivered. WebGIS DSS will be an open geospatial portal comprising of a WebGIS application for supporting decision-making and a catalog application for managing geo-spatial resources. The Geocatalog will provide centralized collection of baseline data. The main sources of geo-referenced data are national datasets (primary source) and international data services. If need be, some of the required layers might be produced by the Unit. In its search for data, the Unit will make use of achievements of past and ongoing initiatives, such as the survey by Work Group for Cropped Land, the 2004 Huambo Baseline and Data Assessment Studies and the 2013 Huambo Province Environmental Strategy.

Figure 17. Actors and Stakeholders of Component 1

The WebGIS will based on the web mapping process and comprises of a server side system where spatial data is hosted and from which it is broadcasted over the internet as images or vector data, and a client side system where data layers are accessible by authorized users through a browser and where operations and queries on data can be performed. For the purpose of the latter, the system will incorporate appropriate toolsets that will allow users to perform actions such as delineating areas, zooming in and out, printing exportable maps, etc. Additionally, the system will offer a toolset allowing users to obtain a report for selected areas, including area-specific information such as land degradation, types of land use, areas of agroecological suitability per crop or farming system etc. Additionally, the report will include guidelines adjusted to the size of delineated areas and aligned with SLM plans. The Geocatalog will be a tool for sharing data and metadata between interested parties.

A set of Open Source services will be used as solution for the projected WebGIS DSS. They must include a web server, CMS, a cartographic web mapping client (Collect Earth), maps server, data service, reporting service and Geocatalog. Hosting will be done by a dedicated or shared reliable and efficient web server. The system will be designed in a way that will enable its scaling up to a national scope as well as including further tools and functions.

Given the uncertain capacity of future WebGIS DSS users, and the fact that the products to be generated need to be designed in a way that would make them useful, accessible and user-friendly, a set of surveys will be launched:

- At project inception: (i) users’ preparedness survey in connection with WebGIS (ii) existing DSS products – survey taking stock and investigating reasons why existing products are not successfully used; and

- Annual surveys of user experience with the WebGIS DSS.

In response to potential knowledge gaps, discovered by the surveys, a training program will be developed, targeting civil servants, along with development and implementation of e-inclusion strategy.

Figure 18. Relations between target scales, products and clients of AEZ Unit

Output 1.5	A two-way hub is set up for (i) collecting AEZ data and (ii) generating AEZ products through WebGIS DSS platform

The four Agroecological Centers (AECs) in Angola (in the provinces of Huambo, Namibe, Cabinda and Cuando Cubango) were established in 2015 by the AfDB/FAO’s Environmental Sector Support Project (ESSP). However, they have not been immediately put to use for providing the expected services and remained generally inactive due to inadequate planning and management approach, that focused only on infrastructure but not on the human resources and management structure needed for their operation. This gap is to be filled through a related AfDB/GEF funded ICE – SLM. This project, through a management unit hosted in CETAC, will activate these four AECs. It will also assign an AEC technical supervisor at CETAC and an AEC director for each of the four AECs. The AEC technical supervisor will maintain regular contact with the AEZ Unit at CETAC to facilitate integration and maximize the synergy potential between the two projects.

This project, through the AEC in Chipipa, will make a two-way connection between the expertise of AEZ Unit and the farmers in selected intervention areas. If successful, the post-project replication of the model will effectively place CETAC as an effective hub for the AEZ system using the AECs as regional antennas in integration with the ICE-SLM project, in which the AECs will function as data collectors and demand channeling centers. As the scope of the Unit’s analysis is projected to be scaled up in time, other centers will be included performing similar roles. More specifically, the AECs will be used as antennas for receiving and generating information and for collecting ground-truth data for the use of AEZ Unit. The latter will be performed based on protocols for data collection and exchange, to be proposed by the Unit during the inception phase of project implementation.

The process of integration and joint capacity development of AEC in Chipipa, will be reinforced by a separate training program delivered to AEC staff through a consultant firm and prepared in a collaboration with the AEZ Unit members, the AEC technical supervisor and the AEC director in Chipipa, who will also supervise its gradual implementation. The training will incorporate two major aspects of being a two-way hub – adopted into two modules: (i) data collection techniques and (ii) using maps and other information generated directly by the Unit or through WebGIS DSS. Optionally, other modules can be added, and the scope of training extended. This way, the personnel of AEC, initially in Chipipa and ultimately in other locations, will serve as a proxy between expertise of the AEZ Unit and the farmers. Under this project’s Component 2 regarding the integration of AEZ products into decision-making under Component 2, this type of relationship is extended downward to turn the AECs into regional hubs for the networks of FFS and APFSs.

Note: Should this proposed articulation with project ICE-SLM prove impossible due to delays or project cancellation, alternative solutions will need to be devised prior to project implementation. A possible solution would be to use the commune of Alto Hama as the intended hub. According to the conducted consultations, eight (8) FFSs in the vicinity of Alto Hama are very close to each other and already work quite well as a network. These FFSs are technically still in the 1st Cycle but the EDA technicians who support these AP/FFSs expressed the view that of these could pass to the 2nd Cycle and some to the 3rd Cycle. The facilities of the Commune of Alto Hama would function as an “antenna” for receiving, collecting and sharing AEZ data with CETAC and the demo sites (Output 1.5) and host the activities foreseen for the AEC under Outputs 2.2 and 2.3. The practical components of the training would take place in the FFSs around Alto Hama. As project ICE-SLM was considered as certain at the time of the PPG studies, this scenario was not envisaged and thus the capacity of the Commune of Alto Hama to enable this solution was not assessed. One can assume, however, that this scenario would involve hiring at least one national GIS expert for facilitating and providing requested services and a room with the appropriate equipment: two computers, a plotter, a printer and a reliable internet connection.

/ See Appendix I) Logical Framework Matrix for the indicators and targets for Component 1. /

/ Refer to Appendix III for full list of activities under Component 1. /

### Component 2) Sustainable Land Management in target landscapes

The project’s Component 2 deals with the integration of the outputs of the AEZ-based decision support system foreseen in Component 1 into decision-making at municipal and local (commune and village) levels. The component’s objective is the effective integration of rational land-use management (using science-based agroecological data) that is able to prevent and reverse processes of land degradation while increasing agricultural productivity. Key to the success of this objective is the endorsement and ownership by administrative authorities and local communities of the proposed allocation of land use based on SLM plans.

For this reason, such stakeholders will be involved in a process of negotiated territorial agreements through participatory methodologies (GreeNTD) that will form the basis of local SLM plans (Output 2.1). SLM arrangements and agricultural methods based on the mentioned SLM plans, will be implemented at village level through the existing network of AP/FFSs in Huambo and Benguela (Output 2.2), with the AEC serving as a centralizing hub for structuring the project’s strategy for capacity building (Output 2.3). Outputs 2.1 and 2.2 will be targeting three specific municipalities: Londuimbali, Bailundo (Huambo), and Chongoroi (Benguela), whereas the training program foreseen by Output 2.3 may also benefit other municipalities who shall be invited to participate voluntarily.

Gender aspect highlighted. While men dominate most decision-making in Angola, women are the most active element at the community and farm levels, and so perhaps the most important target for the promotion of SLM on the ground. In addition, women often have a more prominent role in the rearing and education of children, and therefore constitute an essential channel for dissemination of good practices in a vast range of socially and environmentally relevant areas, including those related to SLM. For these reasons, the activities under Component 2 will pay special consideration to dimension of gender. See also section 3.6 for “The Gender Action Plan”.

#### Outcome under Component 2

Outcome 2.0) Selected rural communities, supported by SLM-trained extension workers through active AP/FFSs, collaborate to promote agroecological approaches, including participatory land use decision-making, in at least 400,000 ha of multi-use demo-landscapes

Of the approximately 100 AP/FFSs established in Huambo and Benguela Provinces, half of them are still active today. They have been established by donor projects MOSAP I and RETESA in the past or more recently by IDA.

In Huambo Province, the largest concentration of AP/FFSs is in Bailundo municipality, followed by Londuimbali. According to the 2014 Census, the commune of Bailundo is the most populous of the three demo landscapes, with a total population of 102,000, of which some 50,000 were classified as rural (i.e. with reference to the rural commune of Bailundo). By end-2018, it was assessed that Bailundo municipality harbored some 15 active FFSs, most of them within Bailundo commune, supported by project SADCP. The rural commune of Alto Hama, which has a total population of 36,000 inhabitants, includes 12 FFSs.  In Benguela Province, there are 2 APFS in the rural municipality of Chongoroi, which were surveyed during PPG. They are respectively located in the two communes within that municipality, namely Chongoroi and Bolonguera, and whose total rural population is 32,000 inhabitants (see e.g. Table 14 for an overview of the profile of communities consulted during the PPG in Alto Hama and Chongoroi.) The rural commune of Bailundo will be surveyed during the project’s inception.

A total of 20 members and leaders from AP/FFSs located in Alto Hama and Chongoroi communes were actively consulted and engaged in the project during the PPG stage (Table 14). It can be assumed that each member of an AP/FFS represents an individual rural household in those communities. The number of members in AP/FFS varies from year to year, but the average in Central Angola is 35 members per AP/FFs. Therefore, the potential project beneficiary at the local level in the three demo landscapes the total number of beneficiaries was estimated at 1,508. This number is broken down into: 1,106 in Alto Hama, 442 of whom are women, 216 in Chongoroi, 86 of whom are women, 186 in Bailundo, 74 of whom are women. The beneficiary target for women is 40% of the total number of beneficiaries.

The selection of these communes as project intervention landscapes and the engagement of their local leadership during the PPG phase is a direct result of their participation as beneficiaries in projects such as MOSAP I or RETESA. Together, this small and local sample of AP/FFSs represents some 500 farming and pastoral households in the mentioned rural communes, within which indicative demo-landscapes have been outlined and will be targeted under Component 2 for improved land-use management. In these demo landscapes, SLM approaches on-the-ground will be either started, tested, sustained or extended through the project.  Figure 19 below outlines the circulation of the main information flows under Component 2. The Agro Ecological Centre of Chipipa will have an instrumental function in this system, being used more as training/meeting center more than information processing centre.

Figure 19. Main Information flows in the implementation of Component 2

With the help of SLM-trained EDA extension officers, communal and municipal technicians and AP/FFS master trainers, the 500+ farming and pastoral households will spearhead a collaborative process aimed at managing the agricultural landscapes and rangelands more sustainably, including through agroecological methods and approaches.

With the above presented data, project target for demo landscapes have been set. It is expected that, as a result of the project, at least 400,000 ha of land will come under more effective agricultural, rangeland and pastoral management, where the functionality of the protective land cover is safeguarded, harmful landscape fires are, where feasible, avoided and that knowledge on agro-ecosystems will contribute to improved land productivity. In fact, the more sensitive SLM indicators should be able to reveal the gradual process of land rehabilitation that will be initiated by the project within the demo landscapes. In addition, techniques of participatory decision-making will be sought implemented with the support from the project. Across the landscapes, the project will influence land use in a manner that pressures on natural resources, that are often driven by competing land uses, be at least attenuated, and in some places – in demo sites within demo landscapes – be visibly reduced.

In addition, context and audience appropriate AEZ products will be developed and put to use through the work on the ground at these demo landscapes, will be some of the techniques and approaches that will be promote. To realize the proposed work, three outputs have been conceived.

#### Outputs of Component 2

Output 2.1	SLM plans: Community-level land-use plans integrating AEZ and SLM are prepared through a participatory approach (GreeNTD) in three municipalities as part of a nested approach to landscape-level management

Based on the data and tools compiled by the AEZ Unit at CETAC, which include land degradation background data and data from the LDN assessment, the SLM plans will determine land-use allocation and establish objectives based on the adopted specific LDN targets that are applicable to the targeted landscapes. See subsection Supportive approaches and tools under Section 1.3.1 for the full list of LDN targets.

In order to meet the LDN targets, the SLM plans will define socially negotiated land-use arrangements for implementing SLM in a group of targeted communities in two municipalities of Huambo (Londuimbali and Bailundo) and one municipality of Benguela (Chongorói). The SLM plans are to be prepared in a participatory process of negotiation and collective agreements that are formalized “in paper” and validated by communes and municipalities. More concretely, this process will involve the following steps:

STEP 1)	For each of three selected municipalities, the AEZ technical Unit at CETAC will — based on the AEZ data collected, compiled and analyzed up to that moment — produce fine-scaled municipal-level zoning with recommended land-use allocation that is optimized for SLM, paying special attention to the preventive and regenerative measures in areas that are particularly vulnerable to land degradation. The proposed land-use allocation will aim at achieving the applicable specific LDN targets, taking into consideration the specific strategies that the GoA has established for meeting the LDN targets. Among a description of soils, current land uses and other environmental parameters, they should include recommendations for different management typologies, measures and methods of agro-pastoral activity to be adopted according to the types of agroecological areas in terms of topography, soils, types and causes of soil degradation. It is important to note that these zoning products are based merely on agroecological conditions and do not constitute land-use plans, not taking into account the socio-economic dimension of current and prospective land-use. Rather they lay the agroecological groundwork for the community-level deliberation and negotiation processes (step 3) to find workable context-specific compromises from the point of view of the communities managing land use on the ground.

STEP 2)	The administrations of targeted municipalities and communes are first contacted and informed of what is intended by the project in general and the process for preparing community-level SLM plans in particular. The municipal administrators are then expected to appoint municipal and communal (if applicable) technicians to monitor and participate in the GreeNTD process at local level. The municipality is the obligatory element of the processes, and communal administrations are involved only when they have capacity to do so, otherwise only the municipality. If communes have such capacity (i.e. technicians able to participate in the process), then municipal and communal technicians participate in parallel. The municipality is therefore always involved.

STEP 3)	Based on the municipal AEZ products prepared by the AEZ Unit, GreeNTD processes occurs in several phases at the level of the Jangos in the selected communities. These involve a process of negotiation between the stakeholders of each community, leading up to collectively agreed land-use allocation and practical arrangements for SLM. This process is driven by the SLM experts and the decision-making expert from the AEZ Unit and, in addition to community stakeholders, GreeNTD sessions will also include the participation of EDA technicians, AP/FFS master trainers and communal/municipal technicians. More than just a facilitating or observance role, the latter also have a say regarding the proposed agreements. In each community, the GreeNTD sessions should take place within a period of no longer than four months, followed by a two-month drafting of the resulting plans. (Refer to Box 5 for gender considerations.)

STEP 4)	This activity deals with the validation process of the SLM plans that resulted from the local negotiated agreements. The process of adjustment and validation takes place at the municipal CACS (see reference in Box 5), which includes the participation of the Municipal Administrator, the Communal Administrators of the respective municipality, and a variety of actors of local socioeconomic relevance (whose participation in the CACS is determined by invitation of the municipal administration). The municipal and communal technicians who are following the process, together with the national SLM experts and the expert in decision-making, also participate in the sessions of the municipal CACS. This step is expected to require between one and two sessions, depending on the need for adjustments. The documentation related to the plans will be provided for consultation prior to the CACS meeting for greater efficiency and productivity.

STEP 5)	Validation and formal adoption of local SLM plans by each municipal administration, which also designate the municipal officers for overseeing the respective implementation. Already operational in their own right, these plans are to integrate the municipal land-use plans (see Box 5 below). Although the SLM plans are validated and formally adopted at municipal level, the proposed bottom-up approach respects the principle of subsidiarity and encourages a strong ownership of the process by the involved communities. Since the actual validation will already have occurred through the CACS, this step constitutes the formal adoption of the plans after clearance from provincial authorities. This will take place in single ceremonial events in each of the targeted municipalities, also attended by provincial authorities.

Note on the number of SLM Plans: There are cases where there may be one plan per community, but others where one plan may cover several communities. For example, according to the conducted consultations, the eight (8) FFSs in the vicinity of Alto Hama are very close to each other and already work quite well as a network. In this case it would not be difficult to make a common SLM plan. The exact number of plans is difficult to define at this stage, but it has been assessed at approximately 10 SLM plans, which will directly involve the participation of some 450 people from approximately 15 communities in GreeNTD sessions, 50% of which women. The resulting SLM plans should cover an estimated area of 400,000 ha.

Box 6. Notes on SLM entry points into the national system of spatial planning and extension

Legal Institutional Framework + Gender

Legal basis and validation: As described in section 1.1.1, articles 31º, 32º and 33º of the “Planning Law” or LOTU (3/04) establish that different types of land-use plans are prepared and proposed by municipalities. Along the Municipal Master Plans (PDMs), these include Rural Land-Use Plans (PORs), which are regulatory plans that establish the rules of occupation and use of the rural areas of the municipal territory. The PORs also set out the models for the preservation and evolution of spatial, natural and human organization, namely, potential areas of mineral exploration, the qualification of agricultural land according to their suitability or crop types, as well as other assets, including economic, natural, landscape and social aspects of rural territorial spaces, in order to provide better living conditions for citizens. Such plans, however, are yet to prepared in Angola. National efforts in developing the Angola system of spatial planning have given priority to urban areas and regarded rural areas as secondary. As a result, a good number of municipalities, including the three targeted municipalities, are now equipped with PDMs but no land-use plans for the rural areas that are detailed enough for guiding SLM.

Institutional anchoring: The SLM plans proposed in this project will provide community-level plans that, in close articulation with the INOTU, are to become constituting parts of the future PORs, thus contributing to the groundwork of a nested approach to the integrated management of these rural landscapes. Until PORs are developed, it is proposed that the SLM plans constitute annexes in the existing PDMs.

The role of local councils: Municipalities have, in addition to the “Municipal Administrator” and a “Deputy Municipal Administrator”, a technical team with variable technical competences and a CACS (Council for Social Consultation and Concertation / “Conselho de Auscultação e Concertação Social”). The same structure is replicated at the level of the commune. The CACS, which normally meet every three months, usually include community authorities (the sobas), local associations and NGOs, religious authorities, people of social and economic importance, companies, among others. Their participation as members of the CACS is determined by invitation of the municipal or communal administration. Currently under public consultation, there is a legislative reform planned regarding the way municipalities function politically, under which the CACS will be replaced by Municipal Councils. This process will be implemented progressively in a phased approach from 2020 onwards and expected changes will not substantially affect the implementation of this project.

Gender Mainstreaming: The territorial agreements reached through GreeNTD will reflect the careful consideration of how land-use will affect the well-being of women, including their rights and opportunities for social advancement. Refer to section 3.6 for additional considerations and entry points for gender mainstreaming and gender-related safeguards. Else, extensive documentation and opportunities for experience exchanges regarding ‘GreeNTD & gender relations’ are readily available to the project within FAO’s realm. See e.g. section on knowledge sharing & lessons learned.

Cooperation with EDA and AECs for demonstrating Agroecological Trials and testing SLM solution Concerning Outputs 2.1 and 2.2

Institutional articulation and collaboration: EDA facilitators and master trainers that will be assisting communities learning and applying SLM in practice are trained, guided and coordinated by the two experts in SLM from the AEZ Unit at CETAC. This will be based on the SLM plans and resort to available AEZ products. A rotational system between the two experts in SLM of the AEZ Unit will be scheduled so as to cover all the targeted communities. The two experts will visit each FFS on a regular basis and alternate those visits with remote training and supervision. Visits will first be monthly and progressively occur in larger intervals as the EDA facilitators and master trainers become more autonomous.

Output 2.2	A network of AP/FFSs (Agro-Pastoral and Farmer Field Schools) in three municipalities is supported in implementing SLM plans and promoting SLM practices

The project will support a network of approximately 15 existing AP/FFSs in integrating SLM as a fundamental dimension of land use at village level, thus integrating SLM in a successful model of knowledge uptake by local community members (including women). The practical application of SLM by communities will be based on the SLM plans produced by Output 2.1 and on the AEZ tools of Output 1.3. It is the EDA technicians and technicians (including master trainers) that will be training communities to use the SLM plans and apply SLM in practice, buy they will need coordination, guidance and training.

The international expert in SLM and the two national experts in SLM will assist and train the EDA technicians and AP/FFS master trainers in strategically adapting the activities of the AP/FFSs to support the implementation of the local SLM plans. Activities under this output will begin once the SLM plans have been adopted and will continue until the project’s end date.

Part of the training received by the extension professionals will occur under the structured capacity building program of Output 2.3 through the AEC in Chipipa but will mostly take place in the respective communities during the weekly AP/FFS meetings in a learning-by-doing approach to capacitation.

The implementation of the SLM plans will continue to pay special attention to the compliance with the collective agreements in regard to their possible effects on women and closely monitor if their practical implementation results in unanticipated negative effects on the general well-being of women and the distribution of resources and benefits across the gender divide. The capacitation strategies at community-level will take into account the specificities of the roles of women within communities and be adapted to more responsive to their specific capacitation needs.

Demonstrative agroecological practices will also be conducted at the AEC, together with experts and advanced students from FCA and IIA. AEC will function as a test ground for the preparation of solutions to be replicated at AP/FFSs, consolidating its role as a knowledge development and teaching center.

Once the support of AEZ products is available, demonstrative agroecological trials undertaken by the AP/FFSs and AEC will contribute to validate the land-use recommendations from the SLM plans in the eyes of the community, or inversely, lead to the identification of gaps in the AEZ system and data whose interpretation needs to be confirmed or revised.

The positive or negative feedback from the agroecological trials shall be reported on a regular basis to the AEC in Chipipa, which in turn feeds these data into the AEZ Unit at CETAC. The AP/FFSs in the project’s intervention areas in Benguela will establish exactly the same relationship with the AEC in Chipipa as those in Huambo.

Based on the arrangements adopted in the SLM plans, an adequate portion of public land within each village may be designated for assisted or unassisted natural regeneration (fallows) to ensure the continued flow of ecosystem services to the remainder of the landscape. Techniques ranging from passive to active land rehabilitation on the one end (recovering the ecological structure and functions), and then to outright land restoration on the other (reconstitution of vegetation cover emulating natural ecosystems as much as possible) will then be applied within these areas for demonstration purposes and ecosystem services.

As with other SGD-related targets, LDN targets have been set for 2030. Within demo sites, this project will seek to demonstrate the effectiveness of AEZ-based SLM for achieving LDN and the and specific targets of the LDN-TSP within a shorter time span, i.e, by project end. This applies to the general LDN goal of “achieving neutral land degradation by 2030 compared to degradation levels for 2015” and also to the specific LDN targets that are relevant to the selected landscapes:

- Reduction of marked land degradation by around 50% compared to the reference year (2015) for land where agriculture is currently practiced;

- Restoration of 50% of ecosystems currently degraded by unsustainable land use practices;

- 30% increase of soil organic carbon content (SOC) in all land classes and halving (0.4%) the current rate of deforestation throughout the country;

- Reinforcing information, education and awareness-raising on good land-use practices including those linked to sustainable agriculture-conservation for 80% of rural households;

- Reduction of 25% of livestock in areas with a strong tradition of livestock production;

- Reduction of greenhouse gas emissions by 50%.

Output 2.3	A broad training program focused on SLM and the use of AEZ products for supporting decision-making at community-level is institutionalized and delivered through a regional antenna

The AEC in Chipipa will host a training program focused on SLM and the use of AEZ products and the negotiated land-use plans for supporting decision-making for SLM at local level. This program for capacity building will be institutionalized and delivered through the Chipipa Agroecological Center in the Province of Huambo in close articulation with the AEZ Unit at CETAC. There will be a 2-month preparation phase in which the SLM experts of the AEZ Unit, together with the other members of the AEZ Unit and the Chipipa AEC director, prepare in detail the curricular modules, calendar and the pedagogical methods to be used. The calendar will have to consider growing seasons and the necessary time lapses for the demonstrative agroecological trials to be meaningful to the participants.

Should this proposed articulation with project ICE-SLM prove impossible due to delays or project cancellation, alternative solutions will need to be devised prior to project implementation. A possible solution would be to use the commune of Alto Hama as the intended hub. According to the conducted consultations, eight (8) FFSs in the vicinity of Alto Hama are very close to each other and already work quite well as a network. These FFSs are technically still in the 1st Cycle but the EDA technicians who support these AP/FFSs expressed the view that of these could pass to the 2nd Cycle and some to the 3rd Cycle. The facilities of the Commune of Alto Hama would host the foreseen activities under Outputs 2.2 and 2.3 and function as an “antenna” for receiving, collecting and sharing AEZ data with CETAC and the demo sites. The practical components of the training would take place in the FFSs around Alto Hama.

Box 7. On the training program for land-use decision making at community-level

SLM & AEZ focused specific features, gender and geographic coverage

Structured in modules, the training program will include as a minimum: - Training for municipal civil servants, AP/FFS master trainers, and EDA / IDA technicians on generating and interpreting AEZ products through the WebGIS DSS platform; - Training for municipal civil servants, AP/FFS master trainers, and EDA / IDA technicians on using such products for SLM; - AP/FFS methodology and approaches for integrating SLM for EDA technicians and AP/FFS master trainers with practical trials conducted in cooperation with researchers and academics. This last point is designed to assist the implementation of Output 2.2.

Indicative curricular topics of the program may include the following (a is provided): - Low soil fertility and how to address it through SLM techniques; - Deforestation and production of charcoal (partly a consequence of the previous topic); - Use of fire (resulting in large losses of organic matter that could be use as fertilizer as well as trees/forest); - Soil erosion (some of the physical erosion is very visible, as the forming of ravines, but some of the erosion processes are much less visible in the form of the loss of fine soil materials and consequent loss of fertility). The above is a non-exhaustive list and based on the project’s threat and root-cause analysis. However, the methodology of training within FFSs is demand-based and these principles should be upheld. Feedback on the activities and conducted trials are regularly reported to the AEZ Unit at CETAC.

Regarding Outputs 2.1 and 2.2 target three specific municipalities: _Londuimbali, Bailundo and Chongoroi_ The training program foreseen by Output 2.3 will primarily benefit professionals that are involved with the targeted communities in these municipalities, so that the three outputs reinforce each other synergistically and maximize respective outcomes. However, as a resource-efficient strategy to scale up the reach of the project’s capacitation strategy, other municipalities in the Provinces of Huambo and Benguela will be invited to voluntarily designate up to 5 professionals per municipality to participate in all or some modules of the training program of Output 2.3, thus paving the way for future replication of the approach.

Gender Mainstreaming: At least 20% of the beneficiaries of the training program will be women. The curriculum and pedagogical methods of the training program will be take into account the specificities of the roles of women within communities. Refer to section 3.6 for additional considerations and indicator setting with respect to gender mainstreaming and safeguards.

/ See Appendix I) Logical Framework Matrix for the indicators and targets for Component 2. /

/ Refer to Appendix III for or full list of activities under Component 2. /

### Component 3) Economic and financial leverage approaches to SLM

#### Outcome under Component 3

Outcome 3.0) Increased availability of funding for, and investments in, land restoration / rehabilitation in Angola

The project’s third component will focus on increasing the amount for resources invested in SLM through the identification of relevant sources and the development of suitable options for SLM finance and on improving national capacity for mobilizing, investing and managing funds for SLM. This will include financial leverage and scale-up of actions needed for restoring/rehabilitating degraded land through evidence from economic analyses on the cost of land degradation and the potential benefits from its restoration in the Provinces of Huambo and Benguela.

Evidence of the costs of land degradation will be produced and disseminated among key decision makers to increase the amounts allocated by the state budget and by private investment in SLM. Adequate management of those resources are a key factor to guarantee their expansion and sustainability. With the efficiency of such management in mind, the project will operationalize both mainstream and innovative finance options for SLM in the targeted municipalities, in parallel to a capacity-building program for mobilizing financial resources, fundraising campaigns and support to the formulation of SLM projects. In practice all these will boost community-based SLM finance, public-private partnerships and targeted matching grants designed and established to channel funds from various funding sources.

As the practical element of this strategy, local businesses related with SLM are funded and promoted through the selected financial mechanisms. In the context of this component, the project will attempt to develop relevant partnerships and ensure the ‘trickle-down’ of resources for SLM and land restoration.

The project will conduct this in targeted communities but aiming to convince others to follow the experiment, complementing the efforts towards Land Degradation Neutrality (LDN) developed under the other components. The component’s outcome will be the increased availability of funding for, and investments in, land restoration/rehabilitation in Angola. Component 3 will be directly coordinated by GABAC through the governance mechanisms that have been put in place for the Angolan Fund for Climate Change and the National Environmental Fund. The outputs produced in this component will have a local focus but its impact will be of national scale, considering the capacities created in the MINAMB the GABAC at national level. Consultants supported this component will be based in Luanda.

#### Outputs of Component 3

Output 3.1	Economic analyses on the cost of land degradation in Huambo and Benguela Provinces are carried out and disseminated among key decision makers to bring financial leverage and scale to the actions needed for restoring/rehabilitating land in central Angola

Having a clear assessment of the costs of land degradation and effectively communicating it to key decision makers – including the Angolan government, international donors and investors, is the selected strategy to mobilize the necessary financial leverage to the GEF intervention and its replication and scale-up of actions needed to protect and restore land. This assessment will be the starting point for lobbying and advocacy to be carried on by GABAC and relevant civil society organizations to attract more public and private resources for SLM and for stronger mechanisms for monitoring the use of already available resources.

After the initial assessment, it will be necessary to continue monitoring the evolution of the costs of land degradation and of the economic benefits generated by landscape restoration processes put in motion by this project.

A national expert in agro-economy will conduct the initial assessment, as described in the ToR, teaming-up with adequate local economists working for GABAC. The aim is to produce the report and, at the same time, contribute to the development of in-house capacity to undertake such assessments.

The same national expert will train a set of professionals from MINAMB, MINAGRIF, MINTURI and relevant NGOs on lobbying and advocacy for fundraising. This training will result in (1) setting up a task force for lobbying & advocacy and (2) developing a strategy based on evidence for the task force’s activities in advocating for sustainable development policies, mobilizing resources for SLM and monitoring costs of land degradation / benefits of land restoration.

Output 3.2	Mainstream and innovative finance options for SLM are assessed, explored/probed and enabling action is undertaken to operationalize them in the targeted municipalities with fundraising campaigns are organized, and projects are formulated to mobilize funds

Enabling action for operationalizing both mainstream and innovative finance options for SLM in the targeted municipalities will start by a systematic survey of specific sources for Angola and of strategies to access their potential. This initial survey will inform the actions for the different stakeholders to be able to tap into those sources: (1) a capacity-building program for fundraising focused (but not only) in MINAMB’s staff at national level, (2) fundraising campaigns and (3) capacity-building and technical assistance on project formulation.

The capacity building on fundraising both at national and international level, should be coordinated with the capacity building for lobbying & advocacy. The latter has a broader scope and will work on other aspects on top of the funding.

In a learning-by-doing approach, the program will include an exploration of financing modalities and instruments. Examples of instruments that may be considered and assessed include international founds and financial mechanisms, national lines of credit to different types of subsidies, de-risk instruments and, where feasible, impact investments. Today, a large body of guidance on SLM finance is already available thanks to the work of the UNCCD Secretariat.

Once it is determined what sources of finance for LDN can be leveraged specifically for Angola, the next step is the design of finance options and mechanisms serving local communities and entrepreneurs in their endeavors to implement SLM techniques and approaches. A clear link to Angola’s NDC under the UNFCCC’s Paris Agreement will also be sought to the extent that common goals and actions can be identified, and their pursuit optimized. The design of these mechanisms will pay attention to the need of their own financial sustainability.

The training on fundraising and the fundraising campaigns will be led by GABAC with technical assistance from the hired consultants. The design of specific mechanisms will be done in consultation with relevant academic and financial institutions already involved in agricultural credit to farmers’ associations and micro and small entrepreneurs. This will allow these institutions to take ownership and continue using the financial mechanisms that prove more effective.

Local expertise will be used to train and provide technical assistance to parties interested in designing and submitting project proposals to potential donors and in developing other mechanisms for resource mobilization. The training on project design should also target extension workers that could replicate the approaches with mature farmers’ associations and smallholders.

Output 3.3	Community-based SLM finance, public-private partnerships and targeted matching grants are designed and implemented to channel funds from various funding sources

As a local ramification of the mechanisms of Output 3.2, community-based SLM finance, public-private partnerships and targeted matching grants are designed and established to channel funds from various funding sources. Special attention will be paid to community rotating funds created and/or supported by projects such as SADCP (MOSAP II) and organizations like ADRA, World Vision and others. The rotating funds will be reinforced with resources that will be made available for associates investing in SLM and related technologies (such as bio-humus, fuel pellets and beekeeping among others).

Under this output, selected communities will be supported in designing and submitting project proposals to the SADCP (MOSAP II) small projects fund. Those communities will also be supported in channeling the return generated by those projects into investments in SLM or NRM.

This output will be generated in partnership with EDAs and NGOs that have developed successful rotating funds and micro-credit schemes.

A fiduciary fund will be created specifically to support community-based SLM finance and micro and small entrepreneurs interested in SLM. Resources mobilized from public and private sources (Outputs 3.1 and 3.2) will constitute the basis of this fund, for which no GEF finance is expected. The fiduciary fund will be developed through a transparent public process that will engage independent and highly qualified professionals based on criteria to be defined during project implementation.

As the practical element of this strategy, local businesses that have the potential to contribute to SLM through the adaptation of current practices are promoted through the adopted financial mechanisms. Examples of existing sectors and activities with such potential include commercial agriculture, forest plantations, seedling nurseries, beekeeping, quarries, construction, the harvest and commercialization of wild fruit, fish arming, tourism, and the production of bio-humus, charcoal, improved stoves, fuel pellets. In the context of these economic activities, Component 3 will develop relevant partnerships and ensure the integration of SLM compatible practices and the ‘trickle-down’ of resources for SLM and land restoration (in particular to communities), complementing the efforts towards Land Degradation Neutrality (LDN) developed under the other components. In practice, the output will attempt to use the community-based financial mechanisms to empower small entrepreneurs who wish to invest in businesses that promote SLM. In order to promote gender equality and the empowerment of women, 30% of the micro entrepreneurs financed through these mechanisms should consist of women.

This activity will be implemented through the support of the fiduciary fund referred to above. Mature experiences will be supported to engage banks, for credit to expand their operation. As in Output 3.3, such financial mechanisms will encourage the partial reinvestment of returns in SLM or NRM.

/ See Appendix I) Logical Framework Matrix for the indicators and targets for Component 2. /

/ Refer to Appendix III for or full list of activities under Component 2. /

### Component 4) Knowledge management, monitoring and evaluation

The objective of Component 4 is to ensure a systematic results-based monitoring and evaluation of project progress. Thus, achieving project outputs and outcome targets that are established in the Project Results Framework, as well as promoting the wider dissemination of project information, data and lessons learned for replication in degraded areas.

MINAMB has dedicated field staff that will support the project implementation, in particular, Components 2 and 3. The FAO will execute the project budget and provide technical backstopping to the overall project cycle. The M&E system will be designed by the short-term M&E specialist. (For further details see sections 2.3, 2.4 and 2.5.)

#### Outcome under Component 4

Outcome 4.0) Project Implementation based on results-based management and application of project lessons learned in future operations facilitated

#### Outputs of Component 4 (M&E)

Output 4.1	A project monitoring system is in place to providing six-monthly reports on progress in achieving project output and outcome targets

In PY1, the Project Chief Technical Advisor will be responsible for preparing a Project Progress Report (six-monthly) in close cooperation with the PSC. The PPR includes the project results framework with project output and outcome indicators, baseline and six-monthly target indicators, the monitoring of the risk matrix, and will identify potential risks and mitigation measures to reduce those unexpected risks. At the end of PY1, the Chief Technical Advisor supported by the National Project Coordinator will, in close coordination with the PSC, provide appropriate input to the Lead Technical Officer (LTO). The Chief Technical Advisor will also be responsible for preparing the yearly Project Implementation Report (PIR). The PIR includes the project results framework with project output and outcome indicators, baseline and yearly target indicators, the monitoring of the risk matrix, and will identify potential risks and mitigation measures to reduce those unexpected risks. The process in PY2, PY3 and PY4 will be the same as in PY1.

Output 4.2	Midterm review and final evaluation conducted

After 18 months of project implementation, a mid-term project review will be conducted by an external consultant hired by FAO, who will work in consultation with the project team including the FAO- GEF Coordination Unit, the LTO, and other partners. At the end of project implementation, a final project evaluation will be conducted by an international external consultant under the supervision of the FAO Independent Evaluation Office, in consultation with the project team including the FAO-GEF Coordination Unit, the LTO, and other partners.

Output 4.3	Project-related “best-practices” and “lessons-learned” disseminated

In PY4, a report will be produced and published on the project’s best practices and lessons learned. All elements of the report will be made available online, and key conclusions will be translated and circulated among local partners, government staff and other relevant stakeholders that were involved in the project’s implementation. This report will be discussed and enriched through the closure workshop, which also explore follow-up initiatives and the project’s sustainability strategy.

Additionally, the project’s midterm review and final evaluation will include a capacity needs assessment focusing on CETAC and other national entities involved in delivering on its technical outputs.

### 1.3.3 Project Assumptions

During PPG phase, the following assumptions have been identified. These assumptions are crucial for the right development of project’s output and outcomes. In general terms, the project has been built based in the following assumptions:

- It is assumed that the project will enjoy high level of political support from key stakeholders across the board and that national and provincial government authorities are fully committed the development of SLM

- The appointment of international/ regional consultants/contractors is not unduly delayed.

- Allocated co-financing and project funding is available in time to allow the expected rolling out of activities according to the present work plan.

Table 9. Project assumptions per Component

| Component | Assumptions |
| --- | --- |
| 1 | - All institutional holders of relevant GIS and agroecological data are expected to be willing to share their databases and GIS material. - The protocols and methods for data-sharing, as well as the organic plans for developing an AEZ Unit within CETAC, will ensure the best results possible in view of building national capacity for AEZ analysis and the pursuit of LDN goals. - People trained will stay in positions where they will use their new skills. - The Angolan government will pay salaries and operation costs of CETAC, the host of the AEZ Unit. - A two-way hub will be is set up, either involving the AEC in Chipipa, supported by the ICE-SLM Project, or another suitable mechanism, so as to allow the necessary conditions for (i) collecting AEZ data and (ii) generating AEZ products through WebGIS DSS platform. [*] |
| 2 | - Communities served by AP/FFS will be willing to participate in the GreeNTD methodology and participatory planning. - it is assumed that communal and municipal administrators will be receptive to the project and willing to deploy the necessary technicians to accompany planning activities and participate in the associated validation steps. - It is assumed that once approved, there will be social acceptance and ownership of SLM plans. - It is assumed by the project’s long-term strategy that interest in the AP/FFS will grow or at least not decline. - Project ICE-SLM will deliver the necessary conditions for the AEC in Chipipa to allow foreseen activities that count on the center’s expected operational status. [*] |
| 3 | - International funding and financial resources to be mobilized will remain available. - Awareness of the costs of land degradation will motivate relevant stakeholders to invest in SLM. |
| 4 | - Allocated co-financing for M&E activities is available on time. |
| [*] Note: Refer to paragraph 197. Should this proposed articulation with project ICE-SLM prove impossible due to delays or project cancellation, alternative solutions will need to be devised prior to project implementation. |  |

### 1.3.4 The global Environmental Benefits

The project’s Global Environmental Objective is to stabilize land use and reverse negative land degradation trends in selected municipalities of Central Angola by integrating science-based agroecological data as a powerful support tool – and mechanism – for participatory SLM planning and implementation at scale across varied landscapes, through the capacitation of local stakeholders.

Using the Landscape Approach, the project will deliver GEBs by turning science-based agroecological data into a powerful support tool, as well as a mechanism, for planning and implementing SLM at scale across varied landscapes. This will imply establishing a dedicated Agroecological Zoning (AEZ) Unit within the Centre of Tropical Ecology and Climate Change (CETAC), located in Huambo. Spatial planning will play a key role in the process, as AEZ products will serve to inform optimal land-use allocation and provide the basis for social agreements at the local level for SLM, which will be translated into SLM plans that are to be integrated in the national spatial planning system.

In terms of SLM frameworks, the design of the project strategy prioritized a nested, multi-scale and participatory approach to spatial planning and to the integration of SLM into prevalent agricultural practices. Through this approach, the project will contribute to stabilizing land use and reversing negative land degradation trends within selected landscapes, directly and indirectly:

- within the 6.1 million-ha Wider Landscape of Huambo and Benguela, and

- within 409,699 ha of multi-use demo-landscapes in the municipalities of Londuimbali, Bailundo and Chongoroi – including at least five ‘production systems’ – (i) agriculture; (ii) rangeland; (iii) pastoral; (iv) forestry; and (v) mixed systems – allowing the project to demonstrate its approach on the ground both within a predominantly agricultural zone and predominant pastoral / rangeland area.

Given the project’s limited scope and duration, halting and reversing land degradation means by and large maintaining the current status quo in terms of above Tons CO2 e/ Ha of above ground biomass (60.7) and soil Carbon (72.6) -- targets summarized for the three demo landscapes. As the AEZ system develops, other parameters can come into play and a more precise measure of land degradation will be refined.

Global environmental benefits to be generated by the project include the improvement of the national knowledge base on land degradation and SLM – where the AEZ system will be a crucial vehicle. As recommended by the GEF’s Scientific and Technical Advisory Panel (STAP), the project will lay the ground for Angola to eventually apply LDN Indicators for assessing land rehabilitation measures on the ground and at scale, given the advantages of the fine-scale tools to be developed through the AEZ system. Project efforts in this respect may also contribute towards expanding the global knowledge on the application AEZ tools and on the monitoring of LDN indicators, generating useful data for global and regional analyses.

In terms of ‘scale considerations in the landscape approach’, the project will combine ground-level data collection and participatory land-use management with remotely sensed data. Globally, there are very few tangible examples of such approach as applied to SLM – i.e. nested, multi-scale, multi-stakeholder and participatory in view of the integration of SLM into land-use management. Table 10.  further down includes the project’s high-level indicators contribution to the GEF’s corporate indicators. These indicators were duly incorporate into the Project’s Logical Framework (See Appendix I for the results from the application of the LD Tracking Tool, which served the purpose of defining these indicators).

Competing land use across broad landscapes has become a norm in post-conflict Angola. With the project, it is expected that decisions based on analysis provided by the AEZ system will have a positive impact on land use allocation and management throughout the country, meaning that, with information and knowledge, the stakes for ecosystem services and biophysical resources such as biodiversity, soil, water and carbon, will be more seriously taken into account. This will be an indirect benefit. Within the Wider Landscape, it will demonstrate results in terms of strengthening cross-sector integration of SLM.

The project is also expected to lead to refinements in the AP/FFS approach in relation to SLM and also to improvements in FAO’s participatory methodology of negotiated territorial planning (GreeNTD) by using AEZ and SLM recommendations for supporting collective negotiation, both of which may be replicable at the global scale. Together they represent three SLM mechanisms that the project will introduce and develop under Components 1 and 2, in addition to the finance mechanism to be developed under Component 3.

The above described global SLM benefits refer primarily to the project’s contribution to its GEF Programmatic fit under LD3 - Program 4 [Integrated Landscapes / Scaling-up Sustainable Land Management through Landscape Approach], and whose general goal is to ‘reduce pressures on natural resources by managing competing land uses in broader landscapes’.

Through it’s the application of INRM practices in the ‘Wider Landscape, the project will generate a range of global benefits in targeted landscapes of Central Angola and throughout the country. The mentioned region is rich in rangelands, miombo forests and harbors rare afro-montane ecosystems. The stream of ecosystem services that the region’s landscapes render is extremely valuable and have global importance. They refer to the project’s contribution to its GEF Programmatic fit under LD3 - Program 4 [Integrated Landscapes / Scaling-up Sustainable Land Management through Landscape Approach]. They can be thus stated:

Activities on the ground in productive landscapes, totaling at least 57,055 ha in the commune of Alto Hama and 84,112 ha in the commune of Bailundo will be focus on demonstrating the practical approaches in the Central Plateau region of Angola, in Huambo Province, in addition to 268,5322 ha of rangelands in Chongoroi, Benguela Province. Although of limited scale, global benefits will be generated, to the extent that the three demo landscapes become fully functional and data on them has been fully surveyed. This implies, among other criteria that LDN indicators are also regularly monitored, and data is validated through ground-truthing, using CETAC’s capabilities in land-based surveys. This includes for e.g. collecting data on soil carbon and type of vegetation cover in critical sites. All of this will contribute to SLM cross-sectoral integration through a series of activities being implemented on the ground, as foreseen in Component 2.

A more specific target for agroecological intensification within the above-mentioned landscapes should be able to reach, as an estimate, a total of 11,000 to 14,000 ha (in total and rounded down, in 11,000 to 14,000 ha of agricultural landscapes. This figure corresponds to approximately 10% of agricultural lands in the Alto Hama and Bailundo demo landscapes, plus 10% of identified rangelands within the Chongoroi demo site (as per Table 10). The location and exact hectarage of demo sites where the envisaged intensification is expected to take place still needs to be confirmed during the project’s inception. This target for agroecological intensification refers to the GEF’ Programmatic fit under LD1 - Program 1 [Agro-ecosystems / Agro-ecological intensification], and whose general goal is to ‘maintain or improve flow of agro-ecosystem services to sustain food production and livelihoods’.

Table 10. GEF Outcome Monitoring & Indicators

| At CEO Endorsement Request stage, i.e. by 2018/2019 – [TT Part III] | Baseline | Mid-Term | End of Project |
| --- | --- | --- | --- |
| LD3 – SLM in Wider Landscapes (integrated management) - PROGRAM 4 |  |  |  |
| i. Support mechanisms for SLM in Wider Landscapes established – measured as the number and type of demonstration results strengthening cross-sector integration of SLM | 0 demonstrations / No decision support system (DSS) support mechanisms for SLM in place, but at GEF CEO Endorsement stage, ‘The Wider Landscape’ has been proposed as the project’s broad target, designed to cover approx. 6.1 million hectares in Huambo and Benguela, and it contains 3 demo landscapes | 1 demonstration / The AEZ support mechanism for integrating SLM across the Wider Landscape, which covers 6.1 million ha, is being established through the project, with the AEZ system fully functional, yielding knowledge products for the integration of SLM practices across the landscape, including in the demo landscapes being established. | Various demonstration results / The AEZ support mechanism is fully consolidated and includes 3 demo landscapes, with 10 SLM plans delivered, and the continued integration of SML across the Wider Landscapes, with 6.1 million ha, as well as in the 3 demo landscapes, through FFSs/APFs, as well as through targeted capacity building of extension services. |
| ii. Integrated landscape management practices adopted by local communities – assessed as the application of INRM practices in the Wider Landscape (hectares) | 0 ha | Approx. 400,000 ha of demo landscapes, where improved practices are in the process of being applied | Approx. 400,000 ha of demo landscapes, where improved practices apply |
| iii. Increased investments in integrated landscape management - measured through progressive increases in resources flowing to INRM and other land uses from diverse sources; units in USD Millions - estimated | $4.8 million, (2016/2017 GoA expenditure with SLM – to be confirmed/updated at inception) [Refer to note linked to item #1 in Table 5 for an explanation on this baseline.] | In average, $5.0 million per year from various sources, or at least a 5% increase vis a vis a baseline, in case the baseline is updated. | In average, $5.3 million per year, or at least a 10% increase vis a vis a baseline, in case the baseline is updated. |
| LD1 – Ecosystem services in production landscapes (agriculture, rangeland) - PROGRAM 1 & PROGRAM 2 |  |  |  |
| ii. Functionality and cover of agro-ecosystems maintained – measured as the land area under effective management in production systems with improved vegetative cover | 0 ha | Estimated projections for micro landscapes: - 6,881 ha of agricultural lands - 7,800 ha of rangelands Total: up to 14,670 ha Considered as 11,000 ha as the mid-term target. [the exact location and surfaces area of demo sites will be confirmed during project inception] | Up to 14,700 ha (in total and rounded down). |

The targets in terms of functionality and cover of agro-ecosystems will be achieved by supporting at least 1,500 farmers in the project area to develop their capacities in SLM and in the rehabilitation of degraded land areas. The capacitation of existing AP/FFSs and communities for SLM will ensure the sustainability of the generated GEBs in the long run. The GEBs will be measured by applying the GEF LD PMAT (See Annex B for the LD Tracking Tool).

### 1.3.5 The Socio-economic Benefits

The project will contribute towards the development of sustainable and rational approaches to spatial planning and decision-making regarding land-use allocation and management in selected landscapes of Central Angola.

It will combine these efforts with the integration of science-based agroecological approaches as through the capacitation of local stakeholders. In the development phase of CETAC’s spatial planning capabilities, (establishing a dedicated to Agroecological Zoning (AEZ) unit within the Center), the focus will be on two provinces: Huambo and Benguela. Component 2 and, in part, Component 3 will be exclusively implemented in these provinces.

The project will contribute to building capacity, structures and resources at national level regarding the AEZ, environmental monitoring and using products related to these for decision- making support. More specifically, the reduction of pressures on natural resources from competing land uses, by addressing on the one hand the needs for analysis and measurements across the Wider Landscape in Central Angola, and on the other, by working locally and on the ground with land users, practitioners, and local decision makers.

The project will achieve its global objective of contributing to stabilizing land use and reverse negative land degradation trends in selected municipalities of Central Angola by integrating science-based agroecological data as a support tool for participatory SLM planning and implementation through the capacitation of local stakeholders.

- At least 100 beneficiaries of the following affiliation will benefit from a SLM training program:  civil servants, AP/FFS master trainers, and EDA / IDA technicians, of which at least 20% women.

- At least 10 SLM plans will be prepared, involving 450 people, 40% of which women in approximately 14 communities.

It is also foreseen that the project, by contributing to the productivity and sustainability of agricultural practices, has the potential for indirectly contributing to long-lasting improvement of livelihoods and food security, particularly in direct beneficiary communities of the demo landscapes.

## 1.4) STAKEHOLDER CONSULTATION AND ENGAGEMENT

### 1.4.1 Project Stakeholders

Table 11 further down presents the categories of stakeholders engaged and consulted during the process of project preparation. This set of stakeholders also corresponds to those who are expected to be particularly relevant to the project’s implementation. Refer to the description of the Institutional Framework under section 1.1.1 for more details on the mandates of governmental entities.

Table 11. Project stakeholders and their role in project implementation

| Stakeholder | Relevant Role |
| --- | --- |
| Central Government |  |
| Ministry of Environment (MINAMB) | MINAMB has the overall responsibility for the coordination of land management and environmental policies. The Ministry will make sure that relevant policies, institutional and legislative frameworks, and other important elements are ready to support the implementation of project activities. It will equally support the process of Agroecological Zoning (AEZ) and related activities in the project. Under MINAMB Office for Biodiversity and Climate Change (GABAC): As the focal government body for the project within MINAMB, the Office for Biodiversity and Climate Change will be the institution responsible for leading the national project coordination and monitoring and evaluation. The office will also coordinate unit responsible for AEZ and will promote synergy between any existing or foreseen project working with similar topics. Provincial Directorates for the Environment in Huambo and Benguela have been established. They will be the key liaison entity of the provincial governments in accompanying the project. (see further below the role of the provincial government). The Center for Tropical Ecology and Climate Change (CETAC) The CENTER will be a central element for the project implementation arrangement at the landscape level and the main focus for capacity building. It will work as a facilitator for the coordination of local partnerships, e.g. with universities, and will host the unit responsible for AEZ, functioning as a ‘hub’ for the national AEZ system. The institution will also be part of efforts of monitoring and evaluation of the project. Centro Agroecológico da Chipipa (AEC) The Chipipa Agroecological Center can function as a hub for FFS and APFS, playing a role in testing techniques and training FFS master-trainers. Training is already on-going supported by SADCP and other projects. Currently, the mandate and attributions of the AECs are under review by government. If there will be important changes that have a bearing on the feasibility of certain activities project team will adapt. |
| Ministry of Agriculture and Forestry (MINAGRIF) | MINAGRIF has the responsibility over the agriculture and forestry sectors. It also has a mandate over a number of rural development issues. Along with MINAMB, MINAGRIF will be engaged in the execution of the project, and the organization of the project’s activities. Under MINAGRIF Agrarian Development Institute (IDA) & the Agro-Development (Field) Station (EDA) IDA and EDAs will work on building capacity, facilitating and integrating AEZ in the local level, involving FFS and APFS. They will be able to promote and monitor SLM in the local level, as well as to collect data and contribute to monitor and evaluation. Provincial Directorates for Agriculture and Forestry in Huambo and Benguela have had a presence for a few years and work closely with Provincial Directorate for the Environment. The will be closely articulated with the provincial IDA regarding the involvement of the municipal EDA’s in the project’s implementation. Food Security Office (GSA) is a technical support entity within MINAGRI in defining and following-up on the implementation of policies and strategies that allow the improvement of food security. GSA is responsible for the collection of meteorological data to operate the agrometeorological crop monitoring and crop yield forecast system for food security. Jointly with IGCA and INAMET, the GSA should participate by sharing its geographic data with the AEZ in the effort of consolidating a centralized database of AEZ relevant data. |
| Ministry for Urban Affairs and Housing (MINOTH) and Ministry of Territorial Administration (MAT) | At a central and local level, in particular MINOTH’s National Institute for Territorial Planning and Urban Development (INOTU) will help with the engagement of different levels of government in land use planning -- central government, provincial and municipal governments. They have an important role to play in decentralizing the spatial and landscape level planning. They also play important roles in statutory commissions that are relevant for the endorsement of plans produced under the legal umbrella of the 2004 LOTU and its 2006 regulations. Also under MINOTH, the Angolan Institute for Geodesy and Cartography (IGCA) is responsible for the ongoing national land cadaster initiative. Jointly with GSA and INAMET, IGCA should participate by sharing its geographic data with the AEZ in the effort of consolidating a centralized database of AEZ relevant data. To a lesser extent, and more in an accompanying role, the MAT will also need to be involved. |
| Ministry of Telecommunications and Information Technologies (MTTI) | The National Institute of Meteorology and Geophysics (INAMET) is the national institution in charge of monitoring the weather and climate. It is also a research organization which provides scientific services in the fields of meteorology and geophysics under the Ministry of Telecommunications and Information Technologies (MTTI). INAMET ensures the functioning of the network of Automatic Weather Stations (AWS) and conventional observations of atmospheric parameters, carrying data storage, processing and dissemination. INAMET is represented across the country through its provincial departments. Jointly with GSA and IGCA, INAMET will be engaged by a partnership to encourage the sharing of geographic data with the AEZ Unit, in a joint effort of consolidating a centralized database of AEZ-relevant data. |
| Provincial and Local Government |  |
| Provincial governments of Huambo and Benguela and Provinces | Mostly through the interfaces of the provincial directorates of MINAMB and MINAGRIF, provincial governments will be engaged in the planning and implementation of the project and support its activities in the demo landscapes. They will support the project in all its phases and will ensure linkage with local development strategies. They are a key beneficiary of project’s capacity building interventions. |
| Municipal Governments | Together with provincial governments, the municipal governments will be working on the project’s execution and provide support throughout the entire time of its implementation and planning. The three target municipalities are: Londuimbali and Bailundo in Huambo, and Chongorói in Benguela. The respective municipal administrations are also a key project beneficiary. |
| Local stakeholders |  |
| Family farmers | These groups will be the direct beneficiary of the project on the ground. The current count of family farmers assisted through AP/FFSs will likely be 1,500, of which 52% are women. |
| Farmers associations organized in AP/FFSs | One of the most important targets of this project for its potential to transform farming systems and recover or degrade land. This category is also the one that suffers more directly the impact of land degradation and the benefits of its recovery. |
| Traditional authorities | They will be supporting the project’s implementation in a role as mediators, enabling communication between local groups engaged in the project. They will also monitor the project’s activities. |
| Funders and NGOs |  |
| Donor agencies and private companies | Wherever relevant the project will to collaborate with possible donors and private sector. Co-financing with multilateral partners is being leveraged and more details will be provided in due course. |
| NGOs and CBOs | The project has been developed with the participation of NGOs, in particular those that are currently helping build the capacity of local land users and managers in from agricultural sector. The scope of their work includes Benguela and Huambo provinces. During project preparation and implementation, the project will develop the collaboration with a wider network of NGOs working in the region. |
| Other relevant stakeholders |  |
| Academic and research institutes | Where applicable, project’s activities will be developed in cooperation with local research institutions. Academic and research institutes that manifested an interest in the project include the Instituto de Investigação Agronómica (IIA) and the Faculdade de Ciências Agrárias (FCA), both located in Huambo city, as well as the Methodist University in Angola and Universidade Lusíada de Angola (ULA), both located in Luanda. |
| Entrepreneurs in relevant domains | Entrepreneurs providing services or products that can contribute to SLM and to the diversification of rural economy have an interest in the sustainability of the resources base of rural areas and could contribute to SLM through their businesses |

### 1.4.2 Stakeholder Engagement Process and Mechanism

#### Stakeholder engagement during the PPG

The success of any project highly depends on the level of stakeholder engagement, which is a continuous process that needs to start during project design and continue through project implementation, building a strong relationship that can help support the project. The stakeholder engagement process and mechanisms used by the team, both during PPG process and during project implementation, comprised a range of activities including consultations, interviews and information disclosure.

/ Refer also to Appendix II, sub-section 1 for the Stakeholder Engagement Matrix. /

### 1.4.3 Stakeholder Engagement

#### Stakeholder engagement during the PPG

During the project preparation process, the PPG team conducted several meetings and consultations with key stakeholders in order to collect and analyze their inputs and views about the local context. An Inception Workshop was also organized during the PPG team’s first field trip to Angola in June 2017. With the presence of 40 participants from different national and international institutions, the PPG team and other participants involved in the project preparation presented its objectives, components and had an open discussion to collect feedback and contributions from the audience, which were thoroughly analyzed and incorporated in the present document.

Following this first step, a series of face-to-face meetings and consultations with both key institutional stakeholders and local communities were organized and conducted by the team during the PPG process, with the aim of collecting first-hand information and data. Based on the categories listed on Table 11, individuals were identified, their contacts obtained, and interviews scheduled. Checklists and questionnaires were prepared to conduct the semi-structured interviews and focus groups. Focus group interviews were the preferred technique for community consultations but were also used with some key stakeholders such as CETAC, FCA and the Provincial Directorate for Environment, in Huambo. Semi-structured interviews and focus-group consultations were complemented with field visits and documentation gathering and analysis.

The PPG team was also responsible for conducting a capacity needs assessment with the main local and national institutions that will be involved in the project implementation. The goal was to evaluate if their infrastructures, resources and tools are suitable to fulfill the needs for the project implementation and what are the gaps that will need to be addressed. The results of this assessment were duly considered during the project preparation. Table 12 presents the main findings of the capacity needs assessment. Table 13 summarizes the affiliation of consulted stakeholders.

Table 12. Organization and Enabling Environment Capacity Needs Assessment

| Level | Strength | Gaps |
| --- | --- | --- |
| Policies on AEZ, SLM and fundraising for both | At the national level - There are key normative documents (land law, spatial planning, environment management, national development strategy, etc) and public structures with the mandate to enforce / implement those policies. - There are no specific policies on funding SLM, but IDA starts adopting an approach of encouraging community revolving funds. | At the national level - Some of the normative documents do not seem to be used systematically in the daily decision making. - Many public structures suffer with a lack of resources to fulfil their mandates - There is a lack of coordination between different actors. - Some documents are not approved. The changes in Angola leadership could result in many changes in some of the policy documents. |
|  | At the municipal level - The process of decentralization is going to give more autonomy to the local level to develop and implement policies, including for environment. - Basic spatial planning exercises have been tried, but with limited ownership and more oriented to urban land. | At the municipal level - Municipal structures suffer with lack resources, including human resources - Communes (the level bellow municipality) are even weaker than municipalities - Municipal level is often not consulted in policy development processes. |
| Actors in AEZ, SLM and funding of both | At the national level - AEZ: FCA is setting up a GIS unit and has been involved in basic land-use surveys and forestry management work; IIA is strengthening its soil labs; Food Security Office is revitalizing its network of weather stations and remote sensing info unit. - SLM: IDA, through SADCP is in promoting sustainable agriculture; IIA, with the support of SADCP has the mandate to develop technologic packages that could include SLM approach. - Funding: some farmers’ associations have been scarce. The financing system in Angola is not geared towards small farmers. | At the national level - There is very poor coordination between actors even at the level of information sharing. |
|  | At the municipal level - Some EDAs include in their extension work techniques of soil conservation and low input agriculture - NGOs such as ADRA, Development Workshop and World Vision promote land tenure projects and appropriate technology projects | At the municipal level - The actors mentioned see environmental matters as secondary. - There are no champions on environmental matters. - Interventions are not coordinated and are not part of a global planed approach |
| Resources & capacity for AEZ, SLM and funding of both | At the national level - CETAC, a national organization with its headquarters in Huambo has valuable facilities that can be an invaluable resource to host the project (training rooms, computers, a 32’’ plotter, etc.). | At the national level - CETAC has almost no experienced human resources and no strategic plan. Except for the Director there are no qualified staff with stable contracts. |
|  | At the municipal level - FAO team and the EDA’s extension workers teams have a strong program that includes experimenting and teaching new technologies at ECAs [FFS]. - There is an Agroecological Centre (in Chipipa) with good infrastructure (training facilities, electric power generated by solar panels, tanks for fish farming, etc.). | At the municipal level - No specific SLM orientation adopted (although there is openness for it). - The Agroecological Centre has a very low level of activity and is making very limited use of its resources. Lack of qualified manpower is probably the main problem. |
| Existing information on AEZ, SLM and funding of both | At the National level - There is relevant information produced in Huambo on land use and status of the environment. | At the National level - Existing information is not easily available and is not being used in decision making. |
|  | At the Municipal level - PDM include generic characterizations on land use and other potentially relevant information. Participatory Rural Appraisals (PRA) reports were done for some communities. | At the Municipal level - Existing PDM are very superficial in what relates to rural areas. |

/ Refer to Appendix II (Stakeholder Engagement Matrix) for more details. /

Table 13. Brief analysis of stakeholder profile and stats, plus gender notes

| Profile Legend | Stakeholder Profile Stats (FAO categories as of Appendix II) | # of individual stakeholders | Of whom, women (~26%) |
| --- | --- | --- | --- |
| a | Academia | 9 | 3 |
| b | Local community | 33 | 8 |
| c | Local Government Institution/body | 6 | 3 |
| d | National Government Institution body | 39 | 7 |
| e | Non-Governmental Organization | 3 | 1 |
| f | Other / Private sector | 6 | 2 |
| g | Resource Partner/Donor | 19 | 6 |
|  | Total | 115 | 30 |
| Brief analytical notes with gender on focus: - The above points out to a tendency towards gender gaps being ‘ironed-out’ in various relevant stakeholder segments. - These include in particular, local government, academia, private sector and ‘resource partner/donor’, where women are 32 to 50% of the stakeholder count shown above. - In turn, women are under-represented in two crucial segments for the project, namely ‘National Government Institution body’ and ‘Local community’ (constituting 24% and 18% of stakeholder count respectively). - In spite of the concerted efforts towards explicitly engaging them. Incidentally, these two latter segments are the core the beneficiary groups. - Therefore, much more is needed during implementation in terms of gender parity when it comes to stakeholder engagement during implementation. Refer to subsection Gender Action Plan in section 3.6. |  |  |  |

##### Community-level Consultations

Two meetings were held in both Alto-Hama and Chongoroi, which congregated members of various AP/FFSs, who represented their communities in the consultations. A total of 12 FFSs of Alto-Hama were consulted through 23 FFS members, including 6 women, and a total of 2 APFSs in Chongoroi through 6 APFS members, of whom 2 were women. Table 14 provides an overview of the profile of consulted communities in Huambo and Benguela.

Table 14. Overview of numbers for the communities consulted during PPG (Aug/Sep 2018)

| Consulted communities | Count of active AP/FFSs | Number of members from AP/FFSs | => Of which women | % of female membership | # of leaders and members consulted during PPG // of which women |
| --- | --- | --- | --- | --- | --- |
| In Londuimbali (municipality in Huambo) | 12 | 405 | 209 | 52% | 23 // 6 women |
| Alto Hama (Legacy ECAs [FFS] MOSAP I) | 7 | 240 | 121 |  | 14 // 5 women |
| Alto Hama (new FFS / ECAs [FFS] novas do IDA) | 5 | 165 | 88 |  | 9 // 1 woman |
| In Chongoroi (municipality in Benguela) | 1 | 79 | 33 | 42% | 5 // 2 women |
| Bolongueira (RETESA legacy) | 1 | 44 | 11 | 25% | 1 // 0 women |
| Chongoroi (RETESA legacy) | 1 | 35 | 22 | 63% | 4 // 2 women |
| Total in consulted communities | 14 | 484 | 242 | 50% |  |

Focus groups were the preferred method for community consultations, similar to the institutional CNA consultations. The stakeholder involvement process was done in a participatory and gender-sensitive way, because separate focus groups were created for women and men. This offered women the possibility of reflecting about issues raised by themselves and of answering the posed questions on their own without being under the influence of men.

Taking into account the aspects raised in the two meetings in both Alto-Hama and Chongoroi, the main trends of gender roles and responsibilities are the following:

- Men are usually more involved in identifying and selecting land to be prepared for cultivation;

- Women usually have a greater participation in agricultural activities from the preparation of land to harvesting, including commercialization;

- Men sometimes decide together with the women about sale prices, but women are generally much more involved in the commercialization than men;

- In the focus groups, women were more receptive and sensitive to the importance of environment-friendly methods (regarding for example the selection of trees to be pruned, slash-and-burn practices, use of composting and green manure), while men seem to be more likely to be interested in practices leading to more immediate results despite their unsustainability;

- Women also showed more interest in issues related to management (perhaps because a large part of them were elected to manage AP/FFSs due to being considered more responsible) and work methodology, while men were more interested in the increase of production.

According to the conducted consultations, the context of the FFSs in Huambo is characterized by their emergence within already existing farmers’ associations and cooperatives. This process has led to the existence of conflicts over the forms of organization, leadership and management, which are different between those of associations/cooperatives and FFS methodology. In the recent past, the process of creation / development of associations/cooperatives was characterized by lack of transparency and internal democratic processes. They often functioned as a collective enterprise in which some did the actual work while others managed profits. The more horizontal and inclusive model of collective organization of FFSs (based on the sharing of experiences and knowledge) came to clash with engrained habits of more authoritarian and centralized distribution of power and responsibilities. Such tensions should be taken into account during the project’s implementation while engaging communities and local partners.

At the time of the consultations, most of these AP/FFSs had not yet undergone a process of evaluation of their development. Most of them are technically still in the 1st Cycle but the EDA technicians who support these AP/FFSs expressed the view that of these could pass to the 2nd Cycle and some to the 3rd Cycle, especially those of Alto-Hama.

In terms of institutional environment, SADCP with the technical support of IDA/EDAs and FAO is currently the only support for monitoring and strengthening FFSs in Huambo, while the APFSs in Chongorói are currently only assisted by the local EDA.

In general, from these consultations it can be concluded that local farmers expressed interest in obtaining more knowledge about the use of fertilizers, new crop varieties, irrigation and pesticides. Considering that some of these techniques have potential negative environmental impacts, there is a clear opportunity for training in SLM. Women also expressed a specific interest in improving their commercialization skills and their access to markets. There is also a need for methods of soil protection against erosion, a serious problem in all of the Central Angola, especially in the highlands.

##### Stakeholder engagement during project implementation

The stakeholder engagement during project implementation will follow the same principles and approaches implemented during the PPG process. The consultation can be seen as a way of initiating and sustaining constructive relationships over time, extending throughout project implementation in order to guarantee stakeholders’ participation and satisfaction with the project outcomes.

During project implementation, at least three main stakeholder engagement events should be organized. First, the Inception Workshop, to define and validate the project implementation strategy and confirm the role of each stakeholder. Ideally, it should happen within 3 months after first disbursement and invite the main stakeholders mentioned in Table 12 further up. Second, a mid-term workshop should be organized as to assess the performance and identify weaknesses to be strengthened and improved during the second half of project implementation. And finally, the Final Workshop will be an opportunity to evaluate the project implementation and its outcomes, as well as to assess the lessons learned and consolidate inputs for the project’s final report, including the consideration of the project’s sustainability strategy and follow-up initiatives.

Besides these main events, throughout the project’s implementation, the team should ensure a clear and continuous communication channel with the main stakeholders in order to inform about the evolving implementation and achievements of the project.

Considerations on gender and ethnicity ought to be fully taken into consideration in the process of engaging stakeholder during project implementation. The respective sections on these topics include various elements of guidance, with contextual information and tools, which serve for project managers to ensure that stakeholder engagement process will comply with FAO’s and GEF standards during project implementation. They are e.g. the following:

- Both a project-level Gender Screening (Table 22) and a Gender Action Plan are included further down in section 3.6. Various considerations with respect to components, outputs, activities and indicators are mentioned in that section and will be fully taken into consideration in the process of engaging both men and women in project activities.

- In section 3.7 (on Indigenous Peoples) important considerations were made on ‘ethnicity’ and land-use traditions in the context of decision-making and management. E.g. in the central and southwestern part of Angola, ‘ethnic identity’ is a key determinant of whether a group is a hunter-gatherer, a pastoralist, an agropastoralist or a farmer – nomadic, semi-nomadic or not. In other words, geophysical conditions do play a strong role in influencing land use, but ethnicity cannot be ignored. Hence, ethnicity should then be much more carefully considered in stakeholder interactions and engagement, irrespective of whether any given ethnic groups identify themselves as ‘indigenous people’.

### 1.4.4 Grievance Mechanism

FAO is committed to ensuring that its programs are implemented in accordance with the Organization’s environmental and social obligations. In order to better achieve these goals, and to ensure that beneficiaries of FAO programs have access to an effective and timely mechanism to address their concerns about non-compliance with these obligations, the Organization, in order to supplement measures for receiving, reviewing and acting as appropriate on these concerns at the program management level, will entrust an Office with the mandate to independently review the complaints that cannot be resolved at that level.

FAO will facilitate the resolution of concerns of beneficiaries of FAO programs regarding alleged or potential violations of FAO’s social and environmental commitments. For this purpose, concerns may be communicated in accordance with the eligibility criteria of the Guidelines for Compliance Reviews Following Complaints Related to the Organization’s Environmental and Social Standards, which applies to all FAO programs and projects.

Concerns must be addressed at the closest appropriate level, i.e. at the project management/technical level, and if necessary, at the Regional Office level. If a concern or grievance cannot be resolved through consultations and measures at the project management level, a complaint requesting a Compliance Review may be filed with the Office of the Inspector-General (OIG) in accordance with the Guidelines. Program and project managers will have the responsibility to address concerns brought to the attention of the focal point.

The principles to be followed during the complaint resolution process include: impartiality, respect for human rights, including those pertaining to indigenous peoples, compliance of national norms, coherence with the norms, equality, transparency, honesty, and mutual respect.

/ Refer to Appendix II (Stakeholder Engagement Matrix), sub-section 2 for the grievance form. /

#### Project-level grievance mechanism

The project will establish a grievance mechanism at field level to file complaints during project inception phase. Contact information and information on the process to file a complaint will be disclosed in all meetings, workshops and other related events throughout the life of the project. In addition, it is expected that all awareness raising material to be distributed will include the necessary information regarding the contacts and the process for filing grievances.

The project will also be responsible for documenting and reporting as part of the safeguards performance monitoring on any grievances received and how they were addressed. The mechanism includes the following stages:

- In the instance in which the claimant has the means to directly file the claim, he/she has the right to do so, presenting it directly to the PCU. The process of filing a complaint will duly consider anonymity as well as any existing traditional or indigenous dispute resolution mechanisms and it will not interfere with the community’s self-governance system.

- The complainant files a complaint through one of the channels of the grievance mechanism. This will be sent to the Project General Coordinator (PGC) to assess whether the complaint is eligible. The confidentiality of the complaint must be preserved during the process.

- Eligible complaints will be addressed by the Project Advisory Committee (PAC). The PGC will be responsible for recording the grievance and how it has been addressed if a resolution was agreed.

- If the situation is too complex, or the complainer does not accept the resolution, the complaint must be sent to a higher level, until a solution or acceptance is reached.

- For every complaint received, a written proof will be sent within ten (10) working days; afterwards, a resolution proposal will be made within thirty (30) working days.

- In compliance with the resolution, the person in charge of dealing with the complaint, may interact with the complainant, or may call for interviews and meetings, to better understand the reasons.

- All complaint received, its response and resolutions, must be duly registered.

##### Internal process

- Project Coordination Unit (PCU). The complaint could come in writing or orally to the PCU directly. At this level, received complaints will be registered, investigated and solved by the PCU.

- If the complaint has not been solved and could not be solve in level 1, then the Project Coordinator  elevates it to the PSC.

- FAO Representative. The assistance of the FAO Representative is requested if a resolution was not agreed in levels 1 and 2.

- FAO Regional Office for Africa. FAO Representative will request if necessary the advice of the Regional Office to resolve a grievance, or will transfer the resolution of the grievance entirely to the regional office, if the problem is highly complex.

- The FAO Regional Representative will request only on very specific situations or complex problems the assistance on the FAO Inspector General who pursuits its own procedures to solve the problem.

##### Resolution

Upon acceptance a solution by the complainer, a document with the agreement should be signed with the agreement.

| Review Level | Contact Details |
| --- | --- |
| Project Coordination Unit (PCU) | Must respond within 5 working days. |
| Project Task Force (PTF) | Anyone in the team may receive a complaint and must provide proof of receipt. If the case is accepted, the Project General Coordinator (PGC) must send the information to all Project Task Force (PTF) members and call for a meeting to find a solution. The response must be sent within 5 working days after the meeting of the Project Task Force. |
| FAO Representation in Country | Must respond within 5 working days in consultation with FAO's Representation. FAO Representative: Ms. Gherda Barreto Cajine. Phone: +244 222 325757 |
| FAO Regional Office for Africa | Must respond within 5 working days in consultation with FAO's Representation. FAO Representative: [as above] |
| Office of the Inspector General (OIG) | To report possible fraud and bad behavior by fax, confidential: (+39) 06 570 55550 By e-mail: Investigations-hotline@fao.org By confidential hotline: (+ 39) 06 570 52333 |

Moreover, to ensure that FAO’s policies and objectives to prevent fraud and misconduct are respected, the team will be informed of the existing grievance mechanism and is required to inform all consultants hired under the project of their duties and rights. In particular, all staff will be invited to consult FAO’s Environmental and Social Management Guidelines (http://www.fao.org/3/a-i4413e.pdf) and Grievance Handling mechanism (http://www.fao.org/aud/en/ and http://www.fao.org/aud/48643/en/), which came into force on 15 March 2015.

In addition, AP/FFSs and other technical methodologies proposed in the project are approaches based on concepts and principles of people-centered learning and were developed as an alternative to the conventional, top-down, extension approaches. The AP/FFS is a participatory common platform that facilitates the resolution of concerns of beneficiaries/stakeholders. Regular AP/FFS sessions allow for regular feedback on major concerns that can be addressed in the most appropriate way by the project.

### 1.4.5 Disclosure

— Non-applicable. —

/ Refer to Appendix II (Stakeholder Engagement Matrix), sub-section 3 for the disclosure form,

if and when applicable. /

### 1.4.6 Partnerships

Fostering existing partnerships between FAO and relevant stakeholders and to setting up partnerships with new stakeholders considered key for the project will be a crucial aspect of the project’s successful implementation. During the local consultations and capacity needs assessment, the PPG team was responsible for evaluating the viability of partnerships, including based on their interest in being actively involved by the project. A list of potential partners is proposed in the section on Implementation Arrangements (2.1), along with  proposed Letters of Agreement (LoAs) to be signed during project implementation. Proposed partnerships are purely indicative and subjected to further appraisal and revisions during the inception phase. All partnerships will be established in accordance with FAO policies on partnerships

## 1.5) ALIGNMENT AND STRATEGIC FIT

The project strategy and proposed outputs are consistent with national development priorities, and have close substantive and institutional links and complementarities with the primary national and international development strategies and plans, including the following listed in the upcoming sections.

### The National Development Plan (PDN) 2018-2022

The National Development Plan (PDN) for the period 2018-2022 is the second medium-term planning exercise carried out under the National Planning System in force, following the PDN for 2013-2017. The PDN is a prospective and multiannual strategic document covering the national, sectoral and provincial levels of planning, and implements the country's long-term strategic development options, as set out in the Long-term Strategy (ELP) Angola 2025. Finalized in April 2018, its preparation was quite innovative, being carried out in close coordination with the sectorial and provincial planning bodies, seeking to maximize their ownership of the national development process. The sectorial approach aimed at identifying programs that would respond to national challenges to the country's development in the different policy areas; to this end, each sector was invited to interact with the provinces and with the relevant private sector and civil society partners in their areas of intervention.

Several of the PDN’s programs are aligned with this project’s objectives. These include programs related to the development of agriculture, environmental protection, spatial planning and poverty alleviation through forestry or rural development. Each program contains specific targets. The most relevant programs and respective objectives and targets for the context of this project are listed in Table 15.

Several other programs have objectives, targets and priority actions that are not necessarily the same as the project’s, but which have many complementary linkages with the project’s expected outcomes, i.e. whose actions and objectives have much to benefit from the project’s contributions. These are mostly related to the potential of the AEZ system to collect and make available data that is of crucial importance for the development of the agricultural sector and the territorial management of land use. This wider group of linkages can also be considered as part of the project’s strategic alignment with the agenda of GoA. They are summarized in a more comprehensive table in section 1.5.

Table 15. Alignment of the Project with the agenda of the National Development Plan (PDN) 2018-2022

| Entity Responsible and Core Public Policy | Selected Priority Actions with strong linkages to this Project * | Relevance to the Project Strategy | Notes |
| --- | --- | --- | --- |
| MINAMB (DNB, INBAC and CETAC), Environmental Sustainability (Policy, XII – Program # 2.4.1: Climate Change) | - Establish a land-use mapping mechanism to allow monitoring of land-use including, for environmental management purposes, identification of land degradation and desertification zones; - Map areas of land degradation; - Formulate and implement strategies for control of desertification at the local level and guidelines for designing and reviewing policies and measures to support the sustainable development of areas susceptible or affected by drought or desertification; and - Implementing long-term integrated measures and strategies in the affected areas, based on increased land productivity, rehabilitation, conservation and sustainable management of land resources, including the establishment of tree nurseries (fodder and fruit trees) for land rehabilitation purposes. | The primary link is to Output 1.4, referring to core products that AEZ Unit will be capable of preparing, in particular the fine-scale WebGIS decision support system (DSS) for SLM, LD and ecosystem services monitoring. Other Outputs under Component 1 are also closely linked it, in particular to the extent that Output 1.1 through 1.3 are pre-conditions for Output 1.4. In terms of operationalization, the core linkage is with Component 2 Outputs. | [a] |
| Ministry of Construction and Public Works (MINCOP), Environmental Sustainability Policy, XII – Program # 2.4.4: Risk Prevention and Environmental Protection. | - Studies of identification and characterization of ravines of priority intervention (linked to Target 1.1: Up to 2022, 250 hectares (ha) of slip risk area are stabilized. | Same as above, relating to Output 1.4 and other related Outputs under Component 1 | [b] |
| MINAGRIF, Promotion of Production, Import Substitution and Export Diversification (Policy, XI – various programs) | - Provide technical support to farmers through EDA's and ECA's [i.e. FFS/APFS] (the latter do not necessarily require the construction of root infrastructures) so as to enable them to properly integrate the use of inputs, increase productivity and, consequently, the income of the households; and - Mapping and registering family and business farms and creating a bank of arable land available for investment, creating conditions for the improvement of land management; - Conduct studies on the phenomena of desertification and reforestation - Train technicians to prepare provincial food balance sheets; - Inventory of automatic agro-meteorological stations in the country; - Collect and process agro-meteorological information from the main areas of agricultural and livestock production | Same as above for Component 1 Outputs. Plus, other outputs under Components 2 and 3: - Output 2.1 (on community-level SLM plans & GreeNTD application) - Output 2.1 and 2.3 (on the project’s support to mainstreaming SLM in AP/FFSs and related frameworks) - Output 3.3 (on community-based SLM finance, public-private partnerships) | [c] |
| MINOTH, Spatial Planning and Urban Planning (Policy, XXII – Program # 5.2.1: Improvement of the National Geodetic and Cartographic System) | - Train and train technicians in the sector Other priority actions related to the objective of providing the country with updated reference mapping at 1: 100,000 scale and, by derivation, reference letters at 1: 250,000, 1: 500,000 and 1: 1,000,000 scales, and to demarcate political and administrative boundaries from the country. | Same as above, relating to Output 1.4 and other related Outputs under Component 1 | [d] |

| # | Table Notes |
| --- | --- |
| [*] | For linkages to the Baseline Finance concerning the PND Programs, see in addition: Table 5. Governmental investment baseline from the National Development Plan (PDN) 2018-2022 |
| [a] | This mechanism will make it possible to identify measures to address land degradation factors, including measurable, verifiable and time-bound targets, based on the UNCCD and SDG indicators related to Target 15.3. This exercise will be triggered, phased, nationally in provincial increments. A specific Target (#3.4: Mapping of Zones with Land Degradation in all provinces by 2022) is actually linked to it. |
| [b] | As much as 11,029 million Kwanzas (equivalent to $36.8 M) were allotted in 2019 to MINCOP’s Program in the medium-term. Relevant targets include: Target 1.1: Up to 2022, 250 hectares (ha) of slip risk area are stabilized; and Target 2: Up to 2022, 17 ha of ravine areas are recovered. Core objectives under the Program 2.4.4 are: (1) To reduce the risk of catastrophe due to landslides and sea-gulling by promoting measures to stabilize slopes, coastal protection and recovery of ravines; (2) To reduce the risk of flood and flood catastrophe by ensuring the implementation of de-erosion works, regularization of flow and protection of riverbank. |
| [c] | There are many possible linkages, but the core Programs include activities that should also support the monitoring of agricultural campaigns by providing information on the agricultural calendar, on agro-meteorological forecasting and possible effects on crop, pasture and animal development, seed period and status, availability and use of inputs (seeds, fertilizers, pesticides), presence of pests and diseases, crop condition and evaluation of crop yields. This is where the project can make a more significant contribution. Programs worth highlighting in this respect include the following with broad objectives that are well aligned with the Project: 2.3.2: Promoting Agricultural Production 2.3.4: Promoting the Sustainable Use and Management of Forest Resources 2.3.5: Improving Food and Nutrition Security |
| [d] | Related but more peripheric actions include: - Acquire ortho-rectified satellite images to update the cartographic information; - Acquire geodetic precision equipment; - Train and train technicians in the sector; - Elaborate technical and legal standards to ensure the process of demarcation of boundaries; - Perform field work; - Develop the cartography; - Construct / rehabilitate and equip reference stations of the National Geodetic Network. |

### Agricultural Sector Mid-Term Plan (PMPSA) 2018-2022

The agenda of the PMPSA has been integrated in the PDN, but it is worth highlighting that its final conclusions contain clear recommendations for creating enabling conditions for more agricultural data: “The elaboration of any study such as the one we are discussing here will always involve a phase of data collection that contributes to the rigor of the analysis. Indeed, it is imperative to pay particular attention to the creation of conditions at the central (capital) and local level (areas of agrarian activity) for the rigorous production of data, which, after treatment, would become important agricultural statistical information. This information would serve as a reliable basis for drawing up coherent plans, projects and work programs, ie to quantify and qualify the necessary investments for the Sector as well as to plan imports so as to reduce waste. Finally, special attention should be given to the strategy of retaining cadres and other qualified technicians of the Sector in the areas of agricultural production.” Whereas the first point refers to some of the potential contributions of the AEZ system for environmental monitoring, the latter point can be linked to capacity-building for SLM in agricultural areas.

### Land Degradation Neutrality Target Setting Program (LDN-TSP)

In the context of the on-going LDN-TSP, and with the general LDN goal of “achieving neutral land degradation by 2030 compared to degradation levels for 2015”, the GoA adopted in November 2018 the following specific LDN targets for avoiding, minimizing and reversing soil degradation. Specific strategies for achieving these targets have also been formally adopted (see subsection Supportive Approaches and Tools, item d, under Section 1.3.1 for a description of the LDN-TSP). The need for support to effectively implement and monitor LDN technical measures and targets – and thereby implement the overall strategy adopted at national level for LDN – has been asserted. The role for this project in creating enabling conditions for the success of the LDN strategy within the broader LDN process is described in the Strategy section (see e.g. the sub-section on ‘Technical Integration with relevant projects’).

The LDN-TSP has so far been exclusively reliant on default data that are still too broadly scaled for an accurate assessment of land degradation and appropriate responses through SLM. The AEZ products of Component 1 will be tailored to data needs of the assessments of the LDN-TSP, thus giving special emphasis to the adequate development and monitoring of LDN indicators, providing the reference basis to guide the implement of the strategies adopted for achieving the LDN targets. Thus, this project will provide a major contribution in supporting the implementation of the LDN-TSP. In addition, the project will train national partners on land degradation assessment tools (e.g. Open Foris, Collect Earth) increasing the country’s capacity for implementing the LDN process.

### National Action Program to Combat Desertification (PANCOD)

The PANCOD is as much a ‘national program’ as it is a convention compliance mechanism for Angola. It is, in addition, an instrument for implementing national policies and actions aimed at controlling and combatting land degradation and desertification, as well as for the achievement of a social pact on the importance of SLM. PANCOD has its bases on the premises of a sustainable development aimed at the Economic and Social Development Programs elaborated and implemented annually or bi-annually by the government. The actions envisaged in the program to combat desertification are national multi-sectoral, which will be implemented in accordance with the overall and specific objectives of all actors and at different scales (local, municipal, provincial, regional and national). This project will be instrumental in helping the GoA implement the PANCOD.

### Angola’s Spatial Planning System

The project is also well aligned with the implementation of the “Spatial Planning Law” or LOTU (3/04). According to this framework law, municipalities have the duty to develop municipal planning instruments which include Municipal Master Plans (PDMs), Environmental Land-Use Plans (POAs) and Rural Land-Use Plans (POR). The latter in particular are of great potential for structuring an organized system of SLM but it is still underdeveloped. This project could provide an essential support for creating the mechanisms and enabling environment for the development of the PORs (see section 1.1.1).

The project is also consistent with the National Communication to the United Nations Framework Convention, the National Action Plan for Adaptation (NAPA), the National Strategy and Action Plan on Biodiversity (NBSAP) and with the main national public policies for development and fight against poverty, many of which contain specific guidelines on the environmental sustainability of the agricultural and livestock sectors and on reducing vulnerability. The project also directly contributes to specific priorities and results set out in the Partnership Framework between the Government of Angola and the United Nations System (UNPAF 2015-2019) and in the FAO Country Program Framework (CPF) for 2018-2023.

Because of the important potential of SLM for Climate Change Mitigation (mostly by contributing to keep and increase soil carbon levels) and Adaptation (by preserving or increasing ecosystem resilience to climate change), this project is also well aligned with the objectives and strategies in these domains, including the:

- Intended Nationally Determined Contribution (INDC), released by Angola in 2015 for the COP-21, which prioritizes the implementation of adaptation measures in the agricultural sector, as well as for the forest, biodiversity and national resources sectors.

- The Angolan National Adaptation Plan (NAP), launched in July 2015. The NAP process is supported by the GEF-founded NAP Global Support Program (NAP-GSP) and seeks to facilitate effective medium and long-term climate change adaptation planning as well as budgeting planning through institutional support, technical support and knowledge brokering. The proposed project can be seen as a way to provide a way forward on the NAP process by developing strong partnerships at national and local levels and contribute to the integration of CCA sustainable Natural Resources Management and SLM.

### Alignment with FAO’s Strategic Objectives and Programs

This project will be contributing to FAO’s Strategic Objective 2: Make agriculture, forestry and fisheries more productive and sustainable, Organizational Outcome 2.1: Countries adopted practices to increase productivity sustainably while addressing climate change and environmental degradation in agriculture, forestry and fisheries. The linkages are as below (same information as on the cover page):

FAO’s Strategic Objective/Organizational Outcomes [Linkages] Objective #2: Make agriculture, forestry and fisheries more productive and sustainable. Organizational Outcome 2.1: Countries adopted practices to increase productivity sustainably while addressing climate change and environmental degradation in agriculture, forestry and fisheries. Country Outcome(s) UNDAF: Strategic Area of Intervention 3: Sustainable and Inclusive Economic Development. Outcome 3.1: Inclusive Growth, Economic Diversification, Production and Job Creation Outcome 3.2: Environmental Sustainability, Climatic Change and reduction of Risks Disasters. Country Programming Framework(s) Output(s): Priority area 1, Strengthening smallholder farming productivity and competitiveness to reduce Food Insecurity. - Outcome 1.1: Improving Government extension services capacities to promote smallholder farming - Output 1.1.1 Technical assistance improved through a better and reinforced rural extension program. - Output 1.1.2 National and local institutions and authorities are sensitized to the impact and relevancy of promoting smallholder farming Priority area 2, Sustainable Management of Natural Resources for mitigation and adaptation of climate change impacts. - Outcome 2.1.: Promote and develop sustainable land management. - Output 2.1.1 Promoted and adapted tools for land and natural resources management in Angola. Priority area 3, Institutional Capacity Building. - Outcome 3.2: Strengthen the capacity of data collection and statistical services. - Output 3.2.1 Supported the elaboration of a Forestry Inventory in Angola. Regional Initiative/Priority Area: Integrated Management of Agricultural Landscapes in Africa / Generating and sharing knowledge and Capacity Building.

Additionally, this project is framed in the Regional Initiative: Integrated Management of Agricultural Landscapes in Africa and Priority area: Generating and sharing knowledge and Capacity Building.

Because of the important potential of SLM for Climate Change Mitigation (mostly by contributing to keep and increase soil carbon levels) and Adaptation (by preserving or increasing ecosystem resilience to climate change), this project is also well aligned with the objectives and strategies in these domains, including the:

- Intended Nationally Determined Contribution (INDC), released by Angola in 2015 for the COP-21, which prioritizes the implementation of adaptation measures in the agricultural sector, as well as for the forest, biodiversity and national resources sectors.

- The Angolan National Adaptation Plan (NAP), launched in July 2015. The NAP process is supported by the GEF-founded NAP Global Support Program (NAP-GSP) and seeks to facilitate effective medium and long-term climate change adaptation planning as well as budgeting planning through institutional support, technical support and knowledge brokering. The proposed project can be seen as a way to provide a way forward on the NAP process by developing strong partnerships at national and local levels and contribute to the integration of CCA sustainable Natural Resources Management and SLM.

### Alignment with relevant GEF-6 Focal Area Strategies

Vis-à-vis the GEF’s Land Degradation Focal Area Strategy for GEF-6, this project aims to enhance the sustainability of land management in Angola in two different fronts.

The Landscape Approach as a core objective and approach (LD-3) is prioritized in terms of scaling-up sustainable land management through the landscape approach. The choice of LD-3 is also highly appropriate for the project, given its Component 1 and 2 activities. This is particularly the case of activities foreseen under Component 1, which are directly linked to the development of national capacity for AEZ. Products from the AEZ will be useful for an informed and rational decision-making process, both nationally, but also on the ground, which will be done through Component 2. The focus on agroecological intensification (LD-1) as a focal area objective under Component 2 has a limited scale regarding landscapes’ surface and number of beneficiaries in terms of the direct implementation of the activities foreseen for the three demo landscapes. This limitation may, in principle, be overcome through methodical technical integration with other projects employing the AP/FFS approach (e.g. IRECEIA, ICE-SLM, ARP) who should lend added scale to the approach of this project’s Component 2. As for Component 3, it contributes to both LD1 focal area objectives more generally. Adequate focal area indicators are currently presented in the LD TT (Annex B).

- / Regarding LD1 and LD3 targets, refer also to: Table 10. GEF Outcome Monitoring & Indicators. /

## 1.6) COMPARATIVE ADVANTAGES

The Food and Agriculture Organization (FAO) is the lead United Nations (UN) agency for agriculture, fisheries, forestry and rural development. Its mandate is to offer member states the technical and policy capability to raise their levels of nutrition, improve agricultural productivity, better the lives of rural populations and contributes to the growth of the world economy while safeguarding natural resources.

The proposed project is aligned with the FAO’s comparative advantage in the area of capacity building, providing technical analysis and assessments in relevant areas such as Sustainable Land Management, Climate Change Adaptation, Agroecology, sustainable crop and animal production, land/range management, policy support, and agrobiodiversity conservation. FAO has considerable technical experience and many field projects in a number of areas covered under this project (LD, agriculture production and food security, CC, agrobiodiversity, capacity building, development of community-based capabilities and rural development, forage production and grassland management). FAO has a comparative advantage on the AP/FFS approaches which have been endorsed by various governments in the region. The AP/FFS will be used for some of the capacity building activities under Component 2, thus strengthening the environmental comprehensiveness of the approach,

FAO has been supporting Angola’s efforts both to develop a National Food and Nutritional Security Strategy and to improve livestock management and land planning. FAO’s Department of Agriculture and Consumer Protection has recently completed a global review of 20 years of FFS experience (available at https://dgroups.org/fao/ffs-eforum2) FAO currently has a significant project portfolio in Angola with a major focus on SLM and CCA including important projects with an agroecological approach being financed by GEF and other donors. These include projects ICE-SLM, FRESAN, ARP and SADCP. (See sub-section ‘Technical Integration with relevant projects’ under section 1.3.1).

FAO’s comparative advantages are its in house technical expertise in virtually every discipline related to rural development and its capacity to respond to the needs of member countries. These areas include, among others, policies and strategies, crop and livestock development, agriculture and food security information systems, early warning systems, agribusiness and enterprises, sustainable land management and planning, forestry, climate change adaptation and mitigation, and livestock and fisheries systems. The FAO has promoted and facilitated the coordination between different governmental institutions, policy makers and relevant stakeholders, all involved in rural development. This advantage and role enhance even more the comparatives advantages of the FAO in Angola.

Additionally, FAO Headquarters technical unit AGPME, a part of the Agriculture Production and Protection Division (AGP), is the Lead Technical Unit (LTU) for this project, with the support of CBDS (FAO’s Geospatial Unit) for Component 1. AGPME is leading the mainstreaming of Agroecology as an important approach for moving towards more sustainable food systems, whose practices, research and policies have seen exponential growth worldwide, through the organization of high-level agroecology symposiums at international and regional level. Through these symposia, FAO has carved out an effective dialog space for national examples on how agroecology is supporting the achievement of the SDGs in Angola, and how national policies, institutions, programs and legal frameworks are supporting transition to a sustainable food production. The latter are closely linked to GEF’s focus on agroecological intensification (LD-1).

The Food and Agriculture Organization (FAO) is the lead United Nations (UN) agency for agriculture, fisheries, forestry and rural development. Its mandate is to offer member states the technical and policy capability to raise their levels of nutrition, improve agricultural productivity, better the lives of rural populations and contributes to the growth of the world economy while safeguarding natural resources.

## 1.7) KNOWLEDGE MANAGEMENT AND COMMUNICATION

### 1.7.1 Knowledge Sharing

The project takes a pragmatic and equitable approach to knowledge management. All data produced by this project will be made public in user-friendly forms—unless for specific reasons, the data is not suitable for sharing. Reports, along with the GIS products and initial metadata will be available on the website of the AEZ unit.

Within the context of the internal implementation of the project, the main system for knowledge management will be the AEZ (Agroecological Zoning) national data analysis unit. The purpose of the AEZ system is to both collect the data and provide the users with the GIS products. The system will provide access to online mapping features for viewing and querying the available spatial data layers. This application, which detailed features will be specified later, will also allow data and document storage and search. Data access will also be possible by downloading files and/or their associated metadata, the application will also provide a document management system. The system will avail archiving of the downloaded data through user friendly a document management system. The system and its services will be operationalized by the agroecological centers.

The idea of the AEZ system takes into consideration the need for GIS products in sustainable land management activities. Making them available and possible to share by stakeholders will facilitate their cooperation, which is crucial for combating land degradation and maintaining the sustainable land management practices. For this reason, information will be disseminated in a user-friendly form to various levels right down to local users through the WebGIS DSS, which will be operated and maintained by the AEZ Unit. The two-way hub that will be set up for collecting AEZ data and generating AEZ products through WebGIS DSS platform (as described under Output 1.5) will be instrumental in ensuring that there is adequate access to these cloud-based platforms. “Local users” means, in this context, AP/FFS master trainers, EDA technicians and municipal officers. The farmers themselves will have access to these products through the latter in the context of the activities of AP/FFSs.

Therefore, under Component 2, the AP/FFSs will be instrumental in bringing the AEZ products to the local level in the target sites, both in the form of the SLM plans — the drafting of which is based on AEZ products —, and also in the form of direct AEZ products that will be used to aid the implementation of the SLM plans. AP/FFS master trainers, EDA facilitators and municipal officers will also receive training on how to generate specific AEZ products from the WebGIS or Collect Earth Platforms. See also Figure 19 for a depiction of the main information flows under Component 2.

Component 1 also foresees the setting up of an AEZ online platform that intends to provide networking, outreach and information to AEZ professionals across the country. Cost-efficiently, this website could include a webpage with updated information on the planned project interventions, making them accessible to any interested stakeholders.

Outputs under Component 4 also deal with knowledge sharing. The project monitoring system will provide six-monthly reports on progress in achieving project output and outcome targets (Output 4.1). Also on the basis of the midterm review and final evaluation (Output 4.2), Output 4.3 relates to the production and dissemination among key stakeholders of a report on “best-practices” and “lessons-learned” from the project’s implementation. The project’s closure workshop will include a discussion of this report which will have been circulated beforehand.

### 1.7.2 Lessons Learned

#### GEF projects and relevant FAO projects

The experience of past project in related domains hold important lessons for the present GEF LD project. Legacy GEF projects include e.g. RETESA and ELISA. The former is described further down. The latter is a UNDP LD Project that was active in Huambo province but closed in 2015, with full title ‘GEFID 5719 - Promotion of Sustainable Charcoal in Angola through a Value Chain Approach’. During the PPG, the former coordinator for the ELISA Project was interviewed, and lessons were actively learned – the main one pertains to the importance of building national capacity and anchoring projects institutionally to fulfil this goal.

Ongoing relevant or planned projects and programs, including FAO’s and GEF’s interventions include the following:

- SREP - Smallholder Resilience Enhancement Project (IFAD)

- ARP - Agricultural Recovery Program (IFAD)

- SAMAP (IFAD)

- SADCP (MOSAP II) (WB)

- ICE-SLM

- IRCEIA IRCEIA

The first two above are described in section 1.2.2, as they are part of the financial baseline for this project. As SADCP (and MOSAP I) are cited in Table 16. SADCP and the other two projects, which are GEF-funded (projects ICE-SLM and IRCEIA, with GEF IDs 5231 and 5432) are also cited in the mentioned table, but there is more relevant information in section 1.3.1 under ‘Technical Integration with relevant projects’. This is because MOSAP and the latter two projects hold potential for important synergies with the present project with respect to implementation. The same applies to other FAO projects equally cited in section 1.1.3.

Table 16. Relevant past and on-going projects, including GEF funded (synergies, collaboration and lessons)

| Partner / Project name / Status | Project objectives | Project components and potential synergies collaboration and /or Lessons-learning | Total project cost + Info | Duration |
| --- | --- | --- | --- | --- |
| EU – FRESAN – Fortalecimento da Resiliência e da Segurança Alimentar e Nutricional (STATUS: 3. signed) | Fortalecimento da Resiliência e da Segurança Alimentar e Nutricional | Project Components are: 1. Agricultural production; 2. Value chains approach and farmer organizations; 3. Institutional capacity building; 4. Applied research. Active in Huila, Cunene, Namibe. The GoA counterpart is MINAGRIF (GSA); MINAMB (Gab Min); Gprov (VG/DSA). Implementing partner. Portugal (I.Camões), FAO, UNDP. [SYNERGIES] | EUR 65 M, grant | end 2018-2022 |
| WB SADCP – Market-Oriented Smallholder Agriculture Project. (STATUS: 5. On-going) * WB MOSAP I (STATUS Completed) | Increase agricultural production through provision of better services and investment support to rural smallholder farmers. | Titled ‘AO-Market Oriented Smallholder Agriculture Project’ (WB ID: P093699), MOSAP I was active in Malange, Huambo, Bié. GoA partner was MINAGRIF (IDA). Implementing through dedicated unit (PIU). MOSAP I was active from 2008/2009 to 2016. In its aftermath SADCP (Smallholder Agriculture Development and Commercialization Project, WB ID P154447) was developed as a continuation of the investment in the small farmers’ segment in Angola. It has similar objectives. SADCP will see close collaboration with the project with respect to activities under Component 2, as described in the current strategy. | MOSAP I: $ 49.35 M, Loan (total costs, blended finance) SADCP: $ Total Project Cost $95 M, of which $70M is a loan from IBRD | MOSAI I: 2008-2016 SADCP: 2016-2021 |
| IRCEA (FAO GEF) Integrating climate resilience into agricultural and agropastoral production systems through soil fertility management in key productive and vulnerable areas using the Farmer Field School approach (STATUS: 4. Under implementation) * | The objective of the project is to strengthen the climate resilience of the agropastoral production systems in key vulnerable areas in the Provinces of Bié, Huambo, Malange and Huila. This will be achieved through: (i) mainstreaming Climate Change Adaptation (CCA) into agricultural and environmental sector policies, programs and practices; and (ii) capacity building and promotion of CCA through soil fertility and Sustainable Land Management (SLM) practices using the FFS approach. | The project strategy is built on four main components. The first is to strengthen knowledge and understanding of climate change vulnerability and adaptation. The second is scaling up of improved CCA/SLM practices through FFS. The third is mainstreaming CCA into agricultural and environmental sector policies and programs. The last component focuses on monitoring and evaluation. Implementing partner FAO. | $30.3 (GEF = $6.7M grant) | 2016-2021 |
| EU - CDAIS Baby 1 - Angola Capacity Development for Agricultural Innovation Systems (CDAIS). (STATUS: 4. Under implementation) | This project provides resources for the implementation of the FAO component of the Capacity Development (CD) for Agricultural Innovation Systems (AIS) project, which is funded by the European Commission and jointly implemented by Agrinatura and FAO. At the country level, the project aims at defining CD needs and existing provision for strengthening AIS in 8 pilot countries through inclusive country-led multi-stakeholder processes. | On that basis, the project will carry out CD interventions in AIS, which are demand-driven and efficient, integrating the development of individual competencies, organizational capacities and enabling policies around priority themes and value chains. GoA partner MINAGRIF | $0.3M | 2015-2020 |
| AfDB/GEF(LDCF) - Integrating Climate Change into Environment and Sustainable Land Management Practices (ICE- SLM): FAO Technical Assistance to Promote climate adaptation measures into SLM practices in four demonstrations sites (Namibe, Huambo, Kuando Kubango and Cabinda). (STATUS: 3. signed) * | The Project development goal is to strengthen climate change into national development activities and promoting adaptive measures and practices in Angola | FAO is the implementing partner, through MINAMB | $4.4M LDCF (grant) | 2018-2021 |
| GIZ-hosted global Economics of Land Degradation Initiative –ELD (http://www.eld-initiative.org) | ELD an initiative on the economic benefits of land and land based ecosystems. highlighting the value of sustainable land management and provides a global approach for analysis of the economics of land degradation. It aims to make economics of LD an integral part of policy strategies and decision making by increasing the political and public awareness of the costs and benefits of land and land-based ecosystems. | Component/Outcome 3: Potential cooperation for training and support framework for the economic analysis of costs associated to land degradation and for the strategies to increase political and stakeholder awareness of the costs of LD and benefits of SLM. | NA | Ongoing |

* Note Refer also to section 1.3.1 under ‘Technical Integration with relevant projects’ for additional content.

#### RETESA

Titled ‘Integrating Climate Resilience into Agricultural and Agropastoral Production Systems through Soil Fertility Management in Key Productive and Vulnerable Areas Using the Farmers Field School Approach’, the RETESA project aimed at addressing the lack of capacity at national, provincial and local levels to prevent and reverse land degradation through the introduction and adoption of participatory approaches for identifying and rehabilitating degraded areas in a coordinated way by multiple stakeholders. The RETESA project has key aspects in common with the present project. It introduced AP/FFSs and produced local land use plans through the application of the GreeNTD methodology. As requested by FAO, this project’s interventions are designed to integrate lessons resulting from the experience of RETESA. In addition, the field work of Component 2 in Benguela will include the APFSs introduced by RETESA in Chongoroi.

Overall, the achievement of the objectives was satisfactory. However, according to the project’s CTA, RETESA failed to build a solid structure that could have more lasting impact. Important recommendations emerged from its final evaluation. Four of these recommendations are particularly important for this project.

1- Invest in the training / certification of national experts on innovative methodologies: Future GEF / FAO projects should focus on the creation, through targeted training, of national experts within the framework of the methodologies they intend to introduce (e.g. AP/FFSs; GreeNTD, LDN etc.). It is about building capacities in the country, through the training / certification of specialists with international training, able to replicate training after project completion so that subsequent projects using these methodologies do not need to rely on the systematic engagement of international consultants / experts. Whenever feasible, the capacitation strategy of this project aims at the replicability and sustainability of the training using a learning by doing approach at all technical levels.

2 - Conduct realistic institutional capacity assessments during the project design and / or installation phase: Future GEF / FAO projects should be designed on the basis of realistic assessments showing existing capacities at national and of local institutions. This should preferably be done at the design stage of projects. It is essential to know the real capacity of the institutions that are to be involved by the project. This avoids the risk of designing projects based on the assumption that public institutions are able to monitor and implement actions, but then have no means at their disposal. The PPG phase of the present project attempted to produce a thorough capacity needs assessment (CNA) to have an accurate perspective of existing capacities.

3 - Promote partnerships with national universities / research institutes for the production of national and regional knowledge: Future GEF and FAO projects that encompass dimensions of knowledge production and dissemination should foresee effective collaborations / partnerships with national universities and research centers. The capacitation strategy that is to be implemented around the AEZ technical unit at CETAC will target graduates from Angolan universities and research institutes, with whom partnerships will be established. The AEZ online platform will also provide outreach to AEZ professionals across the country.

4 - Include formal national education in capacity building processes: Future GEF / FAO projects should also include formal education (high school and higher education) as beneficiaries of capacity building processes, as a complement with the exclusive training of technicians from public institutions (municipal services, agricultural, veterinary and environmental services). The AEZ online platform that intends to provide outreach and information to AEZ professionals across the country can also have the secondary role of providing practical insight to university students wanting to learn about AEZ and respective products.

#### Energy and livelihoods solutions Angola (Elisa) / UNDP-SLM Capacity Building for Angola

Lessons learned from GEF UNDP Sustainable Land Management Capacity Building for Angola highlight critical land management problems at a smaller scale, such as deforestation for charcoal production, and extensive forest fires. Even though these problems are directly caused by poverty and lack of access to information and innovative technologies, also resulting in a lack of understanding about the negative consequences of these practices. UNDP states that in some instances in Huambo, such as the case of forest fires, degradation is derived from cultural habits, which have to be addressed using adequate strategies.

#### FAO Terra- Strengthening the capacities of local governmental institutions land tenure and administration and NRM in the Huambo and Bié

Funded by AECID, the FAO TERRA Project was implemented between 2013 and 2017). The project’s goals were to promote the information about land rights and to work on a local scale in order to introduce an effective land management system. In the Huambo municipalities of Bailundo and Ecunha, this project will build on the capacity gains of the TERRA Project. This will be particularly the case with municipal servants and technicians who have gained experience with the Participatory Negotiated Territorial Development (PNTD) employed by Terra, and which is the precursor to the GreeNTD methodology. The Terra project contributed to strengthening land tenure capacities by supporting primarily local actors, including indigenous people, and to improve the institutional framework developed for the community delimitation approach: The state recognizes the existence of local rights and confers the land right to the community, resulting in a full title document. This document provides strong proof and protection, it is officially recorded in the cadastral database and on official maps and is far less expensive than a private sector cadastral title (as the state covers the cost) or a concession title. Finally, the project lobbied at national and provincial institutional levels to improve rules and details of the Land Law. Through the project, the Land Law application was reinforced, and implementation mechanisms were put in place.

#### Securing Land Tenure and Natural Resource Management for Improved Food Security in Central Angola (EC, Development Workshop, World Vision)

Implemented between 2014 and 2017, the project’s objective was to empower national, provincial and municipality level government and local non-state actors and communities to facilitate the recognition of tenure rights, with the goal of preventing land tenure-related conflicts and improving the security of land occupation. The project intended to assist the GoA in the creation and implementation of a process for regularizing land claims and establishing more-secure land rights of individual smallholders, untitled communities and peri-urban residents that occupy land without formal title deeds. This process is in line with the frameworks established in the Voluntary Guidelines for Responsible Governance of Tenure (VGGT) and also promotes the application of the Social Tenure Domain Model (STDM). The project covered ten municipalities in the provinces of Huambo (7), Bié (2) and Benguela (1). In the municipalities of Londuimbali, Bailundo and Chongoroi, the proposed negotiated planning is likely to be facilitated by the achievements of this intervention gains in the clarification and definition of land-tenure and the gained experience in NRM.

#### MOSAP I - Market-Oriented Smallholder Agriculture Project (FAO-WB)

MOSAP had the objective of Increasing agricultural production through provision of better services and investment support to rural smallholder farmers. Covered Huambo, Malanje Bié. The MOSAP project mainstreamed the approach of AP/FFS as the main rural development approach in Angola. The main general recommendation of the various internal and external evaluations is the need to continue and strengthen the project activities considering its impact as a first experience of this type in Angola, but also the significant challenge that the approach represents, which requires sustained assistance in order to consolidate and ensure the sustainability of the results achieved during the previous phase. The level of coverage in terms of follow-up in the field was poor and regular training of facilitators is a necessary condition to maintain the dynamism of the learning process and should be undertaken by IDA. For that to occur, IDA capacity needs to be further strengthened improving the number of technicians and their technical and training skills. Exchange visits are fundamental, even though expensive, to progressively create a platform of FFS/APFS in Angola. Also, the evolution of FFS 3rd cycle into cooperatives need to focus on municipal pilot experiences and need to be better promoted by the government.

#### General lessons for the application of the AP/FFS approach

Under this project, and within the framework of the AP/FFSs and traditional fora (the Jangos) communities are expected to continue a dialogue with extensions services, first in elaborating territorial negotiated agreements (through GreeNTD) and secondly in implementing the resulting SLM plans. This dialogue will include the discussion and exchange of new information, questions and ideas for continued improvement of land management -- and more specifically for ensuring sustainability through SLM. The technical capacities and growing experience of FAO in the FFS approach started in Angola in 2005 with FAO’s Special Program for Food Security (SPFS). The experience gained during the SPFS led the FFS approach to be recognized by MINAGRI as a suitable and valid approach to providing extension services in rural areas. The AP/FFS approach has since been scaled up by other projects like World Bank-funded MOSAP I and II, IFAD-funded SAMAP and ARP and the GEF-funded RETESA and IRCEIA. Rather than introducing new AP/FFSs, the present project support existing AP/FFSs in promoting the adoption of SLM. Still, the project may benefit from some of the lessons emanating from projects that used the AP/FFS approach. The main lessons learned and recommendations from these past experiences are listed in the table below.

Table 17. Lessons drawn from the application of the FFS approach in Angola FFS

| Lessons Learned | Recommendations |
| --- | --- |
| Planning is needed to maximize efficiencies and improve effectiveness | Proper planning and detailed monitoring should be used as a management tool |
| Coordination is essential to ensure complementarities and synergy creation between various projects / programs | Conceptual technical approaches should be clearly coordinated between projects / programs (including FAO projects) |
| Conditions might vary, and the project needs to be adapted | Flexibility and complementarity of the whole implementation and monitoring systems is needed especially among farmers and local partners of the project involved within an appropriate institutional set-up, financial management and long-term sustainability of the project. This complementarity should lead to operational partnerships registering in time |
| Bottom-up, community-driven approach is effective in promoting smallholder agricultural development | The impact of the switch from top-down to community-driven development has been very positive, both in terms of communities’ incomes and their capacity to identify and implement development activities. The community-level training and local leadership capacity building activities are key in this process |
| The AP/FFS approach is effective in transferring knowledge on improved agricultural practices and technology to smallholder farmers | AP/FFS as an extension approach is able to train and equip smallholder farmers with the skills and experience needed to engage in commercial agriculture |
| Improving governance and building government capacity accelerates project implementation and increases country ownership of results | Government capacity building has proved to be essential, especially to improve the competence and motivation of government staff involved in the supervision of extension agents and to address structural constraints through enhancing agricultural sector policy dialogue |
| AP/FFS are effective for reaching women | A good proportion of women participate in AP/FFS activities. However, as their impacts on community decisions can remain limited, an extra attention is needed to further involve women, especially in community leadership |

#### Spatial planning and other zoning initiatives

As laid out in more detail in the section 1.2.3 regarding the project’s barriers, there have been a few isolated initiatives for mapping land use and agroecological data, with some of these related to the preparation of Municipal Master Plans (PDMs). As of 2013, at least 53 PDMs had been prepared or were under preparation throughout the country. The provinces that are most advanced in this process are Benguela (all 10 of its municipalities had or were preparing a PDM), Huambo (with 7 out of 11 municipalities) and Bié (with 9 out of 16 municipalities). However, PDMs have failed to guide decision-making with spatial implications in a consistent and coherent manner.  In addition, because national spatial planning has given priority to urban areas and regarded rural areas as secondary, PDMs have generally only included detailed planning for the urban areas of municipalities. This would not have been problematic if the PDMs had been complemented by Environmental Spatial Plans (POAs) and Rural Land-Use Plans (PORs) as foreseen by the country’s planning system, but such plans have failed to materialize in Angola in any systematic form. Besides not dealing with actual rural land-use management, the few initiatives that have taken place in this context do not seem to have been integrated with one another.

Lack of national capacity has also led to the systematic hiring of consulting firms to produce such plans, which leads to often unintegrated piecemeal products, often leaving no capacity such initiative on the part of the Angolan administrations to use such products in their environmental governance. Once delivering their reports or plans, which did not seriously involve local actors in their preparation, the contracted firms usually leave the scene with having created the local capacity necessary for effectively using such tools in land-use management. This creates an unfortunate situation where the different initiatives leave behind products that are not only poorly (if at all) integrated with each other but which fail to deliver practical contributions to how land use is actually managed at the different administrative tiers, thus heavily limiting the development gains of not only those initiatives directly related to rural land-use planning and management, but also of those related to agriculture in general. This indicates a clear need for more integrated planning initiatives that involve local stakeholders more actively and closely in order to build national capacity more effectively.

In this project’s intervention areas, there have been relevant planning and zoning initiatives. At the municipal level, PDMs in all of the targeted municipalities (Londuimbali, Bailundo and Chongoroi) have been prepared by mostly foreign consultancy firms.

In the case of the Huambo Province, the following initiatives of provincial-level plans and agroecological assessments are worth mentioning:

##### Provincial plans and zoning

Agroecological baseline assessment for the Provincial Government. In 2003, the provincial government of Huambo appointed a team of consultants (Angola Alliance) to facilitate the establishment and coordination of a multi-disciplinary team to provide it with recent data and information on which future more detailed sectoral studies will be based. Under this proposal the provincial government requested baseline data on the natural resources of Huambo Province and an appraisal to determine optimal areas for the Development of Irrigation Schemes as well as areas that could be earmarked for Conservation/Wildlife establishment. The determining factors for the selection of baseline studies for Huambo was the government’s resolve to develop three specific sectors: Agriculture, Conservation & Tourism and Forestry. To this end, a project team consisting of subject specialists under the guidance of a GIS and Remote Sensing Specialist was compiled to execute a first phase of the study. Additionally, the report also presented an illustration of cropping models for the Province, under dry-land conditions.

The study (completed in 2004) included the production of cartography with: 1. Spatial map of Huambo; 2. Land-cover map of Huambo; 3. Vegetation/habitat types of Huambo. These baseline studies were meant to be a major contribution to the preparation of the Provincial Master Plan (PPOT) but so far this is yet to materialize. As part of the “Transumancia Project” (2002), the same consultancy firm had undertaken in 2002 similar baseline studies in the provinces of Huila, Namibe and Cunene.

##### Strategic Environmental Plan (PEA) for the Province of Huambo (2013)

The Strategic Environmental Plan (PEA) for the Province of Huambo aimed to be a tool for planning and development of reference in the environmental sector for the Province, allowing guide and prioritize strategic actions to ensure sustainable development in the present and in the future. This is only possible by ensuring a balance between the components, economic, social and environmental, so that, in the preparation of the PEA Huambo sought to define strategies that would allow the province to achieve a satisfactory level of social and economic development while ensuring proper use of natural resources and preserving the species and natural habitats. Between August 2012 and April 2013, the preparation of the Plan was based on the information available and collected in the study area and was based on the work of a large multidisciplinary team assembled for the producing the PEA.

##### Provincial Agro-Zoning in Huambo

There was recently an ad-hoc inter-institutional commission created by the provincial governor that included representatives of IGCA, IDA, the Directorate of Agriculture and the Department of Urban Planning. The military and police provided the helicopters for the aerial survey. The initiative managed to map a rough zoning of what is registered in the cadaster and of what is arable or not. The available resources did not allow doing more (i.e. collection of more data and cross-data analysis) and the project had to be suspended. The second phase of this initiative foresees direct cooperation with MINAMB. In this context, FCA is cooperating with Wageningen University on GIS & remote sensing (which includes the development of an operational GIS room) and with Cordoba University on sustainable charcoal production. About 18 staff members are in the 2nd stage of a training program by a network of lusophone universities that selected agroecology and food security as a focus for cooperation. The expected zoning for the Central Plateau should distinguish between areas suitable for agroecology, livestock and monocultural agribusiness. As the initiative is still occurring, it is also considered as part of the technical baselines. But the problems it encountered so far that led to its halt are useful lessons to approach in a more structured, better-funded and integrated manner.

### 1.7.3 Communication

Communication is essential for project effectiveness and sustainability. With respect to communication the project will consider communication at various levels: communication with and between MINAMB, MINAGRIF and MINOTH, and with the local governments, local stakeholders and the Angolan society in general.

Regarding communication with the MINAMB, this will be achieved by regular meetings between the project staff and FAO-MINAMB (GABAC) focal point, as part of the regular activities of the project.

To ensure communication with the local governments, representatives of the local government will be invited to the missions to the field. Besides, regular meetings will be held between the project staff and the local governments.

The project team will directly work with the Communication and Documentation Centre of the MINAMB in order to produce accurate communication products and also to facilitate the flow of information within MINAMB and from MINAMB to other institutions and public in general. This joint work between the Project and the Communication and Documentation Centre of the MINAMB will also provide new capacities to the MINAMB.

Communication with the local stakeholders will be continuous throughout the project duration. Preparatory meetings will be held in all the landing sites supported by the project before the start of any field activities, where the community will be informed of the project and suggestions will be requested. All missions to the field will be required to hold an information meeting with the community representatives.

Giving high visibility to the project and ensuring effective communications in support of the project's ownership will be addressed through a number of activities that have been incorporated into the project design. In particular, under Component 4, the CTA, NPC and M&E will develop a visibility strategy according to the GEF, government and FAO requirements.

Beside elaboration on an integrated curriculum of AP/FFS, a training manual for master trainers on AEZ-based SLM will be elaborated for the use of technicians through synergy with projects FRESAN, ICE-SLM, IRCEIA and SADCP.

Main progresses and achievements of the project will be made known to MINAMB on a regular basis, and will be regularly reported in the FAO-Angola webpage (http://onuangola.org/agencias/fao/) and other FAO’s internet platforms. The project will also prepare brochures, video clips and other communication materials to share project results with the wider community.

Results from the project will be disseminated within and beyond the project intervention zone through existing information sharing strategies (see also section 1.7.1 on ‘Knowledge Sharing’).

The project will identify and participate in, as relevant and appropriate, scientific, policy-based and/or any other networks, which may be of benefit to project implementation though lessons learned. The project will identify, analyze, and share lessons learned that might be beneficial in the design and implementation of similar future projects.

Finally, there will be a two-way flow of information between this project and other projects of a similar scope/focus.

# SECTION 2 – FEASIBILITY

## 2.1) IMPLEMENTATION ARRANGEMENTS

### 2.1.1 Institutional Framework and Coordination

#### a) Institutional framework

The Ministry of Environment (MINAMB) coordinates and develops environmental policies and education, and states rules and procedures to apply legal instruments. MINAMB, through its Office for Climate Change (GABAC), will lead the project from the side of the GoA. The Food and Agriculture Organization of the United Nations (FAO) will be the GEF Agency responsible for supervision and provision of technical guidance during project implementation. This mandate has been formally provided to FAO, as re-confirmed in a OFP letter addressed to the agency and dated 25 September 2019. The project staff will be hosted at the Centre of Tropical Ecology and Climate Change (CETAC), with some of the members of the team having a regular presence in GABAC (Luanda) and the Agroecological Center (AEC) of Chipipa.

The Ministry of Agriculture and Forests (MINAGRIF) is mainly responsible for developing and regulating activities in the agricultural sector, including crops, livestock, forestry and irrigation. MINAGRIF’s primary roles are to formulate appropriate agricultural policies, planning and monitoring, and evaluation within the overall national development framework. MINAGRIF has a very elaborate structure and includes support, technical and consultative services. The following specialized services are important players in the project area: (a) Institute for Agronomic Research (IIA), (b) Institute of Veterinary Research (IIV), (c) Institute of Agricultural Development (IDA), (d) Institute of Forestry Development (IDF), and (e) Veterinary Services (SV).

The Institute for Agricultural Development (IDA), in charge of extension services, mainly to support small farmers, is also represented at the provincial level Provincial Departments under the Provincial Directorate) and local teams at municipal and communal level named Stations of Agrarian Development (EDAs) and Centers for Agrarian Development (CDAs). The EDAs are the units of the front-line extension work involved in the day-to-day field activities with farmers and are present in Londuimbali, Bailundo and Chongoroi.

Specialized government agencies — GSA under MINAGRIF, INAMET and IGCA under MINOTH — will be involved in an information sharing protocol with the AEZ unit regarding relevant data for AEZ in a concerted effort towards consolidating a centralized database at national level (See Table 8. Proposed Products that the AEZ Unit will focus on).

The Provincial Governments are part of the Ministry of Territorial Administration’s structure. They integrate the provincial directorates and the municipal and communal administrations. For this project two provincial directorates are especially relevant: (1) Directorate for Agriculture and Forestry, and (2) Directorate for Environment, Waste and Community Services. Provincial authorities involved in and data management will be regularly consulted but it is not expected that they will have a role in the project implementation, except from contributing to alignment and information sharing.

Municipal administrations are expected to assign municipal technicians who will accompany the foreseen planning approach. The respective validation process will occur through the municipal CACS (Council for Social Consultation and Concertation) and is to be formally adopted by municipal and provincial authorities. Communal Administrations, whenever they have sufficient capacity, will also accompany activities under Component 2.

- See also Sub-section ‘Institutional Framework’ under 1.1.1 and Table 11 concerning the Project’s stakeholders and their role.

#### b) Institutional responsibilities

The technical execution of the project will be supported by the Government of Angola and represented by the Ministry of Environment (MINAMB) in close cooperation with the Ministry of Agriculture and Forests (MINAGRIF). Other executing partners involve the provincial governments (Huambo and Benguela) and the municipal and communal administrations and their technical services. The project will work with other on-going programs in the project implementation areas of central Angola in a complementary manner as described in the project strategy section (1.3.1). The necessary partnerships will be achieved through: (i) formal and informal communication between institutions and partners implementing other programs and projects; (ii) exchange of information and materials from other projects.

Other key partners supporting the execution include: MINAGRIF, the provincial governments, the municipal and communal administrations and their technical services. MINAGRIF, through its IIA, IIV, IDA, and IDF will have an important role to guarantee a good use of knowledge generated by the AEZ unit and a good alignment between their actions and the SLM Plans to be developed. Provincial authorities are expected to facilitate the sharing of their infrastructure (local offices, meeting / training facilities, transport, etc.) and processes (consultation spaces, communication programs, etc.) for planning and training exercises at provincial, municipal and communal level. In addition to its specific activities this project will be providing content that will improve the quality of planning and training processes of those initiatives already being implemented in the domain of (a) forest management, (b) soil and water conservation, (c) productivity increases, among others. Knowledge sharing mechanisms will be planed and negotiated, and letters of agreement will be produced to clarify the mutual expectations and commitments. Academic and research institutions, especially the ones based in Huambo (FCA and IIA), will also play an important role in taking part of activities related to (a) developing the AEZ, (b) providing input to the planning processes, (c) undertaking agroecological trials at the AEC together with extension workers and facilitators from AP/FFSs.

Intersectoral coordination must be strengthened as a key condition for project feasibility and sustainability, given the gaps at this level and the complexity created by several bodies with related mandates and, sometimes, double subordination. In addition, the information flows required by AEZ and its integration in governance structures and processes demand a degree of institutional cooperation that is unprecedented in Angola. One of the project’s objectives is precisely that of establishing national links of cooperation in a more formal way. The organization of the project’s management structure attempts to take these challenges into consideration and is described below, under sub-section d) ‘Project technical, coordination and steering committees’.

#### c) FAO’s role and responsibilities, as the GEF Agency

The Food and Agriculture Organization of the United Nations (FAO) will be the GEF Agency responsible for supervision and provision of technical guidance during project implementation. As the GEF Agency, FAO will

- Administrate funds from GEF in accordance with the rules and procedures of FAO;

- Oversee project implementation in accordance with the project document, work plans; budgets, agreements with co-financiers and the rules and procedures of FAO;

- Provide technical guidance to ensure that appropriate technical quality is applied to all activities concerned;

- Conduct regular supervision missions; and

- Report to the GEF Secretariat and Evaluation Office, through the annual Project Implementation Review, on project progress and provide financial reports to the GEF Trustee.

As agreed with the Government, FAO will provide direct project services for the smooth implementation of project activities. The direct project services would follow FAO policies on the recovery of direct project costs related to GEF funded projects.

In accordance with the present Project Document and the Annual Work Plan and Budget (AWP/B) approved by the PSC, FAO will prepare budget revisions to maintain the budget updated in the financial management system of FAO and will provide this information to the PSC to facilitate the planning and implementation of project activities. In collaboration with the PMU and the PSC, FAO will conduct the planning of contracting and procurement processes. FAO will process due payments for delivery of goods, services and products upon request of the PMU and based on the AWP/B and Procurement Plans that will be annually approved by the PSC.

FAO and the implementing partners will work with the implementing bodies of other programs and projects to identify opportunities and mechanisms to facilitate synergies with other relevant projects supported by GEF and projects supported by other donors. This partnership will be achieved through: (i) informal communications between GEF bodies and partners implementing other programs and projects; (Ii) exchange of information and materials from other projects.

The roles and responsibilities of FAO staff are regulated by the FAO Guide to the Project Cycle, Quality for Results, 2015, Appendix 4: Roles and Responsibilities of the Project Task Force Members, and its updates.

FAO’s representative in Angola will be the Budget Holder (BH) and will be responsible for the management of GEF resources, as applicable. As a first step in the implementation of the project, the FAO Representation in Angola will establish an interdisciplinary Project Task Force (PTF) within FAO, to guide the implementation of the project.

The PTF is a management and consultative body that integrates the necessary technical qualifications from the FAO relevant units to support the project. The PTF is composed of a Budget Holder, a Lead Technical Officer (LTO), the Funding Liaison Officer (FLO) and one or more technical officers based on FAO Headquarters (HQ Technical Officer).

In consultation with the LTO, the FAO Representative in Angola will be responsible for timely operational, administrative and financial management of the GEF project resources, as applicable, including in particular: (1) the acquisition of goods and contracting of services for the activities of the project, according to FAO’s rules and procedures, in accordance with the approved AWP/B; (2) process the payments corresponding to delivery of goods, services and technical products in consultation with the PSC; (3) provide six-monthly financial reports including a statement of project expenditures to the PSC; and (4) at least once a year, or more frequently if required, prepare budget revisions for submission to the FAO-GEF Coordination Unit through the Field Program Management Information System (FPMIS) of FAO.

The FAO Representative in Angola, in accordance with the PTF, will give its non-objection to the AWP/Bs submitted by the PMU as well as the Project Progress Reports (PPRs). PPRs may be commented by the PTF and should be approved by the LTO before being uploaded by the BH in FPMIS.

The Lead Technical Officer (LTO) for the project will be the Plant Production and Protection Division (AGPM). The role of the LTO is central to FAO’s comparative advantage for projects. The LTO will oversee and carry out technical backstopping to the project implementation. The LTO will support the BH in the implementation and monitoring of the AWP/Bs, including work plan and budget revisions. The LTO is responsible and accountable for providing or obtaining technical clearance of technical inputs and services procured by the Organization.

In addition, the LTO will provide technical backstopping to the PTF to ensure the delivery of quality technical outputs. The LTO will coordinate the provision of appropriate technical support from the PTF to respond to requests from the PSC. The LTO will be responsible for:

- Reviewing and providing no-objection to TORs for consultancies and contracts to be performed under the project, and to CVs and technical proposals short-listed by the PMU for key project positions, goods, minor works, and services to be financed by GEF resources;

- Supported by the FAO Representation in Angola, reviewing and clearing final technical products delivered by consultants and contract holders financed by GEF resources before the final payment can be processed;

- Assisting with review and provision of technical comments to draft technical products/reports during project execution;

- Reviewing and approving project progress reports, in cooperation with the BH;

- Supporting the FAO Representative in examining, reviewing and giving no-objection to AWP/B submitted by the PMU, for their approval by the Project Steering Committee;

- Ensuring the technical quality of the six-monthly Project Progress Reports (PPRs). The PPRs will be prepared by the PMU, with inputs from the PTF. The BH will submit the PPR to the FAO/GEF Coordination Unit for comments, and the LTO for technical clearance. The PPRs will be submitted to the PSC for approval twice a year. The BH will upload the approved PPR to FPMIS.

- Supervising the preparation and ensure the technical quality of the annual PIR. The PIR will be drafted by the PMU, with inputs from the PTF. The PIR will be submitted to the BH and the FAO-GEF Coordination Unit for approval and finalization. The FAO/GEF Coordination Unit will submit the PIRs to the GEF Secretariat and the GEF Evaluation Office, as part of the Annual Monitoring Review report of the FAO-GEF portfolio. The LTO must ensure that the GPC and the PTF have provided information on the co-financing provided during the year for inclusion in the PIR;

- Conducting annual (or as needed) supervision missions;

- Reviewing the TORs for the mid-term review, participate in the midterm workshop with all key project stakeholders, development of an eventual agreed adjustment plan in the project execution approach, and supervise its implementation; and

- Providing comments to the TORs for the final evaluation; provide information and share all relevant background documentation with the evaluation team. Participate in the final workshop with all key project stakeholders, as relevant. Contribute to the follow-up to recommendations on how to insure sustainability of project outputs and results after the end of the project.

The HQ Technical Officer is a member of the PTF, as a mandatory requirement of the FAO Guide to the Project Cycle. The HQ Officer has most relevant technical expertise - within FAO technical departments - related to the thematic of the project. The HQ Technical Officer will provide effective functional advice to the LTO to ensure adherence to FAO corporate technical standards during project implementation, in particular:

- Supports the LTO in monitoring and reporting on implementation of environmental and social commitment plans for moderate risk projects.

- Provides technical backstopping for the project work plan.

- Clears technical reports, contributes to and oversees the quality of Project Progress Report(s)

- May be requested to support the LTO and PTF for implementation and monitoring.

- Will contribute to the overall ToR for the final evaluation; review the composition of the evaluation team and support the evaluation function.

The FAO-GEF Coordination Unit will act as Funding Liaison Officer (FLO). The FAO/GEF Coordination Unit will review the PPRs and financial reports, and will review and approve budget revisions based on the approved Project Budget and AWP/Bs. This FAO/GEF Coordination Unit will review and provide a rating in the annual PIR(s) and will undertake supervision missions as necessary. The PIRs will be included in the FAO GEF Annual Monitoring Review submitted to GEF by the FAO GEF Coordination Unit. The FAO GEF Coordination Unit may also participate in the mid-term review and in the development of corrective actions in the project implementation strategy if needed to mitigate eventual risks affecting the timely and effective implementation of the project. The FAO GEF Coordination Unit will in collaboration with the FAO Finance Division request transfer of project funds from the GEF Trustee based on six-monthly projections of funds needed.

The FAO Financial Division will provide annual Financial Reports to the GEF Trustee and, in collaboration with the FAO-GEF Coordination Unit, request project funds on a six-monthly basis to the GEF Trustee.

#### d) Project technical, coordination and steering committees

Project coordination is structured as follows:

- 1. A Project Steering Committee (PSC) – with the role of steering the whole project, taking strategic decisions and supervising its implementation. The PSC will have the key role of promoting the integration between the different actors involved, facilitating the needed intersectoral coordination as well as the inclusion of the different agendas and experiences at the service of the project’s goals. The National Project Director will chair the PSC to ensure government ownership and engagement of national authorities in the project’s business.

- 2. A Project Management Unit (PMU) – with the role of leading the implementation, creating, supervising and supporting different task forces and the coordination between them. The PMU will deal with the functions of project representation, budget management, procurement, human resources management and monitoring & evaluation. The PMU will be based in Huambo.

- 3. A technical team of experts that has been referred to in this document as “AEZ Unit”. The expertise areas of the unit’s members correspond roughly to the three areas of the project’s components: AEZ/GIS, SLM and finance for SLM.

Further detail about each of these elements is provided below in the following three points:

- Point #1) The Project Steering Committee (PSC) corresponds to the highest level of decision-making vis-à-vis project implementation and will be established for the oversight of project activities at a national level. It is proposed that the PSC is chaired by the Director of the GABAC (or his/her nominee) with the participation of a member of the MINAMB’s GEF unit, MINAGRIF, MINOTH, MAT, one Project Political Coordinator, representatives of the Provincial Governments of Huambo and Benguela, FAO, at least one representative from each municipality, and observers from civil society organizations. The members of the PSC will each assure the role of a Focal Point for the project in their respective agencies. Hence the project will have a Focal Point in each concerned institution. As Focal Points in their agency, the concerned PSC members will meet at once per year and will have the following responsibilities: (i) technically oversee activities in their sector or jurisdiction, (ii) ensure a fluid two-way exchange of information and knowledge between their agency and the project, (iii) facilitate coordination and links between the project activities and the work plan of their agency, (iv) taking decisions in the course of the practical organization, coordination and implementation of the project in order to address implementation problems identified by the PPR; (v) facilitating cooperation between MINAMB/MINAGRIF and project participating partners and enabling a sufficient degree of project ownership by national authorities at the central, provincial and local levels; (vi) ensuring that co-financing support is provided in a timely and effective manner; and (vii) reviewing six-monthly Project Progress and Financial Reports and approving the AWP/B (Annual Work Plan and Budget). Moreover, the PSC shall ensure the project’s sustainability (in view of upscaling, replication and mainstreaming).

- Point #2) The Project Management Unit (PMU) will be established in Huambo and will be hosted by either the offices of MINAMB’s Provincial Directorate for the Environment in Huambo or at the CETAC’s facilities. The PMU will be responsible for the project coordination and the day-to-day management of project activities. It will be comprised of the National Project Coordinator (NPC), a Chief Technical Adviser (CTA), and a National Budget and Operations Officer (see below the detailed descriptions of these positions). The PMU will report directly to the BH and work in close collaboration with the LTO. The PMU will report on an annual basis to the Project Steering Committee (PSC). The PMU will carry out its functions in line with FAO rules and regulations and will act as Secretary for the PSC. It will also be responsible for interacting with Ministries for operational and institutional matters. Some key functions of the PMU are:

- Technically identify, plan, design and support all activities;

- Liaise with government agencies and regularly advocate on behalf of the project;

- Prepare the AWP/B and monitoring plan;

- Be responsible for day-to-day implementation of the project in line with the AWP;

- Ensure a results-based approach to project implementation, including maintaining a focus on project results and impacts as defined by the results framework indicators;

- Coordinate project interventions with other ongoing activities;

- Monitor project progress;

- Be responsible for the elaboration of FAO PPRs and the annual PIR; and

- Facilitate and support the mid-term evaluation/review and final evaluation of the project.

Point #3) Regarding Project Staffing and the AEZ Unit: Instead of the Project Local Offices (PLO) and the Local Activity Coordinator (LAC) that have been deployed by similar projects, in the case of this project it is considered more efficient and effective that the local teams of EDA facilitators are periodically supported by the PMU and AEZ Unit to strengthen the tasks of environmental monitoring, planning, recovery of degraded areas and promotion of environmentally friendly agricultural techniques and technology. See brief description of the role of core project personnel.

- A National Project Coordinator (NPC) will lead the PMU and work closely with GABAC and the AEZ Unit in the day-to-day execution of the project. The NPC, with the support of the Chief Technical Adviser (CTA), will be responsible for terminal reporting, PPRs and providing inputs to the LTO for the preparation of the annual PIRs. In addition, the NPC will be responsible for: (i) the real-time monitoring of project progress and the notification of BH and LTO in the case of any foreseen irregularities/delays; (ii) establishment of a participatory monitoring system covering all aspects of the project; (iii) in consultation with the LTO, identifying suitable consultants for the various tasks and supervise their performance; (iv) conducting regular field supervision visits and provide on-site guidance to local technical staff; (v) day-to-day coordination and communication with Field Office staff in charge of the GEF project; (vi) ensure the dissemination of lessons learned and sharing knowledge with all relevant stakeholders. The NPC will have the profile of a national expert in SLM/spatial planning and will, in addition to the above, be part of technical AEZ Unit at CETAC.

- A Chief Technical Adviser (CTA) will support the NPC in the day-to-day execution of the project for the project’s four years and provide technical advice, guidance and support developing the assessment tools and methodologies, as well as the design and implementation of technological and methodological packages. The CTA will provide on-going support to the project for best practice assessment and implementation to enable the project to maintain strategic direction during implementation by helping project management remain focused on overall results in addition to the day-to-day implementation concerns. The CTA will ensure that the project is an active member of a broader knowledge management network on SLM and AEZ. This includes emphasizing a learning and adaptive approach to project management and implementation in close cooperation with the national partners. The main responsibilities of the CTA with regards to the project’s outcomes/outputs are to: i) provide technical backstopping for all aspects related to GIS/AEZ); ii) support implementation of the LDN-based land degradation assessment; The CTA will collaborate in all technical phases of the project and will work in close conjunction with technical personnel from the AEZ Unit, MINAMB and MINAGRIF, ensuring sustainability of the project technologies and approaches in place. Further, the CTA will coordinate the AEZ Unit for the implementation of all project phases and will support the provision of inputs for the preparation of Project Progress Reports - PPRs (6 months) and Project Implementation Reports – PIRs (12 months). The CTA will have the profile of an International expert in GIS/AEZ and will, in addition to the above, lead the technical AEZ Unit at CETAC.

- A short-term Monitoring and Evaluation Specialist will be in charge of developing and updating the project’s M&E system. The M&E system will be used by the National Project Coordinator to monitor project progress and to make informed management decisions. The M&E Specialist will: i) support the NPC in conducting regular field visits to project sites and update project information in the M&E system. This information will be utilized by the NPC and reflected in preparing the six-monthly Project Progress reports (PPRs): ii) monitor progress in achieving project outputs and outcome indicators; and iii) proposing eventual shifts in project implementation strategies if the project is not performing as planned.

A National Budget and Operations Officer (part-time) will be based in Luanda and responsible for the day-to-day financial management of the project. The Budget and Operations Officer will work in close consultation with the NPC, the BH, LTO and executing partners, in particular with the FAO Representative in Angola and will: i) ensure the smooth and timely implementation of project activities according to FAO rules and standards: ii) coordinate the project operational arrangements: iii) provide support in procurement of project equipment and recruitment of project staff and consultants; and iv) support the BH in managing the budget and in preparing six-monthly budget revisions.

Other project staff supporting the PMU include:

    - Two Drivers;

- As for the AEZ Unit, operating at CETAC (Huambo) is a technical team of experts. Although this team has been referred to in this document as “AEZ Unit”, the expertise areas of the unit’s members correspond roughly to the three areas of the project’s components: AEZ/GIS, SLM and finance for SLM. Composed of a mix of international and national consultants, it also includes the CTA and the NPC as experts in AEZ/GIS and SLM respectively. The ToRs relating to each unit member are provided in Appendix VI. Both the CTA and the NPC operate as technical experts within the team. The Unit will be composed of a shifting set of 9 experts according to project phase, who are assigned with specific activities throughout project implementation (see full Work Plan).

Table 18. Further information about the general composition of the AEZ Technical Unit and PMU

| PMU # (budget ref.) |  | Project Core Team | Responsibilities | Estimated Time Allocated | Type of Contract |
| --- | --- | --- | --- | --- | --- |
| [1] |  | Project Coordinator / National specialist in SLM, Land-Use Management and Spatial Planning expert. Costs are spread across C1, and C2 on a 50/50 basis. | Coordinate the entire project. Core focus: Outputs 1.1, 1.2, 2.1, 2.2, 2.3. Other Outputs: 1.1 through 1.5. General support to Component 3 activities. | 4 years | 5543 Consultants - Locally-recruited |
| [2] |  | CTA International GIS and AEZ expert International GIS expert with experience in FAO AEZ methodology over a 3.5-year period. | Assist the NPC to Coordinate the entire project. Core focus: Outputs 1.1, 1.2, 1.3, 1.4, 1.5. Other Outputs: 2.1 through 2.3. General support to all Component 3 activities. | 3.5 years | 5542 Consultants - Internationally-recruited |
| [3] |  | International Agro-Economy expert with good knowledge of SLM finance 24 months over 4 years (part-time, missions to country at least twice a year): Focus on the economics and finance of land degradation and ecosystem restoration. | Outputs 1.3, 2.1, 2.2, 2.3 | 24 months | 5542 Consultants - Internationally-recruited |
| [4] |  | National GIS and AEZ expert (similar technical tasks to those of the coordinator, except, management, but with a less senior profile) | Core focus: Outputs 1.4 and 1.5. Other Outputs: 2.1, 2.2, 2.3, and where needed, support to 1.1, 1.2, 1.3. | 3.5 years | 5543 Consultants - Locally-recruited |
| [5] | International Computer Scientist / ITC Programmer Analyst (part-time) |  | Outputs 1.4 | 12 months | 5542 Consultants - Internationally-recruited |
| [6] |  | Senior Consultant: National expert in GreeNTD (or similar participatory methodologies) who is familiar with Angolan territorial and land-use governance. Field services at approx. 3-5 months per year, over 4 years, or according to demand. | Output 2.1 and others related under Components 2 | 5-6 months | 5543 Consultants - Locally-recruited |
| [7] |  | National Budget and Operations Officer (part-time at 50%) | Oversight, management, support to Comp 3 if needed | 10 months | 5543 Consultants - Locally-recruited |

/ Refer to TOR in Appendix VI for more details. /

##### Proposed Letters of Agreement

The project may achieve a number of key outputs through letters of agreements (LoAs) that will be elaborated and signed between FAO and collaborating partners. The service providers and consultants will be administratively managed in Huambo, but funds will be made available through approval by FAO Luanda. Funds received under a LoA will be used to execute the project activities in conformity with FAO’s rules and procedures. The proposed LoAs are listed under the “Contracts” budget line of the project budget.

Table 19. Proposed Letters of Agreement

| LoAs Budgeted for [*] | Project Partners | General scope of activities | Outputs on focus |
| --- | --- | --- | --- |
| Under C1 | CETAC | LOA: (hosting agreement under negotiations) with CETAC so that the Center is progressively capacitated to (i) serve as the national hub for AEZ experts, including by carving out strategic partnerships, and (ii) maintain the flow of services from the AEZ unit beyond the project’s lifetime. Indicatively may include appointing of young professionals, preferably from amongst CETAC staff, if not then or externally recruited. (C1 activities) | 1.1, 1.2, 1,3, 1.4, 1.5 |
| Under C1, but refers to both components | Instituto de Investigação Agronómica (IIA) and / or Faculdade de Ciências Agrárias (or both – with the necessary budget adjustments) | LOA (prospective): Establishing cooperation agreements with Instituto de Investigação Agronómica (IIA) and Faculdade de Ciências Agrárias, regarding the participation their staff in Outputs 1.2, 1,3, 1.4, 1.5, as well as Outputs 2.1, 2.2, 2.3, covering backstopping aspects on agronomic matters regarding the landscape approach under C2, and also SLM finance under C3, to the extent that they have expertise to offer in the relevant domains[The LOA amount(s) in the budget will be treated flexibly, indicatively as a lump-sum for likely more than one potential LOA amounts that can be adjusted adjusted during project inception.] Refer to Component 1,2 and 3 descriptions. | 1.1, 1,3, 1.4, 1.5, 2.1, 2.2, 2.3, extending also to aspects of Component 3 |
| Under C1, but refers to the entire project | CETAC in collaboration with one of the academic institutions above, or both | LOA (prospective): Job shadowing program engaging trainees and CETAC’s appointed staff members (learning-by-doing). Indicatively may include appointing of young professionals, preferably from amongst CETAC staff, if not then or externally recruited. Refer to Component 1 descriptions for the core strategy behind the ‘Job shadowing program’ and noting that its scope is expected to be relevant for all three Components of the project. Its budget is therefore spread accordingly across the Components. | Relevant outputs under C1, C2 and C3 |
| Under C1 and C2 | IGCA, INAMET and GSA (currently lumped for budgeting purposes – to be harmonized during negotiations) | LOA (prospective): Development of a collaboration agreement with national entities: (1) IGCA regarding the sharing of information relative to mapping and cadaster, including data from the ongoing land tenure registration process (Outputs 1.2, 1,3, 1.4) and development of common products through institutional collaboration; and (2) INAMET regarding cooperation with CETAC on spatial data management, training etc, and the coordination of environmental monitoring activities, and more specifically on the following study topics: (a) Spatiotemporal assessment of Land Degradation; and (b) Monitoring of other LD-related measures (Outputs 1.2, 1,3, 1.4); and (3) GSA for cooperation in environmental monitoring and monitoring the impact of SLM on farmer’s incomes (Outputs 1.2, 1,3, 1.4). [The amount budgeted is a lump-sum for several LOAs and indicative -- to be adjusted during inception.] Refer to Component 1 and Component 2 descriptions. | 1.2, 1.3, 1.4 |
| Under C2 | IDA / EDA | LOA (prospective): Partnership agreement with IDA/EDA. The work on the ground IDA/EDA extension services under senior supervision. Sub-contracting IDA for Implementing Output 2.2 (A network of AP/FFSs (Agro-Pastoral and Farmer Field Schools) is supported in implementing as a fundamental dimension of local land [management] use in a selected group of communities in the Provinces of Huambo and Benguela.) Refer to Component 2 descriptions. | Component 2, in particular 2.2 and others related under Component 1 |

* Note: The budget line used is “5650 Contracts”.

##### Proposed Synergy Partnerships

Table 20. Proposed Synergy Partnerships (prospective MoUs or other applicable arrangements)

| # | Project Partners | General scope of activities | Outputs |
| --- | --- | --- | --- |
| 1. | Instituto de Desenvolvimento Agrário (IDA) | Cooperation agreements with agreement with IDA/EDA concerning work on the ground with IDA/EDA concerning extension services and under senior supervision by project team. | 1.5 2.1, 2.2, 2.3 |
|  | IDA – National Level | Participation in steering committee. LoA authorizing extension workers and AP/FFSs to be part of the project |  |
|  | IDA Departments in Huambo and Benguela | Exchange info, attend coordination meetings, be part of planning and decision making process |  |
|  | EDAs in Londuimbali, Bailundo and Chongorói | Take part in training in SLM and Sustainable Land-use Planning, organized demonstrative agroecological trials at AEC, together with researchers and project experts, organize training and demonstrations sessions at FFS on SLM. Facilitate planning at FFS level to integrate SLM |  |
| 2. | Project ICE-SLM | AEC technical supervisor from ICE-SLM project should closely collaborate with the AEZ Unit, especially concerning activities for which the collaboration of the AEC- Staff is expected. | 1.5, 2.2, 2.3 |

#### e) Coordination with other ongoing and planned related initiatives

The following organizational chart illustrates the institutional implementation arrangements described in the previous sections:

Figure 20. Diagram with the implementation arrangement

### 2.1.2 Government Inputs

The main government input will be the provision of office space, furbished and functional, at CETAC and AEC for the AEZ Unit and SLM teams to operate. Both institutions have a good infrastructure that is not being fully used for lack of human resources, funding and appropriate programs. This project is providing both and expecting to deploy these existing, but currently idle, structures which are also to be strengthened through the project ICE-SLM.

More specifically, and related to MINAMB’s co-financing contribution, it is expected to have as dedicated and shared space in CETAC:

- Dedicated office space for the coordinator, furnished and with a computer;

- Dedicated open space as an office for a group of 8 people with adequate internet connection;

- Dedicated GIS room, equipped with 3 computers and a plotter; and

- Access to a training room and meeting room that will be shared with other activities taking place at CETAC.

From AEC of Chipipa it is expected:

    - Dedicated office space, furbished and equipped with computer and an adequate internet connection.

    - Access to training spaces and meeting rooms that will be shared with other activities;

    - Access to field space and equipment for conducting demonstrative agroecological trials.

From IDA, IIA and FCA it is expected that some of their staff is periodically allocated to the project. The project will provide training opportunities, modest subsidies for work done in the field and access to equipment or information needed for the functionality of the project activities. Opportunities to interact with other professionals will also be provided.

From Provincial Directorates, Provincial Departments, Municipal and Communal administrations and other relevant bodies it is expected that information will be shared and when needed and if available time slots are made available for the project team to give input or collect opinions and data. This also applies to GSA, INAMET and IGCA from whom it is expected a systematic sharing of data.

### 2.1.3 Resource Partner Inputs

All partners to be contracted through the project and associated costs are provided in detail in the budget presented in Appendix IV.

Consultants: The project will hire the list of staff indicated in appendix 6 and/or table 17.

Contracts: The BH, in close collaboration with the Project Coordinator, the LTO and the Program and operational Support Officer will procure service providers as detailed in the detailed budget in Appendix 4 and table 18, in line with the AWP and Budget and in accordance with FAO’s rules and regulations.

Travel: Travel of consultants will be supported to ensure adequate support in the field, and at operational level.

Training: The training line will cover costs for capacity building of the AEZ unit and other training according to the work plan. Specific technical training will be required to support households and groups involved in specialised livelihoods diversification activities. It is expected that the training support will be largely informal through service provider contracts. Workshops in support of the programme development are also covered under the training line.

Expendable equipment: The BH, in close collaboration with the Project Coordinator, the LTO and the Program and operational Support Officer will procure the non-expendable equipment and services provided for in the detailed budget in Appendix 4, in line with the AWP and Budget and in accordance with FAO’s rules and regulations.

As per the guidance in FAO’s Project Cycle Guide, the Project Manager, under supervision of the BH, will draw up an annual procurement plan for major items, which will be the basis of requests for procurement actions during implementation. Provision is made for expandable equipment to ensure adequate support to implementation of the programme, in particular support for the field offices.

Non-expendable equipment: The BH, in close collaboration with the Project Coordinator, the LTO and the Program and operational Support Officer will procure the equipment as detailed in the detailed budget in Appendix 3, in line with the AWP and Budget and in accordance with FAO’s rules and regulations.

Careful procurement planning is necessary for securing goods, services and works in a timely manner, on a “Best Value for Money” basis, and in accordance with the Rules and Regulations of FAO. It requires analysis of needs and constraints, including forecast of the reasonable timeframe required to execute the procurement process. Procurement and delivery of inputs in technical cooperation projects follow FAO’s rules and regulations for the procurement of supplies, equipment and services (i.e. Manual Sections 502 and 507). Manual Section 502: “Procurement of Goods, Works and Services” establishes the principles and procedures that apply to procurement of all goods, works and services on behalf of the Organization, in all offices and in all locations, with the exception of the procurement actions described in Appendix A – Procurement Not Governed by Manual Section 502.

As per the guidance in FAO’s Project Cycle Guide, the Project Manager, under supervision of the BH, will draw up an annual procurement plan for major items, which will be the basis of requests for procurement actions during implementation. The first procurement plan will be prepared at the time of project start-up, if not sooner, in close consultation with the coordinator and LTU. The plan will include a description of the goods, works, or services to be procured, estimated budget and source of funding, schedule of procurement activities and proposed method of procurement. In situations where exact information is not yet available, the procurement plan should at least contain reasonable projections that will be corrected as information becomes available.

The procurement plan shall be updated every 12 months and submitted to FAO BH and LTO for clearance, together with the AWP/B and annual financial statement of expenditures report for the next instalment of funds.

Technical assistance: The project will support  field visits of LTO or other technical officers to assess progress of the project and provide critical inputs to strengthen ongoing activities

General Operating Expenditures: GOE will be covered as well under the project.

The detailed budget (overall and by output) can be found in appendix 3

FAO will provide assisted national implementation, and will thus provide all necessary operational, administrative and procurement services, according to FAO’s rules and regulations. At the same time, the strategy for project implementation relies substantially on a significant number of LoAs as a means to increase project ownership and the efficacy of the project capacity building strategy. All partners with whom proposed LoAs would be signed and partnerships established, are national public institutions and therefore respective inputs are described in the previous section.

The specific type of GIS hardware equipment to be purchased needs to be determined by the GIS experts at project inception.

### 2.1.4 FAO Inputs

| FAO’s resource input and Co-financing per Component ($) | FAO’s co-financing | MINAMB / GABAC and CETAC (Public Investment) | MINAGRIF (Public Investment) | MINAMB / CETAC (in-kind) | GEF amount | PROJECT TOTAL |
| --- | --- | --- | --- | --- | --- | --- |
| 1. Agroecological zoning (AEZ) for integrated planning |  | 2,900,000 | 1,500,000 | 0 | 1,201,576 | 5,601,576 |
| 2. Sustainable Land Management in target landscapes |  | 3,700,000 | 1,500,000 | 0 | 706,825 | 5,906,825 |
| 3. Economic and financial leverage approaches to SLM | 0 | 2,900,000 | 1,500,000 | 0 | 478,525 | 4,878,525 |
| 4. Knowledge management, monitoring and evaluation | 0 |  |  | 0 | 127,100 | 127,100 |
| Project Management (PMC) | 500,000 |  |  | 500,000 | 125,700 | 1,125,700 |
| TOTAL | 500,000 | 9,500,000 | 4,500,000 | 500,000 | 2,639,726 | 17,639,726 |

## 2.2) RISK MANAGEMENT

### 2.2.1 Potential Risks to the Project

Project risks were identified and analyzed during its preparation and mitigation measures have been incorporated into the design of the project (see Risk Matrix in Appendix V). With the support and supervision of FAO, the Project Steering Committee (PSC) will be responsible for managing these risks as well as the effective implementation of mitigation measures. The Monitoring and Evaluation system (M&E) will be used to monitor indicators of outcomes and outputs, project risks and mitigation measures. The PSC shall also be responsible for monitoring the effectiveness of mitigation measures and adjust mitigation strategies as needed, and to identify and manage any new risk that was not been identified during the preparation of the Project, in collaboration with the project partners.

The six-monthly Project Progress Report (PPR) is the main monitoring and risk management instrument. The PPR includes a section of systematic risk monitoring and mitigation actions that were identified in the previous PPR. The PPR also includes a section to identify any new risks or risks that have not been addressed yet, rating and mitigation actions, as well as the staff responsible for monitoring such actions and estimated duration of the same. FAO will monitor the project risk management and the follow up as needed, providing support for adjusting and implementing mitigation strategies. The preparation of reports on risks monitoring and rating will also be part of the Annual Project Implementation Review (PIR) prepared by FAO and submitted to the GEF Secretariat.

A summary of the analysis of risks identified during project preparation, their likelihood of occurrence and proposed mitigation measures are set out in Appendix V – Section A.

### 2.2.2 Environmental and Social Risks from the Project

The project has been rated as low risk by the Lead Technical Officer and therefore, no further action is required. FAOs safeguards will, however, be monitored during project implementation and reported upon in its Project Progress Reports (PPR). Refer to Appendix V – Section B) for details.

## 2.3) MONITORING, PERFORMANCE ASSESSMENT AND REPORTING

### 2.3.1 Monitoring Arrangements

Project oversight will be carried out by the Project Steering Committee (PSC), the FAO GEF Coordination Unit and relevant Technical Units in HQ. Oversight will ensure that: (i) project outputs are produced in accordance with the project results framework and leading to the achievement of project outcomes; (ii) project outcomes are leading to the achievement of the project objective; (iii) risks are continuously identified and monitored and appropriate mitigation strategies are applied; and (iv) agreed project global environmental benefits/adaptation benefits are being delivered.

The FAO GEF Unit and HQ Technical Units will provide oversight of GEF financed activities, outputs and outcomes largely through the annual Project Implementation Reports (PIRs), periodic backstopping and supervision missions.

Project monitoring will be carried out by the Project Coordination Unit (PMU) and the FAO budget holder. Project performance will be monitored using the project results matrix, including indicators (baseline and targets) and annual work plans and budgets. At inception the results matrix will be reviewed to finalize identification of: i) outputs ii) indicators; and iii) missing baseline information and targets. A detailed M&E plan, which builds on the results matrix and defines specific requirements for each indicator (data collection methods, frequency, responsibilities for data collection and analysis, etc.) will also be developed during project inception by the M&E specialist.

### 2.3.2 Reporting

Specific reports that will be prepared under the M&E program are: (i) Project inception report; (ii) Annual Work Plan and Budget (AWP/B); (iii) Project Progress Reports (PPRs); (iv) annual Project Implementation Review (PIR); (v) Technical Reports; (vi) co-financing reports; and (vii) Terminal Report. In addition, assessment of the GEF Monitoring Evaluation Tracking Tools against the baseline (completed during project preparation) will be required at midterm review and final project evaluation.

Project Inception Report. It is recommended that the PMU prepare a draft project inception report in consultation with the LTO, BH and other project partners. Elements of this report should be discussed during the Project Inception Workshop and the report subsequently finalized. The report will include a narrative on the institutional roles and responsibilities and coordinating action of project partners, progress to date on project establishment and start-up activities and an update of any changed external conditions that may affect project implementation. It will also include a detailed first year AWP/B, a detailed project monitoring plan. The draft inception report will be circulated to the PSC for review and comments before its finalization, no later than one month after project start-up. The report should be cleared by the FAO BH, LTO and the FAO GEF Coordination Unit and uploaded in FPMIS by the BH.

Results-based Annual Work Plan and Budget (AWP/B). The draft of the first AWP/B will be prepared by the PMU in consultation with the FAO Project Task Force and reviewed at the project Inception Workshop. The Inception Workshop (IW) inputs will be incorporated and the PMU will submit a final draft AWP/B within two weeks of the IW to the BH. For subsequent AWP/B, the PMU will organize a project progress review and planning meeting for its review. Once comments have been incorporated, the BH will circulate the AWP/B to the LTO and the FAO GEF Coordination Unit for comments/clearance prior to uploading in FPMIS by the BH. The AWP/B must be linked to the project’s Results Framework indicators so that the project’s work is contributing to the achievement of the indicators. The AWP/B should include detailed activities to be implemented to achieve the project outputs and output targets and divided into monthly timeframes and targets and milestone dates for output indicators to be achieved during the year. A detailed project budget for the activities to be implemented during the year should also be included together with all monitoring and supervision activities required during the year. The AWP/B should be approved by the Project Steering Committee and uploaded on the FPMIS by the BH.

Project Progress Reports (PPR). PPRs will be prepared by the PMU based on the systematic monitoring of output and outcome indicators identified in the project’s Results Framework (Appendix I). The purpose of the PPR is to identify constraints, problems or bottlenecks that impede timely implementation and to take appropriate remedial action in a timely manner. They will also report on projects risks and implementation of the risk mitigation plan. The Budget Holder has the responsibility to coordinate the preparation and finalization of the PPR, in consultation with the PMU, LTO and the FLO. After LTO, BH and FLO clearance, the FLO will ensure that project progress reports are uploaded in FPMIS in a timely manner.

Annual Project Implementation Review (PIR). The BH (in collaboration with the PMU and the LTO) will prepare an annual PIR covering the period July (the previous year) through June (current year) to be submitted to the FAO GEF Coordination Unit Funding Liaison Officer (FLO) for review and approval no later than (check each year with GEF Unit but roughly end June/early July each year). The FAO GEF Coordination Unit will submit the PIR to the GEF Secretariat and GEF Evaluation Office as part of the Annual Monitoring Review report of the FAO-GEF portfolio. PIRs will be uploaded on the FPMIS by the FAO GEF Coordination Unit.

Quarterly activity reporting from local project officers and the AEZ unit. Every three months, the project team will report on activities to the Provincial and Municipal Governments keeping the other relevant institutions and collaborating projects informed, such as IDA, EDA and other as applicable.

Technical Reports: Technical reports will be prepared by national, international consultants (partner organizations under LOAs) as part of project outputs and to document and share project outcomes and lessons learned. The drafts of any technical reports must be submitted by the PMU to the BH who will share it with the LTO. The LTO will be responsible for ensuring appropriate technical review and clearance of said report. The BH will upload the final cleared reports onto the FPMIS. Copies of the technical reports will be distributed to project partners and the Project Steering Committee as appropriate.

Co-financing Reports: The BH, with support from the PMU, will be responsible for collecting the required information and reporting on co-financing as indicated in the Project Document/CEO Request. The PMU will compile the information received from the executing partners and transmit it in a timely manner to the LTO and BH. The report, which covers the period 1 July through 30 June, is to be submitted on or before 31 July and will be incorporated into the annual PIR. The format and tables to report on co-financing can be found in the PIR.

GEF Tracking Tools: Following the GEF policies and procedures, the relevant tracking tools will be submitted at two moments: (i) with the project document at CEO endorsement and (ii) with the project’s terminal evaluation or final completion report. The TT will be uploaded in FPMIS by the FAO GEF Coordination Unit. The TT at the baseline were developed by the Project Design Specialist, in close collaboration with the FAO Project Task Force. They are filled in by the PMU and made available for the final evaluation.

Terminal Report: Within two months before the end date of the project, and one month before the Final Evaluation, the PMU will submit to the BH and LTO a draft Terminal Report. The main purpose of the Terminal Report is to give guidance at ministerial or senior government level on the policy decisions required for the follow-up of the project, and to provide the donor with information on how the funds were utilized. The Terminal Report is accordingly a concise account of the main products, results, conclusions and recommendations of the project, without unnecessary background, narrative or technical details. The target readership consists of persons who are not necessarily technical specialists but who need to understand the policy implications of technical findings and needs for insuring sustainability of project results.

The table below provides a summary of the main M&E reports, responsible parties and timeframe.

Table 21. M&E Framework

| Type of M&E Activity | Responsible Parties | Time-frame | Estimate of costs |
| --- | --- | --- | --- |
| Inception Workshop (IW), plus similar events relating to project implementation, e.g. project end workshop | PMU, supported from the LTO, BH, and GEF Coordination Unit (GCU) | Within two months of project start up | USD 8,000 + 8,000 USD = USD 16,000 |
| AEZ Survey to validate PMAT baseline values | PMU and service providers | Within three months of project start up | USD 0 - data is collected by the PMU. Else, costs are already foreseen under different activities |
| Project Inception Report | PMU, cleared by FAO LTO, HQ Officer(s), BH, and the GCU | Immediately after the workshop. | USD 0 - project inception report is developed by the PMU. |
| Field based impact monitoring | PMU, MINAMB and other relevant agencies – including regional and provincial - to participate. | Periodically - to be determined at inception workshop. | USD 0 - data is collected by the PMU and costs already foreseen under different activities |
| Supervision visits and rating of progress in PPRs and PIRs | PMU; FAO (FAO Angola, LTO). FAO-GCU may participate in the visits if needed. | Annual or as required | The visits of the LTO and the GCU will be paid by GEF agency fee. The visits of the NPC and CTA will be paid from the project travel budget |
| Project Progress Reports | BH with support from PMU, with inputs from MINAMB, PSC members and other partners | Semi-annual, or are required | USD 5,100 (budget reserve for a specialized M&E consulting under Component 4, will include focus on “best-practices” and “lessons-learning”) |
| Project Implementation Review report | BH (in collaboration with the PMU and the LTO) Drafted by the NPC, with the supervision of the LTO and BH. Approved and submitted to GEF by the FAO-GCU | Annual | Paid by GEF agency fee |
| PMAT (the LD Tracking Tool) [FAO to determine if still required and amend table accordingly] | PMU supported by the LTO | Project start-up (already completed during the PPG), mid-Term and project end. | USD 0 - data is collected by the PMU. |
| Co-financing Reports | BH with support from PMU and NPC with input from other co-financiers | Annual | Completed by NPC and CTA |
| Technical reports | PMU, BH, LTO & Participating Units | As appropriate | USD 16,000 charged to M&E budget lumped with funds for on translations, report typesetting, web-publishing and other related work) |
| Mid-term Review (MTR) | MTR: FAO Angola, External consultant, in consultation with the project team, including the FAO-GEF Coordination Unit and others | At mid-point of project implementation | USD 15,000 for independent consultants and associated costs. In addition, the agency fee will pay for expenditures of FAO staff time and travel |
| Final evaluation (including accessible report on “best-practices” and “lessons-learned”) | With the support of FAO Office of Evaluation in consultation with the project team including the GCU and other partners | At the end of project implementation | USD 45,000 for external, independent consultants and associated costs. In addition, the agency fee will pay for expenditures of FAO staff time and travel |
| Terminal Report | PMU, LTO, TCSR Report Unit | At least two months before the end date of the Execution Agreement | USD 0 (as completed by CTA and PMU – else, costs are already adequately budgeted for under ‘technical reports’) |

## 2.4) EVALUATION PROVISIONS

At project mid-term, the BH will arrange a Mid-Term Review (MTR) in consultation with the PSC, the PMU, the LTO and the FAO-GEF Coordination Unit. The MTR will be conducted to review progress and effectiveness of implementation in terms of achieving project objective, outcomes and outputs. The MTR will allow mid-course corrective actions, if needed.  The MTR will provide a systematic analysis of the information provided under the M&E Plan (see above) with emphasis on the progress in the achievement of expected outcome and output targets against budget expenditures. The MTR will refer to the Project Budget (see Appendix IV) and the approved AWP/Bs. The MTR will contribute to highlight replicable good practices and main problems faced during project implementation and will suggest mitigation actions to be discussed by the PSC, the LTO and FAO-GEF Coordination Unit.

An independent Final Evaluation (FE) will be carried out six months prior to the terminal report meeting. This independent final evaluation will be supported by the FAO Office of Evaluation in consultation with the project team, the FAO-GEF coordination unit, and other stakeholders. The FE will aim to identify the project impacts, sustainability of project outcomes and the degree of achievement of long-term results. The FE will also have the purpose of indicating future actions needed to expand on the existing Project in subsequent phases, mainstream and upscale its products and practices, and disseminate information to management authorities and institutions with responsibilities in food security, conservation and sustainable use of natural resources, small-scale farmer agricultural production and ecosystem conservation to assure continuity of the processes initiated by the Project.  Both the MTR and FE will pay special attention to outcome indicators and will be aligned with the GEF Tracking tool and to neighboring countries. See previous section about M&E mechanisms. The FAO Office of Evaluation has provided clearance for the provisions of the Final Evaluation, included in this project document at budget and technical level.

## 2.5) FINANCIAL MANAGEMENT AND REPORTING

Financial Records. FAO shall maintain a separate account in United States dollars for the project’s GEF resources showing all income and expenditures. Expenditures incurred in a currency other than United States dollars shall be converted into United States dollars at the United Nations operational rate of exchange on the date of the transaction. FAO shall administer the project in accordance with its regulations, rules and directives.

Financial Reports. The BH shall prepare six-monthly project expenditure accounts and final accounts for the project, showing amount budgeted for the year, amount expended since the beginning of the year, and separately, the un-liquidated obligations as follows:

Details of project expenditures on a component-by-component and output-by-output basis, reported in line with project budget codes as set out in the project document, as at 30 June and 31 December each year.

Final accounts on completion of the project on a component-by-component and output-by-output basis, reported in line with project budget codes as set out in the project document.

A final statement of account in line with FAO Oracle project budget codes, reflecting actual final expenditures under the project, when all obligations have been liquidated.

The BH will submit the above financial reports for review and monitoring by the LTO and the FAO GEF Coordination Unit. Financial reports for submission to the donor (GEF) will be prepared in accordance with the provisions in the GEF Financial Procedures Agreement and submitted by the FAO Finance Division.

Budget Revisions. Semi-annual budget revisions will be prepared, if necessary, by the BH in accordance with FAO standard guidelines and procedures.

Responsibility for Cost Overruns. The BH is authorized to enter into commitments or incur expenditures up to a maximum of 20 % over and above the annual amount foreseen in the project budget under any budget sub-line provided the total cost of the annual budget is not exceeded.

Any cost overrun (expenditure in excess of the budgeted amount) on a specific budget sub-line over and above the 20 % flexibility should be discussed with the GEF Coordination Unit with a view to ascertaining whether it will involve a major change in project scope or design. If it is deemed to be a minor change, the BH shall prepare a budget revision in accordance with FAO standard procedures. If it involves a major change in the project’s objectives or scope, a budget revision and justification should be prepared by the BH for discussion with the GEF Secretariat.

Savings in one budget sub-line may not be applied to overruns of more than 20 % in other sub-lines even if the total cost remains unchanged, unless this is specifically authorized by the GEF Coordination Unit upon presentation of the request. In such a case, a revision to the project document amending the budget will be prepared by the BH.

Under no circumstances can expenditures exceed the approved total project budget or be approved beyond the NTE date of the project. Any over-expenditure is the responsibility of the BH.

Audit. The project shall be subject to the internal and external auditing procedures provided for in FAO financial regulations, rules and directives and in keeping with the Financial Procedures Agreement between the GEF Trustee and FAO.

The audit regime at FAO consists of an external audit provided by the Auditor-General (or persons exercising an equivalent function) of a member nation appointed by the Governing Bodies of the Organization and reporting directly to them, and an internal audit function headed by the FAO Inspector-General who reports directly to the Director-General. This function operates as an integral part of the Organization under policies established by senior management, and furthermore has a reporting line to the governing bodies. Both functions are required under the Basic Texts of FAO which establish a framework for the terms of reference of each. Internal audits of imprest accounts, records, bank reconciliation and asset verification take place at FAO field and liaison offices on a cyclical basis.

Procurement. Careful procurement planning is necessary for securing goods, services and works in a timely manner, on a “Best Value for Money” basis. It requires analysis of needs and constraints, including forecast of the reasonable timeframe required to execute the procurement process. Procurement and delivery of inputs in technical cooperation projects will follow FAO’s rules and regulations for the procurement of supplies, equipment and services (i.e. Manual Sections 502 and 507). Manual Section 502: “Procurement of Goods, Works and Services” establishes the principles and procedures that apply to procurement of all goods, works and services on behalf of the Organization, in all offices and in all locations, with the exception of the procurement actions described in Procurement Not Governed by Manual Section 502. Manual Section 507 establishes the principles and rules that govern the use of Letters of Agreement (LoA) by FAO for the timely acquisition of services from eligible entities in a transparent and impartial manner, taking into consideration economy and efficiency to achieve an optimum combination of expected whole life costs and benefits.

As per the guidance in FAO’s Project Cycle Guide, the BH will draw up an annual procurement plan for major items, which will be the basis of requests for procurement actions during implementation. The first procurement plan will be prepared at the time of project start-up, if not sooner, in close consultation with the CTA/NPC and HQ Officer(s). The plan will include a description of the goods, works, or services to be procured, estimated budget and source of funding, schedule of procurement activities and proposed method of procurement. In situations where exact information is not yet available, the procurement plan should at least contain reasonable projections that will be corrected as information becomes available.

The procurement plan shall be updated every 12 months and submitted to FAO BH and LTO for clearance, together with the AWP/B and annual financial statement of expenditures report for the next instalment of funds.

The BH, in close collaboration with the CTA/NPC, the LTO and the Budget and Operations Officer will procure the equipment and services provided for in the detailed budget in Appendix 3, in line with the AWO and Budget and in accordance with FAO’s rules and regulations.

# SECTION 3 - SUSTAINABILITY

## 3.1) CAPACITY DEVELOPMENT

The project focuses on the capacity development of staff from MINAMB (especially at GABAC, CETAC and at the Agroecological Centre in Chipipa) and from MINAGRIF in domains related to Agroecological Zoning (AEZ), SLM, the AP/FFS approach, the integration of AEZ products in participatory planning, the practical implementation of land-use plans for SLM, and the mobilization of financial resources at various scales for funding initiatives that directly promote SLM.

The above-mentioned target domains for capacity building are approached though a strategy that focuses on the dimensions of enabling environment, organizational capacity and individuals. The first two relate to the institutional structure set up by the project, with CETAC placed as a national hub for AEZ integrated planning, in articulation with the AECs, which in turn serve as operational antennas for supporting extension services in reaching communities and farmers in regards to the practical promotion of SLM based on AEZ products. In particular, the AECs are to become hubs for the network of AP/FFSs that are being installed by a variety of other projects. Individuals (both those outside and within key institutions, are to be capacitated through structured training programs in all project components and regarding all the domains stated above. All capacitation strategies foreseen by the project are permeated by the principle of “learning by doing”.

The project is anchored in the appropriate institutions of MINAMB and MINAGRIF. Institutional sustainability is aimed at by embedding the project in national institutions, including relevant academic institutions such as IIA and FCA. As a Technical Assistance project, institutional support, knowledge-transfer and adaptation to local conditions are among the main elements of the strategy of the project.

Activities related to the setting up of the AEZ WebGIS DSS, the initial municipal AEZ products (C1), the conduction of the GreeNTD sessions, the ensuing drafting of the SLM Plans (C2), and the economic assessment of LD and development of financial mechanisms (C3) are to be executed by the project technical consultants (the experts of the AEZ Unit), but this will be mostly done in a demonstrative manner where national staff are engaged as much as possible in the respective tasks. The project’s national consultants (the ‘Project’s Team’) are part of this process and are expected to take the lead in these activities relieving some of the international consultants of their involvement in the project. In respect other activities, especially those under C2 related to the implementation of the SLM plans, the project team will not directly carry out the main activities, but rather support the staff of MINAMB (at CETAC and the AEC) and MINAGRIF (IDA/EDAs) in carrying them out, running training courses, on-the-job training and overall supervising technically the respective tasks. Thus, upon termination of the project, all tasks and routines will have been absorbed into the regular work of CETAC, AEC, EDAs and AP/FFs. It will, however, be important that the proposed approach is scaled-up through the assistance of follow-up initiatives and projects to help consolidate the capacity gains and funding the necessary investments.

## 3.2) FINANCIAL AND ECONOMIC SUSTAINABILITY

The AEZ system is expected to collect and make available data that is of crucial importance for the development of the agricultural sector and the territorial management of land use. It is extremely likely that a vast array of all kinds of different agricultural projects and initiatives related to the territorial management of land use will be willing to pay for AEZ products in order to maximize their efficacy and efficiency. This simple principle will be key to ensuring the financial and economic sustainability of the AEZ system and of the general approach introduced by the project.

A key to sustainability across all three components is ownership and in Component 3, more specifically, it is leverage. For the AEZ system, as stated above, sustainability is already implied in the design of the outputs that will cater for its development – namely to ensure that the system has good prospect of being sustainably maintained by project end. For Component 2, a core purpose of landscape level plans is to ensure sustainability. Additionally, local ownership and the bottom-up approach of AP/FFS are essential for securing the sustainable future of the changes that both the planning and the learning are expected to bring about.

## 3.3) ENVIRONMENTAL SUSTAINABILITY

A majority of the population in the project intervention areas depends directly on natural resources for their livelihoods; one of the main issues addressed by the project includes the impacts of the ongoing environmental degradation and depletion of natural resources by unsustainable agriculture and land-use more broadly. Environmentally, the project aims to prevent and reverse land degradation, safeguard natural resources, strengthen sustainable agricultural practices and sustainable forest management in Angola in order to reinforce the resilience to climate change of rural communities in the targeted provinces.

The AP/FFs model being promoted under this project integrates an ecosystem-based approach to the agricultural sector. This approach aims at developing and scaling up SLM practices and technologies for local communities through practical activities in the field. The AP/FFS approach promotes the adoption of SLM and CCA practices by local communities, likely to be adopted at a larger scale after the end of the project, which will foster the resilience of the environment and the agricultural sector in the long term.

The project will durably strengthen the ability of local communities and government technicians to prevent and reverse land degradation through AEZ-based SLM and thus indirectly protect local biodiversity and respective ecosystem serves, increasing their resilience to cope with climate change and hazardous climate events that are likely to be more frequent in the future.

## 3.4) INNOVATION AND SCALE UP

### 3.4.1 Innovativeness

Innovation. The project is concerned with capacity building and land use governance for SLM. It adopts a Landscape Approach, through which it negotiates the stakes for land use and its management in Angola, with a view towards SLM. Several aspects of the project constitute ‘novelty’ in the Angolan context and open up the way to innovation. First, innovation will be primed through the AEZ system with all its scope, implications and ramifications. Currently, only oil and gas businesses have the capacity for robust geo-based analysis. To do this at the national level and in fine scale using agroecological parameters, the project will involve national professionals and foresees, among other elements, open-access WebGIS (based, among other tools, on Collect Earth) to produce specific/customized AEZ product to be used for direct use by AP/FFSs and for producing participatory and negotiated SLM plans, the implementation of which will translate into actions capable of containing the most important drivers behind land degradation across the target landscapes. The combination of these elements, along the development and deployment of SLM-specific financial mechanisms, is absolutely new and innovative in Angola.

The project strategy will also add a specific curricular layer of SLM based on the use of AEZ products to the AP/FFS approach, thereby imparting innovation within that specific tool. The same would apply to GreeNTD, which will in this project be able to deal with land use social agreements anchored in much more precise geographical referencing than its previous applications.

In regard to these and other innovative aspects of the project, see the following sections:

- Section 1.3.1 Supportive approaches and tools, where the multiple technical and methodological frameworks are discussed, in particular AEZ, AP/FFSs, GreeNTD and LDN.

- Section 1.1.2 Project intervention areas, where ‘scale considerations’ are made -- with respect to the application of spatial planning and decision-making tools – along with a discussion on “entry points” for managing landscapes or land uses for SLM and an explanation on the ‘nested approach’ to landscape level management.

- Sections Incremental/additional cost analysis and 1.3.4 The global environmental benefits, where the above is made more concrete and linked up to what the project will effectively deliver.

### 3.4.2 Potential for Scaling Up

Scaling up. The project proposes to develop a WebGIS Decision Support System for producing AEZ products (C1) and a mechanism for integrating such products in practical SLM (C2) while developing the availability of specific SLM finance. The AEZ system will be designed in a way that will enable its scaling up to a national scope as well as including further tools and functions. The articulation with the AEC in Chipipa (Huambo) is also to be extended post project to the other AECs in the provinces of Namibe, Cuando Cubando and Cabinda. The added focus on SLM to the AP/FFS approach will be replicable in other areas covered by AP/FFs and for which AEZ products may be customized. The “nested” character of this landscape approach will facilitate integration and scaling up across different geographical scales and administrative tiers. Finally, the application of specific SLM finance mechanisms will target the project focus areas but such mechanisms are also to be scaled up at national level by follow up initiatives.

Through linkages with other programs that use the AP/FFS approach, bringing common lessons learned and ideas for future development into an intensified dialogue with the government and other partners. Institutionalization at government level will enhance access to SLM, agroecology and other relevant themes by a larger number of communities.

## 3.5) DECENT RURAL EMPLOYMENT

In the context of rural Angola, it is traditionally women who take care of agriculture and it is they who contribute most to the household economy. The 2011 FAO Food and Agriculture State reported that 21.8 % of rural households in Angola were headed by women; and the most recent document of 2015, indicated a national value of 55.6%, regarding the participation of female agricultural labor force; and 79.4% for the participation of female laborers working in agriculture. The predominance of women in the family farming sector is widely recognized at all levels; however, this is not reflected in the presence of women in leadership positions at the various levels, from the positions and number of women among extensionists to the number of women presidents of associations and / or farmer cooperatives. This situation seems to be slowly changing with the introduction of the AP/FFS methodology, given that it encourages women take over positions with greater responsibility in AP/FFSs and farmers’ organizations.

The unemployment rate in 2014 was about 26% and reached about 46% in 2018. In August 2018, the Ministry of Public Administration, Labor and Social Security, with the support of the International Labor Organization, has drawn up the National Decent Employment Program, which is a first step towards an approach that is not brought tangible results in Angola.

It can also be considered that steps have been taken for decent employment in rural areas, especially with the promotion of associations and cooperatives to promote agricultural productivity, poverty reduction, more sustainable agricultural practices, and as such also a more dignified, stable and improved access to income from agriculture. The development of the AP/FFS methodology aims, to some extent, at these same goals.

Especially with young people, substantial migration to urban centers is causing the loss of human capital in rural areas. This migration process usually leads young people, who attempt to escape rural poverty, to find themselves in urban poverty, often obtaining undignified employment to survive in contexts where dependence on income is exacerbated.

This project adopts a human rights based approach, and this includes the right to Decent Rural Employment (DRE). This will guide the activities implemented under the project’s Components 2 and 3. It will particularly promote employment creation and enterprise development, while aligning to the other dimensions of DRE, including:

- Governance and social dialogue (support participation of community farmers in local decision-making about community land use through the GreeNTD methodology);

- Social protection (by promoting the long-term environmental and social sustainability of small-scale farming and improving social ties within and between communities); and

- Standards and rights at work (support socially responsible agricultural production, support in preventing and eliminating child labor by tackling its root causes, especially through the increase in productivity making household less dependent on child labor). Community and private businesses targeted by funding for promoting SLM will also have to respect such standards.

With the aim of curbing the rural exodus, FAO and UNICEF have a strategy to introduce methodological aspects of AP/FFSs in formal schools, particularly in rural areas, as a way to sensitize students to see agriculture as a desirable and viable source of income, not just as a source nutrition. For this type of strategy to work, however, and for desirable rural livelihoods to actually exist, the structural transformation of the Angolan rural economy must also take place.

## 3.6) GENDER EQUALITY

In the context of rural Angola, it is traditionally women who take care of agriculture and it is they who contribute most to the household economy. The 2011 FAO Food and Agriculture State reported that 21.8 % of rural households in Angola were headed by women; and the most recent document of 2015, indicated a national value of 55.6%, regarding the participation of female agricultural labor force; and 79.4% for the participation of female laborers working in agriculture. The predominance of women in the family farming sector is widely recognized at all levels; however, this is not reflected in the presence of women in leadership positions at the various levels, from the positions and number of women among extensionists to the number of women presidents of associations and / or farmer cooperatives. This situation seems to be slowly changing with the introduction of the AP/FFS methodology, given that it encourages women take over positions with greater responsibility in AP/FFSs and farmers’ organizations.

As gender equality is at the core of the proposed project and following the GEF Guidance to Advance Gender Equality document, a gender-sensitive approach and analysis were implemented during the PPG process and will continue to be enforced through project implementation as well. A particular attention should be given to the situation of women and the specific vulnerability of women-lead households in Angola.

According to World Bank data, in 2017 women represented almost 51% of Angola’s population, 53% of the population in rural households, nearly 58% of the employment in agriculture and in 2016, 34% of Angola’s households had a female head. Besides that, Angola has a high fertility rate, with 5.9 children per woman over the period of 2012-2015 and the literacy rates among female adults (15 and beyond) is 53%, while among man it reached 79.9% in 2014.The role of women in rural parts of Angola is fundamental for agriculture, as they are usually engaged in many agriculture activities, e.g. livestock grazing, raising small animals, fetching water, fuelwood, collecting medicinal plants, all of the while carrying for the young, elderly and sick. They are also bearers of the traditional knowledge. However, even though women tend to have a heavier work load, they have less leadership roles. It was just recently that the Jango (where deliberations and decisions take place) became more flexible and accepted the participation of women. Hence, any solution for the problems of the agricultural sector in Angola, especially the family farming, needs to have a gender-sensitive approach.

During local consultations carried out during the PPG process, of the 36 people from 17 different AP/FFSs consulted in the localities of Chongorói and Alto Hama, 10 were women. Specific working groups for women were organized, tendencies on gender responsibilities and roles were analyzed and the results were as follows:

- Women tend to have a bigger role in agricultural activities ranging from preparation of land to commercialization of production;

- On the working groups, it was noticed that women were more open and sensitive to environmental issues, e.g. selection of trees to be pruned, composting, etc.;

- Women tend to show more interest in management and work methodology issues, while men showed more interest in production issues.

Although gender equality has been given some attention in Angola – especially in the environment sector, where the current Minister and many of her senior management and technical team members are female – there is still an urgent need to increase women’s engagement in various levels of the socio-economic life, especially in rural regions of Angola. This implies taking gender issues into consideration and maintaining gender balance during the activities of the project’s Component 1 and 2 - while composing staff for both: agroecological unit and centers and for the FFS/APFS and noting that the evaluation of the FFS approach pointed out the need for more gender mainstreaming. This will be crucial to ensure that the direct and indirect benefits of SLM are equitably shared, including in terms of division of labor, new professional opportunities and in the provision of a supportive environment for working mothers.

During the PPG process, mechanisms, activities and indicators to assess and mainstream gender equality through the project were identified and will be considered every step of the way during the project’s implementation. In order to improve the socio-economic situation of rural women and families, the project will: i) ensure sustainability of land use and agricultural and pastoral production, and ii) reduce land degradation impacts among the most vulnerable social groups by making use of their traditional knowledge base to better cope with LD impacts, improving food security. Women are therefore expected to be especially involved in the project’s activities to ensure they will have their share in benefits of land rehabilitation.

### The Gender Action Plan

GENDER MARKING: The current project has been tagged as G2A (see cover page) – i.e. it “[...] addresses gender equality in a systematic way, but this is not one of its main objectives”.

Beyond the gender marking above, the following gender-responsive actions have been mainstreamed in the project and are herein highlighted:

Component 1: - The activity 1.2.3 foresees a Job-shadowing program, under which 2 out of 6 young professionals selected to participate will be women. Component 2: - Activities under outputs 2.1 to 2.3 will pay special attention to the gender dimension, making sure that women are present in a minimum ratio of 1:3 to the number of men. Output 2.1 - The territorial agreements reached through GreeNTD should reflect the careful consideration of how land use will affect the well-being of women, their rights and opportunities for social advancement. Output 2.1 - The implementation of the SLM plans will continue to pay special attention to the compliance with the collective agreements in regard to their possible effects on women and closely monitor if their practical implementation results in unanticipated negative effects on the general well-being of women and the distribution of resources and benefits across the gender divide. - The capacitation strategies at community-level will take into account the specificities of the roles of women within communities and be adapted to more responsive to their specific capacitation needs. Output 2.3 - At least 1/3 of the beneficiaries of the training program will be women; - The curriculum and pedagogical methods of the training program will take into account the specificities of the roles of women within communities, but also the need for gender equality in the roll out of both community-based and institutional training. Component 3: - The activity 3.1.4 will provide training in lobbying and advocacy, and 30% of the selected participants should be women; - The activity 3.2.3 and 3.2.4 will train professionals in fundraising and project design to tap into available funds / mechanisms, and 30% of the selected participants should be women; - The activity 3.3.6 relates to a training program on fund raising campaigns and will also have 30% of women among its selected participants; - Finally, activity 3.4.1 will focus on local micro entrepreneurs and will provide trainings on SLM opportunities and entrepreneurship, 30% of the participants will be women. Project’s Results Framework: - All of the indicators involving target population and number of trained people include a minimum gender-based target.

Table 22. Gender entry points for monitoring during project implementation

| # | Question | Answer | Comment |
| --- | --- | --- | --- |
| 1 | Does the project expect to include any gender-responsive measures to address gender gaps or promote gender equality and women’s empowerment? | Yes | Following a gender-sensitive analysis during the PPG process, gender-responsive measures were designed to increase women’s participation and leadership role in the agricultural sector, especially in family farming, and promote women’s empowerment through the project’s activities. |
| 2 | Which area(s) the project is expected to contribute to gender equality: | [as below:] | The project will be able to contribute to all three areas by creating specific opportunities for women to be part of the project’s activities and benefit from the project’s outcome. |
| 2a) | Closing gender gaps in access and control over natural resources | Yes |  |
| 2b) | Improving women’s participation and decision-making | Yes |  |
| 2c) | Generating socioeconomic benefits or services for women | Yes |  |
| 3 | Does the project’s results framework include gender-sensitive indicators? | Yes | Specific gender-sensitive indicators were included in the project’s Logical Framework in order to assess the project’s progress on promoting gender equality and improvements in women’s participation in decision-making process, as follows: - Several gender sensitive indicators were included in the Logical Framework, which has 20 indicators and 34 sub-indicators, or 54 in total. - Of the 20 indicators, 8 include include explicit gender disaggregation. - Of the 54 indicators and sub-indicators, 6 are not suitable for monitoring gender mainstreaming (e.g. they monitor number of hectares), leaving 48 indicators and sub-indicator where the gender can be potentially included. Among them, 21 include the gender aspect in one way or another. The above is a strong token of gender mainstreaming for a project tagged as “G2a” for its gender mark. |
|  | Source: GEF Guidance to Advance Gender Equality 2018. |  |  |

## 3.7) INDIGENOUS PEOPLES

The project’s geographical focus is on Central Angola, and more specifically on Huambo and Benguela Provinces. The project zone’s coverage is described in Section 1.1.2 Project intervention areas. The prioritized geographical focus for this project had favored the project strategy with respect to the potential for generating global environmental benefits. It also had implications for the PPG approach, not least also concerning indigenous peoples, plus any applicable safeguards in the context of stakeholder engagement. The prescribed screening of the project strategy and its stakeholder engagement approach was carried out, following the guidance currently adopted by FAO.

At PIF stage, it had been determined, on the basis of literature review containing authoritative data concerning indigenous people’s affairs, there are indeed indigenous peoples within the Angolan territory, and that these groups are a minority among the Angolan population -- especially to the extent that their cultural identity is distinct from the large majority of ethnic Bantu peoples, which comprise approximately 87% of the total population. It remained to be determined, at PPG stage, whether indigenous communities could possibly be found within the project areas, in which case applying Free, Prior and Informed Consent (FPIC), plus other socio-environmental safeguard measures would need to apply, when engaging with those groups and proposing their involvement in the project.

Early desk review drew information and data from International Working Group for Indigenous Affairs (IWGIA), a global organization, well-recognized by indigenous people as being able to provide reliable and culturally sensitive information and reports on indigenous affairs worldwide. IWGIA’s criteria for prioritizing and describing indigenous groups are in line with a broad international consensus on the matter, to which FAO adheres.  Other recommended sources of information were equally consulted, such as the ILO Convention 169 and relevant FAO publications.

According to IWGIA, the indigenous people in Angola include the San and the Himba, as well as other possible Khoe-San descendent groups. These populations are situated in Angola’s southern and southwest provinces and represent, as an estimate, 0.1% of the Angolan population. Also according to IWGIA, the San are found mainly in the southern provinces of Huila, Cunene, Cuando Cubango and Moxico. There was no confirmed reference in the mentioned IWGIA publication that groups of indigenous peoples may be present in Huambo and Benguela Provinces, except a single mention regarding the activities of a national social services NGO (Mbakita). Back in 2014, the mentioned NGO was reported by IWGIA to be active in different provinces, including Huambo, and implemented community programs on human rights, food security, preventive health care and education, information and communication. Yet, there was no information in the reference on the exact location for indigenous peoples’ groups in Huambo.

Further web-based research by the PPG Team did not yield significant information regarding the selected project demo landscapes and the possibility that indigenous people could be present in the project area, in light of its current focus on Central Angola, and on Huambo and Benguela more specifically. It did however yield the following:

- The ethnical map of Angola, originally by José Redinha and commonly used in several sources and is from 1960’/70’s. Facts about groups’ location should be carefully interpreted, since some ethnical traits are not clear and ethnical lines may have shifted during and since the war.

- IWGIA mentioned in its 2015 publication various Khosian groups as the ‘indigenous peoples of Angola’, but also a few minority Bantu groups, such as Himba, who are in turn linguistically close to and Herero. A WB source mentions groups of shepherds and agro-shepherds that inhabit the Central Plateau of Angola (the Ovambo, the Herero and the Nyaneka) and that they are “considered to be very conservative and reluctant to accept western culture”. Yet, this may not equate to self-identification, which is the most widely adopted tool or frame for asserting whether a group or tribe can be considered an ‘indigenous people’.

- Furthermore, it is possible that Ovambo and Herero groups are present in certain parts of Benguela, or that they at least use the rangelands for pastoral activities, perhaps also in Huambo, though less likely.

- According to IWGIA, the San groups may have been hunter-gatherers in the past, most now live from a combination of subsistence agriculture, informal manual work and food aid, although a number of significant traditional livelihood practices remain. These include gathering of bush foods and, in some cases, hunting and crafts.

To the extent that this project is will practice a Landscape Approach, it should consider important transformations brought about at landscape level by both historical and recent processes such as colonization, decolonization, armed conflict and post-conflict recovery. When a traditional group abandons their historical land-use patterns (e.g. hunting and gathering) and rapidly transition towards subsistence agriculture, this does not necessarily equate to an ‘intensification of land use’, which is a strategy commonly proposed for ensuring sustainability at the Wider Landscape level. Most likely, it is a token of increased competition for land.

Evidence from the Tracking Tool shows that at every step or new event, the pressure on natural resources has increased, along with competition for the land considered the most fertile. While natural land fertility can be objectively and easily measured from soil structure and composition, the SLM approach sees ‘land resources’ from a broader point of view. It focuses rather on ‘agro-ecosystem productivity’, which in turn stresses the importance of determining agroecological conditions before land uses can be prescribed.

In this light, the conflict resolution mechanisms foreseen under Component 2 in connection with the GreeNTD methodology should be put systematically into practice for pre-empting grievances from and improving the chances of achieving SLM goals.

During the PPG’s site level consultations, efforts were made to confirm the possible presence of indigenous peoples not only in the prospective demo landscapes, i.e. the communes of Alto Hama, Bailundo and Chongoroi, but also other neighboring areas. More specifically, during the meetings held with AP/FFS leaders and members, there was no representation or claims from groups or individuals who had self-declared themselves as ‘indigenous’. Neither were there any registered grievances in connection with the PPG process.

During PPG stage, FAO, the GoA and the PPG Team concluded that applying Free, Prior and Informed Consent (FPIC), plus other measures, when engaging with groups identified as indigenous peoples would not be required, to the extent that there is no confirmation on the presence of indigenous peoples in the ‘sites currently targeted by the project’ (herein considering the demo landscapes). The screening process carried out during the PPG is described in Table 23 below. More information on stakeholder consultations, including at site level are found in Appendix II.

Table 23. Screening for the need of FPIC during PPG and project implementation

| # | Modified screening questions concerning Indigenous People [*] | Screening |
| --- | --- | --- |
| 1 | Are there indigenous peoples in the country? [Note 1] | In the country, yes. According to International Working Group for Indigenous Affairs (IWGIA), a well-recognized global organization that provides reports on indigenous people worldwide, the indigenous people in Angola include the San and the Himba, as well as other possible Khoe-San descendent groups. These populations are situated in Angola’s southern and southwest provinces and represent 0.1% of the population. Else, authoritative information and analysis about indigenous peoples in Angola is generally scant and it may be at times biased. Cultural heritage (and gender) sensitivity was applied in all events relating to stakeholder consultation during the PPG stage. |
| 2 | Based on the stakeholder analysis, and considering possible existing agreements acknowledging their presence: Do indigenous peoples inhabit the project area(s)? [Y / N] | During PPG stage, FAO, the GoA and the PPG Team concluded that applying Free, Prior and Informed Consent (FPIC), plus other measures, when engaging with those groups would not be required, to the extent that there is no confirmation on the presence of indigenous peoples in the ‘sites currently targeted by the project’ (herein considering the demo landscapes). |
| 2a | . If yes, include disaggregated data by indigenous group and geographical location. | NA - see paragraph in this section with reference from IWGIA and further information in the cited publication. |
| 2b | . If not, explain whether project activities may impact (even indirectly) other territories inhabited by indigenous peoples. | There are no indications that project activities may directly or indirectly impact other territories inhabited by indigenous peoples. Yet, should new data prove otherwise during implementation, or should there be at least one grievance filed by an indigenous group regarding negative impacts, FAO will work with government to take measures, following the agency's and the GEF's guidance on the matter. Measures may include FAO experts advising the FAOAO Country Office and the project team for commending and conducting a specific impact analysis with focus on indigenous marginalized groups and their plight for territorial and other culturally bound rights vis-a-vis project planning, rolling stakeholder engagement, including gender and special groups, as well as specific socio-environmental risk assessment. |
| 3 | If applicable, has project design identified interventions which respond to the needs and priorities expressed by the indigenous communities involved and which build upon their knowledge, cultural systems and institutions. | Not applicable. In case it becomes applicable during implementation the prescribed measures will apply. |
| 4 | Has a plan to include indigenous peoples in the consultative process has been developed to ensure representatives of indigenous communities are present at all stages of the project cycle (including participation in the implementation of the project)? | Not applicable. In case it becomes applicable during implementation the prescribed measures will apply. |
| 5 | How has the information related to the project been disclosed? Has been in accordance with Indigenous Peoples’ customs and traditions and whether material has been distributed in the local language? | Not applicable. In case it becomes applicable during implementation the prescribed measures will apply. |
| 6 | As per international standards [Note 2], describe the process and current status of on-going/completed, legitimate consultations to obtain [Note 3] Free, Prior and Informed Consent (FPIC) with the indigenous communities [Note 4]. | Not applicable. In case it becomes applicable during implementation the prescribed measures will apply. |

| Table Notes |  |
| --- | --- |
| [*] | The questions above were derived from FAO's PRODOC template. |
| [1] | Including ILO Convention 169 (Indigenous and Tribal Peoples Convention, 1989), the UN Declaration on the Rights of Indigenous Peoples (2007), UNDG Guidelines on Indigenous Peoples’ Issues, the UN Permanent Forum on Indigenous Issues and the Inter-Agency Support Group on Indigenous Issues. |
| [2] | ILO Convention 169 (Indigenous and Tribal Peoples Convention, 1989), the UN Declaration on the Rights of Indigenous Peoples (2007), FAO policy on Indigenous and tribal Peoples. |
| [3] | Art 6 ILO Convention 169. “Legitimate consultation measures ensure that activities or actions planned respond to indigenous peoples’ concerns and interests, thereby allowing a self-determined development process”, p 5 FAO Policy on Indigenous and Tribal Peoples. |
| [4] | If and when needed, the FAO Officers supporting the project will guide the Project Implementation Team in the processes concerning FPIC. In the publication titled FAO (2016) mentioned further down, refer to its Annex I (“Suggested steps in the process of respecting FPIC”). |

In connection with the application of FAO’s Environmental and Social Risk Analysis, it became clear that obtaining FPIC in the framework of local level consultations for the current project, as proposed, would not be needed. Should it be needed during project implementation, useful and recent tools include the following FAO publications Governance of Tenure Technical Guide No. 3 FAO (2014) and Free Prior and Informed Consent. An indigenous peoples’ right and a good practice for local communities. Manual for Project Practitioners FAO (2016).

# APPENDICES (Standard FAO GEF)

## Appendix I) Logical Framework Matrix

To support strategic planning, the results matrix and the work plan and budget describe the entire chain of inputs, activities, outputs, outcomes and strategic goals. It provides an effective and transparent linkage between means and ends.

| Results Chain | Indicators | Baseline | Mid-term targets | End of Project Target | Means of Verification and Responsible Entity | Assumptions |
| --- | --- | --- | --- | --- | --- | --- |
| Project Objective: To reverse negative land degradation trends in selected landscapes in Central Angola by combining sustainable and rational approaches to planning, decision-making and land-use management with participatory approaches to build the capacity of local stakeholders | Indicator #1) Number of project beneficiaries, of which women: - 1a) Indirect beneficiaries in Wider Landscape (provincial level): /Huambo (rural communes only) /Benguela (no coastal municipalities only, rural communes) - 1b) Indirect beneficiaries in demo landscapes: rural population of selected communes: / Alto Hama (Londuimbali) / Bailundo (Bailundo) / Chongoroi (Chongoroi) - 1c) Direct beneficiaries in demo sites: population of selected communities served by AP/FFSs 1d) Direct beneficiaries of capacity building programs other than AP/FFS (including staff from extension services and public institutions, technicians, academics, decision makers and entrepreneurs) | 1a) /Huambo: 0 /Benguela: 0 1b) Demo landscapes: Communes of: / Alto Hama: 0 / Bailundo: 0 / Chongoroi: 0 - 1c) Demo sites: 0 out of 15 selected communities with a total population of approx. 2500 within demo landscapes 1d) A total of 115 individual stakeholders were engaged, of whom 26% are women | 1a) Approx.: /Huambo 1 million rural inhabitants, 52% women /Benguela 400 thousand rural pop., 52% women 1b) Demo landscapes: Communes of: / Alto Hama: 9165 / Bailundo: 0 / Chongoroi: 0 - 1c) Demo sites: 1250 of which 50% are women in 7 selected communities 1d) At least 200 individual stakeholders engaged by the project including 25% women as a minimum | 1a) Approx.: /Huambo 1 million rural inhabitants, 52% women /Benguela 400 thousand rural pop, 52% women 1b) Demo landscapes: Communes of: / Alto Hama: 9165 / Bailundo: 0 / Chongoroi: 0 - 1c) Demo sites: up to 1500 of which 50% are women in approximately 15 selected communities 1d) At least 300 individual stakeholders engaged by the project including 25% women as a minimum | Project reports Census data, projected and calculated to exclude urban and coastal communes Project stakeholder database - [the exact location and population of demo sites will be determined during project inception] | Population can be adequately assessed, in spite of the limitations of the 2014 Census. |
|  | Indicator #2) Area (ha) targeted by the project for the implementation of SLM frameworks and the integration of SLM into prevalent agricultural practices: - 2a) At the Wider Landscape’s (macro) level, development of a support mechanism for SLM: Approximate area coverage (in millions of ha) for the project’s a broad target for demonstrating the integration of AEZ into decision-making for SLM and LDN - 2b) Demo landscapes: Area within which integrated landscape management practices are adopted by local communities – assessed as the application of INRM practices in demo sites | 2a) 0 ha / No decision support system (DSS) support mechanisms for SLM in place, ‘The Wider Landscape’ is project’s broad target, designed to cover approx. 6.1 million hectares in Huambo and Benguela, and it contains 3 demo landscapes 2b) 0 ha of demo landscapes 2c) 0 ha of demo sites [the exact location and surface areas of demo sites will be determined during project inception] | 2a) 6.1 million ha coverage for ‘The Wider Landscape’ in Huambo and Benguela provinces / The AEZ system constitutes a nascent fine scale DSS and support mechanism for integrating SLM practices across landscapes and in multiple scales and entry points in the two provinces. 2b) Approx. 400,000 ha of 3 Demo landscapes are surveyed, with LDN indicators monitored and INRM practices initiated on the ground in: / Alto Hama 57,055 ha / Chongoroi 286,532 ha / Bailundo: 84,112 ha -------------------------------- Total: 409,699 ha Rounded-off to 400,000 ha for monitoring purposes. 2c) Estimated projections for demo sites: - 6,881 ha of agricultural lands - 7,800 ha of rangelands Total: up to 14,670 ha Considered as 11,000 ha as the mid-term target. | 2a) Within the Wider Landscape, the AEZ support mechanism is fully consolidated with the continued integration of SLM across landscapes, in multiple scales and entry points, including through FFSs/APFs and targeted capacity building of land use planners and local stakeholders. 2b) In approx. 400,000 ha of demo landscapes, the project has influenced planners, land users, local communities and investors to adopt and integrate SLM in landscape-level management practices and monitor LDN indicators through the application of a nested approach to AEZ. 2c) Up to 14,000 ha (in total and rounded down), where ‘Vegetative cover (natural & cultivated cover) is stabilized and regenerated at micro-landscape level (demo sites) managed through the project | Project reports including detailed cartography Data and knowledge generated by the AEZ system Census data | The area targeted by the project and the multi-tiered scale and nested approach to AEZ are well harmonized with the project’s limited (financial) scope, to the extent that it has been designed on the basis of detailed results from baseline capacity assessments. |
| Component 1) | Agroecological zoning (AEZ) integrated planning |  |  |  |  |  |
| Outcome 1.0) Improved national capacity for: (i) carrying out AEZ, (ii) monitoring land degradation at national scale and (iii) generating products of spatial analysis in formats useful for SLM | Indicator #3) Achievement of measures of institutional sustainability regarding national capacity for agroecological zoning (AEZ) and integrated planning by project end. The benchmarks will include the following: 3a) Capacity developed of CETAC’s staff members, including women, to conduct the work of the AEZ Unit [related to outputs 1.2 and the job shadowing activities, and output 1.5 on the broader institutional training and networking.] 3b) Post-project management modality worked out 3c) Number of partnerships developed 3d) Services of the AEZ Unit delivered for other projects / initiatives 3e) Number of people trained in the AEC Chipipa in collaboration with the ICE-SLM project, among them % of women who meet same qualifications criteria as men for selection 3f) Number and profile of the users of the AEZ system (gender disaggregated, if possible, to anonymously collect data on it) |  |  |  | Project reports, including on training, dialogues, events and requests for services directed to the AEZ unit | CETAC’s capacity can be improved as a result of the project. |
| Outputs under Component 1 | 1.1; AEZ Unit: A service-oriented national data analysis and technical unit dedicated to agroecological zoning (AEZ) and LDN-related geospatial analysis is created at CETAC. 1.2; AEZ Services: CETAC is progressively capacitated to (i) serve as a hub for AEZ experts, including by leveraging at least 2 strategic partnerships, and (ii) maintain the provision of AEZ services to at least 3 national entities/clients beyond the project’s lifetime. 1.3; LDN monitoring: AEZ Unit provides services on monitoring of land degradation and of ecosystem services within an area of 6.1 M ha i.e. the project’s Wider Landscape. 1.4; AEZ System: The AEZ-based fine-scale WebGIS decision support system (DSS) for SLM, LD and ecosystem services monitoring is developed, covering 6.1 M ha (the Wider Landscape), providing relevant products and creating a framework for the project’s national up-scaling. 1.5; A two-way hub is set up for (i) collecting AEZ data and (ii) generating AEZ products through WebGIS DSS platform. |
| Outputs 1.1) AEZ Unit: A service-oriented national data analysis and technical unit dedicated to agroecological zoning (AEZ) and LDN-related geospatial analysis is created at CETAC | Indicator #4) Benchmarks for the establishment of the AEZ Unit within CETAC: 4a) Maintenance of an AEZ Unit, i.e. a team of professionals working on AEZ, including women 4b) Maintenance of the Project’s Wider Landscape as the AEZ Unit’ geographical scope 4c) Post-project management modality worked out | There is no AEZ Unit within CETAC. 4a) No Unit exists 4b) No Unit exists 4c) Post project management modality considered in the PRODOC, but no concrete steps to implement what is proposed have been taken. | AEZ Unit is becoming progressively more operational and meets the following benchmarks by the project’s mid-term: 4a) A team of professionals has been formed forming with at least 2 women as a part of the Team and further 2 recruited as trainees 4b) The scope for the project’s Wider Landscape is maintained. 4c) The management modality for the post-project period has been discussed by relevant stakeholders in preparation for, and in the aftermath of, the MRT. | AEZ Unit is fully operational and meets the following benchmarks by project end: 4a) 6 people from amongst CETAC's staff are fully trained for handover of the AEZ Unit as proved by the CNA, of which at least 2 women 4b) The AEZ unit has least maintained the project’s Wider Landscape as the AEZ Unit’ geographical scope 4c) Post-project management modality successfully developed, including by taking specific MTR recommendations into consideration (achievement to be verified by the terminal evaluation). | Mid-term review and final evaluation | The Unit will be established according to the project’s schedule without major delays. |
| Output 1.2) AEZ Services: CETAC is progressively capacitated to (i) serve as a hub for AEZ experts, including by leveraging at least 2 strategic partnerships, and (ii) maintain the provision of AEZ services to at least 3 national entities/clients beyond the project’s lifetime | Indicator #5) Benchmarks for the capacity of the AEZ Unit within CETAC to provide AEZ services 5a) Capacity developed of CETAC’s staff members, including women, to conduct the work of the AEZ Unit [related to outputs 1.2 and the job shadowing activities, and output 1.5 on the broader institutional training and networking.] 5b) Extent of the Unit’s ability to function in a nationwide network hub for professionals engaged in AEZ related subjects | 5a) 0 people trained 5b) No AEZ network exists in Angola creating the opportunity for learning about AEZ as applied to Angola | 5a) 6 selected staff members, including at least 2 women, are fully involved in the job shadowing training and the Unit is commencing preparations for handover at project end as proved by the CNA 5b) The internet platform for networking professionals interested in AEZ has been launched by the AEZ Unit | 5a) 6 people, 2 women among them from amongst CETAC's staff are fully trained for handover of the Unit as proved by the CNA 5b) The AEZ network is actively being used by professionals engaged in AEZ related subjects and the AEZ Unit at CETAC is the national reference for learning about AEZ | Project reports, including on training, dialogues, events and requests for services directed to the AEZ unit CNA Study Verification of the activity /traffic of the online AEZ platform | CETAC’s capacity can be improved as a result of the project. Angolan professionals engaged in GIS and AEZ related subjects will be interest in being networked as to benefit from and contribute to the activities of AEZ Unit at CETAC. |
| Output 1.3) LDN monitoring: AEZ Unit provides services on monitoring of land degradation and of ecosystem services within an area of 6.1 M ha i.e. the project’s Wider Landscape | Indicator #6) AEZ Unit’s capacity to effectively monitor land degradation parameters, ecosystem services and other agro-ecological data 6a) Functioning and coverage of the AEZ Unit monitoring system 6b) Number of partnerships for the networked sharing and monitoring of AEZ and LDN-relevant data developed with national institutions (including INAMET, IGCA and GSA) and academia (FCA and IIA) | 6a) Land degradation parameters and ecosystem services baseline established through the Tracking Tool but it is mostly a desk-based (not ground-truthed) 6b) No partnerships exist | Note: LDN specific indicators to be monitored through Indicator #8 6a) Land degradation parameters (including those relevant to the LDN specific targets) and ecosystem services are monitored, at a reasonably fine-scale, within demo landscapes by the project’s mid-term 6b) At least 3 partnerships secured, of which at least 1 is with academia | Note: LDN specific indicators to be monitored through Indicator #8 6a) Land degradation parameters (including those relevant to the LDN specific targets) and the most important ecosystem services are monitored, in fine-scale, within project’s Wider Landscape and medium scale at national level by project end 6b) At least 5 partnerships secured, of which at least 2 are with academia | Project reports including detailed cartography Data and knowledge generated by the AEZ system | The AEZ unit will be able to develop a reasonably robust fine-scale AEZ system during the project’s duration. |
| Output 1.4) AEZ System: The AEZ-based fine-scale WebGIS decision support system (DSS) for SLM, LD and ecosystem services monitoring is developed, covering 6.1 M ha (the Wider Landscape), providing relevant products and creating a framework for the project’s national up-scaling | Indicator #7) Development of the Web GIS DSS of the CETAC’s AEZ Unit | No DSS in place | WebGIS DSS established: [interim sub-indicators] 7a) is fully operational 7b) is approved by users, with female users' perspective duly mainstreamed, and 7c) its products are proved to successfully provide decision-support to at least 4 clients/beneficiaries [Precise metrics and benchmarks to be informed by the user survey, which will be gender-disaggregated as applicable] | WebGIS DSS covers entire Wider Landscape and constitutes a model at the national scale with a large enough community of users, including women [Final metrics and benchmarks to be informed by the user survey] | Results from the ‘User Survey’ foreseen in Activity 1.5.1, validated by MTR and TE | User perspective is important in the development of the Web GIS DSS of CETAC’s AEZ Unit. |
| Component 2) | Sustainable management and rehabilitation of landscapes |  |  |  |  |  |
| Outcome 2.0) Selected rural communities, supported by SLM-trained extension workers through active AP/FFSs, collaborate to promote agroecological approaches, including participatory land use decision-making, in at least 400,000 ha of multi-use demo-landscapes | Indicator #8) Number of ha, where the general LDN goal of “achieving neutral land degradation by 2030 compared to degradation levels for 2015” is achieved by project end. The project will seek to demonstrate the effectiveness of AEZ-based SLM for achieving LDN and the and specific targets of the LDN-TSP within a shorter time span. The specific LDN targets that apply to the demo landscapes is the following: 8a) Reduction of marked land degradation by around 50% compared to the reference year (2015) for land where agriculture is currently practiced; 8b) Restoration of 50% of ecosystems currently degraded by unsustainable land use practices; 8c) 30% increase of soil organic carbon content (SOC) in all land classes and halving (0.4%) the current rate of deforestation throughout the country; 8d) Reinforcing information, education and awareness-raising on good land-use practices including those linked to sustainable agriculture-conservation for 80% of rural households; 8e) Reduction of 25% of livestock in areas with a strong tradition of livestock production; 8f) Reduction of greenhouse gas emissions by 50%. |  |  |  | Project reports including detailed cartography | Through AEZ on the ground and the application of agroecological intensification SLM techniques within demo sites, pressures on natural resources can be at least attenuated, if not outright reduced within the project’s timeframe. |
| Outputs under Component 2 | 2.1; SLM plans: Community-level land-use plans integrating AEZ and SLM are prepared through a participatory approach (GreeNTD) in three municipalities as part of a nested approach to landscape-level management. 2.2; A network of AP/FFSs (Agro-Pastoral and Farmer Field Schools) in three municipalities is supported in implementing SLM plans and promoting SLM practices. 2.3; A broad training program focused on SLM and the use of AEZ products for supporting decision-making at community-level is institutionalized and delivered. |
| Output 2.1) SLM plans: Community-level land-use plans integrating AEZ and SLM are prepared through a participatory approach (GreeNTD) in three municipalities as part of a nested approach to landscape-level management | Indicator #9) Local SLM plans developed with the project’s assistance in the three municipalities targeted by the project, evidenced by: 9a) Number of plans developed 9b) Number of people involved in preparation of the plans, of which how many are women 9c) Number of communities involved in development of plans | 9a) 0 plans 9b) 0 people 9c) 0 communities | 9a) 4 plans 9b) 200 people, 40% women 9c) 5-6 communities | 9a) 8 to 10 plans 9b) At least 450 people, 40% women 9c) Approximately 15 communities | Project reports, including on training, dialogues, events and requests for services directed to the AEZ unit | Spatial planning services are in demand by local governments and communities, so SLM plans can have an entry point, in particularly in Central Angola. |
| Output 2.2) A network of AP/FFSs (Agro-Pastoral and Farmer Field Schools) in three municipalities is supported in implementing SLM plans and promoting SLM practices | Indicator #10) Qualitative assessments of integration of the SLM plans with decision making in the three municipalities targeted by the project, evidenced by: 10a) Levels of integration of SLM into the activities of the AP/FFSs 10b) The extent to which SLM plans inform land-use allocation and management [Appropriate benchmarking to developed during inception.] | 10a) AP/FFS currently include SLM-relate topics, but not based on AEZ products and not in a systematic manner 10b) SLM plans in Angola do not currently exist | 10a) The activities of AP/FFS place strong emphasis on SLM based on AEZ products and on the 4 SLM plans that will exist by project midterm. 10b) At least 4 land-use plans will be available for informing decision-making and in the communities where they do exist, they will be used as a normative basis for decision-making | 10a) The activities of AP/FFS place strong emphasis on SLM based on AEZ products and on the 10 SLM plans that will exist by project midterm. 10b) 8 to 10 land-use plans will be available for informing decision-making and in the communities where they do exist, they will be used as a normative basis for decision-making | Reporting by the national SLM consultants and extension services Assessment of the specified LD indicators will done thought the monitoring mechanism of the AEZ system | Extension services working with AP/FFSs and respective communities will be receptive to adopting new tools and work methods. The project will seek to demonstrate the effectiveness of AEZ-based SLM for achieving LDN within a shorter time span |
| Output 2.3) A broad training program focused on SLM and the use of AEZ products for supporting decision-making at community-level is institutionalized and delivered | Indicator #11) SLM training program implemented: 11a) Number and type of community stakeholders trained, including a minimum number of women 11b) Effectiveness of SLM community training and capacity building interventions, as assessed by participants through survey(s), which will be gender disaggregated as applicable | 11a) 0 beneficiaries 11b) NA - assessment not yet carried out | 11a) At least 50 training participants by mid-term, of the following affiliation: civil servants, AP/FFS master trainers, EDA / IDA technician, municipal technicians, of whom at least 20% women 11b) Survey(s) designed and baseline assessed | 11a) At least 100 training participants by mid-term, of the following affiliation: civil servants, AP/FFS master trainers, EDA / IDA technician, municipal technicians, of whom at least 20% women 11b) Capacity successfully improved, including by mainstreaming gender aspects through user feedback to be informed by the (gender disaggregated) participants' survey | Project reports, including on training, dialogues, events and requests for services directed to the AEZ unit Training surveys at project inception, mid-term and project end | Training community stakeholders is an effective way of increasing the chances of community members to adopt SLM. |
| Component 3) | Economic and financial leverage approaches to SLM |  |  |  |  |  |
| Outcome 3.0) Increased availability of funding for, and investments in, land restoration / rehabilitation in Angola | Indicator #12) Increase in overall investment (both public and private funds) mobilized for SLM Key target benchmark: Key-decision makers have a solid understanding of how to bring financial leverage and scale to SLM initiatives, resulting in the active mobilization and deployment of investment at both landscape and community level. [From Tracking tool, GEF Outcome Monitoring concerning LD1 and LD3, item [iii.] Increased investments in integrated landscape management, measured as ‘Increased resources flowing to INRM and other land uses form diverse sources’] $4.8 million per year (2016/2017 GoA expenditure with SLM - base year 2016 – to be confirmed/updated at inception) |  |  |  | Project reports, including on training, dialogues, events and requests for services directed to the AEZ unit Information on governmental spending per sector and program | The project will be able to influence financing for SLM among institutional stakeholders. |
| Outputs under Component 3 | 3.1; Economic analyses on the cost of land degradation in Huambo and Benguela Provinces are carried out and disseminated among key decision makers to bring financial leverage and scale to the actions needed for restoring/rehabilitating land in central Angola. 3.2; Mainstream and innovative finance options for SLM are assessed, explored/probed and enabling action is undertaken to operationalize them in the targeted municipalities with fundraising campaigns are organized, and projects are formulated to mobilize funds. 3.3; Community-based SLM finance, public-private partnerships and targeted matching grants are designed and implemented to channel funds from various funding sources. |
| Output 3.1) Economic analyses on the cost of land degradation in Huambo and Benguela Provinces are carried out and disseminated among key decision makers to bring financial leverage and scale to the actions needed for restoring/rehabilitating land in central Angola | Indicator #13) Degree and coverage of assessment of economic cost of LD Indicator #14) Number of professionals from MINAMB, MINAGRIF, MINTURI and relevant NGOs trained in lobbying and advocacy for SLM funding, including a minimum number of women | 13) No assessment in place 14) 0 professionals trained in lobbying and advocacy for SLM funding | 13) The framework and methodology for the assessment is developed and has been applied to the 3 demo landscapes 14) 50 professionals from MINAMB, MINAGRIF, MINTURI and relevant NGOs, among them at least 20% are women, trained in lobbying and advocacy for SLM funding | 13) Assessment of LD costs conducted, and monitoring activities enabled, with a completed assessment of the wider landscape. 14) 100 professionals from MINAMB, MINAGRIF, MINTURI and relevant NGOs, among them at least 20% are women, trained in lobbying and advocacy for SLM funding | Project reports, including on training, dialogues, events and requests for services directed to the AEZ unit | There is reliable data in Angola for conducting an economic assessment of land degradation, its impacts and economic implications. |
| Output 3.2) Mainstream and innovative finance options for SLM are assessed, explored/probed and enabling action is undertaken to operationalize them in the targeted municipalities with fundraising campaigns are organized, and projects are formulated to mobilize funds | Indicator #15) Number of professionals from relevant entities (in particular in MINAMB, MINAGRIF, MINTURI and relevant NGOs) trained in fundraising and resource mobilization for SLM in, including a minimum number of women Indicator #16) Number of supported projects to pilot and adjust the funding mechanisms for SLM Indicator #17) Increases in public funds mobilized for SLM (state budget earmarked for SLM) | 15) Approx. 5 professionals MINAMB (but not in other entities), including 1 woman (i.e. 20%) have received some training in fundraising and resource mobilization for environmental projects – e.g. GEF consultation workshops and other similar events (but not SLM specific) 16) 0 projects supported with SLM specific finance mechanisms 17) $4.8 million per year (2016/2017 GoA expenditure with SLM - base year 2016 – to be confirmed/updated at inception) [refer to note in item #1 in Table 5 or an explanation on the baseline.] | 15) Approx. 50 professionals from MINAMB, MINAGRIF, MINTURI, plus 2-3 relevant NGOs, among them at least 20% are women, have received focused training in fundraising and resource mobilization for SLM 16) 5 projects supported with SLM specific finance mechanisms 17) In average, $5.0 million per year from various sources, or at least a 5% increase vis-à-vis baseline, in case the baseline is updated. | 15) Approx. 100 professionals from MINAMB, MINAGRIF, MINTURI and at least 5 relevant NGOs, among them 20% women, have received focused training in fundraising and resource mobilization for SLM 16) 10 projects supported with SLM specific finance mechanisms 17) In average, $5.3 million per year, or at least a 10% increase vis-à-vis baseline, in case the baseline is updated. | Project reports, including on training, dialogues, events Information on governmental spending per sector and program Training and user surveys at project inception, mid-term and project end | Public awareness, focused education and other related activities will help raise awareness of the importance of SLM in particular if carried out in synergy with related and baseline initiatives. The project will be able to influence financing for SLM among institutional stakeholders. |
| Output 3.3) Community-based SLM finance, public-private partnerships and targeted matching grants are designed and implemented to channel funds from various funding sources | Indicator #18) Operational status of a trust fund for community-based SLM projects is in place with solid governance mechanisms and institutional support Indicator #19) Number of SLM community based projects to have received financial technical assistance or funding through the trust fund (which includes financial technical assistance) Indicator #20) Number of local stakeholders benefitting from finance options for SLM, including a minimum number of female memberships | 18) No trust-fund for community-based SLM exists 19) Number of SLM community based projects have received /fin. technical assistance: 0 /funding via trust fund: 0 20) Approx. 40 institutional stakeholders (at PPG stage), of whom 28% are women | 18) The trust fund for SLM, whose framework, statutes and governance structure of the trust fund for community-based SLM projects have been defined, has strong institutional support and is ready to be deployed 19) Number of SLM community based projects have received /fin. technical assistance: 5 /funding via trust fund: 0 20) Approx. 300 local stakeholders at demo landscapes level, of whom 40% are women | 18) The SLM trust fund will have met its benchmark for the end of the project’s duration, supporting at least 20 community-based SLM projects 19) Number of SLM community based projects have received /fin. technical assistance: 20 /funding via trust fund: 20 20) Approx. 700 local stakeholders at demo landscapes level, of whom 40% are women | Project reports, including on training, dialogues, events Information on governmental and donor spending per sector and synergistic rural development program | It is possible to facilitate access to finance to local farmers in Angola, in particular if this is pursued in synergy with related and baseline initiatives. |

## Appendix II) Stakeholder Engagement Matrix

### 1) Stakeholder Consultation

| Stakeholder Name | Stakeholder Type | Stakeholder profile | Consultation Methodology | Consultation Findings | Expected timing (for Stakeholder Engagement Plans Only) | Comments |
| --- | --- | --- | --- | --- | --- | --- |
| Farmer Field Schools and Agro-Pastoral Field Schools (FFS/APFS) | Direct Beneficiary | Local community | Face-to-face meetings | 18 FFS/APFS were consulted during the PPG process, a total of 32 members, of which 8 were women, were interviewed and participated in gender-based working groups. | From PY2 onwards for the implementation of C2 |  |
| Ministry of Environment (MINAMB) | Direct Beneficiary | National Government Institution body | Face-to-face meetings PGG inception and validation workshops |  | Chairs the PCS from the outset | Participation of IDA/EDAs is essential |
| CETAC | Direct Beneficiary | National Government Institution body | Face-to-face meetings PGG inception and validation workshops | The project will be very important for the institution to develop its strategic thinking and infrastructure | From the onset as key hosting institution and partner for activities under C1 and C2. | Co-financer and LoA |
| Provincial Authorities | Indirect Beneficiary | National Government Institution/body | Face-to-face meetings PGG inception and validation workshops | Local Government Institution/body | Part of PSC |  |
| Municipal Authorities | Direct Beneficiary | Local Government Institution/body | Not consulted during PPG |  | From PY2 onwards for the implementation of C2 | Final shortlist of municipalities was produced based on the baseline assessment, but after PPG consultations took place. |
| Ministry of Agriculture and Forests | Indirect Beneficiary | National Government Institution body | Face-to-face meetings PGG inception and validation workshops | GSA recognizes the importance of centralizing shared information and is receptive to establishing partnerships for this purpose | Part of the PCS from the outset Proposed partnership with GSA foreseen for the 2nd or 3rd quarter of the project | EDA/IDA |
| Non-Governmental Organizations | Partner | Resource Partner/Donor | Face-to-face meetings PGG inception workshop |  |  |  |
| Foreign Embassies | Partner | Resource Partner/Donor | Face-to-face meetings PGG inception workshops | Some foreign embassies have initiatives and projects in the field of agriculture that could open space for partnerships with the project | Engagement foreseen during the implementation of C3 activities | Dutch Embassy to be engaged as a potential donor of funds under SLM finance of C3 |
| Universities | Partner | Resource Partner/Donor | Face-to-face meetings PGG inception and validation workshops | Both FCA and IIA have staff with relevant expertise for the project and are receptive to establishing partnerships. | Proposed LoAs foreseen for the 1st or 2nd quarter of the project |  |
| Other Ministries (Urbanism, Economy, Natural Resources) | Partner | National Government Institution body | Face-to-face meetings PGG inception and validation workshops | INAMET and IGCA recognize the importance of centralizing shared information and are receptive to establishing partnerships for this purpose. | Proposed partnerships with INAMET and IGCA foreseen for the 2nd or 3nd quarter of the project INOTU will be engaged for the implementation of C2 from PY2 onwards |  |
| African Development Bank | Partner | Resource Partner/Donor |  | The AfDB is completing the approval process for a project regarding SLM, which could be close aligned with the project |  |  |

### 2) Grievance Mechanism

| Focal Point Information |  |
| --- | --- |
| Contact Details |  |
| Explain how the grievance mechanism has been communicated to stakeholders |  |

### 3) Disclosure (currently not applicable)

| Disclosure Means |  |  |
| --- | --- | --- |
| Disclosure information/document shared |  |  |
| Disclosure dates | From: Click here to enter a date. | To: Click here to enter a date. |
| Location |  |  |
| Language(s) |  |  |
| Other Info |  |  |

## Appendix III) Work Plan

[Last updated on 29 Dec 2018]

| (work plan index) | Outcomes, Outputs and Indicative Activities | Resp. Entity Workplan & Budget (indicatively) | Y1 Q4 | Y2 Q1 | Y2 Q2 | Y2 Q3 | Y2 Q4 | Y3 Q1 | Y3 Q2 | Y3 Q3 | Y3 Q4 | Y4 Q1 | Y4 Q2 | Y4 Q3 | Y4 Q4 | Y5 Q1 | Y5 Q2 | Y5 Q3 | Y5 Q4 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | PROJECT START-UP | FAO / PMU |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2 | Activity 0.1) Advertise key positions (coordinator and support staff) – activate PMU | FAO / PMU | 1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3 | Activity 0.2) Hiring of staff | FAO / PMU | 1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 4 | Activity 0.3) Activate office space at CETAC | FAO / PMU | 1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 5 | Activity 0.4) Communication to all key stakeholders of project start up | FAO / PMU | 1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 6 | Activity 0.5) Procurement of main equipment | FAO / PMU | 1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 7 | Activity 0.6) Team detailed planning – team building and logframe review | FAO / PMU | 1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 8 | Activity 0.7) National Inception workshop | FAO / PMU |  | 1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 9 | Activity 0.8) Local level inception workshops | FAO / PMU |  | 1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 10 | Activity 0.9) Negotiation of details of exit/sustainability strategy, review and monitoring of institutional agreements | FAO / PMU | 1 | 1 |  | 1 |  |  |  | 1 | 1 |  |  | 1 |  | 1 | 1 | 1 | 1 |
| 11 | Activity 0.10) Administrative closure | FAO / PMU |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 1 | 1 |  |
| 12 | Outcome 1.0) Improved national capacity for: (i) carrying out AEZ, (ii) monitoring land degradation at national scale and (iii) generating products of spatial analysis in formats useful for SLM |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 12 | Activities 1.0.X) General Component 1 Activities: Agro-ecological zoning (AEZ) integrated planning, Rolling activity for 1.1. and 1.3. - managed internally by the unit. | PMU / AEZ Unit | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |
| 13 | Output 1.1) AEZ Unit: A service-oriented national data analysis and technical unit dedicated to agroecological zoning (AEZ) and other related geospatial analysis is created at CETAC | PMU / AEZ Unit |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 14 | Activity 1.1.1.) Signing Letter of Agreement (LoA) with CETAC regarding the use of facilities for hosting the AEZ Unit during project implementation and coordination of general activities, especially those involving CETAC’s staff | PMU / AEZ Unit | 1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 15 | Activity 1.1.2.) Structuring the technical team of the AEZ Unit | PMU / AEZ Unit | 1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 16 | Activity 1.1.3.) Hardware and software CNA and purchase | PMU / AEZ Unit | 1 | 1 |  |  |  |  | 1 |  |  |  |  | 1 |  |  |  |  |  |
| 17 | Activity 1.1.4.) Drafting a plan for data collection - Rolling and joint activity for both Output 1.1 (1.1.4 to 1.1.7) and Output 1.3 (1.3.5 to 1.3.8) - managed internally by the unit1.1. and 1.3. - managed internally by the unit | PMU / AEZ Unit |  | 1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 18 | Activity 1.1.5.) Data harvesting, including collection of ground-truth data, field surveys - Rolling and joint activity for both Output 1.1 (1.1.4 to 1.1.7) and Output 1.3 (1.3.5 to 1.3.8) - managed internally by the unit1.1. and 1.3. - managed internally by the unit | PMU / AEZ Unit |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |
| 19 | Activity 1.1.6.) Data fitness evaluations and data uploading - Rolling and joint activity for both Output 1.1 (1.1.4 to 1.1.7) and Output 1.3 (1.3.5 to 1.3.8) - managed internally by the unit1.1. and 1.3. - managed internally by the unit | PMU / AEZ Unit |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |
| 20 | Activity 1.1.7.) Preparation of guidelines to be generated from WebGIS DSS - Joint activity for both Output 1.1 (1.1.4 to 1.1.7) and Output 1.3 (1.3.5 to 1.3.8) - managed internally by the unit | PMU / AEZ Unit |  |  | 1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 21 | Output 1.2) AEZ Services: CETAC is progressively capacitated to (i) serve as a hub for AEZ experts, including by leveraging at least 2 strategic partnerships, and (ii) maintain the provision of AEZ services to at least 3 national entities/clients beyond the project’s lifetime | AEZ Unit / AEC (GABAC) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 22 | Activity 1.2.1.) Signing Letter of Agreement (LOA) with Instituto de Investigação Agronómica (IIA) regarding the participation of IIA staff in Outputs 1.2, 1,3, 1.4, 1.5, 2.1, 2.2, 2.3 | AEZ Unit / AEC (GABAC) |  | 1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 23 | Activity 1.2.1.) Signing Letter of Agreement (LOA) with Faculdade de Ciências Agrárias (FCA) regarding the participation of FCA staff in Outputs 1.2, 1,3, 1.4, 1.5, 2.1, 2.2, 2.3 | PMU / AEZ Unit |  | 1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 24 | Activity 1.2.3.) Job shadowing program engaging trainees and CETAC’s appointed staff members (learning-by-doing) | PMU / AEZ Unit |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |
| 25 | Activity 1.2.2.) Creating and maintaining a network of professionals involved in AEZ and environmental monitoring at national level in which CETAC plays a centralized role as a national hub, rolling outreach on a continuous basis. | AEZ Unit / AEC (GABAC) |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |
| 26 | Activity 1.2.3.) Designing and implementing a training program to be progressively implemented by the experts of the Unit to their counterparts, members of CETAC's staff | PMU / AEZ Unit |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  |  |  |  |  |  |  |
| 27 | Output 1.3) LDN monitoring: AEZ Unit provides services on monitoring of land degradation and of ecosystem services within an area of 6.1 M ha i.e. the project’s Wider Landscape | AEZ Unit / AEC (GABAC) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 28 | Activity 1.3.1.) Signing Letter of Agreement (LOA) with IGCA regarding the sharing of information relative to mapping and cadaster, including data from the ongoing land tenure registration process (Outputs 1.2, 1,3, 1.4) and development of common products through institutional collaboration | AEZ Unit / AEC (GABAC) |  | 1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 29 | Activity 1.3.2.) Signing Letter of Agreement (LOA) with INAMET regarding sharing of information and the coordination of environmental monitoring activities, and more specifically on the following study topics: (a) Spatiotemporal assessment of Land Degradation; and (b) Monitoring of other LD-related measures (Outputs 1.2, 1,3, 1.4). | AEZ Unit / AEC (GABAC) |  | 1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 30 | Activity 1.3.3.) Signing Letter of Agreement (LOA) with GSA for cooperation in environmental monitoring and monitoring the impact of SLM on farmer’s incomes (Outputs 1.2, 1,3, 1.4) | AEZ Unit / AEC (GABAC) |  | 1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 31 | Activity 1.3.4.) Spatiotemporal assessment and monitoring of land degradation carried out (collaboration frameworks, timing and scope to be confirmed during or post inception) | AEZ Unit / AEC (GABAC) |  |  | 1 | 1 | 1 |  |  |  |  |  |  |  |  |  |  |  |  |
| 32 | Activity 1.3.5.) Drafting a plan for data collection - Rolling and joint activity for both Output 1.1 (1.1.4 to 1.1.7) and Output 1.3 (1.3.5 to 1.3.8) - managed internally by the unit. | AEZ Unit / AEC (GABAC) |  | 1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 33 | Activity 1.3.6.) Data harvesting, including collection of ground-truth data, field surveys - Rolling and joint activity for both Output 1.1 (1.1.4 to 1.1.7) and Output 1.3 (1.3.5 to 1.3.8) - managed internally by the unit. | AEZ Unit / AEC (GABAC) |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |
| 34 | Activity 1.3.7.) Data fitness evaluations and data uploading - Rolling and joint activity for both Output 1.1 (1.1.4 to 1.1.7) and Output 1.3 (1.3.5 to 1.3.8) - managed internally by the unit | AEZ Unit / AEC (GABAC) |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |
| 35 | Activity 1.3.8.) Preparation of guidelines to be generated from WebGIS DSS - Joint activity for both Output 1.1 (1.1.4 to 1.1.7) and Output 1.3 (1.3.5 to 1.3.8) - managed internally by the unit. | AEZ Unit |  |  | 1 | 1 | 1 |  |  |  |  |  |  |  |  |  |  |  |  |
| 36 | Output 1.4) AEZ System: The AEZ-based fine-scale WebGIS decision support system (DSS) for SLM, LD and ecosystem services monitoring is developed, covering 6.1 M ha (the Wider Landscape), providing relevant products and creating a framework for the project’s national up-scaling | AEZ Unit |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 37 | Activity 1.4.1.) WebGIS DSS system development. Critical input by the Computer Scientist / ITC Programmer Analyst | AEZ Unit |  | 1 | 1 | 1 |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 38 | Activity 1.4.2.) Geocatalog development - Critical input by the Computer Scientist / ITC Programmer Analyst | AEZ Unit |  |  |  | 1 |  |  |  |  |  |  |  |  |  | 1 |  |  |  |
| 39 | Activity 1.4.3.) CMS setup - Critical input by the Computer Scientist / ITC Programmer Analyst | AEZ Unit |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  |
| 40 | Activity 1.4.4.) User surveys (y1, y2, y3, y4) - Under the supervision of the Computer Scientist / ITC Programmer Analyst | AEZ Unit |  |  |  |  | 1 |  |  | 1 |  |  |  | 1 |  |  | 1 |  |  |
| 41 | Activity 1.4.5.) Development of e-inclusion strategy and training program - Critical input by the Computer Scientist / ITC Programmer Analyst | AEZ Unit |  |  |  | 1 |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 42 | Output 1.5) A two-way hub is set up for (i) collecting AEZ data and (ii) generating AEZ products through WebGIS DSS platform | AEZ Unit / AEC (GABAC) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 43 | Activity 1.5.1.) Designing and implementing a training program dedicated to: 1) data collection techniques 2) using products of WebGIS DSS and other related topics, to be progressively delivered to AEC in Chipipa in collaboration with ICE SLM project | AEZ Unit / AEC (GABAC) |  | 1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 44 | Activity 1.5.2.) Designing protocols for data collection and exchange | AEZ Unit / AEC (GABAC) |  | 1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 45 | Outcome 2.0) Selected rural communities, supported by SLM-trained extension workers through active AP/FFSs, collaborate to promote agroecological approaches, including participatory land use decision-making, in at least 430,000 ha of multi-use demo-landscapes |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 46 | Activities 2.2.X) General Component 2 Activities: Operational Expenses for Sustainable management and rehabilitation of landscapes. Rolling activity for 1.1. and 1.3. - managed internally by the unit | AEZ Unit / AEC (GABAC) | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |
| 47 | Output 2.1) SLM plans: Community-level land-use plans integrating AEZ and SLM are prepared through a participatory approach (GreeNTD) in three municipalities as part of a nested approach to landscape-level management | AEZ Unit / AEC (GABAC) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 48 | Activity 2.1.1.) For the three selected municipalities — based on the AEZ data collected, compiled and analyzed up to that moment the AEZ technical unit at CETAC will produce fine-scaled municipal AEZ products with a proposal for land-use allocation that is optimized for SLM. | AEZ Unit / AEC (GABAC) |  |  | 1 | 1 |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 49 | Activity 2.1.2.) Contracting national or international expert in GreeNTD (or similar participatory methodologies) who is familiar with Angolan territorial and land-use governance. | AEZ Unit / AEC (GABAC) |  |  |  | 1 |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 50 | Activity 2.1.3.) The administrations of targeted municipalities and communes appoint municipal and communal (if applicable) technicians to monitor and participate in the GreeNTD process at local level in the targeted communities. | AEZ Unit / AEC (GABAC) |  |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |
| 51 | Activity 2.1.4.) A one-month preparation process in which the experts in SLM and the expert in decision-making prepare and structure the GreeNTD methodology to be applied in the selected communities on the basis of the AEZ products provided by the AEZ Unit, including a 3-day workshop on GreeNTD methodology for EDA facilitators and municipal technicians. | AEZ Unit / AEC (GABAC) |  |  |  |  | 1 |  |  |  |  |  |  |  |  |  |  |  |  |
| 52 | Activity 2.1.5.) Based on the municipal AEZ products prepared by the AEZ Unit, GreeNTD sessions occur in several phases at the level of the Jangos in the selected communities. This process will have a total duration of 4 months - Relates to Step 3 described in the PRODOC under Output 2.1. | AEZ Unit / AEC (GABAC) |  |  |  |  | 1 | 1 | 1 |  |  |  |  |  |  |  |  |  |  |
| 53 | Activity 2.1.6.) The land-use arrangements agreed at the Jango are translated into the documents that constitute the SLM plans by the SLM experts and the national GIS expert, with clear descriptions of adopted agreements, assignment of responsibilities and appropriate zoning cartography. This process also involves the participation of the municipal technicians. - Relates to Step 3 described in the PRODOC under Output 2.1. | AEZ Unit / AEC (GABAC) |  |  |  |  |  |  | 1 | 1 |  |  |  |  |  |  |  |  |  |
| 54 | Activity 2.1.7.) In each of the target municipalities, the municipal CACS will meet to validate or, if necessary, propose adjustments to the SLM plans. The documentation related to the plans will be provided for consultation prior to the CACS meeting for greater efficiency and productivity - Relates to Step 4 described in the PRODOC under Output 2.1. | AEZ Unit / AEC (GABAC) |  |  |  |  |  |  |  | 1 | 1 |  |  |  |  |  |  |  |  |
| 55 | Activity 2.1.8.) Validation and formal adoption of local SLM plans by each municipal administration, which also designate the municipal officers for overseeing the respective implementation. - Relates to Step 5 described in the PRODOC under Output 2.1. | AEZ Unit / AEC (GABAC) |  |  |  |  |  |  |  | 1 | 1 |  |  |  |  |  |  |  |  |
| 56 | Output 2.2) A network of AP/FFSs (Agro-Pastoral and Farmer Field Schools) in three municipalities is supported in implementing SLM plans and promoting SLM practices | AEZ Unit / AEC (GABAC) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 57 | Activity 2.2.1.) Planning and development of the framework for cooperation with EDA and Master Trainers working under related initiatives (e.g. SADCP and others) concerning agroecological trials aimed at testing SLM solutions in demo landscapes (related to Output 2.1 and 2.2) | AEZ Unit / AEC (GABAC) |  |  |  |  |  |  |  |  | 1 | 1 | 1 |  |  |  |  |  |  |
| 58 | Activity 2.2.2.) Demonstrative agroecological trials aimed at testing SLM solutions are undertaken at each targeted community and at AEC. | AEZ Unit / AEC (GABAC) |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  |
| 59 | Activity 2.2.3.) The positive or negative feedback from the agroecological trials shall be reported on a regular basis to the AEC in Chipipa, which in turn feeds these data into the AEZ Unit at CETAC. | AEZ Unit / AEC (GABAC) |  |  |  |  |  |  |  |  |  |  |  | 1 | 1 | 1 |  |  |  |
| 60 | Output 2.3) A broad training program focused on SLM and the use of AEZ products for supporting decision-making at community-level is institutionalized and delivered through the Chipipa Agroecological Center in the Province of Huambo | AEZ Unit / AEC (GABAC) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 61 | Activity 2.3.0.) A 2-month preparation phase in which the SLM experts of the AEZ Unit, together with the other members of the AEZ Unit and the Chipipa AEC director, prepare in detail the curricular modules, calendar and the pedagogical methods to be used. | AEZ Unit / AEC (GABAC) |  |  |  |  |  | 1 | 1 |  |  |  |  |  |  |  |  |  |  |
| 62 | Activity 2.3.1.) Delivering the training program in structured in modules to a group of between 20 and 30 people | AEZ Unit / AEC (GABAC) |  |  |  |  |  |  | 1 | 1 | 1 | 1 |  |  |  |  |  |  |  |
| 63 | Activity 2.3.2.) Feedback on the activities and conducted trials are regularly reported to the AEZ Unit at CETAC. | AEZ Unit / AEC (GABAC) |  |  |  |  |  | 1 | 1 | 1 | 1 |  |  |  |  |  |  |  |  |
| 64 | Outcome 3.0) Increased availability of funding for, and investments in, land restoration / rehabilitation in Angola |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 66 | Output 3.1) Economic analyses on the cost of land degradation in Huambo and Benguela Provinces are carried out and disseminated among key decision makers to bring financial leverage and scale to the actions needed for restoring/rehabilitating land in central Angola | GABAC / AEZ Unit |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 67 | Activity 3.1.1.) Conduct the study cost of land degradation | GABAC / AEZ Unit |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  |  |  |  |  |
| 68 | Activity 3.1.2.) Production of report on the cost of land degradation | GABAC / AEZ Unit |  | 1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 69 | Activity 3.1.3.) Mounting of a system to keep track / update info on the costs / benefits of land degradation / recovery | GABAC / AEZ Unit |  | 1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 70 | Activity 3.1.4.) Training in Lobbying & Advocacy through practical activities to promote increased availability of resources for SLM based on measures of the cost of land degradation | GABAC / AEZ Unit |  |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  |  |
| 71 | Activity 3.1.5.) Activities to advocate in favor of increased availability of resources for SLM based on measures of the cost of land degradation | GABAC / AEZ Unit |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  |  |  |  |
| 72 | Output 3.2) Mainstream and innovative finance options for SLM are assessed, explored/probed and enabling action is undertaken to operationalize them in the targeted municipalities with fundraising campaigns are organized, and projects are formulated to mobilize funds | GABAC / AEZ Unit |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 73 | Activity 3.2.1.) Exploration and identification of sources of funding for SLM | GABAC / AEZ Unit |  | 1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 74 | Activity 3.2.2.) Design SLM finance mechanisms to be launched | GABAC / AEZ Unit |  | 1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 75 | Activity 3.2.3.) Training of professionals in fundraising including actual campaigns | GABAC / AEZ Unit |  |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  |  |
| 76 | Activity 3.2.4.) Training of professionals in designing projects to tap into available funds / mechanisms | GABAC / AEZ Unit |  |  | 1 |  |  |  |  |  |  |  |  |  | 1 |  |  |  |  |
| 77 | Activity 3.2.5.) Support projects to pilot and adjust the funding mechanisms | GABAC / AEZ Unit |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 1 |  |
| 78 | Output 3.3) Community-based SLM finance, public-private partnerships and targeted matching grants are designed and implemented to channel funds from various funding sources | GABAC / AEZ Unit |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 79 | Activity 3.3.1.) Creation of a trust fund for community-based SLM projects, with solid governance mechanisms | GABAC / AEZ Unit |  |  |  | 1 | 1 | 1 | 1 |  |  |  |  |  |  |  |  |  |  |
| 80 | Activity 3.3.2.) Training on fund raising campaigns involving an actual campaign | GABAC / AEZ Unit |  |  | 1 |  | 1 |  |  |  |  |  |  |  |  |  |  |  |  |
| 81 | Activity 3.3.3.) Support to the management of the trust fund | GABAC / AEZ Unit |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  |  |  |
| 82 | Activity 3.3.4.) Design SLM finance mechanisms specific for income generation and small entrepreneurs | GABAC / AEZ Unit |  | 1 | 1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 83 | Activity 3.4.5.) Establishment of incentives to channel existing community rotating funds to support businesses with high chances of providing an economic return | GABAC / AEZ Unit |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  |  |  |  |
| 84 | Activity 3.4.6.) Training on entrepreneurship and SLM opportunities for entrepreneurs | GABAC / AEZ Unit |  |  |  |  | 1 | 1 | 1 | 1 | 1 |  |  |  |  |  |  |  |  |
| 85 | Activity 3.4.7.) Technical assistance for designing and supporting SLM pilot projects for financial sustainability | GABAC / AEZ Unit |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  |  |  |  |  |
| 86 | Outcome 4.0) Knowledge management, monitoring and evaluation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 87 | Output 4.1) A project monitoring system is in place to providing six-monthly reports on progress in achieving project output and outcome targets | PMU |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 88 | Activity 4.1.1.) Design of project monitoring system and review of monitoring indicators | PMU |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 89 | Activity 4.1.2.) Design by the CTA, NPC and M&E of a visibility strategy according to the GEF, government and FAO requirements. | PMU | 1 | 1 | 1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 90 | Output 4.2) Midterm review and final evaluation conducted | External Evaluation Team |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 91 | Activity 4.2.1.) Global project midterm review | External Evaluation Team |  |  |  |  | 1 | 1 | 1 |  |  |  |  |  |  |  |  |  |  |
| 92 | Activity 4.2.2.) Midterm workshop with all relevant stakeholders | External Evaluation Team |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 93 | Activity 4.2.3.) Global project final evaluation | External Evaluation Team |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 1 |  |
| 94 | Output 4.3) Project-related “best-practices” and “lessons-learned” disseminated | PMU |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 95 | Activity 4.3.1.) Preparation of accessible report on “best-practices” and “lessons-learned” | PMU | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |
| 96 | Activity 4.3.1.) Circulation of report on “best-practices” and “lessons-learned” | PMU |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |
| 97 | Activity 4.3.1.) Closure workshop with all involved stakeholders for discussing "lessons-learned", follow-up initiatives and the project’s sustainability strategy. | PMU |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 1 |  |

## Appendix IV) Budget

## Appendix V) Risk Management

Risk management is a coordinated set of activities to direct and control an organization with regard to risks. It comprises a structured, methodical approach to identifying and managing risks for the achievement of objectives.

The risk management plan will allow to manage risks by monitoring mitigation actions throughout implementation. Part A focuses on external risks to the project and Part B on the identified environmental and social risks from the project.

### Section A: Risks to the Project

This section will identify external risks to the project. In order to identify risks, the following information will be necessary:

Table 24. Risk Assessment: Overall rating is ‘Low’

| Risk description | Worst case consequence for the project | Risk Score |  | Mitigating action | Action owner |
| --- | --- | --- | --- | --- | --- |
|  |  | Impact | Likelihood |  |  |
| Municipal, provincial and national authorities involved by the process may not realize the project’s importance, thus not being sufficiently motivated to effectively “own” the project and work towards a common vision. | Lack of effective and timely cooperation between different stakeholders / entities, hindering the delivery of expected results. | High | Moderate | Effective communication strategies must be deployed from the outset to ensure that relevant stakeholders realize the strategic importance of the project for Angola’s long-term sustainable development. Structured partnerships promote project ownership and also foresee communication flows that promote a sense of inclusion among stakeholders. | GABAC / PSC / PMU |
| The proposed fit of the AEZ Unit at CETAC fails to work as it should due to the difficulty of CETAC’s management model in hosting an independent technical unit. | This would disturb the capacitation strategy set in place, putting at the risk the its objectives and the project’s long-term sustainability. | High | Moderate | The PSC would intervene to assess the situation and propose mitigation measures to resolve potential tensions within CETAC’s management | PMU / AEZ Unit |
| Remote locations causing problems with personnel, logistics, maintenance, etc. | Delays and difficulty in keeping up with the planning of the activities under Component 2. | Moderate | Low | The selection of communities sought to minimize this risk by using ease of access as one of the factors for the final shortlist. Local professionals and those of the AEZ Unit will be supported on the ground by the municipal administrations and respective infrastructure in the targeted project areas. | PMU / Municipalities |
| New practices might clash with local cultures, resulting in slow adaptation of actions (gender, new forms of management, more effective management, alternative use of resources...) | Difficulty in reaching and implementing local SLM agreements. | Low | Moderate | The project will address this risk by joint planning, implementation and, monitoring and evaluation in order to create project ownership from the start. Only practices with high social acceptance that meet stakeholders’ needs and cultural habits will be promoted by the AP/FFSs. The GreeNTD methodology will take cultural differences into consideration and will seek to find common ground through the negotiated agreements. | AEZ unit / Municipalities |
| Degradation of ecosystem due to droughts and climate shocks | Extreme climatic or environmental conditions may prevent the implementation of the SLM plans as expected. | Low | Low | Project level emergency actions will be discussed and planned with participatory methods as part of the SLM plans, which will consider different environmental scenarios, including the occurrence of extreme events. Appropriate linking with on-going emergency / post- emergency initiatives will improve responses to those risks. | AEZ unit / Municipalities |
| Difficulty in successfully integrating the proposed synergetic activities of this project with those of the other relevant projects because cross-sectoral and institutional collaboration is more of an exception than the rule. | The project fails to achieve the expected synergies with other past and ongoing initiatives. | High | Moderate | Involvement and mobilization of local administrations and the management teams of other projects. Implementation arrangements will include strategies to minimize and mitigate this risk. In addition, during the PPG stage, a concerted effort was carried out in terms of: (i) identifying and listing relevant baseline and related initiatives, as well as opportunities for technical integration with relevant projects; (ii) conducting a thorough Capacity Needs Assessment; (iv) involving stakeholders and documenting; (iv) reassessing the presence of indigenous people in project demo landscapes, which showed to be ‘not confirmed’ – and hence with a decreased socio-environmental risk; (v) applied all due diligence and safeguards till the project could then be classified as E&S compliant and ‘low risk’. | PSC |
| The project’s core contributions are not sufficiently linked to and integrated with initiatives and projects that would should use and build on this project’s achievements (AEZ system and products, SLM plans, capacitation, financial mechanisms). | The project contributions may end up being poorly integrated and underused, rendering the project one more isolated initiative without far-reaching or long-lasting impact. | Low | Moderate | The PSC and PMU will systematically work towards the maximization of synergies and linkages with other projects and with the Angolan administrative and planning system to make sure that the projects outputs build on and built on (i.e. put to use) by other initiatives. Pro-active efforts towards stakeholder engagement will be applied during implementation, not least also building from the sound baseline of information contained in the CNA and in other PPG studies, all of which are duly reflected in the content of the FAO GEF PRODOC. | PSC / PMU |
| The existence of many actors involved in land management renders SLM and planning initiatives administratively complex and difficult to address in an organized way. | Too many actors and institutions claim to be excluded from project related decision-making, resulting in their unwillingness to collaborate or facilitate the proposed processes, putting the achievement of project outcomes at risk. | Moderate | Low | The project will address this risk though well-structured and inclusive project management, making sure that all relevant actors are at least informed of the project’s implementation steps and processes prior to their occurrence and as they take place. Part of this strategy may be implemented though the national AEZ outreach online platform by including a webpage with updated information on the planned project interventions, making them accessible to any interested stakeholder. | PSC / PMU |

### Section B: Environmental and Social Risks from the Project

This section is based on the risk matrix obtained during risk screening in the concept note (in FPMIS) and includes each of the risks identified during concept note. The result will be an environmental and social risk management plan that will be monitored during project implementation and regularly reported upon through the project progress reports.

For low risk projects (which is the case here), this section would not be required. However, because the risk rating changed from PIF stage to now, it is completed for adequate cross checking.

Table 25. Specific E&S Risk Assessment: Overall rating is ‘Low’ / Compliant

| Risk identified | Risk Classification | Risk Description in the project | Mitigation Action (s) | Indicators | Progress on mitigation action |
| --- | --- | --- | --- | --- | --- |
| When it comes to decision-making and land use management, ‘ethnicity’ and gender are a highly relevant determinant of land-use traditions, but often downplayed in decision making processes. If unaddressed these issues may aggravate pre-existing biases and inequities concerning gender and ethnicity, disenfranchising entire groups of stakeholders | Low, decreasing | Geophysical conditions do play a strong role in influencing land use – and these elements will be highly on focus in AEZ analyses. However, ethnicity cannot be ignored -- neither can pre-existing gender biases. In the central and southwestern part of Angola, ‘ethnic identity’ is a key determinant of whether a group is a hunter-gatherer, a pastoralist, an agropastoralist or a farmer – nomadic, semi-nomadic or not. The PRODOC’s gender analysis points out visible inequities, when it comes to decision making on land use management. ELABORATION ON THE ABOVE: - On ethnicity and indigenous peoples: At PIF stage, the project had been classified as ‘moderate risk’ from an E&S point of view, because of the likely presence of indigenous Khoe-San people in the areas that had been initially proposed as targeted landscapes – according to desk review carried out back then. - Those risks have been greatly diminished at PPG stage, given that the project’s currently geographical focus is Central Angola, as prioritized by the GoA, and where presence of indigenous Khoe-San people is much less common. - Furthermore, during the PPG, site level consultations were carried out in Alto Hama and Chongoroi. As a result, there is no confirmation on the presence of indigenous peoples in the above-mentioned demo landscapes targeted by the project. - Hence, even if the application of FPIC had been prescribed for the PPG stage, along with other socio-environmental safeguard measures, it proved not necessary. - Social environmental risks linked to the likely presence of indigenous are considered ‘low’ at this stage. - As for gender mainstreaming, gender-based inequities are still prevalent in Angola across the entire national territory. Although gender equality has been given some attention in Angola – especially in the environment sector -- there is still an urgent need to increase women’s engagement in various levels of the socio-economic life, especially in rural regions of Angola. - At the same, the focused stakeholder consultation processes carried out during the PPG, along with the brief analysis of the gender aspects that followed, pointed out to a tendency towards gender gaps being ‘ironed-out’ in various relevant stakeholder segments. These include in particular, local government, academia, private sector and ‘resource partner/donor’, where women are 32 to 50% of the stakeholder count. - In turn, women are under-represented in two crucial segments for the project, namely ‘National Government Institution body’ and ‘Local community’ (constituting 24% and 18% of stakeholder count respectively) – in spite of the concerted efforts towards explicitly engaging them. Incidentally, these two latter segments are the core the beneficiary groups. - Therefore, much more is needed to ensure that the direct and indirect benefits of SLM are equitably shared, including in terms of division of labor, new professional opportunities and in the provision of a supportive environment for working mothers. | Even though taking issues of ‘ethnicity’ and ‘gender’ into account is the default for FAO GEF projects, these issues should be treated with the due sensitivity when moving from PPG to PRODOC under implementation, avoiding thereby a ‘rubber stamping’ approach to those issues. The PRODOC prescribes in several passages, that gender and ethnicity should be carefully considered during full project implementation, in particular in connection with stakeholder interactions and engagement. This is the norm, irrespective of whether any given ethnic groups identify themselves as ‘indigenous people’ in connection with project design. A similar approach to gender mainstreaming has also applied and should be practiced by the full project’s team, once hired. As for the current project design, at this stage moving from PIF to PRODOC for CEO Endorsement, all safeguards pertaining to gender and ethnicity have been put in place, and risks minimized -- as follows: - Regarding gender: A gender mainstreaming plan was developed on the basis of a brief but project specific gender analysis. Refer to subsection Gender Action Plan in section 3.6. - Several gender sensitive indicators were included in the Logical Framework, which has 20 indicators and 34 sub-indicators, or 54 in total. - Of the 20 indicators, 8 include include explicit gender disaggregation. - Of the 54 indicators and sub-indicators, 6 are not suitable for monitoring gender mainstreaming (e.g. they monitor number of hectares), leaving 48 indicators and sub-indicator where the gender can be potentially included. Among them, 21 include the gender aspect in one way or another. - This is a strong token of gender mainstreaming for a project tagged as “G2a” for its gender mark. With reference to the checklist in PRODOC Table 22 (on the entry points for monitoring gender the mainstreaming of aspects during project implementation), and in light of the above points, project design can be said to be compliant with the GEF’s 2018 Guidance to Advance Gender Equality and applicable FAO safeguards and policies. - Regarding ethnicity: A thorough and well researched section on Indigenous Peoples (3.7) has been prepared in connection with the PPG. Indeed, the need for FPIC was dispensed during the PPG, given that there is, at the current stage, no indications of presence of indigenous peoples in the selected project demo landscapes in Alto Hama and Chongoroi. - Site level consultations in these localities confirmed the above, and the consultations were duly recorded in sequential and thorough PPG Reports. - With the slight adjustment to the project’s geographic focus, targeting Benguela and Huambo, there are at this stage, minimal risks of the project unintentionally causing “adverse effects on indigenous peoples’ rights, lands, natural resources, territories, livelihoods, knowledge, social fabric, traditions, governance systems, and culture or heritage (tangible and intangible)” – as stated in the FAO’s Safeguard #ESS 9 on ‘Indigenous Peoples and Cultural Heritage’. The results from the checklist in PRODOC Table 23 (on the screening for FPIC during PPG and project implementation) pointed out to the project being ‘compliant’ with respect to the need for applying FPIC -- it is currently not applicable. Residual risks concerning gender and ethnicity are minimal. Else, should there be at least one grievance filed by an indigenous group (or of a women’s group) regarding perceived negative impacts, FAO will work with government to take measures, following the agency's and the GEF's guidance on the matter. Measures may include FAO experts advising the FAOAO Country Office and the project team for commending and conducting a specific impact analysis with focus on indigenous and/or marginalized groups and their plight for territorial and other culturally bound rights vis-a-vis project planning, rolling stakeholder engagement, including gender and special groups, as well as specific socio-environmental risk assessment. | E&S safeguards compliance, as attested by the LTO, concerning the checklist elements (see PRODOC Table 26 below) | Compliant throughout the PPG stage (last updated in Dec 2018 – FAO TO UPDATE AS NEEDED) |

Table 26. Summary results from the Project Environmental and Social (E&S) Screening Checklist

| Elements of the E&S Checklist | Status of scoring |
| --- | --- |
| I. FAO VISION/STRATEGIC OBJECTIVES | Compliant |
| II. FAO KEY PRINCIPLES FOR SUSTAINABILITY IN FOOD AND AGRICULTURE | Compliant |
| ESS 1 NATURAL RESOURCES MANAGEMENT | No discernable risk identified |
| ESS 2 BIODIVERSITY, ECOSYSTEMS AND NATURAL HABITATS | No discernable risk identified |
| ESS 3 PLANT GENETIC RESOURCES FOR FOOD AND AGRICULTURE | No applicable risk |
| ESS 4 ANIMAL - LIVESTOCK AND AQUATIC- GENETIC RESOURCES FOR FOOD AND AGRICULTURE | No discernable risk identified |
| ESS 5 PEST AND PESTICIDES MANAGEMENT | No applicable risk |
| ESS 6 INVOLUNTARY RESETTLEMENT AND DISPLACEMENT | No applicable risk |
| ESS 7 DECENT WORK | No applicable risk |
| ESS 8 GENDER EQUALITY | Compliant |
| ESS 9 INDIGENOUS PEOPLES AND CULTURAL HERITAGE | Compliant |

## Appendix VI) Terms of Reference

### TORs for PMU – Core Project Team

PMU - Project Team [1]:	Project Coordinator / National expert in SLM, Land-Use Management and Spatial Planning expert.

PMU - Project Team [2]:	CTA International GIS and AEZ expert. International GIS expert with experience in FAO AEZ methodology over a 3.5-year period.

PMU - Project Team [3]:	International Agro-Economy expert with good knowledge of SLM finance 24 months over 4 years: Focus on the economics and finance of land degradation and ecosystem restoration.

PMU - Project Team [4]:	National GIS and AEZ expert

PMU - Project Team [5]: 	International ITC Program Analyst (part-time)

PMU - Project Team [6]:	Senior Consultant: National expert in GreeNTD (or similar participatory methodologies) who is familiar with Angolan territorial and land-use governance. Field services at approx. 6 months

PMU - Project Team [7]:	(a) Finance & administration officer and (b) Procurement Officer. Standard FAO TORs apply.

For the role of the National Project Director (NPD), refer to [*].

Note: All TOR will be appraised by the GoA before publishing, as a means to engage the national counterparts in the Project’s key processes. This also applies to the TOR of service providers and institutions to be engaged through LOAs.

#### [1] TOR for the National Project Coordinator (NPC)

1. Scope

As the effective Project Manager, the National Project Coordinator (NPC) will be the project technical and managerial leader, with the due seniority required. This position is full time for the entire duration of the project. Total input: up to 4 years.

Under the supervision of: FAO Representative in Angola (FAOR), LTO with reporting linkages to the National Project Director (NPD).

Reporting to: FAO Representative, LTO

Nationally recruited

Based in Huambo, at Angola’s Centre of Tropical Ecology and Climate Change (CETAC), under the Ministry of Environment (MINAMB), with frequent travel to the field and Luanda for liaising with officials from the Office for Climate Change (GABAC)

2. Objective

To ensure the smooth running of the project and the timely provision of high-quality inputs as needed. The NPC will be accountable to both FAO and the NPD for the quality, timeliness and effectiveness of the activities carried out, as well as for the use of funds.

3. Tasks

The NPC will be responsible for the operational planning, management and monitoring of all project’s activities, as indicated in the project document. He/she will work closely with government officials of both GABAC and CETAC under MINAMB. The NPC will provide technical, logistics and managerial support and ensure a good implementation of the activities in line with the project result framework, work plan and approved budget.

In addition, the NPC will have technical expertise in the field of SLM integrate the AEZ Unit (a technical team of experts to be installed at CETAC) as one the team’s experts. This will include:

Project Management

- Organize and lead the inception workshop and prepare inception report;

- Prepare annual and six months work plans and prepare ToR for all inputs;

- Lead process to mobilize PMU staff, project consultants and sub-contracts;

- Lead process to finalize ‘letters of agreement’ with implementation partners;

- Ensure all PMU staff and all consultants fully understand their role and their tasks, and support them in their work;

- Oversee day-to-day implementation of the project in line with the work plans;

- Organize regular planning and communication events, starting with inception mission and inception workshop;

- Oversee preparation and implementation of M&E framework;

- Oversee creation of a participatory monitoring system for the Project’s work;

- Ensure real-time monitoring of project progress and the alerting of MINAMB, BH and LTO of potential problems that could result in delays in implementation;

- Help identify consultant candidates for the AEZ Unit and work with the BH to ensure their timely recruitment;

- Ensure the project’s effective and efficient work with stakeholders in the pilot areas;

- Help organize and supervise consultant inputs;

- Oversee preparation and implementation of project communication and knowledge management frameworks;

- Prepare progress reports and all monitoring reports. This includes the six-monthly progress reports and contributions to the project’s reports

- Prepare and organize the PSC meetings.

Lead interactions with stakeholders

- Liaise with government agencies, the AEZ Unit and AP/FFS facilitators and master trainers;

- Regularly advocate on behalf of the project to partners;

- Coordinate project interventions with other ongoing activities, especially those of MINAMB

- Regularly promote the project and its outputs and findings on a national, and where appropriate, regional stage; and

- Coordinate activities with co-financing donors and other projects related to FFS.

Within the AEZ Unit

- Ensure that the operational and logistic needs of the AEZ Unit at CETAC are met;

- Together with the International SLM expert participate in ensuring that AEZ products are adequate for the purposes of SLM and the specific products to be used within this project (C2) are fit for purpose in terms of the national/regional context in which they will be applied (Outputs 1.1, 1.2, 1.3, 1.4, 1.5 and 2.1);

- Learn from the International SLM expert about the subject matter of the same activities;

- He/she will be responsible for taking over the role of the International SLM expert in coordinating/supervising SLM-related activities within the AEZ Unit upon his/her departure from the project.

- Coordinate activities with the ICE-SLM AEC Director at CETAC and with staff at the AEZ regarding Outputs 1.5, 2.2 and 2.3;

- Together with the other Nat. SLM expert and the GreeNTD expert engage in the participatory planning process with local communities;

- The NPC the other Nat.SLM expert will assist and train EDA Facilitators AP/FFS master trainers in strategically adapting the activities of the AP/FFSs to support the implementation of the local SLM plans.

- The NPC the other Nat.SLM expert will participate in the delivery of a training program focused on SLM and the use of AEZ products and the negotiated land-use plans for supporting decision-making for SLM at local level.

- Under Component 3, and in coordination with the National Agro-Economy Expert and the International SLM Finance expert, the NPC will implement the following activities: 3.2.5. Support projects to pilot and adjust the funding mechanisms; 3.3.6. Training on entrepreneurship and SLM opportunities for entrepreneurs and 3.3.7. Technical assistance for designing and supporting SLM pilot projects for financial sustainability.

Technical support

- Support development of project strategic approach;

- Ensure quality of project activities and project outputs;

- Support development and preparation of training materials;

- Oversee creation of the Project’s approach to managing and sharing knowledge, and to identifying and disseminating lessons learned;

- Communicate, advocate and engage in policy dialogue; and

- Take a lead in the organization and technical implementation of several activities.

4. Qualifications

- Higher degree related to natural resources management, with a specialization in SLM;

- At least ten years’ experience in the Angolan agricultural sector, environmental governance, or land-use governance;

- At least five years’ experience working with local communities in Angola;

- Solid experience in project management and in particular results-based management;

- Previous experience working with international partners on related issues;

- Demonstrated expertise in agro-ecology, conservation agriculture;

- Demonstrated commitment to participatory natural resource management techniques; and

- Intermediate Portuguese and proficient English language skills are essential.

#### [2] TOR for the Chief Technical Advisor (CTA)

1. Scope

The project’s Chief Technical Advisor (CTA) will be internationally recruited, with core skills in Geographic Information Systems (GIS) and Agroecological Zoning (AEZ), possessing excellent and mastery of Sustainable Land Management (SLM) themes. FAO Geospatial Unit, under the Climate and Biodiversity Department (CBDS), a unit that is specialized in Global Agro-Ecological Zones (GAEZ), may be called upon to propose candidates for this position and/or assist with the recruitment.

The International GIS expert with experience in FAO’s AEZ methodology will be engaged over a 3.5-year period. This position is full-time, field-based and located in the offices of and for almost the entire duration of the project, funding permitting, for the full duration. Total input: approximately 3.5 years, up to 4 years (funding permitting)

Under the supervision of the FAO Representative in Angola

Reporting to: FAO Representative, FAO LTO-

International recruitment

Duty Station: Huambo, at Angola’s Centre of Tropical Ecology and Climate Change (CETAC), under the Ministry of Environment (MINAMB), with frequent travel to the field and Luanda.

2. Objective

To directly support the NPC and the PMU and ensure best international technical and management practices are integrated into the Project work plan and activities.

3. Tasks

The CTA will be responsible in coordination with NPC for the operational planning, management and monitoring of all project’s activities. He/She will provide technical support and ensure a good implementation of the activities in line with the project result framework, work plan and approved budget.

In addition, the CTA will have technical expertise in the field GIS/SLM and head the AEZ Unit (a technical team of experts to be installed at CETAC) as the team’s lead expert.

This will include:

Support to the NPC and PMU:

- Ensure that latest and best international practices and approaches are reflected in the design and planning of project activities;

- Support the organization and implementation of the inception workshop and compile inception report in close cooperation with the NPC;

- Contribute directly to all technical activities, notably:

  - Negotiations with partners and development of joint work programs and budgets.

  - Analyze training materials and technical options for implementation methodologies framed on CCA, SLM and Agroecology

  - Identify Sustainable Land Management (SLM) and Climate Change Adaptation (CCA) practices including irrigation that meet the agro-ecological environment and the farmers’ needs.

- Prepare annual work plans in collaboration with NPC, PMU and HQ officer(s);

- Support real-time monitoring of project progress and the alerting of the BH and the LTO to potential problems that could result in delays in implementation;

- Help identify consultant candidates;

- Provide technical advice as required to project experts, consultants, and contractors and help to organize and supervise consultant inputs;

- Support the organization of regular trainings, including Farmer Filed School master training, and the coordination of high-level stakeholder events;

- Support design of the project’s work with stakeholders in the pilot areas;

- Propose an approach to managing and sharing knowledge, and to identifying and disseminating lessons learned;

- Provide on-the-job capacity development to all members of the PMU;

- Develop, together with the NPC and HQ officer(s), terms of reference for the following Expert’s consultations: International Consultant expert in APFS/FFS and community organization, Agroecology, Climate Change Adaptation and Sustainable land management, International Consultant expert in land rehabilitation and management and agroforestry and International Consultant expert in Territorial Management Plan Capacity building and national permanent consultancies of the National Agroecology Technical Officers and Technicians with competences in FFS implementation and monitoring

- Communicate, advocate and engage in policy dialogue;

- Support all aspects of the day-to-day execution of the project;

- Provide technical advice and assistance to the mid-term and final evaluations of the project; and

- Support the NPC in reporting on project progress, and contribute to the development of semi-annual PPRs and reporting as part of the Project’s reports

Within the AEZ Unit

- Coordinate general activities of the AEZ unit throughout project implementation;

- Technically lead in particular all activities related to GIS under Outputs 1.1, 1.2, 1.3, 1.4, 1.5 and 2.1;

- Train the participants of the job shadowing and training programs at CETAC on subjects related to GIS and the integration of SLM, AEZ data and the AEZ WebGIS Decision Support System;

- Define responsibilities and frequency for data collection and monitoring of indicators;

Compile a comprehensive M&E system for the project and prepare shared tools for workplanning and budgeting:

- Define methodologies for measurement and monitoring of indicators and information sources, making sure baseline is established for all indicators and that they are S.M.A.R.T.;

- Define responsibilities and frequency for data collection and monitoring of indicators;

- Allow for adaptive management of project execution;

- Document institutional memory of the project; and

- Facilitate project progress reporting and communication of results.

4. Qualifications

- Higher degree related to GIS, SLM, natural resources, environment management and rural development;

- Experience in establishing project results and progress monitoring systems;

- Solid experience in project management and in particular results-based management;

- At least five years’ experience working with local communities in the agricultural sector in Angola or Central Africa;

- High degree of familiarity with Open Foris / Collect Earth, or alternatively, familiarity with similar systems (e.g. Q-GIS or others) will also fulfil the requirements, along with a commitment to have acquire skills with Open Foris / Collect Earth it by project’s inception;

- Demonstrated previous experience working with the field school approach to extension or with similar approaches in the context of climate change;

- Demonstrated previous experience with GIS applied to SLM practices;

- Previous experience working with international partners on related issues;

- Intermediate Portuguese and proficient English language skills are essential.

- Knowledge of FAO’s project management systems is and assessments.

- Language: Excellent skills in written English. Good working knowledge of Portuguese.

#### [3] TOR for the International Agro-Economy / SLM Finance expert

1. Scope

International Agro-Economy / SLM Finance expert, with focus on the economics and finance of land degradation and ecosystem restoration. Total input: approximate 24 months over 4 years on an intermittent basis, with missions scheduled according to the project’s needs and workplanning

Under the supervision of: CTA, NPC, working closely with government officials within the Office for Climate Change (GABAC) under the Ministry of Environment in Angola (MINAMB)

International recruitment

Duty Station: Luanda with visits to the field in Huambo and Benguela.

2. Tasks

In the context of the Project’s component 3, the International Expert in Agro-Economy and SLM Finance will have responsibilities to leading the activities of Output 3.1) Economic analyses on the cost of land degradation in the Province of Huambo and Benguela are carried out and disseminated among key decision makers to bring financial leverage and scale to the actions needed for restoring/rehabilitating land in that part of the country.

This output will be implemented through the following activities:

3.1.1	Conduct the study on the cost of land degradation

3.1.2	Production of report on the cost of land degradation

3.1.3	Mounting of a system to keep track / update info on the costs / benefits of land degradation / recovery

3.1.4	Training in Lobbying & Advocacy (using the evidence produced)

3.1.5	Activities to advocate in favor of increased availability of resources for SLM based on measures of the cost of land degradation

He/she will conduct the study foreseen under 3.1.1 and plan in detail the remainder of activities, in close collaboration with the National Project Coordinator (NPC) and the Chief Technical Advisor (CTA).

The successful execution of Output 3.1 activities, as well as other activated co-related, will imply: 1. Liaising with existing and potential donors and other Fund stakeholders; 2. Establishing strategic partnerships, and identify key resource mobilization opportunities; 3. Analyzing and research information on donors, prepare substantive briefs on possible areas of cooperation, and support resource mobilization efforts; 4. Ensuring preparation of resource mobilization strategy.

Also, in the context of the Project’s Component 3, and under Outputs 3.2 and 3.3 in particular, the International Expert In Agro-Economy And SLM Finance will have the following main functions:

=>	Under Output 3.2) Mainstream and innovative finance options for SLM are assessed, explored/probed and enabling action is undertaken to operationalize them in the targeted municipalities with fundraising campaigns are organized, and projects are formulated to mobilize funds:

3.2.1	Exploration and identification of sources of funding for SLM

3.2.2	Design SLM finance mechanisms to be launched

=>	Under Output 3.3 Community-based SLM finance, public-private partnerships and targeted matching grants are designed and implemented to channel funds from various funding sources:

3.3.1	Creation of a trust fund for community-based SLM projects, with solid governance mechanisms

3.3.3	Support to the management of the trust fund

3.3.4	Design SLM finance mechanisms specific for income generation and small entrepreneurs

3.3.5	Establishment of incentives to channel existing community rotating funds to support businesses with high chances of providing an economic return

He/she will also be responsible for specific training programs under Component 3, and may be called upon to deliver other training and capacity building foreseen under the project, not least also the training of CETAC’s staff on SLM finance and related matters. The following are some of the relevant activities:

3.2.3	Training of professionals in fundraising including actual campaigns

3.2.4	Training of professionals in designing projects to tap into available funds / mechanisms

1.2.3	Job shadowing program engaging trainees and CETAC’s appointed staff members (learning-by-doing)

1.2.4	Creating and maintaining a network of professionals involved in AEZ and environmental monitoring at national level in which CETAC plays a centralized role as a national hub, rolling outreach on a continuous basis.

1.2.5	Designing and implementing a training program to be progressively implemented by the experts of the Unit to their counterparts, members of CETAC's staff

This will include working closely with the NPC and the other Nat. SLM expert, capacitating them to support projects to pilot and adjust the expect funding mechanisms and to deliver the expected training programs in:

3.3.6	Training on entrepreneurship and SLM opportunities for entrepreneurs

3.3.7	Technical assistance for designing and supporting SLM pilot projects for financial sustainability

The International Consultant’s will ensure linkages and consistency between the Trust Fund and other national related initiatives; support national counterparts to revise and develop policy, strategy, planning and program documents within the framework of the Fund; Support GABAC in the design, identification and implementation of capacity assessment and capacity development plans; and advise GABAC, in preparing guidelines for Participating Organizations for capturing best practices and lessons learned.

Additionally, other activities, for which the input from the International Expert In Agro-Economy And SLM Finance may be sought will include:

2.2.2	Demonstrative agroecological trials aimed at testing SLM solutions are undertaken at each targeted community and at AEC.

Activities under Output 2.3.0.	A broad training program focused on SLM and the use of AEZ products for supporting decision-making at community-level is institutionalized and delivered through the Chipipa Agroecological Center in the Province of Huambo

With respect to a possible the ‘Local Rural Economy Module’, which is envisaged developed as part of the AEZ system, inputs from the International Agro-Economy / SLM Finance expert will be essential. Participation in brainstorming and conceptualization sessions for the purpose with the remainder of the team is also expected.

3. Qualifications

- Advanced degree in economic with a specialization in rural / agrarian economy, and in-depth knowledge of SLM / ecosystem restoration finance. Notions on the technical principles of agroecology are an advantage.

- In depth knowledge of public policy, development studies, economy, political science, international relations, or related field.

- A minimum of 10 years of relevant experience, with strong track record in report writing, team building and contextual analysis and conceptualization processes;

- Experience in high-level negotiations, preferably in an African and/or global context, with excellent facilitation and negotiation skills, as well as the ability to build consensus among a wide variety of stakeholders;

- At least 5 years of experience in developing financial solutions for NRM and ideally SLM in particular;

- Capacity to analyze complex political situations, vulnerability and crisis/ conflict/ post conflict scenarios;

- Strong knowledge of SLM and agroecology;

- In-depth understanding of Trust Fund Operations, and their link to Trust Fund Administration and Trust Fund implementation;

- Ability to lead strategic planning, results based management and reporting interventions for programs and initiatives of various scales;

- Strong verbal and written communication skills

- Strong organizational skills and knowledge of project management, results-based reporting, monitoring and evaluation and basic financial terminology and analysis;

- Experience in working with UN agencies, governments, multilaterals, donors, NGOs and CSOs.

- Language: Excellent skills in written English. Good working knowledge of Portuguese.

#### [4] TOR for the National GIS and AEZ expert

1. Scope

National Expert in Geographic Information Systems (GIS) and Agroecological Zoning (AEZ) and mastery of Sustainable Land Management (SLM) themes. Total input: 3.5 years.

Under the supervision of: CTA, NPC

Nationally recruited. Huambo and Field

2. Tasks

This is in part a cross-learning position, as the ultimate goal of several project activities is to develop national capacity. Therefore, the National GIS and AEZ expert will progressively accumulate relevant experience and exert responsibility in the execution of the same activities as her/his mentors, namely (i) the International Chief Technical Advisor (CTA), who will also have a profile with weight on GIS and AEZ, functioning as an additional mentor to the National GIS and AEZ expert; and (ii) the National Project Coordinator (NPC):

More specifically, the National GIS and AEZ expert will focus on the following cross-learning tasks:

- Learn from the International SLM expert about the subject matter of the relevant activities, given that applications of fine-scale AEZ are, to a great extent, a novelty in Angola;

- Together with the NPC, the National GIS and AEZ expert will assist and train EDA Facilitators AP/FFS master trainers in strategically adapting the activities of the AP/FFSs to support the implementation of the local SLM plans.

- Together with the NPC, the National GIS and AEZ expert will participate in the delivery of a training program focused on SLM and the use of AEZ products and the negotiated land-use plans for supporting decision-making for SLM at local level.

- Work with other relevant team members to train the participants of the job shadowing and training programs at CETAC on subjects related to GIS and the integration of SLM, spatial data and the AEZ WebGIS Decision Support System;

- Together with the NPC, the CTA, and other project experts, participate in the delivery of various training sessions foreseen in the project’s workplan – training that will be focused on SLM, the use of AEZ products and the negotiated land-use plans for supporting decision-making for SLM at local level, and not least also SLM finance.

- Under Component 3, the National GIS and AEZ expert will assist the NPC in implement the following activities: 3.2.5. Support projects to pilot and adjust the funding mechanisms; 3.3.6. Training on entrepreneurship and SLM opportunities for entrepreneurs and 3.3.7. Technical assistance for designing and supporting SLM pilot projects for financial sustainability.

Within the AEZ Unit / GIS related

Under the oversight of the International Chief Technical Advisor (CTA), participate in key project activities, directly assisting the NPC to ensure that AEZ products are adequate for the purposes of SLM and the specific products to be used within this project (C2) are fit for purpose in terms of the national/regional context in which they will be applied (Outputs 1.1, 1.2, 1.3, 1.4, 1.5 and 2.1). These are this stated:

Output 1.1)	AEZ Unit: A service-oriented national data analysis and technical unit dedicated to agroecological zoning (AEZ) and other related geospatial analysis is created at CETAC

Output 1.2)	AEZ Services: CETAC is progressively capacitated to (i) serve as a hub for AEZ experts, including by leveraging at least 2 strategic partnerships, and (ii) maintain the provision of AEZ services to at least 3 national entities/clients beyond the project’s lifetime

Output 1.3)	LDN monitoring: AEZ Unit provides services on monitoring of land degradation and of ecosystem services within an area of 6.1 M ha i.e. the project’s Wider Landscape

Output 1.4)	AEZ System: The AEZ-based fine-scale WebGIS decision support system (DSS) for SLM, LD and ecosystem services monitoring is developed, covering 6.1 M ha (the Wider Landscape), providing relevant products and creating a framework for the project’s national up-scaling

Output 1.5)	AEC networked: The Agroecological Center of Chipipa is set up as a two-way hub for (i) collecting AEZ data and (ii) generating AEZ products through WebGIS DSS platform

Output 2.1)	Community-level land-use plans integrating SLM (SLM plans) based on AEZ are prepared through a participatory approach (GreeNTD) in three municipalities as part of a nested approach to landscape-level management

General activities will also include:

- Develop workplans, budgets and work on M&E related matters, under the guidance from both CTA, NPC

- Prepare reports upon request;

- Carry out research and feed data into systems, maintaining files organized and essential data available;

- Prepare and/or review TOR, recruitment and procurement dossiers;

- Maintain regular communication with project stakeholders, maintaining in connection with it, a complete list and dossier on stakeholder engagement;

- Facilitate the inputs from incoming consultants, fellows, teams, partners and collaborators;

- Liaise with government agencies, the AEZ Unit and AP/FFS facilitators and master trainers;

- Assist the NPC to identify consultant candidates for the AEZ Unit and work with the BH to ensure their timely recruitment;

- Support the NPC and CTA to ensure the project’s effective and efficient work with stakeholders in the pilot areas;

- Assist with the preparation and implementation of project communication and knowledge management frameworks;

- Contribute to prepare progress reports and all monitoring reports. This includes the six-monthly progress reports and contributions to the project’s reports

- Assist the NPC and CTA to prepare for and organize the PSC meetings.

3. Qualifications

- Higher degree related to natural resources management, with a specialization in SLM and or GIS;

- At least five years’ experience in the Angolan agricultural sector, environmental governance, or land-use governance;

- At least three years’ experience working with local communities in Angola;

- Solid experience in project management and in particular results based management is an asset;

- Previous experience working with international partners on related issues;

- Demonstrated expertise in agro-ecology, conservation agriculture;

- Demonstrated commitment to participatory natural resource management techniques; and

- Proficient Portuguese and solid English language skills are essential.

#### [5] TOR for the International Computer Sciences / ITC Program Analyst (part-time)

1. Scope

International ITC Program Analyst, expert in designing online GIS solutions, in particular for what programming and back-end solutions are concerned. Total input: up to 12 months (or as funds permit).

Under the supervision of: CTA, NPC

Internationally recruited. Huambo

One of the key results of the project is the development of national capacity within Angola’s Centre of Tropical Ecology and Climate Change (CETAC), under the Ministry of Environment (MINAMB) for applying Agroecological Zoning (AEZ) as a key tool for spatial planning. The AEZ System will be a fine-scale WebGIS decision support system (DSS) with focus on applications of AEZ modules, techniques and data for promoting Sustainable Land Management (SLM) as a target land use. In addition, the system should be able to monitor Land Degradation (LD) parameters, acquire and process data on ecosystem services, targeting a region of Angola with some 6.1 M hectares (referred to in the project documentation as ‘the Wider Landscape’. The AEZ Unit, to be established within CETAC will be able to provide relevant AEZ products and render related services to potential clients (government agencies, other projects, farmers’ associations etc.), creating thereby a framework for the project’s national up-scaling.

2. Objective

The role of the International ITC Program Analyst is to analyze, define, develop, test and maintain software applications in support of the achievement of business requirements of developing and operating CETAC’s AEZ system. This includes coding, testing, and analyzing software programs and applications in connection with the development of the AEZ system. He/she will also research, design, document and modify software specifications throughout the system development life cycle.

The main responsibility of the Computer Scientist / ITC Programmer Analyst will be design and setup the AEZ system in accordance with needs defined by the AEZ Unit. System setup will feature design of software or/and use of Open Source services.  More specifically, s/he will carry on the following tasks:

- Technical infrastructure setup

- Online GIS system (WebGIS DSS) development

- Geocatalog development

- Portal CMS setup

S/he will be also responsible for system implementation, including testing and applying changes if needed (as indicated by user surveys) as well as debugging the system if needed.

Core project activities under the responsibility of the International ITC Program Analyst will include, where a specific role is assigned:

1.4.1	WebGIS DSS system development. Critical input by the Computer Scientist / ITC Programmer Analyst

1.4.2	Geocatalog development - Critical input by the Computer Scientist / ITC Programmer Analyst

1.4.3	CMS setup - Critical input by the Computer Scientist / ITC Programmer Analyst

1.4.4	User surveys (y1, y2, y3, y4) - Under the supervision of the Computer Scientist / ITC Programmer Analyst

1.4.5	Development of e-inclusion strategy and training program - Critical input by the Computer Scientist / ITC Programmer Analyst

For what the WebGIS DSS development is concerned, the International ITC Program Analyst may also be called upon to contribute to the following activities:

1.2.3	Job shadowing program engaging trainees and CETAC’s appointed staff members (learning-by-doing) – and for which the International ITC Program Analyst may be paired up with a national with similar, but less senior profile, in view of fostering curiosity, skills development and capacity building.

1.2.5	Designing and implementing a training program to be progressively implemented by the experts of the Unit to their counterparts, members of CETAC's staff

3. Qualifications

- At least Bachelor’s degree in in the field of computer science, information systems, or software engineering,

- Some training in GIS, applied mathematics, or other related disciplines is a plus;

- At least 3 years of professional experience in designing tailored online GIS solutions;

- Proficiency in a variety of programming languages

- Pride in creating attractive and intuitive UIX.

- Excellent understanding of relational database and experience – e.g. with MS SQL Server to allow easier integration with commonly used MS software from the Office package.

- Ability to conduct research into software-related issues and products.

- Solid working knowledge of current Internet technologies, including IIS, web services and secure web processing.

- Prior experience interviewing end-users for insight on functionality, interface, problems, and/or usability issues – including by applying gender sensitivity in interviewing or applying surveys.

- Ability to communicate effectively with non-technical staff and with members of cross-functional teams.

- Hands-on experience developing test cases and test plans.

- Flexible and adaptable in regards to learning and understanding new technologies, as well as or working in environments where technical skills are under development.

- Knowledge of applicable data privacy practices and laws.

- Highly self-motivated and directed.

- Keen attention to detail.

- Proven analytical and problem-solving abilities.

- Ability to effectively prioritize and execute tasks in a high-pressure environment.

- Experience working both independently and in a team-oriented, collaborative environment.

- Proficient English is essential, working knowledge of Portuguese is an asset;

- Basic knowledge of agro-ecology, conservation agriculture and SLM is an asset.

#### [6] TOR for the National Expert in GreeNTD or Similar Participatory Methodologies

1. Scope

Expert in GreeNtd or similar participatory methodologies for territorial diagnosis and local agreements for the production of land management plans. Total input: approximately 3-5 months.

Under the supervision of: CTA, NPC

Nationally recruited. Huambo and Field

2. Tasks

Based on the municipal AEZ products prepared by the AEZ Unit, GreeNTD processes occurs in several phases at the level of the Jangos in the selected communities. These involve a process of negotiation according to the GreeNTD methodology between the stakeholders of each community, leading up to collectively agreed land-use allocation and practical arrangements for SLM. In each community, the GreeNTD sessions should take place within a period of no longer than four months, followed by a two-month drafting of the resulting plans.

This process is driven jointly by the Nat. SLM experts and the decision-making (GreeNTD) expert, who will be responsible for:

- preparing the GreeNTD sessions based on the expected AEZ products;

- conducting the GreeNTD sessions;

- deriving the expected agreements and outputs from these sessions;

- Providing guidance and support to the Int. and Nat. SLM experts regarding the substance, details and social implication of reached agreements.

3. Qualifications

- Higher degree related to political science or land use governance, specialized participatory decision-making and public participation;

- Knowledge and practical experience of the GreenNTD methodology are important assets;

- At least five years’ experience in the Angolan agricultural sector, environmental governance, or land-use governance;

- Previous experience working with international partners on related issues;

- Basic knowledge of agro-ecology, conservation agriculture and SLM;

- Proficient Portuguese and solid English language skills are essential.

#### [7a] TOR for the Finance & administration officer

1. Scope

This position is part-time over the entire duration of the Project and will be based at FAO Luanda with travel to Huambo as needed. Total input: 48 months Under the supervision of: FAO BH, Reporting to: FAO BH

Nationally recruited. Duty Station Luanda

2. Tasks

Under the direct supervision of the FAO BH and in consultation with the NPC, the Operations and Administrative Officer will have the following responsibilities and functions:

- Ensure smooth and timely implementation of project activities in support of the results-based work plan, through operational and administrative procedures according to FAO rules and standards;

- Coordinate the project operational arrangements through contractual agreements with key project partners;

- Arrange the operations needed for signing and executing Letters of Agreement (LoA) with relevant project partners;

- Maintain inter-departmental linkages with FAO units for donor liaison, Finance, Human Resources, and other units as required;

- Day-to-day manage the project budget, including the monitoring of cash availability, budget preparation and budget revisions to be reviewed by the NPC;

- Ensure the accurate recording of all data relevant for operational, financial and results-based monitoring;

- Ensure that relevant reports on expenditures, forecasts, progress against work plans, project closure, are prepared and submitted in accordance with FAO defined procedures and reporting formats, schedules and communications channels, as required;

- Execute accurate and timely actions on all operational requirements for personnel-related matters, equipment and material procurement, and field disbursements;

- Participate and represent the project in collaborative meetings with project partners and specially support the project’s PMU in the budget and financial aspects;

- Undertake missions to monitor the outputs-based budget, and to resolve outstanding operational problems, as appropriate;

- Be responsible for results achieved within her/his area of work and ensure issues affecting project delivery and success are brought to the attention of higher level authorities through the BH in a timely manner;

- In consultation with FAO Evaluation Office, the HQ officer(s), and FAO-GEF Coordination Unit, support the organization of the mid-term and final evaluations, and provide inputs regarding project budgetary matters;

- Provide inputs and maintain the FPMIS systems up-to-date; and

- Undertake any other duties as required.

3. Qualifications

- University Degree in Economics, Business Administration, or related fields;

- Three years of experience in project operation and management related to natural resources management, including field experience in developing countries;

- Proven capacity to work and establish working relationships with government and non-government representatives;

- Portuguese language skills preferential, English language skills an asset; and

- Knowledge of FAO’s project management systems is an advantage.

#### [7b] TOR for the Procurement Officer

1. Scope

- This position is part-time over the entire duration of the Project and will be based at FAO Luanda. Total input: 48 months Under the supervision of: FAO BH, Reporting to: FAO BH

- Nationally recruited. Duty Station Luanda

2. Objective

- The procurement officer will be responsible for all the procurement of goods and services of the project in accordance with FAO procurements rules and procedures as outlined MS 502 manual

3. Tasks

- Under the direct supervision of the FAO BH and in consultation with the NPC, the National Procurement Officer will have the following responsibilities and functions:

- Identification of local dealers and potential suppliers of goods from local market applying MS 502 FAO procurement rules and regulations;

- Perform local procurement process of goods from local suppliers applying MS 502 FAO rules and procedures; reviewing incoming PRs, preparing ITB, receipt of quotations, bids or proposals, their evaluation, negotiation of certain conditions of contracts in full compliance with MS 502 FAO procurement rules and regulations; and assist in conducting the procurement activities in the field offices

- Manage and maintain local procurement supplier data base and update vendor list/information per item and process supplier call for expression for interest, evaluate suppliers’ ability and clearance to work with FAO,

- Solicit of low value procurement quotations, evaluating and issuing low value procurement orders;

- Communicate procurement awards decisions to wins and losers;

- Receive and dispatch incoming and outgoing correspondence from procurement office;

- Following approvals of purchase requisitions and soft commitments from the users;

- Assist in the preparation of the invitation for Bids, attending the Local Procurement Committee meetings, preparation and editing the LPC’s reports, POs and all related documents.

- Receive and review all invoices, register them and forward them to finance for payment. In cases, of quality issues coordinate with the technical team on how much liquidated damages to apply before forwarding invoices for payment. For delay in delivery decide how much liquidated damages to apply as per MS 502 rule and regulations.

- Participation in the organization of training for operations/projects staff on Procurement, synthesis of lessons learned and provision of relevant examples from the procurement practice;

- Maintain a proper and appropriate procurement filling system; of procurement registers for contracts, tenders, orders and requisitions system that ensures faster, systematic filing, faster retrieval of information, greater protection of information, and increased administrative stability, and continuity.

- Raise Purchase orders for goods and services for MS 502 and MS 507 LoA’s the GRMS.

- Act as the secretary of LPC for both MS 502 and 507. Prepare all the documentation for presentation to this local procurement committee

- Conduct preliminary quality assurance for LoAs, by making sure that in the LoA file all the documentation is in order and properly completed and filed, before final quality assurances is conducted by the procurement officer;

- Liaise with Logistics Unit for timely preparation and obtaining of letters of import exemption and re-export, follow up on clearance of goods and shipments and ensure safe arrival of the consignments to the final destinations

- Provide assistance in theHelp the constructions activities.

- Assist in sorting out all related service contracts.

- Perform other related duties as required.

4. Qualifications

- University Degree in Economics, Business Administration, Procurement or related fields;

- Three years of experience in procurement management, including field experience in developing countries;

- Proven capacity to work and establish working relationships with government and non-government representatives;

- Knowledge of FAO’s procurement management systems is an advantage.

#### [*] TOR for the National Project Director

Framework

MINAMB will designate a high-level official to act as the National Project Director (NPD) under the project. The following bullet points define the framework of the engagement of the NPD in the Project:

- The NPD will provide the strategic oversight and guidance to Project implementation.

- The NPD will not be paid from the project funds, but represents the Government’s interests in the Project, ensuring policy compliance, institutional anchoring and ownership.

- The NPD’s engagement in the Project in terms of staff-time dedication counts as part of the Government’s co-financing to it.

### Other TORs: Evaluation, Consultancies and other Service Provision Needs

#### TOR Outline for the External Evaluation Team – 6 Weeks

With Support  of FAO Office of Evaluation, in accordance with FAO evaluation procedures and taking into consideration evolving guidance from the GEF Evaluation Office and in close consultation with the Project Coordinator, the FAO budget holder (AGPM) and the FAO HQ Officer(s), the external evaluation team will three months prior to the terminal review meeting of the project partners conduct an independent final evaluation. The final evaluation will review project impact, analyze sustainability of results and whether the project has achieved its adaptation objectives and benchmarks. The evaluation will furthermore provide recommendations for follow-up actions.

The evaluation will, inter alia:

- review the effectiveness, efficiency and timeliness of project implementation;

- analyze effectiveness of implementation and partnership arrangements;

- identify issues requiring decisions and remedial actions to insure sustainability of project outcomes and outputs;

- identify lessons learned about project design, implementation and management;

- highlight technical achievements and lessons learned; and

- Prepare a final evaluation report.

Some critical issues to be evaluated in the midterm and final evaluations will be:

(i) effectiveness of the AEZ Unit in producing the expected AEZ products; (ii) the functioning and effectiveness of the AP/FFS network and of the inter-institutional coordination mechanism in developing and implementing integrated planning in support of SLM for the project’s target landscapes and addressing key biodiversity threats; (iii) the level of capacities and involvement of local staff in terms of improved management effectiveness and land management plan implementation capability; (iv) the level of involvement of farmers and herders in land management models; (v) the effectiveness of the project’s different training programs and capacitation strategies.

Requirements: The team should include professionals specialized in land degradation, SLM and with demonstrated experience in project evaluation. They must have 10 years of professional experience in the field. Previous working experience in the region, as well as experience in project coordination with international bodies, will be especially valuable.

Languages: Portuguese / English

Location: Angola (Huambo and field)

Duration: 2 consultants (international and national) for 6 weeks each.

#### Standardized Professional Services required

- Drivers (x2) Nr 1, budget charged to C1 and C2;

- Engaging field-level data collectors locally. Purpose: Regularity and scheduling, technology involved, priority indicators for data reception/collection. Yearly costs are estimates – under Activity 1.4.3) CMS setup - Critical input by the Computer Scientist / ITC Programmer Analyst, under Output 1.4 on the AEZ System;

- Translations, editorial and web services, bulk - under Output 4.3) Project-related “best-practices” and “lessons-learned”

#### TOR Outline for other Consultancies and Service Provision Needs

| # | Purpose | Linkages |
| --- | --- | --- |
| 1 | Consultancy contract to be tendered out: Technical infrastructure planning and setup for the AEZ Unit. Includes completing a 'Hardware and software CNA' in collaboration with the nascent AEZ unit. | Output 1.1) AEZ Unit |
| 2 | Communications consultant for the AEZ unit and its services, related to Activity 1.2.4 (Creating and maintaining a network of professionals involved in AEZ and environmental monitoring at national level in which CETAC plays a centralized role as a national hub, rolling outreach) and Activity 1.2.5 (Designing and implementing a training program to be progressively implemented by the experts of the Unit to their counterparts, members of CETAC's staff). This work may be merged and/or managed together with a related consultancy under C1 and C2. | Output 1.2) AEZ Services: |
| 3 | Consultancy contract to be tendered out: Development of e-inclusion strategy and training program | Output 1.4) AEZ System: |
| 4 | Consultancy contract to be tendered out: Linked to the following activities under Output 1.4 pertaining to the AEZ System (The AEZ-based fine-scale WebGIS decision support system (DSS) for SLM, LD and ecosystem services monitoring is developed, covering 6.1 M ha (the Wider Landscape), providing relevant products and creating a framework for the project’s national up-scaling) plus related activities under Output 1.2 pertaining to AEZ Services (CETAC is progressively capacitated to (i) serve as a hub for AEZ experts, including by leveraging at least 2 strategic partnerships, and (ii) maintain the provision of AEZ services to at least 3 national entities/clients beyond the project’s lifetime). This work may be merged and/or managed together with a related consultancy under Output 1.5. | Output 1.4) AEZ System: |
| 5 | Consultancy contract to be tendered out: User surveys (y1, y2, … and a survey investigating existing decision-support products). Under the supervision of the PMU's Team member Programmer Analyst. | Output 1.5) AEC networked: |
| 6 | AEC Operationalization National Expert: Consultancy contract to be tendered out: Linked to the following activities under Output 1.5 pertaining to the the functioning of the AEC in network with CETAC (The Agroecological Center of Chipipa is set up as a two-way hub for (i) collecting AEZ data and (ii) generating AEZ products through WebGIS DSS platform). This work may be merged and/or managed together with a related consultancy under Output 1.4 | Output 1.5) AEC networked: |
| 7 | Consultancy contract to be tendered out: Evaluate the effectiveness of implementation of Outputs 2.2 and 2.3 relating to the mainstreaming of SLM in landscape level management, including through FFSs micro-landscape level management, and Municipal / Communal spatial planning. Refers to Activity 2.2.4 (The positive or negative feedback from the agro-ecological experiments shall be reported on a regular basis to the AEC in Chipipa, which in turn feeds these data into the AEZ Unit at CETAC.) and Activity 2.3.3 (Feedback on the activities and conducted experiments are regularly reported to the AEZ Unit at CETAC.) | Output 2.3) SLM Community training program |
| 8 | Community planning Platforms development expert. Consultancy contract to be tendered out: In connection with the training module under Output 2.3, a company will be hired to review and carry out QC on the materials and help format for multi-platforms, including workbook, web and mobile. The training will be delivered by project staff. Refers to the operationalization of various activities under Output 2.3 [from 2.3.1 to 2.A training program focused on SLM and the use of AEZ products for supporting decision-making at community-level is institutionalized and delivered through the Chipipa Agro-Ecological Center in the Province of Huambo.) | Output 2.3) SLM Community training program |
| 9 | National Consultancy in financial mechanisms for SLM. Contracting one or more consulting business to assist with all activities under Output 3.1 (Increase availability of resources for SLM based on measures of the cost of land degradation) and Output 3.2 (Operationalization of a financial mechanisms for SLM) relating to Activities: (3.2.1) Inventory of sources of funding for SLM; (3.2.2) Training of professionals in fund raising including actual campaigns; (3.2.3) Training of professionals in designing projects to tap into available funds / mechanisms; (3.2.4) Support projects to pilot the mechanisms. Note: These two activates should be run together by the same team. 30% of training participants should be women. Training sessions will be organized before in time to prepare projects for the agriculture year. 30% of training participants should be women. | Output 3.1) Economic analyses |
| 10 | Contracting one or more consulting business to assist with all activities under Output 3.3 (Develop community-based financial mechanisms for SLM) relating to (3.3.1) Creation of a trust fund for community-based SLM projects, with solid governance mechanisms; (3.3.2) Training on fund raising campaigns involving an actual campaign; (3.3.3) Support to the management of the trust fund. Notes: Activity 3.3.1 may also imply the transformation of an existing fund. Activity 3.3.3 has a much different character, to the extent that it is tailored for communities and implies that 30% of training participants should be women. | Output 3.3) Community-based SLM finance & PPP |
| 11 | National Expert in Community-based SLM finance and National SLM Business Development Expert. Contracting one or more consulting business to assist with all activities under Output 3.4 (Promote businesses related with SLM) relating to Activities: (3.4.1) Training on entrepreneurship and SLM opportunities for entrepreneurs; (3.4.2) Incentives to channel existing community rotating funds, to support businesses with high chances of providing an economic return; and (3.4.3) Technical assistance for designing and support of SLM pilot- projects with the focus on financial sustainability. Note: 30% of training participants should be women. | Output 3.3) Community-based SLM finance & PPP and Output 3.4 |
| 12 | M&E Technical Consultancy. Monitoring and Evaluation Specialist will be in charge of developing and updating the project’s M&E system (short-term) | Output 4.1) Project M&E system |

# Annexes (Additional – Project Specific)

## Annex A. PRODOC Atlas (separate file)

[Separate file]

## Annex B. Tracking Tool

[See separate file for more details]

Table 27. Reference checklist used in the CNA with reference to sourcing of GIS data for AEZ

| Data Type | Data | Variable (in blie global data sets note) |  | Priority for collection | Data available? |
| --- | --- | --- | --- | --- | --- |
| PART I |  |  |  |  |  |
| GIS data | Climate | Minimum temperature |  | 1 | INAMET. Else, global data sets can be obtained by navigating to and from known sites: IPCC Data - http://www.ipcc-data.org/ ; NOAA https://www.climate.gov/; Climate Change Knowledge Portal shttp://sdwebx.worldbank.org/climateportal/ |
|  |  | Maximum temperature |  | 1 |  |
|  |  | Precipitation |  | 1 |  |
|  |  | Solar radiation |  | 1 |  |
|  |  | Relative humidity |  | 1 |  |
|  |  | Wind speed |  | 1 |  |
|  | Demography | Population density |  | 1 | INE, but accessing raw data (published census data for 2014 is incomplete). |
|  | Land/water | Soil type |  | 1 | Beyond FAO’s, some national data sets exist, but they are not easily available. Faculty of Agrarian Sciences and Institute for Agronomic Research have the best available data for Huambo. SADCC, Soil and Water Conservation and Land Utilization Co-ordination Unit produced a reasonable map on erosion hazard. |
|  |  | Soil attributes, including |  | 1 |  |
|  |  | - Soil texture (% clay, sand, silt) |  | 1 |  |
|  |  | - Coarse fragments |  | 1 |  |
|  |  | - Soil nutrients |  | 1 |  |
|  |  | - Soil carbon |  | 1 |  |
|  |  | - Soil pH |  | 1 |  |
|  |  | - Base saturation |  | 1 |  |
|  |  | - CEC |  | 1 |  |
|  |  | - Soil salinity |  | 1 |  |
|  |  | - Drainage class |  | 1 |  |
|  |  | - Soil depth |  | 1 |  |
|  |  | - Soil water (saturation, field capacity, wilting) |  | 1 |  |
|  |  | - Hydraulic conductivity or infiltration rate |  | 1 |  |
|  |  | Altitude |  | 1 | IGCA Angolan Institute for Geodesy and Cartography (Instituto de Geodesia e Cartografia de Angola) should have reasonable topographical maps. |
|  |  | Terrain slopes |  | 1 |  |
|  |  | Land cover/use by shares: |  | 1 | See global data sets to the right. |
|  |  | - Land under annual and perennial crops |  | 1 | Possibly MINAMB and IGCA |
|  |  | - Grassland/pastures |  | 1 | Regarding vegetation, see considerations in the PRODOC Atlas. Regarding vegetation, see considerations in the PRODOC Atlas. There are no reliable data on vegetation cover in Angola. No comprehensive post-war vegetation assessment exists, though IDF has begun a satellite-based assessment of forest cover; the numbers provided here are only indicative. |
|  |  | - Forest |  | 1 |  |
|  |  | - Plantation (forest) |  | 1 |  |
|  |  | - Woody vegetation (shrubs, etc.) |  | 1 |  |
|  |  | - Grassland/pastures/herbaceous |  | 1 |  |
|  |  | - Wetlands |  | 1 |  |
|  |  | - Sparsely vegetated |  | 1 |  |
|  |  | - Artificial surfaces |  | 1 | Google Earth is the ultimate source |
|  |  | - Water bodies |  | 1 | Esri Data & Maps provides a base map. CETAC has a localized detailed map of water bodies in Huambo. |
|  |  | Protected areas |  | 2 | MINAMB, beyond global data sources that depend on MINAMB's reporting. |
|  |  | Water |  |  | Esri Data & Maps provides a base map. CETAC has a localized detailed map of water bodies in Huambo. |
|  |  | Watershed boundaries |  | 1 |  |
|  |  | Drainage network |  | 2 |  |
|  |  | Irrigated land by type |  | 1 |  |
|  |  | Source of irrigation (% groundwater, surface) |  | 2 |  |
|  |  | Groundwater/Water table depth |  | 2 |  |
|  | Agriculture | Rain-fed multi-cropping |  | 2 | FAO / MINAGRIF |
|  |  | Irrigated multi-cropping |  | 2 |  |
|  |  | Livestock density |  | 2 |  |
|  |  | Crop specific masks |  | 1 |  |
|  |  | Crop calendar |  | 1 |  |
| Statistical data | Population | Population, total |  | 1 | INE, but accessing raw data (published census data for 2014 is incomplete). |
|  |  | Population growth |  | 1 |  |
|  |  | Urbanization rate |  | 1 |  |
|  |  | Agricultural population, total |  | 1 |  |
|  | Economy/ Income | GDP per capita |  | 1 | INE and WB. Data may differ. |
|  |  | GDP growth |  | 1 |  |
|  |  | GDP by primary, secondary, tertiary sector |  | 1 |  |
|  |  | Labor by occupation/sector |  | 1 |  |
|  | Agriculture/ Land use | Crop-wise sown/planted area |  | 1 | MINAGRIF and FAO, but quality of statistics vary. |
|  |  | Crop-wise irrigated area |  | 1 |  |
|  |  | Crop-wise production |  | 1 |  |
|  |  | Yield |  | 1 |  |
|  |  | Cropping intensity |  | 1 |  |
|  |  | Livestock numbers by type |  | 2 |  |
|  |  | Livestock production by type |  | 2 |  |
|  |  | Gross cropped area |  | 1 |  |
|  |  | Net cropped area |  | 1 |  |
|  |  | Gross irrigated area |  | 1 |  |
|  |  | Net irrigated area |  | 1 |  |
|  |  | Land use (by major uses) |  | 1 |  |
|  |  | Size distribution of agricultural holdings |  | 2 |  |
|  | Water supply and use | Irrigated area by source of irrigation |  | 1 | Esri Data & Maps provides a base map. CETAC has a localized detailed map of water bodies in Huambo. |
|  |  | Irrigation infrastructure (number of tube wells, canals, etc.) |  | 2 |  |
|  |  | Total water resources |  | 1 |  |
|  |  | Surface water resources |  | 2 |  |
|  |  | Groundwater resources |  | 2 |  |
|  | Crop economics and utilization | Production costs and net returns, by target crop, separately for rain-fed and irrigated production |  | 1 | MINAGRIF and FAO, but quality of statistics vary. |
|  |  | Fertilizer use; total and by crop |  | 1 |  |
|  |  | Use of inputs (seed, fertilizers, labor, machinery, power, and other costs) |  | 1 |  |
|  |  | Crop utilization |  | 1 |  |
|  |  | Beginning/Ending stocks (of target crop commodities) |  | 1 |  |
|  |  | Georeferenced research station data (best practice/'potential' yield) for target crops |  | 1 |  |
| PART II |  |  |  |  |  |
| Crop / Land Utilization Type | Crop / LUT characteristics | Land utilization type descriptions (description of management and resources applied for commercial farms and small farmers separately) |  | 2 | MINAGRIF and FAO, but quality of statistics vary. INE started collecting agricultural data, but not comprehensive agronomic census has been carried our since before the war. |
|  |  | Harvested products (e.g., for energy tobacco biomass, seed, seedcake and oil) |  | 2 |  |
|  |  | Field/crop management/husbandry (e.g., local crop calendars, transplanting details and harvesting periods (sequences) and methods) |  | 2 |  |
|  |  | Cropping pattern and rotation constraints (e.g. requirements for breaking pest and disease cycles) and main rotation crops/other types of productive fallow |  | 2 |  |
|  |  | Pest and disease management (chemical/biological crop protection applications type, frequency and efficacy) |  | 2 |  |
|  |  | Attainable potential yield, good commercial yields, and average smallholder yields of total biomass (with moisture %), seed, cake and oil; |  | 2 |  |
|  |  | Irrigation methods (if used) |  | 2 |  |
|  |  | Fertilizer requirements. (Uptake of N, P, K per ton of harvested product and per ton DM of plant) |  | 2 |  |
|  | Crop / LUT climate requirements | Thermal climate requirement |  | 2 | Not assessed |
|  |  | Temperature growing period and temperature profile requirements |  | 2 | Not assessed |
|  |  | Temperature sums requirements |  | 2 | Not assessed |
|  |  | Relative humidity requirements (upper/lower limits for optimal conditions, if any) |  | 2 | Not assessed |
|  |  | Photosynthesis response to radiation and temperature |  | 2 | Not assessed |
|  |  | Phenological requirements (e.g., for flowering/seed set) and photoperiodicity implications (if any) |  | 2 | Not assessed |
|  |  | Average growth cycle from emergence to transplanting from transplanting to full maturity/harvest |  | 2 | Not assessed |
|  |  | Durations of main phenological stages |  | 2 | Not assessed |
|  |  | Crop water coefficients (Kc) and factors by crop development stage |  | 2 | Not assessed |
|  |  | Yield response to water deficit (factors Ky) by crop development stage |  | 2 | Not assessed |
|  |  | Harvest index (separately for seed, harvested biomass, etc.) |  | 2 | Not assessed |
|  |  | Maximum leaf area index |  | 2 | Not assessed |
|  |  | Plant height at maturity |  | 2 | Not assessed |
|  |  | Agro-climatic constraints (pest diseases, weeds, workability and sensitivity to frost as related to agro-climate) |  | 2 | Not assessed |
|  |  | Soil born constraints and control of main pest and diseases. |  | 2 | Not assessed |
|  | Crop / LUT soil requirements | Soil profile attribute requirements/tolerances ( Organic matter, pH, CEC, BS, TEB, CaCO3, gypsum, salinity, sodicity) |  | 2 | Not assessed |
|  |  | Soil texture requirements |  | 2 | Not assessed |
|  |  | Soil drainage requirements |  | 2 | Not assessed |
|  |  | Soil phase tolerances |  | 2 | Not assessed |
|  |  | Rooting depth |  | 2 | Not assessed |
|  |  | Terrain/Slope requirements |  | 2 | Not assessed |
|  |  | Waterlogging/flooding tolerances |  | 2 | Not assessed |

Box 8. Reference to useful environmental datasets containing publicly available data and information

| FAO’s initiative ‘Global Agro-Ecological Zones - GAEZ FAO’ GAEZ is not only highly central to the development of a national /sub-national AEZ system for Angola, but also the most relevant global reference for useful environmental datasets containing publicly available data and information. The AEZ system to be hosted and developed within CETAC will draw on GAEZ’ guidelines, data and community of users and developers. Various pre-loaded global datasets can be directly sought and retrieved from FAO’s GAEZ portal. The Portal avails mediated access to agroecological data and data gathering methodologies. Since there is a team in FAO headquarters constantly developing the GAEZ system and standing partnerships with centres of excellence around the world, there are frequent improvements to the data, methods, tools and applications. Many of these improvements are user-driven. This does not preclude the need for national data and ground-truthing of global data that may be used in AEZ products. All of this is well reflected in the Project Strategy with respect to Component 1 and in part also Component 2. | www.fao.org/nr/gaez/en/ The Portal |
| --- | --- |
| Other useful environmental datasets at the global level can also be freely accessed .: Below is a non-exhaustive list :. |  |
| - Biogeographic regions Udvardy’s Biogeographical Provinces - Land cover Terra-i Global Land Cover 2000 IDRISI Land Change Modeler - Ecosystem services Toolkit for Ecosystem Service Sitebased Assessment (TESSA) Integrated Valuation of Ecosystem Services and Trade-offs (InVEST) - Land use and land-use change Dyna-CLUE Globiom Land Systems Map Land cover change rapid assessment tool Global Forest Watch - Climate change IPCC Data - http://www.ipcc-data.org/ NOAA https://www.climate.gov/ Climate Change Knowledge Portal shttp://sdwebx.worldbank.org/climateportal/ - Protected Areas WDPA - Water bodies ESA https://earth.esa.int/web/guest/content/-/article/mapping-water-bodies-from-space-mwbs-2018- - Wild fires NASA Firms Global Forest Watch |  |
| For yet other online resources, refer to Annex 2 in the following FAO publication: Land Resource Planning for Sustainable Land Management: Current and Emerging Needs in Land Resource Planning for Food Security, Sustainable Livelihoods, Integrated Landscape Management and Restoration http://www.fao.org/3/a-i5937e.pdf |  |

## Annex C. Bibliography

Box 9. Suggested reading by STAP and spatial planning, Considerations and Cross-reference

| Papers recommended by the GEF’s STAP | Considerations and Cross-reference |
| --- | --- |
| (1) Schenibel, A. et al. (2017). "Assessment of spatio-temporal changes of smallholder cultivation patterns in the Angolan Miombo belt using segmentation of Landsat time series". Remote Sensing of Environment 195 (2017) 118–129. | The time series segmentation of land use change data, with focus on tropical deforestation and degradation in Angola, revealed detailed information on the dynamics of deforestation and cultivation. The paper refers to Miombo landscapes, which are the most common biome in Angola, hence the discussions are rather relevant. The authors used existing time series segmentation tool (LandTrendr) with a time series of Normalized Burn Ratio (NBR) data in combination with adapted temporal metrics to provide information about the dynamics of different cultivation patterns, to gain insight into historical developments and to assess temporal cultivation characteristics. Such studies can have many uses, including in the development of REDD/REDD+ Programs in Angola. The two interesting facts about the paper: (i) The accuracy obtained with respect to the detection of disturbance in forested / wooded habitats. It reached, according to the authors, 72%. This make the segmentation of spatio-temporal changes a powerful tool for AEZ and spatial planning, to the extent that it can predict, with a reasonable degree of accuracy, the next hectare to be cleared. It can be used preventively across landscapes, in particular, if combined with other data from the AEZ system. (ii) Liked to the above, the mentioned method’s ability to take the effects of the armed conflict on miombo landscapes into account. The paper concludes that it had a strong deterrent on deforestation and degradation – i.e. a ‘positive effect’ of a 70% drop and in spite of the countless negative effects that armed conflict namely has on human society. In turn, the effect of the end of armed conflict, in 2002, resulted in a tripling of disturbance patterns. If a lesson can be learned from this hindsight, is that, with respect to the deforestation and degradation, post-conflict resettlement processes needs to be much more orderly when it comes to decision making on land use allocation. In the PRODOC Atlas in Annex A, a visual study, based on Global Forest Watch data, had focused on land use trends and fire incidence across the landscapes in Angola (covering the entire country as a macro-landscape), Huambo and Benguela provinces. The PPG study is composed of a series of maps, graphs and info boxes, and one conclusion from it is that 2018 was apparently a peak year for fire in Huambo, Angola and Benguela in this order. In Huambo at least, it was ~80% higher than the average for 2001 till Oct 2018. This warrants caution, if fire incidence is closely related to the degradation of woodlands. |
| (2) Cabral, A., et al. (2010). "Spatial dynamics and quantification of deforestation in the central-plateau woodlands of Angola (1990e2009)". Applied Geography 31 (2010) 1185-1193. | This second paper quantifies deforestation in the Huambo province using remote sensing. Similarly, the paper mentioned -- Schenibel, A. et al. (2017) -- above, is also relevant. It equally confirms the tendencies land cover patterns as observed – i.e. the correlations between changes in land use associated with new settlement and the end of the civil war. The paper also points out to the relatively lower potential of Huambo for landscape level recovery. Such tendency should be closely monitored in connection with LDN indicators. |

Table 28. Bibliographical sources mentioned in the PRODOC

| # | Author (year) | Title |
| --- | --- | --- |
| 1 | Angola Alliance (2004) | Huambo Baseline and Data Assessment Studies. Huambo Provincial Government, Huambo, Angola |
| 2 | Barbosa (1970) | Phytogeographic Map of Angola. Instituto de Investigação Científica de Angola, Luanda, Angola |
| 3 | Cabral, Ana Isabel (2007) | Cartografia de coberto do solo para o território angolano utilizando imagens de satélite modis. Instituto de Investigação Científica Tropical (IICT). Revista Portuguesa de Estudos Regionais, Nº 15. |
| 4 | FAO (1996) | Agro-Ecological Zoning: Guidelines. FAO Soils Bulletin 73, Soil Resources, Management and Conservation Service |
| 5 | FAO (1999) | Environmental Impact Guidelines No. 1: What are Environmental Assessments? |
| 6 | FAO (2012) | FAO's Approaches to Capacity Development in Programming: Processes and Tools. Capacity Development Learning Module 2. |
| 7 | FAO (2014) | Governance of Tenure Technical Guide No. 3 |
| 8 | FAO (2016) | Negotiation, environment and territorial development: Green Negotiated Territorial Development (GreeNTD) - More than a methodology- an approach for improving equitable access and sustainable management of territories |
| 9 | FAO (2016) | Free Prior and Informed Consent. An indigenous peoples’ right and a good practice for local communities Manual for Project Practitioners. |
| 10 | FAO (2017): | Land Resource Planning for Sustainable Land Management: Current and Emerging Needs in Land Resource Planning for Food Security, Sustainable Livelihoods, Integrated Landscape Management and Restoration. FAO Land and Water Division, Working Paper 14. |
| 11 | FAO, IFAD, UNICEF, WFP and WHO. (2018) | The State of Food Security and Nutrition in the World 2018. Building climate resilience for food security and nutrition. FAO, Rome, Italy |
| 12 | FAO-MINADER (2004) | Relatório nacional sobre a situação dos recursos zoogenéticos para a alimentação e a agricultura. Angola. Food and Agriculture Organization (FAO); Ministério da Agricultura e do Desenvolvimento Rural (MINADER). |
| 13 | FAOSTATS (n.d) | FAO Statistical Data Angola. FAO, Rome, Italy. Accessed in October 2018. |
| 14 | Global Forest Watch (n.d) | Angola Data and Dashboards. Global Forest Watch, Washington D.C, USA |
| 15 | Government of Angola (2013) | Programa de Acção Nacional de Combate à Desertificação. Government of Angola, Luanda, Angola |
| 16 | Huambo Provincial Government (2013) | Plano Estratégico de Ambiente da Província de Huambo. Huambo, Angola |
| 17 | ILO Convention 169 (1989) | Indigenous and Tribal Peoples Convention of 1989. |
| 18 | INE (2014) | Resultados Preliminares do Recenseamento Geral da População e da Habitação de Angola 2014. INE, Luanda, Angola |
| 19 | INE (2016) | Resultados definitivos. Recenseamento Geral da População e Habitação de 2014. INE, Luanda, Angola |
| 20 | IWGIA (2015) | The indigenous world. 2015. By the International Working Group for Indigenous Affairs (IWGIA). |
| 21 | IWGIA (2018) | IWGIA’s (Interactive) Yearbook for 2018. |
| 22 | Marcelino, B. (1996) | Assessment of slowly exchangeable potassium reserves in some African ferrasoils |
| 23 | Minang, P. A., Duguma, L. A., Alemagi, D., & van Noordwijk, M. (2015) | Scale considerations in landscape approaches. In Minang, P. A., van Noordwijk, M., Freeman, O. E., Mbow, C., de Leeuw, J., & Catacutan, D. (Eds.) Climate-Smart Landscapes: Multifunctionality in Practice, 121-133. Nairobi, Kenya: World Agroforestry Centre (ICRAF). |
| 24 | Ministério do Urbanismo e Habitação (2013) | Relatório de Identificação e Diagnóstico dos Planos Territoriais. |
| 25 | Ministry of Agriculture (2016) | Perspectiva Nacional e Resumo dos Resultados da Análise de Base sobre a Economia do Agregado Familiar. Ministry of Agriculture, Luanda, Angola |
| 26 | Ministry of Agriculture (2017) | Plano de Desenvolvimento de Médio Prazo do Sector Agrário: 2018-2022. Ministry of Agriculture, Luanda, Angola |
| 27 | Orr, B. et al. (2017) | Scientific Conceptual Framework for Land Degradation Neutrality. A Report of the Science-Policy Interface. United Nations Convention to Combat Desertification (UNCCD), Bonn, Germany. |
| 28 | Provincial Government of Huabo (2013) | Plano Estratégico do Ambiente do Huambo - Mar 2013. |
| 29 | UNCCD (2016) | Achieving Land Degradation Neutrality at the Country Level: Building Blocks for LDN Target Setting |
| 30 | UNDG (2007) | UNDG Guidelines on the Declaration on the Rights of Indigenous Peoples. |
| 31 | USAID (2013) | Angola Biodiversity and Tropical Forests: 118/119 Assessment |
| 32 | Wikipedia (2018) | Wikipedia entry “Línguas de Angola” in Portuguese. Accessed in Oct 2018. |
| 33 | World Bank (2007) | Environmental and Social Management Process Report. Volume 2 – Environmental and Social Diagnosis and Institutional and Legal Framework |

## Annex D. OFP Letter dated 25 September 2019 on implementation arrangements

--oOo—

END OF PRODOC

See Guidance Note on Gender Mainstreaming in project identification and formulation.

“Definition of the Land Degradation Neutrality Voluntary National Targets (LDN-TSP)”. Ministry of Environment. November 2018

Eight terrestrial biomes encompass 23 vegetation types (according to Barbosa’s 1970 ‘Phytogeographic Map of Angola’. Instituto de Investigação Científica de Angola, Luanda, Angola).

Real-time estimates from the National Institute of Statistics (INE): http://www.ine.gov.ao/, assessed in October 2018.

FAO Stats: http://www.fao.org/faostat/en/#country/7. Accessed on Accessed on 09 Oct 2018.

According to FAOSTATS, the indicator ‘Cereal import dependency ratio (percent) (3-year average)’ for Angola was 64.1% in 2011-2013 and has been in the increase; it was 55.2% and 53.5% in two preceding periods (Ibid).

LDN targets and strategies were presented by the GoA and validated by stakeholders in November 2018.

The exact number is 25,789,024 inhabitants in 2014, according to the Population Census from that year. Natural growth was assessed at 2,7% INE (2014).

Using different criteria for classifying population as urban, statistics from FAO suggest that in 2017 the urban population was only 45,6% against 54.4% rural. This apparent discrepancy is most likely explained by the fact that many of the areas classified as urban in the census are small urban centers in which most of the population is employed in the surrounding rural areas.

Ministry of Agriculture (2016): Perspectiva Nacional e Resumo dos Resultados da Análise de Base sobre a Economia do Agregado Familiar. The study classified households according to four categories: ‘very poor’, ‘poor’, ‘mid-level income’ and ‘more affluent’. The ‘very poor’ and ‘poor’ represent 32% and 28% of the total respectively.

Refers to indicator ‘Poverty headcount ratio at national poverty lines (% of population) 35% in 2008’. Source: WB Open Data,

(data.worldbank.org), retrieved on 13 Oct 2018. Other sources may show different numbers.

Refer to Annex E for more information on the two provinces and to the PRODOC Atlas in Annex A for additional maps.

The nested jurisdictional entry points for government administration include the national, provincial, commune and village levels.

Includes in Huambo Province: Bailundo, Caála, Catchiungo, Ecunha, Huambo, Londuimbale, Longonjo, Mungo, Tchikala-Tcholohanga, Tchinjenje and Ukuma.

The non-coastal municipalities in Benguela Province are: Balombo, Bocoio, Caimbambo, Chongorói, Cubal and Ganda.

These are the Cuanza, Cuvo, Catumbela and Cunene rivers, which drain into the Atlantic, but also the Cubango river, which form part of the Okavango basin.

“Definition of the Land Degradation Neutrality Voluntary National Targets (LDN-TSP)” .Ministry of Environment. November 2018). (see results in the PRODOC Atlas in Annex A).

Production of Crude Oil including Lease Condensate 2017 (CVS download) from U.S. Energy Information Administration. Retrieved 09 Oct 2018.

See e.g. FAO, IFAD, UNICEF, WFP and WHO. (2018). The State of Food Security and Nutrition in the World 2018. Building climate resilience for food security and nutrition. Rome, FAO.

The GoA household-level survey from 2016 indicates that the average cultivated area per household varies from 0.55 hectares to up to 3.0 hectares according to the different zones in the country.

The GoA household-level survey from 2016 indicates that the average cultivated area per household varies from 0.55 hectares to up to 3.0 hectares according to the different zones in the country.

PMPSA 18-22.

Ministério do Ambiente (MINAMB).

Direcção Nacional do Ambiente.

Direcção Nacional da Biodiversidade.

Direcção Nacional de Prevenção e Avaliação de Impactes Ambientais.

Direcção Nacional de Tecnologias e Normação Ambiental.

Gabinete das Alterações Climáticas (GABAC).

Comissão Multisectorial para o Ambiente.

Ministério de Agricultura e Florestas (MINAGRIF).

Instituo de Desenvolvimento Florestal (IDF).

The Office for Rural Land Management (Gabinete de Gestão de Terras Agrícolas) advises on the competent institution for managing the national cadastre (i.e., the IGCA) in regard to rural lands.

Gabinete de Segurança Alimentar (GSA).

Ministério da Administração Territorial (MAT).

Ministério do Ordenamento do Território e Habitação (MINOTH).

Instituto Nacional de Ordenamento do Território e Desenvolvimento Urbano (INOT).

Instituto de Geodesia e Cartografia de Angola (IGCA).

Direcção Provincial do Ordenamento do Território, Urbanismo e Ambiente (DPOTUA).

Direcção Provincial da Agricultura e do Desenvolvimento Rural (DPADR).

Conselho de Auscultação e Concertação Social (CACS).

The FFS/APFS model was developed by FAO some 25 years ago and has been since replicated in different parts of the world, including Angola.

During PPG phase, the Capacity Needs Assessment looked into this important player for the promotion of SLM and rural planning at farm level, finding that many EDAs have committed and trained extension workers that are receiving a very consistent support in training and infrastructure through SADPC (alias MOSAP II).

Centro de Desenvolvimento Agrário (CDA).

With the current natural growth rate in Angola, by project end, the population within these sites may reach 100,000 people.

- Currently, an important number of FFSs are either established or being established in the municipalities of Lunduimbali (where Alto Hama is located), Bailundo and Chipipa within Huambo Province, as well as in other Provinces (e.g. in Bié and Malange). A total of 26 communes currently have active AP/FFSs or in the process of being created, for which the extension services to the communities are maintained either by donor projects or government programs (according to Mr. Cyprien Ndambi Ndoki, coordinator of Project SADCP in Huambo, consulted by the PPG Team on 13 Nov 2018.). In Benguela, two APFSs remained active as a legacy from a previous FAO GEF Project RETESA).. By having one demo site in Chongoroi, where the predominant land-use is pastoral, and two in Alto Hama and Bailundo, which are predominantly agricultural, provides the Project with an interesting set of land-use types and approaches to extension (e.g. the important differences between APFS and FFS).

Huambo Baseline and Data Assessment Studies, Huambo Provincial Government, Angola Alliance, 2004.

Using 2000 as a baseline year, as per several maps that illustrate the land-use progression in the PRODOC Atlas in Annex A.

At this writing hour (March 2019), a national forestry inventory has been carried out with support from FAO, but its results are not available.

See https://www.globalforestwatch.org/.

The GFW estimates consider 2000 tree cover, at a more than 30% tree canopy cover. These estimates do not take into account tree cover gain. Angola also gained forest in the 2001 to 2017 period, within an area of 63.8Kha, considering >50% tree canopy.

See Ministry of Agriculture (2016): Perspectiva Nacional e Resumo dos Resultados da Análise de Base sobre a Economia do Agregado Familiar.

Cited by Angola Alliance (2004), a study by Beatriz Marcelino showed that fertility levels were low and chemical or organic fertilizers would be required, even when land had been left fallow for about 15 years or when land had been occupied by non-native forests for more than 25 years, in Marcelino,B. (1996). Assessment of slowly exchangeable potassium reserves in some African ferrasoils. SAFE. Silsoe, England, Cranfield.

Also at province-level, as in the case of Huambo there have been initiatives normally related to isolated projects and which have produced relevant data for AEZ. Other examples are listed in the previous section describing baseline initiatives.

Another aspect is institutional (which is also related to Barrier #3). The Ministry of Agriculture (MINAGRIF) has a clear agricultural development agenda, and possibly regards ‘ecology’ and the need to ensure ‘soil adequacy’ based on agroecological conditions as a lower priority. The Ministry of Environment (MINAMB), the proponent of this project, has a different agenda, which includes not just the SLM “flag”, but also biodiversity protection, its mainstreaming into sectoral policies, the adequate management of ecosystem services, climate change and environmental due diligence – to mention a few.

Lei do Ordenamento do Território e Urbanismo (LOTU).

The 2013 “Plano Estratégico de Ambiente da Província do Huambo”.

One should always bear in mind that in Angola the term “municipality” is used to refer to much larger territories than in most other national administrative systems, and include the so called ‘comunas’, which would be more comparable to the size of an average European municipality.

Such as those of the Angola Development Bank.

This overview is sourced from FAO’s 1996 publication: “Agroecological Zoning: Guidelines” in FAO Soils Bulletin 73, Soil Resources, Management and Conservation Service. For more details, this publication can be found at: http://www.fao.org/docrep/w2962e/w2962e00.htm#P-2.

For more information on the theoretical underpinnings and methodologies of the AP/FFS approach, refer to FAO’s publication “Farmer Field School Guidance Document: Planning for quality programmes”, available at http://www.fao.org/3/a-i5296e.pdf.

This overview is sourced from FAO’s 2016 publication: “Negotiation, environment and territorial development: Green Negotiated Territorial Development (GreeNTD) - More than a methodology - an approach for improving equitable access and sustainable management of territories”. For more details, the same publication is available at: http://www.fao.org/3/a-i6603e.pdf.

This global program is implemented in cooperation with numerous partners, including  the Global Environment Facility (GEF), the International Union for Conservation of Nature (IUCN), Food and Agriculture Organization of the United Nations (FAO), United Nations Development Program (UNDP), United Nations Environment Program (UNEP), the European Space Agency, International Soil Reference and Information Centre, Joint Research Centre of the European Commission, World Resources Institute (WRI), Soil Leadership Academy (SLA).

This overview is based on different UNCCD publications. More details and various resources are available at: https://knowledge.unccd.int/knowledge-products-and-pillars/ldn-target-setting-building-blocks/land-degradation-neutrality-ldn-0.

In Huambo, IRCEIA will target the following municipalities: Bailundo, Londuimbale, Mungo, Catchiungo, Caala, Ekunha, Huambo and Tchicala-Tcholoanga

See section 2.1.1 Institutional Framework and Coordination for a full description of the composition of the AEZ technical unit.

See e.g. the following relevant publication on the mentioned conceptual framework: Orr, B. et al. (2017), accessible, among other related ones, through the Portal: http://knowledge.unccd.int.

Both the LDN process and FAO’s CBDS unit favor the approach of using primarily national data (if sufficiently adequate) to be complemented when necessary by GIS global sources.

Currently, the mandate and attributions of the AECs are currently under review by government. If there will be important changes to these and which may have a bearing on the feasibility of certain project activities, the team will adapt them to the new circumstances.

Production landscapes targeted by the project were assessed at 409,699. For rounding-off purposes ‘at least 400,000 ha’ were considered. Refer to Table 2 for details, including the break-down per demo site land use.

Of the full specific target list, only one target does not apply to the project’s wider landscape: “30% increase in water availability in deprived areas of the transhumance triangle (Cunene, Huíla and Namibe)”.

Council for Social Consultation and Concertation / “Conselho de Auscultação e Concertação Social”.

Plano de Ordenamento Rural (POR).

This has meant that PDMs have generally only included detailed planning for the urban areas of municipalities. This would not have been problematic if the PDM had been complemented by Environmental Spatial Plans (POAs) and Rural Land-Use Plans (PORs) as foreseen by the country’s planning system, but such plans have failed to materialize in Angola in any systematic form.

The full municipal coverage of the PORs lies outside the scope of this project.

According to Law 15/16 of September 12 that regulates the functioning of local administrations, “the holder of the Executive Branch, [i.e. the municipal administrator] establishes the structure and defines the competence of municipal administration services, taking into account the economic, geographical and social realities of each municipality, and may delegate to the head of the central body responsible for the administration of the territory”. This means that the exact composition of the municipal technical teams may vary greatly according to existing needs and capacity. However, such teams typically include technical officers in areas such as agriculture, forestry, urban planning, health, education and community services (water, energy and waste).

SASSCAL has received a limited number of project proposals from Angola, probably a sign of low capacity to develop project proposals.

The scale considerations in the landscape approach, the topic is e.g. covered in Minang et al. (2015) concerning interactions and interrelations among ecological and jurisdictional scales in a nested approach to landscape management. The paper served as inspiration for the project. Refer to: Box 2. The tiered nested approach to spatial planning and landscape-level management for SLM.

Surface areas are estimates to be refined during project inception.

Due to its late inclusion as a proposed project site, Bailundo was not surveyed during PPG.

Plano de Desenvolvimento Nacional (PDN).

Plano Médio Prazo do Sector Agrário (PMPSA).

Programa de Acção Nacional de Combate à Desertificação (PANCOD).

The final evaluation concluded that there is evidence that the capacities of communities have been strengthened through the adoption of more sustainable techniques for agricultural systems and pasture, and that the livelihoods of beneficiary households have been improved. Environmental benefits are less visible given their longer-term nature. In technical terms, public institutions are in general more capable and knowledgeable about the approaches introduced for environmental management and planning.

In Benguela and Huambo, the targeted municipalities were: Cubal, Huambo, Katchiungo, Tchicala Tcholohanga, Bailundo, Ekunha, Longonjo and Caala.

Lessons drawn from the Project Document: “Land rehabilitation and rangelands management in smallholders agro-pastoral production systems in south western Angola” – GCP/ANG/048/GFF, combined with lessons learned from MOSAP.

The PDMs for Londuimbali and Bailundo were prepared in 2011 by the consultancy firm Austral Investik. In addition, the firm ECM produced a Biophysical characterization of these municipalities for monitoring the implementation of the PDMs.

As an example of an exception to the habit of hiring foreign firms to produce spatial plans, the PDM for Chongoroi was produced by the Angolan consultancy firm Soapro in 2012.

Plano Estratégico do Ambiente do Huambo - Mar 2013.

The objective of including a “Project Political Coordinator” is to strengthen ownership by governmental counterparts and by other national institutions. This inclusion reflects a recommendation emanating from the RETESA Project, which suffered considerably from very low national ownership.

Same as in the previous footnote.

The status of operability of the mentioned equipment was not assessed but should be reported upon by CETAC during MoU negotiations.

Figures from CIE/UCAN’s “Relatório Económico” and “Jornal DW”.

With reference to FAO’s Guidance Note on Gender Mainstreaming in project identification and formulation.

The topic is discussed in the PRODOC ancillary document ‘GEF-6 Request for the Project Endorsement’ (i.e. the GEF’s CEO Endorsement Request, which accompanies the PRODOC when submitted to the GEF for final approval), in the document’s Part II, Section A (changes in alignment with the project design with the original PIF).

See e.g. Wikipedia entry “Línguas de Angola” (accessed in Oct 2018) and other information iteratively derived from it.

Home site: https://www.iwgia.org/en/

Including ILO Convention 169 (Indigenous and Tribal Peoples Convention, 1989), the UN Declaration on the Rights of Indigenous Peoples (2007), UNDG Guidelines on Indigenous Peoples’ Issues, the UN Permanent Forum on Indigenous Issues and the Inter-Agency Support Group on Indigenous Issues.

Source: IWGIA – The indigenous world – 2015. See also IWGIA’s (Interactive) Yearbook for 2018: (https://www.iwgia.org/en/resources/yearbook)

Other groups are mentioned in IWGIA (2015): the Kwisi and Kwepe, which are Khoe-San, but also the Himba (including Kuvale and Zemba). The latter are Herero-speaking minority groups.

José Redinha’s map is displayed in Wikipedia under “Línguas de Angola”.

See e.g.: World Bank (2007): Environmental and Social Management Process Report. Volume 2 – Environmental and Social Diagnosis and Institutional and Legal Framework. Refer to section 3.11.7 - Cultural Heritage, pp. 71-73.

Oral reporting by PPG Team Member in charge of local level consultations, gender stakeholder engagement and gender.

IWGIA (2015).

For more information, see: http://intranet.fao.org/fileadmin/user_upload/osp/risk/BeginnersGuideRisk-Dec2013.pdf

Refer to: http://www.fao.org/nr/gaez/contact-us/en/.