FINAL REPORT -Mid-Term Review of the UNEP/GEF project titled

“INSTITUTIONAL CAPACITY STRENGTHENING FOR IMPLEMENTATION OF THE NAGOYA PROTOCOL ON ACCESS TO GENETIC RESOURCES AND BENEFIT SHARING IN UGANDA”

GEF ID: 9481

Ecosystems Division, GEF – Biodiversity and Land Degradation Unit

December 2025

Photos Credits:

Front cover:

Photo 1 (Upper Left): Collaborative Forest management (CFM) by the National Forest Authority (NFA)  in Mt Moroto Central Forest Reserve (CFR)

Photo 2 (Upper Centre): Mr. Mbusa Ernest’s Prunus africana Tree Nursery in Kanungu district

Photo 3 (Upper Right): Training of IPLCs on the values and propagation of sandalwood

Photo 4 (Lower Left): NCRI UOBDU and Batwa during collection of herbal medicine samples in Mgahinga

Photo 5 (Lower Centre): Sandalwood Propagation process (Signpost at Nabuin ZARDI)

Photo 6 (Lower Right): Training of IPLCs on the values and propagation of sandalwood

Photo 7 (Bottom): Sandalwood seedlings being raised in the nursery at Nabuin ZARDI

© UNEP/Cliff Bernard Nuwakora, United Nations Environment Programme, Review Mission (2025)

This report has been prepared by an external consultant as part of a Mid-Term Review, which is a management-led process to assess performance at the project’s mid-point. The UNEP Evaluation Office provides templates and tools to support the review process. The findings and conclusions expressed herein do not necessarily reflect the views of Member States or the UN Environment Programme Senior Management.

For further information on this report, please contact:

Evaluation Office of UNEP 
P. O. Box 30552-00100 GPO
Nairobi Kenya 
Tel: (254-20) 762 3389
Email: unep-evaluation-director@un.org

Website: https://www.unep.org/about-un-environment/evaluation

Project Title: “Institutional Capacity Strengthening for Implementation of the Nagoya Protocol on Access to Genetic Resources and Benefit Sharing in Uganda” GEF ID: 9481

Project number: 9481

Date: December/2025

All rights reserved.

© (2025) UNEP

ACKNOWLEDGEMENTS

This Mid-Term Review was prepared for the United Nations Environment Programme (UNEP) Ecosystems Division / GEF Biodiversity Unit by Mr. Cliff Bernard Nuwakora, an Independent Consultant.

The reviewer would like to express sincere gratitude to all persons met and those who contributed to this review, as listed in Annex II.

The review team wishes to thank Mr Johan Robinson, the Portfolio Manager, Ms. Jane Nimpamya, the UNEP/GEF Task Manager, George Saddimbah, the UNEP FMO, Aska Achiel, the UNEP Snr. Programme Assistant and the country project management team and, in particular, Mr. Francis Ogwal the Project Coordinator, Mr. Simon Peter Achuu, the Project Manager and Ms. Diana Nakandi all employees of the National Environment Management Authority (NEMA), for their dedicated contributions, transparency, and collaboration throughout the review process.

Sincere appreciation is also extended to the National Project Steering Committee (NPSC) members who provided valuable comments during the generation of information that constituted to this project draft mid-term review report.

The reviewer further acknowledges the support of the Government of Uganda, specifically the Ministry of Water and Environment (MWE), the Uganda National Council for Science and Technology (UNCST), the Uganda Wildlife Authority (UWA), the National Forestry Authority (NFA), Makerere University, National Forestry Resources Research Institute (NaFORRI), the Uganda Registration Research Bureau (URSB), Natural Chemotherapeutic Research Institute (NCRI) and the Indigenous Peoples’ organizations United Organisation for Batwa Development in Uganda (UOBDU) and the Karamoja Women Cultural Group (KWCG), whose collaboration enriched the review.

Special acknowledgement goes to the Batwa and Karamojong Indigenous Peoples and Local Communities, district local governments of Abim, Moroto, Nakapiripirit, Amudat, Kotido, Kabong, Napak, Kisoro, Kanungu, Rubanda, and Bundibugyo, and all stakeholders and UNEP who generously shared their experiences during the field missions.

The reviewer hopes that the findings, conclusions, and recommendations from this Mid-Term Review will contribute to the successful finalization of the current project, the formulation of its subsequent phase if any, and the continuous improvement of similar UNEP/GEF initiatives in other countries and regions.

BRIEF EXTERNAL CONSULTANT(s) BIOGRAPHY

Mr. Cliff Bernard Nuwakora is an independent Development Policy, Governance, and Monitoring & Evaluation specialist with over 20 years of experience in Mid-Term and Terminal Evaluations for GEF, UNDP, EU, AfDB, and bilateral partners across Africa, Asia, the Pacific, and Europe. He holds master’s degrees in Environmental Policy from Fort Hare University and Makerere University, complemented by postgraduate training in International Human Rights Law (Lund University, Sweden). He has directed numerous environmental and institutional capacity-strengthening evaluations, including projects on biodiversity governance, climate resilience, and access-and-benefit-sharing (ABS). Mr. Cliff Bernard Nuwakora is highly experienced in applying GEF evaluation tools, Theory of Change reconstruction, and rights-based approach, and gender-responsive analysis.

Review Team: Cliff Bernard Nuwakora (cliff.nuwakora@gmail.com)

ABOUT THE REVIEW

Joint review: No

Report Language(s): English.

Review Type: Mid-term Review

Brief Description: This report presents the Mid-Term Review (MTR) of the UNEP/GEF Project “Institutional Capacity Strengthening for Implementation of the Nagoya Protocol on Access to Genetic Resources and Benefit Sharing in Uganda” (GEF ID 9481), implemented between January 2020 and December 2025. The overall goal of the project is to strengthen Uganda’s institutional, legal, and technical capacity to implement the Nagoya Protocol on Access to Genetic Resources (GRs) and the Fair and Equitable Sharing of Benefits Arising from their Utilization (ABS). The project seeks to ensure that Uganda’s genetic resources and associated traditional knowledge are accessed, utilized, and shared in ways that contribute to biodiversity conservation, community well-being, and national development. The review sought to assess project performance to-date, identify strengths, weaknesses, and risks, and provide actionable recommendations to support the remainder of implementation.

Key words: Access and Benefit Sharing (ABS), Genetic Resources, Nagoya Protocol, Biodiversity, Institutional Capacity Strengthening, Indigenous Peoples and Local Communities (IPLCs), Uganda.

Primary data collection period: September – November, 2025

Field mission dates:

- Western Region (Kigezi – Batwa IPLC site): 14–22 October 2025

- Northeastern Region (Karamoja – Karamojong IPLC site): 26–30 October 2025

- National-level Consultations (Kampala, Entebbe, and Moroto): September 2025

TABLE OF CONTENTS

I. EXECUTIVE SUMMARY	11

II. THE PROJECT	16

A.	Context	16

B.	Summary of Project Design Strengths and Weaknesses	17

C.	Results Framework	17

D.	Project Implementation Structure and Partners	18

E.	Stakeholders	19

F.	Changes in Design during Implementation	20

G.	Project Financing	20

A.	Data Collection	22

B.	Data Analysis	24

C.	Limitations and Mitigation Strategies	24

D.	Ethical Considerations	24

IV. THEORY OF CHANGE AT MTR	25

V. REVIEW FINDINGS	28

A.	Strategic Relevance	28

B.	Effectiveness	29

C.	Financial Management	45

D.	Efficiency	49

E.	Monitoring and Reporting	50

F.	Exit Strategy & Sustainability	51

G.	Factors Affecting Performance and Cross-Cutting Issues	53

VI CONCLUSIONS AND RECOMMENDATIONS	56

A.	Conclusions	56

B.	Lessons learned	58

C.	Recommendations	60

ANNEX I: RESPONSE TO STAKEHOLDER COMMENTS	63

ANNEX II:	PEOPLE CONSULTED DURING THE REVIEW	64

ANNEX III: KEY DOCUMENTS CONSULTED	67

ANNEX IV: REVIEW ITINERARY	69

ANNEX V: COMMUNICATION AND OUTREACH TOOLS	70

ANNEX VI: SAFEGUARDS ASSESSMENT TOOL	71

ANNEX VII: BRIEF CV OF THE EVALUATOR	75

ANNEX VIII: GEF PORTAL INPUTS (FOR GEF FUNDED PROJECTS)	77

ANNEX IX: GEF RISKS TO ACHIEVING PROJECT OUTCOMES	81

ANNEX X: IMPLEMENTATION PLAN OF RECOMMENDATIONS	83

ANNEX XI: QUALITY ASSESSMENT OF THE REVIEW REPORT	84

ANNEX XII: SELECTED PHOTOS FOR ABS MTR REPORTING	85

List of Tables

Table 1: Project Identification Table	9

Table 2: Summary project ratings	12

Table 3: Summary recommendation implementation plan	15

Table 4: Summary of project's latest approved results framework	18

Table 5: Key stakeholder and their roles	19

Table 6: (a) GEF budget amount disbursements and expenditures as at 30th sept 2025	20

Table 6b: Co-financing	21

Table 7: Review Respondents and Field Visits	22

Table 8: Justification for reformulation of results statements	25

Table 9: Justification for reformulation / expansion of drivers and assumptions	26

Table 10: Progress Towards Project Outputs	30

Table 11: Progress Towards Project Outcomes	35

Table 12: Likelihood of impact	42

Table 13: Financial management	46

Table 14: Project Extension	50

Table 15: Project Performance Ratings	57

Table 16: Response to stakeholder comments received but not (fully) accepted by the reviewer, where appropriate.	63

Table 17: GEF portal inputs	77

List of Figures

Figure 1: Project intervention locations	16

Figure 2: Project Governance	19

Figure 3: Project Intervention Logic – Theory of Change	27

Figure 4: Some of the medicinal extracts developed together with the Batwa	35

Figure 5: Diseases as reported by beneficiary groups	44

LIST OF ACRONYMS

| Acronym | Full Meaning |
| --- | --- |
| ABS | Access and Benefit Sharing |
| ATK | Associated Traditional Knowledge |
| BIOFIN | Biodiversity Finance Initiative |
| CBD | Convention on Biological Diversity |
| CFM | Collaborative Forest Management |
| COP | Conference of the Parties |
| CSO | Civil Society Organization |
| DLG | District Local Government |
| EA | Executing Agency |
| E&S | Environmental and Social |
| EHS | Environment, Health and Safety |
| ESS | Environmental and Social Safeguards / Standards |
| FGD | Focus Group Discussion |
| GEF | Global Environment Facility |
| GoU | Government of Uganda |
| GRs | Genetic Resources |
| HS | Highly Satisfactory |
| ICCA | Indigenous Community Conserved Area |
| ICT | Information and Communication Technology |
| IGA | Income Generating Activity |
| ILO | International Labour Organization |
| IPLCs | Indigenous Peoples and Local Communities |
| IT | Information Technology |
| JFU | Joint Financing Unit (GEF/UNEP coordination) |
| KII | Key Informant Interview |
| KM | Knowledge Management |
| KWCG | Karamoja Women Cultural Group |
| L | Likely |
| M&E | Monitoring and Evaluation |
| MAT | Mutually Agreed Terms |
| MEL | Monitoring, Evaluation and Learning |
| MoFPED | Ministry of Finance, Planning and Economic Development |
| MTR | Mid-Term Review |
| MWE | Ministry of Water and Environment |
| NARO | National Agricultural Research Organisation |
| NaFORRI | National Forestry Resources Research Institute |
| NBSAP II | National Biodiversity Strategy and Action Plan II |
| NCRI | Natural Chemotherapeutic Research Institute |
| NEMA | National Environment Management Authority |
| NFA | National Forestry Authority |
| PSC | Project Steering Committee |
| PGRC | Plants Genetic Resources Centre |
| PMU | Project Management Unit |
| PIC | Prior Informed Consent |
| PIR | Project Implementation Report |
| PPE | Personal Protective Equipment (in reference to safeguards) |
| POW | Programme of Work (UNEP) |
| ProDoc | Project Document |
| PSC | Project Steering Committee |
| PWD | Persons with Disabilities |
| RTOC | Reconstructed Theory of Change |
| S | Satisfactory |
| SDG | Sustainable Development Goal |
| ToC | Theory of Change |
| ToR | Terms of Reference |
| UCC | Uganda Communications Commission (in digital compliance context) |
| UOBDU | United Organisation for Batwa Development in Uganda |
| UNCST | Uganda National Council for Science and Technology |
| UNDP | United Nations Development Programme |
| UNEG | United Nations Evaluation Group |
| UNEP | United Nations Environment Programme |
| UNESCO | United Nations Educational, Scientific and Cultural Organization |
| URSB | Uganda Registration Services Bureau |
| UWA | Uganda Wildlife Authority |

PROJECT IDENTIFICATION TABLE

Table 1: Project Identification Table

| UNEP SMA ID: | GEF ID: 9481 SMA: 36393 |  | Grant ID (if applicable): |  | GFL-11207-14AC0003-SB-009251 |
| --- | --- | --- | --- | --- | --- |
| UNEP Management (Division/Branch/Unit): | Ecosystems Division, Biodiversity and Land Branch, GEF Biodiversity and Land Degradation Unit. |  |  |  |  |
| Executing Agency/ Implementing Partners: | National Environment Management Authority (NEMA) |  |  |  |  |
| Sources of Funding: | Country(ies): Uganda |  |  | Institution Name/Type: NEMA/Government |  |
| Relevant SDG(s): | Goal 1: End poverty in all its forms everywhere. Goal 2: End hunger, achieve food security and improved nutrition, and promote sustainable agriculture. Goal 5: Achieve gender equality and empower all women and girls. Goal 8: Promote sustained, inclusive, and sustainable economic growth, full and productive employment, and decent work for all. Goal 12: Ensure sustainable consumption and production patterns. Goal 13: Take urgent action to combat climate change and its impacts. Goal 15: Protect, restore, and promote sustainable use of terrestrial ecosystems, manage forests sustainably, combat desertification, halt and reverse land degradation, and halt biodiversity loss. |  |  |  |  |
| MTS (all that apply): | UNEP Medium Term Strategy 2022-2025 |  | UNEP approval date: |  | 2021-01-26 |
| POW Direct Outcome(s) number/reference (applicable for projects approved from 2022): OR POW Output(s) number/reference7 (applicable for projects approved pre-2022): | POW Direct Outcome: Indicator: Nature (i) Number of national or subnational entities that, with UNEP support, adopt integrated approaches to address environmental and social issues and/or tools for valuing, monitoring and sustainably managing biodiversity. Direct outcomes: 2.5, 2.6, 2.7, 2.8 |  | MTS 2025 Outcome(s) number/reference7 (applicable for projects approved from 2022): OR POW Expected Accomplishment(s) number/reference7 (applicable for projects approved pre-2022): |  | MTS 2025 Outcome: 2A; An economically and socially sustainable pathway for halting and reversing the loss of biodiversity and ecosystem integrity is established. 2B: Sustainable management of nature is adopted and implemented in development frameworks. |
|  | POW Output: |  |  |  | POW Expected Accomplishment: N/A |
| Sub-programme: | Nature action |  | Programme Coordination Project (if relevant): |  | Conservation |
| Expected start date: | 2020-07-06 |  | Actual start date: |  | 2021-01-27 |
| Planned completion date:8 | 2025-12-31 |  | Actual operational completion date: |  | N/A |
| Planned project budget at approval: | Planned Core Funding (regular budget, Environment Fund, etc.): GEF Amount: USD 2,560,842 |  |  |  |  |
|  | Planned Extra-budgetary Funds: Cash: USD 2,100,000 In-kind: USD 7,135,000 |  |  |  |  |
|  | Total Planned Budget: USD 11,795,842 |  |  |  |  |
| Secured budget | Secured Core Funding (regular budget, Environment Fund, etc.): |  |  |  |  |
|  | Secured Extra-budgetary Funds: Cash: USD 2,100,000 In-kind: USD 7,135,000 |  |  |  |  |
|  | Total secured budget as of 2021-01-27: USD 11,795,842 |  |  |  |  |
| Actual expenditures reported (cash only): | Actual Core Funding expenditures reported as of 30th June 2025: USD 1,915,495 |  |  |  |  |
|  | Actual Extra-budgetary Funds expenditures reported as of 30th June 2025: USD 1,915,495 |  |  |  |  |
|  | Total actual expenditures reported as of 30th Sept 2025: 1,915,495 |  |  |  |  |
| First disbursement: | 26.04.2021 USD 126,000 |  | Planned date of financial closure: |  | 31st Dec 2026 |
| No. of formal project revisions: | None |  | Date of last approved project revision: |  | N/A |
| No. of Steering Committee meetings: | 5 |  | Date of Last Steering Committee meeting: |  | 15th Aug 2025 |
| Mid-term Review (required or not required): | UNEP requirement: | Yes | Mid-term Review actual date: |  | Sept 2025 – Jan 2026 |
|  | Donor requirement: | Yes |  |  |  |
| Terminal Evaluation (planned date): | 30th Jan 2027 |  | Terminal Review actual date: |  | TBC |
| Coverage Country(ies): | Uganda |  | Coverage - Region(s): |  | Africa |
| Dates of previous project phases: | N/A |  | Status of future project phases: |  | N/A |

# I. EXECUTIVE SUMMARY

Project Background

- The project “Institutional Capacity Strengthening for Implementation of the Nagoya Protocol on Access to Genetic Resources and Benefit Sharing in Uganda” (GEF ID 9481) was implemented by the United Nations Environment Programme (UNEP) and executed by the National Environment Management Authority (NEMA) on behalf of the Government of Uganda (GoU). The project started in January 2021 with USD 2,560,842 in GEF funding and USD 9,235,000 in co-finance from government and partner institutions and is expected to end in December 2026. The project’s rationale is rooted in Uganda’s need to operationalize its obligations under the Convention on Biological Diversity (CBD) and the Nagoya Protocol on Access and Benefit Sharing (ABS). The project aims to ensure that Uganda’s rich genetic resources (GRs) and associated traditional knowledge (ATK) are accessed and used legally and equitably, thereby contributing to biodiversity conservation and national development. The project objective is: “To strengthen the institutional, policy, legal, and technical capacity of Uganda to implement the Nagoya Protocol and ensure equitable sharing of benefits arising from the utilization of genetic resources and associated traditional knowledge.” Implementation involved a wide network of partners including UNCST, UWA, NFA, NaFORRI, NARO, Makerere University, URSB, UOBDU, KWCG, and selected district local governments (DLGs) in Karamoja and Kigezi regions.

This Mid Term Review

- This review assessed the project’s progress toward its planned results and objectives at Mid Term Level, identified challenges, and recommended corrective actions to improve performance during the remaining period. Performance was assessed against seven review criteria: Strategic Relevance, Effectiveness, Efficiency, Financial Management, Monitoring & Reporting, Sustainability, and Factors Affecting Performance using UNEP’s six-point rating scale (HS, S, MS, MU, U, HU). Data were collected through document review, key informant interviews, focus group discussions and field observations at pilot sites. Findings were triangulated against a reconstructed Theory of Change (ToC) and its causal pathways.

Key Findings

- The project has demonstrated strong performance in the areas of:

- Strategic Relevance: The project remains highly aligned with Uganda’s Vision 2040, National Development Plan IV (NDPIV), the National Biodiversity Strategy and Action Plan III (NBSAP III), and national commitments under the Convention on Biological Diversity (CBD) and Nagoya Protocol. It directly supports SDG 15 (Life on Land) and SDG 1 (No Poverty) through equitable benefit-sharing models that promote biodiversity conservation and strengthen community livelihoods.

- Effectiveness: Over 80% of planned outputs are on track, including validation of the draft ABS Policy, Regulations, Guidelines, and Gender Strategy, with only formal approval steps remaining. The ABS-eReg electronic permit and compliance system is 90% complete, piloted across key institutions, and technically ready for national deployment. Capacity-building achievements have exceeded expectations, with more than 230 officers and 27 institutions trained, alongside updated ABS curricula at Makerere University. Key checkpoints within UWA, NFA, URSB, UNCST, and Customs have been identified, trained, and integrated into national compliance mechanisms. Community pilots in Karamoja and Echuya CFR are demonstrating ABS-compliant livelihood models through TK documentation, sandalwood propagation, herbal product development, and strengthened community protocols. Awareness and communication interventions have surpassed targets, reaching more than 1.5 million people with gender responsive IEC materials and diverse media platforms. Women and youth participation has been strong across trainings, consultations, and ABS structures, contributing to inclusive and equitable implementation. Overall, the project demonstrates high effectiveness, strong institutional coordination, and clear progress toward sustainable ABS outcomes.

- Financial Management: As of 30th September 2025, 81% of GEF funds had been received by NEMA and 75% has been expended as per table 6a, the co-financing commitments remain on schedule. Financial reporting and partner accountability have improved across all entities.

- Efficiency: Initial implementation delays at the start of the project caused by COVID-19 restrictions and late fund disbursements extended the project by roughly 18 months. However, adaptive management measures including activity reprioritisation and remote coordination mitigated the challenges faced.

- Monitoring and Reporting: Regular Project Implementation Reports (PIRs), half-yearly progress reports, and field monitoring missions demonstrate systematic output tracking and proactive risk management. Adaptive learning has been integrated into planning cycles through quarterly partner meetings convened by NEMA.

- Sustainability: Strong institutional ownership from all participating partners combined with integration of ABS measures into national frameworks and community structures.

- Cross-Cutting Aspects: Gender mainstreaming and inclusion of Indigenous Peoples and Local Communities (IPLCs) are visible across all components. Over 1,800 stakeholders of whom 48% where women have been trained in ABS awareness, compliance, and policy implementation. Communication and outreach efforts have expanded national visibility of ABS through radio programmes, community dialogues, and national workshops.

The full ratings are presented in Table 2. These ratings indicate that while the project is delivering strong results and remains strategically well aligned, some implementation and institutional risks remain that require management attention cited below.

- Issues Requiring Senior Management Attention

The Mid-Term Review identifies the following strategic risks that require immediate attention by UNEP and the Government of Uganda to safeguard the sustainability and impact of the project:

- Delay in gazettement of the ABS Policy and Regulations. The ABS Policy, Regulations and Guidelines have been validated but are not yet gazetted. Continued delays threaten the legal enforceability of Uganda’s ABS framework and could leave project investments without a binding regulatory foundation.

- Institutional and financial sustainability of the ABS e-Permit System. While the electronic ABS permit and compliance system is technically advanced, long-term hosting, staffing, and budgetary provision within UNCST and NEMA are not yet secured. Without these, national ABS compliance and monitoring could weaken after project closure.

- Weak sub-national monitoring and private-sector engagement. Field-level monitoring remains resource-constrained, limiting data quality and adaptive management. In addition, limited private-sector and value-chain engagement risks reducing the commercialization and benefit-sharing potential of genetic resources and traditional knowledge.

- Gender and youth inclusion risks at community level. Although gender mainstreaming has been achieved at national level, targeted mechanisms for youth and women’s economic participation in community ABS pilots require strengthening to ensure equitable benefit-sharing and long-term livelihood impacts.

If these risks are not addressed during the remaining implementation period, there is a risk that the project’s strong technical achievements will not translate into durable, nationally embedded ABS systems.

Table 2: Summary project ratings

| Criterion | Rating |
| --- | --- |
| Strategic Relevance | Highly Satisfactory (HS) |
| Effectiveness | Highly Satisfactory (HS) |
| Financial Management | Satisfactory (S) |
| Efficiency | Moderately Satisfactory (MS) |
| Monitoring and Reporting | Satisfactory (S) |
| Sustainability | Likely (L) |
| Factors Affecting Performance | Satisfactory (S) |
| Overall Project Rating | Satisfactory (S) |

Conclusions

- Overall, the project’s performance at mid-term is rated Satisfactory (S). The review confirms substantial progress toward achieving the project’s overall objective of strengthening Uganda’s institutional, legal, and technical capacity to implement the Nagoya Protocol on Access to Genetic Resources and Benefit Sharing (ABS). Tangible results include the validation of the national ABS Policy and Regulations, operationalization of ABS checkpoints and implementation of community-level benefit-sharing pilots in Karamoja and Kigezi sub regions. The project has also made significant contributions to capacity building across institutions.

- The strongest performing aspects relate to the project’s strategic relevance, policy and institutional achievements, and broad stakeholder participation, particularly the integration of ABS principles into community-based forest management and traditional knowledge frameworks. Comparative weaknesses were observed in timely fund disbursement, staffing continuity, and monitoring resource allocation, which have slowed execution of certain field activities. However, these constraints are being mitigated through adaptive planning, strengthened coordination among NEMA, UNCST, and UNEP, and the use of consolidated partner reporting templates introduced in 2024.

The Mid-Term Review finds that the project remains highly relevant to Uganda’s biodiversity, legal and development priorities, and to global commitments under the Nagoya Protocol. The project is working effectively, having established validated legal instruments, functional institutional checkpoints, and operational community ABS pilots. However, the long-term sustainability of these achievements depends on timely gazettement of the ABS legal framework and full institutionalization of the e-permit system within UNCST and NEMA. Without these actions, the risk of losing project gains after closure remains significant.

- Lessons Learned

Lesson Learned #1. Early policy validation and legal anchoring are essential for national ownership and sustainability. The project showed that early validation of the draft ABS Policy and Regulations strengthened institutional coherence and accelerated Uganda’s compliance with the Nagoya Protocol. Fast-tracking gazettement will consolidate national ownership and provide an enforceable legal foundation for benefit sharing.

Lesson Learned #2. Digital tools improve governance and transparency but require sustained technical and financial support. The electronic ABS permit and monitoring system developed by UNCST is a major achievement, enabling real time oversight of access, compliance certification, and checkpoint reporting. However, long-term sustainability requires recurrent government funding, IT maintenance, and institutional hosting within UNCST’s core systems.

Lesson Learned #3. Multi-agency coordination enhances implementation efficiency and adaptive management but requires structured monitoring tools. Uganda’s ABS project included 10 implementing partners from State and Non-State actors. Collaboration among the partners has strengthened accountability, reduced duplication, and supported adaptive planning and management. Harmonized reporting formats and joint field missions enabled effective delivery of the project activities despite COVID-19 challenges.

Lesson Learned #4. Meaningful participation of IPLCs ensures legitimacy, cultural relevance, equity, and long-term sustainability. Pilots in Karamoja and Kigezi sub regions demonstrated that empowering Indigenous Peoples and Local Communities to document traditional knowledge, participate in decision making, and negotiate benefit sharing creates stronger compliance, cultural relevance, and ownership of ABS processes. These qualitative gains were not fully captured due to reporting tool limitations.

Lesson Learned #5: Early recruitment of the PMU is essential to avoid implementation challenges. Delayed recruitment of the Project Manager, Project Support officers resulted in nearly two years of limited project implementation and reporting.

Lesson Learned #6: Valorisation of genetic resources depends on private sector engagement and structured technology transfer mechanisms. Research and Development for herbal medicinal products and sandalwood propagation demonstrate commercial potential of the ABS value chain. The project shows that without purposeful Research, Development and commercialisation pathway, innovations risk remaining at pilot stage which undermines the principle of equity and benefit-sharing.

Lesson Learned #7. Gender-responsive ABS design strengthens equity and results. The project showed that embedding gender mainstreaming in project delivery enabled Batwa and Karamoja women to participate meaningfully in traditional knowledge documentation, benefit-sharing, and ABS value chains, strengthening social inclusion and sustainability of ABS outcomes.

Lesson Learned #8. Human-rights-based ABS approaches strengthen IPLC empowerment and compliance. The project demonstrated that applying PIC, MAT, and community protocols as empowerment tools increased IPLC ownership, reduced conflict, and improved legal compliance and legitimacy of Uganda’s ABS system.

- Recommendations

Recommendation #1: Finalize and gazette the National ABS Policy and Regulations to operationalize Uganda’s commitments under the Nagoya Protocol.

Recommendation #2: Operationalize and sustain the National e-Permit and Compliance Management System under the coordination of UNCST. Ensure regular system update, usage and maintenance.  Further training of checkpoints should be undertaken and expedite the development of the ABS Clearing House by Q2 2026.

Recommendation #3: Institutionalize a National ABS Coordination and Monitoring Framework. Constitute the Committee through a ministerial directive and provide budgetary support for quarterly coordination, progress review, and adaptive planning meetings among implementing and partner institutions by Q1 2026, with the MEL framework operational by mid-2026.

Recommendation #4: Enhance gender, youth, and IPLC participation in ABS implementation and community benefit-sharing mechanisms. Collaborate with UOBDU, KWCG, UNCST Gender Focal Points, and District Local Governments to ensure at least 50 percent female representation in training and decision-making structures and to mainstream youth-led livelihood initiatives in ABS pilot sites during 2025–2026 (Ongoing).

Recommendation #5: Strengthen sub-national awareness and capacity building for community-level ABS implementation. Address limited capacity among district officials and traditional leaders through training and institutional support to sustain community ABS initiatives and equitable benefit-sharing practices during 2025–2026 (Ongoing).

Table 3: Summary recommendation implementation plan

| Rec No. | Approved | Responsible Officer / Unit | Mechanism for Implementation |
| --- | --- | --- | --- |
| #1 | Yes | Ministry of Water and Environment (MWE) / National Environment Management Authority (NEMA) | Fast-track Cabinet approval and gazettement of the National ABS Policy and Regulations by Q2 2026, establishing a complete legal framework for compliance monitoring and equitable benefit-sharing. |
| #2 | Yes | Uganda National Council for Science and Technology (UNCST) / NEMA / URSB / UWA / NFA / Customs | Complete design, testing, and roll-out of the national e-permit and compliance-management system by Q3 2026, ensuring budget integration from FY 2026/27 and continuous capacity building and maintenance support. |
| #3 | Partially | NEMA (Project Management Unit – PMU) / MWE / UNCST | Constitute the National ABS Coordination and Monitoring Committee by Q1 2026, with a gender-inclusive membership, and operationalize the joint MEL framework by mid-2026 through quarterly coordination and review meetings. |
| #4 | Yes | United Organisation for Batwa Development in Uganda (UOBDU) / Karamoja Women Cultural Group (KWCG) / District Local Governments (DLGs) / UNCST Gender Focal Points | Mainstream gender, youth, and IPLC participating in all ABS activities including training and decision-making structures; achieve ≥ 50 % female representation and promote youth-led livelihood initiatives during 2025–2026. |
| #5 | Yes | NEMA / UOBDU / KWCG / District Local Governments | Strengthen district- and community-level capacity for ABS implementation through targeted training for district officials, traditional leaders, and community monitors; sustain benefit-sharing mechanisms during 2025–2026. |

# II. THE PROJECT

  - Context

Intervention context

- Uganda’s exceptional biodiversity underpins national food security, health, research, and economic development, yet the absence of a functional ABS system led to unregulated access to genetic resources, loss of traditional knowledge, and inequitable benefit distribution. Prior to this project, the 2005 ABS Regulations were outdated and weakly enforced, offering little control over resource utilization. The project therefore intervenes to tackle three linked barriers: (i) limited legal and institutional capacity to regulate access and ensure fair benefit sharing; (ii) low awareness and weak coordination among government, research, and community actors; and (iii) inadequate participation of IPLCs in decision-making and benefit-sharing processes. These gaps have contributed to unsustainable harvesting, erosion of genetic diversity, and lost economic opportunities. Through policy reform, capacity building, and community-based pilots, the project seeks to ensure that Uganda’s genetic resources are accessed and utilized legally, sustainably, and equitably supporting biodiversity conservation and human well-being. Operating at both national and sub-national levels, the project demonstrates ABS implementation in two contrasting regions: Kigezi (south-western Uganda), where Batwa communities around Bwindi and Mgahinga forests are documenting traditional knowledge and developing benefit sharing models; and Karamoja (north-eastern Uganda), where Karamojong communities in Kadam and Napak forest reserves integrate ABS principles into sustainable management of medicinal and aromatic plants. Together, these pilots reflect Uganda’s ecological and cultural diversity and provide replicable models for national scale-up.

Figure 1: Project intervention locations

Institutional context

- The project is implemented under UNEP’s Ecosystems Division, Biodiversity and Land Branch, GEF Biodiversity and Land Degradation Unit within the Biodiversity Sub-programme of the UNEP Programme of Work, contributing to Expected Accomplishment EA(a): “Countries increasingly integrate biodiversity considerations and ecosystem services into sectoral and cross-sectoral policies and planning frameworks.” UNEP acts as Implementing Agency, providing technical supervision and fiduciary oversight, while the NEMA serves as Executing Agency on behalf of the Government of Uganda. Core partners include the Uganda National Council for Science and Technology (UNCST), leading development of the national e-permit system; Uganda Wildlife Authority (UWA), National Forestry Authority (NFA), National Agricultural Research Organisation (NARO), National Forestry Resources Research Institute (NaFORRI), Uganda Registration Services Bureau (URSB), and Makerere University, supporting research, enforcement, and capacity building. At the community level, the United Organisation for Batwa Development in Uganda (UOBDU) and the Karamoja Women Cultural Group (KWCG) represent IPLCs in implementing pilot activities and documenting traditional knowledge.

- The project was endorsed by the GEF Chief Executive Officer on 6 July 2020, approved by UNEP’s Project Review Committee in November 2020, and a Project Cooperation Agreement (PCA) signed between UNEP and NEMA in January 2021. Initially planned as a five-year project (2021–2025), implementation was extended to December 2026 to accommodate early delays linked to COVID-19 restrictions and fund disbursement timelines. The total budget is approximately USD 11.8 million (USD 2.56 million GEF grant + USD 9.23 million co-finance). This Mid-Term Review (MTR) is the project’s first independent review and will inform the remainder of implementation and serve as a baseline for the Terminal review.

  - Summary of Project Design Strengths and Weaknesses

- The overall design of the Uganda ABS Project is conceptually strong and remains highly relevant to Uganda’s biodiversity priorities and international obligations under CBD and the Nagoya Protocol. The design demonstrates a clear understanding of the national context, with interventions logically organized around four components that address the legal, institutional, technical, and community dimensions of ABS. The project’s alignment with national frameworks, particularly NBSAP II, the National Environment Act (2019), and the National Intellectual Property Policy (2019) has ensured strong government ownership and coherence with ongoing national programmes.

- A key design strength lies in its multi-level implementation structure, combining national level policy and institutional reforms with sub national demonstration pilots among IPLCs. This dual approach allows for both policy testing and community validation, ensuring that lessons from field level practice inform policy development. The inclusion of UNCST as a technical lead on scientific compliance and NEMA as the coordinating authority creates a balanced arrangement that leverages respective institutional mandates.

- The design also integrates gender and social inclusion considerations, explicitly recognizing the role of women and IPLCs in biodiversity conservation and knowledge management. ToC presented in the project document is robust, with well-articulated causal pathways linking activities to outcomes and impacts. The logical framework clearly aligns project outputs to the ToC results chain, and indicators are measurable within the project’s timeframe.

- However, some weaknesses were noted. The implementation delays experienced were largely attributable to external procedural factors, including the complexity of inter-agency coordination and the longer than anticipated government legal and policy approval processes, which ultimately necessitated the one-year extension.

- A further design limitation relates to the monitoring and evaluation (M&E) architecture. Although M&E functions were assigned to NEMA and UNCST, the project lacked a consolidated system and dedicated resources for real-time results tracking and systematic learning. The absence of baseline socio-economic data for the community pilots also constrained the project’s ability to quantitatively assess livelihood, gender, and participation outcomes during early implementation.

- Despite these limitations, the overall project design remains robust, flexible, and well aligned with national ABS priorities. Its participatory and multi-sectoral structure has enabled the project to adapt effectively to emerging challenges, including COVID-19 disruptions, staffing transitions, and evolving institutional needs while maintaining coherence across components. These features continue to provide a strong foundation for long term sustainability, national ownership, and the integration of ABS systems into Uganda’s policy, institutional, and community frameworks.

  - Results Framework

- The project’s results framework provides a coherent hierarchy linking activities to outcomes, intermediate states, and overall impact. Structured around four interrelated components, it aims to strengthen Uganda’s institutional, policy, and technical capacity to implement the Nagoya Protocol on ABS. The framework integrates legal reform, institutional coordination, and community-based action, ensuring that interventions are mutually reinforcing and contribute to national ownership and long-term sustainability.

- At impact level, the project supports the conservation and sustainable use of biodiversity through equitable sharing of benefits from the utilization of genetic resources and associated traditional knowledge. The intended outcome is an operational national ABS system comprising coherent policy, legal, and institutional mechanisms consistent with the Nagoya Protocol.

- The four components together deliver these results: Component 1 strengthens the legal and institutional framework to make ABS policies and mandates coherent and enforceable; Component 2 builds institutional and technical capacity through tools, guidelines, and development of the national e-permit system; Component 3 demonstrates ABS implementation at community level, embedding benefit-sharing within forest management and traditional knowledge systems; and Component 4 promotes awareness, communication, and knowledge management to foster participation and national commitment. A dedicated Project Management Unit within NEMA, under UNEP oversight, coordinates and monitors all components in alignment with the project’s results framework.

Table 4: Summary of project's latest approved results framework

(Source: UNEP/GEF Project Document and MTR Evidence Pack, 2025)

| Results Statement | Description / Key Indicators |
| --- | --- |
| Project Objective | To strengthen the institutional, policy, legal, and technical capacity of Uganda to implement the Nagoya Protocol and ensure equitable sharing of benefits arising from the utilization of genetic resources and associated traditional knowledge. |
| Impact | Biodiversity in Uganda conserved and sustainably used through equitable Access and Benefit Sharing arrangements contributing to national development and community well-being. |
| Intermediate State | Functional national ABS framework operationalized, with regulatory, institutional, and community mechanisms in place and effective coordination among stakeholders. |
| Project Outcomes | - National ABS policy, legal and institutional frameworks operational and aligned to Nagoya Protocol. - Institutional and technical capacity of NEMA, UNCST, and sectoral agencies strengthened. - Community level ABS benefit-sharing mechanisms piloted and functional. - Public awareness and knowledge on ABS increased nationally. |
| Outputs | - Draft ABS Policy and Regulations validated and submitted for approval. - Institutional roles of checkpoints clarified and operationalized (NEMA, UNCST, UWA, NFA, and URSB among others). - Electronic ABS permit management system designed and under testing. - Two CFM agreements revised to integrate ABS principles (LILO and TECA). - 1,800 stakeholders trained on ABS awareness and compliance. - Communication and outreach materials developed and disseminated nationally. |

  - Project Implementation Structure and Partners

- The project applies a two-tier implementation structure consistent with UNEP/GEF procedures, comprising UNEP as the Implementing Agency and the NEMA as the Executing Agency. UNEP, through its Ecosystems Division – Biodiversity and Land Branch, provides strategic guidance, technical supervision, and financial oversight. NEMA manages day-to-day execution, fiduciary control, and stakeholder coordination through a Project Management Unit (PMU) that reports to a National Project Steering Committee (NPSC) chaired by NEMA and co-chaired by MWE.

- UNCST serves as the lead technical partner responsible for compliance oversight and development of the electronic ABS permit management system. Core partners; UWA, NFA, NARO, NaFORRI, URSB, and Makerere University contribute to research, enforcement, and institutional capacity-building. At community level, UOBDU and KWCG represent IPLCs in pilot implementation, while District Local Governments (DLGs) facilitate local coordination and integration into district plans. The governance structure promotes accountability and participatory oversight linking UNEP supervision with national and local implementation. Figure 2 depicts the organizational hierarchy and flow of coordination among agencies.

Figure 2: Project Governance

  - Stakeholders

- The project engages a diverse range of actors (Table 5) across policy, research, and community levels, each contributing to Uganda’s ABS framework. The project prioritises inclusivity through gender-responsive and participatory approaches. Women, youth, and persons with disabilities are actively involved in training, decision-making, and benefit-sharing, with women comprising about 48 percent of trained stakeholders. IPLCs and marginalised groups are recognised as rights-holders and key custodians of Uganda’s genetic resources, ensuring that implementation reflects social equity and sustainability.

Table 5: Key stakeholder and their roles

| Stakeholder | Stakeholder Type | Role in the Project | Power / Interest in the Project |
| --- | --- | --- | --- |
| MWE | Government (Policy Lead) | Provides policy direction and oversight. | High power / High interest |
| NEMA | Government (Executing Agency) | National Focal Point for the Nagoya Protocol; chairs the National Project Steering Committee (NPSC), Leads project implementation; coordinates partners; ensures compliance with UNEP/GEF procedures. | High power / High interest |
| UNCST | Government (Regulatory) | Issues research permits; enforces ABS compliance; provides technical guidance. | High power / Medium interest |
| Makerere University | Academia | Develops ABS related curricula; conducts capacity building and research on genetic resources and traditional knowledge. | Medium power / High interest |
| UWA | Government (Conservation) | Oversees access to wildlife genetic resources and enforces ABS agreements in protected areas. | Medium power / Medium interest |
| URSB | Government (Legal/IP) | Manages intellectual property rights related to genetic resources and traditional knowledge. | Medium power / Medium interest |
| District Local Governments | Local Government | Mobilize communities, support ABS pilot implementation, and integrate ABS into local development plans. | Low power / High interest |
| IPLCs (Batwa, and Karimojong) | Community | Custodians of genetic resources and traditional knowledge; participate in PIC and MAT processes. | Low power / Very high interest |
| UNEP | International (Implementing Agency) | Provides technical oversight, backstopping, and ensures adherence to GEF and UNEP policies. | High power / High interest |
| GEF Secretariat | International (Funding Agency) | Provides financing and monitors project performance for compliance with GEF policies. | High power / Medium interest |

  - Changes in Design during Implementation

- Since inception, the project has experienced limited adjustments in implementation arrangements rather than changes in design. The most notable was the approval of a no-cost extension by UNEP in March 2024, extending the completion date from December 2025 to December 2026. While not a design modification, this extension was introduced to accommodate delays arising from COVID19 restrictions during 2021–2022 and initial slowdowns in fund disbursement and mobilization, thereby ensuring sufficient time to complete all planned activities.

- In 2023, minor refinements were made to the project’s results framework to improve clarity and measurability of a few indicators, specifically those linked to the ABS e-permit system (under Component 2) and the community-based benefit sharing pilots (under Component 3). These refinements involved clarifying indicator wording and specifying measurement parameters to strengthen monitoring alignment. Importantly, they did not alter the project’s objective, scope, Theory of Change, or overall design. No other elements of the funded design including components, outputs, or institutional arrangements were changed during implementation. The MTR further noted that output 3.1.1 Model contractual clauses and codes of conduct on best practices on ABS developed and piloted is too broad hence the 4 pilots should have formed 4 separate outputs.

  - Project Financing

- The project GEF grant is USD 2,560,842, administered by UNEP as the Implementing Agency, and as of 30th September 2025, 81% of GEF funds had been disbursed and 75% has been expended as per table 6a below.

Table 6: (a) GEF budget amount disbursements and expenditures as at 30th sept 2025

| GEF project amount | 2,560,842 |  |
| --- | --- | --- |
| Date of disbursement | Amount | Percentages |
| 26th April 2021 | 126,000 | 5 |
| 29th August 2022 | 728,232 | 28 |
| 24th May 2024 | 892,375 | 35 |
| 20th June 2025 | 321,258 | 13 |
| TOTAL DISBURSED as at 30th sept 2025 | 2,067,865 | 81 |
| Expenditures as at 30th sept 2025 | 1,915,495 | 75 |
| Unspent balance as at 30th sept 2025 | 645,347 | 25 |

- The project co-financing amount is USD 9,235,000 from NEMA and partner institutions, including MWE, UNCST, UWA, NFA, NARO-PGRC, NARO/NaFORRI, Makerere University, and community-based organisations (UOBDU, KWCG). At MTR, 7,419,378 (80%) of co-financing commitments has been realised (as shown in table 6b below) and the rest remains on schedule.

Table 6b: Co-financing

| Sources of Co-financing | Name of Co-financier | Type of Cofinancing | Investment mobilised | Amount ($) |
| --- | --- | --- | --- | --- |
| Recipient Country Government | National Environment Management Authority (NEMA) | Grant | Investment mobilised | 375,000 |
| Recipient Country Government | National Environment Management Authority (NEMA) | In-kind | Recurrent expenditure | 1,167,500 |
| Recipient Country Government | Uganda Wildlife Authority (UWA) | Grant | Investment mobilised | 525,000 |
| Recipient Country Government | Uganda Wildlife Authority (UWA) | In-kind | Recurrent expenditure | 1,077,500 |
| Recipient Country Government | National Forest Authority (NFA) | Grant | Investment mobilised | 284,480 |
| Recipient Country Government | National Forest Authority (NFA) | In-kind | Recurrent expenditure | 400,214 |
| Recipient Country Government | Plant Genetic Resources Centre (PGRC) - National Agricultural Research Organization (NARO) | Grant | Investment mobilised | 146,264 |
| Recipient Country Government | Plant Genetic Resources Centre (PGRC) - National Agricultural Research Organization (NARO) | In-kind | Recurrent expenditure | 330,000 |
| Recipient Country Government | Uganda National Council for Science and Technology (UNCST) | Grant | Investment mobilised | 285,700 |
| Recipient Country Government | Uganda National Council for Science and Technology (UNCST) | In-kind | Recurrent expenditure | 693,720 |
| Recipient Country Government | National Forestry Resources Research Institute - National Agricultural Research Organization (NaFORRI-NARO) | Grant | Investment mobilised | 145,000 |
| Recipient Country Government | National Forestry Resources Research Institute - National Agricultural Research Organization (NaFORRI-NARO) | In-kind | Recurrent expenditure | 600,000 |
| Recipient Country Government | National Chemotherapeutic Research Institute (NCRI) | Grant | Investment mobilised | 134,000 |
| Recipient Country Government | National Chemotherapeutic Research Institute (NCRI) | In-kind | Recurrent expenditure | 475,000 |
| Recipient Country Government | Makerere University | Grant | Investment mobilised | 55,000 |
| Recipient Country Government | Makerere University | In-kind | Recurrent expenditure | 410,000 |
| Beneficiary | Karamoja Women Cultural Group | Grant | Investment mobilised | 10,000 |
| Beneficiary | Karamoja Women Cultural Group | In-kind | Recurrent expenditure | 90,000 |
| Beneficiary | United Organization for Batwa Development in Uganda | Grant | Investment mobilised | 10,000 |
| Beneficiary | United Organization for Batwa Development in Uganda | In-kind | Recurrent expenditure | 205,000 |
| TOTAL |  |  |  | 7,419,378 |

- In line with the UNEP review Policy (2022) and the UNEP Programme and Project Management Manual (PPMM), this MTR was undertaken to assess the progress, performance, and strategic direction of the Uganda ABS Project (GEF ID 9481). The review examined whether the project is on track to achieve its objectives, identified implementation challenges, and proposed corrective actions to enhance delivery and sustainability. It also provides formative insights to strengthen implementation during the remaining period and to inform the Terminal review.

- The primary audiences for the review findings are UNEP, MWE, and NEMA, together with the other core institutions, including; UNCST, UWA, PGRC, NFA, NaFORRI, Makerere University, and district local governments. Secondary audiences include the GEF Secretariat and IPLCs, who are key beneficiaries of strengthened ABS systems. The findings will support policy refinement, regulatory improvements, and operational learning across these actors.

  - Data Collection

Primary data sources

- The review used a mixed-methods approach, combining qualitative and quantitative data collection tools. Primary data were gathered through key informant interviews (KIIs), focus group discussions (FGDs), and field observations in pilot regions, complemented by an extensive document review. In total, 78 respondents (41 male, 37 female) were engaged, representing the project management team, partner institutions, implementing agencies, and beneficiaries.

Table 7: Review Respondents and Field Visits

| Stakeholder Group | Total Involved (M/F) | Contacted (M/F) | Responded (M/F) | Response Rate (%) |
| --- | --- | --- | --- | --- |
| Project Management Unit (NEMA) | 6 (3/3) | 6 (3/3) | 6 (3/3) | 100 |
| Implementing Agency (UNEP) | 3 (2/1) | 3 (2/1) | 3 (2/1) | 100 |
| Executing Partners (UNCST, UWA, NFA, NARO, URSB, Makerere Univ.) | 22 (13/9) | 20 (12/8) | 18 (11/7) | 90 |
| Beneficiaries (IPLC representatives, CFM groups) | 40 (18/22) | 30 (13/17) | 25 (10/15) | 83 |
| FGD-only Participants | 7 (5/2) |  |  | 100 |
| Total | 78 (41/37) | 59 (30/29) | 52 (26/26) | 88 |

- Field data collection was conducted through three mission clusters between September and November 2025. The first mission took place in Karamoja sub region between 14th – 17th October 2025 followed by Kigezi Sub-region between 22nd – 25th October 2025, focusing on the Batwa pilot site where community consultations and field observations were undertaken around the Bwindi and Mgahinga forest landscapes.

The MTR findings reveal that The ABS Project’s interventions in western Uganda were implemented across all four protected areas including Bwindi Impenetrable National Park, Mgahinga Gorilla National Park, Echuya Central Forest Reserve, and Semliki National Park. While Bwindi and Mgahinga featured more prominently due to the concentration of Indigenous Peoples and Local Communities (particularly the Batwa) and the visibility of activities such as community protocols, biodiversity documentation, and herbal knowledge valorisation, similar ABS-related work was undertaken in Echuya and Semliki. In Echuya CFR, the project collaborated with the National Forestry Authority to engage forest-adjacent communities, four community groups participated in the update of existing collaborative forestry management agreements. The agreements also identify priority genetic resources, and support awareness on ABS requirements for potential research and utilisation of non-timber forest products. The project also facilitated consultations with the Kanaba Batwa Community to ensure that IPLC perspectives and potential benefit-sharing arrangements were incorporated into ongoing capacity-building efforts. Similarly, in Semliki National Park, the project mobilised the Batwa community with the aim of strengthening their institutional readiness in embracing the ABS concept. The IPLCs participated in trainings organized by UWA and UOBDU. Facilitation was done by Bundibugyo local government and other national trainers.

The first mission was held in the Karamoja Sub-region (14th – 17th October 2025), covering the Kadam and Napak pilot areas to assess progress on community protocols and benefit-sharing initiatives among the Karamojong Indigenous Peoples. Furthermore, In Karamoja, the ABS Project implemented a structured set of interventions across the three targeted protected areas that is in Kadam CFR, Mt. Moroto CFR, and Napak CFR as identified in the project document. Working in partnership with the National Forestry Authority (NFA), district local governments, cultural leaders, and community-based organisations, the project facilitated extensive consultations, ABS awareness, and capacity-building on PIC, MAT, and sustainable access to genetic resources. A major outcome of these engagements was the development of eight (8) Collaborative Forest Management (CFM) agreements with forest-adjacent communities. These CFMs were developed through participatory processes and now provide a clear framework for community participation in forestry resource protection, regulated access, and potential benefit-sharing related to genetic resources and associated traditional knowledge. A recent report shows that, all eight CFMs had been fully developed and were awaiting signature and launch by NFA and the respective community groups. In addition to CFM development, the project supported the identification and documentation of priority indigenous practices for sandalwood access and benefit sharing in the Kadam Moroto and Napak belt.

The third mission comprised national level consultations in Kampala and Entebbe during September 2025, engaging implementing agencies, policy actors, and development partners to validate findings and triangulate field data with institutional reports.

The Consultant upon completion of the data collection presented the preliminary findings/draft report to the Technical Working Group (TWG) on 2nd December 2025 representing all the key implementing partners. Acopy of the PowerPoint Presentation is available upon request.

Strategies for Inclusivity.

- To ensure inclusivity, the review deliberately targeted both mainstream and marginalised stakeholders. Women, youth, and persons with disabilities were purposively included in focus groups and interviews. IPLCs were consulted in local languages, with interpreters facilitating dialogue to ensure meaningful participation. Divergent perspectives were sought from national, district, and community levels to balance institutional and community viewpoints and avoid bias.

Secondary Data Sources.

- Secondary data were drawn from the Project Documents, Inception Report (2025), PIR reports (2023–2025), co-financing commitment letters, progress reports including partner reports (NEMA, UNCST, NFA, NaFFORRI, GPRC, UOBDU, KWCG), financial statements, and national policy frameworks (ABS Policy Draft, NBSAP II, National Environment Act 2019). Additional materials included field reports, training records, and community CFM agreements.

  - Data Analysis

- Data were analysed using a triangulation approach, combining content analysis of documents, statistical summaries from progress reports, and thematic coding of interview transcripts. review findings were mapped against the reconstructed ToC and delivery of outcomes and outputs assessed using UNEP’s six-point rating scale (HS–HU). Cross-verification among data sources ensured reliability, while case evidence from Kigezi and Karamoja pilot sites provided grounded validation.

  - Limitations and Mitigation Strategies

- The review  did not encounter major limitations that affected the integrity or completeness of the findings. While some consultations required rescheduling due to the competing workloads of partner institutions, all respondents were eventually reached, and all necessary documents including financial records were made available in time for analysis. As such, the evidence base for this MTR is considered robust, and no methodological constraints materially influenced the conclusions.

  - Ethical Considerations

- The review adhered to UNEP’s Standards of Conduct and the UN Evaluation Group (UNEG) Ethical Guidelines (2020). Participation was voluntary and based on prior informed consent. Anonymity and confidentiality were maintained for all respondents, and no personal identifiers are used in this report. Photographs and testimonies were captured only with consent. Efforts were made to ensure that the voices of both mainstream and marginalised groups are equitably represented.

# IV. THEORY OF CHANGE AT MTR

- The Theory of Change for the Uganda ABS Project was reconstructed for this MTR drawing on the approved Project Document (2020), the Inception Report (2021), annual PIRs (2023–2025), and partner progress reports. While the project’s overall intent and causal logic remain broadly aligned with the original design, several results-level statements were refined to better reflect UNEP’s results terminology and the implementation progress observed to date.

- The ToC at review maintains the project’s ultimate goal, enhanced conservation and sustainable use of Uganda’s biodiversity through equitable ABS, while refining the intermediate outcomes to capture institutional, legal, and community-level changes observed during the first half of implementation. It illustrates how four interlinked components contribute to institutional strengthening, regulatory coherence, capacity development, and inclusive community engagement, while integrating key cross-cutting drivers such as gender equality, IPLC empowerment, and digital transparency through the ABS e-permit system.

Table 8: Justification for reformulation of results statements

| Formulation in Original Project Document (2020) | Formulation for Reconstructed ToC at the Review (2025) | Justification for Reformulation |
| --- | --- | --- |
| Long-Lasting Impact “Biodiversity and genetic resources in Uganda conserved and sustainably used.” | “Uganda’s biodiversity and genetic resources conserved and sustainably used through a functional national ABS system that ensures fair and equitable sharing of benefits arising from their utilization.” | Revised for specificity and alignment with Nagoya Protocol obligations and national ABS framework. |
| Intermediate States “Legal, institutional, and community systems established for ABS.” | “Operational policy, institutional, and community frameworks enabling coordinated implementation of ABS at national and local levels.” | Reformulated to reflect functional progress beyond establishment (e.g., operational checkpoints, community pilots). |
| Project Outcomes - National ABS policy and regulatory framework developed. - Institutional capacity strengthened. - Community ABS mechanisms piloted. - Awareness enhanced. | - National ABS policy and regulatory framework advanced toward formal adoption, with draft instruments validated through national processes and positioned for gazettement. - Institutional capacity for coordinated ABS implementation and compliance strengthened within mandated agencies, including NEMA, UNCST, UWA, NFA, NARO/NaFORRI, URSB, and Makerere University. - Community-based ABS models piloted and tested in selected sites to support fair and equitable benefit-sharing with IPLCs. - National awareness and stakeholder participation in ABS enhanced. | Updated to reflect achieved progress and clarify the nature of each outcome in operational terms. |
| Outcome Indicators | No changes were made to the approved indicator statements. Existing indicators were interpreted and applied in line with UNEP and GEF guidance to assess adoption, system functionality, and participation (including gender-disaggregated reporting) based on available project evidence. | Clarified to explain how existing indicators were used for assessment purposes at MTR, without modifying their original formulation or targets. |
| Outputs - Draft ABS Policy and Regulations developed. - Institutional checkpoints for ABS established. - Electronic permit management system designed. - Community ABS protocols and CFM agreements initiated. - Capacity-building delivered for ABS stakeholders. - Communication and outreach materials produced. | - Draft ABS Policy and Regulations validated. - Checkpoints operational within key institutions. - Electronic permit system developed. - Two CFM agreements revised to integrate ABS. - >1,800 stakeholders trained. - Outreach materials disseminated. | Consolidated to remove duplication across components and align with measurable deliverables. |
| Output Indicators | Added performance-based indicators (e.g., “% of institutions implementing ABS procedures”; “No of IPLC protocols developed”). | Enhanced measurability and alignment with GEF and UNEP reporting standards. |

Table 9: Justification for reformulation / expansion of drivers and assumptions

| Formulation in Original Project Document (2020) | Formulation for Reconstructed ToC at review (2025) | Justification for Reformulation |
| --- | --- | --- |
| Drivers - Government commitment to ABS implementation. - Institutional collaboration among key partners. - Awareness of ABS benefits. | - Strong political and institutional commitment to biodiversity governance and ABS policy adoption. - Functional inter-agency coordination through NEMA, UNCST, and NPSC. - Empowerment of IPLCs and gender inclusion as enablers of sustainability. - Operationalization of the electronic ABS permit system. | Expanded to include observed enabling factors particularly gender, IPLC participation, and digital tools that are central to sustaining outcomes. |
| Assumptions - Partners deliver on commitments. - Communities remain supportive. - Sufficient funding maintained. | - Policy approval and gazettement proceed within the project period. - Institutional coordination continues under national leadership. - Communities remain willing to engage in ABS practices. - UNEP and GoU maintain resource commitments through to closure. | Updated to reflect post-COVID realities and dependency on legal approval timelines. |

- The reconstructed ToC demonstrates how the project’s four components collectively contribute to achieving national ABS functionality. The causal pathway begins with outputs: legal instruments, capacity-building activities, institutional systems, and community pilots which lead to outcomes of improved institutional performance, legal clarity, and inclusive community participation. These outcomes generate intermediate states where Uganda operates a coordinated ABS framework supported by empowered institutions, informed stakeholders, and engaged IPLCs. Ultimately, these intermediate states contribute to the long-term impact of conserving Uganda’s biodiversity and ensuring equitable benefit sharing from its utilization.

- Several drivers underpin this causal logic: (i) sustained government and UNEP commitment; (ii) inter-agency collaboration and knowledge exchange; (iii) empowerment of IPLCs and gender responsive participation; and (iv) adoption of digital compliance systems. The main assumptions are that the ABS Policy will be gazetted within the project period, institutional coordination will remain strong, and financial resources will be sustained through closure. The ToC also embeds human rights and equality principles as cross-cutting commitments, ensuring that women, youth, and marginalised groups, including persons with disabilities benefit equitably from project interventions.

Figure 3: Theory of Change at review

Figure 3: Project Intervention Logic – Theory of Change

Source: PRODOC-Figure 3.

# V. REVIEW FINDINGS

This subsection assesses the strategic relevance of the Uganda ABS Project by examining the extent to which its design and implementation are aligned with global, regional, and national strategic priorities. In line with UNEP–GEF Mid-Term Review criteria, the analysis considers coherence with UN Environment Programme Medium-Term Strategy and Programme of Work, Global Environment Facility biodiversity focal area objectives, and Uganda’s obligations under the Convention on Biological Diversity and the Nagoya Protocol. Particular attention is given to whether the project addresses clearly articulated policy gaps, responds to evolving international biodiversity governance frameworks, and remains relevant to national development and conservation priorities.

The reveiw further examines complementarity and coherence with parallel national and regional initiatives, including biodiversity financing, regulatory reforms, and regional ABS capacity-building platforms. By situating the project within Uganda’s broader environmental governance architecture and ongoing regional ABS processes, this subsection evaluates whether the project adds distinct value, avoids duplication, and strengthens institutional synergies.

  - Strategic Relevance

Alignment to UNEP’s, Donors’ and Countries’ (global, regional, sub-regional and national) Strategic Priorities

|  | Assessment and Evidence of Alignment with Strategic Priorities | Level of Alignment |
| --- | --- | --- |
| UNEP Priorities | - Medium-Term Strategy (MTS 2022–2025): The project aligns with the Ecosystem Management and Environmental Governance subprogrammes under UNEP’s Medium-Term Strategy. It contributes directly to Outcome 1.4 (“Strengthened capacities for equitable benefit-sharing from natural resources”) and Outcome 2.3 (“Enhanced policy and institutional frameworks for biodiversity management”). - Programme of Work (POW 2022–2025): The project contributes to POW Output 1.4.2 (“Countries supported to operationalize biodiversity-related multilateral environmental agreements”). - Bali Strategic Plan for Technology Support and Capacity Building: The project builds national capacity in policy, regulation, research, and community-level implementation of ABS, consistent with Bali Plan Objectives 1 and 2. - South–South Cooperation: The project has facilitated regional knowledge exchange through participation in COMESA and African Union ABS technical forums. | Full |
| Donor Priorities | Fully aligned with the GEF Biodiversity Focal Area Strategy, particularly Objective 1 (“Mainstream biodiversity across sectors and landscapes”) and Objective 2 (“Catalyse sustainability of biodiversity use through ABS mechanisms”). UNEP, as GEF Implementing Agency, has ensured consistency with GEF-6 operational priorities, including capacity building for compliance with the Nagoya Protocol | Full |
| Country / Regional / Global Priorities | Fully aligned with Uganda’s National Biodiversity Strategy and Action Plan II & III (NBSAP II & III), which identifies ABS implementation as a national target. The project supports commitments under the Convention on Biological Diversity (CBD) and Nagoya Protocol, and contributes to the Vision 2040 goal of promoting sustainable use of natural resources. | Full |
| Complementarity / Coherence with other interventions | The project complements regional GEF initiatives such as the Pan-African ABS Programme and COMESA Biodiversity Cluster. At the national level, it aligns with related efforts under the National Development Plan IV (NDPIV), National Environment Act (2019) and Wildlife Act (2019), and complements NEMA’s Biodiversity Finance Initiative (BIOFIN) and UNCST’s Research Ethics and Biosafety Framework. Synergies are evident in shared institutional platforms and coordinated training. | Full |

Findings Statements on Strategic Relevance and Complementarity

- The project demonstrates a high level of strategic alignment with UNEP’s Medium-Term Strategy (2022–2025) and the GEF Biodiversity Focal Area priorities by directly supporting Uganda’s implementation of the Nagoya Protocol on ABS. It bridges global biodiversity commitments with national policy frameworks, translating multilateral environmental objectives into tangible national actions. This coherence across governance levels reflects a clear line of sight from international conventions to local implementation, ensuring the project’s continued relevance and contribution to global environmental governance.

- The project effectively addresses Uganda’s critical national priorities under the Nagoya Protocol, particularly the establishment of a legal, policy, and institutional framework for ABS. It was designed to fill key gaps in coordination, regulatory enforcement, and awareness among IPLCs, academia, and the private sector. Strategic partnerships with NEMA, NFA, NaFORRI, MWE, UNCST, Makerere University, UWA, and URSB have strengthened institutional legitimacy, national ownership, and cross-sectoral coordination.

- Complementarity with parallel national and regional initiatives, such as; NBSAP, BIOFIN, the Pan-African ABS Programme, and COMESA biodiversity platforms, has enhanced knowledge exchange, policy coherence, and resource efficiency. Furthermore, alignment with the Kunming–Montreal Global Biodiversity Framework (Targets 13 and 15) reinforces Uganda’s leadership role in advancing equitable benefit sharing and biodiversity conservation in Africa. The project’s integrated approach and strong institutional collaboration provide a model for replicable ABS governance in the region.

Rating for Strategic Relevance: Highly Satisfactory (HS)

  - Effectiveness

Availability of outputs

- By the mid-term point, approximately 85% of project outputs were either fully delivered or on track. The draft national ABS Policy and Regulations were validated and are now undergoing Cabinet review; the electronic permit system is 90% complete (with PIC, MAT, and permit issuance) and under live-testing; and coordination mechanisms through NEMA and the National Steering and Technical Committees are fully functional and meeting quarterly. Capacity-building targets have been exceeded by over 230 officers (42% women) trained across agencies, academia, and civil society supported by a standardized ABS Training Manual endorsed in 2023. A national roster of 63 ABS experts (44 male, 19 female) developed for long-term capacity building. 19 designated checkpoints trained in global certification and ABS monitoring; 28 checkpoints identified, 7 published on the ABS Clearing House. Two pilot ABS agreements with IPLCs (Batwa and Karimojong) demonstrate progress in community level implementation. The National Communication Strategy has achieved wide awareness, reaching more than 25,000 people through radio, TV, and community outreach, accompanied by simplified ABS materials translated into local languages. Gender and inclusion measures have been institutionalized through implementation of the Gender and Social Inclusion Plan (2022).

- The project has delivered several high-impact achievements that go beyond the formal log frame, including the development of Uganda’s genetic resource-based products, such as medicinal ointments, cough remedies, and Vaseline formulations now ready for industrial scale commercialization, representing a major step forward for ABS vaporization. In Karamoja, the establishment of a sandalwood nursery has provided a stock base for propagation thereby promoting sustainable harvesting and reducing pressure on Forest Reserve stocks previously threatened by illegal extraction. The project has also facilitated notable social gains, particularly among Batwa communities, where participation in herbal cultivation initiatives has enhanced social identity, cultural recognition, and economic inclusion.

Table 10: Progress Towards Project Outputs

| Availability of Outputs | Narrative Assessment of Progress | Sources of Information |
| --- | --- | --- |
| Output 1.1.1: National ABS regulatory frameworks in place and operational. Performance against indicator(s) and target(s) Draft ABS Policy & Regulations completed (2024); were finalised and validated by 60+ stakeholders (52% women). Submitted to the Top Ministerial Committee of Ministry of Water and Environment for ministerial clearance and approval. To date, three national regulatory frameworks have been drafted and are awaiting approval. These are: 1.The draft ABS policy 2024 2.The updated ABS regulations 2024 3.The updated ABS guidelines 2024 4.Draft Uganda Wildlife (Community Resource Access) Regulations, 2024 Other information, not related to the indicators, that demonstrates Output delivery: Development of options for integrating the MLS of the ITPGRFA to the National ABS framework | The output is well advanced, with strong technical quality and broad validation. Timeliness is reasonable for national policy processes. The project has realised its set target by drafting the ABS Policy and its attendant Regulations pending cabinet approval. Fully delivered | ProDoc; Draft Policy; Validation Reports; PIRs 2023–25; KIIs (MWE, NEMA, UNCST) |
| Output 1.1.2: Institutional framework compliant with the Nagoya Protocol in place and operational Performance against indicator(s) and target(s). ABS-eReg system 90% complete; integrated with UNCST NRIMS. Includes automated PIC and MAT workflow, digital permit issuance, and compliance dashboard. 28 checkpoints identified; 19 trained; 7 listed on ABS-CH. Other information, not related to the indicators, that demonstrates Output delivery: User testing (Aug 2025); manuals under final QA. | Technical delivery is strong. System functionality is high and onboarding broad-based. Timeliness is acceptable given system complexity. The system is expected to significantly enhance ABS transparency and compliance. The PIC and MAT have been successfully developed and the electronic compliance monitoring system is also in place pending final validation. https://abs.uncst.go.ug Fully delivered | System demos; Field Observations; KIIs; PIR 2024; Test Logs |
| Output 2.1.1: Government agencies at national and sub-national level trained on the implementation and enforcement of Nagoya Protocol on ABS Performance against indicator(s) and target(s) 236 personnel trained across NEMA, UNCST, UWA, NFA, NARO, URSB, Makerere Universities, DLGs and communities; 42% women mean post-test score 82%. Other information, not related to the indicators, that demonstrates Output delivery: Training extended to border checkpoints, IPLCs, and district actors; ABS curriculum integrated in agency modules. | The review noted that out of the 5 targeted government agencies targeted at the MTR level for training, the project has surpassed this by training 22 government agencies in implementation, operationalisation and enforcement of the ABS Nagoya protocols. The project has also undertaken a technical and Institutional Capacity Needs Assessment for NEMA and other CNAs/checkpoints and partners. Delivery is high-quality and wide in scale, producing measurable learning gains. Training reached the intended institutional and community audiences. Timeliness is strong with clear utility for operational ABS implementation. Fully Delivered | Training Reports; FGDs; PIRs; Kigezi & Karamoja observations |
| Output 2.2.1: Training curriculum at Makerere University updated to incorporate ABS for long-term capacity building Performance against indicator(s) and target(s) Makerere University developed curriculum and updated teaching notes to integrate ABS especially in the postgraduate modules. Other information, not related to the indicators, that demonstrates Output delivery: ABS included in National Biodiversity Plan of Action and other development framework such as the NDP IV, Vison 2040, National Green Growth Strategy among others | At MTR level the project had targeted at least 25 stakeholders to be trained and have knowledge & skills in articulating and negotiating PIC and MAT. By the time of MTR, it was noted that 50 stakeholders were trained hence hitting the end of project target on time. This on-time output delivery fast racked the timely and strong academic integration. The ABS module enhances long-term institutional capacity. Fellowships as provided by NaFORRI to students of Busitema University promoted applied research on ABS. Fully Delivered | Makerere documents; University records; PIR 2024, NaFORRI records |
| Output 3.1.1: Model contractual clauses and codes of conduct on best practices on ABS developed and piloted. Performance against indicator(s) and target(s) Two IPLC ABS pilots operational (Batwa & Karimojong). Protocols documented; benefit-sharing models tested (herbal plants & sandalwood propagation and supply chain). Approximately 120 local community members trained in PIC and MAT negotiation skills. This output had 4 pilots which carry the same weight as outputs, as described below; | Delivery is substantial and meaningful for IPLCs. Pilots demonstrate growing community capacity and early benefit-sharing practices. Some elements remain in progress due to Rationalisation of Government Public Expenditure Exercise ( RAPEX). Fully Delivered as of MTR expectations | NARO-PGRC, PIR, NARO-NaFORRI, NFA, UWA, NEMA |
| Pilot 1 – Documentation and utilization of indigenous traditional medicinal knowledge among Batwa IPLCs for herbal product development Performance against indicator(s) and target(s) Natural Chemotherapeutics Research Institute-NCRI has identified and documented traditional knowledge, particularly regarding various diseases (56). Other information, not related to the indicators, that demonstrates Output delivery: Batwa gained visibility through herbal cultivation. The draft document on traditional medicinal knowledge of the Batwa IPLCs monograph and a manuscript in place. | Whereas the project had targeted 30 members from IPLCs to be trained, it was noted that 35 members (12 men and 23 women) were trained Community Protocols and contractual clauses process and procedures in Kigezi while , in the south west six protocols have been developed, emphasizing Prior Informed Consent (PIC) and Mutually Agreed Terms (MAT) in the use of TK for herbal medicine. About 234 medicinal plants have already been documented by the time of the MTR. Of the 234 plants, 155 were scientifically identified, and 79 plants taken to Makerere Herbarium for further identification. 368 treatment formulations have been elaborated. The review also noted that 9 plant samples are being applied to produce products whereby some have been subjected to cold storage phytochemicals preservation. Some plants have been stored in cold storage to preserve essential phytochemicals, while others have been dried, Partially Delivered | NCRI, PMU, PIR, KII, UOBDU |
| Pilot 2: Development and implementation of community protocols on access to Sandalwood (Osiris lanceolata) genetic resources in Karamoja, including their conservation and sustainable use. Performance against indicator(s) and target(s): ABS contract agreements signed. Sandalwood nurseries in place. Other information, not related to the indicators, that demonstrates Output delivery: Karamoja sandalwood integrated into sustainable harvesting strategy. | The MTR noted that this pilot was fully achieved by surpassing the MTR level target hence the drafting of 5 (Five) CFM/CFR contracts. Four contracts have further been drafted with four district local governments for the implementation of Sandalwood community protocols. 4 projects are being implemented as well as the community tree nurseries aimed at the sandalwood propagation. On the aspects of the access to non-timber forest products (NTFP) the project has effected community group formations in Karamoja sub region. Fully Delivered | NaFFORI, PMU, KII, PIR |
| Pilot 3: Development of Prunus Africana ABS compliant value chains around Bwindi forest reserve in western Uganda. Performance against indicator(s) and target(s) A draft report on Mapping of Prunus africana value chain. A draft report environmental, social, and economic impacts of developing the value chain in place. Other information, not related to the indicators, that demonstrates Output delivery: An experienced consultant who collected information beyond the TORs especially on the distribution and abundance of Prunus africana in south western Uganda. | Over 80% of this activity has been achieved where by the project already contracted consultant to map out the value chain as well as review the environmental, socio-economic aspects of the Prunus Africana value chain. Partially Delivered | PMU/NEMA, OUBDU, NCRI, PGRC |
| Pilot 4: Development of ABS compliant collaborative forest management agreements for communities around seven protected areas of Uganda. Performance against indicator(s) and target(s) The CFMs agreements and reports for both in-forest and out-of-forest assessments. Collaborative Resource Management Agreements (CRMAs) in place Other information, not related to the indicators, that demonstrates Output delivery: Ten applications from Karamoja for CFM approval submitted to NFA management. | Out of the 4 targeted CFMs 8 have been developed in Karamoja and 4 CFMs updated in Kigezi sub region. 15 Revenue Sharing Agreements have been updated (6 Mgahinga National Park, 6 in Semliki National Park and 3 in Bwindi Impenetrable Forest. By the time MTR was undertaken about 8 CFM groups have been consulted for a participatory situation analysis in the Karamoja region with a total of 252 community members, (85 females and 167 males). Fully Delivered | NFA, NaFFORI, PIR, DLGs, KII, NEMA |
| Output 3.2.1: Guidelines for gender mainstreaming in ABS for local communities developed and implemented Performance against indicator(s) and target(s). ABS Gender Mainstreaming Strategy and Guidelines developed and in place Other information, not related to the indicators, that demonstrates Output delivery: A report on the conducted gender scoping and analysis in Kisoro and Karamoja in place depicting women and youth involvement in ABS activities. | With the development of the Gender Strategy and Gender mainstreaming guidelines, the MTR noted tremendous women’s participation at national level standing at 30%, whereas at the community level, it reaches 100%. During the project implantation the PMU applies a gender inclusive participation strategy of at least 30% of women participants in all ABS activities hence hitting the MTE level targets. It was therefore noted that gender integration is highly visible in training and participation metrics such as the IPLCs are fully active with women being the majority and highly involved in ABS community activities. Some documentation and analytical limitations remain such as the systematic reporting on gender aspects with specific focused gender tools. Fully Delivered | Gender Plan; KIIs; Training records; PIRs |
| Output 4.1.1: Awareness and communication strategy on ABS developed and implemented Performance against indicator(s) and target(s) Communication strategy developed, Simplified and assorted IEC materials developed and disseminated, Other information, not related to the indicators, that demonstrates Output delivery: 8 radio talk shows, 3 TV features, 10 community dramas delivered; >1.5 million people reached. | Out of the 2000 MTR level targeted assorted IECs materials, the review noted that 15,000 Project brochures were developed (11,000 having project summaries) were developed in English and local languages, published and disseminated which surpassed the MTR level target. Awareness activities reached more than the MTR level target of 50,000 people of the wide demographic segment of the target population hence contributing to national understanding of ABS. The review also noted that the developed IEC Materials are gender-responsive and locally accessible. Awareness has been created to more than 1.5 million people. Fully Delivered | NEMA, PIR, Media logs; Communication reports; KIIs (district leaders) |
| Output 4.1.2 Roster of technical and communication experts on ABS developed and operationalized Performance against indicator(s) and target(s) ABS expert roster developed Other information, not related to the indicators, that demonstrates Output delivery: A list of ABS experts compiled and in place. | A roster of 56 technical and communication experts (Male 41, Female 15) on ABS has been finalized pending online uploading. Fully Delivered | PIR, NEMA, UNCST, NARO-PGRC |

- The trial of herbal extracts identified through Batwa traditional knowledge specifically for treating malaria, wounds, and cough has grown into a powerful cultural and social transformation initiative. Working closely with Batwa elders and healers in 7 sites, the project documented high-value 234 plant species used to treat 72 different health conditions. The communities also recommended establishment of community herbal gardens where such plants can be planted, and tended under guided agronomic practices. One of the elders reiterated that through structured trainings in sustainable harvesting, propagation techniques, and basic extraction processes, Batwa youth and women have gained hands-on skills in medicinal plant management and value addition.

- Beyond their technical contributions, these initiatives have significantly elevated the Batwa’s social standing in communities where they have long faced marginalization and unequal treatment. Their role as custodians of unique medicinal knowledge is now increasingly recognized by neighbouring communities, local leaders, and all other stakeholders. This growing respect has enabled Batwa healers to participate more confidently in local dialogues, strengthening social cohesion and fostering equitable benefit-sharing in line with ABS principles. Additionally, ABS technical literacy has expanded significantly across agencies, district authorities, and research institutions, underscoring the project’s catalytic role in translating ABS principles into concrete economic, environmental, and social opportunities beyond policy development.

Figure 4: Some of the medicinal extracts developed together with the Batwa

- Output delivery under the project demonstrates a strong record of implementation efficiency and technical quality, with most deliverables completed on schedule and meeting or exceeding MTR targets and expected standards. The formulation of the draft ABS Policy and Regulations, development of the electronic permit and compliance system, and execution of large-scale training and outreach programmes illustrate solid execution capacity and effective coordination among implementing partners. Where minor shortfalls exist, principally delays in Cabinet approval and final system rollout, these are largely procedural and external to project control rather than indicative of design or management weaknesses. Moreover, the project has maintained high technical integrity and stakeholder engagement throughout implementation. Gender equality and inclusivity considerations have been substantively integrated across all outputs, ensuring that women, youth, and PWDs benefit equitably from training, consultations, and communication activities. This deliberate inclusiveness not only enhances legitimacy and ownership but also contributes to more sustainable outcomes by embedding equity within institutional and community-level ABS processes. Further still the project has been able to produce and develop tangible herbal medicinal products and solutions as well as create awareness and sensitization of the population beyond the targeted areas due to the utilisation of good strategies like Radio and TV programs, tested and credible government and NGO partner agencies and organisations, capacity building strategies, effective working relationships and buy-in with District Local governments etc.

Progress Towards Project Outcomes

Table 11: Progress Towards Project Outcomes

| Outcome 1.1: | National ABS regulatory and institutional frameworks in compliance with the Nagoya Protocol on ABS in place |
| --- | --- |
| Performance Indicators and Targets | Indicator 1 of Outcome: 1.1: National ABS regulatory frameworks in place and operational. Target: Regulatory frameworks (regulations, guidelines and policy) are developed and/or updated Indicator 2 of Outcome: 1.1: Institutional framework compliant with the Nagoya Protocol in place and operational Targets: • An online permit management system compliant with the Nagoya Protocol developed •Electronic system for monitoring compliance to the Nagoya protocol developed |
| Sources of Information / Evidence | ProDoc; policy drafts (MWE/NEMA); validation workshop reports; PIRs 2022–2024; KIIs (MWE, NEMA, UNCST); field observation notes; FGDs with women’s representatives. |
| Narrative Assessment | The project has substantially strengthened Uganda’s institutional foundation for ABS. Draft national ABS Policy and Regulations were finalized and validated with participation from over 60 stakeholders (52% women), and now pending is Cabinet approval. In the letter of Endorsement, the min-term target for this outcome was the development and/or update of the key regulatory framework. However, by the time of this Mid-Term Review, the project had not only achieved but surpassed this target. All regulatory instruments were updated and developed, underwent internal and external consultations, and were duly cleared by NEMA Top Management. Furthermore, the NEMA Board of Directors formally endorsed the package, and the consolidated regulatory framework was in the process of being submitted to the Top Policy Committee of the Ministry of Water and Environment for final approval. It is imperative to note that this milestone achievement was in the right trajectory in ensuring establishment of a fully functional national ABS framework. Further to the above outcome, it is important to note that the mid-term target outlined in the Letter of Endorsement included the development of an online permit management system aligned with the requirements of the Nagoya Protocol, as well as a functional mechanism for monitoring compliance. By the time of this Mid-Term Review, the electronic ABS system had been fully developed, technically finalized, pilot-tested in 12 agencies, marking Uganda’s first national electronic platform for regulating access to genetic resources. Pending then was its final stakeholder validation and official launch. The assessment further recommends integrating the system with both the ABS Clearing-House and the National Research Information Management System to enhance transparency, streamline permitting processes, and strengthen national compliance monitoring. The primary barrier is procedural rather than technical, indicating that outcome achievement is highly likely once approval timelines are met. |
| Level of Progress | Substantial Progress |

| Outcome 2.1 | Government agencies have the skills and competency to implement and enforce compliance to the Nagoya Protocol on ABS including PIC and MAT |
| --- | --- |
| Performance Indicators and Targets | Indicator 1 of Outcome: 2.1: Improved knowledge and skills in government agencies at national and sub-national level for implementation and enforcement of the Nagoya Protocol on ABS Target: At least 5 government agencies are able to fully implement and enforce the Nagoya Protocol on ABS |
| Sources of Information / Evidence | Community MoUs (Batwa, Karimojong,); FGDs and site visit notes; PIRs 2022–2024; KIIs with MWE, NEMA, Makerere University, and community representatives. |
| Narrative Assessment | The Mid-Term Target for this output was that at least five government agencies would be able to fully implement and enforce the Nagoya Protocol on ABS. By the time of this assessment, the project had substantially exceeded this target. A total of 27 institutions had been capacitated on ABS implementation. At the national level, 12 institutions were trained: NaFORRI, UWA, NFA, National Chemotherapeutics Research Institute (NCRI), Makerere University (MAK), UNCST, NEMA, Plant Genetic Resources Centre (PGRC), Ministry of Water and Environment (MWE), National Livestock Resources Research Institute (NaLIRRI), National Crops Resources Research Institute (NaCRRI), and Ministry of Finance, Planning and Economic Development (MoFPED). At the sub-national level, four non-state institutions were trained: Kachwekano Zonal Agricultural Research and Development Institute (K-ZARDI), Nabuin Zonal Agricultural Research and Development Institute (N-ZARDI), and Bwindi Mgahinga Conservation Trust (BMCT). Additionally, 11 district local governments were supported to enhance ABS readiness Bundibugyo, Kanungu, Rubanda, Kisoro, Kaabong, Kotido, Abim, Moroto, Napak, Nakapiripirit, and Amudat Districts. At the community level, two key institutions the KWCG and the Batwa community were engaged and strengthened to participate effectively in ABS processes. Participation of women demonstrates strong inclusivity. Communities report improved negotiation confidence, understanding of benefit-sharing principles, and ownership of localized business models, such as honey and medicinal plant value chains. Across all components, the outcome is characterized by high institutional ownership, strong gender and inclusion integration, and demonstrable evidence of systemic capacity enhancement across state and non-state actors. Minor constraints such as staff turnover and logistical challenges in remote areas have been mitigated through adaptive training delivery, partnerships with local facilitators, and digital learning approaches. |
| Level of Progress | Substantial Progress |

| Outcome 2.2 | Makerere University training and producing professionals with knowledge on ABS |
| --- | --- |
| Performance Indicators and Targets | Indicator 1 of Outcome 2.2: Training curriculum updated to incorporate ABS for long-term capacity building Target: At least 25 stakeholders (incl. scientists, social workers and lawyers) are trained and have knowledge & skills in articulating and negotiating PIC and MAT |
| Sources of Information / Evidence | Training manuals; training records and evaluation forms; Makerere University ABS curriculum; documentation; community MoUs (Batwa, Karimojong); FGDs and site visit notes; PIRs 2022–2024; KIIs with MWE, NEMA, Makerere University, and community representatives. |
| Narrative Assessment | Outcome 2.2 demonstrates highly satisfactory progress in strengthening Uganda’s institutional, technical, academic, and community capacity for ABS. The performance under this outcome significantly exceeds the expectations set for the Mid-Term Review. The project anticipated that at least 25 stakeholders including scientists, social workers, and legal practitioners would be trained and equipped with the knowledge and skills necessary to articulate and negotiate PIC and MAT. By the time of the MTR, the project had surpassed this target, having capacitated 70 officers across government agencies, academia, and civil society organizations using standardized national ABS training modules. ABS curriculum had been developed (Bachelor of Applied Botany) had been developed and submitted for approval by the University Council. Similarly teaching notes for various courses in the Collage of Natural Sciences had been updated to embrace ABS in their respective content. In practice Makerere University successfully integrated ABS principles into its undergraduate curricula and biodiversity conservation, thereby institutionalizing ABS learning for future professionals. |
| Level of Progress | Substantial Progress |

| Outcome 2.3 | ABS National Focal Point and CNAs effectively carrying out their functions |
| --- | --- |
| Performance Indicators and Targets | Indicator 1 of outcome 2.3: Capacity of NEMA and CNAs for effective implementation of the Nagoya Protocol on ABS strengthened Targets: Uganda is fulfilling at least 40% of her reporting obligations under Nagoya Protocol , and Uganda is able to sign 40 PIC/MAT agreements for access to genetic resources |
| Sources of Information / Evidence | Draft PIR, National ABS Report and Pro |
| Narrative Assessment | Uganda successfully submitted its Interim National Report to the Nagoya Protocol, marking an important step in meeting international reporting obligations. By the time of this Mid-Term Review, the First National ABS Implementation Report had been fully drafted, technically finalized, and was ready for submission to the Nagoya Protocol Secretariat. This demonstrates strengthened national coordination, improved documentation systems, and growing institutional capacity to meet global compliance and reporting requirements under the Protocol. Under the ABS Project, significant progress has been made in strengthening community-level capacity and formal engagement with protected area management authorities. In the Kigezi sub-region, six community groups comprising 35 members (23 women and 12 men) were trained on the ABS regime. In the Karamoja sub-region, eight additional community groups received similar capacity-building support. This work was complemented by the establishment and strengthening of 14 Collaborative Forest Management (CFM) groups, eight newly formed in Karamoja and four updated in the Kigezi sub-region. Furthermore, the project supported 15 Revenue-Sharing Groups across key conservation landscapes: six in Mgahinga Gorilla National Park, six in Semuliki National Park, and three in Bwindi Impenetrable National Park. Importantly, all these community structures have signed formal agreements with the respective protected area management authorities, ensuring legally recognized collaboration, enhanced stewardship of genetic resources, and improved readiness for ABS-related engagement and benefit sharing. |
| Level of Progress | Substantial Progress |

| outcome 3.1 | Effective working models for ABS at the local community level |
| --- | --- |
| Performance Indicators and Targets | Indicator 1 of Outcome: 3.1: (a)Model contractual clauses, codes of conduct on best practices on ABS developed and piloted (b) ABS agreements signed for access to and utilization of GRs from the Batwa and Karimojong IPLCs Targets: •Uganda is fulfilling at least 75% of her reporting requirements under the Nagoya Protocol- Good indicator for outcome 1 •Uganda is able to negotiate and sign 80 to 100 PIC/MAT agreements for access to genetic resources Indicator 2 of Outcome: 3.1: ABS agreements signed for access to and utilization of GRs from the Batwa and Karimojong IPLCs Target: At least 30 members from the two IPLCs (Batwa and Karimojong) are able to negotiate PIC and MAT |
| Sources of Information / Evidence | National ABS Communication Strategy (2023); outreach and media monitoring logs; awareness materials; ABS portal analytics; Gender and Social Inclusion Plan (2022); PIRs 2022–2024; KIIs with NEMA, MWE, UWA, and Makerere University; FGDs with IPLCs, women, youth, and PWDs; site observation records. |
| Narrative Assessment | Under the ABS Project, about 30 contracts and ABS-related agreements have been concluded, reflecting significant progress in formalizing access and benefit-sharing arrangements across multiple landscapes and community groups. Collaborative Forest Management Agreements: Eight (8) CFM contracts were finalized between the National Forestry Authority and communities in Karamoja; Four (4) additional CFM agreements were signed between IPLCs of Echuya Central Forest Reserve and NFA, strengthening co-management and sustainable utilization of forest resources. PIC and Benefit-Sharing Agreements for Herbal Medicine Development: At the community level, six (6) (PIC and benefit-sharing contracts were signed between NCRI and Kisoro community groups from Kanaba, Rukere, Nyagakeke, Birara, Sinuriro, and Biizi. These agreements support collaborative research and development of herbal medicines based on traditional knowledge. Updated Revenue-Sharing Agreements with Protected Area Communities: In addition, 15 benefit-sharing agreements were updated to enhance equitable benefit-sharing arrangements between the UWA and IPLCs residing around Mgahinga Gorilla National Park, Bwindi Impenetrable National Park, and Semuliki National Park. The updates address governance gaps and strengthen accountability in benefit distribution. ABS Agreements Under Development in Karamoja: In Karamoja, NEMA has drafted four (4) contracts with the district local governments of Moroto, Napak, Amudat, and Nakapiripirit to facilitate implementation of Sandalwood Community Protocols and govern community participation in sustainable genetic resource utilization. Pilot ABS Initiatives Established: The project is also supporting four pilot initiatives that operationalize ABS at the community level: Establishment of community tree nurseries for large-scale propagation of Osyris lanceolata (Sandalwood) in Mt. Napak CFR (Nabwal). Formation of community groups to access and utilize non-timber forest products (NTFPs) in Mt. Kadam CFR. Piloting community access and benefit sharing for sustainable harvesting and commercialization of Prunus africana in Rubanda. Piloting ABS-based herbal medicinal bio-trade in Kisoro in collaboration with IPLCs and traditional knowledge holders. Strengthening Community Structures: KWCG has further mobilized and established more than 23, additional community groups across various districts to support implementation of ABS activities, traditional knowledge protection, and sustainable resource management. |
| Level of Progress | Substantial Progress |

| Outcome 3.2 | Effective participation of men and women in benefit sharing |
| --- | --- |
| Performance Indicators and Targets | Indicator 1 of Outcome: 3.2: Guidelines of gender mainstreaming in ABS in place Target: Gender mainstreaming guidelines to guide mainstreaming in all ABS project activities. Indicator 2 of Outcome: 3.2: Percentage of women at local community levels participating in benefit sharing Target: 30% of women actively participating in ABS |
| Sources of Information / Evidence | NEMA, ABS PMU, PIR, UNCST, KII |
| Narrative Assessment | The Draft ABS National Gender Mainstreaming Strategy and the accompanying National Gender Mainstreaming Guidelines were successfully developed and subjected to technical review and discussion by NEMA Top Management. By the time of this Mid-Term Review, both instruments had been finalized and were awaiting consideration and approval by the NEMA Board. Their adoption is expected to significantly strengthen gender-responsive implementation of the ABS regime at national and community levels. |
| Level of Progress | Substantial Progress |

| outcome 4.1 | Increased awareness in Uganda on the Nagoya Protocol on ABS |
| --- | --- |
| Performance Indicators and Targets | Indicator 1 of outcome 4.1: Strategies for improving communication and awareness of the Nagoya Protocol on ABS in place and actively being used Targets: •A draft comprehensive ABS awareness and communication strategy developed •At least 30 staff from NFP, CNAs, check points and publishing authorities trained in information sharing through the ABS-CH •A roster of ABS technical and communications experts in the country developed Indicator 2 of outcome 4.1: Number of ABS communication, education and public awareness materials developed and disseminated Target: At least 2000 assorted awareness materials (quarterly bulletins, brochures, manuals and training toolkits) developed Indicator 3 of outcome 4.1: Number of people reached with education and public awareness materials Target: At least 50,000 people reached about ABS through mass media |
| Sources of Information / Evidence | National ABS Communication Strategy (2023); outreach and media monitoring logs; awareness materials; ABS portal analytics; Gender and Social Inclusion Plan (2022); PIRs 2022–2024; KIIs with NEMA, MWE, UWA, and Makerere University; FGDs with IPLCs, women, youth, and PWDs; site observation records. |
| Narrative Assessment | Outcome 4.1 has achieved a comprehensive and highly satisfactory progress in enhancing public awareness of ABS principles while effectively integrating gender equality and social inclusion across project implementation structures. All implementing partners contributed meaningfully to awareness-raising efforts within their respective mandates and geographic areas of operation. Awareness creation was undertaken through multiple platforms. Under the leadership of NaFORRI, targeted seminars were conducted for government officials, community leaders, researchers, and security personnel. These efforts were complemented by extensive media outreach through national platforms, including social media (X: @NAROUganda), Ateker Radio (serving Karamoja and Teso regions), Uganda Radio Network (URN), Uganda Broadcasting Corporation (UBC) TV, Next Broadcasting Service (NBS) TV, and the New Vision newspaper. Collectively, these outlets reach millions of Ugandans, significantly expanding public understanding of ABS and its national relevance. PGRC further enhanced scientific awareness by engaging researchers within the NARO and associated research institutions. In Karamoja, the sandalwood initiative stands out as a major project achievement. With NARO-NaFORRI’s establishment of a pilot sandalwood woodlot at Nabuin Zonal Agricultural Research and Development Institute, KWCG has established 2 tree nurseries hence ensuring supply of quality seedlings to the communities. This reduces extractive pressure and illegal harvesting in forest reserves and community land. In Kigezi, the project has similarly enabled meaningful social transformation among Batwa communities, where the cultivation of medicinal plants has strengthened community visibility, identity, and pride, as consistently emphasized in community FGDs; however, this qualitative impact has been insufficiently reflected in PIRs due to the absence of a dedicated gender and social safeguards specialist. At sub-national level, awareness activities were conducted in partnership with district local governments. Notably, an ABS-focused radio talk show was aired on Ateker FM in Moroto District one of Karamoja’s widest-reaching stations, covering all districts in the sub-region with an estimated population of 1.5 million people (589,473 men; 619,756 women). NaFORRI also developed and disseminated ABS awareness materials, teardrops, and pull-up banners across Karamoja, expanding the visibility and reach of ABS messages. At the strategic level, the Draft National Communication and Awareness Strategy was finalized, presented to NEMA Top Management, and submitted to the NEMA Board for review and approval. This strategy will guide coordinated national communication on ABS moving forward. A national ABS Roster of Experts, comprising 56 specialists (41 men and 15 women) in technical, legal, and communication domains, was developed to support ongoing capacity-building and advisory services. The final phase of training and the formal launch of the roster is scheduled for January–March 2026. Additionally, NaFORRI documented and disseminated best practices for the propagation, cultivation, and management of sandalwood genetic resources, which have been shared with all district local governments in the Karamoja sub-region to promote sustainable use and conservation of this high-value species. These results demonstrate that awareness raising, gender mainstreaming, and inclusivity have moved beyond token compliance to transformative engagement, creating a social foundation for sustainability. Challenges persist in reaching nomadic or highly remote groups, yet adaptive outreach methods mobile sensitization, partnerships with local FM stations, and hybrid virtual meetings have minimized exclusion. |
| Level of Progress | Substantial Progress |

- The project’s outcome-level performance reflects consistent, substantial, and strategically coherent progress across all four thematic areas, demonstrating a strong alignment between the project’s design intent and actual implementation results. Policy and institutional advances are particularly notable, with the ABS Policy, Regulations, and Guidelines fully developed and validated, a functional national coordination framework established, and an advanced electronic permit and compliance system completed and ready for launch. Capacity-building achievements have significantly exceeded targets, strengthening technical competencies across government agencies, academia, district structures, and IPLCs, while embedding ABS principles within university curricula and research programmes ensures continuity and long-term institutional sustainability.

- Gender equality and social inclusion have been meaningfully integrated throughout implementation, with women, youth, and persons with disabilities actively engaged in trainings, consultations, piloting of community protocols, and negotiation of PIC and MAT agreements an essential indicator of progress transparency, toward equitable and inclusive benefit sharing. Complementing this, expansive national and sub-national awareness efforts have reached millions through radio, television, print media, community dialogues, and targeted scientific engagements, thereby enhancing public understanding of ABS rights, obligations, and opportunities.

- With the majority of outputs and outcomes already delivered or substantially achieved, the remaining steps particularly approvals of the ABS Policy, Regulations and Guidelines as well as full rollout of community-level ABS agreements and pilots represent the final elements required to consolidate the project’s gains. Overall, the project is on track to achieve its intended outcomes, driven by strong institutional ownership, adaptive and coordinated management, and broad-based stakeholder participation that collectively reinforce Uganda’s transition toward a functional, equitable, and sustainable ABS system.

Likelihood of Impact

Table 12: Likelihood of impact

| Factors Influencing Likelihood of Impact | Evident / Emerging | Discussion |
| --- | --- | --- |
| Drivers to support transition from Outputs to the Project Outcomes: | Yes | Strong government leadership, inter-agency coordination, and stakeholder engagement are driving uptake of outputs. MWE and NEMA lead regular coordination meetings, with UNCST, UWA, URSB, Makerere University, and IPLCs actively applying new tools (ABS Policy, e-permit system, training modules). UNEP’s technical support and GEF alignment further sustain implementation momentum. |
| Assumptions for the change process from Outputs to Project Outcomes: | Partially | Progress slightly constrained by Cabinet approval delays and limited field resources. Interim mechanisms; ABS-eReg pilot, active steering committees, and adaptive hybrid trainings are bridging procedural gaps. Continued policy advocacy and financing will ensure full operationalization. |
| Proportion of Project Outcomes fully or partially achieved | Yes | Capacity building, gender integration, and stakeholder engagement targets exceeded. Two community ABS agreements signed, academic curricula operationalized, and coordination mechanisms functional. Remaining actions relate mainly to final policy approval and full system roll-out. |
| Drivers to support transition from Project Outcomes to Intermediate States | Yes | Institutional capacity, policy coherence, and knowledge exchange with JKUAT and Ethiopia enable mainstreaming of ABS into national and district plans. Government commitment reflected in MWE budget allocations and regional leadership roles. |
| Assumptions for the change process from the Project Outcomes to Intermediate States | Partially | Sustained political commitment and financing remain essential. High ownership among institutions and trained staff retention underpin continuity, but post-GEF funding assurance is still evolving. |
| Proportion of Intermediate States achieved | Partially | Early replication seen in district environment plans, research outputs, and academic programs continuing beyond direct project funding. Catalytic effects emerging but not yet fully consolidated. |
| Drivers to support transition from Intermediate States to Impact | Partially | South–South cooperation, cross-border exchanges, and CBD COP-16 engagement are emerging but still at early stages. These linkages show potential to strengthen sustainability and regional ABS learning but are not yet fully established. |
| Assumptions for the change process from Intermediate States to Impact | Partially | Long-term impacts hinge on final policy adoption, integration of ABS into national frameworks, and stable domestic funding. Gender inclusion, awareness, and institutional capacity provide a strong foundation for sustained biodiversity conservation and equitable benefit sharing. |

- The project demonstrates a strong likelihood of achieving lasting impact through sustained institutional maturity and emerging systemic integration. National agencies are increasingly applying ABS principles independently, with cross-sectoral collaboration and regional partnerships reinforcing long-term continuity. Evidence of self-sustaining momentum, such as district governments incorporating ABS into planning tools, academic institutions continuing research and training beyond project support, and community led initiatives maintaining benefit-sharing practices indicates a gradual shift from project-driven outputs to nationally owned processes.

- Regional recognition of Uganda’s approach through South–South cooperation and participation in continental biodiversity forums further amplifies its catalytic influence. While enduring impact will depend on consistent financing and final policy endorsement, the behavioral and institutional transformations already observed suggest that the foundation for sustained biodiversity governance and equitable benefit sharing is firmly in place.

“We have been trained and sensitized about the value of traditional medicine and now we can have our own alternative medicine. We did not know modern medicine is from our own herbs hence we hope you can support us further to carry out research and process our traditional herbs into locally made medicine.” IPLC Mulamba Batwa and Local Communities Herbalist Group - Woman Member “The project has benefitted us women at household levels and entire communities since we can now administer tested herbal medicine to our own family members. We have also been able to unite and as well as get incomes from the herbal medicine which has in turn helped us meet our family needs like buying clothes, paying school fees, buying household items etc. However, the main challenge is that the herbs are mainly in protected areas and at time accessibility is difficult hence we would be glad if communities are provided with gazette gardens to plant our own group herbs” IPLC Mulamba Batwa and Local Communities Herbalist Group - Woman Member. “We had our traditional knowledge but we had no sensitization but NEMA came and enlightened us on the value of our own traditional medicinal plants. At first administering local medicine was seen and labelled as backward. With this knowledge and support from NEMA we can now apply the knowledge and also get incomes from the products as well as benefitting our next generation children so that the acquired knowledge does not die out. The project has also empowered us to vie for leadership positions with the community” IPLC Mulamba Batwa and Local Communities Herbalist Group - Man Member “For me I have never gone to school but the project has taught me many advantages of trees including medicinal uses. We used to cut trees indiscriminately to make fences, firewood but NEMA discouraged us by sensitizing us to conserve certain trees, fruits and medicinal plants for future benefits. In fact, we were also taught that some trees cannot grow alone hence this can affect our environment and ecosystem negatively. The project through such activities has promoted unity and social cohesion amongst women groups as well as enabled us to start VSLA savings groups”. IPLC Rupa Cultural Women’s Group – Woman member. “The project has tremendously contributed and impacted the communities especially the minority Batwa group by providing avenues and opportunities to work with the Batwa communities and contribute to the meaningful development of the district. The project through the Kisoro DLG has also contributed to the naming of the traditional herbs and local medicine which promotes ownership and sustainability. Further still apart from the promotion and preservation of the cultural traditional medicine, the project has amplified the visibility of the Batwa communities since their voices are now heard and being recognized and integrated into community and district decisions making and development processes”. Kisoro District Local Government Leader

Findings Statements on Effectiveness

- Under Output 2.3.1, the project supported the Natural Chemotherapeutics Research Institute (NCRI) to develop GR-based medicinal formulations, including emollients and cough remedies derived from priority genetic resources identified during community ABS assessments. These products were piloted for their curative potential across common community ailments. Figure 4 illustrates the relative effectiveness scores of these formulations against selected diseases as reported by beneficiary groups, with notably higher performance for cough, wounds, and pneumonia. In Karamoja, the establishment of a sandalwood nursery further demonstrated practical valorization pathways by supplying seedlings for community planting, reducing extraction pressure on protected reserves while ensuring a sustainable feedstock supply for future ABS-compliant commercial use. Together, these interventions demonstrate tangible progress in linking conservation outcomes to community livelihoods and private sector demand.

Source: ABS PMU Report

Figure 5: Diseases as reported by beneficiary groups

- The project has achieved substantial progress in delivering its planned outputs, with strong institutional leadership from NEMA and MWE and active engagement of partner agencies, academia, and IPLCs. Most deliverables particularly in policy formulation, capacity building, and awareness were completed or nearing completion at mid-term, reflecting high implementation efficiency and stakeholder ownership.

- Capacity development, gender mainstreaming, and policy coherence have markedly strengthened Uganda’s institutional and community readiness for full scale ABS implementation. The integration of ABS principles into academic curricula, research programs, and district plans demonstrates deep institutionalization beyond project boundaries, while women and youth participation have fostered more inclusive governance structures.

- Remaining gaps primarily concern procedural delays in policy approval and challenges in sustaining outreach to remote IPLC communities. However, adaptive management measures, such as; hybrid training models, flexible scheduling, and localized consultations are mitigating these barriers and maintaining project momentum toward its intended outcomes.

Rating for Effectiveness: Highly Satisfactory (HS)
Rating for Availability of Outputs: Satisfactory (S)
Rating for Achievement of Project Outcomes:  Highly Satisfactory (HS)
Rating for Achievement of Likelihood of Impact (Use ‘Likely’ scale): Likely (L)

  - Financial Management

Adherence to UNEP’s Financial Policies and Procedures

- The Executing Agency (NEMA) and the Implementing Agency (UNEP Ecosystems Division) have maintained a strong record of compliance with UNEP and GEF financial regulations. All financial transactions follow established approval hierarchies and internal control mechanisms that ensure accountability, traceability, and value for money. Expenditures have remained within approved annual budgets, with reports structured according to UNEP’s Fund Management System (Umoja) standards. While financial reports were initially submitted annually due to internal coordination delays in 2020–2021, reporting has since transitioned to a quarterly cycle (from 2022), significantly improving accuracy and timeliness.

- The first disbursement to NEMA was released in February 2021, following completion of the conditions specified in the PCA, including account set-up, staffing arrangements, and submission of initial planning documents. Although this occurred several months after project effectiveness, the timing reflected COVID19 related administrative constraints and government clearance procedures at the time. Subsequent disbursements were processed within the standard PCA defined cycle generally within two to three weeks indicating improved coordination and responsiveness between UNEP and NEMA.

- The project’s financial management performance strengthened notably after the initial implementation period. UNCST consistently demonstrated strong internal controls, timely reporting, and effective use of funds to operationalize the ABS Desk, and overall expenditure patterns remained aligned with planned outputs and PCA provisions. In contrast, NEMA experienced early reporting delays particularly in audit submissions and consolidation of partner expenditures which slowed disbursement processing and temporarily affected partner cash flow during 2021–2022. These delays contributed to slower progress in some early activities. In response, the PMU applied adaptive management by revising workplans in 2023 and 2024 to reflect the remaining implementation window, prioritising high-value regulatory, institutional, and community-level outputs while scaling back non-essential activities. This enabled the project to maintain momentum and safeguard delivery of core outcomes despite earlier operational constraints.

- Financial monitoring and review mechanisms are well institutionalized. Joint quarterly reviews involving UNEP, NEMA, and MWE) ensure close alignment between financial disbursement and activity progress. The Project Management Unit conducts regular expenditure tracking, variance analysis, and reconciliation of cash advances, providing a clear basis for informed financial decision-making throughout implementation.

- Procurement operations were carried out in line with UNEP’s procurement procedures and Uganda’s Public Procurement and Disposal of Public Assets (PPDA) Act. Key procurements, such as the ABS-eReg permit system, consultancy services for capacity building, and contracts for communications and awareness activities were competitively sourced and supported by appropriate documentation. A review of procurement files and interviews with the PMU found no evidence of ineligible expenditures or procedural irregularities.

- UNEP’s regular oversight through its expenditure reviews and financial clearance processes has continued to reinforce accountability and transparency across the project. External audits for 2022 and 2023 confirmed overall sound financial management, noting only minor documentation delays that were resolved during the review cycles. Co-financing contributions from national partners and collaborating institutions have been broadly consistent with their commitments, based on the reports submitted to NEMA and consolidated for this MTR.

Completeness of Financial Information

- The financial documentation system for the Uganda ABS Project is comprehensive and well maintained, providing clear audit trails for all transactions. Key records such as the signed Project Cooperation Agreement (PCA), budget revisions, co-financing reports, fund transfer statements, and expenditure summaries were all made available for review and found consistent with UNEP’s reporting standards.

- The project has steadily strengthened its financial reporting regime. Since the shift to quarterly reporting in 2022, budget execution data and expenditure narratives have become more consistent with workplan timelines, enhancing management decision making. Regular variance analyses by the PMU and UNEP’s Fund Management Officer allow for early detection and correction of deviations, ensuring that expenditure patterns remain aligned with output delivery.

- Cross-verification of financial information between NEMA’s internal accounting records, Uganda’s Integrated Financial Management System (IFMS), and UNEP’s Umoja platform showed consistent figures across all three systems, with no material discrepancies identified during the review. All expenditure records, disbursement vouchers, and liquidation statements are systematically filed both electronically and in hard copy, in line with UNEP’s records retention policy.

- Independent annual audits have consistently confirmed the completeness and reliability of the project’s financial data. Audit reports for FY2022, FY2023, and the recently approved FY2024 audit all validate the reported figures and confirm adherence to UNEP and national financial regulations. Overall, the audits demonstrate a sound financial management environment at both NEMA and partner-institution levels.

- Co-financing and in-kind contributions have been systematically documented and verified across all contributing partners, including MWE, NEMA, UNCST, UWA, NFA, NARO/NaFORRI, Makerere University, and IPLC organisations. These contributions ranging from technical inputs and staff time to office space, research facilities, and community mobilisation demonstrate strong national ownership and institutional commitment to the project. The overall secured budget remains broadly consistent with the projections outlined in the Project Document.

- Procurement and financial archives are complete and fully auditable. Bid evaluation reports, requisition approvals, and Source Selection Plans are organized in a consolidated procurement file managed by the PMU. No missing records or inconsistencies were identified during verification. In conclusion, the project’s financial information is accurate, comprehensive, and audit ready. The strong link between expenditures and achieved outputs demonstrates prudent financial stewardship and supports effective monitoring of cost-to-delivery performance.

Table 13: Financial management

| Financial Management Components | Rating | Evidence / Comments |
| --- | --- | --- |
| 1. Adherence to UNEP’s/GEF’s Financial Policies and Procedures | HS:HU | Compliance with UNEP and GEF standards: The project fully aligns with UNEP’s Financial Rules & Regulations and GEF fiduciary requirements. All financial transactions follow defined approval workflows through Umoja, ensuring accountability and traceability. Expenditures remain within approved budget ceilings per component, and internal verification is done monthly by NEMA’s Finance and Accounts Division. Timeliness of disbursements: The first cash advance (requested Oct 2020) was received Feb 2021, four months beyond the nine-month benchmark, due to COVID-19 restrictions and UNEP clearance delays. Subsequent advances (2022–2024) were processed within 2–3 weeks, in line with PCA provisions. Oversight and monitoring: UNEP conducts quarterly financial supervision missions and verifies quarterly expenditure statements. NEMA submits certified financial reports through the Fund Management Officer (FMO). No evidence of ineligible expenditures or non-compliance has been identified. |
| Any evidence that indicates shortcomings in adherence to UNEP or donor rules | No | Minor reporting delays occurred in 2020–2021 due to staff transitions and the COVID19 lockdown but were corrected from 2022 onward through structured quarterly reporting. No audit qualifications or material misallocations have been reported. |
| Was the first disbursement carried out within nine months of UNEP project approval date? | No | Delay attributed to post-approval clearance bottlenecks and pandemic-related disruptions; documented by UNEP FMO correspondence (2020–2021). Corrective measures instituted ensured subsequent compliance with timeliness standards. |
| Were the procurement policies of UNEP and the donor followed? | Yes | Procurement processes follow UNEP’s Source Selection Plan and Uganda’s PPDA Act. Competitive bidding was applied for major procurements (ABS-eReg System, awareness contracts, training consultancies). All procurement files, including; bids, evaluations, and award memos were reviewed and found compliant. |
| 2. Completeness of Project Financial Information | HS:HU | NEMA maintains a comprehensive documentation system integrating national IFMS and UNEP’s Umoja records. Full sets of legal agreements, disbursement records, and expenditure summaries were provided to the evaluator. Independent audits confirm reliability and integrity of reported figures. |
| A. Co-financing and Project Cost tables at design (by budget lines) | Yes | Detailed cost tables exist within the ProDoc and PCA annexes, broken down by components, outputs, and budget lines. Both cash and in-kind contributions were clearly itemized and aligned with GEF-approved allocations. |
| B. Revisions to the budget | Yes | One formal budget revision (2023) reallocated savings from travel and workshops to system development and gender activities. Revision approved by UNEP FMO; document on file. |
| C. All relevant project legal agreements (e.g. PCA, SSFA, ICA) | Yes | PCA between UNEP and NEMA signed 2020; Sub-agreements with MWE, Makerere University (SSFA) and local CSOs (ICA) available and verified. |
| D. Proof of fund transfers | Yes | UNEP provided bank transfer receipts for each advance (2020–2024); acknowledgement receipts from NEMA on file. Tranches correlate with quarterly expenditure plans. |
| E. Proof of co-financing (cash and in-kind) | Yes | Verified letters and financial statements from MWE (office space and technical support ≈ USD 120,000 in-kind) and Makerere University (training inputs ≈ USD 60,000). UNEP validated figures during PIR 2023 review. |
| F. Summary report on project expenditures (by budget lines/components) | Yes | PMU provided component-wise expenditure summaries for 2021–2024 with variance analyses showing average budget utilization of 83%. Expenditures are correlated to workplan delivery schedules. |
| G. Copies of completed audits and management responses | Yes | FY2022 and FY2023 audits completed by independent firm; both issued unqualified opinions. Minor documentation delays addressed through corrective actions endorsed by UNEP FMO. |
| H. Procurement documents including approved requisitions and Source Selection Plans | Yes | Full procurement archive reviewed at NEMA headquarters; all major tenders include requisition approval forms, bid evaluation reports, and award letters. Conforms to UNEP and national standards. |
| I. Other financial information required for this project | Yes | Monthly bank reconciliation reports and exchange-rate adjustment record available for all quarters. Reconciliations show < 3% variance between national and UNEP records. |
| Overall Rating for Financial Management | Satisfactory | The project displays strong financial discipline, comprehensive documentation, and effective oversight. Audit trails are complete and traceable. Financial flows are timely, transparent, and aligned with delivery milestones. No systemic weaknesses have been identified. Financial performance and reporting practices meet UNEP’s highest standards for accountability and compliance. |

Findings Statements on Financial Management

- The project exhibits exemplary compliance with UNEP and GEF financial management standards. Disbursement procedures are efficient, with funds released in accordance with approved workplans and PCA. Financial oversight is robust and transparent, supported by clearly documented approval workflows, segregation of duties, and multi-tier verification through NEMA’s Finance Division, UNEP’s Fund Management Officer, and external audits. Procurement and contracting strictly follow UNEP’s Source Selection Plan and Uganda’s PPDA regulations, ensuring competitiveness, fairness, and value for money. Internal controls are strong, with regular reconciliation of accounts, variance analysis, and corrective action tracking. The consistent alignment between financial disbursement, activity implementation, and quarterly reporting demonstrates a mature financial governance structure that minimizes fiduciary risk.

- Financial reporting and documentation are comprehensive, accurate, and fully verifiable, demonstrating a direct and traceable link between expenditures and achieved outputs. The quarterly financial statements, audit reports, and variance analyses show prudent resource utilization, with administrative costs maintained below 10% of total expenditure well within acceptable thresholds. The completeness of supporting documentation ranging from proof of fund transfers and co-financing evidence to detailed procurement archives ensures a transparent audit trail. The rate of expenditure (approximately 83% of total budget as of mid-2025) closely matches the level of physical and programmatic delivery, confirming efficient budget execution and strong value-for-money performance. The project’s financial management systems have therefore not only ensured compliance but also actively supported adaptive decision-making and accountability across implementing partners.

Rating for Financial Management:   Highly Satisfactory (HS)

Rating for Adherence to UNEP’s Financial Policies and Procedures: Highly Satisfactory (HS)

Rating for Completeness of Financial Information: Highly Satisfactory (HS)

  - Efficiency

- The project’s overall cost-effectiveness is rated as Moderately Satisfactory (MS). Despite an initially slow start caused by COVID-19 disruptions, the project has since demonstrated efficient use of available resources. By June 2025, approximately 75% of the total GEF grant (USD 2.56 million) had been expended, aligned with around 70% of planned outputs delivered. Co-financing commitments from partner institutions valued at USD 9.23 million in cash and in-kind remained on track, with significant contributions from NEMA, UNCST, NFA, UWA, and UOBDU through staff time, office space, and logistics. Community pilots also demonstrated efficient resource utilization, with EUR 30,000 successfully used to establish Batwa traditional knowledge gardens and community protocols, while low-cost training models in Karamoja built around peer learning and local facilitators enabled wide outreach at minimal expense. These efforts were further strengthened by substantial community contributions in the form of land, labour, and locally sourced seedlings, which significantly reduced implementation costs and enhanced ownership of the interventions. Cost efficiency was further enhanced by integrating ABS training into existing forestry and wildlife programmes, use of shared government facilities, and adoption of hybrid (in-person and virtual) coordination meetings, which reduced travel and event costs. However, the approved GEF budget was significantly lower than what was required for a project of this scale and complexity (multi-partner and multi-site scope). Stakeholders consulted during the MTR estimate that a realistic budget would have been USD 6–8 million to adequately cover the policy, institutional, and community-level interventions. This under-capitalization explains pockets of schedule pressure despite generally sound management.

- Implementation timeliness is Moderately Satisfactory (MS). The project was approved in July 2020, commenced in January 2021, and experienced initial delays in mobilization and recruitment due to global pandemic restrictions and multi-agency clearance processes. Field implementation stalled for nearly two years due to late recruitment of the PMU (Project Manager and site officers). Cash advances were also delayed because NEMA could not meet the ≥75% expenditure accounting threshold for subsequent disbursements while staff were multitasking across non-project duties. Once dedicated staff were in place (2023), reporting quality improved and activity delivery accelerated. To recover lost time, UNEP approved a 12-month no-cost extension (March 2024) extending completion to December 2026. Since then, workplan sequencing has improved markedly, with streamlined quarterly planning, synchronized partner reporting, and joint activity scheduling across institutions. The adaptive approach consolidating related trainings and combining stakeholder engagements has minimized overlap and enhanced delivery efficiency.

- Project coherence is Satisfactory (S). The design and implementation have leveraged existing institutional structures, partnerships, and policy processes to maximize synergy and sustainability. The project builds directly on the National Environment Act (2019), the National Biodiversity Strategy and Action Plan II (NBSAP II), and ongoing research programmes under UNCST and NARO, ensuring alignment with Uganda’s national priorities. It also complements related initiatives, including the GEF-supported Nagoya Protocol Global Project, NEMA’s biodiversity mainstreaming programme, and the UWA/NFA Collaborative Forest Management (CFM) framework. Operationally, the project strengthened coherence by embedding ABS pilots within established community mechanisms (TECA and LILO) and utilizing district coordination structures, thereby minimizing duplication and enhancing institutional learning. The decision to channel funds through a single Executing Agency (NEMA) helped maintain national ownership and is consistent with GEF policy. While this approach increased NEMA’s coordination burden, it ensured a unified implementation pathway and avoided fragmented execution across multiple small partners.

Table 14: Project Extension

| Type of Extension | Duration (months) | Reason for No-Cost Extension |
| --- | --- | --- |
| No-Cost Extension | 12 | The extension was requested to address delays in project start-up caused by COVID-19 restrictions (2021–2022) and slower processing of the initial disbursement from UNEP to NEMA, which affected early implementation schedules. The additional time enabled completion of remaining activities, including policy finalization, e-permit system rollout, and consolidation of community pilots. |

Findings Statements on Financial Management

- The project has demonstrated good cost-effectiveness, supported by adaptive management practices, strategic use of co-financing, and significant in-kind contributions from national partners. Expenditure has remained closely aligned with planned outputs, and resources have been allocated efficiently across priority regulatory, institutional, and community-level interventions.

- Efficiency improved significantly from 2023 onward, following streamlining of partner reporting, hybrid coordination meetings, and targeted budget reallocations to strengthen community-level interventions.

Rating for Rating for Efficiency:   Moderately Satisfactory (MS)

  - Monitoring and Reporting

Monitoring of Project Implementation

- Monitoring and evaluation of project performance have been integrated into implementation through routine planning, quarterly progress reviews, and annual PIRs. The system is largely operational and functional, coordinated by PMU at NEMA and supported by the UNEP Task Manager. Each implementing partner (UNCST, UWA, NFA, NARO, URSB, and UOBDU) submits quarterly technical and financial reports consolidated by NEMA into national progress summaries. These are reviewed by NPSC before submission to UNEP. Progress is tracked against output-level milestones outlined in the project logframe, with 70% of indicators showing satisfactory progress by mid-2025.

- Adaptive management practices have improved since 2023, with partners using monitoring data to revise activity sequencing and strengthen performance. For example, NaFORRI used monitoring feedback to re-target training on sandalwood propagation in Karamoja, while UOBDU adapted awareness programmes for Batwa communities after mid-term lessons on participation barriers. Monitoring data are disaggregated by gender and stakeholder category, indicating 48% female participation in trainings and consultations. While systematic disaggregation by age and disability remains limited, community monitoring mechanisms increasingly capture inclusion indicators through local focal persons. UNEP’s online Project Information and Management System (PIMS) and GEF Portal are regularly updated, and the project’s semi-annual review meetings have been instrumental in identifying bottlenecks and coordinating timely corrective actions. Nonetheless, the absence of a dedicated M&E officer and a gender specialist has constrained systematic outcome tracking and deeper analysis of inclusivity across partners.

Project Reporting

- Project reporting is rated as Satisfactory (S). NEMA has consistently fulfilled UNEP and GEF reporting obligations through the submission of annual PIRs for 2023–2025, supported by semi-annual and partner-level progress updates. Reports are comprehensive and provide both narrative and quantitative summaries, with gender disaggregated data and sections on community engagement, adaptive management, and co-financing.

- Partners such as UNCST, NaFORRI, and UOBDU have contributed structured inputs to each PIR cycle, supported by detailed financial tracking and photographic evidence. Progress reports have also incorporated results from the Karamoja and Kigezi field missions, strengthening the link between qualitative field data and quantitative output indicators. Some delays were noted in partner submissions due to differing internal formats, but the PMU introduced a harmonized reporting template in 2024 that improved coherence and timeliness. In addition, the standard reporting templates offer limited space for qualitative narratives, which has restricted the documentation of change stories and community-level impact that partners often generate but cannot fully reflect in PIR formats.

Findings Statements on Monitoring and Reporting

- Monitoring and reporting mechanisms are functional and have evolved into effective tools for adaptive management and decision-making, though disaggregation by disability and youth requires strengthening.

- Reporting consistency and quality have improved through the harmonized NEMA-led system, enabling timely submission of PIRs and alignment with UNEP and GEF reporting standards.

Rating for Monitoring and Reporting: Satisfactory (S)

Rating for Monitoring of Project Implementation: Moderately Satisfactory (MS)

Rating for Project Reporting: Satisfactory

  - Exit Strategy & Sustainability

- Sustainability is assessed against three sub-criteria: (a) socio-political sustainability, (b) financial sustainability, and (c) institutional sustainability. The review focused on the key factors and conditions likely to either sustain or undermine the continuation of project outcomes and benefits beyond closure. The assessment draws on evidence from field consultations, partner reports, and national policy documents, using the UNEP “Likely–Unlikely” rating scale.

Exit Strategy

- The project’s exit strategy is embedded within its implementation design and has progressively taken shape through national policy ownership, institutional capacity strengthening, and community-level empowerment. The validated National ABS Policy and Regulations provide the foundation for post-project continuity, with gazettement expected by mid-2026. NEMA’s leadership and its formal coordination mandate under the National Environment Act (2019) position it to sustain oversight beyond GEF financing. The transition plan emphasizes mainstreaming ABS functions into regular institutional budgets of NEMA, UNCST, UWA, NFA, and URSB, while consolidating community pilots into district development frameworks. UNEP and the Government of Uganda have agreed that all core project assets, including the ABS e-permit system, will be fully transferred to NEMA and maintained under the Environment Information Management Division that is currently operating Environmental Licensing and Management System (ELMIS-https://eservices.nema.go.ug/home). UNCST confirmed system’s integration with the National Research Information Management System (NRIMS) to ensure sustainability beyond project closure. The system has undergone multi-institutional user testing and now includes automated permit generation, compliance monitoring dashboards, and user/admin interfaces.

Socio-political Sustainability

- Under socio-political sustainability, the review assessed the extent to which social and political factors support the continuation and further development of project outcomes, focusing on the level of ownership, interest, and commitment among government and stakeholders to advance ABS implementation. Socio-political sustainability is rated Likely (L). The project enjoys high-level government commitment and stakeholder ownership, reflected in the direct involvement of the MWE and endorsement by sector agencies such as NARO and NFA. ABS principles are now embedded in multiple national strategies including NBSAP II and the National Environment Act (2019). Community buy-in is evident through the CFM agreements in Kigezi and Karamoja, where IPLCs have incorporated ABS principles into local governance and resource use plans. The inclusion of women, youth, and marginalized groups (48% female participation) further anchors social legitimacy. Continued sensitization at the sub-national level, especially for local governments and traditional leaders, will be key to sustaining community awareness and consolidating long-term political support.

Financial Sustainability

- Financial sustainability is rated Moderately Likely (ML). While core government institutions have budget lines to sustain environmental compliance activities, specific allocations for ABS enforcement and monitoring remain modest. However, NEMA and UNCST have initiated discussions with the Ministry of Finance, Planning and Economic Development (MoFPED) to integrate ABS implementation costs into recurrent budgets. Partner institutions such as UWA and NFA have committed in-kind support for continued field enforcement and training. The project’s e-permit system is expected to generate moderate user fees that will contribute to cost recovery. Additional donor interest has been expressed through UNEP’s Global ABS Programme and bilateral agencies exploring post project technical assistance.

Institutional Sustainability

- Institutional sustainability is rated Likely (L). The project has established strong institutional frameworks through inter-agency collaboration and the creation of the National ABS Committee, which provides a formal coordination platform across government, academia, and IPLCs. Capacity building efforts, particularly within NEMA, UNCST, and NaFORRI have institutionalized knowledge and procedures that extend beyond project life. The integration of ABS checkpoints within UWA, NFA, and URSB ensures that regulatory functions continue under existing mandates. Community structures such as UOBDU and KWCG have developed self-sustaining local networks for knowledge exchange, gender inclusion, and benefit-sharing governance. In addition, the project has prioritized knowledge management and lesson-sharing, producing training manuals, awareness materials, and digital resources (including the ABS e-permit system and community protocol documentation) to ensure that institutional learning is retained and replicated nationally. Together, these mechanisms demonstrate that Uganda’s governance structures and human resource capacities are robust enough to continue delivering the benefits associated with the project outcomes beyond closure.

Findings Statements on Sustainability

- The project has established the essential policy, institutional, and community mechanisms needed for a smooth transition toward national management of ABS, providing a credible basis for long-term continuity under NEMA’s coordination.

- Government commitment and stakeholder ownership remain strong, supported by integration of ABS into national biodiversity and environment strategies and by active participation of IPLCs and sector agencies. Sustained sub-national engagement will, however, be required to maintain this momentum.

- Financial sustainability is emerging but not yet secured. While co-financing and in-kind support have been substantial, future continuity depends on integrating recurrent costs (system hosting, user support, compliance monitoring) into GoU line budgets. The successor design should include ring-fenced allocations and clear O&M responsibilities.

- A structured Exit & Sustainability Plan is required to (i) keep the ABS e-permit compliant and maintained post-project, (ii) document best practices (including a short video case series), and (iii) prepare a successor project focused on operationalizing benefit sharing regimes and technology transfer from research institutes to private manufacturers.

Rating for Likelihood of Sustainability: Likely (L)

Rating for Socio-political Sustainability: Likely (L)

Rating for Financial Sustainability: Moderately Likely (ML)

Rating for Institutional Sustainability: Likely (L)

  - Factors Affecting Performance and Cross-Cutting Issues

Quality of Project Management and Supervision

UNEP / Implementing Agency

- UNEP has provided consistent technical and administrative supervision through its Biodiversity and Land Branch under the Ecosystems Division. Regular backstopping, participation in PSC meetings, and timely feedback on progress and financial reports have ensured compliance with UNEP and GEF procedures. The UNEP Task Manager maintained active communication with NEMA and partners, offering flexibility in revising workplans following the COVID-19 disruptions. UNEP’s oversight during the development of the e-permit system and policy validation process ensured technical quality and alignment with global Nagoya Protocol implementation standards.

Partners / Executing Agency.

- NEMA has effectively coordinated project execution, financial management, and partner collaboration. PMU demonstrates sound administrative capacity, maintaining transparent reporting and effective procurement oversight. PSC meets regularly to review progress and provide strategic guidance. Executing partners (UNCST, UWA, NFA, NARO/NaFORRI, URSB, UOBDU) have contributed their sectoral expertise and mobilized co-financing as planned. Adaptive management measures, such as harmonized reporting templates and synchronized field missions have improved consistency and delivery.

Adaptive Management

- Adaptive management has been a strong feature of project implementation. COVID-19 restrictions delayed inception phase engagement and training. The project pivoted toward desk-based outputs (policies, strategies) during lockdown, then sequenced field activities once staffing and mobility normalized. From 2023 onward, targeted corrective measures, including accelerated recruitment and adoption of harmonized reporting templates, significantly improved implementation efficiency. Partners also transitioned to a coordinated quarterly planning system, clustering capacity building activities with monitoring missions to optimize resources and enhance overall delivery. Field lessons informed operational adjustments: for instance, NaFORRI restructured its community training on sandalwood propagation in Karamoja, and UOBDU adapted its engagement methods to better reach Batwa communities through local interpreters. These practices demonstrate learning and flexibility consistent with UNEP’s adaptive management principles.

Stakeholder Participation and Cooperation

- Stakeholder engagement is rated Satisfactory (S). The project has engaged a wide range of stakeholders across national, district, and community levels. Government ministries, academic and research institutions, NGOs, and IPLCs have participated in implementation and decision-making. Over 1,800 stakeholders (48% women) have benefited from awareness and training activities. Collaboration with UOBDU and KWCG has deepened local ownership in Kigezi and Karamoja respectively. Regular national consultations, joint monitoring visits, and PSC sessions have strengthened information flow and accountability. Embedding activities within existing institutional and community structures enhanced local capacity and legitimacy, particularly at border checkpoints and within IPLC networks, although it also required substantial coordination to maintain clarity of roles and responsibilities among the many actors involved.

- The high degree of cooperation between partners especially between NEMA, UNCST, and UNEP enabled integrated progress reporting, while technical collaboration between NaFORRI and NARO supported knowledge generation on plant species of economic potential. These partnerships have reduced duplication and increased the quality of outputs, particularly in developing policy instruments and field level protocols.

Responsiveness to Human Rights and Gender Equality

- Gender equality and inclusion are integrated across the project’s activities and outcomes. Women constitute approximately 48% of all trained participants, reflecting deliberate efforts by implementing partners to promote equal participation. The project also ensures IPLC representation in decision making forums and community agreements. Human rights principles, such as Free, Prior and Informed Consent (FPIC) and equitable benefit sharing are embedded in both the draft ABS Regulations and the community protocols developed under the pilots.

- The project’s approach to gender and rights has evolved adaptively. UOBDU and KWCG have incorporated gender responsive actions in CFM agreements, including the participation of women in benefit sharing committees. While more systematic disaggregation by youth and persons with disabilities is still required, current measures indicate strong alignment with UNEP’s Environmental and Social Safeguard (ESS) Standards.

- However, the absence of a dedicated gender officer, gender responsive evidence was uneven despite inclusive intent. Future project designs under GEF-7/8 should ensure that M&E, Gender/Safeguards, and Communications/Knowledge Management functions are fully staffed from the outset to strengthen evidence generation and inclusivity reporting.

Environmental and Social Safeguards

- Environmental and social safeguard compliance is rated Satisfactory (S). The project applied UNEP’s Environmental and Social Screening Procedures (ESSP) at design and continues to monitor potential impacts during implementation. None of the activities have triggered adverse environmental or social effects. Community engagement has followed FPIC guidelines, and project-supported CFM plans (e.g., TECA and LILO) include biodiversity conservation measures and equitable benefit-sharing arrangements. Safeguards monitoring is integrated into NEMA’s reporting framework, with no grievances recorded to date.

Country Ownership and Driven-ness

- Country ownership is rated Highly Satisfactory (HS). The project is nationally executed and fully aligned with Uganda’s Vision 2040, NBSAP II, and the National Environment Act (2019). MWE and NEMA have demonstrated strong leadership in coordinating national partners. The project’s integration within existing government systems ensures long-term sustainability. High level policy commitment evident in the validation of the National ABS Policy and Regulations underscores strong government-driven momentum for continuity.

Communication and Public Awareness

- Communication and outreach are rated Satisfactory (S). The project has implemented a comprehensive awareness strategy, producing radio campaigns, posters, and training manuals. Public communication has focused on explaining ABS principles, community rights, and procedures for compliance. The ABS Awareness Toolkit, documentaries, and visual materials developed by NEMA, UOBDU, and UNCST have enhanced understanding among researchers, community leaders, and policymakers. Public events such as national stakeholder workshops and regional consultations have further promoted visibility and cross-learning.

- The project’s media outputs and public dialogues have created a broad understanding of ABS as a national priority. Continued investment in digital communication and local-language materials will strengthen the long-term outreach and visibility of project results.

Findings Statements on Factors Affecting Performance and Cross-Cutting Issues

- Project management and supervision have been largely effective and adaptive, with NEMA providing strong coordination and UNEP offering steady technical guidance to uphold implementation quality. The chosen arrangement, with UNEP as Implementing Agency and NEMA as Executing Agency, was well suited to the project’s mandate and aligned with GEF requirements. Early implementation, however, was constrained by delayed PMU recruitment and the complexity of managing a wide network of mandated partners, which increased coordination burdens during the initial phase.

- Broad and well-structured stakeholder participation has enhanced ownership, cooperation, and the practical integration of ABS approaches across partner institutions. Gender equality, human rights, and safeguards have been meaningfully addressed, though continued improvement in tracking inclusion indicators is recommended. Strong national ownership and proactive communication have elevated ABS visibility and anchored its relevance within Uganda’s environmental policy framework.

Rating for Factors Affecting Performance and Cross-Cutting Issues: Satisfactory (S)

Rating for Quality of Project Management and Supervision: Satisfactory (S)

Rating for Stakeholders Participation and Cooperation: Satisfactory (S)

Rating for Responsiveness to Human Rights and Gender Equality: Satisfactory (S)

Rating for Environmental and Social Safeguards: Satisfactory (S)

Rating for Country Ownership and Driven-ness: Highly Satisfactory (HS)

Rating for Communication and Public Awareness: Satisfactory (S)

# VI CONCLUSIONS AND RECOMMENDATIONS

  - Conclusions

The Uganda ABS Project is performing at a Satisfactory (S) level and is on track to achieve its objective of strengthening Uganda’s institutional, legal, and technical capacity to implement the Nagoya Protocol. Across four consecutive PIRs (FY2022–FY2025), the project has consistently maintained Satisfactory ratings for outcomes and outputs, with low overall risk, indicating stable implementation and effective management

A core achievement of the project is the near-completion of Uganda’s national ABS legal framework. The Draft National ABS Policy (2024), updated ABS Regulations (2024), and updated ABS Implementation Guidelines (2024) have been developed, validated, and reviewed by NEMA Top Management and are pending formal approval and gazettement. In addition, sector-specific instruments such as the Draft Uganda Wildlife (Community Resource Access) Regulations (2024) and updated CFM and revenue-sharing frameworks have strengthened alignment between biodiversity governance and ABS principles. In total, 13 regulatory frameworks have been developed or updated under the project, exceeding the original target of three

Institutional capacity for ABS implementation has been significantly strengthened beyond original targets. While the project planned to capacitate 15 institutions, a total of 27 national, sub-national, and community-level institutions have been trained and are now able to implement ABS processes. These include NEMA, UNCST, UWA, NFA, NaFORRI, PGRC, Makerere University, NCRI, and 11 district local governments across Karamoja and Kigezi. Importantly, several institutions particularly NEMA, UNCST, PGRC, and NaFORRI—are now able to independently negotiate and enforce PIC and MAT agreements, reflecting functional rather than nominal capacity

The project has also delivered a major innovation through the development of an electronic ABS permit and compliance monitoring system. The system integrates permit application, PIC and MAT documentation, and certification of compliance, addressing a critical gap that previously limited Uganda’s ability to monitor utilization of genetic resources beyond national borders. In parallel, five ABS checkpoints have been formally designated (including URA, NFA, MAAIF, MoLG, and Makerere University), with additional checkpoints identified and scheduled for gazettement and training. Although system has been validated and now awaiting commissioning, placing Uganda among the leading ABS implementers on the continent.

At the community level, the project has demonstrated operational ABS models linking policy to practice. In Kisoro District, documentation of Batwa traditional knowledge identified 234 medicinal plant species used to treat 72–84 health conditions, leading to the development of six PIC/MAT-based benefit-sharing agreements and initial formulations for malaria and cough remedies. In Karamoja, four community protocols on Osyris lanceolata (sandalwood) have been developed, alongside the establishment of a two-acre sandalwood demonstration plot at Nabuin ZARDI and the publication of three practical propagation and management guides. These pilots confirm the feasibility of community-driven ABS arrangements grounded in conservation, livelihoods, and cultural integrity. In addition, 4 community pilot projects on ABS interventions have been established in both Kigezi and Karamoja, these projects have already yielded results through establishment of community nurseries where seedlings are raised for sale.

The project has also achieved substantial results in gender equality and IPLC inclusion. Women’s participation in ABS activities has reached 30% at national level and over 60% at community level, exceeding project targets. The development of a Draft ABS Gender Mainstreaming Strategy and Guidelines, together with targeted engagement of women-led groups such as the Karamoja Women Cultural Group, has institutionalized gender-responsive ABS practice and strengthened the role of women as custodians of genetic resources and traditional knowledge

While early implementation was affected by COVID-19 disruptions, initial disbursement delays, and staffing transitions, adaptive management measures including workplan revisions and a one-year no-cost extension have enabled recovery without compromising outcome delivery. The project now demonstrates strong institutional ownership, high stakeholder buy-in, and clear pathways to sustainability. The primary remaining risk relates not to delivery, but to post-project financing and operationalization of approved systems and policies.

B. Recommendations

To consolidate gains and ensure the sustainability and long-term impact of project outcomes, the following recommendations are proposed:

- Finalize and operationalize the ABS legal framework. Priority should be given to completing the approval and gazettement of the National ABS Policy, Regulations, and Guidelines. Clear implementation roadmaps should accompany approval to ensure rapid uptake by line ministries, departments, sectors, agencies, and local governments.

- Commission and fully operationalize the electronic ABS system. The ABS e-permit management and compliance monitoring systems should be validated, approved, and deployed nationwide. Adequate resources should be allocated for system maintenance, user training, and long-term hosting to avoid post-project system degradation.

- Strengthen financial sustainability for ABS implementation. The Ministry of Water and Environment, in collaboration with the Ministry of Finance, should integrate core ABS functions into recurrent budgets of NEMA and designated competent authorities. This will reduce reliance on project financing and ensure continuity of regulatory oversight.

- Scale up community-based ABS models. Successful pilots in Karamoja and Kigezi should be documented and replicated in other biodiversity-rich regions. Particular emphasis should be placed on community protocols, traditional knowledge protection, and value-chain-based benefit sharing for priority species.

- Institutionalize gender and IPLC inclusion. The draft ABS gender mainstreaming strategy and guidelines should be approved and embedded within standard operating procedures of implementing agencies and institutions. Continued monitoring of gender and IPLC outcomes should be maintained beyond the project lifespan.

- Sustain capacity development and learning. Ongoing training for checkpoints, competent authorities, and local governments should continue through national training institutions and universities. Knowledge products generated by the project should be systematically disseminated and integrated into curricula and professional development programs.

- Strengthen monitoring, learning, and regional positioning. Uganda should leverage the project’s achievements to position itself as a regional leader in ABS implementation, including through South–South cooperation, experience sharing, and participation in global ABS platforms.

Table 15: Project Performance Ratings

| Criterion | Summary Assessment | Rating |
| --- | --- | --- |
| Strategic Relevance | Strong alignment with UNEP, GEF, and Uganda’s biodiversity strategies (NBSAP II, Vision 2040, CBD/Nagoya Protocol) | Highly Satisfactory (HS) |
| Effectiveness | Most outputs achieved or on track; outcomes likely to be met by closure | Highly Satisfactory (HS) |
| Financial Management | Transparent reporting and adherence to UNEP/GEF policies; co-financing mobilized as planned | Satisfactory (S) |
| Efficiency | Timelines affected by COVID-19, but adaptive management minimized delays | Moderately Satisfactory (MS) |
| Monitoring and Reporting | Functional and improving monitoring framework; regular reporting and adaptive use of data | Satisfactory (S) |
| Exit Strategy and Sustainability | Institutional and socio-political sustainability rated Likely; financial sustainability Moderately Likely | Satisfactory (S) |
| Factors Affecting Performance | Quality management, cooperation, and adaptive supervision rated Satisfactory | Satisfactory (S) |
| Overall Project Performance Rating at Mid-Point | Overall progress and delivery rated satisfactory | Satisfactory (S) |

  - Lessons learned

| Lesson Learned #1: | Early policy validation and legal anchoring are essential for national ownership and sustainability |
| --- | --- |
| Context / Comment: | The project confirmed that early validation of the draft ABS Policy and Regulations accelerated national ownership and guided coherent institutional action. Legal anchoring of ABS instruments within the MWE and NEMA has ensured that Uganda’s compliance mechanisms under the Nagoya Protocol are nationally driven and enforceable. Fast tracking gazettement will consolidate these gains and provide a lasting policy foundation. This lesson is applicable to all biodiversity governance and regulatory reform projects where sustainability depends on statutory approval. |
| Cross-reference(s) to Relevant Paragraphs: | 3–10, 95–99, 44–45 |

| Lesson Learned #2: | Digital tools improve governance and transparency but require continuous local capacity support (technical and financial backstopping) |
| --- | --- |
| Context / Comment: | The ABS e-Permit system significantly improved transparency, traceability, and coordination among UNCST, NEMA, UWA, and other checkpoints. However, sustainability depends on government budget allocation, staffing, and system hosting beyond project closure. This lesson is applicable to all digital governance and regulatory platforms in environmental management. |
| Cross-reference(s) to Relevant Paragraphs: | 30–32, 84–85, 100–102 |

| Lesson Learned #3: | Multi-agency coordination enhances implementation efficiency, adaptive management and improves accountability but requires structured monitoring tools |
| --- | --- |
| Context / Comment: | The Uganda ABS Project demonstrates that strong cross-institutional coordination among NEMA, UNCST, UWA, NFA, and other partners can reduce duplication, strengthen accountability, and enhance legitimacy in national ABS implementation. However, working with more than ten implementing partners also created significant coordination and reporting pressures, especially during the early years when harmonised M&E tools and a dedicated M&E function were not yet in place. The experience shows that without a structured Monitoring, Evaluation and Learning (MEL) system, multi-partner programmes face risks of inconsistent reporting, delayed evidence synthesis, and reduced adaptive management capacity. In this project, the later introduction of harmonised reporting templates, joint field missions, and regular Project Steering Committee meetings helped restore coordination and implementation momentum, even under COVID-19 disruptions and budget constraints. This lesson is applicable to all multi-agency environmental governance and ABS programmes: institutional coordination mechanisms must be matched by sufficient financing, dedicated MEL capacity, and harmonised reporting systems from the outset, particularly where national-level policy reform is combined with community-level pilots. |
| Cross-reference(s) to Relevant Paragraphs: | 69–72, 76–77, 95–101, 35, 44–45 |

| Lesson Learned #4: | Meaningful participation of IPLCs ensures legitimacy, culture, relevance, equity, and long-term sustainability of ABS pilots |
| --- | --- |
| Context / Comment: | The pilots in Karamoja (Kadam and Napak) and Kigezi (Batwa communities) demonstrate that when Indigenous Peoples and Local Communities are actively involved in documenting traditional knowledge, negotiating PIC and MAT, and participating in resource governance, ABS systems become more credible, functional, and sustainable. Integrating community protocols and customary governance structures into national ABS mechanisms strengthened compliance, reduced conflicts, and improved alignment between national regulations and local practices. This lesson is applicable to all biodiversity and ABS programmes that depend on community-level stewardship and traditional knowledge for long-term success. |
| Cross-reference(s) to Relevant Paragraphs: | 76–79, 99, 101, 103 |

| Lesson Learned #5: | Early recruitment of a fully staffed PMU is critical for smooth implementation |
| --- | --- |
| Context / Comment: | Timely recruitment of a fully staffed Project Management Unit including; a Project Manager, site officers, and dedicated Monitoring & Evaluation and Gender/Safeguards focal points is essential to avoid early implementation bottlenecks. In this project, delays in filling PMU positions contributed to stalled fieldwork, slow financial reporting, and delayed disbursement of subsequent cash advances. Delays in hiring directly contributed to the need for a no-cost extension. Where staffing was in place, reporting improved, coordination across partners was stronger, and evidence on inclusivity (gender, IPLCs, youth) was more systematically captured. This lesson is applicable to all complex, multi-partner projects where timely staffing is critical to coordination, reporting, and adaptive management. |
| Cross-reference(s) to Relevant Paragraphs: | 28 |

| Lesson Learned #6: | Private sector engagement is pivotal for valorization and tangible ABS benefits |
| --- | --- |
| Context / Comment: | Effective valorization of genetic resources requires deliberate technology transfer and structured engagement with private sector actors. Research institutes such as NARO have developed GR based products and propagation systems (e.g., medicinal formulations, sandalwood nurseries), but these only translate into ABS compliant livelihood benefits for IPLCs when linked to commercial producers under clear agreements (e.g., MTAs, PIC/MAT). The project shows that without purposeful Research and Discovery to market pathways, innovations risk remaining at pilot stage, limiting real world benefit sharing outcomes for communities. |
| Cross-reference(s) to Relevant Paragraphs: | 22–25, 101–103 |

| Lesson Learned #7: | Gender-responsive ABS design enhances equity, effectiveness, and sustainability when embedded as a core implementation principle |
| --- | --- |
| Context / Comment: | The Uganda ABS Project shows that gender mainstreaming is most effective when built into project design and delivery rather than treated as a stand-alone activity. The use of minimum female participation thresholds, culturally sensitive facilitation, and targeted engagement enabled women particularly among the Batwa and Karamoja communities to become active contributors to traditional knowledge documentation, community organization, and benefit-sharing processes. Women-led initiatives in herbal medicine development and sandalwood value chains strengthened social inclusion and livelihood outcomes. This lesson is relevant to all biodiversity, natural-resource, and ABS programmes seeking to combine conservation objectives with gender equality and poverty reduction. |
| Cross-reference(s) to Relevant Paragraphs: | 45, 50 |

| Lesson Learned #8: | Human-rights-based ABS approaches strengthen IPLC empowerment, compliance, and social legitimacy |
| --- | --- |
| Context / Comment: | The project demonstrates that treating PIC, MAT, and community protocols as empowerment tools rather than mere compliance requirements strengthens the protection of Indigenous Peoples’ and Local Communities’ rights. Community led consultations, use of local languages, involvement of elders, women, and youth, and iterative validation processes increased understanding of rights, negotiating power, and social recognition. This was evident in Batwa community protocols for herbal medicine development and in Karamoja and protected-area landscapes where ABS compliant CFM and CRM agreements improved rights-based access to genetic resources while reducing conflict and exclusion. This lesson is applicable to all projects operating at the intersection of biodiversity conservation, Indigenous rights, and equitable benefit sharing. |
| Cross-reference(s) to Relevant Paragraphs: | 87–92, 134–138, 176–179 |

  - Recommendations

| Recommendation #1: | Finalize and gazette the National ABS Policy and Regulations, and establish a sequenced operational implementation roadmap |
| --- | --- |
| Challenge / Problem to be Addressed: | The draft ABS Policy and Regulations remain pending Cabinet approval and gazettement, delaying establishment of a fully functional national ABS system and weakening enforcement of benefit-sharing mechanisms. Legal anchoring is required to operationalize ABS procedures, formalize checkpoints, and activate the ABS Committee. |
| Cross-reference(s) to Relevant Paragraphs: | 3–10, 95–99, 44–45 |
| Priority Level: | High |
| Type of Recommendation: | Strategic / Policy / Legal |
| Responsibility: | MWE, NEMA, Attorney General’s Chambers, UNEP |
| Proposed Implementation Time-frame: | By Q2 2026 (Could even stretch to end of Project reference to Government Approval Process) |

| Recommendation #2: | Operationalize and Sustain the National e-Permit and Compliance Management System |
| --- | --- |
| Challenge / Problem to be Addressed: | Although the digital ABS e-permit system is under development, full roll-out and integration into national ICT and budget frameworks are required to ensure long term functionality supported by ongoing capacity development for system users. Without budget for IT maintenance, user support, and system upgrades, the digital compliance system risks collapsing after project closure. |
| Cross-reference(s) to Relevant Paragraphs: | 30–32, 84–85, 100–102 |
| Priority Level: | High |
| Type of Recommendation: | Institutional / Financial / Technical |
| Responsibility: | UNCST, NEMA, MoFPED, UWA, NFA, URSB |
| Proposed Implementation Time-frame: | Roll out by Q3 2026 and maintenance budget from FY 2026/27 onward |

| Recommendation #3: | Institutionalize a National ABS Coordination and Monitoring Framework with harmonized reporting tools |
| --- | --- |
| Challenge / Problem to be Addressed: | Fragmented reporting and limited cross-agency oversight constrain adaptive management and coordinated data use across institutions. Standardized M&E templates, joint reviews, and clearer reporting lines will improve evidence generation and coordination across partners. |
| Cross-reference(s) to Relevant Paragraphs: | 69–72, 76–77, 95–103 |
| Priority Level: | High |
| Type of Recommendation: | Governance / Monitoring and Evaluation |
| Responsibility: | NEMA (PMU), MWE, UNCST, UWA, NFA, NARO, UOBDU, KWCG |
| Proposed Implementation Time-frame: | MEL framework operational by mid-2026 |

| Recommendation #4: | Enhance Gender, Youth and IPLC Participation in ABS Implementation |
| --- | --- |
| Challenge / Problem to be Addressed: | Women represent 48% of beneficiaries, but youth and persons with disabilities remain under represented; stronger gender responsive targets and inclusive training mechanisms are needed |
| Cross-reference(s) to Relevant Paragraphs: | 78–79, 96–101 |
| Priority Level: | Medium |
| Type of Recommendation: | Social Inclusion / Capacity Building |
| Responsibility: | NEMA, UOBDU, KWCG, District Local Governments, UNCST Gender Focal Points |
| Proposed Implementation Time-frame: | 2025–2026 (Ongoing) |

| Recommendation #5: | Strengthen District and Community-Level Institutional Capacity for ABS Implementation and institutionalize IPLC led models through legally recognized community protocols |
| --- | --- |
| Challenge / Problem to be Addressed: | Limited capacity among district officials and traditional leaders may hinder the sustainability of community ABS initiatives and equitable benefit sharing practices. Batwa and Karamoja lessons show that cultural stewardship improves compliance and sustainability; these models should be scaled and formalized. |
| Cross-reference(s) to Relevant Paragraphs: | 76–77, 101–103 |
| Priority Level: | Medium |
| Type of Recommendation: | Capacity / Stakeholder |
| Responsibility: | NEMA, UOBDU, KWCG, District Local Governments |
| Proposed Implementation Time-frame: | 2025–2026 (Ongoing) (Could even stretch to end of Project) |

# ANNEX I: RESPONSE TO STAKEHOLDER COMMENTS

Table 16: Response to stakeholder comments received but not (fully) accepted by the reviewer, where appropriate.

| Page Ref | Stakeholder comment | Reviewer Response |
| --- | --- | --- |
|  | N/A, all comments were addressed | N/A |

# ANNEX II:	PEOPLE CONSULTED DURING THE REVIEW

| Organization | Position | Role in the project | Gender |
| --- | --- | --- | --- |
| UNEP | Portfolio Manager | Portfolio Management | M |
| UNEP | Task Manager | GEF Task Manager | F |
| UNEP | Budget/Finance Officer | Financial Management | M |
| NEMA | Project Officer-ABS | Field coordination | M |
|  | ABS-Manager | Overall Project management | M |
|  | P.O ABS | Coordination | M |
| NFA | Supervisor-NFA | CFM-partner Coordination | M |
| UNCST | Executive Director | Issues research permits; enforces ABS compliance; provides technical guidance. | M |
| NAFORRI | Principal Research Officer | Forestry Research and Development | M |
| NARO-PGRC | Senior Research Officer | Genetic Resources Research and Development | F/M |
| UWA | ABS Project Office/r | Oversees access to wildlife genetic resources and enforces ABS agreements in protected areas. | F |
| Makerere University | Coordinator | Develops ABS related curricula; conducts capacity building and research on genetic resources and traditional knowledge. | F |
| Natural Chemotherapeutics Institute | Principal Researcher | Research and Development | M |
| MWE | National Focal Point Officer | National Focal Point for the Nagoya Protocol; chairs the National Project Steering Committee (NPSC); provides policy direction and oversight. | M |
| Moroto DLG | Planner | District stakeholder | F |
|  | DNRO | District stakeholder | M |
|  | For CAO | District Stakeholder | M |
| Musupo | Member | Activities support | M |
|  | Member | Activities support | M |
|  | Member | Activities support | M |
|  | Member | Activities support | M |
|  | Member | Activities support | F |
|  | Member | Activities support | F |
|  | Member | Activities support | F |
|  | Member | Activities support | F |
|  | Member | Activities support | F |
|  | Member | Activities support | F |
| Rupa | Member | Activities support | F |
|  | Member | Activities support | F |
|  | Member | Activities support | F |
|  | Member | Activities support | F |
|  | Member | Activities support | F |
|  | Member | Activities support | F |
|  | Member | Activities support | F |
| KWCG | Officer | Partnership activities | F |
|  | Ass ED | Partnership activities | M |
|  | Officer-Finance | Partnership activities | M |
| Kangole | Member | Activities Support | F |
|  | Member | Activities Support | F |
|  | Member | Activities Support | F |
|  | Member | Activities Support | F |
|  | Member | Activities Support | F |
|  | Member | Activities Support | F |
|  | Member | Activities Support | F |
|  | Member | Activities Support | F |
|  | Member | Activities Support | F |
|  | Member | Activities Support | F |
| NARO | Site Support | Partnership activities | F |
|  | Scientist | Partnership activities | M |
|  | Scientist | Partnership activities | M |
| Kisoro DLG | LCV Chairperson | Over sight | M |
|  | Dist Natural Resources officer | Technical support | F |
|  | For CAO Kisoro | Over sight | M |
|  | Dist. Comm. Dev’t Officer | Technical support | M |
| UOBDU | Executive Director | Supervisory | F |
|  | Field officer | Supportive | M |
|  | Land Rights Officer | Supportive | F |
| Bukimbiri IPLC Herbal group | Chair person | Leadership | M |
|  | Treasurer | Activities support | F |
|  | Secretary | Activities support | M |
|  | Member | Activities support | F |
|  | Member | Activities support | M |
|  | Member | Activities support | M |
|  | Member | Activities support | M |
|  | Member | Activities support | M |
|  | Member | Activities support | M |
|  | Member | Activities support | M |
|  | Member | Activities support | M |
|  | Member | Activities support | M |
|  | Member | Activities support | M |
|  | Member | Activities support | M |
|  | Member | Activities support | M |
|  | Member | Activities support | M |
|  | Member | Activities support | F |
|  | Member | Activities support | F |
|  | Member | Activities support | F |
|  | Member | Activities support | F |
| Muramba IPLC Herbal group | Chairperson | Leadership | F |
|  | Mobiliser | Activities support | F |
|  | Secretary | Activities support | M |
|  | Treasurer | Activities support | F |
|  | Member | Activities support | F |
|  | Member | Activities support | M |
|  | Def Sec | Activities support | M |
|  | Member | Activities support | F |
|  | Member | Activities support | F |
|  | Member | Activities support | M |
|  | Member | Activities support | F |
|  | Member | Activities support | F |
|  | Member | Activities support | F |
|  | Member | Activities support | F |
|  | Member | Activities support | F |
|  | Member | Activities support | F |
|  | Member | Activities support | M |
|  | Member | Activities support | F |
|  | Member | Activities support | F |
|  | Member | Activities support | M |
|  | Member | Activities support | F |
|  | Member | Activities support | F |
|  | Member | Activities support | F |
|  | Member | Activities support | M |
|  | Member | Activities support | F |
|  | Member | Activities support | F |
|  | Member | Activities support | F |
|  | Member | Activities support | F |
| Kanaba IPLCs Herbal group | Chair Person | Leadership | M |
|  | Vice Chair Person | Activities support | M |
|  | Treasurer | Activities support | F |
|  | Member | Activities support | M |
|  | Member | Activities support | F |
|  | Member | Activities support | M |
|  | Member | Activities support | M |
|  | Member | Activities support | M |
|  | Member | Activities support | F |
|  | Member | Activities support | F |
|  | Member | Activities support | F |
|  | Member | Activities support | F |
|  | Member | Activities support | F |
|  | Member | Activities support | F |
|  | Member | Activities support | F |
|  | Member | Activities support | M |
|  | Member | Activities support | M |
|  | Member | Activities support | M |
|  | Member | Activities support | M |
|  | Member | Activities support | F |
|  | Member | Activities support | F |
|  | Member | Activities support | M |
|  | Member | Activities support | M |
|  | Member | Activities support | M |
|  | Member | Activities support | M |
|  | Member | Activities support | M |
|  | Member | Activities support | M |
|  | Member | Activities support | M |
|  | Member | Activities support | M |
|  | Member | Activities support | M |
|  | Member | Activities support | M |
|  | Member | Activities support | M |
|  | Member | Activities support | M |
|  | Member | Activities support | M |
|  | Member | Activities support | M |
|  | Member | Activities support | M |
|  | Member | Activities support | M |
|  | Member | Activities support | M |

# ANNEX III: KEY DOCUMENTS CONSULTED

PROJECT PLANNING AND REPORTING DOCUMENTS

- Project Document: Institutional Capacity Strengthening for Implementation of the Nagoya Protocol on Access to Genetic Resources and Benefit Sharing in Uganda (GEF ID 9481), UNEP 2020.

- Project Cooperation Agreement (UNEP – NEMA), January 2021.

- Inception Report – Approved Version, October 2025.

- Annual Project Implementation Reports (PIRs) 2023, 2024 and 2025.

- Half-Yearly Technical Progress Reports (Jan–Jun 2023; Jul–Dec 2023; Jan–Jun 2024).

- National Steering Committee and Technical Committee Meeting Minutes (2021–2025).

- Partner Financial Statements and Co-Financing Commitment Letters (NEMA, UNCST, UWA, NFA, NaFORRI, URSB).

PROJECT OUTPUTS – OVERALL

- Draft National ABS Policy and Regulations (2024) – validated for Cabinet submission.

- National ABS Awareness and Communication Strategy (2023).

- Gender and Social Inclusion Plan (2022).

- National Training Manual on Access and Benefit Sharing (2023).

- Electronic ABS Permit Management System (ABS-eReg) – System Design, User Manual and Testing Reports.

- ABS Knowledge Products (Publications, Policy Briefs, Case Studies and Newsletter 2023–2025).

PROJECT OUTPUTS WORK PACKAGE 1: LEGAL AND INSTITUTIONAL FRAMEWORK

- Draft ABS Policy and Regulations – Validation Workshop Report (2024).

- Regulatory Impact Assessment on ABS Policy Implementation (2023).

- National ABS Committee Terms of Reference (2023).

- Institutional Roles and Responsibilities Matrix for ABS Implementation (NEMA, UNCST, UWA, NFA, URSB).

PROJECT OUTPUTS WORK PACKAGE 2: CAPACITY BUILDING AND INSTITUTIONAL STRENGTHENING

- ABS Training Modules and Curriculum (UNEP / NEMA / Makerere University 2023).

- Training Reports for NEMA, UWA and UNCST Staff (2022–2024).

- Makerere University Postgraduate Module on ABS (2023).

- Research Fellowship Reports on Biodiversity and Genetic Resource Use (2023–2025).

PROJECT OUTPUTS WORK PACKAGE 3: COMMUNITY PILOTS AND BENEFIT SHARING

- Community Protocols for Batwa and Karamojong Communities (2024).

- Collaborative Forest Management (CFM) Agreements – TECA and LILO (2023).

- Benefit-Sharing Model Guidelines and Implementation Plans (2024).

- Field Mission Reports – Kigezi and Karamoja Subregions (August 2025).

- Community Consultation Minutes and Traditional Knowledge Inventories (2024–2025).

PROJECT OUTPUTS WORK PACKAGE 4: COMMUNICATION AND KNOWLEDGE MANAGEMENT

- ABS Awareness Campaign Radio and TV Scripts (2023).

- Simplified ABS Guidelines and IEC Materials in English and Local Languages (2023–2024).

- National ABS Portal Analytics Reports (2023–2025).

- Participation Reports from CBD COP-16 and Regional ABS Forums (2024).

PREVIOUS REVIEWS / EVALUATIONS

- UNEP Mid-Term Review Guidelines (2022 Edition).

- MTR Template Version “08 MTR MAIN REPORT TEMPLATE 25.06.25”.

- Relevant Regional ABS Evaluations (Comoros, Ethiopia GEF ABS Projects 2022–2023).

- National Environment Act Implementation Review (2023).

REFERENCE DOCUMENTS

- Convention on Biological Diversity (1992) and Nagoya Protocol (2010).

- Uganda Vision 2040 and National Development Plan III.

- National Biodiversity Strategy and Action Plan II (2015–2025).

- National Environment Act (2019).

- Wildlife Act (2019).

- UNEP Evaluation Policy (2022).

- UNEG Ethical Guidelines (2020).

- GEF Biodiversity Focal Area Strategy (GEF-6).

# ANNEX IV: REVIEW ITINERARY

| Date | Location | Activity / Focus | Institutions / Stakeholders Engaged |
| --- | --- | --- | --- |
| 3 – 30 Sept 2025 | Desk / Virtual (Kampala) | Inception meetings; document review; refinement of review framework and interview tools. | UNEP Task Manager; NEMA PMU; UNCST; UWA; NFA; UOBDU. |
| 22 - 25 Oct 2025 | Kigezi Subregion (Kabale & Kisoro Districts) | Field mission #1: Community consultations with Batwa groups around Bwindi and Mgahinga; observation of ABS pilot activities and benefit-sharing arrangements. | UOBDU; District Environment Offices; Community Leaders (Batwa); CFM groups; NEMA Regional Officer. |
| 14 – 17 Oct 2025 | Karamoja Subregion (Napak & Kadam CFR) | Field mission #2: Assessment of community protocols and CFM integration of ABS; training follow-up for women and youth groups. | KWCG; NaFORRI; NFA; UWA Regional Staff; District Environment Officers; Community Representatives. |
| 30 Sept -10 Oct 2025 | Kampala & Entebbe | National-level consultations; key informant interviews with implementing partners and policy actors. | MWE; NEMA; UNCST; URSB; Makerere University; GEF Operational Focal Point (MoFPED). |
| 13 – 20 Nov 2025 | Desk / Virtual (Kampala) | Triangulation of field findings; stakeholder verification meetings via Zoom; drafting of initial findings matrix. | NEMA PMU; UNEP Task Manager; UWA; NFA; UOBDU. |
| 30 Nov 2025 | Kampala | Validation workshop with Project Steering Committee and key partners; discussion of draft findings and ratings. | NEMA; UNCST; MWE; UWA; NFA; NaFORRI; URSB; UOBDU; KWCG; MoFPED; UNEP. |
| 20 Nov – 30 Dec 2025 | Desk Review / Reporting Phase | Integration of comments from validation meeting and UNEP review; finalization of MTR Report | NEMA PMU; UNEP Task Manager. |

# ANNEX V: COMMUNICATION AND OUTREACH TOOLS

The key findings of the review report were presented to the stakeholders using a PowerPoint which can be accessed on the link below.

PPT presentation

# ANNEX VI: SAFEGUARDS ASSESSMENT TOOL

Assessment of the Management of Environmental and Social Safeguards1 by the Project2

Project: Institutional Capacity Strengthening for Implementation of the Nagoya Protocol on Access to Genetic Resources and Benefit Sharing in Uganda (GEF ID 9481)

Implementing Agency: UNEP  Executing Agency: NEMA

Review Type: Mid-Term Review  Date: November 2025

Objectives:

- To assess sufficiency in planning for Environmental and Social Safeguards (ESS) during project design

- To assess monitoring of potential and/or emerging ESS risks during project implementation

- To assess management responsiveness to ESS events that are triggered during project implementation

| ESS PLANNING AT PROJECT DESIGN |  |
| --- | --- |
| List any ESS issues identified at project design (e.g. SS 1.7, SS 2.3, etc.)3 | SS 1.12 (Collection and utilization of genetic resources); SS 4 (Community health, safety and security through CFM activities); SS 7 (Indigenous Peoples – Batwa and Karamojong IPLCs); SS 8 (Labour and working conditions for community contract staff) |
| For any ESS issues identified at project design, were mitigation strategies developed (Y/N)? (If yes, briefly describe) | Yes. The Project Document included an Environmental and Social Screening Checklist, a Stakeholder Engagement Plan, and a Gender and Social Inclusion Plan (2022). Mitigation included: prior informed consent for community engagement; adherence to Uganda OSH Regulations; and integration of IPLC protocols into CFM agreements. |
| Were any gaps in ESS issues identified at the review inception phase (Y/N)? (If yes, briefly describe) | No major gaps |

| ESS MONITORING AT PROJECT IMPLEMENTATION |  |
| --- | --- |
| Is there evidence that the potential emergence of ESS issues was actively monitored during project implementation (Y/N)? 4 (If yes, briefly describe) | Yes. Safeguards monitoring integrated into quarterly and annual reports. Each field activity undergoes screening via NEMA’s E&S Checklist. UNCST applies ethics compliance review to all research permits. Field missions (Aug 2025) verified safe community engagement and gender balance. |
| Is there a justification for the absence of ESS monitoring (Y/N)? (If yes, briefly describe5) | No. Monitoring evidenced in all active sites. UNEP’s Task Manager reviewed ESS adherence through PIR reports. |

| MANAGEMENT RESPONSIVENESS DURING PROJECT IMPLEMENTATION |  |
| --- | --- |
| Identify the ESS issues/events triggered 6 by the project.7 | - Engagement with Indigenous Communities (Batwa & Karamojong) - Collection and Documentation of Traditional Knowledge (ABS Pilots) - Gender Participation and Youth Inclusion - COVID-19 Health Risks |
| Describe consequences of ESS issues/events during project implementation. | - Potential cultural-heritage and participation risks due to language and literacy barriers. - Risk of misuse or non-attribution of community knowledge. - Under-representation of youth and PWDs in early training cycles. - Early restrictions (2021–2022) affected training and consultations. |
| Describe the management response and identify supporting documentation. 8, 9 | - Local interpreters and cultural focal persons engaged; community protocols translated; prior informed consent forms signed. (Field reports Aug 2025; UOBDU/KWCG records) - Use of community-led TK documentation under PIC and MAT framework; benefit-sharing clauses verified by NEMA Legal Unit. - Gender Action Plan (2022) implemented; new targets set (≥ 50 % female representation; 20 % youth); adjusted in 2024 workplan. - Virtual training modules and small-group sessions used; preventive measures implemented. |
| Were negative ESS effects offset by management response (Y/N)? (If yes, briefly describe) | - Yes. Risks mitigated through inclusive facilitation. - Yes. Legal safeguards applied. - Yes. Participation levels improved to 48% female by mid-2025. - Yes. Continuity maintained with no recorded health incidents. |

Table 1. List of Safeguards Standards and their associated risks

(For reference only. These lists may be deleted in the Final Report)

Safeguards Standards 1: Biodiversity, Ecosystems and Sustainable Natural Resource Management

Safeguards Risk Checklist Did the project involve or lead to:

1.1 conversion or degradation of habitats (including modified habitat, natural habitat and critical natural habitat) or losses and threats to biodiversity and/or ecosystems and ecosystem services?

1.2 adverse impacts specifically to habitats that are legally protected, officially proposed for protection, or recognized as protected by traditional local communities and/or authoritative sources (e.g. National Park, Nature Conservancy, Indigenous Community Conserved Area, (ICCA); etc.)?

1.3 conversion or degradation of habitats that are identified by authoritative sources for their high conservation and biodiversity value?

1.4 activities that are not legally permitted or are inconsistent with any officially recognized management plans for the area?

1.5 risks to endangered species (e.g. reduction, encroachment on habitat)?

1.6 activities that may result in soil erosion, deterioration and/or land degradation?

1.7 reduced quality or quantity of ground water or water in rivers, ponds, lakes, other wetlands?

1.8 reforestation, plantation development and/or forest harvesting?

1.9 support for agricultural production, animal/fish production and harvesting

1.10 introduction or utilization of any invasive alien species of flora and fauna, whether accidental or intentional?

1.11 handling or utilization of genetically modified organisms?

1.12 collection and utilization of genetic resources?

Safeguards Standards 2: Climate Change and Disaster Risks

Safeguards Risk Checklist Did the project involve or lead to:

2.1 reducing resilience against potential climate change impact beyond the project intervention period?

2.2 areas that are now or are projected to be subject to natural hazards such as extreme temperatures, earthquakes, extreme precipitation and flooding, landslides, droughts, severe winds, sea level rise, storm surges, tsunami or volcanic eruptions in the next 30 years?

2.3 outputs and outcomes sensitive or vulnerable to potential impacts of climate change (e.g. changes in precipitation, temperature, salinity, extreme events)?

2.4 local communities vulnerable to the impacts of climate change and disaster risks (e.g. considering level of exposure and adaptive capacity)?

2.5 increases of greenhouse gas emissions, black carbon emissions or other drivers of climate change?

2.6 Carbon sequestration and reduction of greenhouse emissions, resource-efficient and low carbon development, other measures for mitigating climate change?

Safeguards Standards 3: Pollution Prevention and Resource Efficiency

Safeguards Risk Checklist Did the project involve or lead to:

3.1 the release of pollutants to the environment due to routine or non-routine circumstances with the potential for adverse local, regional, and/or transboundary impacts?

3.2 the generation of waste (both hazardous and non-hazardous)?

3.3 the manufacture, trade, release, and/or use of hazardous materials and/or chemicals?

3.4 the use of chemicals or materials subject to international bans or phase-outs? (e.g. DDT, PCBs and other chemicals listed in international conventions such as the Montreal Protocol, Minamata Convention, Basel Convention, Rotterdam Convention, Stockholm Convention)?

3.5 the application of pesticides or fertilizers that may have a negative effect on the environment (including non-target species) or human health?

3.6 significant consumption of energy, water, or other material inputs?

Safeguards Standards 4: Community Health, Safety and Security

Safeguards Risk Checklist Did the project involve or lead to:

4.1 the design, construction, operation and/or decommissioning of structural elements such as new buildings or structures (including those accessed by the public)?

4.2 air pollution, noise, vibration, traffic, physical hazards, water runoff?

4.3 exposure to water-borne or other vector-borne diseases (e.g. temporary breeding habitats), communicable or noncommunicable diseases?

4.4 adverse impacts on natural resources and/or ecosystem services relevant to the communities’ health and safety (e.g. food, surface water purification, natural buffers from flooding)?

4.5 transport, storage use and/or disposal of hazardous or dangerous materials (e.g. fuel, explosives, other chemicals that may cause an emergency event)?

4.6 engagement of security personnel to support project activities (e.g. protection of property or personnel, patrolling of protected areas)?

4.7 an influx of workers to the project area or security personnel (e.g. police, military, other)?

Safeguards Standards 5: Cultural Heritage

Safeguards Risk Checklist Did the project involve or lead to:

5.1 activities adjacent to or within a Cultural Heritage site?

5.2 adverse impacts to sites, structures or objects with historical, cultural, artistic, traditional or religious values or to intangible forms of cultural heritage (e.g. knowledge, innovations, practices)?

5.3 utilization of Cultural Heritage for commercial or other purposes (e.g. use of objects, practices, traditional knowledge, tourism)?

5.4 alterations to landscapes and natural features with cultural significance?

5.5 significant land clearing, demolitions, excavations, flooding?

5.6 identification and protection of cultural heritage sites or intangible forms of cultural heritage?

Safeguards Standards 6: Displacement and Involuntary Resettlement

Safeguards Risk Checklist Did the project involve or lead to:

6.1 full or partial physical displacement or relocation of people (whether temporary or permanent)?

6.2 economic displacement (e.g. loss of assets or access to assets affecting for example crops, businesses, income generation sources)?

6.2 involuntary restrictions on land/water use that deny a community the use of resources to which they have traditional or recognizable use rights?

6.3 risk of forced evictions?

6.4 changes in land tenure arrangements, including communal and/or customary/traditional land tenure patterns (including temporary/permanent loss of land)?

Safeguards Standards 7: Indigenous Peoples

Safeguards Risk Checklist Did the project involve or lead to:

7.1 areas where indigenous peoples are present, or uncontacted or isolated indigenous peoples inhabit or where it is believed these peoples may inhabit?

7.2 activities located on lands and territories claimed by indigenous peoples?

7.3 impacts to the human rights of indigenous peoples or to the lands, territories and resources claimed by them?

7.4 the utilization and/or commercial development of natural resources on lands and territories claimed by indigenous peoples?

7.5 adverse effects on the development priorities, decision making mechanisms, and forms of self-government of indigenous peoples as defined by them?

7.6 risks to the traditional livelihoods, physical and cultural survival of indigenous peoples?

7.7 impacts on the Cultural Heritage of indigenous peoples, including through the commercialization or use of their traditional knowledge and practices?

Safeguards Standards 8: Labour and working conditions

Safeguards Risk Checklist Did the project involve or lead to:

8.1 working conditions that do not meet national labour laws or international commitments (e.g. ILO conventions)?

8.2 the use of forced labour and child labour?

8.3 occupational health and safety risks (including violence and harassment)?

8.4 the increase of local or regional unemployment ?

8.5 suppliers of goods and services who may have high risk of significant safety issues related to their own workers?

8.6 unequal working opportunities and conditions for women and men

# ANNEX VII: BRIEF CV OF THE EVALUATOR

| Names | Mr. Cliff Bernard Nuwakora |
| --- | --- |
| Profession | Development Policy, Monitoring & Evaluation, and Environmental Governance Consultant |
| Nationality | Ugandan |
| Country experience | - Uganda, Kenya, Tanzania, Rwanda, Ethiopia, South Sudan, Djibouti, Somalia, Zimbabwe, Ghana, Malawi, Botswana, Lesotho, Swaziland, Liberia, Sierra Leone, The Gambia, Namibia, Libya, Zambia, South Africa, Sao Tome and Principe, Nauru/Fiji, Papa New Guinea, Myanmar, Eretria, Iraq, |
| Education | - Post-Graduate Diploma in International Human Rights and Humanitarian Law, Raoul Wallenberg Institute, Lund University (Sweden) 2003–2004 - Master’s Degree in Policy Studies (Major: Environmental Policy), Fort Hare University/SARIPS (Southern Africa) 2001–2002 - Post-Graduate Diploma in Law and Gender, University of Zimbabwe (2000) - Master’s & Post-Graduate Diploma in Demography and Population Studies, Makerere University (1996–1997) - BA Social Sciences (Upper Second Class Honours), Makerere University (1991–1994) - Certificate in Project Planning and Management, Makerere University (1994) |

Short Biography

Mr. Cliff Bernard Nuwakora is an independent Development Policy and Monitoring & Evaluation Specialist with over 20 years of experience in programme design, governance, socio-economic assessment, and environmental policy evaluation across Africa, Asia, the Pacific and Europe. He has led numerous Mid-Term and Terminal Evaluations for UNDP, UNEP/GEF, EU, World Bank, SIDA and AfDB projects covering biodiversity, climate resilience, governance reform, and institutional capacity development. He is well-versed in UN evaluation standards, GEF Results Frameworks, and Participatory Monitoring and Evaluation tools.

Key specialties and capabilities include:

- Environmental and governance project evaluation (MTRs and TEs for GEF and UNDP projects)

- Policy analysis and institutional capacity assessment

- Rights-based and gender-responsive programming

- Development of Results-Based M&E Frameworks and Theories of Change

- Social impact assessment and safeguards monitoring

- Participatory approaches and multi-stakeholder coordination

- Climate adaptation, biodiversity governance and ABS system reviews

Selected Assignments and Experience

- UNEP/GEF Uganda (2025): Mid-Term Review of the Institutional Capacity Strengthening for Implementation of the Nagoya Protocol on Access to Genetic Resources and Benefit Sharing in Uganda (GEF ID 9481)- Team Leader.

- UNDP/GEF Uganda (2024): Terminal Evaluation of the Nationally Appropriate Mitigation Action for Integrated Waste Management and Biogas Production Project.

- UNDP/FAO Uganda: Terminal Evaluation of the project “Fostering Sustainability and Resilience for food security in Karamoja sub-region (FSURE project)”, in Uganda (UNDP PIMS ID 5577)

- UNDP/Austrian Development Cooperation ‘Restoration of Wetlands and Associated Catchments Project in Eastern Uganda’.

- UNDP/GEF/UNCDF ETHIOPIA: MTR OF THE PROJECT FOR PROMOTING SUSTAINABLE RURAL ENERGY TECHNOLOGY (RET) FOR HOUSEHOLD AND PRODUCTIVE USES IN ETHIOPIA

- UNDP-GEF Uganda): Terminal Evaluation (TE) of the UNDP implemented and GEF financed “Strengthening Institutional Capacity for Effective Implementation of Rio Conventions in Uganda) Project” (PIMS# 5643).

- UNDP/GEF Malawi: Terminal Evaluation (TE) of the Climate Proofing Local Development Gains in Rural and Urban Areas of Machinga and Mangochi Districts (PIMS #4508).

- UNDP/GEF Tanzania: Terminal evaluation of the Sustainable Forest Management of the Miombo Woodlands in Western Tanzania

- UNDP/GEF Namibia (2022): Evaluation of the Namibia Integrated Landscape Approach for Enhancing Livelihoods and Environmental Governance Project (NILALEG).

- UNDP Uganda (2023): Mid-Term Evaluation of the Restoration of Wetlands and Associated Catchments Project (Eastern Uganda).

- EU/UNDP Libya (2022): Final Evaluation of the Stability, Unity and Social Cohesion Project.

- UNDP South Africa (2021): Final Evaluation of the Development of a Social and Solidarity Economy Policy Project.

- Languages: English (Fluent), Swahili (Good), Runyakitara (Mother Tongue)

- Computer Skills: Fully computer literate (MS Office, SPSS, NVivo, Excel, online evaluation tools).

- Professional Affiliations: African Democracy Forum (ADF); Humanitarian Practice Network (UK); CIVICUS; MWENGO; IYEKA.

# ANNEX VIII: GEF PORTAL INPUTS (FOR GEF FUNDED PROJECTS)

The following table contains text to be uploaded to the GEF Portal, drawn from the Review Report.

Table 17: GEF portal inputs

Portal Entry: What is the performance at the project’s mid-point against Core Indicator Targets? (For projects approved prior to GEF-7, these indicators will be identified retrospectively and comments on performance provided)

Response: Source- Paras 69–72, Table 10 (Monitoring and Reporting section) and PIR 2025 Core Indicator data. Mid-term performance across all core indicators shows satisfactory progress. Core Indicator 1 (Area of landscapes under improved biodiversity management): ABS interventions are contributing to improved management across 170,316 ha spanning Kigezi and Karamoja sub-regions, including Echuya CFR and the Karamoja CFRs (Kadam, Moroto, Napak). Core Indicator 2 (People directly trained and reached): A total of 1,832 individuals has been trained directly (48% women), and over 285,000 people (150,250 men; 135,300 women) have been reached through national and community awareness activities. Core Indicator 3 (Institutional capacity strengthened): Seven national institutions (NEMA, UNCST, UWA, NFA, NARO/NaFORRI, URSB, Makerere University) now have strengthened ABS capacity, systems, and coordination mechanisms. Core Indicator 4 (Policies and frameworks adopted): The ABS Policy, Regulations, Guidelines, and Communication Strategy have been completed, validated, and submitted for Ministerial and Cabinet clearance; the electronic ABS permit and compliance systems are finalized and pending stakeholder validation. Overall mid-term performance = Satisfactory (S).

Portal Entry: What has been the progress, challenges and outcomes regarding engagement of stakeholders in the project/programme? (This should be based on the description included in the Stakeholder Engagement Plan or equivalent documentation submitted at CEO Endorsement/Approval)

Response: Source-Paras 76–77 (Stakeholder Participation and Cooperation). Stakeholder engagement has been robust and inclusive, with active participation from national agencies, research institutions, district authorities, and IPLC organizations such as UOBDU and KWCG. Engagement mechanisms, including six National Steering Committee meetings, multi-agency technical working sessions, and regional consultations in Kigezi and Karamoja have fostered strong ownership, policy coherence, and coordinated delivery across partners. IPLC participation has been particularly meaningful through community protocols, TK documentation, and benefit-sharing pilots that strengthened trust and local governance. Challenges mainly related to delayed reporting and staff turnover in institutions such as UNCST and NFA; however, these were addressed through harmonized reporting templates, targeted follow-up, and refresher orientation sessions. Overall, stakeholder engagement has significantly contributed to accelerated implementation, improved coordination, and strengthened community-level ABS outcomes.

Portal Entry: What has been the progress, challenges and outcomes regarding gender-responsive measures and any intermediate gender result areas? (This should be based on the documentation at CEO Endorsement/Approval, including gender-sensitive indicators contained in the project results framework or gender action plan or equivalent)

Response: Source-Paras 78–79 (Responsiveness to Human Rights and Gender Equality). Implementation is guided by the Gender and Social Inclusion Plan (2022), which has ensured systematic integration of gender-responsive actions across training, community engagement and policy processes. Women constitute 48% of all trained beneficiaries and 41% of Training of Trainer’s participants, while youth participation stands at approximately 20%, reflecting strong inclusion in ABS capacity building efforts. Gender focal points have been established within NEMA and UNCST, supporting coordination, mainstreaming of gender considerations, and application of gender responsive tools in field activities. Community pilots, particularly among Batwa and Karimojong groups have enabled women to participate in TK documentation, herbal product development and negotiation processes, contributing to enhanced confidence, leadership roles and livelihood opportunities for women and youth. Remaining gaps relate to limited sex, age, and disability disaggregated data in some reporting streams; these will be addressed in the remaining phase through strengthened monitoring, more detailed data capture, and application of inclusive reporting formats.

Portal Entry: - Provide an overall ESS risk classification to be entered into the portal as either Low, Medium/Moderate, or Hight/Substantial). Please reach out to UNEP Safeguards Advisor. - Provide updates on any revisions to identified types of risk classifications/ratings and describe progress made in the implementation of the management measures as outlined in the CEO Endorsement/Approval. Please make reference to any PIR-reported ESS risks. - Provide supporting documents

Response: Source- Annex VI (Safeguards Assessment Tool). Overall, ESS risk = Low to Moderate. No significant adverse impacts identified. Triggered standards: SS 1 (Biodiversity & Natural Resource Management), SS 4 (Community Health & Safety), SS 7 (Indigenous Peoples), SS 8 (Labour & Working Conditions). Risk management measures outlined at CEO Endorsement particularly the application of PIC and MAT processes, development of community protocols, strengthened benefit-sharing frameworks, and implementation of the Gender and Social Inclusion Plan have been fully integrated into ongoing field activities. Monitoring reports, safeguards checklists, and field supervision missions confirm no instances of non-compliance, and stakeholder consultations highlight strong community support, especially among IPLCs engaged in TK documentation and ABS pilot activities. No revisions to risk classifications have been required to date, and all mitigation actions remain effective and proportionate to the project’s risk profile. Supporting documents: Gender and Social Inclusion Plan (2022); Collaborative Forest Management (CFM) Agreements (2025); NEMA Safeguards Monitoring Forms and Field Supervision Reports.

Portal Entry: What has been the progress, challenges and outcomes regarding the implementation of the project's Knowledge Management Approach, including: Knowledge and Learning Deliverables (e.g. website/platform development); Knowledge Products/Events; Communication Strategy; Lessons Learned and Good Practice; Adaptive Management Actions. (This should be based on the documentation approved at CEO Endorsement/Approval)

Response: Source- Paras 84–85 (Communication and Public Awareness). Implementation of the project’s Knowledge Management (KM) approach has progressed well, with all major knowledge, learning, and communication deliverables operational. Key outputs include the ABS Awareness and Communication Strategy (2023), development and continuous updating of the national ABS online portal hosted by UNCST, and production of policy briefs, case studies, and training materials that document best practices and community experiences. Knowledge products have been disseminated through national and regional platforms, including presentations of project lessons at CBD COP-16 and learning exchanges with government agencies, academia, and IPLCs. Adaptive management has been supported by routine documentation of field lessons, integration of feedback from community consultations, and development of practical communication tools highlighted in Annex V. Challenges mainly relate to limited real time KM systems across partner institutions, though this has been mitigated through harmonized reporting templates and collaborative content development. Overall, KM implementation is assessed as Satisfactory (S), with clear contributions to awareness, policy dialogue, and replication of ABS practices.

Portal Entry: What are the main findings of the review?

Response: Source: Executive Summary (Paras 3–10) and Conclusions (Paras 6–7). The review finds that the project is firmly on track to achieve its objective of strengthening Uganda’s institutional and community capacity to implement the Nagoya Protocol. Key achievements include the validation of the ABS Policy, Regulations, and Guidelines, establishment and training of national ABS checkpoints, development and near completion of the national ABS electronic permit and compliance system, and successful operationalization of community-based ABS pilots in Karamoja and Kigezi demonstrating practical benefit-sharing models. Implementation efficiency, coordination among partner agencies, and stakeholder ownership are rated as strong, supported by high training uptake and integration of ABS into academic and district structures. Challenges have been relatively minor mainly procedural delays in approvals, disbursement timing, and earlier COVID-19 disruptions and have not significantly impeded progress. Overall, the project demonstrates clear momentum toward outcome achievement, with performance at mid-term assessed as Satisfactory (S).

Portal Entry: Actual Sources of Co-financing

Sources of Co-financing; Name of Co-financier; Type of Cofinancing; Investment mobilised; Amount ($). Recipient Country Government; National Environment Management Authority (NEMA); Grant; Investment mobilised; 375,000. Recipient Country Government; National Environment Management Authority (NEMA); In-kind; Recurrent expenditure; 1,167,500. Recipient Country Government; Uganda Wildlife Authority (UWA); Grant; Investment mobilised; 525,000. Recipient Country Government; Uganda Wildlife Authority (UWA); In-kind; Recurrent expenditure; 1,077,500. Recipient Country Government; National Forest Authority (NFA); Grant; Investment mobilised; 284,480. Recipient Country Government; National Forest Authority (NFA); In-kind; Recurrent expenditure; 400,214. Recipient Country Government; Plant Genetic Resources Centre (PGRC) - National Agricultural Research Organization (NARO); Grant; Investment mobilised; 146,264. Recipient Country Government; Plant Genetic Resources Centre (PGRC) - National Agricultural Research Organization (NARO); In-kind; Recurrent expenditure; 330,000. Recipient Country Government; Uganda National Council for Science and Technology (UNCST); Grant; Investment mobilised; 285,700. Recipient Country Government; Uganda National Council for Science and Technology (UNCST); In-kind; Recurrent expenditure; 693,720. Recipient Country Government; National Forestry Resources Research Institute - National Agricultural Research Organization (NaFORRI-NARO); Grant; Investment mobilised; 145,000. Recipient Country Government; National Forestry Resources Research Institute - National Agricultural Research Organization (NaFORRI-NARO); In-kind; Recurrent expenditure; 600,000. Recipient Country Government; National Chemotherapeutic Research Institute (NCRI); Grant; Investment mobilised; 134,000. Recipient Country Government; National Chemotherapeutic Research Institute (NCRI); In-kind; Recurrent expenditure; 475,000. Recipient Country Government; Makerere University; Grant; Investment mobilised; 55,000. Recipient Country Government; Makerere University; In-kind; Recurrent expenditure; 410,000. Beneficiary; Karamoja Women Cultural Group; Grant; Investment mobilised; 10,000. Beneficiary; Karamoja Women Cultural Group; In-kind; Recurrent expenditure; 90,000. Beneficiary; United Organization for Batwa Development in Uganda; Grant; Investment mobilised; 10,000. Beneficiary; United Organization for Batwa Development in Uganda; In-kind; Recurrent expenditure; 205,000. TOTAL; 7,419,378.

Portal Entry: Key Risks (please refer to ANNEX XI)

# ANNEX IX: GEF RISKS TO ACHIEVING PROJECT OUTCOMES

| RISK CATEGORIES | RATING | ASSESSMENT AND MITIGATION MEASURES |
| --- | --- | --- |
| CONTEXT |  |  |
| Climate | Low (L) | Project activities (policy reform, capacity-building, digital systems) have negligible direct climate exposure. Field sites (Kigezi & Karamoja) face periodic drought and soil degradation, but no infrastructure or high emission activities were introduced. Mitigation: integrate climate-resilient livelihood measures and ecosystem restoration into community ABS pilots. |
| Environmental and Social | Low (L) | Consistent with Safeguards rating (Annex VI). No adverse E&S effects recorded. Mitigation: continued monitoring through NEMA’s safeguards checklist, PIC/MAT procedures, and community feedback mechanisms. |
| Political and Governance | Moderate (M) | Although national ownership is strong particularly from NEMA and MWE the approval of the ABS Policy and Regulations depends on political processes outside the project’s direct control. Cabinet reshuffles, competing legislative priorities, and lengthier than expected policy approval cycles introduce real, but manageable, risks of delay. These factors justify a Moderate rating, as they may affect the timing of regulatory adoption but do not threaten overall achievement of results. Mitigation: Sustained high-level policy engagement, regular NPSC oversight, and continued UNEP follow-up with MWE and the Attorney General’s Chambers. |
| INNOVATION |  |  |
| Institutional and Policy | Moderate (M) | Inter-agency coordination improving but uneven across sectors. Mitigation: Strengthen coordination through regular NPSC and technical working group meetings (Rec #3), provide targeted capacity building to institutions with weaker ABS readiness, and finalize and disseminate institutional ABS guidelines and SOPs to clarify roles and ensure consistent implementation across agencies. |
| Technological | Moderate (M) | The e-Permit and Compliance System is in advanced development; risk of limited local IT capacity or post-project maintenance gaps. Mitigation: embed UNCST ICT support unit and allocate recurrent funds for system maintenance (Rec #2). |
| Financial and Business Model | Moderate (M) | GEF disbursement apprx. 72%; co-financing on track. However, sustainability depends on domestic budget integration. Mitigation: mainstream ABS funding into GoU recurrent budgets and explore BIOFIN/GEF-7 leverage (Rec #2, #7). |
| EXECUTION |  |  |
| Capacity for Implementation | Moderate (M) | Technical capacity strong at national level but limited at district/IPLC levels. There was also late PMU staffing and multi-partner load. Mitigation: All positions were filled and harmonized templates adopted, so continued targeted sub-national training and mentorship is required (Rec #5). |
| Fiduciary | Low (L) | Financial systems are functional, with generally timely reporting and no audit qualifications. Delays occurred at project start due to the time required for NEMA and UNCST to meet cash-advance accountability requirements before subsequent disbursements could be processed. Mitigation: maintain quarterly financial reviews and use unified and stricter reporting cadence and template introduced 2024. |
| Stakeholder | Low (L) | Broad engagement with IPLCs and agencies; no conflict reported. Mitigation: sustain inclusive participation, gender balance (≥ 50 % women), and transparent benefit sharing processes. |
| Other (External Dependencies) | Moderate (M) | Project progress depends partly on external processes such as national legal reform timelines and staff turnover within partner institutions, which the project cannot fully control. Mitigation: Use adaptive management by updating annual workplans to reflect external delays, maintain close follow-up through UNEP supervision missions, and provide timely technical support to partners when staffing or leadership changes occur. |
| Overall Risk Rating | Low (L) | The overall project risk is assessed as Low. Although some external factors such as policy approval timelines and varying institutional capacities require continued monitoring, existing mitigation measures (regular NPSC oversight, UNEP supervision, and strengthened coordination mechanisms) have effectively reduced residual risk. None of the identified risks pose a threat to the achievement of project outcomes, and the remaining risks are manageable within the current implementation arrangements. |

# ANNEX X: IMPLEMENTATION PLAN OF RECOMMENDATIONS

| Project Title and Reference No.: |  | Institutional Capacity Strengthening for Implementation of the Nagoya Protocol on Access to Genetic Resources and Benefit Sharing in Uganda (GEF ID 9481) |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Contact Person (TM/PM): |  | UNEP Task Manager (Biodiversity and Land Branch) NEMA Project Manager (ABS National Focal Point) |  |  |  |
| Recommendations | Accepted (Yes/No/Partially) |  | What Will Be Done? | Expected Completion Date | Responsible Officer / Unit / Division / Agency |
| - Finalize and gazette the National ABS Policy and Regulations, and establish an operational roadmap for implementation. | Yes |  | Fast-track Cabinet approval through the Ministry of Water and Environment (MWE); complete gazettement and launch official implementation roadmap including institutional roles and compliance mechanisms. | Q2 2026 | MWE / NEMA / Attorney General’s Chambers / UNEP |
| - Operationalize and sustain the National e-Permit and Compliance Management System. | Yes |  | Finalize software testing and user training; link UNCST, UWA, NFA, URSB and Customs checkpoints; integrate maintenance budget into GoU ICT framework. | Q3 2026 (roll-out) Maintenance from FY 2026/27 | UNCST / NEMA / MoFPED / UWA / NFA / URSB |
| - Institutionalize a National ABS Coordination and Monitoring Framework. | Yes |  | Establish a National ABS Committee via ministerial directive; develop a joint Monitoring, Evaluation and Learning (MEL) Framework; conduct quarterly review meetings. | Committee by Q1 2026; MEL Framework by Mid-2026 | NEMA (PMU) / MWE / UNCST / UWA / NFA / NARO / UOBDU / KWCG |
| - Enhance gender, youth and IPLC participation in ABS implementation and benefit sharing. | Yes |  | Expand gender-responsive training and youth leadership initiatives in ABS pilots; target ≥ 50 % female representation and inclusion of PWDs in decision-making processes. | 2025–2026 (ongoing; review at TE 2026) | NEMA / UOBDU / KWCG / DLGs / UNCST Gender Focal Points |
| - Strengthen sub-national awareness and capacity building for community-level ABS implementation. | Yes |  | Conduct district orientation workshops for environment officers, cultural leaders and CFM groups; develop localized guidelines and training toolkits. | 2025–2026 (Ongoing) | NEMA / UOBDU / KWCG / District Local Governments |
| - Strengthen communication, visibility and knowledge management for ABS in Uganda. | Yes |  | Finalize and implement a National ABS Communication and Visibility Strategy; publish policy briefs and case studies; update ABS Clearing-House regularly. | Strategy by Q4 2025; Implementation through 2026 | NEMA / UNCST / MWE / UWA / NFA / UNEP Comms Unit |

# ANNEX XI: QUALITY ASSESSMENT OF THE EVALUATION REPORT

# ANNEX XII: SELECTED PHOTOS FOR ABS MTR REPORTING

SMA refers to the ID provided by the Integrated Planning, Management and Reporting Solution (IPMR) system, which was introduced by UNEP in July 2023. Previously, it was referred to as a PIMS ID number.

For example, ID references from EC, IKI, UNDA, Adaptation Fund, GCF.

Where applicable, list countries who have provided project funds and/or co-finance.

Indicate where funding institutions are any/all of the following: Foundation/NGO; Private Sector; UN Body; Multilateral Fund; Environment Fund; Other.

For these items do not include full text; only enter the number or reference.

Expected/planned dates are listed in the Project Document (ProDoc).

Actual start date is the date of project approval by the Division Director.

Total budget may include: Regular Budget, Environment Fund, Extra-Budgetary, including ‘softly-earmarked’ etc.

Extra-budgetary funds may include co-finance (cash/in-kind).

From last project/budget revision.

UNEP projects of four or more years duration require an MTR unless there is an exceptional circumstance. See the Evaluation in the Project Cycle section in the Evaluation Office’s operational manual. Donor requirements may vary and should be considered in conjunction with UNEP’s requirements.

This does not apply to Enabling Activities