Kenya

The Upper Tana Nairobi Water Fund (UTNWF) Project

GEF Terminal Evaluation Report (TER)

FINAL REPORT

Mission Dates: 		4th -11th May 2022

Document Date: 		18 August 2022

Project No: 			Insert number

Report No: 			Insert number

East and Southern Africa Division Programme Management Department

East and Southern Africa Division

Table of Contents

Tables	4

Figures	4

Abbreviations and Acronyms	5

Project Identification and Financial Data	7

Map of the Project Area	8

Executive Summary	9

1. introduction	13

1.1	PURPOSE OF THE EVALUATION	13

1.2 METHODOLOGY	13

2. Project Description and country context	13

2.1 BACKGROUND	13

PROJECT START, DURATION AND FINANCING	13

2.3 PROJECT CONTEXT	14

3. Project Results	15

3.1 RELEVANCE	15

3.2 PROJECT EFFICIENCY	19

3.3 PROJECT EFFECTIVENESS	20

3.4 SUSTAINABILITY	25

3.5 PROGRESS TO IMPACTS	26

4. Assessment of monitoring and evaluation system	28

3.5 Monitoring and Evaluation Design	28

3.6 Monitoring and Evaluation Implementation	28

5. Assessment of implementation and execution	29

5.1 Quality of Project Implementation	29

5.2 Quality of Project Execution	30

6. Other assessments	30

6.1 Targeting and Outreach	30

6.2 Innovation	31

6.3 Potential for Scaling-Up	32

6.4 Environmental and Social Safeguards	32

6.5 Knowledge Management	33

6.6 Gender Concerns	33

7. Conclusions	34

8. Recommendations	36

Annex 1: terminal evaluation itinerary	37

Annex 2 – project logical framework	40

Annex 3 – rating of the utnwf project results	43

Annex 4. Water Funds sites and status across the African continent.	45

Annex 5. Bibliography	46

Annex 6. terms of reference	48

# Tables

Table 1: Co-financing by stakeholders in US$	18

Table 2: Contributions by Counties (2018-2021) in US$	19

Table 3: Changes in Household Assets amongst beneficiary households	25

# Figures

Figure 1: The UTNWF Theory of Change	17

Figure 2: GEF Cumulative Disbursements (USD) up to 31st December 2021	18

Figure 3: Achievements against key output indicators at household levels	21

Figure 4: The cumulative outreach of farmers by year	29

Figure 5: Gender outreach over the project cycle	29

# Abbreviations and Acronyms

| ASALs | Arid and Semi-Arid Lands |
| --- | --- |
| ASTGS | Agricultural Sector Transformation and Growth Strategy |
| AWPB | Annual Work Plan Budget |
| BCG | Biological Conditions Gradient |
| BoM | Board of Management |
| BoT | Board of Trustees |
| CAC | Counties Advisory Committee |
| CASCOM | County Agriculture Sector Steering Committee |
| CIDPs | County Integrated Development Plans |
| COSOP | Country Strategic Opportunities Programme |
| DID | Difference in Difference |
| EX-ACT | Ex-ante carbon balance tool |
| FSIAP | Food Security Integrated Approach Pilot |
| GDP | Gross Domestic Product |
| GEB | Global Environmental Benefits |
| GEF | Global Environment Facility |
| GHG | Green House Gas |
| IAP | Food Security for Sub Saharan Africa |
| ICRAF | World Agroforestry Centre |
| IFAD | International Fund for Agricultural Development |
| INRM | Integrated Natural Resource Management |
| JKUAT | Jomo Kenyatta University of Agriculture and Technology |
| KCEP-CRAL | Kenya Cereal Enhancement Programme-Climate Resilient Agricultural Livelihoods |
| KFS | Kenya Forest Service |
| KM | Knowledge Management |
| LDSF | Land Degradation Surveillance Frameworks |
| M&E | Monitoring and Evaluation |
| MKEPP | Mount Kenya East Pilot Project for Natural Resource Management |
| MoEF | Ministry of Environment and Forestry |
| MOUs | Memorandum of Understandings |
| MPAT | Multidimensional Poverty Assessment Tool |
| MTR | Mid Term Review |
| NCWSC | Nairobi City Water and Sewerage Company |
| NEMA | National Environment Management Authority |
| NMK | National Museums of Kenya |
| PDR | Project Design Report |
| PPP | Public Private Partnerships |
| PSC | Project Steering Committee |
| SECAP | Social environmental and Climate Assessment Procedures |
| SLM | Sustainable Land Management |
| SMS | Short Message Service |
| TNC | The Nature Conservancy |
| TSS | Total Suspended Solids |
| UTaNRMP | Upper Tana Catchment Natural Resource Management Project |
| UTNWF | Upper Tana- Nairobi Water Fund |
| WF | Water Fund |
| WRA | Water Resources Authority |
| WRMA | Water Resources Management Authority |
| WRUAs | Water Resources User Associations |
| WWF | World Wildlife Fund |

# Project Identification and Financial Data

| Project and Terminal Evaluation Data |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| GEF Project ID |  | 9139 |  |  |  |
| GEF Agency project ID |  | 9070 |  |  |  |
| IFAD Grant Agreement |  | 2000001524 |  |  |  |
| Project Name |  | The Upper Tana Nairobi Water Fund (UTNWF) Project |  |  |  |
| Country |  | Kenya |  |  |  |
| Region |  | East and Southern Africa |  |  |  |
| Implementing Agency/Agencies |  | International Fund for Agricultural Development (IFAD) |  |  |  |
| Executing Agency/Agencies |  | The Nature Conservancy (TNC) |  |  |  |
| Focal Area |  | Multi Focal Area |  |  |  |
| GEF Strategy / Operational Program |  | Food Security for Sub Saharan Africa (IAP) |  |  |  |
| GEF Approval date |  | 20th July 2016 |  |  |  |
| IFAD Approval date |  | 6th October 2016 |  |  |  |
| Date of project start /effectiveness |  | 6th October 2016 |  |  |  |
| Grant start up (launched) |  | 17th January 2017 |  |  |  |
| Estimated closing date |  | 30th June 2022 |  |  |  |
| Actual Date of completion |  |  |  |  |  |
| Project Financing |  |  |  |  |  |
|  |  | At endorsement (US $) |  | At completion (US $) |  |
| GEF Project Grant | GEF funding | 7 201 835,00 |  | 7 201 835,00 |  |
|  | Co-financing | 162 745 769 |  | 162 745 769 |  |
| Co-financing | Co-financer type | In-kind | Cash | In-kind | Cash |
|  | Counties & Partners |  | 16 777 212,14 | - | 282 195,00 |
|  | Farmers | 1 284 908,36 | 142 769,36 | 1 284 908,36 | 142 769,36 |
|  | TNC |  | 4 485 693,61 |  | 4 485 693,61 |
| Total GEF funding |  | 7 201 835,00 |  | 7 201 835,00 |  |
| Total Co-financing |  | 162 745 769 [cash] |  | 162 745 769 [cash] 1 284 908,36 [in-kind] |  |
| Total project funding |  | 7 201 835,00 |  | 7 201 835,00 |  |
| Terminal Evaluation/Review Information |  |  |  |  |  |
| TE completion date |  |  |  |  |  |
| TE submission date |  |  |  |  |  |
| Author of TE |  | Sithabiso Gandure, International Consultant for IFAD |  |  |  |
| TER completion date |  |  |  |  |  |
| TER prepared by |  |  |  |  |  |
| TER peer review (if GEF |  |  |  |  |  |

# Map of the Project Area

# Executive Summary

- The main purpose of the terminal evaluation was to assess and report on the extent to which the project met its goal, development objectives and results as anticipated at design, and how the achievements/best practices and lessons learned can inform future programming of similar projects.

- The evaluation used a mixed methods approach of quantitative and qualitative tools to form an informed judgement on overall project performance and results. The terminal evaluation consisted of in-depth analysis of the existing project documentation. Discussions with various stakeholders (beneficiaries; national and county government partners; research/academia, private sector) were conducted on all the activities implemented by the project. Field visits combined with direct observations were conducted in the three of the four counties that the project is implemented: Sagana-Gura sub watershed;  Murang’a - Maragua sub watershed and Murang’a -Thika-Chania sub watershed.  Key informant interviews and focus group discussions were also conducted with the project team, implementing partners, International Fund for Agricultural Development (IFAD), Ministry of Environment and Forestry (MoEF), The Nature Conservancy (TNC) and key stakeholders.

- The Upper Tana Nairobi Water Fund (UTNWF) project design was robust and comprehensive, with clear objectives that are relevant to the mandate of the MoEF. The design built on a strong foundation of a business case for the establishment of the Water Fund (WF) for Nairobi conducted by TNC and its partners between 2012 and 2015. Lessons learned from relevant IFAD-funded projects on agriculture and natural resources management, ecosystem restoration and related activities in the Upper Tana catchment also provided detailed contextual information and technical inputs into the UTNWF project.

- The project addresses the key government priorities in the constitution and the Public Private Partnerships  (PPP) Act, 2013. By implementing riparian management and wetlands protection for vegetation buffering along riverbanks; reafforestation and adoption of agroforestry practices; terracing of hill slopes on steep farmland and support for village nurseries, the project is in line with key national policies. The Water Fund Project is strategically aligned with and highly relevant to the Kenyan government’s objective of conserving water towers (i.e., watersheds) that are critical to the economic well-being of the country and essential to the livelihoods of millions of farmers and citizens. The project is in line with key policy outcomes found in the National Environment Policy (2013), National Policy for the Sustainable Development of Northern Kenya and other Arid Lands (2012), Forest Policy (2014), National Land Policy (2009), Biodiversity Regulations (2006) and the Tana Catchment Management Strategy (2014-2022) which seeks to manage, regulate, protect and equitably allocate water resources. The project remains relevant with the Agricultural Sector Transformation and Growth Strategy (ASTGS) 2019-2029 that supports commercialization of smallholder agriculture.

- UTNWF objectives were largely relevant to the needs of the rural poor and address challenges of low agricultural production caused by water shortages, soil erosion, soil degradation and climate change. At design, particular attention was paid to targeting of youth and also creation of youth employment opportunities (e.g. in biophysical conservation measures, nurseries etc.) or improving women’s and youth representation and decision making in local institutions. Overall, the project performed well as about 8% of the targeted watershed groups were youth. Going forward, more targeted support towards youth would be required to address their underlying constraints concerning access to predictable and sustainable markets (including export markets), access to land and greater linkages with the private sector.

- At the Global Environment Facility (GEF) level, UTNWF contributes to the overall objective of the GEF Food Security Integrated Approach Pilot (FSIAP), to support countries in target geographies for integrating priorities to safeguard and maintain ecosystem services into investments improving smallholder agriculture and food value chains.  The UTNWF was strongly aligned to IFAD’s third Country Strategic Opportunities Programme (COSOP) 2013-2018 which focused on agricultural intensification, value addition, market access and sustainable natural resource management.

- The financial performance of the project is considered highly satisfactory and there is a broad consensus that the project was cost effective. The UTNWF project had an overall financing of 33.6M USD of which a) 7.2M USD grant was from the GEF-IAP; b) USD 3M in-kind contribution by TNC to support administrative/project management costs; c) USD 1.5M as in-kind contribution from project beneficiaries (mostly labour and building material for rainwater harvesting and fixed dome biogas systems); d) USD 11.9 M as in-kind contribution from local NGOs and county governments; e) USD 10M private sector pledges towards capitalisation of the Water Fund.

- The Water Fund is now registered as a charitable trust and fully operational with a Board of Trustees (BoT), Board of Management (BoM), Counties Advisory Committee (CAC), and staff. The BOTs’ role is to manage the overall operations of the WF, establish a Board of Management (BOM), an advisory committee at the county level, and a Technical Secretariat, responsible for the day-to-day management of its activities. At the time of project completion, the target for the Endowment fund had not been achieved. The assumption made at design that the funding would come from the private sector did not fully materialize. Mobilizing contributions from the private sector had not been as successful as originally planned. The design should have included other sources of funding from the public sector and counties.

- Efforts to mobilise resources for the Trust activities and the Endowment Fund have been intensified supported by a dedicated staff from TNC. While there is a strong commitment to continuously engage with the private sector, there are opportunities for intensive engagements with the government through the Ministry of Environment and Forestry as recommended in the previous IFAD mission. Discussions with national and county government partners indicate their readiness in working with the Water Fund and in support of fundraising initiatives and other legal routes towards capitalisation of the endowment fund.

- The project developed Memorandum of Understandings (MOUs) with county and national government agencies as well as the private sector to strengthen the institution as a public-private partnership for a collective implementation and coordinated conservation interventions across the watershed. The project successfully implemented diverse interventions that promote climate-resilient agricultural production systems, agroforestry, wetlands protection and restoration, protection/conservation of riparian zones, biogas generation and other cash crop interventions such as avocado production.

- The Area (ha) influenced to adopt Sustainable Land Management (SLM) had a significant but limited achievement which stood at 35% at completion. The endline survey noted that for example, some riparian conservation activities such as creation of buffer zones between the edge of the water course and the cultivated area had slow adoption. The project tried to provide incentives to arrest this encroachment through upland arrow roots, water harvesting, subsidies etc. The findings at endline show that there is some encroachment despite all the sensitization and training on the need for buffer zones. Apart from individual farmer interest and motivation, the small average land sizes constrain some farmers from adopting the conservation practice.

- There were significant improvements in water quantity observed. According to the endline survey, a total of 93% of households in the treated watersheds had adequate water for 6 - 12 months of the year, slightly higher than 84% for the baseline

- The project registered notable environmental as well as socio-economic outcomes. Reducing Greenhouse Gas (GHG) emissions and increasing carbon sequestration in the project area is a cross-cutting aim and co-benefit of activities that were carried out as part of SLM, riparian management, and by providing training and capacity development for nursery management and diversified crop production, improved Agroforestry management through (fruit) tree planting campaigns and supply of planting materials.

- The project achieved the targets of successfully integrating the Global Environmental Benefits (GEB) monitoring tools and protocols with partner institutions by establishing/completing Land Degradation Surveillance Frameworks (LDSF) for at least 5 sub-watersheds. In addition, a total of 33 biophysical monitoring stations (against a target of 28) have been developed/upgraded and are operational. Further, a water-quality database was established and integrated into Water Resources Authority (WRA) system and is accessible to stakeholders who use the data to develop knowledge products for sharing.

- A project end-line Multidimensional Poverty Assessment Tool (MPAT) and outcome surveys were successfully completed. Results show an improvement in the community livelihoods by 6% and improved nutrition, food production, and biodiversity in the project area. Two DHIS2 databases were established: one for socio-economic data and the second for hydrometeorological data. However, MPAT survey results are yet to be referenced in county development plans, as means for informing policy decisions on climate change adaptation and resilience building. CIDPs are developed on a five year cycle and therefore this can only be done after the elections this august, possibly be next year they will develop the plans. The MPAT was done mid-stream project implementation and therefore the WF would be the one to try and propel this at county level next year.

- In relation to robust knowledge management and learning systems; the project has improved the measurement of water quality and quantity through upgrading of water monitoring stations. The status of land degradation was established through Land Degradation Surveillance Framework (LDSF) mapping; establishment of Water Resources Authority (WRA) water quality database. The project has been active in sharing of information, lessons learned best practices, and in raising awareness of the water fund model at national, regional, and international levels. Through sharing of lessons learned, scaling up to two other WFs in Eldoret and Mombasa was achieved.

- One area that could have been strengthened is the link between component 1 and 3 in terms of ensuring data/knowledge generated had greater policy influence impact especially the capitalisation of the endowment fund. The project generated various lessons but did not systematically consolidate and document these lessons in a balanced way under each component in terms of what worked and what did not.

- The project had a good overall sustainability strategy at the water fund level. The sustainability strategy is expected to be the autonomous Nairobi water fund which is now operational and fully staffed and will continue with farm and community-based interventions. At county level, this sustainability is expected to be boosted by the fact that counties are still represented in the county advisory unit of the Nairobi water fund. Most of the interventions are also funded at county level through county budgets, evidenced by the high levels of co-financing provided by counties. The project developed memorandum of understandings (MOUs) and joint plans with clear annual workplan and budgets with each county. These agreements however did not provide a clear exit strategy on how the counties will support these interventions after the lapse of the MoUs. The project has seamlessly transitioned into a long-term programme with Water Fund Trust and its stakeholders e.g., Counties, WRA, KWS, KFS etc continuing as partners into the long-term. There are, however, still challenges around market linkages, commercialization of some enterprises such as avocadoes as well as value addition that will need to be supported.

- The project had a robust and detailed high-quality monitoring and evaluation plan for the UTNWF. Monitoring and Evaluation (M&E) approaches follow a  theory  of  change. The M&E activities conducted have been found to be in line with the M&E plan. The project‘s data  quality  has  improved  in  terms  of  accuracy  and  adequacy. A strongly digital and real time M&E approach was adopted and implemented through various digital platforms such as Power Bi, Telemetric data, LDSF, conservation SMS platform, DHIS2 etc.

- The project design document has clearly defined implementation arrangements at national and county levels including the private sector partnership. TNC, the BoT and BoM consists of a comprehensive technical skills set which aids in providing sound leadership and guidance regarding the policy, financial, legal and technical aspects of the project. These governance structures consist of individuals who are dedicated and passionate about the Water Fund and the project’s deliverables. The project’s sound implementation arrangements contributed to the greater achievement of results reported under effectiveness.

- The  project  had a strong relationship with the  county governments of Murang’a, Nyeri, Nyandarua and Laikipia. The county governments provided substantial co-financing to the project.  Technology partners and  technical  government  agencies  such  as  National Museums of Kenya (NMK),  Jomo Kenyatta University of Agriculture and Technology (JKUAT),  World Agroforestry Centre (ICRAF), Water Resources Authority (WRA),  Kenya Forest Service (KFS) etc.  were instrumental  in  providing  technical  guidance  and  strengthening  the  delivery  of  the project. However, it has been difficult to assess objectively the effectiveness of the various partnerships with a view to determine what worked well and lessons that can be learnt and taken up by the Water Fund Trust because they also play an oversight role under the BoM, thereby presenting conflict of interest issues even if it is one person particularly if there are no mechanisms in place on how to manage this.

- The ratings of the project are summarized below:

| Criteria | Rating |
| --- | --- |
| Relevance | HS |
| Efficiency | HS |
| Effectiveness | S |
| Sustainability - Financial sustainability - Socio-political sustainability - Institutional and governance sustainability - Environmental sustainability | ML L L L |
| Monitoring and Evaluation Design | HS |
| Monitoring and Evaluation Implementation | HS |
| Quality of project implementation | S |
| Quality of project execution | S |

# 1. introduction

## PURPOSE OF THE EVALUATION

- The terminal evaluation for the Upper Tana Nairobi Water Fund Project (UTNWF) was commissioned jointly by the International Fund for Agricultural Development (IFAD), Ministry of Environment and Forestry (MoEF) and The Nature Conservancy (TNC). The main purpose of the terminal evaluation is to assess and report on the extent to which the project has met its goal, development objectives and results as anticipated at design, and how the achievements/best practices and lessons learned can inform future programming of similar projects. The process will also help define an appropriate hand-over or post-project strategy to the project and relevant stakeholders.

## 1.2 METHODOLOGY

- This terminal evaluation is guided by the methodological framework set out in IFAD’s Project Completion Review Guidelines as well as the Global Environmental Fund (GEF) terminal evaluation guidelines. The evaluation used a mixed methods approach of quantitative and qualitative tools to form an informed judgement on overall project performance and results. The terminal evaluation consisted of the following methods:

  - In-depth analysis of the existing project documentation: Primary sources of information included project reports and documents such as supervision reports, Mid Term Review (MTR) report, progress reports, Annual Work Plan Budget (AWPB), financial statements, monitoring and evaluation data and specific studies and surveys.

  - Feld visits and discussions with various stakeholders (beneficiaries; national and county government partners; research/academia, private sector) on all the activities implemented by the project. Field visits combined with direct observations were conducted in the three of the four counties that the project is implemented: Sagana-Gura sub watershed;  Murang’a - Maragua sub watershed and Murang’a -Thika-Chania sub watershed.  These sites were visited to collect perspectives of beneficiaries and stakeholders on the performance of UTNWF project. Discussions were held with women, men and youth farmers, agriculture extension officers, project field officers, county partners and service providers.

  - Key informant interviews and focus group discussions were also conducted with the project team, implementing partners, IFAD, MoEF, TNC and key stakeholders.

- The terminal evaluation mission programme is found in Annex 1.

# 2. Project Description and country context

## 2.1 BACKGROUND

- The Upper Tana Nairobi Water Fund Project (UTNWF) is a 5-year Public-Private Partnership (PPP) funded by the Global Environment Facility (GEF) through IFAD as the GEF Implementing Agency and executed by The Nature Conservancy (TNC). The project is being implemented in four Counties of Murang’a, Nyeri, Laikipia and Nyandarua that drain two critical water towers – Aberdares and Mount Kenya. The Upper Tana watershed covers 17,000 km2 with a population of about 5.3 million inhabitants. The Upper Tana catchments supply the bulk of the water used in Nairobi through the Sasumua and Ndakaini dams, which draw their water from the Chania and Thika rivers, respectively.

- The goal of the UTNWF project is to “increase investment flows for sustainable land management and integrated natural resource management in the Upper Tana catchment.” The project targeted 21,000 smallholder farmers, and was implemented through four components, namely: a) Water Fund management platform institutionalized; b) Improved Upper Tana catchment ecosystems that support livelihoods, food security, and economic development; c) Robust knowledge management and learning systems implemented to direct UTNWF management and share lessons both nationally and regionally; and d) Project management.

## PROJECT START, DURATION AND FINANCING

- The  project became effective in October 2016 with an overall financing of 33.6M USD of which a)7.2M USD was a grant from  the GEF-IAP; b)3M USD an in-kind contribution by TNC to support   administrative/project management costs; c)1.5M USD as in-kind contribution from project beneficiaries; d)11.9 M USD as in-kind  contribution  from  local  NGOs  and  county  governments; and e)10M USD private sector pledges towards capitalisation of the Water Fund. The project's completion date is 31st December 2021 and the grant closing date is 30th June 2022.

## 2.3 PROJECT CONTEXT

- Kenya covers a total area of 582,646 km2, of which 1.9% or 11,230 km2 is water bodies. Of the remaining 571,416 km2 landmass, some 490,000 km2 (or 84% of total land mass) comprises arid and semi-arid lands (ASALs) which are characterised by low, erratic rainfall, high evapotranspiration rates, poor soil fertility and few water resources. The remaining 16% of Kenya’s landmass is of high and medium agricultural potential with adequate and reliable rainfall. Administratively, Kenya is divided into 47 Counties, in a devolved system of Government introduced under the new constitution, in which certain functions of the national government were transferred to the 47 counties.

- Kenya’s economy has made remarkable recovery from the worst economic effects of the COVID-19 pandemic. Real Gross Domestic Product (GDP) increased by 7.5% in 2021, higher than the estimated growth in Sub-Saharan Africa of 4%. This growth was driven by the recovery of the services sector and expansion in industrial output. Looking ahead, economic growth is expected to moderate in 2022 with real GDP projected to grow by 5.5% in 2022 and 5.2% on average in 2023–24. A key risk to the outlook is a further worsening of the current drought, which is having a devastating effect on food security and livelihoods in affected parts of the country and is necessitating increased social spending on food assistance.

- Agriculture is a key contributor to Kenya’s economy. By contrast, the agriculture sector’s output contracted by 0.2% in 2021, affected by drought conditions in the arid and semi-arid lands (ASAL). The Vision 2030 launched in 2008 placed agriculture at the forefront of efforts to realize an annual economic growth rate of 10% and focused on the Big 4 Agenda. One of the pillars of the Big 4 Agenda of the government, aims to achieve 100% food security for Kenyans through enhanced large scale food production, increased smallholder productivity, and reduction of the cost of food to improve accessibility to all. The agriculture sector in Kenya faces significant challenges including an over-reliance on rainfall; poor utilization of agricultural land; underfunding of the sector; high cost of production; declining fish production due to unsustainable use of water resources rich in fish; inadequate marketing facilities; and limited value addition witnessed in the export of low-value crops amongst others.

- It is estimated that natural resources contribute about 42% of the country's GDP and support about 70% of the country's population's livelihoods. Nonetheless, the natural assets face significant conservation challenges. Forests comprise the country’s water towers and catchments, where over 75% of the country's renewable surface water originate, and therefore, are important for human livelihoods, irrigated agriculture, and hydro-power generation. Generally, the expansion of agriculture, rapid urbanisation, growing demand for timber and charcoal trade and the destruction of the rich biodiversity by human encroachment threatens these forest ecosystems. The Vision 2030 proposes to increase forest cover in the country from 2% in 2010 to 10% coverage under a protected area system.

- Kenya has been classified as a water-scarce country with water resources reportedly declining. The country forest cover remains below the constitutional threshold of 10% tree cover while land degradation is widespread. Kenya’s environmental problems lies at the nexus of population growth, inequality, and high dependence on natural resource–based incomes.

- Climate change is accelerating the impact of existing vulnerabilities to environmental shocks such as flood and droughts. The shocks have continued to threaten agriculture and food production directly through changes in agro-ecological conditions and indirectly. It takes adaptation and mitigation efforts in all key sectors including livelihood diversification, development of human capital, water resources conservation and development, climate-proofed infrastructural development (roads and energy), afforestation and reforestation, and climate-resilient agricultural systems, among others to address these challenges.

# 3. Project Results

## 3.1 RELEVANCE

| Relevance: Were the project outcomes congruent with the GEF focal areas and operational program strategies, country priorities and mandates of the Agencies? Was the project design appropriate for delivering expected outcomes? | Rating: HS |
| --- | --- |

3.1.1 Project Objectives

- The goal of the Project was to increase investment flows for sustainable land management (SLM) and integrated natural resource management (INRM) in the Upper Tana catchment. The development objective of the water fund is to:

- achieve a well-conserved upper Tana River basin with improved water quality and quantity for downstream users (public and private)

- maintain regular flows of water throughout the year

- enhance ecosystem services for food security, freshwater, and terrestrial biodiversity

- improve human well-being and quality of life for upstream communities.

- The project aimed at working with at least 21,000 smallholder households in the three sub-catchments, i.e., about 100,000 individuals as direct beneficiaries, with cascade effects on the total population of 5.3 million inhabitants in the Upper Tana catchment (the logical framework for the UTNWF project is found in Annex 2). The project would achieve its goal through three interrelated components:

- Component 1: Water Fund Management Platform institutionalised. The project was to work closely with private and public partner organisations to establish the Water Fund (WF) as a Charitable Trust registered under Kenyan law and governed by a Board of Trustees. The Board of Trustees were to manage the overall operations of the WF, which would have a set of advisory committees at both national and at county levels, to allow for good collaboration between governmental and WF activities and the uptake of lessons and practices into policy and catchment management processes, and a Technical Secretariat, responsible for the day-to-day management of its activities.

- Upon legal registration of the WF, the financial management system would be established to allow for the capitalisation of the endowment through funds from its public, private, and international partners. The success of the WF would be measured against its ability to disburse funds and to provide incentives for catchment management and to improve downstream water quality and quantity.

- Component 2: Improved Upper Tana catchment ecosystems that support livelihoods, food security and economic development. The aim of investment flows for SLM and INRM to the catchment area, was to foster adaptation and to increase the resilience of the local population through improved food production, household incomes and diversified development options and livelihoods.

- Financial, in-kind, and technical support were to be provided by the project to SLM initiatives based on a modelling approach linking spatial prioritisation with an impact assessment for soil and water conservation, and an analysis for return on investment. The combination of biophysical and agricultural techniques and support for water management was expected to lead to diversified production and increased yield through improved soil retention, broadened adaptation potential and resilience through reduced erosion upstream, as well as at least stabilised catchment ecosystem services. Downstream economic benefits would include reduced water treatment costs through reduced sediment concentration and increased hydropower generation through higher water yield and reduced sedimentation.

- Component 3: Robust knowledge management and learning systems implemented to direct UTNWF management and share lessons both nationally and regionally. Strong emphasis would be placed on Monitoring and Evaluation frameworks to a) support WF decision making and allowing for an adaptive management approach to the targeted incentive schemes, and b) to allow for upscaling, policy integration and replication of lessons learned as quickly as feasible.

3.1.2 Overall Design

- As noted above, the UTNWF project design was robust and comprehensive, with clear objectives that are relevant to the mandate of the Ministry of Environment and Forestry (MoEF).  The design built on a strong foundation of a business case for the establishment of the Water Fund for Nairobi conducted by TNC and its partners between 2012 and 2015. The business case was developed based on a study that modelled the economic impact and expected benefits of a fund supporting land conservation measures in the Upper Tana River Basin. The results of the study presented a strong case for the creation of a fund to secure the health of Nairobi’s water supply, boost agricultural production, and preserve vital hydropower resources.

- Lessons learned from relevant IFAD-assisted projects on agriculture and natural resources management, ecosystem restoration and related activities in the Upper Tana catchment also provided detailed contextual information and technical inputs into the UTNWF project. Projects such as the Upper Tana Catchment Natural Resource Management Project (UTaNRMP) and its predecessor the Mount Kenya East Pilot Project for Natural Resource Management (MKEPP) as well as the Kenya Cereal Enhancement Programme - Climate Resilient Agricultural Livelihoods Window (KCEP-CRAL) helped shape the UTNWF while providing opportunities for creating synergies during implementation. Overall, the UTNWF was guided by a theory of change (figure 1) and a robust monitoring and evaluation system with well-defined gender disaggregated indicators.

3.1.3 Alignment with national and county government policies.

- The UTNWF initiated by TNC is the first of its kind in Africa and specifically in Kenya. The Tana River is known to supply 95 % of the water for Nairobi’s 4 million residents and another 5 million people living in the watershed. In addition, it feeds one of the country’s most important agricultural areas and provides about 65 % of the country’s hydropower output. Hence, the project addresses the key government priorities in the constitution and the Public Private Partnerships (PPP) Act, 2013. By implementing riparian management and wetlands protection for vegetation buffering along riverbanks; reafforestation and adoption of agroforestry practices; terracing of hill slopes on steep farmland and support for village nurseries, the project is in line with key policy outcomes found in the National Environment Policy (2013), National Policy for the Sustainable Development of Northern Kenya and other Arid Lands (2012), Forest Policy (2014), National Land Policy (2009), Biodiversity Regulations (2006) and the Tana Catchment Management Strategy (2014-2022) which seeks to manage, regulate, protect and equitably allocate water resources. The project remains relevant with the Agricultural Sector Transformation and Growth Strategy (ASTGS) 2019-2029 that supports commercialization of smallholder agriculture.

- The Water Fund Project is strategically aligned with and highly relevant to the Kenyan government’s objective of conserving water towers (i.e., watersheds) that are critical to the economic well-being of the country and essential to the livelihoods of millions of farmers and citizens. It enables mainstreaming of the PPP modality in the government planning process and justifies national and county governments and their agencies to support the project financially and with their staff.

- Climate change is an increasing risk with long-term consequences on poverty and food security in Kenya. Under component 2, the UTNWF project supports smallholder farmers in climate smart agriculture through the promotion of agroforestry, water harvesting and conservation measures such as water pans and drip irrigation technologies. The National Climate Change Response Strategy (2010) and National Climate Change Action Plan (2013) seek to mainstream an inclusive and equitable low-carbon development pathway for the country in the face of climate change. The project addresses climate related stresses in the Upper Tana watershed that directly impact water supply for local farmers, Nairobi city and Kenya’s hydropower generation. The activities under component 3 through research, demonstrations, knowledge management and lessons learning are highly relevant to addressing technical and knowledge constraints to improving livelihoods and ecosystem restoration in the project target areas.

3.1.4 Relevance to the poor and vulnerable groups.

- UTNWF objectives were largely relevant to the needs of the rural poor and address challenges of low agricultural production caused by water shortages, soil erosion, soil degradation and climate change. The design was deliberate in its focus on women, youth, and smallholder farmers who can benefit from an increase in their technical knowledge and organisational capacities to enhance their incomes. The targeted watershed groups comprised of 56 % men and 44 % women, which is significant progress towards achieving gender equality in Sustainable Land Management (SLM) and Integrated Natural Resources Management (INRM) interventions.

- At design, particular attention was paid to targeting of youth and also creation of youth employment opportunities (e.g. in biophysical conservation measures, nurseries etc.) or improving women’s and youth representation and decision making in local institutions. Overall, the project performed well as about 8% of the targeted watershed groups were youth. These youth have ventured into new opportunities in agriculture and its value chains, and this approach aligns well with the Kenya Youth Agribusiness Strategy 2017-2021. Going forward, more targeted support towards youth would be required to address their underlying constraints concerning access to predictable and sustainable markets (including export markets), access to land and greater linkages with the private sector.

3.1.5 GEF objectives

- UTNWF contributes to the overall objective of the GEF Food Security Integrated Approach Pilot (FSIAP), renamed Resilient Food Systems [RFS] Program): to support countries in target geographies for integrating priorities to safeguard and maintain ecosystem services into investments improving smallholder agriculture and food value chains. The Water Fund and its integrated approach is encouraged by GEF as a scalable initiative across Africa. It is especially appreciated by the government as it offers an opportunity for MoEF to work with ministries and agencies focused on agriculture, water, and other sectors.

- The Water Fund project addresses objectives of the Conventions on land degradation, biodiversity, and climate change and includes GEF core indicators for global environmental benefits (GEBs). The most innovative and ground-breaking aspects in the Water Fund project are its private sector approach to sustainable fundraising and linking this to the payment for ecosystem services to ensure sustainability and farmer/community incentives. However, these approaches caused some initial challenges, and it took time for players to understand the project.

- The strongest contribution of the GEF-6 Water Fund project to environmental governance is the Water Fund’s Endowment Fund itself. It has been a ground-breaking innovation that led to one more such Fund operating in Cape Town, South Africa, and to seven others being developed across the continent. The relevance of this project is also demonstrated by the government’s recent allocation of counterpart funds for three additional critical water towers in the country.

3.1.6 IFAD objectives and COSOP

- The UTNWF was strongly aligned to IFAD’s third country strategic opportunities programme (COSOP) 2013-2018 which focused on agricultural intensification, value addition, market access and sustainable natural resource management. The three strategic objectives were: (i) gender-responsive, climate-resilient and sustainable community-based natural resource management; (ii) access to productivity-enhancing assets, technologies and services; and (iii) access to improved post-production technologies and markets. UTNWF particularly contributed to maintaining ecological integrity, natural capital and biodiversity, while improving degraded lands through sound soil and water conservation techniques, with a view to mitigating and adapting to climate change and variability (objective 1). By promoting market-oriented production and increased access to markets by smallholders, the project was in line with objective 3 of COSOP. The project remains consistent with IFAD objectives as stated in the Country Strategic and Opportunities Programme (COSOP) for 2020-2025 that retained (with minor adjustments) the three strategic objectives of the 2013 COSOP.

- The UTNWF was aligned with (a) IFAD's Policy for Environment and Natural Resource Management, which proposes greater attention to risk and resilience to manage environmental and natural resource-related shocks and (b) the IFAD Strategy on Climate Change, that aims to support small producers (women and men to increase their resilience to climate change and promote a documented and more coherent dialogue on climate change, rural development, agriculture, and food security. Furthermore, it follows the procedures of an Environmental and Social Assessment and complies with most of the IFAD environment and natural resources management guidelines, which promote, among others, greater attention to risk and resilience to manage environment and natural resource-related shocks.

3.1.7 UTNWF theory of change

- Overall, the UTNWF was guided by a theory of change and a robust monitoring and evaluation system with well-defined gender disaggregated indicators. The project’s theory of change can be summarised as:

IF the project  implement  soil  and  water conservation  activities in the upper Tana watershed, THEN people downstream at the ‘tap’ will have better water security, and people upstream at the ‘top’ will have improved livelihoods and well-being. Conservation benefits from the   project   activities   include   conserving   aquatic biodiversity and restoring natural forest in the upper Tana. The project’s theory of change drove the selection of output and outcome indicators.

Figure 1: The UTNWF Theory of Change

Source: Mati, B.M.; Sijali, I.V.; Ngeera, K.A. 2022. Investigating pathways for agricultural innovation at scale: Case studies from Kenya. Colombo, Sri Lanka: Commission on Sustainable Agriculture Intensification.

- RATING: The PDR was a well-grounded and comprehensive document with clearly articulated logframe and sex disaggregated indicators. The extent of project relevance with the needs and priorities of the rural poor; the extent to which the project was consistent with national development plans and policies relating to the agriculture development, environment, natural resources management and to GEF focal area on climate change, and biodiversity, is highly rated. Based on this analysis, relevance is rated as Highly Satisfactory (HS).

## 3.2 PROJECT EFFICIENCY

| Efficiency: Was the project cost-effective? How does the project cost/time versus output/outcomes equation compared to that of similar projects? | Rating HS |
| --- | --- |

- The financial performance of the project is considered highly satisfactory and there is a broad consensus that the project was cost effective. The UTNWF project had an overall financing of 33.6M USD of which a) 7.2M USD grant was from the GEF-IAP; b) USD 3M in-kind contribution by TNC to support administrative/project management costs; c) USD 1.5M as in-kind contribution from project beneficiaries (mostly labour and building material for rainwater harvesting and fixed dome biogas systems); d) USD 11.9 M as in-kind contribution from local NGOs and county governments; e) USD 10M private sector pledges towards capitalisation of the Water Fund.

- The GEF/IFAD contribution of US$7,201,835 was disbursed and fully absorbed to support the project implementation. As reflected in figure 2, component 2 (Improved Upper Tana catchment ecosystems that support livelihoods, food security and economic development) accounted for 58% of the total budget. The actual budget spend amount for this category was higher than the approved budget amount by USD128,200 and hence the variance on expenditure for this component was the highest of the components amounting to 103%. The second largest component 1(Water Fund Management Platform institutionalised) amounted to 19% of the total budget and had a variance of 99%, followed by component 3 (Robust knowledge management and learning systems implemented to direct UTNWF management and share lessons both nationally and regionally) and project management (6%) with variances of 92% and 98% respectively.

Figure 2: GEF Cumulative Disbursements (USD) up to 31st December 2021

- Co-financing by stakeholders was met or exceeded and the only contribution below the target is the endowment capitalization. Farmers as beneficiaries contributed US$ 1.427million against a target of US$ 1.5 million (US$ 1.23M in-kind and US$0.143M in cash). .

Table 1: Co-financing by stakeholders in US$

|  | Contributions (US$) | % contributions |
| --- | --- | --- |
| Farmers (cash, in kind) | 142 767 772 | 87,7 |
| Counties and NGOs | 15 492 304 | 9,5 |
| TNC | 4 485 694 | 2,8 |
| Total | 162 745 769 | 100 |

- The farmers had the highest partner contributions amounting to 87.7 %, while counties and TNC contributed 9.5 % and 2.8 % respectively (see table 1 above).Data from the UNTWF end of project reports shows that farmers generally increased their cash contributions each year from as low as $4671 in 2018 to $74 657 in 2021, demonstrating a high level of commitment to the project’s interventions. However, in 2020 both cash and in-kind contributions from farmers took a dip largely because of the impact of COVID-19 that interrupted the implementation of activities.

- The NGOs and Counties contributed US$ 15.492M against a target of US$ 11.9 million (Table 2). TNC contributed US$ 3.885M against a target of US$ 3 million and the private sector support at end of December 2022 was US$ 1.3 million for activities and endowment capitalization.

Table 2: Contributions by Counties (2018-2021) in US$

| County | 2018 | 2019 | 2020 | 2021 |
| --- | --- | --- | --- | --- |
| Murang'a | 6 587 181,03 | 684 633,04 | 1 590 175,86 | 1 241 134,13 |
| Nyeri | 61 710,30 | 33 515,98 | 106 523,56 | 1 619 032,64 |
| Nyandarua | 158 274,74 | 196 211,50 | 278 509,33 | 414 347,85 |
| Laikipia | 40 122,06 | 19 067,51 | 416 410,73 | 1 397 970,78 |
| Water Resources Authority | 6 046,18 | 72 055,06 | 62 660,79 | 280 049,93 |
| Partners- CARITAS & SACDEP | - | - | - | 226 670,74 |
| TOTAL | 6 853 334,32 | 1 005 483,10 | 2 454 280,27 | 5 179 206,08 |

- While the project prepared a comprehensive analysis of the co-financing received and the sources as recommended in the previous IFAD mission, the financial data did not include the activities that were financed by those funds.

- In terms of project timelines, all components were generally implemented on time. Some delays were however observed when it came to rolling out the drip kit technology and water pans due to delays in procurement and the impact of COVID-19.

- RATING: The financial performance of the project is considered highly satisfactory and the project was cost effective. The GEF/IFAD contribution of US$7,201,835 was disbursed and fully absorbed to support the project implementation.  Co-financing by stakeholders was met or exceeded and the only contribution below the target is the endowment capitalization. The quality of project implementation was generally good despite with little procurement delays due to the impact of COVID-19. As such, efficiency is rated as Highly Satisfactory (HS).

## 3.3 PROJECT EFFECTIVENESS

| Effectiveness: the extent to which the project’s actual outcomes were commensurate with the expected outcomes? | Rating: S |
| --- | --- |

Component 1: Institutionalization of Water Fund Management Platform

Outcome 1.1: Multi-stakeholder and multi-scale platform supports policy development, institutional reform and upscaling of INRM

- The Water Fund is now registered as a charitable trust and fully operational with a Board of Trustees (BoT), Board of Management (BoM), Counties Advisory Committee (CAC), and staff. The BOTs’ role is to manage the overall operations of the WF, establish a Board of Management (BOM), an advisory committee at the county level, and a Technical Secretariat, responsible for the day-to-day management of its activities. The BoT and BoM met and exceeded the target for the number of sittings to deliberate WF activities, work plans, budgets, policies as well as fundraising targets for the endowment fund. Three technical committees (monitoring and evaluation, resource mobilization, finance, and investments) of the BOM were set up, with terms of references (TORs), to support the governance team in the oversight of project operations.

- The Water Fund business case study focused on the benefits that would arise given a USD 10 million investment in priority sub-watersheds disbursed over a period of 10 years as a preferred scenario. From a financial perspective, the business case recommended that to achieve the results required in the Upper Tana, an annual expenditure of some USD 1 million would be required over a 10-year period, impacting on some 50,000 farms and adjacent forests whereby most farms would be engaged to change their land management and soil management practices. This meant collective action by partners downstream and in the international community, who would mobilize at least USD 1 million annually, to try to achieve the target of USD 10 million that constituted the initial budget of the Water Fund.

- At the time of project completion, the target for the Endowment fund had not been achieved. The assumption made at design that the funding would come from the private sector did not fully materialize. Mobilizing contributions from the private sector had not been as successful as originally planned. The design should have included other sources of funding from the public sector and counties. Assessed against the original target of USD 7.5M, the capitalisation of the Endowment fund is still low, currently at USD 2.4M. At the time of this evaluation, the target had been revised downwards to USD 5M based on conservation investments received by the Water Fund which included a donation of office space, bringing the shortfall to USD 1.4 M.

- Efforts to mobilise resources for Trust activities and the Endowment Fund have been intensified supported by a dedicated staff from TNC. While there is a strong commitment to continuously engage with the private sector, there are opportunities for intensive engagements with the government through the Ministry of Environment and Forestry as recommended in the previous IFAD mission. Discussions with national and county government partners indicate their readiness in working with the Water Fund and in support of fundraising initiatives and other legal routes towards capitalisation of the endowment fund. The water fund can strengthen the use of scientific evidence generated in the life of the project as an advocacy tool for mobilising government funds. This approach will support TNC’s current discussions with national and county governments on earmarked tariffs for water and forestry conservation. There is also need for Private Sector, CoG and community representation to craft better way forward including host counties to consider sustainability budgets in their CIDPs.

- This exceptional achievement in the establishment of the water fund, the first of its kind in Africa is backed by TNC’s commitment to provide USD 200,000 annually as support to the Water Fund for up to 3 years to meet its financial shortfalls. Going forward, the project has developed a 5-year strategic plan that upscales the conservation of the Upper Tana watershed and supports the livelihoods of communities.

Outcome 1.2: Policies and incentives support climate-smart smallholder agriculture and food value chains in financially viable and sustainable watershed stewardship.

- The project developed MOUs with county and national government agencies as well as the private sector to strengthen the institution as a public-private partnership for a collective implementation and coordinated conservation interventions across the watershed. Four policies on wetlands and riparian areas, invasive and alien species, mining and quarries management, and rural roads and stormwater management were formulated. The first drafts of these four policies have been finalized after stakeholder consultations conducted in Nyeri, Nyandarua, and Murang’a counties. The drafts have been submitted to the respective county assemblies and county executive committees for buy-in. If adopted, these policies will be crucial in supporting the county government to provide an enabling environment for public private partnerships that support the protection of the environment and water catchments.

Component 2: Improved Upper Tana catchment Ecosystems that Support Food Security and Economic Development

Outcome 2.1: Increased land area, freshwater, and agroecosystems under INRM and SLM

- The project successfully implemented diverse interventions that promote climate-resilient agricultural production systems, agroforestry, wetlands protection and restoration, protection/ conservation of riparian zones, biogas generation and other cash crop interventions such as avocado production. The number of hectares of land brought under climate resilient management (SLM implemented) increased from a mid-term target of 50 000 ha to 77401 ha at completion (achieving 77 % of planned target). This includes beneficiaries reached by the project and 36,251 ha directly impacted under public forests.

- Analysed at the household level (Figure 3), the project overachieved in terms of persons supported to sustainably manage natural resources and climate risks at 245% (representing 301%, 189%, 215% for men, women and youth respectively). Rainwater harvesting in water pans at the farm level was prioritised as a key intervention to increase farmers’ resilience to climate variability and change. In 2021, 15,463 water pans had been installed and could cumulatively harvest over 1.9 million cubic meters of water annually. The technology has been adopted beyond the project area by 960 households that have established an additional 1,145 water pans in neighboring counties. In places like Githambara micro-watershed where water pans were intensively implemented, over 20% reduction in turbidity was recorded during the rainy seasons compared to the baseline scenarios. However, water pan use amongst women is still low at 57% compared to 117% for men (see figure 3). In some cases, water pan liners were supplied late due to the impact of COVID-19 and so the benefits are yet to accrue to the beneficiaries.To enhance outreach for women-headed households and people living with disabilities, a 50% subsidy was granted over amounts paid by other beneficiaries in the community.

Figure 3: Achievements against key output indicators at household levels

Source: UTNWF project report- Physical progress measured against AWPB, including ORMs indicators

- Farmers were also using drip irrigation kits to enhance efficient water use. There was, however, underperformance when it comes to number of drip kits owned.  In general, women achieved less than men and youth in terms of implementation of the conservation measures. The COVID-19 affected distribution of drip irrigation kits since they were being procured from abroad. In addition, the contracting and bidding process of drip irrigation service providers also took some time hence delaying the process of availing irrigation kits to farmers.

- The Area (ha) influenced to adopt SLM had a significant but limited achievement which stood at 35% at completion. The endline survey noted that for example, some riparian conservation activities such as creation of buffer zones between the edge of the water course and the cultivated area had slow adoption. At least 90% of households with agricultural land had their buffer zones less than 10m from a water course while about 29% of households had land directly bordering a water course. The findings at endline show that there is certainly some encroachment despite all the sensitization and training on the need for buffer zones. As reiterated by an NGO partner during this terminal evaluation mission, apart from individual farmer interest and motivation, the small average land sizes constrain some farmers from adopting the conservation practice.

- The project registered tremendous success in increasing land area under vegetation cover- 3,630,499 trees were planted across the watershed with an average survival rate of 78%. In terms of water harvesting technologies, 15,463 water pans were installed with a capacity of over 1.9 million cubic meters of water annually. In addition, 316 km of riparian land were conserved and put under active protection across the watershed. Farmers adopting SLM measures were reported to have registered improved production and productivity due to better water and nutrient retention. Endline data showed that households had adequate fodder for their livestock through growing, collecting or buying. The endline survey recorded a significant increase in the proportion of households accessing fodder from 57% at baseline to 74% at endline.

- There were significant improvements in water quantity observed. According to the endline survey, a total of 93% of households in the treated watersheds had adequate water for 6 - 12 months of the year, slightly higher than 84% for the baseline. Additionally, 67 % of these households reported having adequate water year-round compared to 61% for the baseline. The proportion of respondents who never had enough water during the dry season reduced considerably in comparison to baseline (from 80% to 37%). Respondents’ perception of water quality before treatment was inconsistent. While at baseline 91% of the respondents reported the quality to be satisfactory, good or very good, the endline recorded only 84 % and 82% of the households for treated and control respectively on the same indicator.

- The project registered notable environmental as well as socio-economic outcomes. For example: the average annual (4-year average) flows in the UTNWF increased by 40 % compared to baseline averages before the project. It was observed that water quantity in the Gathanji micro catchment (treatment) is 19% more than that in Marogoya micro catchment (control). Furthermore, average annual water quality was observed to have increased across the treated micro-watershed, with significantly less sedimentation than in the control. Consequently, rivers in the micro-catchments, such as Maragua river and Chania River have recorded 27% and 31% reduction in sedimentation respectively.

- Reducing GHG emissions and increasing carbon sequestration in the project area is a cross-cutting aim and co-benefit of activities that were carried out as part of SLM, riparian management, and by providing training and capacity development for nursery management and diversified crop production, improved Agroforestry management through (fruit) tree planting campaigns and supply of planting materials.

- The end of project report showed that over 3.6 million trees were planted in the watershed, 995 km of grass strips were established, and 316 km of riparian buffers were established in the watershed to control water, sediments, and nutrients runoff from farms. Using the FAO EX-ACT tool, these interventions were estimated to sequester about 5.8 Mtons CO2eq. against a design target of 10% over 1.6 MtonsCO2eq. at baseline. In addition, 15 tree nurseries (against the design target of 3) were established and are managed by the local communities to sustainably supply tree seedlings and improve carbon stocks in the watershed. From the MPAT endline survey, beneficiaries in the treatment micro watersheds had a higher mean number of trees per acres (114) compared to those in the control micro watershed (86). Overall, the number of trees increased from the average of 77 trees per acre in the baseline to 100 trees per acre in the endline hence more land areas under improved management.

Component 3: Robust knowledge management (KM) and learning systems

Outcome 3.1: Institutions capacitated to monitor Global Environmental Benefits (GEBs)

- The project achieved the targets of successfully integrating the Global Environmental Benefits (GEB) monitoring tools and protocols with partner institutions by establishing/completing Land Degradation Surveillance Frameworks (LDSF) for at least 5 sub-watersheds. In addition, a total of 33 biophysical monitoring stations (against a target of 28) have been developed/upgraded and are operational. Further, a water-quality database was established and integrated into Water Resources Authority (WRA) system and is accessible to stakeholders who use the data to develop knowledge products for sharing. Results for Thika River, for instance, over four years (2017-2020) show increased water yield (4.96% equivalent to 12.3 million cubic metres per year), increased dry season water yield (31.2% from 0.340 to 0.446 averaged over 4 years) and this is equivalent to 3.5 million cubic meters compared to the 2016 baseline values. The capacity of institutions like WRA, NMK, and NCWSC has been enabled and monitor and assess biophysical processes in the watershed. An online information sharing center has been established at the NMK grounds with a wide range of materials accessed by thousands of people daily.

- The databases provide for remote data collection, storage, and visualization for timely decision-making and adaptive management. Two Power BI dashboards established at the Nairobi City Water and Sewerage Company (NCWSC) offices are linked to six telemetric stations that provide real time reports on water quality and quantity in treatment intakes and flows into major rivers and reservoirs. NCWSC reported improved water quality and increased dam levels in the last three years. At the time of this evaluation, NCWSC had challenges of poor network connectivity due to changes in the service provider, which could potentially affect its efficiency in the production of real-time data.

- Many aspects of water quantity and quality are closely interlinked. Through developing a good understanding of the catchment-specific relationships between water quality and flow, it may be possible for authorities to better integrate water quality considerations in determining environmental flow requirements for rivers and environmental watering requirements for wetlands. This will require greater interaction between NCWSC and Water Resources Authority (WRA) through integrated planning and analysis in-order to generate comprehensive analysis useful for effective water management plans.

Outcome 3.2: M&E framework supports the integration of climate resilience into policy making

- A project end-line Multidimensional Poverty Assessment Tool (MPAT) and outcome surveys were successfully completed. Results show an improvement in the community livelihoods by 6% and improved nutrition, food production, and biodiversity in the project area. Two DHIS2 databases were established: one for socio-economic data and the second for hydrometeorological data. However, MPAT survey results are yet to be referenced in county development plans, as means for informing policy decisions on climate change adaptation and resilience building.

Outcome 3.3: Knowledge management and sharing of lessons learned is facilitated

- In relation to robust knowledge management and learning systems; the project has improved the measurement of water quality and quantity through upgrading of water monitoring stations (127% of the appraisal target). The status of land degradation was established through Land Degradation Surveillance Framework (LDSF) mapping (100% of the appraisal target) and the next assessment will be in 2023; establishment of WRMA water quality database (100% of the appraisal target). The project has been active in sharing of information, lessons learned best practices, and in raising awareness of the water fund model at national, regional, and international levels (400% of the appraisal target). Through sharing of lessons learned, scaling up to two other WFs in Eldoret and Mombasa was achieved (100% of the appraisal target). In addition, two online information centres at Sagana and NMK has improved accessibility to raise stakeholders' awareness on the project.

- The project did exceptionally well in terms of knowledge sharing and utilizing various platforms for the dissemination of the achievements. This included the awarding of scholarships to 15 Masters students of Jomo Kenyatta University of Agriculture and Technology (JKUAT’s) Water Resources and Research Centre to undertake research on water and conservation related topics in the Upper Tana catchment. As part of knowledge management and sharing of lessons, the project reached secondary schools with environmental awareness and tree planting activities. In addition, the project established two online information centres at Sagana and National Museums of Kenya (NMK) for information sharing and dissemination of the work of UTNWF to various stakeholders.

- Twelve knowledge management seminars and exchange visits were successfully conducted to share the project’s lessons learned for scaling of intervention to other regions and adaptive management of interventions. In Kenya, two water funds completed the feasibility phase i.e., Mombasa and Eldoret-Iten Water Fund. The design phase of the Eldoret-Iten Water Fund was completed, and a steering committee is in place to lead the creative process of the WF. Seven other water funds are in development across Africa.

- One area that could have been strengthened is the link between component 1 and 3 in terms of ensuring data/knowledge generated had greater policy influence impact especially the capitalisation of the endowment fund. The project generated various lessons but did not systematically consolidate and document these lessons in a balanced way under each component in terms of what worked and what did not.

- RATING: The project successfully implemented diverse interventions that promote climate-resilient agricultural production systems, agroforestry, wetlands protection and restoration, protection/conservation of riparian zones, biogas generation and other cash crop interventions such as avocado production. The Area (ha) influenced to adopt SLM had a significant but limited achievement which stood at 35% at completion. The project registered tremendous success in increasing land area under vegetation cover. There were significant improvements in water quantity and quality observed. The average annual (4-year average) flows increased by 40 % compared to baseline averages before the project. The project achieved the targets of successfully integrating the Global Environmental Benefits (GEB) monitoring tools and protocols with partner institutions by establishing/completing Land Degradation Surveillance Frameworks (LDSF) for at least 5 sub-watersheds. In addition, a total of 33 biophysical monitoring stations (against a target of 28) have been developed/upgraded and are operational. The project did exceptionally well in terms of knowledge sharing and utilizing various platforms for the dissemination of the achievements. One area that could have been strengthened is the link between component 1 and 3 in terms of ensuring data/knowledge generated had greater policy influence impact especially the capitalisation of the endowment fund. The project generated various lessons but did not systematically consolidate and document these lessons in a balanced way under each component in terms of what worked and what did not. Based on this analysis, effectiveness is rated Satisfactory (S).

## 3.4 SUSTAINABILITY

- The project had a good overall sustainability strategy at the water fund level. The sustainability strategy is expected to be the autonomous Nairobi water fund which is now operational and fully staffed and will continue with farm and community-based interventions. At county level, this sustainability is expected to be boosted by the fact that counties are still represented in the county advisory unit of the Nairobi water fund. Most of the interventions are also funded at county level through county budgets, evidenced by the high levels of co-financing provided by counties. The project developed memorandum of understandings (MOUs) and joint plans with clear annual workplan and budgets with each county. These agreements however did not provide a clear exit strategy on how the counties will support these interventions after the lapse of the MoUs. The project has seamlessly transitioned into a long-term programme with Water Fund Trust and its stakeholders e.g., Counties, WRA, KWS, KFS etc continuing as partners into the long-term. There are, however, still challenges around market linkages, commercialization of some enterprises such as avocadoes as well as value addition that will need to be supported.

- Financial sustainability. The project promoted five value chains (avocado, dairy, coffee, rose geranium, and French beans) geared towards boosting food production and increasing income for farmers. Further, farmers benefiting from the project’s interventions had experienced an increase in income from the sale of forest tree seedlings, fruit trees especially avocados, Napier grass and horticulture produce (using water pans and associated drip irrigation). While the project had partnered with several partners especially the local government and private companies, farmer entrepreneurs, and farmers' organizations, this had not fully addressed the challenges of market access and ultimate financial sustainability. Farmers interviewed during this mission, lamented at the challenges of market access, high cost of agriculture production and climate change that threaten the sustainability of the value chains and general income generating activities. In the case of coffee production, the farmers also experienced fluctuating prices which is a risk to financial sustainability.  To address market access challenges, the endline survey recommended the promotion of value addition for different value chains. The WF developed a strategic plan for deepening and scaling up project interventions. Rating: Moderately Unlikely (ML)

- Socio-political sustainability: The UTNWF project had a structured and grounded capacity development strategy which was also demand driven based on the stakeholder needs. As such, project staff, partners, and county extension assistants as well as farmers were trained on different topics and technologies to ensure proper implementation of activities. Some of the topics included agroforestry, drip irrigation, gender and quarry training. Farmer training included on-farm demonstrations, farmer field schools and exchange visits  to promote adoption of technologies and cross- learning amongst farmers.

- The capacities and skills that the beneficiaries require to continue with the conservation approaches and manage the investments promoted by the project do exist. The extent to which these capacities can be sustained vary largely based on the level of motivation and financial benefits. On one hand, there are some farmers who have performed exceptionally, diversified their agriculture production, embraced SLM and INRMs measures, established markets and networks with other private sector actors within the avocado and coffee value chains. With these farmers, there are excellent prospects for sustainability because they have commercialized their businesses and are taking farming to be a business. While on the other hand, there are other farmers, who still require marketing skills and value chain support. Rating: Likely (L)

- Institutional and governance sustainability: As already discussed under effectiveness, (component 1), the project built able structures for institutional and governance sustainability. The project worked with individual farms as the entry point and the local Water Resources User Associations (WRUAs) and other community associations were used for outreach, material distribution and monitoring. However, at the county levels, there was anticipation that the capacity of the WRUAs could have been strengthened to support some of the project interventions particularly in riparian conservation activities (e.g. vegetation buffer zones along riverbanks, agroforestry, terracing of steep and very steep farmlands, grass buffer strips in farmlands, reforestation of degraded lands at forest edges, and erosion mitigation from dirt roads). The WRUAs were proposed by IFAD as part of synergy with the ongoing UTNRMP which works in the catchments and to increase impact. The project approach did not factor in capacity building and financing of WRUAs as this is comprehensively done through the WRUAs development financing cycle fund of the UTaNRMP. The WRUAs in this case were only expected to support TNC in riparian conservation efforts. Even with funding pumped by UTANRMP and years of capacity building efforts, the WRUAs are still  weak as they require income generation activities and good governance. Rating: Likely (L)

- Environmental sustainability. The project has prepared an environmental and social risk management report on how the risks were addressed or mitigated during implementation. These measures include capacity building public and private partners in risks mitigation, institutional collaboration with national and county governments to provide a clear framework for leveraging skills and capacities, project activities and co-financing, provision of a shared platform for financing on nature-based solutions, and communities' livelihoods impacts, integrated climate-smart technologies and socio-economic coping mechanisms – including empowerment of vulnerable groups, women, and youth. Likely (L).

## 3.5 PROGRESS TO IMPACTS

Household assets

- At an aggregate level, data shows improvements in indicators of: households with television sets, housing, clothing and energy, domestic water supply and non-farm assets for beneficiary households (treated) as reflected in table 3.

Table 3: Changes in Household Assets amongst beneficiary households

|  | Baseline | Endline |
| --- | --- | --- |
| Households with TV sets | 41% | 76% |
| Housing, clothing & energy | 63% | 71% |
| Domestic water supply | 66% | 75% |
| Non-farm assets | 59% | 72% |

Source: UNTWF endline survey

- There was a marked improvement in the housing of the respondents in the endline survey. Analysis using the Difference in Difference (DID) method recorded significant differences in housing between the treated and control watersheds at the endline (significant at p<0.01) and also between baseline and endline (significant at p<0.05). However, the control sites gained more than the treatment sites, implying that the change was not entirely due to project activities. Similarly, DID analysis for non-farm assets showed the increase to be statistically insignificant between endline and baseline

Food security

- The endline MPAT survey showed that more households had some degree of insufficient food compared to the situation at baseline. About 50% in the treated areas and 76% in the control areas reported skipping a meal or reducing the portions at least once or twice in the period under observation. This compares unfavourably with the baseline data of 8%. The number of households skipping a meal or reducing the portions showed significant variations between the zones and also among the micro-watersheds. More FHH experienced this phenomenon than MHH. Findings of the survey also showed a very worrying 50% and 55% of treated and control households going to bed hungry at least once or twice during the period under review. This was significantly higher than findings at baseline of just 5%.

Environment and natural resource management

- Notable progress has been made, with the project promoting interventions that aim at increasing the land area under SLM practices. These include water pans, protection of riparian land, excavation of terraces, protection of rural road shoulders, installation of drip kits, rehabilitation of communal pans, agroforestry, wetlands biodiversity atlas, NMK databases development, tree planting etc. Furthermore, farmers have continued to receive regular conservation and extension information through the SMS platform. The project has met or exceeded most of its design targets and some environmental and socio-economic outcomes reported on. The outcomes of the investments in GEBs at landscape and farmer levels need to be reported on adequately and against the new GEF core indicators.

- The project has achieved various milestones and met majority of its design targets. The collaboration with NMK to support biodiversity conservation related interventions, monitoring and reporting has borne fruits. Six (120%) biodiversity mapping reports were produced, and 36 (360%) sites for feed assessed. One biodiversity atlas (100%) and 1 NMK database (100%) have been developed. The public display platform at NMK provides regular conservation and biodiversity information to the public. The LDSF has been critical in mapping the extent of land degradation and ecosystem health, leading to better prioritisation of degradation hot spots.

- So far, about 3.4 M trees have been planted to enhance environmental conservation, carbon sequestration and income generation. The school greening programme has reached 92 schools and is inculcating conservation skills in children, resulting in tree planting and nurturing in schools and homes. The project has made encouraging progress in SLM (72,980 ha) and 38,923 farmers have been reached, with 65% of the project beneficiaries having more than 25% of their land under SLM. Farmers adopting SLM measures are reporting to have registered improved production and productivity due to better water and nutrient retention. In the outcome survey and end line report, the production and productivity enhancement should be backed with quantitative data. The project has also managed to rehabilitate 163 Ha of public forest and 960.9 km of terraces and grass strips have been prepared as soil and water conservation measures. Additional measures include protection of riparian lands protection in 298.3km of rivers in the watershed. A graduation model has been developed that aims at categorising farmers on the basis of their uptake of SLM measures. More investments are required in data collection/analysis including cross-referencing with the baseline situation and the initial farm plan

Adaptation to climate change

- The project made significant contribution to climate change mitigation through planting of trees (382% of the appraisal target) and attaining a survival rate of 78%. Avocado trees are estimated to yield KES1.3 billion shillings and provide youth employment to improve livelihoods. Only drip irrigation is far below target. The project restored 140 km of terraces resulting in increased water yield levels by over 52.8% compared to baseline figures. The project planted 60.9 km of grass strips and this shows willingness to adopt conservation practices leading to reduced sediments and nutrients in rivers. 298.3 km out of 319.7 km of riparian land have been conserved, while water pans have empowered farmers to grow crops in the dry season and improve their food and nutrition security and incomes. SLM interventions have led to the improvement in the water quality and quantity. A survey showed that 82% of the people indicated that crop production had increased leading to improved food and nutrition security and livelihoods.

- Reducing Greenhouse Gas (GHG) emissions and increasing carbon sequestration in the project area is a cross-cutting aim and co-benefit of activities that were carried out as part of SLM, riparian management, and by providing training and capacity development for nursery management and diversified crop production, improved Agroforestry management through (fruit) tree planting campaigns and supply of planting materials.

- Over 3.6 million trees were planted in the watershed, 995 km of grass strips were established, and 316 km of riparian buffers were established in the watershed to control water, sediments, and nutrients runoff from farms. Using the FAO EX-ACT tool, these interventions were estimated to sequester about 5.8 M tons CO2eq. against a design target of 10% over 1.6 M tons CO2eq. at baseline. In addition, 15 tree nurseries (against the design target of 3) have been established and are managed by the local communities to sustainably supply tree seedlings and improve carbon stocks in the watershed.

- From the MPAT endline survey, beneficiaries in the treatment micro watersheds had a higher mean number of trees per acres (114) compared to those in the control micro watershed (86). Overall, the number of trees increased from the average of 77 trees per acre in the baseline to 100 trees per acre in the endline hence more land areas under improved management.

- To increase the resilience and adaptation mechanism against climate change, the project promoted rainwater harvesting through water pans to control excess runoff on farmlands and provide enough water for irrigation during dry seasons. Farmers and institutions in the project area have installed 15,463 water pans with a capacity to harvest over 1.9 million cubic meters of rainwater annually.

- The project worked with the extension officers and technology-based platforms (SMSs) to disseminate weather and climate advisories in form of short messages that were translated into the local language. Climate awareness and knowledge improved from 63% at baseline to 81% by the end of the project. Comparatively a greater improvement was recorded in the semi-arid areas of the Maragua sub watershed from 49% to 81% over the project period. The MPAT score measuring exposure and resilience to shocks improved by 2 points despite the huge impacts of the COVID-19 pandemic on social and economic activities.

# 4. Assessment of monitoring and evaluation system

## 3.5 Monitoring and Evaluation Design

| M&E Design: Was the M&E plan at the point of endorsement practical and sufficient? Did it include baseline data? Did it: specify clear targets and appropriate indicators to track environmental, gender, and socio-economic results | Rating HS |
| --- | --- |

- The project had a robust and detailed high-quality monitoring and evaluation plan for the UTNWF. M&E approaches follow a theory of change, which presents the logic of how the project’s ultimate outcomes/impact will be achieved and shows the causal pathways and the means to the end’s relationships. The M&E plan details the output and outcome indicators the project will track and report on. It also specified data sources for the indicators, indicator definitions as well as data collection frequency for each indicator.

- Household-level indicators would come from 1,000 household interviews, Greenhouse gas estimates from EX-ACT (‘Ex-ante carbon balance tool’) informed by the Land  Degradation  Surveillance  Framework surveys; changes  in  water consumption before and after water conservation activities would be measured using a sample of smallholder treatment  and  control farms and changes  in  water  quality  measurements before  and after project activities will be measured in four control and seven treatment micro-watersheds.

- The socioeconomic baseline was completed in March  2017 and comprised the MPAT’s 143 questions  plus 30 more questions on  various water  fund and  climate  resilience indicators. All socioeconomic data were gender and age disaggregated. The project also developed wetlands and riparian baseline using the Biological Conditions Gradient (BCG) approach, land cover data, land use and soil carbon baseline data using LDSF and hydrological and water quality and quantity data sets dating back over 50 years.

## 3.6 Monitoring and Evaluation Implementation

| M&E Implementation: Whether the M&E system operated as per the M&E plan? Where necessary, whether the M&E plan was revised in a timely manner? Was information on specified indicators and relevant GEF focal area tracking tools gathered in a systematic manner? Whether appropriate methodological approaches have been used to analyze data? Were resources for M&E sufficient? How was the information from M&E system used during the project implementation? | Rating HS |
| --- | --- |

- The M&E activities conducted have been found to be in line with the M&E plan. The project‘s data  quality  has  improved  in  terms  of  accuracy  and  adequacy.  In  addition,  the  M&E officer carries out regular quality checks and engages M&E staff in Partner organisations for participatory M&E and training. Data is collected periodically. For instance, water quality parameters (turbidity and total suspended solids) continue to be monitored in all 33 river gauging stations. A correlation between total suspended solids (TSS) and turbidity has been developed for most river stations that inform future water quality monitoring campaigns.

- The results  shared  during the terminal evaluation showed  an  improvement  in  both  water  quality  and  water  quantity  which  is attributable  to  the  project  SLM  interventions.  M&E reports are available and are submitted on time and besides the regular contractual reports to GEF and IFAD, the project submitted monthly reports to the Ministry on time. There is evidence to show that M&E reports have been used for project planning and reporting and in strategic decision making.

# 5. Assessment of implementation and execution

## 5.1 Quality of Project Implementation

| Quality of project implementation: Roles and responsibilities discharged by the GEF Agencies that have direct access to GEF resources | Rating S |
| --- | --- |

- The project design document has clearly defined implementation arrangements at national and county levels including the private sector partnership. The project’s steering committee is operational and continues to provide oversight and has been meeting as planned.  Moreover, the project draws additional technical expertise on a part time basis from TNC staff such as the Kenya Country Director, Africa Water Funds Director, External Affairs Director, and the finance and operations staff, which forms part of TNC's in kind contribution to the project. The project continues to work with 4 CEAs seconded full time by the county governments of Nyandarua, Murang’a, Laikipia and Nyeri, and one Hydro-meteorological Assistant seconded by the Water Resources Authority. Partnership arrangements established through MoUs and sub-contracts with service providers continue to be effective.

- TNC, the BoT and BoM consists of a comprehensive technical skills set which aids in providing sound leadership and guidance regarding the policy, financial, legal and technical aspects of the project. These governance structures consist of individuals who are dedicated and passionate about the Water Fund and the project’s deliverables. The project’s sound implementation arrangements contributed to the greater achievement of results reported under effectiveness. IFAD played a critical and significant role in ensuring the quality of project implementation through dedicated implementation and supervision missions, targeted training/capacity building efforts sessions for TNC in various aspects including procurement, through midterm reviews, review of project documents and provision of inputs, co-development of KM products etc.

- While the Project Design Report (PDR) was clear on the roles of community level structures of governance – for example the Water Resources User Associations (WRUAs), the situation proved different at implementation. There is a mixed pictures on the extent to which WRUAs were involved in the project. There are some perceptions that WRUAs were underutilized, were not fully engaged nor were they capacitated to ensure continuity and sustainability of the conservation works. While, on the other hand, most of the riparian pegging was conducted in collaboration with WRUAs in Sasumua, Gikira, Gura, Kayahwe. In many instances the WRUAs were involved in tree seedlings demand generation, distribution and tracking of survival.

- Similarly, for all intervention clusters, it was envisaged at design that direct links will be established with the KCEP-CRAL and UTaNRMP project implementation teams as well as with their partner and smallholder beneficiary networks to ensure spatial targeting. The linkages with the KCEP-CRAL were not fully utilized because the project sites differed at implementation. In 2018, the project team recommended that IFAD helps in supporting more strategic alignment of the UTaNRM and KCEP-CRAL projects with water fund activities. While the project took up and upscaled some of the interventions promoted in UTaNRMP into other counties, the proposed strategic alignment throughout project implementation was not clear.

## 5.2 Quality of Project Execution

| Quality of project execution: Roles and responsibilities discharged by the national and county counterparts that received GEF funds from the GEF Agencies and executed the funded activities on the ground | Rating S |
| --- | --- |

- IFAD supervision missions provided appropriate recommendations and consistent follow-up missions that ultimately brought improvements in project implementation across all components. IFAD was found to have provided adequate support through project design, regular annual supervision missions and implementation providing prompt responses to identified bottlenecks. However, greater clarity on IFADs performance scoring system could have been provided at inception so that project teams are prepared and are able to report appropriately. Beyond this, IFAD was found to have operated satisfactorily in terms of technical support, and its reviews of procurement, financial management and Annual Work Plan Budgets (AWPBs), and regularly highlighted problems that negatively impacted project implementation and recommended appropriate solutions.

- The Ministry of  Environment  and  Forestry is the main partner in the delivery of the project and reaching out to other national government agencies.  The  project  had a strong relationship with the  county governments of Murang’a, Nyeri, Nyandarua and Laikipia. The county governments provided substantial co-financing to the project.  Technology partners and  technical  government  agencies  such  as  NMK,  JKUAT,  ICRAF, WRA,  KFS, IFAD etc.  were instrumental  in  providing  technical  guidance  and  strengthening  the  delivery  of  the project. However, it has been difficult to assess objectively the effectiveness of the various partnerships with a view to determine what worked well and lessons that can be learnt and taken up by the Water Fund Trust because they also play an oversight role under the BoM, thereby presenting conflict of interest issues. As noted in the previous mission, partners such as the WRA, National Environment Management Authority (NEMA) and NMK  received  equipment,  digital  technologies  and  other  material  support  that  is  meant  to allow them to improve on their operations. It is anticipated that these institutions will continue to operate these investments under their various institutional budgets.

# 6. Other assessments

## 6.1 Targeting and Outreach

- The project had a clear gender and targeting strategy and has a cumulative total outreach of 51,400 beneficiaries against a PDR target of 21,000. The cumulative outreach of farmers targeted by year is shown in figure 4. The targeting strategy was largely met, with geographical targeting focusing on selected catchments in the four counties and land degradation hotspots. Spatial tools were used to determine the extent of land degradation, farm coordinates etc. Poverty targeting was focused on female headed households and disabled or elderly as they tended to be the most poor within the project sites. Of the 418 farmers supported with drip kits, 40% of them are women out of which 75%, constitute female-headed households (FHHs). Subsidies of 50-75% are offered to the elderly, FHHs youth and disabled persons for water pans, drip kits, and biogas units.

Figure 4: The cumulative outreach of farmers by year

Source: UTNWF End of Project Report, October 2016 – December 2021

- The project has reached 51,682 beneficiaries out of which 282 are institutions like schools, churches, factories etc. With this outreach, 101,684 acres of farmland have been put under sustainable land management with great impacts on both rural livelihoods and ecosystem services. Women comprise 39% of the beneficiaries while youth make up 17.6% of the people who have been reached by the project interventions. The outreach is commendable comparing the national target figures of at least 30% involvement in any project or forum for any gender provided by the Constitution of Kenya. The project has thus surpassed this by 9% over the five year. The outreach was disaggregated by gender as shown in the figure 5 below.

Figure 5: Gender outreach over the project cycle

- The average beneficiaries' age is 50 years. About 17.6% of the total beneficiaries are youth. Like women, youth engagement as direct beneficiaries or household heads is limited by access to land rights. Lands in the project area are mainly owned by men who normally inherit from their fathers.

- The findings show that structural conservation measures are most preferred by males while women were most active in vegetative conservation measures. Land ownership and land rights have been attributed to the capture of more males as the direct beneficiary of project inputs. For instance, the direct beneficiaries of biogas and water pans are women who save time and labour in fetching firewood and water/agricultural labour, yet males have the highest percentage of involvement in construction.

## 6.2 Innovation

- The water fund model was the biggest innovation not only in Kenya but in the African continent. A detailed analysis factors and activities that contributed to the success of this innovation have been documented and published. These include:

- Establishment and institutionalization of the Water Fund management platform. This involved identification of at private sector companies in Nairobi, and linking them with public sector institutions to create a public–private partnership to establish the Water Fund as a charitable trust incorporated under Kenyan law and governed by a board of trustees.

- Mobilization of funds from both public and private sector institutions to support tangible activities in the upstream catchments. This included support from international stakeholders including the Swedish International Development Agency, GEF, IFAD, Frigoken Limited and Coca-Cola.

- There were increased investment flows to upstream catchment land users/landowners that supported sustainable land management and integrated natural resources management implemented by farmers and other land users in the Upper Tana catchments. The farmers in the identified priority conservation areas were rewarded in-kind through training, provision of free tree seedlings and nutritious fodder grasses, subsidized dam liners for water harvesting, subsidized seeds, and linkages to markets.

- Capacity building of farmers, farmer groups, community, county, and national institutions was done using extension services from NGOs in collaboration with county governments (Murang’a, Nyeri, Laikipia and Nyandarua). Farmers were trained on best practices in crop agronomy, soil conservation, water harvesting and farming as a business.

- Establishment of robust knowledge capture, management and learning systems so as to track progress made and share lessons both at local and national levels. Strong emphasis was placed on monitoring and evaluation frameworks to support the Water Fund in decision making and allowing for an adaptive management approach to the targeted incentive schemes, and also to allow for upscaling, policy integration and replication of lessons learned.

- The innovation also faced challenges of sedimentation caused by road developments occurring in some areas and direct over-abstraction of the rivers, and excess flooding during the rainy season. To solve these problems, rainwater harvesting and storage in lined farm ponds were introduced but the high cost of UV-treated dam-liners meant the farmers bore the cost of excavation (at a subsidised price). Secondly, landslides (considered a geological form of erosion) continue to occur in the most upstream parts of the catchment causing erosion damage and sedimentation of rivers, even in some steep forested areas. Lastly, climate change and erratic weather has seen extreme events of rainfall and drought, which hamper both crop intensification and watershed protection.

## 6.3 Potential for Scaling-Up

- The Water Fund model has been upscaled within Kenya and in the African continent. Having first facilitated sharing with Cape Town city to avert the day-zero crisis in 2018, their water fund is now under implementation and the city just invested $4.2million towards its activities. This comes alongside other investors like Coca-Cola, PepsiCo, JP Morgan, REMGRO, and Levi Strauss. French Development Fund has teamed up with TNC to cost-share in the development of Dakar, Senegal, and Mombasa Water Fund in Kenya where the World Bank infrastructure project is investing $5 million on the pilot- proof of concept projects.

- Coca-Cola’s RAIN project supported Catholic Relief Services in designing the Freetown (WAPWF) Water Fund in Sierra Leone while World Wildlife Fund (WWF) with support from the MAVA Foundation and the GEF Small Grants Program of UNDP have supported the development and implementation of Sebou Water Fund in the Kingdom of Morocco, the first in North Africa.

- The GEF in the current phase 8 has offered $2.98 million for implementation of Eldoret -Iten Water Fund in Kenya while Water for People and Catholic Relief Services are co-funding the design of the Blantyre Water Fund in Malawi. Several TNC supporters have invested in the development of Addis Ababa and Tanga Water Funds within the East African region. In total, two Water Funds are under full implementation, 7 are under development, and 6 are undergoing feasibility analysis with key stakeholders. A map of the Water Fund sites in Annex 6.

## 6.4 Environmental and Social Safeguards

- The UTNWFP is designed as a project expected to provide and enhance environmental benefits as well as strengthen farmers’ abilities to adapt and mitigate climate change. To achieve this, the project promotes an array of soil land water management interventions. At its design, the project was rated in category B and a Social Environmental and Climate Assessment Procedures (SECAP) review note was developed, and risks and mitigation actions identified. Previous supervision missions proposed the developed of an ESMP.

- Given that the project is predominantly environment and climate-focused, most of the mitigation measures were embedded in the delivery of the project. At design, no budgetary provision was made for ESMP. Due to that budgetary constraint, the project innovatively addressed the identified and emerging risks and proposed mitigation measures. This was consolidated in a position paper that highlights the risks, mitigation measures, resources and responsibilities, and the resolution of a grievance mechanism.

- The project has undertaken mitigation measures to reduce or avoid significant environmental and social risks as well as enhance environmental benefits. These measures include capacity building public and private partners in risks mitigation, institutional collaboration with national and county governments to provide a clear framework for leveraging skills and capacities, project activities and co-financing, provision of a shared platform for financing on nature-based solutions, and communities' livelihoods impacts, integrated climate-smart technologies and socio-economic coping mechanisms – including empowerment of vulnerable groups, women, and youth.

- UTNWF has a Knowledge Management and Communication Strategy in place and dedicated KM and communication staff. A robust database provides evidence-based data for documentation of lessons learned. Information is shared on social media, online information centres at NMK and at the county level in Sagana office, conferences among others, for upscaling opportunities. Mombasa and Eldoret-Iten have replicated the Water Fund model while many African cities have done the same. UTNWF is providing online training on Feasibility and design of Water Funds. While policy engagement resulting from lessons learned has been with County governments, the mission recommends extending this to include national government to dialogue on legislating the allocation of tax revenue towards the endowment fund.

## 6.5 Knowledge Management

- UTNWF has shown good results in Knowledge Management (KM). The project was a panellist during the World Water Week and received high level commendations from a United Kingdom Government Minister. The Project was also featured by GEF and connect was also shared on IFAD website. KM strategy is adequate and has recently been reviewed following the IFAD Eastern and Southern Africa Knowledge Management event, held in Nairobi in November 2019. Two KM virtual conferences were successfully conducted. The KM activities are coherent with the KM plan and appear AWPB. KM activities incudes: running of the national information centres at NMK and Sagana office; school awareness programme, national and international meetings, documentation and distribution of UTNWF lessons learned; and KM exchange visits. The mission recommends that UTNWF will use M&E data to draw lessons learned which will be shared to improve targeting and project performance.

- The project management team is committed to KM and they have an appreciation of the role of KM in the organisation. The project has a robust web-based Management Information System (DHIS2) for socio-economic and biophysical data on water quality and quantity. UTNWF conducts regular reviews of implementations, using the M&E data and the lessons learnt are used to make an adjustment to improve performance. The project team is actively documenting and sharing lessons from implementation, for instance using Global Water Fund and other platforms. UTNWF also shared experience in the design of the Eldoret- Iten Water Fund in February 2020. The mission observed that the Counties Advisory Committee (CAC) of UTNWF prioritized four policy issues focusing on County governments. The mission recommends that the dialogue be extended to include the national level in view of lobbying for legislation to access tax revenue allocation for the Endowment Fund.

- The KM strategy includes a communication plan. Results on water quality and quantity analysis are shared with stakeholders through KM products, reports and virtual sharing platforms like Zoom, WebEx and Skype and the Power BI. The Water Fund has intensified the use of various social media platforms, including Twitter and Facebook to communicate project activities. The project is using Short Message Service (SMS) platform covering 44,000 farmers to communicate area-specific conservation and meteorological messages, water pan liners and guidelines on their installation. In addition, information is shared through the Water Funds for Africa Network platform. Through this platform, the Water Fund has provided trainings on the feasibility and design of Water Funds, and shared best practices and learnings from other existing Water Funds.

## 6.6 Gender Concerns

- The project has a strong gender mainstreaming strategy across its components and activities guided by the gender equality poverty strategy and gender action plan. The project has in place a gender action plan that stipulates the activities and strategy to achieve gender equity. UNTWF project has impressively prioritised gender empowerment as a critical way to improve the quality and quantity of water in the catchment as well communities' livelihoods. As such, the fund introduced techniques in water storage and irrigation, improved fodder, and agroforestry to try and solve issues affecting women and youth.

- The water fund guided by its gender equality and poverty strategy has provided an extended subsidy to women, the poor, and the elderly for them to access assets such as water pans, drip kits, and biogas. The female-headed household, poor and elderly benefit with 50% of subsidy for the three labor/time-saving technologies. The provision of biogas has provided a clean cooking energy interface that is critical to women's health.

- The UTNWF has also provided various capacity building for youth and women on group dynamics, livelihood improvement projects, various soil and water conservation technologies, record keeping, and leadership. To strengthen women's voices in conservation, the project has ensured women's leadership at various levels of project management. This is seen in the BoM where the current chair is a woman.

# 7. Conclusions

- The UTNWF project design was robust and comprehensive, with clear objectives that are relevant to the mandate of the Ministry of Environment and Forestry (MoEF). Lessons learned from relevant IFAD-assisted projects on agriculture and natural resources management, ecosystem restoration and related activities in the Upper Tana catchment provided rich contextual and technical inputs to the UTNWF project.

- The Upper Tana-Nairobi Water Fund (UTNWF) is strongly aligned to important national and county development plans, strategies, and policies. The strong alignment to the policy environment has allowed the UTNWF project to strategically position itself with the government, private sector, and targeted counties in order to achieve the project’s goal.

- There is strong alignment with IFAD's relevant policies and contributes to GEF’s FSIAP overall objective: to support countries in target geographies for integrating priorities to safeguard and maintain ecosystem services into investments improving smallholder agriculture and food value chains.

- UTNWF objectives were largely relevant to the needs of the rural poor and addressed challenges of low agricultural production caused by water shortages, soil erosion, soil degradation and climate change. The design was deliberate in its focus on women and youth. More targeted support towards youth would be required to address their underlying constraints of challenges with accessing markets, access to land and limited networking and linkages with the private sector.

- The financial performance of the project is considered highly satisfactory and there is a broad consensus that the project was cost effective. The GEF/IFAD contribution of US$7,201,835 was disbursed and fully absorbed to support the project implementation. Co-financing by stakeholders was met or exceeded and the only contribution below the target is the endowment capitalization. Farmers as beneficiaries contributed US$ 1.427million against a target of US$ 1.5 million (US$ 1.23 million in-kind and US$ 0.143 million in cash). The NGOs and Counties contributed US$ 15.492 million against a target of US$ 11.9 million. TNC contributed US$ 3.885 million against a target of US$ 3 million and the private sector support at end of December 2022 was US$ 1.3 million for activities and endowment capitalization.

- The Water Fund is now registered as a charitable trust and fully operational with a Board of Trustees (BoT), Board of Management (BoM), Counties Advisory Committee (CAC) and staff. Some policies and strategies now refer to the water fund as an incentive model and at the close of the project, the County Advisory Committee had finalized four policies for review.

- The project successfully implemented diverse interventions that promote climate-resilient agricultural production systems, agroforestry, wetlands protection and restoration, protection/conservation of riparian zones, biogas generation and other cash crop interventions such as avocado production. Rainwater harvesting (water pans, and in-situ through terraces, grass strips etc) and water use efficiency (drip irrigation) to improve productivity per unit of land and off-season farming (plus crops diversification) were also promoted.

- The Area (ha) influenced to adopt SLM had a significant but limited achievement which stood at 35 % at completion. The endline survey noted that for example, some riparian conservation activities such as creation of buffer zones between the edge of the watercourse and the cultivated area had slow adoption. There is certainly some encroachment despite all the sensitization and training on the need for buffer zones mainly due to the small average land size ownership constraints that farmers face.

- Farmers adopting SLM measures were reported to have registered improved production and productivity due to better water and nutrient retention. Endline data showed that households had adequate fodder for their livestock through growing, collecting or buying. The endline survey recorded a significant increase in the proportion of households accessing fodder from 57 % at baseline to 74 % at endline. There were significant improvements in water quantity observed.

- The project had a robust and detailed high-quality monitoring and evaluation plan for the UTNWF.

- The project had a good overall sustainability strategy at the water fund level, but this strategy was not explicit or clearly defined at the community and farmer levels. As noted already, there are still challenges around market linkages, commercialization of some enterprises such as avocadoes as well as value addition that will need to be supported. The project developed memorandum of understandings (MOUs) and joint plans with clear annual workplan and budgets with each county. These agreements however did not provide a clear exit strategy on how the counties will support these interventions after the lapse of the MoUs. The project has seamlessly transitioned into a long-term programme with Water Fund Trust and its stakeholders e.g. Counties, WRA, KWS, KFS etc continuing as partners into the long-term. This is unique and different from traditional end of project hand overs.

- TNC, the Board of Trustees (BoT) and BoM consists of a comprehensive technical skill set that aids in providing sound leadership and guidance regarding the policy, financial, legal and technical aspects of the project. These governance structures are comprised of individuals who are dedicated and passionate about the Water Fund and the project’s deliverables. The project’s sound implementation arrangements contributed to the greater achievement of results.

- Technology partners and technical government departments were instrumental in providing technical guidance  and  strengthening  the  delivery  of  the project. However, it has been difficult to assess objectively the effectiveness of the various partnerships with a view to determine what worked well and lessons that can be learnt and taken up by the Water Fund Trust because some play an oversight role under a committee of the BoM. Hence presenting some conflict of interest issues even if it is one person particularly if there are no mechanisms in place on how to manage this.

# 8. Recommendations

- The Terminal Evaluation Report recommendations are presented in the table below.

| Thematic area | Recommendation | Responsibility |
| --- | --- | --- |
| Capitalization of the Endowment Fund | - Beyond the private sector, explore alternative strategies of capitalization of the fund focusing on the public sector which should be targeted at channeling funds generated from conservation levies or tariffs, towards Water Fund initiatives. The possibility of advocating that the main funding for conservation comes from the government and should be established by law could be pursued with the Ministry of Environment and Forestry as well as the Private Sector. - Generate advocacy tools utilizing the evidence generated under component 3 on the impact of the project and be used for policy dialogues | TNC, UTNWF, public and private sector partners |
| Increase the adoption of SLM and INRM activities | - Strengthen the capacities of Water Resources User Associations (WRUAs) and use them as entry points for the promotion of SLM and INRM interventions - Strengthen linkages with other similar projects in targeted counties by working closely with the County Agriculture Sector Steering Committee (CASCOM) - As a learning point for the Water Fund, the memorandum of understandings (MOUs) and joint plans developed with each county should have a clear pathway of transition of interventions through the County Integrated Development Plans (CIDPs). | TNC, UTNWF, public and private sector partners IFAD |
| Water quality and water quantity assessments | - Strengthen the integration of water quality and water quantity assessments in determining environmental flow requirements for rivers and environmental watering requirements for wetlands. - This will require greater interaction between the Nairobi City Water and Sewerage Company (NCWSC) and WRA and other water service providers through integrated planning and analysis in order to generate data useful for effective water management plans. | NCWSC and WRA |
| Document lessons learnt generated by the project | - Commission a lesson learnt study that will systematically consolidate, and document clear lessons in terms of what worked and what did not. This information is essential in the upscaling of the water fund model in Kenya as well as in Africa | IFAD and TNC |
| Targeting | - Increase the targeting of youths and work towards addressing their underlying constraints regarding markets, access to land, limited networking and linkages with the private sector | TNC, UTNWF and public and private sector partners |

# Annex 1: terminal evaluation itinerary

Terminal Evaluation Itinerary:  3th – 11th May 2022.

| Date | Activity | Location | Persons Responsible | Participants |
| --- | --- | --- | --- | --- |
| Tuesday May 3rd 2022 – IFAD team/Consultant in Nairobi |  |  |  |  |
| Wednesday May 4th 2022 – Travel to Nyeri and site Visits in Sagana – Gura subwatershed |  |  |  |  |
| 7.30 – 9.00 am | Travel from Nairobi to Kenol – Golden Palm Hotel - Meet and greet – make one team - Debriefs on the TER program – field and partner meetings | Murang’a | Anthony - UTNWF | Consultant/IFAD/TNC and Ministry Team (Evaluation team) UTNWF Staff |
| 9.00 – 1.00 pm | Travel from Kenol to Naromoru - Visit a farm in Solio – Livelihoods improvement through conservation intervention in head waters of Gura River | Solio Settlement scheme – Village 2 | Anthony - UTNWF | Evaluation team UTNWF Staff Farmers |
| 1.00 – 2.30 pm | Travel to Nyeri town - Book in hotel for the night - Lunch at the hotel | White Rhino - Nyeri | Anthony - UTNWF | All |
| 2.30 – 3.45 pm | Visit one farmer in Mukurweini - Coffee farming and Conservation through Rainforest Alliance certification | On -Site/Physical meeting | George - UTNWF | Evaluation team UTNWF Staff Farmers |
| 4.00 – 5.00 pm | Visit a coffee factory – Linkage of conservation benefits to improved yields, quality and market prices. (Kiawamururu Factory) | On -Site/Physical meeting | George - UTNWF | Evaluation team UTNWF Staff Farmers |
| 5.15 pm | Drive to Nyeri for the night |  | Anthony - UTNWF | ALL |
| Thursday, 5th May – travel to Murang’a and site visits in Maragua sub watershed |  |  |  |  |
| 7.30am – 9.00 am | Travel from Nyeri to Murang’a Appreciate the topography, landuse and landcover change. Tree species diversification, and terracing of steep slopes | Transect drive from Sagana – Gura (upstream) to Maragua (downstream) subwatersheds | Anthony - UTNWWF | Evaluation team UTNWF Staff |
| 9.00am – 10.00am | Strengthening County partnership for sustainability and scale - Meeting with Hon. Mwaniki, Murang’a CEC for Agriculture and Board member UTNWF - Key value chains, irrigation, human capacity etc | On -Site/Physical meeting | Anthony - UTNWF | CEC Murang’a County CEA Murang’a Evaluation team UTNWF staff |
| 10.00 – 11.30 am | Riparian conservation -Scaling - Visit Maragua river RGS and riparian farms | On -Site/Physical meeting | Caroline – CEA Murang’a | Evaluation team WRA - HMA UTNWF Staff |
| 11.30 – 1.00 pm | Commercialisation of Avocado farming - Visit a farmer with avocado orchard | On -Site/Physical meeting | Caroline – CEA Murang’a | Evaluation team Caritas and UTNWF Staff Farmers |
| 1.00pm – 2.00 pm | Lunch at Maragua |  |  |  |
| 2.00 pm – 4.00 pm | Visit community Water Pan for farming: Surface runoff harvesting, SLM, improved food production, and livelihood. Kiangamba water pan | On -Site/Physical meeting | Caroline – CEA Murang’a | Evaluation team Caritas and UTNWF Staff Farmers |
| 4.15 | Travel to Nokras Hotel for the night - Check in - Debrief/feedback over dinner | Nokras Riverine Hotel, Sagana | Anthony - UTNWF | Evaluation team UTNWF Staff |
| Friday, 6th May – Site visits in Thika – Chania sub watershed |  |  |  |  |
| 8.00 – 10.00 am | Visit WRA offices in Murang’a - Overview of sub-regional water quality and quantity monitoring - Partnership with UTNWF – automation and data management - Maturing partnership and Sustainability | On -Site/Physical meeting | John - UTNWF | WRA team Evaluation team UTNWF Staff |
| 10.00 – 12.00 pm | Rehabilitation of Landslide sites - Visit a reclaimed site in Ndunyu Chege – nature based solutions for sustainability and scale | On -Site/Physical meeting | Caroline - CEA Murang’a | Evaluation team UTNWF Staff Farmers |
| 12.00pm – 2.00pm | Youth in conservation for income generation - Visit Kikamara tree nurseries - Certification, commercialisation and strategies for sustainability | On -Site/Physical meeting | Caroline – CEA Murang’a | Kikamara team Evaluation team UTNWF Staff |
| 2.00pm – 3.00pm | Drive to Ndakaini Dam offices and light lunch enroute (Dam Resort an option) | By road | Anthony - UTNWF | All |
| 3.00pm – 4.30pm | Visit NCWSC and debrief on ICT for decision support - Role and participation of NCWSC – founder Trustee - Impacts of conservation on Nairobi Water Supply – reservoir and water treatment (quality and quantity) - Dashboard and decision support tools - Enduring partnership and sustainability | On -Site/Physical meeting | Anthony – UTNWF John - UTNWF | NCWSC team Evaluation team UTNWF Staff |
| 4.30pm – 5.00pm | Wrap up and departure for Nairobi | On -Site/Physical meeting | Team leader - IFAD | Evaluation team UTNWF Staff |
| 7 - 8th May – WEEKEND (Consultant/IFAD drafting report) |  |  |  |  |
| Monday 9th May 2022 – Scheduled meetings |  |  |  |  |
| 10.00 – 12.00 Pm | Meeting with TNC - Overall program implementation and partnership with Ministry - Partnership with IFAD – challenges, lessons and recommendations - Sustainability – transition of Water fund as an independent entity and the future | Physical meeting – TNC Boardroom | Fred – Africa Water funds director | Evaluation team TNC team |
| 3.00 – 4.00 pm | Meeting with Directors (BoM) - Governance – roles and structures in place - Strategic direction of the independent Water fund - Lessons, recommendations for other water funds | Physical meeting (Venue to be confirmed) | Anthony - UTNWF | Evaluation team BOM representatives |
| Tuesday 10th May – Scheduled meetings |  |  |  |  |
|  | Meeting with Ministry technical team - Agenda setting by GEF desk Officer | Physical meeting Ministry Boardroom | IFAD/TNC | Evaluation team Ministry team |
|  | Meeting with Trustees/ED | Physical or Virtual | Anthony - UTNWF | Evaluation team Trustees representatives |
| Wednesday 11th May – Scheduled meetings |  |  |  |  |
|  | Meeting with PS – environment (OFP) - Agenda setting by IFAD | Physical meeting Ministry Boardroom | IFAD/TNC | Evaluation team Ministry team |
|  | Technical Wrap up IFAD team, TNC, MoE&F and Water Fund | Physical or Virtual | Consultant/IFAD | Consultant, IFAD, TNC, MoEF, Water Fund |
| Thursday 13th May 2022: Draft Aide Memoire |  |  |  |  |
|  | Share final AM with TNC/Ministry/UTNWF |  |  | Consultant |

# Annex 2 – project logical framework

| Results Hierarchy | Indicators |  |  |  | Means of Verification |  |  | Assumptions |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Description | Baseline | Mid-term | End line | Source | Frequency | Responsibility |  |
| Goal: The Upper Tana-Nairobi Water Fund (UTNWF) as a Public-Private Partnership increases investments flows for sustainable land management and integrated natural resource management in the upper Tana catchment | 21,000 small holder farmer households with improved food-security, climate change adaptation and resilience capabilities (gender and age disaggregated) (RIMS 1.8.2) | Zero | 30% over BL | 21,000 smallholder households | RIMS/ MPAT surveys | BL MTR End line | PMU | National and county governments supportive of the WF concept |
|  | Number of Tonnes of greenhouse gas emissions (CO2) avoided and/or sequestered (RIMS 2.1.9) | TBD | 5 % reduction | 10% reduction compared to baseline | LDSF surveys | BL MTR End line | PMU/ ICRAF | A large shift to perennial crops among smallholders is viable |
| Development objective: a well-conserved upper Tana River basin with improved water quality and quantity for downstream users (public and private; maintaining regular flows of water throughout the year; enhancing ecosystem | 21,000 smallholder farmer households adopt climate-smart SLM practices (gender and age disaggregated) | Zero | 30% over BL | 100% | LDSF surveys | BL MTR End line | PMU/ ICRAF | Downstream water users (public and private) are interested in supporting upstream SLM and watershed conservation to improve water quality and quantity |
|  | Improved base flow in rivers (M3/sec) | TBD | 10% above BL | 30% above BL | Reports from monitoring stations | BL MTR End line | PMU |  |
|  | Reduced sediment load in river basins in wet season (kg/l/sec) | TBD | 5% reduction | 10% reduction | Water monitoring stations | BL MTR End line | PMU |  |
| Component 1: Water fund platform institutionalized |  |  |  |  |  |  |  |  |
| Outcome 1.1: Multi-stakeholder and multi-scale platform supports policy development, institutional reform, and upscaling of integrated natural resource management (INRM) and sustainable land management (SLM) | Water fund endowment is operational | Zero | WF by-laws legally established | WF Capitalized | Legal documents, bank statements | Midterm, Project end | PMU | Proposed Public Benefits Act supports water fund establishment |
|  | Relevant government policies and strategies refer to the water fund as an incentive model | Zero | ≥ 2 policies and strategies at national/ county levels | ≥ 4 policies and strategies at national/ county levels | Official documentation records | Midterm, Project end | PMU | Policies and strategies open for amendment and addition |
| Outcome 1.2: Policies and incentives support climate smart smallholder agriculture and food value chains in financially viable and sustainable watershed stewardships | Coordinated watershed management policies at county and national levels | Overlapping scales and responsibilities | Input into 3 CIDPs and sectoral strategies | 3 CIDPs coordinated with the WRMA | WRMA records | Midterm, Project end | PMU | Policy and strategy formulation at local, county and national level can be coordinated |
|  | Smallholder people/ individuals/ household members receiving project services/incentives (RIMS 1.8.2) | Zero | 30% of target | 21,000 households | WF implementation partners’ records and disbursement records | Midterm, Project end | PMU | Smallholder households are interested in joining incentive schemes |
| Component 2: Improved upper Tana catchment ecosystems that support livelihoods, food security and economic development |  |  |  |  |  |  |  |  |
| Outcome 2.1: Increased land area, freshwater, and agro-ecosystems under INRM and SLM | Number of hectares of land brought under climate-resilient management | Zero | 30,000 Ha | 100,000 ha | Project reports | Start up, mid-term, project end | PMU | Smallholders are actively supporting INRM and SLM approaches |
|  | Number of individuals provided with technologies that reduce or sequester greenhouse gas emissions (RIMS 1.1.18) | Zero | 7,000 households | 21,000 households | Project reports | Start up, mid-term, project end | PMU | Land-use changes can be facilitated and are accepted |
| Component 3: Robust knowledge management and learning systems implemented to direct UTNWF management and to share lessons both nationally and regionally |  |  |  |  |  |  |  |  |
| Outcome 3.1: Institutions capacitated to monitor Global Environmental Benefits | Global Environmental Benefits monitoring tools and protocols integrated with partner institutions | Zero | ≥ 2 Land Degradation Surveillance Framework (LDSF) surveys updated/ completed. ≥ 10 water monitoring stations upgraded/ operational. WRMA prepared to house water-quality database. | LDSF surveys for at least 5 sub-watersheds updated/ completed. 26 monitoring stations upgraded/ operational. A water-quality database established and integrated into WRMA system. | LDSF reports; Project records | Midterm, Project end | PMU | Institutional processes allow for integration of monitoring protocols |
| Outcome 3.2: Monitoring and assessment framework supports the integration of climate resilience into policy making | Multidimensional Poverty Assessment Tool (MPAT) survey results referenced in county development plans | Zero | 2 MPAT survey references | MPAT survey results referenced in ≥ 1 CIDPs | CIDPs, project reports, M&E records | BL, midterm, and project end | PMU | County development agencies open for new approaches |
| Outcome 3.3: Knowledge management and sharing of lessons learned is facilitated | Information sharing platforms established | Zero | 1 county-level information center | 1 county and 1 national-level info center | Project reports | midterm and project end | PMU | Partner organizations willing to establish and operate information centers |
|  | Number of meetings, conferences, and seminars held at national, regional and international levels where water fund knowledge and learning were shared | Zero | Inputs/ presentations at ≥ 5 meetings at national, regional and international levels | Inputs/ presentations at ≥ 10 meetings at national, regional and international levels | Project reports | midterm and project end | PMU | Opportunities for influencing dialogues present themselves |
|  | Lessons learned out-scaled to at least 2 other catchment areas in Kenya | Zero | Lessons learned for scaling out are being complied | ≥ 2 feasibility studies conducted | Project reports | midterm and project end | PMU | Other water towers and relevant authorities interested and engage in feasibility studies |

# Annex 3 – rating of the utnwf project results

The main dimensions of project performance on which ratings are provided in terminal evaluations are: outcomes, sustainability, quality of monitoring and evaluation, quality of implementation, and quality of execution.

Outcomes (relevance, effectiveness and efficiency)

| Rating | Explanation |
| --- | --- |
| Highly satisfactory (HS) | Level of outcomes achieved clearly exceeds expectations and/or there were no short comings. |
| Satisfactory (S) | Level of outcomes achieved was as expected and/or there were no or minor short comings. |
| Moderately Satisfactory (MS) | Level of outcomes achieved more or less as expected and/or there were moderate short comings. |
| Moderately Unsatisfactory (MU) | Level of outcomes achieved somewhat lower than expected and/or there were significant shortcomings. |
| Unsatisfactory (U) | Level of outcomes achieved substantially lower than expected and/or there were major short comings. |
| Highly Unsatisfactory (HU) | Only a negligible level of outcomes achieved and/or there were severe short comings. |
| Unable to Assess (UA) | The available information does not allow an assessment of the level of outcome achievements. |

Sustainability Ratings

The sustainability will be assessed taking into account the risks related to financial, socio-political, institutional, and environmental sustainability of project outcomes.

| Rating | Explanation |
| --- | --- |
| Likely (L) | There is little or no risks to sustainability |
| Moderately Likely (ML) | There are moderate risks to sustainability |
| Moderately Unlikely (MU) | There are significant risks to sustainability |
| Unlikely (U) | There are severe risks to sustainability |
| Unable to Assess (UA) | Unable to assess the expected incidence and magnitude of risks to sustainability |

Project Monitoring and Evaluation Ratings

Quality of project monitoring and evaluation will be assessed in terms of design  and implementation

| Rating | Explanation |
| --- | --- |
| Highly satisfactory (HS) | There were no short comings and quality of M&E design / implementation exceeded expectations. |
| Satisfactory (S) | There were no or minor short comings and quality of M&E design / implementation meets expectations. |
| Moderately Satisfactory (MS) | There were some short comings and quality of M&E design/implementation more or less meets expectations |
| Moderately Unsatisfactory (MU) | There were significant shortcomings and quality of M&E design / implementation somewhat lower than expected |
| Unsatisfactory (U) | There were major short comings and quality of M&E design/implementation substantially lower than expected |
| Highly Unsatisfactory (HU) | There were severe short comings in M&E design/ implementation |
| Unable to Assess (UA) | The available information does not allow an assessment of the quality of M&E design / implementation |

Implementation and Execution Rating

Quality of implementation and of execution will be rated separately. Quality of implementation pertains to the role and responsibilities discharged by the GEF Agencies that have direct access to GEF resources. Quality of Execution pertains to the roles and responsibilities discharged by the country or regional counterparts that received GEF funds from the GEF Agencies and executed the funded activities on ground. The performance will be rated on a six-point scale.

| Rating | Explanation |
| --- | --- |
| Highly satisfactory (HS) | There were no short comings and quality of implementation / execution exceeded expectations |
| Satisfactory (S) | There were no or minor short comings and quality of implementation / execution meets expectations |
| Moderately Satisfactory (MS) | There were some short comings and quality of implementation / execution more or less meets expectations |
| Moderately Unsatisfactory (MU) | There were significant shortcomings and quality of implementation / execution somewhat lower than expected |
| Unsatisfactory (U) | There were major short comings and quality of implementation / execution substantially lower than expected |
| Highly Unsatisfactory (HU) | There were severe short comings in quality of implementation / execution |
| Unable to Assess (UA) | The available information does not allow an assessment of the quality of implementation / execution |

Source: Guidelines for GEF Agencies in Conducting Terminal Evaluation for Full-sized Projects – Annex 2. https://www.gefieo.org/sites/default/files/documents/reports/gef-guidelines-te-fsp-2017.pdf accessed on 9 May 2022.

Annex 4. Water Funds sites and status across the African continent.

# Annex 5. Bibliography

- Additional Qualitative Information on Changes Observed Following the TNC-UTNWF Project, Central Kenya- FINAL REPORT; DECEMBER 2021

- FSIAP GEF IAPIP Evaluation, Kenya Case Study Final Report, 2021.

- Gender action plan (GAP)For Upper Tana Nairobi Water fund, December 2021

- IFAD Project Supervision Report, Sept 2020.pdf

- IFAD, 2013. Republic of Kenya Country strategic opportunities programme (2013-2018). https://webapps.ifad.org/members/eb/109/docs/EB-2013-109-R-14.pdf

- IFAD, 2018. IFAD Strategy and Action Plan on Environment and Climate Change 2019-2025. https://webapps.ifad.org/members/eb/125/docs/EB-2018-125-R-12.pdf

- IFAD, 2019. Republic of Kenya Country strategic opportunities programme (2020-2025). https://webapps.ifad.org/members/eb/128/docs/EB-2019-128-R-19.pdf

- IFAD, 2021. Aide Memoire, Final July 26, 2021.

- Kenya Upper Tana Catchment Natural Resource Management Project Supervision Report, 28 March to 14 April 2022

- Mati, B.M.; Sijali, I.V.; Ngeera, K.A. 2022. Investigating pathways for agricultural innovation at scale: Case studies from Kenya. Colombo, Sri Lanka: Commission on Sustainable Agriculture Intensification. 46p.

- NEMA (2011). State of the Environment and Outlook Report for Kenya 2010. National Environment Management Authority (NEMA), Nairobi

- Project Supervision Report August 30, 2021, revised (002).docx final.docx

- Republic of Kenya (2008). Vision 2030.

- Republic of Kenya, 2020. State of the Environment Report. https://www.nema.go.ke/images/Docs/EIA_1840-1849/Kenya%20State%20of%20Environment%20Report%202019-2021%20final-min.pdf

- The Constitution of Kenya (2010). The Government of the Republic of Kenya.

- The UTNWF End of Project Report, 2021

- TNC 2015. Upper Tana-Nairobi Water Fund Business Case. Available at https://www.nature.org/content/dam/tnc/nature/en/documents/Nairobi-Water-Fund-Business-Case_FINAL.pdf

- UNTWF Gender and Poverty Reduction Strategy, 2018

- UNTWF Position Paper on Gender and youth empowerment after 5 years of implementation, June 24, 2021.

- Upper Tana-Nairobi Water Fund Strategic Plan 2022–2026. https://nairobiwaterfund.org/wp-content/uploads/2021/12/UTNWF-Strategic-Plan_Final.pdf

- UTNWF 2021 Annual Progress Report (ver. 3).docx

- UTNWF End of Project Report, 2022

- UTNWF End of Project Report, October 2016 – December 2021

- UTNWF IFAD 2021 Half Year Progress Report version 2.pdf

- UTNWF IFAD Supervision Mission Report, August 30, 2021

- UTNWF IFAD supervision mission report, September 2020

- UTNWF Position Paper on Contribution of Upper Tana Nairobi water fund to key value chains and Market linkage in the catchment, June 20, 2021.

- UTNWF Project Implementation Report, 2020.

- UTNWF Project progress report July 2018 -June 2019_Final Ver.docx

- UTNWF Trust -Position Paper on Lessons learned and scaling up after 5 years of implementation, January 6, 2022.

- World Bank, 2022. Kenya Economic Update, June 2022 edition No.25. Aiming High: Securing Education to sustain the Recovery. https://documents1.worldbank.org/curated/en/099430006062288934/pdf/P17496106873620ce0a9f1073727d1c7d56.pdf

# Annex 6. terms of reference

INTRODUCTION

- The proposed project terminal evaluation for the Food-IAP: Establishment of the Upper Tana Nairobi Water Fund (UTNWF) (9139) will be undertaken jointly by IFAD, Ministry of Environment and Forestry (MoEF) and the Nature Conservancy (TNC). The main purpose of the TER will be to report on the extent to which the project has met its goal, development objectives and results as anticipated at design, and how the achievements/best practices and lessons learned can inform future programming of similar projects. The process should also help define an appropriate hand-over or post-project strategy to the project and relevant stakeholders .

- The project terminal evaluation will take place from 2-31 December 2021 (30 working days). The terminal evaluation process shall be guided by the methodological framework set out in IFAD’s Project Completion Review Guidelines as well as the GEF terminal evaluation guidelines. These ToRs describe the detailed objectives, timelines and deliverables of the completion review/terminal evaluation mission. In-country, the work of the TER team will be facilitated by TNC, under the overall supervision of the Regional Climate and Environment Specialist.

PROJECT CONTEXT

- PROJECT, GOAL, OBJECTIVES AND EXPECTED OUTCOMES:

INTRODUCTION: The Upper Tana Nairobi Water Fund Project (UTNWFP) is a 5-year Public Private Partnership (PPP) funded by the Global Environment Facility (GEF) through IFAD and implemented by The Nature Conservancy (TNC). The project is being implemented in four Counties (Murang’a, Nyeri, Laikipia and Nyandarua) which cover 17,000 km2 with a population of about 5.3 million inhabitants. The project became effective in October 2016 with an overall financing of 33.6M USD of which a) 7.2M USD grant from the GEF-IAP; b) USD 3M in-kind contribution by TNC to support administrative/project management costs; c) USD 1.5M as in-kind contribution from project beneficiaries; d) USD 11.9 M as in-kind contribution from local NGOs and county governments; e) USD 10M private sector pledges towards capitalisation of the Water Fund. The project's completion date is 31st December 2021 and the grant closing date is 30th June 2022.

GOAL: The goal of the UTNWF project is to as a Public-Private-Partnership, increase investment flows for sustainable land management and integrated natural resource management in the Upper Tana catchment.

DEVELOPMENT OBJECTIVE: A well-conserved Upper Tana River basin with improved water quality and quantity for downstream users (public and private); maintaining regular flows of water throughout the year; enhancing ecosystem services, specifically food security, freshwater and terrestrial biodiversity, and improving human well-being and quality of life for upstream local communities.

RATIONALE: Forests and wetlands in the Upper Tana play an important role in maintaining water quality and quantity, providing areas where runoff water and sediment can be stored and filtered naturally. However, since the 1970s, forests on steep hillsides and areas of wetlands have been converted to agriculture. As a result, sedimentation is becoming a serious problem, reducing the capacity of reservoirs and increasing the cost for water treatment. Today, 60% of Nairobi’s residents are water insecure, while 95% of the water used and consumed in Nairobi is coming from the Upper Tana catchment. The challenges to water security will likely grow as climate change brings increasingly unpredictable rainfall, equally challenging the resilience and food security of upstream smallholder farming systems.

The concept of water funds is based on the principle that it is cheaper to prevent some water problems at the source than it is to address them further downstream. Investments in green infrastructure using natural systems and its services to trap sediment and regulate water often provide a more cost-effective approach than relying solely on grey infrastructure such as reservoirs and treatment systems. Water funds have been successfully implemented elsewhere in the world to help secure the water quality and supply of major cities including New York, Quito, Rio de Janeiro, and Lima, among others. The UTNWF is the first of its kind in Africa. The UTNWF as a public-private-partnership of donors, and major water consumers ‘at the tap’ are expected to contribute to the initial endowment of the Water Fund (WF) to support water and soil conservation measures ‘at the top’. These measures benefit local farmers’ livelihoods, food security and resilience through increasing agricultural yields and introducing climate-smart agricultural techniques, and thus reducing soil erosion that is so damaging both to crop production and to downstream water quality and supply.

PROJECT COMPONENTS: The project is implemented through the following three components:

Component 1: Water Fund Management Platform institutionalised. The project will work closely with private and public partner organisations to establish the Water Fund (WF) as a Charitable Trust registered under Kenyan law and governed by a Board of Trustees. The Board of Trustees will manage the overall operations of the WF, which will have a set of advisory committees at both national and at county levels, to allow for good collaboration between governmental and WF activities and the uptake of lessons and practices into policy and catchment management processes, and a Technical Secretariat, responsible for the day-to-day management of its activities. Upon legal registration of the WF, the financial management system will be established to allow for the capitalisation of the endowment through funds from its public, private and international partners.

Component 2: Improved Upper Tana catchment ecosystems that support livelihoods, food security and economic development. The aim of investment flows for SLM and INRM to the catchment area, by the UTNWF project - and increasingly by the WF itself to sustain these investments - is to foster adaptation and to increase the resilience of the local population through improved food production, household incomes and diversified development options and livelihoods, with due reference and disaggregation of support and results by gender and age.

Component 3: Robust knowledge management and learning systems implemented to direct UTNWF management and share lessons both nationally and regionally. Strong emphasis will be placed on M&E frameworks to a) support WF decision making and allowing for an adaptive management approach to the targeted incentive schemes, and b) to allow for upscaling, policy integration and replication of lessons learned as quickly as feasible.

PROJECT OUTCOMES:

(i) Multi-stakeholder and multi-scale platform supports policy development, institutional reform and upscaling of INRM;

(ii) Policies and incentives support climate smart smallholder agriculture and food value chains in financially viable and sustainable watershed stewardships;

(iii) Increased land area, freshwater, and agro-ecosystems under INRM and SLM;

(iv) Institutions capacitated to monitor Global Environmental Benefits (GEBs);

(v) M&A framework supports the integration of climate resilience into policy making;

(vi) Knowledge management and sharing of lessons learned is facilitated.

PROJECT TARGET AREA AND TARGET GROUP: The is implemented in 4 counties (Muranga, Nyeri, Laikipia and Nyandarua).  UTNWFP works with public and private sector partners to establish the Water Fund as a sustainable financing mechanism to support sustainable land management and integrated natural resource management approaches in the Upper Tana catchment. Through its network of public agencies, NGO and CBO, the Project will support at least 21,000 smallholder households, i.e. about 100,000 individuals in the Upper Tana catchment to adopt climate-smart sustainable land management practices, with the aim to increase food security and climate adaptation potential at household level, to stabilise and restore ecosystem services of the targeted area and to improve water quality and quantity for both upstream and downstream water users.

IMPLEMENTING ARRANGEMENTS: IFAD is the GEF Implementing Agency for the project while TNC is the executing agency. TNC is supported by several implementation partners, including the National Museums of Kenya, Water Resources Management Authority and Kenya Forest Services, through a direct grant agreement between IFAD and TNC, with disclosure to the National Treasury. TNC is in charge of day-to-day project management, together with a broad array of implementation partners, including the Public and Private Sector Partners that constitute the Board of Trustees of the Water Fund, Research Institutions and at least three County Governments. The Project Steering Committee and a Technical and Scientific Committee with appropriate representation from technical partners and both national and county levels ensure alignment of the Project to ongoing programmes and activities and Public and Private Sector partners/members of the UTNWF.

The project management unit (PMU) includes key staff for project management and administration, work plan preparation and implementation and financial control. The unit comprises of the GEF Project Manager, a Monitoring and Evaluation Officer, a Field Conservation Coordinator, three Field Extension Assistants. It is envisaged that with the full establishment of the Water Fund and increasing achievement of project results, the responsibilities and functions of the PMU will be gradually transferred to the Water Fund, taking over full responsibility toward the end of the 5 year project cycle.

BUDGET AND TIMELINES: The project became effective in October 2016 with an overall financing of 33.6M USD of which a) 7.2M USD grant from the GEF-IAP; b) USD 3M in-kind contribution by TNC to support administrative/project management costs; c) USD 1.5M as in-kind contribution from project beneficiaries; d) USD 11.9 M as in-kind contribution from local NGOs and county governments; e) USD 10M private sector pledges towards capitalisation of the Water Fund. The project's completion date is 31st December 2021 and the grant closing date is 30th June 2022.

OBJECTIVE

- The overall objective of the terminal evaluation is to assess and document overall project implementation performance and the results achieved, and to draw relevant lessons for the improvement of GEF projects designs and implementation. This process calls for an informed reflection on the relevance, effectiveness, efficiency and sustainability of project interventions.

- More precisely, the detailed objectives of the terminal evaluation process include the following:

- To assess the effectiveness of project implementation, or the extent to which project objectives were met, and to document the immediate results and impacts of project interventions.

- To assess the relevance of project interventions at the time of project design and in today’s context.

- To review the project costs and benefits and the efficiency of the overall project implementation process, including IFAD’s, TNC’s and partners’ performance.

- To assess the prospects of sustainability of project benefits beyond project completion.

- To generate and document useful lessons from implementation that will help improve future programming and designs.

- To identify any potential for the replication or up-scaling of best project practices.

- To evaluate the relevance of the implemented strategies and approaches as well as their contribution to reaching the development objectives pursued by the project.

- Appreciate the implementation context and modalities, including those relating to the interactions between the project, the beneficiaries and the implementing partners.

- To document and demonstrate the applicability of the proposed interventions and the WF platform as model in similar contexts.

METHODOLOGY

- The methodology of the TER mission will include: (i) an in-depth analysis of the existing project documentation; (ii) field visits and discussions with all stakeholders (beneficiaries; national partners; service providers; platforms; etc.) on all the activities implemented by the project; (iii) in depth consultations with the project team, partners, iFAD, MoEF, TNC and key stakeholders; and (iv) sharing of main conclusions and recommendations with the project team and other partners involved with the project implementation

- The evaluation will use a Theory of change (ToC) approach to help assess project effectiveness, likelihood of impact, sustainability and scaling up. The ToC of a project depicts the causal pathways from project outputs (goods and services delivered by the project) through outcomes (changes resulting from the use made by key stakeholders of project outputs) towards impact (long term changes in environmental benefits and living conditions). A ToC also depicts any intermediate changes required between project outcomes and impact, called ‘intermediate states’. The ToC further defines the external factors that influence change along the major pathways; i.e. factors that affect whether one result can lead to the next. These external factors are either drivers (when the project has a certain level of control) or assumptions (when the project has no control). The ToC also clearly identifies the main stakeholders involved in the change processes. The evaluation will determine the need to reconstruct the ToC of the project based on a review of project documentation and stakeholder interviews. If reconstructed, the evaluator will be expected to discuss the reconstructed ToC with the stakeholders during evaluation missions and/or interviews in order to ascertain the causal pathways identified and the validity of impact drivers and assumptions described in the ToC. This exercise will also enable the consultant to address some of the key evaluation questions and make adjustments to the ToC as appropriate (the ToC of the intervention may have been modified / adapted from the original design during project implementation). The results framework and its adequacy in addressing project deliverables will also be evaluated and feed back provided.

- The mission will use a mix of quantitative and qualitative tools in order to form an informed judgement on overall project performance and results. For transparency and accuracy purposes, it is important that the consultation with project stakeholders shall be as large and inclusive as possible and the list of persons to be met by the mission will require careful consideration.

- Primary sources of information will include project reports and documents (supervision reports, MTR report, progress reports, AWPB, GEF PIRs etc.), M&E and MIS data (including RIMS data), any surveys or specific studies undertaken by the project (MPAT/outcome/impact/end term survey), KM products, PMU and service providers’ records and the records of the groups supported by the project. These sources will be used extensively in order to generate quantitative information on project results or estimate project efficiency.

- In addition to primary sources of information, the mission will collect relevant data from secondary sources, such as national and local statistics, other donors’ statistics, the civil society, private sector entities. These will be used mainly to breach information gaps on certain issues or to cross-examine the data generated from other sources.

- In case sufficient or reliable impact data is not available, the mission should undertake a mini-survey while in the field in order to collect basic information from a small sample of respondents (to be selected using the most appropriate sampling method). To this end, a questionnaire shall be developed before the field work starts.

- In addition and in order to gather an in-depth understanding on certain issues, collect stakeholders’ feedback and generate important insights, the mission will use a variety of qualitative tools, such as key informants’ interviews, focus group discussions and rapid case studies. Before starting the field work, it is important that the mission dedicates sufficient time to prepare the necessary interview guides.

- The method of direct observation will also be used by the mission. A large sample of project sites, or locations where project activities took place, will thus be visited in order to collect impressions and feelings, verify that reported interventions took place, confirm that they met expected quality standards and beneficiaries’ needs, or to take note of the external context of project intervention. Selection of project sites will require careful consideration in order to avoid biases.

- If found useful, the organization of a stakeholders’ workshop either before the field work starts or towards the end of the mission, can be envisaged in order to collect initial feedback on project performance or on initial mission’s findings.

TIME FRAME AND DELIVERABLES

- The evaluation will take place from 2-31 December 2021 (25 days).

- The mission will prepare a Project Terminal Evaluation report (TER) following the outline presented in annex 1 of the present ToRs. A first document (aide-memoire) will be presented at the end of the field mission. The preparation of the technical documents by the consultant (s) will be homebased after the field mission. The first draft TER will be prepared shortly after the end of the terminal evaluation mission and submitted electronically by the consultant to the RCES and the CD, no later than 13 December 2021.

- The draft TER will be circulated among main stakeholders for review and consolidated, written comments will be sent to the consultant (s) no later than 24 December 2021 by the RCES and TNC.

- The Independent Evaluation Office (IOE) of IFAD will review the draft evaluation report and provide comments. The consultants will revise the report and provide a response to comments to IOE in the shape of a revised report using track changes, and a table presenting how each comment has been addressed in the report or explaining why a comment has not been addressed. The final report should be submitted to IFAD on or by 31st December 2021.

REQUIRED SKILLS AND EXPERIENCE

EDUCATION:

A Master’s degree in Climate Change, Natural Resource Management, Environmental

Management/Science, Environmental Law, Development Studies, or other closely related field

EXPERIENCE:

- Minimum of 7 years of professional experience in the technical areas of the project, with demonstrated understanding of national policies and practice of Climate Change and Adaptation;

  - Recent experience with evaluating projects with result-based monitoring and evaluation methodologies and in applying SMART indicators validating baseline scenarios;

  - Knowledge and experience in evaluating development projects, specific experience in IFAD and GEF

project Evaluation;

  - Competence in adaptive management, as applied to Climate Change Adaptation focal area;

  - Experience in working with GEF or GEF – evaluations;

  - An understanding of issues related to gender and GEF focal areas; experience in gender sensitive

evaluation and analysis;

  - Excellent analytical and communication skills;

Language

• Fluency in written and spoken English with exceptional writing, presentation and communication skills;

SPECIFIC TASKS OF THE CONSULTANT (S)

- ___________________

Annex 1. Main performance evaluation questions

- The project terminal evaluation team will answer each of the following detailed questions, grouped according to the criteria to be used in the assessment.

- Project relevance

- Broadly speaking, the mission will assess the extent to which project objectives were consistent with IFAD and GEF’s mandate, with the national policies relating to environment and natural resources management; to climate change adaptation and to biodiversity; with GEF focal areas and operational strategies identified at design stage. More precisely, the mission will answer each of the following detailed questions:

- Did the project design focus on, and were objectives consistent with, the needs and priorities of the rural poor? Was the design process participatory and did it take into account the needs, potential, livelihoods, asset bases and development opportunities of the rural poor at the time of project design? Are these characteristics, constraints and opportunities still the same today?

- Were the approaches promoted consistent Vis à Vis the socio-politico-economic conditions at the time of project design and Vis à Vis prevailing environmental and climate conditions? Were project objectives, approaches and activities consistent with GEF’s and IFAD’s objectives of increasing the assets and incomes of poor rural households, and improving their food security?

- Were project objectives realistic and consistent with national development plans, poverty reduction strategies, agriculture and rural development strategies and other sectoral priorities? In particular, was the project design aligned with [the national policies relating to the themes addressed by the project (in particular policies and strategies relating to environment, natural resource management, climate and biodiversity)]? Are these documents still relevant today or were there important changes in the policy context?

- Were the project objectives consistent with GEF’s and IFAD’s mandate, including policies e.g. on targeting, gender and youth etc?

- Have the objectives and implementation of the project respected the focal areas and operational GEF strategies identified at design stage. Has the project, during its implementation, taken into account the GEF’s priorities in terms of targeting, environment, etc.

- Did the Project Design Document include a well-defined, clearly articulated Logframe or Results’ Framework? Were all identified activities and outputs consistent, and commensurate, for the attainment of proposed goal and objectives? Were external risks (or assumptions) clearly identified? Were the proposed indicators relevant and adequate to monitor project implementation and results?

- Which GEBs did the project address? Were they addressed adequately and achievements aligned with what was anticipated at design?

- Were the initial implementation arrangements well defined and adequate to ensure a smooth, cost-efficient project implementation? Were there any major changes in these arrangements, and if so, were these changes appropriate and timely?

- Were there major changes in the external project environment (e.g. policies, socio-economic conditions, political changes, crisis, etc.) since the project was designed and implementation started? Were project objectives adjusted to reflect changing circumstances during implementation? Are initial (or revised) project objectives still valid?

- What were the main factors that contributed to a positive, or less positive, assessment of project relevance?

- Aspects related to project relevance will be rated on a six-point rating scale from highly satisfactory to highly unsatisfactory. The rating will also be indicated in a table annexed to the report justifying a rating from: highly satisfactory (HS), satisfactory (S), moderately satisfactory (MS), moderately unsatisfactory (MU), unsatisfactory (U), and highly unsatisfactory (HU). (see annex 2)

- Project effectiveness

- The mission will assess the extent to which all project’s objectives were achieved in both quantitative and qualitative terms. This will involve the careful description of the main activities undertaken by the project since its start, as well as a thorough analysis of the results achieved at the output, outcome and impact levels. Variations between initial and actual targets will be highlighted and the external factors that had a bearing on project effectiveness will be explained. More precisely, the mission will answer the following questions:

- Were all activities implemented as planned? If not, what were the reasons? Were all expected outputs achieved in quantitative and qualitative terms? Did they lead to the intended outcomes and were those properly measured and documented? Are there significant discrepancies between original targets and actual achievements, and if so, what are the reasons?

- Did the project achieve its broad and detailed objectives?

- Was project implementation well monitored? Are all results at all levels properly measured, quantified and documented? Is this information reliable?

- Did all results meet expected quality standards?  If not, what were the problems?

- Were all results achieved within the original timeframe and budget?

- Did the project provide all expected benefits to all intended target groups? Do results and achievements adequately fulfil the needs of these intended target groups?

- What are the external factors that have facilitated, or constrained, output delivery and the achievement of project objectives?

- What factors in project design and implementation account the most for the estimated results in terms of effectiveness?

- Aspects related to effectiveness will be rated on a six-point rating scale from highly satisfactory to highly unsatisfactory. The rating will also be indicated in a table annexed to the report justifying a rating from: highly satisfactory (HS), satisfactory (S), moderately satisfactory (MS), moderately unsatisfactory (MU), unsatisfactory (U), and highly unsatisfactory (HU). (see annex 2)

- Project efficiency

- The mission will assess how economically project inputs and resources (funds, expertise, time, etc.) were c	converted into results. This complex analysis will involve a review of the following aspects:

Resources’ use:

- What were the main expenditure patterns? Were original financial and budgetary resources spent as initially anticipated? Were there deviations from original cost estimates and, if so, what were the reasons? Was the budget significantly amended in the course of implementation?

- Were there timely and adequate financing contributions from all project financiers, including in-kind contributions from beneficiaries?

- For the resources spent, was the number (and quality) of outputs optimal? Could the project have produced more with the same resources, or the same results with less money? Could other approaches have produced results more efficiently in terms of costs, time and resources?

Quality of project management:

- How well did the PMU coordinate and manage project activities? Were implementation timetables adequately met? Was project management responsive to changes in the environment or the recommendations made during supervision missions of by the Project Steering Committee? Was the [PMU] adequately staffed with motivated staff members? How useful were the various project management tools (AWPB, Procurement Plan, and M&E Plan) and the Management Information System (MIS) developed during implementation? Were these tools properly used by project management?

- Were there appropriate arrangements in place for sound financial management, flow of funds, financial record keeping and the timely preparation of financial reports? Were there any issues?

- Has the M&E system been conceived in a relevant manner; has a baseline study been planned and conducted; did the indicators respect the “SMART” criteria (Specific, Measurable, Achievable; Realistic and Timely); how efficient was the project M&E or MIS systems in providing reliable, timely information on output delivery, outcomes and impact? Was M&E information adequately analysed and used by project management for planning and decision-making purposes; has the M&E system been sufficiently budgeted at project design and has the M&E system been adequately financed during implementation? (An M&E system rating matrix will be provided in annex of the TER – see annex 2).

- Has the project implemented an M&E system that enables the project’s impact evaluation on the long term?

- Government performance:

- Was the Project Steering Committee useful and proactive to help resolve problems and guide project implementation?

- Aspects related to Government performance will be rated on a six-point rating scale from highly satisfactory to highly unsatisfactory. The rating will also be indicated in a table annexed to the report justifying a rating from: highly satisfactory (HS), satisfactory (S), moderately satisfactory (MS), moderately unsatisfactory (MU), unsatisfactory (U), and highly unsatisfactory (HU). (see annex 4)

Quality of IFAD supervision and implementation support:

- To what extent did the services and support provided by IFAD ensure a sound project design and an efficient project implementation? Did IFAD mobilize the adequate technical expertise and resources in project design and implementation?

- Did IFAD provide an adequate support through direct supervision and/or country presence? Were supervision missions useful and timely? Did IFAD ensure pro-active problem identification, follow-up and resolution?

- How efficient was IFAD in handling loan administration, procurement reviews and AWPB reviews? Were there any delays in funds’ transfers?

- Aspects related to IFAD performance will be rated on a six-point rating scale from highly satisfactory to highly unsatisfactory. The rating will also be indicated in a table annexed to the report justifying a rating from: highly satisfactory (HS), satisfactory (S), moderately satisfactory (MS), moderately unsatisfactory (MU), unsatisfactory (U), and highly unsatisfactory (HU). (see annex 2)

Cost-benefits analysis (this analysis is sufficient in the case of GEF projects: it is not necessary to provide a complete economic and financial analysis):

- For each of the main project investments, what were: (a) the actual costs and value of inputs mobilized (including capital costs, operation and maintenance costs, labour costs, taxes); (b) the estimated economic benefits (including revenues from sales, incomes, value of self-consumed production); and (c) the estimated social benefits?

- What is the cost ratio of inputs to outputs and is it comparable to local, national or regional benchmarks? What are the grant costs per beneficiary? What are the mission’s conclusions with regard to this costs-benefits analysis? What are the main internal or external factors that may have had a negative or positive impact on costs or benefits?

- Where available, how does the actual project internal rate of return (IRR) compare with the estimated IRR calculated during project design?

- IFAD Performance

- Was IFAD proactively engaged in policy dialogue activities at different levels in order to ensure, inter alia, the replication and scaling-up of pro-poor innovations? Was IFAD active in creating effective partnerships?

The aspects related to project efficiency will also be evaluated in the appendix, in a table justifying a rating from: highly satisfactory (HS), satisfactory (S), moderately satisfactory (MS), moderately unsatisfactory (MU), unsatisfactory (U), and highly unsatisfactory (HU). (See annex 2)

- Project impacts

- The impact of project interventions will be carefully presented in quantitative and qualitative terms, using the GEF and IFAD’s impact classification. Aspects related to project impacts should also be rated on a six-point rating scale from highly satisfactory to highly unsatisfactory. The rating will also be indicated in a table annexed to the report justifying a rating from: highly satisfactory (HS), satisfactory (S), moderately satisfactory (MS), moderately unsatisfactory (MU), unsatisfactory (U), and highly unsatisfactory (HU). (see annex 4)

- The consultant (s) will examine in particular the following questions:

- Households’ assets: Did the project contribute to positive changes in households’ assets? Did the composition of incomes change or was there a diversification in livelihoods’ means. Did the project improve ownership, or security of access, to land, water or productive resources? Were there positive changes in households’ assets, and if so, what were the main changes? Was there an increase in households’ financial assets?

- Food security: Did the project improve food availability, whether self-produced or purchased, to ensure a minimum necessary intake for all households members? Do project beneficiaries have an improved and more regular access to enough or more nutritious food? Is there a reduction in the occurrence, or duration, of lean periods? Did children’s nutritional status change (stunting, wasting and underweight status)? To what extent did the rural poor improve their access to input and output markets that could help them enhance their productivity and access to food? To what extent were the rural poor able to overcome market volatility or climate changes to ensure year-round food security?

- Agricultural productivity: Did the project contribute to increase agricultural, livestock and fish productivity, as measured in terms of cropping intensity, yields and land productivity? Are there changes in the levels of local production? Are farmers applying improved or more sustainable farming practices? Did the project ensure that smallholders benefited from increased agricultural production and were enabled to manage market fluctuations and changes in climatic or natural resources conditions?

- Access to markets: Are there changes in farmers’ physical access to markets (e.g. availability of roads and marketing outlets), in their access to market prices and information or in their bargaining power with traders? Did the project have an impact on the timely access to quality agricultural inputs (fertilizers, vaccines, seeds) and on the capacities of Producers/Marketing Groups?

- Impact on the global environment:

  - Natural resources and the environment: Were the approaches to environment preservation and natural resources management appropriate to local circumstances and were they effective in addressing local problems? Are there positive or negative changes in the natural resources base (forests, marine/fisheries resources, pastureland, and water resources) that may be attributable to project interventions? Did the project have positive or negative changes – intended or unintended - on the environment? Did it contribute to the protection or rehabilitation of natural and common property resources (land, water, forests and pastures)? Has the degree of environmental vulnerability changed?

  - Focal area specific aspects (biodiversity ; land degradation ; climate adaptation) – to what extent has the project contributed to the three focal areas of the GEF at design?

- Adaptation to climate change: Were the approaches for climate change adaptation promoted by the project appropriate to local circumstances and were they effective? Did the project manage to empower rural communities to cope with, mitigate or prevent the effects of climate change and natural disasters? Are farming communities more resilient to such disasters and are farming practices better adapted to climate change? Were the coping capacities of vulnerable natural systems restored?

- Gender equity and women empowerment: Did the project generate changes in gender roles or gender relations? Are there changes in women status at the community level (participation in local elections or decision-making processes, representation in rural producers’ groups), at the household level (workload, nutrition status, women influence on decision-making) or the community level)? What is the impact of capacity-building activities on individual women or on Women Groups? Are there changes in the institutional or legal framework that were made in favour of women as a result of project policy dialogue activities?

- Institutions and policies: Are there changes in the capacities of the various grassroots organizations supported during project implementation (such as Rural Producers’ Groups, Interest Groups or Users’ Associations)? Are there changes in the institutional capacities of the main institutions involved in project implementation? Are there changes in the quality or range of services delivered for the rural poor? Are there changes in local governance or in the behaviours of local institutions? Are there changes in the policy or institutional framework as a result of project-led policy dialogue activities (e.g. changes in the laws, statutes, rules, regulations, procedures, national quality standards or norms)?

- Sustainability

- The mission will assess the likelihood that the benefits from project intervention will continue after project completion. It will also assess the likelihood that actual and anticipated results will be resilient to risks, including climate-related risks, beyond project life. The adequacy of the post-project strategy, as designed and/or implemented, will also be examined. More precisely, the mission will examine the following questions:

- Was an appropriate post-project strategy developed and implemented since project start-up?

- Social sustainability (Empowerment): Do project beneficiaries have the necessary capacities and skills, individually or collectively, to continue the approaches or manage the investments promoted by the project? Are these socially acceptable? Is there sufficient local ownership for these approaches or investments? Was there adequate beneficiary participation during project implementation? Is there interest and willingness, among concerned communities, to continue with promoted approaches or investments after project completion?

- Economic and financial sustainability: Do project investments generate sufficient cash flow and income to offset future investment and O&M costs? Are project investments economically and financially viable? If not, what are the constraints?

- Technical sustainability: Are the approaches promoted by the project viable from a technical point of view? Are spare parts for acquired or promoted machineries and equipment locally available? Do beneficiaries have the necessary technical capacities to operate and maintain the investments promoted by the project? Do they have access to adequate funds for operation and maintenance?

- Institutional sustainability: Are the institutions supported by the project self-sufficient and viable? Have operating capacities been created and/or reinforced in national and local partners? Are the new approaches or practices promoted by the project mainstreamed within normal government operations? Is there a clear indication of government commitment after the loan closing date in terms of follow-up actions, provision of O&M funds, etc.?

- Environmental sustainability: Are the approaches and investments promoted by the project environmental-friendly? Are they helping reduce the pressure on the natural resource base? Are they having any negative impact on the environment or the natural resource base? Did promoted techniques and approaches take into account climate change issues? Are they promoting adaptations to climate change? Can recurrent natural hazards endanger prospects of sustainability?

- Climate change: Are the agricultural approaches promoted by the project suitable in a context of a rapidly changing climate? How many changes in climatic conditions affect the sustainability of interventions in the long run?  Which precursors are critical to achieve long-term impact?

- The sustainability analysis will be completed by an annex evaluating the likelihood of sustainability of outcomes at project termination, evaluating four categories of risks (financial risks; socio-political risks; institutional framework and governance risks; environmental risks. Each of the dimensions of risks to sustainability of project outcomes will be rated based on an overall assessment of the likelihood and magnitude of the potential effect of the risks considered within that dimension, with the following ratings: likely (L); moderately likely (ML); moderately unlikely (MU); unlikely (U). (see annex 3)

- Targeting and outreach

- The mission will assess the extent to which project interventions have reached the intended target groups, that is the specific individuals or organizations for whose benefit specific interventions were initially designed and implemented. The mission will also assess the effectiveness of the project targeting strategy. More precisely, the mission will examine the following aspects:

- Did the project reach out to the expected number of beneficiaries in the manner intended? Did the project provide all anticipated benefits to the specific socio-economic groups identified in the Project Design Document? Were there deviations from initial outreach targets and if so, what were the reasons?

- Was outreach properly monitored in both quantitative (e.g. number of direct and indirect beneficiaries) and qualitative terms (e.g. beneficiaries’ socio-economic profile)?

- Did the project implement a sound targeting strategy? Did the project regularly analyse the needs, potentials and priorities of intended target groups and the poverty dynamics in the project target area and developed specific outreach strategies accordingly?

- Were there measures taken to ensure that the poor and vulnerable groups would not be excluded from project implementation and would benefit from it; and that the non-poor would not capture project benefits?

- Did the project implement gender-sensitive implementation approaches? Did the project ensure equal participation of men and women in implementation? Were there specific measures undertaken in order to promote women participation in project activities? Did the project’s M&E system track gender-disaggregated data?

- Innovation

- The mission will assess the extent to which project interventions have introduced and tested innovative approaches to rural poverty reduction. These are any processes, tools or practices that add value or solve a problem in new ways. More precisely, the mission will answer the following questions:

- Was the project designed specifically to test or lead to innovation, for example by piloting new concepts or technologies? Did the project test and introduce innovative ideas in the project target area? What are the characteristics of these innovations? Are these consistent with the IFAD definition of the concept? How did the innovation originate and was it adapted in any particular way during project design? Are these approaches truly innovative with regard to the local or national contexts?

- Were these innovative approaches carefully monitored and documented? Were these innovations discussed with the Government or other actors? Were these innovative approaches successful? Did these innovations address relevant needs of the rural poor and are these viable?

- Were these innovations adopted by the rural poor, local implementation partners, government entities or any other actors?

- Knowledge generation and sharing

- The mission will assess the quality of the project knowledge management system established in the course of project implementation for the generation and sharing of knowledge that could be useful to others. Such knowledge may concern the results of project innovations or any implementation approaches that were successful – or unsuccessful - in addressing rural poverty issues. More precisely, the mission will answer the following questions:

- Did the project design include an appropriate knowledge management strategy? Was it duly implemented during implementation? Did the project produce any knowledge products? Did it organize knowledge-sharing events and activities? If so, what were the quality, usefulness and outcomes of such events?

- Did the project implementation process generate any new and relevant knowledge regarding the implementation of pro-poor approaches or rural development issues? Can this knowledge be applied in other contexts?

- Potential for scaling-up and theory of change

- The mission will evaluate the changes brought by the project. The mission will then assess the extent to which some approaches, technologies or innovative features pilot-tested or successfully implemented by the project are likely to be up-scaled. It will also assess the likelihood that some project approaches may be replicated in other geographical areas. More precisely, the mission will examine the following aspects:

- How likely is it that the project - or some of its activities, approaches or innovative technologies - may be replicated in other localities or at the national level by the Government or other donors? Has any component or activity of the project already been replicated beyond the target area or target group?

- How proactive was project management, or other stakeholders, in discussing future up-scaling with the Government or other development partners? What are the prospects or obstacles?

- Performance of implementation partners

- The mission will assess the performance of each of the various partners involved in project implementation (other than IFAD). These are the organizations or entities directly responsible for project implementation, for providing strategic guidance and oversight or for the provision of essential services. More precisely, and in addition to determining if all implementation partners have adequately fulfilled their respective roles and responsibilities, the mission will examine the following points:

- Service providers: What was the performance of the main service providers (such as NGOs, training institutes, business development service providers, participating financing institutions private contractors or contracted government agencies) involved in service delivery? Were services delivered in a timely manner? Did service providers provide value for money and did they adhere to agreed schedules and contracts?

- Grass-roots institutions: What was the performance of the grass-roots institutions (CBOs, Producers’ Groups, WUAs, etc.) involved in daily project activities, their capacities, motivations, strengths and weaknesses? Were they actively participating in project implementation? What was the performance of the local-level or deconcentrated government agencies involved in project implementation?

- Central Government agencies: Did the Executing Agency and Implementing Agency comply with the covenants of the loan agreement and the provisions of the Project Design Document? Were they proactive in supporting project implementation and identifying solutions to problems? Was the Project Steering Committee fulfilling its role adequately?

- Co-financiers: What was the performance of external project co-financiers? Was there a timely provision of funds in the level expected? Did co-financing partners adequately support project implementation, supervision or oversight? Were all co-financiers’ procedures (for example for financial reporting, the preparation of progress reports, etc.) harmonized among themselves and with Government’s procedures?

- Lessons learned

- The mission will present the main lessons learned from project implementation, based on the analysis of what learning from experience may be applicable to a more generic situation. In so doing, the mission will refrain from exposing platitudes, keeping in mind the following definition of a lesson learned: “knowledge or understandings gained by experience which may be positive, as in a successful experiment, or negative, as in a mishap or failure”.

- All lessons learnt presented should be significant in that they have a real or assumed impact on operations; valid in that they are factually and technically correct; and applicable in that they identify a specific design, process, or decision that reduces or eliminates the potential for failures and mishaps, or reinforces a positive result.

- In particular, the mission will focus on the evaluation of processes that have impeded the achievement of the project’s results, notably in terms of: preparation and readiness (design, project structure, capacities, etc.); country ownership and drivenness; stakeholders’ involvement; financial planning; GEF agency (IFAD) supervision and backstopping; cofinancing and project outcomes and sustainability (If there was a difference in the level of expected cofinancing and the cofinancing actually realized, what were the reasons for the variance?); delays and project outcomes and sustainability (If there was a difference in the level of expected cofinancing and the cofinancing actually realized, what were the reasons for the variance? Did the extent of materialization of cofinancing affect project outcomes and/or sustainability, and, if so, in what ways and through what causal linkages?).

- In order to identify these lessons learned, the mission may examine the following questions:

- What specific knowledge or lessons can we derive from project implementation that may be used in the future in similar, or different, contexts?

- What were the project strengths and its main weaknesses? What were the main opportunities, or threats, in the environment that have facilitated, or constrained, project implementation?

- With the benefits of hindsight, what are the things that should have been done differently? What are the specific dimensions of the project design that one should never repeat again in similar contexts or circumstances?

- What are the specific aspects of project implementation that will be worthwhile replicating in future interventions in the country, or elsewhere, because they were particularly interesting or successful? In the external context, what will be the important conditions required for similar interventions to lead to similar results elsewhere or in the future?

- Conclusions and recommendations

- The consultant (s) will present the overall conclusions with regard to project implementation performance and project results, highlighting salient features and overall impact on poverty reduction.

- The consultant (s) will also make a number of recommendations to the TNC, the GEF and IFAD pertaining to the key elements for post-project sustainability or future programming or project design; and basing the analyses on the previous evaluation (see above) or processes that have affected the achievement of project’s results.

- The consultant will ensure stakeholders (e.g. TNC, Nairobi Water Fund, IFAD, MoEF, private and public sector, counties, service providers, beneficiary representatives etc.) are fully engaged/consulted during the process and that results and findings are shared with them for comments and inputs prior to finalisation of the final report.

Annex 2 – Evaluation of relevance, effectiveness, efficiency and of the project’s M&E system

The levels of evaluation are as follow : highly satisfactory - HS (the project had no shortcomings in the achievement of its objectives in terms of relevance, effectiveness, or efficiency); satisfactory - S(the project had minor shortcomings in the achievement of its objectives in terms of relevance, effectiveness, or efficiency); moderately satisfactory - MS (the project had moderate shortcomings in the achievement of its objectives in terms of relevance, effectiveness, or efficiency); moderately unsatisfactory - MU (the project had significant shortcomings in the achievement of its objectives in terms of relevance, effectiveness, or efficiency); unsatisfactory - U (the project had major shortcomings in the achievement of its objectives in terms of relevance, effectiveness, or efficiency); highly unsatisfactory - HU (the project had severe shortcomings in the achievement of its objectives in terms of relevance, effectiveness, or efficiency).

| Evaluated aspect | Rating and justification |
| --- | --- |
| Relevance |  |
| Effectiveness |  |
| Efficiency |  |
| Monitoring and Evaluation system |  |

Annex 3 – Assessment of Risks to Sustainability of Project Outcomes

The following four dimensions or aspects of risks to sustainability will be addressed:

  - Financial risks. Are there any financial risks that may jeopardize sustainability of project outcomes? What is the likelihood of financial and economic resources not being available once GEF assistance ends? (Such resources can be from multiple sources, such as the public and private sectors or income-generating activities; these can also include trends that indicate the likelihood that, in future, there will be adequate financial resources for sustaining project outcomes.)

  - Socio-political risks. Are there any social or political risks that may jeopardize sustainability of project outcomes? What is the risk that the level of stakeholder ownership (including ownership by governments and other key stakeholders) will be insufficient to allow for the project outcomes/benefits to be sustained? Do the various key stakeholders see that it is in their interest that project benefits continue to flow? Is there sufficient public/stakeholder awareness in support of the project’s long-term objectives?

  - Institutional framework and governance risks. Do the legal frameworks, policies, and governance structures and processes within which the project operates pose risks that may jeopardize sustainability of project benefits? Are requisite systems for accountability and transparency, and required technical know-how, in place?

  - Environmental risks. Are there any environmental risks that may jeopardize sustainability of project outcomes? The terminal evaluation should assess whether certain activities will pose a threat to the sustainability of the project outcomes. For example, construction of a dam in a protected area could inundate a sizable area and thereby neutralize the biodiversity-related gains made by the project.

Each of the above dimensions of risks to sustainability of project outcomes will be rated based on an overall assessment of the likelihood and magnitude of the potential effect of the risks considered within that dimension. The following ratings will be provided:

Likely (L). There are no or negligible risks that affect this dimension of sustainability.

Moderately likely (ML). There are moderate risks that affect this dimension of sustainability.

Moderately unlikely (MU). There are significant risks that affect this dimension of sustainability.

Unlikely (U). There are severe risks that affect this dimension of sustainability.

All the risk dimensions of sustainability are critical. Therefore, overall rating for sustainability will not be higher than the lowest rated dimension. The following matrix gathering the above-mentioned information will be presented in annex of the TER:

| Sustainability dimension | Likelihood for this dimension to be achieved and description of the existing threat |
| --- | --- |
| Financial sustainability |  |
| Socio-political sustainability |  |
| Institutional and governance sustainability |  |
| Environmental sustainability |  |
| Global sustainability |  |

Annexe 4. TER RATING MATRIX (TEMPLATE)

The TER will include in Annex III a table that summarizes the scores provided by the terminal evaluation team for all main evaluation criteria and performance assessment questions, as follows:

| Criterion | Rating |
| --- | --- |
| Project performance |  |
| - Relevance |  |
| - Effectiveness |  |
| - Efficiency |  |
| - Sustainability |  |
| Rural poverty impact |  |
| - Households ‘incomes and assets |  |
| - Human and social capital and empowerment |  |
| - Food security |  |
| - Agricultural productivity |  |
| - Institutions and policies |  |
| - Overall rural poverty impact |  |
| Additional evaluation criteria |  |
| - Gender equality and women’ s empowerment |  |
| - Access to markets |  |
| - Innovation |  |
| - Potential for scaling-up |  |
| - Environment and natural resources management |  |
| - Adaptation to climate change |  |
| - Targeting and outreach |  |
| Partners performance |  |
| - IFAD’ s performance |  |
| - Government performance |  |
| Overall project achievement |  |

The Constitution of Kenya (2010). The Government of the Republic of Kenya.

World Bank, 2022. Kenya Economic Update, June 2022 edition No.25. Aiming High: Securing Education to sustain the Recovery. https://documents1.worldbank.org/curated/en/099430006062288934/pdf/P17496106873620ce0a9f1073727d1c7d56.pdf

ibid

Republic of Kenya (2008). Vision 2030.

https://www.nema.go.ke/images/Docs/EIA_1840-1849/Kenya%20State%20of%20Environment%20Report%202019-2021%20final-min.pdf

NEMA (2011). State of the Environment and Outlook Report for Kenya 2010. National Environment Management Authority (NEMA), Nairobi

A country is considered water scarce if the total per capita water availability is less than 1,000 m3. It is water stressed if the values is below 500 m3.

TNC 2015. Upper Tana-Nairobi Water Fund Business Case. Available at https://www.nature.org/content/dam/tnc/nature/en/documents/Nairobi-Water-Fund-Business-Case_FINAL.pdf

The UTNWF End of Project Report, 2021

UTNWF Project Implementation Report, 2020.

Project implementation report, 2020.

FSIAP GEF IAPIP Evaluation, Kenya Case Study Final Report, 2021.

ibid

IFAD, 2013. Republic of Kenya Country strategic opportunities programme (2013-2018). https://webapps.ifad.org/members/eb/109/docs/EB-2013-109-R-14.pdf

IFAD, 2019. Republic of Kenya Country strategic opportunities programme (2020-2025). https://webapps.ifad.org/members/eb/128/docs/EB-2019-128-R-19.pdf

IFAD, 2018. IFAD Strategy and Action Plan on Environment and Climate Change 2019-2025. https://webapps.ifad.org/members/eb/125/docs/EB-2018-125-R-12.pdf

Project Supervision Report August 30, 2021, revised (002).docx final.docx

UTNWF End of Project Report, October 2016 – December 2021

ibid

TNC, 2015. Upper Tana-Nairobi Water Fund Business Case. Version 2. The Nature Conservancy: Nairobi, Kenya.

Mati, B.M.; Sijali, I.V.; Ngeera, K.A. 2022. Investigating pathways for agricultural innovation at scale: Case studies from Kenya. Colombo, Sri Lanka: Commission on Sustainable Agriculture Intensification

Project Supervision Report August 30, 2021, revised (002).docx final.docx

https://nairobiwaterfund.org/wp-content/uploads/2021/12/UTNWF-Strategic-Plan_Final.pdf

UTNWF End of Project Report, October 2016 – December 2021

# UTNWF 2021 Annual Progress Report (ver. 3).docx

Additional Qualitative Information on Changes Observed Following the TNC-UTNWF Project, Central Kenya- FINAL REPORT; DECEMBER 2021

UTNWF End of Project Report, October 2016 – December 2021

ibid

Aide Memoire, Final July 26, 2021.

UTNWF Position Paper on Contribution of Upper Tana Nairobi water fund to key value chains and Market linkage in the catchment, June 20, 2021.

UTNWF IFAD 2021 Half Year Progress Report version 2.pdf

IFAD Project Supervision Report, Sept 2020.pdf

UTNWF Project progress report July 2018 -June 2019_Final Ver.docx

Kenya Upper Tana Catchment Natural Resource Management Project Supervision Report, 28 March to 14 April 2022

UTNWF IFAD Supervision Mission Report, August 30, 2021

UTNWF End of Project Report, 2022

According to the Kenyan Constitution, youths are recognized as people between the age of 18 – 35.

UTNWF IFAD supervision mission report, September 2020

Mati, B.M.; Sijali, I.V.; Ngeera, K.A. 2022. Investigating pathways for agricultural innovation at scale: Case studies from Kenya. Colombo, Sri Lanka: Commission on Sustainable Agriculture Intensification. 46p.

Mati, B.M.; Sijali, I.V.; Ngeera, K.A. 2022. Investigating pathways for agricultural innovation at scale: Case studies from Kenya. Colombo, Sri Lanka: Commission on Sustainable Agriculture Intensification. 46p.

UTNWF Trust -Position Paper on Lessons learned and scaling up after 5 years of implementation, January 6, 2022.

ibid

UNTWF Gender and Poverty Reduction Strategy, 2018

Gender action plan (GAP)For Upper Tana Nairobi Water fund, December 2021

UNTWF Position Paper on Gender and youth empowerment after 5 years of implementation, June 24, 2021.

ibid

As per Table 1 in the project document.