UNEP GEF PIR Fiscal Year 2025

Reporting from 1 July 2024 to 30 June 2025

# 1. PROJECT IDENTIFICATION

# 1.1. Project details

1. IDENTIFICATION

| Identification Table |  | GEF ID.: 6986 | Umoja WBS: SB-012083 |
| --- | --- | --- | --- |
|  |  | SMA IPMR ID: 39700 | Grant ID: S1-32LDL-000045 |
|  |  | Project Short Title: Rwanda NAP |  |
| Project Title |  | Building the capacity of Rwanda’s government to advance the National Adaptation Planning process |  |
| Duration months | Planned | 48 |  |
|  | Age | 64 |  |
| Project Type |  | Full-Sized Project |  |
| Parent Programme if child project |  | N/A |  |
| Project Scope |  | National |  |
| Region |  | Africa |  |
| Countries |  | Rwanda |  |
| GEF Focal Area(s) |  | Climate Change Adaptation |  |
| GEF financing amount |  | USD 6,000,000 |  |
| Co-financing amount |  | In kind contribution by Ministry of Environment: USD 5,000,000 In kind contribution by UNDP-UNEP: Poverty Environment Action for the SDGs: USD 2,400,000 In kind contribution by UNEP Global Adaptation Network: USD 100,000 Total: USD 7,500,000 - Co-financing: $7,500,000 - Leveraged co-financing so far: $10,149,571 = 135% as of end June 2025 |  |
| Date of CEO Endorsement/Approval |  | 11 January 2019 |  |
| UNEP Project Approval Date (Decision Sheet) |  | 29 October 2019 |  |
| Start of Implementation (PCA entering into force) |  | 29 October 2019 |  |
| Date of Inception Workshop, if available |  | 27 November 2020 |  |
| Date of First Disbursement |  | 10 March 2020 |  |
| Total disbursement as of 30 June 2025 |  | $5,047,456 |  |
| Total expenditure as of 30 June 2025 |  | $4,981,573 |  |
| Midterm undertaken? |  | Yes |  |
| Actual Mid-Term Date, if taken |  | 07-16 June 2023 |  |
| Expected Mid-Term Date, if not taken |  | N/A |  |
| Completion Date | Planned – original PCA | 30 September 2024 |  |
|  | Revised – Current PCA | 31 December 2026 |  |
| Expected Terminal Evaluation Date |  | January 2027 |  |
| Expected Financial Closure Date |  | June 2027 |  |

# 1.2. Project description

- The overarching goal of the project is the facilitation of country-driven medium- to long-term climate change adaptation in Rwanda. The objective of the project is to increase the capacity of governmental authorities and local communities in Rwanda to plan, fund, implement and monitor climate change adaptation solutions in the medium and long term. A special focus is the enhancement of the climate change adaptation knowledge base, with a particular emphasis on guiding adaptation planning based on technical and financial effectiveness of adaptation measures to inform the funding of the National Adaptation Planning (NAP) process. The project is executed by the Rwanda Environment Management Authority (REMA). The project’s five EbA pilot sites are: 1. Ibanda-Makera natural forest (Kirehe District), 2. Umuvumba river (Nyagatare District), 3. Eastern savannas (Nyagatare District), 4. Shagasha tea estate (Rusizi and Nyamasheke Districts), and 5. Nyandungu wetland (Kigali City, Gasabo and Kicukiro Districts). - Component 1: Technical and institutional capacity for the NAP process in Rwanda strengthened - Under this component, gaps related to the technical and institutional capacity to advance the NAP process in Rwanda will be bridged. This will include: i) establishing a NAP Technical Working Group (TWG) to oversee adaptation planning (Output 1.1); ii) developing downscaled catchment-level climate projections for Rwanda to inform the development of climate risk assessments (Output 1.2); iii) developing climate risk assessments for four catchments to inform the design of climate change adaptation (CCA) strategies, including the selection of adaptation measures (Output 1.3); iv) designing four catchment-level CCA strategies based on the results of climate risk assessments to enhance the resilience of the targeted catchments and serve as a model that can be upscaled across the country (Output 1.4); v) extrapolating CCA measures from catchment-level adaptation strategies – designed under Output 1.4 – to the national level to facilitate the development of adaptation plans for three priority economic sectors (Output 1.5); vi) refining Nationally Determined Contributions (NDC) adaptation priorities related to sectoral adaptation plans and the long-term research programme (LTRP), to ensure their effective implementation across the country (Output 1.6); and vii) fostering the national ownership of the NAP process through the dissemination of training manuals and the organisation of awareness-raising events for public and private sectors, CSOs and local communities (Output 1.7). - Component 2: Advancing climate-resilient practices and technologies Under Component 2, climate-resilient practices and technologies related to the NAP process will be adopted and advanced. This will be done by: i) updating the 2013 PERECC through the conduction of a CPEIR to determine available climate finance and assess the effectiveness of climate expenditures to date, determining funding gaps related to sectoral adaptation plans and developing a NAP funding strategy for Rwanda (Output 2.1); ii) providing recommendations to relevant ministries on the mainstreaming of CCA into their development budgeting and planning processes (Output 2.2); iii) establishing a long-term research programme (LTRP) – including landscape-scale EbA pilot sites – to address gaps in knowledge required to inform the design of adaptation plans as well as the selection of appropriate measures and future investments into CCA (Output 2.3); iv) implementing a suite of EbA interventions at LTRP pilot sites (Output 2.4); and v) building awareness of the private sector on future climate scenarios, national priorities and investment opportunities related to increasing the climate-resilience of businesses (Output 2.5). - The holistic approach to the NAP process in Rwanda will be exemplified by the EbA pilot interventions embedded within the proposed project under the LTRP (Output 2.4). EbA is inherently a medium- to long-term, cross-sectoral approach to adaptation that requires strong coordination from the planning phase to the monitoring phase to reach a successful outcome. Therefore, not only will pilot interventions showcase the socio-economic benefits of EbA in Rwanda for future upscaling, but they will demonstrate how the various components of the adaptation process should come into action. Component 3: Monitoring, reviewing and knowledge-sharing framework developed to learn from the NAP process Under Component 3, the limited capacity of Rwanda to monitor, review and share knowledge to learn from the NAP process will be strengthened. This will be done by: i) establishing a framework to monitor the effectiveness of the NAP process, including the revision current and addition of new outcome-level indicators (Output 3.1); ii) training technical staff of national government and district-level officers to monitor, report on and assess the effectiveness of the NAP process in Rwanda (Output 3.2); and iii) reporting and communicating on the progress of the NAP process in Rwanda to ensure knowledge sharing and learning (Output 3.3).

# 1.3. Project Contacts

| Division(s) Implementing the project | Climate Change Division |
| --- | --- |
| Executing Agency(ies) | Rwanda Environment Management Authority (REMA) |
| Names of Other Project Partners | Ministry of Environment (MoE) Ministry of Local Government (MINALOC) Ministry of Finance and Economic Planning (MINECOFIN) Ministry of Agriculture and Animal Resources (MINAGRI) Rwanda Meteorology Agency (Meteo Rwanda) Rwanda Forestry Authority (RFA) Rwanda Green Fund (FONERWA) University of Rwanda (UR) Higher Education Council (HEC) Rwanda Standards Board (RSB) Nyagatare, Kirehe, Rusizi, Gasabo and Nyamasheke Districts |
| UNEP Portfolio Manager(s) | Jessica Troni |
| UNEP Task Manager(s) | Anna Kontorov |
| UNEP Budget/Finance Officer | Priscillah Kaara, Fatma Twahir |
| UNEP Support/Assistants | Linda Chemutai Choge, Evans Madiri, Catherine Goreti Okoch |
| EA Manager/Representative | Herman Hakuzimana |
| EA Project Manager | Fidelité Ninziza |
| EA M&E Specialist | Dinah Kwizera |
| EA Finance Manager | Modeste Mugiraneza |
| EA Communications Lead, if relevant | Cyprien Ngendahimana |

# 2. OVERVIEW OF PROJECT STATUS

2.1 UNEP PoW and UN

| UNEP Current Subprogramme(s) | Climate action |
| --- | --- |
| PoW Indicator(s) | PoW 2022-2023 Indicators: (i) Number of national, subnational and private-sector actors that adopt climate change mitigation and/or adaptation and disaster risk reduction strategies and policies with UNEP support (ii) Amounts provided and mobilized in $ per year in relation to the continued existing collective mobilization goal of the $100 billion commitment through to 2025 with UNEP support (iv) Positive shift in public opinion, attitudes and actions in support of climate action as a result of UNEP action Strategic Objective 2: “Living in harmony with nature”. PoW 2022-2023 Indicators: (i) Number of national or subnational entities that, with UNEP support, adopt integrated approaches to address environmental and social issues and/or tools for valuing, monitoring and sustainably managing biodiversity (iii) Number of countries and national, regional and subnational authorities and entities that incorporate, with UNEP support, biodiversity and ecosystem-based approaches into development and sectoral plans, policies and processes for the sustainable management and/or restoration of terrestrial, freshwater and marine areas (iv) Increase in territory of land- and seascapes that is under improved ecosystem conservation and restoration |
| UNEP previous Subprogramme(s) | Climate Change Subprogramme |
| UNSDCF / UNDAF linkages | United Nations Development Assistance Plan (UNDAP) for Rwanda (2018-2023): Strategic Priority Area 1: “Economic transformation”, Outcome 2: “By 2023 Rwandan institutions and communities are more equitably, productively and sustainably managing natural resources and addressing climate change and natural disasters.” |
| Link to relevant SDG Goal(s) | - Goal 1: End poverty in all its forms everywhere; - Goal 2: End hunger, achieve food security and improved nutrition and promote sustainable agriculture; - Goal 11: Make cities and human settlements inclusive, safe, resilient and sustainable; and - Goal 13: Take urgent action to combat climate change and its impacts by regulating emissions and promoting developments in renewable energy; and - Goal 15: Protect, restore and promote sustainable use of terrestrial ecosystems, sustainably manage forests, combat desertification, and halt and reverse land degradation and halt biodiversity loss. |
| Link to relevant SDG Target(s) | Goal 1: Target 1.5 Goal 2: Target 2.4 Goal 11: Target 11.7 Goal 13: Targets 13.1, 13.2, 13.3, 13.4 and 13.5 Goal 15: Targets 15.1, 15.2, 15.3, 15.5 and 15.9 |

2.2. GEF Core Indicators:

| Indicators | Targets – Expected Value |  |  | Materialized to date |
| --- | --- | --- | --- | --- |
|  | Mid-term | End-of-project | Total target |  |
| Number of people adopting climate resilient practices and technologies | N/A | 40,000 | 40,000 | 107,608 |
| Percentage of females adopting climate resilient practices and technologies | N/A | 51.8% | 51.8% | 51.5% |
| Number of hectares where climate resilient technologies and practices are adopted | N/A | 500 ha | 500 ha | 9,974 ha |
| Number of relevant assessments and knowledge products carried out and updated | N/A | 20 | 20 | 12 |
| Score of country for systems and frameworks for the continuous monitoring, reporting, and review of adaptation | N/A | 6 | 6 | Not yet assessed |

2.3. Implementation Status and Risk

|  | FY 2021 | FY 2022 | FY 2023 | FY 2024 | FY 2025 |
| --- | --- | --- | --- | --- | --- |
| PIR # | 1st | 2nd | 3rd | 4th | 5th |
| Rating towards outcomes (section 3.1) | S | S | S | S | MS |
| Rating towards outputs (section 3.2) | S | S | S | MS | MS |
| Risk rating (section 3.3) | M | L | L | L | L |

Progress: The rating of progress towards project outcomes is moderately satisfactory for this reporting period. While the indicators for project Outcome 2 (EbA pilot interventions) have all been met and most exceeded, progress towards the achievement of the Outcome 1 and 3 indicators is lagging behind. Capacity of project stakeholders (project Objective and Outcome 1 indicators) has continued to be built through their full engagement in the planning and implementation of the project activities. In particular, the ongoing catchment-level climate risk assessment process has involved strong stakeholder engagement, specifically in the review of the draft assessment reports in this reporting period. Furthermore, the meteorological monitoring capacity of Rwanda Meteorology Agency (Meteo Rwanda) and Rwanda Standards Board (RSB) has continued to be enhanced through the successful operation of the Calibration Center for Meteorological, Hydrological and Air Quality Monitoring Instruments established by the project in the previous reporting period. While no additional training workshops have been organized by the project in this reporting period, a plan for a training-of-trainers programme on the NAP process and climate change adaptation, targeting public and private sectors, CSOs and local communities, is currently being developed and a suitable service provided is being identified. The quantitative increase in project stakeholders’ adaptation planning capacity (Outcome 1 indicator) will be measured by the results verification exercise to be undertaken before the project’s Terminal Review. For the EbA pilot interventions (Outcome 2 indicators), the target numbers of beneficiaries and hectares under sustainable land management were exceeded already in previous reporting periods. To date, the project has reached 107,608 beneficiaries, with 9,974 ha hectares of land managed sustainably for long-term adaptation at the pilot sites. The average survival rate of the trees planted as part of the project’s EbA interventions is relatively high, at around 86%. For Outcome 3 indicator focused on NAP monitoring systems, the progress has been limited to date. The recruitment of the Adaptation Monitoring and Knowledge Management consultant was somewhat delayed and is scheduled to be completed with UNEP support in Q3 2025. As such, the integration of NAP indicators in the Ministry of Environment (MoE) Results-Based Monitoring and Evaluation (RBME) system has not been directly advanced yet. Nonetheless, through its engagement in Rwanda’s NDC 3.0 process, the project has in this reporting period contributed to the refinement of the NDC adaptation priorities, and the development of the NDC monitoring framework and indicators. These will feed into and inform the activities to be undertaken under project Component 3. The rating of progress towards project outputs is rated as moderately satisfactory in the current reporting period. Although good progress has been made on several project outputs, others are delayed – in particular those related to the NAP process or long-term adaptation planning. This is largely due to the continued challenges involved in implementing a project that includes very significant field interventions (the EbA pilots) on the one hand, as well as an ambitious workplan of capacity building, technical studies, and policy and planning interventions on the other hand. An additional no-cost extension until December 2026 will be necessary for completing all the project outputs. The key achievements of the current reporting period are outlined below: Under Component 1, in the current reporting period, the climate risk assessment process in the four project catchments was continued. The Climate Impact Storylines report was finalized, following the integration of feedback provided by REMA and UNEP. The four catchment-level climate risk assessment reports have also been drafted in this reporting period. However, their finalization has been delayed, due challenges in access to necessary data and insufficient communication between the service provider and Meteo Rwanda. These challenges have now largely been resolved and the reports are expected to be finalized and validated by Q4 2025. The climate risk assessment process follows the completion of downscaled climate change projections undertaken by the project through a collaboration between REMA and Meteo Rwanda in previous reporting periods. The NDC 3.0 process has been significantly advanced in Rwanda, including the refinement of adaptation priorities. In this reporting period, the project contributed to the development of the various Terms of References and the review of the NDC 3.0 and its adaptation priorities. The NDC adaptation priorities and the consultation undertaken as part of the NDC process will help to inform the development of the catchment adaptation strategies and sectoral adaptation plans under project Outputs 1.4 and 1.5. Under Component 2, the implementation of all the EbA interventions in Nyagatare, Nyamasheke, Kirehe and Rusizi Districts was completed in this reporting period, with the total area of land managed for adaptation benefits being 9,974 ha. Handovers from the contractors to the Districts have been completed in Kirehe, Nyagatare and Rusizi Districts, with the handover in Nyamasheke planned for January 2026. Maintenance (preparation of nurseries, weeding, replacement of trees and clearing of ditches) has continued in all the districts in this reporting period. The formal handover from REMA to the Districts will be undertaken in Q4 2025, following the finalization of the handover reports. The overall survival rate of planted trees is relatively high; currently at around 86%. The survival rate by District and intervention type are detailed under Outcome 2 indicator (iii) in PIR Section 3.1 (marked as Table 2). The achievements to date (30 June 2025) are summarized in the table below. District; Intervention; Achievements. Nyagatare (Eastern Savannas); Silvo-pastoralism; 915 ha. Sub-total; 915 ha. Nyagatare (Umuvumba river); Agroforestry; 1,890 ha. Restoration of gallery forest; 140 ha. Woodlot; 255 ha. Revegetation and protection of Umuvumba and Ngoma riverbanks; 85 ha *43.8 ha at Umuvumba *41.5 ha at Ngoma. Trenches in forest; 261 ha. Fruit trees; 59,572 seedlings. Sub-total; 2,631 ha. Kirehe; Agroforestry; 1,435 ha. Complete agroforestry (Tree planting, trenches excavation and stabilization in agricultural lands); 420 ha. Woodlot; 445 ha. Restoration of Ibanda-Makera natural forest; 77 ha. Demarcation of forest perimeter with live fence; 5 km. Sub-total; 2,377 ha. Rusizi; Simple agroforestry (Tree planting in agricultural lands); 1,400 ha. Complete agroforestry; 998 ha. Reforestation; 293 ha. Trenches in forests; 452 ha. Fruits trees (avocados, guavas, mangos and tree tomatoes); 132,130 seedlings. Sub-total; 3,143 ha. Nyamasheke; Simple agroforestry; 442 ha. Complete agroforestry; 345 ha. Fruit trees (avocados and mangos); 20,890 seedlings. Sub-total; 787 ha. Gasabo and Kicukiro; Restoration of Nyandungu wetland (stream widening, drainage channels, wetland and fen restoration, living fence and medicinal garden); 121 ha. Sub-total; 121 ha. TOTAL; 9,974 ha. In addition, in Rusizi District, 100 rainwater harvesting tanks (of which 39 in this reporting period) were installed by the project in vulnerable communities to provide water for household consumption, as well as to reduce erosion resulting from streams of water flowing from roofs. Furthermore, five small-scale irrigation schemes irrigating a total area of 55 ha were provided in previous reporting periods to local communities in Eastern Province (three in Nyagatare and two in Kirehe District), where rain-fed agriculture is disproportionately affected by water shortages associated with droughts. Finally, 132 dam sheets were provided to local communities in Nyagatare District in previous reporting periods, for capturing rainwater for animals and domestic use. The main objective is to alleviate the impact of drought on pastures and to stop cattle from moving to the riverbanks of Umuvumba river during the dry season. Research undertaken as part of the long-term research programme (LTRP) established by the project has been continued and expanded during the current reporting period. The LTRP was established in 2021 through an MoU between the Higher Education Council (HEC), University of Rwanda (UR) and REMA to inform long-term climate change adaptation planning and implementation in Rwanda. The research findings, including on the technical and economic effectiveness of EbA in the long-term, will help bridge knowledge gaps to inform future adaptation planning and budgeting under the NAP process. In this reporting period, 23 MSc students supported by the project completed their degrees and research projects on EbA-related topics in the project pilot sites. Furthermore, 7 research articles on EbA-related topics were published by university researchers based on research in the project pilot sites (as well as those of the LDCF-funded EbA project). Several more articles will be published from the 11 research projects funded by the project. The research projects study various aspects of EbA in the project sites, including mapping and valuing EbA practices in farmlands, the use of bioindicators to monitor adaptation outcomes, the role of women’s capacity building in reducing vulnerability, and the role of agroforestry in reducing deforestation and land degradation. As for project Component 3, in this reporting period, through its engagement in Rwanda’s NDC 3.0 process, the project has contributed to the refinement of the NDC adaptation priorities and the development of the NDC monitoring framework and indicators. These will feed into and inform the activities to be undertaken under Outputs 3.1 and 3.2. Furthermore, the recruitment of the Adaptation Monitoring & Knowledge Management consultant was advanced and is expected to be completed in Q3 2025. Challenges: One of the main challenges in this reporting period has been the delay in the finalization of the catchment-level climate risk assessment reports. This has been due challenges in access to necessary data (in the right format) from Meteo Rwanda, and insufficient communication between the service provider and Meteo Rwanda. These challenges have now largely been resolved and the reports are expected to be finalized and validated by Q4 2025. The overall risk rating for the project remains low. As outlined in PIR Section 4, the ratings for most risks identified at the CEO endorsement stage have remained low. Furthermore, many of the challenges that were identified in previous reporting periods have been largely resolved (as outlined in previous PIR reports). However, some challenges related to the identified risks continued to be encountered during this reporting period, and will need to continue to be mitigated (as detailed in PIR Section 4): Although the survival rates of planted seedlings have improved (the current overall survival rate of planted trees is around 80% for simple and complete agroforestry, as well as for silvo-pastoralism, and above 90% for woodlots), this risk still remains important for the young trees planted. The damages to planted trees have been due to a variety of reasons, including prolonged dry season, termites and cattle damage in some parts of project intervention areas. Unsuccessful procurement processes for consultancies remain a challenge, due to the limited availability of qualified national consultants and the long procurement processes. In this reporting period, the main procurements were undertaken by UNEP (as requested by REMA). In the next period, actively soliciting qualified consultants to apply will be the main mitigation measure to be undertaken, to ensure the success of the upcoming consultant recruitments by REMA.

2.4. Co-financing

| Planned Co-finance Total Actual to date | Total planned: USD 7,500,000 This consists of: MoE (in-kind): USD 5,000,000 Poverty- Environment Action for the SDG (in-kind): USD 2,400,000 UNEP / Global Adaptation Network (GAN) (grant): USD 100,000 Actual do date (30 June 2025): USD 10,149,571, i.e. 135% |
| --- | --- |
| Progress | The co-finance mobilized by the project consists of in-kind contributions from the Ministry of Environment (MoE) (to the value of USD 5,576,989), and contributions from the UNDP-Poverty Environment Action for the SDGs (PEA project) (USD 1,600,000), the Ministry of Finance and Economic Planning (MINECOFIN) (USD 2,950,582), and UNEP / SIDA funds (USD 22,000). This is summarized in the table below: Co-finance source; Planned amount (USD); Actual amount to date (USD). Ministry of Environment (MoE); 5,000,000; 5,576,989. UNDP-Poverty Environment Action for the SDGs (PEA); 2,400,000; 1,600,000. UNEP / Global Adaptation Network; 100,000; 0. MINECOFIN (RAB and project Districts); N/A; 2,950,582. UNEP/SIDA; N/A; 22,000. Total:; 7,500,000; 10,149,571. The MoE co-finance contribution of USD 5,576,989 (compared with a planned allocation of USD 5,000,000) consists of: - Consultants on the Revised Green Growth and Climate Resilience Strategy, Rwanda's Nationally Determined Contribution updated in 2020, Coordination strategy to track institutional engagement and commitment to the NDC, NDC MRV, NDC Implementation Framework and Baseline Study on Climate Change Impacts on the Private Sector - Administrative support, transport and monitoring services - Contracts for the Vulnerability Index 2018 and for the management for urban wetlands in Kigali / development of wetland master plan - Expendable equipment (energy and water, public relations and awareness-raising, office equipment, furniture, supplies and consumables) - Non-expendable equipment (ICT equipment, software and other ICT assets) Of the planned PEA co-finance contribution of USD 2,400,000, USD 1,600,000 has materialized to date. Co-finance has also been mobilized from MINECOFIN through RAB and the project Districts. This contribution of USD 2,950,582 has supported the implementation and scaling-up of the project’s EbA interventions. Finally, UNEP supported the development of the Policy Brief on the stakeholder-led process for the selection and revision of the project’s EbA measures (see PIR section 2.8 on Knowledge Management) with a contribution of USD 22,000 from SIDA funds. |

2.5. Stakeholder engagement

| Date of project steering committee meeting | The eighth Project Steering Committee (PSC) meeting was held on 7th of October 2024, in Kigali. In addition to REMA representatives, the meeting was attended by representatives from all the project Districts, key project partners (e.g. MoE, MINECOFIN, MINALOC, Meteo Rwanda, University of Rwanda (UR), Higher Education Council (HEC), Rwanda Forest Authority (RFA)), as well as the UNEP Task Manager. Furthermore, District Project Technical Committee (DPTC) meetings were conducted in Nyamasheke and Rusizi Districts for progress evaluation and guidance or recommendations, where needed. |
| --- | --- |
| Stakeholder engagement | During this reporting period, local communities in Rusizi, Nyamasheke, Nyagatare and Kirehe Districts continued to engage in the project’s maintenance activities, such as replacing plants, pruning, weeding, bush clearing and guarding of EbA interventions, to increase their ownership and the sustainability of the interventions after project completion. The Rwanda Forestry Authority, the four Districts of project intervention, the Rwanda Water Resources Board, the Rwanda Agriculture Board, civil society organizations, Water User Associations and local communities all actively continued their participation in the maintenance of the project’s field activities for ensuring their sustainability. REMA and the Districts continue their close collaboration in the implementation of all NAP project activities. Important decisions are taken together to increase the ownership of the Districts. Handover reports from REMA to the Districts are currently being prepared. These will include sustainability aspects and maintenance plans. District staff will also be allocated responsibilities for ensuring the sustainability of the interventions after the project completion, with the related tasks being included in their performance contracts. In previous reporting periods, to engage with local communities and beneficiaries during project implementation, the project has used different methods, including Focus Group discussions with representatives of local communities and discussions with various stakeholders, as appropriate. Targeted awareness raising campaigns associated with the implementation of the activities have further supported the gathering of community views and enhance local ownership of activities for the enhanced sustainability of interventions. The project’s Mid-Term Review (MTR) noted that community engagement and consultation – from the very beginning of the project to the final implementation of the activities – has led to a strong local commitment to implement and sustain the project interventions beyond the project’s life. The successful implementation of EbA interventions can also be attributed to the serious supervision provided by district authorities which provided dedicated and skilled staff as well as time and resources to the project. Furthermore, the project’s MTR recommended strengthening coordination with recent and ongoing relevant initiatives in the country. Specifically, the project should strengthen collaboration with the NAP Global Network initiative focused on adaptation monitoring frameworks and the recently-approved GCF NAP Readiness Project. In previous reporting periods, PMU undertook stakeholder consultations at inception phase with key institutions at national and local levels to introduce the project to key stakeholders, but also to assess the feasibility of activities under the project. The institutions consulted included the Ministry of Environment, the Ministry of Economic Planning and Finance, the Ministry of Emergency Management (MINEMA), Meteo Rwanda, Rwanda Green Fund (FONERWA), Rwanda Forestry Authority, Rusizi District, Kirehe District, Nyamasheke District and Nyagatare District. Extensive stakeholder consultations were also conducted during project feasibility assessment to assess the viability and to elaborate the design of the project’s proposed ecosystem-based adaptation (EbA) interventions across five pilot sites in Rwanda. Stakeholders consulted included potential beneficiaries and institutions at national level and in the districts in which EbA interventions are being conducted. Methodological approaches included key informant interviews with experts, focus group discussions with beneficiaries, and an online validation workshop. In previous reporting periods, a Policy Brief was developed with UNEP lead, focusing on this stakeholder-led process for the selection and revision of the project’s EbA measures. The outcomes of the consultations were used in designing the interventions at each of the project sites. REMA signed separate MoUs with Rwanda Meteorological Agency (Meteo Rwanda), Rwanda Forestry Authority (RFA), Rwanda Standards Board (RSB) and with Nyagatare, Kirehe, Rusizi and Nyamasheke Districts, as well as with the University of Rwanda (UR) and the Higher Education Council (HEC) (for the LTRP), to reflect the planned execution of activities based on the consultations. |

2.6. Gender

| Does the project have a gender action plan? | Yes |
| --- | --- |
| Gender mainstreaming | In the implementation of the different project activities, the integration of gender considerations has been continued in current reporting period. This applies to project implementation from the national to the grassroots level. For example, as part of the participatory approach developed for the Baseline Study, extension officers in the project sites and local authorities, CBOs and CSOs in the remote Districts have engaged in the project’s ecosystem-based adaptation (EbA) interventions across five pilot sites ensure women’s attendance and fair representation in the workshops, to guarantee gender inclusivity and consideration of their needs, capacities, knowledge and role in the communities. In particular, the allocation of project field officers in the pilot Districts has been an important factor in ensuring that the gender considerations identified in the CEO ER, and the Baseline and Feasibility Studies, are fully integrated in project planning and implementation. In this previous reporting period, REMA Gender Monitoring Office (GMO), MoE, MINECOFIN and the project Districts conducted a workshop and developed a Gender Action Plan for the NAP project. In all the trainings and awareness-raising meetings held in the Districts, gender inclusivity has been considered. The project beneficiaries who adopted EbA interventions include a total number of 45,751 women (55.5%) and 36,673 men (44.5%). The project’s MTR report rated its responsiveness to human rights and gender equity as “satisfactory”. It recommended that in the revision of the project results framework, the full inclusions of gender-disaggregated targets is ensured. |

2.7. Environmental and social safeguards management

| Moderate/High risk projects (in terms of Environmental and social safeguards) | Was the project classified as moderate/high risk? No |
| --- | --- |
| New social and/or environmental risks | Have any new social and/or environmental risks been identified during the reporting period? No additional risks have been identified in this reporting period. |
| Complaints and grievances related to social and/or environmental impacts (to be filled in by TM and EA) | Has the project received complaints related to social and/or environmental impacts (actual or potential) during the reporting period? No |
| Environmental and social safeguards management | The project is unlikely to result in any significant, irreversible environmental and/or social impacts as assessed at CEO approval. At the approval stage, it was determined that no Environmental and Social Impact Assessments (ESIA) were necessary to be developed prior to implementation. Comprehensive stakeholder consultations during the project’s Feasibility Study were important in ensuring that potential environmental and social risks were identified, and monitoring and mitigation measures put in place. This stakeholder consultation process, and the way it influenced the design of the adaptation measures, identification of risks, and establishment of mitigation measures is described in the UNEP-led Policy Brief developed in previous reporting period (see Section 2.8 on Knowledge Management). Some additional or modified potential risks of unintended environmental and social impacts have been identified during project implementation (in previous reporting periods), as outlined below. The project has two pilot sites within and adjacent to areas of biodiversity importance – the Ibanda-Makera Natural Forest in Kirehe District and the Shagasha Natural Forest in Rusizi and Nyamasheke Districts. The project’s Feasibility Study for field interventions, including in these two sites, incorporated further analysis of environmental and social risks. It identified potential environmental and social safeguards risks for each of the interventions planned for the five pilot sites and proposed possible mitigation measures. The design of the interventions, as guided by the Feasibility Study, reflects avoidance of safeguards risks, including the prioritization and selection of native or exotic but non-invasive species that can be easily grown locally are proposed for restoration and agroforestry activities. For example, species selection for agroforestry and woodlot planting activities in the Shagasha Tea estate in Rusizi and Nyamasheke Districts considers the unique ecosystem in nearby Shagasha Natural Forest and Nyungwe Forest National Park. The design of project interventions has also been guided by analysis of land tenure arrangements, community organizations and structures, and community access to resources. The compatibility of activities and implementation approaches with local contexts is being ensured, for example through the involvement of local catchment protection committees and environment committees in the implementation and monitoring of activities. In Ibanda-Makera natural forest (Kirehe District), to avoid the potential exclusion of communities from public land used for agriculture in order to establish the buffer zone, the Feasibility Study foresaw the use of existing roads and fringes of forests for the buffer zone. However, due to the lack of sufficient space between the boundaries of the forest and agricultural lands, in practice it has not been possible for the project to establish the planned buffer zone. Instead, the demarcation of the forest boundary was done along the fringes of the forest. In practice, encroachment into the forest has not been a challenge to date. Communities continue to be allowed to farm and graze their cattle up to the edge of the forest, and to collect grasses and dead wood from the forest. The appropriate use of the forest is monitored by guards put in place by the District. As such, unless new challenges emerge, the establishment of an official buffer zone does not seem to be necessary. The Eastern Province, where Nyagatare and Kirehe Districts are located, is exposed to prolonged drought. Local communities living near wetlands have the tendency to encroach on wetland ecosystems’ buffer zones especially for crop production and livestock grazing during dry season. The implementation of the project’s EbA activities at the Umuvumba river in Nyagatare District has also faced challenges in this regard. Riverbank restoration was undertaken in the 20m buffer zone by the river, which is government land. However, as communities continued using this for agricultural land (cultivation and grazing), there was some resistance to the restoration efforts. This continued despite efforts by the District to build awareness of the importance of the buffer zone as well as to enforce it. In the previous reporting period, a joint collaboration between REMA, Rwanda Water Resources Board (RWB), farmers and the District was established to address this issue. Local communities were authorized to temporarily grow low crops in the buffer zone, at the same time maintaining the bamboos planted by the project for the protection of Umuvumba river. The agreement was that when the bamboos will grow larger, the agricultural activities will be halted – as they will no longer be compatible with the grown bamboos, and the bamboos themselves will no longer need maintenance. In the current reporting period this transition has indeed taken place successfully, and there are no more agricultural activities being undertaken in the buffer zone by the communities. In the previous reporting period, the rehabilitated Nyandungu wetland was fenced and guards deployed around the wetland. This will remove the potential risk of wild animals exiting the wetland area and damaging the property of nearby residents. In the previous reporting period, an Environmental and Social Management Plan (ESMP) for the project was developed by REMA, with lead from SPIU Safeguards Experts. |

2.8. Knowledge management

| Knowledge activities and products | All information related to the advancement of the NAP process in Rwanda, including that related to the project’s monitoring framework, will be documented by the project under Component 3. The information will be disseminated to all actors in the NAP process and will be made available nationally and internationally on online platforms, including REMA and UNEP websites, the media, as well as at international adaptation-related meetings where Rwanda is represented. To date, the project has developed the following assessments and technical knowledge products: - Project feasibility study report - Assessment of meteorological, hydrological and air quality monitoring equipment needs - Public Expenditure Review for Environment and Climate Change (PERECC) report - Downscaled climate projections report and Summary for Policymakers - Climate impact storylines report - 4 catchment-level climate change risk assessments (drafts under finalization) (developed in this reporting period) - 7 published research articles on EbA-related topics, based on research in the project pilot sites (published in this reporting period) In addition, a Policy Brief has been developed with UNEP lead, focusing on the stakeholder-led process for the selection and revision of the project’s EbA measures. In addition to describing the context at each pilot site and the EbA interventions selected, the Policy Brief identifies lessons learnt for adaptation programming and implementation, building on the experiences of this project, to help learning and to improve the effectiveness of adaptation projects and NAP processes. |
| --- | --- |
| Main learning during the period | One of the main lessons learnt from this reporting period has been on how collaboration and engagement with local communities can help resolve conflicts over land-use. In Nyagatare District, the restoration of the Umuvumba riverbanks with bamboo was previously undertaken by the project in the 20m buffer zone by the river (government land). However, as communities continued using this for agricultural land (cultivation and grazing), there was some resistance to the restoration efforts. A collaboration between REMA, RWB, farmers and the District was established to address this issue, whereby it was agreed with the local communities that they were authorized to temporarily grow low crops in the buffer zone, while at the same time maintaining the bamboos planted by the project. The agreement was that when the bamboos grow, the agricultural activities will be halted – as they will no longer be compatible with the larger bamboo plants, and the bamboos themselves will no longer need maintenance. In the current reporting period this transition has indeed taken place successfully, and there are no more agricultural activities being undertaken in the buffer zone. |

2.9. Stories to be shared

| Stories to be shared | 1. Plantation of Agroforestry Trees The Musheri and Matimba sectors, located in Nyagatare District, are highly vulnerable to prolonged drought and strong seasonal winds. Previously, these areas were largely barren and lacked tree cover, which exacerbated their exposure to harsh climatic conditions. The strong winds, particularly at the onset of the rainy season, frequently caused significant damage to crops and homes. In response, the project launched agroforestry interventions in 2021 by planting trees throughout both sectors. Five years later, the results are clearly visible. Local testimonies from residents and community leaders report: • A significant reduction in wind intensity, • Availability of firewood which is the main source of cooking energy, • No recent cases of wind-related destruction of houses or crops, • Increased environmental stability and improved local resilience to climate impacts. This successful intervention demonstrates the effectiveness of agroforestry in enhancing climate resilience, protecting livelihoods, and contributing to sustainable land management in drought-prone areas. 2. Provision of Dam Sheets to Cattle Keepers In the Rwempasha and Rwimiyaga sectors in Nyagatare District, cattle rearing was traditionally done through open grazing, which contributed to land degradation and increased vulnerability to climate change. To address these challenges, the project distributed dam sheets to cattle keepers to enable rainwater harvesting for livestock consumption. This intervention aimed to reduce environmental pressure, erosion and enhance climate resilience in the livestock sector. Three years later, testimonies from beneficiaries, local communities, and authorities report several key benefits: • Increased milk production • Reduced spread of livestock diseases • Significant decrease in community conflicts over crop damage caused by free-grazing animals This experience demonstrates that simple, locally adapted solutions can have a meaningful impact on both livelihoods and ecosystem resilience. |
| --- | --- |

# 3. PROJECT PERFORMANCE AND RISK

Based on inputs by the Project Manager, the UNEP Task Manager will make an overall assessment and provide ratings of:

- Progress towards achieving the project Results(s)- see section 3.1

- Implementation progress – see section 3.2

Section 3.3 on Risk should be first completed by the Project Manager. The UNEP Task Manager will subsequently enter his/her own ratings in the appropriate column.

3.1	Rating of progress towards achieving the project outcomes (Development Objectives)

| Project objective and Outcomes | Indicator | Baseline level | Mid-term target | End-of-project target | Progress as of current period (%) | Summary by the EA of attainment of the indicator & target as of 30 June 2025 | Progress rating |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Objective: Increased capacity of governmental authorities and local communities in Rwanda to plan, fund, implement and monitor climate change adaptation solutions in the medium to long-term. | Degree to which the technical and institutional capacity of targeted governmental institutions, district-level stakeholders and local communities is strengthened at national and sub-national levels to advance Rwanda’s NAP process. | Majority of assessed governmental institutions during the baseline study has the capacity and preparedness to advance NAP process varying between 30% and 50% except REMA and RDB with 70% and 75% respectively. | N/A | Increase up to at least 70% the capacity of all 16 governmental institutions to advance NAP process (Max 100%, Min 0%). | 60 | To date, the capacity of 30 governmental institutions (15 at the national and 15 at the district level) to advance the NAP process has been increased through trainings and other capacity building activities organized by the project (outlined below). The quantitative increase in capacity will be measured by the results verification exercise to be undertaken before the project’s Terminal Review. Furthermore, the project’s MTR recommended clarifying the project’s objective and the indicator / target, to better articulate the focus on NAP process and ensure that the target is aligned with the indicator. The capacity of targeted project stakeholders has continued to be built through their full engagement in the planning and implementation of the project activities. In particular, the ongoing catchment-level climate risk assessment process has involved strong stakeholder engagement, with NAP Technical Working Group members being engaged in the review of the draft reports for the four project catchments. The climate change risk assessment process has also included significant capacity building aspects, in particular, in the previous reporting period, through the engagement of stakeholders in data collection, field visits to the four catchments and stakeholder consultations. A national capacity building workshop on the climate risk assessment process was conducted in November 2023. In this reporting period, no additional training workshops have been organized by the project. A plan for a training-of-trainers programme on the NAP process and adaptation, targeting public and private sectors, CSOs and local communities, is currently being developed and a suitable service provided is being identified. In previous reporting periods, the meteorological monitoring capacity of Rwanda Meteorology Agency (Meteo Rwanda) and Rwanda Standards Board (RSB) was enhanced through the establishment of a Calibration Center for Meteorological, Hydrological and Air Quality Monitoring Instruments, which is now fully operational. At the district and local levels, training workshops were organized in September 2022 (for Rusizi and Nyamasheke Districts) and August 2023 (for Kirehe and Nyagatare) on ecosystem-based adaptation and raising awareness of the NAP project. The total number of participants for the workshops was 441 (143 women and 298 men). The Rusizi workshop was attended by 202 participants (69 women and 133 men), the Nyamasheke one by 67 participants (27 women and 40 men), and 172 people participated in the trainings in Kirehe and Nyagatare (47 women and 125 men). The workshops built the capacity of environmental committees and other project stakeholders at district, sector and cell levels to understand emerging challenges in environment and climate change and mechanisms to ensure sustainability, discuss responsibilities for conservation, protection and promotion of environment as well as for addressing climate change, and to discuss with environmental committees and stakeholders on the project progress and their engagement in its implementation. Also in previous reporting periods, the NAP Technical Working Group (TWG) was established, and members were nominated by their respective institutions. The TWG provides technical advice and engagement on a broad range of matters related to national climate change adaptation planning, in the process also strengthening the capacity of the engaged institutions to advance long-term adaptation planning. Also in previous reporting periods, REMA partnered with Rwanda Meteorology Agency (Meteo Rwanda) to strengthen the technical capacity of Meteo Rwanda and other key partners to generate and downscale global and regional climate change model projections. Five training workshops on generating climate projections were provided to Meteo Rwanda technical staff and staff from other key institutions. As a result, in the future these institutions will be able to generate the downscaled projections by themselves. The technical report and summary for policy makers for the downscaled climate change projections were finalized. The updated Public Expenditure Review for Environment and Climate Change (PERECC) report was finalized, with the final stakeholder validation workshop organized in July 2022. As part of the process, a training was provided to the staff from different institutions on conducting public expenditure reviews for environment and climate change. These institutions included the Ministry of Finance and Economic Planning, Rwanda Green Fund (FONERWA), the Ministry of Environment, the Ministry of Agriculture, the Ministry of Infrastructure, the Ministry in Charge of Emergency Management, etc. Following its finalization, REMA presented the PERECC and its findings to Ministry of Environment and Ministry of Finance and Economic Planning. The information will be used by sectors and districts in reporting on how environment and climate change performance indicators have been integrated in their planning and budgeting. Rwanda has also developed a climate budget tagging framework to improve the integration of climate change into the National Accounting System. Finally, an initial awareness-raising programme on the EbA interventions and their benefits was implemented by the project in all districts in the second half of 2021, as the implementation of the interventions was getting underway. Targeted awareness raising has been continued since then on a continuous basis. | MS |
| Outcome 1: Technical and institutional capacity for the NAP process in Rwanda strengthened using up-to-date climate information. | Increase in adaptation planning capacities among national staff across targeted governmental institutions, district- and catchment-level committees and senior high school teachers in the five project sites. | Majority of investigated institutions has the capacity to advance NAP process varying between 30% and 50% except REMA and RDB with 70% and 75%. | N/A | Increase up to at least 70% the capacity of all 16 governmental institutions to advance NAP process (Max 100%, Min 0%). | 60 | In line with the MTR recommendation, the indicator for Outcome 1 will be revised, as it currently duplicates the Objective indicator. The new suggested indicator will be presented to the next Project Steering Committee (PSC) meeting (November 2025) for approval. In this reporting period, the capacity of targeted project stakeholders has continued to be built through their full engagement in the planning and implementation of the project activities. In particular, the ongoing catchment-level climate risk assessment process has involved strong stakeholder engagement, with NAP Technical Working Group members being engaged in the review of the draft reports for the four project catchments. The climate change risk assessment process has also included significant capacity building aspects, in particular, in the previous reporting period, through the engagement of stakeholders in data collection, field visits to the four catchments and stakeholder consultations. A national capacity building workshop on the climate risk assessment process was conducted in November 2023. In this reporting period, no additional training workshops have been organized by the project. A plan for a training-of-trainers programme on the NAP process and adaptation, targeting public and private sectors, CSOs and local communities, is currently being developed and a suitable service provided is being identified. In previous reporting periods, the meteorological monitoring capacity of Rwanda Meteorology Agency (Meteo Rwanda) and Rwanda Standards Board (RSB) was enhanced through the establishment of a Calibration Center for Meteorological, Hydrological and Air Quality Monitoring Instruments, which is now fully operational. At the district and local levels, training workshops were organized in September 2022 (for Rusizi and Nyamasheke Districts) and August 2023 (for Kirehe and Nyagatare) on ecosystem-based adaptation and raising awareness of the NAP project. The total number of participants for the workshops was 441 (143 women and 298 men). The Rusizi workshop was attended by 202 participants (69 women and 133 men), the Nyamasheke one by 67 participants (27 women and 40 men), and 172 people participated in the trainings in Kirehe and Nyagatare (47 women and 125 men). The workshops built the capacity of environmental committees and other project stakeholders at district, sector and cell levels to understand emerging challenges in environment and climate change and mechanisms to ensure sustainability, discuss responsibilities for conservation, protection and promotion of environment as well as for addressing climate change, and to discuss with environmental committees and stakeholders on the project progress and their engagement in its implementation. Also in previous reporting periods, the NAP Technical Working Group (TWG) was established, and members were nominated by their respective institutions. The TWG provides technical advice and engagement on a broad range of matters related to national climate change adaptation planning, in the process also strengthening the capacity of the engaged institutions to advance long-term adaptation planning. Also in previous reporting periods, REMA partnered with Rwanda Meteorology Agency (Meteo Rwanda) to strengthen the technical capacity of Meteo Rwanda and other key partners to generate and downscale global and regional climate change model projections. Five training workshops on generating climate projections were provided to Meteo Rwanda technical staff and staff from other key institutions. As a result, in the future these institutions will be able to generate the downscaled projections by themselves. The technical report and summary for policy makers for the downscaled climate change projections were finalized. The updated Public Expenditure Review for Environment and Climate Change (PERECC) report was finalized, with the final stakeholder validation workshop organized in July 2022. As part of the process, a training was provided to the staff from different institutions on conducting public expenditure reviews for environment and climate change. These institutions included the Ministry of Finance and Economic Planning, Rwanda Green Fund (FONERWA), the Ministry of Environment, the Ministry of Agriculture, the Ministry of Infrastructure, the Ministry in Charge of Emergency Management, etc. Following its finalization, REMA presented the PERECC and its findings to Ministry of Environment and Ministry of Finance and Economic Planning. The information will be used by sectors and districts in reporting on how environment and climate change performance indicators have been integrated in their planning and budgeting. Rwanda has also developed a climate budget tagging framework to improve the integration of climate change into the National Accounting System. Finally, an initial awareness-raising programme on the EbA interventions and their benefits was implemented by the project in all districts in the second half of 2021, as the implementation of the interventions was getting underway. Targeted awareness raising has been continued since then on a continuous basis. | MS |
| Outcome 2: Climate-resilient technologies and practices adopted and scaled up. | Pilot sites established under the LTRP to conduct research on the financial and economic effectiveness of EbA. | 0 EbA pilot sites with operational EbA activities. | N/A | Five EbA pilot sites in four catchments established. | 100 | In previous reporting periods: Five pilot sites in four catchments were established and MoUs signed between REMA, RFA and Nyagatare, Kirehe, Nyamasheke and Rusizi Districts for the implementation of EbA interventions. An MoU between REMA, HEC and University of Rwanda was developed which has guided the research activities conducted at the pilot sites. The Feasibility Study developed articulates the plans for implementing the LTRP in detail, including research questions, proposed governance arrangement, and integration with the pilot activities. | S |
|  | Project beneficiaries helped to adopt adaptation technologies and practices to climate change at the five EbA pilot sites. | 0 people who have been benefiting from adaptation technologies and practices implemented by NAP. | N/A | At least 20,000 people benefited from adaptation technologies and practices at the five pilot sites. | 538 | The total number of project beneficiaries to date (June 2025) is 107,608, of whom 55,374 (i.e. 51.5%) are female. The total beneficiaries’ number is broken down at the District level as follows: - Kirehe District: 4,395 (2,173 Female; 2,222 Male) - Nyagatare District: 35,339 (18,094 Female; 17,246 Male) - Rusizi District: 42,457 (21,722 Female, 20,735 Male) - Nyamasheke District: 25,417 (13,385 Female; 12,032 Male) These numbers comprise the direct beneficiaries (at the household level) of the adaptation technologies and practices introduced by the project at the five EbA pilot sites. | HS |
|  | Land managed sustainably for long-term adaptation at the pilot sites. | 0 hectares managed sustainably for long-term adaptation at the pilot sites. | N/A | 7,030 hectares of land managed sustainably for long-term adaptation at the LTRP’s pilot sites by the end of the project’s implementation period. | 142 | The target has been exceeded, with 9,974 ha of land currently managed sustainably through EbA interventions implemented by the project in Nyagatare, Kirehe, Rusizi and Nyamasheke Districts for long-term adaptation. In this reporting period, handovers from the contractors to the Districts have been completed in Kirehe, Nyagatare and Rusizi Districts, with the handover in Nyamasheke planned for January 2026. Maintenance (preparation of nurseries, weeding, replacement of trees and clearing of ditches) has continued in all the districts in this reporting period. The formal handover from REMA to the Districts will be undertaken in Q4 2025, following the finalization of the handover reports. The EbA interventions implemented include reforestation, simple and complete agroforestry, silvo-pastoralism, woodlot plantation, riverbank protection and revegetation, and restoration of natural forest. The achievements in the project Districts for the various EbA interventions are detailed in Table 1 below. Detailed information on the survival rates for the various interventions and Districts, which average at around 86%, is provided in Table 2. Table 1: Final hectare achievements for the project’s EbA interventions District; EbA intervention; Achievement. Nyagatare (Eastern Savannas); Silvo-pastoralism; 915 ha. Sub-total; 915 ha. Nyagatare (Umuvumba river); Agroforestry; 1,890 ha. Restoration of gallery forest; 140 ha. Woodlot; 255 ha. Revegetation and protection of Umuvumba and Ngoma riverbanks; 85 ha *43.8 ha at Umuvumba *41.5 ha at Ngoma. Trenches in forest; 261 ha. Fruit trees; 59,572 seedlings. Sub-total; 2,631 ha. Kirehe; Agroforestry; 1,435 ha. Complete agroforestry (Tree planting, trenches excavation and stabilization in agricultural lands); 420 ha. Woodlot; 445 ha. Restoration of Ibanda-Makera natural forest; 77 ha. Demarcation of forest perimeter with live fence; 5 km. Sub-total; 2,377 ha. Rusizi; Simple agroforestry (Tree planting in agricultural lands); 1,400 ha. Complete agroforestry; 998 ha. Reforestation; 293 ha. Trenches in forests; 452 ha. Fruits trees (avocados, guavas, mangos and tree tomatoes); 132,130 seedlings. Sub-total; 3,143 ha. Nyamasheke; Simple agroforestry; 442 ha. Complete agroforestry; 345 ha. Fruit trees (avocados and mangos); 20,890 seedlings. Sub-total; 787 ha. Gasabo and Kicukiro; Restoration of Nyandungu wetland (stream widening, drainage channels, wetland and fen restoration, living fence and medicinal garden); 121 ha. Sub-total; 121 ha. TOTAL; 9,974 ha. | HS |
|  |  |  |  |  | Table 2: Survival rates for the projects EbA interventions District; Intervention; Survival rate; Average survival rate. Nyagatare; Afforestation (woodlots); 90.9%; 83.2%. Simple agroforestry; 80.1%. Restoration of Umuvumba gully forests; 80.6%. Silvo-pastoralism within paddock (Phase I); 79.2%. Silvo-pastoralism adjacent to paddock (Phase I); 81.1%. Silvo-pastoralism within paddock (Phase II); 83.3%. Silvo-pastoralism adjacent to paddock (Phase II); 84.7%. Protection of Umuvumba riverbanks; 85.9%. Kirehe; Afforestation (woodlots); 82.2%; 84.7%. Restoration of degraded forest; 90.3%. Simple agroforestry; 84.1%. Complete agroforestry; 82.2%. Rusizi; Complete agroforestry (Phase I); 83.6%; 88.9%. Simple agroforestry; 87.3%. Reforestation (Phase I); 92.1%. Complete agroforestry (Phase II); 91.1%. Reforestation (Phase II); 90.6%. Nyama-sheke; Simple agroforestry; 88.7%; 87.8%. Complete agroforestry; 86.9%. |  |
| Outcome 3: Capacity for monitoring, reviewing and knowledge-sharing to learn from the NAP process in Rwanda increased. | NAP process integrated in the MoE Result Based Monitoring and Evaluation system (RBME). | NAP process is not yet integrated in RBME though it is available in Ministry of Environment. | N/A | NAP indicators to be integrated in RBME. | 10 | In this reporting period, the recruitment of the Adaptation Monitoring & Knowledge Management consultant was advanced and is expected to be completed in Q3 2025. As part of their tasks, the consultant will review existing monitoring and reviewing systems (e.g., the RBME system of the MoE) so that they can be updated to accommodate specific M&E requirements for long-term adaptation outcomes. In this reporting period, through its engagement in Rwanda’s NDC 3.0 process, the project has contributed to the refinement of the NDC’s adaptation indicators. These will feed into and inform the activities to be undertaken under project Component 3. | MU |

3.2	Rating of progress implementation towards delivery of outputs (Implementation Progress)

| Outputs/Activities | Expected completion date | Implementation status as of 30 June 2024 (%) | Implementation status as of 30 June 2025 (%) | Progress rating justification, description of challenges faced and explanations for any delay | Progress rating |
| --- | --- | --- | --- | --- | --- |
| COMPONENT 1: Technical and institutional capacity for the NAP process in Rwanda. Outcome 1: Technical and institutional capacity for the NAP process in Rwanda strengthened using up-to-date climate information. |  |  |  |  |  |
| Output 1.1: NAP technical working group (TWG) established. | Q2 2025 | 60 | 70 | In this reporting period, Technical Working Group members were engaged in the review of the draft climate risk assessment reports for the four project catchments. They will further be involved in the review and validation of the various reports and other outputs being developed under the project. In previous reporting periods, the NAP Technical Working Group was established, members were nominated by their respective institutions, and the TORs were agreed and signed accordingly. Different subsets of Technical Working Group (TWG) members have been engaged to provide guidance and validation for various activities implemented during the reporting period, such as the inception phase of the climate risk assessments work. However, the full operationalization of the TWG and the building of its capacity through training workshops still remains to be implemented, and as such the completion of the output is delayed. The capacity building will be done as part of the NAP process, in the final year of project implementation. | MS |
| Output 1.2: Downscaled catchment-level climate projections for Rwanda developed. | Q2 2021 | 100 | 100 | The output was completed in previous reporting periods. A calibration centre for meteorological, hydrological and air quality monitoring instruments was established and is operational. The calibration centre is composed of a meteorological calibration laboratory, hydrological laboratory and air quality laboratory, and supports Meteo Rwanda and Rwanda Standards Board (RSB) in strengthening the country’s meteorological monitoring capacity. This builds on an assessment of meteorological, hydrological and air quality monitoring equipment needs conducted under the project, and a list of equipment and materials needed that was developed, in the context of an MoU between REMA and Meteo Rwanda. A technical report and summary for policy makers for downscaled catchment-level climate projections were developed. The technical capacity of staff to generate and downscale global and regional climate model projections to national and sub-national scales was strengthened, targeting staff from Meteo Rwanda, Rwanda Civil Aviation Authority, the University of Rwanda, Rwanda Space Agency and Rwanda Airport Company. Five training workshops were organized between September 2021 and January 2022. | S |
| Output 1.3: Climate risk assessments for four catchments developed. | Q2 2025 | 70 | 75 | In the current reporting period, the development of the climate risk assessment reports for the four project catchments has been taking place. The Climate Storylines report was completed, following the incorporation of feedback provided by REMA and UNEP. The four catchment-level climate risk assessment reports have also been drafted in this reporting period. However, their finalization has been delayed, due challenges in access to necessary data and insufficient communication between the service provider and Meteo Rwanda. These challenges have now largely been resolved and the reports are expected to be finalized and validated by Q4 2025. In previous reporting period, data collection, field visits to the four catchments and stakeholder consultations were undertaken as part of the climate risk assessment study. The capacity building workshop on the climate risk assessment process, targeting the technical committee, was conducted in November 2023 for stakeholder engagement. The initiation of activities under this output had experienced significant delays due to failed procurement process by REMA, after which UNEP was requested to undertake the procurement on behalf of REMA. | MS |
| Output 1.4: CCA strategies developed for the four catchments based on climate risk assessments. | Q3 2025 | 5 | 5 | The initiation of activities under this output has been delayed, as the climate risk assessments under Output 1.3 need to be further advanced first. REMA has initiated discussion with University of Rwanda on this assignment, to be launched in Q4 2025. | MS |
| Output 1.5: CCA measures from catchment-level adaptation strategies extrapolated to the national level to develop adaptation plans for three priority economic sectors. | Q3 2025 | 5 | 5 | The initiation of activities under this output has been delayed, as the climate risk assessments under Output 1.3 need to be further advanced first. REMA has initiated discussion with University of Rwanda on this assignment, to be launched in Q4 2025. | MS |
| Output 1.6: Refinement of NDC adaptation priorities related to the sectoral adaptation plans and LTRP. | Q3 2025 | 5 | 70 | The NDC 3.0 process has been significantly advanced in Rwanda, including the refinement of adaptation priorities. In this reporting period, the project has contributed to the development of the various Terms of References and the review of the NDC 3.0 and its adaptation priorities. The NDC adaptation priorities and the consultation undertaken as part of the NDC process will help to inform the development of the catchment adaptation strategies and sectoral adaptation plans under project Outputs 1.4 and 1.5. The development of guidelines for the implementation of updated NDC adaptation priorities to be undertaken by the project will be undertaken in conjunction with activities under these two outputs. | S |
| Output 1.7: Training manuals and awareness-raising events for public and private sectors, CSOs and local communities on the NAP process. | Q4 2025 | 30 | 30 | In this reporting period, no additional training workshops have been organized. A plan for a training-of-trainers programme on the NAP process and adaptation, targeting public and private sectors, CSOs and local communities, is currently being developed and a suitable service provided is being identified. In previous reporting periods, training workshops on ecosystem-based adaptation and raising awareness of the NAP project were organized in Kirehe and Nyagatare Districts (in August 2023) as well as Rusizi and Nyamasheke Districts (in September 2022). The total number of participants for the workshops was 441 (143 women and 298 men). Specifically, the Rusizi workshop was attended by 202 participants (69 women and 133 men), the Nyamasheke one by 67 participants (27 women and 40 men), and 172 people participated in the trainings in Kirehe and Nyagatare (47 women and 125 men). The workshops built the capacity of environmental committees and other project stakeholders at district, sector and cell levels to understand emerging challenges in environment and climate change and mechanisms to ensure sustainability, discuss responsibilities for conservation, protection and promotion of environment as well as for addressing climate change, and to discuss with environmental committees and stakeholders on the project progress and their engagement in its implementation. | MS |
| COMPONENT 2: Advancing climate-resilient practices and technologies under the NAP process. Outcome 2: Climate-resilient technologies and practices adopted and scaled up. |  |  |  |  |  |
| Output 2.1: A NAP funding strategy developed. | Q4 2025 | 60 | 60 | The procurement process is currently underway for the remaining activities under this output. These activities were not advanced in this reporting period and are delayed due to the need to first complete other project outputs. The remaining activities under this output (assessing the funding gap and developing the cross-sectoral funding strategy) can only be undertaken once activities under Output 1.4 and 1.5 are advanced. In terms of the content of the funding strategy to be developed, the project’s MTR recommended integrating elements that would help ensure the longer-term sustainability of the project’s results. In the previous reporting periods, the updated Public Expenditure Review for Environment and Climate Change (PERECC) report was finalized, with the final stakeholder validation workshop organized in July 2022. Trends on public expenditures and expenditures specific to environment and climate change were analysed following the major standard public expenditure review themes of public allocation and expenditure trends, public expenditure composition, efficiency of public spending, targeting of expenditure and public expenditure management. The general results of the review have highlighted several strengths and successes the government has achieved over the period in terms of erecting strategic and policy approaches and aligning its institutional infrastructure with the emerging demands of climate change. Following its finalization, REMA presented the PERECC and its findings to Ministry of Environment and Ministry of Finance and Economic Planning. The information will be used by sectors and districts in reporting on how environment and climate change performance indicators have been integrated in their planning and budgeting. Rwanda has also developed a climate budget tagging framework to improve the integration of climate change into the National Accounting System. Furthermore, the PERECC report is being used by the World Bank through the “Climate-PIMA” (C-PIMA) framework which assesses countries’ capacity to manage climate-related infrastructure. | MS |
| Output 2.2: Recommendations for relevant ministries on the mainstreaming of CCA into their budgeting and planning processes developed. | Q4 2025 | 0 | 0 | To be implemented in of the final year of project implementation, drawing on the reports for climate risk assessment for the four catchments (Output 1.3) and Climate Change Adaptation Strategies (Output 1.4) and Sectoral Adaptation Plans (Output 1.5). | S |
| Output 2.3: Long-term research programme established to address gaps in knowledge needed to inform adaptation planning and funding in Rwanda. | Q4 2025 | 75 | 95 | In this reporting period, 23 MSc students supported by the project completed their degrees and their research projects on EbA-related topics in the project pilot sites, as well as in the intervention sites of the LDCF-funded EbA project. In the previous reporting period, the MSc students had completed their class coursework. Also under the LTRP, in this reporting period, 7 research articles on EbA-related topics were published by university researchers based on research in the project pilot sites (as well as those of the LDCF-funded EbA project). Several more articles will be published from the 11 research projects funded by the project. The research projects study various aspects of EbA in the project sites, including mapping and valuing EbA practices in farmlands, the use of bioindicators to monitor adaptation outcomes, the role of women’s capacity building in reducing vulnerability, and the role of agroforestry in reducing deforestation and land degradation. It should be noted that the project’s MTR recommended the inclusion in the project’s results framework of an indicator specifically focused on the LTRP, to ensure that the benefits from its activities are fully tracked. In the previous reporting period, a training was conducted by REMA in January 2023 to train the MSc students and their supervisors on the concept of Ecosystem-based Adaptation (EbA), data collection and research methodology tailored for EbA activities. Furthermore, an assessment and evaluation of the progress of the ongoing research was conducted in a workshop organized in Musanze District in May 2024. In 2021, in the context of the LTRP launch, an MoU between REMA, the Higher Education Council and the University of Rwanda was developed to guide the research activities to be conducted at the pilot sites. | S |
| Output 2.4: EbA interventions implemented in five pilot sites based on CCA strategy and implementation protocol developed. | Q4 2025 | 96 | 100 | During this reporting period, the implementation of all the EbA interventions was completed, with the total area of land managed sustainably for long-term adaptation being 9,974 ha (compared with an original target of 7,030 ha). The interventions and achievements in terms of numbers of hectares are detailed under Outcome 2 indicator (iii) in PIR Section 3.1 (marked as Table 1). Handovers from the contractors to the Districts have been completed in Kirehe, Nyagatare and Rusizi Districts, with the handover in Nyamasheke planned for January 2026. Maintenance (preparation of nurseries, weeding, replacement of trees and clearing of ditches) has continued in all the districts in this reporting period. The formal handover from REMA to the Districts will be undertaken in Q4 2025, following the finalization of the handover reports. The overall survival rate of planted trees is relatively high; currently at around 86%. The survival rate by District and intervention type are detailed under Outcome 2 indicator (iii) in PIR Section 3.1 (marked as Table 2). The following EbA interventions have been implemented at 5 sites: - Implementation of agroforestry as well as silvo-pastoralism to strengthen livestock production and increase forest cover of savannas in the Nyagatare district; - Demarcation and protection of a buffer zone on the banks of the Umuvumba river and its tributaries in the Nyagatare district through the restoration of riparian vegetation (which will buffer floods and arrest erosion), and the reforestation of upstream catchment areas; - Re-establishment of a buffer zone, restoration of natural forest, promotion of agroforestry with drought-resilient tree species, and introduction of beekeeping benefitting 36 community members (23 women, 13 men) around Ibanda-Makera Natural Forest in the Kirehe district to protect this ecosystem and enhance the livelihoods of local farmers; - Implementation of agroforestry, intercropping and the stabilising of plantation verges with vegetation (agroforestry with trenches) at the Shagasha Tea Estate (Rusizi and Nyamasheke Districts) to enhance the climate-resilience of associated livelihoods against the negative effects of climate change; and - Restoration of a section of Nyandungu wetland (in Kigali City, Gasabo District) through landscape restoration and plantation of medicinal garden. In addition, in Rusizi District 100 rainwater harvesting tanks (of which 39 in this reporting period) were installed by the project in vulnerable communities to provide water for household consumption, as well as to reduce erosion resulting from streams of water flowing from roofs. Furthermore, five (5) small-scale irrigation schemes irrigating a total area of 55 ha were provided in previous reporting periods to local communities in Eastern Province (3 in Nyagatare and 2 in Kirehe District), where rain-fed agriculture is disproportionately affected by water shortages associated with droughts. Finally, 132 dam sheets were provided in previous reporting periods, to local communities in Nyagatare for capturing rainwater for animals and domestic use. The main objective is to alleviate the impact of drought on pastures and to stop cattle from moving to the riverbanks of Umuvumba river during the dry season. | HS |
| Output 2.5: Strengthened awareness of the private sector on national adaptation priorities, future climate scenarios, risk assessments and investment opportunities, to stimulate the implementation of CCA. | Q4 2025 | 0 | 0 | To be implemented in the final year of project implementation, with some delay due to the need to complete other project activities first. The training under this output will be combined with that under Output 1.7. | MS |
| COMPONENT 3: Monitoring, reviewing and knowledge-sharing to learn from the NAP process in Rwanda. Outcome 3: Capacity for monitoring, reviewing and knowledge-sharing to learn from the NAP process in Rwanda increased. |  |  |  |  |  |
| Output 3.1: A framework for the monitoring of long-term CCA outcomes developed. | Q4 2025 | 5 | 10 | In this reporting period, through its engagement in Rwanda’s NDC 3.0 process, the project has contributed to the refinement of the NDC adaptation priorities, and the development of the NDC monitoring framework and indicators. These will feed into and inform the activities to be undertaken under Outputs 3.1 and 3.2. Furthermore, the recruitment of the Adaptation Monitoring & Knowledge Management consultant was advanced and is expected to be completed in Q3 2025. Overall, the implementation of the activities under this output has been delayed. This is due to insufficient coordination between relevant institutions and the resultant lack of clarity on the advancements already made in this area by various institutions. As recommended in the project’s MTR, as a first step, a comprehensive review of existing monitoring and reviewing systems (e.g. the RBME system of the MoE) will be undertaken, so that this project can best address the remaining gaps. | MU |
| Output 3.2: Adaptation indicators mainstreamed into the main sectoral and development monitoring frameworks. | Q4 2025 | 5 | 10 | In this reporting period, through its engagement in Rwanda’s NDC 3.0 process, the project has contributed to the refinement of the NDC adaptation priorities, and the development of the NDC monitoring framework and indicators. These will feed into and inform the activities to be undertaken under Outputs 3.1 and 3.2. Furthermore, the recruitment of the Adaptation Monitoring & Knowledge Management consultant was advanced and is expected to be completed in Q3 2025. The implementation of the activities under this output is somewhat delayed, for the reasons outlined under Output 3.1. | MS |
| Output 3.3: Progress reports and communication material to learn from the formulation, implementation, funding and monitoring of the NAP process. | Q4 2025 | 10 | 10 | In this reporting period, the recruitment of the Adaptation Monitoring & Knowledge Management consultant was advanced and is expected to be completed in Q3 2025. The implementation of the activities under this output are somewhat delayed, for the reasons outlined under Output 3.1. In previous reporting periods, a Policy Brief was developed with UNEP lead, focusing on the stakeholder-led process for the selection and revision of the project’s EbA measures. In addition to describing the context at each pilot site and the EbA interventions selected, the Policy Brief identifies some lessons learnt for adaptation programming and implementation, building on the experiences of this project, to help learning and to improve the effectiveness of adaptation projects and NAP processes. | MS |

4. Risk Rating

4.1 Table A. Project management Risk

Please refer to the Risk Help Sheet for more details on rating.

| Risk Factor | EA’s Rating | TM’s Rating |
| --- | --- | --- |
| 1. Management structure – Roles and responsibilities | L | L |
| 2. Governance structure – Oversight | L | L |
| 3. Implementation schedule | M | M |
| 4. Budget | L | L |
| 5. Financial Management | L | L |
| 6. Reporting | L | L |
| 7. Capacity to deliver | M | M |

4.2 Table B. Risk-Log

| Risk | Risk affecting: | Risk Rating |  |  |  |  |  |  | Variation respect to last rating |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Outcome / outputs | CEO ED | PIR 1 | PIR 2 | PIR 3 | PIR 4 | PIR 5 (this PIR) | Δ | Justification |
| Risk 1. Theft and vandalism of automatic weather stations (AWS) and climate monitoring equipment undermine accuracy of climate data | Outcomes 1-3 | L | L | L | L | L | L | = | The risk is very low, as Meteo Rwanda has a contract with a security company to guard all their equipment across the country. So far, no incidences of vandalism have been experienced on their facilities. |
| Risk 2. Lack of commitment/buy-in from local communities result in failure of demonstration projects | Outcome 2 | L | L | ML | M | L | L | = | Challenges related to the community ownership of project interventions in Rusizi and Nyagatare districts identified in previous reporting periods have been resolved. Local communities are now playing a very active role in maintenance activities, e.g. in the pruning, weeding, and guarding of the EbA interventions that have been handed over to the Districts. Furthermore, the challenges of encroachment by communities of the Umuvumba river buffer zone (in Nyagatare district) were resolved through a collaboration between REMA, Rwanda Water Resources Board (RWB), farmers and the District. Local communities were authorized to temporarily grow low crops in the buffer zone, at the same time maintaining the bamboos planted by the project for the protection of the river. In the current reporting period, in line with the agreement with the communities, as the bamboos have grown larger the agricultural activities by the communities have successfully been halted in the buffer zone. In general, local communities have a positive attitude towards the project and its activities. Local community members are supportive of project activities because they support their livelihoods such as plantation of fruit trees, establishment of radical terraces and agroforestry in tea plantations, which increases community buy-in and commitment. |
| Risk 3. Delays in policy revision process result in delays in advancing the NAP process | All outcomes & outputs | M | L | L | L | L | L | = | The national Environment and Climate Change Policy was revised in 2019. It promotes climate change adaptation, mitigation and response in general, and specifically the strengthening of adaptation mechanisms in planning and implementation. This provides a favourable policy context for advancing the NAP process. |
| Risk 4. Unavailability of requisite human resources hamper project implementation | All outcomes & outputs | M | S | S | S | S | S | = | Many of the procurement processes for the recruitment of required consultants have been problematic and delayed, due to limited expertise available in the country and the complexity of the procurement system / application requirements for applicants. International consultants, in particular, can be discouraged from applying due to the complexity of the process. This is also reflected in the “moderate” risk ratings assigned to the “implementation schedule” and “capacity to deliver” risk categories in Table 4.1 (above) on project management risks, as this challenge contributes to continued implementation delays and capacity gaps. In the current reporting period, the recruitment of the Adaptation Monitoring & Knowledge Management consultant was somewhat delayed, due to the need to transfer the process from REMA to UNEP. As a few major procurements / recruitments still remain to be undertaken (including for the development of adaptation strategies and plans, and the NAP funding strategy), this risk remains significant for the remaining procurements to be undertaken by the project, as also noted by the project’s MTR. |
| Risk 5. Limited government support for project activities results in delays. | All outcomes & outputs | L | L | L | L | L | L | = | The planned project activities are included in the District Performance Contracts. Handover reports from REMA to the Districts will be developed and handover done in the second half of 2025. Integration of adaptation considerations in District Development Strategies (DDSs) will also be undertaken, as these strategies are updated. |
| Risk 6. Limited ownership of the NAP process by district-level officers | Outcome 2 | L | L | L | L | L | L | = | All project activities in the Districts are prepared and executed in collaboration with District staff, particularly the District Directors of Agriculture and Natural Resources and the District Environment Officers. Moreover, there are MoUs in place with all the intervention Districts, where the roles of each institution are clearly defined. The project activities are also embedded in the Districts’ annual performance contracts. |
| Risk 7. COVID-19 related delays | All outcomes & outputs |  | M | L | L | L | L | = | The impacts of COVID-19 pandemic on project implementation in the current reporting period have been very limited. |
| Risk 8. Vulnerability of tree seedlings to drought and other damages in parts of Kirehe and Nyagatare Districts | Outcome 2 |  |  | M | M | M | M | = | Although the current average survival rate of the planted trees is fairly good at around 86%, their vulnerability to drought and other damages still remains an important risk. The damages to young trees planted have been due to a variety of reasons, including drought and prolonged dry season, termites and cattle damage in some parts of project intervention areas. |
| Risk 9. Potential unintended negative environmental and/or social impacts of new activities: solar irrigation and dams | Outcome 2 |  |  | L | L | L | L | = | Solar-powered irrigation systems (using river water) and excavation of small dams have been undertaken in Nyagatare and Kirehe Districts. To date, there have been no reports of any negative environmental or social impacts from these activities. After preparation of the draft handover reports, project staff will do a final assessment, so that any mitigation measures that might be needed can be included in the handover. Some potential risks could include over extraction of water and dam-related safety risks for humans and livestock. |
| Consolidated project risk |  | L | L | L | L | L | L | = |  |

4.3 Table C. Outstanding medium & high risks

| Risk | Actions decided during the previous reporting instance (PIRt-1, MTR, etc.) | Actions effectively undertaken this reporting period | Additional mitigation measures for the next periods |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  |  | What | When | By whom |
| Risk 4. Unavailability of requisite human resources hamper project implementation. (Specifically due to challenges with procurement processes) | Actions identified in the previous PIRs: Potential qualified applicants will be widely reached out to for the upcoming REMA recruitments, as also recommended by the project’s MTR. | In the current reporting period, there haven’t been any procurement or recruitment processes undertaken by REMA. | In next reporting period, potential qualified applicants will be widely reached out to for the upcoming REMA recruitments, as also recommended by the project’s MTR. | During procurement processes | PMU |
| Risk 8. Vulnerability of tree seedlings to drought and other damages in parts of Kirehe and Nyagatare Districts. | Actions identified in the previous PIR: Now that the saplings have grown into young trees and the interventions have been handed over by the project, the engagement of the direct beneficiaries in their protection will be particularly important. The beneficiaries will be encouraged to monitor and provide care for the young plants. This will include watering where needed, as well as continued planting of Euphorbia for termite protection. Support will be provided by the Districts and RAB where needed. Replacement planting will be undertaken by the Districts where there are losses. | Damaged seedlings have been replaced by the Districts and local communities during the maintenance phase of the interventions. Overall, direct project beneficiaries have been engaged in the maintenance of the project interventions, including the tree seedlings. | Same mitigation measures will be continued in the next reporting period. After the handover from REMA to the Districts, the maintenance of the interventions will continue by the communities | Ongoing | PMU, RAB, Kirehe and Nyagatare Districts |

High Risk (H): There is a probability of greater than 75% that assumptions may fail to hold or materialize, and/or the project may face high risks. 
Significant Risk (S): There is a probability of between 51% and 75% that assumptions may fail to hold and/or the project may face substantial risks. 
Medium Risk (M): There is a probability of between 26% and 50% that assumptions may fail to hold or materialize, and/or the project may face only modest risks. 
Low Risk (L): There is a probability of up to 25% that assumptions may fail to hold or materialize, and/or the project may face only modest risks.

5. Project Minor Amendments

5.1 Table A: Listing of all Minor Amendment

|  | Results framework | Minor project objective change |
| --- | --- | --- |
|  | Components and cost | Safeguards |
|  | Institutional and implementation arrangements | Risk analysis |
|  | Financial management | Increase of GEF project financing up to 5% |
|  | Implementation schedule | Co-financing |
|  | Executing Entity | Location of project activity |
|  | Executing Entity Category | Other |

| Minor amendments | [Provide a description of the change that occurred in the fiscal year of reporting] |
| --- | --- |

| Version | Type | Signed/Approved by UNEP | Entry into Force (last signature date) | Agreement Expiry Date | Main changes introduced in this revision |
| --- | --- | --- | --- | --- | --- |
| Original legal instrument | PCA | 29 October 2019 | 29 October 2019 | 30 September 2024 |  |
| Amended legal instrument | PCA | 1 October 2024 | 1 October 2024 | 31 December 2026 | Extension of the PCA duration from 30 September 2024 to 31 December 2026 on a “no cost” basis. Revision of the amount allocated to the Executing Agency (REMA), to account for the procurements (to be) done directly by UNEP. |

5.2 Table B: History of project revisions and/or extensions

6. GEO Location Information

The Location Name, Latitude and Longitude are required fields insofar as an Agency chooses to enter a project location under the set format. The Geo Name ID is required in instances where the location is not exact, such as in the case of a city, as opposed to the exact site of a physical infrastructure. The Location & Activity Description fields are optional. Project longitude and latitude must follow the Decimal Degrees WGS84 format and Agencies are encouraged to use at least four decimal points for greater accuracy. Users may add as many locations as appropriate. Web mapping applications such as OpenStreetMap or GeoNames use this format. Consider using a conversion tool as needed, such as: https://coordinates-converter.com Please see the Geocoding User Guide by clicking here

| Location Name Required field | Latitude Required field | Longitude Required field | Geo Name ID Required field if the location is not an exact site | Location Description Optional text field | Activity Description Optional text field |
| --- | --- | --- | --- | --- | --- |
| Nasho Cell (Kirehe District, Eastern Province, Rwanda) | -2.106258 | 30.84625 |  | Nasho Cell is in Mpanga Sector, Kirehe District, Eastern Province. This area is in a savannah ecosystem, characterised by low rainfall and prolonged dry seasons | Plantation of woodlots on 54.1 Ha around Ibanda-Makera remnant natural forest |
| Kankobwa and Nyarutunga Cells (Kirehe District, Eastern Province, Rwanda) | -2.169547 | 30.806258 |  | Kankobwa Cell is in Mpanga Sector; Nyarutunga Cell is in Nyarubuye Sector, Kirehe District, Eastern Province. This area is in the savannah ecosystem, characterised by low rainfall and prolonged dry seasons | Plantation of woodlots on 340.7Ha |
| Nyarukunga and Kagese Cells (Kirehe District, Eastern Province, Rwanda) | -2.131439 | 30.797572 |  | Nyakabungo Cell is in Mpanga Sector; Kagese Cell is in Nasho Sector, Kirehe District, Eastern Province. This area is in the savannah ecosystem, characterised by low rainfall and prolonged dry seasons | Plantation of complete agroforestry on 420 Ha. This includes soil erosion control trenches and agroforestry trees |
| Mareba and Rugarama Cells (Kirehe District, Eastern Province, Rwanda) | -2.255006 | 30.731111 |  | Mareba Cell is in Nyarubuye Sector; Rugarama Cell is in Kigina Sector, Kirehe District, Eastern Province. This area is in the savannah ecosystem, characterised by low rainfall and prolonged dry seasons | Plantation of simple agroforestry on 1435 Ha, consists of agroforestry trees |
| Kabeza, Gishuro, Tabagwe, Nyagatoma, Ndego, Nyakiga, and Karushuga Cells (Nyagatare District, Eastern Province, Rwanda) | -1.380308 | 30.222633 |  | Kabeza Cell is in Gatunda Sector; Gishuro, Tabagwe, and Nyagatoma Cells are in Tabagwe Sector; Ndego and Nyakiga Cells are in Karama Sector; and Karushuga Cell is in Rwimiyaga Sector, Nyagatare District, Eastern Province. This area is in the savannah ecosystem, characterised by low rainfall and prolonged dry seasons | Plantation of woodlots on 255 Ha |
| Nyagatare, Barira, Gitengure, Rurenge, and Rwempasha Cells (Nyagatare District, Eastern Province, Rwanda) | -1.290961 | 30.343183 |  | Nyagatare and Barira Cells are in Nyagatare Sector; Gitengure Cell is in Tabagwe Sector; Rurenge Cell is in Rukomo Sector; and Rwempasha Cell is in Rwempasha Sector, Nyagatare District, Eastern Province. This area is in the savannah ecosystem, characterised by low rainfall and prolonged dry seasons | Restoration of Umuvumba gallery forest by forest enrichment on 140 Ha |
| Gataba, Kabungo, Karujumba, Nyagara, Kagina, Gatete, and Mahoro Cells (Nyagatare District, Eastern Province, Rwanda) | -1.417053 | 30.259986 |  | Gataba, Kabungo, and Karujumba Cells are in Kiyombe Sector; Nyagara is in Gatunda Sector; Kagina and Gatete Cells are in Mukama Sector; and Mahoro Cell is in Mimuri Sector, Nyagatare District, Eastern Province. This area is in the savannah ecosystem, characterised by low rainfall and prolonged dry seasons | Protection of Umuvumba river and its tributaries on 85.3Ha Ha |
| Karujumba Cell (Nyagatare District, Eastern Province, Rwanda) | -1.39545 | 30.090214 |  | Karujumba Cell is in Kiyombe Sector, Nyagatare District, Eastern Province. This area is in the savannah ecosystem, characterised by prolonged dry seasons | Excavation of trench for soil erosion control on 261 Ha |
| Nyabwishungezi, Rwentange, Kanyonza, Byimana, Musheri, Rugarama I&II, Ntoma, and Gakire Cells (Nyagatare District, Eastern Province, Rwanda) | -1.137111 | 30.428003 |  | Nyabwishungezi, Rwentange, Kanyonza, and Byimana Cells are in Matimba Sector; Musheri, Rugarama I&II, Ntoma, and Gakire Cells are in Musheri Sector, Nyagatare District, Eastern Province. This area is in the savannah ecosystem, characterised by low rainfall prolonged dry seasons | Plantation of simple agroforestry on 1889.7 Ha |
| Bwera, Ntoma, Rutungo, Gachundezi, and Nyampfubire Cells (Nyagatare District, Eastern Province, Rwanda) | -1.125192 | 30.425178 |  | Bwera and Ntoma Cells are in Matimba Sector; Rutungo, Gachundezi, and Nyampfubire Cells are in Rwimiyaga Sector, Nyagatare District, Eastern Province. This area is in the savannah ecosystem, characterised by low rainfall and prolonged dry seasons | Development of silvopastoralism on 915.3 Ha |
| Kigenge, Turambi, Cyendajuru, Ryamuhirwa, Kiziguro, Kamatita, Gatsiro, Rusambu, Kabuye, Karangiro, Kabagina, Tara, Kabahinda, Gahinga, Kiyabo, Buhokoro, Kabakobwa, Kamurehe Cells (Rusizi District, Western Province, Rwanda) | -2.542428 | 28.922539 |  | Kigenge, Turambi, and Cyendajuru Cells are in Giheke Sector; Ryamuhirwa and Kiziguro Cells are in Nkungu Sector; Kamatita and Gatsiro Cells are in Gihundwe Sector, Rusambu, Kabuye, Karangiro, and Kabagina Cells are in Nyakarenzo Sector; Tara, Kabahinda and Gahinga Cells are in Mururu Sector; Kiyabo is in Bweyeye Sector; Buhokoro, Kabakobwa and Kamurehe Cells are in Gashonga Sector, Rusizi District, Western Province. This area is a degraded forest ecosystem, characterised by soil erosion and landslides | Restoration of forest on 285 Ha |
| Kigenge, Giheke, Kiziguro, Ryamuhirwa, Kabasigirira, Karambi, and Gahinga Cells (Rusizi District, Western Province, Rwanda) | -2.490111 | 28.964244 |  | Kigenge and Giheke Cells are in Giheke Sector; Kiziguro and Ryamuhirwa Cells are in Nkungu Sector; Kabasigirira, Karambi and Gahinga Cells are in Mururu Sector, Rusizi District, Western Province. This area is a degraded forest ecosystem, characterised by soil erosion and landslides | Plantation of simple agroforestry on 1,625 Ha |
| Giheke, Kigenge, Turambi, Cyendajuru, Kagarama, Tara, Gahinga, Karangiro, Kabuye Cells (Rusizi District, Western Province, Rwanda) | -2.473303 | 28.954983 |  | Giheke, Kigenge, Turambi and Cyendajuru Cells are in Giheke Sector; Kagarama, Tara and Gahinga are in Mururu Sector; Karangiro and Kabuye Cells are in Nyakarenzo Sector, Rusizi District, Western Province. This area is a degraded forest ecosystem, characterised by soil erosion and landslides | Plantation of complete agroforestry on 1253 Ha |
| Kiziguro Cell (Rusizi District, Western Province, Rwanda) | -2.510467 | 28.981006 |  | Kiziguro Cell is in Nkungu Sector, Rusizi District, Western Province. This area is a degraded forest ecosystem, characterised by soil erosion and landslides | Excavation of trench for soil erosion control on 552 Ha |
| Kanombe (Kicukiro District, Rwanda), Bibare and Masoro Cells (Gasabo District, Kigali, Rwanda) | -1.953817 | 30.144308 |  | Rwimbogo Cell is in Nyarugunga Sector, Kicukiro District; Bibare Cell is in Kimironko Sector and Masoro Cell is in Ndera Sector; both Sectors are in Gasabo District; in the City of Kigali. Nyandungu Wetland is located between two districts of Kigali City; Gasabo district (Kimironko, Remera and Ndera sectors), and Kicukiro district (Nyarugunga sector). The wetland is rich in biodiversity, particularly amphibians and birds. The wetland also serves as flood proof to local communities downstream in Kimironko and Ndera Sectors. | Contribution to restoration of Nyandungu wetland on 121.8 Ha by establishment of vegetated swales, check dams, and bio retention ponds |

Please provide any further geo-referenced information and map where the project interventions are taking place as appropriate. *

[Annex any linked geospatial file]

[Please provide any further geo-referenced information and map where the project interventions are taking place as appropriate]

Kazura, C. 2013. Public expenditure review for environment and climate change for Rwanda, 2008–2012. UNEP and REAM. Final report.

Climate Public Expenditure and Institutional Review

As of the current (2025) PIR, the following assessments and knowledge products have been included in the indicator target progress: Project feasibility study report; Assessment of hydrometeorological monitoring equipment needs; Public Expenditure Review for Environment and Climate Change (PERECC); Downscaled climate projections report; Climate impact storylines report; 7 research articles on EbA-related topics were published by university researchers based on research in the project pilot sites

The risk rating for the FY 2021 PIR was erroneously marked as “M” in this table; it should have been marked as “L” (in line with the narrative and section 3.3 risk table).

For joint projects and where applicable ratings should also be discussed with the Task Manager of co-implementing agency.

Use GEF Secretariat required six-point scale system: Highly Satisfactory (HS), Satisfactory (S), Marginally Satisfactory (MS), Marginally Unsatisfactory (MU), Unsatisfactory (U), and Highly Unsatisfactory (HU)

The assessment of 16 governmental institutions’ capacity undertaken by the Baseline Study used a methodology drawing on the scoring methodologies developed by the TAMD and PPCR and adapted from the GEF - AMAT (2014). The indicator is based on five-step criteria of capacity assessment of targeted governmental institutions. Each aspect is scored from 1-4, resulting in a maximum 20 points. The final institutional summary scores are allocated from 1 to 10, which correspond to percentage capacities as follows: 1 = (0 – 10%); 2 = (11 – 20%); 3 = (21 – 30%); 4 = (31 – 40%); 5 = (41 – 50%); 6 = (51 – 60%); 7 = (61 – 70%); 8 = (71 – 80%); 9 = (81 – 90%) and 10 = (91 – 100%). See Baseline Study Section 5.4 for more details.

Outputs and activities (or deliverables) as described in the project logframe (and workplan) or in any updated project revision.

The completion dates should be as per latest workplan (latest project revision).

As much as possible, describe in terms of immediate gains to target groups, e.g. access to project deliverables, participation in receiving services; gains in knowledge, etc.

To be provided by the UNEP Task Manager