UN Environment GEF PIR Fiscal Year 2019

- July 2018 to 30 June 2019)

| - Identification |  |  | GEF ID: 2967/3735 | Umoja no.: GFL/2328-2716-4C20 |  |
| --- | --- | --- | --- | --- | --- |
| Project Number + Project Title |  |  | Regional Project for Implementing National Biosafety Frameworks in the Caribbean Sub-region |  |  |
| Duration months | Planned |  | September 2011 – September 2015 (48 months) |  |  |
|  | Extension(s) |  | September 2015 – March 2016 |  | 6 months |
|  |  |  | March 2016 – March 2017 |  | 12 months |
|  |  |  | March 2017 – June 2018 |  | 15 months |
|  |  |  | June 2018 – June 2020 |  | 24 months |
| Division(s) Implementing the project |  |  | GEF Biodiversity and Land Degradation Unit, Ecosystems Division |  |  |
| Executing Agency(ies) |  |  | The University of the West Indies |  |  |
| Names of Other Project Partners |  |  | - CARICOM Secretariat |  |  |
|  |  |  | - IICA |  |  |
|  |  |  | - University of Guyana |  |  |
|  |  |  | - National Governments |  |  |
| Project Type |  |  | Full size project |  |  |
| Project Scope |  |  | Regional |  |  |
| Region (delete as appropriate) |  |  | Latin America and Caribbean |  |  |
| Names of Beneficiary Countries |  |  | Antigua and Barbuda, Barbados, the Bahamas, Belize, Dominica, Grenada, Guyana, Saint Christopher and Nevis, Saint Lucia, Saint Vincent and the Grenadines, Suriname and Trinidad and Tobago |  |  |
| Programme of Work |  |  | PoW biennia: 2018‒2019 (although prior biennia over the project history are valid) Subprogramme 3: Healthy and productive ecosystems |  |  |
| GEF Focal Area(s) |  |  | Biodiversity |  |  |
| UNDAF linkages |  |  | There are sub-regional UNDAF and single country UNDAFs; under general priority on sustainable ecosystems and natural resources (with variance between countries in the region) |  |  |
| Link to relevant SDG target(s) and SDG indicator(s) |  |  | Goal 2: End hunger, achieve food security and improved nutrition and promote sustainable agriculture Goal 3: Ensure healthy lives and promote well-being for all at all ages Goal 9: Build resilient infrastructure, promote inclusive and sustainable industrialization and foster innovation Goal 12: Ensure sustainable consumption and production patterns Goal 14: Conserve and sustainably use the oceans, seas and marine resources for sustainable development Goal 15: Protect, restore and promote sustainable use of terrestrial ecosystems, sustainably manage forests, combat desertification, and halt and reverse land degradation and halt biodiversity loss Goal 17: Strengthen the means of implementation and revitalize the global partnership for sustainable development |  |  |
| GEF financing amount |  |  | USD 5,972,493 |  |  |
| Co-financing amount |  |  | USD 6,897,582 |  |  |
| Date of CEO Endorsement |  |  | 6 April 2011 |  |  |
| Start of Implementation |  |  | 22 September 2011 |  |  |
| Date of first disbursement |  |  | 11 October 2011 |  |  |
| Total disbursement as of 30 June |  |  | USD 5,583,868.32 |  |  |
| Total expenditure as of 30 June |  |  | USD 5,737,458.61 |  |  |
| Expected Mid-Term Date |  |  | September 2014 |  |  |
| Completion Date |  | Planned | September 2015 |  |  |
|  |  | Revised | June 2020 |  |  |
| Expected Terminal Evaluation Date |  |  | May 2019 |  |  |
| Expected Financial Closure Date |  |  | 31 December 2020 |  |  |

- OVERVIEW OF PROJECT STATUS

To be completed by UNEP/GEF Task Manager

| UN Environment Subprogramme(s) Insert the Subprogramme(s) and biennia of the PoW to which the project contributes Subprogramme 3: Healthy and productive ecosystems PoW biennia: 2018‒2019 (although prior biennia over the project history are valid) | Specify the relevant Expected Accomplishment(s) & Indicator(s) Insert the Subprogramme’s Expected Accomplishment(s) and Indicator(s) to which the project contributes Expected Accomplishment 3 (a) The health and productivity of marine, freshwater and terrestrial ecosystems are institutionalized in education, monitoring and cross-sector and transboundary collaboration frameworks at the national and international levels Relevant indicators: (i) Increase in the number of countries and transboundary collaboration frameworks that have made progress to monitor and maintain the health and productivity of marine and terrestrial ecosystems (ii) Increase in the number of countries and transboundary collaboration frameworks that demonstrate enhanced knowledge of the value and role of ecosystem services Expected Accomplishment EA3 (b) Policymakers in the public and private sectors test the inclusion of the health and productivity of ecosystems in economic decision-making Relevant indicators: (i) Increase in the number of public sector institutions that test the incorporation of the health and productivity of marine and terrestrial ecosystems in economic decision-making |
| --- | --- |
| Describe any progress made towards delivering the stated PoW Expected Accomplishments and Indicators. State key changes since previous reporting period. [Section to be shared with relevant Regional and Global SubProgramme Coordinators] The key overall measure of progress in delivery relative to the PoW is the contribution to the development of transboundary collaboration framework on biosafety for the Caribbean region. The core of activities under the project were substantially completed within the prior PIR cycle hence limited contributions were made in this PIR cycle. Work concentrated on finalization of last deliverables, with final workshops and meetings along with the conduct of the terminal evaluation, delivered by the Evaluation Office in May 2019. The evaluation concluded with an overall project rating of ‘moderately satisfactory’ which was indicative of a relatively challenging implementation process marked by differences in readiness across the project countries and inherent challenges in the building a process in regional harmonized integration in this field. |  |

For all GEF 6 and later projects:

| GEF Core Indicators Insert core indicator(s) from Core Indicator Worksheet to which the project contributes | Indicative expected Results [add figure approved at CEO endorsement/ approval] N/A |
| --- | --- |
|  | Indicative expected Results [add figure approved at CEO endorsement/ approval] N/A |
| Describe any progress made towards meeting the indicative expected results as per the approved project documentation. Describe any key changes since previous reporting period. N/A |  |

To be completed by Project Manager, as relevant

| Planned linkages with UNDAF | Describe progress towards the UNDAF strategic objective to which the project contributes. [Section to be shared with Monitoring Unit within PPD] The relevant UN frameworks under environment pillars generally have specifications related to threats posed to indigenous biodiversity related to transmittal of modified organisms and linkages to food health and safety (contained in national biodiversity strategies and action plans under the CBD). As for the UNDAFs, linkages to biosafety considerations are not specifically singled out. The UNDP Sub-regional country programme for Barbados and the Organization of Eastern Caribbean States (2017-2021) under sub-regional priority 3 ‘Sustainable ecosystems and natural resources’ seeks that legal and regulatory frameworks, policies and institutions enabled to ensure the conservation, sustainable use, and access and benefit sharing of natural resources, biodiversity and ecosystems, in line with international conventions and national legislation. This is similarly reflected in Jamaica’s 2017-2021 country programme under the priority goal of Jamaica’s maintaining a healthy natural environment. The project has not been reporting against contributions to the UNDAFs. (country documents accessible at: http://www.latinamerica.undp.org/content/rblac/en/home/operations/country-programme-documents.html) |
| --- | --- |

| Planned contribution to relevant SDG target(s) and SDG indicator(s) | Describe progress towards the stated SDG target(s) and SDG indicator(s) to which the project contributes [section to be shared with SDG unit] The most relevant SDGs and targets are: Goal 2: Target: 2.5 - By 2020, maintain the genetic diversity of seeds, cultivated plants and farmed and domesticated animals and their related wild species, including through soundly managed and diversified seed and plant banks at the national, regional and international levels, and promote access to and fair and equitable sharing of benefits arising from the utilization of genetic resources and associated traditional knowledge, as internationally agreed. Indicator: 2.5.2 Proportion of local breeds classified as being at risk, not-at-risk or at unknown level of risk of extinction. Goal 15: Target: 15.8: By 2020, introduce measures to prevent the introduction and significantly reduce the impact of invasive alien species on land and water ecosystems and control or eradicate the priority species. Indicator 15.8.1: Proportion of countries adopting relevant national legislation and adequately resourcing the prevention or control of invasive alien species. The project’s contribution in the context of these SDG targets can be considered relative to the accidental introduction genetically modified organisms that could pose threats to indigenous biodiversity. The project contributed significantly to both national and regional processes and importantly directing strategic orientation by CAHFSA and UWI in maintaining long-term support that are major underpinnings of the region in advancement toward realizing these targets. |
| --- | --- |

[complete the fiscal year and select: 1st PIR; 2nd PIR; …. Final PIR.  Add more columns if needed]

| Implementation Status | FY 2012 | FY 2013 | FY 2014 | FY 2015 | FY 2016 | FY 2017 | FY 2018 | FY 2019 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 1st PIR | 2nd PIR | 3rd PIR | 4th PIR | 5th PIR | 6th PIR | 7th PIR | 8th PIR |

[complete the fiscal year in the first line; select HS; S; MS; MU; U; HU; unknown; not rated to rate the progress towards the development objective for the fiscal year you are reporting in the second line. Add more columns if needed]

| Development Objective Rating FY | FY 2012 | FY 2013 | FY 2014 | FY 2015 | FY 2016 | FY 2017 | FY 2018 | FY 2019 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | N/A | MU | MU | MS | MS | MS | S | S |
| Describe progress made towards achieving the project results as per table 3.1. State key changes since previous reporting period. The information here must be consistent with the assessment and justification provided under 3.1. The project gradually showed progress in the past two years towards the achievement of its outcomes. By the 2018 PIR the majority of the project indicator targets have been met, and the project was rated as having done a good job in addressing remaining gaps toward the close of the project implementation. It should be noted that at the outcome level, while the assessment rating shifted to a more satisfactory rating, the developmental agenda that was fostered by the project needs to be nurtured at both national and regional levels given the variability in progress among the |  |  |  |  |  |  |  |  |

[complete the fiscal year in the first line; select among H; S; MS; MU; U; HU; unknown; not rated to rate the implementation progress in the fiscal year you are reporting in the second line. Add more columns if needed]

| Implementation Progress Rating | FY 2012 | FY 2013 | FY 2014 | FY 2015 | FY 2016 | FY 2017 | FY 2018 | FY 2019 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | N/A | MS | MU | MS | MS | S | S | S |
| Describe annual implementation progress, including any significant [expected and unexpected] environmental or other changes (Results) attributable to project implementation. Also, please discuss any major challenges to meet the objectives or specific project outcomes. [section will be uploaded into the GEF Portal ‘Information on Progress, challenges and outcomes on project implementation activities’ and is the primary report that viewers can see before opening the detailed PIR]. The information must be consistent with the assessment and justification provided under 3.2. The project has achieved most of the activities by this PIR. The main remaining activities that were carried out during this period included: - Model biosafety legislation – the first draft of the model legislation was completed during the period and reviewed by the Biosafety Legislation Specialist. The comments were addressed by the Legal Consultant. - Legislation review/CAHFSA meeting - held to review the revisions made to the legislation and to further discuss with CAHFSA the transfer of responsibility to them after the project ends. A request was made by CAHFSA in June 2019 for a copy of the final draft of the legislation, in light of their intent send it to CARICOM Member States for comment - Country progress (beyond the previous PIR): (1) Antigua & Barbuda: Draft bill and regulations completed; (2) Saint Lucia: active engagement in fine-tuning the draft bill; (3) Grenada: work on the administrative system ongoing; (4) St. Kitts & Nevis: administrative system under review; (5) St. Vincent & the Grenadines: administrative system under development; (6) Trinidad & Tobago: administrative system is in progress - BCH and lab personnel training – undertaken in St. Kitts and Nevis from 9 – 10 August 2018 and 5 – 17 August 2018 respectively. - Awareness building activities – in view of the fact that additional time was granted to complete some outstanding activities, an effort was made to ‘step up’ awareness of the project. The various activities undertaken are described in the “knowledge activities and products” section. - Guidance documents – all new guideline documents were formatted and uploaded to the project website. They were also distributed to persons at the side event in November 2018. - Biosafety videos – four new videos were produced and added to the website to specifically target key decision-makers. - The project closure workshop was held in Barbados in April 2018 - Project audits – commencement and conduct of national project audits, as well as completion of preliminary work on the 2017 regional component audit. - The Terminal evaluation process took place over the period 14 – 31 January 2019 during which Antigua & Barbuda, Barbados, St. Lucia, Guyana, Suriname and Trinidad & Tobago being visited by the evaluator. Discussions with the UWI were held on 21 January 2019, and meetings with key stakeholders in Trinidad (Ministry of the Attorney General and Legal Affairs, Ministry of Agriculture, Land and Fisheries, CARDI, IICA, and CARPHA) held from 28 – 31 January 2019. - Project extension - A further extension to the project to June 2020 has been granted in order to facilitate an update on the strategic directions and final consultations with national and regional stakeholders and importantly to facilitate project hand-off to the lead CARICOM agency, CAHFSA. |  |  |  |  |  |  |  |  |  |

[complete the fiscal year in the first line; select H; S; M; L; to rate the fiscal year you are reporting. Add more columns if needed]

| Risk Rating | FY 2012 | FY 2013 | FY 2014 | FY 2015 | FY 2016 | FY 2017 | FY 2018 | FY 2019 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | N/A | S | H | S | S | M | M | M |
| Describe key changes since previous reporting period. Projects with ESERN rating high medium/ high risk must refer to the safeguards implementation plan and its implementation. [section will be uploaded into the GEF Portal and in UN Environment Open Platform] The information here must be consistent with the assessment and justification provided under 3.3 Although the project has successfully delivered on its outputs since the last reporting period, the risk associated with the long-range uptake/outlook (at the outcome level) in terms of sustainability at both national and regional levels remains, hence the risk is considered moderate. |  |  |  |  |  |  |  |  |

| Stakeholder engagement | Describe progress, challenges and outcomes on stakeholder engagement (based on the description of the Stakeholder engagement plan included at CEO endorsement) [section will be uploaded into the GEF Portal] Stakeholder engagement in terms of the range of partners involved was mainly in line with expectation at project CEO endorsement. The stakeholders that remained actively engaged included the UWI (as the Lead Executing Agency) and national governments. In the last two years of the project, moves were made to engage IICA and CARICOM (in the form of CAHFSA). CARDI too also provided some level of support to the project in terms of assisting with the linkage to CARICOM. However, engagement was less than anticipated. This was mainly attributable to: (a) not sufficiently apprising persons of what their expected role would be; (ii) oversights in terms of engaging these stakeholders at a higher level and ensuring that they were included in discussions that would have been held during the RSC meetings for example; and (iii) the absence of a dedicated communication plan to reach out to stakeholders. The challenge of retaining momentum among stakeholders at the national level was identified as a risk from the early stages of the project. This has much to do with change over in personnel and changing commitments and priorities that may be occupying local agendas at any given time. Where national projects were able to make significant strides, this was primarily due to a sense of ownership, as well as an awareness and comprehension of the systems that are required to address biosafety nationally. The opportunity provided by the project to assist countries in the areas of capacity building and improvements in laboratory infrastructure are positive aspects upon which efforts to address biosafety in the region can be built. The project also provided opportunities for networking, not only among project countries, but also with some of the international collaborators with whom linkages were formed. While in most countries legislation is still in draft form, the project allowed existing drafts to be updated and where absent, facilitated the first time drafting of biosafety legislation. The project also facilitated public engagement on the issue of biosafety as well as the harmonisation of biosafety at the regional level in the form of the policy and draft model legislation. An update on the status of biosafety in the Region was also achieved. |
| --- | --- |

| Gender mainstreaming | Describe progress, challenges and outcomes related to the gender-responsive measures documented at CEO Endorsement/ Approval in the gender action plan or equivalent. Older projects that were designed before gender mainstreaming should proactively report any possible gender benefits, as appropriate. [section will be uploaded into the GEF Portal] The overall goal of the project and hence its expected outcomes were gender-neutral. Consequently, the project had not picked up on gender markers. |
| --- | --- |

| Knowledge activities and products | - Guidance documents – the regional policy (Regional Biosafety Harmonisation) developed by the UWI, along with the 4 new guidance documents produced by the ICGEB, namely: (i) Guidelines for the Risk Assessment of Commonly Regulated GM Crop Events (ii) Risk Communication Guidelines (iii) Saint Lucia Document Concerning the Safety Assessment for Foods and Animal Feeds Derived from Genetically Modified Insect-Resistant Maize MON810 (iv) Saint Lucia Document Concerning the Safety Assessment for Foods and Animal Feeds Derived from Genetically Modified Glyphosate-Tolerant Soya bean GTS 40-3-2 have all been uploaded to the project website and can be accessed at: https://caribbeanbiosafety.org/technical-output/ - CAHFSA meeting - the meeting, which was held on 7 December 2018 in Trinidad, in conjunction with the legislation review meeting, served as a follow-up to the one held in Suriname at CAHFSA Headquarters on 13 December 2017. It was attended by Simeon Collins, Gavin Peters of CAHFSA, Sylna Ambris-Dick, Legal Consultant, Professor Pathmanathan Umaharan, UWI and the RPM. Key areas discussed included: a) Draft model legislation b) Awareness building c) Risk assessment group d) Website e) Phase II project proposal f) Public education and outreach The meeting notes can be found in Anubis. - Legislation review meeting – as indicated above, in light of the detailed review undertaken by Dr. Michael Wach, Biosafety Legislation Specialist, of the second draft of the legislation in August 2018, the proposed meeting was held on 6 and 7 December 2018. The meeting involved a complete review of the third draft produced (based on Dr. Wach’s comments), with all relevant feedback being noted by Mrs. Ambris-Dick. Prior to the submission of the final draft document to the project by Mrs. Ambris-Dick, Dr. Wach’s input was once more sought to clarify some outstanding issues. The consultant’s report will be circulated to the countries for feedback. It will also be subjected to the CARICOM process pertaining to the adoption of regionally produced legislation. - Biosecurity Symposium - the project was invited to participate in a Biosecurity Symposium on “Building Resilience to Biosecurity Threats in the Caribbean” on 3 August 2018, Cave Hill Campus, The UWI, Barbados, at which its Centre for Biosecurity Studies was launched. The proposed Centre will be so designed to co-ordinate initiatives aimed at reducing or eliminating biological threats that could adversely affect the Caribbean’s way of life and destabilise regional economies. In her welcome address, Principal of the Cave Hill Campus, Professor Eudine Barriteau, GCM, noted that the Cave Hill position is one whereby biosafety is considered to be a component of biosecurity. She also made mention of the MSc. Biosafety, indicating that its graduates are among the region’s policy advisors. The symposium encompassed presentations on: - Biosecurity, governance and international diplomacy - Climate change risks - The role of PAHO - Industrial revolutions, global health and biosecurity: Implications for the Caribbean, and - Strengthening biosecurity and preventing bioterrorism in the Caribbean: The role of United Nations Security Council Resolution 1540. In the remarks made by the Attorney General of Barbados, The Honourable Dale Marshall, QC, underscored the importance of the legislation agenda to address issues such as biosecurity and biosafety. It was encouraging to note that in his remarks too that he expressed awareness of the regional biosafety policy. - First BCH III National Workshop, Grenada - The invitation extended to the RPM to participate in this event, was in view of the importance of integrating and continuing the efforts of the BCH III project with those that have been undertaken within the context of other projects such as the Regional Biosafety Project for example. To this end, the RPM gave a presentation on the Regional Project, with a focus on the Grenada national component. After examining the project context, CARICOM and biosafety, project background and project achievements, a look was taken at Grenada’s participation in the project. Note was made of the national component activities which countries had to execute, as well as the expected outputs. Participants were also advised that in light of the mid-term evaluation, which took place in 2014, there was a prioritisation of activites at both the national and regional levels. In terms of what is still required at the national level in Grenada, the RPM noted that it would be essential to ensure that (i) biosafety legislation is enacted; (ii) the design of the administrative system is completed and approved; (iii) the regulations are completed and approved; and (iv) the nBCH is fully functional. It would also be important to identify synergies with other agreements so that the task of addressing biosafety seems less onerous. - ABS workshop – the RPM participated in a workshop on the proposed legislative and administrative framework for the implementation of the Nagoya Protocol on Access to Genetic Resources and the Fair and Equitable Sharing of Benefits (ABS) in Trinidad. It was facilitated by the IUCN under the auspices of the Ministry of Planning and Development. The workshop provided local stakeholders with information about the importance of signing on to the Protocol, among other things. Based on the discussions held, Trinidad and Tobago indicated that the Minister would have to be provided with an ample of amount of supporting information in order to be convinced that this is something that should be signed on to. The RPM considered this to be a good approach in light of the challenges faced relating to the putting in place of systems relating to the full implementation of the CPB nationally. - Awareness building activities – these included: - Participation in the Caribbean Week of Agriculture Market Place 2018 Trade Show – this took place from 10 – 12 October 2018 in Barbados. The project, in conjunction with CAHFSA, hosted a booth at the event. Outreach materials produced by the project were distributed to members of the public, which comprised primary and secondary school children, and the general public. Information was provided about the project and its role in assiting countries in the region (including Barbados), to put sytems in place to address the issue of GMOs. Persons generally did not have any knowlegde of the project. School teachers in particular found the material useful as the topic of GMOs is now on the secondary school science syllabus in Barbados. Even some of the primary school teachers (e.g. Standards 1 and 2) indicated that they would begin to introduce the concept to the children. It was acknowledged that it may be necessary to produce additional material to specifically younger children about the topic of biosafety. Professor Umaharan was invited to participate in a discussion forum hosted by the FAO during the week on “Natural Resources Management and Disaster Risk Management – Implications for the Agriculture Sector”. He gave a presentation on “E-Agriculture lessons on disaster mitigation in the cocoa sector”, which explained how genetic resources and E-agriculture can be used to build resilience to natural disasters. It was also hoped that CARICOM could have assited the project in making arrangements for Professor Umaharan to do a presentation for the Ministers at the COTED meeting on the policy. This was however not possible as the agenda is generally quite packed, and the view was expressed by CARICOM that the Ministers already know about this. A visit by Ambassdor Irwin LaRocque, CARICOM Secretary-General to the booth however disputed this perspective, as he was not aware of the policy. To address this, a copy of the Policy Brief was made available to him as well as to the Honourable Indar Weir, M.P, Minister of Agriculture and Food Security Barbados, who also visited the exhibition area. (ii) Distribution of information packages – in view of the fact that it was possible to host the meeting of Permanent Secretaries of the Ministries of Agriculture and Foreign Affairs in April 2018, the RPM took a decision to post out information packages in November 2018 containing the following items: - General information on biosafety and biotechnology (brochure) - Benefits and risks of genetically modified organisms (brochure) - Project brochure - GMO regulation (fact sheet) - Policy brief - DVD with 4 videos (biosafety and biotechnology; regional biosafety policy; regional biosafety project; and regional laboratory strategy) - Poster A note was also included in the package, which not only served to advise on the purpose of the package, i.e. to sensitise persons about the project, but to also seek support to obtain the necessary approvals for the drafted biosafety legislation. In all. A total of 35 packages were distributed via post as follows: Foreign Affairs (15), Agriculture (18) and CARICOM (2). (iii) Side event – as was the case in 2016, the project was once more succesful in its bid to host a side event at the COP-14 held in Sharm El Sheikh, Egypt from 17 – 29 November 2018. The event was titled “Sustaining Biosafety in the Caribbean Sub-Region”. The report on the side event can be found in Anubis. (iv) SCBD - During the side event the RPM met Ms. Ulrika Nilsson, Associate Information Officer, SCBD. As a follow-up to this meeting, Ms. Nilsson was provided with an article on the project titled “Sustaining Biosafety in the Caribbean Sub-Region”, for registering on the BCH, as well as the links to the public service videos. A link to the project website can now be found on the SCBD’s biosafety facebook page (https://www.facebook.com/UN.Biosafety). It was also further suggested that items such as the tehnical guidelines and videos produced could also be registered on the BCH. - Biosafety videos – under the contract with Jtography Limited, four new videos were produced to specifically target key decision-makers. These are in the areas of biosafety and biotechnology, regional biosafety policy, regional laboratory strategy and regional biosafety project. The videos, along with the previous ones made, can be found on the project website at: https://caribbeanbiosafety.org/technical-output/ - St. Kitts and Nevis – in response to the feedback received from St. Kitts and Nevis regarding future needs as outlined in their presentation at the project closure meeting on 11 April 2018 in Barbados, the regional component provided support to enable the execution of two activities, which are outputs of the implementation project at the national level, namely: (i) BCH workshop – this was undertaken by Qualisys from 9 – 10 August 2018. The primary objective of the workshop was assist in the updating of the national node of the BCH. The workshop was attended by 10 persons and facilitated by Dr. Ernesto Ocampo. The training provided, as with all the other country training undertaken by Dr. Ocampo, had as its major objective the provision of support to project participating countries in the development and implementation of their national BCH systems that would further be linked to the Caribbean Regional Biosafety Portal. The report on the activity can be found in Anubis. (ii) Training of laboratory personnel – this was undertaken by Dr. Marissa Moses, who conducted the training workshop on the detection of GMOs in the food chain over the period 15 – 17 August 2018. The workshop was attended by 13 persons and encompassed both practical and theoretical sessions. Dr. Moses’ report can be found in Anubis. |
| --- | --- |

| Stories to be shared |  |
| --- | --- |

- RATING PROJECT PERFORMANCE AND RISK

Based on inputs by the Project Manager, the UNEP Task Manager will make an overall assessment and provide ratings of:

- Progress towards achieving the project Results(s)- see section 3.1

- Implementation progress – see section 3.2

Section 3.3 on Risk should be first completed by the Project Manager. The UNEP Task Manager will subsequently enter his/her own ratings in the appropriate column.

  - 3.1	Rating of progress towards achieving the project Results(s) [copy and paste the CEO Endorsement (or latest formal Revision) approved Results Framework, adding/deleting outcome rows, as appropriate]

| Project objective and Outcomes | Indicator | Baseline level | Mid-term target or Milestones2 | End-of-project target | Observations/ justification on rating | Progress rating3 |
| --- | --- | --- | --- | --- | --- | --- |
| Objective4 To implement effective, operable, transparent and sustainable National Biosafety Frameworks (NBF) which cater for national and regional needs, deliver global benefits and are compliant with the Cartagena Protocol on Biosafety (CPB) in 12 Caribbean countries | A. Up to 12 Caribbean countries are able to take decisions (mock or real), in accordance with the CPB for different LMO types: A.1 LMO intended for introduction into the environmental (field trial and/or commercial release); A.2 LMO intended for direct use as food, feed or for processing; A.3 LMO produced within the Caribbean region, still at experimental stage. | No Caribbean or project country has yet made a decision (or simulated the decision-making /authorization process) as set out under the CPB for LMOs covered by the Protocol. All countries have a draft NBF which needs to be completed, updated and adopted. |  | A. At least 10 of 12 Caribbean countries are able to take decisions (mock or real), in accordance with the Cartagena Protocol for Biosafety, for at least 2 of the 3 different LMO types considered under the Protocol. | 12 out of 12 project countries obtained training in GMO decision-making. A mock exercise was held in February 2017 in Trinidad and again in Guyana (for Guyanese who did not attend the 1st workshop) in Feb./Mar. 2018. However, because legislation in most countries is still awaiting Cabinet approval, the draft administrative systems cannot yet be implemented to take ‘real’ decisions in the event that this becomes necessary. Two countries are exceptions vis à vis legislation: St. Lucia (where while the legislation, regulations and policy have been endorsed by Cabinet, enactment remains outstanding) and St. Kitts (which had an Act in place at the start of the project). Finally, although training was provided, most countries (with the exception of St. Lucia), failed to do the necessary ‘homework’ to make the exercise a fruitful one, primarily due to poor understanding of what was required. This once more underscores the importance of providing a more ‘hands on’ approach to any future capacity building as against a focus on supporting more MSc. candidates. | S |
|  | B. Improved GEF biosafety tracking tool scores, together with improvements in responses to questions of Second National Reports to the CPB, considering all project countries | Only 2 National Reports to the CPB are available for CARICOM countries. A marked disparity exists amongst current Caribbean NBFs -both in terms of status and robustness- which will be compounded by the onset of the Caribbean Single Market and Economy, a change in scenario that will challenge the extent to which biosafety at the regional scale can be effective. |  | B. Overall tracking tool score is raised by at least 20% matched with a significant (>10%) improvement in responses to questions of the Second National Reports to the CPB. | While several countries have increased their METT scores as of October 2018, namely Antigua and Barbuda (3 to 17), Barbados (8 to 11), Belize (18 to 21), St. Lucia (16 to 22), St. Kitts & Nevis (10 to 14), Guyana (13 to 14) and Grenada (15 to 16), it is notable that no change has occurred in those key areas that are dependent upon Cabinet endorsement, namely areas relating to policy, regulatory regime, risk assessment procedures, administrative system and operational follow-up and monitoring system. This result reiterates the importance of sensitising decision-makers on the importance of Biosafety issues and seeking as far as possible to garner their support for the efforts that have been made at both the national and regional levels, particularly as it relates to the legislation that has been developed. Although the view has been expressed that one should not wait until the legislation has been approved, the reality is that without such approval, all the work that has gone into the development of the requisite systems could be in vain without the necessary ‘high level’ approval/backing. | S |
| Outcome 1: Biosafety governance regimes are improved and aligned with the CPB in 12 countries of the Caribbean sub-region | 1.1 Number of surveyed staff in Government agencies with a responsibility in biosafety who are familiar with their agency‘s role and obligations when processing an LMO request 1.2 Number of countries with revised regulations or new legislation approved by Cabinet that cover the main provisions of the CPB, including: access to information and use of BCH; right to public participation; confidentiality clauses; risk assessment processes; monitoring and inspections; and; bi/multi-lateral agreements with Non-Parties 1.3 Number of National Biosafety Frameworks (NBFs) that have established financing mechanisms 1.4 Number of countries that have biosafety decision-making processes supported by technically sound risk assessments and by advisory structures or experts. 1.5 Number of countries where political support mechanisms for LMO / IAS risk management and stakeholder participation have been strengthened | All countries have a draft NBF which needs to be completed, updated and adopted. Only 2 National Reports to the CPB are available for CARICOM countries. A marked disparity exists amongst current Caribbean NBFs -both in terms of status and robustness- which will be compounded by the onset of the Caribbean Single Market and Economy, a change in scenario that will challenge the extent to which biosafety at the regional scale can be effective. All countries have provided National Reports to the CPB; these reports attest to the low level of progress made in strengthening biosafety governance. Tracking tools provide the baseline for status of biosafety governance at project start. Most countries have prepared draft NBFs that at minimum: include regulatory /policy proposals, designate a National Biosafety Authority, establish support structures and mechanisms (eg. Advisory committees), and require decision-making to be based on LMO risk assessments. These NBFs however are not yet in force, and require completion and updating prior to being adopted. Institutional mandates and operational responsibilities also need to be defined. | 1.1 40% of surveyed staff will be able to acknowledge (i) the role of their agency when processing an LMO request; (ii) the milestones and deadlines in the decision-making process; and (iii) their own designated tasks in relation to processing a request. 1.2 Legislative revisions or new legislations for biosafety will have been passed by at least 6 of 12 participating countries 1.3 Up to 10 participating countries will have identified financing options and sources for maintaining NBF operations 1.4 A minimum of 10 countries will have established Scientific and Technical Advisory Committees, or a roster of experts, or equivalent ad hoc or permanent support structures, for biosafety. 1.5 In at least 8 of 12 project countries, National Steering Committees are either multi-sectorial or will have invited additional sectors to their meetings; and stakeholder consultations have taken place concerning NBF implementation. | 1.1 80% of surveyed staff will be familiar with their agency‘s role and obligations when processing an LMO request 1.2 A minimum of 10 countries will have revised regulations or new legislation approved by Cabinet that cover the main provisions of the CPB. 1.3 A minimum of 10 countries will have established financing mechanisms for their NBFs 1.4 A minimum of 10 countries will have established advisory committees or a roster of experts for biosafety; and will have risk assessment criteria and methodology submitted to peer review. 1.5 In at least 8 of 12 project countries, National Steering Committees are either multisectoral or will have invited additional sectors to their meetings; and stakeholder consultations have taken place concerning NBF implementation. | 1.1 The survey was completed in 2017 and showed 73% of staff surveyed indicated that they were familiar with their agency’s role and obligations when processing an LMO request. 1.2 10 of the 12 project countries have reviewed and revised their legislation. Endorsement has taken place in St. Lucia, but as with all countries (with the exception of St. Kitts that already had an Act in place), enactment remains elusive. 1.3 10 of the 12 project countries have done this, with Barbados and the Bahamas being the exceptions. 1.4 All project countries (i.e. 12 out of 12) have submitted information relating to this. 1.5 All countries (i.e. 12 out of 12) established multisectoral NSCs and stakeholder consultations have taken place. | S S S S HS |
| Outcome 2: Well-articulated and technically sound risk assessment, risk management and follow-up systems are functioning for biosafety in the Caribbean | 2.1 Number of National Biosafety Authorities able to carry out LMO risk assessments and determine risk management requirements (biosafety measures) when taking decisions on LMOs 2.2 Number of National Biosafety Authorities able to take on, or outsource, follow-up activities (LMO monitoring) 2.3 Number of countries with access to the human and technical /technological resources needed to enable or support the risk assessment of LMOs. 2.4 Number of countries with access to the infrastructural resources needed to enable or support the risk management and border control of LMOs. | Biosafety support capacity within the Bureau of Standards of project countries is weak, with no official standards, protocols and tools for carrying out biosafety risk assessments. Biosafety measures for risk management are not applied, nor does LMO monitoring take place; there is no border control for LMOs entering or leaving the CARICOM. Current LMO detection capacities in the region are limited and laboratory facilities are either lacking in relevant technologies or absent in some countries; this precludes effective (and harmonized) biosafety risk management, rationalization of biosafety tasks, and economies of scale, by establishing linkages between national /regional biosafety laboratories. A regional agreement on the extent to which a harmonized approach to biosafety is needed and would be cost effectively institutionalized at the regional level is pending | 2.1 to 2.4 The range of technical risk management capacities available in the Caribbean and of biosafety services that can be cost-effectively accessed at the regional level have been determined through capacity /needs assessments; plus a decision is reached by all countries and relevant regional organizations on which aspects of biosafety should be harmonized and how technical support is to be provided on a regional scale, beyond the GEF project. | 2.1 At least 10 of 12 project countries are able to carry out LMO risk assessments and determine risk management requirements (biosafety measures) when taking decisions on LMOs 2.2 At least 10 of 12 project countries are able to take on, or outsource, follow-up activities (LMO monitoring) 2.3 At least 10 of 12 project countries have access to the human and technical / technological resources needed to enable or support the risk assessment of LMOs. 2.4 All project countries have mechanisms in place to access national and/or regional laboratory services for LMO detection (as required for biosafety audits, inspections, and border control), while detection methods have been standardized and border control procedures defined. | 2.1 Representatives from all 12 project countries have been exposed to training in the area of GMO decision-making as it relates to risk assessment Due to the fact however that countries have not had to make any decisions as yet, these skills have not been out into practice. 2.2 Labs in 11 of the 12 project countries (except Bahamas) were upgraded to assist with the conduct of basic monitoring activities at the national level. 2.3 Training provided to representatives from each of the 12 project countries, the rosters of experts established and the Technical Working Group on Biosafety proposed, all ensure that there is access to human resources to support risk assessment of LMOs. At the regional level technical support in risk assessment is to be provided by CAHFSA, and at the international level, the linkages established with the ICGEB can also be exploited for additional assistance. The technical guidelines produced and distributed to countries can be regarded as a further resource. produced. 2.4 In addition to the nationally designated GMO labs, reference labs on each of 3 campuses of the UWI were also upgraded. The MoU was circulated to countries for feedback. To date it has been signed by Antigua & Barbuda, St. Kitts/Nevis and Suriname. | S S HS |
| Outcome 3: A multidisciplinary cadre of trained personnel and technical support mechanisms, that combine both national and regional capacities, are operational and ensure the future sustainability of biosafety management in CARICOM countries. | 3.1 Number of personnel from scientific and nonscientific backgrounds that receive practical training in risk assessments, risk management and risk communication for different LMO categories (as considered under the CPB). 3.2 Number of personnel from scientific and nonscientific backgrounds that receive practical training in LMO detection and sampling techniques. 3.3 Number of customs officers and inspectors that receive practical training on transport and transit/ transshipment issues, trade facts, unauthorized (illegal or inadvertent) introduction of LMOs, and biosafety information management. 3.4 Establishment of a biosafety training program that both cements regional Co-operation and consolidates the technical support base for NBF | Concomitant, region-wide and systematic technical training has not as yet been offered in biosafety in the Caribbean region, despite isolated biosafety capacity building efforts taking place (and ongoing) in specific countries. Academically-backed programmes and manuals to offer training to biosafety personnel have not been developed. There is a general absence of human resources trained in biosafety risk assessment and safe biotechnology management in the region. The lack of training also affects the customs sector which has generally remained at the margins of LMO trade and NBF developments. There are opportunities in linking with the capacity building efforts of other UNEP/GEF biosafety projects in the LAC region, especially Cuba. | 3.1 At least 6 people from the National Biosafety Authority, other competent authorities, or the Scientific and Technical Advisory Committee (or equivalent) of each country pass the training course in risk assessment satisfactorily. 3.2 At least 3 people from each participating country pass the training course in LMO detection satisfactorily. 3.3 The training course for customs officers and inspectors has been designed. 3.4 The first phase of the Regional Biosafety Training Program is launched regionally, with at least one subscription opened and initiating with trainees from more than 5 CARICOM countries. | 3.1 At least 6 people from the National Biosafety Authority, other competent authorities, or the Scientific and Technical Advisory Committee (or equivalent) of each country partake in a simulated LMO decision-making process (for training purposes), by: i) analyzing LMO data ii) formulating or reviewing recommendations for a decision (for any of 3 LMO types), OR iii) preparing national or regional records for posting on the BCH. 3.2 LMO detection can be applied to mock or real LMO samples in at least 2 laboratories in the region, obtaining standardized results. 3.3 At least 3 people from each participating country are trained in LMO border control and transboundary issues and pass the course satisfactorily. 3.4 The first phase of the Regional Biosafety Training Program is launched regionally, with at least one subscription opened and initiating with trainees from more than 5 CARICOM countries, and subsequent phases have a self-financing plan. | 3.1 A total 17 persons (representing 11 of the 12 project countries) were trained at the BCH workshop held in Trinidad in November 2015. At subsequent trainings held at the national level in 6 project countries, a total of 79 persons were trained as follows: Bahamas – 4; Barbados – 5; Grenada – 17; Suriname – 35; Antigua & Barbuda – 8; St. Kitts and Nevis – 10 3.2 In addition to the LMO detection training undertaken in February 2015 in Trinidad at the St. Augustine Campus of the UWI, additional persons were trained at the workshop held on the Cave Hill Campus in Barbados in December 2015. Tests were carried out in 2 different labs of the UWI for standardisation. A workshop is planned for St. Kitts/Nevis in August 2018 to train lab personnel there in the use of the equipment procured. 3.3 This target was achieved via the hosting by the project of a workshop in August 2016 to sensitise border control officers (customs and plant quarantine) on the issue of biosafety, as well as one hosted by the SCBD in conjunction with the project, specifically for customs officers on developing capacity for national border controls on LMOs. 3.4 With the winding down of the project, no additional workshops were conducted. The MSc. continues to be run out of Cave Hill, Barbados. | HS S S |
| Outcome 4: National and regional mechanisms that provide access to biosafety information in order to promote transparency, raise public awareness and facilitate biosafety decision-making are institutionalized throughout the region | 4.1 Number of countries with improved capacity to access, use and register information on the central portal and National nodes of the Biosafety Clearing- House (BCH) 4.2 Number of national and regional institutions that create, maintain or provide access to data bases related to biosafety and LMOs that have been approved or are subject to transboundary movements/traded within CARICOM. 4.3 Number of hits on the Regional BCH Node. 4.4 Number of technical personnel, politicians/ decision-makers, and non- Government stakeholders that participate in awareness raising activities carried out at the national level to promote biosafety | There is an absence of functional BCH systems and a lack of adequate equipment and trained personnel for coordinated biosafety information management at the national level. Only some project countries executed the first phase of the UNEP/GEF global BCH project. Very few Caribbean countries (excluding Cuba and Dominican Republic) have posted records on the BCH central portal. Public awareness and sensitization programmes for biosafety so far have been scarce, sporadic, insufficient, or altogether absent. There is also poor involvement in biosafety issues across sectors of society. Information needed for making timely and informed biosafety decisions is either not available, or has not been screened for its application in the Caribbean context; nor has it been systematized for easy access on a regional scale. | 4.1 At least 10 of 12 project countries will have increased by 50% the number of national records on the BCH central portal; or have at least 2 records in each obligatory category. 4.2 At least 10 national institutions will have begun to create and populate databases for biosafety and LMOs that have been approved or are traded/ subject to transboundary movements into or within CARICOM. 4.3 The Regional BCH Node will have been launched. 4.4 For each project country, at least 10 Government technical personnel, politicians/ decision-makers, and non-Government stakeholders will have participated in awareness raising activities carried out at the national level to promote biosafety. | 4.1 At least 10 of 12 project countries will have increased by 50% the number of national records on the BCH central portal (or will have at least 2 records in each obligatory category), and will have set up an operational BCH (national node) and made contributions to the Regional Node. 4.2 At least 10 national institutions and 2 regional institutions will have created, populated and provided ongoing access to databases for biosafety and LMOs that have been approved or are traded / subject to transboundary movements into or within CARICOM. 4.3 There will be at least a 10% increase in monthly hits on the Regional BCH Node at project end with respect to hits recorded after 3 months of launching. 4.4 For each project country, at least 30 Government technical personnel, politicians/ decision makers, and non-Government stakeholders will have participated in awareness raising activities carried out at the national level to promote biosafety. | 4.1 BCH training has been provided to all project countries to ensure that they are in a position to increase the number of national records. Further, where individual countries requested additional training, this has been supported by the project. 4.2 Along with the information national institutions would have posted, during the upgrade of the CCB more resources were added to the rBCH vis á vis databases for LMOs such as Risk Assessment Search Mechanism (RASM), for example. 4.3 In the absence of a hit counter on the website it is not possible to assess this. A request was made to the website developer to have this put in place. 4.4 This target has been met and exceeded via the exposure of all participants at the various sensitisation workshops and other workshops conducted, at the start of which, presentations on the project are made. Information packages were sent to PSs in regional Ministries of Foreign Affairs (15) and Agriculture (18). In addition the project participated in the Caribbean Week of Agriculture 2018 exhibition in Barbados, and had the opportunity to interact with the general public. | S |
| Outcome 5: Outcome 5.1 Regional processes aid to lay the foundations for regional biosafety services and a regional framework to assist NBF implementation in the Caribbean Outcome 5.2 Regional processes support project management Outcome 5.3 Regional processes support project M&E | 5.1 Regional mechanisms to sustain and coordinate NBFs cost-effectively are explored and initiated | Regional support, coordination and financing mechanisms are absent for biosafety Specific CARICOM institutions have mandates or capacities to uphold biosecurity standards Countries have not agreed on whether and which existing regional institutions are to take on biosafety tasks | 5.1 Political authorities from countries and regional institutions agree on biosafety services and responsibilities that can devolve at the regional level. | 5.1 An institutional framework has been adopted for providing regional biosafety services, and includes an initial pilot phase for regional coordination of biosafety tasks, and a self-financing plan for such services | 5.1 The draft regional policy was accepted by COTED in October 2017 so that there is now a policy in place for the region, which outlines the objectives, principles and advantages of harmonisation, and the mechanisms via which this is to be achieved. While a copy of the model legislation was circulated to project countries for feedback at the end of the project, CAHFSA will also be sending a copy of the draft legislation for ‘release’ to Member States through the CARICOM Secretariat for their comments. | S |
|  | 5.2 Project is delivered within budget, and achieves its major outputs and planned activities | Countries have experience with NBF Development projects, while UWI has experience in executing this project‘s PPG | 5.2 Mid-term Review /Evaluation is completed with successful ratings, and project reporting (technical and financial) is up-to-date. | 5.2 Project reporting (technical and financial including audits and co-financing) is fully up-to standard and up-to-date | 5.2 Technical closure of the project was achieved in December 2018, and all terminal reports have been uploaded to Anubis. | S |
|  | 5.3 Project achieves its expected outcomes as determined by annual PIRs and external evaluations (MTR and TE) | Countries have experience with NBF Development projects, while UWI has experience in executing this project‘s PPG | 5.3 N/A | 5.3 Terminal Evaluation is completed with successful ratings | 5.3 The terminal evaluation of the project took place over the period November 2018 – March 2019. An overall rating of MS was received. |  |

Overall rating of project progress towards meeting project Result(s) (To be provided by UNEP GEF Task Manager.)

| FY2018 rating [previous] | FY2019 rating [current] | Justification of the current FY rating and explanation of reasons for change (positive or negative) since previous reporting periods. |
| --- | --- | --- |
| S | S | Summarize the annual progress towards meeting project results. Describe any significant [expected and unexpected] environmental or other changes (Results) negative and or positive attributable to project implementation. State any key changes since previous reporting period. Also, please discuss any major challenges to meet the objectives or specific project outcomes. Whenever possible, please provide evidence of attribution between the UNEP/GEF project’s intervention and observed changes towards the achievement of direct outcomes. In cases where several actors are collaborating to achieve common outcomes, evidence of the nature and magnitude of the UNEP/GEF project’s ‘substantive contribution’ and/or ‘credible association’ should be described. This information provides the rationale for the Development Objective Rating in Section 2. The main technical activity the project concluded on was the finalization of the model biosafety legislation. CAHFSA has been engaged in the transitioning of regional organizational responsibility to assist countries in adaptation of the legislation. This is a significant contribution at the project result level. Given that the majority of actions foreseen under the project have been completed, the rating since the last PIR remains unchanged. |

Risks to the delivery of results

The second column should be completed by the Project Manager and the third column should summarize the recommendations that the Project Manager and Task Manager have agreed upon to address the problem/risk.  Projects should complete only the relevant sections and are free to add/delete problems/risks.  This section should inform the risk rating in section 3.3.

| Problems/risks identified | Description of the problem/risk | Agreed recommended actions |
| --- | --- | --- |
| on achieving targets | - The lack of completion / enactment of national legislation, which can nullify all the capacity building, public awareness, laboratory facilitation and policy development achieved during the project at the national and regional levels. | Appointment of a legal consultant to: (a) review the national legislations under various stages of development for their completion and adherence to the regional policy; towards assisting them in furthering the legislative agenda (b) to develop a model draft biosafety legislation to assist countries that have not started the process of developing biosafety legislation. |
|  | - Lack of adherence of national legislations to the regional policy approved by CARICOM can result in these not being implementable as they may violate the Revised Treaty of Chaguaramas. The regional policy was only approved in October 2017, which delayed this process. | Submission of the draft legislation to the ICGEB to facilitate a final vetting and verification of the local consultant’s report. |
|  | - Modified draft may need further revision by the local consultant to ensure adherence to the CARICOM policy and endorsed by CARICOM Member States | - The legal consultant reviews and incorporates suggestions by reviewer, while ensuring that this meets with the Revised Treaty of Chaguaramas that established CARICOM. - The Regional Project will organise a CAHFSA/UWI/Local consultant meeting to review the revisions made - The final modified draft legislation will be sent to the Member States and CARICOM for endorsement |
| on stakeholder engagement | - Lack of awareness of policy makers and the executing bodies can result in the legislation not being taken to the Parliament and being enacted | - Lobby policy makers and the executing agencies at various forums with regard to the importance of the biosafety policy and legislation to regional development and trade as follows: - Meeting of Permanent Secretaries of the Ministries of Agriculture in the 14 CARICOM countries. (b) Meeting of the Ministers of Agriculture of the 14 CARICOM countries during the Caribbean Week of Agriculture. (c) Presentations at meetings of CARICOM’s Legal Affairs Committee (LAC), Senior Officials of the Legal Affairs Committee (SOLAC) and the Regional Agricultural Planner’s Forum. - Produce a series of videos to assist in awareness building, based on the guidelines developed. These are to be showcased at the various meetings proposed above. |
| on gender actions |  |  |
| on safeguards |  |  |
| on delivering GEF Core Indicators |  |  |
| on delivering of PoW EA |  |  |
| on sustainability of results | - Need to transfer the regional regulatory function to the CAHFSA and develop a co-ordination mechanism between UWI and CAHFSA | CAHFSA has been identified by CARICOM as the organisation in which this responsibility should be vested. The regional project will work towards empowering CAHFSA to continue the regulatory functions as a sustainability measure. |
|  | - Lack of a regional IT mechanism for the co-ordination of the regional biosafety clearinghouse and its interactions with the national biosafety clearinghouses, as well as the UWI. | Hold additional discussions with CAHFSA regarding the hosting of the rBCH after the project ends. |
| others | Final administrative actions | Ensure that the following items are addressed: - National-level audits (covering the period 2012 – 2016) - Provision of inputs to the process of developing the Follow-On project - Support to the Terminal Evaluation team - Final audit (for 2017 and remainder of 2018) of the overall project - Preparation and submission of terminal (closure) documents to UNEP, including Final Report, final inventory, last PIR, final audit, and final expenditure statement |

3.2	Rating of progress implementation towards delivery of outputs

| Outputs5 | Expected delivery date6 | Implement-ation status as of 30 June 20187 | Implement-ation status as of 30 June 2019 | Progress rating justification | Progress rating8 |
| --- | --- | --- | --- | --- | --- |
| Component 1: Establishment of national Legal Frameworks for Biosafety/Biotechnology |  |  |  |  |  |
| 1.1 Review of drafted NBF and proposed biosafety legislation, ensuring full alignment with main provisions of the CPB. | 31 March 2012 to 31 December 2018 | 98 | 100 | The review process is complete in all project countries, and steps taken to make the required adjustments, with support being provided by the ICGEB as necessary. In light of the fact that CARICOM has endorsed the regional policy, one of the activities being undertaken by the consultant hired to develop the model legislation is a review of all drafted legislation to ensure that they are aligned with the regional biosafety policy. Despite the review being complete, additional activities at the national level, post project will have to be undertaken to ensure the requisite political buy-in. | S |
| - Support for Office of Attorney General, NEA and NPC to prepare draft legislation for submission to Cabinet/ House of Assembly, including public sensitization program to support enactment of biosafety law. | 31 March 2012 to 31 December 2018 | 90 | 100 | The following is a summary of the status of project countries: Antigua and Barbuda - a Biosafety Policy, biosafety and biotechnology management bill (3rd draft) and regulations (2nd draft) developed; Barbados – a policy document is required prior to the drafting of the Bill. Post project this is an activity that would have to be pursued; Bahamas - Draft Bio-security Act and Biosafety Framework exist, however a biosafety policy is required prior to the drafting of the legislation Post project this will have to be an activity that would have to be pursued; Belize – Draft National Biosafety Policy exists, BAHA Act Chapter 211 has provisions for regulating import, export and use of GMOs, no regulations in place, new Biosafety Bill to be drafted; Dominica – 2014 Climate Change, Environment and Natural Resource Management Bill exists, which includes a section on biosafety (Chapter XVIII); Grenada – Biosafety Bill submitted to the Ministry of Legal Affairs (2015), Biosafety Policy endorsed by Cabinet (2014), work on the administrative system is ongoing; Guyana - Draft Bill and draft regulations being finalised; St. Kitts & Nevis – Biosafety Act 2012 (in existence), biosafety Amendment Bill 2016, final draft of the Biosafety Regulations 2016, Biosafety Policy, and draft Biosafety Administrative System developed and under review; St. Lucia – Biosafety Policy endorsed by the Cabinet in May 2017. Biosafety Bill and Regulations endorsed in 2018. Discussions are ongoing between the AG’s Office and the Department of Sustainable Development to fine tune the Bill in preparation to have it enacted; St. Vincent & the Grenadines – draft policy being finalised, draft legislation completed, and this along with the draft administrative system developed, are being readied for submission to Cabinet; Suriname – a draft Biosafety Law exists, regulations have been identified but these have not been drafted as yet; Trinidad & Tobago – Biosafety Policy (2014) is being updated, legislation has been drafted and is being reviewed, and work on the development of a draft administrative system is in progress | S |
| 1.3 Public participation and stakeholder consultations over regulatory developments through national discussion and meetings. | 31 March 2012 to 30 September 2016 | 100 | 100 |  | S-HS |
| 1.4 Formulation of national biosafety policies, including public outreach program in support of development and adoption of national biosafety policy. (à coupled to activities 4.4 and 4.5) | 31 March 2012 to 31 December 2018 | 90 | 100 | See item 1.2. As noted above, Barbados and Bahamas still have to develop biosafety policies prior to the drafting of legislation. | S |
| 1.5 Coaching and direct assistance to support effective operations of the National Biosafety Authorities and coordinating mechanisms for assessments, decision-making, and monitoring of biosafety and LMOs. | 31 March 2012 to 31 December 2018 | 100 | 100 |  | S-HS |
| 1.6 Develop strategies and procedures that clearly identify institutional mandates, roles and responsibilities in biosafety (risk assessment, risk management and monitoring) and identify capacity gaps that could be filled by specialized institutions or a national or regional roster of experts. | 31 March 2012 to 30 April 2018 | 90 | 100 | 9 out of 12 project countries indicated that they have draft administrative systems in place. Both St. Lucia and Antigua and Barbuda benefitted from the IWPs conceptualised within the 4th ICGEB subcontract. In the case of St. Lucia the outcome was the development of food safety assessment documents for release to the public at an appropriate time. For Antigua and Barbuda, the output was the development of internal processes and guidance, with no consideration as yet being given to the release of the food safety assessment documents to the public. | S |
| 1.7 Using inputs from activity 2.1 assess and put in place financing options for maintaining NBF operations, including BCH functions, considering cost recovery mechanisms and administrative charges for biosafety procedures. | 31 March 2012 to 31 December 2018 | 90 | 100 | The financing option has been agreed upon and the regional approach has been accepted. | MS |
| 1.8 Produce manuals, guidelines and protocols for following administrative procedures within and between National Biosafety Authorities. | 31 March 2012 to 31 October 2018 | 100 | 100 | See 2.11 |  |
| 1.9 Establish formal and informal ties with scientific/research/biotech sector, for scientific validation (inputs and peer review) of criteria and methodology used for LMO risk assessments. (à coupled to activity 2.11) | 31 March 2012 to 30 June 2016 | N/A | N/A |  | HS |
| ## 1.10 Establish Scientific and Technical Advisory Committees and/or Roster of Experts in each country, or equivalent advisory structures/ad hoc mechanisms to support biosafety decision-making. | 31 March 2012 to 30 June 2016 | 100 | 100 |  | NA |
| Component 2: Enhanced establishment and upgrading of resource base and institutional capacities for Biosafety decision-making and management |  |  |  |  |  |
| 2.1 Conduct capacity/needs assessment of key institutions with responsibility for risk assessment and monitoring of LMOs, including assessment of laboratory capacities (equipment, technologies and personnel) and information management needs /capacities (à coupled to activity 4.1). | 1 March 2012 to 31 May 2015 | 100 | 100 |  | S |
| 2.2 Facilitate short term attachments for (scientists) personnel involved in risk assessment or risk management of LMOs. | 1 April 2012 to 31 December 2015 | 100 | 100 |  | S |
| 2.3 Procurement of laboratory equipment, supplies and reagents required for establishing and/or equipping and operationalizing national /reference laboratories for LMO testing and risk assessment that could eventually offer regional services. (àcoupled to activity 2.7) | 1October 2012 to 30 June 2016 | 100 | 100 |  | S |
| 2.4 Conduct detailed analysis to determine the most efficient institutional arrangements (national and regional) for conducting detection tests and research in support of the risk management process. (à coupled to activity 5.2.iii) | 1 January 2014 to 30 June 2015 | 100 | 100 |  | S |
| 2.5 Regional agreement reached on which biosafety services are to be supported regionally, with definition of financing mechanisms and institutional arrangements and responsibilities. (à coupled to activity 5.2.iv) | 1 October 2012 to 31 October 2017 | 100 | 100 |  | S |
| 2.6 Institute recommendations for the best arrangement for coordinating mechanisms for monitoring of biosafety. Select laboratories / research centres that shall provide risk assessment/management support to neighbouring countries. (à coupled to activity 5.2.iv) | 1 October 2013 to 31 July 2015 | 100 | 100 |  | S |
| 2.7 Procure laboratory equipment, supplies and reagents required for operationalizing LMO testing and sampling techniques and enable technical support for risk management and LMO monitoring to be provided at the regional level. (à coupled to activity 2.3 and 2.6) | 1 March 2015 to 30 June 2016 | 100 | 100 |  | NA |
| 2.8 Design, and if possible, put in place a coordinated regional/national accreditation scheme for biosafety laboratories. | 1 September 2015 to 31 December 2015 | N/A | N/A | This is not applicable as it was to be part of the work programme of the Centre of Excellence in Biosafety (CEB) that was envisioned in the original project design; however the CEB was replaced by the Caribbean Centre for Biosafety (a virtual information node on the website). | NA |
| 2.9 Work closely with the Bureau of Standards of each country to strengthen capacity to provide monitoring services and standards for biosafety management. | 1 May 2015 to 30 September 2015 | N/A | N/A | This is not applicable as it was agreed in the early part of the project that national partners should pursue this activity on their own | NA |
| 2.10 Establish formal (MOU’s) linkages between national and regional laboratories and agencies with biosafety capacity as part of technical in support for conducting coordinated biosafety risk assessments. | 1 May 2015 to 30 June 2016 | 100 | 100 |  | S |
| 2.11 Develop technical documents and tools (standards, protocols and guidelines) for biosafety risk assessment, risk management, LMO detection (laboratory testing) and sampling, quality assurance and standardization across laboratories, and identification of LMOs. | 1 April 2015 to 31 March 2016 | 100 | 100 | In all a total of 10 guidelines were produced by the ICGEB | HS |
| 2.12 Propose, and if possible, agree to border control procedures for imports /exports of LMOs, including transshipments and transit, with feedback and inputs from national Customs Offices and CARICOM. | 1 May 2015 to 31 December 2018 | 80 | 100 | # See 1.6. While it may be possible to implement some aspects of these systems, endorsement of these as well as the regulations at the national level is required to ensure the effectiveness of these systems. The Bureau of Standards can be engaged nationally to assist with this. In the draft model legislation developed, Part III addresses the issue of “Control Measures For Regulated Activities”. | MS |
| Component 3: Human resources development in support of Biosafety management throughout CARICOM Member States |  |  |  |  |  |
| 3.1 Develop training manuals and curricula for short courses. | 1 January 2013 to 31 March 2016 | 100 | 100 |  | HS |
| 3.2 Solicit Government agencies to designate staff for training courses. Those being nominated for training in risk assessment will need to confirm their longevity and continuing services with the institution. | 30 June 2013 to 31 March 2016 | 100 | 100 |  | S |
| 3.3 Conduct training on application of standards, protocols and guidelines developed above (2.9), targeted at members of the National Biosafety Authorities and the Scientific and Technical Advisory Committees (or equivalent structures) and at other relevant technical staff. | 31 July 2013 to 30 June 2016 | 100 | 100 |  | S |
| 3.4 Develop a regional Biosafety training programme (with practical exercises and training manuals) intended for scientific and non-scientific personnel involved in LMO risk assessment, management and communication; LMO monitoring, control, and detection; and in certification programmes in biosafety-related areas. | 1 October 2012 to 31 March 2016 | 100 | 100 |  | HS |
| 3.5 Launch inscriptions to the regional biosafety training programme. | 1 March 2014 to 31 March 2016 | 100 | 100 |  | S |
| 3.6 Conduct training workshops and short courses for technical, scientific and non-scientific personnel, including customs officers and border inspectors and laboratory technicians and biotechnology graduates. | 1 April 2013 to 28 February 2017 | 100 | 100 |  | S |
| 3.7 Public-private encounters to discuss the scope of Biosafety risk management measures in different sectors. | 1 April 2015 to 31 December 2018 | 95 | 100 | Although it was not possible to host the awareness building meeting for key decision-makers as planned in April 2018, information packages were posted to Permanent Secretaries in the Ministries of Agriculture and Foreign Affairs in the Region. A significant amount of work still however has to be done in this regard post project. | S |
| 3.8 Nominations to, and compilation of, Regional Roster of Biosafety Experts. | 1 October to 31 May 2016 | 100 | 100 |  | S |
| 3.9 Coaching or training for teachers and specialists involved in human resources formation on the requirements and opportunities of the CPB. | 1 October 2013 to 30 September 2014 | N/A | N/A | This is not applicable as it was agreed in the early part of the project that national partners should pursue this activity on their own | NA |
| 3.10 Seek knowledge exchange with CARICOM and customs officers and border inspectors (feedback and inputs concerning operational challenges, information requirements and standardized procedures) for the preparation of viable border control procedures for imports /exports of LMOs. (à coupled to activity 4.12) | 1 October 2012 to 31 December 2018 | 90 | 100 | # In addition to the work done within the context of the IWPs, the completion of the draft model legislation can also assist in this regard, as in Part III, “Control Measures for Regulated Activities”, Divisions 1 – 5, guidance is given as to the requirements for the import and export of LMOs. This can assist countries with respect to the development of the requisite procedures for these activities. | S |
| 3.11 Conduct a simulated LMO decision-making process (for training purposes) with participation of at least 10 of 12 countries. | 1 February 2016 to 29 February 2016 | 100 | 100 |  | S |
| 3.12 Carry out LMO detection analyses on mock or real LMO samples (for demonstrative purposes), involving at least 2 laboratories in the region. | 1 February 2015 to 28 February 2015 | 100 | 100 |  | S |
| 3.13 Conduct trainings in BCH use (in synergy with BCH-II global project) for technical personnel (from >1 Government institution) and selected stakeholders. (à coupled to activity 4.8) | 1 April 2013 to 30 November 2015 | 100 | 100 |  | S |
| 3.14 Explore potential collaboration and synergies with other UNEP/GEF biosafety capacity building projects in the region (especially Cuba). | 1 October 2014 to 30 June 2014 | 100 | 100 |  | S |
| 3.15 Evaluate the possible development of a postgraduate programme in biosafety, the adoption of novel training curricula, manuals, methods and experiences derived from the project into the regional biosafety training programme. | 1 January 2012 to 30 June 2015 | 100 | 100 |  | S |
| 3.16 Establish self-financing mechanisms that will sustain the regional training programme beyond the project. | 1 January 2012 to 31 December 2013 | 100 | 100 |  | S |
| Component 4: Strengthening Biosafety information management in the Caribbean sub-region |  |  |  |  |  |
| 4.1 Conduct needs assessment to determine the level of resources (physical, human and financial) required to establish and maintain the regional and national biosafety clearing house mechanisms and databases (à coupled to activity 2.1 and 5.2 iii) | 1 February 2015 to 31 December 2018 |  |  | The proposed road map for biosafety in the region was presented at the project closure meeting in April 2018. Additional discussions were also held with CAHFSA in December 2018 on this issue. The work done by Dr. Ocampo with project countries in the enhancement of their nBCHs would have also encompassed elements of this activity. | MS |
| 4.2 Establish a collaborative national/regional / international network for information exchange especially with regards to the Biosafety decision-making and notification processes and links to IAS management. | 1 February 2015 to 31 December 2018 | 95 | 100 | Formalisation of the technical working group of biosafety remains outstanding. This would have to be done by CAHFSA post project. Guidelines and a user’s manual have been developed to direct this process. | MS |
| 4.3 Procure equipment/software and determine data exchange protocols needed to support national and regional information management systems. | 1 April 2015 to 31 July 2015 | N/A | N/A | This is not applicable as it was determined that this activity would be folded in to the regional Biosafety Clearing House (rBCH). | NA |
| 4.4 Design a regional Biosafety public education and outreach strategy (PEO) to promote awareness and communication with various target audiences. | 1 April 2015 to 30 September 2015 | 100 | 100 |  | S |
| 4.5 Implement the Biosafety public education and outreach strategy (PEO) through both national and regional-level activities, including the promotion of BCH use amongst non-government sectors, Biosafety sensitization aimed at decision-makers and politicians, and the production and distribution of a monthly electronic and printed newsletter on Biosafety and other outreach materials. | 1 June 2015 to 31 March 2017 | 100 | 100 |  | S |
| 4.6 Generate and compile Biosafety data (including project products and data on LMOs traded and approved within CARICOM) in order to populate regional and national Biosafety database systems, with links to IAS data if necessary. | 1 December 2014 to 30 June 2016 | 100 | 100 |  | S |
| 4.7 Establish Biosafety clearinghouse mechanisms in each country, both to house information and database systems and to comply with BCH Central Portal registering requirements. These mechanisms should enable the general public to present their opinions and comments on applications, decisions and notifications by electronic means. | 1 July 2015 to 30 April 2016 | 100 | 100 |  | S |
| 4.8 Conduct trainings in BCH use (in synergy with BCH-II global project) for technical personnel and selected stakeholders. (à coupled to activity 3.12) | 1 December 2015 to 31 December 2015 | 100 | 100 |  | S |
| 4.9 Design and determine the institutional host for an effective regional database and clearinghouse mechanism that has inter-institutional linkages, linkages to national BCH systems, compatibility with the BCH Central Portal, and identity as the primary regional node for Biosafety information. | 1 April 2013 to 30 November 2015 | 100 | 100 |  | S |
| 4.10 Initiate operations of the regional Biosafety clearinghouse node, starting with a pilot phase (until mid-term). | 1 December 2015 to 31 December 2015 | 100 | 100 |  | S |
| 4.11 Undertake assessment of effectiveness and usefulness of regional and national Biosafety clearing house mechanisms and database systems to derive lessons learnt and review sustainability factors. | 1 October 2014 to 31 March 2015 | N/A | N/A | This activity was eliminated | NA |
| 4.12 Meetings with Customs Offices and regional organizations to reach agreements on information and documentation requirements for LMO imports. (à coupled to activity 3.8) | 1 October 2013 to 31 December 2018 | 70 | 100 | See 3.10. In addition to the capacity building activities undertaken in August and October 2016, the IWPs also provided a forum for such discussions. These would however have to be continued post project at the national level. | S |
| Component 5: Regional processes in support of the Project and NBF sustainability in the Caribbean |  |  |  |  |  |
| 5.1 Prepare Terms of Reference (TORs) for a viability assessment that analyzes the financial, technical and political implications of various options for establishing sustainable Biosafety services and functions at the regional level. | 1 October 2011 to 31 December 2013 | 100 | 100 |  | S |
| - Organize a technical regional workshop (virtual) to review and adopt TORs. | 1 January 2012 to 31 December 2012 | 100 | 100 |  | S |
| 5.3 Conduct the viability assessment, taking into account results of national and regional needs /capacity assessments conducted previously. | 1 October 2011 to 31 March 2013 | 100 | 100 |  | S |
| 5.4 Determine the potential of the Regional BCH Node to become the “gatekeeper” of regional Biosafety applications (electronic tracking LMOs applications and permits granted, ensuring public access to information on the processing of such applications, facilitating public input into the risk assessment process, etc). | 1 February 2015 to 31 December 2018 | 100 | 100 |  | S |
| 5.5 Review results of viability assessment and potential for expanding Regional BCH Node functions, and organize a political regional workshop to reach a decision on which Biosafety services and responsibilities should be devolved at the regional level. | 1 July 2013 to 30 September 2013 | N/A | N/A | This is not applicable as it was determined that this activity would be folded in to the regional Biosafety Clearing House (rBCH). | NA |
| 5.6 Establish institutional framework for providing regional Biosafety services and taking on regional Biosafety responsibilities, including an initial pilot phase for regional coordination of Biosafety tasks. | 1 October 2013 to 30 June 2016 | 100 | 100 |  | S |
| 5.7 Based on the decision reached above, develop a self-financing plan for the Biosafety services and technical support mechanisms to be provided regionally, including the maintenance of the regional BCH node. | 1 October 2013 to 30 June 2016 | 100 | 100 |  | S |
| 5.8 Apply adaptive management, ensuring timely reporting to NSC / PSC and prompt correction of deviations from plans (stage control and change control), including changes derived from decision on regional Biosafety mechanisms. | 1 October 2011 to 31 December 2018 | 90 | 100 | Feedback from formal and informal meetings held with UNEP, along with the RSC meetings all assisted in the identification of strategies to enhance implementation. Country missions served the purpose of addressing issues on a face-to-face basis at the national level. | S |
| 5.9 Incorporate Midterm Evaluation report findings into modified work plans and share revised project log frame with all those concerned. | 1 October 2011 to 31 December 2018 | 95 | 100 |  | S |
| 5.10 Invite relevant regional/international organizations to RSC meetings to take stock of potential synergies with IAS and pest management frameworks (commonalities in operations, assessment methodologies, data management and training schemes). | 1 October 2012 to 30 September 2013 | N/A | N/A | Activity eliminated | NA |
| 5.11 RSC to take decision on how best to capitalize on potential synergies with IAS and pest management frameworks. | 1 October 2013 to 31 March 2014 | N/A | N/A | Activity eliminated | NA |
| 5.12 Prepare and implement an action plan to pursue synergies between LMO and IAS / pest management frameworks. | 1 October 2011 to 31 December 2013 | N/A | N/A | Activity eliminated | NA |
| 5.13 Incorporate considerations over certification requirements and other trade-related issues in assessment of effectiveness and usefulness of regional and national BCH mechanisms and database systems (à coupled to activity 4.11). | 30 June 2014 | N/A | N/A | Activity eliminated | NA |
| 5.14 Appoint and hire regional project personnel (Lead Executing Agency’s Project Team). | 31 October 2011 to 31 October 2012 | 100 | 100 |  | S |
| 5.15 Establish and equip regional project office (PMU: Project Management Unit). | 31 October 2011 to 31 October 2012 | 100 | 100 |  | S |
| 5.16 Appoint project personnel in participating countries (National Project coordinator and Project Focal Points) | 31 October 2011 to 30 May 2014 | 100 | 100 |  | S |
| 5.17 Establish National Steering Committees (NSC) in each country | 1 January 2012 to 30 May 2014 | 100 | 100 |  | S |
| 5.18 Establish national project offices and financial operations for fund transfers to countries. | 31 December 2013 to 31 December 2014 | 100 | 100 |  | S |
| 5.19 Detailed project planning, including preparation of national logframes and annual workplans. | 30 September 2013 to 31 January 2016 | 90 | 100 |  | S |
| 5.20 Review & finalize annual workplans. | 1 January 2012 to 31 January 2019 | 100 | 100 |  | S |
| 5.21 NSC meetings (at least every 6 months or twice a year). | 1 January 2012 to 30 June 2016 | 100 | 100 |  | S |
| 5.22 Inception workshop / first RSC meeting. | 31 December 2011 | 100 | 100 |  | S |
| 5.23 RSC meetings (physical and virtual) at least every 6 months or twice a year – with physical meetings once a year. | 1 November 2012 to 30 April 2018 | 100 | 100 |  | S |
| 5.24 Establish a project financial management and accounting system. | 30 December 2011 to 31 May 2016 | 100 | 100 |  | S |
| 5.25 Review & finalize M&E plan, indicators and baseline. | 1 March 2015 to 31 March 2015 | 100 | 100 |  | S |
| 5.26 Implement M&E plan and monitor the achievement of benchmarks and outputs as specified in annual workplans. | 1 July 2012 to 31 December 2018 | 90 | 100 |  | S |
| 5.27 Survey design and application amongst Govt staff for measuring outcomes of Comp 1. | 30 November 2016 | 100 | 100 |  | S |
| 5.28 Project reporting – LEA to prepare and submit semi-annual progress reports and financial reports to UNEP (GEF funds and co-financing). | 1 January 2012 to 31 December 2018 | 95 | 100 |  | S |
| 5.29 Prepare and update annually project equipment inventory. | 1 January 2012 to 31 December 2018 | 95 | 100 |  | S |
| 5.30 Annual Project Implementation Reviews (PIR). | 30 June 2012 to 31 January 2019 | 95 | 100 |  | S |
| 5.31 Annual financial audit of project accounts. | 1 October 2012 to 31 March 2019 | 90 | 98 | Ongoing. The report for the 2017 regional component and country audits for the period 2012 – 2016 were sent to UNE. The 2018 audit of the regional component has been completed. The draft report still has to be submitted to the UWI for forward to UNE. | S |
| 5.32 Midterm Evaluation (independent study managed by UNEP) - includes round two of Tracking Tools. | 1 August 2014 to 31 October 2014 | 100 | 100 |  | S |
| 5.33 Annual work plan and budget revisions with UNEP. | 1 January 2012 to 28 February 2019 | 95 | 100 |  | S |
| 5.34 Prepare and submit terminal (closure) documents to UNEP, including Final Report, final inventory, final audit, last PIR, and final expenditure statement. | 1 January 2019 – 28 February 2019 | N/A | 100 |  | S |
| 5.35 Terminal Evaluation (independent study managed by UNEP) –includes final round of Tracking Tools. | 1 September 2018 - 31 March 2019 | N/A | 100 | The final evaluation report was submitted in May 2019. | S |

Overall project implementation progress 9 (To be completed by UNEP GEF Task Manager.):

| FY2018 rating [previous] | FY2019 rating [current] | Justification of the current rating and explanation of reasons for change (positive or negative) since previous reporting periods. |
| --- | --- | --- |
| S | S | The rating of progress in the delivery of outputs should be assessed in terms of both quantity and quality. The assessment must consider ownership by, and usefulness to, intended beneficiaries and the timeliness of their delivery. Use the comments column to explain the reasons behind the success or shortcomings of the project in delivering its programmed outputs and meeting expected quality standards. The project was granted an extension to June 2020 so as to develop a pathway or strategic outlook both at the regional and national levels toward achieving the outcomes only partially achieved under the project. In this regard, this reporting will constitute the final ‘full’ annual PIR. Overall the project successfully implemented the vast majority of the activities and resulted in the realization of most of the expected outputs. It is at the outcome level expressed in terms of transition toward uptake and mainstreaming at national level and regional levels that there are questions over longer-term sustainability; this was captured in the reporting by the project manager in this PIR and captured in the terminal evaluation. In the first instance, sustainability will be highly dependent on national policy driveness. This in turn will be dependent on ensuring that regional-level coordination (the mechanism that the project fostered) remains visible and strong, which calls into focus the role of CAHFSA and the other regional agencies in continuing to lead the process and to support countries of CARICOM. |

Risks in implementation

This section should be completed by the Project Manager and summarize implementation risks (e.g. procurement delays, reputational risks etc).

The first column should be completed by the Project Manager and the second column should summarize the recommendations that the Project Manager and Task Manager have agreed upon to address the problem/risk.  This section should inform the risk rating in section 3.3.

| Problems/risks identified | Agreed recommended actions | By whom | When |
| --- | --- | --- | --- |

________________________

5 Outputs as described in the project logframe or in any updated project revision.

6 As per latest workplan (latest project revision)

7 Implementation may be assessed by qualitative assessments, percentage of delivery, and/or budget expenditure (planned and actually spent).  The 2018 assessment should be copied from previous PIR.

8 To be provided by the UNEP Task Manager

9 Use GEF Secretariat required six-point scale system: Highly Satisfactory (HS), Satisfactory (S), Marginally Satisfactory (MS), Marginally Unsatisfactory (MU), Unsatisfactory (U), and Highly Unsatisfactory (HU)

3.3. Risk Rating [Insert the Medium and High Risks and mitigation measures identified at CEO endorsement (e.g. Section A.5) and any relevant risk from safeguards screening and/or management plans.]  Expand the table to include medium and high risks observed during implementation, e.g. problems identified in sections 3.1. and 3.2.

| Risk | Mitigation at CEO approval | Mitigation at implementation | Rank |
| --- | --- | --- | --- |
| Governments’ commitment to addressing potential risks associated with modern biotechnology is reduced due to changes in the political environment and crisis presented by global economic downturn | - A multi-media public awareness campaign will be implemented at the national level in each participating country, including a focus on the potential economic and trade benefits of biosafety systems, to build a more receptive political audience with broad-based public support. - CARICOM will continue to raise political awareness and mobilize political support through the development and implementation of the CARICOM Policy on Biosafety and Biotechnology which affirms environmental and economic benefits through biosafety application. Also the recent re-endorsement of the project by COTED is a clear sign of support. | - Small strides have been made in this area with the production of outreach materials including brochures, videos, posters and fact sheets. More still has to be done. - CARICOM via CAHFSA has been assisting the project in this regard. The policy developed within the project has received CARICOM approval. | CEO: H |
|  |  |  | TM: S |
|  |  |  | PM: S – the legislation in most countries is still to be endorsed |
| CARICOM member states ineligible for the current project remain at the margins of biosafety capacity building efforts and compromise the extent to which biosafety standards can be upheld in the sub-region. | - Jamaica has confirmed its intention to join this regional effort by presenting an “add-on” project as soon as it has laid its instrument of ratification with the CBD Secretariat, while Haiti, still in a slow process of recovery, has indicated its interest in acceding to the CPB. In as far as possible -subject to consensus and co-financing support- all efforts will be made in this project to be inclusive of the full CARICOM membership. | - Jamaica and Haiti did not participate in the project, despite Jamaica having ratified the CPB in December 2012. | CEO: M |
|  |  |  | TM: M |
|  |  |  | PM: M – the concept note takes the need for “full CARICOM membership” into consideration |
| The lack of skills among staff within key national agencies to support biosafety management, coupled with existing weak institutional coordination and lack of human resources and infrastructure | - A key element of the project is the establishment of a clearing house node and the necessary legal and inter-institutional coordination mechanisms for biosafety risk management that will function with or without regional support mechanisms to re-enforce and enhance national institutional frameworks. - An extensive training program will be undertaken to strengthen biosafety risk management skills amongst existing staff in key national agencies. | - All countries received BCH training under the project, in addition to which, where requested, the project hired a consultant to provide further support at the national level. - Thirteen workshops were held over the duration of the project undertaken in key biosafety-related areas. A MSc. Biosafety was also introduced. | CEO: H |
|  |  |  | TM: M |
|  |  |  | PM: M |
| Lost opportunities to cross-fertilize and coordinate between regional and national initiatives and seek common biosafety management approaches undermine: (a) national attempts to uphold effective biosafety levels; and (b) regional harmonization in support of CSME. | - The regional component of the project will scrutinize and resolve the adoption of harmonized biosafety risk management standards, protocols, tools and manuals for dissemination and use at the national level, and will ensure coordination and a majority decision on regional biosafety services and support mechanisms. - The training component of the project will support an extensive training program on biosafety (risk assessment/management), including standards, protocols, tools and manuals, which will instill a more uniform approach to biosafety management across the region. - National component activities will support a review of proposed legal and institutional NBFs to ensure, where possible, that opportunities for regional harmonization remain viable in the context of the CSME. | - A number of guideline documents were produced and shared with countries. All countries also received training in decision-making and the application of these guidelines. It has also been suggested that CAHFSA, using the guidance risk assessment framework developed under the project, could prepare a risk assessment model for use by the proposed risk assessment group. - An extensive training programme was undertaken, with workshops being conducted in a number of key biosafety areas. - To support the review of the NBFs at the legal and institutional NBFs, training in biosafety legislation and regulation was provided to all project countries so that any reviews could take the issue of harminisation into consideration. Post-workshop support was also provided by a consultant. In addition, draft model biosafety legislation has been developed for the region. | CEO: H |
|  |  |  | TM: M |
|  |  |  | PM: M |
| Absence of competent laboratory and trained staff (at national or regional level) to undertake biosafety testing and research or provide such services undermines effective implementation of the Cartagena Protocol | - The project offers opportunities for: (a) evaluation of national and regional biosafety laboratory capacity and needs, (b) procurement of minimum level of equipment for select detection laboratories which will serve the needs of host and adjoining project countries, (c) the establishment of validated analytical protocols, which can later be harmonized, and (d) the training of laboratory staff in LMO analysis. - The project will strengthen the capacity of a critical mass of biosafety management staff within a coordinated network of national and regional laboratories. | - Based on the evaluation of capacity and needs a basic package of laboratory equipment, materials and supplies was developed. Lab manuals were also produced, and lab detection workshops held. - At the national level, each country identified and designated a laboratory that could be used for GMO testing. Regionally, the laboratories on the 3 UWI campuses were also upgraded to provide support to the countries in terms of: (i) the conduct of advanced testing; (ii) provision of in-service training for staff of the national laboratories; and (iii) provision of opportunities for short-term laboratory attachments | CEO: H |
|  |  |  | TM: M |
|  |  |  | PM: M |
| Sustaining the effective implementation of the Cartagena Protocol after project completion will be a key challenge due to limited resources (human, technical, financial) | - The regional component of the project will support an evaluation of self-financing mechanisms and the implementation of a self-financing strategy to ensure that adequate resources are available to sustain project outcomes after project completion. - Giving due political consideration to the establishment of self-sustaining regional support mechanisms for biosafety will increase the likelihood and ability of CARICOM Member States to maintain the biosafety regimes that are put in place by this project. | - In the early stages of the project it as envisioned that the Centre of Excellence in Biosafety (CeB) would fulfil this requirement. In the absence of this suggested mechanism it may be necessary, in the proposed discussions to be held with CAHFSA to re-examine this project | CEO: H |
|  |  |  | TM: S |
|  |  |  | PM: S |
| Enforcement of biosafety risk management protocols may be difficult due to a lack of awareness of potential risks from modern biotechnology at both the institutional and public level. | - Biosafety clearing houses will be established at the national and a coordinating node at regional level which will disseminate to the public information on LMOs (and possibly IAS) that may be introduced in the Caribbean, or that have been approved for use, and any products from modern biotechnology that may be undergoing a risk assessment prior to release. | - There is ongoing work in the BCH III project that can build on the work that was done under the implementation project. Future work will seek to ensure that more attention is given to the communication aspect. | CEO: M |
|  |  |  | TM: M |
|  |  |  | PM: M |
| Changes in CSME trade regime lead to actions that affect the status of biodiversity in the Caribbean region | - Through information exchange, public education, and training undertaken under the project it is unlikely that CARICOM countries will support trade rules that encourage or support the unrestrained trade in LMOs or IAS that may be harmful to national and regional biodiversity. | - Information provided to stakeholders within the context of the project never sought to influence perspectives, but to merely serve as a basis for countries (in consultation with their publics), to arrive at their own decisions regarding LLMOs. | CEO: M |
|  |  |  | TM: L |
|  |  |  | PM: L |
| Absence of information on the risks to the Caribbean region’s biodiversity and human health from LMOs (and possibly IAS) undermines public and political level support for effective NBF implementation | - Regional and national information exchange mechanisms (biosafety clearing houses) will be fully established under the project to develop a baseline of information on LMOs (and links to other biosecurity information sources) that present a possible risk to Caribbean biodiversity and human health. | - All project countries have their established BCHs, which they have to populate. Under the project, a rBCH was also established. | CEO: L |
|  |  |  | TM: L |
|  |  |  | PM: L |
| The partitioning of GEF funds between country-level activities and the regional component of the project is not optimum for achieving project objectives and slows down NBF operationalization | - Striking the right balance for countries to have sufficient resources to operationalize their NBFs may require additional fund raising efforts while the project is in execution. This task will require lobbying and active search for further donor support intended for national capacity development in areas relevant to biotechnology, biosafety and environment. | - This was not undertaken under the implementation project. While there were countries that wished they couidl have had additional funds for the implementation of national activities, in most instances the funds allocated were underutilised. | CEO: M |
|  |  |  | TM: L |
|  |  |  | PM: L |
| ESERN [add cells as appropriate to capture all Medium and High Risks] |  |  |  |
| Overall Risk Rating Project Manager |  |  | M |
| Overall Risk Rating Task Manager |  |  | M |

| FY2018 rating [previous] | FY2019 rating [current] | Justification of the current risk rating and explanation of reasons for change (positive or negative) since previous reporting periods. |
| --- | --- | --- |
| M | M | Elaborate on indicated risks, including climate change, potential social and environmental risks that might prevent the project to deliver the expected results and, whenever possible, the proposed measures to address these risks. Refer also to the assumptions and drivers e.g. when the assumptions are not holding and/ or the drivers are not in place. Please refer to the GEF risk rating table below The project has substantially completed its activities; the assumptions against which the project risk is being evaluated have largely held by the end of project. The long-term outlook in terms of countries continuing with the mainstreaming of biosafety frameworks is beyond the scope of the project. |

High Risk (H): There is a probability of greater than 75% that assumptions may fail to hold or materialize, and/or the project may face high risks. 
Substantial Risk (S): There is a probability of between 51% and 75% that assumptions may fail to hold and/or the project may face substantial risks. 
Modest Risk (M): There is a probability of between 26% and 50% that assumptions may fail to hold or materialize, and/or the project may face only modest risks. 
Low Risk (L): There is a probability of up to 25% that assumptions may fail to hold or materialize, and/or the project may face only modest risks.

Optional Annexes and/or Links:

- Project Steering Committee Minutes of the year reported

- Half yearly Report

- Quarterly Reports

- Risk Factor Table form previous template (recommended for substantial and high-risk projects)

Risks Factor Table

There are two tables to assess and address risk: the first “risk factor table” to describe and rate risk factors; the second “top risk mitigation plan” should indicate what measures/action will be taken with respect to risks rated Substantial or High and who is responsible to for it.

High Risk (H): There is a probability of greater than 75% that assumptions may fail to hold or materialize, and/or the project may face high risks. 
Substantial Risk (S): There is a probability of between 51% and 75% that assumptions may fail to hold and/or the project may face substantial risks. 
Modest Risk (M): There is a probability of between 26% and 50% that assumptions may fail to hold or materialize, and/or the project may face only modest risks. 
Low Risk (L): There is a probability of up to 25% that assumptions may fail to hold or materialize, and/or the project may face only modest risks.

RISK FACTOR TABLE

Project Managers will use this table to summarize risks identified in the Project Document and reflect also any new risks identified in the course of project implementation. The Notes column should be used to provide additional details concerning manifestation of the risk in your specific project, as relevant. The “Notes” column has one section for the Project Manager (PM) and one for the UNEP Task Manager (TM). If the generic risk factors and indicators in the table are not relevant to the project rows should be added. The UNEP Task Manager should provide ratings in the right hand column reflecting his/her own assessment of project risks.

|  |  |  |  | Project Manager Rating |  |  |  |  |  | Notes | Task Manager Rating |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Risk Factor | Indicator of Low Risk | Indicator of Medium Risk | Indicator of High Risk | Low | Medium | Substantial | High | Not Applicable | To be determined |  | Low | Medium | Substantial | High | Not Applicable | To be determined |
| INTERNAL RISK |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Project management |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Management structure | Stable with roles and responsibilities clearly defined and understood | Individuals understand their own role but are unsure of responsibilities of others | Unclear responsibilities or overlapping functions which lead to management problems | x |  |  |  |  |  | PM : | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: |  |  |  |  |  |  |
| Governance structure | Steering Committee and/or other project bodies meet periodically and provide effective direction/inputs | Body (ies) meets periodically but guidance/input provided to project is inadequate. TOR unclear | Members lack commitment Committee/body does not fulfil its TOR | x |  |  |  |  |  | PM : | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: |  |  |  |  |  |  |
| Internal communications | Fluid and cordial | Communication process deficient although relationships between team members are good | Lack of adequate communication between team members leading to deterioration of relationships and resentment | x |  |  |  |  |  | PM: | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: |  |  |  |  |  |  |
| Work flow | Project progressing according to work plan | Some changes in project work plan but without major effect on overall timetable | Major delays or changes in work plan or method of implementation | x |  |  |  |  |  | PM: | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: |  |  |  |  |  |  |
| Co-financing | Co-financing is secured and payments are received on time | Is secured but payments are slow and bureaucratic | A substantial part of pledged co-financing may not materialize | x |  |  |  |  |  | PM: | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: |  |  |  |  |  |  |
| Budget | Activities are progressing within planned budget | Minor budget reallocation needed | Reallocation between budget lines exceeding 30% of original budget | x |  |  |  |  |  | PM: | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: |  |  |  |  |  |  |
| Financial management | Funds are correctly managed and transparently accounted for | Financial reporting slow or deficient | Serious financial reporting problems or indication of mismanagement of funds |  |  |  |  |  | x | PM: |  | X |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: There does not appear to be any significant flags associated with the audits but there have been inconsistencies in how data was captured in Anubis versus how these have been picked up by the auditors – in some cases significant variance. |  |  |  |  |  |  |
| Reporting | Substantive reports are presented in a timely manner and are complete and accurate with a good analysis of project progress and implementation issues | Reports are complete and accurate but often delayed or lack critical analysis of progress and implementation issues | Serious concerns about quality and timeliness of project reporting | x |  |  |  |  |  | PM: | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: |  |  |  |  |  |  |
| Stakeholder involvement | Stakeholder analysis done and positive feedback from critical stakeholders and partners | Consultation and participation process seems strong but misses some groups or relevant partners | Symptoms of conflict with critical stakeholders or evidence of apathy and lack of interest from partners or other stakeholders |  | x |  |  |  |  | PM: This remains and outstanding matter despite increased efforts to increase awareness about the project prior to its closure in December 2018. Work still has to be done post project at both the national and regional levels to continue to raise awareness about biosafety and the support needed. |  | X |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: This is being addressed based on available remaining funds in the project with an extension into 2020 principally to develop a strategic direction that will draw on the findings of the terminal evaluation and the recommendations from the close-out meeting of the project. This will closely involve UWI (capacity building/ research) and CAFHSA (regulatory) as they remain critical institutional nodes to help drive the regional agenda |  |  |  |  |  |  |
| External communications | Evidence that stakeholders, practitioners and/or the general public understand project and are regularly updated on progress | Communications efforts are taking place but not yet evidence that message is successfully transmitted | Project existence is not known beyond implementation partners or misunderstandings concerning objectives and activities evident | x |  |  |  |  |  | PM: In Q3 and 4 of 2018, the project participated in a number of activities all geared towards apprising the general public and key decision-makers regarding the project. | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: Further opportunity should be sought with the extension of the project to continue awareness raising |  |  |  |  |  |  |
| Short term/long term balance | Project is addressing short term needs and achieving results with a long term perspective, particularly sustainability and replicability | Project is interested in the short term with little understanding of or interest in the long term | Longer term issues are deliberately ignored or neglected |  | x |  |  |  |  | PM: Roles have been identified for both CAHFSA and the UWI regarding both short and long-term sustainability of project outputs. There however needs to be further discussion regarding timelines, gaps and needs, and operationalization of CAHFSA’s role | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: To be built within the strategic directions paper to be developed under the project extension |  |  |  |  |  |  |
| Science and technological issues | Project based on sound science and well established technologies | Project testing approaches, methods or technologies but based on sound analysis of options and risks | Many scientific and /or technological uncertainties | x |  |  |  |  |  | PM: | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: |  |  |  |  |  |  |
| Political influences | Project decisions and choices are not particularly politically driven | Signs that some project decisions are politically motivated | Project is subject to a variety of political influences that may jeopardize project objectives | x |  |  |  |  |  | PM: | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: |  |  |  |  |  |  |
| Other, please specify. Add rows as necessary |  |  |  |  |  |  |  |  |  | PM: |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: |  |  |  |  |  |  |
|  |  |  |  | Project Manager Rating |  |  |  |  |  | Notes | Task Manager Rating |  |  |  |  |  |
| Risk Factor | Indicator of Low Risk | Indicator of Medium Risk | Indicator of High Risk | Low | Medium | Substantial | High | Not Applicable | To be determined |  | Low | Medium | Substantial | High | Not Applicable | To be determined |
| EXTERNAL RISK |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Project context |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Political stability | Political context is stable and safe | Political context is unstable but predictable and not a threat to project implementation | Very disruptive and volatile | x |  |  |  |  |  | PM: | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: |  |  |  |  |  |  |
| Environmental conditions | Project area is not affected by severe weather events or major environmental stress factors | Project area is subject to more or less predictable disasters or changes | Project area has very harsh environmental conditions | x |  |  |  |  |  | PM: |  | X |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: This could be an issue, but considered a small risk to the project given that all activities are wrapped up. |  |  |  |  |  |  |
| Social, cultural and economic factors | There are no evident social, cultural and/or economic issues that may affect project performance and results | Social or economic issues or changes pose challenges to project implementation but mitigation strategies have been developed | Project is highly sensitive to economic fluctuations, to social issues or cultural barriers | x |  |  |  |  |  | PM: | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: |  |  |  |  |  |  |
| Capacity issues | Sound technical and managerial capacity of institutions and other project partners | Weaknesses exist but have been identified and actions is taken to build the necessary capacity | Capacity is very low at all levels and partners require constant support and technical assistance | x |  |  |  |  |  | PM: |  | X |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: In Caribbean SIDS the staff complements in many agencies charged with management responsibility for biosafety matters remains relatively low and the status may not change in the mid to long term. This will have some bearing on sustainability. |  |  |  |  |  |  |
| Others, please specify. Add rows as necessary |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

If there is a significant (over 50% of risk factors) discrepancy between Project Manager and Task Manager rating, an explanation by the Task Manager should be provided below

N/A

TOP RISK MITIGATION PLAN

Rank – importance of risk Risk Statement – potential problem (condition and consequence) Action to take – action planned/taken to handle the risk Who – person(s) responsible for the action Date – date by which action needs to be or was completed

| Rank | Risk Statement |  | Action to Take | Who | Date |
| --- | --- | --- | --- | --- | --- |
|  | Condition | Consequence |  |  |  |

Project overall risk rating (Low, Medium, Substantial or High) (Please include PIR risk ratings for all prior periods, add columns as necessary):

| FY2012 rating | FY2013 rating | FY2014 rating | FY2015 rating | FY2016 rating | FY2017 rating | FY2018 rating | FY2019 rating | Comments/narrative justifying the current FY rating and any changes (positive or negative) in the rating since the previous reporting period |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| N/A | H | S | S | S | M | M | M | Project wind-down and final activities completed under this review period constitute a moderate overall risk mainly in consideration of the longer-term sustainability concerns that were beyond the scope of the project |
|  |  |  |  |  |  |  |  | If a risk mitigation plan had been presented for a previous period or as a result of the Mid-Term Review/Evaluation please report on progress or results of its implementation |
|  |  |  |  |  |  |  |  | N/A |

For joint projects and where applicable ratings should also be discussed with the Task Manager of co-implementing agency.

2 Some projects are adopting/planning to adopt milestones for tracking the achievement of outcomes. Add the corresponding milestones in this column when applicable to inform the rating. Milestones are optional and may substitute for Mid-Term Target.

3 Use GEF Secretariat required six-point scale system: Highly Satisfactory (HS), Satisfactory (S), Marginally Satisfactory (MS), Marginally Unsatisfactory (MU), Unsatisfactory (U), and Highly Unsatisfactory (HU).

4 Add rows if your objective has more than 3 outcome indicators. Same applies for the number of outcomes.

Only for Substantial to High risk.