UN Environment GEF PIR Fiscal Year 2019

- July 2018 to 30 June 2019)

| - Identification |  |  | Insert GEF ID.: 6990 | Insert Umoja no.: GFL-11207-14AC0003, S1-32GFL-000618 |  |
| --- | --- | --- | --- | --- | --- |
| Project Number + Project Title |  |  | Achieving Biodiversity Conservation through Creation, Effective Management and Spatial Designation of Protected Areas and Capacity Building |  |  |
| Duration months | Planned |  | 36 months (5 October 2016 - 5 October 2019) |  |  |
|  | Extension(s) |  | 31 December 2020 |  | 12 months |
| Division(s) Implementing the project |  |  | GEF Biodiversity and Land Degradation Unit, Ecosystems Division |  |  |
| Executing Agency(ies) |  |  | UNEP/ROE |  |  |
| Names of Other Project Partners |  |  | Ministry of Foreign Trade and Economic Relations of Bosnia and Herzegovina (MoFTER) |  |  |
|  |  |  | Ministry for Spatial Planning, Construction and Ecology of Republika Srpska (MSPCE) |  |  |
|  |  |  | Ministry of Environment and Tourism of the Federation of Bosnia and Herzegovina (MET) |  |  |
| Project Type |  |  | Medium-sized Project |  |  |
| Project Scope |  |  | National |  |  |
| Names of Beneficiary Countries |  |  | Bosnia and Herzegovina |  |  |
| Programme of Work |  |  | PoW 2018-2019 Sub-programme 3: Healthy and Productive Ecosystems |  |  |
| GEF Focal Area(s) |  |  | Biodiversity |  |  |
| UNDAF linkages |  |  | UNDAF thematic area 2 “Sustainable and equitable development and employment” |  |  |
| Link to relevant SDG target(s) and SDG indicator(s) |  |  | 2.4 – 2.4.1 15.A – 15.A.1 |  |  |
| GEF financing amount |  |  | USD 1,397,260 |  |  |
| Co-financing amount |  |  | USD 13,548,200 |  |  |
| Date of CEO Endorsement |  |  | 13 July 2016 |  |  |
| Start of Implementation |  |  | 5 October 2019 |  |  |
| Date of first disbursement |  |  | 7 September 2016 |  |  |
| Total disbursement as of 30 June |  |  | USD 1,370,260.00 |  |  |
| Total expenditure as of 30 June |  |  | USD 1,108,709.67 |  |  |
| Expected Mid-Term Date |  |  | December 2018 – May 2019 (finalized) |  |  |
| Completion Date |  | Planned | October 2019 |  |  |
|  |  | Revised | December 2020 |  |  |
| Expected Terminal Evaluation Date |  |  | December 2020 |  |  |
| Expected Financial Closure Date |  |  | June 2021 |  |  |

- OVERVIEW OF PROJECT STATUS

| UN Environment Subprogramme(s) PoW 2018-2019 Sub-programme 3: Healthy and Productive Ecosystems | Specify the relevant Expected Accomplishment(s) & Indicator(s) Expected accomplishment (EA) (a) The health and productivity of marine, freshwater and terrestrial ecosystems are institutionalized in education, monitoring and cross-sector and transboundary collaboration frameworks at the national and international levels. Indicator (i) Increase in the number of countries and transboundary collaboration frameworks that have made progress to monitor and maintain the health and productivity of marine and terrestrial ecosystems; (ii) Increase in the number of countries and transboundary collaboration frameworks that demonstrate enhanced knowledge of the value and role of ecosystem services. |
| --- | --- |
| The project Component (1) should result in an increased national protected area network (outcome 1.1), through outputs 1.1.1 (At least three new protected areas established) and 1.1.2 (At least two existing protected areas re-classified), enabling productive ecosystems and preserving nature. - Seven out of 10 valorisation study documents are finalized and awaiting approval from the cantonal/Republika Srpska governments; - Implemented advocacy meetings with the local communities (at least two for every area proposed for protection); Expected outcome of Component (2) is an improved management capacity for effectiveness of protected areas and biodiversity conservation (2.1), that should be achieved through outputs: 2.1.1 (elaborated reports of participative review of planning and management options for the PA system in BiH), 2.1.2 (developed an enhanced PA financial mechanism developed and strengthened resource mobilization capacity of the main actors in the PA system), 2.1.3 (conducted advocacy and communication of natural values and benefits of PAs to PA staff, conservation authorities and decision makers) and 2.1.4 (increased public awareness and action on nature conservation and resulting economic benefits). - Cooperation with PAs managers is ongoing for three years and planned for continuance in the final implementation year. Operational biodiversity monitoring system in Bosnia and Herzegovina, as expected outcome (3.1) of the component (3), should be achieved through outputs: 3.1.1 (biodiversity indicator framework and related legislation developed for government consideration), 3.1.2 (established information platform for biodiversity monitoring in BiH), and 3.1.3 (established a main biodiversity monitoring tool, based on the existing Red Lists in BiH). - Held preparatory training (in cooperation with IUCN) for the Red Lists assessors; - Drafted and adopted list of indicators for biodiversity for country reporting towards MEAs; - Red Lists assessor training (4-day) planned for the second half of 2019. |  |

For all GEF 6 and later projects:

| GEF Core Indicators 1.1 Terrestrial protected areas newly created (hectares) | Indicative expected Results Project envisages for protection of 10 new areas, in total of approximately 125,000ha (for two areas coverage for protection needs to be agreed by local communities). |
| --- | --- |
| 1.2 Terrestrial protected areas under improved management effectiveness (hectares) | Improved management effectiveness of two areas 907 ha (cave Orlovača and habitat Gromiželj) The project shall measure management effectiveness through METT scoring. At the CEO endorsement METT score was 13, end target is 30. |
| 4.1: Area of landscapes under improved management to benefit biodiversity (hectares, qualitative assessment, non-certified) | Under the project’s third component a biodiversity indicator framework and related legislation were developed and adopted, and an information platform for biodiversity monitoring in BiH is to be established, through which landscape management can be improved and monitored. Indirect benefit to area of landscapes under improved management to benefit biodiversity: app. 50,000ha |

| Planned linkages with UNDAF | The project goals are well aligned with the results matrix of the One UN Programme, since it provides a strong reference to environmental strategies for biodiversity and highlights the need to better integrate environmental efforts on different governance levels in the country and improve MEA reporting and implementation. The project will namely contribute to the UNDAF Focus Area 2 “Sustainable and equitable development and employment” and associated Outcome 5: “By 2019, legal and strategic frameworks enhanced and operationalized to ensure sustainable management of natural, cultural and energy sources.” |
| --- | --- |

| Planned contribution to relevant SDG target(s) and SDG indicator(s) | The project framework to improve environmental strategies for biodiversity through sustainable land use practices relates to SDG target 2.4 and the associated indictors. SDG 2.4 ensures sustainable food productions systems and implementation of resilient agricultural practices; sustainable land management will contribute to SDG 2.4 by improved productivity and addressing issues of declining soil fertility and mismanagement of nutrient resources. The overall objective of the project is to promote biodiversity conservation through expanding the national protected areas coverage by doubling its current size and supporting national capacities for effective management of biodiversity through creation of a good policy and capacity environment, and enhancement of conservation planning, management and biodiversity monitoring while actively involving local stakeholders and vulnerable groups throughout the process. These efforts relate strongly with SDG 15.A, mobilize and significantly increase financial resources from all sources to conserve and sustainably use biodiversity and ecosystems. The project envisages for protection of important sites for terrestrial and mountain areas (9 areas proposed under the project) and freshwater biodiversity (one coastal area in Neum Municipality), vital for ensuring long-term and sustainable use of terrestrial and freshwater natural resources in the country. Under the second component, the project envisages for improved management capacity for effectiveness of protected areas and biodiversity conservation, including development of programme for conservation professionals, resource mobilization, advocacy and communications of nature values. The most fundamental and irreversible human impact on nature is species extinction. Within the third component the project shall develop set of recommendations and an action plan for revision of the current Red List Index in the country and enhance capacities of potential Red List Index assessors through cooperation with the IUCN experts. The project will cooperate with GIZ for establishment of an informational platform/system that will include different modules for data input, such as invasive species, protected areas, degraded land, etc., aimed at halting biodiversity loss and enabled and improved monitoring of biodiversity, ecosystem services and nature conservation. |
| --- | --- |

| Implementation Status | FY 2017 | FY 2018 | FY 2019 | FY 2020 |  |
| --- | --- | --- | --- | --- | --- |
|  | 1st PIR | 2nd PIR | 3rd PIR |  |  |

| Development Objective Rating FY | FY 2017 | FY 2018 | FY 2019 | FY 2020 | FY 20__ |
| --- | --- | --- | --- | --- | --- |
|  | S | S | S |  |  |
| Implementation of the project is on track and it is expected that all results will be achieved in line with the project plan. There are delays in adoption of the valorisation studies by the relevant governments, however the project team is working on overcoming this issue. In line with outcome 1 indicator – at least three new PAs and about 150,000 ha protected - valorization documentation for 7 areas proposed for designation has been finalized: - Mountain Zvijezda,(6222,55 ha) - Livanjsko carst field, (45080ha) - Vjetrenica cave (4713ha) - Mediterannetum botanical reserve (coastal area(1432ha); - Mountain Orjen (16800ha); - Cave Govještica (3500) - Tišina natural habitat (200ha); already designated as protected Outcome 2 indicator targets a METT score of 20 at mid-term, which was achieved by the project for the designated areas Cave Vjetrenica, Mountain Orjen, Livanjsko polje carst field, and the habitat Tišina. Under Outcome 3 the project developed biodiversity indicators and a monitoring system for these is in place, but not yet fully public. |  |  |  |  |  |

| Implementation Progress Rating | FY 2017 | FY 2018 | FY 2019 | FY 2020 | FY 20__ |
| --- | --- | --- | --- | --- | --- |
|  | S | S | S |  |  |
| Some activities are behind the schedule, but the overall implementation of the project is on track For Output 1, seven out of 10 valorization studies are being validated, and a set of training and advocacy workshops was held for the PAs to be established. Documentation for the 3 new PAs is being prepared as foreseen (output 2). Reports for additional livelihood opportunities in and around the new PAs were developed (output 3), as well as an analysis on the financial mechanisms to sustain the PAs, incl. tourism options (output 4). However, as overall knowledge on PAs is low, buy-in with local communities is slower than anticipated, despite the outreach and engagement activities being on track (outputs 5 and 6). A biodiversity indicator framework and related legislation was developed for government consideration (output 7), and a monitoring system is about to be established (output 8), but not yet fully agreed upon and shared between the state entities in Bosnia and Herzegovina. Ongoing collaboration with the IUCN Regional Office for Eastern Europe and Central Asia delivered a Red List guidance report including an overview of the current national Red Lists in Bosnia and Herzegovina and recommendations that can serve to guide future national Red List development will be developed in cooperation with IUCN. |  |  |  |  |  |

| Risk Rating | FY 2017 | FY 2018 | FY 2019 | FY 2020 | FY 20__ |
| --- | --- | --- | --- | --- | --- |
|  | L | L | L |  |  |
| Valorisation documentation for designation of protected areas has been finalized for 7 areas, however, advocacy meetings and additional consultations have to be conducted by the project team. While slow government processes and coordination issues between the two state entities in Bosnia Herzegovina impact on timely delivery, the project has established relations with both entities and is able to catalyse between the two. |  |  |  |  |  |

| Stakeholder engagement | The proposal takes into account roles, responsibilities, and needs of various key ministries, institutions, and agencies in Bosnia and Herzegovina. Ministry of Foreign Trade and Economic Relations of Bosnia and Herzegovina (MoFTER); Ministry for Spatial Planning, Construction and Ecology of Republika Srpska, Ministry of Spatial Planning of the Federation of Bosnia and Herzegovina and Ministry of Environment and Tourism of the Federation of Bosnia and Herzegovina are the main stakeholders from the Government guiding the project implementation. Stakeholder participation and consultation processes are strong and successful in creating broad ownership in the creation of PAs, also at local levels. Frequent communication and meetings with the project stakeholders and decision makers was also used as a mitigation measure against the complex political structure of the country, and relevant national and local CSOs such as the Centre for Environment from Banja Luka, Nase Ptice (Our birds) and Zeleni Neretva (Green Neretva River) were encouraged to take an active role in designing and implementing project activities, notably in the involvement of the local communities in PAs. |
| --- | --- |

| Gender mainstreaming | Gender relations between women and men play a key role in the access to environmental resources, control of the resources, and the goods and services they provide. In Bosnia and Herzegovina, although women represent an important factor for revival of rural areas and their development, they are at disadvantageous position. Women in rural areas in BiH are often viewed as a passive segment of the population, or as ‘helping’ members of the family, rather than as active participants in the fields of agriculture, rural tourism, and rural development. Very few women own land, and, as such, rarely participate in decision-making about rural development and the diversification of rural activities as a source of income. The identification and prioritization for the creation of PAs took gender considerations and socio-economic factors into account so as to validate benefits and improve livelihoods for vulnerable groups as much as possible. The MTR judged that although it is not particularly emphasized by separate activities, the project takes into account human rights and gender equality. First of all, the rights of local communities are emphasized. The project treats the voice of members of both sexes in a completely equal manner. The project is more concerned with the issue of distrust in the younger generation than the issue of full equality. |
| --- | --- |

| Knowledge activities and products | The project developed and actively uses a knowledge management system to ensure the effective collation and dissemination of experiences and information gained in the course of the project’s implementation, to ensure that information and data formats and flows are directed at the most relevant stakeholder groups to support decision-making processes. |
| --- | --- |

| Stories to be shared | The project team supported a successful marking of the World Environment Day 2018 (in BiH), aimed at plastic pollution and used as an opportunity to raise awareness on the importance of combating the plastic pollution, especially in protected areas, and to promote nature and richness of natural values in BiH, and engaging collective efforts towards conservation and sustainability. The project team started the ongoing Protected areas managers day in Bosnia and Herzegovina practice for a third year in a row. Protected areas managers day is a conference + training, a well-established practice, aimed for PA managers in BiH, done every year in cooperation with conservation professionals in BiH. The initiative, started under the auspices of the project is primarily aimed at improving the communication and cooperation of the protected areas managers to address the most common issues they are faced with. |
| --- | --- |

- RATING PROJECT PERFORMANCE AND RISK

Based on inputs by the Project Manager, the UNEP Task Manager will make an overall assessment and provide ratings of:

- Progress towards achieving the project Results(s)- see section 3.1

- Implementation progress – see section 3.2

Section 3.3 on Risk should be first completed by the Project Manager. The UNEP Task Manager will subsequently enter his/her own ratings in the appropriate column.

  - 3.1	Rating of progress towards achieving the project Results(s)

| Project objective and Outcomes | Indicator | Baseline level | Mid-Term Target or Milestones | End of Project Target | Observations/ justification on rating | Progress rating |
| --- | --- | --- | --- | --- | --- | --- |
| Objective Spatial protection of the key biodiversity areas in Bosnia and Herzegovina (BiH) and conservation of the unique nature of the country to best safeguard the wellbeing of its communities. | 1. Number and ha of new protected areas | Insufficient territory of BiH protected (PA network consists of 24 PAs with total of 136,700 ha or 2.7% BiH), protected area network weak and disconnected Underdeveloped management capacities for planning and manage the PAs (no management plans, no financing plans, outdated management plans, no strategy for addressing threats, skills and training are insufficient and |  | National protected area network will increase to 27 PAs and ca 250,000 ha (doubled to 5% of national territory) Improved planning and management options that could be tracked and monitored by management effectiveness tracking tools | National decision makers and local communities have been somewhat responsive and affirmative to designation of new protected areas and the conservation values, and the project is constantly working on improvement. Existing policy and planning documents accessible for analysis and adjustment | S |
|  | 2. Increased score in the Capacity Development Scorecard for GEF Projects | Underdeveloped management capacities for planning and manage the PAs (no management plans, no financing plans, outdated management plans, no strategy for addressing threats, skills and training are insufficient and there is a great need for further training and education) |  | Financial modalities for supporting the PA network in the country developed and submitted for adoption | Analysis of financial mechanisms has been drafted by the project. The next step is for legal/economic expert to suggest financial modalities that will support the PA network. | S |
|  | 3. Number of communities whose understanding of conservation benefits is significantly increased | Large number of communities with limited awareness on benefits of nature conservation in local communities |  | Outreach campaign for communication on nature conservation and its economic benefits developed and conducted for at least 15 communities | Understanding of local communities on nature protection and protected areas is increased but still low. | MS |
| Outcome 1: Increased national protected area system | 1. Increase in number and size of the PA system including at least three new protected areas established | 24 PAs 135,700 ha | PA network of BiH consists of 25 PAs with total of 181,700 ha | National protected area network will increase to 27 PAs with total of 250,000 ha | Valorization documentation for 7 areas proposed for designation has been finalized: - Mountain Zvijezda,(6222,55 ha) - Livanjsko carst field, (45080ha) - Vjetrenica cave (4713ha) - Mediterannetum bothanical reserve (coastal area(1432ha); - Tišina natural habitat (200ha); - Mountain Orjen (16800ha); - Cave Govještica (3500) - Habitat Tišina is designated as protected. | S |
| Outcome 2: Improved management capacity for effectiveness of protected area system and biodiversity conservation | 1. Management Effectiveness Tracking Tool (METT) Score improved (See Annex 10 Section II) increases by 17 points | METT Score: 13 | 20 | 30 | Achieved Mid-Term METT score for most of areas: Cave Vjetrenica, Mountain Orjen, Livanjsko polje carst field, habitat Tišina | S |
| Outcome 3: Operational biodiversity monitoring system in Bosnia and Herzegovina | 1. Biodiversity monitoring system functional and operational for conservation authorities and PA staff | Disconnected, fragmented and scarce biodiversity data | Develop a framework for a viable biodiversity monitoring system in the country | (The system is official and widely used for official biodiversity monitoring) | The project has developed biodiversity indicators and is partnering with GIZ ORF for development biodiversity modules for informational system. | S |
|  | 2. Number of users of the Biodiversity Monitoring System from the PA system | 0 (No viable monitoring system in place) | 100 |  | Biodiversity monitoring system is in place. However, it is in official use by the Fund for Environmental Protection of the Federation of BiH and Institute for Protection of Natural Heritage of Republika Srpska. It shall be widely used once the modules are prepared and system is ready for data input. Project has established cooperation with GIZ for achievement of this outcome. | S |

Overall rating of project progress towards meeting project Result(s) (To be provided by UNEP GEF Task Manager.)

| FY2018 rating [previous] | FY2019 rating [current] | Justification of the current FY rating and explanation of reasons for change (positive or negative) since previous reporting periods. |
| --- | --- | --- |
| S | S | The overall implementation and achievement of expected results is on track. Some results are delayed due to lengthy advocacy procedures with the governments, but the project team is actively engaged to addressing these obstacles. In line with outcome 1 indicator – at least three new PAs and about 150,000 ha protected - valorization documentation for 7 areas proposed for designation has been finalized: - Mountain Zvijezda,(6222,55 ha) - Livanjsko carst field, (45080ha) - Vjetrenica cave (4713ha) - Mediterannetum botanical reserve (coastal area(1432ha); - Mountain Orjen (16800ha); - Cave Govještica (3500) - Tišina natural habitat (200ha); already designated as protected Outcome 2 indicator targets a METT score of 20 at mid-term, which was achieved by the project for the designated areas Cave Vjetrenica, Mountain Orjen, Livanjsko polje carst field, and the habitat Tišina. Under Outcome 3 the project developed biodiversity indicators and a monitoring system for these is in place, but not yet fully public. |

Risks to the delivery of results

The second column should be completed by the Project Manager and the third column should summarize the recommendations that the Project Manager and Task Manager have agreed upon to address the problem/risk.  Projects should complete only the relevant sections and are free to add/delete problems/risks.  This section should inform the risk rating in section 3.3.

| Problems/risks identified | Description of the problem/risk | Agreed recommended actions |
| --- | --- | --- |
| on achieving targets | Some delays experienced due to the long adoption procedures in the country and complex administrative structure. | Project team is organizing frequent meetings with the project stakeholders in this regard |

3.2	Rating of progress implementation towards delivery of outputs

| Outputs | Expected delivery date | Implement-ation status as of 30 June 2018 | Implement-ation status as of 30 June 2019) | Progress rating justification | Progress rating |
| --- | --- | --- | --- | --- | --- |
| Output 1: At least three new protected areas established (Livanjsko Polje wetlands – ca. 45,000 ha, Mt. Bjelašnica – Mt. Igman – the Rakitnica River Canyon – ca. 50,000 ha, Mt. Orjen – Mt. Bijela Gora – ca. 16,000 ha) |  |  |  |  |  |
| Activity 1: Rapid assessment of identified areas selected for spatial protection with key national stakeholders | Oct 2017 | 100% | 100% | Assessment finalized. | S |
| Activity 2: Conduct workshops with relevant stakeholders (consultations on different levels on defining territory/area coverage and location of proposed protected area, benefits of protection and zonation approach, taking into consideration gender equality, socially vulnerable groups) | 1 – Nov, Dec, Jan 2016 2 – May, Jun, Jul 2017 3 – Nov, Dec, Jan 2017/18 4 – May, Jun, Jul, 2018 | 100% | 100% | Held and finalized 20+ bilateral meetings with relevant stakeholders, held two stakeholder high level meetings and PA managers days. Ongoing consultations/collaboration with the relevant stakeholders as per the project needs. | S |
| Activity 3: Prepare valorisation studies for selected sites proposed for protection according to the requirements of national legislation, taking into consideration gender equality, representation of local community and ethnic and religious minorities, based on existing documentation and new data collected through field research | Feb 2017 – Apr 2018 | 40% Preparation of documentation finished | 85% | Seven studies are finalized (awaiting approval process), three need to be drafted. Finished spring/summer field researches for all areas proposed for protection. | S |
| Activity 4: Conduct series of advocacy meetings with local communities regarding planning and management options of the newly proposed protected areas, taking local livelihoods, gender equality and vulnerable groups into consideration | 1st series – Feb, Mar, Apr, 2017 2 - Aug, Sep, Oct 2017 3 - Feb, Mar, Apr 2018 4 - Aug, Sep, Oct 2018 | 100% | 100% | Several advocacy meetings held for all areas proposed for protection. Established good communication. Partaking in several workshops for karst fields, biodiversity preservation and PAs. Ongoing activity, as per the project needs. | S |
| Activity 5: Preparation of all necessary documentation required for submission for approval/adoption by the Government to designate three new protected areas and follow-up advocacy activities for final establishment of PAs | May 2018-Jan 2019 | 25% | 70% | Preparation is on track. | S |
| Output 2: At least two existing protected areas re-classified (Cave System “Vjetrenica” and Botanical Reserve “Mediteranetum”) |  |  |  |  |  |
| Activity 6: Conduct analysis on the current legal status of the Vjetrenica Cave and the Botanical Reserve and existing valorization documents | Aug 2016-Apr 2017 | 100% | 100% | Analysis conducted. Road map for establishment of legal protection of Vjetrenica and Mediteranetum areas finalized | S |
| Activity 7: Propose a road map for obtaining the updated legal status of the PAs, including their territorial expansion, and inclusion in the national PA system | Feb 2018 – Jul 2018 | 90% | 100% | Analysis conducted. Road map for establishment of the legal protection of Vjetrenica and Mediteranetum areas finalized. | S |
| Output 3: Reports of participative review of planning and management options for the PA system in BiH elaborated |  |  |  |  |  |
| Activity 8: Desk analysis of institutional and legal framework of biodiversity/natural resources management, gap analysis and development of a roadmap and recommendations, followed with wide national consultations, taking local livelihoods, gender equality and vulnerable ethnic and religious groups into consideration. | Feb 2017-Jan 2018 | 30% | 50% | Ongoing collaboration with respective ministries and core stakeholder groups | MS |
| Activity 9: Research and promotion of management and governance options for the national/entity PA system including sustainable local livelihoods incentives. | Nov 2017-Aug 2018 | 30% | 50% | Developed documents: Analysis of financial mechanisms for PAs (entire country); Analysis of legal framework for PAs financing (FBiH + region); Program of tourism development. | MS |
| Activity 10: Development of new documents, methodology and guidelines for improved planning and management options for the PA system, prepared for Government adoption | May 2018 – Apr 2019 | 20% | 40% | Developed Program of tourism development. Analysis of financial mechanisms prepared for both entities as a base for compiling guidelines for improved planning and management options. Overview of PAs management conducted with all 35 PA managers via questionnaires (overview will be further used for development of guidelines and methodology for improved planning). | S |
| Output 4: An enhanced PA financial mechanism developed and resource mobilization capacity of the main actors in the PA system is strengthened |  |  |  |  |  |
| Activity 11: Preparation and development of sustainable financing programmes for the PA network of both entities in the country proposed, including active involvement of the entity environment funds (including sustainable funding opportunities and utilizing new PA financing mechanisms, such as Payment for Ecosystem Services) | Feb 2018 – Jan 2019 | 40% | 50% | Developed documents: Analysis of financial mechanisms for PAs (FBiH + region); Analysis of legal framework for PA financing (FBiH + region); Ongoing stakeholder meetings. | S |
| Activity 12: Development of the socio-economic evaluation of area surrounding Igman and Bjelašnica | Aug 2018 – Apr 2019 | 0 | 20 | One of the recommendations of the last Project Steering Committee meeting was to exclude Economic evaluation study that uses TEEB methodology. Rather, the project shall draft the socio-economic evaluation of area surrounding Igman and Bjelašnica which can be used as a communication tool with the local communities. The activity was not on track until May 2019 when area coverage was agreed by the local communities. Development of the document is in progress. | MS |
| Output 5: Advocacy and communication of natural values and benefits of PAs to PA staff, conservation authorities and decision makers is conducted |  |  |  |  |  |
| Activity 13: Develop and conduct training programmes to PA staff related to sustainable protected area planning and management; financing and development opportunities, practical nature protection, sustainable use of non-timber forest products, etc., including gender balance and inclusion of vulnerable groups and ethnic and religious minorities. | Nov 2016 – Aug 2018 | 70% Meeting in Livno | 80% | Ongoing stakeholder meetings. Held protected areas managers day (in 2017, 2018 and one expected for 2019) whereas financing opportunities were presented to protected areas managers; shown best management practices from the region. Questionnaire based research conducted with all protected areas managers. | S |
| Activity 14: High-level decision makers and donors meeting and several national public meetings on promotion of natural values of BiH, advocacy and awareness raising on necessity for its sustainable management and adequate protection | Feb, Mar, Apr 2017 Feb, Mar, Apr 2018 Feb, Mar, Apr 2019 | 100% | 100% | Held stakeholder meetings. WED 2017, 2018 activities. Two high level meetings (one in 2017, one in 2018). | S |
| Output 6: Public awareness and action on nature conservation and resulting economic benefits is increased |  |  |  |  |  |
| Activity 15: Innovative promotion of different aspects of nature protection to local communities around the country, and especially to those living in or near the newly proposed protected areas (radio and TV engagement, showcasing best regional practices…) | May 2017- Oct 2018 | 60% | 70% | WED events 2018 with showcased regional practices. Developed Program of tourism development. Organized study visits in three areas proposed for protection. | S |
| Activity 16: Develop high quality, visually attractive and informative communication materials (publications, short film, guides etc.) to promote unique natural values of Bosnia and Herzegovina, focusing on economic opportunities such as tourism and sustainability of protected areas, to be distributed to different stakeholder groups around the country | Feb 2017 – Jan 2019 | 40% | 50% | Promotional materials developed for stakeholder meetings in 2018. Developed program of tourism for ministries Developed document Overview of PAs values and benefits for local community in terms of area development | MS |
| Output 7: Biodiversity indicator framework and related legislation developed for government consideration |  |  |  |  |  |
| Activity 17: Develop database of biodiversity indicators to monitor on regular basis and establishment of a web-based platform for reporting | May 2017 – Jul 2017 | 100% | 100% | Developed biodiversity indicators. Awaiting adoption from the BiH Government. | S |
| Activity 18: Develop and institutional guidelines for establishing a viable biodiversity monitoring system | Nov 2017 – Apr 2018 | 20% | 50% | Indicator framework developed. | MS |
| Activity 19: Summary of results and dissemination through national stakeholder meetings and trainings on the use of indicators | Jul 2018 – Oct 2019 | 30% | 50% | Ongoing stakeholder meetings. | S |
| Output 8: An information platform for biodiversity monitoring in BiH is established |  |  |  |  |  |
| Activity 20: National consultations on introduction of biodiversity monitoring and identification of needs | N/A | 50% | 60% | Approved biodiversity indicators from the entity governments | S |
| Activity 21: Provide facilitation of the internal communication between conservation authorities through a web-based platform | N/A | 30% | 40% | PA managers day held two times as a base for further development of an information platform | MS |
| Activity 22: Enhancement of the existing CHM portal for BiH to offer a wider range of functionality to end-users | N/A | 30% | 40% | Held several stakeholder meetings | MS |
| Activity 23: Results validation meeting and testing of the platform | N/A | / | / | / | N/A |
| Output 9: A main biodiversity monitoring tool established based on the existing Red Lists in BiH |  |  |  |  |  |
| Activity 24: National consultation – presentation of criteria and most prioritized groups for development of a national red list, taking gender equality and vulnerable ethnic and religious groups into consideration. | Feb 2017 – Jul 2017 | 20% | 30% | Half day training on the Red List Index for BiH stakeholders took place on 29th November 2018/ Collaboration with the IUCN Regional Office for Eastern Europe and Central Asia (ECARO) and GIZ ongoing | MS |
| Activity 25: Development of a set of recommendations and an action plan for revision of the current Red List Index(es) | Aug 2017 – Apr 2018 | 20% | 60% | Ongoing collaboration with the IUCN Regional Office for Eastern Europe and Central Asia/ National Red List guidance report including an overview of the current national Red Lists in Bosnia and Herzegovina and recommendations that can serve to guide future national Red List development will be developed in cooperation with IUCN ECARO | S |
| Activity 26: Documented summary of results and dissemination through national stakeholder meetings. | Jul 2018- Jan 2019- Jul 2019- | 20% | 30% | Ongoing collaboration with the IUCN ECARO | MS |

Overall project implementation progress  (To be completed by UNEP GEF Task Manager.):

| FY2018 rating [previous] | FY2019 rating [current] | Justification of the current rating and explanation of reasons for change (positive or negative) since previous reporting periods. |
| --- | --- | --- |
| S | S | Some activities are behind schedule, mostly due to specific challenges in the overall governance structure inherent to Bosnia and Herzegovina with different government entities. Nevertheless, the project is overall on track with its deliverables and good progress, e.g. with the adoption of valorisation studies indicate that the project will be able to make good on some of the current delays. For Output 1, seven out of 10 valorization studies are being validated, and a set of training and advocacy workshops was held for the PAs to be established. Documentation for the 3 new PAs is being prepared as foreseen (output 2). Reports for additional livelihood opportunities in and around the new PAs were developed (output 3), as well as an analysis on the financial mechanisms to sustain the PAs, incl. tourism options (output 4). However, as overall knowledge on PAs is low, buy-in with local communities is slower than anticipated, despite the outreach and engagement activities being on track (outputs 5 and 6). A biodiversity indicator framework and related legislation was developed for government consideration (output 7), and a monitoring system is about to be established (output 8), but not yet fully agreed upon and shared between the state entities in Bosnia and Herzegovina. Ongoing collaboration with the IUCN Regional Office for Eastern Europe and Central Asia delivered a Red List guidance report including an overview of the current national Red Lists in Bosnia and Herzegovina and recommendations that can serve to guide future national Red List development will be developed in cooperation with IUCN. |

Risks in implementation

This section should be completed by the Project Manager and summarize implementation risks (e.g. procurement delays, reputational risks etc).

The first column should be completed by the Project Manager and the second column should summarize the recommendations that the Project Manager and Task Manager have agreed upon to address the problem/risk.  This section should inform the risk rating in section 3.3.

| Problems/risks identified | Agreed recommended actions | By whom | When |
| --- | --- | --- | --- |

3.3. Risk Rating

| Risk | Mitigation at CEO approval | Mitigation at implementation | Rank |
| --- | --- | --- | --- |
| Governance challenges: The complex political structures in Bosnia and Herzegovina’s Entities and the division of roles and responsibilities for the environment into various ministries and agencies can cause coordination challenges to the project. . | This risk will be mitigated through close collaboration with relevant stakeholders from the outset and by determining collaborative strategies and focal points in each of the key institutions; and equally through the improvement of institutional frameworks for biodiversity management, and the coordination and clarification of mandates. The project will track political support for nature conservation efforts and periodically issue policy briefs on the topic to also emphasize the importance of the intervention to the EU accession process which the country is fully committed to. | Mitigation of the risk at the implementation level is following mitigation strategy at the CEO endorsement. Collaboration with relevant stakeholders in ongoing and well developed. Through PA managers day, the project is improving collaboration of governments representatives and PA mangers and assisting in overcoming long-lasting issues. The project team did an overview of PAs benefits and values (document) and send it to the ministry. The document can be widely used and is aimed at emphasizing the importance of the topic (protected areas and biodiversity protection) for (different level) government officials. | CEO: M |
|  |  |  | TM: M |
|  |  |  | PM: M |
| Climate change as a direct driver of biodiversity loss in Bosnia and Herzegovina: The country is severely affected by climate change and is one of the most vulnerable to the consequences of climate change in Europe. Recent devastated floods that hit Bosnia and Herzegovina in May 2014 and numerous wildfires that hit pristine natural areas of the country in previous years call for urgent implementation of adaptation measures. | Climate change vulnerability will be an integral part of the capacity building activities of this project and awareness raising will be given a full priority. The project will focus on assessing the biodiversity loss related to climate change and incorporating adaptation measures into the PAs management plans. | Mitigation strategy at the implementation level follows the strategy.at the CEO level. Climate change vulnerability is part of awareness raising and communication activities with the local communities. Risk rated as high: Due to the climate change effects to biodiversity loss and unpredictable events it causes, rated risk is at appropriate level. | CEO: H |
|  |  |  | TM: H |
|  |  |  | PM: H |
| Communication among stakeholders: May cause a problem in the data distribution, poor communication across different stakeholder groups, which could ultimately affect the promptness of the project activities | The risk will be mitigated by ensuring proper and inclusive communications channels throughout the project implementation and developing a communication strategy in the project inception phase. | Mitigation strategy includes frequent and well-developed communication with stakeholders and data providers. Risk rated as Medium: appropriate level for this reporting period. We do envisage Low risk for the next reporting period. | CEO: M |
|  |  |  | TM: M-L |
|  |  |  | PM: M-L |
| Gap in conservation capacity development: There is an apparent gap in conservation capacity development and financing projects in Bosnia and Herzegovina. | Apart from GEF-funded national reporting projects and processes process, mostly implemented with support of UNEP, very few other internationally funded projects have tackled the issue of biodiversity management and nature conservation in the country so far. The gap in conservation capacity development is taken into account by the project implementation strategy through development of the guidelines on improved planning and management options and related capacity development options such as research and promotion of management and governance (Component 2 of the project). | Mitigation strategy at the implementation level follows the strategy.at the CEO level Risk rated as Medium: appropriate level, still low number of biodiversity project within the country. | CEO: M |
|  |  |  | TM: M |
|  |  |  | PM: M |
| Overall Risk Rating Project Manager |  |  | M-L |
| Overall Risk Rating Task Manager |  |  | M-L |

| FY2018 rating [previous] | FY2019 rating [current] | Justification of the current risk rating and explanation of reasons for change (positive or negative) since previous reporting periods. |
| --- | --- | --- |
| L | L | The project has experienced some delays in implementation and designation of new protected areas due to the complex and long procedures for protection and readiness of the governments of the Bosnia and Herzegovina entities. The project team has ongoing advocacy meetings aimed at addressing these issues. |

High Risk (H): There is a probability of greater than 75% that assumptions may fail to hold or materialize, and/or the project may face high risks. 
Substantial Risk (S): There is a probability of between 51% and 75% that assumptions may fail to hold and/or the project may face substantial risks. 
Modest Risk (M): There is a probability of between 26% and 50% that assumptions may fail to hold or materialize, and/or the project may face only modest risks. 
Low Risk (L): There is a probability of up to 25% that assumptions may fail to hold or materialize, and/or the project may face only modest risks.

Annexes and/or Links:

- Project Steering Committee Minutes of the year reported

- Risk Factor Table form previous template

Risks Factor Table

There are two tables to assess and address risk: the first “risk factor table” to describe and rate risk factors; the second “top risk mitigation plan” should indicate what measures/action will be taken with respect to risks rated Substantial or High and who is responsible to for it.

High Risk (H): There is a probability of greater than 75% that assumptions may fail to hold or materialize, and/or the project may face high risks. 
Substantial Risk (S): There is a probability of between 51% and 75% that assumptions may fail to hold and/or the project may face substantial risks. 
Modest Risk (M): There is a probability of between 26% and 50% that assumptions may fail to hold or materialize, and/or the project may face only modest risks. 
Low Risk (L): There is a probability of up to 25% that assumptions may fail to hold or materialize, and/or the project may face only modest risks.

RISK FACTOR TABLE

Project Managers will use this table to summarize risks identified in the Project Document and reflect also any new risks identified in the course of project implementation. The Notes column should be used to provide additional details concerning manifestation of the risk in your specific project, as relevant. The “Notes” column has one section for the Project Manager (PM) and one for the UNEP Task Manager (TM). If the generic risk factors and indicators in the table are not relevant to the project rows should be added. The UNEP Task Manager should provide ratings in the right hand column reflecting his/her own assessment of project risks.

|  |  |  |  | Project Manager Rating |  |  |  |  |  | Notes | Task Manager Rating |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Risk Factor | Indicator of Low Risk | Indicator of Medium Risk | Indicator of High Risk | Low | Medium | Substantial | High | Not Applicable | To be determined |  | Low | Medium | Substantial | High | Not Applicable | To be determined |
| INTERNAL RISK |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Project management |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Management structure [Roles and responsibilities] | Stable with roles and responsibilities clearly defined and understood | Individuals understand their own role but are unsure of responsibilities of others | Unclear responsibilities or overlapping functions which lead to management problems | x |  |  |  |  |  | PM: Well-defined, clearly defined and understood roles and responsibilities | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: Well-defined and understood PM structure |  |  |  |  |  |  |
| Governance structure [oversight] | Steering Committee and/or other project bodies meet periodically and provide effective direction/inputs | Body(ies) meets periodically but guidance/input provided to project is inadequate. TOR unclear | Members lack commitment Committee/body does not fulfil its TOR |  | x |  |  |  |  | PM: SC meets periodically but there are challenges when it comes to providing guidance to the project and resolving complexities. |  | X |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: Challenges to the SC and its overarching functions for project guidance persist and occasionally delay decisions, due to the complex political system in BiH |  |  |  |  |  |  |
| Internal communications | Fluid and cordial | Communication process deficient although relationships between team members are good | Lack of adequate communication between team members leading to deterioration of relationships and resentment | x |  |  |  |  |  | PM: Internal communication is well developed and fluent. | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: |  |  |  |  |  |  |
| Work flow Budget | Project progressing according to work plan | Some changes in project work plan but without major effect on overall timetable | Major delays or changes in work plan or method of implementation |  |  | x |  |  |  | PM: There have been both delays and challenges with implementation of the project activities due to the lack of readiness and understanding of local communities and challenges with SC guidance. |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: agree |  |  |  |  |  |  |
| Co-financing | Co-financing is secured and payments are received on time | Is secured but payments are slow and bureaucratic | A substantial part of pledged co-financing may not materialize | x |  |  |  |  |  | PM: Co-financing is secured. | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: |  |  |  |  |  |  |
| Budget | Activities are progressing within planned budget | Minor budget reallocation needed | Reallocation between budget lines exceeding 30% of original budget |  | x |  |  |  |  | PM: Experienced delays in budget allocation (to the Institute of RS) that caused delays in implementation of the project activities. |  | X |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: agree |  |  |  |  |  |  |
| Financial management | Funds are correctly managed and transparently accounted for | Financial reporting slow or deficient | Serious financial reporting problems or indication of mismanagement of funds |  | x |  |  |  |  | PM: Slow financial reporting, but improved since the last reporting period. |  | X |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: Financial management improved from previous reporting periods; minor challenges persist |  |  |  |  |  |  |
| Reporting | Substantive reports are presented in a timely manner and are complete and accurate with a good analysis of project progress and implementation issues | Reports are complete and accurate but often delayed or lack critical analysis of progress and implementation issues | Serious concerns about quality and timeliness of project reporting | x |  |  |  |  |  | PM: Substantive reports are complete and accurate and mostly submitted on time. | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: Reports are comprehensive, substantive and mostly in time |  |  |  |  |  |  |
| Stakeholder engagement | Stakeholder analysis done and positive feedback from critical stakeholders and partners | Consultation and participation process seems strong but misses some groups or relevant partners | Symptoms of conflict with critical stakeholders or evidence of apathy and lack of interest from partners or other stakeholders |  | x |  |  |  |  | PM: Consultation and participation process is strong, stakeholders' engagement is established with minor obstacles from time to time. |  | X |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: Overall strong stakeholder engagement, occasionally different interests affect implementation |  |  |  |  |  |  |
| External communications | Evidence that stakeholders, practitioners and/or the general public understand project and are regularly updated on progress | Communications efforts are taking place but not yet evidence that message is successfully transmitted | Project existence is not known beyond implementation partners or misunderstandings concerning objectives and activities evident |  | x |  |  |  |  | PM: Project has evidenced poor understanding |  | X |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: |  |  |  |  |  |  |
| Short term/long term balance | Project is addressing short term needs and achieving results with a long term perspective, particularly sustainability and replicability | Project is interested in the short term with little understanding of or interest in the long term | Longer term issues are deliberately ignored or neglected |  | x |  |  |  |  | PM: Project is addressing short term needs and achieving results with a long term perspective, however, there is little understanding of interest in the long term. i.e. organization of PA managers day as a long-term practice |  | X |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: Some challenges exist re. ownership of project activities and achievements |  |  |  |  |  |  |
| Science and technological issues | Project based on sound science and well established technologies | Project testing approaches, methods or technologies but based on sound analysis of options and risks | Many scientific and /or technological uncertainties | x |  |  |  |  |  | PM: Project based on sound science and well-established technologies | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: |  |  |  |  |  |  |
| Political influences | Project decisions and choices are not particularly politically driven | Signs that some project decisions are politically motivated | Project is subject to a variety of political influences that may jeopardize project objectives |  |  | x |  |  |  | PM: There are signs that some project decisions are politically motivated – mostly obvious for adoption of legal act for designation of an area as protected and sustainable financial mechanism for PA management improvement. |  | X |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: agree |  |  |  |  |  |  |
| Other, please specify. Add rows as necessary |  |  |  |  |  |  |  |  |  | PM: |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: |  |  |  |  |  |  |

|  |  |  |  | Project Manager Rating |  |  |  |  |  | Notes | Task Manager Rating |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Risk Factor | Indicator of Low Risk | Indicator of Medium Risk | Indicator of High Risk | Low | Medium | Substantial | High | Not Applicable | To be determined |  | Low | Medium | Substantial | High | Not Applicable | To be determined |
| EXTERNAL RISK |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Project context |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Political stability | Political context is stable and safe | Political context is unstable but predictable and not a threat to project implementation | Very disruptive and volatile |  | x |  |  |  |  | PM: So far, political context has been predictable, but it is not stable. At this point it is not a threat to project activities implementation. |  | X |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: Stable but complex political context that occasionally delays project implementation |  |  |  |  |  |  |
| Environmental conditions | Project area is not affected by severe weather events or major environmental stress factors | Project area is subject to more or less predictable disasters or changes | Project area has very harsh environmental conditions |  |  | x |  |  |  | PM: Project areas mainly have harsh environmental conditions, unpredictable and often with poor or no monitoring of biodiversity loss in place. |  |  | X |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: |  |  |  |  |  |  |
| Social, cultural and economic factors | There are no evident social, cultural and/or economic issues that may affect project performance and results | Social or economic issues or changes pose challenges to project implementation but mitigation strategies have been developed | Project is highly sensitive to economic fluctuations, to social issues or cultural barriers |  |  | x |  |  |  | PM: Project is highly sensitive to economic fluctuations, to social issues and cultural barriers, due to the understanding of the protected areas concept and influence local community has for the designation of PAs as an influencer (decision maker) within the country |  |  | X |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: agree |  |  |  |  |  |  |
| Capacity issues | Sound technical and managerial capacity of institutions and other project partners | Weaknesses exist but have been identified and actions is taken to build the necessary capacity | Capacity is very low at all levels and partners require constant support and technical assistance | x |  |  |  |  |  | PM: Mostly sound technical and managerial capacity of institutions and other project partners | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: |  |  |  |  |  |  |
| Others, please specify |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

If there is a significant (over 50% of risk factors) discrepancy between Project Manager and Task Manager rating, an explanation by the Task Manager should be provided below

TOP RISK MITIGATION PLAN

Rank – importance of risk Risk Statement – potential problem (condition and consequence) Action to take – action planned/taken to handle the risk Who – person(s) responsible for the action Date – date by which action needs to be or was completed

| Rank | Risk Statement |  | Action to Take | Who | Date |
| --- | --- | --- | --- | --- | --- |
|  | Condition | Consequence |  |  |  |
| Substantial | Complex political organization of the country | Slow project progress or partial implementation of activities | Frequent communication and meetings with the project stakeholders and decision makers | Project team | Ongoing |
| Substantial | Preparedness of the local community to participate in the process for designation | Slow progress | Frequent advocacy meetings Additional communication material | Project team and project partners | continuously |

Project overall risk rating (Low, Medium, Substantial or High) (Please include PIR risk ratings for all prior periods, add columns as necessary):

| FY2018 rating | FY2019 rating | Comments/narrative justifying the current FY rating and any changes (positive or negative) in the rating since the previous reporting period |
| --- | --- | --- |
| L | L | Despite some existing risks and challenge arising from the complex political context in Bosnia and Herzegovina, the project is progressing mostly according to plan and the project team has established appropriate mitigation measures |
|  |  | If a risk mitigation plan had been presented for a previous period or as a result of the Mid-Term Review/Evaluation please report on progress or results of its implementation |

For joint projects and where applicable ratings should also be discussed with the Task Manager of co-implementing agency.

Some projects are adopting/planning to adopt milestones for tracking the achievement of outcomes. Add the corresponding milestones in this column when applicable to inform the rating. Milestones are optional and may substitute for Mid-Term Target.

Use GEF Secretariat required six-point scale system: Highly Satisfactory (HS), Satisfactory (S), Marginally Satisfactory (MS), Marginally Unsatisfactory (MU), Unsatisfactory (U), and Highly Unsatisfactory (HU).

Add rows if your objective has more than 3 outcome indicators. Same applies for the number of outcomes.

Outputs as described in the project logframe or in any updated project revision.

As per latest workplan (latest project revision)

Implementation may be assessed by qualitative assessments, percentage of delivery, and/or budget expenditure (planned and actually spent).  The 2018 assessment should be copied from previous PIR.

To be provided by the UNEP Task Manager

Use GEF Secretariat required six-point scale system: Highly Satisfactory (HS), Satisfactory (S), Marginally Satisfactory (MS), Marginally Unsatisfactory (MU), Unsatisfactory (U), and Highly Unsatisfactory (HU)

Only for Substantial to High risk.