UN Environment GEF PIR Fiscal Year 2019

- July 2018 to 30 June 2019)

| - Identification |  |  | GEF ID.: 4259 | Umoja no.: P1-33GFL-000531, SB-000768.03.01, BP 1500003743 |  |
| --- | --- | --- | --- | --- | --- |
| Project Number + Project Title |  |  | Conservation Agreements Private Partnership Platform |  |  |
| Duration months | Planned |  | 60 months |  |  |
|  | Extension(s) |  | 30/06/2020, 6 months |  |  |
| Division(s) Implementing the project |  |  | Conservation Stewards Program, Conservation Finance Division, Conservation International |  |  |
| Executing Agency(ies) |  |  | UNEP |  |  |
| Names of Other Project Partners |  |  | Fundación Natura Bolivia |  |  |
|  |  |  | Keystone Foundation |  |  |
|  |  |  | Wildlife Conservation Society |  |  |
|  |  |  | Shan Shui Conservation Centre |  |  |
|  |  |  | Farm Africa |  |  |
| Project Type |  |  | Full size |  |  |
| Project Scope |  |  | Global |  |  |
| Region (delete as appropriate) |  |  | Africa, Asia Pacific, Latin America and Caribbean |  |  |
| Names of Beneficiary Countries |  |  | Colombia, Peru, Guatemala, China, South Africa, Ecuador, Kenya, Cambodia, Mozambique, Uganda, Bolivia, Ethiopia, India |  |  |
| Programme of Work |  |  | PoW 2018-19 Subprogramme 3 Healthy and productive ecosystems |  |  |
| GEF Focal Area(s) |  |  | Biodiversity |  |  |
| UNDAF linkages |  |  | Difficult to align – global project |  |  |
| Link to relevant SDG target(s) and SDG indicator(s) |  |  | 15.1 – 15.1.1, 15.1.2 15.2 – 15.2.1 15.3 – 15.3.1 15.5 – 15.5.1 1.1 – 1.1.1 1.2 – 1.2.1 |  |  |
| GEF financing amount |  |  | $5,000,000 |  |  |
| Co-financing amount |  |  | $15,000,000 |  |  |
| Date of CEO Endorsement |  |  | 28/05/2010 |  |  |
| Start of Implementation |  |  | 30/09/2014 |  |  |
| Date of first disbursement |  |  | 17/11/2014 |  |  |
| Total disbursement as of 30 June |  |  | $4,630,000.11 |  |  |
| Total expenditure as of 30 June |  |  | $4,279,744.00 |  |  |
| Expected Mid-Term Date |  |  | June 2017 (Actual April 2019) |  |  |
| Completion Date |  | Planned | 31/12/2019 |  |  |
|  |  | Revised | 30/06/2020 |  |  |
| Expected Terminal Evaluation Date |  |  | 31/12/2020 |  |  |
| Expected Financial Closure Date |  |  | 31/12/2020 |  |  |

- OVERVIEW OF PROJECT STATUS

| UN Environment Subprogramme(s) PoW 2018-19 Subprogramme 3 Healthy and productive ecosystems | Specify the relevant Expected Accomplishment(s) & Indicator(s) EA (b) Policymakers in the public and private sectors test the inclusion of the health and productivity of ecosystems in economic decision-making Indicator (ii) Increase in the number of private sector entities that adjust their business models to reduce their ecosystem-related risks and/or negative impacts on marine and terrestrial ecosystems |
| --- | --- |
| CAPPP currently includes 69 conservation agreements signed with communities and 722 agreements signed with individuals/families across 14 sites. This amounts to 1,184,852 ha of important ecosystems under improved management using conservation agreements across the portfolio. The conservation agreements (CA) apply one or more of the three private sector engagement/market-based approaches in the CAPPP framework: 1) natural product sourcing 2) corporate responsibility, and 3) SME development. The project has already outpaced the end of project targets for numbers of agreements using each of these approaches, i.e. 36 natural product sourcing CAs; 18 corporate responsibility CAs and 21 SME development CAs are already in place |  |

For all GEF 6 and later projects:

| GEF Core Indicators | Indicative expected Results |
| --- | --- |
| N/A – GEF5 project | Indicative expected Results [ |

| Planned linkages with UNDAF | N/a – global project |
| --- | --- |

| Planned contribution to relevant SDG target(s) and SDG indicator(s) | The project does not track the individual SDG indicators but it is aligned with the goals and would logically contribute to the indicators. The incentives provided through conservation agreements and the project framework of engaging the private sector and improving supply chains is directly aimed at increasing household income. This relates to target 1.1 and 1.2 and the associated indicators. The core objective of the project is nature conservation and each sub-project takes place within a specific threatened ecosystem. Forests are common across the portfolio, therefore target 15.1 and associated indicators are influenced. The project actively preserves forest, restores forest, and improves the management of forests. The Namaqualand and K2C sub-projects specifically target restoration of degraded ecosystems and contribute to target 15.3 and the associated indicator. And finally, all of the projects logically contribute to target 15.5 through the direct conservation of species in some cases (eg. sea turtles in Colombia, panda in China) and conservation of habitat in all cases. |
| --- | --- |

| Implementation Status | FY 2015 | FY 2016 | FY 2017 | FY 2018 | FY 2019 |
| --- | --- | --- | --- | --- | --- |
|  | 1st PIR | 2nd PIR | 3rd PIR | 4th PIR | 5th PIR |

| Development Objective Rating FY | FY 2015 | FY 2016 | FY 2017 | FY 2018 | FY 2019 |
| --- | --- | --- | --- | --- | --- |
|  |  | S | S | S | S |
| CAPPP currently includes 69 conservation agreements signed with communities and 722 agreements signed with individuals/families across 14 sites. This amounts to 1,184,852 ha of important ecosystems under improved management using conservation agreements across the portfolio. The conservation agreements apply one or more of the three private sector engagement/market-based approaches in the CAPPP framework: 1) natural product sourcing 2) corporate responsibility, and 3) SME development. The project has already outpaced the end of project targets for numbers of agreements using each of these approaches. Each of the sub-projects has a specific theory of change. CI is tracking 2-3 environmental and 2-3 social indicators per project, as well as a handful of output-type indicators for the entire portfolio. To date, some points of reference include: - More than 30,000 direct beneficiaries of the incentives/benefits provided through the conservation agreements. - Increase in biomass, halting of soil loss, reduction in invasive species reported in Kruger to Canyons South Africa, based on communities adopting improved rangelands management plans. Simultaneous increases in price/kg for livestock and percentage of people selling livestock. - Increase in sales by 45% for women’s cooperative in Colombia’s indigenous La Guajira department, a critical income source in an otherwise economically impoverished area, based on commitments to protect local sea turtle nests/beaches. Increase of 66% in household income derived from coffee sales in Ethiopia based on conservation of wild coffee forests (and an increase in total household income of 11% derived from the conservation agreements, on average). Over a million dollars generated through livestock auctions based on improved rangelands management for herders in Namaqualand, South Africa, reinforcing conservation of the succulent karoo. - Improved water security and quality across 12 municipalities in Bolivia through the creation of 4 new water funds and strengthening of 5 existing water funds - Adoption of the conservation agreements methodology at the policy level in CAPPP countries South Africa, Peru, Colombia, Bolivia and Guatemala. - Sourcing agreements and co-financing commitments with the private sector including such companies as Coca-Cola, HSBC, Mitsubishi, Mitsui, Cargill, Krasna Kambodi, and Last Forest. It should also be noted that CI’s conservation agreement portfolio currently stands at ~3M hectares and 90,000 beneficiaries. The CAPPP is providing critical lessons which benefit the entire portfolio of conservation agreements. The annual Learning Network Meeting is an important venue through which to share lessons on engaging the private sector, improving supply chains, and helping communities produce nature-based goods and services for the private sector with both high quality and consistent quantity. The final year of the CAPPP needs to focus on identifying lessons learned from the projects and communicating those widely with the aim of encouraging replication. This has been saved until the end of the CAPPP because each sub-project is only two years roughly in duration. Thus, it makes sense to analyse the entire project cycle across all of the sub-projects after they have had a chance to design, negotiate, implement, monitor, and adapt the conservation agreements. A Learning Network meeting is planned for December, 2020 which will provide an important sounding board and thought venue for identifying lessons learned. The mid-term review was also completed during this reporting period. While late in implementation, it did help to identify some important areas for improvement which are being addressed. |  |  |  |  |  |

| Implementation Progress Rating | FY 2015 | FY 2016 | FY 2017 | FY 2018 | FY 2019 |
| --- | --- | --- | --- | --- | --- |
|  |  | S | S | S | S |
| The pre-selected sites are all concluded in terms of CAPPP funding. They continue implementation through other sources of funding and continue to scale up to additional communities. This is a demonstration that he CAPPP was successful in creating longer-term conservation strategies that can be sustained. The projects selected during the two rounds of calls for proposals are still under implementation. Three projects (Cambodia, K2C and Bolivia) may be granted a no-cost extension through April, 2020 if a no-cost extension to the CAPPP is granted. The purpose of doing so is that these projects can achieve and gather evidence on additional outcomes if given additional time, and at no cost. For example, the conservation agreements in South Africa would be able to go through another rainy season and livestock sales cycle which will allow them to gather and provide additional data on rangelands condition and income generation. A steering committee meeting was held in June 2019, during which time a proposed amendment extending CAPPP through June 2020 was discussed. This amendment is under review by UNEP. The final Learning Network meeting is planned for December 2020. And the final year will include a heavy emphasis on identifying lessons learned and external communications. |  |  |  |  |  |

| Risk Rating | FY 2015 | FY 2016 | FY 2017 | FY 2018 | FY 2019 |
| --- | --- | --- | --- | --- | --- |
|  |  | L | L | L | L |
| The only key change since the last report has to do with potential negative changes to community rights to access land and non-timber forest products in the India sub-project. This is due to changes in the Forest Rights Act. CI and Keystone Foundation are monitoring the situation and adapting the project activities, specifically the incentive arrangements which are focused on marketing NTFPs. To date these changes have not affected compliance with the conservation agreement commitments. |  |  |  |  |  |

| Stakeholder engagement | At this stage most of the stakeholder engagement activities take the form of maintaining existing relationships for conservation agreement implementation and communicating with stakeholders about project success. Key activities under the CAPPP is the facilitation of private sector relationships with local communities or other agents along the supply chain for the purchasing of local goods and services derived from nature. |
| --- | --- |

| Gender mainstreaming | Conservation International’s conservation agreements model recognizes that men and women interact with their environment in different ways, and therefore have different needs, priorities and interests in conservation. The sub-projects under this project are encouraged to include gender considerations during feasibility analysis, activity design, monitoring and evaluation and staffing and budgeting. It is critical that the differences across genders with regards to decision-making, use of the environment, and opportunities for economic development are understood and incorporated within the conservation agreement cycle. One example of this approach from this project stems from the work in Colombia’s La Guajira region. The conservation agreement here is focused on sea turtle protection. The incentive package that was negotiated includes support to a women’s handicraft cooperative. This is a critical livelihood activity in an otherwise economically impoverished region. This activity has been a great success, wherein 32 women are beneficiaries of the backpack marketing company Aa’Imaja^a. The project helped to increased sales by 45%, bringing much needed household income to these families. |
| --- | --- |

| Knowledge activities and products | The project is currently planning for the final annual Learning Network Meeting which brings together representatives from all the implementing sub-projects. At this meeting, in CAPPP site in the Sathyamangalam Tiger Reserve in India, participants will identify lessons learned from the entire CAPPP project. These lessons will be made publicly available in a paper produced by CI and will emphasize challenges and opportunities related to mainstreaming the private sector within community-based incentive-driven conservation. During the current reporting period project factsheets for all sub-projects were updated and are available on CI’s website. As part of the last Steering Committee meeting a communications plan is being created for the final year of implementation to ensure that key messaging regarding the CAPPP is made public. In addition, a 4-hr session was proposed for the IUCN World Conservation Congress in Marseille, June 2020. |
| --- | --- |

| Stories to be shared | CI and Keystone Foundation are currently discussing the possibility of communications around the project in India and the opportunity that community-based conservation presents for both the environment and human wellbeing. This would be story which must also address the current changes to the Forest Rights Act which threaten to undermine this project and others in the country. There is ample storytelling material from across the portfolio. CI is already in touch with UNEP regarding stories related to the conservation agreements in China, some of which protect critical panda habitat. There are also significant results from the work in South Africa which deals with rangelands management and has resulted in a model that is now being adopted and replicated as far as Botswana, Lesotho, and Zambia. |
| --- | --- |

- RATING PROJECT PERFORMANCE AND RISK

Based on inputs by the Project Manager, the UNEP Task Manager will make an overall assessment and provide ratings of:

- Progress towards achieving the project Results(s)- see section 3.1

- Implementation progress – see section 3.2

Section 3.3 on Risk should be first completed by the Project Manager. The UNEP Task Manager will subsequently enter his/her own ratings in the appropriate column.

  - 3.1	Rating of progress towards achieving the project Results(s)

| Project objective and Outcomes | Indicator | Baseline level | Mid-Term Target or Milestones | End of Project Target | Observations/ justification on rating | Progress rating |
| --- | --- | --- | --- | --- | --- | --- |
| Objective Demonstrate the potential for achieving biodiversity conservation and ecosystem service maintenance with private sector support through the use of conservation agreements with local land- and resource-users | Conservation outcomes consolidated in globally important sites using CAs with private sector support | 500,000 | 750,000 | 1,000,0000 | 1,184,852 | S |
| Outcome 1: Conservation agreements with communities under implementation with private sector support | Natural product sourcing CAs in place | 3 | 6 | 10 | 36 | HS |
|  | Corporate responsibility CAs in place | 5 | 10 | 15 | 18 | HS |
|  | SME development CAs in place | 3 | 4 | 5 | 21 | HS |
| Outcome 2: Knowledge management: best practice for conservation agreements as private sector engagement tool documented and shared | Annual Learning Network event held | 0 | 2 | 4 | 4 | S |
|  | Information on each CA available on web | 0 | 20 | 30 | 14 There are only 14 actual sub-projects with a factsheet for each; 100% of projects have factsheets. The indicator of “Information on each CA available on web” has been met, but the initial target is not logically aligned to each sub-project having various CAs | S |
|  | Number of publications produced | 0 | 2 | 5 | 5 | S |
| Outcome 3: Project Management: CAPPP effectively managed through sound implementation arrangements and processes | Annual PSC sessions convened | 0 | 2 | 5 | 5 | S |
|  | Operational Manual Approved at first PSC session | 0 | 1 | 1 | 1 | S |
|  | Annual reports, mid-term review, and audits performed | 0 | (see Appendix 8) | (see Appendix 8) | 11 | S |

Overall rating of project progress towards meeting project Result(s)

| FY2018 rating [previous] | FY2019 rating [current] | Justification of the current FY rating and explanation of reasons for change (positive or negative) since previous reporting periods. |
| --- | --- | --- |
| S | S | The project has reached or exceeded most of its midterm targets, particularly regarding the establishment of various forms of conservation agreements. The outcome indicator - conservation outcomes consolidated in globally important sites using CAs with private sector support – with a final target of 1 million ha was achieved, amounting to 1,184,852 ha of important ecosystems under improved management, using conservation agreements across the portfolio. |

Risks to the delivery of results

The second column should be completed by the Project Manager and the third column should summarize the recommendations that the Project Manager and Task Manager have agreed upon to address the problem/risk.  Projects should complete only the relevant sections and are free to add/delete problems/risks.  This section should inform the risk rating in section 3.3.

| Problems/risks identified | Description of the problem/risk | Agreed recommended actions |
| --- | --- | --- |
| on achieving targets |  |  |
| on stakeholder engagement |  |  |
| on gender actions |  |  |
| on safeguards |  |  |
| on delivering GEF Core Indicators |  |  |
| on delivering of PoW EA |  |  |
| on sustainability of results |  |  |
| others |  |  |

3.2	Rating of progress implementation towards delivery of outputs

| Outputs | Expected completion date | Implementation status as of 30 June 2018 (%) | Implementation status as of 30 June 2019 (%) | Comments if variance. Describe any problems in delivering outputs | Progress rating |
| --- | --- | --- | --- | --- | --- |
| Output 1: Conservation agreements with communities under implementation with private sector support |  |  |  |  |  |
| Activity 1: CAs in pre-selected sites renewed and under implementation | 30/08/2019 | 100% | 100% | All CAs have been renewed except for 1 of the 3 sites in Colombia (Amazonas). This CA has taken a different form and is not considered a CA following CI’s model. | S |
| Activity 2: CAs in new sites under implementation | 30/08/2019 | 90% | 100% | CI Cambodia is expanding the model to the Prey Lang Wildlife Sanctuary. This agreement is under design with the community and will be continued post-CAPPP. The Cardamom Mountains CA in Cambodia is under implementation. | S |
| Activity 3: Private sector relationships cultivated and managed | 30/08/2019 | 100% | 100% | At this point the necessary relationships are in place. Relationship management is ongoing and new partnerships can be created as appropriate. | S |
| Activity 4: Training on CA design, implementation, monitoring and financing provided to site implementers | 30/08/2018 | 90% | 100% | Trainings have been provided for all implementers and key partners. However, training continues as new opportunities are identified. | S |
| Activity 5: Individual initiative progress tracked | 30/08/2019 | 75% | 90% | We are nearing completion of most sub-projects. A few will possibly be extended into 2020 with ongoing progress tracking. This is because additional outcomes/evidence can be achieved/gathered at no additional cost. | S |
| Activity 6: Mid-term and final portfolio evaluations performed | 30/08/2019 | 50% | 50% | Mid-term complete | S |
| Output 2: Knowledge Management: best practice for conservation agreements as private sector engagement tool documented and shared |  |  |  |  |  |
| Activity 7: Annual Learning Network Meeting convened | 30/08/2019 | 75% | 75% | Fourth and final LNM is planned for India in December 2019. | S |
| Activity 8: Information on CAPPP portion of CSP disseminated | 30/08/2019 | 75% | 80% | Information shared with private sector partners and with NGOs during individual meetings, training sessions and events. What remains to be shared is end of project outcomes and lessons learned. | S |
| Activity 9: Best practice publications prepared | 30/08/2018 | 60% | 50% | Analyses have been done and metrics tracked. A best practice publication probably makes the most sense once the initial projects have been completed and the newer projects have had the chance to create some real results. | S |
| Activity 10: Publications on impacts of CA on conservation of diverse ecosystems and human wellbeing prepared | 30/08/2019 | 60% | 70% | Factsheets are publicly available on CI’s website. Indicators of impacts are being tracked for all projects. Recently a consultancy was awarded to do some additional analysis of impacts in Namaqualand. The projects still under implementation are still gathering initial impact data. | S |
| Output 3: Project Management: CAPPP effectively managed through sound implementation arrangements and processes |  |  |  |  |  |
| Activity 11: All management and reporting activities ongoing throughout life of the project | 30/08/2019 | 75% | 80% | On track. | S |

Overall project implementation progress  (To be completed by UNEP GEF Task Manager.):

| FY2018 rating [previous] | FY2019 rating [current] | Justification of the current rating and explanation of reasons for change (positive or negative) since previous reporting periods. |
| --- | --- | --- |
| S | S | All implementation activities are on track; CAPPP currently includes 69 conservation agreements (CA) signed with communities and 722 agreements signed with individuals/families across 14 sites. CAs apply one or more of the three private sector engagement/market-based approaches in the CAPPP framework: 1) natural product sourcing 2) corporate responsibility, and 3) SME development. The project has already outpaced the end of project targets for numbers of agreements using each of these approaches, i.e. 36 natural product sourcing CAs; 18 corporate responsibility CAs and 21 SME development CAs are already in place. |

Risks in implementation

This section should be completed by the Project Manager and summarize implementation risks (e.g. procurement delays, reputational risks etc).

The first column should be completed by the Project Manager and the second column should summarize the recommendations that the Project Manager and Task Manager have agreed upon to address the problem/risk.  This section should inform the risk rating in section 3.3.

| Problems/risks identified | Agreed recommended actions | By whom | When |
| --- | --- | --- | --- |
| This project empowers local communities to be active managers and stewards of nature. A key component involves creating and delivering benefits for communities to incentivise conservation. Frequently this involves marketing goods and services derived from nature, such as non-timber forest products. The sub-project in India is being affected by a change in the national Forest Rights Act which includes eviction of forest-dwelling communities and restriction of access to NTFPs. While the communities participating in the project do not face eviction their rights to harvest and sell NTFPs is under threat. | CI is working with the local implementation partner, Keystone Foundation, to adaptively manage this conservation agreement including adaptation of the types of activities that the communities will undertake related to NTFP harvest and sale. This includes focusing on NTFPs that are not affected by changes to the Forest Rights Act (eg. honey) and emphasizing the incentives in the conservation agreement related to organic farming, which are also not yet affected. The risk is more pronounced when considering the long-term sustainability of the conservation paradigm the project intends to create as this can be undermined by unforeseen changes to the Forest Rights Act and other key pieces of legislation. | CI and Keystone Foundation | Ongoing |

3.3. Risk Rating

| Risk | Mitigation at CEO approval | Mitigation at implementation | Rank |
| --- | --- | --- | --- |
| Community cannot deliver consistent quantity/quality of natural product/environment services | Work with private sector partners and local NGO partners to align expectations and invest in requisite capacity Engage sufficient number of communities to enhance likelihood of adequate supply | No indication of threat or failure to deliver necessary quantity/quality of services | CEO: M |
|  |  |  | PM: L |
|  |  |  | TM: L |
| Local small- and medium sized enterprise development fails due to challenges facing business in remote geographies | Perform extensive due diligence/feasibility assessment to ensure selection of suitable enterprise investment, using CI’s proven Verde Ventures methodology Provide technical capacity-building grants | To date, local SMEs have exhibited strong and sustainable growth due to the due diligence process and the work of the partners in providing technical support | CEO: M |
|  |  |  | PM: L |
|  |  |  | TM: L |
| Overall Risk Rating Project Manager |  |  | L |
| Overall Risk Rating Task Manager |  |  | L |

| FY2018 rating [previous] | FY2019 rating [current] | Justification of the current risk rating and explanation of reasons for change (positive or negative) since previous reporting periods. |
| --- | --- | --- |
| L | L | As noted above, only one new risk has been identified for one sub-project. That is changes by government to national laws that regulate how communities use the environment, in this case the Forest Rights Act which determines how the CAPPP-beneficiary communities can or cannot harvest non-timber forest products. The conservation agreement methodology is one of adaptive management and re-negotiation and the implementer, Keystone Foundation, has so far been successful in adapting to these changes. The existential risk of climate change has not been found to affect the sub-projects to date in any unanticipated or material way. The same applies to the above two risks that were considered medium at CEO approval, but never affected the delivery of project implementation, they are thus ranked as low toward the end of project life by both the PM and the TM |

High Risk (H): There is a probability of greater than 75% that assumptions may fail to hold or materialize, and/or the project may face high risks. 
Substantial Risk (S): There is a probability of between 51% and 75% that assumptions may fail to hold and/or the project may face substantial risks. 
Modest Risk (M): There is a probability of between 26% and 50% that assumptions may fail to hold or materialize, and/or the project may face only modest risks. 
Low Risk (L): There is a probability of up to 25% that assumptions may fail to hold or materialize, and/or the project may face only modest risks.

Annexes and/or Links:

- Project Steering Committee Minutes of the year reported

- Risk Factor Table form previous template

Risks Factor Table

There are two tables to assess and address risk: the first “risk factor table” to describe and rate risk factors; the second “top risk mitigation plan” should indicate what measures/action will be taken with respect to risks rated Substantial or High and who is responsible to for it.

High Risk (H): There is a probability of greater than 75% that assumptions may fail to hold or materialize, and/or the project may face high risks. 
Substantial Risk (S): There is a probability of between 51% and 75% that assumptions may fail to hold and/or the project may face substantial risks. 
Modest Risk (M): There is a probability of between 26% and 50% that assumptions may fail to hold or materialize, and/or the project may face only modest risks. 
Low Risk (L): There is a probability of up to 25% that assumptions may fail to hold or materialize, and/or the project may face only modest risks.

RISK FACTOR TABLE

Project Managers will use this table to summarize risks identified in the Project Document and reflect also any new risks identified in the course of project implementation. The Notes column should be used to provide additional details concerning manifestation of the risk in your specific project, as relevant. The “Notes” column has one section for the Project Manager (PM) and one for the UNEP Task Manager (TM). If the generic risk factors and indicators in the table are not relevant to the project rows should be added. The UNEP Task Manager should provide ratings in the right hand column reflecting his/her own assessment of project risks.

|  |  |  |  | Project Manager Rating |  |  |  |  |  | Notes | Task Manager Rating |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Risk Factor | Indicator of Low Risk | Indicator of Medium Risk | Indicator of High Risk | Low | Medium | Substantial | High | Not Applicable | To be determined |  | Low | Medium | Substantial | High | Not Applicable | To be determined |
| INTERNAL RISK |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Project management |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Management structure [Roles and responsibilities] | Stable with roles and responsibilities clearly defined and understood | Individuals understand their own role but are unsure of responsibilities of others | Unclear responsibilities or overlapping functions which lead to management problems | X |  |  |  |  |  | PM : CI has a clear knowledge of roles and responsibilities for project implementation. | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: agree |  |  |  |  |  |  |
| Governance structure [oversight] | Steering Committee and/or other project bodies meet periodically and provide effective direction/inputs | Body(ies) meets periodically but guidance/input provided to project is inadequate. TOR unclear | Members lack commitment Committee/body does not fulfil its TOR | X |  |  |  |  |  | PM: The fifth SC meeting took place in June 2019. Significant additional information was produced as requested. Two members, including the GEF-SEC, did not attend. The risk that this affects the CAPPP is also low. However, it does not benefit the CAPPP positively to the degree that it could. | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: agree |  |  |  |  |  |  |
| Internal communications | Fluid and cordial | Communication process deficient although relationships between team members are good | Lack of adequate communication between team members leading to deterioration of relationships and resentment | X |  |  |  |  |  | PM: Communication with CAPPP task manager has been fluent and cordial. | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: agree |  |  |  |  |  |  |
| Work flow Budget | Project progressing according to work plan | Some changes in project work plan but without major effect on overall timetable | Major delays or changes in work plan or method of implementation | X |  |  |  |  |  | PM: All activities are on track. The only activities which remain to be done to a significant degree are analysis of impact, lessons learned and reporting out. This is due to the nature of the project and the fact that agreements are cooperatively designed. This process is important and intentional. Impact data therefore comes late in the process. Lessons learned should be analyzed at project closure. | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: agree. LL and BP should also be publicized on the web |  |  |  |  |  |  |
| Co-financing | Co-financing is secured and payments are received on time | Is secured but payments are slow and bureaucratic | A substantial part of pledged co-financing may not materialize | X |  |  |  |  |  | PM: Co-financing for pre-selected sites prior project implementation and for current project period has been obtained. There is clear evidence that pre-selected sites which have closed under CAPPP are implementing and expanding under other funding sources, as intended. | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: agree |  |  |  |  |  |  |
| Budget | Activities are progressing within planned budget | Minor budget reallocation needed | Reallocation between budget lines exceeding 30% of original budget | X |  |  |  |  |  | PM: until now activities are progressing according to the budget. | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: agree |  |  |  |  |  |  |
| Financial management | Funds are correctly managed and transparently accounted for | Financial reporting slow or deficient | Serious financial reporting problems or indication of mismanagement of funds | X |  |  |  |  |  | PM: CI´s financial team follows the organization´s procedures for funds management. | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: agree |  |  |  |  |  |  |
| Reporting | Substantive reports are presented in a timely manner and are complete and accurate with a good analysis of project progress and implementation issues | Reports are complete and accurate but often delayed or lack critical analysis of progress and implementation issues | Serious concerns about quality and timeliness of project reporting | X |  |  |  |  |  | PM: reports from partners that have signed grant agreements are submitted on time and are reviewed by the Conservation Stewards Program team. | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: agree |  |  |  |  |  |  |
| Stakeholder engagement | Stakeholder analysis done and positive feedback from critical stakeholders and partners | Consultation and participation process seems strong but misses some groups or relevant partners | Symptoms of conflict with critical stakeholders or evidence of apathy and lack of interest from partners or other stakeholders | X |  |  |  |  |  | PM: Stakeholder involvement for the implementation of CAs in all sites appears to be strong | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: agree |  |  |  |  |  |  |
| External communications | Evidence that stakeholders, practitioners and/or the general public understand project and are regularly updated on progress | Communications efforts are taking place but not yet evidence that message is successfully transmitted | Project existence is not known beyond implementation partners or misunderstandings concerning objectives and activities evident | X |  |  |  |  |  | PM: Many of the external communications activities are undertaken by very strong teams within the actual projects (for example, Peru, Colombia, China, Bolivia, South Africa). CI Headquarters has also run a number of blogs on CAPPP projects. The Learning Network Meeting and trainings have exposed a number of practitioners to the lessons of the CAPPP and new factsheets for each project are in development. Still, a big push on external communications will be done as we are able to leverage actual project outcomes over the final months. | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: agree, all site-specific factsheets were developed, shared and published online |  |  |  |  |  |  |
| Short term/long term balance | Project is addressing short term needs and achieving results with a long term perspective, particularly sustainability and replicability | Project is interested in the short term with little understanding of or interest in the long term | Longer term issues are deliberately ignored or neglected | X |  |  |  |  |  | PM: At this point all sub-grants have been made. The emphasis on day to day management is maintained at the implementer level. The CSP team monitors for appropriate implementation and long-term planning. | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: agree |  |  |  |  |  |  |
| Science and technological issues | Project based on sound science and well established technologies | Project testing approaches, methods or technologies but based on sound analysis of options and risks | Many scientific and /or technological uncertainties | X |  |  |  |  |  | PM: the specific activities undertaken for each individual project are based on sound science and theories of change | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: agree |  |  |  |  |  |  |
| Political influences | Project decisions and choices are not particularly politically driven | Signs that some project decisions are politically motivated | Project is subject to a variety of political influences that may jeopardize project objectives | X |  |  |  |  |  | PM: All projects have been selected based on a rigorous framework which is free from political influences. The only key risk is in India, where a recent legal change has made it difficult for communities to access non-timber forest products. This will not only hinder the CAPPP project there, but much of community-based conservation in India. CI and the implementing partners are monitoring and addressing the situation. | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: agree |  |  |  |  |  |  |
| Other, please specify. Add rows as necessary |  |  |  |  |  |  |  |  |  | PM: |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: |  |  |  |  |  |  |

|  |  |  |  | Project Manager Rating |  |  |  |  |  | Notes | Task Manager Rating |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Risk Factor | Indicator of Low Risk | Indicator of Medium Risk | Indicator of High Risk | Low | Medium | Substantial | High | Not Applicable | To be determined |  | Low | Medium | Substantial | High | Not Applicable | To be determined |
| EXTERNAL RISK |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Project context |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Political stability | Political context is stable and safe | Political context is unstable but predictable and not a threat to project implementation | Very disruptive and volatile | X |  |  |  |  |  | PM: political context is safe in pre-selected sites, and in new sites. No threats have been identified. | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: agree |  |  |  |  |  |  |
| Environmental conditions | Project area is not affected by severe weather events or major environmental stress factors | Project area is subject to more or less predictable disasters or changes | Project area has very harsh environmental conditions |  | X |  |  |  |  | PM: sub-grants in South Africa (Namaqualand) and Colombia (Guajira region) are subject to desertification. No severe weather events anticipated for the other sites and no actual negative effects have been experienced to date. |  | X |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: agree |  |  |  |  |  |  |
| Social, cultural and economic factors | There are no evident social, cultural and/or economic issues that may affect project performance and results | Social or economic issues or changes pose challenges to project implementation but mitigation strategies have been developed | Project is highly sensitive to economic fluctuations, to social issues or cultural barriers | x |  |  |  |  |  | PM: all sub-grants provided under the CAPPP face no social, cultural and/or economic issues that may affect the sub-grants performance. | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: agree |  |  |  |  |  |  |
| Capacity issues | Sound technical and managerial capacity of institutions and other project partners | Weaknesses exist but have been identified and actions is taken to build the necessary capacity | Capacity is very low at all levels and partners require constant support and technical assistance | x |  |  |  |  |  | PM: partners implementing sub-grants know well the conservation agreements model and have proven for several years their capacity to implement conservation agreements. New partners developing implementing conservation agreements are being trained and supported by the regional managers to ensure the quality of the work. | x |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: agree |  |  |  |  |  |  |
| Others, please specify |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

If there is a significant (over 50% of risk factors) discrepancy between Project Manager and Task Manager rating, an explanation by the Task Manager should be provided below

TOP RISK MITIGATION PLAN

Rank – importance of risk Risk Statement – potential problem (condition and consequence) Action to take – action planned/taken to handle the risk Who – person(s) responsible for the action Date – date by which action needs to be or was completed

| Rank | Risk Statement |  | Action to Take | Who | Date |
| --- | --- | --- | --- | --- | --- |
|  | Condition | Consequence |  |  |  |

Project overall risk rating (Low, Medium, Substantial or High) (Please include PIR risk ratings for all prior periods, add columns as necessary):

| FY2018 rating | FY2019 rating | Comments/narrative justifying the current FY rating and any changes (positive or negative) in the rating since the previous reporting period |
| --- | --- | --- |
| L | L | No significant internal or external risks that might affect project implementation as planned for |
|  |  | If a risk mitigation plan had been presented for a previous period or as a result of the Mid-Term Review/Evaluation please report on progress or results of its implementation |

Mid-Term Review

This section should be completed if project progress towards meeting recommendations was rated MS, MU, U or HU during the previous Mid-term Review/Evaluation (To be completed by Project Manager).

| Recommendation | Action(s) taken | By whom | When |
| --- | --- | --- | --- |
| Recommendation #1 |  |  |  |
| Recommendation 1: It is recommended that the project is extended one additional year to focus activities on monitoring biodiversity and social indicators, since there is not much information on these activities that will be of significance when assessing platform’s results. As the executing agency reported that all GEF resources have been already allocated, it is suggested to analyze this information and check if re-allocations of funds are possible to carry out the recommendations from this evaluation. | Based on the review, CI has already built a database and dashboard for keeping track of key information on each agreement. This tracker contains information related to descriptive elements (hectares, beneficiaries, target biome, implementer, funders, etc.). We have also begun to integrate collection in this tracker of each CA’s specific environmental and social indicators, as per the theory of change. This information will be pulled from existing sources, primarily technical reports and interviews. It will be compiled online and will be available at any time to the project team. It is connected to PowerBI so that dashboards can be created, and data analyzed easily. This process itself will not require an extension. However, it will provide a very clear understanding of the level of information available. In terms of finance, no additional funds are required by CI. However, CI is also assessing the opportunities to maximize impact through a no-cost extension. The project in K2C, South Africa for example could use an extension of 3-4 months to establish an additional season’s worth of monitoring data/evidence. The project’s in Bolivia and India can similarly achieve additional outcomes with a no-cost extension. It is also noted that some indicators should be aggregatable from agreement to portfolio level. Existing indicators like beneficiaries and hectares are easily aggregatable. Others, like veld condition (South Africa) are not. CI requested the advice of the SC in terms of additional desired indicators at the aggregated scale. We will continue developing these indicators through the final learning meeting in December 2019. | Zachary Wells | Monitoring tracker was made available to the Steering Committee meeting in June 2019. The tracker itself is complete. Additional data will be added through the full implementation period inclusive of the final reports from each sub-project. Financial analysis was also presented at this meeting. CI is requesting an extension through June 30, 2020 in order to complete analysis of the project’s environmental and social impacts. This date will allow for compilation of data collected by the sub-projects through April 30 2020 if an extension is granted. |
| Recommendation 2: CI would implement a workshop where all CI’s country offices and key site implementers partners would be explained on CAPPP project logic, discuss and update outcomes and indicators, define a set of category indicators where each CA would include their specific biodiversity and social indicators and discuss project logframe. Identification of key information that should be collected in order to report progress for each CA should also be discussed. | We propose to implement this workshop as part of the next planned Learning Network Meeting in December 2019. The category indicators can be compiled prior to the workshop based on the tracker noted above. This work can be finalized at the workshop. The CAPPP logframe will be presented again and an analysis will be done to cross-check each project’s theory of change and monitoring approach with the CAPPP project logic. Plans will be made to address any gaps which are noted with regards to reporting progress against the CAPPP logic at this time. It should be noted that a number of the projects have already closed, and the project team will prioritize establishing lessons learned from those closed projects. We do not feel that organizing regional workshops is the best use of CAPPP funds. However, we do request the advice of the SC in terms of the most impactful communication and dissemination activities. | Zachary Wells | CI is requesting an extension through June 30, 2020 in order to complete analysis of results and lessons learned. This process will be informed by the workshop to be held in December 2019. If granted, additional results will also be delivered by the sub-projects implemented through April 2020. |
| Recommendation 3: Other important activities proposed during this extension is the development of a reporting and monitoring system for the project as a whole. This means that the management will have to discuss and identify the specific requirements of information needed by GEF and UN Environment for reporting on progress, such as the stage of implementation for each conservation agreement, their link with biodiversity conservation objectives, its measurement, level of finance and co-finance for key investments and benefit packages, tracking of implementation status, results from monitoring environmental variables, number and quality of partners involved, for instance. | The project tracker that has been constructed captures much of what is described (stage of implementation, conservation objectives, partners involved, and more). What is not captured is: measurement of conservation objectives (to be captured in the monitoring tracker which is being constructed and which will pull from technical reports), level of finance and co-finance for key investments and benefit packages, and quality of partners. The approved financial reporting templates do not demonstrate levels of finance/co-finance for key investments and benefits packages. An ad-hoc exercise was undertaken by CI during the mid-term review and delivered to the reviewer. More rigorous accounting would be useful information to have, but it requires a large effort to collect and partner engagement not originally outlined in sub-agreements. Also, because the information can’t be used as a management tool for the remainder of the project, as benefit packages have been negotiated and delivered, it makes sense to do an evaluation at the end of the project to understand trends and inform future iterations. In terms of quality of partners, we assume this refers to the main implementing partner (there are multiple technical partners from consultants to longer-term partners for each project). CI applies an organization-wide due diligence process before making any sub-grant, so this baseline data is available. CI programs are exempted but the organization has all historic financial data, for example. We could construct a capacity assessment and apply it with partners, though this should be directed by the Steering Committee as it was not envisaged during the project preparation and approval. | Zachary Wells Kevin McNulty | Monitoring tracker complete by June 2019. Finance/co-finance analysis can be completed as part of final reporting. CI is requesting an extension through June 2020 by which all analysis and reporting will be completed. |
| Recommendation 4: During the extension period, a final project report, a lessons learnt document and a replication and project exit strategy should be elaborated. | The final project report and lessons learned documents are already part of the CAPPP deliverables. They will be completed by project end regardless of an extension. It should be noted that many of the CAPPP programs have already closed or are closing very soon and all have sustainability measures in place. The sustainability of these projects has been described in project factsheets which was provided to the SC in anticipation of the June meeting. We do need to allocate time after project implementation (CAPPP’s financial and technical support to each agreement) closes to allow for the final results to be drawn together in reporting. We are proposing to grant no-cost extensions to two sub-projects through April 2020. Therefore, a project extension through June 2020 will allow us to collate and these results as well. | Zachary Wells Cassandra Kane | All project reporting, a lessons learned document, and an elaboration of the project’s exit strategy/sustainability mechanisms will be delivered by project end. In order to capture the maximum level of results and learning, CI is requesting an extension through June 30, 2020. |

For joint projects and where applicable ratings should also be discussed with the Task Manager of co-implementing agency.

Some projects are adopting/planning to adopt milestones for tracking the achievement of outcomes. Add the corresponding milestones in this column when applicable to inform the rating. Milestones are optional and may substitute for Mid-Term Target.

Use GEF Secretariat required six-point scale system: Highly Satisfactory (HS), Satisfactory (S), Marginally Satisfactory (MS), Marginally Unsatisfactory (MU), Unsatisfactory (U), and Highly Unsatisfactory (HU).

Add rows if your objective has more than 3 outcome indicators. Same applies for the number of outcomes.

Outputs and activities as described in the project logframe or in any updated project revision.

As per latest workplan (latest project revision)

Variance refers to the difference between the expected and actual progress at the time of reporting.

To be provided by the UNEP Task Manager

Use GEF Secretariat required six-point scale system: Highly Satisfactory (HS), Satisfactory (S), Marginally Satisfactory (MS), Marginally Unsatisfactory (MU), Unsatisfactory (U), and Highly Unsatisfactory (HU)

Only for Substantial to High risk.