## Table of Contents
FAO-GEF Project Implementation Report
2025 – Revised Template
Period covered: 1 July 2024 to 30 June 2025
Table of Contents
1. BASIC PROJECT DATA
2. PROGRESS TOWARDS ACHIEVING PROJECT OBJECTIVE(S) (DEVELOPMENT OBJECTIVE)
3. IMPLEMENTATION PROGRESS (IP)
4. SUMMARY ON PROGRESS AND CHALLENGES
5.ENVIRONMENTAL AND SOCIAL SAFEGUARDS (ESS):RISKS FROM THE PROJECT
6. RISKS TO THE PROJECT
7. FOLLOW-UP ON MID-TERM REVIEW OR SUPERVISION MISSION
8. MINOR PROJECT AMENDMENTS
9. STAKEHOLDERS' ENGAGEMENT
10. GENDER MAINSTREAMING
11. KNOWLEDGE MANAGEMENT ACTIVITIES
12. INDIGENOUS PEOPLES AND LOCAL COMMUNITIES INVOLVEMENT
13. CO-FINANCING TABLE
14. GEO LOCATION INFORMATION
GEF-5 LDCF Indicators
GEF 6&7 LDCF Core Indicators
Annex. Monitoring Area-based GEF Core Indicator Commitments and Progress with FERM
IMPORTANT DISCLAIMER:
The final version of this PIR will be submitted to the GEF Secretariat.
The report will then be publicly available on the GEF website (click here).
Sensitive information should be submitted in Annex to be uploaded separately.
In such cases, please contact faogef-pir-support@fao.org for guidance.

## 1. Basic project data
1. Basic Project Data
General Information
Region: | Near East and North Africa (RNE)
Country(ies): | Sudan
Project Title: | Resilience of Pastoral and Farming Communities to Climate Change in North Darfur
FAO Project Symbol: | GCP /SUD/919/LDF
GEF ID: | 10159
Type of Trust Fund(s): | LDCF
GEF Focal Area(s): | Climate Change Adaptation
Project Executing Partners: | HCENR - Higher Council for Environment and Natural Resources, and the State Ministry of Production and Economic Resources of North Darfur State
Initial project duration (years): | 4 years
Project Dates
GEF CEO Endorsement Date: | 2021-12-02
Actual Agency Approval Date | 2021-07-01
Project Implementation Start Date/EOD: | 2022-01-01
First Disbursement Date | 2022-10-31
Planned Project End Date/NTE1: | 2025-12-31
Revised project implementation End date (if approved)2: | NA
Actual Completion Date: | N/A
Expected Financial Closure Date: | 2026-12-31
Funding
GEF Grant Amount (USD): | 2429680
Total GEF grant delivery (as of June 30, 2025 (USD): | 719664.78
Total Co-financing amount (USD)3: | 11300900
Total estimated co-financing materialized as of June 30, 2025: | NA because of on-going war
M & E Milestones
Date of Last Project Steering Committee (PSC) Meeting:
Expected Mid-term Review date5: | 2024-04-01
Actual Mid-term review date (if already completed): | N/A
Expected Terminal Evaluation Date6:
Overall ratings
Overall rating of progress towards achieving objectives/outcomes (cumulative): | Unsatisfactory
Overall implementation progess rating: | Unsatisfactory
Overall risk rating: | High
Status
Implementation Status (1st PIR, 2nd PIR, etc. Final PIR): | 2nd PIR
1 Date that was originally foreseen at the project’s operationalization and indicated in FPMIS. 2 If NTE extension has been requested and approved by the FAO-GEF Coordination Unit. 3 This is the total amount of co-financing as included in the CEO Document/Project Document. 4 Please refer to the Section 13 of this report where updated co-financing estimates are requested and indicate the total co-financing amount materialized. 5 The Mid-Term Review (MTR) should take place after the 2nd PIR, around half-point between EOD and NTE. The MTR report in English should be submitted to the GEF Secretariat within 4 years of the CEO Endorsement date. 6 The Terminal Evaluation date should be discussed with OED 6 months before the project’s NTE date.
Project Contacts
Contact | Name, Title, Division/Institution |  | E-mail
Project Coordinator (PC) | Amira Khojaly |  | Amira.Khojaly@fao.org
Budget Holder (BH) | Yang, Hongjie (FNSDN) |  | Hongjie.Yang@fao.org
GEF Operational Focal Point (GEF OFP) | Mona Ali Mohammed Ahmed |  | monaali202017@gmail.com
Lead Technical Officer (LTO) | Osman, Abdal Monium (OERDD) |  | abdalmonium.osma.@fao.org
GEF Technical Officer (GTO) | Seggel, Anika (OCB) |  | anika.seggle@fao.org
Key Project Management Unit Personnel
Please indicate the composition of the PMU as per the Terms of Reference in the ProDoc. If any new position was establised during the project implementation, please insert it accordingly.
Position planned (as per ProDoc) | Position filled (Yes/No) | Start date, Name, Contact |  | Comments
Project Coordinator | Yes | Amira Khojaly (National) - Amira.Khojaly@fao.org Kennedy Igbokwe ( International) - Kennedy.Igbokwe@fao.org |  | During this war period (since 2023), and with no field intervention, Ms Amira Khojaly has been coordinating this project in collaboration with Kennedy Igbokwe (International Project Officer). However, with the potential change of project location, there is a need for a full time project coordinator.

## _Calc (hidden)
Rating text | Score
Highly Unsatisfactory (HU) | 1
Unsatisfactory (U) | 2
Moderately Unsatisfactory (MU) | 3
Moderately Satisfactory (MS) | 4
Satisfactory (S) | 5
Highly Satisfactory (HS) | 6
Unknown | 0
Not Rated | 0
for DevScore
|  | Person | PM/Coord | Budget Holder | LTO | GEF OFP | GTO
|  | Weight % | 20 | 25 | 25 | 0 | 30
For ImpScore
|  | Person | PM/Coord | LTO | GEF OFP | GTO
|  | Weight % | 25 | 25 | 0 | 40
Once you've filled in 2. Progress towards outcomes & 3. Implementation Progress
Please double click and press enter on Cells D20 and D21 |  | 4
5

## Countries (hidden)
Select Country
Afghanistan
Åland Islands
Albania
Algeria
American Samoa
Andorra
Angola
Anguilla
Antarctica
Antigua and Barbuda
Argentina
Armenia
Aruba
Australia
Austria
Azerbaijan
Bahamas
Bahrain
Bangladesh
Barbados
Belarus
Belgium
Belize
Benin
Bermuda
Bhutan
Bolivia (Plurinational State of)
Bonaire, Sint Eustatius and Saba
Bosnia and Herzegovina
Botswana
Bouvet Island
Brazil
British Indian Ocean Territory
British Virgin Islands
Brunei Darussalam
Bulgaria
Burkina Faso
Burundi
Cabo Verde
Cambodia
Cameroon
Canada
Cayman Islands
Central African Republic
Chad
Chile
China
China, Hong Kong Special Administrative Region
China, Macao Special Administrative Region
Christmas Island
Cocos (Keeling) Islands
Colombia
Comoros
Congo
Cook Islands
Costa Rica
Côte d’Ivoire
Croatia
Cuba
Curaçao
Cyprus
Czechia
Democratic People's Republic of Korea
Democratic Republic of the Congo
Denmark
Djibouti
Dominica
Dominican Republic
Ecuador
Egypt
El Salvador
Equatorial Guinea
Eritrea
Estonia
Eswatini
Ethiopia
Falkland Islands (Malvinas)
Faroe Islands
Fiji
Finland
France
French Guiana
French Polynesia
French Southern Territories
Gabon
Gambia
Georgia
Germany
Ghana
Gibraltar
Greece
Greenland
Grenada
Guadeloupe
Guam
Guatemala
Guernsey
Guinea
Guinea-Bissau
Guyana
Haiti
Heard Island and McDonald Islands
Holy See
Honduras
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Isle of Man
Israel
Italy
Jamaica
Japan
Jersey
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People's Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Martinique
Mauritania
Mauritius
Mayotte
Mexico
Micronesia (Federated States of)
Monaco
Mongolia
Montenegro
Montserrat
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands (Kingdom of the)
New Caledonia
New Zealand
Nicaragua
Niger
Nigeria
Niue
Norfolk Island
North Macedonia
Northern Mariana Islands
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Pitcairn
Poland
Portugal
Puerto Rico
Qatar
Republic of Korea
Republic of Moldova
Réunion
Romania
Russian Federation
Rwanda
Saint Barthélemy
Saint Helena
Saint Kitts and Nevis
Saint Lucia
Saint Martin (French Part)
Saint Pierre and Miquelon
Saint Vincent and the Grenadines
Sint Eustatius and Saba
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Sint Maarten (Dutch part)
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
South Georgia and the South Sandwich Islands
South Sudan
Spain
Sri Lanka
State of Palestine
Sudan
Suriname
Svalbard and Jan Mayen Islands
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
Timor-Leste
Togo
Tokelau
Tonga
Trinidad and Tobago
Tunisia
Türkiye
Turkmenistan
Turks and Caicos Islands
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States Minor Outlying Islands
United States of America
United States Virgin Islands
Uruguay
Uzbekistan
Vanuatu
Venezuela (Bolivarian Republic of)
Viet Nam
Wallis and Futuna Islands
Western Sahara
Yemen
Zambia
Zimbabwe

## TypeofTrustFund (hidden)
Type of Trust Fund
Capacity-building Initiative for Transparency (CBIT)
Global Biodiversity Framework Fund (GBFF)
Global Environment Facility Trust Fund (GFF)
Least Developed Countries Fund (LDCF)
Special Climate Change Fund (SCCF)
Small Grants Program (SGP)

## FocalArea (hidden)
Focal Area
Multi Focal Area
Biodiversity
Chemicals and Waste
Chemicals/PoPs
Climate Change
Climate Change Adaptation
Climate Change Mitigation
International Waters
Land Degradation

## 2. Progress towards outcomes
2. Progress towards Achieving Project Objective(s) (Development objective)
(All inputs in this section should be cumulative from project start, not annual)
Please indicate the project’s main progress towards achieving its objective(s) and the cumulative level of achievement of each outcome since the start of project implementation.
Project or Development Objective | Outcomes | Outcome indicators | Baseline | Mid-term Target | End-of-project Target | Cumulative progress level at 30 June 2025 | % of cumulative progress | Progress rating
To reduce the vulnerability of pastoral and farming communities to climate change along the migratory routes in North Darfur and improve their social protection, food security and nutritional status. |  | Number of vulnerable agro-pastoralists with increased resilience through innovation for climate change adaptation | 0 women and 0 men Vulnerable agro-pastoralists with increased resilience through innovation for climate change adaptation | 10,000 women and 10,000 men Vulnerable agro-pastoralists with increased resilience through innovation for climate change adaptation | 25,000 women and 25,000 men Vulnerable agro-pastoralists with increased resilience through innovation for climate change adaptation | 0 | 0% | Unsatisfactory (U)
Component 1: Participatory sustainable land and resource use planning strategically addresses climate change adaptation and mitigates resource-based conflicts
| Outcome 1: Private sector agriculture and livestock producers cooperatively and effectively managing shared resources to address climate change impacts and build system resilience. | Number of villages that adopt and implement cooperative resource management framework without conflict | 0 villages adopt and implement cooperative resource management framework without conflict | 10 villages adopt and implement cooperative resource management framework without conflict | 200,000 hectares of degraded agricultural and grazing lands under sustainable land management in production systems and managed according to climate resilient land use management plan. | 0 | 0% | Unsatisfactory (U)
|  | Number of hectares of degraded agricultural and grazing lands under sustainable land management in production systems and managed according to climate resilient land use management plan. | 0 hectares of degraded agricultural and grazing lands under sustainable land management in production systems and managed according to climate resilient land use management plan. | 100,000 hectares of degraded agricultural and grazing lands under sustainable land management in production systems and managed according to climate resilient land use management plan. | 3 annual land use planning implementation monitoring reports completed and presented to stakeholders at village level mtgs. | 0 | 0% | Unsatisfactory (U)
|  | Number of annual land use planning implementation monitoring reports completed and presented to stakeholders at village level mtgs. | 0 annual land use planning implementation monitoring reports completed and presented to stakeholders at village level mtgs. | 1 annual land use planning implementation monitoring reports completed and presented to stakeholders at village level mtgs. | 200,000 hectares of degraded agricultural and grazing lands under sustainable land management in production systems and managed according to climate resilient land use management plan. | 0 | 0% | Unsatisfactory (U)
|  | Number of livestock annual migration corridors identified and included within a climate resilient land use management planning framework. | 0 livestock annual migration corridors identified and included within a climate resilient land use management planning framework. | 5 livestock annual migration corridors identified and included within a climate resilient land use management planning framework. | 10 livestock annual migration corridors identified and included within a climate resilient land use management planning framework. | 0 | 0% | Unsatisfactory (U)
Component 2: Pastoralists and farmers adopt sustainable, climate resilient practices and livelihoods
| Outcome 2 North Darfur communities adopt and implement climate resilient agriculture and livestock management approaches | Number of extension officers leading APFS programs designed to deliver resilience improvements | 0 extension officers leading APFS programs designed to deliver resilience improvements | 25 (50% women/50% men) extension officers leading APFS programs designed to deliver resilience improvements Men: 50% Women: 50% | 50 (50% women/50% men) extension officers leading APFS programs designed to deliver resilience improvements Men: 50% Women: 50% | 0 | 0% | Unsatisfactory (U)
|  | Number of private sector farmers and herders enrolled in APFS. | 0 private sector farmers and herders enrolled in APFS. | 10,000 private sector farmers and herders enrolled in APFS. Men: 50% Women: 50% | 50,000 private sector farmers and herders enrolled in APFS. Men: 50% Women: 50% | 0 | 0% | Unsatisfactory (U)
|  | Number of nomadic livestock producers reporting improved livestock production values and household nutrition levels as a result of project emplaced actions. | 0 nomadic livestock producers reporting improved livestock production values and household nutrition levels as a result of project emplaced actions. | 2,000 nomadic livestock producers reporting improved livestock production values and household nutrition levels as a result of project emplaced actions. Men: 50% Women: 50% | 5,000 nomadic livestock producers reporting improved livestock production values and household nutrition levels as a result of project emplaced actions. Men: 50% Women: 50% | 0 | 0% | Unsatisfactory (U)
|  | Number of agricultural producers reporting positive production values and improved nutrition as a result of adopting innovative climate resilient practices. | 0 agricultural producers reporting positive production values and improved nutrition as a result of adopting innovative climate resilient practices. | 10,000 agricultural producers reporting positive production values and improved nutrition as a result of adopting innovative climate resilient practices. Men: 50% Women: 50% | 45,000 agricultural producers reporting positive production values and improved nutrition as a result of adopting innovative climate resilient practices. Men: 50% Women: 50% | 0 | 0% | Unsatisfactory (U)
Component 3: Lessons learnt captured, mainstreamed and upscaled
| Outcome 3: Best climate resilient and adaptive practices are mainstreamed and being applied at local, regional, and national levels | Number of model village level land use plans generated with project support and uploaded into knowledge management website/portal as part of HCENR Website for monitoring, reporting, and upscale. | 0 model village level land use plans generated with project support and uploaded into knowledge management website/portal as part of HCENR Website for monitoring, reporting, and upscale. | 10 model village level land use plans generated with project support and uploaded into knowledge management website/portal as part of HCENR Website for monitoring, reporting, and upscale. | 20 model village level land use plans generated with project support and uploaded into knowledge management website/portal as part of HCENR Website for monitoring, reporting, and upscale. | 0 | 0% | Unsatisfactory (U)
|  | Number of monthly users of project emplaced knowledge management website/portal | 0 of monthly users of project emplaced knowledge management website/portal | 1,500 monthly users of project emplaced knowledge management website/portal Men: 50% Women: 50% | 3,000 monthly users of project emplaced knowledge management website/portal Men: 50% Women: 50% | 0 | 0% | Unsatisfactory (U)
|  | Hectares of agriculture and pasturelands monitored with results uploaded into KM portal showing positive delivery of climate change resilient production management targets. | 0 hectares of agriculture and pasturelands monitored and delivering climate change resilient production management targets. Agriculture: 0 ha Pasture: 0 ha | 10 model village level land use plans generated with project support and uploaded into knowledge management website/portal as part of HCENR Website for monitoring, reporting, and upscale. | 20 model village level land use plans generated with project support and uploaded into knowledge management website/portal as part of HCENR Website for monitoring, reporting, and upscale. | 0 | 0% | Unsatisfactory (U)
|  | Number of persons subscribed to and receiving monthly project updates and electronic newsletters. | 0 persons subscribed to and receiving monthly project updates and electronic newsletters. | 100,000 hectares of agriculture and pasturelands monitored and delivering climate change resilient production management targets. Agriculture: 50,000 ha Pasture: 50,000 ha | 200,000 hectares of agriculture and pasturelands monitored and delivering climate change resilient production management targets. Agriculture: 100,000 ha Pasture: 100,000 ha | 0 | 0% | Unsatisfactory (U)
|  | Number of government agencies with budget lines approved allocating adequate financing to continue critical interventions post-project including improved planning, resilient production practices, and monitoring/reporting. | 0 government agencies with budget lines approved allocating adequate financing to continue critical interventions post-project including improved planning, resilient production practices, and monitoring/reporting. | 1,000 persons subscribed to and receiving monthly project updates and electronic newsletters. Men: 50% Women: 50% | 1,200 persons subscribed to and receiving monthly project updates and electronic newsletters. Men: 50% Women: 50% | 0 | 0% | Unsatisfactory (U)
Average Cumulative progress toward outcomes (%) | Time elapsed since project start/EOD vs Planned Project End Date | % of delivery
0% | 92.33% | 29.62%
Development Objective (DO) Ratings, and Overall Assessment
Please note that the overall DO ratings should be substantiated by evidence and progress reported above. The ratings and comments should reflect the overall progress of results since project start
| FY2025 Development Objective rating¹ | Project Manager/ Coordinator | Budget Holder | Lead Technical Officer13 | GEF Operational Focal Point | GEF Technical Officer (GTO)
|  | Satisfactory (S) | Satisfactory (S) | Satisfactory (S) | Satisfactory (S) | Highly Unsatisfactory (HU)
| Comments/reasons¹² justifying the ratings for FY2025 and any changes (positive or negative) in the ratings since the previous reporting period | The preparatory activities included recruitment of National Project Coordinator and supporting staff are still available but not fuctioning because of the conflict. The current situation is not allowing any progress. | The war is still active in Darfur, no request and activity implemented. | The war is still active in Darfur, no request and activity implemented. | The war is still active in Darfur, no request and activity implemented. | The war is ongoing, implementation cannot proceed. The project remains operationally active, but is basically on hold.
Measures to address MS, MU, U and HU ratings on Section 2 above
Outcome |  | Action(s) to be taken |  | By whom? |  | By When?
Outcome 1 |  | Wait for the conflict to be resolved or change the project the location. |  | HCNER and FAO |  | 2025-09-01
Outcome 2 |  | Wait for the conflict to be resolved or change the project the location. |  | HCNER and FAO |  | 2025-09-01
Outcome 3 |  | Wait for the conflict to be resolved or change the project the location. |  | HCNER and FAO |  | 2025-09-01
7 Some indicators may not identify mid-term targets at the design stage (refer to approved results framework) therefore this column should only be filled when relevant. 8 Use GEF Secretariat required six-point scale system: Highly Satisfactory (HS), Satisfactory (S), Moderately Satisfactory (MS), Moderately Unsatisfactory (MU), Unsatisfactory (U), and Highly Unsatisfactory (HU).

## 3. Implementation Progress
3. Implementation Progress (IP)
(Please indicate progress achieved during this FY as per the Implementation Plan/Annual Workplan)
Outcomes and outputs | Indicators (as per the logical framework) | Main achievements in the last 12 months (please DO NOT repeat results reported in previous year PIR) |  |  | Describe any variance 9 in delivering outputs
Outcome 1.Private sector agriculture and livestock producers cooperatively and effectively managing shared resources to address climate change impacts and build system resilience.
Output 1.1:Participatory climate response conflict resolution and decision-making structures in place. | Number of villages that adopt and implement cooperative resource management framework without conflict. Number of hectares of degraded agricultural and grazing lands under sustainable land management in production systems and managed according to climate resilient land use management plan. Number of annual land use planning implementation monitoring reports completed and presented to stakeholders at village level mtgs. Number of livestock annual migration corridors identified and included within a climate resilient land use management planning framework. | No progress is achieved, or activities executed due to the insecurity in the project sites.
Output 1.2: Strategic sustainable land use management framework operational to support private sector adaptation and resilience |  | No progress is achieved, or activities executed due to the insecurity in the project sites. |  |  | This output was not delivered because the project area is still under conflict. No activity can ve implemented.
Outcome 2
Output 2.1: Concrete investments identified and implemented to strengthen the resilience of private producers | Number of extension officers leading APFS programs designed to deliver resilience improvements. Number of private sector farmers and herders enrolled in APFS. Number of nomadic livestock producers reporting improved livestock production values and household nutrition levels as a result of project emplaced actions. Number of agricultural producers reporting positive production values and improved nutrition as a result of adopting innovative climate resilient practices. | No progress is achieved, or activities executed due to the insecurity in the project sites
Output 2.2: Agro-pastoral Field Schools support application of climate resilient production practices |  | No progress is achieved, or activities executed due to the insecurity in the project sites. |  |  | This output was not delivered because the project area is still under conflict. No activity can ve implemented.
Outcome 3.
Output 3.1 Results strengthen national level resilience and adaptation policies | Number of model village level land use plans generated with project support and uploaded into knowledge management website/portal as part of HCENR Website for monitoring, reporting, and upscale. Number of monthly users of project emplaced knowledge management website/portal. Hectares of agriculture and pasturelands monitored with results uploaded into KM portal showing positive delivery of climate change resilient production management targets. Number of persons subscribed to and receiving monthly project updates and electronic newsletters. Number of government agencies with budget lines approved allocating adequate financing to continue critical interventions post-project including improved planning, resilient production practices, and monitoring/reporting | No progress is achieved, or activities executed due to the insecurity in the project sites
Output 3.2: Project lessons captured and disseminated. |  | No progress is achieved, or activities executed due to the insecurity in the project sites. |  |  | This output was not delivered because the project area is still under conflict. No activity can ve implemented.
Output 3.3: Effective Monitoring and Evaluation Implemented |  | No progress is achieved, or activities executed due to the insecurity in the project sites. |  |  | This output was not delivered because the project area is still under conflict. No activity can ve implemented.
Implementation Progress (IP) , and Overall Assessment
Please note that the overall IP ratings should be substantiated by evidence and progress reported above. The ratings and comments shoud reflect the overall progress of results during the fiscal year (July 1 2024, to June 30, 2025)
| Project Manager/ Coordinator | Lead Technical Officer | Budget Holder | GEF Operational Focal Point (OFP) | GEF Technical Officer (GTO)
FY2025 Implementation Objective rating10 | Satisfactory (S) | Satisfactory (S) | Satisfactory (S) | Satisfactory (S) | Highly Satisfactory (HS)
Comments/reasons justifying the ratings for FY2025 and any changes (positive or negative) in the ratings since the previous reporting period | The preparatory activities included recruitment of National Project Coordinator and supporting staff are still available but not fuctioning because of the conflict. The current situation is not allowing any progress. Comments | The war is still active in Darfur, no request and activity implemented. | The war is still active in Darfur, no request and activity implemented. | The war is still active in Darfur, no request and activity implemented. | Implementation is on hold due to the on-going conflict.
9 Variance refers to the difference between the expected and actual progress at the time of reporting. 10 Implementation Progress Rating – A rating of the extent to which the implementation of a project’s components and activities is in compliance with the projects approved implementation plan.

## 4. Summary_Progress & Challenge
4. Summary on progress and challenges
Please provide a summary paragraph on project implementation progress consistent with the information reported in section 2 and 3 of the PIR (Max 400 words) (This section will be uploaded to the GEF portal)
No progress is achieved, or activities executed due to the insecurity in North Darfur. Due to the ongoing conflict situation, it was not possible to identify specific project intervention localities. Therefore, a comprehensive assessment covering the entire state was undertaken to inform future planning and targeting. Land cover and Net Primary Productivity (NPP) were analyzed to track changes in ecosystem productivity from 2018 to 2024 across key land cover types, including rainfed and irrigated croplands, forests, and rangelands, using the 2020 Sudan land cover map and WaPOR NPP data. NPP deviation was calculated to compare annual productivity against the 5-year average, highlighting areas experiencing environmental stress or recovery. The extent of cultivated areas was mapped over the past five years to understand spatial and temporal trends in agricultural expansion, land use change, and shifting cultivation patterns. Rainfall trends were analyzed to assess changes in precipitation, which directly impact both farming and pastoral livelihoods. Additionally, flood extent between 2018 and 2024 was derived from VIIRS daily flood detection data to identify areas affected by hydrological hazards. These indicators provide critical baseline information to support future climate resilience strategies for pastoral and farming communities across North Darfur” The total OPA signed was USD 609,130 out of which a total of USD 197,025 was transferred to operational partner (HCENR) in 2022 before the war. From the transferred money, the operational partner spent about USD 37,289.96 towards project management, materials & equipment before the war in 2023. HCENR has a balance of USD 159, 735 .04 (unspent). The balance of the OPA (unpaid) which remains with FAO is USD 412,105.
Please provide a summary paragraph on challenges of project implementation consistent with the information reported in section 2 and 3 of the PIR (Max 400 words) (This section will be uploaded to the GEF portal)
The implementation of projects in North Darfur has been hindered by several factors, including ongoing insecurity and conflict, limited financial and institutional resources, and a lack of coordination between government bodies. Additionally, challenges related to access to land and natural resources, as well as the impacts of climate change, have further complicated development efforts. Currently, the PMU is waiting to assume activities, hopefully with the war soon to be finished.
Implementation of Exit Strategy
Has the project developed an Exit Strategy? If yes, please describe the progress to implement it. | No Exit strategy was developed. However, given the on-going conflict/ war in North Darfur with no immediate end in sight, FAO and the government will conduct discussions and explore the possibility of alternative project location in in the safer states
How is the project enhancing institutional capacities to foster country ownership for more durable / sustained results? | The on-going conflict/ war has prevented any institutional capacity strengthening.

## 5. ESS Risk
5. Environmental and Social Safeguards (ESS): risks from the project
Initial ESS Risk Classification (at CEO Endorsement/Approval Stage) | Moderate Risk
New environmental and social risks. | High Risk due to the fighting in North Darfur State New risks: Displacement of people and local communities within the state and to neighbouring countries, reports of deforestation and degradation of vegetation and rangeland.
Progress made towards implementing the Enivronmental and Social Management Plan (ESMP) (only for Moderate and High Risk Projects) | No progress
Grievance Redress Mechanism (GRM) | Not Implemented

## 6. Risks to the Project
6. Risks to the Project
The following table summarizes risks identified in the Project Document and reflects also any new risks identified during the project implementation.
| Type of risk |  | Risk rating11 | Identified in the ProDoc Y/N | Description of Risk | Mitigation measure implemented
1 | Safety & Security |  | High | No | Deterioration of the security situation precluding access to areas of implementation | Have initiated consultations with the HCENR - Higher Council for Environment and Natural Resources to explore various implementation options. Recruited an International consultant on Remote Sensing to work remotely to execute some project tasks
2 | Social |  | High | No | Displacement of local communities | Consultation with HCENR on possible action and Monitoring of the situation
3 | Environmental |  | Moderate | Yes | Deforestation and rangeland disturbances | Monitoring vegetation change is currently underway
Project overall risk rating (Low, Moderate, Substantial or High):
FY2024 rating | FY2025 rating | Comments/reason for the rating for FY2025 and any changes (positive or negative) in the rating since the previous reporting period
Substantial | High | The project risk in North Darfur is extremely high due to the ongoing war and insecurity, which started 15 April 2025. The war has restricted humanitarian access, destroyed infrastructure, and exacerbated food and livelihood insecurity. Due to insecurity, it was difficult for the project to navigate restricted access in the State for any productive community engagement. To mitigate this challenge, the government has recently approved change of project location to Gedaref and Kassala States.
11 Risk ratings means a rating of the overall risk of factors internal or external to the project which may affect implementation or prospects for achieving project objectives. Risk of projects should be rated on the following scale: Low, Moderate, Substantial or High.

## 7. Follow-up on Mid-term review
7. Follow-up on Mid-term review or supervision mission
If the project had an MTR or a supervision mission in 2024, please report on how the recommendations were implemented during this fiscal year as indicated in the Management Response or in the supervision mission report.
MTR or supervision mission recommendations | Measures implemented during this Fiscal Year
Recommendation 1:
Recommendation 2:
Recommendation 3:
Recommendation …
Recommendation…

## 8. Minor project amendments
8. Minor project amendments
Minor amendments are changes to the design or implementation that do not have significant impact on the project objectives or scope, or an increase of the GEF project financing up to 5% as described in Annex 9 of the GEF Project and Program Cycle Policy Guidelines 12. Please describe any minor changes that the project has made under the relevant category or categories and provide supporting documents as an annex to this report if available. (This section will be uploaded to the GEF Portal)
Category of change | Provide a description of the change | Indicate the timing of the change | Approved by
Results framework | No amendment
Components and cost | No amendment
Institutional and implementation arrangements | No amendment
Financial management | No amendment
Implementation schedule | No amendment
Executing Entity | No amendment
Executing Entity Category | No amendment
Minor project objective change | No amendment
Safeguards | No amendment
Risk analysis | No amendment
Increase of GEF project financing up to 5% | No amendment
Co-financing | No amendment
Location of project activity | No amendment
Other minor project amendment (define) | No amendment
12 GEF Council meeting documents, guidelines, project and program cycle policy 2020 update

## 9. Stakeholders' Engagement
9. Stakeholders' Engagement
Please report on progress, challeges, and outcomes on stakeholder engagement (based on the description of the Stakeholder Engagement Plan) included at CEO Endorsement/Approval during this reporting period. (This section will be uploaded to the GEF Portal)
Profile | Stakeholder name | Type of partnership | Progress, results & Challenges on Stakeholder's Engagement
Government Institutions | Higher Council for Environment and Natural Resources (HCENR) | Project Executing Entity Lead for cross sectoral coordination among all relevant Government entities at federal and state levels.) | Stakeholders were involved in the project formulation and were part of the project Inception workshop of the projected and confirmed their commitment. In addition, they are part of the project governance (members of the Project Steering Committee)
Government Institutions | Federal line Ministries | Provide federal assistance, and national logistics | Stakeholders were involved in the project formulation and were part of the project Inception workshop of the projected and confirmed their commitment. In addition, they are part of the project governance (members of the Project Steering Committee)
Government Institutions | State Ministries -North Darfur State | Facilitate and assist in field activities | Stakeholders were involved in the project formulation and were part of the project Inception workshop of the projected and confirmed their commitment. In addition, they are part of the project governance (members of the Project Steering Committee)
Government Institutions | Academic and research institutions | facilitate studies and research | Stakeholders were involved in the project formulation and were part of the project Inception workshop of the projected and confirmed their commitment. In addition, they are part of the project governance (members of the Project Steering Committee)
Government Institutions | Farmers Associations and Unions | Implementation of activities | Stakeholders were involved in the project formulation and were part of the project Inception workshop of the projected and confirmed their commitment. In addition, they are part of the project governance (members of the Project Steering Committee)
Government Institutions | Gum Arabic Producers Association | Implementation of activities | Stakeholders were involved in the project formulation and were part of the project Inception workshop of the projected and confirmed their commitment. In addition, they are part of the project governance (members of the Project Steering Committee)
Government Institutions | SOS Sahel Sudan | Implementation of activities | Stakeholders were involved in the project formulation and were part of the project Inception workshop of the projected and confirmed their commitment. In addition, they are part of the project governance (members of the Project Steering Committee)
Government Institutions | Local associations, (Ewaa Azaayna, Alargoon, Azaytona Societies) | Implementation of activities | Stakeholders were involved in the project formulation and were part of the project Inception workshop of the projected and confirmed their commitment. In addition, they are part of the project governance (members of the Project Steering Committee)
Government Institutions | Herders’ Unions in localities | Implementation of activities | Stakeholders were involved in the project formulation and were part of the project Inception workshop of the projected and confirmed their commitment. In addition, they are part of the project governance (members of the Project Steering Committee)
Government Institutions | Women and youth groups | Implementation of activities | Stakeholders were involved in the project formulation and were part of the project Inception workshop of the projected and confirmed their commitment. In addition, they are part of the project governance (members of the Project Steering Committee)
Private Sector entities | Private Service providers | Facilitation of activities implemintation | Stakeholders were involved in the project formulation and were part of the project Inception workshop of the projected and confirmed their commitment. In addition, they are part of the project governance (members of the Project Steering Committee)
Private Sector entities | Private Entrepreneurs | Facilitation of activities implemintation | Stakeholders were involved in the project formulation and were part of the project Inception workshop of the projected and confirmed their commitment. In addition, they are part of the project governance (members of the Project Steering Committee)
Private Sector entities | Operators of NTFPs value chains | Facilitation of activities implemintation | Stakeholders were involved in the project formulation and were part of the project Inception workshop of the projected and confirmed their commitment. In addition, they are part of the project governance (members of the Project Steering Committee)
Private Sector entities | Banks and micro-finance institutions (e.g. Agricultural Bank of Sudan) | Facilitation of activities implemintation | Stakeholders were involved in the project formulation and were part of the project Inception workshop of the projected and confirmed their commitment. In addition, they are part of the project governance (members of the Project Steering Committee)
Private Sector entities | Sudatel (telecommunication company) | Facilitation of activities implemintation | Stakeholders were involved in the project formulation and were part of the project Inception workshop of the projected and confirmed their commitment. In addition, they are part of the project governance (members of the Project Steering Committee)

## 10. Gender Mainstreaming
10. Gender Mainstreaming
Information on Progress on Gender-responsive measures as documented at CEO Endorsement/Approval in the gender action plan or equivalent (when applicable) during this reporting period. (This section will be uploaded to the GEF Portal)
Category | Yes/No | Briefly describe progress and results achieved during this reporting period.
a. Closing gender gaps in access to and control overal natural resources | No | No progress is made
b. Improving women's participation and decision making | No | No progress is made
c. generating socio-economic benefits or services for women | No | No progress is made
Any other good practices on gender | No | No progress is made

## 11. Knowledge Management
11. Knowledge and Learning Activities
Knowledge activities/products (when applicable), as outlined in Knowledge Management (and Learning) Approach approved at CEO Endorsement/Approval, during this reporting period. (This section will be uploaded to the GEF Portal)
Knowledge management and Learning (KML): Does the project have a KML strategy? | Yes
If YES, what is the implementation progress? In your answer, please describe how the project is fostering knowledge sharing and learning among stakeholders at national and sub-national level. | No
If NO, how does the project identify, collect and document good practices? | No
Please list good practices, including key-technical and/or institutional innovations, from the project thus far. | No
Communication strategy: Does the project have a communication strategy? | No
Please provide a brief overview of the communications successes and challenges this fiscal year. | No
Human-interest story: Please share a human-interest story from your project, focusing on how the project has helped to improve people's livelihoods while contributing to achieving the expected Global Environmental Benefits. Please indicate any Socio-economic Co-benefits that were generated by the project. Include at least one beneficiary quote and perspective, and please also include related photos and photo credits. | No
Please provide links to related website, social media account | No
Please provide a list of publications, leaflets, video materials, newsletters, or other communications assets publised on the web, if any. | No
Please indicate the Communication and/or knowledge management focal point's name and contact detais. | No

## 12. Indigenous & Local Involve.
12. Indigenous Peoples and Local Communites Involvement
Are Indigenous Peoples and local communities involved in the project (as per the approved Project Document)? If yes, please briefly explain.
If applicable, please describe the process and current status of on-going/completed, legitimate consultations to obtain Free, Prior and Informed Consent (FPIC) with the indigenous communities. NA Do indigenous peoples and/or local communities have an active partcipation in the project activities? If yes, briefly describe how. NA

## 13. Co-Financing Table
13. Co-Financing Table
Sources of Co-financing | Name of Co-financer | Type of Co-financing | Amount Confirmed at CEO endorsement/approval (in USD) | Actual Amount Materialized at 30 June 2025 (in USD)
Recipient Government | Higher Council for Environment and Natural Resources (HCENR) | In Kind (Recurrent expenditure) | 700000
Recipient Government | Higher Council for Environment and Natural Resources (HCENR) | In-kind (recurrent expenditure) | 300000
Recipient Government | State Ministry of Agriculture and Animal (North Darfur) | In-kind (recurrent expenditure) | 100000
GEF Agency | FAO | Grants (invested mobilized) | 10000900
GEF Agency | FAO | In-kind (recurrent expenditure) | 200000
Total |  | Total | 11300900 | 0
Please explain any significant changes in project co-financing since CEO Endorsement/Approval, or differences between the pledged and materialized co-financing amounts.

## 14. GEO Location
14. Geo Location Information
This section should be completed ONLY by projects with 1st PIR and in case the geographic coverage of project activities has changed since last reporting period. This information is required by GEF Secretariat in GEF Portal
Are there any changes in the geographic coverage of the project activities since the last PIR report?
Location Name | Latitude | Longitude | Geo Name ID | Location & Activity Description*

## GEF-6&7 LDCF Core Indicators
Core Indicators_LDCF GEF-6 & GEF-7
For GEF-6 & 7 LDC funded projects Please provide cumulative total achieved from the inception, if available in the implementation document
Core Indicator 1 | Total | Male | Fmale | % of women
Total number of direct beneficiaries | 0
Core Indicator 2
Area of land managed for climate resilience (ha) | 0
Core Indicators 3
Total no. of policies/plans that will mainstream climate resilence | 0
Core indicator 4 |  | Male | Female | % of women
Total number of people trained | 0

## Annex
Annex. Monitoring Area-based GEF Core Indicator Commitments and Progress with FERM
The Framework for Ecosystem Restoration Monitoring (FERM), developed by FAO, is the official monitoring platform for tracking global progress and disseminating good practices for the UN Decade of Ecosystem Restoration. The FERM can serve as an integrated GIS-based platform, providing GEF staff and all relevant stakeholders the chance to display the progress of committed versus achieved land under restoration or under improved management for conservation and sustainable use, along with clear results such as the percentage of project achievement. Having a common tracking and monitoring platform allows users to comprehensively assess and report on project progress. A user-friendly dashboard showcasing project results gives stakeholders a clear understanding of the extent to which project targets have been achieved. Projects with area-based GEF Core Indicators (GEF Core Indicators 1-5 and LDCF Core Indicator 2) are encouraged to register in the FERM platform.
Useful links:
• FERM website
• FERM User Guide (PDF)
• FERM YouTube channel
• Email Carmen Morales
26 It also supports countries in reporting areas under restoration for the Kunming-Montreal GBF Target 2 (areas under restoration) for which FAO is the custodian agency.