## Table of Contents
FAO-GEF Project Implementation Report
2025 – Revised Template
Period covered: 1 July 2024 to 30 June 2025
Table of Contents
1. BASIC PROJECT DATA
2. PROGRESS TOWARDS ACHIEVING PROJECT OBJECTIVE(S) (DEVELOPMENT OBJECTIVE)
3. IMPLEMENTATION PROGRESS (IP)
4. SUMMARY ON PROGRESS AND CHALLENGES
5.ENVIRONMENTAL AND SOCIAL SAFEGUARDS (ESS):RISKS FROM THE PROJECT
6. RISKS TO THE PROJECT
7. FOLLOW-UP ON MID-TERM REVIEW OR SUPERVISION MISSION
8. MINOR PROJECT AMENDMENTS
9. STAKEHOLDERS' ENGAGEMENT
10. GENDER MAINSTREAMING
11. KNOWLEDGE MANAGEMENT ACTIVITIES
12. INDIGENOUS PEOPLES AND LOCAL COMMUNITIES INVOLVEMENT
13. CO-FINANCING TABLE
14. GEO LOCATION INFORMATION
Annex. Monitoring Area-based GEF Core Indicator Commitments and Progress with FERM
IMPORTANT DISCLAIMER:
The final version of this PIR will be submitted to the GEF Secretariat.
The report will then be publicly available on the GEF website (click here).
Sensitive information should be submitted in Annex to be uploaded separately.
In such cases, please contact faogef-pir-support@fao.org for guidance.

## 1. Basic project data
1. Basic Project Data
General Information
Region: | Near East and North Africa (RNE)
Country(ies): | Jordan
Project Title: | Achieving land degradation neutrality targets through restoration and sustainable management of degraded land in Northern Jordan
FAO Project Symbol: | GCP /JOR/023/GFF
GEF ID: | 10528
Type of Trust Fund(s): | GFF
GEF Focal Area(s): | Land Degradation
Project Executing Partners: | Royal Scientific Society (RSS)
Initial project duration (years): | 4
Project Dates
GEF CEO Endorsement Date: | 2022-04-07
Actual Agency Approval Date | 2022-05-19
Project Implementation Start Date/EOD: | 2023-01-19
First Disbursement Date | 2023-05-31
Planned Project End Date/NTE1: | 2027-01-18
Revised project implementation End date (if approved)2: | N/A
Actual Completion Date: | N/A
Expected Financial Closure Date: | 2028-01-18
Funding
GEF Grant Amount (USD): | 4000000
Total GEF grant delivery (as of June 30, 2025 (USD): | 1928999.72
Total Co-financing amount (USD)3: | 29045442
Total estimated co-financing materialized as of June 30, 20254: | 10171953
M & E Milestones
Date of Last Project Steering Committee (PSC) Meeting: | July 10th 2023
Expected Mid-term Review date5:
Actual Mid-term review date (if already completed): | 2025-04-18
Expected Terminal Evaluation Date6: | 2026-07-18
Overall ratings
Overall rating of progress towards achieving objectives/outcomes (cumulative): | Moderately Satisfactory (MS)
Overall implementation progess rating: | Moderately Satisfactory (MS)
Overall risk rating: | Low
Status
Implementation Status (1st PIR, 2nd PIR, etc. Final PIR): | 2nd PIR
1 Date that was originally foreseen at the project’s operationalization and indicated in FPMIS. 2 If NTE extension has been requested and approved by the FAO-GEF Coordination Unit. 3 This is the total amount of co-financing as included in the CEO Document/Project Document. 4 Please refer to the Section 13 of this report where updated co-financing estimates are requested and indicate the total co-financing amount materialized. 5 The Mid-Term Review (MTR) should take place after the 2nd PIR, around half-point between EOD and NTE. The MTR report in English should be submitted to the GEF Secretariat within 4 years of the CEO Endorsement date. 6 The Terminal Evaluation date should be discussed with OED 6 months before the project’s NTE date.
Project Contacts
Contact | Name, Title, Division/Institution |  | E-mail
Project Coordinator (PC) | Abdullah Alkloub, RSS project coordinator |  | abdullah.kloub@rss.jo
Budget Holder (BH) | Assaf Nabil, FAO Representation in Jordan |  | Nabil.Assaf@fao.org
GEF Operational Focal Point (GEF OFP) | Mr. Marwan Al-Refai Secretary General Ministry of Planning and International Cooperation |  | marwan.al-refai@mop.gov.jo
Lead Technical Officer (LTO) | Haddad Fidaa Fawwaz Iskandar, Senior Programme Officer, RNETD - Outposted Technical Officers Group |  | Fidaa.Haddad@fao.org
GEF Technical Officer (GTO) | Anika Seggel, FAO GEF Coordination Unit in FAO HQ |  | Anika.Seggel@fao.org
Key Project Management Unit Personnel
Please indicate the composition of the PMU as per the Terms of Reference in the ProDoc. If any new position was establised during the project implementation, please insert it accordingly.
Position planned (as per ProDoc) | Position filled (Yes/No) | Start date, Name, Contact |  | Comments
project coordinator | Yes | May/2023 Abdullah Alkloub Abdullah.kloub@rss.jo
Project Finance & Administrative Assistant (full-time) | Yes | March/2023 Ahmed Abughoush Ahmed.Abughoush@rss.jo
Local Regenerative Ag. Experts | Yes | March/2023 Mohammad Mashatleh mohammad.mashatleh@rss.jo |  | Resigned Will be filled when needed
Irbid Governate community development facilitator | Yes | 2023-03-01 |  | ReSigned on Jan. 2025 New one hired on July 2025
Aljoun Governate community development facilitator | Yes | Feb./2024 Khadeejeh Alatyat khadeejeh.atyat@rss.jo
Mafraq Governate community development facilitator | Yes | Feb./2023 Qusai Izraiqat qusai.izraiqat@rss.jo
M&E officer | Yes | July/2024 Nanci Alziq NANCI.ALZIQ@rss.jo |  | full time basis

## _Calc (hidden)
Rating text | Score
Highly Unsatisfactory (HU) | 1
Unsatisfactory (U) | 2
Moderately Unsatisfactory (MU) | 3
Moderately Satisfactory (MS) | 4
Satisfactory (S) | 5
Highly Satisfactory (HS) | 6
Unknown | 0
Not Rated | 0
for DevScore
|  | Person | PM/Coord | Budget Holder | LTO | GEF OFP | GTO
|  | Weight % | 20 | 25 | 25 | 0 | 30
For ImpScore
|  | Person | PM/Coord | LTO | GEF OFP | GTO
|  | Weight % | 25 | 35 | 0 | 40
Once you've filled in 2. Progress towards outcomes & 3. Implementation Progress
Please double click and press enter on Cells D20 and D21 |  | 4
2

## Countries (hidden)
Select Country
Afghanistan
Åland Islands
Albania
Algeria
American Samoa
Andorra
Angola
Anguilla
Antarctica
Antigua and Barbuda
Argentina
Armenia
Aruba
Australia
Austria
Azerbaijan
Bahamas
Bahrain
Bangladesh
Barbados
Belarus
Belgium
Belize
Benin
Bermuda
Bhutan
Bolivia (Plurinational State of)
Bonaire, Sint Eustatius and Saba
Bosnia and Herzegovina
Botswana
Bouvet Island
Brazil
British Indian Ocean Territory
British Virgin Islands
Brunei Darussalam
Bulgaria
Burkina Faso
Burundi
Cabo Verde
Cambodia
Cameroon
Canada
Cayman Islands
Central African Republic
Chad
Chile
China
China, Hong Kong Special Administrative Region
China, Macao Special Administrative Region
Christmas Island
Cocos (Keeling) Islands
Colombia
Comoros
Congo
Cook Islands
Costa Rica
Côte d’Ivoire
Croatia
Cuba
Curaçao
Cyprus
Czechia
Democratic People's Republic of Korea
Democratic Republic of the Congo
Denmark
Djibouti
Dominica
Dominican Republic
Ecuador
Egypt
El Salvador
Equatorial Guinea
Eritrea
Estonia
Eswatini
Ethiopia
Falkland Islands (Malvinas)
Faroe Islands
Fiji
Finland
France
French Guiana
French Polynesia
French Southern Territories
Gabon
Gambia
Georgia
Germany
Ghana
Gibraltar
Greece
Greenland
Grenada
Guadeloupe
Guam
Guatemala
Guernsey
Guinea
Guinea-Bissau
Guyana
Haiti
Heard Island and McDonald Islands
Holy See
Honduras
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Isle of Man
Israel
Italy
Jamaica
Japan
Jersey
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People's Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Martinique
Mauritania
Mauritius
Mayotte
Mexico
Micronesia (Federated States of)
Monaco
Mongolia
Montenegro
Montserrat
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands (Kingdom of the)
New Caledonia
New Zealand
Nicaragua
Niger
Nigeria
Niue
Norfolk Island
North Macedonia
Northern Mariana Islands
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Pitcairn
Poland
Portugal
Puerto Rico
Qatar
Republic of Korea
Republic of Moldova
Réunion
Romania
Russian Federation
Rwanda
Saint Barthélemy
Saint Helena
Saint Kitts and Nevis
Saint Lucia
Saint Martin (French Part)
Saint Pierre and Miquelon
Saint Vincent and the Grenadines
Sint Eustatius and Saba
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Sint Maarten (Dutch part)
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
South Georgia and the South Sandwich Islands
South Sudan
Spain
Sri Lanka
State of Palestine
Sudan
Suriname
Svalbard and Jan Mayen Islands
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
Timor-Leste
Togo
Tokelau
Tonga
Trinidad and Tobago
Tunisia
Türkiye
Turkmenistan
Turks and Caicos Islands
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States Minor Outlying Islands
United States of America
United States Virgin Islands
Uruguay
Uzbekistan
Vanuatu
Venezuela (Bolivarian Republic of)
Viet Nam
Wallis and Futuna Islands
Western Sahara
Yemen
Zambia
Zimbabwe

## TypeofTrustFund (hidden)
Type of Trust Fund
Capacity-building Initiative for Transparency (CBIT)
Global Biodiversity Framework Fund (GBFF)
Global Environment Facility Trust Fund (GFF)
Least Developed Countries Fund (LDCF)
Special Climate Change Fund (SCCF)
Small Grants Program (SGP)

## FocalArea (hidden)
Focal Area
Multi Focal Area
Biodiversity
Chemicals and Waste
Chemicals/PoPs
Climate Change
Climate Change Adaptation
Climate Change Mitigation
International Waters
Land Degradation

## 2. Progress towards outcomes
2. Progress towards Achieving Project Objective(s) (Development objective)
(All inputs in this section should be cumulative from project start, not annual)
Please indicate the project’s main progress towards achieving its objective(s) and the cumulative level of achievement of each outcome since the start of project implementation.
Project or Development Objective | Outcomes | Outcome indicators | Baseline | Mid-term Target | End-of-project Target | Cumulative progress level at 30 June 2025 | % of cumulative progress | Progress rating
Achieving land degradation neutrality targets through restoration and sustainable management of degraded land in Northern Jordan | Component 1 Enabling Environment for Land Degradation Neutrality (LDN) planning and monitoring
| Outcome 1.1. Land use planning and monitoring frameworks strengthened at national and sub-national levels to support LDN | Number of LDN baseline and monitoring system operational |  | system tested | system operational | "The recruitment process for all the required consultants to support the implementation of this component is still ongoing and has not yet been finalized and this had caused delays in the implementation of the activities. Completion of the recruitment is anticipated by September 2025. No baseline verification has been conducted to date. Following discussions and feedback from FAO staff and the LTO in October 2024, the OP began initial planning for the baseline study. However, implementation has not yet commenced. The baseline assessment is now expected to begin in August 2025. Despite this, RSS with the support from FAO international consultants have developed the updated the Land Degradation Neutrality Decision Support System based on the three global LDN indicators. Their contributions included revising and updating the application based on available open-source datasets, adding new geospatial layers, and improving the overall user interface to ensure a more intuitive and functional design. Key stakeholders have been trained and actively involved in the development of the updated LDN-DSS. A three-day technical workshop was organized from 26 to 28 November 2024, bringing together 43 participants from various sectors, including government institutions, academia, and local administrations. The training focused on the Decision Support System (DSS) integrated into the LDN platform. The DSS training proved to be highly impactful, significantly enhancing participants' abilities to make informed, data-driven decisions. It also strengthened their technical competencies in spatial analysis and data management. Moreover, the workshop fostered intersectoral collaboration and promoted the integration of local knowledge into structured, technology-driven systems. Importantly, the training also introduced participants to tools for scenario analysis and policy development, thereby supporting long-term planning and monitoring of land resources. Furthermore, following comprehensive field visits to the 57 pre-selected intervention sites, a rapid assessment was conducted to evaluate land cover, existing human land uses, and the potential for targeted interventions. Based on the findings, and as part of the 2024 work plan the project has commenced the implementation of DLDD mitigation and restoration activities across 8 pilot sites located within three governorates—specifically, one sites in Irbid, one in Mafraq, and 6 in Ajloun. This work is being carried out in close collaboration with the Ministry of Agriculture. The interventions currently underway encompass two main categories. The first includes forest restoration measures such as the construction of terraces, the establishment of contour lines, and the planting of native seeds. The second focuses on rangeland rehabilitation, with activities including the development of contour lines and the planting of Atriplex halimus shrubs to support soil stabilization and improve vegetation cover. Joint technical field visits between the Royal Scientific Society (RSS) and the Ministry of Agriculture are ongoing, with the objective of finalizing technical specifications and determining the most effective implementation modalities. Although the project experienced initial delays in launching these activities, it remains on track to achieve the expected outcomes. However, in light of the revised timeline, a no-cost extension is currently under consideration to ensure the full and effective completion of planned interventions." |  | Moderately Unsatisfactory (MU)
|  | Number of LDN hot and bright spots confirmed | 0 | hot and bright spots identified | hot and bright spots confirmed |  |  | Moderately Unsatisfactory (MU)
|  | Number of LDN bright spots confirmed | [5 empty] | Moderately Unsatisfactory (MU)
|  | Number of LDN hot spots confirmed | [5 empty] | Moderately Unsatisfactory (MU)
|  | ha under SLM that LDN are under the ‘avoided’ category of the hierarchy of responses | [5 empty] | Moderately Unsatisfactory (MU)
|  | # ha under avoid category - total | 0 | 2000 | 10000 |  |  | Moderately Unsatisfactory (MU)
|  | # ha under avoid category - forest |  | 500 | 2000 |  |  | Moderately Unsatisfactory (MU)
|  | # ha under avoid category - grassland |  | 1500 | 8000 |  |  | Moderately Unsatisfactory (MU)
|  | ha of land restored | [5 empty] | Moderately Unsatisfactory (MU)
|  | # ha under restored category - total | 0 | 300 | 750 | 159 | 21% | Moderately Satisfactory (MS)
|  | # ha under restored category - forest |  | 100 | 250 | 59 | 24% | Moderately Satisfactory (MS)
|  | # ha under restored category - grassland |  | 200 | 500 | 100 | 20% | Moderately Satisfactory (MS)
|  | Mtons CO2eq (EX ACT) |  | 200,000 | 419,006 |  |  | Moderately Satisfactory (MS)
| Outcome 1.2. LDN mainstreamed in national policy/regulatory and institutional frameworks and land use planning processes | LDN principles integrated into the national frameworks |  | 1 | 3 | A national consultant was engaged by the implementing partner to undertake a comprehensive gap analysis of national policies and regulations pertaining to land resources, forestry, and agriculture. The scope of the study includes a focused review of land use planning frameworks, climate change legislation, and related policies, strategies, and regulatory instruments. However, the implementation of this activity has encountered significant delays, and the study has not yet been finalized. The project has initiated a productive and strategic dialogue with the National Committee to Combat Desertification under the Ministry of Environment. This committee is envisioned to serve as a key platform for engaging relevant stakeholders in efforts to address desertification, land degradation, and drought (DLDD) at the national level. In addition to facilitating stakeholder coordination, the committee will also play a central role in building capacity on the concept of Land Degradation Neutrality (LDN), as well as promoting knowledge exchange and experience-sharing with neighboring countries facing similar challenges. As part of this process, a draft Terms of Reference (ToR) for the Desertification, Land Degradation, and Drought National Committee—under the framework of the United Nations Convention to Combat Desertification (UNCCD)—was developed in June 2025. The draft ToR outlines the committee’s mandate, structure, and operational modalities, and will serve as the foundation for institutionalizing its role in supporting national implementation of the UNCCD objectives and fostering regional collaboration. |  | Moderately Satisfactory (MS)
|  | Number of Inter-sectoral coordination mechanisms on SLM, DLDD and LDN |  |  | 2 | 1 | 50% | Moderately Satisfactory (MS)
|  | Number of knowledge product and training/awareness raising materials (which are gender sensitive in content and form) on LDN principles and their application to land planning procedures | 0 |  | 1 | A documentary video has been produced to showcase the restoration activities implemented in collaboration with the Ministry of Agriculture. The video highlights the project's key interventions, achievements, and field-level impact, serving as a visual record of progress made in combating land degradation and promoting sustainable land management practices. To enhance public awareness and increase the project's visibility, the video has been disseminated through various social media platforms and published on official websites. This outreach aims to inform a broader audience, including national stakeholders, development partners, and the general public, about the project's objectives and accomplishments. | 50% | Moderately Satisfactory (MS)
| Outcome 1.3. Enhanced capacity at national and sub-national levels to support the achievement of LDN in Ajloun, Irbid and Mafraq Governorates | Governorate staff trained on Monitoring of status of land and level of land degradation - total |  | 5 | 15 |  |  | Moderately Satisfactory (MS)
|  | Governorate staff trained on Monitoring of status of land and level of land degradation - male |  | 4 | 12 |  |  | Moderately Satisfactory (MS)
|  | Governorate staff trained on Monitoring of status of land and level of land degradation - Female |  | 1 | 3 |  |  | Moderately Satisfactory (MS)
|  | Number of people with enhanced capacity in LDN and SLM at national and sub-national level - Total |  | 45 | 90 |  |  | Moderately Satisfactory (MS)
|  | Number of people with enhanced capacity in LDN and SLM at national and sub-national level - Male |  | 23 | 45 |  |  | Moderately Satisfactory (MS)
|  | Number of people with enhanced capacity in LDN and SLM at national and sub-national level - Female |  | 22 | 45 |  |  | Moderately Satisfactory (MS)
|  | Number of knowledge products and training/awareness raising materials (which are gender sensitive in content and form) on SLM and LDN |  | 2 | 3 |  |  | Moderately Satisfactory (MS)
Component 2: Demonstrating the LDN approach and scaling out SLM practices and approaches in selected landscapes in the Ajloun, Irbid and Mafraq Governorates
| Outcome 2.1. Improved Land Cover/Management, Land Productivity, and SOC through the application of SLM/DLDD practices and approaches in selected landscapes of the Aljoun, Irbid and Mafraq Governates | Number of producers trained through FFS or existing farmer organizations - total | 0 | 1,250 | 2,250 | 100 Between late 2024 and early 2025, the project carried out several key community engagement and capacity-building activities across the target governorates of Ajloun, Mafraq, and Irbid. Four awareness-raising workshops were conducted in collaboration with local CBOs to promote the SLM approach. These workshops, attended by 123 participants (82 males and 41 females), also served as platforms for gathering local input on participatory methods to support project implementation. In parallel, five FFS were established and facilitated by the Ministry of Agriculture, engaging 100 beneficiaries (59 males and 41 females) in hands-on training focused on olive cultivation, vegetables, and potato farming. These trainings are ongoing and provide practical skills to enhance sustainable agricultural practices. Additionally, efforts are underway to rehabilitate a Ministry of Agriculture nursery for the multiplication of native forest and pasture plant species using seeds collected through FFS activities. | 4.4% | Moderately Satisfactory (MS)
|  | Number of producers trained through FFS or existing farmer organizations- male |  | 625 | 1,125 | 59 | 5.2% | Moderately Satisfactory (MS)
|  | Number of producers trained through FFS or existing farmer organizations - female |  | 625 | 1125 | 41 | 3.6% | Moderately Satisfactory (MS)
|  | number of ha under SLM that meet LDN criteria (Total) |  |  | 15,000
|  | number of ha croplands |  |  | 10,000
|  | number of ha mixed land cover types |  |  | 5,000
|  | number of ha of land restored (Total) |  |  | 2,000
|  | Mtons CO2eq (EX ACT) |  |  | 2,120,040
|  | Number of Direct beneficiaries - Total |  | 2,500 | 10,000
|  | Number of Direct beneficiaries - Male |  | 1,250 | 5,000
Number of Direct beneficiaries - Female
| Outcome 2.2. Increased investments in sustainable land management to achieve LDN | Number of LDN Action Plans developed |  | 1 | 3 | An LD expert was selected and to be hired during July 2025, will be working in consultation with local communities to develop land restoration plans per each of the targeted landscapes. |  | Moderately Satisfactory (MS)
|  | Number of value-chains strengthened, resulting in increased revenue of local population (at least two target gender sensitive value chains) |  | 2 | 4 | The project has engaged four specialized consultants to support the development of interventions along the four selected value chains: olive, beekeeping, vegetables, and dairy products. One of the primary responsibilities assigned to each consultant was to conduct a comprehensive training needs assessment for their respective value chain. Based on these assessments, each consultant has also developed a proposed training program tailored to address identified gaps and build the capacities of relevant stakeholders. The training needs assessment reports have been submitted and are currently undergoing review and evaluation by the project team. These training programs are expected to inform the capacity-building component of the ALDNT project. Meanwhile, the broader value chain analysis for each sector is still in progress. This component, which will provide in-depth insight into bottlenecks, opportunities, and market dynamics, is scheduled for completion by August 2025. |  | Moderately Satisfactory (MS)
|  | Number of small-holders with strengthened livelihoods and sources of income - Total |  | 1,250 | 2,500 |  |  | Moderately Satisfactory (MS)
|  | Number of small-holders with strengthened livelihoods and sources of income - Male |  | 625 | 1,250 |  |  | Moderately Satisfactory (MS)
|  | Number of small-holders with strengthened livelihoods and sources of income - Female | [5 empty] | Moderately Satisfactory (MS)
|  | Number of people that receive Value Chain training and support (Total) |  | 50 | 125 |  |  | Moderately Satisfactory (MS)
|  | Number of people that receive Value Chain training - Total |  | 25 | 62 |  |  | Moderately Satisfactory (MS)
|  | Number of people that receive Value Chain training - male |  | 13 | 31 |  |  | Moderately Satisfactory (MS)
|  | Number of people that receive Value Chain training - female |  | 12 |  |  |  | Moderately Satisfactory (MS)
|  | Number of people that receive Value Chain support - Total |  | 25 | 63 |  |  | Moderately Satisfactory (MS)
|  | Number of people that receive Value Chain support - male |  | 12 | 31 |  |  | Moderately Satisfactory (MS)
|  | Number of people that receive Value Chain support - female |  | 13 |  |  |  | Moderately Satisfactory (MS)
Component 3: Project Monitoring, Evaluation and lesson learned
| Outcome 3.1. Knowledge management, M&E and lessons learned disseminated | Functioning M&E system and GEBs and co-benefits established | 0 |  | 1 | This activity is currently facing critical delays due to challenges in the recruitment of key consultants, specifically a Gender Specialist and a specialized national expert in Monitoring and Evaluation (M&E). Despite initial efforts, the required expertise has not yet been secured, which has impacted the timely implementation of related project components. To address this issue and attract a wider pool of qualified candidates, the tender for both positions was re-announced in May 2025 in both Arabic and English. The re-advertisement aims to enhance outreach and ensure transparency and competitiveness in the selection process. Recruitment efforts are ongoing, and the project team remains committed to filling these essential roles as soon as possible to support effective implementation and oversight. |  | Moderately Satisfactory (MS)
|  | Functioning LDN reporting to the UNCCD | [5 empty] | Moderately Satisfactory (MS)
|  | Lessons learned on SLM and LDN mainstreamed in 3 Governorate plans |  |  | 3 |  |  | Moderately Satisfactory (MS)
|  | Lessons learned on SLM and LDN mainstreamed in the national development plan |  |  | 1 |  |  | Moderately Satisfactory (MS)
|  | Best practices and lessons learned summarized and organized in a framework for scaling-up in other regions | [5 empty] | Moderately Satisfactory (MS)
Average Cumulative progress toward outcomes (%) | Time elapsed since project start/EOD vs Planned Project End Date | % of delivery
22.27% | 65.96% | 48.22%
Development Objective (DO) Ratings, and Overall Assessment
Please note that the overall DO ratings should be substantiated by evidence and progress reported above. The ratings and comments should reflect the overall progress of results since project start
| FY2025 Development Objective rating¹ | Project Manager/ Coordinator (RSS) | Budget Holder | Lead Technical Officer13 | GEF Operational Focal Point | GEF Technical Officer (GTO)
|  | Moderately Satisfactory (MS) | Moderately Satisfactory (MS) | Moderately Satisfactory (MS) |  | Moderately Satisfactory (MS)
| Comments/reasons¹² justifying the ratings for FY2025 and any changes (positive or negative) in the ratings since the previous reporting period | The project has faced allot of delays, especially the theme of the project is new, and there are not many consultants who have the needed experience, yet the project team have developed the TORs for most of the services needed and signed the agreement with Ministry of Agriculture. the RSS procurment procedures are very long and time consuming that need to shortend to enhance the project implemenation FAO also have appointed a lead officer to follow up on the project activities and implementation. The project needs more Communication with other projects that were to cofinance its activities to ensure the project reach it is intended targets | The project is making steady progress in recovering from initial delays, with important technical activities and pilot interventions now underway. Although earlier implementation was hindered by delays mainly in consultants recruitments, recent developments mark a positive shift. The recent progress demonstrated positive commitment to advancing the LDN framework through capacity building, training, and improved coordination. Additionally, the formalized partnership with the Ministry of Agriculture and progress on the LDN Decision Support System (DSS) are promising milestones that lay the groundwork for accelerating implementation in the next phases. | The project has made steady but uneven progress. While there have been delays in consultant recruitment, baseline assessment, and policy studies that have limited the overall pace and impact so far, important technical activities and pilot interventions have begun. The partner has also shown clear commitment to updating and applying the LDN framework, investing in training and improving coordination to strengthen implementation moving forward |  | Ever since the last PIR it seems that the cose collaboration between FAO Jordan and RSS is producing increasingly effecetive outcomes. Measured by the deliverables and progress reported, the progress rating is moderately satisfactoary (as we are still lagging behind the original schedule).
Measures to address MS, MU, U and HU ratings on Section 2 above
Outcome |  | Action(s) to be taken |  | By whom? |  | By When?
Outcome 1.1. Land use planning and monitoring frameworks strengthened at national and sub-national levels to support LDN |  | Strengthen the participatory approach and stronger involvement of target communities in all stages Implement HHs survey (i.e. RIMA, SHARP) Identify and integrate local indicators (adding socio-economic focus) |  | RSS |  | by september 2025
Outcome 1.2: LDN mainstreamed in national policy/regulatory and institutional frameworks and land use planning processes |  | fasten the gap analysis of national laws and regulations and explore synergies with the Jordan target setting 2 and possible synergies and cofuding with MOENV Develop master plan for the 16 basins based on the baseline assessment, HHs survey and through the stakeholder mapping exercise and present it to Government and development partners |  | RSS |  | By august 2025
Outcome 1.3. Enhanced capacity at national and sub-national levels to support the achievement of LDN in Ajloun, Irbid and Mafraq Governorates |  | project revision to allow the identification and contracting of a new partner to support RSS the capacity building component |  | RSS and FAO |  | By august 2025
Outcome 2.1: Improved Land Cover/Management, Land Productivity, and SOC through the application of SLM/DLDD practices and approaches in selected landscapes of the Irbid, Mafraq and Ajloun Governorates |  | revise the strategy to reach higher number of FFS beneficiaries despite the budget limitations. improve the monitoring and the quality of the FFS up to FAO standards |  | RSS and FAO |  | By october 2025
Outcome 2.2: Increased investments in sustainable land management to achieve LDN |  | fasten the VC studies from the constultants and strenghten the community involvement and strenghten the linkages of this outcome to the results of the baseline (in outcome 1.1). The result from the HHs survey (SHARP or RIMA) and local validation workshops along with the remote sensing maps can be used for validation/triangulation of data collected to define the needed activities under the selected value chains. |  | RSS |  | by september 2025
Outcome 3.1: Knowledge management, M&E and lessons learned disseminated |  | fasten the recruitment of the needed consultants (communication, M&E and gender) by RSS implement the MTR |  | RSS FAO |  | By august 2025 October 2025
7 Some indicators may not identify mid-term targets at the design stage (refer to approved results framework) therefore this column should only be filled when relevant. 8 Use GEF Secretariat required six-point scale system: Highly Satisfactory (HS), Satisfactory (S), Moderately Satisfactory (MS), Moderately Unsatisfactory (MU), Unsatisfactory (U), and Highly Unsatisfactory (HU).

## 3. Implementation Progress
3. Implementation Progress (IP)
(Please indicate progress achieved during this FY as per the Implementation Plan/Annual Workplan)
Outcomes and outputs | Indicators (as per the logical framework) |  | Main achievements in the last 12 months (please DO NOT repeat results reported in previous year PIR) |  |  | Describe any variance 9 in delivering outputs
Component 1: Enabling Environment for Land Degradation Neutrality (LDN) planning and monitoring
Outcome 1.1 Land use planning and monitoring frameworks strengthened at national and sub-national levels to support LDN
Output.1.1.1: The baseline measured by a set of three global LDN indicators (Land Cover, Land Productivity and Soil Organic Carbon (SOC)) and land degradation status in various land use types (e.g. forest, grassland) in demonstration landscapes verified | Monitoring approach developed | Approved monitoring approach | The OP, RSS, with technical support from two FAO international experts specialized in GIS and the Land Degradation Neutrality Decision Support System (LDN-DSS), undertook a comprehensive review and upgrade of the LDN monitoring application previously developed by FAO. The enhancements included the integration of open-source spatial datasets, the addition of new geospatial layers, and a significant improvement of the user interface to ensure greater functionality and user-friendliness. In parallel, ToRs were developed for the recruitment of a Gender Expert and a Land Tenure Expert. These roles are intended to support the integration of gender-sensitive and conflict-sensitive analyses into the project’s design, as well as the inclusion of nationally relevant indicators in the LDN monitoring framework. Due to initial recruitment challenges, tenders were re-announced in May 2025 in both Arabic and English in an effort to attract qualified national experts in Land Degradation Neutrality (LDN) and Geographic Information Systems (GIS). During the LTO technical mission in October 2024, it was agreed that additional baseline studies would be necessary to strengthen the project’s evidence base. These include SHARP (Self-evaluation and Holistic Assessment of climate Resilience of farmers and Pastoralists), gender analysis, and conflict sensitivity assessments for each of the 16 targeted drainage basins. The outcomes of these studies will contribute to the identification of localized indicators that will be integrated into the national LDN monitoring system. In response, RSS has initiated the drafting of ToRs for these studies and has begun the procurement process to engage a specialized service provider for their implementation.
| Ha covered in baseline monitoring approach | 107571
Number and type of data sources
| Number of data sources | 3
| Type of data sources | 3
Output 1.1.2: Effective approach for monitoring three global LDN indicators (and potentially other participatory field indicators) and land degradation status identified and integrated into the existing national and sub-national monitoring systems | Prototype Monitoring system developed | The LDN monitoring system validated key stakeholders | This will be implemented after the baseline survey envisioned in output 1.1.1.
| Number of stakeholders and institutions who participate in development of LDN framework | 10
| Number of existing land-based monitoring systems that integrate LDN principles and metrics into their analysis | 1
| Number of national indicators incorporated into the system to reinforce and contextualised LDN monitoring | 10
Output 1.1.3: Decision support system (DSS) based on the three global LDN indicators developed, piloted in the Irbid, Mafraq and Ajloun Governorates, calibrated, and scaled up to all of Jordan | modified and improved DSS |  | Development of the Land Degradation Neutrality Decision Support System (LDN DSS) and Strengthening National Capacities in Jordan As part of the efforts to advance Jordan’s capacity in achieving and monitoring Land Degradation Neutrality (LDN), a virtual workshop was organized from 26 to 28 November 2024, engaging 43 participants representing a wide range of stakeholders, including academic institutions, local administrations, and relevant national agencies. The workshop aimed to build the technical competencies of participants in using the Jordan LDN Decision Support System (LDN DSS) and in understanding the methodology for mapping land degradation, with specific focus on Sustainable Development Goal (SDG) Indicator 15.3.1 (the proportion of land that is degraded over total land area). The training enhanced practical skills in spatial data analysis, mapping of degradation processes, and scenario planning. Participants gained a better understanding of essential datasets required for environmental and land degradation assessments, identifying slope data, land cover/use maps, salinity, and soil maps as critical resources. They also recognized data sources such as the Royal Geographic Center and the Ministry of Agriculture, demonstrating improved capacity to identify data gaps and potential national providers. The workshop also functioned as a platform for evaluating existing stakeholder monitoring systems and capabilities, gathering relevant data, and identifying ways to strengthen and harmonize LDN monitoring mechanisms. Field-based mapping activities allowed participants to link theoretical knowledge with observed on-the-ground changes such as overgrazing and urban expansion. Participants were further asked to complete a structured survey on observed degradation drivers and to propose related actions, as part of an exercise in translating local knowledge into spatial data systems. Through interdisciplinary engagement, the training fostered cross-sector collaboration, promoting the integration of scientific, institutional, and local knowledge into a unified monitoring system. The emphasis on participatory methods supported dialogue among academic, governmental, and NGO stakeholders and helped define appropriate legend classes, data sources, and transition matrices for mapping land cover and productivity changes. To institutionalize the process, official letters were sent to nine national organizations requesting nominations to form the project’s LDN DSS Technical Committee. To date, five institutions—Jordan University of Science and Technology (JUST), Royal Botanic Garden (RBG), Department of Statistics (DOS), International Union for Conservation of Nature (IUCN), and the Hashemite Fund for the Development of the Jordanian Badia—have submitted nominations. Responses from the remaining institutions, including NARC, ICARDA, RSCN, and MOA, are still pending.
| Number of stakeholders and institutions who participate in LDN DSS development | 10
Number of data layers in DSS
| Governates covered in DSS | 5
| Ha covered in DSS | 107571
output 1.1.4.: Desertification, Land Degradation and Drought (DLDD) activities integrated into the LDN DSS and tested on target landscapes in the Irbid, Mafraq, and Ajloun Governorates |  | The project has tested the DSS for the pilot landscape activities. | DLDD Activities Implementation and Coordination a) Recruitment of DLDD Activities Consultant In November 2024, the project engaged a DLDD Activities Consultant to provide technical support in reviewing project documentation and updating the workplan. The consultant also actively contributed to discussions with the FAO focal point, particularly concerning proposed amendments to the workplan to enhance alignment with evolving project needs and implementation priorities. b) Workshops on DLDD Activities and Participatory Approaches To support the effective implementation of DLDD interventions within pilot landscapes, the project organized three regional workshops in Ajloun, Irbid, and Mafraq. Conducted by the Royal Scientific Society (RSS) in coordination with the DLDD expert, these workshops brought together key stakeholders, including representatives from government institutions, NGOs, and community-based organizations (CBOs). The workshops aimed to strengthen multi-stakeholder collaboration, promote knowledge sharing, and build technical capacities to address DLDD-related challenges. Thematic discussions focused on a range of sustainable land management measures, including water harvesting, afforestation, soil restoration, rangeland rehabilitation, and the use of treated wastewater. These interventions are consistent with the project's strategic objectives of enhancing land productivity, improving water efficiency, and strengthening the resilience of vulnerable communities. Additionally, a national stakeholder consultation workshop was convened on 5 May 2025 in Amman. This event marked a significant milestone in Jordan’s progress toward achieving Land Degradation Neutrality (LDN). It gathered representatives from government, academia, civil society, and international partners to align national efforts through science-based, community-centered approaches. The workshop resulted in the validation of Jordan’s LDN targets and explored their integration into national frameworks, including the Biodiversity Strategy, Climate Adaptation Plan, and the Agricultural and Water Strategies. The event also facilitated the establishment of an LDN Expert Group and the restructuring of the National Committee to Combat Desertification, now co-led by the Ministries of Agriculture and Environment. The workshop emphasized inclusivity, with a focus on engaging women, youth, and marginalized groups. Participants expressed a shared commitment to advancing GIS, AI-based monitoring, and restoration practices, reaffirming national resolve for achieving LDN by 2030. c) Coordination with the Ministry of Agriculture (MoA) Following the signing of a formal agreement with the MoA in March 2024, RSS submitted an official request to the Ministry for the nomination of a focal point to coordinate implementation. A coordination meeting held in May 2024 facilitated the review of initial site assessments and planning of technical interventions across the themes of forestry, pasture rehabilitation, and land reclamation. Field-Level Implementation (Second Half of 2024): Forests Restoration Activities: Restoration efforts were undertaken across sites in Ajloun, Irbid, and Mafraq governorates. In Ajloun, six sites in Rajeb and Kufranjah (47 hectares) were restored, with 5,762 meters of terracing and 10,760 meters of contour lines established. Native seed planting included: 3 kg of carob, 500 kg of oak, 15 kg each of sidr and sumac, and 60 kg of neem. In Dowgarah (Irbid), 12 hectares were rehabilitated, with 1,500 meters of terracing, 2,700 meters of contour lines, and planting of 5 kg carob and 100 kg oak. Rangeland Restoration Activities: In the Surrah site (A53) in Mafraq, covering 451 hectares, 60 hectares were prepared for planting through digging of planting holes. Additionally, 102.7 meters of contour lines were constructed and 18,200 Atriplex halimus shrubs were planted to support vegetation recovery. Monitoring Activities: A total of 12 joint field monitoring visits were conducted in partnership with MoA to follow up on the implementation and progress of the rehabilitation activities.
| Number of relevant DLDD programmes and activities that are incorporated and analysed within a wider landscape model based LDN framework or principles | 6
| Ha covered under activities | 750
| Forest Restoration | 250
| Grassland Restoration | 500
Ha placed under SLM / SFM practices
| Forest under SFM Practices | 2000
| Grassland under SLM Practices | 8000
Outcome 1.2 LDN mainstreamed in national policy/regulatory and institutional frameworks and land use planning processes
Output.1.2.1: Assessment of LDN policy gaps and development of cross-sectoral policies/legal framework supporting LDN principles at national level and improving the investment policy focusing on land management |  | Policy workshop realised on policy recommendations | Development of Terms of Reference and Re-Announcement of Tender for Land Tenure and Policy Gap Assessment The PMU has developed a comprehensive ToR for the recruitment of a national consultant to undertake an in-depth gap analysis of national policies and regulatory frameworks related to land resources, forestry, and agriculture. The scope of the assignment includes a detailed review of land use planning systems, climate change-related legislation, and associated policies, strategies, and regulatory instruments. Special attention will be given to cross-sectoral legal and policy frameworks that support the principles of LDN at the national level. The study will also assess investment-related policies with a focus on sustainable land management (SLM), particularly those that address the needs and rights of women and other vulnerable groups. In parallel, the consultant will identify key barriers within existing market policies that restrict smallholder farmers’ access to markets in the targeted governorates, and provide actionable policy recommendations to overcome these challenges. These recommendations will be linked to gender-sensitive sustainable livelihood strategies and priority value chains. Furthermore, the consultant will conduct a detailed assessment of land tenure arrangements within the project governorates and identify critical policy constraints hindering the mainstreaming of SLM and related investment initiatives. This component will also address LDN-related gender policy gaps and propose the development of inclusive cross-sectoral policy and legal frameworks to improve land governance and ensure equitable access to land-based resources. Additional tasks will include the identification of entry points to enhance stakeholder participation in the LDN target-setting and implementation process at the sub-national level. This will involve the integration of gender-sensitive and conflict-sensitive programming approaches. A contextual analysis will be conducted to document existing community-level conflict dynamics (including disputes and tensions) surrounding land resources, forestry, agriculture, tenure rights, water management, and related sectors. Based on the findings of this contextual analysis—conducted through a programme clinic approach—the consultant will develop a set of tailored, conflict-sensitive programming recommendations to guide the project’s implementation in a socially inclusive and equitable manner. Re-Announcement of Tender To facilitate this critical assessment, and due to an unsuccessful initial procurement process, the tender for the recruitment of a national expert specializing in land tenure and policy gap assessment was re-announced in May 2025. The announcement was made in both Arabic and English to ensure broader outreach and to attract suitably qualified candidates to support the successful implementation of this assignment.
| Number and sectoral profile of stakeholders interviewed/engaged in policy recommendations | 1
| Number and sectoral profile of stakeholders interviewed/engaged in the contextual analysis of conflictual dynamics and Programme Clinic | 1
| policy proposals produced | 2
| Number of policies, plans and other documents that are Gender mainstreamed and conflict-sensitive in national policy/regulatory and institutional frameworks and land use planning processes | 2
Output 1.2.2: LDN Platform for stakeholder engagement created at national level |  | Platform active | Establishment of the LDN Stakeholder Engagement Platform and Institutional Support to the National Committee to Combat Desertification During the technical mission of the LTO in October 2024, it was agreed that the stakeholder engagement platform for LDN at the national level does not necessarily need to be a digital platform. Rather, it can take the form of an LDN Working Group or coordination body. The core objective of this platform is to strengthen coordination and collaboration among relevant stakeholders. While a digital tool may serve as a useful instrument to facilitate communication, it is not considered the primary focus of this component. In alignment with this approach, the project has begun supporting efforts to re-establish institutional linkages with the national Desertification Working Group operating under the umbrella of the United Nations Convention to Combat Desertification (UNCCD) and led by the Ministry of Environment. This committee has not been active since the conclusion of the most recent National Action Plan (NAP) to Combat Desertification, which covered the period 2015–2020. The Ministry of Environment has expressed its willingness to restructure and institutionalize the NCCD with a renewed mandate and an updated ToR. In response, the project is currently providing technical and strategic support to the Ministry in the drafting of the new ToR for the NCCD, ensuring alignment with the UNCCD framework and the national LDN priorities. The reactivation and institutionalization of the NCCD is expected to provide a formalized and inclusive coordination mechanism for advancing LDN target-setting and implementation in Jordan, while also enhancing multi-sectoral engagement and policy coherence at the national level. |  |  | no digital platform will be established by the project.
| Number and diversity of groups and sectors represented or targeted within Platform | 8
Potential audience and diversity of media formats utilised to share information and updates
Number of Interactive maps, data or associated products available to public to promote LD awareness and LDN principles
Output 1.2.3. Inter-sectoral coordination mechanisms strengthened at all levels for LDN implementation, ensuring upward and downward accountability and transparency |  | At least 2 intersectoral coordination mechanisms | During the meeting with the project LTO the platform creation was discussed, and it was agreed to follow up on reviving the desertification committee at the MoEnv. And on Feb 2025 the project approached the ministry with the support from FAO to set a meeting and discuss, but it was informed that the TPS2 project is already working on that, where the ALDNT project was agreed to give capacity building follow up till the end of it is period. The project and the ministry of environment is now reviewing the committee TOR and agreed to have a meeting with the selected members to discuss the expectations and the support needed
| Number of participant sectors in coordination mechanisms | 4
| Number of GoJ agencies involved | 4
| Number of coordination mechanisms receiving conflict-sensitive programming orientation/ capacity building | 1
| Number of conflict-sensitive programming sessions implemented | 1
Output 1.2.4. Integrated land use planning and drought management using FAO Land Resources Planning Toolbox elaborated, consulted, and adopted by authorities in the Irbid, Mafraq, and Ajloun Governorates | Ha covered under approach | Output results are presented to potential stakeholders and users and validated as a best practice approach. Protocols are established through a stepwise manual to faciltate data and information to MoA, MoE, Higher Socio-Economic Councils and other key policy institutions
Ha covered under approach
Number of direct and indirect beneficiaries of plans (disaggregated by gender)
Number of plans developed
Number of private sector entities involved
Outcome 1.3: Enhanced capacity at national and sub-national levels to support the achievement of LDN in Irbid, Mafraq, and Ajloun Governorates
Output 1.3.1. Knowledge products on SLM and LDN prepared and shared |  |  | • Project Video on Restoration Activities A project video was produced to document and showcase the restoration activities implemented in collaboration with the Ministry of Agriculture. The video highlights key achievements, field-level interventions, and the overall impact of the project. It has been disseminated via social media platforms and official websites to enhance project visibility, raise public awareness, and share progress with a broader audience of stakeholders, partners, and the general public. • Development and Installation of Project Signage As part of the project’s communication and visibility strategy, project identification signage was developed, designed, and installed at restoration sites. These signs serve to improve the visibility of project interventions, promote stakeholder recognition, and raise awareness about the ongoing restoration efforts at the site level. The signage forms part of the project’s suite of knowledge and awareness-raising materials.
| Number and type of Knowledge products developed which are gender sensitive in content and form on SLM and LDN | 3
Number of media formats used by project to promote LDN awareness and size of potential audience
3rd party publications and media coverage of project-produced knowledge products
Output 1.3.2. Capacity development and awareness raising program in place targeting stakeholders and policy makers for LDN targets implementation and monitoring | Number of people trained/participant in LDN workshops and sessions - Total | 90 | No action has been initiated thus far; the activity is scheduled for implementation in November 2025.
| Number of people trained/participant in LDN workshops and sessions - Male | 45
| Number of people trained/participant in LDN workshops and sessions - Female | 45
| Number of Governate staff trained in LDN principles and framework application | 15
| Number of Governate staff trained in LDN principles and framework application | 7
| Number of Governate staff trained in LDN principles and framework application | 8
Component 2: Demonstrating the LDN approach and scaling out SLM practices and approaches in selected landscapes in the Irbid, Mafraq and Ajloun Governorates
Outcome 2.1 Outcome 2.1: Improved Land Cover/Management, Land Productivity, and SOC through the application of SLM/DLDD practices and approaches in selected landscapes of the Aljoun, Irbid and Mafraq Governates
Output 2.1.1: Participatory integrated land-use plans developed and priorities identified by the DSS in the Irbid, Mafraq and Ajloun Governorates |  | LDN DSS developed | An LD expert was selected and to be hired during July 2025, will be working in consultation with local communities to develop land restoration plans per each of the targeted landscapes.
| Number of stakeholders who provide inputs to land-use plan | 5
| Ha covered under activities | 5000
| Ha cropland resotoration | 2000
| SLM/SFM Practices (cropland) | 10000
| SLM/SFM Practices (mixed land cover types) | 5000
| Number of plans developed | 3
| Number of private sector entities involved, including farms (Land Stewardship agreements) - Total | 10000
| Number of private sector entities involved, including farms (Land Stewardship agreements) - Male | 5000
| Number of private sector entities involved, including farms (Land Stewardship agreements) - Female | 5000
Output 2.1.2: Innovative and integrated Sustainable Land/Water Management practices and technologies adopted in farmer field schools (FFS) to enhance land productivity, restore degraded land and reduce pressure on NR (e.g. agro-forestry, afforestation integrated crop/livestock production systems, water harvesting, grazing of riparian zones, grazing crop residues to allow vegetation recovery, pasture and crop rotation, organic manure, soil moisture harvesting, drip irrigation) |  | The mixed organisational approach | Four awareness-raising workshops were conducted in July 2024, one in Ajloun, two in Mafraq, and one in Irbid. The workshops were held with local CBOs to promote the Sustainable Land Management (SLM) approach under the project and to gather feedback on potential participatory methods for achieving the project’s goals and outcomes. In Ajloun, one workshop was held on 15 July 2024, attended by 44 participants (27 males and 17 females). In Mafraq, two workshops were organized on 4 June and 10 July 2024, reaching 39 participants, including 27 males and 12 females. Irbid hosted one workshop on 24 July 2024, with a total of 40 participants, comprising 28 males and 12 females. In summary, the workshops successfully engaged 82 male and 41 female participants, reflecting inclusive participation across the target regions and a cumulative total of 123 individuals sensitized on SLM concepts and approaches. Establishment and Implementation of Farmer Field Schools (FFS) Five Farmer Field Schools (FFS) have been established in close coordination with the Ministry of Agriculture across three target governorates: Mafraq, Ajloun, and Irbid. These schools aim to build the capacities of local farmers through practical, participatory training sessions focused on sustainable agricultural practices aligned with the project’s objectives. A total of 100 beneficiaries (59 males and 41 females) are currently engaged in the FFS activities, which focus on key local value chains including olive (Olea), vegetables, and potato production. All FFS activities are ongoing. Mafraq Governorate FFS on Olea: 20 participants (15 males, 5 females); 10 sessions conducted FFS on Vegetables: 20 participants (16 males, 4 females); 10 sessions conducted Ajloun Governorate FFS on Olea: 20 participants (12 males, 8 females); 2 sessions conducted FFS on Potato: 20 participants (5 males, 15 females); 4 sessions conducted Irbid Governorate FFS on Olea: 20 participants (11 males, 9 females); 2 sessions conducted In addition, the project team participated in three FFS sessions to introduce the project, its goals, and its core activities to the participants. These engagements have helped raise awareness of the project’s objectives and foster local ownership and alignment with Sustainable Land Management (SLM) practices.
Number of MoU signed with participant organisations and/or FFS created
| Number of FFS operational and meeting minimum standard protocols by project end | 20
| No. of people receive training in SLM practices and integrated Landscape Management - Total | 2250
| No. of people receive training in SLM practices and integrated Landscape Management - Male | 1125
| No. of people receive training in SLM practices and integrated Landscape Management - Female | 1125
Number of ha influenced by FFS
Output 2.1.3. Measures and approaches for reducing the impacts of drought integrated into SLM practices and tested/demonstrated in the context of FFS, APFS or participant organisations |  |  | One of the Ministry of Agriculture’s nurseries in Irbid Governorate was selected for rehabilitation to support the propagation of native forest and pasture plant species. This initiative aims to utilize native seeds collected through the Farmer Field Schools (FFS) and establish the nursery as a central production site for seedlings required in the project's forest and rangeland restoration activities. An initial site evaluation was conducted in collaboration with Ministry of Agriculture engineers to assess renovation requirements. Based on this assessment, the rehabilitation needs were documented, detailed technical specifications were developed, and a tender was issued for the required works. However, the process experienced delays due to a formal ministerial decision to change the designated nursery location. The project team responded promptly, and the newly selected Aqraba Nursery in Irbid Governorate was assessed in coordination with ministry engineers. During the current reporting period, the rehabilitation of Aqraba Nursery progressed significantly and was nearly completed. The scope of work included the following key components: a) Establishment of seedling beds b) Installation of a comprehensive irrigation network c) Construction of a plastic house for seedling propagation The rehabilitated nursery is expected to play a vital role in ensuring the sustainability and long-term success of project interventions by providing a reliable and locally adapted source of native seedlings for ongoing and future restoration activities in both forest and rangeland ecosystems.
Number SLM practices / SFM techniques demonstrated, documneted and replicated in sites or demonstration sites.
| SFM techniques demonstrated and documented in Forestry Land Condition. | 2
| SFM techniques demonstrated, documented and replicated in at least no. of sites in Forestry Land Condition. | 2
| SLM practices demonstrated and documneted in Pasture/grazing areas. | 2
| SLM practices demonstrated, documneted and replicated in at least no. of demonstration sites in Pasture/grazing areas. | 2
| SLM practices demonstrated and documented in Cropping Land Condition. | 2
| SLM practices demonstrated, documented and replicated in at least no. of demonstration sites in Cropping Land Condition. | 2
| Number of SLM techniques/ approaches uploaded into global WOCAT database. (Results of demonstrations from participant organisations/FFS are documented and analysed, resulting in publication of knowledge product and addition of at least 1 WOCAT publication per Governate) | 3
Number of participant organistions/FFS involved in demonstrations or study
| Number of people and organisations trained in SLM techniques - Total | 250
| Number of people and organisations trained in SLM techniques - Male | 125
| Number of people and organisations trained in SLM techniques - Female | 125
Number of training led by women trainers
Ha covered in activities
Output 2.1.4. Introduction of gender sensitive sustainable livelihood strategies. | Number of direct / indirect beneficiaries of output activities (members of different participant organisations/FFS realise field days and visits to innovative, sustainable business innitiatives). | Awareness and recognition for those entities and producers utilising LDN and SLM practices that provide for innovations in gender sensitive livelihoods are showcased through events and other forms of recognistion, including virtual media, awards and promotion. | No action has been initiated thus far; the activity is scheduled for implementation in November 2025.
Number of project led or supported events and exchanges
Number of gender sensitive business models developed or showcased within FFS and other project networks
Number and type of collaborative activities realised with CSOs to promote entrepenurial acttivities and investments in project VCs.
Outcome 2.2: Increased investments in sustainable land management to achieve LD
Output.2.2.1: LDN Action Plan with voluntary targets defined in the landscapes of Irbid, Mafraq, and Ajloun Governorates | Number of action plans created to support land plans resulting from Output 2.1.2 | Lessons learnt through development of 1st LDN Action Plan are used to support following Output 2.1.1 plans, with a minium of 3 realised. | No action has been initiated thus far; the activity is scheduled for implementation in November 2025.
Number of staekholder and institutions that provide inputs to action plan
Number of private sector entities that support plans with in kind activities or materials
Output 2.2.2: Market access mechanism identified and key value chains (i.e. vegetables, olives, dairy, Beekeeping) strengthened to achieve LDN in the landscapes of Irbid, Mafraq, and Ajloun Governorates | Number of marketing strategies and initiatives developed |  | Signing Contracts with Value Chain Consultants for the Vegetables, Dairy, Olives, and Beekeeping Sectors To enhance the project's efforts in promoting sustainable livelihoods, the project team initiated a competitive bidding process for the recruitment of national consultants specialized in the value chains of olives, vegetables, dairy products, and beekeeping. The procurement process was finalized by the end of 2024, and contracts were successfully signed with selected experts at the beginning of 2025. Following the contracting phase, the consultants commenced fieldwork, which includes: a) Field Data Collection: Utilizing structured questionnaires designed to gather quantitative and qualitative information relevant to each targeted value chain. b) Focus Group Discussions (FGDs): Engaging with local communities and Community-Based Organizations (CBOs) to conduct participatory value chain analysis, identify bottlenecks, and explore opportunities for improved market access and income generation. c) Key Informant Interviews (KIIs): Conducting in-depth interviews with technical experts and representatives from relevant government institutions in the targeted governorates to gain insights into sector-specific challenges and institutional frameworks. These activities aim to inform the development of inclusive, gender-sensitive, and conflict-aware value chain strategies that align with sustainable land management (SLM) and Land Degradation Neutrality (LDN) objectives.
| Number and type of marketing support activities realised | 2
| Number of VC intervened | 4
| Increase in investments in VCs over project baseline | 2,500 beneficiaries
Output 2.2.3. Training programs on value-chains management (e.g. marketing, processing, certification) for local communities, extension services, farmers, women groups and youth | Total number of people trained/participant in VC workshops and sessions (data disaggregated by gender) | 125 people | Training Needs Assessment and Program Development for Targeted Value Chains As part of their core responsibilities, the four consultants contracted to support the project’s work on the selected value chains—olives, beekeeping, vegetables, and dairy products—have each conducted comprehensive training needs assessments within their respective sectors. These assessments aim to identify capacity gaps among local producers and stakeholders and to inform the design of tailored training programs aligned with the project’s objectives. Each consultant has submitted a detailed report outlining the identified training needs and proposing targeted training programs to be adopted and implemented under the ALDNT project framework. These reports are currently under review and evaluation by the project team to ensure their relevance, feasibility, and alignment with the project’s overall goals, including sustainability, gender inclusion, and market-oriented development.
| receive Value Chain training from the total number of people (%). | 50%
| support from the total number of people (%). | (50% women)
Number of participants in events and exchanges
Number of project led or supported events and exchanges
Number of gender business models developed or showcased within FFS and other project contexts
Number of direct / indirect beneficiaries of output activities
Outcome 3.
Output.3.1.1: Project mid-term and final evaluation conducted | Mid-term and final evaluation reports |  | The mid-term evalaution is scheduled for implementation in october 2025.
Output 3.1.2: Global Environment Benefits, co-benefits and costs of SLM monitored, assessed and lessons analyzed. | M&E system ensuring timely delivery of project benefits and adaptive results-based management | Project M&E system delivers expected reports and informs project management | The M&E Officer ensured that all monitoring and evaluation activities/ arrangements complied with donor agreements and project requirements. An Excel-based monitoring system was developed to support systematic data collection and analysis. Continuous learning was promoted by integrating lessons learned into project planning, and regular progress reports and assessments were prepared to support project manager and improve overall project effectiveness.
Output 3.2.1: Gender-focused communication strategy developed and implemented to support SLM scaling up to meet LDN targets | Number of appearances in local media, partners/regions and partner websites | Gender-focused communication strategy is fully operational | No action has been initiated thus far; the activity is scheduled for implementation in October 2025.
| Number of awareness raising activities | # Awareness raising activities
Number of gender, youth or vulnerable people and LDN stories edited for press release
Implementation Progress (IP) , and Overall Assessment
Please note that the overall IP ratings should be substantiated by evidence and progress reported above. The ratings and comments shoud reflect the overall progress of results during the fiscal year (July 1 2024, to June 30, 2025)
| Project Manager/ Coordinator (RSS) |  | Lead Technical Officer | Budget Holder | GEF Operational Focal Point (OFP) | GEF Technical Officer (GTO)
FY2025 Implementation Objective rating10 | Moderately Satisfactory (MS) |  | Moderately Satisfactory (MS) | Moderately Satisfactory (MS) |  | Moderately Satisfactory (MS)
Comments/reasons justifying the ratings for FY2025 and any changes (positive or negative) in the ratings since the previous reporting period | The project has faced allot of delays, especially the theme of the project is new, and there are not many consultants who have the needed experience, yet the project team have developed the TORs for most of the services needed and signed the agreement with Ministry of Agriculture. the RSS procurment procedures are very long and time consuming that need to shortend to enhance the project implemenation FAO also have appointed a lead officer to follow up on the project activities and implementation. The project needs more Communication with other projects that were to cofinance its activities to ensure the project reach it is intended targets |  | The project is making steady progress in recovering from initial delays, with important technical activities and pilot interventions now underway. Although earlier implementation was hindered by delays mainly in consultants recruitments, recent developments mark a positive shift. The recent progress demonstrated positive commitment to advancing the LDN framework through capacity building, training, and improved coordination. Additionally, the formalized partnership with the Ministry of Agriculture and progress on the LDN Decision Support System (DSS) are promising milestones that lay the groundwork for accelerating implementation in the next phases. | The project is making steady progress in recovering from initial delays, with important technical activities and pilot interventions now underway. Although earlier implementation was hindered by delays mainly in consultants recruitments, recent developments mark a positive shift. The recent progress demonstrated positive commitment to advancing the LDN framework through capacity building, training, and improved coordination. Additionally, the formalized partnership with the Ministry of Agriculture and progress on the LDN Decision Support System (DSS) are promising milestones that lay the groundwork for accelerating implementation in the next phases. | Comments | Overall assessment is MS as progress ever since last PIR is clearly observable. Also, the close cooperation between CO and RSS is well noted and appears very productive. Implementation rate however, even though improved, remains too low. Perhaps Implementation Modalities might nbeed to be re-structured.
9 Variance refers to the difference between the expected and actual progress at the time of reporting. 10 Implementation Progress Rating – A rating of the extent to which the implementation of a project’s components and activities is in compliance with the projects approved implementation plan.

## 4. Summary_Progress & Challenge
4. Summary on progress and challenges
Please provide a summary paragraph on project implementation progress consistent with the information reported in section 2 and 3 of the PIR (Max 400 words) (This section will be uploaded to the GEF portal)
Under Component 1 of the project—Enabling Environment for LDN Planning and Monitoring—the recruitment of key consultants to support implementation remains incomplete, resulting in delays across several activities. Recruitment is expected to be finalized by September 2025. Likewise, the baseline assessment, although initially planned following consultations in October 2024, has not yet been initiated and is now scheduled to begin in August 2025. Despite these delays, important progress has been made. The OP (RSS), with support from FAO international consultants, has updated the Land Degradation Neutrality Decision Support System (LDN-DSS), incorporating new open-source geospatial data and improving its interface. A three-day training workshop in November 2024 engaged 43 participants from various sectors, significantly strengthening their technical capacity in spatial analysis, scenario planning, and data-driven decision-making. This has helped foster intersectoral collaboration and improve long-term land management planning. Field assessments at 57 intervention sites informed the launch of DLDD mitigation and restoration activities across eight pilot sites in Irbid, Mafraq, and Ajloun. DLDD interventions focus on forest restoration (terracing, contour lines, native seed planting) and rangeland rehabilitation (including Atriplex halimus planting) started across 8 pilot sites located within three governorates. Joint technical field visits with the Ministry of Agriculture are ongoing to finalize implementation modalities. A no-cost extension is under consideration to ensure full delivery of expected outcomes. Under Outcome 1.2, a national consultant was recruited to conduct a gap analysis of policies related to land, forestry, and agriculture. The study, however, has faced significant delays and remains incomplete. In parallel, the project began reviving the National Committee to Combat Desertification under the Ministry of Environment. A draft Terms of Reference (ToR), developed in June 2025, outlines the committee’s mandate and will serve as a basis for strengthening national coordination under the UNCCD framework. A documentary video highlighting restoration efforts with the Ministry of Agriculture was also produced and shared on social media and official platforms to raise public awareness. Under Component 2, between late 2024 and early 2025, four awareness workshops and five FFS were implemented in Ajloun, Mafraq, and Irbid. These activities engaged over 220 participants and focused on Sustainable Land Management and practical agricultural training. In addition, the rehabilitation of a Ministry nursery is underway to support the multiplication of native plant species using seeds collected through FFS activities.
Please provide a summary paragraph on challenges of project implementation consistent with the information reported in section 2 and 3 of the PIR (Max 400 words) (This section will be uploaded to the GEF portal)
The project has encountered critical delays in implementation, largely due to the novelty of the LDN concept in the country. As a result, there is a limited pool of qualified consultants with the necessary expertise to support the technical and institutional demands of the project. Additionally, constraints related to subcontracting have restricted the implementing partner's ability to establish new partnerships with specialized institutions that could otherwise enhance delivery capacity. To address this, the project team has developed detailed ToRs for the recruitment of individual consultants to fulfill the required technical roles. A formal agreement has also been signed with the Ministry of Agriculture to support coordination and implementation. Despite these measures, the recruitment process remains ongoing, and delays persist. In response, FAO is currently considering a project revision to allow for the engagement of new specialized partners with the capacity to support effective implementation of key components. Furthermore, improved coordination with other stakeholders and initiatives—particularly those identified as co-financing partners—is needed to ensure alignment, avoid duplication, and optimize the project’s potential impact. Strengthening these partnerships will be essential to ensure the project meets its intended objectives and reaches the targeted beneficiaries in a timely and effective manner.
Implementation of Exit Strategy
Has the project developed an Exit Strategy? If yes, please describe the progress to implement it. | The project has developed a clear exit strategy to ensure the sustainability of its key outcomes beyond the implementation period. Central to this strategy are the Land Degradation Neutrality (LDN) Monitoring System and the Decision Support System (DSS), which are among the most significant outputs of the project. To promote long-term ownership and institutionalization, the project has actively involved both the Ministry of Agriculture and the Ministry of Environment in the design, development, and continuous updating of these systems. Representatives from both ministries have also participated in dedicated training sessions to build their technical capacity in operating and maintaining the systems. It has been agreed that, upon the project’s completion, the LDN Monitoring and DSS software and tools will be formally handed over to these institutions. This will enable their continued use in national planning processes, decision-making, and sustainable land management efforts. In addition, to strengthen intersectoral coordination and support integrated approaches to land degradation and desertification challenges, the project is facilitating the reactivation of the National Committee to Combat Desertification (NCCD) under the leadership of the Ministry of Environment. The restructured committee will serve as a key platform for multi-stakeholder engagement. Members of the committee will receive capacity-building support focused on the LDN conceptual framework and the integration of Desertification, Land Degradation, and Drought (DLDD) considerations into national development and planning strategies. These efforts collectively aim to embed LDN principles into institutional frameworks and ensure that the project’s achievements are sustained and scaled beyond its lifespan.
How is the project enhancing institutional capacities to foster country ownership for more durable / sustained results? | The project is actively enhancing institutional capacities to foster country ownership and ensure long-term, sustained results by embedding its interventions within national systems and building strong partnerships with government institutions, communities, and local organizations. This is being achieved through the following key strategies: ToT Approach: The project adopted a ToT methodology to institutionalize and sustain training efforts. By equipping national staff and local extension agents with the necessary skills to deliver and replicate FFS methodologies and LDN DSS training, the project ensures that knowledge transfer continues well beyond its implementation period. Capacity Building of National Ministries: In close coordination with the Ministries of Agriculture and Environment, the project conducted detailed capacity needs assessments and developed tailored training programs. These focused on key LDN competencies such as spatial data analysis, scenario planning, use of SDG indicator 15.3.1, and integration of LDN principles into sectoral planning and national strategies. Co-Development and Handover of Systems: To strengthen institutional ownership, the LDN DSS and monitoring systems are being co-designed with both ministries. Government staff have been engaged throughout the process—from data integration to technical validation—and it is agreed that the final systems will be officially handed over to the ministries for ongoing use in planning and monitoring. Reactivation of the National Committee to Combat Desertification (NCCD): The project is supporting the Ministry of Environment in re-establishing the NCCD with updated terms of reference. This multi-stakeholder platform is intended to coordinate LDN-related efforts across sectors and ensure policy coherence at the national level. Strengthening Producer and Community-Based Organizations: The project supports value chain development for olives, dairy, vegetables, and beekeeping. Consultants have conducted training needs assessments and fieldwork with cooperatives and CBOs to enhance their capacity to engage in sustainable land management and benefit from improved market access. Gender and Conflict Sensitivity: Institutional capacities will also be strengthened through the integration of gender and conflict-sensitive analyses into planning, ensuring inclusive approaches to land management and enhancing resilience among vulnerable groups.

## 5. ESS Risk
5. Environmental and Social Safeguards (ESS): risks from the project
Initial ESS Risk Classification (at CEO Endorsement/Approval Stage) | LOW RISK
New environmental and social risks. | N/A
Progress made towards implementing the Enivronmental and Social Management Plan (ESMP) (only for Moderate and High Risk Projects)
Grievance Redress Mechanism (GRM) | RSS website link https://www.rss.jo/ has contact information (emails rssinfo@rss.jo and telephone numbers (+962) 6 5344701) announced in public and all beneficiaries can use to file complaints, also during the project launching events on the governorate, the contact information of the project, and the governorate facilitators were announced to the public in the month of January 2024 to allow for smooth communication.

## 6. Risks to the Project
6. Risks to the Project
The following table summarizes risks identified in the Project Document and reflects also any new risks identified during the project implementation.
| Type of risk |  | Risk rating11 | Identified in the ProDoc Y/N | Description of Risk | Mitigation measure implemented
1 | Operational & Logistical |  | Moderate | Yes | Weak incentives for stakeholders, farmers and local communities to cooperate due to time lag for fruition of results, may reduce stakeholder engagement and participation | Pilot activities will be participatory in nature and use marginal reaction test to identify actions that yield immediate benefits for Communities in terms socio economic livelihoods and community enhancements, awareness. preparedness, skill development and income generation activities. This will be emphasized during the inception phase. The project has been using a participatory approach in planning the activities
2 | Social |  | Low | Yes | Failure to involve adequate representation of vulnerable communities including refugees working under work permits outside of camps, particularly women, poverty pockets, and beduins resulting in failed ownership of the project at the community level at project sites. | The capacity building component and value chains activities will ensure engagement of vulnerable groups and women and will adopt a gender-sensitive approach, as guided by the M&E -Gender and Social Expert. The project will adopt a two way communication approach to create community ownership and buy-in of the project intervention. The development of implementation plans will be undertaken in a participatory manner, encouraging input from all bedouin tribal heads, community members, and women. Mitigation measures will also include a conflict-sensitive approach, and conflict-sensitive programming specialist consultations. Failure to involve adequate representation of vulnerable communities including refugees working under work permits outside of camps, particularly women, poverty pockets, and beduins resulting in failed ownership of the project at the community level at project sites.
3 | Social |  | Low | Yes | A significant change in the number of refugees entering the Project area, in addition to their livestock. | Involve refugees in capacity building and training activities, through specific FFS groups or value chain capacity building exercises. The project has been using a participatory approach involving refugees and their stakeholders in planning the activities
4 | Economic |  | Low | Yes | Jordanian government no longer has funds for upscaling | The LDN conceptual framework has been created with resource scarcity to address LD in mind. Many of the activities and processes set in place through the project will not depend on GoJ funds to remain active and continue providing benefits once project funding has ceased. The project is working in closed collaboration with the Government
5 | Operational & Logistical |  | Low | Yes | The Government technicians trained under the Project are reassigned to different posts after the Project training. | Professional staff turnover was identified in various project final evaluations as a significant barrier to successful project outcomes. Capacity building will need to take a strategic approach to this issue and work with GoJ counterparts to ensure traction and impact through capacity building. The project is working in closed collaboration with the Government
6 | Partnership & Coordination |  | Low | Yes | Lack of close cooperation between key institutional stakeholders | Even in the PPG phase, lack of information sharing, or high associated costs of data, were barriers. This risk will be mitigated under Component 1 of the project that will strengthen the inter-sectoral coordination mechanism to enhance cooperation on LDN, as well as the LDN Platform will be public in nature and provide data on LDN and other key performance indicators online. The project is working in closed collaboration with the Government
7 | Institutional |  | Moderate | Yes | Lack of political support to address key policy barriers and disincentives to SLM | Political support is high for SLM and LDN, which is demonstrated by the existing policies related to land and forestry. This project will provide an opportunity to strengthen the LDN framework that requires inter-sectoral coordination and to demonstrate good practices in the field, as linked to ILM planning The project is working in closed collaboration with the Government
8 | Operational & Logistical |  | Moderate | Yes | Low technical capacity in operationalizing LDN at national and regional level impacting project progress | Capacity development for LDN will be provided under Components 1 and 2, which will mitigate the risk. Component 3 will in addition provide capacity building for replication of the LDN in other landscapes. The project is implementing the capacity building component based on a need analsysis
9 | Operational & Logistical |  | Low | Yes | Lack of commitment of local stakeholders at the community level to adopt SLM/SFM to achieve LDN | Implementation will be undertaken through community-based participatory approaches that address local cultural, socio-economic and ecological concerns. The project will provide incentives to farmers to engage in various activities that target LDN, involving both capacity building, awareness, and value-chain strengthening. PPG consultations with the target districts demonstrate a strong commitment of the local population to landscape conservation and CC mitigation. The project has been using a participatory approach in planning the activities
10 | Environmental |  | Moderate | Yes | Climate change risks | The mean and maximum temperatures over the full country of Jordan are expected to rise 2-4 degrees, precipitation will be 15-20 percent lower and potential evapotranspiration about 150 mm higher by the end of the century. Producers are already reporting facing extreme heat/drought, intense rainfall and sudden temperature changes, animal diseases, pest outbreaks and strong winds. Mitigation is realised through the described project Causal Pathways and is both an objective and outcome of project activities The project is starting in quarter 3 2024 the capacity building component based on a need analysis
11 | Safety & Security |  | Moderate | Yes | COVID-19 | COVID –19 did not affect the project during the reporting period
12 | Social |  | Moderate | Yes | Low participation of women/ limited benefits to women | The GAP contains a full list of measures and actions to minimize risks and maximize benefits to women and men, as well as youth. The project has been using a participatory approach in planning the activities. A gender expert will be hired by the project during the quarter 3 2025
Project overall risk rating (Low, Moderate, Substantial or High):
FY2024 rating | FY2025 rating | Comments/reason for the rating for FY2025 and any changes (positive or negative) in the rating since the previous reporting period
LOW | Low | No major change from 2024
11 Risk ratings means a rating of the overall risk of factors internal or external to the project which may affect implementation or prospects for achieving project objectives. Risk of projects should be rated on the following scale: Low, Moderate, Substantial or High.

## 7. Follow-up on Mid-term review
7. Follow-up on Mid-term review or supervision mission
If the project had an MTR or a supervision mission in 2024, please report on how the recommendations were implemented during this fiscal year as indicated in the Management Response or in the supervision mission report.
MTR or supervision mission recommendations | Measures implemented during this Fiscal Year
Recommendation 1: | N/A
Recommendation 2:
Recommendation 3:
Recommendation …
Recommendation…

## 8. Minor project amendments
8. Minor project amendments
Minor amendments are changes to the design or implementation that do not have significant impact on the project objectives or scope, or an increase of the GEF project financing up to 5% as described in Annex 9 of the GEF Project and Program Cycle Policy Guidelines 12. Please describe any minor changes that the project has made under the relevant category or categories and provide supporting documents as an annex to this report if available. (This section will be uploaded to the GEF Portal)
Category of change | Provide a description of the change | Indicate the timing of the change | Approved by
Results framework
Components and cost
Institutional and implementation arrangements
Financial management
Implementation schedule
Executing Entity
Executing Entity Category
Minor project objective change
Safeguards
Risk analysis
Increase of GEF project financing up to 5%
Co-financing
Location of project activity
Other minor project amendment (define)
12 GEF Council meeting documents, guidelines, project and program cycle policy 2020 update

## 9. Stakeholders' Engagement
9. Stakeholders' Engagement
Please report on progress, challeges, and outcomes on stakeholder engagement (based on the description of the Stakeholder Engagement Plan) included at CEO Endorsement/Approval during this reporting period. (This section will be uploaded to the GEF Portal)
Profile | Stakeholder name | Type of partnership | Progress, results & Challenges on Stakeholder's Engagement
Government Institutions | Ministry of Agriculture | Co-financing partner Chair of PSC | MoA is a member of the PSC. An agreement was signed for project implementation with RSS. They nominated a focal point in Amman. Delays on signing the subcontracting agreement with MoA. The agreement was supposed to be signed during the last quarter of 2023, but it was signed in March 2024.
Government Institutions | Ministry of Environment | Co-financing partner PSC | Member of the PSC. They participated in the main project events. They nominated a project focal point in Amman.
Government Institutions | Dept. Lands & Irrigation | Co-financing partner | participated in the Inception Workshops
Government Institutions | Dept. of Forestry + Rangeland | Co-financing partner | Member of the PSC, Joint Planning Meetings of the agreement between MoA and RSS
Government Institutions | NARC | Co-financing partner
Government Institutions | Ministry of Water and Irrigation | Co-financing partner | Member of the PSC
Government Institutions | MOPIC | Co-financing partner | Member of the PSC
Government Institutions | Ministry of Municipal Affairs | Co-financing partner | Member of the PSC
Government Institutions | Agricultural Credit Corporation | Co-financing partner | Member of the PSC
Government Institutions | Regional Agricultural Dep. at Governorate | Co-financing partner | Joint Planning Meetings of the agreement between MoA and RSS field implementation of the activities
Government Institutions | Municipalities | Co-financing partner | participate in meetings and workshops
NGOs | NGOs | indirect beneficiaries | participate in meetings and workshops
Others | National Committee to Combat Desertification (NCCD) | indirect beneficiaries | the project is working to reactivate the committee

## 10. Gender Mainstreaming
10. Gender Mainstreaming
Information on Progress on Gender-responsive measures as documented at CEO Endorsement/Approval in the gender action plan or equivalent (when applicable) during this reporting period. (This section will be uploaded to the GEF Portal)
Category | Yes/No | Briefly describe progress and results achieved during this reporting period.
a. Closing gender gaps in access to and control overal natural resources | Yes | Women are involved and encouraged to participate to at local and national level in access to and control over natural resources
b. Improving women's participation and decision making | Yes | Women are selected and encouraged during the project implementation stage to actively participate during decision making fora
c. generating socio-economic benefits or services for women | Yes | Women directly benefiting from the value chain component of the project
M&E system with gender-disaggregated data? | Yes | Gender disaggregated data are included in the M&E tools
Any other good practices on gender

## 11. Knowledge Management
11. Knowledge and Learning Activities
Knowledge activities/products (when applicable), as outlined in Knowledge Management (and Learning) Approach approved at CEO Endorsement/Approval, during this reporting period. (This section will be uploaded to the GEF Portal)
Knowledge management and Learning (KML): Does the project have a KML strategy? | Yes
If YES, what is the implementation progress? In your answer, please describe how the project is fostering knowledge sharing and learning among stakeholders at national and sub-national level. | the project has design an LDN DSS system that allow the sharing of informaiton and knoledge. Furthermore, the project is actively participating to regional and national knowledge and learning sessions. The project is also promoting TSP and an LDN/Desertification worksing group in Jordan for coordination and knowledge sharing
If NO, how does the project identify, collect and document good practices?
Please list good practices, including key-technical and/or institutional innovations, from the project thus far.
Communication strategy: Does the project have a communication strategy? | No
Please provide a brief overview of the communications successes and challenges this fiscal year. | the project has succesfully published a video on the project
Human-interest story: Please share a human-interest story from your project, focusing on how the project has helped to improve people's livelihoods while contributing to achieving the expected Global Environmental Benefits. Please indicate any Socio-economic Co-benefits that were generated by the project. Include at least one beneficiary quote and perspective, and please also include related photos and photo credits. | The community engagement is at its preliminary stages. The target communities will start benefiting from the project during the year 2025. Human-interest stories and Socio-economic co-benefits generated by the project will be collected and disseminated.
Please provide links to related website, social media account | linkedin
facebook page
instagram page
https://x.com/FAOJordan/status/1935670540297032116
Please provide a list of publications, leaflets, video materials, newsletters, or other communications assets publised on the web, if any. | DSS : https://projectgeffao.users.earthengine.app/view/jordan-ldn FERM: : https://ferm.fao.org/search/initiatives/OqYqpsbGGZKVOfQGm7ZB
=Package¦'C:\Users\3752\OneDrive\Documents\Jordan ALDNT project restoration activities 262025.mp4'!''''
Please indicate the Communication and/or knowledge management focal point's name and contact detais. | FAO: Alkhayyat Dima Email: dima.alkhayyat@fao.org RSS: public relation department

## 12. Indigenous & Local Involve.
12. Indigenous Peoples and Local Communites Involvement
Are Indigenous Peoples and local communities involved in the project (as per the approved Project Document)? If yes, please briefly explain.
If applicable, please describe the process and current status of on-going/completed, legitimate consultations to obtain Free, Prior and Informed Consent (FPIC) with the indigenous communities. Four consultation workshops were held during first quarter 2024, one in Irbid, one in Ajloun and two in Al Mafraq, the total number of attendees was 193; 139 were males and 54 were women, with a participation of 49 representing the local NGOs in those governorates. The names of the NGOs are: Al-Weam Charity Association, Rajab Charity Association, the Raehat Aljaneh Charitable Society, Al-Azmi District Charity Association, Rajab Gate Charitable Association, Saeedat Alataa Association, Wadi Rajab Women's Cooperative Society, Altadamon wa aletefaq Association, Alkawkab alakhdar Society, Kaab Maloul Charitable Association, Al-Hashimiya Charity Association, Al Maharas Cooperative, Anwar Abin Cooperative Society, Sakhrah Women's Association, Sakhrah Cooperative Society, Specific Union of Women Farmers, Umm Al-Wulu Women's Cooperative Society, Rawabi Ajloun Association, Shabab Al-Ruwaished Charitable Association, Al-Wefaq Association for Orphans and Widows, Almawadah wa Alrahmah Association, Ahl Al-Khair Association and the Farmers Union. The project activities were presented to the local communities in the three governorates, and a discussion session was held to take their opinions on the implementation mechanisms and cooperation. After the end of the sessions, special reports were prepared for each session and shared with the attendees. Recommendations from all sessions have been integrated into plans and project execution. The main recommendations received are: 1. Focus on water harvesting at farm level; 2. Focus on planting trees with high blossom and nectar content to support beekeepers; 3. Train local producers on packaging and marketing; 4. Support the community with a dairy and cheese products factory, or olive press; 5. use solar energy in the agricultural projects; 6. Supporting livestock breeders with fodder, water, and feeding; 7. Encourage farmer to adopt agricultural methods that improve soil fertility and increase productivity; 8. Formation of FFS; 9. Establish nursery to produce local verities; 10. Allocating suitable sites as pastures for local livestock owners; 11. Establishment of ecotourism activities and local parks. In the session at Al-Ruwaished area in the governorate of Almafrq, there was a request from the local community on the need to develop the dairy value chain. After the session, TOR of the expert was prepared, and a bid was announced to recruit the expert, as also aligned with the GEF approved project document (activities on value chain development). Do indigenous peoples and/or local communities have an active partcipation in the project activities? If yes, briefly describe how. As part of the project’s effort to strengthen value chains and promote sustainable land management practices, a series of Focus Group Discussions (FGDs) and stakeholder meetings were conducted with key actors in the selected sectors. These included sheep and goat herders, local farmers, dairy factories, and olive mills across the governorates of Ajloun, Irbid, and Mafraq. A total of 13 FGDs were organized, engaging 169 participants, including 97 males and 72 females. These sessions were designed to collect in-depth qualitative data on production practices, supply chain dynamics, and sector-specific challenges. Participants shared insights on several recurring issues affecting value chain performance. Key concerns included: Low feed quality and high feed costs, particularly for livestock producers; Animal health and disease management challenges, which impact productivity and profitability; High production costs and limited access to quality inputs; Marketing and distribution constraints, including limited market access and low price returns for producers; Inadequate infrastructure and services, particularly in processing and storage. The data gathered through these FGDs is informing targeted interventions aimed at improving the efficiency and sustainability of the olive, dairy, vegetable, and beekeeping value chains. The inclusive approach—especially the strong participation of women—ensures that project strategies are responsive to the needs of all value chain actors and contribute to long-term resilience and rural livelihoods.

## 13. Co-Financing Table
13. Co-Financing Table
Sources of Co-financing | Name of Co-financer | Type of Co-financing | Amount Confirmed at CEO endorsement/approval (in USD) | Actual Amount Materialized at 30 June 2025 (in USD)
Recipient Country Government | Ministry of Environment | Public Investment | 4539429 | 4539429
Recipient Country Government | Ministry of Environment | In Kind | 700000 | 700000
GEF Agency | GCF/FAO Funded “Building resilience to cope with climate change in Jordan through improving water use efficiency in the agriculture sector (BRCCJ)” | Grant | 23106013 | 4876164
GEF Agency | FAO (Technical and logistical backstopping including staff time, office space, and meeting facilities) | In Kind | 700000 | 56360
Total |  | Total | 29045442 | 10171953
Please explain any significant changes in project co-financing since CEO Endorsement/Approval, or differences between the pledged and materialized co-financing amounts.
GEF CoFinancing Guidelines 2018

## 14. GEO Location
14. Geo Location Information
This section should be completed ONLY by projects with 1st PIR and in case the geographic coverage of project activities has changed since last reporting period. This information is required by GEF Secretariat in GEF Portal
Are there any changes in the geographic coverage of the project activities since the last PIR report?
Location Name | Latitude | Longitude | Geo Name ID | Location & Activity Description*
Irbid Governate / | 32.55 | 35.85 | A1 Duwaqarah 1 | · A1 land cover is Grassland, registered for forestry department
· A2 land cover is Grassland, registered for forestry department
· The suggested activities are:
· Water harvesting.
· Soil erosion control measures.
· FFS.
· Grazing management measures.
|  |  | A2 Duwaqarah 2 | · Cropland management measures.
|  |  | A36 Sharhabeel Dam 1 | · A36 land cover is Grassland, registered for forestry department
· A37 land cover is Grassland, registered for forestry department
· The suggested activities are:
· Beekeeping measures.
· Soil erosion control measures.
· Farm Field Schools.
· Water harvesting.
|  |  | A37 Sharhabeel Dam 2 | · Grazing management measures.
|  |  | A38 Jedayta (Wadi Al-Rayyan) 1 | · A38 land cover is Grassland, registered for forestry department
· A40 land cover is Grassland, registered for forestry department
· A41 land cover is Grassland, registered for forestry department
· A42 land cover is Grassland, registered for forestry department
· The suggested activities are:
· Soil erosion control measures.
· Farm Field Schools.
|  |  | A40 Jedayta (Wadi Al-Rayyan) 2 | · Water harvesting.
|  |  | A41 Jedayta (Wadi Al-Rayyan) 3 | · Cropland management measures.
|  |  | A42 Jedayta (Wadi Al-Rayyan) 3 | · Grazing management measures.
Jedayta (Wadi Al-Rayyan) 4
|  |  | A43 Der Abi Saeed | · A43 land cover is Grassland, registered for forestry department
· The suggested activities are:
· Beekeeping measures.
· Farm Field Schools.
· Grazing management measures.
· Cropland management measures.
· Water harvesting.
|  |  | A44 Kufr Rakeb Landscape | · A44 land cover is Grassland, registered for forestry department
· The suggested activities are:
· Soil erosion control measures.
· Farm Field Schools.
· Water harvesting.
· Grazing management measures.
|  |  | A45 Saham 1 | · A45 land cover is Grassland, registered for forestry department
· A46 land cover is Grassland, registered for forestry department
· A47 land cover is Grassland, registered for forestry department
· The suggested activities are:
· Water harvesting.
· Soil erosion control measures.
|  |  | A46 Saham 2 | · Farm Field School.
|  |  | A47 Saham 3 | · Grazing management measures
Aljoun Governate / | 32.3325 | 35.7517 | A39 Jedayta (Wadi Al-Rayyan) 5 | · A39 land cover is grassland with artificial forest registered for forestry department
· A6 land cover is grassland registered for forestry department
· The suggested interventions are:
· Erosion control measures.
· Water harvesting.
· Grazing management.
· Fire-fighting measures.
· Afforestation.
|  |  | A6 Jedayta (Wadi Al-Rayyan) 6 | · Farm Field Schools.
|  |  | A10 Sakhrah 1 | · A10 land cover is grassland with less than 10% tree cover registered for forestry department
· A11 land cover is grassland with less than 20% tree cover registered for forestry department
· The suggested interventions are:
· Erosion control measures.
· Water harvesting.
· Eco-parks. Grazing management.
· Fire-fighting measures.
· Afforestation.
|  |  | A11 Sakhrah 2 | · Farm Field Schools.
|  |  | A4 Al- Hashemiyyah 1 | · A4 land cover is Grassland, registered for forestry department
· A5 land cover is Grassland, registered for forestry department
· A8 land cover is Grassland, registered for forestry department
· A9 land cover is Grassland, registered for forestry department
· The suggested activities are:
· Afforestation.
· Erosion control measures.
· Water harvesting.
|  |  | A5 Al- Hashemiyyah 2 | · Grazing management.
|  |  | A8 Al- Hashemiyyah 3 | · Fire-fighting measures.
|  |  | A9/ Al- Hashemiyyah 4 | · Farm Field Schools.
|  |  | A3 Halawah 1 | · A3 land cover is Grassland, registered for forestry department
· A7 land cover is Grassland, registered for forestry department
· The suggested activities are:
· Afforestation.
· Erosion control measures.
· Water harvesting.
· Grazing management.
· Fire-fighting measures.
|  |  | A7 Halawah 2 | · Farm Field Schools.
|  |  | A22 Kufranjah 1 | · A22 land cover is Grassland, registered for forestry department
· A23 land cover is Grassland, registered for forestry department
· The suggested activities are:
· Afforestation.
· Erosion control measures.
· Water harvesting.
· Grazing management.
· Fire-fighting measures.
|  |  | A23 Kufranjah 2 | · Farm Field Schools.
|  |  | A12 Rajeb 22 locations | · All intervention sites land cover is grasslands, registered to forestry department
· Prevent/reduce the negative impact of quarries on vegetation cover (i.e. dust impact).
· Dust control measures due to quarries.
· Afforestation.
· Erosion control measures.
· Water harvesting.
· Grazing management.
· Fire-fighting measures.
Farm Field Schools.
Mafraq Governate | 32.3399 | 36 | A49 Howshah 1 | A49 land cover is Grassland, registered for rangeland department
A50 land cover is Grassland, registered for rangeland department
A51 land cover is Grassland, registered for rangeland department
A57 land cover is Grassland, registered for rangeland department
The suggested activities are:
· Contour tillage and farming.
· Afforestation of indigenous pastoral plants
|  |  | A50 Howshah 2 | · Water harvesting including water-ponding dikes, water spreading-dikes and water excavation to increase water holding in arid-soils.
|  |  | A51 Howshah 3 | · Enhancing value chain of dairy products.
|  |  | A57 Howshah 4 | · Grazing management measures.
|  |  | A48 Mansourah 1 | A48 land cover is Grassland, registered for rangeland department
A52 land cover is Grassland, registered for rangeland department
A53 land cover is Grassland, registered for rangeland department
The suggested activities are:
· Contour tillage and farming.
· Afforestation of indigenous pastoral plants
· Water harvesting including water-ponding dikes, water spreading-dikes and water excavation to increase water holding in arid-soils.
|  |  | A52 Mansourah 2 | · Enhancing value chain of dairy products.
|  |  | A53 Mansourah 3 | · Grazing management measures.
|  |  | A54 Ruwaished1 | · A54 land cover is Hammada vegetation , registered for rangeland department
· The suggested activities are: Soil salinity and drought control measures.
· Deep tillage to break the compaction.
· Contour tillage and farming.
· Afforestation of indigenous pastoral plants which are resistant to soil salinity and drought.
· Water harvesting including water-ponding dikes, water spreading-dikes and water excavation to increase water holding in arid-soils.
· Farm Field Schools.
· Enhancing value chain of dairy products.
· Grazing management measures.
|  |  | A55 Ruwaished 2 | · A55 land cover is Hammada vegetation , registered for rangeland department
· The suggested activities are: Soil salinity and drought control measures.
· Deep tillage to break the compaction.
· Contour tillage and farming.
· Afforestation of indigenous pastoral plants which are resistant to soil salinity and drought.
· Water harvesting including water-ponding dikes, water spreading-dikes and water excavation to increase water holding in arid-soils.
· Farm Field Schools.
· Enhancing value chain of dairy products.
· Grazing management measures.
|  |  | A56 Ruwaished 3 | · A56 land cover is Hammada vegetation , registered for rangeland department
· The suggested activities are: Soil salinity and drought control measures.
· Deep tillage to break the compaction.
· Contour tillage and farming.
· Afforestation of indigenous pastoral plants which are resistant to soil salinity and drought.
· Water harvesting including water-ponding dikes, water spreading-dikes and water excavation to increase water holding in arid-soils.
· Farm Field Schools.
· Enhancing value chain of dairy products.
· Grazing management measures.

## Annex
Annex. Monitoring Area-based GEF Core Indicator Commitments and Progress with FERM
The Framework for Ecosystem Restoration Monitoring (FERM), developed by FAO, is the official monitoring platform for tracking global progress and disseminating good practices for the UN Decade of Ecosystem Restoration. The FERM can serve as an integrated GIS-based platform, providing GEF staff and all relevant stakeholders the chance to display the progress of committed versus achieved land under restoration or under improved management for conservation and sustainable use, along with clear results such as the percentage of project achievement. Having a common tracking and monitoring platform allows users to comprehensively assess and report on project progress. A user-friendly dashboard showcasing project results gives stakeholders a clear understanding of the extent to which project targets have been achieved. Projects with area-based GEF Core Indicators (GEF Core Indicators 1-5 and LDCF Core Indicator 2) are encouraged to register in the FERM platform.
Useful links:
• FERM website
• FERM User Guide (PDF)
• FERM YouTube channel
• Email Carmen Morales
26 It also supports countries in reporting areas under restoration for the Kunming-Montreal GBF Target 2 (areas under restoration) for which FAO is the custodian agency.