WWF GEF Agency

Project Implementation Report

Mainstreaming Biodiversity Conservation in the Tourism Sector of the Protected Areas and Strategic Ecosystems of San Andres, Old Providence, and Santa Catalina Islands (GEF ID 10578)

Project Report information:

| Report Author(s) | Astrid Breuer, Juliana Sintura Arango, Nerieth May Caraballo |
| --- | --- |
| Report Completion Date | September 12, 2025 |

| 1. General Information | PIR Submission Date | September 15, 2025 |
| --- | --- | --- |
|  | Agency Approval Date | November 6, 2022 |
|  | Fiscal Year | FY25 |
|  | Implementation Status (1st PIR, 2nd PIR, Final PIR) | 2nd PIR |
| 2. Current Year Ratings | Overall DO rating | S (87%) |
|  | Overall IP rating | MS (77%) |
|  | Overall Risk rating | Modest |
| 3. Key dates | Actual Implementation Start Date | November 9, 2022 |
|  | First Disbursement Date | November 16th, 2022 |
|  | Expected Mid-Term Review Date | March-May 2025 |
|  | Expected Completion Date | June 30, 2026 |
|  | Expected Financial Closure | December 31, 2026 |
|  | Actual Completion Date |  |
| 4. BUDGET | Total Project Budget (Please indicate amounts under GEF Trust Fund, LDCF, and SCCF) | GEFTF: $2,652,294 |
|  | Total GEF disbursement (USD) through June 30 of the FY for project that has been in implementation for at least 1 FY (Please indicate amounts under GEF Trust Fund, LDCF, and SCCF) | $657,513 |
|  | Committed Co-finance | $21,646,236 |
|  | Materialized Co-finance | $22,164,053 |

PMU Contact information:

| Project Position | Name | E-mail |
| --- | --- | --- |
| F&A Officer | Felipe Cabrales | fcabrales@conservation.org |
| Oceans Director | Pilar Herron | pherron@conservation.org |
| Project Coordinator | Nerieth May Caraballo | nmay@conservation.org |
| M&E Officer | Boyer Robinson | broyer0697@gmail.com |
| Safeguards Specialist | Jose Almeida Alonso | jose.almeida.alonso@gmail.com |
| Local Expert San Andres | Leandra Bent | Leabent@outlook.com |
| Local Expert Providence and Santa Catalina | Sheily Orozco | sheilyarchbold@gmail.com |

WWF GEF Contact information:

| Project Position | Name | E-mail |
| --- | --- | --- |
| Project Manager | Astrid Breuer | astrid.breuer@wwfus.org |
| Safeguards Specialist | Adrienne McKeehan | Adrienne.McKeehan@wwfus.org |
| Gender Specialist | Nathalie Simoneau | Nathalie.Simoneau@wwfus.org |
| RBM Specialist | Amelia Kissick | Amelia.kissick@wwfus.org |
| Finance & Operations Senior Director | Tracey Smith | Tracey.Smith@wwfus.org |
| Co-manager, Freshwater and Marine Ecosystems Specialist | Juliana Sintura | jsintura@wwf.org.co |
| Planning and Monitoring Manager (RBM Support) | Jenny Martinez | jamartinez@wwf.org.co |
| Governance and Social Inclusion Advisor | Carmen Candelo | ccandelo@wwf.org.co |
| Government Affairs and International Relations Director | Ximena Barrera | xbarrera@wwf.org.co |

Instructions:

The WWF GEF Project Manager is responsible for completing the PIR in coordination with the Project Management Unit. It may be necessary to consult with other experts for current data (e.g. Safeguards, Gender, RBM, etc). Please include the following annexed documents:

- Completed Tracking Tool with Results Framework and Annual Work Plan and Budget Tracking (for project year)

- Tracking tools (eg. METT), if applicable

- Knowledge Management products (if links were not provided in the section directly)

- Other supporting documents: meeting minutes, stakeholder consultation, photos, maps, reports, etc.

### Ratings

Fill in all ratings based on the Rating Scale provided in Annex I.

|  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year X |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Development Objective | MS | S |  |  |  |  |  |
| Implementation Progress | MS | MS |  |  |  |  |  |
| Risk | M | M |  |  |  |  |  |

Justification for Current Year Ratings:

A Satisfactory (S) Development Objective (DO) rating is based on the achievement of 87% of the Year 2 indicator targets in the Results Framework. This reflects strong progress in delivering key project outcomes, including the completion of technical studies, stakeholder engagement processes, and early adoption of biodiversity and ecosystem-based management measures. While overall progress is satisfactory, certain indicators under the Development Objective (DO) rating were not achieved as planned, particularly those associated with the operationalization of governance mechanisms and the demonstration of tangible biodiversity outcomes, which remain pending due to delays in implementation. A Moderately Satisfactory (MS) Implementation Progress (IP) rating is justified by the achievement of 77% of the Year 2 targets outlined in the annual workplan. This performance reflects the timely execution of most planned activities, efficient financial management, and effective coordination among project partners and implementing agencies. However, several indicators under the IP rating were not fully achieved, particularly those concerning the punctual delivery of outputs, strict adherence to the approved workplan, and alignment of disbursements with projected timelines. These shortfalls were largely attributable to delays in the selection and contracting processes for consultancies and subgrants. The Modest (M) risk rating reflects a context of ongoing institutional coordination challenges and environmental vulnerabilities in the Archipelago. While risks remain manageable and mitigation measures are in place—particularly regarding procurement timelines, community engagement, and external shocks such as extreme weather events—these require continuous monitoring to prevent impact on long-term delivery. The residual risk for the project is assessed as Moderate (M) rather than Low (L) due to several interrelated factors that persist despite the application of mitigation measures. First, the continued transitions in institutional focal points challenge project coordination—there is an opportunity to strengthen the mechanisms of coordination, highlighting the importance of reinforcing continuity, timely decision making and effective coordination among the project stakeholders and the executing and implementing agencies. Second, the complex governance context of the Archipelago, characterized by overlapping mandates, weak inter-institutional coordination, and inconsistent policy enforcement, continues to present operational risks, particularly for mainstreaming biodiversity into tourism and managing sensitive ecosystems. Third, procurement and selection delays for consultancies and subgrants, although partly mitigated through revised procedures, remain a potential bottleneck for the timely implementation of outputs. In addition, social risks linked to the active consultation processes of the Raizal community under Constitutional Court ruling T-333 of 2022 persist, as these consultations may generate expectations that exceed the scope of the project or delay decision-making at the local level. While gender and safeguards protocols have been developed to mitigate these risks, the potential for misalignment between community expectations and project mandates underscores the need for continuous engagement and adaptive management. Collectively, these risks—governance, institutional, procurement, and social—justify maintaining the overall risk rating at Moderate, as they continue to have a tangible residual effect on project implementation and outcomes.

### Progress, Challenges, and Outcomes on Project Implementation

(Based on Outcomes, Challenges, and Safeguards sections of the Progress Report)

Describe the key outcomes and impacts achieved as well as any challenges during the previous 12 months, using the AWP&B and Results Framework as a reference. Please report by component if feasible. Please note any major positive or negative effects on beneficiaries. Additionally, please summarize progress, challenges and implementation of safeguards for the project. For NGIs only, please indicate any reports and/or public documents—along with links—related to the Agencies’ blended finance projects that include a GEF-supported element. Component 1: Planning and institutional framework for a biodiversity and green recovery focused tourism sector in the MPA, PAs and the three islands of the Archipelago, in the context of the POMIUAC Outcome 1.1. Biodiversity is mainstreamed into tourism for MPA, PAs and three islands of the Archipelago, for improved protection of corals, sandy beaches, mangroves, seagrass, and key species, the PMU of the project has achieved for this first year the following goals related to each output: Output 1.1.1. Interinstitutional coordination group created to advise and accompany the design and implementation of a new sustainable tourism plan for MPA, PAs and the three islands, in the context of POMIUAC, including active participation of the tourism private sector The consultant selected to support the Interinstitutional Coordination Group stepped down in (July/2024). The PMU led the responsibilities related to this output until a replacement was hired, which included: - Assessment of Coordination Gaps - Evaluation of the Interinstitutional Coordination Group’s Role in Tourism and Biodiversity Policy - Interinstitutional Coordination Gaps Assessment Tourism management in the archipelago is hindered by poor coordination among institutions, hindering integration of sustainable development and environmental conservation efforts with local, national and international stakeholders. The assessment identifies five key areas of concern: - Limited Communication & Community Involvement - Local communities, especially the Raizal people, are excluded from decision-making due to poor scheduling, delayed communication, and lack of legal representation. - Weak Public-Private Collaboration - Forums exist but lack authority and coordination, resulting in ineffective decisions and duplicated efforts among diverse stakeholders with different priorities and interests. - Resource Constraints & Management Challenges - Environmental and tourism management efforts are hampered by limited financial and technical resources, as well as bureaucratic delays. The Beaches Committee, for example, struggles to operate effectively due to insufficient funding and staffing. - Policy Misalignment - Conflicting goals between tourism growth and environmental protection lead to unsustainable practices and strain on local agencies. - Regulatory & Implementation Gaps - Environmental plans are under-implemented due to lack of personnel and equipment. Key issues include overcrowding, coral reef damage, unsustainable fishing, and biodiversity threats. - Roles, Responsibilities, and Terms of Reference for the IICG The project identified that poor institutional coordination is undermining the effective management of tourism, biodiversity, and protected area management in the Archipelago. To address this, it: - Developed Terms of Reference for an Interinstitutional Coordination Group (IICG), inspired by successful Colombian models like the Joint Fishing Circular. - Supported the local authorities’ suggestion to revive Ordinance 001 of 2004, which created the Regional Island Tourism Council (CRIT), and use the CRIT as a legal framework for the IICG. - Engaged a Raizal consultant to finalize the IICG structure through comparative analysis of CRIT and the initial proposal. Additionally, the project: - Hired a Raizal consultant to strengthen ties between the tourism sector and community-based organizations. - Implemented a five-phase methodology in late 2024, including 9 workshops, a SWOT analysis and a self-assessment to assess alignment with Global Sustainable Tourism Council (GSTC) criteria. - Selected three key partner organizations based on sustainability commitment, sector leadership, and cultural/environmental impact: - ASOPOSADAS – Promotes cultural heritage and community impact. - ANATO – Educates tourists on sustainable practices and supports ecosystem activities. - ASONTUR – Engages smaller providers and strengthens institutional support. These partnerships aim to expand sustainable tourism leadership, ensure inclusive representation, and enhance project impact across the Archipelago. Between January and June 2025, the project advanced efforts to strengthen collaboration with the tourism private sector across the Archipelago. Key actions included: - San Andrés: Prioritization of stakeholders, verification visits to ANATO agencies and Native Inns, a sustainability workshop, and development of a communications campaign concept. - Providence & Santa Catalina: Sustainability agreements with three enterprises, checklist-based verifications, and exploration of GSTC destination-level certification. - Overall Impact: 17 tourism enterprises engaged (9 Native Inns, 5 ANATO agencies, 3 other businesses). A GSTC-aligned checklist guided monitoring and technical assistance. - Workshop Outcomes: Draft sustainability policies, training logs, and energy tracking formats were developed by Native Inns. - Campaign Concept: “Committed to Sustainability / Wii Lov Seaflower” was created with Native Films to showcase best practices in the tourism sector. Key Lessons Learned - Documentation Strength: ANATO agencies had stronger documentation systems than Native Inns, which needed structured support. - Community Motivation: Tourism operators in Providence were highly motivated, especially due to Hurricane Iota recovery efforts. - Recognition as Incentive: Signage, media, and short clips effectively encouraged participation. - Low Certification Uptake: Only one enterprise (Over Receptour del Caribe) held the NTS-TS-003 certification. Recommendations - Implement periodic coaching to help enterprises complete sustainability documentation. - Provide technical assistance and incentives for certification readiness. - Launch the recognition campaign with symbolic sustainability signage. - Standardize post-training evaluation tools within the monitoring and evaluation framework. - Coordinate a GSTC training cohort to support destination-level certification in Providence. Challenges encountered included limited formal documentation among small enterprises, which was addressed through the provision of templates and guided workshops. Inconsistent post-training evaluation in agencies highlighted the need for standardized tools. Low certification uptake prompted the recommendation to offer technical assistance and peer mentoring via certified actors. In Providence, disaster recovery constraints were addressed by aligning with GSTC destination-level certification efforts to drive broader recovery and sustainability goals. In February 2025, a new consultant was hired to support the PMU in drafting final documents aimed at identifying institutional gaps and enhancing biodiversity mainstreaming in tourism across the Archipelago. The analysis focused on inter-institutional coordination and community involvement. Key findings revealed: - Significant institutional fragmentation in San Andrés, with weak integration between tourism and biodiversity agendas. - Despite this, there is strong potential for improved inter-agency coordination, provided a formal and operative platform is established. - In Providence and Santa Catalina, there is robust community interest in sustainability and greater inclusion in territorial planning, particularly in the context of post-IOTA recovery, which has heightened awareness of long-term sustainability needs. ### Recommendations for Inter-Institutional Coordination (IICG) - Formalize Joint Planning: Across tourism, environment, infrastructure, and law enforcement. - Shared Protocols & Data Systems: Develop interoperable systems linking tourism and biodiversity data. - Community Participation: Institutionalize Raizal representation. - Capacity Building: Address staff turnover and knowledge gaps. - Climate Resilience: Integrate disaster risk management into tourism planning. ### Biodiversity and Tourism Policy Assessment - Relevant Legal Instruments: Include Ley 915/2004, POMIUAC, national ecotourism policies, and international commitments (CBD, UNESCO). - Opportunities for Articulation: - Strengthen governance through a permanent IICG platform. - Integrate biodiversity into territorial and tourism planning. - Coordinate ecosystem management and cultural inclusion. - Align with climate adaptation and monitoring systems. ### Implications for IICG The IICG should serve as: - A permanent, legally backed platform for policy coordination. - A bridge between national and local authorities. - A facilitator of community co-governance. - A knowledge hub for integrated data and adaptive management. ### Implementation Recommendations - San Andrés: Formalize IICG via ordinance or agreement; embed biodiversity and cultural inclusion in planning. - Providencia & Santa Catalina: Build local capacity and align recovery efforts with sustainability goals. Output 1.1.2 Carrying capacity and limits of acceptable change assessments and spatial use analysis of threatened ecosystems of MPA, PAs and three islands for the design of environmental management measures to implement into the tourism sector Substantial progress has been made in creating technical tools to support biodiversity-informed tourism management in the Seaflower Biosphere Reserve. These tools include carrying capacity assessments, spatial use analyses, and limits of acceptable change (LAC), aimed at strengthening institutional frameworks. The Project Management Unit (PMU) and subgrantee CEMARIN organized nine workshops across the Archipelago to: - Advance Protected Area (PA) management goals. - Analyse the impact of tourism planning gaps. - Develop spatial analyses for different user groups in each PA. These workshops included participation from local authorities, community members, and tourism stakeholders. To support Carrying Capacity and Spatial Assessments, CEMARIN produced a draft report reviewing 19 methodologies and proposing a comprehensive, adaptive framework tailored to the Archipelago. The selected methodology integrates: - Physical Carrying Capacity (CAF) – Based on space and visitor density. - Real Carrying Capacity (CAR) – Adjusted for ecological and social factors. - Effective Carrying Capacity (CAEf) – Considers management capacity and infrastructure. - Adaptive Management – Emphasizes ongoing monitoring and responsive adjustments. This integrated approach aims to balance tourism growth with ecological sustainability and community involvement. Deliverables B and C from CEMarin showcase strong technical and participatory approaches, ensuring stakeholder engagement and local relevance. The process began with a participatory diagnosis involving various stakeholders, leading to the identification of over 80 tourism units of analysis (UAs). Fourteen priority UAs were selected across San Andres, Providence, and Santa Catalina based on ecological sensitivity, tourism activity, accessibility, and management challenges. San Andres priority sites include: Spratt Bight, West View, Rocky Cay, Sound Bay, Johnny Cay, Haynes Cay – Rose Cay, White Watta, Old Point (Magrove) Regional Park Providence and Santa Catalina sites include: Southwest Bay, Manchineel Bay, Almond Bay, Freshwater Bay and Fort Warwick in Santa Catalina. A comprehensive and context-sensitive methodology for calculating tourism carrying capacity (TCC) was developed and validated. This methodology integrates four key components: physical, ecological, psychological, and institutional capacity. - The physical carrying capacity (PCC) assesses the physical space available for tourism activities. - The ecological carrying capacity (ECC) evaluates the resilience and vulnerability of ecosystems such as coral reefs, seagrass beds, mangroves, and beaches. - The psychological carrying capacity (PSC) considers perceptions of crowding and visitor satisfaction. - Finally, institutional management measures the ability of local authorities to regulate, monitor, and support sustainable tourism. These elements are synthesized into a final Real Carrying Capacity (RCC) index, tailored to each site’s conditions. Parallel to carrying capacity efforts, CEMarin began identifying preliminary indicators for defining Limits of Acceptable Change (LAC) at selected tourism sites. Using a locally adapted State–Pressure–Response model, they proposed ecosystem-specific indicators such as coral condition trends, live coral and seagrass cover, coastal cleanliness, water quality, and mangrove health. These were preliminarily validated with CORALINA and will inform future monitoring and adaptive management. Next steps, based on Deliverable C, include: - Finalizing carrying capacity calculations for all prioritized sites - Launching pilot monitoring using the developed protocol - Conducting participatory validation workshops with communities and institutions The results will be integrated into CORALINA’s and the Secretariat of Tourism’s planning frameworks, supporting evidence-based tourism management. Deliverable C significantly advances Output 1.1.2 by providing a scientifically sound and socially inclusive foundation for managing tourism impacts. The tools and recommendations contribute to long-term biodiversity conservation, institutional coordination, and sustainable tourism governance in the Seaflower Biosphere Reserve. Output 1.1.3 Sustainable Tourism Plan (STP) developed and under early implementation stages by responsible authorities (CORALINA and the Tourism Secretariat), as part of the POMIUAC Under this output, the Sustainable Tourism Plan (STP) is being developed and initiated by CORALINA and the Tourism Secretariat, as part of the POMIUAC framework. The STP is guided by Law 2068 of 2020, which requires that Sectoral Tourism Development Plans include strategies for conserving, restoring, and protecting public assets designated as tourist attractions. These plans must also feature an action plan for sustainable tourism, aimed at managing tourism’s environmental impacts and ensuring long-term viability. The plan aligns with national sustainability guidelines issued by MinCIT and its methodology draws from tools like the Technical Assistance Manual and MDTT to assess the current state of a destination and identify areas needing focused management or investment. Given the Archipelago’s ecological significance—including its designation as a UNESCO Biosphere Reserve and the presence of the Seaflower Marine Protected Area—the Tourism Environmental Plan (PAT) was selected. This model prioritizes environmental planning (including the promotion of sustainable nautical tourism through responsible practices, clean energy use, and biodiversity conservation) and integrates actions from the POMIUAC Insular plan to protect cultural and ecological heritage. The baseline assessment for the Tourism Plan has been completed, which included. - 23 workshops (13 in San Andrés, 10 in Providencia and Santa Catalina), some in collaboration with National Natural Parks (NNP) to support the McBean Lagoon Ecotourism Management Plan. - Baseline assessment and SWOT analysis validated through community and authority participation. - Strategic alignment with the Departmental Government’s tourism policy. - Commitment from the Mayor’s Office of Providencia and Santa Catalina to formalize the STP by December 2025, supported by the GEF Seaflower Project. The plan emphasizes inclusive governance, environmental sustainability, and local engagement to ensure long-term viability of tourism in the Archipelago. The third product of the consultancy, focused on analysing the tourism policy and regulatory framework in the Archipelago of San Andrés, Providence, and Santa Catalina, was developed in collaboration with the Interinstitutional Governance Committee (IICG), aimed to: - Review tourism policies and regulations at national, departmental, and local levels. - Analyse secondary data on the tourism sector. - Develop a conceptual map to diagnose the tourism system. Using document review and comparative policy analysis, the study evaluated how tourism intersects with environmental and socio-cultural priorities. It assessed over 30 planning and policy instruments, including the National Tourism Development Plan (PNTD), the Departmental Tourism Plan, and CORALINA’s Environmental Management Plan (POMIUAC). While not island-specific, the analysis reflects the broader tourism governance landscape of the archipelago and highlighted institutional fragmentation, overlapping mandates, and a lack of updated data as major governance challenges. The study found that while many tourism regulations exist, they are often outdated, fragmented, and poorly adapted to the archipelago’s biocultural and ecological context. It also noted limited integration of local cultural values and environmental priorities in current strategies, and weak coordination among agencies. Despite these issues, the consultancy identified institutional willingness to collaborate and recognized tourism as a key economic driver. It emphasized the need for: - Improved coordination among tourism and environmental authorities. - Integration of socio-environmental and cultural criteria into planning. - Inclusive, participatory approaches that reflect local realities. Recommendations include: - Updating and harmonizing tourism policies. - Establishing formal coordination mechanisms among CORALINA, the Departmental Secretariat of Tourism, MINCIT, and FONTUR. - Institutionalizing community participation and traditional knowledge in tourism planning. Workshops held in January and February validated findings and initiated co-construction of the STP’s vision. ### Beach Certification Process ATUCA Foundation was selected to lead the consultancy under Output 1.1.3, which assesses the feasibility of implementing international beach certification schemes—particularly the Blue Flag certification—in the Archipelago of San Andrés, Providence, and Santa Catalina. The goal is to promote sustainable beach management that respects environmental and cultural contexts. Key objectives include: - Identifying viable certification frameworks (international, regional, national) - Evaluating demand and awareness among tourists and businesses - Prioritizing beaches with the highest potential for certification - Validating candidate beaches through a participatory, inclusive, and ethnic-territorial approach The consultancy used a mixed-method approach to ensure both technical rigor and community engagement. In the second half of 2024, ATUCA: - Developed a draft report analysing existing beach certification standards and their feasibility. - Conducted 15 workshops across the three islands with community, private tourism organizations, and authorities. - Performed a cross-analysis of physical, ecological, social, and cultural factors to identify suitable certification schemes—four viable options were found: Blue Flag, Colombia’s NTS001-2 standard, the Seascape Certification for Coastal Landscapes, and the “Ranking of Best Beaches,” which is transitioning into a certification mechanism. Key developments include: - Beach Inventory - 27 Beaches were identified using diverse sources (authorities, communities, technical documents, tourist feedback): 15 in San Andrés, 10 in Providence, and 2 in Santa Catalina, with 13 ultimately identified as having the highest potential for certification. - Revealed communication and governance gaps in beach management. - Beach Prioritization - Ten beaches assessed using NTS 001-2 (2024) criteria. - A digital tool is being used to rank beaches based on certification potential. - Participatory Validation - Workshops and surveys gathered feedback to assess each beach’s strengths and weaknesses for environmental, social, or economic certification. In the first half of 2025, ATUCA assessed 34 beach certification schemes at global, regional, and national levels. Blue Flag emerged as the most recognized for its strong sustainability standards across four pillars: water quality, environmental management, education, and safety/services. However, it poses high operational costs and logistical demands, such as monthly water testing and continuous compliance. Colombia’s NTS001-2 standard (updated in 2024) aligns with Blue Flag criteria and offers a more accessible pathway to international recognition. Other alternatives include the Seascape certification and the Ranking of Best Beaches, which are suitable for rural or less urbanized beaches due to their focus on aesthetic and ecological indicators. However, Seascape currently lacks visibility and has limited application in Colombia. The consultancy successfully delivered a prioritized beach inventory and feasibility study for certification in the Archipelago of San Andrés, Providence, and Santa Catalina. Key deliverables included: - Cost analyses for certification schemes - Institutional contact directories - Management toolkits - Technical data sheets for 13 prioritized beaches - Participatory validation with local stakeholders Recommendations for certification efforts: - San Andrés: Focus on Spratt Bight, Rocky Cay, Sound Bay, and Haynes & Rose Cay, leveraging existing management tools and initiating formal applications for Blue Flag or NTS001-2. - Providence and Santa Catalina: Pursue lower-cost, community-driven schemes like Seascape, due to limited infrastructure and ecological sensitivity. These findings provide actionable guidance for decision-makers and support sustainable, inclusive beach management across the archipelago. The consultancy’s work covered the entire Archipelago of San Andrés, Providence, and Santa Catalina, with activities tailored to each island’s context. Key stakeholders included Raizal communities, CORALINA, local and departmental governments, tourism agencies, and private operators. Community participation was central to ensuring cultural relevance and stakeholder buy-in. Findings: - Of the 33 Blue Flag criteria, 9 had available data (2 general, 7 beach-specific), with Rocky Cay showing the highest readiness. - For NTS001-2, 16 of 138 criteria had documented progress, with Rocky Cay, Sound Bay, and Haynes/Rose Cay leading. - Seascape certification had limited coverage (2 of 26 criteria). - The Ranking of Best Beaches had data for 8 of its 20 indicators. These results provide a strong foundation for advancing sustainable beach certification and improving tourism governance in the archipelago. Key challenges included: - Lack of consolidated beach-level data - Gaps in water quality monitoring - Absence of an inter-institutional coordination framework These were mitigated through data triangulation and capacity-building workshops. However, full implementation of certifications—especially Blue Flag—will require additional funding, stronger institutional collaboration, and ongoing technical support. The consultancy’s final product, validated by the technical committee on May 13, lays the groundwork for using beach certification as a strategy to enhance the resilience, competitiveness, and sustainability of coastal tourism in the archipelago. Output 1.1.4 Technical assistance to local authorities to mainstream biodiversity conservation in the design and development of green and grey infrastructure projects (in the context of the POMIUAC and updated tourism plan) The consultancy under this output focused on integrating green and grey infrastructure into territorial planning in the Archipelago of San Andrés, Providence, and Santa Catalina, and was integrated into the existing agreement with CEMARIN, as approved by the Steering Committee (Act 003). Together with CEMARIN, the team developed a diagnostic report to explore the feasibility of applying green-gray infrastructure principles in the Archipelago. The report includes: - Assessment of Current and Planned Infrastructure - Review of existing and proposed projects to understand scope and condition. - Map Local stakeholders and their Capacity and Resources - Analysis of local authorities’ capabilities and needs for planning and implementation. - Identification of Challenges and Opportunities - Exploration of barriers and potential for integrating biodiversity into infrastructure. - Strategic Recommendations - Guidance and materials to promote biodiversity-friendly infrastructure based on findings. Key deliverables of the consultancy include: - Mapping of existing and potential IVG projects - Stakeholder map with over 100 institutions - Analysis of challenges and opportunities for IVG integration Methodology: - Documentary review of global and local IVG literature - Field visits and interviews in Providence, Santa Catalina (Nov 7–8, 2024), and San Andrés (Dec 7–13, 2024) - Data analysis of infrastructure types, stakeholder roles, and biodiversity integration opportunities Findings: - In San Andrés, key actors included IDEAM, CORALINA, Universidad Nacional, DIMAR, and community groups. Projects like coastal protection and decentralized waste/water management were identified, though IVG terminology was not widely known. Stakeholders reported a willingness to engage in IVG approaches but highlighted the need for training, technical guidance, and sustained inter-agency coordination. - In Providence and Santa Catalina, post-hurricane reconstruction offered opportunities for IVG, especially in coastal restoration. Strong community interest in ecosystem-based planning was noted - Challenges: Limited IVG awareness, fragmented planning, weak data systems, and preference for traditional “grey” infrastructure. - Opportunities: Integration of IVG into planning instruments, community education, alliance-building, and hybrid solutions using natural features. Recommendations: - Build on past projects to strengthen institutional memory - Embed IVG principles in land-use planning - Develop long-term monitoring systems - Co-design infrastructure with communities - Increase IVG visibility in policy discourse - Seek national/international financing - Promote education linking ecosystems and society Progress: Output 1.1.4 is partially achieved, with foundational work completed but further technical assistance and implementation needed. The consultancy lays a strong foundation for mainstreaming biodiversity in infrastructure development and enhancing cross-sectoral coordination. Component 2: Management of tourism impacts on key biodiversity of the MPA, PAs and the three islands Outcome 2.1 Reliable information about tourism impacts on coral reef, seagrass, sandy beaches, mangroves, and key species in MPA, PAs and three islands is used by decision makers to respond to environmental threats Output 2.1.1. Training, technical assistance and operational support for development and implementation of a tourism impact monitoring program on 4 threatened ecosystems (mangroves, seagrass, corals, and sandy beaches) and Output 2.1.2 Training, technical assistance and operational support for development and implementation of a tourism impact monitoring program for four (4) species most sensitive to tourism The consultancy for these outputs aims to develop and implement a monitoring program to assess tourism impacts on key ecosystems and species in the Seaflower Biosphere Reserve. Its goals include: - Strengthening local capacities. - Providing tools for evidence-based decision-making in biodiversity conservation and sustainable tourism. Specific Objectives - Identify priority species and ecosystems vulnerable to tourism. - Define units of analysis and monitoring indicators. - Propose locally adapted protocols. - Lay the technical foundation for a long-term monitoring strategy aligned with territorial planning (POMIUAC, updated Tourism Plan). A baseline study was completed to evaluate existing data for monitoring strategic ecosystems and species. A draft protocol was also developed to assess tourism’s impact on these ecosystems. #### Key Components of the Monitoring Methodology: - Literature Review - Compilation of existing monitoring methods and baseline data. - Site Prioritization - Focus on areas with high tourism activity. - Impact Identification & Method Selection - Analysis of ecosystem types and tourism activities to determine relevant impacts and monitoring approaches. - Ecosystem Mapping - Detailed assessments needed to identify strategic ecosystems and tourism pressures, refined through fieldwork and community input. - Monitoring Framework - General structure outlined; site-specific activities to be finalized later. #### Monitoring Variables: - Initial indicators proposed to track tourism impacts and ecosystem health. - Variables and frequency will be adjusted based on field data and community feedback. #### Species Selection Criteria: - Island-Specific Differences – due to differences in tourism activities - Feasibility & Sustainability 0 cost-effective and technologically feasible monitoring to ensure durability - Tourism Interaction & Cultural Relevance – the relationship between species and tourism, including cultural significance An example of emerging complexity is the octopus extraction driven by tourist demand, which is harming coral reefs. CORALINA will finalize the species list and monitoring protocol in the second half of 2025 and begin training relevant authorities. ### Initial activities - Multidisciplinary approach: literature review, participatory consultations, spatial analysis. - Reviewed 80+ sources and technical inputs from CORALINA, Parques Nacionales and Gobernación. - Validated priority ecosystems (mangroves, seagrass beds, coral reefs, sandy beaches) and species (black land crabs, queen conch, sea turtles, long-spined sea urchins). Consultations - Held in San Andrés and Providence with 25+ stakeholders (e.g., CORALINA, local government, universities, community groups). - Helped validate indicators and assess environmental monitoring capacities. ### Technical Outputs - Defined Units of Analysis for each ecosystem and species considering ecological boundaries, tourism use zones and data availability - For example, for coral reefs and seagrass, existing monitoring stations and marine zoning plans were used to delineate priority areas - For species, population dynamics and reproductive behaviour were considered to align monitoring efforts with seasonal tourism trends and habitat sensitivity - Proposed: - Monitoring framework for 4 ecosystems and 4 species. - Priority monitoring sites. - 10 ecosystem and 8 species indicators. - Data collection protocols. - Feasibility analysis (tech and human resources). ### Findings - San Andrés: high tourism pressure zones overlapping with seagrass and coral reefs identified (e.g., Johnny Cay) – while ongoing monitoring efforts exist, these are fragmented and not explicitly linked to tourism impact. - Providence: opportunities for integrating tourism monitoring into post-Hurricane Iota recovery conservation infrastructure and community-based initiatives. ### Lessons Learned - Need for institutional coordination and unified monitoring to develop shared vision for impact management. - Importance of local knowledge and community involvement for tourism monitoring in culturally and ecologically sensitive areas - Importance of adaptive systems that can integrate traditional scientific approaches with community-led observations. ### Recommendations - Strengthen inter-institutional network under CORALINA. - Train local actors including community monitors and tourism service providers. - Pilot indicators in selected sites to validate practicality and relevance. - Integrate results into decision-making platforms e.g. Environmental Observatory and updated STP. - San Andres: begin with areas of high visitation and conflict; Providence: nesting sites and low-impact tourism areas ### The consultancy completed critical baseline assessments, defined indicators and protocols, and generated technical inputs needed for monitoring implementation. While field implementation is pending, the groundwork has been laid for robust and contextually appropriate monitoring systems. ### Challenges - Limited species-tourism data. - Fragmented monitoring across institutions. - Need for operationalization of technical proposals. Outcome 2.2 Improved capacity of CORALINA and local authorities to effectively mitigate tourism impacts and manage corals, sandy beaches, mangroves, seagrass, and associated species in the MPA and Pas Output 2.2.1. Training and technical assistance to CORALINA and tour operators to develop and implement emergency management measures for key species and ecosystems impacted by tourism in the MPA, PAs and three islands, and education and awareness to tourists on interactions with critical ecosystems and sensitive species In July 2024, ECOISLAS SAI BIC was selected to develop a Tourist Environmental Education Program for tourism service providers in the Archipelago of San Andrés, Providence, and Santa Catalina, promoting biodiversity-friendly behavior and sustainable tourism practices. Objectives of the consultancy - Characterize tourism service providers and their interactions with natural resources. - Develop a pedagogical and technical training program tailored to the local sociocultural and ecological context. - Implement and evaluate a pilot phase to inform future scaling. #### Initial Activities: - Reviewed 80+ documents on tourism and biodiversity. - Four participatory workshops and consultations with local experts and institutions held (2 in San Andrés, 2 in Providencia and Santa Catalina). - Engaged raizal communities, tourism actors, and CORALINA. - Surveys conducted with tourism service providers: - 96 in Providencia and Santa Catalina. - 386 in San Andrés. #### Key Outputs: - Characterization of tourism service providers completed. - Environmental Education Program design delivered in December 2024. - Training content Structure - Four pedagogical pillars: - Biodiversity and territory - Empowerment for sustainability - Business formalization - Digital innovation and visibility Due to strong support from communities and institutions, the Steering Committee approved the program’s implementation by amending the existing grant. Pilot Implementation - Key stakeholders: tourism cooperatives, local guides, restaurants, NGOs, academic institutions, and environmental authorities. - San Andrés: Coonative Brothers cooperative. - Providence: ASOCRAB, Discovery Old Providence, and independent providers. San Andrés - Partnered with Coonative Brothers cooperative. - Four weekly sessions (starting April 30, 2025). - Topics: biodiversity and sustainable tourism principles, environmental best practices and ecotourism experience design, legal formalization and sustainable business development, digital marketing tools and AV - 8 participants completed the training. - Certification pending SENA validation. Providence and Santa Catalina - Two-day workshop (May 6–7, 2025). - 18 participants (14 completed). - Topics: marine/terrestrial biodiversity, responsible tourism, carrying capacity, waste management, circular economy, responsible tourism behaviour, technologies and strategies for managing greywater, reducing single-use plastics, and integrating renewable energy. - Participants included ASOCRAB, Discovery Old Providence, community restaurants, and marine guides. - Many had no prior formal training. Key Contributions - Strengthened awareness of local ecosystems and sustainable practices. - Promoted responsible tourism behaviour and business formalization. - Introduced digital tools for visibility and marketing. - Fostered community engagement and capacity building. Findings from the implementation process: - San Andrés: - High tourism pressure on ecosystems highlighted the need for better water, waste, and energy management. - Participants showed interest but had limited availability due to work commitments, affecting consistent engagement. - Providence and Santa Catalina: - Tourism is less intensive and more community-based, leading to stronger participation and interest in integrating sustainability principles into daily operations. - Informal service providers expressed a need for training and support in business visibility. - Cross-Island Insights: - Less than 0.5% of tourism providers have sustainability certifications. - Around 24% of the sector operates informally, limiting access to financing and institutional support. These findings reinforce the importance of environmental education as a transformative tool for promoting sustainable tourism and empowering local communities in tourism governance. Island-Specific Recommendations - San Andrés: - Use a modular and flexible training format to accommodate participants’ work schedules. - Focus on pollution control, energy efficiency, and waste management. - Providence: - Build on existing ecotourism and community-based initiatives. - Integrate digital tools to improve outreach and competitiveness. General Recommendations - Launch awareness campaigns targeting both tourists and community members. - Improve coordination with institutions like CORALINA and SENA to support certification. - Integrate program outcomes into tourism zoning and planning to enhance regulatory impact. Progress and Contributions - Substantial progress under Output 2.2.1: - Successfully tested the educational model. - Engaged key stakeholders. - Produced materials and insights for replication. Challenges: - Inconsistent Participant availability. - Literacy levels. - Institutional delays in certification. - Addressed through participatory methods, visual tools, and culturally adapted content. Output 2.2.2. Training and operational support to CORALINA, Departmental Government, and DIMAR authorities (including basic equipment, maintenance, and field supplies) for improved management (including control and surveillance) of key threatened ecosystems and species ECOISLAS + HABITAT was contracted to design and implement a comprehensive action plan to monitor and manage tourism’s effects on biodiversity. #### Key Activities for the Needs Assessment (Dec 9–23, 2024): - Workshops & Planning Sessions - Held on both islands with 21 participants from institutions like CORALINA, DIMAR, Aerocivil, and local government. - Focused on inter-agency coordination, environmental education, and policy implementation. - Field Assessments - 17 interviews conducted with officials to gather insights on tourism-related biodiversity impacts. #### Main Findings & Recommendations: - Challenges Identified - Limited staffing, outdated equipment, weak enforcement, overpopulation, and uncontrolled tourism. - Equipment & Training Needs - Upgrades to computer systems, acquisition of field tools (e.g., probes, drones, GPS), and specialized software. - Capacity Building - Suggested campaigns, drone pilot certification, and GIS training. - Information Analysis - Reviewed institutional documents, scientific literature, and case studies from similar island contexts. With the needs assessment report completed, the next step was for the sub-grantee to prioritize identified needs and resources for implementation. As part of the implementation of the Control and Monitoring Plan for Tourism Impacts on Biodiversity in the Archipelago of San Andrés, Providence, and Santa Catalina, a strategic framework was developed to: - Strengthen institutional capacities. - Improve environmental monitoring. - Promote sustainable tourism practices. Built on Agreement 002 of 2019 (which defines the zoning of the archipelago and delineated permitted and restricted tourism activities), the plan focuses on enforcement and coordination rather than new regulations. Objectives - Enhance operational capacity of CORALINA, DIMAR, and the Departmental Government. - Support control and surveillance of ecosystems and species affected by tourism. - Align with POMIUAC and Seaflower MPA zoning strategies. - Includes targeted training, provision of essential equipment and field supplies and logistical support to improve monitoring enforcement mechanisms in marine and coastal zones Methodology - Diagnostic analysis, interinstitutional coordination, and logistical planning. - Developed a situational analysis informed by patrol reports, staffing availability and institutional mandates with CORALINA, DIMAR and the Departmental Government and Action Plan for San Andrés, Providence, and Santa Catalina including priority strategies supported by the project. Key Activities San Andrés - Supported interinstitutional working groups, surveillance gaps analysis and participatory mapping. - Identified critical sites: Rocky Cay, Johnny Cay, Haynes Cay, Rose Cay. - Defined patrol frequencies and institutional roles: - CORALINA: environmental oversight. - DIMAR: maritime control. - Departmental Government: public safety and operations. - Proposed rotating patrol calendar and monthly coordination meetings. Providence and Santa Catalina - Focused on enhancing local enforcement capacity and addressing structural gaps. - Collaborated with community guides and NGOs. - Identified priority areas: Crab Cay, Three Brothers, coral zones. - Proposed decentralized support: fuel subsidies, joint inspections, community ranger training. Deliverables - Finalized needs assessment and gap analysis. - Draft Action Plan for tourism control and surveillance in sensitive ecosystems with patrol maps institutional responsibilities and schedules. - Identified equipment and supply needs for patrol operations (GPS, radios, uniforms, monitoring tools). - Achieved interinstitutional consensus on planning and resource deployment. - Defined indicators for tracking progress (e.g., patrol frequency, incident reports, compliance rates). To ensure strategic alignment and implementation, five integrated strategies guide the operationalization of this plan. - Zoning Enforcement and Monitoring - Aims to reduce tourism pressure on fragile ecosystems (coral reefs, mangroves, beaches). - Supported by stakeholder outreach, workshops, operator training, and improved signage. - Environmental Monitoring with Technology - Utilizes drones, water quality sensors, surveillance cameras, and platforms like Wildbook and NEAT+. - Enables real-time environmental threat detection and encourages community participation in data collection and response. - Solid Waste Management - Addresses increased waste from tourism. - Includes public education campaigns on waste separation, inspections, and circular economy initiatives for sustainable reuse and business models. - Ecosystem Conservation - Focuses on highly impacted ecosystems (mangroves, coral reefs, dry forests). - Actions include seasonal monitoring, awareness workshops, and real-time equipment deployment to minimize ecological disturbance and promote community responsibility. - Communication and Outreach - Promotes responsible tourism using the archipelago’s UNESCO Biosphere Reserve status. - Implements multi-platform campaigns, signage, and youth environmental promoter training to promote responsible tourism and biodiversity stewardship. A five-year Action Plan supports the implementation strategies with: - Detailed activities (e.g., patrols, education campaigns, equipment procurement). - Indicators, responsible entities, timelines, and geographic coverage. - Active participation from institutions, communities, and tourism operators. Financial Sustainability - Funding sources: departmental budgets, CORALINA, international cooperation, and the private sector. - Promotes long-term tools like ecotourism revenues and environmental service payments. - Supports replication of successful pilots across the archipelago. Monitoring and Evaluation - Includes a biannual review framework, indicator tracking, and stakeholder feedback for adaptive management. Progress and Status - Significant progress under Output 2.2.2: - Diagnostic and planning phases completed. - Draft Action Plan is in advanced form, pending validation. - Differentiated strategies for San Andrés and Providence & Santa Catalina. - Engaged stakeholders: CORALINA, DIMAR, Departmental Government, Tourist Police, community guides, Old Providence Foundation, and tourism associations. Challenges and Recommendations - Challenges: slow institutional coordination, procurement delays, high operational costs in remote areas. - Addressed through: interagency cooperation, shared logistics, fuel subsidy exploration. - Key recommendations: - Accelerate patrol equipment delivery. - Launch joint field training based on Action plan. - Integrate community to existing surveillance networks, mechanisms and efforts from institutions and authorities. - Ensure adaptive planning via bimonthly reviews. The plan offers a comprehensive, participatory, and tech-enabled roadmap for aligning tourism with biodiversity conservation in the Seaflower Biosphere Reserve. It reflects a strong multi-actor commitment to building a sustainable, inclusive, and ecologically responsible tourism model. Outcome 3.1 Sustainable use of corals, seagrass, sandy beaches, mangroves, and key species is mainstreamed into existing local tourism initiatives Output 3.1.1. Participatory selection of at least 5 local tourism businesses from an existing portfolio with potential to mainstream biodiversity and development of their action plans The main objective of this consultancy is to establish a baseline and select local tourism businesses in the Archipelago of San Andrés, Providence, and Santa Catalina with potential to integrate biodiversity and sustainability into their operations—supporting community-based tourism, biodiversity conservation, and local livelihoods. Specific Goals of the consultancy: - Identify and characterize businesses engaged in or open to adopting sustainable practices, based on principles of biodiversity conservation, circular economy, and community inclusion. - Develop strategic action plans for selected businesses to mainstream biodiversity in tourism services and products. #### Key Achievements: - Stakeholder Engagement - Conducted across San Andrés, Providence, and Santa Catalina. - Engaged local communities and authorities such as ANATO, ASOPOSADAS, DIMAR, FONTUR, Migración Colombia, CORALINA, Departmental Tourism and Planning Secretariats, SENA, Raizal community councils, tourism operators, entrepreneurs, academic institutions, and green economy networks. - 162 participants: 60% women, 72% Raizal community, 82% from local communities. - 20 semi-structured interviews with institutional actors. - Baseline & Business Profiling - Identified 4,000 tourism-related actors linked to CORALINA’s Green Business Window or other sustainability initiatives. - Produced a baseline report detailing socioeconomic, environmental, and operational profiles of businesses with sustainability potential. - Data refinement ongoing with support from CORALINA. - Profiling includes economic, sociocultural, legal, environmental, and technological dimensions using tools like ATDI (2020) and Sustainable Biotrade Corporation (2022). - Data was disaggregated by gender and ethnicity: - 78% raizal participants - 69% women — indicating strong inclusion. - Tourism Business Analysis - Focused on sustainable, community-based businesses using an ethno-territorial approach. - Identified 60+ local tourism initiatives with sustainability potential - Selected a subset for future support in developing detailed action plans. - Included ventures in ecotourism, local gastronomy, artisanal crafts, and cultural tourism, many led by women and raizal community members. - Characterization based on: - Alignment with green business principles - Ecological footprint - Readiness to integrate biodiversity - Green Business Identification - 35 green businesses identified: 3 certified by the Ministry of Green Business. - 60 pending certifications, with data requested from CORALINA. - 24 additional initiatives identified through workshops led by Fundación ATUCA. - Outcomes - Preliminary selection criteria and funding priorities defined. - A scoring system for selecting sustainable tourism initiatives is under development. Key Results Findings - San Andrés: - High tourism traffic but challenges with institutional fragmentation, technical support, and market access. - Growing awareness of environmental issues and willingness to adopt sustainable practices. - Providence & Santa Catalina: - Strong interest in sustainability post-Hurricane Iota. - Challenges include limited infrastructure and weak institutional support. Recommendations - Provide technical and financial support to formalize sustainability action plans. - Align with CORALINA’s Green Business Window for regulatory guidance. - Offer continuous capacity building to business owners in in biodiversity monitoring, sustainable service delivery, and marketing. - Strengthen institutional coordination to improve access to financing and infrastructure. Progress and Contributions - Achieved key milestones for Output 3.1.1: - Completed baseline and initial business portfolio. - Established conditions to select at least five businesses for further support. - Action plans are pending, but groundwork is complete for next implementation phase (starting second semester of 2025). Challenges and Solutions - Delays in data collection due to limited actor availability and logistical constraints (especially post-Iota in Providence). - Addressed through hybrid engagement methods and strong community collaboration. Component 4: M&E, awareness raising and knowledge management Outcome 4.1 Informed and adaptive project management Output 4.1.1. Project M&E plan implemented and PPRs developed and completed - The annual work plan and budget for year 3 of the project was presented to the Project Steering Committee on December 10th, 2024, for approval and will be implemented during 2025. - The annual project progress report for year two was presented on January 31st - The financial Audit was finished by June-2025, and the report was sent to WWF-GEF - A Technical Committee meeting was held in XX, bringing together representatives from Ministry of Environment, CORALINA, Governor’s Office, Municipality of Providence, WWF and CI. The objective of the meeting was to review progress of consultancies and agreements under the GEF Seaflower Project. In the meeting, partners reaffirmed alignment with regional development plans and national policies. - Consultancy Updates - EcoIslas: Progress on Environmental Education Program and certification for tourism providers. - CEMarin: Studies on tourism carrying capacity and green-gray infrastructure. - Native Films: Continued rollout of the “Wii Lov Seaflower” communication campaign. - Fundación Atuca: Advances in sustainable business mapping and beach certification. - Recommendations - Formalize roadmap for environmental education program implementation. - Enhance tourist outreach via mandatory audiovisual content. - Continue inter-institutional coordination for a Sustainable Environmental Tourism Plan. - Clarify: - Tourism typologies - Carrying capacity definitions - Beach and business certification frameworks - Several outputs are ready for institutional adoption. - Ministries and local authorities urged to lead formalization. Output 4.1.2. Annual reflection meeting to track progress against work plan and results framework indicator targets for effective adaptive management - On September 11, 2024, the fourth Technical Committee session was held to present workplans and methodologies from project grantees and consultants. - The Annual Reflection Meeting took place on November 7, 2024, in Providencia, alongside a Technical Committee session. It reviewed project progress and introduced the Annual Work Plan (AWP) for Year 3. - Feedback from committee members was incorporated into the revised AWP, which was presented during the Project Steering Committee (PSC) meeting on December 10, 2024. - During the PSC meeting, participants discussed project challenges and explored adaptive management strategies aligned with project guidelines and local realities. Outcome 4.2 Knowledge Management communications and dissemination Output 4.2.1. Cross-sectoral communication strategy and knowledge products developed. Native Films conducted meetings, school visits, consultations, interviews, and surveys to identify communication gaps in biodiversity conservation across the Archipelago. These efforts informed a gap analysis that is now guiding the development of a comprehensive and participatory communication strategy rooted in local values that amplifies conservation messaging and encourages behavior change among residents, tourism operators, and other stakeholders across the Archipelago of San Andrés, Providence, and Santa Catalina. - The strategy aims to produce at least two knowledge products per year and use diverse formats and tools to engage residents, tourism operators, and stakeholders. - From March-June 2025, Native Films carried out 13 workshops and 20+ interviews across the archipelago. - Created a Community Analysis Matrix to capture communication preferences, trusted information sources, perceptions of past campaigns and thematic priorities. - Participating stakeholders: CORALINA, Departmental Government, Mayor’s Office of Providence, neighbourhood boards, schools, tourism associations, youth groups, environmental educators, local media, and raizal communities. #### Key Findings: - Past Campaigns - Used diverse formats (visual media, workshops, social media, scientific outreach). - Impact was limited due to poor coordination and lack of formal evaluation, leading to ineffective messaging and missed opportunities for meaningful change. - Survey Insights - While awareness of the Seaflower Biosphere Reserve is high, understanding of its ecological importance is limited. - Strong community interest in participating in future conservation communication efforts. - Need for long-term, culturally resonant and localized conservation messaging. - Importance of Raizal perspectives, traditional storytelling formats, and inclusive language. - Institutional trust gaps and fatigue from short-term campaigns. Recommendations: - Host inclusive community meetings to share findings and foster dialogue. - Create collaborative spaces for co-designing the communication strategy. - Ensure accessibility and relevance for all community members and visitors. - Develop a coordinated, sustainable approach to strengthen biodiversity conservation through effective communication. - Ensure consistent visibility across platforms. - Align with local educational institutions. - Build capacity for community ambassadors and tourism operators. - Tailor strategies: - San Andrés: Reinforce trusted channels e.g. radio, schools, TV and Whatsapp (due to skepticism toward institutional campaigns). - Providence & Santa Catalina: Focus on localized content, capacity building in biodiversity messaging and cultural programming (preference for Creola and school-based outreach). Deliverables and Progress - Draft cross-sectoral communication strategy in development. - Two audiovisual products in production: - Short documentary on the Seaflower Reserve. - Testimonial video featuring local voices. - Community Analysis Matrix completed, offers structured overview of communication gaps, opportunities and strategies customized to each territory. - Output is partially delivered, aligned with Year 3 targets. ### Challenges ### Transitions in leaders/project focal points: The project has consistently benefitted from the Ministry of Environment’s strategic guidance and high-level commitment since its formulation, which has been essential to its progress and legitimacy. Building on this leadership, there is now an opportunity to strengthen coordination, communication, and continuity throughout implementation. ### Complexities in Providence and Santa Catalina: In these islands, implementation has been particularly difficult due to an ongoing consultation process mandated by Colombia’s Constitutional Court. This process, initiated as a response to Hurricane Iota, requires communities to engage regularly with authorities to secure commitments for their recovery and well-being. While this process is essential, it has complicated project execution, including raising unrealistic expectations about the project’s objective and scope, as well as a risk of bypassing established project governance structures that may conflict with the positions of local authorities. Leadership Gaps at CORALINA: CORALINA, a key project partner, has yet to appoint a new director (originally planned for 2023). This leadership vacuum has delayed decision-making and hindered progress on the subgrant with Conservation International (CI). CORALINA’s limited engagement due to these internal challenges has significantly impacted project momentum. Fragmentation of Raizal Leadership and Political Tensions: Internal divisions within the Raizal Council, spiritual leadership and political institutions hindered consensus and reduced participation. Political uncertainty – due to dual membership rulings and transitions in leadership - led to delays in consultations and weakened trust in the participatory process. Institutional Coordination and Visibility Gaps: Engagement of strategic partners, including government departments and private sector actors, has faced challenges due to competing priorities and limited alignment with broader national initiatives. These dynamics have occasionally constrained coordination and reduced the project’s visibility within wider development agendas. To address this, the project is working to strengthen institutional positioning, reinforce linkages with national frameworks, and enhance collaboration with both public and private stakeholders to ensure greater integration and long-term sustainability. Operational and Logistical Constraints: Geographic isolation, limited infrastructure, tight scheduled and weather disruptions impacted continuity, especially in Providence and Santa Catalina. Some consultancies lacked logistical resources to ensure inclusive participation, due to weather hindrances. Incomplete participation records (e.g., missing gender or ethnicity data) also hindered the accuracy of monitoring and evaluation efforts. Misalignment Between Technical Outputs and Community Needs (Post-Iota Context): Some deliverables did not reflect the urgency or evolving priorities of communities recovering from Hurricane Iota. Gaps between technical planning and local realities required extra effort to manage expectations and adapt outputs. This highlights the need for greater adaptability and coherence between technical planning and the lived experiences of affected communities. ### Strengths Despite these obstacles, the GEF Seaflower project continues to benefit from several key strengths Local Government Collaboration: The governments of San Andrés and Providence and Santa Catalina have played a vital role in aligning the project with local priorities. Their support has enabled coordinated actions, such as organizing sustainable tourism workshops, and has provided institutional backing that facilitates policy implementation and resource mobilization. Community Engagement by the PMU: The PMU has prioritized inclusive participation, reaching over 900 community members through more than 100 engagement spaces—including workshops, meetings, and consultations. These efforts have empowered stakeholders, increased awareness, and fostered trust and ownership among community members. Strong Community Engagement and Representation: To date, the project has ensured widespread participation, engaging 2,831 individuals in 255 meetings. Women represented 55.1% of participants, and nearly 48% self-identified as members of the Raizal community. This inclusive approach, exemplified by the participatory design of the Raizal representation scheme (which considered gender, age, and community roles), significantly enhanced legitimacy and supported informed, community-driven decision-making. Gender and Safeguards Integration: The integration of gender equality and social-environmental safeguards was a critical enabler of project outcomes. Women made up 55.1% of the safeguards stakeholder database, and culturally sensitive engagement strategies—such as localized meetings at convenient times—strengthened participation. Women’s leadership became more visible within community associations and local councils, fostering broader gender mainstreaming across components. Effective Stakeholder Mapping and Adaptive Communication: The continuous update of the stakeholder map—expanding from 178 to 417 strategic actors—enabled more effective outreach across community, private, and institutional sectors. Adaptive communication methods such as WhatsApp messages, direct calls, and personalized outreach were instrumental in building trust, particularly in fragmented or historically underserved groups. Institutional Coordination for co-execution of the project: Technical collaboration between CI, CORALINA, and local secretariats enabled feedback workshops for technical products (e.g., Sustainable Tourism Plan, environmental education program, and communication strategy). This progress reflects strengthened linkages between local governance and project implementation. Impact of These Strengths: The project’s emphasis on local partnerships and inclusive governance has been crucial for building community pride and long-term sustainability. Collaboration with CORALINA, local governments, and community members has strengthened social cohesion and aligned conservation and development goals. By combining technical expertise with local knowledge and support, the project has laid a strong foundation for effective and lasting impact. ### Safeguards The reporting period included updates to screening processes, identification of risks, and efforts to operationalize grievance mechanisms. ### Updated Risk Classification: The project has been reclassified from Risk Type C to Type B due to potential social risks linked to the engagement of the Raizal Indigenous community. New Risk Assessments and Findings: Recent screenings conducted for community engagement activities, especially those involving sensitive topics like land tenure and Raizal representation—focused on biodiversity conservation, sustainable tourism, and community involvement within the Seaflower Biosphere Reserve—have revealed several new risks: - Possible adverse effects on the Raizal community’s rights, land, and livelihoods. - Risk of worsening existing social and gender inequalities within the community. - Potential harm to areas of cultural, historical, or spiritual significance for the Raizal people. - Social cohesion risk due to fragmentation in Raizal leadership and political uncertainty. - Participation fatigue from repeated consultations with overlapping objectives, particularly in Providence and Santa Catalina. - Cultural sensitivity risk related to marginalization of traditional leaders due to shifting community dynamics. ### Mitigation and Safeguard Measures: To address these risks, the gender and safeguards officer developed a community participation protocol, with special emphasis on engaging Raizal members and women to ensure inclusive and meaningful involvement. The full plan is available here . Mitigation measures include: - Tailored consultations for different Raizal subgroups (faith-based, gender-based, generational). - Streamlined session planning to reduce overlap and fatigue. - Flexible scheduling and use of informal, trusted venues for sensitive discussions. Progress Updated Safeguards Monitoring Tools - Stakeholder database grew to 417 entries, categorized by gender, ethnicity, sector, role, and leadership capacity. - Improved ability to monitor representation and potential risks. - Supported decentralized and inclusive consultancy meetings. Capacity Building - Internal training sessions conducted for consultants and staff. - Focused on WWF-GEF safeguards standards, including: - Gender equality - Free, Prior and Informed Consent (FPIC) - Cultural sensitivity Integration into Technical Deliverables - Reviewed and adjusted products like: - Raizal representation model - Communications strategy - Educational program - Ensured compliance with inclusivity standards and avoided reinforcing community power imbalances. Grievance Redress Mechanism (GRM) - Stakeholders informed about the grievance process through meetings, workshops, and project materials - Delivered in Spanish and Creole - GRM made available through: - WhatsApp and phone lines - Verbal reports during field sessions and visual materials - Community focal points trained during workshops - Community leaders, especially women and faith-based actors, trained to disseminate GRM details. - No formal written grievances recorded. - Informal concerns raised about: - Leadership structures conflicts - Role misunderstandings between consultants and community reps - Requests for more inclusion of spiritual and youth voices - Resolution Measures - Concerns documented by the Safeguards Officer. - Addressed through: - Adjusted stakeholder engagement strategies (i.e., adjusting session compositions) - Clarified roles in meetings - Planned targeted sessions for underrepresented groups Consultation requirements and the Debate on Prior Consultation (Consulta Previa) - During this reporting period, a debate has emerged over whether the project should undergo a formal Free, Prior and Informed Consultation (Consulta Previa) under Colombian law, due to its potential long-term impacts on Raizal collective rights. - Although the project does not involve resource extraction or territorial changes, its influence on governance, tourism planning, and conservation policy has raised concerns. As such, there is a growing call for clarification on whether a formal consulta previa process should be triggered. - Stakeholder Perspectives - Community leaders, institutions, and consultants hold diverse views. - Some argue that the project’s scope warrants formal consultation to protect Raizal rights and autonomy. - Consultancies Addressing the Issue - Interinstitutional Coordination Group: - Analysing legal/political implications. - Facilitating dialogue among CORALINA, government entities, and communities to determine the most appropriate route forward. - Gender and Safeguards Team: - Documenting community concerns. - Identifying risks to legitimacy and consent. - Ensuring culturally appropriate engagement. - Implications - If formal consultation is required: - Potential delays in implementation, particularly for activities requiring community validation or linked to institutional decision-making. - If addressed proactively: - Strengthens legitimacy, trust, and long-term engagement and reduce the risk of future contestation or disengagement. - Failure to respond adequately: - Risks safeguard non-compliance and loss of credibility. - Mitigation Measures - Continued transparent dialogue. - Documentation of participatory processes. - Adaptive engagement strategies to ensure inclusivity and rights-respect while legal clarity is pursued.

### Progress, Challenges, and Outcomes of Stakeholder Engagement

### (Based on Stakeholder Engagement Plan (SEP) or equivalent included in the ProDoc)

Summarize progress, challenges, and/or outcomes of stakeholder engagement, including strategies taken to ensure gender and social inclusion. Please report for each group of stakeholders (e.g. Ips, LCs, local government, etc). identified in the SEP or equivalent plus any other group identified during implementation. To implement inclusive and culturally relevant stakeholder engagement in line with the Stakeholder Engagement Plan (SEP) from the ProDoc, the project ensured participation from: - Indigenous Peoples and Local Communities (IPLCs) - Local authorities - Civil society - Private sector - Prioritized gender equity, cultural relevance, and accessibility. - Enabled meaningful involvement of women, youth, and the Raizal community. Focus Areas - Tailored engagement strategies for each stakeholder group. - Promoted social and gender inclusion in project design and implementation. Community Involvement (Raizal Community) Progress: - Reached 2,831 participants in 255 meetings; 48% Raizal, 55.1% women. - Developed a participatory representation scheme integrating gender, age, and sectoral roles. - In Providence & Santa Catalina, 91.2% of mapped actors were Raizal. Challenges: - Leadership fragmentation and political uncertainty weakened cohesion and delayed consultations. Inclusion Strategies: - Culturally appropriate outreach, gender-balanced facilitation, and targeted engagement of Raizal women, youth, and traditional sectors (artisanal fishers, cultural associations). Local Government Authorities Progress: - Active collaboration with local secretariats (Tourism, Environment, Planning, Social Development) and participation in the Technical Advisory Group (GAT). Challenges: - Inconsistent engagement leading to missed coordination opportunities and lower institutional visibility of the project and schedule conflicts reduced attendance of key officials at some community sessions Inclusion Strategies: - Formal invitations, follow-ups, and co-facilitation of field activities. Civil Society Organizations and NGOs Progress: - NGOs like Fundación ATUCA and ECOISLA supported stakeholder mapping and gender mainstreaming. Challenges: - Misalignment with community readiness affected feedback loops. Inclusion Strategies: - Monthly coordination meetings and validation workshops for technical deliverables. Private Sector Progress: - Sector-specific sessions in Providence with 60+ participants from 30 institutions. - Focused on certification, beach sustainability standards, and waste management. Challenges: - Limited continuity due to time and resource constraints, seasonality and skepticism about viability of project ouputs . Inclusion Strategies: - Tailored invitations, flexible venues, targeted engagement of hotel and transport operators, and green business certification incentives. Government Institutions with Jurisdiction Progress: - CORALINA contributed to technical validation of deliverables and inter-institutional coordination spaces. Challenges: - Irregular participation and low trust from communities weakened institutional legitimacy. Inclusion Strategies: - Coordination with WWF GEF and alignment with government planning cycles and institutional agendas. Educational Institutions and Youth Organizations Progress: - Youth engaged through environmental education and collaboration with INFOTEP and schools. Challenges: - Lack of a dedicated youth strategy limited structured involvement. Inclusion Strategies: - Youth-led cultural content into communications materials and potential expansion via ECOISLA’s programs. General Public and Other Identified Groups Progress: - Included religious leaders, disability committees, and women’s organizations. - strengthened social accountability and broadened representation in island-wide discussions. Challenges: - Required significant awareness-building due to limited prior involvement. Inclusion Strategies: - Personalized outreach and accessible facilitation techniques. ### Overall Progress - Broad Community Engagement Between July 2024 and June 2025, the project engaged a total of 926 participants in over 255 meetings, workshops, and community sessions across San Andrés, Providencia, and Santa Catalina. Of these, 446 participants (48.2%) identified as Raizal, ensuring that nearly half of all engagement directly represented the interests of the Raizal people. Intersectional representation across Raizal / non-Raizal and gender for July 2024 – June 2025: - Raizal Women: ~250 participants (27.0%) - Raizal Men: ~196 participants (21.2%) - Non-Raizal Women: ~329 participants (35.5%) - Non-Raizal Men: ~151 participants (16.3%) - Inclusive Participation Gender equity and social inclusion remained central to the project. Across all activities, 579 women (62.5%) and 347 men (37.5%) participated, maintaining female representation well above the 50% target. Representation extended across sectors: community (Raizal and non-Raizal), institutions, and private actors. Notably, the project strengthened collaboration with the Raizal Council and expanded alliances with more than 33 grassroots organizations. Representation across sectors and gender (GESI indicators) for July 2024 – June 2025: - Sector representation: 48.2% Raizal community, 51.8% non-Raizal participants. - Gender representation: 62.5% women, 37.5% men — exceeding the 50% gender parity goal. - Capacity Strengthening The reporting period saw the implementation of extensive training on gender, social, and environmental safeguards, with tailored sessions provided to all subgrantee teams and consultants. More than 417 stakeholders were identified and incorporated into the project’s database of key actors, enabling more precise targeting of training and inclusion strategies. Activities such as the environmental education pilot with Coonative Brother also reinforced youth engagement and long-term community empowerment. - Flexible Communication Approaches To address challenges of geographic dispersion and institutional fragmentation, the project adopted flexible and decentralized communication strategies. Meetings were scheduled at times and in community spaces more accessible to participants (e.g., El Centro, La Loma, San Luis in San Andrés; Santa Isabel, Bottom House, and Rocky Point in Providencia). Additionally, the use of practical tools such as WhatsApp groups facilitated continuous outreach, feedback, and trust-building with diverse stakeholders. ### Challenges - Representation Difficulties - The Raizal community faces challenges in unified representation, especially within the Raizal Council. To address this, the project holds multiple meetings with relevant Raizal stakeholders to involve as many representatives as possible. - Scheduling meetings with key leaders is hindered by logistical and institutional constraints. - Managing Expectations - Some community members lack clarity about the project’s goals or feel excluded, partly due to misinformation. - Gender Visibility Gaps - Despite women’s active roles in decision-making, their presence is limited in sectors like fishing and nautical guiding, requiring ongoing efforts to promote gender equity. ### Gender and Social Inclusion Strategies - Gender-Focused Training - Training sessions emphasized gender equity, especially in male-dominated fields, using practical exercises and case studies. - Monitoring Participation - Gender-disaggregated data is collected to ensure balanced involvement, with targeted outreach to underrepresented groups. - Culturally Respectful Communication - Inclusive and culturally sensitive language was used to foster respect and avoid alienation. - Emerging Leadership and Representation - During this reporting period, the project has increasingly identified and supported emerging leaders within the Raizal community, with special emphasis on women actively engaged in tourism, cultural preservation, and environmental stewardship. Several Raizal women’s groups have taken on leadership roles in guiding community consultations, coordinating local tourism initiatives, and representing community interests in project decision-making spaces. Their contributions extend beyond direct economic activities, as they also play a central role in maintaining local infrastructure, transmitting traditional knowledge, and safeguarding cultural identity, ensuring that development processes remain rooted in community values. - In parallel, younger Raizal leaders—both women and men—have been engaged through training activities on gender, social, and environmental safeguards, as well as through youth-oriented initiatives such as the environmental education program. These efforts are fostering a new generation of leaders capable of bridging community priorities with broader policy frameworks, thereby strengthening the legitimacy and sustainability of the project’s outcomes. Collectively, this focus on Raizal leadership ensures not only greater representation but also the empowerment of actors who are pivotal in linking biodiversity conservation with local development and cultural preservation. ### Key Outcomes - Empowered Communities: Stakeholders are now more capable of contributing to project planning and implementation, enhancing sustainability. - Greater Awareness: Participants have deepened their understanding of gender equity and biodiversity conservation. - Improved Representation: Inclusive spaces have elevated the voices of women and marginalized groups in decision-making processes at both community and institutional levels. For example, Raizal women engaged in tourism and cultural heritage initiatives have actively participated in consultations and planning workshops, ensuring that project outputs reflect local knowledge and community priorities. Their leadership has influenced discussions on sustainable tourism practices, the preservation of cultural traditions, and the equitable distribution of project benefits. In addition, women leaders from grassroots organizations have contributed to shaping environmental safeguard strategies by providing perspectives on how project activities intersect with social equity and cultural continuity. Their involvement has helped strengthen guidelines for community engagement, land-use planning, and the integration of gender-sensitive approaches in subgrantee activities. Youth-oriented initiatives, such as the environmental education pilot with Coonative Brother, have further highlighted the role of young Raizal women as emerging leaders, linking biodiversity conservation with cultural preservation. Collectively, these examples demonstrate that women are not only participating but are increasingly influencing decision-making spaces, thereby enhancing both the inclusiveness and sustainability of project outcomes.

### Information on Progress on Gender-Responsive Measures

### (As documented in the ProDoc, Results Framework, the Gender Action Plan or Equivalent)

Please provide the completion dates for: the gender assessment or analysis and gender mainstreaming strategy/action plan (GEF-7). 10 /16 /2024. Summarize progress, challenges, and/or outcomes of gender-responsive measures, gender-sensitive indicators and any intermediate gender results in Results Framework, Gender Action Plan or equivalent. The GEF Seaflower project has made notable strides in integrating gender responsiveness throughout its implementation, keeping gender equity at the heart of its approach while navigating key challenges, as well as recognizing the role that raizal women plays in the project development. Progress Achieved - Gender Action Plan in Practice Gender considerations have been embedded throughout the design and execution of the project, supported by a dedicated officer ensuring compliance with social and gender safeguards. Institutionalization of gender criteria has advanced through the integration of gender indicators, quotas, and sex-disaggregated data into the project’s mapping and tracking tools. To date, more than 125 relevant stakeholders—including institutional representatives, Raizal leaders, and grassroots organizations—have been identified for targeted gender-related engagement. It is important to note that specific gender-focused workshops or trainings have not yet been implemented during this reporting period. Nevertheless, gender-related engagement has been consistently mainstreamed into all project activities to guarantee the active participation of women and marginalized groups in decision-making spaces, consultations, and technical processes. For instance, women from Raizal grassroots organizations active in tourism, artisanal production, and cultural preservation have contributed meaningfully to consultations and planning exercises, helping to shape outputs in ways that are both gender-responsive and culturally grounded. Looking ahead, the project has planned dedicated gender-related training activities for leaders during the second semester of 2025 and into Year 4. These sessions will focus on strengthening the leadership and representation of women—particularly Raizal women—as well as youth and other underrepresented groups. They are also intended to coincide with the handover and dissemination of key project outputs, ensuring that women and local leaders are empowered to use and apply project results in advancing their own initiatives. This will include structured collaboration with local organizations already engaged in the project, such as Raizal women’s associations in tourism and artisanal sectors, community-based environmental groups, and grassroots councils, to ensure ownership, sustainability, and enhanced community leadership. - Promoting inclusive and female representation - A target of at least 50% female participation was set and consistently tracked across workshops and consultations (current achievement against this target stands at 55.1% of 2,831 stakeholders engaged are women; 55.8% of actors in the safeguards database were women - Culturally appropriate engagement: Meetings scheduled to accommodate caregivers; informal spaces and trusted leaders used to mobilize women’s groups. - Activities such as stakeholder mapping and participatory meetings prioritized the inclusion of Raizal women leaders. - Inclusive representation: Raizal community representation scheme integrated gender, age, and sectoral diversity, which increased the visibility of women leaders in community councils and associations. - Training on Gender and Safeguards - Tailored workshops and consultations equipped partners and sub-grantees with knowledge on gender equity and environmental/social safeguards. - These sessions emphasized applying gender-sensitive approaches in areas like sustainable tourism and policy development. - Tracking Gender Inclusion - Specific indicators were created to monitor gender inclusivity, including: - Female participation in decision-making roles and consultations. - Integration of gender perspectives into protected area management and tourism strategies. - Integration of Traditional Knowledge The project has explicitly incorporated Raizal women’s traditional knowledge into strategies for biodiversity conservation and tourism management. For example, women artisans and cultural leaders have contributed knowledge on traditional gastronomy, craft-making, and oral history, which informs both sustainable tourism practices and the preservation of intangible heritage within the project’s outputs. This ensures that conservation strategies are not only technically sound but also culturally rooted. - Women Across Generations To strengthen the continuity of women’s leadership, the project has engaged Raizal women from different age groups, ranging from young leaders participating in the Coonative Brother environmental education pilot to elder women who act as custodians of cultural practices and community organization. This intergenerational approach enhances resilience and ensures that leadership is passed on while respecting community traditions. For both, the integration of traditional knowledge and women across generations, female Raizal leaders like the members of ASOPOSADAS, have been key for this achievement, as well as Sound Bay Woman Association, among others. - Baseline and Progress on Indicators Baseline data established in Year 2 indicated that women represented approximately 57% of participants in decision-making spaces. By the end of the July 2024 – June 2025 reporting period, women’s representation had risen to 62.5% across project activities (579 women out of 926 total participants), exceeding the 50% target. Within this, Raizal women accounted for nearly 27% of all participants, demonstrating both cultural and gender inclusivity. These figures provide a strong baseline for monitoring continued progress in leadership roles, consultations, and gender mainstreaming across protected area and tourism strategies. Challenges Faced - Limited Visibility in Certain Sectors - Women remain underrepresented in fields like fishing and nautical tourism, despite ongoing inclusion efforts. Women remain underrepresented in sectors such as fishing and nautical tourism, but this is not primarily due to a lack of interest in participating in project activities. Rather, it reflects structural and cultural barriers that limit their engagement in these traditionally male-dominated fields. As noted in the PPR and progress reports, barriers include limited access to formal training and certifications in nautical operations, restricted decision-making power within household or community fishing associations, and competing responsibilities related to household and care work that reduce availability for sector-specific meetings or workshops. Despite these challenges, the project has observed that when opportunities are adapted to women’s realities—such as scheduling activities in accessible community spaces or linking training with broader cultural and tourism initiatives—Raizal women demonstrate a strong interest in contributing. For instance, their leadership is more visible in land-based tourism, gastronomy, and artisanal production, where participation is both culturally recognized and logistically feasible. The project is therefore working to gradually bridge these gaps by integrating women’s knowledge and perspectives into fisheries and nautical tourism discussions, while also planning targeted capacity-building in future phases to reduce entry barriers and expand women’s representation in these sectors. - Building Community Trust - Historical scepticism toward institutions made it harder to engage some groups, especially women. Trust-building required frequent, culturally respectful interactions. - Logistical Constraints - Scheduling meetings for women, particularly those with household responsibilities, required flexible solutions—such as evening sessions on weekends for women-led groups. - Incomplete Data Capture - In some community sessions, gender information was not fully recorded on attendance forms, reducing the accuracy of disaggregated data and limiting the tracking of gender-based indicators in certain zones. - Uneven Gender Integration Across Components - While gender was well integrated in stakeholder engagement and safeguards, some technical consultancies lacked a strong gender lens in their deliverables, requiring retroactive adjustments and closer support from the Gender Officer. ### Intermediate Outcomes - Empowered Female Leadership - Women leaders, especially in Providence and Santa Catalina, including members of the Sound Bay Women Association in San Andres, have taken on more prominent roles in project activities, contributing to more inclusive project governance, decision-making, fostering peer to peer mobilization and community engagement. Women leaders, especially in Providence and Santa Catalina, along with members of the Sound Bay Women Association in San Andrés, have assumed increasingly prominent roles in project activities. Their contributions have enhanced inclusive governance, decision-making, and peer-to-peer mobilization across the Archipelago. During the July 2024 – June 2025 reporting period, women represented 62.5% of all participants in project activities (579 out of 926 participants), consistently surpassing the 50% inclusion target. Within this, Raizal women accounted for approximately 27% of all participants, ensuring that their voices were strongly represented in decision-making processes. Notably, in community consultations and governance workshops held in Providence and Santa Catalina, women made up nearly two-thirds of attendees, demonstrating growing engagement in strategic discussions. The Sound Bay Women Association, in particular, played a key role in mobilizing grassroots participation and channeling community perspectives into project outputs. This progress illustrates a clear shift: women are not only participating but also leading dialogues, shaping strategies in tourism and cultural preservation, and fostering broader community engagement. Their presence is now firmly embedded in governance spaces, laying the foundation for sustained female and Raizal leadership in biodiversity and sustainable development initiatives. - Greater Gender Awareness - Stakeholders have shown increased understanding and positive attitudes toward gender equity, especially in conservation and tourism contexts. - Strengthened gender mainstreaming across tourism, communications, and education activities, ensuring that women's roles and knowledge systems were reflected in planning and communications products. Examples of this shift include: - Tourism Sector: During community consultations in Providencia, women leaders influenced the design of sustainable tourism strategies by emphasizing the inclusion of traditional Raizal gastronomy, artisanal crafts, and cultural storytelling as central elements of the visitor experience. Male tourism operators acknowledged the value of these contributions and expressed support for greater inclusion of women’s perspectives in the sector. - Conservation and Education: In the environmental education pilot with Coonative Brother, both male and female participants recognized the importance of integrating women’s roles and indigenous knowledge into biodiversity education. This has strengthened acceptance of women as environmental stewards and educators, particularly among younger participants. - Community Engagement: Members of the Sound Bay Women Association in San Andrés reported stronger collaboration with male community leaders, who increasingly recognized women’s organizational capacity and leadership in mobilizing community participation. This reflects a cultural shift toward greater respect for women’s leadership in governance spaces. These examples highlight how project actions are not only increasing participation but also transforming attitudes toward women’s roles, laying the groundwork for long-term gender equity in decision-making, conservation, and community development. - Inclusive Participation - Efforts were made to include women with an intergenerational approach, balancing the experience of older leaders with the fresh perspectives of younger participants allowing to break barriers that limits women participation. Highlighting the importance of traditional knowledge, aligned with the preservation of nature and culture in a biosphere reserve. - Institutional learning - Recommendations include better coordination between consultants and the Gender Officer and mobile tools for improved data capture. ### Training for Partners and Sub-Grantees - Key Topics - Training covered: - Integrating gender into tourism and biodiversity policies. - Developing gender-responsive indicators. - Addressing gender-specific impacts of project activities. - Training Methods - Participatory workshops. - Case studies highlighting gender disparities in environmental management. - Ongoing follow-ups to assess impact and reinforce learning. - Results - Partners and sub-grantees are now better equipped to apply gender-sensitive approaches, leading to more inclusive and equitable project outcomes, bringing an equity legacy for the islands across the project development, that highlights the richness and diversity from the archipelago. - The project made meaningful progress in promoting women’s participation, leadership visibility, and gender-sensitive monitoring. Continued efforts are needed to standardize gender integration and improve data collection for adaptive management. ### Gender Results: Baseline vs. Current vs. Target Indicator; Baseline (Year 2); Current (July 2024 – June 2025); Target (End of Project). Overall female participation in project activities; 57% (approx. 300 of 525 participants); 62.5% (579 of 926 participants); ≥ 50%. Raizal women participation (cultural + tourism sectors); 22% of total participants; 27% of total participants; ≥ 25%. Female participation in decision-making spaces; 57% of participants in decision-making spaces; 62.5% of participants in decision-making spaces; ≥ 50%. Workshops/meetings with >50% women representation; 45% of events; Over 65% of events; ≥ 50% of events. Grassroots/local organizations with active women leaders; 25 organizations; 33 organizations; ≥ 30 organizations. The data demonstrate clear progress in advancing gender inclusion within the project. Women’s overall participation rose from 57% in Year 2 to 62.5% in 2024–2025, surpassing the 50% target. Representation of Raizal women increased from 22% to 27%, and women now account for 62.5% of decision-making spaces, up from 57%. Additionally, over 65% of workshops and meetings achieved majority female participation, compared to 45% in the baseline. Engagement of 33 grassroots organizations with active women leaders also exceeds the original target of 30. While these results highlight strong progress—particularly in participation and organizational leadership—continued efforts are required to consolidate women’s influence in governance roles and ensure consistent integration of gender-sensitive approaches across all components.

### Knowledge Activities / Products

### (When Applicable, as Outlined in Knowledge Management Approach in the ProDoc)

Please summarize progress on the implementation of the project’s KM approach approved at CEO endorsement/ Approval. List knowledge activities/products (including links) developed during this project year. ### Mangrove Conservation Day Activities – July 26, 2024 To mark the International Day of Mangrove Conservation, the PMU organized a series of impactful events in partnership with public and private sector entities. These initiatives led to meaningful outcomes: - Mangrove Cleanup Drive - A cleanup operation was conducted within the mangrove ecosystem, resulting in the collection of substantial waste: - Glass: 1,129.8 kg - Mixed Plastics: 170.37 kg - Cans: 114.4 kg - Educational Outreach for Teens - Students from 10 schools participated in an awareness session highlighting the ecological value of mangroves. - The program included a guided tour through the mangrove forest, leaving many students—most of whom had never visited mangroves before—with a deeper understanding and appreciation of their importance. - Art & Nature Workshop for Young Children - Children aged 4 to 6 engaged in a creative workshop that combined art and environmental education. - Through playful and interactive activities, they learned about the significance of mangrove conservation in an enjoyable and accessible way. These events successfully raised awareness about the vital role mangroves play in biodiversity preservation and environmental resilience. Related content and documentation from these activities are available here. ### Celebrating International Ocean’s Day through Culture, Knowledge, and Conservation – June 8, 2025 - Involving primary school students from Providencia and Santa Catalina. - Focused on reviving the traditional Hucks Boat-building practice—an endangered artisanal skill vital to island heritage Cultural and Educational Impact - Sabedores (knowledge keepers) guided students through hands-on boat-building while sharing stories and values tied to ocean stewardship. - Emphasized sustainable fishing, marine habitat protection, and community cooperation. - Strengthened intergenerational knowledge transfer and cultural pride. Media and Documentation - Conservation International is producing a short documentary to preserve and promote the tradition and its conservation message. - A two-minute video is also in production to highlight the importance of conserving the Seaflower Biosphere Reserve, featuring community voices and biodiversity visuals. Broader Communication Strategy - Collaboration with Native Films ensures documentation of workshops and activities. - Audiovisual records integrate local knowledge, scientific approaches, and community participation in conservation efforts. Seaflower Biosphere Reserve Conservation video - brings together footage from diverse workshops, testimonies from community members, and compelling visuals of the islands’ unique biodiversity - aims to inspire pride, awareness, and action among residents and decision-makers, reinforcing the shared responsibility to protect both the ocean and the cultural heritage of the Seaflower Archipelago.

### Reflows (for NGIs only)

Note: This field is not publicly disclosed.

Please attach the actual reflow (both cumulative, and reflow in the current year), the potential reflows, and other relevant information, including the quarterly investor reports and/or presentations materials the Executing Agencies provide to GEF Agencies. Select the disclosure level based on each document’s confidentiality. Please provide an explanation for any deviations between projected and actual reflows, along with any updates to reflow projections. Include any relevant changes to the project, events, or notifications received from Executing Agencies that may adversely affect future reflows

### Adaptive Management

Please check all applicable modifications made to the project during this reporting period noting a description of the change, justification for the change and the date of No-Objection given by the WWF GEF Agency. If not applicable, please leave blank. Please see guidance on definitions and procedures for Major and Minor Amendments. Note: it is recommended that all changes be discussed in advance with the GEF Program Manager. Category of change; Description of the change; Justification; Date of No-Objection by WWF GEF. Major Amendments. ☐Project Scope. ☐ Project Objective. ☐>5% Increase in financing. Minor Amendments. ☐ Results framework. ☐ Components and cost. ☐Institutional and implementation arrangements. ☐Financial management. ☐Implementation schedule. ☐ Executing Entity. ☐Executing Entity Category. ☐Minor project objective change. ☒ Safeguards; Recategorization of Safeguards risk from C (Low) to B (Modest); In discussions with the PMU, and after hearing feedback from stakeholders, the project is reclassified due to potential social risks associated with the engagement of the Raizal Indigenous community.; April 1, 2025. ☐ Risk analysis. ☐ Increase of GEF project financing up to 5%. ☐ Co-financing. ☐ Location of project activity. ☐ Other:. For any proposed or anticipated changes to the project this coming year, please describe below what those changes would be (e.g., in the workplan or results framework) and provide justification. Note: It may be helpful to reference project lessons, challenges, strengths and/or the project theory of change.

### Geolocation Information

Please provide a location name, latitude and longitude for key locations of GEF-financed activities. Depending on the scope of the project, it may only be necessary to provide geolocation of the capital city. The format should be in Decimal Degrees WGS84 format only – e.g. not degrees, minutes or seconds. Please use ‘-‘ instead of ‘S’ and avoid inserting ‘°’). As an alternative, you may enter a GEOname ID for locations of GEF-financed activities under this project. Location and activity description is optional. Maps or shapefiles are recommended, but optional. Please use this Guide for additional details. Location Name; Latitude; Longitude; Geo Name ID; Location & Activity Description (Optional). Parque Nacional Manglares de Old Point - Isla San Andrés; 12.56597647; -81.70482938. Southwest Bay - Isla Providencia; 13.33446492; -81.39187721. Centroide de Isla San Andrés; 12.543062; -81.71767. Centroide de Isla Providencia; 13.35319; -81.373898. Centroide de Santa Catalina; 13.387817; - 81.374836.

Annex I: Rating Scales and Guidance

### Development Objective Rating

The project Development Objective (DO) rating is quantified by analyzing progress against the Results Framework according to the rating scale below. Note that the average is not taken across component averages, but rather across all indicators in the Results Framework. No percent achieved should surpass 100% even if the target is exceeded.

DO Rating scale

| Rating | % Achievement of Results Framework targets (average) |
| --- | --- |
| Highly Satisfactory (HS) | 100% |
| Satisfactory (S) | 80 – 99 |
| Moderately Satisfactory (MS) | 60 – 79 |
| Moderately Unsatisfactory (MU) | 40 – 59 |
| Unsatisfactory (U) | 20 – 39 |
| Highly Unsatisfactory (HU) | Below 20% |

Guiding Example: How to calculate DO Rating from Results Framework

| Objective/Component/ Outcome | Indicator | Unit | Target Y1 | Achieved Y1 | Percent achieved Y1 |
| --- | --- | --- | --- | --- | --- |
| Project Objective | Indicator 1 | # policies | 5 | 4 | 80 |
|  | Indicator 2 | # ha | 1,000,000 | 900,354 | 90 |
| Component 1 |  |  |  |  |  |
| Outcome 1.1 | Indicator 3 | # beneficiaries | 500 | 410 | 82 |
| Outcome 1.2 | Indicator 4 | # sites | 10 | 12 | 100 |
| Component 2 |  |  |  |  |  |
| Outcome 2.1 | Indicator 5 | % score | 80% | 75% | 93.75 |
| Average of total |  |  |  |  | 89.15 |

### Implementation Progress Rating

The project Implementation Progress (IP) rating is based on progress against the annual workplan, based on the rating scale provided below.  Note that the average is not taken of the component averages, but rather across all indicators in the workplan. No percent achieved should surpass 100% even if the target is exceeded.

IP Rating scale

| Rating | % Achievement of annual workplan targets (average) |
| --- | --- |
| Highly Satisfactory (HS) | 100 |
| Satisfactory (S) | 80 – 99 |
| Moderately Satisfactory (MS) | 60 – 79 |
| Moderately Unsatisfactory (MU) | 40 – 59 |
| Unsatisfactory (U) | 20 – 39 |
| Highly Unsatisfactory (HU) | Below 20% |

Guiding Example: How to calculate IP Rating from AWP&B

| Project Activities Y1 | Unit | Target | Achieved | Percent Achieved |
| --- | --- | --- | --- | --- |
| Component 1 |  |  |  |  |
| Activity 1.1.1 | Sites | 5 | 4 | 80 |
| Activity 1.1.2 | Households | 120 | 122 | 100 |
| Average Component 1 |  |  |  | 90 |
| Component 2 |  |  |  |  |
| Activity 2.1.1 | Plans | 6 | 5 | 83 |
| Activity 2.1.2 | Reports | 2 | 2 | 100 |
| Activity 2.1.3 | Proposals | 10 | 7 | 70 |
| Average Component 2 |  |  |  | 84.3 |
| Component 3 |  |  |  |  |
| Activity 3.1.1 | Trips | 2 | 0 | 0 |
| Activity 3.1.2 | Trainings | 4 | 3 | 75 |
| Average Component 3 |  |  |  | 37.5 |
| Average achievement of all activities in workplan |  |  |  | 72.57 |

### Risks

Examine whether the project faces substantial risks in terms of the achievement and sustainability of project results. First identify the individual risks (internal and external) that the project is facing and rate those according to the rating scale (you may take both probability and impact into consideration). These are the inherent risks (or baseline risks). All of the risks will have mitigation actions to either manage or reduce the risk. After reviewing the mitigation plan for the individual risk, please project what the resulting risk would be, the residual risk – and rate according to the same scale. After assessing all individual residual risks, please determine the overall risk by averaging the individual risk ratings. In this example, the overall rating is identified as Modest given that one risk is substantial, one is modest and one is low. This rating is subjective and considered the best estimate for the average risk the project is facing in terms of achievement of outcomes. The risk rating should take into account the country setting and ambition of the project. See additional details here.

Risk Rating Scale

| Rating |  |
| --- | --- |
| High Risk (H) | There is a probability of greater than 75% that assumptions may fail to hold or materialize, and/or the project may face high risks. |
| Substantial Risk (S) | There is a probability of between 51% and 75% that assumptions may fail to hold, and/or the project may face substantial risks. |
| Modest Risk (M) | There is a probability of between 26% and 50% that assumptions may fail to hold or materialize, and/ or the project may face only modest risks. |
| Low Risk (L) | There is a probability of up to 25% that assumptions may fail to hold or materialize, and/ or the project may face only modest risks. |

Guiding example: How to determine Risk Rating from Risk Analysis in PPR

| Risk Description | Inherent Risk | Mitigation | Residual Risk Rating |
| --- | --- | --- | --- |
| Elections – change of leadership lead to not holding up to commitments | High | Engage and establish rapport with opposition parties, explain MOUs and consequences of non-commitment. | Substantial |
| The newly established coordination mechanism does not meet regularly, and coordination fails | Modest | Ensure only most interested participants become members, engage regularly with members and monitor progress. | Modest |
| The new equipment given to rangers will fail at some point and there will be no expert or replacement parts available to fix. | Modest | The project is developing extension services that will be resourced with government contracts to provide the rangers the support needed. | Low |
| Average risk rating |  |  | Modest |

Start date is grant agreement signature or soft start.

As specified in the CEO Approval/ Endorsement or subsequent revision.

Should be no more than 12 Months after the expected closing date. Please keep current.

Date of Submission of Final PIR (when operations are complete).

Total GEF disbursement defined as amount of project budget spent by the Executing Agency, as a total from project start until June 30 of reporting FY.