United Nations Development Programme

Country: Indonesia

PROJECT DOCUMENT

| Project Title: Advancing Indonesia’s Lighting Market to High Efficient Technologies (ADLIGHT) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Country: Indonesia | Implementing Partner: Ministry of Energy and Mineral Resources (MEMR) |  |  |  | Management Arrangements: National Implementation Modality (NIM) |
| UNPDF/Country Programme Outcome: UNPDF/CPD Outcome 3 -- By 2020, Indonesia is sustainably managing its natural resources, on land and at sea, with an increased resilience to the effects of climate change, disaster and other shocks. |  |  |  |  |  |
| UNDP Strategic Plan Output: CPD Indicative Outputs -- 2.2.1. National energy policies and guideline developed and integrated into sub-national development plan. 2.2.2. Sub-national authorities and key partners are able to implement programmes, mobilize resources and develop public-private partnership for RE/EE, which will contribute to the reduction of national greenhouse gases emission. |  |  |  |  |  |
| UNDP Social and Environmental Screening Category: Moderate |  |  | UNDP Gender Marker: 2 |  |  |
| Atlas Project ID/Award ID number: 00098585 |  |  | Atlas Output ID/Project ID number: 00101814 |  |  |
| UNDP-GEF PIMS ID number: 5721 |  |  | GEF ID number: 9493 |  |  |
| Planned start date: June 2019 |  |  | Planned end date: July 2022 |  |  |
| LPAC date: 26 March 2019 (proposed) |  |  |  |  |  |
| Brief project description: ADLIGHT aims to promote the increased deployment of high efficiency lighting technologies in Indonesia through the transformation of the national market, thereby reducing electricity demand and the related greenhouse gas (GHG) emissions. The project is expected to lead to increased market penetration of high efficiency lighting through capacity building for the country’s lighting industry, thereby enhancing the local manufacturing capability to locally-produce highly quality lighting systems in line with MEPS, through introducing quality and minimum energy performance regulation, procurement policies and improved customs procedures and through introduction of new business models and awareness raising. This will bring about cumulative electricity savings of 310 GWh and cumulative GHG emissions reduction of 250 kt CO2 by year 3 of the project and increase the impact as the selected demonstrations to enhance market penetration will catalyze more replication of these EE lighting technologies for the coming years and beyond to have a total potential of 1,646 kt CO2 emission reduction. This will be achieved through implementation of three Components, namely, (1) Support to local lighting industry to transform the market for high quality, high efficient lighting systems, (2) Regulatory mechanisms and market monitoring, verification, and enforcement, and (3) New business models and awareness raising for high efficiency lighting technology penetration. During the implementation, in addition to the GEF fund of USD 3,895,872, UN Environment contributes in-kind funds of USD 60,000 and UNDP in-kind funds of USD 80,000; the project will be supported by in-kind and cash contributions to support parallel activities from the government (MEMR, BSN and City Government of Solo) to an amount of USD 27,889,337 and from private lighting manufacturers and other partners to an amount of USD 9,065,000. Thus, total resources for project implementation are USD 37,094,337. |  |  |  |  |  |
| Financing Plan |  |  |  |  |  |
| Total Budget Administered by UNDP |  |  |  |  |  |
| - GEF Trust Fund |  |  | USD 2,633,372 |  |  |
| UNDP (Component 1 and 3) |  |  | USD 2,633,372 |  |  |
| UNDP TRAC resources |  |  | 0 |  |  |
| Cash co-financing to be administered by UNDP |  |  | 0 |  |  |
| Total Budget administered by UNDP |  |  | USD 2,633,372 |  |  |
| Total Budget Administered by UN Environment |  |  |  |  |  |
| - GEF Trust Fund |  |  | USD 1,262,500 |  |  |
| UN Environment (Component 2) |  |  | USD 1,262,500 |  |  |
| Total Budget administered by UN Environment |  |  | USD 1,262,500 |  |  |
| Parallel co-financing (all other co-financing that is not cash co-financing administered by UNDP) |  |  |  |  |  |
| UNDP |  |  | USD 80,000 |  |  |
| UN Environment |  |  | USD 60,000 |  |  |
| Government of Indonesia |  |  | USD 27,889,337 |  |  |
| Industry |  |  | USD 9,065,000 |  |  |
| - Total co-financing |  |  | USD 37,094,337 |  |  |
| - Grand-Total Project Financing (1)+(2)+(3) |  |  | USD 40,990,209 |  |  |
| Signatures |  |  |  |  |  |
| Signature: print name below |  | Agreed by Government |  | Date/Month/Year: |  |
| Signature: print name below |  | Agreed by Implementing Partner |  | Date/Month/Year: |  |
| Signature: Christophe Bahuet, Country Director, UNDP Indonesia |  | Agreed by UNDP |  | Date/Month/Year: |  |

# Table of Contents

I.	Table of Contents	3

II.	Development Challenge	7

III.	Strategy	22

IV.	Results and Partnerships	52

V.	Project Management	63

VI.	Project Results Framework	65

VII.	Monitoring and Evaluation (M&E) Plan	70

VIII.	Governance and Management Arrangements	77

IX.	Financial Planning and Management	85

X.	Total Budget and Work Plan	88

XI.	Legal Context	93

XII.	Risk Management	94

XIII.	Mandatory Annexes:	97

Annex A: Multi-Year Work plan

Annex B: Monitoring Plan

Annex C: Evaluation Plan

Annex D: GEF-7 Core Indicators (s) at baseline

Annex E: Terms of Reference

Annex F: UNDP Social and Environmental and Social Screening Template (SESP)

Annex G: UNDP Project Quality Assurance Report

Annex H: UNDP Risk Log

Annex I: Results of the capacity assessment of the project implementing partner and HACT micro assessments

Annex J: Additional Agreements

Annex K: Description of Demonstration Projects

Annex L: GHG Emission Reduction Estimates

Annex M: Annual Targets

Annex N: Gender Analysis and Action Plan

Annex O: Knowledge Management Strategy

Annex P: Stakeholder Engagement Plan

Annex Q: Problem Tree

Annex R: Supplemental Provisions to the Project Document: The Legal Context

List of Tables

Table 1: Activities that will deliver the Outputs resulting to Outcome 1

Table 2: Activities that will deliver the Outputs resulting to Outcome 2

Table 3: Activities that will deliver the Outputs resulting to Outcome 3

Table 4: Summary of Expected Results of Baseline and Alternative Scenarios

Table 5: ADLIGHT Partners and Roles in the Project

Table 6:  ADLIGHT Project Risk Log

List of Figures

Fig. 1: Relationship among the SE4ALL Global Project, Global Leapfrogging Program and the ADLIGHT Project of Indonesia

Fig. 2: Share of Electricity for Lighting in Indonesia for each Sector in Year 2016

Fig. 3: Theory of Change: Advancing Indonesia’s Lighting Market to High Efficient Technologies (ADLIGHT)

Fig. 4: Conservative and optimistic penetration rate and increased efficiency Scenarios

Fig. 5: ADLIGHT Project Management Structure

List of Abbreviations & Acronyms

| Abbreviation | Meaning |
| --- | --- |
| ADLIGHT | Advancing Indonesia’s Lighting Market to High Efficient Technologies |
| AILKI | Asosiasi Industri Luminer & Kelistrikan Indonesia (Association of Indonesia Luminaires and Electricity Industry) |
| ALINDO | Asosiasi Luminer Indonesia (Indonesia Luminaires Association) |
| ALINDO | Asosiasi Luminer Indonesia (Indonesian Luminaire Association) |
| APAEC | ASEAN Plan of Action Energy Cooperation (2016-2025) |
| APERLINDO | Asosiasi Industri Perlampuan Listrik Indonesia or Indonesian Electrical Lighting Industry Association |
| ASEAN-SHINE | Association of Southeast Asian Nations - Standards Harmonization Initiative for Energy Efficiency |
| ASKRINDO | PT Asuransi Kredit Indonesia or Credit Insurance Company |
| BAPPENAS | Badan Perencanaan Pembangunan Nasional (National Development Planning Agency) |
| BMP | Bobot Manfaat Perusahaan (Weight-based company benefit) |
| BPD | Bank Pembangunan Daerah or Regional Development Banks |
| BPPT | Badan Pengkajian dan Penerapan Teknologi (Research Agency for Technology Development and Implementation) |
| BRESL | Barrier Removal to the Cost Effective Development and Implementation of Energy Efficiency Standards and Labeling |
| BSN | Badan Standardisasi National (National Standardization Agency) |
| CFL | Compact Florescent Lamp |
| DANIDA | Danish International Development Agency |
| DGEED | Directorate General of Electricity and Energy Development |
| DGNREEC | Directorate General of New-Renewable Energy and Energy Conservation |
| EE | Energy efficiency |
| EECCHI | Energy Efficiency and Conservation Clearing House Indonesia |
| EEL | Energy Efficient Lighting |
| ES&L | Energy standards and labeling |
| ESCO | Energy Service Company |
| FGDs | Focused group discussions |
| FSP | Full Sized Project |
| GAMATRINDO | Gabungan Industri Manufaktur Lampu Terpadu Indonesia (Indonesian Integrated-Lamp Manufacturing Industry Association) |
| GEF | Global Environment Facility |
| GEFSEC | Global Environment Facility Secretariat |
| GHG | Greenhouse gas |
| GIZ | Die Deutsche Gesellschaft für Internationale Zusammenarbeit (German Agency for International Development) |
| GLP | Global Leapfrogging Program |
| HS Code | Harmonized Commodity Description and Coding System |
| IEC | International Electrotechnical Commission |
| IIGF | Indonesia Infrastructure Guarantee Fund |
| JICA | Japan International Cooperation Agency |
| KAN | Komite Akreditasi Nasional (National Accreditation Body of Indonesia) |
| LED | Light-emitting diode |
| LFA | Logical Framework Analysis |
| LKPP | Lembaga Kebijakan Pengadaan Barang/Jasa Pemerintah or the National Public Procurement Agency |
| MASKEEI | Masyarakat Konservasi dan Efisiensi Energi Indonesia or IECES (Indonesia Energy Conservation and Efficiency Society) |
| MEMR | Ministry of Energy and Mineral Resources |
| MEPS | Minimum Energy Performance Standard |
| MSP | Medium Sized Project |
| MVE | Monitoring, verification and enforcement |
| NAMA | Nationally Appropriate Mitigation Action |
| OJK | Otoritas Jasa Keuangan or Financial Services Authority |
| P3TK EBTKE | MEMR (Research and Development of DGNREEC) |
| PFAN | Private Financing Advisory Network |
| PIF | Project Identification Form |
| PIR | GEF Project Implementation Report |
| PLN | Perusahaan Listrik Negara (State Electricity Company) |
| POPP | Programme and Operations Policies and Procedures |
| PPG | Project Preparation Grant |
| PPP | Public-Private Partnership |
| PT SMI | PT Sarana Multi Infrastruktur - Persero (PT SMI) |
| RAD-GRK | Local Action Plan for Greenhouse Gas Emission Reduction as a supplement to RAN-GRK |
| RAN-GRK | Rencana Aksi Nasional Penurunan Emisi Gas Rumah Kaca (National Action Plan to Reduce Greenhouse Gases Emission) |
| SDGs | Sustainable Development Goals |
| SE4ALL | Sustainable Energy for All |
| SNI | Standar Nasional Indonesia (Indonesia National Standard) |
| STAP | GEF Scientific Technical Advisory Panel |
| TKDN | Tingkat Kandungan Dalam Negeri (Local Content level) |
| TWh | Terawatt-hour |
| U4E | United for Efficiency |
| UNDP-GEF | UNDP Global Environmental Finance Unit |
| UNEP or UN Environment | United Nations Environment Program or UN Environment |
| USAID | United States Agency for International Development |

*Italicized abbreviations/acronyms and titles are from Indonesian titles with their corresponding English title equivalent

# Development Challenge

Context and Global Significance

- With a population of over 250 million and a growth rate of over 5.8% in 2013, Indonesia is facing several interconnected problems. The country is witnessing a high growth in its energy demand (7% per year) and the national electrical generation capacity is failing to keep pace, resulting in underserved areas and frequent power cuts and brownouts. In 2014, 20% of the population did not have access to electricity, and many others only had restricted supplies. This has a negative impact on entrepreneurship, education, health and safety. In addition, Indonesia’s over-reliance on fossil fuels, which accounts for 71% of the country’s energy mix, results in rising greenhouse gas emissions.

- The proliferation of energy efficient and affordable lighting is important to human development because of the significance of lighting in the life of women and men, whether indoor or outdoor in all sectors of the economy. Access to energy efficient lighting (EEL) products and systems is very relevant to national development priorities, global environment and adaptation issues. The proposed project responds to sustainable development goals (SDGs): #7- affordable and clean energy; #9- Industry, innovation and infrastructure; #11- sustainable cities and communities and #12- Responsible consumption and production.

- Government Regulation of the Republic of Indonesia No. 70/2009 on Energy Conservation sets the legal basis for introduction of energy efficiency standards and labeling for electronic appliances. The Ministerial Regulation of the Minister of Energy No.18/2014 came into force in June 2014 and mandates that all compact fluorescent lamps (CFLs) must meet energy efficiency performance standards and must be labeled. The key energy efficiency program of the Ministry includes issuance of energy efficiency regulations, awareness building, energy audits and energy manager program, energy efficiency standards and labeling for appliances and implementation of smart street lighting in cities. Indonesia is also active in the Association of South-East Asian Nations - Standards Harmonization Initiative for Energy Efficiency (ASEAN-SHINE) project regarding performance and testing method for air conditioners, which soon will cover high efficient lighting as well. The Ministry has set an energy efficiency (EE) target to achieve 1% reduction of energy intensity annually and reduction of GHG emission of 14.71 million tCO2 annually by 2019.

- The Directorate General of New-Renewable Energy and Energy Conservation (DGNREEC) of Indonesia was established in August 2010 under the Ministry of Energy and Mineral Resources (MEMR). From March 2011, it began enforcing provisions under Government Regulation 70/2009, which requires that all entities with energy consumption of more than 6,000 tons of oil equivalent per year shall establish an energy efficiency program, appoint an energy manager within the organization, conduct regular energy audits, and implement and report the audit recommendations. DGNREEC established the Energy Efficiency and Conservation Clearing House Indonesia (EECCHI), a facility to promote and share best practices knowledge in energy efficiency and conservation.

- With the issuance of the Presidential Regulation No. 61/2011 on National Action Plan to Reduce Green House Gases or Rencana Aksi Nasional Penurunan Emisi Gas Rumah Kaca (RAN-GRK), the Government initially set a target in 2011 to reduce 5.85 million tons of CO2e by 2014 from the implementation of energy-efficient technologies for home appliances, which reflected its earlier commitment to address the related environmental concern.

- This emissions reduction will contribute to the voluntary national target to reduce 26% of GHG emissions by 2020 which was originally committed in 2009 in Indonesia’s Nationally Appropriate Mitigation Actions (NAMA) pursuant to Cancun Agreement on its own efforts. This was converted in Indonesia’s INDC and later NDC as registered in UNFCCC’s NDC registry on 6 November 2016. As stated therein, the potential emission reduction could reach up to 41% with international support. The Indonesia baseline uses the business-as-usual scenario of emission projections starting 2010, based on a historical trajectory (2000 – 2010), projected increases in the energy sector and the absence of mitigation actions at the outset.

The adoption of the Paris Agreement marks a critical turning point for global climate action in the country. Indonesia’s NDC outlined its transition to a low-carbon future, committing to an unconditional emissions reduction of 29 percent by 2030 compared to the business-as-usual (BAU) scenario. The NDC reiterated Indonesia’s voluntary target of reducing its emissions by 26 percent against the baseline scenario in 2020. As mandated by RAN-GRK, every province in the country needs to develop a Local Action Plan for Greenhouse Gas Emission Reduction or Rencana Aksi Daerah penurunan emisi Gas Rumah Kaca (RAD-GRK) as a supplement to RAN-GRK. The implementation of these mitigation action plans at the provincial level is thus critical to achieving national climate goals and to laying the foundation for more ambitious climate action beyond 2020.

- Considering the above, the Government of Indonesia is proposing a project entitled “Advancing Indonesia’s Lighting Market to High Efficient Technologies (ADLIGHT)” for funding by the Global Environmental Facility (GEF) through the United Nations Development Programme (UNDP) and the United Nations Environment Programme (UN Environment) which is in line with the above-mentioned energy efficiency national policies and plans. The ADLIGHT project aims to promote the increased deployment of high efficiency lighting technologies in Indonesia through the transformation of the national market, thereby reducing electricity demand and the related greenhouse gas (GHG) emissions. The project is expected to lead to increased market penetration of high efficiency lighting through capacity building for the country’s lighting industry, thereby enhancing the local manufacturing capability to locally-produce highly quality lighting systems in line with MEPS, through introducing quality and minimum energy performance regulation, procurement policies and improved customs procedures and through introduction of new business models and awareness raising.

- The ADLIGHT Project of Indonesia is among ten (10) national child projects that will receive support for the development program using an integrated policy approach through the multi-country arrangement under the “Leapfrogging Markets to High Efficiency Products Program (for appliances, including lighting, and electrical equipment)”, also a GEF-supported program, also called as the “Global Leapfrogging Program (GLP)”. The GLP contributes to the UN Secretary General’s Sustainable Energy for All (SE4ALL) initiative’s Lighting and Appliance & Equipment Accelerators. The SE4ALL Global Project has formed a global partnership, named United for Efficiency (U4E), which is a global effort supporting developing countries and emerging economies to move their markets to energy-efficient appliances and equipment. Further, by the end of the SE4ALL project, it will have the commitment from at least thirty developing countries and emerging economies, including Indonesia, to transform their markets to energy efficient lighting, appliances, and equipment.

- The Global Leapfrogging Program will utilize the tools already developed under SE4ALL Global Project, such as country assessments and best practice policy guides in order to increase the number of countries committing to advance energy efficient products considering their respective national context and needs. Further, as a child project under the GLP, the ADLIGHT Project will benefit from the support to be provided by the GLP e.g. by following the consensus recommendations on the policy framework when developing technical guides and training, such as in MEPS and energy labeling. Fig. 1 illustrates the relationship among the SE4ALL Global Project, the Global Leapfrogging Program and the ADLIGHT Project.

Fig. 1: Relationship among the SE4ALL Global Project, Global Leapfrogging Program

and the ADLIGHT Project of Indonesia among other Child Projects

Thus, for the participation in the SE4ALL Global Project, the Project Concept Note (PCN) for ADLIGHT was submitted by the Government of Indonesia in March 2016 and includes: (a) capacity building on MEPS for local lighting industry, (b) regulatory mechanisms and MVE and (c) high efficiency lighting technology penetration. The PCN is herein being elaborated and developed as the ADLIGHT Project Document for a Full Size Project (FSP) to be proposed with GEF 6 funding.

Barriers to Implementation of Programs in the Local Manufacturing and Application of Energy Efficient Lighting Systems

- The archipelagic nature of Indonesia, consisting of 18,307 islands (Indonesia National Institute of Aeronautics and Space – LAPAN 2002), is prone to porous borders and allows the local market to be confronted by imported low quality Energy Efficient Lighting (EEL) products. This situation hampers consumer’s access to good quality of LED products due to relatively easy access to substandard EELs (oftentimes unknowingly) entering the market in Indonesia. Without Minimum Energy Performance Standard (MEPS) being enforced, people are buying substandard EEL products and miss the benefits of EEL products. Without MEPS, the penetration of good quality of EEL products in the market will face difficulty to compete with the low-priced substandard lighting products. The process to issue MEPS requires national standardization procedures set by the National Standardization Agency (BSN). According to the Government Regulation (PP) number 102/2000 regarding National Standardization, standard development can be approached through 2 different methods; 1) consensus, and 2) scientific evidence. For standards with a development dimension value, such as the MEPS, consensus is likely to be the method used in the process. In creating consensus, approval from all relevant stakeholders is crucial and local manufactures will have a bigger percentage in the overall portion in consensus. Currently, the comparison percentage between local and international EEL brands in 3 associations (GAMATRINDO, APERLINDO and ALINDO) is 76% (local manufacturers) and 24% (imported assemblers). Support to local manufacturers on the principles of MEPS and capacity building for local manufacturers will be crucial in order to realize a comprehensive draft of MEPS.

- The e-catalogue, an electronic platform that provides information access to goods and services for public procurement in Indonesia through e-tendering and e-purchasing, was created by the Indonesia Public Procurement Agency (LKPP) to increase transparency and accountability of public procurement in Indonesia. The e-catalogue covers approximately 25% of total public procurement in 2016 (LKPP 2016). The use of the e-catalogue in public procurement is growing steadily since its first launch in 2010, and it was re-enforced under Presidential Regulation number 70/2012 – an upgrade to the previous Presidential Regulation number 54/2010 regarding e-procurement. Despite the practical use of the e-catalogue, which cut significantly the lengthy tendering process in public procurement, the platform still requires improvements. E.g. for public procurement in EEL equipment, the determined specifications are disfavoring local EEL manufacturers. The reason behind the challenge to enter e-tendering is not a matter of quality or technical standards, but more of administrative barriers. The introduction of MEPS should create a level playing field with equal participation of international and local EEL manufacturers.

- The Government of Indonesia is committed to tap the vast economic and environmental benefits of the transformation to energy efficient appliances and lighting products. Three related projects and initiatives in removing barriers regarding introduction of energy efficient lighting systems consist of the UNDP-GEF BRESL Project, the UN Environment’s ASEAN-SHINE Project and the UN Environment En.lighten initiative (details will be discussed further below in the Baseline Scenario section). These projects and other similar projects and their outcomes altogether have been shaping the country’s lighting industry and its markets through the progress of their barrier removal efforts. The lighting industry in the region is evolving rapidly and is moving to a need for further development of EE lighting towards high energy efficient lighting by means of LED products.

For the BRESL project, the following were some of the significant barriers that were addressed and can be complemented by the ADLIGHT Project, including: (a) low public awareness on energy efficiency and absent consumer knowledge on life time costs (consumers choose the cheapest product which is usually not efficient); (b) low energy price (electricity tariff) due to government subsidy; (c) lack of standards and regulations that incentivize energy efficient lighting production, commercial demand and public procurement; (d) lack of local manufacture and capability to implement EE&C technology; and (e) lack of testing laboratory for energy performance. The achievements of the BRESL project laid the foundation of the standards development, capacity building, laboratory and testing procedures, policies, road map and action plan for efficient lighting system as it started to focus on the CFL transition.

ASEAN SHINE (2016-2020) aims to support the establishment of the ASEAN Economic Community by removing non-tariff barriers to trade through harmonization of product standards. ASEAN SHINE currently works on standards harmonization across ASEAN for air conditioners and lighting products. In the area of lighting, the achievements include: the establishment of ASEAN SHINE Lighting Technical and Policy workgroup and the agreement of ASEAN Member States to establish harmonized standards for lighting products in the region.

The UN Environment En.lighten initiative focused on the barriers related to the classification and quality status of the numerous EEL products and applications; the monitoring, verification and enforcement (MVE) issues and the tapping of the energy saving potential in the lighting sector. It examined the status of the efficient lighting MVE activities and programs in six ASEAN countries.

As initially identified by the abovementioned related projects, the barriers to energy efficient lighting deployment have been or are still being addressed and can be complemented by the proposed ADLIGHT Project.

- A variety of barriers to advancing Indonesia’s lighting market to high efficient technologies were identified during the numerous focus group discussions and bilateral meetings during the development of the ADLIGHT Child project under the UN Environment-GEF Global Leapfrogging Program:

- Limited capacity of lighting manufacturers: Although Indonesia is home to an important number of lighting manufacturers; most local manufacturers have limited capacity to meet standards for energy efficiency and quality, and do not have the technical and financial capacity to innovate, thus reducing their capability to produce affordable, high quality LEDs and meet future MEPS standards. Local businessmen do not seem to be capable of developing business transformation plans for shifting from conventional lighting manufacture to high efficiency lighting systems such as LEDs. Without such plans in place, financial institutions develop a risk-averse attitude and therefore, are not able to fund local lighting manufacturers for upgrading production lines.

- Absence of MEPS for LEDs: at the moment, Indonesia does not have any Minimum Energy Performance Standards (MEPS) in place for lighting products other than CFLs. Indonesian consumers will buy any lamp available in the market which usually leads to purchasing low cost, albeit inefficient lamps. At the same time, there is still limited capacity with Customs officers and Ministry of Trade staff to curtail the import of inefficient lamps into the country even as the adoption and implementation of the MEPS for CFLs has already started. As long as low priced - although of low quality - conventional lighting products continue to be distributed, Indonesian consumers still prefer them over LED lighting products. This discourages the manufacturers to produce high energy efficient lighting products.

- Absence of guidelines for public procurement: because no guidelines exist for public procurement, street lighting is often quite inefficient in Indonesia. By having a standard minimum quality requirement available in the guidelines for public procurement, consumers, manufacturers and importers of LED lights in Indonesia will have reference in complying with standards requirement, and therefore, the quality of LED lighting to be made available in Indonesia can be rightly monitored, verified and enforced (in an MVE system). With the standard minimum quality that is aligned with international standards, local LED manufactures have the chance for their products to be included for public procurement as listed in the e-Catalogue. According to statistics data of the state-owned electricity company or Perusahaan Listrik Negara (PLN), the street lighting in Indonesia consumed 3.2 TWh in 2013, which is equal to the emission of 2.6 m tCO2 eq. In 2014, MEMR piloted smart street lighting in two cities and developed a Nationally Appropriate Mitigation Actions (NAMAs) proposal (“Smart Street Lighting Initiative (SSLI)”) that aimed at reducing GHG emissions by increasing the energy efficiency of street lighting systems in Indonesian cities. Application of high efficient street lighting has been one of the priority programs of the Ministry and is in line with another program on Green City Development in cooperation with the Ministry of Public Works.

- Absence of regulatory mechanisms for MVE and lack of capacity of testing laboratories: there are currently no regulatory mechanisms for efficient lighting monitoring, verification and enforcement (MVE) in Indonesia including for mitigation measurement. To date, the Secretariat of RAN-GRK (or the National Action Plan to Reduce Greenhouse Gases Emission) with support from GIZ (or the German International Development Agency) and Japan International Cooperation Agency (JICA) has issued the Guideline for Monitoring, Evaluation and Reporting under the National and Local Action Plans to Reduce Greenhouse Gases Emission (RAN-GRK and RAD-GRK) at a broader MEMR ministerial level. This is certainly an initial step towards a measurement, reporting and verification system, but there is currently no institutional capacity for its implementation, let alone the enforcement. On the other hand, the capacity of existing testing laboratories needs to be improved with updated testing standards on MEPS for CFL to check non-compliant products as well as prepare to cater to the desired demand growth of high efficiency lighting systems including the LEDs.

- Further, in the Logical Framework Analysis (LFA) Workshop conducted in May 22-23, 2017, in Bali, Indonesia during the PPG stage of the ADLIGHT project development, the following concrete problems and challenges were confirmed as the main issues that affect the local manufacture and application of energy efficient lighting systems:

- LED lamp products in the local market have uncertain quality:

- High number of complaints on supposed to be high efficient lighting products

- Lack of standards on EE lighting systems

- Lack of accredited testing laboratories

- Accredited laboratory infrastructure and facilities are not established yet

- No MEPS on LED systems

- Lack of quality control on EE lighting

- Regulation and supervision throughout Indonesia is not optimal

- Low quality and quantity of monitoring of LED products

- Lack of sharing of international knowledge on EE lighting manufacturing

- Low budget allocation for monitoring and MEPS development.

- Lack of clear policy and institutional support to promote manufacture and application of high efficient lighting technology:

- Lack of market data on production and application of lighting in Indonesia, to inform policy development

- Lack of support in manufacturing from government

- Lack of government investments on EE lighting projects

- Lack of coordination among related ministries and local regional/provincial government

- Import policy does not support local LED industry

- Lack of infrastructure to support LED industry growth (logistics, etc.)

- Lack of studies on cost-benefit analysis on LED to support policy making

- Limited national and local budget allocation for EE lighting investment

- Lack of EE lighting implementation incentives from government

- Lack of harmony among related ministries and agencies regarding LED manufacture and application

- Lack of legal basis for establishing a coordination mechanisms in LED

- Government procurement policy is still on least cost approach and the projects are meant for public service and not for making profits (it is not necessarily oriented for life-cycle costing that can justify higher first cost but could be more profitable in the long run)

- EE lighting cannot be a priority in budget allocation in government procurement as long as procurement regulations are based on least up-front costs instead of life-cycle costs

- Lack of tax policy support from government for EE lighting investment and manufacture

- Small market share for locally produced EE lighting products

- Government market for EE lighting is limited by availability of budget

- Low absorption of EE lighting systems by government and other users

- Low preference to select local EE lighting products

- EE lighting budget line is not prioritized compared to other infrastructure

- Low uptake from ESCO on EE lighting

- Benefit from EE lights deployment are not recognized

- Market confidence is not yet there to use local EE lighting products

- Absence of updated procurement guidelines containing standard minimum quality. Government procurement uses a reference listing of registered products and suppliers as contained in the e-Catalogue but this reference coding guide consists of imported products mostly since local producers do not easily become a registered supplier in E-catalogue for government projects.

- Lack of capacity to prepare EE lighting investment projects for public private partnership

- Not many financing institutions or local banks would like to give loans for energy efficient projects

- Lack of kWh meters to measure saving in energy and monetary benefits

The Problem Tree resulting from the LFA Workshop is seen in Annex Q:

- These barriers and possible solutions were further elaborated in the ADLIGHT Validation Workshop conducted with stakeholders and relevant agencies and ministries on July 19-20, 2017. Follow-up focus group discussions (FGDs) on one-on-one basis were also conducted to supplement and update the information and the basis for the detailed project design. These barriers will be addressed by the project towards further resolving them to achieve the outcomes and overall objective of the project.

Baseline Scenario

- In 2016, Indonesia’s on grid electricity consumption was 217.83 TWh. Lighting is estimated to account for 18.8% (ca. 41 TWh) of this electricity consumption in 2016 as shown in Fig. 2. Details can be found in Annex L.

Fig. 2: Estimated Share of Electricity for Lighting in Indonesia for each Sector in Year 2016

- In terms of EE implementation, the MEMR has allocated budget for programs that involve the implementation of energy efficiency activities such as energy audits, fiscal policies, and regulations focusing ES&L. The MEMR, in close coordination with the Ministry of Finance, has implemented import tax reduction for companies that import high-energy-efficiency lights to the country, in order to provide an incentive for lighting industries in the country to manufacture or to assemble energy-efficient products. Specific activities of these programs will be subsumed into ADLIGHT as baseline activities.

- Indonesia implemented several projects related to energy efficient lighting during the period 2009 to 2016. The UNDP-GEF BRESL project - Barrier Removal to the Cost Effective Development and Implementation of Energy Efficiency Standards and Labeling - laid the foundation of the standards development, capacity building, laboratory and testing procedures, policies, road map and action plan for efficient lighting system as it started to focus on the CFL transition. Indonesia was among six countries participating in this project including Bangladesh, China, Pakistan, Thailand and Vietnam. The project has assisted in developing energy efficiency standards and labeling for 6 home appliances including CFL; improved the capacity of testing laboratories so there are at least 4 appointed testing labs for CFL; and built capacity of 5 CFL manufacturers/assemblers to meet the mandatory performance standard. Other results of the BRESL project in Indonesia are the establishment of a database of energy efficient products and implementation of a consumer education scheme. Through the influence of the BRESL project, the government has started to come up with a procurement scheme to go for energy efficient products. The BRESL project also offered training to selected personnel from appliance manufacturing companies regarding ES&L as well as MEPS and enables them to apply the concepts learned in workshops. Such trainings are expected to reduce the barrier related to the inadequate technical know-how in implementing energy efficiency measures when going for ES&L.

- The Switch-Asia project ASEAN SHINE is implemented under the steering of the ASEAN Member States and has been recognized as a key Dialogue Partner by the ASEAN Ministers of Energy Meeting (AMEM). ASEAN SHINE adopts a holistic approach to market transformation, by using mechanisms including policy, regulations, capacity building along the supply chain, and awareness raising among end-users. The ASEAN SHINE lighting-regional market assessment has been done by International Institute for Energy Conservation (IIEC) in year 2015 in all ASEAN member states. The assessment of Indonesia shows that the residential sector was the largest end-use sector (accounting for 41% of total national annual electricity consumption) for 2013. The electrification ratio in Indonesia in year 2013 was 74% (65 million households). Lighting points per household varies from 8 to 12 lamps. Common lamp types are (a) T8 fluorescent lamps (tube and circular), (b) screw-base omnidirectional: CFLs (5 – 8w), LED (5-9W), incandescent, and (c) pin-base directional: Halogen. The estimated lamp stock is 394 million. Based on the survey, it was shown that the lamps in the residential sector were dominated by CFL (71%), followed by LED (20%) and Incandescent (0.5%) and Halogen (0.5%) lighting.

In a related development, LED lamps were collected from nine ASEAN countries in December 2016 (including Cambodia, Indonesia, Lao PDR, Malaysia, Myanmar, Philippines, Singapore, Thailand and Vietnam) for an LED benchmarking exercise, funded by the Australian Government, as part of the ASEAN SHINE initiative on Lighting. The test covered non-dimmable integral LED general service (non-directional) lamps, 3 -15 watts with normal cap size and color temperature according to local preference. The testing of these products using CIE 5025 test method demonstrated that while good quality LED products are available, significant numbers of poor quality products remain available in the market. The comparative results for Indonesia can be used to benchmark the LED production improvements to suit local and international market demand.

- In 2014, the UN Environment En.lighten initiative performed a survey on lamp sampling in Cambodia, Indonesia, Lao DPR, the Philippines, Thailand and Vietnam, which showed that in Indonesia the most popular wattage for CFL and LED lamps are 8 watts (W) and 7W, respectively. It was observed that there are quite a number of local brands available in Jakarta’s lighting market. However, based on on-shelf frequency, international brands still dominate the lighting market in the capital city of Indonesia. For CFL lamps, it is evident that 5W dimmable light (DL) is the most popular model in Indonesia, followed by 8W DL, 14W DL and 18W DL. Philips dominates the Indonesia lighting market, especially in the capital city and Osram is the second brand. The preferred wattages for majority Indonesia are in the low-wattage range (5-10W), followed by mid-wattage range (11-18W) and high wattages. There are more than 18 different wattages of lamps available in the Indonesian market. The wide diversity of lamps in Indonesia clearly shows the size of Indonesian lighting market. Indonesian people are more likely to purchase lower wattage than higher wattage lamps. This fact is different from other ASEAN countries. On the other hand, for LED lamps, 7W DL dominates majority shelf in Jakarta, followed by 9W DL and 11W DL. Here, Philips dominates the efficient lighting market of Indonesia and followed by Osram and Panasonic. Daylight is the popular color for the Indonesian market.

The UN Environment En.lighten initiative also examined the status of the efficient lighting MVE activities and programs in the above-mentioned six ASEAN countries. Through its country lighting assessments in 2010, UN Environment En.lighten estimated that Indonesia has a lighting saving potential of 6.32% of total on-grid electricity use. This is equivalent to a saving of 9.35 TWh or 7.17 Mt of CO2 emissions.

- The shift to CFL with its MEPS adoption and implementation as initiated by the BRESL Project is a big step in the right direction and is moving to a need for further development of EE lighting towards high energy efficient lighting by means of LED products. The ADLIGHT will provide the critical bridging of gaps for the energy efficient lighting technology development program to materialize.

- UNDP in collaboration with MEMR of Indonesia is currently implementing a five-year (2017-2021) project called the “Market Transformation for Renewable Energy and Energy Efficiency” (MTRE3) or also referred to as the Market Transformation through Design and Implementation of Appropriate Mitigation Actions in the Energy Sector”. The project’s main objective is to support the design and implementation of appropriate climate change mitigation action in the energy generation and energy end use sectors. In the energy efficiency sector, it is expected that a 20% reduction on Energy Consumption Intensity (IKE) in the commercial building sector, particularly in office buildings, would be achieved and maintained. The project targets a total of 50,000 m2 of commercial floor space, and could expand to other building floor space up to 500,000 m2, in addition to the baseline target. In this commercial building sector, lighting systems consume significant shares of total energy consumption. Thus, retrofitting the conventional lamps into energy efficient lamps is one of the solutions to meet the target. In addition, one of the activities to meet the project objectives it to establish a Business Center or ‘meeting point’ for ESCOs and the private sector. The activities in the MTRE3 related to energy efficient lighting and ESCO models are subsumed into, and considered as, among the baseline activities in the ADLIGHT project, as discussed below.

- In order to provide more efficient street lighting in Indonesia, ADB, the state-owned utility PT PLN and MEMR collaborated on implementation of a pilot LED Municipal Streetlight and PLN Substation Retrofit Project (Pilot LED Project). The objective of the Pilot LED Project was to demonstrate reduction in the peak electricity demand in the selected municipalities and pilot PLN substations by focusing on demand side management through street lamp retrofit using relatively new energy-efficient LED technology. The pilot consisted of two municipalities in Central Java (Batang and Semarang) and PLN substation and power generation facilities in West Java province. A total of 1,439 LEDs have been retrofitted. The post-retrofit meter reading shows that the energy savings from two municipalities, Batang, Semarang, and PLN substation are up to 59%, 44%, and 44%, respectively. The investment payback period, where cost saving for lower maintenance of LEDs is taken into account, are 3.6 years for Batang and 7.0 years for Semarang, respectively. The significant longer payback period for Semarang was due to the increased cost of LEDs lamps needed to meet the city’s unusually high light level requirements and the addition of control technology in the lamps. This project has addressed four significant challenges and recommendations explained as follows. First, municipalities are often not willing or able to implement LED retrofits due to lacking benefit from the energy savings. This is because, in general, PLN does not bill the municipalities for street lighting based on actual electricity consumption but on a flat fee (lump sum) basis which is not related to actual electricity consumed, even where PLN meters are installed. In fact, street lighting energy consumption is usually not metered. The second challenge is limited knowledge of LEDs and capacity to retrofit, operate and to maintain LEDs. The recommendation for this is to develop a national standard on street lighting that addresses LED technology and incorporates the best practices and lessons learned in the project. The Ministry of Transportation of Indonesia is currently drafting a regulation on street lighting with ADB support. The implementation of multiple demonstration LED projects with different retrofit and financing structures and nationwide capacity-building are also recommended to increase understanding and to build capacity within municipalities. The third challenge is the absence of sufficient municipality budgets and access to financing for citywide LED retrofit programs. It is recommended to develop a new financial product that allow financial institutions and third-party entities like ESCOs to provide the needed long-term financing such as national credit guarantee to back up loans, capital cost and insurance of the street lighting retrofit program. Finally, the fourth challenge is difficulty of municipalities and government agencies to be able to use ESCO services. This is due to absent formalized regulation to support multi-year contracts with ESCOs, government’s procurement procedures based on least cost selection instead of life cycle cost, and budget disincentives.

- Recently, the MEMR of Indonesia has released a Ministerial Decree named Permen ESDM No 14 Year 2016 (issued on 8 June 2016) on ESCO regulation. The main objective is to overcome the barriers for government agencies to access ESCOs services. The regulation provides definitions and guidelines for ESCO service. However, further regulation is still required to allow governments to access ESCO services on paid-from-saving basis.

- The ADLIGHT Project will build upon relevant ongoing EE lighting projects/programs in the country and draw lessons including from those already completed and ongoing. The following were identified during the PPG phase that could be relevant to ADLIGHT, which are mostly in the application of local efficient lighting products:

| Project Name - Sponsor | Areas of Interest/Status | ADLIGHT Additional Outputs* |
| --- | --- | --- |
| Market Transformation through Design and Implementation of Appropriate Mitigation Actions in the Energy Sector (MTRE3)-UNDP | The project will put in place enabling environment and removing barriers to sustainable market of renewable energy and energy efficiency. To achieve this purpose, the project will focus its interventions in renewable-based electricity generation and energy efficiency in commercial building interventions. The project will consist of 3 main components: (1) Climate change mitigation options for the RE-based energy generation and energy efficiency; (2) Market transformation through implementation of appropriate mitigation actions; (3) Measurement, Reporting and Verification (MRV) system and national registry for mitigation actions - Ongoing 2017-2021 | - Market transformation to energy efficient lighting with enhancements on local EEL production capability - Robust policy and guidelines on EEL production and utilization in buildings and street lighting application - Strengthening in MRV and MVE systems with adoption of SNI/MEPS and testing laboratories to support them |
| ASEAN SHINE | Standards harmonization across ASEAN for air conditioners and lighting products in support of the ASEAN Plan of Action for Energy Cooperation (2016-2025) | - MEPS and energy labels in place for high efficient energy lighting products |
| UN Environment en.lighten Initiative | Status of the efficient lighting MVE activities, programs in the selected six ASEAN countries, including Indonesia, the classification and quality status of the numerous EEL products and application, benchmarking and tapping of the energy saving potential in the lighting sector | - Regulatory mechanisms for efficient lighting monitoring, verification and enforcement (MVE) * |
| Super-Efficient Equipment and Appliance Deployment (SEAD) Initiative - Clean Energy Ministerial and the International Partnership for Energy Efficiency Cooperation | Aiming to make it easier for governments and the private sector to capitalize on opportunities regarding appliance and equipment (including lighting) efficiency to reduce energy demand and carbon emissions while lowering energy costs for consumers, businesses, and institutions - Ongoing | - Policy and guidelines for public procurement of LED lighting products (residential, commercial and outdoor) developed and adopted |
| Indonesia Clean Energy Development (ICED) Phase II - USAID | Establish an effective policy, regulatory and incentive environment for low-emission growth in the energy sector, while simultaneously attracting public and private sector investment in clean energy development. Contributing to the Government of Indonesia’s (GOI) targets for increasing access to energy, while concurrently supporting national efforts to curb GHG emissions. Focus on Energy Sustainable Finance, Previous project on EE Street Lighting Pilot in Makasar, ICED in collaboration with GIZ SSLI – Ongoing 2015 -2020 | - Capacity development for policy makers, enforcement &custom officials and other relevant government agencies on market control procedures |
| AFD EE street Lighting - Agence Française de Développement (AFD) | Contribute to Indonesia's efforts in the fight against climate change (appropriate infrastructure development, establishment of dedicated financial instruments). Relevant project in EE Street Lighting in Bogor and Mataram – Ongoing at a preliminary stage | - Regulatory mechanisms for efficient lighting monitoring, verification and enforcement (MVE) including testing standards defined and implemented |
| LED Street Lighting Project in Indonesia – Asian Development Bank | Implement LED Retrofit Project in Batang and Semarang (Pilot Cities) and several power stations of State Owned Utility (PLN) - Completed 2016. | - Pilot demonstrations for accelerated LED lamp deployment in buildings and for street lighting in the context of sustainable cities |
| Smart Street Lighting Initiative (SSLI) NAMA Indonesia - Die Deutsche Gesellschaft für Internationale Zusammenarbeit (GIZ) | Program to increase energy efficiency of SL through implementing efficient technology (lamp, armature, control system, etc) focusing on study in 22 cities and pilot in several cities – piloting completed in 2014; development phase (2015-2017); transformation phase (2017-2019) | - Pilot demonstrations for accelerated LED lamp deployment in buildings and for street lighting in the context of sustainable cities |
| Environmental Support Program Phase 3 (ESP3) - Danish International Development Agency (DANIDA) | Developing inclusive and sustainable growth through improved environmental management and climate change mitigation and adaptation. Supports in implementation and monitoring energy efficiency, energy conservation and renewable energy including pilot projects that will provide demonstration and experience of energy efficiency, energy conservation and renewable energy in Indonesia - Ongoing | - innovative financial mechanisms enabling the accelerated penetration of advanced lighting systems, including ESCO models |
| Green Banking - PT Sarana Multi Infrastruktur - Persero (PT SMI) in partnership with MTRE3 Project | Green infrastructure bank transforming into an infrastructure bank to help fund roads, railways and seaports with private backing and interested in street lighting financing - Ongoing | - Business transformation plans of selected local lighting manufacturers to convert their production lines to the production of more energy efficient LED lamps |
| Synergy Efficiency Solutions (SES) – Private Company | Assists companies in the implementation of savings solutions by minimizing investment costs through its ESCO financing options focusing on energy efficiency, including EE Lighting – On going | - technical assistance program for selected local EEL product manufacturers to upgrade manufacturing facilities |
| Promoting Industrial Energy Efficiency through System Optimization and Energy Management Standards in Indonesia – UNIDO/GEF | Promoting industrial energy efficiency through system optimization approach and introduction of ISO energy management standards – For completion in December 2017 | - business transformation plans of selected local lighting manufacturers to convert their production lines to the production of more energy efficient LED lamps |
| Private Financing Advisory Network (PFAN) – USAID Climate Technology Initiative (CTI) and UNFCCC Expert Group on Technology Transfer | Bridge the gap between investments and clean energy businesses. Identify promising clean energy projects at an early stage and provide mentoring for developing a business plan, investment pitch, and growth strategy, significantly enhancing the possibility of financial closure for the projects – Completed 2012-2014 | - Implemented awareness and promotion program and information system explaining the benefits of high energy efficient lighting technologies |

*Almost all ADLIGHT outputs are commonly applicable to and supplementing the results of the baseline projects listed above through the barrier removal activities of ADLIGHT in pursuit of its goals and objectives.

- According to the definition of the Ministry of Trade, a local manufacturer is an entity producing products that contain at least 40% locally sourced components. The local LED lighting industry in Indonesia is represented by three major industry associations: GAMATRINDO, APERLINDO, and ALINDO. The following table describes number of EE lighting local manufacturers under the three LED industry associations (GAMATRINDO, APERLINDO and ALINDO) with the 2016 production of LED lamps and average efficiency (lumens per watt) both indoor and outdoor types.

|  | Total LED Industry under the Three Associations in Indonesia |
| --- | --- |
| Total no. of members | 68 |
| No. of members in - Indoor light - Outdoor (Street Light) | 68 6 |
| 2016 Production - Indoor light - Outdoor (Street Light) | 98.2 million LED bulbs 51.8 thousands LED-SL |
| 2016 Average Efficiency, lumens per watt - Indoor light - Outdoor (Street Light) | 70 - 90 100 – 110 |

Notes:

  - GAMATRINDO has ten member manufacturers, all of them produce indoor light lamps and only 1 produces outdoor (streetlight)

  - APERLINDO has 48 member manufacturers, all of them produce indoor light lamps and only 1 manufacturer produces outdoor (streetlight)

  - ALINDO has ten member manufacturers, all of them produce indoor light lamps and only 1 manufacturer produces outdoor (streetlight).

Based on data collected from three associations of local EE lighting manufacturers, in the last 8 years from 2007 to 2015, the production of in-door lamps increased by 4% per year for production without LED and by 7% per year for production with LED. By 2015, total in-door lamp production without LED lamps from domestic lighting companies reached 360 million lamps which was still dominated by CFL with a share of 63.6% followed by LED (18.2%), fluorescent lamps (17.1%) and incandescent bulbs (1.1%). The production of CFL lamps, however, increased more than 3 times from 100 million lamps in 2007 up to 340 million lamps in 2014 although in the following year (2015) there was a decrease of 50 million lamps. This seems to be in line with the development of LED lighting technology.

In general, the following table shows significant changes in production patterns as a reflection of market changes or consumer changes in lamp utilization. In addition, two developments are particularly noteworthy: the drastic decline in production of incandescent and fluorescent lamps and the production increases for CFL and LED light bulbs.

Production capacity of locally produced electric lamps in Indonesia

| Year | Indoor (type of lamps), number of lamp (‘000) |  |  |  | Total indoor (‘000) |  | Out door (Street lighting), number of street lighting (PJU) |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Incandes cent | Fluores cent | CFL | LED | Total without LED | Total with LED | Non-LED Street lighting | LED Street lighting |
| 2007 | 90,000 | 65,000 | 100,000 | - | 255,000 | 255,000 | NA | NA |
| 2008 | 70,000 | 75,000 | 120,000 | - | 265,000 | 265,000 | NA | NA |
| 2009 | 60,000 | 75,000 | 160,000 | - | 295,000 | 295,000 | NA | NA |
| 2010 | 50,000 | 75,000 | 200,000 | - | 325,000 | 325,000 | NA | NA |
| 2011 | 40,000 | 75,000 | 260,000 | - | 375,000 | 375,000 | NA | NA |
| 2012 | 40,000 | 75,000 | 320,000 | - | 435,000 | 435,000 | NA | NA |
| 2013 | 25,000 | 75,000 | 330,000 | 15,000 | 430,000 | 445,000 | NA | NA |
| 2014 | 10,000 | 80,000 | 340,000 | 40,000 | 430,000 | 470,000 | NA | 5,938 |
| 2015 | 5,000 | 75,000 | 280,000 | 80,002 | 360,000 | 440,002 | NA | 4,321 |

Source: Aggregated from three Associations of EEL local manufacturers

# Strategy

Project Rationale and Policy Conformity

- The ADLIGHT project aims to promote the increased deployment of high efficiency lighting technologies in Indonesia through the transformation of the national market, thereby reducing electricity demand and the related greenhouse gas (GHG) emissions. The project is expected to lead to increased market penetration of high efficiency lighting through capacity building for the country’s lighting industry, thereby enhancing the local manufacturing capability to locally-produce highly quality lighting systems in line with MEPS, through introducing quality and minimum energy performance regulation, procurement policies and improved customs procedures and through introduction of new business models and awareness raising. The project proposes to have an innovative approach that covers assistance to the upstream portion of the LED value chain, across the midstream of delivery and marketing in to the downstream application of the LED products. Thus, the theory of change includes consideration of internal factors (relating to project design and implementation) and external factors (relating to other partners, stakeholders and the entire value chain participants) that will be critical for achieving the expected change in increasing the national market penetration of affordable, high quality LEDs. Current achievements in the state-of-the–art of the LED technology will support the overall development strategy, including inputs and findings from evaluation and other credible research. With ADLIGHT being aligned with the GEF-supported programmatic global projects, i.e. the Global U4E Project and the Global Leapfrogging Program being implemented by UN Environment, the proposed project will gain the necessary working linkages as well as knowledge, good practices and lessons learned to be shared from said multi-country projects. Likewise, previous work and ongoing projects by UNDP, UN Environment and others, in this country and in other relevant regional contexts, e.g. ASEAN will add to the available resources for ADLIGHT. The ADLIGHT project should carefully examine the dynamics of the entire LED industry from production to application of the LED lamps.

- The proposed project focusing on lighting is in line with the national level theory of change that is being pursued by the Government. The Indonesian Presidential Regulation No.61/2011 on the National Action Plan to Reduce Greenhouse Gases Emission (RAN-GRK), which has set voluntary target for Indonesia of 26% GHG emission reduction by unilateral efforts and 41% emission reduction with international support in 2020 from its trajectory business as usual GHG emission scenario. The interventions proposed under RAN-GRK are potentially considered as NAMAs. RAN-GRK targets reduction of 22 million tons CO2eq by 2020, which shall result from the implementation of energy efficiency actions and 4.53 million tons CO2eq is from implementation of various renewable energy technologies, such as micro and mini hydro, solar photovoltaic, wind power and biomass.

In the energy sector, the Indonesian Energy Law 30/2007 and Presidential Regulation 5/2006 on National Energy Policy renewable energy is targeted to contribute 17% of the primary energy mix in 2025 and energy efficiency in industries, buildings and households is expected to save 15.6% of the total primary energy needed in 2025. In addition, the Government of Indonesia is targeting 100% electrification by 2020, with special annual budget allocation for Rural Electrification Program. Efficient lighting will play a key role in meeting these targets.

Alternative Scenario

- The overall goal of the ADLIGHT project is to reduce the growth rate of annual GHG emissions from lighting energy use by means of reducing electricity consumption in the energy end-use sectors. This is done with a gender-responsive approach, responding to the needs and capacity of women and men.

The project objective of ADLIGHT is to increase the penetration of high quality energy-efficient lighting technologies in Indonesia through the transformation of the national market, thereby reducing electricity demand and the related greenhouse gas (GHG) emissions. Although LED penetration is gradually increasing in Indonesia, these are often low quality products thereby harming the consumer confidence in LED. The specific situation of Indonesia being an archipelago leads to the situation where it is very easy for low quality products to enter the market. The situation in Indonesia is therefore still challenging in terms of creating a market for high quality LED lighting that is  at the same time affordable to consumers and progresses gender equality.

From the barrier analysis described above, the key barriers that need to be addressed are the following:

- Limited capacity of local lighting manufacturers to produce affordable, high quality energy efficient lighting which meet future MEPS and can lead to higher penetration of these products

- Lack of clear policy, regulatory mechanisms and institutional support to promote import, manufacturing and application of high efficient lighting technology

- Limited demand and available business models for energy efficient lighting products resulting in a small market share for locally produced EE lighting products

- Lack of gender-analysis on the LED lighting market in Indonesia, and therefore lack of gender-sensitive approaches within the market.

The project builds on the NDC commitment of Indonesia and proposes an alternative scenario by supporting Indonesia to advance its market to energy efficient lighting technologies. It also builds upon the proven integrated approach that has been successfully developed and introduced during the implementation of the GEF-financed UN Environment implemented En.lighten project and together with results of other earlier initiatives will guide the country to successfully transition to a greatly expanded EE lighting market. The project design is closely following the Concept Note which was earlier agreed on by the MEMR as the Implementing Partner and UN Environment, brought about by the SE4ALL Global Project and the Global Leapfrogging Program as described above. Correspondingly, the ADLIGHT approach comprises the following strategies, each addressing the above-mentioned key barriers to this transition in attaining the objective, consistent with the theory of change discussed above:

Support to local lighting industry to improve the quality and efficiency of lamps and ballasts: The project will collaborate with the Indonesian lamp manufacturing associations to provide support to Indonesian lighting manufacturers to increase their capacity to produce high quality energy efficient lighting that can meet MEPS designed and implemented as part of the project. The strategy focuses mainly on increasing the capability of local manufacturers to expand their production lines e.g. by making them capable of developing good business transformation plans and submitting good bankable proposals to local commercial banks. Since the local manufacturers need financial resources to upgrade their production lines, the proposed project will help them to develop high quality business transformation plans. The project will further establish partnerships with the local banks to foster investment in high efficiency lighting production in Indonesia.

Regulatory mechanisms and market monitoring, verification, and enforcement (MVE): The project will capitalize on the initiatives in place and support MEMR to develop and implement minimum energy performance standards (MEPS) in coordination with the Ministry of Industry (MoI) and the national standards organization regulatory mechanisms. The ambition is to have these standards harmonized within a regional approach. The project will also support Indonesia in developing a well-functioning system of monitoring, surveillance, control, and testing facilities for effective implementation of the MEPs and improved public procurement procedures as a means to higher uptake of LED lighting. Activities under this component will closely coordinate with the ongoing efforts of RAN-GRK and RAD-GRK as far as monitoring and verification are concerned. When it comes to the enforcement of testing standards for high efficiency lighting systems, the project will work closely with the lamp manufacturing associations and respective local industries to educate them on the applicable national and regional standards to be followed in terms of quality and efficiency and enforced by the relevant government agencies and customs authorities in the numerous ports that is characteristic of the unique porous archipelagic situation of the country. This will ensure products comply with MEPS and reduce the number of non-compliant products entering the market to an absolute minimum in collaboration with Ministry of Industry and Ministry of Trade.

High efficiency lighting technology penetration:  The proposed project will study available financial mechanisms and explore for their suitability in the project. The pilot projects will concentrate on the ESCO business models (both guaranteed and shared savings model) as well as develop guidelines for public and private procurement procedures as a gateway to higher uptake of efficient lighting products (residential, commercial and outdoor) in support of the most beneficial business approaches. Since there is a large scope for reducing the energy demand for public lighting, the project will closely work with selected cities and municipalities to scale up the smart street lighting initiative. The technical and financial assistance that the project will provide to building owners and city governments in the demos will aid in their conversion to efficient street lighting. These will involve such upfront costs in formulating and initiating the EE program that usually become barriers affecting possible EE investment initiatives in view of the potential benefits that have been identified. The project will remove these barriers and pave the way to follow this developmental route for more efficient and sustainable operations. Once these developmental concerns are addressed, the EE lighting program will be put in place for MEMR to follow through and sustain through the effective implementation of the replication plan that will be initiated within the project period. The project will take a gender-responsive approach to consultations with relevant stakeholders and the public in order to consider the needs, particularly of women, related to the usage of energy efficient lighting technologies and systems. Sex-disaggregated data will be gathered whenever possible. Further, the project will develop communication campaigns, distribution campaigns, and demonstration projects to raise awareness on the benefits of high efficiency lighting taking into account gender specific aspects to increase the effectiveness of communication. The project will further implement pilot projects with the Green Cities project and the Local Government Association to introduce high efficient street lighting. Innovative financial mechanisms will be built around approaches such as ESCO models to stimulate the deployment of efficient street lighting in wider Indonesian cities. While the project will focus on commercial buildings and street lighting in most of the demonstration and replication activities, it also recognizes the big potential of the high efficiency lighting systems in the residential applications which will need different approaches for the necessary promotion and market penetration. The project will focus on developing and applying business/financing models through ESCOs that can be relevant in commercial buildings, street lighting, whereas the residential market will be addressed in the project’s demonstration, communication and marketing campaigns to bolster overall EEL market penetration.

The ADLIGHT project design strategy is based on the results of the Logical Framework Analysis (LFA) Workshop conducted by UNDP for the stakeholders from the lighting industry of Indonesia and involved key agencies in the form of stakeholder consultation using the cause-and-effect “problem tree” analysis methodology and then transformed to an “objective tree” that became the basis of the ADLIGHT Logical Framework (or Log Frame). The LFA workshop which was conducted on May 22-23, 2017 was supplemented by one-on-one focus group discussions (FGDs) conducted by the Team with the stakeholders to continue discussions and update the information to complete the ADLIGHT Log Frame and list down the project activities under each Output and Outcome.

Fig. 3 shows the project theory of change illustrating how the three strategies (three project Outcomes) lead to addressing the problems and realizing the three main Outcomes towards the achievement of the Project Objective and Goal. The Project Results Framework in Section VI presents a more complete, integrated and purpose-driven theory of change in tabular form with the success indicators, baselines, targets, means of gauging project success and assumptions.

- In line with the above interrelated strategies that will result in the desired outcomes, the various project outputs that will bring about the ADLIGHT Alternative Scenario are composed of the following:

Outcome 1: Improved quality, energy efficient and affordable locally-produced EEL products and systems.

The focus is on increasing the capability of local manufacturers to expand their production lines, with gender considerations, e.g. by making them capable of developing good business transformation plans and submitting good bankable proposals.

- Output 1.1: Establishment of knowledge center and systems that helps manufacturers in their production planning and policy makers in reviewing enabling environment

- Output 1.2: Adopted and implemented business transformation plans of selected local lighting manufacturers to produce high quality energy efficient lighting which meet future MEPS

- Output 1.3: Completed capacity development program for banking/financial institutions on the evaluation and financing of lighting industry modernization projects

Outcome 2: Improved conditions for fair market competition of EE lighting products, informed by robust policy and institutional framework

This component will address the vital need for introduction of minimum quality standards and MEPS as well as support to improve market control systems particularly in addressing the porous borders and archipelagic situation of the country by strengthening customs inspection and procurement procedures as a means to higher uptake of efficient LED lighting.

- Output 2.1: Minimum Energy Performance Standards (MEPS) and energy labels in place for high efficient energy lighting products in line with the ASEAN regional approach

- Output 2.2: Policy and guidelines for public procurement of LED lighting products (residential, commercial and outdoor) developed and processed for adaptation initiated, including environmentally safe waste disposal and recycling practices

- Output 2.3: Regulatory mechanisms for efficient lighting monitoring, verification and enforcement (MVE) including testing standards defined and process for notifying the implementation initiated by relevant agencies at the national and local levels

- Output 2.4:  Capacity development programmes for policy makers, enforcement & custom officials and other relevant government agencies on market control procedures implemented

- Output 2.5: Capacity development program for lamp testing laboratory personnel on LED testing implemented

Outcome 3: Increased penetration of high quality and efficient lighting

This component will focus on determining the most appropriate among the many available financial mechanisms referring to the various experiences abroad and existing instruments in the country. Based on the initial studies, there is a critical need to have pilot demonstrations that would concentrate on the ESCO business model and the big potential for building and street lighting application of LEDs to realize increased EEL market share.

- Output 3.1: Development of an innovative financial model enabling accelerated penetration of advanced lighting systems, focusing on the development of ESCO business models

- Output 3.2: Pilot demonstrations for accelerated LED lamp deployment in buildings and for street lighting in the context of sustainable cities as well as in residential sector

- Output 3.3: Implemented awareness and promotion program and information system explaining the benefits of high energy efficient lighting technologies, taking into account gender specific aspects in developing and implementing the programmes.

The barrier removal activities in each of the ADLIGHT project components comprise the incremental activities of the proposed project that will either be fully or partly funded by GEF resources. All these GEF-funded incremental activities will supplement the baseline activities under the EEL program of the country particularly focusing on the relevant LED manufacturing and application projects by the partners that will be subsumed under ADLIGHT. Altogether, the combined incremental and baseline activities are expected to result in the realization of the expected project outcomes.

Fig. 3: Theory of Change: Advancing Indonesia’s Lighting Market to High Efficient Technologies (ADLIGHT)

OUTCOME 1: Improved quality, energy efficient and affordable locally-produced EEL products and systems.

Table 1 presents major Activities for delivering the planned Outputs that will contribute to the achievement of Outcome 1.

Table 1: Activities that will deliver the Outputs resulting to Outcome 1

| OUTPUTS | ACTIVITIES |
| --- | --- |
| 1.1: Establishment of knowledge center and systems that helps manufacturers in their production planning and policy makers in reviewing enabling environment. | 1.1.1: Identification, design and establishment of an Institute to support energy efficient lighting transformation in Indonesia 1.1.2: Periodic (inception, mid-term and terminal) gender sensitive market surveys of EEL production and application in Indonesia 1.1.3: Development of LED lighting development roadmap for Indonesia, with gender equality goals included 1.1.4: Review and development of recommendations for government policies to provide level playing field to manufacturing of high quality LEDs |
| 1.2: Adopted and implemented business transformation plans of selected local lighting manufacturers to produce high quality energy efficient lighting which meet future MEPS | 1.2.1: Gender-responsive assessment of needs and development of capacity building to prepare local EEL manufacturers to upgrade production facilities to produce high quality, efficient lighting that can meet future MEPS 1.2.2: Development of gender-responsive business transformation plans of local EEL manufacturers to produce high quality LED lamps that can meet future MEPS requirements. 1.2.3: Organization and conduct of workshops and business forums for local manufacturers for the adoption and implementation of the business transformation plans, with gender-sensitive capacity building components. |
| 1.3: Completed capacity development program for banking/financing institutions on the evaluation and financing of lighting industry modernization projects | 1.3.1 Design, planning and conduct of training for financing institution officials on assessment of financial proposals on energy efficiency, focusing on production upgrades of lighting manufacturers, while specifically addressing gender-gaps in the market. |

The following paragraphs describe the Activities that will be conducted to deliver the expected Outputs to contribute to realization of Outcome 1.

- Output 1.1: Establishment of knowledge center and systems that help manufacturers in their production planning and policy makers in reviewing enabling environment.

Activity 1.1.1: Identification, design and establishment of an institute to support energy efficient lighting transformation in Indonesia. This will involve the establishment of an Efficient Lighting Knowledge Center for collecting market information on lighting products, quality of products, consumer perception, including gender-disaggregated consumer data where available and other related information regarding efficient lighting technology and technology providers. Existing agency with relevant mandate and organization, such as BSN, will be assisted in preparing a strategy and design to meet the requirements and purpose of the Knowledge Center and in establishing it in the selected agency that will continue to be responsible in carrying out a sustainable program ushered by the project in providing not only knowledge but also a categorized quality product listing (QPL) and database in cooperation with a network of qualified laboratories. The Knowledge Center to be established within the selected existing agency in Indonesia will complement to the virtual Centre of Excellence and other relevant mechanisms under the Parent Program, with the title: “Leapfrogging Markets to High Efficiency Products” (GEF ID: 9436) as implemented by UN Environment in coordination with the partnerships established in the Parent Program involving international organizations and private sector companies.

GEF support will be provided for the development and implementation of the Knowledge Center.

Activity 1.1.2: Periodic (inception, mid-term and terminal) gender sensitive market surveys of EEL production and application in Indonesia. This activity will involve the conduct of market surveys and analysis to ensure availability of critical market information to support the local LED lighting manufacturers’ information needs in production and application of LEDs as well as to inform the development of a LED lighting roadmap for Indonesia. The periodic market assessment and consumer surveys of EEL production and application in Indonesia includes the gathering and analysis of market data, such as gender-sensitive consumer preferences, trends in market prices and the availability of EEL products and applications including market share of both local and imported EEL lamps manufacturers. The market survey will gather information directly from consumers about their preferences, habits, their purchasing power and other important experiences especially with locally produced EEL, factoring in gender considerations, that will provide local EEL manufacturers with insight about their target customers, such as how much money they spend on certain types of products, product preferences and the interest level for new products. On the other hand, data about EEL products and market share, production facilities and desire to upgrade, or perception of future demand, or other related information will be collected through surveys among manufacturers. In the design of the surveys, the needs of the government for such information shall also be incorporated so that the results of the surveys in terms of generic data gathered will be useful for government policy formulation and decision making.

During the implementation of ADLIGHT, the market assessment and consumer surveys will periodically be undertaken on 3 stages: the first being a baseline survey and the other two are aimed at monitoring project outputs and outcomes in line with mid-term and terminal project evaluations. For the first survey, at the beginning of first year (2018), the baseline market survey aims to get the existing data of EEL production and application in Indonesia. In addition, baseline market survey consists of two activities (a) industry scanning of local lighting industries and market survey of efficient lamps in Indonesia and (b) assessment of physical production facilities and needs in producing efficient and cost-effective LED products and systems per market demand. For the second survey, the market survey will be conducted in mid-term (2020) in order to assess the achievement of the project targets after two years of implementation. For the third survey, an end-of-project market survey (2021) is aimed to evaluate overall ADLIGHT project implementation through which all the outputs and outcomes are consistently achieved towards the overall project goal and objective. The range of the surveys, the list of respondents, the data sets and other requirements to be included in the survey designs can be determined in more detail at the start of the project implementation based on the needs analysis that will be conducted at the outset.

The periodic surveys will be undertaken by ADLIGHT to fully assess the market situation of the local energy efficient lighting in selected cities in general and specifically in city governments, state-owned bank and government buildings and selected residential areas who participated as the hosts in pilot demonstrations. The surveys will involve traditional markets, outlets, minimarkets, malls, residences and the three local EEL manufacturer associations, namely GAMATRINDO, ALINDO and APERLINDO. This activity will also integrate with Activity 1.2.2 on dissemination of the benefits to shift from conventional lighting, including compact fluorescent lamps (CFLs), to LED lamps through local smart lighting corners in hyper markets. The survey results and synthesis of market situation will be provided to the EEL manufacturers to assist them in their own market assessment and production planning.

GEF support will be provided for these three market surveys and synthesis of results on high efficient lamps market in selected cities and the pilot hosts.

Activity 1.1.3: Development of LED lighting development roadmap for Indonesia, including gender equality goals. On the basis of market data collected in Activity 1.1.1, complemented with national statistical data, a modeling exercise and consultation with relevant stakeholders, an LED lighting development roadmap for Indonesia will be developed as agreed among relevant ministries and agencies. In the development of the roadmap, potential gender and environmental impacts from manufacturing, installation, maintenance, operations and disposal of LED lighting technologies and systems will be considered. The development of MEPS and energy labeling in activities under Component 2 will be aligned with the LED lighting roadmap, which will be updated along with the three phases of data collection under Activity 1.1.2.

GEF support will be provided for the LED roadmap development and consultation meetings during the development of the roadmap.

Activity 1.1.4: Review and development of recommendations for government policies to provide level playing field to manufacturing of high quality LEDs. This activity will involve policy studies and recommendations on appropriate import duties on assembled and components of LEDs, CFLs, etc., taxation of lighting manufacturing, and other related policy matters that impact the competitiveness of manufactures vis-à-vis imports.

GEF support will be provided for the conduct of policy studies and consultation meetings leading to the recommendation of policy measures to relevant government bodies.

- Output 1.2: Adopted and implemented business transformation plans of selected local lighting manufacturers to produce high quality energy efficient LED lamps that can meet future MEPS

Activity 1.2.1: Gender-responsive assessment of needs and development and implementation of capacity building to prepare local EEL manufacturers to upgrade production facilities to produce high quality, efficient lighting that can meet future MEPS. This activity will focus on increasing the capability of local manufacturers to expand their production lines by making them capable of developing good business transformation plans and submitting good bankable proposals. This activity will involve evaluation of the existing EEL production facilities of local manufacturers in order to upgrade their manufacturing facilities, production techniques and the capacity of human resources to handle the high technology equipment to produce affordable, high quality EEL products. This assessment consists of a series of activities such as (a) assessment of human resources capability to handle high technology equipment, including assessment of women’s and men’s needs and capabilities for safe and gender equal workplaces; (b) organization and conduct of a workshop for a broad range of local manufacturers on the potential of EEL and upgrading production facilities, ensuring that women staff active participation is encouraged and promoted; (c) assessment of production techniques of the selected local EEL manufacturers to design and produce high EEL systems including LED and (d) assessment of quality assurance needs and how to provide needed technical assistance in local EEL production.

This activity will involve in the needs assessment process, the participation of selected EEL local manufacturers (under three above-mentioned LED industry associations), DGNREEC – MEMR, National Standardization Agency of Indonesia (BSN), Ministry of Trade Ministry of Industry and other relevant agencies, including gender equality-focused institutions. Based on the needs analysis conducted, manufacturers will (a) undergo a series of three progressive trainings on the potential and benefits of EEL and possibilities for upgrading the production facilities in their factories, (b) provide and share utilization of common service utilities, such as die cast moulding for LED street light housing, and (c) receive technical assistance on LED global standard adoption in line with ASEAN approach to local EEL industry.

GEF supports the travel expenses for the field trips, selected local EEL manufacturers, workshops/FGDs and needs assessment, capacity building to handle the high technology equipment, series of three trainings to disseminate the potential and benefits of energy efficient lighting production to all local manufacturers and other related activities.

Activity 1.2.2: Development of gender-responsive business transformation plans of local EEL manufacturers to convert their production lines to the production of high quality LED lamps that can meet future MEPS requirements. This activity is designed to develop business transformation plans of local EEL manufacturers to convert their production lines to the production of high quality, energy efficient LED lamps. This includes the preparation of feasibility studies (FS) on LED business transformation plans at the individual company level as well as the industry integration at the program level. These preparatory works for the gender-responsive transformation plans will be done by the experts to be hired by the project together with an active participation of and consultation with both female and male staff of the local EEL manufactories. As part of the expert study, a selective technical field visit can be organized (benchmarking) in EEL industry abroad, particularly on how the manufacturers have coped with global standards (MEPS) adoption. At the individual company level, the project will provide technical assistance by hand holding the local manufacturers in developing business transformation plans that will be of sufficient high quality so that financial institutions will be able to assess related loan requests in accordance with agreed bank standards and development needs. A training/workshop is to be developed and conducted by the project experts with the required modules on how to develop business plans and what (financial) information to include in a loan request and other pertinent information. Local manufacturers female staff participation in the training/workshop will be particularly encouraged. As the local manufacturers learn individually from this activity and establish their confidence on the transformation program, the confidentiality of business plans will be followed as this issue surfaced as a major hesitancy by the manufacturers. At the industry level, the overall program sustainability will be tackled. At the aggregated level, the consultant will provide guidance and technical assistance in developing an EEL business transformation program and sustainability plan for use by the MEMR in cooperation with other relevant ministries at the national level.

This activity involves selected EEL local manufacturers (under the three above-mentioned LED industry associations), DGNREEC – MEMR, state-owned banks, OJK, BSN with the assistance of a national consultant hired by the ADLIGHT project. This activity will integrate activities in Output 2.1 on MEPS test methods and energy labels that will be adhered to in the transformation of the facilities.

GEF supports the preparation of feasibility studies and a training/ workshop, follow-up FGDs in the development and related technical studies to support EEL transformation plans.

Activity 1.2.3: Organization and conduct of workshops and business forums for local manufacturers for the development of bankable investment proposals of the business transformation plans, with gender-sensitive capacity building components. This activity, as a follow-up of the approved business transformation plan, is intended to organize and conduct a series of three progressive workshops targeted for local manufacturers to prepare bankable investment proposals (including gender responsive budgeting) within the framework developed in Activity 1.2.2. This is in line with the Indonesian context of selected local EEL manufacturers to convert production lines to the production of more LED lamps.

This activity involves selected EEL local manufacturers (under the three above-mentioned LED industry associations), the DGNREEC – MEMR, state-owned banks, OJK, BSN with assistance of a national consultant hired by ADLIGHT project. This activity will integrate activities in Output 2.1 regarding the necessary support for the adoption of MEPS, test methods and energy labels for EELs in line with the ASEAN regional approach.

GEF supports a series of three progressive workshops for local manufacturers across the country to prepare efficient and cost-effective EEL designs, business transformation plan and bankable investment proposals.

- Output 1.3: Completed capacity development program for banking/financing institutions on the evaluation and financing of lighting industry modernization projects.

Activity 1.3.1 Design, planning and conduct of training for financing institution officials on assessment of financial proposals on energy efficiency, focusing on production upgrades of lighting manufacturers, while specifically addressing gender-gaps in the market. This activity will design, plan and conduct training for women and men financing institution officials on assessment of financial proposals on energy efficiency, focusing on production upgrades of lighting manufacturers. The activity will involve the provision of a feasibility template that will be developed by the project on the evaluation and financing of selected local EEL manufacturers’ modernization projects, while addressing barriers to gender equality. In addition, this activity will conduct dissemination trainings for financial institutions (credit officers and risk managers) on assessment and evaluation of business transformation plans and bankable investment proposals focusing on production upgrades of EEL manufacturers /modernization projects. This will also involve dissemination trainings for the eight participant banks of Indonesia First Movers on Sustainable Banking and related Regional Development Banks or Bank Pembangunan Daerah (BPD) of Smart Cities Street Lighting pilots. Women staff participation in the trainings will be particularly encouraged. The Indonesia Finance Service Authority (OJK) will be in the best position to understand and lead the affiliated banks into fully supporting the realization of the LED industry business transformation plan and necessary elements for it to be successfully and timely implemented. The project will in turn provide the necessary technical assistance to develop its capacity, guidance and tools to equip the banks to effectively receive, evaluate and approve loan applications from interested LED manufacturers.

This activity involves, DGNREEC – MEMR, the eight participant banks of Indonesia First Movers on Sustainable Banking and related Regional Development Banks (BPD) of Smart Cities Street Lighting pilots, OJK (Financial Services Authority), National Standardization Agency of Indonesia (BSN) and a national consultant hired by ADLIGHT project. This activity will integrate with activities in Output 1.2, and Output 3.1.

GEF supports Design, planning and conduct of training for financing institution officials and related activities.

OUTCOME 2: Improved conditions for fair market competition of EE lighting products, informed by robust policy and institutional framework

Table 2 presents major Activities for delivering the planned Outputs that will contribute to the achievement of Outcome 2.

Table 2: Activities that will deliver the Outputs resulting to Outcome 2

| OUTPUTS | ACTIVITIES |
| --- | --- |
| 2.1. Minimum Energy Performance Standards (MEPS) and energy labels in place for high energy efficient lighting products in line with the ASEAN regional approach | 2.1.1. Development and implementation of SNI for standard minimum quality for indoor and outdoor LED lamps with BSN |
|  | 2.1.2. Development of MEPS for indoor and outdoor LED lighting with MEMR by aligning and adopting the available standards in Indonesia and international standards. |
|  | 2.1.3. Development and initiation of process for endorsement of LED energy labeling procedure in line with the ASEAN approach by MEMR |
| 2.2: Policy and guideline for public procurement of LED lighting products (residential, commercial and outdoor) developed and process for adaptation initiated, including environmentally safe waste disposal and recycling practices | 2.2.1. Development and initiation of process for endorsement of a government policy, implementing rules and action plan to include adoption of the weight benefit (BMP) mechanism for the LED lighting products in support to government promotion of local EEL products in the market |
|  | 2.2.2. Development and initiation of process for endorsement of a procurement guideline by adopting MEPS and/or standard minimum quality for locally manufactured indoor and outdoor LED lamps and systems including environmentally safe disposal/recycling of lighting products |
|  | 2.2.3 Development and initiation of process for endorsement of a strategy and guidelines for the environmental safe collection, recycling and/or disposal of lighting products and systems |
| 2.3: Regulatory mechanisms for efficient lighting monitoring, verification and enforcement (MVE) including testing standard defined and implemented by relevant agencies at the national and local levels | 2.3.1 Reviewing, assisting and deployment of a software application with BSN to trace SNI, MEPS, and Labels certified LED Lamps including the upgrading of existing hardware and software to support LED lighting MVE. |
|  | 2.3.2. Reviewing and upgrading public procurement monitoring report of LED light procurement from the e-catalogue procurement and non e-catalogue procurement. |
|  | 2.3.3. Re-evaluation of existing certified LED lamp testing laboratory for indoor and outdoor by KAN/BSN on performing the existing SNI-IEC standard. |
| 2.4: Completed capacity development for policy makers, enforcement & custom officials and other relevant government agencies on market control procedures | 2.4.1. Development and initiation of process for endorsement of the institutional framework necessary to define roles and responsibilities among relevant agencies to strengthen program implementation and market transformation to EEL products and systems |
|  | 2.4.2. Design, planning and conduct of training for stakeholders involved in importing LED components and lamps (especially local manufacturers and supply chain importers) on custom and excise procedures |
|  | 2.4.3. Design, planning and conduct of training for LED lighting manufacturers in Indonesia on local content calculation by Ministry of Industry and its authorized certifier |
|  | 2.4.4. Design, planning and conduct of training on market control procedures, development and implementation on certified LED lamps and systems for manufacturers and government stakeholders. |
|  | 2.4.5. Design, planning and conduct of training on waste management and environmentally safe waste disposal and recycling of lighting products |
| 2.5: Completed capacity development program for lamp testing laboratory personnel on LED testings | 2.5.1. Design, planning and conduct of training on the implementation of the upgraded EEL laboratory and testing procedures. |
|  | 2.5.2: Benchmarking and round-robin testing for LED products and systems with local and international LED laboratories |
|  | 2.5.3. Design, planning and conduct of training for manufacturers to understand and implement the LED standard requirement for research, production, and quality assurance on the LED products. |

The following describes the Activities that will be conducted to deliver the expected Outputs that contribute to realization of Outcome 2.

- Output 2.1: Minimum Energy Performance Standards (MEPS) and energy labels in place for high efficient energy lighting products in line with the ASEAN regional approach

Activity 2.1.1: Development and implementation of SNI for standard minimum quality for indoor and outdoor LED lamps with BSN. Considering that MEPS adoption could take a long period, an equivalent Indonesian National Standard (SNI) could be adopted first by the National Standard Agency (BSN) in line with national and international commitments of Indonesia. In order to have applicable MEPS, the Indonesia Government must be aware of the entire set of needed LED lighting standards and adopt them initially to SNI standard. As informed by BSN, currently there are 33 IEC (International Electrotechnical Commission) standards on Lighting/Luminaire and Indonesia has already adopted 18 of the prescribed standards. With the assistance from ADLIGHT, BSN will adopt the necessary IEC standards needed to subsequently draft the standard minimum quality and MEPS by initially adopting them first as SNI. In doing so, the SNI provisional standards can already be used for government procurement guidelines while the MEPS adoption is still in progress.

In addition to the adoption of the needed standards, BSN, MEMR, and other related agencies involved would align the country’s lighting/luminaire standards with the ASEAN regional approach. Indonesia is committed to abide to the ASEAN Plan of Action Energy Cooperation 2016-2025 (APAEC), which highlights regional harmonization of LED lighting standards (Activity 4.1 of the APAEC). Standards such as CIE S025 and other standards agreed in APAEC will be accommodated in their adoption to SNI.

The development of the necessary IEC standards and other standards to applicable SNIs will be supported by consultant experts as well as by international expertise from the Global Leapfrogging Programme. On the basis of a needs assessment at the early start of the project, specified expertise demand will be identified and supported by the project. The overall direction for the standards development for EEL is harmonizing Indonesia testing standard with international standards according to BSN’s standards development plan.

GEF will support all the activities involved in adopting the international standards, the operation of the TWG on MEPS/SNI for lighting/luminaire to SNI, hiring international and national consultants to assist in aligning the standards with ASEAN approach.

Activity 2.1.2: Development of MEPS for indoor and outdoor LED lighting with MEMR by aligning and adopting the available standards in Indonesia and international standards. This activity is in line with LED standards development process initiated in parallel with Activity 2.1.1 but will be started already in the 3rd or 4rd quarter of Year 1 of the project and will continue until the draft is ready to be endorsed as a regulation. The development of MEPS for LED lighting will follow the EEL MEPS/SNI roadmap as agreed among relevant ministries and agencies in Activity 1.1.3.

The development of MEPS is part of MEMR long term strategic planning (RENSTRA 2015-2019) and MEMR has issued MEPS for CFLs and energy label for CFL bulbs. Therefore, the work has already been initiated by MEMR in a similar process. However, in order for the MEPS for LED lighting to be implemented successfully, MEMR will be closely coordinating with BSN so that the application of the MEPS available in Indonesia can be tested and certified by Indonesian laboratories. Therefore, it is crucial that Activity in 2.1.1 be completed in the Year 1 so that the MEPS formulation can easily include the right standards to be facilitated by the coordination mechanism to be implemented through the TWG organized in Activity 2.1.1. Thus, the MEPS development will already be aligned with BSN SNI standards, international standard and ASEAN regional approach in the context of what the Indonesia LED industry and the market need. Since MEPS is a commitment of Indonesia Government to APAEC, MEMR has committed to the ADLIGHT project to have the draft of MEPS available and ready to be endorsed as regulation the latest by end of 2019. By end of Year 1 (2019) of the ADLIGHT project, an initial draft MEPS proposed by the TWG should be available. This activity is linked to Outputs 1.1, 1.2, and 3.2.

The development of the MEPS for indoor and outdoor LED lighting will be supported by consultant experts as well as by international expertise from the Global Leapfrogging Programme. It will specifically look at the implications of safety of women in public spaces, in consultations with relevant stakeholders and members of the public.  On the basis of a needs assessment at the early start of the project, specified expertise demand will be identified and supported by the project.

GEF will support the preparation of the framework and actual documents of MEPS and aligning the needs of MEPS standards with the available SNI standards, the activities and operation of the TWG, hiring of international and national consultants and other related activities for endorsement and participation in regulatory procedures.

Activity 2.1.3: Development and initiation of process for endorsement of LED energy labeling procedure in line with the ASEAN approach by MEMR. This activity will involve the formulation of labeling procedures and designs to be initiated in the 1st quarter of the Year 2. The development of energy labeling for LED lighting will follow the EEL MEPS/SNI roadmap as agreed among relevant ministries and relevant agencies to be facilitated by the TWG on MEPS/SNI as started in Activity 1.1.2. This activity will build upon the work on labeling of CFL bulbs along with some household appliances since similar work has been done and implemented by the Government of Indonesia through the BRESL project. ADLIGHT will assist MEMR in drafting and endorsing the LED energy label. The actual approval of the recommendations may only happen after the MEPS adoption or after the three-year duration of the project, therefore the effectiveness of the labeling program may only be evaluated after the ADLIGHT project. The energy labeling will be developed separately although in line with MEPS development. The TWG on MEPS/SNI will continue to facilitate this process until the draft LED labeling procedures and labeling designs are endorsed by authorized ministries/agencies. This activity is linked to Outputs 1.1, 1.2, and 3.2.

The development of the LED energy label will be supported by consultant experts as well as by international expertise from the Global Leapfrogging Programme. Preliminary LED energy label design will be suggested and proposed to the TWG on MEPS/SNI. Two consultation workshops will be organized to start building support for the LED energy label among Indonesian LED manufacturers. A final consultation workshop targeting Indonesian LED manufacturers as well as relevant government entities will be set up to come to full endorsement of the LED energy label.

GEF will support the activity in Year 2 for the TWG activities, drafting and endorsing the draft documents on labeling procedures and designs, hiring of national consultant, several workshops and communication activities.

- Output 2.2: Policy and guideline for public procurement of LED lighting products (residential, commercial and outdoor) developed and process for adaptation initiated, including environmentally safe waste disposal and recycling practices

Activity 2.2.1: Development and initiation of process for endorsement of a government policy, implementing rules and action plan to include adoption of the weight benefit (BMP) mechanism for the LED lighting products in support to government promotion of local EEL products in the market. This activity, to be initiated starting in Year 1, will involve provision of assistance in the development and endorsement of a government policy, implementing rules and action plan that will work on adopting a policy towards a minimum percentage share of local EEL products in the market as procured by government entities to support the progressive growth in manufacturing and application of high efficiency lighting technologies. The proposed policy will be an act of goodwill and leading by example from the government to support LED manufacturers in Indonesia. The policy will regulate government procurement in that the government will procure a certain percentage of LED lighting from manufacturers in Indonesia.

This activity will also involve the project’s assistance in reviewing and submitting recommendations on the existing local content policy to adopt the weight benefit (BMP) mechanism applicable for the LED lighting Industry. During the project preparation, in consultation with the Ministry of Industry and other relevant stakeholders, it was observed that the current MVE practice on determining local content of local products needs improvement on accuracy and transparency aspects. There are very significant discrepancies in the local content certification among lighting manufacturers in Indonesia, leading to varied questions on the validity and integrity of the certification being issued. The manufacturers also feel that the current local content policy poses certain disadvantages. There is a need to provide assistance in reviewing and making recommendations to transition from present local content determination practice to weighted-benefit modality for the local LED manufacturers. The weight-based approach will stimulate the local manufactures to invest and upgrade their manufacturing plants.

With the proposed activity, the assured LED demand level can stimulate the LED manufacturers in Indonesia to increase their production, produce a higher quality LED and put up new investments to upgrade or produce certain product components locally. This activity is linked to Outputs 1.1, 1.2, 2.3 and 3.2 and will be implemented in cooperation with the Ministry of Industry and other relevant ministries.

The development of a government procurement policy towards adopting more local EEL products in public procurement will be supported by consultant experts as well as by international expertise from the Global Leapfrogging Programme. Preliminary policy design will be suggested and proposed to the relevant government entities. Three (3) regional workshops will be organized to disseminate the policy to government entities who are expected to act upon the new procurement policy.

GEF will provide support to the activity in Year 1 in terms of preparation and endorsement of the draft procurement policy, including reviewing and recommending adoption of the weight benefit (BMP) mechanism for the LED lighting Industry in existing local content policy and related activities to, hiring of a national consultant and conduct of related workshops and dissemination activities, the hiring of a national consultant and conduct of at least three (3) related regional workshops and other related activities.

Activity 2.2.2: Development and initiation of process for endorsement of a procurement guideline by adopting MEPS and/or minimum quality standard for locally manufactured indoor and outdoor LED lamps and systems including environmentally safe disposal/recycling of lighting products. This activity, to be initiated within the second half of Year 1, will involve assistance to MEMR and relevant government agencies in charge of procurements in the development and endorsement of a procurement guideline by adopting MEPS and/or minimum quality standard for locally manufactured indoor and outdoor LED lamps and systems. The procurement guideline can include an environmental requirement. Because of the environmental implications of the potentially hazardous chemicals and used materials from the bulb replacements, the procurement policy will include measures in waste disposal/recycling of replaced lamps.

The procurement policy is aimed at enhancing existing policy and regulations with additional guidelines and assistance to the central government and municipalities in procuring LED lighting for their indoor and outdoor usage. The project will develop and endorse updating of the existing procurement guidelines to reflect the general approach of life-cycle-cost (instead of the current practice of merely procuring based on least capital costs). Currently in Indonesia, there is no guideline for the procurement of LED lighting. From the project preparation meetings and workshops, the central government, municipalities, and manufacturers expressed the need for the government to develop a standard procurement policy so that all lighting manufacturers will have the same chance in participating in government procurement. The lighting standards to be referred by the procurement guideline will be the adopted standard minimum quality contained in the relevant SNI issued by BSN in Activity 2.1.1 while the MEPS is still being developed. The procurement guideline will be updated as soon as the adopted MEPS are available. This proposed arrangement whereby the procurement guideline will initially be using the BSN SNI, will provide clarity in the standard lighting standards, facilitate the procurement process and provide firm basis for the MVE on government procurement. This activity is linked to activities in Outputs 1.1, 1.2, and 3.2.

The development of a government procurement guideline to incorporate MEPs and life-cycle costing concepts will be supported by consultant experts as well as by international expertise from the Global Leapfrogging Programme. Preliminary guideline design will be suggested and proposed to the relevant government entities. At least three (3) regional workshops will be organized to disseminate the policy to government entities who are expected to act upon the new procurement policy.

An important element of the activity is developing an environmental safe disposal/reuse policy document for the country. The policy document will define the roles and mandates to implement the policy and legal framework, including model regulations; processes and requirements of safe transportation, storage and recycling; and (4) options for financing the environmental safe disposal of lighting products.

GEF will provide support for the development and endorsement of the procurement guideline, adoption of the regulation, hiring of a national consultant, several workshops, and other related activities.

Activity 2.2.3: Development and initiation of the process for endorsement of a strategy and guidelines for the environmental safe collection, recycling and/or disposal of lighting products and systems. This activity, to be initiated during Year 2, will involve assistance to MEMR and relevant government in the development and endorsement of a strategy and guidelines to ensure environmentally sound management (i.e. collection, recycling, disposal of lamps, mercury recovery in CFLS, etc.) of lightings products and systems.

GEF will provide support for the development and endorsement of the strategy and guidelines through the hiring of an International Environmental Specialist.

- Output 2.3:  Regulatory mechanism for efficient lighting monitoring, verification and enforcement (MVE) including testing standards defined and process for notifying the implementation initiated by relevant agencies at the national and local levels

Activity 2.3.1: Reviewing, assisting and deployment of a software application with BSN to trace SNI, MEPS, and Labels certified LED Lamps including the upgrading of existing hardware and software to support LED lighting MVE. This activity will provide assistance to BSN (Badan Standardisasi National or the National Standardization Agency) in designing and operationalizing an inspection software that will enable to trace and detect compliance of all the products bearing the SNI product seals. The software is expected to be using a scanner to scan the QR code (type of matrix barcode or two-dimensional barcode) of the SNI label on the products. On the basis of the scanning, the software can provide information such as product technical data and certification data so that authorities will know in a faster and more accurate manner if the products match the particular SNI label. With the SNI, and later the MEPS enforced as regulation, authorities and consumers have the capability to check the product quality instantly. The ADLIGHT project will assist in the software development and in the acquisition of model digital-based inspection hardware that can be replicated by the government subsequently. This activity is linked to pertinent activities under Outputs 1.1, and 1.2.

The development of the product quality checking software and inspection hardware will be supported by consultant experts as well as by international expertise from the Global Leapfrogging Programme. Preliminary software design will be suggested and proposed to the relevant government entities. At least three (3) regional consultation workshops will be organized in Indonesia to disseminate the use of the software to relevant government entities who are involved in product quality checking.

GEF will provide support in reviewing, assisting and deployment of a selected software application with BSN, upgrading of existing hardware and software to support usage and implementation in Year 2, the upgrading of the software to adapt to the SNI standard minimum quality and the MEPS expected to be issued during Year 3, hiring of an international and national consultants, conduct of at least three (3) regional workshops, and knowledge dissemination activities.

Activity 2.3.2: Reviewing and upgrading public procurement monitoring report of LED light procurement from the e-Catalogue procurement and non e-Catalogue procurement. This activity will involve providing assistance in reviewing and upgrading the public procurement monitoring and reporting system regarding LED lighting product procurement from the e-Catalogue and non E-Catalogue procurements. The project will support the enhancement of monitoring the LED lighting product procurements. This activity will facilitate a valid monitoring resource, for instance, for manufacturers to effectively plan their annual production and for banks to have valid data to measure the purchasing capabilities in determining size of loan windows. It will also contribute to necessary data on the quantities of LED lighting procured outside the e-Catalogue system (regular tender), and for decision and policy making as well as tracking the energy savings and emission reduction at national and regional level. This activity is linked to activities under Outputs 1.1, 1.2 and 2.2 and will be implemented with the Public Procurement Agency –LKPP which is responsible for the development and adoption of government procurement policies.

The review and upgrading of the public procurement LED monitoring report will be supported by consultant experts as well as by international expertise from the Global Leapfrogging Programme. Preliminary report design will be suggested and proposed to the relevant government entities. At least three (3) regional consultation workshops will be organized to disseminate the adjusted public procurement LED monitoring report to relevant government entities.

GEF will provide support in reviewing and upgrading public procurement monitoring report of LED light procurement from the E-catalogue procurement and non E-catalogue procurement, hiring a national consultant, conduct of workshops, and the upgrading of the necessary hardware/software of the monitoring system.

Activity 2.3.3: Re-evaluation of existing certified LED lamp testing laboratory for indoor and outdoor by KAN/BSN on performing the existing SNI-IEC standard. This activity will provide assistance in re-evaluation of existing certified LED lamp testing laboratories for indoor and outdoor by KAN/BSN on compliance with the existing SNI-IEC standards. The project will also support the upgrading of one testing laboratory to enable it to conduct the testing procedures on all parameters of LED lighting and luminaire in line with the project’s aim to have an effective MVE on LED lighting. The results of the evaluation will guide KAN/BSN in validating claims by LED light testing laboratories and in certifying them vis-a-vis the established LED laboratory standards. While evaluating the existing laboratories, the project will also analyze and evaluate the necessary upgrades that the laboratories need to conduct full testing of LED lighting products and luminaires. This activity is linked with Output 2.5 where the recommendations on the laboratory upgrading will be implemented.

The re-evaluation and assessment of laboratory upgrading will be supported by consultant experts as well as by international expertise from the Global Leapfrogging Programme. Preliminary proposals for upgrading of laboratory equipment and analytical systems and the related manpower training will be suggested and proposed to the relevant government entities. At least one (1) consultation workshop will be organized to disseminate the findings and the proposed plans to upgrade the LED lamp laboratories to relevant government entities to qualify for accepted international standards.

GEF will provide KAN/BSN support to the re-evaluation of existing LED lamp testing laboratories for indoor and outdoor application for compliance with the existing SNI-IEC standards, operational quality assurance and annual evaluation, hiring a national consultant, conduct of workshops, and making the recommendations  for upgrading the hardware and software of the laboratory system.

- Output 2.4: Completed capacity development for policy makers, enforcement & custom officials and other relevant government agencies on market control procedures

Activity 2.4.1: Development and initiation of process for endorsement of the institutional framework necessary to define roles and responsibilities among relevant agencies to strengthen program implementation and market transformation to EEL products and systems. This activity will provide assistance in conducting an organization development study. The project will support developing and endorsing a proposed institutional framework necessary to define roles and responsibilities among relevant agencies to strengthen existing institutional structure, program implementation and market transformation to EEL products and systems. Special consideration will be given to finding ways to enhance the role of women staff among relevant agencies. Because of the policy and institutional aspects, the activity will involve development and implementation of a coordination mechanism that could be initially exercised through the ADLIGHT Project National Steering Committee (NSC). The NSC can create a Technical Working Group (TWG) on Policy and Institutional Support which will perform the necessary studies and make recommendations through the PMU. In addition, the activity will also see to it that all activities and outputs are getting the critical support from all relevant agencies and that they provide expected inputs and co-financing for the project.

The review and action planning regarding the institutional structure and organizational coordination mechanisms will be supported by consultant experts as well as by international expertise from the Global Leapfrogging Programme. Preliminary recommendations will be suggested and proposed to the relevant government entities. At least one consultation workshop will be organized to disseminate the results of the studies done and proposed action plan, including capacity building program to relevant government entities.

GEF will provide support in terms of needed technical consultancy assistance, conduct of related organizational development workshops and other relevant activities.

Activity 2.4.2: Design, planning and conduct of training for stakeholders involved in importing LED components and lamps (especially local manufacturers and supply chain importers) on custom and excise procedures. This activity will involve assistance in designing, planning and conducting of training for stakeholders involved in importing LED lighting product components and lamps (especially local manufacturers and supply chain importers) on custom and excise procedures by the Directorate General of Customs and Excise (Direktorat Jenderal Bea dan Cukai). During the project preparation stage, it was gathered that manufacturers are importing raw material or product components needed for the LED lamp production by using the wrong importation method, procedure and Harmonized Commodity Description and Coding System (HS Code). This causes delay in production and increases the cost of the imported product components. The irregular practices lead to disputes on the understanding of certain HS code by the manufacturers and importers due to the lack of proper knowledge or resources.

The project will organize at least three (3) regional workshops in the West, Middle and Eastern regions of Indonesia supported by consultant experts as well as by international expertise from the Global Leapfrogging Programme. The target audience of the workshops will consist of women and men staff from relevant government agencies on policy, regulation and implementation of customs and excise procedures with active participation of the local manufacturers and supply chain importers. The workshops will be organized in the West, Middle and Eastern regions of Indonesia.

GEF will provide support a continuing training program, during the three years, conduct of workshops, in three different regions of Indonesia (West, Middle, and East) that have international ports and traffic on LED lighting components, invitation of World Custom Organization (WCO) experts, hiring of a national consultant, and providing a practical handbook for manufacturers, supply chain importers, and relevant agencies on doing proper import for LED lighting components.

Activity 2.4.3: Design, planning and conduct of training for LED lighting manufacturers in Indonesia on local content calculation by Ministry of Industry and its authorized certifier. This activity will involve assistance to local LED manufacturers by conducting a workshop to align their perception and how to maximize the local content value of their products. The workshop will provide manufacturers with essential information for decision making on the best approach to increase the quality and the increase the production of LED lighting with proper assessment of their products’ local content as well as gain maximum local content values from the calculations.

The project will develop and publish a handbook on local content of LED products as well as organize at least three (3) workshops on local content value supported by consultant experts as well as by international expertise from the Global Leapfrogging Programme. The target audience of the workshops will consist of LED manufacturers with active participation of Ministry of Industry and authorized certifiers. The workshops will be organized in the West, Middle and Eastern regions of Indonesia.

GEF will provide support in the design, planning and conduct of training in three different of regions of Indonesia (West, Middle, and East) that have lighting manufacturers, conduct of workshops and the publication of a pocket handbook on local content of LED products.

Activity 2.4.4: Design, planning and conduct of training on market control procedures, development and implementation on certified LED lamps and systems for manufacturers and government stakeholders. This activity will involve the design, planning and conduct of training on market control procedures, development and implementation on certified LED lamps and systems for women and men staff of local manufacturers and governmental institutions according to its main task and functions related to market control using the existing system and the newly developed software. Based on the project preparation observations, each government stakeholder and other relevant agencies have their own mechanism on market control procedures. However, these mechanisms are not known by other stakeholder/agencies. Each agency is operating independently and there is a lack of communication among them. The project will facilitate and align or harmonize the existing mechanisms in a workshop that will provide means by which each agency can share their mechanism to other agencies that have authority in market control. In line with Activity 2.3.1, the project will also facilitate training on the new software developed by BSN and other new software being used by other agencies.

GEF will provide support the design, planning and conduct of training on market control procedures, development and implementation on certified LED lamps and systems for manufactures and government stakeholders according to its main task and functions related to market control using the existing system. The training will cover newly developed software in three different regions of Indonesia (West, Middle, and East).

Activity 2.4.5: Design, planning and conduct of training on waste management and environmentally safe waste disposal/recycling of lighting products. At the moment, not all parties working on lighting retrofitting from conventional lamps to energy efficient lighting are aware of how to handle the waste and what the potential impacts of hazardous waste are if not handled properly. The project will therefore design, plan and conduct a training course on potential impacts of waste on men, women and children, and appropriate waste management and recycling techniques of components and materials of lighting replaced by LED each in the West, Middle and Eastern regions of Indonesia. The training materials and coverage will be based on the pertinent policies and implementing guidelines issued in connection with the procurement policy on waste materials of lighting products and systems under Activity 2.2.2.

GEF will support the design, planning and conduct of training on waste management and recycling of components and materials of lighting replaced by LED and develop the training program and training materials as well as the production of a pocket handbook on waste management and recycling of replaced lamps.

- Output 2.5: Completed capacity development program for lamp testing laboratory personnel on LED testing

Activity 2.5.1: Design, planning and conduct of training on the implementation of the upgraded EEL laboratory and testing procedures. This activity will cover the design, planning and conduct of training on the implementation of the upgraded EEL laboratory and testing procedures. The following are several activities that will be conducted: (a) Assessment of needs for existing laboratories on LED testing capabilities in equipment and manpower in line with Activity 2.3.4; (b) Design and establishment of an internationally accredited and equipped LED testing laboratory to support compliance to international LED laboratory testing protocols and standards and EE labeling procedures and in line with SNI and MEPS of Indonesia and cross referenced with ASEAN practice;  (c) Conduct of a training of trainers workshop for designated personnel, BSN, and selected private laboratory personnel for LED products in line with national (SNI, MEPS) and international accreditation and harmonization of standards (IEC, CIE S025), a pilot training for laboratory personnel and assistance in the certification of selected government laboratory personnel; and (d) Explore partnership opportunities between laboratories domestically and abroad. In adopting the MEPS and standard minimum quality, all laboratories in Indonesia will need to upgrade their facilities; however some of the laboratories may not have the financial capabilities to do so. In this activity, ADLIGHT will explore partnership of the laboratories in Indonesia with international laboratories such as NTLC, TUV, or Intertek as an option to upgrade the Indonesia laboratories with support from the Global Leapfrogging Programme.

GEF will provide support for design, planning and conduct of training for the implementation of the upgrading EEL laboratory and testing procedures, hiring international consultant for Activity 2.5.1 (a), hiring of national consultant for related Activity 2.5.1 (a & b), hiring of an international training and certification company for activity in 2.5.1.(c), and workshop for all of the activities .

Activity 2.5.2: Benchmarking and round-robin testing for LED products and systems with local and international LED laboratories.  This activity will involve comparing and calibrating Indonesian LED laboratories using standard testing protocols vis-à-vis the MEPS/SNI adopted. It will provide information on the accuracy of the testing in Indonesia and will also compare Indonesian laboratories with standard and accredited international laboratories. If there are discrepancies found, then these will be addressed in Activity 2.5.1.

GEF will provide support for costs of sampling and logistics to do the benchmarking and round-robin testing for the LED products and systems with local and international LED laboratories, incidental costs of travel for selected LED laboratory managers and other related costs.

Activity 2.5.3: Design, planning and conduct of training for manufacturers to understand and implement the LED standard requirements for research, production, and quality assurance of the LED products. This activity will provide assistance for enabling and building capacity of the manufacturers to adopt the LED standard requirements in all aspects of their manufacturing operations in producing energy efficient and cost-effective LED products. This will involve conduct of a training workshop in each of the Western, Middle and Eastern regions of Indonesia. The activity aims to increase the knowledge of the manufacturers in producing good quality and highly efficient LED lighting products and systems following MEPS and SNI standard minimum quality in line with the ASEAN regional approach and agreed testing protocols. The project will evaluate the effectiveness of the training courses to improve the enabling and capacity building activities for manufacturers and formulate a sustainability plan to continue the training program beyond the timeline of the project with support from the stakeholders and the manufacturers.

GEF will provide support for the design, planning and conduct of training, workshops and related knowledge management activities, preparation of training manuals and post-training evaluation and preparation of the training sustainability plan.

OUTCOME 3: Increased penetration of high quality and efficient lighting

Table 3 presents major Activities for delivering the planned Outputs that will contribute to the achievement of Outcome 3.

Table 3: Activities that will deliver the Outputs resulting to Outcome 3

| OUTPUTS | ACTIVITIES |
| --- | --- |
| 3.1: Development of an innovative financial model enabling accelerated penetration of advanced lighting systems, focusing on the development of ESCO business models | 3.1.1: Comparative evaluation of international best practices of financial support schemes for EEL financing |
|  | 3.1.2: Development of ESCO business models to be demonstrated in the pilot projects |
|  | 3.1.3: Mainstreaming of the existing national policies and regulations for the banking sector to accelerate penetration of EEL |
| 3.2: Pilot demonstrations for accelerated LED lamp deployment in buildings and for street lighting in context of sustainable cities as well as in residential sector | 3.2.1: Design, approval, capacity development and implementation of pilot demonstrations using ESCO business model |
|  | 3.2.2: Design, planning and conduct of training for local government municipalities and cities and pilot demonstration hosts |
| 3.3: Implemented awareness and promotion program and information system explaining the benefits of high energy efficient lighting technologies, taking into account gender specific aspects in developing and implementing the programmes | 3.3.1: Development of a gender-responsive EEL awareness and promotional program on the benefits of good quality LED lighting |
|  | 3.3.2: Development and implementation of information support network system, database and website on EEL product distribution, sales and performance in the market for various consumer groups |

The following describes the Activities that will be conducted to deliver the expected Outputs to contribute to realization of Outcome 3.

- Output 3.1: Development of an innovative financial model enabling accelerated penetration of advanced lighting systems, focusing on the development of ESCO business models

Activity 3.1.1: Comparative evaluation of international best practices of financial support schemes for EEL financing. This activity will involve a study on the local and international experiences and best practices on finance for EE lighting application in various sectors. The study will focus on evaluating various available schemes being practiced in many countries. In Indonesia, there are existing instruments or schemes that could be applicable to LED lighting projects as they are already being applied to Indonesia’s other infrastructure projects such as: (a) Public Private Partnership (PPP) mechanism for EE lighting, (b) Bankable Investment Proposal for ESCO financing, (c) Credit Guarantee Facility for EEL/LED investment projects, (d) means of bundling LED lighting products/ small transactions to enable them as accepted collaterals for banks.

This activity will involve the participation of DGNREEC-MEMR, PT SMI, PPP-task force (KPBU Terpadu BAPPENAS), Indonesia Financial Service Authority (OJK), PT Asuransi Kredit Indonesia (ASKRINDO, an insurance credit company) and Perum Jaminan Kredit Indonesia (JAMKRINDO, a state-owned credit guarantee company); selected government smart city pilots, PT Sarana Multi Infrastructure (PT SMI, an infrastructure financing company which is newly established as a development bank in Indonesia and an accredited entity for the Green Climate Fund), selected state-owned banks, and PT Nico Securities Indonesia or other similar local investment bank in Indonesia. This activity will further deepen the understanding and appreciation by the stakeholders on actual global best practices and lessons learned regarding the proposed innovative financing support schemes which will listed in Activity 3.1.2. This activity will involve the assistance of two national consultants (a technical expert and a financial expert) and an international consultant.

GEF will provide support the intensive studies including travel expenses, hiring of experts for development of innovative financial support schemes, synthesis of report and recommendations, conduct of FGDs and other related expenses.

Activity 3.1.2: Development of ESCO business models to be demonstrated in the pilot projects. This activity will identify financial support instruments or schemes as evaluated in Activity 3.1.1 that are most relevant and could be practical in expanding the market for EEL in Indonesia. Based on the initial PPG studies, ESCO models are recommended and can be implemented by the project in pilot projects under Activity 3.1.3. In order to strengthen the viability of the ESCO arrangements for various LED applications in buildings and street lighting, the existing instruments in the country as mentioned under Activity 3.1.1 will be explored as to how they could be integrated with the ESCO models. The identified financial support scheme should be able to stimulate and incentivize the implementation of full scale ESCO business model (and/or in combination with other business models) and should be in line with economic and environmental objectives of the project. To be fully supported by the government in the ESCO’s adoption and qualification for a loan, the project will provide support for the development, drafting and issuance of a financial and bank policy through a decree by the Indonesia Finance Service Authority (OJK). This activity is also linked to Output 3.2.

Schemes to be explored in configuring the financial support instruments or schemes to strengthen ESCO models in various LED lighting applications are:

- PPP framework for smart cities LED street lighting projects

- Tools to prepare a Bankable Investment Proposal including Feasibility Study (FS) and Financial Modeling for Financing ESCO business model

- Credit Guarantee Facility for ESCOs implementing shared savings EEL/LED investment projects

- Other financial support schemes such as an alternative/ possibility to bundle multiple EE lighting projects as acceptable collateral for EEL Financing, as maybe deemed necessary for the project’s objectives.

Activity 3.1.3: Mainstreaming of the existing national policies and regulations for the banking sector to accelerate penetration of EEL. This activity will involve up to three nationwide banking forums for Bank credit officers, credit analysts and risk managers of banks and key stakeholders including dissemination of project results in line with the overall market transformation for EE lighting. This will be done in cooperation with OJK, BKF of Ministry of Finance of Indonesia (the Centre for Climate Change Financing and Multilateral Policy), Ministry of Finance and DGNREEC MEMR. Dissemination training and forums on “EE financing and LED lighting investment” will be designed to demonstrate exemplary good practices of EEL financing to equip and enable bankers to evaluate and support lighting industry modernization project. The targeted training participants are Credit Officers and Risk Managers (both divisions construct the “Four Eyes Principles” in credit approval process in a bank) from eight bank participants of the First Movers of Sustainable Banking (an OJK program) for sustainable finance. Particularly, this will be in view of the EE lighting projects of commercial office buildings, plus Regional Development Banks (BPD) of the selected pilot demonstration of street lighting smart city pilot hosts, PT Nico Securities Indonesia, PT SMI, and Indonesian Banking Associations (HIMBARA and PERBANAS). This activity is also linked to the achievement of several other relevant outputs namely Output 1.1, Output 1.3, Output 2.1, Output 2.2 and Output 2.3.

GEF support is for the incremental requirements that may be required in the following activities: drafting of the procedures, the conduct of three nationwide banking forums and expert consultations.

- Output 3.2: Pilot demonstrations for accelerated LED lamp deployment in buildings and for street lighting in context of sustainable cities as well as in residential sector

Activity 3.2.1: Design, approval, capacity development and implementation of pilot demonstrations using ESCO business models in street lighting, buildings and residences. This activity will encourage end users to shift from conventional lamps to LED in selected applications in commercial buildings and street lighting through the following pilot demonstrations as described below. The pilot demonstrations will address technical, investment and financial support requirements which constitute the up-front costs in formulating and initiating the EE program that usually become hurdles for coming to EE investment initiatives even while the potential benefits may have been identified. The project will remove these barriers and pave the way to attract numerous building owners and city governments to follow this developmental route for more efficient and sustainable operations. Once these developmental concerns are addressed, the EE lighting program for government buildings will be properly launched and the sustaining mechanisms will be put in place for MEMR to follow through and sustain through the effective implementation of the replication plan that will be initiated within the project period. The project will provide assistance in terms of investment support and technical assistance as cost-sharing with the energy user and investor. The project will also draw from the demo experiences valuable inputs in developing the procurement policy and guidelines and engagement of ESCOs for EE lighting projects which are expected to be sustainable owing to the indicated energy savings and GHG reduction. The involvement of LKPP as the government procurement agency is strategic in the development and adoption of the procurement policy and guidelines applicable to EELs. After addressing the program-related up-front costs that will be supported by GEF project, the EE lighting program will continue to be supported by the MEMR as part of its regular administrative and monitoring function while the targeted energy users can already budget for its own EE lighting transformation requirement that are sufficiently justified and implemented under the approved procurement plans and guidelines resulting from these project barrier removal activities. The Demo Project Concepts are described in Annex K in terms of project development, demo implementation, performance contracting and replication preparation.

- ESCO business models for public and commercial buildings

This activity will involve the implementation of an ESCO business model at a government agency office (initially identified as the Government Procurement Agency or LKPP building) and commercial office buildings of the eight participant banks of the ‘First Movers of Sustainable Bank’ (a program initiated by the Indonesia Financial Service Authority) to give a worthwhile ‘learning by doing’ experience for those institutions and to demonstrate the workability of the ESCO business model. Demo Concept Notes can be found in Annex K.1 and K.2 for public building and commercial building, respectively. This implementation consists of two pilot demonstrations: a) a pilot to prove the workability of the ESCO business model for “guaranteed savings” of EE lighting in LKPP Building in cooperation with the Property Management/ General Affairs, Accounting Division and Internal Audit Division; and b) pilot demonstrations to demonstrate the workability of the “shared savings” ESCO business model in commercial office buildings in cooperation with Fixed Asset Management Division as well as an Energy Sector Specialist, and Risk Management Division which are the entities in-charge in creating a loan product specialized for ESCO financing.

In the case of the public building demo, the challenges for public building administrators to enter into contracts with ESCOs through the usual procurement procedures pose certain barriers since that practice is not yet in place for EELs and the confidence in ESCOs to guarantee the savings still need to be established. This describes a situation where some entities would be hesitant to convert to EELs for several reasons including unbudgeted financial requirement for the upfront cost of lamps and lack of technical knowhow to implement and measure the impact of the conversion. In this demo, the experiences gathered will lead to two important barrier removal steps: the determination of the necessary elements for developing and approving a government procurement scheme for the government to engage ESCOs and the identification of the needs of the ESCO to strengthen itself to be able to qualify in the enhanced EEL procurement procedures and be able to guarantee the savings. But because the ESCO financial capability is still to be developed and the government does not have the budget to pay as restricted by the current procurement regulations, the project will shoulder the initial up-front cost of the lighting equipment to trigger this scheme. LKPP, being in a strategic position as an energy user and policy maker on government procurement, will pave the way through this barrier removal process. In the future, the project envisions ESCOs are strengthened technically and financially and the government sector could budget for engagement with ESCOs through a government procurement policy involving standard Energy Performance Contracting (EPC) that will be developed through the project.

The second EEL demo scheme involves ESCO Shared Savings model in commercial buildings. The ESCO assumes the investment for the initial EEL equipment outlay and enters in to an EPC arrangementthe building owner.  Depending on the agreed investment scheme, the proportion of the sharing in the savings after cost recovery between the commercial building owner and the ESCO will be determined at the outset and reflected in the EPC. The EPC will stipulate the pay back arrangement as monthly installments to cover for cost recovery and the ESCO service fees as well as the sharing formula for the resultant savings.

This activity will document, monitor and evaluate the technical and financial performance of the two models, prepare reports on advantages and disadvantages, lessons learned and best practices and develop manuals for the effective implementation of each of the models. The development strategy also looks at the possibility of the public sector being able to budget and pay for its EEL conversion and also enter into contracts with ESCOs with the option of using Shared Savings scheme as already being practiced in many places in Europe.

This activity will involve participation of LKPP, ESCOs, three local lighting manufacturers associations (ALINDO, APERLINDO, GAMATRINDO), DG NREEC – MEMR, Laboratory testing of P3TEK of DGNREEC – MEMR, eight participant banks of the First Movers of Sustainable Banking (to be initiated by OJK) for the EE lighting projects of Commercial Buildings. This activity will be undertaken by ADLIGHT project under the supervision of DGNREEC-MEMR, Ministry of Information and Communication and OJK.

GEF supports the implementation of this pilot project to shift from conventional lighting to LED lamps in the selected banks office buildings.

- ESCO Guaranteed Savings model and revolving fund for street lighting

This activity will involve the implementation phase of the selected partner City Governments to conduct a pilot using the ESCO Guaranteed Savings model for EE Street Lighting and setting up a revolving fund to finance future EEL projects in municipalities. The project will provide technical advisory and assistance in design and planning and the financial support for the acquisition and installation of LED lamps replacing less efficient lamps, incorporating women’s and men’s different needs and perceptions of street lighting. The project will also support the initial investments in the municipal EEL transformation and ESCO development.  The energy savings resulting from the conversion will be deposited in a revolving fund that will accommodate the financing of future EEL projects. Each municipality can set up its own revolving fund, where initial project financial assistance allow for using the savings to capitalize the revolving fund and use it for their future projects.

This implementation consists of two pilot demonstration projects. A first pilot project will be in Java Island to prove the workability of the ESCO model for EE Street Lighting. This will include the development of an energy metering and reporting system to measure Energy Savings and Budget Savings (of Local Government Annual Income and Budget/APBD) for EE Street Lighting and to submit the evaluation and recommendation report to the City Government and House of Regional Representatives/ DPRD. A second pilot demonstration of street lighting will be outside Java island under a different setting but typical of other areas using different procurement procedures. The Demo Project Concept is described in Annex K.3. The Government of Indonesia is currently assessing 10 up to 25 candidates for piloting of Smart Cities including those outside Java Island. This activity will involve participation of City Governments, ESCOs, DGNREEC – MEMR, three local lighting manufacturers associations, Lab test P3TEK of DGNREEC – MEMR , Regional Development Banks (BPD) of the selected pilot of Smart Cities. This activity will be undertaken by the project under supervision from DGNREEC-MEMR, Ministry of Information and Communication and Financial Service Authority (OJK).

GEF supports the implementation of this pilot project to shift from conventional lighting to LED lamps in the selected Smart City Street Lighting and other municipalities and technical support in setting up revolving funds.

- On-bill financing model for selected government-owned residential buildings

This will involve the implementation in selected government low-income residential housing which are owned and managed by the government. The pilot demonstration will consist of replacing 250,000 existing lighting with 3-watt LED lighting. The cost of the LED replacement will be included by the housing management in the tenants’ monthly maintenance fees. Lamps will be replaced and costs for the lamps will be recovered from maintenance fee through the regular management and administration of the residential buildings. The activity will also involve training of the residential building administrator on the relevant financing and billing tasks regarding the effective conversion to EEL so as to orient them on the new responsibility to manage and sustain the EEL conversion. Lessons learned from implementation can be used to guide the possible improvement of financial support schemes as necessary for the deployment of more replication projects. In its important role for introducing EEL, government can encourage its housing projects to participate in proliferating EELs. The transition towards efficient lighting in residential sector will be ushered by the government to expedite the uptake of EEL through the formulation and implementation of favorable policies derived from the demonstration projects as well as lessons learned in other countries. This activity will also involve consultations with direct beneficiaries within the residential pilot areas, ensuring equal participation of women and men beneficiaries.

GEF supports the implementation of this pilot project to shift from conventional lighting to LED lamps in the selected residential applications.

Activity 3.2.2: Design, planning and conduct of training for local government municipalities and cities and pilot demonstration hosts This activity will involve capacity development trainings of local government municipalities and cities and pilot demonstration institution hosts about EEL systems and government procurement systems using the ESCO business models. During this activity women’s active participation will be encouraged. This activity is intended for interested city governments to implement EE Street Lighting and to further expand the workability of the ESCO model for EE Street Lighting in the Smart City Design Concept. It will synthesize the lessons learned from pilot demonstration projects to guide the possible improvement of financial support schemes as necessary for the deployment of more replication projects. This activity also includes dissemination of the results of Activities 3.1.3.

GEF will provide support for the design, planning and conduct of training, preparation of training manuals, evaluation and recommendations for improvement and sustainability.

- Output 3.3: Implemented awareness and promotion program and information system explaining the benefits of high energy efficient lighting technologies, taking into account gender specific aspects in developing and implementing the programmes.

Activity 3.3.1: Development of a gender-responsive EEL awareness and promotion program on the benefits of good quality LED lighting. This activity will involve the development of an awareness program, promotion packages and multimedia dissemination for general public, business sector and government sector in Indonesia on the benefits of energy efficient lighting technologies. These awareness raising activities are meant to raise attention as well as increase the knowledge about energy efficient lighting technologies. Target groups are government and non-government procurement agencies, city governments, gender equality-focused organizations, state-owned as well as commercial banks, investment banks and development banks as well as the general domestic market. This activity involves participation of regional office of PLN Regional Office), Regional House of Representative (DPRD), local universities, MASKEEI (Masyarakat Konservasi dan Efisiensi Energi Indonesia) or IECES (Indonesia Energy Conservation and Efficiency Society), and other government smart cities. This activity correlates back to Activity 1.1.2 regarding the market surveys of high efficient lamps in Indonesia, and is also linked to achievement of the results under Output 3.2.

GEF will provide support for the dissemination including exhibition, ‘green corners/desks for local EE lamps’ in retailers, public and social media campaign on the benefits of innovative lighting technologies in several cities.

Activity 3.3.2: Development and implementation of information support network system, database and website on EEL product distribution, sales and performance in the market for various consumer groups  This activity will involve an information support network system and data base which are aimed to allow access by all stakeholders in EE lighting to vital information and data by providing an accredited database by which data on EE lighting product’s distribution, sales, performance in market and other information is made available to support operations, management and decision-making in relation to the business transformation, information and awareness and market control in pursuit of the ADLIGHT goal and objectives. The project looks at an integrated and organized system or network for the collection, organization, storage and communication of information among key project partners and participants. This activity will involve the participation of the National Standardization Body (BSN), local manufacturers association (ALINDO, APERLINDO, GAMATRINDO), DG NREEC – MEMR, Lab test P3TEK of DG NREEC MEMR, State-Owned Utility Company/PLN, city(ies) government and line ministries (Ministries of Public Works, Transportation, Industry, Trade, Custom, OJK, BKF MoF) and other relevant agencies.

GEF will provide support for the development and implementation of the information support network system, database and website.

# Results and Partnerships

- Expected Results

The following describes the expected results from the work that will be done through the ADLIGHT Project using the strategy described above which the project proposes to support Indonesia to advance the market for energy efficient lighting technologies. The project’s planned key interventions, among others, include the following:

- Approval of SNI/MEPs and other policies

- Strengthened institutional structure through capacity building

- Successful demos and replication

- Capable and internationally accredited EEL laboratories

- Financing institutions and ESCOs continuous support to financial schemes

- Effective information and promotions

- Increased awareness around gender gaps and opportunities in the LED lighting market

The significant development that will mark the realization of the Alternative Scenario is the completion and attainment of the various targets under each success indicator which are further detailed in Section VI: Project Result Framework will include the following:

- Overall results

- Cumulative electricity savings by EOP of 77.45 GWh

- Direct project GHG emissions mitigated by EOP of 62.58 kt CO2

- At least 10% of women and at least 10% of men, who previously lacked access to energy efficient lighting services and technologies in the residential areas, public buildings and streets in pilot areas, are benefiting from these services and technologies as influenced by the project

- Women and men are benefiting equally from EEL technologies and increased access to knowledge about energy efficient lighting technologies

2. Improved quality, energy efficient and affordable locally-produced EEL products and systems

- Efficiency of locally produced lighting systems increased, (lm/W) and Production cost decreased from baseline level

- Six (6) lighting manufacturers who received technical assistance on the design and production of high efficient lighting products and systems

- Two (2) investment grade proposals for business transformation plans approved by banks

- Improved conditions for fair market competition of EE lighting products, informed by robust policy and institutional framework

- Three (3) policy documents at the national level, including Standard Minimum Quality and MEPS on LED and other relevant guidelines, developed and approved (specifically, SNI updated and Implemented MEPS and endorsed labeling standard)

- Two (2) policy and guideline on LED procurement developed and implemented in E-catalogue and regular public procurement system

- A set of comprehensive MVE Guideline and required implementing rules and regulations for including resolving custom dispute and legality of products developed and implemented

- Increased market share for high quality and efficient lighting

- Full scale ESCO models incorporating innovative financial support instruments or schemes developed to accelerate penetration of EE lighting systems in public and commercial buildings and street lighting as well as in government-owned residential sector

- Five (5) pilot ESCO demonstrations (2 cities, 2 buildings, and a set of selected residential areas); With possible replication in 2 cities and 7 buildings and other residential areas

- Four (4) municipalities, six (6) clients (project developers/ building owners), five (5) technology providers and two (2) financial institutions stakeholders engaged.

The three-year ADLIGHT project is expected to reduce annual electricity through its direct pilot and immediate replications by 60.17 GWh/yr or cumulatively 77.45 GWh by the end of the project (EOP) in Year 3 (2021). It targets to contribute_378.31 GWh cumulatively in 2026 or 5 years after the EOP and 679.17 GWh in 2031 or 10 years after EOP. The equivalent reduction of CO2 emissions is estimated at 48.62 kton CO2 per year by 2021. Cumulatively, reduction of CO2 emissions amounts to 62.58 kton CO2 by 2021, 305.67 kton CO2 by 2026 and 548.77 kton CO2 by 2031. More details are in Annex L.

Table 4: Summary of Expected Results of Baseline and Alternative Scenarios

| Particulars | 2016 (Baseline) | 2022 EOP Year 3 | 2027 5 yrs after EOP | 2032 10 yrs after EOP |
| --- | --- | --- | --- | --- |
| - Direct and Direct-post project (Pilot and Replication) |  |  |  |  |
| Energy Saving Total, GWh/yr | 0 | 60.17 | 60.17 | 60.17 |
| Cumulative Energy Saving, GWh | 0 | 77.45 | 378.31 | 679.17 |
| Emission Reduction per Year, kt CO2/yr | 0 | 48.62 | 48.62 | 48.62 |
| Direct project GHG emissions mitigated, kt CO2 | 0 | 62.58 | 305.67 | 548.77 |
| - Conservative penetration rate and increased efficiency Scenario |  |  |  |  |
| Penetration rate for all sectors |  |  | 10.0 % | 20 % |
| Increased efficiency in all sectors* | R: 57.0% I,C,S,GO: 49.5% SL: 65.0% | R: 59.4% I,C,S,GO: 51.0% SL: 66.0% | R: 65.4% I,C,S,GO: 58.5% SL: 71.0% | R: 59.4% I,C,S,GO: 51.0% SL: 66.0% |
| Energy Saving Total, MWh/yr |  | 241 | 3,851 | 10,357 |
| Cumulative Energy Saving, MWh |  | 310 | 11,461 | 48,757 |
| Emission Reduction per Year, kt CO2/yr |  | 194 | 3,111 | 8,369 |
| Cumulative Emission Reduction, kt CO2 |  | 250 | 9,261 | 39,395 |
| - Optimistic penetration and increased efficiency Scenario |  |  |  |  |
| Penetration rate for all sectors |  |  | 9.2 % | 32.2 % |
| Increased efficiency in all sectors* | R: 57.0% I,C,S,GO: 49.5% SL: 65.0% | R: 59.4% I,C,S,GO: 51.0% SL: 66.0% | R: 65.4% I,C,S,GO: 58.5% SL: 71.0% | R: 59.4% I,C,S,GO: 51.0% SL: 66.0% |
| Energy Saving Total, MWh/yr |  | 241 | 3,561 | 16,583 |
| Cumulative Energy Saving, MWh |  | 310 | 10,731 | 60,767 |
| Emission Reduction per Year, kt CO2/yr |  | 194 | 2,877 | 13,399 |
| Cumulative Emission Reduction, kt CO2 |  | 250 | 8,671 | 49,100 |

*R-Residential, I-Industry, C-Commercial, S-social, GO-Government Office, SL-Street Lighting

The following figures, illustrate BAU and alternative energy consumption, energy savings, equivalent CO2 reduction under two (2) likely scenarios: (a) conservative penetration rate and improved energy efficiency and (b) optimistic penetration rate and improved energy efficiency as summarized in the estimated projections. Details are seen in Annex L.

      - Conservative Scenario

B. Optimistic Scenario

Fig. 4: Conservative and optimistic penetration rate and increased efficiency Scenarios

- Partnerships

The project will be executed by the Ministry of Energy and Mineral Resources (MEMR). This project is part of the global programmatic framework for which UN Environment is the lead GEF Agency. UNDP will be the lead GEF Agency for the implementation of the project in Indonesia, which will be co-implemented with UN Environment. The initiative will follow the institutional structure as described in Section 6 of the Program Framework Document. The national project steering committee will be composed of the Ministry of Industry, Ministry of Finance, Ministry of Trade, Lighting Industry Association, Indonesia National Standards Organization BSN, national lamp testing laboratories, UN Environment and UNDP. International project partners including international organizations, global manufacturers, utilities, and gender equality-focused organizations working in energy will support the project to achieve its objectives. This support will come in form of in-kind co-financing and parallel activities such as expertise on setting MEPS, training on efficient lighting manufacturing, market surveillance activities, public awareness campaigns and regulatory making processes.

Partners include companies throughout the lighting value chain, financial institutions, academic institutions and laboratory and research centers who will work together in the three-year project which is co-implemented by UNDP and UN Environment with the MEMR as the project executing agency.

Table 5: ADLIGHT Partners and Roles in the Project

| Partners | Role in Project Implementation |
| --- | --- |
| Ministry of Energy and Mineral Resources (MEMR) | Provides overall direction and oversight as the Executing Agency; acts as Chairman of the National Steering Committee; provide the lead role in coordinating with other ministries and agencies in pushing forward the goals and objectives of the efficient lighting industry program and resolving inter-ministry barriers |
| Directorate General of New-Renewable Energy and Energy Conservation (DGNREEC) | Acts as the Responsible Party for the project and leads the Project Management Unit for the day-to-day operations and resolution of issues to ensure smooth implementation of the project; provides technical support for the technology programs; coordinates with other government agencies as well as UNDP and UN Environment |
| MEMR P3TK EBTKE (Research and Development of DGNREEC) | Provides technical support and laboratory services for the needs of the LED industry; leads the capacity building and accreditation of laboratory facilities in meeting the MEPS/SNI standard requirement, benchmarking and round-robin testing |
| Min of Development Planning (Badan Perencanaan Pembangunan Nasional or BAPPENAS) | Acts as the integrator of the related government programs within the overarching objectives of the EEL program which crosses many sectoral boundaries and policy/organizational areas considering overall national interest |
| Public Procurement Agency – Lembaga Kebijakan Pengadaan Barang/Jasa Pemerintah (LKPP) | Acts as main resource agency for the development and adoption of government procurement policies in order to hasten the market penetration of locally produced high efficiency and affordable lighting products |
| Financial Service Authority (Otoritas Jasa Keuangan or OJK) | Coordinates among financial institutions and banks and provides overall policy direction and guidance in implementation of financing mechanisms that will be adopted by the project |
| PT Sarana Multi Infrastruktur - Persero (PT SMI) | Acts as resource group for green banking and green infrastructure as it applies to buildings and street lighting finance |
| City Government – Smart Cities | Act as pilot demonstration hosts in EEL application in street lighting and the evaluation of the impacts of the transformation toward EELs |
| Energy Service Company (ESCO) | Provides the main link between the EEL manufacturers and users and facilities project development, financing and EPC requirements |
| State Owned Banks & Financial Institution | Acts as catalysts in the development and implementation of the business transformation plans to transform the industry to produce and market EELs locally and potentially abroad |
| Perusahaan Listrik Negara (PLN) State Electricity Company) | Acts as resource organization on energy supply, pricing, and policy in support of the increased market for EELs and transition from the conventional lamps as well as possible participation in piloting LED distribution schemes and billing systems through ESCO model will be tested for residential sector LED programme with the cooperation of PLN, using its organization and network for the residential sector |
| Ministry of Trade | Act as resource ministry in the harmonization of policies and regulations regarding trading of locally produced and imported EELs; provides active support in the MVE schemes and market control to encourage efficient and reasonably priced lighting products that meet MEPS/SNI |
| Ministry of Industry | Act as resource ministry for the policies and regulations governing the lighting industry sector and the implementation of business transformation plans towards producing affordable, high quality lighting products and for determination of local content of locally manufactured products |
| Ministry of Public Works and Housing | Acts as resource ministry in the application of EELs in the street lighting and building consumer groups |
| Ministry of Finance/Bureau of Customs | Provides lead role in the application and regulation of policies regarding custom duties and importation of lighting product components as well exportation of standard products whenever viable; participated in the development and implementation of MVE schemes vis-à-vis MEPS/SNI adopted and the corresponding inspection software to discourage entry or usage of inefficient lighting products |
| Badan Standardisasi Nationa (BSN) or National Standardization Agency | Provides technical support and policy coordination in the development and adoption of the SNI and MEPS within the timeframe of the project considering ASEAN and other international commitments in MEPS and labeling |
| BPPT (Research Agency for Technology Development and Implementation) | Acts as resource agency in the R&R and product development for EEL technology and their application |
| Tingkat Kandungan Dalam Negeri (TKDN) or Llocal Content certifiers | Act as resource agency in the policy review and recommendations in enhancing the local content of locally manufactured lighting products |
| Credit Facility Guarantee/Credit Insurance Companies | Act as resource groups for determining appropriate financing support schemes in support of the full scale ESCO model regarding credit guarantee facility |
| Lighting Industry Associations (GAMATRINDO, ALINDO and APERLINDO) | Provides technical support and coordination among local manufacturers; leads the industry associations and its members in policy discussions to achieve timely progress in project implementation and performance targets; lead the transition to higher efficiency and cost-effective EEL production and acts as coordinator and focal point in the monitoring, verification and enforcement representing the EEL industry for measuring impact and corrective actions |
| Development Partners (MTRE3, ICED2, PFAN, and other bilateral projects) | Provide technical support and coordination regarding the implementation of relevant activities towards achievement of outputs that have common project objectives |
| Gender equality-focused organizations and ministry-designated focal points working on energy | Provide support in gender-mainstreaming activities in pursuit of the overall project objectives to be coordinated by the MEMR-designated gender focal point for the project |

- Risk Management

As per standard UNDP requirements, the Project Manager will monitor risks quarterly and report on the status of risks to the UNDP Country Office. The UNDP Country Office will record progress in the UNDP ATLAS risk log. Risks will be reported as critical when the impact and probability are high (i.e. when impact is rated as 5, and when impact is rated as 4, and probability is rated at 3 or higher). Management responses to critical risks will also be reported to the GEF in the annual PIR. Project risks are summarized below in Table 6. A Project Risk Log is provided in Annex H.

Table 6:  ADLIGHT Project Risk Log

| Project Risks |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Description | Type | Impact & Probability | Mitigation Measures | Owner | Status |
| - Prolonged delays in the implementation of MEPS due to Government procedures and processes | Political Regulatory | P = 2 I = 3 | BSN to come up with SNI standards that can be used as reference in the government procurements and other EEL applications while MEPS is being developed | MEMR/DGNREEC BSN Industry associations Min of Trade and Industry | Reducing |
| - Local lighting manufacturers may not be interested to upgrade the lighting production facilities due to increased investments, disruption to operation and business priorities | Financial Operational Strategic | P = 3 I = 3 | Coordinate closely with manufacturers associations and local banks to facilitate investments; facilitate through ESCOs and TWG | MEMR/DGNREEC Industry associations Min of Trade and Industry | Reducing |
| - Petroleum products and electricity prices will be at levels that make energy efficiency projects, particularly in EEL, uncompetitive and not cost effective | Strategic Environmental Political | P = 3 I = 3 | Government to be encouraged to adopt appropriate energy pricing policies and incentives to encourage EE project investments | MEMR/DGNREEC Min of finance Min of Planning Industry associations Min of Trade and Industry | Increasing |
| - Manufacturers are not committed to improving the energy-efficiency and quality of products. | Organizational Operational | P = 2 I = 3 | Coordinate closely with manufacturers associations; facilitate through ESCOs and TWG | MEMR/DGNREEC Industry associations Min of Trade and Industry | Reducing |
| - Manufacturers are not willing to share data on their operations and marketing for MVE | Financial Operational | P = 3 I = 3 | Coordinate closely with manufacturers associations; facilitate through ESCOs and TWG | MEMR/DGNREEC Industry associations Min of Trade and Industry | Reducing |
| - Banks and financial institutions are not convinced about the business potential of manufacturing and market for LED systems | Financial Operational Organizational | P = 3 I = 3 | Coordinate closely with manufacturers associations and local banks to facilitate investments; facilitate through ESCOs and TWG | MEMR/DGNREEC Industry associations Min of Trade and Industry OJK Financial institutions/Banks | Reducing |
| - Commitment to abide with regional and international EEL standards and harmonization is lacking | Political Regulatory | P = 2 I = 3 | Implement Component 2 on policy and institutional support effectively | MEMR/DGNREEC Industry associations Min of Trade and Industry | Reducing |
| - Policy framework may not attractive for manufacturers and users to invest in EEL projects. | Political Regulatory | P = 3 I = 3 | Implement Component 2 on policy and institutional support effectively | MEMR/DGNREEC Industry associations Min of Trade and Industry | Reducing |
| - Local EEL producers could not meet all technical standard specifications | Financial Operational Organizational | P = 3 I = 3 | Coordinate closely with manufacturers associations; facilitate through ESCOs and TWG | MEMR/DGNREEC Industry associations Min of Trade and Industry | Reducing |
| Overall |  | P = 3 I = 3 |  |  |  |

*Probability on a scale from 1 (low) to 5 (high) and Impact on a scale from 1 (low) to 5 (high).

- Stakeholder engagement plan

The stakeholder process for the ADLIGHT project started during the stakeholder consultative meeting and logical framework analysis held in May 2017 where representatives from various sectors relevant to lighting products manufacturing and application were gathered for determining the barriers to transforming the market for efficient lighting devices.  The manufacture and use of lighting product and systems cuts across many sectors: energy, transportation, industry, trade, financial, public works and housing, research and technology development, policy and regulation.  The Project will be organized through a coordination mechanism that will involve representatives from the above-mentioned sectors.

At the national level, the project management team will build on the stakeholder consultation process that includes the inception workshop and other bi-lateral meetings. A broader consultation with a range of stakeholders will be held under the leadership of the Ministry of Energy and Mineral Resources. The consultation will be arranged via the Working groups set up under the Project Management Unit (Figure 6).

At the local level, stakeholders will be engaged through the UNDP’s standard stakeholder engagement processes. The project management team and MEMR/DGNREEC will continue to work closely with key project stakeholders such as project sponsors, co-financing institutions, community-based organizations and relevant NGOs.

The following civil society organizations will be closely involved in project implementation:

- Lighting Industry Associations (GAMATRINDO, ALINDO and APERLINDO)

- Tingkat Kandungan Dalam Negeri (TKDN) or Local Content certifiers

- Masyarakat Konservasi dan Efisiensi Energi Indonesia MASKEEI or IECES (Indonesia Energy Conservation and Efficiency Society)

Special consideration for the disenfranchised groups from the local communities, women, children, elderly, the poor, vulnerable and minorities are also being included because they will benefit greatly from greater access to and use of efficient and cost-effective energy efficient lighting products in terms of day-to-day need, safety and security. To coordinate various interests and needs, the project will have a National Steering Committee whose membership will come from major stakeholders to ensure that their needs are addressed through a broader range of national actors so that stakeholder involvement will widely be an inclusive and participative process.

- Gender equality and empowering women

The ADLIGHT project provides unique opportunities to advance gender equality in interventions for advancing the manufacture and application of EELs systems in Indonesia. The ADLIGHT project has included specific activities and targets that advance and report on gender equality results, including more balanced participation between men and women in workshops and consultations, with particular focus on advancing gender equality through stimulating the LED market. Another particular focus is on the need for women’s consultation through interventions related to sustainable street lighting solutions where EEL, particularly LEDs, have very important contributions.

During the project design, a Gender Analysis and Action Planning were conducted focusing on several areas for consideration in the ADLIGHT project (see Annex N). The main outcomes of the gender analysis are summarized below:

- The traditional energy sector is still one of the least gender-inclusive sectors to date globally. According to one estimate, women represent only 6 percent, 4 percent and less than 1 percent of the technical, decision-making and top management positions, respectively, in the energy sector.

- In Indonesia, women have a limited access to information related to energy, given the male-dominated industry, which in turn limits women’s participation and contribution to shaping policy

- Gender gaps related to access to energy, finances, training, employment and entrepreneurship need to be addressed in Indonesia

- Women and men have different perceptions on what constitutes adequate illumination, as well as the sense of safety it provides on a particular street, with men having the tendency to perceive that the illumination had been adequate while the women tended to claim that it was not bright enough.

- Increasing the energy efficiency of street lighting is not only cost effective, it provides gender-sensitive results by improving nigh-time safety in cities

- Households where women are the predominant decision maker tend to have lower energy consumption

Deeper gendered assessments need to be conducted in order to better illustrate how women and men interact with the local economy differently with regard to LED lighting. Energy sectors are primarily male-dominated in Indonesia and globally, however women are an untapped resource, as key beneficiaries of lighting technologies, and consultants on how to most effectively raise awareness about new lighting technologies. Finally, addressing gender gaps at leadership, policy and industrial levels in the electricity sector is an opportunity to advance gender equality, and the economy of Indonesia at large.

The ADLIGHT project is committed to ensure that women’s and men’s different roles, perceptions, and opportunities in contributing to and benefiting from application of energy efficient LED lighting technologies in Indonesia will be considered. Gender mainstreaming will be included, as appropriate, to be gender transformative in project’s implementation strategies and activities in advancing the application of EELs in the country.

- South-South and Triangular Cooperation (SSTrC)

The ADLIGHT Project will pursue and promote South-South and triangular cooperation forms an integral part. Indonesia is very actively supporting this approach in its participation in many projects of the ASEAN on energy efficiency. The UN Environment’s Global Leapfrogging Program is also advocating this approach where ADLIGHT is part of this leveraging the experience of other countries on advancing high efficient lighting. Within the Global Leapfrogging Program, countries will cooperate in such activities as: knowledge exchange, technology transfer, financing, peer support, and country-to country or multi country initiatives, on high efficient lighting technology.

- Sustainability and Scaling Up

The project’s multi-pronged barrier removal approach, covering policy and planning, commercial and technical viability, financing, and information and awareness, is designed to stimulate ongoing replication of the project demos and, thus, scale-up of project results.

The ADLIGHT project sustainability is well-founded within Indonesia’s long drawn policies and program on energy efficiency and conservation (EE&C) as mandated in the country’s Government Regulation of the Republic of Indonesia No. 70/2009 on Energy Conservation. To strengthen institutional support, the Directorate General of New-Renewable Energy and Energy Conservation (DGNREEC) was established in August 2010 to implement the EE&C program and continued to be reinforced by succeeding regulations and pronouncements placing EE&C an important component in the Presidential Regulation No. 61/2011 on National Action Plan to Reduce Green House Gases (RAN-GRK) as well as in the international commitment in the Nationally Determined Contribution (NDC) and regional agreements such as in the ASEAN. These are among the major policies that are supportive to energy efficient lighting program agenda. Lighting is a major energy end-use that accounts for 18.8% of the total electricity used for all sectors which gives a big reason to pursue sustainable development in this area. The response of the private sector has been very encouraging and constitutes a major driver in achieving the ADLIGHT goal of transforming the market for efficient energy lighting towards its high potential and long lasting impact on energy saving and GHG reduction. The pilot EEL demonstrations in buildings and street lighting will lead to sustained growth and impact.

The strategy focuses on mitigating investment risks on production and increasing market penetration of high quality EELs not only in Indonesia but also in the region. The project will ensure that policy risks are addressed by working closely with the government and establishing the quality and performance standards for investors to invest in quality EEL products without fear of competition from low quality products. The project will support the relevant agencies and stakeholders to ensure technology, policy, institutional and human capacities are established for the realization of ADLIGHT-supported development pathway. With an increasing market and improved standards of EELs, the financial risk will be addressed in a sustainable manner. The ADLIGHT project activities are designed in a way that encourages replication. The project will support the Government of Indonesia in harmonization of its policies and legislative framework, particularly Minimum Energy Performance Standards (MEPS) for LED lighting products with international conventions and ASEAN standards. These activities will require updates and applications in similar related fields. This will increase the sustainability of the regulatory system.

The engagement of the local EEL manufacturing industry as the key stakeholder in this market transformation strategy will ensure its buy-in in demonstrating the benefits of quality production and creating conditions for them to benefit from sustainable application of EELs.

The project will develop business and financing models to implement large scale EEL production upgrade projects. Once financial institutions can see EE lighting investment as a bankable investment, replication will be easier to conduct. The state-owned bank building as one of main targets of pilot demonstration in the ADLIGHT project was selected to encourage banks to have first-hand experience and benefit (energy and cost saving per year) from EE lighting investment and projects. By including banks as project stakeholders and target recipient of pilot demos, the project will work towards improving the bankability perception of EE lighting investment in Indonesia and developing viable ESCO business models for a sustainable approach in future.

The project has included the establishment of an Efficient Lighting Knowledge Center for collecting market information on lighting products, quality standards of products, quality product listing (QPL) and database in cooperation with a network of qualified laboratories, consumer perception, including gender-disaggregated consumer data to be made available, and other related information regarding efficient lighting technology and technology providers. It will ensure that the knowledge management support is fully developed in line the active transition to EELs as a sustainable program.

# Project Management

- Cost efficiency and effectiveness

The ADLIGHT project strategy of focusing on buidlings and street lighting is expected to maximize the energy savings possible within a three-year period through providing assistance to the lighting industry in order to modernize their facilities to produce highly efficient and cost-effective lighting products.  With the estimated CO2 emission reduction of around 1.65 million tons equivalent of the energy saving potential and project cost of US$ 3.89 million, the unit abatement cost is US$ 2.36 per ton CO2.

| ADLIGHT Project | Value |
| --- | --- |
| I - Direct project |  |
| Direct post project CO2 emission reductions (t CO2) | 548,766 |
| II – Indirect |  |
| Indirect CO2 emissions - top-down (tCO2) | 1,097,533 |
| GEF finance (US $) | 3,895,872 |
| Total emission reductions (t CO2) | 1,646,299 |
| Unit Abatement Cost (UAC) ($/tCO2) - (Direct savings) as per GEF CO2 emission reduction calculation methodology ($/tCO2) | 7.0 |
| Unit Abatement Cost (UAC) ($/tCO2) (Direct + Indirect) | 2.36 |

Based on 2016 estimates, the projected 2032 (after 10 years from EOP) cumulative energy savings range from 48.7 GWh to 60.8 GWh in the conservative and optimistic EEL market penetration scenarios. This translates to estimated 4,187 to 5,227 tons of oil equivalent or in terms of foreign exchange equivalent of USD 1.79 million to 2.23 million.

The proposed project’s design aims to deliver a high level of cost efficiency and effectiveness in use of GEF funds. Cost efficiency and effectiveness will be achieved by strategies that leverage limited inputs of GEF funding to stimulate much greater investments by other parties, namely the government and the private sector. The project is expecting to generate USD 18,115,000 in private sector investments within the project timeline and additional resources as the pilot demonstrations are replicated in the country.

- Project management

The Project will be implemented, subject to space availability, at the designated space for the Project Management Unit located at the MEMR.  The project will be attended by Project Manager, Finance and Administrative Assistant and any other national expert hired for the execution of the project. The PMU will take care of day-to-day management and implementation of project activities leading to the Project Outputs and Outcomes, prepare annual work plans and build ownership for the project results.

- Agreement on intellectual property rights and use of logo on the project’s deliverables and disclosure of information

To accord proper acknowledgement to the GEF for providing grant funding, the GEF logo will appear together with the UNDP and UN Environment logo on all promotional materials, other written materials like publications developed by the project, and project hardware. Any citation on publications regarding projects funded by the GEF will also accord proper acknowledgement to the GEF. Information will be disclosed in accordance with relevant policies notably the UNDP Disclosure Policy and the GEF policy on public involvement.

- Social and environmental safeguards

Environmental and social grievances will be reported to the GEF in the annual PIR. The Social and Environmental Screening Report is attached in Annex F.

As can be seen in the Social and Environmental Risk Screening Checklist, there are two risks identified under Principle 2, Gender Equality and Women’s Empowerment and three risks under Standard 7, among which are Pollution Prevention and Resource Efficiency. The latter are regarding risks on potential pollution and risks from hazardous and non-hazardous waste materials from replaced fluorescent lamps/CFL and other conventional lighting systems and accessories, particularly mercury content and sharp glass bulb parts need to be managed and proper disposal system be implemented and monitored. The project’s Activity 2.4.5: Design, planning and conduct of training on waste management and recycling of components and materials of conventional lighting replaced by LED has been included to address this issue and ensure effective waste management and disposal.

The Gender Analysis as described in Annex N includes a Gender Action Plan which was used in elaborating gender sensitive project activities throughout all Project Components.

The project risk categorization following from the Social and Environmental Screening Report as described in Annex F is Moderate.

.

# Project Results Framework

This project will contribute to the following Sustainable Development Goal (s): UNPDF/CPD Outcome 3 -- By 2020, Indonesia is sustainably managing its natural resources, on land and at sea, with an increased resilience to the effects of climate change, disaster and other shocks

This project will contribute to the following country outcome included in the UNDAF/Country Program Document: CPD Indicative Outputs -- 2.2.1. National energy policies and guideline developed and integrated into sub- national development plan. 2.2.2. Sub-national authorities and key partners are able to implement programmes, mobilize resources and develop public-private partnership for RE/EE, which will contribute to the reduction of national greenhouse gases emission.

This project will be linked to the following output of the UNDP Strategic Plan: Output 1.4: Scaled up action on climate change adaptation and mitigation cross sectors which is funded and implemented. Output 1.5: Inclusive and sustainable solutions adopted to achieve increased energy efficiency and universal modern energy access (especially off-grid sources of renewable energy)

|  | Objective and Outcome Indicators | Baseline | Mid-term Target (2020) | End of Project (EOP) Target (2022) | Assumptions |
| --- | --- | --- | --- | --- | --- |
| Project Objective To increase the penetration of high quality energy efficient lighting technologies in Indonesia through the transformation of the national market, thereby reducing electricity demand and the related greenhouse gas (GHG) emissions. | - Cumulative electricity savings by EOP, GWh | - 0 | - 17.27 GWh (62,172,000 MJ) | - 77.45 GWh (278,820,000 MJ) | - Petroleum products and electricity prices will be at levels that make energy efficiency projects, particularly energy efficient lighting (EEL), basically LED manufacturing and application, competitive and cost effective - Acceptance of the benefits and business opportunities resulting from the local manufacture and application of LED - Women’s active participation in trainings is requested and encouraged |
|  | - Direct project GHG emissions mitigated by EOP, kt CO2 (GEF Core Indicator 6.2) | - 0 | - 13.96 kt CO2 (direct by EOP) - 121.76 kt CO2 (Lifetime direct by EOP) | - 62.58 kt CO2 (direct by EOP) - 548.77 kt CO2 (Lifetime direct by EOP) |  |
|  | - Number of women and men participating in capacity building trainings throughout the project (GEF Core Indicator 11) | - -N.A. | - 30/70 | - 60/140 |  |
| Component/Outcome 1: Improved quality, energy efficient and affordable locally-produced EEL products and systems | - Efficiency of locally produced lighting systems increased, (lm/W) and Production cost decreased from baseline level (%) - Indoor Type - Outdoor Type | - Eff: 70 lm/W; - Supply chain cost: 100 % (Baseline supply chain cost to be determined at project inception) - Eff: 100 lm/W; - Supply chain cost:100% (at project inception) | - Eff: 120 lm/W; - Supply chain cost: 80% of Baseline - Eff: 130 lm/W; - Supply chain Cost: 80% of Baseline | - Eff: 150 lm/W; - Supply chaincost: 70% of Baseline - 170 lm/W; - Supply chain cost: 70% of Baseline | - Local lighting manufacturers will take up the transformation of their facilities as viable investment in production techniques for affordable and highly efficient lighting products - Manufacturers remain committed to improving the energy-efficiency and quality of products. - Manufacturers remain willing to share data. |
|  | - Cumulative number of lighting manufacturers who received technical assistance to upgrade production facilities | - 0 | - 3 manufacturers (1 for each association) | - 6 | - Commitment and active participation of manufacturers and associations with adequate financial resources to participate in the program. |
|  | - Investment grade proposal for business transformation plans - Submitted by manufacturers - Approved by banks. | - 0 - 0 | - 3 - 3 | - 6 - 6 | - Banks and financial institutions are convinced about the business potential of manufacturing and market for LED systems. |
|  | - Ratio of women and men who believe they have the capacity to - Submit (local manufacturers) - Approve (banks) investment grade proposal for business transformation plans | - 0 - 0 | - 30/70 - 30/70 | - 30/70 - 30/70 | - Women’s active participation in trainings has been requested and encouraged and women and men employees from relevant government institutions have actively participated in the capacity building activities on business transformation plans |
| Component/ Outcome 2: Improved conditions for fair market competition of EE lighting products informed by robust policy and institutional framework | - No. of policy documents at the national level, including Standard Minimum Quality and MEPS on LED and other relevant guidelines, developed and approved | - 0 | - 2 (1 SNI and 1 Draft MEPS and labeling) | - 3 (SNI updated and Implemented MEPS and labeling endorsed) | - Overall policy to cover MEPS, SNI guideline, market control MVE mechanisms and laboratory testing procedures can be developed and facilitated by the project for approval by the BSN and other authorized agencies within the timeframe of the project. |
|  | - No. of policy and guideline on LED procurement developed and implemented in E-catalogue and regular public procurement system | - 0 | - 1 (policy adapting SNI) | - 2 (policy adapting SNI and MEPS) | - SNI and MEPS for LED lights both indoor and outdoor is a priority for the MEMR . |
|  | - No. of comprehensive MVE Guideline and required implementing rules and regulations for including resolving custom dispute and legality of products developed and implemented | - 0 | - 1 (software by BSN) | - 1 | - Indonesia is committed to abide to the ASEAN Plan of Action Energy Cooperation 2016-2025 (APAEC) which highlights regional harmonization of LED lighting standard (Activity 4.1 of the APAEC) - Assuming the MEPS is approved before the EOP. |
|  | - Ratio of women and men employees in relevant government institutions who believe they have the capacity to monitor verify and enforce high quality efficiency lighting systems | - N.A. | - 30/70 | - 30/70 | - Women’s and men’s active participation in trainings has been requested and encouraged and women and men employees from relevant government institutions have actively participated in the capacity building activities on monitoring verifying and enforcing high quality efficiency lighting systems |
| Component/ Outcome 3: Increased market penetration of high quality and efficient lighting | - Cumulative no. of innovative financial support schemes developed to accelerate penetration of EE lighting systems | - 0 | - 2 | - 4 | - Targeted users and key stakeholders of EEL (basically LED) products and systems are well informed about the long-term benefits and costs and are convinced to invest in such efficient technology application projects |
|  | - Cumulative no. of pilot demonstrations completed and replication plans developed and approved for implementation | - 0 | - 3 (1 cities and 2 buildings) | - 5 (2 cities, 2 buildings and a residential area) With possible replication in 2 cities and 7 buildings. | - Policy framework would allow private investments to invest in energy efficiency street lighting projects. - Local EEL producers can meet all technical standard specifications and ESCOs can develop investment-grade proposals that will convince banks to finance the EEL projects within acceptable insurance and guarantee provisions required by banks for sustainability. |
|  | - Number of stakeholders engaged - municipalities - clients (project developers/ building owners) - technology providers - financial institutions | - 0 - 0 - 0 - 0 | - 2 - 3 - 3 - 1 | - 4 - 6 - 5 - 2 | - Pilot demonstrations will use production from local manufacturers |
|  | - Women’s and men’s level of satisfaction with EEL systems provided (reliability, affordability, convenience, efficiency) | - N.A. | - At least 60 % of women and men beneficiaries are highly satisfied with the EEL systems provided (minimum score 7/10) | - At least 70 % of women and men beneficiaries are highly satisfied with the EEL systems provided (minimum score 7/10) | - The design and installation of the EEL systems is well informed on women’s and men’s needs, preferences and habits in requirement, consumption and disposal of EEL technologies |

# Monitoring and Evaluation (M&E) Plan

The project results as outlined in Section VII: Project Results Framework will be monitored annually and evaluated periodically during project implementation to ensure the project effectively achieves these results.

Project-level monitoring and evaluation will be undertaken in compliance with UNDP requirements as outlined in the UNDP POPP and UNDP Evaluation Policy as well as UN Environment policies in context of Component 2. While these requirements are not outlined in this project document, the UNDP Country Office and Task Manager, GEF UN Environment will work with the relevant project stakeholders to ensure M&E requirements are met in a timely fashion and to high quality standards. Additional mandatory GEF-specific M&E requirements (as outlined below) will be undertaken in accordance with the GEF M&E policy and other relevant GEF policies.

In addition to these mandatory UNDP, UN Environment and GEF M&E requirements, other M&E activities deemed necessary to support project-level adaptive management will be agreed during the Project Inception Workshop and will be detailed in the Inception Report. This will include the exact role of project target groups and other stakeholders in project M&E activities including the GEF Operational Focal Point and national/regional institutes assigned to undertake project monitoring. The GEF Operational Focal Point will strive to ensure consistency in the approach taken to the GEF-specific M&E requirements (notably the GEF-7 Core Indicators) across all GEF-financed projects in the country. This could be achieved for example by using one national institute to complete the GEF-7 Core Indicators for all GEF-financed projects in the country, including projects supported by other GEF Agencies.

M&E Oversight and monitoring responsibilities:

Project Manager:  The Project Manager is responsible for day-to-day project management and regular monitoring of project results and risks, including social and environmental risks. The Project Manager will ensure that all project staff maintain a high level of transparency, responsibility and accountability in M&E and reporting of project results. The Project Manager will be responsible for providing all the regular reports as agreed under the M&E to the UNDP and UN Environment (related to Component 2). The Project Manager will inform the Project Board, the UNDP (Country Office and the UNDP-GEF RTA) and UN Environment of any delays or difficulties as they arise during implementation so that appropriate support and corrective measures can be adopted.

The Project Manager will develop annual work plans based on the multi-year work plan included in Annex A, including annual output targets to support the efficient implementation of the project. The Project Manager will ensure that the standard UNDP, UN Environment and GEF M&E requirements are fulfilled to the highest quality. This includes quarterly reporting on the progress and expenditure reports as per the requirements of UNDP and UN Environment. This includes, but is not limited to, ensuring the results framework indicators are monitored annually in time for evidence-based reporting in the GEF PIR, and that the monitoring of risks and the various plans/strategies developed to support project implementation (e.g. gender strategy, KM strategy etc..) occur on a regular basis.

Project Board:  The Project Board will take corrective action as needed to ensure the project achieves the desired results. The Project Board will hold project reviews to assess the performance of the project and appraise the Annual Work Plan for the following year. In the project’s final year, the Project Board will hold an end-of-project review to capture lessons learned and discuss opportunities for scaling up and to highlight project results and lessons learned with relevant audiences. This final review meeting will also discuss the findings outlined in the project terminal evaluation report and the management response.

Project Implementing Partner (Executing Agency):  The Implementing Partner is responsible for providing any and all required information and data necessary for timely, comprehensive and evidence-based project reporting, including results and financial data, as necessary and appropriate. The Implementing Partner will strive to ensure project-level M&E is undertaken by national institutes, and is aligned with national systems so that the data used by and generated by the project supports national systems.

UNDP Country Office:  The UNDP Country Office will support the Project Manager as needed, including through annual supervision missions. The annual supervision missions will take place according to the schedule outlined in the annual work plan. Supervision mission reports will be circulated to the project team and Project Board within one month of the mission. The UNDP Country Office will initiate and organize key GEF M&E activities including the annual GEF PIR, the independent mid-term review and the independent terminal evaluation. The UNDP Country Office will also ensure that the standard UNDP and GEF M&E requirements are fulfilled to the highest quality.

The UNDP Country Office is responsible for complying with all UNDP project-level M&E requirements as outlined in the UNDP POPP. This includes ensuring the UNDP Quality Assurance Assessment during implementation is undertaken annually; that annual targets at the output level are developed, and monitored and reported using UNDP corporate systems; the regular updating of the ATLAS risk log; and, the updating of the UNDP gender marker on an annual basis based on gender mainstreaming progress reported in the GEF PIR and the UNDP ROAR. Any quality concerns flagged during these M&E activities (e.g. annual GEF PIR quality assessment ratings) must be addressed by the UNDP Country Office and the Project Manager.

The UNDP Country Office will retain all M&E records for this project for up to seven years after project financial closure in order to support ex-post evaluations undertaken by the UNDP Independent Evaluation Office (IEO) and/or the GEF Independent Evaluation Office (IEO).

UNDP-GEF Unit:  Additional M&E and implementation quality assurance and troubleshooting support will be provided by the UNDP-GEF Regional Technical Advisor and the UNDP-GEF Directorate as needed.

UN Environment –GEF Team: UN Environment is responsible for ensuring effective implementation of Component 2 of the project. The National Project Manager will be responsible to UN Environment for timely and adequate reporting to UN Environment on Component 2. UNEP as the GEF Implementing Agency for Component 2 will be responsible for the supervision of the execution of this component to ensure consistency with GEF and UN Environment policies and procedures, and will work with UNDP, as the lead implementing agency, for overall project reporting.

Audit: The project will be audited according to UNDP Financial Regulations and Rules and applicable audit policies on NIM implemented projects.

Additional GEF monitoring and reporting requirements:

Inception Workshop and Report:

A project inception workshop will be held within two months after the project document has been signed by all relevant parties to, amongst others:

  - Re-orient project stakeholders to the project strategy and discuss any changes in the overall context that influence project implementation;

  - Discuss the roles and responsibilities of the project team, including reporting and communication lines and conflict resolution mechanisms;

  - Review the results framework and finalize the indicators, means of verification and monitoring plan;

  - Discuss reporting, monitoring and evaluation roles and responsibilities and finalize the M&E budget; identify national/regional institutes to be involved in project-level M&E; discuss the role of the GEF OFP in M&E;

  - Update and review responsibilities for monitoring the various project plans and strategies, including the risk log; Environmental and Social Management Plan and other safeguard requirements; the gender strategy; the knowledge management strategy, and other relevant strategies;

  - Review financial reporting procedures and mandatory requirements, and agree on the arrangements for the annual audit; and

  - Plan and schedule Project Board meetings and finalize the first year annual work plan.

The Project Manager will prepare the inception report no later than one month after the inception workshop. The inception report will be cleared by the UNDP Indonesia Country Office and the UNDP-GEF Regional Technical Adviser based in Bangkok, in coordination with the designated UN Environment GEF team and its Task Manager in Bangkok office and will be approved by the Project Board. The final Inception Report will be shared with project participants to formalize various agreements and plans decided during the meeting.

GEF Project Implementation Report (PIR):  The ADLIGHT Project Manager, the UNDP Indonesia Country Office, the UNDP-GEF Regional Technical Advisor, and UN Environment – GEF Task Manager based in Bangkok will provide objective input to the annual GEF PIR covering the reporting period July (previous year) to June (current year) for each year of project implementation. The Project Manager will ensure that the indicators included in the project results framework are monitored annually in advance of the PIR submission deadline so that progress can be reported in the PIR. Any environmental and social risks and related management plans will be monitored regularly, and progress will be reported in the PIR.

The PIR submitted to the GEF will be shared with the Project Board. The UNDP Indonesia Country Office will coordinate the input of the GEF Operational Focal Point for Indonesia and other stakeholders to the PIR as appropriate. The quality rating of the previous year’s PIR will be used to inform the preparation of the subsequent PIR.

Lessons learned and knowledge generation:

Results from the implementation of the ADLIGHT project will be disseminated within the project duration through the various knowledge-management-related activities under the three components of the project and beyond the project intervention area through existing information sharing networks and forums and new knowledge sharing schemes initiated by the project. The project will identify and participate, as relevant and appropriate, in scientific, policy-based and/or any other networks, which may be of benefit to the project. The project will identify, analyze and share lessons learned that might be beneficial to the design and implementation of similar projects and disseminate these lessons widely. There will be continuous information exchange between this project and other projects of similar focus in the same country, region and globally.

Results from the project will be disseminated within and beyond the project intervention area through a number of existing information sharing networks and forums that may be held in ASEAN and the UNEP’s global Leapfrogging Program, U4E and similar networks. The project will participate, as relevant and appropriate, in other UNDP/GEF and UN Environment/GEF sponsored projects.

The project has budgeted ample amounts to support the knowledge generation and sharing in pursuit of the project objective. It will also identify, analyze, and share lessons learned that might be beneficial in the design and implementation of similar future projects.

GEF Focal Area Core indicators:

The prescribed GEF Core Indicators will be used to monitor global environmental benefit results. The baseline/CEO Endorsement GEF Focal Area Core Indicators (s) – submitted in Annex D to this ADLIGHT project document – will be updated by the Project Manager/Team and shared with the mid-term review consultants and terminal evaluation consultants before the required review/evaluation missions take place. The updated GEF Core Indicators (s) will be submitted to the GEF along with the completed Mid-term Review report and Terminal Evaluation report.

Independent Mid-term Review (MTR):  An independent mid-term review process will begin after the second PIR has been submitted to the GEF, and the MTR report will be submitted to the GEF in the same year as the 2nd PIR. The MTR findings and responses outlined in the management response will be incorporated as recommendations for enhanced implementation during the final half of the project’s duration. The terms of reference, the review process and the MTR report will follow the standard templates and guidance prepared by the UNDP IEO for GEF-financed projects available on the UNDP Evaluation Resource Center (ERC). As noted in this guidance, the evaluation will be ‘independent, impartial and rigorous’. The consultants that will be hired to undertake the assignment will be independent from organizations that were involved in designing, executing or advising on the project to be evaluated. The GEF Operational Focal Point for Indonesia and other stakeholders will be involved and consulted during the terminal evaluation process. Additional quality assurance support is available from the UNDP-GEF Directorate. The final MTR report will be available in English and will be cleared by the UNDP Country Office and the UNDP-GEF Regional Technical Adviser, UN Evaluation office and UN Environment – GEF Task Manager based in Bangkok and approved by the Project Board.

Terminal Evaluation (TE):  An independent terminal evaluation (TE) will take place upon completion of all major project outputs and activities. The terminal evaluation process will begin three months before operational closure of the project allowing the evaluation mission to proceed while the project team is still in place, yet ensuring the project is close enough to completion for the evaluation team to reach conclusions on key aspects such as project sustainability. The Project Manager will remain on contract until the TE report and management response have been finalized. The terms of reference, the evaluation process and the final TE report will follow the standard templates and guidance prepared by the UNDP IEO for GEF-financed projects available on the UNDP Evaluation Resource Center. As noted in this guidance, the evaluation will be ‘independent, impartial and rigorous’. The consultants that will be hired to undertake the assignment will be independent from organizations that were involved in designing, executing or advising on the project to be evaluated. The GEF Operational Focal Point and other stakeholders will be involved and consulted during the terminal evaluation process. Additional quality assurance support is available from the UNDP-GEF Directorate. The final TE report will be cleared by the UNDP Indonesia Country Office, UN Evaluation office and the UN Environment – GEF Task Manager and the UNDP-GEF Regional Technical Adviser based in Bangkok, and will be approved by the Project Board.  The TE report will be publicly available in English on the UNDP ERC.

The UNDP Indonesia Country Office will include the planned project terminal evaluation in the UNDP Country Office evaluation plan, and will upload the final terminal evaluation report in English and the corresponding management response to the UNDP Evaluation Resource Centre (ERC). Once uploaded to the ERC, the UNDP IEO will undertake a quality assessment and validate the findings and ratings in the TE report, and rate the quality of the TE report.  The UNDP IEO assessment report will be sent to the GEF IEO along with the project terminal evaluation report.

Final Report: The project’s terminal PIR along with the terminal evaluation (TE) report and corresponding management response will serve as the final project report package. The final project report package shall be discussed with the Project Board during an end-of-project review meeting to discuss lesson learned and opportunities for scaling up.

Mandatory GEF M&E Requirements and M&E Budget:

| GEF M&E requirements | Primary responsibility | Indicative costs to be charged to the Project Budget (US$) |  | Time frame |
| --- | --- | --- | --- | --- |
|  |  | GEF grant | Co-financing |  |
| Inception Workshop | UNDP Country Office UN Environment-GEF Task Manager Project Manager (PM) | USD 11,000 |  | Within two months of project document signature |
| Inception Report | Project Manager | (included in routine project staff activity) | None | Within two weeks of inception workshop |
| Standard UNDP monitoring and reporting requirements as outlined in the UNDP POPP and UN Environment Requirements | UNDP Country Office Project Manager | (included in routine project staff activity | None | Quarterly, annually |
| Risk management | Project Manager Country Office UN Environment Task Manager |  |  | Quarterly, annually |
| Monitoring of indicators in project results framework | Project Manager | USD 12,000 (Per year: USD 4,000) |  | Annually |
| GEF Project Implementation Report (PIR) | Project Manager and UNDP Country Office and UNDP-GEF team, and UN Environment Task Manager | (included in routine project staff activity | None | Annually |
| NIM Audit as per UNDP audit policies | UNDP Country Office External auditors | Per year: USD 6,000 |  | Annually or other frequency as per UNDP Audit policies |
| Lessons learned and knowledge generation | Project Manager | USD 9,000 |  | Annually |
| Monitoring of environmental and social risks, and corresponding management plans as relevant | Project Manager UNDP CO UN Environment Task Manager | (included in routine project staff activity |  | On-going |
| Stakeholder Engagement Plan | Project Manager UNDP Country Office |  |  | On-going |
| Gender Action Plan | Project Manager UNDP Country Office UNDP GEF team |  |  | On-going |
| Addressing environmental and social grievances | Project Manager UNDP Country Office BPPS as needed | None for time of project manager, and UNDP CO |  |  |
| Project Board meetings | Project Board UNDP Country Office UN Environment Task Manager Project Manager | USD 6,000 |  | At minimum annually |
| Supervision missions | UNDP Country Office | None |  | Annually |
| Oversight missions | UNDP-GEF team and UN Environment Task Manager | None27 |  | Troubleshooting as needed |
| GEF Secretariat learning missions/site visits | UNDP Country Office and Project Manager and UNDP-GEF team, and UN Environment GEF team | USD 6,000 |  | To be determined. |
| Mid-term GEF Core Indicators to be updated by (add name of national/regional institute if relevant) | Project Manager | (included in routine project staff activity |  | Before mid-term review mission takes place. |
| Independent Mid-term Review (MTR) and management response | UNDP Country Office and Project team and UNDP-GEF team, UN Environment Task Manager | USD 20,000 |  | Between 2nd and 3rd PIR. |
| Terminal GEF Core indicators to be updated by (add name of national/regional institute if relevant) | Project Manager | (included in routine project staff activity |  | Before terminal evaluation mission takes place |
| Independent Terminal Evaluation (TE) included in UNDP evaluation plan, and management response | UNDP Country Office and Project team and UNDP-GEF team, and UN Environment GEF team | USD 50,000 |  | At least three months before operational closure |
| Translation of MTR and TE reports into English | UNDP Country Office | None |  |  |
| TOTAL indicative COST Excluding project team staff time, and UNDP staff and travel expenses |  | USD 132,000 |  |  |

# Governance and Management Arrangements

Roles and responsibilities of the project’s governance mechanism:

The project will be co-implemented by UNDP (as lead) and UN Environment as two Implementing Agencies of GEF under different implementing modalities based on their respective policies and procedures. UNDP will be responsible for Components 1 and 3, whereas UN Environment will be responsible for Component 2 of the project. UNDP will be responsible to manage the funds related to PMU costs and allocation for Components 1 and 3, whereas, UN Environment will be responsible for managing funds allocated for component 2. The funding will be split at the source, with each agency getting its share directly from GEF. One PMU, consisting of Project Manager and Financial and Administrative Support, will be established to manage the whole project. The PMU will be responsible for the overall management and monitoring of project implementation and results.

The Implementing Partner (Executing Agency) for this project is the Ministry of Energy and Mineral Resource (MEMR) with the Directorate General of New Renewable Energy and Energy Conservation (DG-NREEC), under the same Ministry as the key technical partner. The Implementing Partner is accountable for managing this project, including the monitoring and evaluation of project interventions, achieving project outcomes, and for the effective use of project resources and is responsible for:

- Proper achievement of the objectives of the Project;

- Monitoring and evaluation of the project outputs and outcomes;

- Effective use of both international and national resources allocated to it;

- Timely availability of financing to support project implementation;

- Proper coordination among all project stakeholders; in particular national parties;

- Timely submission of all project reports, including work plans and financial reports;

- Approving and signing the multiyear work plan;

- Approving and signing the combined delivery report at the end of the year; and,

- Signing the financial report or the funding authorization and certificate of expenditures.

The Implementing Partner (or EA) will designate a high-ranking official as the National Project Director. He/She will assume responsibility for the Project on behalf of the National Government. The National Project Manager will report to the NPD.

The project organization structure is as follows:

National Project Organization Structure - ADLIGHT

Project Board

National Project Director (Nominated by MEMR)

Senior Beneficiary:

MEMR

Executive:

Minister, Ministry of Energy and Mineral Resources (MEMR)/DG-NREEC

Senior Supplier:

UNDP &

UN Environment

Project Assurance

UNDP & UN Environment

Project Manager

Project Management Unit

TEAM A

Support to Local Lighting Industry

TEAM B

Policy and Institutional Support

TEAM C

Market Penetration

Fig. 5: ADLIGHT Project Management Structure

The Project Board (also called Project Steering Committee) is responsible for making by consensus, management decisions when guidance is required by the National Project Director as Head of the Project Management Unit (PMU), including recommendation for UNDP/UN Environments approval of project plans and revisions. In order to ensure UNDP and UN Environment’s ultimate accountability, Project Board decisions should be made in accordance with standards that shall ensure management for development results, best value money, fairness, integrity, transparency and effective market penetration of EELs. In case a consensus cannot be reached within the Board, final decision shall rest with the UNDP Programme Manager.

Specific responsibilities of the Project Board include:

- Provide overall guidance and direction to the project, ensuring it remains within any specified constraints;

- Address project issues as raised by the project manager;

- Provide guidance on new project risks, and agree on possible countermeasures and management actions to address specific risks;

- Agree on project manager’s tolerances as required;

- Review the project progress, and provide direction and recommendations to ensure that the agreed deliverables are produced satisfactorily according to plans;

- Appraise the annual project implementation report, including the quality assessment rating report; make recommendations for the workplan;

- Provide ad hoc direction and advice for exceptional situations when the project manager’s tolerances are exceeded; and

- Assess and decide to proceed on project changes through appropriate revisions.

The composition of the Project Board must include the following roles:

Executive: The Executive is an individual who represents ownership of the project who will chair the Project Board and for the ADLIGHT Project, the Executive is:  Director of DG NREEC, Ministry of Energy and Mineral Resources (MEMR)/DG-NREEC.

The Executive is ultimately responsible for the project, supported by the Senior Beneficiary and Senior Supplier.  The Executive’s role is to ensure that the project is focused throughout its life cycle on achieving its objectives and delivering outputs that will contribute to higher level outcomes. The executive has to ensure that the project gives value for money, ensuring cost-conscious approach to the project, balancing the demands of beneficiary and suppler.

Specific Responsibilities: (as part of the above responsibilities for the Project Board)

- Ensure that there is a coherent project organisation structure and logical set of plans;

- Set tolerances in the AWP and other plans as required for the Project Manager;

- Monitor and control the progress of the project at a strategic level;

- Ensure that risks are being tracked and mitigated as effectively as possible;

- Brief relevant stakeholders about project progress;

- Organize and chair Project Board meetings.

Senior Supplier: The Senior Supplier is an individual or group representing the interests of the parties concerned which provide funding and/or technical expertise to the project (designing, developing, facilitating, procuring, implementing). The Senior Supplier’s primary function within the Board is to provide guidance regarding the technical feasibility of the project. The Senior Supplier role must have the authority to commit or acquire supplier resources required. If necessary, more than one person may be required for this role. Typically, the implementing partner, UNDP and/or donor(s) would be represented under this role. The Senior Suppler is: UNDP and UN Environment.

Specific Responsibilities (as part of the above responsibilities for the Project Board)

- Make sure that progress towards the outputs remains consistent from the supplier perspective;

- Promote and maintain focus on the expected project output(s) from the point of view of supplier management;

- Ensure that the supplier resources required for the project are made available;

- Contribute supplier opinions on Project Board decisions on whether to implement recommendations on proposed changes;

- Arbitrate on, and ensure resolution of, any supplier priority or resource conflicts.

Senior Beneficiary: The Senior Beneficiary is an individual or group of individuals representing the interests of those who will ultimately benefit from the project. The Senior Beneficiary’s primary function within the Board is to ensure the realization of project results from the perspective of project beneficiaries. The Senior Beneficiary role is held by a representative of the government or civil society. The Senior Beneficiary is: Ministry of Energy and Mineral Resource (MEMR).

The Senior Beneficiary is responsible for validating the needs and for monitoring that the solution will meet those needs within the constraints of the project. The Senior Beneficiary role monitors progress against targets and quality criteria. This role may require more than one person to cover all the beneficiary interests. For the sake of effectiveness, the role should not be split between too many people.

Specific Responsibilities (as part of the above responsibilities for the Project Board)

- Prioritize and contribute beneficiaries’ opinions on Project Board decisions on whether to implement recommendations on proposed changes;

- Specification of the Beneficiary’s needs is accurate, complete and unambiguous;

- Implementation of activities at all stages is monitored to ensure that they will meet the beneficiary’s needs and are progressing towards that target;

- Impact of potential changes is evaluated from the beneficiary point of view;

- Risks to the beneficiaries are frequently monitored.

The Project Board will be comprised of the following individuals:

Chairman: Director of DGNREEC/MEMR (National Project Director)

Members (Designated representatives from):

1. Min of Development Planning (Badan Perencanaan Pembangunan Nasional or BAPPENAS)

2. Public Procurement Agency – Lembaga Kebijakan Pengadaan

3. Financial Service Authority (Otoritas Jasa Keuangan or OJK)

4. Ministry of Trade

5. Ministry of Industry

The final membership of the Project Board will be finalized during the Inception workshop for the project.

The Project Board will meet at least quarterly or more frequently when necessary. The first Steering Committee meeting will convene following the approval of the Project Document in order to discuss the following matters:

- How to ensure successful implementation in line with the country’s energy self-sufficiency goals with the cooperation among all parties involved

- Strategic planning especially in the RE/EE advocacy and support for the needed energy act with its necessary policies, regulations and institutional framework

- Identifying other agencies or units to participate in Project Steering Committee meetings as resource persons on areas relevant to the meeting agenda.

- Maintain knowledge of project status to apply technical applications on the direction of the project

- How to ensure sustainability of the project and to monitor project risks and agree on next steps and follow-up activities.

The National Project Director (NPD) will take responsibility for the management and administration of the ADLIGHT Project. He or she will chair the Project Board (or also referred to as the National Steering Committee) designated by MEMR/DGNREEC, in the overall operation and management of the Project.   NPD will be responsible for calling the Board Meetings.

NPD will be supported by project management unit in undertaking its responsibilities. He or she will be ultimately responsible for the fiscal management of the project.    He or she will manage a staff of with multi-disciplinary capabilities in energy efficient lighting technology, communications, financing, marketing and more. In this role the NPD will be responsible for ensuring high staff performance and motivation. The NPD will directly and indirectly manage and coordinate multi-faceted local and international consultant contracts to ensure their timely completion and high quality. He or she will manage the monitoring and evaluation of both the overall project and its components. The NPD will be responsible for ensuring that project objective is being met in terms of budget and project outputs and must be prepared to recommend changes to the Project Board (NSC) to ensure that all outputs are realized over the project life.

The NPD will be the primary project advocate and representative.   In this role, he or she will meet regularly with stakeholders from the public, the lighting industry, Government of the Indonesia and international donors to further project objective.

The Project Management Unit (PMU) is responsible for the overall execution of the project and is supervised by the National Project Director designated by the Implementing Partner (MEMR/DGNREEC) and will work closely with the DGNREEC as the main Responsible Party. The PMU will coordinate closely with UN Environment for the project component and outputs that are to be administered by UN Environment and will consolidate the project reporting that will monitor and evaluate the progress of the respective activities in achieving the outputs and outcomes, especially in outputs that are inter-linked or related between the two groups of activities. The Implementing Partner in cooperation will establish the PMU for the overall coordination and management of the resources of this project.  The PMU will be organized to include the services of the

- Project Manager

- Finance & Administrative Associate

- 3 Component Coordinators

The PMU will be very helpful in providing management services by following the procedures of UNDP in close coordination with the UN Environment Team and funding agencies and the Financial Regulations and Rules of UNDP and UN Environment and providing for the required guidance to ensure best value for money, fairness, integrity, transparency, and effective market penetration of EEL products that UNDP adheres to.

The Project Manager will run the project on a day-to-day basis on behalf of the Implementing Partner within the constraints laid down by the Board. The Project Manager function will end when the final project terminal evaluation report, and other documentation required by the GEF and UNDP, has been completed and submitted to UNDP (including operational closure of the project). The Project Manager’s prime responsibility is to ensure that the project produces the results specified in the project document, to the required standard of quality and within the specified constraints of time and cost.

The Implementing Partner appoints a full time Project Manager who is not the staff of Implementing Partner and reports to NPD. The Project Manager will be appointed in close consultation with the UNDP and UN Environment the IAs of the project.

With PMU providing the supportive role, the Project Manager is responsible for:

- Provide direction and guidance to project team(s)/ responsible party (ies);

- Liaise with the Project Board to assure the overall direction and integrity of the project;

- Identify and obtain any support and advice required for the management, planning and control of the project;

- Responsible for project administration;

- Plan the activities of the project and monitor progress against the project results framework and the approved annual workplan;

- Mobilize personnel, goods and services, training and micro-capital grants to initiative activities, including drafting terms of reference and work specifications, and overseeing all contractors’ work;

- Monitor events as determined in the project monitoring schedule plan/timetable, and update the plan as required;

- Manage requests for the provision of financial resources by UNDP and UN Environment, through advance of funds, direct payments or reimbursement using the fund authorization and certificate of expenditures;

- Monitor financial resources and accounting to ensure the accuracy and reliability of financial reports;

- Be responsible for preparing and submitting financial reports to UNDP and UN Environment on a quarterly basis;

- Manage and monitor the project risks initially identified and submit new risks to the project board for consideration and decision on possible actions if required; update the status of these risks by maintaining the project risks log;

- Capture lessons learned during project implementation;

- Prepare the annual workplan for the following year; and update the Atlas Project Management module if external access is made available.

- Prepare the GEF PIR and submit the final report to the Project Board;

- Based on the GEF PIR and the Project Board review, prepare the AWP for the following year.

- Ensure the mid-term review process is undertaken as per the UNDP and UN Environment guidance and submit the final MTR report to the Project Board.

- Identify follow-on actions and submit them for consideration to the Project Board;

- Ensure the terminal evaluation process is undertaken as per the UNDP and UN Environment guidance and submit the final TE report to the Project Board.

The Project Manager, through the NPD, should coordinate with the pertinent program and operational units of the MEMR/DGNREEC and UN Environment Project Team on the follow-up of disbursements against obligations and other matters in relation to overall project implementation and management.

A Component Coordinator will be in charge of coordinating the activities and outputs of each of the three Components or Teams and making sure that the linked activities are inplemented effectively and timely.

Project Assurance:  UNDP and UN Environment will provide project assurance funded by the GEF Agency fee. UNDP, as Lead Implementing Agency, provides a three – tier supervision, oversight and quality assurance role – funded by the GEF agency fee – involving UNDP staff in Country Offices and at regional and headquarters levels. UN Environment will be responsible for assurance of component 2 through the GEF Task Manager based in Bangkok and UN Environment GEF team. Project Assurance must be totally independent of the Project Management function. The quality assurance role supports the Project Board and Project Management Unit by carrying out objective and independent project oversight and monitoring functions. This role ensures appropriate project management milestones are managed and completed. The Project Board cannot delegate any of its quality assurance responsibilities to the Project Manager.  This project oversight and quality assurance role is covered by the GEF Agency.

Additional quality assurance will be provided by the UNDP Regional Technical Advisor as needed.

Delineation of Roles and Responsibilities of UNDP and UN Environment

Considering that ADLIGHT is a national as well as a multi-country project being co-implemented by UNDP and UN Environment, there is a need to define the oversight roles and responsibilities among UNDP and UN Environment in the different aspects of governance and project management.

|  | UNDP (as Lead Agency) | UN Environment |
| --- | --- | --- |
| Outcomes and Outputs Coverage | Outcome 1 and 3 | Outcome 2 |
| Budgeting/Financial | USD 2,633,372 | USD 1,262,500 |
| Implementation | NIM | NIM |
| M&E | Standard reporting, e.g. APR/PIR, Quarterly Reports, Mid-term Review, Terminal Evaluation for assigned component, to be consolidated by PMU | Standard reporting, e.g. APR/PIR, Quarterly Reports, Mid-term Review, Terminal Evaluation for assigned component, to be consolidated by PMU |
| Post-project arrangements | As determined in the project plans for Outcome 1 and 3 | As determined in the project plans for Outcome 2 |

Implementation Arrangements for Component 2 by UN Environment under NIM

Component 2 budget and activities will be directly supervised by UN Environment. GEF will transfer the funds for Component 2 to UN Environment directly under an agreement. UN Environment will be responsible for supervising the execution of Component 2. The Project Manager will be responsible to report on progress and expenditures to UN Environment Task Manager for Component 2. The PIR report will jointly be prepared for the whole project led by UNDP and UN Environment will oversee the inputs for Component 2

Following UN Environment Financial Rules and Regulation and polices , UN Environment will sign a Project Cooperation Agreement (PCA) with MEMR as the executing entity of the Component 2.  Component 2 coordinator will be the technical expert responsible for technical execution of project and report to the Project Manager. UN Environment United For Efficiency (U4E) Programme will provide Technical Assistance for implementation of the Component 2 and work closely with the Project Manager through the Component coordinator.  The operational arrangements between UN Environment GEF team, MEMR and U4E shall be finalized leading up to the inception workshop post approval of the project.

UNDP Direct Project Services as Requested by Government

The UNDP, as GEF Agency for this project, will provide project management cycle services for the project as defined by the GEF Council. In addition, the Government of Indonesia may request UNDP direct services for specific projects, according to its policies and convenience.  The UNDP and Government of Indonesia acknowledge and agree that those services are not mandatory, and will be provided only upon Government request. If requested, the services would follow the UNDP policies on the recovery of direct costs. These services (and their costs) are specified in the Letter of Agreement (Annex J). As is determined by the GEF Council requirements, these service costs will be assigned as Project Management Cost, duly identified in the project budget as Direct Project Costs. Eligible Direct Project Costs should not be charged as a flat percentage. They should be calculated on the basis of estimated actual or transaction-based costs and should be charged to the direct project costs account codes: “64397- Services to projects – CO staff” and “74596 – Services to projects – GOE for CO”.

# Financial Planning and Management

The total resources for project implementation are USD 40,990,209. This is financed through a GEF grant of USD 3,895,872 (of which USD 2,633,372 is administered by UNDP and USD 1,262,500 is administered by UN Environment) representing the incremental resources needed achieve the Alternative Scenario under ADLIGHT. This will be supported by in-kind co-financing of USD 80,000 to be administered by UNDP and in-kind co-financing of USD 60,000 to be administered by UN Environment. Complementing these GEF, UNDP and UN Environment grants will be parallel co-financing valued at USD 37,094,337 as detailed below representing related project resources from the Government of Indonesia and the private sector. UNDP, as the lead GEF Implementing Agency, is responsible for the execution of the GEF resources and the cash co-financing transferred to UNDP for Component 1 and 3, while UN Environment will be responsible likewise for Component 2.  Financial reporting to GEF will be the overall responsibility of UNDP through the PIR to be assisted by the PMU, with inputs from UN Environment for Component 2.

Financial planning and management for resources administered by UN Environment shall follow UN Environment Financial Rules and Regulations.

Parallel co-financing:  The actual realization of project co-financing will be monitored during the mid-term review and terminal evaluation process and will be reported to the GEF. The planned parallel co-financing will be used as follows:

| Co-financing Source | Co-financing Type | Co-financing Amount ($) | Planned Activities/ Outputs | Risks | Risk Mitigation Measures |
| --- | --- | --- | --- | --- | --- |
| Government of Indonesia |  |  |  |  |  |
| - Ministry of Energy and Mineral Resource (DG-NREEC) | In-kind | 268,000 | All Outputs | Changes in policy direction, leaders and priorities | Close coordination and effective MEMR/DGNREEC/PMU project management and M&E |
|  | Cash | 13,277,000 |  |  |  |
|  | Subtotal | 13,545,000 |  |  |  |
| - Ministry of Energy and Mineral Resource (P3TEK – R&D Dept) | In-kind (lab) | 4,167,300 | Outputs 1.1, 2.1, 2.3, 2.5 | Budgeting constraints | Coordination with MEMR and PMU |
| - City of Solo/Surakarta (Mayor) Government | In-kind (Pilot EE Street light) | 10,015,037 | Outputs 3.1, 3.2, 3.3 | Budgeting constraints | Close coordination |
| - National Standardization Agency (Badan Standardisasi Nasional, BSN) | In-kind | 112,000 | Output 2.3 | Delays in the development and enforcement of MEPS | Close follow-up and facilitation as well as developing and issuing the SNI |
|  | cash | 50,000 |  |  |  |
|  | Subtotal | 162,000 |  |  |  |
| Sub-total (GOI) |  | 27,889,337 |  |  |  |
| Private Sector |  |  |  |  |  |
| - Indonesian Lighting Manufacturers Association – GAMATRINDO | Equity | 750,000 | All Outputs | Delays in implementation of Business Transformation Plans | Close coordination and active participation in all components |
| - Indonesian Lighting Manufactures Association - APERLINDO | Equity | 5,000,000 | All Outputs | Delays in implementation of Business Transformation Plans | Close coordination and active participation in all components |
| - Solarens (local LED manufacture) | Equity | 1,115,000 | Outputs 3.1, 3.2, 3.3 | Delays in implementation of Business Transformation Plans | Close coordination and active participation in all components |
| - Adyawinsa (local LED manufacture) | Equity | 2,000,000 |  |  |  |
| - Global Efficient Lighting Centre | In-kind | 200,000 | Output 2.3 | Delays in the development and enforcement of MEPS | Close follow-up and facilitation as well |
| Sub-total Private Sector |  | 9,065,000 |  |  |  |
| GEF Agency |  |  |  |  |  |
| - UN Environment | In-kind | 60,000 | All Outputs | None |  |
| - UNDP | In-kind | 80,000 | All Outputs | None |  |
| Sub-total GEF Agency |  | 140,000 |  |  |  |
| Total Co-financing |  | 37,094,337 |  |  |  |

Budget Revision and Tolerance (for the UNDP administered part of the GEF grant): As per UNDP requirements outlined in the UNDP POPP, the Project Board will agree on a budget tolerance level for each plan under the overall annual work plan allowing the Project Manager to expend up to the tolerance level beyond the approved project budget amount for the year without requiring a revision from the Project Board. Should the following deviations occur, the Project Manager and UNDP Country Office will seek the approval of the UNDP-GEF team as these are considered major amendments by the GEF:

  - Budget re-allocations among components in the project with amounts involving 10% of the total project grant or more;

  - Introduction of new budget items/or components that exceed 5% of original GEF allocation.

Any over expenditure incurred beyond the available GEF grant amount will be absorbed by non-GEF resources (e.g. UNDP TRAC or cash co-financing).

Refund to Donor (for the UNDP administered part of the GEF grant):  Should a refund of unspent funds to the GEF be necessary, this will be managed directly by the UNDP-GEF Unit in New York.

Project Closure (for the UNDP administered part of the GEF grant):  Project closure will be conducted as per UNDP requirements outlined in the UNDP POPP. On an exceptional basis only, a no-cost extension beyond the initial duration of the project will be sought from in-country UNDP colleagues and then the UNDP-GEF Executive Coordinator.

Operational completion (for the UNDP administered part of the GEF grant): The project will be operationally completed when the last UNDP-financed inputs have been provided and the related activities have been completed. This includes the final clearance of the Terminal Evaluation Report (that will be available in English) and the corresponding management response, and the end-of-project review Project Board meeting. The Implementing Partner through a Project Board decision will notify the UNDP Country Office when operational closure has been completed. At this time, the relevant parties will have already agreed and confirmed in writing on the arrangements for the disposal of any equipment that is still the property of UNDP.

Transfer or disposal of assets (for the UNDP administered part of the GEF grant): In consultation with the NIM Implementing Partner and other parties of the project, UNDP programme manager (UNDP Resident Representative) is responsible for deciding on the transfer or other disposal of assets. Transfer or disposal of assets is recommended to be reviewed and endorsed by the project board following UNDP rules and regulations. Assets may be transferred to the government for project activities managed by a national institution at any time during the life of a project. In all cases of transfer, a transfer document must be prepared and kept on file.

Financial completion (for the UNDP administered part of the GEF grant):  The project will be financially closed when the following conditions have been met:

  - The project is operationally completed or has been cancelled;

  - The Implementing Partner has reported all financial transactions to UNDP;

  - UNDP has closed the accounts for the project;

  - UNDP and the Implementing Partner have certified a final Combined Delivery Report (which serves as final budget revision).

The project will be financially completed within 12 months of operational closure or after the date of cancellation. Between operational and financial closure, the implementing partner will identify and settle all financial obligations and prepare a final expenditure report. The UNDP Country Office will send the final signed closure documents including confirmation of final cumulative expenditure and unspent balance to the UNDP-GEF Unit for confirmation before the project will be financially closed in Atlas by the UNDP Country Office.

# Total Budget and Work Plan

| Total Budget and Work Plan |  |  |  |
| --- | --- | --- | --- |
| Atlas Proposal or Award ID: | 00098585 | Atlas Primary Output Project ID: | 00101814 |
| Atlas Proposal or Award Title: | Advancing Indonesia’s Lighting Market to High Efficient Technologies (ADLIGHT) |  |  |
| Atlas Business Unit | UNDP Country Office - Indonesia |  |  |
| Atlas Primary Output Project Title | Advancing Indonesia’s Lighting Market to High Efficient Technologies (ADLIGHT) |  |  |
| UNDP-GEF PIMS No. | 5721 |  |  |
| Implementing Partner | Ministry of Energy and Mineral Resources (MEMR) |  |  |

| GEF Outcome/Atlas Activity | Responsible Party/ Implementing Agent | Fund ID | Donor Name | Atlas Budgetary Account Code | ATLAS Budget Description | Year 1 | Year 2 | Year 3 | Total | See Budget Note: |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Component/Outcome 1: Improved quality, energy efficient and affordable locally-produced EE Lighting (EEL) products and systems | UNDP | 62000 | GEF | 71200 | International consultants | 90,000 | 34,000 | 34,000 | 158,000 | 1 |
|  |  |  |  | 71300 | National consultants | 100,000 | 18,000 | 18,000 | 136,000 | 2 |
|  |  |  |  | 72100 | Contractual services-companies | 155,300 | 100,000 | 70,000 | 325,300 | 3 |
|  |  |  |  | 71600 | Travel | 119,440 | 33,250 | 33,250 | 185,940 | 4 |
|  |  |  |  | 75700 | Training, workshop and conference | 55,015 | 5,050 | 5,050 | 65,115 | 5 |
|  |  |  |  | 74200 | Audio Visual & Print Prod Costs | 110,000 | 15,000 | 50,000 | 175,000 | 6 |
|  |  |  |  | 74500 | Miscellaneous | 3,300 | 3,300 | 3,400 | 10,000 | 7 |
|  |  |  |  |  | Sub-total Outcome 1 | 633,055 | 208,600 | 213,700 | 1,055,355 |  |
| Component/Outcome 3: Increased penetration of high quality and efficient lighting | UNDP | 62000 | GEF | 71200 | International consultants | 31,500 | - | - | 31,500 | 8 |
|  |  |  |  | 71300 | National consultants | 35,000 | 35,000 | 35,000 | 105,000 | 9 |
|  |  |  |  | 71400 | Contractual services-Individual | - | - | - | - |  |
|  |  |  |  | 72100 | Contractual services-Companies | 125,000 | 85,000 | 85,000 | 295,000 | 10 |
|  |  |  |  | 71600 | Travel | 35,000 | 34,750 | 34,750 | 104,500 | 11 |
|  |  |  |  | 74100 | Professional services | - | - | - | - |  |
|  |  |  |  | 75700 | Training, workshop and conference | 50,000 | 50,000 | 50,000 | 150,000 | 12 |
|  |  |  |  | 74200 | Audio Visual & Print Prod Costs | 20,000 | 20,000 | 20,000 | 60,000 | 13 |
|  |  |  |  | 72200 | Equipment and furniture | 533,500 | 50,000 | 50,000 | 633,500 | 14 |
|  |  |  |  | 72800 | Information Technology Equipmt | 1,000 | 1,000 | 1,000 | 3,000 | 15 |
|  |  |  |  | 72500 | Supplies | - | - | - | - |  |
|  |  |  |  | 73300 | Rental of Information Technology Equipment | - | - | - | - |  |
|  |  |  |  | 74500 | Miscellaneous | 3,300 | 3,300 | 3,400 | 10,000 | 16 |
|  |  |  |  |  | Sub-total Outcome 3 | 834,300 | 279,050 | 279,150 | 1,392,500 |  |
| ALL COMPONENTS |  |  |  |  | TOTAL COMPONENT 2 and 3 | 1,467,355 | 487,650 | 492,850 | 2,447,855 |  |
| Project Management Cost |  |  |  |  |  |  |  |  |  |  |
| Project Management Cost (5% of Total All components) | UNDP | 62000 | GEF | 71200 | International consultants | 14,000 | 14,000 | 14,000 | 42,000 | 17 |
|  |  |  |  | 71300 | National consultants | 15,000 | 15,000 | 15,000 | 45,000 | 18 |
|  |  |  |  | 74596 | Services to projects-GOE | 15,005.20 | 15,005.20 | 15,005.20 | 45,015.60 | 19 |
|  |  |  |  | 74100 | Professional services | 7,000 | 7,000 | 7,000 | 21,000 | 20 |
|  |  |  |  | 71600 | Travel | 12,000 | 2,500 | 2,000 | 16,500 | 21 |
|  |  |  |  | 72500 | Supplies | 2,000 | 1,500 | 1,500 | 5,000 | 22 |
|  |  |  |  | 75700 | Training, Workshop & Conference | 7,500 | - | 3,501.40 | 11,001.40 | 23 |
|  |  |  |  |  | Sub-total PMC | 72,505.20 | 55,005.20 | 58,006.60 | 185,517 |  |
|  |  |  |  |  | TOTAL PROJECT (including PMC) | 1,539,860.20 | 542,655.20 | 550,856.60 | 2,633,372 |  |

Budget Notes:

| No. | Budget details |
| --- | --- |
|  | Outcome 1 |
| 1 | International consultancy services for needs analysis and provision of technical assistance to selected local EEL product manufacturers on the design and production of high efficiency lighting products and systems, preparation of business transformation plans and related capacity development and establishment of a EEL knowledge center and for allocated costs for Project Management (including allocated independent consultancy costs for MTR and TE for the Component). |
| 2 | Local consultancy services to support the international consultant for needs analysis and provision of technical assistance to selected local EEL product manufacturers on the design and production of high efficiency lighting products and systems, preparation of business transformation plans and related capacity development and waste disposal/recycling of retrofit lamps and for allocated costs for Project Management (including Project Manager, Financial Officer and other support staff as well as allocated MTR and TE costs for the Component).. |
| 3 | Periodic market surveys, assessment of needs for technical assistance and provision of technical advisory support to manufacturers and ESCOs |
| 4 | Travel costs for surveys, capacity development and technical support services |
| 5 | Capacity development, training/workshops for manufacturers and banking/financial institutions and business forums |
| 6 | Awareness programs and knowledge management for manufacturers, banks, and users for EEL |
| 7 | Operation and maintenance of project equipment, report preparation costs, reproduction of reports, sundry expenses, mailing and incidental supplies and expenses |
|  | Outcome 3 |
| 8 | International consultancy services for innovative financial model enabling accelerated penetration of advanced lighting systems, focusing on the development of ESCO business models and for allocated costs for Project Management (including allocated independent consultancy costs for MTR and TE for the Component). |
| 9 | Local consultants for technical and financial advisory services on innovative financial support schemes; development and implementation of appropriate ESCO model; development and implementation of EEL pilot demonstrations; awareness and promotional programs and for allocated costs for Project Management (including Project Manager, Financial Officer and other support staff as well as allocated MTR and TE costs for the Component). |
| 10 | Contractual services-Companies for support services in the implementation of pilot demos using ESCO business models to be contracted with professional groups in performance of energy consumption pre-audits, investment grade energy audits, preparation and legal services for EPC Contracts, MVE, metering and other professional services by service providers |
| 11 | Travel costs for field visits, FGDs, meetings, surveys, capacity development and technical support services |
| 12 | Training workshops on capacity development and implementation of pilot demonstrations using ESCO business model for local government municipalities and cities and pilot demonstration hosts; development and operationalization of an EEL awareness and promotional program and information support network system, database and website |
| 13 | Awareness programs and knowledge management for manufacturers, banks, and users for active market penetration campaigns, promotional activities, and information dissemination |
| 14 | Procurement of equipment and furniture for EEL lighting systems including the design, approval, capacity development and implementation of pilot demonstrations using ESCO business models as applied to buildings and street lighting |
| 15 | Support for hardware and software and other IT requirements in developing and implementing innovative financial support schemes, accelerated LED lamp deployment for buildings and for street lighting |
| 16 | Operation and maintenance of project equipment, report preparation costs, reproduction of reports, sundry expenses, mailing and incidental supplies and expenses |
|  | Project Management |
| 17 | Portion of independent consultant costs to undertake the project inception preparations, mid-term review and the terminal evaluation with remaining project management costs on international consultants allocated among the Components |
| 18 | Portion of the independent national consultant costs to undertake the project inception preparations, mid-term review and the terminal evaluation including that for Project Manager and Financial Officer with remaining project management costs for national consultants allocated among the Components. |
| 19 | Direct project costs as requested by the MEMR (NIM Implementing Partner) |
| 20 | Consultancy services for audit of project implementation |
| 21 | Supplementary travel cost for M&E and knowledge management for PMU |
| 22 | Supplies and other consumables for the PMU office |
| 23 | Inception Workshop and End-of-Project Conference on project accomplishment and related knowledge management and dissemination of results |

Budget for Component 2 - Improved conditions for fair market competition of EE lighting products, informed by robust policy and institutional framework  (to be managed by UN Environment)

|  | Amount (X 1,000 USD) |  |  |  |
| --- | --- | --- | --- | --- |
|  | Year 1 | Year 2 | Year 3 | Total |
| - HR |  |  |  |  |
| International Consultant (incl. U4E Tech. Expert) | 150.93 | 116.05 | 75.42 | 342.40 |
| National Consultant | 79.52 | 54.57 | 63.68 | 211.57 |
| Sub-Total HR | 230.45 | 170.62 | 139.10 | 553.97 |
| - Travel (including DSA) |  |  |  |  |
| International Consultant (incl. U4E Tech. Expert) | 31.35 | 29.55 | 22.859 | 83.75 |
| National Consultant | 6.94 | 4.77 | 4.90 | 16.61 |
| PMU (Component Coordinator 2 and National EE specialist) | 5.92 | 11.09 | 3.65 | 20.66 |
| Participants of stakeholder in national and international meetings | 51.37 | 86.98 | 78.67 | 217.01 |
| Sub-Total Travel | 95.58 | 132.38 | 110.07 | 338.03 |
| - DSA |  |  |  |  |
| International Consultant (incl. U4E Tech. Expert) |  |  |  |  |
| National Consultant |  |  |  |  |
| PMU |  |  |  |  |
| Participants international |  |  |  |  |
| Participants domestic |  |  |  |  |
| Sub-Total DSA |  |  |  |  |
| - Surveys / studies | 18.33 | 33.33 | 8.33 | 60.00 |
| - Equipment |  |  |  |  |
| Purchase of model digital based inspection hardware for product quality checks | 10.00 |  |  | 10.00 |
| - Publication | 13.33 | 26.67 | 20.00 | 60.00 |
| - Services | 101.00 | 31.00 |  | 132.00 |
| - Meetings / conferences | 41.57 | 20.00 | 10.93 | 72.50 |
| - Capacity building events | 7.20 | 11.40 | 17.40 | 36.00 |
| Total | 517.46 | 425.41 | 305.83 | 1,262.50 |
| Project Management |  |  |  | (in-kind UN Environment) |
| Component 2 Total incl. Project Management |  |  |  | 1,262.50 |

Summary of Funds:

|  | Amount Year 1 | Amount Year 2 | Amount Year 3 | Total |
| --- | --- | --- | --- | --- |
| GEF (administered by UNDP) | $1,539,860.20 | $542,655.20 | $550,856.60 | $2,633,372 |
| GEF (administered by UNEP) | $517,460 | $425,410 | $319,630 | $1,262,500 |
| Government of Indonesia | $12,136,039 | $12,136,038 | $3,617,260 | $27,889,337 |
| Private Sector | $5,339,000 | $1,863,000 | $1,863,000 | $9,065,000 |
| UNDP | $26,667 | $26,667 | $26,666 | $80,000 |
| UNEP | $20,000 | $20,000 | $20,000 | $60,000 |
| TOTAL | $19,579,026.20 | $15,013,770 | $6,397,413 | $$40,990,209.00 |

# Legal Context

The project document shall be the instrument envisaged and defined in the Supplemental Provisions (Annex R) to the Project Document, attached hereto and forming an integral part hereof, as “the Project Document”.

This project will be implemented by Ministry of Energy and Mineral Resources/ Directorate General of New-Renewable Energy and Energy Conservation (MEMR/DGNREEC) as “Implementing Partner” in accordance with its financial regulations, rules, practices and procedures only to the extent that they do not contravene the principles of the Financial Regulations and Rules of UNDP. Where the financial governance of an Implementing Partner does not provide the required guidance to ensure best value for money, fairness, integrity, transparency, and effective international competition, the financial governance of UNDP shall apply.

Any designations on maps or other references employed in this project document do not imply the expression of any opinion whatsoever on the part of UNDP concerning the legal status of any country, territory, city or area or its authorities, or concerning the delimitation of its frontiers or boundaries.

# Risk Management

Consistent with the Article III of the Supplemental Provisions to the Project Document, the responsibility for the safety and security of the Implementing Partner and its personnel and property, and of UNDP’s property in the Implementing Partner’s custody, rests with the Implementing Partner.  To this end, the Implementing Partner shall:

- put in place an appropriate security plan and maintain the security plan, taking into account the security situation in the country where the project is being carried;

- assume all risks and liabilities related to the Implementing Partner’s security, and the full implementation of the security plan.

UNDP reserves the right to verify whether such a plan is in place, and to suggest modifications to the plan when necessary. Failure to maintain and implement an appropriate security plan as required hereunder shall be deemed a breach of the Implementing Partner’s obligations under this Project Document.

The Implementing Partner agrees to undertake all reasonable efforts to ensure that no UNDP funds received pursuant to the Project Document are used to provide support to individuals or entities associated with terrorism and that the recipients of any amounts provided by UNDP hereunder do not appear on the list maintained by the Security Council Committee established pursuant to resolution 1267 (1999). The list can be accessed via http://www.un.org/sc/committees/1267/aq_sanctions_list.shtml.

Social and environmental sustainability will be enhanced through application of the UNDP Social and Environmental Standards (http://www.undp.org/ses) and related Accountability Mechanism (http://www.undp.org/secu-srm).

The Implementing Partner shall: (a) conduct project and programme-related activities in a manner consistent with the UNDP Social and Environmental Standards, (b) implement any management or mitigation plan prepared for the project or programme to comply with such standards, and (c) engage in a constructive and timely manner to address any concerns and complaints raised through the Accountability Mechanism. UNDP will seek to ensure that communities and other project stakeholders are informed of and have access to the Accountability Mechanism.

All signatories to the Project Document shall cooperate in good faith with any exercise to evaluate any programme or project-related commitments or compliance with the UNDP Social and Environmental Standards. This includes providing access to project sites, relevant personnel, information, and documentation.

The Implementing Partner will take appropriate steps to prevent misuse of funds, fraud or corruption, by its officials, consultants, responsible parties, subcontractors and sub-recipients in implementing the project or using UNDP funds.  The Implementing Partner will ensure that its financial management, anti-corruption and anti-fraud policies are in place and enforced for all funding received from or through UNDP.

The requirements of the following documents, then in force at the time of signature of the Project Document, apply to the Implementing Partner: (a) UNDP Policy on Fraud and other Corrupt Practices and (b) UNDP Office of Audit and Investigations Investigation Guidelines. The Implementing Partner agrees to the requirements of the above documents, which are an integral part of this Project Document and are available online at www.undp.org.

In the event that an investigation is required, UNDP has the obligation to conduct investigations relating to any aspect of UNDP projects and programmes. The Implementing Partner shall provide its full cooperation, including making available personnel, relevant documentation, and granting access to the Implementing Partner’s (and its consultants’, responsible parties’, subcontractors’ and sub-recipients’) premises, for such purposes at reasonable times and on reasonable conditions as may be required for the purpose of an investigation. Should there be a limitation in meeting this obligation, UNDP shall consult with the Implementing Partner to find a solution.

The signatories to this Project Document will promptly inform one another in case of any incidence of inappropriate use of funds, or credible allegation of fraud or corruption with due confidentiality.

Where the Implementing Partner becomes aware that a UNDP project or activity, in whole or in part, is the focus of investigation for alleged fraud/corruption, the Implementing Partner will inform the UNDP Resident Representative/Head of Office, who will promptly inform UNDP’s Office of Audit and Investigations (OAI). The Implementing Partner shall provide regular updates to the head of UNDP in the country and OAI of the status of, and actions relating to, such investigation.

UNDP shall be entitled to a refund from the Implementing Partner of any funds provided that have been used inappropriately, including through fraud or corruption, or otherwise paid other than in accordance with the terms and conditions of the Project Document.  Such amount may be deducted by UNDP from any payment due to the Implementing Partner under this or any other agreement.

Where such funds have not been refunded to UNDP, the Implementing Partner agrees that donors to UNDP (including the Government) whose funding is the source, in whole or in part, of the funds for the activities under this Project Document, may seek recourse to the Implementing Partner for the recovery of any funds determined by UNDP to have been used inappropriately, including through fraud or corruption, or otherwise paid other than in accordance with the terms and conditions of the Project Document.

Note:  The term “Project Document” as used in this clause shall be deemed to include any relevant subsidiary agreement further to the Project Document, including those with responsible parties, subcontractors and sub-recipients.

Each contract issued by the Implementing Partner in connection with this Project Document shall include a provision representing that no fees, gratuities, rebates, gifts, commissions or other payments, other than those shown in the proposal, have been given, received, or promised in connection with the selection process or in contract execution, and that the recipient of funds from the Implementing Partner shall cooperate with any and all investigations and post-payment audits.

Should UNDP refer to the relevant national authorities for appropriate legal action any alleged wrongdoing relating to the project, the Government will ensure that the relevant national authorities shall actively investigate the same and take appropriate legal action against all individuals found to have participated in the wrongdoing, recover and return any recovered funds to UNDP.

The Implementing Partner shall ensure that all of its obligations set forth under this section entitled “Risk Management” are passed on to each responsible party, subcontractor and sub-recipient and that all the clauses under this section entitled “Risk Management Standard Clauses” are included, mutatis mutandis, in all sub-contracts or sub-agreements entered into further to this Project Document

# Mandatory Annexes:

- Multi-year Work Plan

- Monitoring Plan

- Evaluation Plan

- GEF Core Indicators (s) at baseline

- Terms of Reference for Project Board, National Project Director, Project Manager and Component Coordinators

- UNDP Social and Environmental and Social Screening Template (SESP)

- UNDP Project Quality Assurance Report

- UNDP Risk Log

- Results of the capacity assessment of the project implementing partner and HACT micro assessment

- Additional agreements

  - Co-financing Letter

  - Country Office Support Service Agreement

- Descriptions of Demonstration Projects

- GHG Emission Reduction Estimates

- Annual Targets

- Gender Analysis and Action Plan

- Knowledge Management Strategy

- Stakeholder Engagement Plan

- ADLIGHT Problem Tree

- Supplemental Provisions to the Project Document: The Legal Context

Annex A: Multi Year Work Plan

The schedule of the ADLIGHT project outputs which are not shown in the Project Results Framework in Section VI is further detailed in the multi-year work plan as shown below.

| Outcomes//Outputs | Responsible Party | Year 1 |  |  |  |  | Year 2 |  |  |  |  | Year 3 |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Component/Outcome 1: Improved quality, energy efficient and affordable locally-produced EE Lighting (EEL) products and systems |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 1.1: Establishment of knowledge center and systems that helps manufacturers in their production planning and policy makers in reviewing enabling environment | MEMR/DG-NREEC |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 1.2: Adopted and implemented business transformation plans of selected local lighting manufacturers to produce high quality energy efficient LED lamps that can meet future MEPS | MEMR/DG-NREEC |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 1.3: Completed capacity development program for banking/financial institutions on the evaluation and financing of lighting industry modernization projects | MEMR/DG-NREEC |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Component/Outcome 2: Improved conditions for fair market competition informed by robust policy and institutional framework |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 2.1: Minimum Energy Performance Standards (MEPS) and energy labels in place for high energy efficient lighting products in line with the ASEAN regional approach | MEMR/DG-NREEC |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 2.2: Policy and guideline for public procurement of LED lighting products (residential, commercial and outdoor) developed and process for adaptation initiated, including waste disposal and recycling practices | MEMR/DG-NREEC |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 2.3: Regulatory mechanism for efficient lighting monitoring, verification and enforcement (MVE) including testing standards defined and process for notifying the implementation initated by relevant agencies at the national and local levels | MEMR/DG-NREEC |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 2.4: Completed capacity development for policy makers, enforcement & custom officials and other relevant government agencies on market control procedures | MEMR/DG-NREEC |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 2.5: Completed capacity development program for lamp testing laboratory personnel on LED testing | MEMR/DG-NREEC |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Component/Outcome 3: Increased penetration of high quality and efficient lighting |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 3.1: Development of an innovative financial model enabling accelerated penetration of advanced lighting systems, focusing on the development of ESCO business models | MEMR/DG-NREEC |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 3.2: Pilot demonstrations for accelerated LED lamp deployment in buildings and for street lighting in context of sustainable cities as well as in residential sector | MEMR/DG-NREEC |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 3.3: Implemented awareness and promotion program and information system explaining the benefits of high energy efficient lighting technologies taking into account gender specific aspects in developing and implementing the programmes | MEMR/DG-NREEC |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

Annex B: Monitoring Plan

The Project Manager will collect results data according to the following monitoring plan.

| Monitoring | Indicators | Description | Data source/Collection Method | Frequency | Responsible for data collection | Means of verification | Assumptions and Risks |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Project objective To increase the penetration of high quality energy-efficient lighting technologies in Indonesia through the transformation of the national market, thereby reducing electricity demand and the related greenhouse gas (GHG) emissions | - Cumulative electricity savings by EOP, GWh | Calculated as the difference between the business as usual energy consumption on lighting and the actual electricity consumption | - MEMR/DGNREEC and PNU reporting through M&E | Annually Reported in DO tab of the GEF PIR | MEMR/DGNREEC and PMU | - Monitoring reports from the industry and M&E reports through the UNDP-GEF APR/PIR system by MEMR and PMU in coordination with the LED manufacturers associations - Mid-term review and Terminal Evaluation Reports | - Petroleum products and electricity prices will be at levels that make energy efficiency projects, particularly energy efficient lighting (EEL), basically LED manufacturing and application, competitive and cost effective - Acceptance of the benefits and business opportunities resulting from the local manufacture and application of LED |
|  | - Cumulative CO2 emissions reduction, kt | Calculated from the cumulative electricity savings multiplied by the applicable emission factor for the year. | MEMR/DGNREEC and PNU reporting through M&E | Annually Reported in DO tab of the GEF PIR | MEMR/DGNREEC and PMU | - Monitoring reports from the industry and M&E reports through the UNDP-GEF APR/PIR system by MEMR and PMU in coordination with the LED manufacturers associations - Mid-term review and Terminal Evaluation Reports | - Manufacturers remain committed to improving the energy-efficiency and quality of products. - Manufacturers remain willing to share data. |
|  | - Number of women and men participating in capacity building trainings throughout the project | Calculated from survey results using the typical data regarding the pilot projects | MEMR/DGNREEC and PNU reporting through M&E | Annually Reported in DO tab of the GEF PIR | MEMR/DGNREEC and PMU | Reports on survey results and analysis at inception, mid-term and EOP | The design and installation of the EEL systems is well informed on women’s and men’s needs, preferences and habits in consumption and disposal of EEL technologies |
| Component/Outcome 1: Improved quality, energy efficient and affordable locally-produced EEL products and systems | - Efficiency of locally produced lighting systems increased, (lm/W) and Production cost decreased from baseline level (%) - Indoor Type - Outdoor Type | Calculated from the efficacy of lamps in terms of lumens/watt; Cost is calculated based on average unit cost of the product during the start of the project and in the succeeding 2 years of the project | Through industry association monitoring reports | Annually Reported in DO tab of the GEF PIR | MEMR/DGNREEC and PMU | Annual progress report from PMU and industry associations | - Local lighting manufacturers will take up the transformation of their facilities as viable investment in production techniques matching efficiency and affordability of locally produced EELs - Manufacturers remain committed to improving the energy-efficiency and quality of products. - Manufacturers remain willing to share data. |
|  | - Cumulative number of lighting manufacturers who received technical assistance on the design and production of high efficient lighting products and systems | Registered lighting manufacturers which were selected and qualified for support by the project | Through industry association monitoring reports | Annually | MEMR/DGNREEC and PMU | Annual progress report from PMU and industry associations | - Manufacturers remain committed to improving the energy-efficiency and quality of products. - Manufacturers remain willing to share data. |
|  | - Investment grade proposal for business transformation plans - Submitted by manufacturers - Approved by banks. | Documents on investment proposal submitted and approved with the necessary quality and completeness | Through reports by banks and verified by PMU | Reported in DO tab of the GEF PIR | MEMR/DGNREEC and PMU | Annual progress report from PMU and industry associations | - Manufacturers remain committed to improving the energy-efficiency and quality of products. - Manufacturers remain willing to share data. |
|  | - Ratio of women and men who believe they have the capacity to - Submit (local manufacturers) - Approve (banks) investment grade proposal for business transformation plans | Data collected through the market surveys | MEMR/DGNREEC and PMU reporting through M&E | Annually | MEMR/DGNREEC and PMU | Reports on survey results and analysis at inception, mid-term and EOP | - Periodic market surveys that are designed and to be implemented to target women and men separately and are distributed to both women and men gain the cooperation of the people and the industry associations |
| Component/ Outcome 2: Improved conditions for fair market competition informed by robust policy and institutional framework | - No. of policy documents at the national level, including Standard Minimum Quality and MEPS on LED and other relevant guidelines, developed and approved | Counting of the endorsed/approved policy documents on SNI, MEPS and labeling procedures | MEMR/DGNEERC and validated by PMU | Annually | MEMR/DGNREEC and PMU | Copy of the endorsed/approved policy documents on SNI, MEPS and labeling procedures | - Overall policy to cover MEPS, SNI guideline, market control MVE mechanisms and laboratory testing procedures can be developed and facilitated by the project for approval by the BSN and other authorized agencies within the timeframe of the project. - SNI and MEPS for LED lights both indoor and outdoor is a priority for the MEMR. - Indonesia is committed to abide to the ASEAN Plan of Action Energy Cooperation 2016-2025 (APAEC) which highlights regional harmonization of LED lighting standard (Activity 4.1 of the APAEC). |
|  | - No. of policy and guideline on LED procurement developed and implemented in E-catalogue and regular public procurement system | Counting of the policy guideline documents developed and implemented | MEMR/DGNEERC and validated by PMU | Reported in DO tab of the GEF PIR | MEMR/DGNREEC and PMU | Copy of the endorsed/approved policy and guidelines | The MEPS is approved before the EOP |
|  | - No. of comprehensive MVE Guideline and required implementing rules and regulations for including resolving custom dispute and legality of products developed and implemented | Counting of the policy guideline documents developed and implemented | MEMR/DGNEERC and validated by PMU | Annually | MEMR/DGNREEC and PMU | Documentation of the design and operating manual of the software and the necessary training | The MEPS is approved before the EOP |
|  | - Ratio of women and men employees in relevant government institutions who believe they have the capacity to monitor verify and enforce high quality efficiency lighting systems | Women’s and men’s perceived capacity to monitor verify and enforce high quality efficiency lighting systems | MEMR/DGNEERC and validated by PMU | Annually | MEMR/DGNREEC and PMU | Results from evaluation forms for the trainings and monitoring reports based on stakeholder interviews | Women and men have actively participated in the capacity building activities on monitoring verifying and enforcing high quality efficiency lighting systems MVE Guidelines have been developed and implemented |
| Component/ Outcome 3: Increased penetration of high quality and efficient lighting | Cumulative no. of innovative financial support schemes developed to accelerate penetration of EE lighting systems | Counting of documents on financial support mechanisms that have been developed | MEMR/DGNEERC and validated by PMU | Reported in DO tab of the GEF PIR | MEMR/DGNREEC and PMU | Copy of the endorsed/approved policy and guidelines on financial support schemes | Banks and financial institutions are convinced about the business potential of manufacturing and market for LED systems |
|  | - Cumulative no. of pilot demonstrations completed and replication plans developed and approved for implementation | Counting of pilot demonstration and replication plans that were developed and approve | MEMR/DGNEERC and validated by PMU | Annually | MEMR/DGNREEC and PMU | MEMR Reports on construction and operation of the demo units an dplans for relicaiton. | Banks and financial institutions are convinced about the business potential of manufacturing and market for LED systems |
|  | - Number of stakeholders engaged - municipalities - clients (project developers/ building owners) - technology providers - financial institutions | Calculated from survey results using the typical data regarding the pilot projects | MEMR/DGNEERC and validated by PMU | Annually | MEMR/DGNREEC and PMU | Reports on survey results and analysis at inception, mid-term and EOP | The design and installation of the EEL systems is well informed on women’s and men’s needs, preferences and habits in consumption and disposal of EEL technologies The design and implementation of the awareness raising program has considered women’s and men’s information needs on EEL systems and preferred channels for information sharing |
|  | - Women’s and men’s level of satisfaction with EEL systems provided (reliability, affordability, convenience, efficiency) | Calculated from survey results using the typical data regarding the pilot projects | MEMR/DGNEERC and validated by PMU | Reported in DO tab of the GEF PIR | MEMR/DGNREEC and PMU | - Reports on workshops and promotional events conducted and on participants training evaluation. - Letters of interest from FI, technology providers and municipalities | Banks and financial institutions are convinced about the business potential of manufacturing and market for LED systems |
| Mid-term GEF Core Indicators (if FSP project only) | N/A | N/A | Standard GEF Core Indicators available at www.thegef.org Baseline GEF Core Indicators Tool included in Annex. | After 2nd PIR submitted to GEF | MEMR/DGNREEC and PMU) | Completed GEF Core Indicators | Delays in implementation Delays in hiring international and local consultants |
| Terminal GEF Core Indicators | N/A | N/A | Standard GEF Core Indicators available at www.thegef.org Baseline GEF Core Indicators included in Annex. | After final PIR submitted to GEF | MEMR/DGNREEC and PMU) | Completed GEF Core Indicators | Reports from the industry and consuming sectors are not submitted nor analyzed for the targeted energy saving and GHG reduction |
| Mid-term Review (if FSP project only) | N/A | N/A | To be outlined in MTR inception report | Submitted to GEF same year as 3rd PIR | Independent evaluator | Completed MTR | Delays in implementation Delays in hiring international and local consultants |
| Environmental and Social risks and management plans, as relevant. | N/A | N/A | Updated SESP and management plans | Annually | Project Manager UNDP CO | Updated SESP | Lack of data and information on actual experience |

Annex C: Evaluation Plan

| Evaluation Title | Planned start date Month/year | Planned end date Month/year | Included in the Country Office Evaluation Plan | Budget for consultants | Other budget (i.e. travel, site visits etc…) | Budget for translation |
| --- | --- | --- | --- | --- | --- | --- |
| Mid Term review | September 2019 | December 2019 | Yes | USD 35,000 | USD 5,000 | Not needed |
| Terminal Evaluation | September 2021 | December 2021 | Yes | USD 35,000 | USD 5,000 | Not needed |
| Total evaluation budget |  |  |  | USD 70,000 |  |  |

Annex D: GEF-7 Core Indicators (s) at baseline

Interim Offline Reporting Template for GEF-7 Core Indicators

5721 Indonesia

Baseline // Sept 2018

Contents

Core Indicator 6: Greenhouse gas emissions mitigated (metric tons of carbon dioxide equivalent)	107

Core Indicator 11: Number of direct beneficiaries disaggregated by gender as co-benefit of GEF investment	109

Core Indicator 6: Greenhouse gas emissions mitigated (metric tons of carbon dioxide equivalent)

| GHG emission type | Metric tons CO2-eq (expected at PIF) | Metric tons CO2-eq (expected at CEO ER) | Metric tons CO2-eq (expected at MTR) | Metric tons CO2-eq (expected at TE) |
| --- | --- | --- | --- | --- |
| Lifetime direct project GHG emissions mitigated | n/a | 548,776 |  |  |
| Lifetime direct post-project emissions mitigated |  | N/A (no financial mechanisms) |  |  |
| Lifetime indirect GHG emissions mitigated |  | 1,097,533 |  |  |

Figure at a given stage must be the sum of all figures reported under the first two sub-indicators (6.1 and 6.2) for that stage.

6.1 Carbon sequestered or emissions avoided in the sector of Agriculture, Forestry and Other Land Use

| GHG emission type | Ha (expected at PIF) | Metric tons CO2-eq (baseline at PIF) | Ha (expected at CEO ER) | Metric tons CO2-eq (baseline at CEO ER) | Ha (expected at MTR) | Metric tons CO2-eq (above baseline at MTR) | Ha (expected at TE) | Metric tons CO2-eq (above baseline at TE) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Lifetime direct project GHG emissions mitigated | n/a |  |  |  |  |  |  |  |
| Lifetime direct post-project emissions mitigated |  |  |  |  |  |  |  |  |
| Lifetime indirect GHG emissions mitigated |  |  |  |  |  |  |  |  |
| Anticipated year | --- |  | --- |  | --- |  | --- |  |

6.2 Emissions avoided

| GHG emission type | Metric tons CO2-eq (baseline at PIF) | Metric tons CO2-eq (baseline at CEO ER) | Metric tons CO2-eq (above baseline at MTR) | Metric tons CO2-eq (above baseline at TE) |
| --- | --- | --- | --- | --- |
| Lifetime direct project GHG emissions mitigated | n/a | 548,776 |  |  |
| Lifetime direct post-project emissions mitigated |  | N/A (no financial mechanisms) |  |  |
| Lifetime indirect GHG emissions mitigated |  | 1,097,533 |  |  |
| Anticipated year |  | 2020 |  |  |

6.3 Energy saved (megajoules)

| Type of Intervention | MJ (expected at PIF) | MJ (expected at CEO Endorsement) | MJ (achieved at MTR) | MJ (achieved at TE) |
| --- | --- | --- | --- | --- |
| Cumulative electricity savings by EOP | n/a | 278,820,000 (77.45 GWh) |  |  |

Add rows as needed.

6.4 Increase in installed renewable energy capacity per technology (megawatts).

| Type of Renewable Energy | MW (entered at PIF) | MW (entered at CEO Endorsement) | MW (entered at MTR) | MW (entered at TE) |
| --- | --- | --- | --- | --- |
| [biomass, geothermal, ocean, small hydro, solar photovoltaic, solar thermal, wind power, and storage] | n/a |  |  |  |

Add rows as needed.

Core Indicator 11: Number of direct beneficiaries disaggregated by gender as co-benefit of GEF investment

|  | Total number (expected at PIF) | Total number (expected at CEO Endorsement) | Total number (achieved at MTR) | Total number (achieved at TE) |
| --- | --- | --- | --- | --- |
| Women | n/a | 60 |  |  |
| Men |  | 140 |  |  |
| Total |  | 200 |  |  |

Annex E: Terms of Reference for Project Manager, Component Coordinators, Finance and Administrative Associate

- Project Manager (PM)

Duty Station: 				Jakarta with travel to other places as required.

Duration of assignment: 		12 person-months with possible extension (Full-time).

Direct Supervisor:	National Project Director

Responsibilities and Duties:

The primary task of the PM is to plan, organize and implement the ADLIGHT project under the direction of the National Project Director. He/she will be responsible for in management of input mobilization and day-to-day project operations including timely resolution of issues, problems or bottlenecks. He/she will supervise the technical and administrative staff under the PMU to be established under supervision of National Project Director designated by MEMR/DGNREEC, in close coordination with the UNDP GEF Regional Technical Advisor in Regional Office in Bangkok, UNDP Indonesia CO and UN Environment Task Manager in Bangkok. The PM should have multidisciplinary capabilities in energy efficient lighting (EEL) policy and institutional support development, communication and awareness; technical capacity development; energy efficiency services provision support; financing; and demonstration. To assume this overall responsibility, the specific tasks of the PM are as follows:

- Prepare, update, and submit the required work plan and reports to UNDP Indonesia CO Director for clearance timely and with satisfactory quality, including: Annual Work Plan (AWP), Quarterly Work Plan (QWP), Annual Project Reports (APR), GEF Project Implementation Review (PIR) Report, the Quarterly Progress Reports (QPR), and the Final Project Reports as scheduled;

- Finalize detailed ToRs for key outputs (i.e. personnel, consultants, sub-contractors, training, and procurements), within assistance from the International and National Senior Technical Advisers, and submit to NPD and UNDP Indonesia CO for clearance and approval;

- Take responsibility for monitoring the overall progress and use of the resources of all outputs and initiative corrective actions if necessary;

- Assume direct responsibility for managing the project budget on behalf of the NPD, ensuring that:

  - Project funds are made available when needed, and are disbursed properly;

  - Accounting records and supporting documents are kept;

  - Required financial reports are prepared;

  - Financial operations are transparent and financial procedures/regulations, in coordination with PMU, under a National Implementation Modality (NIM) as maybe adopted for ADLIGHT project;

  - Project Management is ready to stand up audit at any time.

- Assume direct responsibility for managing the physical resources (e.g. vehicles, office, equipment, furniture, stationary...) provided to the project by UNDP;

- Keep record and update the Project issues and risks and recommend necessary actions to NPD to effectively cope with identified risks, and coordinate the implementation of the approved risk mitigation actions;

- Liaison and coordinate the implementation of all project partnership agreements to ensure that partners implement the project components in a collaborative manner with the Project quarterly and annual work plan;

- Liaison with UNDP Indonesia CO or designated quality assurance personnel on the project quality management issues;

- Supervise the project staff and local or international experts/consultants working for the project;

- Provide back-stopping support for administrative work of the Project Management Unit if necessary;

- Implement, monitor and report on project’s Gender Action Plan and Stakeholder Engagement Plan and

- Organize the Inception Workshop, tripartite meetings and NSC meetings as well as evaluation missions in coordination with UNDP/UN Environment.

Qualifications:

- Minimum of Master's Degree in management, administration, economics, or any other relevant fields with engineering background.

- At least 5 years of proven track record on national or international project management experience, and at least three years of experience in energy project;

- Track record of, or proven experience in successful contract management, supervision and reporting skills;

- Excellent English proficiency, both in written and spoken,

- Knowledgeable about Indonesia’s energy policies, EE programs and Indonesia’s administrative structures;

- Familiar with technical assistance projects and GEF/UNDP/UN Environment projects in Indonesia; and

- Highly self-motivated, with good leadership skills.

- Previous experience in analyzing gender sensitive data and incorporating gender aspects in energy project is considered as an asset

- Finance and Administrative Associate

Duty Station: 				Jakarta with travel to other places as required.

Duration of assignment: 		12 person-months with possible extension (full time).

Direct Supervisor:		Project Manager

The Project Management Unit (PMU) will be established and be supervised by UNDP CO, in close coordination with the MEMR/DGNREEC. It will be composed of technical and administrative staff to be hired by combined resources of GEF and co-financing under the ADLIGHT Project.

Responsibilities and Duties:

The Finance and Administrative Associate shall be responsible for staff support in (i) financial management, (ii) procurement, (iii) administrative and operational backstopping, (iv) facilitation of knowledge management, document storage and sharing, and (v) other support activities to the operations of PMU towards ensuring the smooth functioning of administrative systems under the project. Specifically, he/she will be responsible for the following tasks:

- Prepare requests for advance of funds and/or direct payments as maybe instructed by the Deputy Project Manager and approved by the Project Manager

- Monitor budget expenditures and maintain a proper record of approved project budgets and their revisions;

- Prepare proposals for budget revisions;

- Prepare and submit expenditure and program budget status reports;

- Respond to queries with respect to financial aspects of the program, liaise with UNDP appointed and external auditors wherever required;

- Undertake other financial and administrative tasks on an ad hoc basis.

- Support management of procurement of equipment, supplies and services and arrange for equipment maintenance and insurance as required and asset management as per UNDP guidelines

- Maintain contacts with UNDP CO and Implementing Partners on a variety of the operational issues;

- Maintain records on all project personnel/national consultants and their respective status (contracts, ToRs, time and attendance – if appropriate, etc.) in accordance with accepted policies and procedures

- Carry out the administrative system and procedures consistent with UNDP’s National  Implementation Modality

- Provide secretariat support to workshops, seminars and trainings, monitoring, evaluation and information dissemination.

Qualification and Experience:

- Bachelor Degree in accounting or financing,

- At least 5-years of experience as accountant, administration, preferably with UNDP/GEF project;

- Experience in project management such as in meeting deadlines, timely submission of acceptable deliverables, etc.;

- Good English communication skills, both written and verbal;

- Knowledge of the Atlas or any similar systems;

- With satisfactory skills on the use of office software packages such as MS Word, Excel and Power Point, etc.; and

- Good interpersonal skills.

- Component Coordinator

Duty Station: 			Jakarta with travel to other places as required.

Duration of assignment: 	12 person-months with possible extension (full time).

Direct Supervisor:		Project Manager

The primary role of the Component Coordinator is to manage and coordinate the implementation of

various capacity development, enabling environment and technical assistance activities that will

be carried out under each project component. He/She will assist the PM in ensuring quality and

timeliness of activities and delivery of outputs. He/She will be based at the MEMR/DGNREEC.

Responsibilities and Duties:

The Component Coordinator shall report directly to the Project Manager (PM) and shall be responsible for:

- Managing and coordinating the implementation of all component activities to ensure the maintenance of quality and timeliness, and delivery of outputs under the component and in consonance with linked activities in other project components in producing common outputs.

- Liaising and working closely with the project partners and beneficiaries under the component consistent with the agreed partnership arrangements towards common project goals

- Assist the NPM in reporting regularly to the Project Board/NSC on the project’s progress

- Liaising with designated focal points from UNDP and other stakeholders, through the PM, indicating any estimated changes to the work plan, and proposing a budget revision when appropriate

- Ensuring that the requisite allocations for the component are available in accordance with the agreed budget and established schedules of payment, if any, in consultation with the PM, MEMR/DGNREEC and UNDP

- Working closely with key stakeholders in the drafting and preparation of relevant Terms of

- Reference for local consultants.

- Monitoring the project component implementation performance, particularly on the delivery of outputs.

- Preparing progress and financial reports of the project component when required.

- Make use of the project’s accounting system to ensure accuracy and reliability of financial

- Reporting for the component

- Active involvement in the preparation of relevant knowledge products (including publications

- and reports) involved in the component

- Provision of the necessary inputs for the application of the ATLAS External User system, assisting in creating requisitions and vouchers, and other relevant ATLAS processes

- Coordinating the management and implementation of activities of the project component as set out in the project document and recommending any such modifications/revisions as may be necessary to the PMU through the PM;

- Provision of inputs in the preparation of the annual work plan (AWP) and budget of the

- project component and its timely submission to the PM;

- Provision of inputs and assistance in the preparation of regular progress reports for the component to the local implementing agency, MEMR/DGNREEC and UNDP; and,

- Assisting the PM in reporting to the NSC the status and progress of the project component and seek appropriate recommendation if required.

Qualification and Experience:

- Advanced Degree in Mechanical/Electrical/Civil Engineering or Architecture or any other science-based background

- Possess a professional qualification or a member of an acknowledged professional organization or society.

- At least 5 years extensive working experience in the field of energy efficiency and possesses a strong knowledge of the local BSEEP industry and scenario.

- Extensive experience in project management with adequate exposure to financial management.

- Have a good command of the English language.

Annex F: UNDP Social and Environmental and Social Screening Template (SESP)

Project Information

| Project Information |  |
| --- | --- |
| - Project Title | Advancing Indonesia’s Lighting Market to High Efficient Technologies (ADLIGHT) |
| - Project Number | PIMS 5721 |
| - Location (Global/Region/Country) | INDONESIA |

Part A. Integrating Overarching Principles to Strengthen Social and Environmental Sustainability

QUESTION 1: How Does the Project Integrate the Overarching Principles in order to Strengthen Social and Environmental Sustainability?

Briefly describe in the space below how the Project mainstreams the human-rights based approach

The project was designed and will be implemented with due consideration of human rights principles, through engagement of the concepts of equality in the dissemination of knowledge and sharing of benefits. ADLIGHT will implement activities that will be promoting energy efficiency activities in high-energy consuming sector, such as public buildings, thus more energy can be saved and distributed to more households/industries. In the process of selection and implementation of energy efficiency projects that will be demonstrated in the pilot province, participatory approach and free, prior and informed consent (FPIC) process will be conducted by involving stakeholders that will be affected by the projects. The implementing partner as well as the project partners acknowledge human rights practices under international law and the application of human rights-related standards.

Briefly describe in the space below how the Project is likely to improve gender equality and women’s empowerment

The ADLIGHT project includes gender mainstreaming, as appropriate, to be gender responsive or gender transformative, in its implementation strategies and activities in advancing the application of EELs in the country, by means of: - Increase in participation and involvement of women (compared to the baseline level at inception) in the training, surveys, capacity building and dissemination activities for the component’s activities in the business transformation plans in the manufacturers and the support groups in terms of communication, information and educational activities on energy efficiency for both women and men. - Increase of women (compared to the baseline level at inception) in public participation as a result of the training, capacity building and awareness activities from the planning stage through implementation, monitoring and evaluation, e.g., reporting malfunction in street lighting, buildings and other applications. - Considering that women have more security concerns at night, they should be involved in the project particularly in the benefits and environmental impacts of EELs. For the pilot demonstration of the RE technologies, particularly in the outer islands, the project will make sure that sufficient consultations are conducted with women and that their participation in working groups will be encouraged. The proposed GEF project will also involve women working in both management and technical departments of the MEMR and related stakeholder agencies/institutions who can play important roles in the design, development and implementation of various activities of ADLIGHT. The ADLIGHT project considered the government National Gender Policy. UNDP Indonesia in its capacity as the co-implementor of the ADLIGHT project has adopted its Gender Strategy and Action Plan that guides its gender programs for the period 2017-2020. During the project implementation, updates on relevant gender mainstreaming policy and guidelines shall be incorporated in the Project’s action plans and strategies to be reviewed annually.

Briefly describe in the space below how the Project mainstreams environmental sustainability

Sustainability of the project impact will be ensured through the leadership of MEMR in cooperation with all the project stakeholders and with the provincial government which were selected to host the project’s pilot demonstrations. Their mitigation programs and administrative functions are geared towards promoting and supporting energy efficiency implementation as a key for environmental and development agenda. Enforcement of clear supporting regulatory and institutional system for EE investment, engagement of private sector, presence of local capacity to operate and maintain the EE lighting infrastructure and operational EE project financing mechanism are also other key factors ensuring sustainability of project impact. The project activities are designed in a way that encourages scale up and replication building on the experiences in the pilot demonstrations for buildings and street lighting. The project will support the Government of Indonesia in integrating the mitigation program as part of development agenda through Local Energy Planning (RUED). Thus, annually the mitigation actions will be planned and budgeted. Secondly, the scale up is also expected to result from establishment of enabling environment for effectively implementing the Business Transformation Plans, capacity building, MEPS/SNI development and promotional activities to bolster the market penetration of EE Lighting in the target sectors. The scale up and replication in other provinces are also expected to result from the piloting experience replication with the leadership of MEMR/DGNEERC.

Part B. Identifying and Managing Social and Environmental Risks

| QUESTION 2: What are the Potential Social and Environmental Risks? Note: Describe briefly potential social and environmental risks identified in Attachment 1 – Risk Screening Checklist (based on any “Yes” responses). If no risks have been identified in Attachment 1 then note “No Risks Identified” and skip to Question 4 and Select “Low Risk”. Questions 5 and 6 not required for Low Risk Projects. | QUESTION 3: What is the level of significance of the potential social and environmental risks? Note: Respond to Questions 4 and 5 below before proceeding to Question 6 |  |  |  | QUESTION 6: What social and environmental assessment and management measures have been conducted and/or are required to address potential risks (for Risks with Moderate and High Significance)? |  |
| --- | --- | --- | --- | --- | --- | --- |
| Risk Description | Impact and Probability (1-5) | Significance (Low, Moderate, High) | Comments |  | Description of assessment and management measures as reflected in the Project design. If ESIA or SESA is required note that the assessment should consider all potential impacts and risks. |  |
| Potential pollution results in the generation of waste (both hazardous and non-hazardous) from replaced fluorescent lamps/CFL and other conventional lights and particularly, mercury content and sharp cladding and bulb parts of these lamps. (SES Principle 3, standard 7 Pollution, q1, q2, q3) | I = 3 P = 5 | Moderate | Proper waste management actions will be followed to ensure obsolete energy lamp parts as well as mercury contained therein is properly disposed of. |  | During project formulation (PPG phase), an assessment of available energy equipment and extent of replacement was undertaken. A strategy to manage waste/obsolete energy equipment and lamps will be developed so as to avoid potential pollution from waste lamps, and particularly mercury from replaced fluorescent lamps/CFL. The project’s Activity 2.4.5: Design, planning and conduct of training on waste management and recycling of components and materials of conventional lighting replaced by LED has been included to address this issue. |  |
| The project can potentially have adverse impacts on gender equality and/or the situation of women and girls in case the activities related to LED promotion and training/capacity building are skewed towards male participation. (SES Principle 2 Gender, q1, q2) | I = 3 P = 1 | Low |  |  | The professional job capacity development interventions of the project will be designed in such a way that equal opportunities exist for all genders and ages. By doing this, qualified men and women will benefit and this will contribute to the improvement and promotion of gender equality. This will also improve the number of qualified and capable women in Indonesia in technical areas such as the energy efficient lighting sector. The monitoring and evaluation of the project activities will include tracking a number of human development indicators, and among them would be gender equity, like the number of trained and employed women in energy efficient lighting sector. |  |
|  | QUESTION 4: What is the overall Project risk categorization? |  |  |  |  |  |
|  | Select one (see SESP for guidance) |  |  |  |  | Comments |
|  | Low Risk |  |  | ☐ |  |  |
|  | Moderate Risk |  |  |  |  | The project’s Activity 2.4.5: Design, planning and conduct of training on waste management and recycling of components and materials of conventional lighting replaced by LED has been included to address this issue and ensure effective waste management and disposal. Gender considerations are included throughout all project activities. |
|  | High Risk |  |  | ☐ |  |  |
|  | QUESTION 5: Based on the identified risks and risk categorization, what requirements of the SES are relevant? |  |  |  |  |  |
|  | Check all that apply |  |  |  |  | Comments |
|  | Principle 1: Human Rights |  |  | ☐ |  |  |
|  | Principle 2: Gender Equality and Women’s Empowerment |  |  | √ |  | Participation of women need to be encouraged in the project’s gender mainstreaming, as appropriate, to be gender responsive or gender transformative, in its implementation strategies and activities in advancing the application of EELs in the country. The activity areas include surveys, information dissemination, planning, demonstration, monitoring and reporting or almost in all areas of the project. |
|  | 1. Biodiversity Conservation and Natural Resource Management |  |  | ☐ |  |  |
|  | 2. Climate Change Mitigation and Adaptation |  |  | ☐ |  |  |
|  | 3. Community Health, Safety and Working Conditions |  |  | ☐ |  |  |
|  | 4. Cultural Heritage |  |  | ☐ |  |  |
|  | 5. Displacement and Resettlement |  |  | ☐ |  |  |
|  | 6. Indigenous Peoples |  |  | ☐ |  |  |
|  | 7. Pollution Prevention and Resource Efficiency |  |  | √ |  | Potential pollution and risks from hazardous and non-hazardous waste materials from replaced fluorescent lamps/CFL and other conventional lighting systems and accessories particularly mercury content and sharp glass bulb parts need to be managed and proper disposal system be implemented |

Final Sign Off

| Signature | Date | Description |
| --- | --- | --- |
| QA Assessor |  | UNDP staff member responsible for the Project, typically a UNDP Programme Officer. Final signature confirms they have “checked” to ensure that the SESP is adequately conducted. |
| QA Approver |  | UNDP senior manager, typically the UNDP Deputy Country Director (DCD), Country Director (CD), Deputy Resident Representative (DRR), or Resident Representative (RR). The QA Approver cannot also be the QA Assessor. Final signature confirms they have “cleared” the SESP prior to submittal to the PAC. |
| PAC Chair |  | UNDP chair of the PAC. In some cases PAC Chair may also be the QA Approver. Final signature confirms that the SESP was considered as part of the project appraisal and considered in recommendations of the PAC. |

SESP Attachment 1. Social and Environmental Risk Screening Checklist

| Checklist Potential Social and Environmental Risks |  |
| --- | --- |
| Principles 1: Human Rights | Answer (Yes/No) |
| 1. Could the Project lead to adverse impacts on enjoyment of the human rights (civil, political, economic, social or cultural) of the affected population and particularly of marginalized groups? | No |
| 2. Is there a likelihood that the Project would have inequitable or discriminatory adverse impacts on affected populations, particularly people living in poverty or marginalized or excluded individuals or groups? | No |
| 3. Could the Project potentially restrict availability, quality of and access to resources or basic services, in particular to marginalized individuals or groups? | No |
| 4. Is there a likelihood that the Project would exclude any potentially affected stakeholders, in particular marginalized groups, from fully participating in decisions that may affect them? | No |
| 5. Is there a risk that duty-bearers do not have the capacity to meet their obligations in the Project? | No |
| 6. Is there a risk that rights-holders do not have the capacity to claim their rights? | No |
| 7. Have local communities or individuals, given the opportunity, raised human rights concerns regarding the Project during the stakeholder engagement process? | No |
| 8. Is there a risk that the Project would exacerbate conflicts among and/or the risk of violence to project-affected communities and individuals? | No |
| Principle 2: Gender Equality and Women’s Empowerment |  |
| 1. Is there a likelihood that the proposed Project would have adverse impacts on gender equality and/or the situation of women and girls? | Yes |
| 2. Would the Project potentially reproduce discriminations against women based on gender, especially regarding participation in design and implementation or access to opportunities and benefits? | Yes |
| 3. Have women’s groups/leaders raised gender equality concerns regarding the Project during the stakeholder engagement process and has this been included in the overall Project proposal and in the risk assessment? | No |
| 4. Would the Project potentially limit women’s ability to use, develop and protect natural resources, taking into account different roles and positions of women and men in accessing environmental goods and services? For example, activities that could lead to natural resources degradation or depletion in communities who depend on these resources for their livelihoods and well being | No |
| Principle 3: Environmental Sustainability: Screening questions regarding environmental risks are encompassed by the specific Standard-related questions below |  |
| Standard 1: Biodiversity Conservation and Sustainable Natural Resource Management |  |
| 1.1 Would the Project potentially cause adverse impacts to habitats (e.g. modified, natural, and critical habitats) and/or ecosystems and ecosystem services? For example, through habitat loss, conversion or degradation, fragmentation, hydrological changes | No |
| 1.2 Are any Project activities proposed within or adjacent to critical habitats and/or environmentally sensitive areas, including legally protected areas (e.g. nature reserve, national park), areas proposed for protection, or recognized as such by authoritative sources and/or indigenous peoples or local communities? | No |
| 1.3 Does the Project involve changes to the use of lands and resources that may have adverse impacts on habitats, ecosystems, and/or livelihoods? (Note: if restrictions and/or limitations of access to lands would apply, refer to Standard 5) | No |
| 1.4 Would Project activities pose risks to endangered species? | No |
| 1.5 Would the Project pose a risk of introducing invasive alien species? | No |
| 1.6 Does the Project involve harvesting of natural forests, plantation development, or reforestation? | No |
| 1.7 Does the Project involve the production and/or harvesting of fish populations or other aquatic species? | No |
| 1.8 Does the Project involve significant extraction, diversion or containment of surface or ground water? For example, construction of dams, reservoirs, river basin developments, groundwater extraction | No |
| 1.9 Does the Project involve utilization of genetic resources? (e.g. collection and/or harvesting, commercial development) | No |
| 1.10 Would the Project generate potential adverse trans-boundary or global environmental concerns? | No |
| 1.11 Would the Project result in secondary or consequential development activities which could lead to adverse social and environmental effects, or would it generate cumulative impacts with other known existing or planned activities in the area? For example, a new road through forested lands will generate direct environmental and social impacts (e.g. felling of trees, earthworks, potential relocation of inhabitants). The new road may also facilitate encroachment on lands by illegal settlers or generate unplanned commercial development along the route, potentially in sensitive areas. These are indirect, secondary, or induced impacts that need to be considered. Also, if similar developments in the same forested area are planned, then cumulative impacts of multiple activities (even if not part of the same Project) need to be considered. | No |
| Standard 2: Climate Change Mitigation and Adaptation |  |
| 2.1 Will the proposed Project result in significant greenhouse gas emissions or may exacerbate climate change? | No |
| 2.2 Would the potential outcomes of the Project be sensitive or vulnerable to potential impacts of climate change? | No |
| 2.3 Is the proposed Project likely to directly or indirectly increase social and environmental vulnerability to climate change now or in the future (also known as maladaptive practices)? For example, changes to land use planning may encourage further development of floodplains, potentially increasing the population’s vulnerability to climate change, specifically flooding | No |
| Standard 3: Community Health, Safety and Working Conditions |  |
| 3.1 Would elements of Project construction, operation, or decommissioning pose potential safety risks to local communities? | No |
| 3.2 Would the Project pose potential risks to community health and safety due to the transport, storage, and use and/or disposal of hazardous or dangerous materials (e.g. explosives, fuel and other chemicals during construction and operation)? | No |
| 3.3 Does the Project involve large-scale infrastructure development (e.g. dams, roads, buildings)? | No |
| 3.4 Would failure of structural elements of the Project pose risks to communities? (e.g. collapse of buildings or infrastructure) | No |
| 3.5 Would the proposed Project be susceptible to or lead to increased vulnerability to earthquakes, subsidence, landslides, and erosion, flooding or extreme climatic conditions? | No |
| 3.6 Would the Project result in potential increased health risks (e.g. from water-borne or other vector-borne diseases or communicable infections such as HIV/AIDS)? | No |
| 3.7 Does the Project pose potential risks and vulnerabilities related to occupational health and safety due to physical, chemical, biological, and radiological hazards during Project construction, operation, or decommissioning? | No |
| 3.8 Does the Project involve support for employment or livelihoods that may fail to comply with national and international labor standards (i.e. principles and standards of ILO fundamental conventions)? | No |
| 3.9 Does the Project engage security personnel that may pose a potential risk to health and safety of communities and/or individuals (e.g. due to a lack of adequate training or accountability)? | No |
| Standard 4: Cultural Heritage |  |
| 4.1 Will the proposed Project result in interventions that would potentially adversely impact sites, structures, or objects with historical, cultural, artistic, traditional or religious values or intangible forms of culture (e.g. knowledge, innovations, practices)? (Note: Projects intended to protect and conserve Cultural Heritage may also have inadvertent adverse impacts) | No |
| 4.2 Does the Project propose utilizing tangible and/or intangible forms of cultural heritage for commercial or other purposes? | No |
| Standard 5: Displacement and Resettlement |  |
| 5.1 Would the Project potentially involve temporary or permanent and full or partial physical displacement? | No |
| 5.2 Would the Project possibly result in economic displacement (e.g. loss of assets or access to resources due to land acquisition or access restrictions – even in the absence of physical relocation)? | No |
| 5.3 Is there a risk that the Project would lead to forced evictions? | No |
| 5.4 Would the proposed Project possibly affect land tenure arrangements and/or community based property rights/customary rights to land, territories and/or resources? | No |
| Standard 6: Indigenous Peoples |  |
| 6.1 Are indigenous peoples present in the Project area (including Project area of influence)? | No |
| 6.2 Is it likely that the Project or portions of the Project will be located on lands and territories claimed by indigenous peoples? | No |
| 6.3 Would the proposed Project potentially affect the human rights, lands, natural resources, territories, and traditional livelihoods of indigenous peoples (regardless of whether indigenous peoples possess the legal titles to such areas, whether the Project is located within or outside of the lands and territories inhabited by the affected peoples, or whether the indigenous peoples are recognized as indigenous peoples by the country in question)? If the answer to the screening question 6.3 is “yes” the potential risk impacts are considered potentially severe and/or critical and the Project would be categorized as either Moderate or High Risk. | No |
| 6.4 Has there been an absence of culturally appropriate consultations carried out with the objective of achieving FPIC on matters that may affect the rights and interests, lands, resources, territories and traditional livelihoods of the indigenous peoples concerned? | No |
| 6.5 Does the proposed Project involve the utilization and/or commercial development of natural resources on lands and territories claimed by indigenous peoples? | No |
| 6.6 Is there a potential for forced eviction or the whole or partial physical or economic displacement of indigenous peoples, including through access restrictions to lands, territories, and resources? | No |
| 6.7 Would the Project adversely affect the development priorities of indigenous peoples as defined by them? | No |
| 6.8 Would the Project potentially affect the physical and cultural survival of indigenous peoples? | No |
| 6.9 Would the Project potentially affect the Cultural Heritage of indigenous peoples, including through the commercialization or use of their traditional knowledge and practices? | No |
| Standard 7: Pollution Prevention and Resource Efficiency |  |
| 7.1 Would the Project potentially result in the release of pollutants to the environment due to routine or non-routine circumstances with the potential for adverse local, regional, and/or trans-boundary impacts? | Yes |
| 7.2 Would the proposed Project potentially result in the generation of waste (both hazardous and non-hazardous)? | Yes |
| 7.3 Will the proposed Project potentially involve the manufacture, trade, release, and/or use of hazardous chemicals and/or materials? Does the Project propose use of chemicals or materials subject to international bans or phase-outs? For example, DDT, PCBs and other chemicals listed in international conventions such as the Stockholm Conventions on Persistent Organic Pollutants or the Montreal Protocol | Yes |
| 7.4 Will the proposed Project involve the application of pesticides that may have a negative effect on the environment or human health? | No |
| 7.5 Does the Project include activities that require significant consumption of raw materials, energy, and/or water? | No |

Annex G: UNDP Project Quality Assurance Report

| Project QA Assessment: Design and Appraisal |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Overall Project |  |  |  |  |  |  |
| Exemplary (5) | Highly Satisfactory (4) | Satisfactory (3) | Needs Improvement (2) | Inadequate (1) |  |  |
| At least four criteria are rated Exemplary, and all criteria are rated High or Exemplary. | All criteria are rated Satisfactory or higher, and at least four criteria are rated High or Exemplary. | At least six criteria are rated Satisfactory or higher, and only one may be rated Needs Improvement. The SES criterion must be rated Satisfactory or above. | At least three criteria are rated Satisfactory or higher, and only four criteria may be rated Needs Improvement. | One or more criteria are rated Inadequate, or five or more criteria are rated Needs Improvement. |  |  |
| DECISION |  |  |  |  |  |  |
| - APPROVE – the project is of sufficient quality to continue as planned. Any management actions must be addressed in a timely manner. - APPROVE WITH QUALIFICATIONS – the project has issues that must be addressed before the project document can be approved. Any management actions must be addressed in a timely manner. - DISAPPROVE – the project has significant issues that should prevent the project from being approved as drafted. |  |  |  |  |  |  |
| RATING CRITERIA |  |  |  |  |  |  |
| Strategic |  |  |  |  |  |  |
| - Does the project’s Theory of Change specify how it will contribute to higher level change? (Select the option from 1-3 that best reflects the project): - 3: The project has a theory of change with explicit assumptions and clear change pathway describing how the project will contribute to outcome level change as specified in the programme/CPD, backed by credible evidence of what works effectively in this context. The project document clearly describes why the project’s strategy is the best approach at this point in time. - 2: The project has a theory of change. It has an explicit change pathway that explains how the project intends to contribute to outcome-level change and why the project strategy is the best approach at this point in time, but is backed by limited evidence. - 1: The project does not have a theory of change, but the project document may describe in generic terms how the project will contribute to development results, without specifying the key assumptions. It does not make an explicit link to the programme/CPD’s theory of change. *Note: Management Action or strong management justification must be given for a score of 1 Option 3. The project has a theory of change that considers critical factors for achieving an increased market penetration of energy efficient lighting systems, thus contributing to the UNPDF/CPD Outcome 3: By 2020, Indonesia is sustainably managing its natural resources, on land and at sea, with an increased resilience to the effects of climate change, disasters and other shocks (Project Document’s Strategy chapter). |  |  |  |  | 3 | 2 |
|  |  |  |  |  | 1 |  |
|  |  |  |  |  | Evidence |  |
| - Is the project aligned with the thematic focus of the UNDP Strategic Plan? (select the option from 1-3 that best reflects the project): - 3: The project responds to one of the three areas of development work as specified in the Strategic Plan; it addresses at least one of the proposed new and emerging areas; an issues-based analysis has been incorporated into the project design; and the project’s RRF includes all the relevant SP output indicators. (all must be true to select this option) - 2: The project responds to one of the three areas of development work1 as specified in the Strategic Plan. The project’s RRF includes at least one SP output indicator, if relevant. (both must be true to select this option) - 1: While the project may respond to one of the three areas of development work1 as specified in the Strategic Plan, it is based on a sectoral approach without addressing the complexity of the development issue. None of the relevant SP indicators are included in the RRF. This answer is also selected if the project does not respond to any of the three areas of development work in the Strategic Plan. Option 3. The project responds to the development area Sustainable development pathways in the Strategic Plan and addresses the new and emerging area Access to modern energy services and energy efficiency. This will be achieved by promoting the increased deployment of high efficiency lighting technologies in Indonesia through the transformation of the national market, thereby reducing electricity demand and the related greenhouse gas (GHG) emissions. Strategic Plan Areas of Development Work; Strategic Plan New and Emerging Issues. ☒ Sustainable Development Pathways ☐ Inclusive and effective democratic governance ☐ Resilience building; ☐ Sustainable production technologies ☒ Access to modern energy services ☐ Natural resources management ☐ Extractive industries ☐ Urbanisation ☐ Citizen security ☐ Social protection ☐ Risk management for resilience. . | 3 | 2 |
|  |  |  |  |  | 1 |  |
|  |  |  |  |  | Evidence |  |
| Relevant |  |  |  |  |  |  |
| - Does the project have strategies to effectively identify, engage and ensure the meaningful participation of targeted groups/geographic areas with a priority focus on the excluded and marginalized? (select the option from 1-3 that best reflects this project): - 3: The target groups/geographic areas are appropriately specified, prioritizing the excluded and/or marginalized. Beneficiaries will be identified through a rigorous process based on evidence (if applicable.) The project has an explicit strategy to identify, engage and ensure the meaningful participation of specified target groups/geographic areas throughout the project, including through monitoring and decision-making (such as representation on the project board) (all must be true to select this option) - 2: The target groups/geographic areas are appropriately specified, prioritizing the excluded and/or marginalized. The project document states how beneficiaries will be identified, engaged and how meaningful participation will be ensured throughout the project. (both must be true to select this option) - 1: The target groups/geographic areas are not specified, or do not prioritize excluded and/or marginalized populations. The project does not have a written strategy to identify or engage or ensure the meaningful participation of the target groups/geographic areas throughout the project. *Note: Management Action must be taken for a score of 1 Option 2. The main target groups/geographic areas of the project have been identified in the project design. Ways to ensure their participation in the project have been identified in the Stakeholder Engagement Plan. A more detailed specification of beneficiaries and pilot areas will be carried out during project implementation. ROAR Target Groups:; ROAR Target Geographical Areas:. ☐ Extreme poor ☐ Women ☐ Female Headed Households ☐ Youth ☒ Others (specify): Energy efficiency lighting sector: local EEL manufacturers, financing institutions, government agencies, and end users who will benefit from LED lighting in buildings and on the streets of pilot areas; ☒ Urban (large cities) ☐ Urban (small towns) ☐ Peri-urban (surround metropolitan areas & cities) ☐ Rural ☐ Others (specify): _____________. . | 3 | 2 |
|  |  |  |  |  | 1 |  |
|  |  |  |  |  | Select (all) targeted groups: (drop-down) Evidence |  |
| - Have knowledge, good practices, and past lessons learned of UNDP and others informed the project design? (select the option from 1-3 that best reflects this project): - 3: Knowledge and lessons learned (gained e.g. through peer assist sessions) backed by credible evidence from evaluation, corporate policies/strategies, and monitoring have been explicitly used, with appropriate referencing, to develop the project’s theory of change and justify the approach used by the project over alternatives. - 2: The project design mentions knowledge and lessons learned backed by evidence/sources, which inform the project’s theory of change but have not been used/are not sufficient to justify the approach selected over alternatives. - 1: There is only scant or no mention of knowledge and lessons learned informing the project design. Any references that are made are not backed by evidence. *Note: Management Action or strong management justification must be given for a score of 1 Option 3. The ADLIGHT project is built upon knowledge and relevant ongoing energy efficiency lighting projects/programs as well as already completed projects. The added value of ADLIGHT to the contributions of ongoing/completed initiatives in the area of application of local efficient lighting products is summarized in the project document (Project Document’s Development Challenge chapter). |  |  |  |  | 3 | 2 |
|  |  |  |  |  | 1 |  |
|  |  |  |  |  | Evidence |  |
| - Does the project use gender analysis in the project design and does the project respond to this gender analysis with concrete measures to address gender inequities and empower women? (select the option from 1-3 that best reflects this project): - 3: A participatory gender analysis on the project has been conducted. This analysis reflects on the different needs, roles and access to/control over resources of women and men, and it is fully integrated into the project document. The project establishes concrete priorities to address gender inequalities in its strategy. The results framework includes outputs and activities that specifically respond to this gender analysis, with indicators that measure and monitor results contributing to gender equality. (all must be true to select this option) - 2: A gender analysis on the project has been conducted. This analysis reflects on the different needs, roles and access to/control over resources of women and men. Gender concerns are integrated in the development challenge and strategy sections of the project document. The results framework includes outputs and activities that specifically respond to this gender analysis, with indicators that measure and monitor results contributing to gender equality. (all must be true to select this option) - 1: The project design may or may not mention information and/or data on the differential impact of the project’s development situation on gender relations, women and men, but the constraints have not been clearly identified and interventions have not been considered. *Note: Management Action or strong management justification must be given for a score of 1 Option 2. A gender analysis has been conducted during the project design (Annex N). Based on the gender analysis, the project has included gender mainstreaming, as appropriate, in its implementation strategies, outputs, activities, results framework and indicators. |  |  |  |  | 3 | 2 |
|  |  |  |  |  | 1 |  |
|  |  |  |  |  | Evidence |  |
| - Does UNDP have a clear advantage to engage in the role envisioned by the project vis-à-vis national partners, other development partners, and other actors? (select from options 1-3 that best reflects this project): - 3: An analysis has been conducted on the role of other partners in the area where the project intends to work, and credible evidence supports the proposed engagement of UNDP and partners through the project. It is clear how results achieved by relevant partners will contribute to outcome level change complementing the project’s intended results. If relevant, options for south-south and triangular cooperation have been considered, as appropriate. (all must be true to select this option) - 2: Some analysis has been conducted on the role of other partners where the project intends to work, and relatively limited evidence supports the proposed engagement of and division of labour between UNDP and partners through the project. Options for south-south and triangular cooperation may not have not been fully developed during project design, even if relevant opportunities have been identified. - 1: No clear analysis has been conducted on the role of other partners in the area that the project intends to work, and relatively limited evidence supports the proposed engagement of UNDP and partners through the project. There is risk that the project overlaps and/or does not coordinate with partners’ interventions in this area. Options for south-south and triangular cooperation have not been considered, despite its potential relevance. *Note: Management Action or strong management justification must be given for a score of 1 Option 3. Relevant partners have been identified and their role in project implementation has been outlined in the project document. The ADLIGHT Project will also pursue and promote South-South and triangular cooperation forms, such as knowledge exchange, technology transfer, financing, peer support, and country-to country or multi country initiatives, on high efficient lighting technology. (Results and Partnerships chapter) |  |  |  |  | 3 | 2 |
|  |  |  |  |  | 1 |  |
|  |  |  |  |  | Evidence |  |
| Social & Environmental Standards |  |  |  |  |  |  |
| - Does the project seek to further the realization of human rights using a human rights based approach? (select from options 1-3 that best reflects this project): - 3: Credible evidence that the project aims to further the realization of human rights, upholding the relevant international and national laws and standards in the area of the project. Any potential adverse impacts on enjoyment of human rights were rigorously identified and assessed as relevant, with appropriate mitigation and management measures incorporated into project design and budget. (all must be true to select this option) - 2: Some evidence that the project aims to further the realization of human rights. Potential adverse impacts on enjoyment of human rights were identified and assessed as relevant, and appropriate mitigation and management measures incorporated into the project design and budget. - 1: No evidence that the project aims to further the realization of human rights. Limited or no evidence that potential adverse impacts on enjoyment of human rights were considered. *Note: Management action or strong management justification must be given for a score of 1 Option 2. The project was designed and will be implemented with due consideration of human rights principles, through engagement of the concepts of equality in the dissemination of knowledge and sharing of benefits. In the process of selection and implementation and energy efficiency projects that will be demonstrated in the pilot province, participatory approach and free, prior and informed consent (FPIC) process will be conducted by involving stakeholders that will be affected by the projects (Annex P) |  |  |  |  | 3 | 2 |
|  |  |  |  |  | 1 |  |
|  |  |  |  |  | Evidence |  |
| 8. Did the project consider potential environmental opportunities and adverse impacts, applying a precautionary approach? (select from options 1-3 that best reflects this project): - 3: Credible evidence that opportunities to enhance environmental sustainability and integrate poverty-environment linkages were fully considered as relevant, and integrated in project strategy and design. Credible evidence that potential adverse environmental impacts have been identified and rigorously assessed with appropriate management and mitigation measures incorporated into project design and budget. (all must be true to select this option). - 2: No evidence that opportunities to strengthen environmental sustainability and poverty-environment linkages were considered. Credible evidence that potential adverse environmental impacts have been identified and assessed, if relevant, and appropriate management and mitigation measures incorporated into project design and budget. - 1: No evidence that opportunities to strengthen environmental sustainability and poverty-environment linkages were considered. Limited or no evidence that potential adverse environmental impacts were adequately considered. *Note: Management action or strong management justification must be given for a score of 1 Option 3. The project will contribute to carbon emission reduction through promotion and deployment of energy efficient lighting systems. The project’s environmental effects involve pollution from hazardous and non-hazardous waste from replaced fluorescent lamps/CFL and other conventional lights and particularly, mercury content and sharp cladding and bulb parts of these lamps. As a mitigation measure, the project will develop a strategy to manage waste/obsolete energy equipment and lamps. (Annex H) |  |  |  |  | 3 | 2 |
|  |  |  |  |  | 1 |  |
|  |  |  |  |  | Evidence |  |
| 9. Has the Social and Environmental Screening Procedure (SESP) been conducted to identify potential social and environmental impacts and risks? The SESP is not required for projects in which UNDP is Administrative Agent only and/or projects comprised solely of reports, coordination of events, trainings, workshops, meetings, conferences and/or communication materials and information dissemination. [if yes, upload the completed checklist. If SESP is not required, provide the reason for the exemption in the evidence section.] Yes, a SESP has been conducted (Annex F). |  |  |  |  | Yes | No |
|  |  |  |  |  | SESP Not Required |  |
| Management & Monitoring |  |  |  |  |  |  |
| - Does the project have a strong results framework? (select from options 1-3 that best reflects this project): - 3: The project’s selection of outputs and activities are at an appropriate level and relate in a clear way to the project’s theory of change. Outputs are accompanied by SMART, results-oriented indicators that measure all of the key expected changes identified in the theory of change, each with credible data sources, and populated baselines and targets, including gender sensitive, sex-disaggregated indicators where appropriate. (all must be true to select this option) - 2: The project’s selection of outputs and activities are at an appropriate level, but may not cover all aspects of the project’s theory of change. Outputs are accompanied by SMART, results-oriented indicators, but baselines, targets and data sources may not yet be fully specified. Some use of gender sensitive, sex-disaggregated indicators, as appropriate. (all must be true to select this option) - 1: The results framework does not meet all of the conditions specified in selection “2” above. This includes: the project’s selection of outputs and activities are not at an appropriate level and do not relate in a clear way to the project’s theory of change; outputs are not accompanied by SMART, results-oriented indicators that measure the expected change, and have not been populated with baselines and targets; data sources are not specified, and/or no gender sensitive, sex-disaggregation of indicators. *Note: Management Action or strong management justification must be given for a score of 1 Option 3. The project’s Results Framework relates well to the theory of change and includes SMART indicators and sex-disaggregated data where appropriate. One of the baselines is not yet populated and will be established through market surveys during project implementation. (Project Results Framework) |  |  |  |  | 3 | 2 |
|  |  |  |  |  | 1 |  |
|  |  |  |  |  | Evidence |  |
| - Is there a comprehensive and costed M&E plan in place with specified data collection sources and methods to support evidence-based management, monitoring and evaluation of the project? Yes, the project has a M&E plan including M&E budget in the project document (Monitoring and Evaluation Plan). |  |  |  |  | Yes (3) | No (1) |
| 12. Is the project’s governance mechanism clearly defined in the project document, including planned composition of the project board? (select from options 1-3 that best reflects this project): - 3: The project’s governance mechanism is fully defined in the project composition. Individuals have been specified for each position in the governance mechanism (especially all members of the project board.) Project Board members have agreed on their roles and responsibilities as specified in the terms of reference. The ToR of the project board has been attached to the project document. (all must be true to select this option). - 2: The project’s governance mechanism is defined in the project document; specific institutions are noted as holding key governance roles, but individuals may not have been specified yet. The prodoc lists the most important responsibilities of the project board, project director/manager and quality assurance roles. (all must be true to select this option) - 1: The project’s governance mechanism is loosely defined in the project document, only mentioning key roles that will need to be filled at a later date. No information on the responsibilities of key positions in the governance mechanism is provided. *Note: Management Action or strong management justification must be given for a score of 1 Option 2. Roles and responsibilities of the project’s governance mechanism are outlined in the project document (Governance and Management Arrangements chapter and Annex F). The ToR of the Project Board are not attached to the project document. |  |  |  |  | 3 | 2 |
|  |  |  |  |  | 1 |  |
|  |  |  |  |  | Evidence |  |
| 13. Have the project risks been identified with clear plans stated to manage and mitigate each risks? (select from options 1-3 that best reflects this project): - 3: Project risks related to the achievement of results are fully described in the project risk log, based on comprehensive analysis drawing on the theory of change, Social and Environmental Standards and screening, situation analysis, capacity assessments and other analysis. Clear and complete plan in place to manage and mitigate each risk. (both must be true to select this option) - 2: Project risks related to the achievement of results identified in the initial project risk log with mitigation measures identified for each risk. - 1: Some risks may be identified in the initial project risk log, but no evidence of analysis and no clear risk mitigation measures identified. This option is also selected if risks are not clearly identified and no initial risk log is included with the project document. *Note: Management Action must be taken for a score of 1 Option 2. UNDP risk log describes the project’s risks and mitigation measures and is attached to the project document. (Annex H) |  |  |  |  | 3 | 2 |
|  |  |  |  |  | 1 |  |
|  |  |  |  |  | Evidence |  |
| Efficient |  |  |  |  |  |  |
| 14. Have specific measures for ensuring cost-efficient use of resources been explicitly mentioned as part of the project design? This can include: i) using the theory of change analysis to explore different options of achieving the maximum results with the resources available; ii) using a portfolio management approach to improve cost effectiveness through synergies with other interventions; iii) through joint operations (e.g., monitoring or procurement) with other partners. Yes. Cost efficiency and effectiveness will be achieved by strategies that leverage limited inputs of GEF funding to stimulate much greater investments by other parties, namely the government and the private sector. The project is expecting to generate USD 18,115,000 in private sector investments within the project timeline and additional resources as the pilot demonstrations are replicated in the country. (Feasiblity chapter) |  |  |  |  | Yes (3) | No (1) |
| 15. Are explicit plans in place to ensure the project links up with other relevant on-going projects and initiatives, whether led by UNDP, national or other partners, to achieve more efficient results (including, for example, through sharing resources or coordinating delivery?) Yes. The project is in line with the planned interventions of the national government in the development of standards for energy efficient lighting according to the ASEAN Plan of Action Energy Cooperation 2016-2025 (APAEC), which highlights regional harmonization of LED lighting standards. The ADLIGHT project is also in line with the Solo city government’s planned installation of LED street lighting. The linkages between the ADLIGHT project and these interventions have been considered throughout the project document. |  |  |  |  | Yes (3) | No (1) |
| 16. Is the budget justified and supported with valid estimates? - 3: The project’s budget is at the activity level with funding sources, and is specified for the duration of the project period in a multi-year budget. Costs are supported with valid estimates using benchmarks from similar projects or activities. Cost implications from inflation and foreign exchange exposure have been estimated and incorporated in the budget. - 2: The project’s budget is at the activity level with funding sources, when possible, and is specified for the duration of the project in a multi-year budget. Costs are supported with valid estimates based on prevailing rates. - 1: The project’s budget is not specified at the activity level, and/or may not be captured in a multi-year budget. Option 3. The project’s budget is at the activity level presented in the Total Budget and Work Plan chapter. |  |  |  |  | 3 | 2 |
|  |  |  |  |  | 1 |  |
|  |  |  |  |  | Evidence |  |
| - Is the Country Office fully recovering the costs involved with project implementation? - 3: The budget fully covers all project costs that are attributable to the project, including programme management and development effectiveness services related to strategic country programme planning, quality assurance, pipeline development, policy advocacy services, finance, procurement, human resources, administration, issuance of contracts, security, travel, assets, general services, information and communications based on full costing in accordance with prevailing UNDP policies (i.e., UPL, LPL.) - 2: The budget covers significant project costs that are attributable to the project based on prevailing UNDP policies (i.e., UPL, LPL) as relevant. - 1: The budget does not adequately cover project costs that are attributable to the project, and UNDP is cross-subsidizing the project. *Note: Management Action must be given for a score of 1. The budget must be revised to fully reflect the costs of implementation before the project commences. Option 3. The budget fully covers all project costs. |  |  |  |  | 3 | 2 |
|  |  |  |  |  | 1 |  |
|  |  |  |  |  | Evidence |  |
| Effective |  |  |  |  |  |  |
| 18. Is the chosen implementation modality most appropriate? (select from options 1-3 that best reflects this project): - 3: The required implementing partner assessments (capacity assessment, HACT micro assessment) have been conducted, and there is evidence that options for implementation modalities have been thoroughly considered. There is a strong justification for choosing the selected modality, based on the development context. (both must be true to select this option) - 2: The required implementing partner assessments (capacity assessment, HACT micro assessment) have been conducted and the implementation modality chosen is consistent with the results of the assessments. - 1: The required assessments have not been conducted, but there may be evidence that options for implementation modalities have been considered. *Note: Management Action or strong management justification must be given for a score of 1 Assessment of the implementing partner has been conducted by another project under the same implementing partner – Directorate General of New Renewable Energy and Energy Conservation, within the Ministry of Energy and Mineral Resources (Annex I). Based on the assessment conducted, the proposed implementation modality for project components under UNDP’s responsibility is NIM. |  |  |  |  | 3 | 2 |
|  |  |  |  |  | 1 |  |
|  |  |  |  |  | Evidence |  |
| 19. Have targeted groups, prioritizing marginalized and excluded populations that will be affected by the project, been engaged in the design of the project in a way that addresses any underlying causes of exclusion and discrimination? - 3: Credible evidence that all targeted groups, prioritising marginalized and excluded populations that will be involved in or affected by the project, have been actively engaged in the design of the project. Their views, rights and any constraints have been analysed and incorporated into the root cause analysis of the theory of change which seeks to address any underlying causes of exclusion and discrimination and the selection of project interventions. - 2: Some evidence that key targeted groups, prioritising marginalized and excluded populations that will be involved in the project, have been engaged in the design of the project. Some evidence that their views, rights and any constraints have been analysed and incorporated into the root cause analysis of the theory of change and the selection of project interventions. - 1: No evidence of engagement with marginalized and excluded populations that will be involved in the project during project design. No evidence that the views, rights and constraints of populations have been incorporated into the project. Option 1. During the project design the target groups engaged were national and local government institutions, lighting manufacturers and financing institutions. Marginalized and excluded population will be engaged through surveys and stakeholder consultations before, during and after implementation of energy efficiency projects in pilot areas. |  |  |  |  | 3 | 2 |
|  |  |  |  |  | 1 |  |
|  |  |  |  |  | Evidence |  |
| 20. Does the project conduct regular monitoring activities, have explicit plans for evaluation, and include other lesson learning (e.g. through After Action Reviews or Lessons Learned Workshops), timed to inform course corrections if needed during project implementation? Yes. The project will be monitored and evaluated periodically during project implementation according to the Monitoring and Evaluation plan. |  |  |  |  | Yes (3) | No (1) |
| 21. The gender marker for all project outputs are scored at GEN2 or GEN3, indicating that gender has been fully mainstreamed into all project outputs at a minimum. *Note: Management Action or strong management justification must be given for a score of “no” Yes. The project’s outputs score GEN2. |  |  |  |  | Yes (3) | No (1) |
|  |  |  |  |  | Evidence |  |
| 22. Is there a realistic multi-year work plan and budget to ensure outputs are delivered on time and within allotted resources? (select from options 1-3 that best reflects this project): - 3: The project has a realistic work plan & budget covering the duration of the project at the activity level to ensure outputs are delivered on time and within the allotted resources. - 2: The project has a work plan & budget covering the duration of the project at the output level. - 1: The project does not yet have a work plan & budget covering the duration of the project. Option 3. The project has a budget and work plan at the activity level. |  |  |  |  | 3 | 2 |
|  |  |  |  |  | 1 |  |
|  |  |  |  |  | Evidence |  |
| Sustainability & National Ownership |  |  |  |  |  |  |
| 23. Have national partners led, or proactively engaged in, the design of the project? (select from options 1-3 that best reflects this project): - 3: National partners have full ownership of the project and led the process of the development of the project jointly with UNDP. - 2: The project has been developed by UNDP in close consultation with national partners. - 1: The project has been developed by UNDP with limited or no engagement with national partners. Option 2. The project has been designed in close consultation with the Ministry of Energy and Mineral Resources. |  |  |  |  | 3 | 2 |
|  |  |  |  |  | 1 |  |
|  |  |  |  |  | Evidence |  |
| 24. Are key institutions and systems identified, and is there a strategy for strengthening specific/ comprehensive capacities based on capacity assessments conducted? (select from options 0-4 that best reflects this project): - 3: The project has a comprehensive strategy for strengthening specific capacities of national institutions based on a systematic and detailed capacity assessment that has been completed. This strategy includes an approach to regularly monitor national capacities using clear indicators and rigorous methods of data collection, and adjust the strategy to strengthen national capacities accordingly. - 2.5: A capacity assessment has been completed. The project document has identified activities that will be undertaken to strengthen capacity of national institutions, but these activities are not part of a comprehensive strategy to monitor and strengthen national capacities. - 2: A capacity assessment is planned after the start of the project. There are plans to develop a strategy to strengthen specific capacities of national institutions based on the results of the capacity assessment. - 1.5: There is mention in the project document of capacities of national institutions to be strengthened through the project, but no capacity assessments or specific strategy development are planned. - 1: Capacity assessments have not been carried out and are not foreseen. There is no strategy for strengthening specific capacities of national institutions. Option 2.5. A capacity assessment of government institutions has been conducted during project design and is part of the development challenge and strategy of the project. Capacity development for institutions on of EE lighting systems is part of the project’s outputs |  |  |  |  | 3 | 2.5 |
|  |  |  |  |  | 2 | 1.5 |
|  |  |  |  |  | 1 |  |
|  |  |  |  |  | Evidence |  |
| 25. Is there is a clear strategy embedded in the project specifying how the project will use national systems (i.e., procurement, monitoring, evaluations, etc.,) to the extent possible? Yes. The project is proposed to be implemented under NIM modality for project components under UNDP’s responsibility. In this case, if requested by the government, Country Office Support Services will be adopted by UNDP. NIM modality will be implemented for project components under UN Environment’s responsibility. |  |  |  |  | Yes (3) | No (1) |
| 26. Is there a clear transition arrangement/ phase-out plan developed with key stakeholders in order to sustain or scale up results (including resource mobilisation strategy)? Yes. The project activities are designed to encourage scaling up of pilot demonstrations for buildings and street lighting. The scale up is also expected to result from establishment of enabling environment for effectively implementing the Business Transformation Plans, capacity building, MEPS/SNI development and promotional activities to bolster the deployment of EE Lighting in the target sectors. |  |  |  |  | Yes (3) | No (1) |

ANNEX H: UNDP Risk Log

| Project risks |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Description | Type | Impact & Probability | Mitigation Measures | Owner | Status |
| - Prolonged delays in the implementation of MEPS due to Government procedures and processes | Political Regulatory | P = 2 I = 3 | BSN to come up with SNI standards that can be used as reference in the government procurements and other EEL applications while MEPS is being developed | MEMR/DGNREEC BSN Industry associations Min of Trade and Industry | Reducing |
| - Local lighting manufacturers may not be interested to upgrade the lighting production facilities due to increased investments, disruption to operation and business priorities | Financial Operational Strategic | P = 3 I = 3 | Coordinate closely with manufacturers associations and local banks to facilitate investments; facilitate through ESCOs and TWG | MEMR/DGNREEC Industry associations Min of Trade and Industry | Reducing |
| - Petroleum products and electricity prices will be at levels that make energy efficiency projects, particularly in EEL, uncompetitive and not cost effective | Strategic Environmental Political | P = 3 I = 3 | Government to be encouraged to adopt appropriate energy pricing policies and incentives to encourage EE project investments | MEMR/DGNREEC Min of finance Min of Planning Industry associations Min of Trade and Industry | Increasing |
| - Manufacturers are not committed to improving the energy-efficiency and quality of products. | Organizational Operational | P = 2 I = 3 | Coordinate closely with manufacturers associations; facilitate through ESCOs and TWG | MEMR/DGNREEC Industry associations Min of Trade and Industry | Reducing |
| - Manufacturers are not willing to share data on their operations and marketing for MVE | Financial Operational | P = 3 I = 3 | Coordinate closely with manufacturers associations; facilitate through ESCOs and TWG | MEMR/DGNREEC Industry associations Min of Trade and Industry | Reducing |
| - Banks and financial institutions are not convinced about the business potential of manufacturing and market for LED systems | Financial Operational Organizational | P = 3 I = 3 | Coordinate closely with manufacturers associations and local banks to facilitate investments; facilitate through ESCOs and TWG | MEMR/DGNREEC Industry associations Min of Trade and Industry OJK Financial institutions/Banks | Reducing |
| - Commitment to abide with regional and international EEL standards and harmonization is lacking | Political Regulatory | P = 2 I = 3 | Implement Component 2 on policy and institutional support effectively | MEMR/DGNREEC Industry associations Min of Trade and Industry | Reducing |
| - Policy framework may not attractive for manufacturers and users to invest in EEL projects. | Political Regulatory | P = 3 I = 3 | Implement Component 2 on policy and institutional support effectively | MEMR/DGNREEC Industry associations Min of Trade and Industry | Reducing |
| - Local EEL producers could not meet all technical standard specifications | Financial Operational Organizational | P = 3 I = 3 | Coordinate closely with manufacturers associations; facilitate through ESCOs and TWG | MEMR/DGNREEC Industry associations Min of Trade and Industry | Reducing |
| Overall |  | P = 3 I = 3 |  |  |  |

Annex I: Results of the capacity assessment of the project implementing partner and HACT micro assessment

Annex J: Additional Agreements

(Co-financing Letters)

(in separate file)

Commitment Letter -

Ministry of Energy and Mineral Resource (DG-NREEC)

Commitment Letter -

Ministry of Energy and Mineral Resource (P3TEK – R&D Dept)

Commitment Letter -

National Standardization Agency (Badan Standardisasi Nasional, BSN)

Commitment Letter -

City Government of Solo/Surakarta (Mayor)

Commitment Letter -

Indonesian Lighting Manufacturers Association – GAMATRINDO

Commitment Letter -

Indonesian Lighting Manufacturers Association – APERLINDO

Commitment Letter -

Global Efficient Lighting Centre

Commitment Letter -

Solarens (local LED manufacturer)

Commitment Letter -

Adyawinsa (local LED manufacturer)

Commitment Letter -

UN Environment

Commitment Letter -

UNDP

Country Office Support Service Agreement

AGREEMENT BETWEEN UNDP AND THE GOVERNMENT FOR THE PROVISION OF SUPPORT SERVICES

1.	Reference is made to consultations between officials of the Government of Indonesia (hereinafter referred to as “the Government”) and officials of UNDP with respect to the provision of support services by the UNDP Country Office for nationally managed programs and projects.  UNDP and the Government hereby agree that the UNDP Country Office of Indonesia may provide such support services at the request of the Government through its institution designated in the relevant project document, as described below.

2.	The UNDP Country Office – Indonesia may provide support services for assistance with reporting requirements and direct payment.  In providing such support services, the UNDP Country Office shall ensure that the capacity of the Government-designated institution is strengthened to enable it to carry out such activities directly.  The costs incurred by the UNDP Country Office in providing such support services shall be recovered from the administrative budget of the office.

3.	The UNDP Country Office may provide, at the request of the designated institution, the following support services for the activities of the programme/project:

(a)	Identification and/or recruitment of project and programme personnel as well as technical expertise;

(b)	Identification and facilitation of training activities;

(c)	Procurement of goods and services;

(d)	Any other type of activities/services as per prevailing UNDP Universal/Local Price List.

4.	The procurement of goods and services and the recruitment of project and programme personnel by the UNDP Country Office shall be in accordance with the UNDP regulations, rules, policies and procedures.  Support services described in paragraph 3 above shall be detailed in the annual work plan (UNDP as a Responsible Party) as described in the project document.  If the requirements for support services by the Country Office change during the life of a programme or project, the annual/multi-year work plan in the project document is revised with the mutual agreement of the UNDP resident representative and the designated institution.

5.	The relevant provisions of the Revised Basic Agreement for Technical Assistance signed 29 October 1954 between the United Nations, the International Labour Organisation, the Food and Agriculture Organisation of the United Nations, the United Nations Educational, Scientific and Cultural Organisation, the International Civil Aviation Organisation, and the World Health Organisation and the Government of the Republic of Indonesia, the Standard Agreement on Operational Assistance signed 12 June 1969 between the United Nations, the International Labour Organisation, the Food and Agriculture Organisation of the United Nations, the United Nations Educational, Scientific and Cultural Organisation, the International Civil Aviation Organisation, the World Health Organisation, the International Telecommunication Union, the World Meteorological Organisation, the International Atomic Energy Agency, the Universal Postal Union, the Inter-Governmental Maritime Consultative Organisation and the United Nations Industrial Development Organisation and the Government of the Republic of Indonesia, the Agreement signed 7 October 1960 between the United Nations Special Fund and the Government of the Republic of Indonesia, and the Partnership Framework Agreement signed 28 September 2012 between the Government of the Republic of Indonesia and the United Nations Development Programme, including the provisions on liability and privileges and immunities, shall apply to the provision of such support services. The Government shall retain overall responsibility for the nationally managed programme or project through its designated institution.  The responsibility of the UNDP Country Office for the provision of the support services described herein shall be limited to the provision of such support services detailed in the annual/multi-year work plan of the project document.

6.	Any claim or dispute arising under or in connection with the provision of support services by the UNDP Country Office in accordance with this letter shall be handled pursuant to the relevant provisions of the above mentioned agreements.

7.	The manner and method of cost-recovery by the UNDP Country Office in providing the support services described in paragraph 3 above shall refer to the prevailing UNDP Universal/Local Price List and be specified in the Annex to the programme support document or project document.

8.	The UNDP Country Office shall submit progress reports on the support services provided and shall report on the costs reimbursed in providing such services, as may be required.

9.	Any modification of the present arrangements shall be effected by mutual written agreement of the parties hereto.

10.	Upon your signature of the project document, this document shall constitute an agreement between your Government and UNDP on the terms and conditions for the provision of support services by the UNDP Country Office for nationally managed programmes and projects.

Yours sincerely,

________________________

Signed on behalf of UNDP

[Name]

[Title: Resident Representative]

_____________________

For the Government

[Name/title]

[Date]

Attachment

DESCRIPTION OF UNDP COUNTRY OFFICE SUPPORT SERVICES

    - Reference is made to consultations between Ministry of Energy and Mineral Resources (MEMR), the institution designated by the Government of Indonesia and officials of UNDP with respect to the provision of support services by the UNDP country office for the nationally managed project Advancing Indonesia’s Lighting Market to High Efficient Technologies (ADLIGHT), “the Project”.

2.	In accordance with the provisions of the letter of agreement signed on [insert date of agreement] and the programme support document [or project document], the UNDP country office shall provide support services for the Programme [or Project] as described below.

3.	Support services to be provided:

Indicative COSS for the ADLIGHT Project has been calculated as follows:

| No | Service Name | Unit | Volume | Unit Cost (US$) UPL/IPL 2018 | Total (US$) |
| --- | --- | --- | --- | --- | --- |
| 1 | Service Contract recruitment | Human Resources | 9 | 713.21 | 6,418.89 |
| 2 | Creation email address for new recruit UNDP | Human Resources | 9 | 15.99 | 143.91 |
| 3 | Service Contract extension | Human Resources | 18 | 67.68 | 1,218.24 |
| 4 | Procurement process not involving CAP | Procurement | 33 | 260.18 | 8,585.94 |
| 5 | Procurement process involving CAP | Procurement | 15 | 659.46 | 9,891.90 |
| 6 | Consultant recruitment | Procurement | 18 | 286.20 | 5,151.60 |
| 7 | Urgent payment process | Finance | 30 | 55.26 | 1,657.80 |
| 8 | Normal payment process | Finance | 48 | 44.21 | 2,122.08 |
| 9 | Payment of cash distributions | Finance | 36 | 72.77 | 2,619.72 |
| 10 | Settlement of travel advance/F10/petty cash | Finance | 21 | 40.02 | 840.42 |
| 11 | Settlement project cash advance (PCA) | Finance | 14 | 72.77 | 1,018.78 |
| 12 | Review and approval of APJV and GLJE | Finance | 12 | 31.79 | 381.48 |
| 13 | Issue/apply deposit only | Finance | 15 | 26.15 | 392.25 |
| 14 | Hardware specs for desktop, notebook, scanner and printers | Information & Communication Technologies | 3 | 48.75 | 146.25 |
| 15 | Printers setup | Information & Communication Technologies | 3 | 25.75 | 77.25 |
| 16 | New office network setup | Information & Communication Technologies | 3 | 431.45 | 1,294.35 |
| 17 | New notebook installation | Information & Communication Technologies | 9 | 90.55 | 814.95 |
| 18 | Website development | Information & Communication Technologies | 3 | 323.81 | 971.43 |
| 19 | Translation service - regular | Communication | 3 | 19.99 | 59.97 |
| 20 | Proofreading, editing - regular | Communication | 6 | 17.17 | 103.02 |
| 21 | Interpreter service | Communication | 3 | 368.46 | 1,105.38 |
|  | TOTAL |  |  |  | 45,015.60 |

Annex K: Description of Demonstrations

Annex K1: Pilot Demonstration Concept Note #1 – Guaranteed EPC: Government Building

| - Title | Guaranteed Energy Performance Contracting Pilot Demonstration in Government Buildings |  |  |
| --- | --- | --- | --- |
| - Contract Model | Guaranteed Saving |  |  |
| - Proposed Location | Government Building: LKPP Building |  |  |
| - Brief Description |  |  |  |
| - Estimated Number of Lamps Involved | 7,391 pieces |  |  |
| - Estimated Total Load | 124 kW |  |  |
| - Planned Activities | Phase 1: Project Development Phase 2: Implementation Phase 3: Performance Contracting Period Phase 4: Replication Preparation |  |  |
| - Expected Results | Energy Saving | 223 – 292 MWh p. a |  |
|  | Emission Reduction | 181 – 236 tCO2eq p. a |  |
|  | Cost Saving | USD 26,713 – 34,970 p. a |  |
| - Monitoring, Verification and Enforcement Plan | Lighting Retrofit | Product Standard Compliance |  |
|  |  | Product Warranty |  |
|  |  | Installation Safety |  |
|  |  | Commissioning |  |
|  |  | Waste Management |  |
|  | Saving Performance | Basic Functionality |  |
|  |  | Electric Current |  |
|  |  | Electric Voltage |  |
|  |  | Luminous Flux |  |
|  | Financial Settlement | Proper Financial Accounting |  |
|  |  | Service Payment |  |
|  |  | Below/beyond-standard compensation |  |
|  |  | Installment Payment |  |
|  |  | Project Close-Out |  |
| - Host selection criteria | - Energy Utilization Index - Potential Savings - Co-financing commitment - Replication Impact - Technical Compliance |  |  |
| - ESCO selection criteria | - Qualification - Project History - Pre-Energy Audit - Contracting Proposal Compliance - Bankability |  |  |
| - Responsibility Matrix | ADLIGHT | Responsible for host and ESCO selection, and work closely with ESCO in monitoring, verification, enforcement activities in the project. ADLIGHT will also remain providing technical assistance during the replication phase. |  |
|  | Financial Institution | Responsible for providing loans, channeling the fund, collecting it back based on installment scheme, if applicable |  |
|  | Loan Guarantee Agency, e.g. IIGF | Responsible for sharing the risks involved by providing access to loan guarantee funds, if applicable |  |
|  | Energy User (host) | Responsible for the investment and for paying the service received from ESCO based on the contract, supporting ESCO in giving access to do audit and installation activities, procuring the lights, and paying back the loan received from financial institution for the up-front cost |  |
|  | ESCO | Responsible for designing the project, implementing it, and reporting the progress and ultimately ensuring the savings expected from the project. |  |
| - Estimated Budget | Project Development |  | USD 12,500 |
|  | Implementation |  | USD 71,500 |
|  | Performance Contracting |  | USD 19,000 |
|  | Replication Preparation |  | USD 15,000 |
|  | Total |  | USD 118,000 |
| - Implementation Timeline | Project Development | July to August 2018 |  |
|  | Implementation | September to December 2018 |  |
|  | Contracting Period | January 2019 to December 2020 |  |
|  | Replication Preparation | July to September 2019 |  |

Introduction

The Minister of Energy and Mineral Resources (MEMR) in Regulation Nr.13/2012 has made a clear statement that all government building in national, provincial and municipal level must implement the national energy efficiency program, including in lighting system. The energy efficiency projects conducted in government buildings becomes the initial attempt for energy management that will support the reduction of energy cost in all buildings. It can motivate other government building in the same or in different regions.

However, only few of the government building managements have the adequate capability to implement this program. Besides of the lack of knowledge in energy efficiency, the limited budget resources, the hesitation in relying on new technology, the procurement is also facing various restrictions from national and regional procurement regulations. The project demonstration attempts to lift these barriers by delivering the energy efficiency project by the model of Energy Performance Contracting business model (EPC).

EPC shifts the focus away from selling energy efficient lights towards the desired benefits and services derived from the use of the technology. In this project demonstration, the said benefit is the energy saving gained from retrofitting lighting in buildings to LED lamps.

Due to its complexity, energy performance contracting project will involve a third-party company which is well known as the Energy Services Company (ESCO). ESCO provides a broad range of energy solutions including designs and implementation of energy savings projects, retrofitting, and risk management.

The MEMR through in Regulation Nr.14/2016 regulated two kinds of Energy Performance Contracting involving ESCO; the Guaranteed Saving Performance Contract, and the Shared Saving Performance Contract. For government building, the guaranteed saving model is more acceptable and less conflicting with public procurement regulations.

Guaranteed Energy Saving Performance Contract

The ESCO mainly provides technical services: design, installation and operation for which they are paid for by the client (e.g. on monthly basis). In the Guaranteed Savings model the client is making the investment in the (lighting) equipment. The client can pay the ESCO for its technical services from the energy cost savings. In this case, the savings will be guaranteed by the ESCO, during the contract period that has been agreed beforehand. For efficiency project that requires high amount of funding, the energy user will most likely rely on a financial institution.

ESCO will guarantee the energy saving to pay back the investment that the energy user has invested. If the energy saving turns out to be less than guaranteed, ESCO is obliged to compensate the amount of the loss the energy user suffers. Conversely, if the energy saving exceeds the expectation, the energy user should share the surplus saving based on the proportion that has been agreed in the contract.

Financial Mechanism and Sustainability

The demo host government agency building owner, LKPP, has been strategically pre-selected because of its role in government procurement and its involvement in the project will lead to its own appreciation of the EE lighting program and show other similarly situated government agencies the benefits of the program. The project will provide investment support in terms of procurement and installation of EE lighting devices co-shared with LKPP as user and investor In close coordination with LKPP, The project will also provide technical assistance in doing the investment grade energy audits, formulation of EPC and financial arrangements, MVE and preparation and start-up implementation of replication plans. The project will provide technical assistance in developing the procurement policy and guidelines for EE lighting projects in Component 2, drawing from the experience of LKPP in this demo which is expected to be sustainable owing to the energy savings and GHG reduction in shifting to EE lighting systems. As described above, the scheme will follow the “Guaranteed Savings” ESCO model, with the energy user as the government agency owner of the building investing on the lamp replacements and efficient lighting systems and the ESCO being contracted for its services to realize the potential economic and environmental benefits. For purposes in demonstrating this scheme by the ADLIGHT project, the investment support and technical assistance will involve such up-front costs that usually become hurdles for coming to EE investment initiatives even while there are potential benefits that have been identified. The project will remove these barriers and pave the way attract numerous government agency building owners to follow this developmental route for more efficient and sustainable operations. Once these developmental concerns are addressed, the EE lighting program for government buildings will be properly launched and the sustaining mechanisms will be put in place for MEMR to follow through and sustain through the effective implementation of the replication plan that will be initiated within the project period. After addressing the program-related up-front costs that will be supported by GEF project, the EE lighting program will continue to be supported by the MEMR as part of its regular administrative and monitoring function while the targeted government agencies as building owners and energy users can already budget for its own EE lighting transformation requirement that are sufficiently justified and implemented under the approved procurement plans and guidelines resulting from these project barrier removal activities.

Proposed Location

The Policy Institute for Public Procurement (Lembaga Kebijakan Pengadaan Publik/LKPP) is a suitable and potential government building where this project demonstration can take place. It has a significant number of lamps, with almost none of efficient lights. As the national body that regulates public procurement, it has high replication impact when it successfully become the role model of ESCO Guaranteed Savings model for other government buildings.

Expected Results

Annual Energy Saving

Energy efficiency project is using technology that requires less energy to perform the similar function. By replacing lamps into LED lights that consumes lower energy but still give at least the same lighting, the total annual energy saving is expected to reach the range 223 to 292 MWh.

Annual Emission Reduction

Based on the data released by PLN the emission factor for electricity production in Indonesia in year 2016 is 0.808 tons CO2eq/MWh. Thus, the annual emission reduction is estimated in the following to reach the range 181 to 236 tCO2eq.

Annual Cost Saving

The LKPP Building is categorized as P2 (Government Level 2) in PLN (the national utility company) customer classification system. It has to pay IDR 1,614 per kWh (include tax) electric usage. The annual cost saving for both buildings are estimated to reach the range USD 26,713 to 34,970.

Expected Annual Cost Saving

Monitoring, Verification and Enforcement Plan

During the implementation and performance contract period, ADLIGHT will carry out monitoring, verification, and enforcement to make sure the project runs as expected and befits to be a role model demonstration for future replications.

Estimated Budget

The costs in the project development will cover activities in selecting demonstration host and the ESCO, subsidizing the pre-energy audit and pre-feasibility study. The project will also subsidize the cost to conduct the investment grade energy audit and full feasibility study, and legalization process of contracts and agreements. The cost for project development phase activities is estimated to reach USD 12,500.

The project investment which consists of procurement of lighting and devices, installation and commissioning will be provided by energy user or through a financial institution. The project cost to implement the project is estimated to reach USD 71,500.

In the Performance Contracting Period, the ADLIGHT team as a form of assistance during the demonstration period will help the energy user who will be involved in every monitoring activity conducted by the ESCO in a periodical basis. In the verification activities, this project will also cover the cost to provide technical assistance of the financial accounting. The cost to run activities in this phase is estimated to reach USD 19,000.

In the period of replication preparation, the project will cover the cost to conduct seminars to disseminate results of project demonstration to identify potential replications and conduct workshops to formulate next steps recommendations. The cost to prepare the replication is estimated to reach USD 15,000.

The total cost to run this project demonstration is estimated to reach USD 118,000 consisting of USD 35,000 for GEF investment support, USD 46,500 for GEF technical assistance support and USD 36,500 for investment from the user.

| Activity | Estimated cost | GEF Investment Support | GEF TA Support | Investment from User |
| --- | --- | --- | --- | --- |
| PHASE 1: PROJECT DEVELOPMENT |  |  |  |  |
| Investment Grade Energy Audit | 4,000 |  | 4,000 |  |
| Energy Saving Performance Contract | 1,500 |  | 1,500 |  |
| Financing Agreement | 2,000 |  | 2,000 |  |
| Sub Total | 7,500 |  | 7,500 |  |
| PHASE 2: IMPLEMENTATION |  |  |  |  |
| Light and devices procurement | 60,000 | 30,000 |  | 30,000 |
| Installation | 10,000 | 5,000 |  | 5,000 |
| Commissioning | 1,500 |  |  | 1,500 |
| Sub Total | 71,500 | 35,000 |  | 36,500 |
| PHASE 3: PERFORMANCE CONTRACTING PERIOD |  |  |  |  |
| Operation and Maintenance | 3,000 |  | 3,000 |  |
| Monitoring | 8,000 |  | 8,000 |  |
| Verification | 5,000 |  | 5,000 |  |
| Enforcement | 3,000 |  | 3,000 |  |
| Sub Total | 19,000 |  | 19,000 |  |
| PHASE 4: REPLICATION PREPARATION |  |  |  |  |
| Replication potential identification | 17,000 |  | 17,000 |  |
| Next steps recommendation for replication | 3,000 |  | 3,000 |  |
| Sub Total | 20,000 |  | 20,000 |  |
| Total | 118,000 | 35,000 | 46,500 | 36,500 |

Implementation Timeline

The host stipulation and ESCO selection is the main priority activity as soon as the project demonstration begins, in the first quarter of 2019. The audit, contract, and the agreements will be signed right after it, at the fourth quarter of the first year, followed by the implementation of the project at the same term. Thus, the performance contracting period can begin right at the beginning of the second year and could last until the end of the project period or even earlier, depends on the feasibility study and contract agreement later. After six months operating, the saving from the LED light is expected to show an indication of a successful business model. Thus, the replication preparation by disseminating the result of the project demonstration can already be started in the fourth quarter of 2019.

Annex K2: Pilot Demonstration Concept Note #2 – Shared Saving EPC: Commercial Building

| - Title | Shared Energy Performance Contracting Project Demonstration in Commercial Buildings |  |  |
| --- | --- | --- | --- |
| - Contract Model | Shared Saving |  |  |
| - Proposed Location | Commercial Building: BRI Makassar Building |  |  |
| - Brief Description |  |  |  |
| - Estimated Number of Lamps Involved | 1,367 pieces |  |  |
| - Estimated Total Load | 44 kW |  |  |
| - Planned Activities | Phase 1: Project Development Phase 2: Implementation Phase 3: Performance Contracting Period Phase 4: Replication Preparation |  |  |
| - Expected Results | Energy Saving |  | 69 – 89 MWh p. a |
|  | Emission Reduction |  | 56 – 71 tCO2eq p. a |
|  | Cost Saving |  | USD 8,225 – 10,541 p. a |
| - Monitoring, Verification and Enforcement Plan | Lighting Retrofit |  | Product Standard Compliance |
|  |  |  | Product Warranty |
|  |  |  | Installation Safety |
|  |  |  | Commissioning |
|  |  |  | Waste Management |
|  | Saving Performance |  | Basic Functionality |
|  |  |  | Electric Current |
|  |  |  | Electric Voltage |
|  |  |  | Luminous Flux |
|  | Financial Settlement |  | Proper Financial Accounting |
|  |  |  | Service Payment |
|  |  |  | Below/beyond-standard compensation |
|  |  |  | Installment Payment |
|  |  |  | Project Close-Out |
| - Host selection criteria | - Energy Utilization Index - Potential Savings - Co-financing commitment - Replication Impact - Technical Compliance |  |  |
| - ESCO selection criteria | - Qualification - Project History - Pre-Energy Audit - Contracting Proposal Compliance - Bankability |  |  |
| - Responsibility Matrix | ADLIGHT |  | Responsible for host and ESCO selection, and work closely with ESCO in monitoring, verification, enforcement activities in the project. ADLIGHT will also remain providing technical assistance during the replication phase. |
|  | Financial Institution |  | Responsible for providing loans, collecting repayments back based on installment scheme, if applicable. |
|  | Loan Guarantee Agency, e.g. IIGF |  | Responsible for sharing the risks involved by providing access to loan guarantee funds, if applicable. |
|  | Energy User (host) |  | Responsible for paying the service received from ESCO based on the contract, supporting ESCO in giving access to do audit and installation activities, procuring the lights, and paying back the loan received from financial institution for the up-front cost |
|  | ESCO |  | Responsible for designing the project, implementing it, and reporting the progress. |
| - Estimated Budget | Project Development | USD 10,500 |  |
|  | Implementation | USD 16,500 |  |
|  | Performance Contracting | USD 15,500 |  |
|  | Replication Preparation | USD 8,000 |  |
|  | Total | USD 50,000 |  |
| - Implementation Timeline | Project Development | July to August 2018 |  |
|  | Implementation | January to March 2019 |  |
|  | Contracting Period | April 2019 to March 2021 |  |
|  | Replication Preparation | September to December 2019 |  |

Introduction

Commercial buildings have high energy needs and can put great strain on the nation's power grids during peak periods. Developing more efficient buildings helps ensure a steady supply of affordable power and significantly lowers operating costs for business.

Energy saving in commercial buildings, including lighting system, can be implemented through Shared Savings ESCO business model. This shifts the focus away from selling energy efficient lights towards the desired benefits and services derived from the use of the technology. In this project demonstration, the said benefit is the energy saving gained from retrofitting lighting in buildings to LED lamps.

The project will involve a third-party company, the Energy Services Company (ESCO)to provide a broad range of energy solutions including designs and implementation of energy savings projects, retrofitting, and risk management.

Besides of the lack of technical knowledge to implement this program, the lack of schemes from financial institution to fund this kind of project remains the biggest issue.

The MEMR through in Regulation Nr.14/2016 regulated two kinds of Energy Performance Contracting involving ESCO; the Guaranteed Saving Performance Contract, and the Shared Saving Performance Contract. In this pilot the ESCO Shared Saving model will be tested.

Shared Energy Saving Performance Contract

Shared Energy Saving is a financing agreement in which a private company offers to implement an energy efficiency program, including capital improvements (like lighting upgrades) in exchange for a portion of the energy cost saving. In negotiating a successfully shared energy performance contract (SEPC), a third-party financing entity will provide funding to cover the initial upfront costs of the energy-efficient lights. The ESCO providing the investment and LED lamps will return the borrowed investment to the ESCO from the monthly saving. Over the term of the shared savings agreement, after the balance is paid off in entirety, the energy user retains future energy saving and incurs lower energy expenditures for the lifetime of their buildings.

Financial Mechanism and Sustainability

The energy user as a commercial entity and the ESCO share the risk and provide the fund for the investment to replace the lamps and cover other necessary costs.

The project investment can be in a form of equity or loan by the ESCO with a certain interest rate that applies within the financial institution with a loan guarantee back up that can be provided by a loan guarantee agency such as the IIGF. The loan has to be paid back through an installment scheme from the savings earned post-retrofit of the lamps based on the agreement. The financial institution will collect the loan back every month or based on a period agreed in the contract. Eventually, the financial institution is expected to receive the fund back with additional income generated from the interest. It will then provide the cost recovery to finance other replication EPC projects by the bank on a sustained basis.

In this financing model, the project will demonstrate that ESCOs can fit in the EE lighting transformation program and ESCOs can be the investor for the projects to be financed through the financial institutions in partnership with building owners who are both convinced of the EE lighting energy and environmental benefits. The ADLIGHT project will provide significant support to develop ESCOs attain their financial and technical capability, as part of the project’s barrier removal technical assistance initiatives and therefore enhance the trust in ESCOs for them to be qualified and able in developing and implementing EE lighting projects as part of their overall portfolio.

It should be noted that this mechanism is not yet in place but will be part of the project considering that the project itself cannot provide loans or guarantees per UNDP policy.

Proposed Location

The BRI Makassar building is a suitable and potential building where this project demonstration for commercial building can be conducted. The intensive and frequently extended working hours up to midnight causes a significant increase in the energy consumption, especially the use of lighting system which consists of mostly conventional lights. Therefore, conducting this pilot project in a financial institution building can give the empirical understanding of the financial benefits of retrofitting conventional lighting system to efficient ones. It is expected that more financial institutions open up their facilities to finance energy efficiency project based on EPC model business as an outcome of this project demonstration.

Expected Results

Annual Energy Saving

Energy efficiency project is using technology that requires less energy to perform the similar function. By replacing lamps into LED lights that consumes lower energy but still give at least the same lighting, the total annual energy saving is expected to reach the range of 69 to 88 MWh.

Annual Equivalent CO2 Reduction

Based on the data released by PLN the emission factor for electricity production in Indonesia in year 2016 is 0.808 tons CO2eq/MWh. Thus, the annual emission reduction is estimated in the following table to reach the range of 56 to 71 tCO2eq.

Annual Cost Saving

The BRI Makassar Building is categorized as B2 (Business Level 2) in PLN (the national utility company) customer classification system. It has to pay IDR 1,614 per kWh (include tax) electric usage. The annual cost saving for both buildings are estimated to reach the range of USD 8,225 to 10,541.

Monitoring, Verification and Enforcement Plan

During the implementation and performance contract period, ADLIGHT will carry out monitoring, verification, and enforcement to make sure the project runs as expected and befits to be a role model demonstration for future replications.

Estimated Budget

The costs in the project development will cover activities in selecting demonstration host and the ESCO, subsidizing the pre-energy audit and pre-feasibility study. The project will also subsidize the cost to conduct the investment grade energy audit and full feasibility study, and legalization process of contracts and agreements. The cost for project development phase activities is estimated to reach USD 10,500.

The project investment which consists of procurement of lighting and devices, installation and commissioning will be shouldered by the ESCO at a cost estimated to reach USD 16,500.

In the Performance Contracting Period, the ADLIGHT team will be involved in every monitoring activity conducted by the ESCO in a periodical basis. In the verification activities, this project will also cover the cost to provide technical assistance of the financial accounting. The cost to run activities in this phase is estimated to reach USD 15,500.

In the period of replication preparation, the project will cover the cost to conduct seminars to disseminate results of project demonstration to identify potential replications and conduct workshops to formulate next steps recommendations. The cost to prepare the replication is estimated to reach USD 8,000.

The total cost to run this project demonstration to be supported by GEF is estimated to reach USD 18,000 consisting of USD 18,000 for technical assistance support energy audit, EPC and financial agreements documentation. The companies as users are expected to invest USD 15,000 to support operation, maintenance and MVE. The ESCO will invest USD 16,500 for procurement, installation and commissioning of EE lighting.

|  | Estimated Cost | ESCO Investment | GEF TA Support | Investment from User |
| --- | --- | --- | --- | --- |
| PHASE 1: PROJECT DEVELOPMENT |  |  |  |  |
| Investment Grade Energy Audit | 2,000 |  | 2,000 |  |
| Energy Saving Performance Contract | 1,500 |  | 1,500 |  |
| Financing Agreement | 2,000 |  | 2,000 |  |
| Sub Total | 5, 000 |  | 5,000 |  |
| PHASE 2: IMPLEMENTATION |  |  |  |  |
| Light and devices procurement | 12,000 | 12,000 |  |  |
| Installation | 3,000 | 3,000 |  |  |
| Commissioning | 1,500 | 1,500 |  |  |
| Sub Total | 16,000 | 16,500 |  |  |
| PHASE 3: PERFORMANCE CONTRACTING PERIOD |  |  |  |  |
| Operation and Maintenance | 1,500 | 1,500 |  |  |
| Monitoring | 6,000 | 6,000 |  |  |
| Verification | 5,000 | 5,000 |  |  |
| Enforcement | 3,000 | 3,000 |  |  |
| Sub Total | 15,500 | 15,500 |  |  |
| PHASE 4: REPLICATION PREPARATION |  |  |  |  |
| Replication potential identification and planning | 10,000 |  | 10,000 |  |
| Next steps recommendation for replication | 3,000 |  | 3,000 |  |
| Sub Total | 13,000 |  | 13,000 |  |
| Total | 50,000 | 32,000 | 18,000 |  |

Implementation Timeline

The host stipulation and ESCO selection is the main priority activity soon as the project demonstration begins, in the first quarter of 2019. The audit, contract, and the agreements will be signed right after it, at the fourth quarter of the first year, followed by the implementation of the project at the same term. Thus, the performance contracting period can begin right at the beginning of the second year and could last until the end of the project period or even earlier, depends on the feasibility study and contract agreement later. After six months operating, the saving from the LED light is expected to show an indication of a successful business model. Thus, the replication preparation by disseminating the result of the project demonstration can already be started in the fourth quarter of 2019.

Annex K3: Pilot Demonstration Concept Note #3– Guaranteed EPC: Street Lighting

| Title | PPP Project Demonstration for City of Surakarta (+ City to be determined)– Guaranteed Savings |  |
| --- | --- | --- |
| Proposed Location | City of Surakarta (+ City to be determined) |  |
| Brief Description | The city of Surakarta (+ City to be determined) is retrofitting their streetlight from conventional streetlight to LED streetlight using a PPP scheme. There are 21,222 light points, 6,045 are under metering contract and 15,177 are under lump sum contract. The PPP scheme besides retrofitting the existing lights, it will include installing meter on the light points under the lump sum contract. |  |
| Number of Lamps Involved | ± 21,222 light points |  |
| Estimated Total Load | 77,816,862.50 KW |  |
| Planned Activities | Phase 1: Project Development Phase 2: Implementation Phase 3: Performance Contracting Period Phase 4: Replication Preparation |  |
| Expected Results | Annual Energy Saving | ± 22,465.98 MWh |
|  | Annual Emission Reduction | 16,659.85 tons CO2 |
|  | Annual Cost Saving | IDR 35,035,006,078 |
| Monitoring, Verification and Enforcement Plan | Lighting Retrofit | Product Standard Compliance |
|  |  | Product Warranty |
|  |  | Installation Safety |
|  |  | Commissioning |
|  |  | Waste Management |
|  | Saving Performance | Basic Functionality |
|  |  | Electric Current |
|  |  | Electric Voltage |
|  |  | Luminous Flux |
|  |  | Below Standard Compensation |
|  |  | Project Close Out |
| Host selection criteria | - Energy Utilization Index - Potential Savings - Co-financing commitment - Replication Impact - Technical Compliance - Pre-FS readiness |  |
| PPP selection criteria | - Political Will of Executive and Legislative - Partnership with PLN - Adequate Budget Location - Bankability - Streetlight Management Skill |  |
| Responsibility Matrix | ADLIGHT | Responsible for host and PPP selection, provide the fund for finalizing PPP final business case and to assist on the tendering, contracting, and supervision of the deployment of the project. |
|  | Financial Institution | Responsible for providing the fund through loans by the energy user, collecting it back based on installment scheme and later channel the cost recovery for replicative projects by itself on a sustained basis, if applicable. |
|  | City (host) | Responsible to prepare all legal requirements in order for the contract to be awarded and executed to the PPP contract winner as stated on the Presidential Regulation no. 38/2015. The city must assist in the coordination between PLN and the PPP contract winner to make sure on the transparency of the energy billing. |
|  | PPP Contractor (ESCO or project developer) | Responsible for designing the project, providing the funds through equity or loans with loan guarantee back up by a Loan guarantee facility, such as IIGF, implementing it, reporting the progress, and maintenance of the project. |
| - Estimated Budget | Installing metering for street lighting | USD 100,000 |
|  | Project Final Business Case and Contracting Supervision | USD 100,000 |
|  | Investment Assistance & Installation | USD 591,500 |
|  | Contracting, O&M and Replication Preparation | USD 28,000 |
|  | Total | USD 819,500 |
| - Implementation Timeline | Project Final Business Case and Contracting Supervision | January 2019 to June 2019 |
|  | Investment Assistance | January 2019 to End of Contract |
|  | Replication Preparation | June 2019 to January 2021 |

Introduction

As provided in government issuances and ministerial decrees regarding the PPP rules in infrastructure (to which energy efficiency projects are included), the National and Regional Governments must follow the relevant regulations if they want to develop and implement a PPP project for energy efficiency project infrastructure.

With the Presidential Decree No. 38 year 2015, it enables regional government to do PPP in energy conservation infrastructure; many cities in Indonesia want to retrofit their old conventional street lighting to high energy efficiency street lighting. In line with this decree, the Minister of Energy and Mineral Resources issued a Ministry Regulation No.14 Year 2016 about Energy Conservation Service Company (ESCO). This regulation covers two kinds of ESCO modalities on treatment of energy savings: (a) the Guaranteed Energy Saving Performance Contract (Guaranteed ESPC) and (b) Shared Energy Saving Performance Contract (Shared ESPC). However, the Ministry of Finance stated that for government, it can only follow a Guaranteed ESPC for the PPP. In Guaranteed ESPC, the ESCO guarantees to the amount of attainable energy saving achievements.

Proposed Financial Mechanism and Sustainability

ADLIGHT plans to support this demonstration project by providing the fund for partial investment to retrofit the streetlight since this will involve new designs and protection systems that need to be developed and to assist the PPP project until contract signing. The EELs for street lighting are quite different from regular LEDs used in buildings.

The project will shoulder the up-front cost in terms of the initial procurement and installation costs of the EE lighting systems and will provide technical assistance in establishing a municipality-based cost-recovery scheme. The municipality can use the fund utilized for the investment support and recovered from the savings to be pooled as seed money to develop a facility that will be used to accumulate and further create more funds for future street lighting projects. Through the facility, the municipality will be allowed to keep the energy cost savings in order to pool the savings in a “revolving fund”. With the means in the revolving fund, the municipalities will then be able to continue implementing future EE street lighting projects.

The city of Surakarta Streetlight Billing

The electricity bills for the streetlight have increased from year to year for the City of Surakarta, the billing for electricity has increased rapidly. The rapid increase is caused by two factors, the energy price to generate electricity has gone up and the Government of Indonesia has lifted subsidy for streetlight bills. As of 2015, the City of Surakarta streetlight bill was Rp. 44,035,439,005 or around USD 3,310,935. In 2017, the city estimated the streetlight bill will be Rp. 44,400,000,000 or around USD 3,338,346.

Monitoring, Verification and Enforcement Plan

During the implementation and performance contract period, the ADLIGHT project will carry out monitoring, verification, and enforcement (MVE) to make sure the demo project can perform as expected and can become a role model demonstration for future replication.

On March 20, 2015, the Indonesian President issued a Presidential Decree no. 38 year 2015, the presidential decree is about Kerjasama Pemerintah dengan Badan Usaha dalam penyediaan infrastruktur (KPBU)/Public Private Partnership in the provision of infrastructure (PPP). In the Presidential Decree, there are nineteen (19) infrastructures that can be partnership, and one of the infrastructures is energy conservation. The Presidential Decree required a derivative regulation from Ministry or Institution that handles national development planning, finance and states assets, policy on government goods and services, and domestic government. As instructed by the presidential decree the Ministry and Institution issues the necessary regulation.

The total cost to run this project demonstration is estimated to reach USD 819,500 which is composed of GEF Investment support of up to USD 598,500 (resources to be shared over 2 cities) for the procurement of EE lighting system and installation of new power line and commissioning which could be acquired through regular procurement procedures and USD 60,000 for technical assistance support. The city government as user will invest USD 463,750 as counterpart in terms of costs of metering, investment costs for lighting equipment, consultant costs and operation, maintenance and MVE.

| Activity | Estimated Cost PER CITY | GEF Investment Support | GEF Investment Support | GEF TA Support | Investment from CITY A | Investment from CITY B |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | CITY A | CITY B |  |  |  |
| PHASE 0: PREPARATIONS FOR REVOLVING FUND SET-UP |  |  |  |  |  |  |
| Installing metering for street lighting | 100,000 |  |  |  | 100,000 | 100,000 |
| PHASE 1: OUTLINE & FINAL BUSINESS CASE |  |  |  |  |  |  |
| Final business case consultant, financial and legal consultant | 100,000 |  |  | 50,000 | 50,000 | 50,000 |
| Subtotal | 100,000 |  |  | 50,000 | 50,000 | 50,000 |
| PHASE 2: IMPLEMENTATION |  |  |  |  |  |  |
| Light and devices procurement | 354,900 | 177,450 | 177,450 |  | 177,450 | 177,450 |
| Installation new power line & commissioning | 236,600 | 118,300 | 118,300 |  | 118,300 | 118,300 |
| Subtotal | 591,500 | 295,750 | 295,750 |  | 295,750 | 295,750 |
| PHASE 3: PPP CONTRACTING PERIOD |  |  |  |  |  |  |
| Operation and Maintenance | 2,000 |  |  |  | 2,000 | 2,000 |
| Monitoring | 8,000 |  |  |  | 8,000 | 8,000 |
| Verification | 6,000 |  |  |  | 6,000 | 6,000 |
| Enforcement | 2,000 |  |  |  | 2,000 | 2,000 |
| Subtotal | 18,000 |  |  |  | 18,000 | 18,000 |
| PHASE 4: REPLICATION PREPARATION |  |  |  |  |  |  |
| Replication potential identification | 8,000 |  |  | 8,000 |  |  |
| Next steps recommended for replication | 2,000 |  |  | 2,000 |  |  |
| Subtotal | 10,000 |  |  | 10,000 |  |  |
| TOTAL BUDGET | 819,500 | 295,750 | 295,750 | 60,000 | 463,750 | 463,750 |

Implementation Timeline

The host and ESCO selection is the main priority activity as soon as the project demonstration begins, at the first quarter of 2019. The audit, contract, and the agreements will be signed right after it, in the fourth quarter of the first year, followed by the implementation of the project at the same term.

Thus, the performance contracting period can begin right at the beginning of the second year and could last until the end of the project period or even earlier, depends on the feasibility study and contract agreement later. After six months operating, the saving from the LED light is expected to show an indication of a successful business model. Thus, the replication preparation by disseminating the result of the project demonstration can already be started in the fourth quarter of 2019.

Annex L: GHG Emission Reduction Estimates

Business-as-usual (BAU) estimations for energy saving and CO2 emission have been made based on the forecast scenarios in the Electricity Power Supply Business Plan (RUPTL) issued by the Ministry of Energy and Mineral Resources (MEMR). In the last RUPTL for 2017-2026, the electricity consumption and customer growth are presented.

- Electricity demand

The history of electricity consumption in Indonesia in the period 2008 to 2016 is shown in Table L.1. The history of number of customer is shown in Table L.2.

Table L.1. History of electricity consumption

| Year | Sector (in TWh) |  |  |  |  |  | Total |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Residential | Industry | Commercial | Social | Gov. Office | Street Lighting |  |
| 2008 | 50.18 | 47.97 | 22.93 | 3.08 | 2.10 | 2.76 | 129.02 |
| 2009 | 54.95 | 46.20 | 24.53 | 3.31 | 2.33 | 2.89 | 134.21 |
| 2010 | 59.83 | 50.99 | 26.39 | 3.64 | 2.63 | 3.00 | 146.46 |
| 2011 | 65.11 | 54.73 | 28.31 | 3.99 | 2.79 | 3.07 | 157.99 |
| 2012 | 72.13 | 60.18 | 30.99 | 4.50 | 3.06 | 3.14 | 173.99 |
| 2013 | 77.21 | 64.38 | 34.50 | 4.94 | 3.26 | 3.25 | 187.54 |
| 2014 | 85.42 | 87.25 | 36.30 | 5.55 | 3.45 | 3.33 | 221.30 |
| 2015 | 88.68 | 64.08 | 36.98 | 5.94 | 3.72 | 3.45 | 202.85 |
| 2016 | 95.33 | 68.93 | 39.53 | 6.36 | 3.96 | 3.71 | 217.83 |

Note: 2016 data is an estimation

Table L.2. Number of Customers

| Year | Sector |  |  |  |  |  | Total |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Residential | Industry | Commercial | Social | Gov. Office | Street Lighting |  |
| 2008 | 36,025,071 | 47,536 | 1,716,046 | 838,129 | 103,821 | 113,483 | 38,844,086 |
| 2009 | 37,099,830 | 47,900 | 1,879,429 | 873,721 | 108,749 | 120,269 | 40,129,897 |
| 2010 | 39,324,520 | 48,675 | 1,912,150 | 909,312 | 113,676 | 127,054 | 42,435,387 |
| 2011 | 42,577,542 | 50,365 | 2,049,361 | 963,766 | 120,246 | 133,865 | 45,895,145 |
| 2012 | 46,219,780 | 52,661 | 2,218,342 | 1,032,830 | 128,252 | 143,384 | 49,795,249 |
| 2013 | 50,116,127 | 55,456 | 2,418,431 | 1,110,450 | 137,762 | 157,892 | 53,996,118 |
| 2014 | 53,309,325 | 58,350 | 2,626,160 | 1,181,779 | 146,321 | 171,299 | 57,493,234 |
| 2015 | 56,605,260 | 63,314 | 2,894,990 | 1,261,516 | 156,782 | 186,118 | 61,167,980 |
| 2016 | 59,539,981 | 69,381 | 3,064,079 | 1,346,633 | 273,305 | 324,103 | 64,617,482 |

Note: 2016 data is an estimation

Energy share of electricity production in the year 2016 is shown in Figure L.1. Based on the data released by PLN, the emission factor for electricity production in Indonesia in year 2016 is 0.808 ton CO2eq/MWh. This emission factor was used for CO2 emission calculation.

Figure L.1: Energy Share to Produce Electricity and Sectoral Electricity Usage Share in Year 2016

Based on the historical data and GDP, population growth, the projection of electricity consumption and customers has been developed in RUPTL. In the RUPTL, the projection is made until 2026. The average growth rate from year 2023 to 2026 is used to estimate the projection in year 2026 to 2030. The projection of electricity consumption and number of customer in each sector are shown in Table L.3 and Table L.4, respectively.

Table L.3: Projection of Electricity Consumption

| Year | Sector (in TWh) |  |  |  |  |  | Total |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Residential | Industry | Commercial | Social | Gov. Office | Street Lighting |  |
| 2017 | 102.16 | 74.41 | 43.17 | 6.81 | 4.24 | 3.97 | 234.77 |
| 2018 | 109.64 | 80.97 | 47.70 | 7.30 | 4.55 | 4.25 | 254.40 |
| 2019 | 117.86 | 88.15 | 52.22 | 7.84 | 4.88 | 4.57 | 275.52 |
| 2020 | 126.30 | 99.20 | 57.59 | 8.45 | 5.26 | 4.92 | 301.72 |
| 2021 | 136.24 | 109.95 | 63.31 | 9.11 | 5.67 | 5.30 | 329.58 |
| 2022 | 145.80 | 120.27 | 69.10 | 9.82 | 6.11 | 5.72 | 356.81 |
| 2023 | 155.81 | 131.21 | 75.41 | 10.58 | 6.59 | 6.16 | 385.75 |
| 2024 | 166.37 | 143.24 | 82.26 | 11.40 | 7.10 | 6.64 | 417.00 |
| 2025 | 177.50 | 155.43 | 89.82 | 12.29 | 7.65 | 7.15 | 449.84 |
| 2026 | 189.23 | 166.61 | 97.94 | 13.23 | 8.24 | 7.71 | 482.97 |
| 2027 | 201.58 | 178.72 | 106.76 | 14.26 | 8.88 | 8.30 | 518.50 |
| 2028 | 214.56 | 190.51 | 116.49 | 15.36 | 9.57 | 8.95 | 555.44 |
| 2029 | 228.19 | 200.60 | 126.94 | 16.55 | 10.31 | 9.63 | 592.22 |
| 2030 | 242.50 | 211.35 | 138.27 | 17.82 | 11.10 | 10.38 | 631.42 |

Table L.4: Projection of Number of Customers

| Year | Sector |  |  |  |  |  | Total |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Residential | Industry | Commercial | Social | Gov. Office | Street Lighting |  |
| 2017 | 62,251,000 | 72,000 | 3,252,000 | 1,419,456 | 175,923 | 208,621 | 67,379,000 |
| 2018 | 64,782,000 | 74,000 | 3,461,000 | 1,496,566 | 185,480 | 219,954 | 70,219,000 |
| 2019 | 66,703,000 | 77,000 | 3,699,000 | 1,580,758 | 195,914 | 232,328 | 72,488,000 |
| 2020 | 68,572,000 | 79,000 | 3,967,000 | 1,672,818 | 207,324 | 245,858 | 74,744,000 |
| 2021 | 69,911,000 | 82,000 | 4,257,000 | 1,770,386 | 219,416 | 260,198 | 76,500,000 |
| 2022 | 70,960,000 | 85,000 | 4,571,000 | 1,874,248 | 232,289 | 275,463 | 77,998,000 |
| 2023 | 71,893,000 | 88,000 | 4,911,000 | 1,984,405 | 245,941 | 291,653 | 79,414,000 |
| 2024 | 72,685,000 | 91,000 | 5,279,000 | 2,100,071 | 260,276 | 308,653 | 80,724,000 |
| 2025 | 73,419,000 | 94,000 | 5,676,000 | 2,223,604 | 275,587 | 326,809 | 82,015,000 |
| 2026 | 74,118,000 | 98,000 | 6,105,000 | 2,353,432 | 291,677 | 345,890 | 83,312,000 |
| 2027 | 74,665,644 | 102,052 | 6,569,793 | 2,489,695 | 308,565 | 365,917 | 84,501,667 |
| 2028 | 75,148,792 | 106,157 | 7,071,746 | 2,635,182 | 326,597 | 387,300 | 85,675,773 |
| 2029 | 75,591,654 | 111,445 | 7,614,720 | 2,788,019 | 345,539 | 409,762 | 86,861,140 |
| 2030 | 75,875,974 | 116,863 | 8,203,587 | 2,948,363 | 365,411 | 433,329 | 87,943,526 |

- Electricity Demand for Lighting

To estimate electricity demand for lighting, several assumptions were used. The assumptions are presented in Table L.5.

Table L.5: Assumptions for Estimating Energy for Lighting

| Parameter | Sector |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | Residential | Industry | Commercial | Social | Gov. Office | Street Lighting |
| No of Lamps/costumer (En.lighten survey) | 8.35 | 600 | 60 | 20 | 100 | - |
| Average Wattage | 13.8 | 17.2 | 17.2 | 13.8 | 13.8 | - |
| Yearly operation hours | 2,920 | 2,880 | 4,015 | 3,168 | 3,456 | 4,380 |

In the survey of the Indonesian lighting market, the typical wattages of lamps sold in Indonesia are shown in Figure L.2.

Figure L.2: Wattage lighting survey in Indonesia

The energy for lighting in each sector is calculated using the following equation:

(1)

Where,  is number of costumer,  number of lamps in costumer ,

[Watt] is the average capacity of lamp and

[hours] is the average operating hours of the lamps in a year.

Based on those assumptions, the energy share for all lighting in Indonesia is estimated to be 18.81% in year 2016.

Figure L.3: Electricity for Lighting in each Sector in Year 2016

It is assumed that typical Indonesian lamps market is similar until 2030. The average number of lamps and wattage in every sector are constant until 2030. The projections of electricity for lighting until 2030 are estimated and shown in Table L.6.

Table L.6: Projection of Electricity for Lighting in every Sector

| Year | Sector (in TWh) |  |  |  |  |  | Total |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Residential | Industry | Commercial | Social | Gov. Office | Street Lighting |  |
| 2017 | 20.95 | 2.14 | 13.47 | 1.24 | 0.84 | 3.97 | 42.609 |
| 2018 | 21.80 | 2.20 | 14.34 | 1.31 | 0.88 | 4.25 | 44.780 |
| 2019 | 22.44 | 2.29 | 15.33 | 1.38 | 0.93 | 4.57 | 46.942 |
| 2020 | 23.07 | 2.35 | 16.44 | 1.46 | 0.99 | 4.92 | 49.231 |
| 2021 | 23.52 | 2.44 | 17.64 | 1.55 | 1.05 | 5.30 | 51.498 |
| 2022 | 23.88 | 2.53 | 18.94 | 1.64 | 1.11 | 5.72 | 53.805 |
| 2023 | 24.19 | 2.62 | 20.35 | 1.74 | 1.17 | 6.16 | 56.222 |
| 2024 | 24.46 | 2.70 | 21.87 | 1.84 | 1.24 | 6.64 | 58.750 |
| 2025 | 24.70 | 2.79 | 23.52 | 1.94 | 1.31 | 7.15 | 61.428 |
| 2026 | 24.94 | 2.91 | 25.30 | 2.06 | 1.39 | 7.71 | 64.303 |
| 2027 | 25.12 | 3.03 | 27.22 | 2.18 | 1.47 | 8.30 | 67.330 |
| 2028 | 25.29 | 3.16 | 29.30 | 2.30 | 1.56 | 8.95 | 70.550 |
| 2029 | 25.43 | 3.31 | 31.55 | 2.44 | 1.65 | 9.63 | 74.019 |
| 2030 | 25.53 | 3.47 | 33.99 | 2.58 | 1.74 | 10.38 | 77.693 |

- ADLIGHT Pilot Demonstration Projects

There are five (5) pilot demonstrations that will be implemented in the ADLIGHT project in developing and promoting ESCOs in the application of EELs in various potential groups of consumers: two (2) in buildings, two (2) in city street lighting and one (1) for the residential sector which will be participated in by MEMR in cooperation with government housing projects. These pilot demonstrations and saving potentials are shown in Table L.7.

Table L.7 ADLIGHT Pilot Demonstrations on ESCO to Boost LED Market Penetration

|  | Pilot 1 | Pilot 2 | Pilot 3 | Pilot 4 | Pilot 5 (residential) |
| --- | --- | --- | --- | --- | --- |
| Name | LKPP | BRI | City 1 | City 2 | MEMR 250,000 lamps |
| Type | Gov. office | Commercial | Street Lighting | Street Lighting | Change 7W CFL to 3W LED |
| Energy Baseline (MWh/Year) | 470.06 | 139.52 | 19,710 | 19,710 | 7,665 |
| Percent Saving | 48% | 48% | 64% | 64% | 57% |
| Source of Percent saving | Field survey |  | Field Survey |  |  |
| Energy Saving (MWh/Year) | 225.12 | 65.76 | 12,614.4 | 12,614.4 | 4,369.05 |
| Emission Reduction (ton CO2eq/year) | 181.9 | 53.13 | 10,192.43 | 10,192.43 | 3,530.19 |
| Year when Implemented | 2018 | 2018 | 2018 | 2019 | 2018 |
| Number of Replication | 1 | 7 | 1 | 1 | - |
| Year when replications were Implemented | 2019 | 2019 | 2019 | 2019 |  |

Results of Impact Calculations

The goal of ADLIGHT project is the reduction of GHG emissions due to reduced electricity consumption in lighting system in Indonesia. Assuming the project will start in 2018, the ADLIGHT Project will result in a cumulative electricity savings of 77.45 GWh (278,820,000 MJ) by 2020 or at the end of the project in Year 3 against a baseline electricity consumption of 40.98 TWh/year in 2016. The equivalent reduction of CO2 emissions is estimated at 62.57 kilotons (kt) CO2 by the year 2020.

Table L.8: Energy Saving and Emission Reduction of the Project

| ADLIGHT Project | Value | Notes |
| --- | --- | --- |
| I - Direct |  |  |
| Direct CO2 emission reductions (t CO2) | 548,766 | (1) |
| III– Indirect |  |  |
| Indirect CO2 emissions - top-down (tCO2) | 1,097,533 | (2) |
| GEF finance (US $) | 3,895,872 |  |
| Total emission reductions (t CO2) | 1,646,299 | (3) |
| Unit Abatement Cost (UAC) ($/tCO2) - (Direct savings) as per GEF CO2 emission reduction calculation methodology ($/tCO2) | 7.0 |  |
| Unit Abatement Cost (UAC) ($/tCO2) - (Direct + Indirect) as per GEF CO2 emission reduction calculation methodology ($/tCO2) | 2.36 |  |

- Must be considered for 10 years of direct CO2 emission reductions from all pilot projects and replications. Since this project focuses entire sector, cumulative emission reductions during economic lifetime (considered 10 years including project duration of 3 years)

- Based on GEF CO2 emission reduction calculation methodology, as it focuses entire sector. In this case it is the cumulative emission reduction for 10 year from best case of all sectors multiple by factor 0.5.

- Considered for 10 years of economic lifetime as per GEF guidelines (Direct + Indirect). This is calculated as (3) = (1)+(2).

- Energy saving and emission reduction of post projects

It is assumed that during the project, if all of the activities are implemented as planned, the lighting market in Indonesia will be significantly transformed into using high efficient lighting systems. In the case of ADLIGHT, there are two driving forces to attain energy savings. The first is the increasing efficiency of the lamps in the market due to technology development. The second saving comes from the rate of progress of replacing the old lamps into high efficient lamps, referred to as penetration rate. In the first kind of saving, the average of saving in each sector is different. It depends on the current baseline condition and the technology improvement in the future. The present saving and yearly increase in efficiency are presented in Table L.9. In the second kind of saving due to the increasing penetration rate, it will be divided into two scenario assumptions, i.e. conservative and optimistic penetration rates.

Table L.9: Percentages in Baseline Saving, Yearly Increase in Saving, and Projected Saving in 2040

| No | Sector | Baseline Saving | Yearly additional saving [2020-2039] | Final Saving in 2040 |
| --- | --- | --- | --- | --- |
| 1 | Residential | 57% | 1.20% | 79.8% |
| 2 | Industry | 48% | 1.50% | 76.5% |
| 3 | Commercial | 48% | 1.50% | 76.5% |
| 4 | Social | 48% | 1.50% | 76.5% |
| 5 | Government Office | 48% | 1.50% | 76.5% |
| 6 | Street Lighting | 64% | 1.00% | 83.0% |

  - Conservative Penetration Rate

For the conservative penetration scenario, the penetration rate increases 2% yearly and it is assumed to start in 2021. In this assumption, at the present and during the ADLIGHT project, the installed high efficient lighting is very small in comparison to number of lamps in Indonesia. ADLIGHT project will affect the market and the number will increase linearly. The calculation of the conservative penetration has been made during 2020 to 2040. The baseline and projection during 2016 – 2030 are shown in Table L.10.

  - Optimistic Penetration Rate

In this case, the percent share of implemented high efficient lighting (penetration rate) varies as a function of time (year) and calculated using the following logistic function.

(2)

For Indonesia case, Batih and Sorapipatana (2016) suggested the constant a and b which are validated in Thailand case. The constants are:   	     		                       	(3)

The calculation results for this case are presented in Table D.11.

Table L.10: Energy Saving and Emission Reduction during 2016 to 2030 for Conservative Penetration Rate Scenario

| Parameter |  | Base |  | Year 1 | Year 2 | Year 3 | ADLIGHT Post-Project |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 |
| BAU Electricity for Lighting [TWh/year] | 40.98 | 42.61 | 44.78 | 46.94 | 49.23 | 51.50 | 53.80 | 56.22 | 58.75 | 61.43 | 64.30 | 67.33 | 70.55 | 74.02 | 77.69 |
| BAU Emission [MtCO2eq/year] | 33.11 | 34.43 | 36.18 | 37.93 | 39.78 | 41.61 | 43.47 | 45.43 | 47.47 | 49.63 | 51.96 | 54.40 | 57.00 | 59.81 | 62.78 |
| Saving and Emission reduction from Demo |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Electricity saving [GWh/year] | - | - | - | 69.10 | 240.69 | 240.69 | 240.69 | 240.69 | 240.69 | 240.69 | 240.69 | 240.69 | 240.69 | 240.69 | 240.69 |
| Cumulative saving [GWh] | - | - | - | 69.10 | 309.79 | 550.47 | 791.16 | 1,031.85 | 1,272.54 | 1,513.23 | 1,753.91 | 1,994.60 | 2,235.29 | 2,475.98 | 2,716.67 |
| Emission reduction [kilo tCO2eq/year] | - | - | - | 55.83 | 194.48 | 194.48 | 194.48 | 194.48 | 194.48 | 194.48 | 194.48 | 194.48 | 194.48 | 194.48 | 194.48 |
| Cumulative emission reduction [kilo tCO2eq] | - | - | - | 55.83 | 250.31 | 444.78 | 639.26 | 833.73 | 1,028.21 | 1,222.69 | 1,417.16 | 1,611.64 | 1,806.11 | 2,000.59 | 2,195.07 |
| Saving and Emission reduction affected by ADLIGHT for all sectors |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Penetration rate for all sectors [%] |  | - | - | - | - | 2% | 4% | 6% | 8% | 10% | 12% | 14% | 16% | 18% | 20% |
| Saving due to increasing lighting efficacy [%] |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Residential |  |  | 57% | 58.2% | 59.4% | 60.6% | 61.8% | 63.0% | 64.2% | 65.4% | 66.6% | 67.8% | 57% | 58.2% | 59.4% |
| Industry |  |  | 48% | 49.5% | 51.0% | 52.5% | 54.0% | 55.5% | 57.0% | 58.5% | 60.0% | 61.5% | 48% | 49.5% | 51.0% |
| Commercial |  |  | 48% | 49.5% | 51.0% | 52.5% | 54.0% | 55.5% | 57.0% | 58.5% | 60.0% | 61.5% | 48% | 49.5% | 51.0% |
| Social |  |  | 48% | 49.5% | 51.0% | 52.5% | 54.0% | 55.5% | 57.0% | 58.5% | 60.0% | 61.5% | 48% | 49.5% | 51.0% |
| Gov. Office |  |  | 48% | 49.5% | 51.0% | 52.5% | 54.0% | 55.5% | 57.0% | 58.5% | 60.0% | 61.5% | 48% | 49.5% | 51.0% |
| Street Lighting |  |  | 64% | 65.0% | 66.0% | 67.0% | 68.0% | 69.0% | 70.0% | 71.0% | 72.0% | 73.0% | 64% | 65.0% | 66.0% |
| Total saving affected by the project in all sectors [GWh/year] |  |  |  |  |  | 554 | 1,184 | 1,898 | 2,703 | 3,610 | 4,632 | 5,777 | 7,062 | 8,504 | 10,117 |
| Total emission reduction affected by the project in all sectors [ktCO2eq/year] |  |  |  |  |  | 447 | 957 | 1,533 | 2,184 | 2,917 | 3,743 | 4,668 | 5,706 | 6,871 | 8,174 |
| Total Energy Saving and Emission Reduction from DEMO and affected by the ADLIGHT Project |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Total energy saving [GWh/year] |  | - | - | 69 | 241 | 794 | 1,425 | 2,138 | 2,944 | 3,851 | 4,873 | 6,018 | 7,302 | 8,745 | 10,357 |
| Cumulative energy saving [GWh] |  | - | - | 69 | 310 | 1,104 | 2,529 | 4,667 | 7,611 | 11,461 | 16,334 | 22,352 | 29,654 | 38,399 | 48,757 |
| Total Emission reduction [ktCO2eq/year] |  | - | - | 56 | 194 | 642 | 1,151 | 1,728 | 2,378 | 3,111 | 3,937 | 4,863 | 5,900 | 7,066 | 8,369 |
| Cumulative Emission Reduction[ktCO2eq] |  | - | - | 56 | 250 | 892 | 2,043 | 3,771 | 6,150 | 9,261 | 13,198 | 18,060 | 23,961 | 31,027 | 39,395 |

Table L.11: Energy Saving and Emission Reduction during 2016 to 2030 for Optimistic Penetration Rate Scenario

| Parameter |  | Base |  | Year 1 | Year 2 | Year 3 | ADLIGHT Post Project |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 |
| BAU Electricity for Lighting [TWh/year] | 40.98 | 42.61 | 44.78 | 46.94 | 49.23 | 51.50 | 53.80 | 56.22 | 58.75 | 61.43 | 64.30 | 67.33 | 70.55 | 74.02 | 77.69 |
| BAU Emission [MtCO2eq/year] | 33.11 | 34.43 | 36.18 | 37.93 | 39.78 | 41.61 | 43.47 | 45.43 | 47.47 | 49.63 | 51.96 | 54.40 | 57.00 | 59.81 | 62.78 |
| Saving and Emission reduction from Demo |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Electricity saving [GWh/year] | - | - | - | 69.10 | 240.69 | 240.69 | 240.69 | 240.69 | 240.69 | 240.69 | 240.69 | 240.69 | 240.69 | 240.69 | 240.69 |
| Cumulative saving [GWh] | - | - | - | 69.10 | 309.79 | 550.47 | 791.16 | 1,031.85 | 1,272.54 | 1,513.23 | 1,753.91 | 1,994.60 | 2,235.29 | 2,475.98 | 2,716.67 |
| Emission reduction [kilo tCO2eq/year] | - | - | - | 55.83 | 194.48 | 194.48 | 194.48 | 194.48 | 194.48 | 194.48 | 194.48 | 194.48 | 194.48 | 194.48 | 194.48 |
| Cumulative emission reduction [kilo tCO2eq] | - | - | - | 55.83 | 250.31 | 444.78 | 639.26 | 833.73 | 1,028.21 | 1,222.69 | 1,417.16 | 1,611.64 | 1,806.11 | 2,000.59 | 2,195.07 |
| Saving and Emission reduction affected by ADLIGHT for all sectors |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Penetration rate for all sectors [%] |  | - | - | - | - | 2.85% | 3.84% | 5.17% | 6.92% | 9.20% | 12.14% | 15.85% | 20.43% | 25.93% | 32.31% |
| Saving due to increasing lighting efficacy [%] |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Residential |  |  | 57% | 58.2% | 59.4% | 60.6% | 61.8% | 63.0% | 64.2% | 65.4% | 66.6% | 67.8% | 57% | 58.2% | 59.4% |
| Industry |  |  | 48% | 49.5% | 51.0% | 52.5% | 54.0% | 55.5% | 57.0% | 58.5% | 60.0% | 61.5% | 48% | 49.5% | 51.0% |
| Commercial |  |  | 48% | 49.5% | 51.0% | 52.5% | 54.0% | 55.5% | 57.0% | 58.5% | 60.0% | 61.5% | 48% | 49.5% | 51.0% |
| Social |  |  | 48% | 49.5% | 51.0% | 52.5% | 54.0% | 55.5% | 57.0% | 58.5% | 60.0% | 61.5% | 48% | 49.5% | 51.0% |
| Gov. Office |  |  | 48% | 49.5% | 51.0% | 52.5% | 54.0% | 55.5% | 57.0% | 58.5% | 60.0% | 61.5% | 48% | 49.5% | 51.0% |
| Street Lighting |  |  | 64% | 65.0% | 66.0% | 67.0% | 68.0% | 69.0% | 70.0% | 71.0% | 72.0% | 73.0% | 64% | 65.0% | 66.0% |
| Total saving affected by the project in all sectors [GWh/year] |  |  |  |  |  | 788 | 1,137 | 1,635 | 2,337 | 3,321 | 4,684 | 6,539 | 9,017 | 12,250 | 16,342 |
| Total emission reduction affected by the project in all sectors [ktCO2eq/year] |  |  |  |  |  | 637 | 919 | 1,321 | 1,888 | 2,683 | 3,785 | 5,284 | 7,285 | 9,898 | 13,204 |
| Total Energy Saving and Emission Reduction from DEMO and affected by the ADLIGHT Project |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Total energy saving [GWh/year] |  | - | - | 69 | 241 | 1,029 | 1,378 | 1,875 | 2,577 | 3,561 | 4,925 | 6,780 | 9,257 | 12,491 | 16,583 |
| Cumulative energy saving [GWh] |  | - | - | 69 | 310 | 1,339 | 2,717 | 4,592 | 7,170 | 10,731 | 15,656 | 22,436 | 31,693 | 44,184 | 60,767 |
| Total Emission reduction [ktCO2eq/year] |  | - | - | 56 | 194 | 832 | 1,114 | 1,515 | 2,083 | 2,877 | 3,979 | 5,478 | 7,480 | 10,093 | 13,399 |
| Cumulative Emission Reduction[ktCO2eq] |  | - | - | 56 | 250 | 1,082 | 2,195 | 3,711 | 5,793 | 8,671 | 12,650 | 18,128 | 25,608 | 35,701 | 49,100 |

Annex M. Annual Targets

| Indicator | Baseline | Year 1 | Year 2 | Year 3 |
| --- | --- | --- | --- | --- |
| Project Goal: To reduce the growth rate of annual GHG emissions from lighting energy use by means of reducing electricity consumption in the energy end-use sectors |  |  |  |  |
| Project Objective: To increase the penetration of high quality energy efficient lighting technologies in Indonesia through the transformation of the national market, thereby reducing electricity demand and the related greenhouse gas (GHG) emissions. |  |  |  |  |
| - Cumulative electricity savings by EOP, GWh | 0 | 10.0 (36,000,000 MJ) | 17.27 (62,172,000 MJ) | 77.45 (278,820,000 MJ) |
| - Direct project GHG emissions mitigated by EOP, kt CO2 (GEF Core Indicator 6.2) | 0 | 8.08 kt CO2 (direct by EOP) 73.36 kt CO2 (Lifetime direct by EOP) | 13.96 kt CO2 (direct by EOP) 121.76 kt CO2 (Lifetime direct by EOP) | 62.58 kt CO2 (direct by EOP) 548.77 kt CO2 (Lifetime direct by EOP) |
| - Number of women and men participating in capacity building trainings throughout the project (GEF Core Indicator 11) | 0 | 15/35 | 30/70 | 60/140 |
| Outcome 1: Improved quality, energy efficient and affordable locally-produced EEL products and systems |  |  |  |  |
| - Efficiency of locally produced lighting systems increased, (lm/W) and Production cost decreased from baseline level (%) - Indoor Type - Outdoor Type | - Eff: 70 lm/W; - Supply chain cost: 100 % (Baseline supply chain cost to be determined at project inception) - Eff: 100 lm/W; - Supply chain cost:100% (at project inception) |  | - Eff: 120 lm/W; - Supply chain cost: 80% of Baseline - Eff: 130 lm/W; - Supply chain Cost: 80% of Baseline | - Eff: 150 lm/W; - Supply chain cost: 70% of Baseline - 170 lm/W; - Supply chain cost: 70% of Baseline |
| Cumulative number of lighting manufacturers who received technical assistance to upgrade production facilities | 0 |  | 3 manufacturers (1 for each associations) | 6 |
| - Investment grade proposal for business transformation plans - Submitted by manufacturers - Approved by banks. | - 0 - 0 |  | - 3 - 3 | - 6 - 6 |
| - Ratio of women and men who believe they have the capacity to - Submit (by local manufacturers) - Approve (by banks) investment grade proposal for business transformation plans | - 0 - 0 | - 30/70 - 30/70 | - 30/70 - 30/70 | - 30/70 - 30/70 |
| Outcome 2: Improved conditions for fair market competition of EE lighting products informed by robust policy and institutional framework |  |  |  |  |
| - No. of policy documents at the national level, including Standard Minimum Quality and MEPS on LED and other relevant guidelines, developed and approved | - 0 | - 1 SNI | - 2 (1 SNI and 1 Draft MEPS and labeling) | - 3 (SNI updated and Implemented MEPS and labeling endorsed) |
| - No. of policy and guideline on LED procurement developed and implemented in E-catalogue and regular public procurement system | 0 | - Policy monograph developed | - 1 (policy adapting SNI) | - 2 (policy adapting SNI and MEPS) |
| - No. of comprehensive MVE Guideline and required implementing rules and regulations for including resolving custom dispute and legality of products developed and implemented | - 0 | - Comprehensive study completed | - 1 (software by BSN) | - 1 |
| - Ratio of women and men employees in relevant government institutions who believe they have the capacity to monitor verify and enforce high quality efficiency lighting systems | - 0 | - 30/70 | - 30/70 | - 30/70 |
| Outcome 3: Increased market penetration of high quality and efficient lighting |  |  |  |  |
| - Cumulative no. of innovative financial support schemes developed to accelerate penetration of EE lighting systems | - 0 | - 1 | - 2 | - 4 |
| - Cumulative no. of pilot demonstration completed and replication plans developed and approved for implementation | - 0 |  | - 3 (1 cities and 2 buildings) | - 5 (2 cities, 2 buildings and a residential area) With possible replication in 2 cities and 7 buildings |
| - Number of stakeholders engaged - Municipalities - clients (project developers/ building owners) - technology providers - financial institutions | - 0 - 0 - 0 - 0 | - 1 - 1 - 1 - 1 | - 2 - 3 - 3 - 1 | - 4 - 6 - 5 - 2 |
| - Women’s and men’s level of satisfaction with EEL systems provided (reliability, affordability, convenience, efficiency) | - 0 | - At least 50 % of women and men beneficiaries are highly satisfied with the EEL systems provided (minimum score 7/10) | - At least 60 % of women and men beneficiaries are highly satisfied with the EEL systems provided (minimum score 7/10) | - At least 70 % of women and men beneficiaries are highly satisfied with the EEL systems provided (minimum score 7/10) |

Annex N. Gender Analysis and Action Plan

Gender Analysis and Gender Action Plan for the ADLIGHT Project

Gender analysis

Introduction

This assessment aims to provide an overview of the state of gender equality in Indonesia and identify gender gaps, challenges and opportunities for UNDP and Government partners through the ADLIGHT project. This assessment illustrates how gender equality can be advanced through the transformation of Indonesia’s lighting market. The assessment was based on available data from global and Indonesian studies, donor agencies and interviews.

ADLIGHT aims to promote the increased deployment of high efficiency lighting technologies in Indonesia through the transformation of the national market, thereby reducing electricity demand and the related greenhouse gas (GHG) emissions.

This will be achieved through implementation of three Components, namely:
(1) Support to local lighting industry to prepare the market for high quality, high efficient lighting systems, 
(2) Regulatory mechanisms; and market monitoring, verification, and enforcement, and 
(3) New business models and awareness raising for high efficiency lighting technology penetration.

Gender equality in Indonesia: contextual analysis

Status of gender equality in Indonesia

Vast inequalities between men and women persist in Indonesia, at every level of society. In 2016, Indonesia ranked 88th out of 144 countries in the World Economic Forum’s Global Gender Gap Report, scoring .682. This reveals a gap for female legislators, senior officials and managers. Indonesia has a Gender Inequality Index value of 0.467, ranking it 105 out of 159 countries in the 2015 index. The GII reflects gender-based inequalities in three areas: reproductive health, empowerment, and economic activity.

According to the National Labour Data in Indonesia’s national labour survey (SAKERNAS) in 2015, women’s labor force participation rates 48.9% as opposed to 82.7% for men. When compared to previous years, the data reveals that over the last ten years, there is an increase of tertiary educated young women gaining meaningful wage work in the formal sector, mostly in urban areas. However women in poorer families are becoming more likely to resort to informal work to make ends meet. This inequality gap is reflected in the increasing GINI coefficient of .397 in Indonesia. Over the past 20 years inequality has risen faster than any other country in south-east Asia.  Workers in the informal sector, do not have access to minimum wage rights, or benefits of wage work like insurance, parental leave, or sick leave, and are most vulnerable to exploitation, injury and financial instability. The informal sector is mostly made up of low-skilled and low-educated women, either working for family members or running their own businesses.

In Indonesia, small to medium enterprises (SMEs) make up 57% of the GDP. About one-third of medium-sized enterprises are owned by women and this number is increasing by 8% annually while the number of SMEs owned by men is dropping. Women-led SMEs are an important untapped opportunity that can support economic growth and innovation. However, barriers are in the way to unlocking this potential. The results of preliminary research into the barriers faced by women-led SMEs conducted by UNDP Indonesia found that women-led enterprise often lack access to finance, including credit due to a range of challenges: lack of education around managing financing, lending agencies and banks exercise discrimination, combined with women’s tendency to put forward her husband or brother’s name when applying for credit. This results in women having far less agency and decision-making power when operating her enterprise, and spending family income.

Women are underrepresented in positions of leadership in every sector in Indonesia. Particularly at the political level, indicators surrounding progress in female political participation has shown both progress and need for change. There has been an increase in women representation in national parliament from 17.32 to 18.04 per cent in 2016. At the sub-national level women hold less than 15 percent of seats (14.6 percent in provincial and 25.8 percent in regional). In the executive branch, almost half of civil servants are women, yet less than 20% hold decision-making positions. President Joko Widodo has been congratulated for appointing eight women in his cabinet of 34 ministers.

Legal and Administrative Framework Protecting Women and Promoting Gender Equality

At the international leveI, Indonesia has shown commitment to advancing gender equality. In 1984, it ratified the Convention on the Elimination of All Forms of Discrimination against Women (CEDAW) which committed nation states to harmonizing domestic laws with international law.

The Government of Indonesia has committed to achieving 17 Sustainable Development Goals (SDGs), all of which have specific indicators related to gender in addition to Goal 5 for Gender Equality. Gender mainstreaming is an approach public and private sectors are more commonly utilizing to achieve the SDGs, and in particular the Government of Indonesia’s agenda through special regulations on Gender Mainstreaming and Gender Responsive Planning and Budgeting. Specifically, Gender mainstreaming has become national policy since the year of 2000. The commitment to integrate gender equality into national development was confirmed by Presidential Decree No. 9/2000 on “Gender Mainstreaming in National Development” regulating that all government sectors, at national and sub-national level, including the Commander of the Armed Forces, the Chief Police, and the Supreme Attorney, shall integrate a gender mainstreaming policy and strategy into its respective tasks and functions. All sectors shall report the implementation of the policy to the Ministry of Women’s Empowerment and Child Protection annually which reports the progress of gender mainstreaming to the President.

While there is strong commitment to the Gender Mainstreaming Regulation in Indonesia, there are still challenges in its implementation such as lack of mindset and political will for gender-responsive budgeting as well as the lack of investment in sex-disaggregated data. Further to this, improving institutional knowledge, and strengthening monitoring and evaluation, and gender-related accountability mechanisms are necessary for gender mainstreaming at policy and implementation levels.

Gender and energy access

The correlations between poverty, access to affordable and effective energy resources and gender equality has been widely explored. Access to affordable, reliable, sustainable and modern energy is a human development enabler – it provides men and women with more time and money in and outside of the household, at work, while curbing GHGs and improving the health and safety of communities. For example, improved access to time-saving electric appliances has been significantly more transformative for women than men due to women’s primary role relative to household chores. 
Due to persistent gender roles in Indonesia and around the world, lighting technology directly impacts men and women differently, while also impacting structured systems that hinder gender equality.

Ministry of Energy and Mineral Resources states that Indonesia has reached 95.35% of electrification ratio at national level and 97.10% at rural areas. Approximately 2,300 villages are still living without access to electricity, either using firewood for cooking or kerosene lamps for visibility. Kerosene is harmful, particularly for women who are primarily responsible for cooking, cleaning and using electrical sources for household duties.  The World Bank estimates that breathing kerosene fumes is the equivalent of smoking two packets of cigarettes a day and two-thirds of adult females with lung cancer in developing nations are non-smokers. Kerosene lamps are widely used for lighting in rural areas of Asia and Africa where electrical distribution is either not available, or too costly for widespread use. Yet using kerosene for lighting is extremely inefficient, dangerous and expensive, and it has extensive health and environmental drawbacks.

At some other rural areas, the hardship of collecting and using firewood for cooking in the outdoor causes great problems for women. Women cook on open fires by burning dung, wood or other biomass. The collection and transport of fuel represents a labor intensive and time-consuming task, undertaken mainly by women and children. The health impacts on women from using firewood can be enormous — smoke produced from open fires, lung diseases caused by smoke and indoor air pollution, neck and back injuries caused by the transportation of heavy wood loads. These ailments combined with the difficult access to health services at the remote rural areas doubles the burden placed on women.

Dr. Nuzainah Gintin of Indonesia says, “Energy is very important in women’s daily lives, especially for serving food for families, lighting for teaching their children at night, and energy for their small food industries… cooking and small business are the major challenges facing women around access to energy… for the women in my country, a change that would allow them to be financially independent would have the most impact in their lives.”

Gender and energy efficient lighting

Street lighting

Indonesian cities typically have sub-optimal street lighting systems, with illegal connections, limited metering coverage and poor service standards. Increasing the energy efficiency of street lighting is not only cost effective, it provides gender-sensitive results by improving nigh-time safety in cities. According to UN-Habitat, women’s vulnerability to sexual harassment and assault makes them in higher need for security. In Indonesia, for example, one in three women have experienced violence against them in their lifetimes. There are a range of initiatives undertaken in Indonesia to address gender-based violence, using public lighting safety as an entry point. For example, UNWomen in Indonesia is working with the Government to promote ‘Safe Cities’ that addresses lack of street lighting to address the high rates of violence and harassment against women in urban spaces.

The GIZ project Smart Street Lighting Initiative (SSLI) which commenced in 2014 in Indonesia effectively ensured participation of women’s representatives the perceptions of women and men with relation to safe street lighting. As a result of focus group discussions, results showed that there is a need to raise awareness of energy efficiency among both women and men; public perception of street lighting is in general positive, although there were comments on lamps that did not turn on, frequently malfunction, and are not immediately replaced; women and men have different perceptions on what constitutes adequate illumination, as well as the sense of safety it provides on a particular street, with men having the tendency to perceive that the illumination had been adequate while the women tended to claim that it was not bright enough; and in the area where the SSLI was implemented, more men than women accessed the street at night due to both cultural reasons around women staying at the home, and also because it was not lit well.

Residential areas

A pilot study from 2013 on residential energy consumption in the city of Bandung, Indonesia, demonstrated the importance of women’s role in household energy consumption. The results showed that in households where the woman (wife) was the dominant decision maker on decisions about energy expenditure and control of energy consumption in the household, the energy consumption tended to be the lowest. The mean energy consumption of these households was 23-25% lower than in the households where energy decisions were made by the husband or by joint decision.

Representation of women in the energy industry

Beyond household energy consumption, there are many examples of women as producers, technicians and entrepreneurs in sustainable energy. However, the traditional energy sector is still one of the least gender-inclusive sectors to date globally. According to one estimate, women represent only 6 percent, 4 percent and less than 1 percent of the technical, decision-making and top management positions, respectively, in the energy sector.  For women entrepreneurs who would like to thrive within the energy industry, existing structural inequality, which manifests itself in the form of discrimination in law and practice, also poses barriers.

UN Environment has reported on the underrepresentation of women in the energy sector at a global level, and the impact this has on gender equality. Gender aspects in the planning and policy cycles and sectors often has little visibility in formal and centralized policy frameworks. Men over-represent at the global policy level, for example At COP21, where 140 countries presented their plans for emission reductions (Intended Nationally Determined Contributions or INDCs), only 50 countries referred to gender as important in combatting climate change. Energy policies typically focus on issues of investment, tariffs, privies, access, availability, infrastructure development, participation and environment – all of which are linked to gender roles. However energy policy is often considered gender-neutral.

Consequently, the forums in which energy issues are identified and potential solutions proposed are likely to have an inadvertent male bias (UNIDO and UN Women 2013). In addition to the leadership gap, the share of women in the workforce in the energy sector is generally quite low however greater sex-disaggregated data on this is needed. To address this disparity, governments should consider reserving dedicated spots for women as community representatives and within electricity entities, whether a rural electricity cooperative board of directors or a distribution billing and collections team. Intentionally seeking women’s views and insights will lead to innovations and enhance a program’s effectiveness.

Lack of sex-disaggregated data presents challenges for promoting gender equality in the energy sector.
As for Indonesia, there is little data available about the representation of women in the lighting industry, at various levels of the market. However, in a focus group discussion held by Institute for Essential Services Reform with Ministry of Women’s Empowerment and Child Protection on gender mainstreaming in Indonesia’s renewable energy sector, several gender gaps were identified that can be applied to the wider energy sector in general. Access to information related to energy is limited to women, given the male-dominated industry, which in turn limits women’s participation and contribution to shaping policy. This emphasizes that women are underrepresented at the decision making level in public and private spaces resulting in poor understanding of gender implications of policy.

Performance in Indonesia’s labour market has been weak, according to a report by Asia Development Bank Slow job growth and high levels of labor underutilization affect different groups of workers, particularly young people, women and those in rural areas. Investment in education in recent decades has not resulted in the expansion of labor productivity. For men and women, up-skilling and re-skilling opportunities are limited and access to career mobility is limited. Women in particular are restricted in the workforce due to gender roles ensuring their efforts are spent in the home.

In both developed and developing countries women’s best chance of becoming involved in sustainable energy provision is at the community level (UN Environment). Business models for small-scale energy production range from consignment arrangements, to linking of entrepreneurs to microfinancing institutions (possibly through the use of loan guarantee funds, which lowers the risk for financing institutions), to women individually or in groups taking on the manufacture or assembly of devices (sometimes as part of family businesses), to women’s networks raising awareness of, for example, policy, options, pricing and safety.

Gender gaps related to access to energy, finances, training, employment and entrepreneurship need to be addressed in Indonesia. Creating policies that include both men and women, will result in more sustainable outcomes. Infrastructure and market transformation projects such as ADLIGHT have the opportunity to promote new skills, training, increased employment and entrepreneurship opportunities for women, as well as more equitable benefit-sharing at the community level.

Conclusion

ADLIGHT presents unique opportunities to strengthen women’s participation in the energy efficient electricity sector along the entire value chain, from manufacturing, installation, maintenance, distribution, and billings. However deeper gendered assessments need to be conducted in order to illustrate how women and men interact with the local economy differently. Energy sectors are primarily male-dominated in Indonesia and globally, however women are an untapped resource, as key beneficiaries of lighting technologies, and consultants on how to most effectively raise awareness about new lighting technologies. Finally, addressing gender gaps at leadership, policy and industrial levels in the electricity sector is an opportunity to advance gender equality, and the economy of Indonesia at large.

Proposed Gender Action Plan

| Objective | Action | Indicator | Responsible institution |
| --- | --- | --- | --- |
| Overall objective |  |  |  |
| Active participation of women and men in capacity building trainings throughout the project | Require and encourage active participation of women and men in capacity building trainings throughout the project | Cumulative number of women and men participating in capacity building trainings throughout the project Ratio of women and men participating in capacity building trainings throughout the project | PMU MEMR/DGNREEC |
| Outcome 1. Improved quality, energy efficient and affordable locally-produced EE Lighting (EEL) products and systems |  |  |  |
| Enhanced gender balanced employment in the energy sector | Encourage local manufacturers to increase the number of female interns and request lighting manufacturer associations also to encourage the increase of female interns in the local manufactories Contracting women in consultancy, financial and customer services, as appropriate | Ratio of women and men interns in local EEL manufacturing companies Ratio of women and men employed through jobs created from the project (40/60) | PMU MEMR/DGNREEC PMU UNDP UN Environment |
| Active participation of women and men in the periodic market surveys | In the design of periodic market surveys on production of EEL, incorporate gender sensitive questions In the design of periodic market surveys on application of EEL, develop surveys that specifically address women’s needs, preferences and habits in acquirement, consumption and disposal of EEL products Ensure that the periodic market surveys conducted amongst the beneficiaries of the EEL systems are targeting women and men separately (i.e. both men and women in the household rather than one household as a whole) | Ratio of women and men participating in the periodic market surveys | PMU MEMR/DGNREEC |
| Women and men have the capacity to submit (from manufacturers) and approve (by banks) investment grade proposals for business transformation plans | Require and encourage active participation of women and men in trainings, workshops and focus group dialogues | Cumulative number of women and men who believe they have the capacity to submit and approve of investment grade proposals for business transformation plans Ratio of women and men participating in trainings, workshops and focus group dialogues | PMU MEMR/DGNREEC |
| Outcome 2: Improved conditions for fair market competition informed by robust policy and institutional framework |  |  |  |
| Enhanced gender balanced employment in the energy sector | Require and encourage to increase the percentage of women staff in MEMR receiving certification for evaluating bids in LED procurement Require relevant government institutions to increase the number of women interns involved in assignments related to energy efficiency Contracting women in consultancy, financial and customer services, as appropriate | Ratio of women and men certified for evaluating bids in LED procurement Ratio of women and men interns in government institutions engaged in assignments related to energy efficiency Ratio of women and men employed through jobs created from the project | PMU MEMR/DGNREEC UNDP UN Environment |
| Women and men employees in relevant government institutions have the capacity to monitor, verify and enforce high efficiency lighting systems | Require and encourage active participation of women and men in trainings, workshops and focus group dialogues | Cumulative number of women and men employees in relevant government institutions who believe they have the capacity to monitor, verify and enforce high efficiency lighting systems Ratio of women and men employees in relevant government institutions who believe they have the capacity to monitor, verify and enforce high efficiency lighting systems | PMU MEMR/DGNREEC |
| Outcome 3: Increased penetration of high quality and efficient lighting |  |  |  |
| Enhanced gender balanced employment in the energy sector | Contracting women in consultancy, financial and customer services, as appropriate Require and encourage contractors to employ women, as appropriate | Ratio of women and men employed through jobs created from the project | PMU MEMR/DGNREEC UNDP UN Environment |
| Equal participation of women and men in stakeholder consultation meetings on installation of EEL systems in pilot areas | Require and encourage active participation of women and men in stakeholder consultation meetings for the general public on installation of EEL systems in pilot areas Ensure that stakeholder consultation meetings are held at times and locations convenient for women | Ratio of women and men participating in stakeholder consultation meetings in pilot areas | PMU MEMR/DGNREEC |
| Women and men in pilot areas are benefiting from EEL technologies equally | Collect information on number of beneficiaries and their level of satisfaction through periodic market surveys, monitoring visits etc. | Cumulative number of women and men benefiting from EEL technologies as influenced by the project Ratio of women and men benefiting from EEL technologies as influenced by the project Women’s and men’s level of satisfaction with EEL systems provided by the project (reliability, affordability, convenience, efficiency) | PMU MEMR/DGNREEC |
| Women and men have equal access to knowledge about energy efficient lighting technologies and their benefits | Require and encourage active participation of women in consultation meetings on their information needs on EEL systems and preferred channels for information sharing Ensure that the material developed under the awareness and promotion program on the benefits of LED lighting is designed and communicated in a way that is easily understood by women and men with disabilities as well as different levels of education Conduct online survey on the use of the information system (on the website) to capture users’ gender Encourage participation of women’s groups to promote consumer energy efficiency awareness Ensure that the awareness and promotion program and information system on benefits of LED lighting includes gender responsive information material such as the potential benefits of EEL for women and men | Cumulative number of women and men participating in consultation meetings Ratio of women and men participating in consultation meetings Cumulative number of women and men with access to knowledge about EEL technologies and their benefits developed Ratio of women and men with access to knowledge about EEL technologies and their benefits developed Cumulative number of women and men users of the information system Ratio of women and men users of the information system Number of women's groups involved Cumulative number of women and men beneficiaries with increased awareness and access to knowledge about energy efficient lighting technologies | PMU MEMR/DGNREEC |

General recommendations for the ADLIGHT project

- Monitor benefits, participation, and feedback among women and men and incorporate remedial action that promotes gender equality as appropriate

- Ensure that evaluation forms are distributed during each training/workshop collecting information on participant’s gender, previous engagement in similar trainings/workshops and perceived relevance of the workshop/training

- Collect sex-disaggregated data and project’s gender issues/impact through surveys, stakeholder interviews and other appropriate stakeholder engagement methods, as identified in the Stakeholder Engagement Plan

- Consider inclusion of sex-disaggregated data collected during the project in midterm evaluation, project closure reports, annual reports and other project and UNDP information material

- Recruit a gender specialist/expert or ensure at least one member of project management team is gender sensitized

- Create ToRs for project staff that ensure equal opportunity for women and men, and where applicable, require skills/expertise in gender

- Ensure that the implementation of the gender action plan is included as one requirement in the TORs for project staff recruited throughout the project

- Invite universities to focus group dialogues and encourage them to provide more internship positions for women in the energy efficiency sector

- Review, monitor and report regularly on the gender action plan

Proposed implementation arrangements

The project manager should have the overall responsibility for implementing, monitoring and reporting of the gender action plan. In the beginning of the project, a full-time or part time gender focal point could be recruited to provide additional technical assistance for the project management unit on gender action plan annual planning, implementation, monitoring and reporting.

In order to successfully mainstream gender in the project, a portion of the project budget should be allocated for the implementation of the gender action plan. Resources for the implementation of the gender action plan could be drawn from the budgets for project activities such as market surveys, capacity building activities, installation of EEL systems, awareness raising program on the benefits of LED lighting and from the consultancy package.

Annex O: Knowledge Management Strategy for the ADLIGHT Project

1.0 Introduction

The main driver for implementing development projects, such as ADLIGHT, is to serve as a demonstration of how a certain concept can work under given circumstances in order to solve or alleviate a particular challenge. Therefore, it is imperative that, to the extent possible, all information acquired during project design and execution is well documented for purposes of replication in the future. However, more importantly, the aforementioned information is required during project execution in order to determine the extent to which the project is meeting its original objectives and outcomes.

Collectively, the process of handling the aforementioned information is referred to as Knowledge Management. According to the United Nations Joint Inspection Unit (2007), knowledge management is:

“…the systematic processes, or range of practices, used by organizations to identify, capture, store, create, update, represent, and distribute knowledge for use, awareness and learning across the organization.”

Based on the above definition, this document aims at guiding the ADLIGHT project on how to conduct knowledge management during project implementation. In the case of this project, knowledge management will be key due to the fact that there are several parties involved at different stages of the project. Therefore, there is need to harmonize the information gathered as well as capture the knowledge acquired as well as the knowledge brought to the project by the various experts and stakeholders participating in the project. It is anticipated that the knowledge management process for the ADLIGHT project will adopt the approach developed by International Labour Organization (ILO) as summarized in the following diagram:

Source: ILO, 2004

As depicted in the previous diagram, knowledge management is a somewhat cyclical process but requires an enabling environment to thrive. In the case of the ADLIGHT Project, in order to successfully undertake knowledge management, there will be need for a high level of commitment by the Project Manager. In addition, some form of information technology will be required in order to support knowledge acquisition, storage and sharing. In addition, stemming from good project management, there will be the need for fostering a culture of knowledge management based on good knowledge management practices and strategic direction.

Consequently, the overall objective of this Knowledge Management Strategy is to ensure the effective use of the knowledge acquired and availed to the ADLIGHT Project. The specific objectives will be:

- To collate and retain knowledge in order to enhance the project’s institutional memory;

- To ensure timely and open access to knowledge so as to foster high staff performance and  effective work flow processes; and

- To nurture knowledge sharing for more effective project implementation as well as to inform decision-making processes.

2.0 Guiding Principles

In order to ensure the successful implementation of this Knowledge Management Strategy, a number of guiding principles will have to be adhered to. These are discussed in this section:

2.1 Collective Responsibility

While the overall responsibility of knowledge management is that of the Project Manager, it is, however, everyone’s obligation to contribute to the knowledge management process. This is important because different project staff, stakeholders and experts will be involved at different stages of the project. Therefore, having an effective system for collating and sharing information will be crucial.

2.2 Range of Knowledge

It is anticipated that a wide range of knowledge will be acquired and shared during the project lifetime. This includes explicit knowledge acquired from stakeholders during surveys, standard procedures, progress reports as well as implicit knowledge such as the one held by individuals such as experts which is unwritten. It should be noted that some of the progress report formats to be adopted in the project will attempt to elicit the knowledge acquired and, therefore, will require particular attention.

2.3 Simplicity

Due to limitation of financial resources and to ensure ease of utilization, the knowledge management process should be simple yet effective. For instance, there will be no need to acquire complex knowledge management software. Rather, the project could adopt the use of existing tools such as the information sharing systems used by UNDP such as Yammer, OneDrive, Outlook calendar, Web server, etc. It is worth noting that knowledge management is NOT technology-focussed but people-focussed.

2.4 Use of Various Modalities

It is incumbent on the Project Team to use a wide range of knowledge acquisition, storage and sharing modalities based on ease of doing so. For example, a bilateral meeting can provide a forum for the generation and exchange of a lot of knowledge and information. Therefore, in order to capture this knowledge for the benefit of all relevant stakeholders, brief “Meeting Notes” can be drafted and shared after every meeting. This is also important in the case of Workshops and Seminars. Alternatively, voice recording can be utilized to quickly and easily capture the entire meeting proceedings, albeit in a non-distilled format.

2.5 Multifunctional Approach

There is need to recognize that the knowledge acquired can have diverse uses. For example, Workshop Proceedings Report can be evidence that a particular milestone has been attained. In addition, the report can be a source of information for a particular group of stakeholders. Therefore, in the process of knowledge management, care should be taken to ensure that the “packaging” of the knowledge is done in a way to ensure that the products are suitable for the foreseeable different uses.

2.6 Constant Review

For any system to be effective, its performance has to be constantly reviewed and, where need be, adjusted. Therefore, the Project Manager could delegate monitoring and maintenance of knowledge management to the individual allocated the Monitoring and Evaluation responsibility. This will ensure that the opportunities of knowledge acquisition and sharing are not lost.

2.7 Publicity and Public Engagement

By its nature, the ADLIGHT Project has an inherent interest among various stakeholders, the public included. Therefore, an effective knowledge management process should include means of publicizing the knowledge garnered as well as using a simple and effective way of engaging with the public e.g. using mass media (TV, radio, newspapers, website, etc) and social media, such as Twitter and Facebook.

2.8 Alignment to Overall Project Plan

In a number of instances, outputs of the project will contribute as inputs to the ADLIGHT’s Project knowledge management. In other cases, products of knowledge management will contribute to achieving certain outcomes of the project. Therefore, it will be important that the process of knowledge management is aligned to the overall Project Plan. Specifically, the project roll-out plan should include an activity for the development of a Knowledge Management Action Plan.

3.0 Establishment of the EEL Knowledge Management Center

The project in its Component 1, Activity 1.1.1, will support the establishment of an Efficient Lighting Knowledge Center for collecting market information on lighting products, quality of products, consumer perception, including sex-disaggregated consumer data where available and other related information regarding efficient lighting technology and technology providers. Existing agency with relevant mandate and organization, such as BSN, will be assisted in preparing a strategy and design to meet the requirements and purpose of the Knowledge Center and in establishing it in the selected agency that will continue to be responsible in carrying out a sustainable program ushered by the project in providing not only knowledge but also a categorized quality product listing (QPL) and database in cooperation with a network of qualified laboratories.

Annex P: Stakeholder engagement plan

The stakeholder engagement plan provides a description of stakeholders identified during the project design stage, their interest in the project and the most relevant engagement techniques that will be used throughout the project. The stakeholders are not strictly limited to the list as additional stakeholders and stakeholder engagement needs are likely to be identified during the project implementation.

| Stakeholder/Stakeholder group | Why included (interest) | Participation method |  | Timing |
| --- | --- | --- | --- | --- |
|  |  | Method (most common) | Responsibility |  |
| GEF | Donor of funds for the ADLIGHT project | Formal meetings (i.e. supervision missions) Project reports | UNDP UN Environment | Annually |
| Ministry of Energy and Mineral Resources (MEMR) | Provides overall direction and oversight as the Executing Agency; acts as Chairman of the National Steering Committee; provides the lead role in coordinating with other ministries and agencies in pushing forward the goals and objectives of the efficient lighting industry program and resolving inter-ministry barriers | Project board meetings Project reports Workshops, trainings focus group dialogues One-on-one meetings, Phone/email | PMU DGNREEC UNDP UN Environment | Annually, quarterly or more frequently when necessary To be confirmed in the annual work plan As frequently as necessary |
| Directorate General of New-Renewable Energy and Energy Conservation (DGNREEC) | Acts as the Responsible Party for the project and leads the Project Management Unit for the day-to-day operations and resolution of issues to ensure smooth implementation of the project; provides technical support for the technology programs; coordinates with other government agencies as well as UNDP and UN Environment | Project board meetings Project reports Workshops, trainings, focus group dialogues One-on-one meetings, Phone/email | PMU UNDP UN Environment | Quarterly or more frequently when necessary To be confirmed in the annual plan As frequently as necessary |
| MEMR P3TK EBTKE (Research and Development of DGNREEC) | Provides technical support and laboratory services for the needs of the LED industry; leads the capacity building and accreditation of laboratory facilities in meeting the MEPS/SNI standard requirement, benchmarking and round-robin testing | Workshops, trainings, focus group dialogues One-on-one meetings, Phone/email | MEMR/ DGNREEC PMU | To be confirmed in the annual plan As frequent as necessary |
| Min of Development Planning (Badan Perencanaan Pembangunan Nasional or BAPPENAS) | Acts as the integrator of the related government programs within the overarching objectives of the EEL program which crosses many sectoral boundaries and policy/organizational areas considering overall national interest | Project board meetings Project reports Focus group dialogues One-on-one meetings, Phone/email | MEMR/ DGNREEC PMU | Quarterly or more frequently when necessary Annually To be confirmed in the annual plan As frequently as necessary |
| Public Procurement Agency – Lembaga Kebijakan Pengadaan Barang/Jasa Pemerintah (LKPP) | Acts as main resource agency for the development and adoption of government procurement policies in order to hasten the market penetration of locally produced high efficiency and affordable lighting products | Project board meetings Project reports Workshops, trainings, focus group dialogues One-on-one meetings, Phone/email | MEMR/ DGNREEC PMU | Quarterly or more frequently when necessary Annually To be confirmed in the annual plan As frequently as necessary |
| Financial Service Authority (Otoritas Jasa Keuangan or OJK) | Coordinates among financial institutions and banks and provides overall policy direction and guidance in implementation of financing mechanisms that will be adopted by the project | Project board meetings Project reports Workshops, trainings, focus group dialogues, business forums One-on-one meetings, Phone/email | MEMR/ DGNREEC PMU | Quarterly or more frequently when necessary Annually To be confirmed in the annual plan As frequently as necessary |
| PT Sarana Multi Infrastruktur - Persero (PT SMI) | Acts as resource group for green banking and green infrastructure as it applies to buildings and street lighting finance | Workshops, trainings, focus group dialogues One-on-one meetings, Phone/email | MEMR/ DGNREEC PMU | To be confirmed in the annual plan As frequently as necessary |
| City Government – Smart Cities | Act as pilot demonstration hosts in EEL application in street lighting and the evaluation of the impacts of the transformation toward EELs | Workshops, trainings, focus group dialogues Surveys One-on-one meetings, Phone/email | MEMR/ DGNREEC PMU | To be confirmed in the annual plan First year, before mid-term review and before project closure As frequently as necessary |
| Energy Service Company (ESCO) | Provides the main link between the EEL manufacturers and users and facilities project development, financing and EPC requirements | Workshops, trainings, focus group dialogues One-on-one meetings, Phone/email | MEMR/ DGNREEC PMU | To be confirmed in the annual plan As frequently as necessary |
| State Owned Banks & Financial Institution | Acts as catalysts in the development and implementation of the business transformation plans to transform the industry to produce and market EELs locally and potentially abroad | Workshops, trainings, focus group dialogues and business forums One-on-one meetings, Phone/email | MEMR/ DGNREEC PMU | To be confirmed in the annual plan As frequently as necessary |
| Perusahaan Listrik Negara (PLN) State Electricity Company) | Acts as resource organization on energy supply, pricing, and policy in support of the increased market for EELs and transition from the conventional lamps as well as piloting a LED distribution scheme and billing system through PLN infrastructure for the residential sector via the ESCO model. | Workshops, trainings, focus group dialogues One-on-one meetings, Phone/email | MEMR/ DGNREEC PMU | To be confirmed in the annual plan As frequently as necessary |
| Ministry of Trade | Act as resource ministry in the harmonization of policies and regulations regarding trading of locally produced and imported EELs; provides active support in the MVE schemes and market control to encourage efficient and reasonably priced lighting products that meet MEPS/SNI | Project board meetings Project reports Workshops, trainings, focus group dialogues One-on-one meetings, Phone/email | MEMR/ DGNREEC PMU | Quarterly or more frequently when necessary Annually To be confirmed in the annual plan As frequently as necessary |
| Ministry of Industry | Act as resource ministry for the policies and regulations governing the lighting industry sector and the implementation of business transformation plans towards producing affordable, high quality lighting products | Project board meetings Project reports Workshops, trainings, focus group dialogues One-on-one meetings, Phone/email | MEMR/ DGNREEC PMU | Quarterly or more frequently when necessary Annually To be confirmed in the annual plan As frequently as necessary |
| Ministry of Public Works and Housing | Acts as resource ministry in the application of EELs in the street lighting and building consumer groups | Workshops, trainings, focus group dialogues One-on-one meetings, Phone/email | MEMR/ DGNREEC PMU | To be confirmed in the annual plan As frequently as necessary |
| Ministry of Finance/Bureau of Customs | Provides lead role in the application and regulation of policies regarding custom duties and importation of lighting product components as well exportation of standard products whenever viable; participated in the development and implementation of MVE schemes vis-à-vis MEPS/SNI adopted and the corresponding inspection software to discourage entry or usage of inefficient lighting products | Workshops, trainings, focus group dialogues One-on-one meetings, Phone/email | MEMR/ DGNREEC PMU | To be confirmed in the annual plan As frequently as necessary |
| Badan Standardisasi Nationa (BSN) or National Standardization Agency | Provides technical support and policy coordination in the development and adoption of the SNI and MEPS within the timeframe of the project considering ASEAN and other international commitments in MEPS and labeling | Workshops, trainings, focus group dialogues One-on-one meetings, Phone/email | MEMR/ DGNREEC PMU | To be confirmed in the annual plan As frequently as necessary |
| BPPT (Research Agency for Technology Development and Implementation) | Acts as resource agency in the R&D and product development for EEL technology and their application | Workshops, trainings, focus group dialogues One-on-one meetings, Phone/email | MEMR/ DGNREEC PMU | To be confirmed in the annual plan As frequently as necessary |
| Tingkat Kandungan Dalam Negeri (TKDN) or Local Content certifiers | Act as resource agency in the policy review and recommendations in enhancing the local content of locally manufactured lighting products | Workshops, trainings, focus group dialogues One-on-one meetings, Phone/email | MEMR/ DGNREEC PMU | To be confirmed in the annual plan As frequently as necessary |
| Credit Facility Guarantee/Credit Insurance Companies | Act as resource groups for determining appropriate financing support schemes in support of the full scale ESCO model regarding credit guarantee facility | Workshops, trainings, focus group dialogues One-on-one meetings, Phone/email | MEMR/ DGNREEC PMU | To be confirmed in the annual work plan As frequently as necessary |
| Lighting Industry Associations (GAMATRINDO, ALINDO and APERLINDO) | Provides technical support and coordination among local manufacturers; leads the industry associations and its members in policy discussions to achieve timely progress in project implementation and performance targets; lead the transition to higher efficiency and cost-effective EEL production and acts as coordinator and focal point in the monitoring, verification and enforcement representing the EEL industry for measuring impact and corrective actions | Workshops, trainings, focus group dialogues Surveys One-on-one meetings Phone/email | MEMR/ DGNREEC PMU | To be confirmed in the annual work plan First year, before mid-term review and before project closure As frequently as necessary |
| Development Partners (MTRE3, ICED2, PFAN, and other bilateral projects) | Provide technical support and coordination regarding the implementation of relevant activities towards achievement of outputs that have common project objectives | Workshops, trainings, focus group dialogues One-on-one meetings Phone/email | MEMR/ DGNREEC PMU | To be confirmed in the annual work plan As frequently as necessary |
| Beneficiaries of LED distribution in selected cities such as residents in government buildings, owners/visitors of commercial buildings and residents benefitting from street lighting | Stakeholders who will directly benefit from the installation of EEL lighting | Public meetings Surveys Reading material Email, phone, fax or mail Radio/TV Social media, UNDP’s website, other project related websites | MEMR/ DGNREEC PMU | To be confirmed in the annual work plan First year, before mid-term review and before project closure Throughout project implementation |
| Energy efficient lighting manufacturers (local and imported lighting) | Will be involved in trainings on how to increase the quality and value of their LED products | Workshops, trainings, focus group dialogues Forums, conferences and exhibitions Surveys Other reading material Email, phone, fax or mail Radio/TV Social media, UNDP’s website, other project related websites | MEMR/ DGNREEC PMU | To be confirmed in the annual work plan First year, before mid-term review and before project closure Throughout project implementation |
| Masyarakat Konservasi dan Efisiensi Energi Indonesia MASKEEI or IECES (Indonesia Energy Conservation and Efficiency Society) | Will be involved in the development of an awareness program on the benefits of energy efficient lighting technologies | Workshops, focus group dialogues One-on-one meetings Phone/email | MEMR/ DGNREEC PMU | To be confirmed in the annual plan As frequently as necessary |
| General Public, NGOs and other relevant organisations | The general public who does not participate directly in the project activities but has an interest in being informed on project results and lessons learned | Public meetings Annual reports Forums, conferences and exhibitions Other reading material Email, phone, fax or mail Radio/TV Social media, UNDP’s website, other project related websites | MEMR/ DGNREEC PMU UNDP | Before every pilot project start Annually To be confirmed in the annual plan Throughout project implementation |
| Coal power plant workers, conventional lighting manufacturers and other stakeholders | Stakeholders who might have a concern about the project’s potential impacts on them | Public consultation meetings Other reading material Email, phone, fax or mail Radio/TV Social media, UNDP’s website, other project related websites | MEMR/ DGNREEC PMU | Before every pilot project start Throughout project implementation |

Grievance mechanism

The project management unit (PMU) is suggested to take the role of Grievance Redress Mechanism (GRM) with the mandate to:

- Receive and address any concerns, complaints, notices of emerging conflicts, or grievances (collectively“ Grievance”) alleging actual or potential harm to affected person(s) (the “Claimant(s)”) arising from Project;

- Assist in resolution of Grievances between and among Project Stakeholders; as well as the various government ministries, agencies and commissions, CSOs and NGOs, and others in the context of the Project; and

- Conduct itself at all times in a flexible, collaborative, and transparent manner aimed at problem solving and consensus building.

The GRM will receive and consider all comments and complaints associated with the project. Any individual or organisation may send comments and/or complaints in person, by phone, fax, email or mail, or in any other manner that the PMU may deem fit. All Grievances and reports of conflict will be received, assigned a tracking number, acknowledged to Claimant, recorded electronically, and subject to periodic updates to the Claimant as well as the office file.

Normally all grievances will be acknowledged within 3-5 working days in the form of a standard letter or email providing a brief description of the process that will be followed. A response will be communicated to the Claimant within 14-21 working days of receiving the grievance.

Files for each Grievance will be available for review by the Claimant and other Stakeholders involved in the Grievance, or their designated representative(s). Appropriate steps will be taken to maintain the confidentiality of the Claimant, if previously requested. The GRM will provide periodic updates to the Claimant regarding the status and current actions to resolve the Grievance. Not including the acknowledgment of receipt of the Grievance, such updates will occur within reasonable intervals (not greater than every 30 days).

Bi-annually, the GRM will make available to the public, a report describing the work of the GRM, listing the number and nature of the Grievances received and processed in the past six months, a date and description of the Grievances received, resolutions, referrals and ongoing efforts at resolution, and status of implementation of ongoing resolutions. The level of detail provided with regard to any individual Grievance will depend on the sensitivity of the issues and Stakeholder concerns about confidentiality, while providing appropriate transparency about the activities of the GRM.

The aforementioned report will also highlight key trends in emerging conflicts, Grievances, and dispute resolution, and make recommendations regarding: (i) Measures that can be taken by the Government to avoid future harms and Grievances; and (ii) Improvements to the GRM that would enhance its effectiveness, accessibility, predictability, transparency, legitimacy, credibility, and capacity.

In addition to the GRM described above, other channels can be utilized by Complaints through UNDP’s Accountability Mechanism (Stakeholder Response Mechanism [SRM] and Social and Environmental Compliance Unit [SECU]). These channels can be utilized for grievances purporting that UNDP is not complying with the social and environmental policies or commitments that apply to its projects (i.e. corruption, coercion or major systematic violations of rights and/or policies), or in other cases where the Complaint is not satisfied with the GRM’s response. All SECU and SRM Requests can be submitted via an online webform.

Monitoring and reporting

The stakeholders will be engaged in project’s monitoring and reporting process through various activities and communication channels as outlined in the project document’s Monitoring and Evaluation Plan and in Table 3. Results of stakeholder engagement activities will be reported back to the stakeholders throughout the project implementation.

The Stakeholder Engagement Plan itself is a living document and will be reviewed and updated regularly as response to changed project circumstances that might arise during the project implementation period. The overall responsibility of Monitoring and Reporting will be that of the Project Manager who will delegate the responsibility to one of the project staff assigned to undertake Monitoring and Evaluation.

Annex Q:

Annex R: Supplemental Provisions to the Project Document: The Legal Context

General responsibilities of the Government, UNDP and the executing agency

- All phases and aspects of UNDP assistance to this project shall be governed by and carried out in accordance with the relevant and applicable resolutions and decisions of the competent United Nations organs and in accordance with UNDP's policies and procedures for such projects, and subject to the requirements of the UNDP Monitoring, Evaluation and Reporting System.

- The Government shall remain responsible for this UNDP-assisted development project and the realization of its objectives as described in this Project Document.

- Assistance under this Project Document being provided for the benefit of the Government and the people of Indonesia, the Government shall bear all risks of operations in respect of this project.

- The Government shall provide to the project the national counterpart personnel, training facilities, land, buildings, equipment and other required services and facilities. It shall designate the Government Co-operating Agency named in the cover page of this document (hereinafter referred to as the "Co-operating Agency"), which shall be directly responsible for the implementation of the Government contribution to the project.

- The UNDP undertakes to complement and supplement the Government participation and will provide through the Executing Agency the required expert services, training, equipment and other services within the funds available to the project.

- Upon commencement of the project the Executing Agency shall assume primary responsibility for project execution and shall have the status of an independent contractor for this purpose. However, that primary responsibility shall be exercised in consultation with UNDP and in agreement with the Co-operating Agency.  Arrangements to this effect shall be stipulated in the Project Document as well as for the transfer of this responsibility to the Government or to an entity designated by the Government during the execution of the project.

- Part of the Government's participation may take the form of a cash contribution to UNDP. In such cases, the Executing Agency will provide the related services and facilities and will account annually to the UNDP and to the Government for the expenditure incurred.

(a) 	Participation of the Government

- The Government shall provide to the project the services, equipment and facilities in the quantities and at the time specified in the Project Document. Budgetary provision, either in kind or in cash, for the Government's participation so specified shall be set forth in the Project Budgets.

- The Co-operating Agency shall, as appropriate and in consultation with the Executing Agency, assign a director for the project on a full-time basis.  He shall carry out such responsibilities in the project as are assigned to him by the Co-operating Agency.

- The estimated cost of items included in the Government contribution, as detailed in the Project Budget, shall be based on the best information available at the time of drafting the project proposal.  It is understood that price fluctuations during the period of execution of the project may necessitate an adjustment of said contribution in monetary terms; the latter shall at all times be determined by the value of the services, equipment and facilities required for the proper execution of the project.

- Within the given number of man-months of personnel services described in the Project Document, minor adjustments of individual assignments of project personnel provided by the Government may be made by the Government in consultation with the Executing Agency, if this is found to be in the best interest of the project.  UNDP shall be so informed in all instances where such minor adjustments involve financial implications.

- The Government shall continue to pay the local salaries and appropriate allowances of national counterpart personnel during the period of their absence from the project while on UNDP fellowships.

- The Government shall defray any customs duties and other charges related to the clearance of project equipment, its transportation, handling, storage and related expenses within the country.  It shall be responsible for its installation and maintenance, insurance, and replacement, if necessary, after delivery to the project site.

The Government shall make available to the project - subject to existing security provisions - any published and unpublished reports, maps, records and other data which are considered necessary to the implementation of the project.

- Patent rights, copyright rights and other similar rights to any discoveries or work resulting from UNDP assistance in respect of this project shall belong to the UNDP.  Unless otherwise agreed by the Parties in each case, however, the Government shall have the right to use any such discoveries or work within the country free of royalty and any charge of similar nature.

- The Government shall assist all project personnel in finding suitable housing accommodation at reasonable rents.

- The services and facilities specified in the Project Document which are to be provided to the project by the Government by means of a contribution in cash shall be set forth in the Project Budget.  Payment of this amount shall be made to the UNDP in accordance with the Schedule of Payments by the Government.

- Payment of the above-mentioned contribution to the UNDP on or before the dates specified in the Schedule of Payments by the Government is a prerequisite to commencement or continuation of project operations.

(b)	Participation of the UNDP and the executing agency

- The UNDP shall provide to the project through the Executing Agency the services, equipment and facilities described in the Project Document.  Budgetary provision for the UNDP contribution as specified shall be set forth in the Project Budget.

- The Executing Agency shall consult with the Government and UNDP on the candidature of the Project Manager who, under the direction of the Executing Agency, will be responsible in the country for the Executing Agency's participation in the project. The Project Manager shall supervise the experts and other agency personnel assigned to the project, and the on-the-job training of national counterpart personnel.  He shall be responsible for the management and efficient utilization of all UNDP-financed inputs, including equipment provided to the project.

- The Executing Agency, in consultation with the Government and UNDP, shall assign international staff and other personnel to the project as specified in the Project Document, select candidates for fellowships and determine standards for the training of national counterpart personnel.

- Fellowships shall be administered in accordance with the fellowships regulations of the Executing Agency.

- The Executing Agency may, in agreement with the Government and UNDP, execute part or all of the project by subcontract.  The selection of subcontractors shall be made, after consultation with the Government and UNDP, in accordance with the Executing Agency's procedures.

- All material, equipment and supplies which are purchased from UNDP resources will be used exclusively for the execution of the project, and will remain the property of the UNDP in whose name it will be held by the Executing Agency.  Equipment supplied by the UNDP shall be marked with the insignia of the UNDP and of the Executing Agency.

- Arrangements may be made, if necessary, for a temporary transfer of custody of equipment to local authorities during the life of the project, without prejudice to the final transfer.

- Prior to completion of UNDP assistance to the project, the Government, the UNDP and the Executing Agency shall consult as to the disposition of all project equipment provided by the UNDP. Title to such equipment shall normally be transferred to the Government, or to an entity nominated by the Government, when it is required for continued operation of the project or for activities following directly therefrom.  The UNDP may, however, at its discretion, retain title to part or all of such equipment.

- At an agreed time after the completion of UNDP assistance to the project, the Government and the UNDP, and if necessary the Executing Agency, shall review the activities continuing from or consequent upon the project with a view to evaluating its results.

- UNDP may release information relating to any investment oriented project to potential investors, unless and until the Government has requested the UNDP in writing to restrict the release of information relating to such project.

Rights, Facilities, Privileges and Immunities

- In accordance with the Agreement concluded by the United Nations (UNDP) and the Government concerning the provision of assistance by UNDP, the personnel of UNDP and other United Nations organizations associated with the project shall be accorded rights, facilities, privileges and immunities specified in said Agreement.

- The Government shall grant UN volunteers, if such services are requested by the Government, the same rights, facilities, privileges and immunities as are granted to the personnel of UNDP.

- The Executing Agency's contractors and their personnel (except nationals of the host country employed locally) shall:

  - Be immune from legal process in respect of all acts performed by them in their official capacity in the execution of the project;

  - Be immune from national service obligations;

  - Be immune together with their spouses and relatives dependent on them from immigration restrictions;

  - Be accorded the privileges of bringing into the country reasonable amounts of foreign currency for the purposes of the project or for personal use of such personnel, and of withdrawing any such amounts brought into the country, or in accordance with the relevant foreign exchange regulations, such amounts as may be earned therein by such personnel in the execution of the project;

  - Be accorded together with their spouses and relatives dependent on them the same repatriation facilities in the event of international crisis as diplomatic envoys.

- All personnel of the Executing Agency's contractors shall enjoy inviolability for all papers and documents relating to the project.

- The Government shall either exempt from or bear the cost of any taxes, duties, fees or levies which it may impose on any firm or organization which may be retained by the Executing Agency and on the personnel of any such firm or organization, except for nationals of the host country employed locally, in respect of:

- The salaries or wages earned by such personnel in the execution of the project;

- Any equipment, materials and supplies brought into the country for the purposes of the project or which, after having been brought into the country, may be subsequently withdrawn therefrom;

- Any substantial quantities of equipment, materials and supplies obtained locally for the execution of the project, such as, for example, petrol and spare parts for the operation and maintenance of equipment mentioned under (b), above, with the provision that the types and approximate quantities to be exempted and relevant procedures to be followed shall be agreed upon with the Government and, as appropriate, recorded in the Project Document; and

- As in the case of concessions currently granted to UNDP and Executing Agency's personnel, any property brought, including one privately owned automobile per employee, by the firm or organization or its personnel for their personal use or consumption or which after having been brought into the country, may subsequently be withdrawn therefrom upon departure of such personnel.

- The Government shall ensure:

(a)	prompt clearance of experts and other persons performing services in respect of this project; and

(b)	the prompt release from customs of:

(i)	equipment, materials and supplies required in connection with this project; and

(ii)	property belonging to and intended for the personal use or consumption of the personnel of the UNDP, its Executing Agencies, or other persons performing services on their behalf in respect of this project, except for locally recruited personnel.

- The privileges and immunities referred to in the paragraphs above, to which such firm or organization and its personnel may be entitled, may be waived by the Executing Agency where, in its opinion or in the opinion of the UNDP, the immunity would impede the course of justice and can be waived without prejudice to the successful completion of the project or to the interest of the UNDP or the Executing Agency.

- The Executing Agency shall provide the Government through the resident representative with the list of personnel to whom the privileges and immunities enumerated above shall apply.

- Nothing in this Project Document or Annex shall be construed to limit the rights, facilities, privileges or immunities conferred in any other instrument upon any person, natural or juridical, referred to hereunder.

Suspension or termination of assistance

1.	The UNDP may by written notice to the Government and to the Executing Agency concerned suspend its assistance to any project if in the judgement of the UNDP any circumstance arises which interferes with or threatens to interfere with the successful completion of the project or the accomplishment of its purposes.  The UNDP may, in the same or a subsequent written notice, indicate the conditions under which it is prepared to resume its assistance to the project.  Any such suspension shall continue until such time as such conditions are accepted by the Government and as the UNDP shall give written notice to the Government and the Executing Agency that it is prepared to resume its assistance.

2.	If any situation referred to in paragraph 1, above, shall continue for a period of fourteen days after notice thereof and of suspension shall have been given by the UNDP to the Government and the Executing Agency, then at any time thereafter during the continuance thereof, the UNDP may by written notice to the Government and the Executing Agency terminate the project.

3.	The provisions of this paragraph shall be without prejudice to any other rights or remedies the UNDP may have in the circumstances, whether under general principles of law or otherwise.

http://www4.unfccc.int/ndcregistry/pages/Party.aspx?party=IDN

The Green City Development program promotes implementation of green open space, efficient energy/green energy, water management, waste management, green building, green transport and green community. In its implementation, the Green City Development project has mainly achieved promoting green open space in cities, while the green energy components are lagging behind due to low technical and financing capacity of cities in planning and implementing green actions.

ASEAN SHINE lighting-regional market assessment. IIEC.February 2016

ASEAN LED Lamp Benchmarking: Test Results Analysis. August 2017.

Data is aggregated from three Association of EE local manufacturers namely APERLINDO, ALINDO and GAMATRINDO. Unfortunately this data is still temporary because not all data from the three associations are derived from all its members, e.g.  data from Alindo is only obtained from one of its 10 member companies (PT Solaren Ledindo). Therefore, in the implementation of ADLIGHT, more detailed and accurate data are needed in Component 1 activities, especially with regards to market share periodic activity.

Under the Directorate General of Customs and Excise (Direktorat Jenderal Bea dan Cukai)

Currently, most of the SNI on lighting are an identical copy of International Electrotechnical Commission (IEC) standards. For example, SNI IEC 60598-1:2016 is an identical copy of IEC 60598:2014.

With all required standard for Lighting/Luminaire made available in SNI format, BSN will draft and implement a regulation on the minimum quality standard for LED lighting. The minimum quality standard will list down all of minimum testing standard required in order to have good quality LED lighting. Some countries such as Hong Kong, Singapore, and Jamaica have issued such for government procurement guideline documents. By having a minimum quality standard available for consumers, manufacturers of LED in Indonesia and importation from abroad must comply with standards requirements, and therefore, the quality of LED lighting to be made available in Indonesia can be rightly monitored, verified and enforced (in an MVE system). With the minimum quality standard that is aligned with international standards, local LED manufactures have the chance for their products to be marketed also internationally.

For example, if a manufacturer invests in equipment for production, the cost of equipment is not credited to the local content value of their products; therefore, the policy appears to be a disincentive to the manufacturers

Countries like Hong Kong, Singapore, China, Jamaica, and other countries have a procurement guideline for the government based on national standards issued by the respective governments to assist in procuring LED lighting.

The manufacturers have been informed that HS codes were created by the World Custom Organization (WCO) and that WCO has detailed definition of all wording on the HS codes which the custom can use and follow as their definition guideline

As of now, the current practice are: to store them at the warehouse, donate, or dispose them as regular waste, but these materials are potentially hazardous to the environment, therefore it need to be dispose with a proper waste management technique.

Must be considered for 10 years of direct CO2 emission reductions from all pilot projects and replications. Since this project focuses entire sector, cumulative emission reductions during economic lifetime (considered 10 years including project duration of 3 years)

Based on GEF CO2 emission reduction calculation methodology, as it focuses entire sector. In this case it is the cumulative emission reduction for 10 year from best case of all sectors multiple by factor 0.5

Considered for 10 years of economic lifetime as per GEF guidelines (Direct + Indirect).

See http://www.undp.org/content/undp/en/home/operations/transparency/information_disclosurepolicy/

See https://www.thegef.org/gef/policies_guidelines

Various banks and financing institutions in Indonesia, including Bank Mandiri, BRI, BNI, BCA, Bank Muamalat, BRI Syariah, BJB and Bank Artha Graha are mobilized and introduced by OJK on financing EEL business opportunities

SNI refers to Standard National Indonesia (or National Indonesian Standard) issued by BSN as a recommended standard (standard minimum quality for LED) that is in line with the ASEAN Regional approach that can be used by local authorities while the MEPS with the required energy labeling is being developed The MEPS and labeling development and approval at the national and regional levels could take 2 – 3 years or more and therefore need to be facilitated by the Project by removing barriers.

Ideas on  developing SNI Software is already initiated by BSN.The software will be one of the MVE tools to trace products when Standard Miminum Qualilty/MEPS is established to ensure the LED product in the market are legal. HS code dispute on imported LED component is already well addressed by the Custom authorities (PKSI)–  Service for import to get clarification on Harmonization System (HS) clasification and Indonesian National Single Window (INSW) . HS code dispute is one of core barriers for imported EE lighting components for local LED manufacturers. The system can also include the use a database and searching system for LED products and codes. We will also make a pocket guide for manufactures on how to import their raw materials in order to manufacture their LED products.

Proposed innovative financial support schemes to accelerate penetration of advanced lighting systems, may include: (a) PPP mechanism for smart city(ies) LED street lighting projects; (b) ESCO model Feasibility Study (FS) Template and Financial Modeling Software; (c) Credit Guarantee Facility for Energy Efficiency LED lighting investment; and (d) Bundling LED lighting projects as accepted collateral for banking sector

Initially identified pilot demonstrations during the PPG stage include the following: (a) smart lighting and smart monitoring system LED, (b) ESCO model for state-owned bank building, (c) ESCO model for LKPP (Public Procurement Agency) for government LED implementation, and (d) public-private partnership scheme model for LED projects.

Assistance in completing the pending existing ESCO model in Smart Cities in Solo and Bandung as the 2 cities which have on-going project development, being assisted by Bappenas and LKPP, but it requires next stage of mobilization towards final financial arrangement

See guidance here:  https://info.undp.org/global/popp/frm/pages/financial-management-and-execution-modalities.aspx

Excluding project team staff time and UNDP staff time and travel expenses.

The costs of UNDP Country Office and UNDP-GEF Unit’s participation and time are charged to the GEF Agency Fee.

See https://popp.undp.org/_layouts/15/WopiFrame.aspx?sourcedoc=/UNDP_POPP_DOCUMENT_LIBRARY/Public/PPM_Project%20Management_Closing.docx&action=default.

This includes 13,800 USD allocated for 4th year to help close the project.

Summary table should include all financing of all kinds: GEF financing, cofinancing, cash, in-kind, etc...

Various banks and financing institutions in Indonesia, including Bank Mandiri, BRI, BNI, BCA, Bank Muamalat, BRI Syariah, BJB and Bank Artha Graha are mobilized and introduced by OJK on financing EEL business opportunities

Initially identified pilot demonstrations during the PPG stage include the following: (a) smart lighting and smart monitoring system LED, (b) ESCO model for state-owned bank building, (c) ESCO model for LKPP (Public Procurement Agency) for government LED implementation, and (d) public-private partnership scheme model for LED projects.

Assistance in completing the pending existing ESCO model in Smart Cities in Solo and Bandung as the 2 cities which have on-going project development,  being assisted by Bappenas and LKPP, but it requires next stage of mobilization towards final financial arrangement

Various banks and financing institutions in Indonesia, including Bank Mandiri, BRI, BNI, BCA, Bank Muamalat, BRI Syariah, BJB and Bank Artha Graha are mobilized and introduced by OJK on financing EEL business opportunities

Various banks and financing institutions in Indonesia, including Bank Mandiri, BRI, BNI, BCA, Bank Muamalat, BRI Syariah, BJB and Bank Artha Graha are mobilized and introduced by OJK on financing EEL business opportunities

Prohibited grounds of discrimination include race, ethnicity, gender, age, language, disability, sexual orientation, religion, political or other opinion, national or social or geographical origin, property, birth or other status including as an indigenous person or as a member of a minority. References to “women and men” or similar is understood to include women and men, boys and girls, and other groups discriminated against based on their gender identities, such as transgender people and transsexuals.

In regards to CO2, ‘significant emissions’ corresponds generally to more than 25,000 tons per year (from both direct and indirect sources). [The Guidance Note on Climate Change Mitigation and Adaptation provides additional information on GHG emissions.]

Forced evictions include acts and/or omissions involving the coerced or involuntary displacement of individuals, groups, or communities from homes and/or lands and common property resources that were occupied or depended upon, thus eliminating the ability of an individual, group, or community to reside or work in a particular dwelling, residence, or location without the provision of, and access to, appropriate forms of legal or other protections.

Potential pollution and risks from hazardous and non-hazardous waste materials from replaced fluorescent lamps/CFL and other conventional lighting systems and accessories particularly mercury content and sharp glass bulb parts need to be managed and proper disposal system be implemented and monitored.

1. Sustainable development pathways; 2. Inclusive and effective democratic governance; 3. Resilience building

sustainable production technologies, access to modern energy services and energy efficiency, natural resources management, extractive industries, urbanization, citizen security, social protection, and risk management for resilience

This question will have a “Not Applicable” checkbox which can be activated for global and regional projects, or country projects with clearance from the RBx desk officer.

This question will have a “Not Applicable” checkbox which can be activated for global and regional projects, or country projects with clearance from the RBx desk officer.

This question will have a “Not Applicable” checkbox which can be activated for global and regional projects

This question will have a “Not Applicable” checkbox which can be activated for global and regional projects, or country projects with clearance from the RBx desk officer.

This question will have a “Not Applicable” checkbox which can be activated for global and regional projects, or country projects with clearance from the RBx desk officer.

Proposed innovative financial support schemes to accelerate penetration of advanced lighting systems, may include: (a) PPP mechanism for smart city(ies) LED street lighting projects; (b) ESCO model Feasibility Study (FS) Template and Financial Modeling Software; (c) Credit Guarantee Facility for Energy Efficiency LED lighting investment; and (d) Bundling LED lighting projects as accepted collateral for banking sector

http://www.id.undp.org/content/dam/indonesia/2017/doc/INS Indonesia_Country%20Explanatory%20Note_HDR2016.pdf

https://www.adb.org/sites/default/files/publication/182935/ino-paper-16-2016.pdf

https://www.oxfam.org/sites/www.oxfam.org/files/bp-towards-more-equal-indonesia-230217-en_0.pdf

http://www.id.undp.org/content/indonesia/en/home/presscenter/articles/2017/09/15/no-sdg-untouched-by-women-owned-social-enterprises.html

https://sustainabledevelopment.un.org/memberstates/indonesia

https://www.energytoday.net/economics-policy/policies/women-energy-economic-empowerment-applying-gender-lens-amplify-impact-energy-access/

### Ministry of Energy and Mineral Resources – Strategi Pemerintah Capai Rasio Elektrifikasi 99% di Tahun 2019, https://www.esdm.go.id/id/berita-unit/direktorat-jenderal-ketenagalistrikan/strategi-pemerintah-capai-rasio-elektrifikasi-99-di-tahun-2019

Ibid

James Melik, “Solutions sought to end use of kerosene lamps”, http://www.bbc.com/news/business-18262217

Energia - Gender Training Manual, http://www.energia.org/cm2/wp-content/uploads/2015/04/04.-1319143629-Gendertrainingmanual.pdf

https://www.transparency-partnership.net/sites/default/files/ssli_nama_mrv.pdf

https://unhabitat.org/wp-content/uploads/2014/07/Gender-Responsive-Urban-Planning-and-Design.pdf

http://asiapacific.unwomen.org/ru/countries/indonesia

http://www.nama-database.org/index.php/Smart_Street_Lighting_Initiative_(SSLI)

Sugandi Pernama, Aziz & Siong (2014). Is mom energy efficient? A study of gender, household energy consumption and family decision making in Indonesia. Energy Research & Social Science 6 (2015) 78-86

http://www.academia.edu/20862146/Is_mom_energy_efficient_A_study_of_gender_household_energy_consumption_and_family_decision_making_in_Indonesia

http://web.unep.org/sites/default/files/ggeo/ggeo_summary_report_final.pdf

http://iesr.or.id/2017/01/fgd-gender-mainstreaming-in-the-energy-sector/?lang=en

https://www.adb.org/sites/default/files/publication/182935/ino-paper-16-2016.pdf

https://www.energytoday.net/economics-policy/policies/women-energy-economic-empowerment-applying-gender-lens-amplify-impact-energy-access/

Standard annex to project documents for use in countries which are not parties to the Standard Basic Assistance Agreement (SBAA).

May also be designated Project Co-ordinator or Chief Technical Adviser, as appropriate.