# Mid Term Review of the UNEP project:

# Ecosystem Conservation and Community Livelihood Enhancement in Northwestern Zambia Project, GEF ID:10192

December 2025

Photo Credits

Front cover: Members of the Kewundu Community Forestry Group Executive Committee, Women’s Sub-Committee and Honorary Forestry Officers, Ntambu, Mwinilunga, Zambia, 17th June 2025. Photo by Mulaku K. Muyunda.

© UNEP / G. Mickels-Kokwe (External Reviewer), United Nations Environment Programme, Review Mission (2025)

This report has been prepared by an External Consultant as part of a Mid-Term Review, which is a management-led process to assess performance at the project’s mid-point. The UNEP Evaluation Office provides templates and tools to support the review process. The findings and conclusions expressed herein do not necessarily reflect the views of Member States or the UN Environment Programme Senior Management.

For further information on this report, please contact:

UNEP Ecosystems Division/GEF Biodiversity and Land Degradation Unit

United Nations Avenue, Gigiri, Nairobi, Kenya

P.O. Box 3055, 00100, Nairobi, Kenya

Tel: +254 (0) 20 7621234

Email: daniel.pouakouyou@un.org

“Ecosystem Conservation and Community Livelihood Enhancement in Northwestern Zambia”
 GEF ID:10192

December 2025

All rights reserved

© UNEP 2025

#### Acknowledgements

This Mid-Term Review (MTR) was prepared for UNEP Ecosystems Division / GEF Biodiversity and Land Degradation Unit by Ms. Guni Mickels-Kokwe (External Reviewer). The MTR was conducted with the help of the Ecosystem Conservation and Community Livelihood Enhancement in Northwestern Zambia (ECCLE) Project Team and the Forestry Department in Zambia. The MTR process was consultative, aiming to integrate stakeholders in the review, to whom I am indebted for their valuable feedback and comments, to everyone who shared their time and support to make this review process a success. The final report is prepared in accordance with the UNEP Review Guidelines for Structure and Content.

My special appreciation goes to the Project Manager, Ms. Ethel S. Mudenda and the entire ECCLE team; The Nature Conservancy (TNC) for logistical and office support; the Director Forestry Mr. Sitwala Wamunyima, Provincial Forestry Officer Mr. Maxwell Phiri and Provincial ECCLE Focal Point Mr. Mulako K. Muyunda; and the community members in Kelongwa Kamanana and Ntambu project sites.

I would further like to acknowledge the support rendered by the UNEP Task Manager, Dr Daniel Pouakouyou and Fund Management Officer Mr. George Saddimbah.

The views expressed in this report are intended to provide an overview of and some lessons from the ECCLE project progress. I have tried to balance my views and offer a fair perspective of what was observed, with recommendations that point towards the future. The contribution this project may make towards mainstreaming Community Forestry for Sustainable Forest Management in Zambia is significant. I would like to wish the project every success in their continuing endeavours.

Guni Mickels Kokwe

MTR Review Expert

Koskenkylän Saha, Finland

25 September 2025

UNEP Task Manager: Dr Daniel Pouakouyou, UNEP HQ, Nairobi

Fund Management Officer: Mr. George Saddimbah, UNEP HQ, Nairobi

#### External Consultant Brief Biography

Mrs. Guni Mickels Kokwe (M.Sc. Dev. Geog.) is a rural development and community forestry expert, social scientist by education, with 20+ years of working experience from Central, Southern and Eastern Africa, i.e. Zambia, Ethiopia, Kenya, Tanzania and Zimbabwe. Her core competence is project design, management and implementation of natural resources-based livelihood development for sustainable landscape management. She has worked extensively in Zambia, with rural communities to strengthen food and livelihood security; develop smallholder agribusiness; to set up local structures for community forestry; and in developing natural product value chains, in nine of Zambia’s ten provinces.

Her experience ranges from the identification and appraisal, participatory planning and design to the implementation, monitoring and evaluation of natural resource development projects for the Zambian Government and multiple donors, bilateral and multilateral, including MFA Finland, FAO, UNDP, WB. Her practical project experience ranges from the local to the national and across many stakeholder groups. She enjoys developing applications in the form of research tools, analytical models and project assessment frameworks. She worked in Zambia as a Technical Advisor with the Forestry Department in the early 2000s, when participatory forestry was piloted and has had the privilege to follow the process ever since.

#### About the Review

Joint review: No.

Report language(s): English

Review type: Mid-term Review

Brief description: This report is a management-led Mid-Term Review (MTR) of the UNEP Ecosystem Conservation and Community Livelihood Enhancement in Northwestern Zambia (ECCLE) Project implemented since 2021.

The ECCLE project is a five-year project aimed at addressing the direct and indirect drivers of deforestation and the degradation of forest and agricultural lands. The Project further addresses barriers to sustainable land management and to biodiversity conservation at three project sites in three districts in the Northwestern Province (NWP) of the Republic of Zambia. The project also aims to develop models for community driven sustainable forest management ready for mainstreaming. This aligns with the priorities of the GEF-7 Impact Program (IP) on Sustainable Forest Management (SFM) in Drylands Landscapes.

In line with the UNEP Evaluation Policy and the UNEP Programme and Project Management Manual, the Mid-Term Review (MTR) is undertaken to analyse whether the project is on-track, what problems or challenges the project is encountering, and what corrective actions are required. The assessment is formative and consultative. A key aim of the Mid-Term Review is to encourage reflection and learning by UNEP staff, the implementing partners and key project stakeholders.

Key words: Community Forestry (CF), Participatory Forestry (PF), Gender; Sustainable Forest Management (SFM); Biodiversity Conservation; Miombo Eco-Region

Project period under Review: August 2021 – December 2024

Primary data collection period: May-August 2025

Field Mission dates: 3-26 June 2025

#### Table of Contents

Figures & Tables	vi

Abbreviations and Acronyms	vii

Project Identification table	ix

Executive Summary	1

I: Project Overview	5

II: Review Methods	11

III: Theory of Change	14

IV: Review Findings	20

A:  Strategic Relevance	20

B: Quality & Revision of Project Design	21

C: Effectiveness	23

D: Financial Management	33

E: Efficiency	33

F: Monitoring and Reporting	35

G: Exit and Sustainability	37

H: Factors and Processes Affecting Project Performance and Cross-cutting Issues	39

V: Conclusions	46

VI: Lessons Learned	51

VII: Recommendations	53

Annexes	62

Annex 1. Response to stakeholder comments	62

Annex 2. People consulted during the Mid Term Review	65

Annex 3. Key Documents Consulted	66

Annex 4. Review itinerary	67

Annex 5. Project budget, expenditures and co-financing	69

Annex 6. Financial Management	71

Annex 7. Communication and Outreach Tools (sample)	72

Annex 8. Brief CV of the Reviewer	74

Annex 9. MTR Terms of Reference (Less original ToC / RF and Annexes)	75

Annex 10. GEF Portal inputs (for GEF funded projects)	101

Annex 11. GEF Risks to achieving project outcomes (for GEF funded projects)	105

Annex 12. Theory of Change (original)	108

Annex 13. Project Results Framework (original)	110

Annex 14. Intervention Logic Narrative (original)	125

Annex 15. ECCLE Project Stakeholders @ Mid-Term Review: power and interest	126

Annex 16. “Results Chain at Review”:  Proposed revisions to the ECCLE results chain	128

Annex 17. Specific Review Questions and Auxiliary Issues	130

Annex 18.  ECCLE project progress against key deliverables and benchmarks	131

Annex 19. ECCLE Project Sustainability Analysis	136

Annex 20. Project Management (H2): ECCLE implementor roles and performance	138

### Figures & Tables

Figures

Figure 1. Location of Zambia’s Northwestern Province and the three ECCLE project areas

Figure 2. ECCLE Project Implementation Structure

Figure 3. ECCLE Theory of Change at Review (rToC)

Tables

Table 1. Summary of ECCLE project performance rating

Table 2. ECCLE Project review parameters

Table 3. ECCLE Project Assumptions and drivers, TOC at Review

Table 4. Weighted rating of the Quality of ECCLE Project Design (criterion B)

Table 5. Overall rating of ECCLE Project Effectiveness (criterion C)

Table 6. MT Review Findings: Monitoring of ECCLE Project Implementation

Table 7. MT Review Findings: ECCLE Project Reporting

Table 8. Rating the ECCLE Project likelihood of sustainability

Table 9. Gender mainstreaming tracking table as measured by ECCLE M&E Unit

Table 10. Summary of ECCLE project successes and shortcomings

Table 11. UNEP Key Strategic Questions

Table 12. ECCLE Project Performance Rating (full)

### Abbreviations and Acronyms

| CFM | Community Forest Management |
| --- | --- |
| CFMA | Community Forest Management Area |
| CFMG | Community Forest Management Group |
| CSA | Climate Smart Agriculture |
| CRB | Community Resource Board |
| CSR(P) | Corporate Social Responsibility (Programmes) |
| DIDP | District Integrated Development Plan |
| DNPW | Department of National Parks and Wildlife |
| EA | Executing Agency (vis-à-vis GEF, The Nature Conservancy) |
| ECCLE | Ecosystem Conservation and Community Livelihood Enhancement (Project) |
| FD | Forestry Department |
| FNRM | Forest and Natural Resources Management |
| GA | Gender Analysis / Audit |
| GMAP | Gender Mainstreaming and Action Plan |
| GSAP | Gender Strategy and Action Plan |
| GEF | Global Environment Facility |
| GRZ | Government of the Republic of Zambia |
| HQ | Headquarters |
| IA | Implementing Agency (vis-à-vis GEF, UNEP) |
| IDP | Integrated Development Plan |
| ILUP | Integrated Land Use Plan |
| IP | Implementation Partner |
| KCF | Kasempa Community Foundation |
| KM | Knowledge Management |
| M&E | Monitoring and Evaluation |
| MCDSS | Ministry of Community Development and Social Services |
| MFL | Ministry of Fisheries and Livestock |
| MGEE | Ministry of Green Economy and Environment |
| MLNR | Ministry of Lands and Natural Resources ( |
| MLGRD | Ministry of Local Government and Rural Development |
| MoA | Ministry of Agriculture |
| MoU | Memorandum of Understanding |
| MTR | Mid-Term Review |
| NGO | Non-governmental organization |
| NR | Natural Resources |
| NRM | Natural Resources Management |
| NTFP | Non-Timber Forest Product |
| NWP | Northwestern Province |
| OFP | Operational Focal Point (GEF) |
| PCA | Project Cooperation Agreement |
| PLIR | Policy, legislation, institution, regulation |
| PIR | Project Implementation Review (GEF) |
| PIU | Project Implementation Unit (ECCLE) |
| PM | Project Management |
| ProDoc | Project Document |
| PSC | Project Steering Committee (ECCLE) |
| PTC | Project Technical Committee (ECCLE) |
| REDD+ | Reducing Emissions from Deforestation and Forest Degradation (UNFCC) |
| rTOC | Theory of Change at Review |
| SA | Sustainable Agriculture |
| SDG | Sustainable Development Goals |
| SFM | Sustainable Forest Management |
| SI | Statutory Instrument |
| TFL | Trident Foundation Limited |
| TNC | The Nature Conservancy |
| TOC | Theory of Change |
| TOR | Terms of Reference |
| TSU | Technical Support Unit (ECCLE) |
| UN | United Nations |
| UNEP | United Nations Environment Programme |
| USD | United States Dollars |
| WLCP | West Lunga Conservation Project |
| WWF | World Wildlife Fund for Nature |

## Project Identification Table

| UNEP PIMS ID/SMA ID: | 85583 | Grant ID (if applicable): S1-32GFL-000707 | GEF ID: 10192 |
| --- | --- | --- | --- |
| UNEP Management (Division/Branch/Unit): | Ecosystems Division / GEF Biodiversity and Land Degradation Unit / Biodiversity and Land Branch |  |  |
| Implementing Partners: | The Ministry of Green Economy and Environment – Department of Forestry and The Nature Conservancy |  |  |
| Sources of Funding: | Country(ies): Zambia | Institution Name/Type: - The Nature Conservancy, executing agency, NGO - Ministry of Green Economy and Environment (formerly Ministry of Lands and Natural Resources), Government of Zambia - Ministry of Agriculture, Government of Zambia - Ministry of Tourism, Government of Zambia - World Wildlife Fund, Implementation partner, NGO - Trident Foundation Ltd for Kalumbila Minerals Limited, Implementation partner, private sector |  |
| Relevant SDG(s): | Goal 5: Achieve gender equality and empower all women and girls. 5.a: Undertake reforms to give women equal rights to economic resources, as well as access to ownership and control over land and other forms of property, financial services, inheritance and natural resources, in accordance with national laws Goal 10: Reduce inequality within and among countries. 10.1: By 2030, progressively achieve and sustain income growth of the bottom 40 per cent of the population at a rate higher than the national average. 10.2: By 2030, empower and promote the social, economic and political inclusion of all, irrespective of age, sex, disability, race, ethnicity, origin, religion or economic or other status. Goal 13: Take urgent action to combat climate change and its impacts. 13.3: Improve education, awareness-raising and human and institutional capacity on climate change mitigation, adaptation, impact reduction and early warning 13.b. Promote mechanisms for raising capacity for effective climate change-related planning and management in least developed countries and small island developing States, including focusing on women, youth, and local and marginalized communities Goal 15: Protect, restore, and promote sustainable use of terrestrial ecosystems, sustainably manage forests, combat desertification, and halt and reverse land degradation and halt biodiversity loss. 15.6: Promote fair and equitable sharing of the benefits arising from the utilization of genetic resources and promote appropriate access to such resources, as internationally agreed |  |  |
| MTS (all that apply): | Outcomes 1, 2 and 3 | UNEP approval date: | 2021-08-19 |
| Sub-programme: | Thematic: Nature action sub-Programme | Programme Coordination Project: | Conservation |
| Expected start date: | 2021-06-02 | Actual start date: | 2021-08-20 |
| Planned completion date: | 31.08.2026 | Actual operational completion date: | N/A |
| Planned total project budget at approval: | 25,718,585.00 | Actual total expenditures reported as of 2025-09-30: | $ 3,893,723.50 |
| Planned Extra-budgetary Funds:Co-Finance | Cash $1,700,000 In-kind: $18 680,000 | Secured Extra-budgetary Funds: | Cash: 3,668,854 In-kind: 50,251,316 |
|  |  | Actual Extra-budgetary Funds expenditures reported as of 2025-06-30 | Cash: 3,668,854 In-kind: $ 50,251,316 |
| First disbursement: | 20.09.2021 -$500,000 | Planned date of financial closure: | Estimated 1 year after operational completion. 2027-08-31 |
| No. of formal project revisions: | 0 | Date of last approved project revision: | N/A |
| No. of Steering Committee meetings: | 5 | Date of Last Steering Committee meeting: | 2025-07-23 |
| Mid-term Review/ Evaluation (planned date): | 2024-08-31 | Mid-term Review/ Evaluation (actual date): | 2024-09-27 |
| Terminal Evaluation (planned date): | 2027-02-28 | Terminal Evaluation (actual date): | N/A |
| Coverage – Implementing Country(ies): | Republic of Zambia | Coverage – Implementing Region(s): | Africa |
| Dates of previous project phases: | N/A | Status of future project phases: | N/A |

## Executive Summary

The Ecosystem Conservation and Community Livelihood Enhancement (ECCLE) project in Northwestern Province of Zambia is a five-year project under the GEF-7 cycle. It addresses the barriers to sustainable management of forests and other natural resources and the barriers to the development of sustainable agriculture in line with the priorities of the GEF-7 Impact Program (IP) Sustainable Forest Management (SFM) in Drylands Landscapes. The start date of the project was 20 August 2021. The planned technical completion date is 31 August 2026. The Implementing Agency (IA) is the UNEP Ecosystems Division. The Executing Agency (EA) is the Nature Conservancy (TNC) working together with the Forestry Department of the Ministry of Green Economy and Environment in Zambia.

The key threats to the rich biodiversity in the Northwestern Zambia include loss of forests and other natural resources and land degradation due to expansion of agriculture, unsustainable charcoal production, illegal logging, illegal mining, overfishing and uncontrolled bushfires. The root causes are poverty, food insecurity and a lack of alternative income opportunities, coupled with a high market demand for unsustainably produced forest products and inadequate benefits from biodiversity conservation to local communities. The ECCLE project addresses the barriers to sustainable land management and biodiversity conservation at three sites in three districts in the Northwestern Province. The project premise states that support to (i) communities strengthen systems for community-driven management of forests and other natural resources; (ii) the development of productive nature-based investments for sustained self-financing to conservation and enterprise development; and (iii) the adoption of sustainable agriculture practices and technologies to improve agriculture production and productivity, while also reducing the deforestation footprint of agriculture; would result in sustainable resource management and consequently enhanced biodiversity and improved livelihoods (reduced poverty).

The ECCLE project has a two-pronged approach and strategy. First, building local sustainable forest management at three project sites, strengthening community-based sustainable management of forest landscapes and improved livelihood opportunities for targeted forest-dependent rural communities. Second, building preparedness for mainstreaming gender-responsive community forestry at a greater geographical scale through the development of tested, proven systems of community management of forests and natural resources. The total budget for the project is USD 25,718,585, comprising USD 5, 338,585 in GEF funds and USD 20,380,000 USD in co-financing.

##### The Mid-term Review

This report presents the findings from the ECCLE project mid-term review (MTR) conducted between April and September 2025, which included a field mission to Zambia. The review was carried out in accordance with the UNEP Evaluation Policy and Programme Manual and the GEF requirements. In accordance with UNEP requirements, a revision to the project Theory of Change was proposed at inception and deliberated with the stakeholders during the review. A revised Theory of Change (rToC), compliant with UNEP terminology is presented in Section III. A recommendation of adjustment of outcome indicators is made, to improve on progress tracking and results-based management.

The MTR assessed project performance against the eight criteria prescribed in the UNEP evaluation methodology. It further explored the underlying factors for the project’s successes and challenges thus far and proposes corrective action. The MTR took place at 2/3 implementation point, which shaped the recommendations. Lessons learnt and recommendations are mainly targeted at the implementation partners and individuals with oversight roles in the project, in particular Government duty-bearers. However, findings and recommendations may be of interest also to other stakeholder interested in the mainstreaming of participatory forest management for biodiversity conservation in Zambia and the miombo eco-region of Central-Southern Africa.

##### Review Findings

The ECCLE project faced a slow start with a one-year delay between the time of signing the agreement in 2021 and the actual commencement of activities on the ground. From late 2022 (Project Year, PY 2), the project vigorously embarked on full-scale implementation, largely to be attributed to the efforts by a strong project team. At MTR, by 2/3 implementation point, the project had caught up on most quantitative benchmarks and was progressing well. The recommendations emphasize the need to consolidate achievements qualitatively and to find ways to optimally direct project resources to ensure long-term sustainability.

In terms of strategic relevance (criterion A), the ECCLE project is very relevant to Zambia’s national aspirations for economic development and the role the forest and natural resources sector may play in empowering local communities and reducing poverty. Demonstrating good practice and modelling gender responsive community forest management, ECCLE is contributing to the ongoing national process of policy and legal review. The project is also well aligned with UNEP and GEF strategic priorities.

The ECCLE project was designed in 2019-2020 with the support of a GEF Project Preparatory Grant under the GEF-7 cycle. With several good project design features (criterion B), the project is a significant initiative. Successful features include a collaborative implementation model based on public-private-community partnerships; integration of community forest management (CFM) into district land use planning; a socially inclusive implementation strategy attempting to address economic viability at the nexus of conservation and poverty reduction; and, the explicit intent to generate tested, proven CFM system, ready for mainstreaming and replication (after 20 years of piloting co-management in Zambia). The main weaknesses of the project design are the challenging timelines, which pose risk for overall sustainability, and the over-optimistic incremental cost reasoning scenarios. The project will not fully attain the expected results, as governance structures and profit-turning community business take long to establish, and the adoption of sustainable agriculture will take several years. The project must come to terms with the design flaws. The MTR recommends a strategic review for adjusting project targets; a timely project closure through strategic consolidation and phased exit, to allow for key processes to mature; and the development of sustainability plans to guide the post-project collaboration between Community Forest Management Groups and their private sector corporate social responsibility (CSR) partners. Fortunately, the private CSR partners are committed to the project.

In terms of effectiveness (criterion C), the ECCLE project performance is moderately satisfactory. Though delayed at start, rapid progression commenced in two components from 2023. The weak performance of component 3, sustainable agriculture, brings down the average performance. With a timely project closure through strategic consolidation and phased exit, the project is likely to consolidate output level results and enhance sustainability. At outcome and impact level, results remain limited. While outputs are relevant and realistic, they are insufficient to ensure lasting change. The devolution of CFMG governance and the development of viable livelihood income steams require more time to mature. Through strategic consolidation, prioritization of high potential interventions, and a carefully managed phased exit that progressively strengthens local capacity and partnerships, the project can enhance sustainability and improve the likelihood that community-led forest management systems endure beyond the implementation period.

In terms of adherence to policies and completeness of financial information (criterion D), the ECCLE project performance is satisfactory. Reporting on co-financing, however, was less than optimal and the project is tasked to update records. One co-financier did not report any expenditure or activity in the project area, and their removal as partner should be considered. Procedures also need tightening for partner agreements, contracts and memoranda of understanding and archiving of decision-maker meeting minutes. Due to the delays at mobilisation, timeliness was less than optimal and activity sequencing distorted, rendering the rating of efficiency unsatisfactory (criterion E).

The project monitoring and reporting (criterion F) function was found to be performing well, however with shortcomings identified, including the need for adjustment of outcome indicators; attending to missing baseline and target values; and overcoming constraints on reporting on vulnerable groups.

At MTR, the project had not yet prepared plans or strategies for exit and sustainability (criterion G). From a sustainability point of view, the design is premised on the notion that the devolution of forest management responsibilities to communities, combined with empowering them with community enterprises and household level options to increase income, will provide sufficient incentive for those communities to continue to invest in the long-term forest stewardship beyond the term of the project. For these systems to be successful several social, financial, institutional and ecological conditions need to be met. This will be difficult for the project within the available project period. The MTR recommends that the ECCLE project prepares an exit plan for the project, but also sustainability plans for how individual CFM community groups may be strengthened in readiness for their envisaged role as equal parties to negotiated post-project partnerships with Corporate Social Responsibility Partners.

Criterion H assesses other factors affecting performance and cross-cutting issues. Overall, the project has performed well in project management. Environmental safeguards and cross-cutting issues are well recognized. Appropriate gender-initiatives have been implemented at local level. Stakeholder participation and ownership are fair. After the MTR, the project will need to build stronger CFMG capacity for a post-project existence. A more gendered approach to Knowledge Management will provide appropriate guidance to the exit plan activities and gender responsive sustainability plans. Support structures will be enhanced by updating duty-bearer roles and responsibilities. The sharing of lessons learnt in readiness for mainstreaming will benefit from an adjustment to the communications strategy. A summary of the review ratings is found below in Table 1 and the full project performance rating Table 12 in Section V: Conclusions.

##### Conclusions

Overall, although much delayed in start-up, the implementation of the ECCLE project got underway briskly in 2022. The project is well managed and is progressing as per work plan. At local level, the beneficiaries, the local communities are engaged and demonstrate ownership and willingness to embrace community forestry. Substantive efforts have been made to integrate gender equality and tangible achievements are visible on the ground. At strategic level, weaknesses in project design have impeded progress and the project will need to review some of the fundamental underpinnings of CFM modelling and mainstreaming. Provided the project ensures a timely closure through strategic consolidation and phased exit, the proposed consolidation of activities, risk and strategic reviews and sustainability planning are undertaken expediently, the ECCLE project stands a fair chance to achieve a successful outcome, contribute significantly to community forestry development in Zambia and its expected long-term impact.

As a formative assessment, the MTR focus on challenges, what may be improved in project performance, tends to impact on ratings. The ECCLE overall rating at 2/3 implementation point is moderately satisfactory (Tables 1 and 12). Issues of delays and design issues (challenging timelines, overly optimistic incremental cost reasoning, and a few untenable project premises) have disproportionately weighed down the performance rating. Was focussed to be placed only at project management alone, overall performance rating would have been more favourable, a finding which in itself points to an important lesson to learn.

In terms of the strategic questions posed, the  ECCLE project presents (i) substantive evidence of growing community awareness on and interest in forest management in the project areas;  (ii) fair evidence that community forestry business and enterprise investment will contribute to improving community livelihoods, and, provided a timely project closure through strategic consolidation and phased exit is ensured, the long-term likelihood of this happening will increase substantively. The project also presents (iii) some evidence of a positive impact on household livelihoods and income in Northwestern Province. The project is doing valuable work creating awareness of and in introducing alternative production technologies for climate smart, conservation and sustainable agriculture in the project areas. It will take time for these practices to mature and become widespread.

##### Lessons Learned

The review provides a case for adhering to established evaluation procedures. Amendments to the project intervention logic, the Theory of Change and associated Results Framework and Indicators are best undertaken at project appraisal or inception, not at mid-term. Conducted at 2/3 implementation point, the review took note of the disadvantages of a poorly worded intervention logic had played out in the project: increased effort project M&E reporting and performance tracking; sub-optimally supported adaptive project and risk management; and, diverted MTR resources to looking at ‘past problems’, rather than examining ways of providing constructive future formative assessment. The delayed timing of the mid-term review also challenged its utility. With only one year remaining of the project, the generation of meaningful recommendations to help the project make changes, consolidate achievements became difficult, straining the project further.

##### Recommendations

The Mid-Term review process yielded normative observations, mitigation measures and technical recommendations, which were discussed with the project team, presented to the stakeholders as preliminary findings, and deliberated as part of the first draft review and subsequent validation process. The remaining interventions are summarized as fifteen key management recommendations. As part of the strategic review, the project will select the most feasible ones for implementation during the remaining project period.

Substantive concerns and recommendations for further action to Senior Management and Project Management include major recommendations for to ensure a timely closure through strategic consolidation and a phased exit approach (Recommendation # 1); Strengthened Project Governance (including IA and EA) (# 2); a Strategic Review and Course Correction (# 3). Other project management related recommendations relate to the revised Theory of Change and Results Framework (# 4); addressing issues of co-Financing # 5); evolving Stakeholder Roles and Responsibilities to meet exit requirements (# 11); and Setting Meeting Records and Archives straight (#14).

Project design recommendations include: (# 4) Adoption of the Revised Theory of Change and Revisions to the Results Framework and Outcome Indicators; (# 13) Drafting an Exit Plan and Sustainability Strategies at project and beneficiary level (one for each CFMG group); and (# 15) Issues for the Consideration of the Terminal Evaluation. The Lessons Learned also speak to the importance to appraise project design early on (Lessons Learned # 1).

Project implementation recommendations include:( # 6-9) Consolidation and Re-focus of the work under the three Components; (# 10) Strengthening Sustainability at Local Level; and (# 12) ways to further boost Gender-responsiveness.

A summary of ECCLE Project Performance Rating is found below. For the full table see Section VI, Conclusions.

Table 1. Summary of ECCLE project performance rating

| Criterion | Summary Assessment | Rating |
| --- | --- | --- |
| A: Strategic Relevance | Aligned to UNEP and GEF strategic priorities. Very relevant to national needs, with the potential to support policy renewal. | S |
| B: Quality of Project Design | Several good design features, regrettably undermined by challenging timelines and a few untenable project premises | MS |
| C: Effectiveness | Due to delayed start, project now at mid-point. | MU |
| D: Financial Management | Adherence to policies and completeness of financial information satisfactory | S |
| E: Efficiency | Cost-effectiveness not rated. Rating of timeliness/delays, their impact on at least one group of stakeholders, and sequencing of project activities and events unsatisfactory. | U |
| F: Monitoring & Reporting | The project monitoring and reporting system is performing well, with some shortcomings identified for correction. | S |
| G: Exit and Sustainability | The project has initiated the process of drafting a sustainability strategy and exit plan. It is recommended that an exit plan is prepared for the project, but that sustainability plans are prepared also for each CFMG and implementation partner. This is likely to happen, and the changes that socio-political, financial and institutional issues are addressed are good. | MS |
| H: Other Factors | The overall performance of the project is good. | S |
| Overall Project Rating at 2/3 implementation point | Calculated as a simple average of the rating for each criterion (A-H) = Moderately Satisfactory | MS |

## I: Project Overview

The Ecosystem Conservation and Community Livelihood Enhancement in Northwestern Zambia (ECCLE) is a five-year project under the GEF-7 cycle. It is addressing the barriers to sustainable management of forests and other natural resources and the barriers to the development of sustainable agriculture in line with the priorities of the GEF-7 Impact Program (IP) Sustainable Forest Management (SFM) in Drylands Landscapes. The start date of the project is 20 August 2021. The planned technical completion date is 31 August 2026.

In line with the UNEP Evaluation Policy, a Mid-Term Review is undertaken approximately half-way through project implementation span to analyse whether the project is on-track, what problems or challenges the project is encountering, and what corrective actions are required. This review will comprise a technical and financial review of the Ecosystem Conservation and Community Livelihood Enhancement in Northwestern Zambia (ECCLE) project performance from the effective start date 13 September 2021 until 31st December 2024. A key aim of the Mid-Term Review is to encourage reflection and learning by UNEP staff, the implementing partners and key project stakeholders. The Review Consultant should consider how reflection and learning can be promoted, both through the review process and in the communication of review findings and key lessons.

The review is commissioned by the UNEP / Ecosystems Division / GEF Biodiversity and Land Degradation unit. The Review Consultant reports to the GEF Task Manager, under the overall guidance of the Portfolio Manager.

#### Institutional Context and Implementation Structure

The Implementing Agency (IA) is the UNEP Ecosystems Division. The Executing Agency (EA) is the Nature Conservancy (TNC) working together with the Forestry Department of the Ministry of Green Economy and Environment in Zambia. The project implementation structure is shown in Figure 2 below.

Figure 2. ECCLE Project Implementation Structure

The project aims at developing and strengthening partnerships with Government of Zambia, local communities, private sector actors, and non-governmental organizations to attain long lasting conservation outcomes. Against this background, The Nature Conservancy has adopted a consortium-like implementation approach and partnered with three local conservation organizations to support implementation of the project activities; West Lunga Conservation Project (WLCP) in the Ntambu project area; Kasempa Conservation Foundation (KCF) in Kelongwa Kamanana; and Trident Foundation (TFL) in Kalumbila. TNC has further engaged and signed contracts with several service providers.

Day-to-day project management is carried out by the Project Implementation Unit (PIU) in collaboration with the Forestry Department, at three geographical locations: (i) The TNC Lusaka office in Kabulonga hosts the Project Manager, M&E Officer and Finance Officer, who draw on TNC administrative and logistical support. (ii) The National Project Coordinator operates from the Forestry Department Headquarters at Kwacha House Annex in the city center. (iii) The Technical Support Unit, hosting the two technical advisers, was originally established in Kalumbila, but later moved to Forestry Department Offices in Solwezi, Northwestern Province. Recently, a Provincial Focal Point in Solwezi has been nominated to the project.

##### Oversight and Supervision: Project Steering Committee

A Project Steering Committee (PSC) was established during the second year of project implementation (2022). In its second meeting, the PSC revised its charter and formed a joint PSC for two UNEP GEF funded projects. The two projects are located at far ends of Zambia: ECCLE in the Northwest, and the Eastern Province Jurisdictional Sustainable Landscape Programme (EP-JSLP) in the East.

In its 2023 charter, the PSC revised and adopted the following membership: the Ministry of Environment and Green Economy, Ministry of Agriculture, Ministry of Tourism, Ministry of Local Government and Rural Development, Ministry of Water and Sanitation, Ministry Fisheries and Livestock, Ministry of Lands and Natural Resources, Ministry of Finance and National Planning, Zambia Environmental Management Agency and the Provincial Administration of Northwestern, Eastern and Western Provinces (all represented at Permanent Secretary level). Further, key implementation partners of the two projects attend meetings:  UNEP; The Nature Conservancy; WWF and FAO.  The Department of Environmental Management represents the GEF Operational Focal Point and the Department of Forestry acts as Secretariat to the PSC.

The PSC provides overall guidance and strategic direction and oversight and approves all final outputs and deliverables of the project. In addition, the PSC is responsible for (i) evaluation and monitoring project outputs and achievements; (ii) supporting changes to the work plan or budget, and (iii) ensuring that the project remains on target with respect to its outputs. Where necessary, the PSC supports the setting of new targets in coordination with the PIU/FD/Executing Agency and approval from the Implementing Agency. The PSC is chaired by the Permanent Secretary, Ministry of Environment and Green Economy.

##### Technical Support and Supervision: Project Technical Committee

The Project further established a Project Technical Committee (PTC) specifically for the ECCLE project. The PTC comprises technical specialists of Government agencies, the private sector and NGOs as relevant. Members include the Department of Forestry; Department of National Parks and Wildlife; Department of Agriculture; Department of Climate Change; Zambia Environmental Management Agency and Department of Environment Management. The corporate private sector implementation partners are members: West Lunga Conservation Project; Kasempa Conservation Foundation and Trident Foundation. The PTC is chaired by the Director Forestry Department.

The role and responsibilities of the PTC are: (i) Providing primary oversight and regular technical oversight of the Project manager and the PIU and technical advice to the implementation of the project; (ii) Reporting to the institutions and organisations that they represent with regard to the project activities being carried out; (iii) Providing advice and technical guidance to the PIU; and (iv) Assisting with planning and participating in training/workshop activities. The Terms of Reference of the PTC were substantively amended following the merger of the two Project Steering Committees, an on-going process whose implications are discussed in the review (Section IV, Criterion H, Annex 20).

##### Technical Implementation Support and Supervision: The District Technical Team

At district level, technical teams were set up at the start of the project. The teams consist of Government staff at district level: the Department of Forestry, Department of Agriculture, Department of Fisheries and Livestock, Department of National Parks and Wildlife, largely corresponding to the natural resources management sub-committee of the District Development Coordination Committee (DDCC), with the addition of the planning officer from the Local Councils. The district technical team staff are responsible for providing technical guidance for project activity implementation in their specialised fields to the local conservation implementing partners. They are also responsible for preparing reports at district level and submitting to the Project Technical Support Unit (TSU) and the DDCC. The district technical teams work in collaboration with staff from the TSU supporting the Implementation Partners and other Sub-awardees, Service-providers and Consultants engaged by the Project with the technical implementation of activities.

##### The Project Implementing Partners

At community level the key Implementing Partners are the Community Forest Management Groups together with the three key Implementation Partners, from among local conservation organisations: the West Lunga Conservation Project (WLCP), Kasempa Conservation Foundation (KCF), Trident Foundation Limited (TFL). Two of the partners, WLCP and TFL, bring in co-funding funding from First Quantum Minerals, whereas KCF relies entirely on the project budget for implementation.

The key Implementing Partners are supported by a conglomerate of private sector operators: Miombo Ecosystem Enterprise Limited, Impulse Africa, and a number of market off-takers with whom The Nature Conservancy on behalf of the project has signed agreements, contracts and/or Memoranda of Understanding (MoUs) each to support distinct aspects of implementation. District and provincial level offices facilitate and backstop implementation (see paragraph 34 above).

#### Project Problem

The key threats to the rich biodiversity in the Northwestern Zambia include loss of forests and other natural resources and land degradation due to expansion of agriculture, unsustainable charcoal production, illegal logging, illegal mining, overfishing and uncontrolled bushfires. The root causes of these threats are poverty, food insecurity and a lack of alternative income opportunities, coupled with a high market demand for such products and inadequate benefits from biodiversity conservation to local communities.

The ECCLE project addresses the barriers to sustainable land management and to biodiversity conservation at three sites in three districts in the Northwestern Province (NWP) of Zambia (Map 1). The project rationale is based on the assumption that (i) supporting communities strengthen systems for community-driven management of forests and other natural resources, (ii) providing support towards development of productive nature-based investments for sustained self-financing to conservation and enterprise development and (iii) supporting the adoption of sustainable agriculture practices and technologies to improve agriculture production and productivity while reducing the deforestation footprint of agriculture, would result in sustainable resource management and consequently enhanced biodiversity and improved livelihoods (reduced poverty).

This GEF-7 project will provide global environmental benefits in terms of the Biodiversity Focal Area BD under Objective 1 of the GEF and BD strategy: Focal Area Objective 1 - Mainstream biodiversity across sectors as well as within production landscapes and seascapes. It will also contribute to Sustainable Development Goals (SDGs): SDG 5 (Gender Equality); SDG 10 (Reduced Inequalities); SDG 13 (Climate Action); and SDG 15 (Life on Land).

Figure 1: Location of Zambia’s Northwestern Province and the three ECCLE project areas

#### Project Results Framework

The Results Framework (RF), as presented in the Project Document, supported implementation during the first four project years and provides the baseline at Mid-Term Review (Annex 13). The MTR proposes changes to the Theory of Change (ToC), outputs and outcomes, which will affect the Results Framework.  A recommendation to amend and develop the RF presented below to improve project tracking of progress.  (Section III; Lesson Learned #1; Recommendation 4).

#### Project Objective and Components

The ECCLE project has a two-pronged approach, aiming at building local sustainable forest management at the project sites, and building preparedness for mainstreaming at a greater geographical scale:

- The objective of the ECCLE project is strengthened community-based sustainable management of forest landscapes and improved livelihood opportunities for targeted forest-dependent rural communities in Zambia's Northwestern Province. (ProDoc, p. 62)

- The strategic objective of the project is enhanced sustainable land management and biodiversity conservation in Northwestern Province through the development of tested, proven systems of community management of forests and natural resources ready for mainstreaming. (ProDoc, p. 62)

Working with Government, other collaborating public and private stakeholders in the landscape and forest-dependent communities themselves, the Project facilitates the development and strengthening of community-based natural resource tenure, governance, and management systems, stimulating the establishment of forest-based enterprise models and supports sustainable agricultural systems on the forest margins under three thematic areas:

Component 1: Strengthening the enabling regulatory, planning and governance frameworks for community-based, sustainable forest management; this component supports communities with awareness raising on community forest management, undertaking assessments of forest conditions, determining the potential socio-economic importance of forest products, delineation of forests for community management, grouping of villages into management units of optimum geographic and economic scale, development of community forest management plans, development of plans for equitable sharing of costs and benefits and application of the Community Forest Management Groups for legal recognition and subsequent transfer of user rights by government.

Component 2: Promoting the conservation and sustainable use of natural resources in community-managed forests. Under this component the project assists the communities to develop business plans and investment plans and provides catalytic funding for productive investments and for the interim hiring of professional staff for CFMGs with a view to developing self-financing forest/natural resource management capacity and ensure enterprise development and conservation sustainability.

Component 3: Improved productivity and climate resilience from sustainable agricultural practices. This component focuses on the promotion of smallholder agricultural technologies and practices by small-scale crop and small livestock farmers living in the project target areas that contribute to the maintenance and enhancement of productivity on existing agricultural lands, thus reducing the need for farmers to extend their agricultural footprint into forests and other natural ecosystems because of declining productivity on their traditional lands. The project places a special focus on the promotion of technologies and practices that both maintain and enhance ecosystem health and increase the resilience of smallholder agricultural communities against climate change.

#### Change in Project Design

From ECCLE project start-up in 2021, until the mid-term review point December 2024, there were no major changes to project design, Theory of Change, outputs or outcomes, results framework, etc.  During the same period, however, minor changes in implementation arrangements, activities and in project sites have taken place. They have been formally approved by the Project Steering Committee, endorsed by the Implementing Agency, and reported in the GEF Project Implementation Review (PIR), as relevant. Such changes include the amended composition of the Project Steering Committee; the geographical modification of the project site in Kalumbila; the expansion of the Community Forest Management (CFMA) area in Ntambu; and budget revisions.

In late 2024, a substantive revision to the budget presented by the project to the Steering Committee and the Implementation Agency. The changes proposed by the MTR to the wording of the rToC, outputs and outcomes will need be adopted by the Project Governance bodies and the Implementation Agency as soon as possible to enable the project prepare exit and sustainability plans (recommendation 4).

#### Stakeholders

At design stage, stakeholder mapping insufficiently differentiated gender and vulnerability dimensions, resulting in uneven engagement of women, youth, and other marginalized groups during early implementation (ProDoc p.45). While women’s participation has been relatively strong at community level—through CFMG sub-committees, women forest guards, beekeeping and NTFP activities—their engagement remains largely confined to operational roles, with limited representation in governance structures, enterprise leadership, and market-facing decision-making. Youth engagement has similarly focused on labour-intensive activities such as forest patrols, nurseries, and CSA demonstrations, with few structured pathways for leadership development, skills certification, or entrepreneurship. Marginalized households, including the very poor, female-headed households, and forest-dependent safety-net users, are not yet systematically identified or tracked as distinct stakeholder groups, constraining the project’s ability to assess differentiated benefits, risks, and inclusion outcomes. As CFMG forest commodity businesses mature, the absence of formal engagement with business associations has clear gender implications, as women-led micro-enterprises and informal producer groups risk exclusion from emerging value chains without deliberate linkages, capacity-building, and representation mechanisms. Limited engagement with conservation organisations beyond implementation partners has reduced access to specialised gender, social inclusion, and rights-based expertise needed to mitigate elite capture and strengthen equitable benefit-sharing, while the envisaged role of academic institutions in supporting the self-financing CFM model has not materialised, limiting applied research on gender-differentiated outcomes, youth skills development, and inclusive governance to inform replication. In parallel, the non-materialisation of other donors and private-sector investment brokers, including development banks linked to the Forest Investment Programme, has narrowed financing and scaling pathways, disproportionately affecting women- and youth-led enterprises during the transition to sustainability. Annex 15 provides an updated stakeholder power–interest analysis and underscores the need to identify primary stakeholders for exit and sustainability, including women leaders within CFMGs, youth enterprise champions, and local gender advocates. Accordingly, the MTR recommends recalibrating stakeholder engagement to (i) integrate women, youth, and marginalized groups into governance structures with real decision-making authority; (ii) prioritise engagement with business associations, conservation NGOs, and academia to support inclusive value chains and evidence-based mainstreaming; and (iii) embed gender- and vulnerability-disaggregated tracking within M&E and exit planning, directly underpinning Recommendations 10 and 11.

#### External challenges

The project encountered several external challenges during the first four years.

- Zambia’s Presidential Elections in 2021 resulted in a change of political leadership, a restructuring of Government Ministries and a subsequent change of management in the Forestry Department.

- The envisaged National Forest Investment Plan (FIP) for Zambia did not attract the level of investment as expected (ProDoc p. 81), impacting on the sustainability options for the ECCLE project.

- Zambia experienced its worst drought in over two decades, beginning in January 2024 and continuing into early 2025. The drought was primarily driven by El Niño-induced irregular rainfall patterns, which were further exacerbated by climate change. The 2023/24 agricultural season was badly affected.

#### Project parameters for the review

The ECCLE project key parameters are shown in Table 2.

Table 2. ECCLE Project review parameters

| PIF Approval Date | 14-05-2019 |
| --- | --- |
| Preparatory Project Grant | 2019-2020 |
| CEO Endorsement Date | 01-06-2021 |
| UNEP Project Approval Date | 19-08-2021 |
| Project Cooperation Agreement Date | 20-08-2021 |
| First GEF Fund Disbursement Date | 07-09-2021 |
| Planned Start Date | 20-08-2021 |
| Actual Start Date | 13-09-2021 |
| Date of Inception Workshop | 29-03-2022 |
| Expected Date of Mid-Term Review | 31-08-2024 |
| Actual Date of Mid-Term Review | 01-04 to 27-09-2025 |
| Expected Terminal Evaluation Date | 28-08-2027 |
| Planned Closing Date | 31-08-2026 |
| GEF Financing Amount | 5,338,585 USD |
| Co-financing Amount | 20,380,000 USD |
| Total Budget | 25,538,585 USD |
| Expenditure at 30-09-3025 (GEF, Annex 5) | 3,893,723.50 USD (73%) |
| Expenditure at 30-06-2025 (co-financing, Annex 5) | 53,920,170 USD (265%) |

#### Project Finance

The total project financing as per the Project Document was 25,718,585 USD, of which GEF funding was 5,338,585 USD and co-financing 20,380,000 USD. By end March 2025, the project had spent, 3,893,723 USD (73% of total the GEF funding, see Annex 5).  By June 2024, co-financing expenditure was reported at 53,920,170,333. A specification of excess contribution was requested but not obtained. Annex 5 shows the project budget, project expenditures by component, and co-financing.

## II: Review Methods

This Mid-Term Review has been conducted in accordance with the UNEP Evaluation Methodology, the UNEP Programme and Project Management Manual and GEF requirements. The aim is to analyse whether the ECCLE project is on-track, what problems or challenges the project is encountering, and what corrective actions are required. The Terms of Reference and the UNEP Evaluation office set of methodological tools and templates provided a comprehensive framework for the process. Accordingly, the project was reviewed against eight key criteria (see Section IV, Review Findings).  Additional key strategic questions required by UNEP are addressed in the conclusions (see Section V).

The Review was carried out by one international consultant reviewer under the guidance of the Implementing Agency UNEP and working closely with the Project Team. The review was carried between April and September 2025, remotely, and via mission travel to Zambia. The review consisted of four phases: (i) an inception; (ii) the main review; (iii) the findings analysis and (i) MTR report development.

During the inception phase the project design quality was reviewed, a stakeholder analysis undertaken, the Theory of Change reconstructed in consultation with the project team, the evaluation matrix developed, interview questions, sampling frames and potential respondents identified. An Inception Report was submitted in May 2025, and the final 2nd revised version approved 10 July 2025.

The main review phase employed a standard evaluation design utilizing the following methods: (i) desk review of available project documentation, (ii) data collection in the field (interviews and site visits), (iii) consultative meetings with stakeholders, and (iv) in-depth desk analysis. Close communication was maintained throughout the process, with the Project Manager (PM) and her team.

Information sources used. The project management unit (PMU) granted access to project documents through a shared drive, and in response to requests.  The materials reviewed included project preparation and design documents; the Project Document (ProDoc) and appendices; the Theory of Change and Results Framework; implementation strategies and work plans; commissioned studies (Forest Assessment, Gender Analysis, Knowledge Management); Bi-Annual and Annual reports, PIR reports; Project Steering Committee (PSC) and Project Technical Committee (PTC) meeting minutes; and other data requested from the project, including financial reports, progress tracking tables, copies of Terms of Reference and contracts. The UNEP team availed key contractual and financial documents. A list of materials is provided in Annex 3. Additional planning and reference documents were obtained from the internet.

Mission travel took place between 3rd and 26th June 2025, with one week spent in Lusaka and two weeks in Northwestern Province (NWP). The purpose of mission travel was to engage with the executing agency, the project management and technical support units, and to meet with project implementation partners, stakeholders and beneficiaries. The field visit included engagements in the provincial capital of Solwezi, and the district capitals of Kasempa and Kalumbila. During Mission Travel, the consultant worked closely with the Provincial Focal Point, who also provided translation support. Implementation partners readily availed other members of staff to support the visits and meetings, though at times they were asked to excuse themselves to allow respondents liberty of reply. Site observation and focal group discussions with the CFM communities were carried out in two project sites: Kelongwa Kamanana (Kasempa District) and Ntambu (Mwinilunga District). The Mwinilunga District Team was interviewed by telephone. The review itinerary for mission travel is found in Annex 4.

For interviews and focal group meetings, tailored checklists and semi-structured interview questionnaires were prepared. Interviews were conducted in-person, on-line and by e-questionnaire, individually and in group with actors ranging from project management, finance and administration to technical support, Forestry Department, Government duty bearers, implementation partners, service providers, CFM committees, resource user and interest groups (e.g. farmers, beekeepers, forest guards and gender champions. Purposeful sampling was undertaken, within the available time window, focussing on ensuring a representative sample of respondents carrying different roles and responsibilities, and taking into consideration triangulation requirements. Key informant interviews were conducted with implementation partners and strategic stakeholders. Among beneficiaries, focal group discussions were given preference to encourage learning and the exchange of views. Field and district level meetings attendance rates were very good. The review met with representatives from all stakeholder groupings (100%), through sampling approximately 52% of potential respondents. In total, the reviewer met with more than 130+ people across 34 stakeholder categories, representing implementation partners, private sector, government, civil society and beneficiaries. An updated list of project stakeholders is found in Annex 15, and the list of persons met is found in Annex 2.

Efforts were made to ensure that the voice of women was heard in this explicitly gender-responsive project. The gender ratio among respondents reflected the prevailing situation on the ground, ranging from a relatively balanced representation among implementation partners (M60:F40), to a high male-bias among government stakeholders in the natural resources sector (M90:F10), to an encouraging female representation in local communities (M75:F25). To amplify, gender advocates at provincial, district and local level (gender champions) were targeted for in-depth interviews.

The UNEP methodology encourages reflection and learning. Accordingly, the review consultant worked closely with the ECCLE project team throughout the assignment. During the mission, the consultant met several times with the project team and Forestry Department staff. The Inception Report findings were presented to key stakeholders in Lusaka and Solwezi (see sample communication tool in Annex 7). Members of the Project Technical Committee were consulted in Solwezi. A field debriefing note, a PowerPoint presentation was presented to key stakeholders on 4th July 2025. The field itinerary is attached as Annex 4.

Analysis: The Project Document, implementation strategies, work plans and project reports were used as the skeleton for the analysis. The status of activities and outputs were assessed against implementation strategies, bi-annual and annual (PIR) reports while challenges and successes were verified in discussion with stakeholders and implementors. A consideration for wise use of time and resources, in combination with the findings from the inception phase, favoured in-depth review of the project design and intervention logic (Section III); and giving special attention to the criteria  of Quality and Revision of project design (B); Effectiveness (C); Exit strategy and sustainability (G); and selected factors affecting project performance and cross cutting issues (H) (See Inception Report and Section IV). The comprehensive nature of the UNEP matrix evaluation tool and wide-ranging set of evaluation questions necessitated the generation of several interim products to underpin the analysis, such as tables and diagrams, some of which are presented below and in the annexes.  Key methods for analysis included scoring, matrix ranking and comparative analysis. Validation included triangulation of data, events and cross-referencing with comparative studies. A preferential bias was also adopted towards project level (as compared to programmatic level) analysis; and observations in support of project sustainability. Information generated from document review and key informant interviews was cross-referenced with data generated during the field visits. Key informant interviews were compared with data from focal group discussions with project staff and stakeholders.

Reporting on the mid-term review findings took place in September 2025. A first version of the mid-term review report was circulated in the project by mid-September for stakeholder review. A full draft report was submitted to Zambian stakeholders for review 18th September; to UNEP on the 25th of September; and a validation workshop was held 30th September 2025. Stakeholder feedback has been incorporated in the document, specified in Annex 1. The process of clarification continued until December.

Limitations: Timing of the MTR review. The Mid-Term Review was commissioned to start in April 2025, three years and 7 months after project start, effectively at 2/3 implementation point. With only one year of project time remaining at the end of the MTR period, the Consultant encountered challenges in translating findings into appropriate recommendations. Even assuming additional time for consolidation and a phased transition, formulating practical measures to strengthen achievements proved challenging. Mid-Term Reviews are best executed at the designated time, to gain optimal benefit from the findings (Lesson Learned # 2).

Revising the ToC. Revision of the wording of the Theory of Change (ToC) and associated drivers and assumptions in keeping with UNEP definitions (ToRs, p. 34) was done during the Inception Phase (cf. Section III and Inception Report). The modifications were discussed with stakeholders during the main review and the revised version is presented for adoption by Project Management (Recommendation 4). Whilst a relevant exercise, the timing was awkward. The revision was perceived of by many as a time-consuming, less productive exercise, untimely in view of the short remaining implementation period. The review consultant agrees. Undertaken earlier in the project cycle, as part of project appraisal or during start-up and inception, ToC revision and other amendments would have guided the project implementation team more appropriately. This also applies to Result Framework indicators. (Lesson Learned # 1).

Data availability and timeliness at project level also impacted the MTR in several ways: (i) The performance tracking tables, developed in full compliance with RF requirements, only partially supports the MTR requirements.  (ii) Delays in the execution of key consultancies compromised the generation of baseline data rendering assessment of progress towards outcomes difficult. For example, the cycle for knowledge management reviews did not support the MTR process as envisaged. (iii) Mini-surveys intended to capture the satisfaction rates of vulnerable groups have not been undertaken as envisaged. These issues are further discussed in Section IV, criterion F and in recommendations 4 and 14. This finding underscores the need for an early review of the ToC, which would ensure that the project team is fully aware of the data needed to comply with the requirements of the mid-term and the UNEP review criteria matrix (Lesson learned # 1)

Availability of duty bearers. Due to the high number of stakeholders and beneficiaries, a purposeful stratified sampling frame was proposed during the MTR Inception phase to derive at a manageable, yet representative sample of respondents, in particular duty bearers (See Inception Report, Annex 15). Regrettably, difficulties were encountered in engaging some key informants, in particular duty bearers, due to circumstances beyond the control of the parties involved, e.g. conflicting government programmes.  As a plan B, where key informants were not available this was resolved by meeting a former office holder (i.e. previous FD PFO – Provincial Forestry Officer; retired GEF OFP - Operational Focal Point) or the next senior officer by rank (i.e. MLGRD); or administering an e-questionnaire (i.e. UNEP). Generally, the response rate to e-questionnaires was generally below par and is not recommended.

Generating a voice for community members and vulnerable groups. The original ProDoc stakeholder engagement plan is weak in its analysis of the beneficiaries, local communities, short of information about social cohesion, internal organisation and community dynamics, beyond a very generic categorization of ‘vulnerable groups and a listing of typically occurring institutions. Some project mobilisation activities partly addressed this shortcoming (e.g. gender action plan and socio-economic surveys), but undoubtedly, the project team has been at a disadvantage. The MTR made an effort to distinguish between the different interest groupings in relation to the project – i.e. direct and indirect beneficiaries; forest-dependent households vs. households oriented towards other livelihoods (see Inception Report and Annex 15). Within available time, resources and geographical set-up, it was deemed not possible for the MTR Review mission to configure opportunities to discuss with indirect beneficiaries, household engaged in other livelihoods, vulnerable groups and/or very poor households reliant on forests as a safety net. It is recommended that the ECCLE M&E Unit, as part of project progress tracking, makes an extra effort to capture the voice of the vulnerable, e.g. undertaking beneficiary satisfaction surveys that are disaggregated to cater for a differentiated sampling of local communities (recommendations 12 & 14).

Harmonising review processes. The UNEP MTR review cycle differs from prevailing consultancy praxis in Zambia. Report review and validation practices differ substantively, which was pointed out as a negative feature by attendants at the Validation Meeting held 30th September 2025 (Annex 1). Despite the consultant’s best efforts to harmonise processes, the outcome was less than optimal at times. The Implementation Agency and Executing Agency are advised to take note of this for future reference to encourage more effective shared learning and reflection.

Ethics and human rights: Throughout this review process and in the compilation of the Final Review Report efforts have been made to represent the views of both mainstream and more marginalised groups. Data was collected with respect for ethics and human rights issues. All pictures were taken, and other information gathered after prior informed consent from people, all discussions remained anonymous, and all information was collected according to the UN Standards of Conduct.

## III: Theory of Change

The ECCLE project results were reformulated during the Inception Phase, as the original ToC as presented in the Project Documents does not follow UNEP’s definitions of different results levels. (See Inception Report). The proposed changes to the project’s results hierarchy are detailed in Annex 16, comparing the results as stated in the ProDoc logical framework and TOC with the revisions as formulated in the TOC at Review. In relation to GEF requirements, the proposed current adjustments are ‘minor’ (non-substantive) and warrant an approval by the Project Steering Committee and Implementation Agency, as well as a record in relevant project documentation.

The rewording of project assumptions and drivers brings clarity to the intervention logic, stakeholder roles and responsibilities, risk mitigation and the formulation of a sustainable exit strategy.  Past project design features, such as weak formulation of assumptions and drivers in combination with inadequate consideration of local stakeholder capacity, resulted in a situation whereby the ECCLE project team become unnecessarily burdened with activities outside their responsibility. (Recommendation 11).

The process of ToC reconstruction was consultative and collaborative. At inception, the revised TOC at Review Inception was presented for discussion with the project team twice during mission travel (Inception meeting, internal meeting with ECCLE PIU/TSU team).  Based on further review of the project documentation and subsequent assessment of Criterion C, a second version is presented to project key implementation stakeholders for review. The third version, as amended in September 2025, is presented in Figure 3, Table 3 and Annex 16. (Recommendation 4).

The ECCLE project document contains a clear intent to develop a gendered approach to participatory forestry in Zambia, e.g. all outcomes emphasize the significance of gender equality. The ProDoc terminology is variable – the terms gender equality, gender sensitive and gender responsive are used interchangeably. In the revised Theory of Change, the term gender-responsive is preferred, used to reflect a pro-active approach to promoting gendered project implementation, being sensitive to and striving towards gender equality, in bringing a strong gender dimension to the development of community forestry models, strategies and programs.

In accordance with UNEP recommendations, the assumptions/drivers relating to human rights and gender equality were amended during the Inception Phase. The ToC narrative has been only mildly amended in order not to create a situation of “moving goal posts”. However, it is clear that a stronger gender-responsive approach at design stage (original ToC) would have resulted in more attuned gender-responsive CFM models. A related course correction is found in Recommendation 12.

As with the Theory of Change and Intervention Logic, the ECCLE Results Framework has not been updated, since CEO endorsement (June 2021). While output indicators were adjusted by the project in 2022, the outcome indicators remain unchanged. Several indicators are inadequately worded (Annex 12) and effectively restrict progress tracking and results-based management (See Criterion F). The MTR recommends that a revision of the Results Framework indicators is undertaken in conjunction with adoption of the revised ToC (Recommendation 4).

The revised Theory of Change is depicted below in Figure 3, with accompanying assumptions and drivers in Table 3. The original versions, including the intervention logic narrative, are found in Annexes 12, 13 and 14.

Figure 3.  ECCLE Theory of Change at Review (rToC), September 2025

Table 3. ECCLE Project Assumptions and drivers, TOC at Review (September 2025)

Numbering – please refer to rToC in Figure 3.

| ALL | Theory of Change at Review (rToC) statements regarding intervention and action are gender sensitive / responsive, or strive towards gender equality, even when not explicitly so stated. The community approach and engagement is cognizant of the different needs of men, women, youth, marginalized groups and other interest groups, even when not explicitly so stated |
| --- | --- |
| ALL | Increasing equality across all groups is part of the UNEP mandate on human rights. |

Output level:   Pathway 1: Strengthening the enabling regulatory and planning frameworks for community-based sustainable forest management

| 1 | Communities (consisting of men, women, youth and marginalized groups) are interested in community forest management (CFM) and participate in planning processes cognizant of community members differentiated and at times conflicting interests (assumption / driver) Traditional authorities endorse and support community forestry (assumption) District actors are supported by their provincial and national counterparts, to harmonize CFM and other natural resource management (wildlife, fisheries) in district land use plans (driver / assumption) Revised district plans will be recognized, approved and endorsed by Ministry of Local Government and Rural Development as well as Physical Planning within the project life span (assumption) |
| --- | --- |
| 2 | Communities and traditional authorities - as above With external support, the communities are able to develop gender-responsive structures at an appropriate economic scale and to agree on rules for costs and benefit sharing (driver) External support will be made available, post-project, for long enough a time for community management structures to mature (assumption). |
| 3 | Knowledge management effectively supports the development and testing of CFM models and systems to facilitate learning, replication and upscaling (driver) Gender-responsive guidelines for sustainable forest management at Community Forestry Management Area (CFMA) for key value chains are developed (e.g. silviculture for honey production) and tested during the project life span (driver) Lessons learnt from ECCLE are peer reviewed (CFM practitioners and communities) across Zambia for testing and learning lessons (driver / assumption) |
| 4 | Gender-responsive project guidelines, schedules, training materials and other support documentation developed for district and CFMA level will provide practical guidance for cross-sectoral, harmonized implementation of forest and natural resources management (FNRM) policies, legislation and regulation across sectors Gender-responsive auxiliary guidelines, schedules, training materials and other support documentation developed by the project will be adopted by relevant Government departments at national level in support of post-project CFM mainstreaming nationwide (assumption) |

Pathway 2: Improved management of forest resources for gender equality and enhanced welfare and livelihoods

| 5 | Investments in skills, training and capacity-building will strengthen Community Forest Management Group (CFMG) governance and management systems (driver); Investments in capacitating the CFMG to train and deploy technical staff to provide stewardship to forest and other natural resources; and to train and deploy business staff to manage sustainable community enterprise (driver); Stewards of the forest resources (forest guards, honorary forest officers) are suitably motivated (assumption), incentivized and supervised (driver); CFMGs will put in place gender-responsive by-laws, rules, regulations and sanctions that all community members accept as binding (driver / assumption). |
| --- | --- |
| 6 | Gender-responsive Business plans are based on sound, long-term determination of forest products, their market access, profitability, availability of investment and staff (assumption) Gender responsive strategies and pathways are identified to allow women equal access to benefit from CFM related business (driver) Seed money for nature-based enterprise will be made available by project (driver) and private sector partners (assumption) Private sector will come forth to build long-term partnerships with communities and CFMGs (e.g. carbon trading) (assumption) CFM revenue will be adequate to cover forest management costs, business capitalization and operational costs, as well as providing tangible benefits to community members (driver / assumption) Communities and CFMGs will develop commitment to long-term sustainable production, avoiding short-term over-harvesting to maximize revenue, threatening sustainability (assumption) Sustainability challenges and risks are effectively overcome and risks mitigated throughout the project life span and beyond by developing private-community partnerships (driver / assumption) |

Pathway 3: Enhancing the sustainability and productivity of agricultural practices on the lands zoned for agriculture.

| 7 | Attractive, varied sustainable, climate smart, agricultural technologies and practices (CSA) suitable to the project area are available and profitable to the farmers, (assumption) Appropriate CSA technologies suitable to the project area are tested and adapted to beneficiary use in zones adjacent to CFM forests, taking into consideration population growth and the future need for agricultural expansion (driver) No expansion of agriculture into protected areas will occur (assumption) and, if it does, CFMGs together with government and other stakeholders will find the means to find appropriate solutions (assumption/driver) Adequate CSA capacities built among key stakeholders to avail CFM communities differentiated access (men, women, youth) to reliable CSA technologies that are profitable and tested (driver) Access to CSA market input services (inputs, extension) developed during the project life span (driver / assumption) |
| --- | --- |
| 8 | Markets for CSA products emerge during the project life span (driver / assumption) Private sector partners committed to the principles of appropriate sustainable, climate smart, agricultural technologies and practices (CSA) (assumption) Private sector partners are able to sustain services to CFMGs and CBEs beyond the project life-span (assumption) |

Outcome level:

| 9 | Self-financing CFM models can be developed, tested and proven during the project lifespan (driver) Communities are committed to gender-responsive CFM, accountability, transparency and governance, and agree to equitable sharing of benefits (driver / assumption) Sustainable forest management technologies (i.e. silviculture) are identified, tested and adopted (driver) Local government commit support to CFM development and the mainstreaming CFM plans into district planning (driver) Knowledge management systems effectively support the development of viable models and proven systems (driver) Forestry Department actively supports the development of module and tools that support a legal review within the life span of the project (driver / assumption) |
| --- | --- |
| 10 | Self-financing CFM models – as above Business and enterprises developed are profitable, capable of generating a surplus big enough to pay for (i) the cost of managing forests sustainably, (ii) business capitalization and operational costs, as well as (iii) providing tangible benefits to community members (driver / assumption) Communities choose to, and are able to organize at a large enough economic / geographic scale (driver / assumption) Equitable, fair and inclusive benefit sharing mechanisms are developed and respected by the communities (driver) Elite capture is avoided and/or controlled through CFM structures (driver) |
| 11 | Barriers to the adoption of sustainable agricultural technologies and practices overcome through model development (assumption) Productivity of sustainable agricultural technologies and practices greater than that of current, unsustainable practices (assumption) Profitability of sustainable agricultural technologies and practices exceeds income from conventional agriculture and impacts positively on rural households’ income and welfare |

Project Objective & Goal

| 12 | Benefits of CFM provide adequate incentives for sustainable forest management and forest conservation (driver / assumption). Profitable enterprises developed and tested within project life span (driver / assumption). Key stakeholders, including the private sector and service providers, will maintain high levels of support during, and extend their commitment beyond, the project life span (assumption) Communities motivated to effectively participate and invest time and resources in CFM structures throughout the project life span and beyond (driver / assumption). Sustainability challenges and risks are effectively overcome and risks mitigated throughout the project life span and beyond (driver / assumption) |
| --- | --- |
|  | Strategic objective: The ECCLE project allocates adequate attention and resources to the development of tested and proven models for community forest management (driver) Key stakeholders support the review and institutionalization of said models to allow for mainstreaming (driver / assumption) |

## IV: Review Findings

The Mid Term Review covers the period September 2021 to December 2024 (with occasional data to 31.3. 2025). Therefore, the MTR covers a total of 40 months (67%) of the planned project period. This is referred to as 2/3 implementation point in subsequent text. The MTR was originally planned for the end of August 2024, but took place only the following year, after the 2024/25 rainy season. The MTR was executed between April and September 2025. At MTR completion point, only 11 months of project implementation time remains. This is sub-optimal for effective project delivery (Lessons Learned # 2).

The Review was carried out by one international consultant reviewer under the guidance of the Implementing Agency UNEP and working closely with the Project Team. As per Terms of Reference, an Inception Report was prepared (2nd revised version, 10 July); and a Field Debrief / Preliminary Findings Note in the form of a PowerPoint presentation was presented to key stakeholders on 4th July 2025. A draft report was submitted to stakeholders in Zambia for review 18th September and a validation workshop was held 30th September 2025. The full draft main review report was submitted to UNEP on 25th September 2025.

As tasked in the Terms of Reference (Annex 9), the review findings chapter provides information and rating on A –Strategic Relevance; B – Quality of Project Design; C – Effectiveness; D – Financial Management; E – Efficiency; F – Monitoring and Reporting; G – Exit and Sustainability; and H – Other Factors and Processes Affecting Project Performance and Cross-Cutting Issues. Based on the prioritization during the Inception Phase, greater emphasis has been given effectiveness, efficiency, sustainability, project inception, stakeholders, gender and country ownership. (See Inception Report). In addition, the review addresses a few specific questions raised by the project steering committee and stakeholders (Annex 17).

## A:  Strategic Relevance

The Ecosystem Conservation and Community Livelihood Enhancement (ECCLE) project in Northwestern Zambia is aligned with UNEP strategic priorities, policies and work plan as demonstrated by a review of the Project Document and subsequent implementation strategies. The ECCLE project is also fully compliant with GEF policies and requirements, and project goals are aligned with global environment benefits. The review further confirmed that the ECCLE project is well suited to the stated environmental concerns and needs at national (Zambia)and sub-region (miombo eco-region) level. The project aligns well with GEF-7 and UNEP regional aspirations, as well as global development goals. It provides strategic relevance at international level and underscores Zambia’s commitment to the Sustainable Development Goals (SDGs), especially Goal 15 (sustainable forest management) and Goal 5 (gender equality).

At the time of its conception and planning, the ECCLE project was very well attuned to forest policy and legislation, forest investment planning and regional UN-REDD+ considerations. Building on lessons from earlier co-management initiatives combined with a strong government commitment to create a legal environment for citizen empowerment, the project presented a compelling vision for a process of change, local and strategic.

At local level, through strengthening “community-based sustainable management of forest landscapes and providing improved livelihood opportunities for targeted forest-dependent rural communities” (project objective) in selected forests intended to produce environmental and socio-economic benefits for Northwestern Province. At strategic level, the project was expected to generate / bring about a model that will enable future replication of community-driven sustainable forest management across the province. Furthermore, nationally, the project would contribute to “the development of tested, proven systems of community management of forests and natural resources [at multiple scales] that are ready for mainstreaming. These highly relevant, but very ambitious objectives are highly relevant for other ongoing initiatives and create pronounced expectations on the results from the ECCLE project across Zambia.

Through its explicit strategic objective to develop CFM models for mainstreaming and Knowledge Management component, the ECCLE project has the potential to generate substantive interest among other GEF funded projects and non-GEF initiatives in Zambia. The adaptive forest management reviews, joint steering committee meetings and attendance at the regional implementation partner knowledge management facilitate such exchanges.

Since project approval in August 2021, several changes have taken place within Zambia’s policy, legislative, institutional and regulatory (PLIR) environment, some of which have made it more difficult for the project to attain its goals. Key changes include:

- After the 2021 elections, a period of institutional change followed, with ministerial restructuring and Forest Department internal reorganization.

- Slow integration of REDD+ lessons in national forest policy and the Forest Investment Programme not taking off as envisaged; at the same time, important lessons were drawn from the first-generation landscape level carbon projects (e.g. TRALARD, ZIFL-P).

- An emerging parallel policy process strengthening climate change action culminating in the establishment of a legal framework for integrating environmental sustainability into Zambia, the Climate Change Act of 2024.

- The declared intent by Government to review and revise both the 2015 Wildlife and Forests Act, processes which were still on-going at the time of the MTR; and

- The declaration of a National Emergency in February 2024, following the El Niño-driven drought which devastated the 2023/2024 agriculture season.

At the first Project Steering Committee held in June 2023, the Forestry Department requested to postpone the implementation of ECCLE output 1.5. (Subsidiary legislation) in anticipation of the revision of the main Act. A request was made to variate the use of funds (from subsidiary legislation to support the main review process). The Project Steering Committee granted a postponement until PY4 (2024-2025). By May 2025, the legal review of the Forest Act was still on-going. The Forestry Department secured funds for the legal review from elsewhere and output 1.5 is awaiting a decision.

Whilst the suspension may have been meaningful from the point of view of policy development, it did not optimally support the ECCLE project objective and process of CFM modelling for mainstreaming. The project still has the potential to play an important role in supporting policy review, effectively supporting Zambia’s aspirations to attain sustainable forest management through the devolution of powers to local communities, by reviewing and updating the very foundation of subsidiary legislation as part of CFM model development, by clarifying on how best to shape deliverables and key output in a way that serves policy development. The project may support the process in various ways: providing direct access to community input, availing resources (budget) to the formulation of models, and access to a peer review function through the knowledge management component (Recommendation 7).

Rating for Criterion A – Strategic Relevance:  Satisfactory

## B: Quality & Revision of Project Design

The review of the ECCLE project design in the MTR Inception Report refers. Below are summarised key strengths and weaknesses:

Project design strengths. The Ecosystem Conservation and Community Livelihood Enhancement (ECCLE) project is a significant initiative for the development of sustainable forest and natural resources management in Zambia (see Criterion A: Strategy).  In summary, the successful design features are: (i) a dynamic, collaborative implementation model based on public-private-community partnerships, facilitated by civil society; (ii) long-term integration of sustainable forest management into district land use planning; (iii) a socially inclusive implementation strategy attempting to address economic viability at the nexus of conservation and poverty reduction; and, (iv) the explicit intent to generate tested, proven CFM systems for sustainable forest management, ready for mainstreaming and replicating (after 20 years of piloting co-management in Zambia).

Project design weaknesses. The weaknesses in design features are: (i) challenging timelines poses risk for overall sustainability; (ii) higher level, intermediate and impact level risks to key project premises, not well elaborated nor mitigated; (iii) project rationale not grounded in firm evidence, in particular component 3 (sustainable agriculture); (iv) timeline for testing, proving and validating models (CFM and CSA) too short; (v) assumptions and drivers supporting ToC weakly formulated; (vi) incremental cost reasoning scenarios over-optimistic; (vii) stakeholder capacity, engagement, roles and responsibilities not clearly formulated; (viii) private sector mode of engagement and co-financing commitments unspecified; (ix) community treated as ‘black box’, without due appreciation of the need for differentiated engagement and benefit-sharing; (x) gender barriers / pathways  to effective inclusive participation and economic empowerment not well formulated; (xi) project design lacks sustainability/exit strategy.

Revision/amendments to design. The project was designed in 2019-2020 with the support of a GEF Project Preparatory Grant (PPG). There is limited documentation to show whether a formal appraisal of the Project Document was conducted. It is conceivable that such a process could have provided an opportunity to identify and address some of the design considerations noted above. The project Inception Phase was comparatively brief and it appears that a comprehensive review of the project design was not undertaken during that period. The project team, however, was aware of some of the weaknesses in the Project Document and has attempted moderation through variation of project expenditure and the implementation strategies (adaptive management), which have been approved by the project governance structures and the Implementation Agency, UNEP.

The quality of project design was further assessed by systematically examining the thirteen sub-categories defined in the Project Design Quality template and scoring against the standard weighted rates provided in UNEP Mid-Term Review Criteria Ratings Matrix (2024). The results are shown in Table 4.

Table 4. Weighted rating of the Quality of ECCLE Project Design

| PROJECT DESIGN ELEMENT | RATING (1-6) | SCORE |
| --- | --- | --- |
| Operating Context | moderately satisfactory | 3.9 |
| Project Preparation | moderately satisfactory | 3.9 |
| Strategic Relevance | highly satisfactory | 5.15 |
| Intended Results and Causality | moderately unsatisfactory | 3.0 |
| Logical Framework and Monitoring | moderately satisfactory | 3.9 |
| Governance and Supervision Arrangements | satisfactory | 4.75 |
| Partnerships | satisfactory | 4.75 |
| Learning, Communication and Outreach | satisfactory | 4.75 |
| Financial Planning / Budgeting | satisfactory | 4.75 |
| Efficiency | moderately unsatisfactory | 3.0 |
| Risk identification and Social Safeguards | moderately unsatisfactory | 3.0 |
| Sustainability / Replication and Catalytic Effects | unsatisfactory | 2.25 |
| Identified Project Design Weaknesses/Gaps | unsatisfactory | 2.25 |
|  | 49.35 / 13 = 3.8 points |  |

Rating for Criterion B: Quality of Project Design - Moderately Satisfactory

## C: Effectiveness

The review assesses effectiveness across four dimensions: availability of outputs (criterion C2), progress towards project outcomes (C3), likelihood of impact (C4) and adaptive management (C5). Emphasis is placed on the timeliness, quality and ownership of outputs and whether the project is adopting approaches or delivering activities to support the uptake of outputs (i.e. outcome level results) (ToRs, p. 37).

#### C1 - Theory of Change

The process of review and validation of the Theory of Change at Review (ToC), with associated barriers and key assumptions, is presented in Section III above.  In terms of impact on project progress and performance, working with an outdated ToC, generated extra and unnecessary work for the project M&E Unit, constrained model development, hampered synergies and reduced on the efficiency of results-based management. It is strongly recommended that, in future projects, ToC revisions are made before start-up or at an early stage of project implementation (see Lessons Learned # 1).

#### C2 – Availability of Outputs

The Review will assess the project’s success in producing the planned outputs and making them available to the intended beneficiaries as well as its success in achieving milestones as per the project design document or any formal revisions (ToRs, p. 37).

The ECCLE project has made good progress during its two full years of implementation, producing the planned outputs and making them available to the beneficiaries. Performance varies significantly between components, with two components on track and one lagging behind. By the end of 2024, the ECCLE team estimated that Component 1 (CFM frameworks) had completed 95%, Component 2 (CFMG NR business) 81%, but Component 3 (sustainable agriculture) only 51% of the planned activities. The weak performance of the agriculture component is worrisome considering its weighty significance for project overall sustainability; likelihood of impact; and synergies between outputs and outcomes. The causes appear derived from design error and slow mobilisation, not from the process of delivering outputs to the beneficiaries. The detailed performance is further elaborated below.

Progress against key deliverables and benchmarks, measured against the progression estimated by the team (“Completion of Deliverable”) against that outlined in the ProDoc (p. 109) ranges between satisfactory and highly satisfactory (Annex 16). General quantitative progress against deliverables and benchmarks in general has been good, but closer scrutiny resulted in the downward adjustment of some estimates.

Output 1.4. Knowledge management had come to a delayed start, and only one participatory review had been held at the time of the MTR. This is unfortunate, as the KM process is critical to model development. Outputs 2.2. and 2.3. have made good progress but are still far from functional business enterprises generating revenue that will pay for costs and salaries of trained staff. Component 3 is lagging behind on several aspects, the field programme did not take off due to several factors, including a change of service provider; a deliberately delayed start; and the drought affecting the 2023/24 agricultural season.

Whilst quantitative catch-up is good, and many deliverables have been produced, time for reflection, consolidation and learning lessons has been short. During the remainder of the project, there is need to consolidate deliverables, learn lessons, build synergies and integrate key findings into project exit and CFMG sustainability strategies. (See below and Recommendations 6, 7, 8, 9, 10, 11).

Component 1.  Sustainable forest management (SFM) embraced by local communities and mainstreamed in gender-responsive local development plans (formerly Developing the enabling regulatory and planning frameworks for community-based sustainable forest management) comprises five outputs. Below an assessment of output quantity and quality

Output 1.1. Forest and Socio-Economic Assessment. The assessment has been completed, but outputs not fully embraced by beneficiaries, as delays have prevented synergies and consolidation. The process of contracting a service provider took very long. Contracting started early 2022, but the report was only submitted two years later, in March 2024 (i.e. in total delayed 2 years as per original work plan).

The delayed execution impacted the project negatively in at least three ways: (i) Lack of timely baseline data for adjusting progress indicators for the results framework; (ii) Key information on forest not available at the time the Community Forest Management Plans were being drafted: (iii) Lack of information on the volumes available of forest products for the development of viable value chains at the time of drafting business plans. Consequently, the utility of the Socio-economic and Bio-physical Forest Assessment was substantively reduced. At the time of the MTR, the findings from the assessment were being used in the updating of business plans. However, for CFM mainstreaming purposes, there is no immediate recommendation on how to compute the viability of CFM areas back into FNRM plans. A recommendation is made below for making use of the findings from the forest assessment in developing the CFMG sustainability strategies (Recommendation 10).

Progress rating: good quantitative progress, qualitative consolidation pending.

Output 1.2. Awareness leading to CFM. The activities planned under this output were successfully completed during PY2 and PY3: CFMA areas were delineated and plans prepared. CFMG committees put in place / strengthened and constitutions developed. Some targets were exceeded, as the number of CFM groups formed and hectares of forest placed under CFM in Ntambu substantively increased.

Issues arise concerning qualitative aspects of the process: (i) Long-term viability of CFMA areas. The documentation suggests that long-term scenario building (i.e. population projections over a 30-year period) were not considered in the planning. There may need to revisit and reconfirm the viability of CFMA areas before binding agreements are entered into (i.e. carbon off-set trading). (ii) Alignment of project-specific CFMA plans to findings from critical consultancies. Not only the Socio-economic and Bio-Physical Assessment but also the Gender Audit and Gender Strategy and Action Plan findings were delayed and could therefore not fully be integrated into the CFMA plans and CFMG governance structures. There is need to revisit the assessment findings and update plans as well as take these into consideration when drafting exit plans and CFMG sustainability strategies.

(iii) At strategy and mainstreaming level, the lessons from Forest Assessments and Gender Audit for CFM model development have not been fully captured. For two reasons: reports did not arrive on time and were not available when critical CFM frameworks and tools were established, second as the project has not yet been able to draw the strategic lessons from the consultancies. The current mechanism for reviewing consultancy reports appears slow and may benefit from speeding up (see Adaptive management C5 and Project Management H2)

Ascertaining a “large enough scale to realize the financial economies of scale needed for profitability” is premised to be a critical criterion for CFM viability and financial sustainability (ProDoc p. 84). The Forest Assessment, completed in mid-2024, makes observations on the size of project areas, but does not provide generic recommendations for model development. It would be good if the Knowledge Management Component would consolidate the lessons on optimal CFMA size.

The recommendations by the Gender Audit and Gender Strategy and Action Plan, completed in early 2023, do not recognize the draft Gender Mainstreaming and Action Plan (ProDoc p. 128). As a result of this disjoint, there is no clear recommendation on the types of gender-responsive measures the project should use to best address GEF action areas (closing gender gaps in resource access and control, improving women’s participation in decision-making and conservation management, and contributing to social and economic benefits for women).  During the remaining project period it would be good to continue implementing the gender action plan, but also to further explore and undertake some strategic analysis of which gender-responsive means are most appropriate for CFM (e.g. quotas, committees, gender champions, affirmative action). The latter should also feed into the exit plan and CFMG sustainability plans.

Progress rating: good quantitative progress, qualitative consolidation pending.

Output 1.3. District Integrated Development Plans. Integrated land use plans were successfully developed by an external consultant for all the three project areas during PY3-PY4 through a participatory process. The activities were completed, but, at the time of the MTR, the outputs were yet to be fully embraced by the communities and by the Government stakeholders. The formation of CFM planning sub-teams may improve the situation. At community level, communities lack experience in engaging in planning processes it is difficult to ascertain whether a broader segment of the community is aware of the plans. The size of the CFMG in Kelongwa – Kamanama also does not allow for easy adoption. Ownership was enhanced by co-opting the Ward Development Committee and the Ministry of Community Development into the process. However, the procedure for effectively integrating ILUP and CFMA planning will require efforts beyond those of the project. During implementation, the project discovered that the next possible time to formally integrate plans will come at the end of the decade, when DIDPs will be updated. In addition to timing, a number of factors will influence the way forward: the appropriate type of overall maps (ILUP thematic maps are difficult for zoning and community understanding); the sequencing of updating CFMAs under DIDPs; the relationship between CFMAs, ILUPs, land use maps prepared for Game Management Areas by DNPW; and the effective communication of land use plans to communities and other stakeholders. It is recommended that a lessons learnt document is prepared, and that the Ministry of Local Government and Rural Development together with the Provincial Planning unit may be tasked with taking over this process as part of the exit plan and sustainability strategies.

Progress rating: good quantitative progress, major qualitative issues pending and 
procedure for integrating plans into DIDPs to be elaborated in exit plan.

Output 1.4. Knowledge management. The identification and contracting of a consultant to undertake the activities envisaged under output 1.4. took long. The consultant came on board only in early 2024 (2.5 years after project effective start date) and activities have had to be squeezed into a period of two years. Several activities commenced more or less simultaneously: The reviews of CFM/adaptive management/CSA agriculture; establishment of a KM system; network building, participation in regional exchange, development of a CFM related curriculum and course materials.

A very ambitious KM plan was developed, with emphasis on establishing a learning infrastructure and system.  The result was congestion and a slow implementation pace. The mechanism of feeding KM findings into on-going implementation under components 1 and 2 seems to have suffered (adaptive management) and slowed down budding efforts of modelling. Learning lessons through the various participatory management reviews is the key activity. At the time of the MTR, activities that had the potential to directly support the implementation of the project, were behind schedule. The findings from the initial participatory CFM review had not been finalised, hence adaptive feedback with outputs 1.1. and 1.2. (establishment of CFM governance structures and business enterprise) was only partially possible, mostly verbally through the Consultant frequent engagement in the project areas. The annual reviews of progress in sustainable agriculture had not commenced. At current implementation pace, the agreed upon planned works and deliverables will not be completed within the remaining project period. Recommendation # 7 encourages the project to refocus, an activity which will be supported by the Strategic Review (proposed under Recommendation # 3).

Progress rating: Quantitatively behind, qualitatively too broad. Need to refocus.

Output 1.5. Subsidiary legislation. At the 1st Project Steering Committee meeting held 23 June 2023, the activities under this output were rescheduled until 2025, with the justification that Government has approved a review of the 2015 Forest Act. It was observed that, “therefore, all subsidiary legislation can only be reviewed after review of the principal legislation”.  Whilst this is procedurally correct, this should not prevent the project from supporting the Government prepare the ground for improving subsidiary CFM legislation by attending to policy and legal, institutional and regulatory (PLIR) matters of relevance.

Based on the review of the project documentation, the following PLIR issues have been raised by stakeholders during the course of implementation, all of which would benefit project implementation and the future mainstreaming of CFM in Zambia. The MTR concurs. Recommendation # 7 proposes to consider these aspects under a modified output 1.5.

- Distilling recommended good CFM practice, through debating content and generating consensus on key principles, consolidating them as draft generic recommendations for consideration of the Government (in collaboration with Knowledge Management) – recommendation in ProDoc.

- Preparing for the revision of existing forest subsidiary legislation that in their current form pose barriers to CFMG business development, in particular

- SI 52 revision – license and conveyance fees for honey too high for honey producers and community businesses. The Statutory Instrument also concerns other commercial non-wood forest products – see risk management in PIR.

- Other forest products – legal constraints and requirements for co-opting potential products such as sawn timber (wild harvested, plantation) and charcoal into CFMG business plans – see value chain analyses in ProDoc, Forest Assessment and CFMA plans.

- Harmonization of FNMR governance at local level – recommendations for how CFMG and CRB mandates are harmonised at area level (feeding into the revision of both Forestry and Wildlife Acts) – see DNPW general discussion input and WLCP decision to circumvent CRB in Ntambu area by forming CFMG association.

- Effective use of by-laws - the process of strengthening sustainable land management through the use of council by-laws to build sanction into CFMA plans – how to establish generic recommendations to support CFM mainstreaming – see recommendations from ILUP consultant.

- Other KM Recommendations from the KM process that may be of relevance to the revision of and additional formulation of subsidiary legislation.

Progress rating: Quantitatively and qualitatively unsatisfactory.

Component 2. Communities empowered through gender-responsive community forest management (CFM) to manage forest resources, engage in sustainable FNRM-based enterprise and improve livelihoods (formerly Promoting the conservation and sustainable use of natural resources in community-managed forests) comprises three outputs. Below an assessment of output quantity and quality

2.1. Gender-responsive business plans. Activities started in early 2023 with a strong emphasis on training of beneficiaries and stakeholders in business planning (delayed one year from original work plan). The CFMG business plans were completed within a year. The focal value chains were those prioritised in the ProDoc (honey, carbon, NTFPs, mushroom and caterpillars).  Integration of findings from Forest Assessment was not possible because of report delay – hence communities fell back on resources available in the CFMA. Apparently, no assessment of realistic market demand, processing or ecological viability of highly seasonal NTFPs had yet been made, and the current propositions are likely not viable. The carbon engagement, envisaged in the Project Document has largely been managed by the implementation partners, WLCP and TNC, outside the scope of the project. Stakeholders have recommended caution as volatility of carbon markets need to be considered for sustainable outcomes. The recommendations from the Gender Consultant (GA/GSAP) appear to have only partially, if at all, been useful to develop the business plans. The very low skills levels in the community (including financial literacy) constitute a substantive challenge.

In general, at the time of the MTR, the business plans had less than a season in implementation, and it was difficult to gauge progress. At the time of the MTR, the component was planning to revise business plans that would extend beyond project completion. This is a very welcome initiative. It is recommended that the project (i) adopts a strong focus on economic viability, carefully assessing the value chains to be promoted for financial sustainability; (ii) ascertain that all value chains adopted for development are ecologically sustainable; (iii) taking a two-pronged approach to planning, looking at how to develop viable natural resource-based enterprise at both community and household level. Supporting the latter may take the form of looking at how CFMGs may support individual entrepreneurs develop business in the long run. (iv) Reviewing options for developing gendered pathways to group and entrepreneurial business establishment, considering the particular constraints women face in business taking a starting point structures established by the project (committees and champions).

- Recommendation # 8 encourages the project to consider broadening support to include household level enterprise and to financial viability as a key element in sustainability plans for CFMG business enterprise.

Progress rating: good quantitative progress, qualitative concerns to be addressed

Output 2.2. Gender-responsive community-based NR enterprises. At MTR, this output was still in the mobilisation phase and overall progress difficult to discern. Immediate investments were impressive: Low-hanging fruits (honey value chain) were adopted, and flagship infrastructure investments were made in the Ntambu honey factory and Kelongwa – Kamanana bulking facility. Honorary Forest Offices (HFOs) were engaged to patrol community forests successfully. Technical Business Units were established. By the end of 2024, technical business unit managers had been engaged at Kelongwa-Kamanana and Ntambu, and fresh investment plans made. Construction of an eco-tourism camp site and a mushroom value chain bulking centre commenced in Kelongwa-Kamanana. At the time of the MTR the broader community was yet to embrace the achievements and forge ownership.

In August 2024, a nature-based enterprise seed fund was launched in two sites. It ran into administrative difficulties, and nine months later funds were yet to be released. The impression obtained was that the activity could “go either way”, suggesting that project management should give this output adequate attention, not least because its contribution to overall project success through generating options for alternative livelihood income is significant.

Key considerations for the remaining project period include administrative efficiency, financial viability, financing, consolidation of major infrastructure ownership, legal documentation and title deeds. The support from the partnering Corporate Social Responsibility Programmes will be crucial and will benefit from being engaged in planning for sustainability as soon as possible. For local communities to fully adopt outputs, this component will require strengthened consolidation efforts and sustained support from project management, partners and stakeholders.

Progress rating: fair quantitative progress (low hanging fruits), next step qualitative focus on the selection and foundational development of a few, financially viable community business enterprises.

Output 2.3. Capacities for gender-responsive governance, NRM and business. Much relevant and necessary training has been delivered. A first round of training and capacity-building had been completed at the time of the MTR. A second capacity needs assessment undertaken at the end of 2024 would be guiding both the revision of business plans and the development of further skills training. Some considerations advisable to bear in mind are: (i) the biggest training and capacity-building needs are found at community level; (ii) the special needs of women and vulnerable groups for training in gendered business strategies and functional literacy; (iii) the need to optimise on resources over the long-term: The project is able to finance training and basic equipment, that will be difficult for the CFMGs to maintain after project closure. Not all trainings should be restricted to CFMG members, for example, awareness-raising across the community on the pros and cons of carbon-offset trading to generate solid buy-in for sustainable forest management would benefit from being executed widely.

For Component 2 to demonstrate tangible results, a deliberate phase and careful forward planning will be required, including preparation of the Exit Plan and the CFMG Sustainability Plans. These plans will need to draw strategically on financing from Corporate Social Responsibility Programmes to strengthen CFMG business ventures and secure their long-term viability.

Progress rating: good quantitative progress, capacity-building for exit and sustainability 
key to continued consolidation of training pending.

Component 3. Productivity, household income and climate resilience from sustainable gender-responsive agricultural practices improved in CFM communities (formerly Enhancing the sustainability and productivity of agricultural practices in community-managed forests).

The quantitative and qualitative progress of Component 3 is unsatisfactory, due to several reasons:

- The component design is unsatisfactory. The Project Document emphasizes the significance of Component 3 as a driver for changing community behaviour in favour of sustainable land use. At the same time, it grossly underestimates the challenges associated with the successful conversion of conventional shifting cultivation to more permanent, modes of cultivation that are able to sustain productivity and provide a fair return to farmer effort and labour. The Project Documents registers these challenges but provides no remedy to them.

- The 2022 draft agriculture strategy prepared by the Ministry of Agriculture for the project, proposes a course of action that partially matches project realities. Adoption of sustainable agriculture technologies and agronomic practices are seen as the most viable way to ensure that current land under agriculture sustains smallholder improvement of productivity. Sustainable agriculture equals Climate Smart Agriculture (CSA) or Conservation Agriculture (CA) as “an integrated approach to managing landscapes – cropland, livestock, forests and fisheries that addresses the interlinked challenges of food security and accelerated climate change”. The strategy proposes to increase the adoption of CSA through a market-based approach, whereby “the focus will be on creating solid value chains with strong market incentives for a diversified farm product portfolio that assures both short- and long-term income for the farmers”. The strategy further proposes to work with on-going initiatives that have been promoted by other actors: horticulture, small livestock, legumes and agro-forestry. The first three are considered crops suitable for women. In the project sites, among the value chains proposed, only beans have an immediate market.  In 2022/23, the project successfully supported a pilot out-grower scheme was supported in Kamikolo and Kelongwa Kamanana, available to all farmers in the area. Meanwhile, the strategy underestimated the effort necessary to support remote, small-scale farmers convert production to CSA technologies, and for the project to address extension services, capitalisation, access to inputs and output markets, and risk management.

- Start-up was delayed by slow progress in identification of a suitable implementation partner. Activities appear also to have been deliberately delayed as “the engagement of farmers was seen to be dependent upon the completion of the CFMA consolidation”, possibly referring to restricting the component activities to “agricultural lands adjacent to CFM areas”. Although understandable, this was most unfortunate as agriculture interventions are highly seasonal. Component 3 would require a minimum of 3 agricultural seasons. Within the project life span (Aug-2021 to Aug 2026), this would have been possible, if activities had started in a timely fashion in 2022/2023.

- No consistent hosting. For the 2023/24 season, the project outsourced the component activities to a specialized organisation, the Conservation Farming Unit. During the season, farmer field schools were established, demo sites constructed, some 3,600 farmers trained in CSA practices. The contract was discontinued after a year, the reasons for which are not clear from project reports. The implementation of activities was taken over by the Department of Agriculture in collaboration with Zambia Agriculture Research Institute for the 2024/2025 season.

- Drought. Zambia was affected by a serious drought starting January 2024, which resulted in a national emergency. This impact was greatest in the 2023/2024 season, but effects were felt the following year. The forecasts for bean and honey harvests were poor for the 2024/2025 season.

The MTR recommends several measures for the remaining period, consolidating farmer engagement and learning lessons (Recommendation 9). However, already at this point in time, it is clear that  Component 3 will not provide the expected alternative source of livelihood envisaged, and the project is encouraged to look for other ways of supporting communities generate income, by expanding the focus in component 2.2 to embrace also household enterprise, in particular that which is accessible to women and youth (Recommendation 8).

Progress rating: quantitative and qualitative progress unsatisfactory

Output ownership by, and usefulness to, intended beneficiaries

The project has been committed to generating outputs that will be useful to the intended beneficiaries, primarily the Community Forest Management Groups, aiming to foster beneficiary ownership. Field visits and interviews with selected CFMG executive committee members showed utility and ownership.  Among rank-and-file members and the wider community, however, many were quite oblivious to the CFM achievements, ownership and relationships of authority and representation. The role of the CFMG executive committee in relation to the rest of the community and the relationship between the CFMG and the Implementation Partner were raised in discussions. After only two years of implementation, this is hardly surprising, as the process is still in its infancy. To establish an atmosphere of transparency and openness, a sustained effort will be needed to communicate project results and create awareness around governance principle through continued outreach in the CFMG areas (Recommendation 10).

Timeliness of the provision of outputs

Multiple delays at start-up affected timeliness negatively. At the end of the first project year (PY 1) in June 2022, no outputs had been produced.  Activities commenced in earnest during the second half of the second project year (PY2), i.e. in early 2023. Effectively, therefore at the time of the MTR, the project had been under implementation for two years.

The project team had made an impressive effort in catching up with activities. The process of CFM establishing and rooting itself in the community, however, difficult to speed up. It takes time to appreciate new ideas, to build new structures, develop relationships and trust, to learn and embrace new ways of doing things. In the CFMGs, it would be advisable to continue regular engagement at a steady pace, allowing new ideas to sink in, matters to be debated comprehensively, cascading trainings to be completed, repeat events and refresher courses to be held – in short, allowing for everyone to catch up.

Performance of those outputs that are most important to achieve outcomes

The components 1 & 2 – putting in place CFM frameworks and CFM business infrastructure – are cornerstones for the project outcomes. Key outputs were the successful establishment of the CFM governance structures and the establishment of forest monitoring and protection structures.

For the CFMG structures to mature and develop financial viability, activities under Component 2 and Component 3 are critical as the project evolves. At the time of the MTR, the enterprise component was less than a year old in implementation. A minimum of 5-6 years is commonly recognized for any newly established enterprise to gain a modicum of stability. If all goes well, the CFMG business enterprises will therefore attain maturity around 2028-29, underscoring the need for project partnerships to continue post-project. The CFMG NR business enterprises will need a lot of support during the remainder of the project period and be firmly written into the project exit strategy involving the implementation partners and into the CFMG sustainability strategies.

The poor performance of Component 3 is worrisome, as this component is intended to compensate ordinary households from the loss of access to forest resources, and provide for the generation of alternative livelihood income. As observed above, this outcome is not likely to materialise during the project lifespan and the output needs reorganisation (Recommendation 9).

Rating for Criterion C2:  Availability of outputs - Moderately Satisfactory

#### C3 - Progress towards Project Outcomes

Current project outputs are relevant and realistic to the situation, and they will contribute positively towards the expected change at outcome level. However, the outputs are necessary, but not sufficient to bring about the desired outcome. Additional activities and strategic adjustments will be needed, i.e. consolidation of activities, streamlining strategies, long-term investment in business processes, and building a support network for sustainability (see C2, G Sustainability and VII Recommendations).

Attaining project success at outcome level is dependent on external conditions, e.g. an enabling policy environment, availability of supportive private sector partners, sustained capacity of government to support CFM, and an absence of counter-productive land use change. Drivers and assumptions were elaborated in the rToC (Figure 1) providing a fuller understanding of contextual factors and risks.

The outputs generated under Component 1 are necessary for Outcome 1: Sustainable Forest management (SFM) embraced by local communities and mainstreamed in gender-responsive local development plans, but current efforts are not adequate to bring about the desired change. Local communities have positively embraced CFM/SFM, but model refinement, integration and mainstreaming are lagging behind. The main concern is that that key drivers are not likely to materialize within the life span of the project. (i) Self-financing CFM models take long to develop, test and validate. (ii) Support from the Forestry Department to the revision of model development and the development subsidiary legislation is not forthcoming as expected, as demonstrated by the lack of progress in Output 1.5.; and (iii) The process of fusing CFMA and ILU plans into district integrated development plans cannot be fast-tracked outside the government planning framework, as demonstrated by progress in Output 1.3. Meanwhile, the project still has time work towards codifying results from knowledge management products and integrating recommendations for best CFM/SFM practices into government policy and legislation.

The outputs generated under Component 2 are highly relevant for Outcome 2: Communities empowered through gender-responsive community forest management (CFM) to manage forest resources, engage in sustainable FNRM-based enterprise and improve livelihoods, but the project is yet to demonstrate the viability of the self-financing model. The project, during its life span, is not likely to be able to demonstrate the basic premise, i.e. that community business and enterprises are profitable, capable of generating a surplus big enough to pay for (a) the cost of managing forests sustainably, (b) business capitalization and operational costs, as well as (c) providing tangible benefits to community members (driver / assumption). From this does not follow that lack of viability has been demonstrated, but rather that time and resources are needed to test the model. It is envisaged that testing and validation will only take place after project closure.

The outputs generated under Component 3, are relevant for Outcome 3: Productivity, household income and climate resilience from sustainable gender-responsive agricultural practices improved in CFM communities, but not adequate. The main concerns are (i) no immediate technology package is available, that is attractive enough to overcome barriers to the adoption of sustainable agricultural technologies and practices, at a scale envisaged in the Project Document; and (ii) the economic viability of alternative models to farmers is poor. The productivity of sustainable agricultural technologies and practices do not exceed that of current, unsustainable practices; and their profitability does not exceed income from conventional agriculture, undermining their envisaged role as ‘game-changer’ for sustainable land use.

The answer to the question whether sufficient effort and attention is being directed towards reaching outcome levels, is: ‘not yet’. During the remaining project period, there is need for consolidating activities that will enable communities to embrace project achievements, stakeholders to engage to support sustainability and allow project management an opportunity to address issues at outcome level. Allowing additional time for structured consolidation and transition increase the likelihood of achieving stronger results at outcome level.

Rating for Criterion C3:  Achievement of Outcomes - Unsatisfactory

#### C4 - Likelihood of Impact

During the MTR Inception Phase, the wording of result statements at intermediate state and long-term impact level was amended. Levels of ambition were moderated and UNEP terminology adopted. The amended Theory of Change is shown above in Figure 3, and detailed wording in Annex 16.

At project level, the likelihood of the intended, positive impacts becoming a reality is good. Success is dependent on the extent to which the project is able to consolidate achievements; support communities embrace outputs and build ownership; retain ownership among duty-bearers and engage implementation partners in co-creating a sustainable exit / future.

The likelihood of the project producing outputs and outcomes necessary for scaling up, replication and mainstreaming across the province / country, is, at the most, fair. As observed above (C3), much attention and time will still be needed to consolidate, test and validate outcomes. By necessity, this work will extend beyond the project lifespan. The impact will depend on factors outside the immediate control of the project, namely external support (i.e. the Forest Department stepping in and taking ownership of key outputs) and adequate resources (i.e. the project and its successors being allowed additional time to consolidate, test and validate, CFM models and practices).

The ECCLE project is already playing a catalytic role in generating conducive conditions for community forestry in Zambia. The knowledge management component has generated widespread interest among practitioners across the country. ECCLE has the potential to positively impact on the scaling up of CFM in Zambia. For this to happen (i) the CFM model building and knowledge product development, testing and validation must continue systematically; (ii) resources are earmarked for clearly packaging results for dissemination; (iii) the Forestry Department accepts greater ownership of the project outputs. Indeed, the project deliverables may contribute positively to the revision of the Forest Act, which further improves the likelihood of scaling up and replication of the model across dryland forests in Zambia.

The evidence suggests that the CFM models developed by the ECCLE project, if appropriately consolidated, presented and embraced, are applicable across Zambia. Hence, potential for future replication is significant. Currently, there is limited evidence of the project ability to create “readiness for mainstreaming” – however, the project is on track, proceeding in this direction and, given the time and support needed, may do so.

Rating for Criterion C4:  Likelihood of impact – Moderately Unsatisfactory

#### C5 - Adaptive management

‘Adaptive management’ is a central concept in the ECCLE Project Document, at two levels:

Adaptive management is an important tool in the project implementation at community level. It is seen as a key tool to generating a common understanding during mapping and planning under several outputs (e.g. Output 1.3. DIDPs), in annual participatory management reviews central to discursive learning in CFM and CSA (i.e. Output 2.3. and 3.2. annual adaptive management reviews).  Component performance in adaptive management is discussed under review criterion C2. In general, the project has performed very well in adaptive management at community level.

Adaptive management plays an important part in project management, considered a “key to project implementation, and thus the specific modes of delivery of the outputs, the choice of partners, etc. remains flexible to ensure that decisions made during project implementation are made based on information gathered during the project and the continued input of stakeholders” and that “measures [are taken] if progress is not being made” (ProDoc, p. 59, 62).

As part of project management there is ample evidence of constructive adaptive management, whereby the PM and PIU/TSU have demonstrated innovation and resourcefulness in resolving administrative glitches and technical dilemmas. The Forestry Department HQ and EA specialists have routinely been consulted. Issues and risks have been reported to the project governing bodies, the PTC and the PSC, for resolution and the IA has been called upon in matters relating to GEF-7.

Adaptive management measures have tended to focus on immediate implementation issues affecting project implementation, a myriad of small administrative and technical concerns that needed attention for the project to progress. The project has succeeded well, as shown by the performance against quantitative benchmarks (Annex 16).

Project management has had less success in addressing strategic issues, such as the adjustment of project document, model development, progression towards outcomes, and risk management. This is a result of a combination of factors, i.e.  weaknesses in project design, delayed project mobilization and start-up, substantive delay in establishing the decision-making structure necessary for resolving more complicated matters. However, strategic decision-making has been suboptimal due to a lack of timely input from the Implementing Agency and shortcomings in the support from key implementation partners, in particular Forestry Department. Some implementation partners have not fully embraced their role and responsibility. A further discussion is found in H2 project management, H3 stakeholder participation and H6 stakeholder ownership. Recommendation 2 addresses the need for strengthened project governance which is a precondition for strategic adaptive management to improve.

Rating for Criterion C5:  Adaptive project management –Satisfactory

Overall project effectiveness is rated based on three criteria in the UNEP matrix: availability of outputs, achievement of outcomes and likelihood of impact. See scoring in Table 5. When considering the project efforts (C2 and C5, adaptive management), the rating is moderately satisfactory.

Table 5. Overall rating the ECCLE Project Effectiveness (criterion C)

| EFFECTIVENESS ELEMENT | RATING (1-6) | SCORE |
| --- | --- | --- |
| C2 Availability of outputs | Satisfactory | 4.3-5.2 |
| C3 Achivement of outcomes | Unsatisfactory | 1.8-2.7 |
| C4 Likelihood of impact | Moderately unsatisfactory | 2.7-3.5 |
| Overall score | Moderately unsatisfactory |  |

## D: Financial Management

The review considers the rate of spend in relation to project’s length of implementation to MTR cut-off date, the agreed workplan and the delivery of outputs. The rate of expenditure at 2/3 implementation point is 61%, (at 31.03.2025), with slightly better expenditure in relation to the project implementation period (67%). The rate of delivery of outputs during the same period was fair (see C2 and Annex 16).

No shortcomings in project financial reporting and/or auditing requirements were reported. Standards were considered adequate by all parties. No formal record was found of financial documentation required by the donor as missing, inaccurate, incomplete or unavailable.

However, reporting on co-financing was less than optimal. Reports were submitted three years into implementation, with inconsistencies (Annex 5). A query placed by the MTR regarding the accuracy of reported MGEE over-expenditure did not receive a reply. One co-financier, WWF Zambia, did not report any expenditure or activity in the project area, and their removal should be considered (Recommendation 5).

Further, delays in internal EA contracting of sub-awardees, Implementation Partners, were observed, which affected project implementation on the ground. These shortcomings are discussed under Efficiency (Criterion E) and Project Management (Criterion H2) and a recommendation is given on tightened contracting procedures (Recommendation 5).

Financial management issues that are affecting the timely delivery of the project or the quality of its performance raised by stakeholders include delayed disbursement of funds (moderated by EA pre-financing). The IA observed that the pre-financing of activities by the Nature Conservancy (TNC), the Executing Agency helped maintain implementation momentum but temporarily introduced unusual practices into the UNON financial system. These practices were quickly identified and corrected through reinforced controls and improved communication between the IA and EA finance teams, thereby restoring normalcy. Inadequate reporting on co-finance was a challenge, rectified in reporting (PIR 2024).

In terms of adherence to proper financial management standards and adherence to UNEP’s financial management policies, the IA reports. The financial management performance of the ECCLE project has been satisfactory, reflecting strong adherence to UNEP's fiduciary standards and transparent reporting mechanisms. Financial planning, budgeting and reporting have been timely and generally of high quality, allowing project delivery to proceed with minimal disruption. The IA notes with appreciation that challenges were addressed promptly, ensuring alignment with UNEP policies and donor requirements.

Overall, the corrective measures taken demonstrate a responsive and adaptive management approach. The project operates on a sound financial footing, which inspires confidence in its continued delivery of intended outcomes.

Rating for Criterion D: Financial Management - Satisfactory

## E: Efficiency

Under the efficiency criterion, the Review assesses the extent to which the project delivered maximum results from the given resources, the cost-effectiveness and timeliness of project execution (ToRs p. 39).

Cost-effectiveness. Findings from the financial management review suggest that project has successfully relied on administrative and financial norms and procedures of the Executing Agency, The Nature Conservancy, in managing project cost-effectiveness. It is outside the scope of the MTR to investigate cost-effectiveness in any greater detail. Broader issues may warrant attention by the  Terminal Evaluation (TE) include: (i) the relative cost-effectiveness of a large consortium approach, where each partner will have independent administrative costs and operational costs; (ii) the impact of delays in signing of agreements and Memoranda of Understanding on overall cost-effectiveness; (iii) the extent to which a project is able to support CFMGs develop cost-efficiency modes of operation and conducting business (Recommendation 15).

Timeliness. The project suffered from a slow start-up and mobilisation of staff, resulting in a loss of one year of implementation time, with subsequent multiple delays arising from administrative procedure and slow preparation of contracts and agreements. The project is approximately 10 months behind schedule but has been able to catch up on activities deliverables (see C2 and Annex 16). However, delays distorted activity sequencing. Consolidation will be necessary to ensure quality. The negative impact of delays has been the greatest on innovation in governance structures (e.g. developing gender-responsive community enterprises).

Efforts to increase efficiency. During implementation the project has excelled in efforts to try to increase efficiency. Efforts include a the good project management by a strong and dedicated project team (PIU/TSU), the use of institutional mechanisms (e.g. nomination of Provincial Focal Point to boost FD oversight); seeking complementarities with other GEF projects (e.g. joint steering committee with other GEF project); close follow-up with stakeholders and partnerships (e.g. contributions to project deliverables);  and other synergies and complementarities (e.g. making good use of district and provincial commemoration of Forestry and Environment Day to increase project visibility).

Timely project closure. Regrettably, stronger project management cannot offset the negative impact of earlier delays. The project will require a carefully managed closure through strategic consolidation and phased exit to allow key processes to mature (see Criterion B: project design, C2-C4, timeliness). Other factors supporting this approach include:

- Improved likelihood of impact, as outputs and results are consolidated.

- Better prospects for financial viability and sustainability as community governance and business structures strengthen.

- Opportunity for farmers and beekeepers to recover from loss of one season due to the 2023/2024 drought.

- Increased outreach to farmers adopting climate smart agriculture as an alternative livelihood strategy.

- Greater overall sustainability through adequate time to develop a viable project exit plan and sustainability strategies at community level.

Scope and duration of the timely project closure through strategic consolidation and phased exit. Not all components need to conclude simultaneously. A staggered closing down may be considered, whereby outputs are gradually phased out. Two components will benefit the most from a timely closure through strategic consolidation and phased exit: the development of community enterprise (Output 2), and the adoption of climate smart agriculture (Output 3). The final implementation cycle should be aligned with the 2026 agricultural season to ensure operational learning, consolidation of results, and continuity arrangements are in place before project completion. If resources are constrained, a shorter, focused transition period may be applied, during which time, the activities of the two key components are handed over to project partners at the change of budget years. Component 2 activities are included in the CFMG sustainability plans and taken over by Corporate Social Responsibility partners. Component 3 may be integrated into MoA work plans with a government budget line from 2027.

UNEP Matrix Review Criteria Rating - E: Efficiency

Only two sub-criteria in the UNEP matrix are used when rating Project efficiency: timeliness/delays and (i) their impact on at least one group of stakeholders, and (ii) sequencing of project activities and events. The overall rating at 2/3 implementation point was unsatisfactory, due to the delayed start and the subsequently loss of synergies and distorted sequencing of activities. The rating is likely to improve as efforts to enhance effectiveness, and activities are consolidated during the proposed extended project period. (Recommendations 1, 8, 9, 10).

Rating for Criterion E:  Efficiency - Unsatisfactory

## F: Monitoring and Reporting

The Mid-Term Review was tasked to assess monitoring and reporting across two sub-categories: (i) monitoring of project implementation and (ii) project reporting (ToRs, p. 39-40). The findings are summarised in Tables 6 and 7. The tables provides justifications for Recommendation 4 (Adoption of revised ToC and amendment of Result Framework Indicators) and Recommendation 14 (Consolidating Documentation and Records).

Table 6. MTR Review Findings: Monitoring of ECCLE Project Implementation.

| - Sub-criteria/variables | ECCLE Project findings |
| --- | --- |
| - Availability of a sound monitoring plan that is designed to track progress against SMART results towards the provision of the project’s outputs and the achievement of the project outcomes, | Yes. The Draft M&E plan presented in the ProDoc (p. 95) has been regularly revised and updated, annually. The latest M&E plan relevant to the MTR was approved by the Project Steering Committee on 4th April 2024. |
| - Appropriate disaggregation by gender, marginalisation or vulnerability, including those living with disabilities. | Yes. The project disaggregates data by gender routinely. Disaggregation by vulnerability/disability and age are culturally sensitive. Vulnerability reporting is mostly qualitative. |
| - Relevance and appropriateness of the project indicators as well as the methods used for tracking progress against them as part of conscious results-based management. | No, only partially. Output indicators were adjusted by project in conjunction with work planning in 2022. Some project outcome indicators are not SMART, do not capture progress well and do not support results-based management. Some are lagging indicators, measuring progress enterprise success on what essentially is a break-through curve (e.g. number of CFMG turning profits and sharing benefits with surrounding communities, Outcome 2, Indicator a). For the project to track incremental progress they would need performance indicators, showing how far each CFMG group has advanced on the route of becoming a viable enterprise. Drawing on Section III (ToC, associated drivers and assumptions), the project is encouraged to develop and adopt performance indicators that measure CFMG step-wise progress towards sustainability, which may serve as proxies for the progression towards outcomes. (Recommendations 4 and 13) |
| - Operationality of the monitoring system | Yes. The monitoring system is operational, and the project regularly reports to the IA and project governance bodies as per requirement. |
| - Facilitates of timely tracking of results and progress towards project milestones and targets throughout the project implementation period. | No, only partially. At output level tracking of progress is good, but at outcome level, tracking is difficult due to the inadequacy of some of the indicators. They need to be substituted/supplemented with performance indicators appropriately tracking progress (See iii above, Section III and Recommendation 4). |
| - Availability, accuracy and documentation of relevant and good quality baseline data. | No. The project baseline conducted in conjunction with the Socio-Economic and Biophysical Assessment, produced partial data, but too late (March 2024, two years after project start-up). The M&E Unit has pro-actively attempted to remedy this by using the Rapid Agricultural Survey data. Regrettably, the Gender Analysis baseline data and indicators are too general to serve project needs. Current project tracking table baseline data at outcome level is incomplete and many targets at MTR are missing rendering it less useful for measuring progress. As outcome indicators are adjusted (see iii above and recommendation 4), it is recommended that complementary indicators are added for which proxy baseline data may be construed retro-actively. Satisfaction surveys (see vii) may support baseline data generation. They should be selected in a way that will support sustainability planning at CFMG level. |
| - Monitoring the representation and participation of disaggregated groups, including gendered, marginalised or vulnerable groups, such as those living with disabilities, in project activities. | Partially. As observed above, the project reports principally qualitatively on vulnerable groups and youth. However, systematic surveys to gauge the satisfaction of specific segments of the target group appear not to have been done (cf. Output 2.2. satisfaction with business plans; and Outcome 2, satisfaction mini-survey envisaged in conjunction with Annual Management Reviews (ProDoc p. 137). The project is encouraged to make use of satisfaction surveys to filling data gaps (Recommendation 14). |
| - Use of quality monitoring data to adapt and improve project execution, achievement of outcomes and ensure sustainability. | Yes. Project management uses output monitoring data regularly to steer project execution. However, the outcome indicators do not optimally monitor the gradual progression towards outcomes and at a strategic level (see above iii, v and vi). For drafting and subsequent monitoring of the exit plans and sustainability strategy, it is proposed to develop progress indicators that measure CFMG progress towards sustainability outcomes. (Recommendation 14, 13 and 10) |
| - The Review should confirm that funds allocated for monitoring are being used to support this activity. | Yes. Funds allocated for monitoring are being used accordingly. However, the M&E budget may need revision, to allow for additional surveys to generate baseline data (see vii and Recommendation 14). The budget also does not adequate to support independent duty-bearer stakeholder monitoring (e.g. Forestry Department and/or District Teams to visit project sites independently), which reduces on stakeholder ownership. (Recommendation 11) |

Table 7. MT Review Findings: ECCLE Project Reporting.

| - Assess the extent to which both UNEP and Donor reporting commitments have been fulfilled. | At supervisory level, the review found a high level of satisfaction with UNEP and GEF reporting commitments, noting they were met in a timely, transparent, and reliable manner. |
| --- | --- |
| - Confirmation that meeting and field mission reports are being written and centrally stored. | At supervisory level, meeting and field mission reports were consistently prepared and centrally stored for easy reference and accountability. At project level, monitoring reports are being written and centrally stored. Project is advised to improve on document identifiers (data, author, revisions). (Recommendation 14) |
| - Need for any corrective action has been indicated in any project reports (e.g. as an identified risk), and action taken. | At supervisory level, there was no mention of need for any corrective action, and most risks were carefully mitigated and monitored. At project level, identified risks reported regularly and forwarded to project governing bodies (PSC and PTC) for resolution and action. The key project partners, including Forestry Department and IA, are encouraged to intensify follow-up (Recommendation 2 and 14). |
| - Confirm whether formal reports have been appropriately authorised by both the author and the relevant supervisor. | At supervisory level, the review confirmed that all formal reports have been duly authorized by their respective authors and validated by the relevant supervisor. However, as observed elsewhere the mechanism for adoption of consultancy reports needs improvement in support of Knowledge Management and full project ownership. At project level, semi-annual reports authorized by PM and supervisor (EA, TNC Director). Minutes from Project Steering Committee have only partially been signed and archived. As the Project Technical Committee has been granted more decision-making powers, there is need to produce final, corrected minutes, that are signed and archived. Forestry Department is expected to assume greater responsibility (Recommendation 2, 14). Generally, project is advised to improve on document identifiers (version, author, revisions). This applies to contract and agreement data base as well (PIU, The Nature Conservancy) |

UNEP Matrix Review Criteria Rating - F:  Monitoring and Reporting

Project monitoring and reporting is rated against the two criteria Monitoring of Project Implementation and Project reporting. The performance is very good, with a few shortcomings as identified above, bringing the review score to satisfactory.

Rating for Criterion F:  Monitoring and Reporting - Satisfactory

## G: Exit and Sustainability

The Review will (i) identify and assess the key conditions or factors that are likely to undermine or contribute to the endurance of benefits at the outcome level; and (ii) ascertain that the project has put in place an appropriate exit strategy and measures to mitigate risks to sustainability. (ToR, p. 40).

#### G1 – Exit strategy and plan

The ECCLE Project Document is silent on the timing of the drafting of an exit strategy. The Inception Review workshop held at the end of March 2022 encouraged the project to put in place an exit strategy early so as to address sustainability issues during implementation. Considering the delayed start-up of the project, the project made an informed decision to await the results from the project mid-term. Stakeholder interviews confirmed that initial discussions with Project Partners had commenced for the formulation of an exit strategy. After the MTR, the project should prepare an exit plan in which sustainability, financial and institutional concerns and measures to mitigate risks to sustainability, are considered. It is further recommended that the exit strategy includes a financial component and is matched with sustainability plans at CFMG level (Recommendation 13).

Rating for Exit strategy: Likely

#### G2 – Sustainability

The MTR considered sustainability from the perspectives of socio-political, institutional and/or financial sustainability (Annex 19). Further, the project strategic objective (Annex 16) and the revision of intervention logic (Figure 3) render it meaningful to consider two tangential aspects of sustainability, namely: Replicability and likelihood of scaling up; and Measures to mitigate risks to sustainability, e.g. building stakeholder ownership, robust institutional frameworks and good governance, and securing future funding.

At the time of the MTR, the ECCLE project had not yet prepared a sustainability plan nor an exit strategy. The Project Document provides guidance regarding the initial thinking around sustainability. In addition to the factors embedded in the project design and implementation approaches, contextual circumstances or conditions that have evolved over the life of the intervention are emphasized.

From a sustainability point of view, the ECCLE project design is premised on the notion that the devolution of forest management responsibilities to communities and empowering them with community enterprises and household level options to increase income, will provide sufficient incentive for them to continue to invest in the long-term forest stewardship beyond the term of the project. For these systems to be successful in the long-term, several social, financial, institutional and ecological conditions need to be met. The key conditions and factors affecting sustainability, likely to undermine or contribute to the endurance of achieved project outcomes are summarised in Annex 19.

The UNEP matrix rates sustainability in terms of the probability of socio-political, financial and institutional sustainability, i.e. the likelihood of project outcomes being maintained and developed after the close of the intervention. Table 8 shows the tentative rating, in the context of the current absence of an exit plan / clear sustainability strategy. The rating will improve as the project develops an exit strategy for the project and sustainability plans for the CFMGs. (See Recommendation 13).

Table 8. Rating the ECCLE Project likelihood of sustainability

| Sustainability dimension | From the UNEP matrix - scoring against variables | Tentative rating (04092025) |
| --- | --- | --- |
| Socio-political | Dependency on socio-political factors (low-high) Stakeholder ownership (low-high) Mechanism adaptability to changes | High dependency, moderate to fairly strong ownership, partial, weak to moderate adaptability mechanism = MODERATELY UNLIKELY |
| Financial | Dependency on future funding (low-high) Required securing of future funds (low-high) Exit strategy with financial component | High dependency, some funding secured (2/3), no exit strategy = MODERATELY UNLIKELY |
| Institutional | Dependency/sensitivity to institutional frameworks and governance (PLIR) - (low-high) Mechanism in place to sustain/support institutionalization Capacity of individuals increased / they will stay in project Exit strategy with institutional component | High future dependency to institutional support, partial to weak mechanism to sustain/support institutionalisation, capacity built, but loss of staff likely, no exit strategy = UNLIKELY |

Rating for Sustainability:  Moderately Unlikely

Project overall sustainability is rated against the two criteria (i) Exit Plan and (ii) Sustainability. The rating is measured as likelihood of project efforts bringing about the endurance of benefits at the outcome level. In the absence of an exit plan and strategy the Project sustainability rating must score low (moderately unlikely). However, as the likelihood of the project preparing viable exit and sustainability plans is high (likely), the overall score is moderately likely.

Rating for Criterion G:  Exit and Sustainability – Moderately Likely

## H: Factors and Processes Affecting Project Performance and Cross-cutting Issues

Criterion H encompasses seven sub-criteria: (i) Project inception; (ii) Quality of project management and supervision; (iii) Stakeholder participation and cooperation; (iv) Responsiveness to human rights and gender equality; (v) Environmental and social safeguards; (vi) Country ownership and drivenness; and (vii) Communication and public awareness. During the inception phase, four were identified as more significant than the others, above highlighted in bold.

#### H1 - Project inception

The date of ECCLE project approval was 1st June 2021, and the first disbursement took place on 14th September 2021 (totalling 3.5 months). UNEP project approval date was 19th August 2021, and an agreement with TNC was signed on 20th August 2021. A cash advance was effected a month later.

Subsequently, starting in September 2021, it took the EA, TNC, long to prepare partnership agreements and mobilise staff. Two co-financing agreements were signed only in 2022. An operational Memorandum of Understanding with the Forestry Department was drafted but not finalised. The project manager (PM) came on board in January 2022 and other technical staff recruitment was concluded by May 2022. Formally, the Inception phase ended 31st March 2022. Hence the total period from project approval until the end of inception was ten months.

Beyond that, vetting and contracting of new implementation partners (Trident Foundation Ltd) by TNC head office delayed until mid-2023. Putting in place project governance structures took even longer, with the Steering Committee convening for the first time only in June 2023. Though the Project Technical Committee holding its inaugural meeting a year after project start in October 2021. Hence, important aspects of project mobilisation delayed between one and two years from date of project approval and had a negative cumulative impact on project performance.

Although quality considerations of project inception have been met, the very substantive delays in mobilising staff, putting in place critical contractual and governance arrangements, at times exceeding 12 months, justify the rating of moderately unsatisfactory.

Rating for Criterion H1:  Project Inception – Moderately Unsatisfactory

#### H2 - Quality of project management and supervision

The MTR will review the planned implementation structure and the roles and responsibilities assigned to each partner or party. Where roles are not being played as planned, an appropriate recommendation to formalise correction action and/or a change in the implementation structure, should be made. (ToR, p. 41). The findings from the review are:

Planned implementation structure and the roles and responsibilities assigned to each partner: The current implementation arrangements are described in the Terms of Reference. Annex 20 summarises observations made during the MTR review on partner current performance, roles and responsibilities, deviations from plans, with recommendations where relevant. The findings support recommendations 2 (strengthened governance); 3 (strategic review and course correction); 10 (strengthening CFM at local level for sustainability); and 11 (stakeholder roles and responsibilities). See section VII.

ECCLE ‘project management and supervision’: The responsibility for implementing the ECCLE project rests with the Project Manager (for PIU/EA) and the National Coordinator (for Director of Forestry) under the supervision of the Task Manager (for IA). The review findings show that PIU is delivering effectively but is encountering strategic issues that require the action and support from the Forestry Department and UNEP. There is room for improvement. The project would benefit from a more pro-active stance and more strategic support from the IA, UNEP. The project would also benefit from the Forestry Department increasing ownership of project processes and outputs. The EA is advised to improve on the efficiency of sub-contracting. (See Annex 20 and recommendations, 2, 5, 13)

The effectiveness of project management to-date was reviewed against the prescribed sub-criteria (see below). The overall rating for project management at project field level is satisfactory. Generally, PIU/EA has handled the project well and overall project execution has been good. Suggestions for further improvement are found in Annex 20.

- providing leadership towards achieving the planned outcomes - managing team structures. - maintaining productive partner relationships (including Steering Groups etc.). - maintaining project relevance within changing external and strategic contexts. - communication and collaboration with UNEP colleagues. - risk management. - use of problem-solving. - project adaptation and - overall project execution

Rating for Criterion H2 -Project Management & Supervision: Satisfactory

#### H3 - Stakeholder participation and cooperation

An analysis of ECCLE stakeholders is found in the Inception report. The updated stakeholder list in Annex 15 and partner roles and responsibilities in implementation in Annex 20 refer. See also the discussion on stakeholder ownership under criterion H6.

In general, the ECCLE project engagement with stakeholders has been strong and effective, in implementation of activities, project monitoring and in oversight. However, vague understanding of their roles and responsibilities among some stakeholders in the project is an observed shortcoming, which has tended to increase the workload at PIU. Remedial measures have been undertaken, including a stakeholder mapping undertaken in 2022. Other efforts to enhance stakeholder participation included drafting of Terms of Reference for district teams.

Further updating stakeholder roles and responsibilities in the project exit plan and CFMG sustainability plans will bring more gains. Stronger stakeholder engagement will support consolidation of achievements. Clarifying on duty-bearer roles in specific activities will enhance the outcomes. For example: developing and delivering appropriate products for gender responsive CFM mainstreaming in Zambia with Forestry Department; strengthening climate smart agriculture outputs with Department of Agriculture; and consolidating the integrated land use planning process with the Department of Physical Planning. Other advantages will arise from providing recognition of key stakeholders, their strengths and weaknesses in support of developing sustainability strategies (e.g. clarifying district team roles in providing post-project support to communities, developing CFMGs cognizant of partner roles and responsibilities within and outside the communities). Recommendations 10, 11, 13.

The project efforts to ensure clear and effective communication and consultation with stakeholders throughout the project to-date have been good. The project has shared plans and information freely and provided for opportunities for peer-to-peer learning and exchange visits.

The inclusion of differentiated groups, including women’s groups and representatives for vulnerable segments of the community, has not been easy to arrange as these groups seldom have recognized representation at community level. The introduction of “gender champions” and “women’s committees” have the potential to significantly enhance communication between the project, CFMG leadership and community members. Recommendations 10, 11, 12.

Rating for Criterion H3: Stakeholder Participation and Cooperation – Moderately Satisfactory to Satisfactory

#### H4 - Responsiveness to human rights and gender equality

##### Adherence to Gender Policy and Strategy

The ECCLE project does not apply an explicit Human Rights Based Approach (HRBA), but the project design does not conflict with HRBA principles. The ECCLE project target group does not include people defined as Indigenous Peoples by the UN or the Zambian Government.

The ECCLE project approach adheres to UNEP’s Policy and Strategy for Gender Equality and the Environment (2015). It also strives for alignment with the GEF Policy on Gender Equality (2017) and its supporting Gender Equality Action Plan and Implementation Strategy (2020) lay out gender-responsive indicators to guide project design, monitoring, and reporting.

##### Gender analyses at design

The ECCLE project document contains a draft Gender Mainstreaming and Action Plan (GMAP) (ProDoc pp. 131-136). This plan outlines key principles for mainstreaming; provides draft gender sensitive outcome indicators to the Results Framework; lists due diligence activities at output level; and sets monitoring and reporting procedures.

During implementation, site specific Gender Analyses (GA) were undertaken, and a Gender Strategy and Action Plan (GSAP) was prepared in 2023. Unfortunately, the latter is not cognizant of the earlier GMAP and does not reflect on mainstreaming concerns, therefore does not update the project GMAP. The generic nature of the GA/GSAP recommendations and the delay in their completion rendered them less useful than expected, though a gender mainstreaming toolkit has been prepared and used in trainings across the project sites.  The project staff has continued reporting on gender in activity reports and the M&E unit maintains a gender mainstreaming tracking tool (see Table 9). The latter, however, appears somewhat over-optimistic in relation to the actual results on the ground, and may need to be moderated, as findings from satisfaction surveys are obtained (much as the estimate of progress against deliverables was moderated in Annex 16) (Recommendation 14).

##### Extent identified actions and/or applied adaptive management implemented

- The implementation of a gendered approach in ECCLE, is best analysed in two phases:

The start-up “GMAP period (2021-2023)”, when project structures were formed at community level. During this period, activities were guided by the draft Gender Mainstreaming and Action Plan (GMAP (ProDoc Appendix 13). The plan is strongly focussed on project management level, with key actions (i) Institutionalizing Gender Mainstreaming Across All Project Levels; (ii) Addressing GEF Gender Action Areas; (iii) Balancing Participation in Training & Capacity-Building; (iv) Integrating Gender in Planning, Implementation, Monitoring & Evaluation. There is no data on whether specific disaggregated targets (ProDoc p. 134-136) were attained. Spot checks suggest that most activity targets were met (e.g. training quotas), whilst strategic objectives (e.g. measures to overcome barriers, e.g. "use land use planning to improve access for women to agricultural lands”) were not systematically addressed. The Knowledge Management reports, for example, do not contain specific analysis of gender, despite this being a widely acknowledged shortcoming in participatory forestry in Zambia.

During the “Gender in Project Areas period from 2023-2024, and onwards, the project vigorously implemented the recommendations from the Gender Audits and Gender Strategy and Action Plan. The plan is focussed on delivering the project on the ground and key strategic actions focus on awareness-raising, education and training, dialogue and advocacy, collaboration with other actors, gender training for stakeholders, youth targeted programs and strengthening of monitoring and evaluation (GSAP pp. 14-17). Good progress has been achieved at local level.

The GA/GSAP report is silent on specific gender guidance to gender mainstreaming and supporting due gender diligence in the core project activities, i.e. the establishment of gender-responsive CFM structures and gender-responsive businesses and developing gendered approaches to climate smart agriculture and alternative livelihoods. The 2023 gender reports only put forward the proposal to develop and enforce gender quota for leadership positions.

The gap between the GMAP and GA/GSAP, may be overcome with consolidated action. The energetic field activities currently running, in combination with a more gendered approach to Knowledge Management will provide appropriate guidance to the exit plan activities and the drafting of sustainability plans. It is recommended that the project considers systematically reviewing all gender outputs in support of drafting sustainability plans and CFM modelling (Recommendation 12).

##### Extent to which project has taken into consideration particular gender / HRBA concerns

The ECCLE project has created ample awareness of the circumstances in Northwestern Province perpetuating gender inequalities in access to, and the control over, natural resources. As engrained socio-cultural practices, these are difficult to change. The project is encouraged to try to further push for means and mechanisms suitable to CFM that will address inequality, for example through quotas in leadership and representation as well as gender-specific intervention mechanisms (Recommendation 6,12).

The ECCLE project is aware of the specific vulnerabilities of disadvantaged groups (especially women, youth and children and those living with disabilities) to environmental degradation or disasters. However, the project has only had limited time to explore these vulnerabilities and how best they can be addressed so far. The project may consider engaging themselves with the said groups, conducting satisfaction surveys and arranging focal group discussions to discuss how barriers to participation are best removed, which may inform sustainability strategies. In doing so, the project is well served to work together with an NGO and/or Government Department that knows the target group well and is able to facilitate the discussions. (Recommendations 12,13,14).

The ECCLE project has encountered positive experiences with gender champions and women who join the CSA farmer field schools. In these individuals and groups, the project may find women who may be groomed in not only expanding project activities into the broader community, but exploring ways of strengthening CFM governance, grooming household enterprise under the CFMG umbrella, gendering climate smart agriculture and also, in future, mitigating or adapting to environmental changes and engaging in environmental protection and rehabilitation as part of a CFM future. (Recommendations 7, 8, 9, 10, 13)

Rating for Criterium H4: Responsiveness to Gender Equity - Satisfactory

Table 9. Gender mainstreaming tracking table as measured by ECCLE M&E Unit

#### H5 - Environmental and social safeguards

The ECCLE Project has put in place an Environmental and Social Management Framework in July 2024. A review of thereto related factors and procedures suggest that safeguarding considerations are at a good level of quality, detail and consistency:

- Initial risk levels were rated low.

- Safeguarding issues raised in the UNEP Environmental, Social and Economic Review Note (ESERN) addressed by the project.

- Environmental and social impacts to key stakeholders and vulnerable groups considered in gender-responsive CFM design and gender strategy and action plan (GSAP).

- Review of risk ratings has been done annually in conjunction with Project Implementation Review (PIR) reporting.

- Monitoring of project implementation has included safeguarding issues.

- Risks and safeguard responses have been discussed in Project Steering Committee.

- A Grievance Mechanism has been put in place at project level.

- Reporting on grievances and safeguarding done annually in conjunction with PIR reporting.

- No record of environmental footprint maintained by Implementing Agency or project.

Rating for Criterium H5: Environmental and Social Safeguards - Satisfactory

#### H6 - Country ownership and drivenness

An analysis of ECCLE stakeholders is found in the Inception report, an updated stakeholder list in Annex 15. Key stakeholder implementation roles and responsibilities are discussed above and detailed in Annex 20. Stakeholder participation is assessed under criterion H3. Whilst there is some overlap between Country Ownership and Institutional Sustainability (criterion G2), this criterion, H6, focuses primarily on the forward momentum of the intended project results.

The key Government Departments needed to move the project results forward, to consolidate sustainable forestry and natural resource management in the three project sites and to mainstream the CFM model across Zambia are the three technical ministries – forestry, wildlife, agriculture – together with local government and planning (Councils, MLGRD, Provincial Planning Unit). The Forestry Department is the key department, whose agency and determination is critical for success. These are the Direct Duty-bearers. The recommended roles and responsibilities of some of them are described in Annex 20.

Government stakeholder engagement is limited by budget availability. Co-financing in kind provides for staff salaries, but government operational funding is lacking. Multiple individuals at national, provincial, district and local level have engaged actively, when project funding is available to cover their costs. With the exception of a few instances of district level monitoring, government do not independently engage with the community stakeholders. This is at odds with their critical role at exit. During the remaining project period, it may be advisable for each partner to work out their exact roles and responsibilities, to identify the appropriate intervention level and to detail their commitments in the exit strategy, including budgets, which partly will need be covered by Government funding. The Forestry Department will need support for independent field monitoring (Recommendations 2, 11).

Indirect duty-bearers. In addition to the government actors currently explicitly involved in project implementation, technical and management oversight, there are the Government Departments whose cooperation is needed for the institutionalization of change, for mainstreaming gender responsive CFM, becoming embedded in their respective institutions and offices. They include representatives from multiple sectors, civic society and ministries, among whom are several duty-bearers whose support will be critical. Below is listed significant partners and their role in removing barriers, facilitating the completion of on-going processes and ensuring post-project sustainability.

- Ministry of Justice (revision of Statutory Instruments to remove barriers (see C2); learning lessons for the harmonization of Forest and Wildlife Acts; and integrating models and knowledge management products into the process of revising forestry subsidiary legislation).

- Ministry of Local Government and Rural Development (integration of CFMA plans and ILUPs in DIDPs around 2030).

- Ministry of Finance (post-project GRZ budgeting).

- Ministry of Lands and Natural Resources (harmonization of land registry, land use and sustainable land management initiatives).

- Ministry of Chiefs and Traditional Affairs (awareness on gender-responsive CFM for mainstreaming and upscaling and coordinated recognition of CFM across Zambia’s different traditional authorities).

- House of Chiefs (disseminating ECCLE findings among traditional authorities).

- Gender Division, Office of the President (awareness on and promotion of gender-responsive CFM models for mainstreaming and upscaling across Zambia).

- Ministry of Community Development and Social Service (effective representation of the needs and interests of all gender and marginalised groups in CFM across Zambia); and

- NGOs and/or other civil society organisations for monitoring and advocacy gender responsive CFM across Zambia.

Action to strengthen duty-bearer ownership over outputs and outcomes necessary for long term impact and is best included in the project exit plan. The Forest Department (Director and National Coordinator) are best placed to update the stakeholder engagement plan and submit it to the Project Steering Committee for approval as part of the ECCLE project exit strategy and sustainability plan (Recommendations 11, 13).

UNEP Matrix Review Criteria Rating– H6: Country ownership and drivenness

The sub-criteria prescribed by the UNEP matrix relevant to rating country ownership and drivenness are: the number of government ministries and public sector agencies that took a leadership role in three or more specific ways, ranging from providing co-financing, initiating complementary activities, endorsing project results, advocating for change to achieve higher level results and/or provided strategic guidance to project delivery. The rating has only been applied to those stakeholders that are currently engaged with the project, the Direct Duty-bearers.

Rating for Criterium H6: Country ownership and drivenness – Moderately Satisfactory

#### H7 - Communication and public awareness.

The project has supported effective communication of learning and experience sharing between project partners and interested groups as exemplified by the Knowledge Management Reviews and regular showcasing of the project within Government during its lifespan in the form of events (e.g. project launch) and field visits for direct duty bearers (e.g. PTC and PSC, GEF OFP). Public awareness events include participation in national celebrations (e.g. Forestry and Environment Day) at local and provincial level.

Shortcomings include the publication of the envisaged Quarterly Newsletter and the establishment of a knowledge hub, which did not materialise as planned. Reaching target groups have been less than optimal, e.g. meeting the differentiated needs of gender or marginalised groups. Feeback channels were enhance as the Provincial Focal Point came on board in 2024 and a formal Grievance Mechanism was established in 2025, whose efficacy remains to be confirmed. The project is advised to include a communications strategy in the Exit plan (recommendation 13).

Rating for Criterium H7:  Communication & Public Awareness - Moderately satisfactory

## V: Conclusions

Planning of the ECCLE project was initiated a few years after the 2014 Forestry Policy and 2015 Forest Act of Zambia made possible sustainable forest management through local participation. Communities could be empowered to manage forests through community forest management groups (CFMGs). The new Policy and Act were received with much anticipation and several projects were started, among them the GEF 5/UNDP initiatives aiming at effective protected areas management and the Decentralised Forest and Other Natural Resources Management Programme (DFNRMP) which ran from 2015 to 2018, piloting CFM in three districts in Northwestern and developing subsidiary CFM legislation. The ECCLE project was initiated in 2019, building on, and leveraging the work of previous initiatives, consolidating and mainstreaming sustainable forest and natural resource management, with a promise of delivering the next generation community forestry, under the auspices of GEF-7.

The Project Document holds high expectations towards the ECCLE project (ProDoc, p. 62). The objective was two-pronged: to develop ‘tested, proven systems of community management of forests and other natural resources that are ready for mainstreaming’ (strategic objective), and to establish and strengthen community based sustainable management of forest landscapes and provide improved livelihood opportunities for targeted forest-dependent rural communities in Northwestern province (specific objective).

The project start-up in 2021 coincided with several external challenges and the project came to a slow start. By mid-2022, however, project staff (less National Coordinator) were in place and by early 2023, activities had commenced in earnest in the three project sites. Naturally, the project team focused on getting the activities off the ground in the three project sites: Kelongwa Kamanana (Kasempa); Ntambu (Mwinilunga) and Kamikolo (Kalumbila). In each site, various difficulties were encountered, as is to be expected when the local community needs to become aware of, assess, adopt and embrace a new initiative.

At the end of 2024, project progress against benchmarks good at all three sites, to be attributed to the hard work of the project team and the implementation partners on the ground. Much training and capacity-building had taken place, Community Forest Management governance structures had been established, and the project was working hard to introduce community-based forest enterprise in all three locations. Initial productive investments had been made, and project site infrastructure was being built.

At strategic level, however, progress was disjointed and lagged behind. The project rationale, as stated in the Project Document, is overly optimistic, does not specify a clear strategy for how to turn practical experiences into model recommendations, and the timeline for how to bind different strands of activities together was unclear. Multiple delays at start-up confused the sequencing of inputs and prevented outputs learning from each other. The procedure for adopting critical deliverables (e.g. consultant reports) was removed from the Project Technical Committee and handed to the Forestry Department, which already was struggling with meeting ECCLE time requirements and staff needs.

The review of good practice in community forestry commenced in 2024, but the Knowledge Management component activities (Output 1.4) were tangential to the processes of establishing CFM governance structures and did not learn lessons from the Gender Analysis. The Subsidiary Legislation component (Output 1.5) was suspended in its entirety. The delay in producing the two foundation documents, the Socio-Economic and Bio-Physical Assessment (2024) and the Gender Analysis and Gender Strategy and Action Plan (2023) caused baseline information and gender input to become available only after critical CFMG structures and procedures had been established, confused the sequencing of inputs and prevented outputs learning from each other.

The Mid-Term Review undertaken between April and September 2025 has highlighted the achievements and challenges of the project.

  - At local and provincial level, the next step for the ECCLE project is to consolidate activities and work towards developing an exit plan for the project and sustainability plans for each site. Major challenges will be to find ways of consolidating Component 2 (natural resourced based community enterprise) and compensating for the loss of expected household level economic benefits from Component 3 (sustainable agriculture). (Recommendations 8, 9).

  - At strategic level, the project will need to come to terms with not being able to deliver on the expectations of CFM modelling for mainstreaming. A recommendation is placed for Project Management (PIU/IA/EA) to engage with the Forestry Department and Project Governance Bodies (PTC/PSC) to convene a strategic review to discuss the implications of non-delivery on the project premised assumptions, the financial drivers underpinning the CFM model (Recommendation 3). A second recommendation is place for the Knowledge Management Component to be re-focused towards more effectively learning lessons from ECCLE implementation and feeding them to the project governance bodies for discussion. The underspend of Output 1.5. provides the project with additional resources towards this (Recommendation 7).

#### ECCLE Main Strengths and Weaknesses

The main strengths of the ECCLE project are its alignment with Zambia’s forestry, natural resource and sustainable land management policies and Government efforts. The implementation approach builds on successful draft CFM models developed by previous projects. The energetic and robust project implementation team – PIU, TSU and implementation partners KCF, TFL and WLCP - deliver outputs to beneficiaries successfully. Problems encountered on the ground are those to be expected as part of the process, most of which have been resolved through PIU/PTC adaptive management. At project area level, the establishment of CFMG governance and business structures has been impressive during the past two years.

The main weaknesses of the ECCLE project derive from the unrealistic expectations contained in the design that were not attended to during the project appraisal and inception phase and therefore strained the delivery of project management services. External challenges have impacted negatively, e.g. the 2024 drought and the 2021 Government restructuring after elections. The Forestry Department capacity to co-create project leadership has fallen short of expectation. Administrative inertia, e.g. protracted engagement of implementation partners and contracting of sub-awardees, has delayed implementation. Whilst the project has made a gallant effort to catch up with activities, process consolidation will take time. The project is approximately one year behind. The delays have impacted negatively on the sequencing of activities and synergies. E.g. gender recommendations and findings from forest inventories became available only after CFM governance structures had been put in place. Fortunately, this may be corrected at local level. Sadly, the cumulative impact of design weaknesses and delays, primarily affects the strategic goals (model development, mainstreaming of CFM), which will not be attained during the project lifespan.

A summary of project successes and shortcomings are found in Table 10. The report contains multiple recommendations for the future ECCLE course correction through review and adjustment of localised and strategic goals by Project Management (PIU/IA/EA) together with Project Governance Bodies (PTC/PSC) (Recommendations Section VII).

Table 10. Summary of ECCLE project successes and shortcomings

| Strengths | Weaknesses |
| --- | --- |
| Attuned to national priorities, responding to Forest Policy and Act, supports Government efforts | Shortcomings in original project design and appraisal (not attended to during Inception) |
| Approach builds on draft CFM model developed by previous projects well suited to local circumstances (e.g. DFNRMP implementation model and draft subsidiary legislation) | Substantive delays in project mobilization and start-up (caused by factors outside the control of the Project Implementation Team. IA and EA to learn lessons). |
| Implementation partners on the ground (WLCP, TFL, KCF) provide good quality on-the ground facilitation and supervision | Project decision-making structures operational only two years after project start, stakeholder roles and responsibilities not clear |
| Communities very interested in intervention, in particular its potential to relieve poverty. Strength which can turn into weakness if project is not able to deliver on benefits. | Administrative inertia. Delays and persistent problems with slow pace of contracting, distorted progress, causing vital process inputs not to be available in a timely manner. |
| Hard-working and energetic technical project teams @ PIU / TSU and @ project area level (implementation partner field facilitators) | Implementation arrangements: Generally good dialogue and synergies compromised by (i) sequencing of activities distorted due to delays; (ii) ineffective mechanisms for adoption of reports; (iii) delay in integrating lessons from the field, reporting findings and KM products into model development. |

#### Summary Statement: Overall project performance

Overall, although much delayed in start-up, the implementation of the ECCLE project got underway briskly in 2022. The project is aligned with Zambian Government, UNEP and GEF priorities, it is well managed and is progressing as per work plan. At local level, the beneficiaries, the local communities are engaged and demonstrate ownership and willingness to embrace community forestry. Substantive efforts have been made to integrate gender equality and tangible achievements are visible on the ground. At strategic level, weaknesses in project design have impeded progress and the project will need to review some of the fundamental underpinnings of CFM modelling and mainstreaming. Provided the project ensures timely closure through strategic consolidation and phased exit, the proposed consolidation of activities, risk and strategic reviews and sustainability planning are undertaken expediently, the ECCLE project stands a fair chance to achieve a successful outcome, contribute significantly to community forestry development in Zambia and its expected long-term impact.

As such this project is rated as moderately satisfactory. Answers to UNEP’s strategic questions and a summary of the review findings and ratings can be found in tables 11 and 12 below.

Table 11. UNEP Key Strategic Questions

UNEP Strategic Questions

- What evidence exists indicating that the project is contributing to raising community awareness on and interests in forest management? (ToRs, p. 35)

The ECCLE project presents substantive evidence of growing community awareness on and interest in forest management in the project areas. Through consolidating achievements and dissemination of ‘good practice’ through the Knowledge Management component, the project has the potential of greatly increasing awareness and promote the adoption of CFM and SFM in Zambia. At 2/3 project time, with the possibility of a timely project closure through strategic consolidation and phased exit, the robust project is fully capable of addressing issues of activity consolidation, Forestry Department ownership, effective Duty Bearer engagement, and resolution of strategic issues such as CFM financial viability.

- What evidence is available that the project is contributing to improving community livelihoods through assisting them to develop business and enterprise investment plans? (ToRs, p. 35)

Component 2: The ECCLE project presents fair evidence that CFMG business and enterprise investment will contribute to improving community livelihoods. As the component has been in operation for two years, business and investment plans have been prepared, but effective implementation is only just starting, and it is premature to expect results on the ground. Provided a time project closure through strategic consolidation and phased exit is ensured, and the Component is able to consolidate efforts, selecting only financially viable value chains for development, and developing sustainability strategies, the long-term likelihood is substantive of CFMG business and enterprise contributing to community livelihoods. However, in the short term, there is need to develop household enterprise and small-scale business to have substantive impact on the livelihood and well-being of local communities in the project areas, and women and vulnerable groups in particular.

- What evidence is available that the project is contributing to the promotion of sustainable and climate smart smallholder agricultural technologies and practices by farmers living in the project areas? (ToRs, p. 35)

Component 3: The ECCLE project presents some evidence that the project is making an impact on household livelihoods and income in Northwestern Province. The project is doing valuable work creating awareness off and in introducing alternative production technologies for climate smart, conservation and sustainable agriculture in the project areas. However, attendance records do not show evidence of reaching the expected number of farmers, mostly due to economic reasoning: Farmers do not consider the proposed CSA/CA technologies do not constitute a financially competitive alternative to conventional agriculture. The 2024 drought also impacted negatively. Provided a timely closure through strategic consolidation and phased exit is ensured, the project may through training and extension activities and the introduction of CSA technologies via market access for specific products, present farmers in Northwestern Province with an option of somewhat more sustainable agriculture practices. However, as an element to the self-financing CFM model, the introduction of CSA/CA sustainable agriculture practice will only be marginally relevant.

Table 12. ECCLE Project Performance Rating (full version, as per UNEP 2023 criteria ratings matrix)

| Criterion | Assessment | Rating |
| --- | --- | --- |
| A: Strategic Relevance | Aligned to UNEP and GEF strategic priorities. Very relevant to national needs, with the potential to support policy renewal. | S |
| B: Quality of Project Design | Several good design features, regrettably undermined by challenging timelines and a few untenable project premises | MS |
| C: Effectiveness | Due to delayed start, project now at mid-point. | MU |
| C2 Availability of Outputs | Delayed start, but rapid progression in two components from 2023, showing good quantitative deliverables. With a timely closure through strategic consolidation and phased exit, the project is likely to consolidate results and enhance sustainability. The poor performance of component 3, sustainable agriculture, brings down the average performance. | MS |
| C3 Achievement of Outcomes | At 2/3 implementation point, the project is yet to demonstrate evidence of outcome-level results. Current outputs are relevant and realistic to the situation on ground, necessary but not sufficient for reaching outcome levels. CFMG governance and business structures need to mature and viable sources of household livelihood income other than sustainable agriculture need to be groomed for self-financing to materialize. | U |
| C4 Likelihood of Impact | ECCLE’s contribution to long-lasting impact is largely dependent on the replicability and scaling-up of the CFM model being developed. Whilst likelihood of impact is good in project sites, provided achievements are consolidated and a sustainable exit co-created the likelihood of impact through modelling for mainstreaming is far less. At 2/3 implementation point, the likelihood of impact little. However, with focused consolidation and strategic re-direction, during the remaining project period, this trajectory could improve. | MU |
| D: Financial Management | Adherence to policies and completeness of financial information satisfactory | S |
| E: Efficiency | Cost-effectiveness not rated. Rating of timeliness/delays, their impact on at least one group of stakeholders, and sequencing of project activities and events unsatisfactory. | U |
| F: Monitoring & Reporting | The project monitoring and reporting system is performing well, with some shortcomings identified for correction. | S |
| G: Exit and Sustainability | The project has initiated the process of drafting a sustainability strategy and exit plan. It is recommended that an exit plan is prepared for the project, but that sustainability plans are prepared also for each CFMG and implementation partner. This is likely to happen, and the changes that socio-political, financial and institutional issues are addressed are good. | ML |
| H: Other Factors | The overall performance of the project is good. | S |
| H1: Project Inception | Project mobilisation was slow due to institutional and administrative challenges. Project design shortcomings were not addressed. Project activities start-up delayed by between six and 14 months. | MU |
| H2: Project Management | Overall project management has been good. Implementation partner performance ranges from moderately satisfactory to satisfactory, Areas of improvement identified for all implementation partners. | S |
| H3: Stakeholder Participation | Stakeholder engagement has been good. Clarification on duty bearer roles and responsibilities needed as the project is coming to an end. | S |
| H4: Gender | Project approach to gender pro-active and. Appropriate consolidation of strategies; further modelling elements of gender-responsiveness in CFMG; and innovative use of gender-active strategies ('gender champions’, women’s committees) will enhance achievements further. | S |
| H5: ESS | Safeguarding considerations at a good level of quality, detail and consistency. | S |
| H6: Country Ownership | Forestry Department cannot mainstream gender-responsive CFM in isolation, the support from other Duty Bearers is needed. Not all duty-bearers are aware of their role and responsibility. An updated stakeholder engagement plan is needed for sustainability. | MS |
| H7: Communication | The project has only partially delivered on planned project communication outputs. On the other hand, the project has made good use of other opportunities to show-case achievements and share lessons learnt. The exit plan should include a revised communications strategy for mainstreaming. | MS |
| Overall Project Rating at 2/3 implementation point | Calculated as a simple average of the rating for each criterion (A-H) = Moderately Satisfactory | MS |

## VI: Lessons Learned

Key lessons learnt during the Mid-Term Review are listed below in Section VI.

Lesson Learned 1: Revision of the Theory of Change. The ECCLE Theory of Change (TOC), as presented in the Project Document, is not consistent with UNEP requirements. This prompted the preparation of a revised TOC at Review Inception during Inception, consultations with the project team and stakeholders, and a revised TOC at Review as presented in Figure 3 in this report. Although a relevant exercise, the timing was awkward. Conducted at 2/3 implementation point, all the disadvantages of the old ToC had already played out in the project. It had increased project M&E reporting and performance tracking; it sub-optimally supported project management and risk assessment; and, diverted MTR resources to looking at ‘past problems’, rather than examining ways of providing constructive future formative assessment. Stakeholders further considered the revision a ‘futile’ exercise of little value to the project. The Implementing Agency, UNEP, is advised to consider better timing of the revision of a Theory of Change, to an earlier stage in the project cycle.

Context/comment: The UNEP Evaluation methodology tasks the Mid-Term Review to revise the project Theory of Change and, if necessary, rephrase indented results (outputs, outcomes, intermediate states, impact) in line with UNEP results definitions and to create a TOC at Review diagram consistent with UNEP result levels. This was done by the ECCLE Review Consultant. In the process it was observed that the Results Framework indicators are sub-optimal. A recommendation has been made for their adjustment (Recommendation 4). More appropriate would be to undertake the revision of the ToC earlier in the project cycle and at the same time revising sub-optimal Results Framework indicators (if relevant). Appropriate junctures would be, e.g. (i) in conjunction with the appraisal of the Project Document; (ii) During the Project Inception Phase (initiated as a request by the IA); or (iii) At the very latest, in the first update of the M&E Plan, at which point in time, drivers and assumptions would benefit from an update resulting in improved risk reporting, and more targeted outputs and deliverables.

Lesson Learned 2: Timing of the MTR review. The ECCLE project supports long-term change in forest management regimes, through the introduction of new management practices; the creation of new governance structures; and finding new ways of working under new policy, legal, institutional and regulatory arrangements. The processes are bureaucratic and prone to challenges. The process will benefit from regular opportunities for check-in, review and re-alignment. To optimally support the process, it is helpful to strive to avoid delays and to adhere to established procedures. The Implementing Agency, UNEP, is advised to adhere to appropriate timing of the Mid-Term Reviews in the execution of the project cycle, to optimise its benefits.

Context/Comment. The Mid-Term Review was commissioned to start in April 2025, three years and 7 months after project start. With only one year of project time remaining at the end of the MTR period, the Consultant encountered challenges in translating findings into appropriate and practical recommendations that would help the project consolidate achievements. Even assuming additional time for structured consolidation and transition, formulating meaningful recommendations proved unnecessarily difficult, with a limited time for their implementation.

Lesson Learned 3: Human Rights and Gender Equity. Human rights and gender equity are most effectively integrated when they are embedded from the outset in the project design and then translated into concrete governance, participation, and accountability mechanisms. Moving beyond policy statements to practical tools – such as gender analyses, inclusive decision-making structures, targeted capacity building -strengthens legitimacy, reduces elite capture, improves trust amongst stakeholders, and ultimately enhances sustainability and development outcomes. The Implementing Agency, UNEP, is advised to systematically mainstream human rights and gender equity across the full project cycle by early analytical work, enforceable inclusion measures within governance and enterprise structures, and adaptive M&E systems with sex-and vulnerability- disaggregated indicators, while maintaining senior-level leadership commitment to ensure these gains are institutionalized beyond the project lifespan.

Context/Comment. The project is implemented in a context where persistent gender inequalities and unequal access to rights, resource, and decision-making limit the ability of women, youth, and marginalized groups to benefit equitably from natural resources management and livelihood opportunities. Human rights and gender equity are therefore central to the project rationale, ensuring inclusive participation, fair benefit sharing, and accountability.

## VII: Recommendations

The Mid-Term review process yielded some three dozen normative observations, mitigation measures and technical recommendations. They were discussed with the project team, presented to the stakeholders as preliminary findings, and deliberated as part of the first draft review and subsequent validation process. They have been summarized as fifteen management recommendations and presented to the project implementation unit for review and action.

| Recommendation # 1: | Ensure Timely Project Closure through Strategic Consolidation and Phased Exit |
| --- | --- |
| Challenge/ problem to address: | Challenging timelines pose risk for overall sustainability. The incremental cost-reasoning scenarios are over-optimistic. With the remaining implementation period, priority should be placed on testing, proving and validating models for CFM mainstreaming; supporting governance structures and community business to reach minimum operational viability; addressing recovery needs following the 2024 drought; and managing risk through the development of medium-term sustainability strategies. Progression towards outcomes and likelihood of impact will depend on focusing available resources on consolidation rather than expansion of activities. Not all components need to close simultaneously, and a staggered closing down should be considered, whereby completed outputs are gradually phased out while critical processes receive targeted final support. Two components require particular prioritization during the remaining period: the development of community enterprise (Output 2), and the adoption of climate smart agriculture (Output 3). The final implementation cycle should be aligned with no more than agricultural season, 2026, to secure operational learning, consolidate results, and ensure continuity arrangements are in place before project completion. Should project resources prove insufficient, a shorter, but well-sequenced phasing-out strategy should be implemented (See Criterion E). |
| Priority level: | High |
| Type: | Project Design |
| Responsibility: | PIU/FD/TNC/UNEP |
| Time-frame: | Approval by March 2026 |

| Recommendation # 2: | Strengthen Project Governance |
| --- | --- |
| Challenge/ problem to address: | The project will need to make important decisions about the future, including revisions (Recommendation 3) and strategic adjustments. The decisions are to be made by the Project Governance bodies, with strong input from the Forestry Department (FD), Implementing Agency UNEP and the Executing Agency TNC. The PIU needs the full support from the implementation partners to propose and facilitate decisions for the ECCLE project to optimise its impact. To boost strategic adaptive project management (criterion C5), the MTR found room for improvement in key partner support to project implementation, the Forestry Department, the Implementing Agency (UNEP) and the Executing Agency (TNC). Table 10 summarizes shortcomings. Other specific recommendations are scattered in the report, include the revised ToRs for the National Project Coordinator (FD); recognition of the PSC and PTC formal composition; PSC and PTC Terms of Reference to be consolidated; Committee members role and responsibilities to be clarified; All Meeting Minutes to be signed and archived; implementation partner contracts and agreements need to be signed and archived. Executing and Implementing Agency to actively support FD in consolidating project governance. FD to increase ownership of and engagement. Suggestions for detailed action found in Annex 20. |
| Priority level: | High |
| Type: | Project Management |
| Responsibility: | FD/UNEP/TNC/PIU |
| Time-frame: | Completed by December 2025 with report back to PSC in 2026 |

| Recommendation # 3: | Undertake Strategic Review and Course Correction |
| --- | --- |
| Challenge/ problem to address: | The project design contains weaknesses and unrealistic expectations, which were not addressed during appraisal, mobilisation, inception. Weaknesses include challenging timelines, which pose risk for overall sustainability, and the over-optimistic incremental cost reasoning scenarios. The project will not be able to fully attain the expected results, as governance structures take long to mature, profit-turning community business take long to establish, and the adoption of sustainable agriculture takes several years. Self-financing principles will not be demonstrated during project life span. The project strategic goal, the development of CFM models ready for mainstreaming unlikely to materialize during project lifespan. The project must now come to terms with the design flaws. The MTR recommends a strategic review for adjusting project targets; a timely closure through strategic consolidation and phased exit to allow for key processes to mature; and guide the project in developing exit and sustainability plans to guide the post-project collaboration. MTR recommends that the PIU together with the FD commissions a strategic review with the intent to advise the project governance bodies and the Zambian Government on a course-correction for the ECCLE project and beyond. The strategic review would feed into the on-going PLIR development. |
| Priority level: | High |
| Type: | Strategic Development |
| Responsibility: | PTC / PSC / UNEP |
| Time-frame: | Completed by January 2026. Recommendations to be discussed by PSC February 2026. Revisions to be included in project timely closure through strategic consolidation and phased exit strategy. |

| Recommendation # 4: | Adopt Revised Theory of Change, Drivers and Assumptions. Reconsider Results Framework and Outcome Indicators |
| --- | --- |
| Challenge/ problem to address: | As per UNEP requirements, the MTR has updated the project theory of change (rToC) and revised the drivers and assumptions. The project is advised to adopt the revisions and to amend the project design accordingly. During the MTR, the project expressed concern about the adequacy of higher-level indicators to track progress towards outcomes. The MTR shares this concern: Current indicators do not allow for tracking incremental progress, rendering measurement of progress towards outcomes difficult. Furthermore, some indicator results may end up unattainable, not materialising during the project lifespan at all. The project would be well served with more nuanced indicators, that would also better support the development of sustainability plans. UNEP is advised to take the lead on a review the Results Framework and consider revisions. If such are not found feasible, the use of complementary proxies to allow for tracking relative progress towards outcome levels is to be considered. |
| Priority level: | High |
| Type: | Project design |
| Responsibility: | UNEP / PIU / FD / TNC |
| Time-frame: | Completed by December 2025. Revisions to be discussed by PSC February 2026 and included in project timely closure through strategic consolidation and phased exit strategy. |

| Recommendation # 5: | Financial and Administrative Documentation |
| --- | --- |
| Challenge/ problem to address: | No record was found of financial documentation required by the donor as missing, inaccurate, incomplete or unavailable. (Criterion D). However, the Executing Agency is encouraged to tighten contracting procedures in order for administration not to slow down the pace of implementation. Forestry Department and PIU are encouraged to review the accuracy of co-financing reporting. One co-financier, WWF Zambia, did not report any expenditure or activity in the project area, and their removal should be considered by the Project governance bodies and the decision recorded by the Project Steering Committee. |
| Priority level: | Moderate |
| Type: | Project Finances |
| Responsibility: | GRZ / PIU / TNC / UNEP |
| Time-frame: | Completed by December 2025, revisions to be submitted to PSC for approval in February 2026. |

| Recommendation # 6: | Consolidation of Community Forestry Governance (Component 1) |
| --- | --- |
| Challenge/ problem to address: | The Project Component 1: Sustainable Forest Management embraced by local communities and mainstreamed in local development plans has made good quantitative progress so far. The next step is qualitative consolidation, re-creating linkages with key inputs and synchronizing gender-responsiveness and the findings from the forest assessment and knowledge management products with the CFMG governance tools in readiness for mainstreaming. To bolster community ownership, awareness-raising, training and capacity-building at CFMG level to continue throughout the project lifespan. (Recommendation 10). Detailed exit strategies to be developed together with MLGRD and relevant planning institutions for the continued process of integrating CFM processes into the District Development Plans (around 2028-2030). Role of District Teams to be clarified. |
| Priority level: | High |
| Type: | Work Planning, Sustainability Planning |
| Responsibility: | TSU/PIU/Implementation Partners (KCF, TFL, WLCP) |
| Time-frame: | Work Plans implemented from 2026. Recommendations to be discussed by PSC February 2026. Revisions to be included in project timely closure through strategic consolidation and phased exit strategy. |

| Recommendation # 7: | Refocus Outputs 1.4 Knowledge Management and 1.5. Subsidiary Legislation in support of CFM model development and mainstreaming |
| --- | --- |
| Challenge/ problem to address: | To effectively support the ECCLE project objective and strategic objective, the two outputs, 1.4. Knowledge Management and 1.5. Subsidiary Legislation will need re-focusing and replanning in order for these activities to optimally support the consolidation of lessons learnt by the ECCLE project, the process of creating viable models and demonstrable practice, their transformation into a draft ‘model elements’, peer review, adoption and subsequent support to Government PLIR development. It is vital that deliverables are appropriated, that they have an easy application by CFM actors. Revision to follow Strategic Review and to optimally support effective learning of lessons and communication of project results. Activities are best aligned to the exit plan and CFMG sustainability plans. |
| Priority level: | High |
| Type: | Project design |
| Responsibility: | PIU/FD/UNEP |
| Time-frame: | Revisions by December 2025. Work Plans implemented from 2026. Recommendations to be discussed by PSC February 2026. Revisions to be included in project timely closure through strategic consolidation and phased exit strategy. |

| Recommendation # 8: | Consolidate CFMG Business and Support Household Enterprise (Component 2) |
| --- | --- |
| Challenge/ problem to address: | Component 2. Communities empowered through gender-responsive community forest management (CFM) to manage forest resources, engage in sustainable FNRM-based enterprise and improve livelihoods has made good quantitative progress. During the remaining project period, qualitative concerns need to be addressed through refocusing. Still very much in a startup phase, the component needs substantive support from project management, partners and stakeholders to succeed. Key considerations in consolidating CFMG business will be (i) adopting a strong focus on economic viability, (ii) ascertaining that commercial utilization of all value chains adopted for development are ecologically sustainable; (iii) taking a two-pronged approach to planning, looking at how to develop viable natural resource-based enterprise at both community and household level. (iv) reviewing options for developing gendered pathways to group and entrepreneurial business establishment, considering the particular constraints of women in business. More detailed recommendations found elsewhere in the report and in earlier technical recommendations. For Component 2 to show tangible results, a structured consolidation phase and careful forward planning will be required, including preparation of the Exit Plan and the CFMG Sustainability Plans. For at least 5-8 years, CFMG business will need to rely on financing from Corporate Social Responsibility Programmes financing for CFMG business ventures to attain viability. CSRP partners should be engaged as partners in developing CFMG Sustainability Plans. |
| Priority level: | High |
| Type: | Work planning, sustainability planning |
| Responsibility: | TSU/PIU, Implementation Partners (KCF, TFL, WLCP) |
| Time-frame: | Revisions by December 2025. Work Plans implemented from 2026. Recommendations to be discussed by PSC February 2026. Revisions to be included in project timely closure through strategic consolidation and phased exit strategy. |

| Recommendation # 9: | Climate Smart / Sustainable Agriculture (Component 3) |
| --- | --- |
| Challenge/ problem to address: | Component 3. Productivity, household income and climate resilience from sustainable gender-responsive agricultural practices improved in CFM communities. Already at this point in time, it is clear that Component 3 will not be able to bring forth the expected alternative source of livelihood envisaged, and the project, supported by the project governance structures and the IA and EA, is encouraged to look for other ways of supporting communities generate income (see Recommendation 3). The most immediate alternative is to broaden focus in component 2.2 to embrace also household enterprise, in particular that which is accessible to women and youth (Recommendation 7). In terms of taking Component 3 forward, the current set of on-ging activities is best completed diligently, making the most of opportunities to train farmers in the project areas in sustainable agriculture, document and disseminate them for the CFM/CBNRM community to learn from this valuable experience. (i) The Department of Agriculture and ZARI complete the training programme as comprehensively as possible; (ii) Market linkage activities are profiled more clearly in terms of their contribution to CSA; (iii) A Lessons learnt overview is undertaken to document the experiences and that this review is presented to the PSC and PTC for discussion; (iv) The review is circulated among KM products, so as to share not just “good practice”. - Time and resources allowing, the project may also consider investigating to what extent the current market-linkage approach (facilitating buyers access to farmers for selected products, e.g. beans and honey) could be used as a platform for developing “climate smart agriculture out-grower schemes” as a more attractive platform for the introduction of CSA and SA in rural communities in Zambia. This is demanding in terms of resource and time and would be best done in a different project / by other players. However, the private sector implementation partners, who have a long-term engagement, may be interested in developing this option as part of their other CSRP programmes. If adopted, the ECCLE project may generate some data for such initiatives that will feed into the exit plan and sustainability strategies. |
| Priority level: | Medium |
| Type: | Work Planning, Sustainability Planning, Project Design, Lessons Learnt |
| Responsibility: | DoA, ZARI, Implementation Partners (KCF, TFL, WCLP), TSU/PIU, FD |
| Time-frame: | Work planning done by December 2025. |

| Recommendation # 10: | Strengthening Community Forest Management at local level for sustainability |
| --- | --- |
| Challenge/ problem to address: | The rationale of the ECCLE project on incremental cost reasoning scenarios and the assumption that self-financing models can be found, upon which the sustainability of CFMG rests. The MTR has cast doubts on viability of several basic premises; suggest that community business will take long to mature and argues that activities under component 3 will not bring the expected household level benefits. At project and policy level, the recommendation is for a Strategic Review (# 3). At community level the recommendation is for utilizing the remaining project and resources towards strengthening the community members and the CFMGs as capable actors. Meaningful activities include investment in training and capacity-building, widening of the membership, support to expanding the role of gender champions, focusing on economically viable business, etc. elaborated by the review. It is proposed that these efforts are consolidated in a Sustainability Plan, developed for each project area, carefully elaborating what will be done before the end of the project, and what activities need to be carried over to the CSR partners. The TSU/PIU should see to it that agreements and contracts are signed between CFMGs and Implementation Partners, before project closing. The key output are the training and capacity-building activities, sustainability plans, and key investments. |
| Priority level: | Medium |
| Type: | Work Planning / Sustainability planning |
| Responsibility: | PIU/TSU/FD, Implementation Partners (WLCP, KCF, TFL) |
| Time-frame: | By December 2025, incorporated into Work Plans |

| Recommendation # 11: | Stakeholder roles and responsibilities |
| --- | --- |
| Challenge/ problem to address: | Forestry Department cannot mainstream gender-responsive CFM in isolation, the support from other Duty Bearers is needed. Not all duty-bearers are aware of their role and responsibility. Updating the stakeholder engagement plan will support sustainability planning. The review has at several junctures (Criteria B, C, C5, H3, H6) recognized the important role stakeholders play for ECCLE success. In particular, the direct duty-bearers (e.g. Forestry Department); the implementation partners (i.e. KCF, TLF, WCLP); and the project governance bodies (PSC, PTC) play a very important role. The review, however, has also highlighted the role of indirect duty-bearers (e.g. MLGRD); different members of the local communities; and future duty-bearers (e.g. Ministry of Finance) post-project. For sustainability, it is recommended that an identification of key post-project stakeholders is undertaken, their strengths assessed, their role and responsibilities clarified and commitment verified. (See also Recommendation 2). |
| Priority level: | Medium |
| Type: | Sustainability planning |
| Responsibility: | PIU / FD together with PTC and PSC |
| Time-frame: | As part of exit and sustainability planning for CFMGs in 2026 |

| Recommendation # 12: | Gender and vulnerable groups |
| --- | --- |
| Challenge/ problem to address: | The ECCLE project is unique in Zambia in its efforts to support a gender-responsive strategy for CFM and other local level forest and natural resource management in Zambia. The project is encouraged to try to consolidate achievements, to link project level activities back to gender mainstreaming, project management and component implementation, and optimally learn lessons for CFM modelling and practice that may be passed on as means and mechanisms suitable to CFMGs for implementation. Examples include mechanisms for how CFMGs may address inequality (e.g. quotas in leadership and representation, gender-specific intervention strategies). Satisfaction surveys may generate an effective baseline for CFMGs to measure future progress and impact. Focal group discussions at local level may support the integration of lessons into CFMG operations, e.g. how barriers to participation are best removed and opportunities may be harnessed. In developing further options, the project is well served to work together with gender champions, women’s committees, progressive female entrepreneurs and farmers (women who join the CSA farmer field schools). To harness the full advantage of gender work done, it is recommended that resources are allocated to “gendering” knowledge management products, CFM models, and CFMG sustainability plans. |
| Priority level: | High |
| Type: | Cross-cutting |
| Responsibility: | PM / PIU / TSU |
| Time-frame: | Develop gendered exit plan by end 2025. Thereafter, staggered over work planning, sustainability planning and implementation |

| Recommendation # 13: | Strategies and Plans for Exit and Sustainability |
| --- | --- |
| Challenge/ problem to address: | The ECCLE project must put in place plans and strategies for how to bring the project to an end in a way that optimises on the support to beneficiaries and plans for how project activities will be sustained in project areas; and how lessons learnt and “CFM models” will be packaged for stakeholder use. It is recommended that the project considers two levels of plans: - an exit plan for the project and its stakeholders. - sustainability plans for each CFMG, negotiated with their CSR partner, covering a time-span that will carry them to institutional and financial sustainability. Issues of enhanced risk management and mitigation will need attention. (See updated risk assessment Annex 11 and Annex 19). |
| Priority level: | High (exit plan), Moderate (Sustainability Plans) |
| Type: | Sustainability Planning |
| Responsibility: | PIU/TSU/FD with support from UNEP/TNC and IPS (WLCP, KCF, TFL) |
| Time-frame: | Exit plan by March 2026. Sustainability plans by December 2026. |

| Recommendation # 14: | Monitoring and Evaluation |
| --- | --- |
| Challenge/ problem to address: | The review identified a few issues warranting attention in project record keeping, monitoring, evaluation and reporting, including establishing baseline data for sustainability planning; use of satisfaction surveys to capture project progress among vulnerable groups and to generate data against some key indicators; to improve the linking of M&E data with adaptive management reviews; and revise outcome indicators (see criterion F and Recommendation 4) in order to improve tracking of progress and support sustainability planning. Additional budget may be needed for some of these activities (i.e. surveys). Together with the Forestry Department there is also needed to produce signed minutes from PSC and PTC meetings for archiving with EA and FD Registry. Generally, the project is advised to improve on document identifiers for deliverables (date, author, revisions) and planning for their dissemination as relevant. |
| Priority level: | Medium to high |
| Type: | Project Management |
| Responsibility: | M&E Unit/PIU/FD |
| Time-frame: | Update M&E Strategy by December 2025 in order to enable other recommendations and include activities in Work Plans implemented from 2026. Report back to PSC. |

| Recommendation # 15: | For the consideration of the Terminal Evaluation |
| --- | --- |
| Challenge/ problem to address: | The Terminal Evaluation (TE) is encouraged to look at the following: (i) Baseline data was only partially available at the time of the MTR. The project is encouraged to consolidate data from available surveys to provide a stronger data base for evaluating impact, in particular taking into consideration different segments of community, including vulnerable groups (Recommendation 14). The TE is encouraged to assess the extent of success. (ii) The outcome indicators do not capture incremental progress and revision is recommended (# 4). The TE is encouraged to look into the impact of weak outcome indicators on effectiveness, adaptive management and monitoring of project performance. (iii) The "Consortium Implementation Model” adopted by ECCLE has several demonstrated advantages, among them being a variant of the private-public-community partnership models favoured by Government of Zambia, but it also comes at an administrative cost (overheads, delays in contracting), which may reduce on effectiveness and efficiency. The TE is encouraged to assess the efficiency of the model. |
| Priority level: | N/A |
| Type: | Monitoring & Evaluation |
| Responsibility: | UNEP |
| Time-frame: | At project end |

## Annexes

### Annex 1. Response to stakeholder comments

The comments below were presented in response to the draft report and draft recommendations circulated among project stakeholders in Zambia, during the validation meeting held 30th September 2025 and in writing.

| Section number | Stakeholder comment | Evaluation team response and/or action taken |
| --- | --- | --- |
| Section II, Review Methods | Sharing of draft reports should allow for at least one week review during the consultative process. [Comment at Consultative Stakeholder Validation Meeting, 30/9/25] | Paragraph added to section on limitations |
| Section II Review Questions & Ratings | Question raised on compatibility of UNEP Review Criteria Ratings Matrix with GEF PIR performance ratings [Comment at Consultative Stakeholder Validation Meeting, 30/9/25; Written comments by PIU] | UNEP Review Criteria Ratings Matrix clarified in meeting and shared with PIU. |
| Section III Tabl4 4. | Wording of intermediate state too comprehensive with FNRM focus. Revert to focusing on replication and scaling up of Community Forestry in Zambia only. [Written comments by PIU] | ToC, Figure 3 and Annex 16 amended accordingly. |
| Section IV: F Monitoring & Reporting, Table 6 | The project results framework is not helpful to implementors, overall. Outcome indicators are pegged at too high a level and hamper progress evaluation [Comment at Consultative Stakeholder Validation Meeting, 30/9/25] | Paragraph added to Section III, ToC Recommendation 4 amended accordingly. |
| Section IV: A Strategic relevance C3: Progress toward outcomes C4: impact G2: Sust-ainability | Reflections on role of the ECCLE project in catalysing lessons beyond NWP preparing for mainstreaming for national-level change. Is this a change of goalposts? Should ECCLE focus on community forest management within the province, and/or drive national level change? In terms of the knowledge management element, this would be good to understand. [Comment at Consultative Stakeholder Validation Meeting, 30/9/25] | Significance of strategic review to generate a shared understanding of ECCLE contribution toward mainstreaming of gender-responsive CFM underscored Recommendation 3 amended accordingly. |
| Section IV: A Strategic Relevance | Complementary of the ECCLE project with existing intervention/coherence, including other GEF and non-GEF projects [Comment in writing, 15.10.2025] | ECCLE significance for other NRM and livelihood projects in Zambia emphasized |
| Section IV: A C2: Availability of outputs | Project role is to recommend to Government and not to engage in policy change. [Comment at Consultative Stakeholder Validation Meeting, 30/9/25] | With lead Forestry Department, project role may extend beyond recommendations. See Annex 20. |
| Section IV: C2: Availability of outputs | Question on principles for weighting of Component 3. As a smaller component its negative rating disproportionately affects the computation of the overall rating for outputs. With only 10,000 ha to be converted to sustainable agriculture, as compared 130,000 ha under improved forest management. [Comment at Consultative Stakeholder Validation Meeting, 30/9/25] | Principles for computing weighted averages, and ranges for performance provided for under UNEP Review Criteria Ratings Matrix clarified in meeting and shared with PIU. |
| Section IV: C2: Availability of outputs C2: Component 1 | The subsistence use of forests is not well known, which sets limits for supporting communities gravitating towards their semi-commercial use. [Comment at Consultative Stakeholder Validation Meeting, 30/9/25] | Underscores significance of refocusing KM products accessible to CFM communities, and their effective dissemination (para 105) |
| Section IV: C2: Availability of outputs C2: Component 1.4 | Are there any specific recommendations for Knowledge Management (KM) products (as handbooks or guidelines)? In particular considering that they will be recommendations. [Comment at Consultative Stakeholder Validation Meeting, 30/9/25] | No. The MTR proposes to refocus KM products in any way that supports product uptake optimally among CFM users, for peer learning and mainstreaming (Recommendation 7) |

| Section IV: C2: Availability of outputs Component 2 Viable NR enterprise portfolio | Community enterprise portfolio will need to include carbon offsets in order for CFM community enterprise to generate adequate income to pay for management costs, recognizing the risks and volatility of carbon markets. [Comment at Consultative Stakeholder Validation Meeting, 30/9/25] | Significance of carbon income re-emphasized in Component 2 strategies and recommendations 8 9. |
| --- | --- | --- |
| Section IV: C2: Availability of outputs Component 2 Viable NR enterprise portfolio | We (FD, IPs) need to support CFMGs develop processing strategies and NR-business for very high value end market [Comment at Consultative Stakeholder Validation Meeting, 30/9/25] | Comment underscores the importance of the project supporting CFMGs develop viable financial sustainability. (This is emphasized in recommendation 10) |
| Section IV: C2: Availability of outputs Component 3, sustainable agriculture | Achievements by Department of Agriculture highlighted: technology elements identified such as climate resilient crops, soil fertility methods, and training farmers in technologies done for one year. Design shortcoming in Component 3 – agreed [Comment at Consultative Stakeholder Validation Meeting, 30/9/25] | Comment underscores the importance of the project continuing to support the long-term introduction of CSA in the project area. (This is emphasized in recommendation 9) |
| Section IV: C2: Availability of outputs Component 3, sustainable agriculture | Agricultural change is a long-term process, and there is a fundamental flaw in the project design assuming that the project with a few years of training would be able to leap-frog farmers into adoption of CSA technologies. However, the project has supported the identification of technologies and their integration in extension systems. [Comment at Consultative Stakeholder Validation Meeting, 30/9/25] | Comment reconfirms MTR findings, whilst showing appreciation for Department of Agriculture work done. Speaks to the positive results at field facilitation level as well (Table 10) |

| Section IV: D Finance Management Annex 5 | Co-financing reporting suggests that some Government Departments have exceeded their commitments. Are these numbers correct? [Comment at Consultative Stakeholder Validation Meeting, 30/9/25] | Paragraph added to Section on Finance Reporting (D) Recommendation 5 amended accordingly |
| --- | --- | --- |
| Section IV: D Finance Management Annex 5 | WWF Zambia is an actor in Northwestern Province, but is not an effective ECCLE partner on the ground and has not contributed co-financing [Comment at Consultative Stakeholder Validation Meeting, 30/9/25] | Paragraph added to Section on Finance Reporting (D) Recommendation 5 amended accordingly |
| Section IV: F Monitoring Reporting C2: Availability of outputs Section V : Conclusions | The expression “poor sequencing” to described how chains of deliverables unfolded is incorrect. The sequenced planning was properly done, it was the activities that were delayed which caused the concern, bringing about less than optimal outcome. [Comment at Consultative Stakeholder Validation Meeting, 30/9/25, Written comment by PIU] | Language corrected in Table 10 and other paragraphs to better describe how events unfolded. |
| Section IV: F Monitoring Reporting C5: Adaptive management Section V : Conclusions | Ineffective mechanisms for adoption of reports is not a project failure, but a system failure as the mechanism for approval is provided for in the Project Document. Technical reports are verified by the relevant technical units (Agriculture, Forestry) [Comment at Consultative Stakeholder Validation Meeting, 30/9/25. Written comment PIU] | Correct. The cross-sectoral adoption mechanism, as per project design, is inadequate. The project is, through adaptive management, encouraged to improve adoption of project deliverables in a way that generates greater buy-in and commitment among stakeholders towards integrated FNRM (recommendations 2, 11). |
| Section IV: G2: Sustainability | Substantive work on subsistence use of forests, processing strategies and products for high value -end markets will be needed for Zambia to develop financially viable CFM systems. [Comment at Consultative Stakeholder Validation Meeting, 30/9/25] | Underscores significance of refocusing KM products learning and sharing lessons and developing viable sustainability plans. |
| Section IV: G2: Sustainability | Sustainability efforts (beyond sustainability plan) embarked upon by the Implementation Partners (TNC, WLCP) should be recognized. [Comment at Consultative Stakeholder Validation Meeting, 30/9/25] | Addition appreciated. Wording in Annex 19 and subsequent recommendation changed to reflect advanced IP plans. |
| Section IV: E Efficiency Section V: Conclusions Section VII Recommendations | Even with the best implementation arrangements some of these processes take time: sustainable agriculture and community enterprise. Business execution to the point of viability and profitability is a long-term prospect. Even with a timely closure through strategic consolidation and phased exit strategy this will not be achieved. [Comment at Consultative Stakeholder Validation Meeting, 30/9/25] | Observation underscores the MTR recommendations to develop sustainability plans for CFMGs working with their CSR implementation partners, for longer periods into the future. Recommendation 10 amended accordingly. |
| Section VII Recommendation | What would be an appropriate timeframe for the proposed consolidation and transition period? If too long, it will be counterproductive, as project resources are limited. [Comment at Consultative Stakeholder Validation Meeting, 30/9/25] | Criteria for determining the consolidation and transition period added to report. See paragraph added in Section E and Recommendation 1. |

### Annex 2. People consulted during the Mid Term Review

Communities (beneficiaries): Community Forest Management Group (executive committee members, women’s committee members, honorary forest officers, gender champions, beekeepers, farmers) in two locations: Kelongwa Kamanana and Ntambu. Scanned copies of attendance lists have been submitted to the UNEP Task Manager.

In Kelongwa Kamanana focal group discussions with executive CFMG committee, staff members, Honorary Forest Officers, beekeepers, gender champions and farmers.

In Ntambu, visit to the palace of his Royal Highness, Chief Ntambu, visit to honey processing plant, focal group discussions with CFMG Network, CFMG executive and women’s committee in Kewundu.

District teams; Kasempa district; (Kibra Mweetwa, DFO; Jack Coetzee, SAO; Ernest Munthali, MACO; Boston Hakapabila, Agric.; Brian Zemba, LFP, Obrian Mutinta, DFO, and Ncimunya Haniinga, Council); and Mwinilunga district; (Collins Kyombela, DFO, Mubita Nalisheba, MFL, Francis Mutale, MoA).

ECCLE Project Manager Ethel Sibajene Mudenda and team Chella Ngoma, Eneya M’simuko, Philip Daka, and Precious Zimba Mwape.

Ministry of Green Economy and Environment: Forestry Department–Director Mr. Sitwala Wamunyima, National Project Coordinator attached to the PIU – Ing’utu Simasiku Kazinga / Joyce Masinja Mutasha; Tekla Kafwimbi (CFM); Provincial Forestry Officer Mr. Maxwell Phiri, Provincial Focal Point Mr. Mulaku K. Muyunda, Interim PFO Serah Lunda.

Environmental Management Department Director and GEF Focal Point Person –Mr. Fishani Gondwe (retired).

GRZ Other Ministries and Departments

Department of Agriculture - Mr. Stanley Banda (National Focal Point Officer) Simbarashe Mubambwe (PAO, Provincial Focal Point); Muyobo Shimabale (Provincial Agriculture Coordinator)

Gender Division, Cabinet Office - Provincial Gender Officer Limpo Sishekanu

Ministry of Community Development and Social Services – Nancy Yando, Sr. Com. Dev. Officer

Ministry of Finance and National Development Planning - Jonathan Malinga (Provincial Planning Unit)

Ministry of Livestock and Fisheries – Bonna Zulu (Provincial Livestock Development Officer)

Ministry of Local Government and Rural Development Planning – Department of Physical Planning Mr. David Namutoka (Sr. Planner), Mr. Danny Lumba (Planner), Chrispin Mayaka (SLACO)

Ministry of Tourism - Department of National Parks and Wildlife – Mr. Chaka Kaumba (National Focal Point Officer), Dominic Kapokola (SWW)

Provincial Administration: Permanent Secretary Col. Grandson Wishikoti Katambi

NGOs/CSOs/Private Sector – Dorian Tilbury (WLCP), WCLP team: Hellen Sambaulu, Steven Munyandi; Norman Kalima (KCF), KCF team: Muleya Sindowe, Emmah Mubiakana, Martha Mkoka, Gladson Mbomena, Natasha Kabamba; Dr. David Square TFL, TFL team: Innocent Kayumba Dr. Royd Vinya (Miombo Ecosystem Enterprise Limited). Field level staff from Impulse Africa (Spencer Nakauno), Good Nature, and Wuchi Wami.

TNC The Nature Conservancy (TNC) Country Director Dr. Robert Munroe, TNC Finance and Grants team Mr. Charles Mbugua and Ms. Precious Zimba Mwape

UNEP Project Manager and team members: Daniel Pouakouyou, UNEP current Task Manager, Aska Ochiel; and Charles Imbenzi, UNEP Fund Management Officer (FMO), George Saddimbah.

### Annex 3. Key Documents Consulted

ECCLE Project Documents:

- Project Document and Appendices; Project design documents (including minutes of the project design review meeting at approval); including approved work plan and budget.

- Relevant implementation documentation and deliverables, inter alia: Project M and E Plan, Project Implementation Review reports –PIR, Semi Annual Progress Reports, Quarterly Reports, Technical Project Reports – including Consultancy Reports, Socio-Economic and Bio-Physical Forest Assessment, Minutes of the Project Steering Committee and Project Technical Committee Meetings, Annual Budgets and Work Plans, , Environmental and Social Management Plan, Gender Analysis and Gender Strategy and Action, Integrated Land Use Plans.

- Other progress reports from collaborating partners/sub awardees, project related meeting minutes, relevant correspondence etc.; as well as other reports as relevant (e.g. West Lunga Project).

- Various CFMG documents, Reports from training and capacity-building; Constitutions and By-Laws, CFMA Plans, Business Plans and records (see sample below).

### Annex 4. Review itinerary

GEF 7 ECCLE MID TERM REVIEW – CONSULTANT’S FIELD VISIT SCHEDULE

JUNE 11 – JUNE 20, 2025

| TIME | DAY | DATE | ACTIVITY |
| --- | --- | --- | --- |
| 08:00 | Tuesday | 10.06.25 | Arrival in Solwezi |
| 09:00 | Tuesday | 10.06.25 | Courtesy call to PS |
| 14:00 | Tuesday | 10.06.25 | Meeting with PIU (TSU) |
| 09:30 | Wednesday | 11.06.25 | Meeting PTC members |
| 14:00 | Wednesday | 11.06.25 | Individual Calls on Selected PTC Members: -Provincial Agric. Coordinator & PAO -Provincial Livestock Officer |
| 07:00 | Thursday | 12.06.25 | Travel to Kasempa |
| 11:00 | Thursday | 12.06.25 | Courtesy Call on District Commissioner |
| 14:00 | Thursday | 12.06.25 | Meeting with Local Conservation Partner (KCF) |
| 09:00 | Friday | 13.06.25 | Meeting with District Team |
| 12:00 | Friday | 13.06.25 | Travel to Kelongwa |
| 14:30 | Friday | 13.06.25 | Meeting with Beekeepers (Including Wuchi Wami) |
| 16:00 | Friday | 13.06,25 | Meeting with Gender Champions |
| 17:30 | Friday | 13.06.25 | Night Stop at Kelongwa CFMG - Eco Camp Site |
| 09:30 | Saturday | 14.06.25 | Meeting with CFMG Executive, TBU, & HFOs |
| 14:00 | Saturday | 14.06.25 | Meeting with Farmers (Crop and Livestock), Agriculture extension officers from MOA, GNA, Impuls A. |
| 16:00 | Saturday | 14.06.25 | Travel back to Kasempa Boma |
| 08:00 | Sunday | 15.06.25 | Travel to Ntambu |
| 08:00 | Monday | 16.06.25 | Meeting with Local Conservation Partner (WLCP) - Carbon Project included |
| 14:00 | Monday | 16.06.25 | Meeting with Chief Ntambu |
| 09:30 | Tuesday | 17.06.25 | Meeting with CFMG Network and TBU |
| 14:00 | Tuesday | 17.06.25 | Meeting with Kewundu CFMG - CFMG Executive & Women Sub Committee |
| 08:00 | Wednesday | 18.06.25 | Travel to Kalumbila |
| 10:30 | Wednesday | 18.06.25 | Meeting with Local Conservation Partner (TFL) |
| 14:00 | Wednesday | 18.06.25 | Travel to Solwezi |
| 09:00 | Thursday | 19.06.25 | Virtual meeting with Mwinilunga District Team |
| 11:00 | Thursday | 19.06.25 | Meeting with: -Provincial Gender Dev. Officer -Provincial Community Dev. Officer -Provincial Youth Dev. Officer |
| 14:00 | Thursday | 19.06.25 | Meeting PIU (TSU) |
| 09:30 | Friday | 20.06.25 | Meeting with: - Provincial Local Govt Officer - Provincial Physical Planner - Provincial Planning Unit |
| 11:30 | Friday | 20.06.25 | Virtual Meeting with Former PFO (Mr. Maxwell Phiri) |
| 16:00 | Friday | 20.06.25 | Travel Back to Lusaka |

### Annex 5. Project budget, expenditures and co-financing

Table 5.1. ECCLE cumulative expenditure statement (30-09-2025) by budget line

Source: Report compiled by ECCLE Finance Department/Executing Agency 29 April 2025

Table 5.2. ECCLE cumulative expenditure statement (31-03-2025) by component- Project not reported by component

Source: ECCLE Finance Department/Executing Agency PIR 2025

Table 5.3. ECCLE break-down of co-financing (30-06-2025)

| Sources of Co-financing | Name of Co-financier | Type of Cofinancing |  | Amount ($) committed | Co-finance expenditure @ MTR (30.06.2025) | Comment |
| --- | --- | --- | --- | --- | --- | --- |
| Recipient Country Government | Ministry of Lands and Natural Resources | In-kind | Recurrent expenditure | 7,200,000 | $48,719,545 | Ministry of Green Economy and Environment. Over-expenditure queried, no reply. |
| Recipient Country Government | Ministry of Agriculture | In-kind |  | 1,900,000 | $647,734 |  |
| Recipient Country Government | Ministry of Tourism and Arts | In-kind | Recurrent expenditures | 750,000 | $ 0 | Department of National Parks and Wildlife (DNPW) |
| Non-Government Organization | The Nature Conservancy (TNC) | In Kind | Recurrent expenditures | 300,000 | $ 178,000 |  |
|  |  | Grant | Investment Mobilized | 1,700,000 | $ 3,668,854 |  |
| Non-Government Organization | World Wildlife Fund (WWF) | In Kind | Recurrent expenditures | 3,780,000 | $0 | None reported. MTR recommends removal of WWF from list of co-financiers. |
| Non-Government Organization | West Lunga Conservation Project | In Kind |  |  | $515,650 |  |
| Private Sector | Trident Foundation Ltd for Kalumbila Minerals Limited | In Kind | Recurrent expenditures | 2,250,000 | $190,387 |  |
|  | First Quantum Minerals | In-kind | Recurrent expenditures | 2,500,000 | $ 0 |  |
| Total Co-financing |  |  |  | 20,380,000 | $53,920,170 |  |

Source: ECCLE Finance Department, September 2025

### Annex 6. Financial Management

| NON-GEF AND GEF PROJECTS |  |  |  |
| --- | --- | --- | --- |
| Financial management components: |  | Rating | Evidence/ Comments |
| - Adherence to UNEP’s policies and procedures: |  | HS:HU | S |
| Any evidence that indicates shortcomings in the project’s adherence to UNEP or donor policies, procedures or rules |  | Yes/No | No |
| - Completeness of project financial information: |  |  |  |
| Provision of key documents to the reviewer (based on the responses to A-H below) |  | HS:HU | S |
| A. | Co-financing and Project Cost’s tables at design (by budget lines) | Yes/No or N/A | Yes, full report received and relevant details annexed |
| B. | Revisions to the budget | Yes/No or N/A | Yes |
| C. | All relevant project legal agreements (e.g. SSFA, PCA, ICA) | Yes/No or N/A | Yes |
| D. | Proof of fund transfers | Yes/No or N/A | Yes |
| E. | Proof of co-financing (cash and in-kind) | Yes/No or N/A | Yes, relevant details annexed |
| F. | A summary report on the project’s expenditures during the life of the project (by budget lines, project components and/or annual level) | Yes/No or N/A | Yes, relevant details annexed |
| G. | Copies of any completed audits and management responses (where applicable) | Yes/No or N/A | Yes |
| H. | Any other financial information that was required for this project (list): | Yes/No or N/A | No |
| - Communication between finance and project management staff |  | HS:HU |  |
| Project Manager and/or Task Manager’s level of awareness of the project’s financial status. |  | HS:HU | S |
| Fund Management Officer’s knowledge of project progress/status when disbursements are done. |  | HS:HU | S |
| Level of addressing and resolving financial management issues among Fund Management Officer and Project Manager/Task Manager. |  | HS:HU | S |
| Contact/communication between by Fund Management Officer, Project Manager/Task Manager during the preparation of financial and progress reports. |  | HS:HU | MS |
| Project Manager, Task Manager and Fund Management Officer responsiveness to financial requests during the review process |  | HS:HU | MS |
| Overall rating |  |  | S |

### Annex 7. Communication and Outreach Tools

### Annex 8. Brief CV of the Reviewer

Name: Ms. Guni Mickels Kokwe

| Profession | Development Consultant |
| --- | --- |
| Nationality | Finnish |
| Country experience | - Europe: Finland - Africa: Ethiopia, Kenya, Tanzania, Malawi, Zambia, Zimbabwe |
| Education | Master of Science, University of Helsinki |
| E-mail: | gmickelskokwe@gmail.com |

Guni is a Development Consultant based in Finland and Zambia. She holds a degree in Development Geography from the University of Helsinki and possesses a range of professional skills relevant to project cycle, e.g. project planning and management, stakeholder participation, M&E, indicator development as well as specialised tools for community forestry and enterprise development.

Guni is a capable and trusted consultant who has worked with multiple stakeholders across the agriculture, livestock and fisheries subsectors in Zambia for more than 20 years – from capacity-building government staff at sub-district and district level; to working with farmer associations, Community Based Organisations (CBOs) and Non-Governmental Organisations (NGOs)

. She has supported various donors in the planning, appraising and evaluating projects and supported product research with the private sector and local forest communities. She is innovative, possesses excellent analytical and writing skills, and has a good understanding of how cross-cutting issues affect rural development, including human-rights based approaches

Sample of specialties and capabilities / assignments and experience relevant to the current assignment:

- Support to Government of Zambia and the Accredited Entity, the World Bank, develop an application to the Green Climate Fund (GCF), by undertaking a feasibility study of a transformative landscape project in Northern Zambia (World Bank, 2020).

- Design of an indicator framework for a survey of best practice in participatory forest management (PFM). The framework identifies eight necessary conditions for effective community engagement in PFM, for which proxy indicators were identified and specific checklist questions developed. The survey was part of an assignment to identify scalable interventions for the operationalisation of participatory forest management / community-forestry under REDD+ in Zambia (FAO/Forest Department, 2016-17).

- Mid-line evaluation of the Finland-FFD-AgriCord programme ‘Finland’s Support to Farmers Fighting Poverty’. Team leader, contracted by AgriCord, Belgium with field work in Tanzania and Ethiopia. The initiative builds the capacity of local producer organizations through small grants. Projects included forestry initiatives (AgriCord, December 2014 – April 2015).

- Environmental and social due diligence. Member of a team assessing the compliance of a REDD+ private sector operator seeking funding from international climate investment funds to expand their operations in the Luangwa Valley. The performance standards of the International Finance Corporation formed the basis for the assessment (Sanga/TLLG, 2019).

- Design and implementation of a qualitative survey of a non-wood forest product supply chain. Mapping economic strategies of actors along the chikanda supply chain, from harvesters to processors, as a precursor for a quantitative survey. Chikanda, is the trade name for edible ground orchids, a key non-wood forest product in Zambia, the trade of which spans from Angola and Congo across to Malawi and Tanzania (Kew Gardens, Darwin Initiative 2019).

- Mid-Term Review. Community centred conservation in the Kavango Zambezi trans-frontier conservation area (WWF 2015-2016).

### Annex 9. MTR Terms of Reference (Less original ToC / RF and Annexes)

Mid-Term Review of the UNEP project

Project Title: Ecosystem Conservation and Community Livelihood Enhancement in Northwestern Zambia Project GEF ID Number 10192

Section 1: PROJECT BACKGROUND AND OVERVIEW

(This section describes what is to be reviewed. Key parameters are project timeframe, funding envelope, results framework and geographic scope)

1. Project General Information

Table 1. Project Summary

(This is a generic table to summarise a project. Integrate the information below with the standard ‘project summary’ table of the relevant donor e.g. Adaptation Fund, GCF, GEF).

| UNEP PIMS ID/SMA ID: | 85583 | Grant ID (if applicable):S1-32GFL-000707 |  | GEF ID: 10192 |
| --- | --- | --- | --- | --- |
| UNEP Management (Division/Branch/Unit): | Ecosystems Division |  |  |  |
| Implementing Partners: | The Ministry of Green Economy and Environment – Department of Forestry and The Nature Conservancy |  |  |  |
| Sources of Funding: | Country(ies): Zambia |  | Institution Name/Type: |  |
| Relevant SDG(s): | Goal 5: Achieve gender equality and empower all women and girls. 5.a: Undertake reforms to give women equal rights to economic resources, as well as access to ownership and control over land and other forms of property, financial services, inheritance and natural resources, in accordance with national laws Goal 10: Reduce inequality within and among countries. 10.1: By 2030, progressively achieve and sustain income growth of the bottom 40 per cent of the population at a rate higher than the national average. 10.2: By 2030, empower and promote the social, economic and political inclusion of all, irrespective of age, sex, disability, race, ethnicity, origin, religion or economic or other status. Goal 13: Take urgent action to combat climate change and its impacts. 13.3: Improve education, awareness-raising and human and institutional capacity on climate change mitigation, adaptation, impact reduction and early warning 13.b. Promote mechanisms for raising capacity for effective climate change-related planning and management in least developed countries and small island developing States, including focusing on women, youth, and local and marginalized communities Goal 15: Protect, restore, and promote sustainable use of terrestrial ecosystems, sustainably manage forests, combat desertification, and halt and reverse land degradation and halt biodiversity loss. 15.6: Promote fair and equitable sharing of the benefits arising from the utilization of genetic resources and promote appropriate access to such resources, as internationally agreed |  |  |  |
| MTS (all that apply): |  | UNEP approval date: |  | 2021-08-19 |
| Sub-programme: | Thematic: Nature action sub-Programme | Programme Coordination Project: |  | Conservation |
| Expected start date: | 2021-08-20 | Actual start date: |  | 2021-08-20 |
| Planned completion date: | 31.08.2026 | Actual operational completion date: |  | 2027-08-31 |
| Planned total project budget at approval: | $ 5,338,585.00 | Actual total expenditures reported as of 2025-09-30: |  | $3893723.50 |
| Planned Extra-budgetary Funds:Co-Finance | Cash: 0.00 In-kind: $ 18,680,000 | Secured Extra-budgetary Funds: |  | Cash: $3,668,854 In-kind: 20,380,000.00 |
|  |  | Actual Extra-budgetary Funds expenditures reported as of 2024-06-30 |  | Cash: $3,668,854 In-kind: $50,251,316 |
| First disbursement: | 20.09.2021 | Planned date of financial closure: |  | Estimated 1 year after operational completion. 2027-08-31 |
| No. of formal project revisions: | 0 | Date of last approved project revision: |  | N/a |
| No. of Steering Committee meetings: | 5 | Date of Last Steering Committee meeting: |  | 2024-04-04 |
| Mid-term Review/ Evaluation (planned date): | 2024-08-31 | Mid-term Review/ Evaluation (actual date): |  |  |
| Terminal Evaluation (planned date): | 2027-03-29 | Terminal Evaluation (actual date): |  |  |
| Coverage – Implementing Country(ies): | Republic of Zambia | Coverage – Implementing Region(s): |  | Northwestern Zambia |
| Dates of previous project phases: | N/A | Status of future project phases: |  | N/A |

2. Project Rationale

[Describe project context and justification]

The Ecosystem Conservation and Community Livelihood Enhancement in Northwestern Zambia project is a five-year project aimed at addressing the direct and indirect drivers of deforestation and the degradation of forest and agricultural lands. The Project further addresses to sustainable land management and to biodiversity conservation at three project sites in three districts in the Northwestern Province (NWP) of the Republic of Zambia. This aligns with the priorities of the GEF-7 Impact Program (IP) on Sustainable Forest Management (SFM) in Drylands Landscapes.

The key threats to the rich biodiversity in the Northwestern Zambia include loss of forests and other natural resources and land degradation due to extensive and shifting agriculture, unsustainable charcoal production, illegal logging, illegal mining, overfishing and uncontrolled bushfires.  The drivers of these threats include poverty, food insecurity, and high demand for these products in illegal markets, all enabled by inadequate benefits from biodiversity conservation to local communities. The rationale of the project is based on the premise that supporting communities to strengthen systems for communal management of forests and other natural resources, providing support towards development of productive nature-based investments for sustained self-financing to conservation and enterprise development and supporting the adoption of sustainable agriculture practices and technologies to improve agriculture production and productivity, while also reducing the deforestation footprint of agriculture would result in sustainable resource management and consequently enhanced biodiversity.

The overall objective of the project is to strengthen community-based sustainable management of forest landscapes and provide improved livelihood opportunities for targeted forest-dependent rural communities in Zambia's Northwest Province. The  targeted geographical scope for the project is the north central portion of the West Lunga Complex specifically a 50,000 hectares area which is part of the 147,000 ha Chibwika Ntambu Game Management Area (GMA);  a 50,000 hectares of the Kelongwa - Makaba Community Forest Management Area that is part of the Greater Kafue Ecosystem (GKA) adjacent to the Lunga Luswishi GMA; and the communal lands east-northeast of Kalumbila town under Senior Chief Mukumbi comprising 4000Ha of the Kamikolo Community Forest Management Area. Further, the project has expanded this scope through an additional 150,000ha of communal lands under the Ntambu Chiefdom surrounding the Chibwika Ntambu GMA.  This is aimed at tapping into the vison to support the transformation of the Kafue ecosystem into a wildlife-abundant, climate-resilient, and financially sustainable landscape anchored by a national park, buffered by thriving community conserved lands, and connected to the West Lunga landscapes through community-managed wildlife corridors.

Working with Government, other collaborating public and private stakeholders in the landscape and forest-dependent communities themselves, the Project focuses on facilitating the development and strengthening of community natural resource tenure, governance, and management systems, stimulating the establishment of forest-based enterprise models and supports sustainable agricultural systems on the forest margins under three thematic areas:

Component 1: Strengthening the enabling regulatory, planning and governance frameworks for community-based, sustainable forest management; this component supports communities with awareness raising on community forest management, undertaking  assessments of forest conditions, determining the potential socio-economic importance of forest products, delineation of forests for community management, grouping of villages into management units of optimum geographic and economic scale, development of community forest management plans, development of plans for equitable sharing of costs and benefits and application of the Community Forest Management Groups for legal recognition and subsequent transfer of user rights by government through an Agreement.

Component 2: Promoting the conservation and sustainable use of natural resources in community-managed forests. Under this component the project assists the communities to develop business plans and investment plans and provides catalytic funding for productive investments and for the interim hiring of professional staff for CFMGs with a view to developing self-financing forest/natural resource management capacity and ensure enterprise development and conservation sustainability.

Component 3: Improved productivity and climate resilience from sustainable agricultural practices. This component focuses on the promotion of smallholder agricultural technologies and practices by small-scale crop and small livestock farmers living in the project target areas that contribute to the maintenance and enhancement of productivity on existing agricultural lands, thus reducing the need for farmers to extend their agricultural footprint into forests and other natural ecosystems because of declining productivity on their traditional lands. The project places a special focus on the promotion of technologies and practices that both maintain and enhance soil health as a critical factor in wider ecosystem health and increase the resilience of smallholder agricultural communities against climate change.

A critical aspect to the project implementation approach is the development and strengthening of partnerships with government, local communities, private sector actors, and non-governmental organizations to attain long lasting conservation outcomes. Against this background, The Nature Conservancy has partnered with West Lunga Conservation Project (WLCP), Kasempa Conservation Foundation (KCF) and Trident Foundation (TFL) the three (3) local conservation organizations implementing similar activities in the 3 project sites to support implementation of the project activities.

The expected outcomes of the project include the following:

Outcome 1: Sustainable forest management (SFM) mainstreamed in local development plans addressing gender equality:

Outputs:

1.1 Comprehensive assessment of forests and communities in the project area, sex and age disaggregated.

1.2 In-depth awareness raising on inclusive, gender sensitive CFMA creation leading to the declaration by

government of the new or modified CFMG.

1.3 Sustainable Forest and natural resource management promoted in gender responsive District Integrated

Development Plans and CFMA management plans.

1.4 Knowledge management (KM) system developed in support of gender sensitive community-

management of forests and natural resources.

1.5 Subsidiary legislation for forestry reviewed and revised in support of gender responsive sustainable forest-

management.

Outcome 2: Improved management of forest resources for gender equality and enhanced welfare and livelihoods.

Outputs:

2.1. Gender responsive business plans developed in support of each community forest management group.

2.2. Develop gender responsive community-based enterprises based on the business plan.

2.3. Capacities developed for gender responsive good governance, NRM and business management.

Outcome 3: Improved productivity, gender equality and climate resilience from sustainable agricultural practices on the lands zoned for agriculture adjacent to community-managed forests:

Outputs:

3.1. Gender responsive network of actors developed, and capacity built to deliver sustainable agricultural-

practices on the lands zoned for agriculture adjacent to community-managed forests.

3.2. Farmers and agricultural supply chain actors trained to encourage the adoption of gender responsive,

sustainable agricultural practices in agricultural zones in villages adjacent to community forests.

3.3. Crop and livestock male and female farmers adjacent to CFMAs equally trained to sustainably improve

their productivity and net income.

3. Project Results Framework

Theory of Change, Intervention Logic

(See Annexes 8, 9 & 10)

4. Executing Arrangements

UN Environment Programme’s Division of Ecosystems represents the Implementing Agency (IA) of the Global Environment Facility (GEF), with the following roles:

With regard to project implementation -

- Provide, in its role as GEF Implementing Agency, project oversight to ensure that GEF policies and criteria are adhered to and that the project meets its objectives and achieves expected outcomes in an efficient and effective manner (Project supervision is entrusted to the Director, who discharges this responsibility through the assigned UNEP/GEF Task Manager and Fund Management Officer (refer to Appendix 4 of the Project Cooperation Agreement (PCA). Project supervision missions by the Task Manager and/or Fund Management Officer are outlined in the project supervision plan appended (as per Appendix 5 of the PCA).

- Have a representative on the project steering committee (refer to paragraph Section C of Appendix 1 of the PCA).

- Perform the liaison function with the GEF Secretariat on the project.

- Inform the GEF Secretariat whenever there is a potentially substantive co-financing change (i.e. one affecting the project objectives, the underlying concept, scale, scope, strategic priority, conformity with GEF criteria, likelihood of project success, or outcome of the project).

- Rate, on an annual basis, progress in meeting project objectives, project implementation progress, risk, and quality of project monitoring and evaluation, and report to the GEF Secretariat through the Project implementation Review (PIR) report.

- Review and clear manuscripts prepared by the Executing Agency before publication, and review and agree any publishing contracts.

- Undertake a mid-term review or request the Evaluation Office (EO) of UNEP to perform an independent mid-term evaluation (refer to paragraph Section C of Appendix 1 of the PCA).

- Ensure that EO arranges for an independent terminal evaluation and submits its report to the GEF Evaluation Office.

- As deemed appropriate, facilitate access to information, advisory services, technical and professional support available to UNEP and will assist the Executing Agency to access the advisory services of other United Nations Organizations, whenever necessary.

Regarding funding and Procurement from GEF Funds -

- Ensure that both GEF and UNEP guidelines and standards are applied and met (technical, fiduciary, M&E) and ensure timely disbursement/sub-allotment to the executing agency, based on agreed legal documents.

- Approve budget revision, certify fund availability, and transfer funds.

The Nature Conservancy (TNC) as Executing Agency for UNEP will have the following roles and obligations:

- Has the primary responsibility for ensuring successful implementation and completion of the project. They are responsible for recruiting the respective senior project personnel in accordance with the terms of reference set out in the project document appended as Appendix 11; and ensure that the personnel performing project-related activities meet the highest standards of qualification and technical and professional competence necessary for the achievement of the objectives and results of the Project.

- Provide all reports, including half yearly progress reports, quarterly technical and financial reports the audit reports, the Project Implementation Review (PIR) report; the operational completion and all other reports as prescribed in the supervision plan (Appendix 5 of the CPA).

- Inform UNEP in writing whenever there is a substantive co-financing change.

- Notify UNEP, in writing, about any expected variations on the project budget on an annual basis.

- Ensure all subcontracts are established in writing which includes but is not limited to reporting and audit obligations which flow down in the subcontracts and monitor the performance of their contractors and ensure that they comply with all applicable terms and conditions of their Agreement.

- Ensure that procurement of goods and consulting services financed by GEF funds are subject to rules and regulations of the Executing Agency and include written standards based on widely recognized processes and an internal control framework to protect against fraud, corruption and waste.

- Utilize the funds and any supplies and equipment provided by UNEP in full compliance with the project document and maintain complete accurate records of non-expendable equipment purchased with GEF project funds and a duly authorized official of the Executing Agency shall take periodic physical inventories.

- Be responsible for the proper custody, maintenance, and care of all non-expendable equipment as well as items of attraction (items costing less than US$ 1,500, but with a useful life of more than a year) purchased with GEF funds.

- By Agreement with the IA, the Executing Agency shall submit a final inventory of equipment to UNEP and a proposal for the disposal/transfer of the said equipment using the format appended as Appendix 8B, unless otherwise agreed upon between the Parties.

The Project Implementation Unit (PIU) will be responsible for the following:

- Implementing the Annual Workplan as developed by the PIU with technical input from the Project Technical Committee and approved by the Project Steering Committee.

- Follow-up on recommendations and requests of the PSCF

- Financial management and procurement.

- Facilitating communications, organising meetings and acting as secretariat support for all meetings.

- Providing technical cooperation and coordination between stakeholder agencies and project partners.

- Reviewing technical documents and report compilation

- Supporting consultants hired to complete project activities.

The Ministry of Green Economy and Environment through the Forestry Department will:

- Provide implementation oversight to the Project and coordinate all aspects of project implementation.

- Coordinate the engagement of project partners and chairs the Project Steering Committee and Project Steering Committee.

- Ensure that lessons learned are shared among sites and within national committees and provide visibility of the project at the national and international level.

- Ensure adequate communication of information to all national and international partners.

The Project Steering Committee (PSC)

The project established a PSC during its second year of project implementation. During their second meeting, the PSC revised its charter and formed a joint PSC for the two GEF funded projects being executed through the Nature Conservancy and WWF. In its new charter, the following membership has been adopted: The Ministry of Environment and Green Economy; The Ministry of Agriculture; The Ministry of Tourism; The Ministry of Local Government and Rural Development; The Ministry of Water and Sanitation; The Ministry Fisheries and Livestock; Ministry of Lands and Natural Resources; The Minst5ry of Finance and National Planning; The Provincial Administration – Northwest, Eastern and Western Provinces (all represented at Permanent Secretary level). Further we have the Zambia Environmental Management Agency; UNEP; FAO; The Nature Conservancy; WWF; the Department of Environmental Management representing the GEF Country Focal Point and the Department of Forestry as Secretariate to the PSC.

The PSC provides overall guidance and strategic direction and oversight to project management and approves all final outputs and deliverables of the project. In addition, the following is their mandate:

- Responsible for evaluation and monitoring of the project outputs and achievements.

- Supporting any changes to the work plan or budget, and responsible for ensuring that the project remains on target with respect to its outputs.

- Where necessary, the PSC supports the definition of new targets in coordination with, and approval from, the Executing/Implementing parties.

The Project further established a Project Technical Committee (PTC) that comprise technical specialists of government agencies and the private sector and NGOs as relevant. Government agencies include: The Department of Forestry; Department of National Parks and Wildlife; Department of Agriculture; Department of Climate Change; Zambia Environmental Management Agency and Department of Environment Management. Private sector and NGOs include West Lunga Conservation Project; Kasempa Conservation Foundation and Trident Foundation. The PTC is Chaired by the Director of the Forestry Department. The roles and responsibilities of the PTC are:

- Providing primary oversight and regular technical oversight of the Project manager and the PIU and technical advice to the implementation of the project.

- Reporting to the institutions and organisations that they represent with regard to the project activities being carried out.

- Providing advice and technical guidance to the PIU, including, inter alia, by:

  - advising on technical issues faced by the Project.

  - Approving matters to be recommended to the PSC.

  - Reviewing TORs for procurement

  - Assisting with technical evaluations of proposals

  - Carrying out peer reviews of documents and reports

  - Assisting with planning and participating in training/workshop activities

The Project Technical Committee

The Project Technical Committee (PTC) is the primary oversight organ providing regular technical oversight to the Project manager and the PIU and providing technical advice to the implementation of the project. The Project Technical Committee plays an advisory support role to the PIU through:

- Advising the PIU on technical issues faced by the Project.

- Approving matters to be recommended to the PSC.

- Reviewing TORs for procurement

- Assisting with technical evaluations of proposals

- Carrying out peer reviews of documents and reports

- Assisting with planning and participating in training/workshop activities

The PTC meets twice a year and is composed of technical specialists of government agencies and the private sector and NGOs as relevant. Government agencies include Department of Forestry, Department of National Parks and Wildlife, Department of Agriculture, Department of Climate Change, Zambia Environmental Management Agency and the Department of Environment Management. NGOs and Private sector co-opted into the PTC include West Lunga Conservation Project, Trident Foundation and Kasempa Conservation Foundation.

The District Technical Team

The district technical team was set up at the start of the project. The technical team consists of government staff at district level from the Department of Forestry, Department of Agriculture; Department of Fisheries and Livestock; Department of National Parks and Wildlife and the Local Council. The district technical team staff are responsible for providing technical guidance for project activity implementation in their specialised fields to the local conservation implementing partners.  They are also responsible for preparing reports at district level and submitting to the Project Technical Support Unit (TSU) and the District Development Coordination Committee (DDCC). The district technical team works in collaboration with staff from the TSU supporting the Local Conservation Sub awardees and other sub awardees and Consultants engaged by the Project with the technical implementation of activities.

The Project Implementing Partners

The Project has several implementing partners ranging from government, non-government, and the private sector. From government, the leading implementing institution is the Ministry of Green Economy and Environment through the Department of Forestry. Others are: - the Ministry of Tourism through the Department of National Parks and Wildlife, The Ministry of Agriculture, The Ministry of Fisheries and Livestock, The Ministry of Local Government through the Council Offices in the 3 implementing districts and the Provincial Administration – Northwestern Province. From NGOs and the Private Sector, the key implementing partners include West Lunga Conservation Project, Kasempa Conservation Foundation, Trident Foundation, Miombo Ecosystem Enterprise Limited and a number of Market Off takers with whom The Nature Conservancy has signed MoUs to support various aspects of project implementation. At community level the key implementing partners are the Community Forest Management Groups.

5. Project Cost and Financing

| Project Components | Funding Source | Type of funding in US Dollars |  |  |
| --- | --- | --- | --- | --- |
|  |  | Cash/In Kind | GEF Project Financing | Co-financing |
| Component 1: Developing the enabling regulatory and planning frameworks for community-based, sustainable forest management | GEF TF | Cash | 1,173,137 |  |
|  | Ministry of Lands and Natural Resources | In Kind | - | 4,705,000 |
|  | Ministry of Agriculture | In Kind | - |  |
|  | Ministry of Tourism and Arts | In Kind | - |  |
|  | The Nature Conservancy (TNC) | In Kind | - |  |
|  | The Nature Conservancy (TNC) | Grant (investments mobilized) | - |  |
|  | World Wildlife Fund (WWF) | In Kind | - |  |
|  | Trident Foundation Ltd for Kalumbila Minerals Limited | In Kind | - |  |
|  | First Quantum Minerals | In Kind | - |  |
| Component 2: Promoting the conservation and sustainable use of natural resources in community-managed forests | GEF TF | Cash | 2,919,830 |  |
|  | Ministry of Lands and Natural Resources | In Kind | - | 8,980,000 |
|  | Ministry of Agriculture | In Kind | - |  |
|  | Ministry of Tourism and Arts | In Kind | - |  |
|  | The Nature Conservancy (TNC) | In Kind | - |  |
|  | The Nature Conservancy (TNC) | Grant (investments mobilized) | - |  |
|  | World Wildlife Fund (WWF) | In Kind | - |  |
| Component 3: Enhancing the sustainability and productivity of agricultural pracices on the lands zoned for agriculture adjucent to community forests | GEF TF | Cash | 979,870 |  |
|  | Ministry of Lands and Natural Resources | In Kind | - | 8,980,000 |
|  | Ministry of Agriculture | In Kind | - |  |
|  | Ministry of Tourism and Arts | In Kind | - |  |
|  | The Nature Conservancy (TNC) | In Kind | - |  |
|  | The Nature Conservancy (TNC) | Grant (investments mobilized) | - |  |
|  | World Wildlife Fund (WWF) | In Kind | - |  |
| Sub total |  |  | 5,072,838 | 18,440,000 |
| Project Management Cost (PMC) |  |  | 265,748 1 | 940,000 |
| Total Project Cost |  |  | 5,338,585 | 20,380,000 |

Break Down of Sources of Co-financing.

| Sources of Co-financing | Name of Co-financier | Type of Cofinancing | Investment Mobilized | Amount ($) |
| --- | --- | --- | --- | --- |
| Recipient Country Government | Ministry of Lands and Natural Resources | In-kind | Recurrent expenditures | 7,200,000 |
| Recipient Country Government | Ministry of Agriculture | In-kind |  | 1,900,000 |
| Recipient Country Government | Ministry of Tourism and Arts | In-kind | Recurrent expenditures | 750,000 |
| Non-Government Organization | The Nature Conservancy (TNC) | In Kind | Recurrent expenditures | 300,000 |
| Non-Government Organization | The Nature Conservancy (TNC) | Grant | Investment Mobilized | 1,700,000 |
| Non-Government Organization | World Wildlife Fund (WWF) | In Kind | Recurrent expenditures | 3,780,000 |
| Private Sector | Trident Foundation Ltd for Kalumbila Minerals Limited | In Kind | Recurrent expenditures | 2,250,000 |
| Private Sector | First Quantum Minerals | In-kind | Recurrent expenditures | 2,500,000 |
| Total Co-financing |  |  |  | 20,380,000 |

UNEP GEF APPROVED BUDGET AND EXPENDITURES AS AT JUNE 2024 (QUARTER 2 – 2024)

| Project number: |  | 10192 / GFL-11207-14AC0003-SB-017844 |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Project executing partner: |  | The Nature Conservancy (TNC) |  |  |  |  |  |  |  |  |  |
| Project implementation period: |  | From: | 20-Aug-21 |  |  |  | To: | 31-Aug-26 |  |  |  |
| Reporting period: |  | From: | 1-Apr-24 |  |  |  | To: | 30-Jun-24 |  |  |  |
| UNEP Budget Line |  | GEF-approved budget |  | Actual expenditures incurred* |  |  |  |  |  |  | Cumulative unspent balance to-date |
|  |  | Total project budget | Current year budget | Cummulative expenditures from previous period | Jan-Mar Qtr 1 | Apr-Jun Qtr 2 | Jul-Sep Qtr 3 | Oct-Dec Qtr 4 | Current year total | Cumulative expenditures to-date |  |
| BL** | Budget Line description | A | B | C | D | E | F | G | H=D+E+F+G | I=C+H | J=A-I |
| 1100 | Project personnel | 563,829 | 154,077 | 240,686 | 31,573 | 57,303 | - | - | 88,876 | 329,562 | 234,267 |
| 1200 | Consultants | 331,482 | 102,640 | 137,290 | 15,788 | 34,026 | - | - | 49,814 | 187,104 | 144,377 |
| 1300 | Administrative support ICR |  |  |  |  |  |  |  |  |  |  |
| 1600 | Travel on official business | 251,319 | 66,719 | 102,563 | 19,536 | 29,413 | - | - | 48,949 | 151,512 | 99,807 |
| 2100 | Sub-contracts (UN entities) |  |  |  |  |  |  |  |  |  |  |
| 2200 | Sub-contracts (supporting organizations) | 2,657,408 | 1,787,245 | 511,873 | 276,949 | 95,242 | - | - | 372,191 | 884,064 | 1,773,344 |
| 2300 | Sub-contracts (for commercial purposes) |  |  |  |  |  |  |  |  |  |  |
| 3200 | Group training | 900,500 | 462,257 | 360,968 | 77,605 | 82,262 | - | - | 159,867 | 520,835 | 379,665 |
| 3300 | Meetings/Conferences | 199,430 | 57,045 | 65,265 | 1,746 | 7,900 | - | - | 9,646 | 74,911 | 124,518 |
| 4100 | Expendable equipment | 2,193 | 818 | 478 | - | 482 | - | - | 482 | 960 | 1,233 |
| 4200 | Non-expendable equipment | 170,044 | 52,440 | 106,103 | 19,339 | - | - | - | 19,339 | 125,442 | 44,602 |
| 4300 | Premises |  |  |  |  |  |  |  |  |  |  |
| 5100 | Operation and maintenance of equipment | 157,381 | 48,564 | 60,307 | 11,252 | 4,917 | - | - | 16,168 | 76,476 | 80,905 |
| 5200 | Reporting costs |  |  |  |  |  |  |  |  |  |  |
| 5300 | Sundry |  |  |  |  |  |  |  |  |  |  |
| 5400 | Hospitality and entertainment |  |  |  |  |  |  |  |  |  |  |
| 5500 | Evaluation | 105,000 | 49,541 | 1,959 | 1,394 | 1,951 | - | - | 3,345 | 5,304 | 99,696 |
| GRAND TOTAL |  | 5,338,585 | 2,781,347 | 1,587,493 | 455,183 | 313,495 | - | - | 768,678 | 2,356,170 | 2,982,414 |

6. Implementation Issues

- The project experienced significant delays before project inception. Despite the endorsement letter being signed on 2nd June 2021, the 1st disbursement was only made on 13th September 2022. This led to delays in staff recruitment and project inception. The inception meeting was held on 29th March 2022 and full staff complement was only achieved in June 2022.

- The project developed a significant underspend of the budgets, largely attributable to the slow implementation of the community forestry work in the Kamikolo site in Kalumbila District. The delays in implementation in this project site were caused by multiple reasons, including disagreements by the community on the size of the Community Forest Management Area, the death of the traditional Chief of the area that led to conflicts between the communities and a decision to pull out of the project by part of the project. There were therefore protracted negotiations before the community was finally reorganized and commenced the processes in 2024. This issue was reported to the Project Steering Community sittings of both 27th June 2023 and 6th April 2024 for resolution. A decision was made to downsize activities in Kamikolo due to concerns over the sustainability of project activities in this particular site after the end of the project to and scale up activities in the Mwinilunga Project Site instead.

- Constraints across some budget lines leading to budget over expenditure and under expenditures across budget lines including project management and project activities. The budget needed realigning to the actual budget requirements of the affected lines. UNEP gave approval to the PIU to review the project budget and approval was granted on 10th May 2024.

Section 2. OBJECTIVE AND SCOPE OF THE MID-TERM REVIEW

7. Objective of the Review

In line with the UNEP Evaluation Policy and the UNEP Programme and Project Management Manual, the Mid-Term Review (MTR) is undertaken approximately half-way through project implementation to analyze whether the project is on-track, what problems or challenges the project is encountering, and what corrective actions are required.

8. Key Review Principles

Mid-Term review findings and judgements will be based on sound evidence and analysis, clearly documented in the Review Report. Information will be triangulated (i.e. verified from different sources) as far as possible, and when verification is not possible, the single source will be mentioned (whilst anonymity is still protected). Analysis leading to evaluative judgements should always be clearly spelled out.

Possible questions to be considered include, (MTR Review Framework Questions available from UNEP Project Manager):

- Does the TOC properly reflect the project’s intended change process?

- Is the stakeholder analysis still appropriate and adequate to support the project’s ambitions?

- Are results statements in keeping with UNEP definitions (e.g. outcomes are expressed as the uptake or use of outputs)

- Are roles and responsibilities commonly understood and playing out effectively?

- Is there an effective monitoring mechanism for the project’s implementation (this is separate from, and supports, reporting)?

- Is the rate of expenditure appropriate for the mid-point?

- Have plans for inclusivity, equality and/or equity been implemented as planned, or does more need to be done?

- Are safeguard identification and mitigation plans being monitored and steps taken to minimize negative effects?

- Is there an exit strategy in place and are the elements needed for the project’s benefits to be sustained after the project end being incorporated in the project implementation?

- (Where relevant) Have recommendations from previous learning exercises/performance assessments been appropriately addressed

- (Where relevant) What changes were made to adapt to the effects of COVID-19 and how might any changes affect the project’s performance?

Key Strategic Questions

- What evidence exists indicating that the project is contributing to raising community awareness on and interests in forest management?

- What evidence is available that the project is contributing to improving community livelihoods through assisting them to develop business and enterprise investment plans?

- What evidence is available that the project is contributing to the promotion of smallholder agricultural technologies and practices by small-scale crop farmers and pastoralists living in the project areas?

A Mid-Term Review is a formative assessment, which requires that the consultant(s) go beyond the assessment of “what” the project performance is and make a serious effort to provide a deeper understanding of “why” the performance is as it is.

Attribution, Contribution and Credible Association: In order to attribute any outcomes and impacts to a project intervention, one needs to consider the difference between what has happened with, and what would have happened without, the project (i.e. take account of changes over time and between contexts in order to isolate the effects of an intervention). This requires appropriate baseline data and the identification of a relevant counterfactual, both of which are frequently not available for reviews. Establishing the contribution made by a project in a complex change process relies heavily on prior intentionality (e.g. approved project design documentation, logical framework) and the articulation of causality (e.g. narrative and/or illustration of the Theory of Change). Robust evidence that a project was delivered as designed and that the expected causal pathways developed supports claims of contribution and this is strengthened where an alternative theory of change can be excluded. A credible association between the implementation of a project and observed positive effects can be made where a strong causal narrative, although not explicitly articulated, can be inferred by the chronological sequence of events, active involvement of key actors and engagement in critical processes.

Partners and Key Project Stakeholders.  A key aim of the Mid-Term Review is to encourage reflection and learning by UNEP staff, the implementing partners and key project stakeholders The Review Consultant should consider how reflection and learning can be promoted, both through the review process and in the communication of review findings and key lessons.

9. Review Criteria

All review criteria will be rated on a six-point scale as follows: Highly Satisfactory (HS = 6); Satisfactory (S = 5); Moderately Satisfactory (MS = 4); Moderately Unsatisfactory (MU =3); Unsatisfactory (U = 2); Highly Unsatisfactory (HU =1). A Criteria Ratings Matrix is available, within the suite of tools, to support a common interpretation of points on the scale for each review criterion. The Overall Performance Rating is calculated as a simple average of the ratings for each criterion (A-H). Any criterion assessed as being in the ‘Unsatisfactory’ range should trigger corrective action in the Management Response.

For GEF-funded projects there are a series of questions that need to be uploaded to the GEF Portal. The consultant should complete the table in Annex 5 of these TOR and append it to the Final Review report.

Where UNEP funding partners have areas of specific interest, these are noted, below.

A. Strategic Relevance

The Mid Term Review (MTR) will assess the extent to which the activity is suited to the priorities and policies of UNEP, the donors, implementing regions/countries and target beneficiaries and is operating in a way that is complementary to other ongoing interventions.

The MTR will assess whether there have been any changes in priorities since the project was designed and whther the project has/should adapt to address the changing policy/strategy context.

This criterion comprises two elements:

Alignment to UNEP’s, Donors and Country (global, regional, sub-regional and national) strategic priorities

The Review should assess the project’s alignment with the UNEP Medium Term Strategy (MTS) and Programme Of Work (POW) under which the project was approved and include, in its narrative, reflections on the scale and scope of any contributions made to the planned results reflected in the relevant MTS and POW. UNEP strategic priorities include the Bali Strategic Plan for Technology Support and Capacity Building (BSP) and South-South Cooperation (S-SC). The MTR will assess the extent to which the project is suited to, or responding to, donor priorities as well as alignment of the project with global priorities such as the SDGs and Agenda 2030. The extent to which the project is suited, or responding to, the stated environmental concerns and needs of the countries, sub-regions or regions where it is being implemented will also be considered. Examples may include: UN Sustainable Development Cooperation Framework (Cooperation Framework) or, national or sub-national development plans, poverty reduction strategies or Nationally Appropriate Mitigation Action (NAMA) plans or regional agreements etc. Within this section consideration will be given to whether the needs of all beneficiary groups are being met and reflects the current policy priority to leave no-one behind.

Complementarity/Coherence with Relevant Existing Interventions

An assessment will be made of how well the project is taking account of ongoing and planned initiatives (under the same sub-programme, other UNEP sub-programmes, or being implemented by other agencies within the same country, sector or institution) that address similar needs of the same target groups.

The MTR will consider if the project team, in collaboration with all partners, is fulfilling any commitments to collaborate made at project design and is working to ensure their own intervention is complementary to other interventions. Examples may include work within UN Sustainable Development Cooperation Frameworks (UNSDCF) or One UN programming. Linkages with other interventions should be described and instances where UNEP’s comparative advantage has been particularly well applied should be highlighted.

| Adaptation Fund | To encourage utilization, each review should optimize relevance by ensuring (i) that the primary intended users of the evaluation and their intended uses are clearly identified and engaged at the beginning of the evaluation process; (ii) that “intended users” include funding, implementing, and beneficiary stakeholders; and (iii) that evaluators ensure these intended users contribute to decisions about the evaluation process. |
| --- | --- |
| Green Climate Fund | Coherence in climate finance delivery with other multilateral entities. |

B. Quality & Revision of Project Design

The MTR should provide a brief overview of the strengths and weaknesses of the project design and assess whether all elements of the project design have been initiated and/or are still planned for. Based on a review of the project design document, regular reports and meeting minutes, the Review Consultant will confirm whether any amendments have been made to the activities and/or results of the project. This includes changes to the formulation of results statements as well as changes in results indicators and/or project targets and the associated budget. Where revisions have been made the Consultant should confirm that formal documentation for these amendments is available and that UNEP/donor policies for revisions have been followed. In the absence of such formalisation the Review Consultant will make appropriate recommendations.

C. Effectiveness

The Review will assess effectiveness across four dimensions: availability of outputs, progress towards project outcomes and adaptive management. The Review Consultant will confirm that all results statements conform to UNEP’s definitions and make recommendations for adjustments where necessary. At the project’s mid-point emphasis is placed on the timeliness, quality and ownership of outputs and whether the project is adopting approaches or delivering activities to support the uptake of outputs (i.e. outcome level results).

Theory of Change

- The Review will assess whether the Theory of Change/Results Framework represents a coherent and realistic change process from a cause-and-effect perspective. Considerations will be given to whether the causal pathways are effectively shown/articulated and supported by a full set of contributing conditions ((‘drivers’ are external factors largely under the influence of the project; ‘assumptions’ are external factors largely outside the influence of the project). The TOC should also reflect UNEP’s commitment to increasing equality in line with the UN’s commitment to human rights. If adjustments are needed, they should be clearly presented and justified during the MTR process and a recommendation made on how any revisions could be formally approved.

Availability of Outputs

The Review will assess the project’s success in producing the planned outputs and making them available to the intended beneficiaries as well as its success in achieving milestones as per the project design document or any formal revisions. The availability of outputs will be assessed in terms of both quantity and quality, and the assessment will consider their ownership by, and usefulness to, intended beneficiaries and the timeliness of their provision. It is noted that emphasis is placed on the performance of those outputs that are most important to achieve outcomes.  The Review will briefly explain the reasons behind the success or shortcomings of the project in delivering its planned outputs and recommend corrective action as appropriate.

Progress towards Project Outcomes

At the project mid-point, the Review Consultant will focus on the links between the provision of outputs and their adoption at the outcome level. The MTR will explore whether the assumptions and drivers that need to be in place to support the uptake of outputs are evident/emerging and consider whether sufficient effort and attention is being directed towards reaching outcome levels.

The Review Consultant will review the project Theory of Change (TOC) and confirm that is properly reflects all levels (outputs, outcomes, intermediate states and long-lasting impact) of results included in the project design. Where necessary, the TOC should be reconstructed, in discussion with the project team, to better guide and strengthen project implementation.

Likelihood of Impact

Based on the articulation of long-lasting effects in the reconstructed TOC (i.e. from project outcomes, via intermediate states, to impact), the Review will assess the likelihood of the intended, positive impacts becoming a reality.

The Review will consider the extent to which the project has played a catalytic role or has promoted scaling up and/or replication as part of its Theory of Change (either explicitly as in a project with a demonstration component or implicitly as expressed in the drivers required to move to outcome levels) and as factors that are likely to contribute to greater or long-lasting impact.

Adaptive Management

The Review will assess whether any adaptive management is evident, possibly reflected in annual reports or reports from field missions etc. The Review Consultant will consider the project’s performance to-date from a risk perspective considering: a) the likelihood of any non/late delivery of the project’s workplan; b) likelihood of any negative effects, including reputational risks and safeguard issues and c) factors undermining the endurance of project achievements.

During the MTR, forward plans should be reviewed and adaptive management strategies discussed such that the project’s effectiveness and efficiency are maximized. Actions for adaptive management should be reflected in the MTR recommendations, which may include recommendations on governance structures, implementation arrangements, project design elements, monitoring and/or exit strategies etc.

| Adaptation Fund | The Review should consider, under Effectiveness, the extent to which the evaluand is reaching Strategic Results Framework indicator targets. |
| --- | --- |
| Adaptation Fund | The Review should consider, under Effectiveness, the extent to which the intervention demonstrates that Climate Change Adaptation can be increased or replicated at a broader scale, as well as in other contexts. |
| Green Climate Fund | The Review should consider, under Effectiveness, the project’s Innovativeness in result areas – the extent to which interventions may lead to paradigm shift towards low-emission and climate-resilient development pathways. |
| Global Environment Facility | The Review should consider, under Effectiveness, the extent to which the evaluand is reaching Core Indicator targets (from GEF-6 onwards). |
| Global Environment Facility | The Review will determine, under Effectiveness, the project’s additionality by comparing the benefits of GEF support to a scenario without GEF support. It will identify specific areas where GEF support has contributed additional results and what these additional results were. It will provide quantitative and qualitative evidence to support the findings. |

D. Financial Management

Under financial management the Mid-Term Review will assess: a) whether the rate of spend is consistent with the project’s length of implementation to-date, the agreed workplan and the delivery of outputs and b) whether financial reporting and/or auditing requirements are being met consistently and to adequate standards by all parties. Any financial management issues that are affecting the timely delivery of the project or the quality of its performance will be highlighted. Expenditure should be reported, where possible, at output/component level and will be compared with the approved budget.

Ratings should be provided for two sub-categories (adherence to policies and completeness of financial information), as assessed at the mid-point: i) the Review will verify the application of proper financial management standards and adherence to UNEP’s financial management policies; ii) the Review will record where standard financial documentation is missing, inaccurate, incomplete or unavailable in a timely manner. The Review may comment on the level of communication between the UNEP Project Manager and the Fund Management Officer as it relates to the effective delivery of the planned project and the needs of a responsive, adaptive management approach.

| Global Environment Facility | The Review will determine, under Financial Management, i) time from CEO endorsement (FSP) / CEO approval (MSP) to first disbursement; ii) disbursement balance; iii) whether the project has secured co-financing higher than 35% and iv) time between CEO Endorsement and (likely) end of MTR. |
| --- | --- |

E. Efficiency

Under the efficiency criterion, the Review will assess the extent to which the project delivered maximum results from the given resources. The Review will assess the cost-effectiveness and timeliness of project execution.

Focusing on the translation of inputs into outputs, cost-effectiveness is the extent to which an intervention has achieved, or is expected to achieve, its results at the lowest possible cost. Timeliness refers to whether planned activities have been/are being delivered according to expected timeframes as well as whether events are being sequenced efficiently. The Review will give special attention to efforts being made by the project teams during project implementation to make use of/build upon pre-existing institutions, agreements and partnerships, data sources, synergies and complementarities with other initiatives, programmes and projects etc. to increase project efficiency. The Review will also assess ways in which potential project extensions can be avoided through stronger project management.

F. Monitoring and Reporting

The Review will assess monitoring and reporting across two sub-categories: monitoring of project implementation and project reporting.

Monitoring of Project Implementation

Each project should be supported by a sound monitoring plan that is designed to track progress against SMART results towards the provision of the project’s outputs and the achievement of the project outcomes, including at a level disaggregated by gender, marginalisation or vulnerability, including those living with disabilities. In particular, the Review will assess the relevance and appropriateness of the project indicators as well as the methods used for tracking progress against them as part of conscious results-based management.

The Review will assess whether the monitoring system is operational and facilitates the timely tracking of results and progress towards project milestones and targets throughout the project implementation period. This assessment will include consideration of whether the project gathered relevant and good quality baseline data that is accurately and appropriately documented. This should include monitoring the representation and participation of disaggregated groups, including gendered, marginalised or vulnerable groups, such as those living with disabilities, in project activities. It will also consider how quality monitoring data are being used to adapt and improve project execution, achievement of outcomes and ensure sustainability. The Review should confirm that funds allocated for monitoring are being used to support this activity.

Project Reporting

UNEP has a centralised information management system in which project managers upload six-monthly progress reports against agreed project milestones. This information will be provided to the Review Consultant by the UNEP Project Manager. Donors may have specific reporting requirements and copies of reports will be made available by the UNEP Project Manager. The Review will assess the extent to which both UNEP and Donor reporting commitments have been fulfilled. This should include confirmation that meeting and field mission reports are being written and centrally stored.

Where the need for any corrective action has been indicated in any project reports (e.g. as an identified risk), the Review Consultant will record whether this action has been taken. This may include responses made during the COVID-19 pandemic or other unpredictable external events of a disruptive or crisis nature. The Review Consultant will also confirm whether formal reports have been appropriately authorised by both the author and the relevant supervisor.

| Global Environment Facility | For internally executed projects the Review Consultant should review the quality of regular reports and confirm they have been submitted on a timely basis. |
| --- | --- |

G. Exit Strategy & Sustainability (for Adaptation Fund, read Human and Ecological Sustainability and Security)

Sustainability is understood as the probability of the benefits derived from the achievement of the project outcomes being maintained and developed after the close of the intervention. It may be considered from the perspectives of socio-political, institutional and/or financial sustainability. The Review will identify and assess the key conditions or factors that are likely to undermine or contribute to the endurance of benefits at the outcome level. Some factors of sustainability may be embedded in the project design and implementation approaches while others may be contextual circumstances or conditions that evolve over the life of the intervention. It is assumed that environmental sustainability is central to any UNEP project design but where applicable an assessment of bio-physical factors that may affect the sustainability of project outcomes may also be included.

The Review will ascertain that the project has put in place an appropriate exit strategy and measures to mitigate risks to sustainability. The Review Consultant will consider: a) the level of ownership, interest and commitment among government and other stakeholders to take the project achievements forwards; b) the extent to which the sustainability of project outcomes is dependent on issues relating to institutional frameworks and governance and c) the extent to which project outcomes are dependent on future funding for the benefits they bring to be sustained. It will consider whether institutional achievements such as governance structures and processes, policies, sub-regional agreements, legal and accountability frameworks etc. are robust enough to continue delivering the benefits associated with the project outcomes after project closure.

| Adaptation Fund | The Review should consider, under Human and ecological sustainability and security – the extent to which the intervention is likely to generate continued positive or negative, intended and unintended impacts beyond its lifetime, taking into consideration, social, institutional, economic, and environmental systems. Is the intervention sensitive to conflict and fragility, i.e., to what extent does it consider the political context and the sharing of natural resources? Is it contributing towards targeted communities’ livelihoods and to the health or well-being of the ecosystems on which they depend? |
| --- | --- |

H. Factors and Processes Affecting Project Performance and Cross-Cutting Issues

Project Inception

This criterion focuses on the inception or mobilisation stage of the project. The Review will assess whether appropriate measures were taken to either address weaknesses in the project design, fill information gaps or respond to changes that took place between project approval, the securing of funds and project mobilisation. In particular, the Review will consider the nature and quality of engagement with stakeholder groups by the project team, the confirmation of partner capacity and development of partnership agreements as well as initial staffing and financing arrangements. The Review Consultant will confirm whether appropriate inception meetings were held and whether an inception report is available on file.

Quality of Project Management and Supervision

During the MTR the consultant will review the planned implementation structure and the roles and responsibilities assigned to each partner or party. Where roles are not being played as planned, an appropriate recommendation to formalise correction action and/or a change in the implementation structure, should be made.

In some cases, ‘project management and supervision’ may refer to the supervision and guidance provided by UNEP to partners and national governments while in others it may refer to the project management performance of an implementing partner and the technical backstopping and supervision provided by UNEP. The performance of parties playing different roles should be discussed and a rating provided for both types of supervision (UNEP/Implementing Agency; Partner/Executing Agency) and the overall rating for this sub-category is established as a simple average of the two.

The Review will assess the effectiveness of project management to-date with regard to: providing leadership towards achieving the planned outcomes; managing team structures; maintaining productive partner relationships (including Steering Groups etc.); maintaining project relevance within changing external and strategic contexts; communication and collaboration with UNEP colleagues; risk management; use of problem-solving; project adaptation and overall project execution. Evidence of adaptive project management should be highlighted.

| Adaptation Fund | The Review should consider the extent to which the evaluand is being adapted in response to lessons and reflections during implementation; and the extent to which the intervention supports the use, development, or diffusion of innovative practices, tools, or technologies to improve or accelerate Climate Change Adaptation. |
| --- | --- |
| Global Environment Facility | For internally executed projects the Review Consultant should review whether the segregation of responsibilities meets the GEF requirements (the GEF Agency must separate its project implementation and execution duties and establish each of the following: (a) A satisfactory institutional arrangement for the separation of implementation and executing functions in different departments of the GEF Agency; and (b) Clear lines of responsibility, reporting and accountability within the GEF Agency between the project implementation and execution functions. |

Stakeholder Participation and Cooperation

Here the term ‘stakeholder’ should be considered in a broad sense, encompassing all project partners; duty bearers with a role in delivering project outputs; target users of project outputs and any other collaborating agents external to UNEP and the implementing partner(s). The assessment will consider the quality and effectiveness of all forms of communication and consultation with stakeholders throughout the project life to-date and the support given to maximise collaboration and coherence between various stakeholders, including sharing plans, pooling resources and exchanging learning and expertise. The inclusion and participation of all differentiated groups, including gender groups, should be considered.

Responsiveness to Human Rights and Gender Equality (for Adaptation Fund, read ‘Equity’; for GCF, read ‘Gender Equity’)

The Review will ascertain to what extent the project has applied the UN Common Understanding on the human rights-based approach (HRBA) and the UN Declaration on the Rights of Indigenous People.  Within this human rights context the Review will assess to what extent the intervention adheres to UNEP’s Policy and Strategy for Gender Equality and the Environment.

The report should present the extent to which the intervention, following an adequate gender analysis at design stage, has implemented the identified actions and/or applied adaptive management to ensure that Gender Equality and Human Rights are adequately considered. In particular, the Review will consider the extent to which project implementation has taken into consideration: (i) possible gender inequalities in access to, and the control over, natural resources; (ii) specific vulnerabilities of disadvantaged groups (especially women, youth and children and those living with disabilities) to environmental degradation or disasters; (iii) the role of women in mitigating or adapting to environmental changes and engaging in environmental protection and rehabilitation.

| Adaptation Fund | The Review should consider the extent to which the project’s design and implementation include input of the designated authority (DA) and vulnerable groups such as women, youth, persons with disability, Indigenous Peoples, minorities, and other potentially marginalized groups or locations. It also encompasses the degree to which the intervention reduced or perpetuated inequalities, and how equitably benefits were accrued to vulnerable groups. |
| --- | --- |

Environmental and Social Safeguards (for Adaptation Fund, read Human and ecological sustainability and security ‘)

UNEP projects address environmental and social safeguards primarily through the process of environmental and social screening, risk assessment and management (avoidance or mitigation) of potential environmental and social risks and impacts associated with project and programme activities. The Review will confirm whether UNEP requirements were met to: screen proposed projects for any safeguarding issues; conduct sound environmental and social risk assessments; identify and avoid, or where avoidance is not possible, mitigate, environmental, social and economic risks; apply appropriate environmental and social measures to minimize any potential risks and harm to intended beneficiaries and report on the implementation of safeguard management measures taken.

The Review will also consider the extent to which the management of the project is minimising UNEP’s environmental footprint.

Country Ownership and Driven-ness

The Review will assess the quality and degree of engagement of government / public sector agencies in the project to-date. While there is some overlap between Country Ownership and Institutional Sustainability, this criterion focuses primarily on the forward momentum of the intended projects results, i.e. either: a) moving forwards from outputs to project outcomes or b) moving forward from project outcomes towards intermediate states. The Review will consider the involvement not only of those directly involved in project execution and those participating in technical or leadership groups, but also those official representatives whose cooperation is needed for change to be embedded in their respective institutions and offices (e.g. representatives from multiple sectors or relevant ministries beyond Ministry of Environment). This factor is concerned with the level of ownership generated by the project over outputs and outcomes and that is necessary for long term impact to be realised. This ownership should adequately represent the needs and interests of all gender and marginalised groups.

Communication and Public Awareness

The Review will assess the effectiveness of: a) communication of learning and experience sharing between project partners and interested groups arising from the project during its life and b) public awareness activities that were undertaken during the implementation of the project to influence attitudes or shape behaviour among wider communities and civil society at large. The Review should consider whether existing communication channels and networks were used effectively, including meeting the differentiated needs of gender or marginalised groups, and whether any feedback channels were established. Where knowledge sharing platforms have been established under a project the Review will comment on the plans to sustain, handover or decommission the communication channel at the end of the project.

Section 3. REVIEW APPROACH, METHODS AND DELIVERABLES

The Mid-Term Review will use a participatory approach whereby key stakeholders are kept informed and consulted throughout the review process. Both quantitative and qualitative review methods will be used as appropriate to determine project achievements against the expected outputs, outcomes and impacts. It is highly recommended that the Review Consultant maintains close communication with the project team and promotes information exchange throughout the review implementation phase in order to increase their (and other stakeholder) ownership of the review findings.

The findings of the Review will be based on the following:

  - A desk review of:

Relevant background documentation, inter alia: Project M and E Plan, Project Implementation Review reports –PIR, Semi Annual Progress Reports, Quarterly Reports, Technical Project Reports – including consultancy Reports, Minutes of the Project Steering Committee and Project Technical Committee Meetings, Annual Budgets, Quarterly Financial Statements/Reports, Annual Audit Reports, Environmental and Social Management Plan, Gender Strategy and Action Plan and Draft Exit Strategy and Sustainability Plan.

Project Document and Appendices

Project design documents (including minutes of the project design review meeting at approval); including approved work plan and budget.

Other progress reports from collaborating partners/sub awardees, project related meeting minutes, relevant correspondence etc.

Monitoring Reports, Evaluations/Reviews of similar projects.

  - Interviews (individual or in group) with:

UNEP Project Manager and team members: UNEP GEF Coordinator a.i. (Ersin Esen), UNEP current Task Manager (Daniel Pouakouyou), Yunae Yi (Head of Gender and Safeguards Unit (a.i) and Safeguards Advisor, and team members; Johan Robinson (Head GEF BLD Unit), Charles Imbenzi, and Sophia Wangi, UNEP Fund Management Officer (FMO) - George Saddimbah

- Project Manager and team (Ethel S Mudenda, Chella Ngoma, Eneya M’simuko, Phillip Daka, Precious Zimba.

- Representatives of Implementing Agencies and National Governments etc.

  - Ministry of Green Economy and Environment:  – Department of Forestry Director Mr. Sitwala Wamunyima, National Project Coordinator attached to the PIU – Ms. Ing’utu Kazinga, Provincial Forestry Officer Mr. Maxwell Phiri and Provincial Focal Point Mr. Kingsley Muyunda. Environmental Management Department Director and GEF Focal Point Person – Mr. Godwin F Gondwe.

  - Department of Agriculture - Mr. Stanley Banda (National Focal Point Officer); Mr Simbarashe Mubambwe,

  - Ministry of Tourism - Department of National Parks and Wildlife – Mr. Chaka Kaumba (National) and Mr Dominic Kapokola.

  - Ministry of Local Government and Rural Development Planning – Department of Physical Planning Mr. David Namutoka and Mr. Danny Lumba.

  - Ministry of Finance and National Development Planning - Mr. Christopher Bwalya and Ms. Mwaka Kasitu (Provincial Planning Unit)

  - The Nature Conservancy (TNC) Country Director Dr. Robert Munroe, TNC Finance and Grants team Mr. Charles Mbugua and Ms. Precious Zimba Mwape

  - District teams; Mwinilunga district; (Collins Kyombela, Kennedy Chinyanta, Bovax Kachali, Serafana Banda and Zifa Ziba), Kasempa district; (O’Brien Mutinta, Kibra Mweetwa, Boston Hakapabila, and Ncimunya Haniiinga); Kalumbila district (Joseph Phiri, Dr. Lubinda Inambao, Paul Mwansa, and Joseph Zulu.

  - NGOs/CSOs/Private Sector – Dorian Tilbury (WLCP), Royd Vinya (MEEL), Norman Kalima (KCF), Dr. David Square TFL, Renier van Vuuren (Impulse Africa), Harry Malichi (Wuchi Wami), Luka Banda (Good Nature Agro), Dr. Royd Vinya (Miombo Ecosystem Enterprise Limited), Moses Phiri (Petauke Land Alliance), Dr. Dinah Mambwe (Copperbelt University), Mr. R Banda (Zambia Forestry College).

  - Community Groups: Community Forest Management Group (executive committee members) from Ntambu’s 12 CFMGs; Kelongwa Makaba CFMG and Kamilkolo CFMG; Farmer Groups from the 14 CFMGs (sample per project site); Bee keeping Groups from each of the 3 project sites, other enterprise groups, women groups/committees and representatives of the Ntambu CFMG Association.

Field visits: [indicate number of proposed country visits, as appropriate]  This will be determined with the MTR Consultant based on the reviewed data (desk review) and on the interviews with national level staff.

Other data collection tools: If needed, to be decided by the Review Consultant at the inception phase

10. Review Deliverables and Review Procedures

See Annex 1 of these TOR for a list of tools and guidance available, see Annex 2 for a list of review criteria and sub-categories to be assessed. The Review Consultant will prepare:

Inception Report: (see Annex 3 of these TOR for guidance on structure and content) containing confirmation of the results framework and Theory of Change of the project, project stakeholder analysis, review framework and a tentative review schedule.

Preliminary Findings Note: typically, in the form of a PowerPoint presentation, the sharing of preliminary findings is intended to support the participation of the project team, act as a means to ensure all information sources have been accessed and provide an opportunity to verify emerging findings.

Draft and Final Review Reports: (see Annex 4 for guidance on structure and content) containing an Executive Summary that can act as a stand-alone document; detailed analysis of the review findings organised by review criteria and supported with evidence; lessons learned and recommendations and an annotated ratings table.

Review of the draft Review Report. The Review Consultant will submit a draft report to the UNEP Project Manager and revise the draft in response to their comments and suggestions. Once a draft of adequate quality has been peer-reviewed and accepted, the Project Manager will share the cleared draft report with key project stakeholders for their review and comments. Stakeholders may provide feedback on any errors of fact and may highlight the significance of such errors in any conclusions as well as providing feedback on the proposed recommendations and lessons. Any comments or responses to draft reports will be sent to the Project Manager for consolidation. The Project Manager will provide all comments to the Review Consultant for consideration in preparing the final report, along with guidance on areas of contradiction or issues requiring an institutional response.

At the end of the review process and based on the findings in the Review Report, the UNEP Project Manager will prepare a Recommendations Implementation Plan in the format of a table, to be completed and updated at regular intervals, and circulate Lessons Learned.

11. The Review Consultant

The Review Consultant who will work under the overall responsibility of the UNEP Project Manager, Daniel Pouakouyou in consultation with the Head of Branch/Unit Johan Robinson, Fund Management Officer, George Saddimbah. The consultant will liaise with the Project Manager on any procedural and methodological matters related to the Review. It is, however, the consultant’s individual responsibility (where applicable) to arrange for their travel, visa, obtain documentary evidence, plan meetings with stakeholders (with assistance from the Partners), organize online surveys, and any other logistical matters related to the assignment. The Project Manager and project team will, where possible, provide logistical support (introductions, meetings etc.) allowing the Review Consultants to conduct the review as efficiently and independently as possible.

The Review Consultant will be hired over a period of 5 months from early 2025 to mid-July 2025 and should have the following: a university degree in environmental sciences, international development or other relevant political or social sciences area is required and an advanced degree in the same areas is desirable;  a minimum of 7 years of technical / evaluation experience is required, preferably including evaluating large, regional or global programmes and using a Theory of Change approach; and a good/broad understanding of natural resource management is desired. English and French are the working languages of the United Nations Secretariat. For this consultancy, fluency in oral and written English is a requirement. Working knowledge of the UN system and specifically the work of UNEP is an added advantage. The work will be home-based with possible field visits.

The Review Consultant will be responsible, in close consultation with the UNEP Project Manager, for overall management of the Review and timely delivery of its outputs, described above in Section 10 Review Deliverables, above. The Review Consultant will ensure that all review criteria and questions are adequately covered.

12. Schedule of the Review

The table below presents the tentative schedule for the Review.

Table 3. Tentative schedule for the Review

| Milestone | Tentative Dates |
| --- | --- |
| Inception Report | Mid-March 2025 |
| Review Mission | last 2 weeks of March 2025 |
| E-based interviews, surveys etc. | 2nd week of April 2025 |
| PowerPoint/presentation on preliminary findings and recommendations | Week 1 of May 2025 |
| Draft Report to UNEP Project Manager | End May 2025 |
| Draft Report shared with the wider group of stakeholders | Mid-June 2025 |
| Final Main Review Report | End June 2025 |
| Final Main Review Report shared with all respondents | 1st week of July 2025 |

13. Contractual Arrangements

The Review Consultant will be selected and recruited by the UNEP Project Manager under an individual Special Service Agreement (SSA) on a “fees only” basis (see below). By signing the service contract with UNEP/UNON, the consultant certifies that they have not been associated with the design and implementation of the project in any way which may jeopardize their independence and impartiality towards project achievements and project partner performance. Consultants who carry out a Mid-Term Review may not be contracted for a Terminal Review of the same evaluand. All consultants are required to sigh the Code of Conduct Agreement Form.

Fees will be paid on an instalment basis, paid on acceptance by the UNEP Project Manager of expected key deliverables. The schedule of payment is as follows:

Schedule of Payment for the Consultant:

| Deliverable | Percentage Payment |
| --- | --- |
| Approved Inception Report (as per Guidance Note) | 30% |
| Approved Draft Main Review Report (as per Guidance Note) | 30% |
| Approved Final Main Review Report (as per Report Template) | 40% |

Fees only contracts: Where applicable, air tickets will be purchased by UNEP and 75% of the Daily Subsistence Allowance for each authorised travel mission will be paid up front. Local in-country travel will only be reimbursed where agreed in advance with the UNEP Project Manager and on the production of acceptable receipts. Terminal expenses and residual DSA entitlements (25%) will be paid after mission completion.

The consultants may be provided with access to UNEP’s information management systems (e.g. PIMS, IPMR, Anubis, SharePoint etc) and if such access is granted, the consultants agree not to disclose information from that system to third parties beyond information required for, and included in, the Review Report.

In case the consultant is not able to provide the deliverables in accordance with these guidelines, and in line with the expected quality standards by the UNEP Project Manager, payment may be withheld at the discretion of the Head of Branch/Unit until the consultants have improved the deliverables to meet UNEP’s quality standards.

If the consultant fails to submit a satisfactory final product to the UNEP Project Manager in a timely manner, i.e. before the end date of their contract, UNEP reserves the right to employ additional human resources to finalize the report, and to reduce the consultants’ fees by an amount equal to the additional costs borne by the project team to bring the report up to standard or completion.

### Annex 10. GEF Portal inputs (for GEF funded projects)

The following table contains text to be uploaded to the GEF Portal. It will be drawn from the Review Report, either as copied or summarised text. In each case, references should be provided for the paragraphs and pages of the report from which the responses have been copied or summarised.

Table 10.1: GEF portal inputs

Portal Entry: What is the performance at the project’s mid-point against Core Indicator Targets? (For projects approved prior to GEF-7, these indicators will be identified retrospectively and comments on performance provided)

Response: The ECCLE project performance at mid-point against Core-Indicator Targets is highly satisfactory as results exceed expectations. The GEF Template capturing results as at MTR for all core/sub indicators that had targets at CEO Endorsement is shown as a picture below and attached separately as a separate excel file.

Portal Entry: What has been the progress, challenges and outcomes regarding engagement of stakeholders in the project/programme? (This should be based on the description included in the Stakeholder Engagement Plan or equivalent documentation submitted at CEO Endorsement/Approval)

Response: The ECCLE project performance at mid-point rates stakeholder engagement as satisfactory, based on the assessment of partnerships (B), participation (H3), and ownership (H6). The project has mobilised stakeholder widely, though some duty-bearers are not fully aware of their role and responsibilities to effective engagement. As the project is coming towards its end, an updated stakeholder engagement plan will be needed to support the development of local sustainability strategies, with clarification of key duty bearer post-project roles and responsibilities. Clarification on co-financing will also be needed.

Portal Entry: What has been the progress, challenges and outcomes regarding gender-responsive measures and any intermediate gender result areas? (This should be based on the documentation at CEO Endorsement/Approval, including gender-sensitive indicators contained in the project results framework or gender action plan or equivalent)

Response: The ECCLE project performance at mid-point rated gender-responsive measures and gender result areas as satisfactory (H4). The project approach to gender has been pro-active, in line with national aspirations. Appropriate consolidation of strategies, further modelling of gender responsive Community Forest Management as part of Knowledge Management, and the continued innovative use of gendered strategies (e.g. ‘gender champions’) will enhance achievements further.

Portal Entry: - Provide an overall ESS risk classification to be entered into the portal as either Low, Medium/Moderate, or Hight/Substantial). Please reach out to UNEP Safeguards Advisor. - Provide updates on any revisions to identified types of risk classifications/ratings and describe progress made in the implementation of the management measures as outlined in the CEO Endorsement/Approval. Please make reference to any PIR-reported ESS risks. - Provide supporting documents

Response: The ECCLE project risk ratings have mostly been assessed as low throughout the project period, and no variation had been reported at MTR review point (December 2024). The MTR findings support the low risk assessment for the ECCLE project execution, but observes that issues of social, financial and institutional sustainability (G2, Annex 20), as well as externalities such as the “Kasempa Gold Rush”, pose a risk to conservation efforts in the long run, to attaining project outcomes and contributing intermediate states. The MTR therefore recommends a risk review to accompany the proposed strategic review, together with the drafting of plans for structured consolidation, transition and sustainability (Recommendations 1, 3, 13).

Portal Entry: What has been the progress, challenges and outcomes regarding the implementation of the project's Knowledge Management Approach, including: Knowledge and Learning Deliverables (e.g. website/platform development); Knowledge Products/Events; Communication Strategy; Lessons Learned and Good Practice; Adaptive Management Actions. (This should be based on the documentation approved at CEO Endorsement/Approval)

Response: The ECCLE Knowledge Management (KM) Component got underway substantively delayed, due to difficulties in consultant and partner identification and contracting. Re-prioritisation was not done. At MTR point, the project still aimed to deliver on a rather demanding set of deliverables much behind schedule. A key event, the 2nd KM Review intended to be held just before and to support the MTR, did not take place. Due to the delayed start, the communication and sharing of KM products had only partially commenced (C2; H7). The MTR proposes to consolidate and refocus efforts towards supporting the development of “CFM models for mainstreaming” in synergy with output 1.5. (Recommendation 7).

Portal Entry: What are the main findings of the review?

Response: Overall, although much delayed in start-up, the implementation of the ECCLE project got underway briskly in 2022. The project is aligned with Zambian Government, UNEP and GEF priorities, it is well managed and is progressing well. At local level, the beneficiaries, the local communities are engaged and demonstrate ownership and willingness to embrace community forestry. Substantive efforts have been made to integrate gender equality and tangible achievements are visible on the ground. At strategic level, weaknesses in project design have impeded progress and the project will need to review some of the fundamental underpinnings of CFM modelling and mainstreaming. Provided a timely closure through strategic consolidation and phased exit is ensured, the proposed consolidation of activities, risk and strategic reviews and sustainability planning are undertaken expediently, the ECCLE project stands a fair chance to achieve a successful outcome, contribute significantly to community forestry development in Zambia and its expected long-term biodiversity and livelihood impacts (V Conclusions).

Portal Entry: Actual Sources of Co-financing

Response: ECCLE Co-Financing reporting as per June 2024 (Source: PIU/TNC) Sources of Co-financing; Name of Co-financier; Type of Cofinancing; Investment Mobilized; Amount ($) (30.06.2024). Recipient Country Government; Ministry of Green Economy and Environment; In-kind; 7,200,000; $26,452,617. Recipient Country Government; Ministry of Agriculture; In-kind; 1,900,000; $647,734. Recipient Country Government; Ministry of Tourism and Arts; In-kind; 750,000; $ 7,765. Non-Government Organization (International); The Nature Conservancy (TNC); In-kind; 300,000; $ 610,243. Grant (investment); 1,700,000; $ 738,937. Private Sector; Trident Foundation Ltd for Kalumbila Minerals Limited; In-kind and grant; 2,250,000; $190,387. Private Sector; First Quantum Minerals (West Lunga Conservation Project); In-kind and grant; 2,500,000; $ 401,650. Non-Government Organization (International); WWF-Zambia; In-kind; 3,780,000; Nil (1). (1) No co-financing or formal response reported for over a year since request sent out by EA in 2024. MTR recommends for removal of WWF from list of co-financiers.

Portal Entry: Key Risks (please refer to ANNEX XI below)

### Annex 11. GEF Risks to achieving project outcomes (for GEF funded projects)

Summarize risks that might affect the achievement of desired outcomes and the mitigation measures which are planned or already undertaken to address these. The risk rating should reflect the residual risk to achieving outcomes after considering the implementation of mitigation measures. The rating scale is: High, Substantial, Moderate, Low. See the GEF Risk Appetite document (GEF/C.66/13) for more information and its Annex B for a description of each risk category. Note that the rating for the “Environment and Social” category should be the same as the risk rating for Safeguards.

| RISK CATEGORIES | RATINGS | ASSESSMENT AND MITIGATION MEASURES |
| --- | --- | --- |
| CONTEXT |  |  |
| Climate | Moderate | Climate change increases the risk of short spells and seasonal drought affecting smallholders in Central Southern Africa. In the 2023/2024 agricultural season, the El Niño oscillation brought about severe rainfall disturbances and drought, which affected the project area as well. A national emergency was proclaimed in February 2024. The events disturbed and delayed the ECCLE agricultural and enterprise development components. In the long run, the introduction of climate smart agriculture and income diversification, will mitigate risks at household level. However, drought-induced loss of income will impact the pace at which innovations may be embraced and community enterprise may gain sustainability. |
| Environment and Social | Low | Initial project ESS risk ratings were very low. The project has put in place a gender-responsive strategy, established new gender platforms, an ESM framework, a grievance mechanism and other measures. Provided appropriate mitigation measures are put in place locally, in sustainability plans, and integrated into mainstreaming models, this project will have very positive environmental and social impacts. |
| Political and Governance | Low | The project supports the implementation of Zambia’s policy to sustainably manage forest and other natural resources through the devolution of user rights to local communities, as outlined in the 2014 Forest Policy and 2015 Forest Act. There is political will to expand community forestry across the country, and objective which the project greatly may support through developing good practice and refine existing models, making them ready for mainstreaming and policy development and legal review. Aligning knowledge management closer to model development as recommended by the MTR will further reduce residual risk. |
| INNOVATION |  |  |
| Institutional and Policy | Moderate | The project is designed to address institutional and policy issues through the development of CFM models for mainstreaming in support of integrated land use planning and the development of appropriate subsidiary legislation. Delay in producing key PLIR deliverables and limited Forestry Department engagement have substantively increased the risk of failure. With renewed focus and strategic reorientation towards model development and sustainability, the project may make a significant contribution to ongoing processes for the revision of key legislation (Forest Act, Wildlife Act). |
| Technological | Low | The ECCLE project has contributed to developing appropriate technologies for sustainable forest management, including refining Community Forestry Management (CFM) models, developing gender responsive approaches, and adapting climate smart agriculture practices for sustainable land management in the province. Implementation delays have had a negative impact on the possibilities to test and validate these innovations. With a timely closure through strategic consolidation and phased exit strategy, the project will be able to consolidate achievements, learn lessons and package ‘good practice’ and appropriate technologies that will make them available for replication and mainstreaming post-project. |
| Financial and Business Model | Moderate | The development of a self-financing business model for community forestry, ready for replication and mainstreaming in Zambia, is one of the ambitious strategic objectives of the ECCLE project. Regrettably, within the current project time span, this will not be achieved. However, the project has the potential and the drive to establish a sound foundation for sustainable natural resource-based community enterprise, that the local beneficiaries may develop further in envisaged continued partnerships with their private sector Corporate Social Responsibility partners. Their likelihood of success is good, provided the project optimises on the timely closure through strategic consolidation and phased exit strategy, continues vigorous training and capacity-building, prepares detailed sustainability plans and helps local communities negotiate viable agreements. |
| EXECUTION |  |  |
| Capacity for Implementation | Moderate | Local communities in Zambia face many challenges in meeting the necessary standards for governance and management of community resource structures and enterprises. Provided the remaining project time and resources are used wisely: community awareness, training and capacity-building is prioritized, robust networks of support organisations are identified, detailed sustainability plans are prepared, and viable partner agreements are negotiated, the ECCLE communities will have fair chance to succeed in the long-term. |
| Fiduciary | Moderate | The project is following UNEP/GEF financial procedures and meeting requirements and has undergone a financial audit by an independent auditor. Assuming outstanding issues of delays in contracting and procurement are addressed; co-financing from Government is obtained to complete on-going climate smart agriculture adaptation trials; and available funds are allocated wisely for the timely closure through strategic consolidation and phased exit strategy, the project is likely to close successfully. However, local community forestry groups need to develop skills and capacities to financially manage their future. A wise project exit budget, smart sustainability strategies, and well negotiated viable partner agreements will help mitigate the risk. |
| Stakeholder | Moderate | Stakeholder engagement with the ECCLE project has been good as the project objectives are well aligned with Government policy and institutional mandate. Unclear roles and responsibilities and the lack of independent operational funds have reduced ownership. Provided the Forestry Department and other key government duty bearer to shoulder their responsibilities in order to ensure that the project achievements, not least the CFM models, good practices and tested technologies, are carried forth into mainstreaming, the risk of stakeholder failure will be mitigated. Private sector engagement has been good, though delays in contracting and disputes dampened progress. Provided community capacity in strengthened, viable agreements are negotiated for local communities with their CSR partners, the risk of stakeholder failure will be greatly mitigated. |
| Other: threats to biodiversity conservation / sustainable forest management from mining and other land use | Moderate | Mining in Northwestern Province has expanded significantly over the past twenty+ years. Since the opening of the first big mine at Lumwana, the miombo woodlands have encountered previously unseen levels of in-migration, labour migration, exploration and artisanal mining. The recent “gold rush” in Kasempa and Manyinga districts is a case in point, raised as a risk in the recent PIR, as illegal miners entered the CFMA to dig gold. Uncontrolled unsustainable land use remains a major threat to community forestry management. Provided the project puts in place beneficiary sustainability plans negotiated with corporate social responsibility partners, as planned, the threat will be substantively mitigated. |
| Overall Risk Rating | Moderate | There is a moderate residual risk to achieving outcomes after considering the implementation of mitigation measures. |

A note on GEF risk rating:

The above rating is based on the GEF Risk Appetite document (GEF/C.66/13). The risk rating reflects the residual risk to achieving outcomes after considering the implementation of mitigation measures. The rating scale is: High, Substantial, Moderate, Low. See the document link for more information and document Annex B for a description of each risk category.

### Annex 12. Theory of Change (original)

Table 12.1: Assumptions in the logic model (original)

### Annex 13. Project Results Framework (original)

| Project Title: Ecosystem Conservation and Community Livelihood Enhancement in Northwestern Zambia |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Project Objective | Objective level Indicators | Baseline | Targets and Monitoring Milestones | Means of Verification | Assumptions & Risks | UNEP MTS reference* |
| To strengthen community-based sustainable management of forest landscapes, and provide improved livelihood opportunities for targeted forest- dependent rural communities in Zambia's Northwest Province | - Hectares of dryland forests and lands under improved, more sustainable management | a. 189,339ha transferred to CFMG, but without viable SFM systems | - EOP: 130,000 ha Mid-Point Target: 50,000 ha | - Data collected by community guards, district DF & DNPW agents, PIU staff. | - Benefits of CFM provide adequate incentives for forest conservation. Low risk of inadequacy | Healthy and productive ecosystems |
|  | - % change in the income of women, men and youth from forest-based products and services. | b. ZMW 2,100 | - EOP: 15% increase (ZMW 2,415) Mid-Point target: None – no survey | - Semi-annual and Annual reports Verified by Mid- Term and Final Evaluation teams. Baseline survey redone in Yr 5. | - Profitable enterprises developed. Low to moderate risk enterprises not profitable. |  |

| Project Outcomes and outputs | Outcome Indicators | Baseline | Targets and Monitoring Milestones | Means of Verification | Assumptions & Risks |  | MTS EA |
| --- | --- | --- | --- | --- | --- | --- | --- |
| COMPONENT 1: Developing the enabling regulatory and planning frameworks for community-based, sustainable forest management |  |  |  |  |  |  | EA (a) The health and productivity of marine, freshwater and terrestrial ecosystems are institutionalized in education, monitoring and cross-sector and transboundary collaboration frameworks at the national and international level |
| Outcome 1: Sustainable forest management (SFM) mainstreamed in local development plans in target Community Forest Management Areas (CFMAs) | - Area covered by recognized CFMAs with operational forest/NR management systems | - 78,347ha covered by existing CFMA in Kasempa District, but w/o viable management systems. | - End of project Target: 120,000 ha. Mid-Point Target: 120,000 ha. | - The legal documents creating the CFMA, Mid- term and EOP evaluations | - Community stakeholders develop capacities for accountability, transparency, sound management of funds and equitable sharing of costs and benefits. Low risk they fail to develop capacities |  |  |
|  | - Number of District Integrated Development Plans with SFM mainstreamed addressing gender equality | - No. DIDP mainstreaming CFM in the 3 districts | - EOP: 2 MTT: 1 | - Copies of approved DIDP. MT & EOP evaluations | - District councils commit to support for CFM development. Moderate risk of inadequate support. |  |  |
| Output 1.1. Comprehensive assessment of forests and communities in the project area – sex and age disaggregated. | 1.1.1 Number of forest department and PIU staff trained in GIS | N/a | 20 | Training attendance list, Activity report, Training Evaluation summary | Assumption: The staff trained in GIS have the necessary foundational knowledge and skills to effectively apply GIS techniques in their work on the project. Risk: The training may not lead to sustained GIS capacity within the forest department and PIU due to inadequate follow-up support, insufficient hands-on practice, or high staff turnover rates. Staff may not have the necessary baseline skills or may be unwilling to participate. |  |  |
|  | 1.1.2 Number of GIS maps of the project sites and geocoded locations of interventions supported by the Project generated | N/a | 3 | Activity reports, Arc GIS pro projects, PIR | The GIS maps and geocoded locations accurately reflect the current spatial configuration and boundaries of the project sites and interventions. Risk: Data inaccuracies or software/hardware issues could delay map creation |  |  |
|  | 1.1.3. Number of In-depth Biophysical assessments conducted with reports generated | N/a | 1 | Assessment report | The biophysical assessments are conducted using standardized and scientifically valid methods, ensuring consistent and reliable results. The biophysical assessments may not accurately capture the complexity and variability of environmental conditions due to limitations in sampling design, data collection techniques, or equipment constraints |  |  |
|  | 1.1.4 Number of detailed in-depth socioeconomic assessments conducted with reports generated | N/a | 1 | Socio-economic assessment report | The data collected for the socioeconomic assessments is accurate, reliable, and comprehensive, reflecting the true situation. The assessments may not capture a complete or accurate picture of the socioeconomic context due to methodological limitations, |  |  |
|  | 1.1.5. Number of reports on analysis of optimal scale of operations generated | N/a | 1 | Socio-economic assessment report | Assumption: The analysis of optimal scale of operations is based on reliable and comprehensive data, including accurate cost and production data. Risk: The reports on optimal scale of operations may not accurately reflect the true situation due to methodological limitations, or failure to account for external factors that could impact operations. |  |  |
| Output 1.2. In-depth awareness raising on inclusive, gender sensitive CFMA creation leading to the declaration by government of the new or modified CFMG | 1.2.1. Number of Maps of Community Forest Management Areas (CFMA) boundaries generated | N/a | 3 | ILUPs, Georeferenced maps, Shapefiles in ArcGis Pro. | Assumption: The boundaries of the Community Forest Management Areas (CFMA) are clearly defined and agreed upon by all relevant stakeholders. Risk: The maps of CFMA boundaries may not accurately reflect the true boundaries or be accepted by all stakeholders due to potential disputes, inconsistent data, or inadequate community engagement and validation. |  |  |
|  | 1.2.2 Hectares of CFMAs mapped | N/a | 120,000 | Georeferenced maps, Activity reports, Shapefiles in Arc GIS pro projects, PIR | Assumption: The mapping of CFMAs accurately reflects the actual area under community forest management. Risk: The actual area of CFMAs may be inaccurately recorded or mapped due to errors in measurement, inconsistent boundary demarcation, or unauthorized changes in land use |  |  |
|  | 1.2.3. Number of CFMG executive committee members trained in constitution development | N/a | 45 | Training/activity reports, Training attendance list, Training Database | The training provided to CFMG executive committee members is effective in building their capacity to develop a constitution that reflects the needs and aspirations of the community. Risk: The trained executive committee members may not be able to effectively apply their knowledge and skills in developing a constitution due to lack of follow-up support, inadequate community engagement, or internal conflicts within the committee |  |  |
|  | 1.2.4. Number of CFMG constitutions developed and or reviewed | N/a | 3 | Activity report, Meeting reports, Training reports, CFMG constitutions, | The developed or reviewed constitutions accurately reflect the collective decisions and agreements of the CFMG members and align with relevant laws and regulations. Risk: The constitutions may not be effective or sustainable due to inadequate community participation, lack of clear guidelines, or insufficient consideration of potential conflicts or disputes. |  |  |
|  | 1.2.5. Number of Community Forest Management Groups recognized by government | N/a | 3 | Letter of recognition, Activity reports | The Community Forest Management Groups (CFMGs) have the necessary capacity, organization, and documentation to meet the government's requirements for recognition. The government recognition of Community Forest Management Groups (CFMGs) is based on a clear and transparent process, ensuring that all recognized groups meet the necessary criteria. Risk: The recognition of CFMGs by the government may be delayed, inconsistent, or influenced by external factors, potentially undermining the legitimacy and effectiveness of the community-led forest management initiatives. |  |  |
| Output 1.3. Sustainable forest and natural resource management promoted in gender responsive District Integrated Development Plans and CFMA management plans | 1.3.1. Number of Integrated land use plans (ILUPs) developed for communal lands belonging to CFMG | N/a | 3 | Finalized Integrated Land use plans, Activity reports, Semi-annual reports, | Assumption: The Integrated Land Use Plans (ILUPs) developed for communal lands are inclusive, participatory, and based on accurate spatial data and stakeholder engagement. Low Risk: The ILUPs may not be effectively implemented or sustained due to lack of resources, conflicting interests among stakeholders, or inadequate institutional capacity to enforce and monitor plan provisions |  |  |
|  | 1.3.2. Number of CFA management unit maps generated | N/a | 3 | CFMG ArcGIS Shapefiles, CFMG management plan | Assumption: The CFMA management unit maps accurately reflect the spatial arrangement and boundaries of the community forest resources and are accepted by all stakeholders. Low Risk: The maps may contain errors, inconsistencies or omissions, leading to disputes or ineffective management of the community forest resources due to inadequate data validation, stakeholder engagement or cartographic expertise. |  |  |
|  | 1.3.3. Number of Natural Resource and Forest management plans finalized, submitted by CFMGs and approved by FD | N/a | 3 | Copies of approved NRM plans, Quarterly Output Indicator data collection tool | Assumption: The Natural Resource and Forest management plans submitted by CFMGs are comprehensive, scientifically sound, and aligned with national forestry policies and regulations, ensuring timely approval by FD. Risk: The plans may not be approved or implemented effectively due to technical deficiencies, inadequate stakeholder consultation, or delays in Forestry Department review and approval processes |  |  |
|  | 1.3.4. Number of DIDPs with CFM mainstreamed | N/a | 2 | Plans committee reports, Special Council meeting reports, Ordinary council meeting reports, Plan committee reports. | Assumption: The District Integrated Development Plans effectively incorporate community forest management (CFM) priorities and objectives, ensuring alignment with national and local development agendas. Risk: CFM may not be sustainably mainstreamed into District plans due to limited institutional commitment, inadequate budget allocation, or insufficient capacity building for local authorities to support CFM initiatives. |  |  |
| Output 1.4: Knowledge management (KM) system developed in support of gender sensitive community management of forests and natural resources | 1.4.1. Number of participatory reviews conducted | N/a | 3 | Participatory Review reports. Attendance register | Assumption: Stakeholders will actively participate and provide valuable insights during the knowledge management participatory reviews. Risk: Low participation or engagement from stakeholders could result in incomplete or biased reviews, affecting the quality of the knowledge management process |  |  |
|  | 1.4.2. Number of KM networks developed (semi-annual newsletters and Internet CFM discussion groups) | N/a | 2 | Semi-annual newsletters/ Links to CFM discussion platforms, KM reports | Assumption: There will be sufficient interest and collaboration among stakeholders to establish and maintain knowledge management (KM) networks, including semi-annual newsletters and Internet CFM discussion groups. Risk: Limited engagement or technical challenges could impede the development and sustainability of these KM networks. |  |  |
|  | 1.4.3. Number of regional exchange events attended | N/a | 3 | Regional exchange visit reports | Assumption: PIU and local community representatives will actively engage and participate in regional exchange events, contributing to the successful sharing of knowledge and best practices Risk: Due to the nature of external organizations arranging regional exchange events, there may be scheduling conflicts, resource limitations, or misalignment with local project goals, potentially reducing the effectiveness of these events. |  |  |
|  | 1.4.4. Number of CFM course material prepared and made available for integration in curricula by universities and colleges | N/a | 2 | CFM review reports, CFM curricular Modules | Assumption: Developing CFM course materials will be thorough and collaborative, meeting educational standards. Risk: Development may face challenges like insufficient collaboration, lack of expertise, or delays, affecting quality and timely availability. |  |  |
|  | 1.4.5. Number of universities/colleges integrating CFM course material in their curricula by universities and colleges | N/a | 2 | CFM review reports, Curricula review reports/ Revised curricula | Assumption: Universities and colleges will be willing and able to integrate the prepared Community Forest Management (CFM) course materials into their curricula. Risk: Due to varying institutional priorities and resource constraints, universities and colleges may face challenges in integrating the CFM course materials into their existing curricula. |  |  |
| Project Outcomes and outputs | Outcome Indicators | Baseline | Targets and Monitoring Milestones | Means of Verification |  | Assumptions & Risks | MTS EA |
| COMPONENT 2: Promoting the conservation and sustainable use of natural resources in community-managed forests |  |  |  |  |  |  |  |
| Outcome 2: Improved management of forest resources enhances gender equality and contributes to enhanced welfare and livelihoods | - Number of CFMG receiving funds from their investments and dispersing funds in accordance with their benefit sharing plan and investment plan. | - None | - EOP: At least 6 MTT: At least 3 | - Semi-annual report |  | - Successful development of profitable enterprises and respect for plan for equitable sharing of benefits. |  |
|  | - % of men, women and youth satisfied with the current CFMG plan for equitable sharing of costs and benefits | - Not applicable | - EOP: Men: 50% Women: 60% Youth: 50% MTT: Men 50% Women: 40% Youth: 30% | - CFMG Accounts Evaluation teams Project financial reports; CFMG audit reports |  | - Communities choose to organize at a large enough economic/geographic scale. Low risk they go small scale. |  |
|  | - Amount of investments in community businesses made by Project and by CFMG Beneficiaries disaggregated by gender | - None | - EOP: US$ 1,259,000 by Project and $100,000 by CFMG Gender targets: Men 45% Women 35% Youth 20% MTT: 600,000 by Project and 20,000 by CFMG Men: 55%, Women 30%, Youth 15% | - CFMG Accounts Evaluation teams Project financial reports; CFMG audit reports. |  | - CFM benefits provide incentives for enforcement of SFM ban on deforestation, Low risk. |  |
| Output 2.1: Gender responsive business plans developed in support of each community forest management group | 2.1.1. No. of CFMG members trained in Business and investment Planning | N/a | 45 | Training/activity reports, Training attendance list, Training Database |  | Assumption: Community Forest Management Group (CFMG) members will be willing and able to participate in business and investment planning training sessions. |  |
|  | 2.1.2. Number of gender responsive business plan developed | N/a | 3 | CFMG business plans, Activity reports |  | Assumption: Community Forest Management groups have the necessary resources and support to develop comprehensive business plans. Risk: Limited capacity and resource constraints within Community Forest Management groups may impede the development and quality of business plans. |  |
|  | 2.1.3. Number of gender responsive investment plans developed | N/a | 3 | CFMG business plans, CFMG Investment, Activity reports |  | Assumption: CFMGs have the necessary knowledge and resources to effectively develop investment plans that prioritize equitable benefits and women's empowerment |  |
| Output 2.2 Gender responsive community-based enterprises developed based on the business plan | 2.2.1. No. of CFMG members trained in Enterprise Plan Development | N/a | 45 | Training/activity reports, Training attendance list, Training Database |  | Assumption: The training provided to CFMG members on Enterprise Plan Development equips them with the necessary skills and knowledge to create viable and sustainable forest-based enterprises. Risk: Trained CFMG members may not effectively apply their knowledge due to lack of follow-up support, limited access to finance, or inadequate market linkages, hindering the successful implementation of enterprise plans. |  |
|  | 2.2.2. Number of operational CFMG-owned and locally owned forest and NR-based businesses | N/a | 3 | Enterprise Databases, Enterprise User-group registers, |  | Assumption: CFMGs have the necessary support and resources to successfully establish and operate nature-based enterprises. Risk: CFMGs encounter operational challenges such as inadequate infrastructure, limited technical skills, and insufficient market access, which could impede the successful launch and sustainability of their nature-based enterprises. |  |
|  | 2.2.3. Number of Technical staff recruited, and onboarded in the CFMG | N/a | 3 | Recruitment documentation/Contracts, Technician activity reports |  | Assumption: Recruited technical staff possess necessary skills and expertise to support CFMG's forest management and business operations. |  |
|  | 2.2.4. No. of Honorary Forest Officers recruited and deployed | N/a | 60 | HFO registers, Patrol Databases, HFO pass out certificates, Activity reports |  | Assumption: Recruited Honorary Forest Officers have the necessary expertise and commitment to effectively support forest conservation and management |  |
| Output 2.3. Capacities developed for gender responsive good governance, NRM and business management | 2.3.1. Number of training needs assessment undertaken | N/a | 1 | TNA report, CNA inception report |  | Assumption: Training needs assessments accurately identify CFMG's knowledge gaps and capacity building requirements. Risk: Inadequate assessment methodologies or insufficient stakeholder engagement may lead to inaccurate training needs identification, hindering effective capacity building. |  |
|  | 2.3.2. Number of standard training modules developed (business management and NRM) | N/a | 2 | Standard training modules |  | Assumption: Developed training modules are relevant, effective, and aligned with CFMG's business management and natural resource management (NRM) needs. |  |
|  | 2.3.3 No. of CFMG members trained in good governance and Natural Resource Management | N/a | 45 | Training/activity reports, Training attendance list, Training Database |  | Assumption: Trained CFMG members will apply gained knowledge and skills to enhance good governance and sustainable Natural Resource Management practices. Risk: Limited retention of training information, inadequate follow-up support, or resistance to change may hinder effective implementation of learned practices. |  |
|  | 2.3.4. No of HFOs trained in Forest protection and NRM. | N/a | 60 | Training/activity reports, Training attendance list, Training Database |  | Assumption: Trained Honorary Forest Officers (HFOs) will effectively enforce forest protection laws and implement sustainable Natural Resource Management (NRM) practices. Risk: Inadequate training quality, insufficient field support, or conflicting community interests may undermine HFOs' ability to effectively protect forests and manage natural resources. |  |
|  | 2.3.5. No. of CFMG members trained in Finance and Business Management | N/a | 45 | Training/activity reports, Training attendance list, Training Database |  | Assumption: Trained CFMG members will apply financial and business management skills to improve operational efficiency, sustainability, and profitability. Risk: Limited practical application, inadequate follow-up coaching, or lack of access to finance may hinder trained members from effectively implementing learned financial and business management skills. |  |
|  | 2.3.6 No. of CFMG/ Champions trained in Enterprise Plan Development | N/a | 45 | Training/activity reports, Training attendance list, Training Database |  | Assumption: Trained CFMG members and champions possess the expertise and willingness to effectively cascade enterprise plan development training to other community members Risk: Insufficient mentorship, inadequate resources, or champion turnover may compromise the sustainability and quality of cascade training, limiting community-wide impact. |  |
|  | 2.3.7. No. of TBU/CFMG members trained in Credit Appraisal | N/a | 45 | Training/activity reports, Training attendance list, Training Database |  | Assumption: Trained Technical Business Unit/CFMG members will effectively assess creditworthiness, manage risk, and make informed lending decisions. Risk: Inadequate practical application, insufficient follow-up support, or biased credit appraisal may lead to poor lending decisions and compromised financial sustainability for the CFMG. |  |
|  | 2.3.8. No. of TBU/CFMG members trained in Loan Management | N/a | 45 | Training/activity reports, Training attendance list, Training Database |  | Assumption: Trained TBU/CFMG members will effectively manage loan portfolios, reduce default rates and ensure financial sustainability. Risk: Inadequate systems for tracking repayments, insufficient enforcement of loan conditions, or lack of follow-up support may lead to poor loan performance, increased defaults, and financial instability. |  |

| Project Outcomes and outputs | Outcome Indicators | Baseline | Targets and Monitoring Milestones | Means of Verification | Assumptions & Risks | MTS EA |
| --- | --- | --- | --- | --- | --- | --- |
| COMPONENT 3: Enhancing the sustainability and productivity of agricultural practices in community-managed forests |  |  |  |  |  |  |
| Outcome 3: Improved productivity, gender equality and climate resilience from sustainable agricultural practices on the lands zoned for agriculture adjacent to community- managed forests | - Number of farmers (disaggregated by sex and age) adopting gender sensitive sustainable agricultural practices | - 156 farmers (107 Male (69%), 49 Female, Youth (31%)) | - EOP: 10,000 additional farmers – 45 % men, 35% women, 20% youth: MTT: 3000 new farmers; 60% men, 30% women, men & 10% youth: | - Monitoring by PIU, SA experts and collaborators. Annual adaptive management reviews; | - Full participation of women and youth. Low risk of non- participation |  |
|  | - Area under more sustainable agricultural practices in number of hectares | - 52.1 Ha | - EOP: 10,000ha. MTT: 3,000 ha. | - Extension agents Monitoring by PIU. Use of SHARP tool for monitoring resilience (relevant baseline/targets TBD) | - Attractive, varied technologies for SA and climate smart agriculture. Low to moderate risk suitable technologies not adequate. |  |
| Output 3.1. Gender responsive network of actors developed, and capacity built to deliver sustainable agricultural practices on the lands zoned for agriculture adjacent to community- managed forests | 3.1.1. Number of participatory surveys conducted of farmers and extension agents to establish a baseline for training | N/a | 1 | Baseline survey report, Training Needs assessment report | Assumption: Participatory surveys accurately capture farmers' and extension agents' training needs, providing a reliable baseline for targeted capacity building |  |
|  | 3.1.2. Number of comprehensive information, communication and education materials (ICE) disseminated to the target agricultural communities | N/a | 1 | ICE materials, Brochures, Leaflets | Assumption: Disseminated Information, Communication, and Education (ICE) materials effectively inform and educate target agricultural communities, enhancing knowledge and practice adoption. Risk: Limited accessibility, relevance, or coverage of ICE materials may reduce their impact, leaving some communities uninformed or misinformed. |  |
|  | 3.1.3. Number of extension staff and change agents trained in sustainable agricultural practices | N/a | 50 | Training report, Capacity building plan. | Assumption: Trained extension staff and change agents will effectively disseminate and demonstrate sustainable agricultural practices to farmers. Risk: Inadequate post-training support, insufficient resources, or competing priorities may hinder trained extension staff and change agents from applying and scaling up sustainable agricultural practices |  |
| Output 3.2. Capacity building provided to encourage the adoption of gender responsive, sustainable agricultural practices in agricultural zones in villages adjacent to community forests | 3.2.1. Number of farmer field schools established | N/a | 25 | Activity reports, Farmer field reports. | Assumption: Established farmer field schools provide effective hands-on training and peer-to-peer learning, enhancing farmers' knowledge and adoption of sustainable agricultural practices. Risk: Lack of clear curriculum, inadequate trainer expertise, and insufficient monitoring and evaluation may compromise the quality and effectiveness of farmer field schools |  |
|  | 3.2.2. Number of Annual participatory adaptive management reviews undertaken | N/a | 3 | Annual participatory adaptive management reports generated, | Assumption: Annual participatory reviews identify effective sustainable agriculture practices and inform evidence-based adjustments. Risk: Insufficient representation or poor facilitation may limit review effectiveness. |  |
|  | 3.2.3 Number of participants taking part in annual Agriculture adaptive management reviews | N/a | 300 | Annual participatory adaptive management reports generated, Attendance lists | Assumption: Participants in annual Agriculture adaptive management reviews actively contribute to identifying best practices and solutions, improving sustainable agriculture implementation. Risk: Low stakeholder participation or representation (e.g., farmers, extension officers) may compromise review effectiveness and relevance |  |
|  | 3.2.4. Hectarage of agricultural land adjacent to CFMAs mapped | N/a | 10,000 | Farmer Bio-data database on ESRI ArcGIS, Farmer | Assumption: Accurate land mapping informs effective land-use planning and sustainable agriculture expansion. Risk: Inaccurate or outdated mapping data may misguide interventions, failing to address critical areas of agricultural expansion or forest encroachment. |  |
|  | 3.2.5. Number of farmers trained in CSA technologies and practices | N/a | 10,000 | Training activity report, Training Database, attendance registers, | Assumption: Training farmers in Climate-Smart Agriculture (CSA) technologies and practices enhances their resilience, productivity, and sustainable land management. Risk: Limited follow-up support, inadequate resources, or poor extension services may hinder trained farmers' ability to adopt and scale up CSA practices |  |
| Output 3.3. Crop and livestock male, female and young farmers adjacent to CFMAs equally assisted to sustainably improve their productivity and net income | 3.3.1. Number of field days held at farmer field-schools | N/a | 3 | farmer field school reports | Assumption: Field days at farmer field-schools effectively demonstrate and promote adoption of sustainable agriculture practices, technologies, and innovations. Risk: Poor organization, inadequate facilitation, or insufficient stakeholder participation may reduce field day impact and knowledge sharing. |  |
|  | 3.3.2. Number of farmers (unique) that graduate from farmer field schools | N/a | 1,800 | farmer field school reports | Assumption: Field school graduates become change agents, influencing peers and contributing to community-wide adoption of sustainable agriculture. Risk: Limited tracking or follow-up with graduates may prevent assessment of long-term impact, identification of best practices, or replication of successful models. |  |
|  | 3.3.3. Number of farmers linked to business support services | N/a | 5,000 | Signed Agreements | Assumption: Linking farmers to business support services enhances their access to markets, finance, and technical assistance, improving livelihoods. Risk: Poor quality or unresponsive BSS providers may fail to meet farmers' needs, hindering sustainable business growth. |  |
|  | 3.3.3. Number of farmers linked to grower schemes and off-takers | N/a | 5,000 | Signed Agreements | Assumption: Linking farmers to grower schemes and off-takers ensures stable markets, improves income, and incentivizes sustainable agriculture practices. Risk: Failure to establish clear quality standards, grading, or payment terms may lead to disputes and undermine farmer-off-taker relationships. |  |

Project outputs: - Comprehensive assessment of forests and communities in the project area – sex and age disaggregated. - In-depth awareness raising on inclusive, gender sensitive CFMA creation leading to the declaration by government of the new or modified CFMG. - Sustainable forest and natural resource management promoted in gender responsive District Integrated Development Plans and CFMA management plans. - Knowledge management (KM) system developed in support of gender sensitive community management of forests and natural resources. - Subsidiary legislation for forestry reviewed and revised in support of gender responsive sustainable forest management. - Training and deployment of a corps of gender sensitive community forest guards in targeted CFMAs - Gender responsive business plans developed in support of each community forest management group. - Gender responsive community-based enterprises developed based on the business plan. - Capacities developed for gender responsive good governance, NRM and business management. - Gender responsive network of actors developed, and capacity built to deliver sustainable agricultural practices on the lands zoned for agriculture adjacent to community-managed forests. - Capacity building provided to encourage the adoption of gender responsive, sustainable agricultural practices in agricultural zones in villages adjacent to community forests. - Crop and livestock male, female and young farmers adjacent to CFMAs equally assisted to sustainably improve their productivity and net income.

### Annex 14. Intervention Logic Narrative (original)

The project’s theory of change can be summarized as: IF the enabling regulatory and planning frameworks for community-based, sustainable forest management are developed by in-depth awareness raising on inclusive, gender sensitive CFMA creation leading to the declaration by government of the new or modified CFMG, and by mainstreaming sustainable community forest and natural resources management into district integrated development plans (DIDP); and IF the project promotes the conservation and sustainable use of natural resources in community-managed forests by assisting communities to develop gender responsive business plans and investment plans, and by building capacity in self-financing forest/natural resource management; and IF the sustainability and productivity of agricultural practices in community- managed forests are enhanced by developing a network of gender responsive network of actors and building capacity to deliver sustainable agricultural practices on lands zoned for agricultural purposes adjacent to community managed forests, and by facilitating access to the wider agricultural market environment for male, female and young farmers managing diverse and sustainable agricultural systems;

THEN by February 2026, approximately 130,000 hectares of dryland forests and lands will be under improved, more sustainable management in North Western Zambia; there will be a 15% change in the income of women, men and youth from forest-based products and services; 120,000 hectares of dryland forests and lands will be covered by recognized CFMAs with operational forest/NR management systems; 2 District Integrated Development Plans (DIDP) will have SFM mainstreamed addressing gender equality; 6 CFMGs will have begun receiving funds from their investments and dispersing accordance with their benefit sharing plan and investment plan; 50% of men, 60% of women and 50% of youths would have been satisfied with the current CFMG plan for equitable sharing of costs and benefits; $1,259,000 will be invested in community business by project and $100,000 by the CFMG beneficiaries; 10,000 additional farmers will have adopted gender sensitive sustainable agricultural practices; 10,000 hectares of land purposed for agriculture will be under more sustainable agricultural practices; and ultimately community-based sustainable management of forest landscapes will be strengthened and improved livelihood opportunities will be provided for targeted forest-dependent rural communities in Zambia's North Western Province

BECAUSE structured communities will have been empowered to control access to their forests, to sustainably manage these forests and protect their forests from conversion to agriculture or other land uses as they receive substantial benefits from managing their forests greater than that from destructive practices; and BECAUSE each CFMG will have its own business plan based on local market assessment, local forest/NR potential, analysis of profitability, investment and staff needs; and BECAUSE self-financing models  of community forest management will have been tested and proven; and BECAUSE conversion of forest to agriculture is greatly reduced as farmers adopt sustainable technologies that can both maintain soil fertility at high levels of productivity and are profitable for the farmer; and BECAUSE efforts will have been made to develop market linkages with input, output, service and financial markets to improve farmer yields through sustainable agriculture.

### Annex 15. ECCLE Project Stakeholders @ Mid-Term Review: power and interest

| Stake-holder Cate-gory | Name of Stakeholder | Role | Level of |  |
| --- | --- | --- | --- | --- |
|  |  | (as per Project Document, p. 45-47) | Power | Interest |
| Public Sector | Ministry of Green Economy and Environment (MGEE); Forestry Department (FD) | - Project oversight and implementation. - Supports the planning, management, monitoring and enforcement of protected forest areas. - Facilitates the development of public-private-community partnerships in the stewardship of protected forests. | HIGH | HIGH |
|  | Department of Environmental Management | - Government host to GEF (Operational Focal Point) | HIGH | HIGH |
|  | Department of Climate Change | - During implementation: Co-opted in Project Steering Committee (PSC) | HIGH | HIGH |
|  | Ministry of Tourism; Department of National Parks and Wildlife (DNPW) | - Project collaborating partner in implementation. - Supports VAGs in targeted GMAs in planning and control of land use in GMAs in partnership with communities; monitoring of wildlife populations; administration of Village Scout programs; negotiation of hunting concessions in partnership with communities; collection of hunting revenues and (partial) allocation to Community Resource Boards (CRBs); and monitor usage of funds by CRBs | HIGH | HIGH |
|  | Ministry of Agriculture Department of Agriculture /Technical Services Branch | - Project collaborating partner in implementation - Provides agricultural extension services in crop production, horticultural production, nutrition, crop protection and soil fertility to smallholder farmers | HIGH | HIGH |
|  | The Provincial Administration | - During implementation: Co-opted in PSC | HIGH | HIGH |
|  | Ministry of Community Development and Social Services (MCDSS) | - During implementation: No formal decision taken on participation - excluded by default? - Project collaborating partner in implementation - Provides training to District Officers in gender equality in line with gender action plan | N/A | N/A |
|  | Ministry of Livestock and Fisheries Department of Fisheries | - -Support to forest and wildlife management within the context of Game Management Areas as multiple use zones | LOW | LOW |
|  | Ministry of Lands | - During implementation: Co-opted in PSC | LOW | LOW |
|  | Ministry of Finance and National Planning | - During implementation: Co-opted in PSC | HIGH | LOW |
|  | Ministry of Local Government and Rural Development | - During implementation: Co-opted in PTC and PSC | HIGH | LOW |
|  | Zambia Environmental Management Agency (ZEMA) | - During implementation: Co-opted in PSC - Knowledge sharing - Regulating EI of some developments - Coordination, collaboration and information-exchange | HIGH | LOW |
| Local Authorities | District Leadership District Commissioner | - Local government support to conservation and sustainable development | HIGH | LOW |
|  | Local Municipality/ Council/ District Councils | - Project collaborating partner in implementation. - Integration of SFM into IDPs; delivery of services to target communities | HIGH | LOW |
|  | Chiefs / Traditional authorities | - Project collaborating partners in implementation | HIGH | HIGH |
| Private Sector | Corporate Business Mines, Micro-finance institutions, Agric businesses, Forest carbon project development companies | - Prospective project collaborating partners in implementation - Provide access to credit for small businesses; deliver project co-financing; support project implementation; support capacity building and training of CFMGs and SFMCs; mitigate sectoral impacts on the integrity of protected forest areas. | HIGH | LOW |
|  |  | - Narratives for Carbon markets and community beneficiation on carbon schemes, the role of carbon initiatives enhancing conservation and socio-economic outcomes | HIGH | HIGH |
|  | Natural Resource (NR) Business Associations | - - Creating business opportunities for members (wildlife producers, safari hunting, timber, honey) | LOW | LOW |
|  | Small businesses Agric input and output marketing, Timber companies, Honey Companies, Out-grower Schemes | - Private sector support to business development, market linkages and financing and advocacy - Gain access to target groups, e.g. farmers, beekeepers via project | LOW | HIGH |
| Community- based organizations | Village Action Groups (VAGs)/ Community Resource Boards (CRBs) in Game Management Areas (GMAs) Participatory Forest Management Committees (PFMC) / Community Forest Management Groups (CFMG) in project Local Forests (LFs) and in communal lands Local Foundations/Trusts | - Role of Community Based Natural Resource Management principles in improving community conservation stewardship and beneficiation. - Policy and regulatory barriers and opportunities and proposed best management models for community led conservation - Project beneficiaries and project collaborating partners in implementation - As outlined in the Wildlife Act and Forest Act. develops, monitors and implements forest management plans; allocates and controls income and expenditure from forest resources; employs and manages community forest guards; hosts - Community meeting; maintain records and reports. | LOW | HIGH |
|  | Producer groups (NR user groups not registered) | - Beekeepers, pit sawyers, mushroom gatherers, collectors of medicinal plants, basket makers, caterpillar collectors | LOW | HIGH |
| Vulnerable groups | Women, Youth, Physically challenged, Elderly men and women, Children, Unemployed | - Knowledge sharing - Targets for participation, economic empowerment and transformation | LOW | LOW |

- Annex 16. “Results Chain at Review”:  Proposed revisions to the ECCLE results chain

| Results hierarchy | Original wording of results (project document) | Revised wording of results (“results at review”) |
| --- | --- | --- |
| Long- Term Impact | Threats to dryland miombo forests in NW Province are removed/minimized, ecosystem services provided by the forests are maintained, communities benefit equitably from sustainable natural resource management through long term revenue streams that increase the opportunity costs of destructive utilization of natural resources. | Threats to dryland forests on customary lands in Zambia are reduced, ecosystem services provided by the forests are maintained, and communities benefit equitably from sustainable forest and other natural resource management (FNRM) through long term revenue streams that increase the opportunity costs of destructive utilization of natural resources |
| Inter-mediate State | - Strengthened enabling environment for replication and scaling up of CFM in Zambia - Economic value derived by communities from sustainable forest management greater than destructive illicit activity - Private investment in NRM creates opportunity for long term revenues to communities from CFM - Forest resources are better managed for biodiversity/ecosystem conservation and enhanced welfare and livelihoods - Farmers realize financial benefits from sustainable agricultural practice and adoption rates increase | Strengthened enabling environment for replication and scaling up of gender-responsive sustainable community forestry in Zambia |
|  |  | Economic value derived by communities from sustainable forest management, in the long term, commensurate with, or greater than, that from destructive activities |
|  |  | Opportunities for communities to generate long term revenues from CFM created through private investment in collaborative FNRM |
|  |  | Biodiversity, ecosystem conservation, welfare and livelihoods enhanced through better management of forest and other natural resources |
|  |  | Enhanced income and livelihoods among an increasing number of male and female farming households derived from climate smart sustainable agriculture practice |
| Project level | Project Strategic Objective: Sustainable land management and biodiversity conservation are enhanced in NWP through the development of tested, proven systems of community management of forests and natural resource that are ready for mainstreaming |  |
|  | Project Objective: To strengthen community-based sustainable management of forest landscapes and provide improved livelihood opportunities for targeted forest-dependent rural communities in Zambia’s Northwestern Province |  |
| Outcome | 1: Sustainable forest management (SFM) mainstreamed in local development plans addressing gender equality | 1: Sustainable forest management (SFM) embraced by local communities and mainstreamed in gender-responsive local development plans |
| Outcome | 2: Improved management of forest resources for gender equality and enhanced welfare and livelihoods | 2: Communities empowered through gender-responsive community forest management (CFM) to manage forest resources, engage in sustainable FNRM-based enterprise and improve livelihoods |
| Outcome | 3: Improved productivity, gender equality and climate resilience from sustainable agricultural practices on the lands zoned for agriculture adjacent to community-managed forests | 3: Productivity, household income and climate resilience from sustainable gender-responsive agricultural practices improved in CFM communities |
| Output | 1.1 Comprehensive assessment of forests and communities in the project area, sex and age disaggregated 1.2 In-depth awareness raising on inclusive, gender sensitive CFMA creation leading to the declaration by government of the new or modified CFMG 1.3 Sustainable Forest and natural resource management promoted in gender responsive District Integrated Development Plans and CFMA management plans 1.4 Knowledge management (KM) system developed in support of gender sensitive community management of forests and natural resources 1.5 Subsidiary legislation for forestry reviewed and revised in support of gender responsive sustainable forest management | 1.1 Forest, natural resources and socio-economic assessments (sex and age disaggregated) conducted in support of community forestry 1.2 Communities aware of, willing to adopt and committed to gender responsive community forestry, leading to the declaration by government of new or modified CFMGs 1.3 Sustainable Forest and Natural Resources Management (SFNRM) promoted in gender responsive District Integrated Development Plans and CFMA management plans 1.4 Knowledge management (KM) system developed in support of developing, testing and monitoring gender responsive models for community management of forests and natural resources (CFNRM) 1.5 Gender-responsive CFM models for FNRM reviewed, revised and validated in support of upscaling, replicating and mainstreaming community forestry in sustainable forest management across Zambia (Recommendation 7) |
| Output | 2.1. Gender responsive business plans developed in support of each community forest management group 2.2. Develop gender responsive community-based enterprises based on the business plan 2.3. Capacities developed for gender responsive good governance, NRM and business management | 2.1. Community capacity developed for gender responsive good governance, sustainable FNRM and CFM business management 2.2. Gender responsive business plans developed in support of each community forest management group (CFMG) 2.3. Gender responsive community-based enterprises (CBE) developed and capitalized; CFMGs empowered to enter into partnerships with the private sector for the purpose of engaging in sustainable long-term FNRM business 2.4. Income and livelihood benefits from CFM enhanced through sustainable FNR-based enterprise at household level (Recommendation 8) |
| Output | 3.1. Gender responsive network of actors developed, and capacity built to deliver sustainable agricultural practices on the lands zoned for agriculture adjacent to community-managed forests. 3.2. Farmers and agricultural supply chain actors trained to encourage the adoption of gender responsive sustainable agricultural practices in agricultural zones in villages adjacent to community forests. 3.3. Crop and livestock male and female farmers adjacent to CFMAs equally trained to sustainably improve their productivity and net income. | 3.1. Networks of gender-responsive change agents formed and their capacity built to deliver climate smart agriculture (CSA) to farming communities on agriculture lands adjacent to community-managed forests 3.2. Farmers, youth and supply chain actors trained and capacity-built to adopt to climate smart agricultural (CSA) practices, convert to CSA farming and sustainably improve the productivity of their agriculture lands 3.3. Male and female CSA farmers, youth and supply chain actors facilitated to adopt best practice, to develop sustainable CSA farm business and to improve their productivity and income through accessing new input and output markets. |

### Annex 17. Specific Review Questions and Auxiliary Issues

- The Terms of Reference further poses evaluation questions (ToRs, p. 34), and the Project Steering Committee (PSC) tasked the Mid-Term Review to review issues that warrant recognition and attention. The table below lists the specific evaluation questions and the structural concerns identified by the implementation agency, project decision-making bodies and stakeholders.

- Table 17.1.  Key questions / concerns presented to the Mid-Term Review

| - Issue / concern | Source: | Location: |
| --- | --- | --- |
| - Does the TOC properly reflect the project’s intended change process? | Terms of Reference | Section III, Criterion C1 |
| - Are results statements in keeping with UNEP definitions (e.g. outcomes are expressed as the uptake or use of outputs) | Terms of Reference | Section III, Criteria C1, C2, C3 |
| - Is the stakeholder analysis still appropriate and adequate to support the project’s ambitions? | Terms of Reference | Section I, Criteria H3, H6 |
| - Are roles and responsibilities commonly understood and playing out effectively? | Terms of Reference | Section I, Criteria H3, H6 |
| - Is there an effective monitoring mechanism for the project’s implementation (this is separate from, and supports, reporting)? | Terms of Reference | Criterion F |
| - Is the rate of expenditure appropriate for the mid-point? | Terms of Reference | Criterion D |
| - Have plans for inclusivity, equality and/or equity been implemented as planned, or does more need to be done? | Terms of Reference | Criterion H4 |
| - Are safeguard identification and mitigation plans being monitored and steps taken to minimize negative effects? | Terms of Reference | Criterion H5 |
| - Way forward with the suspension of activities under output 1.5. in anticipation of a legal review of the 2015 Forest Act; | Project Steering Committee | Criterion C1 Recommendations (Section VII) |
| - Way forward with the difficulties encountered in effectively operationalizing Component 3 (sustainable agriculture); | Project Stakeholders | Criterion C1 Recommendations (Section VII) |
| - Way forward with the results indicators and targets that do not optimally capture project progress; | Project Team | Section III and Criterion F. Recommendations (Section VII) |
| - Way forward with the budget revision proposed in 2024. | Project Steering Committee | Criterion D and Recommendations (Section VII) |

### Annex 18.  ECCLE project progress against key deliverables and benchmarks

| Components / Outcomes/Outputs |  | Summary of Activities | Deliverables | Benchmarks | ECCLE “Completion of Deliverable” | MTR observations |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Project Component 1: Developing enabling regulatory and planning frameworks for community-based, sustainable forest management |  |  |  |  |  |  |
|  | Outcome 1: Sustainable forest management (SFM) mainstreamed in local development plans in target CFMAs or PFMAs: |  |  |  |  |  |  |
| Output 1.1 Comprehensive assessment of forests and communities in the project area – sex and age disaggregated. |  | - GIS capacities built. CFMG advisory boards created. Awareness raising of candidate communities. PIU and FD staff and consultants conduct assessments of forests and natural resources. Private sector company conducts detailed socio-economic analysis with focus on forest and natural- resource based livelihoods. Value chains analyzed. Options for geographic scale defined. | - Set of GIS maps on forest/natural resource and bio-physical conditions - Assessment reports on forest and NR conditions and socio-economic conditions at the four project sites. - Report on value chains. - Report on analysis of optimal scale of operations for each CFMG. | - Key value chains confirmed for each site. - Optimal economic and geographic scale of operations proposed for each potential CFMG. | 100% |  | - Draft GIS maps available (to be refined for CFMG use). - Socio-economic and biophysical assessment completed. - Value chains confirmed for each CFMG (to be elaborated in next generation and plans). - Proposal for optimal scale for target CMFAs prepared. - Analysis of optimal scale of operations pending (for modelling / mainstreaming objective) Analysis and consolidation pending |
| Output 1.2. In-depth awareness raising on inclusive, gender sensitive CFMA creation leading to the declaration by government of the new or modified CFMG |  | - Awareness raising on results of assessments. - Participatory analysis, debate and choice of options for grouping villages into CFMG. - Constitutions developed for each CFMG - CFMG legally recognized by government | - Maps of CFMG boundaries - Constitutions for each CFMG - Application by each CFMG for government recognition as a CFMG. | - CFMG legally recognized by government | 100% |  | - Boundary maps for each CFMA. - CFMG constitutions were drafted and adopted through participatory process. - Application for GRZ recognition submitted (Kalumbila) - GRZ recognition received (Ntambu and Kelongwa Kamanana - Application for transfer of carbon rights submitted to GRZ by Ntambu CFMG Association Analysis and consolidation pending |

| Components / Outcomes/Outputs | Summary of Activities | Deliverables | Benchmarks | ECCLE “Completion of Deliverable” | MTR observations |
| --- | --- | --- | --- | --- | --- |
| Output 1.3. Sustainable forest and natural resource management promoted in gender responsive District Integrated Development Plans and CFMA management plans | - Conduct integrated land use planning (ILUP) for communal lands belonging to CFMG. - Participatory zoning of forest and NR management units. - Participatory development of rules governing access, management and harvest of NR products. Finalize forest and NR management plans. - Create CFM planning sub- teams for mainstreaming CFM into district integrated development plans (DIDP). - Develop and apply criteria for selecting priority forests for CFM development. - Integrate CFM into DIDP | - ILUP plans for CFMG lands. - Maps of management units for CFMG forests and natural resources. - Detailed rules governing access, mgt. and harvest for each CFMG. - Forest and NR management plans - DIDP with CFM mainstreamed. | - All CFMG have approved forest management plans - CFM integrated into published DIDP | 100% | - ILUP planned completed in all three sites. - Draft CFMA maps prepared. - Drafting of management rules underway in each CFMG. - Integration of CFM into DIDP pending. To be adjusted to MLGH internal timetable for plan revision (estimated at 2030). Integration into GRZ processes pending |
| Output 1.4. Knowledge management (KM) system developed in support of gender sensitive community management of forests and natural resources | - Create a KM network and conduct three participatory KM reviews of CFM. Develop KM newsletter and Internet CFM discussion group. Participate in Drylands Sustainable Landscapes IP regional KM exchange. - Develop CFM courses integrated into university and technical college curricula. | - Reports of the 3 participatory reviews. - Semi-annual Newsletters - Website with discussion groups - Reports on regional exchange events - CFM courses listed in curricula of university and technical colleges. | - Published syntheses of lessons learned and best practices. - CFM courses prepared and made available to 2 universities and 1 technical college. offered to | 75% 60% | - One Participatory review held - One synthesis report prepared - Attendance at one regional SLIP KM exchange - One newsletter published - Website pending - CFM curriculum report prepared - CFM course prepared Several key deliverables pending |
| Output 1.5. Subsidiary legislation for forestry reviewed and revised in support of gender responsive sustainable forest management | - Legal consultant and two regional stakeholder workshops identify barriers in the existing statutory instrument and propose revisions. - Revisions finalized and submitted to MLNR for adoption. | - Workshop reports. - Revised Statutory Instrument (SI) for the Forest Act. | - Revised SI submitted to MLNR for adoption. | 0% | Output activities suspended by Project Steering Committee until PY4. |

| Components / Outcomes/Outputs |  |  | Summary of Activities | Deliverables | Benchmarks | ECCLE “Completion of Deliverable” | MTR observations |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Component 2: Promoting the conservation and sustainable use of natural resources in community-managed forests |  |  |  |  |  |  |
|  | Outcome 2: Improved management of forest resources for gender equality and enhanced welfare and livelihoods |  |  |  |  |  |  |
| Output 2.1. Gender responsive business plans developed in support of each community forest management group |  | - Confirm investment opportunities identified in Outcome 1. Conduct detailed analysis of investment and operational costs and of profitability. - Synthesis results in a business plan for each CFMG. Define who should own each enterprise. Define staff needs. Assess capacities needed. Identify partnership opportunities. Develop an investment plan that extends well beyond project completion. Define how NRM costs will be covered out of revenues. Define how investment costs will be covered out of revenues. Develop a provisional timeline. |  | - Reports on the analysis of profitability of various enterprises, of their staffing needs, of the capacities needed, of potential partnerships. - Syntheses of these elements into separate business plans for each CFMG, plans that extend well beyond Project completion. Plans will define the measures for the development and financing of forest/NR management plans and for investment plans for the development of existing and new enterprises. Investment plans will include a provisional and flexible timeline. | - Finalized business plans for each CFMG. - Investment plans for each CFMG. | 100% | - Enterprise / value chain analysis - CFMG business plans - CFMG investment plans Business and investment plans to be consolidated for exit and sustainability plans |
| Output 2.2 Gender responsive community- based enterprises developed based on the business plan |  | - Provide seed money and technical support for creation/development of community level, forest and NR- based enterprises. - Provide interim funding for TBU staff. - Create system for covering NRM and investment costs out of a portion of revenues generated. |  | - CFMG-owned and locally owned forest and NR-based businesses operational. - Community-based enterprises generating profits and contributing to the CFMG forest/NR management costs and investment costs. | - CFMG invest in enterprise development using money generated from existing enterprises. - Forest guards, professional and technical staff paid out of revenues generated. | 75% 40% | - Project investments done - CFMG CBE status at start-up, supported by project - CFMG income obtained, but no profits - No profits to re-invest - Proportion investment costs covered by revenue - nil Project investments have been made but CFMG enterprises freshly started, not yet generating profits |
| Output 2.3. Capacities developed for gender responsive good governance, NRM and business management |  | - Training needs assessment of community members, enterprises, CFMG, and district technical staff. Development of training plans and training modules and implementation training - Redo training needs assessment in Yr 3. - Revise training plan and modules and continue training. |  | - Training needs assessments - Training plan and modules | - Community managers have the governance; technical and business capacities they need to manage their forests and their enterprises | 100% 40% | - Two training needs assessments - One round of trainings implemented - Some CFMG staff (technical and business) skills enhanced Project trainings arranged, but not completed Few CFMG staff have the capacity to manage forests and enterprises |

| Components / Outcomes/Outputs |  |  | Summary of Activities |  | Deliverables | Benchmarks |  | ECCLE “Completion of Deliverable” | MTR observations |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Component 3: Enhancing the sustainability and productivity of agricultural practices in community-managed forests |  |  |  |  |  |  |  |  |
| Outcome 3: Improved productivity, gender equality and climate resilience from sustainable agricultural practices on the lands zoned for agriculture adjacent to community-managed forests: |  |  |  |  |  |  |  |  |  |
| Output 3.1. Gender responsive network of actors developed, and capacity built to deliver sustainable agricultural practices on the lands zoned for agriculture adjacent to community- managed forests |  | - Conduct a participatory survey of farmers and extension agents to establish a baseline for training and the extent and understanding of sustainable agricultural technologies in target smallholder communities around forested areas - Develop and implement a programme of capacity building of extension staff and change agents from the agricultural community in target areas, based on the information identified in the participatory baseline survey. |  | - Report on lessons learned, best practices, technologies ready for scaling up and on barriers to adoption, on differences in gender perspectives from baseline survey. - Document on a targeted programme of information dissemination to the target agricultural communities - Programme on capacity building for extension staff and change agents. Comprehensive package of training. |  |  | - SA technologies ready for scaling up identified. - Key barriers to farmer adoption of CA and other SA technologies identified - Programme of capacity building implemented | 83% 50% | - Component start delayed, then affected by change of service provider, drought. - Participatory baseline survey done - Report on CSA technologies and key barriers prepared - Key barriers to adoption identified, but limited action to overcome them - CSA technologies tested in demonstrations, not ready for scaling up, - Capacity-building & extension activities undertaken Network activated, draft strategy developed, selected trainings undertaken, but CSA technology still under testing. Delays. |
| Output 3.2. Capacity building provided to encourage the adoption of gender responsive, sustainable agricultural practices in agricultural zones in villages adjacent to community forests |  | - Development of demonstration ‘sites of best practice’, managed by progressive and influential lead farmers in the target areas that will be the focal points for farmer trainings and information dissemination at community level - Annual participatory adaptive management reviews with extension officers, lead farmers, farmers managing demonstration sites and a sampling of male, female and young farmers who are implementing sustainable agriculture practices. |  | - Demonstration sites on best practices for a diverse range of production options established on farms of progressive lead farmers - Report on findings from annual adaptive management reviews. - Synthesis of the finding from the adaptive management review |  |  | - Demo sites established and used for training and awareness raising - Regular analysis for improvement to the extension programme. | 47% | - One season demo established (CFU) - No annual adaptive reviews held - Drought 2023/24 season - One season analysis undertaken (MoA) One season of demos (out of three possible) held, selected trainings undertaken, CSA technology still being tested for appropriate scaling up. Component delayed at start-up, by change of service provider and drought. |
| Output 3.3. Crop and livestock male, female and young farmers adjacent to CFMAs equally assisted to sustainably improve their productivity and net income |  | - Field days will be held at the demonstration sites, ideally arranged and hosted by a local input supplier or other market actor that can offer access to inputs, information and technologies that support these production systems (e.g. seed and/or seedling supplier, day-old-chick supplier, irrigation technology supplier). - Using the demonstration sites and change agents as nodes of information dissemination, the project will also facilitate access to the wider agric market for farmers managing diverse and sustainable agricultural systems. |  | - Programme of field days integrating market actors implemented - Reports analyzing the strengths and weaknesses of the field days and proposing future improvements. - Demo sites and agents of change used to disseminate information of agricultural market. - Market linkages established and with market support services (eg finance) |  |  | - Markets linkages established - Farmers’ knowledge of the functioning of the markets improved. | 57% 40% | - Market access & linkages established (beans only) - Field days and demos arranged one season - Assessments of field day and demo programs not done - Enhanced farmer knowledge not demonstrated One season of market linkages (out of three possible) is held, selected trainings undertaken, but number of farmers participating remains low. Remarkable interest among women. |

### Annex 19. ECCLE Project Sustainability Analysis

The ECCLE Project Document (p. 83-84) lists the key sustainability factors as follows:

- Social sustainability is to be based on incentives and equitability: participation must be voluntary and based on the communities gaining an understanding of potential benefits and risks; benefits must exceed costs; benefit-sharing must be fair and equitable; benefits must accrue to the community as a whole; and good governance must prevail, enhancing gender equality.

- Financial sustainability is to be based on developing profitable, self-financing CFM NR-based enterprises at economic scale. To arrive at this, several conditions must be met: the forest resource must be adequate, and CFMG communities must be empowered to harness and manage business opportunities. The project would home in on value chains of high potential, e.g. honey and carbon, assisting communities establish profitable business relationships and attain greater benefits through informed negotiations with partners. In the long-term the development of other non-timber forest product (NTFP) value chains, and investment in infrastructure such as bulking facilities are seen as a priority means of increasing community bargaining powers.

- Institutional sustainability is to be based on ensuring that the CFM structures are supported beyond the lifespan of the project. The Project Document instructs the project to seek support to the CFMGs from (i) the Government (e.g. project implementation partners, district level within the context of the DIDP) (ii) the Private Sector (value chain operators;  CSR units of mining companies (i.e. Project Partners); and (iii) technical staff mobilized by the CFMGs themselves (i.e. directly employed staff and “support from private sector service providers engaged by the community managers and paid out of the forest management fund or the investment fund”). At present, among these options, only CSRP support is likely to materialise, with Government willing, but financially severely constrained. The mobilisation of duty bearers to support the project is discussed in sub-criteria H3 Stakeholder participation and H6 Country Ownership.

- Ecological sustainability is to be based on the preservation of healthy regeneration of habitat (miombo dryland forest); conservation of wildlife habitat; and the adoption of appropriate FNRM management measures through community forestry. Such measures include protection of sensitive ecosystems, safeguards for agriculture production (e.g. climate smart agriculture against expansive slash-and-burn) and safeguards for NTFP harvesting (e.g. caterpillar harvesting protocols to avoid destructive practices). At present, biodiversity and ecological concerns are addressed at forest level through the management plans, but their effective integration into the national protected area network (Game Management Area zoning) and district development planning is pending.

Factors affecting of sustainability. The key conditions and factors that are likely to undermine or contribute to the endurance of achieved project outcomes are summarised in Table 19.1. below.

Table 19.1. Key factors of sustainability in the ECCLE Project

| Criteria (as per Terms of Reference) | MTR observations |
| --- | --- |
| The level of ownership, interest and commitment among government and other stakeholders to take the project achievements forwards | Stakeholder interest is high, but commitment and capacity to take project achievements forward varies: - Community ownership will depend on whether the CFMG NR-based enterprises will be able to turn a profit, and provide benefits to be shared - Enhanced, active Forestry Department engagement in and ownership of project is key for overall sustainability (Recommendations 2, 11 and 13) - As duty bearers, active engagement also by other Government departments (agriculture, lands, councils, district teams) is necessary – clarifying their roles and responsibilities will be key (Recommendation 11) - Implementation Partners (WLCP, TFL, KCP, TNC) continued commitment to access to external funding and enter into negotiated agreements with the forest communities post-project (Recommendation 10). |
| The extent to which the sustainability of project outcomes is dependent on issues relating to institutional frameworks and governance | Outcome sustainability is highly dependent on issues relating to institutional frameworks and governance. First and foremost, the project needs to consolidate achievements and plan for a sustainable exit. Important PLIR issues identified elsewhere in this report may inform the plan (see Sub-criteria C1, C2). |
| The extent to which project outcomes are dependent on future funding for the benefits they bring to be sustained | The viability of the self-financing model will not be possible to demonstrate during the project life span. Project areas will remain highly dependent on external funding for at least 5-8 years to consolidate benefits. At outcome level, for benefits to be sustained and scaled up, future funding is likely to be needed to moderate the current market-based strategy. (Recommendations 3 and 10) |
| The robustness of the enabling environment (institutional achievements such as governance structures and processes, policies, legal and accountability frameworks) to continue delivering the benefits associated with the project outcomes after project closure | Stakeholder capacity to continue delivering project outcome is limited. Most Government Departments are severely constrained in funding. There is need for Forestry Department to demonstrate the viability of the ECCLE model to Central Government in order to obtain funding for the envisaged transition phase, and to further policies of sustainable FNRM vis-à-vis competing national economic interests (Recommendations 2 and 11). |

### Annex 20. Project Management (H2): ECCLE implementor roles and performance

| Partner/party | Observations & findings | Performance and Recommended action |
| --- | --- | --- |
| Implementing Agency – UNEP | The IA is delivering on role and responsibilities, but at a level less than optimal for project progress: Project design and inception. Weaknesses in the project design (project rationale, Theory of Change, assumptions, indicators, and risks) were not captured well before project commencement. UNEP staff changes may have contributed to this. As a result, the project encountered unnecessary start-up difficulties. Frequency of supervision missions –stakeholders wish for regular annual visits in the field Pro-active support to PIU – project will benefit from more IA support, as exemplified by delays caused by incomplete co-financing reporting and advisory on GEF requirements. Expediency in feedback on PIRs – PIU lacks copies of some of the finalized PIR reports. | Moderately satisfactory. UNEP to More proactively engage with PIU for quality assurance and to ensure that GEF requirements are fully met. Increase allocation of project time to Task Manager allowing for regular visits also to the field. See Recommendation 2. |
| Executing Agency - TNC | The EA is delivering on role and responsibilities, but has encountered internal administrative issues that are less than optimal for project progress: Staff mobilization slow: Agreement signed with UNEP in September 2021, PIU/TSU only fully staffed ten months later. Inception period ineffective: In the absence of project staff, the EA (and IA) inadequately captured the need for revisions to the Project Design allowing for shortcomings to persist into implementation Sub-contracting and outsourcing slow – tendering and contracting procedures have at times been excessively slow, attributed to administrative inertia, cumbersome procedures and workload Handling of implementation partner contracts – delays in renewing contracts have affected the progress in the delivery outputs. In some instances, delays have slowed down progress, while in others implementation partner have stepped up to compensate. In general, however, periods of partners lacking contracts are not acceptable by industry standards. Quality assurance – although EA in-house expertise has been successfully engaged in the drafting of Terms of Reference, their in-depth knowledge would also be useful in reviewing technical reports of significance for CFM model development | Moderately satisfactory. TNC to Take note of lessons from project mobilization and start-up for consideration in future GEF projects. Internally review administrative procedures to ensure that outsourcing and contracting will run smoothly during the final years of the project. Consider supporting PIU with in-house TNC staff helping review backlog of technical reports to facilitate their review, approval and adoption. Recommendations 2, 14. |
| Project Implementation Unit | The Project Implementation Unit is delivering on role and responsibilities, but is encountering strategic and qualitative issues that need correction for project outcomes to materialize: Strong capacity to deliver. After an administrative delay of almost one year, the PIU/TSU successfully mobilized partners and communities for project implementation, performing very well against delivery milestones and benchmarks. The good quantitative progression in volume of activities needs matching in terms of qualitative outputs – key deliverables have been produced, but not yet consolidated; PM needs to backstop TSU, in particular Components 2 and 3 which are facing challenges. The peer review and adoption of technical documents (consultancy reports) mechanism was less than optimal (see also FD, EA, PTC, IA). The filing and archiving of project deliverables, e.g. PSC and PTC meeting minutes such reports, as well as their dissemination to stakeholders, need attention (see also FD). Role of PSC - PIU appears to have made less than optimal use of the PSC in seeking approval and guidance for key project management decisions. However, this is difficult to confirm as signed PSC minutes are not available. Stakeholders do not fully embrace their responsibilities, and this creates extra work for PIU. In the absence of clearly formulated expectations, roles and responsibilities, the project (PIU/TSU) often ends up undertaking tasks on the behalf of stakeholders for expediency – while this approach has helped the project gain back time lost, this is not good for sustainability - all partners should now shoulder their responsibilities. | Satisfactory. PIU to Revise work plans to consolidate achievements optimally over the remainder of the project period bearing in mind strategic objective. Work out an improved mechanism for the review, adoption and integration of technical report finding in the project implementation (together with FD, PTC and KM). Formally revise the ToRs for both PSC and PTC, and have the PSC formally approve. Ensure that all PSC minutes are produced and signed (with FD). Review stakeholder roles and responsibilities. Recommendations 2, 6-10, 11, 14. |
| Forestry Department | The Forestry Department, on behalf of the Ministry of Green Economy and Environment, is tasked with implementation oversight and overall coordination. These tasks did not unfold as expected. Deviations to what was planned, that have had an impact on progress, include: General commitment and collaboration. FD has been supportive of project objectives implementation, available and supportive upon request, but not pro-active. Frequency and scope of engagement affected by department re-organization, and loss of several senior members of staff since 2021. Ownership. The planned for a full-time position of senior National Project Coordinator, at M.Sc. level, providing substantive technical input in the execution of all components (75%) as well as project management support as a running mate to the Project Manager (25%) did not materialize. Instead, a part-time (< 50%), administratively oriented, national coordinator came on board in Project Year 3. In total the project has had three national coordinators, each mid-career forest officers, none at the envisaged level of education and seniority. This resulted in a less-than-optimal project team, reduced project ownership within the host institution, and sub-optimal guidance and backstopping to the province and districts. The 2024 nomination of a provincial project focal point (Solwezi) and the drafting of Terms of Reference for the District Teams somewhat alleviated the situation. Forest PLIR products. The absence of a full-time national project coordinator undoubtedly influenced the suspension of activities under output 1.5. (Subsidiary legislation). As argued elsewhere, the project may make a significant contribution by preparing the ground for mainstreaming CFM in Zambia, not least by generating an active internal dialogue within FD for revisions to the model, for addressing forestry-related barriers and constraints encountered by project independently (e.g. transfer of user rights). Project liaison, visibility and impact. A short-coming associated with the absence of a full-time senior National Project Coordinator is the rallying of project interests with other Government partners, such as DNPW on the harmonization of CFM and Community Based Natural Resource Management (CBNRM)on local level, and the sharing lessons and provision of visibility nationally. | Moderately unsatisfactory. Forestry Department together with PIU to Revise the Terms of Reference for the National Coordinator, to be presented to the IA and the PSC for approval. Forestry Department to increase the time allocation of the National Coordinator, in line with the Project Document. Identify additional staff at FD HQ who may support the integration of ECCLE project findings at its current stage of consolidating CFM governance. The PIU and NC to arrange for a mechanism for how CFM model and KM materials to be reviewed systematically at Forestry Department HQ to ensure that products meet national requirements, to generate awareness of project achievements and build ownership Recommendation 2. |

| Partner/party | Observations & findings | Performance and Recommended action |
| --- | --- | --- |
| Project Steering Committee (PSC) | The establishment of a Project Steering Committee took long, and the inaugural meeting was held in June 2023, close to two years after project approval. Since then, the PSC has held annual meetings and is delivering on its role and responsibilities, though at a level less than optimal for project progress. Key issues observed: At a programmatic level, establishing a joint steering committee for the two GEF funded projects has been a success. The division of labour between the PSC and the PTC (Project Technical Committee) has been altered with the PTC taking up more of PSC preparatory duties and the PSC retaining strategic oversight. The revised Terms of Reference (charter) were not available to the MTR consultant. The PSC retains approval of key project instruments (work plans, budgets and reports) for its mandate to provide supervision and monitor progress and authorize significant revisions thereto. The timing of meetings sometimes do not match the work planning cycle, and the PSC is increasingly dependent on the recommendation from the PTC for approval. Furthermore, the PSC may be sidelined by the IA independent approval procedure. Formal, signed minutes from the PSC meetings were not available. As these are documents that are administratively and legally binding, vis-vis GEF and within a Government context, they need to be archived appropriately. The role of PSC in the Exit Plan needs careful consideration, in order not to create administrative hindrances that may affect its smooth implementation. | Moderately satisfactory. The PIU and NC to closely collaborate to Produce revised Terms of Reference for both the PSC and PTC for review and adoption by the PSC, to be archived appropriately, including the FD HQ registry. Produce final, signed minutes of the PSC meetings, to be archived appropriately, including the FD HQ registry. Avail project stakeholder channel of access to PSC (and PTC) minutes. Carefully consider the roles of the PSC and PTC in the exit plan and sustainability strategies, to ensure appropriate endorsements. Recommendation 2, 3, 14. |
| Project Technical Committee (PTC) | The establishment of a Project Technical Committee took about a year, and the inaugural meeting was held in October 2022, one year after project approval. Since then, the PTC has held annual meetings and is delivering on its role and responsibilities. Key issues observed: The composition of the Project Technical Committee has changed from what was envisaged in the Project Document. For example, the Ministry of Community Development and Social Services (MCDSS) is listed as a “project collaborating partner in implementation” in the Project Document, but has not been invited to the PTC, though they participated in the land use planning. Recently the Ministry of Local Government and Rural Development (MLGRD) and the Provincial Gender Division were co-opted. The principle of equitable and effective representation in an appropriate skills mix seems only partially enacted. A formal updated list of the members of the PTC, by position and non-person, indicating whether an institution is represented from national or provincial level, needs to be prepared and approved by the PSC, for the PTC legitimacy to be upheld. During the project life span, the duties of the PTC have evolved, as the PSC has delegated more powers to the PTC. There is need to update the Terms of Reference formally, for approval by the PCS and appropriate filing. The role of PTC members should also be clarified (full members, observer) so as not to create situations whereby the executive (project staff, implementation partners) involuntarily are placed in decision-making vis-à-vis themselves. The frequency of PTC meetings is less than planned for (annual as against twice a year), making it more difficult for the project to match meetings with work planning and reporting cycles and obtain approvals. Monthly meetings with Implementation Partners have relieved some pressure. Separation of executive and decision-making powers needed. PTC suffers from turn-over of participants. Due to busy schedules in the Government departments, meetings are attended by different persons every time, rendering decision-making less effective and slowing down progress. Expediently availing PTC members’ meeting minutes will enable stakeholders to better keep track of matters and support individuals report back to institutions they represent. As the PTC has been delegated greater powers by the PSC, and at times, due to the infrequency of PSC meetings, ends up being the approving authority, it is important that PTC meetings are fully minutes and that signed copies are archived. A copy of the meeting minutes should be lodged with the Provincial Development Coordination Committee (PDCC) through the office of the Provincial Permanent Secretary. The PTC activities should also be reported back to the PSC. One of the changes made to the PTC charter is to reduce on the day-to-day technical support to implementation (e.g. tasks of reviewing ToRs, technical evaluation of proposals, peer reviews of consultancy reports have been dropped). This has increased the work burden in PIU. Alternative measures for quality assurance and availing the PTC members and their host institutions’ access to the updated information should be envisaged. The M&E officer and the KM component may play a key role here. | Satisfactory The PIU and NC to closely collaborate to Produce revised Terms of Reference for both the PTC (and PSC) for review and adoption by the PSC, to be archived appropriately, including the FD HQ registry. Take a formal decision on PTC members, which is to be approved by PSC. Produce final, signed minutes of the PTC meetings, to be archived appropriately, including the FD HQ registry. Makes a systematic effort to avail meeting minutes both to the formal representative of each Government department (for filing) and to the individual who attended the meeting. Avail project stakeholder channel of access to PTC (and PSC) minutes Recommendations 2, 3, 14. |
| District Technical Team | The district technical teams were set up at the start of the project, modelled on the DFNRMP approach. They were envisaged a dual role – providing technical guidance to CFMGs and reporting on activities hierarchically (through the TSU) and horizontally (through the District Development Coordination Committee, DDCC). Team efficiency has been very variable with some teams performing well, while others have struggled. A key factor appears to be the aptitude and engagement of the District Forestry Officer. The district teams do not have a budget line for working independently but have to request for funds for participation in specific activities from the project. In establishing the teams some deviations from plans were observed. Composition. The status of the Department of Community Development and Social Welfare as a team member is not clear. In other CFM pilots, the role of this department has been seen as crucial, not least to support fledgling women’s groups and female leaders. Composition. The Department of Fisheries is an active and contributory member, however, as the collaboration with WWF – Zambia did not materialize as envisaged – this participation supports the work of the NRM subcommittee of the DDCC currently, more than the project. Comprehensive Terms of Reference for the district teams were prepared in 2024. Although technically correct, the activities listed are beyond what is feasible within the project context and, especially, beyond the project lifespan. There is need to extract a few key service functions (technical support, liaison, reporting) and the district teams will be expected to deliver to the CFMGs post-project and strengthen their capacity to deliver on these. The district teams will play an important role in the Exit Plan as they take on the responsibility of delivering government services to CFMG with limited support from provincial and national level. There is need to consolidate their capacity to take on this role effectively. | Moderately satisfactory. The PIU and NC to closely collaborate to To formally recognize the composition of the District Teams (acknowledging KM recommendations), bearing in mind the CFMG needs and financial constraints after the project end. To provide the three reconstituted district teams with some funds to do independent monitoring visits in order to establish rapport with the CFMGs (for post-project sustainability purposes). To revise the Terms of Reference in such a way that the Terms support the intended function – provision of technical support and liaison between CFMGs and districts – is retained. To define the role of the district teams in a post-project sustainability plan, looking at how support levels may be retained. Recommendations 2 (thorough FD HQ), 10, 11. |
| Project implementation partners | The Project Partners are delivering on responsibilities and have played a significant role in project progress, for which they should be acknowledged. Below some issues that would benefit from attention. The Private Sector CSRP partners (WLCP, Trident Foundation) reports on the detailed use of co-financing support other than staffing has been sparse, making it difficult to evaluate their contribution to the transformation of output into outcomes (see C3). As the CFMGs grow in strength and ability, it is recommended that the Private Sector CSRP partners adopt more of a “sustained equal partnership” approach with them allowing them to grow into independent partners in a negotiated relationship. This applies in particular to carbon engagement, where there the communities must be able to make informed and responsible decisions on behalf of the wider community for several decades. Among the NGO partners (KCF, WWF and to some extent TNC) KCF – as above, the need to support, empower and recognize the Kelongwa Kamanana CFMG as a full partner, including the formalization of ownership of key structures (Eco-Tourism Camp, Bulking Facility) within the remaining project period. WWF Zambia has not effective partner, and should be removed from list of co-financiers Among the sub-contracted service providers (Miombo Ecosystem Enterprise Ltd., Impulse Africa, several market partners) – The very extensive engagement of Miombo Ecosystem Enterprise Ltd through various project implementation contracts (with PIU and IPs) raises some concern regarding capacity to deliver in a timely manner. – All contracts with market partners have been drafted for one year at a time. There is need to review the lessons from the first years before negotiating a controlled exit plan. | Satisfactory. PIU/EA to: Consider removing WWF Zambia from list of partners and co-financiers due to inaction (see para 155, criterion D). Close monitoring of sub-awardees and service providers, taking rapid action in case of slippage in delivery timetables, and carefully assessing their performance before negotiating their participation in exit arrangements. The NGO and Private Sector IPs to: Increase transparency and reporting on the use of co-financing for the benefit of the ECCLE project and good governance principles Adopt more of a “sustained equal partnership” approach with CFMG and CFMG Association to perform their full duties as independent partners in a negotiated relationship Recommendations 10, 11 and 13. |
| CFMGs | During the first project years the roles and responsibilities of the communities have been those of ‘beneficiary’. During the final part of the project period, the role and the responsibilities of the CFMGs will change. The CFMGs will become ‘partners’ in implementation and gradually take on substantively more responsibility. This process should be groomed and guided – so that the CFMGs develop the necessary capacity and obtain the necessary skills and tools to survive and thrive post-project. The CFMGs will benefit from developing skills needed for partnerships, e.g. negotiation and long-term planning. | Moderately satisfactory PIU to: Invest in additional training and capacity-building that will enable CFMGs become independent actors in their own right. Oversee the negotiations with IPs for sustainability strategies and commercial contracts, supporting the CFMGs where necessary. Recommendation 10 |

SMA refers to the ID provided by the Integrated Planning, Management and Reporting Solution (IPMR) system, which was introduced by UNEP in July 2023.

For example, ID references from EC, IKI, UNDA, Adaptation Fund, GCF.

Where applicable, list countries who have provided project funds and/or co-finance.

Indicate where funding institutions are any/all of the following: Foundation/NGO; Private Sector; UN Body; Multilateral Fund; Environment Fund; Other.

Total budget may include Regular Budget, Environment Fund, Extra-Budgetary, including ‘softly-earmarked’ etc.

Extra-budgetary funds may include co-finance (cash/in-kind).

Review Consultant Terms of Reference, p. 29. The revised charter has not been available to the Review (see recommendation 14).

Project Document, Terms of Reference, Annex 11, p. 125-127.

ProDoc, para 159, page 68.

During the Inception Phase of the review process a TOC at Review Inception is created based on the information contained in the approved project documents (these may include either logical framework or a TOC or narrative descriptions), formal revisions and annual reports, etc. During the review process this TOC is revised based on changes made during project implementation and becomes the TOC at Review.

Revisions to results may be formalized through official communication between the project team and the funding partner (e.g. Steering Committee minutes; email exchange with the donor; GEF Project Implementation Review report; email confirming adoption of revisions after a Mid-Term Review, etc.).

Mid-Term Review of the UNEP project: Ecosystem conservation and Community Livelihood Enhancement in Northwestern Zambia Project, GEF ID 10192. Inception Report, final corrected version 10.07.2025 [Author: Review Consultant].

The Project Preparation Grant documentation was only partially available to the Review Consultant.

Weighted project quality design, as per UNEP MTR Review Criteria Ratings Matrix, 2024, p. 5.

Excluding output 1.5. Subsidiary legislation, which was suspended by the First Project Steering Committee meeting held during the second project implementation year (PY 2), in anticipation of a legal review of the 2015 Forest Act. The activities were postponed to PY4 (2024-2025). By the time of the MTR, no revision had been made of the plans for how to best utilise the funds.

ECCLE project team self-assessment, derived from Semi-Annual Progress Reports 2022-2024. See also Progress Tracking in Annex 18.

Shortened identifiers and abbreviations are used in order not to clog the text too much. For revised wording in full, see recommended wording of the outputs in Annex 16 and the proposal for a revised ToC in Figure 3 above.

Semi-Annual Report January-July 2023.

Adaptive management is an iterative process in which practitioners test hypotheses and adjust behaviour, decisions, and actions based on experience and actual changes (Stankey et al., 2005, quoted in UNEP 2023).

Weighted project quality design, as per UNEP MTR Review Criteria Ratings Matrix, 2024, p. 5.

SMART refers to results that are specific, measurable, achievable, relevant and time-oriented. Indicators help to make results measurable (UNEP 2023).

An exit strategy is a set of documented and planned management actions that describe an approach to sustaining the effects of a project beyond its planned operational life. (UNEP 2023)

The terms scaling up and replication are inter-related and generally refer to extending the coverage or magnitude of the effects of a project. Scaling up and Replication require more intentionality for projects, or individual components and approaches, to be reproduced in other similar contexts. Scaling up suggests a substantive increase in the number of new beneficiaries/affected area reached and may require adapted delivery mechanisms while Replication suggests the repetition of an approach or component at a similar scale but among different beneficiaries. Even with highly technical work, where scaling up or replication involves working with a new community, some consideration of the new context should take place and adjustments made as necessary (UNEP Review Criteria Ratings Matrix, 2024)

Mid-Term Review of the UNEP project: Ecosystem conservation and Community Livelihood Enhancement in Northwestern Zambia Project, GEF ID 10192. Inception Report, final corrected version 10.07.2025 [Author: Review Consultant].

UNEP, Mid-Term Review, Guidance on the Structure and Contents of the Mid-Term Review Inception Report.

Copies of meeting attendance sheets have been submitted to the Task Manager / PIU.

If the Review raises concerns over adherence with policies or standard procedures, a recommendation maybe given to cover the topic in an upcoming audit, or similar financial oversight exercise.

See also document ‘Criterion Rating Description’ for reference

SMA refers to the ID provided by the Integrated Planning, Management and Reporting Solution (IPMR) system, which was introduced by UNEP in July 2023.

For example, ID references from EC, IKI, UNDA, Adaptation Fund, GCF.

Where applicable, list countries who have provided project funds and/or co-finance.

Indicate where funding institutions are any/all of the following: Foundation/NGO; Private Sector; UN Body; Multilateral Fund; Environment Fund; Other.

Total budget may include Regular Budget, Environment Fund, Extra-Budgetary, including ‘softly earmarked’ etc.

Extra-budgetary funds may include co-finance (cash/in-kind).

https://wedocs.unep.org/handle/20.500.11822/41114

https://wedocs.unep.org/20.500.11822/42752

Sustainability is similarly rated on a six-point scale but labelled from Highly Likely (HL) down to Highly Unlikely (HU).

UNEP’s Medium-Term Strategy (MTS) is a document that guides UNEP’s programme planning over a four-year period. It identifies UNEP’s thematic priorities, known as Sub-programmes (SP), and sets out the desired outcomes, known as POW Outcomes and POW Direct Outcomes of the Sub-programmes.  https://www.unenvironment.org/about-un-environment/evaluation-office/our-evaluation-approach/un-environment-documents.

http://www.unep.fr/ozonaction/about/bsp.htm

This sub-category is consistent with the new criterion of ‘Coherence’ introduced by the OECD-DAC in 2019.

The conditions and processes for amendments should abide by the terms of the funding agreement. For example, the GEF has specific requirements for the approval/reporting of ‘minor’ and ‘major’ amendments. This includes the provision that any minor and major (approved) amendments should be reflected in the PIR report of the same year.

UNEP, 2023, Glossary of Results Definitions.

This can be as a driver or assumption if there is no specific equality results statement.

Outputs are the availability (for intended beneficiaries/users) of new products and services and/or gains in knowledge, abilities and awareness of individuals or within institutions (UNEP, 2023)

An outcome is a change at institutional level,  or changes in behaviors, attitudes or conditions achieved from the use (i.e., uptake, adoption, application) of outputs by intended beneficiaries (UNEP, 2023).

The terms catalytic effect, scaling up and replication are inter-related and generally refer to extending the coverage or magnitude of the effects of a project. Catalytic effect is associated with triggering additional actions that are not directly funded by the project – these effects can be both concrete or less tangible, can be intentionally caused by the project or implied in the design and reflected in the TOC drivers, or can be unintentional and can rely on funding from another source or have no financial requirements. Scaling up and Replication require more intentionality for projects, or individual components and approaches, to be reproduced in other similar contexts. Scaling up suggests a substantive increase in the number of new beneficiaries reached/involved and may require adapted delivery mechanisms while Replication suggests the repetition of an approach or component at a similar scale but among different beneficiaries. Even with highly technical work, where scaling up or replication involves working with a new community, some consideration of the new context should take place and adjustments made as necessary.

For GEF funded projects the UNEP Project Manager refers to is the Task Manager.

Complementarity with other interventions during project design, inception or mobilization is considered under Strategic Relevance above.

SMART refers to results that are specific, measurable, achievable, relevant and time-oriented. Indicators help to make results measurable.

Project Information Management System (PIMS) or, from 2022, Integrated Planning Monitoring and Reporting (IPMR)

As used here, ‘sustainability’ means the long-term maintenance of outcomes and consequent impacts, whether environmental or not. This is distinct from the concept of sustainability in the terms ‘environmental sustainability’ or ‘sustainable development’, which imply ‘not living beyond our means’ or ‘not diminishing global environmental benefits’ (GEF STAP Paper, 2019, Achieving More Enduring Outcomes from GEF Investment)

During 2023 UNEP is reviewing its Partnership Policy and Procedures and a future version is expected to include a requirement for risk mitigation against weak performance among partners.

GEF Minimum Fiduciary Standards: Separation of Implementation and Execution Functions in GEF Partner Agencies (2019).

The Evaluation Office notes that Gender Equality was first introduced in the UNEP Project Review Committee Checklist in 2010 and, therefore, provides a criterion rating on gender for projects approved from 2010 onwards. Equally, it is noted that policy documents, operational guidelines and other capacity building efforts have only been developed since then and have evolved over time.   https://wedocs.unep.org/bitstream/handle/20.500.11822/7655/-Gender_equality_and_the_environment_Policy_and_strategy-2015Gender_equality_and_the_environment_policy_and_strategy.pdf.pdf?sequence=3&isAllowed=y

For the review of project concepts and proposals, the Safeguard Risk Identification Form (SRIF) was introduced in 2019 and replaced the Environmental, Social and Economic Review note (ESERN), which had been in place since 2016. In GEF projects safeguards have been considered in project designs since 2011.

For GEF funded projects, UNEP Project Manager refers to the Task Manager.

This does not apply to Enabling Activities

Source: Project Document p. 109 and ECCLE internal tracking report, 2025.

Project Progress Tracker, 17 July 2025, ECCLE M&E Unit

Project Progress Tracker, 17 July 2025, ECCLE M&E Unit