Annex 1.  Multi Year Work Plan

| Output | Indicator | Responsible Party | Year 1 |  |  |  | Year 2 |  |  |  | Year 3 |  |  |  | Year 4 |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 |
| Contract project unit members |  | UNDP | x |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.1. Transboundary Diagnostic Analysis |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Prepare workplan and budget |  | Project unit |  | x |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Contract TDA integration consultant |  | Project unit |  | x |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Contract consultants to compile information for TDA |  | Project unit |  | x |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Consultants compile and organise existing information to support TDA preparation |  | Project unit |  | x | x |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Contract TDA/SAP methodology trainer |  | Project unit |  | x |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Countries select and designate members of TDA development team |  | Project unit |  | x |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Training workshop on the TDA/SAP methodology |  | Project unit |  |  | x |  |  |  |  |  |  |  |  |  |  |  |  |  |
| TDA initiation workshop |  | Project unit |  |  | x |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Contract TDA support consultants |  | Project unit |  | x |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| TDA support consultants contribute to the process |  | Project unit |  | x | x | x | x | x | x |  |  |  |  |  |  |  |  |  |
| Workshop to identify priority transboundary problems and impacts |  | Project unit |  |  | x |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Causal chain analysis workshop |  | Project unit |  |  |  | x |  |  |  |  |  |  |  |  |  |  |  |  |
| Contract thematic reports |  |  |  |  | x |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Development of thematic reports |  | Project unit |  |  |  | x | x | x |  |  |  |  |  |  |  |  |  |  |
| Thematic reports meeting |  | Project unit |  |  |  |  |  | x |  |  |  |  |  |  |  |  |  |  |
| Workshop to validate the causal chain analysis and SAP linkage |  | Project unit |  |  |  |  | x |  |  |  |  |  |  |  |  |  |  |  |
| Drafting of the TDA |  | Project unit |  |  |  |  |  | x |  |  |  |  |  |  |  |  |  |  |
| TDA review meeting |  | Project unit |  |  |  |  |  | x |  |  |  |  |  |  |  |  |  |  |
| TDA adoption by steering committee |  | Project unit |  |  |  |  |  |  | x |  |  |  |  |  |  |  |  |  |
| Translate TDA document into English |  | Project unit |  |  |  |  |  |  | x |  |  |  |  |  |  |  |  |  |
| Distribution of electronic document to local and international audiences |  | Project unit |  |  |  |  |  |  |  | x | x |  |  |  |  |  |  |  |
| 2.1. Strategic Action Programme |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Prepare workplan and budget |  | Project unit |  |  |  |  |  | x |  |  |  |  |  |  |  |  |  |  |
| Contract SAP integration consultant |  | Project unit |  |  |  |  |  |  | x |  |  |  |  |  |  |  |  |  |
| Contract participation and gender equality specialist to support SAP preparation |  | Project unit |  |  |  |  |  |  | x |  |  |  |  |  |  |  |  |  |
| Contract TDA/SAP methodology trainer |  | Project unit |  |  |  |  |  |  | x |  |  |  |  |  |  |  |  |  |
| Identification and designation of SAP development team |  | Project unit |  |  |  |  |  |  | x | x |  |  |  |  |  |  |  |  |
| Training workshop on the TDA/SAP methodology |  | Project unit |  |  |  |  |  |  |  | x |  |  |  |  |  |  |  |  |
| SAP initiation workshop |  | Project unit |  |  |  |  |  |  |  | x |  |  |  |  |  |  |  |  |
| Strategic thinking meeting 1 |  | Project unit |  |  |  |  |  |  |  | x |  |  |  |  |  |  |  |  |
| Strategic thinking meeting 2 |  | Project unit |  |  |  |  |  |  |  |  | x |  |  |  |  |  |  |  |
| Consultation to key stakeholders |  | Project unit |  |  |  |  |  |  |  |  |  | x | x |  |  |  |  |  |
| Drafting of the SAP |  | Project unit |  |  |  |  |  |  |  |  |  |  |  | x |  |  |  |  |
| High level government consultation |  | Project unit |  |  |  |  |  |  |  |  |  |  |  |  | x |  |  |  |
| Final SAP review meeting |  | Project unit |  |  |  |  |  |  |  |  |  |  |  |  | x |  |  |  |
| SAP endorsement |  | Project unit |  |  |  |  |  |  |  |  |  |  |  |  | x |  |  |  |
| Translate TDA document into English |  | Project unit |  |  |  |  |  |  |  |  |  |  |  |  | x |  |  |  |
| Distribution of SAP and policy brief to local and international audiences |  | Project unit |  |  |  |  |  |  |  |  |  |  |  |  |  | x | x |  |
| 3.1. Training of key national and subnational stakeholders to strengthen IWRM. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| a. Training course on water governance in a transboundary context |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Contract service provider |  | Project unit |  |  |  | x |  |  |  |  |  |  |  |  |  |  |  |  |
| Training needs assessment of target group |  | Project unit |  |  |  | x |  |  |  |  |  |  |  |  |  |  |  |  |
| Adjust training materials and case studies to local conditions |  | Project unit |  |  |  | x | x |  |  |  |  |  |  |  |  |  |  |  |
| Run training course |  | Project unit |  |  |  |  |  | x | x |  |  |  |  |  |  |  |  |  |
| Prepare short videos with key messages for transboundary water governance |  | Project Unit |  |  |  |  |  |  | x |  |  |  |  |  |  |  |  |  |
| b. Binational water school |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Contract course development team |  | Project Unit |  |  |  | x |  |  |  |  |  |  |  |  |  |  |  |  |
| Training needs assessment of target groups |  | Project Unit |  |  |  | x |  |  |  |  |  |  |  |  |  |  |  |  |
| Develop curriculum and training materials |  | Project Unit |  |  |  |  | x |  |  |  |  |  |  |  |  |  |  |  |
| Develop training of trainers’ course and materials |  | Project Unit |  |  |  |  | x |  |  |  |  |  |  |  |  |  |  |  |
| Implement training of trainers |  | Project Unit |  |  |  |  |  | x |  |  |  |  |  |  |  |  |  |  |
| Implement a test run of binational water school |  | Project Unit |  |  |  |  |  | x | x | x | x |  |  |  |  |  |  |  |
| Assess performance and adjust curriculum and materials as needed |  | Project Unit |  |  |  |  |  |  |  |  |  | x |  |  |  |  |  |  |
| Prepare short videos with key messages on watershed management, water cultivation and best practice on irrigation and potable water boards for online dissemination |  | Project Unit |  |  |  |  |  |  |  | x |  |  |  |  |  |  |  |  |
| c. Technical training for irrigation and potable water board members |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Prepare training needs assessment of irrigation and potable water boards based on thematic report 1 and findings of binational water school |  | To be defined |  |  |  |  |  | x |  |  |  |  |  |  |  |  |  |  |
| Develop curriculum and training materials |  | To be defined |  |  |  |  |  |  | x |  |  |  |  |  |  |  |  |  |
| Develop training of trainers’ course and materials (a course related to governance and course related to operations) |  | To be defined |  |  |  |  |  |  | x |  |  |  |  |  |  |  |  |  |
| Implement training of trainers |  | To be defined |  |  |  |  |  |  |  | x |  |  |  |  |  |  |  |  |
| Implement a test run of course in a Colombia location |  | To be defined |  |  |  |  |  |  |  | x |  |  |  |  |  |  |  |  |
| Implement a test run of course in an Ecuadorian location |  | Project Unit |  |  |  |  |  |  |  | x |  |  |  |  |  |  |  |  |
| Assess performance and adjust curriculum and materials as needed |  | To be defined |  |  |  |  |  |  |  | x |  |  |  |  |  |  |  |  |
| Prepare institutional and financial arrangements to anchor training of irrigation and potable water boards into local entities. |  | To be defined |  |  |  |  |  |  | x | x | x |  |  |  |  |  |  |  |
| 4.1.1. Three small scale innovate intervention on IWRM |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Pilot 1. Domestic wastewater treatment using vermifilters (binational) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Prepare and sign implementation agreements with local entities |  | Project unit |  |  |  | x |  |  |  |  |  |  |  |  |  |  |  |  |
| Procurement process of domestic wastewater treatment plants |  | UNDP |  |  |  | x |  |  |  |  |  |  |  |  |  |  |  |  |
| Implementation of domestic wastewater treatment plants |  | To be defined |  |  |  |  | x | x | x | x |  |  |  |  |  |  |  |  |
| Transfer to local entities |  | Project unit |  |  |  |  |  |  |  |  | x |  |  |  |  |  |  |  |
| Long-term operation by local entities |  | Local partners |  |  |  |  |  |  |  |  | x | x | x | x | x | x | x | x |
| Monitor pilot implementation and performance |  | Project unit |  |  |  |  | x | x | x | x | x | x | x | x |  |  |  |  |
| Assess experience and document lessons |  | Project unit |  |  |  |  |  |  |  |  | x |  |  |  | x |  |  |  |
| Pilot 2. Integration of hydrometeorological binational information system (binational) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Procurement process of equipment, services and personnel |  | UNDP |  |  |  | x |  |  |  |  |  |  |  |  |  |  |  |  |
| Implementation of pilot activities |  | IDEAM / INAMHI |  |  |  |  | x | x | x | x | x | x | x | x |  |  |  |  |
| Long-term operation of binational information system |  | IDEAM / INAMHI |  |  |  |  |  |  |  |  |  | x | x | x | x | x | x | x |
| Monitor pilot implementation and performance |  | Project unit |  |  |  |  | x | x | x | x | x | x | x | x |  |  |  |  |
| Assess experience and document lessons |  | Project unit |  |  |  |  |  |  |  |  | x |  |  |  | x |  |  |  |
| Pilot 3. Community bioengineering to reduce landslides (national, Colombia) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Prepare and sign implementation agreements with local entities |  | Project unit |  |  |  | x |  |  |  |  |  |  |  |  |  |  |  |  |
| Implementation of pilot activities |  | WWF |  |  |  |  | x | x | x | x |  |  |  |  |  |  |  |  |
| Post-pilot green infrastructure maintenance and operation |  | Local partners |  |  |  |  |  |  |  |  | x | x | x | x | x | x | x | x |
| Assess experience and document lessons |  | Project unit |  |  |  |  |  |  |  |  | x |  |  |  | x |  |  |  |
| 4.1.2. One pre-feasibility study on investments required for transboundary IWRM |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Procurement process of consultant firm |  | UNDP |  |  |  | x |  |  |  |  |  |  |  |  |  |  |  |  |
| Prepare pre-feasibility study |  | Contractor |  |  |  |  | x | x | x |  |  |  |  |  |  |  |  |  |
| Submit and process the proposal with public sources of project finance |  | Gobernación de Nariño |  |  |  |  |  |  |  | x | x |  |  |  |  |  |  |  |
| Implement public financed project |  | Gobernación de Nariño |  |  |  |  |  |  |  |  |  | x | x | x | x | x | x | x |
| Assess experience and document lessons |  | Project unit |  |  |  |  |  |  |  | x |  | x |  |  | x |  |  |  |
| 4.2.1. Systematisation of results, lessons and experience are available for national and international audiences |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Inception workshop |  | UNDP | x |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Train project team in safety and security in the field |  | UNDP | x |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Train project team in conflict sensitivity and conflict-sensitive planning |  | UNDP | x |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Prepare security plan for the project |  | Project unit | x |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Implement project´s security plan |  | Project unit | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x |
| Adjust multi-year workplan to be conflict-sensitive |  | Project unit | x |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Adjust first annual workplan to be conflict-sensitive |  | Project unit | x |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Prepare conflict-sensitive annual workplans |  | Project unit |  |  |  | x |  |  |  | x |  |  |  | x |  |  |  |  |
| In-person meetings of the project board |  | Project unit |  |  |  |  | x |  |  |  | x |  |  |  |  |  |  | x |
| Initiation workshop with local stakeholders in Colombia |  | Project unit | x |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Initiation workshop with local stakeholders in Ecuador |  | Project unit | x |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Onsite meetings for self-assessment and reflection with local key stakeholders implementing pilot interventions. |  | Project unit |  |  |  |  |  | x |  | x | x |  |  |  |  |  |  |  |
| Onsite meetings with women´s groups |  | Project unit |  |  | x |  |  |  | x |  |  |  | x |  |  | x |  |  |
| Annual measurement of project indicators |  | Project unit |  |  |  | x |  |  |  | x |  |  |  | x |  | x |  |  |
| Annual assessment of compliance with social and environmental safeguards |  | Project unit |  |  |  | x |  |  |  | x |  |  |  | x |  | x |  |  |
| Independent midterm review |  | Project unit |  |  |  |  |  |  |  | x |  |  |  |  |  |  |  |  |
| Independent final assessment |  | Project unit |  |  |  |  |  |  |  |  |  |  |  |  |  |  | x |  |
| Participation in IW2020 and IWC2022 |  | Project unit |  |  | x |  |  |  |  |  |  |  | x |  |  |  |  |  |
| Development of project website according to IW: LEARN guidelines, linked web portals of project partners. |  | Project unit |  | x |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Annual financial audits |  |  |  |  |  | x |  |  |  | x |  |  |  | x |  |  | x |  |
| Prepare and edit learning documents (three documents). |  |  |  |  |  |  |  |  |  |  |  |  |  | x | x |  |  |  |
| Prepare and distribute project memoirs. |  |  |  |  |  |  |  |  |  |  |  |  |  | x | x |  |  |  |
| Binational closing event with key stakeholders and beneficiaries |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | x |  |  |
| Operational project closure |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | x |  |  |
| Prepare project final report |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | x | x |