| Annex E. Stakeholder Engagement Plan |  |
| --- | --- |
| # Project: Conservation and sustainable use of indigenous agricultural genetic diversity in Hubei (C-SAP4) |  |
| # UNDP PIMS: 5822 | # GEF Project ID: TBD |

# Introduction

This document presents the stakeholder engagement plan for the UNDP-GEF project “Conservation and sustainable use of indigenous agricultural genetic diversity in Hubei”.

## Project Overview

The project is part of an innovative programmatic approach to mainstream in-situ conservation of agrobiodiversity across China and reduce key threats to globally significant genetic resources for food and agriculture (GRFA). This project is designed to remove barriers currently restricting the protection and sustainable use of local agricultural genetic diversity in Hubei province, contributing towards achievement of the long-term objective of strengthening conservation of Hubei’s globally significant agrobiodiversity, through an enhanced provincial policy framework, strengthened institutional capacity, the establishment of innovative incentive mechanisms, and improved knowledge and understanding of the economic and environmental value of local agricultural varieties.

A core focus of the project is demonstration of innovative, participatory, partnership-based and incentivized approaches that support the achievement of long-term agrobiodiversity conservation and sustainable development outcomes, including sustainable livelihood impacts for poor farming communities. Three demonstration landscapes have been identified, showcasing the following GRFA varieties: rouge rice, Wudang Tao tea and black goat. The project has a strong potential for catalytic impact, supporting institutional capacity building,  strengthened enabling environments, and the establishment of long-term partnerships between farmers, private and public sector agencies and the creation of marketing networks, certification schemes and new markets for traditional GRFA varieties.

## Stakeholder Engagement Approach

The approach to stakeholder involvement and participation encourages adherence to the following guiding principles:

- Adding value to project activities;

- Ensuring accessibility of information, including by both government and non-government, to inform decision-making processes;

- Encouraging adherence to values of transparency, trust, equity, and fairness;

- Ensuring local ownership, and the creation of outputs that are relevant and of benefit to communities;

- Supporting collaborative approaches to project interventions;

- Including different types of stakeholder groups in participatory processes, including but not limited to capacity building, skills transfer, sharing of knowledge and the increase of awareness of the value of agrobiodiversity conservation;

- Being flexible to adapt to changing circumstances;

- Fostering well-coordinated and planned implementation;

- Generating, and responding to, feedback; and

- Creating proactive partnerships that will enhance sustainability of project results after GEF funding ceases.

## Objectives of Effective Stakeholder Engagement

Effective stakeholder engagement is expected to support the project in generating the following benefits:

- Relate better to the local context;

- Provide technical excellence;

- Follow international good practice;

- Harmonize with other development partners and projects; and

- Reflect a broad range of information and perspectives.

# Summary of Stakeholder Engagement Activities during Project Preparation

Stakeholder consultations completed during the PPG phase are summarized below in Table E-1.

Table E-1: Stakeholder consultations during PPG phase

| Date | Activity | Location | Remarks |
| --- | --- | --- | --- |
| 10 Apr 2018 | C-SAP program inception workshop | Beijing | The objectives of the C-SAP program and each child project, including the Hubei project were described. The project preparation phase activities and timeframes were discussed. |
| 16 Apr 2018 | C-SAP4 project inception workshop | Wuhan | The objective of the C-SAP4 project were discussed with provincial stakeholders, PPG tasks were outlined, and feedback obtained during workshop discussions. |
| 17 Apr 2018 | Visit to and consultations, Yunyang County | Yunyang County | Consultations and field visits were made with local government officials, enterprises and farmers in where rouge rice is cultivated and processed |
| 18 Apr 2018 | Visit to and consultations, Yunxi County | Yunxi County | Consultations were made with local government officials and farmers in where Maotou goat is bred. |
| 19 Apr 2018 | Visit to and consultations, Danjiangkou County | Danjiangkou Conty | Consultations and field visits were made with local government officials, enterprises and farmers in where Wudang Tao tea is cultivated and processed. |
| 19 Apr 2018 | Stakeholder consultations | Wudangshan Township | A stakeholder consultation was held in Wudangshan Township with local officials and other stakeholders, to discuss potential project activities in the Danjiangkou Reservoir area. |
| 01 May 2018 | Visit to and consultations, Xishui County | Huanggang City | Consultations and field visits were made with local government officials, enterprises and farmers in where black goat is bred. |
| 05 Jun 2018 | Visit Consultations with Hubei Agricultural Resources and Planning Office | Wuhan | Hubei Agricultural Resources and Planning Office is taking the responsibility for agricultural resources management for policy making. Consultation was made to make cooperation between agricultural resource management and biodiversity conservation. |
| 08 Jun 2018 | Consultations with Wuhan Agricultural Remote Sensing Center of ministry of Agriculture | Wuhan | Wuhan Agricultural Remote Sensing Center of ministry of Agriculture is a research institute. The consultations are focused on the mapping of the landscape of rouge rice and Tao tea. |
| 10-27 Jun 2018 | Consultations with Hubei government officers | Wuhan | For scorecard: Hubei Provincial Dept Agriculture Hubei Provincial Dept Ecology & Environment Hubei Provincial Dept Forestry Hubei Provincial Dept Land and Resources Hubei Provincial Dept Water Hubei Provincial Dept Poverty Alleviation Hubei Provincial Dept Education Hubei Provincial Dept Finance Hubei Provincial Women's Federation Hubei Provincial Youth League Committee |
| 22-28 Jul 2018 | Field visits to and consultations at Yugang village (Black goat) | Sanhua Township, Xishui County | Field visits and consultations with local government officials, representatives of agriculture associations and enterprises, and farmers in Yugang village, to gather socioeconomic information and to discuss interest and potential activities associated with the rouge rice. |
| 4-11 Aug 2018 | Field visits to and consultations at Huangcaopo village (Tao tea) | Yanchihe Township, Danjiangkou County | Field visits and consultations with local government officials, representatives of agriculture associations and enterprises, and farmers in Huangcaopo village, to gather socioeconomic information and to discuss interest and potential activities associated with the rouge rice. |
| 28 Aug – 1 Sep 2018 | Field visits to and consultations at Dadunzi village Rouge rice) | Baoxia Township, Yunyang County | Field visits and consultations with local government officials, representatives of agriculture associations and enterprises, and farmers in Dadunzi village, to gather socioeconomic information and to discuss interest and potential activities associated with the rouge rice. |
| 20 Sep 2018 | Field visits to and consultations at Sanhua Tow | Sanhua, Xishui | Field visits and consultations with local farmers and company |
| 9 Oct 2018 | Field visits to and consultations at Wudangkou | Wudangshan, Dangjiangkou County | Field visiting and consultation with Shengwu Tea Company and local farmers |
| Jul-Nov 2018 | Consultations with Universities in Hubei | Wuhan and Yichang | Four professors who study biodiversity in Hubei province, From Central China Normal University, Chinese University of Geology Chang Jiang University, Three Gorge University |
| 7 Nov 2018 | C-SAP4 PPG review workshop | Wuhan | A PPG review workshop was held in Wuhan with provincial and county officials, representatives of agricultural associations and enterprises, and other stakeholders to discuss proposed project outputs and activities and remaining steps before completing the project document for review. |

# Project Stakeholders

The project will engage with a broad spectrum of stakeholders, utilizing existing structures as much as practicable. A stakeholder analysis is summarized below in Table E-2, which indicates the interest of each stakeholder group in relation to the project, the estimated effect on project interests and their importance and influence on the project.

Table E-2: Stakeholder Analysis

| Stakeholders |  | Interests at stake in relation to project | Effect of project on interests (+ 0 -) | Importance 1=Little/No Importance 2=Some Importance 3=Moderate Importance 4=Very Important 5=Critical player | Influence 1=Little/No Influence 2=Some influence 3=Moderate Influence 4=Significant Influence 5=Very Influential |
| --- | --- | --- | --- | --- | --- |
| Implementing partner: |  |  |  |  |  |
| 1 | Hubei Department of Agriculture and Rural Affairs (DARA) | Strengthen policies and capacities on agrobiodiversity management | + | 5 | 5 |
| GEF agency: |  |  |  |  |  |
| 2 | UNDP | Ensure global environmental benefits are generated, and effective and efficient project implementation | + | 5 | 5 |
| Key national agencies and central governmental stakeholders: |  |  |  |  |  |
| 3 | Ministry of Finance | Efficient utilization of resources and cofinancing delivered | + | 5 | 5 |
| 4 | Ministry of Agriculture and Rural Affairs (MARA) | Contributions towards national level objectives on agrobiodiversity management | + | 4 | 4 |
| Key provincial agencies and governmental stakeholders: |  |  |  |  |  |
| 5 | Hubei Department of Finance | Efficient project implementation, according to provincial policies and procedures | + | 5 | 5 |
| 6 | Hubei Department of Ecology and Environment | Strengthened capacities and integration of agrobiodiversity into sectoral strategies | + | 3 | 2 |
| 7 | Hubei Department of Natural Resources | Strengthened capacities and integration of agrobiodiversity into sectoral strategies | + | 3 | 2 |
| 8 | Hubei Development and Reform Commission | Strengthened capacities and integration of agrobiodiversity into provincial development strategies | + | 3 | 2 |
| 9 | Hubei Office of Poverty Alleviation | Strengthened capacities and integration of agrobiodiversity into poverty alleviation strategies | + | 3 | 2 |
| 10 | Hubei Department of Education | Strengthened capacities and integration of agrobiodiversity into sectoral strategies | 0 | 2 | 2 |
| 11 | Hubei Department of Water Resources | Strengthened capacities and integration of agrobiodiversity into sectoral strategies | 0 | 2 | 1 |
| Local government unit stakeholders: |  |  |  |  |  |
| 12 | Prefecture and county Agriculture Bureaus; Township Agriculture Stations | Scale-able demonstrations of participatory approaches to agrobiodiversity management, and strengthened capacities | + | 4 | 4 |
| Social organizations and non-governmental organizations (NGOs) |  |  |  |  |  |
| 13 | All-China Women’s Federation | Strengthened capacities and promotion of women empowerment | + | 4 | 2 |
| 14 | Communist Youth League of China | Strengthened capacities and promotion of youth inclusion | + | 2 | 1 |
| 15 | Other social organizations | Promotion of development objectives associated with agrobiodiversity management | + / 0 | 2 | 1 |
| Local communities where project interventions are planned: |  |  |  |  |  |
| 16 | Local communities, farmers | Increased knowledge, strengthened capacities, sustainable livelihood opportunities, expanded or new partnerships | + | 5 | 4 |
| Agricultural associations, including cooperatives: |  |  |  |  |  |
| 17 | Agricultural associations, including cooperatives | Increased knowledge, strengthened marketing and organizational capacities, expanded or new partnerships | + | 4 | 3 |
| Enterprises: |  |  |  |  |  |
| 18 | Enterprises engaged in GRFA varieties | Increased knowledge, strengthened marketing and organizational capacities, improved supply/value chain management, expanded or new partnerships | + | 4 | 3 |
| 19 | Trade associations | Promotion of best management practices and marketing opportunities for members | 0 | 2 | 2 |
| Academic and research organizations: |  |  |  |  |  |
| 20 | Academic and research organizations | Strengthened capacities, dissemination of best practices and approaches in agrobiodiversity management | + | 3 | 2 |
| Certification Organizations |  |  |  |  |  |
| 21 | Certification Organizations for geographical indication, organic food, etc. | Increased awareness of GRFA varieties, promotion of best management practices | + | 2 | 2 |

# Stakeholder Engagement Plan

## Project-Specific Stakeholder Engagement Considerations

The project objective to “strengthen the in-situ conservation and sustainable use of globally significant agrobiodiversity in Hubei through the development of incentive mechanisms for farmers to sustain populations of endemic crops and livestock, the establishment of a supportive ‘enabling environment’ and strengthened institutional capacity” will be achieved through four mutually supportive outcomes, distributed across the following four components:

Component 1: Enhanced provincial policy and regulatory framework

Outcome 1: Provincial framework for in-situ agrobiodiversity conservation enhanced by strengthened enabling policies, regulations and strategies and improved inter-sectoral and cross-sectoral coordination

Component 2: Demonstration of sustainable incentive mechanisms for in-situ conservation and sustainable use of agrobiodiversity

Outcome 2: Market- and non-market-based incentive mechanisms established and demonstrated in target landscapes to increase conservation and sustainable use of GRFA and enable long-term livelihood benefits for local farmers

Component 3: Mainstreaming of approaches and strengthened institutional capacity

Outcome 3: Demonstrated approaches mainstreamed and capacities strengthened to facilitate upscaling of incentivized conservation and sustainable use of GRFA

Component 4: Knowledge management and monitoring & evaluation

Outcome 4: Knowledge, attitudes and practices improved, and knowledge management structures enhanced to broaden participation in the conservation and sustainable use of GRFA

Effective stakeholder engagement will be one of the key factors in the implementation of the project.

Under Component 1, the project will facilitate stakeholder engagement and dialogue into the development of provincial and county GRFA implementation frameworks and ensuring that market-based and non-market-based incentive mechanisms for expanding engagement of GRFA farming will equitable reflect the capacities, needs and priorities of women and men farmers. Recommendations for allocating eco-compensation appropriations towards GRFA conservation will consider equitable benefits to women and men. The GRFA Intersectoral Coordination Committee will function as a central stakeholder engagement platform, established in Component 1 and influencing the entire project.

Stakeholder engagement under Component 2 is focused at the local level, starting with the establishment of GRFA Landscape Coordination Committees in each of the three demonstration landscapes. The committees will help ensure that project interventions are inclusive and consider a cross-section of stakeholder interests. Activities involving strengthening marketing capacities and development of GRFA markets will help strengthen and expand partnerships between public and private stakeholders, with the underlying aim to deliver sustainable livelihood benefits for local farmers, with equitable participation by women and youth.

Under Component 3, institutional stakeholder capacity development activities will also promote equitable involvement of women and youth. Sectoral work programs at the province and county levels will be developed through proactive stakeholder engagement. Best management practices demonstrated in Component 2 will be upscaled to other landscapes in the province, including sharing the effective stakeholder engagement approaches applied.

The stakeholder engagement plan will be presented during the project inception workshop under Component 4, and adaptive management adjustments made, e.g., in case circumstances change between the time of project development and initiation of project implementation. Monitoring and evaluation of the stakeholder engagement plan are included in the project M&E plan and project progress reports will document findings and present any adaptive management measures taken and recommendations. The knowledge, attitudes and practices (KAP) baseline survey will address differences between women and men, and the resultant knowledge management strategy and action plan will include specific actions to address these differences. Lessons learned will be shared across the C-SAP program using the program level knowledge management platform, the program steering committee, exchange visits among the child projects and informal interactions among the project teams.

## Long-term Stakeholder Participation

The project will facilitate long-term stakeholder participation, with a special emphasis on the active participation of women and youth, and enhancement of intersectoral coordination for implementing agrobiodiversity management strategies and plans.

Decision-making – through the establishment of the Project Steering Committee (PSC). The establishment of the structure will follow a participatory and transparent process involving the confirmation of all key project stakeholders; conducting one-to-one consultations with stakeholders; refinement of the terms of reference and ground-rules; inception meeting to agree on the constitution of the PSC.

Capacity building – at systemic, institutional and individual levels – is one of the key strategic interventions of the project and will target stakeholders that have the potential to be involved in implementation of the project, including demonstration activities at the local level. Women and youth present within the project sites will be proactively considered for capacity building activities.

Communication - will include the participatory development of knowledge management strategy and action plan. The knowledge management strategy will be based on the following key principles: providing information to stakeholders; promoting dialogue between stakeholders; and promoting access to information.

The project design incorporates several features to ensure on-going and effective stakeholder participation in the project’s implementation. The mechanisms to facilitate involvement and active participation of different stakeholders in project implementation will comprise several different components, as described below.

### Project Inception Workshop

The project will be launched by a multi-stakeholder inception workshop, building on the PPG review workshops already held. The inception workshop will provide an opportunity to provide stakeholders with the most updated information on the project, refine and confirm the work plan and results framework, and will establish a basis for further consultations as the project implementation phase commences.

### Project Steering Committee

The Project Steering Committee’s membership will ensure representation of key interests throughout the 5-year project implementation timeframe. The members and terms of reference of the steering committees are described in the Governance and Management Arrangements section  and Annex C to the project document. The establishment of this structure will follow a participatory and transparent process involving the confirmation of  key project stakeholders and nominated focal points. The inception workshop will agree on the constitution of the committee, and finalization of its terms of reference and ground-rules.

### Project Management Office and Focal Points among Provincial and Local Government Units

The Project Management Office (PMO) will take direct operational responsibility for facilitating stakeholder involvement of the project and its results. The PMO will be located in the Hubei Department of Agriculture and Rural Affairs (DARA) offices in Wuhan to ensure coordination among key stakeholder groups at provincial and local government levels.

The National Project Director (NPD), the Deputy Director General of the Hubei DARA, will be accountable to the DARA and UNDP for the achievement of objectives and results in the assigned project. The NPD will be a member and chair of the Project Steering Committee and answer to it. The NPD will be financed through provincial government cofinancing fund. The NPD will designate focal points within the county agriculture bureaus for each of the three target counties; these local government focal points will garner support for the project within their organizations and other stakeholder groups.

### GRFA Intersectoral Coordination Committee and Activity Level Working Groups

The project will facilitate establishment of a GRFA Intersectoral Coordination Committee, having representatives from key provincial agencies. This committee will be an important stakeholder engagement platform, providing advisory support to the project, e.g., reviewing policy and regulatory reforms, eco-compensation guidelines and systems and procedures for improving knowledge management.

At the activity level, working groups will be established as required, e.g., policy reform, to facilitate the active participation of affected institutions, organizations and individuals in the implementation of the respective project activities. Different stakeholders may take the lead in each of these groups, depending on their respective mandates. There will be representation of women according to the targets of the project’s gender action plan in working groups and activities such as capacity building and awareness programs.

### GRFA Landscape partnership working groups

The project will establish landscape partnership working groups in each of the three demonstration landscapes that will oversee completion of participatory landscape assessments and development of GRFA conservation and sustainable use plans. Through the function of the landscape coordination committees and joint planning activities, participatory structures will be developed, improving information sharing and awareness among stakeholders.

### Project Knowledge Management and Communications

The project will develop, implement and annually update a knowledge management strategy and action plan to ensure that stakeholders are informed on an ongoing basis about the project activities, overall project progress, and the opportunities for stakeholders’ involvement in various aspects of the project’s implementation.

# Resources, Roles and Responsibilities

The PMO, led by the Project Manager, will be responsible for implementation of the stakeholder engagement plan and for installing adaptive management measures as deemed relevant based on progress made on project activities. The GRFA Intersectoral Coordination Committee will be responsible for providing technical and strategic guidance during implementation, and the committee members might be invited to make presentations at Project Steering Committee meetings as needed. At the local level, the GRFA Landscape partnership working groups will be the main stakeholder engagement structures for guiding the activities associated with the three demonstration landscapes. Engagement with multilateral and bilateral financial and technical cooperation agencies will be facilitated largely through technical advisory arrangements and networking on complementary projects and initiatives, as described below in Table E-3.

Table E-3: Stakeholder engagement roles and responsibilities

| Position / Function | Roles and Responsibilities |
| --- | --- |
| National Project Director | The National Project Director (NPD) will have overall responsibility for the implementation of the project. The NPD will ensure that the project operates according to relevant national and provincial policies and procedures. |
| Project Manager | The Project Manager will have responsibility for the day-to-day implementation of the project, be tasked with the important role of ensuring that stakeholders are engaged according to plan, oversee the procurement and implementation of project activities and be accountable that stakeholder engagement is inclusive and according to plan. |
| Project Steering Committee | The Project Steering Committee (PSC) will provide strategic oversight to the project, ensuring that the interests of the representative members are considered, including stakeholder engagement objectives. |
| GRFA Intersectoral Coordination Committee | The GRFA Intersectoral Coordination Committee will be comprised of provincial stakeholders having mandates that include aspects related to in-situ conservation and sustainable use of agrobiodiversity. |
| All-China Women’s Federation | A representative of the provincial office of the All-China Women’s Federation (ACWF) will be included onto the PSC and the GRFA Intersectoral Coordination Committee, providing an important linkage between the national and provincial gender mainstreaming objectives with those of the project. |
| Local Government Unit Focal Points | Project focal points will be designated in the three counties where project demonstrations are planned. These focal points will be responsible to ensure local stakeholders are engaged in the project, with particular emphasis on participation of women and youth. |
| Landscape partnership working groups | Landscape partnership working groups are planned in each of the three demonstration landscapes, and include representation by local governments, farmers, agricultural associations, enterprises and NGOs. These committees will ensure stakeholder engagement through the community-level project interventions. |
| C-SAP Program M&E / Coordination Officer | The C-SAP program coordination team will include a Monitoring & Evaluation (M&E) / Coordination Officer, tasked with coordinating M&E across the five child projects. This officer will provide advisory support to the Project Manager and other project stakeholders, sharing approaches and lessons learned regarding stakeholder engagement and other aspects of the program M&E plan. |
| C-SAP Program KM / Communications Officer | The C-SAP program coordination team will also include a Knowledge Management (KM) / Communications Officer, who will be responsible for the development and implementation of the program level KM strategy and action plan and providing advisory support to the child projects, including sharing approaches and lessons learned. |

# Grievance Mechanism

Interested stakeholders may raise a grievance at any time to the Project Management Office, the Executing Agency (Hubei DARA) or the Implementing Agency (UNDP).

Due diligent efforts will be made by the local project representatives to first resolve grievances locally, in a manner sensitive to local social and cultural norms. If the local process does not result in resolution of a grievance, the case will be upgraded to the PMO (Executing Agency), with the process managed by the Project Manager and National Project Director providing guidance and signing off on written responses to grievances.

The UNDP Country Office, as the Implementing Agency, will be the next avenue for resolving grievances if the case is not resolved at the local level or by the Executing Agency. The Resident Representative will identify a member of the Country Office management team to oversee and manage the grievance through the UNDP Stakeholder Response Mechanism (SRM). The SRM ensures individuals, peoples, and communities affected by projects have access to appropriate grievance resolution procedures for hearing and addressing project-related complaints and disputes. Further information, including how to submit a grievance to the SRM is found on the UNDP website at: http://www.undp.org/content/undp/en/home/operations/accountability/secu-srm/

# Timetable

Stakeholder engagement will be facilitated through the Project Steering Committee, the GRFA Intersectoral Coordination Committee, the GRFA Landscape partnership working groups, and through organizing workshops, trade fairs, awareness campaigns. An indicative stakeholder engagement schedule is listed below in Table E-4.

Table E-4: Indicative stakeholder engagement schedule

| No. | Description | Timing | Location |
| --- | --- | --- | --- |
| 1 | Project Inception workshop | Year 1 | Wuhan |
| 2 | Program Inception workshop | Year 1 | Beijing |
| 3 | Project Steering Committee | Annual | Wuhan in Year 1 and rotating among the demonstration landscapes in other years |
| 4 | C-SAP Program Steering Committee (host one program steering committee meeting, showcasing results achieved and providing an opportunity to share lessons learned and experiences) | To be determined | Wuhan, with field visit(s) to demonstration landscape(s) |
| 5 | GRFA Coordination Committee | Est. 2X per year | Wuhan |
| 6 | GRFA Landscape partnership working group, rouge rice | Est. quarterly | Baoxia Township, Yunyang County |
| 7 | GRFA Landscape partnership working group, Wudang Tao tea | Est. quarterly | Yanchihe Township, Danjiangkou County |
| 8 | GRFA Landscape partnership working group, black goat | Est. quarterly | Sanhua Township, Xishui County |
| 9 | Provincial workshop to inform stakeholders of the GRFA strategies and regulatory frameworks developed | Year 3 | Wuhan |
| 10 | Provincial workshop, inviting governmental and non-government sector, agriculture associations, enterprises, etc., to discuss eco-compensation opportunities | Year 2 | Wuhan |
| 11 | Workshop to share best practices and lessons learned on application of traditional knowledge for agrobiodiversity management | Year 4 or 5 | Wuhan |
| 12 | Provincial trade fair, promoting GRFA products and offerings, showcasing nutritional and taste value of GRFA varieties and to facilitate marketing and partnership opportunities, with a special focus on inclusion of women and youth. | Year 3 or 4 | Wuhan |
| 13 | County trade fair, promoting GRFA products and offerings, showcasing nutritional and taste value of GRFA varieties and to facilitate marketing and partnership opportunities, with a special focus on inclusion of women and youth. | Year 3 or 4 | Yunyang County |
| 14 | County trade fair, promoting GRFA products and offerings, showcasing nutritional and taste value of GRFA varieties and to facilitate marketing and partnership opportunities, with a special focus on inclusion of women and youth. | Year 3 or 4 | Danjiangkou County |
| 15 | County trade fair, promoting GRFA products and offerings, showcasing nutritional and taste value of GRFA varieties and to facilitate marketing and partnership opportunities, with a special focus on inclusion of women and youth. | Year 3 or 4 | Xishui County |
| 16 | Provincial workshop to disseminate information on incentivized approaches for participatory GRFA conservation and sustainable use | Year 4 or 5 | Wuhan |
| 17 | County workshop to disseminate information on incentivized approaches for participatory GRFA conservation and sustainable use | Year 4 or 5 | Yunyang County |
| 18 | County workshop to disseminate information on incentivized approaches for participatory GRFA conservation and sustainable use | Year 4 or 5 | Danjiangkou County |
| 19 | County workshop to disseminate information on incentivized approaches for participatory GRFA conservation and sustainable use | Year 4 or 5 | Xishui County |
| 20 | Advocate the global environmental benefits generated through the project by participating in national, regional and international conferences, workshops, seminars and other events | To be determined | To be determined |
| 21 | Organize awareness raising and advocacy campaigns, focused on specific themes and aimed at defined target groups, e.g., farmers, governmental agencies, enterprises and the public, through methods identified in the knowledge management action plan, e.g., social media, printed media, radio, local and provincial TV, etc. | To be determined | To be determined |

# Monitoring and Evaluation

The implementation of the stakeholder engagement plan will be monitored and evaluated through the 5-year project timeframe. Stakeholder engagement details will be captured in project reports, meeting memorandums and through various knowledge products. Adaptive management measures will be put in place, as needed, to adjust the plan to current circumstances and according to the findings of monitoring and evaluation efforts.

Monitoring and evaluation of the implementation of the stakeholder engagement plan are part of the project M&E plan, and cofinancing contributions are included.