United Nations Development Programme

Project Document

| Project title: Strengthening coordinated approaches to reduce invasive alien species (IAS) threats to globally significant agrobiodiversity and agroecosystems in China |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Country: People’s Republic of China | Implementing Partner: Ministry of Agriculture and Rural Affairs |  |  |  | Management Arrangements: National Implementation Modality (NIM) |
| UNDAF/Country Programme Outcome: Outcome 2: More people enjoy a cleaner, healthier and safer environment as a result of improved environmental protection and sustainable green growth |  |  |  |  |  |
| UNDP Strategic Plan Output: 1.4.1 Solutions scaled up for sustainable management of natural resources, including sustainable commodities and green and inclusive value chains |  |  |  |  |  |
| UNDP Social and Environmental Screening Category: Moderate |  |  | UNDP Gender Marker: GEN 2 |  |  |
| Atlas Project ID (formerly Award ID): 00096221 |  |  | Atlas Output ID (formerly Project ID): 00100197 |  |  |
| UNDP-GEF PIMS ID number: 5821 |  |  | GEF ID number: 9874 |  |  |
| Planned start date: September 2019 (Estimated) |  |  | Planned end date: August 2024 (60 months) |  |  |
| PAC meeting date: May 2019 (TBD) |  |  |  |  |  |
| Brief project description: China is one of Vavilov’s eight ‘independent centers of crop origin’ and more than 130 of the world’s crop species originates from here, including vast numbers of rice, soybean and wheat varieties as well as fruits like wild litchi. Around 85% of China’s plant genetic resources stem from local varieties. In recognition of this, the GEF-6 biodiversity strategy lists eastern China as a global priority for genetic reserve conservation. The project provinces Hainan and Chongqing are some of the most biodiverse rich provinces in China which is also reflected in the amount of varieties found within the provinces. However, China’s agrobiodiversity, which is an important part of its heritage, is facing an increasing threat from the encroachment of invasive alien species, that are substantially impacting the agroecosystems and the biodiversity, including traditional varieties and the genetic resources from food and agriculture (GRFA) within. The long-term solution is to strengthen the protection of the globally important agrobiodiversity in China through reducing threats and strengthening and mainstreaming IAS prevention, control and management into government and sectoral planning. This is currently constrained by the following barriers: Incomprehensive policy, legal and management frameworks and lack of sector and national, provincial and county level integration. Lack of comprehensive assessment, monitoring, early warning and rapid response tools, and the institutional capacity to use them; lack of effective and adopted approaches for controlling IAS impacts on agrobiodiversity and weak public and institution awareness of the positive impacts of IAS Management. The project will seek to remove these barriers through the following Components: 1) Strengthened Enabling Environment; 2) Strengthened IAS management frameworks and institutional capacity; 3) Demonstration of IAS threat reduction in agroecosystems and 4) Raise the awareness, knowledge management and coordination. Key results of the project will be the long-term threat reduction of 35,000 ha of agricultural landscapes in Hainan and Chongqing and the build capacity of 12,000 government employees working with IAS prevention, control and management at national, provincial and country levels. The capacity of 6,000 farmers and others working within the agricultural sector in local communities will likewise be build. |  |  |  |  |  |
| Financing Plan |  |  |  |  |  |
| GEF Trust Fund or LDCF or SCCF |  |  | USD 2,789,908 |  |  |
| UNDP TRAC resources |  |  | USD 0 |  |  |
| Cash co-financing to be administered by UNDP |  |  | USD 0 |  |  |
| - Total Budget administered by UNDP |  |  | USD 2,789,908 |  |  |
| Parallel co-financing |  |  |  |  |  |
| UNDP |  |  | USD 0 |  |  |
| Government |  |  | USD17,040,000 |  |  |
| Private Sector |  |  | USD 1,860,000 |  |  |
| - Total co-financing |  |  | USD 18,900,000 |  |  |
| - Grand-Total Project Financing (1)+(2) |  |  | USD 21,689,908 |  |  |
| Signatures |  |  |  |  |  |
| Signature: print name below |  | Agreed by Government |  | Date/Month/Year: |  |
| Signature: print name below |  | Agreed by Implementing Partner |  | Date/Month/Year: |  |
| Signature: print name below |  | Agreed by UNDP |  | Date/Month/Year: |  |

# Table of Contents

I.	Table of Contents	3

II.	Development Challenge	1

III.	Strategy	12

IV.	Results and Partnerships	21

V.	Project Management	67

VI.	Project Results Framework	69

VII.	Monitoring and Evaluation (M&E) Plan	78

VIII.	Governance and Management Arrangements	85

IX.	Financial Planning and Management	92

X.	Total Budget and Work Plan	96

XI.	Legal Context	107

XII.	Risk Management	107

XIII.	Mandatory Annexes	110

Annex A: Multi-year Workplan	110

Annex B: Overview of technical consultancies/subcontracts	110

Annex C: Terms of Reference for Project Steering Committee, Project Coordinator, Chief Technical Advisor and other positions	110

Annex D: UNDP Social and Environmental and Social Screening Template (SESP)	110

Annex E: Stakeholder Engagement Plan	110

Annex F: Gender Analysis and Action Plan	110

Annex G: UNDP Risk Log	110

Annex H: Results of the capacity assessment of the project implementing partner and HACT micro assessment	110

Annex I: Additional agreements: (i) co-financing letters; (ii) draft LOA between UNDP and MEE/FECO and UNDP and GACC/CAIQ	110

Annex J: UNDP Project Quality Assurance Report	110

Annex K: Social Economic survey	110

Annex L:  Situation analysis	110

Annex M: KAP Methodology	110

Annex N: Capacity Development Scorecards	110

Annex O: Yangpu Scorecard	110

Annex P: Yangpu port description	110

Annex Q: Landscape profiles	110

Annex R: Program Organizational Chart	110

Annex S: C-SAP Program Results Framework	110

Annex T: GEF Core Indicators	110

Annex U: Roles of Implementing Partner and Co-Implementing Partners in activity implementation	110

Annex V: Stakeholder involvement in project activities.	110

Acronyms and abbreviations:

ACWF	All China Women’s Federation

BSAP 	Biodiversity Strategy and Action Plan

CAAS	Chinese Academy of Agricultural Sciences

CAS	Chinese Academy of Sciences

C-IP	Co-Implementing Partner

CMES	Coordination, Monitoring and Evaluation Secretariat

CO	Country Office

COP	Conference of the Parties

CRAES               Chinese Research Academy of Environmental Sciences

C-SAP	China – Sustainable Agriculture Program

DNA	Deoxyribonucleic acid

DSTE	Department of Science, Technology and Education

ECBP	EU China Biodiversity Program

ERC	Evaluation Resource Center

FECO	Foreign Economic Cooperation Office

FAO	Food and Agricultural Organization

GACC	General Administration of Customs

GEF	Global Environment Facility

GIS	Geographic Information System

GRFA                 Genetic Resources from Food and Agriculture

GRM	Grievance Redress Mechanism

Ha	Hectare

IAIP	Invasive Alien Insect Pests

IEO	Independent Evaluation Office

M&E	Monitoring and Evaluation

MARA	Ministry of Agriculture and Rural Affairs

MEE	Ministry of Ecology and Environment

MOF	Ministry of Finance

MOOC	Massive Open Online Courses

MTR	Mid-term Review

MU	Management Units

NBSAP	National Biodiversity Conservation Strategy and Action Plan

NIM	National Implementation Modality

NSAP	National Strategic Action Plan

OAI	Office of Audit and Investigations

OFP	Operational Focal Point

PIR	Project Implementation Report

PMO	Project Management Office

POPP	Programme and Operations Policies and Procedures

PPG	Project Preparation Grant

PCR	polymerase chain reaction

PSAP	Provincial Strategic Action Plan

PSC	Project Steering Committee

ROAR	Result Oriented Annual Reporting

SBAA	Standard Basic Assistance Agreement

SES	Social Environmental Standards

SESP	Social Environmental Screening Procedures

SFGA	State Forestry and Grassland Administration

TE	Terminal Evaluation

UNDP	United Nations Development Programme

USD	United States Dollars.

# Development Challenge

- China is one of 15 mega-diverse countries, as well as one of Vavilov’s eight ‘independent centers of crop origin’ and the place of origin of more than 130 of the world’s crop species, including wild litchi, kiwi, chestnuts, apples and a wealth of other edible plants and fruits. Around 85% of China’s plant genetic resources stem from local varieties evolved through cropping practices and traditional husbandry across China’s diverse environmental and cultural landscapes. The cultivated crops in China count more than 1350 species, but more importantly more than 2170 wild relatives exist, such as 420 wild relatives of fruit trees and 103 wild relatives of food crops, including rice and millet. Further expanding the country’s genetic resources from food and agriculture (GRFA), an exuberant number of varieties exist. China has over 70,000 varieties of cultivated and wild rice, 30,000 varieties of millet, 20,000 varieties of soybean, 6,000 varieties of buckwheat and more than 7,000 varieties of oats. Based on this, the GEF-6 biodiversity strategy lists eastern China as a global priority for genetic reserve conservation.

- China’s agrobiodiversity is an important part of its heritage. For one, Hainan Island, which is home to more than 4,200 plant species, contains globally important agrobiodiversity that is unique for China and has a wide range of endemic tropical fruits, that are only found there. There are 142 species of tropical fruit, among which 66 species are cultivated, with over 170 local varieties of among other mango, banana, seedless litchi, rambutan, longan, shaddock, orange and lemon. Unofficial records refer to litchi in China, as far back as 2,000 BC, and endemic wild mango species has been cultivated in Hainan for over 400 years. Shanlan rice, although it may have originated from common wild rice from Guangdong and Hunan province, is a traditional upland rice variety, well-suited to mountainous areas and it is very popular for daily consumption in Hainan. Today over 400 Shanlan rice varieties are known in Hainan, including black-kerneled varieties.

- As another example, Chongqing houses more than 1,000 varieties of agricultural crops, including 195 rice species, 12 varieties of sweet potato, 59 maize varieties, as well as wheat, citrus and the raw lacquer tree. In addition, there are more than 5270 species of medicinal plants in Chongqing and the Municipality rank’s fifth in China with regard to specie occurrence.

- This project is one of five child projects under the PRC-GEF Partnership Program for Sustainable Agricultural Development (C-SAP Program), which objective is to support the implementation of the Sustainable Development Goals and China’s National Plan for Sustainable Development of Agriculture (2015-2030). The C-SAP 2 IAS project focuses on addressing threats posed by alien invasive species (IAS) to agrobiodiversity, including traditional varieties and Genetic Resources from Agriculture (GRFA).

- When IAS enter an area with no natural enemies, or local competition, they will spread unhindered and colonize the area. Depending upon the aggressiveness of the IAS spread, it can impact communities, or ecosystems, by decreasing local plant species diversity, alter the rate of nutrient cycles and can potentially influence the population dynamics of resident species, resulting in community changes and habitat structures, as well as ecosystem functions, leading to an erosion of China’s genetic and species diversity, including agrobiodiversity in the agroecosystems.

- The impacts of IAS on the agroecosystems, found in all of China’s provinces, have not been quantified, but the economic cost of IAS in China, provides a proxy for its scale. It has been estimated to be between 14.5 – 18.9 billion USD annually, where the direct loss to agriculture are mostly caused by a few species, including crofton weed A. adenophora, alligator weed A. philoxeroides, common ragweed A. artemisiifolia, whitefly B. tabaci and Trialeurodes vaporariorum and vegetable leafminer Liromyza sativae.  Reported direct economic losses caused by A. philoxeroides and A. artemisiifolia  alone have been estimated to be 4,4 billion USD annually. Furthermore, it is estimated that the indirect economic loss to China’s agroecosystem service functions resulting from A. adenophora invasions is 1.4 billion USD annually.

Root causes and drivers:

- Abandonment and idleness of agricultural lands: The rural areas in China have undergone a drastic change in the wake of the country’s rapid urbanization and economic growth. Rural-to-urban migration is a main cause for this change, where more than 200 million rural migrant workers have employment in China’s big cities. A direct impact of this is a reduction of the productive areas in the villages, where the remaining farmers engage in farming on their more easily accessible and productive plots, thereby reducing their opportunity cost. As a result, more remote, difficult to access, farming plots or poor-quality plots are abandoned. Surveys undertaken of households in 262 counties in 29 provinces in 2011 and 2013 by the China Family Financial Survey and Research Center found that, respectively, 13.5% and 15% of agricultural land were idle. In Yulin city in Shaanxi province, for instance, 80.8 thousand ha (13.9%) have been abandoned.  For additional information on this and the below mentioned root causes and drivers see Annex L, as well as other baseline analysis documentation in Annex K and Annex Q

- With land not being actively managed, it is left open for encroachment by IAS, which have a comparative advantage over the natural occurring resident species in the succession process. In Qianxinan Prefecture Guizhou, alone, 40,000 ha of farm and grassland have been impacted by crofton weed Eupatorium adenophurum. The expansion of the IAS, through the idle farm land, places an increased pressure on the productive lands, which previously had been buffered by the more marginal lands that were farmed prior to the abandonment.

- Agricultural production systems: The push towards a modern country side, which among other is relying on the consolidation of land and an increase and improvement of production methods, has led to a landscape simplification and reduced habitat heterogeneity. The mono-agricultural production systems of, for instance rice and soybean, expand the living areas of IAS and lessen the distances between suitable patches. This is particularly important for species with poor dispersal abilities such as L. oryzophilus and B. longissima.

- And while the consolidation of farmland, for instance through farming cooperatives, is on the rise, China is predominantly based on a smallholder farming system with small farm-plots scattered through-out the villages’ farmlands. This often provides for a localized assortment of crops, including high-value commodities like fruits and vegetables, which in turn provides for a diverse food source for, for instance, the vegetable leafminer, L. sativae and other invasive insect species.

- Past intentional introduction: Many of the IAS species found in China today have been intentionally introduced in the past. For instance, A. philoxeroides was used as horse fodder in the 1930s in Shanghai and Zhejiang province, and in southern China as swine feed in the 1950s, but its distribution changed radically in the 1980s, with the halt of these practices, it has now become one of the most notorious weeds in China’s agroecosystems.

- In a similar manner was the growing of water hyacinth Eichhornia crassipes, as animal fodder, actively encouraged by local governments in the 1960-70s. With the abandonment of the active cultivation and management of the specie, it spread to rivers and lakes in Southern China causing damage to ecosystems, in as many as 20 provinces.

- Another example is the golden apple snail Pomacea canaliculata, initially introduced for food production in Guangdong in the 1980s. Due to the large economic interest in the aquaculture of the species, productions sites spread to 11 provinces within ten years, followed by a decline after the 1990s, caused by poor economic returns and the apparent, significant and unintended crop damage, resulting from the snails. While the active aquaculture production of the golden apple snail has by and large ceased, the spread of the snail has continued and, like water hyacinth, is one of the specie included in the “First Priority” IAS species list, containing 52 of the most serious IAS found in China.

- Increase in transportation hubs and trade-routs: The increase in global and national trade, and its transportation of natural goods, provides for increased possibilities for IAS to be accidentally transported from their area of occurrence. Ports are one of the gateways for IAS to enter into China. This fact is well recognized, and inspection and quarantine are indispensable safeguard against the unintended IAS diffusion, resulting from shipments passing through the ports.

- The variety of pests intercepted at the national ports and border posts is constantly on the rise, with 229,000 interceptions in 2008 and 579,000 in 2012 representing an annual increase of over 30 %. In the grain trade alone, inspection in China’s ports intercepted 72,160 batches containing a total of 1060 species/genus originating from 54 countries of which 66.64 % of the IAS identified were non-native plants.

- In-spite of that there is a well-established control system in place at the national ports, it is not a question of if, but rather when, samples of the various IAS will unintentionally exit the ports’ areas. This can be seen, although indirectly, by that the first detection of new IAS has primarily been in the southern and central coastal regions. And while now there is also a rapid inland spread of plant IAS to China’s central and northern provinces, IAS are mostly concentrated in the provinces along the country’s coastline, which coincidently also harbors many of the world’s largest seaports.

- Increases in local IAS populations: Long-distance spread of IAS mainly rely on a human intermediary, where transport plays and important role. The interchanging of agriculture, horticulture and forest products between, and within, countries are a main accelerator for IAS long-range disbursement. The long-range disbursement facilitates an increase in establishments in local IAS populations from which the IAS can spread, thus creating the opportunities for an accelerated secondary spread. How fast such secondary local populations will spread will depend on a different sub-set of factors, for example the specie’s mobility or seed dispersal potential. Wind and flowing water are both factors which can increase the spreading of IAS, as are the cases of both mile-a-minute and alligator weed. In addition, seeds from mile a minute are also dispersed by animals and birds, thus providing for a range of dispersal vectors. Other species like alligator weed produces seeds, but mainly propagate through vegetative means, and even small fragments of alligator weed can easily regrow, making mechanical management of the specie very complicated.

- As humans are an intermediary in the primary spread of IAS, they are also a factor in the secondary disbursement and can inadvertently be the reason for a specie re-introduction in areas where the specie locally has been removed or eradicated. For instance, seeds of crofton weed (Ageratina adenophora) can, often in mud, attach to farmers clothes and shoes as well as farm machinery, in this way, be transported back into an area. Humans can thus act as a vector, also for other species such as mile-a-minute and alligator weed. Thus, without the proper knowledge of the IAS and their biology, farmers might be less effective in their control and management of species.

- Project conceptual model: The diversity of direct and indirect factors hindering an effective intervention towards IAS, which are threatening agrobiodiversity, including traditional varieties and GRFA in China, are shown in Figure 1. This indicates the relationships between direct threats and various underlying factors (or root causes), and the points of intervention where project strategies (yellow boxes) will contribute towards a reduction in the level of threats, and therefore contribute towards the long-term vision of the project, namely to strengthen the protection of agrobiodiversity, by reducing threats from IAS through improved management systems and strengthened coordination and cooperation for the on-the-ground prevention, control and management of priority IAS in the agroecosystems. The outputs and outcomes of these strategies are summarized in the Theory of Change diagram in the strategy section of this document (Figure 2).

Baseline projects and resources that will be committed from them:

- This section provides a synthesis of baseline projects and related resources supporting the implementation of the GEF project. Tables 3, 4, 5 and 6 provide a summary of the baseline and GEF Alternative for the outputs in each project component. For further information, see the situation analysis in Annex L, the landscape and site profiles in Annex Q, as well as the socio-economic survey Annex K and gender analysis Annex F.

- The State Council has assigned the organization and coordination of the national IAS prevention, control and management (hereafter also referred to as IAS Management) to the Ministry of Agriculture and Rural Affairs (MARA). The Office of Management of IAS under the ministry ensures IAS coordination within MARA and the ministry is supported technically by the MARA Research Center for IAS Prevention and Control. In 2012, the Rural Energy and Environment Agency was established to improve the national capacity in IAS warning and monitoring, by running a national, provincial, prefectural and county level monitoring and warning network for IAS. It has established 276 ground-level stations and 1572 county environmental stations in 34 provinces (autonomous regions and municipalities). During the period 2016-2020 MARA will invest around 1.8 million USD annually into early warning and monitoring of IAS. Furthermore, the ministry has established sub-stations across China in different regions for environmental control.

- China has an ongoing emergency response program for outbreaks of IAS and major pests. In addition to the “First Priority” IAS species list (52 species), MARA has prepared 23 sectoral standards for the prevention, control and management of IAS, such as mile-a-minute and golden apple snail. MARA has also over 40 technical guidelines for IAS emergency response. China has issued 52 technical guidelines for monitoring, preventing, controlling and managing different IAS.

- The Ministry of Ecology and Environment (MEE) is involved in IAS management within protected areas, including key ecological functioning zones and in 2013 the ministry established a National Biosafety Management Office. MEE has investigated 35 IAS known to have a significant negative effect on biodiversity, and has developed and demonstrated prevention, control and management techniques in national protected areas and other conservation areas. In 2003, 2004, 2014 and 2016 MEE released IAS lists covering a total of 71 species found in China. The annual investment into IAS-related matters by MEE is around 5 million USD.

- The prevention, control and management of IAS at China’s border fall under the General Administration of Customs (GACC). GACC which plays a key role in the interception of IAS at China’s borders, has 35 Inspection and Quarantine Bureaus that conduct inspections and quarantine of IAS at more than 400 ports nationwide. In addition to carrying out inspection and quarantine for general cargo, the port inspection and quarantine departments undertake inspection of passengers and mail, focusing on high risk items, such as seedlings and plants and animals. Regulations, such as the “regulation for inspection and quarantine of aquatic animals” and “regulation for quarantine of plant propagation materials” guides the IAS supervision at ports.

- Although there has been a decrease in the number of ministries following the ministerial re-shuffling of the Chinese Government initiated in March 2018, the responsibilities for IAS prevention, control and management has generally not changed. Because of this, the changes in government structures will, at least in the short term, not have an impact on the management and coordination of the IAS work in China as most of the agencies and departments maintain their responsibilities, even though they have been reallocated. A good example of this is China’s Inspection and Quarantine Agency, which was moved to the General Administration of Customs.

- There are a number of scientific and research institutions, which play an important role in supporting the respective ministries in undertaking needed scientific research related to the various IAS problematics. These institutions include the Chinese Academy of Sciences (CAS) and the Chinese Academy of Agricultural Sciences (CAAS). CAAS, which is affiliated with MARA, undertakes agricultural research and oversees many different projects. Chinese Academy of Inspection and Quarantine (CAIQ) undertake/s, among other, risk assessments on IAS for GACC. MEE works, for instance, with the Chinese Research Academy of Environmental Sciences (CRAES) and the Nanjing Institute of Environmental Sciences and the Chinese Academy of Inspection and Quarantine (CAIQ).

- Each provincial government in turn works with the academic institutions subordinates in the different provinces to focus on applied research tailored to the agroecological challenges for the provinces, for instance to investigate and monitor IAS within the agroecosystem, including national natural reserves and key ecological functioning zones.

- 18 provinces (autonomous regions and province-level municipalities) have established IAS Management Office or a mechanism of joint conference (of relevant departments). Furthermore, 40% of the counties in China, including in Hainan and Chongqing, have designated IAS management agencies or established coordinating bodies supporting local implementation of national laws, regulations and policies.

- The database of IAS in China provides comprehensive information on 114 Invasive Alien Insect Pests (IAIP) and supports remote information retrieval and exchange. A new system for quantitative risk assessment of introduction, adaptation, spread and outbreak of IAS has been established. The system integrates computer simulation, modeling software and various GIS-based tools. Based on the system, the potential range of 52 IAIP has been predicted and has led to the development of control plans and management measures for 30 high-risk species.

- PCR (polymerase chain reaction) based, rapid detection techniques and identification kits have been developed for more than 70 IAS are now available and used in China, including at entry/exit ports. Rapid molecular detection techniques and DNA barcoding for nearly 200 insects in China have also been developed.

- Field monitoring systems, which, depending on the biology of the target insect, rely on, among other, real-time data collection, rapid molecular detecting, chemical pheromone monitoring, remote data transferring and ground penetrating radar have been established nationwide for more than 80 insect IAS, including red imported fire ant, rice water weevil and codling moth Cydia pomonella.

- Chemical, biological and alternative control technologies for IAS have been developed and demonstrated, including the development of efficient spraying techniques like low-volume spraying.

- China has a longer tradition with using natural enemies to IAS, which dates back to the 1950s. Today more than 40 species have been introduced to combat IAS. For instance, both adults’ and larvae of Agasicles hygrophilia feed on alligator weed A. philoxeroides thereby substantially suppressing its growth in the release areas. China is looking at, and implementing, ways to mass rear and release A. hygrophilia, as well as how to simplify the rearing steps and improve releasing methodologies to ensure a sustainable post-release beetle population, while reducing the economic cost of the control efforts. Trials in Hunan, Guangxi, Jiangxi and Guangdong have used Epiblema strenuana and Ophraella communa for controlling the common ragweed A. artemisiifolia, to reduce the ragweed’s growth by entering into the stem as well as feeding on the leaves. However, large scale release of these biological agents has still not been undertaken.

- Neochetina eichhornia and Neochetina bruchi have been tested in Ningbo and Wenzhou in Zhejiang, as a biological agent for controlling water hyacinth with comparatively good results. However, the over-wintering survival rate of the weevils is very low, minimizing the possibilities for establishing a viable population in the years following release.  Natural enemies Tetrastichus brontispae and Asecodes hisponarum, are used to control Brontispa longissimi and have shown to have a suppressing rate higher than 85%. Biological agent factories have been established in Hainan, which have a daily production of 2 million parasitoids that are used to control Brontispa longissimi in an area exceeding 100,000 ha.

- China has worked on IAS vegetation replacement technologies using native plants to outcompete invasive species in a given area. A specific focus in China has been on the common ragweed A. artemisiifolia and crofton weed A. adenophora where native plants including indigobush Amorpha fruticose and common sea-buckthorn Hippophae rhamnoides have proven successful in effectively replacing the weeds. Over 40 native species have shown promise for outcompeting and repressing A. adenophora, including the tree species Chinese red pine Pinus massoniana. In addition, damages due to the codling moth Cydia pomonella have been reduced to less than 3% in the Gansu and Xinjiang provinces using sex-pheromone based mating disruption.

Barriers

- Although the government has made significant efforts to reduce the threats of IAS to agrobiodiversity its efforts have been impeded by a number of barriers.

Barrier 1: Incomprehensive policy, legal and management frameworks and lack of sector and national, provincial and county level integration.

- Fragmented legislation on IAS prevention and management. Although China has a large body of laws regulating the IAS Management, such as the agriculture law, fisheries law, forest law, and environment protection law, legal gaps and deficiencies exist, stemming from the narrow sectoral focus of each provision. Thus, the legislation and the affiliated rules, regulations and administrative supervision related to IAS Management is fragmented, with narrow focus and limited scope. The situation is further aggravated by the fact, that there is no commonly agreed concept of invasive alien species, and because of this existing laws and regulations lack explicit provisions on IAS, furthermore IAS are often “hidden” under broader terms like pests, weeds and diseases. There is therefore a need for an overarching strategic approach to guide the revision of the existing and future legal and regulatory frameworks.

- Insufficient institutional coherence and cross-sector coordination at national, provincial and local levels. Despite efforts to streamline China’s IAS related institutional framework, it remains intricate and insufficiently coordinated. Limited inter institutional and intra sectoral cooperation and coordination are among the main identified bottlenecks to a coherent institutional approach to IAS management. Nationally, MARA are overall responsible for the prevention and control of IAS, MEE oversees biodiversity conservation, including the supervision of IAS of protected areas, the State Forestry and Grassland Administration (SFGA) is in charge for forests and grasslands, including management of IAS in these areas, and GACC is responsible for preventing and regulating the entry of IAS into China. Within each ministry and administration, there is a subset of offices and departments working on different aspects of IAS Management, which collaborate with each other through the ministries own internal coordination mechanisms. However, at present there is no consolidated cooperation network between the various ministries/administrations. And while a National Collaborative Committee on Prevention and Control of IAS exists, it meets too infrequently to be an effective coordination body for the ongoing cooperation. Furthermore, there is not a smooth alignment between the mandate of the sectoral ministries, leaving certain areas in a grey zone, where it is either unclear who has the mandate, or where there is an overlap in mandates. Both cases result in a lack of clarity on the division of responsibilities. Also, many government institutions have similar functions, within their respective sector, for instance local forestry departments and agricultural departments both work on IAS Management, but are responsible for its implementation in separate areas in the physical landscape. Such diffused, and at times overlapping, roles and responsibilities among the institutions often hampers effective IAS Management responses, particularly at local level where the on the ground implementation occurs. Following the restructuring of the Chinese Government announced in March 2018, IAS management has been consolidated into fewer ministries. Despite this, the departmental and institutional setup has not markedly changed, leaving previous overlaps, fragmentations, duplications, gaps in the overall prevention, control and management responsibilities unaddressed. There is therefore a need for establishing a functional IAS management and coordinating mechanism with multi-sector participation to ensure a holistic institutional response to IAS Management. This need is also apparent at the provincial and local levels where Invasive Alien Species Management Offices have only been created in 18 of China’s provinces, despite MARA’s intend to have a full national coverage. The limited roll-out is in part because, the establishment of these management offices depends on provincial leaders’ discretion, and often hinges on said leaders understanding of the negative impact of IAS and general ecological conservation awareness.

- For supporting baseline information for Barrier 1, please do also see Table 3 and Annex L

Barrier 2: Lack of institutional capacity.

- Limited inspection and supervision capacity. There are inadequate inspections and supervision capacity overseeing the entry and exit pathways for IAS, at China’s borders and in-between China’s provinces. The ports process significant volumes of agricultural and forest products, which hold the intrinsic risk of harboring IAS that can threaten China’s agroecosystems. The lack of professionally trained staff with knowledge and expertise in how to effectively minimize/halt the spread of IAS, hinders the necessary strict control and management of these priority pathways. And although acknowledged, there are limited training plans in place, and staff trainings are infrequent and non-systematic, as well as missing to encompass individual positions or different management levels. With the increase in cross-border transfer of exotic species and internationally-imported varieties, the IAS inspection modes and monitoring systems are being challenged, and with the emergence of e-commerce, there is an increased need to adapt. Technological limitations include, a lack of efficient large-scale monitoring and remote sensing techniques for IAS risk assessment and detection.

- Insufficient know how and knowledge management capacity. China has an established organizational structure for IAS Management and has trained a large number of professional and technical staff, as part of their governmental programs. However, the people trained are to some extent localized and associated with geographical areas covered, by said programs. Because of this, and due to China’s size, there is still a knowledge deficit in the areas, which have not been involved in larger provincial or national interventions. As a result, there are still within many departments relatively weak basic understanding and capabilities for adequate ISA Management, lack of sufficient facilities and equipment, unavailability of education and the skills to provide trainings. Thus, there is a persistent need to build local capacities to ensure appropriate IAS Management long-term.

- Poor integration of IAS concerns in local planning and funding. As IAS are still not a mainstreamed concern, they are seldom part of the integrated planning processes, and thus funding for IAS is not part of the governmental budgets, as a matter of course. Because of this, interventions focusing on building local capacity for IAS Management is most often undertaken in areas with acute situations, or where the IAS populations have become sufficiently large to seriously affect the productive sectors. Thus, there is a need to raise the awareness of the threats of IAS to the environment and the economy, and through that to ensure that IAS Management becomes a regular featured budget item.

- In effective use of Government staff working on the ground. The lack of mainstreaming provides for missed opportunities. For instance, when local extension services or other relevant departments/offices do not look for IAS, while in the field providing services to farmers, opportunities are being missed for an adequate early response. Thus, the possibility for recognizing and recording IAS before they become a major concern of the farmers or the respective government have been forfeited. However, to fully benefit from such an approach extension service workers and others need to be capacitated.

- For supporting baseline information for Barrier 2, please do also see Table 4 and Annex E, Annex L and Annex P.

Barrier 3: Lack of effective approaches for controlling IAS impacts on agrobiodiversity.

- Insufficient knowledge management and replication of effective approaches for IAS Management. In its IAS Management programs, China has effectively upscaled biological, ecological, manual and chemical approaches, in a substantial number of IAS affected areas throughout China. However, dissemination of these techniques to non-program areas are slow. One reason for this is, that trainings are developed and provided to, for instance, farmers within the program areas, but these trainings are not, as a matter of course, made available via websites, making it difficult for other interested parties to train themselves or as a minimum become aware of that such techniques and methodologies exist.

- Untapped research and development potential. In addition, and in spite of the many advances in China's research on IAS Management technologies, there is a need for further research demonstrations as current successes only covers a small proportion of IAS found in China, and approaches working in one region might not work in another. Thus, there is the need for field testing solution models in different habitats and under different climate conditions, to develop cost-efficient, practical and implementable technologies needed to propel on-the-ground IAS Management in China forward.

- It should be noted that parts of the barriers and underlying causes mentioned elsewhere in this section also are also contributing to barrier 3 but has not been restated here. For supporting baseline information for Barrier 3, please do also see Table 5 and Annex E and Annex L

Barrier 4: Weak public and institution awareness of IAS’ threats to biodiversity and the positive impacts of IAS Management.

- Nominal awareness within provincial and local governments of the economic and ecological impact of IAS on agrobiodiversity. In conjunction with the lack of capacity among government officials there is a lack of awareness within provincial and county government departments IAS’ negative impacts on economy and the ecology. Without such understanding the influence from IAS could easily be underestimated and result in inaction or in insufficient interventions. In this connection, economic reasoning is seldom used and if it is, most often it is in response to an already occurring large economic loss from damages and/or decrease in production.

- Limited outreach of IAS concerns among the grassroots stakeholders and general public. Farming communities, and the general public, are not currently involved in supporting agricultural and environmental agencies in the prevention, control and management of IAS impacting significant agrobiodiversity, including traditional varieties, across the agricultural landscapes. This is in part due to the low stakeholder awareness of the intrinsic value and long-term economic benefits to the community by addressing IAS infestations beyond the productive farming areas. Part of this is related to the limited knowledge of how the farmers can benefit, including how to generate adequate revenue from local agricultural varieties, some of which have been shown to be effective in IAS Management.

- Limited capacity for IAS Management awareness raising and training among the farming communities. Although farmers within the government project/programs demonstration areas have received training, the remaining farming communities in China have, generally speaking, limited knowledge of IAS and their impacts outside their own villages. Farmers are therefore ill equipped to engage in up to date and effective approaches for “on the ground” interventions. Because of this, farmers often opt for an indiscriminate use of chemicals to combat an IAS infestation, with little regard to the environmental impact of the treatment. As farmers, in broad terms, see the IAS as just a different pest/weed, they do not seek to identify the IAS, nor request assistance for better control and management techniques for the specie/s in question, something which is important particularly in the early stages of the infestation. Also, as the aggressiveness of many IAS is not fully recognized, farmers tend to only deal with the IAS, which have entered their fields and would leave IAS in the land surrounding the field, leaving the IAS free to spread unattended in the areas, which are considered public.

- Public lack of awareness. The overall awareness on IAS prevention, control and management is low and while IAS are recognized as being a problem, which have impact on the farmers’ fields and crops, they are generally viewed, and managed, as any other pest and weed, usually through broad allocation of chemicals. The awareness on IAS among the general public is also very low, and this lack of public awareness is becoming an increasing problem within China, as the public plays an increasing role in the release of IAS. According to preliminary statistics, there are more than 1000 random releases of IAS in China every year. In one incident approximately 100 bullfrogs, which are native to North America, were released to the wetland in the Beijing Olympic Forest Park.  For supporting baseline information for Barrier 4, please do also see Table 6 and Annex L

National policy alignment:

- The project will assist the Government of China in implementing its obligations under the Convention on Biological Diversity, in particular Aichi Targets 7 and 9 (see below). In 2020, China will host the 15th Conference of the Contracting Parties to the Convention of Biological Diversity, providing an important opportunity for the Government to showcase progress towards its advancements in its protection of globally important biodiversity, including traditional varieties and GRFA, as well as to contribute to the development and launch of the next Aichi Biodiversity Targets. The project will contribute to this by hosting a full-day IAS Management side event.

- The Objective and Outcomes of the project are fully in line with national priorities and plans for biodiversity conservation and IAS Management in China. The project will address key priorities under the National Biodiversity Conservation Strategy and Action Plan (NBSAP 2011-2030) by supporting the implementation of its priority area 7 (to strengthen biosafety management of IAS and genetically modified organisms) by 1) strengthen government cross-sector coordination and collaboration in IAS Management; 2) improve related regulations, guidelines and methodologies enhancing the management of IAS and reducing the threats from these to agrobiodiversity; 3) building the capacity for IAS Management of relevant Government staff at national, provincial and county levels, as well as local stakeholders including farmers; 4) improve IAS related knowledge management 5) raise public awareness and strengthen international cooperation and exchange and 6) development and demonstration of IAS integrated prevention, control and management technologies.

- The project will address key priorities under the National Agricultural Sustainable Development Plan (2015-2030) by supporting the implementation focusing on restoring agricultural ecology and its improving ecological functions. In this regard, the project will support the plan calls for strengthening the protection of agricultural wild plant resources and strictly prevent invasion of alien species through the utilization of demonstration bases, risk analysis, and IAS Management planning.

- The project is also in line with the Chongqing Biodiversity Strategy and Action Plan (BSAP), which was developed under the UNDP implemented EU China Biodiversity Program (ECBP). The Chongqing BSAP (2010), includes IAS in the plan’s fifth objective which is supported by a specific action program (number 5) aimed at prevention and management of IAS. The Hainan Biodiversity Conservation Strategy and Action Plan (2014-2030), with initial support from ECBP, has also an IAS focus via its Priority Area 4. As with the Chongqing BSAP the BSAP in Hainan seek to improve its regulatory framework and expand its capacity for prevention and management of IAS.

- Furthermore, the 13th five- year plans for agriculture and environment has a focus on IAS Management and both have specific priority projects related to prevention, control and management of IAS. Similar focuses can for instance also be found in the provincial 13th agricultural plans.

- SDGs and Aichi Targets: This project will primarily contribute towards the 15th Sustainable Development Goal (Life on land): Sustainably manage forests, combat desertification, halt and reverse land degradation, halt biodiversity loss, supporting activities that address multiple targets. Most notably it supports target 15.8 to reduce the impacts of IAS on land and water ecosystems and target 15.5 to stem the rate of biodiversity loss, but also target 2.4 to ensure sustainable and resilient food production systems and target 2.5 to maintain the genetic diversity of seeds, cultivated plants and farmed and domesticated animals and their related wild species. The project will contribute towards Strategic Goal B and C of the Aichi Targets (to Reduce the direct pressures on biodiversity and promote sustainable use and to improve the status of biodiversity by safeguarding ecosystems, species and genetic diversity respectively),  primarily target 7, to managed sustainably and conserve biodiversity in agriculture, aquaculture and forestry; target 9 to control IAS and their pathways and target 13 to maintain genetic diversity of cultivated plants, domesticated animals and wild relatives.

Figure 1. Conceptual Model for the Project

# Strategy

- The Project Objective is to strengthen intersectoral coordination mechanisms, approaches and technical capacity for more effective prevention, control and management of IAS threats to agrobiodiversity in China. To achieve this objective, the project will deploy four strategies (Project Components) with intervention pathways described in the theory of change diagram in Figure 2 below. The baseline situation, incremental reasoning and global environmental benefits are summarized in Tables 3, 4, 5 and 6 in the Results Section. The Project Components (as the GEF Project Alternative) aim to remove the barriers to achieving the long-term solution (see Figure 1, Section II Development Challenge), namely: to strengthen the protection of agrobiodiversity, by reducing threats from IAS through improved management systems and strengthened coordination and cooperation for the on-the-ground prevention, control and management of priority IAS in the agroecosystems. The proposed Components are described below.

- Component 1: Strengthened the Enabling Environment. The component will strengthen the cross-sector coordination and collaboration for managing and implementing the prevention, control and management of IAS by establishing and running functional Coordinating Groups at national, provincial and county levels. The component will address the need for revising relevant IAS regulations and revisions of the IAS Rapid Response Guideline, an IAS Early Warning Guideline will be undertaken. In addition, an IAS Biodiversity Risk Assessment Guideline will be developed. The IAS Biodiversity Risk Assessment Guideline will provide the, not currently available, input into the “First Priority” IAS species list and National Quarantine Pest list updating. The component will strengthen China’s work in reducing threats from IAS to protected areas and other conservation areas by developing IAS buffer zones guidelines, providing additional safeguards against the encroachment of IAS, as well as develop protected area specific IAS Risk Assessment, IAS Early Warning and Rapid Response guidelines, thereby increasing the efforts to safeguard national and globally important biodiversity. National and provincial IAS Management will be strengthened through the development and implementation of IAS Management Strategy and Action Plans (IAS NSAP and IAS PSAPs). These plans are expected to, among other, focus on strengthened cross-sector collaboration, expansion/improvement of the monitoring stations network and monitoring methodologies, improved capabilities for data analysis and data management, which all will be aimed at reducing the threat from IAS to agrobiodiversity including traditional varieties and GRFA occurring within the border agroecosystems. The plans will also include sections on financing, south/south and north/south cooperation and expanded public engagement and citizens science. The overall approach taken by the project, which is to be reflected in the  IAS NSAP and IAS PSAPs, will provide for national and Global Environment Benefits (GEB) by targeting IAS Management in the broader production landscapes, which contains pockets of traditional varieties, endemic species and protected species within said landscapes, thereby providing IAS Management solutions from an integrated landscape perspective. The IAS NSAP and IAS PSAPs will be translated into sectoral/ministerial Implementation Plans, which combined will provide for an embedded holistic approach for IAS Management, and the individual implementation plans will form part of the ministerial 14th and 15th five-year planning process. Under component 1, the project supports the Chinese Government in establishing the underlying regulatory and strategic framework needed to enable China to more holistically address current and future threats posed by IAS and ensure that IAS Management is optimized, providing for long-term national and global environmental benefits.

- Component 2: Comprehensive IAS management frameworks and strengthened institutional capacity. Based on the project developed guidelines (component 1), practical and user-friendly Biodiversity IAS Risk Assessment, IAS Early Warning and IAS Rapid Response methodologies will be formulated and tested (in Hainan). These will be important practical tools to be used by relevant staff working on the prevention, control and management of IAS, and training will be provided to support this. Thus, capacity for an effective and up to date IAS Management will be directly enhanced. Further under this component consolidated training packages will be prepared and implemented to strengthen the capacity of government staff at national, but particularly at provincial and county level. The component will facilitate best practice sharing and specialized technical trainings on a number of priority subjects, including ecological and economic impact of IAS, IAS risk assessment and early detection and response. As a priority the trainings will be targeted to staff in relevant agencies and departments and will aim to capacitate them to carry out IAS Management related work. Thus, the outcome of these activities will result in a strengthened administrative and technical capacity in IAS management, which will focus on the productive sector, at large, and on localized areas, within the agricultural landscape, where traditional varieties and GRFA are grown, thereby providing GEBs. Finally, to increase the local capacity for on-the-ground identification and monitoring of IAS, an IAS application (APP) will be developed and used by the public, including farmers and Government staff, alike.

- Component 3: Demonstration of IAS threat reduction in agroecosystems. An integral part of the project is the application of measures and approaches in the targeted project agricultural landscapes, showcasing applicable measures for IAS prevention, control and management at community level in Hulu, Wenchang city, Hainan and Longfei, Bishan district, Chongqing. This will be achieved through the targeted capacity building of individual farmers, cooperatives, agricultural enterprises and other relevant stakeholders. Site specific applicable IAS Management techniques will be provided, thereby empowering stakeholders to apply effective techniques for reducing IAS encroachment within their fields and the surrounding public village areas. The expected overarching outcome will result in reduced IAS threats to agrobiodiversity, including traditional varieties in the agricultural landscape around Hulu and Longfei. A key part of the component will be the formulation of comprehensive IAS management plans, undertaken with the active participation of local authorities, farmers and other relevant stakeholders. For that purpose, IAS distribution surveys and IAS impact assessment reports will be developed. To obtain up to date information and evaluate the impact on agrobiodiversity of the main IAS found in Wenchang city and Bishan district, the component will make use of readily available, user-friendly technologies and applications to collect information, including the project developed IAS APP (component2). These will be used in conjunction with a citizen’s driven monitoring approach involving local farmers, CSOs and the public at large, to create a GIS based information layer, which can be overlaid with information collected from available sources such as the existing monitoring system. This public participation process will be documented. The project approach considers that productive landscapes in China are often a mosaic of small land plots on which different crops are grown, including traditional varieties, which makes interventions targeted on individual subsections of these small plots unfeasible, as IAS reintroduction from the surrounding areas are unavoidable unless IAS is actively managed in these surrounding areas as well. Therefore, the plans developed by the project, will be holistic, treating the targeted agricultural landscape as a single combined unit, where, to reduce the risk of IAS re-establishment within the area, IAS control and management will be provided in equal measures to the productive areas, fallow lands and public/common areas alike. The outcome of the component will translate not only into comprehensive local IAS management action plans for Wenchang City and Bishan District, but IAS distribution surveys and IAS impact assessments will also ensure sustainable incorporation of enhanced IAS knowledge in the local planning and implementation of science-based technics for IAS Management.

- Component 4: Awareness raising, knowledge management and coordination. The efforts under this component will focus on raising awareness of IAS, as a threat to agrobiodiversity and equally important, of the know-how to effectively manage them. IAS awareness will be raised through prepared materials and public events. IAS knowledge will also be shared through developed educational materials, school curriculums and Massive Open Online Courses (MOOC), which will be publicly accessible through the developed IAS Knowledge Management platform. Thus, creating a long-lasting and extensive contribution to the IAS prevention, control and management education and awareness in China. In addition to the outreach to the public at large, dissemination of knowledge materials and trainings to the other child-projects under the C-SAP Program is also envisaged. The development of the IAS Knowledge Management platform will act as a clearing-house mechanism for IAS related knowledge, and is expected, through the project’s interventions, to provide for an accelerated knowledge uptake, and use, among practitioners, farmers and other stakeholder groups, providing for not only national, but also global, benefits. The project will facilitate an agreement between main government institutions, academic institutions, public organizations and other stakeholders to contribute documents and information to the platform. The IAS Knowledge Management platform will be linked up to the C-SAP Knowledge Platform developed under the FAO implemented C-SAP 1 child project. Links will also be made the C-PAR Program Biodiversity Knowledge Platform. There is a pronounced international vector to this component. A synthesis of the project’s achievements, particularly in the island of Hainan, could present a useful input to senior government officials from MARA, MEE and GACC for their use in international engagements related to IAS Management. This could further facilitate bringing IAS issues onto the international agenda. Hainan’s lead could also be promoted as an island-based approach for IAS Management, which might be of interest to small island states. The component will also provide support to MARA, MEE and GACC in their efforts to establish, where possible, bilateral cooperation agreements related to the areas identified in the IAS NSAP 2021-2030 directions on improving South-South/North-South cooperation and coordination. Finally, the project will organize a full-day “IAS side event” in connection with the Fifteenth Meeting of the Conference of the Parties to the Convention on Biological Diversity (COP15) in 2020, thereby increasing the attention of IAS problematics in the international arena.

- Indicators and assumptions for the accomplishment of expected Outcomes for the project Components are given in the Project Results Framework, and the assumptions indicated in the Theory of Change diagram (Figure 2) are described below in Table 1. Gender mainstreaming has been integrated throughout the project design based on a gender analysis and gender mainstreaming plan (see Annex F).

- This project is part of the C-SAP Program, under which the Program Coordinating Officer and Program Steering Committee will liaise with the Project Steering Committee and Project Coordinator to ensure that a coordinated approach to knowledge management, sharing of lessons learned, monitoring and evaluation, social and environmental safeguards, gender mainstreaming and risk management takes place across the program.  The project components will contribute towards the C-SAP Program Outcomes as shown in Table 2.

- Innovation: The C-SAP 2 IAS project is part of an innovative program that addresses a broader subset of barriers to effective and comprehensive agrobiodiversity conservation and sustainable agricultural development. The project promotes a paradigm shift towards mainstreaming IAS prevention, control and management into day-to-day farming and environment protection practices. By concentrating the IAS Management efforts in areas with agroecosystems with traditional varieties, including GRFA, the project creates important synergies with protecting traditional varieties, thereby highlighting additional benefits, which, not only can support the in-situ conservation efforts of the C-SAP Program’s other child projects, but also provide important results and lessons for China overall. The project will work together with MARA, MEE and GAAC to establish an effective cooperation mechanism, which will ensure that national, provincial and local level IAS Management efforts will be coordinated between the responsible agencies working with IAS, thus, addressing the IAS problematic in a holistic and cross-sectoral manner. As part of this, synergy-based, multi-sectoral IAS Management approaches will be developed, including early detection and warning, and integrated rapid management responses to emerging IAS threats.

- National Socio-economic Benefits:  Improved protection of the agroecosystem in Hainan and Chongqing will be achieved through the combined effect of project components, which will facilitate a reduction in the IAS threat to agrobiodiversity found in the project targeted agricultural landscapes and beyond. Reducing the negative impact of IAS will have positive ecological and economic consequences, where the latter will have impact on the local farmer communities’ livelihoods, as well as financial implications. While 35.000 ha of farm land will benefit from direct project interventions, areas benefitting from voluntary replication of similar type of IAS Management, facilitated by the project, is expected to be much larger. The project’s work on cross-sector coordination and cooperation, as well as its work on relevant regulations and guidelines, will provide for a more holistic and integrated approach to IAS Management. This will benefit, not only, the sites subject to direct project interventions, but also Hainan and Chongqing more broadly, as well as, through the national engagement of other provinces in China.

- The direct project beneficiaries include national provincial and local government agency staff who improved their knowledge and skills on IAS Management due to the project – at least 12,000 (50% female) will be trained under the project. 6,000 local community members including farmers, farmers cooperatives and agrobusinesses etc. will be capacitated in the use of IAS Management technologies reducing the threat of IAS to agrobiodiversity and traditional varieties.  These activities will mainly be located in the targeted project areas, but where possible trainings will also be conducted in counties participating in the other C-SAP Program child projects. Also, the training materials, training videos and MOOCs will be made available for all interested parties through the publicized project IAS Knowledge Management platform. Indirect beneficiaries will include the wider farming communities of the areas within and adjacent to the project targeted agricultural landscapes, although it is difficult to quantify the nature of the benefits, both ecologically and economically, the impact of the project is expected to be substantial.

Project Scope and targeted agricultural landscapes and intervention sites.

- The project addresses IAS Management at national and provincial levels with a specific focus on Hainan and Chongqing. The focus of the project’s, on the ground, interventions are three selected sites. Two sites are located in the agricultural landscape of Wenchang city (Hainan) and Bishan district (Chongqing) (see Annex Q for landscape related information and for socio-economic information Annex K). Hulu village, which is the main village in the project targeted agricultural landscape in Hainan (Figure 3), is a predominant Han village located 35 kilometers north west of Wenchang city. Hulu village lies in a flat plain area and has approximately 3500 mu of cultivated land, 500 mu of garden plot, 2800 mu of woodland and 250 mu of pasturelands. The village is characterized by individual small holdings, which form a non-uniform patchwork of farming plots scattered in the agricultural landscape. Although some land consolidation has occurred, such consolidation generally does not make up for areas larger than 15-30 mu. Litchi is the main fruit produced in the village, and rice (a hybrid) is grown twice a year (mainly for own consumption). The village also has chickens, ducks, buffalos, pigs (again mainly for own consumption). Within the village area there are also 100-year-old jack fruit trees (Artocarpus heterophyllus), 300 old litchi trees (Litchi chinensis) and Poison Arrow Trees (Antiaris toxicaria), which are more than 400 years old, as well as a wild rice reserve that is located close to the village. The agricultural landscape, in and around Hulu village, is afflicted by the occurrence of IAS including Mikania micrantha, Eichhornia crassipes, Eupatorium odoratum and Pomacea canaliculata. These IAS are impacting agrobiodiversity in the area, including traditional variesties of Litchi chinensis Sonn., Areca catechu L., Oryza sativa L. The invasion of IAS causes a local economic loss (at village level) of about 500,000 RMB each year. Within the 24,000 ha large project target agricultural landscape around Hulu village alligator weed, mile-a-minute and golden apple snail can be found on respectively 3,500 ha, 13,500 ha and 7,500 ha.

Figure 3: Location of the project target agricultural landscapes in Hainan and Chongqing.

- Longfei village, which is the main village in the project targeted agricultural landscape in Chongqing (Figure 3), is a predominant ethnic minority village located in the Meijiang Mountains, 15 kilometers from Bishan town. The landscape in and around the Longfei village consists of an undulating topography. The village has approximately 3,000 mu of cultivated land, 1,200 mu of garden plots, 1,000 mu of orchards and 5,600 mu of woodland equating to an approximate household land area of 4.3 mu. Thus, as is the case in Hulu village, the agricultural area in Longfei village is characterized by small holdings with some consolidated lands with uniform crops. The main agricultural products are corn, vegetables, various fruits, table grapes and citrus and the traditional crop wild rice stem (Zizania aquatica). The agricultural industry in project targeted agricultural landscape, as well as in Bishan district in general, is affected by IAS, such as Alternanthera philoxeroides, water hyacinth (Eichhornia crassipes), Ampullaria gigas spix and P. canaliculata, etc. which are widespread and is considered a serious problem. Aside from impacting on agrobiodiversity, in the project targeted agricultural landscape, they are also impacting local traditional varieties such as Zizania latifolia, and Panulirus stimpsoni. The economic losses (at village level) caused by IAS in the Longfei area amounts approximately 540,000 RMB per year. Within the 11,000 ha large project target agricultural landscape around Hulu village alligator weed and golden apple snail can be found on respectively 5,000 and 1,000 ha.

- The third site, Yangpu Port, is situated on the Yangpu peninsula in Hainan (See Annex P for site profile). It is a national first-class deep-water open port, which serves as an exit port for the industrial corridors in the northwest of Hainan. In the past two years the port accounted for 65% of all entry and exit ships in Hainan. Yangpu Port has been a designated port for grain imports since 2015 and the port has the qualification for importing plants and plant products that meet the Governmental entry conditions standards, except seedlings, fruits, and Buddhist pine (Podocarpus macrophyllus). Between 2015-2017 the port mainly received wood for paper (chip and pulp) from Vietnam, Indonesia, Brazil and Chile and in 2017 the port was approved to receive stripped wooden logs. At the port, specific health, plant and animal inspection and quarantine procedures are followed, and on-site quarantine and treatment are undertaken. In cases where there is no effective treatment method on site, the goods are be destroyed or returned. The port has a remote identification system that is mainly used by staff at the customs services department. The port has various quarantine facilities including a fumigation station for small scale cargo. However, at present it does not have the facility to treat infested logs. Currently if IAS are identified in debarked logs, the log treatment is outsourced to a third-party company, which is entrusted to remove the pest. There are currently 3 test companies in Hainan and at present, 11 persons in the quarantine treatment enterprises at Yangpu Port have obtained the qualification for customs registration.

Figure 2. Theory of Change Diagram for the Project

Table 1. Assumptions for Theory of Change Diagram

| Symbol in Fig. | Assumption | Notes and References |
| --- | --- | --- |
| 1 | There is political support for the strengthening the legal and institutional framework for the prevention, control and management of IAS and for mainstreaming these into provincial planning and management processes. | The Chinese government is placing a strong emphasis on preventing, controlling and managing IAS, which is emphasized by the inclusion of IAS in a large subset of national legislations, and underlying regulatory framework. The government’s commitment towards combatting IAS is also expressed in the National Biodiversity Strategy Action Plan (2011-2030) where IAS Management is part of the strategic priorities and supported by specific actions. The China’s National Plan for Sustainable Development of Agriculture (2015-2030) re-emphasizes the government focus on IAS in that this plan also specifically mentioned IAS backed by a set of actions. China also has substantial annual investments into IAS prevention, control and management, as part of their many programs, which also vouch for the political commitment. In addition, Ministry of Finance with its endorsement of the current project underscores that addressing the threats that IAS poses towards the ecology and economy is a national priority and the commitment, including co-financing, towards this project from MARA, MEE and GACC also testifies to a political will within these ministries/administrations. |
| 2 | The developed capacities of governmental institutions and supporting technologies are sufficient to create a viable and effective change in the national, provincial and local prevention, control and management of IAS. | In line with the above, there is an increasing realization among the project partners that to have an effective and cost-effective IAS Management implementation there is a need for cross-sector coordination and collaboration. To support this, a baring element of the current project is to ensure such coordinating bodies are established and maintained. Through the work (and through that the building of capacity) of the coordinating bodies, IAS Management efforts at national, provincial and county levels towards more holistic responses to IAS infestations will be ensured. Also, China has a long-standing experience in IAS Management gained through the implementation of its different IAS Management programs. Through these programs, a large body of capacity building experience has been accumulated from, which the current project will benefit. This will be further enhanced by the project’s own engagement towards the development of guidelines and methodologies and building capacity of government staff to use them. |
| 3 | The increased capacities of local extension services and local stakeholders, including farmers, improves the prevention, control and management of IAS and reduces the threat to local endemic species, traditional varieties and GRFA. | The results of China’s research efforts, field testing and program implementation has generated a sizeable catalog of interventions to be used in IAS prevention, control and management including the use of biological agents and vegetation replacement techniques. China has also had some success in using low chemical spraying techniques. The project will benefit from these, in that suitable techniques will be tested and implemented in the project targeted agricultural landscapes. In Wenchang and Bishan these approaches will be innovative, and they will serve as learning centers for the farmers and government staff in the surrounding counties. The lessons learned including the feedback on technology usage will be channeled back into the collective knowledge base and will be used in other areas in China with similar climate and ecological conditions. |
| 4 | The raised awareness and increased knowledge management expand political understanding and actions supporting IAS prevention, control and management within and outside the country. | The importance of actively addressing IAS Management is recognized by the government of China and can as mentioned be seen in for instance, the National Biodiversity Strategy Action Plan and other planning document. The requested establishment of the national and provincial IAS coordinating groups (to be established under the project) provides for an additional verification. In turn, these committees will create a stronger combined voice that can better influence and inform about the need to include IAS Management issues/concerns into other areas which, off glance, do not have any relation to this, such as construction and poverty alleviation. The project analysis of the negative impacts of IAS on ecology and economy in Wenchang and Bishan, will become important case-studies, which MARA, MEE and GACC can use, through the project and individually, to table discussions and bring IAS Management into the mainstream. Hosting a full-day side event on IAS Management will be a key part of bringing the issues surrounding IAS to senior leaders’ attention, which will be important to bring it more center stage on the national and international agenda. |

Table 2. Contribution of the IAS Project (C-SAP 2) to the C-SAP Program-level results

| C-SAP Program Components and related C-SAP2 Components and Outcomes | C-SAP Program Outcomes/Indicators | C-SAP2 Project contributions to C-SAP program level results |
| --- | --- | --- |
| Objective: Support the implementation of the Sustainable Development Goals and China’s National Plan for Sustainable Development of Agriculture (2015-2030) by a) piloting and scaling up effective policy and investment measures to mainstream in-situ conservation and sustainable use of globally important genetic resources for food and agriculture (GRFA), b) improving the prevention, control and management of invasive alien species (IAS), c) conserving and enhancing carbon stock and promoting evidence-based and climate-smart conservation of grassland ecosystems, and d) collaborative innovation in climate change and biodiversity from the aspects of policy, mechanism, knowledge sharing and partnerships |  |  |
| C-SAP Component 1: Strengthened enabling environment C-SAP2 Component 1: Strengthened Enabling Environment C-SAP2 OUTCOME 1 Strengthened policy, regulatory and strategic framework for IAS Management incorporated into inter-sectoral response mechanisms for the reduction of IAS threats to agrobiodiversity, including traditional varieties and GRFA. | C-SAP Program Outcome 1.1: Strengthened policy, regulatory and strategic frameworks and cross-sectoral coordination at national and provincial levels | 1 National IAS protection, control and management strategies adopted. 2 Provincial IAS protection, control and management strategies (including sectoral strategies) adopted. 3 new or updated Ministerial regulation proposals ready for inclusion in the legislative process cycle/pipeline. 6 new or updated Provincial Department regulation proposals ready for inclusion in the legislative process cycle/pipeline. (indicator 3) |
|  | 1.2: Strengthened cross-sectoral coordination results in more effective approaches for the conservation and sustainable use of GRFA and grasslands, including for improved control and management of IAS threats | 12 budget supported local IAS coordination bodies or IAS offices in Chongqing that regularly coordinate local inter-sectoral IAS Management, including implementation of the developed strategic action plan. 8 budget supported local IAS coordination bodies or IAS offices in Hainan that regular coordinate local inter-sectoral IAS Management, including implementation of the developed strategic action plan. (Indicator 4) |
|  | 1.3: Increased government financing for in-situ conservation and sustainable use of GRFA and grassland ecosystem, including for the prevention, control and management of IAS threats | An annual operating budget of 14,700,000 RMB provided for IAS prevention, control and management allocated via MARA’s financial department. An annual operating budget of 7,000,000 RMB provided for IAS prevention, control and management allocated via MEE’s financial department. An annual operating budget of 6,000,000 RMB provided for IAS prevention, control and management allocated via GACC’s financial department. Total annual allocation from the three entities 27,700,000 RMB. (indicator 5) |
| C-SAP Component 2: Incentive mechanisms C SAP2 Component 3: Demonstration of IAS threat reduction in agroecosystems C SAP OUTCOME 3 Strengthened IAS threat reduction through collaborative IAS Management by IAS Management agencies, agricultural enterprises and farming communities in Hainan and Chongqing agricultural landscapes | 2.1: Sustainable conservation and management approaches established which improve the in-situ sustainable use and conservation of GRFA and deliver social, financial and livelihood benefits to farmers in parallel | No contributions from the C-SAP2 IAS project. |
|  | 2.2: Effective participatory approaches for the prevention, control and management of IAS impacts on GRFA developed and tested in target agricultural landscapes | APP widely used in and outside project landscapes and APP provide timely information to local governments IAS monitoring systems and is used for decision-making (Indicator 12) |
|  | 2.3: Community-based grassland management approach (including sound biodiversity and IAS management practices) and evidence-based payments for ecosystem services (PES) policy scheme with creditable monitoring, reporting and verification (MRV) system tested in selected provinces and ready for national scale up | No contributions from the C-SAP2 IAS project. |
| C-SAP Component 3: Institutional capacity strengthening S-CAP2 Component 2: Strengthened IAS management frameworks and institutional capacity. C-SAP2 OUTCOME 2 Strengthened institutional capacities and interagency response mechanisms for IAS detection, quarantine, disposal, monitoring, early warning and rapid response. | 3.1: Increased effectiveness of approaches for the conservation and sustainable use of GRFA | The coverage of mile-a-minute, alligator weed and golden apple snail within the Hainan project targeted agricultural landscape has been reduced by 60 %. The coverage of mile-a-minute, alligator weed and golden apple snail within the Hainan project targeted agricultural landscape has been reduced by 60 %. (Indicator 9) |
|  |  | Area coverage of traditional varieties and GRFA (2,600 ha/Hainan & 1800 ha/Chongqing) is unaltered in the project’s 35,000 ha large targeted agricultural landscapes in Hainan and Chongqing. (Indicator 10) |
|  |  | No encroachment of key IAS* within the project targeted agricultural landscapes in Hainan and Chongqing where IAS Management interventions has been implemented to prevent or control mile a minute, golden apple snail or alligator weed. (Indicator 11) * Alligator weed, Golden apple snail, Mile-a-minute, Fragrant Eupatorium Herb, Common Parthenium, White horseweed and Crofton weed. |
|  | 3.2: Strengthened institutional capacity of relevant public sector agencies within target sites, and of lead national institutions, for the in-situ conservation and sustainable use of GRFA, for the management of IAS impacts on agrobiodiversity, and for evidence-based and climate-smart grassland management practices | The Institutional capacities and interagency response mechanisms for IAS protection, control and management including detection, quarantine, disposal, monitoring early warning and rapid response is increased with 33-45 %. (Indicator 6) |
|  |  | Staff capacity at Yangpu port for inspection, detection and species identification, quarantine and destruction of IAS at demonstration port is increased with 33%. (Indicator 7) |
|  |  | 1000 female and 8000 male Government staff have received comprehensive and specialized trainings on IAS prevention, control and management and of these 300 women and 200 men are below 35 years of age (youth) upon certification. (Indicator 8) |
| C-SAP Component 4: Program Coordination, Knowledge Management C-SAP2 Component 4: Awareness raising, knowledge management and coordination C-SAP2 OUTCOME 4 Improved IAS knowledge management systems and awareness heightened, as well as effective program coordination, monitoring and evaluation | 4.1: Improved understanding among decision makers, the general public and key stakeholder groups on the value of GRFA and importance of in-situ conservation, and evidence-based policy making for climate-smart grassland management, and increased access by all groups to information, as indicated by Knowledge, Attitude and Practices surveys to be conducted at beginning, middle and end of projects | The level of knowledge, attitude and practice of public, government, farmers and other key stakeholder groups on the environmental and economic threats posed by IAS, to be determined. (The end-of-project gender disaggregated targets will be determined based on the baseline KAP survey results initiated upon project inception). (Indicator 13) |
|  | 4.2: Monitoring and evaluation demonstrates efficient use of program funds, rationalization of national, provincial and local level inputs, and sharing of information, resources and expertise between projects, along with on-going exchange of lessons and best practices | IAS Knowledge Management platform established in year 1 and has an annual visitation of at least 1000 platform visits per year by the end of the project. (Indicator 14) |
|  | 4.3: Effective coordination of program activities across national and provincial stakeholders and GEF agencies | The Program is effectively coordinated through efficient program steering function and annual program reports indicate clear progress towards outcomes and achievements beyond individual C-SAP child projects. (Indicator 15) |

# Results and Partnerships

Expected Results:

- The Long-Term Impact of the project is improved protection of agrobiodiversity, including traditional varieties and GRFA, against the threats from IAS in China, with a special emphasis on Hainan and Chongqing. This will be achieved through an improvement in the management systems and strengthened capacity for coordination and cooperation for the on the ground prevention, control and management of priority IAS in the agroecosystems. The reduction in the IAS threats to the agroecosystem and its agrobiodiversity, as well as benefits to project stakeholders will be reflected through the Project Objective indicators (see Results Framework for details).

- Global Environmental Benefits: China is one of 15 mega-diverse countries, as well as one of Vavilov’s eight ‘independent centers of crop origin’ and is the place of origin of more than 130 of the world’s crop species.  The C-SAP IAS project will be supporting the GEF core indicator 4.3 in that it will ensure improved IAS prevention, control and management of mile-a-minute, alligator weed and golden apple snail in 35,000 ha of agrobiodiversity landscapes in Hainan and Chongqing. Within in the project areas traditional varieties, such as Litchi chinensis Sonn., Areca catechu L., Oryza sativa L can be found in Wenchang (Hainan) and Zizania latifolia, and Panulirus stimpsoni in Bishan (Chongqing), alongside Chinese herbs and medicinal plants. The C-SAP project will also support the GEF core indicator 11 by providing training to 6,000 female and 6,000 male government staff at national, provincial and local levels, as well as 6,000 farmers with an equal gender representation providing for 18,000 direct beneficiaries.

- The GEF funding requested by the Ministry of Agriculture and Rural Affairs will be used to achieve the project Objective through the achievement of four integrated and complementary Components:

- Component 1: Strengthened enabling environment.

- Component 2: Strengthened IAS management framework and institutional capacity.

- Component 3: Demonstration of IAS threat reduction in agroecosystems.

- Component 4: Awareness raising, knowledge management and coordination.

- To ensure the achievement of the above Components the project will deliver the following key outputs (the project’s products and services):

Component 1: Strengthened enabling environment.

- For additional information for the project baseline related to component 1 please see section II Development Challenge and Annex E, F, K, L, N, O, P, and Q.

Table 3. Summary of baseline and incremental reasoning for Component 1

| Summary of Baseline Situation | Incremental Reasoning |
| --- | --- |
| Component 1: Strengthened enabling environment. |  |
| Output 1.1 Inter-agency coordination mechanisms are established to support IAS strategic plan implementation and improve the management of IAS threats to agrobiodiversity. |  |
| Ministry of Agriculture and Rural Affairs is the appointed lead ministry for IAS Management in China. As part of its coordination and collaboration mandate among the ministries and administrations working on IAS, MARA set up an inter-ministerial coordination mechanism. It has however, only met infrequently, and the coordination efforts has proved insufficient. Ministries and administrations, and their provincial and local equivalents, by and large, work independently on addressing IAS issues within their assigned areas of responsibilities, reducing the impact of IAS management plans, reducing the effectiveness of IAS actions and their impact on reducing IAS threats to biodiversity. | The project will support MARA and the Government of China in establishing a functional coordination and collaboration system aimed at improving the overall planning and management of IAS. The Government of China sees this as an important step in the holistic approach towards managing and reducing the threat to biodiversity from IAS in China. It will establish and run a National IAS Management Coordinating Group, which will have a specified and agreed mandate. The project will support the development of guidelines and instructions for the establishment of provincial and county level coordination groups and will set up and run such Coordinating Groups in Hainan Province, Chongqing Municipality, Wenchang City and Bishan District. The coordinating groups will be actively involved in a larger subset of the project’s activities. |
| Output 1.2 Regulations influencing management of IAS and their negative impacts on agrobiodiversity are reviewed and revised/ developed at the national level and in target provinces to provide protection of traditional varieties and GRFA in agroecosystems. |  |
| While the national legislative and regulatory framework is generally speaking well developed, there are inconsistencies stemming from the isolation the different acts and regulations have been developed in. Cross-sector collaboration with other ministries or administrations is loosely formulated or non-existing. At provincial and local levels where mandates and areas of responsibilities are more loosely defined, this is also an issue, providing for inefficient on the ground IAS Management interventions. Cross-sector collaboration and responses are also lacking from the national and provincial rapid response and early warning guidelines, making these less effective. Further, the “First Priority” IAS species list and the 2007 National Quarantine Pest list, do not include a biodiversity risk assessment, leaving little safeguard for biodiversity overall. Also, there are limited, functioning mechanisms to alert if IAS are entering into protected areas, key ecological function zones, and other conservation areas from the surrounding landscapes, thereby posing a new threat to these areas. | The project will at national level assist ministries and administrations in aligning key IAS regulations with the new governmental mandates, as well as improving on the regulations guidance for cross-sector collaboration. Similar work will be done at provincial level where provincial regulations in Hainan and Chongqing will be reviewed and revised, providing examples for other provinces in China to voluntarily use as templates. This work will facilitate the needed interactions between departments for expedite and enhance on-the-ground implementation of IAS threat reduction measures, which, in landscapes that, for instance, contains areas with traditional varieties, will provide for national and global benefits. The project will further revise IAS Rapid Response Guidelines and IAS Early Warning Guidelines to be used at national, provincial and local levels. In addition, the project will develop an IAS Biodiversity Risk Assessment Guideline, which will assist in the identification of IAS posing as threats to biodiversity. The IAS Biodiversity Risk Assessment Guideline will be a “first” in China and will provide for an additional tool towards safeguarding China’s global, as well as national, important biodiversity. A key step in this regard is that the IAS Biodiversity Risk Assessment Guideline will be used in the project’s updating of the “First Priority” IAS species list and the updating of the National Quarantine Pest list. To further safeguard the preservation functions of conservation areas, and the important biodiversity within, the project will develop IAS buffer-zone guidelines, which will provide an extra protective layer against the encroachment of IAS into said preservation areas. The IAS buffer-zone guidelines will be an important reference document for the IAS Strategic Action Plans developed under output 1.3 The project will also, based on existing and project prepared guidelines, develop specific IAS Biodiversity Risk Assessment, Early Warning and Rapid Response guidelines for protected areas to be used by managers and staff in their work. These, and the IAS buffer-zone guidelines, will be disseminated to the provincial and local Environment Protection Bureaus. |
| Output 1.3 National and Provincial IAS Strategic Action Plans are developed, defining common targets and actions, and clarifying the responsibilities of agencies involved in IAS management, including roles related to agrobiodiversity conservation. |  |
| IAS are recognized to be a substantial threat to economy, livestock, crop and having considerable health and social implications. IAS Management has been included in the National Biodiversity and Action Plan 2011-2030, the Hainan and Chongqing Biodiversity Strategic Action Plans, as well as the national and provincial agriculture 13th five-year plans. In spite of this, China does not have an IAS strategy per se, and in extension, such strategies do not exist at provincial level either. There is therefore an unaddressed gap of how, in a holistic manner, to approach the prevention, control and management of IAS within the territory of China. Also, without a strategy, China does not have a national focus on the requirement for the development and maintenance of needed underlying structures. This combined provides for an inability to target IAS Management in a holistic manner and reduces the effectiveness in China’s IAS interventions, negatively affecting biodiversity. | The project will support the development of national and provincial IAS Management Strategy and Action Plans (IAS NSAP and IAS PSAPs). To frame the development of the NSAP, a long-term strategic vision for reducing IAS threats to economy and ecology, will be developed. Accompanying this will be an outline of the main areas where target interventions are needed to achieve the vision, including strengthened cross-sector collaboration, expansion/improvement of the monitoring stations network and monitoring methodologies, improved capabilities for data analysis and data management and safeguarding conservation areas and biodiversity. In addition, IAS Management financing, south/south and north/south cooperation and expanded public engagement and citizens science will be part of the strategies. Based on this vision the project will develop the National IAS Management Strategy and Action Plan and subsequently based on the national strategy develop the Provincial IAS Management Strategy and Action Plans (Hainan and Chongqing), ensuring consistency with the national approach and guidance. The process will be expert driven, through participatory approaches, where a broader set of stakeholders will be involved through social media platforms and selected focus groups. The NSAP and PSAPs will cover the period from 2021-2030 and 2022-2030, respectively. |
| Output 1.4 Sectoral strategies are revised to align with the national IAS strategic plan, mainstreaming relevant actions, indicators and targets to address IAS threats to agroecosystems. |  |
| Without a strategic framework in place ministries and administrations, and their provincial and local equivalents, by and large work independently on addressing IAS issues within their assigned areas of responsibilities. And while sector specific management plans for IAS prevention, control and management exist at all levels, these however, combined provide for a non-optimal intervention in the overall IAS Management. | The IAS NSAP and IAS PSAPs developed under output 1.3 will provide the strategic guidance to the individual ministries and administrations, and their respective provincial departments, for the future development of their sectoral Implementation Plans. Following the common framework provided by the IAS NSAP and IAS PSAPs, the combined sectoral Implementation Plans will constitute a more holistic approach for IAS Management, targeting the broader production landscapes, while at the same time providing IAS management solutions to the pockets of traditional varieties, endemic species and protected species found within said landscapes. In addition, the planning processes following the IAS NSAP and IAS PSAPs development will become part of the discussions and preparation of the ministries’ 14th and 15th five-year plans, providing long-term national and GE benefits. |

OUTCOME 1: Strengthened policy, regulatory and strategic framework for IAS Management incorporated into inter-sectoral response mechanisms for the reduction of IAS threats to agrobiodiversity, including traditional varieties and GRFA.

Output 1.1 Inter-agency coordination mechanisms are established to support IAS strategic plan implementation and improve the management of IAS threats to agrobiodiversity.

Intermediate Outcome (Result of the Output): More effective national, provincial and local level cooperation and collaboration for IAS Management

- As part of the efforts to prepare an adopted inter-sectoral approach to an integrated IAS Management response mechanism at national, provincial and local level, the project will support collaborative discussions on the scope and mandate of the National IAS Management Coordinating Group, between MARA, MEE and GACC and other ministries and administrations, working on IAS Management. The discussions will take fully into account the individual roles of the participating ministries and administrations. In addition, the National IAS Coordination Group will develop the TOR for the group outlining the responsibilities and main tasks of the coordination committee. It will also develop an initial workplan for the group, as well as develop and instructions for provincial and county level IAS Management Coordinating groups establishment (to be used in activities 1.1.2 and 1.1.3.).The project will further support the provincial and county level coordination group in Hainan (Wenchang) and Chongqing (Bishan) in their establishment and long-term running. Members of the groups, particularly in Hainan (Wenchang) and Chongqing (Bishan), will be capacitated through the participation in different project trainings (output 2.3). The coordinating groups will also play an active role in a sub-set of the project’s activities. Cumulatively these measures will contribute to an improved national, provincial and local cooperation and collaboration for IAS Management and will create a momentum for an adopted inter-sectoral approach.

Indicative Activities under Output 1.1 include:

1.1.1 Establish and operationalize the National IAS Coordination Group (co-financed) consisting of technical and legal IAS experts and representatives from the main ministries/administrations to guide and actively participate in the optimizing of the cross-sectoral IAS Management in China. The Coordination Group will be chaired by MARA and have members from agriculture, customs, forestry, fishery, animal husbandry, grassland, ocean and environment protection. The National IAS Coordination Group will meet regularly.

MARA/REEA will act as the activity lead supported by MEE/FECO and GACC/CAIQ. MARA/REEA, as overall responsible for the activity, will coordinate and obtain underlying inputs from MEE/FECO and GACC/CAIQ. MARA/REEA, MEE/FECO and GACC/CAIQ will work on, and be responsible for, the individual ministry work related to the activity. Hereinafter this will be referred to as (MARA-Lead; MEE-Support; GACC-Support.), see also Annex U and V for an overview of MARA’s, MEE’s and GACC’s implementation and financial responsibilities related to the individual activities.

1.1.2. Create and run Provincial IAS Management Coordinating Groups in Hainan and Chongqing (co-financed), following the instructions developed under activity 1.1.1. and the guiding principles for the establishment of the National IAS Management Coordinating Group. The Provincial IAS Management Coordinating Groups will be created and meet regularly throughout the project period and beyond. (MARA-Lead; MEE-Support; GACC-Support.)

1.1.3. Create and run County IAS Management Coordinating Groups in Wenchang and Bishan (co-financed), following the instructions developed under activity 1.1.1. and the guiding principles for the establishment of National IAS Coordination Group. The County IAS Coordination Groups will be created and meet regularly throughout the project period and beyond. (MARA-Lead; MEE-Support; GACC-Support.)

1.1.4. Hold annual multi-sector coordination seminars (starting year 2), where county, provincial and national experts, together with invited foreign experts, meet to discuss and learn about effective interagency collaboration, strategy formulation, action planning and IAS Management financing. (MARA-Lead; MEE-Support; GACC-Support.)

NOTE: BOLD indicates that the entity will manage GEF funding under the activity, please see project budget, budget notes and Annex U for details.

Output 1.2 Regulatory framework to strengthened management of IAS and their negative impacts on agrobiodiversity are reviewed and revised/ developed at the national level and in target provinces to provide protection of agrobiodiversity.

Intermediate Outcome (Result of the Output): Protection of agrobiodiversity, is supported/ensured through the implementation of developed regulations and guidelines.

- In order to efficiently address the negative impact of IAS on agrobiodiversity, including traditional varieties and GRFA, an adequate regulatory framework needs to be in place covering in a holistic manner IAS Management. The project will support the revision of the ministry and administration main/key IAS regulations with a specific focus on ensuring an alignment with the new governmental mandates, as well as improving on the regulations guidance for cross-sector collaboration, which is important for effectuating holistic on-the-ground implementation. Regulations covering the same topics/areas will be cross referenced and discussed by experts to ensure that the individual regulation revisions, combined, provide for clear and workable directions for effective coverage, as well as coordination. Subsequently, the revisions will be approved through the ministries and administrations own internal processes. The project developed revisions will provide for a more practical, integrated and focused cross-sectoral cooperation and implementation. The revised national level regulations will provide the guidance for a revision of similar provincial regulations in Hainan and Chongqing, which will be done through project support following the same processes as for the national revisions. As a further follow up, and strengthen the regulatory framework, IAS Rapid Response Guideline and the IAS Early Warning Guideline will be revised considering the project’s regulatory work and the Governmental regrouping. The aim will be to bring in cross-sectoral cooperation and collaboration and to make these guidelines timely, as well as, technically up-to date by including best national and international practices and approaches.

- To address the current gap in the national IAS risk assessments, which are essential for the updating of the “First Priority” IAS species list and the National Quarantine Pest list, the project will assist in the development of an IAS Biodiversity Risk Assessment Guideline. The guideline development will draw on national and international information, as well as research on IAS impact on biodiversity. The guideline will provide guidance for how to risk-assess IAS currently found in China, as well as known IAS that have not entered China yet. This guideline will provide a new and needed perspective on the IAS risk to biodiversity of both national and global importance.

- Furthering the aspect of protecting national and globally important biodiversity, an IAS buffer zones guideline, to be used in areas surrounding protected areas and other ecological sensitive zones, will be developed to provide additional security against IAS encroachment in key ecological function areas and other conservation and protected areas. The guideline will outline how to use existing structures like monitoring stations and activities such as regular surveys, as a base for the design and management (through a cross-sectoral approach) of areas surrounding conservation areas (i.e. IAS buffer zones). As part of this, typical IAS spread pathways will be determined and guidance for cost-effective options for “blocking“ these pathways will be provided. As such the IAS buffer zones would/should not be seen as an “add on”, but rather as part of the local monitoring and early warning systems/mechanisms, which via its early response will hinder (or minimize the risk of) IAS entering into conservation areas. From a protected areas management perspective, the protection from IAS will be further strengthened by the project developed IAS Risk Assessment, Early Warning and Rapid Response guidelines for protected areas, which will assist protected area managers and staff in implementing relevant and timely IAS Management actions. The project developed guidelines will be instrumental for the development of up-to-date coherent IAS regulations, ensuring the effective protection of traditional varieties and GRFA in agroecosystems inside, and outside, key ecological function areas and other conservation and protected areas. Incorporated cross-sectoral cooperation replicated at both national and regional level as well as implemented best technological and knowledge-based solutions will ensure effective and sustainable results of the IAS regulatory reform on IAS prevention, control and management.

Indicative Activities under Output 1.2 include:

1.2.1. Revise and adopt the national regulation framework to optimize cross-sectoral IAS Management, based on a verification of the PPG discussions (see also Annex L), the individual ministries and administrations (MARA, MEE and GACC) will update their regulations/ordinances, redirecting, enhancing and clarifying these to corresponded changes made during the Government restructuring exercise, make them technically up to date, as well as ensuring an increased cross-sectoral cooperation and coordination with other ministries and administrations.

1.2.2. Develop provincial regulation for IAS prevention, control and management in Hainan and Chongqing, which will draw from the work and results obtained under activity 1.2.1. while at the same time ensuring that the provincial regulations are specific to the individual province, taking local conditions into consideration. The regulations will provide instructions for the organization and implementation of cross-sectoral IAS Management. As with activity 1.2.1 the individual departments in (MARA, MEE and GACC) will undertake this work. The results of this activity will influence the IAS Management plans for Wenchang city and Bishan district (activity 3.4.1)

1.2.3. Revise IAS Early Warning Guidelines, to guide national, provincial and county level institutions and agencies in how to set up early warning systems and develop operational methodologies. The guidelines (activity 1.2.3, 1.2.4 and 1.2.5) is part of the overall policy expansion, which will strengthen the implementation of the regulatory framework. The IAS Early Warning Guideline will “step-off” from the current situation in China but will at the same time bring in the element of future requirements and needs. The work on the IAS early warning guideline will be interlinked with the National and Provincial IAS Management Strategy and Action Plan process (output 1.3) (MARA-Lead; MEE-Support; GACC-Support.)

1.2.4. Revise IAS rapid response guidelines, which, as for activity 1.2.3, will guide national, provincial and county level institutions and agencies. As activity 1.2.3, the guideline will be framed around the current situation in China, but also consider the element of future requirements and needs. The work on the IAS rapid response guideline will also be interlinked with the National and Provincial IAS Management Strategy and Action Plan process (output 1.3). The guideline work under activity 1.2.3 and 1.2.4 will also influence the IAS Management plans for Wenchang city and Bishan district (activity 3.4.1) (MARA-Lead; MEE-Support; GACC-Support.)

1.2.5. Develop an IAS Biodiversity Risk Assessment Guideline to complement the existing assessments which mainly focuses on invasive species impacts on production, economy, social and health. The IAS Biodiversity Risk Assessment guideline will enable risk estimations of species impact on biodiversity and the ecosystem services they provide. The guideline will be robust enough to enable evaluation of IAS already found in China and species that has the potential to entered China in the future. The developed guidelines will be used by the Government ministries and add a previously non-existing biodiversity layer to the updating of, for instance, the “First Priority” IAS species list (Activity 1.2.8.) and the National Quarantine Pest list (Activity 1.2.9.). (MEE-Lead; MARA-Support; GACC-Support.)

1.2.6 Develop IAS buffer zone guideline for areas surrounding ecological functioning zones and protected areas aimed at improving the protection of conservation areas and key ecological functioning zones from IAS encroachment. The guideline will be taking under consideration, during the develop of the sectoral/ department Implementation Plans supporting the Provincial IAS Management Strategy and Action Plans in Hainan and Chongqing (output 1.3). It will also influence the IAS Management plans for Wenchang city and Bishan district (activity 3.4.1) (MEE-Lead; MARA-Support; GACC-Support.)

1.2.7. Develop IAS Biodiversity Risk Assessment, Early Warning and Rapid Response guidelines for protected areas. Based on the guidelines developed under this output which are to support the Government ministries more broadly, a tailored set of documents providing additional directions to protected area managers and staff for how to ensure implementation within protected areas and other specialized functions conservation areas. These and the IAS buffer zone guideline (activity 1.2.6), will be disseminated to the provincial and local Environment Protection Bureaus. (MEE-Lead.)

1.2.8. Include biodiversity in the biennial updates of the “First Priority” IAS species list. Following the completion of the IAS Biodiversity Risk Assessment Guidelines (Activity 1.2.5) it will be used as an additional assessment layer in the biennial process of updating the “First Priority” IAS species list. The updating process (co-financed) will follow the established procedures and mechanisms within MARA. (MARA-Lead.)

1.2.9 Include biodiversity in the updating of the 2007 National Quarantine Pest list. Following the completion of the IAS Biodiversity Risk Assessment Guidelines (Activity 1.2.5) it will be used as an additional assessment layer in the biennial process of updating the 2007 National Quarantine Pest list. The updating process (co-financed) will follow the established procedures and mechanisms within GACC. (GACC-Lead.)

Output 1.3 Strategic plans for IAS are developed at national and provincial level defining common targets and actions and clarifying the responsibilities of agencies involved in IAS management, including roles related to agrobiodiversity conservation.

Intermediate Outcome (Result of the Output): Strategic Action Plans provide clear directives for long-term IAS prevention, control and management engagement by national and provincial governments, IAS Management agencies and other stakeholders.

- Integral part of the efforts to strengthen the strategic framework for IAS Management is the development of strategic plans putting forward long-term goals for IAS prevention, control and management at national and provincial level and outlining the actions and responsibilities of all institutional stakeholders involved. The project will support MARA in collaborative discussions with MEE and GACC and other ministries and administrations working on IAS Management, to develop the strategic vision and content of the National IAS Management Strategy and Action Plan (IAS NSAP 2021-2030). The vision and content setting process will springboard from the PPG identified barriers currently limiting China in effectively reducing the threats from IAS to China’s agrobiodiversity including traditional varieties and GRFA. The selection of the sub-set of areas to be addressed will observe optimal cost efficiency impact ratio, based on current and predicted future funding levels. The strategic vision will not be all-embracive, but rather pragmatic and realistic in scope providing practical guidance for the preparation of the IAS NSAP and their provincial equivalents (Provincial IAS Strategic Action Plans IAS PSAP). The National IAS Coordination Group will oversee the IAS NSAP development, whereas the main work will be done by sub-working groups for each of the “strategic areas” identified in the strategic vision document. The sub-working group will in turn work with individual focus groups as well as stakeholders at large through the social network platforms.

- A similar process will be followed for the development of the two IAS PSAPs for Hainan and Chongqing provinces, and the provincial process will generally follow the national process so as to ensure that the PSAPs correlates to the NSAP. Once developed the IAS NSAP and the IAS PSAPs will be submitted for approval to the National and Provincial governments. The National and Provincial IAS Strategic Management Action Plans will address priority areas of IAS Management until 2030 and will ensure sustainability in IAS Management at national and provincial level and an improved strategic IAS framework.

Indicative Activities under Output 1.3 include:

1.3.1 Develop the strategic vision and content of the National IAS Management Strategy and Action Plan (IAS NSAP 2021-2030) outlining the main strategic areas of intervention for the period 2021-2030 such as, but not limited to, expansion/improvement of the monitoring station network and monitoring methodologies, improved capabilities in data analysis and data management, including better data integration and synergies in, and between, provinces and national systems, safeguarding of preservation areas and biodiversity, expanded public engagement and citizens science, implementation of early response measures and expansion/improvement of early warning systems and methodologies. In addition, the strategy would also have a section on south/south and north/south cooperation. (MARA-Lead; MEE-Support; GACC-Support.)

1.3.2. Prepare the National IAS Management strategy and action plan (IAS NSAP 2021-2030) in line with the strategic vision (activity 1.3.1). For each of the identified main “strategic areas” sub-working groups (app. 4-7 people) will be formed (co-financed) to develop the respective chapters of the IAS NSAP 2021-2030, including realistic time-bound actions with associated budgets and performance indicators. For the development process links to key national strategies and action plans will be ensured. The sub-working groups, which are overseen by the National IAS Coordination Group, will on a regular basis interact among themselves to ensure coherence and synergies between the proposed actions. For instance, how best to have the expansion/improvement of the monitoring network link up with the provincial and national data management system/s. As part of the drafting process stakeholder focus group meetings on the IAS NSAP 2021-2030 planning will be held. Also, an IAS NSAP 2021-2030 verification workshop will be held for a broader audience, presenting the “strategic areas” as an integrated part of a holistic whole, highlighting the synergies and interlinkages between the different areas. The workshop will also present the proposed realistic time-bound actions, in draft form, their associated budgets and the associated performance indicators. The IAS NSAP 2021-2030 will be submitted for overall government approval. (MARA-Lead; MEE-Support; GACC-Support.)

1.3.3. Prepare Provincial IAS Management Strategy and Action Plan (IAS PSAP 2022-2030) for Hainan and Chongqing in line with the IAS NSAP 2021-2030 (Activity 1.3.2). The development process will be similar to that mentioned for activity 1.3.2 and links to key national and provincial strategies and action plans, such as the provincial BSAP, agrobiodiversity strategy and action plan and provincial ecological red lines and, for instance the IAS buffer zone guideline (activity 1.2.6), will be ensured. The sub-working groups, which are overseen by the Provincial IAS Coordination Group, will on a regular basis interact among themselves to ensure coherence and synergies between the proposed actions. Stakeholder focus group meetings on the IAS PSAP 2022-2030 planning will be held. As for the national planning process, IAS PSAP 2022-2030 verification workshops in Hainan and Chongqing, respectively, will present, for a broader audience, the “strategic areas” as an integrated part of a holistic whole, highlighting the synergies and interlinkages between the different areas. The workshop will also present the proposed realistic time-bound actions, in draft form, their associated budgets and the associated performance indicators. In Hainan, representative stakeholders involved in the Hainan C-SAP child project will be invited to ensure cross project input into the IAS PSAP 2022-2030 process. The two IAS PSAP 2022-2030 will be submitted for overall government approval. The National and Provincial processes (activity 1.3.2 and 1.3.3) will influence the IAS Management plans for Wenchang city and Bishan district (activity 3.4.1) (MARA-Lead; MEE-Support; GACC-Support.)

Output 1.4 Sectoral plans are revised to align with the national IAS strategic plan and updated regulations, mainstreaming relevant actions, indicators and targets to address IAS threats to agroecosystems.

Intermediate Outcome (Result of the Output): Sectoral implementation plans for the IAS NSAP and PSAPs ensuring an effective and cost-effective IAS prevention, control and management at national and provincial levels are adopted

- As part of an improved strategic IAS framework sectoral Implementation Plans for the NSAP and PSAPs need to be developed in concurrence with the priorities embedded in the IAS NSAP and PSAPs, as well as reflecting the updated regulations. As the IAS NSAP and IAS PSAPs have been cleared by the national and provincial coordinating groups, the project developed IAS NSAP and IAS PSAPs will, even in their draft forms, provide guidance to the different ministries and administrations’ IAS Implementation Plans. Thus, the draft IAS NSAP and IAS PSAPs can be used in the planning processes of the national ministries and administrations and their provincial equivalents. The project will support the relevant institutions/ departments at national and provincial levels in converting the IAS NSAP and IAS PSAPs into individual Implementation Plans, ensuring plan coordination and where possible will enable joint activities for larger scale undertakings in several sectors, providing for more cost-effective use of resources and time. The Implementation Plans will be approved through the respective ministry and department internal approval processes.

Indicative Activities under Output 1.4 include:

1.4.1. Develop sectoral/ministerial Implementation Plans for the IAS NSAP 2021-2030. Based on the IAS NSAP 2021-2030 (output 1.3), each of the main ministries and administrations (Agriculture, Ecology and Environment, Customs etc.) working on IAS Management in China, prepares Implementation Plans bringing together the various “strategic areas” activities relevant for the ministry/administration, while taking fully into account the project facilitated regulatory work (output 1.2). The sectoral/ministerial plans developed under this activity, which is largely co-financed, will become part of the discussions and preparation of the ministries’ 14th and 15th five-year plans.

1.4.1a Develop MARA Implementation Plans for the IAS NSAP 2021-2030 (MARA-Lead)

1.4.1b Develop MEE Implementation Plans for the IAS NSAP 2021-2030 (MEE-Lead)

1.4.1c Develop GACC Implementation Plans for the IAS NSAP 2021-2030 (GACC-Lead)

1.4.2. Develop sectoral/department Implementation Plans for the IAS PSAP 2022-2030 in Hainan and Chongqing. Based on the IAS PSAP 2022-2030 (output 1.3), each of the main departments (Agriculture, Ecology and Environment, Customs etc.) working on IAS Management in Hainan and Chongqing prepares Implementation Plans. As for activity 1.4.1, the departments will bring together the various “strategic areas” activities relevant for the departments, including IAS buffer zones (output 1.2), while taking fully into account the project facilitated regulatory work (output 1.2). The sectoral/department plans developed under this activity, which is largely co-financed, will become part of the discussions and preparation of the provincial 14th and 15th five-year plans.

1.4.2a Develop provincial agriculture Implementation Plans for the IAS NSAP 2021-2030 (MARA-Lead)

1.4.2b Develop provincial environment Implementation Plans for the IAS NSAP 2021-2030 (MEE-Lead)

1.4.2c Develop provincial customs Implementation Plans for the IAS NSAP 2021-2030 (GACC-Lead)

1.4.3. Ministry/administration approval of individual ministry/administrations and provincial/department IAS Implementation Plans. The ministry/administrations IAS Implementation Plans will go through the respective internal ministry/administration approval processes, whereas the individual department IAS Implementation Plans in Hainan and Chongqing will go through the respective internal departmental approval processes.

Component 1: Strengthened enabling environment: Total Cost: $ 4,289,870; GEF project grant requested: $ 664,250; Co-financing: $ 3,625,620

Component 2: Strengthened IAS Management frameworks and institutional capacity.

- For additional information for the project baseline related to component 2 please see section II Development Challenge and Annex E, F, K, L, N, O, P, and Q.

Table 4. Summary of baseline and incremental reasoning for Component 2

| Summary of Baseline Situation | Incremental Reasoning |
| --- | --- |
| Component 2: Strengthened IAS Management frameworks and institutional capacity. |  |
| Output 2.1 Methodologies for risk assessment, early warning and rapid response to IAS incursions in agroecosystems are developed and used. |  |
| As noted under output 1.2, national and provincial rapid response and early warning guidelines, as well as other existing IAS guidelines, provide insufficient guidance towards cross sector collaboration and are in many cases in need of updates to reflect the new realities in today’s China. Following this, the methodologies for the practical implementation of said guidelines are also in need of revision. In addition, for the project developed IAS Biodiversity Risk Assessment guideline there is currently not a methodology available and this needs to be developed. Overall this currently leaves implementors with insufficient tools and guidance to assess and advise on the appropriate steps to be taken for effective and targeted IAS Management aimed at reducing the risk to agrobiodiversity. | The project will, based on the project developed guidelines, formulate and test (in Hainan) practical and user-friendly Biodiversity IAS Risk Assessment, IAS Early Warning and IAS Rapid Response methodologies, thereby providing improved tools to be used in the day to day operation of staff working on the prevention, control and management of IAS. The use of the methodologies will enhance the protection of the agrobiodiversity in the productive landscape against IAS encroachment, and will, along with the general production species, also provide protection for areas with traditional varieties, GRFA and endemic species found within the agroecosystem. To ensure that the methodologies developed for Hainan adequately supports the IAS PSAP, they will be revisited, and based on user feedback revised as needed, following the approval of the IAS PSAP. |
| Output 2.2 Strengthened IAS inspection, detection, quarantine and disposal systems are developed for ports, and demonstrated at Yangpu ports, reducing the threat of entry of IAS through a high-risk invasion pathway. |  |
| The Chinese ports can be considered the first line of defense for preventing IAS from entering into China, and there is an extensive and complex set-up to control and manage screening and handling of IAS at the more than 400 Chinese ports. However, with the increase in international trade more and more cargo is channeled through the ports leading to an exponentially increasing possibility of IAS inadvertently goes undetected and leaves the port areas. At the same time the current management systems, methodologies and IAS related standards and technical specifications have not recently been updated. An example of this is the mentioned 2007 National Quarantine Pest list. Another example is the low technical and administrative capacities for “on-site” identification of IAS, where currently only a few IAS can be identified on spot without samples having to be sent out for “off-site” identification. A procedure which slows down the response process. And while port staff and staff within GACC are being trained on how to manage and work with the current systems, the trainings are infrequent and non-systematic. This reduces their effectiveness and increasing the possibility of IAS leaving the ports undetected, thereby increasing the potential threat to biodiversity. | The project will update a sub-set of national technical specifications for inspection and quarantine of IAS, focusing on the specifications currently in use at ports, with characteristics similar to Yangpu port, in China. This will include revisions of existing quarantine management systems currently in use, as well as updating of the standards and methodologies for cargo inspection. The project will also provide extensive trainings for port and GACC staff, and third-party operators, working with IAS prevention, control and management within the ports, enabling them (and the ports) to expedite the inspection and quarantine procedures, while maintaining the highest level of control quality. The planned improved capacity for “on-site” identification of IAS is a good illustration of this, as it will decrease the “time-laps” in the identification of IAS, thereby, as mentioned, reducing time for response. The project will enhance the ports “first line of defense” functions aimed at ensuring that IAS are contained at the entry ports and do not exit into the Chinese hinterlands, where they can have damaging impact on national and globally important biodiversity. |
| Output 2.3 Skills base of core IAS management agencies is strengthened through training and the integration of R&D supporting upscaling of IAS prevention, control and management systems. |  |
| The level of technical knowledge of IAS Management within the government institutions, particularly at the provincial and county level, is generally rudimentary, especially at entry levels positions, but also amongst mid-level management and technical personnel, even within the specialized departments. In addition to the lack of staff’s broad-based knowledge of the negative impact of IAS on the economy and ecology, IAS spread pathways and the need for cross sector coordination, there is also a lack of more comprehensive trainings for government officials/staff focusing on core aspects of IAS Management. The lack of knowledge at all levels provides for inadequate interventions which reduces the impact on IAS and in turn increases the threats to agrobiodiversity. Local extension services, for one, need capacity building, as IAS Management is a niche area, outside their main mandate. As a result, local farmers do only receive minimalistic information and training related to IAS Management, thus providing for only limited protection for biodiversity within the agroecosystem. Also, land use departments and departments working on rural development have limited knowledge of how their activities impact (and facilitate) the spread of IAS and do therefore not include safeguards in their planning and implementation of their activities. Furthermore, and although, monitoring systems and stations are in place, in China, these do not provide the capacity for IAS monitoring within local agricultural landscapes. Making IAS Management inefficient providing for an ineffective IAS threat reduction to agrobiodiversity. | The project will prepare and implement consolidated training packages to strengthen the capacity of government staff at national, but particularly at provincial and county levels. Identified training needs will be addressed via the delivery of the development of training modules. The project will facilitate specialized best practice technical trainings on a number of priority subjects. The trainings will be provided to staff in relevant agencies and departments and will capacitate them to carry out IAS Management related work in the productive landscape, safeguarding traditional varieties and general production species alike from IAS encroachment. The trainings will, via the project’s output 4.2, be made available on-line for e-learning, thus considerably increasing their outreach and magnitude. The project will also under this output develop an IAS application (APP), which can be used by Government Staff and other stakeholders including farmers, to identify, map and monitor IAS in the field. The data will enable local managers to gain up to date information on the IAS spread and species composition in the local agricultural landscapes. Training in the use of the APP and its management potential will be provided under the output, and the IAS APP will be actively used as part of the activities under component 3, as well as be an important tool in connection with the implementation of the IAS buffer zone guideline developed under activity 1.2.6. |

Outcome 2: Strengthened institutional capacities and interagency response mechanisms for IAS detection, quarantine disposal, monitoring, early warning and rapid response.

Output 2.1 Methodologies for risk assessment, early warning and rapid response to IAS incursions in agroecosystems are developed and used.

Intermediate Outcome (Result of the Output): Staff of state, regional and local administrations assigned with the protection of the agroecosystems from IAS incursions use Biodiversity IAS Risk Assessment, IAS Early Warning methodologies in their daily work.

- On-the-ground implementation of activities identified in the IAS strategic plans requires that practical tools and methodologies for IAS management are developed and put in place. The project will convert IAS Biodiversity Risk Assessment, IAS Early Warning and Rapid response guidelines (Output 1.2) into practical user-friendly methodologies to aid staff, working with IAS Management, in executing their duties in compliance with the guidelines. The functionality of the methodologies will be tested in Hainan and feedback from the users will be collected to evaluate the functionality of the methodologies, and by association the guidelines.

- To ensure that the methodologies adequately support the IAS PSAP they will be revisited, upon PSAP completion, and, where needed, be revised following the provided user feedback. The testing and revision of the methodologies will include, to the extent possible, relevant stakeholders from the Hainan C-SAP child project. The entire process is steered towards setting best practice example for a coherent and efficient IAS management leading to a sustainable reduction of IAS threats to agrobiodiversity including traditional varieties harbored within the agroecosystem.

Indicative Activities under Output 2.1 include:

2.1.1. Develop provincial IAS Biodiversity Risk Assessment Methodologies in Hainan. Following the project facilitated provincial regulatory work (output 1.2) and based on the developed IAS Biodiversity Risk Assessment Guidelines (output 1.2) the Provincial IAS Coordination Group will lead the development of the provincial methodology for assessing IAS risk in Hainan, considering the provincial characteristics and capacities (current and future). The provincial IAS Biodiversity Risk Assessment Methodology will initially be done following the guideline preparation, as well as by the end of the project. In Hainan representative stakeholders involved in the Hainan C-SAP child project will be consulted and included in the process as relevant. (MEE-Lead; MARA-Support)

2.1.2. Undertake an IAS Biodiversity Risk Assessment for Hainan. Together with department experts and following the developed provincial Biodiversity IAS Risk Assessment Methodology (Activity 2.1.1) the Provincial IAS Coordination Group will oversee the IAS risk assessment, combining the current procedures with that of the Biodiversity IAS Risk Assessment. The risk assessment will draw data from the provincial monitoring network (including ports) and information from the project developed IAS APP (output 2.3) and other feedback and information collection systems. In Hainan representative stakeholders involved in the Hainan C-SAP child project will be consulted and included in the process as relevant. (MEE-Lead)

2.1.3. Develop provincial IAS Early Warning Methodologies in Hainan. Following the project facilitated provincial regulatory work (output 1.2) and based on the developed IAS Early Warning Guideline (output 1.2) the Provincial IAS Coordination Group will oversee the development of the provincial methodology for the implementation of early warning of IAS introduction and establishment in Hainan, taking into account the provincial characteristics and capacities (current and future), particularly with regard to data providers, data management and data analysis. In Hainan representative stakeholders involved in the Hainan C-SAP child project will be consulted and included in the process as relevant. (MARA-Lead; MEE-Support; GACC-Support)

2.1.4. Operationalize IAS Early Warning in Hainan. Following the developed Provincial IAS Early Warning Methodology (Activity 2.1.3) provincial experts managing the province’s IAS data management systems will run early warning analysis regularly. The assessment will draw data from the provincial monitoring network (including ports) and information from the project developed IAS APP (output 2.3) and other feedback and information collection systems.  In addition, alerts and feedback via using mobile phones will be tested.  In Hainan representative stakeholders involved in the Hainan C-SAP child project will be consulted and included in the process as relevant. The activity will be undertaken via co-financing with no cost to the project. (MARA-Lead; MEE-Support; GACC-Support)

Output 2.2 Strengthened IAS inspection, detection, quarantine and disposal systems are developed for ports, and demonstrated at Yangpu port, reducing the threat of entry of IAS through a high-risk invasion pathway.

Intermediate Outcome (Result of the Output): Staff at Yangpu port use updated systems and methodologies for IAS inspection, quarantine and disposal in their daily work and training of staff at ports similar to Yangpu is delivered

- The Yangpu port is the largest deep see port in Hainan and the entry and exit ships accounted for 65% of the total volume in Hainan, making Yangpu port a key gateway to the island, as well as an important throughway for cargo going to other places in China. In this regard the Project will, using Yangpu as a demonstration port, assist China in reviewing and revising a sub-set of national technical specifications for inspection and quarantine of IAS, focusing on the specifications currently in use at the port. As the specifications are not port specific, they will be applicable to all ports with similar characteristics as Yangpu. As part of this the project will revise the port’s existing quarantine management systems and update standards and methodologies for cargo inspection. Port related staff including GACC staff and third-party port operators will be trained to manage and ensure a high level of scrutiny and safety in the inspection and quarantine procedures in a process where expediency is becoming ever more important. With the trainings being provided to a larger subset of ports, with similar characteristics as Yangpu, this output is an important linchpin in China’s protection of its biodiversity and ecosystems from IAS infringement.

Indicative Activities under Output 2.2 include:

2.2.1. Update the national technical specification for IAS inspection, quarantine and disposal used at Yangpu port to reflect the newest safeguards, based on an initial comparative analysis of new national research, improved national practices and best international practices. (GACC-Lead)

2.2.2. Review and update quarantine standards being followed at the Yangpu port, and similar ports in China, up-dating them to accommodate the current and future increase in cargo handling, while maintaining the highest degree quality control of the inspection process. (GACC-Lead)

2.2.3 Formulate/revise quarantine management methodologies used at Yangpu port enabling port staff to safely expedite the IAS identification, quarantine and disposal processes at the port, and similar ports in China. (GACC-Lead)

2.2.4. Develop and organize trainings. Training materials on 1) “on-site” identification of IAS 2) strengthened IAS inspection 3) revised quarantine management systems and 4) implementation of the updated technical specifications for quarantine and disposal of IAS will be developed. As part of the activity the training requirements and needed skills level of the training modules will be verified based on feedback from the port authorities. Following the development of the training materials training will be organized for relevant port staff and employees, taking fully into account gender equality and the mainstreaming of women in the work-place. With the project target of training 12,000 Government staff (Activity 2.2.4, 2.3.1 and 2.3.2 combined) the project will provide funding support for part of the trainings, while the remaining trainings will be undertaken separately through co-financing. (GACC-Lead)

Output 2.3 Skills base of core IAS management agencies is strengthened through training and the integration of R&D supporting upscaling of IAS prevention, control and management systems.

Intermediate Outcome (Result of the Output): Core IAS management agencies are capacitated to support upscaling of IAS prevention, control and management interventions at national, provincial and county levels.

- It is recognized that capacity and know-how of relevant staff are fundamental for a comprehensive and effective IAS management framework. In that line, the project will determine the training requirements and needed skills level of the training modules to be developed. The training materials developed for the project will rely on national and international best practices and include relevant research to ensure that the trainings are cutting edge and are based on the latest knowledge. The trainings will also incorporate aspects of the project developed guidelines, where relevant, and specific training on the developed guidelines will also be held, among other in connection with the development of the Biodiversity IAS Risk Assessment, and IAS Early Warning methodologies (output 2.1). The developed training modules (together with the trainings delivered under output 2.2) will be provided to a planned total of 12,000 government staff from various departments and agencies, primarily at provincial and county levels, but also national.

- The main focus of the trainings will be within the project provinces and counties, but depending on need and interest, the training modules can also be provided in the provinces and counties involved in the other C-SAP program child projects, including the UNDP Hainan and Hubei projects. Or alternatively stakeholders from these projects would be invited to the trainings held within the C-SAP 2 IAS project’s area of influence.

- MEE has during the PPG phase identified that there is a specific need to train provincial and local environmental bureaus, as well as, protected areas managers and staff on IAS Biodiversity Risk Assessment, and Early Warning measures, as well as non-chemical IAS control and managements techniques (see Annex E). To accommodate this specific target group, the relevant sub-set of the developed training modules will be adapted for the use in protected areas and tailored to the specific audience.

Indicative Activities under Output 2.3 include:

2.3.1. Develop and organize R&D supported technical training courses, part of which will be certification courses, on key subjects to address training needs, such as:

- Introduction to IAS

- Ecological and economic impact of IAS

- Traditional varieties, endemic species and GRFA

- Use of biological agents in IAS Management

- Use of vegetation replacement techniques in IAS Management

- Chemical reduction approaches in IAS Management

- Village and local level planning of IAS Management

- Safety handling and management of chemicals

- IAS removal and eradication techniques

- IAS risk assessment

- Early detection and response

- Participatory approaches and facilitation to engage the public, including farmers

- Interagency coordination and cooperation

- Briefing on project developed guidelines and revised/new regulations

The training requirements and needed skills level of the training modules will be evaluated in collaboration with the National and Provincial IAS Coordination Groups and feedback from county departments. The trainings will be developed based on the extensive knowledge and research, as well as lessons learned and feedback from implementation of IAS Management undertaken in China previously. The trainings will be forward looking and bring in new approaches from China and internationally. Following the training and training material development, trainings will be organized for staff and employees working in IAS Management at national, provincial and county levels, taking fully into account gender equality and the mainstreaming of women in the work-place. With the project target of training 12,000 Government staff (Activity 2.2.4, 2.3.1 and 2.3.2 combined) the project will provide funding support for part of the trainings while the remaining trainings will be undertaken separately or through co-financing support. Part of the Government staff at provincial and county levels will be from the extension services, who will engaged in the training of farmers etc. at local level (output 3.2 and 3.4). The trainings will have equal relevance for all the agroecosystems, including areas containing traditional varieties and small conservation areas, harbored within the productive landscape. Efforts will be made to invite and engage interested stakeholders from the Hainan child project and the other C-SAP child projects to the extent possible (participation cost covered by C-SAP child projects or through co-financing). (MARA-Lead; MEE-Support)

2.3.2 Organize selected trainings for managers and staff working at protected areas, reserves or other ecological sensitive areas, taking fully into account gender equality and the mainstreaming of women in the work-place. The activity will tailor-make the activity 2.3.1 trainings to the needs of protected areas’ (and other conservation areas’) managers and staff, thereby providing specific project support tailored towards areas of high biodiversity value. With the project target of training 12,000 Government staff (Activity 2.2.4, 2.3.1 and 2.3.2 combined) the project will provide funding support for part of the trainings while the remaining trainings will be undertaken separately or through co-financing support. Efforts will be made to invite and engage interested stakeholders from the other C-SAP child projects to the extent possible (participation cost covered by C-SAP child projects or through co-financing). (MEE-Lead)

2.3.3. Develop an IAS application (APP), which is accessible to Government staff and researchers working on IAS Management, other stakeholders with interest in IAS Management, including farmers and the general public. This APP will be based on an existing CAAS APP for IAS field data collection, species identification, data upload, data and information query. A software specialist will expand on the existing APP enabling it to be used by, and manage data from, the public, as well as ensuring that it is user-friendly. The testing and demonstration of the app is done under Component 3, where the IAS APP will be used for IAS identification and monitoring. Government staff will be trained, under the current output, in the use of the APP, as well as in how the APP can be an effective tool in local IAS monitoring, early detection and early response. (MARA-Lead; MEE-Support; GACC-Support)

Component 2: Strengthened IAS Management frameworks and institutional capacity: Total Cost: $ 4,890,887; GEF project grant requested: $ 576,295; Co-financing: $ 4,314,592

Component 3: Demonstration of IAS threat reduction in agroecosystems.

- For additional information for the project baseline related to component 3 please see section II Development Challenge and Annex E, F, K, L, N, O, P, and Q.

Table 5. Summary of baseline and incremental reasoning for Component 3

| Summary of Baseline Situation | Incremental Reasoning |
| --- | --- |
| Component 3: Demonstration of IAS threat reduction in agroecosystems. |  |
| Output 3.1 Farming communities, including cooperatives, agricultural enterprises and other relevant stakeholders are capacitated in IAS Management through training that builds the knowledge and skills base of all groups to work together to address IAS threats to agroecosystems. |  |
| The PPG process, including the field visits to the project areas and the surveys undertaken, demonstrated that farmers, including cooperatives, have in general little knowledge of IAS and how to control and manage them, and they treat them as they would any other weed and pest encountered within the agroecosystem. This result in ineffective removal of the IAS and often an excessive use of pesticide, which has both health and environmental consequences. Most training provided at village level is related to improving villagers’ livelihoods options, such as better household management or establishment of small businesses. Thus, a negligible number of farmers in villages (including within the project target agricultural landscape) have received information or training related to proper IAS Management, leaving agrobiodiversity exposed for IAS encroachment, which could result in local biodiversity loss. | The project will prepare and implement consolidated training packages to strengthen the capacity of farmers, including cooperatives, agricultural enterprises and other relevant stakeholders to appropriately prevent, control and manage IAS within their fields and the surrounding public village areas, aimed at providing a holistic approach to IAS Management at village level rather than piecemeal individual interventions. The project will facilitate specialized best practice technical trainings on a number of priority subjects. The trainings will be provided to local stakeholders enabling them to implement suitable IAS Management techniques, which remove or reduce the threat of IAS to agrobiodiversity, including traditional varieties grown within their area. The trainings, including videos of the practical on-the-ground trainings, will via the project’s output 4.2 be made available on-line for e-learning, increasing considerably their outreach and magnitude. |
| Output 3.2 Participatory approaches for IAS Management are demonstrated in 60 ha within two target agricultural landscapes, providing viable and cost-effective techniques to reduce IAS threats and impacts. |  |
| Land management at the village level is fractioned and restricted mainly to the farming plots of the individual farmers. Although some coordination does occur when farmers help each other out during planting and harvesting for instance, it takes place on plots of land scattered throughout the village areas. Farming cooperatives, which have consolidated lands, do, within their consolidated lands (often adjacent), have joint land management and therefore benefits from area of scale. Overall, however, the undertaken IAS Management activities in the villages are not coordinated, nor part of a broader intervention to prevent, control or manage IAS. And while IAS is being managed within the individual farming plots, the lack of coordination and overall approach results in that IAS remain in public areas, abandoned areas and areas with no clear ownership, thus leaving “islands” of IAS populations from which the IAS can continuously spread into the farming systems and threaten agrobiodiversity. | The project will, through trainings, empower farming communities in Hulu and Longfei in engaging in various tested and area-appropriate techniques demonstrating their effectiveness in the local area. The farmers will also, through a participatory process, formulate IAS Management Plans for the project core areas, containing a mix of fields with traditional varieties and common commercial crops, in the two villages, focusing on the combined management of the areas to reduce the risk of IAS re-establishment. To ensure the integrity of the project core areas, buffer zones surrounding the areas will also be agreed to and managed as part of the planning process and plan implementation. To facilitate the planning and create an expanded understanding of the IAS threat, the IAS populations will be mapped and described using the IAS APP. Furthermore, the planning processes, the area mapping and the on the ground implementation of the taught IAS Management techniques will be recorded and visualized, and the documentation of the interventions will be presented in the IAS Management Science Base/ Public Science Popularization Base established under this output. |
| Output 3.3 Improved understanding of IAS distribution and impacts on agrobiodiversity at two target landscapes through targeted and management-oriented surveys and assessments. |  |
| Within Wenchang city and Bishan district regular surveys using village reporting are conducted at 3-5 years intervals. However, these surveys focus on individual species (and are based on present/non-present determination within the village area) and do not provide a comprehensive picture of the IAS infestation. Also, there are no joint monitoring activities being organized between departments, so information is disaggregated and so far, no efforts have been made to combine available data, rendering an incomplete picture of the actual encroachment of, even the most critical, IAS occurring in Wenchang and Bishan. And while the previously undertaken surveys do rely on reporting from farmers, and thus participatory, they do not encompass other people such as the public, tourists, local villagers or volunteers from CSOs. Also, surveys so far have not relied on the latest information technology, such as the use of smart phones APP, drones, or other easy to use and low-cost remote sensing technologies. The lack of comprehensive surveys and aggregation of data, provides for an incomplete picture making implementation of holistic approaches to IAS Management difficult, thus reducing the impact on IAS and increasing the risk to biodiversity. | To obtain up to date information of the main IAS found in Wenchang city and Bishan district and evaluate their impact on agrobiodiversity, the project will make use of the project developed IAS APP, which provides for a user-friendly technology and application for on the ground species identification and information collection. The project will use these in conjunction with a citizens’ driven monitoring approach, using the APP, involving local farmers, CSOs and the public at large, to create a GIS based information layer, which can be overlaid with information collected from the existing monitoring system. This public participation process will be documented. Based on the IAS distribution the project will assess the impact aspects on for instance productivity, cost of IAS Management, livelihoods, and agrobiodiversity, including traditional varieties, based on latest research and knowledge including IAS economics, IAS spread patterns and risk assessments. The project will also undertake a similar survey in a representative protected area to demonstrate the benefits and suitability of the project promoted methodology in a protected area’s setting, involving protected area stakeholders. |
| Output 3.4 Operational IAS management plans are developed for two target agricultural landscapes and implemented on 35,000 ha demonstrably reducing IAS threats on agrobiodiversity and traditional varieties. |  |
| Operational IAS management planning is not part of the general land management in China and do currently not occur in Wenchang City and Bishan district. However, large scale IAS control and management initiatives have been implemented in various parts of China in the past years. These interventions are mostly focusing on single or few species and are implemented as part of sectoral engagements without any cross-sector collaboration and or coordination. The interventions are generally also undertaken within administrative boarders without consideration of the IAS spread in the physical landscape. | The project will support local authorities, farmers and other stakeholders to together in a participatory process formulate an IAS management plan for Wenchang City and Bishan District with a specific focus on the project targeted agricultural landscapes. The plan will hinge on cross-sectoral development and implementation approaches and will rely on the active participation of the local farming communities, who will use the IAS Management skills and techniques taught by the project. The plan will be holistic, treating the project targeted agricultural landscapes, containing a mix of traditional varieties and common commercial crops, as single combined units, where IAS control and management is provided in equal measures to productive areas and public/common areas alike, to reduce the risk of IAS re-establishment. Parts of the IAS management plan for Wenchang City and Bishan District will include testing the local monitoring system’s ability to identify an influx of new IAS into the project targeted agricultural landscapes and undertake eradication of any new specie entering the area. The implementation of the management plans will rely on technical support being provided to farmers, government staff and other stakeholders on the ground. In addition, many of the interventions are of no cost to the project. For instance, local farmers are already engaged in active management of weeds in their fields, including IAS. The project, however, will promote, for instance, timing of spraying and the usage of low chemical spraying, substituting local spraying practices reducing spraying cost and minimizing the environmental impact from excessive chemical usage. Usage of biological agents and crop-plants as vegetative replacement on IAS infested lands, will rely on cost benefit incentives in form of increased income earnings. However, to ensure critical mass, subsidies (co-financing) towards the purchase of biological agents will be provided. Aside from this, local Government will have its own programs and projects (co-financed), which are to be implemented in the two-project targeted agricultural landscapes, including potential rapid response and early engagement in IAS eradication as needed. |

Outcome 3: Strengthened IAS threat reduction through collaborative IAS Management by IAS Management agencies, agricultural enterprises and farming communities in Hainan and Chongqing agricultural landscapes.

Output 3.1 Farming communities, including cooperatives, agricultural enterprises and other relevant stakeholders are capacitated through training building the knowledge and skills base of all groups to work together to address IAS threats to agroecosystems.

Intermediate Outcome (Result of the Output): Farming communities, including cooperatives, agricultural enterprises and other relevant stakeholders capacitated to effectively address IAS threats to agroecosystems and their biodiversity.

- The success of the overall efforts to reduce IAS threats to agroecosystems and the biodiversity within them largely depends on the adequate involvement of all relevant stakeholders including those on the front line dealing with IAS in their daily lives. The project will therefore improve the IAS knowledge and skills of the local farmers and farming communities to bring them to par with the rest of the IAS Management network. The project will do this by custom tailored trainings lifting up local farmers’ understanding, know-how and practices for addressing IAS threats. The trainings will be based on practical on-the-ground demonstration activities, where farmers and other stakeholders will gain hands-on experience with the IAS Management techniques the project is promoting. The trainings developed will contain easy to follow and practical manuals and guidelines, for the trainees to use and have as reference materials following training completion. Planning for IAS Management for village areas will be an essential part of the training.  The developed training modules will be provided to a planned total of 6,000 farmers, including cooperatives, agricultural enterprises and other relevant stakeholders.

- The main vehicle for the training delivery will be the local extension services, which will be trained in the different IAS Management techniques and on how to provide trainings to local stakeholders. The project will ensure that at least 50% of the people trained are women, and that the trainings will be done through a mix of all women’s groups and combined groups.  The project will also aim at training at least 20 % of participants who are under 35 years of age when they are being trained. Special efforts will also be made to ensure ethnic mainstreaming, to the extent possible.

- The main focus of the trainings will be placed on the stakeholders from the project targeted agricultural landscapes but depending on need and interest from other C-SAP program child projects, including the UNDP-supported Hainan and Hubei agrobiodiversity projects, could be invited to participate in the trainings, or to visit the project targeted agricultural landscapes. The project will also create local capacity at village level, by ensuring that one or more people in a village are trained in all provided training modules. In the Hulu and Longfei villages the Village Capacity Personnel will act as resource persons for the IAS Management Science Base/ Public Science Popularization Base. The expected results of the trainings will translate into that local individual farmers, farming communities, cooperatives, agricultural enterprises and other relevant stakeholders are capacitated to effectively address IAS threats to agrobiodiversity in the broader context of biodiversity and environmental conservation.

Indicative Activities under Output 3.1 include:

3.1.1. Adapt trainings on key subjects, based on the develop training courses (output 2.3) to address farmers and other stakeholders training needs, such as:

- Use of biological agents in IAS Management

- Use of vegetative replacement techniques in IAS Management

- Chemical reduction in IAS Management

- Safety handling and management of chemicals

- IAS removal and eradication techniques

- Village planning of IAS Management

- Local IAS monitoring and reporting

- IAS spread pathways and available countermeasures

The training requirements will be evaluated in collaboration with the National and Provincial IAS Coordination Groups and the County IAS Management Coordinating Group and feedback from the farming communities etc. (MARA-Lead)

3.1.2 Organize adapted trainings for different stakeholder groups including farmers, cooperatives, enterprises and other stakeholders. As part of the planning and implementation of the trainings the organizers will ensure that gender and mainstreaming of women play a central role in the provision of trainings, including having all women trainings and observing the gender equality. Local extension service personnel, and other relevant provincial and county staff trained under output 2.3, will provide the trainings following the adapted training materials (Activity 3.1.1.). Efforts will be made to invite and engage interested stakeholders from the Hainan child project and the other C-SAP child projects to the extent possible. (participation cost is co-financed). Also, extended trainings for Village Capacity Personnel (ViCaP) will be provided, thereby establishing a local resource person, who can assist the local community in day to day IAS Management issues. In Wenchang and Bishan the ViCaP will act as resource persons for the IAS Management Science Base/Public Science Popularization Base (Activity 3.2.3.). (MARA-Lead)

Output 3.2 Participatory approaches for preventing, controlling and managing IAS are demonstrated in 60 ha within two target agricultural landscapes, providing viable and cost-effective techniques to reduce IAS threats and impacts.

Intermediate Outcome (Result of the Output): IAS threats in the project core areas are reduced through participatory planning and implementation of areas management plans.

- The project will support Hulu and Longfei villages to develop, through a participatory process, long-term management plans for mile-a-minute, alligator weed and golden apple snail (in Hulu) and mile-a-minute and alligator weed (in Longfei) for the project’s core areas, where local farmers will implement the IAS Management technologies, for which the farmers have received training (output 3.1). These small-scale management plans will ensure that the project’s core areas are managed, as a combined unit, so that public areas, abandoned areas and areas with no clear ownership are managed on an equal footing with the actual farmland within the core area. Thereby safeguarding that IAS do not reestablish themselves from a residual population within the site. The participatory management plans will also include a surrounding buffer area, in which an integrated IAS Management would be pursued to ensure the integrity of the project core areas. The local management planning processes for the core areas in Hulu and Longfei villages, will act as a template for other village agreement needed as part of the management plans to be implemented for the project targeted agricultural landscapes in Wenchang and Bishan (output 3.4).

- As part of the participatory planning process the farmers will identify and map the IAS within the project core sites, and in the surrounding areas using the project developed IAS APP. The use of the IAS APP for IAS identification and monitoring, by the farming community in Hulu and Longfei village will be part of the project’s testing of the APP and will provide for one of the feedback loops towards improving the user friendliness and usability of the APP.

- Based on the basic information collected using the IAS APP and the project ascertained knowledge of available IAS Management techniques, the farmers will determine the best approach for long-term IAS control and management of the project core areas and will subsequently implement the developed management plan according to the farmer-to-farmer agreements made at village level. By actively managing the village areas holistically, the threat from IAS towards the mix of common crop species and traditional varieties within the local agroecosystem will be reduced.

- The project will also support the IAS Management Science Base/ Public Science Popularization Base in Hulu and Longfei villages, which are to be established in existing premises, through the provision of educational and awareness raising materials developed under the project. In addition, the participatory planning process, the plan implementation, as well as the use of the taught IAS Management techniques will be recorded and visualized. The documentation of the interventions will be presented in the IAS Management Science Base/ Public Science Popularization Base, as good practice examples.  The demonstrated participatory approach and IAS management techniques, in the core project areas, will result in reduced IAS threats in these areas, and will create a baseline for best practices to be replicated in other areas in China.

Indicative Activities under Output 3.2 include:

3.2.1. Demonstrate verified and applicable participatory IAS Management approaches in Wenchang and Bishan core project areas, through the application of farmers’ and other stakeholders’ skills acquired in the provided trainings (output 3.1) (MARA-Lead):

- Use of biological agents in IAS Management

- Use of vegetative replacement techniques in IAS Management

- Chemical reduction in IAS Management

- Safety handling and management of chemicals

- IAS removal and eradication techniques

- Village planning of IAS Management

- Local IAS monitoring and reporting

3.2.2. Utilize the publicly accessible IAS APP (output 2.3) for on the ground IAS identification and monitoring in and around the Hulu and Longfei villages, as well as the larger project targeted agricultural landscapes. The activity will facilitate the carrying out of farmer supported and voluntary public IAS monitoring and data collection. The latter being undertaken by villagers and other stakeholders, including through the engagement of local schools. Popularization of the IAS APP will be done via 1) the social media and other information outlets; 2) introduction of the APP as an educational tool to schools and; 3) using the APP as a tool in extension services/farmers interactions and in farmers trainings. (MARA-Lead)

3.2.3 Support the IAS Management Science Base/Public Science Popularization Base in Wenchang and Bishan. The facilities for the Public Science Popularization Base and its running cost will be co-financed by the county government, whereas the project will provide training materials, pull-ups, posters etc. developed under the project. The Public Science Popularization Base will be used for the demonstration and dissemination of knowledge of, among other, the ecological and economic impact of IAS, importance of traditional varieties, endemic species and GRFA, approaches to reduce the threats from IAS. As part of this, the Public Science Popularization Base will have access to the materials on the Knowledge Management platform (Output 4.2). The ViCaP (output 3.1) in Wenchang and Bishan will act as resource persons for the Public Science Popularization Base. (MARA-Lead)

Output 3.3 Improved understanding of IAS distribution and impacts on agrobiodiversity, at two agriculture landscapes through targeted and management-oriented surveys and assessments.

Intermediate Outcome (Result of the Output): Distribution and impacts of occurring main IAS in Wenchang and Bishan, on agrobiodiversity, including traditional varieties and GRFA, are well understood and documented.

- To effectively design measures for prevention and control of IAS it is important that correct and up-to-date data for their distribution and impact is collected and analyzed. Indispensable to this process is the broad base participation of local farmers and citizens who through various techniques could fill in the profiles of the currently occurring IAS. For the collection of data of the main IAS found in Wenchang city and Bishan district the project will use a citizen’s driven participatory approach using readily available, user-friendly technologies and applications for field identification and recording of IAS, including the IAS APP (output 2.3). Local farmers, CSOs and the public at large will through social media and other means be sensitized to participate in the project promoted citizens driven monitoring approach. The collected data will provide a GIS based information layer, which can be overlaid with information collected from the existing monitoring and data collection systems in Wenchang and Bishan. In this regard, the project’s two agricultural landscapes will undergo a more targeted investigation. In all two surveys will be conducted, one at the completion of the IAS APP where this first survey will act as an initial test of the reliability and functionality of the information collected. As part of the management and use by local authorities of the various monitoring and information platforms and collection methods, a second survey will be conducted by the end of the project.

- To create additional momentum the public participatory citizens driven monitoring exercise will be documented by the project, through the collection of the participants own stories, video reporting and other social media entries. The participants’ social media postings will stir interest which will assist the project in creating a broad participants base, as well as will provide material suitable for short documentaries, awareness raising and public dissemination.

- The impact (current and future) on agrobiodiversity will, following the identification of the main IAS occurring in Wenchang and Bishan, be assessed. The impact assessment will be based on latest research and knowledge on for instance IAS economics, IAS spread patterns, consultations with local farmers, and information on current, and planned, IAS Management interventions by Government authorities. The impacts to be reviewed would include, but not limited to, the impact on ecology, including endemic species and traditional varieties, ecological functions/ecosystem services, impacts on productivity and cost of IAS Management, livelihoods, including household loss in production and/or reduction in accessible land, and IAS’ spread impact on land usage.

- The project will involve protected area stakeholders in a similar survey, in a representative protected area, to demonstrate the benefits and suitability of the project promoted methodology in a protected area’s setting. In the end, the distribution and impact on agrobiodiversity of the main IAS found in the project’s two agricultural landscapes will be well studied and documented, thus again creating a best practice example and a benchmark for qualitative IAS data collection and knowledge base development.

Indicative Activities under Output 3.3 include:

3.3.1 Design the IAS distribution survey and IAS impact assessment of selected IAS in Wenchang and Bishan, in collaboration with the IAS Coordination Groups in Hainan, Chongqing, Wenchang and Bishan, as well as feedback from the farming communities etc. In designing the IAS distribution surveys, the broad-based involvement of government and public stakeholders will be ensured, as will the use of various surveying techniques and information collection tools, including an expanded use of web-based technologies and platforms. This will include the project developed public accessible IAS APP (output 2.3), as well as different easily accessible remote sensing methodologies and approaches. (MARA-Lead; MEE-Support)

3.3.2 Design the IAS distribution survey and IAS impact assessment of selected main IAS in a representative protected area in collaboration with the Provincial IAS Coordination Group and the protected area’s management with feedback from farming communities and other stakeholder groups engaged in the vicinity of the protected area. (MEE-Lead)

3.3.3. Undertake the IAS distribution survey and IAS impact assessment in Wenchang, Bishan and a representative protected area, following the developed implementation plan (Activity 3.3.1. and 3.3.2.). In Hainan efforts will be made to invite and have representatives from the Hainan child project counties participate in the field work (and preparation) to create synergies and a link to the child project’s work on participatory landscape assessment. Prior to undertaking the actual work, confirmation and agreement, of the individual institutions and stakeholder groups tasks under the IAS distribution surveys and IAS impact assessments, will be ensured, for instance through signed cooperation agreements. Also, the IAS distribution surveys and IAS impact assessments in Wenchang, Bishan and the representative protected area will be documented through Weibo, short videos (by participants), local interviews (by and of participants), local news reporting etc.

3.3.3a. Undertake the IAS distribution survey and IAS impact assessment in Wenchang and Bishan (MARA-Lead)

3.3.3b. Undertake the IAS distribution survey and IAS impact assessment in a representative protected area (MEE-Lead)

3.3.4. Formulate the IAS distribution survey and IAS impact assessment reports for Wenchang, Bishan and the representative protected area. The collected material and data will be analyzed and individual reports for Chongqing and Hainan will be prepared, as will a report for the protected area. The IAS distribution surveys and IAS impact assessment reports will be presented for a broader audience, including key provincial decision makers, and publicize the reports’ findings through local and national media, as well as through various social media platforms. The reports will provide for key documentation on the consequential impacts of IAS and their cost to biodiversity, economy and livelihoods, which is much needed in the governmental and public debate.

3.3.4a. Formulate the IAS distribution survey and IAS impact assessment reports for Wenchang and Bishan. (MARA-Lead)

3.3.4b. Formulate the IAS distribution survey and IAS impact assessment reports for the representative protected area (MEE-Lead)

Output 3.4 Operational IAS management plans are developed for two target agricultural landscapes and implemented on 35,000 ha demonstrably reducing IAS threats on agrobiodiversity and traditional varieties.

Intermediate Outcome (Result of the Output): Agrobiodiversity, including traditional varieties are safeguarded against the threat of IAS in 35,000 ha of land which is actively being managed according to developed management plans.

- The project will support the development of an IAS management plans for Wenchang City and Bishan District that includes a specific section related to the projects two agricultural landscapes. The plans will be formulated through a participatory process involving local authorities, farmers and other stakeholders. A central part of the plan will be its cross-sectoral focus and holistic approach towards IAS control and management, combining actions from all parties. Furthermore, the plan will ensure that for the targeted interventions in IAS affected areas there will be an equal focus on the productive areas and public and common areas to reduce the risk of IAS re-establishment. The plans will be approved by the Wenchang City and Bishan District Governments and each entity (Agriculture, forestry environment etc.) will be responsible for the implementation within their respective sectors, and they will integrate their tasks into their workplans. In addition, other stakeholder groups such as farmer cooperatives and villages/township authorities (farmers) will have their assigned tasks. The plan implementation will be coordinated by the County IAS Management Coordinating Groups in Wenchang and Bishan.

- The implementation of the plan will rely on the active participation of the local farming communities, and their increased capacity to employ the project promoted, and taught, IAS control and management techniques. For the two project agricultural landscapes, consultations with the various institutions and stakeholder groups will be held to ensure that the immediate and long-term actions to be undertaken, by stakeholders within the affected areas, are understood and agreed to.

- The project will, through its interventions, halt and reverse the encroachment of mile-a-minute, alligator weed and golden apple snail within the projects targeted 35,000 ha large agricultural area through a range of different proven control and management methods involving use of biological agents, vegetation replacement techniques, and use of low chemical interventions (Annex L). Training in different removal and eradication techniques will also be provided, however outside the provided trainings, larger scale removal and eradication activities will be undertaken via project co-financing or other funding sources. The project on the ground engagement is aimed at safeguarding and reducing the threat from IAS towards the traditional varieties found within the project targeted agricultural landscapes (see Development Challenge, as well as Annex Q).

- Parts of the IAS management plan for Wenchang City and Bishan District will include the testing of IAS APP facilitated “monitoring system” ability to identify an influx of new IAS into the project targeted agricultural landscapes and undertake the eradication of any new specie entering the area. The important result of the above measures would translate in not only 35,000 ha of land being protected from IAS threat but also in the efficiency of IAS management plans and the adopted participatory approach being demonstrated and a best practice being established.

Indicative Activities under Output 3.4 include:

3.4.1 Formulate IAS Management plans for Wenchang city and Bishan district in collaboration with the IAS Management Coordinating Groups in Wenchang and Bishan and the involvement of extension agencies experts (and other experts), farming community representatives, businesses and other relevant stakeholders (including women groups), taking fully into account:

- the IAS distribution surveys and IAS impact assessment reports (output 3.3)

- the IAS buffer zones guidelines for ecological functioning zones and protected areas (output 1.2)

- the best practices promoted by the project through its trainings (output 2.3 and 3.1)

- the protection of traditional varieties and GRFA and

- stakeholder participation in ensuring IAS Management in public areas, as well as IAS monitoring and early warning.

The plans will also consider the projects regulatory work, as well as its work on guidelines (output 1.2) and the IAS Strategic Action Plan processes (output 1.3). The plans will be approved by the Wenchang City and Bishan District Governments. (MARA-Lead; MEE-Support)

3.4.2 Implement the IAS Management plans for the two, project targeted, agricultural landscapes in Wenchang city and Bishan district following the agreed implementation plan (Activity 3.4.1.).  Prior to undertaking the actual work, confirmation and agreement, of the individual institutions and stakeholder groups tasks for the implementation of the IAS Management plans in the Wenchang and Bishan counties, will be ensured. For instance, through signed cooperation agreements with among other farming cooperatives and villages/township authorities (farmers). Eradication of new IAS, or halting new IAS population expansions, in the two project-targeted agricultural landscapes, in Wenchang city and Bishan district, will also be undertaken, where the local governments (co financed) will use the best practices promoted by the project through its trainings (output 2.3 and 3.1). As part of the activity the validity of broad usage the IAS APP, as an effective monitoring tool to discover new IAS, or IAS population expansions, will be tested in Wenchang and Bishan. (MARA-Lead)

Component 3: Demonstration of IAS threat reduction in agroecosystems: Total Cost: $ 5,090,211; GEF project grant requested: $ 560,450; Co-financing: $ 4,529,761

Component 4:  Awareness raising, knowledge management and coordination.

For additional information for the project baseline related to component 3 please see section II Development Challenge and Annex E, F, K, L, N, O, P, and Q.

Table 6. Summary of baseline and incremental reasoning for Component 4

| Summary of Baseline Situation | Incremental Reasoning |
| --- | --- |
| Component 4: Awareness raising, knowledge management and coordination. |  |
| Output 4.1 Awareness-raising materials and educational curricula are developed and used by a range of national, provincial and local organizations. |  |
| While awareness raising materials related to the impact and management of IAS have been prepared, these have been produced on an ad hoc basis and with a varied effectiveness in reaching the stakeholders at large. Thus, efficient large-scale penetration of IAS related knowledge among the general public, students, farmers and other main stakeholder groups within China appears to be limited. Thus, the baseline IAS awareness levels for the larger proportion of relevant stakeholder groups are considered to be low, including in the project provinces. The lack of awareness for instance among the public results in that IAS are unintentionally brought into the country by travelers and that exotic pets are released into the wild, thereby threatening biodiversity. | The project will, immediately following the signing of the project document, determine the baseline awareness levels for targeted audiences using the KAP methodology in Annex M. An end of project survey will also be undertaken. Building upon the first KAP survey, a knowledge management plan will be designed following the overall C-SAP program Knowledge Management strategy. An integral part of the knowledge management plan will be the development of school curriculums and other educational and awareness raising materials, based on the project developed training materials (output 2.3 and 3.1). The prepared materials will also be used for the design of Massive Open Online Courses (MOOC), which will be made widely available on internet via the IAS Knowledge Management platform (output 4.2). The developed awareness raising materials will be used in public events and at the Public Science Popularization Base in Wenchang and Bishan. Dissemination to the other child-projects under the C-SAP Program is also envisaged. The project will seek to heighten the attention to the IAS problematics in the international arena by organizing an IAS day in connection with the Fifteenth Meeting of the Conference of the Parties to the Convention on Biological Diversity (COP15) in 2020. The event will not only highlight the C-SAP 2 IAS project, but will ensure a full day’s discussions on the topic. More importantly, the buildup to the event will provide for a critical impetus for elevating IAS Management (and the threat IAS poses to biodiversity, economy and livelihoods) to the forefront among relevant ministries and the Chinese Government in general. The side events will be accompanied by a stall area presenting Chinese and international innovations in IAS Management. Finally, best practice learning and knowledge sharing exchange missions will be undertaken to gain first-hand knowledge of how other countries ensures strong coordination in their IAS Management. |
| Output 4.2 A national web-based IAS information and communication platform is established providing a forum for information-sharing and communication on prevention, control and management of IAS in agroecosystems. |  |
| Individual ministries and academic institutions have web-sites where stakeholders can access IAS knowledge related materials including guidelines, manuals, various training materials and educational videos. However, such information is scattered and currently there is not one centralized access point, where interested parties can obtain IAS related information and knowledge products from. Not even a site providing a comprehensive list of useful web-pages and links is available. This makes it difficult for interested stakeholders to obtain the available materials and knowledge products on how to combat IAS encroachments and spread threatening biodiversity in the agroecosystem. | The project will develop an IAS Knowledge Management platform that can act as a clearing-house mechanism for IAS related knowledge. The project will facilitate an agreement between main government institutions, academic institutions, public organizations and other stakeholders to contribute documents and information to the platform. The platform partners will, together, determine the content of the platform and once completed, will populate the platform with the agreed materials and keep it updated on an ongoing and long-term basis. This broad access to an expanded knowledge base will facilitate the knowledge uptake and outreach among practitioners, farmers and other stakeholder groups, on improved IAS Management practices aimed at not only local and national, but also global, benefits. The IAS Knowledge Management platform will have a simple and easy to navigate structure. It will be linked up to the C-SAP Knowledge platform developed under the FAO implemented C-SAP child project, as well as the Biodiversity Knowledge Platform developed under the C-PAR program. |
| Output 4.3 Strengthened engagement in international cooperation on the prevention, control and management of IAS impacts on agrobiodiversity |  |
| Ministry of Ecology and Environment is the lead ministry for biodiversity conservation and the CBD, and international engagements related to the CBD, including IAS falls under the purview of the ministry. The matter of IAS prevention, control and management is not internationally addressed by other ministries and administrations, although it is embedded in their national mandates. Because of this, international cooperation on IAS, between China and other countries, has a narrow focus. | The documenting of the project achievements, particularly from the island of Hainan, and the provision of this information and materials, to senior government officials from MARA, MEE and GACC, for their use in transnational engagements on the topics of IAS prevention, control and management, will not only facilitate bringing IAS issues on the international agenda. Also, the project interventions in prevention, control and management of IAS in Hainan will enable China to showcase a viable example of an island-based approach for IAS Management, which have both national and global environmental benefits. An example that might be of interest to small island states. The project will also provide support to MARA, MEE and GACC in their efforts to establish, where possible, bilateral cooperation agreements related to, for instance, capacity building in China, of people from partner countries or other areas identified in the IAS NSAP directions on improving South-South/North-South cooperation and coordination (output 1.3). |
| Output 4.4 A Program Coordination, Monitoring and Evaluation Plan is developed, adopted and effectively implemented. |  |
| MARA will be responsible for the project. It has a long-standing capacity for implementing international projects including GEF projects, and high standards for monitoring and evaluation. Although less familiar with ensuring gender equality and mainstreaming of women into the project portfolios, the PMO will be guided by the developed Gender Management Plan. | The project’s PMO will effectively support the project steering committee in its overall oversight of the project. The project monitoring and evaluation will be carried out as per the evaluation plans outlined in the project documentation. A high quality of the project’s PIR, APR, QPR and other relevant reports will be ensured. Mid-term Review and Terminal Evaluations will be undertaken timely according to the UNDP rules and procedures. The project will also undertake the overall coordination of the C-SAP program via the C-SAP 2 IAS Project’s Project Management Office (PMO), which will have a Technical Program Advisor attached to ensure the implementation of the developed Program Coordination, Monitoring and Evaluation Plan. The PMO, through the Technical Program Advisor, will provide high quality program reporting and timely program evaluations. |

Outcome 4: Sustainability and impact of project/program results enhanced by effective KM, awareness, M&E and coordination.

Output 4.1 Awareness-raising materials and educational curricula are developed and used at national, provincial and local level.

Intermediate Outcome (Result of the Output): Awareness-raising materials and educational curricula are developed and used nationally, provincially and locally.

- A determining factor for sustainability of the effect from efforts to prevent and control IAS spread, and encroachment is the broad base disseminated knowledge about IAS and the threats they pose on the agro-ecosystems. Recognizing that, the project will aim to propose adequate measures based on the current IAS awareness levels at national, provincial and local level. For that purpose, the baseline awareness levels for targeted audiences using the KAP methodology in Annex M will be determined within the first six months of the project. A second survey will be undertaken by the end of the project. Following the first KAP survey the project’s knowledge management plan will be developed. The knowledge management plan will be in line with the overall C-SAP program Knowledge Management strategy and will among other focus on the development of awareness raising materials, school curriculums and similar educational materials, based on the project developed training materials (output 2.3 and 3.1). These developed materials will then be used in schools and made accessible for the public and interested stakeholders mainly through the IAS Knowledge Management platform (output 4.2), but also using other dissemination channels.

- The project will also create Massive Open Online Courses (MOOC) based on the developed training materials (output 2.3 and 3.1) and the provided trainings. The trainers will, in addition to provide face-to-face trainings (output 2.3 and 3.1), have their trainings and lectures video recorded so that they can be uploaded along the training materials for interested parties to do self-study. The MOOCs containing the online lectures etc. will also have course tests, which needs to be passed to obtain a MOOC certificate. Within the MOOC there will be links to shorter practical training videos for on the ground implementation of IAS Management, developed as part of the projects trainings activities (output 2.3 and 3.1). The MOOC will be accessible via the IAS Knowledge Management Platform (output 4.2), and links to the C-SAP FAO lead C-SAP Knowledge Platform and the C-PAR Biodiversity Knowledge Platform and e-learning will be ensured to enable an as broad dissemination of the MOOCs as possible.

- The developed awareness raising materials will also be used in public events and at the Public Science Popularization Base in Hulu and Longfei (output 3.2) and will be disseminated to the other child-projects under the C-SAP Program. The project designed activities for IAS awareness raising will be delivered to targeted audiences and will potentially have a much larger and expanded outreach. The project prepared IAS knowledge packages, curricula and awareness raising materials could be further used and replicated for an extended and long-term effect resulting in additional environmental (national/global), economic and livelihood benefits.

- The project will seek to heighten the attention to the IAS problematics in the international arena by organizing an IAS day in connection with the Fifteenth Meeting of the Conference of the Parties to the Convention on Biological Diversity (COP15) in 2020. The event will not only highlight the C-SAP 2 IAS project, but will ensure a full day’s discussions on the topic. The side events will be accompanied by a stall area presenting Chinese and international innovations in IAS Management. Furthermore, the event, and COP15, will act as a catalyst for mainstreaming IAS Management among relevant ministries and the Chinese Government.

Indicative Activities under Output 4.1. include:

4.1.1. Undertake the knowledge, attitude and practices (KAP) survey (at project start and end), following the guidance provided in Annex M, on the IAS impact on ecology and economy and main approaches in IAS Management. The initial KAP survey will be undertaken as soon as possible after the project document signing. (MARA-Lead; MEE-Support; GACC-Support)

4.1.2. Develop the projects knowledge management action plan, based on the baseline KAP survey and the knowledge management strategy for the C-SAP program developed under the FAO child project. (MARA-Lead)

4.1.3. Prepare IAS education and awareness-raising materials for use by 1) middle schools 2) primary schools 3) farmers 4) businesses and 5) the public by adapting and tailor the project developed training materials (output 2.3 and 3.1) to the different target groups, making them more accessible.

4.1.3a. Prepare MARA IAS education and awareness-raising materials (MARA-Lead)

4.1.3b. Prepare MEE IAS education and awareness-raising materials (MEE-Lead)

4.1.3c. Prepare GACC IAS education and awareness-raising materials (GACC-Lead)

4.1.4 Develop and publicize Massive Open Online Courses (MOOC). Based on the developed trainings and materials, project trainers will prepare video recordings of their trainings etc. and these, including the training materials, will be packaged into MOOCs. These will be accessible online via the project IAS Knowledge Platform (output 4.2) and linked to the C-SAP and C-PAR Biodiversity Knowledge Platforms, to ensure a broad dissemination to enable interested stakeholder to increase their understanding and practical knowledge regarding IAS Management.

4.1.4a Develop and publicize MARA related Massive Open Online Courses (MOOC) (MARA-Lead).

4.1.4b Develop and publicize MEE related Massive Open Online Courses (MOOC) (MEE-Lead).

4.1.4c Develop and publicize GACC related Massive Open Online Courses (MOOC) (GACC-Lead).

4.1.5. Organize publicity and awareness events at national, provincial and local levels, by using project developed information materials (Activity 4.1.3.), as for instance part of international, national and local “day” events, such as the “World Environment Day” and “International Day for Biological Diversity” or in connection with long-term exhibitions at for instance city zoos and botanical gardens. This activity will also disseminate developed materials, trainings etc. to the relevant departments in the provinces and counties working with the C-SAP program, via its other child-projects, to broaden the scope, impact and benefits of the developed educational and public awareness materials (Activity 2.3.1., 3.1.1. and 4.1.3.). The use of the provided materials will be facilitated by the active promotion by MARA, MEE and GACC etc. The activity will further engage local middle and primary schools, by engaging them in school project exercises on IAS identification, mapping of IAS distribution in the local area, using the project developed IAS APP. The project will also raise public/visitors’ awareness on IAS and IAS Management at the IAS Management Science Base/ Public Science Popularization Base in Wenchang and Bishan (Activity 3.2.3.), using the project developed MOOCs and the awareness raising materials. Finally, the project will, under this activity, use mass and social media to increase the public awareness of the negative harmful effects of IAS on the national/global environment and the economy (MARA, MEE and GACC co-lead).

4.1.6. Organize a full day IAS side event in connection with the Fifteenth Meeting of the Conference of the Parties to the Convention on Biological Diversity (COP15) in 2020, hosted by China. The project will support a full day of side-events focusing on key aspects of IAS Management. The side events will be accompanied by a stall area presenting Chinese and international innovations in IAS Management. (Mara-Lead; MEE-Support; GACC-Support)

4.1.7 Best practice learning and knowledge sharing exchange missions. The project will support MARA, MEE and GACC in obtaining first-hand knowledge of best practice in IAS Management related to IAS invasion in the agroecosystems, preventing IAS from exiting entry ports and integrating ecology and biodiversity concerns into the national IAS Management. As part of this, each of the project partners will tailor specific missions to one or more select countries which have, and are implementing, high standards of IAS related prevention, control and management in the respective areas of concern. Obtaining information and good practices for inter-agency coordination and collaboration will be a key part of the different missions.

4.1.7a MARA best practice learning and knowledge sharing exchange missions (MARA-Lead)

4.1.7b MEE best practice learning and knowledge sharing exchange missions (MEE-Lead)

4.1.7c GACC best practice learning and knowledge sharing exchange missions (GACC-Lead)

Output 4.2 A national web-based IAS information and communication platform is established providing a forum for information-sharing and communication on prevention, control and management of IAS in agroecosystems.

Intermediate Outcome (Result of the Output): A national web-based IAS Knowledge Management platform is established and maintained.

- An important component of the project’s designed IAS Knowledge Management Plan is the development of an IAS Knowledge Management platform, which will be created under this output. The IAS Knowledge Management platform is a main online tool for IAS awareness raising and will act as a clearing-house mechanism for IAS related knowledge. A bearing element in this regard will be the project facilitated agreement between main government institutions, academic institutions, public organizations and other stakeholders to become platform partners. The platform partners, together with the National IAS Coordination Group, will identify the platform’s main content areas. As part of this, discussions with experts working on different data-systems will also be held, to identify different easy to implement technical options, which will facilitate data transfer from existing systems and the project establish platform

- Following the platform design and development, the partners will populate the platform with agreed materials and will keep it updated on an ongoing and long-term basis. To ensure user-friendly interface, the platform will have a simple and easy to navigate structure and will be linked up to the C-SAP Knowledge platform developed under the FAO implemented C-SAP child project.

- The popularizing of the IAS Knowledge Management platform will be a critical step for the success of the project’s awareness raising, educational and training outreach, as the platform will be the main vehicle from, which these materials, including the MOOCs are to be accessed. Because of this, a specific strategy for its roll-out will be developed. The impact of the IAS Knowledge Management platform is expected to be ground breaking and a turning point in the efforts to raise awareness on IAS in China, facilitating a broad knowledge uptake and outreach among practitioners, farmers and other stakeholder groups, thus expanding the implementation of improved IAS Management practices beyond the project direct beneficiaries and providing for increased local, national, and global benefits. To ensure broad dissemination and access links will be made to the C-SAP Knowledge Platform developed and coordinated under the C-SAP FAO child project, as well as the C-PAR Biodiversity Knowledge Platform.

Indicative Activities under Output 4.2. include:

4.2.1. Design the IAS Knowledge Management platform. Under this activity the project will establish a Cooperation Agreement between government institutions, academic institutions, public organizations and other stakeholders for voluntary (and for free) contributing documents and information to the web-based IAS Knowledge Management platform. The Cooperation Agreement partners in collaboration with the National IAS Coordination Group will determine the content of the web-based IAS Knowledge Management platform, ensuring that the platform will act as an IAS Management clearing house containing the main information related to IAS Management such as:

- Legislation

- Strategies and action plans

- Research

- Trainings

- Education materials

- Videos

- Links to sources

- Discussion forum (topic separated)

- Events

The Knowledge Management Platform design will be based on the identified content requirements. In addition, related website protocols for guiding the long-term functioning and management of the IAS Knowledge Management platform will be developed. (MARA-Lead; MEE-Support; GACC-Support)

4.2.2. House and populate the IAS Knowledge Management Platform. The decision as to where the platform is to be housed, and issues related to the long long-term maintenance responsibilities will be determined within the first year of the project. In addition, following the developed management protocols (Activity 4.2.1.) the assigned focal points from the Cooperation Agreement partners will regular upload relevant and required information to the platform. The web-based IAS Knowledge Management platform will be linked to the C-SAP program website and knowledge platform developed under the FAO child project, as well as the C-PAR Biodiversity Knowledge Platform. (MARA-Lead; MEE-Support; GACC-Support)

4.2.3 Popularize the IAS Knowledge Management platform among IAS Management stakeholders, including government institutions and their provincial and county departments, academia, NGOs/CSOs, farmers and businesses, through MARA, MEE and GACC formal and informal networks, including social media. Feedback on the IAS Knowledge Management platform will be sought from the users, on its practicality so as to obtain suggestions for platform improvements with the aim to making it more user friendly and useful. (MARA-Lead; MEE-Support; GACC-Support)

Output 4.3 Strengthened engagement in international cooperation on the prevention, control and management of IAS impacts on agrobiodiversity.

Intermediate Outcome (Result of the Output): China engages in agreements on prevention, control and management of IAS impacts on agrobiodiversity internationally.

- With the spread of IAS through international and national trade routes, as stowaways and hitchhikers, the improved prevention, control and management of IAS in China is not only a national issue but also a global one, where a reduction of the IAS threat in China will decrease the likelihood of IAS being spread to other countries (through export) and vice versa. Thus, the need for international integration in the efforts to prevent and control IAS is there and will only be growing in the future. Strengthened capacity for bringing IAS on the international agenda is another area where the project could add value. Documenting and using the project’s approaches and achievements in Hainan, being and island and the main example, the project will develop documentation that can be used by senior government officials from MARA, MEE and GACC, in international meetings, to, where deemed appropriate, promote the Chinese approach in IAS prevention, control and management, as well as bring the IAS issues on the agenda or make them part of the discussions. Such discussions will also be an important component of the planned best practice learning and knowledge sharing exchange missions.

- The project will also provide support to MARA, MEE and GACC in their efforts to establish, where possible, bilateral cooperation agreements related, for instance to capacity building in China of people from partner countries or other areas identified in the IAS NSAP 2021-2030 directions on improving South-South/North-South cooperation and coordination (output 1.3).

Indicative Activities under Output 4.3. include:

4.3.1.  Support China’s advocating IAS Management (with Hainan as the main example) in international settings and meetings, via China’s South-South cooperation rollout under the Belt and Road Initiative (BRI), the "Plant Protection Alliance", the China-Africa Cooperation Agreement and China’s involvement with the ASEAN countries -  aim at having IAS Management included in joint agreements, thus ensuring a broader cooperation on prevention, control and management IAS within and outside the region. (MARA-Lead; MEE-Support; GACC-Support)

4.3.2. Support China’s bilateral IAS partnership agreements on IAS Management activities and training programs, including, for instance, updating of IAS Management systems in particular with regard to that IAS do not exit the country of origin, or other issues identified in the IAS NSAP such as directions on improving South-South/North-South cooperation and coordination (output 1.3). (MARA-Lead; MEE-Support; GACC-Support)

Output 4.4 A Program Coordination, Monitoring and Evaluation Plan is developed, adopted and effectively implemented.

Intermediate Outcome (Result of the Output): Project is implemented effectively and timely

- The day to day management will be carried out by the Project Management Office (PMO) ensuring effective implementation, monitoring and evaluation, as well as the coordination between the C-SAP program’s five child projects. The PMO will ensure that gender mainstreaming and SESP requirements are met, as part of the project and program planning, implementation, monitoring and evaluation. The PMO’s M&E officer will aside from the regular project and program monitoring and evaluation tasks, act as the focal point for monitoring and addressing any emerging gender concerns and safeguards issues, occurring during project/program implementation, as well as manage the projects established grievance mechanism. Monitoring and evaluation activities will include the regular review of the project and program results framework and their underlying indicators, annual work plans and budgets and the generation of monitoring and progress reports.

- Regular Project Steering Committee meetings, including the projects inception meeting, will be held to provide overall oversight and guidance and ensure that the main project stakeholders are involved in the project’s approval processes. Terms of Reference for the steering committees are included in Annex C (see also Section VIII: Governance and Management Arrangements).  The PMO will also coordinate the hosting of the C-SAP Program inception workshop and subsequent Program Steering Committee meetings, which will be held on a rotational basis between the five C-SAP child projects.  The project and program inception workshops will be held within three months of project document signing and will provide opportunity for verification of stakeholder’s roles and responsibilities, agree on the multiyear workplans, confirm the results frameworks, as well as, review and confirm any project and program related agreements, including Letters of Agreements (LOAs).

- The project will conduct a Mid-term Review (MTR) and Terminal Evaluation (TE) to take stock of the implementation process, and (at mid-term) to alert towards potential issues affecting the positive outcome of the project, as well as formulate possible adaptive management responses to these, to ensure overall implementation success. In addition to the project’s evaluations, a Program Synthesis will be performed at mid-term and the end of the project. The Program Synthesis will review the performance of all of the C-SAP’s five child projects. To ensure a timely program review, the PMO will coordinate the planning of the individual MTR’s and TE’s. The Program Synthesis’ will be managed by the PMO, through a combined term of reference (with the C-SAP 2 IAS Project) in which the consultancy team will be responsible for preparing individual reports for both the project evaluation and the Program Synthesis.

Indicative Activities under Output 4.4. include:

4.4.1. Hold program inception workshops, within 3 month of project document signing, as well as prepare inception report according to the UNDP/GEF rules and regulations. During the workshop stakeholders will review and agree on the program results framework, workplans and provide guidance for initiating the implementation of the program. Furthermore, the Program Coordination, Monitoring and Evaluation Plan will be finalized and agreed upon. (MARA-Lead)

4.4.2. Hold project inception workshops, within 3 month of project document signing, as well as prepare inception report according to the UNDP/GEF rules and regulations. During the workshop stakeholders will review and agree on the C-SAP 2 IAS projects results framework, workplan and activity set etc. and provide guidance for initiating the implementation of the project. In addition, internal management arrangements and the signed LOA will be re-confirmed. (MARA-Lead; MEE-Support; GACC-Support)

4.4.3. Prepare C-SAP Program annual reports and other relevant project/program reporting, including final reports, as well as undertake C-SAP Program regular monitoring and ensure adaptive management of the program. A template for the annual program report will be developed in year 1 of the project. (MARA-Lead; MEE-Support; GACC-Support)

4.4.4. Prepare C-SAP 2 IAS project annual reports, PIR and other relevant project/program reporting, including final reports, as well as undertake C-SAP 2 IAS project regular monitoring and ensure adaptive management of the project (MARA-Lead; MEE-Support; GACC-Support)

4.4.5. Procure and support an independent midterm review of the project and program, according to UNDP and GEF guidelines. (MARA-Lead; MEE-Support; GACC-Support)

4.4.6. Procure and support an independent terminal evaluation of the project and program, according to UNDP and GEF guidelines. (MARA-Lead; MEE-Support; GACC-Support)

4.4.7. Monitor and report on the implementation of the C-SAP 2 IAS project’s gender mainstreaming action plan (MARA-Lead)

4.4.8. Hold C-SAP 2 IAS project Steering Committee meetings annually to review the project progress and ensure that the project is time relevant. The PSC meeting will rotate between MARA, MEE and GACC (MARA-Lead; MEE-Support; GACC-Support)

4.4.9. Organize annual C-SAP program steering committee meetings and host one of them to report on the progress of the project, share lessons learned and advocate new tools and practices, which would be relevant for stakeholders in other C-SAP child projects. (MARA-Lead)

Component 4:  Awareness raising, knowledge management and coordination: Total Cost: $ 6,352,133; GEF project grant requested: $ 856,913; Co-financing: $ 5,495,220

Partnerships:

- The project is one of five child projects under the government’s C-SAP Program, which objective is to support the implementation of the Sustainable Development Goals and China’s National Plan for Sustainable Development of Agriculture (2015-2030) by a) piloting and scaling up effective policy and investment measures to mainstream in-situ conservation and sustainable use of globally important genetic resources for food and agriculture, b) improving the prevention, control and management of IAS, c) conserving and enhancing carbon stock and promoting evidence-based and climate-smart conservation of grassland ecosystems, and d) collaborative innovation in climate change and biodiversity from the aspects of policy, mechanism, knowledge sharing and partnerships. As described in the section III Strategy, this project will make a substantive contribution to help the C-SAP program address program barriers and will contribute results directly to the C-SAP programmatic results framework (see Table 2), as well as collaborating with the other four child projects to support coordinated knowledge management and sharing of lessons learned. The project will work closely with the other child projects, and in particular the UNDP-supported C-SAP 3 project in Hainan, sharing project approaches for IAS Management, lessons learned and knowledge materials from this project.

- The project in its implementation will rely on the strong partnership between the project Implementing Agency MARA and the two Co-Implementing Partners MEE/FECO and GACC/CAIQ. In a coordinated effort the partners will implement specific but interrelated parts of the project, which will promote a more integrated and cross-sectoral approach to IAS Management in China. Collaboration within and between different entities in government will be enhanced through the national, provincial and county IAS Management Coordinating Groups, which will bring together lead government managers and experts. Partnerships and collaboration, particularly with other stakeholder groups outside government, will be strengthened through consultations, networking, inter-sectoral platforms, training, technical advice, information sharing and joint strategic planning and implementation to ensure the delivery and achievement of project goals and objectives.

- Component 1 will under output 1.1 establish national, provincial and county IAS Management Coordinating Groups, which will play a central role in the projects implementation, as they will be engaged in and oversee (technically) many of the project’s activities. The component will foster an active stakeholder engagement among the key agencies engaged in IAS Management regulatory and strategic planning work. The National IAS Management Coordinating Groups will guide implementation processes for output 1.2 on revising ministries and administrations regulations framework and the development/revision of risk assessment, early warning, and rapid response guidelines.  The national and provincial Coordinating Groups will play a central role in the development of national and provincial IAS Strategic Action Plans under output 1.3, which will be developed through expert sub-groups and active involvement from representative stakeholder groups. The public will also be involved through various social media engagements. The national and provincial Coordinating Groups will also be a main driver for the development of sectoral Implementation Plans (at ministry and provincial department levels) undertaken under output 1.4. For activities (particularly related to the provincial IAS Strategy and Action Plan and the sectoral/department Implementation Plans) in Hainan, efforts will be made to include representatives from the C-SAP 3 Hainan project to foster synergies and cross fertilization.

- Component 2 of the project focuses on the strengthening of IAS Management frameworks and institutional capacity. Under output 2.1 Hainan Provincial IAS Coordination Group will oversee the development of methodologies for biodiversity risk assessment, early warning and rapid response for Hainan undertaken by lead experts. The project will under this component develop the main training materials based on latest research, best national and international practices and standards aimed at 1) minimizing the risk of IAS entering into China from ports (output 2.2) and 2) reducing threats from IAS to the agrobiodiversity, including traditional varieties in the agroecosystems (output2.3). Particularly the training development under output 2.3 will involve consultations and feedback from training target groups. Feedback from the training implementation (under the same outputs) will also be used in refining the trainings over time. Social media will in this regard be used to solicit feedback and input from a broader audience. For activities (particularly in regard to the provision of training) will to the extent possible include representatives from the other C-SAP Program child projects to foster synergies and cross fertilization, with a particular reference to the C-SAP 3 Hainan project.

- Under Component 3’s output 3.1, parts of the output 2.3 developed trainings will be adapted for the use of training of farmers, farmer cooperatives, agrobusinesses and other stakeholder groups. The adaptation will be based on farmer consultations and input from the county IAS Management Coordination Groups, and for the delivery of trainings, it will be ensured that at least 50% of the trainees are women and at least 20% are younger than 35. The trainings will form the base for the long-term, on the ground, implementation of IAS Management techniques and interventions will be undertaken by the local stakeholders in the project’s targeted agricultural landscapes (output 3.2 and 3.4). Output 3.3 will involve a broad range of local stakeholders in the collection of data on the distribution of key IAS from the “First Priority” IAS species list. Local farmers etc. will also be involved in the development of management plans for the project’s areas and subsequent implementation done under output 3.2 and 3.4. As for activities under component 3, and particularly in regard to the provision of training, the project will to the extent possible include representatives from the other C-SAP Program child projects to foster synergies and cross fertilization, with a particular reference to the C-SAP 3 Hainan project.

- In Component 4 the project will setup an IAS Knowledge Management platform, which is to be linked to the C-SAP Program Knowledge Management platform developed under the C-SAP 1 FAO project. The IAS platform will act as a clearing house where training materials, videos, publications and other knowledge management materials will be collected through input from a group of collaborating government and academic institutions. The IAS platform will be public accessible and would be one of the means through, which project trainings and material are shared with the other child projects of the C-SAP program, as well as any other interested party. Under this component the project will hold various project meetings for presenting project results and updating stakeholders (UNDP, governments, NGOs, scientists etc.) and exchange experience among child projects and participants.

- The Project Steering Committee and the Project Management Office will play a key role in ensuring that these partnerships work effectively. UNDP, as both the GEF Implementing Agency and a development partner to MARA, MEE and GACC, will play a central role in the oversight of these partnership mechanisms, and will liaise at the highest level with government to ensure that the project fully delivers against its work plan and targets and is well integrated with the C-SAP Program as a whole. The UNDP Country Office (CO) will assign a program officer for project oversight, and the UNDP-GEF Regional Technical Advisor located in Bangkok will also provide technical support to the CO for implementation, monitoring and evaluation of the project.

- For additional information on project stakeholders’ engagement under the different components see Annex E and Annex V

- The project will contribute towards the UNDP Country Programme Outcome 2. “More people enjoy a cleaner, healthier environment as a result of improved environmental protection and sustainable green growth”. The project will build on UNDP’s long-term partnership with MARA which has included a number of successful related projects, including the GEF funded projects on “Market transformation of energy-efficient bricks and rural buildings”, “Conservation and sustainable utilization of wild relatives of crops” and “Energy conservation and pollution control in township and village enterprises”, as well as other non-GEF UNDP projects. It also builds of the long term partnership UNDP has with MEE/FECO which include the long running GEF project China Biodiversity Partnership and Framework for Action (CBPF) and the recently GEF approved China's Protected Area System Reform (C-PAR) program, as well as with GACC with which UNDP has implemented a sub-set of initiatives among other related to the phaseout of Ozone Depleting Substances under the Montreal Protocol.

- Table 7 below lists the main ongoing strategies and plans that offer strong linkage with the project and shows their connections with the components and outputs of this project.

Table 7. Intersection of Related Initiatives with Project Outputs

| Related Initiatives | Intersections with Project Outputs |  |  |  |
| --- | --- | --- | --- | --- |
|  | Comp. 1 | Comp. 2 | Comp. 3 | Comp. 4 |
| National Biodiversity Conservation Strategy and Action Plan (NBSAP 2011-2030) | Output 1.2; Output 1.3; | Output 2.1; Output 2.3 | Output 3.1 | Output 4.1 |
| National Agricultural Sustainable Development Plan (2015-2030) | Output 1.2; | Output 2.1; Output 2.3 | Output 3.1 | Output 4.1 |
| Environment 13th five-year plan | Output 1.2; | Output 2.1; |  |  |
| Agriculture 13th five-year plan | Output 1.2; | Output 2.1; |  |  |
| Hainan Biodiversity Conservation Strategy and Action Plan (2014-2030) | Output 1.2; | Output 2.1; Output 2.3 | Output 3.1 | Output 4.1 |
| Chongqing Biodiversity Strategy and Action Plan | Output 1.2; | Output 2.1; Output 2.3 | Output 3.1 | Output 4.1 |

Risks and Assumptions:

- Table 8 lists the identified project risks, their overall rating and the mitigation actions required during project implementation. The assumptions on which these project risks depend are listed in the project’s Theory of Change (Figure 2), with assumptions applied to the project indicators also described in the project Results Framework (Section VI). Risks are only shown if their rating is considered to be Moderate or High, with the exception of risks identified in the Social and Environmental Screening Procedure (SESP, Annex D) which are all described.  As per standard UNDP requirements, the Project Coordinator will monitor risks quarterly and report on the status of risks to the UNDP Country Office. The UNDP Country Office will record progress in the UNDP ATLAS risk log.  Risks will be reported as critical when the impact and probability are high. Management responses to critical risks will also be reported to the GEF in the annual PIR.

- The SESP was finalized during project preparation, as required by UNDP’s Social and Environmental Standards (SES). The SESP identified seven risks for this project that could have potential negative impacts in the absence of safeguards, two of these risks were rated as low and five rated as moderate. Therefore, the overall SESP risk categorization for the project is Moderate. The following safeguards are triggered: Human Rights; Gender Equality and Women’s Empowerment; Climate Change Mitigation and Adaptation; Community Health, Safety and Working Conditions; Indigenous Peoples and Pollution Prevention and Resource Efficiency.

- Overall, the project is expected to result in major long-term positive impacts for the protection of agrobiodiversity, including traditional varieties, as well as having socio-economic benefits to China. It will do this through a more effective Government IAS Management coordination and cooperation and via the participatory engagement of rural communities in implementation of IAS control and management, thereby improving benefits from a reduced threat from IAS to the local ecology and economy. Through the close monitoring of the identified SESP risks the project aims to closely manage, avoid or mitigate all the indicated social and environmental risks.

- In addition, a project-level Grievance Redress Mechanism (GRM) will be established upon project inception and managed by the PMO. The GRM will provide for a “first line” of response to stakeholder concerns that have not been prevented by proactive stakeholder engagement.

Table 8. Description of project risks, impact and probability and mitigation measures

(NB. Only risks with a rating of moderate or above are listed. In addition, all risks identified from the SESP are included.)

| Description of Risk | Type | Impact and Probability | Mitigation Measures | Owner |
| --- | --- | --- | --- | --- |
| Brief description of the risk | Category of risk | Potential effect on the project | What actions have been/will be taken to counter this risk | Person appointed to monitor this risk |
| Risk 1: The National Government has a limited interest in maintaining the financial support for IAS protection, control and management into the short-term and long-term budget planning. | Institutional | P=2, I=3 MODERATE | The Government of China is recognizing the vast impact of IAS and it is actively seeking to address the direct impacts of IAS as well as the underlying barriers hindering an optimized IAS Management within China. IAS Management has been included as a priority area under several key strategic document including the National Biodiversity Strategy and Action Plan, the National Agricultural Sustainable Development Plan as well as the 13th five-year plans of both environment and agriculture. The project will address a subset of nationally recognized barriers, which currently are hindering an effective response to the threats posed by IAS. As part of this, the Project Coordinator will follow the project implementation including the progress towards the results framework, where government financial support is one of the project indicators. Should government interest in maintaining financial support towards IAS or the commitments to the project, the PM and the National Project Director will engage as relevant, and where needed through the Project Steering Committee. | Project Coordinator |
| Risk 2: Provincial and county level governments do not see the relevance of establishing IAS offices and/or coordination bodies within their jurisdiction. | Institutional | P=2, I=3 MODERATE | As noted above the prevention control and management is a concern for China at both national and perhaps more so at provincial and county levels. IAS Management are, as also noted, part of key strategic document and plans where particularly increasing the provincial capacity for monitoring and early warning and rapid response capabilities are ranked high. As part of this is the need for effective implementation of management responses to IAS encroachment, which by and large is relying upon cross sectoral cooperation. As cross sectoral collaboration through the IAS Management Coordinating groups are a central part of the project implementation their establishment and effective running is of the outmost importance for the project’s success. The Project Coordinator with the relevant counterparts in the cases where progress is not as expected. In this regard the PM will, where needed, seek interventions from the National Project Director and/or the project Steering Committee. | Project Coordinator |
| Risk 3: The review and approval processes for changes in the regulatory framework is prolonged due to internal and other bureaucratic processes. | Operational | P=3, I=2 MODERATE | The progress on obtaining the approvals (and the underlying work of document preparation) will be reviewed as part of the regular projects monitoring and reporting. The Project Coordinator will where appropriate engage with relevant senior government officials engaged with approval processes ensure that the approvals needed are timely provided. Where needed the Project Coordinator will engage the National Project Director and/or the project Steering Committee. | Project Coordinator |
| Risks 4: Project activities are not deemed interesting/ relevant by direct beneficiaries who will refrain from participating | Operational | P=2, I=3 MODERATE | While the project will be providing training, which are highly relevant for local direct beneficiaries, including local farmers, farming cooperatives and agrobusinesses, local stakeholders might not engage. The main reason for this would be that the trainings are not organized in a way which are accommodating to farmers etc. Because of this the project will place trainings outside, for instance, planting and harvesting times and other “busy” seasons within the agricultural year. Also, trainings would be provided, where possible, in such a way that they impact the least on day to day activities. For instance, by having half day trainings to accommodate young women with school children. In addition, the types of trainings and the expected benefits of the trainings to the local stakeholders will be publicized, during the build up to the trainings. Furthermore, highlighting trainings in local media (and through social media) will be used to heighten interests in the trainings. | Project Coordinator |
| Risks from Social and Environmental Screening Procedure (Annex D C-SAP 2) |  |  |  |  |  |
| SESP Risk 1: People do not have opportunity to have their grievance heard. | Human Rights | P = 1, I = 3 LOW | The project will set up its own grievance mechanism and the projects PMO will act as a “door way” for any potential grievance raised by any of the project stakeholders or direct or indirect beneficiaries. Equally important is it that there is already a grievance system within China, where for instance village issues/grievances can/are brought up at the village committee meetings or are brought up at county meetings etc. In addition, UNDP-China has since 2015 had its grievance mechanism in accordance with UNDP rules and procedures, where people can bring their complaints if they feel that national grievance system has not adequately addressed the raised concern. | Project Coordinator |
| SESP Risk 2: Efforts to halt/minimize the threats of IAS to agrobiodiversity, including traditional varieties and GRFA, do not materialize or are insufficient, leading to reduced productivity of land impacting on local farmers livelihoods. | Human Rights/ Displacement and Resettlement/ Ethnic Minorities | P = 1, I = 4 MODERATE | As noted in the project documentation, the Government of China is recognizing the vast impact of IAS and it has among other requested GEF for support to expedite its process in this area. The current project will address a subset of nationally recognized barriers, which currently are hindering an effective response to the threats posed by IAS. Part of the current project interventions are the training of 6,000 farmers in IAS Management, including vegetation replacement techniques, biological control and low volume pesticides management, all aimed at reducing the immediate impact on farmers’ fields and crops. The trainings and other project interventions also focus on combatting IAS in the broader environment so as to reduce the overall re-colonization pressures on villager’s fields and pasture lands. Also, the project has in its approach a clear gender focus aimed at ensuring gender equality and the mainstreaming of women, as mentioned in the SESP section on how the project is likely to improve gender equality and women’s empowerment. In this regard the projects Gender Mainstreaming Plan will be a main instrument and guide. | Project Coordinator |
| SESP Risk 3: Gender based discrimination related to access to opportunities and benefits remains unaltered. | Gender Equality and Women’s Empowerment | P = 2, I = 3 MODERATE | While China is on a path towards gender equality and women’s empowerment, China is still struggling with gender imbalance. To ensure that the project adequately addresses this, it has during the PPG phase undertaken a gender analysis and developed a Gender Mainstreaming Plan (Annex F) which will be a guiding document in the project implementation. As mentioned in the above section on how the project is likely to improve gender equality and women’s empowerment the project’s Gender Mainstreaming Plan will ensure that project related application processes are without gender bias and engage with women in its local level activities including farmers trainings with the aim of having 50% or more of the project beneficiaries being women. The project’s gender equality and women’s empowerment monitoring will follow the project’s performance in this regard. | Project Coordinator |
| SESP Risk 4: IAS prevention, control and management efforts will have a negative impact on endangered species, critical habitats and/or environmentally sensitive areas | The project will conduct targeted IAS eradication, control and management activities at IAS degraded agricultural landscapes and the removal or reduction of these IAS (and the methods used) could result in that ecological function/structure/ processes change locally in the project targeted agricultural landscapes, affect endangered species house within these areas or facilitate an unintentional spread of IAS. | P = 1, I = 4 MODERATE | With the project’s aim to minimize the threat from Alligator weed, Golden apple snail and Mile-a-minute to agrobiodiversity. It will do this by providing expert led trainings in tested IAS Management techniques, which are to be implemented in the project targeted agricultural landscapes. Local and county level management plans will be developed through a participatory process, relying on latest research and expert input. The projects guidelines and methodologies will also provide guidance to the on-the-ground implementation. All aimed at ensuring an IAS reduction with no or limited impact to the agrobiodiversity the project is seeking to protect. While, instance with the removal of the IAS, has the potential of causing loss in vegetation cover, disturbing the topsoil, change local habitat and the ecosystem services, including carbon sequestration, as well as leave the area prone for a reintroduction of new or existing IAS, the project will engage in appropriate counter measure to minimize these effects. For instance, the use of vegetation replacement techniques using cash crops or livelihoods facilitating vegetation such as hybrid elephant grass Pennisetum sinese and nectar producing plant Sophora davidii, which are suited to local conditions, can be used as countermeasures, particularly on abandoned/fallow lands. On productive agricultural lands the eradication of the IAS will be followed up by the planting of cash crops, often in a rotational production system, limiting the period with bare top soil and minimizing the time for a potential reinvasion of IAS. The use of IAS specific biological agents will also be used to combat IAS infestation within the productive landscape. A key concern with regard to the productive land is to control the IAS in the areas bordering the fields etc. as IAS in these areas is a constant source for re-entry into the fields by the IAS. Addressing this issue, is one of the main components of the local management planning processes. Here vegetation replacement techniques can be used, using local plants, which are found to be able to out-compete the IAS by hindering germination and vegetative spread. In this regard, vegetative replacement could be used together with biological control agents and/or a chemical defense. With regard to the use of chemicals the project will be promoting a “low-chemical” techniques, as part of its overall strategic approach benefitting not only the environment, but which will have positive health implications as well. Also, the projects coordination and systematic work is mainly designed to ensure a more holistic approach where ministries and institutions, in a cross sectoral manner, jointly engage in IAS Management to ensure optimized and cost-effective interventions. All put together it is not envisaged that there will be any negative impacts on the environment or components hereof, and with the planned reduction of the IAS threat in the project targeted agricultural landscape there would be an overall positive impact. Negative impacts might occur, if the projects interventions fail to deliver as expected and therefore does not halt the IAS encroachment as anticipated. But this would be highly doubtful as the techniques to be used have been proven to be successful in tests in other areas in China, and project’s trainings and planning processes are supported by national experts from the leading institutions working with IAS in China. | Project Coordinator |
| SESP Risk 5: Local communities are negatively impacted through the use of pesticides to eradicate IAS invasions. | Community Health, Safety and Working Conditions/ Pollution Prevention and Resource Efficiency | P = 1, I = 4 MODERATE | The project is to address this in various ways, using best national and international practices. Part of the project’s demonstrations is to introduce together with local farmers new practices in IAS Management. These include the use of biological agents, and equally important the use of specific and optimized dosages of pesticides aimed at a more target specific delivery as well as minimizing the amount of pesticides used. Furthermore, safety measures in connection with handling and use, such as storage and waste disposal, use of protective gear and weather conditions suitable for spraying etc., will be a key part of the provided farmers training. A step, which will have much broader impact, as much of the pesticides used in IAS Management are also used for other types of pest and weed control. In addition, techniques such as vegetation replacement will suppress IAS and hinder IAS recolonization in the localized areas where these practices are being implemented, providing for a pesticide free alternative. Also, the project will demonstrate and use biological agents in controlling, for instance Alligator weed. The overall project aim is to prevent, control and manage IAS thereby reducing the threat of IAS on traditional varieties, and agrobiodiversity in general. Meaning that fewer new areas will be invaded by IAS in the future and areas currently affected by IAS will experience a decreased impact from IAS. A key project component in this regard is the establishment of the IAS knowledge platform, which among other things identify and collect best international practices for the prevention, control and management of IAS, thereby broadening the potential non-pesticide options available to China, as well as options for effective low-level usage of chemicals where other options are not available and or feasible. Finally, in line with UNDP guidance the project will not use products that fall in Classes Ia (extremely hazardous) and Ib (highly hazardous) of the World Health Organization Recommended Classification of Pesticides by Hazard WHO Class II (moderately hazardous) chemicals will not be used. Chemicals will also be handled, stored, applied and disposed of in accordance with international good practice such as the FAO International Code of Conduct on the Distribution and Use of Pesticides | Project Coordinator |
| SESP Risk 6: Local communities and minority communities are negatively impacted by strengthened IAS prevention, control and management efforts. | Ethnic Minorities | P = 1, I = 2 LOW | The project will work with local farmers, including those from minority communities on safe product handling. Also, the project’s activities to be implemented with or by local communities will be developed in a participatory manner, taking local concerns (and conditions) into account in the design and implementation of identified IAS Management actions. The engagement of local farmers, including ethnic minorities representatives, will provide for an important feedback loop to ensure that the on the ground intervention within the project targeted agricultural landscapes a as optimal as possible in design and execution. In addition, the overall project aim is to prevent, control and manage IAS thereby reducing the threat of IAS on traditional varieties and GRFA, as well as agrobiodiversity. Meaning that fewer new areas will be invaded by IAS in the future and in areas currently affected by IAS will experience a decrease in their impact areas. Compared to the business as usual scenario the project intervention will overall bring about an improvement in local livelihoods within local communities, including those of ethnic origin. | Project Coordinator |
| SESP Risk 7: Climate change will lessen impact of project’s IAS prevention, control and management intervention. | Climate Change Mitigation and Adaptation | P = 2, I = 2 LOW | Scientific research and data from China show a correlation between the range boundaries of IAS and temperature, and with the general and localized changes in climate (including temperature) there is an apparent likelihood that areas optimal for the invading IAS will increase in size in the coming years as temperature increases. However, this is a comparatively slow change and while the effects of climate change, in all likelihood, will not show any marked changes during the project duration, it will have impact long-term. This fact is well recognized, and the project is to address this issue through an optimization in the information exchange between monitoring and data management systems, which among other will be used for risk assessments and model analysis. These will assist the national, provincial and local governments in their IAS Management planning, as well as their targeting of IAS Management interventions aimed at halting IAS advances into new areas opening up due to the changes in climate. | Project Coordinator |

Stakeholder engagement plan:

- Project implementation will involve extensive engagement with stakeholders at all levels, and particularly in the demonstration landscape pilot sites. Table 9 summarizes the roles and responsibilities for key project stakeholders at all levels during project implementation. In addition to the general engagement in the project, Annex E outlines the various stakeholders’ planned engagement in the project’s trainings, Annex U denotes where MARA, MEE and GACC are utilizing GEF funding for activity implementation and Annex V provides a schematic outline of stakeholders’ involvement in the project activities. MARA and its provincial and local administrations will coordinate closely with other governmental stakeholders, particularly through the provincial and county level project Management Units, the established IAS Coordination Groups, as well as, via the existing governance structures at national, provincial and county levels. The county level project Management Units in Wenchang city and Bishan district will collaborate with the village administrations, NGOs and the private sector with in the project areas. Stakeholders will in addition to their direct involvement in the project activities be consulted, engaged and informed throughout the project implementation phase to: (i) promote understanding of the project’s outcomes; (ii) promote stakeholder ownership of the project through engagement in planning, implementation and monitoring of the project interventions; (iii) build public awareness; and (iv) maximize linkage and synergy with other ongoing projects.

Table 9. Summary stakeholder analysis indicating main roles and responsibilities

| Stakeholder | Roles and Responsibilities | Engagement in the project |
| --- | --- | --- |
| Ministry of Finance (MoF) | MOF is the GEF Operational Focal point of China responsible for coordinating the programming of GEF resources and overseeing the China GEF portfolio with the GEF Agencies. As a ministry MOF is responsible for public finance, taxation etc. The ministry also provides loan guarantees for the governmental agencies, financial institutions, and state enterprises. | As the GEF Operational Focal Point MOF will receive the GEF grant for the current project on behalf of the Chinese Government. MOF will be a core member of the Project Steering Committee, as well as the overall Program Steering Committee. MOF will have a core role in providing guidance, coordination and supervision on the disbursement and expense of GEF grant, performance evaluation, summary and promotion of project results. |
| United Nations Development Programme (UNDP) | UNDP is the assigned GEF Implementing Agency for the project and the UNDP-China office is a close development partner of MARA. UNDP China works in four main areas 1) poverty, equity and governance 2) south-south and global cooperation 3) environment and energy and 4) disaster management. Overall UNDP works in about 170 countries and territories, helping to achieve the eradication of poverty, and the reduction of inequalities and exclusion. UNDP helps countries to develop policies, leadership skills, partnering abilities, institutional capabilities and build resilience in order to sustain development results. | As the GEF Agency for the project it is overall responsible for the project oversight and management. UNDP will ensure project quality control and support the project in its achievement of the set objective and planned outcomes. UNDP will also ensure that the project follows UNDP/GEF rules and regulations for project implementation. UNDP as the Implementing Agency will manage the project's GEF grant on behalf of the Chinese Government. UNDP will be a core member of the Project Steering Committee as well as the overall Program Steering Committee. |
| Ministry of Agriculture and Rural Affairs (MARA) | Ministry of Agriculture and Rural Affairs is in charge of agriculture and rural economic development, research and development of strategies and long-term and mid-term policy and plans for agriculture and the rural economy. MARA is the lead ministry for the management of IAS in China and is responsible for risk assessment, monitoring and early warning, comprehensive management, and information release of agricultural IAS, drafting laws, rules, and regulations on IAS, formulating development strategies, plans and initiatives, and proposing relevant policies, and develop relevant technical specifications and organize implementation. | MARA is the project Implementing Partner and chairs the Project and Program Steering Committees. MARA, through REEA (please see below), will host the PMO and will coordinate the project and program and ensure the preparation of regular reporting of achievements in accordance with UNDP rules and Procedures. MARA, as the projects Implementing Partner will, not including the overall project management and oversight undertaken by REEA, be engaged in a larger subset of project activities in the projects four components and will play a specific role under outputs 1.1, 1.2, 1.3, 2.3, 3.1, 3.4 and 4.3. |
| Rural Energy & Environment Agency (REEA), MARA | REEA is a directly affiliated institution under Department of Science, Technology and Education (MARA). REEA is entrusted by the DSTE as the fund manager for international projects and are undertaking the day to day implementation and management of said projects including the C-SAP 2 IAS Project. | REEA will, as the day-to-day project implementer and fund manager of the Implementing partner MARA, establish a PMO which will provide the technical support and coordination for the project team (output 4.4). The PMO will also coordinate the C-SAP Program overall. REEA will be engaged in, and coordinating, the majority of activities under the project. |
| Ministry Ecology and Environment (MEE) | Ministry Ecology and Environment is responsible for the overall coordination, supervision and administration of the environment and ecological and environment concerns. MEE is involved in IAS management within protected areas, including areas of special ecological significant and MEE is the lead ministry with regard to IAS in connection with the Convention on Biological Diversity. | MEE, through its implementing arm FECO (please see below), is a Co-Implementing Partner under the project and will be a core member of the projects steering committee, as well as the program steering committee. MEE as the Co-Implementing Partner will, not including the overall project management and oversight undertaken by FECO, be engaged in a larger subset of project activities in the projects four components, and will play a specific role under output 1.1, 1.2, 1.3, 2.3, 3.3 and 4.3. |
| Foreign Economic Cooperation Office (FECO), MEE | FECO is an institution affiliated to the Ministry of Ecology and Environment of China, mainly responsible for Multilateral Environment Agreements (MEAs) implementation, bilateral and multilateral cooperation, global environmental policy research. FECO implemented projects, including international projects under the supervision of MEE. | FECO will undertake the day-to day implementation of the project related activities related to MEE. FECO will in this regard work under the supervision of Department of Nature and Ecology Conservation of MEE. FECO will be engaged in the majority of activities under the project and will act as the activity coordinator for a smaller subset of activities. |
| General Administration of Customs (GACC） | Following the Government restructuring in 2018 the inspection and quarantine responsibilities of the General Administration of Quality Supervision, Inspection and Quarantine has been moved to the General Administration of Customs. GACC is therefore now in charge of the inspection and quarantine of imported animals and plants and their products, and is charged with undertaking inspection, quarantine, supervision and management of the entry and exit of animals, plants and their products, as well as undertaking risk analysis and emergency prevention measures related to IAS. | GACC through its implementing arm CAIQ (please see below), is a Co-Implementing Partner under the project and will be a core member of the projects steering committee, as well as the program steering committee. GACC, as the Co-Implementing Partner will, not including the overall project management and oversight undertaken by CAIQ, be engaged in a larger subset of project activities in the projects four component and will play a specific role under output 1.1, 1.2, 1.3, 2.2 and 4.3 |
| Chinese Academy of Inspection and Quarantine Research (CAIQ), GACC | Chinese Academy of Inspection and Quarantine Research (CAIQ) is a Central Research Institute of public welfare inspection and quarantine established by the state. Its main task is to carry out research on the application of inspection and quarantine and related basic, high-tech and soft science. It focuses on solving the scientific and technological problems with overall, comprehensive, critical, sudden and basic characteristics in the work of inspection and quarantine, and to make decisions for the national inspection and quarantine. Provide technical support for inspection and Quarantine Law enforcement and provide social services for quality and safety education and social practice training. | CAIQ will be a supporting academic institution for the project, where they will provide input and guidance as well as expertise to a range of the project activities. CAIQ will be engaged in the majority of activities under the project and will act as the activity coordinator for a smaller subset of activities. |
| All-China Women’s Federation (ACWF) | The All-China Women's Federation is a quasigovernmental institution, which as its main duties are to represent and safeguard women's rights, promote gender equality, empower women to create opportunities for learning and education, and enhance women's awareness of social activities. | ACWF is a member of the project and program steering committees. ACWF and its local entities will, as part of the project’s stakeholder engagement, be involved in output 1.3, 3.3 and 3.4. In addition, ACWF representatives will take part in project trainings output 2.3 and 3.1 |
| Hainan Provincial Department of Agriculture (HPDA) | The Hainan Provincial Department of Agriculture is the provincial equivalent to MARA and undertakes many of the same functions but at provincial level. The Department of Agriculture is the provincial lead with regard IAS prevention, control and management. | Hainan Provincial Department of Agriculture will be responsible for supervision and guidance of project implementation in Hainan. The Department of Agriculture will be engaged in most of the project activities at provincial and country level, but play a specific role under output 1.1, 1.3, 1.4, and 2.1 and will partake in the project developed trainings output 2.3. and 3.1 |
| Department of Ecology and Environment of Hainan (DEEH) | Department of Ecology and Environment of Hainan is the provincial equivalent to MEE and undertakes many of the same functions but at provincial level. The Bureau of Ecology and Environment is the provincial lead involved in IAS management within protected areas, including areas of special ecological significant with regard IAS prevention, control and management. | Department of Ecology and Environment of Hainan will be involved in the MEE related activities in Hainan. It will play a specific role under output 1.1, 1.3 and 2.1 and will take part in the MEE developed trainings output 2.3 |
| Haikou Customs District (HCD) | The Haikou Customs District is the provincial equivalent to GACC and undertakes many of the same functions but at provincial level. Haikou Customs District is therefore charged with undertaking inspection, quarantine, supervision and management of the entry and exit of animals, plants and their products. | Haikou Customs District will oversee and implement specific tasks related to Hainan and Yangpu port in specific. It will play a specific role under output 1.1, 1.3 and will take part in the GACC developed trainings output 2.2 |
| Chongqing Agriculture Committee (CAC) | The Chongqing Agriculture Committee is the municipality's equivalent to MARA and undertakes many of the same functions but at provincial level. The Agriculture Committee is the provincial lead with regard to IAS prevention, control and management. | Agriculture Committee will be responsible for supervision and guidance of project implementation in Chongqing, assisting the government at the county level in project coordination and resource integration. The Agriculture Committee will be engaged in most of the project activities at provincial and country level, but will play a specific role under output 1.1, 1.3, 1.4, and 2.1 and will partake in the project developed trainings output 2.3. and 3.1 and the development of local management plans output 3.4 |
| Bureau of Ecology and Environment of Chongqing (BEEC) | Bureau of Ecology and Environment of Chongqing is the provincial equivalent to MEE and undertakes many of the same functions but at city level. The Bureau of Ecology and Environment is the city lead involved in IAS management within protected areas, including areas of special ecological significant with regard IAS prevention, control and management. | Bureau of Ecology and Environment of Chongqing will be involved in the MEE related activities in Chongqing. It will play a specific role under output 1.1, 1.3 and 2.1 and will take part in the MEE developed trainings output 2.3 and the development of local management plans output 3.4 |
| The People's Government of Wenchang City (PGWC) | The People's Government of Wenchang City encompasses all of the local governmental departments and undertake the day to day governing of the city and the implementation of the city’s projects and programs. People's Government of Wenchang City will be responsible for project organization, implementation and daily regulation at local area, and provides support to the IAS project. | People's Government of Wenchang City will be responsible for supervision and guidance of project implementation in Wenchang City. The Wenchang City Government will be engaged in most of the project activities at country level, but will play a specific role under output 1.1, 1.3, 3.2 and 3.4, including participating in the project trainings output 2.3. and 3.1 |
| Chinese Research Academy of Environmental Sciences (CRAES) | The Chinese Research Academy of Environmental Sciences is a national environmental non-profit multidisciplinary research institution, which is responsible for developing China’s environmental science and technologies and solving major environmental problems. CRAES has a professional team engaged in IAS prevention, control and management research within protected areas and other conservation areas, providing theoretical and technical support for protected areas’ work in this field. | The IAS team of CRAES will provide input and guidance as well as expertise to a range of the project activities. They will play a specific role under output 1.1, 1.2, 1.3, will partake in the project developed trainings output 2.3 and 3.1 and the provision of said trainings output 3.2 and 3.4 |
| Wenchang Agricultural Technology Promotion Service Center (WATPSC) | As part of the People's Government of Wenchang City the Wenchang Agricultural Technology Promotion Service Center is in charge of providing agricultural production service and technical promotion of Wenchang City and is responsible for the implementation of IAS prevention, control and management at local level. | The Wenchang Agricultural Technology Promotion Service Center will be engaged in local activities within the project agricultural landscape in Hainan. They will play a specific role under output 1.1, 1.3, 3.2, 3.3 and 3.4 and will partake in the project developed trainings output 2.3. and 3.1 ( |
| Wenchang Forestry Bureau (WFB) | As part of the People's Government of Wenchang City the Wenchang Forestry Bureau is in charge of forestry management in Wenchang City including the implementation of IAS prevention, control and management at local level within the forested areas of Wenchang. | The Wenchang Forestry Bureau will be engaged in local activities within the project agricultural landscape in Hainan. They will play a specific role under output 1.1, 1.3, 3.2, 3.3 and 3.4 and will partake in the project developed trainings output 2.3. and 3.1 |
| Wenchang Eco-environmental Protection Bureau (WEPB) | As part of the People's Government of Wenchang City the Wenchang Eco-environmental Protection Bureau is in charge of ecological environment protection in Wenchang City and is responsible for the implementation of IAS prevention, control and management within protected areas and other conservation areas. | The Wenchang Eco-environmental Protection Bureau will be engaged in local activities within the project agricultural landscape in Hainan. They will play a specific role under output 1.1, 1.3, 2.1, 3.2, 3.3 and 3.4 and will partake in the project developed trainings output 2.3. and 3.1 |
| Division of Quarantine Supervision of Yangpu Customs (DQSPYC) | Division of Quarantine Supervision of Yangpu Customs and the third-party operators undertaken (with different responsibilities) the inspection, quarantine and supervision of said entry-exit commodities, goods, animals and plants, as well as animal and plant products and organizing the implementation of risk assessment and emergency precaution measures | Division of Quarantine Supervision of Yangpu Customs and the third-party operators at Yangpu port and similar ports in China will be the direct beneficiaries of the GACC developed trainings output 2.2. |
| The People's Government of Chongqing, Bishan District (PGCBD) | The People's Government of Chongqing, Bishan District encompasses all of the local governmental departments and undertakes the day to day governing of the city and the implementation of the city’s projects and programs. People's Government of Wenchang City will be responsible for project organization, implementation and daily regulation at local area, and will provide support to the IAS project. | The Bishan District Government will be responsible for supervision and guidance of project implementation in Wenchang City. The Wenchang City Government will be engaged in most of the project activities at country level, but will play a specific role under output 1.1, 1.3, 3.2 and 3.4, including participating in the project trainings output 2.3. and 3.1 |
| Bishan Agricultural Technology Extension Center (BATEC) | The Bishan Agricultural Technology Extension Center is in charge of providing agricultural production service and technical promotion of Bishan District and is responsible for the implementation of IAS prevention, control and management at local level. | The Bishan Agricultural Technology Extension Center will be engaged in local activities within the project agricultural landscape in Hainan. They will play a specific role under output 1.1, 1.3, 3.2, 3.3 and 3.4 and will partake in the project developed trainings output 2.3. and 3.1 |
| Bishan District Forestry Bureau (BDFB) | As part of the Bishan District Government the Bishan Forestry Bureau is in charge of forestry management in Bishan District including the implementation of IAS prevention, control and management at local level within the forested areas of Bishan. | The Bishan Forestry Bureau will be engaged in local activities within the project agricultural landscape in Hainan. They will play a specific role under output 1.1, 1.3, 3.2, 3.3 and 3.4 and will partake in the project developed trainings output 2.3. and 3.1 |
| Bishan District Environmental Protection Bureau (BDEPB) | As part of the Bishan District Government the Bishan Environmental Protection Bureau is in charge of ecological environment protection in Bishan District and is responsible for the implementation of IAS prevention, control and management within protected areas and other conservation areas. | The Bishan Environmental Protection Bureau will be engaged in local activities within the project agricultural landscape in Hainan. They will play a specific role under output 1.1, 1.3, 2.1, 3.2, 3.3 and 3.4 and will partake in the project developed trainings output 2.3. and 3.1 |
| Chinese Academy of Agricultural Sciences (CAAS) | The Chinese Academy of Agricultural Sciences is a national agricultural scientific research institution, which is responsible for the basic, applied and high-tech research of agricultural and its applications in China. CAAS has a dedicated professional team working on agrobiodiversity utilization and IAS Management, it provides important theoretical and technical support for the country's work in the field of IAS prevention, control and management. | CAAS will be a supporting academic institution for the project, where they will provide input and guidance as well as expertise to a range of the project activities. This will include support to the development of the IAS guidelines under output 1.2, 1.3 and 1.4. CAAS will also be involved in the development and provision of the project developed trainings (Output 2.3, 3.2 and 3.4). |
| Provincial universities and research institutions (PURI) | This group of stakeholders are local scientific research institutions, which as non-profit scientific research institutions are responsible for scientific research and personnel training. They have professional teams engaged in IAS prevention, control and management research, providing theoretical and technical support to local, provincial and central actors in this field. | The local scientific research institutions will provide input and guidance as well as expertise to, among other output 1.3, 1.4 and 2.1. The research institutions will also be involved in the development and provision of the project developed trainings (Output 2.3, 3.2 and 3.4). |
| Local agro-businesses, farmers cooperatives and other enterprises (LBFCOE) | Local agrobusinesses, farmers cooperatives and other enterprises will be a key stakeholder group for the project as they are part of the agricultural producers which are affected by IAS and thus are part of the main stakeholders which will be actively engaged in applying IAS Management techniques on their lands in order to reduce the threat from IAS on their crop. | Local agrobusinesses, farmers cooperatives and other enterprises will be part of the projects direct beneficiaries as they will be the main target for the on-the-ground training on and implementation of the project promoted IAS Management techniques which is undertaken under component 3 |
| Civil society groups and NGOs (CSO/NGO) | While the PPG phase did not identify any specific NGO/CSOs being active in the area of IAS Management the project will during its implementation be on an active look out for organizations which could/would play a part in the project. One organization already mentioned earlier is the ACWF and in particular its local chapters will be an important stakeholder for the project as they are active even at village level and thorough them the project would be able to reach local women. | Where identified the local NGO/CSOs will be engaged to the extent possible and in particularly collaboration with local NGO/CSO would be sought to have them directly involved in the project's social public awareness raising. The local NGO/CSO including the ACWF will receive IAS related training to enable them to better engage and interact with the communities they serve. |
| Farming communities (FC) | Local farmers will be the main key stakeholder group for the project, as they, as the local agrobusinesses and farmers cooperatives are affected by IAS and thus will be actively engaged in applying IAS Management techniques on their lands in order to reduce the threat from IAS on their crop. | Local farmers will be part of the projects direct beneficiaries as they will be the main target for the on-the-ground training on and implementation of the project promoted IAS Management techniques which is undertaken under component 3 |

Gender equality and empowering women:

- During the PPG phase, socio-economic (Annex K) and gender assessments (Annex F) reviewed the role of females and males related to the focus of project and its implementation and potential impacts of the project on each gender group. In addition, a gender action plan for the project was developed (Annex F). This aimed to ensure an inclusive approach through which women and men are able to participate actively and benefit equitably, have equitable access to the project resources and receive fair social and economic benefits. The assessments identify that through-out society there is a gender imbalance where women are more disadvantaged than men. Something which is being reflected in the men/female ratio among government staff. While for low level positions this is less explicit, it becomes more pronounced moving up through middle and upper management. Differentiation in job types also occurs, for instance in lower education groups where women tend to hold jobs, such as education, hospitality and child/healthcare, which could be seen as an extension of inherited gender roles. The assessment also identified that 70 percent of inhabitants in villages are women. This was verified to be true in Wenchang and Bishan during the project’s field missions. It was also noted that women seem to fall victim to traditional gender bias perceptions, where the husband or oldest male family member is the household’s spokes-person, and for instance during field visits, if not otherwise directed, women would keep in the background and say little. At the same time, as females account for the majority of the population, many of whom are ”left behind women” are sole responsible for caring for the household’s farm land and livestock and with that are also a key stakeholder group with regard to IAS Management.

- The Gender mainstreaming approach to be taken by the project is detailed in the Gender Assessment and Action Plan in Annex F, which describes specific actions to mainstream gender into project output implementation including gender indicators. The key strategies to be followed to achieve this include but are not limited to: a) Mobilize support from gender specialists; b) Ensure women’s genuine and equal representation (i.e. in task forces, committees, training, sustainable livelihoods etc.); c) Ensure women’s equal access to project information; d) Project specific actions to empower women, including providing capacity support for women’s groups in sustainable IAS Management. According to UNDP gender marker standards, the project has a UNDP GEN2 gender marker.  Key gender-disaggregated indicators and targets in the project results framework and monitoring plan will be tracked throughout project implementation.

South-South and Triangular Cooperation (SSTrC):

- The project will facilitate cooperation with other countries through the involvement of visiting experts’ participation in project organized events, trainings and seminars. The part of the developed trainings, including MOOCs will be made available in English thereby facilitating their use outside the borders of China. Although outside the scope of the project, these trainings might also be supported by ongoing or future training programs undertaken by MARA, MEE, GACC or other parties, relying on the long tradition of China to offer training opportunities to other developing countries. As part of the project, the experience of the island of Hainan will be documented and promoted for use as an example small island states. The project outputs will provide support to south/south cooperation in its strategic planning process for IAS Management, and the developed National and Provincial IAS Management strategy and action plans will guide the national and provincial engagement internationally. The project will also internationally promote IAS Management among other countries through holding an IAS Management full-day side event in connection with the Fifteenth Meeting of the Conference of the Parties to the Convention on Biological Diversity (COP15) in 2020. Furthermore, the project will provide support to MARA, MEE and GACC in their meetings on IAS Management with international partners with the aim to make IAS Management more pronounced in the international agenda

Sustainability and Scaling Up:

- This project is part of the GEF-6 China’s Partnership Program for Sustainable Agricultural Development (C-SAP) for strengthening the implementation of the Sustainable Development Goals and China’s National Plan for Sustainable Development of Agriculture (2015-2030) and has the full support of the Chinese Government. The project itself has the strong support of MARA, MEE and GACC that are the project’s Implementing Partner and Co-Implementing Partners, respectively, and, which are, together with the respective provincial departments, providing co-financing to the project of a total of USD 18.9 million. The project will, with its support to the establishment of the National and Provincial IAS Management Coordinating Groups, create lasting institutions that will ensure an integrated cross-sector coordination of IAS Management long-term. Changes to regulations and internal ordinances will further institutionalize such cross-sector cooperation and facilitate a more holistic approach to IAS Management at all levels. The project will develop National and Provincial IAS Management Strategy and Action Plans, which will provide the guidance towards IAS Management implementation in key areas until 2030, including, but not limited to, expansion/improvement of the monitoring station network and monitoring methodologies, improved capabilities in data analysis and data management, expanded public engagement and citizens science, implementation of early response measures and expansion/improvement of early warning systems and methodologies and south/south and north/south cooperation. The NSAP and PSAPs will be used in the national and provincial 14th and 15th five-year planning processes.

- The project will also develop guidelines and methodologies for IAS biodiversity risk assessment, buffer zone establishment and emergency response providing new and updated guidance for provincial and local implementers. Institutional capacities of the main governmental institutions, including extension workers and IAS inspection staff at the ports will be build. Furthermore, farmers, farmer cooperatives and businesses will be trained, through participatory partnership-based approaches, in on-the-ground techniques and management responses to IAS encroachment thereby building their skills and capacities. Capacitated farmers and extension workers, as well as other stakeholders, will implement IAS management plans on 35,000 ha in Hainan and Chongqing, demonstrating the positive results of biological, vegetation replacement and low chemical techniques. This, both in terms of reducing the IAS threat to agrobiodiversity, as well as the economy. The project will also develop an IAS APP, which can be used by farmers and the public alike for on-farm reporting of IAS occurrences in their fields or in public areas such as parks and scenic spots. The IAS APP is expected to provide an important information layer to the local IAS monitoring efforts

- The projects IAS Knowledge Management platform will provide for a clearing house type web-based system, which will house all of the project developed trainings, as well as knowledge management material, from the project partners and other interested parties, which are agreeing to make information available to the platform. The platform will be publicly accessible and will enable the provision of knowledge materials and trainings to an audience which vastly exceeds the project’s direct beneficiaries. Also, the project will work closely together with the other C-SAP child projects, and to the extent it is practical and economically feasible, ensure that, for instance training of government staff, is undertaken in the counties or provinces where the other C-SAP Program child project operates. In addition, in Hainan synergies with the C-SAP 3 project will be ensured to heighten the outreach of the project. Furthermore, all developed training materials, videos etc. will be shared with the C-SAP Program’s other child projects, as well as linked to the C-SAP 1 FAO projects Knowledge Platform and the C-PAR Biodiversity Knowledge Platform. In addition, good practices and lessons learned developed as part of this project will be fed into on-going work of MARA, MEE and GACC and disseminated through their internal systems.

# Project Management

Cost efficiency and effectiveness:

- As part of the national C-SAP Program, the project focuses on a key threat to endemic species, traditional varieties and GRFA, namely invasive alien species, thus supporting the Chinese Government’s efforts for conserving agrobiodiversity, as well as its work to combat IAS encroachment in China in its own right.

- The project’s approach towards addressing the barriers hindering an effective IAS prevention, control and management in China (including incomprehensive policy, legal and management frameworks and lack of sector and national, provincial and county level integration, lack of comprehensive assessment, monitoring, early warning and rapid response tools, and the institutional capacity to use them, lack of effective and adopted approaches for controlling IAS impacts on agrobiodiversity and weak public and institution awareness of the positive impacts of IAS Management) is cost-effective, as its applicability at provincial and national levels will be broad, including expanding outside the targeted project agricultural landscapes and the project’s direct beneficiaries.

- The project contributes directly to the cross-sector coordination and collaboration engagement that will facilitate a coherent approach to IAS Management, with different agencies working together holistically, improving agencies actions in common intervention areas thus, maximizing impacts. Knowledge-sharing of the IAS Management activities and approaches through the C-SAP Program will magnify the impact from the investment in this project. As will the provision of the project’s knowledge materials through the developed IAS Knowledge Management platform, which forms part of the Knowledge Management work undertaken by the C-SAP 1 FAO project.

- The project implementation is interlinked with the implementation of the C-SAP Program and both are under the overall guidance of the Program Steering Committee, which, among other, will safeguard that synergies between projects and overall cost effectiveness of the individual C-SAP child projects and the overall program is ensured.

- The total GEF investment of USD 2,789,908 for this project will leverage a minimum of $18.9 million in co-financing from the Chinese government, a highly cost-effective ratio of 6.77 with additional associated financing inputs anticipated during project implementation. Overall this represents a very cost-effective investment of GEF funds.

Project management:

- The project Implementing Partner is the Ministry of Agriculture and Rural Affairs (MARA), which will have the full responsibility for implementing the project. As part of MARA’s implementation of the project it has requested UNDP to (on their behalf) delegate parts of the project outputs and underlying activities to MEE/FECO and GACC/CAIQ, which will act as Co-Implementing Partners (C-IP) for the project (see section VIII Governance and management Arrangements). The project will be managed, overall, via a Project Management Office (PMO) established in REEA, located in the Department of Science, Technology and Education (DSTE) under MARA, in Beijing. The PMO, which is under the auspices of the National Project Director, will in addition to oversee the C-SAP 2 IAS project, also oversee and coordinate the C-SAP China – Sustainable Agriculture Program (C-SAP). In addition to this, the C-SAP 2 IAS child project will receive knowledge management support from the C-SAP 1 and C-SAP 5 child projects (no cost to the C-SAP 2 IAS child project).

- At provincial level project Management Units (MU) will be established in the Agricultural Departments in Chongqing and Hainan and managed by a MU Focal Point whom will oversee provincial project implementation and ensure provincial coordination between provincial project partners and stakeholders. Similar MUs will be established in Bishan (Chongqing) and Wenchang (Hainan) where MU Focal Points/Coordinators supported by Community Mobilizers will ensure local implementation of project activities. All positions will be part of the project’s co-financing.

- Designated Focal Points/Coordinators (co-financed) at the Haikou Customs District will oversee the management of project activities implemented at the demonstration port conducted by port authorities. The work of the Haikou Customs District falls under the GACC as the projects Co-Implementing Partner.

- In a similar manner FECO will be overseeing and managing the project activities assign to MEE as a Co-Implementing Partner. But in contrast to GACC, MEE will only have few local level activities (in Hainan) and thus no management structures will be established at lower levels.

Agreement on intellectual property rights and use of logo on the project’s deliverables and disclosure of information:

- To accord proper acknowledgement to the GEF for providing grant funding, the GEF logo will appear together with the UNDP logo on all promotional materials, other written materials like publications developed by the project, and project hardware. Any citation on publications regarding projects funded by the GEF will also accord proper acknowledgement to the GEF. Information will be disclosed in accordance with relevant policies notably the UNDP Disclosure Policy and the GEF policy on public involvement.

# Project Results Framework

| This project will contribute to the following Sustainable Development Goal (s): Goal 2: Indicator 2.5 and Indicator 2.4: Goal 15: Indicator 15.1 and Indicator 15.8. Secondary contribution towards SDG Goals 1 (end poverty), SDG 5 (gender equality), SDG10 (reduce Inequality), SDG 13 (climate change) and SDG 17 (global partnership for sustainable development) |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| This project will contribute to the following country outcome included in the UNDAF/Country Programme Document: UNDAF 2016-2020: Priority Area No 2: Improved and Sustainable Environment; Outcome 2: More people enjoy a cleaner, healthier and safer environment as a result of improved environmental protection and sustainable green growth |  |  |  |  |  |  |
| This project will be linked to the following output of the UNDP Strategic Plan: 1.4.1 Solutions scaled up for sustainable management of natural resources, including sustainable commodities and green and inclusive value chains |  |  |  |  |  |  |
|  | Objective and Outcome Indicators (no more than a total of 15 -16 indicators) | Baseline | Mid-term Target | End of Project Target | Data Collection Methods and Risks/Assumptions |
| Project Objective: To strengthen intersectoral coordination mechanisms, approaches and technical capacity for more effective prevention, control and management of IAS threats to agrobiodiversity in China. | Indicator 1: Area of landscape under improved IAS prevention, control and management practices (hectares) (GEF Core Indicator 4.3) | 0 | 15,000 ha & management plan for project target agricultural landscapes developed | 35,000 ha | Data source and Measurements: Project targeted agricultural landscapes will be plotted by stakeholders, in terms of IAS spread and location of traditional varieties, through GPS and reported to the project focal point at the local government. Known replication and up-scaling sites will likewise be reported. Visual site recordings documenting change will also be used. MoV: Project’s annual reporting and the annual PIR. |
|  |  |  |  |  | Risks: Local farmers show little or no interest in project IAS protection, control and management activities and are therefore not interested in undertaking an up-scaling of project developed initiatives on their own accord. Assumptions: Project activities are well designed and relevant to target groups (including farmers) and the local benefits of the project interventions (including livelihood improvements) are well demonstrated and documented, providing for sufficient interest by stakeholders |
|  | Indicator 2: Number of direct beneficiaries disaggregated by gender as a co-benefit of GEF investment (GEF Core Indicator 11) | 0 | Women 3,000 Men 3,000 Total 6,000 | Women 9,000 Men 9,000 Total 18,000 | Data source and Measurements: Participation lists from project trainings, people receiving training certificates, farmers receiving/testing specific project interventions etc. as reported via project reporting or through reporting to the project PMO. MoV: Project’s annual reporting and the annual PIR. |
|  |  |  |  |  | Risks: Project activities are not deemed interesting/relevant by direct beneficiaries who will refrain from participating Assumptions: Project activities are well designed and relevant to target groups who have an interest in improving their skill set and livelihood options |
| Component 1: Strengthened Enabling Environment OUTCOME 1 Strengthened policy, regulatory and strategic framework for IAS Management incorporated into inter-sectoral response mechanisms for the reduction of IAS threats to agrobiodiversity, including traditional varieties and GRFA. | Indicator 3: Extent of strategies/regulations for comprehensive IAS prevention, control and management adoption which have addressed identified barriers and gaps, as measured by: ia) The National IAS Strategic Action Plan adopted. ib) The Provincial IAS Strategy and Action Plans in Hainan and Chongqing) adopted. iia) Number of new or updated Ministerial IAS prevention, control and management regulations adopted. iib) Number of new or updated Provincial Department IAS prevention, control and management regulations approved | ia) N/A | ia.) IAS NSAP ready for inclusion in the legislative process cycle/pipeline | ia.) IAS NSAP adopted | Data source and Measurements: Consultations with national and local partners who review and follow national and local changes in the policy and regulatory framework. MoV: Public announcement of new and/or updated documents/regulations on Government web-sites |
|  |  | ib) N/A | ib) Hainan and Chongqing IAS PSAPs being drafted for inclusion in the legislative process cycle/pipeline | ib) Hainan and Chongqing IAS PSAPs adopted |  |
|  |  |  |  |  | Risks: The review and approval processes for changes in the policy and regulatory framework is prolonged due to internal and other bureaucratic processes. Assumptions: There is a keen interest amongst line ministries and at provincial level for improving the policy and regulatory framework for IAS protection, control and management to ensure a more effective and comprehensive intervention against IAS establishment and introduction in China. |
|  |  | iia) N/A | iia) at least 3 Ministerial IAS regulations being drafted for inclusion in the legislative process cycle/pipeline 0 | iia) at least 3 Ministerial IAS regulations adopted by the respective Ministry |  |
|  |  | iib) N/A | iib) at least 6 Provincial department IAS regulations being drafted for inclusion in the legislative process cycle/pipeline | iib) at least 6 Provincial department IAS regulations adopted by the respective provincial department |  |
|  | Indicator 4: Number of budget-supported local IAS coordination bodies or IAS offices that regularly coordinate local inter-sectoral IAS Management, including implementation of the developed strategic action plan : i). Chongqing ii) Hainan. | i) 6 ii) 3 | i) 9 ii) 5 | i) 12 ii) 8 | Data source and Measurements: Provincial focal points report annually to the project PMO, which includes the data in the annual report and annual PIR. MoV: Provincial registration/notification. |
|  |  |  |  |  | Risks: County level governments do not see the relevance of establishing IAS offices and/or coordination bodies within their jurisdiction. Assumptions: The current nascent process in China for cross-sectoral cooperation and engagement in IAS protection, control and management is amplified through the project activities and engagement at provincial and local levels |
|  | Indicator 5: Government financing for the prevention, control and management of IAS threats, as measured by annual operating budget provided by the financial department of: i) MARA. ii) MEE. iii) GACC. | 2018 (RMB) MARA: 14,000,000 MEE: 6,000,000 GACC: 5,000,000 | 2021 (RMB) MARA: 14,280,000 MEE: 6,500,000 GACC: 5,500,000 | 2023 (RMB) MARA: 14,700,000 MEE: 7,000,000 GACC: 6,000,000 | Data source and Measurements: MARA, MEE and GACC project focal points report annually to the project PMO. MoV: Projects annual reporting and the annual PIR. |
|  |  |  |  |  | Risks: The National Government has a limited interest in maintaining the financial support for IAS protection, control and management into the short-term and long-term budget planning. Assumptions: The current focus on IAS is maintained and is expected to increase due to project activities particularly regarding awareness raising amongst government officials. Also, the project activities focusing on the international cooperation on IAS protection, control and management are expected to heighten the national interest. |
| Component 2: Strengthened IAS management frameworks and institutional capacity. OUTCOME 2 Strengthened institutional capacities and interagency response mechanisms for IAS detection, quarantine, disposal, monitoring, early warning and rapid response. | Indicator 6: Institutional capacities and interagency response mechanisms for IAS protection, control and management including detection, quarantine, disposal, monitoring early warning and rapid response, as indicated by the UNDP capacity scorecard: i) National ii) Chongqing iii) Hainan iv) Bishan v) Wenchang | i). National: 14% ii) Chongqing: 16% iii) Hainan: 20% iv) Bishan: 22% v) Wenchang: 22% | i) National: 23% ii) Chongqing: 27% iii) Hainan: 31% iv) Bishan: 33% v) Wenchang: 33% | i) National: 47% ii) Chongqing: 49% iii) Hainan: 53% iv) Bishan: 67% v) Wenchang: 58% | Data source and Measurements: The Capacity Development Scorecard survey was undertaken among stakeholders using the UNDP Scorecard during the PPG phase. For the mid-term and terminal scorecards surveys these are undertaken prior to the project’s mid-term and final evaluations. MoV: Capacity Development Scorecard survey during formulation, at mid-term and at project completion. (Annex N) |
|  |  |  |  |  | Risks: Lack of interest within government institutions for engaging their staff in the project’s capacity building activities. In addition, high staff turnover can reduce the long-term institutional knowledge built through project activities. Assumptions: Government institutions, as project stakeholders and partners have an interest in building their internal capacity for IAS protection, control and management, as well as retaining their staff. |
|  | Indicator 7: Staff capacity at Yangpu port for inspection, detection and species identification, quarantine and destruction of IAS at demonstration port, as measured by PPG developed port capacity scorecard. | 41% | 59% | 74% | Data source and Measurements: The port capacity Scorecard survey was undertaken among stakeholders using the UNDP Scorecard during the PPG phase. For the mid-term and terminal scorecards surveys these are undertaken prior to the project’s mid-term and final evaluations. MoV: Capacity Development Scorecard survey during formulation, at mid-term and at project completion. (Annex O) |
|  |  |  |  |  | Risks: Lack of interest within GACC and port authorities in the project’s capacity building activities. In addition, high staff turnover can reduce the long-term institutional knowledge built through project activities. Assumptions: GACC and port authorities, as project stakeholders and partners have an interest in building their internal capacity for IAS protection, control and management, as well as retaining their staff. |
|  | Indicator 8: Number of government staff at national, provincial and county levels staff (gender and youth disaggregated) obtaining certificates for successful completion of comprehensive and specialized trainings on IAS prevention, control and management delivered by certified training entities | 0 | Total 450 Women 350 Men Youth 120 Women 80 Men | Total 1000 Women 800 Men Youth 300 Women 200 Men | Data source and Measurements: Participation lists from project trainings, people receiving training certificates for specialized certification trainings, as reported via project reporting or through reporting to the project. MoV: Project’s annual reporting and the annual PIR. |
|  |  |  |  |  | Risks: Lack of interest within government institutions for engaging their staff in the project’s capacity building activities. In addition, high staff turnover can reduce the long-term institutional knowledge built through project activities Assumptions: Government institutions, as project stakeholders and partners have an interest in building their internal capacity for IAS protection, control and management, as well as retaining their staff. |
| Component 3: Demonstration of IAS threat reduction in agroecosystems OUTCOME 3 Strengthened IAS threat reduction through collaborative IAS Management by IAS Management agencies, agricultural enterprises and farming communities in Hainan and Chongqing agricultural landscapes | Indicator 9: Reduction of identified IAS threats in the project’s 35,000 ha large targeted agricultural landscapes, as measured by: Hainan i) ha covered by mile-a- minute. ii) ha covered by alligator weed. iii) ha covered by golden apple snail. Chongqing j) ha covered by alligator weed. jj) ha covered by golden apple snail. | Hainan i) 13,000 ha ii) 3,500 ha iii) 7,500 ha Chongqing j) 5,000 ha jj) 1,000 ha | Hainan i). 10,400 ha ii) 2,800 ha iii) 6,000 ha Chongqing j) 4,000 ha jj) 800 ha | Hainan i). 5,2000 ha ii) 1,400 ha iii) 3,000 ha Chongqing j) 2,000 ha jj) 400 ha | Data source and Measurements: Project targeted agricultural landscapes will be plotted by stakeholders through GPS, in terms of IAS spread and location of traditional varieties and reported to the project focal point at the local government. Visual site recordings documenting change will also be used. MoV: Project’s annual reporting and the annual PIR. (Annex N) |
|  |  |  |  |  | Risks: Local farmers show little or no interest in project IAS protection, control and management activities and are therefore not interested in undertaking an up-scaling of project developed initiatives on their own accord. Assumptions: Project activities are well designed and relevant to target groups (including farmers) and the local benefits of the project interventions (including livelihood improvements) are well demonstrated and documented, providing for sufficient interest by stakeholders |
|  | Indicator 10: Area coverage of traditional varieties and GRFA in the project targeted agricultural landscapes: i) Hainan ii) Chongqing. | i) 2,600 ha ii) 1,800 ha | i) Remain the same ii) Remain the same | i) Remain the same ii) Remain the same | Data source and Measurements: Project targeted agricultural landscapes will be plotted by stakeholders through GPS, in terms of IAS spread and location of traditional varieties and reported to the project focal point at the local government. Visual site recordings documenting change will also be used. MoV: Project’s annual reporting and the annual PIR. (Annex N) |
|  |  |  |  |  | Risks: Local farmers show little or no interest in project IAS protection, control and management activities and are therefore not interested in undertaking an up-scaling of project developed initiatives on their own accord. Assumptions: Project activities are well designed and relevant to target groups (including farmers) and the local benefits of the project interventions (including livelihood improvements) are well demonstrated and documented, providing for sufficient interest by stakeholders |
|  | Indicator 11 No encroachment of key IAS* on areas where IAS Management interventions have been implemented to prevent or control mile a minute, golden apple snail or alligator weed i) Hainan ii) Chongqing * Alligator weed, Golden apple snail, Mile-a-minute, Fragrant Eupatorium Herb, Common Parthenium, White horseweed and Crofton weed | N/A; | i) No encroachment of key IAS ii) No encroachment of key IAS | i) No encroachment of key IAS ii) No encroachment of key IAS | Data source and measurements: Project targeted agricultural landscapes will be monitored by local farmers and staff from the local agricultural bureau through GPS and reported to the project focal point at the local government. MoV: Project’s annual reporting and the annual PIR. |
|  |  |  |  |  | Risks: Local farmers show little or no interest in project IAS protection, control and management activities and are therefore not interested in monitor and report on IAS in the project agricultural landscapes on their own accord. Assumptions: Project activities are well designed and relevant to target groups (including farmers) and the local benefits of the project interventions (including livelihood improvements) are well demonstrated and documented, providing for sufficient interest by stakeholders |
|  | Indicator 12: Established participatory approach for reporting and monitoring of IAS in target agricultural landscapes, as measured by adoption of IAS app. | Non-technology supported surveys every 3 years | IAS APP developed and being piloted in the core areas | APP widely used in and outside project landscapes and APP provide timely information to local governments IAS monitoring systems and is used for decision-making. | Data source and measurements The web-based applications to be used in the public participation will be accessed and engagement and results will be assessed and reported on. As part of this the project will track how many people have been participating in the approaches and will disaggregate the data in terms of gender and youth. MoV: Reports from websites and apps used in public participation initiatives. |
|  |  |  |  |  | Risks: The popularization of the developed initiatives for public participation piloted by the by the project are not effective and people are not interested in engaging in the initiatives Assumptions: The dissemination of the developed initiatives for public participation piloted by the by the project through social media, to schools and within the farming communities reach critical mass to make “word of mouth” effective. Also the game like aspects of the initiatives and their easy use should facilitate broad based engagement. |
| Component 4: Awareness raising, knowledge management and coordination OUTCOME 4 Improved IAS knowledge management systems and awareness heightened, as well as effective program coordination, monitoring and evaluation | Indicator 13: Level of knowledge, attitude and practice of public, government, farmers and other key stakeholder groups on the environmental and economic threats posed by IAS, as indicated by results of the KAP surveys | Baseline KAP surveys will be made during project inception phase. | No midterm target | End-of-project targets, gender disaggregated, to be set in the analyses of the baseline KAP survey results. | Data source and Measurements: See Annex M for KAP methodology |
|  |  |  |  |  | Risks: The project’s awareness and knowledge management activities do not reach beneficiaries, stakeholders and the general public in a sufficient way to effectively build awareness in a measurable way. Assumptions: The project’s awareness and knowledge management activities will make use of current day communication channels etc. to facilitate broad scale communication and dissemination. |
|  | Indicator 14: IAS Knowledge Management platform is actively used as measured by platform visits per year. | N/A | Platform established with 350 annual visits. | 1000 annual visits. | Data source and Measurements: The establishment of the IAS Knowledge Management platform will be reported in the project annual reporting, and platform visits and use will be recorded through the website and reported on an annual basis. |
|  |  |  |  |  | Risks: Government staff working on IAS and other relevant stakeholders including farmers and research institutions are not interested in using the platform - or do not know about it, resulting in low platform visits. Assumptions: The IAS Management platform is extensively promoted, and stakeholders have an interest in obtaining IAS Management related information. |
|  | Indicator 15: Effectiveness of program coordination, as measured by i) Program management team and governance ii) Program level reporting | i) Terms of reference for PMO positions and PSC developed with clearly identified program-level responsibilities ii) Budget allocated for Coordination Officer to oversee program level coordination | i) PMO fully staffed; project and program level steering committees providing timely guidance ii) Aggregated reporting mechanism implemented, and results across the program are tracked and reported through knowledge platform | i) Program effectively coordinated through efficient program steering function ii) Annual program reports indicate clear progress towards outcomes and achievements beyond individual child projects | Data source and Measurements: Under the project/program the PMO will ensure appropriate project management and keep complete project records. MoV: PMO staff contracts, independent evaluations, project risk log records, steering committee meeting minutes, etc. |
|  |  |  |  |  | Risks: Delays associated with recruitment of qualified PMO staff and consultants and child projects operate in isolation, not capitalizing upon program approach. Assumptions: Recruitment for PMO staff and consultants is successful and not delayed and aggregated reporting mechanism is user friendly and effectively tracks key program wide results. |

# Monitoring and Evaluation (M&E) Plan

- The project results as outlined in the project results framework will be monitored annually and evaluated periodically during project implementation to ensure the project effectively achieves these results. Supported by Component/Outcome Four:  Awareness raising, knowledge management and coordination the project monitoring and evaluation plan will also facilitate learning and ensure knowledge is shared and widely disseminated to support the scaling up and replication of project results.

- Project-level monitoring and evaluation will be undertaken in compliance with UNDP requirements as outlined in the UNDP POPP and UNDP Evaluation Policy. The UNDP Country Office will work with the relevant project stakeholders to ensure UNDP M&E requirements are met in a timely fashion and to high quality standards. Additional mandatory GEF-specific M&E requirements (as outlined below) will be undertaken in accordance with the GEF M&E policy and other relevant GEF policies.

- In addition to these mandatory UNDP and GEF M&E requirements, other M&E activities deemed necessary to support project-level adaptive management will be agreed during the Project Inception Workshop and will be detailed in the Inception Report. This will include the exact role of project target groups and other stakeholders in project M&E activities including the GEF Operational Focal Point. The GEF Operational Focal Point will strive to ensure consistency in the approach taken to the GEF-specific M&E requirements across all GEF-financed projects in the country.

M&E Oversight and monitoring responsibilities:

- Project Coordinator:  The Project Coordinator is responsible for day-to-day project management and regular monitoring of project results and risks, including social and environmental risks. The Project Coordinator will ensure that all project staff maintain a high level of transparency, responsibility and accountability in M&E and reporting of project results. The Project Coordinator will report to the National Project Director and inform the Project Steering Committee, the UNDP Country Office and the UNDP-GEF RTA of any delays or difficulties as they arise during implementation so that appropriate support and corrective measures can be adopted.

- The Project Coordinator will develop annual work plans based on the multi-year work plan included in Annex A, including annual output targets to support the efficient implementation of the project. The Project Coordinator will ensure that the standard UNDP and GEF M&E requirements are fulfilled to the highest quality. This includes, but is not limited to, ensuring the results framework indicators are monitored annually in time for evidence-based reporting in the GEF PIR, and that the monitoring of risks and the various plans/strategies developed to support project implementation (e.g. gender action plan, stakeholder engagement plan etc.) occur on a regular basis.

- Project Steering Committee/Project Board:  The Project Steering Committee will take corrective action as needed to ensure the project achieves the desired results. The Project Steering Committee will hold project reviews to assess the performance of the project and appraise the Annual Work Plan for the following year. In the project’s final year, the Project Steering Committee will hold an end-of-project review to capture lessons learned and discuss opportunities for scaling up and to highlight project results and lessons learned with relevant audiences. This final review meeting will also discuss the findings outlined in the project terminal evaluation report and the management response.

- Project Implementing Partner:  The Implementing Partner (MARA) is responsible for providing all required information and data necessary for timely, comprehensive and evidence-based project reporting, including results and financial data, as necessary. The Implementing Partner will strive to ensure project-level M&E is undertaken by national institutes and is aligned with national systems so that the data used and generated by the project supports national systems. In this regard the Implementing Partner is responsible for ascertaining the all required information and data necessary from the project’s Co-Implementing Partners MEE and GACC (see VIII Governance and Management arrangements).

- UNDP Country Office:  The UNDP Country Office will support the Project Coordinator as needed, including through annual supervision missions. The annual supervision missions will take place according to the schedule outlined in the annual work plan. Supervision mission reports will be circulated to the project team and Project Steering Committee within one month of the mission. The UNDP Country Office will initiate and organize key GEF M&E activities including the annual GEF PIR, the independent mid-term review and the independent terminal evaluation. The UNDP Country Office will also ensure that the standard UNDP and GEF M&E requirements are fulfilled to the highest quality.

- The UNDP Country Office is responsible for complying with all UNDP project-level M&E requirements as outlined in the UNDP POPP. This includes ensuring the UNDP Quality Assurance Assessment during implementation is undertaken annually; that annual targets at the output level are developed and monitored and reported using UNDP corporate systems; the regular updating of the ATLAS risk log; addressing environmental and social grievances and, the updating of the UNDP gender marker on an annual basis based on gender mainstreaming progress reported in the GEF PIR and the UNDP ROAR. Any quality concerns flagged during these M&E activities (e.g. annual GEF PIR quality assessment ratings) must be addressed by the UNDP Country Office and the Project Coordinator.

- The UNDP Country Office will retain all M&E records for this project for up to seven years after project financial closure to support ex-post evaluations undertaken by the UNDP Independent Evaluation Office (IEO) and/or the GEF Independent Evaluation Office (IEO).

- UNDP-GEF Unit:  Additional M&E and implementation quality assurance and troubleshooting support will be provided by the UNDP-GEF Regional Technical Advisor and the UNDP-GEF Directorate as needed.

- Audit: The project will be audited as per UNDP Financial Regulations and Rules and applicable audit policies on NIM implemented projects.

Additional GEF monitoring and reporting requirements:

- Inception Workshop and Report:  A project inception workshop will be held within three months after the project document has been signed by all relevant parties to, amongst others:

        - Re-orient project stakeholders to the project strategy /approach and discuss any changes in the overall context that influence project strategy and implementation;

        - Discuss the roles and responsibilities of the project team, including reporting and communication lines and conflict resolution mechanisms;

        - Review the results framework and finalize the indicators, means of verification and monitoring plan;

        - Discuss reporting, monitoring and evaluation roles and responsibilities and finalize the M&E budget; identify national/regional institutes to be involved in project-level M&E; discuss the role of the GEF OFP in M&E;

        - Update and review responsibilities for monitoring the various project plans and strategies, including the risk log; SESP and other safeguard requirements; project grievance mechanisms; the gender strategy; the knowledge management strategy, and other relevant strategies;

        - Review financial reporting procedures and mandatory requirements, and agree on the arrangements for the annual audit; and

        - Plan and schedule Project Steering Committee meetings and finalize the first-year annual work plan.

- The Project Coordinator will draft the inception report for discussion during the Inception Workshop and finalize the inception report no later than one month after the inception workshop. The inception report will be cleared by the UNDP Country Office and the UNDP-GEF Regional Technical Adviser and will be approved by the Project Steering Committee.

- GEF Project Implementation Report (PIR):  The Project Coordinator, the UNDP Country Office, and the UNDP-GEF Regional Technical Advisor will provide objective input to the annual GEF PIR covering the reporting period July (previous year) to June (current year) for each year of project implementation. The Project Coordinator will ensure that the indicators included in the project results framework are monitored annually in advance of the PIR submission deadline so that progress can be reported in the PIR. Any environmental and social risks and related management plans will be monitored regularly, and progress will be reported in the PIR.

- The PIR submitted to the GEF will be shared with the Project Steering Committee. The UNDP Country Office will coordinate the input of the GEF Operational Focal Point and other stakeholders to the PIR as appropriate. The quality rating of the previous year’s PIR will be used to inform the preparation of the subsequent PIR.

- Lessons learned and knowledge generation:  Results from the project will be disseminated within and beyond the project intervention area through existing information sharing networks and forums. The project will identify and participate, as relevant and appropriate, in scientific, policy-based and/or any other networks, which may be of benefit to the project. The project will identify, analyze and share lessons learned that might be beneficial to the design and implementation of similar projects and disseminate these lessons widely, including uploading project publications to UNDP’s resource platform. There will be continuous information exchange between this project and other projects of similar focus in the same country, region and globally.

- GEF Core Indicators: The GEF Core Indicators will be assessed and evaluated using the template for GEF Core Indicator reporting. This will be done by the PMU in preparation for the project’s Midterm Review and Terminal Evaluation (and Program Synthesis) as part of the project and program reporting. See Annex T for details about data on the selected Core Indicators for this project.

- Independent Mid-term Review (MTR):  An independent mid-term review process will begin after the second PIR has been submitted to the GEF, and the MTR report will be submitted to the GEF in the same year as the 3rd PIR. The MTR findings and responses outlined in the management response will be incorporated as recommendations for enhanced implementation during the final half of the project’s duration. The terms of reference, the review process and the MTR report will follow the standard templates and guidance prepared by the UNDP IEO for GEF-financed projects available on the UNDP Evaluation Resource Center (ERC). As noted in this guidance, the evaluation will be ‘independent, impartial and rigorous’. The consultants that will be hired to undertake the assignment will be independent from organizations that were involved in designing, executing or advising on the project to be evaluated. The GEF Operational Focal Point and other stakeholders will be involved and consulted during the terminal evaluation process. Additional quality assurance support is available from the UNDP-GEF Directorate. The final MTR report will be available in English and will be cleared by the UNDP Country Office and the UNDP-GEF Regional Technical Adviser and approved by the Project Steering Committee.

- Terminal Evaluation (TE):  An independent terminal evaluation (TE) will take place upon completion of all major project outputs and activities. The terminal evaluation process will begin three months before operational closure of the project allowing the evaluation mission to proceed while the project team is still in place, yet ensuring the project is close enough to completion for the evaluation team to reach conclusions on key aspects such as project sustainability. The Project Coordinator will remain on contract until the TE report and management response have been finalized. The terms of reference, the evaluation process and the final TE report will follow the standard templates and guidance prepared by the UNDP IEO for GEF-financed projects available on the UNDP Evaluation Resource Center. As noted in this guidance, the evaluation will be ‘independent, impartial and rigorous’. The consultants that will be hired to undertake the assignment will be independent from organizations that were involved in designing, executing or advising on the project to be evaluated. The GEF Operational Focal Point and other stakeholders will be involved and consulted during the terminal evaluation process. Additional quality assurance support is available from the UNDP-GEF Directorate. The final TE report will be cleared by the UNDP Country Office and the UNDP-GEF Regional Technical Adviser and will be approved by the Project Steering Committee.

- The UNDP Country Office will include the planned project terminal evaluation in the UNDP Country Office evaluation plan and will upload the final terminal evaluation report in English and the corresponding management response to the UNDP Evaluation Resource Centre (ERC). Once uploaded to the ERC, the UNDP IEO will undertake a quality assessment and validate the findings and ratings in the TE report and rate the quality of the TE report.  The UNDP IEO assessment report will be sent to the GEF IEO along with the project terminal evaluation report.

- Final Report: The project’s terminal PIR along with the terminal evaluation (TE) report and corresponding management response will serve as the final project report package. The final project report package shall be discussed with the Project Steering Committee during an end-of-project review meeting to discuss lesson learned and opportunities for scaling up.

Program level monitoring & evaluation:

- Progress towards program level results will also be regularly monitored and evaluated, under Component 4 of the project.  Separate program level M&E procedures will be implemented as described below.

- Program Inception Workshop and Report:  Synchronized with the Project Inception Workshop, a Program Inception Workshop will be held to:

- Re-orient program stakeholders to the program strategy/approach and discuss changes in the overall context that influence program implementation;

- Clarify roles and responsibilities of the coordination team, including the C-SAP 2 PMO, the Program Coordination Agency (UNDP), other participating GEF Agencies (FAO, World Bank), and the project teams of the other C-SAP child projects, including reporting and communication lines and conflict resolution mechanisms;

- Review the program results framework and finalize the indicators and program targets, means of verification and monitoring plan;

- Discuss program level reporting, monitoring & evaluation roles and responsibilities, and finalize the M&E budget; discuss the role of the GEF OFP in M&E;

- Update and review responsibilities for consolidating the inputs from monitoring the various project plans and strategies, including the risk logs; SESPs, and other safeguard requirements (as required by individual GEF Agency policies); project grievance mechanisms; gender strategies and mainstreaming plans; the knowledge management strategy, and other relevant strategies;

- Plan and schedule Program Steering Committee meetings.

- In addition, the program inception report will be reviewed and discussed at the draft inception workshop. The draft will be finalized (incorporating steering committee comments) no later than one month after the inception workshop. The inception report will be cleared by the UNDP Country Office and the UNDP-GEF Regional Technical Adviser and will be approved by the Program Steering Committee

- Program Coordination: The three GEF Agencies (FAO, UNDP and World Bank) supporting the C-SAP program will exchange annual reports on project implementation as well as synchronize as much as possible the timing and modality of project inception workshops, mid-term reviews and terminal evaluations, and coordinate program and project communication activities. Each project will have its own internal monitoring and evaluation process including regular reporting. In addition, the C-SAP 2 IAS project will assume program coordination functions through a Technical Program Advisor, who will monitor and evaluate the progress and effectiveness of the five child projects. The Technical Program Advisor will help ensure efficient program implementation, ensuring the program remains consistent with the overall Program objectives and outcomes, by monitoring activities by other initiatives and liaising with government line ministries, the institutional sector delivering technical support to the governmental partners, with civil society organizations, and with the private sector.

- Program Steering Committee:  The Program Steering Committee will provide strategic oversight to ensure the desired results at the program level. The Program Steering Committee will hold program reviews to assess the performance of the program, as indicated by achievement of program outcomes. In the project’s final year, the Program Steering Committee will hold an end-of-program review meeting to capture lessons learned and discuss opportunities for scaling up and to highlight project results and lessons learned with relevant audiences. This final review meeting will also discuss the findings outlined in the program project terminal evaluation report and the management response. The Program Steering Committee will be organized annually on a rotational basis among each of the C-SAP child projects.

- UNDP’s responsibility is to ensure that the program adheres to program level M&E requirements and support the PMO to fulfil these requirements, such as coordinate the national or regional institutions regarding the monitoring and reporting on the progress towards achieving the agreed Program outcomes, report to the Program Steering Committee, and report back to the GEF through the annual program report.

- C-SAP Program Annual Report:  The Program Coordination Officer, with inputs from each of the project managers of the child projects, the UNDP Country Office and the UNDP-GEF Regional Technical Advisor, and other C-SAP GEF Agencies, will prepare the annual C-SAP program report covering the reporting period July (previous year) to June (current year) for each year of program implementation. The report will highlight program level activities and achievements that go beyond those of the individual child projects as presented in PIRs. And, the report will include progress towards program level outcomes, major milestones achieved through overall program implementation, and engagement in regional and/or global for as a means of advancing the overall program goal. A template for the annual program report will be developed in year 1 of the project. The program annual report will be shared with the Program Steering Committee and submitted to the GEF. The UNDP Country Office will coordinate the input of the GEF Operational Focal Point and other stakeholders as appropriate (e.g., with the other GEF agencies on the C-SAP program and their child project governance bodies).

- Independent Evaluation Synopsis: The program will be subjected to at least two independent external evaluation synopsis one at the project midterm and one 3 months prior to project finalization.  The Terms of Reference for these Synopsis will be integrated into the TOR for the C-SAP 2 IAS project MTR and TE, prepared by the UNDP CO based on guidance from the UNDP-GEF Regional Coordinating Unit. The evaluation team completing the coordination project evaluation will also carry out the program level evaluation synopsis. Separate reports will be delivered, one each for the project and for the program. Mid-term reviews and terminal evaluations will also be conducted for each of the other child project led by respective GEF Agencies, which will feed into the program level review and evaluation exercise. The MTR and TE processes will be synchronized as much as practicable to occur concurrently.

Mandatory GEF M&E Requirements and M&E Budget:

- Project and program level M&E activities, responsibilities, indicative budget and timeframes are summarized in Table 10 below. The budget will be covered under the Component 4 of the C-SAP 2 IAS project.

Table 10: Project and Program M&E Requirements and Budget

| GEF M&E requirements | Primary responsibility | Indicative costs to be charged to the Project Budget [1] (USD) |  | Time frame |
| --- | --- | --- | --- | --- |
|  |  | GEF | Co-financing |  |
| Project level monitoring & evaluation: |  |  |  |  |
| Inception Workshop | Project Coordinator, MARA | USD 10,000 | USD 10,000 | Within three months of project document signature |
| Inception Workshop Report | Project Coordinator | None | None | Within one month after inception workshop |
| Standard UNDP monitoring and reporting requirements as outlined in the UNDP POPP | UNDP CO | None | None | Quarterly, annually |
| Risk management | Project Coordinator, UNDP CO | None | USD 10,000 | Quarterly, annually |
| Monitoring of indicators in project results framework | Project Coordinator, M&E/Safeguards Officer, | None | USD 20,000 | Annually before PIR |
| GEF Project Implementation Review (PIR) | Project Coordinator, UNDP CO and UNDP-GEF team | None | USD 5,000 | Annually |
| NIM Audit as per UNDP audit policies (tendered to auditing company) | UNDP CO | Per year: USD 5,000 (Total: USD 25,000) | None | Annually or other frequency as per UNDP Audit policies |
| Lessons learned and knowledge generation | Project Coordinator | Per year: USD 3,000 (Total: USD 15,000) | USD 20,000 | Annually |
| Monitoring of environmental and social risks, and corresponding management plans as relevant | Project Coordinator, UNDP CO, M&E/Safeguards Officer, | Per year: USD 1,000 (Total: USD 5,000 | USD 15,000 | On-going |
| Stakeholder Engagement Plan | Project Coordinator, UNDP CO | None | USD 15,000 | On-going |
| Gender Action Plan | Project Coordinator, UNDP CO, M&E/Safeguards Officer. | Per year: USD 1,000 (Total: USD 5,000) | USD 5,000 | On-going |
| Addressing environmental and social grievances | Project Coordinator, UNDP CO | None | USD 3,000 | On-going |
| Project Steering Committee (PSC) meetings (annual, convened on rotational basis among pilot sites) | Project Coordinator, PSC, UNDP CO | Per year: 5,000 (Total: USD 25,000) | USD 10,000 | Annually, organized on a rotational basis among the project provinces |
| Supervision missions | UNDP CO | None | None | Annually |
| Oversight missions | UNDP-GEF team | None [2] | None | Troubleshooting as needed |
| GEF Secretariat learning missions/site visits | UNDP CO, Project Coordinator and UNDP-GEF team | None [2] | None | To be determined. |
| Mid-term assessment of Capacity Development Scorecard | Project Coordinator | None | None | Before mid-term review mission takes place. |
| Independent Mid-term Review (MTR) and management response (same team and timing for program MTR, separate reports) | UNDP CO, PMO and UNDP-GEF team | USD 45,000 | USD 15,000 | Between 2nd and 3rd PIR. |
| Terminal assessment of Capacity Development Scorecard | Project Coordinator | None | None | Before terminal evaluation mission takes place |
| Independent Terminal Evaluation (TE) included in UNDP evaluation plan, and management response (same team and timing for program TE, separate reports) | UNDP CO, PMO and UNDP-GEF team | USD 45,000 | USD 10,000 | At least three months before operational closure |
| Translation of key sections of MTR and TE reports | PMO | None | None | As required. GEF will only accept reports in English. |
| Final Report (includes final PIR, TE report and TE management response) | Project Coordinator, UNDP CO | None | None | At least one month prior to final PSC meeting |
| Sub-total, Indicative Project level M&E COST: |  | USD 175,000 | USD 138,000 |  |
| Program level monitoring & evaluation: |  |  |  |  |
| Program Inception Workshop | UNDP CO, Technical C-SAP Program Advisor | USD 10,000 | USD 10,000 | Coincident with Project Inception Workshop |
| Program Inception Report | UNDP CO, Technical C-SAP Program Advisor | None | None | Within one month after inception workshop |
| Measurement of Means of Verification for Program Progress and Performance (measured on an annual basis) | Technical C-SAP Program Advisor | None | None | Annually |
| Consolidation and evaluation of environmental and social monitoring reports from child projects | Technical C-SAP Program Advisor, with support from M&E/Safeguards Officers for individual child projects | Per year: USD 1,000 (Total: USD 5,000) | USD 5,000 | Annually |
| C-SAP annual program report | Technical C-SAP Program Advisor, UNDP, FAO, World Bank | None | USD 5,000 | Annually |
| Program Steering Committee meetings (annual meetings, held on a rotational basis at child project sites) | Technical C-SAP Program Advisor, Program Steering Committee, UNDP CO | Per year: USD 5,000 (Total: USD 15,000) [3] | USD 15,000 | Annually, organized on a rotational basis among the child projects |
| Mid-Term Review (same MTR team as recruited for project MTR, separate report for program MTR) | UNDP CO, Technical C-SAP Program Advisor, PMO and UNDP-GEF team | USD 15,000 | USD 5,000 | Between 2nd and 3rd PIR. |
| Terminal Evaluation (same TE team as recruited for project TE, separate report for program TE) | UNDP CO, Technical C-SAP Program Advisor, PMO and UNDP-GEF team | USD 10,000 | USD 5,000 | At least three months before operational closure |
| Final Report (includes final annual C-SAP program report, program TE report and TE management response | UNDP CO and Technical C-SAP Program Advisor | None | None | At least one month prior to final Program Steering Committee meeting |
| Sub-total, Indicative Program Level M&E COST: |  | USD 55,000 | USD 45,000 |  |
| TOTAL indicative COST Excluding project team staff time, and UNDP staff and travel expenses |  | USD 230,000 | USD 183,000 |  |
| [1] Excluding project team staff time and UNDP staff time and travel expenses [2] The costs of UNDP Country Office and UNDP-GEF Unit’s participation and time are charged to the GEF Agency Fee [3] The C-SAP 2 IAS project will cover the cost of one Program Steering Committee meeting. The cost of the remining four meetings will be covered by the remaining four C-SAP child projects |  |  |  |  |

# Governance and Management Arrangements

- Roles and responsibilities of the project’s governance mechanism: The project will be implemented following UNDP’s national implementation modality, according to the Standard Basic Assistance Agreement between UNDP and the Government of China, and the Country Programme.

- The Implementing Partner for this project is Ministry of Agriculture and Rural Affairs. The Implementing Partner is the entity to which the UNDP Administrator has entrusted the implementation of UNDP assistance specified in this signed project document along with the assumption of full responsibility and accountability for the effective use of UNDP resources and the delivery of outputs, as set forth in this document. The Implementing Partner is responsible for executing this project. Specific tasks include:

- Project planning, coordination, management, monitoring, evaluation and reporting.  This includes providing all required information and data necessary for timely, comprehensive and evidence-based project reporting, including results and financial data, as necessary. The Implementing Partner will strive to ensure project-level M&E is undertaken by national institutes and is aligned with national systems so that the data used and generated by the project supports national systems. Risk management as outlined in this Project Document;

- Procurement of goods and services, including human resources;

- Financial management, including overseeing financial expenditures against project budgets; Approving and signing the multiyear workplan;

- Approving and signing the combined delivery report at the end of the year; and,

- Signing the financial report or the funding authorization and certificate of expenditures

- The Co -Implementing Partners for the project are, by the request of the IP, MEE/FECO and GACC/ CAIQ. The Co-implementing Partners will be responsible for the financial management, and implementation, of the activities, under the various components, designated to them. The specific activities are outlined in the project document (IV Results and Partnerships, IX Financial Planning and Management, Annex I and Annex U). The Co-Implementing partners will ensure that the assigned tasks and outputs are met, in accordance with the agreed budget and work-plans stated in the Letters of Agreement (LOA) signed, individually, between UNDP China and MEE/FECO and GACC/CAIQ respectively (Annex I).

- UNDP: UNDP is accountable to the GEF for the implementation of this project. This includes oversight of project execution to ensure that the project is being carried out in accordance with agreed standards and provisions. UNDP is responsible for delivering GEF project cycle management services comprising project approval and start-up, project supervision and oversight, and project completion and evaluation. UNDP is responsible for the Project Assurance role of the Project Steering Committee.

- The project organization structure is as follows:

Notes:

*These positions will be supported by governmental co-financing contributions; existing department staff sharing their time. **Specialist support will be provided on an as-needed basis, through short-term contractual arrangements.

- Project Steering Committee:  The Project Steering Committee is responsible for taking corrective action as needed to ensure the project achieves the desired results. In order to ensure UNDP’s ultimate accountability, Project Board decisions should be made in accordance with standards that shall ensure management for development results, best value money, fairness, integrity, transparency and effective international competition.

- In case consensus cannot be reached within the PSC, the UNDP Resident Representative (or their designate) will mediate to find consensus and, if this cannot be found, will take the final decision to ensure project implementation is not unduly delayed.

- Specific responsibilities of the Project Steering Committee include:

- Provide overall guidance and direction to the project, ensuring it remains within any specified constraints;

- Address project issues as raised by the Project Coordinator;

- Provide guidance on new project risks, and agree on possible mitigation and management actions to address specific risks;

- Agree on Project Coordinator’s tolerances as required, within the parameters set by UNDP-GEF, and provide direction and advice for exceptional situations when the Project Coordinator’s tolerances are exceeded;

- Advise on major and minor amendments to the project within the parameters set by UNDP-GEF;

- Ensure coordination between various donor and government-funded projects and programmes;

- Ensure coordination with various government agencies and their participation in project activities;

- Track and monitor co-financing for this project;

- Review the project progress, assess performance, and appraise the Annual Work Plan for the following year;

- Appraise the annual project implementation report, including the quality assessment rating report;

- Ensure commitment of human resources to support project implementation, arbitrating any issues within the project;

- Review combined delivery reports prior to certification by the implementing partner;

- Provide direction and recommendations to ensure that the agreed deliverables are produced satisfactorily according to plans;

- Address project-level grievances;

- Approve the project Inception Report, Mid-term Review and Terminal Evaluation reports and corresponding management responses;

- Review the final project report package during an end-of-project review meeting to discuss lesson learned and opportunities for scaling up.

- Ensure that UNDP Social and Environmental Safeguards Policy is applied throughout project implementation; and, address related grievances as necessary.

- The composition of the PSC will include the following member entities, subject to confirmation during the project inception period. Observers may be included at PSC meetings upon the agreement of the PSC members.

- Ministry of Finance (MOF)

- Ministry of Agriculture and Rural Affairs (MARA)

- Ministry of Ecology and Environment (MEE)/Foreign Economic Cooperation Office (FECO)

- General Administration of Customs (GACC)/ Chinese Academy of Inspection and Quarantine (CAIQ)

- Chongqing Agriculture and Rural Affairs Committee (ChARAC)

- Hainan Agriculture and Rural Affairs Department (HaARAD)

- All China Women’s Federation (ACWF)

- United Nations Development Program (UNDP)

- The first annual Project Steering Committee meetings will be held in Beijing and subsequently the Project Steering Committee meetings will be convened on a rotational basis between Chongqing Municipality and Hainan Province, providing the committee members to observe first-hand progress and issues. The indicative locations of the Program Steering Committee meetings are subject to agreement at the Program Inception Workshop and adjustments, based on Program Steering Committee agreement, during implementation.

- The Project Steering Committee will include the following roles:

- Project Executive: Is an individual who represents ownership of the project and chairs the Project Steering Committee. The Executive is normally the national counterpart for nationally implemented projects. The Project Executive (National Project Director) is: Deputy Director General, Department of Science, Technology and Education, MARA. The Executive is ultimately responsible for the project, supported by the Senior Beneficiary and Senior Supplier.  The Executive’s role is to ensure that the project is focused throughout its life cycle on achieving its objectives and delivering outputs that will contribute to higher level outcomes. The executive has to ensure that the project gives value for money, ensuring cost-conscious approach to the project, balancing the demands of beneficiary and suppler.

- Specific Responsibilities: (as part of the above responsibilities for the Project Steering Committee)

- Ensure that there is a coherent project organization structure and logical set of plans;

- Set tolerances in the AWP and other plans as required for the Project Coordinator;

- Monitor and control the progress of the project at a strategic level;

- Ensure that risks are being tracked and mitigated as effectively as possible;

- Brief relevant stakeholders about project progress;

- Organize and chair Project Steering Committee meetings.

- Beneficiary Representative: Individuals or groups representing the interests of those who will ultimately benefit from the project. Their primary function within the board is to ensure the realization of project results from the perspective of project beneficiaries. Often civil society representative(s) can fulfil this role. The Beneficiary representative is: China All Women’s Federation.

- Development Partners: Individuals or groups representing the interests of the parties concerned that provide funding and/or technical expertise to the project. The Development Partners are: Ministry of Finance, Ministry of Agriculture and Rural Affairs, Ministry of Ecology and Environment, General Administration of Customs, Chongqing Municipality, Hainan province.

- Project Assurance: UNDP performs the quality assurance role and supports the Project Steering Committee and Project Management Unit by carrying out objective and independent project oversight and monitoring functions. This role ensures appropriate project management milestones are managed and completed. The PSC cannot delegate any of its quality assurance responsibilities to the Project Coordinator. UNDP provides a three – tier oversight services involving the UNDP Country Offices and UNDP at regional and headquarters levels. Project assurance is totally independent of the Project Management function.

- Project Management Office: Project management services will be delivered by the Project Management Office, staffed as follows:

- Project Coordinator: The Project Coordinator has the authority to run the project on a day-to-day basis on behalf of the Implementing Partner within the constraints laid down by the Project Steering Committee. The Implementing Partner appoints the Project Coordinator, who must be different from the Implementing Partner’s representative in the Project Steering Committee. The Project Coordinator’s primary responsibility is to ensure that the project produces the results specified in the project document, to the required standard of quality and within the specified constraints of time and cost. The Project Coordinator will inform the Project Steering Committee and the Project Assurance roles of any delays or difficulties as they arise during implementation so that appropriate support and corrective measures can be adopted. The Project Coordinator will remain on contract until the Terminal Evaluation report and the corresponding management response have been finalized and the required tasks for operational closure and transfer of assets are fully completed.

- The Implementing Partner appoints the Project Coordinator, who will be a Project Coordinator providing technical assistants to the project as well as undertaking managerial duties. The Project Coordinator should be different from the Implementing Partner’s representative in the Project Steering Committee.

- Specific responsibilities of the Project Coordinator include:

- Manage the overall conduct of the project.

- Perform Secretariat duties for the PSC

- Plan the activities of the project and monitor progress against the approved workplan.

- Execute activities by managing personnel, goods and services, training and low-value grants, including drafting terms of reference and work specifications, and overseeing all contractors’ work.

- Monitor events as determined in the project monitoring plan, and update the plan as required.

- Provide support for completion of assessments required by UNDP, spot checks and audits.

- Manage requests for the provision of UNDP financial resources through funding advances, direct payments or reimbursement using the FACE form.

- Monitor financial resources and accounting to ensure the accuracy and reliability of financial reports.

- Monitor progress, watch for plan deviations and make course corrections when needed within project board-agreed tolerances to achieve results.

- Ensure that changes are controlled and problems addressed.

- Perform regular progress reporting to the project board as agreed with the board, including measures to address challenges and opportunities.

- Prepare and submit financial reports to UNDP on a quarterly basis.

- Manage and monitor the project risks – including social and environmental risks - initially identified and submit new risks to the Project Board for consideration and decision on possible actions if required; update the status of these risks by maintaining the project risks log;

- Capture lessons learned during project implementation.

- Prepare revisions to the multi-year workplan, as needed, as well as annual and quarterly plans if required.

- Prepare the inception report no later than one month after the inception workshop.

- Ensure that the indicators included in the project results framework are monitored annually in advance of the GEF PIR submission deadline so that progress can be reported in the GEF PIR.

- Prepare the GEF PIR;

- Assess major and minor amendments to the project within the parameters set by UNDP-GEF;

- Monitor implementation plans including the gender action plan, stakeholder engagement plan, and any environmental and social management plans;

- Monitor and track progress against the GEF Core indicators.

- Support the Mid-term review and Terminal Evaluation process.

- Help establish and maintain the IAS coordination bodies.

- Facilitate the national and local planning processes and provide technical input to said processes

- Provide project advocacy among key stakeholders.

- Oversee the exchange and sharing of experiences and lessons learned with relevant projects nationally and internationally.

- Assist local government units, others with development of essential skills through training workshops and on the job training thereby increasing their institutional capabilities.

- Encourage staff, partners and consultants such that strategic, intentional and demonstrable efforts are made to actively include women in the project, including activity design and planning, budgeting, staff and consultant hiring, subcontracting, purchasing, formal community governance and advocacy, outreach to social organizations, training, participation in meetings; and access to program benefits.

- Assists and advises the local government focal points and service providers responsible for activity implementation at the demonstration landscapes.

- Carry out regular, announced and unannounced inspections of all sites and the activities in the field.

- Project Management Office (PMO): The PMO is located at the Department of Science, Technology and Education, within the Ministry of Agriculture and Rural Affairs. It will be led by the Project Coordinator who coordinates the overall project as well as undertaking the administrative work of the Project Management Office (PMO), while also being responsible for financial accounting and reporting, and procurement of goods and services for the implementation of the C-SAP 2 IAS project. The Project Coordinator will also play a vital role in coordinating the M&E Specialist in the monitoring and evaluation of the project. The PMO’s M&E Specialist is responsible for the C-SAP IAS 2 project’s and C-SAP Program’s monitoring and evaluation, including managing the project’s Mid-term Review and Terminal Evaluation, as well as the Program Synthesis. The M&E Specialist will also act as the PMO’s gender and safeguard focal point and will as such be the focal point for the projects Grievance Redress Mechanism. Finally, a C-SAP Technical Program Advisor who will work on program related matters, will ensure harmonization of approaches and coherence in implementation processes across the overall program. The Project Coordinator is budgeted as full-time position, fully charged against the GEF implementation grant for the project through a long-term contractual arrangement with the Implementing Partner, whereas the M&E Specialist is a co-financed position. See Annex C for Terms of Reference.

- The positions of Project Coordinator will be jointly recruited by MARA and UNDP nationally, and the desired candidate would be someone with relevant experience. The Project Coordinator should be delegated with sufficient decision-making authority to allow effective project management. The other positions of the PMO will also be recruited nationally. A Chief Technical Advisor who will provide project level technical advisory support to both MARA, MEE and GACC will be selected jointly together with UNDP by the three entities. The terms of reference (TOR) for long-term positions are compiled in Annex C.

- Short-term support will be procured as needed among qualified national and local consultants, institutes, and civil society organizations through competitive bidding processes. The types of expertise envisaged on short-term assignments include but are not limited to the following:

- Policy specialist;

- Resource economist;

- IAS specialist;

- Capacity development specialist;

- Gender and ethnic minorities specialist

- Public awareness and education, including knowledge, attitudes and practices (KAP) survey;

- Monitoring and evaluation;

- Agricultural technical expert

- Rural development expert

- Information management, including with geographic information systems (GIS)

- Knowledge management and communication

- For certain specialized services, including leading the two independent evaluations, recruitment will be made internationally, using the UNDP procurement system.

Governance role for project target groups:

- The Project Steering Committee will be the main governance organ of the project providing oversight and guidance. During the implementation central governance mechanisms will be established in form of National and Provincial IAS Coordination Groups which are to provide strategic oversight and direction of the implementation of IAS prevention, control and management at national and provincial levels.

- In addition, participatory processes involving experts and interested parties will be created in form of: 1) non-permanent stakeholder groups for the preparations of the national and provincial IAS Strategy and Action Plans.; 2) non-permanent expert groups formed in connection with the management plan processes in Hainan and Chongqing. Farmer communities and other stakeholders involved in the project 1) will provide for a forum for collection of feedback and suggestions and 2) be engaged through the, before mentioned, non-permanent stakeholder groups in the development of IAS management plans for the project targeted agricultural landscapes in Wenchang and Bishan. Furthermore, stakeholders, direct and indirect beneficiaries can engage with the project through one or more of its communication channels and can, if needed, make use of the established grievance mechanisms.

Program Governance and Management Arrangements:

- The C-SAP program consists of five child projects; UNDP is the PCA and the GEF Agency for three of the five child projects. FAO and World Bank are each implementing one child project, as indicated below in Table 10.

- Program Steering Committee: The Program Steering Committee will be established, with participation of the three GEF Agencies and the national and subnational implementing partners, to supervise and guide program implementation. The proposed composition of the Program Steering Committee includes representatives from the following partners:

- Ministry of Finance (MOF)

- Ministry of Agriculture and Rural Affairs (MARA)

- Ministry of Ecology and Environment (MEE) /Foreign Economic Cooperation Office (FECO)

- General Administration of Customs (GACC) / Chinese Academy of Inspection and Quarantine (CAIQ)

- Hubei Agriculture and Rural Affairs Department (HuARAD)

- Hainan Agriculture and Rural Affairs Department (HaARAD)

- Food and Agricultural Organization (FAO)

- World Bank (WB)

- All China Women’s Federation (ACWF)

- United Nations Development Program (UNDP)

- The chairperson of the Program Steering Committee will be the Deputy Director General, Department of Science, Technology and Education, MARA.

- Annual Program Steering Committee meetings will be convened on a rotational basis among the child projects, enabling the committee members to observe first-hand progress and issues. The indicative locations of the Program Steering Committee meetings are subject to determination at the Program Inception Workshop and adjustments, based on Program Steering Committee agreement, during implementation.

- A Technical C-SAP Program Advisor, guided by and working closely with the C-SAP 2 IAS Project Coordinator, will provide program level support, including 1) ensuring program level coherence for achievement; 2) maintaining alignment of the C-SAP program to government agenda through facilitating cross-sectoral stakeholder engagement and acting as a go-between with national and international partners; 3) provide similar support to the C-SAP 2 IAS project and (4) performing secretariat duties for the Program Steering Committee. The coordinator’s work will work exclusively on program matters supporting program technical alignment, monitor program training and demonstration activities under the programs five projects (i.e. C-SAP 1, C-SAP 2, C-SAP 3, C-SAP 4, and C-SAP 5) and together with the program’s projects prepare and disseminate news, lessons learned and success stories, as well as coordinate the C-SAP 2 (IAS) project’s knowledge management work with the C-SAP 1 and 5 projects.  The Technical C-SAP Program Advisor will further assist in developing government memos and briefs etc. related to the program, and visualize the programm’s successes on various media. The Technical C-SAP Program Advisor will also support the projects M&E Specialist in the the program’s monitoring and evaluation work.  The coordinator will also closely liaison with the C-SAP 1 FAO project in connection with its development of the Program Knowledge Management platform. As noted, the C-SAP Technical C-SAP Program Advisor is budgeted as full-time position, fully charged against the GEF implementation grant for the project through a long-term contractual arrangement with the Implementing Partner. The PMO M&E Specialist will, in addition her/his project related responsibilities also provide program level support, such as 1) delivering program level monitoring and evaluation (M&E), including completion of the annual program reports 2) cooperating with and consolidating information from the M&E Officers on the separate child projects; and 3) support the C-SAP 2 IAS project in its monitoring and evaluation activities. The M&E Specialist is a co-financed position.

Table 12: List of projects under the C-SAP program

| Project Title / Target Geographies | SESP Risk Rating | GEF Agency / Contact person | Implementing Partner | Proposed GEF Implementation Grant, USD | Co-financing, USD |
| --- | --- | --- | --- | --- | --- |
| C-SAP 1 On-farm conservation and sustainable use of genetic diversity of crops originated in China Target geography: Yunnan, Hebei and Liaoning, Heilongjiang Provinces | Low | FAO | MARA | 2,725,688 | 18,480,000 |
| C-SAP 2 Strengthening coordinated approaches to reduce invasive alien species (IAS) threats to globally significant agrobiodiversity and agroecosystems in China Target geography: National, Hainan province (Wenchang city) and Chongqing Municipality (Bishan district) | Moderate | UNDP Gabriel Jaramillo | MARA | 2,789,908 | 18,900,000 |
| C-SAP 3 Participatory in-situ conservation and sustainable use of agrobiodiversity in Hainan Target geography: Hainan province (Qionghai County, Baisha County, Haikou County and Qiongzhong County) | Moderate | UNDP Gabriel Jaramillo | Hainan Agricultural Department | 1,509,633 | 10,200,000 |
| C-SAP 4 Conservation and sustainable use of indigenous agricultural genetic diversity in Hubei Target geography: Hubei province (Danjiangkou Reservoir Area) | Moderate | UNDP Gabriel Jaramillo | Hubei Agricultural Department | 1,509,633 | 10,200,000 |
| C-SAP 5 Climate-smart management of grassland ecosystems Target geographies: Qilian Mountain (Qilian County of Qinghai Province and Shandan County of Gansu Province) | Low | World Bank | MARA | 3,769,083 | 25,500,000 |
| Total: |  |  |  | 12,303,945 | 83,280,000 |

# Financial Planning and Management

- The total cost of the project is 21,689,908 USD.  This is financed through a GEF  grant of USD 2,789,908 and USD 18,900,000 in parallel co-financing.  UNDP, as the GEF Implementing Agency, is responsible for the execution of the GEF resources and the cash co-financing transferred to UNDP bank account only.

- Parallel co-financing:  The actual realization of project co-financing will be monitored during the mid-term review and terminal evaluation process and will be reported to the GEF. The planned parallel co-financing will be used as follows:

| Co-financing source | Co-financing type | Co-financing amount $ | Planned Activities/Outputs | Risks | Risk Mitigation Measures |
| --- | --- | --- | --- | --- | --- |
| Recipient Government: Ministry of Agriculture and Rural Affairs | Grant | 1,520,000 | Inputs across all Components, particularly Component 2 | Low | PMO will work with MARA on linking co-financing with project outputs and will monitor/ report annually. PMO will respond to lack of agreed support in a follow up with MARA and seek UNDP assistance if needed. |
|  | In-kind | 600,000 |  |  |  |
| Recipient Government: Ministry of Ecology and Environment | Grant | 4,400,000 | Inputs across all Components, particularly Component 2 | Low | PMO will work with MEE on linking co-financing with project outputs and will monitor/ report annually. PMO will respond to lack of agreed support in a follow up with MEE and seek UNDP assistance if needed. |
|  | In-kind | 200,000 |  |  |  |
| Recipient Government: General Administration of Customs | Grant | 3,820,000 | Inputs across all Components, particularly Component 2 | Low | PMO will work with GACC on linking co-financing with project outputs and will monitor/ report annually. PMO will respond to lack of agreed support in a follow up with GACC and seek UNDP assistance if needed. |
|  | In-kind | 200,000 |  |  |  |
| Department of Agricultural and Rural Affairs, Hainan Province (DARA/HP) | Grant | 3,050,000 | Inputs across all Components, particularly Component 3 | Low | PMO will work with DARA/HP on linking co-financing with project outputs and will monitor/ report annually. PMO will respond to lack of agreed support in a follow up with DARA/HP and seek UNDP assistance if needed. |
|  | In-kind | 100,000 |  |  |  |
| Department of Agricultural and Rural Affairs Bishan District (DARA/BD), Chongqing Municipality | Grant | 3,150,000 | Inputs across all Components, particularly Component 3 | Low | PMO will work with DARA/BD on linking co-financing with project outputs and will monitor/ report annually. PMO will respond to lack of agreed support in a follow up with DARA/BD and seek UNDP assistance if needed. |
| Beijing Huaheng Rongtong Technology Co. Ltd (BHRTcl) | Grant | 600,000 | Component 2 | Low | PMO will work with BHRTcl on linking co-financing with project outputs and will monitor/ report annually. PMO will respond to lack of agreed support in a follow up with BHRTcl and seek UNDP assistance if needed. |
| Wenchang Wenting Agritourism and Ecological Agriculture Co. Ltd (WWAEAcl) | Grant | 630,000 | Component 3 | Low | PMO will work with WWAEAcl on linking co-financing with project outputs and will monitor/ report annually. PMO will respond to lack of agreed support in a follow up with WWAEAcl and seek UNDP assistance if needed. |
| Chongqing Late Orange Planting Farmers’ Cooperative (CLOPFC) | Grant | 630,000 | Component 3 | Low | PMO will work with CLOPFC on linking co-financing with project outputs and will monitor/ report annually. PMO will respond to lack of agreed support in a follow up with CLOPFC and seek UNDP assistance if needed. |
| Total $ |  | 18,900,000 |  |  |  |

- Budget Revision and Tolerance:  As per UNDP requirements outlined in the UNDP POPP, the Project Steering Committee will agree on a budget tolerance level for each plan under the overall annual work plan allowing the Project Coordinator to expend up to the tolerance level beyond the approved project budget amount for the year without requiring a revision from the Project Steering Committee. Should the following deviations occur, the Project Coordinator and UNDP Country Office will seek the approval of the UNDP-GEF team to ensure accurate reporting to the GEF: a) Budget re-allocations among components in the project with amounts involving 10% of the total project grant or more; b) Introduction of new budget items/or components that exceed 5% of original GEF allocation.

- Any over expenditure incurred beyond the available GEF grant amount will be absorbed by non-GEF resources (e.g. UNDP TRAC or cash co-financing).

- Refund to GEF:  Should a refund of unspent funds to the GEF be necessary, this will be managed directly by the UNDP-GEF Unit in New York.

- Project Closure:  Project closure will be conducted as per UNDP requirements outlined in the UNDP POPP. On an exceptional basis only, a no-cost extension beyond the initial duration of the project will be sought from in-country UNDP colleagues and then the UNDP-GEF Executive Coordinator.

- Operational completion: The project will be operationally completed when the last UNDP-financed inputs have been provided and the related activities have been completed. This includes the final clearance of the Terminal Evaluation Report (that will be available in English) and the corresponding management response, and the end-of-project review Project Steering Committee meeting. The Implementing Partner through a Project Steering Committee decision will notify the UNDP Country Office when operational closure has been completed. At this time, the relevant parties will have already agreed and confirmed in writing on the arrangements for the disposal of any equipment that is still the property of UNDP.

- Transfer or disposal of assets: In consultation with the NIM Implementing Partner and other parties of the project, UNDP programme manager (UNDP Resident Representative) is responsible for deciding on the transfer or other disposal of assets. Transfer or disposal of assets is recommended to be reviewed and endorsed by the project board following UNDP rules and regulations. Assets may be transferred to the government for project activities managed by a national institution at any time during the life of a project. In all cases of transfer, a transfer document must be prepared and kept on file.

- Financial completion:  The project will be financially closed when the following conditions have been met: a) The project is operationally completed or has been cancelled; b) The Implementing Partner has reported all financial transactions to UNDP; c) UNDP has closed the accounts for the project; d) UNDP and the Implementing Partner have certified a final Combined Delivery Report (which serves as final budget revision).

- The project will be financially completed within 12 months of operational closure or after the date of cancellation. Between operational and financial closure, the implementing partner will identify and settle all financial obligations and prepare a final expenditure report. The UNDP Country Office will send the final signed closure documents including confirmation of final cumulative expenditure and unspent balance to the UNDP-GEF Unit for confirmation before the project will be financially closed in Atlas by the UNDP Country Office.

# Total Budget and Work Plan

| Total Budget and Work Plan |  |  |  |
| --- | --- | --- | --- |
| Atlas Proposal or Award ID: | 00096221 | Atlas Primary Output Project ID: | 00100197 |
| Atlas Proposal or Award Title: | Reduce IAS threat to Agrobiodiversity. |  |  |
| Atlas Business Unit | CHN10 |  |  |
| Atlas Primary Output Project Title | Strengthening coordinated approaches to reduce invasive alien species (IAS) threats to globally significant agrobiodiversity and agroecosystems in China |  |  |
| UNDP/GEF PIMS No. | 5821 |  |  |
| Implementing Partner | Ministry of Agriculture and Rural Affairs |  |  |

| GEF Component/Atlas Activity | Responsible Party/[1] | Fund ID | Donor Name | Atlas Budgetary Account Code | ATLAS Budget Description | Amount Year 1 (USD) | Amount Year 2 (USD) | Amount Year 3 (USD) | Amount Year 4 (USD) | Amount Year 5 (USD) | Total (USD) | See Budget Note: |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | (Atlas Implementing Agent) |  |  |  |  |  |  |  |  |  |  |  |
| COMPONENT 1: Strengthened Enabling Environment | MARA (Output 1.1, 1.2, 1.3 & 1.4) | 62000 | GEF | 71300 | Local Consultants | 28,290 | 57,160 | 27,600 | 24,600 | 11,600 | 149,250 | 1 |
|  |  |  |  | 71600 | Travel | 0 | 6,000 | 6,000 | 4,000 | 0 | 16,000 | 2 |
|  |  |  |  | 72100 | Contractual Services-Companies | 24,065 | 23,635 | 15,400 | 10,400 | 0 | 73,500 | 3 |
|  |  |  |  | 74500 | Miscellaneous | 4,500 | 0 | 0 | 0 | 0 | 4,500 | 4 |
|  |  |  |  | 75700 | Training, Workshops and Confer | 3,000 | 19,000 | 11,000 | 0 | 2,000 | 35,000 | 5 |
|  |  |  |  | Sub-total Component 1 (MARA) |  | 59,855 | 105,795 | 60,000 | 39,000 | 13,600 | 278,250 |  |
|  | MEE (Output 1.1, 1.2, 1.3 & 1.4) | 62000 | GEF | 71300 | Local Consultants | 32,000 | 33,250 | 7,000 | 4,000 | 0 | 76,250 | 6 |
|  |  |  |  | 71600 | Travel | 0 | 1,000 | 1,000 | 2,000 | 0 | 4,000 | 7 |
|  |  |  |  | 72100 | Contractual Services-Companies | 48,875 | 75,375 | 8,000 | 4,000 | 0 | 136,250 | 8 |
|  |  |  |  | 74500 | Miscellaneous | 1,000 | 0 | 0 | 0 | 0 | 1,000 | 9 |
|  |  |  |  | 75700 | Training, Workshops and Confer | 0 | 4,500 | 5,000 | 0 | 0 | 9,500 | 10 |
|  |  |  |  | Sub-total Component 1 (MEE) |  | 81,875 | 114,125 | 21,000 | 10,000 | 0 | 227,000 |  |
|  | GACC (Output 1.1, 1.2, 1.3 & 1.4) | 62000 | GEF | 71300 | Local Consultants | 13,250 | 14,000 | 7,000 | 2,000 | 12,500 | 48,750 | 11 |
|  |  |  |  | 71600 | Travel | 0 | 0 | 1,000 | 1,000 | 0 | 2,000 | 12 |
|  |  |  |  | 72100 | Contractual Services-Companies | 24,750 | 31,600 | 16,200 | 9,200 | 17,500 | 99,250 | 13 |
|  |  |  |  | 74500 | Miscellaneous | 1,000 | 0 | 0 | 0 | 0 | 1,000 | 14 |
|  |  |  |  | 75700 | Training, Workshops and Confer | 0 | 3,000 | 3,000 | 2,000 | 0 | 8,000 | 15 |
|  |  |  |  | Sub-total Component 1 (GACC) |  | 39,000 | 48,600 | 27,200 | 14,200 | 30,000 | 159,000 |  |
|  | TOTAL Component 1 (MARA+MEE+GACC) |  |  |  |  | 180,730 | 268,520 | 108,200 | 63,200 | 43,600 | 664,250 |  |
| COMPONENT 2: Strengthened IAS management frameworks and institutional capacity. | MARA (Output 2.1 & 2.3) | 62000 | GEF | 71300 | Local Consultants | 35,100 | 31,350 | 13,100 | 11,600 | 11,600 | 102,750 | 16 |
|  |  |  |  | 71600 | Travel | 6,500 | 1,250 | 2,000 | 3,000 | 2,000 | 14,750 | 17 |
|  |  |  |  | 72100 | Contractual Services-Companies | 45,000 | 27,500 | 0 | 0 | 0 | 72,500 | 18 |
|  |  |  |  | 72800 | Information Technology Equipment | 3,750 | 1,250 | 0 | 0 | 0 | 5,000 | 19 |
|  |  |  |  | 74500 | Miscellaneous | 0 | 5,200 | 0 | 0 | 0 | 5,200 | 20 |
|  |  |  |  | Sub-total Component 2 (MARA) |  | 90,350 | 66,550 | 15,100 | 14,600 | 13,600 | 200,200 |  |
|  | MEE (Output 2.1 & 2.3) | 62000 | GEF | 71300 | Local Consultants | 18,690 | 19,935 | 7,750 | 4,875 | 6,250 | 57,500 | 21 |
|  |  |  |  | 71600 | Travel | 1,000 | 2,000 | 2,000 | 3,000 | 1,000 | 9,000 | 22 |
|  |  |  |  | 72100 | Contractual Services-Companies | 25,940 | 19,060 | 3,750 | 2,500 | 5,000 | 56,250 | 23 |
|  |  |  |  | 72800 | Information Technology Equipment | 3,750 | 1,250 | 0 | 0 | 0 | 5,000 | 24 |
|  |  |  |  | 74500 | Miscellaneous | 0 | 1,000 | 0 | 0 | 0 | 1,000 | 25 |
|  |  |  |  | 75700 | Training, Workshops and Confer | 0 | 0 | 5,000 | 5,000 | 0 | 10,000 | 26 |
|  |  |  |  | Sub-total Component 2 (MEE) |  | 49,380 | 43,245 | 18,500 | 15,375 | 12,250 | 138,750 |  |
|  | GACC (Output 2.1, 2.2, & 2.3) | 62000 | GEF | 71300 | Local Consultants | 33,750 | 33,750 | 5,000 | 5,000 | 0 | 77,500 | 27 |
|  |  |  |  | 71600 | Travel | 0 | 8,000 | 4,000 | 4,000 | 4,000 | 20,000 | 28 |
|  |  |  |  | 72100 | Contractual Services-Companies | 56,250 | 54,250 | 11,500 | 0 | 11,845 | 133,845 | 29 |
|  |  |  |  | 72800 | Information Technology Equipment | 3,750 | 1,250 | 0 | 0 | 0 | 5,000 | 30 |
|  |  |  |  | 74500 | Miscellaneous | 0 | 1,000 | 0 | 0 | 0 | 1,000 | 31 |
|  |  |  |  | Sub-total Component 2 (GACC) |  | 93,750 | 98,250 | 20,500 | 9,000 | 15,845 | 237,345 |  |
|  | TOTAL Component 2 (MARA+MEE+GACC) |  |  |  |  | 233,480 | 208,045 | 54,100 | 38,975 | 41,695 | 576,295 |  |
| COMPONENT 3: Demonstration of IAS threat reduction in agroecosystems | MARA (Output 3.1, 3.2, 3.3 & 3.4) | 62000 | GEF | 71300 | Local Consultants | 20,350 | 63,475 | 33,225 | 33,225 | 33,225 | 183,500 | 32 |
|  |  |  |  | 71600 | Travel | 1,000 | 10,000 | 10,000 | 10,000 | 11,000 | 42,000 | 33 |
|  |  |  |  | 72100 | Contractual Services-Companies | 13,250 | 96,125 | 28,875 | 28,875 | 28,875 | 196,000 | 34 |
|  |  |  |  | 72800 | Information Technology Equipment | 0 | 30,000 | 0 | 0 | 0 | 30,000 | 35 |
|  |  |  |  | 74500 | Miscellaneous | 0 | 0 | 5,200 | 0 | 0 | 5,200 | 36 |
|  |  |  |  | 75700 | Training, Workshops and Confer | 0 | 14,500 | 0 | 0 | 0 | 14,500 | 37 |
|  |  |  |  | Sub-total Component 3 (MARA) |  | 34,600 | 214,100 | 77,300 | 72,100 | 73,100 | 471,200 |  |
|  | MEE (Output 3.3) | 62000 | GEF | 71300 | Local Consultants | 8,750 | 15,000 | 0 | 0 | 0 | 23,750 | 38 |
|  |  |  |  | 71600 | Travel | 1,000 | 3,000 | 0 | 0 | 0 | 4,000 | 39 |
|  |  |  |  | 72100 | Contractual Services-Companies | 19,000 | 39,000 | 0 | 0 | 0 | 58,000 | 40 |
|  |  |  |  | 74500 | Miscellaneous | 0 | 0 | 1,000 | 0 | 0 | 1,000 | 41 |
|  |  |  |  | 75700 | Training, Workshops and Confer | 0 | 2,500 | 0 | 0 | 0 | 2,500 | 42 |
|  |  |  |  | Sub-total Component 3 (MEE) |  | 28,750 | 59,500 | 1,000 | 0 | 0 | 89,250 |  |
|  | TOTAL Component 3 (MARA+MEE) |  |  |  |  | 63,350 | 273,600 | 78,300 | 72,100 | 73,100 | 560,450 |  |
| COMPONENT 4: Awareness raising, knowledge management and coordination | MARA (Output 4.1, 4.2, 4.3 & 4.4) | 62000 | GEF | 71200 | International Consultants | 0 | 0 | 22,750 | 0 | 26,000 | 48,750 | 43 |
|  |  |  |  | 71300 | Local Consultants | 37,900 | 45,400 | 55,400 | 45,400 | 50,650 | 234,750 | 44 |
|  |  |  |  | 71600 | Travel | 2,000 | 2,000 | 69,250 | 2,000 | 17,500 | 92,750 | 45 |
|  |  |  |  | 72100 | Contractual Services-Companies | 50,000 | 17,500 | 22,500 | 22,500 | 36,250 | 148,750 | 46 |
|  |  |  |  | 74500 | Miscellaneous | 0 | 0 | 0 | 3,568 | 0 | 3,568 | 47 |
|  |  |  |  | 75700 | Training, Workshops and Confer | 20,000 | 0 | 38,000 | 12,000 | 15,000 | 85,000 | 48 |
|  |  |  |  | Sub-total Component 4 (MARA) |  | 109,900 | 64,900 | 207,900 | 85,468 | 145,400 | 613,568 |  |
|  | MEE (Output 4.1, & 4.4) | 62000 | GEF | 71300 | Local Consultants | 0 | 7,500 | 7,500 | 7,500 | 0 | 22,500 | 49 |
|  |  |  |  | 71600 | Travel | 0 | 0 | 10,000 | 0 | 0 | 10,000 | 50 |
|  |  |  |  | 72100 | Contractual Services-Companies | 0 | 9,375 | 10,000 | 14,375 | 5,000 | 38,750 | 51 |
|  |  |  |  | 74500 | Miscellaneous | 0 | 0 | 0 | 1,095 | 0 | 1,095 | 52 |
|  |  |  |  | 75700 | Training, Workshops and Confer | 5,000 | 0 | 10,000 | 5,000 | 0 | 20,000 | 53 |
|  |  |  |  | Sub-total Component 4 (MEE) |  | 5,000 | 16,875 | 37,500 | 27,970 | 5,000 | 92,345 |  |
|  | GACC (Output 4.1, & 4.4) | 62000 | GEF | 71300 | Local Consultants | 0 | 3,750 | 3,750 | 3,750 | 0 | 11,250 | 54 |
|  |  |  |  | 71600 | Travel | 0 | 0 | 50,000 | 0 | 0 | 50,000 | 55 |
|  |  |  |  | 72100 | Contractual Services-Companies | 0 | 15,000 | 20,000 | 20,000 | 8,750 | 63,750 | 56 |
|  |  |  |  | 74500 | Miscellaneous | 0 | 0 | 0 | 0 | 1,000 | 1,000 | 57 |
|  |  |  |  | 75700 | Training, Workshops and Confer | 0 | 8,750 | 3,750 | 8,750 | 3,750 | 25,000 | 58 |
|  |  |  |  | Sub-total Component 4 (GACC) |  | 0 | 27,500 | 77,500 | 32,500 | 13,500 | 151,000 |  |
|  | TOTAL Component 4 (MARA+MEE+GACC) |  |  |  |  | 114,900 | 109,275 | 322,900 | 145,938 | 163,900 | 856,913 |  |
|  |  |  |  | 71600 | Travel | 3,000 | 2,000 | 2,000 | 2,000 | 3,000 | 12,000 | 59 |
|  |  |  |  | 71800 | Contractual services – Implementing Partner | 24,200 | 24,200 | 24,200 | 24,200 | 22,000 | 118,800 | 60 |
|  |  |  |  | 74500 | Miscellaneous | 240 | 240 | 240 | 240 | 240 | 1,200 | 61 |
|  |  |  |  | Total Project Management |  | 26,840 | 26,840 | 26,840 | 26,840 | 24,640 | 132,000 |  |
|  |  |  |  | Project Total |  | 619,300 | 886,280 | 590,340 | 347,053 | 346,935 | 2,789,908 |  |

Summary of Funds:

|  | Amount Year 1 | Amount Year 2 | Amount Year 3 | Amount Year 4 | Amount Year 5 | Total |
| --- | --- | --- | --- | --- | --- | --- |
| GEF | $619,300 | $886,280 | $590,340 | $347,053 | $346,935 | $2,789,908 |
| Donor 2 (e.g. UNDP) | $0 | $0 | $0 | $0 | $0 | $0 |
| Ministry of Agriculture and Rural Affairs (MARA) | $460,252 | $541,660 | $487,600 | $299,556 | $330,932 | $2,120,000 |
| Ministry of Ecology and Environment (MEE) | $998,660 | $1,175,300 | $1,058,000 | $649,980 | $718,060 | $4,600,000 |
| General Administration of Customs (GACC) | $872,742 | $1,027,110 | $924,600 | $568,026 | $627,522 | $4,020,000 |
| Department of Agricultural and Rural Affairs, Hainan Province (DARA/HP) | $673,065 | $784,200 | $735,125 | $455,500 | $502,110 | $3,150,000 |
| Department of Agricultural and Rural Affairs Bishan District (DARA/BD), | $683,865 | $804,825 | $724,500 | $445,095 | $491,715 | $3,150,000 |
| Beijing Huaheng Rongtong Technology Co. Ltd (BHRTcl) | $130,260 | $153,300 | $138,000 | $84,780 | $93,660 | $600,000 |
| Wenchang Wenting Agritourism and Ecological Agriculture Co. Ltd (WWAEAcl) | $136,773 | $160,965 | $144,900 | $89,019 | $98,343 | $630,000 |
| Chongqing Late Orange Planting Farmers’ Cooperative (CLOPFC) | $125,973 | $140,340 | $155,525 | $99,424 | $108,738 | $630,000 |
| Donor 3 (grant) from Government and private sector (TOTAL) | $4,081,590 | $4,787,700 | $4,368,250 | $2,691,380 | $2,971,080 | $18,900,000 |
| TOTAL | $4,700,890 | $5,673,980 | $4,958,590 | $3,038,433 | $3,318,015 | $21,689,908 |

| BUDGET NOTES |  |
| --- | --- |
| Component 1 |  |
| 1 | Local consultants: National Technical Advisor for engaging support of high-level stakeholders, coordinating all consultancy and service contract inputs and overall implementation of Outputs under Component 1, but with a specific focus on output 1.2 and 1.3 ($2,900 pm x 20 months = $58,000) (= 33.3% of the contract – see also budget notes 17, and 34); C-SAP Chief Technical Advisor support primarily for output 1.2 and 1.3 (20pw x $1,500 = $30,000 (= 40% of the contract – see also budget notes 17, 34 and 47); Agricultural sector IAS policy specialist support for output 1.2 (35 pw x $1,250 = $43,750 (= 85% of the contract – see also budget note 17)); Agricultural sector IAS planning specialist support for output 1.3 and 1.4 (14 pw x $1,250 = $17,500 (= 33% of the contract – see also budget note 34)). Total = $149,250 |
| 2 | Travel and DSA for Agricultural sector IAS policy specialist & Agricultural IAS planning specialist (4 x $1,000 = $4,000); Travel and DSA for PMO to coordinate implementation of Component 1 ($12,000); Total = $16,000 |
| 3A | Contractual Services – Companies: Sub-contract – Strengthen the regulatory framework and develop integrated IAS guidelines and methodologies (Agriculture). Revise and adopt the regulation framework within MARA to optimize cross-sectoral IAS Management ($10,000); Develop provincial regulations for IAS prevention, control and management within MARA in Hainan and Chongqing ($6,250); Revise IAS Early Warning guidelines ($6,250); and Revise IAS rapid response guidelines ($6,250); Support the MEE led development of an IAS Biodiversity Risk Assessment Guideline ($6,250), all under output 1.2. Total = $35,000 (=74% of the total contract – see also budget note 20A). The subcontract will run simultaneously with similar sub-contracts managed by MEE and GACC focusing on their respective sectors (see budget note (9A and 25A MEE) and (14A and 31A GACC)) and the subcontractors will coordinate and cooperate with one another. MARA coordinates the process for the development of the IAS Early Warning guidelines and the IAS rapid response guidelines, whereas MEE leads the development of the IAS Biodiversity Risk Assessment Guideline. |
| 3B | Contractual Services – Companies: Sub-contract – Develop National and Provincial IAS planning including Strategic Action Plans (Agriculture). Prepare the National IAS Management strategy and action plan (IAS NSAP 2021-2030) ($6,250); Prepare Provincial IAS Management Strategy and Action Plan (IAS PSAP 2022-2030) for Hainan and Chongqing ($13,000) both under output 1.3; Develop MARA sectoral/ministerial Implementation Plans for the IAS NSAP 2021-2030 ($6,250); Develop MARA sectoral/department Implementation Plans for the IAS PSAP 2022-2030 in Hainan and Chongqing ($13,000) both under output 1.4. Total = $38,500 (=21% of the total contract – see also budget note 37A). The subcontract will run simultaneously with similar sub-contracts managed by MEE and GACC focusing on their respective sectors (see budget note (9B, MEE) and (14B GACC)) and the subcontractors will coordinate and cooperate with one another. MARA coordinates the process for the development of the National and Provincial Strategic Action plans. |
| 4 | Miscellaneous: Contingency to cover exchange rate fluctuations and miscellaneous costs associated with organizing specialized meetings i.e. M&E monitoring of indicators in Results Framework. Total = $4,500 |
| 5 | Trainings, workshops & conferences: Project co-financing will be used for most of the meetings related to the project’s consultation process under Component 1. The GEF financing will be used to hold annual MARA led multi-sector coordination workshops (2 x $2,000 = $4,000) under output 1.1; MARA led stakeholder workshop for the formulation of the National IAS Management strategy and action plan (IAS NSAP 2021-2030) (8 x $1,500 = $12,000); Verification workshop for the formulation of the IAS NSAP (2 x $2,500 = $5,000); MARA led stakeholder workshop for the formulation of the Hainan and Chongqing IAS PSAPs (6 x $1,500 = $9,000); Verification workshop for the formulation of the Hainan and Chongqing IAS PSAPs $(2 x $2,500) all under output 1.3. Total = $35,000. Additional workshops will be led by MEE and GACC (see budget note 11 and 16). |
| 6 | Local consultants: Environmental sector IAS policy specialist support for output 1.2 (46 pw x $1,250 = $57,500 (= 71% of the contract – see also budget note 23)); Environmental sector IAS planning specialist support for output 1.3 and 1.4 (15 pw x $1,250 = $18,750 (= 44% of the contract – see also budget note 41)). Total = $76,250 |
| 7 | Travel and DSA for Environmental sector IAS policy specialist & Environmental IAS planning specialist (4 x $1,000 = $4,000); Total = $4,000 |
| 8A | Contractual Services – Companies: Sub-contract – Strengthen the regulatory framework and develop integrated IAS guidelines and methodologies (Environment). Revise and adopt the regulation framework within MEE to optimize cross-sectoral IAS Management ($5,000); Develop provincial regulation for IAS prevention, control and management within MEE in Hainan and Chongqing ($5,000); Support the Mara led revision of IAS Early Warning guidelines ($5,000); and Support the Mara led revision of IAS rapid response guidelines ($5,000); Develop an IAS Biodiversity Risk Assessment Guideline ($17,500); Develop IAS buffer zone guideline for areas surrounding ecological functioning zones and protected areas ($30,000); Develop IAS Biodiversity Risk Assessment, Early Warning and Rapid Response guidelines for protected areas ($48,750), all under output 1.2. Total = $116,250 (=89% of the total contract – see also budget note 25A). The subcontract will run simultaneously with similar sub-contracts managed by MARA and GACC focusing on their respective sectors (see budget note (4A and 20A MEE) and (14A and 31A GACC)) and the subcontractors will coordinate and cooperate with one another. MARA coordinates the process for the development of the IAS Early Warning guidelines and the IAS rapid response guidelines, whereas MEE leads the development of the IAS Biodiversity Risk Assessment Guideline. |
| 8B | Contractual Services – Companies: Sub-contract – Develop National and Provincial IAS planning including Strategic Action Plans (Environment). Support the MARA led preparation of the National IAS Management strategy and action plan (IAS NSAP 2021-2030) ($5,000); Support the MARA preparation of Provincial IAS Management Strategy and Action Plan (IAS PSAP 2022-2030) for Hainan and Chongqing ($5,000) both under output 1.3; Develop MEE sectoral/ministerial Implementation Plans for the IAS NSAP 2021-2030 ($5,000); Develop MEE sectoral/department Implementation Plans for the IAS PSAP 2022-2030 in Hainan and Chongqing ($5,000) both under output 1.4. Total = $20,000 (=26% of the total contract – see also budget note 43). The subcontract will run simultaneously with similar sub-contracts managed by MEE and GACC focusing on their respective sectors (see budget note (4B and 37A MARA) and (14B GACC)) and the subcontractors will coordinate and cooperate with one another. MARA coordinates the process for the development of the National and Provincial Strategic Action plans. |
| 9 | Miscellaneous: Contingency to cover exchange rate fluctuations and miscellaneous costs associated with organizing specialized meetings i.e. M&E monitoring of indicators in Results Framework. Total = $1,000 |
| 10 | Trainings, workshops & conferences: Project co-financing will be used for most of the meetings related to the project’s consultation process under Component 1. The GEF financing will be used to hold annual multi-sector coordination workshops (1 x $2,000 = $2,000) under output 1.1; Stakeholder workshop for the formulation of the National IAS Management strategy and action plan (IAS NSAP 2021-2030) (2 x $1.500 = $3,000); Stakeholder workshop for the formulation of the Hainan and Chongqing IAS PSAPs (3 x $1,500 = 4,500) both under output 1.3. Total = $9,500. Additional workshops will be led by MARA and GACC (see budget note 6 and 16). |
| 11 | Local consultants: Customs sector IAS policy specialist support for output 1.2 (26 pw x $1,250 = $32,500 (= 38% of the contract – see also budget note 29)); Customs sector IAS planning specialist support for output 1.3 and 1.4 (13 pw x $1,250 = $16,250 (= 40 % of the contract – see also budget note 29)). Total = $48,750 |
| 12 | Travel and DSA for Customs sector IAS policy specialist & Customs IAS planning specialist (2 x $1,000 = $2,000). Total = $2,000 |
| 13A | Contractual Services – Companies: Sub-contract – Strengthen the regulatory framework and develop integrated IAS guidelines and methodologies (Customs). Revise and adopt the regulation framework within GACC to optimize cross-sectoral IAS Management ($12,500); Develop provincial regulation for IAS prevention, control and management within GACC in Hainan and Chongqing ($10,000); Support the MARA led revision of IAS Early Warning guideline ($12,500); Include biodiversity into the updates of the 2007 National Quarantine Pest list ($17,500), all under output 1.2. Total = $52,500 (=38% of the total contract – see also budget note 31A). The subcontract will run simultaneously with similar sub-contracts managed by MARA and MEE focusing on their respective sectors (see budget note (4A and 20A MARA) and (9A and 25A MEE)) and the subcontractors will coordinate and cooperate with one another. MARA coordinates the process for the development of the IAS Early Warning guidelines. |
| 13B | Contractual Services – Companies: Sub-contract – Develop National and Provincial IAS planning including Strategic Action Plans (Customs). Support the MARA led preparation of the National IAS Management strategy and action plan (IAS NSAP 2021-2030) ($15,000); Support the MARA preparation of Provincial IAS Management Strategy and Action Plan (IAS PSAP 2022-2030) for Hainan and Chongqing ($11,500) both under output 1.3; Develop GACC sectoral/ministerial Implementation Plans for the IAS NSAP 2021-2030 ($8,750); Develop GACC sectoral/department Implementation Plans for the IAS PSAP 2022-2030 in Hainan and Chongqing ($11,500) both under output 1.4. Total = $46,750 (=100% of the total contract). The subcontract will run simultaneously with similar sub-contracts managed by MEE and GACC focusing on their respective sectors (see budget note (4B and 37A MARA) and (9B and 43 MEE)) and the subcontractors will coordinate and cooperate with one another. MARA coordinates the process for the development of the National and Provincial Strategic Action plans. |
| 14 | Miscellaneous: Contingency to cover exchange rate fluctuations and miscellaneous costs associated with organizing specialized meetings i.e. M&E monitoring of indicators in Results Framework. Total = $1,000 |
| 15 | Trainings, workshops & conferences: Project co-financing will be used for most of the meetings related to the project’s consultation process under Component 1. The GEF financing will be used to hold annual multi-sector coordination workshops ($2,000) under output 1.1; Stakeholder workshop for the formulation of the National IAS Management strategy and action plan (IAS NSAP 2021-2030) ($1,500); Stakeholder workshop for the formulation of the Hainan and Chongqing IAS PSAPs (3 x $1,500 = 4,500) both under output 1.3. Total = $8,000. Additional workshops will be led by MARA and MEE (see budget note 6 and 11). |
| Component 2 |  |
| 16 | Local consultants: National Technical Advisor for engaging support of high level stakeholders, coordinating all consultancy and service contract inputs, and overall implementation of Outputs 2.1, 2.2 and 2.3 with most focus on output 2.1 (20 pm x $2,900 = $58,000 (= 33.3% of the contract – see also budget notes 1, and 34); C-SAP Chief Technical Advisor support primarily for output 2.1 (8 pw x $1,500 = $12,000) (= 16% of the contract – see also budget note 1, 34 and 47); Agricultural sector IAS policy specialist support for output 2.1 (6 pw x $1,250 = $7,500 (= 15% of the contract – see also budget note 1)); Agricultural sector training specialist support for output 2.3 (20 pw x $1,250 = $25,000 (= 27% of the contract – see also budget note 34)). Total = $102,750 |
| 17 | Travel and DSAs for Agricultural sector training specialist ($4,750); Travel and DSA for PMO to coordinate implementation of Component 2 ($10,000); Total = $14,750 |
| 18A | Contractual Services – Companies: Sub-contract – Strengthen the regulatory framework and develop integrated IAS guidelines and methodologies (Agriculture). Provide support to the MEE led development of provincial IAS Biodiversity Risk Assessment Methodologies in Hainan ($6,250); Develop provincial IAS Early Warning Methodologies in Hainan ($6,250) both under output 2.1. Total $12,500. (=26% of the total contract – see also budget note 4A). The subcontract will run simultaneously with similar sub-contracts managed by MEE and GACC focusing on their respective sectors (see budget note (9A and 25A MEE) and (14A and 31A GACC)) and the subcontractors will coordinate and cooperate with one another. MARA coordinates the process for the development of the IAS Early Warning Methodologies, whereas MEE leads the development of the IAS Biodiversity Risk Assessment Methodologies. |
| 18B | Contractual Services – Companies: Sub-contract – Develop project training and build stakeholder capacity (Agriculture). Develop and organize R&D supported technical training courses ($25,000) under output 2.3 Total = $25,000 (=28% of the total contract – see also budget note 37B and 50C). The subcontract will run simultaneously with a similar sub-contract managed by MEE which will bring in the aspect of biodiversity and biodiversity concerns into the trainings (see budget note (25B MEE)) and linked to the GACC training subcontract (budget note 31B) and the subcontractors will coordinate and cooperate with one another. MARA coordinates the process for the development of the training courses, and MARA will implement local trainings within the agricultural landscape. |
| 18C | Contractual Services – Companies: Sub-contract – Develop mobile based application for IAS Management. Develop an easy to use and publicly-accessible IAS application (APP) for IAS identification, IAS GIS location mapping and general IAS Management related information ($35,000) under output 2.3. Total = $35,000 |
| 19 | Information Technology Equipment: Equipment related to monitoring or identification of IAS including small drones (with cameras), low cost mobile phones to be used for demonstration of the IAS app or other small-scale technical equipment ($5,000). |
| 20 | Miscellaneous: Contingency to cover exchange rate fluctuations and miscellaneous costs associated with organizing specialized meetings i.e. M&E monitoring of indicators in Results Framework. Total = $5,200 |
| 21 | Local consultants: Environmental sector IAS policy specialist support for output 2.1 (16 pw x $1,250 = $20,000 (= 29% of the contract – see also budget note 1)); Environmental sector training specialist support for output 2.3 (30 pw x $1,250 = $37,500 (= % of the contract – see all bn)). Total = $57,500 |
| 22 | Travel and DSAs for Environmental sector training specialist ($9,000); Total = $9,000 |
| 23A | Contractual Services – Companies: Sub-contract – Strengthen the regulatory framework and develop integrated IAS guidelines and methodologies (Environment). Develop provincial IAS Biodiversity Risk Assessment Methodologies in Hainan ($5,000); Support the MARA led development of provincial IAS Early Warning Methodologies in Hainan ($5,000); Undertake an IAS Biodiversity Risk Assessment for Hainan ($5,000); all under output 2.1. Total $15,000. (= 11% of the total contract – see also budget note 9A). The subcontract will run simultaneously with similar sub-contracts managed by MARA and GACC focusing on their respective sectors (see budget note (4A and 20A MEE) and (14A and 31A GACC)) and the subcontractors will coordinate and cooperate with one another. MARA coordinates the process for the development of the IAS Early Warning Methodologies, whereas MEE leads the development of the IAS Biodiversity Risk Assessment Methodologies. |
| 23B | Contractual Services – Companies: Sub-contract – Develop project training and build stakeholder capacity (Environment). Support the development of R&D supported technical training courses ($31,250); Organize selected trainings for managers and staff working at protected areas, reserves or other ecological sensitive areas ($10,000) both under output 2.3 Total = $41,250. (=80% of the total contract – see also budget note 55A). The subcontract will run simultaneously with a similar sub-contract managed by MEE which will bring in the aspect of biodiversity and biodiversity concerns into the trainings (see budget note (20B MARA)) and linked to the GACC training subcontract (budget note 31B) and the subcontractors will coordinate and cooperate with one another. MEE will adapt and provide the training for protected areas staff and other stakeholders. |
| 24 | Information Technology Equipment: Equipment related to monitoring or identification of IAS including small drones (with cameras), low cost mobile phones to be used for demonstration of the IAS app or other small-scale technical equipment ($5,000). Total = $5,000 |
| 25 | Miscellaneous: Contingency to cover exchange rate fluctuations and miscellaneous costs associated with organizing specialized meetings i.e. M&E monitoring of indicators in Results Framework. Total = $1,000 |
| 226 | Trainings, workshops & conferences: Organize selected trainings for managers and staff working in protected areas, reserves or other ecological sensitive areas (2 x $5,000 = $10,000). Total = 10,000 |
| 27 | Local consultants: Customs sector IAS policy specialist support for output 2.1 (42 pw x $1,250 = $52,500 (= 62% of the contract – see also budget note 1)); Customs sector IAS planning specialist support for output 2.3 (20 pw x $1,250 = $25,000 (=60 % of the contract – see also budget note 12)). Total = $77,500 |
| 28 | Travel and DSAs for Customs sector training specialist (20 x $1,000 = $20,000). Total = $20,000 |
| 29A | Contractual Services – Companies: Sub-contract – Strengthen the regulatory framework and develop integrated IAS guidelines and methodologies (Customs). Support the MARA led development of provincial IAS Early Warning Methodologies in Hainan ($12,500); under output 2.1. Update the national technical specification for IAS inspection, quarantine and disposal used at Yangpu port ($25,000); Review and update quarantine standards ($25,000); Formulate/revise quarantine management methodologies ($25,000) all under output 2.2. Total $87,500. (=62% of the total contract – see also budget note 14A). The subcontract will run simultaneously with similar sub-contracts managed by MARA and MEE focusing on their respective sectors (see budget note (4A and 20A MARA) and (9A and 25A MEE)) and the subcontractors will coordinate and cooperate with one another. MARA coordinates the process for the development of the IAS Early Warning Methodologies. |
| 29B | Contractual Services – Companies: Sub-contract – Develop project training and build stakeholder capacity (Customs). Develop and organize trainings on the implementation of the national technical specification for IAS inspection, quarantine and disposal, the updated quarantine standards and methodologies ($46,345) under output 2.2. Total = $46,345. (=82% of the total contract – see also budget note 61A) GACC will provide the training to the customs staff and other relevant stakeholders. |
| 30 | Information Technology Equipment: Equipment related to monitoring or identification of IAS including small drones (with cameras), low cost mobile phones to be used for demonstration of the IAS app or other small-scale technical equipment ($5,000). Total = $5,000 |
| 31 | Miscellaneous: Contingency to cover exchange rate fluctuations and miscellaneous costs associated with organizing specialized meetings i.e. M&E monitoring of indicators in Results Framework. Total = $1,000 |
| Component 3 |  |
| 32 | Local consultants: National Technical Advisor for engaging support of high level stakeholders, coordinating all consultancy and service contract inputs, and overall implementation of Component 3 but primarily focusing on output 3.1 (20 pm x $2,900 = $58,000 (= 33.3% of the contract – see also budget notes 1, and 17); C-SAP Chief Technical Advisor support primarily for output 3.3 and 3.4 (12 pw x $1,500 = $18,000) (= 24% of the contract – see also budget note 1, 17 and 47); Agricultural sector IAS planning specialist support for output 3.2 (29 pw x $1,250 = $36,250 (= 67% of the contract – see also budget note 1)); Agricultural sector training specialist support for output 3.1 (55 pw x $1,250 = $68,750 (= 73% of the contract – see also budget note 17)). Gender specialist (2 pw x 1,250=2,500) (= 20% of the contract – see also budget note 47). Total = $183,500 |
| 33 | Travel and DSAs for Agricultural sector training specialist (10 x $1,000 = $10,000) and the Agricultural sector IAS planning specialist (16 x $1000 = 16,000); Travel and DSA for PMO to coordinate implementation of Component 3 ($16,000). Total = $42,000 |
| 34A | Contractual Services – Companies: Sub-contract – Develop National and Provincial IAS planning including Strategic Action Plans (Agriculture). Design the IAS distribution survey and IAS impact assessment of selected IAS in Wenchang and Bishan ($6.250); Undertake the IAS distribution survey and IAS impact assessment in Wenchang, Bishan and the representative protected area ($21,000); Formulate the IAS distribution survey and IAS impact assessment reports for Wenchang, Bishan and the representative protected area ($15,000); Formulate IAS Management plans for Wenchang city and Bishan district ($20,000) all under output 3.3; Implement the IAS Management plans for the two project targeted agricultural landscapes in Wenchang city and Bishan district ($73,000) both under output 3.4. Total = $135,250 (=79% of the total contract – see also budget note 4B). The subcontract will run simultaneously with similar sub-contracts managed by MEE and GACC focusing on their respective sectors (see budget note (9B MEE) and (14B GACC)) and the subcontractors will coordinate and cooperate with one another. |
| 34B | Contractual Services – Companies: Sub-contract – Develop project training and build stakeholder capacity (Agriculture). Adapt trainings on key subjects, based on the developed training courses (output 2.3) to address farmers and other stakeholders training needs ($8,750); Organize adapted trainings for different stakeholder groups including farmers, cooperatives, enterprises and other stakeholder ($42,500) both under output 3.1; Demonstrate verified and applicable participatory IAS Management approaches in Wenchang and Bishan ($9,500) under output 3.2. Total = $60,750 (=67% of the total contract – see also budget note 20B and 50C). |
| 35 | Information Technology Equipment: Computers, printers and other IT related equipment in support to the IAS Management Science Base/Public Science Popularization Base in Wenchang and Bishan (2 x $15,000 = $30,000) under output 3.2. Total = 30,000 |
| 36 | Miscellaneous: Contingency to cover exchange rate fluctuations and miscellaneous costs associated with organizing specialized meetings i.e. M&E monitoring of indicators in Results Framework. Total = $5,200 |
| 37 | Trainings, workshops & conferences: Stakeholder workshop for the formulation of the IAS distribution survey and IAS impact assessment reports for Wenchang, Bishan ($2,500) under output 3.3; Stakeholder workshop for the formulation of the IAS Management plans for Wenchang city and Bishan district (8 x $1,500 = $12,000)) under output 3.4. Total =$14,500 |
| 38 | Local consultants: Environment sector IAS planning specialist support for output 3.3 (19 pw x $1,250 = $23,750 (= 66% of the contract – see also budget note 7)); Total = $23,750 |
| 39 | Travel and DSAs the Environment sector IAS planning specialist ($4000). Total = $4,000 |
| 40 | Contractual Services – Companies: Sub-contract – Develop National and Provincial IAS planning including Strategic Action Plans (Environment). Design the IAS distribution survey and IAS impact assessment of selected IAS in a representative protected area ($5,000); Undertake the IAS distribution survey and IAS impact assessment in a representative protected area ($43,000); Formulate the IAS distribution survey and IAS impact assessment reports for the representative protected area ($10,000) all under output 3.3. Total = $58,000 (=74% of the total contract – see also budget note 9B). The subcontract will run simultaneously with similar sub-contracts managed by MEE and GACC focusing on their respective sectors (see budget note (4B and 37A MARA) and (14B GACC)) and the subcontractors will coordinate and cooperate with one another. |
| 41 | Miscellaneous: Contingency to cover exchange rate fluctuations and miscellaneous costs associated with organizing specialized meetings i.e. M&E monitoring of indicators in Results Framework. Total = $1,000 |
| 42 | Trainings, workshops & conferences: Stakeholder workshop for the formulation of the IAS distribution survey and IAS impact assessment reports for a representative protected area ($2,500) under output 3.3. Total =$2,500 |
| Component 4 |  |
| 43 | International consultants for: Mid-term Review ($650 x 35 days = $22,750) in Year 3; Terminal Evaluation ($650 x 40 days = $26,000 ) in Year 5. TOTAL = $48,750 |
| 44 | Local consultants: for: Technical C-SAP Program Advisor to support program technical alignment and coordinate the C-SAP 2 (IAS) project’s knowledge management work with the C-SAP 1 and 5 projects. The Technical Program Advisor will also develop government memos and briefs etc. related to the program, as well as visualize the programm’s successes on various media. The Technical Program Advisor will also work with the projects M&E Specialist in the program’s monitoring and evaluation work. (60 pm x $2,200 = $132,000); Mid-term Review ($250 x 40 days = $10,000) in Year 3; Terminal Evaluation ($250 x 46 days = $11,500) in Year 5; C-SAP Chief Technical Advisor support primarily for output 4.3 and 4.4 (10 pw x $1,500 = $15,000) (= 20% of the contract – see also budget note 1, 17 and 34); Awareness raising consultant (Agriculture) (21 pw x $1,250 = $26,250) under output 4.1; Gender specialist (8 pw x 1,250=10,000) (= 80% of the contract – see also budget note 34); Short term consultant for Monitoring of environmental and social risks, distillation of knowledge products, and lessons learned identification (24 pw x $1,250 = $30,000) both under output 4.4. Total $234,750 |
| 45 | Travel and DSA: Mid-term Review in year 3- International travel ($1,500); and domestic travel (5 x $1000 = $5,000); DSA (IC) (9 x $250 = $2,250); DSA (NCs) (14 x $250 = $3,500); Terminal Evaluation in year 5 - International travel ($1,500); and domestic travel (9 x $1000 = $9,000); DSA (IC) (12 x $250 = $3,000); DSA (NCs) (16 x $250 = $4,000); Travel and DSA for Best practice learning and knowledge sharing exchange missions (9 persons x $5,000 = $55,000); Travel and DSA for PMO to coordinate implementation of Component 4 ($8,000). TOTAL = $92,750 |
| 46A | Contractual Services – Companies: Sub-contract - Knowledge, attitude and practices (KAP survey) First survey initiated with 3 months of project start and second survey initiated at a minimum six months before project end (2 x $20,000 = 40,000) under output 4.1. Total $40,000 |
| 46B | Contractual Services – Companies: Sub-contract - NIM Audit (5 x $5,000 = $25,000). Total $25,000 |
| 46C | Contractual Services – Companies: Sub-contract – Develop project training and build stakeholder capacity (Agriculture). Develop and publicize Agriculture relevant Massive Open Online Courses based on the project developed trainings ($ 10,000) under output 4.1. Total = $ 10,000 (=11% of the total contract – see also budget note 20B and 37B) |
| 46D | Contractual Services – Companies: Sub-contract – Develop awareness raising materials relevant for the public and main agricultural sector stakeholders. Prepare IAS awareness-raising materials for public events and general distribution ($18,750); Organize publicity and awareness events at national, provincial and local levels ($25,000) both under output 4.1. Total = $43,750 |
| 46E | Contractual Services – Companies: Sub-contract – Develop IAS Knowledge Management platform. Design the IAS Knowledge Management platform including integration of needed software, making it ready for stakeholder use and handover ($30,000) under output 4.2. Total = $30,000 |
| 47 | Miscellaneous: Contingency to cover exchange rate fluctuations and miscellaneous costs associated with organizing specialized meetings i.e. M&E monitoring of indicators in Results Framework. Total = $3,568 |
| 48 | Training & workshops: Side event at COP ($30,000) under output 4.1; Publicity and awareness raising events at national, provincial and local levels (5 x $4,000 = $20,000); C-SAP 2 IAS project inception workshop ($10,000); C-SAP Program inception workshop ($10,000); annual C-SAP 2 IAS project steering committee meetings ($5,000) held on a rotational basis; one annual C-SAP Program steering committee meeting ($10,000) all under output 4.4. TOTAL = $ 85,000 |
| 49 | Local consultants: Awareness raising consultant (Environment) (18 pw x $1,250 = $22,500) under output 4.1. Total $22,500 |
| 50 | Travel and DSA: Travel and DSA for Best practice learning and knowledge sharing exchange missions (2 Persons x $5,000 = $10,000). TOTAL = $10,000. |
| 51A | Contractual Services – Companies: Sub-contract – Develop project training and build stakeholder capacity (Environment). Develop and publicize Environment relevant Massive Open Online Courses based on the project developed trainings ($ 10,000) under output 4.1. Total = $ 10,000 (=20% of the total contract – see also budget note 25B) |
| 51B | Contractual Services – Companies: Sub-contract – Develop awareness raising materials relevant for the public and main agricultural sector stakeholders. Prepare IAS awareness-raising materials for public events and general distribution ($20,000); Organize publicity and awareness events at national, provincial and local levels ($8,750) both under output 4.1. Total = $28,750 |
| 52 | Miscellaneous: Contingency to cover exchange rate fluctuations and miscellaneous costs associated with organizing specialized meetings i.e. M&E monitoring of indicators in Results Framework. Total = $1,095 |
| 53 | Training & workshops: Provincial awareness events (2 x 5,000 = $10,000) under output 4.1; annual C-SAP 2 IAS project steering committee meetings (2 x $5,000 = $10,000) held on a rotational basis under output 4.4. TOTAL = $ 20,000 |
| 54 | Local consultants: Awareness raising consultant (Customs) (9 pw x $1,250 = $11,250) under output 4.1. Total $11,250 |
| 55 | Travel and DSA: Travel and DSA for Best practice learning and knowledge sharing exchange missions (10 Persons x $5,000 = $50,000). TOTAL = $50,000. |
| 56A | Contractual Services – Companies: Sub-contract – Develop project training and build stakeholder capacity (Customs). Develop and publicize Environment relevant Massive Open Online Courses based on the project developed trainings ($ 10,000) under output 4.1. Total = $ 10,000. (=18% of the total contract – see also budget note 31B) |
| 56B | Contractual Services – Companies: Sub-contract – Develop awareness raising materials relevant for the public and main agricultural sector stakeholders. Prepare IAS awareness-raising materials for public events and general distribution ($18,750); Organize publicity and awareness events at national, provincial and local levels ($35,000) both under output 4.1. Total = $53,750 |
| 57 | Miscellaneous: Contingency to cover exchange rate fluctuations and miscellaneous costs associated with organizing specialized meetings i.e. M&E monitoring of indicators in Results Framework. Total = $1,000 |
| 58 | Training & workshops: Awareness events (12 x 1,250 = $15,000) under output 4.1; annual C-SAP 2 IAS project steering committee meetings (2 x $5,000 = $10,000) held on a rotational basis under output 4.4. TOTAL = $ 25,000 |
| Project management |  |
| 59 | PMO travel: Mission travel to project locations to monitor project progress and participate in project events (12 x $1,000 = $12,000); Total = $12,000 |
| 60 | Contractual Services – Implementing Partner: Project Coordinator for overall project management including administrative and financial management (54 pm x $2,200 = $118,800); TOTAL = $118,800 |
| 61 | Miscellaneous: Contingency to cover exchange rate fluctuations and miscellaneous costs associated with organizing specialized meetings i.e. M&E monitoring of indicators in Results Framework. Total = $1,200 |

# Legal Context

Option a. Where the country has signed the Standard Basic Assistance Agreement (SBAA)

- This project document shall be the instrument referred to as such in Article 1 of the Standard Basic Assistance Agreement between the Government of (country) and UNDP, signed on 29 June 1979.   All references in the SBAA to “Executing Agency” shall be deemed to refer to “Implementing Partner.”

- This project will be implemented by the Ministry of Agriculture and Rural Affairs (“Implementing Partner”) in accordance with its financial regulations, rules, practices and procedures only to the extent that they do not contravene the principles of the Financial Regulations and Rules of UNDP. Where the financial governance of an Implementing Partner does not provide the required guidance to ensure best value for money, fairness, integrity, transparency, and effective international competition, the financial governance of UNDP shall apply.

- Any designations on maps or other references employed in this project document do not imply the expression of any opinion whatsoever on the part of UNDP concerning the legal status of any country, territory, city or area or its authorities, or concerning the delimitation of its frontiers or boundaries.

# Risk Management

Option a. Government Entity (NIM)

- Consistent with the Article III of the SBAA, the responsibility for the safety and security of the Implementing Partner and its personnel and property, and of UNDP’s property in the Implementing Partner’s custody, rests with the Implementing Partner.  To this end, the Implementing Partner shall:

- put in place an appropriate security plan and maintain the security plan, taking into account the security situation in the country where the project is being carried;

- assume all risks and liabilities related to the Implementing Partner’s security, and the full implementation of the security plan.

- UNDP reserves the right to verify whether such a plan is in place, and to suggest modifications to the plan when necessary. Failure to maintain and implement an appropriate security plan as required hereunder shall be deemed a breach of the Implementing Partner’s obligations under this Project Document.

- The Implementing Partner agrees to undertake all reasonable efforts to ensure that no UNDP funds received pursuant to the Project Document are used to provide support to individuals or entities associated with terrorism and that the recipients of any amounts provided by UNDP hereunder do not appear on the list maintained by the Security Council Committee established pursuant to resolution 1267 (1999). The list can be accessed via http://www.un.org/sc/committees/1267/aq_sanctions_list.shtml.

- Social and environmental sustainability will be enhanced through application of the UNDP Social and Environmental Standards (http://www.undp.org/ses) and related Accountability Mechanism (http://www.undp.org/secu-srm).

- The Implementing Partner shall: (a) conduct project and programme-related activities in a manner consistent with the UNDP Social and Environmental Standards, (b) implement any management or mitigation plan prepared for the project or programme to comply with such standards, and (c) engage in a constructive and timely manner to address any concerns and complaints raised through the Accountability Mechanism. UNDP will seek to ensure that communities and other project stakeholders are informed of and have access to the Accountability Mechanism.

- All signatories to the Project Document shall cooperate in good faith with any exercise to evaluate any programme or project-related commitments or compliance with the UNDP Social and Environmental Standards. This includes providing access to project sites, relevant personnel, information, and documentation.

- The Implementing Partner will take appropriate steps to prevent misuse of funds, fraud or corruption, by its officials, consultants, Co-Implementing Partners, subcontractors and sub-recipients in implementing the project or using UNDP funds.  The Implementing Partner will ensure that its financial management, anti-corruption and anti-fraud policies are in place and enforced for all funding received from or through UNDP.

- The requirements of the following documents, then in force at the time of signature of the Project Document, apply to the Implementing Partner: (a) UNDP Policy on Fraud and other Corrupt Practices and (b) UNDP Office of Audit and Investigations Investigation Guidelines. The Implementing Partner agrees to the requirements of the above documents, which are an integral part of this Project Document and are available online at www.undp.org.

- In the event that an investigation is required, UNDP has the obligation to conduct investigations relating to any aspect of UNDP projects and programmes. The Implementing Partner shall provide its full cooperation, including making available personnel, relevant documentation, and granting access to the Implementing Partner’s (and its consultants’, Co-Implementing Partners’, subcontractors’ and sub-recipients’) premises, for such purposes at reasonable times and on reasonable conditions as may be required for the purpose of an investigation. Should there be a limitation in meeting this obligation, UNDP shall consult with the Implementing Partner to find a solution.

- The signatories to this Project Document will promptly inform one another in case of any incidence of inappropriate use of funds, or credible allegation of fraud or corruption with due confidentiality.

- Where the Implementing Partner becomes aware that a UNDP project or activity, in whole or in part, is the focus of investigation for alleged fraud/corruption, the Implementing Partner will inform the UNDP Resident Representative/Head of Office, who will promptly inform UNDP’s Office of Audit and Investigations (OAI). The Implementing Partner shall provide regular updates to the head of UNDP in the country and OAI of the status of, and actions relating to, such investigation.

- UNDP shall be entitled to a refund from the Implementing Partner of any funds provided that have been used inappropriately, including through fraud or corruption, or otherwise paid other than in accordance with the terms and conditions of the Project Document.  Such amount may be deducted by UNDP from any payment due to the Implementing Partner under this or any other agreement.

- Where such funds have not been refunded to UNDP, the Implementing Partner agrees that donors to UNDP (including the Government) whose funding is the source, in whole or in part, of the funds for the activities under this Project Document, may seek recourse to the Implementing Partner for the recovery of any funds determined by UNDP to have been used inappropriately, including through fraud or corruption, or otherwise paid other than in accordance with the terms and conditions of the Project Document.

- Note:  The term “Project Document” as used in this clause shall be deemed to include any relevant subsidiary agreement further to the Project Document, including those with Co-Implementing Partners, subcontractors and sub-recipients.

- Each contract issued by the Implementing Partner in connection with this Project Document shall include a provision representing that no fees, gratuities, rebates, gifts, commissions or other payments, other than those shown in the proposal, have been given, received, or promised in connection with the selection process or in contract execution, and that the recipient of funds from the Implementing Partner shall cooperate with any and all investigations and post-payment audits.

- Should UNDP refer to the relevant national authorities for appropriate legal action any alleged wrongdoing relating to the project, the Government will ensure that the relevant national authorities shall actively investigate the same and take appropriate legal action against all individuals found to have participated in the wrongdoing, recover and return any recovered funds to UNDP.

- The Implementing Partner shall ensure that all of its obligations set forth under this section entitled “Risk Management” are passed on to each Co-Implementing Partners, subcontractor and sub-recipient and that all the clauses under this section entitled “Risk Management Standard Clauses” are included, mutatis mutandis, in all sub-contracts or sub-agreements entered into further to this Project Document.

# Mandatory Annexes

## Annex A: Multi-year Workplan

## Annex B: Overview of technical consultancies/subcontracts

## Annex C: Terms of Reference for Project Steering Committee, Project Coordinator, Chief Technical Advisor and other positions

## Annex D: UNDP Social and Environmental and Social Screening Template (SESP)

## Annex E: Stakeholder Engagement Plan

## Annex F: Gender Analysis and Action Plan

## Annex G: UNDP Risk Log

## Annex H: Results of the capacity assessment of the project implementing partner and HACT micro assessment

## Annex I (a): Additional agreements: Co-financing letters

## Annex I (b): Letter of Agreements

## Annex J: UNDP Project Quality Assurance Report

Other Annexes:

## Annex K: Social Economic survey

## Annex L:  Situation analysis

## Annex M: KAP Methodology

## Annex N: Capacity Development Scorecards

## Annex O: Yangpu Scorecard

## Annex P: Yangpu port description

## Annex Q: Landscape profiles

## Annex R: Program Organizational Chart

## Annex S: C-SAP Program Results Framework

## Annex T: GEF Core Indicators

## Annex U: Roles of Implementing Partner and Co-Implementing Partners in activity implementation

## Annex V: Stakeholder involvement in project activities.

Megadiversity: Earth's biologically wealthiest nations (Mittermeier, Gil and Mittermeier eds. 1997. Cemex, Mexico).

FAO. 2008. China Country Report on the State of Plant Genetic Resources for Food and Agriculture.

YUAN, Nan-nan & WEI, Xin & XUE, Da-yuan & YANG, Qing-wen. (2013). The origin and evolution of upland rice in Li ethnic communities in Hainan Province, China. Journal of Plant Genetic Resources. 14. https://www.researchgate.net/publication/263222416_The_origin_and_evolution_of_upland_rice_in_Li_ethnic_communities_in_Hainan_Province_China

Vila` M et al (2011): Ecological impacts of invasive alien plants: a meta-analysis of their effects on species, communities and ecosystems Ecology Letters, 14: 702–708

Xu H, et al. 2006. The distribution and economic losses of alien species invasion to China. Biological Invasions 8: 1495–1500

Wan FH and Yang N (2016): Invasion and Management of Agricultural Alien Insects in China Annual Review of Entomology Volume 61, 77-98

Zhang G. ,Cao A., Fu D .Agricultural Major Invasive Biological Emergency Prevention and Control Technology Guide .Science Press.2009.

Cao A., Ouyang  C., Zhang G. Progress on the Prevention and Control Technologies of Invasive Weeds .Chemical Industry Press. 2016.

Zhang G., Fu W., Song Y. Monitoring and control of invasive alien species. China Agricultural Press, 2018.

Gan N, Yin Z, Tan Z, 2015. China Household Finance Survey Report 2014. Chengdu: Southwestern University of Finance and Economics Press.

Y. Zhang, et al., Traditional culture as an important power for maintaining agricultural landscapes in cultural heritage sites: A case study of the Hani terraces, Journal of Cultural Heritage (2016), http://dx.doi.org/10.1016/j.culher.2016.12.002

Wan FH and Yang N (2016): Invasion and Management of Agricultural Alien Insects in China Annual Review of Entomology Volume 61, 77-98

Fu W., Zhang G., Zhang R. Monitoring and control of Alligator weed . China Agriculture Press. 2016.

Fu W., Zhang G., Zhang R .Monitoring and control of water hyacinth. China Agriculture Press.2017.

Jianqing Ding, Richard n. Mack, Ping Lu Mingxun Ren and Hongwen Huang (2008) China’s Booming Economy Is Sparking and Accelerating Biological Invasions BioScience Vol. 58 No. 4 doi:10.1641/B580407

Yang, Y. et al. Historical invasion, expansion process and harm investigation of Pomacea canaliculata in China. Chinese Agri. Sci. Bull. 26, 245–250 (2010)

The Ministry of Environmental Protection of China. (2014) China's Fifth National Report on the Implementation of the Convention on Biological Diversity

Han Xu, Ke Chen, Zhiyun Ouyang, Xubin Pan and Shuifang Zhu (2012, )Threats of Invasive Species for China Caused by Expanding International Trade Environ. Sci. Technol. 46, 7063−7064 dx.doi.org/10.1021/es301996x

Axmacher JC, Sang W (2013) Plant Invasions in China – Challenges and Chances. PLoS ONE 8(5): e64173. doi:10.1371/journal.pone.0064173

The Ministry of Environmental Protection of China. (2014) China's Fifth National Report on the Implementation of the Convention on Biological Diversity

Wan FH and Yang N (2016): Invasion and Management of Agricultural Alien Insects in China Annual Review of Entomology Volume 61, 77-98

Zhang G.,Fu W., Song Y. Technical Manual for Integrated Prevention and Control of National  Key Management of Invasive Species. China Agriculture Press, 2013.

The Ministry of Environmental Protection of China. (2014) China's Fifth National Report on the Implementation of the Convention on Biological Diversity

Wan FH and Yang N (2016): Invasion and Management of Agricultural Alien Insects in China Annual Review of Entomology Volume 61, 77-98

Jiang M., Huang Y., Wan F. (2017) Biological Invasions in Agricultural Ecosystems in China. In: Wan F., Jiang M., Zhan A. (eds) Biological Invasions and Its Management in China. Invading Nature - Springer Series in Invasion Ecology, vol 11. Springer, Dordrecht

Jiang M., Huang Y., Wan F. (2017) Biological Invasions in Agricultural Ecosystems in China. In: Wan F., Jiang M., Zhan A. (eds) Biological Invasions and Its Management in China. Invading Nature - Springer Series in Invasion Ecology, vol 11. Springer, Dordrecht

Zhang G. ,Cao A., Fu D .Agricultural Major Invasive Biological Emergency Prevention and Control Technology Guide .Science Press.2009.

Fu W., Zhang G., Zhang R. Monitoring and control of Alligator weed . China Agriculture Press. 2016.

Fu W., Zhang G., Zhang R .Monitoring and control of water hyacinth. China Agriculture Press. 2017.

Zhang G., Fu W., Song Y. Technical Manual for Integrated Prevention and Control of National Key Management of Invasive Species. China Agriculture Press, 2013

Jiang M., Huang Y., Wan F. (2017) Biological Invasions in Agricultural Ecosystems in China. In: Wan F., Jiang M., Zhan A. (eds) Biological Invasions and Its Management in China. Invading Nature - Springer Series in Invasion Ecology, vol 11. Springer, Dordrecht

The Ministry of Environmental Protection of China. (2014) China's Fifth National Report on the Implementation of the Convention on Biological Diversity

Jiang M., Huang Y., Wan F. (2017) Biological Invasions in Agricultural Ecosystems in China. In: Wan F., Jiang M., Zhan A. (eds) Biological Invasions and Its Management in China. Invading Nature - Springer Series in Invasion Ecology, vol 11. Springer, Dordrecht

China's Protected Area System Reform program GEF Project ID‎: ‎9403

Megadiversity: Earth's biologically wealthiest nations (Mittermeier, Gil and Mittermeier eds. 1997. Cemex, Mexico).

China's Protected Area System Reform program GEF Project ID‎: ‎9403

China's Protected Area System Reform program GEF Project ID‎: ‎9403

Source: GEF/C.52/Inf.06, April 2017, Guidelines on the Project and Program Cycle Policy - Potential effect on the project if this risk were to occur: Probability P: 1 (low) to 5 (high); Impact I: 1 (low) to 5 (high)

See http://www.undp.org/content/undp/en/home/operations/transparency/information_disclosurepolicy/

See https://www.thegef.org/gef/policies_guidelines

See https://www.thegef.org/gef/policies_guidelines

See guidance here:  https://info.undp.org/global/popp/frm/pages/financial-management-and-execution-modalities.aspx

see  https://info.undp.org/global/popp/ppm/Pages/Closing-a-Project.aspx

See https://popp.undp.org/_layouts/15/WopiFrame.aspx?sourcedoc=/UNDP_POPP_DOCUMENT_LIBRARY/Public/PPM_Project%20Management_Closing.docx&action=default.