Annex B:  Overview of Technical Consultancies and Service Contracts

| Position/ Contract type | Time Input | Tasks, Inputs and qualifications |
| --- | --- | --- |
| Project Management Office |  |  |
| Local / National contracting |  |  |
| Technical Project Manager Rate: $2,900*/month * average based on 5% annual increment per year | 12 months per year over 5 years (= 60 months) | The Technical Project Manager (TPM), together with the CTA will be responsible for the overall management of the project, including the mobilization of all project inputs, supervision over project staff, consultants and sub-contractors. See the expanded TOR in Annex C for details. The Technical Project Manager’s costs are allocated as follows: Component 1: 14 months, Component 2: 18 months, Component 3: 10 months, Component 4: 10 months and Project Management 8 months |
| Project Assistant/ Finance/ Procurement Officer Rate: $2,200*/month * average based on 5% annual increment per year | 12 months per year over 5 years (= 60 months) | The Project Assistant/ Finance/ Procurement Officer will be responsible for Finance, Administration and procurement. See the expanded TOR in Annex C for details. The Project Assistant/ Finance/ Procurement Officer’s costs are allocated as follows: Component 4: 33 months and Project Management 27 months |
| Program Coordinator Rate: $2,200*/month * average based on 5% annual increment per year | 12 months per year over 5 years (= 60 months) | The Program Coordinator will be responsible for program coordination. See the expanded TOR in Annex C for details. The Program Coordinator costs are allocated as follows: Component 2: 12 months, Component 3: 15 month, Component 4: 25 months and Project Management 8 months |
| Program M&E /Safeguards Officer (Co-financed) | 12 months per year over 5 years (= 60 months) | The Program M&E/ Safeguard officer will be respobsible for the program monitoring and evaluation activities and actions including the child projects social and environmental reporting. See the expanded TOR in Annex C for details. |
| Chief Technical Adviser Rate: $5,500*/month * average based on 5% annual increment per year | 10 weeks per year in YRs1-5 (11.5 months) | Technical and adaptive management advice to Component 1. See the expanded TOR in Annex C for details. The C-SAP Chief Technical Adviser’s costs are allocated as follows: Component 1: 4.3 months, Component 1.5 months, Component 6.4 months. |
| For Technical Assistance |  |  |
| Local / national contracting |  |  |
| Sub-contract – Strengthen the regulatory framework and develop integrated IAS guidelines and methodologies (Agriculture) Cost for Component 1 = $35,000; Cost for Component 2 = $12,500; Total Cost = $47,500 | Years 1-2 | Tasks Under close supervision of the Technical Project Manager (TPM) and Chief Technical Advisor (CTA) and working closely with all experts from other service contracts and national experts working on the project, the successful supplier will specifically be responsible for MARA’s outputs in connection with activities: - Revise and adopt the regulation framework within MARA to optimize cross-sectoral IAS Management; - Develop provincial regulations for IAS prevention, control and management within MARA in Hainan and Chongqing; - Revise IAS Early Warning guidelines; - Revise IAS rapid response guidelines; - Support the MEE led development of an IAS Biodiversity Risk Assessment Guideline; - Provide support to the MEE led development of provincial IAS Biodiversity Risk Assessment Methodologies in Hainan; - Develop provincial IAS Early Warning Methodologies in Hainan. The subcontract will run simultaneously with similar sub-contracts managed by MEE and GACC (see below) which focuses on these entities respective sectors and the subcontractors will coordinate and cooperate with one another. MARA coordinates the process for the development of the IAS Early Warning guidelines and the IAS rapid response guidelines, whereas MEE leads the development of the IAS Biodiversity Risk Assessment Guideline. Expertise & Qualifications: - An academic institution/organization/enterprise/NGO or an alliance of above, either registered in China or a legal entity having a representative office in China, - An academic institution/organization/enterprise/NGO experienced in IAS prevention, control and management. International experience is preferred. - An academic institution/organization/enterprise/NGO experienced in working on national, provincial and local policy and regulatory frameworks. - The team leader should have solid expertise and rich experiences in policy making and its influence on IAS prevention, control and management in agroecosystems. - The team should have excellent skills in consulting, communicating, and coordinating and could tie-up with international and national experts who are qualified to provide related services - The professional expertise and background of key members should well cover the requirement of the tasks. - Expertise, sensitivity and knowledge on gender balance is required. - Excellent language skills in English (writing, speaking and reading) will be an advantage |
| Sub-contract – Develop National and Provincial IAS planning including Strategic Action Plans (Agriculture). Cost for Component 1 = $38,500; Cost for Component 3 = $135,250 Total Cost = $173,750 | Years 1-4 with bulk of work in years 2-3 | Tasks Under close supervision of the Technical Project Manager (TPM) and Chief Technical Advisor (CTA) and working closely with all experts from other service contracts and national experts working on the project, the successful supplier will specifically be responsible for MARA’s outputs in connection with activities: - Prepare the National IAS Management strategy and action plan (IAS NSAP 2021-2030); - Prepare Provincial IAS Management Strategy and Action Plan (IAS PSAP 2022-2030) for Hainan; - Develop MARA sectoral/ministerial Implementation Plans for the IAS NSAP 2021-2030; - Develop MARA sectoral/department Implementation Plans for the IAS PSAP 2022-2030 in Hainan and Chongqing; - Design the IAS distribution survey and IAS impact assessment of selected IAS in Wenchang and Bishan; - Undertake the IAS distribution survey and IAS impact assessment in Wenchang, Bishan and the representative protected area; Formulate the IAS distribution survey and IAS impact assessment reports for Wenchang, Bishan and the representative protected area; - Formulate IAS Management plans for Wenchang city and Bishan district; - Implement the IAS Management plans for the two project targeted agricultural landscapes in Wenchang city and Bishan district. The subcontract will run simultaneously with similar sub-contracts managed by MEE and GACC (see below) which focuses on these entities respective sectors and the subcontractors will coordinate and cooperate with one another. MARA coordinates the process for the development of the National and Provincial Strategic Action plans. Expertise & Qualifications: - An academic institution/organization/enterprise/NGO or an alliance of above, either registered in China or a legal entity having a representative office in China, - An academic institution/organization/enterprise/NGO experienced in IAS prevention, control and management. International experience is preferred. - An academic institution/organization/enterprise/NGO experienced in national and local planning processes including strategic planning as well as on the ground management plan development. - The team leader should have solid expertise and rich experiences in IAS prevention, control and management and leading planning processes. - The team should have excellent skills in consulting, communicating, and coordinating and could tie-up with international and national experts who are qualified to provide related services. - The team should have experience in stakeholder participation processes and have experience in holistic planning. - The professional expertise and background of key members should well cover the requirement of the tasks. - Expertise, sensitivity and knowledge on gender balance is required. - Excellent language skills in English (writing, speaking and reading) will be an advantage |
| Sub-contract – Develop project training and build stakeholder capacity (Agriculture). Cost for Component 2 = $25,000; Cost for Component 3 = 60,750; Cost for Component 4 = $10,000; Total Cost = $95,750 | Years 1-5 with main bulk of work in year 1 and 2. Provisions of training runs from year 2 onwards. | Tasks Under close supervision of the Technical Project Manager (TPM) and Chief Technical Advisor (CTA) and working closely with all experts from other service contracts and national experts working on the project, the successful supplier will specifically be responsible for MARA’s outputs in connection with activities: - Develop and organize R&D supported technical training courses; - Develop and publicize Agriculture relevant Massive Open Online Courses based on the project developed trainings; - Adapt trainings on key subjects, based on the developed training courses to address farmers and other stakeholders training needs; - Organize adapted trainings for different stakeholder groups including farmers, cooperatives, enterprises and other stakeholder; - Demonstrate verified and applicable participatory IAS Management approaches in Wenchang and Bishan; The subcontract will run simultaneously with a similar sub-contract managed by MEE (please see below) which will bring in the aspect of biodiversity and biodiversity concerns into the trainings and linked to the GACC training subcontract (see below) and the subcontractors will coordinate and cooperate with one another. MARA coordinates the process for the development of the training courses, and MARA will implement local trainings within the agricultural landscape. Expertise & Qualifications: - An academic institution/organization/enterprise/NGO or an alliance of above, either registered in China or a legal entity having a representative office in China, - An academic institution/organization/enterprise/NGO experienced in IAS prevention, control and management. International experience is preferred. - An academic institution/organization/enterprise/NGO experienced in stakeholder engagement and local community involvement. - An academic institution/organization/enterprise/NGO experienced in developing and delivering training in IAS Management targeting IAS in Agroecosystems. - The team leader should have solid expertise and rich experiences in IAS prevention, control and management preparing and delivering trainings to both government staff and members of the farming communities. - The team should have excellent skills in consulting, communicating, and coordinating and could tie-up with international and national experts who are qualified to provide related services. - The team should have experience in preparing training packages, making presentations and training videos, including preparing MOOCs. - The professional expertise and background of key members should well cover the requirement of the tasks. - Expertise, sensitivity and knowledge on gender balance is required. - Excellent language skills in English (writing, speaking and reading) will be an advantage |
| Sub-contract – Develop awareness raising materials relevant for the public and main environment agricultural sector Cost for Component 4 = $43,750. Total cost = $43,750 | Years 1-5 via renewable 1-year contracts | Tasks Under close supervision of the Technical Project Manager (TPM) and working closely with all experts from other service contracts and national experts working on the project, the successful supplier will specifically be responsible for MARA’s outputs in connection with activities: - Prepare IAS awareness-raising materials for public events and general distribution; - Organize publicity and awareness events at national, provincial and local levels. The subcontract will run simultaneously with similar sub-contracts managed by MEE and GACC (see below) which focuses on these entities respective sectors and the subcontractors will coordinate and cooperate with one another to avoid duplication and benefit from each other’s work. MARA/REEA, MEE/FECO and GACC/AIQ MARA will also ensure coordination among the entities to maximize the benefits from the different subcontractors. |
| Sub-contract - NIM Audit Cost for Component 4 = $25,000. Total cost = $25,000 | Years 1-5 Individual contracts tendered each year | See UNDP standard TOR for NIM Audits. |
| Sub-contract - Knowledge, attitude and practices (KAP survey) Cost for Component 4 = $40,000. Total cost = $40,000 | Year 1 and Year 5 | See the Annex M for details. |
| Sub-contract – Strengthen the regulatory framework and develop integrated IAS guidelines and methodologies (Environment) Cost for Component 1 = $116,250; Cost for Component 2 = $15,000; Total Cost = $131,250 | Years 1-2 | Tasks Under close supervision of the MEE/FECO and Chief Technical Advisor (CTA) and working closely with all experts from other service contracts and national experts working on the project, the successful supplier will specifically be responsible for MEE’s outputs in connection with activities: - Revise and adopt the regulation framework within MEE to optimize cross-sectoral IAS Management; - Develop provincial regulation for IAS prevention, control and management within MEE in Hainan and Chongqing; - Support the Mara led revision of IAS Early Warning guidelines; - Support the Mara led revision of IAS rapid response guidelines; Develop an IAS Biodiversity Risk Assessment Guideline; - Develop IAS buffer zone guideline for areas surrounding ecological functioning zones and protected areas; - Develop IAS Biodiversity Risk Assessment, Early Warning; - Rapid Response guidelines for protected areas; - Develop provincial IAS Biodiversity Risk Assessment Methodologies in Hainan; - Support the MARA led development of provincial IAS Early Warning Methodologies in Hainan; - Undertake an IAS Biodiversity Risk Assessment for Hainan. The subcontract will run simultaneously with similar sub-contracts managed by MARA (see above) and GACC (see below) which focuses on these entities respective sectors and the subcontractors will coordinate and cooperate with one another. MARA coordinates the process for the development of the IAS Early Warning guidelines and the IAS rapid response guidelines, whereas MEE leads the development of the IAS Biodiversity Risk Assessment Guideline. Expertise & Qualifications: - An academic institution/organization/enterprise/NGO or an alliance of above, either registered in China or a legal entity having a representative office in China, - An academic institution/organization/enterprise/NGO experienced in IAS prevention, control and management. International experience is preferred. - An academic institution/organization/enterprise/NGO experienced in working on national, provincial and local policy and regulatory frameworks, with specific reference to protected areas and other conservation areas. - The team leader should have solid expertise and rich experiences in policy making and its influence on IAS prevention, control and management in protected areas and other conservation areas. - The team should have excellent skills in consulting, communicating, and coordinating and could tie-up with international and national experts who are qualified to provide related services - The professional expertise and background of key members should well cover the requirement of the tasks. - Expertise, sensitivity and knowledge on gender balance is required. - Excellent language skills in English (writing, speaking and reading) will be an advantage |
| Sub-contract – Develop National and Provincial IAS planning including Strategic Action Plans (Environment). Cost for Component 1 = $20,000; Cost for Component 3 = $58,000 Total Cost = $78,000 | Years 1-4 with bulk of work in years 2-3 | Tasks Under close supervision of the MEE/FECO and Chief Technical Advisor (CTA) and working closely with all experts from other service contracts and national experts working on the project, the successful supplier will specifically be responsible for MEE’s outputs in connection with activities: - Support the MARA led preparation of the National IAS Management strategy and action plan (IAS NSAP 2021-2030); Support the MARA preparation of Provincial IAS Management Strategy and Action Plan (IAS PSAP 2022-2030) for Hainan and Chongqing; - Develop MEE sectoral/ministerial Implementation Plans for the IAS NSAP 2021-2030; - Develop MEE sectoral/department Implementation Plans for the IAS PSAP 2022-2030 in Hainan and Chongqing; - Design the IAS distribution survey and IAS impact assessment of selected IAS in a representative protected area; - Undertake the IAS distribution survey and IAS impact assessment in a representative protected area; - Formulate the IAS distribution survey and IAS impact assessment reports for the representative protected area The subcontract will run simultaneously with similar sub-contracts managed by MARA (see above) and GACC (see below) which focuses on these entities respective sectors and the subcontractors will coordinate and cooperate with one another. MARA coordinates the process for the development of the National and Provincial Strategic Action plans. Expertise & Qualifications: - An academic institution/organization/enterprise/NGO or an alliance of above, either registered in China or a legal entity having a representative office in China, - An academic institution/organization/enterprise/NGO experienced in IAS prevention, control and management. International experience is preferred. - An academic institution/organization/enterprise/NGO experienced in national and local planning processes including strategic planning as well as on the ground management plan development. - The team leader should have solid expertise and rich experiences in IAS prevention, control and management and leading planning processes. - The team should have ample experience in how integrate biodiversity as a valid parameter in the IAS Management planning processes. - The team should have excellent skills in consulting, communicating, and coordinating and could tie-up with international and national experts who are qualified to provide related services. - The team should have experience in stakeholder participation processes and have experience in holistic planning. - The professional expertise and background of key members should well cover the requirement of the tasks. - Expertise, sensitivity and knowledge on gender balance is required. - Excellent language skills in English (writing, speaking and reading) will be an advantage |
| Sub-contract – Develop project training and build stakeholder capacity (Environment). Cost for Component 2 = $41,250; Cost for Component 4 = $10,000; Total Cost = $51,250 | Years 1-5 with main bulk of work in year 1 and 2. Provisions of training runs from year 2 onwards. | Tasks Under close supervision of MEE/FECO and Chief Technical Advisor (CTA) and working closely with all experts from other service contracts and national experts working on the project, the successful supplier will specifically be responsible for MEEs outputs in connection with activities: - Support the development of R&D supported technical training courses; - Organize selected trainings for managers and staff working at protected areas, reserves or other ecological sensitive areas; - Develop and publicize Environment relevant Massive Open Online Courses based on the project developed trainings. The subcontract will run simultaneously with a similar sub-contract managed by MARA (see above) which will bring in the aspect of biodiversity and biodiversity concerns into the trainings and linked to the GACC training subcontract (please see below) and the subcontractors will coordinate and cooperate with one another. MEE will adapt and provide the training for protected areas staff and other stakeholders. Expertise & Qualifications: - An academic institution/organization/enterprise/NGO or an alliance of above, either registered in China or a legal entity having a representative office in China, - An academic institution/organization/enterprise/NGO experienced in IAS prevention, control and management. International experience is preferred. - An academic institution/organization/enterprise/NGO experienced in developing and delivering training in IAS Management targeting IAS in protected areas. - The team leader should have solid expertise and rich experiences in IAS prevention, control and management preparing and delivering trainings to both government staff with a specific focus on staff working with protected areas and other conservation areas. - The team should have excellent skills in consulting, communicating, and coordinating and could tie-up with international and national experts who are qualified to provide related services. - The team should have experience in preparing training packages, making presentations and training videos, including preparing MOOCs. - The professional expertise and background of key members should well cover the requirement of the tasks. - Expertise, sensitivity and knowledge on gender balance is required. Excellent language skills in English (writing, speaking and reading) will be an advantage |
| Sub-contract – Develop awareness raising materials relevant for the public and main Environment sector Cost for Component 4 = $28,750. Total cost = $28,750 | Years 1-5 via renewable 1-year contracts | Tasks Under close supervision of MEE/FECO and working closely with all experts from other service contracts and national experts working on the project, the successful supplier will specifically be responsible for MEE’s outputs in connection with activities: - Prepare IAS awareness-raising materials for public events and general distribution; - Organize publicity and awareness events at national, provincial and local levels. The subcontract will run simultaneously with similar sub-contracts managed by MARA (see above) and GACC (see below) which focuses on these entities respective sectors and the subcontractors will coordinate and cooperate with one another to avoid duplication and benefit from each other’s work. MARA/REEA, MEE/FECO and GACC/AIQ MARA will also ensure coordination among the entities to maximize the benefits from the different subcontractors. |
| Sub-contract – Strengthen the regulatory framework and develop integrated IAS guidelines and methodologies (Customs) Cost for Component 1 = $52,500; Cost for Component 2 = $87,500; Total Cost = $140,000 | Years 1-2 | Tasks Under close supervision of the GACC/CAIQ and Chief Technical Advisor (CTA) and working closely with all experts from other service contracts and national experts working on the project, the successful supplier will specifically be responsible for GACC’s outputs in connection with activities: - Revise and adopt the regulation framework within GACC to optimize cross-sectoral IAS Management; - Develop provincial regulation for IAS prevention, control and management within GACC in Hainan and Chongqing; - Support the MARA led revision of IAS Early Warning guideline; - Include biodiversity into the updates of the 2007 National Quarantine Pest list; - Support the MARA led development of provincial IAS Early Warning Methodologies in Hainan; - Update the national technical specification for IAS inspection, quarantine and disposal used at Yangpu port; - Review and update quarantine standards; - Formulate/revise quarantine management methodologies The subcontract will run simultaneously with similar sub-contracts managed by MARA and MEE (see above) which focuses on these entities respective sectors and the subcontractors will coordinate and cooperate with one another. MARA coordinates the process for the development of the IAS Early Warning guidelines and the IAS rapid response guidelines, whereas MEE leads the development of the IAS Biodiversity Risk Assessment Guideline. Expertise & Qualifications: - An academic institution/organization/enterprise/NGO or an alliance of above, either registered in China or a legal entity having a representative office in China, - An academic institution/organization/enterprise/NGO experienced in IAS prevention, control and management. International experience is preferred. - An academic institution/organization/enterprise/NGO experienced in working on national, provincial and local policy and regulatory frameworks, with specific reference to regulations guiding IAS Management at ports. - The team leader should have solid expertise and rich experiences in policy making and its influence on IAS Management in ports, as well as knowledge about quarantine procedures and IAS handling at ports. - The team should have excellent skills in consulting, communicating, and coordinating and could tie-up with international and national experts who are qualified to provide related services - The professional expertise and background of key members should well cover the requirement of the tasks. - Expertise, sensitivity and knowledge on gender balance is required. - Excellent language skills in English (writing, speaking and reading) will be an advantage |
| Sub-contract – Develop National and Provincial IAS planning including Strategic Action Plans (Customs). Cost for Component 1 = $46,750 Total Cost = $46,750 | Years 1-4 with bulk of work in years 2-3 | Tasks Under close supervision of the GACC/CAIQ and Chief Technical Advisor (CTA) and working closely with all experts from other service contracts and national experts working on the project, the successful supplier will specifically be responsible for GACC’s outputs in connection with activities: - Support the MARA led preparation of the National IAS Management strategy and action plan (IAS NSAP 2021-2030); - Support the MARA preparation of Provincial IAS Management Strategy and Action Plan (IAS PSAP 2022-2030) for Hainan and Chongqing; - Develop GACC sectoral/ministerial Implementation Plans for the IAS NSAP 2021-2030; - Develop GACC sectoral/department Implementation Plans for the IAS PSAP 2022-2030 in Hainan and Chongqing; The subcontract will run simultaneously with similar sub-contracts managed by MARA and MEE (see above) which focuses on these entities respective sectors and the subcontractors will coordinate and cooperate with one another. MARA coordinates the process for the development of the National and Provincial Strategic Action plans. Expertise & Qualifications: - An academic institution/organization/enterprise/NGO or an alliance of above, either registered in China or a legal entity having a representative office in China, - An academic institution/organization/enterprise/NGO experienced in IAS prevention, control and management. International experience is preferred. - An academic institution/organization/enterprise/NGO experienced in national and local planning processes including strategic planning as well as on the ground management plan development. - The team leader should have solid expertise and rich experiences in IAS prevention, control and management and leading planning processes. - The team should have ample experience in how to integrate port safety measures into local planning with the aim to prevent IAS spread - The team should have excellent skills in consulting, communicating, and coordinating and could tie-up with international and national experts who are qualified to provide related services. - The team should have experience in stakeholder participation processes and have experience in holistic planning. - The professional expertise and background of key members should well cover the requirement of the tasks. - Expertise, sensitivity and knowledge on gender balance is required. - Excellent language skills in English (writing, speaking and reading) will be an advantage |
| Sub-contract – Develop project training and build stakeholder capacity (Customs). Cost for Component 2 = $46,345; Cost for Component 4 = $10,000; Total Cost = $56,345 | Years 1-5 with main bulk of work in year 1 and 2. Provisions of training runs from year 2 onwards. | Tasks Under close supervision of GACC/CAIQ and Chief Technical Advisor (CTA) and working closely with all experts from other service contracts and national experts working on the project, the successful supplier will specifically be responsible for GACC’s outputs in connection with activities: - Develop and organize trainings on the implementation of the national technical specification for IAS inspection; - Develop and organize trainings on quarantine and disposal; - Develop and organize trainings on the updated quarantine standards and methodologies; - Develop and publicize Environment relevant Massive Open Online Courses based on the project developed trainings. The subcontract will focus on customs and personnel at ports but as there is a link to the other trainings developed by MARA and MEE (see above) and the subcontractors will coordinate and cooperate with one another. GACC will provide the training to the customs staff and other relevant stakeholders. Expertise & Qualifications: - An academic institution/organization/enterprise/NGO or an alliance of above, either registered in China or a legal entity having a representative office in China, - An academic institution/organization/enterprise/NGO experienced in IAS prevention, control and management. International experience is preferred. - An academic institution/organization/enterprise/NGO experienced in developing and delivering training in IAS Management targeting IAS in protected areas. - The team leader should have solid expertise and rich experiences in IAS prevention, control and management at ports, particularly with regard to national standards and quarantine procedures. - The team should have expert knowledge of the standards and guidelines used at Yangpu (and similar) ports, and be familiar with the new quarantine standards and methodologies. - The team should have excellent skills in consulting, communicating, and coordinating and could tie-up with international and national experts who are qualified to provide related services. - The team should have experience in preparing training packages, making presentations and training videos, including preparing MOOCs. - The professional expertise and background of key members should well cover the requirement of the tasks. - Expertise, sensitivity and knowledge on gender balance is required. - Excellent language skills in English (writing, speaking and reading) will be an advantage |
| Sub-contract – Develop awareness raising materials relevant for the public and main Customs sector Cost for Component 4 = $53,750. Total cost = $53,750 | Years 1-5 via renewable 1-year contracts | Tasks Under close supervision of GACC/CAIQ and working closely with all experts from other service contracts and national experts working on the project, the successful supplier will specifically be responsible for GACC’s outputs in connection with activities: - Prepare IAS awareness-raising materials for public events and general distribution; - Organize publicity and awareness events at national, provincial and local levels. The subcontract will run simultaneously with similar sub-contracts managed by MARA and MEE (see above) which focuses on these entities respective sectors and the subcontractors will coordinate and cooperate with one another to avoid duplication and benefit from each other’s work. MARA/REEA, MEE/FECO and GACC/AIQ MARA will also ensure coordination among the entities to maximize the benefits from the different subcontractors. |
| 2 National consultants for the Mid Term Review Rate: $250/day | 20 days (each) in Year 3 | See UNDP standard TOR for this position. |
| 2 National consultants for the Terminal Evaluation Rate: $250/day | 23 days (each) in Year 5 | See UNDP standard TOR for this position. |
| International/regional and global contracting |  |  |
| International consultant for the Mid Term Review Rate: $650/day | 35 days in Year 3 | See UNDP standard TOR for this position. |
| International consultant for the Terminal Evaluation Rate: $650/day | 40 days in Year 5 | See UNDP standard TOR for this position. |