UN Environment GEF PIR Fiscal Year 2019

- July 2018 to 30 June 2019)

| - Identification |  |  | 4668 | SB-001062.01.04 |
| --- | --- | --- | --- | --- |
| Project Number + Project Title |  |  | Demonstration of effectiveness of diversified, environmentally sound and sustainable interventions, and strengthening national capacity for innovative implementation of integrated vector management (IVM) for disease prevention and control in the WHO AFRO |  |
| Duration months | Planned |  | 60 months |  |
|  | Extension(s) |  |  |  |
| Division(s) Implementing the project |  |  | UNEP GEF Chemicals and Waste |  |
| Executing Agency(ies) |  |  | WHO Regional Office for Africa, Brazzaville, Congo |  |
| Names of Other Project Partners |  |  | International Centre of Insect Physiology and Ecology (ICIPE) Ministries of Health (Botswana, Namibia, Mozambique, Eswatini, South Africa, Zambia, Zimbabwe, The Gambia, Kenya, Liberia, Madagascar, Senegal and Uganda) |  |
| Project Type |  |  | FSP |  |
| Project Scope |  |  | Regional |  |
| Region (delete as appropriate) |  |  | AFR |  |
| Names of Beneficiary Countries |  |  | Tier 1: Botswana, Eswatini Mozambique, Namibia, South Africa, Zambia, Zimbabwe, Tier 2: The Gambia, Kenya, Liberia, Madagascar, Senegal, Tanzania, Uganda, |  |
| Programme of Work |  |  | Chemicals and Health Programme of Work |  |
| GEF Focal Area(s) |  |  | POPs |  |
| UNDAF linkages |  |  | Where appropriate, insert the UNDAF strategic objective to which achievement of the project contributes. Mozambique: The UNDAF 2017-2020 strategic objective is to achieve a situation where “The population of Mozambique, especially those living in the most vulnerable conditions, enjoy prosperity through equitable access to resources and quality services in a peaceful and sustainable environment”. The UNDAF is founded on a shared approach: “Delivering as One” that underpin Agenda 2030 and the 17 Sustainable Development Goals (SDGs) at its core. The Government, with UN support international gender standards, equitable access to timely, quality and affordable health care and a healthy environment. Zimbabwe: The 2016-2020 Zimbabwe United Nations Development Assistance Framework (ZUNDAF) is the one nationally-owned United Nations (UN) strategic programme framework towards the achievement of the SDGs as well as other international commitments, norms and standards. The implementation of the 2016-2020 ZUNDAF has a sustainable impact in its contribution to ending poverty, achieving gender equality, transforming all lives, and protecting the planet. The ZUNDAF offers opportunities to strengthen partnerships, linkages and programming, including those with other major development frameworks. Botswana: The collective aspiration under the United Nations Sustainable Development Framework (UNSDF) 2017-2021 is to move toward realization of SDGs through greater collaboration, focus and coherence in programming, and to improve the quality of life for all people in Botswana, particularly the most vulnerable groups. The UNSDF 2017-2021 thus focuses on strengthening coherence between Agencies, and promotes greater, accountability, efficiency, effectiveness and sustainability in Botswana’s pursuit of sustained and inclusive economic growth, social development and environmental protection. Namibia: The United Nations Partnership Framework (UNPAF) 2019-2023, strives towards partnership to enhance the coherence and efficiency to achieving the longer-term SDGs, the Africa Agenda 2063, and the country’s human rights obligations and other commitments under internationally agreed conventions and treaties, including Social transformation, environmental sustainability and good governance. The overarching objective of the UNPAF 2019-23 is to make Namibia a developed nation with an equitable, inclusive, peaceful and sustainable societal and economic fabric, a resilient environment and transformational governance in line with the SDGs by 2030.” Eswatini: The UNDAF 2016-2020 aims to catalyze sustainable changes that will strengthen systems during and beyond the period covered (2016 – 2020). Three priority areas have been identified for the UNDAF; Poverty and inequality reduction, inclusive growth and sustainable development, Equitable and efficient delivery and access to social services, and Good Governance and Accountability. Zambia: The United Nations Sustainable Development Partnership Framework (2016-2021) is in line with the SDGs and aspirations for transformation towards a “prosperous middle-income nation” by 2030. The efforts are underpinned by three results pillars: Inclusive Social Development, Environmentally Sustainable and Inclusive Economic Development, and Governance and Participation. The Vision is based on seven key principles, including: i) gender responsive sustainable development; iii) respect for human rights; and vii) private-public partnerships. Progress towards middle-income Zambia comes with addressing inequality, strengthening social protection and reducing vulnerabilities |  |
| Link to relevant SDG target(s) and SDG indicator(s) |  |  | Where appropriate, insert the most relevant SDG target(s) and indicator(s) to which the project contributes The AFRO II Project is directly linked with the 2030 Agenda for SDG 1, 3, 6, 11, 12, 13 and 17 with their associated sub-goals and targets. The progress made towards respective goals, sub-goals and associated targets to which they contribute are as follows: Goal 1: End poverty in all its forms everywhere; Targets 1.1, 1.2 and 1.5 Goal 3: Ensure healthy lives and promote well-being for all at all ages; Target 3.1, 3.2 and 3.3. Goal 6: Ensure availability and sustainable management of water and sanitation for all; Target 6.3. Goal 11: Make cities and human settlements inclusive, safe, resilient and sustainable; Targets 11.1 and 11.5; sub-goals 11.a and 11.b Goal 12: Ensure sustainable consumption and production patterns; Target 12.4; sub-goal 12.a. Goal 13: Take urgent action to combat climate change and its impacts; Target 13.3, and sub-goal 13.b. Goal 17: strengthen the means of implementation and revitalize the global partnership for sustainable development. Target 17.3, 17.9 and 17.17. |  |
| GEF financing amount |  |  | 9550000 |  |
| Co-financing amount |  |  | 243103508 |  |
| Date of CEO Endorsement |  |  | 07-Mar-16 |  |
| Start of Implementation |  |  | 01-Dec-16 |  |
| Date of first disbursement |  |  | 11-Jul-16 |  |
| Total disbursement as of 30 June |  |  | 2400000 |  |
| Total expenditure as of 30 June |  |  | 2267654 |  |
| Expected Mid-Term Date |  |  | July 2019 |  |
| Completion Date |  | Planned | 01-Dec-21 |  |
|  |  | Revised | na |  |
| Expected Terminal Evaluation Date |  |  | na |  |
| Expected Financial Closure Date |  |  | Dec-22 |  |

- OVERVIEW OF PROJECT STATUS

To be completed by UNEP/GEF Task Manager

| UN Environment Subprogramme(s) Chemicals, Waste and Air Quality Subprogramme EA (a) Policies and legal, institutional and fiscal strategies and mechanisms for sound chemicals management developed or implemented in countries within the framework of relevant multilateral environmental agreements and the Strategic Approach to International Chemicals Management (SAICM) | Specify the relevant Expected Accomplishment(s) & Indicator(s) a(i) Increase in the number of countries that have used UNEP analysis or guidance, and where possible are applying a multi-sectoral approach, in developing or implementing legislation, policies or action plans that promote sound chemicals management and implementation of the relevant multilateral environmental agreements and SAICM |
| --- | --- |
| Describe any progress made towards delivering the stated PoW Expected Accomplishments and Indicators. State key changes since previous reporting period. [Section to be shared with relevant Regional and Global SubProgramme Coordinators] The project has contributed to the Expected Accomplishment in the last year by promoting action by governments towards adopting alternatives to DDT. Following the achievement in the previous PIR of Zimbabwe notifying the Stockholm Secretariat of its use of DDT via the DDT Register, progress was made with reporting to the Stockholm Convention in the 2018 reporting round. Although only three countries submitted the DDT Questionnaire (the same number as the baseline), two further countries did submit information on stockpiles for a global survey (Namibia and Zambia). Two countries (Botswana and Namibia) have developed national IVM strategies with project support, these national policies / strategic documents promote alternative approaches to relying only on spraying with insecticides and especially DDT. |  |

For all GEF 6 and later projects:

| GEF Core Indicators Insert core indicator(s) from Core Indicator Worksheet to which the project contributes | Indicative expected Results [add figure approved at CEO endorsement/ approval] |
| --- | --- |
| Indicator 9.4 Number of countries with legislation and policy implemented to control chemicals and waste Indicator 9.5 Number of low-chemical/non-chemical systems implemented particularly in food production, manufacturing and cities | Indicative expected Results Seven countries with IVM strategies Six countries applying IVM for malaria control |
| Describe any progress made towards meeting the indicative expected results as per the approved project documentation. Describe any key changes since previous reporting period. Two of the seven project countries have developed national IVM strategies in the reporting period. Five countries have obtained ethical clearance of an IVM demonstration protocol to roll out alternatives to indoor residual spraying with DDT in malarious regions. |  |

To be completed by Project Manager, as relevant

| Planned linkages with UNDAF | Describe progress towards the UNDAF strategic objective to which the project contributes. Mozambique: The project contributes towards achieving international gender standards by providing equitable job opportunities for project personnel. The project ensures equitable access to timely, quality and affordable health care by protecting people from malaria through effective vector control. The project has also contributed towards achieving a healthy environment by promoting the use of non-insecticide vector control as well as community sensitization on the use of DDT. Zimbabwe: The project contributes towards ending poverty by protecting people from malaria through vector control and preventing malaria related absenteeism from work or schools. The project also contributes towards achieving gender equality by providing equitable job opportunities for project personnel, and protects the planet by promoting the use of non-insecticide vector control as well as community sensitization on the use of DDT. Botswana: The AFRO II project contributes towards efficiency, effectiveness and sustainability, and social development by providing scale vector control interventions to the most vulnerable population groups; The project provides inclusive economic growth by empowering women and youth to be contracted and participate in the project. Environmental protection is achieved in the project by promoting non-insecticide interventions for vector control. Namibia: The AFRO II project contributes towards social transformation through provision of wide scale vector control interventions to the marginalized and vulnerable populations; The project provides inclusive gender responsive economic opportunities and sustainable societal and economic fabric by empowering women and youth to participate in the project. Multi-sectoral stakeholder meetings contribute towards transformational governance. To contribute to environmental sustainability the project promotes non-insecticide interventions for vector control. Eswatini: The project contributes towards: support the domestication of international instruments on environment by providing employment opportunities to youth and women and sustainable livelihoods improvement. It also contributes towards via improved management of natural resources by communities’ and national institutions, including supporting the domestication of international instruments on environment such as the SSC. Also by equitable and efficient delivery and access to social services, eg increased access to and uptake of quality health vis a vis vector control by families and communities. The project also contributes to Good Governance and Accountability through Citizen and Civil Society Organizations’ participation in decision-making processes at all levels during multisectral meetings, community consultations. Zambia: The project contributes towards inclusive social development through provision of access and utilization of vector control interventions by marginalized and vulnerable populations; The project provides gender responsive economic opportunities that are decent and promote sustainable livelihoods by empowering women and youth to participate in the project. Public-private partnerships are assured through stakeholder meetings. The project contributes to environmental sustainability by promoting non-insecticide interventions for vector control. [Section to be shared with Monitoring Unit within PPD] |
| --- | --- |

| Planned contribution to relevant SDG target(s) and SDG indicator(s) | Describe progress towards the stated SDG target(s) and SDG indicator(s) to which the project contributes [section to be shared with SDG unit] The AFRO II Project is directly linked with the 2030 Agenda for SDG 1, 3, 6, 11, 12, 13 and 17 with their associated sub-goals and targets. The progress made towards respective goals, sub-goals and associated targets to which they contribute by project countries, particularly Botswana, Eswatini, Mozambique, Namibia and Zambia, are as follows: Goal 1: End poverty in all its forms everywhere; The project countries have made progress in contributing towards targets 1.1, 1.2 by reducing absenteeism from work and school due to episodes of malaria through effective vector control, and towards 1.5 by contracting and engaging women and youth in the project implementation, and sensitizing them on DDT thus building their resilience to environmental shocks. Goal 3: Ensure healthy lives and promote well-being for all at all ages; By implementing effective vector control to protect people from malaria, countries have made progress on target 3.1 and 3.2 in reducing deaths of new borns and children under 5 years of age. Botswana, Eswatini and Namibia have made progress towards target 3.3 as they drive to focalized malaria elimination. Goal 6: Ensure availability and sustainable management of water and sanitation for all; By implementing larval source management as alternative to DDT through larvicides through environmental manipulation of water bodies to deprive malaria vector of suitable breeding sites, and supporting countries in DDT reporting to the Stockholm Convention Secretariat on use and storage of obsolete quantities, All the six countries have made progress towards target 6.3 to minimize release of hazardous chemicals into water bodies. Goal 11: Make cities and human settlements inclusive, safe, resilient and sustainable; Mozambique, Zambia and Zimbabwe have made progress on target 11.1 by implementing the house screening demonstration as a safe and basic service, and towards target 11.5 by protecting the poor and people in vulnerable situations through hose screening to reduce the number of people dying from malaria. The countries have also contributed towards target 11.a and 11.b by supporting social and environmental links through social impact assessments on DDT as part of integrated policies and plans. Goal 12: Ensure sustainable consumption and production patterns; In all the six countries, the project contributes to target 12.4; achieving the environmentally sound management of chemicals and all wastes throughout their life cycle by monitoring reporting, judicious use and obsolete quantities storage of DDT to avoid adverse impact on human health and environment, and sub-goal 12.a; by supporting the six countries on scientific and technological capacities on insecticide consumption. Goal 13: Take urgent action to combat climate change and its impacts; The project contributes target 13.3, and sub-goal 13.b through information sharing during multi-sectoral meetings and community engagement efforts during project activity implementation. Goal 17: strengthen the means of implementation and revitalize the global partnership for sustainable development. All project has made appreciable progress towards target 17.3 by mobilizing resources for activity implementation for all the six countries; progress has also been made towards target 17.9 through effective and targeted capacity building to support international plans with a harmonized training manual for indoor residual spraying developed and a centralized Master trainers of trainers conducted for all six countries, To contribute to target 17.17, effective multi-sectoral steering committee have been established to facilitate project implementation. |
| --- | --- |

[complete the fiscal year and select: 1st PIR; 2nd PIR; …. Final PIR.  Add more columns if needed]

| Implementation Status | FY 2017__ | FY 2018__ | FY 2019__ | FY 20__ | FY 20__ |
| --- | --- | --- | --- | --- | --- |
|  | 1st PIR | 2nd PIR | 3rd PIR | … PIR | … PIR |

[complete the fiscal year in the first line; select HS; S; MS; MU; U; HU; unknown; not rated to rate the progress towards the development objective for the fiscal year you are reporting in the second line. Add more columns if needed]

| Development Objective Rating FY | FY 2017__ | FY 2018__ | FY 2019__ | FY 20__ | FY 20__ |
| --- | --- | --- | --- | --- | --- |
|  | MU | S | S |  |  |
| Describe progress made towards achieving the project results as per table 3.1. State key changes since previous reporting period. As of 30 June 2019, the implementation of demonstration projects has been accelerated and countries are at different levels of preparation for year 1 data collection. Priority planned actions have emphasized on preparation for activities and collection including parasitological and entomological data during the 2018/19 malaria transmission in each participating country. COMPONENT 1: Reporting of DDT use to the Secretariat of the Stockholm Convention has been regularized and communication strengthened between MoH and MOE in 5 Countries namely Botswana, Eswatini, Namibia Mozambique and Zimbabwe. All seven Tier 1 countries reported submitting DDT questionnaires in 2018 but only three (Mozambique, Zimbabwe, South Africa) were included in the final Stockholm Convention CoP report. A further 2 countries (Zambia, Namibia) submitted a different questionnaire on stockpiles. Policy and strategic vector control documents have been developed and operationalized. Two countries namely Botswana and Namibia have developed IVM strategies. COMPONENT 2: Protocols developed and approved, Demo sites assessed, and selected Baseline data collected in Five countries except Zimbabwe which has received conditional approval of protocol. Five Tier 1 countries have conducted entomological and epidemiological baseline data and are making requisite preparations for Year 1 demonstration data collection in the 2019/2020 malaria season (all except Zimbabwe, see below). Procurement for Entomological kits and supplies as well as supplies for house screening and larviciding initiated for data collection in 2019/2020 malaria transmission season. COMPONENT 3: Consultant recruited to develop methodology for social impact assessments Collaboration and reporting mechanisms for DDT have been strengthened. Project countries have developed plans for KAP / data collection as part of national demo projects and initial funding has been provided. Activities are planned for Q4 2020. Initial inventory for DDT use and obsolete quantities conducted in Botswana, Eswatini, Namibia and Zimbabwe in 2018 Q3 and in Mozambique in 2018 Q4. The regional coordination and steering committee meeting was held in Harare Zimbabwe, 10 -12 April 2019. Collaboration with requite and key institutions has been strengthened. |  |  |  |  |  |

[complete the fiscal year in the first line; select among H; S; MS; MU; U; HU; unknown; not rated to rate the implementation progress in the fiscal year you are reporting in the second line. Add more columns if needed]

| Implementation Progress Rating | FY 2017__ | FY 2018__ | FY 2019__ | FY 20__ | FY 20__ |
| --- | --- | --- | --- | --- | --- |
|  | . MU | . S | S |  |  |
| Describe annual implementation progress, including any significant [expected and unexpected] environmental or other changes (Results) attributable to project implementation. Also, please discuss any major challenges to meet the objectives or specific project outcomes. [section will be uploaded into the GEF Portal ‘Information on Progress, challenges and outcomes on project implementation activities’ and is the primary report that viewers can see before opening the detailed PIR]. In the last one year, implementation of the AFRO II project has progressed well albeit on a slow rate. The main thrust for planning of activities that integrate robust design approaches for demonstration sites in six project countries has been the collection of quality-scientifically informed data. Over the reporting period, enhanced provision of technical assistance to countries, ensuring regular mutual dialogue, monthly teleconferences with National Project Coordinators (NPC) has provided impetus to project implementation. Furthermore, the recruitment of NPCs has created an enabling environment for operational implementation and facilitated stakeholder mobilization and engagement. COMPONENT 1: Reporting of DDT use to SSC has been regularized and communication strengthened between MoH and MOE in 5 Countries namely Botswana, Eswatini, Namibia Mozambique and Zimbabwe. Policy and strategic vector control documents have been developed and operationalized. Two countries namely Botswana and Namibia have developed IVM strategies, Eswatini and South Africa, Zambia and Zimbabwe have planned to develop/revise national IVM plans in line with the Global Vector Control Response. Needs assessment conducted only in Zimbabwe on institutional arrangements to support the Global Vector Control Response, and they have requested for technical support from WHO/AFRO. COMPONENT 2: Technical support missions provided for all six demonstration countries facilitated by the Regional manager, coordinator and consultants. Insecticide susceptibility testing kits and supplies were procured and delivered to all countries. Procurement of resistance monitoring test kits for year 1 data collection has been initiated for the 7 countries in 2019 Q4. Five countries have organized and trained teams for entomological and epidemiological baseline data collection. Entomological surveillance focussing on vector distribution and insecticide resistance was conducted by NPCs in Mozambique and Zambia and consultants engaged for Botswana, Namibia and Eswatini. The countries are in the process of incorporating the collected data in the national data base. The detailed generic regional demo protocol developed by ICIPE and has been cleared by the WHO AFRO Ethics Review Committee. Five countries have identified demo project coordinators (students) and have embarked on efforts to recruit data collectors. Parasitological and entomological base-line data has been collected in 5 countries base on country-tailored protocols developed by country teams, with roles and responsibilities allocated fully established and approved by the country ethical review, except for Zimbabwe that received conditional approval. All countries are using insecticide resistance data to develop IRM plans to inform policies on vector control. The maps will be produced based on data that is collected over time in all the six countries. Of the six project countries implementing the demonstrations only Zimbabwe is yet to start demonstration activities but has received conditional approval of the protocol. COMPONENT 3: Five countries namely Botswana, Eswatini, Namibia, Mozambique and Zimbabwe have conducted initial assessments on social impact of DDT, the inventory on availability and distribution of DDT and assessed DDT use in 2018 Q3. Further to the assessment of compliance to DDT reporting, initial efforts towards assessment of social impact of the insecticide, as well as an inventory regarding use and quantities of obsolete DDT have been embarked upon in five countries implementing the demonstrations except Zambia. Another consultant recruited on regional report (including 7 tier 1 countries) on data on the use of DDT and obsolete DDT Planned for Q3 and Q4, 2019. While South Africa is yet to conduct the inception stakeholder’s meetings, the country has now developed a tailored proposal based on component 3 of the project. The Executing agency, WHO/AFRO and the sub-contracted institute, ICIPE, have provided technical assistance to all participating Countries (except South Africa). WHO has supported development of IVM strategy in Botswana and Namibia, and overall project implementation in all six countries. ICIPE has supported protocol development, and site selection in Botswana, Eswatini, Mozambique, Namibia and Zambia. UNEP has collaborated with WHO in recruitment of a consultant and conducting of social impact assessments and quantification and reporting obsolete quantities, stocks and distribution of DDT for Botswana, Eswatini, Namibia, Mozambique and Zimbabwe. The assessments for Zambia is scheduled for Q1 2020. M&E AND PROJECT MANAGEMENT Quarterly technical project implementation reports and financial reports including co-financing have been submitted in a timely manner by all active project countries. All the six countries; Botswana, Eswatini, Mozambique, Zambia and Zimbabwe have recruited NPCs. Students have also been engaged to coordinate demonstration projects in Botswana, Eswatini, Mozambique, Namibia and Zambia. Procurements of commodities and equipment has been completed in Namibia and is underway in Botswana, Eswatini and Zambia. Procurement efforts have been embarked upon in Mozambique and Zimbabwe but the actual processes are yet to be initiated. Central level procurements at WHO/AFRO had been delayed but have now being accelerated. Different modalities have been adopted by countries to provide transport for the project. Some countries intend to engage drivers (Botswana), others opt to use government vehicles but being fuelled and serviced by project funds (Eswatini and Zambia), and others still have preferred to hire the vehicles (Namibia). Though the modalities for initiating the South African component of the project are yet to be established and executed, implementation of the project is on target to collect detailed baseline data for the 2018/19 malaria season and to confirm and/or update baseline data in the project log frame. |  |  |  |  |  |

[complete the fiscal year in the first line; select H; S; M; L; to rate the fiscal year you are reporting. Add more columns if needed]

| Risk Rating | FY 2017__ | FY 2018__ | FY 2019__ | FY 20__ | FY 20__ |
| --- | --- | --- | --- | --- | --- |
|  | M | L | L |  |  |
| Describe key changes since previous reporting period. Projects with ESERN rating high medium/ high risk must refer to the safeguards implementation plan and its implementation. [section will be uploaded into the GEF Portal and in UN Environment Open Platform] The risks highlighted in the previous years’ PIR have been addressed in the last year. Consensus was reached that no country will procure vehicles but should include transport in their annual action plan, identify dates of field visits and estimate costs either for fuel, drivers, maintenance or vehicle hire, according to whatever option can be available in each country. Procurements have been and confirm in the annual procurement plan and expedited and commodities and equipment will be delivered in September. The project in South Africa has been redesigned and the DEA have embarked on a project to assess presence of DDT in some environmental media, fresh produce, human and animal milk, in areas where DDT is sprayed, to support advocacy for the replacement of DDT with alternative IVM-based approaches to malaria control. |  |  |  |  |  |

| Stakeholder engagement | Describe progress, challenges and outcomes on stakeholder engagement (based on the description of the Stakeholder engagement plan included at CEO endorsement) [section will be uploaded into the GEF Portal] The Executing Agency, WHO-AFRO has delegated the WHO Offices in each project country for the day to day supervision and support for implementation of project activities, provision of policy and technical guidance through National Project Coordinators as well as collaboration with various relevant sectors. National Malaria Control Programs (NMCPs) lead the execution of the project in each country in collaboration with the health-, agriculture-, and environment sectors as the main sectors involved also urban planning, rural development, local governments etc. Execution of an Integrated Vector Management project like this one requires a multi-sectoral involvement and commitment. A Regional Project Steering Committee (RPSC) composed of experts in the various fields relevant to the project has been established to advise the WHO-AFRO on all technical issues. National Project Steering Committees (NPSCs) composed of sectoral representatives have been established and play advisory and supervisory role. The National Project Coordinators and the PSCs work closely together with existing national structures like the Global Fund CCM (Country Coordination Mechanism) to allow full transparency, efficiency, and sustainability even after the project life time. The Executing Agency has subcontracted ICIPE in Kenya, a specialised partner for supporting the development and execution of specific demonstration projects in representative areas in each country. ICIPE works with the national malaria control programs in the development of the demonstration projects based on the latest scientific principles in the field of Integrated Vector Management. The entire execution of these demonstration projects is within the responsibilities of the national malaria control programs. They regularly report on progress and expenditure to the Executing Agency. Local NGOs have been subcontracted to cater for the execution of the community involvement related activities and awareness raising in each project countries. |
| --- | --- |

| Gender mainstreaming | Describe progress, challenges and outcomes related to the gender-responsive measures documented at CEO Endorsement/ Approval in the gender action plan or equivalent. Older projects that were designed before gender mainstreaming should proactively report any possible gender benefits, as appropriate. [section will be uploaded into the GEF Portal] Gender dimensions have been reflected at both operational - and policy-level interventions for sound chemical management. Vector control efforts in all project countries implementing indoor residual spraying (IRS) have involved women at all levels of the intervention e.g. importation, transportation, storage, usage and disposal. Implementation of demonstration projects has involved women during the entomological and epidemiological surveys to collect baseline data. The actual total numbers of women involved is yet to be reported by countries. The social impact assessments for DDT have involved gender related aspects in five countries. |
| --- | --- |

| Knowledge activities and products | Provide a narrative of knowledge activities/ products (when applicable), as outlined in knowledge management approved at CEO Endorsement/ Approval [section will be uploaded into the GEF Portal] In the last reporting period, the knowledge management activities were based on exchanges and sharing of experience between country teams developing the research protocols for the demonstration pilots. This was done during regular reporting via the Executing Agency and at the Regional Steering Committee meeting. Countries used their own systems for recording the baseline data collected (entomological surveys and insecticide resistance monitoring), as this will aid long term sustainability and official use of these data. However, the project promotes consistency and comparability between data through a single technical support contract with ICIPE in Kenya, which ensures technical experience sharing between the countries. A communication strategy has been developed to ensure documentation of the interventions being rolled out (e.g. house screening and winter larviciding) and to share these pilots with the public and decision makers. |
| --- | --- |

| Stories to be shared | Optional for mature projects: Provide a brief summary of any especially interesting and impactful project results that are worth sharing with a larger audience, and/or investing communications time in, if any. [section to be shared with communication division/ GEF communication] The social impact assessments for DDT have involved gender related aspects in five countries. Production of stories regarding national social impact assessment that highlight impacts on vulnerable groups from use of DDT is yet to be conducted. |
| --- | --- |

- RATING PROJECT PERFORMANCE AND RISK

Based on inputs by the Project Manager, the UNEP Task Manager will make an overall assessment and provide ratings of:

- Progress towards achieving the project Results(s)- see section 3.1

- Implementation progress – see section 3.2

Section 3.3 on Risk should be first completed by the Project Manager. The UNEP Task Manager will subsequently enter his/her own ratings in the appropriate column.

  - 3.1	Rating of progress towards achieving the project Results(s) [copy and paste the CEO Endorsement (or latest formal Revision) approved Results Framework, adding/deleting outcome rows, as appropriate]

| Project objective and Outcomes | Indicator | Baseline level | Mid-Term Target or Milestones | End of Project Target | Observations/ justification on rating | Progress rating |
| --- | --- | --- | --- | --- | --- | --- |
| Objective To strengthen national capabilities for implementation and scaling up of evidence-based, innovative, diversified and environmentally sound disease vector control interventions alternative to DDT (with special emphasis on malaria) with multi-stakeholder participation within context of IVM | 1. Reduced use of DDT for malaria control in six (6) countries where innovative interventions are demonstrated (in Botswana, Eswatini, Mozambique, Namibia; Zambia, Zimbabwe) | About 305 tons of DDT used annually across all project countries. | Year 3: 30 tons of DDT reduced in DDT demo countries Year 4: 50 tons of DDT reduced in demo countries Year 5: 300 tons of DDT reduced in all countries | 300 tons of DDT reduced in all countries | Initial efforts to establish the inventory for DDT use and obsolete quantities conducted in Botswana, Eswatini, Namibia and Zimbabwe in 2018 Q3 and in Mozambique in 2018 Q4. Zambia will reintroduce DDT in IRS | MU |
|  | 2. Innovative, environmentally sound and effective alternative IVM approaches (house screening, larviciding and evidence based intensive community education and communication IEC) demonstrated in at least 12 sites in 6 countries | No large-scale demonstrations implemented at program level (in NMCPs) | 1st Round demo intervention implemented and assessed | 6 demonstration projects completed | Protocols developed and approved; Demo sites assessed and selected Baseline data collected in Five countries. Only conditional approval of protocol in Zimbabwe. | S |
|  | 3. Evidence on effectiveness of large scale house screening, larviciding and evidence based systematic community education and communication-IEC for malaria vector control documented in countries | No well documented evidence, experience and lesson on large scale house screening, larviciding and evidence based systematic IEC interventions | As above | As above |  | N/A |
|  | 4. IVM strategy, approaches streamlined into relevant non-health sector(s) in 6 countries | No countries have streamlined IVM into sector policies and strategies, |  | Outcomes of demo sites communicated with relevant sectors and streamlined into malaria control strategies | Activity rescheduled for 4th Year (2019-2020) in work plans. Two countries have developed national IVM policies. | S |
|  | 5. Technical capacity for evidence based multi-sectoral alliance strengthened in 7 countries | No country has technical capacity to established evidence based multi-sectoral alliance | At least half of the total number of Project countries with established technical capacity for evidence based multi-sectoral alliance | All countries with requisite Technical capacity for evidence based multi-sectoral alliance | Activity scheduled for 4th Year (2019-2020) in work plans. Technical capacity built by ICIPE in designing and rolling out IVM approaches | MU |
|  | 6.Intersectoral collaboration for better compliance with the Stockholm Convention is strengthened in all project countries | Only 1 country reports regularly on amounts of DDT use to the Stockholm Convention secretariat | At least half of the total number of Project countries regularly report on status use of DDT SC secretariat | All 7 countries regularly report on the status use of DDT to the Stockholm Convention secretariat | All seven countries reported submitting DDT questionnaires in 2018 but only three (Mozambique, Zimbabwe, South Africa) were included in the final SSC Report. A further 2 countries (Zambia, Namibia) submitted a global survey questionnaire. | S |
| Outcome 1: Countries develop and implement integrated cross sectoral policies, strategies and plans and have managerial capacity to fully comply with terms of the SC on the use of DDT for diseases vector control through implementation of IVM | 1.Number of countries with IVM streamlined into sector policies, strategies and plans; | No countries have streamlined IVM into sector policies and strategies, | Year 2: relevant staff of stakeholder institutions trained in IVM At least 1 sector integrated IVM activities in 7 countries | All countries streamlined IVM into sector policies and strategies | Botswana and Namibia have developed/updated IVM strategic plans | MS |
|  | 2.Number of countries in compliant with Stockholm Convention in the use of DDT; | Only 1 country is in compliance with the Stockholm Convention reporting requirements on DDT. | Stakeholder meetings on DDT between Ministries of health and environment done for all 14 project countries | 14 countries compliant with the Stockholm Convention reporting requirements on DDT. | Stakeholder meetings held for 6 countries – not needed for tier 2 countries. Three countries (Mozambique, Zimbabwe, South Africa) made the required DDT report in 2018. | MS |
|  | 3.Number of countries with improved capacity to manage the implementation of IVM in an integrated manner across sectors compared to initial capacity assessment completed at inception phase; | No countries with. Integrated implementation of IVM. | 7 Countries have completed developing/revising national IVM documents | 14 countries with improved capacity to implement IVM | Five countries have developed detailed protocols for rolling out an IVM trial and obtained national approval from the required ethics committee. First year’s data collected | S |
| Outcome 2: Countries adopt the implementation of effective, sustainable and innovative interventions in demonstration project areas | Number of countries that adopt the IVM strategy as an alternative to DDT in line with results from IVM demonstration projects | All (tier 1) project countries currently use DDT for malaria vector control, and have not demonstrated at large level (national) IVM interventions | Year 3: DDT use reduced by 30 tons in demos Year 4: 6 countries designed, implemented and evaluated demo project One regional sensitization workshop for high level decision makers | National consensus workshop to revise or incorporate IVM approaches in malaria or other vector-borne disease strategic document 6 countries revised and streamlined IVM strategic documents based on results of demo project | Contract with ICIPE since 2017. Five national demo protocols approved. Baseline data collection delayed until 2019 season | MS |
| Outcome 3: Countries and regional institutions are using guidelines on IVM and social impact assessments to guide and influence policies on DDT use | Number of regional technical guidelines/ manuals/ operational framework on IVM produced/revised and published | No regional or country-specific technical guidelines / manuals/ operational framework on IVM produced/revised based outcomes of demonstrable available evidence | 7 countries have completed social impact assessment survey to guide and influence policies on IVM/use of DDT | Relevant regional IVM guidelines/ manual revised and disseminated to both tier 1 and 2 countries | Planned for 2020 | N/A |

Overall rating of project progress towards meeting project Result(s) (To be provided by UNEP GEF Task Manager.)

| FY2018 rating [previous] | FY2019 rating [current] | Justification of the current FY rating and explanation of reasons for change (positive or negative) since previous reporting periods. |
| --- | --- | --- |
| S | S | Summarize the annual progress towards meeting project results. Describe any significant [expected and unexpected] environmental or other changes (Results) negative and or positive attributable to project implementation. State any key changes since previous reporting period. Also, please discuss any major challenges to meet the objectives or specific project outcomes. Whenever possible, please provide evidence of attribution between the UNEP/GEF project’s intervention and observed changes towards the achievement of direct outcomes. In cases where several actors are collaborating to achieve common outcomes, evidence of the nature and magnitude of the UNEP/GEF project’s ‘substantive contribution’ and/or ‘credible association’ should be described. This information provides the rationale for the Development Objective Rating in Section 2. Progress is steadily being made toward project results. Under Component 1, progress on reporting to the Stockholm Convention was made with three of the seven countries submitting their reports in 2018 and the establishment of national coordinating and information exchange mechanisms between SC Focal Points and malaria control programmes. Five of the countries submitted stockpiles information to a separate global survey initiative which was reported to the COP. Two countries (Botswana and Namibia) have developed national IVM strategies with project support, these national policies / strategic documents promote alternative approaches to relying only on spraying with insecticides and especially DDT. Progress under Component 2 is also good, with five demonstration pilot projects well established and collecting baseline information, with procurement and other logistics in place to roll out the alternative interventions in the coming malaria season. Progress under Component 3 is slow, with countries yet to produce their detailed plans and budgets for conducting the inventory, social assessment, and reporting work packages. A regional consultant has however visited most countries to develop the framework for this work and the methodology was presented and discussed at the Regional Steering Committee meeting in April. |

Risks to the delivery of results

The second column should be completed by the Project Manager and the third column should summarize the recommendations that the Project Manager and Task Manager have agreed upon to address the problem/risk.  Projects should complete only the relevant sections and are free to add/delete problems/risks.  This section should inform the risk rating in section 3.3.

| Problems/risks identified | Description of the problem/risk | Agreed recommended actions |
| --- | --- | --- |
| on achieving targets | Lack of clear understanding of the formats and data required for SC reporting | Offer a webinar on reporting requirements to SC Focal Points and malaria programmes (UNEP, together with BRS) |
|  | Delays in procurement of entomological supplies, commodities and equipment and deliver to 7 countries | WHO/AFRO to expedite procurement and delivery of supplies, commodities and equipment to all project countries |
|  | Lack of transport at country level and difficulties for access to partner vehicles | Countries to use available options for transport such as hiring, fuel etc depending on the country context |
|  | Delayed participation of South Africa in the project | Redesign and confirm project activities and execution in by the environment sector in South Africa |
| on safeguards |  |  |
| on stakeholder engagement | Delay in country inception processes for Training and technical support provided to countries to develop integrated national legal frameworks and IVM plans with managerial capacity for IVM to a harmonized standard | Focus on legal, IVM and Component 3 activities on inventories and social assessments during 2020 annual work planning |
| on delivering GEF Core Indicators |  |  |
| on sustainability of results | SADC ministerial declaration in favour of continued DDT use | Ensure high quality data collection including from the 2018/9 season. |
| on delivering of PoW EA | Delayed country inception processes for Production programmatic communications / awareness materials and strategies | Implementation of activities have been prioritized |
|  | Weak country capacity/ Workflow: delays in achieving work plan, and financial reporting | Increased personnel and technical support/ Training of staff |
| on gender actions | Delay in aggregating data based on participation in project activities by male and female ratio | Segregate all the participants of training and field activities by male and female. |
| others |  |  |

3.2	Rating of progress implementation towards delivery of outputs

| Outputs | Expected delivery date | Implement-ation status as of 30 June 2018 | Implement-ation status as of 30 June 2019) | Progress rating justification (as much as possible, describe in terms of immediate gains to target groups, e.g. access to project deliverables, participation in receiving services; gains in knowledge, etc) | Progress rating |
| --- | --- | --- | --- | --- | --- |
| Output 1.1: Technical support to countries to notify the Stockholm Convention on the use of DDT by the their | 2018, Q3 | 100% | 100% | Complete since 2018. Zimbabwe notified DDT use via the SC DDT Register | HS |
| Output 1.2: Countries regularly report to the Stockholm Convention Secretariat on the use of DDT for disease control as stipulated in the Stockholm Convention, Annex B, Part II, para 4 Activities include national workshops on intersectoral alliance, and agreeing a mechanism for reporting included in an MOU between the two ministries | 2022 Q2 | 0 | 50% | 5 Countries namely Botswana, Eswatini, Namibia Mozambique and Zimbabwe have held meetings between MoH and MoE to regularize reporting for DDT between the two ministries. However, no formal mechanism or MOU was agreed, and some confusion remained about the correct form to use to report. The next reporting date is 2022 and further support will be needed until then. | MS |
| Output 1.3: Training and technical support provided to countries to develop integrated national legal frameworks and IVM plans with managerial capacity for IVM to a harmonized standard Activities include: Technical support missions to develop national legal frameworks; ; Organize national workshops on development, implementation, monitoring and evaluation of national IVM plans; Organize one regional IVM training for NMCP managers; Develop/ revise national IVM documents, in 7 countries | 2019, Q3 | 42.9% | 85.7% | 2 countries namely Botswana and Namibia have developed IVM strategies, Eswatini and South Africa, Zambia and Zimbabwe have planned to develop/revise national IVM plans in line with the Global Vector Control Response. Have requested for technical support from WHO/AFRO | S |
| Output 1.4: Training, technical support and provision of equipment to countries to support implementation of evidence based national policies and plans for IVM to a harmonized standard Activities include: Conduct needs assessment in 7 countries; Carry out technical support mission in 7 countries; Procure basic entomological kits and supplies and deliver to 7 countries; Organize national training workshops for national and district staff in basic entomological techniques in 7 countries (combine with activity 1.3.3) | 2019; Q4 | 70% | 90% | Technical support missions provided for 6 countries. The Regional manager, coordinator and consultants facilitated these visits. Kits and supplies procured for all and delivered to all countries. 5 counties have organized and trained teams for entomological baseline data collection. | S |
| Output 2.1: Mapping of vector distribution and associated insecticide resistance (this is planned for 6 countries. Activities include: Conduct entomological survey focusing on vector distribution in 7 countries; Conduct insecticide resistance monitoring in 7 countries; Incorporate collected entomological data into updated national data base in 7 countries; Produce report on vector distribution and update vector distribution maps; Update national insecticide resistance data and produce maps in 7 countries( once every year); Compile resistance data And produce report.; Conduct consensus workshop and finalize report on insecticide resistance | 2020, Q1 | 50% | 65% | NPCs conducted entomological surveys focusing vector distribution in Mozambique and Zambia and consultants engaged for Botswana, Eswatini and Namibia. 5 Countries have collected data and are in the process of incorporating in the national data base. Production of report and maps is planned for 2020 Q3 after baseline data collection. Updating of insecticide resistance data, compilation and finalization of report is planned for 2020 Q3 | MS |
| Output 2.2: Three IVM approaches developed and demonstrated in six countries Activities include: Develop study (demo) protocol in 6 countries; Recruit and train required personnel in 6 countries; Conduct baseline data collection in 6 countries; : Implement 1st round demo interventions in 6 countries; Assess impact of 1st round demo interventions and document outcomes in 6 countries; : Implement 2nd round demo interventions in 6 countries; Assess impact of 2nd round demo interventions and document outcomes in 6 countries; Assess and document demo interventions outcomes in 6 countries; Streamline demo interventions proved to be effective strategies of the NMCP at least in 6 countries; | 2020, Q2 | 50% | 60% | Detailed generic regional demo protocol developed by ICIPE and has been cleared by the WHO AFRO Ethics Review Committee. 5 countries have identified demo project coordinators (Students) and have embarked on efforts to recruit data collectors. Base-line data has been collected in 5 countries base on Country-tailored protocols developed by country teams, with roles and responsibilities allocated fully established and approved by the ethical review committee. Zimbabwe received conditional approval. 1st round demo will be undertaken in 2019 Q4. Second round will be in 2020 Q4. MDAST activities are not relevant as countries have their own data systems. A recommendation will be made for the RSC to cancel these activities. | S |
| Output 3.1: Manuals and related technical guidelines on IVM updated and published Activities include: Organize regional consensus workshop on outcomes of demos; Update and publish regional technical guidelines and manuals based on demos proved to be effective; Organize national consensus workshops on outcomes of demos; Update and publish national technical guidelines and manuals based on demos proved to be effective at least in 5 countries. | 2021, Q2 | 0 |  | Planned for Year 3-5. Included in the regional demo protocol | N/A |
| Output 3.2: Production programmatic communications / awareness materials and strategies Activities include: Conduct KAP surveys on IVM in vulnerable communities at least in 7 countries; Publish IVM KAP survey results at least in 7 countries; Produce and publish locally appropriate IEC-BCC material and approaches based on outcomes of the IVM KAP surveys; : Implement the evidence based IEC-BCC materials and approaches in vulnerable communities in at least 7 countries; Assess impact of implementation of evidence based IEC-BCC materials and approaches in vulnerable communities in at least 7 countries; : Publish IVM KAP survey results at least in 7 countries. | 2019, Q2 | 0 |  | Delayed country inception processes have led to delays in planning for this activity. | MU |
| Output 3.3: Social Impact of the use of DDT on vulnerable groups assessed and documented Activities include: Conduct assessment on social impacts of DDT in 7 countries; Present the results of social impacts assessments to SSC; Present and publish impact assessment outcomes to stakeholder sectors (MoH, MoE. MoA) in 7 countries in consensus building workshops. | 2020, Q2 | 60% |  | Consultants visits to develop the methodology have been conducted assessments on social impact in Q3 2018 in 5 Countries namely Botswana, Eswatini, Namibia, Mozambique and Zimbabwe. National plans are drafted, will be approved by PSC for fund transfer for the field work in 2019/ 2020. Results are planned to be presented in 2020 Q2 | MU |
| Output 3.4: Production of reports to the Stockholm Convention Sec (SCS) on DDT usage including amount and local distribution of obsolete DDT in project countries Activities include: Conduct inventory on the availability and distribution of obsolete DDT in 7 countries; Assess DDT use in 7 countries | 2018, Q2 | 66.7% | 83.3% | Planned for Year 2 and 5 5 Countries namely Botswana, Eswatini, Namibia, Mozambique and Zimbabwe have conducted the inventory and assessed DDT use in Q3 2018. | MS |

Overall project implementation progress  (To be completed by UNEP GEF Task Manager.):

| FY2018 rating [previous] | FY2019 rating [current] | Justification of the current rating and explanation of reasons for change (positive or negative) since previous reporting periods. |
| --- | --- | --- |
| S | MS | The rating of progress in the delivery of outputs should be assessed in terms of both quantity and quality. The assessment must consider ownership by, and usefulness to, intended beneficiaries and the timeliness of their delivery. Use the comments column to explain the reasons behind the success or shortcomings of the project in delivering its programmed outputs and meeting expected quality standards. Delivery of outputs under Component 1 is highly satisfactory, with the first output delivered in 2018. Component 2 is also progressing well with the demos being finally approved (albeit with some delay compared to the original plan) and logistics and teams set for field works in Q3 and Q4. However, Component 3 outputs are delayed compared to the original workplan and have not been delivered in a concrete way at the country level yet. |

Risks in implementation

This section should be completed by the Project Manager and summarize implementation risks (e.g. procurement delays, reputational risks etc).

The first column should be completed by the Project Manager and the second column should summarize the recommendations that the Project Manager and Task Manager have agreed upon to address the problem/risk.  This section should inform the risk rating in section 3.3.

| Problems/risks identified | Agreed recommended actions | By whom | When |
| --- | --- | --- | --- |
| Procurement delays for equipment for entomological surveys and alternative IVM | Close oversight by project manager and Task Manager | WHO, UNEP | To be completed by Q3 2019 |
| Delay in country planning and delivery of Component 3 activities | Oversight by project manager and additional support from BRS convention bodies (DDT expert group) | WHO, UNEP | 2019 Q4 |

3.3. Risk Rating [Insert the Medium and High Risks and mitigation measures identified at CEO endorsement (e.g. Section A.5) and any relevant risk from safeguards screening and/or management plans.]  Expand the table to include medium and high risks observed during implementation, e.g. problems identified in sections 3.1. and 3.2.

| Risk | Mitigation at CEO approval | Mitigation at implementation | Rank |
| --- | --- | --- | --- |
| Increased malaria transmission posed by reduced reliance on DDT or its withdrawal for IRS applications | This risk can be averted through the establishment of an effective disease surveillance system coupled with prompt diagnosis and treatment. |  | CEO: M |
|  |  |  | TM: |
|  |  |  | PM: |
| Lack of new chemical control entering the market or under development. | Strength countries capacity for insecticides resistance management to sustain effectiveness of available insecticides in the context of IVM |  | CEO: M |
|  |  |  | TM: |
|  |  |  | PM: |
| Potential for leakage of obsolete DDT stocks and new stocks imported for IRS into the agriculture sector. | Intensify community education and information dissemination of hazardous impacts of the miss use of DDR and any other insecticide -Strengthen inter-sectoral collaboration and information sharing |  | CEO: M |
|  |  |  | TM: |
|  |  |  | PM: |
| Overall Risk Rating Project Manager |  |  |  |
| Overall Risk Rating Task Manager |  |  |  |

| FY2018 rating [previous] | FY2019 rating [current] | Justification of the current risk rating and explanation of reasons for change (positive or negative) since previous reporting periods. |
| --- | --- | --- |
|  |  | Elaborate on indicated risks, including climate change, potential social and environmental risks that might prevent the project to deliver the expected results and, whenever possible, the proposed measures to address these risks. Refer also to the assumptions and drivers e.g. when the assumptions are not holding and/ or the drivers are not in place. Please refer to the GEF risk rating table below |

High Risk (H): There is a probability of greater than 75% that assumptions may fail to hold or materialize, and/or the project may face high risks. 
Substantial Risk (S): There is a probability of between 51% and 75% that assumptions may fail to hold and/or the project may face substantial risks. 
Modest Risk (M): There is a probability of between 26% and 50% that assumptions may fail to hold or materialize, and/or the project may face only modest risks. 
Low Risk (L): There is a probability of up to 25% that assumptions may fail to hold or materialize, and/or the project may face only modest risks.

Optional Annexes and/or Links:

- Project Steering Committee Minutes of the year reported

- Half yearly Report

- Quarterly Reports

- Risk Factor Table form previous template (recommended for substantial and high-risk projects)

Risks Factor Table

There are two tables to assess and address risk: the first “risk factor table” to describe and rate risk factors; the second “top risk mitigation plan” should indicate what measures/action will be taken with respect to risks rated Substantial or High and who is responsible to for it.

High Risk (H): There is a probability of greater than 75% that assumptions may fail to hold or materialize, and/or the project may face high risks. 
Substantial Risk (S): There is a probability of between 51% and 75% that assumptions may fail to hold and/or the project may face substantial risks. 
Modest Risk (M): There is a probability of between 26% and 50% that assumptions may fail to hold or materialize, and/or the project may face only modest risks. 
Low Risk (L): There is a probability of up to 25% that assumptions may fail to hold or materialize, and/or the project may face only modest risks.

RISK FACTOR TABLE

Project Managers will use this table to summarize risks identified in the Project Document and reflect also any new risks identified in the course of project implementation. The Notes column should be used to provide additional details concerning manifestation of the risk in your specific project, as relevant. The “Notes” column has one section for the Project Manager (PM) and one for the UNEP Task Manager (TM). If the generic risk factors and indicators in the table are not relevant to the project rows should be added. The UNEP Task Manager should provide ratings in the right hand column reflecting his/her own assessment of project risks.

|  |  |  |  | Project Manager Rating |  |  |  |  |  | Notes | Task Manager Rating |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Risk Factor | Indicator of Low Risk | Indicator of Medium Risk | Indicator of High Risk | Low | Medium | Substantial | High | Not Applicable | To be determined |  | Low | Medium | Substantial | High | Not Applicable | To be determined |
| INTERNAL RISK |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Project management |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Management structure [Roles and responsibilities] | Stable with roles and responsibilities clearly defined and understood | Individuals understand their own role but are unsure of responsibilities of others | Unclear responsibilities or overlapping functions which lead to management problems | X |  |  |  |  |  | PM: The clarity of responsibilities of Ministries of Environment vary from one country to the other. RC recommended improvement. |  | X |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: Responsibilities under Component 3 are not clearly defined and understood. Environment ministries roles are not clear or included in WHO Country Office arrangements. |  |  |  |  |  |  |
| Governance structure [oversight] | Steering Committee and/or other project bodies meet periodically and provide effective direction/inputs | Body(ies) meets periodically but guidance/input provided to project is inadequate. TOR unclear | Members lack commitment Committee/body does not fulfil its TOR | X |  |  |  |  |  | PM: Country and regional project coordination and steering committee meetings occur annually. | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: Timely meetings of RSC with clear TOR |  |  |  |  |  |  |
| Internal communications | Fluid and cordial | Communication process deficient although relationships between team members are good | Lack of adequate communication between team members leading to deterioration of relationships and resentment | X |  |  |  |  |  | PM: Monthly calls between PM with National Project Coordinators in the project countries. | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: Regular calls between IA and EA. SC recommendation for more regular communications between EA and countries. |  |  |  |  |  |  |
| Work flow Budget | Project progressing according to work plan | Some changes in project work plan but without major effect on overall timetable | Major delays or changes in work plan or method of implementation |  | X |  |  |  |  | PM: Adjustments in timelines for baseline data collection and beginning of the demonstration activities. |  |  | X |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: Component 3 delivery is delayed at country level. |  |  |  |  |  |  |
| Co-financing | Co-financing is secured and payments are received on time | Is secured but payments are slow and bureaucratic | A substantial part of pledged co-financing may not materialize |  | X |  |  |  |  | PM: The bureaucracy in obtaining information on co-financing is lengthy and slow. |  |  | X |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: Cofinance of 6.6m USD was reported only by Tier 1 countries. A very high amount was committed by Tier 2 countries who are not actively engaged in the project to date. |  |  |  |  |  |  |
| Budget | Activities are progressing within planned budget | Minor budget reallocation needed | Reallocation between budget lines exceeding 30% of original budget |  | X |  |  |  |  | PM: Minor adjustments and reallocation of funds will be required as prompted by the delay in component 2 and 3 project activities. |  | X |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: Due to a 1-year delay in initiating demo projects, some reallocation of demo funds may be required in the coming year. |  |  |  |  |  |  |
| Financial management | Funds are correctly managed and transparently accounted for | Financial reporting slow or deficient | Serious financial reporting problems or indication of mismanagement of funds | X |  |  |  |  |  | PM: Quarterly financial reports submitted on time. | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: Timely financial reporting. |  |  |  |  |  |  |
| Reporting | Substantive reports are presented in a timely manner and are complete and accurate with a good analysis of project progress and implementation issues | Reports are complete and accurate but often delayed or lack critical analysis of progress and implementation issues | Serious concerns about quality and timeliness of project reporting | X |  |  |  |  |  | PM: Reporting is done regularly and in a timely manner. | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: Regular reporting in place, including monthly calls with the IA. |  |  |  |  |  |  |
| Stakeholder engagement | Stakeholder analysis done and positive feedback from critical stakeholders and partners | Consultation and participation process seems strong but misses some groups or relevant partners | Symptoms of conflict with critical stakeholders or evidence of apathy and lack of interest from partners or other stakeholders |  | X |  |  |  |  | PM: Partner engagement including environment sector has been slow and varies from one country to the other. |  | X |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: Slow process in engaging environment sector. See comment above on Management Structure |  |  |  |  |  |  |
| External communications | Evidence that stakeholders, practitioners and/or the general public understand project and are regularly updated on progress | Communications efforts are taking place but not yet evidence that message is successfully transmitted | Project existence is not known beyond implementation partners or misunderstandings concerning objectives and activities evident |  | X |  |  |  |  | PM: External communications have only been achieved through country steering committee meetings. This will be improved as results emerge from ongoing research. |  | X |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: External communications slow as field work was being set up with limited results to share with external partners. |  |  |  |  |  |  |
| Short term/long term balance | Project is addressing short term needs and achieving results with a long-term perspective, particularly sustainability and replicability | Project is interested in the short term with little understanding of or interest in the long term | Longer term issues are deliberately ignored or neglected | X |  |  |  |  |  | PM: Implementation of the IVM approach in the context of the Global Response for Vector Control. | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: Good connection of IVM with wider WHO and continent approaches, especially Global Vector Control Approach. |  |  |  |  |  |  |
| Science and technological issues | Project based on sound science and well-established technologies | Project testing approaches, methods or technologies but based on sound analysis of options and risks | Many scientific and /or technological uncertainties | X |  |  |  |  |  | PM: Technical support has been provided by ICIPE and Ethical Clearance of research protocols has been obtained in all project countries. | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: Technical support by ICIPE and Ethical Clearance of protocols in all countries. |  |  |  |  |  |  |

|  |  |  |  | Project Manager Rating |  |  |  |  |  | Notes | Task Manager Rating |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Risk Factor | Indicator of Low Risk | Indicator of Medium Risk | Indicator of High Risk | Low | Medium | Substantial | High | Not Applicable | To be determined |  | Low | Medium | Substantial | High | Not Applicable | To be determined |
| EXTERNAL RISK |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Project context |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Political stability | Political context is stable and safe | Political context is unstable but predictable and not a threat to project implementation | Very disruptive and volatile | X |  |  |  |  |  | PM: DDT use within the framework of IVM has been politically advocated in the region. |  | X |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: DDT use issue is highly politicized in the region, with 2016 SADC Ministerial declaration calling for DDT use options |  |  |  |  |  |  |
| Environmental conditions | Project area is not affected by severe weather events or major environmental stress factors | Project area is subject to more or less predictable disasters or changes | Project area has very harsh environmental conditions |  | X |  |  |  |  | PM: Climate change and extreme weather events might expand the distribution range of malaria vectors that are susceptible to DDT and potentially increase the need for its use. |  | X |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: climate change may be expanding the range of malaria vectors, potentially increasing the need for DDT. Extreme weather events in 2019 affected delivery of project activities. |  |  |  |  |  |  |
| Social, cultural and economic factors | There are no evident social, cultural and/or economic issues that may affect project performance and results | Social or economic issues or changes pose challenges to project implementation but mitigation strategies have been developed | Project is highly sensitive to economic fluctuations, to social issues or cultural barriers | X |  |  |  |  |  | PM: Social, cultural and economic factors with potential to affect the project are presently non-existent. | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: |  |  |  |  |  |  |
| Capacity issues | Sound technical and managerial capacity of institutions and other project partners | Weaknesses exist but have been identified and actions is taken to build the necessary capacity | Capacity is very low at all levels and partners require constant support and technical assistance |  | X |  |  |  |  | PM: Technical support has been provided to build requisite capacity in countries with identified weaknesses. |  | X |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: |  |  |  |  |  |  |

If there is a significant (over 50% of risk factors) discrepancy between Project Manager and Task Manager rating, an explanation by the Task Manager should be provided below

TOP RISK MITIGATION PLAN

Rank – importance of risk Risk Statement – potential problem (condition and consequence) Action to take – action planned/taken to handle the risk Who – person(s) responsible for the action Date – date by which action needs to be or was completed

| Rank | Risk Statement |  | Action to Take | Who | Date |
| --- | --- | --- | --- | --- | --- |
|  | Condition | Consequence |  |  |  |
| Substantial | Component 3 of the project is very slow to be delivered by National Coordinators, NMCP and WHO country offices | The outcomes will not be achieved. Cross-sectoral collaboration opportunities missed | Proactively seek detailed workplans, budget, and agreed methodologies from country teams, including defining specific roles for environment sector partners | Project Manager | By Q4 2019 |
|  |  |  | Additional linkages made to BRS Secretariat and the DDT Expert Group, including webinar on reporting | UNEP | Q4 2019 - Q2 2020 |
| Substantial | Lack of engagement of Tier 2 countries | Non-achievement of co-finance targets | Tier 2 countries will be engaged in regional activities planned for 2019/ 2020, including IVM training and regional support to countries developing IVM strategies. | WHO | From Q3 2019 into 2020 |
| Substantial | South Africa does not participate in the project | Countries do not perceive regional leadership in line with the project and lose commitment | Support from IA for direct contracting of South Africa DEA and close oversight by EA and IA. | UN Environment | By Oct 2019 |

Project overall risk rating (Low, Medium, Substantial or High) (Please include PIR risk ratings for all prior periods, add columns as necessary):

| FY2017 rating | FY2018 rating | FY2019 rating | Comments/narrative justifying the current FY rating and any changes (positive or negative) in the rating since the previous reporting period |
| --- | --- | --- | --- |
| Medium | low | low |  |
|  |  |  | If a risk mitigation plan had been presented for a previous period or as a result of the Mid-Term Review/Evaluation please report on progress or results of its implementation |
|  |  |  | 2018 Risk Mitigation Plan: - Lack of transport at country level: Countries are using available options to address the challenge of transport. Following discussions and clarifications provided by EA and during the RSC, some countries have managed to find WHO or malaria programme vehicles to use; and others have arranged car hire. - South Africa participation in the project: A legal agreement has been developed with the Ministry of Environment in South Africa, to support Component 3 activities. |

For joint projects and where applicable ratings should also be discussed with the Task Manager of co-implementing agency.

Some projects are adopting/planning to adopt milestones for tracking the achievement of outcomes. Add the corresponding milestones in this column when applicable to inform the rating. Milestones are optional and may substitute for Mid-Term Target.

Use GEF Secretariat required six-point scale system: Highly Satisfactory (HS), Satisfactory (S), Marginally Satisfactory (MS), Marginally Unsatisfactory (MU), Unsatisfactory (U), and Highly Unsatisfactory (HU).

Add rows if your objective has more than 3 outcome indicators. Same applies for the number of outcomes.

Integrated vector management strategic plan 2019-2023. Ministry of Health and Wellness. Botswana. 31 January 2019.

Integrated vector management guidelines 2019-2023. Ministry of Health and Social Services. Namibia. August 2019.

Outputs as described in the project logframe or in any updated project revision.

As per latest workplan (latest project revision)

Implementation may be assessed by qualitative assessments, percentage of delivery, and/or budget expenditure (planned and actually spent).  The 2018 assessment should be copied from previous PIR.

To be provided by the UNEP Task Manager

Use GEF Secretariat required six-point scale system: Highly Satisfactory (HS), Satisfactory (S), Marginally Satisfactory (MS), Marginally Unsatisfactory (MU), Unsatisfactory (U), and Highly Unsatisfactory (HU)

Only for Substantial to High risk.