## Annex B:  Overview of Technical Consultancies/subcontracts

| Consultant/Individual/Contractor | Time Input | Tasks, Inputs and Outputs |
| --- | --- | --- |
| Project Management |  |  |
| Local / National contracting: |  |  |
| Project Manager USD 2,050 per month, with 5% cost of living adjustment (COLA) per year from Year 2 | 3 months per year; 15 months total over 5 years | The Project Manager will be responsible for the overall management of the project, including the mobilization of project inputs, supervision over project staff, consultants and sub-contractors. See the full TOR in Annex C for details. |
| Project Assistant/Finance Officer USD 1,500 per month, with 5% COLA per year from Year 2 | 7 months per year; 35 months total over 5 years | The Project Assistant/Finance Officer will be responsible for finance, administration, IT and support translations. See the full TOR in Annex C for details. |
| Component 1 |  |  |
| Local / National contracting: |  |  |
| Project Manager USD 2,050 per month, with 5% COLA per year from Year 2 | 2 months per year; 10 months total over 5 years | The Project Manager will be responsible for the overall management of the project, including the mobilization of project inputs, supervision over project staff, consultants and sub-contractors. See the full TOR in Annex C for details. |
| Project Assistant/Finance Officer USD 1,500 per month, with 5% COLA per year from Year 2 | 1 month per year; 5 months total over 5 years | The Project Assistant/Finance Officer will be responsible for finance, administration, IT and support translations. See the full TOR in Annex C for details. |
| Chief Technical Officer (local/national consultant) USD 1,500 per week | 12 weeks over 5 years | The Chief Technical Advisor provides overall strategic guidance on the project, working closely with the Project Manager and contracted consultants and service providers on developing TORs, reviewing deliverables and liaising with the GRFA coordination committees. See the full TOR in Annex C for details. |
| Environmental Economist (local consultant) USD 1,250 per week | 7 weeks | Output 1.3: - Lead an analysis of opportunities to implement eco-compensation schemes to incentivize in-situ conservation and sustainable use of GRFA in Hainan province, according to the guideline on promoting green agricultural development in Hainan province; e.g., direct payments for growing GRFA varieties, rewards for maintaining diversity, etc., and emphasizing equitable participation by women and youth. - Contributed to the preparation of an implementation plan for demonstrating appropriation of eco-compensation funds for the conservation and sustainable use of indigenous GRFA varieties in the Central Highlands area, consistent with the regulatory framework associated with key ecological function areas in China. |
| Policy/legal development assistance (contractual services: company) USD 1,250 per week | 18 weeks | Output 1.1: - Prepare charters for one provincial and three county level GRFA inter-sectoral coordination committees; the charters should include but not be limited to, a description of the purpose of the committee, an indication of the form of type of committee, membership and chairperson, roles and responsibilities, and standard committee procedures. - Contribute to the preparation of coordination procedures and protocols for the knowledge-sharing platform developed under Output 4.2. Output 1.2: - Carry out a gap analysis on policies, strategies and regulations associated with conservation and sustainable use of GRFA in Hainan province, and prepare recommendations for revising or introducing policies, strategies and regulations to better enable incentivized conservation and sustainable use of GRFA, including mechanisms to encourage increased participation by women and youth. - Prepare a provincial agrobiodiversity strategy and action plan, complementary to the provincial biodiversity strategy and action plan. - Prepare provincial GRFA implementation framework, to provide a regulatory framework for encouraging beneficial activities and removing disincentives that reduce agrobiodiversity. - Prepare GRFA implementation frameworks for Baisha County, Qiongzhong County and Qionghai City that facilitate incentive mechanisms for farmers, agricultural associations and enterprises to expand conservation and sustainable use of GRFA. |
| Knowledge management technical assistance (contractual services: company) USD 1,250 per week | 1 week | Output 1.1: - Contribute to the development of procedures and protocols for the knowledge-sharing platform. |
| Capacity development technical assistance (contractual services: company) USD 1,250 per week | 4 weeks | Output 1.1: - Contribute to the establishment of inter-sectoral and cross-sectoral GRFA coordination committees. |
| GRFA expert technical assistance (contractual services: company) USD 1,250 per week | 6 weeks | Output 1.3: - Contribute to the gap analysis of eco-compensation opportunities and development of draft guidelines. - Contribute to the preparation of the eco-compensation demonstration plan. - Contribute to the evaluation of the results of the eco-compensation demonstration. |
| Component 2 |  |  |
| Local / National contracting: |  |  |
| Project Manager USD 2,050 per month, with 5% COLA per year from Year 2 | 3 months per year; 15 months total over 5 years | The Project Manager will be responsible for the overall management of the project, including the mobilization of project inputs, supervision over project staff, consultants and sub-contractors. See the full TOR in Annex C for details. |
| Project Assistant/Finance Officer USD 1,500 per month, with 5% COLA per year from Year 2 | 2 months per year; 10 months total over 5 years | The Project Assistant/Finance Officer will be responsible for finance, administration, IT and support translations. See the full TOR in Annex C for details. |
| Chief Technical Officer USD 1,500 per week | 8 weeks over 5 years | The Chief Technical Advisor provides overall strategic guidance on the project, working closely with the Project Manager and contracted consultants and service providers on developing TORs, reviewing deliverables and liaising with the GRFA coordination committees. See the full TOR in Annex C for details. |
| Environmental Economist (local consultant) USD 1,250 per week | 10 weeks | Output 2.1: - Support development of the GRFA conservation and sustainable use plans. Output 2.2: - Provide technical assistance in the implementation of the eco-compensation demonstration. Output 2.3: - Support the value/supply chain analyses for the three target GRFA varieties. |
| Community Development/M&E Specialist (local consultant) USD 1,250 per week | 41 weeks | Output 2.1: - Support the establishment and operationalization of landscape committees for the three demonstration landscapes in Baisha County, Qiongzhong County and Qionghai City, with participation by local farmers, agricultural associations and cooperatives, enterprise sector, NGOs and local government units, and having equitable representation of women and youth. - Deliver trainings to landscape committee members. - Support the participatory GRFA landscape assessments of the three demonstration landscapes. Output 2.2: - Support development of calls for proposals, review of submitted proposals. - Support implementation of GRFA conservation and sustainable use plans, establishment of community seed bank(s) for Shanlan rice, organization of livestock competitions. - Provide professional assistance in support of the eco-compensation demonstration. - Provide monitoring & evaluation services of the implementation of the GRFA conservation and sustainable use plans. - Support organization of a workshop on traditional knowledge. Output 2.4: - Support the development of a capacity development plan for farmers, agricultural associations and enterprises. - Support implementation of actions according with capacity development plans. - Contribute to the organization of trade fairs showcasing GRFA products and services. |
| Gender Specialist (local consultant) USD 1,250 per week | 12 weeks | Output 2.1: - Provide professional assistance in operationalizing the landscape committees and delivering training to the committee members. Output 2.2: - Provide professional assistance towards the implementation of the GRFA conservation and sustainable use plans. - Support the organization of a workshop on traditional GRFA knowledge. Output 2.3: - Provide professional assistance in the establishment and operationalization of women’s GRFA marketing groups. Output 2.4: - Provide professional assistance in knowledge transfer and partnership establishment exchanges. |
| Business Development Specialist (local consultant) USD 1,250 per week | 17 weeks | Output 2.1: - Deliver training to landscape committee members. Output 2.3: - Lead the value/chain analyses of the three target GRFA varieties and preparation of business development plans. - Contribute to the development of promotional products of GRFA offerings. Output 2.3: - Provide professional assistance in the establishment and operationalization of women’s GRFA marketing groups. Output 2.4: - Provide technical assistance for developing capacity development plans for farmers and agricultural associations. - Support the implementation of the capacity development plans. - Support the organization of GRFA trade fairs on showcasing GRFA products and services. |
| GRFA expert technical assistance (contractual services: company) USD 1,250 per week | 34 weeks | Output 2.1: - Lead the development of standard protocol for participatory GRFA landscape assessments. - Lead the participatory landscape assessments of the three GRFA demonstration landscapes. - Lead development of GRFA conservation and sustainable use plans. Output 2.2: - Provide technical assistance to the implementation of the GRFA conservation and sustainable use plans, design and establishment of the Shanlan rice community seed bank, and design and implementation of livestock competitions. - Support monitoring and evaluation of the implementation of the GRFA conservation and sustainable use plans. Output 2.4: - Support the development of the capacity development plan for farmers, agricultural associations and enterprises. |
| Knowledge management technical assistance (contractual services: company) USD 1,250 per week | 8 weeks | Output 2.2: - Support the communication of results of the implementation of GRFA conservation and sustainable use plans and development of knowledge products of the community interventions. Output 2.4: - Support preparation of a standard code of practice for GRFA conservation and promotional and informative products for specific GRFA offerings. |
| Microgrant management services (contractual services: company) USD 1,250 per week | 26 weeks | Output 2.2: - Develop calls for proposals for implementing actions under the GRFA conservation and sustainable use plans, review proposals and prepare microgrant agreement - Facilitate the implementation of interventions funded with the microgrants. Output 2.3: - Facilitate disbursement and oversee microgrants for interventions associated with the business development plans. Output 2.4: - Facilitate disbursement and overseeing microgrants for interventions associated with farmer capacity development plans. |
| Capacity development technical assistance (contractual services: company) USD 1,250 per week | 5 weeks | Output 2.4: - Prepare an updated capacity development plan for farmers, agricultural associations and enterprises. - Deliver trainings and support other capacity development activities. |
| Marketing/branding technical assistance (contractual services: company) USD 1,250 per week | 5 weeks | Output 2.3: - Support the establishment and operationalization of women’s GRFA marking groups. - Support interventions implemented under the business development plans. Output 2.4: - Deliver trainings and support other capacity development activities. |
| Component 3 |  |  |
| Local / National contracting: |  |  |
| Project Manager USD 2,050 per month, with 5% COLA per year from Year 2 | 3 months per year; 15 months total over 5 years | The Project Manager will be responsible for the overall management of the project, including the mobilization of project inputs, supervision over project staff, consultants and sub-contractors. See the full TOR in Annex C for details. |
| Project Assistant/Finance Officer USD 1,500 per month, with 5% COLA per year from Year 2 | 1 month per year; 5 months total over 5 years | The Project Assistant/Finance Officer will be responsible for finance, administration, IT and support translations. See the full TOR in Annex C for details. |
| Chief Technical Officer USD 1,500 per week | 5 weeks over 5 years | The Chief Technical Advisor provides overall strategic guidance on the project, working closely with the Project Manager and contracted consultants and service providers on developing TORs, reviewing deliverables and liaising with the GRFA coordination committees. See the full TOR in Annex C for details. |
| Gender Specialist (local consultant) USD 1,250 per week | 4 weeks | Output 3.1: - Provide professional assistance in the development of an institutional capacity development plan. - Contribute to the development of capacity-building materials and guidelines. - Contribute to the delivery of training to women professionals. |
| Environmental Economist (local consultant) USD 1,250 per week | 1 week | Output 3.3: - Contribute to the development of a replication strategy and upscaling plan |
| Community Development/M&E Specialist (local consultant) USD 1,250 per week | 6 weeks | Output 3.3: - Provide professional assistance for the participatory GRFA landscape assessments and for developing GRFA conservation and sustainable use plans for two replication landscapes. |
| Policy/legal development assistance (contractual services: company) USD 1,250 per week | 9 weeks | Output 3.2: - Develop a best practices guideline for incentivized approaches for participatory GRFA conservation. - Support integration of incentivized approaches into agricultural sector work programs. - Support stakeholder workshops on disseminating information mainstreaming incentivized approaches. Output 3.3: - Contribute to the development of a replication strategy and upscaling plan. |
| GRFA expert technical assistance (contractual services: company) USD 1,250 per week | 17 weeks | Output 3.1: - Support development of institutional capacity development plan, preparing capacity-building materials, and trainings on GRFA conservation and sustainable use. - Participate in / contribute to knowledge transfer exchanges. - Contribute to targeted trainings for women and youth. Output 3.3: - Support preparation of a replication strategy and upscaling plan. - Contribute to knowledge transfer exchanges in replication landscapes. - Provide technical assistance for participatory landscape assessments and development of GRFA conservation and sustainable use plans in replication landscapes. |
| Capacity development technical assistance (contractual services: company) USD 1,250 per week | 21 weeks | Output 3.1: - Lead the development of an institutional capacity development plan. - Contribute to preparation of capacity-building materials. - Deliver trainings and support other capacity-building activities. - Contribute knowledge transfer exchanges. Output 3.3: - Contribute to knowledge transfer exchanges in replication landscapes. |
| Component 4 |  |  |
| Local / National contracting: |  |  |
| Project Manager USD 2,050 per month, with 5% COLA per year from Year 2 | 1 month per year; 5 months total over 5 years | The Project Manager will be responsible for the overall management of the project, including the mobilization of project inputs, supervision over project staff, consultants and sub-contractors. See the full TOR in Annex C for details. |
| Project Assistant/Finance Officer USD 1,500 per month, with 5% COLA per year from Year 2 | 1 month per year; 5 months total over 5 years | The Project Assistant/Finance Officer will be responsible for finance, administration, IT and support translations. See the full TOR in Annex C for details. |
| Chief Technical Officer USD 1,500 per week | 5 weeks over 5 years | The Chief Technical Advisor provides overall strategic guidance on the project, working closely with the Project Manager and contracted consultants and service providers on developing TORs, reviewing deliverables and liaising with the GRFA coordination committees. See the full TOR in Annex C for details. |
| Community Development/M&E Specialist (local consultant) USD 1,250 per week | 11 weeks | Output 4.1: - Provide professional M&E assistance. - Support the independent midterm review and terminal evaluation. |
| GRFA expert technical assistance (contractual services: company) USD 1,250 per week | 4 weeks | Output 4.3: - Support development and training of the GRFA database. |
| Knowledge management technical assistance (contractual services: company) USD 1,250 per week | 18 weeks | Output 4.2: - Design, administer and interpret baseline and end-of-project KAP surveys. - Develop a knowledge management action plan for the project. - Develop knowledge and communication platforms. - Organize awareness-raising and advocacy campaigns - Organize a targeted awareness event for youth. |
| Database development assistance (contractual services: company) USD 1,250 per week | 24 weeks | Output 4.3: - Prepare a database development plan. - Provide technical assistance for improving the existing GRFA provincial database. - Deliver trainings on the operation of the database. |
| Professional Services for financial NIM auditor | Annual service contract | Output 4.1. See UNDP standard TOR for this service. |
| International contracting: |  |  |
| Midterm Reviewer USD 3,000 per week | 6 weeks in Year 3 | Output 4.1; see UNDP standard TOR for this position. |
| Terminal Evaluator USD 3,000 per week | 6 weeks in Year 5 | Output 4.1; see UNDP standard TOR for this position. |