| Annex E. Stakeholder Engagement Plan |  |
| --- | --- |
| # Project: Participatory in-situ conservation and sustainable use of agrobiodiversity in Hainan (C-SAP3) |  |
| # UNDP PIMS: 5823 | # GEF Project ID: TBD |

# Introduction

This document presents the stakeholder engagement plan for the UNDP-GEF project “Participatory in-situ conservation and sustainable use of agrobiodiversity in Hainan”.

## Project Overview

The project is part of an innovative programmatic approach to mainstream in-situ conservation of agrobiodiversity across China and reduce key threats to globally significant genetic resources for food and agriculture (GRFA). This project is designed to remove barriers currently restricting the protection and sustainable use of agricultural genetic diversity in Hainan province, contributing towards achievement of the long-term objective of strengthening conservation of Hainan’s globally significant agrobiodiversity, through an enhanced provincial policy framework, strengthened institutional capacity, the establishment of innovative incentive mechanisms, and improved knowledge and understanding of the economic and environmental value of agricultural varieties.

A core focus of the project is demonstration of innovative, participatory, partnership-based and incentivized approaches that support the achievement of long-term agrobiodiversity conservation and sustainable development outcomes, including sustainable livelihood impacts for poor farming communities. Three demonstration landscapes have been identified, showcasing the following GRFA varieties: Shanlan rice, Wuzhishan pig and Jiaji duck. The project has a strong potential for catalytic impact, supporting institutional capacity building,  strengthened enabling environments, and the establishment of long-term partnerships between farmers, private and public sector agencies and the creation of marketing networks, certification schemes and new markets for traditional GRFA varieties.

## Stakeholder Engagement Approach

The approach to stakeholder involvement and participation encourages adherence to the following guiding principles:

- Adding value to project activities;

- Ensuring accessibility of information, including by both government and non-government, to inform decision-making processes;

- Encouraging adherence to values of transparency, trust, equity, and fairness;

- Promoting responsiveness to identified needs and the highest ethical standards and respects for differing priorities and values;

- Ensuring local ownership, including ethnic minority communities, and the creation of outputs that are relevant and of benefit to communities and organizations;

- Supporting collaborative approaches to project interventions;

- Including different types of stakeholder groups in participation processes and benefit distribution, including but not limited to engagement, capacity building, employment, skills transfer, sharing of knowledge and the increase of cultural awareness;

- Developing mechanisms to manage conflicts in the public interest;

- Being flexible to adapt to changing circumstances;

- Fostering well-coordinated and planned implementation;

- Generating, and responding to, feedback; and

- Creating proactive partnerships that will enhance sustainability of project results after GEF funding ceases.

## Objectives of Effective Stakeholder Engagement

Effective stakeholder engagement is expected to support the project in generating the following benefits:

- Relate better to the local context;

- Provide technical excellence;

- Follow international good practice;

- Harmonize with other development partners and projects; and

- Reflect a broad range of information and perspectives.

# Summary of Stakeholder Engagement Activities during Project Preparation

Stakeholder consultations completed during the PPG phase are summarized below in Table E-1.

Table E-1: Stakeholder consultations during PPG phase

| Date | Activity | Location | Remarks |
| --- | --- | --- | --- |
| 10 Apr 2018 | C-SAP program inception workshop | Beijing | The objectives of the C-SAP program and each child project, including the Hainan project were described. The project preparation phase activities and timeframes were discussed. |
| 12 Apr 2018 | C-SAP3 project inception workshop | Haikou | The objective of the C-SAP3 project were discussed with provincial stakeholders, PPG tasks were outlined, and feedback obtained during workshop discussions. |
| 12 Apr 2018 | Visit to Yongxing Town, Haikou City | Haikou | Field visit to local community where wild and cultivated litchi are farmed. Interviews were made with local government officials and local farmers. |
| 13 Apr 2018 | Visit to and consultations at Nanwan village | Shangan Township, Qiongzhong County | Consultations were made with local government officials and farmers in Nanwan village, where Shanlan rice is cultivated. |
| 13 Apr 2018 | Consultations with Baisha County officials and stakeholders | Baisha County | A stakeholder consultation meeting was held in Baisha county with local government officials and other stakeholders to discuss potential project activities associated with the Wuzhishan pig. |
| 14 Apr 2018 | Visit to and consultation at Dabing village | Qingsong Township, Baisha county | Consultations were made with local government officials, enterprise sector stakeholders and farmers in Dabing village, where Wuzhishan pig is reared. |
| 14 Apr 2018 | Consultations with Qionghai City officials and stakeholders | Qionghai City | A stakeholder consultation was held in Qionghai City with city officials and other stakeholders, to discuss potential project activities associated with the Jiaji duck. |
| Jul 2018 | Field visits to and consultations at Nanwan village | Qiongzhong County, Shang’an Township | Field visits and consultations with local government officials, representatives of agriculture associations and enterprises, and farmers in Nanwan village, to gather socioeconomic information and to discuss interest and potential activities associated with the Shanlan rice. |
| Jul 2018 | Field visits to and consultations at Yada village | Baisha County, Qingsong Township | Field visits and consultations with local government officials, representatives of agriculture associations and enterprises, and farmers in Yada village, to gather socioeconomic information and to discuss interest and potential activities associated with the Wuzhishan pig. |
| Jul 2018 | Field visits to and consultations at Dahe village | Baisha County, Qingsong Township | Field visits and consultations with local government officials, representatives of agriculture associations and enterprises, and farmers in Dahe village, to gather socioeconomic information and to discuss interest and potential activities associated with the Wuzhishan pig. |
| Jul 2018 | Field visits to and consultations at Shibi village | Qionghai City, Shibi Township | Field visits and consultations with local government officials, representatives of agriculture associations and enterprises, and farmers in Shibi village, to gather socioeconomic information and to discuss interest and potential activities associated with the Jiaji duck. |
| Jul 2018 | Field visits to and consultations at Nanxing village | Qionghai City, Shibi Township | Field visits and consultations with local government officials, representatives of agriculture associations and enterprises, and farmers in Nanxing village, to gather socioeconomic information and to discuss interest and potential activities associated with the Jiaji duck. |
| Jul 2018 | Field visits to and consultations at Shuangfeng village | Qionghai City, Shibi Township | Field visits and consultations with local government officials, representatives of agriculture associations and enterprises, and farmers in Shuangfeng village, to gather socioeconomic information and to discuss interest and potential activities associated with the Jiaji duck. |
| 5 Nov 2018 | C-SAP3 review workshop | Haikou | A PPG review workshop was held in Haikou with provincial and county officials, representatives of agricultural associations and enterprises, and other stakeholders to discuss proposed project outputs and activities and remaining steps before completing the project document for review. |
| 28 Nov 2018 | Field visit to and consultations at Kecheng village | Baisha County | Field visits and consultations with local government officials, representatives of agriculture associations and enterprises, and farmers in Kecheng village, to gather socioeconomic information and to discuss interest and potential activities associated with the Wuzhishan pig. |

# Project Stakeholders

The project will engage with a broad spectrum of stakeholders, utilizing existing structures as much as practicable. A stakeholder analysis is presented below in Table E-2, indicating the interest of each stakeholder group in relation to the project, the estimated effect on project interests and their importance and influence the project.

Table E-2: Stakeholder Analysis

| Stakeholders |  | Interests at stake in relation to project | Effect of project on interests (+ 0 -) | Importance 1=Little/No Importance 2=Some Importance 3=Moderate Importance 4=Very Important 5=Critical player | Influence 1=Little/No Influence 2=Some influence 3=Moderate Influence 4=Significant Influence 5=Very Influential |
| --- | --- | --- | --- | --- | --- |
| Implementing partner: |  |  |  |  |  |
| 1 | Hainan Department of Agriculture and Rural Affairs (DARA) | Strengthen policies and capacities on agrobiodiversity management | + | 5 | 5 |
| GEF agency: |  |  |  |  |  |
| 2 | UNDP | Ensure global environmental benefits are generated, and effective and efficient project implementation | + | 5 | 5 |
| Key national agencies and central governmental stakeholders: |  |  |  |  |  |
| 3 | Ministry of Finance | Efficient utilization of resources and cofinancing delivered | + | 5 | 5 |
| 4 | Ministry of Agriculture and Rural Affairs (MARA) | Contributions towards national level objectives on agrobiodiversity management | + | 4 | 4 |
| Key provincial agencies and governmental stakeholders: |  |  |  |  |  |
| 5 | Hainan Department of Finance | Efficient project implementation, according to provincial policies and procedures | + | 5 | 5 |
| 6 | Hainan Department of Ecology and Environment | Strengthened capacities and integration of agrobiodiversity into sectoral strategies | + | 3 | 2 |
| 7 | Hainan Department of Natural Resources | Strengthened capacities and integration of agrobiodiversity into sectoral strategies | + | 3 | 2 |
| 8 | Hainan Development and Reform Commission | Strengthened capacities and integration of agrobiodiversity into provincial development strategies | + | 3 | 2 |
| 9 | Hainan Office of Poverty Alleviation | Strengthened capacities and integration of agrobiodiversity into poverty alleviation strategies | + | 3 | 2 |
| 10 | Hainan Department of Education | Strengthened capacities and integration of agrobiodiversity into sectoral strategies | 0 | 2 | 2 |
| 11 | Hainan Department of Water Resources | Strengthened capacities and integration of agrobiodiversity into sectoral strategies | 0 | 2 | 1 |
| Local government unit stakeholders: |  |  |  |  |  |
| 12 | County Agriculture Bureaus; Township Agriculture Stations | Scale-able demonstrations of participatory approaches to agrobiodiversity management, and strengthened capacities | + | 4 | 4 |
| Social organizations and non-governmental organizations (NGOs) |  |  |  |  |  |
| 13 | All-China Women’s Federation | Strengthened capacities and promotion of women empowerment | + | 4 | 2 |
| 14 | Communist Youth League of China | Strengthened capacities and promotion of youth inclusion | + | 2 | 1 |
| 15 | Other social organizations | Promotion of development objectives associated with agrobiodiversity management | + / 0 | 2 | 1 |
| Local communities where project interventions are planned: |  |  |  |  |  |
| 16 | Local communities, farmers | Increased knowledge, strengthened capacities, sustainable livelihood opportunities, expanded or new partnerships | + | 5 | 4 |
| Agricultural associations, including cooperatives: |  |  |  |  |  |
| 17 | Agricultural associations, including cooperatives | Increased knowledge, strengthened marketing and organizational capacities, expanded or new partnerships | + | 4 | 3 |
| Enterprises: |  |  |  |  |  |
| 18 | Enterprises engaged in GRFA varieties | Increased knowledge, strengthened marketing and organizational capacities, improved supply/value chain management, expanded or new partnerships | + | 4 | 3 |
| 19 | Trade associations | Promotion of best management practices and marketing opportunities for members | 0 | 2 | 2 |
| Academic and research organizations: |  |  |  |  |  |
| 20 | Academic and research organizations | Strengthened capacities, dissemination of best practices and approaches in agrobiodiversity management | + | 3 | 2 |
| Certification Organizations |  |  |  |  |  |
| 21 | Certification Organizations for geographical indication, organic food, etc. | Increased awareness of GRFA varieties, promotion of best management practices | + | 2 | 2 |

# Stakeholder Engagement Plan

## Project-Specific Stakeholder Engagement Considerations

The project objective to “strengthen the in-situ conservation and sustainable use of globally significant agrobiodiversity in Hainan through the development of incentive mechanisms for farmers to sustain populations of endemic crops and livestock, the establishment of a supportive ‘enabling environment’ and strengthened institutional capacity” will be achieved through four mutually supportive outcomes, distributed across the following four components:

Component 1: Strengthened provincial framework

Outcome 1: Policy and regulatory frameworks reformed, and inter-sectoral coordination reinforced to expand the conservation and sustainable use of GRFA

Component 2: Demonstration of sustainable incentive mechanisms for in-situ conservation and sustainable use of agrobiodiversity

Outcome 2: Market- and non-market-based incentive mechanisms established and demonstrated in target landscapes to increase conservation and sustainable use of GRFA and enable long-term livelihood benefits for local farmers

Component 3: Mainstreaming and institutional capacity strengthening

Outcome 3: Demonstrated approaches mainstreamed and capacities strengthened to facilitate upscaling of incentivized conservation and sustainable use of GRFA

Component 4: Monitoring & evaluation and knowledge management

Outcome 4: Knowledge, attitudes and practices improved, and knowledge management structures enhanced to broaden participation in the conservation and sustainable use of GRFA

Effective stakeholder engagement will be one of the key factors in the implementation of the project.

Under Component 1, the project will facilitate stakeholder engagement and dialogue into the development of provincial and county agrobiodiversity management implementation frameworks and ensuring that market-based and non-market-based incentive mechanisms for expanding engagement of GRFA farming will equitable reflect the capacities, needs and priorities of women and men farmers. Recommendations for allocating eco-compensation appropriations towards GRFA conservation will consider equitable benefits to women and men – and to ethnic minority people. The GRFA Intersectoral Coordination Committee will function as a central stakeholder engagement platform, established in Component 1 and influencing the entire project.

Stakeholder engagement under Component 2 is focused at the local level, starting with the establishment of GRFA Landscape partnership working groups in each of the three demonstration landscapes. The committees will help ensure that project interventions are inclusive and consider a cross-section of stakeholder interests. Activities involving strengthening marketing capacities and development of GRFA markets will help strengthen and expand partnerships between public and private stakeholders, with the underlying aim to deliver sustainable livelihood benefits for local farmers, with equitable participation by ethnic minorities, women and youth.

Under Component 3, institutional stakeholder capacity development activities will also promote equitable involvement of women and youth and ethnic minorities. Sectoral work programs at the province and county levels will be developed through proactive stakeholder engagement. Best management practices demonstrated in Component 2 will be upscaled to other landscapes in the province, including sharing the effective stakeholder engagement approaches applied.

The stakeholder engagement plan will be presented during the project inception workshop under Component 4, and adaptive management adjustments made, e.g., in case circumstances change between the time of project development and initiation of project implementation. Monitoring and evaluation of the stakeholder engagement plan are included in the project M&E plan and project progress reports will document findings and present any adaptive management measures taken and recommendations. The knowledge, attitudes and practices (KAP) baseline survey will address differences between women and men and the circumstances of ethnic minority communities, and the resultant knowledge management strategy and action plan will include specific actions to address these differences. Lessons learned will be shared across the C-SAP program using the program level knowledge management platform, the program steering committee, exchange visits among the child projects and informal interactions among the project teams.

## Long-term Stakeholder Participation

The project will facilitate long-term stakeholder participation, with a special emphasis on the active participation of women and youth, and enhancement of intersectoral coordination for implementing agrobiodiversity management strategies and plans.

Decision-making – through the establishment of the Project Steering Committee (PSC). The establishment of the structure will follow a participatory and transparent process involving the confirmation of all key project stakeholders; conducting one-to-one consultations with stakeholders; refinement of the terms of reference and ground-rules; inception meeting to agree on the constitution of the PSC.

Capacity building – at systemic, institutional and individual levels – is one of the key strategic interventions of the project and will target stakeholders that have the potential to be involved in implementation of the project, including demonstration activities at the local level. Women, youth and people of ethnic minority present within the project sites will be proactively considered for capacity building activities.

Communication - will include the participatory development of knowledge management strategy and action plan. The knowledge management strategy will be based on the following key principles: providing information to stakeholders; promoting dialogue between stakeholders; and promoting access to information.

The project design incorporates several features to ensure on-going and effective stakeholder participation in the project’s implementation. The mechanisms to facilitate involvement and active participation of different stakeholders in project implementation will comprise several different components, as described below.

### Project Inception Workshop

The project will be launched by a multi-stakeholder inception workshop, building on the PPG review workshops already held. The inception workshop will provide an opportunity to provide stakeholders with the most updated information on the project, refine and confirm the work plan and results framework, and will establish a basis for further consultations as the project implementation phase commences.

### Project Steering Committee

The Project Steering Committee’s membership will ensure representation of key interests throughout the 5-year project implementation timeframe. The members and terms of reference of the steering committees are described in the Governance and Management Arrangements section  and Annex C to the project document. The establishment of this structure will follow a participatory and transparent process involving the confirmation of  key project stakeholders and nominated focal points. The inception workshop will agree on the constitution of the committee, and finalization of its terms of reference and ground-rules.

### Project Management Office and Focal Points among Provincial and Local Government Units

The Project Management Office (PMO) will take direct operational responsibility for facilitating stakeholder involvement and ensuring local ownership of the project and its results. The PMO will be located in the Hainan Department of Agriculture and Rural Affairs (DARA) offices in Haikou to ensure coordination among key stakeholder groups at provincial and local government levels.

The National Project Director (NPD), the Deputy Director General of the Hainan DARA, will be accountable to the DARA and UNDP for the achievement of objectives and results in the assigned project. The NPD will be a member and chair of the Project Steering Committee and answer to it. The NPD will be financed through provincial government cofinancing fund. The NPD will designate focal points within the county agriculture bureaus and township agricultural stations for each of the three target counties; these local government focal points will garner support for the project within their organizations and other stakeholder groups.

### GRFA Intersectoral Coordination Committee and Activity Level Working Groups

The project will facilitate establishment of a GRFA Intersectoral Coordination Committee, having representatives from key provincial agencies. This committee will be an important stakeholder engagement platform, providing advisory support to the project, e.g., reviewing policy and regulatory reforms, eco-compensation guidelines and systems and procedures for improving knowledge management.

At the activity level, working groups will be established as required, e.g., policy reform, to facilitate the active participation of affected institutions, organizations and individuals in the implementation of the respective project activities. Different stakeholders may take the lead in each of these groups, depending on their respective mandates. There will be representation of women according to the targets of the project’s gender action plan in working groups and activities such as capacity building and awareness programs.

### GRFA Landscape partnership working groups

The project will establish landscape partnership working groups in each of the three demonstration landscapes that will oversee completion of participatory landscape assessments and development of GRFA conservation and sustainable use plans. Through the function of the landscape partnership working groups and joint planning activities, participatory structures will be developed, improving information sharing and awareness among stakeholders.

### Project Knowledge Management and Communications

The project will develop, implement and annually update a knowledge management strategy and action plan to ensure that stakeholders are informed on an ongoing basis about the project activities, overall project progress, and the opportunities for stakeholders’ involvement in various aspects of the project’s implementation.

## Ethnic Minority Engagement

The project will ensure that stakeholder engagement is undertaken in a culturally appropriate manner, including for the Li and Miao ethnic minority peoples that predominate the local communities within the Shanlan rice landscape in Da’an Township in Qiongzhong County and within the Wuzhishan pig landscape in Dabing Township in Baisha Li Autonomous County.

### Ethnic minorities in the project demonstration landscapes

Most of the Li ethnic group lives in the Hainan Li autonomous counties Ledong, Dongfang, Baisha, Lingshui, Changjiang and other counties, the two Hainan Li-Miao autonomous counties of Baoting and Qiongzhong, and the two cities Sanya and Tongshi. Livelihoods of the Li people are mainly generated through agricultural activities. Li women are known for their weaving skill, particularly using silk cotton.

The Miao people are one of the largest ethnic minority groups in southwest China. In the 16th century Miao people settled on Hainan island, as results of military conscription, and now constitute the second largest ethnic group in the Province, with a population of approximately 60,000. They have their own languages, mostly spoken, with no formal written characters. The majority of Miao people reside in the central mountainous areas in Hainan Island, and many of their livelihoods depend on traditional agriculture practices. Li people are the biggest ethnic minority group in Hainan Province. They have their own language, but most Li people speak Mandarin. Based on a nationwide survey in 2010, there were 1.46 million Li people.

Due to a number of factors, including language constraints, education attainment, geographic location, etc., socioeconomic conditions in some ethnic minority communities lag behind the broader population in the province and in the country.

Shanlan rice landscape in Shang’an Township, Qiongzhong Li and Miao Autonomous County:

As part of the project preparation phase, socioeconomic surveys were made in July 2018 at 25 households in Shang’an Township, Qiongzhong County, about 7.5% of the total households in the landscape. There are 334 households and a population of 1,248 (793 females and 445 males) in Nanwan. Nanwan is a rural village, with most inhabitants engaged in farming. Among the people surveyed, 11 are Li people and 14 are Miao people; no Han people were among those surveyed.

Wuzhishan pig landscape in Da’an Township, Baisha Li Autonomous County:

As part of the project preparation phase, socioeconomic surveys were made in November 2018 at 25 households in the village of Kecheng in Baisha County, about 1.7% of the total of the total households in the landscape. There are 329 households and a population of 1,468 (668 females and 800 males) in Kecheng. Kecheng is a rural village, with most inhabitants engaged in farming. All the people surveyed were Li people, 24 people surveyed were male, while 1 was female.

### Legal and institutional frameworks applicable to the ethnic minority people

China is signatory to the United Nations Declaration on the Rights of Indigenous Peoples, a comprehensive statement addressing the human rights of indigenous peoples. There are a total of 56 ethnic groups identified in China, mainly based on their similarities such as common ancestry, language, society, and culture. Of the 56 ethnic groups, Han ethnicity is the ethnic majority and the other 55 ethnic groups are considered ethnic minorities. The term “indigenous peoples” is not used in China.

The Constitution (1982, revised in 2004) addresses the issue of PA through confirming the state and collective ownership of land and natural resources and prescribing the State’s responsibility in environmental and resource protection. The Constitution emphasizes that all nationalities in the People’s Republic of China are equal. The State protects the lawful rights and interests of minority nationalities and upholds and develops a relationship of equality, unity and mutual assistance among all of China’s nationalities. The State assists areas inhabited by minority nationalities in accelerating their economic and cultural development according to the characteristics and needs of the various minority nationalities. Regional autonomy is practiced in areas where people of minority nationalities live in concentrated communities; in these areas organs of self-government are established to exercise the power of autonomy. And in exploiting natural resources and building enterprises in the national autonomous areas, the State shall give due consideration to the interests of those areas. And all these provisions are reiterated in the Regional Ethnic Autonomy Law (1984, revised in 2001).

The Rules of the State Council on the implementation of the Law of the People's Republic of China on Regional National Autonomy (2005) stipulates that the state strengthens the poverty alleviation and development of the ethnic autonomous areas, and emphasizes the infrastructure and the basic construction of the farmland in the poor rural areas of the autonomous areas, which focus on water, electricity, access, radio, television construction, and the transform of thatched house and dilapidated house, and ecological migration. And all these activities are based on the residents’ willingness.

### Action plan for inclusive engagement of ethnic minority people

The objective of the of the action plan for inclusive engagement of ethnic minority people is to encourage ethnic minorities to participate in the project, ensuing that they benefit from project and minimize negative impacts on them.

- Communicate project information in local languages and through methods that are culturally appropriate.

- Ensure ethnic minorities have equitable representation in the decision-making bodies associated with the community level project activities – particularly the landscape partnership working groups.

- Ensure participation of ethnic minorities is gender inclusive and tailored to the needs of disadvantaged and vulnerable groups.

- Facilitate/strengthen community organizations, e.g., agricultural associations, including cooperatives.

- Deliver skills and know-how training, including professional training for farmers, capacity building for establishing or strengthening markets for GRFA products and services, including specialized agro-ecotourism products and services.

- Focus on delivering broad sustainable livelihood benefits, including improvements to soil fertility, strengthening protection of germplasms, e.g., through community seed banks, improving social cohesion, e.g., through capacity building for agricultural associations, including cooperatives.

- Ensure timely access to information. Project details will be communicated orally and visually as well as in written form in local languages, to ensure local stakeholders can understand the specific activities being implemented and the potential impacts and benefits.

### Free, prior and informed consent (FPIC) during project implementation

Implementation of project activities in the communities predominated by ethnic minorities require a FPIC process based on the following appraisal criteria:

- The activities involve natural resource extraction such as logging agricultural development on the lands/territories of ethnic minorities.

- The activities involve the accessing of traditional knowledge, innovations and practices of ethnic minorities and local communities.

- The activities involve making commercial use of natural and/or cultural resources on lands subject to traditional land rights and/or under customary use by ethnic minorities?

Through the guidance of the Landscape partnership working groups and in conjunction with development of the GRFA conservation and sustainable use plans for the demonstration landscapes, FPIC consultations will be carried out with ethnic minority communities in the demonstration landscapes as part of project implementation.

### Proposed project activities involving ethnic minority communities

Proposed project activities involving ethnic minority communities are summarized below in Table E-3:

Table E-3: Proposed project activities in ethnic minority communities

| Project Output | Proposed Activity |
| --- | --- |
| Output 2.1: Participatory structures and planning and monitoring protocols put in place to improve conservation of traditional GRFA varieties in three demonstration landscapes | - Establish and operationalize landscape committees for the three demonstration landscapes, with participation by local farmers, agricultural associations and cooperatives, enterprise sector, NGOs and local government units, and having equitable representation of ethnic minorities, women and youth. - Deliver training to the landscape committee members on topics including community development, fund management, nutritional value of GRFA varieties, cultural value and traditional knowledge, conflict resolution, GRFA conservation, etc. - Carry out participatory GRFA landscape assessments of the demonstration landscapes. - Develop GRFA conservation and sustainable use plans for the three demonstration landscapes. - Facilitate free, prior and informed consent (FPIC) consultations with ethnic minorities communities in the demonstration landscapes. |
| Output 2.2: Gender-mainstreamed market- and non-market-based incentive mechanisms for in-situ agrobiodiversity conservation are demonstrated at 3 target agricultural landscapes, resulting in enhanced germplasm protection and securing sustained livelihood benefits for farmers and improved conservation of target varieties | - Facilitate implementation of the GRFA conservation and sustainable use plans, disbursing micro grants for selected interventions and providing advisory support to local beneficiaries, to introduce new farming approaches, increase yield, demonstrate improved breeding practices, improve management of agricultural chemicals and wastes, strengthen management of invasive alien species, etc. - Design, procure and establish a community seed bank for Shanlan rice, collaborating with local government units, farmers, agricultural associations and enterprises, to provide an enduring mechanism for enhancing the germplasm of this GRFA variety. - Plan and organize annual livestock competitions for Wuzhishan pig and Jiaji duck, collaborating with local government units, farmers, agricultural associations and enterprises, to provide an enduring mechanism for enhancing the germplasm of these GRFA varieties. - Prepare knowledge products on the community interventions and disseminate through the knowledge management platform developed under Output 4.2. - Organize and convene a workshop, sharing best practices and lessons learned on application of traditional ecological knowledge for GRFA conservation and sustainable use. |
| Output 2.3: Agrobiodiversity supply and value chains of the target GRFA varieties enhanced through strengthened marketing capacities and expanded application of marketing tools, including cultural value branding and product certification | - Carry out supply or value chain analyses, elaborating specific recommendations into marketing strategies and plans for each of the target GRFA varieties. - Based on the recommended actions in the organizational and partnership development plans and in collaboration with existing farmer field schools, provide technical and microgrant assistance to farmers, agricultural associations and enterprises, including but not limited to: (a) developing niche markets; (b) obtaining or improving the marketing of product certification; (c) promoting cultural preference/branding; (d) strengthening collective marketing approaches; (e) improving quality control of GRFA products and offerings; (f) developing specific agro-ecotourism experiences; (g) introducing or expanding traceability schemes for GRFA varieties; (h) promoting recognition of tradition knowledge; etc. |
| Output 2.4: Farmers, agriculture associations and enterprises capacitated and GRFA conservation and sustainable use improved through partnership development and organizational strengthening, with a focus on increasing participation by women and youth | - Based on the recommended actions in the organizational and partnership development plans and in collaboration with existing farmer field schools, provide technical and microgrant assistance to farmers, agricultural associations and enterprises, including but not limited to: (a) improving financial management and other small business skills; (b) expanding online trading approaches; (c) improving quality control of GRFA products and offerings; (d) specific trainings on expanding inclusion of women and youth; etc. - Organize one trade fair in Hainan province and one in each of the three target provinces, promoting GRFA products and offerings, showcasing nutritional and taste value of GRFA varieties and to facilitate marketing and partnership opportunities, with a special focus on inclusion of ethnic minorities, women and youth. |

# Resources, Roles and Responsibilities

The PMO, led by the Project Manager, will be responsible for implementation of the stakeholder engagement plan and for installing adaptive management measures as deemed relevant based on progress made on project activities. The GRFA Intersectoral Coordination Committee will be responsible for providing technical and strategic guidance during implementation, and the committee members might be invited to make presentations at Project Steering Committee meetings as needed. At the local level, the GRFA Landscape partnership working groups will be the main stakeholder engagement structures for guiding the activities associated with the three demonstration landscapes. Engagement with multilateral and bilateral financial and technical cooperation agencies will be facilitated largely through technical advisory arrangements and networking on complementary projects and initiatives, as described below in Table E-4.

Table E-4: Stakeholder engagement roles and responsibilities

| Position / Function | Roles and Responsibilities |
| --- | --- |
| National Project Director | The National Project Director (NPD) will have overall responsibility for the implementation of the project. The NPD will ensure that the project operates according to relevant national and provincial policies and procedures. |
| Project Manager | The Project Manager will have responsibility for the day-to-day implementation of the project, be tasked with the important role of ensuring that stakeholders are engaged according to plan, oversee the procurement and implementation of project activities and be accountable that stakeholder engagement is inclusive and according to plan. |
| Project Steering Committee | The Project Steering Committee (PSC) will provide strategic oversight to the project, ensuring that the interests of the representative members are considered, including stakeholder engagement objectives. |
| GRFA Intersectoral Coordination Committee | The GRFA Intersectoral Coordination Committee will be comprised of provincial stakeholders having mandates that include aspects related to in-situ conservation and sustainable use of agrobiodiversity. |
| All-China Women’s Federation | A representative of the provincial office of the All-China Women’s Federation (ACWF) will be included onto the PSC and the GRFA Intersectoral Coordination Committee, providing an important linkage between the national and provincial gender mainstreaming objectives with those of the project. |
| Local Government Unit Focal Points | Project focal points will be designated in the three counties and three townships where project demonstrations are planned. These focal points will be responsible to ensure local stakeholders are engaged in the project, with particular emphasis on participation of ethnic minorities, women and youth. |
| Landscape partnership working groups | Landscape partnership working groups are planned in each of the three demonstration landscapes, and include representation by local governments, farmers, agricultural associations, enterprises and NGOs. These committees will ensure stakeholder engagement through the community-level project interventions. |
| C-SAP Program M&E / Coordination Officer | The C-SAP program coordination team will include a Monitoring & Evaluation (M&E) / Coordination Officer, tasked with coordinating M&E across the five child projects. This officer will provide advisory support to the Project Manager and other project stakeholders, sharing approaches and lessons learned regarding stakeholder engagement and other aspects of the program M&E plan. |
| C-SAP Program KM / Communications Officer | The C-SAP program coordination team will also include a Knowledge Management (KM) / Communications Officer, who will be responsible for the development and implementation of the program level KM strategy and action plan and providing advisory support to the child projects, including sharing approaches and lessons learned. |

# Grievance Mechanism

Interested stakeholders may raise a grievance at any time to the Project Management Office, the Executing Agency (Hainan DARA) or the Implementing Agency (UNDP).

Due diligent efforts will be made by the local project representatives to first resolve grievances locally, in a manner sensitive to local social and cultural norms. If the local process does not result in resolution of a grievance, the case will be upgraded to the PMO (Executing Agency), with the process managed by the Project Manager and National Project Director providing guidance and signing off on written responses to grievances.

The UNDP Country Office, as the Implementing Agency, will be the next avenue for resolving grievances if the case is not resolved at the local level or by the Executing Agency. The Resident Representative will identify a member of the Country Office management team to oversee and manage the grievance through the UNDP Stakeholder Response Mechanism (SRM). The SRM ensures individuals, peoples, and communities affected by projects have access to appropriate grievance resolution procedures for hearing and addressing project-related complaints and disputes. Further information, including how to submit a grievance to the SRM is found on the UNDP website at: http://www.undp.org/content/undp/en/home/operations/accountability/secu-srm/

# Timetable

Stakeholder engagement will be facilitated through the Project Steering Committee, the GRFA Intersectoral Coordination Committee, the GRFA Landscape partnership working groups, and through organizing workshops, trade fairs, awareness campaigns. An indicative stakeholder engagement schedule is listed below in Table E-5.

Table E-5: Indicative stakeholder engagement schedule

| No. | Description | Timing | Location |
| --- | --- | --- | --- |
| 1 | Project Inception workshop | Year 1 | Haikou |
| 2 | Program Inception workshop | Year 1 | Beijing |
| 3 | Project Steering Committee | Annual | Haikou in Year 1 and rotating among the demonstration landscapes in other years |
| 4 | C-SAP Program Steering Committee (host one program steering committee meeting, showcasing results achieved and providing an opportunity to share lessons learned and experiences) | To be determined | Haikou, with field visit(s) to demonstration landscape(s) |
| 5 | GRFA Intersectoral Coordination Committee | Est. 2X per year | Haikou |
| 6 | GRFA Landscape partnership working group, Shanlan rice | Est. quarterly | Shang’an Township, Qiongzhong County |
| 7 | GRFA Landscape partnership working group, Wuzhishan pig | Est. quarterly | Da’an Township, Baisha County |
| 8 | GRFA Landscape partnership working group, Jiaji duck | Est. quarterly | Shibi Township, Qionghai City |
| 9 | Provincial workshop to inform stakeholders of the GRFA strategies and regulatory frameworks developed | Year 3 | Haikou |
| 10 | Provincial workshop, inviting governmental and non-government sector, agriculture associations, enterprises, etc., to discuss eco-compensation opportunities | Year 2 | Haikou |
| 11 | Workshop to share best practices and lessons learned on application of traditional knowledge for agrobiodiversity management | Year 4 or 5 | Haikou |
| 12 | Provincial trade fair, promoting GRFA products and offerings, showcasing nutritional and taste value of GRFA varieties and to facilitate marketing and partnership opportunities, with a special focus on inclusion of women and youth. | Year 3 or 4 | Haikou |
| 13 | County trade fair, promoting GRFA products and offerings, showcasing nutritional and taste value of GRFA varieties and to facilitate marketing and partnership opportunities, with a special focus on inclusion of women and youth. | Year 3 or 4 | Qiongzhong County |
| 14 | County trade fair, promoting GRFA products and offerings, showcasing nutritional and taste value of GRFA varieties and to facilitate marketing and partnership opportunities, with a special focus on inclusion of women and youth. | Year 3 or 4 | Baisha County |
| 15 | County trade fair, promoting GRFA products and offerings, showcasing nutritional and taste value of GRFA varieties and to facilitate marketing and partnership opportunities, with a special focus on inclusion of women and youth. | Year 3 or 4 | Qionghai City |
| 16 | Provincial workshop to disseminate information on incentivized approaches for participatory GRFA conservation and sustainable use | Year 4 or 5 | Haikou |
| 17 | County workshop to disseminate information on incentivized approaches for participatory GRFA conservation and sustainable use | Year 4 or 5 | Qiongzhong County |
| 18 | County workshop to disseminate information on incentivized approaches for participatory GRFA conservation and sustainable use | Year 4 or 5 | Baisha County |
| 19 | County workshop to disseminate information on incentivized approaches for participatory GRFA conservation and sustainable use | Year 4 or 5 | Qionghai City |
| 20 | Advocate the global environmental benefits generated through the project by participating in national, regional and international conferences, workshops, seminars and other events, including but not limited to ... | To be determined | To be determined |
| 21 | Organize awareness raising and advocacy campaigns, focused on specific themes and aimed at defined target groups, e.g., farmers, governmental agencies, enterprises and the public, through methods identified in the knowledge management action plan, e.g., social media, printed media, radio, local and provincial TV, etc. | To be determined | To be determined |

# Monitoring and Evaluation

The implementation of the stakeholder engagement plan will be monitored and evaluated through the 5-year project timeframe. Stakeholder engagement details will be captured in project reports, meeting memorandums and through various knowledge products. Adaptive management measures will be put in place, as needed, to adjust the plan to current circumstances and according to the findings of monitoring and evaluation efforts.

Monitoring and evaluation of the implementation of the stakeholder engagement plan are part of the project M&E plan, and cofinancing contributions are included.

State Ethnic Affairs Commission of the People’s Republic of China. Regional Ethnic Autonomy Law (second amendment), 28 February 2001).  http://www.seac.gov.cn/art/2011/6/29/art_4901_128701.html

General Office of the State Council. Rules of the State Council on the implementation of the Law of the People's Republic of China on Regional National Autonomy. Issued on 11 May 2005. http://www.gov.cn/xxgk/pub/govpublic/mrlm/200803/t20080328_31650.html