United Nations Development Programme

Project Document

| Project title: Participatory in-situ conservation and sustainable use of agrobiodiversity in Hainan |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Country: People’s Republic of China (China) | Implementing Partner: Hainan Department of Agriculture and Rural Affairs |  |  | Management Arrangements: National Implementation Modality (NIM) |  |  |
| UNDAF/Country Programme Outcome (2016-2020): Priority Area: Improved and Sustainable Environment; Outcome 2: More people enjoy a cleaner, healthier and safer environment as a result of improved environmental protection and sustainable green growth |  |  |  |  |  |  |
| UNDP Strategic Plan (2018-2021) Output: 1.4.1. Solutions scaled up for sustainable management of natural resources, including sustainable commodities and green and inclusive value chains |  |  |  |  |  |  |
| UNDP Social and Environmental Screening Category: Moderate |  |  | UNDP Gender Marker: 2 |  |  |  |
| Atlas Project ID (formerly Award ID): 00096245 |  |  | Atlas Output ID (formerly Project ID): 00100222 |  |  |  |
| UNDP-GEF PIMS ID number: 5823 |  |  | GEF ID number: 9875 |  |  |  |
| Planned start date: 01 Jan 2020 (estimated) |  |  | Planned end date: 31 Dec 2024 (60 months) |  |  |  |
| PAC meeting date: May 2019 (TBD) |  |  |  |  |  |  |
| Brief project description: The project is part of an innovative programmatic approach to mainstream in-situ conservation of agrobiodiversity across China and reduce key threats to globally significant genetic resources for food and agriculture (GRFA). This project is designed to remove barriers currently restricting the protection and sustainable use of local agricultural genetic diversity in Hainan Province, contributing towards achievement of the long-term objective of strengthening conservation of Hainan’s globally important agrobiodiversity, through an enhanced provincial policy framework, strengthened institutional capacity, the establishment of innovative incentive mechanisms, and improved knowledge and understanding of the economic and environmental value of GRFA varieties. A core focus of the project is demonstration of innovative, participatory, partnership-based and incentivized approaches that support the achievement of long-term agrobiodiversity conservation and sustainable development outcomes. Participatory approaches will be implemented in three demonstration landscapes having a cumulative area of 13,787 hectares, with target GRFA varieties in the demonstration landscapes including Shanlan rice (Oryza sative), Wuzhishan pig (Sus scrofa) and Jiaji duck (Anas domestica). The project is expected to reach an estimated 5,522 direct beneficiaries, which include 5,412 residents in the demonstration landscapes, 50% of whom are women, and the inhabitants within two of the three landscapes are predominantly ethnic minority Li and Miao peoples. The direct beneficiaries also include 110 institutional staff members (30% women) who work in provincial, county and township agencies and have mandates associated with conservation and sustainable use of GRFA in Hainan. Involvement of women is a cornerstone of the project, as they play a traditional and increasingly broader contemporary role in the agricultural sector in China. The project aims to strengthen women’s capacities, increase their knowledge regarding agrobiodiversity conservation and expand their decision-making responsibilities among agricultural associations, enterprises and governmental agencies. Apart from gender mainstreaming, youth (14-35 years old) make up an estimated 20% of the direct beneficiaries, or approximately 1,100 people. Encouraging and maintaining youth engagement is an important element of sustaining traditional knowledge while also embracing modern approaches to farming and marketing GRFA varieties in Hainan Province. The theory of change for the project outlines the incremental reasoning of the GEF funds in catalyzing change towards achieving the mutually beneficial long-term impacts of improved diversity status of agrobiodiversity and enhanced well-being of local farmer households in Hainan Province, through implementing participatory approaches, ensuring committed governmental funding and viable market-based incentives, sustaining institutional and individual capacity building, establishing enduring partnerships and increasing knowledge-sharing and access to information. |  |  |  |  |  |  |
| Financing Plan |  |  |  |  |  |  |
| GEF Trust Fund |  |  |  |  |  | USD 1,509,633 |
| - Total Budget administered by UNDP |  |  |  |  |  | USD 1,509,633 |
| Parallel co-financing |  |  |  |  |  |  |
| Recipient Government (Hainan Department of Agriculture and Rural Affairs) |  |  |  |  |  | USD 9,920,000 |
| Private Sector (Hainan Tian Heng Agricultural Development Co. Ltd.) |  |  |  |  |  | USD 60,000 |
| Private Sector (Fomianshan Farmers Assoc. of Cultivation and Animal Husbandry in Baisha) |  |  |  |  |  | USD 150,000 |
| Private Sector (Hainan Chuanwei Muscovy Duck Breeding Co. Ltd.) |  |  |  |  |  | USD 30,000 |
| - Total co-financing |  |  |  |  |  | USD 10,160,000 |
| - Grand-Total Project Financing (1)+(2) |  |  |  |  |  | USD 11,669,633 |
| Signatures |  |  |  |  |  |  |
| Signature: International Financial Cooperation Department, Ministry of Finance |  | Agreed by Government |  |  | Date/Month/Year: |  |
| Signature: Deputy Director General, Hainan Department of Agriculture and Rural Affairs |  | Agreed by Implementing Partner |  |  | Date/Month/Year: |  |
| Signature: Devanand Ramiah, Deputy Country Director UNDP China |  | Agreed by UNDP |  |  | Date/Month/Year: |  |

# Table of Contents

I.	Table of Contents	3

II.	Development Challenge	6

III.	Strategy	19

IV.	Results and Partnerships	32

V.	Project Management	68

VI.	Project Results Framework	70

VII.	Monitoring and Evaluation (M&E) Plan	76

VIII.	Governance and Management Arrangements	80

IX.	Financial Planning and Management	85

X.	Total Budget and Work Plan	88

XI.	Legal Context	97

XII.	Risk Management	97

XIII.	Annexes	99

List of Tables:

Table 1: Breakdown of Capacity Development Scorecard baseline assessment	13

Table 2: Project contributions towards Sustainable Development Goals	16

Table 3: Project contributions towards Aichi targets	17

Table 4: Examples of non-market-based and market-based incentives	19

Table 5: Project contributions towards C-SAP program results	23

Table 6: Summary of the three demonstration agricultural landscapes	28

Table 7: Summary of baseline and incremental reasoning for Component 1	33

Table 8: Summary of baseline and incremental reasoning for Component 2	38

Table 9: Summary of baseline and incremental reasoning for Component 3	44

Table 10: Indicative breakdown of institutional capacity development beneficiaries	46

Table 11: Summary of baseline and incremental reasoning for Component 4	48

Table 12: Intersection of related initiatives with project outputs	54

Table 13: Project risks and proposed mitigation measures	56

Table 14: Stakeholder summary indicating mandates and roles in the project	60

Table 15: Project M&E Requirements and Budget	79

List of Figures:

Figure 1: Problem tree analysis	18

Figure 2: Project theory of change	22

Figure 3: Location map of agricultural demonstration landscapes	29

Figure 4: Vicinity map of Wuzhishan pig demonstration landscape	30

Figure 5: Vicinity map of Shanlan rice demonstration landscape	31

Figure 6: Vicinity map of Jiaji duck demonstration landscape	31

Figure 7: Project Organization Structure	81

List of Boxes:

Box 1: Definition of eco-agricultural landscape	28

Abbreviations and Acronyms:

| ABS | Access and Benefit-Sharing |
| --- | --- |
| AGRFA | Animal Genetic Resources for Food and Agriculture |
| AWP | Annual Work Plan |
| BoC | Bank of China |
| CAAS | Chinese Academy of Agricultural Sciences |
| CATAS | Chinese Academy of Tropical Agricultural Sciences |
| CNAS | China National Accreditation Service for Conformity Assessment |
| CNCA | Certification and Accreditation Administration of the People’s Republic of China |
| CNY | Chinese yuan |
| COFCC | China Organic Food Certification Center |
| CPC | Communist Party of China |
| C-SAP | PRC-GEF Partnership Program on Sustainable Agricultural Development |
| CTA | Chief Technical Advisor |
| CWR | Crop Wild Relatives |
| DARA | Provincial Department of Agriculture and Rural Affairs |
| FAO | Food and Agriculture Organization of the United Nations |
| FPIC | Free Prior and Informed Consent |
| GEF | Global Environment Facility |
| GI | Geographical Indication |
| GRFA | Genetic Resources for Food and Agriculture |
| ha | Hectare |
| HAAS | Hainan Academy of Sciences |
| IAS | Invasive Alien Species |
| IFOAM | International Federation of Organic Agriculture Movements |
| KAP | Knowledge, Attitudes and Practices |
| KBA | Key Biodiversity Area |
| KM | Knowledge Management |
| LGU | Local Government Unit |
| M&E | Monitoring and Evaluation |
| MARA | Ministry of Agriculture and Rural Affairs |
| MEE | Ministry of Ecology and Environment |
| MNR | Ministry of Natural Resources |
| MTR | Mid-term Review |
| NBSAP | National Biodiversity Strategy and Action Plan |
| NGO | Non-Governmental Organization |
| NPD | National Project Director |
| OFDC | Organic Food Development & Certification Center of China |
| PFD | Program Framework Document |
| PGRFA | Plant Genetic Resources for Food and Agriculture |
| PIMS | Project Information Management System |
| PIR | GEF Project Implementation Review |
| PMO | Project Management Office |
| POPP | Programme and Operations Policies and Procedures |
| PPG | Project Preparation Grant |
| PSC | Project Steering Committee |
| RTA | Regional Technical Advisor |
| SDG | Sustainable Development Goal |
| SES | Social and Environmental Standards (UNDP) |
| SESP | Social and Environmental Screening Procedure (UNDP) |
| STAP | GEF Scientific Technical Advisory Panel |
| TBD | To Be Determined |
| TE | Terminal Evaluation |
| UNDAF | United Nations Development Assistance Framework |
| UNDP | United Nations Development Programme |
| UNDP CO | United Nations Development Programme Country Office |
| USD | United States Dollar |

# Development Challenge

- As the only province harboring tropical ecosystems in the country, Hainan contains diverse and globally significant agrobiodiversity, with many locally distinct varieties of livestock, tropical fruit and rice. The agricultural sector of Hainan Province is facing some of the broader challenges being addressed across the People’s Republic of China (China). Agricultural production in China has impressively grown by nearly 5% annually since the late 1970s, helping to lift hundreds of millions of people out of poverty and reducing hunger. The productivity gains have been achieved largely through technological innovation coupled with economic and institutional reforms. With leading agricultural policies primarily focused on food security, there have been certain costs, including environmental ones,  associated with the transformations realized. The government of China has recently instituted policies and national development strategies on eco-civilization and green growth that address the increasing environmental pressures associated with economic growth. The National Sustainable Agricultural Development Plan adopted by the Ministry of Agriculture and Rural Affairs (MARA) in 2016 is one example of how these central government visions are being implemented. This plan calls for improving nitrogen fertilizer efficiency, increasing the application of water-saving irrigation technology, upgrading animal waste treatment, etc. Food safety has been an increasing concern as well, as many consumers begin to demand safer, healthier and greener food, and the population is becoming more aware of the impacts of agrochemicals. The intensification of agricultural production in China – as in many other parts of the world - have also resulted in increased genetic vulnerability, as certain varieties have become more uniform, making crops more susceptible to pest, pathogen and environmental hazards. The consequences associated with rapid development of large-scale agricultural production systems are also relevant in the livestock sector. The second national survey in China on animal genetic resources revealed significant threats to diversity, reporting that numbers of nearly 300 varieties, accounting for about half of all breeds, had declined since the first national survey was made.

- China is one of the eight global centers of crop genetic diversity identified by Vavilov in the 1920s as original regions for the domestication of plants.  Among the vast number of cultivated crops in China, there are 1,356 cultivated species and 2,172 wild relatives. Conservation of agrobiodiversity in China is an important part of country’s biodiversity strategy and the government has allocated significant resources for conservation of animal and plant genetic resources. There are formidable challenges to achieving these objectives in the face of continued economic development.

- Covering an area of 33,920 km2, Hainan is the southernmost and the only island province in China. Important GRFA varieties include, an upland rice variety well-suited to mountainous areas and very popular in Hainan, particularly among Li and Miao ethnic minority communities. The Li and Miao peoples have been farming highland and lowland areas in Hainan for many centuries and have an in-depth knowledge of the land, traditional species and farming practices suited to the range of conditions found in Hainan.

- The specific geographical and climatic conditions and farming practices in Hainan have also supported the development of a range of globally-important livestock varieties with unique characteristics and traits, and which are extremely popular in China. There are 16 endemic livestock species in Hainan, representing 10% of the local livestock varieties that exist in China. Many of these traditional GRFA varieties are being developed and marketed in the province, in response to burgeoning consumer demand across China for food that is culturally-preferred and healthful. An uneven policy focus, however, that has favored intensification of agricultural production is leading to a decline in traditional farming practices, lack of understanding of the value of conserving genetic resources for food and agriculture (GRFA) varieties and a loss of diversity. The GEF funding will provide incremental benefits towards conservation and sustainable use of GRFA in Hainan Province, applying integrated and participatory landscape approaches to conserving landraces, native varieties, strengthening the requisite incentivized enabling environment and increasing awareness and knowledge among farmers and decision-makers regarding the value of protecting traditional varieties of GRFA.

Threats and Root Causes:

There is general lack of understanding of the magnitude, root causes and consequences of the loss of agrobiodiversity resources, including traditional species and varieties and their wild relatives, and traditional agroecosystems. In Hainan Province, as well as in China as whole, rapid economic growth resulting in an increasing demand for land resources and structural changes to agricultural policies and systems have contributed to loss of agrobiodiversity.

- Modernization of the agricultural sector: The approach to agricultural development in China over the past couple of decades has been centered on the “three S’s”, i.e., security, sustainability and safety, with a particular emphasis on the first “s”, food security. Agricultural production was heavily intensified, with the introduction of modern technology, expanded irrigation systems and application of agro-chemicals. The result was the adoption of commercialized crops and livestock, displacing more traditional varieties. This situation is relevant in Hainan Province, where advances to cultivate new crop and livestock varieties are displacing traditional varieties and increasing genetic vulnerability. As genetic resources are eroded, potentially important means of adaptation, e.g. combating disease, are put at increased risk. There is increasing consumer demand for higher quality and safer food supplies, and the government has instituted policies on reducing environmental pressures through more sustainable agricultural practices.

- Economic development priorities: Until the late 20th century, Hainan’s economy was predominantly agricultural, with agricultural products accounting for most of the island’s exports. The central government encouraged rapid development of the island designating it as China’s largest special economic zone. Economic development, including urbanization, industrialization, commercialization of the agriculture sector, an expanding tourism sector, and a growing population have put significant pressure on Hainan’s natural resource base, through increasing demand for food, land and water. These development-related impacts have included widespread deforestation, reclamation of land for construction and farming, over-grazing of pastoral lands and ongoing expansion of the built environment. These mounting development pressures are reducing the habitats important to Hainan’s agrobiodiversity, resulting in a continual decline of the genetic diversity of plant and animal species in the province.

- Attrition of traditional production systems:  In many rural areas in China, including in Hainan Province,   migration to urban areas for alternative employment, mostly by men, has contributed to the decline of traditional, small-scale farming practices. The country report of the second national report on animal genetic resources indicates that the movement of people out of livestock rearing threatens the genetic resources associated with traditional types of livestock. Moreover, women and the elderly have assumed the primary burden of managing agricultural production systems in the countryside, and many of them have poor knowledge of local agrobiodiversity varieties and production techniques along with little incentive to cultivate or market them, and there is a lack of interest among the young generation.

- Fragmentation and degradation of habitats.  In a 2012 inventory of invasive alien species (IAS) in China, it was reported that 7.5% of the IAS reported in China over the period of 1990-2009 were first detected in Hainan Province.  The establishment of IAS is partly attributed to the abandonment of traditional farms, exposing areas of IAS growth and leading to fragmentation of agroecosystem landscapes. The spread of IAS is a particular threat to the island ecosystems of Hainan. There are 280 species of IAS recorded in Hainan, that combined threaten up to 40% of the province’s significant biological resources. The establishment of IAS results in a loss of habitat for crops, the introduction and spread of livestock diseases, and insect pests that damage crops and fruit orchards. For example, an invasion of the coconut hispid beetle Brontispa longissima resulted in the death of some 3.3 million coconut trees in 2015. Since its arrival in Hainan in 2003, the noxious weed Mikania micrantha has spread to spread to multiple counties and cities, with invasions threatening many endemic and rare fruit varieties including broad-leaved kiwifruit, pineapple, longan and lychee. These IAS have the potential to establish widely across agroecosystems and natural ecosystems, risking agricultural production and agrobiodiversity, and more broadly the conservation of Hainan’s globally significant biodiversity.

- Climate change.  Expected climate change impacts extend to the agricultural sector, including likely increases in volatility of agricultural yields, crop diseases and insect pests. Certain negative impacts have already manifested, e.g., in Hainan Province the areas with rice plant hoppers have increased fivefold over the period of 1991 to 2007.  Climate change is also placing increasing pressure on the livestock sector, especially on production systems that depend heavily on the conditions of local ecosystems. Traditional farming practices offer adaptation benefits that have not been fully recognized in local climate change strategies. For instance, many traditional varieties of crops have inherent resilience traits compared to modern varieties, such as enhanced drought and pest resistance. Moreover, small-scale mixed farming systems that harbor many locally adapted livestock breeds often possess characteristics that enable them to thrive in harsh conditions. These breeds, and other animal genetic resources, increase the available options for adapting farming systems to the effects of climate change.

- It is also important to note that agriculture is a significant contributor to human-induced climate change, including the largest contributor of non-CO2 greenhouse gas emissions. And, the total greenhouse gas emissions from food systems is estimated to be 19-29% of the total.  Traditional farming practices, which for example often involve diversified inter-cropping systems, have been shown to have lower greenhouse gas emissions as compared to conventional monoculture systems. The Chinese government has made commitments to promote low-emission development in agriculture, e.g., as one part of the Paris Climate Agreement. Recognizing the important role of traditional agricultural approaches will be an important element to low-emission development strategies.

More information on threats and root causes is contained in Annex K (Baseline Report on Policy, Governance and Knowledge Management) and Annex L (Baseline Report on Demonstration Landscapes).

Baseline Activities:

- There are a number of baseline activities that are relevant to the objectives of the project.

- At the national level, the central government has made substantial investments in the conservation of crop genetic diversity, including the Crop Germplasm Resources Protection program which has been implemented by MARA since 2001 with funding of approximately USD 4.5 million annually. The medium term and long-term objectives of this program were updated in the 13th 5-year plan in 2016, with a continued focus on collection, ex situ conservation, in situ conservation, evaluation and gene discovery of crop germplasm resources. A national priority list of crop wild relatives (CWR) is regularly evaluated and as of 2018, 205 protected sites for CWR had been established nationwide. The national priority list does not include agricultural varieties. There is limited funding from the central government for protected sites of CWR; approximately CNY 50,000 (approx. USD 7,250) is allocated annually for basic management of these sites. Among the 205 protected sites across China, 8 are situated in Hainan Province.

- China issued the 13th 5-year plan on the Conservation and Sustainable Utilization of Animal Genetic Resources (AGRFA) in 2016. The national priority list for conservation of AGRFA totals 159 breeds, including the Wuzhishan pig, one of the three GRFA varieties targeted by the project. In Hainan Province, there are no regular budgetary allocations for conservation of AGRFA, but there is some nonrecurrent, project-based funding.

- The Hainan Island Central Highlands Mountainous Region Tropical Rainforest Area is one of the 25 key ecological function zone in China. This national designation protects the original habitat of the tropical rainforest, tropical monsoon forest and the gene pool of its species. The central government has implemented an eco-compensation program for counties situated within key ecological function zones, as a form of subsidy for certain land use restrictions. The project will work with provincial and county officials in exploring ways to allocate some of the available eco-compensation funds for in-situ conservation of traditional GRFA varieties.

- The Department of Agriculture and Bureau of Tourism of Hainan are implementing initiatives through the Leisure Agriculture Development Fund including provincial agriculture and tourism activities with annual investment around USD 500,000. The development of “demonstration beautiful countryside villages” will involve a further USD 225,000 investment from the provincial DoA. These initiatives encourage and support farmers to engage in tourism-related activities and to showcase farming ecosystems and traditions – including traditional crops, livestock and products – as part of rural environment experience tours. The provincial government is also supporting the Farmers' Increasing Income in Central Hainan initiative. Although its core focus is on income generation, one of its objectives is to support ecosystem conservation and environmental sustainability. Further, the Fund for Returning Farmland to Forest provides eco-compensation to support restoration of agricultural areas.

- The Hainan Nature Reserve Construction Fund supports the in-situ conservation of ecosystems, species and genetic resources within nature reserves. It is led by the Department of Ecology and Environment, with initiatives also implemented by the DARA and the Forestry Bureau.

- The government of Hainan and the Chinese Ministry of Agricultural and Rural Affairs have supported extensive ex-situ conservation and the identification, evaluation and recording of animal and plant genetic resources important for food and agriculture throughout the province. Facilities have been established for conserving genetic resources such as the medium-term gene bank of crop genetic resources, field gene banks for tropical crops and preservation farms for livestock. Several research and higher education institutions take responsibilities, with these facilities built and maintained within campuses. These institutions include Chinese Academy of Tropical Agricultural Sciences, Hainan University and Hainan Provincial Academy of Agricultural Sciences, all of which are headquartered in Hainan. In addition, Chinese Academy of Agricultural Sciences, which are headquartered in Beijing, are partly involved in the activities

- The national and provincial governments are also investing in the control of IAS that threaten agrobiodiversity. Over 2016-2020, MARA and the Hainan government are investing USD 2.5 million through the project Prevention and Control of Alien invasive Species in building extension skills and training of farmers in the control of key IAS. Relevant IAS research and demonstration activities are underway by the Chinese Academy of Tropical Agricultural Resources. This includes the USD 2.5 million Research and Demonstration of the Key Technology of Biosafety Monitoring, Early Warning and Control in South Area project and USD 150,000 investment via projects on the impact of IAS on South sea ecosystems and the development of control technology research products.

- There are a number of highly qualified agricultural research/academic institutions in Hainan Province, and these institutes, universities and colleges play an important role in training professional institutional staff as well as farmers. While the focus of research/academic institutions mirrors the governmental policies, e.g., towards modernization and intensification of agricultural production, several universities offer training in agrobiodiversity conservation, including the Chinese Academy of Tropical Agricultural Sciences, the Hainan Academy of Agricultural Sciences and Hainan University.

- The agricultural institutional sector in the province has developed extensive training programs and facilities. The Science, Technology and Education Unit of DARA and the Hainan Academy of Agricultural Sciences are regularly organizing trainings for farmers. And, there is a training center based at the Chinese Academy of Tropical Sciences, which has led trainings of more than 10,000 farmers since 2014. These training courses mostly focus on techniques regarding horticulture and animal husbandry and on how to raise income, while very limited efforts have been made to capacitate and promote awareness on conservation and sustainable use of agrobiodiversity.

- In 2017, the provincial government issued the Implementation Plan for the Development of Agricultural Products Public Brands in Hainan Province, which aims to promote 500 original agricultural brands, cultivate and build 30 public brands of local agricultural products (including planting, breeding, agricultural products processing industries, etc.) and identify 50 famous brands of agricultural products in the province in the next 3-5 years. Allocating resources for operationalizing this implementation plan has not yet been worked out.  The outlook for this plan was strengthened in 2018, as part of the central government’s initiative on developing Hainan Province as Free Trade Area.

- GEF-financed interventions have also contributed to the baseline of this project. The UNDP-supported, GEF-financed project “Conservation and Sustainable Utilization of Wild Relatives of Crops” (UNDP PIMS 2277; GEF ID 1319) was implemented by MARA in partnership with provincial DARAs and research institutes from 2007 through 2013, working in 15 provinces in China, protecting 39 different species in 64 sites. China was also one of the countries that participated in the global GEF-financed project “Conservation and Sustainable Use of Crop Genetic Diversity to Control Pests and Diseases in support of Sustainable Agriculture” (GEF ID 4983). This project was implemented by the United Nations Environment Programme, with the Yunnan Agricultural University executing the activities in China and Bioversity International as the project coordinator. These projects have contributed towards raising awareness on the value of agrobiodiversity, strengthened capacities among national, provincial and local government stakeholders and introduced best international management practice.

- With funding from the German Federal Ministry for Economic Cooperation and Development (BMZ), the European Union (EU) and the Government of China, a project on “Sustainable management of agrobiodiversity in mountain regions in Southern China” was implemented between 2005 and 2011 by MARA and  the German federal enterprise Deutsche Gesellschaft für Internationale Zusammenarbeit (GIZ) GmbH. One of the three geographical target areas was in the Wuzhi Mountains in Hainan Province, which is also the location of one of the three demonstration landscapes for this project (Wuzhishan pig). One of the important lessons from the GIZ-implemented project was the importance of building capacity among farmers in the areas of value chain development, including identifying marketing strategies and strengthening negotiation skills. The project will build upon the achievements made by the GIZ project, for instance supporting provincial and county agencies in developing GRFA implementation frameworks and work plans, which will provide a sustainable framework for mainstreaming conservation and sustainable use of agrobiodiversity into the agricultural sector.

- In coordination with MARA, the Food and Agriculture Organization of the United Nations (FAO) has introduced the Globally Important Agricultural Heritage Systems (GIAHS) program in China. The objective of GIAHS to integrate the protection of traditional production approaches and genetic resources with local economic development and improvement in people’s living standards. As of 2017, there were 91 Nationally Important Agricultural Heritage Systems (NIAHS) in the country, including 2 in Hainan Province: Haikou Litchi Planting system in Yangshan Region and Shanlan Rice Culture – this rice variety is one of the three GRFA varieties targeted by the project.

More information on threats and root causes is contained in Annex K (Baseline Report on Policy, Governance and Knowledge Management).

Long-term vision and barriers towards achieving it:

- The long-term vision is for Hainan Province to follow a sustainable development path that includes the effective in-situ conservation and sustainable use of its unique and globally significant agrobiodiversity, mainstreaming conservation of diversity in agro-ecosystems among broader socioeconomic development priorities in the province. Four barriers are currently impeding the achievement of this vision:

Barrier 1: The absence of a cohesive policy and regulatory framework to support the in-situ conservation of agrobiodiversity and a lack of inter-sectoral coordination mechanisms

- There are a number of provincial and national governmental programs aimed at mainstreaming biodiversity conservation into agricultural production practices. In 2014, the provincial government issued two important strategies:  Management of Crop Germplasm Resources and the Biodiversity Strategy and Action Plan (2014-2030). And in 2017, the provincial government issued the Implementation Guidance on Agricultural Modernization Acceleration and Realization of a Comprehensive Well-off Society in Rural Areas. In this guidance, the government outlines a strategy on cultivating new professional farmers, to strengthen the protection and efficient use of agricultural resources, to strengthen the construction and management of nature reserves, to implement mandatory protection of important ecosystems and species resources, and to implement measures for conservation of endangered wild animals and plants. These plans and strategies reflect the recognition of the value of crop germplasm resources for sustainable development. However, there is limited strategic direction with respect to in-situ conservation and sustainable use of GRFA varieties. The guidance document, does outline the need to establish and improve ecological protection compensation mechanisms and ecological restoration mechanisms, and to carry out pilot projects of river basin and horizontal ecological compensation in the three major river basins of Nandujiang River, Wanquanhe River and Changhuajiang River, and to actively support farmers to develop leisure tourism cooperatives and create a number of national, provincial, city and county-level leisure agriculture and rural tourism demonstration parks. Specific incentives, however, are still lacking for farmers and public sector support structures and market-based mechanisms are absent to establish these incentives.

- Although the policy framework is lacking for in-situ conservation and sustainable uses of landraces, broader policy directions have been initiated by Chinese Central Government to “support Hainan Province to establish a Free Trade Area and to support the province in establishing  Free Trade Ports in certain paces” (Speech by President Xi Jinping, 13 April 2018). Additionally, in 2018, the provincial government has issued guidance on further promoting the development of civilized ecological villages in the province. The guidance presents the vision to accelerate development of ecological agriculture through vigorously developing tropical high-efficiency agriculture and brand agriculture, expanding the production of pollution-free agricultural products, green foods and organic foods, focusing on "one village one product, one village one specialty", developing characteristic ecological agriculture, promoting the construction of information infrastructure for civilized ecological villages, and actively guiding farmers to use network information to build Hainan's characteristic agricultural products e-commerce brand. The guidance also outlines the plans to accelerate the development of ecotourism by focusing on creating a number of rural tourism demonstration sites and promoting the upgrading and upgrading of civilized ecological villages according to the location characteristics, historical traditions and natural characteristics. It is clear that the provincial government is eager to take advantage of the opportunity supported by the central government and try to integrate construction of free trade area and promotion of tourism attraction partly by conservation of agrobiodiversity and sustainable agricultural development.

- Several provincial government agencies are responsible for the conservation and sustainable use of agro-biodiversity in Hainan Province. There are four major agencies:

- Department of Agriculture and Rural Affairs, which is responsible for in-situ and ex-situ conservation, use and commercialization of landraces of crops and livestock and wild species which are of potential importance for human foods;

- Department of Ecology and Environmental, which mainly focus on ecosystem-level issues for biodiversity conservation;

- Department of Natural Resources, which includes the Forestry Bureau, which is responsible for conservation of woodlands and under-forest crop plantation and livestock cultivation;

- Marine and Fishery Department, which concentrates on conservation of fish stocks and other marine resources.

- Moreover, several other provincial agencies play supporting roles in the conservation and sustainable use of agrobiodiversity while fulfilling their work. These other agencies include the Department of Science and Technology, Office of Poverty Alleviation, and Women’s Federation. Although there are several agencies contributing towards conservation and sustainable use of agro-biodiversity, there is limited intersectoral coordination, resulting in policies, regulations and strategies that are disjoined, inconsistent, or even contradictory to each other.  In areas where mandates and responsibilities overlap, absence of administration commonly occur. Further, governments at city, county and township levels are responsible for administration of conservation and sustainable use practices of agrobiodiversity, but they usually do not work within an integrated provincial framework.

- The government has realized the problems outlined above and has started to make changes. In late 2017, the provincial government issued an Implementation Guideline on Eco-compensation Mechanisms, which calls for strengthened organizational leadership and establishment of intersectoral coordination mechanism. The guideline further indicates that the Provincial Development and Reform Commission and the Provincial Department of Finance shall establish coordination mechanisms with relevant departments to strengthen coordination of ecological protection compensation across administrative regions, to develop and a monitoring and evaluation policy, and to solve problems in the implementation of ecological protection compensation mechanisms. Each department shall formulate specific implementation plans according to job responsibilities, assign responsibility for delegating tasks at different levels, strengthen departmental linkages, and jointly promote the smooth implementation of various tasks. This is a good beginning, but the current situation is far from integrated and coordinated manner in implementation of conservation and sustainable use of traditional crops and livestock endemic to Hainan.

More information on policy and governance shortcomings is contained in Annex K (Baseline Report on Policy, Governance and Knowledge Management).

Barrier 2: Uncoordinated and insufficient incentive mechanisms for farmers to engage in the conservation and sustainable use of local agricultural varieties, and the absence of public sector support structures and market-based mechanisms to establish these incentives

- Non-market incentives, such as ecological compensation programs in the province, are not oriented towards conservation and sustainable use of agrobiodiversity, e.g., direct payments for growing GRFA varieties or rewards for maintaining diversity. The ecological compensation funds extended to counties situated within the Central Highlands area are linked to protection of water resources, but there is no linkage to the role of agrobiodiversity conservation towards safeguarding the ecosystems and ecosystem services that influence the provisioning of sufficient quantity and quality of water resources. Moreover, many of the eco-compensation schemes are managed by central government and the provincial level agencies have limited decision-making authority. There are also limited incentive mechanisms that provide access to good quality seed or breeding stock of GRFA varieties. The provincial and local government level agricultural agencies provide certain subsidies to farmers; however, there are no specific programs that focus on adding value on farm to better enable implementation of traditional farming practices and cultivating and rearing GRFA varieties.

- There are some market incentives available, e.g., eco-labelling. While the eco-labelling programs include some traditional GRFA varieties, the focus is rather on food safety or cultural value of the products, rather than promoting conservation of varieties. Marketing capacities vary widely, with some very sophisticated enterprises having national level markets, while many small-scale farmers and agricultural associations and cooperatives lack marketing training and are unaware of supply chain dynamics, rendering them susceptible to below market pricing.

- While some producers and enterprises are aware of the potential value of agrobiodiversity, there are currently no support structures to encourage farmers – whether men or women – to conserve or farm traditional crops and livestock and farmers subsequently do not prioritize habitat protection or the use of these varieties. Production, processing and marketing of most agricultural varieties has been initiated by several enterprises in the province and the rapid uptake of social media in China has provided many entry points that were unavailable a few years ago. However, the linkages between policy makers and producers are not sufficiently efficient, production approaches and marketing strategies are not factoring the interconnectivity across agro-ecosystem landscapes and conservation outcomes are no being effectively considered.

- The provincial government has pledged to issue a Regulation of Ecological Compensation in Hainan Province before 2020. This timing is opportune for the C-SAP project to support the province in realizing these goals.

More information on incentive mechanisms is contained in Annex K (Baseline Report on Policy, Governance and Knowledge Management) and Annex L (Baseline Report on Demonstration Landscapes).

Barrier 3: Limited capacity for in-situ conservation and sustainable use of agrobiodiversity and a lack of mainstreamed institutional support structures

- With the lack of cohesive policy and regulatory frameworks, it is unsurprising that there is limited institutional capacity for in-situ conservation and sustainable use of agrobiodiversity. Agricultural sector policies, training and funding have been primarily focused on intensification of production, increasing efficiency in order meet food security demands. The agricultural institutional sector in Hainan is led by the DARA, supported by county and township agricultural bureaus and stations and complemented by other provincial and local government level agencies, as well as academic and research institutes. The baseline capacity of the Hainan agricultural institutional sector was assessed using the adapted UNDP Capacity Development Scorecard (see Annex M).  The baseline assessment concluded an overall capacity of 42% of the possible total, as outlined below in Table 1.

Table 1: Breakdown of Capacity Development Scorecard baseline assessment

| Strategic Area | Provincial Agricultural Institutional Sector |
| --- | --- |
| Area 1: Capacities for Engagement | 44% |
| Area 2: Capacities to Generate, Access and Use Information and Knowledge | 40% |
| Area 3: Capacities for Strategy, Policy and Legislation Development | 44% |
| Area 4: Capacities for Management Implementation | 50% |
| Area 5: Capacities to Monitor and Evaluate | 33% |
| Total Score: | 42% |

- There is room for improvement across each of the five strategic areas evaluated in the baseline scorecard assessment. For instance, capacities to monitor and evaluate are relatively low, as there are no consolidated agrobiodiversity programs with results-based performance frameworks in place, and evaluations of the management of the protected sites are irregularly conducted.

- Agricultural support and extension staff have limited experience in in-situ conservation and sustainable use of agrobiodiversity, and consequently limited knowledge and capacity to support these approaches. In-situ agrobiodiversity conservation is not currently included within the annual workplans and multi-year strategies of across the province and they have little access to tools and information.

- Local farmers and enterprises have recognized agricultural varieties and developed them into marketable products. However, efforts to date have been based on farmers’ and enterprises’ own initiatives with little support by government provided.

Barrier 4: Lack of awareness on the importance of crops and livestock and a lack of access to knowledge and information

- At the national level, the Ministry of Agriculture and Rural Affairs (MARA) and the Ministry of Science and Technology are the main governmental bodies responsible for development, promotion and administration of knowledge management. Under MARA, the Department of Science, Technology and Education is mainly responsible for knowledge management, and Department of Crop Production, Department of Livestock Production and Bureau of Seed management usually play minor roles in, but sometimes dominate, collection of information of germplasms and other agricultural biological resources. Under the Ministry of Science and Technology, the Department of Science and Technology for Rural Development is responsible for knowledge management related to conservation and sustainable use of agrobiodiversity, focusing on the basic science side with specific research goals. Moreover, the National Forestry and Grassland Administration and the State Administration of Traditional Chinese Medicine are involved in agrobiodiversity in some cases.

- At the provincial level, the Hainan Provincial Department of Agriculture is responsible for agrobiodiversity knowledge management, while the Hainan Provincial Department of Science and Technology and Forestry Department of Hainan Province play important roles in part of the work.  In each city and county, there is an agricultural bureau, and in some cities and counties, there is an animal husbandry bureau; also, at the township level, there are agricultural stations (for popularizing agricultural techniques). Regarding agrobiodiversity management, cross-sectoral systems are not well developed, and thus activities involving inter-department cooperation are very limited.

- Research institutions are also actively involved in knowledge management of agrobiodiversity issues. At the national level, the Chinese Academy of Agricultural Sciences (CAAS) and the Chinese Academy of Tropical Agricultural Sciences (CATAS) are the main institutions that develop and administer agrobiodiversity knowledge management systems. The technical aspects are delegated to the Institute of Crop Sciences of the Chinese Academy of Agricultural Sciences and the Crop Genetic Resources Institute of the Academy of Tropical Agricultural Sciences. At the provincial level, the Hainan Provincial Academy of Agricultural Sciences and the Hainan University are involved in knowledge management involving agrobiodiversity. Due to limited financial support, research activities are, however, limited. For example, information regarding collection or protection of germplasms and their background is not sufficient enough considering the rich resources in Hainan.

- Knowledge products are shared to farmers mainly through training. The Department of Science, Technology and Education of MARA is in charge of the development of training plans and administration at the national level. At the provincial level, the Unit of Science, Technology and Education under DARA and the Hainan Provincial Academy of Agricultural Sciences are responsible for organizing and running training courses. Financial departments at the city and county levels provide additional financial support for the trainings. Summing up, each city and county has budget of CNY 0.8-0.9 million (approx. USD 0.12-0.13 million) for training. There is a training center based at the Chinese Academy of Tropical Agricultural Sciences that is actively involved in delivering trainings. From 2014, the center has organized over 100 training sessions, with over 10,000 farmers trained in Hainan. However, training courses mostly focus on techniques regarding horticulture and animal husbandry and on how to raise income, while very limited efforts have been made to capacitate and promote awareness on conservation and sustainable use of agrobiodiversity.

- Knowledge products are shared with the public mostly through web-based databases. The National Platform of Plant Germplasms has made public information on over 470,000 germplasms for 340 crops (http://www.cgris.net/). The National Infrastructure of Domestic Animal Resources has an information sharing platform, but little specific information is provided on the website (http://www.cdad-is.org.cn/). The National Data Center for Rice provides germplasm information for rice species, including Shanlan rice, specifically. However, available information is not organized and is not straightforward for users. There is no integrative platform available for knowledge sharing either at the national or provincial level.

More information on institutional and individual capacity issues is included in Annex K (Baseline Report on Policy, Governance and Knowledge Management) and Annex M (Preliminary Capacity Development Needs Assessment, Baseline Scorecard and Indicative Capacity Development Plan).

Summary of Problem Analysis

- As outlined in the problem tree analysis illustrated in Figure 1, several direct threats are increasing the genetic vulnerability of agrobiodiversity. Unsustainable activities, such as intensification of agricultural crop production and indiscriminate cross-breeding of livestock. Conflicts in land use and water supply are increasing as a result of expansions in economic development.  Abandonment of small-scale farms as larger-scale production systems have been operationalized are leading to fragmentation of habitats of certain varieties and resulting in proliferation of IAS. Inherent adaptative benefits of traditional agricultural varieties and practices are also being lost, and the over-dependence on agrochemicals is affecting food safety and long-term soil fertility.

- These direct threats are a consequence of incoherent policies and a lack of strategic direction regarding in-situ conservation and sustainable use of traditional GRFA varieties. With agricultural professionals being trained in modern farming practices, there has been a loss of capacities to implement sustainable GRFA approaches. And the lack of government investment has resulted in inadequate infrastructure and supporting structures. The impacts of climate change are increasing the uncertainty associated with managing agricultural production, as well as exacerbating environmental pressures, including an increased incidence of pests and disease and disruptions in the water cycle.

- The lack of an effective enabling environment coupled with wide-ranging demographic shifts has led to an attrition of the traditional knowledge. The migration of mostly men from rural areas for alternative employment in cities has left women and the elderly to manage family agricultural plots. The labor pool is dwindling due to the general aging of farmers and the lack of interest among youth. Many farmers and agricultural enterprises have initiated production of GRFA products and offerings, but there is no coordinated effort to sustainable develop the resources, e.g., through implementing an integrated, landscape-based approach. Consumer demands and habitats are changing, e.g., for food that is certified safe and healthful, but the marketing approaches are typically not addressing protection of genetic resources and conservation outcomes are not factored into business plans.

National Policy Alignment:

- The project is aligned with several national policies, starting with 13th Five-Year Plan for Economic and Social Development of the People’s Republic of China (2016-2020) – the five-year plans the primary planning documents in China and are produced at the national, subnational and sector-specific levels. The agricultural development objectives in the national 13th Five-Year plan are heavily oriented towards modernization and increasing productivity, but there are specific targets regarding sustainable agriculture, including under Chapter 21, Improve Systems for Providing Support and Protection for Agriculture, which states: “With an emphasis on ensuring the supply of major agricultural products promoting increases in rural incomes and achieving sustainable agricultural development, we will improve policy support aimed at strengthening agriculture, benefitting farmers, and raising rural living standards and raise our level of support and protection of agriculture.” Moreover, there are complementary objectives among the agricultural modernization projects earmarked under the 13th Five-Year Plan, including the those under the Agricultural product quality and safety section of the plan: “Make a serious push to reduce pesticide and chemical fertilizer use in the production of agricultural products” and “Develop pollution-free agricultural products, green foodstuffs, organic agricultural products, and agricultural products using geographical indications”.

- There are two additional five-year plans that are relevant to the project: the Agriculture Modernization Plan (2016-2020), which in Chapter 3 focuses on “demonstration of standardizing special agricultural products, extending production of famous and high-quality agricultural products and related techniques, and development of geographical indication products”; and the Development Plan on Science and Technology of Agriculture (2016-2020), which in Chapter 3 calls for “strengthening collection, conservation and utilization of germplasm resources and their wild relatives, establishing gene pools, preservation facilities and conservation sites for important germplasm resources.”

- The project is consistent with the objectives of three longer-term national strategic frameworks, including: the National Plan for Sustainable Development of Agriculture (2015-2030), specifically Chapter 3 (Biological Conservation), which outlines priorities for “strengthening conservation of germplasm resources and their wild relatives and monitoring important germplasm resources to reduce the speed of disappearing biodiversity.”; the Crop Germplasm Resources Conservation Plan (2015-2030), specifically Action 1 in Chapter 5 which focuses on “collection of all kinds of germplasm resources in China, emphasizing conservation of local varieties of crops and their related traditional knowledge.”; and the National Biodiversity Strategy and Action Plan (NBSAP) (2011-2030), particularly Priority Area 2, Action 4, “incorporating biodiversity conservation into sectoral and regional planning and programmes”, and Action 5, “ ensure sustainable use of biodiversity”; Priority Area 3, Action 7, “carry out baseline surveys on biological resources and ecosystems”, and Action 8, “survey and catalogue genetic resources and related traditional knowledge”; Priority Area 10, Action 29, “establish mechanisms for public participation”, and Action 10, “promote the establishment of biodiversity conservation partnerships”.

- With regard to the United Nations Development Assistance Framework (UNDAF) for the People’s Republic of China for 2016-2020, the project is most closely aligned with Priority Area 2, “Improved and Sustainable Environment”, specifically Outcome 2, “More people enjoy a cleaner, healthier and safer environment as a result of improved environmental protection and sustainable green growth”. As part of this priority area, the UN plans on providing technical assistance and capacity building support for China's ecosystem protection and restoration, and the sustainable development of mountainous and forest regions, to slow down ecological degradation, reduce relevant poverty incidence, promote green growth, and strengthen community resilience through promotion of sustainable environmental  practices and use of natural resources.

- The project is also relevant to Priority 1, “Poverty Reduction and Equitable Development” of the 2016-2020 UNDAF, specifically Outcome 1, “More people, particularly the vulnerable and disadvantaged, enjoy improved living conditions and increased opportunities for economic, social and cultural development.” Ensuring a sustainable agriculture sector is an important part of realizing poverty reduction and equitable development, addressing skills development in rural areas and ensuring food security.

Relevance to Sustainable Development Goals (SDGs):

- The project is relevant with respect to several of the sustainable development goals (SDGs), most notably SDG 2, “End hunger, achieve food security and improved nutrition and promote sustainable agriculture”; and SDG 15, “Protect, restore and promote sustainable use of terrestrial ecosystems, sustainably manage forests, combat desertification, and halt and reverse land degradation and halt biodiversity loss”.  Specific project contributions that are consistent these two SDG’s are described below in Table 2:

Table 2: Project contributions towards Sustainable Development Goals

| SDG Target and Indicator: | Project Contribution: |
| --- | --- |
| Target 2.3: By 2030, double the agricultural productivity and incomes of small-scale food producers, in particular women, indigenous peoples, family farmers, pastoralists and fishers, including through secure and equal access to land, other productive resources and inputs, knowledge, financial services, markets and opportunities for value addition and non-farm employment. Indicator 2.3.2: Average income of small-scale food producers, by sex and indigenous status. | Direct project beneficiaries: 5,522, including 2,739 women, delivering sustainable livelihood benefits through strengthened capacity, increased knowledge and awareness of agrobiodiversity conservation. Increase in the number of farmer households engaged in the three target GRFA varieties: 30. |
| Target 2.4: By 2030, ensure sustainable food production systems and implement resilient agricultural practices that increase productivity and production, that help maintain ecosystems, that strengthen capacity for adaptation to climate change, extreme weather, drought, flooding and other disasters and that progressively improve land and soil quality. Indicator 2.4.1: Proportion of agricultural area under productive and sustainable agriculture | 13,787 ha of landscapes under improved practices, managed under a sustainable use and conservation of agrobiodiversity regime. |
| Target 2.5: By 2020, maintain the genetic diversity of seeds, cultivated plants and farmed and domesticated animals and their related wild species, including through soundly managed and diversified seed and plant banks at the national, regional and international levels, and promote access to and fair and equitable sharing of benefits arising from the utilization of genetic resources and associated traditional knowledge, as internationally agreed. Indicator 2.5.1: Number of plant and animal genetic resources for food and agriculture secured in either medium or long-term conservation facilities | Enhanced germplasm protection of agrobiodiversity varieties through establishment of one community seed bank established for Shanlan rice, and regular livestock competitions with traditional knowledge organized for Wuzhishan pig and Jiaji duck. |
| Target 15.6: Promote fair and equitable sharing of the benefits arising from the utilization of genetic resources and promote appropriate access to such resources, as internationally agreed Indicator 15.6.1: Number of countries that have adopted legislative, administrative and policy frameworks to ensure fair and equitable sharing of benefits | One provincial GRFA implementation framework and three county level GRFA implementation frameworks provide strengthened enabling environment for incentivized conservation and sustainable use of agrobiodiversity. |
| Indicator 15.A: Mobilize and significantly increase financial resources from all sources to conserve and sustainably use biodiversity and ecosystems Indicator 15.A.1: Official development assistance and public expenditure on conservation and sustainable use of biodiversity and ecosystems | CNY 1 million (approx. USD 150,000) of eco-compensation funds allocated towards conservation and sustainable use of agrobiodiversity. |

- The project will also make secondary contributions towards SDG Goal 1 (End poverty in all its forms everywhere); SDG Goal 5 (Achieve gender equality and empower all women and girls); SDG Goal 10 (Reduce inequality within and among countries); SDG Goal 13 (Take urgent action to combat climate change and its impacts); and SDG Goal 17 (Revitalize the global partnership for sustainable development).

Contributions towards Aichi Targets

- The project will make contributions towards several of the Aichi targets, primarily Target 13 to maintain the genetic diversity of cultivated plants and animals and their wild relatives, as well as Target 1 (awareness), Target 7 (sustainable agriculture), Target 14 (benefits from biodiversity and ecosystem services) and Target 18 (traditional ecological knowledge), as outlined below in Table 3.

Table 3: Project contributions towards Aichi targets

| Aichi Target |  | Project Contribution |
| --- | --- | --- |
| Strategic Goal A: Address the underlying causes of biodiversity loss by mainstreaming biodiversity across government and society |  |  |
|  | Target 1: By 2020, at the latest, people are aware of the values of biodiversity and the steps they can take to conserve and use it sustainably. | 5,522 direct beneficiaries, having increased knowledge and awareness of the value of agrobiodiversity management. |
| Strategic Goal B: Reduce the direct pressures on biodiversity and promote sustainable use |  |  |
|  | Target 7: By 2020 areas under agriculture, aquaculture and forestry are managed sustainably, ensuring conservation of biodiversity. | 13,787 ha of agricultural landscapes managed sustainably, ensuring conservation of agrobiodiversity resources. |
| Strategic Goal C: To improve the status of biodiversity by safeguarding ecosystems, species and genetic diversity |  |  |
|  | Target 13: By 2020, the genetic diversity of cultivated plants and farmed and domesticated animals and of wild relatives, including other socio-economically as well as culturally valuable species, is maintained, and strategies have been developed and implemented for minimizing genetic erosion and safeguarding their genetic diversity. | Provincial agrobiodiversity strategy and action plan developed, and conservation plans for three GRFA varieties implemented across three demonstration landscapes. Enhanced protection of germplasm resources, including establishment of one community seed bank and regular livestock competitions. |
| Strategic Goal D: Enhance the benefits to all from biodiversity and ecosystem services |  |  |
|  | Target 14: By 2020, ecosystems that provide essential services, including services related to water, and contribute to health, livelihoods and well-being, are restored and safeguarded, taking into account the needs of women, indigenous and local communities, and the poor and vulnerable. | Sustainable livelihoods enhanced within three demonstration landscapes, with 5,522 direct beneficiaries (50% women), including an increase of 30 farmer households engaged in conservation and sustainable use of GRFA varieties. |
| Strategic Goal E: Enhance implementation through participatory planning, knowledge management and capacity building |  |  |
|  | Target 18: By 2020, the traditional knowledge, innovations and practices of indigenous and local communities relevant for the conservation and sustainable use of biodiversity, and their customary use of biological resources, are respected, subject to national legislation and relevant international obligations, and fully integrated and reflected in the implementation of the Convention with the full and effective participation of indigenous and local communities, at all relevant levels. | Provincial agrobiodiversity strategy and action plan promoting traditional knowledge, and traditional knowledge integrated into three GRFA conservation and sustainable use plans implemented across three demonstration landscapes. |

Figure 1: Problem tree analysis

# Strategy

- The Project Objective is to “Strengthen the in-situ conservation and sustainable use of globally significant agrobiodiversity in Hainan through the development of incentive mechanisms for farmers to sustain populations of endemic crops and livestock, the establishment of a supportive enabling environment and strengthened institutional capacity”.

- The project strategy as the GEF alternative aimed at removing the barriers outlined above is broken down into the following four integrated components and described in the theory of change diagram in Figure 2:

Component 1:	Strengthened provincial framework

Component 2: 	Demonstration of sustainable incentive mechanisms for in-situ conservation and use of agrobiodiversity

Component 3: 	Mainstreaming and institutional capacity strengthening

Component 4: 	Knowledge management and monitoring & evaluation

- Component 1 is designed to strengthen governance arrangements and policy, strategy and regulatory frameworks for  in-situ conservation and sustainable use of GRFA in Hainan Province. Facilitating inter-sectoral and cross-sectoral coordination structures is an important aspect towards developing an enabling environment. A provincial GRFA coordination committee will established, led by the Hainan DARA and having cross-sectoral representation by other provincial departments including Ecology and Environment, Natural Resources, Water Resources, Officer for Poverty Alleviation, Development and Reform Commission and All Women’s Federation, as well as academic/research sector experts and representatives from relevant agricultural trade associations. The GRFA coordination committee will support the implementation of the project activities, provide advisory support to the project steering committee and guide the development of incentivized polices and regulations (Output 1.1). The project will support an exchange of best practices with the national level GRFA coordination mechanisms led by MARA, and the provincial level GRFA coordination committee will provide inter-sectoral oversight to the three county level coordination committees in the counties where the demonstration landscapes under Component 2 are located.

- Informed by the results of a gap analysis, an agrobiodiversity strategy and action plan will be developed in Component 1 to provide stakeholders with a framework for systematically mainstreaming GRFA conservation priorities into provincial planning processes. The strategy and action plan will outline a framework on incentivizing agrobiodiversity conservation through both non-market-based and market-based incentive mechanisms and discontinuing possible negative incentives that are currently in place; some examples are listed below in Table 4. Moreover, GRFA implementation frameworks will be formulated and instituted at the provincial and local levels to better enable uptake of incentivized approaches (Output 1.2). Guidelines for appropriating eco-compensation funds and other non-market incentive mechanisms for conservation and sustainable use of agrobiodiversity will be developed (Output 1.3) and landscape level demonstrations implemented in Component 2.

Table 4: Examples of non-market-based and market-based incentives

| Types of incentives | Positive incentive (measures designed to encourage beneficial activities: economic, legal or institutional) | Negative incentive (measures that induce unstainable behavior and reduce agrobiodiversity) |
| --- | --- | --- |
| Direct incentives (non-market) (directly encourages conservation and sustainable use of agrobiodiversity) | - Direct payments for growing GRFA varieties (eco-compensation); - Rewards for maintaining diversity (eco-compensation); - Improved access to good quality seed and breeding stock of GRFA varieties (such as seed banks, livestock competitions, trade fairs, etc.); - Access to credit for growing GRFA varieties; - Adding value on farm (improved soil fertility, farming facility construction, improved approaches/practices); | - Non-acceptance of GRFA varieties by buyers; - Processing constraints because of heterogeneity and small volumes/quantities; - Illegal status of marketing seeds and raising stock of non-registered varieties; |
| Indirect incentive (market) (induces changes in the policy, socioeconomical or agroecological environment which affects conservation and use of agrobiodiversity) | - Legislation that allows farmers to exchange and market seeds and breeding stock of GRFA varieties; - Development of supply chains (e.g., processing, eco-labelling, collective marketing); - Development of niche markets; - Agro-ecotourism; - Cultural preferences/branding; - Participatory learning; - Access to information; - Recognition of traditional knowledge; - Development of e-commerce in rural areas | - Subsidies for modern varieties; - Extension messages promoting mono-culture; - Promotion of export/cash crops at the expense of food crops; - Access to credit linked to use of modern varieties; - Fewer farmers having traditional knowledge |

- As outlined in the theory of change analysis shown in Figure 2, the policy reforms initiated through the project will lead to an intermediate state involving implementation of priority actions according to the framework developed in the provincial agrobiodiversity strategy and action plan, through an adaptive management approach, making adjustments under changing circumstances. One of the key impact drivers advancing the process towards this intermediate state and ultimately fulfilling long-term biodiversity and sustainable livelihood outcomes is enduring advocacy by governmental and non-governmental change agents. Achieving this intermediate state depends on the assumption that governmental funding for non-market incentive mechanisms will be allocated.

- The funds allocated under Component 2 make up nearly 50% of the total GEF implementation grant. The component will add value through characterizing local GRFA resources in three demonstration landscapes; the three target GRFA varieties are Shanlan rice (Oryza sative), Wuzhishan pig (Sus scrofa) and Jiaji duck (Anas domestica). GRFA conservation and sustainable use plans will be developed based on the results of participatory GRFA landscape assessments (Output 2.1) and then implemented to demonstrate participatory approaches in improving local resources (Output 2.2), e.g., through establishing a community seed bank for Shanlan rice, arranging regular livestock competitions for Wuzhishan pig and Jiaji duck, and strengthening marketing capacities and facilitating public-private and private-private partnerships among local stakeholders (Outputs 2.3 and 2.4) in establishing viable GRFA products and other offerings, such as agro-ecotourism initiatives, branding and eco-labelling, etc.

- According to the project theory of change, Outcome 2 will facilitate an intermediate state of traditional GRFA varieties continuing to gain popularity and GRFA products and offerings are competitive in price and viable under dynamic market conditions characterized by increasing consumer demand and efficient market incentives. This intermediate state will be achieved through wider adoption of the demonstrated GRFA approaches, facilitated through sustained advocacy by enabling stakeholders (impact driver). Two important assumptions associated with achievement of the intermediate state is sufficient buy-in among farmers and agricultural enterprises, and content by local farmers to share traditional knowledge.

- Component 3 includes strengthening institutional capacity, which is an important aspect of an enabling environment for mainstreaming and upscaling GRFA approaches in province. A total of 110 institutional staff members are targeted for capacity development, representing several provincial agencies, county and township offices and research/academic institutions. The project strategy includes a multifaceted approach to capacity building, including formal course-based training, learning-by-doing interventions and domestic and international knowledge transfer exchanges (Output 3.1). Integrating incentivized GRFA approaches into provincial and county level work programs will help facilitate upscaling (Output 3.2), and GEF resources will help initiate replication in at least two landscapes beyond the areas focused on in Component 2 (Output 3.3).

- The replication strategy and upscaling strategy instituted in Component 3 will lead to broader update across the province (intermediate state), according to the project theory of change. The main impact driver associated with the pathway leading to this intermediate state is effective operation of collaborative mechanisms, including landscape level partnerships involving farmers, local government units and agricultural enterprises, as well as governmental level coordination committees. Broader replication of the GRFA approaches depends on increasing demand for GRFA products and offerings, with competitive returns to farmers and enterprises (assumptions). Another important assumption is that the institutional capacity built is not lost due to staff departures.

- Improving access to information and raising awareness are among the expected results under Component 4.  The added value of a programmatic approach includes sharing best practices and lessons learned through collaborative monitoring & evaluation activities (Output 4.1). A knowledge management strategy and action plan will be developed for the project based on the results of a baseline knowledge, attitudes and practices (KAP) survey carried out at project inception. Awareness-raising and advocacy campaigns will be carried out, with a particular emphasis on women and youth stakeholders (Output 4.2). GEF funds are also allocated for strengthening a provincial GRFA database, expanding the functions of the system and broadening participation (Output 4.3).

- Changing knowledge, attitudes and practices will require time. The actions completed under Component 4 will form a strong foundation that can be built upon after GEF funding ceases. Continued improvement of GRFA approaches will be promoted by newer knowledge acquired by the scientific community, farmers or enterprises (intermediate state). This intermediate state will be driven by active participation in knowledge-sharing (impact driver) and is based on the assumptions that funding for the GRFA database and other knowledge systems will be maintained and that the academic/research sector efficiently transfers theoretical knowledge into practical field applications.

Figure 2: Project theory of change

Program Contributions:

- This project is one of five child projects under the GEF-financed C-SAP Program (GEF Program ID 9403). This programmatic approach will support coordinated knowledge management and cross-fertilization between individual child projects, coordinated by the MARA Program Coordination Office, supported by the M&E/Coordination Officer, the KM/Communications Officer and the Program Steering Committee. The project components will contribute towards the C-SAP programmatic outcomes as shown below in Table 5. Program coordination is further detailed in Section V and the project document for the national project on invasive alien species (IAS) (UNDP PIMS 5821).

Table 5: Project contributions towards C-SAP program results

| C-SAP Program Components / outcomes / indicators | C-SAP3 Project contributions to C-SAP program level results. Components / outcomes / indicators |
| --- | --- |
| Program Objective: Support the implementation of the Sustainable Development Goals and China’s National Plan for Sustainable Development of Agriculture (2015-2030) by a) piloting and scaling up effective policy and investment measures to mainstream in-situ conservation and sustainable use of globally important genetic resources for food and agriculture (GRFA), b) improving the prevention, control and management of invasive alien species (IAS), c) conserving and enhancing carbon stock and promoting evidence-based and climate-smart conservation of grassland ecosystems, and d) collaborative innovation in climate change and biodiversity from the aspects of policy, mechanism, knowledge sharing and partnerships |  |
| C-SAP Component 1: Strengthened enabling environment | C-SAP3 Component 1: Strengthened provincial framework C-SAP3 Outcome 1: Provincial policy, strategy and regulatory framework for in-situ conservation and sustainable use of agrobiodiversity enhanced |
| Outcome 1.1: Strengthened policy, regulatory and strategic frameworks and cross-sectoral coordination at national and provincial levels support a) in-situ conservation and sustainable use of GRFA, and b) the control of threats posed by IAS to sustainable agricultural development, and c) evidence-based and climate-smart conservation and management of grassland ecosystems Indicator 1.1: Development of a comprehensive framework of policies, regulations and strategies across sectors which have addressed barriers and gaps identified in baseline assessments | Indicator 1.1: Strengthened policy, regulatory and strategic frameworks at provincial level support in-situ conservation and sustainable use of GRFA, as indicated by (a) a provincial Agrobiodiversity Strategy and Action Plan, a complement to the provincial Biodiversity Strategy and Action Plan; (b) provincial GRFA implementation framework; and (c) county GRFA implementation frameworks for Baisha County, Qiongzhong County and Qionghai City End target: (a) Approved by DARA; (b) Approved by DARA and submitted to the Provincial Government for approval; (c) Approved by county agriculture bureaus |
| Outcome 1.2: Strengthened cross-sectoral coordination results in more effective approaches for the conservation and sustainable use of GRFA and grasslands, including for improved control and management of IAS threats Indicator 1.2: i) The establishment of a strategic plan and coordination mechanism for IAS prevention, control and management at national and provincial level, leading to improved response times and increased engagement in IAS management by relevant sectors. ii) The establishment of inter-sectoral coordination mechanisms for the in-situ conservation and sustainable use of GRFA in target provinces and their use by a range of sectoral agencies to support in-situ agrobiodiversity conservation. iii) The establishment of a cross-sectoral coordination mechanism for the management and sustainable use of grassland ecosystems and its use by a range of sectoral agencies to improve management efficiency, increasing the resilience of grassland ecosystems to climate change | Indicator 1.2: Strengthened intersectoral and cross-sectoral cooperation leads to more effective approaches for the conservation and sustainable use of GRFA, including improved control and management of IAS threats, as indicated by number of coordination mechanisms at (a) provincial level and (b) county level. End target: (a) One provincial coordination committee, with charter approved by DARA (b) Three county coordination committees, with charters approved by county agriculture bureaus |
| Outcome 1.3: Increased government financing for in-situ conservation and sustainable use of GRFA and grassland ecosystem, including for the prevention, control and management of IAS threats Indicator 1.3: National and provincial budget allocations | Indicator 1.3: Prioritized appropriation of government financing, as indicated by increased allocation of eco-compensation funds in the Central Highlands area for sustainable use and conservation of GRFA End target: CNY 1 million of eco-compensation funds allocated for agrobiodiversity conservation in the final year of project implementation or earmarked for the year following project closure |
| C-SAP Component 2: Incentive mechanisms | C-SAP3 Component 2: Demonstration of sustainable incentive mechanisms for in-situ conservation and use of agrobiodiversity C-SAP3 Outcome 2: Market- and non-market-based incentive mechanisms established and demonstrated for in-situ conservation and sustainable use of agrobiodiversity, enabling long-term livelihood benefits for local farmers |
| Outcome 2.1: Sustainable conservation and management approaches established which improve the in-situ sustainable use and conservation of GRFA and deliver social, financial and livelihood benefits to farmers in parallel Indicator 2.1: i) 15% increase in income of farming and herder households in target agricultural and pastoral landscapes attributed to their engagement in conservation and use of GRFA and/or green livestock development and sustainable grassland management. ii) The establishment of at least three successful business partnerships between farmers and commercial marketing outlets in five target provinces which are based on the production, processing and sale of agrobiodiversity products. iii) Eco-compensation schemes established and providing financial and social recognition to farmers and herders of their contribution to the conservation of GRFA and the sustainable management of grassland ecosystems. iv) 40% increase in the coverage of traditional varieties (in hectares, or number per hectare) in target agricultural landscapes | Indicator Obj-1: Area of landscapes under participatory conservation and sustainable use of agrobiodiversity (GEF Core Sub-Indicator 4.3) (UNDP IRRF 1.4.1: Natural resources that are managed under a sustainable use, conservation, access and benefit-sharing regime: (g) other) End target: 13,787 ha |
|  | Indicator 2.1: Sustainable livelihood benefits to farmers generated through incentivized in-situ conservation and sustainable use of GRFA, as indicated by the number of farmer households engaged in GRFA varieties in the demonstration landscapes for (a) Wuzhishan pig, (b) Shanlan rice and (c) Jiaji duck End target: Additional 20 households engaged in Wuzhishan pig, 5 households engaged in Shanlan rice and 5 households engaged in Jiaji duck |
|  | Indicator 2.2: Expanded non-market incentives through improved access to genetic resources, as indicated by (a) number of community seed banks established for Shanlan rice; (b) number of annual livestock competitions for Wuzhishan pig mainstreamed into local extension offerings; (c) number of annual livestock competitions for Jiaji duck mainstreamed into local extension offerings End target: (a) 1 (b) 1 (c) 1 |
|  | Indicator 2.3: Expanded GRFA market incentives and strengthened marketing capacities, as indicated by (a) number of new product certification marketing tools for the target GRFA varieties; and (b) number of new partnerships established End target: (a) 2 (b) 2 |
| Outcome 2.2: Effective participatory approaches for the prevention, control and management of IAS impacts on GRFA developed and tested in target agricultural landscapes Indicator 2.2: i) The involvement of at least 40% of farmers and all relevant extension agencies in the identification, monitoring and removal of IAS and in habitat restoration at target landscapes. ii) No new IAS establishments, at least 60% reduction in the area affected by IAS and demonstrated IAS threat reduction to target GRFA in target agricultural landscapes (indicators to be developed for impact of IAS threat reduction on target GRFA) | No contributions by the C-SAP3 project. |
| Outcome 2.3: Community-based grassland management approach (including sound biodiversity and IAS management practices) and evidence-based payments for ecosystem services (PES) policy scheme with creditable monitoring, reporting and verification (MRV) system tested in selected provinces and ready for national scale up | No contributions by the C-SAP3 project. |
| C-SAP Component 3: Institutional capacity strengthening | C-SAP3 Component 3: Mainstreaming and capacity strengthening C-SAP3 Outcome 3: Demonstrated approaches mainstreamed and capacities strengthened to facilitate upscaling of incentivized conservation and sustainable use of GRFA |
| Outcome 3.1: : Increased effectiveness of participatory approaches for the conservation and sustainable use of GRFA and sustainable management of grassland ecosystems Indicator 3.1: i) At least 40% of households led by women and 20% of teenagers actively engaged in the conservation and sustainable use of GRFA in target agricultural landscapes, and at least 50% of households led by women actively engaged in climate-smart grassland management in target pastoral landscapes. ii) Increase in the management and technical capacity of stakeholders related to conservation and sustainable use of GRFA and sustainable management of grassland ecosystems. iii) Effective prevention, early detection, rapid response and management of IAS in agroecosystems (measured by relevant items of the GEF IAS Tracking Tool) | Indicator Obj-2: Number of direct project beneficiaries, measured based on: (a) Cumulative total of the following: (b) Number of people living in the communities within the demonstration landscapes (50% women) (c) Number of institutional staff members having strengthened capacities with regard to in-situ conservation and sustainable use of agrobiodiversity (30% women) (GEF Core Indicator 11: Number of direct beneficiaries disaggregated by gender as a co-benefit of GEF investment) End target: (a) 5,522 (2,739 women; 2,783 men) (b) 5,412 (2,706 women; 2,706 men) (c) 110 (33 women; 77 men) |
|  | Indicator 3.3: Level of mainstreaming incentive-based approaches of in-situ conservation and sustainable use of GRFA, as indicated by having incentivized approaches for in-situ conservation and sustainable use of GRFA included in the work program for DARA End target: Approved work program included in the 14th 5-year plan for DARA |
| Outcome 3.2: Strengthened institutional capacity of relevant public sector agencies within target sites, and of lead national institutions, for the in-situ conservation and sustainable use of GRFA, for the management of IAS impacts on agrobiodiversity, and for evidence-based and climate-smart grassland management practices Indicator 3.2: i) Capacity assessments at the beginning, middle and end of the program; ii) Counties within target agricultural landscapes have established IAS management institutions | Indicator 3.1: Strengthened institutional capacity of the Provincial Department of Agriculture and Rural Affairs (DARA) for in the in-situ conservation and sustainable use of GRFA, as indicated by capacity development scorecard End Target: 67% |
|  | Indicator 3.2: Degree of upscaling of participatory approaches for the conservation and sustainable use of GRFA, as indicated by (a) number of participatory landscape assessments completed beyond the demonstration landscapes using the best practice guideline developed in Component 2; (b) hectares under in-situ conservation and sustainable use of GRFA replicated beyond the demonstration landscapes (excluding protected areas); (c) number of additional GRFA varieties having eco-certification in the province End target: (a) 2 (b) 2,200 ha (c) 3 |
| C-SAP Component 4: Program Coordination, Knowledge Management | C-SAP3 Component 4: Knowledge management and monitoring & evaluation C-SAP3 Outcome 4: Knowledge, attitudes and practices, and knowledge management structures enhanced to broaden participation in the conservation and sustainable use of GRFA |
| Outcome 4.1: Improved understanding among decision makers, the general public and key stakeholder groups on the value of GRFA and importance of in-situ conservation, and evidence-based policy making for climate-smart grassland management, and increased access by all groups to information Indicator 4.1: Knowledge, Attitude and Practices surveys to be conducted at beginning, middle and end of projects | Indicator 4.1: Improved understanding among key stakeholder groups on the value of GRFA and the importance of in-situ conservation, as indicated by results of knowledge, attitude and practices (KAP) surveys (disaggregated by women and youth), among the following stakeholder groups: (a) Provincial governmental stakeholders; (b) Local governmental stakeholders; (c) Farmers; (d) Agricultural associations and enterprises End target (provisional): (a) Increase of at least 20% percentage points; (b) Increase of at least 30% percentage points; (c) Increase of at least 50% percentage points; (d) Increase of at least 20% percentage points |
| Outcome 4.2: Monitoring and evaluation demonstrates efficient use of program funds, rationalization of national, provincial and local level inputs, and sharing of information, resources and expertise between projects, along with on-going exchange of lessons and best practices | Indicator 4.2: Adoption of participatory knowledge management systems, as indicated by (a) the number of GRFA varieties described on the provincial agrobiodiversity database, and (b) number of lessons learned, case studies and other posts submitted on the C-SAP program knowledge and communication platform End target: (a) 6 (b) 20 |
| Outcome 4.3: Effective coordination of program activities across national and provincial stakeholders and GEF agencies | Same as for Indicator 4.2. |

Innovativeness:

- Innovativeness is integrated throughout this project. At the policy level, the project will facilitate a transformation of regulatory frameworks, providing a more incentivized enabling environment for participation in conservation and sustainable use of agrobiodiversity. The project will establish inter-sectoral and cross-sectoral coordination mechanisms within the government sector, and also develop multi-stakeholder alliances involving provincial and local governments, farmers, agricultural associations and enterprises and research and academic institutions. And substantial resources are allocated for strengthening institutional and farmers’ capacities, leading to increased knowledge, awareness and practices associated with agrobiodiversity management.

- This project will demonstrate several innovative approaches, including promotion of a landscape approach towards agrobiodiversity conservation and sustainable use. Managing agro-ecological resources sustainably to maintain biodiversity and ecosystem services requires an integrated, landscape approach that addresses topography, vegetation, land use, settlement patterns, etc. These objectives cannot be achieved at an individual farm or plot level, but rather at a landscape scale.  The project will facilitate best management practices within three demonstration agricultural landscapes and the demonstrated approaches will be replicated across at least two other landscapes, according to a replication strategy and upscaling plan that will be initiated in Component 3 through cofinancing contributions and guidance by the lessons learned in the demonstrations implemented in Component 2. The replication strategy and upscaling plan will not be limited to the two replication landscapes, but also cover other potential areas in the province. Integrating GRFA approaches into work programs, included in the 14th 5-year plan for DARA will further enhance the likelihood for replication.

- The project will establish innovative systems, tools and approaches for the protection of agricultural species varieties in Hainan, including the mainstreaming of participatory approaches for in-situ conservation and the establishment of incentive-based mechanisms for sustainable use and conservation. The close involvement of the enterprise sector is another aspect of project innovation. Cofinancing contributions have been confirmed from three enterprises and the project will facilitate participation of other agricultural enterprises as well as agricultural associations and cooperatives in the implementation of GRFA conservation and sustainable use plans and development and strengthening of GRFA markets. The innovative, market-based tools and approaches for the conservation of traditional GRFA varieties will supply chain development (e.g., collective marketing), developing niche markets, promoting agro-ecotourism, enhancing cultural preference branding, showcasing nutritional branding, recognizing traditional knowledge, enhancing e-commerce among rural communities, facilitating new partnerships, etc.

- The project will also demonstrate the application of non-market-based measures to conservation such as eco-compensation schemes in the Central Highlands area. While these schemes are actively used in China to address other environmental challenges, they have not yet been applied to the in-situ conservation and sustainable use of agricultural varieties.

- Innovativeness is also featured through the C-SAP programmatic approach. The program will ensure linkages across the individual child projects and enabling cross fertilization between projects through sharing of best practices, lessons and technical expertise. Moreover, multiple activities recognize the importance of integrating international best practice into conservation and sustainable use of agrobiodiversity.

Socioeconomic Benefits:

- Agrobiodiversity is inherently linked to the well-being of the communities that are engaged in the conservation and/or sustainable use of resources and of the broader public who benefit from the nutritional values delivered. Women play a particularly important role in this matter, considering their tasks and responsibilities for food production, management of agricultural systems in rural areas where many men have migrated from for work opportunities in cities and marketing agricultural products and services. The project will generate the following socioeconomic benefits:

- A cumulative total of 5,522 direct project beneficiaries, including 2,739 women and 2,783 men, and broken down by 5,412 people (2,706 women and 2,706 men) living in the communities within the demonstration agricultural landscapes (Li and Miao ethnic minorities living in 2 of the 3 target landscapes) and 110 institutional staff members (33 women and 77 men) having strengthened capacities with regard to in-situ conservation and sustainable use of agrobiodiversity.

- 500 farmers trained in best practice approaches to conservation and sustainable use of GRFA varieties.

- Sustainable livelihood benefits generated as a result of increased engagement of farmer households in conservation and sustainable use of GRFA varieties: an additional 30 households are estimated to become engaged over the course of the project.

- Enhanced access to improved genetic resources through establishment of a community seed bank for Shanlan rice and livestock competitions for Wuzhishan pig and Jiaji duck.

- Increased resilience of local communities through completion of participatory landscape assessments and development and implementation of GRFA conservation and sustainable use plans. These activities will facilitate an increased awareness and knowledge of the value of agrobiodiversity and introduction of improved agricultural practices and approaches, leading to an increase in the protection of ecosystem services and more sustainable use of available natural resources.

- Increased knowledge and availability of traditional GRFA varieties, through targeted awareness campaigns, strengthened marketing capacities and formation of new partnerships for new and strengthened GRFA products and offerings, such as agro-ecotourism.

- Increased involvement of youth in the conservation and sustainable use of GRFA varieties, thus increasing the likelihood that results achieved will be sustained among future generations of institutional and production sector stakeholders.

- Increased membership into agricultural associations such as cooperatives.

Agricultural Demonstration Landscapes:

- An integrated, landscape-based approach is promoted through the demonstration interventions in Component 2.  Consistent with the objectives of eco-agriculture, maintaining biodiversity and ecosystem services, managing agricultural production sustainably and delivering livelihood benefits to local households cannot be achieved at the farm or plot level, but rather at a landscape scale. Landscapes can be defined based upon topography or drainage basin, or by vegetation or soil type, or cultural heritage or by settlements. A more informative definition is presented below in Box 1.

Box 1: Definition of eco-agricultural landscape

As described by Scherr and McNeely (2008), the term “landscape” is defined, depending upon the spatial units needed or actually managed by the group of stakeholders working together to achieve biodiversity, production and livelihood goals. Eco-agriculture landscapes are land use mosaics with: - ‘Natural’ areas (with high habitat quality and niches to ensure critical elements for habitat or ecosystem services that cannot be provided in areas under production), which are also managed to benefit agricultural livelihoods either through positive synergies with production or other livelihood benefits, - Agricultural production areas (productive, profitable and meeting food security, market and livelihood needs), which are also configured and managed to provide a ‘matrix’ with benign or positive ecological qualities for wild biodiversity and ecosystem services, and - Institutional mechanisms to coordinate initiatives to achieve production, conservation and livelihood objectives at landscape, farm and community scales, by exploiting synergies and managing trade-offs among them. The concept of eco-agriculture further recognizes that agriculture-dependent rural communities are critical (and sometimes the principal) stewards of biodiversity and ecosystem services. While protected natural areas are essential in eco-agriculture landscapes to ensure critical habitat for vulnerable species, maintain water sources and provide cultural resource, these resources often may be owned or managed by local communities and farmers.

- The three landscapes occupy a cumulative land area of 13,787 hectares (ha) with a combined total of 5,412 direct beneficiaries, as summarized below in Table 6, with locations shown on Figure 3.

Table 6: Summary of the three demonstration agricultural landscapes

| Target GRFA variety | County Township | Agricultural Demonstration Landscape |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  | Mid-point Georeferenced Coordinates |  | Area, ha | Est. number of direct beneficiaries |
|  |  | Longitude | Latitude |  |  |
| Wuzhishan pig (Sus scrofa) | Baisha* Da’an | 109o15’ | 19o10’ | 1,328 | 1,316 |
| Shanlan rice (Oryza sativa) | Qiongzhong** Shang’an | 109o48’ | 18o53’ | 11,140 | 1,336 |
| Jiaji duck (Anas domestica) | Qionghai City Shibi | 110o18’ | 19o09’ | 1,319 | 2,760 |
| Total: |  |  |  | 13,787 | 5,412 |

*Full name: Baisha Li Autonomous County

**Full name: Qiongzhong Li and Miao Autonomous County

Figure 3: Location map of agricultural demonstration landscapes

- Wuzhishan pig demonstration landscape: The demonstration landscape for Wuzhishan pig is located in Da’an township, in the north-central part of Baisha Li Autonomous County (see Figure 4). This county along with adjacent counties are situated within the central highland region of Hainan Province, classified as one of the 25 key ecological function zones in China and harboring extensive primary rainforest ecosystems. The 1,328-ha demonstration landscape was delineated on the basis the prevalence of rural farmers in this township providing pig-rearing services to Fomianshan Farmers Association of Cultivation and Animal Husbandry, a local enterprise interested in expanding production and marketing of Wuzhishan pig and working with the project in applying an integrated, landscape-based approach towards sustainably managing this GRFA variety.

- Wuzhishan pigs are native to the Wuzhishan area where Li and Miao people live in the central part of Hainan Province. The variety was classified as endangered in the 1980’s due to rapid displacement by commercial varieties, but it has recovered somewhat in recent years with renewed consumer demand, as the Wuzhishan pig has low fat content and good meat quality. Wuzhishan pig is an ancient variety, reared in certain natural habitats. The dwarf size of this variety of pig is related to the long-term inbreeding of local wild boars and their own many genetic controls. A recent comparative study showed that both pure and complex or hybrid utilization have the characteristics of genetic instability. According to a field survey made by the Institute of Tropical Agricultural Sciences of China, Wuzhishan pigs are mainly distributed in the mountainous areas where ethnic minorities live in Qiongzhong, Baoting, Baisha, Changjiang and Sanya cities and counties in Hainan Province. According to the survey, more than 50 germplasms of Wuzhishan pigs are endangered. At the same time, a variety of exotic plants have invaded the Wuzhi Mountains, encroaching into vegetation habitats traditionally favored by the Wuzhishan ig. Eupatorium odoratum and Praxelis clematidea have spread all over the island's forest margins, wilderness, wasteland, roadsides, and front houses. Moreover, water gourds and African snails have caused damage to some water bodies.

Figure 4: Vicinity map of Wuzhishan pig demonstration landscape

- Shanlan rice demonstration landscape. The demonstration landscape for Shanlan rice is located in the Shang’an Township (see Figure 5), a mountainous area of central Hainan Province, in the south part of Qiongzhong Li and Miao Autonomous County. Globally significant biodiversity in this region includes the 13,436-ha Wuzhishan National Nature Reserve (KBA 15785), located in the south reaches of the county (18.83 N, 109.68 E). The demonstration landscape covers an area of approximately 11,140, delineated on the basis of habitat suitability and traditional knowledge for cultivating this variety of rice in the township. Shanlan rice is a dryland variety, an important component to the diet and culture of local Li people for centuries; some experts have estimated that Li people have cultivated this variety using traditional techniques since the Han Dynasty, more than 2,000 years ago.

- Currently there are two newer varieties, Shanlan Lu No. 1 and Shanlan Nuo No. 1 available, but these are not used for cultivation by farmers in Shangan Township. Rather, local farmers tend to grow traditional landraces, and germplasms are conserved by themselves using simple methods, which may bring risk of germplasm diversity loss, as the seeds under the current conditions are very easy to be eroded by insects and fungi.   During the recent years, the growing area of this rice variety is shrinking, as it has serious competition from other crops like betel nut (fruit of Areca catechu)  and Chinese black cardamom (Alpinia oxyphylla), which likely bring farmers more revenue. Current cultivation practices rely on land reclamation, imparting pressure onto nearby rainforest ecosystems. Erosion of traditional knowledge is also a concern, due to the lack of interest among youth and an aging population of local farmers.

Figure 5: Vicinity map of Shanlan rice demonstration landscape

- Jiaji duck demonstration landscape. The 1,319-ha Jiaji duck demonstration landscape is located in Shibi Township on the north bank of the middle section of the Wanguan River in the southwest part of Qionghai City (see Figure 6). Shibi township has an administrative area covering 171 km2 and a population of 17,250 inhabitants, and has jurisdiction over 7 administrative villages, 77 natural villages and 104 villager groups.  The demonstration landscape was delineated on the basis of an area where there is a prevalence of local farmers raising Jiaji duck – currently or in the past.

Figure 6: Vicinity map of Jiaji duck demonstration landscape

- Jiaji duck is characteristic of thick meat, thin skin, soft bones and little fat, in contrast to usual commercial varieties. It is welcome in local markets in Qionghai City and other areas of Hainan Province.  However, due to the complexities and high costs associated with rearing Jiaji duck, it is currently facing competition from other varieties. Conservation of germplasms of Jiaji duck is complicated, and there is loss and erosion of the germplasm.

More information is included in the Baseline Report on Demonstration Landscapes in Annex L.

# Results and Partnerships

Expected Results:

- In the baseline scenario, the absence of a cohesive policy and strategic framework, the lack of coordination  among governmental and other enabling stakeholders and low levels of awareness will limit the conservation of agrobiodiversity, leading to further attrition of traditional knowledge and practices, increasing genetic vulnerability and decreasing the diversity status of GRFA varieties. Small-scale farmers will continue to be displaced by large-scale operations favoring production of high-yielding cultivars. Agricultural enterprises will likely continue to develop niche markets for culturally preferred GRFA varieties; however, the full range of market opportunities will not be developed, and agricultural production will remain disconnected with efforts to protect ecosystem services and conserve valuable biodiversity.

- The alternative scenario facilitated through the GEF funds involves formulation of a comprehensive agrobiodiversity strategy and action plan through a cross-sectoral and inter-sectoral coordinated process that addresses the policy, capacity and market constraints. Through participatory approaches involving farmers, enterprises and local government units, landscape-scale demonstrations of conservation and sustainable use of GRFA varieties will implemented that identify the ecological and cultural values of genetic diversity, combines traditional knowledge with best practices learned domestically and internationally, engages women and youth into decision-making roles and establishes new and strengthens existing markets for GRFA varieties applying both non-market-based and market-based incentive mechanisms. Strengthened institutional and individual capacities, increased knowledge and expanded access to information will underpin broader uptake and appreciation of agrobiodiversity conservation across the province.

- Global Environmental Benefits: The project is expected to generate global environmental benefits of improved management of landscapes covering 13,787 ha. This contributes towards the 320 million ha target for the GEF-7 Core Indicator No. 4, “Area of landscapes under improved practices”. More specifically, the project is aligned with GEF-7 component sub-indicator No. 4.3, “Area of landscapes under sustainable land management in production systems”.

- The project will generate socio-economic co-benefits for 5,522 direct beneficiaries, including 2,739 women, or 50% of the total; these co-benefits contribute towards GEF-7 Core Indicator No. 7, “Number of direct beneficiaries disaggregated by gender”.

- Consistent with GEF-6 biodiversity strategy, Program 7, “Securing Agriculture’s Future: Sustainable Use of Plant and Animal Genetic Resources”, the project will increase the diversity status of Wuzhishan pig, Shanlan rice and Jiaji duck through implementation of participatory conservation and sustainable use approaches, and enhancement of germplasm resources through establishment of a community seed bank for Shanlan rice and arranging regular livestock competitions for Wuzhishan pig and Jiaji duck.

- Project objective: The project objective is to strengthen the in-situ conservation and sustainable use of globally significant agrobiodiversity in Hainan through the development of incentive mechanisms for farmers to sustain populations of endemic crops and livestock, the establishment of a supportive enabling environment and strengthened institutional capacity.

- Expected objective-level results include the following:

- 13,787 ha of landscapes under participatory conservation and sustainable use of agrobiodiversity;

- 5,522 direct project beneficiaries, including 2,739 women and 2,783 men, and broken down by 5,412 people (2,706 women and 2,706 men) living in the communities within the demonstration agricultural landscapes and 110 institutional staff members (33 women and 77 men) having strengthened capacities with regard to in-situ conservation and sustainable use of agrobiodiversity.

Component 1: Enhanced provincial policy and regulatory framework

Total Cost: USD 1,134,990; GEF project grant requested: USD 142,990; Cofinancing: USD 992,000

- The alternative proposed by the project involves strengthening the enabling framework for incentivized participatory conservation and sustainable use of GRFA. Under this component, GEF resources are allocated for facilitating improved inter-sectoral and cross-sectoral coordination among provincial and local government level agencies, developing an agrobiodiversity strategy and action plan that provides a roadmap for achieving sustainable management of GRFA in the province, formulating GRFA implementation frameworks that encourages participation in agrobiodiversity conservation and preparing guidelines for implementation of non-market incentives, including appropriation of eco-compensation funds for agrobiodiversity conservation. The baseline situation and incremental reasoning for Component 1 are summarized below in Table 7.

Table 7: Summary of baseline and incremental reasoning for Component 1

| Summary of Baseline Situation | Incremental Reasoning |
| --- | --- |
| Output 1.1: Inter-sectoral and cross-sectoral coordination mechanisms are established and being used to facilitate the planning and implementation of approaches for the sustainable use and conservation of varieties |  |
| The roles and responsibilities for instituting agrobiodiversity conservation in the province cut across several institutional level stakeholders, with DARA as the lead agency, the Provincial Department of Ecology and Environment as the main focal point for biodiversity conservation, and the Provincial Department of Natural Resources responsible for forest management and overseeing land use planning and development. Other agencies involved include the Provincial Development and Reform Commission, the Provincial Office for Poverty Alleviation, the Department of Water Resources, the Department of Education and the All Women’s Federation. At the local government level, including county and township levels, there are respective departments representing the provincial level agencies listed above. Under the baseline situation, the efforts and responsibilities related to conservation and sustainable use of agrobiodiversity are disjointed and not aligned among the key enabling provincial and local government level agencies. More information is included in the Baseline Report on Policy, Governance and Knowledge Management in Annex K. | Through this output, the project will facilitate establishment of a provincial and three county level GRFA Coordination Committees, having representatives from key agencies, as well as representatives from the research/academic sector, the enterprise sector (e.g., trade associations), and social organizations. The committees will provide advisory support to the project, e.g., reviewing policy and regulatory reforms, eco-compensation guidelines and systems and procedures for improving knowledge management. The committees will also provide support to the project activities implemented in the three demonstration landscapes. Through knowledge transfer exchange, the operation of the county level committees will be advocated in the replication landscapes under Component 3, promoting increased collaboration across counties and among stakeholders in the province. Decisions issued by DARA and the county level agricultural bureaus, the GRFA Coordination Committee will be institutionalized, ensuring continued coordination after GEF funding ceases. |
| Output 1.2: Policies, strategies and regulations related to in-situ conservation and sustainable use of agrobiodiversity are strengthened and developed |  |
| There are a number of provincial and national governmental programs aimed at mainstreaming biodiversity conservation into agricultural production practices. In 2014, the provincial government issued two important strategies: Management of Crop Germplasm Resources and the Biodiversity Strategy and Action Plan (2014-2030). And in 2017, the provincial government issued the Implementation Guidance on Agricultural Modernization Acceleration and Realization of a Comprehensive Well-off Society in Rural Areas. In this guidance, the government outlines a strategy on cultivating new professional farmers, to strengthen the protection and efficient use of agricultural resources, to strengthen the construction and management of nature reserves, to implement mandatory protection of important ecosystems and species resources, and to implement measures for conservation of endangered wild animals and plants. These plans and strategies reflect the recognition of the value of crop germplasm resources for sustainable development. However, there is limited strategic direction with respect to in-situ conservation and sustainable use of GRFA varieties. More information is included in the Baseline Report on Policy, Governance and Knowledge Management in Annex K. | The incremental support delivered under this output includes strengthening policy, strategic and regulatory frameworks to provide an incentivized enabling environment for conservation and sustainable use of agrobiodiversity. The planned agrobiodiversity strategy and action plan will lay out the institutional roles and responsibilities and identify specific measures to implement to move towards a more coordinated and targeted approach, and identify A provincial GRFA implementation framework will be developed to better enable farmers to engage in agrobiodiversity conservation, including promoting development of agro-ecotourism. At the county level, where project demonstrations are planned, GRFA implementation frameworks will be developed to address the specific varieties that are traditional and prevalent in those areas. |
| Output 1.3: Eco-compensation appropriation policies are revised to support the in-situ conservation and sustainable use of agrobiodiversity and an eco-compensation plan is developed for protection of agricultural varieties in the Central Highlands area |  |
| The Chinese central government has implemented a number of eco-compensation programs nationwide, including those associated key national ecosystem function areas. The Central Highlands area of Hainan Province listed as a key national ecological function zone, and eco-compensation funds are appropriated to the affected counties, as certain land use activities and development in these areas are prohibited or restricted. Under the baseline situation, agricultural ecosystems are currently not included these eco-compensation schemes. Under the baseline situation, there are limited eco-compensation funds and other non-market incentive mechanisms earmarked for agrobiodiversity conservation. More information is included in the Baseline Report on Policy, Governance and Knowledge Management in Annex K. | The incremental benefits delivered through the GEF funds include a gap analysis on eco-compensation and other non-market incentive mechanisms for facilitating increased participation in conservation and sustainable use of GRFA. Non-market incentives could include direct payments for growing GRFA varieties, or rewards for maintaining diversity status, etc. A draft guideline will be developed for appropriating available eco-compensation funds for agrobiodiversity conservation; the guideline will be further elaborated following a demonstration of the guidelines in one or more of the demonstration landscapes under Component 2. More information is included in the Baseline Report on Demonstration Landscapes in Annex L. |

Outcome 1:  Provincial policy, strategy and regulatory framework for in-situ conservation and sustainable use of agrobiodiversity enhanced

- Results expected through achievement of Outcome 1 include:

- Provincial agrobiodiversity strategy and action plan approved by Hainan DARA.

- Provincial GRFA implementation framework approved by Hainan DARA, and county level GRFA implementation frameworks approved by Baisha County, Qiongzhong County and Qionghai City agricultural bureaus.

- Provincial GRFA coordination committee established, with charter approved by Hainan DARA, and three county GRFA coordination committees established with charters approved by the county agricultural bureaus.

- CNY 1 million of eco-compensation funds allocated for agrobiodiversity conservation in the final year of project implementation or earmarked for the year following project closure.

Output 1.1: Inter-sectoral and cross-sectoral coordination mechanisms are established and being used to facilitate the planning and implementation of approaches for the sustainable use and conservation of varieties

Key deliverables/results:

- GRFA coordination committee meetings convened regularly, providing advisory support to the implementation of project activities.

- Procedures and protocols for the knowledge-sharing platform (developed under Output 4.2) prepared and operationalized.

- One of the important requisites for establishing an enduring enabling environment for realizing broader participation in the conservation and sustainable use of agrobiodiversity is strong inter-sectoral and cross-sectoral coordination structures. Under this output the project will help facilitate such structures through establishing and operationalizing provincial GRFA coordination committee and county level GRFA coordination committees in the counties where the three demonstration landscapes under Component 2 are located, namely Baisha County, Qiongzhong County and Qionghai City. The GRFA coordination committees will be inter-sectoral, e.g., collaborating across provincial, county, township and village levels, and cross-sectoral, e.g., involving representatives from sectors having mandates associated with agrobiodiversity. Participation on the coordination committees will not be limited to the governmental sector; consideration will be given to including representatives from research and academic institutions, non-governmental organizations (NGOs), agricultural trade associations, etc.

- The project will provide technical assistance for preparing charters for the coordination committees that will include, but not be limited to, the purpose of the committees, an indication of the form or type of committee, membership and chairperson, roles and responsibilities, and standard committee procedures. The committees will operate throughout the 5-year project implementation timeframe, providing advisory support towards the implementation of the project, and also be operationalized as functioning committees that will continue to operate after project closure. By the end of the project, the charters of the committees are expected to be approved by the Hainan DARA and county agricultural bureaus, respectively.

- A knowledge transfer exchange is planned with the national level coordination committee that is planned to be established under the national agrobiodiversity child project (C-SAP1) of the C-SAP program. The purpose of the knowledge transfer exchange is to share experiences on the functions and procedures of the committees, and to allow Hainan representatives an opportunity to become more familiar with emerging national level policies, strategies and programs associated with agrobiodiversity conservation.

- The GRFA coordination committees will also have an important role in advising on coordination procedures and protocols for the knowledge-sharing platform developed under Output 4.2, working closely with the National Technical Advisor, Project Coordinator and knowledge management specialists, as well as with the C-SAP program Knowledge Management Officer, who will help link the project level knowledge platform with the program level one.

- Indicative activities under Output 1.1 include:

| 1.1.1. | Establish a provincial GRFA coordination committee and county level GRFA coordination committees in Baisha County, Qiongzhong County and Qionghai City, ensuring cross-sectoral representation, and equitable participation by women and youth. |
| --- | --- |
| 1.1.2. | Prepare charters for one provincial and three county level GRFA inter-sectoral coordination committees; the charters should include but not be limited to, a description of the purpose of the committee, an indication of the form or type of committee, membership and chairperson, roles and responsibilities, and standard committee procedures. |
| 1.1.3. | Convene regular committee meetings, including providing advisory support services to the project steering committee and project implementation teams. |
| 1.1.4. | Organize a knowledge transfer exchange with the national level GRFA coordination committee, to be established under the national agrobiodiversity project (C-SAP1) of the C-SAP program. |
| 1.1.5. | Advise on coordination procedures and protocols for the knowledge-sharing platform developed under Output 4.2. |
| 1.1.6. | Operationalize the provincial and three county level committees through departmental or local government decisions. |

Output 1.2: Policies, strategies and regulations related to in-situ conservation and sustainable use of agrobiodiversity are strengthened and developed

Key deliverables/results:

- Gap analysis on policies, strategies and regulations associated with conservation and sustainable use of GRFA in Hainan Province.

- Workshop convened to discuss and information stakeholders of proposed policy and regulatory reforms.

- The activities under this output are designed to strengthen the policies, strategies and regulatory frameworks associated with conservation and sustainable use of GRFA in Hainan Province.

- Through the provincial GRFA coordination committee, a policy working group will be assembled for providing advisory support to the project team and contracted policy specialists. The first step will be carrying out a gap analysis, reviewing existing policies, strategies and regulations, identifying disincentives making recommendations for improving an incentivized enabling environment. The gap analysis will include a feasibility study for introducing Access and Benefit-Sharing (ABS) systems in the province for in-situ conservation and sustainable use of agrobiodiversity. The recommendations of the gap analysis will help inform the preparation of an agrobiodiversity strategy and action plan that will provide a practical roadmap to provincial stakeholders on instituting regulatory reforms for incentivizing conservation and sustainable use of agrobiodiversity. The agrobiodiversity strategy and action plan will complement the Hainan provincial biodiversity strategy and action plan 2014-2030 (PBSAP) and capture the existing agriculture sector policies and strategies into a consolidated form.

- Considering the recommendations in the gap analysis and the prioritization of key actions outlined in the agrobiodiversity strategy and action plan, policy specialists will work with legal department officials from the Hainan DARA and the three country agriculture bureaus where the demonstration landscapes are located, in preparing GRFA implementation frameworks that strengthen non-market incentive mechanisms for expanding conservation and sustainable use of GRFA and remove disincentives that reduce agrobiodiversity. A stakeholder workshop will be convened to discuss the recommended regulatory reforms and solicit feedback before finalizing the implementation frameworks for submittal for approval to the Hainan DARA and county agriculture bureaus.

- Indicative activities under Output 1.2 include:

| 1.2.1. | Establish a policy working group and convene regular meetings to review the policy and regulatory recommendations and draft deliverables produced. |
| --- | --- |
| 1.2.2. | Carry out a gap analysis on policies, strategies and regulations associated with conservation and sustainable use of GRFA in Hainan Province, and prepare recommendations for revising or introducing policies, strategies and regulations to better enable incentivized conservation and sustainable use of GRFA, including mechanisms to encourage increased participation by women and youth. |
| 1.2.3. | Prepare a provincial agrobiodiversity strategy and action plan, complementary to the provincial biodiversity strategy and action plan. |
| 1.2.4. | Develop a provincial GRFA implementation framework, to provide a regulatory framework for encouraging beneficial activities and removing disincentives that reduce agrobiodiversity. |
| 1.2.5. | Develop GRFA implementation frameworks for Baisha County, Qiongzhong County and Qionghai City that facilitate incentive mechanisms for farmers, agricultural associations and enterprises to expand conservation and sustainable use of GRFA. |
| 1.2.6. | Convene a provincial workshop to inform stakeholders of the GFRA strategies and regulatory frameworks developed. |
| 1.2.7. | Provide advocacy for disseminating information on and advancing the approval of the GRFA strategy and action plan and implementation frameworks. |

Output 1.3: Eco-compensation appropriation policies are revised to support the in-situ conservation and sustainable use of agrobiodiversity and an eco-compensation plan is developed for protection of agricultural varieties in the Central Highlands area

Key deliverables/results:

- Draft guideline on allocating eco-compensation funds to incentivize in-situ conservation and sustainable use of agrobiodiversity in Hainan Province.

- Implementation plan for demonstrating appropriation of eco-compensation funds for the conservation and sustainable use of agrobiodiversity in the Central Highlands area.

- One type of non-market incentive mechanism is eco-compensation, e.g., direct payments for growing GRFA varieties or rewards for maintaining diversity. There are a number of eco-compensation programs in Hainan Province, for instance in the Central Highlands area, which is classified as a key ecological function zone because of the importance of protecting valuable water resources. The activities under this output are designed to provide provincial and county level decision makers with demonstrable evidence of appropriating eco-compensation funds for incentivizing conservation and sustainable use of agrobiodiversity.

- The preliminary baseline analysis made as part of the project preparation phase (see the Baseline Report on Policy, Governance and Knowledge Management in Annex K) will be updated and developed into a draft guideline for allocating eco-compensation funds for promoting agrobiodiversity conservation.  An environmental economist (resource economist) will prepare this guideline, through consultations with stakeholders responsible for managing existing eco-compensation funds, as well as information obtained through interviews with farmers, agricultural associations and enterprises. A stakeholder workshop will be convened to present the draft guideline, to obtain further feedback and to discuss demonstration of appropriating eco-compensation funds in the Central Highlands area. A knowledge transfer exchange is also planned under this output, to learn from a functioning eco-compensation scheme in China focused on incentivizing conservation and sustainable use of agrobiodiversity.

- An implementation plan will then be prepared for such a demonstration in the Central Highlands area. Initiation of the implementation plan will be made under Component 2. After approximately 2 seasons of implementing the eco-compensation demonstration, the results will be evaluated, and the draft guideline will be finalized for submittal to the Hainan provincial and county governmental agencies for upscaling in the Central Highlands area and other regions in the province.

- Indicative activities under Output 1.3 include:

| 1.3.1. | Carry out an analysis and prepare a draft guideline on allocating eco-compensation funds to incentivize in-situ conservation and sustainable use of agrobiodiversity in Hainan Province, according to the guideline on promoting green agricultural development in Hainan Province; e.g., direct payments for growing GRFA varieties, rewards for maintaining diversity, etc., and emphasizing equitable participation by women and youth. |
| --- | --- |
| 1.3.2. | Organize a knowledge transfer exchange to other interventions in China where eco-compensation schemes involving agrobiodiversity are under implementation or development. |
| 1.3.3. | Organize an inter-sectoral and cross-sectoral provincial workshop, inviting governmental, enterprise sector, farmer association and NGOs stakeholders, to discuss eco-compensation opportunities. |
| 1.3.4. | Prepare an implementation plan for demonstrating appropriation of eco-compensation funds for the conservation and sustainable use of GRFA varieties in the Central Highlands area, consistent with the regulatory frameworks associated with key ecological function zones in China. |
| 1.3.5. | Evaluate the demonstration-level implementation results in Component 2 and finalize the guideline for allocation of eco-compensation funds or introducing new eco-compensation schemes for in-situ conservation and sustainable use of agrobiodiversity. |

Component 2: Demonstration of sustainable incentive mechanisms for in-situ conservation and use of GRFA

Total Cost: USD 5,902,320; GEF project grant requested: USD 726,320; Cofinancing: USD 5,176,000

- The largest proportion of the project cost is allocated to this component, which includes demonstrating incentivized approaches to conservation and sustainable use of GRFA in three demonstration landscapes. After building up participatory structures and procedures, GRFA conservation and sustainable use plans will be developed on the basis of the results of participatory landscape GRFA assessments. Implementation of the GRFA conservation and sustainable use plans will then be initiated, with opportunities available to farmers, agricultural associations and enterprises to add value on farm, strengthen marketing capacities, expand partnerships and learn from complementary interventions. Protection of germplasms of the target varieties will be enhanced through establishing a community seed bank for Shanlan rice and organizing regular livestock competitions for Wuzhishan pig and Jiaji duck. Provincial and county level trade fairs will also be organized to showcase the GRFA products and offerings developed and strengthened under this component. The baseline situation and incremental reasoning for Component 2 are summarized below in Table 8.

Table 8: Summary of baseline and incremental reasoning for Component 2

| Summary of Baseline Situation | Incremental Reasoning |
| --- | --- |
| Output 2.1: Participatory structures and planning and monitoring protocols put in place to improve conservation of traditional GRFA varieties in three demonstration landscapes |  |
| Under the baseline situation, farmers, agricultural associations, enterprise and local governments are engaged with GRFA varieties in the demonstration landscapes, but many stakeholders are unaware of available incentive mechanisms, there is a lack of coordinated, participatory approaches that consider broader landscape level ecosystem services, marketing capacities are lacking among some of the agricultural associations and enterprises to develop enduring markets, consumers are unaware of many of the GRFA products and offerings. In the rural areas within the demonstration landscapes, many men have migrated to cities for alternative employment, leaving women and elderly to manage the agricultural operations, and the young generation generally lack interest. These socioeconomic factors are contributing to the decline in traditional farming practices. Information on the demonstration landscapes, including socioeconomic conditions, is compiled in the baseline reports in Annex L. | Under this output, the GEF resources are directed to building grassroots level, participatory structures and procedures. Landscape partnership working groups will be established in each of the three demonstration landscapes. These committees will include farmers, members of agricultural associations and enterprises, local government staff members, representatives from social organizations, and have equitable representation by women and youth. Through the function of the landscape partnership working groups and joint planning activities, participatory landscape GRFA assessments will be carried out for each of the three demonstration landscapes, and then GRFA conservation and sustainable use plans developed. |
| Output 2.2: Market- and non-market-based incentive mechanisms are demonstrated three target agricultural landscapes, resulting in enhanced germplasm protection and securing sustained livelihood benefits for farmers and improved conservation of target varieties |  |
| Under the baseline situation, there are limited and uncoordinated efforts on protecting and enhancing germplasms of the target GRFA varieties in the demonstration landscapes, and there are gaps in awareness among farmers, agricultural associations, enterprises and local government units on best practices and approaches. The decline in traditional farming systems is resulting in increased genetic vulnerability, e.g., through poor seed management, cross-breeding, etc. Information on the demonstration landscapes, including socioeconomic conditions, is compiled in the baseline reports in Annex L. | Through implementation of GRFA conservation and sustainable use plans in the three demonstration landscapes, GEF funding will result in enhanced protection of germplasms and improved agricultural practices and approaches, leading to a strengthened enabling environment for ensuring long-term conservation of agrobiodiversity and viable and sustainable livelihood options for local farmers, associations and enterprises. Interventions aimed at adding value on farm will be implemented, a community seed bank for Shanlan rice will be established, and annual livestock competitions with traditional knowledge for Wuzhishan pig and Jiaji duck will be organized. |
| Output 2.3: Agrobiodiversity supply and value chains of the target GRFA varieties enhanced through strengthened marketing capacities and expanded application of marketing tools, including cultural value branding and product certification |  |
| Agrobiodiversity supply and value chains are operating to varying degrees for some GRFA varieties in the demonstration landscapes; however, there are shortcomings in terms of limited marketing capacities among farmers, agricultural associations and enterprises; lack of awareness of available incentive mechanisms and marketing tools; and underdeveloped agro-ecotourism sector. Information on the demonstration landscapes, including socioeconomic conditions, is compiled in the baseline reports in Annex L. | Through supply and/or value chain analyses, the project will provide incremental support in identifying opportunities for expanding sustainable utilization of agrobiodiversity and increasing livelihood benefits to local communities in the demonstration landscapes. GEF funding is also allocated for implementing specific actions identified in the supply/value chain analyses aimed at strengthening marketing capacities and application of marketing tools and incentive mechanisms. |
| Output 2.4: Farmers, agricultural associations and enterprises capacitated and GRFA conservation and sustainable use improved through partnership development and organizational strengthening, with a focus on increasing participation by women and youth |  |
| Under the baseline situation, trainings to farmers and agricultural associations tend to focus on modern varieties, with limited resources allocated for strengthening capacities in conservation and sustainable use of agrobiodiversity. Distribution of agrobiodiversity products and services tend to be limited in scale, often only at the local level. And there are few opportunities for local farmers to learn of partnership possibilities with agricultural associations and enterprises. Information on the demonstration landscapes, including socioeconomic conditions, is compiled in the Baseline Report on Demonstration Landscapes in Annex L. | GEF funds will support capacity building among farmers and agricultural associations, expanding partnerships through organizing exchange visits among provinces within China and trade fairs at various levels, providing microgrant assistance to local stakeholders to strengthen their operations or introduce specific GRFA offerings. A particular emphasis is placed on strengthening capacities of women and youth |

Outcome 2: Market- and non-market-based incentive mechanisms established and demonstrated for in-situ conservation and sustainable  use of agrobiodiversity, enabling long-term livelihood benefits for local farmers

- Results expected through achievement of Outcome 2 include:

- Sustainable livelihood benefits to farmers generated through incentivized in-situ conservation and sustainable use of GRFA: by the end of the project, 56 farmer households engaged in Wuzhishan pig, 10 households engaged in Shanlan rice and 10 households engaged in Jiaji duck.

- Enhanced access to genetic resources, including establishment of community seed bank(s) for Shanlan rice and regular livestock competitions for Wuzhishan pig and Jiaji duck mainstreamed into local extension offerings.

- Strengthened GRFA markets and marketing capacities through at least two new product certifications for GRFA varieties and at least two new partnerships established.

Output 2.1: Participatory structures and planning and monitoring protocols put in place to improve conservation of traditional GRFA varieties in three demonstration landscapes

Key results/deliverables:

- Establishment and operationalization of landscape partnership working groups in the three demonstration landscapes.

- Standard protocol for participatory GRFA landscape assessments.

- Three participatory GRFA landscape assessments completed.

- Three GRFA conservation and sustainable use plans developed.

- Output 2.1 is focused on establishing the requisite participatory coordination structures and procedures for implementing GRFA conservation and sustainable use plans in three demonstration landscapes in Hainan Province. A landscape partnership working group will be established for each of the demonstration landscapes, with participation by farmers, agricultural associations and cooperatives, enterprise sector, NGOs, and local governments, with equitable representation of women and youth. Community development specialists will deliver training to the committee members on topics such as sustainable livelihoods, natural resource management, GRFA varieties, fund management, traditional knowledge and conflict resolution.

- Under this output, a GRFA specialist will be retained to develop a standard protocol for a participatory GRFA landscape assessment and using the developed protocol and through involvement of the landscape partnership working groups, participatory assessments will be made for each of the three demonstration landscapes. These assessments will document the physical, cultural, agricultural, social and traditional aspects of the landscapes, focusing on GRFA varieties. The participatory landscape assessments will be used as the foundations for the development of GRFA conservation and sustainable use plans for the three target GRFA varieties that will include specific actions for achieving sustainable management of agrobiodiversity resources in the demonstration landscapes.

- Indicative activities under Output 2.1 include the following:

| 2.1.1. | Establish and operationalize landscape partnership working groups for the three demonstration landscapes in Baisha County, Qiongzhong County and Qionghai City, with participation by local farmers, agricultural associations and cooperatives, enterprise sector, NGOs and local government units, and having equitable representation of women and youth. |
| --- | --- |
| 2.1.2. | Develop a standard protocol for participatory GRFA landscape assessments and for monitoring and evaluating agroecosystem health. |
| 2.1.3. | Deliver training to the landscape partnership working group members on topics including community development, fund management, nutritional value of GRFA varieties, cultural value and traditional knowledge, gender mainstreaming, conflict resolution, GRFA conservation, monitoring and evaluation of agroecosystem health, etc. |
| 2.1.4. | Carry out participatory GRFA landscape assessments of the three demonstration landscapes in Hainan Province. |
| 2.1.5. | Develop GRFA conservation and sustainable use plans for the three demonstration landscapes. |
| 2.1.6. | Procure monitoring and evaluation equipment and supplies, capacitating the landscape partnership working groups for assessing progress of the implementation of the GRFA conservation and sustainable use plans. |

Output 2.2: Market- and non-market-based incentive mechanisms are demonstrated three target agricultural landscapes, resulting in enhanced germplasm protection and securing sustained livelihood benefits for farmers and improved conservation of target varieties

Key results/deliverables:

- Implementation of GRFA conservation and sustainable use plans initiated.

- 500 farmers capacitated in approaches to conservation and sustainable use of GRFA.

- Community seed bank for Shanlan rice established.

- Regular livestock competitions for Wuzhishan pig and Jiaji duck organized.

- Eco-compensation demonstration implemented.

- Knowledge products on lessons learned prepared and disseminated.

- Under this output, the implementation of the GRFA conservation and sustainable use plans developed under Output 2.1 will be initiated. Microgrants will be disbursed to local farmers and agricultural associations based on proposals reviewed by the landscape partnership working groups. Expected interventions include introduction of new farming approaches, increase yield, demonstrate improved breeding practices, improve management of agricultural chemicals and wastes, strengthen management of invasive alien species, etc. A service provider will be retained to manage the microgrant funds, in close cooperation with the landscape partnership working groups. Participation of women and youth will be facilitated, with an estimated 50% of the available microgrant funds earmarked for women’s and youth groups.

- GEF resources are also allocated for enhancing protection of genetic resources, through establishing a community seed bank for Shanlan rice, and for organizing annual livestock competitions for Wuzhishan pig and Jiaji duck. These actions will be designed by GRFA specialists in consultation with local governments, farmers, agricultural associations and cooperatives, agricultural enterprises and research and academic institutions, with cofinancing contributions from local government and enterprise sector partners.

- Demonstration of the non-market incentive mechanism of allocating eco-compensation funds for promoting conservation and sustainable use of GRFA varieties will be implemented, based on the plan developed under Output 1.3. The project will facilitate monitoring and evaluation of the results of this demonstration and the implementation of the GRFA conservation and sustainable use plans, and distilling information into case studies and other knowledge products, for dissemination on the project and C-SAP program knowledge-sharing platform and through communication locally on social media, print media, radio and local television.

- Indicative activities under Output 2.2 include the following:

| 2.2.1. | Through collaboration with the landscape partnership working groups, develop calls for proposals for implementing actions in the GRFA conservation and sustainable plans, such as adding value on farm, management of invasive alien species, improved access to good quality seed and breeding stock, etc., and facilitating equitable participation by women and youth. |
| --- | --- |
| 2.2.2. | Review proposals for implementing actions in the GRFA conservation and sustainable use plans and prepare microgrant agreements with beneficiaries. |
| 2.2.3. | Facilitate implementation of the GRFA conservation and sustainable use plans, disbursing micro grants for selected interventions and providing advisory support to local beneficiaries, to introduce new farming approaches, increase yield, demonstrate improved breeding practices, improve management of agricultural chemicals and wastes, strengthen management of invasive alien species, etc. |
| 2.2.4. | Design, procure and establish a community seed bank for Shanlan rice in Qiongzhong County, collaborating with local government units, farmers, women’s groups and other community organizations, agricultural associations and enterprises, to provide an enduring mechanism for enhancing the germplasm of this GRFA variety. |
| 2.2.5. | Plan and organize annual livestock competitions for Wuzhishan pig in Baisha county, collaborating with local government units, farmers, women’s groups and other community organizations agricultural associations and enterprises, to provide an enduring mechanism for enhancing the germplasm of this GRFA variety. |
| 2.2.6. | Plan and organize annual livestock competitions for Jiaji duck in Qionghai City, collaborating with local government units, farmers, women’s groups and other community organizations agricultural associations and enterprises, to provide an enduring mechanism for enhancing the germplasm of this GRFA variety. |
| 2.2.7. | Implement the demonstration plan developed under Output 1.2 on non-market incentivized GRFA conservation through allocation of eco-compensation funds within the Central Highlands area. |
| 2.2.8. | Carry out participatory monitoring and evaluation of the implementation of the GRFA conservation and sustainable use plans, including assessment of achievement of gender mainstreaming objectives, communicating the results to the local communities and disseminating information on the C-SAP knowledge management platform. |
| 2.2.9. | Prepare knowledge products on the community interventions and disseminate through the knowledge management platform developed under Output 4.2, targeting specific stakeholder groups, including women’s groups, youth groups, agricultural enterprises, etc. |
| 2.2.10. | Organize and convene workshops, sharing best practices and lessons learned on application of traditional ecological knowledge for GRFA conservation and sustainable use. |

Output 2.3: Agrobiodiversity supply and value chains of the target GRFA varieties enhanced through strengthened marketing capacities and expanded application of marketing tools, including cultural value branding and product certification

Key results/deliverables:

- Supply/value chain analyses completed for the target GRFA varieties.

- Business development plans for the three target GRFA varieties.

- Implementation of the GRFA business development plans.

- Promotional and information products regarding GRFA offerings.

- The focus of Output 2.3 is focused on enhancing supply and/or value chains of the target GRFA varieties and strengthening marketing capacities of farmers, agricultural associations and enterprises. Based on supply/value chain analyses completed for the three target GRFA varieties, business development plans will be developed for expanding and improving market development and marketing of GRFA products and offerings. A standard code of practice for GRFA conservation will be prepared and voluntary adoption of the code by agricultural associations, enterprises, community-based organizations and other operators will be facilitated.

- Microgrant assistance will be made available to farmers, agricultural associations and enterprises on based on proposals reviewed by the landscape partnership working groups. Similar to the arrangements under Output 2.2, a service provider will be hired to manage the microgrant fund. Indicative types of support include assistance for (a) developing niche markets; (b) obtaining or improving the marketing of product certification; (c) promoting cultural preference/branding; (d) strengthening collective marketing approaches; (e) improving quality control of GRFA products and offerings; (f) developing specific agro-ecotourism experiences; (g) introducing or expanding traceability schemes for GRFA varieties; (h) promoting recognition of tradition knowledge; etc.

- Project resources are also allocated for preparing promotional and information products regarding GRFA offerings and disseminated on the project and C-SAP program knowledge-sharing platforms.

- Indicative activities under Output 2.3 include:

| 2.3.1. | Carry out supply or value chain analyses, elaborating specific recommendations into business development plans for each of the target GRFA varieties, including strategies for ensuring equitable participation by women and youth. |
| --- | --- |
| 2.3.2. | Develop a standard code of practice for GRFA conservation in the three target counties and facilitate voluntary adoption of the code of practice by enterprises, women’s groups and other community organizations and other operators. |
| 2.3.3. | Establish or strengthen a women’s GRFA marketing group in each of the three demonstration landscapes, facilitating participation in business development activities. |
| 2.3.4. | Based on the recommended actions in the business development plans and in collaboration with public and private partners, provide technical and microgrant assistance to farmers, women’s groups and other community organizations, agricultural associations and enterprises, including but not limited to: (a) developing niche markets; (b) obtaining or improving the marketing of product certification; (c) promoting cultural preference/branding; (d) strengthening collective marketing approaches; (e) improving quality control of GRFA products and offerings; (f) developing specific agro-ecotourism experiences; (g) introducing or expanding traceability schemes for GRFA varieties; (h) promoting recognition of traditional knowledge; etc. |
| 2.3.5. | Prepare promotional and informative products regarding GRFA offerings and disseminate on the knowledge and communication platform developed under Output 4.2. |

Output 2.4: Farmers, agricultural associations and enterprises capacitated and conservation and sustainable use of GRFA improved through partnership development and organizational strengthening, with a focus on increasing participation by women and youth

Key results/deliverables:

- Capacity development strategies and action plans for farmers, agricultural associations and enterprises for each of the three target GRFA varieties.

- 500 farmers capacitated in best practice approaches to conservation and sustainable use of GRFA.

- One provincial and three county level GRFA trade fairs, promoting GRFA products and offerings and showcasing nutritional and traditional value of GRFA varieties.

- Output 2.4 is designed to strengthen the capacities of farmers, agricultural associations and enterprises through targeted training, partnership development and organizational strengthening. The preliminary capacity needs assessment and indicative capacity development plan for farmers made at the PPG phase (see Annex M) will be updated, and microgrant resources made available for delivering capacity development assistance in cooperation with existing training institutions and other capacity development service providers. The indicative types of assistance include   (a) improving financial management and other small business skills; (b) expanding online trading approaches; (c) improving quality control of GRFA products and offerings; (d) specific trainings on expanding inclusion of women and youth; etc.

- Under this output, the project will help organize one provincial and three county level trade fairs, promoting GRFA products and offerings and showcasing nutritional and traditional values of GRFA varieties, and facilitating partnership opportunities with public and private partners.

- Indicative activities under Output 2.4 include:

| 2.4.1. | Update information gathered during the PPG phase on capacities of farmers, agricultural associations and enterprises regarding GRFA conservation and sustainable of GRFA and produce capacity development strategies and action plans for the three target GRFA varieties. |
| --- | --- |
| 2.4.2. | Deliver capacity development actions to farmers and members of agricultural associations and enterprises, according to the capacity development strategy and action plan for each of the three demonstration landscapes and ensuring equitable participation by women and youth. |
| 2.4.3. | Based on the recommended actions in the capacity development plans and in collaboration with existing training institutions and service providers, provide technical and microgrant assistance to farmers, agricultural associations and enterprises, including but not limited to: (a) improving financial management and other small business skills; (b) expanding online trading approaches; (c) improving quality control of GRFA products and offerings; (d) specific trainings on expanding inclusion of women and youth; etc. |
| 2.4.4. | Carry out knowledge transfer and partnership development exchanges by bringing stakeholders from the target counties to other areas in the province or other parts of China. |
| 2.4.5. | Organize one trade fair in Hainan Province and one in each of the three target provinces, promoting GRFA products and offerings, showcasing nutritional and traditional values of GRFA varieties and to facilitate marketing and partnership opportunities, with a special focus on inclusion of women and youth. |

Component 3: Mainstreaming of approaches and strengthened institutional capacity

Total Cost: USD 1,767,300; GEF project grant requested: USD 255,300; Cofinancing: USD 1,512,000

- This component includes strengthening institutional capacities, a requisite for successful implementation of the agrobiodiversity strategy and action plan in the years to come. Integrating incentivized GRFA approaches into the 5-year work program of the Hainan DARA will provide a committed framework for implementation of the priority actions included in the agrobiodiversity strategy and action plan. And, expanding the best management approaches demonstrated under the project to landscapes beyond the demonstration landscapes in Component 2 will be facilitated through development of a replication strategy and upscaling plan and initiating implementation in at least replication landscapes. The baseline situation and incremental reasoning for Component 3 are summarized below in Table 9.

Table 9: Summary of baseline and incremental reasoning for Component 3

| Summary of Baseline Situation | Incremental Reasoning |
| --- | --- |
| Output 3.1: Institutional capacities strengthened to facilitate and oversee incentive-based in-situ conservation and sustainable use of GRFA, through targeted trainings, learning by doing participation and knowledge transfer |  |
| Hainan Province is a major agricultural center in China, and the institutional stakeholders are highly qualified, mostly in modern agricultural practices. The provincial Department of Agriculture and Rural Affairs oversees agricultural support services at the county and township levels, and there are several research institutions and universities providing technical advisory services and research inputs. Institutional capacities to implement agrobiodiversity conservation and sustainable use initiatives is relatively low. These capacity shortcomings extend to other agencies and organizations having cross-cutting mandates associated with agrobiodiversity management, including the Department of Ecology and Environment, Department of Natural Resources, Department of Education, Office of Poverty Alleviation, Department of Water Resources, etc. More information is included in the Preliminary Capacity Development Needs Assessment, Baseline Scorecard and Indicative Capacity Development Plan in Annex M. | The project will deliver a targeted institutional capacity development plan, aimed at building upon existing structures and services and introducing training modules on agrobiodiversity topics and providing learning-by-doing experiences, focusing on strengthening and expanding involvement of women and youth. Leveraging the programmatic approach of the C-SAP program, GEF funds are also earmarked for organizing knowledge transfer learning exchanges domestically and internationally, providing opportunities to learn from best practice approaches in agrobiodiversity conservation. More information is included in the Preliminary Capacity Development Needs Assessment, Baseline Scorecard and Indicative Capacity Development Plan in Annex M. |
| Output 3.2: Provincial and target county agricultural institutions have incorporated incentive mechanisms for in-situ agrobiodiversity conservation and sustainable use as part of agency workplans |  |
| Under the baseline situation, agriculture sector work programs, e.g., the 13th 5-year plan, have limited focus on agrobiodiversity conservation. Consequently, initiatives on conservation and sustainable use of GRFA varieties are mostly based on nonrecurrent, project-based funding. | Through this output, the project will facilitate mainstreaming agrobiodiversity conservation, including the incentivized approaches demonstrated under Component 2, into the work programs of the provincial DARA and the county Agricultural Bureaus where the three demonstrations were implemented. The work programs will include specific targets for strengthening inclusion of women and youth into the agrobiodiversity conservation and sustainable use. |
| Output 3.3: Approaches developed under the project are extended to additional agricultural landscapes covering other varieties, generating expertise and support for scaling up across the province |  |
| Hainan Province covers 33,920 km2 and is administered through 4 prefectures, 20 counties and 218 townships. Under the baseline situation, there is limited exchange across counties regarding dissemination of new approaches, or experiences on specific projects, including those funded with international donor resources. | The project will provide incremental support in facilitating upscaling in other landscapes in the province, including assistance in completing participatory landscape assessments and developing GRFA conservation and sustainable use plans, using the approaches and protocols deployed in Component 2. Moreover, farmer exchanges will be organized, allowing firsthand knowledge transfer among farmers, as well as agricultural associations/organizations and enterprises. Expanding agrobiodiversity opportunities to other parts of the province is certainly of interest to the enterprise sector; the project will help facilitate establishing partnerships, with public and private sector stakeholders. |

Outcome 3: Demonstrated approaches mainstreamed and capacities strengthened to facilitate upscaling of incentivized conservation and sustainable use of GRFA

- Results expected through achievement of Outcome 3 include:

- Strengthened institutional capacity of the provincial DARA for in-situ conservation and sustainable use of GRFA, as indicated by the capacity development scorecard.

- Upscaling of participatory approaches for the conservation and sustainable use of GRFA through completion of 2 participatory landscape assessments in replication landscapes, 2,200 ha under participatory management of agrobiodiversity beyond the demonstration landscapes, and at least 3 additional GRFA varieties having eco-certification in the province.

- Incentivized approaches of in-situ conservation and sustainable use of GRFA integrated into 14th 5-year plan for DARA.

Output 3.1: Institutional capacities strengthened to facilitate and oversee incentive-based in-situ conservation and sustainable use of GRFA, through targeted trainings, learning by doing participation and knowledge transfer

Key deliverables/results:

- Capacity development plan for the project;

- 110 institutional staff members capacitated on in-situ conservation and sustainable use of GRFA.

- Achieving meaningful expansion of agrobiodiversity conservation and sustainable use will depend on  an effective institutional enabling environment, which is largely influenced by the capacities of institutional staff members. The activities under this output are focused on strengthening institutional through., delivering a series of trainings, supporting implementation of technical guidelines and strengthening partnerships.

- The results of the preliminary capacity needs assessment and indicative capacity development plan completed during the PPG phase (see the Preliminary Capacity Development Needs Assessment, Baseline Scorecard and Indicative Capacity Development Plan in Annex M) will be updated and finalized during project inception.

- The indicative capacity development plan has a target of 110 institutional staff members, distributed across provincial and local government agencies, as well as research and academic institutions. The indicative breakdown is shown below in Table 10.

Table 10: Indicative breakdown of institutional capacity development beneficiaries

| Institution | Indicative number of staff members included in project institutional capacity development plan |
| --- | --- |
| Department of Agriculture and Rural Affairs | 18 |
| Department of Natural Resources (incl. Forestry, Land Resources) | 8 |
| Department of Ecology and Environment | 8 |
| Department of Water Resources | 2 |
| Office for Poverty Reduction | 2 |
| Department of Education | 2 |
| Department of Finance | 2 |
| All Women’s Federation, Hainan Province | 1 |
| Youth League Committee, Hainan Province | 1 |
| Baisha Li Autonomous County Animal Husbandry Bureau | 19 |
| Da’an Township Agriculture Station | 1 |
| Qiongzhong Li and Miao Autonomous County Agriculture Bureau | 19 |
| Shang’an Township, Agriculture Station | 1 |
| Qionghai City Animal Husbandry Bureau | 19 |
| Shibi Township, Agriculture Station | 1 |
| Chinese Academy of Tropical Agricultural Sciences (CATAS) | 2 |
| Hainan Academy of Sciences (HAAS) | 2 |
| Hainan University | 2 |
| TOTAL | 110 |

- Site-level learning will focus on implementation capacities including for the field interventions designed under Component 2 of the project, with capacity building delivered through a learning-by-doing approach. The domestic knowledge transfer trainings are planned in collaboration with the other child projects under the C-SAP program. Resources are also allocated under this output for international knowledge transfer exchange, providing key stakeholders an opportunity to directly observe and interact with stakeholders involved in international best practices in conservation and sustainable use of agrobiodiversity. The focus will be on senior staff members who are deemed potential “change agents”, i.e., persons having the authority and aptitude to proactively advocate for integration of the knowledge gained into sector level plans and strategies. These international trainings will also be designed to deliver specific competencies. The location and thematic focus of the trainings will be determined as part of validating the capacity development plan for the project during the inception phase and regularly updating the plan, following an adaptive management approach as circumstances and priorities might change over the course of the 5-year project.

- Through the networking associated with arranging the international trainings and international experts, the project will help facilitate improved partnerships. The International Cooperation Office of the Hainan DARA will be able to help maintain and expand these partnerships after GEF funding ceases.

- Indicative activities under Output 3.1 include:

| 3.1.1. | Verify the capacity needs assessment completed during the PPG phase and design an institutional capacity development plan, which will be rolled out over the course of the project and also advocated to be an integral part of the GRFA work programs produced in Output 3.2. |
| --- | --- |
| 3.1.2. | Develop capacity-building materials, guidelines, training manuals and identify specific trainings and/or courses through collaboration with national and provincial research, academic and farmer field school stakeholders, and including specific capacity development actions addressing women and youth. |
| 3.1.3. | Deliver GRFA conservation and sustainable use training to provincial and county institutional stakeholders, including the provincial Department of Agriculture and Rural Affairs, county Agricultural Bureaus and other members of the GRFA inter-sectoral coordination committee. |
| 3.1.4. | Organize domestic knowledge and international transfer trainings, e.g., through cross visits to other interventions implemented on other C-SAP child projects and complimentary programs and initiatives. |
| 3.1.5. | Deliver targeted training to women professionals, organized in collaboration with the provincial Women’s Federation. |
| 3.1.6. | Deliver site-level training for young agricultural professionals, coordinating with field activities under Component 2 to provide hands-on experience and to foster employment opportunities among institutional and business sector stakeholders. |

Output 3.2: Provincial  and target county agricultural institutions have incorporated incentive mechanisms for in-situ agrobiodiversity conservation and sustainable use as part of agency workplans

Key results/deliverables:

- Best practices guideline for incentivized approaches to participatory in-situ conservation and sustainable use of GRFA.

- Recommended work program for inclusion into the 14th 5-year plan for the Hainan DARA.

- Stakeholder workshop convened, sharing information on incentivized approaches to in-situ conservation and sustainable use of GRFA.

- Under this output, the best practices demonstrated in Component 2 for incentivized approaches to participatory conservation and sustainable use of GRFA will be mainstreamed into agriculture sector planning frameworks. The project will support development of a best practices guideline that will inform draft work programs for the Hainan DARA and the agriculture bureaus of Baisha County, Qiongzhong County and Qionghai City. Project resources are also allocated for organizing a stakeholder workshop, in which the best practices guideline and draft work plans will be shared and discussed. The project management team, along with the GRFA coordination committee will actively advocate for inclusion of the draft work programs into the 14th 5-year plan before the end of the project.

- Indicative activities under Output 3.2 include:

| 3.2.1. | Develop a best practices guideline for incentivized approaches to participatory in-situ conservation and sustainable use of GRFA. |
| --- | --- |
| 3.2.2. | Support integration of incentivized approaches for participatory in-situ conservation and sustainable use of GRFA into gender and youth inclusive results-based work programs, included in the 5-year plans for the provincial Department of Agriculture and Rural Affairs and the county Agricultural Bureaus of Baisha County, Qiongzhong County and Qionghai City. |
| 3.2.3. | Organize one provincial and three county level stakeholder workshops, to disseminate information on incentivized approaches for participatory GRFA conservation and sustainable use. |
| 3.2.4. | Provide concerted advocacy for ensuring GRFA approaches are reflected in the provincial 5-year plan. |

Output 3.3: Approaches developed under the project are extended to additional agricultural landscapes covering other varieties, generating expertise and support for scaling up across the province

Key results/deliverables:

- Replication strategy and upscaling plan.

- Knowledge transfer exchange carried out in at last one replication landscape.

- Completion of participatory GRFA landscape assessments in two replication landscapes.

- GRFA conservation and sustainable use plans for two additional GRFA varieties in replication landscapes.

- Under this output, the replication of the approaches demonstrated in Component 2 will be facilitated through firstly development a replication strategy and upscaling plan, in close consultation with provincial DARA officials and the provincial GRFA coordination committee. The project will finance a knowledge transfer exchange to at least one replication landscape or inviting representatives from a replication landscape to visit one or more of the demonstration landscapes under Component 2.  Applying the protocol developed under Output 2.1, the project will support, with the majority of funding coming from cofinancing contributions, participatory GRFA landscape assessments in two replication landscapes.

- Replication will be further facilitated through supporting the development of GRFA conservation and sustainable use plans for two additional GRFA varieties in the two replication landscapes. These plans will provide provincial and local partners with an actionable framework, which specific funding opportunities for governmental, enterprise or domestic or international donor partners.

- Indicative activities under Output 3.3 include:

| 3.3.1. | Develop a replication strategy and upscaling plan, identifying opportunities for implementing GRFA in-situ conservation and sustainable approaches demonstrated on the project to other areas in the province. |
| --- | --- |
| 3.3.2. | Organize knowledge transfer exchanges with farmers, agricultural associations and enterprises in the demonstration landscapes with stakeholders in the replication landscape(s). |
| 3.3.3. | Support participatory landscape GRFA assessments in minimum two other landscapes in the province. |
| 3.3.4. | Provide technical assistance in developing GRFA conservation and sustainable use plans for minimum two other landscapes in the province. |

Component 4: Knowledge management and monitoring & evaluation

Total Cost: USD 1,741,023; GEF project grant requested: USD 253,023; Cofinancing: USD 1,488,000

- This component focuses on putting in place effective project monitoring and evaluation procedures for ensuring efficient use of resources, inclusive participation, and improved knowledge management. A knowledge management action plan for the project will be developed and implemented based on the results of a baseline knowledge, attitudes and practices (KAP) survey and the C-SAP program knowledge management strategy. Funds are also allocated for improving the GRFA provincial database, increasing the functionality of the system, improving awareness of farmers and other key stakeholders and encouraging broader use among the stakeholder community. The baseline situation and incremental reasoning for Component 4 are summarized below in Table 11.

Table 11: Summary of baseline and incremental reasoning for Component 4

| Summary of Baseline Situation | Incremental Reasoning |
| --- | --- |
| Output 4.1: Effective monitoring & evaluation supported by a representative steering committee and through cross-collaboration on the C-SAP program |  |
| The implementing partner, the Hainan provincial DARA, is committed to the successful implementation of the project, supported through USD 9.92 million in recipient government cofinancing. DARA has passed the UNDP capacity assessment and harmonized approach to cash transfers (HACT) assessment (see Annex I). Commitment is further demonstrated through the nomination of the Deputy Director General of DARA as the National Project Director and designation of focal points among county agriculture bureaus and township agricultural stations. | GEF funds will support one full-time position within the project management office (PMO): Project Coordinator. The PMO will be embedded into the DARA operations in Haikou and receive guidance by the NPD, day-to-day support from the Project Director and interact with technical and administrative staff in the department. The PMO will also be supported by the focal points among the county agricultural bureaus, where the demonstration activities are planned under Component 2. The project will contribute to the C-SAP programmatic approach, through the program knowledge management platform, exchange visits and steering committee meetings, and program level monitoring and evaluation activities. |
| Output 4.2: Knowledge, attitudes and practices among farmers, governmental agencies, enterprises and the public improved through implementation of a targeted knowledge management strategy and action plan |  |
| Although most institutional stakeholders have a strong knowledge base in modern agricultural practices and local farmers have deep-seated traditional knowledge, attitudes and practices, the baseline surveys made during the project preparation phase confirm that there are knowledge gaps with respect to agrobiodiversity conservation and sustainable use. And, there are shortcomings with respect to transferring knowledge gained among the research/academic sector to practical approaches that are implementable in the field. Stakeholders including government, administrative agencies, institutes, universities, enterprises, and farmers have limited knowledge and low levels of awareness of conservation and utilization of local GRFA, mainly because of lack of training and advocacy for new technologies and new varieties by the governments. There is also insufficient media coverage on GRFA. Most stakeholders, even those working in related areas such as crop production, environment protection, etc., are lacking knowledge on the importance, main threats, root causes, potential benefits to farmers’ livelihoods, potential impacts to sustainable development and climate change, etc. More information is included in the Baseline Report on Policy, Governance and Knowledge Management in Annex K; the Baseline Report on Demonstration Landscapes in Annex L; and the Preliminary Capacity Development Needs Assessment, Baseline Scorecard and Indicative Capacity Development Plan in Annex M. | Effective knowledge management is a key element to the project strategy, and the project will develop a targeted knowledge management strategy and action plan, according to results of a baseline knowledge, attitudes and practices (KAP) survey and in line with the program level knowledge management strategy. This project will directly participate in the knowledge sharing mechanisms under the C-SAP program, contributing knowledge gained through the project and disseminating lessons learned. In addition, the project aims to strengthen provincial capacity for knowledge management on agrobiodiversity conservation through technical reports, online news articles, awareness materials and technical briefs, case studies and best practices – shared on the knowledge platform that will be developed under the C-SAP1 (national agrobiodiversity) project. The project will organize a series of awareness raising actions focusing on demonstrating the importance, main threats, root causes, potential impacts to sustainable development and climate change etc. to stakeholders at provincial, county, township and village levels from the very beginning of the project. Utilizing as many types of media as practicable, results of the project will be publicized and advocated through development of best practices, lessons, etc. The knowledge management strategy will address provincial level outreach, not only within the three demonstration landscapes. A framework for the design of the KAP survey is presented in Annex N. |
| Output 4.3: A provincial agrobiodiversity database is strengthened to support ongoing monitoring of agroecosystems health and to collate information on varieties, coverage, farming practices and the impact of incentive mechanisms |  |
| Information management on agrobiodiversity resources in the province is fragmented across governmental agencies and research institutions. DARA has developed a database for agrobiodiversity, but the system has limited scope, is not sufficiently interactive among relevant stakeholder groups. More information is included in the Baseline Report on Policy, Governance and Knowledge Management in Annex K | The project will support DARA in enhancing their existing information management system with broader representation of agrobiodiversity varieties, enabling more effective monitoring and evaluation of agroecosystem health, coverage and diversity of traditional crops and livestock, and uptake of incentive-based mechanisms. |

Outcome 4: Knowledge, attitudes and practices improved, and knowledge management structures enhanced to broaden participation in the conservation and sustainable use of GRFA

- Results expected through achievement of Outcome 4 include:

- Improved understanding among key stakeholder groups of the value of GRFA and the importance of in-situ conservation.

- Adoption of participatory knowledge management systems, including operationalization of an improved GRFA agrobiodiversity database, and dissemination of lessons learned, case studies and other posts on the C-SAP program knowledge and communication platform.

Output 4.1: Effective monitoring & evaluation supported by a representative steering committee and through cross-collaboration on the C-SAP program

Key results/deliverables:

- Project inception workshop and report.

- Annual project steering committee meetings convened and reported.

- One C-SAP program steering committee meeting hosted and reported.

- Project progress reports and other monitoring & evaluation deliverables.

- Midterm review report.

- Terminal evaluation report.

- Final project report.

- The activities under this output are designed to put in place enabling procedures and protocols to facilitate effective monitoring & evaluation. The project inception workshop, to be held within three months of signing of the project document, is a critical milestone on the implementation timeline, providing an opportunity to validate the project document, including the environmental and social management framework; confirming governance implementation arrangements, including agreements with responsible parties; assessing changes in relevant circumstances and making adjustments to the project and program results framework accordingly; verifying stakeholder roles and responsibilities; updating the project risks and agreeing to mitigation measures and responsibilities; and agreeing to the multi-year work plan. An inception workshop report will be prepared and disseminated among the project steering committee members.

- One of the responsibilities of the project management team is to develop the annual work plans and budgets. Annual stakeholder workshops will be organized with the support of the provincial GRFA coordination committee, to discuss plans for the subsequent year, issues associated with implementation of the project, and recommended adaptive management measures on an as-needed basis.

- The project steering committee (PSC) will be the main platform for high-level and strategic decisions, and the proposed compositions of the committee provides for efficient and representative feedback (see Section VIII: Governance and Management Arrangements). Annual PSC meetings are planned. For budgetary purposes, PSC meetings in Years 1 and 5 are planned in Haikou, and the meetings in Years 2, 3 and 4 are planned to be held at the counties where the three demonstration landscapes are located, enabling the committee members to observe first-hand progress and issues. Terms of Reference for the steering committee are included in Annex C. The project will also host one C-SAP program steering committee meeting, tentatively scheduled for Year 3.

- According to GEF requirements, two independent evaluations will be carried out of the project, a midterm review and terminal evaluation. At least one month before the midterm and terminal evaluations, the project will contract a local institute, local consultant or other service provider to carry out assessments of the UNDP Capacity Development Scorecard and other results requiring verification/analysis.

- Indicative activities under Output 4.1 include:

| 4.1.1. | Organize the project inception workshop, including review of multi-year work plan, project results framework, stakeholder engagement plan, social and environmental screening procedure, etc., and prepare an inception report to provide guidance for initiating the implementation of the project. |
| --- | --- |
| 4.1.2. | Organize annual project steering committee meetings, preceded by stakeholder workshops and supported by the provincial GRFA coordination committee as part of annual work plan development and adaptive management review sessions. |
| 4.1.3. | Host one C-SAP program steering committee meeting, highlighting results achieved by the Hainan Province and providing an opportunity to share lessons and experiences with the other child projects. |
| 4.1.4. | Provide monitoring and evaluation of the project progress and results, facilitating adaptive management, preparing project progress reports and organizing periodic financial auditing services. |
| 4.1.5. | Procure and support an independent midterm review of the project, according to UNDP and GEF guidelines. |
| 4.1.6. | Procure and support an independent terminal evaluation of the project, according to UNDP and GEF guidelines. |
| 4.1.7. | Prepare the final report for the project; including the PIR for the last year of implementation, the terminal evaluation report, and the management response to the terminal evaluation report. |

Output 4.2: Knowledge, attitudes and practices among farmers, governmental agencies, enterprises and the public improved through implementation of a targeted knowledge management strategy and action plan

Key results/deliverables:

- Knowledge, attitudes and practices (KAP) surveys made at project inception (baseline) and at the end of the project.

- Knowledge management action plan for the project.

- Advocacy of project results through participation in national, regional and international conference, workshops, seminars and other events.

- Awareness raising and advocacy campaigns on specific themes, delivered by various methods, including social media, print media, radio, local and provincial television, etc.

- Under this output, a knowledge management (KM) action plan for the project will be developed, based upon the results of a baseline knowledge, attitudes and practices (KAP) survey and the C-SAP program KM strategy. A framework for the KAP survey is presented in Annex N to the project document. A few examples of issues assessed as part of the KAP survey include, but are not limited to the following:

- Perceptions of target stakeholder groups related to agrobiodiversity conservation and its impacts on their communities;

- Knowledge of agrobiodiversity and its benefits;

- Attitudes and practices of target stakeholder groups towards proposed incentive mechanisms;

- Differences in knowledge, attitudes and practices between women and men ... ethnic minorities.

- The range of existing household livelihood activities and diversity of community livelihood options;

- The willingness and ability of farmer households to engage with new or modified GRFA livelihood options; and

- The means of communication best suited for promoting improved agrobiodiversity management.

- The indicative stakeholder groups that will be surveyed include:

- Provincial government institutional stakeholders;

- Local government institutional stakeholders (e.g., county, township and village levels);

- Farmers;

- Agricultural associations and enterprises;

- The KAP survey will be conducted by a qualified service provider/institute recruited through a competitive procurement process. Indicative end targets for measuring changes to knowledge, attitudes and practices are presented in the project results framework; these will be reviewed and finalized as part of the baseline KAP survey. And an end-of-project KAP survey will be made during the last year of implementation, to assess actual changes realized.

- The KM action plan will cover knowledge management elements across the project, e.g., in the design of trainings and in the way in which knowledge shared. Knowledge products will include case studies distilled from the results achieved on the project and will also include awareness raising materials to support advocacy and public participation campaigns. Project case studies, lessons learned, generated knowledge products, etc. will be uploaded onto the project and program knowledge-sharing platforms, and also communicated through various methods, including social media, print media, radio, local and provincial television, etc.

- Advocating the global environmental benefits generated through the project will be part of the KM action plan. Participating in national, regional, and international conferences, workshops and seminars will be one way to share information and promote the global benefits generated.

- Indicative activities under Output 4.2 include:

| 4.2.1. | Design, administer and interpret a baseline knowledge, attitudes and practices (KAP) survey, assessing knowledge, attitudes regarding the importance and value associated with conservation of GRFA among target stakeholder groups disaggregated by gender. |
| --- | --- |
| 4.2.2. | Based on the results of the baseline KAP survey of this project and the knowledge management strategy for the C-SAP program, develop and regularly update a knowledge management action plan for the project, including specific KM actions for target stakeholder groups and ensuring equitable outreach to women and youth. |
| 4.2.3. | Develop a knowledge and communication platforms for the project, in coordination with the information systems operated by the provincial Department of Agriculture and Rural Affairs and with links to C-SAP program website and knowledge platform. |
| 4.2.4. | Advocate the global environmental benefits generated through the project by participating in national, regional and international conferences, workshops, seminars and other events. |
| 4.2.5. | Organize awareness raising and advocacy campaigns, focused on specific themes and aimed at defined target groups, e.g., farmers, women’s groups, governmental agencies, enterprises and the public, through methods identified in the knowledge management action plan, e.g., social media, print media, radio, local and provincial television, etc. |
| 4.2.6. | Organize a targeted awareness event for young people, encouraging interest and disseminating knowledge on conservation and sustainable use of traditional GRFA varieties. |
| 4.2.7. | Administer and interpret the results of an end-of-project KAP survey, assessing changes in knowledge, attitudes and practices regarding the importance and value associated with conservation of GRFA. |

Output 4.3: A provincial agrobiodiversity database is strengthened to support ongoing monitoring of agroecosystems health and to collate information on varieties, coverage, farming practices and the impact of incentive mechanisms

Key results/deliverables:

- Improved provincial GRFA database.

- Stakeholders trained on operation of the database and utilizing the database for monitoring and evaluating agro-ecosystem health and of the diversity and coverage of GRFA varieties.

- Under this output, an existing provincial agrobiodiversity database will be improved, expanding access and increasing the functionality of the system as a decision-making tool. Through technical assistance arrangements, a GRFA specialist and database specialist will work with Hainan DARA staff members and other involved stakeholders in improving the agrobiodiversity database. The indicative plans for the database include providing additional information on diversity status and coverage of GRFA varieties and market information, broadening usage of the system among both governmental and non-governmental stakeholders.

- The improved database will be populated with information gathered through the outputs delivered under Component 2 on the three target GRFA varieties. This information will provide a solid foundation for training stakeholders on the use of the database and on using the system for monitoring and evaluating agro-system health of specific agricultural landscapes.

- Indicative activities under Output 4.3 include:

| 4.3.1. | Update the information gathered during the PPG phase on the database needs and prepare a database development plan, in coordination with provincial stakeholders and consistent with the C-SAP knowledge management strategy, with the plan including sustainable financing arrangements for ensuring the database is maintained following completion of the project. |
| --- | --- |
| 4.3.2. | Adapt and upgrade a provincial GRFA database to support monitoring of agroecosystem health and to share information on GRFA varieties, including information on the genetic resources and traditional knowledge of the three target varieties on the project. |
| 4.3.3. | Deliver training on the operation and updating of the GRFA database. |
| 4.3.4. | Deliver training on monitoring of agroecosystem health and of the diversity and coverage of GRFA varieties. |

Partnerships:

- The project strategy has a strong emphasis on building upon baseline activities implemented by project partners, as well as on establishing new and strengthening existing partnerships to ensure the sustainability of the results achieved. One of the advantages of the programmatic approach of the C-SAP program is the benefit of partnerships across the child projects. MARA, as the lead implementing partner for the C-SAP program, will support program level coordination through the C-SAP Program Coordination Office in Beijing and the Program Steering Committee. The national IAS project (C-SAP2) will maintain a Program Coordination, Monitoring and Evaluation Secretariat  supported by a full-time M&E/Coordination Officer, who will help coordinate program reporting and M&E activities. The national agrobiodiversity project (C-SAP1) and the climate smart agriculture project (C-SAP5) will jointly help coordinate program level knowledge management, including management of the C-SAP program website and knowledge platform. As the lead GEF agency for the program, UNDP will provide guidance to the implementing partners on strategic, technical and administrative issues throughout the implementation timeframe, through their country office and the regional technical advisor based at the Asia-Pacific regional hub.

- Some of the key related initiatives where partnerships will be fostered are listed below in Table 12.

Table 12: Intersection of related initiatives with project outputs

| Other Initiatives | Main Partner(s) | Other Partners | Intersections with project outputs |
| --- | --- | --- | --- |
| PRC-GEF Partnership Program for Sustainable Agricultural Development (C-SAP) | MARA, UNDP | FAO, World Bank | All outputs; see details in Table 5 |
| PRC-GEF China’s Protected Area System Reform (C-PAR) program | MEE, MNR, UNDP | Provincial Governments, Conservation International | Outputs 4.1, 4.2 |
| Crop Germplasm Resources Protection | MARA | Hainan DARA | Outputs 2.2, 2.4, 3.1, 4.2, 4.3 |
| National 13th 5-Year Plan on Conservation and Sustainable Use of Animal Genetic Resources | MARA | Hainan DARA | Outputs 1.2, 2.2, 2.3, 4.2, 4.3 |
| Hainan Province 13th 5-year Plan (2016-2020) | Hainan Provincial Government | Provincial agencies | Outputs 1.1, 1.2, 1.3, 3.1, 3.2, 3.3, 4.1, 4.2 |
| Eco-compensation programs (key ecological function zone) | Central Government | Hainan Provincial Government, counties in the Central Highlands area | Outputs 1.1, 1.2, 1.3, 2.1, 2.2, 3.1, 3.2, 4.1, 4.2 |
| Hainan’s Biodiversity Conservation Strategy and Action Plan (PBSAP) | Hainan Provincial Government | Dept of Ecology and Environment, other provincial agencies | Outputs 1.1, 1.2, 1.3, 3.1, 3.2, 3.3, 4.2, 4.3 |
| Beautiful Countryside Development | Hainan Provincial Government | DARA, Dept of Urban and Rural Construction, Dept of Transportation | Outputs 1.1, 1.2, 3.1, 3.2, 3.3, 4.2 |
| Agricultural Support Protection Subsidy Fund (Cultivated Land Conservation Protection Subsidy) | Central Government | DARA | Outputs 1.2, 1.3, 2.1, 2.2, 2.3, 2.4, 3.3 |
| Tropical Characteristic High-efficiency Agriculture Development Fund | Hainan Provincial Government | DARA | Outputs 1.2, 1.3, 2.1, 2.2, 2.3, 2.4, 3.3 |
| 2018 Agricultural Project Funds (First Batch) | Hainan Provincial Government | DARA | Outputs 2.1, 2.2, 2.3, 2.4, 3.3 |
| Development of Agricultural Products Public Brands in Hainan Province | Hainan Provincial Government | DARA | Outputs 1.1, 1.2, 1.3, 2.3, 2.4, 3.3, 4.2, 4.3 |
| Study and Demonstration Project on Protection and Use of Technology of Agricultural Wild Plants, a long-term scientific research project | MARA, China Agricultural University, CAAS | DARA | Outputs 2.2, 3.1, 4.2, 4.3 |
| UNDP-supported, GEF-financed project Developing and Implementing the National Framework on Access and Benefit Sharing (ABS) of Genetic Resources and Associated Traditional Knowledge | UNDP | Provincial partners (not including Hainan) | Outputs 1.2, 3.2, 4.2 |
| Globally Important Agricultural Heritage Systems (GIAHS) | MARA, FAO | DARA | Outputs 1.2, 2.1, 3.1, 3.2, 4.2, 4.3 |
| Agrobiodiversity Index program | Bioversity International | CAAS | Outputs 1.2, 2.1, 3.1, 4.2, 4.3 |

- The project will cooperate with other GEF-6 programs in China, including the China’s Protected Area System Reform (C-PAR) program, implemented by UNDP, led by Ministry of Ecology and environment and the Ministry of Natural Resources,  the People's Republic of China and jointly implemented by provincial governments and Conservation International. There are potential synergies with respect to knowledge management and program coordination, as well as participating in the 15th Conference of Parties (COP15) to the Convention on Biological Diversity (CBD) that will be held in China in 2020.

- There is an ongoing UNDP-GEF project in China on Access and Benefit-Sharing (ABS): Developing and Implementing the National Framework on Access and Benefit Sharing (ABS) of Genetic Resources and Associated Traditional Knowledge. The feasibility of introducing ABS systems in Hainan Province in relation to conservation and sustainable use of agrobiodiversity will be carried out under Output 1.2, and the project will reach out to the ongoing ABS project, for lessons learned, recommendations for policy reform, etc.

- At the national level, the project will coordinate with the Crop Germplasm Resources Protection program financed by the Chinese government and run by MARA to protect crop genetic diversity. The proposed project will coordinate with this initiative, drawing on available information on agricultural genetic resources in Hainan, building on research and survey techniques, sharing best practices for establishing community seed banks and participatory incentive-based approaches. In cooperation with the Animal Husbandry Division of the Hainan DARA and MARA, the project will also coordinate with the implementation of the 13th 5-Year Plan on the Conservation and Sustainable Use of Animal Genetic Resources, including best practices in improved breeding techniques and other approaches for enhancing protection of germplasm resources.

- Assisted by the GRFA Coordination Committee, the project will coordinate with the implementation of the Hainan 13th 5-Year Plan, e.g., in the development of the agrobiodiversity strategy and action plan, integrating GRFA approaches into the 14th 5-Year Plan for DARA.

- Two of the three project demonstration landscapes are located in the Central Highlands area. There are several ongoing programs being implemented in this region of the province, including the eco-compensation scheme.

- There are also coordination opportunities with the research/academic sector, including with Study and Demonstration Project on Protection and Use of Technology of Agricultural Wild Plants, a long-term scientific research project organized by the Ministry of Agriculture and jointly implemented by China Agricultural University and the Chinese Academy of Agricultural Sciences (CAAS). The project will also collaborate with Hainan based research institutions, on specific research initiatives focused on GRFA varieties, delivering training to institutional and production level stakeholders, and on knowledge-sharing.

- There are direct partnership opportunities with the provincial government’s program on Development of Agricultural Products Public Brands in Hainan Province. Also, the project will coordinate with the Globally Important Agricultural Heritage Systems (GIAHS) initiative being implemented jointly by the Food and Agriculture Organization of the United Nations (FAO) and MARA. One of the two Nationally Important Agricultural Heritage Systems (NIAHS) in Hainan Province is Shanlan rice, which is also one of the target varieties in the demonstration landscape in Qiongzhong County. The project will promote synergies with the county level partners, and promotion of further protection of traditional production approaches and garnering national and international recognition and partnership opportunities.

- One of the main comparative advantages of UNDP-GEF’s global outreach is the extensive networks of multilateral agencies, inter-governmental bodies, public and private research institutions, academia, civil society, and the private sector. The project will leverage off this institutional capacity through working with regional and international partners, facilitating collaborative partnerships that will help sustain the project results after GEF funding ceases. There are potential collaborative synergies with Bioversity International, an international research organization having a 30-year national level partnership with CAAS, e.g., in the application of the Agrobiodiversity Index, a long-term monitoring tool developed by Bioversity International to help guide governments, investors and enterprises in making decisions that ensure food systems are more diverse and sustainable.

Risks and Assumptions:

- The key risks that could threaten the achievement of results through the chosen strategy are described below in Table 13, along with proposed mitigation measures and recommended risk owners who would be responsible to manage the risks during the project implementation phase.

Table 13: Project risks and proposed mitigation measures

| Risk | Type | Impact and Probability | Proposed Mitigation Measure | Risk Owner |
| --- | --- | --- | --- | --- |
| Brief Description of the risk | Category of risk | Potential effect on project if risk were to occur. Probability P and Impact I: 1 (low) to 5 (high) | What actions have been or will be taken to counter the risk | Who is designated to monitor and act upon this risk |
| 1. Local farmers are resistant to changing their agricultural approaches and practices, not seeing the value of engaging in agrobiodiversity conservation and sustainable use. | Strategic | I=3; P=2 MODERATE | Through a participatory-based approach, the project will implement a range of mechanisms to generate farmer interest and awareness of the values of agrobiodiversity. The project design is predicated on facilitating increased farming of GRFA varieties through establishing and strengthening market-based and non-market-based incentives for farmers, agricultural associations and enterprises. These stakeholders were consulted during the PPG phase and consultations will continue throughout the implementation phase. Stakeholder workshops are planned under Outputs 1.1 and 1.2, to obtain feedback on enabling regulatory frameworks and eco-compensation schemes. For the community level activities planned in Component 2, landscape partnership working groups will be established for each of the three demonstration landscapes and have equitable stakeholder representation, including farmers. The KAP survey planned under Output 4.2 will be designed to identify specific gaps in knowledge, attitudes and practices, and the knowledge management strategy and action plan include specific actions that increase awareness and encourage changes in practices, building ownership at the grassroots level for engagement into in-situ conservation and sustainable use of GRFA. | Project Coordinator, Project Director, LGU focal points, farmers |
| 2. Lack of qualified and available project coordinator candidates. | Operational | I=2; P=2 LOW | The Project Coordinator position has an important function on the project, and it is important to fill this position with a qualified and motivated candidate. Recruitment of the Project Coordinator position will start as early as possible, and the UNDP will assist the Implementing Partner in recruitment of the Project Coordinator, reviewing applications and participating in interview processes. | NPD, UNDP |
| 3. Conflicting policy directions of the Chinese Government that encourage the extension of the growing areas of staple crops or the promotion of new varieties to support food security. | Political | I=3; P=1 | The project will be implemented by the Hainan DARA, a major provincial policymaker in agriculture. Both DARA and the program level implementing partner MARA, are committed to expanding knowledge and update of agrobiodiversity management in Hainan Province and throughout China. DARA will be able to integrate the directions of this project within broader policy directions and sector plans. The project will also raise awareness of provincial decision makers on the importance of in-situ agrobiodiversity conservation to food security. | NPD, LGU units, GRFA Intersectoral Coordination Committee, Project Coordinator |
| 4. Inability to establish strong market drivers that provide effective incentives and/or market fluctuations affect the business prospects of GRFA products. | Strategic | I=2; P=2 LOW | Viable market opportunities for agrobiodiversity products have already been identified and there is strong potential to strengthen these and establish new markets linked to eco-tourism and through certification and branding schemes. The project will focus on developing these identified opportunities. Market risks will be further assessed as part of the participatory landscape assessments and supply/value chain analyses planned under Component 2. The project will also take a broad approach to the development of incentive mechanisms and incorporate non-market-based incentive mechanisms where there are no or limited markets or where market risks are assessed to be high. | Project Coordinator, NPD, LGU units, |
| 5. Regulatory approval flows do not match project implementation timeframe. | Political | I=3; P=1 LOW | Consultations with provincial and county government officials were carried out during the PPG phase, and policy and regulatory reform targets were established based upon governmental processes and achievable results over the course of the project. For instance, for the provincial level GRFA regulation, the end target is to garner approval by the Department of Agriculture and Rural Affairs (DARA) and to submit the regulation for approval to the Provincial Government. The National Project Director (NPD) and Project Director, supported by the Project Coordinator, will advocate for regulatory approval during the project implementation phase, and one of the roles of the GRFA Intersectoral Coordination Committee is to help facilitate regulatory reform through the lifespan of the project and after GEF funding ceases. | NPD, Project Director, Project Coordinator |
| 6. Inadequate coordination at the local level | Operational | I=3; P=1 LOW | Local government units (LGUs), including the county departments of agriculture and rural affairs and the township agricultural stations, have important roles in ensuring inclusive implementation of the project activities, particularly the community-level activities under Component 2. The National Project Director (NPD) will designate focal points within the LGUs for each of the three target counties, and these focal points will garner support within their organizations and other stakeholder groups. The LGU focal points will be members on the landscape partnership working groups, providing them with firsthand knowledge of progress and issues. And, the county level focal points will be represented on the project steering committee, enabling them to report and obtain guidance at the provincial level. | NPD, LGU focal points, Project Coordinator |
| 7. Cofinancing contributions are not realized as planned. | Financial | I=3; P=1 LOW | Cofinancing contributions are primarily represented by parallel, baseline funding for initiatives and investments that have been approved or are ongoing, by both governmental and enterprise sector partners. The project was designed to feed into these baseline activities, providing incremental benefits. There are three mechanism built into the design to facilitate synergies with cofinancing partners and activities: (1) the Project Steering Committee, (2) the GRFA Intersectoral Coordination Committee and (3) the three local Landscape partnership working groups. | NPD, Project Director, LGU focal points, Project Coordinator |
| 8. Project implementation could be challenged by natural disasters, resulting in damage to target agricultural landscapes, challenging project implementation timeframes and damaging crops. | Operational | I=2; P=2 LOW | Farmers, as well as agricultural associations and enterprises, are faced with natural disaster risks every year, and they have developed conventional and traditional ways to mitigate these risks. Through the landscape-based and participatory approach promoted in the project design, the landscape assessments will identify natural disaster risks across the landscapes and the GRFA conservation and sustainable use plans will integrate mitigation measures, which will further strengthen the resilience of the local communities. The project will align with relevant provincial strategies to support disaster risk assessment and mitigation. | Project Coordinator, LGU units, farmers |
| 9. Unfavorable fluctuations in USD:CNY exchange rates. | Financial | I=2; P=1 LOW | GEF financed projects have been implemented in China, including Hainan Province, over the past decade with limited impacts associated with currency fluctuation. Inflation rates in recent years been close to 2%. Disbursements will be made based on annual work plans, which will be adjusted to possible currency fluctuations. | Project Coordinator |
| Risks from Social and Environmental Screening Procedure (Annex D): |  |  |  |  |
| SESP Risk 1: Changes in farming approaches and practices, focused on improving in-situ conservation and sustainable use of GRFA varieties, have the potential to affect lands, cultural heritage and livelihoods (e.g., reduced access to resources) of ethnic minority populations within the project demonstration areas, including in Shang’an Township in Qiongzhong County and Da’an Township in Baisha County. Standard 6: Indigenous Peoples, 6.1, 6.8; Principle 1: Human Rights, Question 3; Standard 5: Displacement and Resettlement, 5.4; Standard 4: Cultural Heritage, 4.2. | Environmental and Social | I=2; P = 3 MODERATE | During the project preparation phase, consultations were made with local communities, local government officials, as well as provincial governmental agency officials. The indicative activities outlined in the project design will be elaborated in GRFA conservation and sustainable use plans, which will be developed for each of the demonstration landscapes. Local landscape coordination committees will guide these processes, ensuring equitable representation of farmers, agricultural associations, enterprises and local government officials. Moreover, culturally appropriate consultations will be carried out with the objective of achieving understanding and agreement on issues that may affect the rights and interests, lands, access to resources and traditional livelihoods of ethnic minority communities. Local youth will have an important role in the project, with a target of 20% youth involvement. As youth are the succeeding rights-holders, it is imperative that traditional knowledge is passed on to them and they have the skills to sustainable manage the natural resources in their communities. As elsewhere in China, ethnic minority youth tend to be fluent in Mandarin Chinese. The project will actively advocate for involvement of youth throughout the project, including representation on coordination committees and other community consultative processes. A stakeholder engagement plan (Annex E) was completed during the PPG phase and will guide proactive participation of ethnic minorities during implementation. Please see this plan for further details | NPD, Project Director, LGU focal points, Project Coordinator |
| SESP Risk 2: There are disparities between women and men in the rural areas where project demonstrations are planned that could potentially be reproduced by project activities, and women are under-represented among most provincial and county governmental agencies, limiting engagement and involvement of women in project implementation. Principle 2: Gender Equality and Women’s Empowerment, question 3 | Environmental and Social | I=2; P = 3 MODERATE | A gender analysis and action plan were completed during the PPG phase and will guide proactive women’s empowerment efforts during project implementation. Please see this plan (Annex G) for further details of specific project gender mainstreaming actions and targets. | Project Coordinator |
| SESP Risk 3: Communities in the project areas (including ethnic minorities) could face economic displacement and/or restricted access to resources because of changes in farming approaches and practices, focusing on improved in-situ conservation and sustainable use of GRFA varieties. These impacts could impact women differently than men. Principle 1: Human Rights, question 1.1; Principle 2 Gender Equality and Women’s Empowerment, 2.3; Standard 4: Cultural Heritage, 4.5; Standard 5: Displacement and Resettlement, 5.4. | Environmental and Social | I = 2; P = 2 LOW | Farming communities (including minority communities) are integral to project design and implementation. The project aims to ensure farming communities are central to business partnerships and value chains to ensure that they are able to reap benefits from development of traditional GRFA varieties. Project activities will provide training in market skills and development to farming communities so that they have the skills required to initiate and negotiate partnerships with enterprises for product development, and to form farmers cooperatives to take products to market. This will mitigate the risk of farming communities not benefitting from these market opportunities. There is the chance that market opportunities for traditional GRFA varieties might fail or take time to bring to fruition. To mitigate this risk, market assessments and supply/value chain analyses will be conducted and explored only where there are clearly identified opportunities. Incentive mechanisms will also include non-market-based opportunities for situations where there are no or weak market opportunities, and to avoid the risk of product development when there is not a clear demand. In each of the three demonstration landscapes, local coordination committees will be established, ensuring that farmers have equitable representation in decision making processes regarding market development, changes in farming approaches and dissemination of traditional knowledge. | Project Coordinator |
| SESP Risk 4: Potential increase in the use and market development of traditional GRFA varieties could have adverse impacts on biodiversity or land management. Standard 1: Biodiversity Conservation and Sustainable Natural Resource Management, 1.9. | Environmental and Social | I = 2; P = 1 LOW | The project will promote on-farm use of traditional GRFA varieties, shifting away from modern cultivars. Local varieties will be promoted along with traditional techniques to ensure that farming is well-suited to the local environmental conditions. For each of the three demonstration landscapes, participatory landscape assessments will be made, followed by development of GRFA conservation and sustainable use plans, which will be guided by local coordination committees having equitable representation of farmers, agricultural associations, enterprises and local government units. Management measures will be developed and implemented through these processes. There is, therefore, a low risk that the increased use of these varieties will have negative impacts on biodiversity or land condition – rather it will be likely to have positive impacts. Through market development and incentivizing engagement in farming GRFA, there could be a significant expansion in the production of traditional varieties, potentially resulting in increased pressures on natural environments. This risk is considered low as the market opportunities are unlikely to get to that scale and will be likely to be linked to farmland improvement initiatives such as eco-tourism and/or replacement of modern agricultural varieties. The project will target increased use of traditional varieties on existing farmland on which modern cultivars are currently used. The shift towards increased farming of GRFA varieties would have net benefits to natural resources, e.g., as traditional varieties tend to more resilient than modern cultivars, requiring few inputs such as pesticides and chemical fertilizers. | Project Coordinator |
| SESP Risk 5: Climate change has potential to negatively impact the diversity and viability of sustaining GRFA varieties in the project area. Standard 2: Climate Change Mitigation and Adaptation, 2.2. | Environmental and Social | I = 2; P = 2 LOW | Participatory landscape assessments planned for each of the three demonstration landscapes at project inception will include evaluation of potential climate change impacts. The GRFA conservation and sustainable use plans that will be developed based on the results of the participatory landscape assessments will include climate change adaptation management measures. | Project Coordinator |
| SESP Risk 6: Increased farming of GRFA varieties could entail an increase in the quantity of agrochemicals applied, potentially impacting the environment or human health. Standard 7: Pollution Prevention and Resource Efficiency, 7.4. | Environmental and Social | I = 2; P = 1 LOW | The project will be obliged to fulfill governmental regulations and UNDP standards regarding the use of agrochemicals. For instance, farmers participating in project activities will be required to handle, store, apply and dispose of agrochemicals in accordance with international good practice, such as the FAO International Code of Conduct on the Distribution and Use of Pesticides. Management measures will be integrated into project procurement processes and targeted training will be delivered to farmers, agricultural associations, enterprises and local government units. | Project Coordinator |

- The social and environmental screening procedure (SESP) (see Annex D) was finalized during project preparation phase, as required by UNDP’s Social and Environmental Standards (SES). The SESP identified six risks for this project that could have potential negative impacts in the absence of safeguards, four of these risks were rated as low and two as moderate. Therefore, the overall SESP risk categorization for the project is Moderate. The two moderate rated risks are on ethnic minorities and gender equality / women empowerment.

- The project will adhere to UNDP SES Guidance Note Standard 6 on Indigenous Peoples (ethnic minorities in China).  In accordance with guidance note, project activities that could adversely affect the existence, value, use or enjoyment of traditional lands, resources or territories shall not be conducted unless agreement has been achieved through the free, prior and informed consent (FPIC) process. Culturally appropriate consultation will be carried out with the objective of achieving agreement and FPIC will be ensured on any matters that may affect the rights and interests, lands, resources, territories (whether titled or untitled to the people in question) and traditional livelihoods of ethnic minorities. The Stakeholder Engagement Plan included as Annex E to the project document includes a separate section on ethnic minority engagement, describing the populations in the demonstration landscapes, the legal and institutional frameworks, an action plan for engagement with ethnic minority people, a description of how FPIC will be implemented in the communities within the demonstration landscapes and outlines the indicative activities on the project involving ethnic minorities.

- Separately, a Gender Analysis and Action Pan, included Annex G, were developed to provide project-specific safeguards for ensuring gender mainstreaming and presents targets for enabling monitoring and evaluation of project performance with respect to gender.

- Per the UNDP policy, a project-level Grievance Redress Mechanism (GRM) will be established during the first year of project implementation.

Stakeholder engagement plan:

- A stakeholder analysis was undertaken during project preparation to identify key stakeholders, consult with them regarding their interests in the project and define their roles and responsibilities during project implementation. Based upon this analysis, summarized below in Table 14, a stakeholder engagement plan has been developed to guide the implementation team (see Annex E).

Table 14: Stakeholder summary indicating mandates and roles in the project

| Stakeholders | Mandate / Interest | Role in Project |
| --- | --- | --- |
| Implementing Partner: |  |  |
| Hainan Provincial Department of Agriculture and Rural Affairs (DARA), including: - International Cooperation Division; - Animal Husbandry Division; - Science, Technology and Education Division; - Crop plantation Division - Horticulture Division - Station of Agricultural Ecology and Environmental Protection | The Hainan Provincial Department of Agriculture and Rural Affairs is mandated to implement State principles, policies, laws and rules concerning agricultural production, animal husbandry and conservation of agrobiodiversity in Hainan Province. The DARA drafts regulations and is responsible for enforcement, is responsible for issuing product certifications for agricultural products and is mandated to lead efforts to expand agro-tourism in the province. | The DARA is the implementing partner for the project and will designate a National Project Director (NPD), who will be responsible for overall implementation of the project. The DARA will also set up a Project Management Office (PMO) and recruit PMO staff. Chair of the Project Steering Committee. Chair of the GRFA Intersectoral Coordination Committee. Involved on all outputs. |
| GEF Agency: |  |  |
| United Nations Development Programme (UNDP) | The UNDP has had a resident office in China for many years, providing a broad spectrum of development assistance, including sustainable management of natural resources, governance, gender equality, and the rule of law. | The UNDP is the GEF Agency for the project and the C-SAP Program Coordination Agency. UNDP will be responsible to help steer and ensure quality control throughout implementation, to meet UNDP, Government of China and GEF standards and strategic objectives. UNDP will be the Senior Supplier on the Project Steering Committee. The UNDP Country Office will provide administrative and strategic guidance to the project, and support procurement processes, including for international sourced goods and services. The UNDP-GEF Regional Technical Advisor based at the Regional Hub for Asia and the Pacific will provide strategic technical assistance and project assurance. All outputs. |
| Key National Agencies and Central Governmental Stakeholders: |  |  |
| Ministry of Finance | The Ministry of Finance is responsible for allocating government funding and coordinating extra budgetary donor financing. The GEF Operational Focal Point is also based in the Ministry of Finance. | The Ministry of Finance will be a key member of the C-PAR Program Steering Committee and will be provide high-level guidance to the project implementation. Output 4.1. |
| Ministry of Agriculture and Rural Affairs (MARA) | The Ministry of Agricultural and Rural Affairs (MARA) is in charge of agriculture and rural economic development. MARA works out development strategies and long-term and medium-term development plans for agriculture and rural economy. The ministry directs research and formulates guidelines and policies regarding agricultural production, including control of invasive alien species. And, the ministry establishes and implements technical standards for certification of various agricultural products, protection of nationally important varieties, monitoring and quality control of agricultural inputs, and supervision of domestic animal and plant disease prevention. | MARA is the lead implementing partner for the C-SAP program and will chair the program steering committee. A program coordination team will be based at MARA in Beijing, providing guidance to all child projects, including coordinating monitoring & evaluation efforts, developing a program knowledge management strategy and facilitating cross-learning exchanges. All outputs |
| Key Provincial Agencies and Governmental Stakeholders: |  |  |
| Hainan Provincial Department of Finance | The Hainan Provincial Department of Finance is responsible for allocation and control of provincial finances for the province. | The Hainan Provincial Department of Finance is the main governmental cofinancing partner on the project and will provide an oversight function for financial management and control of GEF funds dispersed. The Department of Finance will also be involved in an advisory role in the project activities associated with incentive mechanisms and eco-compensation schemes. Member of the Project Steering Committee. Outputs 1.2, 1.3, 3.1, 4.1 |
| Hainan Department of Ecology and Environment | The Hainan Department of Ecology and Environment is responsible for legislating and enforcing environmental protection issues in the province and is the provincial focal point for biodiversity conservation. | The Department of Ecology and Environment is one the key provincial government stakeholders, providing advisory support to policy reform, synergizing the proposed agrobiodiversity strategy and action plan to the provincial biodiversity strategy and action plan, and delivering key inputs on a wide range of project activities, including monitoring of agroecological health, eco-compensation, database development, etc. Member of the Project Steering Committee. Member of the GRFA Intersectoral Coordination Committee. All outputs under Component 1, Output 3.2, Output 4.2. |
| Hainan Department of Natural Resources, including the Forestry Bureau and Land and Resources Bureau | The Department of Natural Resources is a newly formed department, as part of the ministry level restructuring that occurred in 2018, with the establishment of the Ministry of Natural Resources. At the provincial level, several sectors have been merged into the Department of Natural Resources, including the Forestry Bureau and the Land and Resources Bureau. | The Department of Natural Resources is one the key provincial government stakeholders, providing advisory support to policy reform, delivering key inputs on a wide range of project activities, eco-compensation, access to forest resources, database development, etc. Member of the Project Steering Committee. Member of the GRFA Intersectoral Coordination Committee. All outputs under Component 1, Output 3.2, Output 4.2. |
| Hainan Development and Reform Commission | Among its wide-ranging mandate, the Hainan Development and Reform Commission is in charge of the management of agricultural natural resources by law and provides guidance in the zoning of agricultural resources and development planning of the agricultural sector. | The Development and Reform Commission will be a member of the GRFA Intersectoral Coordination Committee, providing advisory support to the proposed policy reforms and development of GRFA work programs. All outputs under Component 1, Output 3.2, Output 4.2. |
| Hainan Office of Poverty Alleviation | The Office of Poverty Alleviation is responsible for implementing the provincial poverty alleviation strategy and provides cross-cutting support to provincial and local governmental agencies. | The Office of Poverty Alleviation will be a member of the GRFA Intersectoral Coordination Committee, providing advisory support to the proposed policy reforms, community level activities designed to deliver sustainable livelihood benefits, awareness raising and knowledge management. All outputs under Components 1 and 2, Output 3.2, Output 4.2. |
| Hainan Department of Education | The Department of Education is responsible for implementing national education polices across the province and setting provincial and local level policies and standards. | The Department of Education will be a member of the GRFA Intersectoral Coordination Committee, providing advisory support to capacity development, awareness raising and knowledge management activities. All outputs under Component 1, Output 2.4, Output 3.2, Output 4.2. |
| Hainan Department of Water Resources | The Department of Water Resources is responsible for management of water resources in the province, including agricultural water, and disaster prevention and mitigation, including flood control. | The Department of Water Resources will be a member of the GRFA Intersectoral Coordination Committee, providing advisory support to policy reforms, e.g., development of an agrobiodiversity strategy and action plan, to the development of local GRFA conservation and sustainable use plans, e.g., regarding agricultural water supply, and to awareness raising and knowledge management. All outputs under Component 1, Output 3.2, Output 4.2. |
| Local Governmental Stakeholders: |  |  |
| Prefecture and County Agriculture Bureaus; Township Service Centers for Agricultural Techniques Baisha Li Autonomous County, Da’an Township: Wuzhishan pig Qiongzhong Li and Miao Autonomous County, Shang’an Township: Shanlan rice landscape Qionghai County, Shibi Township: Jiaji duck | County agricultural bureaus issue local regulations and provide support to farmers and agricultural associations. Township agriculture stations provides local level support to farmers and deliver extension related services. | County and township local government units are key stakeholders on the project, providing direct support to the project activities through governmental cofinancing contributions. The three County Departments of Agriculture and Rural Affairs will be members of the Project Steering Committee and will each designate one official as the focal point for the project, facilitating inputs from both county and township units and reporting to the DARA. The three Township Agricultural Stations will also designate one official as project focal point, who will help coordinate and facilitate the community level activities. Representatives of the Township Agricultural Stations will be included in the planned Landscape partnership working groups in the three demonstration landscapes. All outputs. |
| Social organizations and non-governmental organizations (NGOs) |  |  |
| All-China Women’s Federation | The All-China Women’s Federation (ACWF) is a women’s rights organization, responsible for promoting government policies on women and protecting women’s rights within the government. The ACWF is run from the national level, with support delivered to local government units at the provincial, municipal, county, township and village levels. | Considering that gender mainstreaming is an integral part of the project design, the provincial office of the ACWF will be represented on the Project Steering Committee and also the GRFA Intersectoral Coordination Committee, providing advisory support on implementation, monitoring and evaluation of women empowerment targets. ACWF representatives at the county, township and/or village level will be members of the landscape demonstration committees, providing support to the gender mainstreaming activities at the community level. All outputs. |
| Communist Youth League of China | The Communist Youth League of China (CYLC) is run by the Communist Party of China and is tasked with mobilizing various youth organizations to participate in social activities and organizing training programs to enhance leadership, knowledge and skills of youth. The leading organization of the CYLC is the National Congress and the Central Committee, and General Affairs Committees oversee the affairs of the League and lead organizations in 31 provincial level administrative areas in the country. | The provincial organization of the CYLC will be represented on the GRFA Intersectoral Coordination Committee, providing advisory support on ensuring youth participation in project implementation. Output 1.3, all outputs under Component 2, Output 3.2, Output 4.2. |
| Hainan Provincial Commission for Ethnic and Religious Affairs, and county level commissions in the three demonstration counties | There are commissions for ethnic and religious affairs at both provincial and county levels to coordinate ethnic affairs, policy making, governing of public activities, education, official training, etc. | The commissions will be invited to participate in the community consultations with ethnic minorities in the demonstration landscapes. |
| Other social organizations | Based on stakeholder consultations made during the PPG phase, there is limited involvement of NGOs and other social organizations in agrobiodiversity management in the province. During project implementation phase, the project team will further advocate for involvement of social organizations. | Other social organizations will be invited to participate on the project, providing technical advisory support and advocacy on issues they are focusing on. Outputs1.1, Output 1.2, all outputs under Component 2, Output 3.3, Output 4.2 |
| Local communities where project interventions are planned: |  |  |
| Local communities, farmers | Local communities where project interventions are planned are among the key beneficiaries of the project. The farmer households engaged in GRFA varieties and the other residents of the villages where project demonstration activities are planned are counted as direct beneficiaries. | Local communities will be engaged on a number of project activities, including involvement in carrying out participatory landscape assessments, development of GRFA conservation and sustainable use plans, representation on the local Landscape partnership working groups, trainings, microgrant opportunities for implementing improved farming practices and developing market niches, participating in workshops and trade fairs, etc. All outputs under Component 2, Output 3.3, Output 4.2. |
| Agricultural Associations, including Cooperatives |  |  |
| Agricultural associations, including cooperatives, engaged in the GRFA varieties in the demonstration landscapes and in broader areas the province. | Many farmers in the demonstration landscape are members of agricultural associations, including cooperatives. These associations contribute towards strengthening social capital within local communities and provide farmers with broadened market access and improved access to credit and knowledge. | Agricultural associations, including cooperatives, will be involved on a number of project activities, and be represented on the local Landscape partnership working groups. The project will facilitate strengthening of agricultural associations, through increasing membership, training, development of markets, building partnerships with enterprises, etc. Outputs 1.2, all outputs under Component 2, Output 3.3, Output 4.2. |
| Enterprises |  |  |
| Enterprises engaged in the GRFA varieties in the demonstration landscapes and in broader markets in and beyond the province, including but not limited to: - Fomianshan Farmers Association of Cultivation and Animal Husbandry (Wuzhishan pig; cofinancing partner); - Hainan Tian Heng Agricultural Development Co. Ltd. (Shanlan rice; cofinancing partner); - Hainan Chuanwei Muscovy Duck Breeding Co. Ltd. (Jiaji duck; cofinancing partner). | The enterprise sector is an important stakeholder group, with capital investments in expanding GRFA production and offerings. Three enterprises have confirmed cofinancing at project entry and additional partners will be sought during project implementation. | The enterprise sector will be involved on most aspects of the project, including providing advisory inputs to proposed regulatory reforms and incentive mechanisms, having representation on the local Landscape partnership working groups, supporting development of the GRFA conservation and sustainable use plans, benefitting from market development activities and trainings, strengthening agro-ecotourism offerings, and participating in awareness raising and knowledge management. The project will also be facilitating increased partnerships between the enterprise sector and local farmers and agricultural associations, including cooperatives. Output 1.1, Output 1.3, all outputs under Component 2, Output 3.3, Output 4.2. |
| Agricultural Trade Associations, e.g., Hainan Provincial Association of Tropical Agricultural Product Marketing | Agricultural trade associations provide information and advocacy support to enterprises and agricultural associations. Every year the Association of Tropical Agricultural Product Marketing leads the Hainan International Winter Trade Fair for Tropical Agricultural Products in Haikou, which enjoys increasing popularity within China and beyond. | Trade associations will be invited to participate on the project, providing advisory support on activities involving strengthening marketing capacities, development of partnerships, organizing trade fairs, etc. Output 2.3, Output 2.4, Output 3.3, Output 4.2. |
| Academic and Research Institutions: |  |  |
| Chinese Academy of Agricultural Sciences | The Chinese Academy of Agricultural Sciences (CAAS) is a national, integrative agricultural scientific research organization with responsibility for carrying out both basic and applied research, as well as research into new technologies impacting agriculture. | CAAS will provide high-level technical support to the project, including dissemination of research advances in agrobiodiversity management and delivering capacity development services according to activities procured during the implementation phase. |
| Chinese Academy of Tropical Agricultural Sciences | The Chinese Academy of Tropical Agricultural Sciences (CATAS) is a national agricultural research institution engaged in researches on tropical agriculture, including rubber tree, tropical fruits, tropical bio-fuel crops, tropical vegetables, tropical forage, tropical textile fiber crops, tropical arboreal oil crops, tropical spice and beverage crops, tropical medicinal crops, working in the fields of agricultural machinery, environment and plant protection, biotechnology, genetic resource conservation and development for tropical agriculture, as well as agro-product quality and safety standards formulation and monitoring and test technology for tropical agriculture. | Academic and research institutions will be engaged on a number of project activities, including advisory support on regulatory reform, establishment of incentive mechanisms, technical guidance on in-situ conservation and sustainable use of GRFA varieties and development of knowledge management systems. These stakeholders will also have an important role with respect to capacity development, delivering trainings to both institutional and farmer beneficiaries. All outputs. |
| Hainan Provincial Academy of Agricultural Sciences | The Hainan Academy of Sciences (HAAS) centers on scientific innovation, commercialization of research findings, market extension and provision of technical services to farmers within Hainan Province. It also serves as think tank to Hainan provincial government regarding policies on agriculture and rural areas. |  |
| Hainan University | Hainan University is a comprehensive university in Hainan Province. In agriculture field. There is a large tropical agriculture research and education program, focusing on cultivation, breeding and biotechnology of tropical agriculture. |  |
| Hainan College of Vocation and Technics | Hainan College of Vocation and Technics focuses on vocational education including that of agricultural technics in Hainan university. |  |
| Bioversity International | Bioversity International is an international research organization specializing in agrobiodiversity, and through a cooperation arrangement with CAAS, they have been active in China for 30 years. | Bioversity International will be invited to participate on project activities, providing technical advisory support regarding international best practices in agrobiodiversity management. Output 1.1, Output 1.2, Output 2.4, Output 3.3, Output 4.2, Output 4.3. |
| Certification Organizations |  |  |
| China Organic Food Certification Center (COFCC) | COFCC is a special organization responsible for organic agriculture promotion and engaged in organic-food certification and management under MARA. | Certification organizations will support product certifications for select GRFA varieties, provide linkages with international certification bodies and supply chains, and provide training services to agricultural associations and enterprises. Output 1.1, Output 2.3, Output 2.4, Output 3.3, Output 4.2. |
| Agri-product Quality Safety Center | According to the Trademark Law of China, Geographical Indication (GI) is a sign that signifies the place of origin of the goods for which the specific quality, reputation or other features is decided by the natural or cultural factors of the regions. In December 2007, MARA began to carry out the certification of GIs. MARA issued "Administrative Measures of GIs of Agricultural Products" and is responsible for the registration of GIs of agricultural products. The Agri-product Quality Safety Center of MARA is responsible for the work of examination and review. |  |
| Organic Food Development and Certification Center of China (OFDC) | OFDC, a center under the Ministry of Ecology and Environment, is a specialized certification body that has been registered at the Chinese national authority (CNCA) and is both nationally (CNAS) and internationally (IFOAM) accredited. |  |
| Other certification organizations will be engaged according to the opportunities for the GRFA varieties in the demonstration landscapes. |  |  |

Gender equality and empowering women:

- Women in rural communities throughout China play an important role as custodians of genetic animal and plant resources, including in seed collection and storage, home gardens, gathering of ‘wild crops’ alongside a range of other aspects of agrobiodiversity conservation and sustainable use. In fact, women farmers outnumber male farmers in many communities as men have the tendency to migrate to urban areas for factory jobs. Even though women are de facto managing households and agricultural activities, men may retain decision-making power. It is, therefore, important to recognize gender considerations in agrobiodiversity management, considering women’s and men’s roles, responsibilities, interests and needs

- The gender mainstreaming strategy for the project recognizes the differences between labor, knowledge, needs, and priorities of men and women, and calls for:

- Consultation with women groups on needs and requirements associated with project interventions;

- Promotion of equitable representation of women and men in project activities and groups established and/or strengthened;

- Development of strategic and planning documents  in consultation with women;

- Targeted budgeting of activities promoting active involvement of women, and monitoring and evaluation of such activities;

- Participation, training and skills building of women identified and budgeted in relevant project outcomes;

- Encouragement of women participation in the recruitment of project implementation staff, including consultancies and other service providers; and

- When applicable, equal payment of women and men.

- More information on gender mainstreaming is included in Annex G (Gender Analysis and Action Plan) to the project document. Specific gender equality and mainstreaming targets have been set, including ensuring equitable representation of women in project decision-making bodies; ensuring equitable proportion of benefits realized from the project will be delivered to women; ensuring gender considerations are integrated into GRFA regulations, plans and sectoral work programs; promoting gender awareness throughout the project implementation phase, and promoting equal opportunity for employment for positions within the project management office, consultancies and other service providers. Moreover, resources have been allocated for gender specialist to be hired under short-term consultancy arrangement, to support implementation of the gender mainstreaming plan.

Youth Participation:

- Ensuring youth are engaged in the conservation and sustainable use of agrobiodiversity is an important aspect of an enduring strategy moving forward. Consistent with the Medium- and Long-term Youth Development Plan (2016-2025), issued by the Communist Party of China (CPC) and the State Council, that aims at improving education, employment and healthcare for the nation’s youth, the project has set a target for 20% of the direct beneficiaries to be youth.

- Youth involvement is planned across the four project components. The agrobiodiversity strategy and action plan developed under Component 1 will reflect the role of youth, for instance. Youth participation will also be promoted among the three demonstration landscapes in Component 2, with specific opportunities made available for interested young farmers and representatives of agricultural associations and enterprises. Institutional capacity development under Component 3 will be extended to staff members within the youth age bracket, and youth spokespersons will participate in the knowledge transfer exchanges to replication landscapes. The baseline KAP survey carried out in Component 4 will be include disaggregated feedback of youth respondents, and the project knowledge management action plan will include specific activities for raising awareness and increasing knowledge of youth.

South-South and Triangular Cooperation (SSTrC):

- Resources have been allocated under Component 3 for triangular cooperation, specifically through international knowledge transfer exchange visits to enable stakeholders from Hainan opportunities to learn firsthand of best practices in conservation and sustainable use of agrobiodiversity.

- There are also opportunities for South-South cooperation, building upon the 2010 agreement between UNDP China and the Chinese government on strengthening South-South and global cooperation, e.g., towards achieving Sustainable Development Goal 2 on ending hunger, supporting developing countries on agricultural issues.

Sustainability and Scaling Up:

- The sustainability of the project is ensured across several fronts. With respect to the financial dimension of sustainability, the project will help facilitate improved and broader uptake of incentive mechanisms, both market-based and non-market-based. Development of a guideline on appropriating eco-compensation funds for promoting conservation and sustainable use of agrobiodiversity and demonstrating allocation of such funds in the Central Highlands area will provide decision makers with a workable framework for upscaling in this region and in other parts of the province. Strengthening the capacities of local farmers, agricultural associations and enterprises will help build stronger markets for GRFA products and offerings and enable these stakeholders to expand their operations through implementing sound business and financial decisions.

- In terms of institutional frameworks and governance, the agrobiodiversity strategy and action plan will provide the Hainan DARA with strategic guidance on prioritizing resources for expanding conservation and sustainable use of agrobiodiversity in the province. The provincial and county level GRFA implementation frameworks will further help create an enabling environment that incentivizes participation in agrobiodiversity management. And integrating priority actions into the 14th 5-Year Plan of the Hainan Dara, conservation and sustainable use of GRFA varieties will continue as a routine part of provincial and county government planning processes. Inter-sectoral and cross-sectoral coordination will also be enhanced through the establishment and operationalization of provincial and county coordination committees.

- Strengthened capacities of local farmers, agricultural associations and enterprises, increased awareness of the nutritional and traditional values of GRFA varieties, and implementation of participatory GRFA conservation and sustainable use plans will contribute towards ensuring project results are sustained after GEF funding ceases. The increased social capital and sustainable livelihood benefits generated through the project activities will provide demonstrable socio-economic incentives for new entrants and existing stakeholders to engage in conservation and sustainable use of agrobiodiversity resources. Enabling facilities and activities, including a community seed bank for Shanlan rice and mainstreaming livestock competitions for Wuzhishan pig and Jiaji duck, also enhance the likelihood that project results will be sustained.

- With respect to environmental sustainability, promoting and demonstrating an integrated landscape approach towards agrobiodiversity conservation will facilitate more effective protection of biodiversity and ecosystem services, and increase the resiliency of local communities to the potential impacts of climate change.

- Scaling Up: The project design focuses on building an incentivized enabling environment for agrobiodiversity conservation, including development of an agrobiodiversity strategy and action plan, preparation GRFA implementation frameworks and eco-compensation guidelines, operationalization of inter-sectoral and cross-sectoral coordination mechanisms, and strengthened institutional and farmer’s capacities. Moreover, the largest proportion of the GEF funds are allocated under Component 2 for demonstrating effective implementation of non-market-based and market-based incentive mechanisms. Mainstreaming is a core outcome of Component 3 so that the approaches and tools developed at demonstration landscapes are institutionalized for wider application and incorporated into agency work plans. The best management approaches and lessons learned will be integrated into the replication strategy and upscaling plan. And, project resources are earmarked to support governmental and non-governmental stakeholders to initiate the implementation of the upscaling plan in at least two agricultural landscapes beyond the demonstration ones.

- The partnerships established between farmers, private sector enterprises, public sector and research institutions will build a secure base from which to expand incentive mechanisms across the province. Approaches, knowledge and results achieved will be shared with national partners under the C-SAP program to support exchange of knowledge and encourage scaling up of best practice initiatives beyond Hainan Province, including through possible South-South and Triangulation cooperation opportunities.

- The niche aspects implemented on the project, an integrated landscape approach towards agrobiodiversity conservation, participatory GRFA landscape assessments and conservation plans, appropriating eco-compensation funds for agrobiodiversity conservation, cofinancing partnerships with the enterprise sector, etc., also provide scale-able models for replication across the landscape and elsewhere in the province and in China. The project will also provide best practice guidance on social inclusion, including strengthened community engagement, broader participation by women, involvement of youth, and increasing awareness on the value of the agrobiodiversity.

# Project Management

Cost efficiency and effectiveness:

- The project strategy is predicated on strengthening an enabling environment that encourages conservation and sustainable use of agrobiodiversity through market-based and non-marked-based incentive mechanisms. Incentivizing increased participation by farmers, agricultural associations and enterprises into agrobiodiversity management is a cost-effective and sustainable approach that facilitates increased protection of GRFA varieties and delivers sustainable livelihood benefits to local communities.

- With respect to cost efficiency, GEF funds are allocated for capacity building activities aimed at strengthening capacities at the institutional level, delivering pragmatic knowledge to local famers, agricultural associations and enterprises and facilitating more participatory approaches towards agrobiodiversity management. This is considered a cost-efficient investment, by contributing to foundational capacities for sustainable protection of GRFA varieties. Efficiency gains are integrated into the project through collaborating with the other child projects on technical advisory, knowledge management, aggregated reporting, etc. Several cost-effective considerations are also incorporated into the design of the project activities. For instance, local service providers, including agricultural associations and cooperatives, research institutions and consultants, are envisaged to carry out many of the community level activities. Field interventions are designed as demonstrations that can be replicated and scaled up in the same target landscapes and in other areas in the province and China.

- The total GEF investment of USD 1,509,633 for this project will be complemented by a minimum of USD 10,160,000 in cofinancing from governmental and enterprise sector cofinancing partners, a highly cost-effective ratio of 6.7.  Finally, the receipt of GEF resources channeled through a UN agency often facilitates their ability to achieve the necessary political commitment to take difficult decisions on issues such as reforming outdated legislation, prioritizing conservation activities, strengthening intersectoral coordination, and adopting more environmentally friendly practices in related sectors. Overall this represents a very cost-effective investment of GEF funds.

Project management:

- The Project Management Office (PMO) will be based at the Hainan Department of Agriculture and Rural Affairs (DARA) in Haikou. Coordination with other C-SAP child projects will be led by the Project Coordinator in liaison with the C-SAP Programme Coordinator/M&E Officer working under the C-SAP2 National Invasive Alien Species (IAS) Project.  Coordination amongst provincial government agencies will be facilitated by the NPD, and the GRFA Intersectoral Coordination Committee will be established to provide a platform for coordination, information exchange and engagement with a wide range of provincial stakeholders, including NGOs and academic institutions.

- Local level project management support will be delivered by county and township agriculture sector offices where the three demonstration landscapes are located. County level GRFA coordination committees will be established at the three target counties to guide the project activities and to provide advisory support on regulatory reform and community interventions. Moreover, multi-stakeholder landscape partnership working groups will be assembled at the three demonstration landscapes, to ensure inclusive participation and representation of the interests of local farmers, agricultural associations and enterprises.

Agreement on intellectual property rights and use of logo on the project’s deliverables and disclosure of information:

- To accord proper acknowledgement to the GEF for providing grant funding, the GEF logo will appear together with the UNDP logo on all promotional materials, other written materials like publications developed by the project, and project hardware. Any citation on publications regarding projects funded by the GEF will also accord proper acknowledgement to the GEF. Information will be disclosed in accordance with relevant policies notably the UNDP Disclosure Policy and the GEF policy on public involvement.

# Project Results Framework

This project will contribute to the following Sustainable Development Goal (s): Goal 2: End Hunger, achieve food security and improved nutrition and promote sustainable agriculture. Indicator 2.5: By 2020, maintain the genetic diversity of seeds, cultivated plants and farmed and domesticated animals and their related wild species, including through soundly managed and diversified seed and plant banks at the national, regional and international levels, and promote access to and fair and equitable sharing of benefits arising from the utilization of genetic resources and associated traditional knowledge, as internationally agreed. Indicator 2.4: By 2030, ensure sustainable food production systems and implement resilient agricultural practice that increase productivity and production, that help maintain ecosystems, that strengthen capacity for adaptation to climate change, extreme weather, drought, flooding and other disasters and that progressively improve land and soil quality. Goal 15: Protect, restore and promote sustainable use of terrestrial ecosystems, sustainably manage forests, combat desertification, and halt and reverse land degradation and halt biodiversity loss. Secondary contributions towards SDG Goals 1 (end poverty), SDG 5 (gender equality), SDG 10 (reduce inequality), SDG 13 (climate change), and SDG 17 (global partnerships for sustainable development)

This project will contribute to the following country outcome included in the UNDAF/Country Program Document: UNDAF 2016-2020: Priority Area No. 2: Improved and Sustainable Environment; Outcome 2: More people enjoy a cleaner, healthier and safer environment as a result of improved environmental protection and sustainable green growth

This project will be linked to the following output of the UNDP Strategic Plan 2018-2021: 1.4.1. Solutions scaled up for sustainable management of natural resources, including sustainable commodities and green and inclusive value chains

|  | Outcome Indicators | Baseline | Mid-term Target | End of Program Target | Data Collection Methods and Risks/Assumptions |
| --- | --- | --- | --- | --- | --- |
| Project Objective: Strengthen the in-situ conservation and sustainable use of globally significant agrobiodiversity in Hainan through the development of incentive mechanisms for farmers to sustain populations of endemic crops and livestock, the establishment of a supportive enabling environment and strengthened institutional capacity | Indicator Obj-1: Area of landscapes under participatory conservation and sustainable use of agrobiodiversity (GEF Core Indicator 4.3: Area of landscapes under sustainable land management in production systems) (UNDP IRRF 1.4.1: Natural resources that are managed under a sustainable use, conservation, access and benefit-sharing regime: (g) other) | 0 ha | GRFA conservation and sustainable use plans for demonstration landscapes developed and implementation initiated. | 13,787 ha | Data Source & Measurement: Progress reports based on results of monitoring & evaluation of demonstration landscape activities. Approved demonstration landscape GRFA conservation and sustainable use plans. Product certification confirmation. Risks: Local farmers reluctant to proceed with recommended improvements to farming practices. Cofinancing support does not materialized as planned. Project implementation time is insufficient to achieve required changes in behavior and adjustments to enabling frameworks. Assumptions: Active participation by local farmers and other stakeholders. Cofinancing materializes as planned. Project implementation timeframe is sufficient achieve improved in-situ conservation and sustainable use of GRFA in the demonstration landscapes. |
|  | Indicator Obj-2: Number of direct project beneficiaries, measured based on: (a) Cumulative total of the following: (b) Number of people living in the communities within the demonstration landscapes (50% women) (c) Number of institutional staff members having strengthened capacities with regard to in-situ conservation and sustainable use of agrobiodiversity (30% women) (GEF Core Indicator 11: Number of direct beneficiaries disaggregated by gender as a co-benefit of GEF investment) | 0 | (a) 2,050 (1,015 women; 1,035 men) (b) 2,000 (1,000 women; 1,000 men) (c) 50 (15 women; 35 men) | (a) 5,522 (2,739 women; 2,783 men) (b) 5,412 (2,706 women; 2,706 men) (c) 110 (33 women; 77 women) | Data Source & Measurement: Socioeconomic surveys of demonstration landscapes based on a statistical representative sampling of households. Results of other project monitoring & evaluation efforts documented in progress reports. Risks: Uneven stakeholder involvement within the demonstration landscapes. Limited number of women among institutional beneficiaries. Assumptions: The best practices demonstrated through the project will provide benefits to all farmer households in the target landscapes. Assume 4 persons per household in target villages. Targeted trainings for women among institutional stakeholders. |
| Component 1: Strengthened provincial framework Outcome 1: Provincial policy, strategy and regulatory framework for in-situ conservation and sustainable use of agrobiodiversity enhanced | Output 1.1: Inter-sectoral and cross-sectoral coordination mechanisms are established and being used to facilitate the planning and implementation of approaches for the sustainable use and conservation of varieties Output 1.2: Policies, strategies and regulations related to in-situ conservation and sustainable use of agrobiodiversity are strengthened and developed Output 1.3: Eco-compensation appropriation policies are revised to support the in-situ conservation and sustainable use of agrobiodiversity and an eco-compensation plan is developed for protection of agricultural varieties in the Central Highlands area |  |  |  |  |
|  | Indicator 1.1: Strengthened policy, regulatory and strategic frameworks at provincial level support in-situ conservation and sustainable use of GRFA, as indicated by (a) a provincial Agrobiodiversity Strategy and Action Plan, a complement to the provincial Biodiversity Strategy and Action Plan; (b) provincial GRFA implementation framework; and (c) county GRFA implementation frameworks for Baisha County, Qiongzhong County and Qionghai City | Under-representation of GRFA conservation and sustainable use in the current policy and regulatory frameworks. | (a) Draft completed and under review (b) Draft completed and under review (c) Draft completed and under review | (a) Approved by DARA (b) Approved by DARA and submitted to the Provincial Government for approval (c) Approved by County Agriculture Bureaus | Data Source & Measurement: DARA decisions; County Agriculture Bureau decisions. Risks: Project implementation time is insufficient to achieve approval. Provincial and local governments are not committed to advance regulatory reforms. Assumptions: Through proactive advocacy and stakeholder engagement, there will be sufficient time and commitment to advance the regulatory reforms. |
|  | Indicator 1.2: Strengthened inter-sectoral and cross-sectoral cooperation leads to more effective approaches for the conservation and sustainable use of GRFA, including improved control and management of IAS threats, as indicated by number of coordination mechanisms at (a) provincial level and (b) county level. | No GRFA coordination mechanisms are in place. | (a) One provincial coordination committee established and providing advisory support to the project (b) Three county coordination committees established and providing advisory support to the project | (a) One provincial coordination committee, with charter approved by DARA (b) Three county coordination committees, with charters approved by county agriculture bureaus | Data Source & Measurement: Committee meeting minutes; DARA and county agriculture bureau decisions, documenting the approved charters for the GRFA coordination committees. Risks: Provincial and county stakeholders do not actively engage with the GRFA coordination committees. Assumptions: Agency leaders will promote active engagement with the coordination committees. |
|  | Indicator 1.3: Prioritized appropriation of government financing, as indicated by increased allocation of eco-compensation funds in the Central Highlands area for sustainable use and conservation of GRFA. | No eco-compensation funds appropriated to the Central Highlands area allocated for agrobiodiversity conservation. | Draft policy/approach on appropriating eco-compensation funds for agrobiodiversity, and demonstration plan under implementation in the Central Highlands area. | CNY 1 million of eco-compensation funds allocated for agrobiodiversity conservation in the final year of project implementation or earmarked for the year following project closure | Data Source & Measurement: Central, provincial and local government financial allocation records. Risks: Administrative constraints are prohibitively rigid, limiting the achievability of adjusting eco-compensation allocations. Assumptions: Central, provincial and local governments proactively facilitate adjustments to eco-compensation allocations. |
| Component 2: Demonstration of sustainable incentive mechanisms for in-situ conservation and use of agrobiodiversity Outcome 2: Market- and non-market-based incentive mechanisms established and demonstrated for in-situ conservation and sustainable use of agrobiodiversity, enabling long-term livelihood benefits for local farmers | Output 2.1: Participatory structures and planning and monitoring protocols put in place to improve conservation of traditional GRFA varieties in three demonstration landscapes Output 2.2: Market- and non-market-based incentive mechanisms are demonstrated three target agricultural landscapes, resulting in enhanced germplasm protection and securing sustained livelihood benefits for farmers and improved conservation of target varieties Output 2.3: Agrobiodiversity supply and value chains of the target GRFA varieties enhanced through strengthened marketing capacities and expanded application of marketing tools, including cultural value branding and product certification Output 2.4: Farmers, agriculture associations and enterprises capacitated and conservation and sustainable use of GRFA improved through partnership development and organizational strengthening, with a focus on increasing participation by women and youth |  |  |  |  |
|  | Indicator 2.1: Sustainable livelihood benefits to farmers generated through incentivized in-situ conservation and sustainable use of GRFA, as indicated by the number of farmer households engaged in GRFA varieties in the demonstration landscapes for (a) Wuzhishan pig, (b) Shanlan rice and (c) Jiaji duck. | (a) 36 (b) 5 (c) 5 | (a) 46 (b) 7 (c) 7 | (a) 56 (b) 10 (c) 10 | Data Source & Measurement: Socioeconomic surveys of demonstration landscapes based on a statistical representative sampling of households. Results of other project monitoring & evaluation efforts documented in progress reports. Risks: Local farmers are reluctant to implement recommended improvements to farming practices. Incentive mechanisms are not developed as planned. Market prices prohibit expansion of GRFA production. Women and/or youth participation falls short of targets. Assumptions: The best practices demonstrated through the project will provide benefits to all farmer households in the target landscapes. Incentive mechanisms are developed in time and available to farmers, farmer associations and enterprises. Market prices will support expansion of GRFA production. Proactive implementation of the gender-youth action plan will facilitate active participation. |
|  | Indicator 2.2: Expanded non-market incentives through improved access to genetic resources, as indicated by (a) number of community seed banks established for Shanlan rice; (b) number of annual livestock competitions for Wuzhishan pig mainstreamed into local extension offerings; (c) number of annual livestock competitions for Jiaji duck mainstreamed into local extension offerings. | (a) 0 (b) 0 (c) 0 | (a) Plan vetted and approved by demonstration landscape partnership working group; (b) At least one competition organized by the demonstration landscape partnership working group; (c) At least one competition organized by the demonstration landscape partnership working group. | (a) 1 (b) 1 (c) 1 | Data Source & Measurement: Commissioning records; M&E findings of usage and participation; approved plans. Risks: Financing is not secured to maintain the facilities and events. Assumptions: Provincial and local governments and other stakeholders ensure financial resources for maintaining the facilities and events established for enhancing access to improved genetic resources. |
|  | Indicator 2.3: Expanded GRFA market incentives and strengthened marketing capacities, as indicated by (a) number of new product certification marketing tools for the target GRFA varieties; and (b) number of new partnerships established | (a) 0 (b) 0 | (a) 1 (b) 1 | (a) 2 (b) 2 | Data Source & Measurement: Local government registers, documenting product certification marketing tools. Written partnership agreements between local farmers, farmer associations, business enterprises and governmental stakeholders. Risks: Local agro-tourism operators lack sufficient capacity to operate viable offerings. Opportunities for productive partnership arrangements do not materialize. Assumptions: Project support trainings, government programs and incentive mechanisms, and market conditions facilitate viable eco-tourism offerings and GRFA marketing partnerships. |
| Component 3: Mainstreaming and capacity strengthening Outcome 3: Demonstrated approaches mainstreamed and capacities strengthened to facilitate upscaling of incentivized conservation and sustainable use of GRFA | Output 3.1: Institutional capacities strengthened to facilitate and oversee incentive-based in-situ conservation and sustainable use of GRFA, through targeted trainings, learning by doing participation and knowledge transfer Output 3.2: Provincial and target county agricultural institutions have incorporated incentive mechanisms for in-situ agrobiodiversity conservation and sustainable use as part of agency workplans Output 3.3: Approaches developed under the project are extended to additional agricultural landscapes covering other varieties, generating expertise and support for scaling up across the province |  |  |  |  |
|  | Indicator 3.1: Strengthened institutional capacity of the provincial agricultural institutional sector for in the in-situ conservation and sustainable use of GRFA, as indicated by capacity development scorecard | 42% | 53% | 67% | Data Source & Measurement: Capacity development scorecard assessments at project entry, midterm and end of project. Risks: Limited stakeholder involvement, rendering minimal or no change in the capacity development scorecard results. Assessment of institutional capacities is inconsistent and not sufficiently participatory. Assumptions: Implementation of the project stakeholder engagement plan will facilitate active involvement by key institutional stakeholders. Capacity assessments are carried out consistently, with representative participation. |
|  | Indicator 3.2: Degree of upscaling of participatory approaches for the conservation and sustainable use of GRFA, as indicated by (a) number of participatory landscape assessments completed beyond the demonstration landscapes using the best practice guideline developed in Component 2; (b) hectares under in-situ conservation and sustainable use of GRFA replicated beyond the demonstration landscapes (excluding protected areas); (c) number of additional GRFA varieties having eco-certification in the province. | (a) 0 (b) 0 ha (c) 0 | (a) 1 (b) 0 ha (c) 1 | (a) 2 (b) 2,200 ha (c) 3 | Data Source & Measurement: Participatory landscape assessment reports. Local government records on GRFA cultivation and production. Eco-certification records. Risks: Incentive mechanisms are not realized or are insufficient to facilitate expansion of in-situ conservation and sustainable use of GRFA. Market conditions, including prices, are not conducive for expansion of GRFA expansion. Ineffective communication beyond the demonstration landscapes. Assumptions: Facilitated by the inter-sectoral GRFA coordination committee and effective implementation of the project communication and knowledge management plan, upscaling of demonstrated best practices is achieved beyond the target landscapes. Incentive mechanisms and market conditions are favorable for upscaling of in-situ conservation and sustainable use of GRFA. |
|  | Indicator 3.3: Level of mainstreaming incentive-based approaches of in-situ conservation and sustainable use of GRFA, as indicated having incentivized approaches for in-situ conservation and sustainable use of GRFA included in the work program for DARA | Incentivized approaches for in-situ conservation and sustainable use of GRFA not reflected in DARA work program | Draft work program under review | Approved work program included in the 14th 5-year plan for DARA | Data Source & Measurement: Provincial and local government registers, documenting approved agency work plans and budget allocations. Risks: DARA officials are reluctant to integrate in-situ conservation and sustainable use of GRFA into their work programs. Assumptions: Facilitated by the intersectoral GRFA coordination committees, the agencies will integrate in-situ conservation and sustainable use of GRFA into their work programs. |
| Component 4: Knowledge management and monitoring & evaluation Outcome 4: Knowledge, attitudes and practices, and knowledge management structures enhanced to broaden participation in the conservation and sustainable use of GRFA | Output 4.1: Effective monitoring & evaluation supported by a representative steering committee and through cross-collaboration on the C-SAP program. Output 4.2: Knowledge, attitudes and practices among farmers, governmental agencies, enterprises and the public improved through implementation of a targeted knowledge management strategy and action plan Output 4.3: A provincial agrobiodiversity database is strengthened to support ongoing monitoring of agroecosystems health and to collate information on varieties, coverage, farming practices and the impact of incentive mechanisms |  |  |  |  |
|  | Indicator 4.1: Improved understanding among key stakeholder groups of the value of GRFA and the importance of in-situ conservation, as indicated by results of knowledge, attitude and practices (KAP) surveys (disaggregated by women and youth), among the following stakeholder groups: (a) Provincial governmental stakeholders; (b) Local governmental stakeholders; (c) Farmers; (d) Agricultural associations and enterprises; | Baseline KAP surveys will be made during project inception phase. | No midterm targets, as measurable changes require time. | Provisional end targets: (a) Increase of at least 20% percentage points (b) Increase of at least 30% percentage points (c) Increase of at least 50% percentage points (d) Increase of at least 20% percentage points | Data Source & Measurement: KAP survey results (framework for KAP survey design is outlined in Annex N). Risks: The KAP surveys do not sufficiently capture the level of knowledge, attitudes and practices among project stakeholders. The baseline survey is not carried out in a timely manner. Assumptions: The design of the KAP survey will be participatory and lead to a genuine assessment of the level of knowledge, attitudes and practices among project stakeholders. Priority is given to completing the design and baseline KAP survey during project inception. |
|  | Indicator 4.2: Adoption of participatory knowledge management systems, as indicated by (a) the number of GRFA varieties described on the provincial agrobiodiversity database, and (b) number of lessons learned, case studies and other posts submitted on the C-SAP program knowledge and communication platform | (a) 0 (b) 0 | (a) 3 (b) 5 | (a) 6 (b) 20 | Data Source & Measurement: Reports generated by the GRFA database. Content and usage statistics of the knowledge and communication platform. Risks: The GRFA database is not used beyond the project. Use of the knowledge and communication platform is limited, due to shortcomings regarding user-friendliness, access and/or advocacy. Assumptions: The GRFA database and knowledge and communication platform will be designed through a participatory process; sufficient training will be provided to users; and proactive advocacy will facilitate broad usage among stakeholder groups. |

# Monitoring and Evaluation (M&E) Plan

- The project results as outlined in the project results framework will be monitored annually and evaluated periodically during project implementation to ensure the project effectively achieves these results. Supported by Component 4: Knowledge Management and Monitoring & Evaluation, the project monitoring and evaluation plan will also facilitate learning and ensure knowledge products are shared and widely disseminated to support the scaling up and replication of project results.

- Project-level monitoring and evaluation will be undertaken in compliance with UNDP requirements as outlined in the UNDP POPP and UNDP Evaluation Policy. The UNDP Country Office will work with the relevant project stakeholders to ensure UNDP M&E requirements are met in a timely fashion and to high quality standards. Additional mandatory GEF-specific M&E requirements (as outlined below) will be undertaken in accordance with the GEF M&E policy and other relevant GEF policies.

- In addition to these mandatory UNDP and GEF M&E requirements, other M&E activities deemed necessary to support project-level adaptive management will be agreed during the Project Inception Workshop and will be detailed in the Inception Report. This will include the exact role of project target groups and other stakeholders in project M&E activities including the GEF Operational Focal Point and national/regional institutes assigned to undertake project monitoring. The GEF Operational Focal Point will strive to ensure consistency in the approach taken to the GEF-specific M&E requirements (e.g., the GEF Tracking Tools) across all GEF-financed projects in the country.

M&E Oversight and monitoring responsibilities:

- Project Coordinator:  The Project Coordinator is responsible for day-to-day project management and regular monitoring of project results and risks, including social and environmental risks. The Project Coordinator will ensure that all project staff maintain a high level of transparency, responsibility and accountability in M&E and reporting of project results. The Project Coordinator will inform the Project Steering Committee, the UNDP Country Office and the UNDP-GEF RTA of any delays or difficulties as they arise during implementation so that appropriate support and corrective measures can be adopted.

- The Project Coordinator will develop annual work plans based on the multi-year work plan included in Annex A, including annual output targets to support the efficient implementation of the project. The Project Coordinator will ensure that the standard UNDP and GEF M&E requirements are fulfilled to the highest quality. This includes, but is not limited to, ensuring the results framework indicators are monitored annually in time for evidence-based reporting in the GEF PIR, and that the monitoring of risks and the various plans/strategies developed to support project implementation (e.g., gender action plan, stakeholder engagement plan etc.) occur on a regular basis.

- Project Steering Committee:  The Project Steering Committee (PSC) will take corrective action as needed to ensure the project achieves the desired results. The PSC will hold project reviews to assess the performance of the project and appraise the Annual Work Plan for the following year. In the project’s final year, the PSC will hold an end-of-project review to capture lessons learned and discuss opportunities for scaling up and to highlight project results and lessons learned with relevant audiences. This final review meeting will also discuss the findings outlined in the project terminal evaluation report and the management response.

- Project Implementing Partner:  The Implementing Partner is responsible for providing all required information and data necessary for timely, comprehensive and evidence-based project reporting, including results and financial data, as necessary. The Implementing Partner will strive to ensure project-level M&E is undertaken by national institutes, consultants or other service providers, and is aligned with national systems so that the data used and generated by the project support national systems.

- UNDP Country Office:  The UNDP Country Office will support the Project Coordinator as needed, including through annual supervision missions. The annual supervision missions will take place according to the schedule outlined in the annual work plan. Supervision mission reports will be circulated to the project team within one month of the mission. The UNDP Country Office will initiate and organize key GEF M&E activities including the annual GEF PIR, the independent mid-term review and the independent terminal evaluation. The UNDP Country Office will also ensure that the standard UNDP and GEF M&E requirements are fulfilled to the highest quality.

- The UNDP Country Office is responsible for complying with all UNDP project-level M&E requirements as outlined in the UNDP POPP. This includes ensuring the UNDP Quality Assurance Assessment during implementation is undertaken annually; that annual targets at the output level are developed and monitored and reported using UNDP corporate systems; the regular updating of the ATLAS risk log; and, the updating of the UNDP gender marker on an annual basis based on gender mainstreaming progress reported in the GEF PIR and the UNDP ROAR. Any quality concerns flagged during these M&E activities (e.g. annual GEF PIR quality assessment ratings) must be addressed by the UNDP Country Office and the Project Coordinator.

- The UNDP Country Office will retain all M&E records for this project for up to seven years after project financial closure to support ex-post evaluations undertaken by the UNDP Independent Evaluation Office (IEO) and/or the GEF Independent Evaluation Office (IEO).

- UNDP-GEF Unit:  Additional M&E and implementation quality assurance and troubleshooting support will be provided by the UNDP-GEF Regional Technical Advisor and the UNDP-GEF Directorate as needed.

- Audit: The project will be audited as per UNDP Financial Regulations and Rules and applicable audit policies on NIM implemented projects.

Additional GEF monitoring and reporting requirements:

- Inception Workshop and Report:  A project inception workshop will be held within three months after the project document has been signed by all relevant parties to, amongst others:

    - Re-orient project stakeholders to the project strategy and discuss any changes in the overall context that influence project strategy and implementation;

    - Discuss the roles and responsibilities of the project team, including reporting and communication lines and conflict resolution mechanisms;

    - Review the results framework and finalize the indicators, means of verification and monitoring plan;

    - Discuss reporting, monitoring and evaluation roles and responsibilities and finalize the M&E budget; identify national/regional institutes to be involved in project-level M&E; discuss the role of the GEF OFP in M&E;

    - Update and review responsibilities for monitoring the various project plans and strategies, including the risk log; SESP and other safeguard requirements; project grievance mechanisms; the gender strategy; the knowledge management strategy, and other relevant strategies;

    - Review financial reporting procedures and mandatory requirements, and agree on the arrangements for the annual audit; and

    - Plan and schedule PSC meetings and finalize the first-year annual work plan.

- The Project Coordinator will prepare the inception report no later than one month after the inception workshop. The inception report will be cleared by the UNDP Country Office and the UNDP-GEF Regional Technical Advisor and will be approved by the PSC.

- GEF Project Implementation Report (PIR):  The Project Coordinator, the UNDP Country Office, and the UNDP-GEF Regional Technical Advisor will provide objective input to the annual GEF PIR covering the reporting period July (previous year) to June (current year) for each year of project implementation. The Project Coordinator will ensure that the indicators included in the project results framework are monitored annually in advance of the PIR submission deadline so that progress can be reported in the PIR. Any environmental and social risks and related management plans will be monitored regularly, and progress will be reported in the PIR.

- The PIR submitted to the GEF will be shared with the PSC. The UNDP Country Office will coordinate the input of the GEF Operational Focal Point and other stakeholders to the PIR as appropriate. The quality rating of the previous year’s PIR will be used to inform the preparation of the subsequent PIR.

- Lessons learned and knowledge generation:  Results from the project will be disseminated within and beyond the project intervention area through existing information sharing networks and forums. The project will identify and participate, as relevant and appropriate, in scientific, policy-based and/or any other networks, which may be of benefit to the project. The project will identify, analyze and share lessons learned that might be beneficial to the design and implementation of similar projects and disseminate these lessons widely. There will be continuous information exchange between this project and other projects of similar focus in the same country, region and globally.

- GEF Focal Area Tracking Tools: GEF Tracking Tools will not be used on the project, according to the new Core Indicator policy. The UNDP Capacity Development Scorecard adapted for the project is being used as a M&E tool to assess institutional capacity. The baseline/CEO Endorsement assessment – included in Annex M to this project document – will be updated by the Project Coordinator/Team (not the evaluation consultants hired to undertake the MTR or the TE) through a focus group arrangement with the institutional partners and shared with the mid-term review consultants and terminal evaluation consultants before the required review/evaluation missions take place. The updated Capacity Development Scorecard will be submitted to the GEF along with the completed mid-term review report and terminal evaluation report.

- Independent Mid-term Review (MTR):  An independent mid-term review (MTR) process will begin after the second PIR has been submitted to the GEF, and the MTR report will be submitted to the GEF in the same year as the 3rd PIR. The MTR findings and responses outlined in the management response will be incorporated as recommendations for enhanced implementation during the final half of the project’s duration. The terms of reference, the review process and the MTR report will follow the standard templates and guidance prepared by the UNDP IEO for GEF-financed projects available on the UNDP Evaluation Resource Center (ERC). As noted in this guidance, the evaluation will be ‘independent, impartial and rigorous’. The consultants that will be hired to undertake the assignment will be independent from organizations that were involved in designing, executing or advising on the project to be evaluated. The GEF Operational Focal Point and other stakeholders will be involved and consulted during the terminal evaluation process. Additional quality assurance support is available from the UNDP-GEF Directorate. The final MTR report will be available in English and will be cleared by the UNDP Country Office and the UNDP-GEF Regional Technical Advisor and approved by the PSC.   Resources have been allocated for translation of key sections of the MTR report to Chinese, to ensure the findings and recommendations are effectively shared with the Implementing Partner, and other project stakeholders and beneficiaries.

- Terminal Evaluation (TE):  An independent terminal evaluation (TE) will take place upon completion of all major project outputs and activities. The terminal evaluation process will begin three months before operational closure of the project allowing the evaluation mission to proceed while the project team is still in place, yet ensuring the project is close enough to completion for the evaluation team to reach conclusions on key aspects such as project sustainability. The Project Coordinator will remain on contract until the TE report and management response have been finalized. The terms of reference, the evaluation process and the final TE report will follow the standard templates and guidance prepared by the UNDP IEO for GEF-financed projects available on the UNDP Evaluation Resource Center. As noted in this guidance, the evaluation will be ‘independent, impartial and rigorous’. The consultants that will be hired to undertake the assignment will be independent from organizations that were involved in designing, executing or advising on the project to be evaluated. The GEF Operational Focal Point and other stakeholders will be involved and consulted during the terminal evaluation process. Additional quality assurance support is available from the UNDP-GEF Directorate. The final TE report will be cleared by the UNDP Country Office and the UNDP-GEF Regional Technical Advisor and will be approved by the PSC.  The TE report will be publicly available in English on the UNDP ERC.  Resources have been allocated for translation of key sections of the MTR report to Chinese, to ensure the findings and recommendations are effectively shared with the Implementing Partner, and other project stakeholders and beneficiaries.

- The UNDP Country Office will include the planned project terminal evaluation in the UNDP Country Office evaluation plan and will upload the final terminal evaluation report in English and the corresponding management response to the UNDP Evaluation Resource Centre (ERC). Once uploaded to the ERC, the UNDP IEO will undertake a quality assessment and validate the findings and ratings in the TE report and rate the quality of the TE report.  The UNDP IEO assessment report will be sent to the GEF IEO along with the project terminal evaluation report.

- Final Report: The project’s terminal PIR along with the terminal evaluation (TE) report and corresponding management response will serve as the final project report package. The final project report package shall be discussed with the PSC during an end-of-project review meeting to discuss lesson learned and opportunities for scaling up.

Mandatory GEF M&E Requirements and M&E Budget:

- Project level M&E activities, responsibilities, indicative budget, cofinancing and timeframes are summarized in Table 15 below. The budget will be covered under Component 4 of the project.

Table 15: Project M&E Requirements and Budget

| GEF M&E requirements | Primary responsibility | Indicative costs to be charged to the Project Budget [1] (USD) |  | Time frame |
| --- | --- | --- | --- | --- |
|  |  | GEF | Co-financing |  |
| Inception Workshop | Project Coordinator, DARA | USD 11,000 | USD 15,000 | Within three months of project document signature |
| Inception Workshop Report | Project Coordinator | None | None | Within one month after inception workshop |
| Standard UNDP monitoring and reporting requirements as outlined in the UNDP POPP | UNDP CO | None | None | Quarterly, annually |
| Risk management | Project Coordinator, UNDP CO | None | USD 30,000 | Quarterly, annually |
| Monitoring of indicators in project results framework (tendered to local institute, local consultant or service provider) | Project Coordinator | Per year: USD 1,000 (Total: USD 5,000) | USD 25,000 | Annually before PIR |
| GEF Project Implementation Review (PIR) | Project Coordinator, UNDP CO and UNDP-GEF team | None | USD 10,000 | Annually |
| Lessons learned and knowledge generation (distillation of knowledge products tendered to local consultant, institute or service provider) | Project Coordinator | None | USD 10,000 | Annually |
| Monitoring of environmental and social risks, and corresponding management plans as relevant (tendered to national institute, local consultant, institute or service provider) | Project Coordinator, UNDP CO, County and Township Focal Points | Per year: USD 2,000 (Total: USD 10,000) | USD 20,000 | On-going |
| Stakeholder Engagement Plan | Project Coordinator, UNDP CO, DARA | None | USD 35,000 | On-going |
| Monitoring/M&E aspects of Gender Action Plan (tendered to local consultant or service provider) | Project Coordinator, UNDP CO, County and Township Focal Points | Per year: USD 1,000 (Total: USD 5,000) [3] | USD 10,000 | On-going |
| Addressing environmental and social grievances | Project Coordinator, UNDP CO | None | USD 2,000 | On-going |
| Project Steering Committee (PSC) meetings (annual) | Project Coordinator, PSC, UNDP CO | Per year: 2,000 (Total: USD 10,000) | USD 15,000 | Annually |
| Supervision missions | UNDP CO, | None | None | Annually |
| Oversight missions | UNDP-GEF team | None [2] | None | Troubleshooting as needed |
| GEF Secretariat learning missions/site visits | UNDP CO, Project Coordinator and UNDP-GEF team | None [2] | None | To be determined. |
| Mid-term assessment of Capacity Development Scorecard (tendered to local institute, local consultant or service provider) | Project Coordinator | USD 2,000 | 3,000 | Before mid-term review mission takes place. |
| Independent Mid-term Review (MTR) and management response | UNDP CO, PMO and UNDP-GEF team | USD 20,000 | USD 10,000 | Between 2nd and 3rd PIR. |
| Terminal assessment of Capacity Development Scorecard (tendered to local institute, local consultant or service provider) | Project Coordinator | USD 2,000 | 3,000 | Before terminal evaluation mission takes place |
| Independent Terminal Evaluation (TE) included in UNDP evaluation plan, and management response | UNDP CO, PMO and UNDP-GEF team | USD 30,000 | USD 10,000 | At least three months before operational closure |
| Translation of key sections of MTR and TE reports into Chinese (for benefit of Implementing Partner) | PMO | None | USD 2,000 | As required. GEF will only accept reports in English. |
| Final Report (includes final PIR, TE report and TE management response) | Project Coordinator, UNDP CO | None | None | At least one month prior to final PSC meeting |
| TOTAL indicative COST Excluding project team staff time, and UNDP staff and travel expenses |  | USD 95,000 | USD 200,000 |  |
| [1] Excluding project team staff time and UNDP staff time and travel expenses |  |  |  |  |
| [2] The costs of UNDP Country Office and UNDP-GEF Unit’s participation and time are charged to the GEF Agency Fee [3] Only the monitoring and M&E-related aspects of plans are included in this table, not the full costs of implementing these plans. Refer to Annex G for broader information on the Gender Analysis and Action Plan. |  |  |  |  |

# Governance and Management Arrangements

- Roles and responsibilities of the project’s governance mechanism: The project will be implemented following UNDP’s national implementation modality, according to the Standard Basic Assistance Agreement between UNDP and the Government of the People’s Republic of China, and the United Nations Development Assistance Framework for the People’s Republic of China (UNDAF 2016-2020).

The Implementing Partner for this project is the Hainan Provincial Department of Agriculture and Rural Affairs. The Implementing Partner is the entity to which the UNDP Administrator has entrusted the implementation of UNDP assistance specified in this signed project document along with the assumption of full responsibility and accountability for the effective use of UNDP resources and the delivery of outputs, as set forth in this document. The Implementing Partner is responsible for executing this project. Specific tasks include:

- Project planning, coordination, management, monitoring, evaluation and reporting.  This includes providing all required information and data necessary for timely, comprehensive and evidence-based project reporting, including results and financial data, as necessary. The Implementing Partner will strive to ensure project-level M&E is undertaken by national institutes and is aligned with national systems so that the data used and generated by the project supports national systems.

- Risk management as outlined in this Project Document;

- Procurement of goods and services, including human resources;

- Financial management, including overseeing financial expenditures against project budgets;

- Approving and signing the multiyear workplan;

- Approving and signing the combined delivery report at the end of the year; and,

- Signing the financial report or the funding authorization and certificate of expenditures.

- UNDP: UNDP is accountable to the GEF for the implementation of this project. This includes oversight of project execution to ensure that the project is being carried out in accordance with agreed standards and provisions. UNDP is responsible for delivering GEF project cycle management services comprising project approval and start-up, project supervision and oversight, and project completion and evaluation. UNDP is responsible for the Project Assurance role of the Project Steering Committee.

- The project organization structure is illustrated below in Figure 7.

Figure 7: Project Organization Structure

- Project Steering Committee: The Project Project Steering Committee is responsible for taking corrective action as needed to ensure the project achieves the desired results. In order to ensure UNDP’s ultimate accountability, PSC decisions should be made in accordance with standards that shall ensure management for development results, best value money, fairness, integrity, transparency and effective international competition.

- In case consensus cannot be reached within the PSC, the UNDP Resident Representative (or their designate) will mediate to find consensus and, if this cannot be found, will take the final decision to ensure project implementation is not unduly delayed.

- Specific responsibilities of the PSC include:

- Provide overall guidance and direction to the project, ensuring it remains within any specified constraints;

- Address project issues as raised by the Project Coordinator;

- Provide guidance on new project risks, and agree on possible mitigation and management actions to address specific risks;

- Agree on Project Coordinator’s tolerances as required, within the parameters set by UNDP-GEF, and provide direction and advice for exceptional situations when the Project Coordinator’s tolerances are exceeded;

- Advise on major and minor amendments to the project within the parameters set by UNDP-GEF;

- Ensure coordination between various donor and government-funded projects and programmes;

- Ensure coordination with various government agencies and their participation in project activities;

- Track and monitor co-financing for this project;

- Review the project progress, assess performance, and appraise the Annual Work Plan for the following year;

- Appraise the annual project implementation report, including the quality assessment rating report;

- Ensure commitment of human resources to support project implementation, arbitrating any issues within the project;

- Review combined delivery reports prior to certification by the implementing partner;

- Provide direction and recommendations to ensure that the agreed deliverables are produced satisfactorily according to plans;

- Address project-level grievances;

- Approve the project Inception Report, Mid-term Review and Terminal Evaluation reports and corresponding management responses;

- Review the final project report package during an end-of-project review meeting to discuss lesson learned and opportunities for scaling up.

- Ensure that UNDP Social and Environmental Safeguards Policy is applied throughout project implementation; and, address related grievances as necessary.

- PSC meetings will be convened annually at a minimum, and the composition of the PSC includes the following roles.

- Project Executive: Is an individual who represents ownership of the project and chairs the PSC. The Executive is normally the national counterpart for nationally implemented projects. The Project Executive (the National Project Director - NPD) is: Deputy Director General, Hainan Department of Agricultural and Rural Affairs (DARA). The NPD will assign three other co-financed, seconded positions within DARA, a Project Director, Deputy Project Director and Provincial Coordinator. These positions will provide day-to-day support to the Project Management Office, help facilitate the engagement of provincial agencies and other stakeholders in the GRFA Coordination Committee and coordinate the local government units where the demonstration activities will be implemented. The NPD will also designate focal points within the local government units for each of the three target counties, to represent the project, advocate for the policy and regulatory reforms and coordinating administrative and technical assistance in the implementation of project activities.

- Beneficiary Representative: Individuals or groups representing the interests of those who will ultimately benefit from the project. Their primary function within the PSC is to ensure the realization of project results from the perspective of project beneficiaries. Often civil society representative(s) can fulfil this role. The Beneficiary representative is: China All Women’s Federation.

- Development Partner(s): Senior Supplier: Individuals or groups representing the interests of the parties concerned that provide funding and/or technical expertise to the project. The Development Partners include the following: Hainan DARA, Hainan Provincial Department of Finance, Hainan Provincial Department of Ecology and Environment, Hainan Department of Natural Resources, Qiongzhong County, Baisha County and Qionghai City.

- Project Assurance: UNDP performs the quality assurance role and supports the PSC and Project Management Unit by carrying out objective and independent project oversight and monitoring functions. This role ensures appropriate project management milestones are managed and completed. The PSC cannot delegate any of its quality assurance responsibilities to the Project Coordinator. UNDP provides a three – tier oversight services involving the UNDP Country Offices and UNDP at regional and headquarters levels. Project assurance is totally independent of the Project Management function.

- Project Management Office: Project management services will be delivered by the Project Management Office, staffed as follows:

- Project Coordinator

- Project Coordinator: The Project Coordinator has the authority to run the project on a day-to-day basis on behalf of the Implementing Partner within the constraints laid down by the PSC. The Implementing Partner appoints the Project Coordinator, who must be different from the Implementing Partner’s representative in the PSC.

- The Project Coordinator’s primary responsibility is to ensure that the project produces the results specified in the project document, to the required standard of quality and within the specified constraints of time and cost. The Project Coordinator will inform the PSC and the Project Assurance roles of any delays or difficulties as they arise during implementation so that appropriate support and corrective measures can be adopted. The Project Coordinator will remain on contract until the Terminal Evaluation report and the corresponding management response have been finalized and the required tasks for operational closure and transfer of assets are fully completed. Specific responsibilities include the following (full terms of reference is included in Annex C):

- Coordinate the overall conduct of the project;

- Provide Secretariat duties for the PSC;

- Lead preparation of Inception Report, Annual Work Plans, Quarterly Work Plans, project change request and all other relevant technical documents.

- Perform regular progress reporting to the PSC as agreed with the committee, including measures to address challenges and opportunities.

- Prepare the GEF PIR, as well as quarterly and annual progress reports.

- Develop terms of reference for the recruitment of staff, technical contractors and consultants. Manage recruitment process in consultation with DARA and the UNDP Country Office.

- Liaise with UNDP Country Office for assuring timely project technical delivery and the operational compliance with the UNDP rules and regulations.

- Prepare the Result-Based Management reporting documents for timely submission and oversee the Mid-Term Evaluation Report and Terminal Evaluation Report preparation, and support and facilitate scheduled and unscheduled project areas inspections.

- Manage and monitor the project risks – including social and environmental risks - initially identified and submit new risks to the PSC for consideration and decision on possible actions if required; update the status of these risks by maintaining the project risks log.

- Assists and advises the local government focal points and service providers responsible for activity implementation at the three demonstration landscapes.

- Manage requests for the provision of UNDP financial resources through funding advances, direct payments or reimbursement using the FACE form.

- Responsible for financial accounting and reporting, and procurement of goods and services for the implementation of the project.

- Monitor financial resources and accounting to ensure the accuracy and reliability of financial reports and ensure timely and quality submission of financial reports to UNDP on a quarterly basis.

- Create project impact communication platform (e.g. WeChat), prepare and coordinate dissemination project communication materials and curate project success stories from the stakeholders and beneficiaries.

- The position of Project Coordinator will be jointly recruited by the DARA and UNDP nationally, and the desired candidate would be someone with relevant experience. The Project Coordinator should be delegated with sufficient decision-making authority to allow effective project management.

- Technical support will be procured as needed among qualified national and local consultants, institutes, and civil society organizations through competitive bidding processes. A full-time National Technical Advisor will provide technical guidance for the implementation of project activities, ensuring indicators in the project results framework are regularly monitored, maintaining the GRFA Coordination Committee, overseeing exchange and sharing of experiences and lessons with other child projects in the C-SAP program and other complementary initiatives, and assisting local government units in developing essential skills through training workshops and on-the-job training.  A part-time Chief Technical Advisor will provide high-level advisory support. The Chief Technical Advisor position will be contracted through a long-term consultancy arrangement; the position is budgeted for a total of 30 workdays over the 5 years of implementation. The Chief Technical Advisor will advise on project level outcomes and impacts towards agrobiodiversity reform in Hainan Province, provide strategic input into project implementation, assist in developing clear messaging for the project and liaising with senior provincial and national level stakeholders. The terms of reference for the National Technical Advisor and Chief Technical Advisor are included in Annex C.

- The types of other expertise envisaged on short-term assignments include but are not limited to the following:

- Policy reform;

- Eco-compensation;

- GRFA conservation and sustainable use;

- Business development and organizational strengthening;

- Marketing and branding

- Capacity development;

- Community development;

- Monitoring and evaluation;

- Gender mainstreaming;

- Knowledge management and communication, including KAP survey;

- Database development.

- The local government units having jurisdiction over the demonstration landscapes will each designate a county and township level focal point. The focal points will be staff members of the county and township agricultural sector, seconded in part-time arrangements and funded through local government cofinancing contributions, providing support for project activities at the local level.

- For certain specialized services, including leading the two independent evaluations, recruitment will be made internationally, using the UNDP procurement system.

- Project Advisory: The provincial and county level GRFA intersectoral coordination committees established under Output 1.3 of the project will provide technical and strategic guidance to the PMO and to the PSC through regular thematic meetings during implementation and on an as-needed basis, e.g., reviewing specific deliverables, terms of reference, etc. The provincial GRFA Coordination Committee will be chaired by the NPD and facilitated by the National Technical Advisor, with support from the Project Coordinator and Chief Technical Advisor, and have with representation by provincial departments, local government units, academic/research institutions, agricultural associations, enterprise sector and NGOs.

- Governance role for project target groups:  The project will work with existing multi-stakeholder partnership mechanisms and establish new partnerships where necessary to ensure project target groups are involved in the design, implementation, and monitoring & evaluation of the activities in their communities. Multi-stakeholder landscape partnership working groups will be established at each of the three demonstration landscapes, providing guidance and ensure inclusive participation of project activities.

# Financial Planning and Management

- The total cost of the project is USD 11,669,633.  This is financed through a GEF grant of USD 1,509,633, and USD 10,160,000 in parallel co-financing.  UNDP, as the GEF Implementing Agency, is responsible for the execution of the GEF resources and the cash co-financing transferred to UNDP bank account only.

- Parallel co-financing:  The actual realization of project co-financing will be monitored during the mid-term review and terminal evaluation process and will be reported to the GEF. The planned parallel co-financing will be used as follows:

| Cofinancing source | Cofinancing type | Cofinancing amount | Planned Activities/Outputs | Risks | Risk Mitigation Measures |
| --- | --- | --- | --- | --- | --- |
| Recipient government: Hainan Department of Agriculture and Rural Affairs | Grant | USD 9.92 million | All outputs | Insufficient cross-sectoral involvement. Regulatory approval flows do not match project implementation timeframe. Cofinancing contributions are not realized. Inefficient project management. Difficulties in recruiting qualified PMO staff. | Assign senior official to NPD position. Proactively promote the project among the key provincial and local government agencies. Facilitate regular meetings of the GRFA coordination committee. Participate in project sponsored trainings. Recruit qualified project staff and involve UNDP in recruitment. |
| Private sector: Hainan Tian Heng Agricultural Development Co. Ltd. | Grant | USD 0.06 million | Output 1.1: cross-sectoral coordination; Output 1.2: provincial and county level GRFA implementation frameworks; Output 2.1: participatory landscape assessment and GRFA conservation and sustainable use plan; Output 2.2: adding value on farm, establishing community seed bank for Shanlan rice, livestock competitions for Wuzhishan pig and Jiaji duck; Output 2.3: supply/value chain analyses, strengthening marketing capacities, partnership development; Output 2.4: capacity building, knowledge transfer exchanges, provincial and county level trade fairs; Output 3.3: knowledge transfer exchanges to replication landscapes; Output 4.2: KAP survey, awareness raising; Output 4.3: GRFA database. | Available incentives are insufficient to encourage investment in expansion of GRFA activities. Market prices decrease, rendering GRFA operation unprofitable. Weather hazards, pests, IAS, etc. disrupt production. Cofinancing contributions are not realized. | Participation by representatives from the enterprise sector in most aspects of the project. Provide targeted capacity development support based on direct feedback. Strengthened capacities and better-informed farmers will result in more resilient operations. |
| Private sector: Fomianshan Farmers Association of Cultivation and Animal Husbandry in Baisha | Grant | USD 0.15 million |  |  |  |
| Private sector: Hainan Chuanwei Muscovy Duck Breeding Co. Ltd. | Grant | USD 0.03 million |  |  |  |

- UNDP Direct Project Services (DPS) as requested by Government (if any): The UNDP, as GEF Agency for this project, will provide project management cycle services for the project as defined by the GEF Council. In addition, the Government of China may request UNDP direct services for specific projects, according to its policies and convenience.  The UNDP and Government of China acknowledge and agree that those services are not mandatory and will be provided only upon Government request. If requested, the services would follow the UNDP policies on the recovery of direct costs. These services (and their costs) are specified in the Letter of Agreement (Annex O). As is determined by the GEF Council requirements, these service costs will be assigned as Project Management Cost, duly identified in the project budget as Direct Project Costs. Eligible Direct Project Costs should not be charged as a flat percentage. They should be calculated on the basis of estimated actual or transaction-based costs and should be charged to the direct project costs account codes: “64397- Services to projects – CO staff” and “74596 – Services to projects – GOE for CO”.

- Budget Revision and Tolerance:  As per UNDP requirements outlined in the UNDP POPP, the PSC will agree on a budget tolerance level for each plan under the overall annual work plan allowing the Project Coordinator to expend up to the tolerance level beyond the approved project budget amount for the year without requiring a revision from the PSC. Should the following deviations occur, the Project Coordinator and UNDP Country Office will seek the approval of the UNDP-GEF team to ensure accurate reporting to the GEF: a) Budget re-allocations among components in the project with amounts involving 10% of the total project grant or more; b) Introduction of new budget items/or components that exceed 5% of original GEF allocation.

- Any over expenditure incurred beyond the available GEF grant amount will be absorbed by non-GEF resources (e.g., UNDP TRAC or cash co-financing).

- Refund to GEF:  Should a refund of unspent funds to the GEF be necessary, this will be managed directly by the UNDP-GEF Unit in New York.

- Project Closure:  Project closure will be conducted as per UNDP requirements outlined in the UNDP POPP.  On an exceptional basis only, a no-cost extension beyond the initial duration of the project will be sought from in-country UNDP colleagues and then the UNDP-GEF Executive Coordinator.

- Operational completion: The project will be operationally completed when the last UNDP-financed inputs have been provided and the related activities have been completed. This includes the final clearance of the Terminal Evaluation Report (that will be available in English) and the corresponding management response, and the end-of-project review PSC meeting. The Implementing Partner through a PSC decision will notify the UNDP Country Office when operational closure has been completed. At this time, the relevant parties will have already agreed and confirmed in writing on the arrangements for the disposal of any equipment that is still the property of UNDP.

- Transfer or disposal of assets: In consultation with the NIM Implementing Partner and other parties of the project, UNDP program manager (UNDP Resident Representative) is responsible for deciding on the transfer or other disposal of assets. Transfer or disposal of assets is recommended to be reviewed and endorsed by the PSC following UNDP rules and regulations. Assets may be transferred to the government for project activities managed by a national institution at any time during the life of a project. In all cases of transfer, a transfer document must be prepared and kept on file.

- Financial completion:  The project will be financially closed when the following conditions have been met: a) The project is operationally completed or has been cancelled; b) The Implementing Partner has reported all financial transactions to UNDP; c) UNDP has closed the accounts for the project; d) UNDP and the Implementing Partner have certified a final Combined Delivery Report (which serves as final budget revision).

- The project will be financially completed within 12 months of operational closure or after the date of cancellation. Between operational and financial closure, the implementing partner will identify and settle all financial obligations and prepare a final expenditure report. The UNDP Country Office will send the final signed closure documents including confirmation of final cumulative expenditure and unspent balance to the UNDP-GEF Unit for confirmation before the project will be financially closed in Atlas by the UNDP Country Office.

# Total Budget and Work Plan

| Total Budget and Work Plan |  |  |  |
| --- | --- | --- | --- |
| Atlas Proposal or Award ID: | 00096245 | Atlas Primary Output Project ID: | 00100222 |
| Atlas Proposal or Award Title: | Participatory in-situ conservation and sustainable use of agrobiodiversity in Hainan |  |  |
| Atlas Business Unit | CHN10 |  |  |
| Atlas Primary Output Project Title | Participatory in-situ conservation and sustainable use of agrobiodiversity in Hainan |  |  |
| UNDP/GEF PIMS No. | 5823 |  |  |
| Implementing Partner | Hainan Department of Agriculture and Rural Affairs |  |  |

| GEF Output/Atlas Activity | Responsible Party / (Atlas Implementing Agent) | Fund ID | Donor Name | Atlas Budgetary Account Code | ATLAS Budget Description | Amount Year 1 (USD) | Amount Year 2 (USD) | Amount Year 3 (USD) | Amount Year 4 (USD) | Amount Year 5 (USD) | Total (USD) | See Budget Note: |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Component 1 | Hainan DARA | 62000 | GEF | 71300 | Local Consultants | 11,500 | 12,690 | 13,005 | 11,600 | 11,945 | 60,740 | 1 |
|  |  |  |  | 71600 | Travel | 3,700 | 3,700 | 3,700 | 3,700 | 3,700 | 18,500 | 2 |
|  |  |  |  | 72100 | Contractual Services-Companies | 7,250 | 10,250 | 10,250 | 4,250 | 4,250 | 36,250 | 3 |
|  |  |  |  | 74200 | Audio Visual & Print Prod Costs | 1,000 | 1,000 | 1,000 | 1,000 | 1,000 | 5,000 | 4 |
|  |  |  |  | 75700 | Training, Workshops and Confer | 0 | 6,750 | 6,750 | 6,750 | 2,250 | 22,500 | 5 |
|  |  |  |  |  | Total Component 1 | 23,450 | 34,390 | 34,705 | 27,300 | 23,145 | 142,990 |  |
| Component 2 | Hainan DARA | 62000 | GEF | 71300 | Local Consultants | 30,600 | 31,020 | 31,440 | 31,900 | 32,360 | 157,320 | 6 |
|  |  |  |  | 71600 | Travel | 4,500 | 4,500 | 4,500 | 4,500 | 4,500 | 22,500 | 7 |
|  |  |  |  | 72100 | Contractual Services-Companies | 21,000 | 21,000 | 21,000 | 21,000 | 21,000 | 105,000 | 8 |
|  |  |  |  | 72200 | Equipment and Furniture | 3,450 | 20,700 | 20,700 | 20,700 | 3,450 | 69,000 | 9 |
|  |  |  |  | 72600 | Grants | 0 | 72,500 | 145,000 | 72,500 | 0 | 290,000 | 10 |
|  |  |  |  | 74200 | Audio Visual & Print Prod Costs | 2,100 | 2,100 | 2,100 | 2,100 | 2,100 | 10,500 | 11 |
|  |  |  |  | 75700 | Training, Workshops and Confer | 3,600 | 21,600 | 21,600 | 14,400 | 10,800 | 72,000 | 12 |
|  |  |  |  |  | Total Component 2 | 65,250 | 173,420 | 246,340 | 167,100 | 74,210 | 726,320 |  |
| Component 3 | Hainan DARA | 62000 | GEF | 71300 | Local Consultants | 10,400 | 10,715 | 11,030 | 11,375 | 11,720 | 55,240 | 13 |
|  |  |  |  | 71600 | Travel | 3,015 | 18,090 | 18,090 | 15,075 | 6,030 | 60,300 | 14 |
|  |  |  |  | 72100 | Contractual Services-Companies | 11,750 | 11,750 | 11,750 | 11,750 | 11,750 | 58,750 | 15 |
|  |  |  |  | 74200 | Audio Visual & Print Prod Costs | 3,802 | 3,802 | 3,802 | 3,802 | 3,802 | 19,010 | 16 |
|  |  |  |  | 75700 | Training, Workshops and Confer | 0 | 15,500 | 15,500 | 15,500 | 15,500 | 62,000 | 17 |
|  |  |  |  |  | Total Component 3 | 28,967 | 59,857 | 60,172 | 57,502 | 48,802 | 255,300 |  |
| Component 4 | Hainan DARA | 62000 | GEF | 71200 | International Consultants | 0 | 0 | 18,000 | 0 | 18,000 | 36,000 | 18 |
|  |  |  |  | 71300 | Local Consultants | 8,350 | 8,560 | 8,770 | 9,000 | 9,230 | 43,910 | 19 |
|  |  |  |  | 71600 | Travel | 3,400 | 3,400 | 3,400 | 3,400 | 3,400 | 17,000 | 20 |
|  |  |  |  | 72100 | Contractual Services-Companies | 11,500 | 11,500 | 11,500 | 11,500 | 11,500 | 57,500 | 21 |
|  |  |  |  | 72800 | Information Technology Equipment | 0 | 0 | 10,000 | 0 | 0 | 10,000 | 22 |
|  |  |  |  | 74100 | Professional Services | 5,000 | 5,000 | 5,000 | 5,000 | 5,000 | 25,000 | 23 |
|  |  |  |  | 74200 | Audio Visual & Print Prod Costs | 720 | 720 | 720 | 733 | 720 | 3,613 | 24 |
|  |  |  |  | 75700 | Training, Workshops and Confer | 12,000 | 12,000 | 12,000 | 12,000 | 12,000 | 60,000 | 25 |
|  |  |  |  |  | Total Component 4 | 40,970 | 41,180 | 69,390 | 41,633 | 59,850 | 253,023 |  |
| Project Management | Hainan DARA | 62000 | GEF | 71600 | Travel | 2,000 | 2,000 | 2,000 | 2,000 | 2,000 | 10,000 | 26 |
|  |  |  |  | 71800 | Contractual Services - Imp Partner | 18,000 | 18,900 | 19,860 | 20,880 | 21,960 | 99,600 | 27 |
|  |  |  |  | 72500 | Supplies | 600 | 600 | 600 | 600 | 600 | 3,000 | 28 |
|  |  |  |  | 72800 | Information Technology Equipment | 5,110 | 0 | 0 | 0 | 0 | 5,110 | 29 |
|  |  |  |  | 74500 | Miscellaneous Expenses | 2,460 | 3,455 | 2,460 | 3,455 | 2,460 | 14,290 | 30 |
|  |  |  |  |  | Total Project Management | 28,170 | 24,955 | 24,920 | 26,935 | 27,020 | 132,000 |  |
|  |  |  |  | PROJECT TOTAL |  | 186,807 | 333,802 | 435,527 | 320,470 | 233,027 | 1,509,633 |  |

Summary of Funds:

| Source | Amount | Amount | Amount | Amount | Amount | Total |
| --- | --- | --- | --- | --- | --- | --- |
|  | Year1 | Year 2 | Year 3 | Year 4 | Year 5 |  |
| GEF | $186,807 | $333,802 | $435,527 | $320,470 | $233,027 | $1,509,633 |
| Recipient Government, Hainan Provincial DARA | $1,984,000 | $1,984,000 | $1,984,000 | $1,984,000 | $1,984,000 | $9,920,000 |
| Hainan Tian Heng Agricultural Development Co., Ltd. | $12,000 | $12,000 | $12,000 | $12,000 | $12,000 | $60,000 |
| Fomianshan Farmers Association of Cultivation and Animal Husbandry in Baisha | $30,000 | $30,000 | $30,000 | $30,000 | $30,000 | $150,000 |
| Hainan Chuanwei Muscovy Duck Breeding Co., Ltd. | $6,000 | $6,000 | $6,000 | $6,000 | $6,000 | $30,000 |
| TOTAL | $2,218,807 | $2,365,802 | $2,467,527 | $2,352,470 | $2,265,027 | $11,669,633 |

Budget Notes:

| Budget note number | Comments |
| --- | --- |
| Component 1 / Outcome 1: |  |
| 1 | 71300. Local consultants. Project National Technical Advisor supporting all outputs under Component 1 (3 months per year for 5 years, at a gross salary of USD 2,050 per month, adjusted with a cost of living adjustment of 5% per year starting in year 2; Total: USD 33,990); Project Chief Technical Advisor supporting all outputs under Component 1 (12 weeks over 5 years at USD 1,500 per week; Total: USD 18,000); Environmental Economist under Output 1.3 for analysis of eco-compensation opportunities, developing draft guideline, preparing implementation plan for eco-compensation demonstration and evaluating demonstration results, and preparing final version of guideline (7 weeks at USD 1,250 per week; Total: USD 8,750). Total: USD 60,740 |
| 2 | 71600. Travel. Travel expenses associated with: Output 1.1: operationalizing the provincial GRFA coordination committee and the 3 county-level GRFA coordination committees under over the course of the 5-year project (Total: USD 10,000); Output 1.1: knowledge transfer exchange between the provincial/county GRFA coordination committees with national level GRFA coordination mechanisms (Total: USD 3,000); Output 1.3: knowledge transfer exchange to other interventions in China where eco-compensation schemes involving GRFA conservation are under implementation (Total: USD 4,000); Output 1.3: cross-sectoral workshop on eco-compensation (Total: USD 1,500). Total: USD 18,500 |
| 3 | 72100. Contractual services – Company. Technical assistance by research institutions, consultancies, companies or other service providers: Policy/legal development assistance under Output 1.1 for preparing GRFA coordination committee charters and knowledge-sharing procedures (2 weeks at USD 1,250 per week; Total USD 2,500); under Output 1.2 for carrying out policy/legal gap analysis and preparing recommendations, preparing a provincial agrobiodiversity strategy and action plan, preparing draft provincial GRFA implementation frameworks, preparing county level GRFA implementation frameworks (14 weeks at USD 1,250 per week; Total: USD 17,500); under Output 1.3 for supporting the development of an eco-compensation demonstration plan and for evaluating the results of the demonstration (2 weeks at USD 1,250 per week; Total: USD 2,500). Knowledge management technical assistance under Output 1.1 for supporting the development of procedures and protocols for the knowledge-sharing platform (1 week at USD 1,250; Total: USD 1,250). Capacity development technical assistance under Output 1.1 for supporting the establishment of inter-sectoral and cross-sectoral GRFA coordination committees (4 weeks at USD 1,250 per week; Total: USD 5,000) GRFA expert technical assistance under Output 1.3 for supporting the gap analysis of eco-compensation opportunities and development of draft guidelines, preparing the eco-compensation demonstration plan, and evaluating the results of the demonstration (6 weeks at USD 1,250 per week; Total: USD 7,500). Total: USD 36,250 |
| 4 | 74200. Audio-visual and print production costs. Audio-visual and print production for knowledge products used for disseminating information, awareness-raising and advocacy. Output 1.2 in support of the stakeholder workshop on GRFA strategies and regulatory frameworks (Total: USD 2,500). Output 1.3 in support of the stakeholder workshop on eco-compensation schemes (Total: USD 2,500). Total: USD 5,000 |
| 5 | 75700. Training, workshop, conference. Output 1.1: convening regular GRFA coordination meetings (Total: USD 2,500). Output 1.1: organizing a knowledge transfer exchange with the national GRFA coordination mechanisms (Total: USD 5,000). Output 1.2: organizing a stakeholder workshop on GRFA strategies and regulatory frameworks (Total: USD 5,000). Output 1.3: organizing a domestic knowledge transfer exchange to other interventions in China where eco-compensation schemes involving GRFA conservation are under implementation (Total: USD 5,000). Output 1.3: Organizing a stakeholder workshop on eco-compensation schemes and opportunities (Total: USD 5,000). Total: USD 22,500 |
| Component 2 / Outcome 2: |  |
| 6 | 71300. Local consultants. Project National Technical Advisor supporting all outputs under Component 2 (4 months per year for 5 years, at a gross salary of USD 2,050 per month, adjusted with a cost of living adjustment of 5% per year starting in year 2; Total: USD 45,320); Project Chief Technical Advisor supporting all outputs under Component 2 (8 weeks over 5 years at USD 1,500 per week; Total: USD 12,000); Environmental Economist under Output 2.1, supporting development of GRFA conservation and sustainable use plans (3 weeks at USD 1,250 per week; Total: USD 3,750); under Output 2.2, providing technical assistance in the implementation of the eco-compensation demonstration plan (4 weeks at USD 1,250 per week; Total: USD 5,000); under Output 2.3, providing technical assistance for value/supply chain analyses (3 weeks at USD 1,250 per week; Total: 3,750). Community Development/M&E Specialist under Output 2.1, supporting operationalization of landscape partnership working groups and delivering training to committee members, and supporting the participatory GRFA landscape assessments (8 weeks at USD 1,250 per week; Total: USD 10,000); under Output 2.2, supporting development of calls for proposals, review of submitted proposals, facilitating implementation of GRFA conservation and sustainable use plans, establishment of community seed bank(s) for Shanlan rice, organization of livestock competitions for Wuzhishan pig and Jiaji duck, eco-compensation demonstration, monitoring & evaluation of the implementation of the GRFA conservation and sustainable use plans, and organization of a workshop on traditional knowledge (28 weeks at USD 1,250 per week; Total: USD 35,000); under Output 2.4, supporting the development of a capacity development plan for farmers, agricultural associations and enterprises, supporting implementation of actions according with capacity development plans, and organizing trade fairs showcasing GRFA products and services (5 weeks at USD 1,250 per week; Total: USD 6,250). Gender Specialist under Output 2.1, providing professional assistance in operationalizing the landscape partnership working groups and delivering training to the committee members (4 weeks at USD 1,250 per week; Total: USD 5,000); under Output 2.2, facilitating the implementation of the GRFA conservation and sustainable use plans and supporting the organization of a workshop on traditional GRFA knowledge (4 weeks at USD 1,250 per week; Total: USD 5,000); under Output 2.3, providing professional assistance in the establishment and operationalization of women’s GRFA marketing groups (3 weeks at USD 1,250 per week; Total: USD 3,750); under Output 2.4, providing professional assistance in knowledge transfer and partnership establishment exchanges (1 week at USD 1,250 per week; Total: USD 1,250). Business Development Specialist under Output 2.1, delivering training to landscape partnership working group members (2 weeks at USD 1,250 per week; Total: USD 2,500); under Output 2.3, providing technical assistance for value/chain analyses, preparing business development plans and preparing promotional products (8 weeks at USD 1,250 per week; Total: USD 10,000); under Output 2.4, providing technical assistance for developing capacity development plans for farmers and agricultural associations, supporting the implementation of the capacity development plans, and organizing GRFA trade fairs on showcasing GRFA products and services (7 weeks at USD 1,250 per week; USD 8,750). Total: USD 157,320 |
| 7 | 71600. Travel. Travel expenses associated with: Output 2.1: delivering training to landscape partnership working groups (Total: USD 2,000); Output 2.1: carrying out 3 participatory GRFA landscape assessments (Total: USD 6,000); Output 2.2: carrying out monitoring & evaluation of the implementation of GRFA conservation and sustainable use plans (Total: USD 2,500); Output 2.2: organizing a workshop on best practices in applying traditional knowledge for GRFA conservation (Total: USD 3,000); Output 2.3: carrying out value/supply chain analyses for each of the three target GRFA varieties (Total: USD 3,000); Output 2.4: knowledge transfer exchange and partnership development exchanges (Total: USD 4,000); Output 2.4: GRFA trade fairs, showcasing GRFA products and services (Total: USD 2,000). Total: USD 22,500 |
| 8 | 72100. Contractual services – Company. Technical assistance by research institutions, consultancies, companies or other service providers: GRFA expert technical assistance under Output 2.1 for developing a standard protocol for participatory GRFA landscape assessments, carrying out participatory landscape assessments of the three GRFA demonstration landscapes and developing GRFA conservation and sustainable use plans (9 weeks at USD 1,250 per week; Total: USD 11,250); under Output 2.2 for supporting the implementation of the GRFA conservation and sustainable use plans, design and establishment of the Shanlan rice community seed bank(s), and design and implementation of livestock competitions for Wuzhishan pig and Jiaji duck, and support M&E activities (24 weeks at USD 1,250 per week; Total: USD 30,000); under Output 2.4 for supporting the development of the capacity development plan for farmers, agricultural associations and enterprises (1 week at USD 1,250 per week; Total USD 1,250). Knowledge management technical assistance under Output 2.2 for supporting the communication of results of the implementation of GRFA conservation and sustainable use plans and development of knowledge products of the community interventions (4 weeks at USD 1,250 per week; Total: USD 5,000); under Output 2.3 for preparing a standard code of practice for GRFA conservation and preparing promotional and informative products for specific GRFA offerings (4 weeks at USD 1,250 per week; Total: USD 5,000). Microgrant management services under Output 2.2 for developing calls for proposals for implementing actions under the GRFA conservation and sustainable use plans, reviewing proposals and preparing microgrant agreements and facilitating the implementation of interventions funded with the microgrants (18 weeks at USD 1,250 per week; Total: USD 22,500); under Output 2.3 for facilitating disbursement and overseeing microgrants for interventions associated with the business development plans (4 weeks at USD 1,250 per week; Total: USD 5,000); under Output 2.4 for facilitating and overseeing microgrants for interventions associated with farmer capacity development plans (4 weeks at USD 1,250 per week; Total: USD 5,000). Microgrant funds Capacity development technical assistance under Output 2.4 for preparing an updated capacity development plan for farmers, agricultural associations and enterprises and supporting the delivery of capacity development activities (5 weeks at USD 1,250 per week; Total: USD 6,250). Marketing/branding technical assistance under Output 2.3 for supporting the establishment and operationalization of women’s GRFA marking groups and facilitating interventions implemented under the business development plans (7 weeks at USD 1,250 per week; Total: USD 8,750); under Output 2.4 for supporting the interventions implemented under the capacity development plans (4 weeks at USD 1,250 per week; USD 5,000). Total: USD 105,000 |
| 9 | 72200. Equipment and furniture. Output 2.1: procuring equipment to support the operation of the three landscape partnership working groups, including basic office furniture, cameras, laptop and printer, etc. (USD 3,000 per landscape; Total: USD 9,000). Output 2.1: procuring equipment to support monitoring and evaluation of agroecosystem health and diversity status within the three GRFA demonstration landscapes, indicatively including stationary cameras, video cameras, basic weather station, soil testing equipment, water testing equipment, etc. (USD 20,000 per landscape; Total: USD 60.000) Total: USD 69,000 |
| 10 | 72600. Grants. Microgrant schemes implemented consistent with the UNDP on-granting facility and managed by a contracted service provider. Microgrants include: under Output 2.2, for interventions associated with improved farming approaches, to increase yield, demonstrate improved breeding practices, improve management of agricultural chemicals and wastes, strengthen management of invasive alien species, etc. (USD 25,000 allocated for each of the three landscapes for microgrants estimated between USD 1,000-3,000; Total: USD 75,000), for establishment of a community seed bank for Shanlan rice (Total: USD 10,000), for implementation of Wuzhishan pig livestock competitions (USD 7,500 per competition for 3 years: Total: USD 22,500), for implementation of Jiaji duck livestock competitions (USD 7,500 per competition for 3 years: Total: USD 22,500), for supporting the eco-compensation demonstration (USD 25,000); under Output 2.3 for interventions available to farmers, women’s groups and other community organizations, agricultural associations and enterprises, including but not limited to: (a) developing niche markets; (b) obtaining or improving the marketing of product certification; (c) promoting cultural preference/branding; (d) strengthening collective marketing approaches; (e) improving quality control of GRFA products and offerings; (f) developing specific agro-ecotourism experiences; (g) introducing or expanding traceability schemes for GRFA varieties; (h) promoting recognition of traditional knowledge; etc. (USD 20,000 allocated per landscape for microgrants estimated between USD 1,000-3,000; Total: USD 60,000); under Output 2.4 for interventions available to farmers, agricultural associations and enterprises, including but not limited to: (a) improving financial management and other small business skills; (b) expanding online trading approaches; (c) improving quality control of GRFA products and offerings; (d) specific trainings on expanding inclusion of women and youth; etc. (USD 25,000 allocated per landscape for microgrants estimated USD 1,000-3,000; Total: USD 75,000). Total: USD 290,000 |
| 11 | 74200. Audio visual & print production costs. Audio-visual and print production for knowledge products used for disseminating information, awareness-raising and advocacy. Output 2.1 in support of the standard protocol for participatory GRFA landscape assessments (Total: USD 2,500). Output 2.2 for knowledge products on community interventions as part of implementation of GRFA conservation and sustainable use plans (Total: USD 2,500). Output 2.2 in support of the stakeholder workshop on traditional knowledge for GRFA conservation (Total: USD 1,500). Output 2.3 in support of the development of a standard code of practice for GRFA conservation (Total: USD 500). Output 2.3 in support of the operationalization of women’s GRFA marketing groups (Total: USD 500). Output 2.3 for promotional and information products for specific GRFA offerings (Total: USD 3,000). Total: USD 10,500 |
| 12 | 75700. Training, Workshop, Conference. Output 2.1: delivering training to the members of the landscape partnership working groups in the three demonstration GRFA landscapes (Total: USD 3,000). Output 2.2: convening a workshop on best practices in applying traditional knowledge for GRFA conservation (Total: USD 4,000). Output 2.4: delivering capacity development to farmers and members of agricultural associations and enterprises, with a target of a total of 480 people trained. For each of the three demonstration landscapes, USD 15,000 allocated (Total: USD 45,000). Output 2.4: organizing one trade fair in Hainan Province (USD 8,000) and one in each of the three target provinces (3 x USD 4,000), promoting GRFA products and offerings, showcasing nutritional and taste value of GRFA varieties and to facilitate marketing and partnership opportunities (Total: USD 20,000). Total: USD 72,000 |
| Component 3 / Outcome 3: |  |
| 13 | 71300. Local consultants. Project National Technical Advisor supporting all outputs under Component 3 (3 months per year for 5 years, at a gross salary of USD 2,050 per month, adjusted with a cost of living adjustment of 5% per year starting in year 2; Total: USD 33,990); Project Chief Technical Advisor supporting all outputs under Component 3 (5 weeks over 5 years at USD 1,500 per week; Total: USD 7,500); Gender Specialist under Output 3.1, providing professional assistance in the development of an institutional capacity development plan, developing capacity-building materials and guidelines, and delivering training to women professionals (4 weeks at USD 1,250 per week; Total: USD 5,000). Environmental Economist under Output 3.3, providing technical assistance in developing a replication strategy and upscaling plan (1 week at USD 1,250; Total: USD 1,250). Community Development/M&E Specialist under Output 3.3, providing professional assistance for the participatory GRFA landscape assessments and for developing GRFA conservation and sustainable use plans for two replication landscapes (6 weeks at USD 1,500 per week; Total: USD 6,250); Total: USD 55,240 |
| 14 | 71600. Travel. Travel expenses associated with: Output 3.1: delivering capacity development to institutional staff members (Total: USD 5,000); Output 3.1: organizing domestic and international knowledge transfer exchanges, including at least one international exchange involving 5 institutional staff members (Total: USD 40,000); Output 3.1: delivering targeted training to women professionals (Total: USD 1,500); Output 3.1: delivering targeted training to young professionals (Total: USD 1,800); Output 3.2: organizing a provincial workshop on mainstreaming incentivized approaches for participatory GRFA conservation (Total: USD 3,000); Output 3.3: organizing domestic knowledge exchange with stakeholders in replication landscapes (Total: USD 5,000); Output 3.3: supporting participatory landscape assessments in two replication landscapes (Total: USD 4,000). Total: USD 60,300 |
| 15 | 72100. Contractual services – Company. Technical assistance by research institutions, consultancies, companies or other service providers: Policy/legal development assistance under Output 3.2 for developing a best practices guideline for incentivized approaches for participatory GRFA conservation, for supporting integration of incentivized approaches into agricultural sector work programs, and supporting stakeholder workshops on disseminating information mainstreaming incentivized approaches (8 weeks at USD 1,250 per week; Total: 10,000); under Output 3.3 for supporting the development of a replication strategy and upscaling plan (1 week at USD 1,250 per week; Total: USD 1,250). GRFA expert technical assistance under Output 3.1 for supporting development of institutional capacity development plan, preparing capacity-building materials, delivering trainings on GRFA conservation and sustainable use, participating in knowledge transfer exchanges, and delivering targeted trainings for women and youth (8 weeks at USD 1,250 per week; Total: 10,000); under Output 3.3 for supporting preparation of a replication strategy and upscaling plan, participating in knowledge transfer exchanges in replication landscapes, supporting participatory landscape assessments and development of GRFA conservation and sustainable use plans in replication landscapes (9 weeks at USD 1,250 per week; Total: USD 11,250). Capacity development technical assistance under Output 3.1 for developing an institutional capacity development plan, preparing capacity-building materials, delivering trainings, organizing knowledge transfer exchanges, and delivering targeted trainings for women and youth (19 weeks at USD 1,250 per week; Total: USD 23,750); under Output 3.3 for supporting the organization of knowledge transfer exchanges in replication landscapes (2 weeks at USD 1,250 per week; Total: USD 2,500). Total: USD 58,750 |
| 16 | 74200. Audio visual & print production costs. Audio-visual and print production for knowledge products used for disseminating information, awareness-raising and advocacy. Output 3.1 for capacity-building materials, guidelines and training manuals (Total: USD 15,000). Output 3.2 in support of the stakeholder workshop on incentivized approaches for participatory GRFA conservation (Total: USD 3,510). Output 3.3 in support of the participatory landscape assessments in two replication landscapes (Total: USD 500). Total: USD 19,010 |
| 17 | 75700. Training, Workshop, Conference. Output 3.1: delivering capacity development activities to institutional staff members of the provincial and county level agencies, with the target of training 180 people, in GRFA conservation and sustainable use (Total: USD 30,000). Output 3.1: organizing domestic and international knowledge transfer exchanges to other C-SAP child projects and complimentary programs and initiatives (Total: USD 20,000). Output 3.1: delivering targeted training to women professionals (Total: USD 2,000). Output 3.1: delivering targeted training to young professionals (Total: USD 2,000). Output 3.2: organizing stakeholder workshops (one provincial and three county level) to disseminate information on incentivized approaches for participatory GRFA conservation (Total: USD 5,000). Output 3.3: organizing knowledge transfer exchanges with stakeholders in replication landscapes (Total: USD 3,000). Total: USD 62,000 |
| Component 4 / Outcome 4: |  |
| 18 | 71200. International consultants. Midterm review consultant under Output 4.1 (6 weeks at USD 3,000 per week, in Year 3; Total: USD 18,000); Terminal evaluation consultant under Output 4.1 (6 weeks at USD 3,000 per week, in Year 5; Total: USD 18,000); Total: USD 36,000 |
| 19 | 71300. Local consultants. Project National Technical Advisor supporting all outputs under Component 4 (2 months per year for 5 years, at a gross salary of USD 2,050 per month, adjusted with a cost of living adjustment of 5% per year starting in year 2; Total: USD 22,660); Project Chief Technical Advisor supporting all outputs under Component 4 (5 weeks over 5 years at USD 1,500 per week; Total: USD 7,500); Community Development/M&E Specialist, under Output 4.1, providing professional M&E assistance and supporting the independent midterm review and terminal evaluation (11 weeks at USD 1,250 per week; Total: USD 13,750). Total: USD 43,910 |
| 20 | 71600. Travel. Travel expenses associated with: Output 4.1: carrying out midterm review (Total: USD 4,000); Output 4.1: carrying out terminal evaluation (Total: USD 4,000); Output 4.2: carrying out the baseline KAP survey (Total: USD 2,500); Output 4.2: organizing awareness raising and advocacy campaigns (Total: USD 2,000); Output 4.2: organizing a targeted awareness event for young people (Total: USD 2,000); Output 4.2: carrying out the end-of-project KAP survey (Total: USD 1,500); Output 4.3: delivering training on monitoring agroecosystem health, as part of the GRFA database development (Total: USD 1,000). Total: USD 17,000 |
| 21 | 72100. Contractual services – Company. Technical assistance by research institutions, consultancies, companies or other service providers: GRFA expert technical assistance under Output 4.3 for supporting development and training of the GRFA database (4 weeks at USD 1,250 per week; Total: USD 5,000). Knowledge management technical assistance under Output 4.2 for designing, administering and interpreting baseline and end-of-project KAP surveys, development a knowledge management action plan for the project, developing knowledge and communication platforms, organizing awareness-raising and advocacy campaigns, organizing targeted awareness for youth (18 weeks at USD 1,250 per week; Total: USD 22,500). Database development assistance under Output 4.3 for preparing a database development plan, improving the existing GRFA provincial database, and delivering trainings on the operation of the database (24 weeks at USD 1,250 per week; Total: USD 30,000). Total: USD 57,500 |
| 22 | 72800. Information technology equipment. IT equipment to support demonstration of remote operation of the GRFA database (Total: USD 10,000). Total: USD 10,000 |
| 23 | 74100. Professional Services. Financial NIM audit under Output 4.1 (USD 5,000 per year for each year). Total: USD 25,000 |
| 24 | 74200. Audio visual & print production costs. Audio-visual and print production for knowledge products used for disseminating information, awareness-raising and advocacy. Output 4.2 in support of the baseline KAP survey (Total: USD 500). Output 4.2 in support of awareness-raising and advocacy campaigns (Total: USD 2,000). Output 4.2 in support of a targeted awareness event for young people (Total: USD 1,113). Total: USD 3,613 |
| 25 | 75700. Training, Workshop, Conference. Output 4.1: organizing the project inception workshop in Year 1, including the first project steering committee meeting (USD 11,000). Output 4.1: organizing annual project steering committee meetings in Years 2, 3, 4 and 5, coincident with annual stakeholder meetings (USD 5,000 per year for 4 years; Total: 20,000). Output 4.1: hosting one C-SAP program steering committee meeting, showcasing the results achieved on the Hainan project (Total: USD 8,000). Output 4.2: advocating the global environmental benefits generated through the project by participating in conferences, workshops, seminars and other events (Total: USD 10,000). Output 4.2: organizing awareness-raising and advocacy campaigns (Total: USD 5,000). Output 4.2: organizing a targeted awareness event for youth (Total: USD 3,000). Output 4.3: delivering training on the operation and updating of the GRFA database (Total: USD 1,500). Output 4.3: delivering training on monitoring of agroecosystem health, in connection with the GRFA database (Total: USD 1,500). Total: USD 60,000 |
| Project Management: |  |
| 26 | 71600. Travel. Travel expenses in support of project management, including local transportation for the project management office team (USD 2,000 per year). Total: USD 10,000 |
| 27 | 71800. Contractual services – Implementation Partners. Project Coordinator (12 months per year for 5 years, at a gross salary of USD 1,500 per month, adjusted with a cost of living adjustment of 5% per year starting in year 2; Total: USD 99,600); Total: USD 99,600 |
| 28 | 72500. Supplies. Costs of office supplies at USD 600 per year for each of the 5 years of implementation. Total: USD 3,000 |
| 29 | 72800. Information technology equipment. IT equipment including laptop computer, multifunction printer/scanner and other IT equipment for Project Coordinator. Total: USD 5,110 |
| 30 | 74500. Miscellaneous expenses. PMO related expenses including telephone, internet, insurance, etc. Total: USD 14,290 |

# Legal Context

Option a. Where the country has signed the Standard Basic Assistance Agreement (SBAA)

- This project document shall be the instrument referred to as such in Article 1 of the Standard Basic Assistance Agreement between the Government of (country) and UNDP, signed on (date).   All references in the SBAA to “Executing Agency” shall be deemed to refer to “Implementing Partner.”

- This project will be implemented by the Hainan Department of Agriculture and Rural Affairs (“Implementing Partner”) in accordance with its financial regulations, rules, practices and procedures only to the extent that they do not contravene the principles of the Financial Regulations and Rules of UNDP. Where the financial governance of an Implementing Partner does not provide the required guidance to ensure best value for money, fairness, integrity, transparency, and effective international competition, the financial governance of UNDP shall apply.

- Any designations on maps or other references employed in this project document do not imply the expression of any opinion whatsoever on the part of UNDP concerning the legal status of any country, territory, city or area or its authorities, or concerning the delimitation of its frontiers or boundaries.

# Risk Management

Option a. Government Entity (NIM)

- Consistent with the Article III of the SBAA, the responsibility for the safety and security of the Implementing Partner and its personnel and property, and of UNDP’s property in the Implementing Partner’s custody, rests with the Implementing Partner.  To this end, the Implementing Partner shall:

- put in place an appropriate security plan and maintain the security plan, taking into account the security situation in the country where the project is being carried;

- assume all risks and liabilities related to the Implementing Partner’s security, and the full implementation of the security plan.

- UNDP reserves the right to verify whether such a plan is in place, and to suggest modifications to the plan when necessary. Failure to maintain and implement an appropriate security plan as required hereunder shall be deemed a breach of the Implementing Partner’s obligations under this Project Document.

- The Implementing Partner agrees to undertake all reasonable efforts to ensure that no UNDP funds received pursuant to the Project Document are used to provide support to individuals or entities associated with terrorism and that the recipients of any amounts provided by UNDP hereunder do not appear on the list maintained by the Security Council Committee established pursuant to resolution 1267 (1999). The list can be accessed via http://www.un.org/sc/committees/1267/aq_sanctions_list.shtml.

- Social and environmental sustainability will be enhanced through application of the UNDP Social and Environmental Standards (http://www.undp.org/ses) and related Accountability Mechanism (http://www.undp.org/secu-srm).

- The Implementing Partner shall: (a) conduct project-related activities in a manner consistent with the UNDP Social and Environmental Standards, (b) implement any management or mitigation plan prepared for the project to comply with such standards, and (c) engage in a constructive and timely manner to address any concerns and complaints raised through the Accountability Mechanism. UNDP will seek to ensure that communities and other project stakeholders are informed of and have access to the Accountability Mechanism.

- All signatories to the Project Document shall cooperate in good faith with any exercise to evaluate any project-related commitments or compliance with the UNDP Social and Environmental Standards. This includes providing access to project sites, relevant personnel, information, and documentation.

- The Implementing Partner will take appropriate steps to prevent misuse of funds, fraud or corruption, by its officials, consultants, responsible parties, subcontractors and sub-recipients in implementing the project or using UNDP funds.  The Implementing Partner will ensure that its financial management, anti-corruption and anti-fraud policies are in place and enforced for all funding received from or through UNDP.

- The requirements of the following documents, then in force at the time of signature of the Project Document, apply to the Implementing Partner: (a) UNDP Policy on Fraud and other Corrupt Practices and (b) UNDP Office of Audit and Investigations Investigation Guidelines. The Implementing Partner agrees to the requirements of the above documents, which are an integral part of this Project Document and are available online at www.undp.org.

- In the event that an investigation is required, UNDP has the obligation to conduct investigations relating to any aspect of UNDP projects and programmes. The Implementing Partner shall provide its full cooperation, including making available personnel, relevant documentation, and granting access to the Implementing Partner’s (and its consultants’, responsible parties’, subcontractors’ and sub-recipients’) premises, for such purposes at reasonable times and on reasonable conditions as may be required for the purpose of an investigation. Should there be a limitation in meeting this obligation, UNDP shall consult with the Implementing Partner to find a solution.

- The signatories to this Project Document will promptly inform one another in case of any incidence of inappropriate use of funds, or credible allegation of fraud or corruption with due confidentiality.

- Where the Implementing Partner becomes aware that a UNDP project or activity, in whole or in part, is the focus of investigation for alleged fraud/corruption, the Implementing Partner will inform the UNDP Resident Representative/Head of Office, who will promptly inform UNDP’s Office of Audit and Investigations (OAI). The Implementing Partner shall provide regular updates to the head of UNDP in the country and OAI of the status of, and actions relating to, such investigation.

- UNDP shall be entitled to a refund from the Implementing Partner of any funds provided that have been used inappropriately, including through fraud or corruption, or otherwise paid other than in accordance with the terms and conditions of the Project Document.  Such amount may be deducted by UNDP from any payment due to the Implementing Partner under this or any other agreement.

- Where such funds have not been refunded to UNDP, the Implementing Partner agrees that donors to UNDP (including the Government) whose funding is the source, in whole or in part, of the funds for the activities under this Project Document, may seek recourse to the Implementing Partner for the recovery of any funds determined by UNDP to have been used inappropriately, including through fraud or corruption, or otherwise paid other than in accordance with the terms and conditions of the Project Document.

- Note:  The term “Project Document” as used in this clause shall be deemed to include any relevant subsidiary agreement further to the Project Document, including those with responsible parties, subcontractors and sub-recipients.

- Each contract issued by the Implementing Partner in connection with this Project Document shall include a provision representing that no fees, gratuities, rebates, gifts, commissions or other payments, other than those shown in the proposal, have been given, received, or promised in connection with the selection process or in contract execution, and that the recipient of funds from the Implementing Partner shall cooperate with any and all investigations and post-payment audits.

- Should UNDP refer to the relevant national authorities for appropriate legal action any alleged wrongdoing relating to the project, the Government will ensure that the relevant national authorities shall actively investigate the same and take appropriate legal action against all individuals found to have participated in the wrongdoing, recover and return any recovered funds to UNDP.

- The Implementing Partner shall ensure that all of its obligations set forth under this section entitled “Risk Management” are passed on to each responsible party, subcontractor and sub-recipient and that all the clauses under this section entitled “Risk Management Standard Clauses” are included, mutatis mutandis, in all sub-contracts or sub-agreements entered into further to this Project Document.

# Annexes

- Annex A: Multi Year Work Plan

- Annex B: Overview of Technical Consultancies/subcontracts

- Annex C: Terms of Reference for Project Steering Committee, National Project Director, Project Coordinator, National Technical Advisor and Chief Technical Advisor

- Annex D: UNDP Social and Environmental Screening Procedure

- Annex E: Stakeholder Engagement Plan

- Annex F: List of people consulted during project development

- Annex G: Gender Analysis and Action Plan

- Annex H: UNDP Risk Log

- Annex I: Results of the capacity assessment of the project IP and HACT micro assessment

- Annex J: UNDP Project Quality Assurance Report

- Annex K: Baseline report on policy, governance and knowledge management

- Annex L: Baseline report on demonstration landscapes

- Annex M: Preliminary Capacity Development Needs Assessment, Baseline Scorecard and Indicative Capacity Development Plan

- Annex N: Framework for knowledge, attitudes and practices (KAP) survey

- Annex O: Additional Agreements (cofinancing agreements)

China country report of the second national survey of animal genetic resources, 2012, Ministry of Agriculture and Rural Affairs (MARA).

Vavilov, N.I. 1949. The origin, variation, immunity and breeding of cultivated plants. Chron. Bot. 13:1-54.

China country report on the state of plant genetic resources for food and agriculture, 2008. MARA

Xu H, Qiang S, Genovesi P, Ding H, Wu J, Meng L, Han Z, Miao J, Hu B, Guo J, Sun H, Huang C, Lei J, Le Z, Zhang X, He S, Wu Y, Zheng Z, Chen L, Jarošík V, Pyšek P (2012) An inventory of invasive alien species in China.NeoBiota 15: 1–26. doi: 10.3897/neobiota.15.3575

Ren et al. 2013. Climate change impacts on Central China and adaptation measures. Advances in Climate Change Research 4(4):215-222.

Direct agricultural emissions (food emissions) factsheet. Research program on Climate Change, Agriculture and Food Security. CGIAR, CCAFS.

Impact on South sea ecosystem by invasive alien species in Southern breeding and the research and service platform construction of ecological security defense system in Southern breeding, specifically for the development of invasion ecology and control technology research products of Mikania micrantha, Alternanthera philoxeroides and Brontispa longissimi.

Seib, N. (ed., 2011): Best Practices, Sino-German Project on Sustainable Management of Agrobiodiversity. GIZ, Beijing.

Wen, J. and Q. Min. September 2017. Reviewing the Progress in the Identification, Conservation and Management of China-Nationally Important Agricultural Heritage Systems (China-NIAHS). Sustainability 2017, 9, 1698; doi:10.3390/su9101698. MDPI.

Scherr, S.J. and J. A. McNeely, 2008. Biodiversity conservation and agricultural sustainability: towards a new paradigm of ‘eco-agriculture’ landscapes. Phil. Trans. R. Soc. B (2008) 363, 477–494.

Cai et al., Study on Identification of Hainan Special Wild Boar by DNA Barcoding, China Animal Husbandry & Veterinary Medicine 2018,45(05),1283-1288.

Cao et al., The Status Quo, Protection, Development and Utilization of Wuzhishan Pig Resources, Journal of Domestic Animal Ecology, 2017,38(07),79-83

Personal communication with Dr. Yin Ming, Associate Researcher and Rice Research Expert, Institute of Varieties Resources of the Chinese Academy of Tropical Sciences, Hainan Province.

Updated Results Architecture for GEF-7. GEF/C.54/11/Rev.02, June 26, 2018.

GEF-6 Programming Directions. Extract from GEF Assembly Document GEF/A.5/Rev.01, May 22, 2014.

The referenced Medium and Long-term Youth Development Plan (2016-2025) defines “youth” as those aged from 14 to 35 years.

See http://www.undp.org/content/undp/en/home/operations/transparency/information_disclosurepolicy/

See https://www.thegef.org/gef/policies_guidelines

Outcomes are short to medium term results that the project makes a contribution towards, and that are designed to help achieve the longer-term objective.  Achievement of outcomes will be influenced both by project outputs and additional factors that may be outside the direct control of the program

Baseline, mid-term and end of project target levels must be expressed in the same neutral unit of analysis as the corresponding indicator. Baseline is the current/original status or condition and need to be quantified. The baseline must be established before the project document is submitted to the GEF for final approval. The baseline values will be used to measure the success of the program through implementation monitoring and evaluation.

Target is the change in the baseline value that will be achieved by the mid-term review and then again by the terminal evaluation.

Data collection methods should outline specific tools used to collect data and additional information as necessary to support monitoring. The PIR cannot be used as a source of verification.

See https://www.thegef.org/gef/policies_guidelines

See https://www.thegef.org/gef/gef_agencies

See guidance here:  https://info.undp.org/global/popp/frm/pages/financial-management-and-execution-modalities.aspx

see  https://info.undp.org/global/popp/ppm/Pages/Closing-a-Project.aspx

See https://popp.undp.org/_layouts/15/WopiFrame.aspx?sourcedoc=/UNDP_POPP_DOCUMENT_LIBRARY/Public/PPM_Project%20Management_Closing.docx&action=default.