GEF-6 REQUEST FOR PROJECT ENDORSEMENT/APPROVAL

Project Type:

Type of Trust Fund:

For more information about GEF, visit TheGEF.org

# part i: project information

| Project Title: On-farm Conservation and Sustainable Use of Genetic Diversity of Crops Originated in China. |  |  |  |  |
| --- | --- | --- | --- | --- |
| Country(ies): | China | GEF Project ID: |  | 9876 |
| GEF Agency(ies): |  | GEF Agency Project ID: |  | 640059 |
| Other Executing Partner(s): | Rural Energy and Environment Agency, Department of Science, Technology and Education, Ministry of Agriculture and Rural Affairs | Submission Date: |  | 28 May 2019 |
| GEF Focal Area (s): | Biodiversity | Project Duration (Months) |  | 60 |
| Integrated Approach Pilot | IAP-Cities IAP-Commodities IAP-Food Security |  | Corporate Program: SGP |  |
| Name of Parent Program | N/A | Agency Fee ($) 258,940 |  |  |

## A. Focal Area  Strategy Framework and Other Program Strategies

| ### Focal Area Objectives/Programs | ### Focal Area Outcomes | ### Trust Fund | ### (in $) |  |
| --- | --- | --- | --- | --- |
|  |  |  | ### GEF Project Financing | ### Co-financing |
| BD-3 Program 7 | Increased genetic diversity of globally significant cultivated plants and domesticated animals that are sustainably used within production systems. |  | 2,725,688 | 20,234,320 |
| Total project costs |  |  | 2,725,688 | 20,234,320 |

## B. Project description summary

| ### Project Objective: To mainstream on-farm conservation and sustainable use of globally important local varieties of crops originated in China for food and agriculture, through a strengthened enabling environment, and the development and demonstration of long-term incentive mechanisms. |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| ### Project Components/ ### Programs | ### Financing Type | ### Project Outcomes | ### Project Outputs | ### Trust Fund | ### (in US$) |  |
|  |  |  |  |  | ### GEF Project Financing | ### Confirmed Co-financing |
| Component 1: Strengthening the enabling environment to promote mainstreaming of on-farm conservation and sustainable use of the genetic diversity of important indigenous local crops and varieties. |  | Outcome 1.1: In-situ conservation and sustainable use of genetic diversity of significant indigenous local crops and varieties mainstreamed into policies or plans at different levels, and also in three targeted provinces, to support the development of national strategies that protect agrobiodiversity | Output 1.1.1: Social, cultural and economic evaluation of local varieties (e.g. nutrition and food security, public health, environmental benefits among others) conducted to serve as the basis for policy and legislation development. Output 1.1.2: One national strategy or policy for conservation and sustainable use of the genetic diversity of important indigenous local crop and variety prepared and submitted to MARA; four provincial strategies/policies prepared for the targeted provinces respectively. Output 1.1.3: Recommendations developed for revision / reform of national legislations (i.e. eco-compensation legislation) that incorporates valuing the roles of the traditional farmers, including women and young people to support on-farm conservation and sustainable use of crop genetic diversity, promoting sustainable agrobiodiversity systems. Output 1.1.4: A national and four provincial inter-institutional cooperation mechanisms established to streamline cross-sectoral approaches to agro-biodiversity conservation. |  | 277,877 | 1,880,000 |
| Component 2: Capacity building to promote adaptive management and improved conservation and sustainable use of crop diversity for resilient agriculture and sustainable production. | TA | Outcome 2.1: Capacities strengthened to support long-term plans and up-scaling of incentive-based approaches for on-farm conservation and sustainable use of crop diversity for resilient agriculture and sustainable production. | Output 2.1.1: Development/ implementation of management mechanisms that carry out self-sustained planning, management and evaluation for on-farm conservation and use of local varieties by empowering and improving farmers’ capacities and promoting information sharing among farmers. Output 2.1.2: Stakeholders trained and priorities set (based on needs identified by the communities and coordination with research groups dedicated to agricultural development) in participatory training/education services for on-farm conservation and use of local crop varieties. enhance the knowledge and skills of farmers, agricultural researchers and extension agents in the field Output 2.1.3: Dissemination to the wider public through media, such as TV, radio, programs, internet, publications, etc. to improve public awareness of on-farm conservation and sustainable use of local varieties. |  | 992,752 | 4,680,000 |
| Component 3: Mainstreaming diversity of local varieties through biological, socio-cultural and economic evaluation and the development of market/non-market incentives and linkages in target sites. | TA | Outcome 3.1: Improved marketing of products made from local varieties, including through the use of both traditional knowledge and modern technologies, taking into account market /non-market incentives to increase local crop diversity production and availability. | Output 3.1.1: Evaluation of local varieties through traditional knowledge, socio-cultural assessment and economic issues. Output 3.1.2: Development of on-farm conservation approaches and technologies to ensure long term, demand-driven conservation of local varieties. Output 3.1.3: Business and marketing plans developed in pilot communities to maximize opportunities for product development and revenue creation based on strengthening market linkages among breeders, small-scale farmers and local and provincial markets to mainstream local crop diversity. |  | 970,127 | 10,344,320 |
| Component 4: Strengthened knowledge management. |  | Outcome 4.1: Information and knowledge of social, cultural, economic, research and marketing aspects related to crops and their local varieties will be collected, documented and published for providing basic support for further conservation and sustainable utilization. | Output 4.1.1: Traditional and new knowledge, generated through participatory research for on-farm conservation and sustainable use of local varieties, documented together with best practices/lessons learnt from pilot sites to applicability to other local crops and varieties in China. Output 4.1.2: Establishing information and communication platforms (web-based information platform and inter-sector working groups), dedicated to on-farm conservation. Output 4.1.3: Databases of species, varieties, traditional research and development practices for conservation and sustainable use of local varieties created. Output 4.1.4: Support provided for exchange of experiences and lessons between child projects, inter-institutions, national/ international organizations for effective scaling-up of project impacts. |  | 355,432 | 2,690,000 |
| Subtotal |  |  |  |  | 2,596,188 | 19,594,320 |
| Project Management Cost (PMC) |  |  |  |  | 129,500 | 640,000 |
| Total project costs |  |  |  |  | 2,725,688 | 20,234,320 |

## C. confirmed sources of Co-financing for the project by name and by type

Please include evidence for co-financing for the project with this form.

| Sources of Co-financing | Name of Co-financier | Type of Cofinancing | Amount (US$) |
| --- | --- | --- | --- |
| Recipient Government | Ministry of Agriculture and Rural Affairs | In-kind | 3,080,000 |
| Recipient Government | Agriculture Department of Hebei Province | In-kind | 3,465,000 |
| Recipient Government | The People's Government of Muling City, Heilongjiang Province | In-kind | 3,465,000 |
| Recipient Government | The People's Government of Kaiyuan County, Liaoning Province | In-kind | 4,969,320 |
| Recipient Government | The People's Government of Yuanjiang County, Yunnan Province | In-kind | 3,465,000 |
| Private sector | Youtehulian Zhangjiakou Agriculture Technology Co. Ltd, Hebei | In-kind | 270,000 |
| Private sector | Zhangjiakou NorthOat Food Development Co. Ltd, Hebei | In-kind | 115,000 |
| Private sector | Li-feng Yuan Farmers' Professional Cooperatives, Muling City, Heilongjiang | In-kind | 385,000 |
| Private sector | Liaoning Boning Soybean Planting Cooperatives | In-kind | 385,000 |
| Private sector | Yunnan Guyutian Agriculture Development Co. Ltd | In-kind | 385,000 |
| GEF Agency | Food and Agriculture Organization of the United Nations | In-kind | 250,000 |
| Total Co-financing |  |  | 20,234,320 |

## D. Trust Fund  Resources Requested by Agency(ies),  Country(ies), Focal Area and the Programming of Funds

| GEF Agency | Trust Fund | Country Name/Global | Focal Area | Programming of Funds | (in $) |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | GEF Project Financing (a) | Agency Fee a) (b)2 | Total (c)=a+b |
|  |  | China | Biodiversity | N/A | 2,725,688 | 258,940 | 2,984,628 |
| Total Grant Resources |  |  |  |  | 2,725,688 | 258,940 | 2,984,628 |

a ) Refer to the Fee Policy for GEF Partner Agencies

## E. Project’s Target Contributions to GEF-6 CORE INDICATORS

Provide the expected project targets as appropriate.

| GEF-6 Core Indicators | Expected Project Target |
| --- | --- |
| Core Indicator 4: Area of landscapes under improved practices | At least 36,000 ha of farmland under improved agrobiodiversity management practices. |
| Core Indicator 11: Number of direct beneficiaries disaggregated by gender as co-benefit of GEF investment | More than 6,600 beneficiaries, including 48% females, with improved agricultural livelihoods. |
| ## F. PROJECT TAXONOMY Level 1; Level 2; Level 3; Level 4. Infleuncing Models; Transform policy and regulatory environment. Strengthen institutional capacity and decision-making. Convene multi-stakeholder alliances. Demonstrate innovative approaches. Stakeholders; Private sector; Financial intermediaries and market facilitators. SMEs. Individuals/ Entrepreneurs. Beneficiaries. Local Communities. Civil society; Community-based organization. Type of engagement; Information dissemination. Partnership. Consultation. Participation. Communications; Awareness raising. Education. Behavior change. Capacity, knowledge and research; Enabling activities. Capacity development. Knowledge generation and sharing. Targeted research. Learning; Adaptive management. Innovation. Knowledge and learning; Knowledge management. Innovation. Capacity development. Learning. Stakeholder engagement plan. Gender Equality; Gender mainstreaming; Beneficiaries. Women groups. Sex-disaggregated indicators. Gender result areas; Participation and leadership. Access to benefits and services. Capacity development. Awareness-raising. Knowledge generation. Focal Area/ Theme; Biodiversity; Mainstreaming; Agriculture and agrobiodiversity. Species; Plant genetic resources. |

# PART II:  PROJECT JUSTIFICATION

## DESCRIBE ANY CHANGES IN ALIGNMENT WITH THE PROJECT DESIGN WITH THE ORIGINAL PIF

Some minor changes have occurred in the project design from the project concept note. These are summarized below with rationale:

| Project Aspect | Project Concept Note | GEF CEO ER | Rationale |
| --- | --- | --- | --- |
| Revision in number of target provinces | Three target provinces: Hebei for millet and oat; Liaoning for soybean; and Yunnan for rice. | Four target provinces: Heilongjiang has been proposed an additional province for soybean | Heilongjiang is a key province for the revitalization of China's soybean industry. Characterized by extreme cold, it has a different agro-climatic condition from that of Liaoning and presents the opportunity to conserve different traditional soybean varieties under different planting system. The soybean varieties in Heilongjiang have high potential for processed soybean products whereas the ones in Liaoning are primarily meant for consumption as fresh green soybean. |
| Budget revisions | Total GEF project financing projected at USD 2,725,688 C1: 369,000 C2: 739,000 C3: 1,105,000 C4: 385,688 PMC: 127,000 | Total GEF project financing remains USD 2,725,688. However, there are some changes in the budgets for the components as shown below: C1: 277,877 C2: 992,752 C3: 970,127 C4: 355,432 PMC: 129,500 | Budget reallocations in line with the project priorities that became clearer during project design. The most significant change has occurred in C2. This is primarily because of the need to invest more on capacity development as the capacity scorecards revealed that the baseline capacity at both national and provincial levels were extremely low (ranging between 7% to 31%). If capacity is not sufficiently developed, the sustainability of project results will be at stake. Other component deviations are marginal to moderate. PMC has also increased marginally but remains below 5% of the GEF financing. |
| Increase in co-financing | Total co-financing: USD 18,480,000 | Total co-financing: USD 20,234,320 | Addition of FAO co-financing of USD 250,000 towards project management cost, and increased co-financing commitment of USD 4,969,320 from the People’s Government of Kaiyuan County, Liaoning Province. |

Apart from the above changes, the project design has not deviated from the project concept note as described below:

### A.1. Project description

#### Global environmental problem, root causes and barriers to be addressed

The project seeks to mainstream in-situ conservation of agrobiodiversity across China and reduce key threats to globally significant genetic resources for food and agriculture. It is designed to remove key barriers of inadequate policy and institutional framework, deficient implementation capacity, limited knowledge and awareness, and lack of markets and incentives currently restricting the on-farm conservation and sustainable use of traditional genetic diversity. It targets four key crops, namely millet, oat, rice and soybean, that have originated in China contributing towards achievement of the long-term objective of strengthening conservation of China’s globally important agrobiodiversity.

The project will enhance existing policy and strategic frameworks at the national level and in the four target provinces, focusing on promoting incentivized mechanisms and the role of women and youth in agrobiodiversity conservation. Institutional mechanisms will also be strengthened at the central level and in the target provinces to ensure a coordinated and holistic approach to on-farm conservation of agrobiodiversity. Capacity of institutional staff with responsibilities for agricultural development planning, research and extension services, as well as farmers and farm cooperatives will be built through training, awareness-raising, exchange programs, and field guidelines and toolkits for participatory agricultural research and extension services. At least 300 institutional staff in government agencies at central, provincial, county and township levels with responsibilities for agricultural development are expected to be benefitted from various capacity development activities under the project. Product development and market access for traditional crop varieties will be enhanced through strengthening of value chains and development of business and marketing plans for farmers’ cooperatives/ farmers in the project demonstration sites. Knowledge management will be intrinsic to the project and it will be actively pursued through strengthening of databases, case studies on key concepts, approaches and practices employed by the project, information and knowledge-sharing within and with other child projects. A knowledge management strategy will be developed based on a knowledge, attitude and practice (KAP) survey carried out in the initial year of the project, and changes in KAP as a result of the project will be assessed towards the end of the project.

A key focus of the project is demonstration of innovative, community-based and incentivized approaches that support the achievement of long-term agrobiodiversity conservation and sustainable development outcomes. Participatory approaches that integrate sustainable management of traditional crop varieties and enhanced socio-economic benefits for local communities will be implemented in five project demonstration sites namely: Shuangyinzi village, Xuanhua county, for millet and Zhonghua village, Zhangbei county, for oat in Hebei province; Shandong village, Muling city, for soybean in Heilongjiang province; Sandaogou village, Kaiyuan county, also for soybean in Liaoning; and Yangjie village, Yuanjiang county, for rice in Yunnan province.  The selected traditional crop varieties include DaBaigu (for millet), Sanfensan (for oat), Suinong4 (for soybean in Heilongjiang), Kaiyu9, Kai8157 and Dabaimei (for soybean in Liaoning), and Mazha Gu and Hongehzi Gu (for rice in Yunnan).

Baseline scenario

Under baseline scenario, traditional crop diversity will continue to diminish as local farming systems increasingly focus on few high-yielding modern crop varieties. Current policy framework and institutional mechanisms, at national level as well as provincial level, are inadequate for on-farm conservation and sustainable use of traditional crop genetic diversity. Existing agrobiodiversity conservation policies and legislations do not clearly encompass aspects related to on-farm conservation of traditional crop varieties. The level of staff capacity, stakeholder awareness and knowledge for conservation of traditional crop diversity is extremely low as reflected by the capacity scorecards (see prodoc appendices 10a-10d). There are no incentives, either market or non-market, for farmers to engage in sustainable agrobiodiversity management and conservation of traditional crop varieties. Without market access and incentives, local communities are unlikely to continue with the cultivation of traditional crop varieties despite their better nutrional, health and environmental values, as they are generally low-yielding and labor-intensive. Low capacity of government staff will mean inadequate delivery of agricultural research and extension services to farmers for sustainable agrobiodiversity management and conservation of traditional crop varieties. These will consequently lead to deterioration of traditional agrobiodiversity systems and the surviving traditional varieties may disappear altogether. On the positive side, previous initiatives such as GIAHS/ NIAHS and farmer field schools have gained strength and recognition. These present opportunities to integrate lessons in the project implementation especially in terms of participatory agrobiodiversity management based on traditional systems and one that generates improved economic benefits and espouses community-based learning.

Without the incremental GEF contribution, the baseline will result in further loss to global environmental values. The Government will not be capacitated to promote on-farm conservation and sustainable use of traditional agrobiodiversity and communities will continue to undermine traditional genetic diversity of globally important crops that have originated in China. This will result in continued: (i) losses of globally valued agrobiodiversity in China; and (ii) loss of social, economic and environmental benefits that traditional crop varieties can offer local communities through incentivized approach and sustainable management practices.

#### Proposed alternative scenario

The overall development goal of the project is to strengthen sustainable livelihoods through improved management and utilization of crop genetic diversity. The project objective is to improve the on-farm conservation and sustainable use of globally important genetic diversity of crops originated in China. The proposed project is designed around the focal area of biodiversity conservation. It is designed to address the existing barriers to conservation of traditional agrobiodiversity through an integrated and holistic approach which fosters better linkages between improved agricultural livelihoods and on-farm conservation of traditional crop varieties through conducive policies and legislations, better institutional mechanisms, enhanced capacity of government staff as well as local communities, increased stakeholder awareness, improved market access and incentive mechanisms, and strengthened knowledge management.

The project component can be summarized as below:

Component 1: Strengthening the enabling environment to promote mainstreaming of on-farm conservation and sustainable use of the genetic diversity of important indigenous local crops and varieties.

The project will support the mainstreaming of conservation and sustainable use of local crop varieties indicated as a priority area in the National Biodiversity Strategies and Action Plans (NBSAP) for 2011-2030 submitted to the Secretariat of the Convention on Biological Diversity, as well as other national development plans such as the 13th Five-Year Plan (2016 -2020) which underlines the importance of environmental protection and the creation of China as an ‘ecological civilization’.

This component will lend support to the strengthening of conservation and sustainable utilization of local varieties into strategies/policies at national/provincial levels; to make recommendations for streamlining into the national legislation framework. The efforts under this component will directly benefit the activities under component 2 and 3. Beyond establishing conservation and sustainable utilization of local crop varieties as a policy-level priority, this component is also envisioned to create the necessary policy and legal conditions for premium market development for the activities under component 2 and 3.

In-depth analysis of existing policies and legislations relevant to agrobiodiversity conservation with emphasis on traditional crop varieties and incentive mechanisms for their in-situ conservation will be carried out to develop recommendations for formulation of suitable policies/ strategies at the national and provincial levels.  Socio-cultural and economic evaluations of traditional crop varieties and studies on appropriate market/ non-market incentive mechanisms will be carried out to inform the formulation of the national and provincial policies/ strategies. These evaluations and studies will also closely examine the role of women and youth in sustaining traditional agrobiodiversity systems and offer necessary policy recommendations for enhancing their roles.

This component will also focus on creating inter-institutional mechanisms for agrobiodiversity conservation at the national level and in the target provinces based on detailed studies of existing institutional mechanisms and gaps for coordinated and inter-sectoral approach. With vastly improved policy and institutional frameworks at the national level and in the target provinces, this component will be instrumental in creating an enabling environment for successful implementation of other project components and the sustainability of project results in the long term.

Component 2: Capacity building to promote adaptive management and improved conservation and sustainable use of crop diversity for resilient agriculture and sustainable production.

Component 2 is aimed at developing the capacity of government agencies at the national level and in the provinces, research institutions, local communities, and farmers. Training needs assessment of national institutions and various agencies in the provinces for participatory agricultural research and extension services will be carried out. Based on this assessment, a training module will be developed. Based on this module, training materials will be developed and training of trainers (ToT) will be conducted to create a core team of well-trained professionals with training skills to impart training on participatory agricultural research and extension services for the local agricultural staff in all the four target provinces. Farmers will be encouraged to put social value to their own roles in the society for empowerment by creating co-management mechanisms to carry out self-sustained planning, management and evaluation for the on-farm conservation and use of local varieties. Organization of inter-provincial exchange workshops will promote information sharing among farmers and agriculturists to learn from each other’s successful experiences. The outputs from component 2 are envisioned to provide a base for the activities in component 3.

Public awareness of the importance and benefits of traditional crop varieties and of sustainable methods and practices to improve the management and production of traditional crop varieties will be increased through a series of communication and information activities in partnership with media agencies. Overseas study tours will be organized by the project to secure wider exposure and knowledge from international institutions to supplement knowledge and skills in participatory training and extension acquired from in-country training workshops.

With implementation of component 2, it is expected that by the end of the project, at least 50% increase in awareness of the importance of crop genetic diversity amongst key stakeholders, compared to baseline established at year 1 of the project and no less than 15% of new households (men and women) involved in the on-farm conservation and sustainable use of local varieties will have increased significantly.

Component 3: Mainstreaming diversity of local varieties through biological, socio-cultural and economic evaluation and the development of market/non-market incentives and linkages in target sites.

This component will support farmers and/or farmers’ cooperatives and demonstrate the effectiveness of a market/non-market incentive mechanism to make agrobiodiversity conservation economically profitable for local communities. Such incentives will derive from providing special recognition to farmers who maintain local diversity (“custodian” or “heritage farmers”), improving market access and prices for products that follow good practices. When market mechanisms alone are not adequately effective, incentives through non-market such as “eco-compensation” and “eco-labelling” will enable complementarity. Involvement of farmers’ cooperatives and companies that use local crop diversity will be encouraged to participate in detailing the market incentive schemes. The market demand and future potential for products like local varieties and species that contribute to the conservation of local varieties is an important aspect of the proposed project. This component will benefit from improved policy and institutional frameworks created through Component 1 and capacity built for participatory agricultural research and extension services through Component 2.

This project will also support the combination of traditional and modern technologies, as well as conservation and sustainable technologies, comprehensively integrate the existing technologies adapting to the farmers’ needs by enhancing researchers’ ability to understand what processes underlie the generation and maintenance of local crop varieties. Farmer field schools (FFS) will be established and operated at the project demonstration sites to facilitate community-based learning and farmer-to-farmer transfer of knowledge on sustainable methods and practices for improved management and production of traditional crop varieties. Improved on-farm conservation practices developed through the FFS will be linked to strengthening of value chains and marketing of the products from traditional crop varieties. Value chain analysis and market studies will be conducted to help farmers/ farm cooperatives develop marketing and business plans to identify and secure markets and develop products in accordance with location-specific comparative advantages and market situation. Small grants will be disbursed to farmers/ farm cooperatives to be used as collaterals to secure loans to implement their business/ marketing plans. Partnerships between private companies and local farmers/ farm cooperatives will be fostered to improve product development and marketing. These activities will maximize farmers’ economic benefits from conservation, providing not only incentives to expand corresponding practices, but also sustainable financing to maintain, replicate and scale up dynamic conservation beyond the project itself. At the end of the project, pilot communities will have the necessary knowledge and skills and access to markets to derive substantial economic benefits from on-farm conservation of traditional crop varieties.

Component 4: Strengthened knowledge management.

Component 4 will seek to strengthen the linkages between the critical stakeholders, identifying, validating, documenting and promoting the knowledge base that underpin traditional agrobiodiversity ecosystems and the traditional practices and research that maintain local varieties. There is little recognition of the important role of traditional crops in sustainable agricultural development in China and little recognition of the importance of on-farm conservation of local varieties for long term food security, and thus for poverty alleviation and sustainable development.

This component will improve the accessibility of information and knowledge on agrobiodiversity including local crop varieties, effective approaches for on-farm conservation and sustainable use of local varieties and tools and guidelines, in order to support up-scaling of approaches and impacts across China. Multi-sectoral information sharing networks, databases, monitoring networks and web- based information platforms for conservation of local varieties will be developed. These will be institutionalized within MARA and within provincial level departments of agriculture in target provinces to enable the exchange of knowledge and information between child projects, the exchange of information with other initiatives outside the program, and will ensure that resources and experiences developed within child projects are captured, stored and shared, to support scaling up of program results. Independent evaluations and regular feedback from stakeholders will be used to ensure that the project undergoes adaptive management and can provide support to the real-time dynamic platform for decision making.

A knowledge, attitude and practice (KAP) survey will be conducted at the initial stage of the project, leading to the development of a knowledge management strategy in concert with other child projects under the C-SAP program. Also, an end-of-project KAP survey will be conducted in the final year of the project to assess actual changes realized through the project. The KAP surveys will be conducted and the knowledge management strategy will be developed by a qualified service provider/institute recruited through a competitive procurement process. Indicative targets for measuring changes to knowledge, attitudes and practices are presented in the project results framework; these will be reviewed and finalized as part of the baseline KAP survey.

#### Innovativeness

At the policy level, the project is designed to create conducive policies/ strategies that among other things will focus on fostering incentivize mechanisms and creating better economic opportunities for local communities, especially women and youth in the conservation and sustainable use of indigenous crop diversity. The project will develop and institute inter-institutional coordination mechanisms at the national as well as provincial levels to facilitate a collaborative and holistic approach, conduct community-based learning to infuse sustainable on-farm crop diversity management methods and practices in local agricultural systems, promote local community partnerships with private sector for better product development and marketing, and introduce incentive mechanisms to offset the higher production costs, e.g. due to labor-intensive practices and low yields, associated with the cultivation traditional crop varieties. In this respect, the project will not only address market-based incentives but also explore and demonstrate how non-market incentives, e.g. eco-compensation and eco-labelling, can be effectively employed in the on-farm conservation of traditional crop varieties.

Building on FAO’s experience in FFS in China and elsewhere, the project will develop and operationalize FFS customized to the local circumstances and needs in the project sites and create a hands-on community-based learning environment based on interactions between agricultural researchers, extension workers and farmers and between farmers themselves. It will also employ ToT approach to training, which will have a multiplier effect and is more sustainable.

- The project will maintain close linkages with other individual child projects of C-SAP to learn and share knowledge, ideas and experiences. It will take turn with other child projects to organize the program steering committee meeting, which will enable it to facilitate exchange of knowledge and information with other projects.

#### Potential for scaling up

- The potential scaling up of the proposed project approach will be promoted in various ways through project implementation. Pilot activities in the projected sites are expected to have high demonstration value through the FFS, providing opportunities to spread out to the other neighboring villages in the townships. The integration of economic incentives will likely enthuse neighboring communities to embark on similar activities and the proposed project will generate positive collaboration between communities and local-level government through participatory agricultural research and extension services. This increased collaboration will benefit the sustainability of the project results and subsequently promote the upscaling of similar interventions to other farming communities in China.

- Case studies to highlight specific concepts, approaches, practices and issues addressed by the project will be conducted, and lessons learned and best practices from the project activities will be collated, analysed, documented and disseminated through the information and communication platforms and knowledge events conducted under component 4. Partnerships between private sector and farming communities will be fostered, which will among other things help the project interventions to extend out to other villages where the concerned private agencies are active or will become active.

#### Sustainability

To sustain the project results over a long term, capacity will be developed within the government at the central and provincial levels. Systemic capacity will be built through development of favorable policies and strategies, institutional capacity will be strengthened through better inter-institutional coordination mechanisms, development of technical guidelines and toolkits, and knowledge management including improved databases and communication platforms, and individual capacity will be developed through trainings to improve knowledge and skills of government staff as well farmers and other stakeholders. Capacity development at systemic, institutional and individual levels will complement each other and create a larger capacity environment for sustainability of project results.

The approach of the project will be to engage with a wide range of stakeholders so that there is broad-based ownership of the project interventions. Inter-institutional coordination mechanisms developed and instituted through the project are expected to contribute to a holistic and inter-disciplinary approach to the delivery and management of project interventions, which in turn will enhance the sustainability of the project. Participatory approaches and practices such as through farmer field schools will create a community-based learning environment which is linked to the lives and livelihoods of the local communities in a very practical manner. These are expected to stimulate the interest and engagement of the local communities and built their capacity for the long-term management of traditional crop varieties. The ToT approach for participatory research and extension services for on-farm conservation of traditional agrobiodiversity will create in-house training capacity, which will be valuable beyond the conclusion of the project. By the end of the project, at least 300 institutional staff in relevant government agencies at the national, provincial, county and township levels will have received training in one or more subjects addressed by the project. At the same time, widespread public awareness will be built through a series of communication and public awareness-building activities. An increased public and professional understanding will contribute to improved public and professional support for the conservation of traditional crop varieties.

With respect to the financial dimension of sustainability, the project will help facilitate improved and broader uptake of incentive mechanisms, both market-based and non-market-based. Partnerships will be built with the private sector and corporate social responsibility mechanisms will be pursued to promote domestic financing over the long-term. The project will help the communities/ farmers cooperatives in project demonstration sites to come up with business and marketing plans that generates economic benefits, which can be ploughed back to financially sustain the on-farm conservation of traditional crop varieties. Policy-level advocacy will be pursued to increase government budget allocation for the conservation of indigenous agrobiodiversity (reflected as an indicator under Outcome 1.1, see Appendix I). The project will avoid expensive technology and focus on low-cost technology which can be sustained at the community level over a long term.

### A.2. Child project?

The proposed is one of the five child projects proposed under the PRC-GEF Partnership Program for Sustainable Agricultural Development (C-SAP).

### A.3.  Stakeholders

Will project design include the participation of relevant stakeholders from civil society organisations (yes  /no) and indigenous peoples (yes  /no)?

During the course of the project preparatory grant (PPG) phase, widespread consultations in the central government agencies, provincial and local governments, private sector, farmers cooperatives, civil society and local communities were carried out to elicit information and insights required for project design as well as to raise awareness of the stakeholders about the project, its objectives and expected benefits as well as their anticipated roles in the project. Stakeholder consultations took place through the following key activities/ events:

- PPG Inception Workshop, 21 May 2018 at Beijing.  There were altogether 37 participants at the workshop, representing MARA, FAO, provincial government agencies for rural energy and environment, academia and research, and media. The workshop introduced the project concept and components, the process and timeline to conduct and complete the project design (PPG work), and the activities and tasks for the PPG team.

- Preliminary field missions for local stakeholder consultations and appraisal of potential project sites. The PPG team undertook two preliminary field missions: the first to Yunnan province from 22-24 May 2018; and the second to Hebei, Heilongjiang and Liaoning provinces from 1-9 July 2018. During the preliminary field missions, the PPG team visited potential project sites and consulted local stakeholders to appraise local conditions and issues related to the conservation of traditional crop varieties and confirm the project sites. During this field mission, stakeholder consultations involved 117 people in the provincial and local government agencies, local communities, academia and research agencies, farm cooperatives, women federations, and local agri-businesses. Women constituted more than 21 percent of the people consulted during the preliminary field missions.

- Baseline assessments for the project design were carried out by the local technical experts to collect detailed socio-economic, technical, policy and institutional information related to the conservation of target crops in the selected project sites. These baseline assessments altogether involved consultations with 137 people in local government agencies, academia and research, local communities, farm cooperatives, women federations, and local agri-businesses. More than 23 percent of the people consulted during the baseline assessments constituted women.

- Project Design Review Workshop, 7 November 2018 at Beijing. A total of 46 people representing central government agencies, provincial government agencies, research and academia, international conservation organizations, private sector, media, and FAO participated in the workshop to review the key elements of the project design including the overall project logic and strategy, results matrix, work plan, implementation arrangements, co-financing, and baseline assessments.

During the project implementation, the involvement of a wide range of stakeholders is envisaged. The following table identifies key project stakeholders and their roles in the project implementation:

Table: Stakeholder Engagement Table

| Name of the Stakeholder | Stakeholder Type | Role in the Project | Project Impact on the Stakeholder |
| --- | --- | --- | --- |
| Ministry of Agriculture and Rural Affairs | Government ministry | Overall supervision and management of the project; Guidance and backstopping to provincial agriculture departments; Communication and coordination with other central government agencies where necessary for project implementation; Coordination with FAO. | Policy and management capacity of MARA for on-farm conservation of traditional crop varieties will be built. |
| Chinese Academy of Agriculture Sciences | National scientific research institute | Research on traditional crop varieties; Technology development and technical backstopping; Training of farmers and agriculture extension agents. | Research work and training capacity of CAAS in the area of on-farm conservation of traditional crop varieties will be strengthened. |
| Local Women Federations | Community-based organization | Facilitation of women’s participation in project activities and ensuring that they address women’s specific needs; Creation of awareness and development of skills for new technology among women farmers. | The role and capacity of women federations in on-farm conservation of traditional crop varieties will be strengthened, enabling gender mainstreaming in project activities |
| Food and Agriculture Organization of the United Nations | UN organization (GEF Agency) | Facilitation of delivery of GEF resources for the project; Quality assurance as per GEF project requirements/ standards including progress reporting; Facilitation of knowledge-exchange and communication; Guidance and technical backstopping. | FAO’s capacity and experience for managing GEF project will be strengthened. |
| Farming communities | Local people | Implementation of planned activities on their farms; Knowledge-sharing; Self-mobilization for project activities including sustainable production, value addition and marketing; Participation in training and agricultural activities. | Improved livelihoods and incomes, better knowledge and skills, access to improved markets. |
| Ministry of Finance | Government ministry | GEF focal point; guidance and oversight | Improved understanding of financial resources planning and management for agrobiodiversity conservation. |
| Ministry of Ecology and Environment | Government ministry | Responsible for biodiversity conservation in national level; coordinate with project on sustainable use and conservation of GRFA; member of the inter-sectoral coordination committee; member of PSC. | Within MEE there is a need for raising the awareness of other departments and their staff of particularly the importance of on-farm conservation of traditional crop varieties to China's biodiversity. In addition, more general awareness on on-farm conservation of traditional crop varieties needs to be raised, and trainings related to the project developed/revised regulations and guidelines will also be needed. |
| Ministry of Natural Resources | Government ministry | Members of the project steering committee, responsible for the planning, management, protection and effective use of natural resources such as land and resources. | Within MNR there is a need for raising the awareness of other departments and their staff of particularly the importance of on-farm conservation of traditional crop varieties to China's biodiversity. In addition, more general awareness on on-farm conservation of traditional crop varieties needs to be raised, and trainings related to the project developed/revised regulations and guidelines will also be needed. |
| National Forestry and Grassland Administration | Government ministry | Monitoring and protection of grassland biodiversity | Within NFGA there is a need for raising the awareness of other departments and their staff of particularly the importance of on-farm conservation of traditional crop varieties to China's biodiversity. In addition, more general awareness on on-farm conservation of traditional crop varieties needs to be raised, and trainings related to the project developed/revised regulations and guidelines will also be needed. |
| All-China Women’s Federation (ACWF) | Government ministry | As a member of the project steering committee, it guides project design and implementation, guarantees equal opportunities for women participation | Although not specifically target towards ACWF, ACWF representatives will be invited to a subset of the project trainings as part of the project overall awareness raising initiatives but also to enable ACWF to provide feedback on the trainings with the aim to improve the gender aspect of said trainings. |
| The State Council Leading Group for Poverty Alleviation and Development | Government ministry | As a member of the project steering committee, it guides the design and implementation of the project, and provides guidance and suggestions for complementing and integrating the project activities and poverty alleviation work. | The role and capacity of the State Council Leading Group for Poverty Alleviation and Development in on-farm conservation of traditional crop varieties will be strengthened. |
| Rural Energy and Environment Agency, MARA | Government ministry | Responsible for the day-to-day management and fund management of the project, and provide technical support and coordination for the project team. | The staff of REEA and in particular staff in the Project's Management Office will be participating in as many of the project developed trainings as possible to increase the PMOs knowledge but also to provide feedback on the developed training materials. |
| Hebei AD | Local department | As the focal point in Hebei province, Hebei Provincial Department of Agriculture will be responsible for supervision and guidance of project implementation in Hebei, assisting the government at the county level in project coordination and resource integration. Promote the establishment of a coordination mechanism for the GRFA management department of the province. | The Hebei Provincial Department of Agriculture will be the target for a range of project developed trainings. Relevant staff will also be receive training in the more practical on the ground trainings of on-farm conservation of traditional crop varieties |
| Yunnan AD | Local department | As the focal point in Yunnan province, Yunnan Provincial Department of Agriculture will be responsible for supervision and guidance of project implementation in Yunnan, assisting the government at the county level in project coordination and resource integration. Promote the establishment of a coordination mechanism for the GRFA management department of the province | The Yunnan Provincial Department of Agriculture will be the target for a range of project developed trainings. Relevant staff will also be receive training in the more practical on the ground trainings of on-farm conservation of traditional crop varieties |
| Heilongjiang AD | Local department | As the focal point in Heilongjiang province, Heilongjiang Provincial Department of Agriculture will be responsible for supervision and guidance of project implementation in Heilongjiang, assisting the government at the county level in project coordination and resource integration. Promote the establishment of a coordination mechanism for the GRFA management department of the province. | The Heilongjiang Provincial Department of Agriculture will be the target for a range of project developed trainings. Relevant staff will also be receive training in the more practical on the ground trainings of on-farm conservation of traditional crop varieties |
| Liaoning AD | Local department | As the focal point in Liaoning province, Liaoning Provincial Department of Agriculture will be responsible for supervision and guidance of project implementation in Liaoning, assisting the government at the county level in project coordination and resource integration. Promote the establishment of a coordination mechanism for the GRFA management department of the province. | The Liaoning Provincial Department of Agriculture will be the target for a range of project developed trainings. Relevant staff will also receive training in the more practical on the ground trainings of on-farm conservation of traditional crop varieties |
| China Agricultural University | National scientific research institute | As one of the important technical support units of the project, responsible for provide technical support on GRFA in the province; assist government departments on policy research, technical promotion and training of grassroots agricultural technicians, preparation of publicity information materials. | Research work and training capacity of CAU in the area of on-farm conservation of traditional crop varieties will be strengthened. |
| China Society of Agro-Ecological Environment Protection | NGO | Specialized association for the protection of agricultural biodiversity, in conjunction with the project to carry out relevant training and publicity activities | The role and capacity of CSAEEP in on-farm conservation of traditional crop varieties will be strengthened. |
| Crops Germplasm Resources Committee | National scientific research institute | Responsible for the management of national germplasm and the development of national germplasm strategies and policies | The role and capacity of CGRC in on-farm conservation of traditional crop varieties will be strengthened. |

### A.4. Gender equality and women's empowerment

Are gender equality and women's empowerment taken into account (yes  /no)?

The project will equally benefit men and women. There are more than 6,600 people living in the project demonstration sites; 48% of them are females. Women in rural communities throughout China play an important role in the management of local agricultural systems, including cultivation and harvesting, collection and storage of seeds, keeping home gardens, gathering of ‘wild crops’ alongside a range of other aspects of agrobiodiversity conservation and sustainable use. Although in the project demonstration sites the male population is slightly higher, in many communities in China women farmers outnumber male farmers as men have the tendency to migrate to urban areas for jobs in cities, factories and construction projects. Even though women in many communities have in effect the primary role of managing households and farms, men generally retain the decision-making role. It is, therefore, important to recognize distinct gender roles in agrobiodiversity management, considering the distinct roles and responsibilities, interests, and needs between men and women.

The project will seek to develop conducive policies/ strategies for traditional agrobiodiversity management at national and provincial levels. These will among other things examine and integrate the role and opportunities for women and youth in the management of local agrobiodiversity systems and improvement of local agricultural livelihoods.

The All China Women’s Federation (ACWF) is a women's rights organization established in China in 1949. The ACWF is responsible for promoting government policies on women, and protecting women’s rights within the government. Its institutional presence runs from the national level to provincial, county, township and all the way down to village levels. The local women’s federations engage in grassroots community development including agriculture. The national and provincial inter-institutional coordination mechanisms that are to be instituted for agrobiodiversity conservation at the national and provincial levels will have representation from ACWF at their respective levels. This will help ensure that women’s interests and needs are recognized and incorporated in the planning and implementation of agrobiodiversity conservation programs and activities. In the project demonstration sites, the project will maintain close contact with representatives of the ACWF at the local level to mobilize women’s participation and integrate women’s issues and needs in the planned field activities.

### A.5 Risks

The proposed project has been screened and categorized as low risk in accordance with FAO´s Environmental and Social Risk Classification system. While the project itself will bear low environmental and social risks, a number of risks external to the project but with bearing on realization of the project objectives were identified. These are outlined along with mitigation measures in the table below:

| Risks | Risk rating | Mitigation measures |
| --- | --- | --- |
| Policy risks: The project involves rice, oat, millet, and soybean. Compared to the improved varieties of staple crops, the government attaches less importance to the traditional local varieties. At present the country has witnessed bumper harvest for ten consecutive years. As such, it is easy to gain government support to carry out conservation and sustainable use of traditional crop varieties, and relevant policy recommendations are also likely to be formulated and implemented. However, if the grain yield decreases, the government may not want to invest in conservation of traditional crop varieties but increase its focus on expanding the planting area of the main grain crops and promoting new high-yielding varieties for increased grain production because ensuring food security is a major priority for the Chinese government. In such circumstance, government may deviate policy support, adversely impacting the efforts to conserve traditional crop varieties. | Low | The operational partner and main government counterpart for the project is the Ministry of Agriculture and Rural Affairs. MARA is the country's main government agency for the development of agricultural policy. Prior to the formulation of any policy, research must be carried out in the agricultural systems, thus project officials including the National Project Director, are the first ones to obtain information related to the policy development. The project can develop response plans to mitigate the policy risk before the new policy is issued. In addition, the main distribution areas of the traditional crop varieties are generally not suitable for the cultivation of the improved varieties of staple crops. As a result, even if China developed policies to encourage the cultivation of the improved varieties, the impact on the project will be very limited. Furthermore, the project will pilot field interventions on small-scale farms in a few sites, which are unlikely to be intervened for large-scale production. |
| Natural risks: because the targeted local crop varieties are mainly distributed in the local and special ecosystems, which are prone to natural disasters such as drought, there are risks of natural disasters during project implementation, resulting in loss of crop production. In such an event, local communities may misconceive the impact as one due to project design, discouraging the active participation of all stakeholders of the project. | Low | During the project implementation, new commercial varieties will be selected as reference. In case of natural disasters, the advantage of the local variety will be proved by the performance of the new variety and the selected local variety, thus to eliminate the doubt stakeholders, so they will continue to implement the project and achieve the expected objectives. |
| Market risk: One important aspect of this project is to reflect the market value of the genetic diversity of local varieties through markets, providing the farmers with relatively large benefit while at the same time protecting the genetic diversity. However, since China is still in the primary stage of socialist market economy, If the market is fluctuating or even falling back under the impacts of the external environment, it may affect the market outlook for the local crop varieties. | Moderate | The commercialization of the genetic diversity of local varieties is only one way for sustainable utilization; the project will enable farmers to benefits from the conservation and utilization of agricultural diversity. Market and business plans will be developed by the project to improve economic benefits and enhance market resilience of the traditional crop varieties. |
| Co-financing risk: Since the Chinese economy is in the stage of slowing down of the growth rate, whether the committed co-finance can be in full or in time is subject to the influences of many factors including China's economic development. Due to the high proportion of project co-finance, the governments would be in difficulty if the economy were to decline during project implementation. | Low | Co-financing has been be guaranteed through letters of commitment by MARA, provincial/ local governments, private companies and FAO. The co-financing commitments will be monitored and their status assessed during mid-term review and terminal evaluations. In addition, with the adjustment of the agricultural industry policy by the Chinese government, more and more private investment will be involved in the project, so as to ensure that the project has adequate funding sources. |
| Climate change risks: Climate change is increasing impacting many spheres of development including agriculture. The target project provinces are located in different geoclimatic conditions of China, thereby increasing the likelihood of risks from extreme weather events. | Low | The project will focus on sustainable agricultural methods and practices, which will include increasing resilience to climate change. In addition, close communication will be maintained with meteorological stations in the provinces to alert farmer and mitigate any major impacts due to extreme weather. |

### A.6. Institutional arrangements and coordination

Operational Partner

Ministry of Agriculture and Rural Affairs will be the principal government agency for project implementation. MARA will have the overall supervisory and technical responsibility for project implementation, with FAO providing technical oversight and quality assurance as the GEF Agency for the project. Within MARA, the national project management office (NPMO) will be located at the Department of Science, Technology and Education. The project will be implemented in accordance with the FAO’s Operational Partners Implementation modality (OPIM).

At the provincial level, the project will receive project management and implementation support from the provincial departments of agriculture and rural affairs in Hebei, Heilongjiang, Liaoning and Yunnan provinces where the project sites are located. The implementation of the activities in the field will be the responsibility of the township agricultural bureaus with backstopping and monitoring from the county and provincial agricultural departments. A project focal person will be appointed in each province and county where the project sites are located.

The apex body for project management oversight and guidance will be the Project Steering Committee (PSC). In addition, a Technical Advisory and Coordination Committee (TACC) will function as an intermediate multi-disciplinary group to provide inter-disciplinary technical guidance and coordination to the project in keeping with the holistic and integrated approach that it seeks to pursue in project implementation.

Project Steering Committee

A PSC will be established to provide high-level oversight and management guidance to the project. The PSC will be chaired by the Director General, Rural Energy and Environment Agency, MARA, and will have members from the Ministry of Finance, MARA, Ministry of Ecology and Environment, Ministry of Natural Resources, the provincial DARAs in Hebei, Heilongjiang, Liaoning and Yunnan, and FAO. The National Project Manager will serve as the secretary to the PSC.

The PSC will meet at least once a year to oversee and steer project implementation through provision of management decisions and guidance in keeping with the policies and agreed standards of the Government of PRC, GEF and FAO and to ensure that the project is implemented, outputs are delivered and resources are mobilized and used as per project design. The terms of reference of the PSC is provided in Appendix VI of the project document.

National Project Management Office

The Ministry of Agriculture and Rural Affairs (MARA) will be the principal government agency for project implementation. MARA will have the overall executing and technical responsibility for project execution, with FAO providing technical oversight and quality assurance as the GEF Agency for the project. Established in 1949, MARA was restructured in 2018. It is made up of 24 different departments and bureaus. MARA will coordinate all efforts to implement the project, aligning with other initiatives and assuring timely implementation of all project activities as planned in concert with other project partners. Within MARA, the national project management office (NPMO) will be located at the Department of Science, Technology and Education, MARA.

The NPMO will be responsible for day-to-day project management, including planning, monitoring and evaluation, and coordination with the various agencies at the central and provincial levels for implementation of the activities planned for the delivery of project results in a timely and effective manner and as per standards set for FAO/GEF projects. Under the overall supervision and guidance of the National Project Director, the NPMO will be run by a National Project Manager on a day-to-day basis with the support of a Project/ Finance Assistant, and a Knowledge Management/ Monitoring & Evaluation Officer. The PMO will also engage a part-time Chief Technical Advisor for technical guidance and backstopping to the project activities from time to time.The ToRs for the various positions in the NPMO are provided in Appendix VI of the project document).

Provincial-level Project Management

Project level project management and implementation support will be delivered by provincial departments of agriculture and rural affairs in Hebei, Heilongjiang, Liaoning and Yunnan provinces. County level project coordination committees will be established in the counties where the project demonstration sites are located to guide and support the implementation of the project activities in the field. Each province and county covered by the project will appoint a focal person for the project. At the project demonstration sites, the project will mobilize and facilitate community participation in the project activities in close consultation with local government authorities and to ensure that field activities are being implemented as planned. Women federations at local level will be engaged to facilitate the participation of women farmers and to ensure that project activities are also responsive to the interests and needs of local women.

Figure 3: Project Organogram

Technical Guidance and Assistance

A Technical Advisory and Coordination Committee (TACC) will function as an intermediate group to provide inter-disciplinary technical guidance and coordination to the project to ensure that the project interventions are technically sound and there is coordination among the relevant technical sectors/ agencies for a holistic approach to project implementation. The TACC will meet at least once a year before the PSC meetings so that all key technical issues relevant to project implementation are deliberated in advance and are ready for presentation at the PSC meetings.

The ToR for the TACC is provided in Appendix VI of the project document.

Short-term consultancies will be procured through competitive bidding processes for technical assistance required for project implementation. The types of expertise envisaged on short-term assignments include but are not limited to the following:

- Agrobiodiversity policy/ strategy development;

- Technical evaluation of traditional crop varieties;

- Farmer field school design and guidance;

- Value chain analysis and business/ marketing plan development.

For mid-term review and terminal evaluation of the project, independent evaluators will be recruited directly by FAO using its internal procurement system.For mid-term review and terminal evaluation of the project, independent evaluators will be recruited directly by FAO using its internal procurement system.

GEF Agency

Food and Agriculture Organization of the United Nations (FAO) will be the GEF Agency for the project. FAO will provide technical guidance and ensure quality assurance during the project execution. Administration of the GEF grant will be in compliance with the rules and procedures of FAO, and in accordance with the agreement between FAO and the GEF Trustee.

As the GEF agency for the project, FAO will:

- manage and disburse funds from GEF in accordance with the rules and procedures of FAO;

- oversee Project implementation in accordance with the Project Document, work plans, budgets, Agreements with co-financiers and the rules and procedures of FAO;

- provide technical support to ensure that appropriate technical quality is applied to all activities concerning wetland biodiversity conservation and restoration and capacity development in wetland protected areas management;

- review expenditure and financial statements, monitor financial management of the Project and carry out spot checks and audits, contracting the services of an audit firm, as necessary;

- supervise and monitor contracting and procurement processes;

- carry out at least one supervision mission per year;

- ensure independent mid-term and final evaluations are conducted; and

- report to the GEF Secretariat and Evaluation Office, through the annual Project Implementation Review on Project progress, and provide Financial Reports to the GEF Trustee.

### A.7 Benefits

#### Socio-economic development

Sustainable management of local agrobiodiversity achieved through the combined impacts of all project components will contribute to improved agricultural livelihoods of the local communities. By the end of the project, it seeks to improve  incomes of local farmers by at least 15% of the baseline whilst improving the status of local crop diversity. This will be achieved through creation of better skills among farmers for improved on-farm conservation as well as enhancement of commodities and their marketing. More than 6,600 local people, of which 48% will be females and 20% youth, will directly benefit from the project activities. Apart from the direct beneficiaries in the project sites, the larger local population in the neighboring villages are also expected to benefit from improved capacity of agricultural researchers and extension agents who will be trained in participatory research and extension services and visibility of improved on-farm conservation methods and practices in the project sites.

By creating an enabling policy environment and enhanced institutional capacity at national as well as the provincial levels, the project is expected to open up huge opportunities for both agricultural development workers as well as farmers to embark on similar initiatives whick seek to improve local livelihoods through sustainable management of local agrobiodiversity systems. Pilot local communities will be equipped with business and marketing plans to guide and aid them in developing high-value commodities, accessing profitable markets and forging business partnerships with the private sector. Local agrobiodiversity management systems will be incentivized to offset the additional costs that the farmers would incur in the conservation and production of local crop varieties, such as those resulting from low yields and high labour inputs.

With improvement in agricultural livelihoods, and combined with relevant government’s initiatives, the project is expected to slow down the ongoing rural-urban migration especially among the youth and contribute to the revitalization of youth’s role and engagement in rural economic advancement.

#### Environmental sustainability and benefits

In terms of environmental sustainability, the project will primarily pursue and promote environmentally sound organic methods and practices for the on-farm conservation of traditional crop varieties. In fact, the selected traditional crop varieties for project interventions are those that are far more suitable for cultivation in organic conditions than the modern varieties and have high potential to be developed and marketed as niche organic crops and products. It will promote and demonstrate an integrated and participatory approach towards agrobiodiversity conservation which will facilitate more effective protection of biodiversity and ecosystem services, and increase the resilience of local communities to the potential impacts of climate change. As a result of the project, at least 36,000 ha of farmland will be brought under improved agrobiodiversity management. Thus, improving local environment conditions and agro-ecosystems.

### A.8 Knowledge management

Knowledge management is an intrinsic part of the project. Component 4 of the project is entirely dedicated to strengthening knowledge management. Through this component, the project will ensure that information and knowledge accumulated and produced within the project will be documented and made available for wider communication and dissemination of project lessons and experiences to support the replication and scaling-up of project results. It will strengthen existing databases on agrobiodiversity with focus on the target traditional crop varieties at the national and provincial levels and enhancing their utility and user base, including linkages to global agrobiodiversity database such as the ones maintained by FAO. It will also improve information and communication platforms, facilitate knowledge-sharing between the C-SAP child projects, develop case studies to highlight important concepts, approaches, practices and issues addressed by the project, and review, document and disseminate lessons learnt and best practices.

At the inception of the project, a KAP survey will be designed and carried out to assess the level of knowledge, attitudes and practices among stakeholders. A knowledge management strategy will be developed based on the results of this KAP survey and taking into account knowledge management in the other project components. Advocacy on the project socio-economic benefits and global environmental benefits will be a key part of this strategy. In the final year of the project, another KAP survey will be conducted to assess change in knowledge, attitudes and practices among the stakeholders as a result of the project.

Furthermore, policy and institutional reforms and on-farm conservation demonstrations will be developed based on the knowledge emanating from various studies, evaluations and assessments conducted through the project, including through consultations with various stakeholders and taking into account the experiences such as those related to farmer field schools and GIAHS/NIAHS which employ community-based approaches in development and maintenance of sustainable agricultural systems.

The proposed project will build on the knowledge and experience accrued through these key baseline initiatives:

# National in-situ conservation programme: In the 1950s, approximately 240,000 accessions of local varieties have been preserved through a nationwide investigation and collection of crop germplasm resources that led to a selection of a group of superior local varieties for large area planting.  As the economy grew rapidly, an increase and demand for large scale farming of improved varieties resulted in a sharp decline of local varieties. In responding to the decreasing indigenous local varieties, the Government of China succeeded in collecting over 400,000 crop genetic resources, mainly through ex-situ conservation. Acknowledging that in-situ conservation also plays a crucial role in conserving the genetic resources; MARA invests about $3.5 billion each year on agro-biodiversity conservation, of which about $15 million is used for crop genetic resources conservation. MOA has also launched an in-situ conservation programme in 2001, mainly targeting crop wild relatives and established 189 conservation sites for 52 plant species in 26 provinces.

# Conservation projects in China: Since the ratification of the Convention on Biological Diversity (CBD), some international organizations and developed countries carried out lots of programs and projects on in-situ conservation for genetic resources of crops and obtained valuable experiences. To apply those international experiences and best practices for the conservation of genetic resources in China, the government cooperated with institutions such as UNDP, EU, GEF and GIZ to carry out conservation projects in China. For example, sponsored by the GEF, MARA and UNDP implemented the project, “Conservation and Sustainable Utilization of Wild Relatives of Crops”(CWRC) from 2006 to 2013, which was demonstrated in 8 provinces focusing on wild rice, wild soybeans and wild relatives of wheat and extended to 15 provinces covering 39 wild plant species. The project has introduced the advanced international concepts and technologies of in-situ conservation including establishment of market based incentive mechanisms. Furthermore, MARA implemented another cooperation project with UNDP and GIZ (Germany) titled “Sustainable Management of Agro-biodiversity in the Mountain Area of Southern China” (MAMSC) from 2005 to 2011.It introduced innovative strategies and methods in the model villages for agro-biodiversity in Wuzhi mountain area in Hainan province and Wuling mountain area in Hunan province to promote farming methods that are friendly to agricultural biodiversity. The project has made achievements in many aspects after its implementation with favorable results, serving as a wakeup call in raising the awareness of people about agriculture biodiversity by calling attention to the rich agricultural biodiversity in mountain areas.

# GIAHS/ NIAHS: In coordination with MARA, FAO has introduced the Globally Important Agricultural Heritage Systems (GIAHS) program in China. The GIAHS seeks to integrate the protection of traditional production approaches and genetic resources with local economic development and improvement in community livelihoods. China became one of the earliest responders to the GIAHS initiative with the designation of Qingtian Rice-Fish Culture in 2005. It is also one of the best practitioners and one of the most active promoters of the conservation of agricultural heritage systems. Over the past ten years, it has made tremendous achievements in the identiﬁcation, conservation and management of agricultural heritage systems. It is the ﬁrst country that identiﬁed and conserved agricultural heritage systems at the national level and currently has the largest number of Nationally Important Agricultural Heritage Systems (NIAHS) sites as well as the largest number of GIAHS sites in the world. Among the 91 NIAHS sites, 18 are located within the provinces targeted by this project. These include five in Hebei, two in Heilongjiang, three in Liaoning, and eight in Yunnan. Among the 15 GIAHS sites in China, one is located in Hebei and two are located in Yunnan

# Conservation projects in target provinces: At the provincial level, the government also implements projects on conservation of crop genetic resources. Among the selected provinces (Yunnan, Hebei, Liaoning), Yunnan Province has the most projects on conservation, as it has the richest biodiversity in China. It funds about $60 million every year for biodiversity conservation, one third of which (about 20 million) are used on agro-biodiversity conservation. For example, in 1960s, 1980s and 2000s, it has collected their crop and livestock genetic resources and conserving them ex-situ. The province also carried out activities on genetic resource conservation by implementing national and international projects. The Province also supported Yunnan Agricultural University to successfully apply for the National Basic Research Program “Principles and Methods of Pest and Disease Control and Germplasm Conservation Using Agricultural Biodiversity” (PMCCAB) in 2006, which aimed to achieve the goal of the conservation of agro-biodiversity and control of the pest and disease to lay a foundation for the harmonious development of food production and agricultural biodiversity conservation. All targeted provinces have also implemented national projects under MARA including agro-biodiversity conservation and control of invasive alien species.

## B. Description of the consistency of the project with:

### B.1 Consistency with national priorities

The proposed project is consistent with the China’s National Biodiversity Strategy and Action Plan 2011-2030 (NBSAP). The NBSAP 2011-2030 identifies ten priority areas. This project will specifically contribute to five of the identified priority areas, namely: priority area 1 - improve the policy and legal system of biodiversity conservation and sustainable use; priority area 4 - strengthen in-situ biodiversity conservation; priority area 6 - to promote rational use and benefit sharing of biological genetic resources and associated traditional knowledge; priority area 9 - strengthen scientific research and human resources development in the field of biodiversity; and priority area 10 - establish public participatory mechanisms and partnerships for biodiversity conservation.

The project is also in line with China’s National Plan on Implementation of the 2030 Agenda for Sustainable Development. It will specifically contribute to the implementation of the National Plan for Sustainable Agricultural Development (2015-2030), which among other things seeks to achieve notable progress in sustainable agricultural development and establish a new model of sustainable agricultural development featuring adequate supplies, high resource efficiency, fertile farmlands, stable ecosystem, prosperous rural households, and pastoral beauty. This national action plan correspond to SDG 2, Target 2.4 - by 2030, ensure sustainable food production systems and implement resilient agricultural practices that increase productivity and production, help maintain ecosystems, strengthen capacity for adaptation to climate change, extreme weather, drought, flooding and other disasters and progressively improve land and soil quality.

## C.  Describe the budgeted m&e plan:

The project results as outlined in the project results framework will be monitored annually and evaluated periodically during project implementation to ensure the project effectively achieves these results.  Supported by Component Four:  Strengthened Knowledge Management, the project monitoring and evaluation plan will also facilitate learning and ensure knowledge is shared and widely disseminated to support the scaling up and replication of project results. The project’s M&E plan is presented in the table below:

| M&E Activity | Responsible Parties | Time-frame | GEF Budget (USD) |
| --- | --- | --- | --- |
| Inception Workshop | National Project Management Office | Within two months of project document signature | 20,000 |
| Project Inception Report | National Project Manager | Within two weeks of inception workshop | None |
| Annual financial audits | FAO China Representation Office/ NPMO | Annually | 30,000 (6,000 per year) |
| Project Progress Reports | National Project Manager and Knowledge Management/ M&E officer | Annually | None |
| Project Implementation Review report (PIR) | National Project Manager | Annually in July | None |
| Co-financing Reports | FAO China Representation Office | Annually | Co-financing |
| Mid-term Review | FAO Office of Evaluation | In the 3rd quarter of the 3rd year of the project | 40,000 |
| Final Evaluation | FAO Office of Evaluation | At least three months before operational closure | 40,000 |
| Terminal Report | FAO China Representation Office/ NPMO | Within two months of project closure | 6,550 |
| Total Budget |  |  | 136,550 |

- Specific reports that will be prepared under the M&E program are: (i) Project inception report; (ii) Annual Work Plan and Budget (AWP/B); (iii) Project Progress Reports (PPRs); (iv) annual Project Implementation Review (PIR); (v) Technical Reports; (vi) co-financing reports; and (vii) Terminal Report. In addition, assessment of the relevant GEF-7 core indicators (see Appendix I: Results Matrix) and capacity scorecards (Appendices X(a) to X(e)) against the baselines (completed during project preparation) will be required at mid-term and final project evaluation.

- Project Inception Report. It is recommended that the NPMO prepare a draft project inception report in consultation with the LTO, BH and other project partners. Elements of this report should be discussed during the Project Inception Workshop and the report subsequently finalized. The report will include a narrative on the institutional roles and responsibilities and coordinating action of project partners, progress to date on project establishment and start-up activities and an update of any changed external conditions that may affect project implementation. It will also include a detailed first year AWP/B, a detailed project monitoring plan. The draft inception report will be circulated to the PSC for review and comments before its finalization, no later than one month after project start-up. The report should be cleared by the FAO BH, LTO and the FAO GEF Coordination Unit and uploaded in FPMIS by the BH.

- Results-based Annual Work Plan and Budget (AWP/B). The draft of the first AWP/B will be prepared by the NPMO in consultation with the FAO Project Task Force and reviewed at the project Inception Workshop. The Inception Workshop (IW) inputs will be incorporated and the NPMO will submit a final draft AWP/B within two weeks of the IW to the BH. For subsequent AWP/B, the NPMO will organize a project progress review and planning meeting for its review. Once comments have been incorporated, the BH will circulate the AWP/B to the LTO and the FAO GEF Coordination Unit for comments/clearance prior to uploading in FPMIS by the BH. The AWP/B must be linked to the project’s Results Framework indicators so that the project’s work is contributing to the achievement of the indicators. The AWP/B should include detailed activities to be implemented to achieve the project outputs and output targets and divided into monthly timeframes and targets and milestone dates for output indicators to be achieved during the year. A detailed project budget for the activities to be implemented during the year should also be included together with all monitoring and supervision activities required during the year. The AWP/B should be approved by the Project Steering Committee and uploaded on the FPMIS by the BH.

- Project Progress Reports (PPR): PPRs will be prepared by the NPMO based on the systematic monitoring of output and outcome indicators identified in the project’s Results Framework (Annex 1). The purpose of the PPR is to identify constraints, problems or bottlenecks that impede timely implementation and to take appropriate remedial action in a timely manner. They will also report on projects risks and implementation of the risk mitigation plan. The Budget Holder has the responsibility to coordinate the preparation and finalization of the PPR, in consultation with the NPMO, LTO and the FLO. After LTO, BH and FLO clearance, the FLO will ensure that project progress reports are uploaded in FPMIS in a timely manner.

- Annual Project Implementation Review (PIR): The BH (in collaboration with the NPMO and the LTO) will prepare an annual PIR covering the period July (the previous year) through June (current year) to be submitted to the FAO GEF Coordination Unit Funding Liaison Officer (FLO) for review and approval no later than (check each year with GEF Unit but roughly end June/early July each year). The FAO GEF Coordination Unit will submit the PIR to the GEF Secretariat and GEF Evaluation Office as part of the Annual Monitoring Review report of the FAO-GEF portfolio. PIRs will be uploaded on the FPMIS by the FAO GEF Coordination Unit.

- Key milestones for the PIR process:

- Early July: the LTOs submit the draft PIRs (after consultations with BHs, project teams) to the GEF Coordination Unit (faogef@fao.org , copying respective GEF Unit officer) for initial review;

- Mid July: FAO GEF Coordination Unit responsible officers review main elements of PIR and discuss with LTO as required;

- Early/mid-August: the FAO GEF Coordination Unit prepares and finalizes the FAO Summary Tables and sends to the GEF Secretariat by (date is communicated each year by the GEF Secretariat through the FAO GEF Coordination Unit;

- September/October: PIRs are finalized. PIRs carefully and thoroughly reviewed by the FAO GEF Coordination Unit and discussed with the LTOs for final review and clearance;

- Mid November: (date to be confirmed by the GEF): the FAO GEF Coordination Unit submits the final PIR reports -cleared by the LTO and approved by the FAO GEF Coordination Unit - to the GEF Secretariat and the GEF Independent Evaluation Office.

- Technical Reports: Technical reports will be prepared by national, international consultants (partner organizations under LOAs) as part of project outputs and to document and share project outcomes and lessons learned. The drafts of any technical reports must be submitted by the NPMO to the BH who will share it with the LTO. The LTO will be responsible for ensuring appropriate technical review and clearance of said report. The BH will upload the final cleared reports onto the FPMIS. Copies of the technical reports will be distributed to project partners and the Project Steering Committee as appropriate.

- Co-financing Reports: The BH, with support from the NPMO, will be responsible for collecting the required information and reporting on co-financing as indicated in the Project Document/CEO Request. The NPMO will compile the information received from the executing partners and transmit it in a timely manner to the LTO and BH. The report, which covers the period 1 July through 30 June, is to be submitted on or before 31 July and will be incorporated into the annual PIR. The format and tables to report on co-financing can be found in the PIR.

Terminal Report: Within two months before the end date of the project, and one month before the Final Evaluation, the NPMO will submit to the BH and LTO a draft Terminal Report. The main purpose of the Terminal Report is to give guidance at ministerial or senior government level on the policy decisions required for the follow-up of the project, and to provide the donor with information on how the funds were utilized. The Terminal Report is accordingly a concise account of the main products, results, conclusions and recommendations of the project, without unnecessary background, narrative or technical details. The target readership consists of persons who are not necessarily technical specialists but who need to understand the policy implications of technical findings and needs for insuring sustainability of project results.

Mid-term Review and Final Evaluation: Two independent project evaluations, one a mid-term review (MTR) in the 3rd quarter of project year 3 and the other a final evaluation (FE) three months prior to the terminal review meeting of the project partners, will be carried out. The MTR will assess the project progress and the likelihood of achieving the various project results, identify issues and challenges, and provide recommendations for enhancing project implementation. The FE will aim to identify the project impacts and sustainability of project results and the degree of achievement of long-term results. This evaluation will also have the purpose of indicating future actions needed to sustain project results and disseminate products and best-practices within the country and to other countries.

# PART iII:  certification by gef partner agency(ies)

## GEF Agency(ies) certification

This request has been prepared in accordance with GEF policies and procedures and meets the GEF criteria for CEO endorsement under GEF-6.

| Agency Coordinator, Agency Name | Signature | Date (MM/dd/yyyy) | Project Contact Person | Telephone | Email Address |
| --- | --- | --- | --- | --- | --- |
| Alexander Jones, Director, Climate and Environment Division, FAO |  |  | Jeffrey Griffin, Senior Coordinator, FAO GEF Coordination Unit | +39 06 570 55680 | jeffrey.griffin@fao.org; |

# List of annexures

Annex A: Project results framework

Annex B: Responses to project reviews

Annex C: Status of implementation of PPG activities

Annex D: Calendar of expected reflows

Annex E: Environmental, social and risk management plan

ANNEX A: Project Results Framework

The project will contribute primarily to the following Sustainable Development Goals: SDG 2: End Hunger, achieve food security and improved nutrition and promote sustainable agriculture. It will particularly contribute to SDG 2, Target 2.5: By 2020, maintain the genetic diversity of seeds, cultivated plants and farmed and domesticated animals and their related wild species, including through soundly managed and diversified seed and plant banks at the national, regional and international levels, and promote access to and fair and equitable sharing of benefits arising from the utilization of genetic resources and associated traditional knowledge, as internationally agreed. In addition, it will contribute to SDG 2, Target 2.4: By 2030, ensure sustainable food production systems and implement resilient agricultural practice that increase productivity and production, that help maintain ecosystems, that strengthen capacity for adaptation to climate change, extreme weather, drought, flooding and other disasters and that progressively improve land and soil quality. SDG 15: Protect, restore and promote sustainable use of terrestrial ecosystems, sustainably manage forests, combat desertification, and halt and reverse land degradation and halt biodiversity loss. It will make secondary contributions towards SDG 1 (end poverty), SDG 5 (gender equality), SDG 10 (reduce inequality), SDG 13 (climate change), and SDG 17 (global partnerships for sustainable development)

FAO’s Strategic Framework (reviewed, 2017): Strategic Objective 2: Make agriculture, forestry and fisheries more productive and sustainable. Strategic Objective 4: Enable more inclusive and efficient agriculture and food production systems. FAO Country Programming Framework (2016-2020): Priority Area: Fostering sustainable and climate-resilient agriculture development. Output 1.1: Introduction and adoption of innovative approaches and best practices in global agriculture development, such as agro-ecology, nutrition-sensitive agriculture, ICT, facilitated and strengthened to contribute to sustainable agricultural development in China; Output 1.2: Biodiversity conservation and development interventions supported to revitalize key forest, water and wetland agro-ecosystems in the country.

Development Objective: Strengthen sustainable livelihoods through improved management and utilization of crop genetic diversity. Project Objective: Mainstream on-farm conservation and sustainable use of globally important local varieties of crops originated in China for food and agriculture, through a strengthened enabling environment, and the development and demonstration of long-term incentive mechanisms.

| Results Chain | Indicator(s) | Baseline | Mid-term Milestone | Target | Means of Verification | Assumption(s) |
| --- | --- | --- | --- | --- | --- | --- |
| GEF-7 Core Indicator | Core Indicator 4: Area of landscapes under improved practices (hectares; excluding protected areas). | - | Sustainable agrobiodiversity management approaches and practices developed and initiated in the project sites | 36,000 hectares of farmland under sustainable agrobiodiversity management in the project sites. | Project progress reports; Project mid-term review and final evaluation reports. | There is active participation by local farmers and other stakeholders; Co-financing materializes as planned; Project timeframe is sufficient to achieve in situ conservation and sustainable use of traditional crop diversity in the demonstration landscapes; Local population will not move out of the selected project sites. |
|  | Core Indicator 11: Number of direct beneficiaries disaggregated by gender as a co-benefit of GEF investment. | - | At least 50% of the target local people; At least 50% of the target agricultural relevant government officials. | 6,600 local people in the project sites, including at least 48% female local population; 300 institutional agricultural relevant staff in government agencies at central and provincial/ local levels. | Project progress reports; Project mid-term review and final evaluation reports. |  |
| Component 1: Strengthen the enabling environment to promote mainstreaming of on-farm conservation and sustainable use of the genetic diversity of important indigenous local crops and varieties |  |  |  |  |  |  |
| Outcome 1.1: In situ conservation and sustainable use of genetic diversity of significant indigenous local crops and varieties mainstreamed into policies or plans at different levels, and also in four targeted provinces, to support the development of national strategies that protect agro-biodiversity. | Existence of a comprehensive framework of policies and strategies across sectors at the national level and in the target provinces based on the results of social, cultural and economic evaluations of local crop varieties. | No policy or strategy for on-farm conservation and sustainable use of traditional/ local crop varieties at the national level and in target provinces | Draft national policy/ strategy in place, and draft provincial policy/ strategy in place in all four target provinces | Drafts of national and provincial policies/ strategies reviewed by MARA and submitted to the concerned government authority | Policy/ strategy drafts; Evaluation reports; Project progress reports. | National and provincial governments are receptive to recommended policy and institutional reforms; Proactive advocacy and stakeholder engagement for consensus on the policies/ strategies can be achieved within the given timeframe; There will be cooperation from other sectors/ agencies for the inter-institutional cooperation mechanisms; Financial data on budget allocation for PGRFA conservation will be readily available; Capacity scorecards have been accurately interpreted and completed. |
|  | Number of coordination mechanisms between sectors and agencies at the national level and in the target provinces for on-farm conservation and sustainable use of local crop varieties. | No cross-sector coordination mechanism specific to on-farm conservation and sustainable use of local crop varieties at the national level and in target provinces | Cross-sector coordination mechanisms developed at the national level and in the four target provinces | Cross-sector coordination mechanisms instituted and fully operational at the national level and in the four target provinces | Minutes of the meetings of the cross-sector coordination bodies |  |
|  | Increased allocation of funds for programs and activities for conservation and sustainable use of genetic resources in the budgets of MARA and the provincial agriculture departments (four target provinces) | CNY 40 million (USD 5.8 million) per year – overall (central level and provinces) | At least 2% increase over 2019 baseline | At least 5% increase over 2019 baseline | Documents of finance support proof of MARA and the provincial agriculture departments |  |
|  | Scores for capacities for: (a) strategy, policy and legislation development; and (b) stakeholder engagement as indicated by capacity scorecard | National level: 11% Hebei: 33% Heilongjiang: 11% Liaoning: 11% Yunnan: 0% | National level: 25% Hebei: 40% Heilongjiang: 25% Liaoning: 25% Yunnan: 25% | National level: 50% Hebei: 50% Heilongjiang: 50% Liaoning: 50% Yunnan: 50% | Capacity scorecards; Project progress reports. |  |
| Component 2: Capacity building to promote adaptive management and improved conservation and sustainable use of crop diversity for resilient agriculture |  |  |  |  |  |  |
| Outcome 2.1: Capacities strengthened to support the long-term plans and upscaling of incentive-based approaches for on-farm conservation and sustainable use of crop diversity for resilient agriculture and sustainable production. | Number of communities/ farm cooperatives with capacity to implement management mechanisms for incentive-based on-farm conservation and sustainable use of local crop varieties. | No communities/ farm cooperatives with capacity to implement management mechanisms for incentive-based on-farm conservation and sustainable use of local crop varieties in the target provinces | Five communities/ farm cooperatives with capacity to implement management mechanisms for incentive-based on-farm conservation and sustainable use of local crop varieties in the target provinces. | Ten communities/ farm cooperatives/ private sectors with capacity to implement management mechanisms for incentive-based on-farm conservation and sustainable use of local crop varieties in the target provinces (i.e. five project demo sites plus five additional sites to be extended during project implementation). | Site visits; Project progress reports; Local stakeholder consultations. | Capacity development activities are efficiently and effectively designed and conducted; Government staff involved in agrobiodiversity conservation have the inclination for participatory approaches, including gender-inclusivity; ToT involves people with training aptitude and inclination; There is interest and willingness among the local stakeholders to engage in the recommended participatory agrobiodiversity management mechanisms; Capacity scorecards have been accurately interpreted and completed. |
|  | Proportion of key stakeholders, viz. farmers, agricultural researchers, extension workers, and private entrepreneurs in the target sites with knowledge and awareness for on-farm conservation and sustainable use of local crop varieties. | X% Baseline survey to be done in year 1 (preferably within the first six months) | 20% more than the baseline (less than half of the end-of-the-project target considering that the initial period may take more time in development of training modules and materials). | 50% more than the baseline (as per concept note) | Sample surveys; Project progress reports; Training/ workshop reports. |  |
|  | Score for capacities for management implementation as per capacity scorecard | National level: 17% Hebei: 33% Heilongjiang: 17% Liaoning: 17% Yunnan: 17% | National level: 25% Hebei: 40% Heilongjiang: 25% Liaoning: 25% Yunnan: 25% | National level: 50% Hebei: 50% Heilongjiang: 50% Liaoning: 50% Yunnan: 50% | Capacity scorecards; Project progress reports; Training/ workshop reports. |  |
| Component 3: Mainstreaming diversity of local varieties through biological, socio-cultural and economic evaluation and the development of market/ non-market incentives and linkages in target sites |  |  |  |  |  |  |
| Outcome 3.1: Improved marketing of products from local varieties including through the use of both traditional knowledge and modern technologies, taking into account market/ non-market incentives to increase local crop diversity production and availability. | Number of local communities/ farm cooperatives with incentive-based schemes on-farm conservation of traditional/local crop varieties in the target provinces. | No local community/ farm cooperatives with incentive-based schemes for on-farm conservation of traditional/ local crop varieties | Five local communities/ farm cooperatives and private sectors with incentive-based schemes for on-farm conservation of traditional/local crop varieties. | Ten local communities/ villages and private sectors with incentive-based schemes on-farm conservation of traditional/local crop varieties, including five that are fully operational in the project demo sites. | Site visits; Local stakeholder consultations; Project progress reports. | Incentive mechanisms and market conditions are favorable to sustain active engagement of local communities and their partners; There is interest and willingness in the private sector to collaborate with local communities in the conservation and marketing of traditional crop varieties. |
|  | Number of local communities/ farm cooperatives with business and marketing plans for products of traditional/ local crop varieties in the target provinces | No local community/ farm cooperatives with business and marketing plan for products of traditional/ local crop varieties | Five local communities/ farm cooperatives with business and marketing plans for products of traditional/ local crop varieties. | Ten local communities/ farm cooperatives with business and marketing plans for products of traditional/ local crop varieties, including five that are fully operational in the project demo sites. | Marketing and business plan documents; Site visits; Local stakeholder consultations; Project progress reports. |  |
|  | Increase in household income of the farmers involved in the project from improved business and marketing schemes in the target project sites. | Baseline to be established (there are tentative figures in the baseline assessments but a proper baseline survey will be necessary to determine more accurate figures, recommended to be done in Year 1. | Business and marketing plans developed for improved income of farmers involved in the target project sites | 15% increase in annual household income of the farmers involved in the project from improved business and marketing schemes in the target project sites. | Household surveys; Site visits; Local stakeholder consultations. |  |
| Component 4: Strengthened knowledge management |  |  |  |  |  |  |
| Outcome 4.1: Information and knowledge of social, cultural, economic, research and marketing aspects related to crops and their local varieties will be collected, documented and published for providing basic support for further conservation and sustainable utilization. | Proportion of various categories of stakeholders (policy-makers, researchers, extension workers, farmers and private entrepreneurs) with improved knowledge and awareness of the traditional/ local crop varieties and their importance/benefits | Baseline % (Knowledge, attitude and practice – KAP - survey to be conducted in Year 1, preferably within the first six months) | 15 % improvement over baseline for policy-makers; 10 percent for researchers; 20 percent for extension workers 30 percent for farmers; 30 percent for private sectors managers. | 30 percent improvement over baseline for policy-makers; 15 percent for researchers; 50 percent for extension workers; 70 percent for farmers; 70 percent for private sectors managers. | KAP surveys (baseline, mid-term and end-of-the-project); Project progress reports. | The design of the KAP survey will be participatory and lead to a genuine assessment of the level of knowledge, attitudes and practices among project stakeholders. Priority is given to completing the design and baseline KAP survey during project inception; The database and knowledge platform will be designed through a participatory process; Sufficient training will be provided to users as well as database managers; Proactive advocacy will be undertaken to facilitate broad usage among stakeholders; Expertise to carry out genuine case-studies and analysis of lessons learnt/ best practices is available. |
|  | Number of knowledge products, including databases and case studies, developed and disseminated | Some agrobiodiversity databases exist within MARA and in the target provinces but they are not systematized. There are also various FAO databases, which could integrate data dissemination needs. | Five case studies, one from each project site, developed and disseminated; Agrobiodiversity databases in MARA and in the provinces strengthened, including integration of data on traditional crop varieties and linkage with FAO databases. | 10 case studies, two from each project site, developed and disseminated; Improved agrobiodiversity databases in MARA and in the provinces fully operational backed up with necessary technical capacity | Knowledge products; Access to databases; Project progress reports; Stakeholder consultations. |  |
|  | Score for capacity to generate, access and use information and knowledge as per capacity scorecards | National level: 13% Hebei: 33% Heilongjiang: 20% Liaoning: 20% Yunnan: 13% | National level: 25% Hebei: 40% Heilongjiang: 30% Liaoning: 30% Yunnan: 25% | National level: 50% Hebei: 50% Heilongjiang: 50% Liaoning: 50% Yunnan: 50% | Capacity scorecards; Project progress reports. |  |

# ANNEX B:  RESPONSES TO PROJECT REVIEWS

There were no STAP / GEF Council comments specific to the FAO Child Project.

# Annex C:  status of implementation of project preparation activities and the use of funds

This table needs to be filled in by FAO:

A.  Provide detailed funding amount of the PPG activities financing status in the table below:

| PPG Grant Approved at PIF: |  |  |  |
| --- | --- | --- | --- |
| Project Preparation Activities Implemented | GETF/LDCF/SCCF/CBIT Amount ($) |  |  |
|  | Budgeted Amount | Amount Spent To date | Amount Committed |
| Total |  |  |  |

# annex D:  calendar of expected reflows (if non-grant instrument is used)

Provide a calendar of expected reflows to the GEF/LDCF/SCCF/CBIT Trust Funds or to your Agency (and/or revolving fund that will be set up)

N/A

# ANNEX E: Environmental, social and risk management plan

The proposed project has been screened and categorized as low risk in accordance with FAO´s Environmental and Social Management Guidelines and shown the screening checklist below:

| Would the project, if implemented? | Not applicable | No | Yes | Unknown |
| --- | --- | --- | --- | --- |
| I. FAO VISION/STRATEGIC OBJECTIVES |  |  |  |  |
| Be in line with FAO’s vision? |  |  |  |  |
| Be supportive of FAO’s strategic objectives? |  |  |  |  |
| II. FAO KEY PRINCIPLES FOR SUSTAINABILITY IN FOOD AND AGRICULTURE |  |  |  |  |
| Improve efficiency in the use of resources? |  |  |  |  |
| Conserve, protect and enhance natural resources? |  |  |  |  |
| Protect and improve rural livelihoods and social well-being? |  |  |  |  |
| Enhance resilience of people, communities and ecosystems? |  |  |  |  |
| Include responsible and effective governance mechanisms? |  |  |  |  |
| ESS 1 NATURAL RESOURCES MANAGEMENT |  |  |  |  |
| Management of water resources and small dams |  |  |  |  |
| Include an irrigation scheme that is more than 20 hectares or withdraws more than 1000 m3/day of water? |  |  |  |  |
| Include an irrigation scheme that is more than 100 hectares or withdraws more than 5000 m3/day of water? |  |  |  |  |
| Include an existing irrigation scheme? |  |  |  |  |
| Include an area known or expected to have water quality problems? |  |  |  |  |
| Include usage of non-conventional sources of water (i.e. wastewater)? |  |  |  |  |
| Include a dam that is more than 5 m. in height? Include a dam that is more than 15 m. in height? |  |  |  |  |
| Include measures that build resilience to climate change? |  |  |  |  |
| Tenure |  |  |  |  |
| Negatively affect the legitimate tenure rights of individuals, communities or others? |  |  |  |  |
| ESS 2 BIODIVERSITY, ECOSYSTEMS AND NATURAL HABITATS |  |  |  |  |
| Make reasonable and feasible effort to avoid practices that could have a negative impact on biodiversity, including agricultural biodiversity and genetic resources? |  |  |  |  |
| Have biosafety provisions in place? |  |  |  |  |
| Respect access and benefit-sharing measures in force? |  |  |  |  |
| Safeguard the relationships between biological and cultural diversity? |  |  |  |  |
| Protected areas, buffer zones and natural habitats |  |  |  |  |
| Be located such that it poses no risk or impact to protected areas, critical habitats and ecosystem functions? |  |  |  |  |
| ESS 3 PLANT GENETIC RESOURCES FOR FOOD AND AGRICULTURE |  |  |  |  |
| Planted forests |  |  |  |  |
| Have a credible forest certification scheme, national forest programmes or equivalent or use the Voluntary Guidelines on Planted Forests (or an equivalent for indigenous forests)? |  |  |  |  |
| ESS 4 ANIMAL - LIVESTOCK AND AQUATIC- GENETIC RESOURCES FOR FOOD AND AGRICULTURE |  |  |  |  |
| Involve the procurement or provision of pesticides? |  |  |  |  |
| Aquatic genetic resources |  |  |  |  |
| Adhere (Aligned) to the FAO Code of Conduct for Responsible Fisheries (CCRF) and its related negotiated instruments? |  |  |  |  |
| Be aligned, where applicable, with FAO’s strategic policies established in the FAO Technical Guidelines for Responsible Fisheries (including aquaculture)? |  |  |  |  |
| Livestock genetic resources |  |  |  |  |
| Be aligned with the Livestock Sector Strategy including the animal disease, public health and land degradation provisions? |  |  |  |  |
| ESS 5 PEST AND PESTICIDES MANAGEMENT |  |  |  |  |
| Involve the procurement or provision of pesticides? |  |  |  |  |
| Result in increased use of pesticides through expansion or intensification of production systems? |  |  |  |  |
| Require the disposal of pesticides or pesticide contaminated materials? |  |  |  |  |
| ESS 6 INVOLUNTARY RESETTLEMENT AND DISPLACEMENT |  |  |  |  |
| Avoid the physical and economic displacement of people? |  |  |  |  |
| ESS 7 DECENT WORK |  |  |  |  |
| Adhere to FAO’s guidance on decent rural employment, promoting more and better employment opportunities and working conditions in rural areas and avoiding practices that could increase workers’ vulnerability? |  |  |  |  |
| Respect the fundamental principles and rights at work and support the effective implementation of other international labour standards, in particular those that are relevant to the agri-food sector? |  |  |  |  |
| ESS 8 GENDER EQUALITY |  |  |  |  |
| Have the needs, priorities and constraints of both women and men been taken into consideration? |  |  |  |  |
| Promote women’s and men’s equitable access to and control over productive resources and services? |  |  |  |  |
| Foster their equal participation in institutions and decision-making processes? |  |  |  |  |
| ESS 9 INDIGENOUS PEOPLES AND CULTURAL HERITAGE |  |  |  |  |
| Are there any indigenous communities in the project area? |  |  |  |  |
| Are project activities likely to have adverse effects on indigenous peoples’ rights, lands, natural resources, territories, livelihoods, knowledge, social fabric, traditions, governance systems, and culture or heritage (tangible and intangible)? |  |  |  |  |
| Are indigenous communities outside the project area likely to be affected by the project? |  |  |  |  |
| Designed to be sensitive to cultural heritage issues? |  |  |  |  |

Note: Screening Checklist as per FAO Environmental and Social Management Guidelines, 2015

While the project itself will bear low environmental and social risks, a number of risks external to the project but with bearing on realization of the project objectives were identified. These are outlined along with mitigation measures in the table below:

| Risks | Risk rating | Mitigation measures |
| --- | --- | --- |
| Policy risks: The project involves rice, oat, millet, and soybean. Compared to the improved varieties of staple crops, the government attaches less importance to the traditional local varieties. At present the country has witnessed bumper harvest for ten consecutive years. As such, it is easy to gain government support to carry out conservation and sustainable use of traditional crop varieties, and relevant policy recommendations are also likely to be formulated and implemented. However, if the grain yield decreases, the government may not want to invest in conservation of traditional crop varieties but increase its focus on expanding the planting area of the main grain crops and promoting new high-yielding varieties for increased grain production because ensuring food security is a major priority for the Chinese government. In such circumstance, government may deviate policy support, adversely impacting the efforts to conserve traditional crop varieties. | Low | The operational partner and main government counterpart for the project is the Ministry of Agriculture and Rural Affairs. MARA is the country's main government agency for the development of agricultural policy. Prior to the formulation of any policy, research must be carried out in the agricultural systems, thus project officials including the National Project Director, are the first ones to obtain information related to the policy development. The project can develop response plans to mitigate the policy risk before the new policy is issued. In addition, the main distribution areas of the traditional crop varieties are generally not suitable for the cultivation of the improved varieties of staple crops. As a result, even if China developed policies to encourage the cultivation of the improved varieties, the impact on the project will be very limited. Furthermore, the project will pilot field interventions on small-scale farms in a few sites, which are unlikely to be intervened for large-scale production. |
| Natural risks: because the targeted local crop varieties are mainly distributed in the local and special ecosystems, which are prone to natural disasters such as drought, there are risks of natural disasters during project implementation, resulting in loss of crop production. In such an event, local communities may misconceive the impact as one due to project design, discouraging the active participation of all stakeholders of the project. | Low | During the project implementation, new commercial varieties will be selected as reference. In case of natural disasters, the advantage of the local variety will be proved by the performance of the new variety and the selected local variety, thus to eliminate the doubt stakeholders, so they will continue to implement the project and achieve the expected objectives. |
| Market risk: One important aspect of this project is to reflect the market value of the genetic diversity of local varieties through markets, providing the farmers with relatively large benefit while at the same time protecting the genetic diversity. However, since China is still in the primary stage of socialist market economy, If the market is fluctuating or even falling back under the impacts of the external environment, it may affect the market outlook for the local crop varieties. | Moderate | The commercialization of the genetic diversity of local varieties is only one way for sustainable utilization; the project will enable farmers to benefits from the conservation and utilization of agricultural diversity. Market and business plans will be developed by the project to improve economic benefits and enhance market resilience of the traditional crop varieties. |
| Co-financing risk: Since the Chinese economy is in the stage of slowing down of the growth rate, whether the committed co-finance can be in full or in time is subject to the influences of many factors including China's economic development. Due to the high proportion of project co-finance, the governments would be in difficulty if the economy were to decline during project implementation. | Low | Co-financing has been be guaranteed through letters of commitment by MARA, provincial/ local governments, private companies and FAO. The co-financing commitments will be monitored and their status assessed during mid-term review and terminal evaluations. In addition, with the adjustment of the agricultural industry policy by the Chinese government, more and more private investment will be involved in the project, so as to ensure that the project has adequate funding sources. |
| Climate change risks: Climate change is increasing impacting many spheres of development including agriculture. The target project provinces are located in different geoclimatic conditions of China, thereby increasing the likelihood of risks from extreme weather events. | Low | The project will focus on sustainable agricultural methods and practices, which will include increasing resilience to climate change. In addition, close communication will be maintained with meteorological stations in the provinces to alert farmer and mitigate any major impacts due to extreme weather. |

Project ID number remains the same as the assigned PIF number.

Wen, J. and Q. Min. September 2017. Reviewing the Progress in the Identification, Conservation and Management of China-Nationally Important Agricultural Heritage Systems (China-NIAHS). Sustainability 2017, 9, 1698; doi:10.3390/su9101698. MDPI.

http://www.fao.org/giahs/giahsaroundtheworld/designated-sites/asia-and-the-pacific/en/

GEF policies encompass all managed trust funds, namely: GEFTF, LDCF, SCCF and CBIT.

If at CEO Endorsement, the PPG activities have not been completed and there is a balance of unspent fund, Agencies can continue to undertake the activities up to one year of project start.  No later than one year from start of project implementation, Agencies should report this table to the GEF Secretariat on the completion of PPG activities and the amount spent for the activities.  Agencies should also report closing of PPG to Trustee in its Quarterly Report.