GEF - PROJECT IMPLEMENTATION REPORT (PIR)

Document Generated by: CCA TM

At: 2025-07-16 02:51:42

# Table of contents

1 PROJECT IDENTIFICATION	3

1.1 Project Details	3

1.2 Project Description	4

1.3 Project Contacts	5

2 Overview of Project Status	6

2.1 UNEP PoW & UN	6

2.2. GEF Core and Sub Indicators	7

2.3. Implementation Status and Risks	7

2.4 Co Finance	8

2.5. Stakeholder	8

2.6. Gender	9

2.7. ESSM	9

2.8. KM/Learning	9

2.9. Stories	10

3 Performance	11

3.1 Rating of progress towards achieving the project outcomes	11

3.2 Rating of progress implementation towards delivery of outputs (Implementation Progress)	12

4 Risks	15

4.1 Table A. Project management Risk	15

4.2 Table B. Risk-log	15

4.3 Table C. Outstanding Moderate, Significant, and High Risks	18

5 Amendment - GeoSpatial	21

5.1 Table A: Listing of all Minor Amendment (TM)	21

5.2 Table B: History of project revisions and/or extensions (TM)	21

UNEP GEF PIR Fiscal Year 2025

Reporting from 1 July 2024 to 30 June 2025

# 1 PROJECT IDENTIFICATION

## 1.1 Project Details

| GEF ID: 8009 | Umoja WBS:SB-013183 |
| --- | --- |
| SMA IPMR ID:40652 | Grant ID: S1-32LDL-000045 |
| Project Short Title: Kathmandu Urban EbA |  |
| Project Title: Ecosystem-based Adaptation for Climate-resilient Development in the Kathmandu Valley, Nepal |  |
| Duration months planned: | 48 |
| Duration months age: | 31 |
| Project Type: | Full-Sized Project (FSP) |
| Parent Programme if child project: |  |
| Project Scope: | National |
| Region: | Asia Pacific |
| Countries: | Nepal |
| GEF Focal Area(s): | Climate Change Adaptation |
| GEF financing amount: | 6,242,700.00 |
| Co-financing amount: | 32,460,000.00 |
| Date of CEO Endorsement/Approval: | 2019-08-02 |
| UNEP Project Approval Date: |  |
| Start of Implementation (PCA entering into force): | 2019-02-12 |
| Date of Inception Workshop, if available: | 2021-11-30 |
| Date of First Disbursement: | 2020-02-17 |
| Total disbursement as of 30 June 2025 (to KVDA): | $ 961835.17 |
| Total expenditure as of 30 June 2025: | $ 538042.57 |
| Midterm undertaken? | No |
| Actual Mid-Term Date, if taken: |  |
| Expected Mid-Term Date, if not taken: | 2025-12-02 |
| Completion Date Planned - Original PCA: | 2023-12-31 |
| Completion Date Revised - Current PCA: | 2027-03-30 |
| Expected Terminal Evaluation Date: | 2027-03-30 |
| Expected Financial Closure Date: | 2027-09-30 |

## 1.2 Project Description

The Kathmandu Valley is under immense pressure to adapt to the escalating impacts of climate change, which is further complicated by the challenge of unplanned urbanization. Built structures are expanding in an unregulated manner, encroaching upon vital blue and green urban assets. This has led to increasingly intense urban flooding, alongside unusual recurring dry spells and drought phenomena. Research consistently shows that groundwater depletion is directly linked to the expansion of built-up areas, a trend fundamentally incompatible with the principles of ecosystem-based adaptation (EbA). Unlike a decade ago, the heat island effects, a consequence of global warming, have become a new normal in the cities of Kathmandu Valley. Simultaneously, the government's limited capacity and policy space to mainstream EbA as an approach to urban climate adaptation in Kathmandu Valley remains a critical area for improvement.

Research-based data and information to guide urban planning and develop climate-resilient cities are a top priority for the Ministry of Urban Development under the Government of Nepal. Equally important is raising public awareness and strengthening the civil society-led climate movement, as a strategy to pressure the government for climate action in urban areas. To address urban climate change adaptation challenges, including urban flooding, drought, landslides, and the urban heat island effect, the Kathmandu Valley Development Authority (KVDA) has been implementing the Ecosystem-based Adaptation for Climate-Resilient Development in the Kathmandu Valley (Kathmandu Urban EbA Project), with financial support from the Least Developed Countries Fund (LDCF)/GEF and technical and financial oversight from the UN Environment Programme (UNEP). The project aims to reduce the vulnerability of urban communities in the Kathmandu Valley to climate change by building resilience through the protection and restoration of urban ecosystems, such as wetlands, lakes, urban forests, open spaces, urban parks, and roadside trees. It also creates new ecosystems, like conservation ponds, to help minimize urban flooding risks. Meanwhile, the project seeks to enhance the institutional and technical capacity of government bodies through training and policy updates, integrating ecosystem-based approaches into urban climate adaptation strategies.

The Project has three components.  Component 1: Mainstreaming EbA into development planning in the Kathmandu Valley. Component 2: strengthened knowledge and awareness of EbA in the Kathmandu Valley. Component 3: EbA interventions to establish climate-resilient communities in the Kathmandu Valley. A total of 60 activities will be implemented to derive 17 outputs by the end of the Project. Component 1 will contribute to enabling the government capacity to integrate EbA into development planning in the Kathmandu Valley (Outcome 1) through the development of urban EbA technical guides; revision of policies, strategies, plans, by-laws, and development budgets, including 20-year strategic development plan of the Kathmandu Valley; and preparation and sharing of policy briefs for revisions of the national policies, including technical training to KVDA and local government staff (by ensuring 50% women participation).  Component 2 will contribute to enhancing the research-informed EbA knowledge base and public awareness of EbA (Outcome 2).  Component 3 contributes to alleviating climate vulnerabilities of local communities in the Kathmandu Valley to climate change impacts such as floods, landslides, and droughts (Outcome 3).  KVDA is the executing agency of this project. KVDA is under the Ministry of Urban Development (MoUD) of the Government of Nepal. The Project has received co-financing from the High-Powered Committee for Integrated Development of the Bagmati Civilization (HPCIDBC) and the Dhobikhola Corridor Improvement Project (DCIP). Moreover, the project adopts a demonstration approach as a proof of concept to i) enhance groundwater recharge; ii) improve soil stability; iii) check urban flooding surge; iv) reduce urban heat effect, and v) build the resilience capacity of urban households. At the same time, the entire Kathmandu population will benefit indirectly through institutionalization and mainstreaming of the EbA in the municipalities and KVDA’s decision-making and annual planning process.

The main government stakeholders of the project are the Ministry of Forests and Environment (Climate change focal point and forests management), Ministry of Federal Affairs and General Administration (focal ministry for local governments), Ministry of Energy, Water Resources, and Irrigation (responsible for water resources management) and municipal governments in the Kathmandu Valley. Additionally, the Nepal Academy of Science and Technology (NAST) is a research partner, and UN-Habitat Nepal is a policy support and capacity-building partner for the effective implementation of the project.

## 1.3 Project Contacts

| Division(s) Implementing the project | Ecosystems Division |
| --- | --- |
| Name of co-implementing Agency | N/A |
| Executing Agency (ies) | Kathmandu Valley Development Authority (KVDA) |
| Names of Other Project Partners |  |
| UNEP Portfolio Manager(s) | Jessica Troni |
| UNEP Task Manager(s) | Moon Shrestha |
| UNEP Budget/Finance Officer | Bwiza Wameyo-Odemba |
| UNEP Support Assistants | 0 |
| Manager/Representative | Durga Prasad Upadhyay |
| Project Manager | Lila Khatiwada (Mr.) |
| Finance Manager | Smriti Purja (Ms.) |
| Communications Lead, if relevant |  |

# 2 Overview of Project Status

## 2.1 UNEP PoW & UN

| UNEP Current Subprogramme(s): | Thematic: Climate action sub-programme |
| --- | --- |
| UNEP previous Subprogramme(s): | i) Number of national, subnational, and private-sector actors that adopt climate change mitigation and/or adaptation and disaster risk reduction strategies and policies with UNEP support(ii) Amounts provided and mobilized in $ per year in relation to the continued existing collective mobilization goal of the $100 billion commitment through 2025 with UNEP support(iv) Positive shift in public opinion, attitudes, and actions in support of climate action as a result of UNEP action. |
| PoW Indicator(s): | - Climate: (i) Number of national, subnational, and private-sector actors that adopt climate change mitigation and/or adaptation and disaster risk reduction strategies and policies with UNEP support. - Climate: (ii) Amounts provided and mobilized in $ per year in relation to the continued existing collective mobilization goal of the $100 billion commitment through to 2025 with UNEP support. - Climate: (iii) Number of national, subnational and private-sector actors reporting under the enhanced transparency arrangements of the Paris Agreement with UNEP support. - Climate: (iv) Positive shift in public opinion, attitudes and actions in support of climate action as a result of UNEP action - Nature: (i) Number of national or subnational entities that, with UNEP support, adopt integrated approaches to address environmental and social issues and/or tools for valuing, monitoring, and sustainably managing biodiversity. - Nature: (iii) Number of countries and national, regional and subnational authorities and entities that incorporate, with UNEP support, biodiversity and ecosystem-based approaches into development and sectoral plans, policies and processes for the sustainable management and/or restoration of terrestrial, freshwater and marine areas - Nature: (iv) Increase in the territory of land and seascapes that are under improved ecosystem conservation and restoration |
| UNSDCF/UNDAF linkages | Aligned with priority thematic area 3, "Resilience, disaster risk reduction, and climate change". |
| Link to relevant SDG Goals | - Goal 13: Take urgent action to combat climate change and its impacts |
| Link to relevant SDG Targets: | - 13.1 Strengthen resilience and adaptive capacity to climate-related hazards and natural disasters in all countries - 13.2 Integrate climate change measures into national policies, strategies, and planning |

## 2.2. GEF Core and Sub-Indicators

GEF core or sub-indicators targeted by the project, as defined at CEO Endorsement/Approval, as well as results

|  | Targets - Expected Value |  |  |  |
| --- | --- | --- | --- | --- |
| Indicators | Mid-term | End-of-project | Total Target | Materialized to date |
| People benefitting from GEF-financed investments | 41000 | 82,000 | 82,000 | 13408 |
| Area of land under restoration | 20 ha | 30 ha | 30 ha | 13.94 ha |
| Level of National/Local reforms and active participation of Inter-Ministerial Committees | 1 | 2 | 2 | 0 |
| People benefitting from GEF-financed investments | 40,000 | 83,280 | 83,280 | 302 (related to training and awareness) |

Implementation Status 2024: 4th PIR

## 2.3. Implementation Status and Risks

|  | PIR# | Rating towards outcomes (section 3.1) | Rating towards outputs (section 3.2) | Risk rating (section 4.2) |
| --- | --- | --- | --- | --- |
| FY 2025 | 4th PIR | S | S | L |
| FY 2024 | 3rd PIR | MS | S | L |
| FY 2023 | 2nd PIR | U | U | M |
| FY 2022 | --Select-- | --Select-- | --Select-- | --Select-- |
| FY 2021 | --Select-- | --Select-- | --Select-- | --Select-- |
| FY 2020 | --Select-- | --Select-- | --Select-- | --Select-- |
| FY 2019 | --Select-- | --Select-- | --Select-- | --Select-- |
| FY 2018 | --Select-- | --Select-- | --Select-- | --Select-- |
| FY 2017 | --Select-- | --Select-- | --Select-- | --Select-- |
| FY 2016 | --Select-- | --Select-- | --Select-- | --Select-- |
| FY 2015 | --Select-- | --Select-- | --Select-- | --Select-- |

Summary of status

Progress

Outcome 1: Enhancing government capacity to integrate EbA into development planning in the Kathmandu Valley

With technical assistance from UN-Habitat, urban EbA technical training modules and resource materials have been developed. These training materials help enhance the technical understanding, knowledge, and programming skills related to EbA integration in urban planning and budgeting, EbA actions and approaches among municipal staff, elected officials, political leaders, and staff of the Kathmandu Valley Development Authority. Twenty-seven urban EbA trainers (currently active) from municipalities, the Ministry of Urban Development, and KVDA have been prepared to enhance EbA skills among municipal authorities, the Ministry, and KVDA.  An urban EbA research grant manual has been developed to guide the research initiatives by the Nepal Academy of Science and Technology (NAST).

Outcome 2: Enhancing the research-informed EbA knowledge base and public awareness of EbA

To strengthen the national knowledge base on urban EbA and promote evidence-informed, climate-resilient urban planning and practices in the Kathmandu Valley and beyond, the research grant award process is underway for 41 research scholars and two research institutions under 43 different research themes. Furthmoer,, capacity-building training and awareness raising  benefited 302 people directly.

Outcome 3: Alleviating climate vulnerabilities of local communities in the Kathmandu Valley to climate change impacts such as floods, landslides, and droughts

The urban dwellers directly benefiting from the project have reached 13,408, mostly through interventions such as rainwater harvesting and groundwater recharge, plantation and greenery works at urban public spaces, and EbA interventions in public schools. 13.94 hectares of land have been restored through nature-based interventions, such as plantations along the roadsides, open spaces, rainwater harvesting, and gardening at public schools.  The total beneficiaries reached by 30 June 2025 are 13,710 (direct beneficiaries and people benefiting from training).

A total of 7,373 students (3,306 males and 4,067 females) from nine public schools—one primary school and eight secondary schools—in the Kathmandu Valley have benefited from EbA interventions, such as rainwater harvesting, groundwater recharge, green roofing, plantation, and school gardening. School eco-clubs, along with teachers, directly participated in implementing EbA activities. Both teachers and students have gained firsthand experience of how urban nature-based solutions can effectively address climate adaptation challenges in the city.

Climate impact studies, ecosystem protection plans, and cost estimates have been completed for the Nagdaha Lake ecosystem in Lalitpur Metropolitan City, the Chyasindole urban forest in Budhanilkantha Municipality, the Gale and Hattichwok urban open space ecosystems in Tokha Municipality, and the Nilbarahi urban forest in Madhyapur Thimi Municipality. Additionally, design studies and cost estimates for building a conservation pond (with a 20,000-cubic-meter stormwater capacity to reduce urban flood risks) towards the upstream of the Dhobikhola River in Budhanilkantha Municipality have been finalized. The contract with the selected bidder for restoring the Nilbarahi urban forest has been signed, while procurement processes for protecting other ecosystems and implementing EbA measures at public buildings in Tokha, Tarakeshwor, Madhyapur Thimi, and Budhanilkantha municipalities are in progress. The installation of rainwater harvesting systems in the administrative building of Budhanilkantha Municipality (Ward no 6) and three private residences (Ward no 10) has proven the concept, supporting efforts to implement Ecosystem-based Adaptation (EbA) activities on both public properties and private homes. Furthermore, tree planting in urban open spaces and along roadsides has enhanced greenery and strengthened urban ecosystem protection.

On average, 44.81% (55.17 % in school EbA works and 34.45% in training and rainwater harvesting) of the total beneficiaries are women. Women's participation in EbA works, including at public schools, training, and the ecosystem protection planning process, has yielded tangible results.

Every major ecosystem restoration work will have an environmental and social safeguard plan. For example, the Environmental and Social Management Framework for Nil Barahi Forest Ecosystem Protection and the Environmental and Social Management Framework for Urban Public Open Space and Park Ecosystems in Tokha Municipality, Ward No. 2 (Gale, Provincial Hospital) and Tokha Municipality, Ward No. 6 (Ward Office) have been prepared.

Challenges

No significant challenges have been identified. Some activities are still awaiting the identification of partners and procurement of experts however this has not presented major issues. Processes to identify and engage partners are ongoing.

Rating:

The overall rating is satisfactory. In the reporting period, the project has proactively addressed the challenges and issues faced by the project in previous years. The project has prepared technical guidelines, a detailed implementation plan for each project site, and the procurement process is underway. Once the partners are identified, the activities is expected to be implemented smoothly.

## 2.4 Co-Finance

| Planned Co-finance: | USD 32,360,000 |
| --- | --- |
| Actual to date: | USD 24,723,709 |
| Progress | Justify progress in terms of the materialization of expected co-finance. State any relevant challenges: In this reporting period, USD 4,590,938 was co-financed with actual expenses in total, involving the Dhobikhola River Corridor Improvement Project (USD 48,308) implemented by the Ministry of Urban Development, and the Bagmati River Basin Improvement Project (USD 4,542,629) implemented by the High-Powered Committee for Integrated Development of Bagmati Civilization (HPCIDBC). The co-financing by HPCIDBC contributed to improving the Bagmati river ecosystems through tree plantation, footpath management with grass paving, green belt creation and improvement, river check dam construction, and river bed dredging. Similarly, co-financing by the Dhobikhola River Corridor Improvement project mainly supported to improve the Dhobikhola River system with improved flood and inundation management, footpath management and development of the physical master plan for the Dhobikhola River corridor improvement The materialization of the co-finance stands at 76.40% against the committed amount, and this progress has been satisfactory to date, as summarized in the table below. S.No.; Co-financing partners; Planned Budget; Actual Expenditure (2021-2022); Actual Expenditure (2022-2023); Actual Expenditure (2023-2024); Actual Expenditure (2024-2025); Total till June 2025; Total Progress against Total Co-financing %. 1; Dhobikhola Corridor Improvement Project, DCIP; 16360000; 805,984; 292,338; 89,117; 48,308; 1,235,747; 3.82%. 2; High Power Integrated Development of Bagmati Civilization, HPIDBC; 16000000; 9,302,074; 9,535,860; 107,398; 4,542,629; 23,487,961; 72.58%. TOTAL CO-FINANCING; 32,360,000; 10,108,058; 9,828,198; 196,515; 4,590,938; 24,723,709; 76.40%. See annex 2 for details. |

## 2.5. Stakeholder

| Date of project steering committee meeting | 2025-03-17 |
| --- | --- |
| Stakeholder engagement (will be uploaded to GEF Portal) | The Ministry of Urban Development, Department of Soil Conservation and Watershed Management (DSCWM), Department of Environment Management, Ministry of Forest and Environment, High Powered Committee for the Integrated Development of Bagmati Civilization (HPCIDBC), Nepal Academy of Science and Technology, Budhanilkantha Municipality, Changunaryan Municipality, Kathmandu Metropolitan City (Ward no 7), Lalitpur Metropolitan City and Ward no 24, Gokarneshwor Municipality, Madhyapur Thimi Municipality, Suryabinayak Municipality, Tarakeshwor municipality, Kirtipur Municipality, Tokha Municipality, Shivapuri Nagarjun National Park, Divisional Forest Office (Kathmandu), Department of National Parks and Wildlife Conservation, and the Government Integrated Data Center (GIDC) were key government stakeholders that supported project implementation. Likewise, UN-Habitat played a key role in delivering activities under outcome 1. Meanwhile, engaging nine public schools in Kathmandu Valley helped successfully implement EbA works in schools. The cooperation of local urban communities, including local NGOs, the environmental organization (NEPCEMAC Lalitpur), was crucial to materialize EbA activities and planning for ecosystem protection activities. The Stakeholder Engagement Plan was updated in June 2025 (Annex 4). The list of stakeholders engaged in this reporting period is given in Annex 3. |

## 2.6. Gender

| Does the project have a gender action plan? | Yes |
| --- | --- |
| Gender mainstreaming (will be uploaded to GEF Portal): | During this reporting period, women's participation in planning, implementing, and maintaining EbA activities was encouraging to build resilience against climate change impacts in the urban areas of Kathmandu Valley. Out of 260 participants, the number of women in plantation activities was 114. Out of 302 participants in the EbA training, 104 were women, and school EbA interventions involved 4067 women (out of 7373) . Furthermore, out of 7373 students, 4067 (55.17%) were female students from nine public schools in the Kathmandu Valley who have benefited from EbA interventions, such as rainwater harvesting, groundwater recharge, green roofing, plantation, and school gardening. Out of 27 EbA trainers trained to transfer EbA planning and implementation knowledge and skills, 9 are women. One hundred and four research scholars have applied for urban EbA research grants under this project to conduct studies in Kathmandu Valley and beyond. The research cooperation partner, the Nepal Academy of Science and Technology (NAST), is currently screening research applicants to select 43 candidates for research grants, with at least 33% of the successful grantees expected to be women. Additionally, gender-responsive climate change and EbA awareness campaigns will be developed as part of the project’s advocacy and communication strategy. Women’s participation was encouraged in every ecosystem protection plan; their ideas and input were actively sought. For example, 43 women participated in developing plans for the Nagdaha lake ecosystem, and 45 were men. Activity-specific details of gender mainstreaming against the gender action plan are given in Annex 5. |

## 2.7. ESSM

| Moderate/High risk projects (in terms of Environmental and social safeguards) | Was the project classified as moderate/high risk, CEO Endorsement/Approval Stage? Classified the project as If yes, what specific safeguard risks were identified in the SRIF/ESERN? Environmental, Social and Economic Review Note (ESERN) was prepared in August 2018, and reviewed & accepted in September 2018. The Safeguard Advisor recommended the project to be put under 'moderate safeguard risk category' considering the possibility of sedimentation and water contamination in the project sites (SS 2), and impact on heritage sites during project operation (SS 7). Furthermore, the risk, as pointed out by the ESERN report, includes (a) construction activities may result in temporary downstream sedimentation, and (b) groundwater recharge may result in groundwater contamination. Environmental and Social Safeguards and Implementation Mechanism and Safeguard Risk Identification Form (SRIF) developed in July 2022, mentions in chapter 2.1 that "based on the nature and activities of the Project, almost all activities will have no environmental and social risks and impacts. Once specific construction activities are identified and designed for component 3 and its outputs, a low level of risks and impacts is predicted (likely to occur) during Project implementation in the spirit of the ESSF and Nepal's environmental laws and other national requirements". The . . However, for each of the ecosystem protection sites, a separate ESFM will be prepared. For example, for the Nil Barahi Forest Ecosystem and the Tokha open space ecosystem, individual Environmental and Social Management for Tokha open space ecosystem and Nil Barahi open space ecosystems have been developed (Annex 7 and Annex 8) . They will be implemented accordingly during the ecosystem restoration and protection time. Likewise, the Environmental and Social Management Framework (ESMF) will be developed in Q3, 2025 for the Nagdaha lake ecosystem (Lalitpur Metropolitan City, Ward no 24), Chyasindol urban open space ecosystem (Budhanilkantha municipality, Ward no 6), and the Conservation-pond (Budhanilkantha municipality, Ward no. 2 and 13). Currently, the Project is conducting an Initial Environmental Examination (IEE) for the conservation pond, following the environmental rules of the Government of Nepal. In Q4, 2025, the ESMF will be developed for Shivabatika urban open space ecosystem (Changunarayan municipality, Ward no 1) and Bhootkhel urban space ecosystem (Tokha municipality, Ward no.3). The safeguard expert or project technical staff will be given responsibilities for the implementation, monitoring, and reporting of safeguard issues. |
| --- | --- |
| New social and/or environmental risks | Have any new social and/or environmental risks been identified during the reporting period? No If yes, describe the new risks or changes. |
| Complaints and grievances related to social and/or environmental impacts | Has the project received complaints related to social and/or environmental impacts (actual or potential) during the reporting period? No If yes, please describe the complaint(s) or grievance(s) in detail, including the status, significance, who was involved, and what actions were taken? . Grievance Redress Mechanism for the Nil Barahi urban forest ecosystem in Madhyapur Thimi municipality has been formed with the following structure: SN; Representative; Role. 1; Deputy Mayor; Coordinator. 2; Ward Chair of Ward no 9; Member. 3; A representative of the Nil Barahi Community Forestry Group; Member. 4; A representative of the local community; Member. 5; A representative of KVDA; Member. 6; Ward Secretary of Ward no 9; Member Secretary. The Grievance and Redress Mechanism will be developed in Q3, 2025, for Gale and Hattichowk urban open space ecosystems, Nagdaha lake ecosystem, and Chyasindol urban open space ecosystem. In Q4, 2025, a similar mechanism will be developed for Shivabatika urban open space ecosystem in Changunarayan municipality and Bhootkhel urban open space ecosystem in Tokha municipality. |
| Environmental and social safeguards management | The project has an Environmental and Social Management Framework (ESMF) developed following the standards defined in the UNEP Environmental and Social Safeguards. Additionally, addressing safeguard issues at the municipal level has been prioritized. For example, for Nil Barahi Forest Ecosystems protection, a separate ESMF (Annex 7) has been developed, and it will be implemented while undertaking the ecosystem restoration activities. Likewise, for each of the ecosystem protection sites as indicated earlier, a separate ESFM will be prepared. The safeguard expert will be given responsibilities for the implementation, monitoring, and reporting of safeguard issues. |

## 2.8. KM/Learning

| Knowledge activities and products | Urban EbA technical training modules and resource materials on planning and implementing EbA interventions have been prepared. The EbA training materials are being utilized for the capacity building of KVDA staff, municipal elected representatives, and technical staff, climate change, and EbA/NbS awareness among urban communities in the Kathmandu Valley. The Plantation policy brief is in the preparation phase and will come out in Q3, 2025. |
| --- | --- |
| Main learning during the period | Learning 1: In the context of a decentralized governance system where local governments are legally mandated to shape up their policy, planning, and development practices to address the overall climate and development needs at the local level, collaboration with municipalities would make the project delivery easy, and they would take active responsibility for the success of the project. At the same time, informing, consulting, and input from community people as stakeholders of the project would be extremely vital. For this reason, the implementation progress in this reporting period has picked up. Learning2: If explored, there would be a potential for resource collaboration to deliver the common goal of building ecosystem resilience, thereby enabling people's adaptation capacity. This learning is linked to the discussion in progress about forming a separate partnership deal between the Urban EbA Project (KVDA) and the High-Powered Committee for Integrated Development of Bagmati Civilization (HPCIDBC) to build a 20,000 cubic meter conservation pond at Budhanilkantha municipality (Ward no. 2 and 13). As per the design and cost estimate report of the intervention, the urban EbA project budget for this EbA intervention is likely to be inadequate, and the HPCIDBC may step in to work together for the construction of the conservation pond. Learning 3: For the continuous maintenance and protection of the new ecosystems created by the project, handing them over as urban green assets to the local government would be highly effective. And, the handing-over needs to be immediate and in writing, with clear responsibilities on the part of the local government. This learning is associated with the project's efforts to promote urban greenery and roadside tree ecosystems through plantation with massive mobilization of local urban dwellers, community groups, NGOs, Private Organizations, and Ward Offices of the concerned municipalities. |

## 2.9. Stories

| Stories to be shared | Two case stories |
| --- | --- |

# 3 Performance

## 3.1 Rating of progress towards achieving the project outcomes

| Project Objective and Outcomes | Indicator | Baseline level | Mid-Term Target or Milestones | End of Project Target | Progress as of current period (numeric, percentage, or binary entry only) | Summary by the EA of attainment of the indicator & target as of 30 June | Progress rating |
| --- | --- | --- | --- | --- | --- | --- | --- |
| To reduce the vulnerability to climate change of people living in the Kathmandu Valley through implementation of urban EbA. | % of development budget allocated for EbA measures in Kathmandu Valley | 0 | 0 | 10% of the development budget in 11 municipalities allocated for EbA measures | 15% | Being positively influenced in the process of planning and developing Detailed Project Report of ecosystem restoration and protection interventions, training and promotion of rainwater harvesting, Budhanilkantha municipality, Tokha municipality, Madhyapur Thim municipality, and Lalitpur metropolitan city have allocated a budget for EbA measures such as plantation, landslide management, wildfire prevention awareness, flood control, and rainwater harvesting, conservation of urban water bodies, including rivers, among others. Tokha municipality and Budhanilkantha municipality have approached Kathmandu Valley Development Authority (Urban EbA Project) to assist them in providing technical support to institutionalize the existing rainwater harvesting guidelines and decisions. | MS |
| Increased capacity of government to integrate EbA into development planning in the Kathmandu Valley. | Number of plans, strategies, and guides established and/or adapted for urban EbA in the Kathmandu Valley | 0 | 0 | At least one strategic plan and one set of by-laws integrate urban EbA and associated budget prioritized for urban EbA measures, tested by the project | 20% | Technical training modules and materials for planning, design, implementation, and maintenance of urban EbA have been prepared with the technical assistance of UN-Habitat. Using the training materials, the EbA orientation program for the urban communities of Madhyapur Thimi municipality has been delivered. Tokha municipality and Budhanilkantha municipality have developed a rainwater harvesting plan targeting new construction sites (private buildings). Budhanilkantha municipality has established a provision for 50% cost subsidies for new housing to install a rainwater harvesting system Twenty-seven EbA resource persons have been prepared (active in delivering training currently) who will provide EbA planning and implementation knowledge and skills to local political leaders, municipal staff, KVDA staff, and community people. UN-Habitat has been assisting the Project in reviewing already prepared technical guides for EbA interventions, including a framework for assessing the cost-effectiveness of EbA interventions, developing a roadmap with time-bound targets for integration of EbA into municipality-level planning processes, developing a policy recommendation report to enable budgetary allocation for EbA interventions at the municipality level, and developing policy briefs. The EbA training schedule has been developed, and dates of training have been tentatively fixed with UN-Habitat and four municipalities. | MS |
| Knowledge and awareness of local communities living in the Kathmandu Valley on EbA enhanced. | Level of knowledge and awareness on EbA of men and women living in the project intervention sites (6 wards in 5 municipalities in 3 districts:82,000 people in the Kathmandu Valley. | 0 | 25500 | 41000 | 50% | EbA awareness was raised among more than 26,500 people through training, EbA information sharing at 30 public schools, and EbA activity implementation at nine public schools. Local knowledge and evidence generation through research programs are underway. Forty-three research programs are being managed by Nepal Academy of Science and Technology (this project's research partner) in this regard. The selection of researchers is almost in the final stage. Web-based urban EbA knowledge platform is under update for better functions, and the web platform will be accessible from the 1st week of September 2025. | S |
| Decreased vulnerability of communities in the Kathmandu Valley to the climate change impacts of flooding, landslides, and droughts. | Supply of ecosystem services in the intervention sites (6 wards in 5 municipalities:82000 people) e.g. flood, water availability, soil stability greenery. Hectares of land on which urban EbA is being implemented. | 0 |  | 50% of men and women living in the project intervention sites (6 Wards in 5 municipalities:82000 people) notice an improvement in the supply of ecosystem services (flood control, water availability, soil stabilization, greenery improvement). 30 hectares of land on which urban EbA is being implemented. | 16.35% | The urban dwellers directly benefiting from the project with reduced vulnerability state have reached 13,408, mostly through rainwater harvesting and groundwater recharge, plantation and greenery works in urban public spaces, and EbA works at public schools 13.94 hectares of land have been undergoing restoration through nature-based works such as plantation along roadsides, open spaces, rainwater harvesting, and gardening at public schools. The climate impact assessment, ecosystem intervention design, and cost estimates for major ecosystems such as Nil Barahi forest ecosystem, Chyasindol urban open space ecosystem, Gale and Hattichowk urban open space ecosystems, Nagdaha lake ecosystem, conservation pond ecosystem, have already been completed. Based on the ecosystem design and cost estimates, a contractor has been selected and a contract has been awarded for the protection of the Nil Barahi forest ecosystem, while for other ecosystems, the e-bidding process is underway following the procurement rules of the Government of Nepal. The restoration and protection of those ecosystems will commence in Q4 of 2025. In the meantime, climate impact assessment and restoration design for Bhootkhel urban open space ecosystem and Shivabatika urban open space ecosystem have begun. Once the design and cost estimate report is produced in October 2025, the procurement of contractors for the restoration of the ecosystem will begin thereafter as per the procurement procedures of the Government of Nepal. | MS |

## 3.2 Rating of progress implementation towards delivery of outputs (Implementation Progress)

| Component No | Output/Activity | Expected completion date | Implementation status as of the previous reporting period (%) | Implementation status as of the current reporting period (%) | Progress rating justification, description of challenges faced, and explanations for any delay | Progress Rating |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Output 1.1. Urban EbA technical guides developed to direct the planning, design, implementation, and maintenance of urban EbA in the Kathmandu Valley. | 2024-12-31 | 48% | 55% | The existing technical guides should be updated, and UN-Habitat will update them in Q3/4 of 2025 following the stakeholder consultation. For this, the UN-Habitat has begun the process of procuring the consultants. | S |
| 1 | Output1.2. Reports developed that provide recommendations on revisions to policies, strategic plans, by-laws, and development budgets for the mainstreaming of urban EbA. | 2025-06-30 | 0 | 0 | The reports with recommendations on revisions to policies, strategic plans, by-laws, and development budgets for mainstreaming of urban EbA should be updated and the UN-Habitat will update the reports in Q3/4 of 2025, engaging the relevant stakeholders. For this, UN-Habitat has already initiated the process to procure the consultants. | MS |
| 1 | Output 1.3. Recommendations approved by the Physical Development Committee for revisions to the 20-year strategic development plan, relevant development by-laws and budget allocated to support the integration of urban EbA in the development planning | 2025-09-30 | 0 | 0 | The existing reports need updating by an expert from UN-Habitat. Once the reports are updated in Q3 of 2025, they will be submitted to the Development Commissioner of Kathmandu Valley Development Authority (KVDA), who will call a meeting of the Physical Development Committee to discuss, own, endorse, and consider the recommendations to be integrated into KVDA's strategic development plan, bylaws, and budgeting. | MS |
| 1 | Output 1.4. Policy briefs for revisions to national policies submitted to MoUD, MoFE and the NPC. | 2025-06-30 | 0 | 0 | UN-Habitat will carry out this activity in Q3/4 of 2025. The process of service procurement has been initiated. | MS |
| 1 | Output 1.5. Seven technical training modules and materials delivered for 175 KVDA and municipal staff on planning and implementing EbA interventions in the Kathmandu Valley. | 2024-12-31 | 0 | 10% | EbA technical training modules and resources have been developed. Two events of EbA technical orientation to community people in Madhypur Thimi municipality were conducted. | S |
| 2 | Output 2.1 Thirty research projects delivered within an ongoing research programs on EbA interventions in the Kathmandu Valley. | 2025-12-31 | 10% | 20% | An urban EbA research grant manual has been developed to guide the research initiatives by the Nepal Academy of Science and Technology (NAST). To strengthen the national knowledge base on urban EbA and promote evidence-informed, climate-resilient urban planning and practices in the Kathmandu Valley and beyond, the research grant award process is underway for 41 research scholars and two research institutions under 43 different research themes. 104 research grant applications have been received, of which 48 are from women. | MS |
| 2 | Output 2.2. Public awareness-raising campaign implemented in all 3 districts of Kathmandu Valley through popular broadcast media on the effects of climate change and the role of EbA to address them. | 2025-12-31 | 0 | 5% | An awareness-raising pamphlet titled 'climate change impacts and adaptation measures 'was produced and distributed among the students of 30 public schools across the cities in Kathmandu Valley. The pamphlet was also used during the Urban EbA programs for teachers and students. The public awareness raising through media mobilization has been rescheduled for Q3 2025 onwards. | MS |
| 2 | Output 2.3 EbA interventions implemented at 10 schools in 3 districts of the Kathmandu Valley to raise awareness on urban EbA. | 2025-06-30 | 5% | 90% | EbA interventions at schools have been implemented, thereby raising EbA awareness through their direct engagement in EbA actions. A total of 7,373 students (3,306 males and 4,067 females) from nine public schools—including one primary and eight secondary schools—in the Kathmandu Valley have benefited from EbA interventions such as rainwater harvesting, groundwater recharge, green roofing, planting, and school gardening. School Eco-clubs, along with teachers, were directly involved in implementing EbA activities. Both teachers and students have gained firsthand experience of how urban nature-based approaches can effectively help them adapt to climate challenges in their city. | S |
| 2 | Output 2.4: Web-based urban EbA knowledge-sharing platform developed to disseminate less learned and best practices nationally and internationally. | 2025-06-30 | 20% | 50% | Web-based urban EbA knowledge-sharing platform was developed and launched in the previous reporting period. However, due to some technical glitches, the web platform needs to be upgraded, and thus, the web platform is under repair and will be functional in August this year. Climate risk information, best practices, lessons learnt, and other relevant matters to EbA and NbS will be collated and uploaded onto the websites for wider reach. | MS |
| 3 | Output 3.1: Site assessments conducted and participatory community planning undertaken in 5 municipalities across 3 districts for urban EbA interventions in Kathmandu Valley. | 2025-12-31 | 10% | 90% | Site assessments (climate impact studies, ecosystem protection plans, and cost estimates) have been completed for the Nagdaha Lake ecosystem in Lalitpur Metropolitan City, the Chyasindole urban forest in Budhanilkantha Municipality, the Gale and Hattichwok urban open space ecosystems in Tokha Municipality, and the Nilbarahi urban forest ecosystem in Madhyapur Thimi Municipality. Also, design studies and cost estimates for building a conservation pond (with a 20,000-cubic-meter stormwater capacity to reduce urban flood risks) towards the upstream of the Dhobikhola River in Budhanilkantha Municipality have been finalized. The additional ecosystem sites at climate risk have been identified, and their assessment will be carried out in Q3/4 of 2025. | S |
| 3 | Output 3.2: GIS-based EbA flood management decision-making tool developed for identifying future sites and interventions in three municipalities. | 2025-06-30 | 5% | 5% | The Project Steering Committee (PSC) meeting on 17th March 2025 decided to remove this activity for the reason that the Master Plan clearly identifies the potential sources of urban flooding in the Kathmandu Valley. The Master Plan also allows KVDA to evaluate the flood impacts and implement EbA interventions in the flood-prone locations of the Kathmandu Valley. | xx |
| 3 | Output 3.3: Flood management, erosion control and groundwater recharge measures in 5 vulnerable public spaces in 5 municipalities across 3 districts. | 2025-12-31 | 0 | 10% | Nil Barahi urban forest ecosystem, Nagdaha lake ecosystem, Chyasindol urban open space ecosystem, Gale and Hattichowk urban open space ecosystems, Bhootkhel urban open space ecosystem, and Shivabatika urban open space ecosystem are the key urban natural ecosystems of the Kathmandu Valley. Their restoration and protection are vital in improving flood management, controlling soil erosion, and enabling groundwater recharge in the Kathmandu Valley. For the restoration and protection of Nil Barahi forest ecosystem, the contractor has been selected following the procurement rules of the Government of Nepal, and the protection works will begin at the end of September 2025, after the intensity of monsoon rain dwindles. The procurement of a contractor for the protection of Nagdaha lake ecosystem, Gale&Hattichowk urban open space ecosystems, and Chyasindol urban open space ecosystem has been initiated as per the procurement procedures of the Government of Nepal. In the meantime, climate impact assessment with ecosystem restoration design and cost estimates for Bhootkhel urban open space ecosystem and Shivabatika urban open space ecosystem has been initiated. The protection and restoration interventions of these ecosystems will begin once the contractors are selected and the contract is awarded. | MS |
| 3 | Output 3.4: Groundwater recharge wells, tree plantation, and permeable paving parking lots on 60 public building plots in 5 municipalities across 3 districts. | 2025-03-30 | 10% | 20% | Public properties, such as offices of municipalities and their Wards, health centers and hospitals, community buildings and schools, offer opportunities to demonstrate how urban EbA interventions, such as rainwater harvesting, tree plantation, and permeable parking lots, can reduce the climate-induced risks of urban flooding, drought, and heat stress. During this reporting period, a rainwater harvesting system was installed in the administrative buildings of Budhanilkantha municipality with the capacity of harvesting 1 million liters of rainfall per year and channeling rainwater underground through recharge wells. As a pilot intervention for testing rainwater harvesting technology, the scheme was successful. Based on the successful results gained from the pilot scheme, the e-bidding to select a contractor to carry out EbA activities (rainwater harvesting, permeable parking lots, and plantation) in Tokha municipality has been initiated as per the procurement rules of the Government of Nepal. Evaluation of bidders has been completed. Likewise, similar EbA interventions at 16 public buildings in Tarakeshor municipality, 18 public buildings in Budhanilkantha municipality, and 8 buildings at Madhypur Thimi municipality have been planned, and the procurement process will be initiated in Q3 2025. | MS |
| 3 | Output 3.5: 4,000 climate resilient trees planted and 10,000 cubic meter of conservation ponds constructed in the SNNP buffer zone. | 2025-09-30 | 5% | 15% | Design and cost estimates (DPR) of conservation pond construction have been completed. An Initial Environmental Examination (IEE) of the conservation pond construction has been initiated.The Terms of Reference following the IEE format of the Government of Nepal have been drafted and are now in the consultation stage. Once the IEE study is completed, e-bidding of the construction work will be initiated in Q4 of 2025. Tree plantation in the SNNP buffer zone around the conservation pond will happen during the construction of the conservation pond. | MS |
| 3 | Output 3.6: Implementation guide for the household-level EbA interventions developed based on a stakeholder engagement process run by the 5 municipalities across 3 districts. | 2024-03-30 | 100% | 100% | As reported in the previous reporting period, the implementation guide for the household-level EBA interventions has been completed. The guidebook will be referred to while implementing household-level EbA works. The first phase of household-level EbA will be carried out in Budhanilkantha municipality in Q4 of 2025. | S |
| 3 | Output 3.7: EbA interventions, including rainwater harvesting, household-level infiltration pits and urban farming/gardening implemented in 280 private households across 5 municipalities in the Kathmandu Valley. | 2025-06-30 | 15% | 20% | As a pilot scheme, rainwater harvesting and rooftop farming systems were installed in three selected private homes in Ward no 10 of Budhanilkantha municipality. For a full scale implementation, the e-bidding process will commence in Q4 2025. | MS |
| 3 | Output 3.8: 4000 climate resilient trees planted in roadsides, along river banks and in public spaces in urban areas of the Kathmandu Valley. | 2025-06-30 | 38% | 100% | As of 30 June 2025, altogether 5275 tree saplings have been planted. Plantation sites are Araniko Highway (Suryabinayak municipality and Madhyapur Thimi municipality), Nikoshera road (Madhyapur Thimi municipality), Duwakot Road (Changunarayan municipality), Jhaukhelo (Changunarayan municipality), Chhaling (Changunarayan municipality), Nagarkot (Changunarayan municipality), Katunje (Suryabinayak municipality), Hanumanthe river corridor (Madhyapur Thimi municipality), Bagamati river corridor (Gokarneshwor municipality), Shantidanda park road (Changunarayan municipality). There is still surplus budget under this activity, at least 4,000 trees saplings will be planted in Q2/3 of 2025. | S |

The Task Manager will decide on the relevant level of disaggregation (i.e. either at the output or activity level).

# 4 Risks

## 4.1 Table A. Project management Risk

Please refer to the Risk Help Sheet for more details on rating

| Risk Factor | EA Rating | TM Rating |
| --- | --- | --- |
| 1 Management structure - Roles and responsibilities | Low | Low |
| 2 Governance structure - Oversight | Low | Low |
| 3 Implementation schedule | Low | Low |
| 4 Budget | Low | Low |
| 5 Financial Management | Low | Low |
| 6 Reporting | Low | Low |
| 7 Capacity to deliver | Low | Low |

If any of the risk factors is rated a Moderate or higher, please include it in Table B below

## 4.2 Table B. Risk-log

Implementation Status (Current PIR)

Insert ALL the risks identified, either at CEO endorsement (inc. safeguards screening), previous/current PIRs, and MTRs. Use the last line to propose a suggested consolidated rating.

| Risks | Risk affecting: Outcome/outputs | CEO ED | PIR 1 | PIR 2 | PIR 3 | PIR 4 | PIR 5 | PIR 6 | Δ | Justification |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Sedimentation and water contamination at the project site | Outcome 3: Decreased vulnerability of communities in the Kathmandu Valley to the climate change impacts of flooding. landslides. and droughts. Output 3.3: Flood management. erosion. control. and groundwater recharge measures in 5 vulnerable public spaces in 5 municipalities across 3 districts. | M | L | L | L | L |  |  | ↓ | The Project does not foresee it as a major challenge. If sedimentation and contamination happen to be a problem, it will implement the proposed mitigation measures (risk mitigation plan) effectively. |
| Climate risks and extreme climate events impact on project interventions. | Outcomes 1-3 | M | M | M | M | M |  |  |  | The risk is medium because the project sites may be impacted by climate risks and extreme climate events like urban flooding and landslides, water scarcity, etc. EbA interventions are planned to address these climate vulnerabilities. The flooding hazard may impact the tree plantation sites, rainwater harvesting at private and public properties. The landslide may affect the project while implementing the restoration of Chyasindole urban forest ecosystems, Nagdaha lake ecosystem, and Nil Barahi forest ecosystem. As per the Public Procurement Policy of the Government of Nepal, the ecosystem site-specific insurance policy needs to be purchased by the contractor and in case the extreme event causes physical damage, the insurance will cover the loss. The project activity will temporarily be halted during the extreme events to avoid additional loss and damage. |
| High rate of staff turnover within the project management and steering committee. | All outcomes & outputs | L | L | M | L | L |  |  |  | The project functionary has been firm since January 2024 with no staff turnover. Though the National Project Manager is new to the role, he has already developed a deep understanding of the project in no time. The cooperation and guidance of the Project Steering Committee (PSC) were significantly helpful for the project implementation. |
| Risk of low community ownership of project activities and interventions post-project implementation. | Output 3 | L | L | L | L | L |  |  |  | Community ownership of the project is high. Community engagements were ensured during the ecosystem sites assessments. Local people, including NGOs, local youths, schools, and the private organizations working in the environment sector, voluntarily participated in plantation activities. Local municipal governments would encourage the participation of local communities in the project activities. The Project Management Unit would have consultations with local environmental activists and direct beneficiaries of the project activities. Local governments fully supported the project implementation, at the time of ecosystem sites assessments, tree plantation, outworking of EbA works in public buildings, private homes, and public schools. |
| Loss of political support at post-project implementation | All outcomes & outputs | L | L | L | L | L |  |  |  | Local political leaders show their support for KVDA with pressure to implement the project. Their participation in the project's meetings with local governments was encouraging. |
| Limited technical on-the-ground expertise for implementing project interventions. | All outcomes & outputs | M | M | M | L | L |  |  |  | The PMU/KVDA mobilized its technical staff for monitoring of the ground works. PMU has hired two assistant civil engineers with a good understanding of EbA principles. At the same time. if required, KVDA will mobilize a temporary technical person for monitoring and supervision of the ground works from the contingency. Additionally, technical assistance provided by the UN-Habitat and Nepal Academy of Science and Technology (NAST) will meet the needs of technical expertise on the ground. |
| Interventions are not cost-effective. | Outcome 3 | L | L | L | L | L |  |  |  | The interventions are cost-effective. Assessment, protection designs, and cost estimates for five ecosystem sites have been completed. Plantation in urban river corridors, city roads, and urban open spaces will be cost-effective in reducing urban heat stress compared to engineering measures. Rainwater harvesting systems in public buildings and private homes will contribute to reducing urban runoff and floods, and the same system will improve groundwater tables and reduce the drought effects, impacts. Construction of a conservation pond (20,000 cubic meters capacity) at Shivapuri Nagarjun National Park buffer zone at Budhanilkantha municipality will hold stormwater and contribute to reducing urban flooding at the Dhobikhola river in the Kathmandu Valley. |
| Groundwater recharge results in groundwater contamination | Outcome 3 | M | M | L | L | L |  |  |  | The groundwater recharge technology adopted in this project has a device that filters the rainwater. So, there is no possibility of groundwater contamination. |
| Pandemic issues like covid 19 resulting delay in the project | All outcomes & outputs | N/A | M | L | L | L |  |  |  | No more pandemic now |
|  |  | M | L | L | L |  |  |  | ↓ | The overall risk is low. |

## 4.3 Table C. Outstanding Moderate, Significant, and High Risks

Additional mitigation measures for the next period

| Risk | Actions decided during the previous reporting instance (PIRt-1, MTR, etc.) | Actions effectively undertaken during this reporting period | What | When | By Whom |
| --- | --- | --- | --- | --- | --- |
| Sedimentation and water contamination in the project site (M) | No activities were implemented under outcome 3/output 3.3 and output 3.5 | The identified risk is temporary and of low impact; therefore, it is low risk. The assessment process of the five urban ecosystems (Nil Barahi urban forest ecosystem, Nagdaha urban wetland ecosystem, Chyasindol urban forest ecosystem, Tokha open space/park ecosystem at Gale and Hattichowk-two sites). The design and cost estimate for the construction of the conservation pond at the Dhobikhola River in Budhanilkantha municipality have also been completed. | Sedimentation removal in the Nagdah wetland, filling appropriate soil in the landslide management site in Nil Barahi forest, earthworks in conservation pond construction in Budhanilkantha municipality at the Dhobikhola River (SNNP buffer zone), and Chysindole forest ecosystem protection sites in Budhanilkantha municipality. The Environmental and Social Management Framework for the Tokha open space ecosystem and the Nil Barahi urban forest ecosystem have been prepared and will be implemented during the implementation of ecosystem protection. A similar framework for other ecosystem sites will also be developed and put into action. | During the EbA interventions for the restoration and maintenance of the ecosystems | KVDA/Project Management Unit, concerned municipalities, and contractors. |
| Governance structure – Oversight (M) | The project developed a project operating manual. | The project has been implemented following the project operational manual. However, the project has yet to develop an M&E framework. The position of M&E expert will be filled in Q3 of 2025 and will be supporting the project for its effective implementation. | The M&E framework will be developed once the M&E expert is hired. | Q3 of 2025 | Project Management Unit/KVDA |
| Implementation schedule (S) | The Project Manager was hired on the 1st of January 2024. The implementation schedule was prepared and endorsed by the Project Steering Committee meeting on the 6th of February 2024 and revised and approved on the 17th 2025. UN-Habitat and Nepal Academy of Science and Technology have been brought on board, which will put the implementation into speedy mode with higher efficacy. | The project has met the plantation targets. Ecosystem site assessments with detailed designs and cost estimates have been completed. EbA resource persons have been prepared to deliver the EbA capacity-building training to municipal staff, political leaders, communities, and KVDA. EbA capacity-building resources have been prepared and are ready to use during the training. Research work has gained pace in technical support from the Nepal Academy of Science and Technology. Activities under outcome ONE have made progress in action with technical assistance from UN-Habitat. The Project Steering Committee meeting held on the 17th of March 2025 approved the budget and plan for 2025/26, extended the project duration until March of 2027 for the time required to implement activities under outcome 3. | To implement the project as planned and endorsed by Project Steering Committee. | 2025/26 | Project Management Unit/KVDA |
| Yo |  |  |  |  |  |

High Risk (H): There is a probability of greater than 75% that assumptions may fail to hold or materialize, and/or the project may face high risks. Significant Risk (S): There is a probability of between 51% and 75% that assumptions may fail to hold and/or the project may face substantial risks. Moderate Risk (M): There is a probability of between 26% and 50% that assumptions may fail to hold or materialize, and/or the project may face only modest risks. Low Risk (L): There is a probability of up to 25% that assumptions may fail to hold or materialize, and/or the project may face only modest risks.

# 5 Amendment - GeoSpatial

Project Minor Amendments

Minor amendments are changes to the project design or implementation that do not have a significant impact on the project objectives or scope, or an increase of the GEF project financing up to 5% as described in Annex 9 of the Project and Program Cycle Policy Guidelines. Please tick each category for which a change occurred in the fiscal year of reporting, and provide a description of the change that occurred in the textbox. You may attach supporting documents as appropriate

## 5.1 Table A: Listing of all Minor Amendments (TM)

| Minor Amendments | Changes |
| --- | --- |
| Results Framework: | No |
| Components and Cost: | No |
| Institutional and implementation arrangements: | No |
| Financial Management: | No |
| Implementation Schedule: |  |
| Executing Entity: | No |
| Executing Entity Category: | No |
| Minor project objective change: | No |
| Safeguards: | No |
| Risk analysis: | No |
| Increase of GEF financing up to 5%: | No |
| Location of project activity: | No |
| Other: | No |

Minor amendments

Implementation of activities under Outcome 1 (all activities) to be implemented with technical assistance from UN-Habitat Nepal from 15 July 2024 to 31 December 2025. Activities under Output 2.1 (Outcome 2) will be implemented in collaboration Nepal Academy of Science and Technology (NAST) from July 2024 to December 2025. Activities under Output 2.2 and 2.3 (Outcome 2) will be implemented from July 2024 to December 2025. And, activities under Outcome 3 will be implemented from July 2024 to March 2027.

## 5.2 Table B: History of project revisions and/or extensions (TM)

| Version | Type | Signed/Approved by UNEP | Entry Into Force (last signature Date) | Agreement Expiry Date | Main changes introduced in this revision |
| --- | --- | --- | --- | --- | --- |

GEO Location Information:

The Location Name, Latitude, and Longitude are required fields insofar as an Agency chooses to enter a project location under the set format. The Geo Name ID is required in instances where the location is not exact, such as in the case of a city, as opposed to the exact site of a physical infrastructure. The Location & Activity Description fields are optional. Project longitude and latitude must follow the Decimal Degrees WGS84 format, and Agencies are encouraged to use at least four decimal points for greater accuracy. Users may add as many locations as appropriate. Web mapping applications such as OpenStreetMap or Geo Names use this format. Consider using a conversion tool as needed, such as https://coordinates-converter.com. Please, see the Geocoding User Guide by clicking here

| Location Name | Latitude | Longitude | GEO Name ID | Location Description | Activity Description |
| --- | --- | --- | --- | --- | --- |
| Nagdaha wetland ecosystem | 27.62456 | 85.33331 |  | Nagdaha lake ecosystem is located in Lalitpur Metropolitan City. Ward no 24. Dhapakhel in the Kathmandu Valley. |  |
| Chyasindole forest ecosystem | 27.757161 | 85.337433 |  | Chyasindole forest ecosystem lies in Budhanilkantha municipality at Kathmandu Valley. |  |
| Nilbarahi forest ecosystem | 27.697589 | 85.396353 |  | Nilbarahi forest lies in Madhyapur Thimi municipality at Kathmandu Valley. |  |
| Conversation pond ecosystem construction site | 27.762642 | 85.364342 |  | The conservation pond ecosystem construction site is located in Budhanilkanth municipality (wards no 13 and 2) |  |
| Roadside tree ecosystem (plantation) sites | 27.674533 | 85.397511 |  | The sites are located Chardobato intersection in Madhyapur Thimi municipality to Suryabinayak in Suryabinayak municipality |  |
| Duwakot roadside tree ecosystem (plantation site-1) | 27.68105 | 85.409894 |  | It is located in Changunarayan municipality |  |
| Jhaukhel roadside tree ecosystem (plantation site) | 27.696083 | 85.428658 |  | It is located in Changunarayan municipality |  |
| Balkumari Bishnubhir community forest ecosystem (plantation site) | 27.67763 | 85.384388 |  | It is located in Madhyapur Thimi municipality |  |
| Rudreshwor Mahadev temple area roadside tree ecosystem (plantation site) | 27.720544 | 85.342777 |  | It is located in Kathmandu Metropolitan City ward no 7 |  |
| Nikoshera roadside tree ecosystem (plantation site) | 27.086997 | 85.393863 |  | It is located in Madhyaapur Thimi municipality |  |
| Duwakot roadside tree ecosystem (plantation site-2) | 27.687238 | 85.41245 |  | It is located in Changunarayan municipality |  |
| Byasi to Jhaukhel roadside tree ecosystem (plantation site) | 27.684183 | 85.430197 |  | It is located in Changunarayan municipality |  |
| Sainik Pratisthan to Jhaling roadside ecosystem (tree plantation site) | 27.683858 | 85.446411 |  | It is located in Changunarayan municipality |  |
| Suryabinayak administrative building roadside tree ecosystem (tee plantation site) | 27.664544 | 85.404844 |  | It is located in Suryabinayak municipality |  |
| Nakkhukhola corridor roadside tree ecosystem (plantation site) | 27.664972 | 85.301680 |  | It is located in Lalitpur Metropolitan City |  |
| Bhootkhel urban open space ecosystem | 27.763980 | 85.328422 |  | It is located in Tokha Municipality |  |
| Shiva Batika Urban Open Space Ecosystem | 27.705141 | 85.404738 |  | It is located in Changunarayan Municipality |  |
| Bagmati river corridor roadside tree ecosystem (plantation site) | 27.717977 | 85.380948 |  | It is located in Gokarneshwor Municipality |  |
| Shanti Danda urban open space, roadside tree ecosystem (plantation site) | 27.710557 | 85.502576 |  | It is located in Changunarayan Municipality |  |
| Shree Balkumari Secondary School eba intervention (public school site) | 27.630263 | 85.320502 |  | It is located in Lalitpur Metropolitan City |  |
| Shree Aadarsha Saul Secondary School eba intervention (public school site) | 27.632827 | 85.303780 |  | It is located in Lalitpur Metropolitan City |  |
| Shree Patan High School eba intervention (public school site) | 27.678333 | 85.321375 |  | It is located in Lalitpur Metropolitan City |  |
| Shree Janapremi Primary School eba intervention (public school site) | 27.672447 | 85.361747 |  | It is located in Madhyapur Thimi Municipality |  |
| Shree Jalupa Secondary School eba intervention (public school site) | 27.748747 | 85.318683 |  | It is located in Tokha Municipality |  |
| Shree Chandeshwory Secondary School eba intervention (public school site) | 27.771441 | 85.329047 |  | It is located in Tokha Municipality |  |
| Shree Kalidevi Secondary School eba intervention (public school site) | 27.788922 | 85.311463 |  | It is located in Tarakeshwor Municipality |  |
| Shree Janauddhar Secondary School eba intervention (public school site) | 27.762544 | 85.365438 |  | It is located in Budhanilkantha Municipality |  |
| Shree Janajagrity Secondary School eba intervention (public school site) | 27.747355 | 85.376597 |  | It is located in Budhanilkantha Municipality |  |

Please provide any further geo-referenced information and map where the project interventions is taking place as appropriate. *

<p>N/A</p>

Additional Supporting Documents:

| Filename | File Uploaded By | File Uploaded At |  |
| --- | --- | --- | --- |
| Annex_1_Beneficiary_2024_25.docx | Executing Agency |  | Download |
| Annex_2_Cofinance_PIR_2024_25.xls | Executing Agency |  | Download |
| Annex_3_Stakeholder Engagement_2024_25.xlsx | Executing Agency |  | Download |
| Annex_4_Project Stakeholder Plan_CRM_2025.docx | Executing Agency |  | Download |
| Annex_5_Gender response_PIR_2024_25.docx | Executing Agency |  | Download |
| Annex_6_HH list_EbA.xlsx | Executing Agency |  | Download |
| Annex_7_ESM Framework-Madhyapur Municipality-Nilbarahi.docx | Executing Agency |  | Download |
| Annex_8_ESM Framework-Tokha Municipality-2&6 Open Space & Park.docx | Executing Agency |  | Download |