PROJECT IMPLEMENTATION REPORT (PIR)

for the project:

Conservation and Sustainable use of Liberia’s Coastal Natural Capital

FY25

July 1, 2024 – June 30, 2025

(Year 5)

Executing Partners

| Project Information |  |  |  |
| --- | --- | --- | --- |
| Project Title: | Conservation and Sustainable Use of Liberia’s Coastal Natural Capital |  |  |
| Country(ies): | Liberia | GEF ID: | 9573 |
| GEF Agency(ies): | Conservation International | Duration In Months: | 78 months |
| Executing Agency(ies): | The Environmental Protection Agency (EPA) CI-Liberia | Actual Implementation Start Date: | February 1, 2020 |
| GEF Focal Area(s): | Biodiversity and Land Degradation | Expected Project Completion Date: | July 31, 2026 |
| GEF Grant Amount: | US$ 3,944,220 | Expected Financial Closure Date: | January 31, 2027 |
| Expected Co-financing: | US$ 11,194,248 | Date of Last Steering Committee Meeting: | Feb 10, 2025 |
| Co-financing Realized as of June 30, 2025: | US$ 9,910,196 | Mid-Term Review-Planned Date: | October 1, 2022 |
| Date of First Disbursement: | February 1, 2020 | Mid-Term Review-Actual Date: | November 23, 2022 |
| Cumulative disbursement as of June 30, 2025: | US$ 2,457,350 | Terminal Evaluation-Planned Date: | December 1, 2025 |
| PIR Prepared by: | David D. Dennis, Solomon C. Carlon, Joseph Moinsema, and Roger Emmou | Terminal Evaluation-Actual Date: | TBD |
| CI-GEF Project Manager: | Charity Nalyanya Laureen Cheruiyot | CI-GEF Finance Lead: | Susana Escudero Shannon Wiecks |

The CI-GEF Project Agency Project Implementation Report (PIR) is composed of seven sections:

Section I:    General Project Status Summary: provides a brief summary of the project as well as a table summarizing the trend on implementation progress rating, development objective rating, and overall project risk rating;

Section II:   Project Performance: describes the progress made towards (a) achieving the project objective and outcomes since the start of the project and (b) delivery of outputs and implementation of activities as well as recommendations to improve the project performance, when needed;

Section III:  Key Risks Status and Rating: describes the progress made towards managing and mitigating project risks, the project risks mitigation rating reassessment as needed, as well as recommendations to improve the management of project risks;

Section IV:  Project Environmental and Social Safeguards Implementation Status and Rating: describes the progress made towards

complying with the Environmental & Social Safeguards and the Plans prepared during the PPG phase, the safeguard plans implementation rating, as well as recommendations to improve the project safeguards;

Section V:  Project Implementation Experiences and Lessons Learned: describes the experiences learned by the project managers and the lessons learned through the process of implementing the project; and

Section VI: Project Geocoding: documents the precise and specific geographic location(s) of activities supported by GEF

investments based on information available in Project Document.

Section VII: Minor Amendment: describes the changes to the project design or implementation that do not have significant impact on the project objectives or scope, or an increase of the GEF project financing up to 5%.

SECTION I: GENERAL PROGRESS STATUS SUMMARY

SUMMARY OF RATINGS AND TRENDS

| PROJECT PART | PRIOR FY24 PROGRESS RATING | CURRENT FY25 PROGRESS RATING | RATING TREND |
| --- | --- | --- | --- |
| DEVELOPMENT OBJECTIVE (OBJECTIVE AND OUTCOMES) RATING | HS | S | Improving |
| IMPLEMENTATION PROGRESS (OUTPUTS AND ACTIVITIES) RATING | HS | S | Improving |
| OVERALL PROJECT RISK RATING | L | L | Unchanged |

# SECTION II: PROJECT PERFORMANCE

This section describes the progress made since the start of the project towards achieving the project objective and outcomes, the implementation progress rating of the project, as well as recommendations to improve the project performance. This section is composed four parts:

a. Progress towards Achieving Project Expected Objective: this section measures the likelihood of achieving the objective of the project

b. Progress towards Achieving Project Expected Outcomes (by project component)

c. Overall Project Results Progress Rating, and

d. Recommendations for improvement

## a. Progress towards Achieving Project Objective and Outcomes (Development Objective):

This section of the report assesses the progress in achieving the objective of the project.

| PROJECT OBJECTIVE: | To improve conservation and sustainable use of Liberia’s coastal natural capital by mainstreaming the value of nature into Liberia’s development trajectory |
| --- | --- |

| OBJECTIVE INDICATORS | END OF YEAR INDICATOR STATUS | PROGRESS RATING | COMMENTS/JUSTIFICATION |
| --- | --- | --- | --- |
| Indicator a: Number of national development policy instruments explicitly incorporating Natural Capital Accounting (NCA) Target a: At least five (5) national development policy instruments explicitly incorporating Natural Capital Accounting (NCA) (Tied to Outcome Target 1.1a) | Three (3) national development policy instruments explicitly incorporating NCA, namely: - ARREST Agenda for Inclusive Development (AAID), - Nationally Determined Contributions (NDC 2.0) - County Development Agendas (CDAs) | IS | Based on the project’s objective of mainstreaming Natural Capital Accounting (NCA) into at least five national policies, progress has been made with three policies already incorporating the concept of coastal NCA, even if not using that exact terminology. These include Pillar V of the ARREST Agenda for Inclusive Development (AAID), which focuses on environmental sustainability and integrates NCA concepts to assess key indicators such as the economic contribution of forests, including mangroves. In addition, the updated Nationally Determined Contributions (NDC 2.0) and the County Development Agendas (CDAs) of two coastal counties have also integrated coastal natural capital considerations. To further strengthen this process, OIKO Consultancy is building the capacity of 50 Government of Liberia technicians (25) and policymakers (25) to enhance their ability to mainstream NCA concepts into national development policies, including the establishment of a Mangrove Account. |

This part of the report assesses the progress towards achieving the outcomes of the project.

| COMPONENT NO. / TITLE - OUTCOME NO./NAME | OUTCOMES TARGETS/INDICATORS | END OF PROJECT INDICATOR TARGET | END OF YEAR INDICATOR STATUS | PROGRESS RATING | COMMENTS/JUSTIFICATION |
| --- | --- | --- | --- | --- | --- |
| Component 1: Natural Capital Accounting (NCA) in Coastal Ecosystems |  |  |  |  |  |
| Outcome 1.1: Decision-making improved in coastal ecosystem governance by mainstreaming natural capital accounting (NCA) into the Government of Liberia (GOL) development strategy, policy, and planning | Outcome Indicator 1.1.a: Number of natural capital accounts established and embedded in key government policies and plans | At least one natural capital account (mangroves) established and embedded in at least five (5) key government policies and plans | Zero (0) natural capital accounts are embedded in key government policies and plans; the project is in progress towards achieving the outcome indicator. | IS | The project focused on five priority natural capital accounts: Ecosystem Extent, Ecosystem Condition, Ecosystem Services Flow (including crop provisioning, wood provisioning, fisheries resources, climate regulation, soil erosion control, and coastal protection), Monetary Assets, and Thematic Accounts (biodiversity and species). Despite initial progress on establishment of a Mangrove Account, there were substantial challenges related to the withdrawal of the Moore Center of Science (MCS) which caused a major delay on achieving this target. However, a consortium of firms led by OIKO consultancy has been contracted and is conducting capacity building toward the establishment of a Mangrove Account for Liberia. As capacity building session have commenced, development of NCA Roadmap and establishment of a Mangrove Account for Liberia should be finalized in Feb. 2026. |
|  | Outcome indicator 1.1.b: Number of government officials and other relevant stakeholders trained on the technical aspects of NCA | At least fifty (50) (10 women and 40 men) government officials and other relevant stakeholders trained on the technical aspects of NCA | Zero (0) | IS | Throughout FY25, most efforts have been focused on replacement of the MCS to lead component one of the project. However, OIKO consultancy began preparations for training in FY26 of selected trainees from GoL ministries and agencies. Per the inception report, initial training for technicians will be in earnest while policymakers’ capacity building would follow. |
| Revised Outcome Indicator | Outcome indicator 1.1.c: Number of decision-makers trained on how to use NCA results for the conservation and sustainable use of globally important biodiversity | At least 50 decision-makers trained on how to use NCA results for the conservation and sustainable use of globally important biodiversity. | Zero (0) | IS | OIKO consultancy firm has been contracted to continue capacity building for 25 policy makers trained on how to NCA results for the conservation and sustainable use of globally important biodiversity. Also, 25 technicians are trained on how to collect NCA related data to support natural capital management. However, based on prior trainings conducted, Liberia’s Nationally Determined Contributions (NDCs) incorporated the NCA and its support for Liberia’s recovery; two of the recently developed County Development Agenda (CDAs) and the national development plan known as the ARREST Agenda have mainstreamed the NCA in the chapters on natural resource and environmental management. The trainings and establishment of the account will be concluded by February 2026. |
| Component 2: : Innovative Financing Schemes for Conserving Coastal Natural Capital |  |  |  |  |  |
| Outcome 2.1: Funding sources for sustainable management and restoration of coastal ecosystems increased | Indicator 2.1.a: Financial resources (USD) available for the sustainable management and restoration of coastal ecosystems | Financial resources for the sustainable management and restoration of coastal ecosystems increased by 50% (USD 2.5 million over the lifetime | To-date: In FY25 40% The Blue Oceans Program (US$2.2M) expansion in the NCA landscape. The breakdown is below: FY21: US$ 600,000 (prince Albert II of Monaco FY22: Zero (0) FY23: US$ 185,000 FY24: US$ 40,000 Turing Foundation FY25: US$ 2.2M (Blue Oceans Program expansion) | IS | As of FY25, at least 40% (US$ 2.2M) of funding through the SIDA sponsored BOP expansion in southeastern Liberia to support sustainable management of coastal ecosystems and conduct a national Mangrove inventory. The NCA project will use the Mangrove inventory data in the establishment of a national mangrove account for Liberia. FY24: US 40,000 secured from the Turing Foundation to support mangrove conservation in the Marshall Wetland landscape. FY23: US$ 185,000 was secured from Broadleaf for the development of the Project Identification Note (PIN), Project Opportunity Profile, and feasibility study for carbon project in Marshall and Lake Piso. Also, discussions are ongoing with Proctor and Gamble to fund a blue carbon worth US$ 25 million for 25 years (US$ 1 million p.a.) FY22: Zero (0) FY21: US$ 600,000 was secured from Prince Albert II of Monaco Foundation to support the gazettement of Marshall Wetlands. |
|  | Indicator 2.1.b: Number of revenue streams to support the long-term sustainability of coastal ecosystems | At least two (2) new revenue streams to support the long-term sustainability of coastal ecosystems developed. | To date, three (3) revenue streams: - US$2 million from the World Bank. - US$ 2.2 million from the Blue Oceans Program expanded with an additional | IS | FY25, selection of four sub-grantees to benefit from a small grant program worth up to US$300,000 to support conservation-friendly activities in the project landscape FY24: In addition to the World Bank support, the Blue Oceans Program expansion work that focuses on enhancing the capacity of local women through a Cooperative approach is active in the landscape. FY23: US$ 2 million was secured from the World Bank-supported Liberia Sustainable Fisheries Management Project granting facility to build capacity of local fisherfolks and provide support to Small and Medium Enterprises (SMEs) in coastal areas. |
|  | Indicator 2.1.c: Number of local organizations receiving small grants for coastal conservation | Small grants provided to at least three local organizations | To date, four (4) local organisations have received a small grant for coastal Conservation. These are: - The Nature Compact (TNC): USD - BudGIT Liberia: USD - VADEMCO: USD - BASA Development Initiative (BDI): USD | IS | Since FY22, the Liberia Conservation Action Fund (LCAF) was set up to support small-scale natural resource stewardship projects. To this end, the Small Grant Program has been established to compliment the LCAF through support to local SMEs and CSOs. Consequently, four conservation friendly CSOs are receiving small grant to support conservation initiatives in the project landscape. They include The Nature Compact (TNC) working in Rivercess County, BudGIT Liberia working across Grand Cape Mount County, VADEMCO working across the Western Coastline and BASA Development Initiative (BDI) working in Sinoe on Mangrove reforestation. |
| Component 3: Community Incentives to Conserve and Sustainably Manage Natural Capital in Coastal Ecosystems |  |  |  |  |  |
| Outcome 3.1.: Community-level conservation and sustainable use of coastal resources improved through performance-based payments using conservation agreements | Indicator 3.1.a: Area (hectares) of mangrove ecosystems under protection across Liberia | 11,975 additional hectares of mangrove ecosystems under protection across Liberia. | To date: FY21: 2,449.67 ha FY22: 2,449.67 ha FY23: 2,449.67 ha FY24: 2,449.67 ha FY25: 13,803 ha | IS | Having renewed CAs in the initial six communities, a total of 2,449.67 ha of mangrove ecosystems are still under voluntary protection. Additional hectares of mangroves are set for protection in new Conservation Agreements communities in FY25. Consequently, in FY25, with the addition of three conservation agreements in Rivercess (covering seven communities using a cluster approach), one in Margibi (covering three commnunities), a total of 13,803 ha of mangrove ecosystem under voluntary protection. |
|  | Indicator 3.1.b: Area (hectares) of terrestrial forest ecosystems under sustainable management in coastal areas. | 5,000 additional hectares of terrestrial forest ecosystems under sustainable management in coastal areas. | To date: FY21: 4,159.74 ha FY22: 4,159.74 ha FY23: Zero (0) ha FY24: 4,159.74 ha FY25: 6,110 ha | IS | Having signed additional four CAs in the new communities, a total of 1,950.26 ha has been added to the initial 4,159.74 ha is under voluntary protection. This brings the current total terrestrial forest ecosystems under sustainable management in coastal areas to 6,110 ha. |
|  | Indicator 3.1.c: Income (USD) within coastal and mangrove communities targeted by the project | Income within coastal and mangrove communities targeted by the project improved by 50%. | Zero (0) | IS | A planned endline survey to assess the impact of project implementation on local communities in the project area to provide the data. In addition to the endline survey/assessment, an ongoing nation-wide conservation agreement consultancy will provide the required socioeconomic data on project impact on beneficiaries. The Assessment is set to be finalized in FY26Q1. |

| DEVELOPMENT OBJECTIVE (OBJECTIVE AND OUTCOMES) RATING | JUSTIFICATION |
| --- | --- |
| S | This section’s rating is Satisfactory (HS) because 100% outcomes are under implementation and on schedule. The project has made notable progress in mainstreaming NCA in 3 Policies and capacity-building efforts underway for 25 officials in FY26. Although delays occurred due to the withdrawal of CI's Moore Center of Science in FY24, OIKO Consultancy was contracted to advance work on a Mangrove Account and an NCA roadmap by February 2026. However, this consultancy stretches beyond the November 2025 project end date, raising concerns about the feasibility of the current proposed project end date Innovative financing efforts are advancing strongly, with USD 2.2 million mobilized through the Blue Oceans Program and additional funding from the World Bank and small grants. Discussions with Proctor & Gamble on a long-term blue carbon initiative further strengthen sustainability prospects. At the community level, Conservation Agreements have expanded protection to 13,803 hectares of mangroves and 6,110 hectares of forests, exceeding annual targets. While data on income improvements is pending, upcoming surveys and studies are expected to address this. Overall, financing and conservation agreements are progressing well, while embedding NCA into policies and strengthening institutional capacity are catching up and remain on track. However, given that critical activities such as the Mangrove Account, capacity building, and the endline survey are only just beginning while the project is set to close in November 2025, there is a risk of rushed implementation. The project team should urgently re-evaluate the timeline and activity feasibility and re-engage CI-GEF to request a No-Cost Extension (NCE) to ensure the project completion date is realistic and the pending activities are implemented meaningfully, resulting in lasting impact. |

## b. Progress towards Implementation Progress (Delivery of Outputs and Implementation of Activities)

This part of the report assesses the progress towards delivery of outputs and implementation of activities planned for the year.

## Progress: Information on progress outcomes of project implementation activities

Based on implementation efforts throughout FY25, the project has been able to report on the following outcomes per component. Component 1 - Capacity building for 50 government officials (technicians and policymakers) initiated. The same training will lead ot the development of a Roadmap for NCA integration and establishment of a Mangrove Account for Liberia. - Through the Blue Oceans Program (BOP) with support from the NCA PMU, a National Managrove Inventory has been launched and results will be used for the establishment of a Mangrove Account. - A policy assessment has been conducted which identified at least three (3) policies at national level that integrates the coastal natural resources (coastal natural capital) concept. The policies include Arrest Agenda for Inclusive Development (AAID Pillar V), Two Coastal Counties’ County Development Agenda (CDAs) and the national determined contributions (NDCs 2.0). Component 2 - Efforts have been made through a consultancy to link the The Liberia Conservation Fund to the GEF NCA Small Grant Program (Liberia Conservation Action Fund/LCAF) as a suatinable financing stream. Consequently, a Roadmap to link the LCAF to the LCF developed and validated by stakeholders. - Capacity building conducted for GoL staff and other stakeholders including small grant beneficiaries with respect to different funding mechanisms for sustainable coastal ecosystem conservation (e.g. a Mangrove Conservation Fund as a Trust Fund to support management Mangrove Ecosystems). - Four Local Conservation orgranizations vetted and provided small grant to support conservation-friendly activities across the project landscape. Component 3 - Ten (10) Conservation Agreements signed and are implemented in Grand cape Mount, Margibi, Grand Bassa and Rivercess counties along the coastline of Liberia. - A nation-wide conservation agreement assessment conducted to evaluate approaches to inform implementation. This activity was simultaneously conducted with FDA and UNDP as the government had expressed a need to develop a national framework to guide conservation agreements across Liberia.

Challenges: Information on challenges of project implementation activities

Despite significant progress made toward implementation throughout FY25, the following challenges were experienced. They include: - Delay in completing several activities due to staff turnover in FY22 and FY23. This led to a request for no cost extension (NCE) which was approved to cover the period Jul. 2025 – Feb. 2026. - Recruitment of a consultancy firm with the right profile to conduct capacity building for GoL officials and establish a Mangrove Account for Liberia. The profile sorted was a firm, if international, with a local partner (Liberian) and if local, vice versa. - Selection of qualified local conservation enterprises to receive small grant. Many institutions did not meet certain requirement but a clear mitigation strategy has been designed to enhance capacity for both technical and financial management of the grant. - Finding snergies with the FDA, UNDP and other partners on a synchronized framework for conservation agreements.

| IMPLEMENTATION PROGRESS (DELIVERY OF OUTPUTS AND IMPLEMENTATION OF ACTIVITIES) RATING | JUSTIFICATION |
| --- | --- |
| S | This section is rated Satisfactory(HS) because 100% of the outputs are under implementation/on schedule. The project has made tangible progress, particularly through the ten conservation agreements now being implemented across four coastal counties. These agreements have proven to be an effective mechanism for engaging communities, promoting conservation-friendly practices, and laying the groundwork for a national framework on conservation agreements in Liberia. In addition, strong strides in sustainable financing such as linking the Liberia Conservation Fund with the Small Grants Program, demonstrate the project’s capacity to secure long-term impact. Given these achievements and the momentum built across components, it is highly likely that all planned outputs will be delivered before the project’s completion in FY26. In conclusion, the project is progressing well. However, critical activities such as the Mangrove Account, NCA roadmap, and endline survey will likely extend beyond the November 2025 implementation end date. To avoid rushed delivery and ensure lasting impact, the project team should urgently reassess timelines and request a No-Cost Extension (NCE) from CI-GEF. |

## c. Recommendations

| CORRECTIVE ACTION(S) | RESPONSIBLE PARTY | DEADLINE |
| --- | --- | --- |
| - The project team should urgently assess whether pending activities can realistically be completed by the November 30, 2025 deadline and, if not, submit a request to CI-GEF for a No-Cost Extension (NCE): Given that several critical activities, such as the establishment of the Mangrove Account, capacity building for officials, and finalization of the endline socioeconomic survey, are only just starting while the project is set to close in November 2025, there is a significant risk of rushing implementation. | CI-Liberia, CI-GEF | October 6 2025 |
| - Accelerate NCA capacity building: Prioritize the training of government officials, technicians, and policymakers to ensure that by the end of FY26, the Mangrove Account is fully developed and integrated into national planning frameworks. | CI-Liberia, EPA | November 2025 |
| - Prepare a sustainability and exit strategy well ahead of project closure in December 2025, ensuring clear ownership, funding pathways, and continued operation of project interventions beyond the project’s lifespan. | CI-Liberia, EPA | November 2025 |
| - To highlight key achievements, challenges, and recommendations from the project, develop knowledge management, challenges, recommendations and lessons learnt report that will be shared with all partners and uploaded on the CI-GEF project page | CI-Liberia, EPA | November 2025 |
| - During the remaining execution period, uphold GEF visibility by consistently acknowledging the funding source in all events and ensuring the GEF logo is displayed on communications materials, reports, and presentations, in line with the GEF visibility policy. | CI-Liberia, EPA | February 2026 |

# SECTION III: PROJECT RISKS STATUS AND RATING

## a. Progress towards Implementing the Project Risk Mitigation Plan

This section describes the activities implemented to manage and reduce high, substantial, modest, and low risks of the project. This section has three parts:

a. Ratings for the progress towards implementing measures to mitigate project risks and a project risks annual reassessment

b. Recommendations for improving project risks management

Progress towards Implementing the Project Risk Mitigation and Plan Project Risks Annual Reassessment

| PROJECT RISKS | PRODOC RISK DEFINITION AND MITIGATION MEASURE | MITIGATION MEASURES IMPLEMENTATION PROGRESS | PRODOC RISK RATING | CURRENT FY25 RISK RATING |
| --- | --- | --- | --- | --- |
| CONTEXT |  |  |  |  |
| Risk 1: Insufficient political will to adopt and mainstream NCA | Work on developing NCA will be done in close collaboration with government counterparts to promote buy-in. | The NCA project is socialized among key government institutions and key government technicians. Policymakers are also involved in the implementation of the project | Moderate (M) | Low (L) |
|  | Project delivery will emphasize capacity-building within relevant government agencies. | Five (5) trainings held where 30 government trainees (24 men and 6 women) from MFDP, EPA, FDA, MoA, LISGIS, and Liberia hydrological Services attended |  |  |
|  | Continued consultations will solicit input and cultivate support on an ongoing basis. | Consultations were held with 24 Institutions including Government: 11; Private sector: 1; Academia: 2; NGOs: 4 and local communities: 6 where a total of 522 (375 men and 147 women) attended. |  |  |
|  | The evolution of the NCA framework will be guided by Government priorities. | Five priority natural capital accounts and six priority policies were identified by government |  |  |
|  | Demonstrate to the Ministry of Finance and Development Planning (MFDP) that NCA will better capture Liberia’s economic status and trends and help attract investor and donor support for sustainable development. | Ministry of Finance and Development Planning (MFDP) is represented at the Project Steering Committee (PSC) and Technical Advisory Committee (TAC). A National Strategy and Action Plan for the implementation of Natural Capital Accounting in Liberia was produced with the Government of Liberia including MFDP. |  |  |
| Risk 2: Political instability undermines work with government | - Investment in building and embedding technical expertise in government has proven effective ever since 2004, regardless of changes in administration. This project will devote explicit attention to applying this lesson, which also serves as means to mitigate the impact of the first risk listed. | - A total of 28 (23 men and 5 women) government officials and other relevant stakeholders were trained on the technical aspects of NCA. | Low (L) | Moderate (M) |
| EXECUTION |  |  |  |  |
| Risk 3: Investor/donor confidence insufficient for adequate contributions to sustainable financing mechanisms | - Careful site/intervention selection under the project to maximize demonstration impact. | - All NCA sites were included as sites for the World Bank funded project | Low (L) | Low (L) |
|  | - Build on previous successes with small grants to scale up. | The LCAF small grant appraisal committee has been operationalized and will receive support from UNDP Small Grants Programme in Liberia |  |  |
|  | Align project with wider national sustainable conservation finance efforts. | In the development of a national strategy and action plan for NCA discussions were held with officials from MFDP who identified Climate change and climate finance as key priorities |  |  |
| Risk 4: Enterprise development fails or is not adopted by local Communities | - Leverage the proven viability of existing conservation-friendly enterprises. | Final report on value-chain analysis of conservation-friendly enterprises was produced which will inform the promotion of conservation friendly enterprises in project target sites. | Moderate (M) | Moderate (M) |
|  | - Focus community-based development on activities with which they already are familiar (e.g., agriculture, fisheries). |  |  |  |
| Risk 5: Community members are not interested in behavior change through commitments in Conservation Agreements (CAs) | Apply Rights-Based Approach to ensure appropriate communication, engagement, and participation processes, including Free, Prior, and Informed Consent (FPIC). | In all 21 engagements held, prior information was provided, and consent sought from all participants to renew conservation agreements. | Low (L) | Low (L) |
|  | Cultivate local champions (through Community-Based Organizations, traditional leadership, and local NGOs) to act as intermediaries | Traditional leaders were included in the design and negotiations of Conservation Agreement Committees. They lead key engagements during negotiations. |  |  |
|  | Conduct site-level feasibility assessments to identify local appetite for participation in the project. | Site feasibility assessments were completed in Lexington, Panama, Down the mangrove, Seebeh, Timbo Kru, Dioh town, and Neegba, Grand Cess, and Picnicess in Southeast Liberia landscape and Nyangba, Bleewein, Mandoe, Falie, Sarwein and Bendu in Northwest Liberia landscape |  |  |
|  | Tailor Conservation agreement (CA) benefit packages to address local needs and priorities. | CA benefits are always tailored to address local needs and priorities including green jobs, access to credit, cold storage, Farming tools, sustainable fishing gears |  |  |
| Risk 6: Stakeholder Other stakeholders such as local governments are reluctant to share planning and management responsibilities with communities | Consult and engage local government as key stakeholders in planning and executing CA initiatives. | Local government authorities including county authorities, District commissioners and town chiefs are always consulted on land use planning | Moderate (M) | Low (L) |
|  | Ensure that capacity-building efforts include local government. | Refresher training was provided to 79 Frontline Conservationists and all six communities were sensitized on Liberia’s National standards for participatory land use planning. |  |  |
|  | Emphasize the role of local government in monitoring and enforcement of relevant laws and regulations. | 79 local frontline Conservationists participated in monitoring compliance with conservation agreements in six communities that have already signed the agreements. Also, the District and County Superintendents were involved in the monitoring of field activities. |  |  |
|  | Build awareness within local government of the advantages of working toward a green economy. | Local government representatives were sensitized on the contribution of Liberia’s National standards for participatory land use planning towards a green economy. |  |  |
| Risk 7: Institutional competition with respect to housing a national conservation agreement program and its associated funding streams | Conduct national program design in collaboration with a full range of stakeholder agencies. | Multi-stakeholder participation was prioritized in the development of a National Strategy and Action Plan (NSAP) for the implementation of NCA in Liberia | Moderate (M) | Moderate (M) |
|  | Jointly work toward a clear definition of roles and responsibilities for all concerned stakeholders. | ToRS and SOPs for operationalization of the LCAF has been developed and an appraisal committee established. |  |  |
|  | Build on existing structures and forums for interagency coordination and collaboration (REDD+ working group; LCF; etc.). | The PMU participated in the Environmental Sector Working Group., and PSC meetings |  |  |
| Risk 8: Impacts of climate change undermine project outcomes | Select sites that offer the maximum likelihood of weathering climate change impacts given project support. | The PMU is collaborating with the UNDP project entitled, “Mapping Nature for People and Planet in Liberia.” | Substantial (S) | Low (L) |
|  | Prioritize early action on maintaining green infrastructure that buffers climate change impacts. | The NCA team participated in the inception workshop with the UNDP’s project, “Mapping Nature for People and Planet in Liberia,” which aims to map ‘Essential Life Support Areas’ (ELSAs), where actions to protect, manage and restore nature can conserve critical biodiversity, mitigate climate change, and provide humans with essential ecosystem services, such as carbon storage, food, freshwater provisioning, and disaster risk reduction. |  |  |
|  | Ensure that land - and resource use planning takes into consideration climate change impacts. | During the policy assessment, one of the priority policies that was selected is the 2018 National Policy and Response Strategy on Climate Change. To that end, the NCA project team is collaborating with UNDP on mapping nature for people and planet in Liberia |  |  |
| Risk 9: Implementation capacity is inadequate. | Build-in extensive training opportunities | A total of 14 government staff (12 men and 2 women) participated in different meetings and online workshop. Also, 79 Frontline Conservationists were trained on conservation related issues. | Moderate (M) | Moderate (M) |
|  | Design implementation processes such that they contribute to capacity-building | - A National Strategy and Action Plan (NSAP) for the implementation of NCA in Liberia - Liberian Scientists were selected and trained on various field survey tools for collecting primary data on relevant to ecosystem services, biodiversity, and condition indicators. - NCA capacity building plan |  |  |
|  | Rely on local partners to ensure cost-effectiveness | All the successful consultancy firms had local consultants in their team |  |  |
|  | Align with complementary programs to design mutually reinforcing investments (e.g., LFSP, WA -BiCC) | The NCA was aligned with: - UNDP’s project, “Mapping Nature for People and Planet in Liberia - US$ 2 Swedish funded project on promoting resilient Livelihoods and mangrove conservation in Southeast Liberia - US$ 2 million World Bank project on Liberia Sustainable Fisheries Management - All the listed funding streams are current and very active |  |  |
| Risk 10: Impacts of COVID-19 Baseline risk rating: High | Revise the work plan to identify activities that can be undertaken remotely | Work plan was not revised | High (H) | Low (L) |
|  | Follow and abide by the Government regulations and measures to combat the COVID-19 pandemic | Handwashing and use of sanitizers was undertaken in all local communities. |  |  |
|  | Create awareness of the COVID-19 pandemic and provide Personal protective equipment (PPE) to project communities | Awareness on the importance of handwashing and use of sanitizers was undertaken in all local communities. |  |  |
| NEW Risk 11: Staff turnover affects timely implementation of the project | This is a new risk. Activity 1: Expedite recruitment and on-boarding of replacement staff. | New Project Manager and M&E Manager recruited and on-boarded | N/A | Low (L) |
| NEW Risk 12: Delay in transporting samples to laboratories impacts smooth implementation. | This is a new risk. Activity 1: Ensure that specimens collected are transported to laboratories for analysis and reporting. | Engagements with DHL to help transport specimens is ongoing. A service contract has been signed with DHL to expediate the transport. | N/A | High (H) |
|  | Keep the government focal point for the NCA project abreast with every aspect of project implementation so that he can act as the Project Manager in the interim | A high-level meeting was held between CI and EPA Leadership. |  |  |

| OVERALL RISK RATING | JUSTIFICATION | RISK RATING TREND |
| --- | --- | --- |
| L | The Risk Rating for FY25 is Low. This rating is similar to FY24 In FY25, 70% of the risks were rated Low and 10% of the risks were rated High. This is the same rating as FY24. The mitigation measures in place have been effective and the project teams continue monitoring. The challenge with the shipment of specimens was resolved and testing of the samples collected was completed. | Unchanged. |

## Recommendations

| MITIGATION AND CORRECTIVE ACTION(S) | RESPONSIBLE PARTY | DEADLINE |
| --- | --- | --- |
| N/A | N/A | N/A |

SECTION IV: PROJECT ENVIRONMENTAL AND SOCIAL MANAGEMENT IMPLEMENTATION STATUS AND RATING

This section of the PIR describes the progress made towards complying with the approved ESMF plans, as well as recommendations to improve the implementation of the ESMF plans, when needed. This section is divided into six parts:

a. Progress towards complying with the CI-GEF Project Agency’s ESMF

b. Information on Progress, challenges and outcomes on stakeholder engagement

c. Information on the progress towards achieving gender sensitive measures/targets

d. Lessons learned and Knowledge Management products developed and disseminated

e. Overall Project ESMF Implementation Rating

f. Recommendations

a. Progress towards complying with the CI-GEF Project Agency’s ESMF

| MINIMUM ESMF INDICATORS | PROJECT TARGET | END OF YEAR STATUS | CUMULATIVE STATUS | PROGRESS RATING | COMMENTS/JUSTIFICATION |
| --- | --- | --- | --- | --- | --- |
| ACCOUNTABILITY AND GRIEVANCE MECHANISM |  |  |  |  |  |
| - Number of conflict and complaint cases reported to the project’s Accountability and Grievance Mechanism | No target set at CEO endorsement | 10 | Total: 30 complaints To date, FY24: 20 complaints FY25: 10 complaints | IS | A total of 10 complaints were captured by the PMU. These complaints were in two parts: A) Mobile Money payments delay in Q3 and Q4, and; B) Frontline Conservationists alerted the PMU that there was an outstanding balance of one stipend payment for patrol in March 2024. However, after a thorough review of payment records, this was resolved with the communities. |
| - Percentage of conflict and complaint cases reported to the project’s Accountability and Grievance Mechanism that have been resolved. | No target set at CEO endorsement | 100% | 100% | IS | 100% percent of cases reported to the PMU were either resolved at PMU level or escalated to the country office through our country level grevience committee. Through FY25, no NCA related complaint reached the CI Ethics Hotline. |
| GENDER MAINSTREAMING |  |  |  |  |  |
| - Number of men and women that participated in project activities (e.g. meetings, workshops, consultations) | No target set at CEO endorsement To avoid double counting, the project maintains or does not count previous participants. | 1,639 people (967 men and 672 women) 1,117 (628 men and 489 women) were new participant. Therefore, 1,117 is the end-year status of new participants. | 2,695 (1,636 men and 1,059women) | IS | So far, 2,695 (1,059/39% women and 1,636/61% men) have been involved in the project activities such as workshops, meetings, and consultations (cumulative). Progress (breakdown per year): FY21: 362 (73 women and 289 men) FY22: 683 (338 women and 345 men) FY23: 423 (129 women and 294 men) FY24: 110 (30 women and 80 men) FY25: 1,117 (489 women and 628 men) |
| - Number of men and women that received benefits (e.g. employment, income generating activities, training, access to natural resources, land tenure or resource rights, equipment, leadership roles) from the project | No Target was set at CEO Endorsement Target set at the implementation phase: At least 6,050 direct beneficiaries. [2,904 female (48%) and 3,146 Male (52%) | 1,257 (712 men and 545 women) are all new beneficiaries. | To date, 2,776 (1,583 men and 1,193 women), but 1,257 (712 men and 545 women) are new beneficiaries. To avoid double counting. | IS | So far, a total of 2776 (1583/57% men and 1193/43% women) Progress (break down of direct beneficiaries per year): FY21: 260 (197 men and 63 women) FY22: 671 (329 men and 342 women) FY23: 162 (146 men and 16 women) FY24: 426 (199 men and 227 women) FY25: 1,257 (712 men and 545 women) There is a massive increase in project beneficiaries in FY25 due to active implementation as a result of signing four new CAs using a community cluster approach, recording trainings conducted by consultants, in-kind grant beneficiaries from government partners and demographic data of each community or cluster of communities covered by the 10 active conservation agreements being implemented. |
| - Number of strategies, plans (e.g. management plans and land use plans) and policies derived from the project that include gender considerations (this indicator applies to relevant projects) | No Target was set at CEO Endorsement. Target set at the implementation phase: At least five (5) strategy documents that include gender considerations (where relevant) generated: at least 1 document generated per year). | 2 documents (A national conservation agreement implementation plan and a National framework for Liberia Conservation Fund | To date, five strategies have either a direct product of the project or have mainstream the project concept. | IS | To date, five strategies have either a direct product of the project or have mainstream the project concept. See PIRs from FY21 to FY24 for reference. For FY25, 2 documents produced, i.e. One (01) – A national conservation agreement implementation plan for livelihood projects in Liberia One (01) – National framework for Liberia Conservation Fund (LCF) implementation in Liberia. |
| - Keep track of the number of men/women demonstrating leadership in project implementation. Responsible party(ies): PMU - Targets: At least 150 people (105 Men and 45 Women) demonstrating leadership in project implementation | No Target was set at CEO Endorsement The target set at the implementation phase: At least 150 people [105 Men (70%) and 45 Women (30%)] demonstrating leadership in project implementation. | 30 (20 men and 10 women) | 155 (110 men and 45 women) | IS | Total number of men & women in leadership roles to-date: 155 (110/71% men and 45/29% women). Break down per year: FY21: 39 (33 men and 6 women); FY22: 27 (10 men and 17 women); FY23: 28 (24 men and 04 women); FY24 31 (23 men and 8 women) and FY25 30(20 men and 10 women). The number of men and women demonstrating leadership roles on the project has increased slightly compared to previous FY due to active intervention in the landscape which include expansion of conservation agreements programs. As a fact, we now have permanent female representative from the FDA to the PSC and more women have been recruited as F.Cs and VSLA beneficiaries. |
| STAKEHOLDER ENGAGEMENT |  |  |  |  |  |
| - Number of government agencies, civil society organizations, private sector, indigenous peoples and other stakeholder groups that have been involved in the project implementation phase on an annual basis | No Target was set at CEO Endorsement Target set at the implementation phase: Cumulatively, at least 50 institutions involved (with representation from Government, CSOs, local communities, Private sector, Media, and Academia). | In FY25, twelve (12) new institutions have been involved in project implementation | To avoid double counting, 55 institutions were involved as outlined below: - Govern ment: 15 - Local commun ities: 18 - Private sector: 2 - NGOs/CSOs: 15 Academi a: 4 Media: 1 | IS | To data and by avoiding double counting, a total of six different stakeholder groups have been engaged on the project. See PIRs from FY21 to FY24 for reference. |
| - Number persons (sex disaggregated) that have been involved in project implementation phase (on an annual basis) | No Target was set at CEO Endorsement. To avoid double- counting, the project follows the target numbers under Activity 1 in the gender mainstreaming plan. | 1,639 people (967 men and 672 women) but 1,117 (628 men and 489 women) were new participant. To avoid double counting. | 2,695 (1, men and 1,198 women) | IS | So far, 2,695 (1,059/39% women and 1,636/61% men) have been involved in the project activities such as workshops, meetings, and consultations (cumulative). Progress (breakdown per year): FY21: 362 (73 women and 289 men) FY22: 683 (338 women and 345 men) FY23: 423 (129 women and 294 men) FY24: 110 (30 women and 80 men) FY25: 1,117 (628 men and 489 women) |
| - Number of engagement (e.g. meeting, workshops, consultations) with stakeholders during the project implementation phase (on an annual basis) | No Target was set at CEO Endorsement. Target set at the implementation phase: At least 175 engagements held by the end of five years (35 engagements per year). | A total of 55 enagements were held. | Cumulatively, 192 engagements conducted. | IS | Total number of engagements to date: 192 enagements Breakdown: FY21: 40 Engagements FY22: 29 Engagements FY23: 22 Engagements FY24: 46 Engagements FY25: 55 Engagements There were several engagements in the NCA landscape, especially during conservation agreement feasibility assessments, negotiations, signing ceremonies, technical advisory committee (TAC) and project steering committee (PSC) meetings in FY25. |
| RESETTLEMENT AND PHYSICAL AND ECONOMIC DISPLACEMENT |  |  |  |  |  |
| - Number of persons whose access to and use of natural resources have been voluntary restricted Target: At least 1100 (Men 700 and Women 400) people’s access to and use of natural resources has been voluntarily restricted |  | 4,564 people (2,868 men and 1,696 women) | To date, a total of 7,027 (4,030 men and 2,997 women) access to natural resources have been voluntarily restricted. However, | IS | TO-DATE: Total of persons with voluntary restricted access to and use of natural resources 7,027 [4,030 male (57%) and 2,997 women (43%)]. The breakdown is provided below of people whose access to mangroves was voluntarily restricted from the following communities where conservation agreements were signed and are being implemented including: - Nyangba: 158 (72 male and 86 female) - Bleewein: 361 (173 male and 188 female) - Sarwein: 198 (83 male and 115) female) - Bendu: 1047 (479 male and 568 female) - Mandoe: 243 (124 male and 119 female) - Falie: 456 (234 male and 222 female) - Charlesville cluster: 1,352 (725 men and 627 women - Rivercess clusters 3,212 (2,143 men and 1,069 women) |
| - Number of persons whose access to and use of natural resources have been involuntarily restricted. | No Target was set at CEO Endorsement. Target set at the implementation phase: Zero (0) males and Zero (0) females have been involuntarily restricted to access and use of natural resources. | 0 | 0 | IS | TO-DATE: Total involuntary restricted persons: Zero (0) FY21: 0 persons. FY22: 0 persons. FY23: 0 persons. FY24: 0 persons. |
| - Percentage of persons who gave their consent for voluntary restrictions Target: 100% of persons involved have given their consent for voluntary restrictions | No Target was set at CEO Endorsement. Target set at the implementation phase: 100% of persons involved have given their consent for voluntary restrictions. | 100% | 100% |  | 100% of communities who signed conservation agreements are committed to voluntary access to certain natural resources, |
| - Percentage of persons who have received compensation for voluntary restrictions. | No Target was set at CEO Endorsement. Target set at the implementation phase: 100% of persons who voluntarily consented to restrictions to access and use of natural resources have received compensation. | 100% | 100% | IS | 100% of persons whose access to resources were voluntarily restricted (7,027) are receiving compensation for voluntary restrictions. FY21 to FY24 2,463 people (1,062 male and 1,216 women) FY25 4,564 people (2,868 men and 1,696 women) |
| - Keep track of the number of persons whose access to and use of natural resources has been involuntarily restricted | No Target was set at CEO Endorsement. Target set at the implementation phase: 100% of persons who have been involuntarily restricted to access and use of natural resources have received compensation. | Zero (0) | 0% | IS | No community access to resources was involuntarily restricted. |

## b. Information on Progress, challenges and outcomes regarding engagement of stakeholders in the project based on the description included in the Stakeholders Engagement Plan

In FY25, the project engaged 14 new institutions through field activities, technical meetings, and joint steering committee sessions. Significant progress was made in strengthening partnerships with government, civil society, academia, the private sector, and local communities. The growing number of communities with signed and implemented conservation agreements further demonstrates broad engagement at community, county, and national levels. Additionally, seven local NGOs were vetted through a rigorous process, resulting in four being selected to receive small grants to support conservation-friendly initiatives. However, challenges were raised by stakeholders regarding CI’s use of electronic payments for transportation reimbursements and field-related expenses. In response, the project is working with mobile service providers, in collaboration with the government and Project Steering Committee, to improve service delivery in remote implementation areas.

## c. Information on the progress towards achieving gender sensitive measures/targets and any intermediate gender result areas as documented at CEO Endorsement/Approval including gender-sensitive indicators contained in the project results framework or gender action plan

For FY25, sex-disaggregated data from project activities showed 1,639 participants (967 men and 672 women), with 1,117 new participants (628 men and 489 women). Gender mainstreaming efforts included separate meetings with men and women for Conservation Agreement negotiations to accommodate women's views and avoid male domination. In addition, each CA community was encouraged to have at least 30% female inclusion in the list of Frontline Conservationists. These meetings were held at a favorable time ad accessible venues and gathering views of women during the negotiations for renewal of conservation agreements. Initially, there was hesitation from local leaders to accept women as frontline conservationists, but with constant awareness and capacity building, women are now part of these groups. Interestingly, based on the approaches employed for Village Savings and Loans Associations (VSLA) and Frontline Conservationist programs, we are seeing signs of more female participation in meetings and overall involvement in project implementation. As for the PSC and the TAC, we now have two permanent women members from their respective institutions, the case of the Forest Development Authority. Based on male domination in project activities, we began to request female participation in programs like the F.Cs patrol and intentionally requested that the chairlady from each community come to every community engagement on the project. Moving into FY26, we want to improve on this approach and request women's participation at all levels of the project.

## d. Lessons learned on the Environmental and Social Management Implementation

- Instead of relying on verbal reminders of the GrievanceRedress Mechanism (GRM) in all meetings, the PMU intentionally created a section dedicated to tracking AGM in the each Conservation Agreement. This has allowed communities to pick up and report issues of concern at our regular engagement. However, as most of the communities are relatively older communities, they handle most issues through the Conservation Agreement Committee (CAC).

- All the contact numbers on the AGM, except for the General Council’s Office (GCO), are from local staff because most of the local communities do not comprehensively understand all the information that a non-local person provides due to differences in dialects.

- Critical information about the delivery of the project are now provided to local communities through face-to-face meetings with all community members and not through focal point persons to ensure the information delivered is not distorted .

- Project staff should be trained in the generation and documentation of success stories.

- As the project is gradually going to a close, ESMF Knowledge management products generated are now in the form of a GRM, a compilation of success stories best practices, and recommendations.

- Conservation International-Liberia has set up country level nine (9) member Accountability and Grievance Redress Mechanism (AGRM) Committee headed by Peace and other colleagues are part of the committee to help track grievances and resolve them in a timely manner.

## e. Overall Project ESMF Implementation Progress Rating

| SUMMARY: PROJECT ESMF IMPLEMENTATION RATING BY TYPE OF PLAN |  |  |
| --- | --- | --- |
| ESMF PLAN REQUIRED BY THE PROJECT (delete those not applicable) | CURRENT FY25 IMPLEMENTATION RATING | RATING TREND |
| Accountability and Grievance Mechanism | HS | Unchanged |
| Gender Mainstreaming Plan (GMP) | S | Increasing |
| Stakeholder Engagement Plan (SEP) | S | Unchanged |
| ESS 3: Voluntary Resettlement Action Plan/Process Framework | HS | Unchanged |

| OVERALL PROJECT ESMF IMPLEMENTATION RATING |  |  |  |
| --- | --- | --- | --- |
| RATING |  | JUSTIFICATION | RATING TREND |
| S | The project has an operational AGM, with the grievance mechanism being disseminated, and grievances tracked and resolved. The project received several grievances related to delays in payments. These grievances were processed through the AGM and resolved. On the GMP, the project has made good efforts to advance indicator targets and has achieved those related to the development of documents with gender considerations and the number of men and women demonstrating leadership in project implementation. However, the two other targets are still lagging behind. The project is making steady progress toward meeting the SEP indicator targets, having already achieved two of them. It has also successfully met all the targets for ESS3. |  | Unchanged |

## f. Recommendations

| CORRECTIVE ACTION(S) | RESPONSIBLE PARTY | DEADLINE |
| --- | --- | --- |
| The AGM needs to continue being disseminated with communities and other stakeholders through both verbal and printed channels, with dissemination tracked using the indicator: “Number of times the Accountability and Grievance Mechanism is communicated/disseminated to stakeholders.” Efforts should also continue to implement activities aimed at meeting the outstanding GMP and SEP targets. In-person engagements with communities remain important to strengthen relationships and fulfill commitments made, particularly those related to conservation agreements. Regarding the issue with mobile money payments that prevented some community members from accessing funds, the team should maintain open communication on the steps being taken to address such situations as they arise. Consistent updates and reassurances will help foster a positive relationship with the community and allow the team to monitor community sentiments and concerns regarding the situation. | PMU | 30th June, 2026 |

SECTION V: PROJECT IMPLEMENTATION EXPERIENCES, KNOWLEDGE MANAGEMENT AND LESSONS LEARNED

## a. Progress on the implementation of the project’s KM approach approved at CEO Endorsement/Approval

On knowledge management, we have been active in the last few months on dissinating information on our implementation through the Conservation International, Liberia Facebook page. As there is a dedicated intern handling this task, we are working to increase our visibility to other platforms like LinkedIn, Twitter/X and other reputable social media handles for visibility. Finally, the project is finalizing its sharepoint site for knowledge management, especially now that government officials are about to receive technical training in natural capital accounting.

b. Additional optional topics (please choose two)

- Scientific and technological issues: In FY25, much effort and resources were put into getting specimen collected from the landscape to laboratories in Eswatini, Canada and Sierra Leone as part of the RAP Assessment conducted in the project landscape. The final report which should provide insight on the biodiversity potention of the NCA landscape is being developed by the scientists and their assistants.

- Interpretation and application of GEF guidelines: For GEF guidelines and best practices, Small Grant beneficiaries on the project have began taking trainings in GEF standard financial due diligence and other related GEF policies and procedures.

- Financial management and co-financing: Almost every cofinancing institution on the project is committed, except Liberia Maritime Authority (LiMA) due to change in administration and limited understanding of the new administration on in-kind cofinancing. However, with constant engagement, cofinancing committements have been met.

- Capacity building: For capacity building, OIKO has been contracted to conduct capacity building for GoL staff on natural capital accounting to enhance their understanding of the concept at national level. The goal is to improve decision-making and ability to collect data on natural capital to inform management of natural resources at national level. In addition to the general NCA capacity building, GoL staff are also being trained on the development of a trust fund for nature. NatureRevamp, a Kenyan firm was contracted and is conducting capacity building for government, private sector and civil society groups on the trust fund concept as a sustainable approach to managing resources rather than reliance on projects to fund resource management at community and national levels.

- Factors that encourage replication, including outreach, dissemination of lessons learned, and communications strategies: As the NCA concept is still new in most parts of Africa, the project has served as an eye-opener to government and other stakeholders at national level. Establishment of a Mangrove Account is serving as a pilot to help the government and her partners to begin replicating the model for other ecosystems such as forests, freshwater, fisheries and oceans.

SECTION VI: PROJECT GEOCODING

This section of the PIR documents the precise and specific geographic location(s) of activities supported by GEF investments based on information provided in the Project Document.  The following information should be contained in this section:

  - Geo Location Information of Project Location(s) for the current fiscal year

  - Project Map and Coordinates from Project Document

Geo Location Information of Project Location(s) for the current fiscal year (add additional columns as needed)

Please provide a justification regarding changes in location during implementation. Justifications should also be provided in the event the geographic

| Geo Location Information | Location No. 1 | Location No. 2 | Location No. 3 | Location No.3 |
| --- | --- | --- | --- | --- |
| CLASSIFICATION Indicate whether the site is new or already existing in the previous PIR or indicate whether the site is included at CEO Endorsement/Approval or not. Please add more columns for projects with more than 3 locations. | Already existing site included in the CEO Endorsement | Already existing site included in the CEO Endorsement | Already existing site included in the CEO Endorsement | Already existing site included in the CEO Endorsement |
| Note: Provide justification if the location is a new site in this line |  |  |  |  |
| GEO NAME ID Provide the location’s Geo Name ID in a numerical format. IDs are available in the GeoNames’ geographical database covering all countries and containing millions of placenames with free access at: http://www.geonames.org. | 2274324 | 2276161 | 2273189 | 2588492 |
| LOCATION NAME Name of the geographic locations in which the activity is taking place. In instance when a GeoNames ID is provided above, the name of the said ID should be reflected. Otherwise, the location name provided will be considered as an exact location. | Butra | Karh | Webado Beach | Borkon Point |
| LATITUDE Provide locations in Decimal Degrees WGS84 format, a notation expressing geographic coordinates as decimal fractions of a degree. Include at least four decimal points. | 4.75839 | 4.87826 | 4.53861 | 5.91667 |
| LONGITUDE Provide locations in Decimal Degrees WGS84 format, a notation expressing geographic | -8.57048 | -8.5624 | -8.06606 | -9.36667 |
| Geo Location Information | Location No. 5 | Location No. 6 | Location No. 7 | Location No.8 |
| CLASSIFICATION Indicate whether the site is new or already existing in the previous PIR or indicate whether the site is included in CEO Endorsement/Approval or not. Please add more columns for projects with more than 3 locations. | Already existing site included in the CEO Endorsement | Already existing site included in the CEO Endorsement | Already existing site included in the CEO Endorsement | Already existing site included in the CEO Endorsement |
| GEO NAME ID Provide the location’s Geo Name ID in a numerical format. IDs are available in the GeoNames’ geographical database covering all countries and containing millions of placenames with free access at: http://www.geonames.org. | 9891550 | 2278912 | Not available in GeoNames geographical database | 2597292 |
| LOCATION NAME Name of the geographic locations in which the activity is taking place. In the instance when a GeoNames ID is provided above, the name of the said ID should be reflected. Otherwise, the location name provided will be considered as an exact location. | Neegba | Bame Town | Down The Mangrove | Greenville-Dioh Town |
| LATITUDE Provide locations in Decimal Degrees WGS84 format, a notation expressing geographic coordinates as decimal fractions of a degree. Include at least four decimal points. | 5.4295 | 5.20583 | 5.016175 | 4.98694 |
| LONGITUDE Provide locations in Decimal Degrees WGS84 format, a notation expressing geographic coordinates as decimal fractions of a degree. Include at least four decimal points. | -9.43562 | -9.34139 | -9.035279 | -9.01389 |
| LOCATION DESCRIPTION (Optional field) Text description that qualifies in a sentence or so the location in which an activity is taking place, such as for example “mini-grid energy system” or “park ranger site”. |  |  |  |  |
| ACTIVITY DESCRIPTION (Optional field) Text description that qualifies in a sentence or so the activity taking place at the location, for example, “Installing a mini- grid energy system”. | Conservation Agreement negotiation | No activity has been carried out at this site because it has been replaced. | Conservation Agreement negotiation | Conservation Agreement negotiation |
| Geo Location Information | Location No. 9 | Location No. 10 | Location No. 11 | Location No.12 |

| CLASSIFICATION Indicate whether the site is new or already existing in the previous PIR or indicate whether the site is included in CEO Endorsement/Approval or not. Please add more columns for projects with more than 3 locations. | Already existing site included in the CEO Endorsement | Already existing site included in the CEO Endorsement | New Site | New site |
| --- | --- | --- | --- | --- |
| Note: Provide justification if the location is a new site in this line |  |  | Accessible has a good community structure to work with, located close to dense mangrove ecosystem, has expressed interest in working with CI to manage their wetlands (mangrove) and terrestrial forests, performed well under previous CA signed under CI’s GEF Mangrove project. | Accessible has a good community structure to work with, located close to dense mangrove ecosystem, has expressed interest in working with CI to manage their wetlands (mangrove) and terrestrial forests, performed well under previous CA signed under CI’s GEF Mangrove project. |
| GEO NAME ID Provide the location’s Geo Name ID in a numerical format. IDs are available in the GeoNames’ geographical database covering all countries and containing millions of placenames with free access at: http://www.geonames.org. | Not available in GeoNames geographical database | 2279055 | 2278712 | 2275149 |
| LOCATION NAME Name of the geographic locations in which the activity is taking place. In instance when a GeoNames ID is provided above, the name of the said ID should be reflected. Otherwise, the location name provided will be considered as an exact location. | Togbawon | Turnata | Bendu | Mandoe |
| LATITUDE Provide locations in Decimal Degrees WGS84 format, a notation expressing geographic coordinates as decimal fractions of a degree. Include at least four decimal points. | 5.107265 | 5.17306 | 6.76203 | 6.69294 |
| LONGITUDE Provide locations in Decimal Degrees WGS84 format, a notation expressing geographic coordinates as decimal fractions of a degree. Include at least four decimal points. | -9.200296 | -9.28361 | -11.21253 | -11.18691 |
| LOCATION DESCRIPTION (Optional field) Text description that qualifies in a sentence or so the location in which an activity is taking place, such as for example “mini-grid energy system” or “park ranger site”. |  |  | Located within a nature reserve, along the shores of Liberia’s largest open water (Lake Piso) | Located within a nature reserve, along the shores of Liberia’s largest open water (Lake Piso) |
| ACTIVITY DESCRIPTION (Optional field) Text description that qualifies in a sentence or so the activity taking place at the location, for example, “Installing a mini- grid energy system”. | No activity has been carried out in this area, as it has been replaced due to inaccessibility | No activity has been carried out in this area, as it has been replaced due to inaccessibility | Implementation of Conservation Agreement | Implementation of Conservation Agreement |
| Geo Location Information | Location No. 13 | Location No. 14 | Location No. 15 | Location No.16 |
| CLASSIFICATION | New site | New site | New site | New site |
| Indicate whether the site is new or already existing in the previous PIR or indicate whether the site is included in CEO Endorsement/Approval or not. Please add more columns for projects with more than 3 locations. |  |  |  |  |
| Note: Provide justification if the location is a new site in this line | Accessible, has a good community structure to work with, located close to dense mangrove ecosystem, has expressed interest in working with CI to manage their wetlands (mangrove) and terrestrial forests, performed well under previous CA signed under CI’s GEF Mangrove project. | Accessible, has a good community structure to work with, located close to dense mangrove ecosystem, has expressed interest in working with CI to manage their wetlands (mangrove) and terrestrial forests, performed well under previous CA signed under CI’s GEF Mangrove project. | Accessible, has a good community structure to work with, located close to dense mangrove ecosystem, has expressed interest in working with CI to manage their wetlands (mangrove) and terrestrial forests, performed well under previous CA signed under CI’s GEF Mangrove project. | Accessible, has a good community structure to work with, located close to dense mangrove ecosystem, has expressed interest in working with CI to manage their wetlands (mangrove) and terrestrial forests, performed well under previous CA signed under CI’s GEF Mangrove project. |
| GEO NAME ID Provide the location’s Geo Name ID in a numerical format. IDs are available in the GeoNames’ geographical database covering all countries and containing millions of placenames with free access at: http://www.geonames.org. | 2277453 | Not available in GeoNames geographical database | Not available in GeoNames geographical database | 2274753 |
| LOCATION NAME Name of the geographic locations in which the activity is taking place. In instance when a GeoNames ID is provided above, the name of the said ID should be reflected. Otherwise, the location name provided will be considered as an exact location. | Falie | Sarwein | Bleewein | Nyangba |
| LATITUDE Provide locations in Decimal Degrees WGS84 format, a notation expressing geographic coordinates as decimal fractions of a degree. Include at least four decimal points. | 6.67729 | 5.830076 | 5.814727 | 5.789012 |
| LONGITUDE Provide locations in Decimal Degrees WGS84 format, a notation expressing geographic coordinates as decimal fractions of a degree. Include at least four decimal points. | -11.20848 | -10.016004 | -10.00495 | -9.972392 |
| LOCATION DESCRIPTION (Optional field) Text description that qualifies in a sentence or so the location in which an activity is taking place, such as for example “mini-grid energy system” or “park ranger site”. | Located within a nature reserve, along the shores of Liberia’s largest open water (Lake Piso) | Coastal Community with rich ecosystems containing endangered species | Coastal Community with rich ecosystems containing endangered species | Coastal Community with rich ecosystems containing endangered species |
| ACTIVITY DESCRIPTION (Optional field) Text description that qualifies in a sentence or so the activity taking place at the location, for example, “Installing a mini- grid energy system”. | Implementation of Conservation Agreement | Implementation of Conservation Agreement | Implementation of Conservation Agreement | Implementation of Conservation Agreement |
| Geo Location Information | Location No. 17 | Location No. 18 | Location No. 19 | Location No.20 |
| CLASSIFICATION Indicate whether the site is new or already existing in the previous PIR or indicate | This is a new site | This is a new site | This is a new site | This is a new site |
| whether the site is included in CEO Endorsement/Approval or not. Please add more columns for projects with more than 3 locations. |  |  |  |  |
| Note: Provide justification if the location is a new site in this line | Accessible, has a good community structure to work with, located close to dense mangrove ecosystem, has expressed interest in working with CI to manage their wetlands (mangrove) and terrestrial forests, performed well under previous CA signed under CI’s GEF Mangrove project. | Accessible, has a good community structure to work with, located close to dense mangrove ecosystem, has expressed interest in working with CI to manage their wetlands (mangrove) and terrestrial forests. | Accessible, has a good community structure to work with, located close to dense mangrove ecosystem, has expressed interest in working with CI to manage their wetlands (mangrove) and terrestrial forests. | Accessible, has a good community structure to work with, located close to dense mangrove ecosystem, has expressed interest in working with CI to manage their wetlands (mangrove) and terrestrial forests. |
| GEO NAME ID Provide the location’s Geo Name ID in a numerical format. IDs are available in the GeoNames’ geographical database covering all countries and containing millions of placenames with free access at: http://www.geonames.org. | Not available in GeoNames geographical database | 2273589 | 9977140 | 2274325 |
| LOCATION NAME Name of the geographic locations in which the activity is taking place. In instance when a GeoNames ID is provided above, the name of the said ID should be reflected. Otherwise, the location name provided will be considered as an exact location. | Ben’s Town | Timbo Kru | Lexington | Panama |
| LATITUDE Provide locations in Decimal Degrees WGS84 format, a notation expressing geographic coordinates as decimal fractions of a degree. Include at least four decimal points. | 6.182766 | 5.560943 | 5.39119 | 4.99318 |
| LONGITUDE Provide locations in Decimal Degrees WGS84 format, a notation expressing geographic coordinates as decimal fractions of a degree. Include at least four decimal points. | -10.417478 | -9.719325 | -8.49794 | -8.93804 |
| LOCATION DESCRIPTION (Optional field) Text description that qualifies in a sentence or so the location in which an activity is taking place, such as for example “mini-grid energy system” or “park ranger site”. |  | Coastal Community with rich ecosystems containing endangered species |  |  |
| ACTIVITY DESCRIPTION (Optional field) Text description that qualifies in a sentence or so the activity taking place at the location, for example, “Installing a mini- grid energy system”. | Implementation of Conservation Agreement | Conservation Agreement negotiation | Conservation Agreement negotiation | Conservation Agreement negotiation |
| Geo Location Information | Location No. 21 | Location No. 22 | Location No. 23 | Location No.8 |
| CLASSIFICATION Indicate whether the site is new or already existing in the previous PIR or indicate whether the site is included at CEO Endorsement/Approval or not. Please add | New site | New site | New site |  |

| more columns for projects with more than 3 locations. |  |  |  |  |
| --- | --- | --- | --- | --- |
| Note: Provide justification if the location is a new site in this line | Accessible has a good community structure to work with, located close to dense mangrove ecosystem, has expressed interest in working with CI to manage their wetlands (mangrove) | Accessible has a good community structure to work with, located close to dense mangrove ecosystem, has expressed interest in working with CI to manage their wetlands (mangrove), and coastal resources. | Accessible has a good community structure to work with, located close to dense mangrove ecosystem, has expressed interest in working with CI to manage their wetlands (mangrove), coastal and forest resources. |  |
| GEO NAME ID Provide the location’s Geo Name ID in a numerical format. IDs are available in the GeoNames’ geographical database covering all countries and containing millions of placenames with free access at: http://www.geonames.org. | 2597291 | 2276625 | 2274100 |  |
| LOCATION NAME Name of the geographic locations in which the activity is taking place. In instance when a GeoNames ID is provided above, the name of the said ID should be reflected. Otherwise, the location name provided will be considered as an exact location. | Seebeh | Grand Cess | Sass Town |  |
| LATITUDE Provide locations in Decimal Degrees WGS84 format, a notation expressing geographic coordinates as decimal fractions of a degree. Include at least four decimal points. | 4.99528 | 4.5689 | 4.66343 |  |
| LONGITUDE Provide locations in Decimal Degrees WGS84 format, a notation expressing geographic coordinates as decimal fractions of a degree. Include at least four decimal points. | -9.02917 | -8.21999 | -8.42819 |  |
| LOCATION DESCRIPTION (Optional field) Text description that qualifies in a sentence or so the location in which an activity is taking place, such as for example “mini-grid energy system” or “park ranger site”. |  | Coastal Settlement close to rich mangrove settlement |  |  |
| ACTIVITY DESCRIPTION (Optional field) Text description that qualifies in a sentence or so the activity taking place at the location, for example, “Installing a mini- grid energy system”. | Conservation Agreement negotiation | Conservation Agreement negotiation | Conservation Agreement negotiation |  |

location of key project activities cannot be provided at CEO Endorsement/Approval stage.

(Geo Name ID: Location Name) Justification: Some scope of the project was adjusted to in component three due to challenges of working those terrains. A request and justification for scope adjust in component three was submitted, reviewed and approved by the CI-GEF Agency.

Project Map and Coordinates

Please provide geo-referenced information and image map where the project interventions took place. If available, please provide attachments as 	appropriate such as in the case of locations presented along geometric shapes in popular formats like shapefiles, KML and GeoJSON.

NCA_Project_Sites.zi p

Section VII: Minor Amendments

This section of the PIR captures the changes to the project design or implementation that do not have significant impact on the project objectives or scope as described in Annex 9 of the Project and Program Cycle Policy Guidelines. Select any minor amendment that happened to the project during the latest fiscal year and provide a description of the minor amendment in a narrative format (max 100 words) as appropriate in the related textbox. You may provide supporting documents as attachment to this PIR

| Minor Amendment Categories | Minor Amendment Justification |
| --- | --- |
| Results framework | Target 1.1.2a (1 Analytical Framework); Target 1.1.2b (1 Milestone-based road map articulating key policies that include NCA results); outcome indicator and target 2.1a (adjusted 50% to 25%) and outcome indicator 3.1b (Ha of terrestrial forest outside protected areas |
| Components and cost |  |
| Institutional and implementation arrangements |  |
| Financial management |  |
| Implementation schedule | The project timeline was updated with a no-cost extension agreement, amending the end date from June 30, 2025, to July 31, 2026. |
| Executing Entity |  |
| Executing Entity Category |  |
| Minor project objective change |  |
| Safeguards |  |
| Risk analysis | Limited timeframe to complete capacity building and establish Mnagrove Account (NEW). Limited time to conduct Participatory Land Use Plan for each Conservation Agreement community under the project (NEW). |
| Increase of GEF project financing up to 5% |  |
| Co-financing |  |
| Location of project activity | Project scope adjusted (conservation agreement implementation under component 3 adjusted to cover Rivercess, Grand Bassa, Margibi, and Grand Cape Mount counties. (NEW) Due to the poor road conditions in the rainy season and the high cost of wear and tear relative to conservation agreement implementation in southeastern Liberia, a request for scope adjustment and related justification was submitted to the Project Steering Committee (PSC) and the GEF Agency for approval. Based on the approval received, all conservation agreements have covered only the counties listed above. |
| Other |  |

MINOR AMENDMENT RESPONSE FROM CI-GEF

All the minor amendments are approved by CI-GEF.

APPENDIX I: PROJECT ANNUAL IMPLEMENTATION PROGRESS RATING

| Rating |  | Overdue (O) | Delayed (D) | Not started on schedule (NS) | Under implementation on schedule (IS) | Completed/Achieved (CA) |
| --- | --- | --- | --- | --- | --- | --- |
| Highly Satisfactory (HS) | HS | 0% |  | 100% |  |  |
| Satisfactory (S) | S | 20% |  | 80% |  |  |
| Moderately Satisfactory (MS) | MS | 40% |  | 60% |  |  |
| Moderately Unsatisfactory (MU) | MU | 60% |  | 40% |  |  |
| Unsatisfactory (U) | U | 80% |  | 20% |  |  |
| Highly Unsatisfactory (HU) | HU | 100% |  | 0% |  |  |

- Highly Satisfactory: 100% of the indicators:  a) have been completed/achieved, b) are under implementation on schedule, and/or c) have not started but are on schedule, according to the approved/revised Annual Workplan for the project. The project can be presented as an example of “good practice” project,

- Satisfactory: 80% of the indicators: a) have been completed/achieved, b) are under implementation on schedule, and/or c) have not started but are on schedule, according to the approved/revised Project Annual Workplan for the project; except for only 20% that are delayed and/or overdue and need remedial action,

- Moderately Satisfactory: 60% of the indicators: a) have been completed/achieved, b) are under implementation on schedule, and/or c) have not started but are on schedule, according to the approved/revised Project Annual Workplan for the project; while 40% are delayed and/or overdue and need remedial action,

- Moderately Unsatisfactory: 40% of the indicators: a) have been completed/achieved, b) are under implementation on schedule, and/or c) have not started but are on schedule, according to the approved/revised Project Annual Workplan for the project; while 60% are delayed and/or overdue and need remedial action,

- Unsatisfactory: only 20% of the indicators: a) have been completed/achieved, b) are under implementation on schedule, and/or c) have not started but are on schedule, according to the approved/revised Project Annual Workplan for the project; while 80% are delayed and/or overdue and need remedial action, and

- Highly Unsatisfactory: 100% of the indicators: a) are overdue, and/or b) delayed in their implementation, according to the approved/revised Project Annual Workplan for the project.

# APPENDIX II: RISK RATINGS

| Rating |  |
| --- | --- |
| Low (L) | L |
| Moderate (M) | M |
| Substantial (S) | S |
| High (H) | H |

- Low Risk (L): There is a probability of up to 25% that assumptions may fail to hold or materialize, and/or the project may face only modest risks.

- Moderate Risk (M): There is a probability of between 26% and 50% that assumptions may fail to hold or materialize, and/or the project may face only modest risks.

- Substantial Risk (S): There is a probability of between 51% and 75% that assumptions may fail to hold and/or the project may face substantial risks.

- High Risk: There is a probability of greater than 75% that assumptions may fail to hold or materialize, and/or the project may face high risks.

# APPENDIX III: PROGRESS TOWARDS ACHIEVING PROJECT EXPECTED OUTPUTS

| INDICATORS | PROJECT TARGET | END-OF-YEAR INDICATOR STATUS | PROGRESS RATING | COMMENTS/JUSTIFICATION |
| --- | --- | --- | --- | --- |
| Outcome 1.1: Decision-making improved in coastal ecosystem governance by mainstreaming natural capital accounting (NCA) into the Government of Liberia (GOL) development strategy, policy, and planning |  |  |  |  |
| Output Indicator 1.1.1: Number of NCA Steering Committees established | Target 1.1.1: One (1) NCA Steering Committee | One (1) NCA Project Steering Committee (PSC) has been established. | CA | Accomplished in FY20 |
| Indicator 1.1.2a: An analytical framework developed in line with UN-SEEA guidelines [New/Revised based on MTE report]. | Target 1.1.2a: 1 analytical framework developed, in line with UN-SEEA guidelines. | Zero (0) analytical framework developed | NS | A consulting frame has been hired to establish the mangrove ecosystem accounts and part of it should be to develop an analytical framework which describes the methodology that will be used to create the various ecosystems accounts, in line with the UN- SEEA guidelines. This is expected to be done in FY26. |
| Indicator 1.1.2b: Number of milestone-based roadmaps articulating key policies and plans that include NCA results and how the Project plans to achieve each milestone [New/Revised based on MTE report]. | Target 1.1.2b: 1 milestone-based roadmaps articulating key policies and plans that include NCA results and how the Project plans to achieve each milestone. | Zero (0) milestone-based roadmaps | NS | A consulting frame has been hired to establish the mangrove ecosystem accounts and part of it should include milestone-based roadmaps articulating key policies and plans that include NCA results and how the Project plans to achieve each milestone. This is expected to be done in FY26. |
| Output Indicator 1.1.3: Number of standardized modular-based NCA training programme developed, approved by the NSC and TAC, and executed [New/Revised based on MTE report]. | New/Revised (FY25) Target 1.1.3: At least one standardized NCA training module |  | IS | A consulting frame has been hired to established the mangrove ecosystem accounts and develop a standardized training materials t train government officials and other stakeholders. This is expected to be done in first half of FY26 or throughout the NCE period on the project. |
| Output Indicator 1.1.4: Number of national planning instruments that incorporate NCA results. [New/Revised based on MTE report]. | Target 1.1.4: One national planning instrument incorporates NCA results for assessing key indicators (mangroves’ contribution to the economy) | To date: three (3) national planning instruments including ARREST Agenda for Inclusive Development (AAID), County Development Agenda (CDAs) and NDC 2.0 | IS | Pillar V of the AAID which is focused on environment sustainability incorporates NCA results for assessing key indicators (forests’ of which mangroves are included, contribution to the economy). In addition, the NDC 2.0 and two coastal counties development agenda incorporates natural capital concept. |
| Output Indicator 1.1.5: Number of reporting mechanisms for international commitments that incorporate NCA results by end of FY25. [New/Revised based on MTE report]. | Target: 1.1.5: One monitoring mechanism (Monitoring and Evaluation Framework incorporates NCA results for reporting progress on International frameworks (GBF and SDGs). | Zero (0) | NS | Not started. This is now expected to be done in FY26 or throughout the NCE period on the project. |
| Outcome 2.1 Funding sources for sustainable management and restoration of coastal ecosystems increased |  |  |  |  |
| Output Indicator 2.1.1: Number of prospectuses for Blue Carbon demonstration/pilot project | Target 2.1.1: One (1) prospectus for blue carbon demonstration/pilot project | One (01) prospectus for blue carbon demonstration/pilot project. | CA | To develop a blue carbon project, a Project Opportunity Profile (POP) is being developed. So far US$ 185,000 has been realized from Broadleaf for the development of the Project Identification Note (PIN), Project Opportunity Profile, and feasibility study. In addition, there are discussions with Proctor and Gamble for US$ 25 million for 25 years (US$ 1 million p.a.) for a blue carbon project. This was accomplished in FY23. |
| Output Indicator 2.1.2: Number of conservation-friendly enterprises active in the project area | Target 2.1.2: One (1) enterprise | Zero (0) | IS | A small grant committee was established. A call for proposals was launched to identify and develop partnership with Four (4) conservation friendly enterprises. Partnership with these Four conservation-friendly enterprise is expected to take place in FY26. |
| Output Indicator 2.1.3: Number of organizations receiving small grants | Target 2.1.3: Three (3) local organizations | Zero (0) | IS | A consulting firm hired to connect small grants program to LCAF |
| Output Indicator 2.1.4: Number of comprehensive design documents for national coastal conservation financing mechanism formally adopted by relevant government body/bodies | Target 2.1.4: One (1) design document | Zero (0) | IS | A consulting firm hired for conducting feasibility analyses and stakeholder consultations on developing either a stand-alone financing mechanism for mangrove conservation or as a subsidiary mechanism housed under the LCF. This is expected to be completed in FY26. |
| Outcome 3.1: Community-level conservation and sustainable use of coastal resources improved through performance-based payments using conservation agreements |  |  |  |  |
| Output Indicator 3.1.1: Number of Conservation Agreements (CAs) signed with communities | Target 3.1.1: Ten (10) Conservation Agreements | A total of 10 Conservation Agreement signed. | CA | Ten Conservation agreements were signed and are being implemented in Grand Cape Mount (Mandoe, Falie, and Bendu), Margibi (Charlesville cluster), Grand Bassa (Sarwein, Blewein and Nyangba) and Rivercess (Cestors cluster, Neegba and Timbo cluster). |
| Output Indicator 3.1.2: Number of national conservation agreement programs designed and established | Target: 3.1.2: One (1) national conservation agreement program | Zero (0) | IS | A consultant was hired to developed a National Aonservation Agreement Program model. This will completed in FY26. |

A no cost extension of 8 months from April 2025 to November 2025 for active implementation of activities. Terminal evaluation and project closeout activities will be conducted from December 2025 to July 2026.

Progress (IP) Rating: Highly Satisfactory (HS), Satisfactory (S), Moderately Satisfactory (MS), Moderately Unsatisfactory (MU), Unsatisfactory (U), and Highly Unsatisfactory (HU). For more details about IP rating, please see the Appendix I of this report

Rating trend: Improving, Unchanged, or Decreasing

Risk Rating: Low (L), Moderate (M), Substantial (S), High (H)

O= Overdue; D= Delayed; NS= Not started on schedule; IS= Under implementation on schedule; and CA= Completed/Achieved

O= Overdue; D= Delayed; NS= Not started on schedule; IS= Under implementation on schedule; and CA= Completed/Achieved

Rating trend: Increasing, Unchanged or Decreasing

O= Overdue; D= Delayed; NS= Not started on schedule; IS= Under implementation on schedule; and CA= Completed/Achieved

O= Overdue; D= Delayed; NS= Not started on schedule; IS= Under implementation on schedule; and CA= Completed/Achieved