## _Calc (hidden)
Evaluation text | Score
Very Unsatisfactory (HU) | 1
Unsatisfactory (U) | 2
Moderately Unsatisfactory (MU) | 3
Moderately Satisfactory (MS) | 4
Satisfactory (S) | 5
Very satisfactory (HS) | 6
Unknown | 0
Not rated | 0
for DevScore
|  | Person | PM/Coord | Budget holder | LTO | FEM OFP | GTO
|  | Weight % | 20 | 25 | 25 | 0 | 30
For ImpScore
|  | Person | PM/Coord | LTO | FEM OFP | GTO
|  | Weight % | 25 | 35 | 0 | 40
Once you have completed sections 2. Progress Towards Outcomes and 3. Implementation Progress
Please double-click and press Enter on cells D20 and D21 |  | #N/A
5

## Table of Contents
FAO-GEF Project Implementation Report
2025 – Revised Model
Period covered: from July 1, 2024 to June 30, 2025
Table of Contents
1. BASIC PROJECT DATA
2. PROGRESS TOWARDS ACHIEVING PROJECT OBJECTIVE(S) (DEVELOPMENT OBJECTIVE) | Progress towards achieving project objectives (development objective)
3. IMPLEMENTATION PROGRESS (IP) | Implementation Progress (IP)
4. SUMMARY ON PROGRESS AND CHALLENGES | Summary of progress, challenges and results
5.ENVIRONMENTAL AND SOCIAL SAFEGUARDS (ESS):RISKS FROM THE PROJECT
6. RISKS TO THE PROJECT
7. FOLLOW-UP ON MID-TERM REVIEW OR SUPERVISION MISSION
8. MINOR PROJECT AMENDMENTS
9. STAKEHOLDERS' ENGAGEMENT
10. GENDER MAINSTREAMING
11. KNOWLEDGE MANAGEMENT ACTIVITIES
12. INDIGENOUS PEOPLES AND LOCAL COMMUNITIES INVOLVEMENT
13. CO-FINANCING TABLE
14. GEO LOCATION INFORMATION
GEF 6&7 LDCF Core Indicators
Annex. Monitoring Area-based GEF Core Indicator Commitments and Progress with FERM
IMPORTANT DISCLAIMER:
The final version of this PIR will be submitted to the GEF Secretariat.
The report will then be publicly available on the WEF website (click here).
Sensitive information must be submitted as an attachment to be uploaded separately.
In such cases, please contact faogef-pir-support@fao.org for advice.

## 1. Basic project data
1. Basic project data
General information
Region: | Africa (RAF)
Country(ies): | Benin
Project Title: | Strengthening human and natural systems resilience to climate change through the mangrove ecosystems conservation and sustainable use in southern Benin
FAO project symbol: | GCP /BEN/064/GFF and GCP /BEN/066/LDF
GEF ID: | 10166
Trust fund type: | GFF, LDCF
GEF intervention area(s): | Biodiversity and climate change
Project Implementation Partners: | Ministry of Living Environment and Transport, in charge of sustainable development (MCVT) of the Republic of Benin
Initial project duration (years): | Five (5) years
Project Dates
GEF CEO Approval Date: | 2022-11-09
Actual Agency Approval Date | 2022-03-18
Project/EOD Implementation Start Date: | 2023-03-01
Date of first disbursement | 2023-12-31
Expected project end date/NTE1: | 2028-02-29
Date of completion of implementation of the revised project (if approved)2: | N / A
Actual Completion Date: | N / A
Expected financial closing date: | 29/02/2029
Funding
GEF Grant Amount (USD): | 7155936
Total GEF grant amount (as of June 30, 2025 (USD)): | LDF $1,277,022.38 GFF $ 737,460.12 TOTAL $2,014,482.50
Total amount of co-financing (USD)3: | 62864797
Estimated total co-financing materialized as of June 30, 2025: | 524172
Key steps in M&E
Date of last Project Steering Committee (PSC) meeting: | 2024-12-11
Expected date of mid-term review5: | 2026-11-09
Actual date of mid-term review (if already done): | n/a
Expected Terminal Evaluation Date: | 2027-08-29
Overall Ratings
Overall assessment of progress towards achieving objectives/results (cumulative): | Satisfactory (S)
Overall assessment of implementation progress: | Satisfactory (S)
Overall risk assessment: | Moderate
Status
Implementation status (1st PIR, 2nd PIR, etc. final PIR): | 1st PIR
1 Date originally planned during project implementation and indicated in the FPMIS. 2 If an extension of the NTE was requested and approved by the FAO-GEF Coordinating Unit. 3 This is the total amount of co-financing as indicated in the PDG document/project document. 4 Please refer to section 13 of this report where updated co-financing estimates are requested and indicate the total amount of co-financing materialized. 5 The Mid-Term Review (MTR) should take place after the 2nd PIR, approximately halfway between the end of the day and the NTE. The MTR report in English must be submitted to the GEF Secretariat within 4 years of the PDG approval date. 6 The date of the final evaluation should be discussed with the OED 6 months before the project NTE date.
Project Contacts
Contact | Name, title, division/institution |  | E-mail
Project Coordinator (PC) | Fiacre C. AHONONGA, National Project Coordinator, General Directorate of Water, Forests and Hunting /MCVT |  | fiacreahononga@gmail.com
Budget Holder (BH) | Angue Obama Oyana, Isaias (FRBEN) FAO Representative |  | Isaias.AngueObama@fao.org
GEF Operational Focal Point (GEF FPO) | Boni Yalla, Memanton (MCVT) Director of Planning, Administration and Finance |  | mboniyalla@gouv.bj
Senior Technical Manager (LTO) | Bouda, Zoewinde Henri-Noel (SFWDD) Forestry Officer, SFW |  | Zoewinde.Bouda@fao.org
GEF Technical Officer (GTO) | Maude VeyretPicot (OCBD) |  | Maude.VeyretPicot@fao.org
Key personnel of the project management unit
Please indicate the composition of the PMU in accordance with the terms of reference of the ProDoc. If a new position was created during the implementation of the project, please indicate this.
Planned position (according to ProDoc) | Position filled (Yes/No) | Start Date, Name, Contact |  | Comments
National Project Coordinator | Yes | July 1, 2023, Fiacre Codjo AHONONGA fiacreahononga@gmail.com , +2290196004685
Expert in planning, monitoring and evaluation | Yes | July 1, 2023 Abdou Gafar Agnila SALAMI g1salami@yahoo.fr , +2290197874305
Administrative and financial manager | Yes | July 1, 2023 Julienne F. VOGLOZIN SOHINTO, voglofifame@yahoofr, +229 0197607442
Gender and Social Inclusion Specialist | Yes | October 1, 2024, Randolph EGBETON egbetonrandolphe@gmail.com , +2290166575539
Communications Specialist | Yes | July 1, 2023 Mobèrèola Oloufounmilayo OLLOUDE funelleolive@yahoo.fr , +2290195404572
Pole Assistant (Ahémé Mangrove) | Yes | July 1, 2023 Ghislain Comlan AKABASSI cgakabassi@gmail.com , +229 0161 11 27 29
Pole Assistant (Coastal Mangrove) | Yes | July 1, 2023 Guy-Elvis C. SEMONDJI guyelvis66@gmail.com , +229 0197 42 81 77
Pole Assistant (Ouémé Mangrove) | Yes | July 1, 2023 Bertrand AYIHOUENOU abettyfr@gmail.com , +229 0197 89 86 55
Administrative secretary | Yes | October 1, 2024, Romaric QUENUM qromaric30@gmail.com , +2201996174084

## Country (hidden)
Select a country
Afghanistan
Åland Islands
Albania
Algeria
American Samoa
Andorra
Angola
Anguilla
Antarctic
Antigua and Barbuda
Argentina
Armenia
Aruba
Australia
Austria
Azerbaijan
Bahamas
Bahrain
Bangladesh
Barbados
Belarus
Belgium
Belize
Benign
Bermuda
Bhutan
Bolivia (Plurinational State of)
Bonaire, Saint Eustatius and Saba
Bosnia and Herzegovina
Botswana
Bouvet Island
Brazil
British Indian Ocean Territory
British Virgin Islands
Brunei Darussalam
Bulgaria
Burkina Faso
Burundi
Cape Verde
Cambodia
Cameroon
Canada
Cayman Islands
Central African Republic
Chad
Chile
China
China, Hong Kong Special Administrative Region
China, Macao Special Administrative Region
Christmas Island
Cocos (Keeling) Islands
Colombia
Comoros
Congo
Cook Islands
Costa Rica
Ivory Coast
Croatia
Cuba
Curacao
Cyprus
Czech Republic
Democratic People's Republic of Korea
Democratic Republic of Congo
Denmark
Djibouti
Dominique
Dominican Republic
Ecuador
Egypt
El Salvador
Equatorial Guinea
Eritrea
Estonia
Eswatini
Ethiopia
Falkland Islands (Malvinas)
Faroe Islands
Fiji
Finland
France
French Guiana
French Polynesia
French Southern Territories
Gabon
Gambia
Georgia
Germany
Ghana
Gibraltar
Greece
Greenland
Grenade
Guadeloupe
Guam
Guatemala
Guernsey
Guinea
Guinea-Bissau
Guyana
Haiti
Heard Island and McDonald Islands
Holy See
Honduras
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Isle of Man
Israel
Italy
Jamaica
Japan
Jersey
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People's Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Martinique
Mauritania
Mauritius
Mayotte
Mexico
Micronesia (Federated States of)
Monaco
Mongolia
Montenegro
Montserrat
Morocco
Mozambique
Burma
Namibia
Nauru
Nepal
Netherlands (Kingdom of)
New Caledonia
New Zealand
Nicaragua
Niger
Nigeria
Niue
Norfolk Island
North Macedonia
Northern Mariana Islands
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Pitcairn
Poland
Portugal
Puerto Rico
Qatar
Republic of Korea
Republic of Moldova
Meeting
Romania
Russian Federation
Rwanda
Saint-Barthélemy
Saint Helena
Saint Kitts and Nevis
Saint Lucia
Saint-Martin (French part)
Saint Pierre and Miquelon
Saint Vincent and the Grenadines
Saint Eustatius and Saba
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Sint Maarten (Dutch part)
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
South Georgia and the South Sandwich Islands
South Sudan
Spain
Sri Lanka
State of Palestine
Sudan
Suriname
Svalbard and Jan Mayen Islands
Suede
Swiss
Syrian Arab Republic
Tajikistan
Thailand
Timor-Leste
Go
Tokelau
Tonga
Trinidad and Tobago
Tunisia
Türkiye
Turkmenistan
Turks and Caicos Islands
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States Minor Outlying Islands
the United States of America
United States Virgin Islands
Uruguay
Uzbekistan
Vanuatu
Venezuela (Bolivarian Republic of)
Vietnam
Wallis and Futuna Islands
Western Sahara
Yemen
Zambia
Zimbabwe

## Trust fund type (hidden)
Trust fund type
Capacity Building Initiative for Transparency (CBIT)
Global Biodiversity Framework Fund (GBFF)
Global Environment Facility (GEF) Trust Fund
Least Developed Countries Fund (LDCF)
Special Climate Change Fund (SCCF)
Small Grants Program (SGP)

## Focal zone (hidden)
Focal zone
Multifocal zone
Biodiversity
Chemicals and waste
Chemicals/PoP
Climate change
Adaptation to climate change
Climate change mitigation
International waters
Land degradation

## 2. Progress towards results
2. Progress towards achieving project objectives (development objective)
(All entries in this section should be cumulative since the start of the project, not annual)
Please indicate the main progress made by the project towards achieving its objective(s) and the cumulative level of achievement of each result since the start of project implementation.
Objective of the project or development | Results | Results indicators | Baseline | Medium-term objective | End of project objective | Cumulative progress level as of June 30, 2025 | % cumulative progress | Progress Assessment
Increase the resilience of mangrove ecosystems and the agricultural, forestry and fishing communities that depend on them in the face of climate change and support the conservation of biodiversity and ecosystem services in mangrove landscapes of Ramsar sites 1017 and 1018 | Outcome 1: Mangrove ecosystems and their ecosystem services and goods are sustainably managed to strengthen the resilience of local agricultural, forestry and fishing communities and increase biodiversity in demonstration sites. | Indicator 1: Number of hectares of vulnerable and degraded mangrove landscapes benefiting from improved management to increase climate resilience and biodiversity status. Indicator 2a: Increase in average species abundance and 2b: Decrease in area of ​​biodiversity loss. Indicator 2c: Mangrove robustness. | Indicator 1: Some ACCBs and APCs have developed management plans, but need support for their implementation. Other mangrove areas, notably in Ramsar Site 1018, have community-based organizations or management plans that hinder their sustainable management and lead to their degradation. Baseline indicators 2a: 0.24; 2b: 158,465 ha; 2c: to be determined. | Objective 1: 30,000 ha Objective 2: Six municipalities have adopted integrated mangrove landscape management plans | Objective 1: 50,000 ha of vulnerable and degraded mangrove landscapes under integrated and sustainable management to increase community resilience to climate change and benefit biodiversity in 9 demonstration communities, then extended to the neighboring 90,000 ha (through training and capacity building) in Ramsar sites 1017 and 1018 for a total area of ​​140,000 ha. Objective 2: Nine municipalities adopt and implement integrated mangrove landscape management plans, directly benefiting the climate resilience of at least 300,000 people, 50% of whom are women. | Indicator 1: Nine (9) municipalities have adopted integrated mangrove landscape management plans covering a total area of ​​245,627 ha, including 1,303 ha of mangroves. It is estimated that mangrove landscapes cover approximately 20%, or 49,125.40 ha, of the total area covered by integrated management plans. Indicator 2a: Average species abundance (AMS): RAMSAR Site 1017 = 33.56% and RAMSAR Site 1018 = 44.24% Indicator 2a: - AMS RAMSAR Site 1017 = 33.56% - AMS RAMSAR Site 1018 = 44.24% Indicator 2b: Reduction in the area of ​​biodiversity loss - Mangrove area 2010: 3,146.63 ha - Mangrove area 2023: 3,139.74 ha Conversion rate: -0.22%/year Indicator 2c: Mangrove robustness RAMSAR Site 1017: - Basal area (Gm) = 1.16 - average height (hm) = 1.19 RAMSAR Site 1018: - Basal area (Gm) = 0.74 - height mean (hm) = 0.8 | 100% | Satisfactory (S)
|  | Indicator 3: Number of municipalities adopting and implementing integrated mangrove landscape management plans, and number of people benefiting from increased resilience. Indicator 4: Direct and indirect carbon benefits. Integrated management plans and number of people benefiting from increased resilience. Indicator 4: Direct and indirect carbon benefits. |  | Objective 3: the direct carbon benefit of SLM on 30,000 ha is equivalent to 1,682,926 tCO2eq | Objective 3: The direct carbon benefit of SLM on 50,000 ha is equivalent to 2,804,876 tCO2eq, and the indirect benefit on an additional 90,000 ha is equivalent to 4,727,161 tCO2eq | Indicator 3: 9 mangrove conservation plans (MCPs) available Indicator 4: In progress EX-Ante Carbon Footprint (EX-ACT 9.0) | 40% | Moderately Satisfactory (MS)
| Outcome 2: Agricultural, forestry and fishing communities that depend on mangrove ecosystems adopt alternative, biodiversity-friendly and sustainable livelihoods that strengthen their resilience to climate change. | Indicator 1: Number of people benefiting from increased income through alternative livelihoods resilient to climate change | Existing value chains in the agriculture, fisheries, forestry and tourism sectors are poorly developed and provide unreliable incomes. | Goal 1: 1,000 people, 50% of whom are women, benefit from increased income through climate-resilient alternative livelihoods | Goal 1: 27,000 people, 50% of whom are women, benefit from increased income through alternative livelihoods resilient to climate change (including 9,000 fishermen and 18,000 agricultural and forestry producers, processors and traders) | Indicator 1: In progress | 8% | Moderately Unsatisfactory (MU)
| Outcome 3: Strengthened national institutional and policy frameworks to sustainably manage mangrove landscapes in a changing climate and knowledge on climate-resilient mangrove ecosystem management improved, captured and disseminated | Indicator 1: Number of local decrees developed and proposed amendments to policy documents to support sustainable and climate-resilient mangrove management. Indicator 2: Number of institutional coordination mechanisms strengthened for integrated mangrove landscape planning. | Few local decrees emphasize the implementation of existing national policies on sustainable management and protection of mangrove ecosystems. Current planning processes do not sufficiently involve local communities and all relevant sectors. | Objective 1: At least two local ordinances developed to support sustainable and climate-resilient mangrove management. Objective 2: At least one institutional coordination mechanism for integrated mangrove landscape planning strengthened. | Objective 1: At least three local decrees developed and proposed amendment to a national law to support sustainable and climate-resilient mangrove management. Objective 2: At least two institutional coordination mechanisms (a collaboration platform and a decision-making and planning process) for integrated mangrove landscape planning strengthened. | Indicator 1: 5 draft decrees and one (01) draft law. | 50% | Moderately Satisfactory (MS)
Average cumulative progress towards results (%)
49.5%
Assessment of Sustainable Development Goals (SDGs) and overall assessment
Please note that overall DO scores should be supported by the evidence and progress reported above. Scores and comments should reflect the overall change in results since the start of the project.
| Rating of development objectives for the 2025 financial year¹ | Project Manager/Coordinator | Budget holder | Senior Technical Manager13 | GEF Operational Focal Point | GEF Technical Officer (GTO)
|  | Satisfactory (S) | Satisfactory (S) | Satisfactory (S) | Satisfactory (S) | Satisfactory (S)
| Comments/reasons¹² justifying the ratings for the 2025 financial year and any changes (positive or negative) in the ratings since the previous reporting period | The 2024 work plan was 80% complete as of December 31 and the 2025 work plan was 46.33% complete as of June 30, 2025. | Human and financial resources are managed in accordance with the provisions in force (See Spot-Check report) | Despite the challenges encountered in facilitating field supervision by the implementing agency, considerable efforts have been made so far to achieve the maximum expected results. I am convinced of the high implementation rate of this project before the national evaluation, thanks to the commitment, experience and skills of the PMU. | The UGP is periodically supported by the GEF OFP. | Based on the progress made on the key outcomes, it is estimated that the expected results will be achieved or even exceeded. The outcomes related to governance and the institutional and political environment, in particular, are modifiable and could contribute to sustainable, replicable and scalable results.
Measures to address the MS, MU, U and HU grading issues mentioned in section 2 above
Result |  | Action(s) to be taken |  | By whom? |  | When?
Outcome 1: Mangrove ecosystems and their ecosystem services and goods are sustainably managed to strengthen the resilience of local agricultural, forestry and fishing communities and increase biodiversity in demonstration sites. |  | English - Framing and launching of the various study files - Setting up local audiovisual communication platforms to raise awareness among community champions, at least 50% of whom are women - Hosting audiovisual programs to raise awareness among local communities, CSOs of local authorities, extension and agricultural advisory services, private companies and other stakeholders concerned with the preservation of mangrove ecosystems - Implementation of mangrove restoration, reforestation and watercourse opening activities - Development/Implementation of 9 communal mangrove conservation plans; - Development of 14 thematic ecosystem maps to fill knowledge gaps on mangrove ecosystems, - Carrying out the inventory of fauna and flora, - Updating the sustainable mangrove management strategy; - Capacity building of ACCB/ACPE and other relevant community organizations, as well as local stakeholders, in administrative and financial management, project management and monitoring. - Capacity building of grassroots communities in fishing regulations and techniques, in compstage, in agroecology in improved salt production technique (soliare); - Establishment of “young junior ambassadors” environmental clubs - Equipping environmental clubs and carrying out school plantations - Production of radio programs in local languages ​​and in French on the ecosystem services of mangroves and climate change - Formalization of nurserymen, producers of forest plants in mangrove landscapes. |  | Project Management Unit |  | From July 2024
Outcome 2: Farming, forestry and fishing communities that depend on mangrove ecosystems adopt alternative, biodiversity-friendly and sustainable livelihoods that strengthen their resilience to climate change. |  | - Framing and launching of the various study files; - Identification of priority sectors promoting the conservation of biodiversity and improving resilience to climate change; - Definition of selection criteria for business plans developed by community members for the implementation of IGAs. - Support to the NGO EcoBenin in the certification of the carbon credit project in the Bouche du Roi |  | Project Management Unit |  | From July 2024
Outcome 3: National institutional and policy frameworks are strengthened to sustainably manage mangrove landscapes in a changing climate and knowledge on the management of mangrove ecosystems is strengthened. |  | - Recruitment of NGOs for mobilization and social inclusion activities; - Strengthening the institutional and legal framework for the management of mangrove landscapes (including community management); - Development and implementation of an appropriate knowledge management strategy to capture and share lessons learned from the project and other relevant initiatives; - Development of the communication plan and the gender and social inclusion action plan; - Implementation of the project monitoring and evaluation plan; administrative management and procurement; - Organization and celebration of World Wetlands Day; - Participation in the Covè telefood fair in Zou and the National Tree Days (JNA) - Holding of steering committee sessions |  | Project Management Unit |  | From July 2024
7 Some indicators may not identify medium-term targets at the design stage (refer to the approved results framework); therefore, this column should only be completed where relevant. 8 Use the six-point scale system required by the GEF Secretariat: Highly Satisfactory (HS), Satisfactory (S), Moderately Satisfactory (MS), Moderately Unsatisfactory (MU), Unsatisfactory (U), and Highly Unsatisfactory (HU).

## 3. Implementation progress
3. Implementation Progress (IP)
(Please indicate the progress made during this financial year in accordance with the implementation plan/annual work plan)
Results and outputs | Indicators (according to the logical framework) | Key achievements over the past 12 months (please DO NOT repeat results reported in the previous year's PIR) |  |  | Describe any variation 9 in the delivery of results
Outcome 1: Mangrove ecosystems and their ecosystem services and goods are sustainably managed to strengthen the resilience of local agricultural, forestry and fishing communities and increase biodiversity in demonstration sites.
Outcome 1.1 Knowledge gaps on the distribution, composition, health, value and resilience of mangrove ecosystems are addressed to inform integrated mangrove landscape management planning under Outcome 1.4. | Number of ecosystem maps, inventories, land use maps, value assessments, socio-economic analyses and research projects undertaken to fill knowledge gaps on mangrove ecosystems | Under result 1.1, - 59 ecosystem and land use maps produced, - Five (5) maps of potential intervention areas - Nine (9) land use forecast maps of mangrove landscapes in 2030, 2050 and 2010 were produced and covered the nine (09) communes) benefiting from the project intervention, namely: Grand-popo; Ouidah; Abomey-Calavi; Bopa; Comè; Kpomassè; Sèmè-Kpodji; Aguégués and Sô-Ava. - One (01) inventory of fauna and flora, - A value assessment and a socio-economic analysis carried out Overall, this result was achieved at a rate of100% by June 30, 2025. Regarding the more sustainably managed areas, it should be noted that thirty-three (33) districts belonging to these nine (09) municipalities are home to mangrove landscapes which are monitored.
Outcome 1.2 Local awareness-raising platforms in demonstration sites have been created and made operational to mobilize and involve local stakeholder groups in the planning, implementation and monitoring of mangrove ecosystem management. | Number of awareness events and tools designed and organized/disseminated by local awareness platforms | As part of Activity 1.1.2 of the 2025 Annual Work Plan and Budget (AWPB), 21 events were carried out (two television broadcasts, six press articles, nine radio broadcasts and four articles in the online press). In total, this output was implemented at a rate of 84% as of June 30, 2025. |  |  | The report on the implementation of the platforms was validated in April 2025.
Result 1.3 Integrated mangrove landscape management plans are developed/updated to increase climate resilience and support biodiversity in nine municipalities, involving local stakeholders, including from the agriculture, forestry and fisheries sectors. | Number of integrated mangrove landscape management plans developed/updated | As part of activity 1.1.3 of the PTBA 2025, nine (09) municipal mangrove conservation plans that have integrated restoration issues and climate change are being developed with local stakeholders. In total, this result has been implemented at a rate of 90% as of June 30, 2025.
Result 1.4 Integrated mangrove landscape management plans implemented in 9 municipalities, promoting innovative and integrated technologies and approaches in the agriculture, forestry and fisheries sectors that contribute to ecosystem restoration, resilience to climate change and biodiversity conservation | Number of integrated mangrove landscape management plans under implementation Increased biodiversity index (using B-Intact indicators) | At least nine (09) plans have been developed and will be implemented through the Sitatunga and Grand Nokoué development plans which are currently being developed. Indicator: Mean Species Abundance (MSA): RAMSAR Site 1017 = 33.56% and RAMSAR Site 1018 = 44.24% Indicator 2a: - MSA RAMSAR Site 1017 = 33.56% - MSA RAMSAR Site 1018 = 44.24%
Outcome 1.5 The capacities of Community Biodiversity Conservation Areas (CBCAs), Farmer Contract Farming Associations (PCAAs) and other relevant local stakeholders have been strengthened in administrative and financial management, project management and monitoring. | Number of functional and autonomous CBCAs, PCAAs and other competent CSOs with 50% women members Number of monitoring systems established and operational | Three (03) IECs, including training on women's leadership and other community mushrooms, young junior ambassadors and salt production techniques with solar tarpaulins, were developed. This impacted 2,138 people, including 61.31% women, and 1,598 people from CBCAs and PCAAs. A monitoring system is being put in place.
Outcome 2: Agricultural, forestry and fishing communities that depend on mangrove ecosystems adopt alternative, biodiversity-friendly and sustainable livelihoods that strengthen their resilience to climate change.
Outcome 2.1 Strengthened sustainable nature-based value chains to increase the resilience of community livelihoods using a participatory and gender-responsive approach | Number of business plans implemented | Studies aimed at refining and identifying priority value chains that support biodiversity conservation and business plan scoring criteria were conducted. |  |  | These activities are ongoing
Outcome 2.2 At least three local public-private partnerships established and operationalized to catalyze investments in nature-based alternative livelihoods and value chains in targeted communities | Number of public-private partnerships created and operationalized | A partnership is underway with the Non-Governmental Organization "Benin Ecotourism Concern (Eco-Benin)" for the development and certification of a carbon project linked to the reduction of wood energy consumption in the mangrove areas of Mono and the Atlantic.
Release 2.3 | Number of public and private funding sources collaborating with the project | Planned for 2026 and 2027
Outcome 3: Strengthened national institutional and policy frameworks to sustainably manage mangrove landscapes in a changing climate and knowledge on climate-resilient mangrove ecosystem management improved, captured and disseminated
Result 3.1 Strengthening of the institutional and legal framework relating to the management of mangrove landscapes (including community management) | Indicator 1: Number of local decrees developed and proposed amendments to policy documents to support sustainable and climate-resilient mangrove management. Indicator 2: Number of institutional coordination mechanisms strengthened for integrated mangrove landscape planning. | Five draft orders were finalized through two studies in 2024. The 2025 PTBA provides for the recruitment of a service provider to refine these draft orders. Overall, this activity is completed at a rate of 50% as of June 30, 2025. A national platform is being established following a thorough assessment of local awareness platforms in the targeted sites, identifying community champions and funding sources to support awareness and behavior change within their community groups. Overall, this activity is completed at a rate of 30% as of June 30, 2025. |  |  | This activity, which has been partially completed, is continuing. The decision-making and planning process still needs to be implemented and strengthened.
Output 3.2 Capacity development plan designed and implemented for government institutions working on mangroves in Benin and the region to be able to support integrated, participatory and gender-sensitive processes for the sustainable management of mangrove landscapes under changing climatic conditions | Number of capacity building events organized for government institutions | Planned for 2026 and 2027 |  |  | Arrangements are underway for the implementation of this activity.
Outcome 3.3 Knowledge and awareness on the conservation and sustainable use of climate-resilient mangrove ecosystems are strengthened to facilitate decision-making at national, regional and global scales. | Number of knowledge events undertaken and tools developed and disseminated | One (1) national platform has been developed and communication supports are proposed in the communication plan. This product has been executed at a rate of 33% as of June 30, 2025. |  |  | These activities are currently being implemented.
Result 3.4 Implementation of the project monitoring and evaluation plan | Number of monitoring and evaluation reports submitted | Five (05) reports were produced. In total, this product was implemented at a rate of 83% as of June 30, 2025.
Implementation Progress (IP) and Overall Assessment
Please note that overall IP ratings should be supported by the evidence and progress reported above. Ratings and comments should reflect the overall change in results over the financial year (July 1, 2024 to June 30, 2025).
| Project Manager/Coordinator | Senior Technical Manager | Budget holder | GEF Operational Focal Point (OFP) | GEF Technical Officer (GTO)
Note on the implementation objective for the financial year 202510 | Satisfactory (S) | Satisfactory (S) | Satisfactory (S) | Satisfactory (S) | Satisfactory (S)
Comments/reasons for the ratings for the 2025 financial year and any changes (positive or negative) in the ratings since the previous reporting period | The 2024 work plan was 80% complete as of December 31 and the 2025 work plan was 46.33% complete as of June 30, 2025. | The project team is working hard to catch up on the delays incurred at the start of the project. The progress made is promising, and the planned implementation rate this year is expected to be close to the 100% target. | Human and financial resources are managed in accordance with the provisions in force (See Spot-Check report) | The UGP is periodically supported by the GEF OFP. | Progress is steady and agreed activities, included in the annual work plan and budget, are being implemented. Progress on results is satisfactory and efforts are directed towards achieving environmental, social and environmental (ESE) objectives and benefits related to climate change adaptation.
9 Gap refers to the difference between expected progress and actual progress at the time of reporting. 10 Implementation Progress Assessment – ​​Assessment of the extent to which the implementation of a project's components and activities is in accordance with the approved project implementation plan.

## 4. Summary_Progress and Challen
4. Summary of progress and challenges
Please provide a summary paragraph on the progress of project implementation, consistent with the information reported in sections 2 and 3 of the PIR (maximum 400 words) (This section will be uploaded to the GEF portal)
The implementation of the project activities from its inception until June 30, 2025 has resulted in: - Nine (9) communal mangrove landscape conservation plans covering a total area of ​​245,627 ha, including 1,303 ha of mangroves. It is estimated that mangrove landscapes cover approximately 20%, or 49,125.40 ha, of the total area to be covered by the integrated management plans. - Signing of six (6) agreements with the CPCA/PCAA for forest management; - Signing of three (03) contracts with NGOs to support co-management structures; - Restoration of 43.3 ha of mangrove in the three intervention centers; - Reforestation of 25.25 ha with acacia auriculiformis in the intervention areas; - Opening of 10.9 km of watercourses invaded by vegetation; - Validation and finalization of several study reports including: the monitoring and evaluation plan, the communication plan; the gender action plan, the identification of value chains, the business plan, the fine and detailed mapping, land security; the strategy and communal plans for the conservation of mangroves, the inventory of fauna and flora. - Signature of three (03) agreements with NGOs for the equipment of environmental clubs and the implementation of school plantations; - Organization of twenty-seven training sessions on administrative management, female leadership and negotiation techniques in the nine (09) communes with 2138 people including 61.31% women. 1598 people from CPCA/PCAA. - Organization of an exchange visit and training of 20 groups of women salt workers on improved extraction techniques for salt production; - Organization of three training courses on agroecology practices in mangrove ecosystems. - A partnership is underway with the Non-Governmental Organization “Benin Ecotourism Concern (Eco-Benin)” for the development and certification of a Carbon Project linked to the reduction of wood energy consumption in the mangrove areas of Mono and the Atlantic.
Please provide a summary paragraph on the challenges of project implementation, consistent with the information reported in sections 2 and 3 of the PIR (maximum 400 words) (This section will be uploaded to the GEF portal)
- Update the development and management plan for Grand Nokoué and Sitatunga - Implement restoration, reforestation and road opening activities in accordance with the forest management agreement - Implement activities related to component 2 of the project; - Develop the Project's administrative and accounting procedures manual - Develop the procedures and risk management manual - Set up the IT platform for backing up and securing Project data
Implementation of the exit strategy
Has the project developed an exit strategy? If so, please describe the progress made in implementing it. | The project is under the direction of the General Directorate of Water, Forests and Hunting (DGEFC), which is its national director. This system is in place to ensure the project's sustainability.
How does the project strengthen institutional capacities to foster country ownership for more sustainable results? | The PMU involves government institutions, NGOs, CPCB/PCCA, and communities in all aspects of project planning, development, and validation of studies and technical reports. The project organizes capacity-building activities for CPCB/PCAA and women's groups, carried out by local NGOs in partnership with the municipalities.

## 5. ESS risk
5. Environmental and social protection measures (ESM): project risks
Initial ESS Risk Classification (at CEO approval stage) | Moderate
New environmental and social risks. | ESS #1 Natural Resource Management - Negative impact on land tenure/access rights (country does not have a land tenure system that protects community rights to forests: definition of customary land rights, benefit-sharing mechanisms for communal forests, conflict resolution, etc.) ESS #2 Biodiversity, Ecosystems and Natural Habitats - Negative impact on protected area, buffer zone or natural habitats - Unregulated access and benefit-sharing of genetic resources ESS #3 Plant Genetic Resources for Food and Agriculture - Negative impact of the provision of seeds and planting materials ESS #3 Plant Genetic Resources for Food and Agriculture - Negative impact of the provision of seeds and planting materials ESS #4 Animal (Livestock and Aquatic) Genetic Resources for Food and Agriculture - Habitat modification ESS #7 Decent Work - Negative impact on the creation of better employment opportunities, especially for youth and women
Progress made in the implementation of the Environmental and Social Management Plan (ESMP) (only for moderate and high risk projects) | ESS #1 Natural Resource Management - The management of mangrove ecosystems is taken into account in the new forestry plan currently being developed. Its adoption will allow for the implementation of regulations at the local level. - Radio broadcasts in local languages ​​and French on ecosystem services and climate change in the intervention municipalities. - All municipalities have been provided with a municipal mangrove management plan. ESS #2. Biodiversity, ecosystems and natural habitats - Implementation of forest management agreements covering the restoration of 47 ha of mangroves and the establishment of 34 ha of reforestation and wood energy plantations - 6 km of waterways have been developed to facilitate the movement of small boats. ESS #3 Plant Genetic Resources for Food and Agriculture - The project does not introduce plant seeds and favors native species - An environmental study will be conducted for AGR business plans - Plantation establishment is carried out manually in compliance with environmental standards. The seeds used are local. ESS#4 Animal Genetic Resources (Livestock and Aquatic) for Food and Agriculture Consultant recruitment process underway to: - Design and implement, with local government institutions and in collaboration with ACCBs, APCs, a biomonitoring system covering: i) ecosystem regeneration, degradation and health; and ii) the evolution of mangrove species of high ecological and economic interest. - Design and implement a monitoring plan to ensure compliance with logging regulations, using a participatory approach with forest inspections, DPHs and ATDAs. ESS#7 Decent Work - The project implements the Gender and Social Inclusion Action Plan to ensure that all categories benefit from the interventions. - The implementation of value chain reports and business plans will make a big step towards the implementation of component 2 of the project which promotes sustainable green jobs and improves mangrove ecosystems. - For restoration and reforestation activities, 6 forest management agreements worth 160,737,740 FCFA were signed in September 2024 and are currently being implemented with congestion structures such as ACCB Vodounto, ACCB Chenal de Gbaga, ACCB Lac Ahémé, ACPE Aguégués, Sèmè-Kpodji and Sô Ava. Youth and women's groups are involved in restoration and reforestation activities through the management of these agreements.
Grievance Redress Mechanism (GRM)

## 6. Risks to the project
6. Risks to the project
The following table summarizes the risks identified in the project document and also reflects any new risks identified during project implementation.
| Type of risk |  | Risk assessment11 | Identified in the ProDoc Y/N | Risk description | Mitigation measure implemented
1 | Environment |  | Moderate | Yes | Considering current climate trends and future climate predictions is essential to the project's success. ANR sites will be selected based on models of future habitat suitability under different climate scenarios. These sites, available in the future, will be integrated as much as possible into community-based management areas for mangrove conservation. Available information on mangrove resilience to sea-level rise and increased salinity remains limited, but it is improving. For example, it is now known that Avicennia germinans is more resistant to high salinity than Rhizophora racemosa. The most recent knowledge will be used, and conservation and restoration activities will be designed based on the species-site combinations with the best chance of long-term success in each subsite. In addition, research projects on species and ecosystem resilience will be initiated as part of the project to fill knowledge gaps and support the design of future climate-resilient restoration efforts. | The completion of the detailed mapping study, as well as the inventory of the fauna and flora of mangrove ecosystems, have improved knowledge of these ecosystems. The implementation of co-management contracts with the ACCB/ACPE for restoration and regeneration activities, as well as the creation of ecological corridors, will also contribute to reducing this risk.
2 | Institutional |  | Moderate | Yes | Inter-institutional cooperation was identified as one of the obstacles that the project must overcome. Several interventions were therefore designed specifically to increase knowledge sharing and support integrated planning processes. The respective role of each institution in the management of mangrove ecosystems will be clarified, intersectoral collaboration for knowledge sharing and consultative decision-making processes will be strengthened, and decision-support tools will be developed to facilitate inclusive processes (Outcome 3.1). | A study was conducted to clarify the role of different stakeholders in the management of mangrove landscapes. The national strategy for the sustainable management of mangrove ecosystems was updated and nine municipal plans were developed. Local awareness-raising platforms were created to support awareness-raising and behavioral changes within communities.
3 | Legal and regulatory |  |  |  | The project design took into account lessons learned and best practices in behavior change in the intervention areas, thus providing concrete solutions to overcome the identified risk. Local implementing decrees for national legislation will be developed, where appropriate, to increase the effectiveness of implementation by local authorities. Information on preferred practices, as identified in the management plans, will be widely disseminated to the populations of the targeted municipalities and neighboring municipalities, through various communication media and events. In addition, community leaders (religious leaders, traditional chiefs, youth workers, etc.) will be closely involved at every stage of project implementation. They will play a key role in identifying measures to support the adoption of good practices and the abandonment of harmful ones. Their influence makes their support for the project crucial, as it should facilitate community compliance with local regulations. | The project proposed and integrated a "mangrove ecosystem management" component into the decree on forestry regulations. Its adoption will allow for the implementation of the regulations at the local level. Forest management agreements for the implementation of activities are signed with the communities through the ACCB/ACPE, which allows for their close involvement at all stages of the project.
4 | Safety and security |  | Weak | Yes | Safety measures will be implemented for all individual and group meetings. The budget for each training and awareness-raising session includes sufficient funds to implement the necessary safety measures throughout project implementation (e.g., sanitation tools, rental of adequately equipped, spacious, and ventilated premises). Virtual meetings will be organized whenever necessary at the central level. Authorizations to continue field interventions during critical phases at the local level will be granted if necessary, while ensuring the safety of project staff, community members, and partners. As the project is primarily focused on local stakeholders, it is expected that a temporary change in government priorities in the event of a new health crisis should not have a dramatic impact on project implementation. | Most monthly and quarterly meetings with FAO are held via videoconference, in strict compliance with social distancing guidelines. Participants in the various training and awareness-raising sessions benefit from the project's support.
5 | Partnership and coordination |  | High | Yes | The low level of community involvement in decision-making and uncertain access to natural resources have led some communities to lose interest in projects. Previous initiatives, which did not enjoy the full support of local communities, have had very limited success. Community interest in the project approach (adoption of sustainable nature-based livelihoods and/or mangrove conservation) was included as one of the criteria for selecting intervention sites and defining interventions during the PPG phase. Community motivation and ownership of the interventions will be a prerequisite for their implementation at each site, as they are a condition for success. The active participation and contribution of communities during kick-off meetings and participatory decision-making processes at the beginning of the project will confirm their interest in the project. The expected financial benefits from strengthening sustainable nature-based value chains will help maintain community motivation to protect mangrove ecosystems in the long term. | Contracts were signed with ACCB/APC, which is heavily involved in the management of mangrove ecosystems in the three intervention areas, as part of reforestation and restoration activities and the opening of waterways. The establishment of fuelwood plantations to compensate for the destruction of mangroves for specific needs was also carried out. Groups were also trained in improved salt production techniques and the adoption of good agroecological practices in mangrove ecosystems.
Overall project risk assessment (low, moderate, substantial or high):
2024 Financial Year Rating | 2025 Financial Year Rating | Comments/reasons for the rating for the 2025 financial year and any changes (positive or negative) in the rating since the previous reporting period
Moderate | Moderate
11. Risk assessment means an evaluation of the overall risk associated with factors internal or external to the project that may affect its implementation or the prospects for achieving its objectives. Project risk should be assessed on the following scale: low, moderate, substantial or high.

## 7. Follow-up MTR
7. Follow-up of the mid-term review or supervision mission
If the project was subject to an MTR or oversight engagement in 2024, please indicate how the recommendations were implemented during that fiscal year, as indicated in the management response or oversight engagement report.
Recommendations of the MTR or supervision mission | Measures implemented during this financial year
Recommendation 1:
Recommendation 2:
Recommendation 3:
Recommendation …
Recommendation…

## 8. Minor amendments
8. Minor changes to the project
Minor modifications are changes in design or implementation that do not significantly impact the project objectives or scope, or an increase in GEF funding for the project of up to 5%, as described in Annex 9 of the GEF Project and Program Cycle Guidelines. 12. Please describe any minor modifications to the project in the relevant category(ies) and provide supporting documentation as an annex to this report, if available. (This section will be posted on the GEF portal.)
Category of change | Provide a description of the change | Indicate the time of change | Approved by
Results framework
Components and cost
Institutional and implementing arrangements
Financial management
Implementation timeline
Executing entity
Executing Entity Category
Minor change to project goal
Guarantees
Risk analysis
GEF project funding increased by up to 5%
Co-financing
Location of project activity
Other minor change to the project (define)
12 GEF Council Meeting Documents, Guidelines, Project and Program Cycle Policy - 2020 Update

## 9. Stakeholder engagement
9. Stakeholder Engagement
Please report on the progress, challenges, and results of stakeholder engagement (based on the description of the stakeholder engagement plan) included in the CEO endorsement during the reporting period. (This section will be published on the GEF portal.)
Profile | Name of the stakeholder | Type of partnership | Progress, results and challenges in stakeholder engagement
Government institutions | DGEFC | Key | She provides national leadership for the project and is a member of the steering committee. She is at the strategic level and facilitates exchanges with FAO and the Project Management Unit. She contributes to the implementation of reforestation restoration activities and the opening of waterways to facilitate navigation, commercial traffic, and fishing. In terms of challenges, she will have to continue the actions listed above.
Government institutions | DGEC; ABE; CENAGREF; DPH; DDEAP; CIF | Key | They are members of the project steering committee and participate in monitoring and controlling the project. They continue to support the project in its activities related to climate change adaptation and the regulation of fishing activities.
NGO | ECO-BENIN; ACTION PLUS; NGO BEES; etc. | Key | They are operational partners of the project and carry out mobilization and social inclusion activities, including IEC and capacity building. They must contribute to the successful implementation of restoration, reforestation, opening of waterways, sanctification, etc. activities.
Private sector entities | Microfinance structures (AVEC, DAME, CAVECA, Alidé, PADME); private sector companies involved in value chains, etc. | Secondary | The activities for which its structures are needed have not yet started. Faced with the challenges, the UGP must establish links with these structures to ensure their effective involvement.
Others | Universities and research laboratories (LABEF; LEA) etc. | Key | The project has signed partnership agreements with research laboratories to conduct research aimed at filling knowledge gaps. Two reports were produced as part of this partnership in 2024. Further reports are expected as part of this partnership.
Others | Co-management associations of community biodiversity conservation areas (CCBA), community environmental protection areas (ACPE) and other relevant CBOs | Primary | - Co-management associations (ACCB/ACPE) and other community organizations benefit from capacity building and carry out forestry activities and duplicate the concepts received among their peers. "In terms of challenges, we must respect the project's guidelines and continue eco-citizen monitoring for the preservation of mangrove ecosystems.

## 10. Gender
10. Integration of the gender dimension
Information on progress made on gender-responsive measures, as documented during the CEO approval in the Gender Action Plan or equivalent (if applicable) during the reporting period. (This section will be published on the GEF portal.)
Category | Yes/No | Briefly describe the progress and results achieved during this reporting period.
a. Closing gender gaps in access to and control of global natural resources | Yes | Development of the gender and social inclusion action plan. Development of the document identifying land security activities guaranteeing women's access to land.
b. Improve women's participation and decision-making | Yes | - Nine (09) environmental clubs were created in the project intervention municipalities with 540 young junior ambassadors, 50% of whom were women; - Organization of twenty-seven training sessions on administrative management, female leadership and negotiation techniques in the nine (09) municipalities with 2138 people, 61.31% of whom were women. 1598 people from CPCA/PCAA. Participation of women and young people in reforestation and restoration activities; - Organization of exchange visits and training of 20 groups of women salt workers on improved salt extraction and production techniques.
c. generate socio-economic benefits or services for women | Yes | - Improving income through their participation in mangrove restoration, reforestation and fair activities. - Creating partnerships through meetings and exchange visits. Identification of identified sectors: Coastal Pole: Smoked Fish and Fresh Tomatoes; Ahémé Pole: Smoked Fish, Fresh Cassava, Fresh Fish and White Gari, Ouémé Pole: Smoked Fish, Organic Compost, Fresh Fish, Fresh Corn and Fresh Tomatoes.
Other good practices in gender | Yes | Taking gender into account in all project activities (meeting; validation; consultation, etc.).

## 11. Knowledge management
11. Knowledge and Learning activities
Knowledge activities/products (if applicable), as described in the CEO-approved knowledge management (and learning) approach, during the reporting period. (This section will be published on the GEF portal.)
Knowledge Management and Learning (KML): Does the project have a KML strategy? | No
If yes, what is the status of implementation? Please describe in your response how the project promotes knowledge sharing and learning among stakeholders at the national and subnational levels.
If NO, how does the project identify, collect and document good practices? | - The project identifies good practices through IEC activities; exchange visits and meetings. - Holders of these good practices are invited to share their good practices with their peers. - However, the study on the project's knowledge management strategy is underway to refine the identification, collection and archiving.
Please list good practices, including key technical and/or institutional innovations, of the project so far. | - The use of solar panels and seawater for salt production. - The production of compost to replace chemical fertilizers. - The use of legumes to restore soil fertility: the case of mucuna. - The creation and management of “young junior ambassador” environmental clubs.
Communication strategy: Does the project have a communication strategy? | Yes
Please provide a brief overview of the communication successes and challenges during this exercise. | - The creation of young junior ambassadors for environmental clubs as communication relays at the level of the intervention municipalities. - Organization of activities on the ecosystem services of mangroves and the impacts of climate change on five community radio stations (Ahémé FM, Mono FM, Tado FM; Gerdès FM and radio Kpassè in French and local language). - Production of capsules for environmental clubs, environmentally friendly techniques, training on female leadership. In terms of challenges: - Continue raising awareness among stakeholders and strengthening the achievements; - Animate the environmental clubs created; - Establish partnerships with regional television stations.
Humanitarian Story: Please share a humanitarian story from your project, focusing on how it has helped improve people's lives while contributing to the expected global environmental benefits. Please indicate any socioeconomic benefits generated by the project. Please include at least one quote and a beneficiary's perspective, along with associated photos and photo credits.
Please provide links to related websites and social media accounts | https://youtu.be/zBhftgBJiK4?si=puqQxLmjWSckSYC https://www.facebook.com/share/v/1Esu8Hhj2j/ https://www.facebook.com/share/v/1DfJvqSotx/?mibextid=wwXIfr
Please provide a list of publications, leaflets, videos, newsletters or other communication materials published on the web, if applicable. | • Production of three (03) capsules on: 1- The creation and installation of members of the Environmental Clubs of the AMBASSADEURS Juniors Mangrove students of Benin in the nine municipalities of intervention of the project in the schools. 2- Environmentally friendly practices (exchange visit of community organizations on improved extraction and processing techniques in the commune of Sèmè-Podji with the GBENONKPÖ Group of Sèmè-Okoun on salt production techniques with seawater, tarpaulins and solar rays. through women salt producers from other communes. 3- Capacity building session for women champion leaders and community organizations on awareness-raising methods, administrative and financial management, good governance and negotiation in the project intervention communes. - Recording of 20 radio programs in the communes on five community radio stations with high audience on ecosystem services and the impacts of climate change with experts (Tado Fm 106.3 in (French and xwémè) for the communes of Abomey-Calavi and Sô-Ava; Mono Fm 97.7 in (French) and Mina) for the municipalities of Comè and Grand-Popo; Radio Kpassè 93.8 in (French and Pédah) for the communes of Ouidah and Kpomassè; Fm Ahémé 87.7 in (French, Aizo and Wla) for the commune of Bopa; Gerdess Fm 89.5 in (French Goun and Tofin) for the municipalities of Aguégués and Sèmè-Podji.
Please provide the name and contact details of the Communication and/or Knowledge Management focal point. | - Communication focal point: OLLOUDE Mobèrèola Oloufounmilayo; 0195404572; funelleolive@yahoo.fr - Knowledge management focal point: SALAMI Abdou Gafar Agnila; 0197874305; g1salami@yahoo.fr

## 12. Indigenous Peoples
12. Participation of indigenous peoples and local communities
Are indigenous peoples and local communities involved in the project (in accordance with the approved project document)? If yes, please explain briefly.
If applicable, please describe the process and current status of ongoing or completed legitimate consultations aimed at obtaining the free, prior, and informed consent (FPIC) of indigenous communities. The project collaborates with associations responsible for the management of biodiversity conservation areas, called CBCA/PCAA. These associations are composed of local elected officials, traditional leaders, representatives of different activity categories, youth, and women, and therefore effectively and actively involve local communities in decision-making and project implementation. As part of the implementation of its activities, the project has signed forest management agreements with these associations for the restoration, reforestation, and opening of watercourses or corridors.

## 13. Co-financing
13. Co-financing table
Sources of co-financing | Name of co-financier | Type of co-financing | Amount confirmed upon CEO approval (in USD) | Actual amount materialized as of June 30, 2025 (in USD)
Recipient Country Government | MCVDD | Public investment | 58640000 | 0
GEF Agency | FAO | Grants | 4224797 | 524172
Total |  | Total | 62864797 | 524172
Please explain any significant changes in project co-financing since CEO approval, or differences between pledged and actual co-financing amounts.
GEF Guidelines on Co-financing 2018

## 14. Geographic location
14. Geolocation Information
This section should ONLY be completed by projects that have had a first Preliminary Assessment Report (PIR) and if the geographical coverage of project activities has changed since the last reporting period. This information is required by the GEF Secretariat on the GEF Portal.
Are there any changes in the geographical coverage of project activities since the last PIR report? |  |  |  | No |  | 1st PIR
Location Name | Latitude | Longitude | Geographic Name ID |  | Description of the place and activity*
General Directorate of Water, Forests and Hunting/Ministry of Living Environment and Transport in charge of Sustainable Development | 6°21'56'N | 2°27'51'E |  |  | Project Management Unit Headquarters in Cotonou, BENIN
Abomey-Calavi | 6.4539 | 2.3542 |  |  | Municipalities benefiting from the project's interventions on the RAMSAR 1018 site
Aguégués | 6.4533 | 2.5436
Kpomasse | 6.445 | 2.0137
Sémè Kpodji | 6.3815 | 2.6045
Sô-Ava | 6.497 | 2.4005
Bopa | 6.5893 | 1.9669 |  |  | Municipalities benefiting from the project's interventions on the RAMSAR 1017 site
Come on | 6.4042 | 1.8841
Grand-Popo | 6.2764 | 1.8067
Ouidah | 6.3666 | 2.0854

## GEF 6&7 LDCF indicators
Basic indicators_LDCF FEM-6 and FEM-7
For GEF-6 and GEF-7 funded LDC projects, please indicate the cumulative total achieved since inception, if available in the implementation document.
Basic indicator 1 | Total | Male | Women | % of women
Total number of direct beneficiaries | 300000 | 150000 | 150000 | 50%
Basic indicator 2
Area of ​​land managed for climate resilience (ha) | 50000
Basic indicators 3
Total number of policies/plans that will integrate climate resilience | 10
Basic Indicator 4 |  | Male | Female | % of women
Total number of people trained | 2138 | 828 | 1310 | 61.31%
Questions? Contact our support team: faogef-pir-support@fao.org

## Appendix
Annex. Monitoring of GEF Core Indicator Commitments by Area and Progress under FERM
The Ecosystem Restoration Monitoring Framework (FERM), developed by FAO, is the official platform for tracking global progress and disseminating good practices for the UN Decade on Ecosystem Restoration. FERM can serve as an integrated GIS platform, providing GEF staff and all relevant stakeholders with the ability to visualize progress on land restored or under improved management for conservation and sustainable use, as well as clear results such as the percentage of project completion. Having a common monitoring and tracking platform allows users to comprehensively assess and report on project progress. A user-friendly dashboard presenting project results allows stakeholders to clearly understand the extent to which project objectives have been achieved. Projects with GEF core indicators by area (GEF Core Indicators 1-5 and LDCF Core Indicator 2) are encouraged to register on the FERM platform.
Useful links:
• FERM website
• FERM User Guide (PDF)
• FERM YouTube channel
• Send an email to Carmen Morales
It also helps countries report areas under restoration for GBF Kunming-Montreal Target 2 (Areas Under Restoration) for which FAO is the custodian agency.