## _Calculation (hidden)
Evaluation text | Score
Very unsatisfactory (HU) | 1
Unsatisfactory (U) | 2
Moderately unsatisfactory (MU) | 3
Moderately satisfactory (MS) | 4
Satisfactory (S) | 5
Very satisfactory (HS) | 6
Unknown | 0
Not rated | 0
for DevScore
|  | Person | PM/Coord | Budget manager | LTO | FEM OFP | GTO
|  | Weight % | 20 | 25 | 25 | 0 | 30
For ImpScore
|  | Person | PM/Coord | LTO | FEM OFP | GTO
|  | Weight % | 25 | 35 | 0 | 40
Once sections 2. Progress towards results and 3. Status of implementation are completed, you will be able to proceed to the next step.
Please double-click and press Enter in cells D20 and D21. |  | 5
5

## Table of Contents
FAO-FEM Project Implementation Report
2026 – Revised Model
Period concerned: from July 1, 2025 to June 30, 2026
Table of Contents
1. BASIC PROJECT DATA
2. PROGRESS TOWARDS ACHIEVING PROJECT OBJECTIVE(S) (DEVELOPMENT OBJECTIVE) | Progress made towards achieving the project's objectives (development objective)
3. IMPLEMENTATION PROGRESS (IP) | Implementation Status (IP)
4. SUMMARY ON PROGRESS AND CHALLENGES | Summary of progress, challenges and results
5.ENVIRONMENTAL AND SOCIAL SAFEGUARDS (ESS):RISKS FROM THE PROJECT
6. RISKS TO THE PROJECT
7. FOLLOW-UP ON MID-TERM REVIEW OR SUPERVISION MISSION
8. MINOR PROJECT AMENDMENTS
9. STAKEHOLDERS' ENGAGEMENT
10. GENDER MAINSTREAMING
11. KNOWLEDGE MANAGEMENT ACTIVITIES
12. INDIGENOUS PEOPLES AND LOCAL COMMUNITIES INVOLVEMENT
13. CO-FINANCING TABLE
14. GEO LOCATION INFORMATION
GEF 6&7 LDCF Core Indicators
Annex. Monitoring Area-based GEF Core Indicator Commitments and Progress with FERM
IMPORTANT WARNING:
The final version of this preliminary evaluation report will be submitted to the GEF Secretariat.
The report will then be made available to the public on the WEF website (click here).
Sensitive information must be submitted as an attachment and uploaded separately.
In such cases, please contact faogef-pir-support@fao.org for advice.

## 1. Basic project data
1. Basic project data
general information
Region: | Africa (RAF)
Country : | Benin
Project title: | Strengthening the resilience of human and natural systems to climate change through the conservation and sustainable use of mangrove ecosystems in southern Benin
Symbol of the FAO project: | GCP /BEN/064/GFF and GCP /BEN/066/LDF
ID GEF: | 10166
Type of trust fund: | GFF, LDCF
Area(s) of intervention of the GEF: | Biodiversity and climate change
Project implementation partners: | Ministry of the Environment and Transport responsible for sustainable development (MCVT)
Initial project duration (years): | Five (5) years
Project dates
GEF CEO Endorsement Date: | 2022-11-09
Actual Agency Approval Date: | 2022-03-18
Project Implementation Start Date/EOD | 2023-03-01
Date of the first payment | 2023-12-31
Expected completion date of project/NTE1: | 2028-02-29
Date of completion of implementation of the revised project (if approved)2: | N / A
Actual completion date: | N / A
Expected financial closing date: | 29/02/2029
Funding
Amount of the GEF grant (USD): | 7155936
Total amount of the GEF grant (as of June 30, 2026 (USD)): | 2,025,279.32
Total co-financing amount (USD)3: | 62864797
The total estimated co-financing materialized on June 30, 2025: | 524172
Key steps in monitoring and evaluation
Date of the last meeting of the Project Steering Committee (PSC): | 2026-01-21
Expected date of the midterm exam⁵: | 2026-11-09
Effective date of the mid-term evaluation (if it has already taken place): | n / A
Expected date of the final evaluation: | 2027-08-29
Overall rating
Overall assessment of progress made towards achieving objectives/results (cumulative): | Satisfactory (S)
Overall assessment of implementation progress: | Satisfactory (S)
Overall risk assessment: | Low
Status
Implementation progress status (1st PIR, 2nd PIR, etc., final PIR): | 2nd PIR
1. Date originally planned during project implementation and indicated in the FPMIS. 2. Request for and approval of an extension of the project completion date (DAP) by the FAO-GEF Coordination Unit. 3. Total co-financing amount as indicated in the CEO/project document. 4. Please refer to section 13 of this report, where updated co-financing estimates are requested, and indicate the total amount of co-financing actually disbursed. 5. The Mid-Term Review (MTR) should take place after the second Preliminary Evaluation Report (PER), approximately halfway between the end of the day and the DAP. The MTR report in English should be submitted to the GEF Secretariat within four years of the CEO approval date. 6. The date of the Final Evaluation should be discussed with the Bureau of Environmental Assessment (BEA) six months before the project's DAP.
Project contacts
Contact | Name, title, division/establishment |  | E-mail
Project Coordinator (PC) | Fiacre C. AHONONGA, National Project Coordinator, Directorate General of Water, Forests and Hunting /MCVT |  | fiacreahononga@gmail.com
Budget Manager (BH) | Bouda, Zoewinde Henri-Noël (SFWDD) Acting Resident Representative of the FAO |  | Zoewinde.Bouda@fao.org
GEF Operational Focal Point (GEF PFOG) | Boni Yalla, Memanton (MCVT), Director of Planning, Administration and Finance |  | mboniyalla@gouv.bj
Senior Technical Officer (LTO) | Nathalie Diagne, Forestry and Natural Resources Expert |  | nathalie.diagne@fao.org
FEM Technical Officer (GTO) | Maude VeyretPicot (OCBD) |  | Maude.VeyretPicot@fao.org
Key personnel of the project management unit
Please indicate the composition of the project management unit (PMU) according to the specifications in the project document. If a new position was created during the project, please specify this.
Position planned (according to ProDoc) | Position filled (Yes/No) | Start date, Name, Contact |  | Comments
National Project Coordinator | Yes | July 1, 2023, Fiacre Codjo AHONONGA fiacreahononga@gmail.com , +2290196004685
Expert in planning, monitoring and evaluation | Yes | July 1, 2023 Abdou Gafar Agnila SALAMI g1salami@yahoo.fr , +2290197874305
administrative and financial manager | Yes | July 1, 2023 Julienne F. VOGLozin SOHINTO, voglofifame@yahoo.fr , +229 0197607442
Specialist in gender equality and social inclusion | Yes | October 1, 2024, Randolph EGBETON egbetonrandolphe@gmail.com , +2290166575539
Communications Specialist | Yes | July 1, 2023 Mobèrèola Oloufounmilayo OLLOUDE funelleolive@yahoo.fr , +2290195404572
Assistant to the Pole (Ahémé Mangrove) | Yes | July 1, 2023 Ghislain Comlan AKABASSI cgakabassi@gmail.com , +229 0161 11 27 29
Assistant to the coastal mangrove unit | Yes | July 1, 2023 Guy-Elvis C. SEMONDJI guyelvis66@gmail.com , +229 0197 42 81 77
Assistant to the Pole (Ouémé Mangrove) | Yes | October 1, 2025 Djabarou Ibrahim djabatou@yahoo.fr , +229 0197 89 86 55
Administrative Secretary | Yes | October 1, 2024, Romaric QUENUM qromaric30@gmail.com , +2201996174084

## Country (hidden)
Select a country
Afghanistan
Åland Islands
Albania
Algeria
American Samoa
Andorra
Angola
Anguilla
Antarctic
Antigua and Barbuda
Argentina
Armenia
Aruba
Australia
Austria
Azerbaijan
Bahamas
Bahrain
Bangladesh
Barbados
Belarus
Belgium
Belize
Benign
Bermuda
Bhutan
Bolivia (Plurinational State of)
Bonaire, Saint Eustatius and Saba
Bosnia and Herzegovina
Botswana
Bouvet Island
Brazil
British Indian Ocean Territory
British Virgin Islands
Brunei Darussalam
Bulgaria
Burkina Faso
Burundi
Cape Verde
Cambodia
Cameroon
Canada
Cayman Islands
Central African Republic
Chad
Chile
China
China, Hong Kong Special Administrative Region
China, Macao Special Administrative Region
Christmas Island
Cocos (Keeling) Islands
Colombia
Comoros
Congo
Cook Islands
Costa Rica
Ivory Coast
Croatia
Cuba
Curaçao
Cyprus
Czech Republic
Democratic People's Republic of Korea
Democratic Republic of the Congo
Denmark
Djibouti
Dominique
Dominican Republic
Ecuador
Egypt
El Salvador
Equatorial Guinea
Eritrea
Estonia
Eswatini
Ethiopia
Falkland Islands (Malvinas)
Faroe Islands
Fiji
Finland
France
French Guiana
French Polynesia
French Southern Territories
Gabon
Gambia
Georgia
Germany
Ghana
Gibraltar
Greece
Greenland
Grenade
Guadeloupe
Guam
Guatemala
Guernsey
Guinea
Guinea-Bissau
Guyana
Haiti
Heard Island and McDonald Islands
Holy See
Honduras
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Isle of Man
Israel
Italy
Jamaica
Japan
Jersey
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People's Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Martinique
Mauritania
Mauritius
Mayotte
Mexico
Micronesia (Federated States of)
Monaco
Mongolia
Montenegro
Montserrat
Morocco
Mozambique
Burma
Namibia
Nauru
Nepal
Netherlands (Kingdom of)
New Caledonia
New Zealand
Nicaragua
Niger
Nigeria
Niue
Norfolk Island
North Macedonia
Northern Mariana Islands
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Pitcairn
Poland
Portugal
Puerto Rico
Qatar
Republic of Korea
Republic of Moldova
Meeting
Romania
Russian Federation
Rwanda
Saint-Barthélemy
Saint Helena
Saint Kitts and Nevis
Saint Lucia
Saint-Martin (French side)
Saint-Pierre-et-Miquelon
Saint Vincent and the Grenadines
Saint Eustatius and Saba
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Sint Maarten (Dutch part)
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
South Georgia and the South Sandwich Islands
South Sudan
Spain
Sri Lanka
State of Palestine
Sudan
Suriname
Svalbard and Jan Mayen Islands
Suede
Swiss
Syrian Arab Republic
Tajikistan
Thailand
Timor-Leste
Go
Tokelau
Tonga
Trinidad and Tobago
Tunisia
Türkiye
Turkmenistan
Turks and Caicos Islands
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
Minor and isolated islands of the United States
the United States of America
U.S. Virgin Islands
Uruguay
Uzbekistan
Vanuatu
Venezuela (Bolivarian Republic of)
Vietnam
Wallis and Futuna Islands
Western Sahara
Yemen
Zambia
Zimbabwe

## type of trust fund (hidden)
type of trust fund
Capacity Building Initiative for Transparency (CBIT)
Global Biodiversity Framework Fund (GBFF)
Global Environment Facility (GEF) Trust Fund
Fund for Least Developed Countries (LDCs)
Special Climate Change Fund (SCCF)
Small Grants Programme (SGP)

## Focal zone (hidden)
Focal zone
Multifocal zone
biodiversity
Chemicals and waste
Chemicals/PoP
climate change
Adaptation to climate change
climate change mitigation
international waters
land degradation

## 2. Progress towards results
2. Progress made towards achieving the project objectives (development objective)
(All data in this section should be cumulative since the start of the project, not annual.)
Please indicate the main progress made by the project in achieving its objectives and the cumulative level of achievement of each result since the start of its implementation.
Project or development objective | Results | Performance indicators | baseline | Medium-term objective | ultimate goal of the project | Cumulative progress level as of June 30, 2026 | % cumulative progress | Progress assessment
In order to increase the resilience of mangrove ecosystems and the agricultural, forestry and fishing communities that depend on them to climate change and to support the conservation of biodiversity and ecosystem services in the mangrove landscapes of Ramsar sites 1017 and 1018 | Result 1: Mangrove ecosystems and their ecosystem services and goods are managed sustainably to strengthen the resilience of local farming, forestry and fishing communities and to increase biodiversity in demonstration sites. | Indicator 1: Number of hectares of vulnerable and degraded mangrove landscapes benefiting from improved management aimed at increasing their climate resilience and biodiversity. Indicator 2a: Increase in average species abundance. Indicator 2b: Decrease in the area of ​​biodiversity loss zones. Indicator 2c: Mangrove resilience. | Indicator 1: Some ACCBs and ACPEs have developed management plans but require support for their implementation. Other mangrove areas, particularly within Ramsar site 1018, have community organizations or management plans that hinder their sustainable management and contribute to their degradation. Reference indicators: 2a: 0.24; 2b: 158,465 ha.2c: to be determined. | Objective 1: 30,000 ha. Objective 2: Six municipalities have adopted integrated mangrove landscape management plans. | Objective 1: To establish integrated and sustainable management of 50,000 ha of vulnerable and degraded mangroves to increase community resilience to climate change and promote biodiversity in nine pilot communities. This management will then be extended to the neighboring 90,000 ha (through training and capacity building) of Ramsar sites 1017 and 1018, for a total area of ​​140,000 ha. Objective 2: Nine municipalities will adopt and implement integrated mangrove management plans, directly benefiting the climate resilience of at least 300,000 people, 50% of whom will be women. | - Indicator 1: Nine (9) Municipal Mangrove Conservation Plans adopted by the municipalities. - The management plans have adopted integrated mangrove landscape management measures covering a total area of245,627 ha, of which3,139.75 hhas mangroves (Municipal Mangrove Conservation Plans and Detailed Mapping Report of Mangrove Ecosystems, 2025). - Indicator 2a: Average Species Abundance (AME): RAMSAR Site 1017 = 33.56% and RAMSAR Site 1018 = 44.24% - Indicator 2b: Reduction of Biodiversity Loss Area - Mangrove Area in 2010:1178.6 and 1303.3 ha in 2020 (Project document p.18). Mangrove area in 2023: 3,139.74 ha. Conversion rate: +35.23%/year. Indicator 2c: Mangrove robustness. RAMSAR site 1017: - Basal area (Gm) = 1.16 - Average height (hm) = 1.19. RAMSAR site 1018: - Basal area (Gm) = 0.74 - Average height (hm) = 0.8. | 50% | Satisfactory (S)
|  | Indicator 3: Number of municipalities that have adopted and implemented integrated mangrove management plans and number of people benefiting from increased resilience. Indicator 4: Direct and indirect carbon-related benefits. |  | Target 3: The direct carbon benefit of sustainable land management on 30,000 ha is equivalent to 1,682,926 tCO₂eq. | Target 3: The direct carbon benefit of sustainable land management on 50,000 ha is equivalent to 2,804,876 tCO2eq, and the indirect benefit on an additional 90,000 ha is equivalent to 4,727,161 tCO2eq. | Indicator 3: 9 municipal mangrove conservation plans (PMCMs) available. Indicator 4: In progress. EX-Ante Carbon Footprint (EX-ACT 9.0) | 60% | Satisfactory (S)
| Result 2: Farming, forestry and fishing communities that depend on mangrove ecosystems adopt alternative, biodiversity-friendly and sustainable livelihoods that strengthen their resilience to climate change. | Indicator 1: Number of people benefiting from an increase in their income through alternative and climate-resilient livelihoods | Existing value chains in the agriculture, fishing, forestry and tourism sectors are underdeveloped and generate irregular incomes. | Objective 1: To enable 1,000 people, 50% of whom are women, to benefit from an increase in their income through alternative and climate-resilient livelihoods. | Target 1: 27,000 people, 50% of whom are women, benefit from increased incomes through alternative and climate-resilient livelihoods (including 9,000 fishermen and 18,000 agricultural and forestry producers, processors and traders). | Indicator 1: 971 people benefit from 21 business plans and increased incomes through alternative and resilient livelihoods. This could represent 5,438 people from households impacted by the implementation of value chains. | 20% | Satisfactory (S)
| Result 3: Strengthening of national institutional and policy frameworks for the sustainable management of mangrove landscapes in a context of climate change; improvement, capitalisation and dissemination of knowledge on the management of climate-resilient mangrove ecosystems. | Indicator 1: Number of local decrees developed and amendments proposed to policy documents aimed at supporting sustainable and climate-resilient mangrove management. Indicator 2: Number of strengthened institutional coordination mechanisms for integrated mangrove landscape planning. | Few local decrees emphasize the implementation of existing national policies related to the sustainable management and protection of mangrove ecosystems. Current planning processes do not sufficiently involve local communities and all relevant sectors. | Objective 1: Develop at least two municipal regulations to support sustainable and climate-resilient mangrove management. Objective 2: Strengthen at least one institutional coordination mechanism for integrated mangrove landscape planning. | Objective 1: Develop at least three local decrees and propose amendments to a national law to support sustainable and climate-resilient mangrove management. Objective 2: Strengthen at least two institutional coordination mechanisms (a collaboration platform and a decision-making and planning process) for integrated mangrove landscape planning. | Indicator 1: "- 5 draft decrees and the law prepared, - 1 municipal decision to implement the Municipal Mangrove Management Framework (MCMF) was prepared during the period from 1/07/2025 to 30/06/2026. Objective 2: - Establishment of two (2) institutional consultation frameworks for the Community Associations for the Management of Mangrove Ecosystems of the two (2) RAMSAR sites (CC-ACEM-1017 and CC-ACEM-1018) and an umbrella organization for the two consultation frameworks. - Creation of a Municipal Framework for Mangrove Management Stakeholders (MCMF) at the level of each of the nine municipalities | 70% | Satisfactory (S)
Average cumulative progress towards results (%) | Time elapsed since the start/end of the project compared to the planned project end date | % delivery
50%
Evaluation of the Sustainable Development Goals (SDGs) and overall assessment
Please note that overall DO scores must be supported by the evidence and progress reported above. Scores and comments should reflect the overall evolution of results since the start of the project.
| FY2026 Development Objective rating¹ | Project Manager/Coordinator | Budget manager | Senior Technical Manager 13 | Operational focal point of the GEF | FEM Technical Officer (GTO)
|  | Satisfactory (S) | Satisfactory (S) | Satisfactory (S) | Satisfactory (S) | Satisfactory (S)
| Comments/reasons¹² justifying the ratings for the 2026 financial year and any changes (positive or negative) to the ratings since the previous reference period | As of the end of June 2026, the overall project completion rate is 57.54%. The 2026 work plan is 46% complete as of June 30, 2026. | Financial resources are allocated based on expressed needs. As of June 30, 2026, a single transfer of US$562,895,835 has been made and is being processed according to the established procedure. | Despite the challenges encountered in facilitating on-the-ground monitoring by the implementing agency, considerable efforts have been made to date to achieve the expected results. I am confident in the project's completion rate prior to the final evaluation, thanks to the commitment, experience, and skills of the project management team. | The operational focal point organised a follow-up mission in March 2026 to the project's intervention communes to inquire about the progress and difficulties encountered. | This assessment takes into account the project's progress, providing a solid foundation for achieving the development objective. Nine municipalities have adopted integrated mangrove management plans, and their implementation is underway in each of them. The ongoing carbon assessment will precisely measure the project's contribution to climate change mitigation and demonstrate its tangible results.
Measures to resolve the MS, MU, U and HU notation problems mentioned in section 2 above
Result |  | Measures to be taken |  | By whom? |  | When?
Result 1: Mangrove ecosystems and their ecosystem services and goods are managed sustainably to strengthen the resilience of local farming, forestry and fishing communities and to increase biodiversity in demonstration sites. |  | - Continued restoration, reforestation, and opening of mangrove waterways; - Development and implementation of 9 mangrove conservation plans; - Training and equipping of 9 environmental clubs and creation of nurseries and school plantations; - Production of 20 radio programs in local languages ​​and French on mangrove ecosystem services and climate change; - Formalization of nursery owners and forest plant producers in mangrove landscapes; - Organization of 9 awareness-raising sessions for Community Action Committees (CACCs) and Community Action Committees (CAPCs) on ecosystem services and the impacts of climate change; - Organization of 20 awareness-raising sessions for co-management structures and traditional religious leaders on mangrove site sanctification practices in the 9 municipalities; - Field visit with the FAO national team to the 9 municipalities; - Visits by FAO national and GEF regional teams to the 9 project communes to produce a mini-documentary on project activities; - Organization of ecotourism visits in mangrove areas; - Organization of a nature walk in the Grand Popo commune; - Organization of a mini-fair in Grand Popo to mark the International Day for the Conservation of Mangrove Ecosystems (IDCE); - Celebration of IDCE 2025 in Grand Popo; - Celebration of and participation in World Wetlands Day; - Participation in the International Day for Biological Diversity with young mangrove ambassadors in Lokossa; - Participation in the International Day of Forests with young mangrove ambassadors/child forest ambassadors; - Development of a monitoring plan to ensure compliance with regulations on mangrove exploitation and training on biomonitoring and effectiveness monitoring systems for interventions in mangrove landscapes; - Selection of 5 research projects to fill the remaining knowledge gaps through master's degrees. |  | Project Management Unit |  | From July 2025
Result 2: Farming, forestry and fishing communities that depend on mangrove ecosystems adopt alternative, biodiversity-friendly and sustainable livelihoods that strengthen their resilience to climate change. |  | - Defining the selection criteria for business plans developed by community members for the implementation of income-generating activities (IGAs); - Training 33 groups and cooperatives in business plan development; - Development of 33 business plans; - Selection of 21 business plans and acquisition of equipment for their benefit; - Handover of equipment to the 21 selected groups; - Support to the NGO EcoBenin for the certification of the carbon credit project in the Bouche du Roy. |  | Project Management Unit |  | From July 2025
Result 3: National institutional and policy frameworks are strengthened to sustainably manage mangrove landscapes in a context of climate change and knowledge on the management of mangrove ecosystems is strengthened. |  | - Renewal of the partnership with the 3 NGOs for mobilization and social inclusion activities; - Strengthening of the institutional and legal framework for mangrove landscape management (including community management); - Development and implementation of an appropriate knowledge management strategy to capitalize on and disseminate lessons learned from the project and other relevant initiatives; - Updating of the action plan for the national mangrove management strategy; - Continued implementation of the communication plan; - Continued implementation of the action plan for gender equality and social inclusion; - Continued implementation of the project monitoring and evaluation plan; - Design and training in the use of administrative and financial management software; - Holding of steering committee meetings; - Establishment of the Community Association Consultation Framework for the conservation of mangrove ecosystems in Ramsar sites 1017 and 1018; - Creation of the National Federation of Consultation Frameworks of Community Associations for the Conservation of Mangrove Ecosystems in Benin (FeCACEM-Benin). |  | Project Management Unit |  | From July 2025
7 Some indicators may not identify medium-term targets at the design stage (see the approved results framework); therefore, this column should only be completed where applicable. 8 Use the six-point scale required by the GEF Secretariat: Very Satisfactory (VS), Satisfactory (S), Fairly Satisfactory (FS), Fairly Unsatisfactory (FA), Unsatisfactory (U), and Very Unsatisfactory (VU).

## 3. Progress of implementation
3. Implementation Progress (IP)
(Please indicate the progress made during this financial year in accordance with the implementation plan/annual work plan)
Results and outputs | Indicators (according to the logical framework) | Key achievements of the last 12 months (please DO NOT repeat the results presented in the previous year's annual report) |  |  | Describe any variations in the presentation of the results
Result 1: Mangrove ecosystems and their ecosystem services and goods are managed sustainably to strengthen the resilience of local farming, forestry and fishing communities and to increase biodiversity in demonstration sites.
Result 1.1 Knowledge gaps on the distribution, composition, health, value and resilience of mangrove ecosystems are addressed to inform integrated planning for mangrove landscape management under Result 1.4. | Numerous ecosystem maps, inventories, land cover maps, value assessments, socio-economic analyses and research projects have been undertaken to fill knowledge gaps on mangrove ecosystems. | In accordance with result 1.1, of the 14 planned documents, fifteen (15) have been finalized and validated, and five (5) are currently being implemented. These include: - 14 cartographic products, comprising five (5) maps of potential intervention areas and nine (9) land cover projection maps for mangroves for 2030, 2050, and 2100, developed for the nine (9) municipalities benefiting from the project's intervention: Grand-Popo, Ouidah, Abomey-Calavi, Bopa, Comè, Kpomassase, Sèmè-Kpodji, Aguégués, and Sô-Ava. - One (1) inventory of fauna and flora has also been completed, accompanied by a value assessment and a socio-economic analysis. - Five (5) research projects have been selected and are currently underway (student selection, contract signing, project scope definition). Overall, this objective was 70% achieved by June 30, 2026. |  |  | Fifteen (15) of the fourteen (14) projects are available; five (5) research projects have been selected and are underway.
Result 1.2 Local awareness-raising platforms were created and implemented at demonstration sites to mobilize and involve local stakeholder groups in the planning, implementation and monitoring of mangrove ecosystem management. | Number of awareness-raising events and tools designed, organized and disseminated by local awareness platforms | As part of this initiative, two additional events were organized before June 30, 2026, bringing the total to 23 out of the 25 planned. Furthermore, 20 radio programs were produced to celebrate the International Day for the Conservation of Mangrove Ecosystems (IDCME). |  |  | - Production of a short documentary; - publication on social networks as part of JICEM 2025; - production of radio programs on the following themes: ecosystem services of the mangrove landscape and impacts of climate change on mangrove ecosystems.
Result 1.3 Integrated mangrove landscape management plans are developed/updated to increase climate resilience and support biodiversity in nine municipalities, involving local stakeholders, including the agriculture, forestry and fishing sectors. | Number of integrated mangrove landscape management plans developed/updated | As part of this outcome, nine (9) municipal mangrove ecosystem conservation plans (PCCMs) were developed and adopted atJune 30, 2026- National Strategy for the Sustainable Management of Mangrove Ecosystems: Updated Action Plan for the Management of Mangrove Landscapes of Ramsar Sites 1017 and 1018 (2026-2030). Three (3) documents are currently being developed: - Management Plan for the Grand Nokoué Intercommunity Biosphere Reserve - Management Plan for the Sitatunga Valley Community Nature Park - Simplified Management Plan for the Mangrove Forest of the Togbin-Adounko Community Biodiversity Conservation Area (ACCB) |  |  | - Drafting texts as part of the implementation of municipal consultation mechanisms;
Result 1.4: Integrated mangrove landscape management plans have been implemented in 9 municipalities, promoting innovative and integrated technologies and approaches in the agriculture, forestry and fisheries sectors, thereby contributing to ecosystem restoration, resilience to climate change and biodiversity conservation. | Number of integrated mangrove landscape management plans currently implemented; increase in the biodiversity index (using B-Intact indicators) | The nine (9) plans developed are currently being implemented in the nine municipalities. Indicator: Average Species Abundance (AME): RAMSAR Site 1017 = 33.56% and RAMSAR Site 1018 = 44.24%. Indicator 2a: - AME RAMSAR Site 1017 = 33.56% - AME RAMSAR Site 1018 = 44.24%
Result 1.5 The capacities of Community Biodiversity Conservation Areas (CBCAs), Contract Farmers' Associations (PCAAs) and other relevant local actors have been strengthened in the areas of administrative and financial management, project management and monitoring. | Number of competent, functional, and autonomous community-based citizen organizations (CCOs), pro-community citizen organizations (PCCOs), and other civil society organizations (CSOs) with at least 50% women members. Number of monitoring systems in place and operational. | Six (6) ACCBs and three (3) ACPEs have benefited from capacity building on functionality and are operational. ACCB Bouche de Roy Office: 2/11 = 18.18% women; ACCB Togbin Adoukno Office: 3/7 = 42.85% women; ACCB Vodunto Office: 5/13 = 38.46% women; ACCB LCO Office: 5/11 = 45% women; ACCB Ahémé Office: 5/15 = 33.33% women; ACCB Gbaga Office: 3/11 = 27.3% women; ACPE Sèmè Office: 2/5 = 40% women; ACPE Agugués Office: 2/5 = 40% women; ACPE Vodunto Office: 2/5 = 40% women |  |  | A participatory monitoring plan aimed at ensuring compliance with the rules of operation with IF (DDEFC), DPH and ATDA has been developed and validated.
Result 2: Farming, forestry and fishing communities that depend on mangrove ecosystems adopt alternative, biodiversity-friendly and sustainable livelihoods that strengthen their resilience to climate change.
Result 2.1 Strengthen sustainable and nature-based value chains to increase the resilience of community livelihoods through a participatory and gender-sensitive approach | Number of business plans implemented | Based on the identified value chains, 33 groups and cooperatives were pre-selected and trained in business plan development. For the first phase of value chain support, 31 business plans were selected to receive equipment. Of these 31 groups, only 21 were actually equipped during the first phase. These included: - 5 groups and cooperatives involved in salt production, - 6 involved in market gardening and composting, - 10 involved in fishing and aquaculture, which received equipment and supplies to increase their production capacity and income.
Outcome 2.2 At least three local public-private partnerships established and operational to catalyze investments in nature-based alternative livelihoods and value chains in targeted communities | Number of public-private partnerships created and implemented | Three (03) agreements are being signed with NGOs for the establishment of public-private partnerships in the three areas of the project.
Outcome 2.3 Improved access to financial opportunities for community members – including the most vulnerable and poorest – in mangrove landscapes to support the adoption of sustainable and nature-based livelihoods. | Number of public and private funding sources collaborating on the project | Scheduled for 2026 and 2027
Result 3: Strengthening of national institutional and policy frameworks for the sustainable management of mangrove landscapes in a context of climate change; improvement, capitalisation and dissemination of knowledge on the management of climate-resilient mangrove ecosystems.
Result 3.1 Strengthening of the institutional and legal framework relating to the management of mangrove landscapes (including community management) | Indicator 1: Number of local decrees developed and amendments proposed to policy documents aimed at supporting sustainable and climate-resilient mangrove management. Indicator 2: Number of strengthened institutional coordination mechanisms for integrated mangrove landscape planning. | In addition to the five (5) draft regulatory texts developed and validated in 2025, a knowledge management database has been established for the sustainable management of mangrove ecosystems. These include: - Draft decree on the responsibilities, organization, and operation of the consultation framework for stakeholders involved in the sustainable management of mangrove ecosystems in the Republic of Benin; - Draft decree on the recognition, creation, and management of community protected areas (CPAs) and community biodiversity conservation areas (CBCAs) in the Republic of Benin; - Draft order establishing the principles for the management, legal recognition, and integration of mangrove ecosystems into the protected areas system; - Code of good conduct for the management and use of mangroves; - Charter for the conservation and sustainable management of mangrove ecosystems
Result 3.2 Capacity building plan designed and implemented for government institutions working on mangrove management in Benin and the region, to support integrated, participatory and gender-sensitive processes for sustainable management of mangrove landscapes in a context of climate change. | Number of capacity-building events organized for government institutions | A workshop is planned for 2026 and 2027 to strengthen the capacities of local administrations (ATDA, town halls, DDEFC, DPH, ABE, CENAGREF) in the field of ecological restoration of mangroves. |  |  | Arrangements are being made for the implementation of this activity.
Result 3.3 Knowledge and awareness of the conservation and sustainable use of climate-resilient mangrove ecosystems are strengthened to facilitate decision-making at national, regional and global levels. | Number of knowledge-sharing events organized and tools developed and disseminated | A national mangrove data-sharing platform exists and is operational. Communication equipment has been acquired to improve the project's visibility.as of June 30, 2026
Result 3.4 Implementation of the project monitoring and evaluation plan | Number of monitoring and evaluation reports submitted | Twelve (12) reports have been produced to date. Of these twelve reports, five (5) were produced in the last twelve months.
Progress of implementation and overall assessment
Please note that overall intellectual property assessments must be supported by the evidence and progress presented above. Assessments and comments must reflect overall performance over the financial year (July 1, 2025 to June 30, 2026).
| Project Manager/Coordinator | Senior Technical Manager | Budget manager | Operational Focal Point (FFO) of the GEF | FEM Technical Officer (GTO)
FY2026 Implementation Objective rating10 | Satisfactory (S) | Satisfactory (S) | Satisfactory (S) | Satisfactory (S) | Satisfactory (S)
Comments/reasons for the ratings for the 2026 financial year and any changes (positive or negative) to the ratings since the previous reference period | At the end of June 2026, the overall project execution rate is 57.54% and the execution rate of the 2026 annual work plan as of June 30 is 46%. | Despite the somewhat late start of the project in 2023, execution is proceeding normally and the results obtained are satisfactory thanks to the effectiveness of the monitoring system put in place. | Financial resources are allocated based on expressed needs. As of June 30, 2026, a single transfer of US$562,895,835 has been made and is being processed according to the established procedure. | The operational focal point organised a follow-up mission in March 2026 to the project's intervention communes to inquire about the progress and difficulties encountered. | Implementation of the annual work plan is progressing, and value chain support has reached the target groups. The main challenge identified by the team concerns procurement, which is managed by a central authority without dedicated support within the project unit. Addressing this staffing gap could accelerate project implementation during its remaining timeframe.
9. The variance represents the difference between the planned progress and the actual progress at the time the report was submitted. 10. Implementation progress assessment – ​​Evaluation of the extent to which the implementation of a project's components and activities is in line with the approved implementation plan.

## 4. Summary_Progress and Challen
4. Summary of progress and challenges
Please provide a summary paragraph on the progress of project implementation, in accordance with the information presented in sections 2 and 3 of the preliminary assessment report (maximum 400 words) (This section will be uploaded to the GEF portal).
The implementation of project activities, covering the period from July 1, 2025 to June 30, 2026, has led to significant progress: - the implementation of nine (9) community-based mangrove landscape conservation plans, covering a total area of ​​245,627 ha, including 3,139.75 ha of mangroves; - the continued implementation of agreements signed with co-management associations; the renewal of agreements with NGOs following satisfactory evaluations; - the increase in the restored area from 43.3 to 47 ha; and the reforestation of…Acacia auriculiformisThe area increased from 25.25 ha to 29 ha; - the reopening of waterways invaded by vegetation progressed from 10.9 km to 12 km; - several study reports were validated and finalized; - documents relating to the development and certification of a carbon project linked to the reduction of wood energy consumption in the Mono and Atlantic mangroves were validated; - equipment was acquired and given to the nine (9) environmental clubs "Young Ambassadors of the Mangrove" as part of school plantings; two sessions of the National Steering Committee were organized; - two consultation frameworks and a Federation of co-management associations were established; following the study to identify agricultural value chains, - 33 groups and cooperatives were shortlisted and trained in the development of business plans. For the first phase of support for income-generating activities (IGAs), 21 groups were selected and received equipment to increase their production capacities and incomes.
Please provide a summary paragraph on the difficulties encountered during the implementation of the project, in accordance with the information presented in sections 2 and 3 of the preliminary evaluation report (maximum 400 words) (This section will be uploaded to the GEF portal).
- The lack of vehicles hinders the smooth running of field activities. The project covers nine municipalities in southern Benin. Most activities take place in the field and sometimes require the use of boats to reach the beneficiary communities. Unfortunately, the acquisition of vehicles to allow the Project Management Unit (PMU) to work easily was not planned. It is not uncommon for PMU staff to resort to public transportation to achieve their objectives. This constitutes a real obstacle to achieving results. - Lack of a procurement specialist. Purchases made under this partnership with FAO are carried out according to the OPIM approach. This is a management method based on the national procedure that involves the central procurement officer, known as the PRMP. Unfortunately, the Mangrove project does not have a public procurement specialist to liaise with this organization, which causes a significant delay in the project's procurement process.
Implementation of the exit strategy
Has the project developed an exit strategy? If so, please describe the progress made in its implementation. | The project is led by the Directorate General of Water, Forests and Hunting (DGEFC), which oversees it at the national level. This structure aims to ensure its sustainability. Municipalities are closely involved in the implementation and monitoring of activities. Forest management activities (reforestation, restoration, creation of biological corridors) are carried out by community management structures using mangrove landscape planning and management tools. NGOs are operational partners; they conduct mobilization and social inclusion activities and support the establishment of value chains.
How does this project strengthen institutional capacities to foster national ownership and achieve more sustainable results? | The Project Management Unit (PMU) involves government institutions, NGOs, co-management structures (ACCB/ACPE), and communities at all stages of planning, development, and validation of studies and technical reports. The project organizes capacity-building activities for co-management structures (ACCB/ACPE) and women's groups, led by local NGOs in partnership with municipalities. Three consultation frameworks, including a federation, are in place to ensure cohesion among the co-management structures in the different mangrove areas.

## 5. ESS Risk
5. Environmental and Social Protection Measures (ESPMs): Project-related risks
Initial classification of risks related to ESS systems (at the CEO approval stage) | Moderate
New environmental and social risks. | The mangrove landscapes of the ACCBs of Togbin-Adounko, Vodunto, and the Coastal Lagoon are included in the government's "Fishing Route" program, which also promotes ecotourism. A study is underway to assess the environmental and social risks.
Progress made in the implementation of the Environmental and Social Management Plan (ESMP) (only for moderate and high risk projects) | ESS No. 1 Natural Resource Management - Mangrove ecosystem management is integrated into the new forestry plan currently being developed. Its adoption will allow for the implementation of regulations at the local level. - Radio programs on ecosystem services and climate change are broadcast in local languages ​​and French in the municipalities concerned. - All municipalities have received a municipal mangrove management plan. ESS No. 2 Biodiversity, Ecosystems, and Natural Habitats - Implementation of forest management agreements covering the restoration of 60 hectares of mangroves and the creation of 38 hectares of reforestation and fuelwood plantations. - 16 km of waterways have been developed to facilitate the movement of small boats. ESS No. 3 Plant Genetic Resources for Food and Agriculture - The project does not introduce seeds and prioritizes native species. - An environmental impact assessment will be conducted for the business plans of income-generating activities. - Plantations are established manually in accordance with environmental standards. The seeds used are of local origin. ESS No. 4 Animal Genetic Resources (Livestock and Aquatic Species) for Food and Agriculture: A consultant is being recruited to: - Design and implement, with local government institutions and in collaboration with ACCBs and ACPEs, a biomonitoring system covering: i) ecosystem regeneration, degradation, and health; and ii) the evolution of mangrove species of major ecological and economic importance. - Design and implement a monitoring plan to ensure compliance with forestry regulations, using a participatory approach with forest inspections, DPHs, and ATDAs. ESS No. 7 Decent Work: - The project is implementing the action plan for gender equality and social inclusion to ensure that all categories benefit from the interventions. The implementation of value chain reports and business plans will be an important step towards the implementation of component 2 of the project, which promotes sustainable green jobs and improves mangrove ecosystems. As part of the restoration and reforestation activities, seven forest management agreements worth 200,380,440 FCFA have been signed. These agreements are currently being implemented by management structures such as ACCB Vodounto, ACCB Chenal de Gbaga, ACCB Lac Ahémé, ACCB Togbin Adounko, ACPE Aguégués, Sèmè-Kpodji and Sô Ava. Youth and women's groups participate in these restoration and reforestation activities through the management of these agreements.
Grievance Resolution Mechanism (GRM) | In January 2026, the Project Management Unit: - established three (3) zonal platforms, coordinated by the umbrella platform, working together to boost and coordinate mangrove conservation efforts, facilitating information sharing and support for village committees through ACCB/ACPE. - supports the establishment of the "Biodiversity Alert" platform with Eco-Benin in the municipalities and in Ramsar sites 1017 and 1018 to manage any conflicts and disputes between grassroots communities for the sustainable management of mangrove ecosystems in southern Benin.

## 6. Project-related risks
6. Project-related risks
The following table summarizes the risks identified in the project document and also reflects any new risks identified during the implementation of the project.
| Type of risk |  | Risk assessment | Identified in the ProDoc Y/N | Description of risks | Mitigation measure implemented
1 | Environment |  | Moderate | Yes | Considering current climate trends and future climate projections is essential for the project's success. ANR sites will be selected based on models of future habitat potential under various climate scenarios. These sites, available at a later date, will be integrated as much as possible into community-managed mangrove conservation areas. Information on mangrove resilience to sea-level rise and increasing salinity remains limited but is improving. For example, it is now known that Avicennia germinans is more resistant to high salinity than Rhizophora racemosa. This updated knowledge will be used, and conservation and restoration activities will be designed based on the species-site combinations with the best chances of long-term success for each sub-site. Furthermore, research projects on species and ecosystem resilience will be initiated within the project to address knowledge gaps and support the design of future climate-resilient restoration efforts. | Mapping studies and flora and fauna inventories have led to a better understanding of mangrove ecosystems in the project's intervention areas. Similarly, municipal mangrove conservation plans, whose implementation has initiated hydrological restoration in the Togbin Adounko Community of Municipalities (ACCB) and the process of establishing Community Mangrove Management Frameworks (CGCM), have also been implemented. Through the implementation of forest management agreements with co-management structures (ACCB/ACPE), several core mangrove areas have been designated as protected zones in the nine (9) project municipalities to strengthen measures for the protection and conservation of mangrove ecosystems.
2 | Institutional |  | Moderate | Yes | Inter-institutional cooperation has been identified as one of the obstacles the project must overcome. Several interventions have therefore been specifically designed to strengthen knowledge sharing and support integrated planning processes. The respective role of each institution in the management of mangrove ecosystems will be clarified, inter-sectoral collaboration for knowledge sharing and consultative decision-making processes will be strengthened, and decision-support tools will be developed to facilitate inclusive processes (Outcome 3.1). | The regular meetings of the Mangrove Project's National Steering Committee (NSC), held every six months, provide a forum for dialogue among the various stakeholders and institutions involved. These meetings allow for discussions on synergy and guide the Project Management Unit (PMU) towards improved management of mangrove ecosystems. Furthermore, the establishment of consultation frameworks for mangrove ecosystem management (CC-ACEM) and their federation (FN-ACEM) have facilitated cooperation within the co-management structure, thereby promoting better knowledge sharing about these ecosystems.
3 | Legal and regulatory |  | Moderate | Yes | The project design incorporated lessons learned and best practices in behavior change in the intervention areas, thus providing concrete solutions to overcome the identified risk. Local implementing decrees, supplementing national legislation, will be developed where necessary to optimize implementation by local authorities. Information on best practices, as identified in the management plans, will be widely disseminated to the populations of the targeted municipalities and neighboring municipalities through various media and events. Furthermore, community leaders (religious leaders, traditional chiefs, youth leaders, etc.) will be closely involved at every stage of project implementation. They will play a crucial role in identifying measures to encourage the adoption of good practices and the abandonment of harmful ones. Their influence makes their support for the project essential, as it should facilitate community compliance with local regulations. | Within the framework of the PTAB 2026 (Agricultural and Forestry Action Plan 2026), a charter for the conservation and sustainable management of mangrove ecosystems, as well as a code of conduct for mangrove management and use, were developed to facilitate the sharing of knowledge and best practices in mangrove ecosystem management. Similarly, to better involve local communities in the project's implementation, forest management agreements were signed with the ACCB/ACPE co-management structures. Furthermore, an agreement was signed for the management of the Sitatunga Valley, which constitutes an additional management area beyond the nine planned by the project, and enabled the development of management rules for four localities: Zinvié, Kpanrou, So-Ava, and Akassato.
4 | Safety and security |  | Weak | Yes | Security measures will be implemented for all individual and group meetings. The budget for each training and awareness session includes sufficient funds to ensure the implementation of necessary security measures throughout the project (e.g., sanitary supplies, rental of spacious, well-ventilated, and properly equipped premises). Virtual meetings will be organized at the central level if necessary. Authorizations to continue field operations during critical phases at the local level will be granted as needed, while respecting the safety of staff, community members, and partners. As the project is primarily focused on local actors, a temporary shift in government priorities in the event of a new health crisis is not expected to have a significant impact on its implementation. | Social distancing measures are being respected at the UGP level because most of the meetings organized from July 2025 to June 2026 are being held via video conference in order to avoid the risks associated with the second wave of COVID.
5 | Partnership and coordination |  | Low | Yes | The low level of community involvement in decision-making and uncertain access to natural resources have led some communities to disengage from projects. Previous initiatives, lacking full support from local communities, have met with very limited success. Community interest in the project's approach (adoption of sustainable, nature-based livelihoods and/or mangrove conservation) was integrated as a criterion for selecting intervention sites and defining interventions during the participatory planning phase. Community motivation and ownership of the interventions will be essential for their implementation at each site, as they are a prerequisite for success. Active community participation and contributions during kick-off meetings and participatory decision-making processes at the beginning of the project will confirm their interest. The expected financial benefits of strengthening sustainable, nature-based value chains will help maintain community motivation to protect mangrove ecosystems in the long term. | In addition to the agreements signed and implemented with Community Action Groups for Environmental Protection (CACB/ACPE), which strongly involve communities in the management of mangrove ecosystems, several groups and cooperatives have been selected, trained, and are receiving project support in the form of equipment. Furthermore, nine "Young Mangrove Ambassadors" environmental clubs have been established, trained, and equipped to liaise with the project within the beneficiary communities. The project has also partnered with three NGOs for social inclusion and community mobilization activities.
Overall project risk assessment (low, moderate, significant or high):
Note regarding the 2025 financial year | Note regarding the 2026 financial year | Comments/reasons for the rating for the 2026 financial year and any changes (positive or negative) to the rating since the previous reference period
Moderate | Low | Substantial mitigation measures have already been implemented, including the signing of agreements with co-management associations, support for groups and cooperatives, and the creation of environmental clubs. These actions demonstrate a strong commitment from stakeholders and contribute positively to reducing implementation risks.
11. Risk assessment consists of evaluating the overall risk associated with internal or external factors that could affect the implementation of the project or the prospects for achieving its objectives. The project risk should be assessed on the following scale: low, moderate, significant, or high.

## 7. MTR Tracking
7. Follow-up to the mid-term evaluation or supervision mission
If the project was subject to a management review or follow-up in 2025, please indicate how the recommendations were implemented during that financial year, as detailed in the management response or follow-up report.
Recommendations from the MTR or the supervisory mission | Measures implemented during this financial year
Recommendation 1:
Recommendation 2:
Recommendation 3:
Recommendation…
Recommendation…

## 8. Minor modifications
8. Minor modifications made to the project
Minor modifications refer to changes in design or implementation that do not significantly affect the project's objectives or scope, or an increase in GEF funding for the project of up to 5%, in accordance with Annex 9 of the GEF Project and Programme Cycle Guidelines. 12. Please describe any minor project modifications in the appropriate category or categories and provide supporting documentation as an annex to this report, if applicable. (This section will be published on the GEF portal.)
Category of change | Please describe the modification. | Indicate the time of the change | Approved by
Results framework
Components and cost
Institutional and implementation arrangements
Financial management
implementation schedule
Executing entity
Category of executing entity
Minor modification to the project's objective
Guarantees
Risk analysis
Funding for GEF projects has increased by up to 5%.
Co-financing
Location of the project activity
Other minor modifications made to the project (to be defined)
Documents, guidelines and policies relating to the GEF Council's project and programme cycle (2020 update)

## 9. Mobilization of stakeholders
9. Stakeholder mobilization
Please report on the progress made, challenges encountered, and results achieved through stakeholder engagement (as described in the stakeholder engagement plan) included in the CEO approval during the reporting period. (This section will be published on the GEF portal.)
Profile | Name of the stakeholder | Type of partnership | Progress, results and challenges in stakeholder engagement
government institutions | DGEFC | Key | She oversees the national project and sits on the steering committee. Strategically, she facilitates communication with the FAO and the Project Management Unit. She contributes to the implementation of reforestation activities and the opening of waterways to facilitate navigation, commercial traffic, and fishing. In the face of future challenges, she will need to continue the actions mentioned above.
government institutions | DGEC; ABE; CENAGREF; DPH; DDAEP; CIF | Key | They are members of the project's steering committee and participate in its monitoring and control. They continue to support the project in its activities related to climate change adaptation and the regulation of fishing activities.
NGO | ECO-BENIN; ACTION PLUS; BEES NGO; etc. | Key | These are operational partners of the project who carry out mobilization and social inclusion activities, particularly in the areas of information, education and communication, as well as capacity building. They must contribute to the success of restoration, reforestation, river opening, sanctuary creation, and other projects.
private sector entities | Microfinance structures (AVEC, DAME, CAVECA, Alidé, PADME); private sector companies involved in value chains, etc. | Secondary | The activities for which these structures are needed have not yet begun. Faced with these challenges, the UGP must establish links with these structures to ensure their effective participation.
Others | Universities and research laboratories (LABEF; LEA) etc. | Key | As part of the partnership with universities, five Master's level research agreements were signed with research laboratories in May 2026 with the aim of addressing knowledge gaps regarding mangroves. The research is currently underway.
Others | Community Biodiversity Conservation Area Co-management Associations (CBCAs), Community Environmental Protection Associations (CEPAs), and other relevant community organizations | Primary | Community management associations (ACCB/ACPE) and other community organizations benefit from capacity building and implement forestry activities, while disseminating the acquired concepts to their peers. "Faced with the challenges, we must adhere to the project guidelines and continue eco-citizen monitoring for the preservation of mangrove ecosystems."
Others | Town Halls | Primary | They are responsible for implementing management tools, including municipal mangrove conservation plans (PMCMs) developed within the framework of the project. They are members of the project's steering committee and participate in its monitoring.

## 10. Genre
10. Integration of the gender dimension
Information on progress made on gender-responsive measures, as documented during the Director-General's approval of the Gender Equality Action Plan or equivalent document (where applicable) during the reporting period. (This section will be published on the GEF portal.)
Category | Yes/No | Briefly describe the progress and results achieved during the period under consideration.
a. Reduce gender inequalities in access to and control over global natural resources | Yes | - Integration of the specific needs of women (access to land, participation in resource management activities, etc.) in the 9 Municipal Plans for the Conservation of Mangrove Ecosystems (PCCM); - Restructuring of the management bodies of the ACCB/ACPE, increasing the percentage of women to approximately 45%; - Integration of the gender dimension in the update of the management plan of the Sitatunga valley (document in preparation).
b. Improve women's participation and decision-making | Yes | "- Active participation of women in the establishment of consultation frameworks on Ramsar sites, according to the principle of 50% women; - Support for projects of women's groups and cooperatives for the development of business plans; - Organization of awareness sessions in order to strengthen dialogue between women and men within communities.
c. generate socio-economic benefits or services for women | Yes | - Increased income through women's participation in site and mangrove restoration and reforestation. - Capacity building and support in the form of materials and equipment for fishing/aquaculture, salt production, and market gardening/composting groups and cooperatives to improve their production and income. - Selection of women's groups and cooperatives to benefit from income-generating activities (IGAs).
Other good practices in gender | Yes | - Support for women nursery owners to obtain accreditation, enabling them to fully engage in the activity and increase their income; - Integration of the gender dimension into all project activities (workshops, meetings, validation, consultations, etc.); - The project has ensured increased representation of women in the management bodies of co-management structures and in consultation frameworks; - Integration of the gender dimension into the selection criteria for groups and cooperatives; - Creation of nine (9) environmental clubs “Young Ambassadors of the Mangrove” in the intervention municipalities, composed of 50% girls, in order to promote good environmental practices.

## 11. Knowledge Management
11. Knowledge and learning activities
Knowledge management activities and products (if any), as described in the CEO-approved knowledge management (and learning) approach, during the reporting period. (This section will be published on the GEF portal.)
Knowledge management and learning (KML): Does the project have a KML strategy? | Yes
If so, what is the current state of its implementation? Please describe in your response how the project promotes knowledge sharing and learning among stakeholders at national and international levels. | The project has a database and a knowledge-sharing platform: - knowledge base: https://mangroves.gouv.bj - databasehttps://mangroves.gouv.bj/tableau de bord/.Each member of the Project Management Unit (PMU) and the field team has an account to upload project-related documents to the database. This upload is done monthly. After validation by the coordinator, the communications specialist disseminates the communication materials to the general public via the knowledge-sharing database. The platform is accessible to everyone, while the database centralizes the data produced by the PMU.
Otherwise, how does the project identify, collect, and document good practices? | This project identifies best practices through communication, exchange, and networking activities. Individuals recognized for these best practices are invited to share them with their peers. These practices are also documented through short videos and excerpts shared in the database.
Please list the good practices, including key technical and/or institutional innovations, implemented so far within the project. | - Use of sunlight, black tarpaulins, and seawater for salt production. - Production of compost as a replacement for chemical fertilizers. - Use of legumes to restore soil fertility: the case of mucuna. - Creation and management of environmental clubs of "young mangrove ambassadors" for training in nurseries and plantations. - Management of mangroves according to indigenous practices of sacred preservation.
Communication strategy: Does the project have a communication strategy? | Yes
Please provide a brief overview of the successes and difficulties in communication encountered during this exercise. | - Creation of a network of young mangrove ambassadors for environmental clubs, serving as communication relays at the community level. - Organization of activities on mangrove ecosystem services and the impacts of climate change on five community radio stations (Ahémé FM, Mono FM, Tado FM; Gerdès FM and Radio Kpassè in French and the local language). - Production of modules for environmental clubs on environmentally friendly techniques and on training for women's leadership (children's panel). The difficulties encountered were: - Lack of television in the project communities to support the initiatives; - Lack of vehicles to achieve the set objectives.
https://drive.google.com/file/d/1x0hExWRDeKNk-PWQYf0-1BS2OJ30sO-2/view?usp=drive_link
https://drive.google.com/file/d/1Pa5TuIvkvFRJviJyonro1TkmL8H2RqZC/view?usp=drive_link
https://drive.google.com/file/d/1z4BsrS_3-8e6kGyepT1fbPBXydsVcxxA/view?usp=drive_link
https://drive.google.com/file/d/1hnVoorF76FP5IAcbU6sVoi_JCFQA7Zu3/view?usp=drive_link
https://drive.google.com/file/d/1z4BsrS_3-8e6kGyepT1fbPBXydsVcxxA/view?usp=drive_link
Please provide links to associated websites and social media accounts. | https://mangroves.gouv.bj https://mangroves.gouv.bj/tableau de bord/.
Please provide a list of publications, leaflets, videos, newsletters or other communication materials published on the Web, if applicable. | - Recording of 20 radio broadcasts in the communes on five community radio stations with a large audience on ecosystem services and the impacts of climate change with experts (Tado Fm 106.3 in (French and Xwémè) for the communes of Abomey-Calavi and Sô-Ava; Mono Fm 97.7 in (French and Mina) for the communes of Comè and Grand-Popo; Radio Kpassè 93.8 in (French and Pédah) for the communes of Ouidah and Kpomassase; Fm Ahémé 87.7 in (French, Aizo and Wla) for the commune of Bopa; Gerdess Fm 89.5 in (French, Goun and Tofin) for the communes of Aguégués and Sèmè-Podji.
Please provide the name and contact details of the focal point for communication and/or knowledge management. | - Communication focal point: OLLOUDE Mobèrèola Oloufounmilayo; 0195404572; funelleolive@yahoo.fr - Knowledge management focal point: SALAMI Abdou Gafar Agnila; 0197874305; g1salami@yahoo.fr

## 12. Indigenous Peoples
12. Participation of Indigenous Peoples and Local Communities
Are Indigenous peoples and local communities involved in the project (as per the approved project document)? If so, please explain briefly.
Yes, with local communities. The project collaborates with Biodiversity Conservation Area Management Associations (BCAAs). These associations bring together local elected officials, traditional leaders, representatives from various sectors, youth, and women, and thus actively and effectively participate in the project's decision-making and implementation. As part of its activities, the project has signed ten (10) forest management agreements with these associations for the restoration, reforestation, and opening of waterways or ecological corridors. Local labor is widely employed to carry out the work in the project's intervention areas.

## 13. Co-financing
13. Co-financing table
Sources of co-financing | Name of the co-funder | Type of co-financing | Amount confirmed after CEO approval (in USD) | Amount actually realized as of June 30, 2025 (in USD)
Government of the beneficiary country | MCVDD | Public investment | 58640000 | 0
GEF Agency | FAO | Subsidies | 4224797 | 524172
Total |  | Total | 62864797 | 524172
Please explain any significant changes in project co-financing since CEO approval, or any discrepancies between promised and actual co-financing amounts.
GEF Co-financing Guidelines 2018

## 14. Geographical location
14. Geolocation information
This section should only be completed by projects that have been the subject of an initial Preliminary Assessment Report (PAR) and if the geographical coverage of the project's activities has changed since the last reporting period. This information is required by the GEF Secretariat on the GEF portal.
Have there been any changes in the geographical coverage of project activities since the last PIR report? |  |  |  | No |  | 3rd PIR
Place name | Latitude | Longitude | Geographic name identifier |  | Description of the location and activity*
Directorate General for Water, Forests and Hunting/Ministry of the Environment and Transport responsible for sustainable development | 6.3656 | 2.4642 |  |  | Headquarters of the project management unit in Cotonou, Benin
Abomey-Calavi | 6.4539 | 2.3542 |  |  | Municipalities benefiting from project interventions at RAMSAR site 1018
Aguégués | 6.4533 | 2.5436
Kpomasse | 6.445 | 2.0137
Sémè Kpodji | 6.3815 | 2.6045
Sô-Ava | 6.497 | 2.4005
Bopa | 6.5893 | 1.9669 |  |  | Municipalities benefiting from project interventions at RAMSAR site 1017
Come | 6.4042 | 1.8841
Grand-Popo | 6.2764 | 1.8067
Ouidah | 6.3666 | 2.0854

## GEF Indicators 6 and 7 (PMA)
Basic Indicators_LDCF FEM-6 and FEM-7
For LDC projects funded by GEF-6 and GEF-7, please indicate the cumulative total achieved since the beginning, if this information is included in the implementation document.
Basic indicator 1 | Total | Male | Women | % of women
Total number of direct beneficiaries | 5438 | 2794.5882 | 2643.4118 | 48.61%
Basic indicator 2
Area of ​​land managed for climate resilience (ha) | 245627
Basic Indicators 3
Total number of policies/plans integrating climate resilience | 10
Basic indicator 4 |  | Male | Female | % of women
Total number of people trained | 2847 | 1200 | 1647 | 57.85%
Questions? Contact our support team: faogef-pir-support@fao.org

## Appendix
Annex. Monitoring of commitments relating to GEF core indicators by area and progress made under the GEF
The Ecosystem Restoration Monitoring Framework (FERM), developed by FAO, is the official platform for monitoring global progress and disseminating good practices for the UN Decade on Ecosystem Restoration. FERM can serve as an integrated GIS platform, enabling GEF staff and all relevant stakeholders to visualize progress on restored or improved lands for conservation and sustainable use, as well as specific results such as project completion percentages. This common monitoring platform allows users to comprehensively assess and report on project progress. A user-friendly dashboard displaying project results allows stakeholders to clearly understand the extent to which objectives have been met. Projects with GEF baseline indicators by area (GEF baseline indicators 1 to 5 and PLM baseline indicator 2) are encouraged to register on the FERM platform.
Useful links:
• FERM website
• FERM User Guide (PDF)
• YouTube channel closed
• Send an email to Carmen Morales
It also helps countries to report areas under restoration for objective 2 (Areas under restoration) of the GBF Kunming-Montreal, for which FAO is the responsible agency.