# Planning and Financing Adaptation in Niger

GEF Secretariat Review for Full Sized Project – GEF - 6

Basic Information

GEF ID

8020

Countries

Niger

Project Title

Planning and Financing Adaptation in Niger

GEF Agency(ies)

UNDP

Agency ID

UNDP: 5336

GEF Focal Area(s)

Climate Change

Program Manager

Katya Kuang-Idba

PIF

CEO Endorsement

Project Design and Financing

1. If there are any changes from that presented in the PIF, have justifications been provided?

Secretariat Comment at CEO Endorsement

9/11/2018 - More information requested. A detailed matrix in Section 1 of Part II summarizes all changes in the CEO ER from PIF stage. The main change is that the focus of the intervention has been narrowed down to the water sector, from the multi-sectoral approach presented at PIF.  The focus of the proposal has been shifted accordingly throughout. Additionally, outputs under component 2 have been revised as follows:

Output 2.1, as a result of PPG consultations, only five of the originally targeted 15 villages corresponded to the criteria set for the selection of villages (which includes the depth of available water table resources that were neither too easily available, making such an investment irrelevant, or too deep making the investment too costly).

Under output 2.2, following PPG-stage consultations, it was decided that instead of focusing on 3 large scale multi-purpose pilots, that the project would focus on smaller scale infrastructures, which would reach more people and have more replication potential.

Additionally, "other minor revisions were made since the PIF, including reformulation of components, outcomes and outputs, to clarify them and align them better with the activities."

RECOMMENDED ACTION: If the value amount for component 2 remains as at PIF stage, please justify how the resources will be reallocated from 15 pilots to just 5, and how the remaining resources will be re-allocated. Additionally, please briefly clarify if all the "other minor revisions" indicated in the last sentence are referring to changes in wording only. If there are substantive changes, please list them here.

GEFSEC, 4/2/2019 - Cleared. The agency has clarified that while the number of villages was reduced from 15 to 5, the infrastructure will cover an equivalent area as originally envisioned. The agency has also reiterated that all other revisions are related only wording and syntax for clarity.

Response to Secretariat comments

sans-serif

UNDP, 11 February 2019

For Output 2.1. as explained in the table, most of the initially targeted villages are not expected to have the adequate water resources for sustainably pumping ground water, therefore, only five villages were selected during the PPG phase. However, even though the number of villages was reduced to 5 instead of 15, the infrastructures will have larger capacities than planned under the PIF and cover an equivalent area. This is expected to provide economies of scale, that will be partly covered by the in-depth feasibility study that will provide detailed data on the sustainability of the infrastructures. This increased cost for the study can be explained by the need for exhaustive and more reliable data, caused by a growing concern about the use of water table resources, that are becoming exponentially scarcer in this region.

For output 2.2. the cost has not been reduced as more infrastructures and investments than planned will be done under the PIF (3 large infrastructures were planned under the PIF). This can be explained as smaller scale infrastructures in the agriculture sector were found to be more impactful and more replicable. The choice of building a dam or other large-scale infrastructure would not have enabled local communities to build on the lessons learned to replicate the dams to further streams due to financial constraints.

Regarding the comment on minor revisions, these revisions are only related to wording and this was clarified in the table.

2. Is the project structure/ design appropriate to achieve the expected outcomes and outputs?

Secretariat Comment at CEO Endorsement

9/10/2018 - Clarifications requested. While the project components seem to support the delivery of the intended objective and and outcomes, some outputs do not seem to be quantifiable or measurable.

RECOMMENDED ACTION: It would appreciated if some of the outputs could be re-written so as to ensure they are concrete, tangible, measurable, and quantifiable against the delivery of the expressed outcomes. For example:

- -  Output 1.2: National, subnational and local stakeholders have an adequate understanding of CCA practices related to sustainable water resources management  - Within this context, what constitutes an "adequate" understanding?

- - Output 2.1:  Hybrid household water supply solutions and smallholder irrigation systems are successfully promoted in vulnerable communities - Within this context, what is "successfully"?

Additionally, the components seem to be listed out of order. Please ensure that the components are listed correctly, corresponding to how the project is structured and in line with the results framework.

GEFSEC, 4/2/2019 - Cleared. While output 1 is still not really written as an output, measuring the understanding of these stakeholders is difficult. It appears that this "understanding" will be measured by the number of municipalities integrating CCA into water sector policies. Other outputs have been revised accordingly, as requested.

Response to Secretariat comments

sans-serif

UNDP, 11 February 2019

Both outputs have been reformulated as follow:

-       Output 1.2: National, subnational and local stakeholders understand CCA practices related to sustainable water resources management

-       Output 2.1: Hybrid household water supply solutions and smallholder irrigation systems are promoted and adopted in vulnerable communities

The outcomes and components were revised in the stakeholder’s engagement table and the project result framework table.

The revised outputs are now excluding the vague terms “adequate” and “successful” and are measurable through the achievement of the activities as detailed in the project document.

3. Is the financing adequate and does the project demonstrate a cost-effective approach to meet the project objective?

Secretariat Comment at CEO Endorsement

9/11/2018 - Not clear. Due to issue with the Portal system, the CEO ER was submitted without the the relevant values in Tables B,C, and D.

RECOMMENDED ACTION: The Portal issues have now been resolved, so please populate the relevant tables with the correct value figures. Additionally, please briefly indicate how the proposed activities are cost-effective in comparison with feasible alternatives.

GEFSEC, 43/2019 - More clarification requested. While there are some indications of alternatives which are not cost-effective, there is no succinct summary of this project's cost-effectiveness.

Recommended Action: Please briefly summarize the points in gleaned through the alternatives analysis to demonstrate the basis for cost-effectiveness presented by this project's design.

GEFSEC, 6/22/2019 - Cleared. The agency has indicated that project activities will be based on existing and ongoing structures and initiatives, and has added detailed information justifying the selection of project activities and how they are more cost-effective than alternatives.

Response to Secretariat comments

sans-serif

UNDP, 11 February 2019

The cost-effectiveness compared to other feasible activities had already been briefly presented in the Prodoc p44 (V.1 Cost-efficiency and effectiveness). This has now been also added in the CEO ER under the section A1. 6) Innovativeness, sustainability and potential for scaling up.

UNDP, 6/5/2019 - A succinct summary was added under section 6 “Innovativeness, sustainability and potential for scaling up”.

4. Does the project take into account potential major risks, including the consequences of climate change, and describes sufficient risk response measures? (e.g., measures to enhance climate resilience)

Secretariat Comment at CEO Endorsement

9/11/2018 - Yes. The risk matrix is adequately developed and presents a comprehensive list of potential major risks, along with sufficient mitigation measures.

Response to Secretariat comments

sans-serif

5. Is co-financing confirmed and evidence provided?

Secretariat Comment at CEO Endorsement

9/11/2018 - More information requested.

RECOMMENDED ACTION: Please indicate whether co-financing letters have been included in the portal submission, as they do not seem to be readily accessible on the Roadmap for this project. Additionally, please provide a stronger rationale for using the GCF-funded Readiness project as co-financing - please clarify whether the project being referred to as co-financing is a Readiness project or a NAP project. If this is a NAP readiness project, it seems to make more sense to include it as part of the baseline scenario, as opposed to a baseline investment that is providing co-financing.

GEFSEC, 4/2/2019 - Not cleared. I do not see the co-financing letters in the Roadmap section of this submission.

Recommended Action: Please upload the co-financing letters to the Roadmap section of the Portal. If I have missed them, apologies.

GEFSEC, 6/22/2019 - Not cleared. The co-financing letters do not seem to be on the  Portal.

Recommended action: Please upload the co-financing letters onto the Roadmap section of the portal.

GEFSEC, 7/8/2019 - Cleared. The co-financing letters have now been uploaded onto the portal.

Response to Secretariat comments

sans-serif

UNDP, 11 February 2019

Co-financing letters have now been included in the portal submission[CG1] .

The NAP-GCF project is a NAP project, financed through the Readiness window of the GCF for NAP projects (see the readiness support page “The GCF Board has also allocated up to USD 3 million per country for the formulation of national adaptation plans and/or other adaptation planning processes by NDAs or focal points. This support can facilitate the development of National Adaptation Plans, which set national priorities for measures to address adaptation to climate change”).

This project appears both in the baseline and in the contribution from co-financing. This can be explained by the strong synergies between both projects. Synergies will take the form of shared results and objective – national adaptation cannot be achieved through the adaptation of the different sectors independently and needs to be conducted through the coordination of the process between sectors. In particular, the water sector is a cross-cutting sector in the area of adaptation, which is critical for health, food security, water security, gender equality, etc. In addition, both projects were formulated with a strong involvement of the national counterpart (CNEDD) that facilitated and ensured the coordination between both initiatives. This synergy was initiated during the workshop that was held in August 2018, which gathered the same key stakeholders for both the inception workshop of the GCF-NAP project and the validation workshop of the PFNAC. The Prodoc provides more details about the synergies throughout the section “IV.2 Components, outcomes, outputs and activities”, where the outcomes 1 and 3 are building on the results of the NAP-GCF project.

JP- 15May2019: the co-financing letters are uploaded to portal.

JP - the co-financing letter is uploaded as showned below

6. Are relevant tracking tools completed?

Secretariat Comment at CEO Endorsement

9/18/2018 - Please be advised that the Secretariat is currently in the process of programming the GEF-7 core indicators into the Portal, and the agency will be asked to asked to input the information into the Portal once it has been programmed.

GEFSEC, 4/2/2019 - In line with the Adaptation Program’s efforts to align more closely with GEF Trust Fund procedures, we have developed four Core Indicators for PIF-stage (as well as subsequent-stage) submissions to the LDCF and SCCF. These will also contribute to an adaptation section of the GEF Corporate Scorecard.

Reommended action: Due to overwhelming demands on the Portal at the moment which preclude our being able to program them in, we would like you to please include a separate brief document (can be just a page) in your GEF-7 LDCF/SCCF PIF submissions to us, titled “Core Indicators”.

The four Core LDCF/SCCF Indicators are:

- Number of direct beneficiaries  (gender-segregated, M/F)
Please include a breakdown of male/female beneficiaries. Please also note that “direct beneficiaries” in this case are those that directly benefit from adaptation technologies, improved livelihoods, climate-resilient facilities/infrastructure, and those with significantly reduced vulnerability to climatic hazards due to new or enhanced early warning systems. It does not include recipients of trainings or awareness-raising efforts (which is captured by Core Indicator 4, below). It also does not include an entire community far downstream of an area where a riverbank protection measure has been installed/improved, or the entire group of people who have downloaded an early warning app on their phones (many of whom may not necessarily be vulnerable).

- Number of hectares of land under climate-resilient management: Please provide numbers for this indicator in hectares only. This indicator has been selected due to the large volume of LDCF/SCCF projects in the agriculture and food security sectors. If not relevant to the project, please omit.

- Number of policies, plans and development frameworks that mainstream climate resilience: Please include regional, national, sub-national and sectoral plans that the project will mainstream adaptation in.

- Number of people with enhanced capacity to identify climate risk and/or engage in adaptation measures (gender-segregated, M/F): This number may include government staff, communities and households, private sector workers, etc. Please include a breakdown of male/female beneficiaries.

GEFSEC, 6/22/2019 - Not cleared. There does not seem to be any information related to core indicators on the roadmap section of the portal.

Recommended action: Please fill out and upload the Core Indicators and Meta-Data Spreadsheet that was circulated to Agencies following the Adaptation Task Force Meeting on April 1, 2019.

GEFSEC, 7/8/2019 - Cleared. The agency has uploaded the core indicators and meta-data spreadsheet onto the roadmap section of the portal.

Response to Secretariat comments

sans-serif

UNDP, 11 February 2019

This is well noted and action will be taken when the portal is updated

UNDP, 6/5/2019 - The Excel table for core indicators has been uploaded

JP - uploaded as requested.

7. Only for Non-Grant Instrument: Has a reflow calendar been presented?

Secretariat Comment at CEO Endorsement

NA

Response to Secretariat comments

sans-serif

8. Is the project coordinated with other related initiatives and national/regional plans in the country or in the region?

Secretariat Comment at CEO Endorsement

9/11/2018 - More information requested. This project is supporting the implementation of the NAP roadmap defined by the Government of Niger and will directly support the formulation of the NAP framework for the water sector, while also responded to priorities identified in Niger's NAPA and INDC. However, many of the national plans and policies cited in the CEO ER are outdated by 3 year or more.

RECOMMENDED ACTION: Please update the relevant national plans and policies accordingly, if relevant.

GEFSEC, 4/2/2019 - Cleared. The PDES has been updated and the other plans and policies appear to be current and up-to-date.

Response to Secretariat comments

sans-serif

UNDP, 11 February 2019

The 2012-2015 PDES has been continued through the 2017-2021 PDES. This has been corrected in the CEO ER. The text has been updated accordingly in the CEO ER. No other National plan or policy appears outdated, kindly advise otherwise

9. Does the project include a budgeted M&E Plan that monitors and measures results with indicators and targets?

Secretariat Comment at CEO Endorsement

9/12/2018 - Yes. A budgeted M&E project is included in Section C.

Response to Secretariat comments

sans-serif

10. Does the project have descriptions of a knowledge management plan?

Secretariat Comment at CEO Endorsement

9/12/2018 - Yes. This is captured under component 3 -  output 3.3 will directly contribute to the delivery of the KM strategy.  An online community platform will also be set up to foster partnerships between local authorities and beneficiaries, to enable them to assess progress made, and support the scaling up of local experiences, through the availability of options impact assessments and appraisal. Under this project, such partnerships will be extended to research institutions intervening in the water sector, including local and international research centers, in order to support the performance and impact assessments in the intervention sites, using the monitoring and evaluation framework established under the output 3.2. Additionally, using the knowledge and lessons learned collected from the field-tested interventions under outcome 2  will be also strengthened with the information collected in the online platform, which will provide a broad source of data for the water sector.

Response to Secretariat comments

sans-serif

Agency Responses

11. Has the Agency adequately responded to comments at the PIF stage from:

GEFSEC

Secretariat Comment at CEO Endorsement

GEFSEC, 4/2/2019 - Yes.

Response to Secretariat comments

sans-serif

STAP

Secretariat Comment at CEO Endorsement

9/11/2018 - Yes. Responses to STAP comments are provided in Annex B.

Response to Secretariat comments

sans-serif

GEF Council

Secretariat Comment at CEO Endorsement

NA

Edit - Comment was entered under the next item by accident.

9/11/2018 - More information requested. Please indicate if responses to comments sent by Germany on March 3, 2017 have been recorded and where.

GEFSEC, 4/2/2019 - Yes, a response matrix was included in Annex B of the CEO ER, which displays the agency's answers to Germany's comments.

Response to Secretariat comments

sans-serif

Convention Secretariat

Secretariat Comment at CEO Endorsement

Response to Secretariat comments

sans-serif

UNDP, 8 February 2019

The response table to Germany’s comments was added in the Annex B of the CEO Endorsement. It is worth noting that this entailed the inclusion of two additional projects (PISA and PROMAP) in the section “IV.3 Partnerships” of the Prodoc and “Associated baseline” in the CEO endorsement.

Recommendation

12. Is CEO endorsement recommended?

Secretariat Comment at CEO Endorsement

9/18/2018 - Not yet. Please respond to Items 1,3,5, and 8 and resubmit.

4/3/2019 - Not yet, please refer to the flagged items and resubmit.

6/22/2019 - Not yet, please refer to the minor comments relating the missing documents and resubmit.

7/8/2019 - After reviewing this proposal, the majority of the proposal clearly presents what the project is attempting to achieve; however, at this stage of project development, the Secretariat would appreciate slightly more details regarding the specific project activities, particularly under outcomes 1 and 2. At the moment, some of the terms seem a bit too broad for CEO endorsement stage - for example, "Hybrid household water supply solutions"; and "Multi-purpose infrastructures." There also seems to be a discrepancy between output 2.1 in the submission - is output 2.1 delivering water supply solutions, or is it "National, subnational and local stakeholders understand CCA practices related to sustainable water resources management?" There should be further information regarding exactly how many and what these solutions and infrastructures are.

Recommended action: Please provide more detail on the outputs under outcomes 1 and 2.

GEFSEC, 8/29/2019 - Cleared. The agency has provided more detailed information on the alternative scenario, particularly for outcomes 1 and 2, as requested by the Secretariat.

GEFSEC, 9/26/2019 - GEF PPO has brought several issues to our attention. Please rectify and resubmit for clearance.

  - Co-financing letters need to be translated into English – we have reviewed all co-fin docs and found that all the amounts are matching, but could not check whether the type of co-fin (grant, in-kind) are correct. The Agency can translate (no need of official translation).

  - In Section Project Information, Executing Partner Type is incorrect – it cannot be GEF Agency (see screenshot below). Please ask the Agency to amend.

  - The M&E Plan includes some budget lines that either cannot be paid from the M&E (i.e. the Audit as it has to be paid from the PMC, or the translations of the reports into English) or that are not applicable (i.e. tracking tools, as now projects have to report on Core Indicors). Please amend

  - In the ProDoc – section Governance and management arrangements (page 60 onwards), one finds issues that need to be corrected. (i) Para 131 it is indicated that the Implementing Partner is responsible for the “effective use of UNDP resources." It might be a typo, but the resources are mainly from GEF. Please amend. (ii) In Para 136 it is not specified who the Executive is (see screenshot below). In most UNDP projects the Executive (whose role is an executing function) is UNDP,      which is not allowed unless the secretariat approves it. Please ask the Agency to explicitly mention who the Executive is. (iii) In Para 138 it is not specified who the Senior Supplier is (see screenshot below). In most UNDP projects the Senior Supplier (whose role is an executing function) is UNDP, which is not allowed unless the secretariat approves it. Please ask the Agency to explicitly mention who the Senior Supplier is.

  - In the ProDoc – section Total budget and work plan (page 65 onwards), the pro-rata salary of the National Finance and Administrative Specialist + the Communications Specialist (who belong to the Project Management Unit) is charged to the project’s components – these salaries totaling $150,000 have to be charged to the PMC – please  amend.

GEFSEC, 1/2/2019  - Not yet, please see minor requests below.

1)  Not cleared. GEF PPO will request that the type of co-financing is specifically stated in the letters - i.e., wherein co-financing is listed as "grants", this must be explicitly indicated in the letter. Please rectify.

2)  This is cleared.

3) This is cleared.

4) Not cleared  - Minor clarification requested: In the graphic showing the project organization structure under Para 131, UNDP is still listed as the Senior Supplier. Please amend.

5) Not cleared – Minor clarification requested: If this is the case, please provide justification within the portal submission and Prodoc and change the title of the position so as to leave no doubt as to exactly what this person is doing.

GEFSEC, 1/14/2020 -

1) Cleared.

4) Cleared.

5) The justification for this is acceptable, cleared.

GEFSEC, 1/30/2020 -

In consultation with GEF PPO, the following issues remain (below). Please address and resubmit for consideration.

1- Co-financing documents were all translated. However, the document from (i) Ministry of Hydraulics and Sanitation and (ii) Ministry of Planning and Financing do not specify the type of Co-financing as ‘Grant’. In order to accept the type of Co-financing in Table C as ‘Grant’, this should be either explicit in the documents, or supported by somebody (co-financier or the Agency).
Additionally, both sources of co-financing mentioned above are represented in two projects – however, the time life of both projects don’t match the timeline of the LDCF project, reason why the amount proposed cannot be accepted in full as co-finance:
(a) "Rural Hydraulics Support Programme for the Water and Sanitation Sector (PHRASEA)", financed with the support of the Swiss Cooperation 2017-2021
(b) “Community Action for Climate Resilience (CAP/RC)”, approved in 2012, with an additional financing approved in 2019 and expected closing May 2021.
A third source of co-financing is represented by a Green Climate Fund financed project (“National Adaptation Plan-Advancing, medium and long term adaptation planning and budgeting in Niger (NAP)”) whose timeline is from 2018 to 2022 – as the projects above, time life of this project doesn’t match the timeline of the LDCF project, reason why the amount proposed cannot be accepted in full as co-finance.

Please consult the co-financiers and reasonably propose co-financing amounts that accurately match the LDCF’s project timeline.

2- M&E Plan still has ineligible expenses (Audit and Translation) - Please amend.

3- Still in the ProDoc – section Total budget and work plan (page 69 onwards), the pro-rata salary of the National Finance and Administrative Specialist + the Communications Specialist (who belong to the Project Management Unit) is charged to the project’s components (see screenshot below). While you the explanation is clear, the TORs that show the activities and the deliverables that will be expected from paying the costs of these professionals out of the Components are not available. Please provide these TORs in order to understand what the GEF portion is paying for. In the same section, there are two budget lines that we overlooked in our previous review: Direct Project Costs and Rental & Maintenance-Premises (see screenshot below). Please request the Agency to assure that the charge of these two items will be covered by the co-financing portion of the PMC, not by the GEF portion.

Response to Secretariat comments

UNDP Response, 24 April 2020

- The type of co-financing was mistakenly attributed to grant, and, besides UNDP TRAC resources and the GCF NAP project (for a revised total of US$ 3,167,282), the other co-financings are in-kind. Regarding the duration of the projects in co-financing, it should be noted that these letters date back from July 2018, when the projects still had most of their implementation period to go. New co-financings were however identified, and new letters were issued by the Ministry of Hydraulics and Sanitation and the CNEDD for a total of in-kind co-financing of US$ 28,700,000. Letters are available in annex and the new amounts were revised in the Project Document and CEO ER.

- Audit and translation were withdrawn from the M&E table. In addition, following new guidance from UNDP, an M&E component was added into the budget, reflecting the costs identified in table 5, provided in section VII.

- The TORs, that were provided in Annex C, detail the activities to be conducted by the Communication Specialist and the Project Coordinator – who are both budgeted under the different components considering their technical support to the project. The ToRs now provide additional details as per the explanation provided in the previous resubmission – see annex C. The ToRs for the Finance and Administrative specialist are also available in Annex C, but this staff is budgeted under the PMC and focuses mainly on project management functions, providing only limited technical inputs. Finally, the Direct Project Costs and Rental & Maintenance-Premises are already budgeted under UNDP TRAC co-financing and not charged to the LDCF budget.

3Dec2019 CG

1. The co-financing letters have been translated (the French version remains the official and signed document, however the English version is available in a document provided in a separate document).

2. In the GEF Portal, the Executing partner Type was wrongly indicated.  It should read “Government”.  The required change has been communicated to the GEF Sec IT department as the Portal does not allow us to make the changes.

3. The M&E budget is an indicator of all the costs related to M&E, which are later spread into the project budget. M&E costs include audit which is budgeted under project management costs in the total budget (see section X. Total budget and workplan, budget line 25, p72).  The costs for the update of the tracking tools, this was deleted from the M&E budget and replaced by the costs for the monitoring of core indicators. The change was made both in the project document and the CEO Endorsement. Please note the document was first submitted in September 2018, when tracking tools were still requested.

4.  In the section on Governance and Management arrangements, (i) the paragraph 131 was corrected to mention LDCF resources “the effective use of LDCF and UNDP resources”, (ii) under paragraph 135, it is specified that the SE/CNEDD will be the executive, (iii) the senior supplier has been specified and is the National Project Director, at the SE/CNEDD.

5.  The communication specialist does not only perform project management function and should therefore be also included in the project component costs instead of only PMC. Part of his costs have been included under PMC and the rest remains under the different components. His role will be to improve the KM on the results of the project in order to (i) strengthen the ownership, (ii) increase the understanding of climate change and the project for project beneficiaries and other stakeholders and (iii) enable the up scaling. Another option would have been to recruit a national consultant to intervene punctually, but it is considered less efficient in the case of this project. More specifically, he will play an important role for the implementation of the activities 1.2.3, 1.3.5, 2.2.3, 3.1.2 and the output 3.3.  The costs of the Finance and Administration specialist were imputed to the PMC.  The costs of the project manager were partly re-allocated into the outcomes as the project manager technically supports the achievements of the outcomes and is not solely responsible for the management of the daily activities. The project manager will have a strong background on adaptation, with a focus on water resources, and will be qualified to technically support the three project components. The project manager will be working with the different experts for the design and the implementation of the activities, in particular he will guide the identification of the sites and best options for the activities under outcome 2, on water resources. He will also support the coordination of planning activities under outcome 1 and avoid inconsistency between the different mechanisms, planning revisions or training. Finally, he will also participate and facilitate dialogues to be organized as part of the outcome 3.