United Nations Development Programme

Country: Argentina

PROJECT DOCUMENT

| Project title: Mainstreaming biodiversity conservation and sustainable land management (SLM) into development planning: Making Environmental Land Use Planning (ELUP) Operational in Argentina |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Country: Argentina | Implementing Partner: Secretariat of the Environment and Sustainable Development (SGAyDS) |  |  |  | Management Arrangements: National Implementation Modality (NIM) |
| UNDAF/Country Programme Outcome: UNDAF Outcome 4: By 2020, the country will have reinforced the sustainable management of natural resources and implemented adaptation and mitigation policies with respect to climate change and man-made damage, using a gender and intercultural approach CPD Output 4.1: Land use strategies promoted for the sustainable management of natural resources and ecosystems |  |  |  |  |  |
| UNDP Strategic Plan Output: Output 1.4.1: Solutions scaled up for sustainable management of natural resources, including sustainable commodities and green and inclusive value chains |  |  |  |  |  |
| UNDP Social and Environmental Screening Category: Moderate |  |  |  | UNDP Gender Marker: 2 |  |
| Atlas Project ID (formerly Award ID): 114826 |  |  |  | Atlas Output ID (formerly Project ID): 112703 |  |
| UNDP-GEF PIMS ID number: 5791 |  |  |  | GEF ID number: 9583 |  |
| Planned start date: March 2019 |  |  |  | Planned end date: March 2025 |  |
| PAC meeting date TBD |  |  |  |  |  |
| Brief project description: The objective of the proposed project is to generate multiple biodiversity and land degradation benefits by developing a system of policy, economic, financial and technical instruments and governance mechanisms for Environmental Land Use Planning to mainstream socioeconomic and environmental evaluation of ecosystem goods and services in decision-making in different government levels and sectors. The project will reduce biodiversity loss and land degradation by integrating biodiversity conservation and sustainable land management approaches into the production practices of the main sectors driving these processes, namely the agriculture and livestock sector and the emerging threats from mining, infrastructure expansion in peri-urban areas and tourism in decision-making, planning and sectoral finance allocations at different government levels. To undertake this approach and achieve the stated objective the project has been organized into four outcomes: a) Federal enabling framework and strategies to reinforce ELUP, and underpin implementation in priority ecosystems and habitats to reduce pressure from key production sectors (target sectors: agriculture & livestock; mining and peri-urban infrastructure; b) Application of ELUP procedures and instruments in pilot provinces with targeted ecoregions and production sector land uses; c) Replicability framework for ELUP uptake in all Argentine provinces; and d) Dissemination of lessons learned, monitoring & evaluation. Expected global and local benefits include: a) 5,079,260 hectares (ha) where ELUP has been agreed upon and implemented in priority landscapes of the three pilot provinces through the application of regulations, instruments and approaches to enforce modified production; b) an additional 507,926 has in the three pilot provinces in which upscaling is expected due to project dissemination activities and co-financed interventions; c) 613,128 has in the target landscapes of the pilot provinces under improved practices to benefit BD and sustainable land management in production systems and where BD conservation and LD reduction benefits have been accrued, measured through the level of improvement in Net Primary Productivity (NPP), percentage of land cover and soil organic carbon content (GEF Core Indicator 4); d) 128,370 has of land (agricultural, forest and forest lands and natural grass and shrubland) restored in the target landscapes of the pilot provinces (GEF Core Indicator 3); e) 11,665 direct project beneficiaries that improve their livelihoods through environmentally friendly natural resource management and sustainable production (at least 40% are women; 10% of total number belong to indigenous groups) (GEF Core Indicator 11); f) 20% increase in the Sustainable Livelihoods Framework Index of beneficiaries in the target landscapes. |  |  |  |  |  |
| Financing Plan |  |  |  |  |  |
| GEF Trust Fund |  |  |  | USD 8,995,434 |  |
| UNDP TRAC resources |  |  |  | USD 0 |  |
| Cash co-financing to be administered by UNDP |  |  |  | USD 0 |  |
| - Total Budget administered by UNDP |  |  |  | USD 8,995,434 |  |
| Parallel co-financing |  |  |  |  |  |
| UNDP |  |  |  | USD 200,000 |  |
| Secretariat for Environment and Sustainable Development |  |  |  | USD 15,521,232 |  |
| National Agricultural Technology Institute |  |  |  | USD 6,140,000 |  |
| Provincial Agency for Sustainable Development of Buenos Aires |  |  |  | USD 6,833,332 |  |
| Ministry of Environment of Jujuy |  |  |  | USD 1,512,104 |  |
| Secretariat of Environment and Land Use Planning of Mendoza |  |  |  | USD 6,833,332 |  |
| National Council for Technical and Scientific Research |  |  |  | USD 5,000,000 |  |
| National Indigenous Peoples Institute |  |  |  | USD 350,000 |  |
| - Total co-financing |  |  |  | USD 42,390,000 |  |
| - Grand-Total Project Financing (1)+(2) |  |  |  | USD 51,385,434 |  |
| Signatures |  |  |  |  |  |
| Signature: print name below |  | Agreed by Government | Date/Month/Year: |  |  |
| Signature: print name below |  | Agreed by Implementing Partner | Date/Month/Year: |  |  |
| Signature: print name below |  | Agreed by UNDP | Date/Month/Year: |  |  |

# Table of Contents

I.	Table of Contents	3

II.	Development Challenge	6

III.	Strategy	14

IV.	Results and Partnerships	26

V.	Project Management	57

VI.	Project Results Framework	59

VII.	Monitoring and Evaluation (M&E) Plan	67

VIII.	Governance and Management Arrangements	73

IX.	Financial Planning and Management	78

X.	Total Budget and Work Plan	83

XI.	Legal Context	91

XII.	Risk Management	91

XIII.	Mandatory Annexes	94

Annex A:  Multi Year Work Plan	95

Annex B:  Core Indicators  at baseline	110

Annex C:  Overview of Technical Consultancies	116

Annex D: Terms of Reference	120

Annex E:  UNDP Social and Environmental Screening Procedure and plans as needed	132

Annex F:  Stakeholder Engagement Plan	154

Annex G: Gender and Ethnic Analysis and Action Plan	176

Annex H:  UNDP Risk Log	187

Annex I:  Results of the capacity assessment of the project implementing partner	194

Annex J:  Letter of Agreement with the Government of Argentina and Description of UNDP Country Office Support Services (Signed version will be included by ProDoc Signature)	219

Annex K :  UNDP Project Quality Assurance Report	223

Annex L :  Target Landscapes Profiles and Maps	224

ACRONYMS

| APN | National Parks Administration |
| --- | --- |
| BAPRO | Bank of the Province of Buenos Aires |
| BD | Biodiversity |
| BNA | Argentine National Bank |
| CABA | Autonomous City of Buenos Aires |
| CIOUT | Commission for Urban and Territorial Land Use Planning of Buenos Aires |
| COFELMA | Federal Legislative Council for Environment |
| COFEMA | Federal Council of Environment Ministers |
| COFEPLAN | Federal Council for Planning and Land use Planning |
| CONADIBIO | National Advisory Committee for Conservation and Sustainable Use of Biodiversity |
| CONICET | National Council for Technical and Scientific Research |
| CPD | Country Programme and Action Plan Document |
| CPOT | Provincial Council for Land Use Planning of Mendoza |
| CSO | Civil Society Organization |
| EAE | Strategic Environmental Assessment |
| ELUP | Environmental Land Use Planning |
| EBA | Endemic Bird Area |
| EG&S | Ecosystem goods and services |
| EIA | Environmental Impact Assessments |
| ES | Ecosystem services |
| FAO | Food and Agriculture Organization |
| FONTAR | Argentine Technology Fund |
| FPIC | Free, Prior and Informed Consent |
| FSP | Full Sized Project |
| GDP | Gross Domestic Product |
| GEF | Global Environment Facility |
| GEFSEC | Global Environment Facility Secretariat |
| GIS | Geographical Information Systems |
| GoA | Government of Argentina |
| IAS | invasive alien species |
| IBA | Important Bird Areas |
| IDE Ambiente | Environmental Spatial Infrastructure Data |
| IDERA | Spatial Data Infrastructure of the Republic of Argentina |
| INAI | National Indigenous Peoples Institute |
| INTA | National Agricultural Technology Institute |
| IPP | Indigenous Peoples Plan |
| LADA | Land Degradation Assessment in Drylands |
| LD | Land Degradation |
| M&E | Monitoring and Evaluation |
| MAB | Man and Biosphere |
| MINAI | Ministry of Agro-Industry |
| MTR | Mid-Term Review |
| NAP | National Plan of Action to Combat Desertification |
| NBSAP | National Biodiversity Strategy and Plan of Action |
| NIM | National Implementation Modality |
| NGO | Non-Governmental Organization |
| OBIO | National Biodiversity Observatory |
| ONDTyD | National Observatory on Land Degradation and Desertification |
| OPDS | Provincial Agency for Sustainable Development |
| PA | Protected Areas |
| PB | Project Board |
| PES | Payment for Ecosystem Services |
| PIECAS | Strategic Plan for Conservation and Sustainable Use of the Parana River Delta |
| PIF | Project Identification Form |
| PIR | GEF Project Implementation Report |
| PMU | Project Management Unit |
| POPP | Programme and Operations Policies and Procedures |
| PPG | Project Preparation Grant |
| PROCODAS | Social Actors Demand Council Program |
| PRODEAR | Rural Area Development Program |
| PRODECCA | Goat Value Chain Development Program |
| PRODERI | Inclusive Rural Development Program |
| PROSAP | Provincial Agricultural Services Program |
| PT | Project Technical Team |
| PY | Project Year |
| SAOT | Secretariat for Environment and Land Use Planning |
| SBAA | Standard Basic Assistance Agreement |
| SDG | Sustainable Development Goals |
| SEM-OAT | System to Evaluate and Monitor ELUP Implementation in Argentina |
| SESP | Social and Environmental Screening Procedure |
| SGAyDS | Secretariat for Environment and Sustainable Development |
| SLM | Sustainable Land Management |
| STAP | GEF Scientific Technical Advisory Panel |
| TE | Terminal Evaluation |
| TSA | Targeted Scenario Analysis |
| UNDAF | United Nations Development Assistance Framework |
| UNESCO | United Nations Educational Scientific and Cultural Organization |
| UNDP | United Nations Development Programme |
| UNDP-GEF | UNDP Global Environmental Finance Unit |
| USD | United States Dollars |
| VGA | Valuable Grassland Areas |
| WHSRN | Western Hemisphere Shorebird Reserve Network |
| WWF | World Wide Fund |

# Development Challenge

- Global significance. The Republic of Argentina is a federal country made up of 23 provinces and the Autonomous City of Buenos Aires (CABA). With an expansive continental and marine territory, Argentina has vast natural, cultural and economic complexity and diversity. Indeed, it is one of the countries with the highest number of ecoregions worldwide with 15 terrestrial ecoregions and 3 marine/freshwater ecoregions as per the national classification system. These are the High Andes; Puna; High Monte, Yungas Forest; Dry Chaco; Humid Chaco; Parana Forest; Ibera Wetlands; Plains and Shrubs; Parana Delta and Flooded Savanna; Espinal; Pampas; Low Monte; Patagonian Steppe; Patagonian Forests; South Atlantic Islands, Argentine Sea and Antarctica. Of these, 8 have been classified amongst the highest priorities for conservation both nationally (National Biodiversity Strategy and Plan of Action- NBSAP) and regionally. Five are exclusive or semi-exclusive to Argentina and house a significant number of endemic species. The Argentine Sea Ecoregion includes coastal environments considered unique due to the influence of the cold Malvinas currents along the south coast of Buenos Aires province. Arid, semi-arid, sub-humid and dry ecosystems cover 75% of the national territory. Collectively referred to as drylands, these ecosystems include dry forest, scrub, grasslands, high altitude deserts and Andean wetlands.

- Global ecoregion classifications recognize this extraordinary diversity; 16 ecoregions are recognized under the World Wide Fund (WWF) classification of which 6 are included in the Global 200 List: Patagonian Steppe, Valdivian Forest, Dry Puna; Dry Central Puna; Yungas Forest; Atlantic Forest; and High Andean Lakes. The Parana Delta and Flooded Savanna forms part of the large river Parana ecoregion also known for its significant biodiversity. The Pampas grasslands have several Valuable Grassland Areas (VGA). Collectively these ecoregions house 10,006 species of vascular plants out of which 1,749 are country endemic species. There are 385 mammal species; 1,002 bird species; 175 amphibian species; 256 lizard and amphisbaena species; 136 snake species and 14 turtle species. Within invertebrates, around 110,000 arthropods are believed to live in the country, and also 550 mollusk species, and 550 annelid species.

- With a population of 40,117,096 inhabitants in 2010, and an economy based on its natural resources, these ecoregions also provide key ecosystem services for society at large and a broad range of production sectors, particularly conservation of land and soil for agriculture and livestock breeding in the Pampas, Wet Chaco and Dry Chaco ecoregions which are the main producers and exporters of farm products. Other ecoregions such as the Parana Delta and Flooded Savanna render services to sustain wetlands and related fisheries in the River Plate basin. Ecoregions such as the High Andes, Parana Forest, Yungas Forest and Patagonian Forest are water producers, and, overall, they provide key services not only at the global level but also for the national economy and the population’s well-being.

- Problem to be addressed. The country has taken measures to protect the core areas important for biodiversity conservation. Currently the country has 440 public and private protected areas (PA) covering 12% of the country. A total of 13% are coastal-marine; 53 are under the national jurisdiction of the National Parks Administration (APN) and 386 are under the 23 Provinces and CABA jurisdiction. They include 21 Ramsar sites and 15 Biosphere Reserves in the MAB-UNESCO Programme and four World Heritage Sites. In addition, the country has eight sites in the Western Hemisphere Shorebird Reserve Network (WHSRN), four of global importance, two hemispheric and two of regional importance. It has 47 Valuable Grassland Areas (VGAs); 273 Important Bird and Biodiversity Areas, and 192 private natural reserves covering 726,000 ha.

- Despite these significant steps in establishing protected areas, large expanses of key ecosystems remain throughout the production lands and are increasingly threatened by: 1) Habitat loss and ecosystem fragmentation: land-use changes are the main cause leading to biodiversity (BD) loss. They also lead to the emission of carbon from the reduction of forest and scrub stocks and to land degradation processes and water and soil pollution; 2) Climate change and invasive alien species (IAS) are secondary causes of biodiversity loss. One of the main pathways of introduction of IAS is the expansion of the agricultural frontier. The spread of IAS in different ecoregions has caused biodiversity losses through inter-specific competition and changes as well as socioeconomic impacts (654 invasive plant, vertebrate, invertebrate, algae and alien fungi species have been recorded). Climate scenarios described in Argentina´s Third National Communication indicate in general increases in the high temperature and rainfall extremes in most of the country. Given the extension and climatic diversity of Argentina, climate change will affect different regions differently. The subtropical Andean region will experience the highest temperature increase with an increasing water stress scenario, decrease in efficiency of water use and productivity of ecological systems, accelerated desertification processes, displacement or reduction in the geographic range of certain species and probable local extinction of species with less tolerance to the new conditions.  Wetlands of the High Andes and Puna will suffer reduction in their surface areas and fragmentation, affecting animal populations that depend on such habitats.  Overgrazing will have synergistic effects with the climate trends. Temperature increases in Jujuy, Catamarca and Salta could affect the life cycle of queñoas (Polylepis spp) which are an important source of fuelwood.  The agriculturally important provinces of Mendoza and San Juan, which are highly dependent on irrigation, will experience a decrease in surface water availability with increases in costs to extract underground water risking the viability of irrigated agriculture. Patagonia will experience higher temperatures and less rainfall with a tendency to increased aridity. Current species of the Patagonian Steppe will be replaced by more xerophytic grasses or shrubs, affecting distribution of many bird species and increasing vulnerability of threatened ones.  The Pampas Region is the main agricultural and livestock production area. Although no great changes in temperature and rainfall are expected the greater risk in the Northern portion will come from the interdecadal variation in rainfall magnified by land use change.  In the Center increases in rainfall in summer will increase soy and maize yields while rainfall decreases in winter will reduce wheat yields.  Due to changes in forage production, livestock production will be reduced in the Northern portion, will be stable in the Center and will increase in the Western portion of the Pampas.  No important changes in rainfall are expected for the Semi-arid Region but the dry winter period would be longer. The greater climate risk in this area would come from land use change for agriculture. 3) Pollution, particularly of soil and water is also causing BD losses and degradation of land and water ecosystems. It is driven by high agrochemical use in agro-businesses; insufficient waste treatment in urban expansion areas such as in the Matanza-Riachuelo and Reconquista River water basins; and  inappropriate management of mine waste.

- These same drivers are causing increasing land degradation particularly in the large expanses of Argentina drylands where 30% of the population reside and generate some 30% of Argentina’s agriculture and livestock GDP. Based on LADA/WOCAT data, 45% of the national territory has some level of degradation and deterioration of biological, physical and chemical soil properties generating important negative environmental impacts that go beyond production. Furthermore, land degradation processes are increasing at an estimated 650,000 hectares/year. Some of the ecoregions targeted by this project suffer particularly high levels of land degradation: 48% of the plains scrubland; 62% of the dry valley scrubland and 75% of the Puna suffer moderate to strong degradation.

- Agriculture and livestock: Argentina is the world’s 3rd soybean and 11th beef producer. Exports of grain, oil and by- products increased by 205.72% in the last 22 years alone. Originally centered in the Pampas region the agricultural frontier expanded from the 1990s onwards into areas where conditions had previously been inappropriate for production. This expansion was driven by adaptation and resistance of crops, by new technological progress and new generation agrochemicals, by new management practices; and also due to the increase in the price of commodities, particularly soy. Expansion in soy production led to displacement and intensification of livestock breeding mainly in ecoregions where ecosystems are vulnerable. Today agricultural production and livestock rearing is spread across large areas of Pampas, Espinal, Humid and Dry, Wet Chaco, Yungas Forest, Plains and Shrub.

- Expanding agricultural frontiers have led to fragmentation and loss of native forest habitat and forest degradation especially in the Chaco, Atlantic Forest and Yungas Forests that have suffered deforestation over 1.145 million ha in the last five years. Between 2006–2014, 2.827 million ha of forests were lost, largely due to conversion of forests and grasslands to agricultural systems in the Humid and Dry Chaco ecoregions. The long-term conservation of animal and plant species in these environments is severely threatened. The National Native Forest Law (Law Nº 26331), calls for categorizing forest ecosystems into different land uses. Category I forests cover 10,061,753 ha in 21 provinces and as forest transformation is prohibited in this zone, it provides a significant framework for protection. There is more uncertainty on the effective management of the non-forest ecosystems. The most critical are mountain grasslands and shrubs, arid and semi-arid ecosystems in almost all of Patagonia and the Pampa ecoregion to the High Andes where many hotspots are found such as VGAs, IBAs, Western Hemisphere Shorebird Reserve Network, and Biosphere Reserve transition or buffer areas, which are under no formal legal frameworks and are exposed to encroachment.

- In addition to biodiversity loss, the removal of natural vegetation due to expanding agriculture and livestock frontier in these drylands exacerbates land degradation exposing the fragile soils to wind and water erosion. Fires used to clear land for agriculture often get out of control in these dry and windy areas. In the more fertile valleys, irrigation-based agriculture is causing water deficiencies in regions where water deficits are already high (~-1000-1500mm). In many cases this is also increasing soil salinization and alkalinization. Livestock rearing also ranks high amongst the direct causes of land degradation in the drylands. Originally mainly sheep, this is now combined with goats and to a lesser extent, cattle. The increasing animal loads combined with the limited pasture have generated overgrazing, causing loss of native species, soil compaction as well as increased soil erosion with high rates of material (e.g., in excess of 150 tons/ha/year in the Puna), and reductions in wetlands and associated ecosystems. In turn this affects the ecosystems´ production and regulation functions.

- Mining: Argentina is an important regional producer of minerals, including primary aluminum, lead, copper, zinc, silver and gold. It also has the world's third largest reserve of lithium which is now being more actively mined. The national government has already granted mining rights over an area of 183,000 km2 and has identified another 750,000 km2 with a high mining potential mainly in the ecoregions of the High Monte, Puna, High Andes and Patagonian Steppe. In 2016, the Mining Secretariat identified 435 mine prospects including for lithium, silver, gold, copper, lead, boron and zinc. Of these only 16 are in the production stage, however, given increases in the price of mineral commodities, expansion is expected and production will most likely take place using extraction technologies that generate waste on a large scale.

- Peri-Urban infrastructure expansion: Ninety-one percent of the country’s population lives in urban settlements of over 2,000 inhabitants. Expanding infrastructure for urban uses and tourism in the peri-urban areas is another driver of habitat loss and fragmentation and land degradation affecting ecosystems of high ecological and production value. This is particularly prevalent in the Pampas and Parana Delta ecoregions. The Buenos Aires Metropolitan Area, for example, has a projected increase of almost two million inhabitants in the next 10 years; and tourist areas are expanding along the Atlantic Coast in Buenos Aires province. The number of permanent residents in coastal tourist cities has increased rapidly (100% in Pinamar District for 1991-2001 and 24% for the period 2001-2010; in Partido de la Costa district, 57% for 1991-2001 and 15% for 2001- 2010). Deficient planning and land occupation has led to encroachment in vulnerable and prohibited areas causing erosion in coastal ecosystems, with extreme cases of marine intrusions of 5-6m/year.

- Thus, although there are important areas under conservation through protected areas, almost 83% of the country (2,348,148 km2) that includes key ecosystems are currently or will be used for production and would be exposed to the above-mentioned threats if other land use frameworks are not in place. In recognition of this the General Law of the Environment Nº 25675, through Article 10, sets up environmental land use planning (ELUP) as an environmental management policy and instrument to guide the use of natural resources. One that allows a maximum production in each ecosystem while guaranteeing the minimum level of degradation and promoting social participation in decisions that are necessary for sustainable development. ELUP is a strategic tool to organize land use and occupation and reflects priorities and the value society has assigned to different environments and to production, ecosystems and communities´ needs as a whole. As an environmental policy tool, ELUP includes command and control mechanisms as well as incentives and disincentives to organize activities spatially in a given territory and is implemented in part through state regulations to align different sectoral interests and oversee the actual and potential conflicts between these to protect the common good.

- Significant advances have been made within some specific sectors to define norms and policies that promote land use zoning and reduce environmentally “aggressive” practices. Amongst these the Federal level minimal standards, which establish the framework for undertaking environmental management in provinces. This is a regulatory instrument that sets the basic standards and procedures for a specific environmental mechanism or instrument and defines among others the process and characteristics that should be applied as a minimum in each Province. Of note are the: a) National Law Nº 26331 on Minimum Standards for the Environmental Protection of Native Forests (Native Forests Law), which recognizes the services this ecosystem provides to society and creates a National Fund for the Enrichment and Conservation of Native Forests for those provinces that have forest zoning in place; b) National Law Nº 26639 on Minimum Standards for Glacier and Peri-glacial Environment Preservation, including strategic water resource reserves and water supplies for biodiversity protection; and c) the Bill on Wetlands, which sets minimum standards for the conservation, restoration and sustainable development of wetlands in Argentina, so production activities are compatible with the conservation of environmental services. These all focus on specific ecosystems and do not address the mosaic of ecosystems in a landscape.

- The Government of Argentina (GoA) has outlined a number of large-scale initiatives to reactivate the economy in areas of extreme poverty and provide basic necessities to the rural population while stimulating production in sectors such as agriculture and mining through the building of infrastructure and improvement of ports to facilitate exportation. In this context, dialogues between the Secretariat for the Environment and Sustainable Development (SGAyDS) and production sectors are underway to identify common areas and agreements on best practices and ways to ensure the above said development plans progress in an environmentally adequate manner. This is an opportunity to further advance the General Law of the Environment through the implementation of Article 10 on ELUP and the instruments for its effective implementation listed in Article 8 of the same Law. These instruments include, among others, environmental impact assessments; environmental information systems and an economic regime (tools and instruments) for promoting sustainable development.

- However, under the business-as-usual scenario, these policies and initiatives will continue to be implemented largely through a sector-based approach and with weak inter-institutional and inter-sectoral coordination and will not be sufficient to enable a shift towards an ELUP that is effective across such vast territories and to address the complex threats and sectors that are driven by strong prices in global economies. More is needed to ensure ELUP and it is essential to adopt an integrated approach to ecosystem management at scales that recognize the complex spatial dimensions of the processes that drive the threats, while also mainstreaming environmental considerations into the management practices of production sectors with particular potential to generate threats to global environmental values. It also requires decision-making and planning to be based on sound information regarding the status and functioning of the ecosystems in question and the threats that affect them, as well as the nature and magnitude of the goods and services that these ecosystems generate, and the significance and value of these goods and services for the diverse stakeholder groups and the sustainable development of production sectors.

- The proposed long-term solution is to advance ELUP and build the instruments needed to support its implementation with the vision of establishing an operational framework through which areas in the production landscape that are priorities for conservation or combatting land degradation can be protected from sector driven pressures.   Although ELUP is recognized as a valuable means to achieve this integrated management and agree on land use to sustain ecosystem for development management there are several constraints that hamper its effective operationalization, namely:

- Insufficient policy and regulatory framework and reliable information to effectively develop ELUP at national and provincial levels;

- Weaknesses in provincial tools and instruments to approve, implement and oversee ELUP; and

- Dispersed knowledge and insufficient sharing of environmental management practices at provincial and inter-provincial levels.

- Insufficient policy and regulatory framework and reliable information to effectively develop ELUP at national and provincial levels: Provinces have the mandate over natural resources within their territory and are responsible for overseeing land use. Although some, such as Mendoza, have already made progress in establishing a legal framework for ELUP, this is missing in most provinces and existing land use planning focuses mainly on economic development, transportation, and population criteria. At the federal level standards can be defined to ensure Provinces comply with a minimum set of criteria and elements in provincial regulations (e.g., the Native Forest Law), however these have not been set for ELUP nor for the tools to support its implementation. The result is that even if provinces advance ELUP legislation this is being done in an ad hoc manner and can lead to unequal standards which put at risk ecosystems shared between provinces and hamper the achievement of national level conservation targets for different ecoregions.

- Instruments such as Environmental Impact Assessments (EIA) do limit or reduce the impact of production sectors on the environment but these are incomplete and are sectoral or limited by the specificities of each province that can list those activities required to undertake EIAs. As EIAs are site-based, and thus limited to the “development project” and related sector in a specific site, they rarely assess the effect of ecosystem service loss of other sectors nor considers the effects on the provision of ecosystem services at landscape scale. This scale level analysis is needed to appropriately consider the ecological processes on which the very sector relies. There is a more serious aggravating factor for the agricultural sector; in most cases these activities are not governed by EIAs and do not need an environmental permit. There is interest in some sectors in analyzing the territory at a larger scale and seeking inter-sectoral synergies but this is hampered by poor integration of public policies and government plans between and within the various government levels (national, provincial and municipal). This integrated analysis at scale also faces constraints due to the low levels of awareness of the relationship between impact and loss of ecosystem services that are important for sectoral production and/or human health and wellbeing.

- Underpinning these constraints is the scarce and fragmented information on ecosystems and the goods and services they provide and their vulnerability to the impact of the different sectors. There are a number of  initiatives dealing with information systems and data banks, but in most cases, the information is fragmented, outdated and does not include data on ecosystem status, vulnerability and resilience nor the values of ecosystem services to different sector production and hence the impact of their loss.

- Weakness in provincial tools and instruments to approve, implement and oversee ELUP: Institutions responsible for ELUP generally operate under provincial public planning agencies. The information gaps and regulatory constraints for developing ELUP indicated in the federal level also apply to the provinces but there are additional barriers for effective implementation and oversight. Although provincial authorities seek to comply with responsibilities they are hampered by: a) Few staff members and scarce resources to oversee implementation particularly over remote rural areas and large territories; b) Insufficiently clear procedures on how to conduct environmental planning; d) Insufficient mechanisms and spaces for participation, negotiation and interdisciplinary and inter-sectoral dialogue among private and public actors to reach agreements on objectives and goals, technologies and production restrictions in priority areas; e) Insufficient awareness of the negative impacts of production on ecosystems and the services they provide to society; f) Inadequate experience at the local or provincial level on tools to facilitate ELUP implementation both through command and control approaches or through incentives that recognize losses are incurred where land uses are restricted on private land for the common good. Although there are data on various technical, economic or financial instruments, most are based on sectors or specific ecosystems and do not reflect the economic value of the ecosystem goods and services of the different ecoregions. There is increasingly broad agreement that the benefits of ecosystem services ought to be considered in decision-making and in the design of compensation mechanisms, but development of protocols or clear methodologies is still fledgling and precise tools are needed for decision-making and for example, on compensation systems for different land uses.

- Dispersed knowledge and insufficient sharing of environmental management practices for ELUP at provincial and inter-provincial levels: The diversity of scenarios across Argentina’s 23 provinces with different legal and institutional frameworks, tools and instruments, ecoregions, ecosystems, land use patterns and production sectors, provides a plethora of experiences that could provide a strong input on which to build effective and more standardized approaches to environmental management including ELUP across the country. However, this knowledge is dispersed within and across provinces. It is rarely codified to identify lessons learned or assessed ex-post using stringent metrological approaches to evaluate cost effectiveness and efficiencies. On the one hand, this leads to repetition of ineffective sub-optimal approaches, and, on the other, it reduces the uptake of positive experiences across larger areas and at scale. The result is that an opportunity is missed to better understand, disseminate and apply ELUP instruments in other provinces, and even across larger areas of each ecoregion and land use pattern. It also further constrains the application of ELUP in ecosystems shared by provinces that have different management models. Joint management of land use between provinces is also made more complex by the limited experience of decision-makers and technical planning agencies in inter-jurisdictional environmental management of any sort. There are some experiences with ELUP with varying degrees of progress in different provinces, but few have moved forward with thorough planning or have attempted to transfer these experiences. The lost opportunity to gain from the wealth of experiences nationwide in a systematic way compounds the previously described barriers above, further impeding advances towards the long term solution.

- The GoA is requesting GEF assistance through UNDP to provide incremental financing to overcome these barriers and pursue a path to the proposed long-term solution. This will build on the robust baseline identified during the PPG that will provide a foundation on which to build this ELUP framework consisting of land use planning and zoning instruments, environmental information systems for decision making, and economic and financial instruments (these are described in the project´s intervention strategy and expected results in Section IV Results and Partnerships below).

- By removing the identified barriers the project will create an enabling framework for integrated environmental land use planning and the full development of the tools needed for its implementation. In doing so it will consolidate the past single ecosystem and sector approaches and ensure that new development plans take into account the different ecosystems across the entire country and comply with land use guidance that confers conservation and sustainable use of critical habitats and the ecosystem goods and services they provide to society. This will ensure the continued provision of these services to production, avoid foreclosure of future development options and also provide global environmental benefits at scale.

- As such, the project is in line with national and provincial priorities and objectives. ELUP is a cross-cutting topic in almost all of the National Biodiversity Strategy and Action Plan (NBSAP) pillars and is aligned with the National Plan of Action to Combat Desertification (NAP). The project objectives are a priority for the national and provincial governments and will support ELUP in Argentina pursuant to the provisions of the General Environment Law Nº 25 675. The project is consistent with the enforcement of the Native Forest Law Nº 26 331, Fauna Conservation Law Nº 22421; Glacier and Peri-glacial Environment Law Nº 26639 and the current Bill on Wetlands. The coordination of policies, regulatory frameworks and national plans on ELUP, biodiversity conservation and the fight against desertification, with provincial policies and plans on the same topics, are consistent with the objectives and coordination of these environmental topics at federal agencies such as Federal Council of Environment Ministers (COFEMA), National Advisory Committee for Conservation and Sustainable Use of Biodiversity (CONADIBIO), Federal Council for Planning and Land use Planning (COFEPLAN) and the Federal Legislative Council for the Environment (COFELMA). The project will also be aligned with several of the national priority programs of SGAyDS (e.g., Management and Sustainable Use of Wild Species, Conservation of Endangered Species, Protection of Fauna Habitats and Flora Management). At the regional level, the project is aligned with the MERCOSUR Regional Strategy on Biodiversity, which promotes and supports a set of joint instruments and measures for ecosystem and BD conservation. The project is also aligned with the Argentina´s ongoing process to define national targets for its Land Degradation Neutrality Framework.

- At provincial level the project is aligned with land use planning instruments: in Buenos Aires, with the Environment and Natural Resources Law Nº 11723 Native Forest Law Nº 14888 and the Strategic Plan for Conservation and Sustainable Use of the Parana River Delta (PIECAS); in Jujuy with Law Nº5676 Adaptive Land Use Plan for Forest Areas of Jujuy, Urban Solid Waste Management Law Nº 5954, Law Nº6080 Provincial System of Natural Protected Areas and the Green Jujuy: Carbon Neutral 2030 Plan; and in Mendoza with the 2030 Development Strategic Plan of Mendoza and its land use planning regulatory framework (e.g., Law Nº 8051 Land Use Planning of Mendoza; Law Nº 8999 approving the Provincial Land Use Plan, Law Nº 5804 declaring of public interest and land use regulation an area located to the West of the Mendoza Metropolitan Area and Law Nº6045 Provincial Protected Areas).

- The project will synergistically address the GEF-6 focal areas of Biodiversity and Land Degradation and four of its programs:

- BD-4 Mainstream biodiversity conservation and sustainable use into production landscapes and seascapes and production sectors: Program 9: Managing the Human- Biodiversity Interface and Program 10: Integration of Biodiversity and Ecosystem Services into Development & Finance Planning

- LD-3: Integrated Landscapes: Reduce pressures on natural resources from competing land uses in the wider landscape.  Program 4: Scaling-up sustainable land management through the Landscape Approach; and

- LD-4 Maximizing transformational impact: Maintain land resources and agroecosystem services through mainstreaming at scales.  Program 5: SLM Mainstreaming in Development.

- It is also in alignment with Aichi Targets helping Argentina respond to Aichi Targets Strategic Goal A: Address the underlying causes of biodiversity loss by mainstreaming biodiversity across government and society, Targets:

- 1: By 2020, at the latest, people are aware of the values of biodiversity and the steps they can take to conserve and use it sustainably;

- 2: By 2020, at the latest, biodiversity values have been integrated into national and local development and poverty reduction strategies and planning processes and are being incorporated into national accounting, as appropriate, and reporting systems;

- 3: By 2020, at the latest, incentives, including subsidies, harmful to biodiversity are eliminated, phased out or reformed in order to minimize or avoid negative impacts, and positive incentives for the conservation and sustainable use of biodiversity are developed and applied, consistent and in harmony with the Convention and other relevant international obligations, taking into account national socio economic conditions;

- 4: By 2020, at the latest, Governments, business and stakeholders at all levels have taken steps to achieve or have implemented plans for sustainable production and consumption and have kept the impacts of use of natural resources well within safe ecological limits;

- 7: By 2020, areas under agriculture, aquaculture and forestry are managed sustainably, ensuring conservation of biodiversity; and

- 14: By 2020, ecosystems that provide essential services, including services related to water, and contribute to health, livelihoods and well-being, are restored and safeguarded, taking into account the needs of women, indigenous and local communities, and the poor and vulnerable.

- Moreover, the project is consistent with the Sustainable Development Goals (SDG), particularly Goal 15 Protect, restore and promote sustainable use of terrestrial ecosystems, sustainably manage forests, combat desertification, and halt and reverse land degradation and halt biodiversity loss.

# Strategy

- The objective of the proposed project is to generate multiple biodiversity and land degradation benefits by developing a system of policy, economic, financial and technical instruments and governance mechanisms for Environmental Land Use Planning to mainstream socioeconomic and environmental evaluation of ecosystem goods and services in decision-making in different government levels and sectors. The project will reduce biodiversity loss and land degradation by integrating biodiversity (BD) conservation and sustainable land management (SLM) approaches into the production practices of the main sectors driving these processes, namely the agriculture and livestock sector and the emerging threats from mining and infrastructure expansion in peri-urban areas in decision-making, planning and sector finance allocations at different government levels.

- The intervention strategy to implement the ELUP approach takes into account the country’s federal structure and the prerogatives of the national and provincial governments that own the natural resources found in their land. It also recognizes the need to work at multiple levels to address barriers that stem from beyond national boundaries such as market limitations; and the need to test at local levels instruments and tools that encompass a set of different ecoregions and land use modalities. To optimize the generation of global environmental benefits (GEB) the project will focus principally on the targeted sectors driving biodiversity conservation loss and land degradation. The guidance, instruments and approaches to define and enforce production practices in the different land use zones to be defined in ELUP will be tailored to these sectors.

- In addition, ground level work to pilot these approaches will focus on ecoregions recognized for their globally significant biodiversity or prioritized in national plans to reduce land degradation and desertification. These are the High Andes, Puna, Yungas Forest, Patagonian Steppe, Pampas Lower Parana river ecoregion (Parana Delta & Flooded Savannas), Low Monte & High Monte. It will be undertaken in three pilot provinces, namely Buenos Aires, Jujuy, and Mendoza. They were selected to represent the main challenges from the three sectors; different levels of advances in regulatory framework or on the ground experiences with ELUP-related instruments; and the presence of the target ecoregions.

- To implement these approaches and achieve the stated objective the project has been organized into four outcomes (see Figure 1 – Theory of Change):

1. Federal enabling framework and strategies to reinforce ELUP, and underpin implementation in priority ecosystems and habitats to reduce pressure from key production sectors (target sectors: agriculture & livestock; mining; and peri-urban infrastructure

2. Application of ELUP procedures and instruments in pilot provinces with targeted ecoregions and production sector land uses;

3. Replicability framework for ELUP uptake in all Argentine provinces; and

4. Dissemination of lessons learned, monitoring & evaluation

- Project Outcome 1 will work at the Federal level and will develop a policy framework, strategies and regulations to promote and regulate ELUP. Working in close coordination with results from Outcomes 2 and 3 below, through Outcome 1 the project will support the national framework for procedures, instruments and tools to be used at different levels to define and implement ELUP. This will include achieving a set of agreements and commitments between the national and provincial governments to reinforce planning and ELUP; mainstreaming new decision-making tools into sectoral planning and finance allocation such as the economic appraisal of ecosystem goods and services, including land degradation and desertification; and promoting inter-sectoral and inter- jurisdictional coordination to implement plans, programs and projects related to environmental planning and ELUP.

- Implementation of this outcome will be undertaken through several approaches. One approach will be to develop a system for analysis of environmental variables and dissemination of environmental information in support of the ELUP process.  A second approach will be to define and agree upon ELUP criteria at the Federal level to guide ongoing and future processes in the provinces and provide the minimal standards that will be regulated through law for ELUP in provinces. A third approach will be to develop and agree on criteria and standards for undertaking ELUP, incentives, and sectoral and economic instruments for implementation and mainstreaming into sector finance. A fourth approach will be to develop and strengthen inter-institutional and inter-sectoral dialogue and coordination, including with civil society and private sector. Through multi-stakeholder dialogue and coordination spaces, the above instruments and approaches will be discussed with, agreed upon and standardized by the main sectors. The end result will be a public policy framework and strategies to reinforce ELUP as a Federal instrument to mainstream environmental, social and economic variables in development planning and sector finance.

- Project Outcome 2 will support ground-level work to develop decision-making instruments to facilitate ELUP in the three pilot provinces in target landscapes selected in accordance with the conditions and scale needed for each instrument and also to optimize the generation of GEBs by validating different approaches to adjust production practices needed to deliver increased BD conservation and reduce LD. Action will cover different spatial areas, namely provincial level; target landscape level including several municipalities but not the entire province, and specific sites in the landscape to validate ELUP instruments and production practices to be set for each land use zone.  Provincial counterparts will be the Provincial Agency for Sustainable Development (OPDS) in Buenos Aires, the Ministry of Environment in Jujuy, and the Secretariat for Environment and Land Use Planning (SAOT) in Mendoza.

- Several approaches will be undertaken. One will be to support building the ELUP provincial governance framework to plan, agree upon and implement land use restrictions taking into account the status of ELUP development in each province.  Buenos Aires has some experience in land use planning having realized the land zoning for the Native Forest Law and is working in developing regulations. This provides an entry point for project support in mainstreaming ELUP in planning and regulatory instruments. Jujuy has acquired experience in participatory land zoning, mainly at urban level but no sufficiently in regards to natural resources. In this case, the entry point for the project is mainstreaming the environmental dimension through ELUP in planning and regulatory instruments. Mendoza has an ELUP framework comprising provincial regulations and a provincial land use plan; however it is not fully implemented therefore the project will in this province support the implementation of the existing framework.

- A second approach will be to pilot mechanisms for inter-institutional stakeholders and for multi-sectoral decision-making, seeking to facilitate the ELUP process and ensure stakeholder participation and buy in.  The third approach will be validating and applying a set of instruments to enhance compliance with ELUP and define sector practice limits and production guidance for each zone; and strengthening surveillance and oversight to promote the uptake of the newly defined production practices by sectoral and civil society stakeholders.  A key aspect will be focusing on the target production sectors and mainstreaming guidelines and approaches into relevant sectoral programs that channel resources to provinces to support production. Incorporating regulations for adoption of specific production practices in the federal programs will further enhance implementation of the land use restrictions defined in provincial ELUP. A fourth approach will be the validation and assessment of the production and environmental viability of management practices with the potential to reduce threats and optimize the flows of ecosystem goods and services in areas identified as priorities for BD conservation and reduction of LD.  This will deliver direct benefits to ecoregions with globally significant BD or top priorities for combatting LD.

- The target landscapes in Buenos Aires, Jujuy and Mendoza are representative of the main challenges from the three sectors and therefore the experiences and lessons have a high potential for replicability. They were selected based on the following criteria: a) ecological significance, b) BD value, c) impacts of the target sectors, d) potential for improving livelihoods of the inhabitants, and e) presence of programs and projects with potential for building synergies as well as local capacities.  To select the target landscapes the territories characterized by socio-environmental problems or imbalances and territories with strategic environmental values to preserve were assessed in each province. The above criteria were applied in these territories incorporating in the analysis data such as baseline information; maps of native forest distribution, ecoregions, watersheds, and important BD areas of the province for mammals, birds, reptiles and amphibians, and information on cultural values, as available in each province.  Table 1 below summarizes the main characteristics of the selected target landscapes. Annex L includes a more detailed profile of each target landscape.

Table 1 – Summary of main characteristics of the selected Target Landscapes

| Province | Buenos Aires |  |  | Jujuy |  | Mendoza |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Target Landscapes | Riverine Forests, Eastern “Talares” and Samborombon Bay | Parana River Delta | Southwestern Buenos Aires | Hornocal-Valle Grande | Susques-Jama-Catua-Olaroz | Andean Piedmont of the Metropolitan Area of Mendoza | Piedmont of the Uco Valley | Llancanelo Lagoon –Malargüe River Basin | Northern Oasis – Green Belt |
| Ecoregions | Pampas | Delta and islands of the Parana River | Espinal | Puna, Yungas Forest, High Monte | Puna, High Andes | High Andes, Low Monte, High Monte | High Andes, Low Monte, Patagonian Steppe | High Andes, Patagonian Steppe | Low Monte |
| Surface area (has) | 275,000 | 6,300 | 180,400 | 86,974 Puna: 51,915 Yungas: 14,403 High Monte: 20,656 | 32,354 Puna: 9,962 High Andes: 22,392 | 25,711 High Andes: 358 Low Monte: 19,034 High Monte: 6,319 | 28,525 High Andes: 2,138 Low Monte: 200 Patagonian Steppe: 26,187 | 42,884 High Andes: 29,647 Patagonian Steppe: 13,237 | 63,350 Low Monte: 63,350 |
| Main localities and population | Magdalena, Punta Indio, Chascomús, Lezama, Castelli 67,936 inhabitants, mostly urban (only 4.8% is rural) | Campana; San Fernando Low population density | Villarino; Carmen de Patagones > 60,000 inhabitants; important rural exodus | Humahuaca, Huacalera, Valle Grande, Uquía, San Francisco, Santa Ana, Yacoraite, Caspalá, Valle Colorado, Palca de Aparzo, Coctaca, Pampichuela, Palca de Varas, Cianzo, Aparzo 14,255 inhabitants 26 indigenous communities | Susques, Catua, Olaroz Chico, Jama, Mina Providencia 2,331 inhabitants 10 indigenous communities | Las Heras- Capital- Godoy Cruz- Luján 30,000 inhabitants | Tunuyán, San Carlos, Tupungato Low population density; mostly rural landowners | 27,660 inhabitants Presence of indigenous peoples: 600 individuals (150 families) | Guaymallén, Lavalle, Maipú 25,000 inhabitants |
| Main land uses | Livestock; extraction of seashells in coastal areas and wood for fuel | Fishing; hunting; bee-keeping; fruticulture, livestock | Livestock is the main land use; agriculture (wheat and other winter crops) in areas prone to drought and wind erosion. Irrigation is used in agricultural areas; in non-irrigated areas mixed agriculture-livestock production | Commercial horticulture along the Grande River; subsistence agriculture and livestock; tourism in protected areas | Subsistence agriculture and livestock; tourism in protected areas; area of high commercial transit – Jama Pass to Chile; mining (quarries, prospection; requests for exploration permits and concessions) | Urban development; agriculture | Large scale commercial agricultural operations (mainly vineyards) using ground and underground water for irrigation; tourism | Subsistence livestock production (mainly goat); tourism; oil extraction is the main income of the area | Commercial and family horticulture, main supplier of fresh vegetables to Mendoza and other provinces |
| Main environmental characteristics - Global and local values | BD rich landscape; supply of freshwater located under seashell deposits in wetlands; synergies between forests and wetlands; forests located over seashell deposits help fix soils and landscape shapes; ES provided by wetlands and forests. Presence of protected areas including Delta del Parana Biosphere Reserve and Otamendi Natural Reserve Ramsar Site. See Table 2 below for globally significant species in the ecoregions of which this landscape is part | BD rich landscape; wetlands provide aquifer recharge; flood control; sediment retention; stabilization of coasts; erosion control; resources for local population (fauna, fisheries, forest products; forage); tourism; water supply. Protected areas: 2 Biosphere Reserves (El Destino, Parque Costero del Sur) and 3 Ramsar Sites (Bahia Samborombon, Bahia Samborombon Natural Reserve, Bahia Samborombon Wildlife Refuge). See Table 2 below for globally significant species in the ecoregions of which this landscape is part | Transition area between semi-arid and humid ecosystems; combines forest patches with grasslands and sometimes wetland communities; characterized by the presence of species of the gender Prosopis; forest remnants provide refuge to threatened pampean species e.g. Pampas deer. Several protected areas (natural reserves and wildlife refuges). See Table 2 below for globally significant species in the ecoregions of which this landscape is part | High ecosystem diversity: Yungas forest, grasslands, montane forests, queñoa and churqui forests, Puna shrub steppe, wetlands and water bodies; important protected areas (e.g., Quebrada de Humahuaca and Qhapac Ñam or Inca Road are World Heritage Sites, Yungas Biosphere Reserve). See Table 2 below for globally significant species in the ecoregions i of which this landscape is part | Altitudes range from 3,500-6,000 meters above sea level; water is scarce, BD and productive activities concentrate around water bodies; geological attractions (e.g. volcanos, salt flats); presence of protected areas (e.g. Olaroz-Cauchari-Catua Flora and Fauna Reserve). See Table 2 below for globally significant species in the ecoregions of which this landscape is part | Transition area between mountain and plains (up to 1,500 meters above sea level) where fauna and flora species of both regions co-exist; dominant shrub steppe is the “jarillal” (Larrea spp); Divisadero Largo Reserve; there is good vegetation cover in slopes preventing erosion and facilitating infiltration of water reducing probability of landslides over populated areas; presence of archaeological sites. See Table 2 below for globally significant species in the ecoregions of which this landscape is part | Transition area between mountain and plains (2,000 meters above sea level and higher); dominant shrub steppe is the “jarillal” (Larrea spp); subject to water erosion accelerated by slopes; presence of protected areas (Manzano Historico Natural and Cultural Reserve). See Table 2 below for globally significant species in the ecoregions of which this landscape is part | Llancanelo lagoon and salt flat make up an endhoreic basin fed by the Malargüe River; the river and aquifers supply drinking water and for industrial and agricultural uses; it is a Ramsar Site and protects over 150 bird species (flamingo populations are the largest in the world) and numerous mammal species. Aquatic and sub-aquatic plant species are dominant. See Table 2 below for globally significant species in the ecoregions of which this landscape is part | The most important of the province´s oases formed by the watersheds of the Mendoza and Tunuyan rivers; important aquifers that provide freshwater for human and animal consumption and irrigation; diverse agro-ecosystem where horticulture, vineyards, olive groves and fruit orchards co-exist with natural vegetation. See Table 2 below for globally significant species in the ecoregions of which this landscape is part |
| Threats to BD conservation and SLM | Deforestation of “talar” (Celtis tala) forests for extraction of seashells, agriculture and pastures, fuelwood; use of agro-chemicals over “talares”; Invasive alien species of flora and fauna; urban expansion. | Wildfires; “Imported” practices from other ecosystems (invasive alien species of flora and fauna, construction of retaining walls to stop flooding; alteration of natural ground level, modification or creation of water bodies, housing developments. | Loss of forest cover and fragmentation (erosion, salinization, soil loss, rising of water levels); overgrazing; wildfires; agricultural practices not adapted to the region. | Uncontrolled urban expansion; unsustainable extraction of natural resources (e.g., queñoa for fuelwood, hunting); unsustainable livestock practices. Tourism is expected to increase in the future with potential negative impacts (increased solid wastes, road maintenance, use of chemical baths, commercial signing). | Uncontrolled urban expansion; unsustainable extraction of natural resources (e.g., queñoa for fuelwood, hunting); unsustainable livestock practices. Tourism is expected to increase in the future. Increased tourism forecasts with potential negative impacts (increased solid wastes, road maintenance, use of chemical baths, commercial signing); mining is also expected to increase | Unplanned urban and agricultural expansion along the Andean piedmont increases the risk of landslides, habitat fragmentation; unsustainable extraction resources (fuelwood, hunting); unsustainable production practices (e.g., overgrazing); lack of effective conservation strategies and management of protected areas. | Unplanned urbanization of the piedmont; housing and agricultural developments without considering the piedmont´s hydrological functions and mitigation measures; expansion of agricultural frontier along the valley and Mendoza River due to availability of water and adequate climate for vineyards. | Decreased water flow of the Malargüe River due to over-use for agriculture; unsustainable extraction of resources (fuelwood, hunting); unsustainable production practices (e.g. overgrazing); lack of effective conservation strategies and management of protected areas; urban growth. | Urban expansion over agricultural lands; contamination of soil and water by domestic and industrial wastes and over-use of agro-chemicals; degraded lands and salinization; increasing open dumps. |
| National and/or provincial regulatory framework for land use and ELUP | A proposal elaborated to develop the ELUP Strategic Plan for Buenos Aires; Federal Native Forest Law Nº26331 and Provincial Native Forest Law Nº14888; Comprehensive Law on Environment and Natural Resources Nº 11723; ongoing project “Inventory of Wetlands of Buenos Aires”; Strategic Plan for Conservation and Sustainable Use of the Parana River Delta |  |  | Federal Native Forest Law Nº26331 and Provincial Law Nº5676 Adaptive Land Use Plan for Forest Areas of Jujuy: Law Nº6080 Provincial System of Natural Protected Areas |  | Provincial laws: Law Nº 8999 approving the Provincial Land Use Plan; Law Nº8051 for Land Use Planning and Land Uses; Law Nº 4886 establishing zoning and land uses in the Western Area of the City of Mendoza; Law Nº 5804 declaring public interest and land use regulation for an area located to the West of the Mendoza Metropolitan Area; Law Nº6045 Provincial Protected Areas |  |  |  |
| Key sectors and expected global benefits | Agriculture and Livestock SLM, reduced pressure on VGA; optimizing sustainable productivity; reduction of pressure on BD | Agriculture and Livestock; Peri-urban infrastructure SLM and reduced pressure of urban expansion | Agriculture and Livestock SLM; optimizing sustainable productivity; reduction of pressure on BD | Agriculture and Livestock; Tourism; Peri-urban and tourism infrastructure; SLM; optimizing sustainable productivity; reduced pressure on BD; enhanced BD conservation in PA | Agriculture and Livestock; Tourism; Peri-urban and tourism infrastructure; Mining SLM; optimizing sustainable productivity; reduced pressure on BD; enhanced BD conservation in PA | Agriculture and Livestock; Peri-urban and tourism infrastructure SLM; optimizing sustainable productivity; reduced pressure on BD; enhanced BD conservation in PA | Agriculture and Livestock; Peri-urban and tourism infrastructure SLM; optimizing sustainable productivity; reduced pressure on BD | Agriculture and Livestock SLM; optimizing sustainable productivity; BD conservation and reduced pressure | Agriculture and Livestock; Peri-urban and tourism infrastructure SLM; optimizing sustainable productivity; reduced pressure on BD |

- Project Outcome 3 will support the development of a replicability framework for ELUP uptake in all Argentine provinces by strengthening the input of other provinces into the development of ELUP and enhancing its uptake at scale across the country through a threefold approach.  Selection of the non-pilot provinces to participate in this outcome will be undertaken during project implementation and will take into account selecting at least one province representing each of the regions into which Argentina is divided, that is, Center, Cuyo, Northeast, Northwest and South. The first approach will support a broader analysis of experiences throughout the country.  This will include defining an optimal mix of instruments to implement land use zoning and related requirements for sector production.  This approach will also provide inputs to the processes to be undertaken in Component 1 for mainstreaming ELUP at federal level.

- The second approach involves undertaking a program to strengthen provincial institutions to carry out ELUP, which will comprise training addressing the non-pilot provinces as well as developing methodological guides for ELUP in pilot provinces, in non-pilot provinces and for upscaling in ecoregions and shared ecosystems.  The third approach will entail developing a system to evaluate and monitor ELUP implementation in Argentina. This system will serve to analyze the process of mainstreaming policies, regulations and instruments in support of public planning and management of the territory under an ELUP approach. It will monitor progress in the implementation of ELUP, evaluate the impacts and degree of acceptance by stakeholders, propose measures and recommendations to decision makers and promote awareness raising within the general public.

- Project Outcome 4 will provide the necessary means for the monitoring and evaluation (M&E) of project results in order to contribute to the adaptive management of the project and improve its implementation. A Mid-term Review (MTR)  will be undertaken after the third PIR and  a Terminal Evaluation (TE) will be prepared by independent evaluation teams and compiled into reports. Outcome 4 will also enable consolidation of lessons learned extracted throughout the course of the project’s implementation and support dissemination of lessons learned and experiences at national and provincial levels. The project will systematize and publish best practices and lessons learned, which will help ensure access to this information by the wider stakeholder community to the experiences, failures and successes of the pilots undertaken by the project.  This outcome will also monitor the effectiveness of implementation of the Gender Mainstreaming Strategy and Action Plan.

- Project design takes into account the assumption that achievement of the proposed outcomes relies heavily on the willingness and support of the federal and provincial institutions and key stakeholders to overcome the identified barriers that result in inefficiencies, overlap of actions, and missed opportunities for inter-sectoral collaboration. The strategy explained above is built upon the active participation of public, private and civil society partners and is expected to result in the development of an enabling framework for ELUP at federal and provincial levels for reducing biodiversity loss and land degradation and generating multiple benefits for the long-term protection of global and local environmental values in Argentina (see also Figure 1 – Theory of Change below).

- Gender mainstreaming and empowerment of women is a fundamental part of the intervention strategy.  The project strategy mainstreams gender issues through among others: i) political and technical dialogue at federal level to ensure the participation of women in the development of the instruments and approaches to facilitate ELUP in multi-stakeholder dialogue and coordination spaces, and other project processes; ii) building the capacities of public institutions to mainstream gender into the ELUP instruments and approaches to be undertaken; iii) targeted training for women beneficiaries (indigenous and non-indigenous) in the target landscapes to: promote gender equality in the management, use and conservation of biodiversity; understand the differential roles of women and men and ensure that a tailored approach is used for both men and women so that they will benefit from project interventions; and promote the participation and consideration of gender issues in the design and implementation of the project; iv) sex-disaggregated data for M&E; and v) extracting lessons which will be included in the project´s publications.  Further details are included in Section IV Results and Partnerships below on gender mainstreaming and Annex G Gender Analysis and Action Plan.

- Given the presence of indigenous peoples in the Jujuy and Mendoza target landscapes, special attention will be paid to multi-cultural aspects and participation processes. Interventions addressing indigenous communities will follow and respect their organizational ways and cultural patterns; will ensure that stakeholders show respect for their dignity and human rights and will be carried out with a multi-cultural approach, respecting their collective and individual rights protected by international and national regulations and including safeguards to ensure actions do not negatively affect the livelihoods of indigenous communities. All actions with indigenous peoples will be guided by the respect to their rights to: a) participation in the design, implementation and evaluation of public policies, plans and programs; b) prior consultation before adopting administrative or regulatory measures that may affect them; and c) Free, Prior and Informed Consent in cases where their fundamental rights may be affected or their integrity may be put at risk. Further details are included in Section IV Results and Partnerships below on stakeholder engagement plan and Annex F Stakeholder Engagement Plan).

- The project will deliver a number of environmental and socio-economic benefits, which are detailed in the Results Framework (Section VI) and Annex B GEF Core Indicators, including: a) 5,079,260 hectares (has) where ELUP has been agreed upon and implemented in priority landscapes in the three pilot provinces through applying regulations, instruments and approaches to enforce modified production; b) an additional 507,926 has covering the total surface of  ecoregions in the three pilot provinces in which upscaling is expected due to project dissemination activities and co-financed interventions; c) 613,128 has in the target landscapes of the pilot provinces under improved practices to benefit BD and sustainable land management in production systems and where BD conservation and LD reduction benefits have been accrued as measured through the level of improvement in Net Primary Productivity (NPP), percentage of land cover and soil organic carbon content  (GEF Core Indicator 4); d) 128,370 has of land (agricultural, forest and forest lands and natural grass and shrubland) restored in the target landscapes of the pilot provinces (GEF Core Indicator 3); e) 11,665 direct project beneficiaries that improve their livelihoods through environmentally-friendly natural resource management and sustainable production (at least 40% are women; 10% of total number belong to indigenous groups) (GEF Core Indicator 11); f) 20% increase in the Sustainable Livelihoods Framework Index of beneficiaries in the target landscapes.

- These benefits will also translate into direct benefits for species many of which are globally significant, as summarized in Table 2 below:

Table 2 – Globally significant BD in ecoregions of Argentina targeted by the project

| Ecoregion | Examples of species to benefit |
| --- | --- |
| Espinal | Reduced pressures on relict populations of endangered species facing conservation problems such as the Pampas deer (Ozotoceros bezoarticus) and the yellow cardinal (Gubernatrix cristata) |
| Pampas | Endangered pampas deer (Ozotoceros bezoarticus); ruddy-headed goose (Chloephaga rubidiceps) and the Swainson’s hawk (Buteo swainsoni), migratory birds, the endangered species Pampas Meadowlark (Sturnella defilippii-). |
| Low Monte | Fragile ecosystems with endemic flora and fauna with varying degrees of endangerment; pressures reduced on shrubs and steppes and their related fauna: Andean fox (Lycalopex culpaeus), Molina's Hog-nosed Skunk (Conepatus chinga), common yellow-toothed cavy (Galea musteloides) |
| High Andes | Andean condor (Vultur gryphus), pressure will be reduced on species such as the guanacos -(Lama guanicoe) |
| High Monte | Fragile ecosystems, with land degradation and desertification risks: benefits to wild fauna: golden lancehead (Bothrops ammodytoides), Amazon false coral snake (Oxyrhopus rhombifer), burrowing parrot (Cyanoliseus patagonus), puma (Puma concolor), and also on endemic fauna and flora |
| Puna, High Andes | Andean cat (Leopardus jacobita), Lesser Rhea (Pterocnemia pennata), puma (Puma concolor), Andean condor (Vultur gryphus), wetland bird congregations such as the Chilean flamenco -(Phoenicopterus chilensis), Andean flamingo (Phoenicoparrus andinus), Puna flamingo (Phoenicoparrus jamesi) and the horned coot (Fulica cornuta); Andean fox (Lycalopex culpaeus), puma (Puma concolor), amphibians and invertebrates. |
| Yungas Forest | Important flora: trees, e.g., palo blanco (Calycophyllum multiflorum), palo amarillo (Phyllostylon rhamnoides), pink lapacho (Handroanthus impetiginosus)- and endangered fauna: jaguar (Panthera onca), lowland tapir (Tapirus terrestris, N. Andean Deer (Hippocamelus antisensis), solitary eagle (Buteogallus solitarius), Chaco eagle (Buteogallus coronatu) |
| Patagonian Steppe | Threatened macá tobiano (Podiceps gallardoi); endemic reptiles (Diplolaemus genus); restricted distribution Somuncura frog (Somuncuria somuncurensis) |
| Parana Delta | Reduced pressure on wetlands benefits wild fauna e.g., Marsh Deer (Blastocerus dichotomus), Dusky-Legged Guan (Penelope obscura), long-tailed otter (Lontra longicaudis) and Geoffroy’s Cat (Leopardus geoffroyi) |
| Coastal Ecosystems | Reduced LD protects dune ecosystems and the habitats of species important for conservation, e.g-, spotted tree iguana (Liolaemus multimaculatus), Southern tuco-tuco (Ctenomys australis), black-and-white monjita (Xolmis dominicanus), Olrog’s Gull (Larus atlanticus), Magellanic Plover (Pluvianellus socialis), migratory shorebirds |

128,370 has of land restored in the target landscapes

128,370 has of land restored in the target landscapes

Additional 507,926 has in the three pilot provinces where upscaling is expected due to project dissemination activities and co-financing

Additional 507,926 has in the three pilot provinces where upscaling is expected due to project dissemination activities and co-financing

613,128 has in the target landscapes under improved practices to benefit BD and SLM in production systems and where BD conservation and LD reduction benefits accrued

613,128 has in the target landscapes under improved practices to benefit BD and SLM in production systems and where BD conservation and LD reduction benefits accrued

11,665 direct project beneficiaries improve their livelihoods (20% increase in Sustainable Livelihoods Framework Index

11,665 direct project beneficiaries improve their livelihoods (20% increase in Sustainable Livelihoods Framework Index

5,079,260 has where ELUP has been agreed upon and implemented in priority landscapes of the three pilot provinces

5,079,260 has where ELUP has been agreed upon and implemented in priority landscapes of the three pilot provinces

Project Impacts

Project Impacts

Knowledge management, M&E

Knowledge management, M&E

Replicability framework for ELUP uptake in all Argentine provinces

Replicability framework for ELUP uptake in all Argentine provinces

Application of ELUP procedures and instruments in pilot provinces with targeted ecoregions and production sector land uses

Application of ELUP procedures and instruments in pilot provinces with targeted ecoregions and production sector land uses

Federal enabling framework and strategies to reinforce ELUP, and underpin implementation in priority ecosystems and habitats to reduce pressure from key production sectors

Federal enabling framework and strategies to reinforce ELUP, and underpin implementation in priority ecosystems and habitats to reduce pressure from key production sectors

Project Outcomes

Project Outcomes

Nationwide ELUP experiences and related instruments evaluated

Nationwide ELUP experiences and related instruments evaluated

Provincial regulatory framework for ELUP strengthened

Provincial regulatory framework for ELUP strengthened

Environmental information system updated and standardized to support the ELUP process & decision- making

Environmental information system updated and standardized to support the ELUP process & decision- making

Project Outputs

Project Outputs

Lesson learned publications

Lesson learned publications

Provincial governance framework for participatory ELUP & sector consensus building

Provincial governance framework for participatory ELUP & sector consensus building

Nationwide ELUP capacity strengthening programme for provincial authorities

Nationwide ELUP capacity strengthening programme for provincial authorities

Federal level ELUP criteria agreed upon

Federal level ELUP criteria agreed upon

Dissemination to sectors

Dissemination to sectors

System to monitor ELUP implementation nationwide established

System to monitor ELUP implementation nationwide established

Set of instruments validated in pilot landscapes for defining and implementing ELUP

Set of instruments validated in pilot landscapes for defining and implementing ELUP

Standardized instruments for implementing ELUP for targeted sectors

Standardized instruments for implementing ELUP for targeted sectors

SLM and biodiversity-friendly production practices validated for different ELUP land use zones

SLM and biodiversity-friendly production practices validated for different ELUP land use zones

Inter-sectoral and inter jurisdictional co-ordination mechanisms

systems

Inter-sectoral and inter jurisdictional co-ordination mechanisms

systems

Project Outcome 4

Project Outcome 4

Project Outcome 3

Project Outcome 3

Project Outcome 2

Project Outcome 2

Project Outcome 1

Project Outcome 1

Development Challenge

Development Challenge

Generate multiple biodiversity and land degradation benefits by developing a system of policy, economic, financial and technical instruments and governance mechanisms for environmental land use planning (ELUP) to mainstream socioeconomic and environmental evaluation of ecosystem goods and services (ES&G) in decision-making at different government levels and sectors

Generate multiple biodiversity and land degradation benefits by developing a system of policy, economic, financial and technical instruments and governance mechanisms for environmental land use planning (ELUP) to mainstream socioeconomic and environmental evaluation of ecosystem goods and services (ES&G) in decision-making at different government levels and sectors

Barriers

Barriers

Dispersed knowledge and insufficient sharing of environmental management practices at provincial and interprovincial levels

Dispersed knowledge and insufficient sharing of environmental management practices at provincial and interprovincial levels

Weakness in provincial tools and instruments to approve, implement and oversee ELUP

Weakness in provincial tools and instruments to approve, implement and oversee ELUP

Inadequate policy & regulatory framework and reliable information to effectively develop ELUP at national and provincial levels

Inadequate policy & regulatory framework and reliable information to effectively develop ELUP at national and provincial levels

Disperse knowledge within and across provinces; insufficient lessons extracted; repetition of sub-optimal approaches; reduced capacity for uptake of positive experiences; few ELUP experiences in provinces

Disperse knowledge within and across provinces; insufficient lessons extracted; repetition of sub-optimal approaches; reduced capacity for uptake of positive experiences; few ELUP experiences in provinces

Information gaps and regulatory constraints; provinces have few staff members and scarce resources; insufficient mechanisms and spaces for participation; insufficient awareness of negative impacts of production; inadequate experience to implement ELUP; information and data do not reflect the value of ES&G

Information gaps and regulatory constraints; provinces have few staff members and scarce resources; insufficient mechanisms and spaces for participation; insufficient awareness of negative impacts of production; inadequate experience to implement ELUP; information and data do not reflect the value of ES&G

ELUP missing in most provinces; sector based approaches; regulations and standards not set for ELUP; limited capacity to reduce impact of production sectors; no assessment of ES loss; lack of inter-institutional and inter-sectoral coordination; disperse environmental information; low level of awareness

ELUP missing in most provinces; sector based approaches; regulations and standards not set for ELUP; limited capacity to reduce impact of production sectors; no assessment of ES loss; lack of inter-institutional and inter-sectoral coordination; disperse environmental information; low level of awareness

Structural/ Root Causes

Structural/ Root Causes

Figure 1. Theory of Change

# Results and Partnerships

Expected Results:

- The principal outputs of the project, which will support the achievement of the project’s four (4) outcomes, are the following:

Outcome 1: Federal enabling framework and strategies to reinforce ELUP, and underpin implementation in priority ecosystems and habitats to reduce pressure from key production sectors (target sectors: agriculture & livestock; tourism, mining and peri-urban infrastructure)

Output 1.1: Information system for analysis of environmental variables to support the ELUP process & decision- making

- The project will technically assist the SGAyDS in developing an information system for analysis of environmental variables in support of the ELUP process. This system will build on existing data banks and will have the objectives of consolidating environmental information and evaluating and monitoring environmental parameters and variables to provide key inputs for better decision-making at all levels. Environmental variables will be defined, validated and finally measured in a collaborative manner through inter-institutional coordination. This will both guide work under Outcome 2 and also be the receptacle of new information as this arises in the pilot provinces.

- Building on the experience of the National Observatory on Land Degradation and Desertification (ONDTyD), the system will comprise a network of political, technical and scientific institutions that will provide data and knowledge and at the same time are the users of the information.  This will include identifying the relevant organizations and inviting them to participate in the network, convening meetings to agree on objectives, rules and procedures.

- There is a large volume of data and information useful for ELUP decision making that are available at national, provincial and local levels from numerous sources, but this needs to be standardized and systematized in order to develop a comprehensive database and to facilitate identifying and filling gaps, both in terms of themes and at the different geographical and jurisdictional scales considered.  Between Project Year (PY) 1 and PY2, the data banks identified during the PPG phase as well as others that may be identified during project implementation will be unified. Given that information is disperse among numerous institutions, an ELUP sub-system within SGAyDS´s Environmental Spatial Infrastructure Data (IDE Ambiente) will be developed to concentrate all the ELUP- related information of interest.  Information and metadata available in the data banks will be standardized and systematized. The existing information within IDE Ambiente will be migrated by the SGAyDS to the sub-system while the information available in other online data bases will be uploaded remotely by each institution, following the existing information sharing protocols of the different IDEs.  The project will provide support for training of technical staff in the protocols and processes for standardizing, systematizing and sharing data and information. In parallel, the environmental variables as well as the methodology for measuring them will be identified and validated within the inter-institutional dialogue spaces to be established under Output 1.4 below.

- Once established, this system will define and/or update a set of SMART and cost-effective indicators for ELUP monitoring and establish the protocols for measuring the different indicators. SDGAyDS and INTA will collaborate to undertake monitoring of indicators. The ELUP sub-system of IDE Ambiente will be the information platform where all the information generated and/or compiled by the project will be uploaded hence facilitating access and dissemination. This will include, among others, geographical information and documentary and audio-visual information.

- Beginning in PY2 and as the information is consolidated and uploaded it will be made available online following the criteria established by the Spatial Data Infrastructure of the Republic of Argentina (IDERA). It will also be continuously updated as new information is generated.  Updating of information will entail the SGAyDS uploading data internally to IDE Ambiente while the other institutions will improve/update their respective information within their own data banks, and the new information will be reflected in the ELUP sub-system.  The environmental variables defined and the results of their application and measurement will also be made available.  All the information produced by the provinces within the framework of the project will be made available to the SGAyDS.

- A key aspect in the functioning of the information system will be the active participation in IDERA. This will be undertaken through sharing information using the IDE Ambiente platform as a tool for online coordination with different government areas, jurisdictions and technical and scientific organizations; and participating in the meetings (annual or bi-annual) of the different IDERA working groups (e.g., cartography, platform, metadata, services) where issues related to information management are discussed and defined. The SGAyDS will participate through IDE Ambiente. This will help to promote the SGAyDS vision on ELUP and support coordination with the participating institutions.

Output 1.2: Federal level ELUP criteria agreed upon

- This output will support defining and agreeing upon ELUP criteria at the Federal level to guide ongoing and future processes in the provinces and provide a public policy framework and strategies to reinforce existing territorial planning and advance ELUP as a Federal instrument to mainstream environmental, social and economic aspects into development planning and finance. Working in close coordination with results from Outcomes 2 and 3, the project will support the national framework for procedures, instruments and tools to be used at different levels to define and implement ELUP.  This output will strengthen the SGAyDS as the national leader of ELUP and will benefit decision-makers at federal level.

- A first set of activities will include assessing mechanisms for ES valuation, BD conservation and SLM practices and developing strategies to promote areas for conservation and restoration with compensation schemes for ELUP implementation. During PY1-PY2 the project will work with SGAyDS, INTA and key stakeholders to undertake these assessments.  For ES valuation this will include further analyzing the viability of three pre-selected methodologies: a) INTA´s ECOSER protocol, b) Targeted Scenario Analysis (TSA), and c) Multi-criteria analysis with Geographical Information Systems (GIS) in the different target landscapes and confirming the methodology to be used in each, as well as identifying and agreeing on the ES to be valued based on experiences of past and ongoing projects (see below). Valuation will be undertaken in the pilot provinces under Output 2.3.

- For BD conservation the measures proposed under the 2016-2020 National Biodiversity Strategy and Action Plan (NBSAP) will be assessed. This will include analyzing in PY1 with the SGAyDS and the environmental authorities of the pilot provinces the categorization of existing species in the target landscapes to define the conservation status of each species and gather the related data. This will be done with information that exists at project start-up. For SLM practices the project will work with the SGAyDS, INTA and pilot provinces environmental authorities to further assess the practices identified during the PPG and those published by the ONDTyD as well as analyzing the status of soils in the target landscapes to confirm which practices are the most feasible (a list of practices is included under Output 2.4).  These different options will be discussed and agreed upon with key stakeholders through participatory mechanisms, including the multi-stakeholder dialogue spaces to be established (Outputs 1.4 and 2.2). The results of these assessments and participatory validation will help consolidate the identification of the ES in each target landscape, key species for conservation and soil conditions resulting in agreed practices to be implemented under Output 2.4.

- Between PY1 and PY3 the project will technically assist the SGAyDS to assess experiences and lessons learned from compensation schemes. This will include the compensations schemes tested by the UNDP-UNEP-GEF Project 3623 “Incentives for Conservation of Globally Significant Ecosystem Services”. The former tested several schemes, namely: PES for water ecosystem services and BD in the Province of Misiones (deductions in the water bill); PES for conservation of native forests focusing mainly on carbon and BD in the Provinces of Chaco and Formosa (payments through forest management plans); and payments for ecosystem services (PES) based on incentives foreseen in the Soil Law of the Province of Entre Rios for BD and soils (tax deductions).  In addition, experiences in implementing the compensation schemes under the Native Forest Law Nº 26331 in different provinces will also be evaluated.  These different options will be discussed and agreed with key stakeholders through participatory mechanisms, including the multi-stakeholder dialogue spaces to be established. The results of these assessments will be taken into account in developing compensation schemes in the pilot provinces under Output 2.3.

- The selected methodologies and schemes will be tested through Outcome 2 beginning in PY3. The results of the above processes together with the results of the implementation of ground work in Outcome 2 will serve as inputs to develop by PY5 two documents: one document containing criteria to determine land uses and restrictions to productive activities that are compatible with local realities and one document containing the strategies to promote areas for conservation and restoration with compensation schemes. These documents will provide inputs to national and provincial ELUP regulations (Outcomes 1 and 2) and will also be the basis for preparing methodological guides for ELUP (to be prepared under Outcome 3).

- A second set of activities will entail strengthening the regulatory framework for implementation of ELUP. This will include undertaking between PY1 and PY2 a comparative study of the ELUP-related regulations to assess experiences and lessons on how other countries have mainstreamed ELUP; as well as an analysis of the existing ELUP-related regulations at national and provincial levels to identify gaps and gather information on the approaches to ELUP taken by each province.  These will generate inputs to develop between PY3 and PY4 proposals to fill in the identified gaps as well as proposals for harmonizing and adjusting the regulatory framework for ELUP mainstreaming BD conservation and SLM. The experiences and lessons acquired in developing and implementing sectoral regulations will be also assessed, analyzing the processes undertaken for their elaboration and adoption, as well as the criteria employed to develop their contents. The above activities will lead to developing a federal minimum standard regulation for ELUP (PY5-PY6). These different assessments, processes and proposals will be discussed and agreed upon through sectoral fora and in the dialogue spaces under Output 1.4 (and including the selected target sectors). At provincial level the results of these processes will serve to strengthen regulations and instruments in Outcome 2 (e.g., planning instruments and regulations in Buenos Aires and Jujuy that currently do not mainstream ELUP criteria and ELUP regulations in Mendoza that are not fully implemented).

- A third set of activities will address mainstreaming ELUP criteria in sector planning and finance frameworks.  Several national level public and private economic instruments related to LD, BD and sustainable development were identified during the PPG, of which the following have been selected for work under this output: a) Forest Plantations Fund (Forest Plantations Investment Law Nº 25 080) ; b) Sheep Recovery Fund (National Sheep and Wool Recovery Law Nº25 422); c) Recovery, Promotion and Development of Goat Production Law Nº 26 141; and d) Galicia Bank Mezzanine Financing credit line.  The project will provide technical assistance to mainstream ELUP criteria in the eligibility criteria of these funds. This will include establishing dialogue and agreements with the institutions in PY2 and from PY3 onward working together to adjust the eligibility criteria, validate them through the dialogue spaces (Outputs 1.4 and 2.2), and testing them through ongoing bottom-up and top-down approaches where the results in the target landscapes (Output 2.3) will provide inputs to undertake such adjustments, which will in turn be then applied in the target landscapes to gain experience and extract lessons for continuous improvement. In addition, the project will continue to assess the instruments identified during the PPG to identify other instruments in which the above process may be replicated, hence increasing the number of instruments mainstreaming ELUP criteria by end of project. Besides the above instruments, Output 2.3 will also assess other instruments which have been identified focusing on the target landscapes. This will serve to develop, e.g., specific financing lines adapted to the characteristics of each landscape and of the provinces, which will be tested for lessons and upscaling.  The work will include mainstreaming climate change considerations (e.g. incentives for practices that favor adaptation) in the above instruments.

- Participation of key stakeholders will be fostered in the above activities through the dialogue spaces to be established in Outputs 1.4 and 2.2 to introduce, discuss and agree on the proposals developed. This will include discussing and agreeing on the results of the assessments, proposed methodologies and schemes, how to implement the methodologies and how to use them to regulate land uses, and validating those that best suit the local realities and adapting them to each target landscape.

Output 1.3: Standardized instruments for implementing ELUP for targeted sectors

- This output will support developing agreed instruments to mainstream ELUP in the target sectors (agriculture and livestock, tourism, peri-urban infrastructure and mining). This includes: a) criteria and mapping of priority areas of environmental value; b) criteria and standards for production practices in restricted use areas that are a priority for BD & ES conservation; c) protocol for setting up protected areas (PA) as a basis for ELUP; and d) tools for Strategic Environmental Assessment tailored to ELUP zoning.

- Project assistance to the SGAyDS will address developing between PY1 and PY3 criteria to define priority areas of environmental value for ELUP to guide the mapping of such areas and initiate a land zoning and land use planning process. Based on the previous inputs, the project will work with the SGAyDS in defining the criteria and guidelines to assess, identify and map the priority areas, as well as the methodology for the analysis and mapping. A document will be prepared containing the basic and auxiliary criteria and selected methodology to guide the process.  The SGAyDS and INTA will work together in evaluating the natural resources through satellite imagery. The project will then work with SGAyDS in collecting, analyzing and processing information and finally elaborating a Map of Priority Areas of Environmental Values for ELUP. To ensure accurateness and representativity of the map the project will support between PY2 and PY4 validation of the criteria and map with scientific committees, experts, and national and provincial technicians through participatory workshops and online. In PY4 based on the results of the validation process the maps will be adjusted as needed and will be published and made available online through IDE Ambiente (Output 1.1) to provinces and institutions to support decision-making processes (e.g., identifying if a proposal for a certain land use affects a protected area or a native forest or a territory inhabited by endangered species).

- In parallel the project will work with the SGAyDS, INTA, pilot provinces and key stakeholders to develop and agree: a) criteria and standards for production practices in the priority areas of environmental value and key sectors; and b) a protocol for setting up PA as the basis for ELUP. In undertaking these activities the project will also work in close coordination with Output 1.2 above, in particular the process for defining the SLM, BD conservation and ES valuation criteria for defining different land use zones and production practices restrictions. Likewise, there will be an iterative process between the federal and provincial levels through feeding inputs in design and implementation of activities under Component 2 and in turn receiving feedback on inputs, experiences and lessons especially from the target landscapes. As part of this process, instruments for Strategic Environmental Assessment (SEA) will be assessed and developed. The planning experiences and lessons acquired in the target landscapes (Component 2) will serve to define guidelines that may contribute to the development of SEA as a planning instrument for ELUP.

Output 1.4 Inter-sectoral and inter jurisdictional coordination mechanisms

- The project will support the development of a twofold approach to promote the permanent dialogue and coordination between institutions, productive sectors and jurisdictions, including public and private sectors and civil society at horizontal (national) and vertical (national, provincial and municipal) levels. This will include: a) multi-stakeholder dialogue and coordination; and b) capacity building for dialogue, coordination and participation.

- The first approach will entail developing multi-stakeholder dialogue and coordination spaces. These will be led by the SGAyDS and will have the objective of providing long-term spaces where the different sectors and institutions can align, take ownership and develop joint concrete actions for mainstreaming of BD conservation and SLM and ELUP in key sectors; generating proposals for inter-sectoral and inter-jurisdictional coordination to prepare and implement ELUP related plans, programs and projects; sectoral planning and mainstreaming provincial ELUP in federal programs; as well as multi-sectoral decision-making to facilitate ELUP implementation; sharing information, lessons and experiences; and optimizing the impact of the different interventions.

- In PY1 the project will work with the SGAyDS and pilot provinces to develop a detailed Indigenous Peoples Plan (IPP) following UNDP standards (a draft IPP is included in Annex E-1) . The project will support the SGAyDS in designing the dialogue spaces, including updating the stakeholder mapping undertaken during the PPG and identifying other institutions that may be invited to participate, convening meetings and agreeing on their structure and functioning (e.g., terms of reference, rules of procedure, protocol for meetings, record keeping, decision making and coordination mechanisms), as well as promoting agreements between the key stakeholders involved to establish dialogue and coordination, and ensuring adequate representation of women and indigenous peoples. Establishment of these spaces will take into account existing national level spaces such as the Federal Council of Environment Ministers (COFEMA), National Advisory Committee for Conservation and Sustainable Use of Biodiversity (CONADIBIO), Federal Council for Planning and Land use Planning (COFEPLAN) and Federal Legislative Council for Environment (COFELMA), which can provide experiences and lessons on inter-institutional and inter-disciplinary participation as well as synergies.  Participants will include national public institutions, technical and scientific committees, pilot provinces, private sector, universities, CSOs and NGOs (the list of institutions identified during the PPG is included in Table 1 of Annex F -Stakeholder Engagement Plan).  As part of the multi-stakeholder coordination under Outcome 1 the project will participate in the roundtables of the National Climate Change Cabinet and in turn the institutions that comprise this cabinet will be invited to participate in the dialogue spaces for participatory ELUP where the proposals for regulations and instruments will be discussed and validated. Climate change considerations will be mainstreamed in these processes through these participatory spaces. Discussions on climate change and its potential impacts will also be a part of the participatory dialogue spaces at provincial level under Outcome 2.

- These spaces will begin to operate in PY2 and throughout the project´s lifetime through – among others to be defined – plenary sessions, working groups, round tables, public audiences, dialogues and fora where the different instruments and approaches developed under the project´s outputs will be discussed with, standardized and agreed upon by the main sectors and key stakeholders. The project will undertake a financial sustainability study during the first year of their operation to identify funding sources to sustain the dialogue spaces.

- The second approach will include developing a capacity building program for mainstreaming ELUP, BD conservation and SLM. The capacity building program will include different formats and contents and will be implemented at national level through this Output, for pilot provinces and target landscapes through Output 2.2 and for non-pilot provinces through Output 3.2.

- The project will technically assist the SGAyDS in PY1 to design the capacity building program for national and provincial levels and it will be implemented throughout the project´s lifetime. Capacity building will target staff from the SGAyDS and government sectoral institutions, provincial governments as well as academia, private sector and NGOs, CSOs, producers and communities covering key themes including: ELUP as a tool, BD, SLM, livelihoods, key aspects of social participation, skills and tools for participation and conflict resolution (with a special focus on indigenous peoples participation). The program will seek to: a) assess the training needs and demands of the different national level stakeholders and beneficiaries; b) define objectives, prioritize themes and develop materials; c) establish the methodologies for each type of capacity building activity proposed, identifying the tools to be used, which must include both theory and practice; and d) evaluate the capacity building activities and the program itself to determine changes in knowledge, understanding and skills for ELUP. Training will be supported by communication and information materials to raise awareness about ELUP and about the economic value of ecosystem goods and services. Table 3 below summarizes the preliminary design of the capacity building program.

Table 3 – Main aspects of the capacity building program (national level and provincial levels)

| Type of Activity | Subjects | Available Resources | Participants |
| --- | --- | --- | --- |
| Capacity building workshops Face-to-face modality 8-16 hour workshops Objective: Presentation and discussion and mainstreaming of ELUP and fundamental concepts | ELUP: a) Conceptual and legal framework; b) Public management aspects; c) Experiences at national, regional and international levels; d) Ecosystem goods and services; e) Environmentally friendly productive practices; f) BD; g) Land uses; h) Economic, fiscal, social instruments for ELUP; i) Climate change (vulnerabilities and expected impacts) | SGAyDS Universities NGOs (e.g., Environment and Natural Resources Foundation) | SGAyDS (areas both working with and not working with ELUP); INTA; sectoral institutions (agriculture and livestock, infrastructure, mining, tourism); academia, NGOs, CSOs, producers, communities |
| Workshops and clinics for exchange of best practices and lessons learned | Existing experiences in design, management and implementation of ELUP in the public sector | Project technical team | SGAyDS (staff working in ELUP); INTA; academia, NGOs, CSOs, |
| Capacity building workshops Face-to-face modality 8-16 hour workshops Objective: Improve institutional and sectoral capacities, coordination, and management of interests, and practices in relation to ELUP | Participation, collaboration and dialogue for ELUP: a) ELUP conceptual framework; b) Processes and tools for participation; c) Conflict management and strategies: dialogue-negotiation or mediation; d) Project mechanisms to manage consultations and conflicts; e) promotion of participation of women (indigenous and non-indigenous) and consideration of gender issues in the design and implementation of project interventions | Specialists in participation systems and coordination with ELUP | SGAyDS; INTA; sectoral institutions (agriculture and livestock, infrastructure, mining, tourism); academia, NGOs, CSOs, |
| Capacity building workshops Face-to-face modality 8 hour workshops Objective: Improve institutional capacities on traditional knowledge and practices | Role of Indigenous Peoples in ELUP: a) legal framework for Indigenous Peoples; b) productive experiences and livelihoods of indigenous peoples in target landscapes; c) project´s social safeguards; d) participation schemes (free, prior and informed consent); e) promotion of participation of women and consideration of gender issues in the design and implementation of project interventions | Specialists in Indigenous Peoples issues (preferably representatives of indigenous peoples) | SGAyDS; INTA; sectoral institutions (agriculture and livestock, infrastructure, mining, tourism); academia, NGOs, CSOs, producers, communities |
| Training and awareness raising workshops Face-to-face modality 8 hour workshops Objective: improve institutional capacities for gender mainstreaming | Promotion of participation of women, gender approach and gender mainstreaming in the design and implementation of project interventions | Specialists in gender mainstreaming | SGAyDS; INTA; sectoral institutions (agriculture and livestock, infrastructure, mining, tourism); academia, NGOs, CSOs, producers, communities |

Outcome 2: Application of ELUP procedures and instruments in pilot provinces in targeted ecoregions and production sector land uses

Output 2.1. Provincial Regulatory Framework for ELUP strengthened

- The project will support the provinces of Buenos Aires, Jujuy and Mendoza in strengthening the provincial regulatory framework for ELUP. This will done through: a) strengthening existing provincial laws through criteria, methodological protocols, legal and administrative procedures, and technical, economic and financial instruments for ELUP, incentive mechanisms, credit restrictions, or trade-off mechanisms; b) developing regulations and instruments to implement ELUP at provincial and/or municipal levels; and c) analysis of alternative strategies to identify “best-bet” approaches for internalizing the flows of costs and benefits of different environmental management approaches. The different proposals developed for strengthening the regulatory frameworks of the provinces will be discussed and agreed upon in the multi-stakeholder dialogue spaces to be established under Output 2.2. All the information produced by the provinces within the framework of the project and related to ELUP will be made available to the SGAyDS.

- Buenos Aires: The project will support OPDS in developing in PY1-PY2 a proposal (e.g., decree or resolution) to regulate articles 7 and 9 of the Law Nº 11 723 for Environment and Natural Resources of the Province of Buenos Aires mainstreaming ELUP. In addition, in PY1 and PY2 the project will assist in developing guidelines for all sectors mainstreaming ES and watershed perspectives, and beginning in PY3 through the remainder of the project in promoting the adoption of these guidelines in the design and implementation of provincial and municipal initiatives. At the same time the project will support the assessment of strategies to identify the best options for mainstreaming costs and benefits in accordance with different approaches to environmental management.

- The project will also assist in establishing two Observatories. The first one will be an Environmental Observatory to oversee interventions in the target landscapes; it will have the objectives of: a) assisting OPDS in evaluating and implementing environmentally sound practices adopted by urban, peri-urban and rural stakeholders, and b) selecting and validating indicators addressing soil, water and BD for monitoring the sustainability of relevant production systems in the target landscapes.  The second one will be a Territorial Practices Observatory to promote new development perspectives and share information and knowledge between stakeholders in defined areas, e.g., the project´s target landscapes.

- Jujuy: The project will support the Ministry of Environment in improving the provincial regulatory framework through mainstreaming ELUP criteria into provincial laws.  Two laws have been identified, namely Law Nº 5 676 which approves the Adaptive Land Use Plan for Forest Areas of Jujuy and the General Environment Law Nº 5 063.  The project and provincial authorities will agree on a workplan to strengthen these laws. This may include developing guidelines and/or regulations for ELUP as well as incorporating the results of economic valuations and the economic and financial instruments assessed and developed under Output 2.3, which will be undertaken between PY2 and PY3.  As the results of the activities undertaken in Output 2.3 are made available, these will feed into this Output and new guides or regulations may be developed throughout the remainder of the project. The proposals developed will be discussed and agreed within the multi-stakeholder dialogue spaces to be established under Output 2.2. In addition, project support will address evaluating the implementation of Law Nº 6 080 Provincial System of Natural Protected Areas, extracting experiences and lessons and based on them developing a Management Plan for the system (PY1-PY3). Project support will also address designing specific instruments for the target landscapes (PY1-PY3) to be implemented under Output 2.4 through the remainder of the project. These include developing: a) guidelines for strategic planning of the Hornocal-Valle Grande corridor with an integrated approach that incorporates environmental, social and economic variables; b) a schematic plan to implement the Urban Solid Waste Management System within the framework of the Provincial Urban Solid Waste Management Law Nº 5954; c) tourist corridor from Susques to Catua in the Susques-Jama-Catua-Olaroz target landscape; and d) management plan for the Olaroz-Cauchari / Catua Fauna and Flora Reserve.

- Mendoza: Project assistance will address supporting the Secretariat of Environment and Land Use Planning (SAOT) in the implementation of Law Nº 8 051 Land Use Planning of Mendoza. This will be done through strengthening existing regulations and mainstreaming ELUP criteria into regulatory instruments. This will include developing specific regulations to operationalize the law and to strengthen ELUP schemes, as well as strengthening land use planning programs at the municipal level to operationalize ELUP provincial regulations.  The project will support assessing implementation and enforcement through protocols, methodological guidelines, strategic plans, and economic and financial instruments.

- The project will support strengthening the regulatory and control framework regarding land uses and development of activities in the piedmont of the Pre-Andean Range and the Front Andean Range. This will include several approaches.  One approach will be to define criteria for land uses compatible with natural and cultural values and their functionality, and incorporating environmental risk considerations – particularly the risk of alluvial fan hazards that may be created by land clearing -  and mainstreaming these criteria in regulations. This activity will be based on Law Nº 5804 declaring of public interest and land use regulation an area located to the West of the Mendoza Metropolitan Area and zoning that incorporates productive and conservation areas as well as management criteria of the productive units.

- For the Mendoza Green Belt the project will support developing planning instruments specifically addressing SLM, BD and ES (PY1-PY6).  This could include for instance mainstreaming soil management and BD conservation criteria in the corporate social responsibility programs of the large scale agricultural operations in this landscape. In addition, the project will assist in generating baseline information to understand and zone territories in rural areas and the urban-rural interface to elaborate municipal ELUP plans that mainstream the results of the ES valuation exercises under Output 2.3. For the Uco Valley target landscape the project will assist in developing integrated plans for restoration of degraded areas due to mining operations.

- In addition, the project will support approaches targeting protected areas: a) assessing Law Nº4 902 that creates the Divisadero Largo Reserve (Piedmont AMM target landscape) to develop regulations for conservation compatible activities (agriculture, industry and tourism);  b) analyzing and developing instruments to establish private protected areas with the active participation of the private sector; c) developing a comprehensive plan for public use infrastructure in protected areas and other strategic sites; d) developing management models that mainstream sustainable natural resource management following criteria such as those of UNESCO´s Man and Biosphere Program. Moreover, the assistance will be provided to discussions and agreements to focus the provincial policy toward integrated management of water resources as a basic tool for strategic development and land use planning.

Output 2.2 Provincial Governance Framework for participatory ELUP & sector consensus building

- The project will promote participatory ELUP and sector consensus building through: a) inter-institutional dialogue spaces for multi-sectoral decision-making in the three pilot provinces, to contribute to and facilitate ELUP zoning and coordinate production changes with sectors in programs and policies at the eco-regional level; b) a sustainable commodities platform for beef in Buenos Aires; and a c) capacity building program to train and raise awareness on ELUP to increase participation and implementation, on the economic appraisal of economic goods and services (EG&S), and the consequences of land use management options in target sectors and ecosystems.

- Inter-institutional dialogue spaces for multi-sectoral decision-making in Buenos Aires, Jujuy and Mendoza: In recognition that multiple stakeholders are needed for ELUP, the project will support the three provinces to pilot mechanisms for inter-institutional stakeholder dialogue, coordination and for multi-sectoral decision-making to facilitate the ELUP process and ensure stakeholder participation and buy-in.  This will allow for horizontal coordination (between institutions of the same government level) and vertical (between national, provincial and municipal levels) in ELUP processes and facilitate implementation through enhanced coordination, joint planning and implementation of ELUP policies. Moreover, strengthened coordination between local communities, governments and sector stakeholders will improve efforts to generate broader participation in monitoring and surveillance and to support sustainable production.

- The project will take into account existing experiences. In Buenos Aires two experiences will be considered. One is the Inter-ministerial Commission for Urban and Territorial Land Use Planning (CIOUT). And the second one is an Inter-sectoral Roundtable for Land Use Planning of the Province of Buenos Aires, which was established in 2016 with a multi-sectoral composition and rules of procedure and was operational for one year until 2017. Mendoza has established a Provincial Council for Land Use Planning (CPOT), which has the potential to act as the space for dialogue and coordination.  In addition, the experience acquired in designing an Environmental and Territorial Council in the Malargüe River target landscape, which includes local and multi-sectoral stakeholders will be taken into account.  Jujuy does not have a provincial level space but there are several local experiences in multi-sectoral coordination such as the Qhapac Ñam Management Unit or local committees in the Quebrada de Humahuaca.

- In PY1 the project will assess these experiences and undertake stakeholder mapping to identify key stakeholders to be involved in the dialogue and coordination spaces in each province. These will be led by the OPDS in Buenos Aires, SAOT in Mendoza and Ministry of Environment in Jujuy and will have the objective of providing long-term spaces where the different sectors and institutions can align, take ownership and develop joint concrete actions for mainstreaming BD conservation and SLM and ELUP in key sectors; generating proposals for inter-sectoral and inter-jurisdictional coordination to prepare and implement ELUP related plans, programs and projects; sectoral planning and mainstreaming provincial ELUP in federal programs; as well as multi-sectoral decision making to facilitate ELUP implementation; sharing information, lessons and experiences; and optimizing the impact of the different interventions.

- Design will include convening meetings and agreeing on structure and functioning of the spaces (e.g., terms of reference, rules of procedure, protocol for meetings, record keeping, decision making and coordination mechanisms), as well as promoting agreements between the key stakeholders involved to establish dialogue and coordination, and ensuring adequate representation of women and indigenous peoples (the latter In Jujuy and Mendoza).  Participants will include national public institutions, technical and scientific organizations, private sector, universities, CSOs and NGOs (the list of institutions identified during the PPG is included in Table 1 of Annex F- Stakeholder Engagement Plan).  These spaces will begin to operate in PY2 and throughout the project´s lifetime through – among others to be defined – plenary sessions, working groups, round tables, public audiences, dialogues and fora where the different instruments and approaches developed under the project´s outputs will be discussed with, standardized and agreed upon by the main sectors and key stakeholders. The project will undertake a financial sustainability study during the first year of their operation to identify funding sources to sustain the dialogue spaces.

- Sustainable commodities platform in Buenos Aires: The project will support OPDS in establishing a sustainable commodities platform for beef. This sectoral platform will constitute the mechanism to convene and coordinate the public and private sector stakeholders to promote sustainable production; to define potential approaches and policies for complying with ELUP in priority areas; and to reach agreement on possible instruments and minimal standards e.g. sowing methods, reduced agro-chemicals (fertilizers, insecticides, fungicides and herbicides). The project will seek to help the platform members develop a long-term space where the different sectors can align, take ownership and develop joint concrete actions to mitigate the negative impacts of commodity production and maximize productivity, hence strengthening the country's enabling environment for sustainable commodity production. The platforms will be based on the following principles: neutrality, empowerment and social inclusion, multi-stakeholder, strong facilitation, and conflict resolution.

- The establishment of the platform will build upon UNDP´s Green Commodities Program, providing lessons learned and guidelines to facilitate multi-stakeholder dialogue and providing the expertise and analysis to scale up action to other areas of the country. Coordination will be made with similar supply chain approaches to commodities supported through GEF funds in Brazil, Paraguay, Peru and Ecuador. A detailed stakeholder mapping will be undertaken in PY1 and PY2 and the identified institutions will be invited to participate in the platform. The participation of women representing their organizations will be encouraged.  Upon establishment of the platforms, the Project will support drafting of Codes of Conduct, which will be discussed and agreed upon by the platform members.  The Code of Conduct will define the rules of procedure for the platform, including objectives, protocol for meetings, record keeping, decision making and coordination mechanisms.

- The project will undertake studies that will provide inputs to the platform so that it may undertake the assessment processes leading to the development of action plans for sustainable beef. The studies may include among others, markets, commercialization processes and channels, stakeholders, relevant case studies, and methods for assessing and measuring the demand for sustainable products. Between PY3 and PY4 and based on the previous studies the platform will undertake a root cause analysis of the supply chain, identifying the root causes of the socio-environmental externalities, as well as preparation of an Action Plan for Sustainable Beef. The analyses will also include organizational aspects, links between producers and supply chains at local level, and inter-institutional coordination between national and provincial public and private institutions. It will identify the strategies and lines of work for sustainable beef, including assessing and verifying the legal mandates and competencies of institutional stakeholders, and assessing public sector budgets. The Action Plan will be validated through the plenary sessions and formally adopted.

- The project will also support the platform with a financial sustainability study to ensure the continuation of the actions initiated under the project. The platform will hold plenary meetings throughout the project´s lifetime where representatives of each of the beef value chains will be convened. All members will be invited. The plenary sessions will consist of presentations given by different working groups, stakeholders and institutions related to issues identified in the action plan and that have a direct relation to defining the model for responsible production and trade under the project.  These sessions will be an opportunity for stakeholders to voice opinions and reach consensus on key issues.

- In recognition that land use change faces market barriers beyond the specific sites of production, the project will support between PY5 and PY6 the promotion of sustainable products from Argentina at the international level through a marketing and outreach program that will help advertise a differentiated approach to production in vulnerable environmental areas. This will include fostering partnerships between producers and buyers of sustainable products; and participating in events such as interviews and business conferences with international buyers of sustainable products; national fairs and other events. Implementation of the Action Plan will be monitored and adjustments and improvements made.

- Capacity building: The capacity building program for ELUP at the provincial level will include different formats and contents. It will target staff from the environmental authorities of Buenos Aires, Jujuy and Mendoza, regional INTA offices, sectoral institutions, universities, and producers, NGOs and CSOs and communities of the target landscapes. The program will seek to: a) assess the training needs and demands of the different national level stakeholders and beneficiaries; b) define objectives, prioritize themes and develop materials; c) establish the methodologies for each type of capacity building activity proposed, identifying the tools to be used, which must include both theory and practice; and d) evaluate the capacity building activities and the program itself to determine changes in knowledge, understanding and skills for ELUP. Training will be supported by communication and information materials to raise awareness about ELUP and about the economic value of ecosystem goods and services. Please refer to Table 3 above for information on the  capacity building program.

Output 2.3. Set of instruments validated in pilot landscapes for defining and implementing ELUP

- The project will support ground level work to develop decision-making instruments to facilitate ELUP in the selected target landscapes of the pilot provinces. This will include instruments needed to define ELUP and the respective types of land use restriction for specific locations.  These will include methodologies to assess the valuation of ecosystem goods and services and scenario analysis in different ecoregions and land uses to provide decision makers with information on the implications of different courses of action affecting natural resources and global environmental values. It will also include an assessment of the influence on these sector practices on the ecosystem goods and services under alternative macroeconomic and climate change scenarios. Careful coordination will be made with ex-post evaluations in Component 3 and other projects. In addition to the economic valuation of ecosystem services and trade off scenarios, methodologies for evaluation of ecosystem functions will be undertaken to further determine priority areas for conservation based on ecosystem values and or vulnerability. Moreover, instruments related to land use restrictions will also be tested to implement ELUP, including  command and control instruments to deter incompliance with established land use zones, incentives for transitions to new production practices or new approaches, and instruments to compensate for opportunity costs for land owners that are required to reduce or change production in areas designated in ELUP for strict conservation of biodiversity or those where extreme measures are needed to reduce land degradation. Development of economic and financial instruments will include mainstreaming climate change considerations (e.g., incentives for practices that favor adaptation) in these instruments.

- Buenos Aires: Three approaches will be undertaken, namely: a) ES valuation; b) assessment of incentives for changing land uses in areas defined as priority in ELUP, and c) development of protocols for implementing ELUP.

- Valuation of ecosystem goods and services: Under Output 1.2 above the project will assess in detail the feasibility of two pre-selected ES evaluation methodologies, namely ECOSER and multi-criteria analysis with GIS. In each target landscape the project will support the application of the selected methodology to undertake a bio-physical evaluation which will be followed by an economic valuation as a basis to define policies and management instruments for ELUP that mainstream BD conservation and SLM. INTA will provide training to OPDS in approaches, methodologies and tools for ES valuation and their use in ELUP. The project will support OPDS in: a) identifying strategic ecosystems for their provision of ES (e.g.,wetlands, native forests, Valuable Grassland Areas (VGA)); areas of high ecological fragility due to their vulnerability to anthropogenic activity (e.g., soils prone to erosion); and areas of probable occurrence of physical hazards due to environmental degradation or human intervention (e.g., urban expansion over floodplains or water recharge areas, filling of wetlands, expansion of agriculture over grasslands); and b) generating together with INTA baseline information, systematizing the information and defining the methodology for economic valuation of ES.  The results will be validated with key stakeholders.

- The selected economic valuation methodology will be applied in each target landscape calculating the willingness-to-pay for the prioritized ES.  In the Parana Delta landscape the ES valuation will build on the Comprehensive Strategic Plan for Conservation and Sustainable Use of the Parana Delta (PIECAS), which has generated baseline information, stakeholder mapping and a strategic environmental evaluation. The results of the ES valuation will serve to strengthen the long-term implementation of the PIECAS.

- Economic, financial and fiscal incentives: Project assistance will address the agriculture and livestock, tourism, and peri-urban insfrastructure sectors working through the different levels of institutions and sectors to link environmental sustainability of production practices and location in ELUP zoning as criteria in different incentive programs currently supported by government. The project will assist OPDS beginning in PY2 and throughout the project´s lifetime in promoting in the three target landscapes access of landowners that have management plans, to payments under the compensation schemes for producers that apply SLM under the federal Native Forest Law Nº26331, Forest Plantation Investment Law Nº25080, and the Provincial Native Forest Law Nº 14 888.

- The project will assess national funding programs to develop specific financing lines to address land uses defined in the ELUP instruments to be developed by the project, and for promoting environmentally-friendly BD and SLM practices that are adapted to the province for testing in the target landscapes. These include the Seed Funds of the Ministry of Production (soft loans), ArgenINTA Foundation (soft loans) and the Ministry of Tourism (non-reimbursable funding); and banks, namely Bank of the Province of Buenos Aires (BAPRO)  Argentine National Bank (BNA) and Galicia Bank. The project will also support the assessment of other options such as tax exemptions and incentives.

- The results of the ES valuation above together with the assessment of compensation schemes in Output 1.3 will serve as the basis for designing PES schemes to be tested.  Potential PES schemes to be analyzed include: a) payments addressing conservation and sustainable use of wetlands within the framework of the Inventory of Wetlands of the Buenos Aires Province Project being implemented by OPDS to be applied in the Delta and Talares target landscapes and potentially to South-western Buenos Aires if soil preservation services are included; and b) payments for private protected areas and municipalities.  The assessment will also include reviewing the Provincial Emergency Law Nº10390, which provides grants to producers affected by natural disasters to analyze if this compensation scheme could be linked to the provision of environmental services.

- Protocols for implementing ELUP: The project will assist OPDS in developing ELUP protocols. This will include undertaking between scenario analyses through applying a prospective environmental analysis, and incorporating the criteria used for valuation of ecosystem goods and services as well as the results of the valuations; undertaking vulnerability assessments of ecosystems and comparing them with productive activities; and defining sustainability indicators. As the results of these activities are available the protocols to approach the vulnerability in the ecosystem-productive activity links will be elaborated.  The different economic and financial instruments will be incorporated in the protocols and linked to the productive activities.

- Mendoza. Valuation of ecosystem goods and services: The project will support the SAOT and INTA to undertake ES valuation as the basis to design compensation schemes for PES.  In North Oasis-Green Belt, INTA is piloting the ECOSER methodology in the locality of Guaymallen, which will serve to prioritize ES in this target landscape. The project will support systematizing the available information on ELUP in rural areas; identifying information gaps on ES; and agreeing on criteria for identifying and prioritizing functions and ES related to agricultural and livestock production as well as an agreed list of local ES in the target landscape. Information produced by INTA by preparing and monitoring LUP plans, and training stakeholders will be incorporated in the analyses.

- In the Uco Valley the project through INTA will support assessing how territorial transformations influence rural stakeholders as well as the value chains comprising the provincial agri-food system. This will serve to include ES valuation and generate criteria for soil management to be included in the EIAs of agricultural projects, as well as identifying which economic and/or financial instrument is more effective in the different links of the value chains. In the Piedmont Area of AMM the project will assess several initiatives that can provide background information for ES valuation in protected areas, namely: in Mendoza the Villavicencio Natural Reserve (private protected area with conservation compatible productive activities) and the law proposal to establish an ES fee to finance protected areas; in other provinces the Private Natural Reserves Network of Argentina; incentives targeting private protected areas; and the lessons learned in the GEF-UNDP-UNEP PES Project. Based on the results of the above assessments, a valuation methodology will be selected and applied.

- Economic, financial and fiscal instruments: Mendoza has prioritized making use of the provincial economic, financial and fiscal instruments while the national level instruments will be considered as complimentary. Project assistance will address the agriculture and livestock, tourism, and peri-urban infrastructure sectors working through the different levels of institutions and sectors to link environmental sustainability of production practices and location in ELUP zoning as criteria in different incentive programs currently supported by government.

- The project will assist in the implementation of the Provincial Land Use Plan through providing support to economic instruments foreseen in the plan. This will include designing and testing compensation schemes through PES addressing the conservation and protection of natural areas in public and private protected areas of all four target landscapes, including components addressing ecotourism and conservation of vegetation cover. This will entail applying economic valuation methodologies, designing the scheme and testing it in small scale pilot projects for validation and extracting lessons that can be replicated elsewhere in the province throughout the remainder of the project.

- Moreover, project support will enable the development of technical and legal terminology to forward the elaboration of regulations to implement other instruments contained in the land use plan, namely: property tax, capital gain and promotion. In addition, for property tax, econometric and geostatistical models will be used to value properties and implement mechanisms for real time updating of fiscal values to generate incentives (e.g., exemptions, discounts). For capital gain analyzing the implementation of the Commission for Analysis of Regulations is foreseen in the provincial plan to propose regulations to capture capital gains according to zoning at municipal level. In the case of promotion (group of economic tools, e.g., exemption, discounts, grants, loans with preferential conditions, training, to support municipal zoning and foster investment and efficiency of productive activities), baseline information will be generated within the framework of Municipal Land Use Plans to adjust these instruments to the characteristics of the territory.

- The project will support several additional approaches according to the characteristics of each target landscape. In the Piedmont AMM landscape the project will address: a) assessing funding options (e.g., from the Ministry of Tourism)  to develop specific financing lines to address land uses defined in the ELUP instruments to be developed by the project, and for promoting environmentally-friendly BD and SLM practices that are adapted to the province for testing in the target landscapes; b) developing the instruments foreseen under the Provincial Protected Areas Law Nº 6045 and more specifically targeting the Divisadero Largo Reserve located in the Piedmont AMM landscape and the Llancanelo Wetland located in the Llancanelo-Malargüe landscape and facilitating access to funding to strengthen those PAs; and c) exploring and establishing synergies between the SAOT and the University of Cuyo to implement research activities and projects in the Piedmont AMM target landscape addressing productive innovation.

- In the Green Belt landscape, the project will support developing regulations for ELUP restrictions in those cases where economic and/or financial instruments would not produce a substantial impact in terms of the restrictions.  In the Uco Valley landscape the project will support generating criteria for soil management to be included in EIA procedures for agricultural projects based on work undertaken by the INTA. In the Malargüe landscape the project will assess the implementation of the National Sheep and Wool Recovery Law Nº25422 and the Goat Value Chain Development Program (PRODECCA) to extract lessons that can be used to improve access to  funding by producers in the target landscape to finance the implementation of environmentally friendly and SLM practices and will promote improved access to funds during the remainder of the project.  For small and medium sized producers in the target landscapes the project will support channeling financing options with more favorable conditions for environmentally-friendly and SLM practices, particularly credit lines from Galicia Bank and Argentine National Bank.

- Jujuy.  Valuation of ecosystem goods and services: The project will support a Targeted Scenario Analysis (TSA) in Jujuy to provide a framework for facilitating ES valuation and analyzing the impacts of policies and looking at tradeoffs in specific landscapes and sectors under different production practices. Socio-economic valuation of ES will be emphasized here since most of the population in the target landscapes belongs to indigenous groups for whom ecosystem services are highly significant and therefore the valuation of cultural services provided by ecosystems is more important in these areas.  ES valuation will build upon a land use planning experience in the Santa Rita stream basin undertaken by INTA, INTA experience in the ECOSER methodology and land use scenarios developed by the GEF-UNEP-UNDP funded PES project to determine differential payments under the Native Forest Law.  Based on the previous results the project will support developing and testing compensation schemes based on PES.

- Economic, financial and fiscal incentives: The project will support the implementation of economic, financial and fiscal incentives addressing the agriculture and livestock, tourism and mining sectors, and in addition in the areas of forests and biodiversity, renewable energies and solid waste. The project will support partnering with national funds to develop specific funding lines adapted to the characteristics of the province and for testing in the target landscapes. For tourism it will explore two options. One will be funding from the Ministry of Tourism (Emprender Turismo, Fondetur and international cooperation funds). The second option will be improving the instruments included in the Provincial Law for Promotion of Tourism Development Nº 5428 (e.g., fiscal credits; deferral in fulfilment of fiscal obligations; favorable credit conditions; grants, scholarships and technical assistance; public-private partnerships; provincial support to facilitate tax exemptions, tax deferrals and discounts). This will include adjusting documents, procedures or regulations pertaining to the instruments to facilitate their implementation within the framework of ELUP initiatives.  Moreover, the project will assist in reviewing the results and impacts of the Provincial Fund for Tourism Promotion and Development and analyzing the options to improve its implementation.

- For forests and biodiversity the project will support several approaches. One will be analyzing within the framework of the Native Forest Law the effectiveness of the implementation of Land Use Plans and proposing improvements for implementing the plans and for landowner access to the compensations foreseen by the law, as well as analyzing the implementation of the National Forest Management Plan with Integrated Livestock and propose measures to promote silvo-pastoral production in the target landscapes. A second approach will be to assess the interventions of, and explore synergies with, the UNDP-GEF Sustainable Use of Biodiversity Project in the Yungas ecoregion to implement in the target landscapes, namely: a) lessons acquired by USUBI in the production of vicuña and vicuña wool, and conservation of the environmental, cultural and tourism values of BD associated with the harvesting of vicuña wool; b) branding of local products; and d) replicating experiences of adding value to textile handcrafts.  The third approach will entail evaluating the implementation of federal programs, assessing the existing instruments and adapting them to the local realities and needs and the characteristics of the target groups, namely Social Actors Demand Council Program (PROCODAS) (grants that can be directed to family agriculture), Inclusive Rural Development Program (PRODERI) (livestock production in high-level valleys), Rural Area Development Program (PRODEAR) (non-reimbursable funds for community projects) and PROLANA (best practices for llama wool harvesting) and propose measures to improve the implementation of these programs to address land uses defined in the ELUP instruments to be developed by the project, and for promoting environmentally-friendly BD and SLM practices. For renewable energies the project will support the analysis of instruments and incentives to access credit to promote renewable energies, such as the Galicia Bank credit lines to finance renewable energy projects (e.g., solar energy and biomass) and green bonds.

- For the mining sector the project will provide technical assistance the development of coordination mechanisms for public-private partnerships to contribute to the sustainable productive development of communities living in the area of influence of the mining operations.

Output 2.4 SLM and biodiversity-friendly production practices validated for different ELUP land use zones

- This output will serve the purpose of validating and assessing the production and environmental viability of management practices with the potential to reduce threats and optimize the flows of ecosystem goods and services in the target landscapes identified as a priority for BD conservation and reduction of LD. These will provide costs and efficiency data to guide the definition of production practice restrictions in priority areas and feed into the regulatory framework being defined in Output 2.1. These demonstrations will take into account the results of ecosystem valuations and economic evaluations and the potential implications of changes in macroeconomic and climatic conditions developed under Output 2.3.  The economic and financial instruments assessed and developed in Output 2.3 will provide incentives for transitions to new production practices or new approaches, and/or compensation for the opportunity costs for landowners that are required to reduce or change production in accordance with ELUP criteria and zoning.

- Table 4 below summarizes the sustainable and environmentally friendly practices that were pre-selected during the PPG based on existing experiences and the needs expressed by the three provinces. During project implementation, these practices will be further assessed and costed to ensure their technical and economic feasibility. The assessment will also take into account the vulnerabilities and impacts of climate change identified for the different regions of Argentina so that the analysis will consider their potential to comply with the adaptation needs of each region. Based on the results of this assessment they will be prioritized for testing and validation in the target landscapes of the province. During project implementation other practices may be identified and included for assessment and testing. Implementation of the proposed practices will include defining the specific methodologies to be used in each province and target landscape to disseminate practices, promote their adoption and upscaling according to the local realities and target groups. Methodologies will emphasize “learning-by-doing” approaches and may include: training workshops; field visits; exchange of experiences between producers/communities within a target landscape or within target landscapes in the same province with similar problems; demonstration units; and farmer field schools that include in-farm theoretical and practical participatory training; and learning and listening to traditional knowledge.

- Training and technical assistance will take into account the work schedules of producers and their families, and communities, for minimum interference with the daily chores of men and women in order to ensure their participation in the activities organized by the project. Specific training will be developed targeting women beneficiaries (indigenous and non-indigenous) in the target landscapes to: i) promote gender equality in the management, use and conservation of biodiversity; and ii) ensure that both women and men´s needs are addressed through the project interventions. Practices will be implemented beginning in PY3 and throughout the project´s lifetime. Experiences and lessons will be extracted periodically during implementation and will provide feedback to other project outputs for adjustment and improvement of regulations and/or instruments under development.

Table 4 – Summary of sustainable and environmentally friendly practices in target landscapes

| Province | Target Landscape | Sector | Stakeholders involved/ Beneficiaries | BD friendly and SLM practices |
| --- | --- | --- | --- | --- |
| BUENOS AIRES | Talares del Este – Bahia de Samborombon | Agriculture and Livestock | Horticultural farmers | - Agro-ecological practices: organic fertilizers; substitution of agro-chemicals with bio-preparations and/or products with low or no environmental impact, use of biogas and/or compost, crop rotation, inter-cropping, green fertilizers |
|  |  |  | Livestock producers | - Seasonal monitoring of the status of natural grasslands in livestock ranches, considering management practices and planning, species in different environments (Magdalena, Punta Indio, Chascomus area) - Preliminary studies and silvo-pastoral management practices (Coastal areas) - Implementation of a commercial scale demonstration module for validation of sustainable management practices for natural grasslands (Chascomus area) - Monitoring of a site for recovery of natural grasslands following agricultural use through grazing management (Chascomus) - Monitoring of physical-chemical evolution of soil and condition of natural grasslands following management differentiated by environments (Punta Indio area) - Evaluation of optimum grazing height in lowland grassland communities for maximum secondary production and conservation of grassland biodiversity (Chascomus) |
|  | SOBA | Agriculture and Livestock | Farmers (mainly wheat producers) | - Conservation agriculture: rotation with green fertilizers, zero-tilling, cover crops |
|  |  |  | Livestock producers | - Ecosystem restoration in large ranches by improving grazing methods through sub-division of paddocks and locating water supply in strategic places for a homogeneous distribution of grazing pressure to increase BD. - Subsoiling to reduce soil compaction in grassland areas turned to agricultural use allowing cultivation of pastures and regeneration of species with forage value. - Cultivation of adapted perennial pastures to improve livestock efficiency - Recovery of natural grasslands turned to agricultural use through: a) managing recovery periods to stimulate germination of seeds in soils and establishing in-situ seed banks, b) inter-cropping with forage legumes (e.g., Vicia villosa) to recover degraded soils. - Management of herd stocks, including adjusting carrying capacity of paddock according to forage availability and paddock rotations to avoid overgrazing and under-grazing. |
|  | Parana River Delta | Urban expansion Agriculture and Livestock | Communities and inhabitants of the Delta | - Demarcation and characterization of wetland units - Define zoning of priority wetlands and coastal habitats to strengthen sustainable uses and practices within the PIECAS. - Restrictions to urban expansion and traditional tourism - Practices include: silvo-pastoral systems; livestock production in islands with natural grassland management, forestation with water management; bee-keeping; artisanal fisheries; game management; fruits especially pecan nuts; rural tourism; protected areas; birdwatching; forest tree and ornamental nurseries |
| JUJUY | Hornocal-Valle Grande | Tourism | Tourism operators Family producers Indigenous communities | - Tourism Environmental Information System for the San Franciso-Hornocal corridor, which will include an ELUP module for decision making - Tourism Development Plan including sustainable tourism activities in Qhapac Ñam and Jordan River Hot Springs, - Dissemination of information on regional festivities and products (e.g., handcrafts) - Dialogue spaces with stakeholders of the San Francisco-Hornocal corridor |
|  |  | Agriculture and Livestock | Family producers Indigenous communities | - Best livestock practices (cattle, sheep, camelids): e.g. silvo-pastoral schemes, tree barriers, trees/grasses for dune fixation/restoration of degraded areas; grazing management (length of grazing and recovery periods) - Agro-ecological practices: e.g. organic fertilizers, compost, bio-preparations to reduce agro-chemicals, crop rotation, cover crops; planting of trees/grasses for dune fixation/restoration of degraded areas; rainwater harvesting), tree barriers - Promotion of non-timber forest products e.g., beekeeping - Management Plan for Queñoa (Polylepis spp) and Churcal (shrubby forest with predominance of churqui (Prosopis ferox): (e.g., use of fuelwood saving stoves) - Management Plan for wildlife (e.g., management of predator/livestock relations) |
|  |  | Urban expansion | Municipalities | - Solid waste management - Risk studies to identify vulnerabilities and threats of urban expansion in Valle Grande |
|  | Susques-Jama-Catua-Olaroz | Tourism | Tourism operators Indigenous and non-indigenous communities | - Design of tourist corridor Susques-Catua - Design a tourist promotion strategy for Olaroz salt flats, Cauchari solar park and Olaroz Reserve - Promotion of Renewable energy through visits to Cauchari solar park - Management plan for Olaroz-Cauchari-Catua Flora and Fauna Reserve |
|  |  | Livestock | Indigenous and non-indigenous communities | - Best livestock practices (camelids): e.g. silvo-pastoral schemes, tree barriers, trees/grasses for dune fixation/restoration of degraded areas; grazing management (length of grazing and recovery periods) |
|  |  | Urban expansion | Municipalities | - Solid waste management |
|  |  | Mining | Indigenous and non-indigenous communities Mining companies | - Public-private partnerships to contribute to the sustainable productive development of communities living in the area of influence of mining operations (evaluate experiences and lessons of initiatives to support communities, e.g., participatory monitoring, promotion of renewable energies, BD conservation that may be replicated within the target landscapes. |
| MENDOZA | Piedmont AMM | Tourism/Protected areas | Protected area managers | - Best practice manual for ecotourism in protected areas: evaluate carrying capacity, trail design, incorporating locals as guides. |
|  |  | Agriculture and Livestock Urban expansion | Producers | - Improved grazing practices e.g., adjusting carrying capacity, paddock rotation, managing length of grazing and recovery periods to reduce overgrazing and under-grazing - Restoration of degraded non-irrigated areas |
|  | Northern Oasis- Green Belt | Agriculture and Livestock Urban expansion | Large scale producers | - Horticultural community parks with agro-ecological practices: e.g. organic fertilizers; substitution of agro-chemicals with bio-preparations and/or products with low or no environmental impact, use of biogas and/or compost, crop rotation, management of plastic wastes (from greenhouses) - Livestock parks (demonstration plots) with improved grazing practices e.g., adjusting carrying capacity, paddock rotation, managing length of grazing and recovery periods to reduce overgrazing and under-grazing - Management of water and drains in the areas of water table outcrops for recovery of wetlands and optimizing productive uses - Recovery of wetlands and awareness raising on their value - Systems to reuse water for production in areas with restrictions |
|  | Uco Valley | Agriculture and Livestock Urban expansion | Producers | - Soil conservation and management in piedmont transition areas between oasis and dryland - BD connectivity from agroecosystem to landscape levels |
|  | Malargüe | Agriculture and Livestock | Producers Communities (including indigenous communities) | - Reconversion of traditional migratory goat production for ecosystem conservation through sustainable intensification models: infrastructure to manage herds (e.g., corrals, paddocks); cultivation of irrigated pasture areas to reduce herd stocks in higher areas; grazing management; herd management to increase productivity - Establish guidelines for sustainable use of wetlands: adjust herd stock density - Afforestation and reforestation with communities in buffer areas of alluvial fan hazard |

Outcome 3: Replicability framework for ELUP uptake in all Argentine provinces

Output 3.1 Nationwide ELUP experiences and related instruments evaluated as an input to determine the best mix of instruments for different productive sectors and ecoregions

- To optimize the development of the ELUP process and increase the uptake across the country this output will support a broader analysis of experiences throughout the country. The project will support the SGAyDS in defining an optimal mix of instruments to implement land use zoning and related requirements for sector production. This will include ex-ante and ex-post assessments of projects and programs in non-pilot provinces that have applied ELUP and related instruments or innovative instruments for addressing the various causes of environmental degradation. In PY1 and PY2 the project will work with the SGAyDS in assessing projects and programs.

- The assessment will take into account relevant projects that have been recently completed or are nearing completion including "Restoration and Control of Factors leading to Deterioration of Native Forests in National Parks 2010-2013"; “Incentives for the Conservation of Globally Important Ecosystem Services, 2010-2018; “Sustainable Forest Management in the Trans-border Ecosystem of the Gran Chaco Americano, 2010-2015”, “Support to the Implementation of the National Programme on Native Forest Protection, 2012-2017; “Conservation of Native Forests at landscape level and social and environmental inter-relationships in the San Luis centre-area hills 2015; “Rural Corridors and Biodiversity” and “Native Forests and the Community” that started up in 2015; "Increasing Climate Resilience and Improving Sustainable Land Management in Buenos Aires Province, 2011-2016; Land Assessment in Dryland Areas – LADA- Project.  The assessment will also review financial flows for BD and for SLM and how these can be increased to support ELUP as well as the knowledge generated by these initiatives in regards to climate change. The findings will be evaluated and systematized according to efficiencies and outcomes, lessons learnt for eco-regional, social and typology-based land use/land use systems. They will be used as inputs to federal level regulations (Output 1.2), to the capacity building program (Output 3.2) and to the methodological guides for ELUP (Output 3.3).

Output 3.2. Nationwide ELUP Capacity Strengthening Program for all Provincial Authorities

- The project will undertake a twofold approach to strengthen the capacities of provincial institutions (intra and inter-provincial) to carry out ELUP.  The first approach envisages a capacity building program for non-pilot provinces. It will comprise different formats and contents, including: a) presenting and discussing ELUP processes, biodiversity conservation and ecosystem criteria, policies, strategies, methodologies, instruments and practices in different ecosystems; and b) exchange of lessons learned to make ELUP operational in the different pilot provinces and ecoregions, according to their ecosystem characteristics, problems, drivers, barriers, typology of social actors involved, and typology of land use and occupation. The availability of methodologies, proven in different ecoregions, on the application of economic and financial instruments to evaluate ecosystem services and their consideration in ELUP will entail a significant step forward for decision-making in various sectors and government levels.

- The capacity building program will be implemented between PY3 and PY6 and will target staff from the environmental authorities of non-pilot provinces, regional INTA offices, sectoral institutions, universities, NGOs and CSOs. Different provinces will take the protagonist roles leading sessions and imparting know-how according to their strengths. The program will seek to: a) assess the training needs and demands of the different national level stakeholders and beneficiaries; b) define objectives, prioritize themes and develop materials; c) establish the methodologies for each type of capacity building activity proposed, identifying the tools to be used, which must include both theory and practice; and d) evaluation of the capacity building activities and the program itself to determine changes in knowledge, understanding and skills for ELUP. Training will be supported by communication and information materials to raise awareness about ELUP and about the economic value of ecosystem goods and services. The project will promote dialogue with institutions (e.g., universities) to encourage the incorporation of ELUP into their academic and/or training programs and develop scholarship or research programs related to ELUP. The experiences and lessons learned by the project will strengthen and enrich these study programs. Table 6 below summarizes the preliminary design of the capacity building program.

Table 5 – Main aspects of the capacity building program (non-pilot provinces)

| Type of Activity | Subjects | Available Resources | Participants |
| --- | --- | --- | --- |
| Capacity building workshops Face-to-face modality 8-16 hour workshops Objective: Presentation and discussion and mainstreaming of ELUP and fundamental concepts | ELUP: a) Conceptual and legal framework; b) Public management aspects; c) Experiences at national, regional and international levels; d) Ecosystem goods and services; e) Environmentally- friendly productive practices; f) BD; g) Land uses; h) Economic, fiscal, social instruments for ELUP; i) Climate change (expected impacts and mitigation/adaptation) | SGAyDS Universities NGOs (e.g., Environment and Natural Resources Foundation) | Authorities and technical staff of provinces Technical and scientific organizations NGOS and CSOs involved in productive activities |
| Capacity building workshops Face-to-face modality 8 hour workshops Objective: Raise awareness and provide tools for stakeholder participation and gender mainstreaming | Participation: a) Inter-sectoral and inter-institutional coordination; b) project dialogue spaces; c) legal framework for participation and Indigenous Peoples; d) project´s social safeguards; e) participation and consultation schemes; f) promotion of participation of women and consideration of gender issues in the design and implementation of interventions | Indigenous Peoples and Gender specialists | Authorities and technical staff of provinces Technical and scientific organizations NGOS and CSOs involved in productive activities |

- The second approach to capacity-building will include developing methodological guides for upscaling ELUP to the different ecoregions and for implementing ELUP in shared ecosystems at national, provincial and local levels.  The project will provide technical assistance to the SGAyDS to elaborate the guides drawing on the experiences and lessons extracted under Outputs 2.4 and 3.1 above.

- In PY3 and PY4 two guides will be developed: a) Methodological Guide for implementing ELUP in pilot provinces, and b) Methodological Guide for implementing ELUP in non-pilot provinces.  These guides will be discussed and reviewed in the multi-stakeholder dialogue spaces to obtain inputs and suggestions.  In parallel, the non-pilot provinces will be selected for validating and upscaling ELUP experiences and lessons, based on progress made in ELUP, pressures, expected impacts, operational capacity and risks among other criteria, and agreements will be signed with these provinces. To define the number of provinces one of two criteria could be used: one province per geographical region (Center, Cuyo, Northeast, Northwest and South) or one province per ecoregion (Pampas, Delta and Islands of the Parana River, Espinal, Puna, Yungas Forest, High Monte, Low Monte, High Andes,  Dry Chaco and Patagonian Steppe). This will be defined during project implementation.  Between PY5 and PY6 the guides will be piloted in the selected provinces. A third guide will be developed in PY5 and PY6, namely a Methodological Guide for upscaling of ELUP in ecoregions and shared ecosystems.

Output 3.3. System to Evaluate and Monitor ELUP implementation nationwide established

- The project will support the establishment of a System to Evaluate and Monitor ELUP Implementation in Argentina (SEM-OAT). The SEM-OAT will be a system to analyze the process of mainstreaming policies, regulations and instruments in support of public planning and management of the territory under an ELUP approach. It will monitor progress in the implementation of ELUP, evaluate the impacts and degree of acceptance by stakeholders, propose measures and recommendations to decision makers and promote awareness raising within the general public.

- Detailed design and establishment of the SEM-OAT will be undertaken during project implementation based on discussions with stakeholders of the provinces. The SEM-OAT will be a system to enable the analysis of the process of mainstreaming regulatory policies and practices to support public planning and management of the territory under an ELUP approach. Once the system is operational, it will initially monitor progress in the target landscapes, followed by the non-pilot provinces toward the end of the project and in the long-term the whole country. A protocol and financial plan will be developed to ensure sustainability of the SEM-OAT.  The National Directorate of Planning and Environmental Land Use Planning of the SGAyDS will be the focal point to develop and implement the system with the information fed by the provinces.

Outcome 4: Dissemination of lessons learned, monitoring & evaluation

Output 4.1: Project M&E system operational and generating periodic reports

- The Project Technical Team (PT) (see section VIII below on governance and management arrangements for detailed information) will be responsible for implementing the project´s M&E plan, including the project´s inception workshop, annual planning workshops, monitoring of activities, outputs and outcomes, monitoring of the risk matrix and identifying potential risks and mitigation measures to reduce those unexpected risks (see section VII for further details). The Project Coordinator will provide inputs to the UNDP-CO for the preparation of the annual Project Implementation Reports (PIR). These reports will also include gathering of information on the GEF core indicator data and the UNDP Capacity Scorecard at mid-term and end of project.

- Project M&E will collect sex-disaggregated and multi-cultural data related to governance and regulatory frameworks, participation, access to economic and financial incentives, and sustainable production among others.  As part of the project M&E, the nature, extent and effectiveness of gender mainstreaming actions will be assessed periodically.

Output 4.2: Knowledge management system set up to disseminate good practices and lessons learned

- Dissemination will be undertaken through the project´s communication and information strategy. The strategy will have the following objectives: a) raising awareness on ELUP, inform project progress and results of project M&E, among others; b) managing technical information regarding ELUP and processing it to develop communication products to provide key stakeholders information that is reliable, clear and accessible; and c) systematizing project information, results and lessons to disseminate the knowledge generated and provide input for learnings and adjustments in the M&E process.  Through it the project will guarantee: a) timely dissemination of information on social and environmental implications before decisions are taken; b) easy access to information related to the project by project stakeholders and the public; and c) appropriate formats and languages adapted to the different target audiences (e.g., authorities, technicians, academia, communities).

- A number of communications products will be developed and disseminated throughout the life of the project in printed and electronic formats as well as on-line (mailing lists, SGAyDS and other partners´ websites, radio and television, and social media). These will include: a) Information materials on the project approach and proposals, in order to generate interest in collaboration, as well as to prepare target audiences to receive and take on board subsequent messages and results; b) briefing documents for policy makers, in order to stimulate discussion and serve as inputs for policy influence; c) communication materials aimed at communicating project results to decision makers, institutional stakeholders and project managers beyond the project area, in order to contribute to up-scaling; d) awareness raising and communication materials related to gender issues and the project’s approach and impacts in relation to gender equality; e) communication materials aimed at local and regional stakeholders to encourage their engagement in raising awareness regarding the project´s objectives.

- The project will prepare and disseminate reports systematizing project experiences, best practices and lessons learned. These reports will tackle different themes such as: economic and financial instruments for ELUP; environmentally friendly and sustainable practices in the target landscapes; ELUP implementation in pilot provinces; gender mainstreaming; multi-stakeholder dialogue spaces and participation and particularly women’s participation; and ELUP methodological guidelines at national and provincial levels. Publications will include information on the methodologies applied, the difficulties encountered, as well as success stories and their contribution to the project’s objectives.

- These reports will also be disseminated to a broader range of stakeholders through communication channels such as websites, information networks, fora and publications, among others, to support the implementation of similar projects in the region. COFEMA, CONADIBIO, COFEPLAN and COFELMA will also serve as conduits for dissemination of best practices and for management, dialogue and consensus building at the federal level to implement ELUP. In addition, the project will participate, as relevant and appropriate, in networks sponsored by UNDP/GEF, organized by expert staff who work in projects that share common characteristics.

Partnerships:

- The ELUP project will coordinate with several ongoing projects financed by GEF as well as national programs and projects. A set of specific mechanisms will be used for such coordination: a) annual coordination and planning meetings; b) technical meetings for sector-specific matters; c) meetings and activities to exchange lessons learned and good practices, with the authorities and technical and other sectors. The role of SGAyDS as a national executing agency will facilitate coordination, supplementation and synergies with other initiatives and will also help to tap lessons learned. Implementation through UNDP will also make coordination easier, and its experience in implementing other sustainable development projects together with SGAyDS in Argentina will be key to programming activities and fulfilling objectives.

- GEF-UNDP Full Sized Project 5734 “Sustainable Business Models for Biogas Production from Organic Municipal Solid Waste” which seeks to introduce biogas technologies for energy generation as part of the national program for integrated municipal solid waste management.  Production of biogas may be an eligible option in several localities of the target landscapes of the three provinces.

- GEF-UNDP Full Sized Project 5044 “Sustainable Land Use Management in the Drylands of North-west Argentina” with the objective of building a sustainable land management framework to alleviate land degradation, maintain ecosystem services and improve rural livelihoods.  This project includes developing integrated management plans and tools and methodologies in the ecoregions of Jujuy and Mendoza that are shared with the ELUP project.

- GEF-FAO Full Sized Project 4768 “Strengthening the Governance for Protection of Biodiversity through the Formulation and Implementation of the National Strategy on Invasive Alien Species” seeking the effective protection of biodiversity against the impact of invasive alien species, which may provide experiences to strengthen BD protection in the ELUP project in target landscapes where there are problems with invasive alien species.

- GEF-FAO Enabling Activity 5897 “Alignment of the National Action Programs of Argentina with the UNCCD Ten-Year Strategy” which seeks to control desertification through practices which can be coordinated with the ELUP project in target landscapes.

- The project will also coordinate and establish synergies with SGAyDS programs and projects, such as the “National Plan for Restoration of Native Forests”, the “Zero Extinction Action Plan”, and the Adaptation Fund Project “Increasing climate resilience and improving sustainable land management in the South-west of the Province of Buenos Aires.  Likewise, it will coordinate with several INTA projects that may provide inputs for developing ELUP instruments and designing best practices in the target landscapes. At national level, these include the projects “Territorial Information Systems for decision making at national and local level”; “Land use planning of the rural territory”; “Observatories of rural sustainability” and in Mendoza and Jujuy the projects “Territorial dynamic in land use and cover in the Argentine Republic” and “Technical support and training in rural land use processes”.  The project will also coordinate with the pilot site implemented by the ONDTyD in Jujuy where LD indicators are being measured and the methodology for evaluating lands and best management practices is being implemented.

- The project will place special emphasis on assessing lessons learned from relevant projects that are recently completed or nearing completion. The list of identified projects has been included in Output 3.1 above.  During project implementation other projects may be identified and will be included for assessment.

Risks and Assumptions:

- As per standard UNDP requirements, the Project Coordinator will monitor risks on a quarterly basis and report on the status of risks to the UNDP Country Office. The UNDP Country Office will record progress in the UNDP ATLAS risk log. Risks will be reported as critical when the impact and probability are high (i.e., when impact is rated as 5, and when impact is rated as 4 and probability is rated at 3 or higher). Management responses to critical risks will also be reported to the GEF in the annual Project Implementation Report (PIR). The detailed UNDP Risk Log is included in Annex H.

- As per the social and environmental risk screening exercise conducted at PPG stage the project risk has been categorized as moderate.  Annex E includes the project´s Social and Environmental Screening Procedure detailing the identified risks and management measures.

- Management responses to critical risks as well as the environmental and social grievances will be reported to the GEF in the annual Project Implementation Report (PIR).

Stakeholder engagement plan:

- During the PPG phase, key stakeholders participated in project planning and design workshops and focus group meetings.  These participative fora included: a) PPG inception workshop; b) provincial level workshops with local authorities, staff of the regional INTA offices and other social stakeholders in Buenos Aires, Jujuy and Mendoza; c) individual meetings and consultations with key national and local institutions, UNDP Argentina and SGAyDS authorities; and d) meetings with national level CSOs to gather information. Based on these consultations and assessments a Stakeholder Engagement Plan was developed and is included in Annex F.

- At national level the SGAyDS is the main institutional stakeholder as well as the COFEMA as the space for national level coordination.  Moreover, the project will interact with other key ministries, national secretariats and institutions, being of greater relevance the National Agricultural Technology Institute (INTA), National Parks Administration (APN), National Indigenous Peoples Institute (INAI), University of Buenos Aires (UBA) and CSOs such as the Environment and Natural Resources Foundation (FARN) and the Wildlife Foundation (FVS). The different coordination spaces such as CONADIBIO, National Council for Technical and Scientific Research (CONICET), ONDTyD and the National Biodiversity Observatory (OBIO) will be taken into account in developing multi-stakeholder dialogue and coordination spaces.

- Key provincial government stakeholders are in Mendoza the Secretariat for Environment and Land Use Planning (SAOT), through its Land Use Planning Provincial Agency (APOT); in Buenos Aires the Provincial Agency for Sustainable Development (OPDS) through its Provincial Directorate of Natural Resources and Environmental Land Use Planning; and the Sub-secretariat for Environment Planning and Sustainable Development through its Provincial Directorate for Sustainable Development and Climate Change; in Jujuy the Ministry of Environment through the Environmental Land Use Planning Directorate and the Biodiversity Secretariat. The INTA regional offices – INTA Salta-Jujuy, INTA Mendoza-San Juan and INTA Buenos Aires North and South - will also participate in project implementation.  Coordination will be undertaken with other government stakeholders, institutions, universities and CSOs such as the Irrigation Directorate of Mendoza, In Jujuy the Indigenous Peoples Secretariat, Urban Solid Waste Management System, Tourism Secretariat and Production Ministry, and in Buenos Aires with the Revenue Agency and the Water Authority.

- Key stakeholders at target landscape level will be the local communities and organizations. Each target landscape has its own characteristics and a number of stakeholders have been identified. In Mendoza these include the Municipalities of Malargüe, Mendoza, San Carlos, Las Heras, Tunuyán, Tupungato, Luján de Cuyo and Godoy Cruz; the Malalweche Mapuche Organization of Malargüe, the Livestock Advisory Council and the Agricultural Advisory Council of Malargüe, the Association of Bolivian Producers, Guaymallen Concentration Market, wine producers of the Argentine Wine Corporation and/or Bodegas Argentinas. In Jujuy, they include 36 indigenous communities in the Departments of Susques, Humahuaca and Valle Grande, the Qhapac Ñac Management Unit, the Quebrada de Humahuaca Management Unit, Jujuy Salt Company and CSOs such as Proyungas or CEBIO Foundation, the tourist operators in Humahuaca, San Francisco, Valle Grande, Santa Ana and Valle Colorado. In Buenos Aires, the Municipalities of Campana, San Fernando, Magdalena, Punta Indio, Chascomús, Lezama, Castelli, Villarino and Carmen de Patagones; the Risk Management and Emergency Directorate and CSOs such as Fundacion Humedales and the Argentine Flower Cooperative.

- The successful implementation of the project will largely depend on effective communication and coordination with the multiple project stakeholders, capacity building and the implementation of mechanisms to ensure these stakeholders’ participation.  These include: a) communication and capacity building; b) dialogue mechanisms; and c) conflict prevention and management.  The stakeholder engagement plan includes the stakeholder mapping and describes the above stakeholders in more detail including their role in project implementation and participation in the project components; as well as the mechanisms to foster participation, which have been included in the project intervention strategy.

- The Jujuy and Mendoza target landscapes involve indigenous communities. The project will respect the ethno-cultural characteristics of the indigenous communities to be involved (Omaguaca, Kolla, Atacama in Jujuy and Mapuche in Mendoza) in the design of interventions. The project will work with the existing organizational structures and decision making processes of each group and will take advantage of the dialogue and work spaces already developed between provincial governments and communities. Representatives of indigenous communities/organizations will be invited to participate in project planning, implementation and monitoring and evaluation.  Participatory dialogue and coordination will be established with communities to report, motivate, engage and to receive feedback in regards to project planning and implementation. All actions with indigenous peoples will be guided by the respect to their rights to: a) participation in the design, implementation and evaluation of public policies, plans and programs; b) Prior Consultation before adopting administrative or regulatory measures that may affect them; and c) Free, Prior and Informed Consent in cases where their fundamental rights may be affected or their integrity may be put at risk.  During the first year of project implementation the project will develop a detailed Indigenous Peoples Plan (a draft plan is included in Annex F), which will be the basis for the project and provincial authorities to undertake prior consultations and FPIC processes (as per ILO 169) to obtain consent in those cases where potential activities are identified as framed in the cases pointed out by the international framework and UNDP guidelines (e.g extraction of natural resources such as felling or mining or agricultural developments in their lands or territories; a decision that could affect the status or rights of people to their lands/territories, resources or livelihoods; access to traditional knowledge, innovations and practices; commercial use of natural and/or cultural resources in lands subject to traditional ownership or under traditional use by Indigenous Peoples; decisions in regards to benefit sharing when such benefits derive from their lands, territories or resources). At target landscape level the action lines outlined in the previous section above will be defined in detail during project implementation. For this the project will apply prior consultations at all times and FPIC will be ensured on any matters that may affect the rights and interests, lands, resources and territories.

- The stakeholder engagement plan and the Social and Environmental Screening Template (Annex E) include more detailed information.

Gender equality and empowering women:

- The project mainstreams gender and multi-cultural issues throughout its entire cycle, based on the premise that besides ensuring participation of women (and their organizations) in the spaces generated by the project, it will contribute to their effective empowerment as social actors. The project recognizes the ethno-cultural characteristics of the relevant groups (e.g., Omaguaca, Kolla, Atacama and Mapuche indigenous peoples) such as the role of the family in production and income generation and the socio-economic differences between men and women.

- The project has developed a strategy that links the most important gaps identified in relation to its outcomes, the proposed interventions, and the country´s policies and commitments toward gender equality. The gaps identified in the analysis and which are considered in the strategy include: a) lack of parity in decision-making spaces; b) better conditions in terms of incomes and livelihoods for men over women; c) differences in use of time; and access to, and control of resources that favor men.

- The main strategies considered are:

- Gender balance will be taken into account in engaging the project team, the Project Board and multi-sectoral, multi-stakeholder dialogue spaces. The recruitment processes that will be undertaken as part of the project will aim at ensuring workforce diversity, including in terms of gender. This will be achieved through a variety of measures, including ensuring that ToRs target men and women as potential candidates (“He/She”) equally, provisions that women are encouraged to apply, and requesting basic understanding, skills, experience and commitment required to work in a gender-sensitive and multicultural-sensitive manner. Where applicable, strong candidates will be assessed as part of written tests and/or behavioural interviews held as part of recruitment processes (e.g., through adding one or more gender-related and multicultural-based questions).  In the multi-stakeholder dialogue spaces, the project will work through political dialogue at the federal level to ensure the participation of women in these spaces and other project processes.

- Including gender and ethnicity disaggregated data collected from official sources in the development of policy, economic, financial and technical instruments and governance mechanisms for ELUP. All data reviewed and prepared for entry to the system of policy, economic, financial and technical instruments and governance mechanisms for ELUP will be looked at through a gender and inter-cultural lens, and reference gender and ethnicity if and where needed (i.e., who owns, controls, uses land areas in question, how will planned measures affect women and men both indigenous and non-indigenous, etc.). If no official sources are available, a specific survey will be conducted including specific questions that reveal relevant gender and multicultural dimensions (e.g.,  gender dimensions in the use of BD and ecosystem resources management; economic impact of land degradation on women/men, both indigenous and non-indigenous).

- Development of a capacity building program aimed at public officials and/or technical teams to raise awareness on the importance of engaging both women and men in decision-making processes and addressing gender issues. Gender and intercultural approaches will be integrated into capacity-building initiatives through distinct gender sessions, workshop or training sessions aimed at public officials and/or technical teams (e.g., pointing out the gender division of labor or use of time in the prioritized areas by presenting data disaggregated by sex). It is also key to ensure that both women and men have access to capacity-building initiatives, and that obstacles, which usually prevent women from benefitting from these activities, are addressed (e.g., in places and at times where women have the chance to participate). It is also important to identify suitable female participants and invite these women, and explain the benefits of enhancing women and men’s capacities equally, including for target communities as a whole, to authorities/decision-makers.

- Gender mainstreaming in the promotion of dialogue mechanisms, making the most of existing spaces and structures for consultation, deliberation, decision-making and inter-institutional coordination at the national, provincial and pilot levels, by fostering equal participation of women and men and indigenous populations in agenda-setting, decision-making and/or policy-making processes. This will include undertaking consultations with women and men from target sites as well as with institutions (e.g., INAM and INAI at the national level and the gender and ethnicity agencies in each of the provinces levels). When designing the contents, methodologies and approaches, the project will ensure that women and men’s knowledge and interests are considered and that women are included in decision-making processes (e.g., through highlighting the benefits of their involvement and ensuring consultations and dialogue spaces are held at a time and place where both women and men can participate).

- Development of a capacity building program aimed at women beneficiaries (indigenous and non-indigenous) in the three prioritized areas and target landscapes. The project will coordinate with the National Institute of Women (INAM), the Federal Council of Women and the INAI and with the three provincial gender mechanisms and indigenous affairs bureaus (Buenos Aires: the Provincial Council of Women under the Secretariat for Gender and Sexual Diversity of the Secretariat for Human Rights of the Province of Buenos Aires and the Provincial Council for Indigenous Affairs; Mendoza: the Directorate of Women, Gender and Diversity under the Ministry of Social Development and Human Rights and in Jujuy, the Gender Parity Secretariat under the Ministry of Human Development and the Secretariat of Indigenous Peoples. The project will enhance collaboration with civil society organizations with support of each of the above entities in the three prioritized areas to ensure women and men are equally included in capacity building programs. The project will ensure consultation of women and men working in agriculture and identify female-headed households to facilitate their engagement in project activities (i.e., ensure that participation is possible given their particularly tight schedules). Additionally, the project will collaborate with stakeholders working on gender equality, women’s empowerment and other relevant actors in the tourism sector (e.g. Ministry of Tourism, women working in the tourism sector and those interested to get engaged) to find out about suitable business opportunities.

- Enhance knowledge management and dissemination by systematizing, assessing, replicating and/or scaling up lessons learned, case studies, and promising and/or best practices on gender mainstreaming in BD/SLM and ELUP and on women’s participation in dialogue platforms and/or mechanisms in the three prioritized areas. The documentation and dissemination of results will consider gender and the multicultural approach, too. To achieve this, knowledge products prepared under the project will reflect on gender and ethnicity to the extent possible, for instance through the presentation of data disaggregated by sex and ethnicity and the inclusion of sections that analyze the respective gender and ethnic dimensions. Gender and ethnicity will also be considered in the dissemination of research results, knowledge and information. For instance, when circulating knowledge products, the project will ensure the inclusion of various stakeholders that work on gender equality, women’s empowerment and ethnicity, both from civil society and public entities and both at the national level and in the three prioritized areas and pilot sites.

- Annex G includes the Gender Analysis and Action Plan. Gender mainstreaming has also been assessed in the Social and Environmental Screening (see Annex E).

Sustainability and Scaling Up:

- The sustainability of the project is linked to the creation of policy and regulatory frameworks that mainstream ELUP process and instruments into key sectors and financial programs/ mechanisms that underpin these.  Project design builds on a robust baseline of existing policies, regulations, instruments and initiatives, thus ensuring institutional ownership and sustainability of results. Instruments will be developed that use incentives and innovative approaches such as those targeted at generating economic and financial options to include the value of ecosystem services in negotiation and planning processes. In addition to the preparation of a policy framework, a legal and institutional proposal for ELUP sustainability will also be developed and agreed upon.

- The optimization of inter-institutional and inter-sectoral coordination, strengthened dialogue, improved policy and regulatory instruments, and better coordination in the implementation of the different government programs and projects will help the project partners and especially the participating government institutions to overcome the predominant culture of short term planning, sector-based solutions and the influence of political interests in prioritizing interventions, and develop a discipline of coordinating and collaborating under a common approach – ELUP - thus ensuring sustainability of project results. The information system for analysis of environmental variables and the system for evaluation and monitoring of ELUP implementation will support sustainability of ELUP processes by defining and measuring indicators and continuous updating and uploading of information in the long term.

- Capacity development will enable project partners to improve their capacities for planning, implementation, enforcing and monitoring of ELUP through training tailored to the specific stakeholder needs and demands. The project will improve productive sectors´ know how for BD conservation and SLM management by testing and validating approaches, training and outreach. This will increase the awareness of producers, communities and other productive stakeholders on the value of ecosystem goods and services, and the risks that unsustainable production represent, thereby increasing uptake of sound environmental practices. Dialogue and the development of partnerships will be essential tools for building consensus, enabling coordinated planning and regulatory oversight and encouraging sustainable forms of investment.

- In the target landscapes, project interventions will take into account gender equality seeking to empower women through participation in decision-making spaces; better access to, and control of resources, and improving their incomes and livelihoods. Furthermore, interventions addressing indigenous communities will follow and respect their organizational ways and cultural patterns; will ensure that stakeholders show respect for their dignity and human rights and will be carried out with a multi-cultural approach, respecting their collective and individual rights protected by international and national regulations and including safeguards to ensure actions do not negatively affect the livelihoods of indigenous communities. These approaches will help secure project ownership by these stakeholders and the sustainability of project results.

- All this will consolidate the past single ecosystem and sector approaches and ensure that the new development plans take into account the different ecosystems across the entire country and comply with land use guidance that promotes conservation and sustainable use of critical habitats and the ecosystem goods and services they provide to society. This will ensure not only the sustainability of project results but the continued  provision of those services to production, avoiding foreclosure of future development options and also providing global environmental benefits at scale.

- Scaling up: The potential for scaling up is high given the complementarity with federal and provincial policies, programs and plans.  Mainstreaming of ELUP in planning, regulations and economic and financial instruments will contribute to upscaling.  Moreover, a federal minimum standards regulation for ELUP will be developed that will provide the framework for all of the country´s provinces to regulate ELUP.  The multi-stakeholder dialogue spaces will be replicable to other regions of the country. The Buenos Aires sustainable beef platform will be replicable for the same commodity in other provinces or for other commodities. These stakeholder dialogue spaces will constitute a space where the project results will be internalized by different stakeholders, thereby contributing to the replication of project actions.

- The project will intervene in target landscapes of three pilot provinces, which have their own characteristics but at the same time reflect the problems of biodiversity loss and land degradation as a whole; therefore, the experiences and lessons learned in each area will be replicable to the rest of the pilot provinces and the other provinces of Argentina. Actions such as field days, exchange of experiences, technical visits and workshops will maximize the exposure of producers to the most successful and innovative aspects of the project and will also facilitate the extension of project benefits.

- A framework for replicability within Argentina is already built into the project through Component 3, comprising the assessment of lessons learned from past programs and projects; an evaluation and monitoring system to disseminate ELUP information, experiences and lessons nationwide; methodological guides for replicating ELUP; and a capacity building program.

- Finally, the project´s communication and information strategy will enable sharing the experiences and lessons to facilitate upscaling of project results through communication channels such as websites, information networks, fora and publications among others. In addition, the good practices and lessons will be disseminated to a broad range of stakeholders to support the implementation of similar projects in the region. COFEMA, CONADIBIO, COFEPLAN and COFELMA will also serve as conduits for the replication of best practices and for management, dialogue and consensus building at the federal level to implement ELUP.

# Project Management

Cost efficiency and effectiveness:

- Project interventions will collectively attend the barriers to addressing the identified problems through development of policies, regulations, instruments and participatory strategies that improve inter-institutional and inter-sectorial coordination; strengthening opportunities for dialogue and consensus; capacity building of national and provincial stakeholders, access to economic and financial instruments for environmentally friendly and sustainable production conservation and restoration for the long-term protection of global and local values ​​in Argentina´s ecoregions. Project design includes several strategies to maximize cost-effectiveness:

- The project will capitalize on a robust baseline which will be improved through mainstreaming ELUP. GEF funds will be used primarily for interventions addressing the policy and regulatory frameworks, institutional capacity building, targeted technical assistance, for training and for dissemination of information.

- Inter-institutional coordination and cooperation as well as operational frameworks will provide for a more effective and efficient use of resources of the institutions as well as increased long-term funding to sustain project results. Effective coordination with other programs, projects and initiatives will serve to reinforce synergies, avoid duplication of efforts and reduce overall costs. Regular coordination meetings with projects and programs will serve to identify complementarity and joint planning and implementation of activities in the field will contribute to cost-effectiveness.

- The project will develop and strengthen partnerships with multiple entities at national and provincial levels, in the public and private sectors and in civil society, taking advantage of their existing capacities and social and institutional structures.

- Economic and financial instruments for ELUP will be developed to reward and facilitate environmentally sustainable forms of production allowing costs and benefits to be internalized by those who experience them.

- Stakeholder participation at all project levels will contribute to the cost-effectiveness of the project. The  project governance bodies (Project Board, Technical Committee, Provincial Committees) as well as the multi-stakeholder dialogue spaces will ensure adequate planning and implementation of activities in line with the project objectives, national and provincial objectives and priorities, as well as complementarity with ongoing and planned programs and projects. Coordination mechanisms will be closely linked, ensuring in this manner that stakeholder concerns are up-streamed into higher project management levels and likewise project management decisions are down-streamed to keep stakeholders duly informed.

- Promotion of socioeconomically and environmentally sustainable production systems will help to maintain and improve the biodiversity value of the landscape as a whole and to reduce productive and extractive pressures affecting ecosystems, thereby reducing the need for measures based on control and punishment and associated costs. In addition, based on experience acquired mainly by INTA in promoting best production practices as well as technical and scientific data the project will assess and prioritize the environmentally friendly and sustainable practices that have the highest potential to allow producers to maintain and increase their production levels and yields with a low level of use of external technologies. This, coupled with a strategy of accessing economic and financial instruments, will allow producers to reduce production costs, obtain better prices and improve family incomes.

- Systematization of project experiences and lessons learned will contribute to cost-effective upscaling and replication of project results.

- Project management:  The Project Management Unit will be located within the premises of the SGAyDS which will provide office facilities. The SGAyDS will also provide administrative suppport staff, ELUP specialists and a Communication Specialist. The project will intervene in three provinces and target landscapes within the three provinces.  The environmental authorities of the three provinces (OPDS, Environment and Land Use Planning Secretariat of Mendoza and Ministry of Environment of Jujuy) will designate project Focal Points and provide backstopping and support to the project team when they are present in their territories by providing and/or coordinating with other institutions office space, infrastructure for training and dialogue spaces.

- Agreement on intellectual property rights and use of logo on the project’s deliverables and disclosure of information:  To accord proper acknowledgement to the GEF for providing grant funding, the GEF logo will appear together with the UNDP logo on all promotional materials, other written materials like publications developed by the project, and project hardware. Any citation on publications regarding projects funded by the GEF will also accord proper acknowledgement to the GEF. Information will be disclosed in accordance with relevant policies, notably the UNDP Disclosure Policy and the GEF policy on public involvement.

# Project Results Framework

| This project will contribute to the following Sustainable Development Goal (s): 15: Protect, restore and promote sustainable use of terrestrial ecosystems, sustainably manage forests, combat desertification, and halt and reverse land degradation, and halt biodiversity loss |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| This project will contribute to the following country outcome included in the UNDAF/Country Programme Document: UNDAF Outcome 4: By 2020, the country will have reinforced the sustainable management of natural resources and implemented adaptation and mitigation policies with respect to climate change and man-made damage, using a gender and intercultural approach. CPD Output 4.1: Land use strategies promoted for the sustainable management of natural resources and ecosystems |  |  |  |  |  |
| This project will be linked to the following output of the UNDP Strategic Plan: Output 1.4.1: Solutions scaled up for sustainable management of natural resources, including sustainable commodities and green and inclusive value chains |  |  |  |  |  |
|  | Objective and Outcome Indicators | Baseline | Mid-term Target | End of Project Target | Data Collection Methods and Risks/Assumptions |
| Project Objective: Generate multiple biodiversity and land degradation benefits by developing a system of policy, economic, financial and technical instruments and governance mechanisms for environmental land use planning (ELUP) to mainstream socioeconomic and environmental evaluation of ecosystem goods and services (ES&G) in decision making at different government levels and sectors | UNDP Mandatory indicator 1: Natural resources that are managed under a sustainable use, conservation, access and benefit-sharing regime, measured through: a) Number of hectares where ELUP has been agreed upon and implemented in priority landscapes covering approx.10% of target ecoregions in 3 pilot provinces through applying instruments to enforce modified production i.e., EIA of sector development initiatives include mitigation measures to reduce pressures, sector specific and development programs include production practices restrictions, protocols/regulations to maximize effectiveness in combatting sector-related threats b) Number of additional hectares covering the total surface of global ecoregions in 3 pilot provinces in which upscaling is expected due to project dissemination activities and co-financed interventions | 0 |  | a) Total: 5,079,260 Buenos Aires: 3,059,070 - Espinal: 300,610 - Pampas: 2,726,370 - Delta/Flooded Savannas: 32,090 Jujuy: 532,600 - High Andes: 115,790 - High Monte: 14,870 - Yungas: 80,970 - Dry Chaco: 50,500 - Puna: 270,470 Mendoza: 1,487,590 - High Monte: 37,050 - Low Monte: 837,190 - Patagonian Steppe: 305,900 - High Andes: 307,450 b) Total: 507,926 (additional hectares) Buenos Aires: 305,907 - Espinal: 30,061 - Pampas: 272,637 - Delta/Flooded Savannas: 3,209 Jujuy: 53,260 - High Andes: 11,579 - High Monte: 1,487 - Yungas: 8,097 - Dry Chaco: 5,050 - Puna: 27,047 Mendoza: 148,759 - High Monte: 3,705 - Low Monte: 83,719 - Patagonian Steppe: 30,590 - High Andes: 30,745 | Periodic project monitoring Field assessments/Remote sensing |
|  |  |  |  |  | Risks: No short term implementation of land use changes agreed upon in the initial ELUP Difficulties to keep ELUP in place including the sustainable use of ecosystems due to international commodity prices that favor expansion of production Delays in ELUP implementation as a result of political changes at different levels (national, provincial and municipal) Modification of land use suitability due to climate change Assumptions: Political will and commitment of target sector institutions to plan, implement and enforce ELUP processes Stakeholders from target sectors are receptive and willingly engage in ELUP processes and adopt BD and SLM friendly and sustainable practices |
|  | UNDP Mandatory indicator 2/GEF Core Indicator 11: Number of direct project beneficiaries (by gender and ethnicity) that improve their livelihoods through environmentally friendly natural resources management and sustainable production | 0 | 3,400 (40% are women; 10% belong to indigenous groups) | 11,665 At least 40% are women; 10% belong to indigenous groups (based on average % of female and indigenous population in 3 target landscapes as per the 2017 Permanent Household Survey). Breakdown is: Buenos Aires: 2,750 (0% indigenous peoples) Mendoza: 7,000 (2% indigenous peoples) Jujuy: 1,905 (70% indigenous peoples) | Periodic project monitoring Household surveys, focus groups disaggregated by gender and ethnicity |
|  |  |  |  |  | Risks: Beneficiaries are reluctant to participate in project activities and adopt the proposed practices because they do not perceive the advantages or disagree with restricted land uses that may come with ELUP. Assumptions: Beneficiaries are receptive and perceive the benefits of environmental sustainability to their livelihoods in the long term |
|  | Indicator 3: Degree of improvement in BD conservation and LD reduction in three target landscapes as a result of ELUP implementation, measured through increases in Net Primary Productivity (NPP); % of land cover; and soil organic carbon content (trends in hectares) | Baseline and specific targets for NPP, % land cover and soil organic content tbd in PY1 | Mid-term targets tbd in PY1 | Total surface area where measurements to be taken: Buenos Aires: 461,700 - Pampa: 275,000 - Espinal: 180,400 - Flooded Savanna: 6,300 Jujuy: 119,328 - Puna: 61,877 - High Andes: 22,392 - Yungas: 14,403 - High Monte: 20,656 Mendoza: 160,470 - High Monte: 6,319 - Low Monte: 82,584 - Patagonian Steppe: 39,424 - High Andes: 32,143 Targets tbd at project outset | Periodic project monitoring Field/remote sensing assessments Methodology by MAyDS and the National Observatory for Land Degradation and Desertification (PRAIS Report 2018) Land Degradation Neutrality Framework Interaction with the National Observatory for Land Degradation and Desertification |
|  |  |  |  |  | Risks: Insufficient political prioritization of interventions and weak institutional capacities reduce the effectiveness of ELUP and best practices promoted by the project. Assumptions: NPP is maintained and/or improved through adoption and upscaling of SLM and BD-friendly practices. Land cover and soil organic carbon are maintained and/or improved through adoption and upscaling of SLM practices. |
| Outcome 1 Federal enabling framework and strategies to reinforce ELUP, and underpin implementation in priority ecosystems and habitats to reduce pressure from key production sectors. (target sectors: agriculture & livestock; mining and peri-urban infrastructure, tourism) | Indicator 4: Capacity to plan and implement ELUP & ES valuation in development plans and sector financing to reduce threats to BD & LD in priority areas, measured by: a) 20% increase in Adapted UNDP Capacity Scorecard ratings of SGAyDS and other sectoral institutions b) Percentage of sector financing instruments that mainstream ELUP and new production guidelines and/or improved access to instruments | a) 46.6% (maximum score 100% on Adapted UNDP Capacity scorecard) for SGAyDS Other sectoral institutions will be selected in PY1. b) 12 economic instruments related to LD, BD and sustainable development: i) Native Forest Law Fund, ii) Forest Plantations Fund, iii) Sheep Recovery Fund, iv) Inclusive Rural Development Program, v) Rural Area Development Program, vi) Technology Fund, vii) Social Actors Demand Council Program, viii) Seed Fund, ix) Tourism Program, x) Sustainable Territorial Innovation, xi) Galicia Bank credit line, xii) Provincial Agricultural Services Program. 7 instruments partially include ELUP criteria or aspects related to ELUP. | a) 50% (maximum score 100% on Adapted UNDP Capacity scorecard) b) Inter-sectoral coordination established and agreed for mainstreaming of ELUP criteria | a) 56% (maximum score 100% on Adapted UNDP Capacity scorecard) for SGAyDS 20% increase for the sectoral institutions selected in PY1 b) At least 50% have mainstreamed ELUP in their funding eligibility criteria (Forest Plantations Fund; Sheep Recovery Fund; Goat Production Fund; Galicia Bank; others tbd) | Periodic project monitoring Interviews with key staff and authorities Capacity Scorecard applied at mid-term and end of project Review of economic instruments and confirmation of inclusion of ELUP |
|  |  |  |  |  | Risks: Lack of political will and weak institutional management / lack of interest of financial institutions reduce ELUP efficiency Assumptions: Government/private sector institutions recognize the need to improve institutional processes, collaboration and cooperation, are receptive and supportive of ELUP processes |
|  | Indicator 5: Number and type of national level land-use policy, planning, strategy and regulatory instruments that mainstream ELUP. | Regulations partially including ELUP: Environment General Law Nº25 675, Native Forest Law Nº26 331, Glacier Law Nº 26 639, National Parks Law Nº 22 351; Wildlife Conservation Law Nº 22 421; Law Nº 24 375 ratifying the Convention on Biological Diversity; Law Nº 23 919 ratifying the RAMSAR Convention; Law Nº 24 701 ratifying the United Nations Convention to Combat Desertification; Environmental Management of Water Law Nº 25 688; and Law Nº 27 037 National System of Marine Protected Areas | Sector coordination and dialogue established through the dialogue spaces (see Indicator 7 below). Preliminary criteria agreed. | 1 Federal minimum standards regulation for ELUP developed. | Periodic project monitoring Federal ELUP minimum standards regulation proposal Interviews with key staff and authorities Institutional reports |
|  |  |  |  |  | Risks: Lack of political will and weak institutional management reduce ELUP efficiency Assumptions: Political will to adopt and enforce ELUP and approve regulatory instruments in target sectors Commitment of institutions to implement ELUP processes |
|  | Indicator 6: Number and type of new partnership mechanisms at federal level for dialogue to mainstream BD and ELUP in sectoral programming and finance decisions (including level of direct participation of women and indigenous peoples). | There are several federal level spaces that deal with different subjects e.g. COFEMA, CONADIBIO, ONDTyD but none specifically addressing ELUP | 1 inter-institutional and inter-sectoral dialogue space established (with at least 40% female membership and including indigenous peoples). | 1 inter-institutional and inter-sectoral dialogue space to mainstream BD and ELUP in sectoral programming and finance decisions functioning with work plans and budget (with at least 40% female membership and including indigenous peoples). | Periodic project monitoring Institutional reports Interviews with partnership members Platform reports |
|  |  |  |  |  | Risks: Lack of interest of target sectors in inter-sectoral coordination and engaging with other sectors Assumptions: There is political will to develop partnership mechanisms to mainstream BD and ELUP in association with different sectors and incorporating key stakeholders including civil society |
| Outcome 2 Application of ELUP procedures and instruments in pilot Provinces with targeted ecoregions and production sector land uses. | Indicator 7: Capacity to manage human-biodiversity interface in target provinces to produce BD and LD benefits and flow of ES, measured through: a) Adapted UNDP Capacity Scorecard ratings of pilot province environmental authorities: i) Buenos Aires Office for Sustainable Development (OPDS), ii) Ministry of Environment of Jujuy, iii) Environment Secretariat of Mendoza. b) Number and type of provincial level policy, planning and regulatory instruments for ELUP that include an approach to landscape sustainability, resilience and inclusiveness | a) OPDS: 48.8% Jujuy: 48.8% Mendoza: 80% (maximum score: 100% on Adapted UNDP Capacity Scorecard) b) 7 provincial instruments that partially incorporate ELUP criteria or aspects: i) Law Nº8051 Mendoza, ii) 3 provincial laws for native forest land zoning, iii) 3 provincial general environment laws | a) OPDS: 53% Jujuy: 53% Mendoza: 86% (maximum score: 100% on Adapted UNDP Capacity Scorecard) b) Sector coordination and dialogue established through the provincial multi-stakeholder platforms (see Indicator 9 below). | a) OPDS:59% Jujuy: 59% Mendoza: 96% (maximum score: 100% on Adapted UNDP Capacity Scorecard) b) At least 3 provincial laws strengthened with economic instruments, guidelines and/or regulations for ELUP. At least 5 new instruments developed and approved to implement ELUP at provincial/municipal level (i.e, methodological guides, ELUP protocols, planning guidelines) | Periodic project monitoring Interviews with key staff and authorities Capacity scorecards at mid-term and end of project |
|  |  |  |  |  | Risks: Lack of political will and weak institutional management reduce ELUP efficiency Assumptions: Commitment of pilot provinces institutions to mainstream, implement and monitor ELUP processes |
|  | Indicator 8: Number and type of new partnership mechanisms at provincial level for participatory ELUP and consensus building (including level of direct participation of women and indigenous peoples) | Mendoza has a Land Use Planning Provincial Council which will serve as dialogue space. Jujuy and Buenos Aires do not have participatory mechanisms for ELUP. | 1 multi-stakeholder space strengthened with new members (Mendoza) 2 multi-stakeholder spaces (Buenos Aires and Jujuy) and 1 sustainable commodities platform (Buenos Aires) designed and stakeholders identified | 3 provincial multi-stakeholder spaces functioning with work plans and budgets (at least 40% female membership and including indigenous peoples) 1 sustainable commodities platform (beef) established and functioning with action plans developed (Buenos Aires) | Periodic project monitoring; Institutional reports; Interviews with partnership members; minutes of meetings; sustainable beef action plan |
|  |  |  |  |  | Risks: Lack of interest of target sectors in inter-sectoral coordination and engaging with other sectors Assumptions: Political will to develop partnership mechanisms for participatory ELUP and consensus building in association with different sectors and incorporating key stakeholders including civil society |
|  | Indicator 9/GEF Core Indicator 4: Surface area (hectares) of landscapes under improved practices in the target landscapes excluding protected areas, measured through: a) Area of landscapes under improved management to benefit biodiversity, e.g., agro-ecological practices, management of grazing and recovery periods, (qualitative assessment, non-certified) (GEF Sub-indicator 4.1) b) Area of landscapes under sustainable land management in production systems, e.g., silvo-pastoral systems, tree barriers, zero tilling, crop rotation (GEF Sub-indicator 4.3) | 0 | Total: 183,938 ha a) 57,021 ha b) 126,917 ha | Total: 613,128 ha a) 240,644 ha - Buenos Aires 31% (116,631 ha) - Mendoza 46% (59,560 ha) - Jujuy 60% (64,453 ha) b) 372,484 - Buenos Aires 69% (259,598 ha) - Mendoza 54% (69,918 ha) - Jujuy 40% (42,968 ha) | Periodic project monitoring Institutional reports Field assessments Remote sensing |
|  |  |  |  |  | Risks: Target sectors stakeholders (private sector, producers, communities) are reluctant to adopt the proposed practices Economic activity such as farming, harvesting and grazing may be restricted in some areas and alternative practices could have an opportunity cost to small-scale producers and to indigenous people Assumptions: Target sectors stakeholders (private sector, producers, communities) are receptive to messages of environmental sustainability and increased productivity |
|  | Indicator 10/GEF Core Indicator 3: Area of land restored (hectares) in the targeted ecoregions/ landscapes, measured through: a) Area of degraded agricultural lands restored (GEF sub-indicator 3.1) b) Area of forest and forest land restored (GEF sub-indicator 3.2) | 0 | Total: 38,592 ha a) 29,441 ha b) 9,150 ha | Total: 128,370 ha a) 97,868 ha - Bs As: 85,471 ha - Mendoza: 12,397 ha - Jujuy 0 ha b) 30,502 ha - Bs As: 0 ha - Mendoza: 18,595 ha - Jujuy: 11,907 ha |  |
|  | Indicator 11: Level of improvement in livelihoods of beneficiaries in target landscapes differentiated by gender and ethnicity, measured through the Land Degradation Assessment in Drylands (LADA) Livelihood Index which measures 5 capitals: social, productive, human, physical and natural | Index baseline values to be determined in PY1 for each target landscape (Index ranges from 1 (low) to 5 (high). |  | 20% improvement in the Livelihood Index | Periodic project monitoring; LADA methodology; household surveys, focus groups disaggregated by gender and ethnicity |
|  |  |  |  |  | Risks: Beneficiaries are reluctant to engage in project interventions. Livelihoods could not be positively impacted quickly enough during the time period of the project. Assumptions: Beneficiaries are aware of the need to adopt sustainable and environmentally-friendly best practices and their advantages to help improve production, productivity and livelihoods, engage and adopt best practices |
| Outcome 3 Replicability framework for ELUP uptake in all Argentine provinces | Indicator 12: Increase in capacity of non-pilot provincial environmental authorities to adopt and implement ELUP criteria and SLM practices in remaining provinces and nationally important ecoregions, measured through the % of increase in the Adapted UNDP Capacity Scorecard ratings of environmental authorities | Non-pilot provincial environmental authorities to be identified and agreed in PY1/PY2 | Adapted UNDP Capacity scorecards applied. Baseline established. | 20% increase in Capacity scorecard ratings. | Periodic project monitoring Interviews with key staff Capacity scorecard |
|  |  |  |  |  | Risks: Lack of political will and weak institutional management in non-pilot provinces reduce the project´s potential for replicability. Argentina´s financial crisis will affect the amount of funding available for programs that support replication. Assumptions: Commitment of institutions to mainstream, implement and monitor ELUP processes |
|  | Indicator 13: Monitoring of ELUP used to adjust sectoral and financial programming guidance | 0 | System to evaluate and monitor ELUP implementation of ELUP in Argentina designed | System to evaluate and monitor implementation of ELUP in Argentina functioning in target landscapes and selected non-pilot provinces monitoring ELUP uptake | Proposal for system design Reports produced by the system User statistics |
|  |  |  |  |  | Assumptions: Commitment of institutions to mainstream, implement and monitor ELUP processes |
|  | Indicator 14: Level of improvement in knowledge, aptitudes and practices (KAP) in ELUP, ES, sustainable production and other key issues at national and provincial levels measured through surveys in Year 1 and Year 6 (including gender disaggregated data) as a result of capacity building programs on ELUP | KAP survey in PY1. Baseline and targets to be established. |  | KAP survey (target in terms of improved knowledge to be determined in PY1) | Periodic project monitoring KAP surveys |
|  |  |  |  |  | Assumptions: Institutions engage in ELUP capacity building and ELUP processes upscaling project lessons and experiences |
| Outcome 4 Dissemination of lessons learned and monitoring and evaluation | Indicator 15: Knowledge effectively managed in support of ELUP, measured through: a) Number and type of project knowledge products and publications on best practices and lessons learned (at least 1 on gender) disseminated b) Number of institutions at federal and provincial levels that receive project publications and communications products aimed at improving knowledge and practices on ELUP | 0 | a) 6 b) At least 50 | 15 (e.g. i) annual reports, newsletters; ii) lessons/case studies on: best BD/SLM practices, ELUP in provinces, gender mainstreaming, dialogue platforms and participation; iii) ELUP methodological guidelines at national and provincial levels) b) At least 70 (government, private sector, CSOs) | Periodic project monitoring Annual reports; newsletters, publications; interviews with stakeholders |
|  |  |  |  |  | Risks: Institutions not willing to share information and experiences Assumptions: Project partners are open about project challenges and successes, as well as lessons learned so these can be captured, published and disseminated at national and international level. |

# Monitoring and Evaluation (M&E) Plan

- The project results as outlined in the project results framework will be monitored annually and evaluated periodically during project implementation to ensure the project effectively achieves these results.

- Project-level monitoring and evaluation will be undertaken in compliance with UNDP requirements as outlined in the UNDP POPP and UNDP Evaluation Policy. The UNDP Country Office will work with the relevant project stakeholders to ensure UNDP M&E requirements are met in a timely fashion and to high quality standards. Additional mandatory GEF-specific M&E requirements (as outlined below) will be undertaken in accordance with the GEF M&E policy and other relevant GEF policies.

- In addition to these mandatory UNDP and GEF M&E requirements, other M&E activities deemed necessary to support project-level adaptive management will be agreed during the Project Inception Workshop and will be detailed in the Inception Report. This will include the exact role of project target groups and other stakeholders in project M&E activities including the GEF Operational Focal Point and national/regional institutes assigned to undertake project monitoring. The GEF Operational Focal Point will strive to ensure consistency in the approach taken to the GEF-specific M&E requirements (notably the core indicator data) across all GEF-financed projects in the country. This could be achieved for example by using one national institute to complete the GEF core indicator data for all GEF-financed projects in the country, including projects supported by other GEF Agencies.

M&E Oversight and monitoring responsibilities:

- Project Coordinator:  The Project Coordinator is responsible for day-to-day project management and regular monitoring of project results and risks, including social and environmental risks. The Project Coordinator will ensure that all project staff maintain a high level of transparency, responsibility and accountability in M&E and reporting of project results. The Project Coordinator will inform the Project Board, the UNDP Country Office and the UNDP-GEF RTA of any delays or difficulties as they arise during implementation so that appropriate support and corrective measures can be adopted.

- The Project Coordinator will develop annual work plans based on the multi-year work plan included in Annex, including annual output targets to support the efficient implementation of the project. The Project Coordinator will ensure that the standard UNDP and GEF M&E requirements are fulfilled to the highest quality. This includes, but is not limited to, ensuring the results framework indicators are monitored annually in time for evidence-based reporting in the GEF PIR, and that the monitoring of risks and the various plans/strategies developed to support project implementation (e.g. ESMP, gender action plan, stakeholder engagement plan etc..) occur on a regular basis.

- Project Board:  The Project Board will take corrective action as needed to ensure the project achieves the desired results. The Project Board will hold project reviews to assess the performance of the project and appraise the Annual Work Plan for the following year. In the project’s final year, the Project Board will hold an end-of-project review to capture lessons learned and discuss opportunities for scaling up and to highlight project results and lessons learned with relevant audiences. This final review meeting will also discuss the findings outlined in the project terminal evaluation report and the management response.

- Project Implementing Partner:  The Implementing Partner is responsible for providing all required information and data necessary for timely, comprehensive and evidence-based project reporting, including results and financial data, as necessary. The Implementing Partner will strive to ensure project-level M&E is undertaken by national institutes, and is aligned with national systems so that the data used and generated by the project support national systems.

- UNDP Country Office:  The UNDP Country Office will support the Project Coordinator as needed, including through annual supervision missions. The annual supervision missions will take place according to the schedule outlined in the annual work plan. Supervision mission reports will be circulated to the project team and Project Board within one month of the mission. The UNDP Country Office will initiate and organize key GEF M&E activities including the annual GEF PIR, the independent mid-term review and the independent terminal evaluation. The UNDP Country Office will also ensure that the standard UNDP and GEF M&E requirements are fulfilled to the highest quality.

- The UNDP Country Office is responsible for complying with all UNDP project-level M&E requirements as outlined in the UNDP POPP. This includes ensuring the UNDP Quality Assurance Assessment during implementation is undertaken annually; that annual targets at the output level are developed, and monitored and reported using UNDP corporate systems; the regular updating of the ATLAS risk log; and, the updating of the UNDP gender marker on an annual basis based on gender mainstreaming progress reported in the GEF PIR and the UNDP ROAR. Any quality concerns flagged during these M&E activities (e.g. annual GEF PIR quality assessment ratings) must be addressed by the UNDP Country Office and the Project Coordinator.

- The UNDP Country Office will retain all M&E records for this project for up to seven years after project financial closure to support ex-post evaluations undertaken by the UNDP Independent Evaluation Office (IEO) and/or the GEF Independent Evaluation Office (IEO).

- UNDP-GEF Unit:  Additional M&E and implementation quality assurance and troubleshooting support will be provided by the UNDP-GEF Regional Technical Advisor and the UNDP-GEF Directorate as needed.

- Audit: The project will be audited as per UNDP Financial Regulations and Rules and applicable audit policies on NIM implemented projects.

Additional GEF monitoring and reporting requirements:

- Inception Workshop and Report:  A project inception workshop will be held within two months after the project document has been signed by all relevant parties to, amongst others:

a) Re-orient project stakeholders to the project strategy and discuss any changes in the overall context that influence project strategy and implementation;

b) Discuss the roles and responsibilities of the project team, including reporting and communication lines and conflict resolution mechanisms;

c) Review the results framework and finalize the indicators, means of verification and monitoring plan;

d) Discuss reporting, monitoring and evaluation roles and responsibilities and finalize the M&E budget; identify national/regional institutes to be involved in project-level M&E; discuss the role of the GEF OFP in M&E;

e) Update and review responsibilities for monitoring the various project plans and strategies, including the risk log; SESP, Environmental and Social Management Plan and other safeguard requirements; project grievance mechanisms; the gender strategy; the knowledge management strategy, and other relevant strategies;

f) Review financial reporting procedures and mandatory requirements, and agree on the arrangements for the annual audit; and

g) Plan and schedule Project Board meetings and finalize the first year annual work plan.

- The Project Coordinator will prepare the inception report no later than one month after the inception workshop. The inception report will be cleared by the UNDP Country Office and the UNDP-GEF Regional Technical Adviser, and will be approved by the Project Board.

- GEF Project Implementation Report (PIR):  The Project Coordinator, the UNDP Country Office, and the UNDP-GEF Regional Technical Advisor will provide objective input to the annual GEF PIR covering the reporting period July (previous year) to June (current year) for each year of project implementation. The Project Coordinator will ensure that the indicators included in the project results framework are monitored annually in advance of the PIR submission deadline so that progress can be reported in the PIR. Any environmental and social risks and related management plans will be monitored regularly, and progress will be reported in the PIR.

- The PIR submitted to the GEF will be shared with the Project Board. The UNDP Country Office will coordinate the input of the GEF Operational Focal Point and other stakeholders to the PIR as appropriate. The quality rating of the previous year’s PIR will be used to inform the preparation of the subsequent PIR.

- Lessons learned and knowledge generation:  Results from the project will be disseminated within and beyond the project intervention area through existing information sharing networks and forums. The project will identify and participate, as relevant and appropriate, in scientific, policy-based and/or any other networks, which may be of benefit to the project. The project will identify, analyse and share lessons learned that might be beneficial to the design and implementation of similar projects and disseminate these lessons widely. There will be continuous information exchange between this project and other projects of similar focus in the same country, region and globally.

- GEF core indicator data:  The GEF core indicator data) will be used to monitor global environmental benefits:

- The baseline/CEO Endorsement core indicator data – submitted as an Annex to this project document – will be updated by the Project Coordinator/Team (not the evaluation consultants hired to undertake the MTR or the TE)  and shared with the mid-term review consultants and terminal evaluation consultants before the required review/evaluation missions take place. The updated core indicator data will be submitted to the GEF along with the completed Mid-term Review report and Terminal Evaluation report.

- Independent Mid-term Review (MTR):  An independent mid-term review process will begin after the third PIR has been submitted to the GEF, and the MTR report will be submitted to the GEF in the same year as the 4th PIR at the latest. The MTR findings and responses outlined in the management response will be incorporated as recommendations for enhanced implementation during the final half of the project’s duration. The terms of reference, the review process and the MTR report will follow the standard templates and guidance prepared by the UNDP IEO for GEF-financed projects available on the UNDP Evaluation Resource Center (ERC). As noted in this guidance, the evaluation will be ‘independent, impartial and rigorous’. The consultants that will be hired to undertake the assignment will be independent from organizations that were involved in designing, executing or advising on the project to be evaluated. The GEF Operational Focal Point and other stakeholders will be involved and consulted during the terminal evaluation process. Additional quality assurance support is available from the UNDP-GEF Directorate. The final MTR report will be available in English and will be cleared by the UNDP Country Office and the UNDP-GEF Regional Technical Advisor, and approved by the Project Board.

- Terminal Evaluation (TE):  An independent terminal evaluation (TE) will take place upon completion of all major project outputs and activities. The terminal evaluation process will begin three months before operational closure of the project allowing the evaluation mission to proceed while the project team is still in place, yet ensuring the project is close enough to completion for the evaluation team to reach conclusions on key aspects such as project sustainability. The Project Coordinator will remain on contract until the TE report and management response have been finalized. The terms of reference, the evaluation process and the final TE report will follow the standard templates and guidance prepared by the UNDP IEO for GEF-financed projects available on the UNDP Evaluation Resource Center. As noted in this guidance, the evaluation will be ‘independent, impartial and rigorous’. The consultants that will be hired to undertake the assignment will be independent from organizations that were involved in designing, executing or advising on the project to be evaluated. The GEF Operational Focal Point and other stakeholders will be involved and consulted during the terminal evaluation process. Additional quality assurance support is available from the UNDP-GEF Directorate. The final TE report will be cleared by the UNDP Country Office and the UNDP-GEF Regional Technical Adviser, and will be approved by the Project Board.  The TE report will be publicly available in English on the UNDP ERC.

- The UNDP Country Office will include the planned project terminal evaluation in the UNDP Country Office evaluation plan, and will upload the final terminal evaluation report in English and the corresponding management response to the UNDP Evaluation Resource Centre (ERC). Once uploaded to the ERC, the UNDP IEO will undertake a quality assessment and validate the findings and ratings in the TE report, and rate the quality of the TE report.  The UNDP IEO assessment report will be sent to the GEF IEO along with the project terminal evaluation report.

- Final Report: The project’s terminal PIR along with the terminal evaluation (TE) report and corresponding management response will serve as the final project report package. The final project report package shall be discussed with the Project Board during an end-of-project review meeting to discuss lesson learned and opportunities for scaling up.

Table 6 -Mandatory GEF M&E Requirements and M&E Budget:

| GEF M&E requirements | Primary responsibility | Indicative costs to be charged to the Project Budget (US$) |  | Time frame |
| --- | --- | --- | --- | --- |
|  |  | GEF grant | Co-financing |  |
| Inception Workshop | UNDP Country Office | USD 15,000 (national) USD 15,000 (provinces) | 90,000 | Within two months of project document signature |
| Inception Report | Project Coordinator | None | None | Within two weeks of inception workshop |
| Standard UNDP monitoring and reporting requirements as outlined in the UNDP POPP | UNDP Country Office | None | None | Quarterly, annually |
| Risk management | Project Coordinator Country Office | None | None | Quarterly, annually |
| Monitoring of indicators in project results framework | Project Coordinator External consultants | USD 14,014 time of Project Coordinator allocated to M&E USD 94,000 external consultants for field assessments and measurement of indicators Livelihood Index, BD/LD methodologies, other surveys | 106,051 | Annually before PIR Livelihood Index; BD/LD benefits; at project start-up and end; other surveys as needed |
| GEF Project Implementation Report (PIR) | Project Coordinator and UNDP Country Office and UNDP-GEF team | None | None | Annually |
| NIM Audit as per UNDP audit policies | UNDP Country Office | USD 30,000 (USD/yr 5,000) | 90,000 | Annually or other frequency as per UNDP Audit policies |
| Lessons learned and knowledge generation | Project Coordinator | USD 30,000 (USD/yr 5,000) annual workshops for planning and lessons learned | 90,000 | Annually |
| Monitoring of environmental and social risks, and corresponding management plans as relevant | Project Coordinator UNDP Country Office | USD 7,000 (time of Stakeholder Engagement Specialist dedicated to M&E( | 21,000 | On-going |
| Stakeholder Engagement Plan | Project Coordinator Stakeholder Engagement Specialist UNDP Country Office | USD 7,000 (time of Stakeholder Engagement Specialist dedicated to M&E) | 21,000 | On-going. |
| Gender Action Plan | Project Coordinator Gender Specialist UNDP Country Office UNDP GEF team | USD 18,000 (time of Gender Specialist dedicated to M&E) | 54,000 | On-going. |
| Addressing environmental and social grievances | Project Coordinator UNDP Country Office | None for time of Project Coordinator and UNDP CO |  | On-going |
| Project Board meetings | Project Board UNDP Country Office Project Coordinator | USD 6,000 (USD/yr 1,000) | 18,000 | At minimum annually |
| Supervision missions | UNDP Country Office | None | 5,000 | Annually |
| Oversight missions | UNDP-GEF team | None83 | 5,000 | Troubleshooting as needed |
| GEF Secretariat learning missions/site visits | UNDP Country Office and Project Coordinator and UNDP-GEF team | None | 5,000 | To be determined. |
| Updating of core indicator data at mid-term | Project Coordinator | USD 2,000 | 6,000 | Before mid-term review mission takes place. |
| Independent Mid-term Review (MTR) and management response | UNDP Country Office and Project team and UNDP-GEF team | USD 25,818 (int´l consultant) USD 6,000 (nat´l consultant) | 108,000 | Between 3nd and 4rd PIR. |
| Updating of core indicator data before Terminal Evaluation | Project Coordinator | USD 2,000 | 6,000 | Before terminal evaluation mission takes place |
| Independent Terminal Evaluation (TE) included in UNDP evaluation plan, and management response | UNDP Country Office and Project team and UNDP-GEF team | USD 28,818 (int´l consultant) USD 6,000 (nat´l consultant) | 54,000 | At least three months before operational closure |
| Translation of MTR and TE reports into English | UNDP Country Office | USD 10,000 | 30,000 | As required. GEF will only accept reports in English. |
| TOTAL indicative COST Excluding project team staff time, and UNDP staff and travel expenses |  | 316,650 | 709, 051 |  |

# Governance and Management Arrangements

- Roles and responsibilities of the project´s governance mechanism: The project will be implemented following UNDP’s national implementation modality, according to the Standard Basic Assistance Agreement signed on February 26, 1985 and approved by Law Nº23396 of October 10, 1986 between UNDP and the Government of Argentina, and the Country Programme.

- The Implementing Partner for this project is the Secretariat of Environment and Sustainable Development (SGAyDS).  The Implementing Partner is responsible for:

- Approving and signing the multiyear workplan;

- Approving and signing the combined delivery report at the end of the year; and,

- Signing the financial report or the funding authorization and certificate of expenditures.

- The SGAyDS is responsible and accountable for managing this project, including the monitoring and evaluation of project interventions, achieving project outcomes, and for the effective use of UNDP/GEF resources.  The SGAyDS will work in a coordinated manner with the provincial authorities, with other strategic partners in the project and with co-funding bodies. The SGAyDS will also carry out effective coordination between this and other projects involving ELUP and other related issues.

- The Secretariat of Environment and Land Use Planning of the Province of Mendoza, the Ministry of Environment of the Province of Jujuy and the Provincial Agency for Sustainable Development of the Province of Buenos Aires, will be Other Responsible Parties of the proposed project. To this end, the Implementing Partner will sign a letter of agreement with each provincial counterpart in order to undertake the necessary field activities to guarantee compliance with the objectives according to the counterpart presented for each province. These agreements will identify the activities through which field tasks will be implemented in each province, contributing consequently to the Project's Operational Plans and overall objective. Within the framework of the agreement letters, the project may allocate resources during the term of the project, which shall be subject to compliance with the activities and products indicated in each agreement, the amount of co-financing contributed by each province and under the implementing regulations defined by UNDP.

- The environmental authorities of each province as well as INTA will designate Focal Points who will be responsible for provincial level coordination for the effective implementation of the project within each jurisdiction.  The Focal Points will be the reference points for coordination among the different agencies and departments of the provincial governments and the local stakeholders, as well as with the Project Management Unit, project consultants and other project partners.  The responsibilities of the Focal Points as well as other commitments will be defined in the implementation agreements between the SGAyDS and the provinces, which will be developed and signed in PY1.

- As GEF implementing agency, UNDP is ultimately accountable and responsible for the delivery of results, subject also to their certification by SGAyDS, as Implementing Partner. UNDP shall provide project cycle management services as defined by the GEF Council (described in Section IV Part XII), that will include the following:

- Providing financial and audit services to the project

- Overseeing financial expenditures against project budgets,

- Ensuring that activities including procurement and financial services are carried out in strict compliance with UNDP/GEF procedures,

- Ensuring that the reporting to GEF is undertaken in line with the GEF requirements and procedures,

- Facilitate project learning, exchange and outreach within the GEF family,

- Contracting the project mid-term and final evaluations and triggering additional reviews and/or evaluations as necessary and in consultation with the project counterparts.

- The project organisation structure is as follows:

Figure 2 – Project Organization Structure

- Project Board:  The Project Board (also called Project Steering Committee) is responsible for making by consensus, management decisions when guidance is required by the Project Coordinator, including recommendations for UNDP/Implementing Partner approval of project plans and revisions, and addressing any project level grievances. In order to ensure UNDP’s ultimate accountability, Project Board decisions should be made in accordance with standards that shall ensure management for development results, best value money, fairness, integrity, transparency and effective international competition. In case a consensus cannot be reached within the Board, final decision shall rest with the UNDP Programme Manager.

- Specific responsibilities of the Project Board include:

- Provide overall guidance and direction to the project, ensuring it remains within any specified constraints;

- Address project issues as raised by the Project Coordinator;

- Provide guidance on new project risks, and agree on possible countermeasures and management actions to address specific risks;

- Agree on Project Coordinator’s tolerances as required;

- Review the project progress, and provide direction and recommendations to ensure that the agreed deliverables are produced satisfactorily according to plans;

- Appraise the annual project implementation report, including the quality assessment rating report; make recommendations for the workplan;

- Provide ad hoc direction and advice for exceptional situations when the Project Coordinator’s tolerances are exceeded; and

- Assess and decide to proceed on project changes through appropriate revisions.

- Draft Terms of Reference for the Project Board are included in Annex D.  These Terms of Reference will be reviewed and finalized in the Inception Workshop.

- The composition of the Project Board must include the following roles:

- Executive: The Executive is an individual who represents ownership of the project who will chair the Project Board. This role can be held by a representative from the Government Cooperating Agency or UNDP.  The Executive for this project will be: the Executive Secretary of the SGAyDS. The Executive is ultimately responsible for the project, supported by the Senior Beneficiary and Senior Supplier.  The Executive’s role is to ensure that the project is focused throughout its life cycle on achieving its objectives and delivering outputs that will contribute to higher level outcomes. The executive has to ensure that the project gives value for money, ensuring a cost-conscious approach to the project, balancing the demands of beneficiary and supplier.

- Specific Responsibilities: (as part of the above responsibilities for the Project Board)

- Ensure that there is a coherent project organization structure and logical set of plans;

- Set tolerances in the AWP and other plans as required for the Project Coordinator;

- Monitor and control the progress of the project at a strategic level;

- Ensure that risks are being tracked and mitigated as effectively as possible;

- Brief relevant stakeholders about project progress;

- Organize and chair Project Board meetings.

- Senior Supplier: The Senior Supplier is an individual or group representing the interests of the parties concerned which provide funding and/or technical expertise to the project (designing, developing, facilitating, procuring, implementing). The Senior Supplier’s primary function within the Board is to provide guidance regarding the technical feasibility of the project. The Senior Supplier role must have the authority to commit or acquire supplier resources required. If necessary, more than one person may be required for this role. Typically, the implementing partner, UNDP and/or donor(s) would be represented under this role. The Senior Supplier for this project is: the UNDP Resident Representative.

- Specific Responsibilities (as part of the above responsibilities for the Project Board)

- Make sure that progress towards the outputs remains consistent from the supplier perspective;

- Promote and maintain focus on the expected project output(s) from the point of view of supplier management;

- Ensure that the supplier resources required for the project are made available;

- Contribute supplier opinions on Project Board decisions on whether to implement recommendations on proposed changes;

- Arbitrate on, and ensure resolution of, any supplier priority or resource conflicts.

- Senior Beneficiary: The Senior Beneficiary is an individual or group of individuals representing the interests of those who will ultimately benefit from the project. The Senior Beneficiary’s primary function within the Board is to ensure the realization of project results from the perspective of project beneficiaries. The Senior Beneficiary role is held by a representative of the government or civil society. The Senior Beneficiaries are: Representatives of the provincial authorities of Buenos Aires, Jujuy and Mendoza, and INTA. The Senior Beneficiary is responsible for validating the needs and for monitoring that the solution will meet those needs within the constraints of the project. The Senior Beneficiary role monitors progress against targets and quality criteria. This role may require more than one person to cover all the beneficiary interests. For the sake of effectiveness, the role should not be split between too many people.

- Specific Responsibilities (as part of the above responsibilities for the Project Board)

- Prioritize and contribute beneficiaries’ opinions on Project Board decisions on whether to implement recommendations on proposed changes;

- Specify the Beneficiary’s needs in an accurate, complete and unambiguous manner;

- Monitor implementation of activities at all stages to ensure that they will meet the beneficiary’s needs and are progressing towards that target;

- Evaluate impact of potential changes from the beneficiary point of view;

- Frequently monitor risks to the beneficiaries.

- Project Management Unit: The Project Management Unit (PMU) will consist of a National Project Director, a Project Coordinator, an Administrative Assistant and an Accountant. In addition, technical and administrative staff of the SAyDS will also participate and provide support to the PMU. To obtain specific outputs, the incremental support of GEF will be used to hire specialized consultants for specific periods of time. Agreements will be established with national institutions or organizations and provincial organizations as well as other institutions as deemed necessary.

- Project National Director: The Project National Director (PD) will be the Secretary of Environment and Natural Resources Policy of the SGAyDS, who will be accountable to the SGAyDS and UNDP for the achievement of objectives and results in the assigned Project. The PD will be part of the Project Board and answer to it. The PD will be financed through national government funds (co-financing).

- Specific responsibilities include:

- Serve as a member of the Project Board.

- Supervise compliance with objectives, activities, results, and all fundamental aspects of project execution as specified in the project document.

- Supervise compliance of project implementation with SGAyDS policies, procedures and ensure consistency with national plans and strategies.

- Facilitate coordination with other organizations and institutions that will conduct related activities or same themes.

- Participate in project evaluation, testing, and monitoring missions.

- Coordinate with national governmental representatives on legal and financial aspects of project activities.

- Coordinate and supervise government staff inputs to project implementation.

- Coordinate, oversee and report on government cofinancing inputs to project implementation.

- Project Coordinator: The Project Coordinator will be funded by the project and will be locally recruited following UNDP procedure. The Project Coordinator has the authority to run the project on a day-to-day basis on behalf of the Project Board within the constraints laid down by the Board. The Project Coordinator is responsible for day-to-day management and decision-making for the project. The Project Coordinator’s prime responsibility is to ensure that the project produces the results specified in the project document, to the required standard of quality and within the specified constraints of time and cost.

- Specific responsibilities include:

- Provide direction and guidance to project team(s)/ responsible party (ies);

- Liaise with the Project Board to assure the overall direction and integrity of the project;

- Identify and obtain any support and advice required for the management, planning and control of the project;

- Responsible for project administration;

- Plan the activities of the project and monitor progress against the project results framework and the approved annual workplan;

- Mobilize personnel, goods and services, and training for activities, including drafting terms of reference and work specifications, and overseeing all contractors’ work;

- Monitor events as determined in the project monitoring schedule plan/timetable, and update the plan as required;

- Manage requests for the provision of financial resources by UNDP, through advance of funds, direct payments or reimbursement using the fund authorization and certificate of expenditures;

- Monitor financial resources and accounting to ensure the accuracy and reliability of financial reports;

- Be responsible for preparing and submitting financial reports to UNDP on a quarterly basis;

- Manage and monitor the project risks initially identified and submit new risks to the project board for consideration and decision on possible actions if required; update the status of these risks by maintaining the project risks log;

- Capture lessons learned during project implementation;

- Prepare the annual workplan for the following year; and update the Atlas Project Management module if external access is made available.

- Prepare the GEF PIR and submit the final report to the Project Board;

- Based on the GEF PIR and the Project Board review, prepare the AWP for the following year.

- Ensure the mid-term review process is undertaken as per the UNDP guidance, and submit the final MTR report to the Project Board.

- Identify follow-on actions and submit them for consideration to the Project Board;

- Ensure the terminal evaluation process is undertaken as per the UNDP guidance, and submit the final TE report to the Project Board.

- Project Assurance:  UNDP provides a three–tier supervision, oversight and quality assurance role – funded by the GEF agency fee – involving UNDP staff in Country Offices and at regional and headquarters levels. Project Assurance must be totally independent of the Project Management function. The quality assurance role supports the Project Board and Project Management Unit by carrying out objective and independent project oversight and monitoring functions. This role ensures appropriate project management milestones are managed and completed. The Project Board cannot delegate any of its quality assurance responsibilities to the Project Coordinator.  This project oversight and quality assurance role is covered by the GEF Agency.

- Governance role for project target groups:  A Project Technical Committee and three Provincial Working Groups will be established. The Project Technical Committee will be chaired by the SGAyDS and will comprise technical level representatives from SGAyDS, UNDP, INTA, provincial governments of Buenos Aires, Jujuy and Mendoza, and other institutions and organizations. Upon project start-up the Project Board will agree on the composition of the committee, including representatives of public and private institutions and CSOs, particularly those related to the target sectors. The Technical Committee will provide technical inputs for the achievement of project products and/or outcomes, and will be specifically responsible for ensuring alignment of project activities with institutional mandates as well as for the adequate participation of all key target groups in project activities and project-related decision making processes. The functioning of this committee shall be agreed upon during the project´s start-up phase, including specific programs of work, scope of roles and responsibilities, decision-making flow and frequency of meetings.

- Three Provincial Working Groups will be established, one in each of the pilot provinces.  These working groups will be comprised of the focal points designated by the provincial authorities and technical teams designated by each province, with the participation of other key institutions of the province that are relevant to the project.  The main responsibilities of these committees will be: linking the project objectives with the provincial plans (both institutional and sectoral) as well as ongoing or planned interventions or investments; promoting inter-institutional and inter-sectoral coordination; coordinating the participation of institutions in the implementation of project activities; and fostering stakeholder participation. The composition and functioning will be agreed upon during the project´s start-up phase, including specific programs of work, the scope of roles and responsibilities, decision-making flow and frequency of meetings.

# Financial Planning and Management

- The total cost of the project is USD 51,385,434.  This is financed through a GEF grant of USD 8,995,434, and USD 42,390,000 in parallel co-financing.  UNDP, as the GEF Implementing Agency, is responsible for the execution of the GEF resources and the cash co-financing transferred to UNDP´s bank account only.

- Parallel co-financing:  The actual realization of project co-financing will be monitored during the mid-term review and terminal evaluation process and will be reported to the GEF. The planned parallel co-financing will be used as follows:

Table 7 – Parallel Co-financing

| Co-financing source |  | Co-financing type | Co-financing amount USD | Planned Activities/Outputs | Risks | Risk Mitigation Measures |
| --- | --- | --- | --- | --- | --- | --- |
| National government | SGAyDS | Grants | 12,611,232 | Cost of salaries of managerial, technical (ELUP specialists, Communication Specialist) and administrative staff assigned to the project; publications; operation and maintenance of premises for project offices; operation and maintenance of equipment; investment in Policies and Programs of the Secretariat of Environmental Policy for Natural Resources and the National Directorate for Planning and Environmental Land Use Planning | Medium Risk. Dependent on annual budgeting and effective allocation of funds to the institution. | The UNDP CO will monitor the co-financing contributions to the project. |
|  |  | In-kind | 2,910,000 | Premises for project offices; basic services; office furniture and equipment; vehicles. | Low Risk | The UNDP CO will monitor the co-financing contributions to the project. |
| National government | INTA | Grants | 4,500,000 | Cost of salaries of managerial, technical and administrative staff assigned to the project; contracts with third party organizations; training (individual, group, field trips, study tours, workshops, seminars); meetings; maintenance of equipment. | Medium Risk. Dependent on annual budgeting and effective allocation of funds to the institution. | The UNDP CO will monitor the co-financing contributions to the project. |
|  |  | In-kind | 1,640,000 | Computer equipment; environmental monitoring and laboratory equipment and inputs (e.g,. for monitoring of water and soil quality), agricultural implements; vehicles; premises and infrastructure. | Low Risk | The UNDP CO will monitor the co-financing contributions to the project. |
| National government | CONICET | In-kind | 5,000,000 | Cost of salaries of managerial, technical and administrative staff assigned to the project; contracts with third party organizations; training (individual, group, field trips, study tours, workshops, seminars); meetings; maintenance of equipment; investments in programs and projects related to BD and LD, land use and social issues. | Medium Risk. Dependent on annual budgeting and effective allocation of funds to the institution. | The UNDP CO will monitor the co-financing contributions to the project. |
| National government | INAI | In-kind | 350,000 | Cost of salaries of managerial, technical and administrative staff assigned to the project; contracts with third party organizations; training (individual, group, field trips, study tours, workshops, seminars); meetings; maintenance of equipment; investments in programs and projects supporting indigenous communities. | Medium Risk. Dependent on annual budgeting and effective allocation of funds to the institution. | The UNDP CO will monitor the co-financing contributions to the project. |
| Provincial government | Ministry of Environment of Jujuy | Grants | 1,054,054 | Cost of salaries of managerial, technical and administrative staff assigned to the project; contracts with third party organizations; training (individual, group, field trips, study tours, workshops, seminars); meetings; maintenance of equipment; investments in programs and projects related to ELUP, native forests and renewable energies. | Medium Risk. Dependent on annual budgeting and effective allocation of funds to the institution. | The UNDP CO will monitor the co-financing contributions to the project. |
|  |  | In-kind | 458,050 | Computer equipment; equipment for environmental monitoring (e.g. GPS, camping equipment, sampling and analysis equipment; vehicles; premises and infrastructure. | Low Risk | The UNDP CO will monitor the co-financing contributions to the project. |
| Provincial government | OPDS | Grants | 6,666,666 | Cost of salaries of managerial, technical and administrative staff assigned to the project; contracts with third party organizations; training (individual, group, field trips, study tours, workshops, seminars); meetings; maintenance of equipment | Medium Risk. Dependent on annual budgeting and effective allocation of funds to the institution. | The UNDP CO will monitor the co-financing contributions to the project. |
|  |  | In-kind | 166,666 | Computer equipment; equipment for environmental monitoring (e.g. GPS, camping equipment, sampling and analysis equipment) vehicles; premises and infrastructure. | Low Risk | The UNDP CO will monitor the co-financing contributions to the project. |
| Provincial government | SAOT | Grants | 6,666,666 | Cost of salaries of managerial, technical and administrative staff assigned to the project; contracts with third party organizations; training (individual, group, field trips, study tours, workshops, seminars); meetings; maintenance of equipment; investments in programs and projects related to ELUP, particularly the provincial laws Nº8051 and Nº8999 | Medium Risk. Dependent on annual budgeting and effective allocation of funds to the institution. | The UNDP CO will monitor the co-financing contributions to the project. |
|  |  | In-kind | 166,666 | Equipment for environmental monitoring (e.g., GPS, camping equipment, sampling and analysis equipment) and computer equipment; vehicles; premises and infrastructure. | Low Risk | The UNDP CO will monitor the co-financing contributions to the project. |
| GEF Agency | UNDP | Grants | 200,000 | Other projects being implemented by UNDP Country Office that will provide a federal enabling framework to reinforce ELUP, will allow application of ELUP procedures and instruments in pilot provinces and will provide a replicability framework. | Low Risk | UNDP CO is the implementing agency for these projects that represent co-financing and will monitor the inputs to the project. |
| Total |  |  | 42,390,000 |  |  |  |

- UNDP Direct Project Services as requested by Government (if any):  UNDP, as the Implementing Agency for this project, will provide project management cycle services for the project as defined by the GEF Council.  In addition, the Government of Argentina may request UNDP direct services for specific projects, according to its policies and convenience.  The UNDP and the Government of Argentina acknowledge and agree that those services are not mandatory, and will be provided only upon Government request. If requested the services would follow the UNDP policies on the recovery of direct costs. These services (and their costs) are specified in the Agreement (Annex J). As is determined by the GEF Council requirements, these service costs will be assigned as Project Management Cost, identified in the project budget.

Cost Recovery Policy

- As per Determination and Decision of the UNDP’s Executive Board on the Policy on Cost Recovery from Regular and Other Resources, UNDP shall recover costs for the provision of direct project services (DPS).  In GEF funded projects, DPS costs are those incurred by UNDP for the provision of services requested by a host Government and that are execution driven and can be traced in full to the delivery of project inputs. They relate to operational and administrative support activities carried out by UNDP offices on behalf of the Direct Implementation Modality (DIM) or Country Office support to National Implementation Modality (NIM) and include the provision of the following estimated services:

- Payments, disbursements and other financial transactions.

- Recruitment of staff, project personnel, and consultants.

- Procurement of services and equipment, including disposal.

- Organization of training activities, conferences, and workshops, including fellowships.

- Travel authorization, visa requests, ticketing, and travel arrangements.

- Shipment, custom clearance, vehicle registration, and accreditation.

- In accordance with UNDP policy on cost recovery (2010) and the BOM and UNDP GEF guidance on Direct Project Costs (2012) the costs incurred by UNDP for the provision of direct project services needs to be recovered on the basis of estimated actual costs expected to be incurred or on a per-transaction basis using the Universal price list or Local Price List costing template and should be charged directly to project budgets. The estimated costs are included in the project budget and are funded within the total project management Costs (PMC) allocation provided by GEF to the Implementation Parties and cannot exceed the total PMC allocation. Once incurred after each of the above services is provided by UNDP, costs shall be charged against direct project costs account codes: 64397 – ‘Services to projects - CO staff’ and 74596 – ‘Services to projects - GOE for CO’.

- Budget Revision and Tolerance:  As per UNDP requirements outlined in the UNDP POPP, the project board will agree on a budget tolerance level for each plan under the overall annual work plan allowing the project Coordinator to expend up to the tolerance level beyond the approved project budget amount for the year without requiring a revision from the Project Board. Should the following deviations occur, the Project Coordinator and UNDP Country Office will seek the approval of the UNDP-GEF team to ensure accurate reporting to the GEF: a) Budget re-allocations between components in the project with amounts involving 10% of the total project grant or more; b) Introduction of new budget items/or components that exceed 5% of the original GEF allocation.

- Any over-expenditure incurred beyond the available GEF grant amount will be absorbed by non-GEF resources (e.g. UNDP TRAC or cash co-financing).

- Refund to GEF:  Should a refund of unspent funds to the GEF be necessary, this will be managed directly by the UNDP-GEF Unit in New York.

- Project Closure:  Project closure will be conducted as per UNDP requirements outlined in the UNDP POPP. On an exceptional basis only, a no-cost extension beyond the initial duration of the project will be sought from the UNDP-GEF Regional Technical Advisor and then the UNDP-GEF Executive Coordinator.

- Operational completion: The project will be operationally completed when the last UNDP-financed inputs have been provided and the related activities have been completed. This includes the final clearance of the Terminal Evaluation Report (that will be available in English) and the corresponding management response, and the end-of-project review Project Board meeting. The Implementing Partner through a Project Board decision will notify the UNDP Country Office when operational closure has been completed. At this time, the relevant parties will have already agreed and confirmed in writing on the arrangements for the disposal of any equipment that is still the property of UNDP.

- Transfer or disposal of assets: In consultation with the NIM Implementing Partner and other parties of the project, UNDP programme manager (UNDP Resident Representative) is responsible for deciding on the transfer or other disposal of assets. Transfer or disposal of assets is recommended to be reviewed and endorsed by the project board following UNDP rules and regulations. Assets may be transferred to the government for project activities managed by a national institution at any time during the life of a project. In all cases of transfer, a transfer document must be prepared and kept on file.

- Financial completion:  The project will be financially closed when the following conditions have been met: a) The project is operationally completed or has been cancelled; b) The Implementing Partner has reported all financial transactions to UNDP; c) UNDP has closed the accounts for the project; d) UNDP and the Implementing Partner have certified a final Combined Delivery Report (which serves as final budget revision).

- The project will be financially completed within 12 months of operational closure or after the date of cancellation. Between operational and financial closure, the implementing partner will identify and settle all financial obligations and prepare a final expenditure report. The UNDP Country Office will send the final signed closure documents including confirmation of final cumulative expenditure and unspent balance to the UNDP-GEF Unit for confirmation before the project will be financially closed in Atlas by the UNDP Country Office.

# Total Budget and Work Plan

| TOTAL BUDGET AND WORK PLAN |  |  |  |
| --- | --- | --- | --- |
| Proposal or Award ID: | 114826 | Atlas Primary Output Project ID: | 112703 |
| Atlas Proposal or Award Title: | Mainstreaming biodiversity conservation and sustainable land management (SLM) into development planning: Making Environmental Land Use Planning (ELUP) Operational in Argentina |  |  |
| Atlas Business Unit | ARG10 |  |  |
| Atlas Primary Output Project Title | Mainstreaming biodiversity conservation and sustainable land management (SLM) into development planning: Making Environmental Land Use Planning (ELUP) Operational in Argentina |  |  |
| UNDP-GEF PIMS No: | 5791 |  |  |
| Implementing Partner | Secretariat of Environment and Sustainable Development (SGAyDS) |  |  |

| GEF Component/ Atlas Activity | Impl. Partner | Fund ID | Donor Name | Account Code | ATLAS Budget Description | Amount Year 1 | Amount Year 2 | Amount Year 3 | Amount Year 4 | Amount Year 5 | Amount Year 6 | Total | Budget Note: |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Outcome 1: | SGAyDS | 62000 | GEF | 71300 | Local Consultants | 12,000 | 12,000 | 12,000 | 12,000 | - | - | 48,000 | 1 |
|  | SGAyDS | 62000 | GEF | 71400 | Contractual Servicies - Individ | 34,617 | 34,617 | 34,617 | 22,617 | 22,618 | 22,618 | 171,704 | 2 |
|  | SGAyDS | 62000 | GEF | 71600 | Travel | 73,759 | 73,759 | 61,260 | 67,927 | 67,928 | 67,927 | 412,560 | 3 |
|  | SGAyDS | 62000 | GEF | 72200 | Equipment and Furniture | 75,000 | - | - | - | - | - | 75,000 | 4 |
|  | SGAyDS | 62000 | GEF | 72400 | Communic & Audiovisual Equip | 5,356 | - | - | - | - | - | 5,356 | 5 |
|  | SGAyDS | 62000 | GEF | 72800 | Information Technology Equipmt | 61,025 | - | - | - | - | - | 61,025 | 6 |
|  | SGAyDS | 62000 | GEF | 74200 | Audio Visual & Print Prod Costs | 2,000 | 2,000 | 2,000 | 3,333 | 9,333 | 9,334 | 28,000 | 7 |
|  | SGAyDS | 62000 | GEF | 75700 | Training, Workshops and Confer | 132,669 | 132,669 | 132,669 | 132,669 | 132,670 | 132,669 | 796,015 | 8 |
| Total Outcome 1 |  |  |  |  |  | 396,426 | 255,045 | 242,546 | 238,546 | 232,549 | 232,548 | 1,597,660 |  |
| Outcome 2: | SGAyDS | 62000 | GEF | 71400 | Contractual Services - Individ | 52,486 | 52,486 | 52,486 | 52,486 | 52,488 | 52,488 | 314,920 | 9 |
|  | SGAyDS | 62000 | GEF | 71600 | Travel | 23,832 | 23,832 | 23,832 | 23,832 | 23,832 | 23,832 | 142,992 | 10 |
|  | SGAyDS | 62000 | GEF | 72200 | Equipment and Furniture | 112,500 | 100,000 | 100,000 | 100,000 | 100,000 | - | 512,500 | 11 |
|  | SGAyDS | 62000 | GEF | 72300 | Materials & Goods | 8,333 | 8,333 | 8,333 | 8,333 | 8,334 | 8,334 | 50,000 | 12 |
|  | SGAyDS | 62000 | GEF | 72100 | Contractual Services-Companies | - | 940,000 | 940,000 | 940,000 | 940,000 | 940,000 | 4,700,000 | 13 |
|  | SGAyDS | 62000 | GEF | 75700 | Training, Workshops and Confer | 25,390 | 25,391 | 25,391 | 25,391 | 25,392 | 25,392 | 152,347 | 14 |
| Total Outcome 2 |  |  |  |  |  | 222,541 | 1,150,042 | 1,150,042 | 1,150,042 | 1,150,046 | 1,050,046 | 5,872,759 |  |
| Outcome 3: | SGAyDS | 62000 | GEF | 71400 | Contractual Services - Individ | 15,950 | 15,950 | 15,950 | 27,950 | 27,952 | 27,952 | 131,704 | 15 |
|  | SGAyDS | 62000 | GEF | 71600 | Travel | 8,617 | 8,617 | 8,617 | 22,105 | 22,106 | 22,106 | 92,168 | 16 |
|  | SGAyDS | 62000 | GEF | 72100 | Contractual Services-Companies | 20,000 | - | - | - | - | 20,000 | 40,000 | 17 |
|  | SGAyDS | 62000 | GEF | 74200 | Audio Visual&Print Prod Costs | - | - | - | 10,000 | 10,000 | 10,000 | 30,000 | 18 |
|  | SGAyDS | 62000 | GEF | 75700 | Training, Workshops and Confer | 15,333 | 15,333 | 15,332 | 132,703 | 83,539 | 83,540 | 345,780 | 19 |
| Total Outcome 3 |  |  |  |  |  | 59,900 | 39,900 | 39,899 | 192,758 | 143,597 | 163,598 | 639,652 |  |
| Outcome 4: | SGAyDS | 62000 | GEF | 71200 | International Consultants | - | - | 15,000 | - | - | 18,000 | 33,000 | 20 |
|  | SGAyDS | 62000 | GEF | 71300 | Local Consultants | 4,000 | 4,000 | 12,000 | 4,000 | 4,000 | 12,000 | 40,000 | 21 |
|  | SGAyDS | 62000 | GEF | 71400 | Contractual Services - Individ | 11,950 | 11,950 | 11,950 | 11,950 | 11,952 | 11,952 | 71,704 | 22 |
|  | SGAyDS | 62000 | GEF | 71600 | Travel | 2,000 | 2,000 | 12,818 | 2,000 | 2,000 | 12,818 | 33,636 | 23 |
|  | SGAyDS | 62000 | GEF | 72100 | Contractual Services-Companies | 15,000 | 2,500 | 17,500 | - | 2,500 | 32,500 | 70,000 | 24 |
|  | SGAyDS | 62000 | GEF | 74100 | Professional Services | 5,000 | 5,000 | - | 5,000 | 5,000 | 10,000 | 30,000 | 25 |
|  | SGAyDS | 62000 | GEF | 74200 | Audio Visual & Print Prod Costs | 1,337 | 20,266 | 30,266 | 20,266 | 20,267 | 20,267 | 112,669 | 26 |
|  | SGAyDS | 62000 | GEF | 75700 | Training, Workshops and Confer | 36,000 | 6,000 | 6,000 | 6,000 | 6,000 | 6,000 | 66,000 | 27 |
| Total Outcome 4 |  |  |  |  |  | 75,287 | 51,716 | 105,534 | 49,216 | 51,719 | 123,537 | 457,009 |  |
| Project Management | SGAyDS | 62000 | GEF | 71400 | Contractual Services - Individ | 20,909 | 20,909 | 20,909 | 20,909 | 20,910 | 20,910 | 125,456 | 28 |
|  | SGAyDS | 62000 | GEF | 72800 | Information Technology Equipmt | 4,500 | - | - | - | - | - | 4,500 | 29 |
|  | SGAyDS | 62000 | GEF | 74596 | UNDP Recovery Cost Charges | 49,733 | 49,733 | 49,733 | 49,733 | 49,733 | 49,733 | 298,398 | 30 |
| Total PMC |  |  |  |  |  | 75,142 | 70,642 | 70,642 | 70,642 | 70,643 | 70,643 | 428,354 |  |
| PROJECT TOTAL |  |  |  |  |  | 829,296 | 1,567,345 | 1,608,663 | 1,701,204 | 1,648,554 | 1,640,372 | 8,995,434 |  |

| Summary of Funds |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Institution | Amount | Amount | Amount | Amount | Amount | Amount | Total |
|  | Year 1 (USD) | Year 2 (USD) | Year 3 (USD) | Year 4 (USD) | Year 5 (USD) | Year 6 (USD) |  |
| GEF | 829,296 | 1,567,345 | 1,608,663 | 1,701,204 | 1,648,554 | 1,640,372 | 8,995,434 |
| SGAyDS | 2,586,872 | 2,586,872 | 2,586,872 | 2,586,872 | 2,586,872 | 2,586,872 | 15,521,232 |
| INTA | 1,023,333 | 1,023,333 | 1,023,333 | 1,023,333 | 1,023,334 | 1,023,334 | 6,140,000 |
| SAOT/Mendoza | 1,139,000 | 1,139,000 | 1,139,000 | 1,139,000 | 1,139,000 | 1,138,332 | 6,833,332 |
| Ministry of Environment/Jujuy | 252,017 | 252,017 | 252,017 | 252,017 | 252,018 | 252,018 | 1,512,104 |
| OPDS/Buenos Aires | 1,139,000 | 1,139,000 | 1,139,000 | 1,139,000 | 1,139,000 | 1,138,332 | 6,833,332 |
| CONICET | 833,333 | 833,333 | 833,333 | 833,333 | 833,334 | 833,334 | 5,000,000 |
| INAI | 58,333 | 58,333 | 58,333 | 58,333 | 58,334 | 58,334 | 350,000 |
| UNDP | 33,334 | 33,334 | 33,333 | 33,333 | 33,333 | 33,333 | 200,000 |
| Total | 7,894,518 | 8,632,567 | 8,673,884 | 8,766,425 | 8,713,779 | 8,704,261 | 51,385,434 |

| Budget note number | Comments |
| --- | --- |
| Outcome 1: Federal enabling framework and strategies to reinforce ELUP, and underpin implementation in priority ecosystems and habitats to reduce pressure from key production sectors, (target sectors: agriculture & livestock; mining and peri-urban infrastructure, tourism) |  |
| 1 | Local consultant to support the development of criteria for priority areas of environmental value for ELUP (Output 1.3). Total costs: USD 48,000 (48 months x USD 1,000/month) |
| 2 | - Project Coordinator to technically support the SGAyDS in the implementation of the ELUP approach, including the development of ELUP criteria; assessment of ELUP instruments; development of maps of priority areas of environmental value for ELUP; analysis of ELUP regulations; assessment of valuation methodologies for environmental services. Total cost: USD 28,028 (14 months x USD 2,002/month) - Information Systems Specialist to support the development of the environmental information system: systematization and standardization of information; defining indicators for ELUP; preparation of maps of priority areas for ELUP (Output 1.1). Total cost: USD 36,000 (36 months x USD 1,000/month) - Economic and Financial Instruments Specialist to support assessment and development of compensation schemes; valuation of ecosystem goods and services (Output 1.2) and development of eligibility criteria for accessing economic and financial instruments and mainstreaming of ELUP in economic and financial instruments (Output 1.3). Total Cost: USD 48,000 (48 months x USD 1,000/month) - Stakeholder Engagement Specialist to support national implementation of the Stakeholder Engagement Plan, including stakeholder mapping, development of the detailed Indigenous Peoples Plan (IPP), design and implementation of multi-stakeholder dialogue and coordination spaces, developing capacity building programs for national level strengthening, promotion of stakeholder participation in project interventions (Output 1.4). Total cost: USD 30,000 (30 months x USD 1,000) - Gender Specialist for supervision, coordination and implementation of the Gender Action Plan: gender mainstreaming in environmental information management (Output 1.1), ELUP federal regulations (Output 1.2), economic and financial instruments (Output 1.3) and women´s participation in stakeholder dialogue (Output 1.4). Total cost: USD 18,000 (18 months x USD 1,000/month). - Administrative Assistant to support the Project Coordinator in planning and supporting implementation of activities under Outcome 1. Total cost: USD 11,676 (14 months x USD 834/month) |
| 3 | Travel related to technical support for data collection, validation of environmental data and participation in IDERA meetings (Output 1.1), dialogue and coordination for: validation of ELUP criteria, valuation of environmental services, ELUP regulatory proposals (Output 1.2); economic and financial instruments (Output 1.3); stakeholder mapping, development of IPP, and stakeholder participation in dialogue spaces (Output 1.4) and gender mainstreaming in project activities (cross-cutting). Total cost: USD 412,560 (72 months x average USD 5,730/month) |
| 4 | Two 4x4 vehicles for mobilization of project staff for inter-institutional coordination, development of partnerships and dialogue spaces. Total cost: USD 75,000 (2 x USD 37,500). Purchase of vehicles is proposed given that the concerned institutions cannot guarantee that their own resources are sufficient given that public institutions currently have budgetary restrictions in regard to procurement of - among others -equipment and vehicles. |
| 5 | Projector and camera for presentations in workshops and meetings. Total cost: USD 5,356 |
| 6 | Computer equipment for management of GIS/data bases and mapping of priority areas for ELUP (PCs, printers, external drives, accessories). Total cost: USD 61,025 |
| 7 | Publications related to ELUP implementation. Total cost: USD 28,000: a) criteria to define valuation of ES, BD conservation, SLM practices and assessment of compensation schemes (USD 8,000); b) guide to define land uses and restrictions to production adapted to local realities (USD 8,000); c) information materials on ELUP (USD 8,000). d) project communication and information materials (USD 4,000) |
| 8 | Workshops/meetings/roundtables for national discussion, awareness raising and capacity building. Total cost USD 796,015 a) environmental variables and data, ELUP criteria, maps of priority areas for ELUP, coordination with provincial IDEs (Output 1.1): USD 272,015; b) criteria for federal level regulations and development of a federal minimum standard regulation for ELUP (Output 1.2): USD 107,000 c) mainstreaming of ELUP in economic and financial instruments (Output 1.3): USD 42,000 d) awareness raising and capacity building for ELUP and stakeholder participation (Output 1.4): USD 303,000 e) awareness raising and capacity building for gender mainstreaming (cross-cutting): USD 72,000 |
| Outcome 2: Application of ELUP procedures and instruments in pilot Provinces with targeted ecoregions and production sector land uses |  |
| 9 | - Project Coordinator to provide technical advice in the three pilot provinces and to participating environmental authorities and key stakeholders in planning and developing ELUP at provincial and target landscape levels. Total cost: USD 28,028 (14 months x USD 2,002/month) - Stakeholder Engagement Specialist to support provincial implementation of the Stakeholder Engagement Plan, including stakeholder mapping, design and implementation of multi-stakeholder dialogue and coordination spaces, developing capacity building programs for provincial level strengthening, promotion of stakeholder participation in project interventions (Output 2.2). Total cost: USD 14,000 (14 months x USD 1,000). - Gender Specialist for supervision, coordination and implementation of the Gender Action Plan: gender mainstreaming in provincial ELUP instruments (Output 2.1), participation of women in dialogue spaces (Output 2.2), economic and financial instruments (Output 2.3) and testing and validating best practices (Output 2.4). Total cost: USD 18,000 (18 months x USD 1,000/month). - Three provincial technicians, one based in each province for backstopping and technical support, and monitoring of project activities in pilot provinces. Total cost: USD 243,216 (3 x 72 months x USD 1,126/month) - Administrative Assistant to support the Project Coordinator in planning and supporting implementation of activities under Outcome 2. Total cost: USD 11,676 (14 months x USD 834/month) |
| 10 | Travel related to technical support for development of provincial ELUP (Output 2.1); promotion of stakeholder participation (Output 2.2); economic instruments (Output 2.3); and monitoring of best practices implemented by the provinces in the target landscapes (Output 2.4). Total cost: USD 142,992 (72 months x USD 1,986/month) |
| 11 | - Three 4 x 4 vehicles for project mobilization in the provinces of Buenos Aires, Mendoza and Jujuy. Total cost: USD 112,500 (3 x USD 37,500). Purchase of vehicles is proposed given that the concerned institutions cannot guarantee that their own resources are sufficient to ensure an adequate level of presence in the target landscapes to ensure the proposed interventions are effectively carried out to achieve the expected outputs and outcomes. Several target landscapes are located far from the provincial capitals and distances are large. Public institutions currently have budgetary restrictions in regard to procurement of vehicles. - Equipment to strengthen the provinces for implementation and monitoring of activities: computer equipment and accessories; equipment for management of remote sensing information and large data bases; equipment for environmental monitoring. Total cost: USD 400,000. This equipment will be detailed in the agreements to be signed by the SGAyDS and pilot provinces for implementation of activities at provincial level. |
| 12 | Fuel for project mobilization in target landscapes of the provinces (Mendoza – Malargüe; La Plata – Carmen de Patagones; Jujuy – Paso Jama and Jujuy – Valle Grande). Total cost: USD 50,000 |
| 13 | Plan to engage the provincial governments of Buenos Aires, Mendoza and Jujuy, and INTA, for development of provincial ELUP regulations (Output 1.1), stakeholder dialogue and coordination (Output 2.2); economic and financial instruments (Output 2.3) and testing and validating environmentally friendly and sustainable practices (Output 2.4). Total cost: USD 4,700,000 (3 agreements with provinces x USD 1,300,000 each; USD 800,000 agreement with INTA). All agreements will follow UNDP policies. |
| 14 | Workshops/meetings/roundtables for provincial level discussion. Total cost USD 152,347 a) environmental variables, standardization of data, ELUP regulations (Output 2.1): USD 20,000 b) dialogue, awareness raising and capacity building for ELUP and stakeholder participation (Output 2.2): USD 56,000 c) development of economic and financial instruments (Output 2.3): USD 40,347 d) awareness raising and capacity building for gender mainstreaming (cross-cutting): USD 36,000 |
| Outcome 3: Replicability framework for ELUP uptake in all Argentine provinces |  |
| 15 | - Project Coordinator to technically support the SGAyDS in development of the ELUP approach, including the assessment of experiences and lessons learned from ongoing and past projects; facilitating dialogue and coordination with selected non-pilot provinces to initiate ELUP; elaboration of methodological guides for ELUP. Total cost: USD 28,028 (14 months x USD 2,002/month) - Information Systems Specialist to support the design of the system for evaluation and monitoring of ELUP implementation and develop a financial sustainability plan for the system (Output 3.3). Total cost: USD 36,000 (36 months x USD 1,000/month) - Economic and Financial Instruments Specialist to support assessment of lessons learned on ecosystem services valuation, economic and financial instruments and compensation schemes at national level (Output 3.1). Total Cost: USD 24,000 (24 months x USD 1,000/month) - Stakeholder Engagement Specialist to support development of capacity building programs for non-pilot provinces and promotion of stakeholder participation (Output 3.2). Total cost: USD 14,000 (14 months x USD 1,000). - Gender Specialist for supervision, coordination and implementation of the Gender Action Plan: gender mainstreaming assessment in non-pilot provinces (Output 3.1) in capacity building programs (Output 3.2), and methodological guides for ELUP (Output 3.3). Total cost: USD 18,000 (18 months x USD 1,000/month). - Administrative Assistant to support the Project Coordinator in planning and following implementation of activities under Outcome 3. Total cost: USD 11,676 (14 months x USD 834/month) |
| 16 | Travel related to support in evaluating lessons from ongoing and past projects in non-pilot provinces (Output 3.1), stakeholder mapping and development of capacity building programs for non-pilot provinces (Output 3.2); and participation in IDERA meetings for development of the system for evaluation and monitoring of ELUP. Total cost: USD 92,168 |
| 17 | Contract to undertake a Knowledge, Aptitude and Practice (KAP) survey to assess the degree in which stakeholders have increased their knowledge, acceptance and application of ELUP (baseline in PY1 and target measurement in PY6). Total cost: USD 40,000 |
| 18 | Publications related to ELUP implementation and upscaling: Methodological guides for implementation of ELUP in pilot provinces (USD 9,000); Methodological guides for implementation of ELUP in non-pilot provinces (USD 9,000); Methodological guides for implementation of ELUP in shared ecosystems (USD 9,000); project communication and information materials (USD 3,000). Total cost: USD 30,000 |
| 19 | Workshops/meetings/roundtables. Total cost: USD 345,780 a) Assessment of lessons learned (Output 3.1): USD 20,000 b) Awareness raising and capacity building of non-pilot provinces for developing and implementing ELUP (Output 3.2): USD 216,167 c) Development of the system for evaluation and monitoring of ELUP and coordination for mainstreaming of ELUP in national programs (Output 3.3): USD 109,613 |
| Outcome 4: Dissemination of lessons learned and monitoring and evaluation |  |
| 20 | International consultants for: - Mid-term Review. Total cost USD 15,000 (6 weeks x USD 2,500) - Terminal Evaluation. Total cost USD 18,000 (6 weeks x USD 3,000) |
| 21 | Local consultants to support: - Mid-term Review. Total cost: USD 6,000 (6 weeks x USD 1,000) - Terminal Evaluation Total cost: USD 6,000 (6 weeks x USD 1,000)); - Tracking of GEF Core Indicators at mid-term (1 month x USD 2,000) and end of project (1 month x USD 2,000) - Annual monitoring of indicators. Total cost: USD 24,000 (6 years x USD 4,000/year) Total cost: USD 40,000 |
| 22 | - Project Coordinator to coordinate and implement the M&E plan. Total cost: USD 28,028 (14 months x USD 2,002/month) - Stakeholder Engagement Specialist to monitor project-level stakeholder engagement and implementation of the IPP. Total cost: USD 14,000 (14 months x USD 1,000). - Gender Specialist to monitor project-level gender mainstreaming. Total cost: USD 18,000 (18 months x USD 1,000/month). - Administrative Assistant to support the Project Coordinator in implementing the M&E plan. Total cost USD 11,676 (14 months x USD 834) |
| 23 | Travel: International travel for external evaluations (USD 21,636) and local travel for monitoring and exchange of lessons/experiences in ELUP: Total cost: USD 12,000. Total cost. USD 33,636 |
| 24 | Contracts for: measurement of progress in the Sustainable Livelihoods Framework Index (baseline and end of project): USD 30,000; field surveys/assessments to measure progress in best practices in target landscapes/BD and LD indicators: USD 30,000; gender surveys: USD 10,000 Total cost of contracts: USD 70,000 |
| 25 | Annual project audits: USD 30,000 (6 audits x USD 5,000/each) Total cost: USD 30,000 |
| 26 | Publications on project best practices and lessons learned (at least 1 on gender mainstreaming) and project communication and information materials. All publication costs includes its translations services. Total cost: USD 112,669 |
| 27 | Workshops. Total cost: 66,000 a) Project Inception Workshop (national): USD 15,000 b) Project Inception Workshops (3 provinces): USD 15,000 (3 workshops x USD 5,000/each) c) Annual meetings of the Project Board: USD 6,000 (6 meetings x USD 1,000/each) d) Annual project planning/lessons learned workshops: USD 30,000 (6 workshops x USD 5,000/each) |
| Project Management Cost |  |
| 28 | - Part of time of Project Coordinator dedicated to project management: Total cost USD 28,028 (14 months x USD 2,002/month) - Part of time of Administrative Assistant in support of project management. Total cost USD 11,676 (14 months x USD 834/month) - Project Accountant for project management. Total cost USD 85,752 (72 months x USD 1,191/month) |
| 29 | Computer equipment for Project Coordinator, Project Administrative Assistant and Project Accountant. Total cost USD 4,500 (3 PCs x USD 1,500) |
| 30 | UNDP Cost Recovery Charges: USD 298,398. Estimated UNDP Direct Project Service/Cost recovery charges to UNDP for executing services. In accordance with GEF Council requirements, the costs of these services will be part of the executing entity’s Project Management Cost allocation identified in the project budget. DPS costs will be charged at the end of each year based on the UNDP Universal Price List (UPL) or the actual corresponding service cost. The amounts here are estimations based on the services indicated, however as part of annual project operational planning the DPS to be requested during the calendar year will be defined and the amount included in the yearly project management budgets and will be charged based on actual services provided at the end of that year. |

# Legal Context

- This project document shall be the instrument referred to as such in Article 1 of the Standard Basic Assistance Agreement between the Government of Argentina and UNDP, signed on February 26, 1985 and approved by Law 23396 of October 10, 1986.   All references in the SBAA to “Executing Agency” shall be deemed to refer to “Implementing Partner.”

- This project will be executed by the Secretariat of Environment and Sustainable Development (SGAyDS) (“Implementing Partner”) in accordance with its financial regulations, rules, practices and procedures only to the extent that they do not contravene the principles of the Financial Regulations and Rules of UNDP. Where the financial governance of an Implementing Partner does not provide the required guidance to ensure best value for money, fairness, integrity, transparency, and effective international competition, the financial governance of UNDP shall apply.

- Any designations on maps or other references employed in this project document do not imply the expression of any opinion whatsoever on the part of UNDP concerning the legal status of any country, territory, city or area or its authorities, or concerning the delimitation of its frontiers or boundaries.

# Risk Management

- Consistent with the Article III of the SBAA [or the Supplemental Provisions to the Project Document], the responsibility for the safety and security of the Implementing Partner and its personnel and property, and of UNDP’s property in the Implementing Partner’s custody, rests with the Implementing Partner.  To this end, the Implementing Partner shall:

- put in place an appropriate security plan and maintain the security plan, taking into account the security situation in the country where the project is being carried;

- assume all risks and liabilities related to the Implementing Partner’s security, and the full implementation of the security plan.

- UNDP reserves the right to verify whether such a plan is in place, and to suggest modifications to the plan when necessary. Failure to maintain and implement an appropriate security plan as required hereunder shall be deemed a breach of the Implementing Partner’s obligations under this Project Document.

- The Implementing Partner agrees to undertake all reasonable efforts to ensure that no UNDP funds received pursuant to the Project Document are used to provide support to individuals or entities associated with terrorism and that the recipients of any amounts provided by UNDP hereunder do not appear on the list maintained by the Security Council Committee established pursuant to resolution 1267 (1999). The list can be accessed via http://www.un.org/sc/committees/1267/aq_sanctions_list.shtml.

- Social and environmental sustainability will be enhanced through application of the UNDP Social and Environmental Standards (http://www.undp.org/ses) and related Accountability Mechanism (http://www.undp.org/secu-srm).

- The Implementing Partner shall: (a) conduct project and programme-related activities in a manner consistent with the UNDP Social and Environmental Standards, (b) implement any management or mitigation plan prepared for the project or programme to comply with such standards, and (c) engage in a constructive and timely manner to address any concerns and complaints raised through the Accountability Mechanism. UNDP will seek to ensure that communities and other project stakeholders are informed of and have access to the Accountability Mechanism.

- All signatories to the Project Document shall cooperate in good faith with any exercise to evaluate any programme or project-related commitments or compliance with the UNDP Social and Environmental Standards. This includes providing access to project sites, relevant personnel, information, and documentation.

- The Implementing Partner will take appropriate steps to prevent misuse of funds, fraud or corruption, by its officials, consultants, responsible parties, subcontractors and sub-recipients in implementing the project or using UNDP funds.  The Implementing Partner will ensure that its financial management, anti-corruption and anti-fraud policies are in place and enforced for all funding received from or through UNDP.

- The requirements of the following documents, then in force at the time of signature of the Project Document, apply to the Implementing Partner: (a) UNDP Policy on Fraud and other Corrupt Practices and (b) UNDP Office of Audit and Investigations Investigation Guidelines. The Implementing Partner agrees to the requirements of the above documents, which are an integral part of this Project Document and are available online at www.undp.org.

- In the event that an investigation is required, UNDP has the obligation to conduct investigations relating to any aspect of UNDP projects and programs. The Implementing Partner shall provide its full cooperation, including making available personnel, relevant documentation, and granting access to the Implementing Partner’s (and its consultants’, responsible parties’, subcontractors’ and sub-recipients’) premises, for such purposes at reasonable times and on reasonable conditions as may be required for the purpose of an investigation. Should there be a limitation in meeting this obligation, UNDP shall consult with the Implementing Partner to find a solution.

- The signatories to this Project Document will promptly inform one another in case of any incidence of inappropriate use of funds, or credible allegation of fraud or corruption with due confidentiality.

- Where the Implementing Partner becomes aware that a UNDP project or activity, in whole or in part, is the focus of investigation for alleged fraud/corruption, the Implementing Partner will inform the UNDP Resident Representative/Head of Office, who will promptly inform UNDP’s Office of Audit and Investigations (OAI). The Implementing Partner shall provide regular updates to the head of UNDP in the country and OAI of the status of, and actions relating to, such investigation.

- UNDP shall be entitled to a refund from the Implementing Partner of any funds provided that have been used inappropriately, including through fraud or corruption, or otherwise paid other than in accordance with the terms and conditions of the Project Document.  Such amount may be deducted by UNDP from any payment due to the Implementing Partner under this or any other agreement.

- Where such funds have not been refunded to UNDP, the Implementing Partner agrees that donors to UNDP (including the Government) whose funding is the source, in whole or in part, of the funds for the activities under this Project Document, may seek recourse to the Implementing Partner for the recovery of any funds determined by UNDP to have been used inappropriately, including through fraud or corruption, or otherwise paid other than in accordance with the terms and conditions of the Project Document.

- Note:  The term “Project Document” as used in this clause shall be deemed to include any relevant subsidiary agreement further to the Project Document, including those with responsible parties, subcontractors and sub-recipients.

- Each contract issued by the Implementing Partner in connection with this Project Document shall include a provision representing that no fees, gratuities, rebates, gifts, commissions or other payments, other than those shown in the proposal, have been given, received, or promised in connection with the selection process or in contract execution, and that the recipient of funds from the Implementing Partner shall cooperate with any and all investigations and post-payment audits.

- Should UNDP refer to the relevant national authorities for appropriate legal action any alleged wrongdoing relating to the project, the Government will ensure that the relevant national authorities shall actively investigate the same and take appropriate legal action against all individuals found to have participated in the wrongdoing, recover and return any recovered funds to UNDP.

- The Implementing Partner shall ensure that all of its obligations set forth under this section entitled “Risk Management” are passed on to each responsible party, subcontractor and sub-recipient and that all the clauses under this section entitled “Risk Management Standard Clauses” are included, mutatis mutandis, in all sub-contracts or sub-agreements entered into further to this Project Document.

# Mandatory Annexes

- Multi-year Workplan

- GEF Core Indicators at baseline

- Overview of technical consultancies/subcontracts

- Terms of Reference for Project Board, Project Coordinator, Chief Technical Advisor and other positions as appropriate (see example template below)

- UNDP Social and Environmental and Social Screening Template (SESP) and Environmental and Social Management Plan (ESMP) for moderate and high risk projects

- Stakeholder Engagement Plan, including list of people consulted during project development

- Gender Analysis and Action Plan

- UNDP Risk Log

- Results of the capacity assessment of the project implementing partner and HACT micro assessment (to be completed by UNDP Country Office)

- Letter of Agreement with the Government of Argentina and Description of UNDP Country Office Support Services.

- UNDP Project Quality Assurance Report (to be completed in UNDP online corporate planning system by UNDP Country Office, does not need to be attached as separate document)

- Project Target Landscapes and Maps

## Annex A:  Multi Year Work Plan

| Output | Responsible Party | Year 1 |  |  |  | Year 2 |  |  |  |  | Year 3 |  |  |  |  | Year 4 |  |  |  |  | Year 5 |  |  |  |  | Year 6 |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Q1 | Q2 | Q3 | Q4 |  | Q1 | Q2 | Q3 | Q4 |  | Q1 | Q2 | Q3 | Q4 |  | Q1 | Q2 | Q3 | Q4 |  | Q1 | Q2 | Q3 | Q4 |  | Q1 | Q2 | Q3 | Q4 |
| Output 1.1: Environmental information system updated and standardized to support the ELUP process & decision- making |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.1.1 Standardize and systematize data at national, provincial and local levels | SGAyDS |  | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |
| - Incorporate an ELUP sub-system to IDE Environment | SGAyDS |  | X | X | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Generate, consolidate, standardize information and metadata | SGAyDS |  | X | X | X |  | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Online availability of information | SGAyDS |  |  |  |  |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |
| 1.1.2 Define/ update indicators for ELUP | SGAyDS Provinces INTA |  | X | X | X |  | X | X | X | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.1.3 Participate in the IDERA Initiative for inter-institutional and inter-jurisdictional coordination | SGAyDS |  |  |  |  |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |
| - Receive positive feedback from IDERA members | SGAyDS |  |  |  |  |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |
| - Disseminate public information | SGAyDS |  |  |  |  |  |  |  |  |  |  |  |  | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |
| Output 1.2: Federal level ELUP criteria agreed-upon |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.2.1 Elaborate criteria to define ES valuation, BD conservation and SLM | SGAyDS |  | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |
| - Analyze mechanisms | SGAyDS INTA |  | X | X | X |  | X | X | X | X |  | X | X | X | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Stakeholder coordination workshops | SGAyDS Provinces INTA |  | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X |  |  |  |  |  |  |  |  |
| - Validate mechanisms with key stakeholders | SGAyDS Provinces INTA |  |  |  |  |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |  |  |  |  |  |
| - Elaborate criteria document | SGAyDS INTA |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | X | X | X | X |  | X | X | X | X |
| 1.2.2 Develop strategies to promote conservation and restoration areas with compensation schemes for ELUP | SGAyDS INTA |  | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |
| - Collect, analyze and identify compensation schemes | SGAyDS INTA |  | X | X | X |  | X | X | X | X |  | X | X | X | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Validate schemes through dialogue platforms | SGAyDS INTA |  |  |  |  |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |  |  |  |  |  |  |  |  |  |  |
| - Elaborate document with strategies | SGAyDS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | X | X | X | X |  | X | X | X | X |
| 1.2.3 Design management instruments for ELUP at national, provincial and local levels | SGAyDS INTA |  | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |
| - Harmonize ELUP regulations | SGAyDS |  | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |
| - Assessment of ELUP related regulations | SGAyDS |  | X | X | X |  | X | X | X | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Inter-sectoral coordination for mainstreaming ELUP into regulations | SGAyDS Provinces INTA |  | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |  |  |  |  |  |  |  |  |  |  |
| - Mainstream ELUP in at least 4 existing financial instruments | SGAyDS Provinces INTA |  |  |  |  |  |  |  | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |
| - Proposal for ELUP legal framework | SGAyDS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |
| - Methodological guides for ELUP | SGAyDS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | X |  | X | X | X | X |  | X | X | X | X |
| Output 1.3: Standardized instruments for implementing ELUP for targeted sectors |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.3.1 Elaborate criteria for priority areas for ELUP | SGAyDS |  | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |  |  |  |  |  |
| - Define criteria | SGAyDS Provinces INTA |  | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |  |  |  |  |  |  |  |  |  |  |
| - Define main territorial problems | SGAyDS Provinces INTA |  | X | X | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Categorize problems | SGAyDS Provinces INTA |  |  |  |  |  | X | X | X | X |  | X | X | X | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Identify ELUP instruments for different problems | SGAyDS Provinces INTA |  |  |  |  |  |  |  |  |  |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |  |  |  |  |  |
| 1.3.2 Elaborate and validate maps of priority areas of environmental value for ELUP | SGAyDS |  | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |  |  |  |  |  |  |  |  |  |  |
| - Identify priority areas for ELUP based on criteria | SGAyDS |  | X | X | X |  | X | X | X | X |  | X | X | X | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Analyze NNRR evaluation systems thru satellite imagery | SGAyDS |  | X | X | X |  | X | X | X | X |  | X | X | X | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Elaborate and validate maps of priority areas | SGAyDS |  |  |  |  |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |  |  |  |  |  |  |  |  |  |  |
| - Adjust maps | SGAyDS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | X | X |  |  |  |  |  |  |  |  |  |  |
| 1.3.3 Develop criteria for production best practices in priority areas for BD and ES conservation | SGAyDS INTA |  | X | X | X |  | X | X | X | X |  | X | X | X | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.3.4 Develop protocol to establish protected areas as basis for ELUP | SGAyDS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |
| Output 1.4 Inter-sectoral and inter jurisdictional co-ordination mechanisms |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.4.1 Inter-institutional and inter-sectoral dialogue spaces | SGAyDS Provinces INTA |  | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |
| - Update stakeholder mapping | SGAyDS |  | X | X | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Develop detailed Indigenous Peoples Plan | SGAyDS |  | X | X | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Establish inter-institutional working agreements for multi-stakeholder dialogue | SGAyDS |  | X | X | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Establish multi-stakeholder dialogue spaces | SGAyDS Provinces INTA |  | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |  |  |  |  |  |  |  |  |  |  |
| - Functioning of spaces with work plans and budget | SGAyDS Provinces INTA |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | X | X | X | X |  | X | X | X | X |
| - Design and implement a communication program for ELUP | SGAyDS |  | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |
| - Design and implement a capacity development program for ELUP and participation | SGAyDS |  | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |
| Output 2.1. Provincial Regulatory Framework for ELUP strengthened |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Buenos Aires |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.1.1 Develop provincial regulations for ELUP | OPDS |  | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |
| - Elaborate proposal for regulating the provincial environment law (Law Nº11723) | OPDS |  | X | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.1.2 Define and implement guidelines for design of initiatives by targeted sectors | OPDS |  | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |
| 2.1.3 Establish two observatories | OPDS |  |  |  |  |  |  |  |  |  |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |
| Jujuy |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.1.1 Develop guidelines for strategic planning of pilot site 1 corridor | Ministry of Environment |  | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.1.2 Design schematic plan for the GIRSU | Ministry of Environment |  | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Define implementation schemes | Ministry of Environment |  | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Upscale to other municipalities | Ministry of Environment |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |
| 2.1.3 Design Susques-Catua tourism corridor | Ministry of Environment |  | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |
| 2.1.4 Develop Management Plan for Olaroz-Cauchari-Catua Reserve | Ministry of Environment |  | X | X | X |  | X | X | X | X |  | X | X | X | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Assess enforcement of Law 6080 | Ministry of Environment |  | X | X | X |  | X | X | X | X |  | X | X | X | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Develop proposal for management plan | Ministry of Environment |  | X | X | X |  | X | X | X | X |  | X | X | X | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Implementation of the management plan | Ministry of Environment |  |  |  |  |  |  | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |
| Mendoza |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.1.1 Develop regulations for piedmont areas | SAOT |  | X | X | X |  | X | X | X | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Define land use criteria | SAOT |  | X | X | X |  | X | X | X | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Develop and implement regulations |  |  |  |  |  |  |  |  |  |  |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |
| 2.1.2 Strengthen legal framework for EIA agricultural projects | SAOT |  | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |
| - Assess implementation of Law 6045 and Law 4902 | SAOT |  | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |
| 2.1.3 Develop instruments for PAs | SAOT |  | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |
| - Develop a best practice manual for tourism in PAs | SAOT |  |  |  |  |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |
| - Assess and design instruments to promote private protected areas | SAOT |  | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |  |  |  |  |  |  |  |  |  |  |
| - Design the network of protected natural spaces | SAOT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |
| - Develop an integrated plan for public use infrastructure in Pas | SAOT |  |  |  |  |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |
| - Develop a capacity strengthening plan for the network of protected natural spaces | SAOT |  |  |  |  |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |
| 2.1.4 Develop instruments for Green Belt target landscape | SAOT |  | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |
| - Develop regulations for SLM, BD and ES | SAOT |  | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |
| - Generate baseline information for zoning of rural and rural-urban areas for municipal ELUP plans | SAOT |  | X | X | X |  | X | X | X | X |  | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 2.2 Provincial Governance Framework for participatory ELUP & sector consensus building |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Buenos Aires, Jujuy, Mendoza |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.2.1 Inter-institutional and inter-sectoral dialogue spaces | OPDS Ministry Environment SAOT |  | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |
| - Update stakeholder mapping | OPDS Ministry Environment SAOT |  | X | X | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Establish inter-institutional working agreements for multi-stakeholder dialogue | OPDS Ministry Environment SAOT |  | X | X | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Establish multi-stakeholder dialogue spaces | OPDS Ministry Environment SAOT |  | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |  |  |  |  |  |  |  |  |  |  |
| - Functioning of platform with work plans and budget | OPDS Ministry Environment SAOT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | X | X | X | X |  | X | X | X | X |
| - Design and implement a communication program for ELUP | OPDS Ministry Environment SAOT |  | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |
| - Design and implement a capacity development program for ELUP and participation | OPDS Ministry Environment SAOT |  | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |
| Buenos Aires |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.2.2 Establish a Sustainable Commodities Platform (beef) | OPDS |  | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |
| - Update stakeholder mapping | OPDS |  | X | X | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Convene meetings and facilitate dialogue | OPDS |  |  |  |  |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |
| - Assess root causes | OPDS |  |  |  |  |  |  |  |  |  |  | X | X | X | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Develop action plan | OPDS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | X | X | X | X |  |  |  |  |  |  |  |  |  |  |
| - Partnerships to promote sustainable beef |  |  |  |  |  |  |  |  |  |  |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |
| Output 2.3. Set of instruments validated in pilot landscapes for defining and implementing ELUP |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Buenos Aires |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.3.1 Valuation of ES | OPDS | X | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |
| - Assess ECOSER and multi-criteria analysis and select methodology | OPDS |  | X | X | X |  | X | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Generate baseline information for ES valuation methodology | OPDS |  | X | X | X |  | X | X | X | X |  | X | X | X | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - ES quantification and valuation | OPDS |  |  |  |  |  |  |  |  |  |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |
| 2.3.2 Promote economic, financial and fiscal incentives | OPDS |  |  |  |  |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |
| - Promote access of landowners to Native Forest Laws compensations | OPDS |  |  |  |  |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |
| - Assess national funding programs for promoting BD and SLM practices and test/validate in target landscapes | OPDS |  |  |  |  |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |
| - Develop and test compensation schemes | OPDS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |
| 2.3.3 Develop and implement ELUP protocols | OPDS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |
| Jujuy |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.3.1 Develop ELUP protocols | Ministry of Environment |  | X | X | X |  | X | X | X | X |  | X | X | X | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Risk studies in Valle Grande | Ministry of Environment |  | X | X | X |  | X | X | X | X |  | X | X | X | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Generate inputs for ELUP protocols | Ministry of Environment |  | X | X | X |  | X | X | X | X |  | X | X | X | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Design and adapt economic, fiscal and financial instruments | Ministry of Environment |  |  |  |  |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |  |  |  |  |  |
| - Implement instruments, monitor and adjust | Ministry of Environment INTA |  |  |  |  |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |
| 2.3.2 ES valuation in target landscapes | Ministry of Environment INTA |  | X | X | X |  | X | X | X | X |  | X | X | X | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.3.3 Develop compensation schemes (TSA, government funding) | Ministry of Environment |  |  |  |  |  |  |  |  |  |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |
| - Assess methodologies, funding options | Ministry of Environment INTA |  | X | X | X |  | X | X | X | X |  | X | X | X | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Adapt instruments to local realities and needs | Ministry of Environment INTA |  |  |  |  |  |  |  | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |
| - Implement schemes | Ministry of Environment INTA |  |  |  |  |  |  |  | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |
| Mendoza |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Valuate ecosystem goods and services | SAOT INTA |  | X | X | X |  | X | X | X | X |  | X | X | X | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Implement the ECOSER methodology in Green Belt target landscape | SAOT INTA |  | X | X | X |  | X | X | X | X |  | X | X | X | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Assess ES valuation and land use criteria in Uco Valley | SAOT INTA |  | X | X | X |  | X | X | X | X |  | X | X | X | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Valuate ES in protected areas of Piedmont target landscape | SAOT INTA |  | X | X | X |  | X | X | X | X |  | X | X | X | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Design and implement compensation schemes for PES | SAOT INTA |  |  |  |  |  |  |  |  |  |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |
| 2.3.2 Promote economic, financial and fiscal incentives and regulations | SAOT |  |  | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |
| - Assess funding options for tourism and PAs in Piedmont target landscape | SAOT |  |  | X | X |  | X | X | X | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - EIA procedures for agriculture in Uco Valley | SAOT INTA |  |  | X | X |  | X | X | X | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Develop regulations for ELUP restrictions in Green Belt | SAOT INTA |  |  | X | X |  | X | X | X | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Assess national programs in Malargue | SAOT INTA |  |  | X | X |  | X | X | X | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Implement ELUP regulations and economic instruments | SAOT |  |  |  |  |  |  |  |  |  |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |
| 2.3.3 Develop an integrated plan for conservation of BD and landscapes | INTA |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |
| Output 2.4 SLM and biodiversity-friendly production practices validated for different ELUP land use zones |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Buenos Aires |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.4.1 Validate sustainable practices for agro-industrial crops, soy | INTA |  | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |
| - Analysis and studies in agro-ecological farms | INTA |  | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |
| 2.4.2 Sustainable livestock practices in sensitive areas | INTA |  | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |
| - Develop silvo-pastoral systems in Delta | INTA |  | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |
| 2.4.3 Zoning of priority wetlands and coastal habitats | OPDS |  |  |  |  |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X |  |  |  |  |  |  |  |  |
| 2.4.4 Sustainable agro-ecological practices in transition areas | INTA |  | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |
| 2.4.5 Sustainable livestock practices in Espinal | INTA |  | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |
| 2.4.5 Recovery of degraded agricultural soils | INTA |  | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |
| 2.4.6 Recovery of native grasslands | INTA |  | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |
| Jujuy |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.4.1 Establish a Tourism Information System for San Francisco-Hornocal | Ministry of Environment |  | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |
| - Design, validate | Ministry of Environment |  | X | X | X |  | X | X | X | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Implement System with ELUP module and user module | Ministry of Environment |  |  |  |  |  |  |  |  |  |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |
| - Replicate to Quebrada Puna | Ministry of Environment |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | X | X | X | X |  | X | X | X | X |
| 2.4.2 Strengthen Tourism Development Plan of Qhapac Ñam and Jordan River hot springs | Ministry of Environment |  | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |
| - Promote regional activities and products | Ministry of Environment |  | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |
| - Disseminate sustainable tourism practices | Ministry of Environment |  | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |
| 2.4.3 BD/forests | Ministry of Environment |  | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |
| - Develop management plan for Queñoa and Churca | Ministry of Environment |  | X | X | X |  | X | X | X | X |  | X | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Develop management plan for fauna | Ministry of Environment |  | X | X | X |  | X | X | X | X |  | X | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Implement sustainable management practices | Ministry of Environment |  |  |  |  |  |  |  |  |  |  |  |  | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |
| 2.4.4 Sustainable production practices (cattle, sheep, camelids) | Ministry of Environment |  | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |
| - Assess practices and synergies with other projects | Ministry of Environment |  | X | X | X |  | X | X | X | X |  | X | X | X | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Implement practices | Ministry of Environment |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |
| 2.4.5 Environment friendly agricultural practices with family agriculture | Ministry of Environment |  | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |
| - Assess practices and synergies with other projects | Ministry of Environment |  | X | X | X |  | X | X | X | X |  | X | X | X | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Implement practices | Ministry of Environment |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |
| 2.4.6 Promote sustainable management of non-timber products | Ministry of Environment |  | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |
| - Assess practices and synergies with other projects | Ministry of Environment |  | X | X | X |  | X | X | X | X |  | X | X | X | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Implement practices | Ministry of Environment |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |
| 2.4.7 Promote renewable energy in target landscape 2 | Ministry of Environment |  | X | X | X |  | X | X | X | X |  | X | X | X | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Mendoza |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.4.1 Develop sustainable production practices in non-irrigated areas | SAOT INTA |  | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |
| 2.4.2 Strengthen forest management plans | SAOT INTA |  | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |
| 2.4.3 Develop sustainable best practice criteria and guidelines | SAOT INTA |  | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |
| - Design and redesign of agroecosystems | SAOT INTA |  | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |
| - Soil conservation management in oasis-piedmont interface | SAOT INTA |  | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |  |  |  |  |  |
| - BD connectivity in agroecosystems | SAOT INTA |  | X | X | X |  | X | X | X | X |  | X | X | X | X |  |  |  |  |  |  |  |  |  | X |  | X |  |  |  |
| - Promotion of functional BD in agroecosystems | SAOT INTA |  |  |  |  |  |  |  |  |  |  |  |  |  | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |
| 2.4.4 Sustainable production of goats | SAOT INTA |  |  |  |  |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |
| Output 3.1 Nationwide ELUP experiences and related instruments evaluated as an input to determine the best mix of instruments for different productive sectors and ecoregions |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.1.1 Assessment of instruments, plans, programs and projects for BD, LD, SLM, ELUP in non-pilot provinces | SGAyDS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |
| 3.1.2 Consultation and validation of assessments with non-pilot provinces | SGAyDS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |
| 3.1.3 Systematization of information and results | SGAyDS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |
| Output 3.2. Nationwide ELUP Capacity Strengthening Programme for Provincial Authorities |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.2.1 Develop a capacity strengthening program | SGAyDS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |
| 3.2.2 Develop methodological guides for upscaling ELUP | SGAyDS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |
| Output 3.3. System to Monitor ELUP implementation nationwide established |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.3.1 Inter-sectoral coordination at different levels for planning, monitoring and mainstreaming ELUP in national programs | SGAYDS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |
| 3.3.2 Design and implement SEM-OAT | SGAyDS Provinces INTA |  |  |  |  |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |
| Output 4.1: Project M&E system operational and generating periodic report |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 4.1.1 Project M&E System | PMU SGAyDS |  | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |
| Output 4.2: Knowledge management system set up to disseminate good practices and lessons learned |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 4.2.1 Information and communication program | PMU, SGAyDS |  | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |

## Annex B:  Core Indicators  at baseline

Core Indicator 3: Area of land restored (hectares)

| Ha (expected at PIF) | Ha (expected at CEO Endorsement) | Ha (achieved at MTR) | Ha (achieved at TE) |
| --- | --- | --- | --- |
| N/A | 128,370 |  |  |

Figure at a given stage must be the sum of all figures reported under the four sub-indicators (3.1, 3.2, 3.3 and 3.4) for that stage.

3.1 Area of degraded agricultural lands restored

| Ha (expected at PIF) | Ha (expected at CEO Endorsement) | Ha (achieved at MTR) | Ha (achieved at TE) |
| --- | --- | --- | --- |
| N/A | 97,868 |  |  |

3.2 Area of forest and forest land restored

(values are for both)

| Ha (expected at PIF) | Ha (expected at CEO Endorsement) | Ha (achieved at MTR) | Ha (achieved at TE) |
| --- | --- | --- | --- |
| N/A | 30,502 |  |  |

3.3 Area of natural grass and shrublands restored

| Ha (expected at PIF) | Ha (expected at CEO Endorsement) | Ha (achieved at MTR) | Ha (achieved at TE) |
| --- | --- | --- | --- |
| N/A | N/A |  |  |

3.4 Area of wetlands (including estuaries and mangroves) restored

| Ha (expected at PIF) | Ha (expected at CEO Endorsement) | Ha (achieved at MTR) | Ha (achieved at TE) |
| --- | --- | --- | --- |
| N/A | N/A |  |  |

Core Indicator 4: Area of landscapes under improved practices (hectares; excluding protected areas)

| Ha (expected at PIF) | Ha (expected at CEO Endorsement) | Ha (achieved at MTR) | Ha (achieved at TE) |
| --- | --- | --- | --- |
| 723,677 | 613,128 |  |  |

Figure at a given stage must be the sum of all figures reported under the four sub-indicators (4.1, 4.2, 4.3 and 4.4) for that stage.

4.1 Area of landscapes under improved management to benefit biodiversity (qualitative assessment, noncertified)

| Ha (expected at PIF) | Qualitative description at PIF | Ha (expected at CEO Endorsement) | Qualitative description at CEO ER | Ha (achieved at MTR) | Qualitative description at MTR | Ha (achieved at TE) | Qualitative description at TE |
| --- | --- | --- | --- | --- | --- | --- | --- |
| N/A | N/A | 240,644 | Espinal ecoregion: reduced pressures on relict populations of endangered species e.g. Pampas deer - Ozotoceros bezoarticus High Andes: conservation of wetlands, pressures reduced on bird species and wild fauna e.g guanaco Lama guanicoe Puna: conservation of wetlands, benefits to congregatory species e.g. Andean flamingo - Phoenicoparrus andinus and other flamingo species High Monte: reduced fires and pressure over wild fauna e.g. puma - Puma concolor- Low Monte: pressures reduced on shrubs and steppes and their related fauna e.g. Andean fox Lycalopex culpaeus Yungas Forest: reduced deforestation and degradation will benefit important tree species e.g. palo blanco Calycophyllum multiflorum, and endangered fauna e.g. jaguar Panthera onca Patagonian Steppe: reduced vegetation loss from overgrazing will benefit threatened species eg. macá tobiano Podiceps gallardo Parana Delta: reduced pressure of urban expansion on wetland benefits and wild fauna e.g. Marsh Deer -Blastocerus dichotomus Pampas: reduced pressure on VGAs and benefits to threatened species e.g. the endangered species Pampas Meadowlark -Sturnella defilippii-) |  |  |  |  |

Add rows as needed.

4.2 Area of landscapes that meet national or international third-party certification and that incorporates biodiversity considerations

| Ha (expected at PIF) | Type of Certification at PIF | Ha (expected at CEO Endorsement) | Type of Certification at CEO ER | Ha (achieved at MTR) | Type of Certification at MTR | Ha (achieved at TE) | Type of Certification at TE |
| --- | --- | --- | --- | --- | --- | --- | --- |
| N/A | N/A | N/A | N/A |  |  |  |  |

Add rows as needed.

4.3 Area of landscapes under sustainable land management in production systems

| Ha (expected at PIF) | Description of Management Practices at PIF | Ha (expected at CEO Endorsement) | Description of Management Practices at CEO ER | Ha (achieved at MTR) | Description of Management Practices at MTR | Ha (achieved at TE) | Description of Management Practices at TE |
| --- | --- | --- | --- | --- | --- | --- | --- |
| N/A | N/A | 372,484 | Agriculture & Livestock sector: - Conservation agriculture/ agro-ecological practices - Monitoring of status of natural grasslands in cattle ranches. - Management of herd stocks and grazing (e.g. carrying capacity, paddock rotation - Optimum grazing height in grasslands for conservation of soil and grassland - Silvo-pastoral schemes, tree barriers - Sustainable intensification of traditional goat rearing Peri-urban infrastructure sector: - Zoning of priority wetlands and coastal habitats - Restrictions to urban expansion - Solid waste management - Management of water and drains in the areas of water table outcrops for recovery of wetlands and optimizing productive uses - Systems to reuse water for production in areas with restrictions Mining sector: - Public-private partnerships for sustainable productive development of communities living in the area of influence of mining Tourism sector: - Tourism Development Plans - Best practice manual for ecotourism in protected areas: evaluate carrying capacity, trail design, incorporating locals as guides - Design of tourist corridors |  |  |  |  |

Add rows as needed.

4.4 Area of High Conservation Value forest loss avoided

| Total Ha (expected at PIF) | Total Ha (expected at CEO Endorsement) | Total Ha (achieved at MTR) | Total Ha (achieved at TE) |
| --- | --- | --- | --- |
| N/A | N/A |  |  |

Figure at a given stage must be the sum of all individual PAs reported in the next table, for that stage. Prepare and upload file that justifies the HCVF.

| Name of HCVF | Ha (expected at PIF) | Counterfactual at PIF | Ha (expected at CEO Endorsement) | Counterfactual at CEO ER | Ha (achieved at MTR) | Ha (achieved at TE) |
| --- | --- | --- | --- | --- | --- | --- |
| N/A | N/A | N/A | N/A |  |  |  |

Add rows as needed.

Core Indicator 11: Number of direct beneficiaries disaggregated by gender as co-benefit of GEF investment

|  | Total number (expected at PIF) | Total number (expected at CEO Endorsement) | Total number (achieved at MTR) | Total number (achieved at TE) |
| --- | --- | --- | --- | --- |
| Women | N/A | 4,665 |  |  |
| Men | N/A | 7,000 |  |  |
| Total | N/A | 11,665 |  |  |

## Annex C:  Overview of Technical Consultancies

| Consultant | Time Input | Tasks, Inputs and Outputs |
| --- | --- | --- |
| For Project Management / Monitoring & Evaluation |  |  |
| Local / National contracting |  |  |
| Project Coordinator Rate: USD 2,002/month | 72 months | The Project Coordinator (PC) will be responsible for the overall management of the project, including the mobilization of all project inputs, supervision of project staff, consultants and sub-contractors. The PC will also act as the project´s specialist on Environmental Land Use Planning with the support of a team of ELUP technicians of the SGAyDS. See the full TORs below for details. |
| For Technical Assistance |  |  |
| Local / National contracting |  |  |
| Specialist for definition of criteria for priority areas of environmental value Rate: USD 1,000/month | 48 months | Under close supervision of the Project Coordinator the consultant will work closely with the SGAyDS technical team and key stakeholders to identify, assess, prioritize and validate criteria for priority areas of environmental value for ELUP implementation under Output 1.3, which will serve as the basis for the elaboration of maps of such priority areas. The specialist will: - Research criteria that can be used to define priority areas of environmental value for ELUP. - Identify a list of basic and auxiliary criteria that could be used to define priority areas. - Assess each criteria and propose a set of pertinent criteria. - Facilitate at different stages of the process workshops and meetings with scientific committees, experts and national/provincial technicians to discuss the criteria and methodology to assess them, obtain inputs and suggestions, and validate the final set of criteria. - Elaborate a document containing the final set of criteria and the methodology to guide the application of the criteria in mapping the priority areas. Specific TORs will be prepared during project implementation. |
| Information Systems Specialist Rate: USD 1,000/month | 72 months | Under the overall supervision of the Project Coordinator, and in coordination with the Implementing Partner and other project partners, the Information Systems Specialist will coordinate and provide technical advice for the implementation of activities under Outputs 1.1 and 3.3, including the following: - Support the development of the information system for analysis of environmental variables, including systematization and standardization of information; establishing the ELUP module in the IDE Ambiente data base. - Training of national and provincial technicians in information sharing and standardization protocols. - Support defining indicators for ELUP. - Support the development of maps of priority areas of environmental value for ELUP implementation. - Support the design and development of the system for evaluation and monitoring of ELUP implementation - Prepare a proposal for the financial sustainability plan of the system. See TORs below for details. |
| Economic and Financial Instruments Specialist Rate: USD 1,000/month | 72 months | Under the overall supervision of the Project Coordinator, and in coordination with the Implementing Partner and other project partners, the Economic and Financial Instruments Specialist will coordinate and provide technical advice for the implementation of activities under Outputs 1.2, 1.3, 2.3 and 3.1, including the following: - Support the assessment, development and participatory validation of SLM, BD conservation and ecosystem services valuation criteria/methodologies for defining different land use zones and production practices restrictions; - Support the assessment, development and participatory validation of compensation schemes; - Coordinate mainstreaming of ELUP criteria in sector planning and finance frameworks working with national programs and private sector banks. - Support development and participatory validation of eligibility criteria and standards for accessing economic instruments for production practices in restricted use areas that are a priority for BD & ES conservation. - Provide guidance and advice to provincial governments of the pilot provinces in the assessment and testing of economic and financial instruments in the provinces. - Support assessing lessons/experiences from ongoing and past projects as well as economic, financial and fiscal incentives, valuation of ecosystem services and compensations schemes in non-pilot provinces. See TORs below for details. |
| Stakeholder Engagement Specialist Rate: USD 1,000/month | 72 months | Under the overall supervision of the Project Coordinator, and in coordination with the Implementing Partner and other project partners, the Stakeholder Engagement Specialist will be responsible for strategically organizing and strengthening consultation and stakeholder engagement within the framework of the Project´s Stakeholder Engagement Plan, including the following: - Undertake national and provincial stakeholder mapping to further identify key stakeholders. - Develop the detailed Indigenous Peoples Plan. - Coordinate the design and implementation of national and provincial multi-stakeholder dialogue and coordination spaces. - Develop capacity building programs for national level strengthening; - Implement social safeguards, particularly in regard to participation of indigenous peoples, and ensure their application - Promote stakeholder participation, particularly women and indigenous peoples, in project interventions; - Support the SGAyDS´s Communication Specialist in preparing communication materials and messages to encourage stakeholder engagement. - Support the Project Coordinator in coordinating collection of M&E data with regard to stakeholder participation, including sex-disaggregated data; synthesizing lessons on best practices and knowledge on stakeholder engagement and preparing related publications. - Oversee the implementation of field assessments to measure project progress, including a livelihood assessment; a knowledge, aptitude and practice survey; and other surveys that may needed. See TORs below for details. |
| Gender Specialist Rate: USD 1,000/month | 72 months | Under the overall supervision and guidance of the Project Coordinator, the Gender Specialist will have the responsibility for the implementation of the Gender Action Plan. Specific responsibilities will include: - Monitor progress in implementation of the project Gender Action Plan ensuring that targets are fully met and the reporting requirements are fulfilled. - Oversee/develop/coordinate implementation of all gender-related work. - Establish collaborations with gender-related national and provincial institutions to promote their participation in project activities. - Review the Gender Action Plan annually, and update and revise corresponding management plans as necessary. - Support the Project Coordinator to ensure that reporting, monitoring and evaluation fully address the gender issues of the project and feed into the project´s communication and information program - Support the Project Coordinator collecting gender related M&E data; in synthesizing lessons on gender mainstreaming best practices and knowledge on and preparing related publications. See TORs below for details. |
| Provincial Technicians (3) Rate: USD 1,126/month | 72 months | Under the overall supervision of the Project Coordinator, and in coordination with the Implementing Partner, Provincial Governments of Buenos Aires, Jujuy and Mendoza, and project specialists, the Provincial Technicians will be responsible for providing technical support, coordination, oversight and monitoring and evaluation for the adequate implementation of project activities in each province, including: - Support the Project Coordinator in supervising and coordinating the production of project outputs. - Provide support in coordinating all project inputs. - Support the implementation of stakeholder engagement mechanisms in coordination with the stakeholder engagement specialist. - Support the implementation of gender mainstreaming in project activities in coordination with the gender specialist. - Support the dissemination of information on the project. - Support project M&E - Liaise and follow up with the responsible parties for implementation of project activities in the target landscapes of each province and promote and maintain partnerships with relevant provincial agencies and institutions. See TORs below for details. |
| Mid-term Review Expert Rate: USD 1,000/week | 6 weeks | The local Mid-term Review Expert will support the International MTR Expert in assessing progress towards the achievement of the project objectives and outcomes as specified in the Project Document, and assessing early signs of project success or failure with the goal of identifying the necessary changes to be made in order to set the project on track to achieve its intended results; as well as the project’s strategy, its risks to sustainability. |
| Terminal Evaluation Expert Rate: USD 1,000/week | 6 weeks | The local Terminal Evaluation expert will support the International TE Expert in the evaluation of the project to assess the achievement of project results, and to draw lessons that can both improve the sustainability of benefits from this project, and aid in the overall enhancement of UNDP programming. |
| International / Regional and global contracting |  |  |
| Mid-term Review Expert Rate: USD 2,500/week | 6 weeks | The Mid-term Review Expert will assess progress towards the achievement of the project objectives and outcomes as specified in the Project Document, and assess early signs of project success or failure with the goal of identifying the necessary changes to be made in order to set the project on-track to achieve its intended results. The MTR will also review the project’s strategy, and the risks to sustainability, among other elements. |
| Terminal Evaluation Expert Rate: USD 3,000/week | 6 weeks | The Terminal Evaluation expert will undertake an evaluation of the project to assess the achievement of project results, and to draw lessons that can both improve the sustainability of benefits from this project, and aid in the overall enhancement of UNDP programming. |

.

## Annex D: Terms of Reference

Terms of Reference for the Project Board

The Project Board (PB) will serve as the project’s decision-making body. It will meet according to necessity, at least once each year, to review project progress, approve project work plans and approve major project deliverables. The PB is responsible for providing strategic guidance and oversight to project implementation to ensure that it meets the requirements of the approved Project Document and achieves the stated outcomes. The PB’s role will include:

- Provide strategic guidance to support project implementation;

- Ensure coordination between various donor- funded and government- funded projects and programs;

- Ensure coordination with various government agencies and their participation in project activities;

- Approve annual project work plans and budgets, as  proposed by the Project Manager;

- Approve any major changes in project plans or programs;

- Oversee monitoring, evaluation and reporting in line with GEF requirements;

- Ensure commitment of human resources to support project implementation, arbitrating any issues within the project;

- Negotiate solutions between the project and any parties beyond the scope of the project;

- Ensure that UNDP Social and Environmental Safeguards Policy is applied throughout project implementation; and, address related grievances as necessary.

These terms of reference will be finalized during the Project Inception Workshop.

Terms of Reference for the Project Technical Committee (PTC)

The PTC will provide technical advice and inputs relating to project implementation and will be chaired by the Project National Director with support from the Project Coordinator.  The members of the PTC will consist of representatives of SGAyDS, UNDP, provincial governments of Buenos Aires, Mendoza and Jujuy, INTA, other relevant government agencies, research and educational organizations, NGOs, technical experts and other relevant stakeholders to be agreed by the Project Board. Technical experts may be invited in to discuss specific issues. Indicative Terms of Reference are as follows:

- Review planned activities and ensure that they are technically sound and that, wherever possible, there is integration and synergy between the various project components during planning and implementation;

- Promote technical coordination between institutions, where such coordination is necessary and where opportunities for synergy and sharing of lessons exist;

- Provide technical advice and guidance on specific issues related to environmental land use planning;

- Share information on project progress and lessons learned with related stakeholders at the national level;

- The PTC or a subset of its members may be requested to undertake specific project-related tasks, such as preparing or reviewing analytical reports, strategies and action plans, etc.;

- Other tasks as indicated by the Project Board

These terms of reference will be reviewed by the Project Board during project inception and may be extended as necessary.

Terms of Reference of Key Project Staff

Project Coordinator

The Project Coordinator (PC) will act as the head of the Project Management Unit (PMU) and will be responsible for overall project implementation and supervision of the PMU. The PC will be locally recruited following UNDP procedures, with inputs into the selection process from the Project partners. The position will be appointed by the project implementing agencies and funded entirely from the Project. The PC will be responsible for the overall management of the Project, including the mobilization of all project inputs, and supervision of project staff, consultants and sub-contractors. The PC will report to the Project National Director in close consultation with the assigned UNDP Programme Manager for all of the Project’s substantive and administrative issues.

The PC will work closely with the Institutions represented on the Project Board, the Technical Committee and key stakeholders. The PC will report on a periodic basis to the Project Board, based on the Project National Director´s instruction. Generally, the PC will support the Project National Director who will be responsible for meeting government obligations under the Project, under the NIM execution modality. The PC will perform a liaison role with the government, UNDP and other GEF agencies, CSOs and project partners, and maintain close collaboration with other institutions providing co-financing.  The PC will also act as the project´s ELUP specialist coordinating and providing technical advice to implement the ELUP approach.

Duties and Responsibilities

- Provide overall project coordination and M&E for the achievement of the Project outcomes and objectives, based on Results-Based-Management.

- Coordinate work with UNDP offices and programs to ensure the alignment of the project results with UNDP´s Strategic Plan and the Country Programme Document and Gender Strategy.

- Establish the PMU internal working procedures and coordination mechanisms with UNDP, the Project Board, the Technical Committee and other key stakeholders.

- Prepare the annual workplans and budgets and submit them for approval by the Project Board.

- Plan the activities of the project and monitor progress against the approved workplan.

- Supervise and coordinate the production of project outputs, as per the Project Document in a timely and high- quality fashion.

- Coordinate all project inputs and ensure that they adhere to UNDP procedures for nationally executed projects.

- Ensure project expenditures and procurement respond to the principle of transparency and best value for money, and are in accordance with the activities established in the Project Document and plans.

- Supervise and coordinate the work of all project staff, consultants and sub-contractors, ensuring timing and quality of outputs.

- Coordinate the recruitment and selection of project personnel, consultants and sub-contracts, including drafting terms of reference and work specifications and overseeing all contractors’ work.

- Manage requests for the provision of financial resources by UNDP, through advance of funds, direct payments, or reimbursement using the UNDP provided format.

- Monitor financial resources and accounting to ensure accuracy and reliability of financial reports, submitted on a quarterly basis.

- Manage and monitor the project risks initially identified and submit new risks to the project board for consideration and decision on possible actions if required; update the status of these risks by maintaining the project risk log.

- Liaise with UNDP, Project Board, relevant government agencies, and all project partners, including co-financing organizations and CSOs for effective coordination of all project activities.

- Oversee and ensure timely submission of the Inception Report, Project Implementation Reports, technical reports as needed, quarterly financial reports, and other reports as may be required by UNDP, GEF and other oversight agencies.

- Disseminate project reports and respond to queries from concerned stakeholders.

- Report progress of project to project partners and ensure the fulfilment of Project Board directives.

- Oversee the exchange and sharing of experiences and lessons learned with relevant related projects nationally and internationally.

- Ensure a gender approach is maintained in all activities, including specific activities, aligned with UNDP´s Gender Strategy. Encourage staff, partners and consultants such that strategic, intentional and demonstrable efforts are made to actively include women in the project, including activity design and planning, budgeting, staff and consultant hiring, subcontracting, purchasing, outreach to project partners, training, participation in meetings; and access to project benefits, among others.

- Assist and advise the project partners responsible for activity implementation in the target landscapes.

- Undertake meetings and visits to the project stakeholders at national, provincial and local levels as part of the overall supervision of project implementation and prepare visit reports.

- Represent the project in national and international fora.

- Prepare, together with UNDP, the justification for any proposed changes in budgets, activities and objectives that differ from the original ProDoc and plans.

- Coordinate and provide technical advice to the Implementing Partner and project partners on the ELUP approach, including the development of ELUP criteria; assessment of ELUP instruments; development of maps of priority areas of environmental value for ELUP; analysis of ELUP regulations; assessment of valuation methodologies for environmental services; assessment of experiences and lessons learned from ongoing and past projects; facilitating dialogue and coordination with non-pilot provinces to initiate ELUP; and elaboration of methodological guides for ELUP.

Required skills and expertise

- Graduate degree – MSc is desirable - in a relevant field such as natural resource management, environmental science or studies, or environmental land use planning

- At least 10 years of experience in land use planning, natural resource management and/or environmental management.

- At least 5 years of demonstrable project/program management experience.

- At least 5 years of experience working with ministries, national or provincial institutions or NGOs that are concerned with natural resource and/or environmental management.

Competencies

- Strong leadership, managerial and coordination skills, with a demonstrated ability to effectively coordinate the implementation of large multi-stakeholder projects, including financial and technical aspects.

- Ability to effectively manage technical and administrative teams, work with a wide range of stakeholders across various sectors and at all levels, to develop durable partnerships with collaborating agencies.

- Ability to administer budgets, train and work effectively with counterpart staff at all levels and with all groups involved in the project.

- Ability to coordinate and supervise implementation of technical activities in partnership with a variety of national and provincial stakeholder groups, including government, community, private sector, CSOs.

- Strong drafting, presentation and reporting skills.

- Strong communication skills, including timely and accurate responses to emails.

- Strong computer skills, in particular mastery of all applications of the MS Office package and internet searches.

- Knowledge of productive sectors and environmental land use planning in Argentina.

- Excellent verbal and writing communication skills in Spanish.

- Working knowledge of English is mandatory.

Administrative Assistant

The Administrative Assistant will provide support to the Project Coordinator in management and administration of the project.  Under the supervision of the Project Coordinator, and in coordination with UNDP and the Implementing Partner, the Administrative Assistant will have the following specific responsibilities:

Duties and Responsibilities

- Undertake low complexity tasks with the purpose of contributing to the achievement of the planned results.

- Participate in situation analyses and diagnoses.

- Support the Project Coordinator in implementing monitoring and control mechanisms to ensure compliance with provisions set out in the Project Document on administrative and financial management, monitoring, preparation and presentation of project and financial reports to UNDP.

- Provide support in the selection and contracting processes for procurement of goods and services, as well as in screening and hiring individuals and travel management according to UNDP policies, standards, procedures and good practices.

- Ensure that transactions are undertaken in accordance with the procurement plan and agreements and/or contracts signed with third parties, and in accordance with UNDP rules and regulations.

- Verify that all payments for remunerations and other services are made in accordance with the terms of the contracts or agreements and the corresponding authorizations.

- Follow up requirements and purchase orders in coordination with UNDP´s Procurement Unit.

- Keep an updated inventory record of project physical resources, which have been given in custody, ensuring their good use until their final disposal by UNDP.

- Coordinate logistical aspects for the organization of workshops, meetings and events in coordination with the project´s technical team and partners.

- Keep updated files on administrative and financial issues (reports, communications, payment requests, procurements).

- Ensure permanent communication and coordination on administrative and financial issues with the Implementing Partner and other project partners.

- Provide support to project audits and external evaluations.

- Manage the project office (contracts, cleaning services, etc.)

- Other tasks necessary for adequate project management.

Required skills and expertise:

- Graduate degree or secondary school diploma with experience in management and administration.

- At least five years of relevant work experience in project administration, procurement and project management.

- Working experience in a project management setting involving multi-lateral/ international funding agency, preferably with UN projects is desirable.

- Experience in liaising and cooperating with government officials

- Acquaintance with UNDP procedures is highly desirable.

- Experience in organizing meetings, trip and per diem requests and in administrative functions.

- Computer skills and experience with data processing.

- Excellent verbal and written communication skills in Spanish.

Project Accountant

The Project Accountant will provide support to the Project Coordinator in management and administration of the project. Under the supervision of the Project Coordinator and in coordination with UNDP and the Implementing Partner, the Project Accountant will have the following specific responsibilities:

Duties and Responsibilities

- Support the Project Administrator in processes related to planning, administration, procurement, payments, conciliations, budgetary revisions and inventories, ensuring the adequate administrative and financial management in accordance with UNDP procedures.

- Carry out accounting procedures in accordance with the guidelines established by UNDP.

- Review project expenditures and ensure that project funds are used in compliance with the Project Document and Government of Argentina financial rules and procedures;

- Keep records of project funds and expenditures and ensure all project-related financial documentation are well maintained and readily available when required by the Project Coordinator.

- Budgetary control, ensuring that project activities are carried out within the limits of the approved budget and UNDP rules and procedures.

- Verify quarterly and annual CDRs for certification.

- Conciliate project expenses and commitments with those registered in the UNDP systems.

- Support the reconciliation of project intermediate and financial reports.

- Interact with the ATLAS ERP System managing: requisitions, purchase orders, vendors, vouchers and others.

- Provide necessary financial information as and when required for project management decisions;

- Provide necessary financial information during project audit(s);

- Consolidate financial progress reports submitted by the responsible parties for implementation of project activities;

- Elaborate and monitor contracting processes of the Project. Issue and record requests for payments and purchase orders required by the project.

- Keep updated files on accounting and financial issues (General Ledger, inventories, etc.)

- Undertake financial monitoring and control of the project, as well as disbursement schedules to ensure adequate recording of all financial operations.

- Provide support to external staff mobilization (requirement processing, per diem allocation and travel settlement) in accordance with UNDP policies and procedures.

- Provide support for the organization and holding of meetings.

- Liaise and follow up with the responsible parties for implementation of project activities on matters related to project funds and financial progress reports.

Required skills and expertise

- Graduate or advanced degree in accounting/ financial management.

- At least five years of relevant work experience in project accounting, procurement and project management.

- Working experience in a project management setting involving multi-lateral/ international funding agency, preferably with UN projects is desirable.

- Experience in organizing meetings, trip and per diem requests and in administrative functions

- Computer skills and experience with data processing.

- Excellent verbal and written communication skills in Spanish.

Information Systems Specialist

Under the overall supervision of the Project Coordinator, and in coordination with the Implementing Partner and other project partners, the Information Systems Specialist will be responsible for supporting the development and implementation of an information system for analysis of environmental variables for environmental land use planning as well as a system to evaluate and monitor the implementation of environmental land use planning.

Duties and Responsibilities

- Prepare the annual workplan and budget for the activities that fall under his/her responsibility and contribute to preparation of the project´s annual workplan and budget

- Prepare periodic reports of the activities carried out and contribute to the preparation of the project progress reports

- Support the project partners in undertaking in-depth assessments of existing data bases and information systems to identify requirements to standardize and share environmental information as well as identify and fill gaps.

- Support the development and application of protocols and criteria to update, standardize and systematize information from project partners.

- Provide technical backstopping and recommendations to the Implementing partner and other project partners in updating, standardizing and systematizing information.

- Provide training to staff of the Implementing Partner and other project partners in the protocols and processes for standardizing, systematizing and sharing data and information.

- Support the design and implementation of an information system for analysis of environmental variables to address environmental land use planning.

- Support the design of a system to evaluate and monitor the implementation of environmental land use planning.

- Support online coordination with project partners and key stakeholders.

- Support the design and implementation of tools to support online dissemination of information and make information available to potential users of the environmental information system.

- Support the development of SMART indicators to monitor the implementation of environmental land use planning and protocols for measuring the different indicators.

- Participate in consultation processes with project partners and stakeholders with regard to development of the information system and monitoring indicators.

- Support the development of maps for environmental land use planning, identifying map information needs, accessing map information sources and ensuring that the produced reports/maps meet the requirements of the project.

- Support project M&E, coordinating, supervising and monitoring the data collection processes carried out by project consultants and the technical teams of the participating institutions working on the ground/collecting data for each of the activities, and ensuring dynamic linkages between GIS data, partners´ databases, and the environmental information system.

- Undertake analysis of data and geographic information as needed to show progress of project activities, visually portray impact in line with project indicators, identify geographical/thematic needs and recommendations for the project.

Required skills and expertise

- Postgraduate degree in Information Technology (IT), engineering, data or computer science, or related discipline.

- At least 7 years of overall professional experience, with incremental responsibilities, preferably with some experience in the UN system.

- At least 5 years of experience and in-depth knowledge and track record in relevant areas including information management, GIS, natural resource management and environmental land use planning.

- Detailed understanding of IT support services including IT hardware/infrastructure support and other IT applications support.

- Knowledge of environmental issues, policies and programs in Argentina is desirable, including knowledge on issues related to environmental land use planning and relevant regulations.

- Ability to coordinate and supervise implementation of technical activities in partnership with a variety of national and provincial stakeholder groups, including government, community, private sector, CSOs.

- Strong interpersonal and communication skills; commitment to team work and to working across disciplines.

- Computer skills. Knowledge of QGIS is mandatory.

- Excellent verbal and written communication skills in Spanish.

Economic and Financial Instruments Specialist

Under the overall supervision of the Project Coordinator, and in coordination with the Implementing Partner and other project partners, the Economic and Financial Instruments Specialist will be responsible for supporting the development and implementation of economic, financial and fiscal instruments for environmental land use planning.

Duties and Responsibilities

- Prepare the annual workplan and budget for the activities that fall under his/her responsibility and contribute to preparation of the project´s annual workplan and budget.

- Prepare periodic reports of the activities carried out and contribute to the preparation of the project progress reports.

- Support the Implementing Partner and project partners in assessing and defining the methodologies for valuation of ecosystem goods and services in different ecoregions and land uses to provide decision makers with information on the implications of different courses of action affecting natural resources and global environmental values.

- Carry out research on representative existing incentive measures, review of case studies, identification of new opportunities for incentive measures, and dissemination of information.

- Carry out the analysis and support the technical teams of SGAyDS and provinces to design compensation schemes based on the results of valuation of ecosystem goods and services.

- Asses in coordination with SGAyDS and provinces  the most feasible economic, financial and fiscal instruments to put in place through the project to compensate for the opportunity costs for land owners who are required to reduce or change production in areas designated in environmental land use planning for strict conservation of biodiversity or those where extreme measures are needed to reduce land degradation and to promote implementation of production practices in restricted areas defined through environmental land use planning.

- Participate in the consultation processes with project partners and stakeholders with regard to  the development and implementation of economic, financial and fiscal instruments.

- Provide technical backstopping and recommendations to project partners for application of valuation methodologies and testing and validation of different economic, financial and fiscal instruments in the field, identifying lessons and supporting the adaptation of instruments to local realities when needed.

- Support project M&E, coordinating, supervising and monitoring data collection processes carried out by project consultants and the technical teams of the participating institutions working on the ground/collecting data for each of the instruments being tested.

- Support the Project Coordinator in synthesizing lessons and encourage uptake of best practices and knowledge on economic, financial and fiscal instruments.

Required skills and expertise

- Postgraduate degree in a relevant field such as natural resource economics.

- At least 7 years of overall professional experience, with incremental responsibilities, preferably with some experience in the UN system.

- At least 5 years of experience and in-depth knowledge and track record in economic valuation and/or financial and fiscal instruments to promote conservation and sustainable natural resource management.

- Knowledge of environmental issues, policies and programs in Argentina is desirable, including knowledge on issues related to environmental land use planning and production sectors.

- Ability to coordinate and supervise implementation of technical activities in partnership with a variety of national and provincial stakeholder groups, including government, community, private sector, CSOs.

- Strong interpersonal and communication skills; commitment to team work and to working across disciplines

- Computer skills.

- Excellent verbal and written communication skills in Spanish.

Stakeholder Engagement Specialist

Under the overall supervision of the Project Coordinator, and in coordination with the Implementing Partner and other project partners, the Stakeholder Engagement Specialist will be responsible for strategically organizing and strengthening consultation and stakeholder engagement within the framework of the Project´s Stakeholder Engagement Plan.

Duties and Responsibilities

- Prepare the annual workplan and budget for the activities that fall under his/her responsibility and contribute to preparation of the project´s annual workplan and budget

- Prepare periodic reports of the activities implemented and contribute to the preparation of the project progress reports.

- Assess the capacity of various agencies and stakeholder groups, in respect of their roles, functions and/or responsibilities in environmental land use planning, environmental management and productive sectors targeted by the project, and identify the capacity development needs of the different stakeholder groups to ensure development of adequate capacity strengthening programs.

- Support the development of strategies that are gender balanced and will enable the full and effective participation of key stakeholders including government institutions, NGOs, communities, producers, indigenous peoples and the private sector.

- Develop the detailed Indigenous Peoples Plan based on the draft IPP, the Social and Environmental Screening Procedure and the Stakeholder Engagement Plan.

- Support, maintain and update information and tools that will facilitate effective stakeholder participation such as stakeholder and network mapping and analysis and others included in the Stakeholder Engagement Plan.

- Support the development of multi-stakeholder dialogue and coordination spaces with adequate representation of key stakeholders including government institutions, NGOs and CSOs, private sector, academia, indigenous peoples, and ensure that these are gender balanced.

- Support the development and application of social safeguards, and particularly in regard to participation of indigenous peoples, respecting existing consultation mechanisms where they exist, and ensuring their rights to: participation in public policies; Prior Consultation in regard to specific regulatory or administrative measures; and Free, Prior and Informed Consent in specific cases that may affect their fundamental rights or risk their integrity.

- Support effective stakeholder engagement in other activities where necessary.

- Liaise with key stakeholders to ensure their needs and concerns are appropriately addressed in project planning and implementation.

- Develop and maintain communication and coordination with key stakeholders to ensure successful project implementation and ensure full disclosure of information to concerned stakeholders.

- Support the SGAyDS´s Communication Specialist in preparing communication materials and messages to encourage stakeholder engagement.

- Support the communication specialist of the Implementing Partner in the development of communication and information materials for publication in media (newspapers, radio and television, posters, webpage, blogs)

- Coordinate with the communication specialist of the Implementing Partner to ensure the availability and accessibility of information to enhance awareness and capacity among key stakeholders.

- Support the Project Coordinator in synthesizing lessons and encourage uptake of best practices and knowledge on stakeholder engagement.

- Provide support to ensure that social risks are identified, avoided, mitigated and managed throughout project implementation.

- Support the Project Coordinator to ensure reporting, monitoring and evaluation fully address the social safeguard issues of the project; providing well-documented, evidence-based compliance reports to be incorporated into the project annual reports.

- Develop an appropriate grievance mechanism for complaints and concerns arising from project implementation.

- Ensure social and environmental grievances are managed effectively and transparently through the grievance redress mechanisms.

- Oversee the development and implementation of field assessments to measure project progress, including among others, a livelihood assessment; field surveys; knowledge, aptitude and practice surveys.

Required skills and expertise

- Postgraduate degree in a relevant field such as social science or rural development, preferably with professional specialization in issues of ecologically sustainable production practices, natural resource management, biodiversity and/or ecosystem management, land use planning or stakeholder engagement.

- At least 10 years of overall professional experience, preferably with some experience in the UN system.

- At least 7 years of experience and in-depth knowledge and track record in stakeholder engagement and consultations, issues facing indigenous and traditional peoples, socioeconomic research and rural livelihood issues in the context of research, project design or management

- Demonstrated experience in constructing and implementing stakeholder engagement programs with a range of stakeholders

- Demonstrated experience in developing awareness materials for projects or institutions.

- Ability to network and engage in team-building.

- Knowledge of environmental issues, policies and programs in Argentina is desirable, including knowledge on issues related to environmental land use planning and production sectors

- Computer skills

- Excellent verbal and written communication skills in Spanish.

Gender Specialist

Under the overall supervision of the Project Coordinator, and in coordination with the Implementing Partner and other project partners, the Gender Specialist will be responsible for ensuring that gender is mainstreamed during project execution and for the implementation of the project Gender Action Plan, on related aspects of project implementation, reporting, monitoring, evaluation and communication.

Duties and Responsibilities

- Coordinate with the Project Coordinator, project team, consultants and the different technical and administrative units of the Implementing Partner and provincial governments for gender mainstreaming.

- Prepare the annual workplan and budget for the activities that fall under his/her responsibility and contribute to preparation of the project´s annual workplan and budget ensuring the necessary time and resources to implement the project Gender Action Plan.

- Prepare periodic reports of the activities implemented and contribute to the preparation of the project progress reports.

- Coordinate closely with the Stakeholder Engagement Specialist to ensure adequate gender mainstreaming and representation of women in consultation processes and stakeholder dialogue spaces.

- Support the development and application of social safeguards, and particularly in regard to the participation of women.

- Support the development of an appropriate grievance mechanism for complaints and concerns arising from project implementation, particularly in regard to the participation of women.

- Support effective and transparent management of social and environmental grievances through the grievance redress mechanisms.

- Collect sex‐disaggregated data in line with the Project Results Framework and the Gender Action Plan.

- Provide support to the Project Coordinator in preparing gender‐based reports required by UNDP and the GEF, as well as provide inputs into project evaluations on this issue, indicating, among other things, the progress in complying with the indicators included in the Project Results Framework and activities in the Gender Action Plan.

- Participate and coordinate project training activities for gender mainstreaming.

- Coordinate actions with government agencies, NGOs, CSOs, and women’s organizations or groups whose work focuses on gender in the project´s pilot provinces.

Required skills and expertise

- Postgraduate degree in a relevant field such as social science or natural sciences, preferably with professional specialization in gender and project cycle management.

- At least 7 years of overall professional experience, preferably with some experience in the UN system.

- At least 5 years of experience and in-depth knowledge and track record in the field of gender equality and gender mainstreaming.

- Demonstrated expertise in mainstreaming gender. Experience in gender-responsive capacity building.

- Demonstrated understanding of the links between sustainable development, social and gender issues.

- Experience working with government institutions and international organizations that support gender and development work in environmental projects and programs.

- Knowledge of gender analysis tools and methodologies for gender mainstreaming

- Knowledge of environmental issues, policies and programs in Argentina is desirable, including knowledge on issues related to environmental land use planning and production sectors

- Strong interpersonal and communication skills, commitment to team work and to working across disciplines

- Computer skills

- Excellent verbal and written communication skills in Spanish.

Provincial Technicians (3)

Under the overall supervision of the Project Coordinator, and in coordination with the Implementing Partner, the Provincial Governments of Buenos Aires, Jujuy and Mendoza, and project specialists, the Provincial Technicians will be responsible for providing technical support, coordination, oversight and monitoring and evaluation for the adequate implementation of project activities in each province.

Duties and Responsibilities

- Prepare the annual work plan and budget for the activities that fall under his/her responsibility and contribute to the preparation of the project´s annual workplan and budget.

- Prepare periodic reports of the activities implemented and contribute to the preparation of the project progress reports.

- Support project M&E, coordinating, supervising and monitoring data collection processes being carried out by project consultants and the technical teams of the participating institutions working on the ground/collecting data for the different activities carried out in the provinces.

- Support the Project Coordinator in supervising and coordinating the production of project outputs, as per the Project Document in a timely and high-quality fashion.

- Provide support in coordinating all project inputs and ensure that they adhere to UNDP procedures for nationally executed projects.

- Support the implementation of stakeholder engagement mechanisms as foreseen in the Stakeholder Engagement Plan, in coordination with the stakeholder engagement specialist.

- Support the implementation of gender mainstreaming in project activities as foreseen in the Gender Action Plan, in coordination with the gender specialist.

- Support the dissemination of information on the project.

- Undertake frequent meetings and visits to the project stakeholders, including government agencies, CSOs and communities, as part of the overall supervision of project implementation and prepare visit reports.

- Liaise and follow up with the responsible parties for implementation of project activities on matters related to planning and implementation of activities.

Required skills and expertise

- Graduate degree in a relevant field such as social science or rural development, preferably with professional specialization in issues such as ecologically sustainable production practices, natural resource management, biodiversity and/or ecosystem management, and/or land use planning.

- At least 5 years of overall professional experience in her/his field.

- Knowledge of environmental issues, policies and programs in Argentina is desirable, including knowledge on issues related to environmental land use planning and production sectors.

- Ability to coordinate and supervise implementation of technical activities in partnership with a variety of national and provincial stakeholder groups, including government, community, private sector, CSOs.

- Working experience in the provinces of Buenos Aires, Jujuy or Mendoza.

- Computer skills.

- Excellent verbal and written communication skills in Spanish.

## Annex E:  UNDP Social and Environmental Screening Procedure and plans as needed

(Signed version is in a separate file)

Project Information

| Project Information |  |
| --- | --- |
| - Project Title | Mainstreaming biodiversity conservation and sustainable land management (SLM) into development planning: Making Environmental Land Use Planning (ELUP) Operational in Argentina |
| - Project Number | 5791 |
| - Location (Global/Region/Country) | Argentina |

Part A. Integrating Overarching Principles to Strengthen Social and Environmental Sustainability

QUESTION 1: How Does the Project Integrate the Overarching Principles in order to Strengthen Social and Environmental Sustainability?

Briefly describe in the space below how the Project mainstreams the human-rights based approach

This project will provide technical support and resources to the Government of Argentina (GoA) to reduce biodiversity loss and land degradation in Argentina by mainstreaming biodiversity (BD) conservation and sustainable land management (SLM) approaches into the production practices of the main sectors driving these processes, namely the agriculture and livestock sector and the emerging threats from mining and infrastructure expansion in peri-urban areas. The approach to achieve this mainstreaming will be through spatial planning, specifically, Environmental Land Use Planning-ELUP. This is recognised within the General Law of the Environment (Law 25675, 2002), through Article 10, that sets up ELUP as an environmental management policy and instrument to guide the use of natural resources. One that allows a maximum production in each ecosystems whilst guaranteeing the minimum level of degradation and promoting social participation in decisions that are necessary for sustainable development. ELUP has to respect the interest and nature of the communities, applying public participation as a key mechanism during the ELUP decision making process. The core of the project is to strengthen the governance and zoning to guard against the expansion of production practices that may undermine ecosystem health and the loss of goods and services. Protecting these ecosystem services and goods in turn will maintain current and future development options of communities and indigenous peoples. In doing so the project upholds the generic concept of the centrality of human rights to sustainable development and is committed to supporting “universal respect for, and observance of, human rights and fundamental freedoms for all.” The project seeks to enhance or maintain the livelihoods of communities, preserve habitats and the value of ecosystems. The proposed changes regarding the use of the land must ensure the integrity of the ecosystems, the habitats and the preservation of the livelihoods of the communities and indigenous peoples. Specifically it will uphold the following principles as described below: Participation and inclusion: At the local and provincial levels, the project will engage multiple and diverse governmental institutions, organizations and stakeholder groups. A stakeholder mapping was undertaken during the PPG and the key stakeholders identified along with their roles in project implementation and participation in project components (see Annex F Stakeholder Engagement Plan of the UNDP/GEF Project Document). Project Component 2 will undertake interventions in three pilot provinces (Buenos Aires, Jujuy and Mendoza). Target landscapes have been selected in each province and interventions will be undertaken in rural areas of these sites. In Jujuy two target landscapes have been selected, which are inhabited by 16,586 people (2010 Population Census), the majority of which are Omaguaca, Kolla and Atacama indigenous peoples (36 communities in total), with the remainder being non-indigenous small producers. Four target landscapes in Mendoza are inhabited by 82,660 people (2010 Census) mainly small, medium and large-scale producers, including 150 families (600 individuals) of the Mapuche indigenous peoples living in one of the selected sites. In Mendoza, consultations were held with the “Werken” or spokesman, on behalf of the communities and the organization of the Mapuche communities of Mendoza. In Jujuy, the PPG team worked with provincial authorities and the Secretariat of Indigenous Peoples, which is responsible for the promotion and protection of the rights of Indigenous Peoples in the province, and in particular to guarantee the right to Prior Consultation and FPIC. In both cases oral and general agreements to the project were obtained as well as their agreement to jointly develop during project implementation specific consultations before elaborating specific ELUP related interventions in the target landscapes. Project interventions will be addressed within a human rights and livelihoods protection approach, particularly for Indigenous Peoples. and addressing the improvement and sustainability of their livelihoods. In this regard the decisions will be taken under appropriate consultation processes to obtain consent, and where appropriate Free, Prior and Informed Consent. In Buenos Aires the selected target landscapes cover rural areas with wetland and riverine areas with low population density, and agricultural areas occupied by small, medium and large-scale producers (1500 farms). According to information gathered during the PPG, there are Mapuche communities living in urban areas of one of the target landscapes of Buenos Aires; however, since project interventions will be undertaken in rural areas they are not likely to be affected. The PPG undertook an assessment of substantive indigenous rights and consultation and information requirements as per the relevant national and international legislation to foster full respect for indigenous peoples’ human rights including but not limited to their rights to self-determination, their lands, resources and territories, traditional livelihoods and cultures. Project activities are in line with the national legal framework that supports participation with regard to this project including the General Law of the Environment, the Native Forest Law (Nº26331), the Environmental Policy Law (Nº 25675) and the Law for Access to Public Information (Nº27275). At provincial level, participation is guaranteed through the Land Use Planning Law (Nº5961) in Mendoza; the General Law of the Environment (Nº 5063) and the Law for Adaptive Land Use Planning of Forest Areas (Nº5676) in Jujuy, and in Buenos Aires the Environment Law (Nº11723) and the Land Use Planning Law (Nº8912). Furthermore, the legal framework regarding Indigenous Peoples participation include the National Constitution, Law Nº24071 ratifying the ILO Convention 169, Law Nº23302 in support of indigenous communities and Law Nº26160 on indigenous territories. The assessment is included in the Stakeholder Engagement Plan. This legal framework has a wide approach to participation and will be complementary to the UNDP Standards, which will be closely followed during project implementation. Active participation in project activities will be voluntary and provisions have been made to increase understanding and buy-in as this is crucial to increase the feasibility, effectiveness and social sustainability of the actions proposed. Participation will be fostered through several components and mechanisms that have been identified to ensure full, effective and meaningful stakeholder participation and avoid negative human rights impacts. These are: a) communication and capacity development for informed participation; b) dialogue mechanisms taking advantage of existing spaces and structures for consultation, deliberation, decision making and inter-institutional coordination; and c) conflict prevention and management (spaces for negotiation, mediation, information requests and grievance). With regard to the participation of indigenous peoples in pilot provinces, the province of Mendoza has over 20 years of experience in undertaking participatory processes in land use planning. In particular, the Mapuche communities in the Mendoza target landscape have participatory structures such as the Community Assembly and the Council of Authorities in each community, and are organized in the Malalweche Mapuche Territorial Organization. A protocol for prior consultation has been developed and proven and there is experience in prior consultation processes with government and non-government stakeholders. Jujuy has also developed wide experience in participatory processes. The Kolla, Omaguaca and Atacama peoples have very similar decision-making structures in each community such as the Community Council, the Council of Elders and the Assembly. The communities in the target landscapes do not have specific protocols (as do other communities throughout the province) but have a high degree of coordination with the Indigenous Peoples Secretariat of the province, which provides technical backstopping for designing and undertaking consultation processes in the communities and facilitating dialogue with public and private institutions. The Secretariat has a specific unit to provide support to the communities in implementing consultation processes. The communities regularly undertake dialogues with public authorities and private sector on subjects of their interest. The project will make use of these existing structures, protocols and processes to ensure participation of indigenous peoples in planning, implementation and monitoring of interventions in the target landscapes. In addition, during the first year of project implementation the project will develop a detailed Indigenous Peoples Plan (IPP), building on the draft IPP (Project Document Annex E-1, this SESP and the Stakeholder Engagement Plan. Based on that IPP the project and provincial authorities will undertake the processes for prior consultations and FPIC (as per UNDP’s SES and in line with ILO 169) to obtain consent for potential activities that trigger requirement under the international framework and UNDP (e.g extraction of natural resources such as felling or mining or agricultural developments in their lands or territories; a decision that could affect the status or rights of people to their lands/territories, resources or livelihoods; access to traditional knowledge, innovations and practices; commercial use of natural and/or cultural resources in lands subject to traditional ownership or under traditional use by Indigenous Peoples; decisions in regards to benefit sharing when such benefits derive from their lands, territories or resources). The principle of accountability and rule of law will also be upheld by following all standard UNDP policies on monitoring, evaluation, audits, and transparency in project implementation. The legal context of the project is defined by the CPAP signed by the Government and UNDP and which includes reference to “ensure the inclusion of a sustainable development approach… promotion of sustainable livelihoods, conservation, equitable and sustainable use of biodiversity and ecosystems…”. All CPAP provisions apply to this document. In addition, UNDP has established accountability mechanisms with two main components: 1) A Compliance Review to respond to any potential claims that UNDP is not in compliance with applicable environmental and social policies; and 2) A Stakeholder Response Mechanism (SRM) that ensures individuals, peoples, and communities affected by projects have access to appropriate grievance resolution procedures for hearing and addressing project-related complaints and disputes. A project-level grievance redress mechanism (GRM) will also be established, as described in the Stakeholder Engagement Plan and draft IPP.

Briefly describe in the space below how the Project is likely to improve gender equality and women’s empowerment

Women and men play important but differentiated roles in biodiversity and natural resource management, use, and conservation while satisfying their various livelihood requirements that are highly dependent on biodiversity and ecosystem services. Women often take the lead in the selection and improvement of local production and in more remote areas they are also the primary collectors of wild foods in forests and they possess extensive knowledge of their location and characteristics. The project recognizes that roles for women and men in natural resource management are different. The project also appreciates the importance of participation of and consideration of gender issues in project design and implementation. In this regard the project will mainstream gender into all activities based on a detailed gender analysis carried out during the PPG. Additionally, gender balance will be taken into account in engaging the project team, the Steering Committee and multi-sectoral, multi-stakeholder committees. Gender and ethnic analysis carried out during the PPG (main findings). 1. In Argentina the causes of gender inequality and discrimination are mainly explained by the prevalence of traditional patriarchal structures and norms and gender roles, particularly in remote, rural and agricultural areas. 2. Young, poor, rural and indigenous women represent around 40% of the agricultural labor force. Although there are no legal instruments that prevent women from owning property, such as land, in Argentina 80% of men have such ownership (FAO, 2010). Men are the ones who mostly make decisions related to access, use and management of ecosystem resources; therefore, most women cannot enjoy the benefits of profitable land, access credit and/or productive resources derived from land. While women are not as active as men in agricultural labor force, women take on major roles in sustainable forest management. As caregivers they are highly dependent on forests and are the primary users of forest products. However, they are often excluded from forestry-related decision-making. This bears the risk/concern that women’s valuable knowledge remains underutilized. 3. In Argentina, there are more women (52%) than men (48%). The number of women 46 years and older is higher, while the ratio is reversed in younger ages (from 0 to 35 years), with the exception of the age bracket 14 to 15 years. This distribution of the population by sex and age groups is conserved without statistically significant differences in the three prioritized areas (52.0% women and 48.0% men in Buenos Aires; 51.5% women and 48.5% men in Jujuy and 52.2% women and 47.8% men in Mendoza (INDEC, 2017). 4. 91% of the Argentine population lives in urban areas and the remaining 9% in rural areas. Mendoza is the province with the largest number of inhabitants in rural areas (19.1%), followed by Jujuy (12.5%) and then Buenos Aires (3%). The distribution of rural population disaggregated by sex in the province of Jujuy is 51.7% men and 48.3% women (DIPEC, 2012). So far, information disaggregated by sex in rural areas has not been available in Mendoza or Buenos Aires. 5. The proportion of indigenous peoples with respect to the total population of each jurisdiction is variable: 2.38% at the national level, 1.92% in Buenos Aires; 2.4% in Mendoza and 7.8% in Jujuy with respect to provincial totals. Jujuy has the largest indigenous population in relative terms (8%). The distribution of the indigenous population according to sex presents a fairly homogeneous behavior within each jurisdiction and in the country as a whole (50% men and 50% women). The proportion of the Afro-descendant population is less than 1% in the three prioritized areas. 6. Regarding the heads of household, of every 10 people who claim to be head of the household at the national level, 4 are women and 6 are men (41.2% and 58.8%, respectively). This proportion is consistent in each priority area. In relation to the age of women heads of household both at the country level and in the priority areas, 6 out of 10 women heads of household are 50 years old and over, and they are more affected by the double burden of domestic and paid work that falls on them alone. Note: A head of household is “the person, either a man or a woman, or both, recognized as such by the other members of the household”. Source: Situation and Social Evolution (Synthesis N ° 4); INDEC. 7. Regarding socio-economic indicators, at the country level, approximately 40% of women up to 29 years old participate in the labor market against almost 60% of men in the same age group. Only in Jujuy is there a marked decrease in the proportion of men who participate in the economy (38.8%) compared to the national percentage, although the rate of men in the labor market still exceeds that of women in the labor market in that province (29.2%). In Mendoza, the male activity rate is also lower than the national rate for that same age group (52.0%) and also exceeds that of women (39.1%). The employment rate is higher for men than for women (65.7% and 43.5%, respectively), a trend that, although there are nuances, is reproduced inside the prioritized areas. Men earn 26% more than women (WEF, 2017). 8. The unemployment rates follow an inverse pattern, registering a higher percentage of unemployed women at the country level than men in the same situation (8.7% and 6.1%, respectively). In Jujuy and Mendoza the percentage variations are smaller. Within the age group up to 29 years, there is a marked gap between the unemployment of men and women. The difference at the national level is 7.4 percentage points, to the detriment of women, a trend that is exacerbated in Mendoza and Buenos Aires, with 7.55 and 11.1 percentage points, respectively. The trend softens in the case of Jujuy, where the difference is only 1.8 percentage points. 9. According to the World Economic Forum's Global Gender Gap Index (WEF, 2017), Argentina stands out in terms of access to education for men and women, obtaining a score of 0.998 out of 1, which indicates parity between men and women. This proportion holds true in each priority area. 10. Regarding the level of poverty and indigence, in the second half of 2017 the percentage of households below the poverty line was 17.9%; these comprise 25.7% of people. In the three prioritized areas, the differences are not statistically significant, except for Buenos Aires where the percentage of households and people below the poverty line exceeds the national average (21.3% and 29.5%, respectively) and the same situation is observed in terms of the indigence analysis, where the values ​​exceed the percentage at the country level (4.6% of households that comprise 6.2% of the population in this prioritized area). 11. The amount of average weekly hours that women devote to unpaid work is much higher than that of men, and as the age of children increases, women’s participation in the labor market increases, too. This is unlike what happens with men, whose participation remains stable. In the country as a whole, women spend, on average, 76.4% of their time on unpaid domestic work, while men spend, on average, only 23.6% of their time on the same activity (EAHU, 2013). That is, women spend 3.3 times more of their time on unpaid domestic work than men. This proportion is evident in each priority area. Main strategies to mainstream gender and ethnicity in the project - Gender balance will be taken into account in engaging the project team, the Project Board and multi-sectoral, multi-stakeholder dialogue spaces. For this sake, a consultant will be hired or contracted during project implementation to work on gender mainstreaming aspects. - Including gender and ethnicity disaggregated social and economic data collected from official sources in the development of policy, economic, financial and technical instruments and governance mechanisms for ELUP. If the latter are scarce, specific instruments (e.g. survey) should be created by the project to gather sensible and evidence-based gender and ethnicity disaggregated data to examine gender dimensions in the use of BD and ecosystem resources management. - Development of a capacity building program aimed at public officials and/or technical teams to raise awareness on the importance of engaging both women and men in decision-making processes and addressing gender issues. - Gender and ethnicity mainstreaming in the promotion of dialogue mechanisms, making the most of existing spaces and structures for consultation, deliberation, decision-making and inter-institutional coordination at the national, provincial and pilot levels, by fostering equal participation of women and men and indigenous populations in agenda-setting, decision-making and/or policy-making processes. 5. Development of a capacity building program aimed at women beneficiaries (indigenous and non-indigenous) in the three prioritized areas and pilot sites to: i) promote gender equality in the management, use and conservation of biodiversity; ii) ensure that both women and men´s needs are addressed through the project interventions; iii) engaging men and women equally in order to ensure their participation in multi-sectoral and multi-stakeholder dialogue spaces (dialogue platforms and/or mechanisms in the three prioritized areas). For this purpose, the project will articulate with the gender machinery at the national level (National Institute of Women – INAM, the Federal Council of Women and the National Institute of Indigenous Affairs) and with the three provincial gender and indigenous affairs institutions (Buenos Aires: the Provincial Council of Women under the Secretariat for Gender and Sexual Diversity of the Secretariat for Human Rights of the Province of Buenos Aires and the Provincial Council for Indigenous Affairs (CPAI), a co-decision body of the Human Rights Secretariat of the Province of Buenos Aires; Mendoza: the Directorate of Women, Gender and Diversity under the Ministry of Social Development and Human Rights and in Jujuy, the Gender Parity Secretariat under the Ministry of Human Development and the Secretariat of Indigenous Peoples). Each of these entities will enhance collaboration with civil society organizations in the three prioritized areas. 6. Enhance project knowledge management by systematizing, assessing, replicating and/or scaling up lessons learned, case studies, and promising and/or best practices on gender mainstreaming and multicultural approach in BD/SLM and ELUP and on women’s participation in dialogue platforms and/or mechanisms in the three prioritized areas. This strategy is based on the assumption that beneficiaries are aware of the need to adopt sustainable and environmentally friendly best practices and their advantages to help improve production, productivity and livelihoods, engage and adopt best practices. 7. Gender-disaggregated indicators have been included in the Project Results Framework and financial and human resources have been set aside for gender mainstreaming and monitoring the effectiveness of doing so. A consultant will be hired or contracted during project implementation to work on gender mainstreaming aspects.

Briefly describe in the space below how the Project mainstreams environmental sustainability

The project will provide support to make this ELUP operational and will be based on criteria such as valuation of ecosystem goods and services and trade off scenario analysis to determine changes or modifications needed in production practices to reduce impact in priority areas in the landscape. It will support ELUP in three provinces (Buenos Aires, Jujuy and Mendoza), test sustainable production practices for different zones and model a mix of instruments to implement restrictions in priority landscapes as needed. These include command and control mechanisms, such as fines, fiscal approaches and incentives (e.g., preferential credit, market-based). This will deliver direct benefits to nine ecoregions with globally significant biodiversity or top priorities for combatting land degradation (Pampas, Delta and Islands of the Parana River, Espinal, Puna, Yungas Forest, High Monte, Low Monte, High Andes and Patagonian Steppe). In parallel the project will strengthen Federal public policy for ELUP including setting the minimum standards for the application of these approaches in Provinces across the nation, and will incorporate the ELUP mechanisms into sector planning and finance frameworks. In doing so it will trigger changes in the use of public finance flows on the scale necessary to address threats to priority areas and develop the policy reforms needed to mitigate the key sectoral drivers of biodiversity loss and land degradation and encourage sustainable development through the better management of biodiversity and natural capital.

Part B. Identifying and Managing Social and Environmental Risks

| QUESTION 2: What are the Potential Social and Environmental Risks? Note: Describe briefly potential social and environmental risks identified in Attachment 1 – Risk Screening Checklist (based on any “Yes” responses). If no risks have been identified in Attachment 1 then note “No Risks Identified” and skip to Question 4 and Select “Low Risk”. Questions 5 and 6 not required for Low Risk Projects. | QUESTION 3: What is the level of significance of the potential social and environmental risks? Note: Respond to Questions 4 and 5 below before proceeding to Question 6 |  |  |  |  | QUESTION 6: What social and environmental assessment and management measures have been conducted and/or are required to address potential risks (for Risks with Moderate and High Significance)? |
| --- | --- | --- | --- | --- | --- | --- |
| Risk Description | Impact and Probability (1-5) | Significance (Low, Moderate, High) | Comments |  |  | Description of assessment and management measures as reflected in the Project design. If ESIA or SESA is required note that the assessment should consider all potential impacts and risks. |
| Risk 1 The project activities will take place within and adjacent to critical habitats and/or environmentally sensitive areas, including legally protected areas and indigenous people’s lands. The risk is that unless proposed land uses take into account ecosystem structure and function limitations, it may adversely affect conservation values of these areas. (Standard 1, questions 1.1, 1.2 and 1.3) | I = 3 P = 1 | Low | The focus of the project is precisely on maintaining areas that are identified as being priorities for their high biodiversity conservation value; or that are identified as vulnerable to land degradation, and in turn, loss of ecosystem goods and services that are important for livelihoods and production sectors. The project will foster land use planning, governance and management that harmonize national, provincial and local priorities that will guide land use to those activities and practices that do not harm ecosystem goods and services. |  |  |  |
| Risk 2: Through Output 2.1 the project will support land use planning and regulation in sensitive areas where economic activity could potentially impact the ecosystem. This may result in economic displacement (e.g., loss of access to resources due to land use restrictions) and could have an opportunity cost to small-scale producers although there will be no loss of access to land or physical relocation. (Standard 5, question 5.2) (Principle 1, question 3) (Standard 6, question 6.6) | I = 3 P = 3 | Moderate |  |  |  | The project strategy has been designed to compensate any potential opportunity costs in the short term by testing a range of incentives and compensation mechanisms. In parallel it will work through sectoral programmes and facilitate access to markets or credit to increase financial flows in the medium term to transition to new production or provide continued support for private conservation. Potential pressure of future land use changes in response to changes in economic and trade contexts (for instance, changes in commodity prices) would also be offset based on: a) use of multi-stakeholder dialogue platforms/sustainable commodities platform to coordinate new production interests and demands; b) testing of economic and financial instruments to maintain sustainable and compatibles uses. The main focus of the project strategy is to promote sustainable uses that guarantee the preservation and improvement of the ecosystems and their services as well as livelihoods, particularly of Indigenous Peoples. Decisions regarding the territories inhabited by Indigenous Peoples will be taken in accordance with the regulatory framework on Indigenous Peoples’ Human Rights, undertaking prior consultation in all cases and FPIC when required. The draft Indigenous Peoples Plan, which is included in the Project Document, will be further developed during the first year of implementation into a fully detailed Plan. |
| Risk 3: Indigenous peoples are present in the selected pilot sites of the provinces of Mendoza and Jujuy. Some of the environmentally sensitive areas may be located in their lands and unless the culturally appropriate consultations are carried out with the objective of achieving FPIC, the land use planning in these areas may affect the rights and interests, lands, resources, territories and traditional livelihoods of the indigenous peoples concerned. (Standard 6, questions 6.1, 6.2, 6.3, 6.4) | I = 4 P = 2 | Moderate | Argentina ratified 169 ILO Convention concerning indigenous and Tribal Peoples, which recognizes indigenous rights and mandatory consultations and FPIC on specific cases. Moreover, the national and provincial legal framework related to this project provides for stakeholder participation including indigenous peoples and have been assessed during the PPG to ensure project alignment. During the PPG consultations were undertaken with provincial authorities and representatives of indigenous peoples to identify the strategies to best ensure their participation and inclusion in project planning, implementation and monitoring. In both Mendoza and Jujuy provinces oral and general agreements to the project were obtained as well as the agreement to jointly develop during project implementation specific consultations before elaborating the detailed ELUP related interventions in the target landscapes |  |  | Environmental Land Use Planning is essentially a participatory tool, and this principle will prevail during project implementation. To this effect a project Stakeholder Engagement Plan (Project Document Annex F) and a draft IPP (Annex E-1) have been developed that include several participatory mechanisms and specific provisions and measures. This draft IPP will be developed in detail during project year 1. At target landscape level the action lines outlined in the Project Document will be defined in detail during project implementation. For this the project will apply prior consultations at all times and FPIC will be ensured on any matters that may affect the rights and interests, lands, resources, territories, namely extraction of natural resources such as felling, mining or agricultural activities in their lands or territories; a decision affecting the status or people’s rights to their land/territories, resources or means of support; access to traditional knowledge and practices; commercial use of natural and / or cultural resources in plots of land subject to traditional ownership rights and / or traditional use by indigenous peoples; decisions regarding benefit sharing arrangements, where the benefits are derived from their land, territories or resources (eg., management of natural resources or extractive industries). The project will take advantage of the existing institutional experience in consultation processes in Mendoza and Jujuy, as well as the existing community structures and organizations, and protocols and processes that have already proven successful with the indigenous communities that will participate in project interventions. In addition, at provincial level participation of indigenous peoples will fostered in two spaces. One of them will be the the multi-stakeholder dialogue spaces (Output 2.2) which will engage stakeholders with different levels of power and use of resources in participatory land use planning. Another space will be a Provincial Project Working Group, which will include key stakeholders involved in project implementation and will be in charge of providing strategic guidance in each pilot province. Furthermore, these mechanisms will be strengthened through communication and capacity building for informed consent that will be implemented at provincial level within the dialogue platforms (Output 2.2) and at pilot site level within the consultation processes for planning and implementing field interventions (Output 2.4). A System for Prevention and Management of Consultations and Conflicts (project-level grievance redress mechanism) will be put in place to prevent potential conflicts, manage conflicts that may arise and to serve as a grievance mechanism. More detailed information is included in the draft Indigenous Peoples Plan, Annex E-1 of the Project Document. |
| Risk 4: The project could potentially limit women’s ability to use, develop and protect natural resources, taking into account the different roles and positions of women and men in accessing environmental goods and services (Principle 2, question 4) | I = 3 P = 3 | Moderate | The project mainstreams gender and multi-cultural issues, based on the premise that besides ensuring participation of both women and men (and their organizations) in the spaces, dialogue platforms and mechanisms generated by the project, it will contribute to their effective empowerment as social actors by ensuring that both women and men´s needs are addressed through the project interventions. The gaps identified in the analysis and which are considered in the strategy include: i) lack of parity in decision-making spaces; ii) differences between men and women in access to improved incomes and livelihoods; iii) differences in use of time; and iv) differences in access to, and control of resources between men and women. |  |  | A gender analysis was undertaken during the PPG. The findings were used to develop a Gender Analysis and Action Plan, which will be implemented throughout the project. (See Annex G of the Project Document). Key strategies include: 1) All data, reports and inputs for the development of the policy, economic, financial and technical instruments and governance mechanisms for ELUP will be looked at through a gender and intercultural view. 2) The project will develop a capacity building program aimed at public officials and/or technical teams to raise awareness on the importance of engaging both women and men in decision-making processes and addressing gender issues, such as how the different roles and positions of women and men affect the use, development and protection of environmental goods and services. 3) Gender and ethnicity will be mainstreamed in the dialogue mechanisms by fostering equal participation of women and men and indigenous populations in agenda-setting, decision-making and/or policy-making processes. 4) The project will develop a capacity building program aimed at women beneficiaries (indigenous and non-indigenous) in the three prioritized areas and target landscapes to: i) promote gender equality in the management, use and conservation of biodiversity; ii) ensure that both women and men´s needs are addressed through the project interventions; iii) engaging men and women equally in order to ensure their participation in multi-sectoral and multi-stakeholder dialogue spaces. 5) The project will enhance knowledge management by systematizing, assessing, replicating and/or scaling up lessons learned, case studies, and promising and/or best practices on gender mainstreaming and the multicultural approach in BD/SLM and ELUP. More detailed information is included in the Gender Analysis and Action Plan, Annex G of the Project. In addition, the Stakeholder Engagement Plan (Annex F of the UNDP Project Document) foresees the participation of women through several mechanisms that include dialogue, communication and information, and capacity building. |
| Risk 5: Land use suitability could change due to climate change, making potential outcomes of the project sensitive or vulnerable to potential impacts of climate change (Standard 2, question 2.2) | I = 3 P = 3 | Moderate | Climate scenarios described in Argentina´s Third National Communication indicate in general increases in high temperature and rainfall extremes in most of the country. Given the extension and climatic diversity of Argentina, climate change will affect different regions differently. |  |  | The PPG team assessed the risk and management measures have been integrated into the Project Document. These include: 1) coordination with projects that share intervention areas to exchange experiences and lessons on climate change issues; 2) the project will participate in the roundtables of the National Climate Change Cabinet and in turn the institutions that comprise this cabinet will be invited to participate in the dialogue spaces for participatory ELUP to mainstream climate change considerations (Outcome 1); 3) Discussions on climate change and its potential impacts will also be a part of the participatory dialogue spaces at provincial level (Outcome 2); 4) environmentally friendly and sustainable practices (Outcome 2) taking into account the vulnerabilities and impacts of climate change and adaptation needs; 5) development of economic and financial incentives (Outcomes 1 and 2) will incorporate CC considerations; 6) assessment of experiences and lessons (Outcome 3) will also take into account knowledge in regards to climate change; 7) awareness raising and training of landowners and communities for a better understanding of vulnerability and climate change impacts. |
|  | QUESTION 4: What is the overall Project risk categorization? |  |  |  |  |  |
|  | Select one (see SESP for guidance) |  |  |  |  | Comments |
|  | Low Risk |  |  | ☐ |  |  |
|  | Moderate Risk |  |  | x | Given that the project has an explicit focus on biodiversity conservation and Sustainable Land Management through best practice land-use planning and setting up the framework for its implementation, the risk of adversely affecting conservation values is limited. However, because communities and indigenous peoples are present in several target landscapes covering globally important ecoregions where the project will work, measures are needed to ensure risks are managed. The design of the project takes into account measures, which will be further developed during project implementation. Full and meaningful participation and inclusion of indigenous peoples at all levels will be guaranteed. At target landscape level the action lines outlined in the Project Document will be defined in detail during project implementation. For this the project will apply prior consultations at all times and FPIC will be ensured on any matters that may affect the rights and interests, lands, resources, territories. Agreement will be sought in all cases where project activities that may adversely affect the existence, value, use or enjoyment of indigenous lands, resources or territories, as per UNDP’s Standard 6 on Indigenous Peoples. Interventions addressing indigenous communities will follow and respect their organizational ways and cultural patterns; will ensure that stakeholders show respect for their dignity and human rights and will be carried out with a multi-cultural approach, respecting their collective and individual rights protected by international and national regulations and including safeguards to ensure actions do not negatively affect the livelihoods of indigenous communities. Participation will be ensured through: a) accumulated institutional experience in consultation processes in Jujuy and Mendoza; b) existing community structures and organizations, and c) proven participation protocols and processes; d) capacity building and awareness raising for participation; and e) communication and information. |  |
|  | High Risk |  |  | ☐ |  |  |
|  | QUESTION 5: Based on the identified risks and risk categorization, what requirements of the SES are relevant? |  |  |  |  |  |
|  | Check all that apply |  |  |  |  | Comments |
|  | Principle 1: Human Rights |  |  | x | With the support to Environmental Land Use Planning, there may be restrictions on potential production activities that may incur opportunity costs. These restrictions will be negotiated during land use planning with different levels of government and communities. Additionally, as noted above the project design includes testing economic and financial incentives and selecting and promoting those best feasible to compensate for potential opportunity costs. The project is committed to supporting “universal respect for, and observance of, human rights and fundamental freedoms for all” through: a) implementation of the stakeholder engagement plan that has been designed to ensure buy-in and full and meaningful participation and inclusion of all concerned stakeholders at all levels; b) a conflict prevention and management system, including a grievance mechanism; and c) a gender mainstreaming strategy. |  |
|  | Principle 2: Gender Equality and Women’s Empowerment |  |  | x | As outlined above (Question 1 and Question 2/Risk 4) the gender analysis identified several gaps including: parity in decision-making spaces; women´s incomes and livelihoods; use of time; and access to, and control of resources. The project has developed a strategy that links the most important gaps identified in relation to its outcomes, the proposed interventions, and the country´s policies and commitments toward gender equality. See Annex G of the UNDP Project Document for further details). In addition, the Stakeholder Engagement Plan (Annex F of the UNDP Project Document) foresees the participation of women through several mechanisms that include dialogue, communication and information, and capacity building. |  |
|  | 1. Biodiversity Conservation and Natural Resource Management |  |  | ☐ |  |  |
|  | 2. Climate Change Mitigation and Adaptation |  |  | x | Argentina´s Third National Communication identifies the climate scenarios for the different regions of the country as well as vulnerabilities and impacts. These include forecasts for the project´s three pilot provinces (Buenos Aires, Jujuy and Mendoza), which will be taken into account during project implementation to promote an Environmental Land Use Planning management model that is flexible and adjustable to increase resilience to climate change. Adaptation to climate change will be incorporated in capacity building activities, in the design of economic and financial incentives and in testing and validating environmentally friendly and sustainable best practices. |  |
|  | 3. Community Health, Safety and Working Conditions |  |  | ☐ |  |  |
|  | 4. Cultural Heritage |  |  | ☐ |  |  |
|  | 5. Displacement and Resettlement |  |  | X | This Standard will be met through the development and implementation of the detailed IPP; see the following comment for more detail. |  |
|  | 6. Indigenous Peoples |  |  | X | As described above (Question 1 and Question 2/Risks 2 and 3) the Jujuy and Mendoza pilot sites involve indigenous communities. In Mendoza and Jujuy consultations were held with the “Werken” authority and the Secretariat of Indigenous Peoples respectively. In both cases oral and general agreements for the project have been obtained as well as the agreement to jointly develop during project implementation specific consultations before elaborating detailed ELUP related interventions in the target landscapes. A project Stakeholder Engagement Plan and a draft IPP have been developed that include several participatory mechanisms and specific provisions and measures. The draft IPP will be developed in detail in project year 1. At target landscape level the action lines outlined in the Project Document will be defined in detail during project implementation. For this the project will apply prior consultations at all times and FPIC will be ensured on any matters that may affect the rights and interests, lands, resources and territories. The project will respect the ethno-cultural characteristics of the indigenous communities to be involved (Omaguaca, Kolla, Atacama and Mapuche) in the design of interventions. The project will work with the existing organizational structures and decision-making processes of each group and will take advantage of the dialogue and workspaces already developed between provincial governments and communities. Representatives of indigenous communities/organizations will be invited to participate in project planning, implementation and monitoring and evaluation. Participatory dialogue and coordination will be established with communities to report, motivate, engage and receive feedback with regard to the project. See Annex F of the UNDP Project Document. |  |
|  | 7. Pollution Prevention and Resource Efficiency |  |  | ☐ |  |  |

Final Sign Off

| Signature | Date | Description |
| --- | --- | --- |
| QA Assessor |  | - UNDP staff member responsible for the Project, typically a UNDP Programme Officer. Final signature confirms they have “checked” to ensure that the SESP is adequately conducted. |
| QA Approver |  | UNDP senior manager, typically the UNDP Deputy Country Director (DCD), Country Director (CD), Deputy Resident Representative (DRR), or Resident Representative (RR). The QA Approver cannot also be the QA Assessor. Final signature confirms they have “cleared” the SESP prior to submittal to the PAC. |
| PAC Chair |  | UNDP chair of the PAC. In some cases PAC Chair may also be the QA Approver. Final signature confirms that the SESP was considered as part of the project appraisal and considered in recommendations of the PAC. |

### SESP Attachment 1. Social and Environmental Risk Screening Checklist

| Checklist Potential Social and Environmental Risks |  |
| --- | --- |
| Principles 1: Human Rights | Answer (Yes/No) |
| 1. Could the Project lead to adverse impacts on enjoyment of the human rights (civil, political, economic, social or cultural) of the affected population and particularly of marginalized groups? | No |
| 2. Is there likelihood that the Project would have inequitable or discriminatory adverse impacts on affected populations, particularly people living in poverty or marginalized or excluded individuals or groups? | No |
| 3. Could the Project potentially restrict availability, quality of and access to resources or basic services, in particular to marginalized individuals or groups? | Yes |
| 4. Is there likelihood that the Project would exclude any potentially affected stakeholders, in particular marginalized groups, from fully participating in decisions that may affect them? | No |
| 5. Is there a risk that duty-bearers do not have the capacity to meet their obligations in the Project? | No |
| 6. Is there a risk that rights-holders do not have the capacity to claim their rights? | No |
| 7. Have local communities or individuals, given the opportunity, raised human rights concerns regarding the Project during the stakeholder engagement process? | No |
| 8. Is there a risk that the Project would exacerbate conflicts among and/or the risk of violence to project-affected communities and individuals? | No |
| Principle 2: Gender Equality and Women’s Empowerment |  |
| 1. Is there likelihood that the proposed Project would have adverse impacts on gender equality and/or the situation of women and girls? | No |
| 2. Would the Project potentially reproduce discriminations against women based on gender, especially regarding participation in design and implementation or access to opportunities and benefits? | No |
| 3. Have women’s groups/leaders raised gender equality concerns regarding the Project during the stakeholder engagement process and has this been included in the overall Project proposal and in the risk assessment? | No |
| 4. Would the Project potentially limit women’s ability to use, develop and protect natural resources, taking into account different roles and positions of women and men in accessing environmental goods and services? For example, activities that could lead to natural resources degradation or depletion in communities who depend on these resources for their livelihoods and well being | Yes |
| Principle 3: Environmental Sustainability: Screening questions regarding environmental risks are encompassed by the specific Standard-related questions below |  |
| Standard 1: Biodiversity Conservation and Sustainable Natural Resource Management |  |
| 1.1 Would the Project potentially cause adverse impacts to habitats (e.g. modified, natural, and critical habitats) and/or ecosystems and ecosystem services? For example, through habitat loss, conversion or degradation, fragmentation, hydrological changes | Yes |
| 1.2 Are any Project activities proposed within or adjacent to critical habitats and/or environmentally sensitive areas, including legally protected areas (e.g. nature reserve, national park), areas proposed for protection, or recognized as such by authoritative sources and/or indigenous peoples or local communities? | Yes |
| 1.3 Does the Project involve changes to the use of lands and resources that may have adverse impacts on habitats, ecosystems, and/or livelihoods? (Note: if restrictions and/or limitations of access to lands would apply, refer to Standard 5) | Yes |
| 1.4 Would Project activities pose risks to endangered species? | No |
| 1.5 Would the Project pose a risk of introducing invasive alien species? | No |
| 1.6 Does the Project involve harvesting of natural forests, plantation development, or reforestation? | No |
| 1.7 Does the Project involve the production and/or harvesting of fish populations or other aquatic species? | No |
| 1.8 Does the Project involve significant extraction, diversion or containment of surface or ground water? For example, construction of dams, reservoirs, river basin developments, groundwater extraction | No |
| 1.9 Does the Project involve utilization of genetic resources? (e.g. collection and/or harvesting, commercial development) | No |
| 1.10 Would the Project generate potential adverse transboundary or global environmental concerns? | No |
| 1.11 Would the Project result in secondary or consequential development activities, which could lead to adverse social and environmental effects, or would it generate cumulative impacts with other known existing or planned activities in the area? For example, a new road through forested lands will generate direct environmental and social impacts (e.g. felling of trees, earthworks, potential relocation of inhabitants). The new road may also facilitate encroachment on lands by illegal settlers or generate unplanned commercial development along the route, potentially in sensitive areas. These are indirect, secondary, or induced impacts that need to be considered. Also, if similar developments in the same forested area are planned, then cumulative impacts of multiple activities (even if not part of the same Project) need to be considered. | No |
| Standard 2: Climate Change Mitigation and Adaptation |  |
| 2.1 Will the proposed Project result in significant greenhouse gas emissions or may exacerbate climate change? | No |
| 2.2 Would the potential outcomes of the Project be sensitive or vulnerable to potential impacts of climate change? | Yes |
| 2.3 Is the proposed Project likely to directly or indirectly increase social and environmental vulnerability to climate change now or in the future (also known as maladaptive practices)? For example, changes to land use planning may encourage further development of floodplains, potentially increasing the population’s vulnerability to climate change, specifically flooding | No |
| Standard 3: Community Health, Safety and Working Conditions |  |
| 3.1 Would elements of Project construction, operation, or decommissioning pose potential safety risks to local communities? | No |
| 3.2 Would the Project pose potential risks to community health and safety due to the transport, storage, and use and/or disposal of hazardous or dangerous materials (e.g. explosives, fuel and other chemicals during construction and operation)? | No |
| 3.3 Does the Project involve large-scale infrastructure development (e.g. dams, roads, buildings)? | No |
| 3.4 Would failure of structural elements of the Project pose risks to communities? (e.g. collapse of buildings or infrastructure) | No |
| 3.5 Would the proposed Project be susceptible to or lead to increased vulnerability to earthquakes, subsidence, landslides, erosion, flooding or extreme climatic conditions? | No |
| 3.6 Would the Project result in potential increased health risks (e.g. from water-borne or other vector-borne diseases or communicable infections such as HIV/AIDS)? | No |
| 3.7 Does the Project pose potential risks and vulnerabilities related to occupational health and safety due to physical, chemical, biological, and radiological hazards during Project construction, operation, or decommissioning? | No |
| 3.8 Does the Project involve support for employment or livelihoods that may fail to comply with national and international labor standards (i.e. principles and standards of ILO fundamental conventions)? | No |
| 3.9 Does the Project engage security personnel that may pose a potential risk to health and safety of communities and/or individuals (e.g. due to a lack of adequate training or accountability)? | No |
| Standard 4: Cultural Heritage |  |
| 4.1 Will the proposed Project result in interventions that would potentially adversely impact sites, structures, or objects with historical, cultural, artistic, traditional or religious values or intangible forms of culture (e.g. knowledge, innovations, practices)? (Note: Projects intended to protect and conserve Cultural Heritage may also have inadvertent adverse impacts) | No |
| 4.2 Does the Project propose utilizing tangible and/or intangible forms of cultural heritage for commercial or other purposes? | No |
| Standard 5: Displacement and Resettlement |  |
| 5.1 Would the Project potentially involve temporary or permanent and full or partial physical displacement? | No |
| 5.2 Would the Project possibly result in economic displacement (e.g. loss of assets or access to resources due to land acquisition or access restrictions – even in the absence of physical relocation)? | Yes |
| 5.3 Is there a risk that the Project would lead to forced evictions? | No |
| 5.4 Would the proposed Project possibly affect land tenure arrangements and/or community based property rights/customary rights to land, territories and/or resources? | No |
| Standard 6: Indigenous Peoples |  |
| 6.1 Are indigenous peoples present in the Project area (including Project area of influence)? | Yes |
| 6.2 Is it likely that the Project or portions of the Project will be located on lands and territories claimed by indigenous peoples? | Yes |
| 6.3 Would the proposed Project potentially affect the human rights, lands, natural resources, territories, and traditional livelihoods of indigenous peoples (regardless of whether indigenous peoples possess the legal titles to such areas, whether the Project is located within or outside of the lands and territories inhabited by the affected peoples, or whether the indigenous peoples are recognized as indigenous peoples by the country in question)? If the answer to the screening question 6.3 is “yes” the potential risk impacts are considered potentially severe and/or critical and the Project would be categorized as either Moderate or High Risk. | Yes |
| 6.4 Has there been an absence of culturally appropriate consultations carried out with the objective of achieving FPIC on matters that may affect the rights and interests, lands, resources, territories and traditional livelihoods of the indigenous peoples concerned? | Yes |
| 6.5 Does the proposed Project involve the utilization and/or commercial development of natural resources on lands and territories claimed by indigenous peoples? | No |
| 6.6 Is there a potential for forced eviction or the whole or partial physical or economic displacement of indigenous peoples, including through access restrictions to lands, territories, and resources? | Yes |
| 6.7 Would the Project adversely affect the development priorities of indigenous peoples as defined by them? | No |
| 6.8 Would the Project potentially affect the physical and cultural survival of indigenous peoples? | No |
| 6.9 Would the Project potentially affect the cultural heritage of indigenous peoples, including through the commercialization or use of their traditional knowledge and practices? | No |
| Standard 7: Pollution Prevention and Resource Efficiency |  |
| 7.1 Would the Project potentially result in the release of pollutants to the environment due to routine or non-routine circumstances with the potential for adverse local, regional, and/or transboundary impacts? | No |
| 7.2 Would the proposed Project potentially result in the generation of waste (both hazardous and non-hazardous)? | No |
| 7.3 Will the proposed Project potentially involve the manufacture, trade, release, and/or use of hazardous chemicals and/or materials? Does the Project propose use of chemicals or materials subject to international bans or phase-outs? For example, DDT, PCBs and other chemicals listed in international conventions such as the Stockholm Conventions on Persistent Organic Pollutants or the Montreal Protocol | No |
| 7.4 Will the proposed Project involve the application of pesticides that may have a negative effect on the environment or human health? | No |
| 7.5 Does the Project include activities that require significant consumption of raw materials, energy, and/or water? | No |

Annex E-1 DRAFT INDIGENOUS PEOPLES PLAN

LEGAL FRAMEWORK FOR INDIGENOUS PEOPLES

In order to address the engagement and participation of Indigenous Peoples, the following international and domestic laws and regulations shall be taken into account.

The federal legal framework under which the Argentine state protects the human rights of indigenous peoples is made up of the following elements, in  hierarchical order: Argentine Constitution Article 75(17) and related provisions; international human rights declarations and treaties with a constitutional status, particularly international economic, social and cultural rights treaties and civil and political rights treaties, the American Convention on Human Rights and the International Convention on the Elimination of all Forms of Racial Discrimination (Argentine Constitution Article 75(22)); other duly ratified international covenants, ranking below the Constitution but above domestic law (Argentine Constitution Article 75 (22)); particularly the International Labour Organization Convention No. 169 concerning Indigenous and Tribal Peoples in Independent Countries (Argentine Law No. 24,071); specific domestic laws, particularly Law No. 23,302 providing for support to aboriginal communities (1985). Under Law No. 26.160/06, extended until 2021, the National Indigenous Peoples Institute (INAI) was instructed to carry out a Technical, Legal and Land Survey of the ownership status of the lands occupied by indigenous communities, and to adopt such measures as are necessary with the Indigenous Engagement Council (CPI); provincial aboriginal institutes; national universities; national, provincial and local bodies; indigenous organizations and non-governmental organizations. Provinces too may enact legislation as provided for in the final clause of the Argentine Constitution Article 75 (17). This has been interpreted to mean that the provinces may contribute to legally developing the law of the indigenous peoples and communities, provided that the minimum set of rights enshrined by federal legislation are recognized.

It should be noted that International Labour Organization Convention No. 169, in a chapter dealing with participation, imposes upon States a duty to consult with the peoples concerned, through appropriate procedures and in particular through their representative institutions, whenever consideration is being given to legislative or administrative measures which may affect them directly. For that purpose, mechanisms should be put in place so that indigenous peoples may participate to the same extent as other sectors of the population (Article 6 (a) and (b)). Additionally, Article 7 provides that indigenous peoples have a right to “decide their own priorities for the process of development as it affects their lives, institutions and spiritual wellbeing and the lands they occupy or otherwise use, and to exercise control over their own economic, social and cultural development.” In addition, the United Nations Universal Declaration on the Rights of Indigenous Peoples mentions Free, Prior and Informed Consent (FPIC) and constitutes an integral part of the human rights-based approach. Participation implies going beyond mere consultation and must lead to the concrete appropriation of projects by the indigenous peoples. The declaration specifically requires the specialized bodies and entities of the United Nations system (including the UNDP) to promote respect for, and full application of, the rights enshrined therein.

The effective implementation of the indigenous peoples’ right to consultation is relevant for a variety of reasons ranging from a strict respect for the rights established by domestic and international legislation to the construction of a community that respects diversity living in harmony with its environment. Thus, some of the main contributions of the respect of the indigenous peoples’ right to be consulted are the fact that it dignifies indigenous peoples; strengthens our democratic system and contributes to enforcing rights; helps build an inclusive, diversity-friendly citizenry; helps prevent and transform conflicts; and contributes to sustainable development.

### SOCIAL ASSESSMENT WITH INDIGENOUS PEOPLES AND PROJECT ENGAGEMENT PLAN

Consultations were carried out in Mendoza with authorities representing the communities and the organization of communities in Mapuche communities of Mendoza living in the Malargüe district. In Jujuy, work was carried out together with the Secretariat of Indigenous Peoples. Since 2016, Jujuy has a Secretariat of Indigenous Peoples, which is responsible for promoting and protecting the rights of the Indigenous Peoples, particularly guaranteeing the right to consultation. The Secretariat of Indigenous Peoples has come to act as a liaison body between public policies and governmental bodies on the one hand, and the indigenous peoples’ own existing processes, on the other; and has opened dialogue between those bodies and the indigenous peoples. Therefore, for PPG-related activities, requests for information, the identification of communities and the identification of appropriate measures for this and future project implementation stages have been carried out in consultation with the provincial project leaders and the Secretariat of Indigenous Peoples.

In all cases, a brief introduction about the framework of the project was provided, as well as the legal framework and the standards governing the project, including the rationale behind the Land Use Planning instrument which constitutes the core of the project. As already explained, the Land Use Planning —and the project itself— contain a participative and collaborative logic. Afterwards, and as information became available, the project was discussed in greater detail, emphasizing the various mechanisms for participation —at the national, provincial and pilot site level— and the specific consultation and participation stages that could be developed jointly with indigenous peoples.

In Mendoza, consultations were held with the “Werken” or spokesman, on behalf of the communities and the organization of the Mapuche communities of Mendoza in the Malargüe target landscape. In Jujuy, the PPG team worked with provincial authorities and the Secretariat of Indigenous Peoples, which is responsible for the promotion and protection of the rights of Indigenous Peoples in the province, and in particular to guarantee the right to Prior Consultation and FPIC. In both cases oral and general agreements with the project were obtained as well as their agreement to jointly develop during project implementation specific consultations before elaborating specific ELUP related interventions in the target landscapes.

Owing to the specific features of the project which require sustained negotiation, coordination and consultation processes as key elements of ELUP, during the initial year of the project, prior to designing specific plans to make the Environmental Land Use Planning operational, the appropriate consultation processes for each indigenous community involved in the specific activities will be designed for each pilot site. This is without prejudice to the information discussed below, which will form the basis for the coordination.

ENGAGEMENT, CONSULTATION AND FPIC PROCESSES IN THE TERRITORY

Social and Political Organization of Indigenous Peoples in Mendoza. In the Mapuche communities in Malargüe decisions are taken by an Assembly of Communities and the Council of Authorities of each Community. The ancestral political Authorities are the “Logko” (head - political authority), “Inan Logko” (Vice-president), “Werken” (messenger - spokesman) and “Kona” (warrior). The communities are grouped into political organizations or councils. In the case of Malargüe, they refer to Malalweche, i.e., the Territorial Organization of the Mapuche People. These communities and their political organization are ruled by a prior consultation protocol developed by Encuentro Nacional de Organizaciones Territoriales de Pueblos Originarios (ENOTPO, in Spanish). The organized Malargüe communities hold several prior consultation processes with the government and other actors. In particular, they have had experience participating in a land-use planning process with the Malargüe Municipality concerning a specific sector of “Cañada Colorada.” Besides, as mentioned above, Mendoza has been working on a land-use planning process for over 20 years, including an engagement element which has been tested, analyzed and improved. This included the implementation of prior consultation processes, which can be considered as experience to improve engagement practices in this project. For these reasons and due to the capacity of the Land-use Planning Agency to liaise with indigenous peoples and actors of the Municipality and other producers, locals are extremely willing to engage.

Social and Political Organization of Indigenous Peoples Communities in Jujuy. The Kolla, Omaguaca, and Atacama peoples have very similar political institutions in each community, such as the Community Council, the Council of the Elderly, and the Assembly. The differences lie in some specific attributes. Moreover, the families form social networks based on family bonds, godfatherhood, and neighborliness which reinforce their relationship system. The minga, which originated from a community tradition deeply rooted in the Andean world, is a form of cooperative and voluntary work which gathers several families or neighbors and is based, precisely, on a network system. If the work is performed for a single family, this family is to compensate it with similar work for those who cooperated with them.

According to the information obtained from the Indigenous Peoples Secretariat and other governmental actors working in the territory, even though the communities in the target landscapes of Jujuy do not have their own consultation protocol as do other communities in the province , they do maintain a close liaison with said Secretariat, which provides technical support for designing and developing consultation processes with the communities and FPIC when necessary, working as an intermediary in the dialogue between governmental entities, private actors and communities. The Secretariat has a specific area which provides guidance and support to communities in carrying out consultation processes.

In these communities, there are internal deliberative practices, sustained stages for liaison with governmental entities and processes for consolidation of the peoples’ capacities. which provide the proper conditions for timely implementation of an initial phase of the project, the processes named Consultation about the Consultation, i.e., adequate processes in each site to identify not only the procedure but also the topics and the number of consultations to be carried out based on the activities to be considered. For example, in Jujuy, a prior consultation process with communities of Quebrada de Humahuaca was conducted for holding a concert in the World Heritage site. In the case of Susques, jujuy, all ten communities involved follow a consolidated tradition of internal deliberation by means of a community assembly and a general assembly of ten communities. They also conduct a deliberation practice with authorities and actors of the private sector within the framework of community assemblies where Secretaries or Ministers are invited to participate, as well as high ranking officers of the company “Sales de Jujuy”, to carry out a dialogue on topics of interest for the communities. These extended assemblies are held once a month and attended by authorities and members of the ten communities. Minutes of such assemblies are drafted reflecting the items discussed and the agreements reached. Based on the experience gained by the consultant in its interaction with these communities, and the reference given by the Indigenous Peoples Secretariat, this dialogue and deliberation system will be an adequate space for developing the first stages of Consultation on the Consultation, when required to identify the proper mechanisms for addressing several issues or projects involving this pilot site.

In any case, in both sites a strong institutional presence is noteworthy in conjunction with a close liaison with local stakeholders, members of the indigenous communities, and other private actors (such as tourism service providers, mining companies, hygiene service providers, among others).

Additionally, all indigenous communities of the country have two indigenous representatives per People at the provincial level, who are appointed in a process entailing community assemblies convened by INAI, with whom they comprise the Indigenous Participation Council, which is a space for collaborative work and cooperation between the National Government and the indigenous peoples of Argentina. This space has the purpose of promoting participation of indigenous communities in the Land Surveying Programme –Law No. 26,160-; guiding communities in formulating development projects with cultural identity; strengthening communities in the organization and registration of their legal identity and participating in several consultation processes concerning public policies that might affect the interests of indigenous peoples.

SUPPORT CAPACITY

As part of the Capacity Strengthening Program to be implemented within the project, several participatory workshops will be carried out to work on enhancing information and strengthening capacities for several actors involved in the project. Some of the topics and practices to be discussed are as follows: Environmental Land Use Planning for government and civil society actors, as well as for indigenous peoples. A discussion will also be held to improve engagement practices and collaborative resolution of any disputes which may arise from discussions and dialogue on the use and regulation of practices involving territories. Moreover, and especially, another topic for discussion will be capacity strengthening for government and civil society actors on human rights and engagement practices, consultation and consent associated with the challenges and opportunities posed by this project.

GRIEVANCE MECHANISM FOR COMPLAINTS

The project will implement a comprehensive System for Prevention and Management of Consultations and Conflicts (SPCC, in Spanish). This system will comprise a specific structure for all cases in addition to a specific mechanism entailing adequate practices to address discrepancies, consultations or conflicts involving the Indigenous Peoples in connection with project activities. For these cases the mechanisms used by the communities to address disputes will be considered: for example, the Mapuche communities use a specific assembly method named Kumen Feley for their daily assembly practice and Nor Feley to solve disputes or conflicts and may be convened at the community level or at the community organization level.  In any case, besides primarily opting for managing and inquiring into the disputes concerning indigenous people’s practices, mechanisms will be implemented according to national and international laws related to indigenous peoples.

PLAN FOR INDIGENOUS PEOPLE’S ENGAGEMENT IN PROJECT IMPLEMENTATION

During the initial phase of project implementation, there will be consultations to discuss the later consultation processes to be carried out, i.e., adequate consultation processes will be implemented in each pilot site where indigenous peoples are identified to establish proper mechanisms for prior consultation and FPIC as applicable.

In the initial consultations on the consultation processes, meetings with indigenous communities will be held so as to design further consultation processes and at this initial stage the aim will be to identify:  the communities involved by the specific consultation topic, the topics or types of topics involving consultation processes in each project or specific area, decision-making mechanisms to be implemented, and the type of result (Prior Consultation or FPIC), internal or external advisors or technicians, as required, agreed relevant time periods, type of information (format, modality, access) to be considered for the relevant process; and any other matters to be identified and clarified as deemed necessary by the communities at the so-called Consultation on the Consultation stage.

In these consultation processes, the following general principles will be followed for engaging indigenous peoples in the project:

The project will seek, as the case may be, to follow the mechanisms established, within the framework of dialogue and in agreement with the communities involved. These rights are as follows: the right to engagement throughout the public policy making cycle, to prior consultation in regard to concrete legislative or administrative measures, and to free, prior and informed consent in specific cases which might affect fundamental rights or jeopardize their integrity.

- Engagement. Indigenous peoples’ representatives will take part in the phases of the project preparation, implementation and evaluation cycle, as well as in national, regional and local plans, policies and development programs resulting from said cycle and which may affect it, in order to ensure that their development priorities are taken into account, that the improvement of their life conditions is prioritized and that their integrity is not affected.  Decisions are made collectively among the indigenous peoples and the State, on the basis of processes for dialogue and understanding.

- Prior Consultation.  Under the aforesaid Convention No. 169, the State will implement good faith dialogue processes with indigenous communities before adopting concrete administrative or legislative measures which might affect them, with the objective of achieving agreement or consent through dialogue. Even though the decision is on the State, it must justify such decision.

- Free, Prior and Informed Consent. However, when their fundamental rights are affected, or the integrity of the peoples is at stake, in addition to the consultation, the state may only adopt the measure with the consent of those affected by it. In these cases, consent is not only the aim but also a requirement for the state to act.

Environmental Land Use Planning is essentially a participatory tool, and this principle will prevail in the process of identifying projects and any processes existing as of the date of implementation of the project, as well as existing dialogue processes and platforms and any sustainable production activities to be developed or prioritized.  The action lines outlined in the Project Document will be defined in detail during project implementation. Within this framework, the governmental authorities of the provinces involved will work through prior consultation at all times and free, prior and informed consent mechanisms, in such cases where activities to be implemented might imply: extraction of natural resources such as felling, mining or agricultural activities in their lands or territories; a decision affecting the State or people’s rights to their land/territories, resources or means of support; access to traditional knowledge and practices; commercial use of natural and / or cultural resources in plots of land subject to traditional ownership rights and / or low customary use by indigenous peoples; decisions regarding benefit allocation arrangements, where the benefits are derived from their land, territories or resources (for example, management of natural resources or extractive industries).

Within this framework, the Consultation, as well as any other participatory stage involving indigenous peoples must meet the basic requirements, i.e. It must be free, without coercion, intimidation or manipulation; prior, previous to adopting the measure subject to consultation; informed, as the State must provide the following information in order to make a decision: nature of the measure, reasons, duration, preliminary evaluation, risks and benefits, among others. The peoples have the right to inform the State about their priorities of life, cultural aspects, among others; in good faith, which implies the parties’ acceptance of the consultation procedure, the creation of a relationship based on trust and mutual respect, with the true objective of holding dialogue, which will allow them to make decisions and reach an agreement; through indigenous representative institutions, resulting from the indigenous peoples´ own and internal processes, whether traditional or modern, providing that they have been pre-established, that they are adequate and accessible, that is to say, according to customs and traditional methods for decision making, respecting symbols and images to represent them; moreover, the timing, language and manners inherent to each people must be respected, and the process must be systematic and transparent: it must be made in a formal and systematic manner -which might be repeated for another issue- and transparent, so that all the people involved are aware of the situation.

## Annex F:  Stakeholder Engagement Plan

LEGAL FRAMEWORK GOVERNING STAKEHOLDER ENGAGEMENT WITH ENVIRONMENTAL LAND USE PLANNING

The Argentine Constitution, international human rights and environmental law treaties, the General Law of the Environment and sector-specific laws setting out minimum environmental protection standards all incorporate the right to access to information, engagement in decision-making processes and access to justice for the protection of environmental rights.

Access to information as part of the engagement stage established in the General Law of the Environment for the Environmental Land Use Planning (ELUP) process represents a key factor of the process and all jurisdictional levels must comply with this requirement. Environmental Land Use Planning is outlined in Articles 9 and 10 of the General Law of the Environment, which set out the requirements that must be met under this novel conception of the tool which we have been developing:

ARTICLE 9. Environmental planning shall develop the functioning structure of the Argentine territory as a whole, and it is to be carried out through inter-jurisdictional coordination between local and provincial governments and between the city of Buenos Aires and provincial governments and the Argentine government, through the Federal Council of Environment Ministers (COFEMA). The environmental plan must seek to match the interests of the various sectors of society with one another and with the interests of the government.

ARTICLE 10. The environmental planning process must ensure the environmentally appropriate use of natural resources, afford maximum production and use of existing ecosystems, guarantee minimum degradation and waste, and promote society’s engagement with the fundamental decisions regarding sustainable development, taking into account the political, physical, social, technological, cultural, economic, legal and ecological aspects of local, regional and national realities.

Likewise, in locating anthropic activities and developing human settlements, the following aspects are to be taken into account and given first priority:

- The vocation of each area or region, based on its natural resources and social, economic and ecological sustainability characteristics; (b) the distribution of population and its specific features; (c) the nature and specific characteristics of existing biomes; (d) any alterations in the biomes resulting from human settlements, economic activities or other human activities or natural phenomena; (e) the preservation and protection of important ecosystems.

Law No. 26,331 on minimum standards for environmental protection of native rainforests provides that environmental planning is to be carried out with the engagement of relevant stakeholders.

Additionally, the Argentine law on minimum environmental policy standards considers the promotion of citizen engagement as one of its goals (Law No. 25,675/02 Article 2) and recognizes the right to participate. “Every person is entitled to be consulted and heard in any administrative proceedings involving the preservation and protection of the environment affecting either the general public or a portion thereof and having a general scope” (Law No. 25,675/02 Article 19). However, this Article refers to the right to engage but does not associate it with the right to decide. The provision establishes that “the opinion or objection of participants shall not be binding on the authority requesting such opinion” (Law No. 25,675/02, Article 20), although the authorities must justify and publicly show any reasons for setting aside the citizens’ opinion.

Among the minimum standards laws, Law No. 25,831 on Access to Public Environmental Information is worth noting. Said law safeguards the right of every person to obtain environmental information owned by local and provincial governments, the national government or the government of the City of Buenos Aires, or by independent government agencies and public service companies, whether state- or privately-owned, or both.

It is also worth noting that the Access to Public Information Law No. 27,275, which was recently enacted (in September 2016), regulates access to public information, a key citizen participation tool which is crucial for transparency and oversight of governmental action. The law imposes a duty upon the three branches of government, the Public Ministry, companies, political parties, universities and workers’ unions receiving public funds to answer any requests for information made by citizens within a month.

With regard to provincial laws, Mendoza is the first Argentine province to have a Land Use Planning Law, enacted on May 5, 2009 following a period of 20 years in which draft bills were introduced but failed to reach a consensus; the statute represents a landmark in the history of the province and the whole country. The enactment has placed the province at the forefront of participative lawmaking, breaking the stalemate of conflicting sectorial interests, with a view to achieving a common collective construction. The law establishes the development of a participative, inclusive and democratic space providing legitimacy and sustainability to the process of making and executing the plans.

The province of Jujuy enacted provincial General Environmental Law No. 5063 and provincial Adaptive Land Use Plan for Forest Areas Law No. 5676, and it there is a land use planning bill that is being debated in the provincial legislature. In the province of Buenos Aires, Decree-Law No. 8912/77 on Land Use Planning is in effect, and Provincial Environmental Law No. 11723 has been enacted. Law No. 1496/08 is also relevant, as it establishes an Inter-ministerial Urban and Land Use Planning Commission.

STAKEHOLDER ENGAGEMENT PLAN

General Principles

Two key elements are to be considered to tackle this subject: on the one hand, engagement, and on the other hand, the concept of collaboration or collaborative processes. Engagement is a complex process of human interrelations including opinion, analysis, reflection, confrontation, discussion, dialogue, consensus and joint decision-making to achieve the purposes established by all.

The different elements of the project and ELUP as a tool give rise to a dual engagement expectation, as set forth in the General Law of the Environment, consisting of the identification and creation of proper inter jurisdictional coordination mechanisms amongst the country, the provinces and the municipalities to implement the project and, also, the concurrence of the different sectoral interests of society, as well as of these interests with the public administration (pursuant to art. 9 GLE), promoting social engagement in key decisions of sustainable development (pursuant to Art. 10 GLE). Therefore, the implementation of this project requires a multi-sectoral, multi-disciplinary and multi-level approach.

There are different forms of engagement involving different stakeholders, and so it is important to identify such differences. For this reason, it is recommended that these differences be conceptualized as Collaborative Processes involving individuals and groups with different perspectives and interests on a given matter so that they may work together through dialogue, helped by a third party, on an agenda of common interest and with specific objectives.

When suggesting a collaborative process (or collaborative space) it is essential that its purposes and scope be clarified. It may only be intended to promote Dialogue to gather different perspectives, inquire, expand, share information and views, create a shared understanding and identify disagreements. It may go a step further and propose a space for Discussion to share arguments, identify potential solutions and make suggestions. Lastly, in terms of Decision-making, it is essential to measure its impact on decisions and decision makers: decisions are made by an authority who is not a part of this group (consulting-advisory group), or made, on some or all issues, by the group itself through negotiation, consensus or vote.

Finally, another distinctive element in collaborative processes are the basic conditions for their establishment and operation. Spaces designed within the project framework must regularly verify that conditions are met and, upon modification, provide for the relevant corrections:

- Political will. The legitimate and sustained will of the political stakeholders involved and their commitment to the space. Experience shows that not only an initial manifestation of will is required (access to and implementation of the initiative) but also an ongoing display of interest and determination in the process, showing signs that the initiative is legitimated not only through the allocation of logistical or technical resources but also through other signs of appropriation (communication actions, participation of their political and technical teams at work meetings, among others).

- Reliable organizers. Usually, several organizers are involved. A condition for good dialogue is that those who extend the invitation to dialogue be individuals or institutions with some sort of knowledge and legitimacy in the opinion of all the parties involved. Given that it is difficult for a single individual or institution to be reliable in the eyes of all sectors, it is usually recommended that a group of organizers be created to provide the initial characteristics of legitimacy and reliability that are necessary for the sectors to feel welcome to take part in the dialogue and so as to guarantee that different perspectives are taken into account when thinking the space up.

- Inclusion. It is important that the stakeholders (individuals and organizations) that will be taking part in the space be carefully identified, in order to include all relevant parties. This involves different challenges: evaluating if they will have decision-making capabilities or if all interested parties will be invited to participate. There are different ways to define participation, which is closely related to the objectives of the space and what they seek to achieve.

- Power balance: This should also be assessed, in order to act based on the relative power condition of each sector. In some cases, face-to-face dialogue will not be possible until actions to balance the power and capabilities of each group are carried out for them to be able to take part in the space. In other cases, imbalances that may not be reduced to participate in the dialogue will have to be expressly recognized, thus seeking transparent mechanisms to work on them (such as mechanisms that are more bilateral, spaces for mediation or other alternatives).

- Generation and communication of understandable, accessible, relevant and reliable information for all stakeholders, as an element that strengthens and enriches discussion and decision making. In this sense, land information must be generated and periodically updated, public information provided by different sources must be coordinated based on the competency of the different public entities, the complexity of the technical studies related to land uses must be translated into a simpler and more accessible language, and mechanisms to guarantee transparency in terms of the concession and environmental and economic regulation of production activities must be established.

- Process logic. Design and facilitation. It is essential that these types of processes and spaces be carefully designed and facilitated, considering their existence within an extended temporary framework, suitable for the generation of changes not only in structures (laws or policies) but also in cultural aspects. Their design involves assessing the situation, identifying objectives, expected outcomes, activities, planning meetings, defining game rules, mapping stakeholders, and the need to take into account temporary factors to achieve changes. Facilitation (or coordination) is a key role that makes it possible for the space to continue to exist, to keep focusing on objectives and to ensure that the identified goals are reached at each meeting, thus ensuring that process conditions are met.

- Conflict sensitivity. ELUP implies a complexity of interests that may benefit from or be affected by the decisions made. The tool can have an impact on structural and current issues that could imply conflicts in social-environmental matters. This is the reason why it is important to take these conflicts into consideration, seeking to implement prevention strategies whenever possible, or otherwise seek alternative ways to manage said conflicts. In any case, it is recommended that these conflicts be tackled in a sensitive manner in order to avoid their worsening and to prevent them from having a negative impact on the project.

- Cultural sensitivity. Dialogue processes must be sensitive to cultural factors in particular. Specific aspects related to Indigenous Peoples and gender will be discussed below. It will suffice to say here that some of these factors may modify substantive aspects of dialogue spaces, such as the timeframe, accessibility of information, participation logic, etc.

RELEVANT STAKEHOLDER ENGAGEMENT MECHANISMS

#### During the PPG phase:

During the PPG phase, key stakeholders participated in project planning and design workshops and focus group meetings.  These participative fora included: a) PPG inception workshop; and b) multiple individual meetings and consultations with key national and local institutions, UNDP Argentina and the national authorities of the Secretariat of Environment and Sustainable Development (SGAyDS in Spanish).

- During the PPG phase, a close relationship was built with national and local stakeholders. National, provincial and local institutions participated directly in project development. Several consultations were made with multiple stakeholders to discuss the different aspects of project design, namely: an inception workshop was held in May 2018 with the participation of the national authorities of MAyDS and the provincial environmental agencies, particularly, national technicians of the National Directorate of Planning and Environmental Land Use Planning and the National Directorate of Biodiversity of MAYDS; provincial Land Use Planning technicians of Mendoza, Jujuy and Buenos Aires, the National Agricultural Technology Institute (INTA, in Spanish) national and regional offices of Buenos Aires, Mendoza and Jujuy, UNDP representatives and PPG consultants.

- Several provincial workshops were held with local authorities, members of INTA’s regional office and other civil society actors:

  - June, July and August 2018, Buenos Aires: a meeting was held at the Provincial Agency for Sustainable Development (OPDS, in Spanish) with technicians of the organization and INTA, as well as the team of PPG phase consultants.

  - June, July and August 2018, Mendoza: several meetings were held in Mendoza with national authorities and environment technicians of the Land Use Planning Agency and INTA. Several meetings were held in Malargüe with municipal authorities, local actors, mapuche peoples, and technicians from INTA’s Malargüe office. Also, meetings on site were held to present the project and liaise with local actors in Uco Valley, in the Green Belt area and Malargüe.

  - June, July and August 2018, Jujuy: several meetings were held in San Salvador de Jujuy with national authorities and environment technicians of the Secretariat of Indigenous Peoples of Jujuy, the Secretariat of Production, Tourism, the Management Unit of Quebrada de Humahuaca, the Secretary of Family Agriculture and INTA.

- Additionally, during the PPG phase the project team, the UNDP country office staff, and SGAyDS staff held multiple focus group meetings and consultations with national, provincial and local key actors. Meetings were held with the Secretary of Environmental Policy on Natural Resources, the National Directorate of Biodiversity of SGAyDS, the National Directorate of Forest Protection of SGAyDS, the National Directorate of Water Resources of SGAyDS, with UN REDD and the National Directorate of Planning and ELUP of SGAyDS. Meetings were held with the staff responsible for projects and methodologies related to this project such as Ecoser, GEF Sustainable Use of Biodiversity Project (USUBI), TSA methodology, several representatives of Banco Galicia, and the World Bank Project named “Increasing Climate Resilience and Improving Sustainable Land Management in the South-west of Buenos Aires Province.”

- Also, meetings were held with national civil society organizations such as Fundación Vida Silvestre and Fundación Cambio Democrático.

#### During project implementation:

During the PPG stage, the form of intervention was analyzed from the perspective of three work levels (national, provincial and pilot sites). In order to facilitate liaison and engagement, cooperation agreements will be signed with the governmental entities handling the different areas involved in Environmental Land Use Planning (relevant actors associated with planning specifically, as well as with biodiversity, protected areas, tourism, culture, indigenous peoples, production, among others). A liaison will be made with actors who have already started such processes in order to leverage existing processes and projects, as well as to improve and escalate them.

Stakeholder Mapping

During the PPG phase a Stakeholder Map was put together that identified the relevant stakeholders for the project, namely the people, groups or institutions whose participation is essential and required for fulfilling the purpose, objectives and goals of the initiative to be developed. In different ways, these key actors have the power, capacity and means to decide upon and influence the critical areas that will allow or hinder the development of a proposal. The relevant actors are characterized by some of the following factors:

1) They form part of the community where the situation analysis was undertaken and they represent legitimate interests of a group, or are actors that will be directly benefited or affected by the project’s actions;

2) Their roles and responsibilities are directly in line with the project´s objectives;

3) They have the capacities, skills, knowledge, infrastructure and resources to identify, address and solve scientific and technical problems;

4) They have financing mechanisms or could donate resources;

5) They have managerial and negotiating capacity with the various agents and/or with different levels of government to help build consensus and reach agreements.

Table 1 below identifies the relevant actors, their role in the implementation of the project, and the project components in which they will participate.

Table 1. Stakeholder Matrix

| Organization | Role/Responsibility in Project | Participation in Components of the Project |
| --- | --- | --- |
| National level |  |  |
| Secretariat for the Environment and Sustainable Development - National Directorate of Environmental Land Use Planning under the Ministry of Environmental Policy in Natural Resources (SAyDS) | Implementing Partner. Co-financier. Member of the Project´s Board and Technical Committee. Leadership and convening of partner institutions and participants in the implementation of the project. The institution where the project will physically be carried out. Its main role will be that of coordinating with other organizations and of leading the different stages of the project’s execution. Member of dialogue platforms. Will participate in the M&E of the project. | C1, C2, C3, C4 |
| National Agricultural Technology Institute. Ministry of Agribusiness of the Nation. (INTA) | Its presence throughout the country and its technical capacity will be of great importance in the development and application of innovative instruments and in the development of ELUP (Environmental Land Use Planning). It runs programmes throughout the country with farmers, peasant communities and indigenous peoples. It will bring concrete knowledge to the project regarding modes of production in use, alternative production techniques, sustainable production developments and technical knowledge regarding production in general. The project will benefit from INTA´s access to the territory and INTA in turn will benefit from information generated by the project regarding concrete alternative production experiences. Member of national and provincial dialogue platforms and of sustainable commodities platform, participation in work teams at pilot sites. Member of the Technical Committee | C1, C2, C3 |
| Federal Council of Environment Ministers (COFEMA) | Analysis and dialogue about ELUP policies and legal frameworks and the necessary interjurisdictional coordination. Participation in dialogue platforms through committees. Dissemination to promote the replication of experiences and lessons learned throughout the country | C1, C3 |
| National Advisory Committee for Conservation and Sustainable Use of Biological Diversity. (CONADIBIO) | Its role in the project will be that of consultation and dialogue on relevant ELUP matters linked to biodiversity. Participation in dialogue platforms and sustainable commodities platform | C1 |
| National Council for Technical and Scientific Research. (CONICET) | It will have a consultative role in the project through departments or researchers focused on the project´s subject matters. Participation in dialogue platforms | C1 |
| National Parks Administration. Ministry of Environment and Sustainable Development (APN) | The APN will have special relevance in the national and provincial dialogue spaces, and it will also be able to help access protected areas, as well as provide knowledge about the land and the needs of the most isolated populations in pilot sites. Participation in national and provincial dialogue platforms and support for work teams in pilot sites that include national parks | C1, C2, C3 |
| National Observatory of Land Degradation and Desertification under the Ministry of Environment and Sustainable Development (ONDTyD) | As well as having a consultative role in the project through participation in dialogue spaces at the national level, it will also contribute valuable relevant information associated with the project´s indicators. | C1, C2, C3 |
| National Biodiversity Observatory in the Ministry of Environment and Sustainable Development (OBIO) | As well as having a consultative role in the project through participation in dialogue spaces at the national level, it will also contribute valuable relevant information associated with the project´s indicators. | C1, C2, C3 |
| National Indigenous Peoples Institute of the Ministry of Justice and Human Rights (INAI) | Due to the presence of indigenous peoples in the territory of the Project’s pilot sites, and the role of indigenous peoples’ policies in the overall ELUP framework, they are included as consultative actors for national dialogue spaces and they can offer support in the territory through the CPIs and also by providing information on several issues, such as the hierarchical structure of communities, ancestral modes of production, the role of women within the community, among others. | C1, C2 |
| Environment and Natural Resources Foundation (FARN) | Its role in the project will be of a consultative nature in national multisectoral dialogue spaces, and it will be able to offer its knowledge and experience in the surveying and analysis of ELUP matters | C1 |
| Democratic Change Foundation (FCD) | Its role in the project will be of a consultative nature in national multisectoral dialogue spaces, and it will be able to bring its knowledge and experience to participation issues related to ELUP. | C1 |
| Wildlife Foundation (FVS) | Its role in the project will be of a consultative nature in national multisectoral dialogue spaces and it will be able to provide knowledge and experience on environmental issues and work in the territory. | C1 |
| Provincial Level |  |  |
| Universities National Universities of Cuyo, Jujuy, Buenos Aires and La Plata | They will participate in an advisory role, providing technical and scientific knowledge that will lead to the identification of relevant criteria for ELUP. At the same time, they may also facilitate the dissemination of the knowledge arising from the project by incorporating it into university curricula, scholarships, forums, talks and presentations and by coordinating with the departments for continuing education at each university. In the territories, the universities play relevant roles as parts of existing platforms or committees with which the project will work. | C1, C2, C3 |
| Provincial Governments Mendoza: Ministry of Environment and Land Use Planning of Mendoza - Provincial Land Use Planning Agency Buenos Aires: Provincial Agency for Sustainable Development Jujuy: Ministry of Environment - Directorate of Environmental Land Use Planning and the Secretariat of Biodiversity. | Co-financiers. Members of the Project Board, Technical Committee and Provincial working groups. They will have the role of implementing the project at the provincial level and pilot sites in coordination with MAyDS. They will provide the necessary tools for the management and coordination of project activities with the different provincial agencies as they are incorporated during the course of the project. Members of the provincial dialogue spaces and the sustainable commodities platform. Replication of experiences and lessons learned at the provincial level. | C2 |
| Municipalities: Mendoza: Malargüe, Mendoza Capital, San Carlos, Las Heras, Tunuyán, Tupungato, Luján de Cuyo, Godoy Cruz. Jujuy: Departments of Susques, Humahuaca and Valle Grande. Buenos Aires: Campana, San Fernando, Magdalena, Punta Indio, Chascomús, Lezama, Castelli, Villarino and Carmen de Patagones. | They will be involved in the teams or multisectoral work spaces at the pilot site level. They will participate in the implementation of the initiative at the local level, fostering communication and participation with the territory´s key actors, and they will also have a consultative role in relation to ELUP actions in the territory, promoting an effective ELUP approach in their jurisdictions, helping to resolve conflicts of use, and facilitating dialogue between the parties. Members of provincial dialogue platforms and (relevant) sustainable commodities platform and members of work teams in pilot sites | C2 |
| General Department of Irrigation of Mendoza (DGI) | It will take on an advisory, consultative role and will also be key in the identification of instruments and actions at the pilot sites level due to the special relevance of water as a resource in the province and the self-sufficient nature of the department. Members of the provincial dialogue spaces | C2 |
| Water Authority in the Ministry of Infrastructure and Public Services of Buenos Aires (ADA) | Its role will be consultative and it will provide information at a local level through the basin advisory committees. They have gathered information about ecosystem services. Member of the provincial dialogue spaces | C2 |
| Buenos Aires Revenue Agency (ARBA) | Its role will be consultative given that it has digitized georeferenced information but it will also support field work due to the precise information in its possession and its territorial reach. | C2 |
| Ministry of Infrastructure of the Province of Buenos Aires (MIPBA) | Its role will be consultative and one of interinstitutional coordination, in particular through its provincial directorates of Risk Management and Emergencies, and Land and Urban Planning. Member of the platform for provincial dialogue spaces | C2 |
| Territorial Organization of the Mapuche People "Malaweche" and Mapuche Indigenous Communities from Malargüe - Mendoza | Their role in the project is key because they will be leading figures in the preliminary consultations to define ELUP-related actions in their territories. In this regard, they will provide the project with key information on production methods and conditions in the territory, the environmental, economic and social challenges they face and on working with other local actors. In terms of the benefits that the communities that participate in the project will obtain, they will principally benefit from better production conditions, improvements in the ability to work alongside local actors, and participation in the definition of local ELUP policies. Participation in the provincial dialogue platform. Dissemination of experiences and lessons learned to other communities in the province. Participation in local work team or multisector space for the implementation of the project at the pilot site. Will grant consent to project interventions in their territories through prior consultation processes at all times and FPIC in those cases that may affect their rights and interests, lands, resources, territories | C2 |
| Association of Bolivian Producers of Mendoza (APBM) | Their role in the project will be to participate in local dialogue spaces, in training spaces, and eventually in the benefits arising from improvements of practices linked to ELUP. | C2 |
| Actors from the wine sector (COVIAR or Bodegas Argentinas A.C.) of Mendoza | Their role in the project will be to participate in local dialogue spaces, in training spaces and eventually in specific actions related to the restoration of native biodiversity. | C2 |
| Indigenous Communities from the territory in the Province of Jujuy of the Atacama, Omaguaca and Kolla peoples in Jujuy | Their role in the project is key because they will be leading figures in the preliminary consultations to define ELUP-related actions in their territories. In this regard, they will provide the project with key information on production methods and conditions in the territory, the environmental, economic and social challenges they face and on working with other local actors. In terms of the benefits that the communities that participate in the project will obtain, they will principally benefit from better production conditions, improvements in the ability to work alongside local actors, and participation in the definition of local ELUP policies. Participation in the provincial dialogue platform. Dissemination of experiences and lessons learned to other communities in the province. Participation in local work team or multisector space for the implementation of the project at the pilot site. Will grant consent to project interventions in their territories through prior consultation processes at all times and FPIC in those cases that may affect their rights and interests, lands, resources, territories | C2 |
| Qhapac Ñam Management Unit in Jujuy (UGCÑ) | At the pilot site, this unit will have an advisory role and it will also be crucial for coordinating activities where there is an overlap between the unit´s plans and the project management. Participation in the provincial dialogue platform. Dissemination of experiences and lessons learned to other communities in the province. Participation in local work team or multisector space for the implementation of the pilot site project | C2 |
| Quebrada de Humahuaca Management Unit in Jujuy (UGQH) | Participation in the provincial dialogue platform. Dissemination of experiences and lessons learned to other communities in the province. Participation in local work team or multisector space for the implementation of the pilot site project | C2 |
| CEBIO - Jujuy | Their role in the project will be advisory, participating in local dialogue spaces, in training spaces and eventually in working jointly with local actors. Participation in the provincial dialogue platform. | C2 |
| Proyungas Foundation - Jujuy | Their role in the project will be advisory, participating in local dialogue spaces, in training spaces and eventually in working jointly with local actors. Participation in the provincial dialogue platform. | C2 |
| Foundation for the Conservation and Sustainable Use of Wetlands / Wetlands International Argentina- Buenos Aires (FH) | Consultative in relation to participation in provincial dialogue and active in relation to the wetlands at the Buenos Aires pilot site. Participation in the provincial dialogue platform. Participation in local work team or multisector space for the implementation of the pilot site project | C2 |
| Félix de Azara Natural History Foundation (FHNFA) | Consultative in relation to participation in provincial dialogue and active in relation to the “Talares” forests at the Buenos Aires pilot site. Participation in the provincial dialogue platform. Participation in local work team or multisector space for the implementation of the pilot site project | C2 |
| Council of Producers of the Delta (CONPRODEL) | Consultative in relation to participation in provincial dialogue and active in relation to the wetlands at the Buenos Aires pilot site. Participation in the provincial dialogue platform. Participation in local work team or multisector space for the implementation of the pilot site project | C2 |
| Argentine Forest Association - Regional Delta (AFOA) | Their role in the project will be consultative, participating in local dialogue spaces, in training spaces and eventually working in coordination with local actors. Participation in the provincial dialogue platform. Participation in local work team or multisector space for the implementation of the pilot site project | C2 |
| Other provincial and local grassroots and social organizations | They will participate in activities such as multisector dialogue platforms, the development of SLM practices, as well as practices related to the conservation of ecosystem services and biodiversity, and ELUP practices. Their role will also be important in facilitating the replication of good ELUP practices. | C2 |
| Provincial Council for Land Use Planning of Mendoza | It will have a key role in the coordination of spaces for dialogue and in coordinating the instruments, plans and actions of the ELUP at the provincial level. Its members will also provide relevant information, and they will provide support through their communication and advocacy skills on ELUP matters. It is the basis of the provincial dialogue platform on ELUP. | C2 |

Stakeholder Engagement Mechanisms

In order to engage the relevant project stakeholders, in compliance with the social safeguards and the principles set out above, work will be carried out with the following components, key stakeholders, phases, and programs:

  - Communication (Com) and capacity building (Cap) for informed participation

  - Creation of dialogue mechanisms (consultation, deliberation, decision making, inter-institutional coordination, and use of existing spaces) (Part)

  - Creation of conflict prevention and management mechanisms (provision for negotiation, mediation, requests for information, complaints) (PrevCon)

Each component or program of stakeholder engagement will be deployed in three differentiated phases: planning, implementation, and assessment. Project planning will include annual meetings with key stakeholders from the national, provincial, and local government, the civil society, the local communities (including members of the Project Board). During such meetings, the annual goals for each project component will be outlined. Such annual planning meetings will also specify which activities are to be financed by means of each co-financing source. The project will be implemented according to the annual plans to be approved by the Project Board. The SGAyDS will be the Implementing Partner.

The Stakeholder Engagement Plan will be implemented by the Project Management Unit or by such local or provincial teams as may be deemed appropriate for it. The above programs are set out below:

Communication and Information Program (“PCI” in Spanish) (Output 4.2)

The purpose of this program will be to design and develop the Project communication and information policy at the national level, and to coordinate this policy at the local and provincial levels for its general alignment. This program will be coordinated and developed by a Communication Specialist of the SGAyDS, who will work in close coordination with the Project Management Unit, project specialists and provincial peers in implementing any relevant actions.

Three dimensions will be coordinated in this program: a) design and implementation of a project dissemination policy, to raise awareness on ELUP-related matters, to account for project progress and the results of the monitoring activities, among others. The instruments and activities which may be used by this program include, without limitation: development of web sites, brochures, or flyers, videos, radio/TV broadcastings; b) managing technical information regarding ELUP and processing it to develop communication products to provide key stakeholders with information that is reliable, clear and accessible; and c) systematization of the information arising out of the project, in order to manage the knowledge gained, systematize data from the project, and provide inputs for learning and adjustments in the monitoring process. All the dimensions will be implemented in coordination with the program and the jurisdictional level supported.

This program will ensure:

•         Timely dissemination of information on social and environmental implications of the project before decisions are taken.

•        Easy access to information so that the project stakeholders may easily access the information related to the project activities. To that effect, the suitable media for each territory will be considered; for instance:  postings on websites, public meetings, local organizations or boards, newspapers, radio and television reports, flyers, exhibitions, direct mail.

•       Appropriate formats and languages: The information must be made available in a language which may be understandable and accessible for the group in question. To that effect, local information dissemination media and formats will be taken into account.

Capacity Strengthening Program for ELUP (“PFC” in spanish) (Outputs 1.4, 2.2 and 3.2)

This program will be responsible for cross-sectional coordination of capacity strengthening on different critical issues in furtherance of the success of the project. This entails designing a federal program which will be aimed at strengthening the capacities of state actors (from several local, provincial, and national organizations), of relevant actors from civil society, including academia, the private sector, small local farmers, and indigenous peoples, among others. The Capacity Strengthening Program will outline the curricula of tailor-made capacity strengthening and formation processes, on the basis of the evaluation of needs to be carried out; identify the target audiences in each case; and design suitable devices for such audiences. The activities may include workshops, seminars, online courses, scholarships on existing courses, specific information conferences. The key issues on which the Capacity Strengthening Program must be focused are: ELUP in general as a tool, specific biodiversity issues, SLM, means of subsistence, key aspects of social participation, skills, and tools for conflict resolution and participation. In particular, the Capacity Strengthening Program will ensure that the generation of capacities to work with Indigenous Peoples, the understanding of the legal framework, and the prior consultation processes and free, prior and informed consent are mainstreamed in the project.  The Capacity Strengthening Program will deploy different kinds of activities, based on the needs of the target audiences, the jurisdictional level, or the subject needs. Such activities will include, without limitation:

Multi-stakeholder Coordination and Dialogue Spaces for ELUP (Outputs 1.4 and 2.2)

Spaces will be provided for the creation of multi-sectoral dialogue mechanisms as well as horizontal (among institutions at the same level of government) coordination mechanisms and vertical (among the national, provincial, and municipal levels) coordination mechanisms. The creation of participatory dialogue spaces is promoted, which may provide for differentiated decision making, negotiation, and dialogue spaces/processes, depending on the scale, jurisdiction, and responsibilities. Such a structure may generate inter-sectoral and inter-jurisdictional coordination mechanisms to integrate ELUP in sectoral programming, and it may also generate proposals to coordinate several jurisdictions and sectors to prepare and implement plans, programs, and projects related to ELUP, sectoral planning, and integration of provincial ELUP in the federal programs, and multi-sectoral decision making which makes the implementation of ELUP easier. Furthermore, it will generate higher coordination among local communities and governments and will increase their efforts to provide for a broader participation in monitoring and surveillance activities to support sustainable production.

These spaces will make use of the existing mechanisms at the national and provincial levels where appropriate.  At the provincial level, the existing experiences will be considered as a starting point to identify coordination spaces: in Mendoza, for example, the dialogue platform may take advantage of the existence of the Provincial Council for Land Use Planning of Mendoza (CPOT), a multi-sectoral consultation space which must be strengthened by an enhanced stakeholder mapping on the basis of this project, or, Cañada Colorada Territorial Land Use Planning, located at a limited portion of the polygon at the pilot site at Malargüe river basin, which has included the Land Use Planning and Environmental Council in its multi-sectoral and local composition implementation plan. In Jujuy there are several local multi-sectoral coordination experiences, such as the Qhapac Ñam Management Unit, or the Local Committees in the Quebrada de Humahuaca, even though a specific coordination space will be generated for the province and the pilot sites. In Buenos Aires, there has been a previous experience, consisting of the Inter-sectoral Round Table for Land Use Planning of the Province of Buenos Aires, which was operational until June 2017, with a work history of more than one year and internal operational regulations, a multi-sectoral composition which could be used as previous experience, in spite of the fact that the type of framework which governs its operation entails certain complexity for reactivation. It is suggested that the regulatory framework set by Executive Order No.1496/08, which provides for the creation of a Commission for Urban and Territorial Land Use Planning of Buenos Aires be considered. In view of the characteristics of the instrument, several mechanisms must be identified to extend its composition or outline multi-sectoral spaces to leverage its operation. There has been another experience in Buenos Aires referred to as the Territorial Land Use Planning Process of the Municipality of Balcarce, which was the first territorial land use planning experience in the province, which may be useful to identify and exchange lessons learnt. Dialogue experiences in environmental territorial planning, land use planning, and other experiences which may be useful to identify lessons learned, key stakeholders, and relevant information will also be considered.

The activities carried out by the dialogue spaces may be different: ordinary activities include plenary dialogue sessions, based on clear work agendas. The dialogue spaces may also work on technical committees (officers’ committees, scholars committees, sectoral committees, or topic-based committees). All the sessions held must be facilitated by a third party able to implement a detailed agenda containing collaborative work methodologies which may make it possible for working teams to attain the goals set in general and in particular. Irrespective of the regular members who form the dialogue space, on the basis of the dialogue and expression needs of other stakeholders, the development of open activities or extended sessions with other social stakeholders in different formats may be considered (public audiences and exchange sessions with legislative branches of government, among others).

These multi-sectoral participation spaces at the provincial level, and the level of the pilot sites will include the participation of Indigenous Peoples’ representatives. Nevertheless, the necessary consultation processes, whenever they are related to project activities on Indigenous Peoples’ territories must be implemented according to guidelines on Indigenous Peoples below.

Sustainable Commodities Platform (beef) (Output 2.2)

The project will foster the creation of a sectoral platform at the provincial level, to call and coordinate the private and public sector actors in order to promote the sustainable production of beef; define prospective policies and approaches to comply with the ELUP in priority areas; and reach an agreement on possible instruments and minimum standards. The sectoral platform will support the promotion of sustainable beef through a differentiated approach to producing in environmentally vulnerable areas. The platform will rely on the UNDP’s experience in developing commodity platforms, by providing guidelines and lessons learned to foster dialogue among multiple interested parties and to provide the experience and the analysis required to expand the action to other areas of the country. Coordination will be based on similar approaches of the supply chain for products backed by GEF funds in other countries of the region, such as Brazil, Paraguay, Peru, and Ecuador. In particular, this platform will generate a a solid dialogue space, sustained in time so that the sector may analyze, debate, and build consensus on alternatives, to develop joint actions to mitigate any negative impact of the reforms to be introduced and identify ways of maximizing production. The platform will prepare an Action Plan for Sustainable Beef Production.

##### System for Prevention and Management of Consultations and Conflicts (SPCC)

A System for Prevention and Management of Consultations and Conflicts  will be developed as an early warning system to address discrepancies, consultations or conflicts in connection with project activities. The system will address: 1) inquiries, doubts and/or suggestions regarding project implementation; and 2) a grievance redress mechanism for prevention and management of grievances, problems or conflicts.

INDIGENOUS PEOPLES PLAN

LEGAL FRAMEWORK FOR INDIGENOUS PEOPLES

In order to address the engagement and participation of Indigenous Peoples, the following international and domestic laws and regulations shall be taken into account.

The federal legal framework under which the Argentine state protects the human rights of indigenous peoples is made up of the following elements, in  hierarchical order: Argentine Constitution Article 75(17) and related provisions; international human rights declarations and treaties with a constitutional status, particularly international economic, social and cultural rights treaties and civil and political rights treaties, the American Convention on Human Rights and the International Convention on the Elimination of all Forms of Racial Discrimination (Argentine Constitution Article 75(22)); other duly ratified international covenants, ranking below the Constitution but above domestic law (Argentine Constitution Article 75 (22)); particularly the International Labour Organization Convention No. 169 concerning Indigenous and Tribal Peoples in Independent Countries (Argentine Law No. 24,071); specific domestic laws, particularly Law No. 23,302 providing for support to aboriginal communities (1985). Under Law No. 26.160/06, extended until 2021, the National Indigenous Peoples Institute (INAI) was instructed to carry out a Technical, Legal and Land Survey of the ownership status of the lands occupied by indigenous communities, and to adopt such measures as are necessary with the Indigenous Engagement Council (CPI); provincial aboriginal institutes; national universities; national, provincial and local bodies; indigenous organizations and non-governmental organizations. Provinces too may enact legislation as provided for in the final clause of the Argentine Constitution Article 75 (17). This has been interpreted to mean that the provinces may contribute to legally developing the law of the indigenous peoples and communities, provided that the minimum set of rights enshrined by federal legislation are recognized.

It should be noted that International Labour Organization Convention No. 169, in a chapter dealing with participation, imposes upon States a duty to consult with the peoples concerned, through appropriate procedures and in particular through their representative institutions, whenever consideration is being given to legislative or administrative measures which may affect them directly. For that purpose, mechanisms should be put in place so that indigenous peoples may participate to the same extent as other sectors of the population (Article 6 (a) and (b)). Additionally, Article 7 provides that indigenous peoples have a right to “decide their own priorities for the process of development as it affects their lives, institutions and spiritual wellbeing and the lands they occupy or otherwise use, and to exercise control over their own economic, social and cultural development.” In addition, the United Nations Universal Declaration on the Rights of Indigenous Peoples mentions Free, Prior and Informed Consent (FPIC) and constitutes an integral part of the human rights-based approach. Participation implies going beyond mere consultation and must lead to the concrete appropriation of projects by the indigenous peoples. The declaration specifically requires the specialized bodies and entities of the United Nations system (including the UNDP) to promote respect for, and full application of, the rights enshrined therein.

The effective implementation of the indigenous peoples’ right to consultation is relevant for a variety of reasons ranging from a strict respect for the rights established by domestic and international legislation to the construction of a community that respects diversity living in harmony with its environment. Thus, some of the main contributions of the respect of the indigenous peoples’ right to be consulted are the fact that it dignifies indigenous peoples; strengthens our democratic system and contributes to enforcing rights; helps build an inclusive, diversity-friendly citizenry; helps prevent and transform conflicts; and contributes to sustainable development.

SOCIAL ASSESSMENT WITH INDIGENOUS PEOPLES AND PROJECT ENGAGEMENT PLAN

Consultations were carried out in Mendoza with authorities representing the communities and the organization of communities in Mapuche communities of Mendoza living in the Malargüe district. In Jujuy, work was carried out together with the Secretariat of Indigenous Peoples. Since 2016, Jujuy has a Secretariat of Indigenous Peoples, which is responsible for promoting and protecting the rights of the Indigenous Peoples, particularly guaranteeing the right to consultation. The Secretariat of Indigenous Peoples has come to act as a liaison body between public policies and governmental bodies on the one hand, and the indigenous peoples’ own existing processes, on the other; and has opened dialogue between those bodies and the indigenous peoples. Therefore, for PPG-related activities, requests for information, the identification of communities and the identification of appropriate measures for this and future project implementation stages have been carried out in consultation with the provincial project leaders and the Secretariat of Indigenous Peoples.

In all cases, a brief introduction about the framework of the project was provided, as well as the legal framework and the standards governing the project, including the rationale behind the Land Use Planning instrument which constitutes the core of the project. As already explained, the Land Use Planning —and the project itself— contain a participative and collaborative logic. Afterwards, and as information became available, the project was discussed in greater detail, emphasizing the various mechanisms for participation —at the national, provincial and pilot site level— and the specific consultation and participation stages that could be developed jointly with indigenous peoples.

In Mendoza, consultations were held with the “Werken” or spokesman, on behalf of the communities and the organization of the Mapuche communities of Mendoza in the Malargüe target landscape. In Jujuy, the PPG team worked with provincial authorities and the Secretariat of Indigenous Peoples, which is responsible for the promotion and protection of the rights of Indigenous Peoples in the province, and in particular to guarantee the right to Prior Consultation and FPIC. In both cases oral and general agreements with the project were obtained as well as their agreement to jointly develop during project implementation specific consultations before elaborating specific ELUP related interventions in the target landscapes.

Owing to the specific features of the project which require sustained negotiation, coordination and consultation processes as key elements of ELUP, during the initial year of the project, prior to designing specific plans to make the Environmental Land Use Planning operational, the appropriate consultation processes for each indigenous community involved in the specific activities will be designed for each pilot site. This is without prejudice to the information discussed below, which will form the basis for the coordination.

ENGAGEMENT, CONSULTATION AND FPIC PROCESSES IN THE TERRITORY

Social and Political Organization of Indigenous Peoples in Mendoza. In the Mapuche communities in Malargüe decisions are taken by an Assembly of Communities and the Council of Authorities of each Community. The ancestral political Authorities are the “Logko” (head - political authority), “Inan Logko” (Vice-president), “Werken” (messenger - spokesman) and “Kona” (warrior). The communities are grouped into political organizations or councils. In the case of Malargüe, they refer to Malalweche, i.e., the Territorial Organization of the Mapuche People. These communities and their political organization are ruled by a prior consultation protocol developed by Encuentro Nacional de Organizaciones Territoriales de Pueblos Originarios (ENOTPO, in Spanish). The organized Malargüe communities hold several prior consultation processes with the government and other actors. In particular, they have had experience participating in a land-use planning process with the Malargüe Municipality concerning a specific sector of “Cañada Colorada.” Besides, as mentioned above, Mendoza has been working on a land-use planning process for over 20 years, including an engagement element which has been tested, analyzed and improved. This included the implementation of prior consultation processes, which can be considered as experience to improve engagement practices in this project. For these reasons and due to the capacity of the Land-use Planning Agency to liaise with indigenous peoples and actors of the Municipality and other producers, locals are extremely willing to engage.

Social and Political Organization of Indigenous Peoples Communities in Jujuy. The Kolla, Omaguaca, and Atacama peoples have very similar political institutions in each community, such as the Community Council, the Council of the Elderly, and the Assembly. The differences lie in some specific attributes. Moreover, the families form social networks based on family bonds, godfatherhood, and neighborliness which reinforce their relationship system. The minga, which originated from a community tradition deeply rooted in the Andean world, is a form of cooperative and voluntary work which gathers several families or neighbors and is based, precisely, on a network system. If the work is performed for a single family, this family is to compensate it with similar work for those who cooperated with them.

According to the information obtained from the Indigenous Peoples Secretariat and other governmental actors working in the territory, even though the communities in the target landscapes of Jujuy do not have their own consultation protocol as do other communities in the province , they do maintain a close liaison with said Secretariat, which provides technical support for designing and developing consultation processes with the communities and FPIC when necessary, working as an intermediary in the dialogue between governmental entities, private actors and communities. The Secretariat has a specific area which provides guidance and support to communities in carrying out consultation processes.

In these communities, there are internal deliberative practices, sustained stages for liaison with governmental entities and processes for consolidation of the peoples’ capacities. which provide the proper conditions for timely implementation of an initial phase of the project, the processes named Consultation about the Consultation, i.e., adequate processes in each site to identify not only the procedure but also the topics and the number of consultations to be carried out based on the activities to be considered. For example, in Jujuy, a prior consultation process with communities of Quebrada de Humahuaca was conducted for holding a concert in the World Heritage site. In the case of Susques, jujuy, all ten communities involved follow a consolidated tradition of internal deliberation by means of a community assembly and a general assembly of ten communities. They also conduct a deliberation practice with authorities and actors of the private sector within the framework of community assemblies where Secretaries or Ministers are invited to participate, as well as high ranking officers of the company “Sales de Jujuy”, to carry out a dialogue on topics of interest for the communities. These extended assemblies are held once a month and attended by authorities and members of the ten communities. Minutes of such assemblies are drafted reflecting the items discussed and the agreements reached. Based on the experience gained by the consultant in its interaction with these communities, and the reference given by the Indigenous Peoples Secretariat, this dialogue and deliberation system will be an adequate space for developing the first stages of Consultation on the Consultation, when required to identify the proper mechanisms for addressing several issues or projects involving this pilot site.

In any case, in both sites a strong institutional presence is noteworthy in conjunction with a close liaison with local stakeholders, members of the indigenous communities, and other private actors (such as tourism service providers, mining companies, hygiene service providers, among others).

Additionally, all indigenous communities of the country have two indigenous representatives per People at the provincial level, who are appointed in a process entailing community assemblies convened by INAI, with whom they comprise the Indigenous Participation Council, which is a space for collaborative work and cooperation between the National Government and the indigenous peoples of Argentina. This space has the purpose of promoting participation of indigenous communities in the Land Surveying Programme –Law No. 26,160-; guiding communities in formulating development projects with cultural identity; strengthening communities in the organization and registration of their legal identity and participating in several consultation processes concerning public policies that might affect the interests of indigenous peoples.

SUPPORT CAPACITY

As part of the Capacity Strengthening Program to be implemented within the project, several participatory workshops will be carried out to work on enhancing information and strengthening capacities for several actors involved in the project. Some of the topics and practices to be discussed are as follows: Environmental Land Use Planning for government and civil society actors, as well as for indigenous peoples. A discussion will also be held to improve engagement practices and collaborative resolution of any disputes which may arise from discussions and dialogue on the use and regulation of practices involving territories. Moreover, and especially, another topic for discussion will be capacity strengthening for government and civil society actors on human rights and engagement practices, consultation and consent associated with the challenges and opportunities posed by this project.

GRIEVANCE MECHANISM FOR COMPLAINTS

The project will implement a comprehensive system named System for Prevention and Management of Consultations and Conflicts (SPCC, in Spanish). This system will comprise a specific structure for all cases in addition to a specific mechanism entailing adequate practices to address discrepancies, consultations or conflicts involving the Indigenous Peoples in connection with project activities. For these cases the mechanisms used by the communities to address disputes will be considered: for example, the Mapuche communities use a specific assembly method named Kumen Feley for their daily assembly practice and Nor Feley to solve disputes or conflicts and may be convened at the community level or at the community organization level.  In any case, besides primarily opting for managing and inquiring into the disputes concerning indigenous people’s practices, mechanisms will be implemented according to national and international laws related to indigenous peoples.

PLAN FOR INDIGENOUS PEOPLE’S ENGAGEMENT IN PROJECT IMPLEMENTATION

During the initial phase of project implementation, there will be consultations to discuss the later consultation processes to be carried out, i.e., adequate consultation processes will be implemented in each pilot site where indigenous peoples are identified to establish proper mechanisms for prior consultation and FPIC as applicable.

In the initial consultations on the consultation processes, meetings with indigenous communities will be held so as to design further consultation processes and at this initial stage the aim will be to identify:  the communities involved by the specific consultation topic, the topics or types of topics involving consultation processes in each project or specific area, decision-making mechanisms to be implemented, and the type of result (Prior Consultation or FPIC), internal or external advisors or technicians, as required, agreed relevant time periods, type of information (format, modality, access) to be considered for the relevant process; and any other matters to be identified and clarified as deemed necessary by the communities at the so-called Consultation on the Consultation stage.

In these consultation processes, the following general principles will be followed for engaging indigenous peoples in the project:

The project will seek, as the case may be, to follow the mechanisms established, within the framework of dialogue and in agreement with the communities involved. These rights are as follows: the right to engagement throughout the public policy making cycle, to prior consultation in regard to concrete legislative or administrative measures, and to free, prior and informed consent in specific cases which might affect fundamental rights or jeopardize their integrity.

- Engagement. Indigenous peoples’ representatives will take part in the phases of the project preparation, implementation and evaluation cycle, as well as in national, regional and local plans, policies and development programs resulting from said cycle and which may affect it, in order to ensure that their development priorities are taken into account, that the improvement of their life conditions is prioritized and that their integrity is not affected.  Decisions are made collectively among the indigenous peoples and the State, on the basis of processes for dialogue and understanding.

- Prior Consultation.  Under the aforesaid Convention No. 169, the State will implement good faith dialogue processes with indigenous communities before adopting concrete administrative or legislative measures which might affect them, with the objective of achieving agreement or consent through dialogue. Even though the decision is on the State, it must justify such decision.

- Free, Prior and Informed Consent. However, when their fundamental rights are affected, or the integrity of the peoples is at stake, in addition to the consultation, the state may only adopt the measure with the consent of those affected by it. In these cases, consent is not only the aim but also a requirement for the state to act.

Environmental Land Use Planning is essentially a participatory tool, and this principle will prevail in the process of identifying projects and any processes existing as of the date of implementation of the project, as well as existing dialogue processes and platforms and any sustainable production activities to be developed or prioritized.  The action lines outlined in the Project Document will be defined in detail during project implementation. Within this framework, the governmental authorities of the provinces involved will work through prior consultation at all times and free, prior and informed consent mechanisms, in such cases where activities to be implemented might imply: extraction of natural resources such as felling, mining or agricultural activities in their lands or territories; a decision affecting the State or people’s rights to their land/territories, resources or means of support; access to traditional knowledge and practices; commercial use of natural and / or cultural resources in plots of land subject to traditional ownership rights and / or low customary use by indigenous peoples; decisions regarding benefit allocation arrangements, where the benefits are derived from their land, territories or resources (for example, management of natural resources or extractive industries).

Within this framework, the Consultation, as well as any other participatory stage involving indigenous peoples must meet the basic requirements, i.e. It must be free, without coercion, intimidation or manipulation; prior, previous to adopting the measure subject to consultation; informed, as the State must provide the following information in order to make a decision: nature of the measure, reasons, duration, preliminary evaluation, risks and benefits, among others. The peoples have the right to inform the State about their priorities of life, cultural aspects, among others; in good faith, which implies the parties’ acceptance of the consultation procedure, the creation of a relationship based on trust and mutual respect, with the true objective of holding dialogue, which will allow them to make decisions and reach an agreement; through indigenous representative institutions, resulting from the indigenous peoples´ own and internal processes, whether traditional or modern, providing that they have been pre-established, that they are adequate and accessible, that is to say, according to customs and traditional methods for decision making, respecting symbols and images to represent them; moreover, the timing, language and manners inherent to each people must be respected, and the process must be systematic and transparent: it must be made in a formal and systematic manner -which might be repeated for another issue- and transparent, so that all the people involved are aware of the situation.

LIST OF PEOPLE CONSULTED DURING THE PPG PHASE

| Name | Institution | Position |
| --- | --- | --- |
| Moreno, Diego | SGAyDS | Secretary of Environmental Policy in Natural Resources (SPARN) |
| Duverges, Dolores | SGAyDS | National Director of Environmental Land Use Planning (DNPyOAT) of the SPARN |
| Corso, María Laura | SGAyDS | Expert on Soil and the Fight against Desertification, DNPyOAT |
| Pietragalla, Vanina | SGAyDS | ELUP Expert, DNPyOAT |
| Chiavassa, Silvia | SGAyDS | DNPyOAT |
| Pien, Graciela | SGAyDS | Protected Areas Expert, DNPyOAT |
| Fabricant, Jorge | SGAyDS | DNPyOAT |
| Heider, Jorge | SGAyDS | DNPyOAT |
| Tonelli, María | SGAyDS | DNPyOAT |
| García García, Fernando | SGAyDS | DNPyOAT |
| Martínez, Paula | SGAyDS | DNPyOAT |
| Etorena, Joaquín | SGAyDS | Coordinator of the World Bank Project, "Increasing Climate Resilience and Enhancing Sustainable Land Management in the Southwest of the Buenos Aires Province" |
| Gaspes, Ezequiel |  | World Bank Project, "Increasing Climate Resilience and Enhancing Sustainable Land Management in the Southwest of the Buenos Aires Province" |
| Sívori, Pablo |  | World Bank Project, "Increasing Climate Resilience and Enhancing Sustainable Land Management in the Southwest of the Buenos Aires Province" |
| Iza, Hugo | SGAyDS | Project Coordinator MST NOA CUYO "Sustainable Land Management in the Dry Regions of the Argentine Northwest" UNDP ARG/14/G55 |
| Buitrago, Nicolás |  | Project MST NOA CUYO "Sustainable Land Management in the Dry Areas of the Argentine Northwest" UNDP ARG/14/G55 |
| Apellaniz, Melisa | SGAyDS | National Biodiversity Directorate |
| Banchs, Ricardo | SGAyDS | National Biodiversity Directorate |
| Marino, Gustavo | SGAyDS | Coordinator of the Sustainable Use of Biodiversity Project (USUBI) - UNDP ARG 15/G53 |
| Bonafina, Micaela | SGAyDS | Project Coordinator "Promoting the application of the Nagoya Protocol on ABS in Argentina" - UNDP ARG 16 G54 |
| Cano, Juan Pedro | SGAyDS | National Forest Director (DNB) |
| Fermani, Sebastian | SGAyDS | National Programme Coordinator for the Protection of Native Forests |
| Bono, Julieta | SGAyDS | DNB |
| Manghi, Eduardo | SGAyDS | DNB |
| García Espil, Javier | SGAyDS | National Director of Environmental Management of Water and Aquatic Ecosystems (DNGAAyEA) |
| García Silva, Leandro | SGAyDS | Water Programme Coordinator DNGAAyEA |
| D'Alessio, Santiago | SGAyDS | Coordinator of Biodiversity Programme associated with water DNGAAyEA |
| De Nichilo, Antonio | SGAyDS | Coordinator of the Sea and Coasts Programme DNGAAyEA |
| Pacific, Nicolás | SGAyDS | Chief of Staff DNGAAyEA |
| Neme, Javier | SGAyDS | Environmental Information Coordinator |
| Miño, Mariela | SGAyDS | Expert in GIS Coordination of Environmental Information |
| Candia, Indiana | SGAyDS | SPARN Communication |
| Ferrando, Juan | UN-Environment | Regional Adviser ONUREDD |
| De Lamo, Xavier | UN-Environment | Programme Officer |
| Walcott, Yudith | UN-Environment | Programme Officer |
| Lazzari, Lucía | UN-REDD National Programme | Technician |
| Alcobé, Fernanda | UN-REDD National Programme | Coordinator |
| Lapalma, Laura | UN-REDD National Programme | Operative Unit |
| Yasky, Marcelo | Provincial Agency for Sustainable Development (OPDS) of the Province of Buenos Aires | Provincial Director of Natural Resources |
| Canciani, Marcos | Provincial Agency for Sustainable Development (OPDS) of the Province of Buenos Aires | Technician for Provincial Office of Natural Resources and Environmental Land Use Planning |
| Achinelli, Moira | Provincial Agency for Sustainable Development (OPDS) of the Province of Buenos Aires | Technician for Directorate of Sustainable Development and Climate Change |
| Mariano, Guillermo | Provincial Agency for Sustainable Development (OPDS) of the Province of Buenos Aires | Technician for Provincial Office of Natural Resources and Environmental Land Use Planning |
| Mingorance, Humberto | Ministry of Environment and Land Use Planning of the Province of Mendoza (SAOT) | Environment and Land Use Planning Secretary |
| Rapali, Nadia | SAOT | Land Use Planning Agency under the Ministry of Environment and Land Use Planning |
| Fenoy, Laura | SAOT | Technician for Ministry of Environment and Land Use Planning |
| Sorli, Laura | SAOT | Technician for Ministry of Environment and Land Use Planning |
| Castaño, Ana Rosa | ICES CNEA | Regional ICES |
| Pachecho, Facundo | Municipality of Malargüe Tourism Office | Technician for Municipality of Malargüe Tourism Office |
| López, José Luis | Malargüe Strategic Plan | Director of the Malargüe Strategic Plan |
| Elissonde, Arturo | Cañada Colorada Land Use Planning Management and the Llancanelo Upper Basin | Land Use Planning Management of Cañada Colorada and the Upper Basin of Llancanelo |
| Jofré, Gabriel | Malalweche Mapuche Land Use Planning Organization | Malalweche Werken Organization |
| Bouille, Vanesa | Malalweche Mapuche Land Use Planning Organization | Malalweche Mapuche Land Use Planning Organization |
| Zigarán, María Inés | Ministry of Environment of the Province of Jujuy | Minister of the Ministry of Environment of the Province of Jujuy |
| Amador, Susana | Ministry of Environment of the Province of Jujuy | Director of Land Use Planning |
| Mogni, Paula | Ministry of Environment of the Province of Jujuy | Deputy Director of Land Use Planning |
| Cabezas, Ivana | Ministry of Environment of the Province of Jujuy | Technician for Land Use Planning Office |
| Valera Prieto, Llanos | Ministry of Environment of the Province of Jujuy | GIS Technician for Land Use Planning Office |
| Zamorano, Mercedes | Ministry of Environment of the Province of Jujuy | Director of Protected Areas |
| Gronda, Javier | Ministry of Environment of the Province of Jujuy | Secretary of Biodiversity |
| Zenón, Daniel | Ministry of Environment of the Province of Jujuy | Director of Changes in Land Use |
| Olmos, Sandra | Ministry of Environment of the Province of Jujuy | Tourism Management Office under the Tourism Management Secretariat. |
| Deiana, María Emilia | Ministry of Production - Province of Jujuy | Secretariat of Production Development |
| Bisgarra, Sergio | Secretariat of Family Agriculture - Jujuy | Secretariat of Family Agriculture |
| Pérez, Carolina | Secretariat of Indigenous Peoples - Jujuy Province | Head of Department of Legal Affairs and Legal Defence |
| Augusto de Haro | INTA | National Coordination of Transfer and Extension/Expansion |
| Silva Colomer, Jorge | INTA | EEA Mendoza |
| Van den Bosch, María Eugenia | INTA | EEA Mendoza |
| Gudiño, José | INTA | Director of the Mendoza-San Juan Regional Centre - INTA |
| Vitale, Javier | INTA | EEA Mendoza |
| Pérez, Martín | INTA | EEA Mendoza |
| Portela, José | INTA | EEA La Consulta |
| Macario, Javier | INTA | Head of Rural Extension/Expansion Agency Malargue |
| Daniele, Martín | INTA | EEA Director Rama Caída |
| Picca, Cecilia | INTA | EEA Rama Caída |
| Goites, Enrique | INTA | Research Institute Research and Technological Development for Family Agriculture - Pampas Region |
| Zelarayan, Ana | INTA | EEA Salta |
| Pedersen, Leif | UNDP Green Commodities Programme | Senior Commodities Adviser |
| Jaramillo, Manuel | Argentine Wildlife Foundation | Managing Director |
| Miñarro, Fernando | Argentine Wildlife Foundation | Pampas and Gran Chaco Programmes Coordinator |
| Democratic Change Foundation |  |  |
| Wetlands Foundation |  |  |
| Gorleri, Constance | ADEBA Sustainable Finance Committee / Banco Galicia | ADEBA Secretary Coordinator / Banco Galicia Sustainability Manager |
| Busch, Hernan | Banco Galicia | Agribusiness Commercial Manager |
| Furmanski, Martín | Banco Galicia | Leader of Loans and Wholesale Banking Investment Projects |
| Vaccaro, Victoria | Provincial Gender and Sexual Diversity Institute of the Province of Buenos Aires | Advisor to the President and Gender Specialist |
| Barrios, Natalia | National Women´s Institute | Chief of Cabinet |
| Piñol, Verónica | Provincial Directorate for Gender and Diversity of the Province of Mendoza | Advisor, Observatory Area |

## Annex G: Gender and Ethnic Analysis and Action Plan

A. Summary of the Main Findings of the Gender and ethnic analysis carried out during the PPG

1. In Argentina the causes of gender inequality and discrimination are mainly explained by the prevalence of traditional patriarchal structures and norms and gender roles, particularly in remote, rural and agricultural areas.

2. Young, poor, rural and indigenous women represent around 40% of the agricultural labor force. Although there are no legal instruments that prevent women from owning property, such as land, in Argentina 80% of men have such ownership (FAO, 2010). Men are the ones who mostly make decisions related to access, use and management of ecosystem resources; therefore, most women cannot enjoy the benefits of profitable land, access credit and/or productive resources derived from land. While women are not as active as men in the agricultural labor force, women take on major roles in sustainable forest management. As caregivers they are highly dependent on forests and are the primary users of forest products. However, they are often excluded from forestry-related decision-making. This bears the risk/concern that women’s valuable knowledge remains underutilized.

3. In Argentina, there are more women (52%) than men (48%). The number of women 46 years and older is higher, while the ratio is reversed in younger ages (from 0 to 35 years), with the exception of the age bracket 14 to 15 years. This distribution of the population by sex and age groups is conserved without statistically significant differences in the three prioritized areas (52.0% women and 48.0% men in Buenos Aires; 51.5% women and 48.5% men in Jujuy and 52.2% women and 47.8% men in Mendoza (INDEC, 2017).

4. 91% of the Argentine population lives in urban areas and the remaining 9% in rural areas. Of the three prioritized provinces, Mendoza has the largest number of inhabitants in rural areas (19.1%), followed by Jujuy (12.5%) and then Buenos Aires (3%). The distribution of rural population disaggregated by sex in the province of Jujuy is 51.7% men and 48.3% women (DIPEC, 2012). So far, information disaggregated by sex in rural areas is not available in Mendoza or Buenos Aires.

5. The proportion of indigenous peoples with respect to the total population of each jurisdiction is variable: 2.38% at the national level, 1.92% in Buenos Aires; 2.4% in Mendoza and 7.8% in Jujuy with respect to provincial totals. Jujuy has the largest indigenous population in relative terms (8%). The distribution of the indigenous population according to sex presents a fairly homogeneous behavior within each jurisdiction and in the country as a whole (50% men and 50% women). The proportion of the Afro-descendant population is less than 1% in the three prioritized areas.

6. Regarding the heads of household, of every 10 people who claim to be head of the household at the national level, 4 are women and 6 are men (41.2% and 58.8%, respectively). This proportion is consistent in each priority area. In relation to the age of women who are heads of household both at the country level and in the priority areas, 6 out of 10 women heads of household are 50 years old and over, and they are more affected by the double burden of domestic and paid work that falls on them alone. Note: A head of household is “the person, either a man or a woman, or both, recognized as such by the other members of the household”. (Source: INDEC, Situation and Social Evolution-Synthesis N ° 4. 2016).

7. Regarding socio-economic indicators, at the country level, approximately 40% of women up to 29 years old participate in the labor market against almost 60% of men in the same age group. Only in Jujuy is there a marked decrease in the proportion of men who participate in the economy (38.8%) compared to the national percentage, although the rate of men in the labor market still exceeds that of women in the labor market in that province (29.2%). In Mendoza, the male activity rate is also lower than the national rate for that same age group (52.0%) and also exceeds that of women (39.1%). The employment rate is higher for men than for women (65.7% and 43.5%, respectively), a trend that, although there are nuances, is reproduced inside the prioritized areas. Men earn 26% more than women (WEF, 2017).

8. The unemployment rates follow an inverse pattern, registering a higher percentage of unemployed women at the country level than men in the same situation (8.7% and 6.1%, respectively). In Jujuy and Mendoza the percentage variations are smaller. Within the age group up to 29 years, there is a marked gap between the unemployment of men and women. The difference at the national level is 7.4 percentage points, to the detriment of women, a trend that is exacerbated in Mendoza and Buenos Aires, with 7.55 and 11.1 percentage points, respectively. The trend softens in the case of Jujuy, where the difference is only 1.8 percentage points.

9. According to the World Economic Forum's Global Gender Gap Index (WEF, 2017), Argentina stands out in terms of access to education for men and women, obtaining a score of 0.998 out of 1, which indicates parity between men and women. This proportion holds true in each priority area.

10. Regarding the level of poverty and indigence, in the second half of 2017 the percentage of households below the poverty line was 17.9%; these comprise 25.7% of people. In the three prioritized areas, the differences are not statistically significant, except for Buenos Aires where the percentage of households and people below the poverty line exceeds the national average (21.3% of households and 29.5% of people respectively) and the same situation is observed in terms of the indigence analysis, where the values ​​exceed the percentage at the country level (4.6% of households that comprise 6.2% of the population in this prioritized area).

11. The amount of average weekly hours that women devote to unpaid work is much higher than that of men, and as the age of children increases, women’s participation in the labor market increases, too. This is unlike what happens with men, whose participation remains stable. In the country as a whole, women spend, on average, 76.4% of their time on unpaid domestic work, while men spend, on average, only 23.6% of their time on the same activity (EAHU, 2013). That is, women spend 3.3 times more of their time on unpaid domestic work than men. This proportion is evident in each priority area.

B.  Gender Mainstreaming Strategies

B.1 Main Strategies Mainstreaming the Gender Approach within the Project´s Intervention Strategy

- Gender balance will be taken into account in engaging the project team, the Project Board and multi-sectoral, multi-stakeholder dialogue spaces. The recruitment processes that will be undertaken as part of the project will aim at ensuring workforce diversity, including in terms of gender. This will be achieved through a variety of measures, including ensuring that ToRs target men and women as potential candidates (“He/She”) equally, provisions that women are encouraged to apply, and requesting basic understanding, skills, experience and commitment to work in a gender-sensitive and multicultural-sensitive manner. Where applicable, strong candidates will be assessed as part of written tests and/or behavioral interviews held as part of recruitment processes (e.g., through adding one or more gender-related and multicultural-based questions).  In the multi-stakeholder dialogue spaces, the project will work through political dialogue at the federal level to ensure the participation of women in these spaces and other project processes.

- Including gender and ethnicity disaggregated data collected from official sources in the development of policy, economic, financial and technical instruments and governance mechanisms for ELUP. All data reviewed and prepared for entry to the system of policy, economic, financial and technical instruments and governance mechanisms for ELUP will be looked at through a gender and inter-cultural lens, and will reference gender and ethnicity if and where needed (i.e., who owns, controls, uses land areas in question, how will planned measures affect women and men both indigenous and non-indigenous, etc.). If no official sources are available, a specific survey will be conducted including specific questions that reveal relevant gender and multicultural dimensions (e.g., gender dimensions in the use of BD and ecosystem resources management; economic impact of land degradation on women/men, both indigenous and non-indigenous).

- Development of a capacity building program aimed at public officials and/or technical teams to raise awareness on the importance of engaging both women and men in decision-making processes and addressing gender issues. Gender and intercultural approaches will be integrated into capacity-building initiatives through distinct gender sessions, workshop or training sessions aimed at public officials and/or technical teams (e.g., pointing out the gender division of labor or use of time in the prioritized areas by presenting data disaggregated by sex). It is also key to ensure that both women and men have access to capacity-building initiatives, and that obstacles, which usually prevent women from benefitting from these activities, are addressed (e.g., in places and at times where women have the chance to participate). It is also important to identify suitable female participants and invite these women and explain the benefits of enhancing women and men’s capacities equally, including for target communities as a whole, to authorities/decision-makers.

- Gender mainstreaming in the promotion of dialogue mechanisms, making the most of existing spaces and structures for consultation, deliberation, decision-making and inter-institutional coordination at the national, provincial and pilot levels, by fostering equal participation of women and men and indigenous populations in agenda-setting, decision-making and/or policy-making processes. This will include undertaking consultations with women and men from target sites as well as with institutions (e.g., the National Institute of Women-INAM- and National Indigenous Peoples Institute- INAI- at the national level and the gender and ethnicity agencies in each of the provincial levels). When designing the contents, methodologies and approaches, the project will ensure that women and men’s knowledge and interests are considered and that women are included in decision-making processes (e.g., through highlighting the benefits of their involvement and ensuring consultations and dialogue spaces are held at a time and place where both women and men can participate).

- Development of a capacity building program aimed at women beneficiaries (indigenous and non-indigenous) in the three prioritized areas and target landscapes. The project will coordinate with the INAM, the Federal Council of Women and the INAI and with the three provincial gender mechanisms and indigenous affairs bureaus (Buenos Aires: the Provincial Council of Women under the Secretariat of Gender and Sexual Diversity of the Secretariat for Human Rights of the Province of Buenos Aires and the Provincial Council for Indigenous Affairs; Mendoza: the Directorate of Women, Gender and Diversity under the Ministry of Social Development and Human Rights and in Jujuy, the Gender Parity Secretariat under the Ministry of Human Development and the Secretariat of Indigenous Peoples. The project will enhance collaboration with civil society organizations with support of each of the above entities in the three prioritized areas to ensure women and men are equally included in capacity building programs. The project will ensure consultation of women and men working in agriculture and identify female-headed households to facilitate their engagement in project activities (i.e., ensure that participation is possible given their particularly tight schedules). Additionally, the project will collaborate with stakeholders working on gender equality, women’s empowerment and other relevant actors in the tourism sector (e.g., Ministry of Tourism, women working in the tourism sector and those interested in getting engaged) to find out about suitable business opportunities.

- Enhance knowledge management and dissemination by systematizing, assessing, replicating and/or scaling up lessons learned, case studies, and promising and/or best practices on gender mainstreaming in BD/SLM and ELUP and on women’s participation in dialogue platforms and/or mechanisms in the three prioritized areas. The documentation and dissemination of results will consider gender and the multicultural approach, too. To achieve this, knowledge products prepared under the project will reflect on gender and ethnicity to the extent possible, for instance through the presentation of data disaggregated by sex and ethnicity and the inclusion of sections that analyze the respective gender and ethnic dimensions. Gender and ethnicity will also be considered in the dissemination of research results, knowledge and information. For instance, when circulating knowledge products, the project will ensure the inclusion of various stakeholders that work on gender equality, women’s empowerment and ethnicity, both from civil society and public entities and both at the national level and in the three prioritized areas and pilot sites.

B.2.  Specific Strategies to Mainstream the Gender Approach within the Project´s Outcome Framework

| Project Outcomes/ Outputs | Responsible Party | Specific activities with a gender approach |
| --- | --- | --- |
| Outcome 1: Federal enabling framework and strategies to reinforce ELUP, and underpin implementation in priority ecosystems and habitats to reduce pressure from key production sectors. (target sectors: agriculture & livestock; mining and peri-urban infrastructure, tourism) |  |  |
| Output 1.1: Environmental information system updated and standardized to support the ELUP process & decision- making | SGAyDS | 1. Include data disaggregated by sex and ethnicity in the development of the environmental information system so that decision-making within ELUP at a national, provincial and local level incorporates the gender and ethnicity perspective in order to bridge inequality gaps. 2. In developing criteria for defining Priority Areas for ELUP include specific criteria with a gender and ethnicity approach (multiculturalism). 3. Carry out a quali-quantitative analysis of the degree to which the main land issues identified affect men and women differently, both from indigenous and non-indigenous peoples. 4. Assess, in developing and validating the maps of priority areas of environmental value for ELUP, whether access, use and control over the ecosystemic resources and services is equitable between men and women and to what extent they affect indigenous peoples 5. Assess, in developing and validating the maps of priority areas of environmental value for ELUP, whether costs and benefits of accessing, using and controlling ecosystemic resources in each priority areas of environmental value are shared equitably between men and women (both indigenous and non-indigenous). 6. Guarantee actual participation of male and female expert users and indigenous peoples in the validation of the maps. 7. Incorporate the gender and ethnicity approach in the development of indicators for monitoring ELUP. 8. Include the participation of the National Institute of Women (INAM, in Spanish) and the National Indigenous Peoples Institute (INAI, in Spanish) in the dissemination of information generated through the environmental information system. |
| Output 1.2: Federal level ELUP criteria agreed upon | SGAyDS | 1. Facilitate the participation of INAM and INAI in participatory workshops to: - Define the criteria for assessing ecosystem services, biodiversity conservation and sustainable land management practices with a view to incorporating the gender and multicultural approaches into the agreed criteria. - Incorporation of gender and multicultural approaches in preparing, validating and drafting a document discussing strategies for promoting conservation and restoration areas with compensation schemes for implementing ELUP. |
| Output 1.3: Standardized instruments for implementing ELUP for targeted sectors | SGAyDS | 1. Facilitate the participation of INAM and INAI in: - Mainstreaming the gender and ethnicity approaches in the incorporation of ELUP criteria in economic instruments that favor men and women equitably and enhance women’s economic independence. - Discussions and development of the proposal for a federal minimum standards regulation on ELUP |
| Output 1.4 Inter-sectoral and inter jurisdictional co-ordination mechanisms |  | 1. Incorporate INAM and INAI as members of the inter-institutional and inter-sectoral dialogue and coordination spaces. 2. Ensure space for open dialogue placing special focus on the gender-sensitive forms of interaction of the stakeholders which actively acknowledges the concerns of all legitimate stakeholders, men and women, and considering their interests in decision-making and operations. 3. Develop training and awareness raising programs on gender and mainstreaming of the gender approach with the participation of INAM targeting the technical teams of the national institutions. 4. Develop training and awareness raising programs on multi-cultural issues given by the National Indigenous Peoples Institute (INAI) and targeted at the participating national institutions. |
| Outcome 2: Application of ELUP procedures and instruments in pilot Provinces with targeted ecoregions and production sector land uses. |  |  |
| Output 2.1. Provincial Regulatory Framework for ELUP strengthened | OPDS SAOT Ministry of Environment of Jujuy | 1. Coordinate the participation of provincial government agencies and civil society organizations with a gender and indigenous peoples mandate to incorporate the gender and ethnicity perspectives in formulating the provincial regulatory proposals regarding ELUP by strengthening and harmonizing existing legislation and in ELUP criteria to be applied to existing regulatory instruments: Buenos Aires: - The Undersecretariat of Human Rights and the Provincial Institute for Gender and Sexual Diversity, both under the Secretariat for Human Rights of the Province of Buenos Aires. - The Council of Women of the Province of Buenos Aires. - The Provincial Council for Indigenous Affairs (CPAI, in Spanish). - Social Undersecretariat for Land, Urban Planning and Housing Mendoza: - Directorate of Gender and Diversity which falls under the Undersecretariat of Social Development of the Ministry of Health, Social Development and Sports of the Province of Mendoza - Municipal Women Areas of the Municipalities of Malargüe, Luján de Cuyo, Godoy Cruz, Las Heras, Mendoza Capital City, Tunuyán, San Carlos and Tupungato and Maipú, whose pilot sites are directly affected by the project - Indigenous Participation Council (Mendoza representation) under the INAI Jujuy: - Gender Parity Secretariat under the Ministry of Human Development of the Province of Jujuy. - Secretariat of Indigenous Peoples and the Indigenous Participation Council (Jujuy representatives) under the INAI 2. Explicitly incorporate the ethnicity and gender perspective in drafting the proposals for provincial regulations and standards on ELUP ensuring parity between indigenous and non-indigenous men and women in the lawmaking process and in the development and content of specific regulations to put into practice the mandates set forth within the general regulatory framework at the provincial level and the drafting of protocols, methodological guides, strategic plans, economic, tax, and/or financial instruments, among others |
| Output 2.2 Provincial Governance Framework for participatory ELUP & sector consensus building | OPDS SAOT Ministry of Environment of Jujuy | 1. Ensure the engagement of the above-mentioned institutions with gender mandates in the development and implementation of the provincial multi-stakeholder dialogue and coordination spaces in each province and the sustainable beef platform in Buenos Aires. 2. Update the stakeholder mapping with gender-sensitive forms of interaction (civil society organizations, cooperatives, women’s collaborative spaces, etc.) at the local and provincial level who may be willing to participate 3. Promote women’s engagement and capacity development to increase participation in dialogue spaces. 4. Ensure space for open dialogue placing special focus on the gender-sensitive forms of interaction of the stakeholders which actively acknowledge the concerns of all legitimate stakeholders, men and women, and considering their interests in decision-making and operations. 5. Develop training and/or awareness raising programs on gender and mainstreaming of the gender approach with the participation of the provincial institutions with gender mandates; targeting the technical teams of the provincial institutions responsible for drafting specific regulations to put into practice the mandates set forth within the general regulatory frameworks at the provincial level and the drafting of protocols, methodological guides, strategic plans, economic, tax, and/or financial instruments, among others. 6. Develop training and/or awareness raising programs on multi-cultural issues given by the National Indigenous Peoples Institute (INAI) and targeted at the participating institutions responsible for drafting specific regulations to put into practice the mandates set forth within the general regulatory framework at the provincial level and the drafting of protocols, methodological guides, strategic plans, economic, tax, and/or financial instruments, among others. |
| Output 2.3. Set of instruments validated in pilot landscapes for defining and implementing ELUP | OPDS SAOT Ministry of Environment of Jujuy | 1. Mainstream the gender and ethnicity approach into the analysis and design of ES valuation mechanisms so as to value the different uses and management of environmental services by men and women. 2. Mainstream the gender approach into the design of compensation schemes in order to boost women’s economic autonomy by creating positive economic incentives that broaden their employment opportunities and production activities (by individuals or organizations). 3. Mainstream the gender and ethnicity approach into the establishment of comprehensive socioeconomic and environmental strategies intended for the conservation of biodiversity, soils and landscapes in order to design specific strategies to promote the economic empowerment of women (indigenous and non-indigenous). |
| Output 2.4 SLM and biodiversity-friendly production practices validated for different ELUP land use zones | OPDS SAOT Ministry of Environment of Jujuy | 1. Establish dialogue and consultation mechanisms amongst the provincial environmental authorities and gender and indigenous peoples authorities to: - Gather information on the relevant stakeholders in each target landscape, paying special attention to indigenous communities and women’s organizations of the region. - Gather information disaggregated by sex and ethnicity - Identify the main economic activities mainstreaming the gender and ethnicity approach (i.e., percentage of men and women, indigenous and non-indigenous, taking part in economic activities, by type of activity). - Identify practices in which women’s participation (indigenous and non-indigenous) represents an added value 2. Mainstream the gender and ethnicity approach into the development and implementation of specific environmentally-friendly and sustainable practices in each target landscape. 3. When developing technical assistance and training consider the work schedules of producers and their families, and communities, for minimum interference with the daily chores of men and women in order to ensure their participation in the activities organized by the project. 4. Develop specific training targeting women beneficiaries (indigenous and non-indigenous) in the target landscapes to: i) promote gender equality in the management, use and conservation of biodiversity; and ii) ensure that both women and men´s needs are addressed through the project interventions |
| Outcome 3: Replicability framework for ELUP uptake in all Argentine provinces |  |  |
| Output 3.1 Nationwide ELUP experiences and related instruments evaluated as an input to determine the best mix of instruments for different productive sectors and ecoregions | SGAyDS | 1. Coordinate with INAM and INAI their participation within the framework of inter-sectorial and inter-jurisdictional coordination in order to agree on guidelines that incorporate gender and multicultural approaches in the process of creating a database of validated instruments to implement ELUP at national, provincial and local levels, for each ecoregion and sector. 2. Incorporating differential gender, ethnicity and inter-sectional approaches into the assessment and evaluation of instruments, plans, programs and projects linked to biodiversity, land degradation, SLM and ELUP implemented in provinces not covered by the project. This activity will be carried out through consultations with the provincial and/or local gender mechanisms in order to identify and assess cases in which an integration of gender issues exists according to the various types of actors and the various groups of men and women that are part of the population and who benefit from ecosystemic resources differently according to their social background, physical abilities, age, age groups, sexual diversity, ethnicity, poverty conditions, etc. 3. Incorporating a differential gender and ethnicity approach in systematizing the information obtained, emphasizing the differential participation of men and women in the cases assessed in connection with biodiversity, land degradation, SLM and ELUP and how these affect (e.g., impact) men, women and indigenous peoples differently. |
| Output 3.2. Nationwide ELUP Capacity Strengthening Programme for all Provincial Authorities | SGAyDS | 1. Coordinate with INAM and INAI their participation in the development of a capacity strengthening program to enable provinces to mainstream the differential gender and multiculturalism approaches into the design and implementation of ELUP in their territories. This will include developing capacities for: identifying and assessing the targeted practices; how these will be implemented; who they are targeted at, whether men, women or both (both indigenous and non-indigenous); what changes in men and women are expected to be promoted through these practices; the number of beneficiaries (minimum percentage of indigenous and non-indigenous women); the number of hectares to be covered; management practices; and number of beneficiaries of the training activities (minimum percentage of indigenous and non-indigenous women). |
| Output 3.3. System to Monitor ELUP implementation nationwide established | SGAyDS | 1. Coordinate with INAM and INAI their participation with a view to mainstreaming the differential gender and multiculturalism approaches into designing and implementing an assessment and monitoring system that coordinates the sectors at various scales, for the purpose of planning, monitoring and integrating ELUP at the national, provincial and local levels. |
| Outcome 4: Dissemination of lessons learned and monitoring and evaluation |  |  |
| Output 4.1: Project M&E system operational and generating periodic report | SGAyDS Project Management Unit | 1. Collect sex-disaggregated and multi-cultural data related to governance and regulatory frameworks, participation, access to economic and financial incentives, and sustainable production, among others. As part of project M&E, the nature, extent and effectiveness of gender mainstreaming actions will be assessed periodically. |
| Output 4.2: Knowledge management system set up to disseminate good practices and lessons learned | SGAyDS Project Management Unit | 1. In assessing project lessons and best practices and developing knowledge products expressly identify the differential contributions of men and women in all knowledge outputs (i.e., project publications and communication outputs). 2. Prepare and disseminate at least one publication on gender mainstreaming. |

B.3 Gender Indicators in the Project´s Results Framework

|  | Objective and Outcome Indicators | Baseline Value | Mid-term Target | End of Project Target |
| --- | --- | --- | --- | --- |
| Project Objective: Generate multiple biodiversity and land degradation benefits by developing a system of policy, economic, financial and technical instruments and governance mechanisms for environmental land use planning (ELUP) to mainstream socioeconomic and environmental evaluation of ecosystem goods and services (ES&G) in decision making at different government levels and sectors | Number of direct project beneficiaries (by gender and ethnicity) that improve their livelihoods through environmentally- friendly natural resource management and sustainable production | 0 | 3,400 (40% are women; 10% belong to indigenous groups) | 11,665 At least 40% are women; 10% belong to indigenous groups |
| Outcome 1 Federal enabling framework and strategies to reinforce ELUP, and underpin implementation in priority ecosystems and habitats to reduce pressure from key production sectors. (target sectors: agriculture & livestock; mining and peri-urban infrastructure, tourism) | Indicator 6: Number and type of new partnership mechanisms at federal level for dialogue to mainstream BD and ELUP in sectoral programming and finance decisions (including level of direct participation of women and indigenous peoples). | There are several federal level spaces that deal with different subjects, e.g., COFEMA, CONADIBIO, ONDTyD but none specifically addressing ELUP | 1 inter-institutional and inter-sectoral dialogue space established (with at least 40% female membership and including indigenous peoples). | 1 inter-institutional and inter-sectoral dialogue space to mainstream BD and ELUP in sectoral programming and finance decisions functioning with work plans and budget (with at least 40% female membership and including indigenous peoples). |
| Outcome 2 Application of ELUP procedures and instruments in pilot Provinces with targeted ecoregions and production sector land uses. | Number and type of new partnership mechanisms at provincial level for participatory ELUP and consensus building (including level of direct participation of women and indigenous peoples) | Mendoza has a Land Use Planning Provincial Council which will serve as a dialogue space. Jujuy and Buenos Aires do not have participatory mechanisms for ELUP. | 1 multi-stakeholder space strengthened with new members (Mendoza) 2 multi-stakeholder spaces (Buenos Aires and Jujuy) and 1 sustainable commodities platform (Buenos Aires) designed and stakeholders identified | 3 provincial multi-stakeholder spaces functioning with work plans and budgets (at least 40% female membership and including indigenous peoples) |
|  | Level of improvement in livelihoods of beneficiaries in target landscapes differentiated by gender and ethnicity, measured through the Land Degradation Assessment in Drylands (LADA) Livelihood Index which measures 5 capitals: social, productive, human, physical and natural | Index baseline values to be determined in PY1 for each target landscape (Index ranges from 1 (low) to 5 (high). |  | 20% improvement in the Livelihood Index |
| Outcome 3 Replicability framework for ELUP uptake in all Argentine provinces | Level of improvement in knowledge, aptitudes and practices (KAP) in ELUP, ES, sustainable production and other key issues at national and provincial levels measured through surveys in Year 1 and Year 6 (including gender disaggregated data) as a result of capacity building programs on ELUP | KAP survey in PY1. Baseline and targets to be established. |  | KAP survey (target in terms of improved knowledge to be determined in PY1) |
| Outcome 4 Dissemination of lessons learned and monitoring and evaluation | Number and type of project knowledge products and publications on best practices and lessons learned (at least 1 on gender) disseminated | 0 |  | 15, with at least 1 on gender (e.g. i) annual reports, newsletters; ii) lessons/case studies on: best BD/SLM practices, ELUP in provinces, gender mainstreaming, dialogue platforms and participation; iii) ELUP methodological guidelines at national and provincial levels) |

## Annex H:  UNDP Risk Log

| Project risks |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Description | Type | Impact & Probability | Mitigation Measures | Owner | Status |
| Lack of political will and commitment of institutional stakeholders for inter-institutional and inter-sectorial coordination for ELUP results in reduced effectiveness of ELUP implementation | Institutional | P= 3 I= 4 Significance: Moderate Potential impacts: Key institutional stakeholders will continue interventions based on a sectoral approach with little or no coordination. Lack of mainstreaming of ELUP will continue to weaken coordinated planning efforts. ELUP is not sufficient to halt environmental problems. | The General Law of the Environment charges the SGAyDS with the role of leading mainstreaming and implementation of ELUP. The project will support SGAyDS in leading this process and fulfilling its mandate. The three pilot provinces will be part of the Project Board thus ensuring political dialogue for implementation of ELUP. Key sector institutions will be invited to participate in the Project´s Technical Committee (see Section VIII on implementation arrangements). This will ensure dialogue at the managerial and technical level as well as coherence in planning and implementation of project interventions. The project will also promote inter-institutional and inter-sectoral coordination through several interventions: i) strengthening dialogue at national and provincial levels; ii) participatory and joint development of standards and regulations will reinforce coordination between sector institutions and jurisdictions; iii) multi-stakeholder coordination mechanisms will serve as a long term space where the different national and provincial sectors can align, take ownership and develop joint concrete actions. The national and provincial dialogue spaces will promote coordination for ELUP, while the sustainable beef platform will engage the productive sectors to agree on sustainable production policies and market access for sustainable production within the framework of ELUP. Different government institutions will be involved in the project, thus reinforcing their commitment and participation; and iv) training will serve to raise awareness and build capacities at different levels for ELUP implementation. | UNDP CO | Identified risk |
| High staff turnover (authorities and technical personnel) of implementing partner and key institutions at national, provincial and municipal levels delays project implementation and reduces uptaking of ELUP | Institutional | P= 4 I= 3 Significance: Moderate Potential impacts: Periodic rotation of the staff of public institutions. New staff may replace trained technical staff without knowledge of project themes (e.g., ELUP, sustainable production) hence delaying capacity development and project activities. Implementation arrangements between SGAyDS and provinces may encounter difficulties due to changes in authorities. | The participating institutions will sign inter-institutional agreements for coordination and implementation of project interventions (e.g., SGAyDS and provinces, and with sectoral institutions). The project will promote adequate coordination at all levels amongst all institutions and stakeholders, with clearly defined roles and responsibilities and decision-making channels. In case of significant changes that may affect project implementation, the Project Board and the Project Coordinator will promote high level and/or technical meetings and prepare information materials to inform and raise awareness on the value of the project for ELUP mainstreaming and compliance with the General Law of the Environment. UNDP as implementing agency will provide a neutral space for project implementation and promoting dialogue in case of changes of authorities to inform and raise awareness on the importance of the project. The project will support building a policy and regulatory framework agreed upon by consensus between SGAyDS and provincial governments that will aid in continuity of actions in case of changes. The multi-stakeholder dialogue spaces will serve to reinforce dialogue and dissemination of project-related information to new authorities and staff members. These spaces will also serve to ensure the relevance of ELUP decisions and their consistency with local priorities, thereby facilitating continuity. Ensuring the commitment of the private sector (particularly in the sustainable beef platform) will survive any changes in the public sector when there is a change in administration. The project will incorporate new staff members in the training programs to continue raising awareness and building capacities in ELUP. The project´s communication strategy will also contribute to awareness raising when there is a change in administration. | UNDP CO | Identified risk |
| Argentina´s financial crisis may affect timely availability of co-financing for project implementation or may reduce the co-financing due to budgetary restrictions | Financial | P= 3 I= 5 Significance: High Potential impacts: Budgetary restrictions especially at the provincial level may affect the operational budgets of the provinces and other government partners. Ongoing cofinancing programs could receive less funding. | The project will prioritize key strategic interventions. The UNDP CO will monitor the co-financing contributions to the project. UNDP, SGAyDS, provincial governments and INTA are the Project Board members and will hold regular dialogues at the highest political level on cofinancing issues and will seek to develop alternative strategies (.e.g partnerships with private sector or other stakeholders working in the target landscapes to mobilize additional resources) to reduce impacts on the project interventions in case the cofinancing contributions are affected. The stakeholder mapping will be updated in PY1 so new potential partners and co-financiers may be identified. | UNDP CO | Identified risk |
| Difficulties to keep ELUP in place including the sustainable use of ecosystems due to favorable market prices of commodities and prioritization of short-term economic growth and social delivery over conservation and sustainable use | Economic | P= 3 I= 3 Significance: Moderate Potential impacts: Variations in prices could influence land use decisions, e.g., current or increased prices could favor continued expansion of the agricultural frontier. Ecosystems will continue to be degraded especially in urbanizing areas and other areas where economic activities are being undertaken or new areas where activities may be expanded. Proposed environmental benefits are not fully accrued. | Potential pressure of future land use changes in response to changes in economic and trade contexts (for instance, changes in commodity prices) could be offset based on: a) use of dialogue spaces to ensure that the new production interests and demands are met in a sustainable fashion; b) facilitation and incentives to maintain sustainable and compatibles uses, through applying the economic and financial instruments; c) support of the responsible authorities to keep the achieved ELUP in place or seek new ELUP based on the new contextual conditions; and d) valuation studies of ecosystem goods and services to demonstrate the most favorable scenarios for land use and raise awareness to ensure sustainable interventions. | UNDP CO | Identified risk |
| Landowners and communities are not aware of the need to adopt sustainable and environmentally-friendly best practices and their advantages to help improve production, productivity and livelihoods, and are reluctant to engage and adopt best practices | Socio-economic | P= 3 I= 3 Significance: Moderate Potential impacts: Delay in uptake of sustainable and environmentally-friendly best practices and the proposed environmental benefits are not fully accrued. | ELUP approach will serve to determine the best land uses and options of best practices for each target landscape. Valuation studies will serve to demonstrate the most favorable scenarios for land uses in the provinces and raise awareness of these stakeholders on the subject. Dialogue mechanisms will contribute to raise awareness on the need for sustainable and environmentally friendly productive interventions. The economic and financial instruments will contribute to adoption of best practices. Strengthening of value chains and improved market access for sustainable beef will help encourage producers by improving their incomes. Gender and multi-cultural mainstreaming throughout project activities in the target landscapes will also help facilitate adoption. The project´s training and communication strategies will reinforce the project´s messages on the advantages of adopting best practices. | UNDP CO | Identified risk |
| The project activities will take place within and adjacent to critical habitats and/or environmentally sensitive areas, including legally protected areas and indigenous people’s lands. The risk is that unless proposed land uses take into account ecosystem structure and function limitations, it may adversely affect conservation values of these areas. | Socio-economic | P= 3 I= 1 Significance: Low Potential impacts: Negative impacts on conservation values of critical habitats and/or environmentally sensitive areas | The focus of the project is precisely on maintaining areas that are identified as being priorities for their high biodiversity conservation value; or that are identified as vulnerable to land degradation, and in turn, loss of ecosystem goods and services that are important for livelihoods and production sectors. The project will foster land use planning, governance and management that harmonize national, provincial and local priorities that will guide land use to those activities and practices that do not harm ecosystem goods and services. | UNDP CO | Identified risk |
| The project will support land use planning and regulation in sensitive areas where economic activity could potentially impact the ecosystem. This may result in economic displacement (e.g., loss of access to resources due to land use restrictions) and could have an opportunity cost to small-scale producers although there will be no loss of access to land or physical relocation. | Socio-economic | P= 3 I= 3 Significance: Moderate Potential impacts: Conflicts between small scale producers and indigenous peoples and government agencies over land uses. Lack of alternatives for these stakeholders may result in displacement, increased poverty and rural exodus. | The project strategy has been designed to compensate any potential opportunity costs in the short term by testing a range of incentives and compensation mechanisms. In parallel it will work through sectoral programmes and facilitate access to markets or credit to increase financial flows in the medium term to transition to new production or provide continued support for private conservation. Potential pressure of future land use changes in response to changes in economic and trade contexts (for instance, changes in commodity prices) would also be offset based on: a) use of multi-stakeholder dialogue platforms/sustainable commodities platform to coordinate new production interests and demands; b) testing of economic and financial instruments to maintain sustainable and compatibles uses. The main focus of the project strategy is to promote sustainable uses that guarantee the preservation and improvement of the ecosystems and their services as well as livelihoods, particularly of Indigenous Peoples. Decisions regarding the territories inhabited by Indigenous Peoples will be taken in accordance with the regulatory framework on Indigenous Peoples’ Human Rights, undertaking prior consultation in all cases and FPIC when required. The draft Indigenous Peoples Plan, which is included in the Project Document, will be further developed during the first year of implementation into a fully detailed Plan. | UNDP CO | Identified risk |
| Indigenous peoples are present in the selected pilot sites of the provinces of Mendoza and Jujuy. Some of the environmentally sensitive areas may be located in their lands and unless the culturally appropriate consultations are carried out with the objective of achieving FPIC, the land use planning in these areas may affect the rights and interests, lands, resources, territories and traditional livelihoods of the indigenous peoples concerned | Socio-economic | P= 4 I= 2 Significance: Moderate Potential impacts: Weakened participation of indigenous peoples could create resistance of communities toward the project. Communities could decide not to work with the project. Reduced adoption of environmentally friendly and sustainable practices | Environmental Land Use Planning is essentially a participatory tool, and this principle will prevail during project implementation. To this effect a project Stakeholder Engagement Plan (Project Document Annex F) and a draft IPP (Annex E-1) have been developed that include several participatory mechanisms and specific provisions and measures. This draft IPP will be developed in detail during project year 1. At target landscape level the action lines outlined in the Project Document will be defined in detail during project implementation. For this the project will apply prior consultations at all times and FPIC will be ensured on any matters that may affect the rights and interests, lands, resources, territories, namely extraction of natural resources such as felling, mining or agricultural activities in their lands or territories; a decision affecting the status or people’s rights to their land/territories, resources or means of support; access to traditional knowledge and practices; commercial use of natural and / or cultural resources in plots of land subject to traditional ownership rights and / or traditional use by indigenous peoples; decisions regarding benefit sharing arrangements, where the benefits are derived from their land, territories or resources (eg., management of natural resources or extractive industries). The project will take advantage of the existing institutional experience in consultation processes in Mendoza and Jujuy, as well as the existing community structures and organizations, and protocols and processes that have already proven successful with the indigenous communities that will participate in project interventions. In addition, at provincial level participation of indigenous peoples will fostered in two spaces. One of them will be the the multi-stakeholder dialogue spaces (Output 2.2) which will engage stakeholders with different levels of power and use of resources in participatory land use planning. Another space will be a Provincial Project Working Group, which will include key stakeholders involved in project implementation and will be in charge of providing strategic guidance in each pilot province. Furthermore, these mechanisms will be strengthened through communication and capacity building for informed consent that will be implemented at provincial level within the dialogue platforms (Output 2.2) and at pilot site level within the consultation processes for planning and implementing field interventions (Output 2.4). A System for Prevention and Management of Consultations and Conflicts (project-level grievance redress mechanism) will be put in place to prevent potential conflicts, manage conflicts that may arise and to serve as a grievance mechanism. | UNDP CO | Identified risk |
| The project could potentially limit women’s ability to use, develop and protect natural resources, taking into account the different roles and positions of women and men in accessing environmental goods and services | Socio-economic | I = 3 P = 3 Significance: Moderate Potential impacts: Weakened participation of women could create resistance of communities toward the project. Communities could decide not to work with the project. Reduced adoption of environmentally friendly and sustainable practices | A gender analysis was undertaken during the PPG. The findings were used to develop a Gender Analysis and Action Plan, which will be implemented throughout the project. (See Annex G of the Project Document). Key strategies include: 1) All data, reports and inputs for the development of the policy, economic, financial and technical instruments and governance mechanisms for ELUP will be looked at through a gender and intercultural view. 2) The project will develop a capacity building program aimed at public officials and/or technical teams to raise awareness on the importance of engaging both women and men in decision-making processes and addressing gender issues, such as how the different roles and positions of women and men affect the use, development and protection of environmental goods and services. 3) Gender and ethnicity will be mainstreamed in the dialogue mechanisms by fostering equal participation of women and men and indigenous populations in agenda-setting, decision-making and/or policy-making processes. 4) The project will develop a capacity building program aimed at women beneficiaries (indigenous and non-indigenous) in the three prioritized areas and target landscapes to: i) promote gender equality in the management, use and conservation of biodiversity; ii) ensure that both women and men´s needs are addressed through the project interventions; iii) engaging men and women equally in order to ensure their participation in multi-sectoral and multi-stakeholder dialogue spaces. 5) The project will enhance knowledge management by systematizing, assessing, replicating and/or scaling up lessons learned, case studies, and promising and/or best practices on gender mainstreaming and the multicultural approach in BD/SLM and ELUP. | UNDP CO | Identified risk |
| Impacts of climate change: Land use suitability could change due to climate change, making potential outcomes of the project sensitive or vulnerable to potential impacts of climate change | Environmental | P= 3 I= 3 Significance: Moderate Potential impacts: Displacement of current production areas to new areas may generate land use conflicts. ELUP frameworks may change at slow rates and may not adapt to changing local realities. Producers, especially small scale poor producers, may not have the capacities to access and undertake new investments to reduce potential risks, increasing rural exodus. This may influence uptake of sustainable practices. | Permanent monitoring of ecosystem services and different related land uses, together with reinforced, more efficient institutions will lead to a flexible and adjustable ELUP management model that will help to increase resilience to climate change. Coordination with ongoing projects that share intervention areas to exchange experiences and lessons, in particular the GEF-UNDP Project 5044 “Sustainable Land Use Management in the Drylands of North-west Argentina” and the Adaptation Fund Project “Increasing climate resilience and improving sustainable land management in the South-west of the Province of Buenos Aires. As part of the multi-stakeholder coordination under Outcome 1 the project will participate in the roundtables of the National Climate Change Cabinet and in turn the institutions that comprise this cabinet will be invited to participate in the dialogue spaces for participatory ELUP where the proposals for regulations and instruments will be discussed and validated. Climate change considerations will be mainstreamed in these processes through these participatory spaces. Discussions on climate change and its potential impacts will also be a part of the participatory dialogue spaces at provincial level under Outcome 2. The project will promote environmentally friendly and sustainable practices (Outcome 2). Selection of best practices will take into account the vulnerabilities and impacts of climate change identified for the different regions of Argentina and adaptation needs. The adoption of SLM practices that favor adequate management of soils and water in productive systems (e.g., silvo-pastoral systems, live fences, restoration of lands and forests, zero tilling, crop rotation) will serve to minimize the impacts of climate variability and favor adaptation. The development of economic and financial incentives (Outcomes 1 and 2) will take into account the potential effects of climate change and will incorporate this consideration (e.g., incentives for practices that favor adaptation). The assessment of experiences and lessons acquired through programs and projects under Outcome 3 will also take into account knowledge generated by these initiatives in regard to climate change The project will also include awareness raising and training of landowners and communities for a better understanding of vulnerability and climate change impacts. | UNDP CO | Identified risk |

## Annex I:  Results of the capacity assessment of the project implementing partner

Province of Buenos Aires

| Capacity Result / Indicator | Staged Indicators | Rating | Score | Comments | Next Steps | Contribution to which outcome |
| --- | --- | --- | --- | --- | --- | --- |
| CR 1: Capacities for Engagement |  |  |  |  |  |  |
| Indicator 1: Degree of legitimacy/mandate of lead environmental organizations | Organizational responsibilities for environmental management are not clearly defined | 0 |  |  |  |  |
|  | Organizational responsibilities for environmental management are identified | 1 |  |  |  |  |
|  | Authority and legitimacy of all lead organizations responsible for environmental management are partially recognized by stakeholders | 2 | 2 |  | Promote OPDS as leader in the provincial ELUP process | 2 |
|  | Authority and legitimacy of all lead organizations responsible for environmental management recognized by stakeholders | 3 |  |  |  |  |
| Indicator 2: Existence of operational co-management mechanisms | Some co-management mechanisms are formally established through agreements, MOUs, etc. | 0 |  |  |  |  |
|  | Some co-management mechanisms are in place and operational | 1 |  |  |  |  |
|  | Some co-management mechanisms are formally established through agreements, MOUs, etc. | 2 | 2 | There are mechanisms through agreements |  |  |
|  | Comprehensive co-management mechanisms are formally established and are operational/functional | 3 |  |  |  |  |
| Indicator 3: Existence of cooperation with stakeholder groups | Identification of stakeholders and their participation/involvement in decision-making is poor | 0 |  |  |  |  |
|  | Stakeholders are identified but their participation in decision-making is limited | 1 |  |  |  |  |
|  | Stakeholders are identified and regular consultations mechanisms are established | 2 | 2 | Consultation mechanisms and processes in place | Consultation mechanisms are not specific to ELUP. Build on existing mechanisms to improve them for ELUP |  |
|  | Stakeholders are identified and they actively contribute to established participative decision making processes | 3 |  |  |  |  |
|  |  | 9 | 6 |  |  |  |
|  |  |  | 66,6% |  |  |  |
| CR 2: Capacities to Generate, Access and Use Information and Knowledge |  |  |  |  |  |  |
| Indicator 4: Degree of environmental awareness of stakeholders | Stakeholders are not aware about global environmental issues and their related possible solutions (MEAs) | 0 |  |  |  |  |
|  | Stakeholders are aware about global environmental issues but not about the possible solutions (MEAs) | 1 |  |  |  |  |
|  | Stakeholders are aware about global environmental issues and the possible solutions but do not know how to participate | 2 | 2 | Although key stakeholders are aware of ELUP, there are neither coordination spaces nor specific regulations to define their participation in ELUP | Consolidation of participatory spaces for ELUP with key stakeholders | 2 |
|  | Stakeholders are aware about global environmental issues and are actively participating in the implementation of related solutions | 3 |  |  |  |  |
| Indicator 5: Access and sharing of environmental information by stakeholders | The environmental information needs are not identified and the information management infrastructure is inadequate | 0 |  |  |  |  |
|  | The environmental information needs are identified but the information management infrastructure is inadequate | 1 | 1 | Needs are identified, but infrastructure is not adequate since information is disperse and must be systematized | Strengthening of information platforms to concentrate information and disseminate to stakeholders |  |
|  | The environmental information is partially available and shared among stakeholders but is not covering all focal areas and/or the information management infrastructure to manage and give information access to the public is limited | 2 |  |  |  |  |
|  | Comprehensive environmental information is available and shared through an adequate information management infrastructure | 3 |  |  |  |  |
| Indicator 6: Existence of environmental education programmes | No environmental education programmes are in place | 0 |  |  |  |  |
|  | Environmental education programmes are partially developed and partially delivered | 1 | 1 | There are educational programs addressing different sectors but none specific to ELUP | Develop training programs on ELUP and participation |  |
|  | Environmental education programmes are fully developed but partially delivered | 2 |  |  |  |  |
|  | Comprehensive environmental education programmes exist and are being delivered | 3 |  |  |  |  |
| Indicator 7: Extent of the linkage between environmental research/science and policy development | No linkage exist between environmental policy development and science/research strategies and programmes | 0 |  |  |  |  |
|  | Research needs for environmental policy development are identified but are not translated into relevant research strategies and programmes | 1 |  |  |  |  |
|  | Relevant research strategies and programmes for environmental policy development exist but the research information is not responding fully to the policy research needs | 2 | 2 |  | Incorporation of academic and scientific contributions to discussion and proposals for ELUP | 2 |
|  | Relevant research results are available for environmental policy development | 3 |  |  |  |  |
| Indicator 8: Extent of inclusion/use of traditional knowledge in environmental decision-making | Traditional knowledge is ignored and not taken into account into relevant participative decision-making processes | 0 | N/A |  |  |  |
|  | Traditional knowledge is identified and recognized as important but is not collected and used in relevant participative decision-making processes | 1 |  |  |  |  |
|  | Traditional knowledge is collected but is not used systematically into relevant participative decisionmaking processes | 2 |  |  |  |  |
|  | Traditional knowledge is collected, used and shared for effective participative decision-making processes | 3 |  |  |  |  |
|  |  | 12 | 6 |  |  |  |
|  |  |  | 50% |  |  |  |
| CR 3: Capacities for Strategy, Policy and Legislation Development |  |  |  |  |  |  |
| Indicator 9: Extent of the environmental planning and strategy development process | The environmental planning and strategy development process is not coordinated and does not produce adequate environmental plans and strategies | 0 |  |  |  |  |
|  | The environmental planning and strategy development process does produce adequate environmental plans and strategies but there are not implemented/used | 1 | 1 | There are ELUP planning strategies but have not been implemented | Incorporation of ELUP strategies in planning processes |  |
|  | Adequate environmental plans and strategies are produced but there are only partially implemented because of funding constraints and/or other problems | 2 |  |  |  |  |
|  | The environmental planning and strategy development process is well coordinated by the lead environmental organizations and produces the required environmental plans and strategies; which are being implemented | 3 |  |  |  |  |
| Indicator 10: Existence of adequate environmental policy and regulatory frameworks | The environmental policy and regulatory frameworks are insufficient; they do not provide an enabling environment | 0 |  |  |  |  |
|  | Some relevant environmental policies and laws exist but few are implemented and enforced | 1 |  |  |  |  |
|  | Adequate environmental policy and legislation frameworks exist but there are problems in implementing and enforcing them | 2 | 2 | There are sectoral policies and regulations but none specific to ELUP | Develop specific ELUP strategies |  |
|  | Adequate policy and legislation frameworks are implemented and provide an adequate enabling environment; a compliance and enforcement mechanism is established and functions | 3 |  |  |  |  |
| Indicator 11: Adequacy of the environmental information available for decision-making | The availability of environmental information for decision-making is lacking | 0 |  |  |  |  |
|  | Some environmental information exists but it is not sufficient to support environmental decision-making processes | 1 | 1 | Information partially incorporated but there is still relevant information that must be generated. | Information generation for ELUP and dissemination to stakeholders | 2 |
|  | Relevant environmental information is made available to environmental decision-makers but the process to update this information is not functioning properly | 2 |  |  |  |  |
|  | Political and administrative decision-makers obtain and use updated environmental information to make environmental decisions | 3 |  |  |  |  |
|  |  | 9 | 4 |  |  |  |
|  |  |  | 44.4% |  |  |  |
| CR 4: Capacities for Management and Implementation |  |  |  |  |  |  |
| Indicator 12: Existence and mobilization of resources | The environmental organizations don’t have adequate resources for their programmes and projects and the requirements have not been assessed | 0 |  |  |  |  |
|  | The resource requirements are known but are not being addressed | 1 |  |  |  |  |
|  | The funding sources for these resource requirements are partially identified and the resource requirements are partially addressed | 2 | 2 | Needs partially identified but not all resources required available for development of ELUP | Strengthening access to necessary resources for ELUP | 2 |
|  | Adequate resources are mobilized and available for the functioning of the lead environmental organizations | 3 |  |  |  |  |
| Indicator 13: Availability of required technical skills and technology transfer | The necessary required skills and technology are not available and the needs are not identified | 0 |  |  |  |  |
|  | The required skills and technologies needs are identified as well as their sources | 1 |  |  |  |  |
|  | The required skills and technologies are obtained but their access depend on foreign sources | 2 | 2 | Technical capacity at national level which must be updated and made sustainable at policy level. ELUP depends on foreign sources. | Exchange of information and improvement of ELUP in each territory; capacity building |  |
|  | The required skills and technologies are available and there is a national-based mechanism for updating the required skills and for upgrading the technologies | 3 |  |  |  |  |
|  |  | 6 | 4 |  |  |  |
|  |  |  | 66.6% |  |  |  |
| CR 5: Capacities to Monitor and Evaluate |  |  |  |  |  |  |
| Indicator 14: Adequacy of the project/programme monitoring process | Irregular project monitoring is being done without an adequate monitoring framework detailing what and how to monitor the particular project or programme | 0 |  |  |  |  |
|  | An adequate resourced monitoring framework is in place but project monitoring is irregularly conducted | 1 | 1 | Monitoring frameworks exist but are irregularly conducted, without participation of key stakeholders | Develop participatory monitoring system |  |
|  | Regular participative monitoring of results in being conducted but this information is only partially used by the project/programme implementation team | 2 |  |  |  |  |
|  | Monitoring information is produced timely and accurately and is used by the implementation team to learn and possibly to change the course of action | 3 |  |  |  |  |
| Indicator 15: Adequacy of the project/programme evaluation process | None or ineffective evaluations are being conducted without an adequate evaluation plan; including the necessary resources | 0 |  |  |  |  |
|  | An adequate evaluation plan is in place but evaluation activities are irregularly conducted | 1 | 1 | There are evaluation plans but irregularly conducted without participation of key stakeholders | Develop participatory evaluation system |  |
|  | Evaluations are being conducted as per an adequate evaluation plan but the evaluation results are only partially used by the project/programme implementation team | 2 |  |  |  |  |
|  | Effective evaluations are conducted timely and accurately and are used by the implementation team and the Agencies and GEF Staff to correct the course of action if needed and to learn for further planning activities | 3 |  |  |  |  |
|  |  | 6 | 2 |  |  |  |
|  |  |  | 33.3% |  |  |  |
| Total |  |  | 48.88% |  |  |  |

Province of Jujuy

| Capacity Result / Indicator | Staged Indicators | Rating | Score | Comments | Next Steps | Contribution to which outcome |
| --- | --- | --- | --- | --- | --- | --- |
| CR 1: Capacities for Engagement |  |  |  |  |  |  |
| Indicator 1: Degree of legitimacy/mandate of lead environmental organizations | Organizational responsibilities for environmental management are not clearly defined | 0 |  |  |  |  |
|  | Organizational responsibilities for environmental management are identified | 1 |  |  |  |  |
|  | Authority and legitimacy of all lead organizations responsible for environmental management are partially recognized by stakeholders | 2 | 2 |  | Strengthening of capacities of the Ministry of Environment and coordination with other government stakeholders | 2 |
|  | Authority and legitimacy of all lead organizations responsible for environmental management recognized by stakeholders | 3 |  |  |  |  |
| Indicator 2: Existence of operational co-management mechanisms | Some co-management mechanisms are formally established through agreements, MOUs, etc. | 0 |  |  |  |  |
|  | Some co-management mechanisms are in place and operational | 1 | 1 | There are specific mechanisms but not in relation to ELUP | Development of inter-institutional coordination mechanisms for target landscapes and upscaling to province level | 2 |
|  | Some co-management mechanisms are formally established through agreements, MOUs, etc. | 2 |  |  |  |  |
|  | Comprehensive co-management mechanisms are formally established and are operational/functional | 3 |  |  |  |  |
| Indicator 3: Existence of cooperation with stakeholder groups | Identification of stakeholders and their participation/involvement in decision-making is poor | 0 |  |  |  |  |
|  | Stakeholders are identified but their participation in decision-making is limited | 1 |  |  |  |  |
|  | Stakeholders are identified and regular consultations mechanisms are established | 2 | 2 | Key stakeholders are clearly identified. There are consultation processes in place to address policy development but mostly sector oriented (e.g. tourism, mining) | Improvement of coordination capacity between productive stakeholders and communities | 2 |
|  | Stakeholders are identified and they actively contribute to established participative decision making processes | 3 |  |  |  |  |
|  |  | 9 | 5 |  |  |  |
|  |  |  | 55.5% |  |  |  |
| CR 2: Capacities to Generate, Access and Use Information and Knowledge |  |  |  |  |  |  |
| Indicator 4: Degree of environmental awareness of stakeholders | Stakeholders are not aware about global environmental issues and their related possible solutions (MEAs) | 0 |  |  |  |  |
|  | Stakeholders are aware about global environmental issues but not about the possible solutions (MEAs) | 1 | 1 | Provincial institutions (INTA, Ministry of Environment) work under an ELUP approach | Strengthening of knowledge and work approaches with other stakeholders | 2 |
|  | Stakeholders are aware about global environmental issues and the possible solutions but do not know how to participate | 2 |  |  |  |  |
|  | Stakeholders are aware about global environmental issues and are actively participating in the implementation of related solutions | 3 |  |  |  |  |
| Indicator 5: Access and sharing of environmental information by stakeholders | The environmental information needs are not identified and the information management infrastructure is inadequate | 0 |  |  |  |  |
|  | The environmental information needs are identified but the information management infrastructure is inadequate | 1 |  |  |  |  |
|  | The environmental information is partially available and shared among stakeholders but is not covering all focal areas and/or the information management infrastructure to manage and give information access to the public is limited | 2 | 2 | There is information available; need to generate more information |  | 2 |
|  | Comprehensive environmental information is available and shared through an adequate information management infrastructure | 3 |  |  |  |  |
| Indicator 6: Existence of environmental education programmes | No environmental education programmes are in place | 0 |  |  |  |  |
|  | Environmental education programmes are partially developed and partially delivered | 1 | 1 | The Ministry has educational programs | Development of ELUP related training programs and specific subjects e.g. participation and indigenous peoples | 2 |
|  | Environmental education programmes are fully developed but partially delivered | 2 |  |  |  |  |
|  | Comprehensive environmental education programmes exist and are being delivered | 3 |  |  |  |  |
| Indicator 7: Extent of the linkage between environmental research/science and policy development | No linkage exist between environmental policy development and science/research strategies and programmes | 0 |  |  |  |  |
|  | Research needs for environmental policy development are identified but are not translated into relevant research strategies and programmes | 1 | 1 | INTA and government programs e.g. Family Agriculture have generated information | Strengthening of strategies and programs related to science and technology working with INTA | 2 |
|  | Relevant research strategies and programmes for environmental policy development exist but the research information is not responding fully to the policy research needs | 2 |  |  |  |  |
|  | Relevant research results are available for environmental policy development | 3 |  |  |  |  |
| Indicator 8: Extent of inclusion/use of traditional knowledge in environmental decision-making | Traditional knowledge is ignored and not taken into account into relevant participative decision-making processes | 0 |  |  |  |  |
|  | Traditional knowledge is identified and recognized as important but is not collected and used in relevant participative decision-making processes | 1 |  |  |  |  |
|  | Traditional knowledge is collected but is not used systematically into relevant participative decision making processes | 2 | 2 | Consultation processes are undertaken. Ministry of Environment coordinates closely with the Indigenous Peoples Secretariat | Specific consultation processes in each target landscape for development of ELUP processes | 2 |
|  | Traditional knowledge is collected, used and shared for effective participative decision-making processes | 3 |  |  |  |  |
|  |  | 15 | 7 |  |  |  |
|  |  |  | 46,6% |  |  |  |
| CR 3: Capacities for Strategy, Policy and Legislation Development |  |  |  |  |  |  |
| Indicator 9: Extent of the environmental planning and strategy development process | The environmental planning and strategy development process is not coordinated and does not produce adequate environmental plans and strategies | 0 |  |  |  |  |
|  | The environmental planning and strategy development process does produce adequate environmental plans and strategies but there are not implemented/used | 1 | 1 | There are several sector planning strategies but integrated planning strategies are needed | Develop integrated strategies for ELUP |  |
|  | Adequate environmental plans and strategies are produced but there are only partially implemented because of funding constraints and/or other problems | 2 |  |  |  |  |
|  | The environmental planning and strategy development process is well coordinated by the lead environmental organizations and produces the required environmental plans and strategies; which are being implemented | 3 |  |  |  |  |
| Indicator 10: Existence of adequate environmental policy and regulatory frameworks | The environmental policy and regulatory frameworks are insufficient; they do not provide an enabling environment | 0 |  |  |  |  |
|  | Some relevant environmental policies and laws exist but few are implemented and enforced | 1 |  |  |  |  |
|  | Adequate environmental policy and legislation frameworks exist but there are problems in implementing and enforcing them | 2 | 2 | There are sectoral regulations and policies but no ELUP regulatory framework | Develop specific strategies for ELUP |  |
|  | Adequate policy and legislation frameworks are implemented and provide an adequate enabling environment; a compliance and enforcement mechanism is established and functions | 3 |  |  |  |  |
| Indicator 11: Adequacy of the environmental information available for decision-making | The availability of environmental information for decision-making is lacking | 0 |  |  |  |  |
|  | Some environmental information exists but it is not sufficient to support environmental decision-making processes | 1 | 1 | Information is partially incorporated but generation of information is still necessary | Promote generation of sufficient and adequate information for ELUP decision making | 2 |
|  | Relevant environmental information is made available to environmental decision-makers but the process to update this information is not functioning properly | 2 |  |  |  |  |
|  | Political and administrative decision-makers obtain and use updated environmental information to make environmental decisions | 3 |  |  |  |  |
|  |  | 9 | 4 |  |  |  |
|  |  |  | 44.4% |  |  |  |
| CR 4: Capacities for Management and Implementation |  |  |  |  |  |  |
| Indicator 12: Existence and mobilization of resources | The environmental organizations don’t have adequate resources for their programmes and projects and the requirements have not been assessed | 0 |  |  |  |  |
|  | The resource requirements are known but are not being addressed | 1 |  |  |  |  |
|  | The funding sources for these resource requirements are partially identified and the resource requirements are partially addressed | 2 | 2 | The needs are partially identified and not all the resources for their development are available | Strengthening of resources for ELUP |  |
|  | Adequate resources are mobilized and available for the functioning of the lead environmental organizations | 3 |  |  |  |  |
| Indicator 13: Availability of required technical skills and technology transfer | The necessary required skills and technology are not available and the needs are not identified | 0 |  |  |  |  |
|  | The required skills and technologies needs are identified as well as their sources | 1 | 1 |  | Exchange of information and improve progress toward ELUP in each territory. Capacity building |  |
|  | The required skills and technologies are obtained but their access depend on foreign sources | 2 |  |  |  |  |
|  | The required skills and technologies are available and there is a national-based mechanism for updating the required skills and for upgrading the technologies | 3 |  |  |  |  |
|  |  | 6 | 3 |  |  |  |
|  |  |  | 50% |  |  |  |
| CR 5: Capacities to Monitor and Evaluate |  |  |  |  |  |  |
| Indicator 14: Adequacy of the project/programme monitoring process | Irregular project monitoring is being done without an adequate monitoring framework detailing what and how to monitor the particular project or programme | 0 |  |  |  |  |
|  | An adequate resourced monitoring framework is in place but project monitoring is irregularly conducted | 1 | 1 |  | Adjustment and implementation of current monitoring | 2 |
|  | Regular participative monitoring of results in being conducted but this information is only partially used by the project/programme implementation team | 2 |  |  |  |  |
|  | Monitoring information is produced timely and accurately and is used by the implementation team to learn and possibly to change the course of action | 3 |  |  |  |  |
| Indicator 15: Adequacy of the project/programme evaluation process | None or ineffective evaluations are being conducted without an adequate evaluation plan; including the necessary resources | 0 |  |  |  |  |
|  | An adequate evaluation plan is in place but evaluation activities are irregularly conducted | 1 | 1 |  | Improvement of the current evaluation system |  |
|  | Evaluations are being conducted as per an adequate evaluation plan but the evaluation results are only partially used by the project/programme implementation team | 2 |  |  |  |  |
|  | Effective evaluations are conducted timely and accurately and are used by the implementation team and the Agencies and GEF Staff to correct the course of action if needed and to learn for further planning activities | 3 |  |  |  |  |
|  |  | 6 | 2 |  |  |  |
|  |  |  | 33.3% |  |  |  |
| Total Score |  |  | 48.8% |  |  |  |

Province of Mendoza

| Capacity Result / Indicator | Staged Indicators | Rating | Score | Comments | Next Steps | Contribution to which outcome |
| --- | --- | --- | --- | --- | --- | --- |
| CR 1: Capacities for Engagement |  |  |  |  |  |  |
| Indicator 1: Degree of legitimacy/mandate of lead environmental organizations | Organizational responsibilities for environmental management are not clearly defined | 0 |  |  |  |  |
|  | Organizational responsibilities for environmental management are identified | 1 |  |  |  |  |
|  | Authority and legitimacy of all lead organizations responsible for environmental management are partially recognized by stakeholders | 2 |  |  |  |  |
|  | Authority and legitimacy of all lead organizations responsible for environmental management recognized by stakeholders | 3 | 3 | There is a provincial ELUP law. The Provincial Land Use Planning Agency (APOT) is recognized and there are mechanisms for cooperation and co-management | Strengthening of APOT for ELUP implementation at municipal level. |  |
| Indicator 2: Existence of operational co-management mechanisms | Some co-management mechanisms are formally established through agreements, MOUs, etc. | 0 |  |  |  |  |
|  | Some co-management mechanisms are in place and operational | 1 |  |  |  |  |
|  | Some co-management mechanisms are formally established through agreements, MOUs, etc. | 2 | 2 | ELUP law establishes co-management mechanisms. The Provincial Land Use Planning Council (CEPOT) is the advisory and consultative body established by law; it is recognized and formally established | Strengthen co-management mechanisms to contribute to development of municipal ELUP plans |  |
|  | Comprehensive co-management mechanisms are formally established and are operational/functional | 3 |  |  |  |  |
| Indicator 3: Existence of cooperation with stakeholder groups | Identification of stakeholders and their participation/involvement in decision-making is poor | 0 |  |  |  |  |
|  | Stakeholders are identified but their participation in decision-making is limited | 1 |  |  |  |  |
|  | Stakeholders are identified and regular consultations mechanisms are established | 2 |  |  |  |  |
|  | Stakeholders are identified and they actively contribute to established participative decision making processes | 3 | 3 | ELUP related stakeholders are members of the CEPOT and participate in debates and decision making | Incorporate other stakeholders interested in ELUP |  |
|  |  | 9 | 8 |  |  |  |
|  |  |  | 88,8% |  |  |  |
| CR 2: Capacities to Generate, Access and Use Information and Knowledge |  |  |  |  |  |  |
| Indicator 4: Degree of environmental awareness of stakeholders | Stakeholders are not aware about global environmental issues and their related possible solutions (MEAs) | 0 |  |  |  |  |
|  | Stakeholders are aware about global environmental issues but not about the possible solutions (MEAs) | 1 |  |  |  |  |
|  | Stakeholders are aware about global environmental issues and the possible solutions but do not know how to participate | 2 |  |  |  |  |
|  | Stakeholders are aware about global environmental issues and are actively participating in the implementation of related solutions | 3 | 3 | Provincial ELUP law. Participatory space exists. | Improve access to participatory mechanisms | 2 |
| Indicator 5: Access and sharing of environmental information by stakeholders | The environmental information needs are not identified and the information management infrastructure is inadequate | 0 |  |  |  |  |
|  | The environmental information needs are identified but the information management infrastructure is inadequate | 1 |  |  |  |  |
|  | The environmental information is partially available and shared among stakeholders but is not covering all focal areas and/or the information management infrastructure to manage and give information access to the public is limited | 2 | 2 | Information exists but is disperse, must be organized and systematized and disseminated | Organize and systematize information | 2 |
|  | Comprehensive environmental information is available and shared through an adequate information management infrastructure | 3 |  |  |  |  |
| Indicator 6: Existence of environmental education programmes | No environmental education programmes are in place | 0 |  |  |  |  |
|  | Environmental education programmes are partially developed and partially delivered | 1 |  |  |  |  |
|  | Environmental education programmes are fully developed but partially delivered | 2 | 2 | There are specific educational programs | Strengthening of educational programs addressing ELUP | 2 |
|  | Comprehensive environmental education programmes exist and are being delivered | 3 |  |  |  |  |
| Indicator 7: Extent of the linkage between environmental research/science and policy development | No linkage exist between environmental policy development and science/research strategies and programmes | 0 |  |  |  |  |
|  | Research needs for environmental policy development are identified but are not translated into relevant research strategies and programmes | 1 |  |  |  |  |
|  | Relevant research strategies and programmes for environmental policy development exist but the research information is not responding fully to the policy research needs | 2 |  |  |  |  |
|  | Relevant research results are available for environmental policy development | 3 | 3 | The province works with academic, technical and scientific institutions. ELUP law was developed incorporating technical and scientific levels |  |  |
| Indicator 8: Extent of inclusion/use of traditional knowledge in environmental decision-making | Traditional knowledge is ignored and not taken into account into relevant participative decision-making processes | 0 |  |  |  |  |
|  | Traditional knowledge is identified and recognized as important but is not collected and used in relevant participative decision-making processes | 1 |  |  |  |  |
|  | Traditional knowledge is collected but is not used systematically into relevant participative decision making processes | 2 | 2 | Indigenous peoples are identified and traditional knowledge is being identified but not mainstreamed in ELUP policies | Mainstreaming of traditional knowledge in ELUP policies |  |
|  | Traditional knowledge is collected, used and shared for effective participative decision-making processes | 3 |  |  |  |  |
|  |  | 15 | 12 |  |  |  |
|  |  |  | 80% |  |  |  |
| CR 3: Capacities for Strategy, Policy and Legislation Development |  |  |  |  |  |  |
| Indicator 9: Extent of the environmental planning and strategy development process | The environmental planning and strategy development process is not coordinated and does not produce adequate environmental plans and strategies | 0 |  |  |  |  |
|  | The environmental planning and strategy development process does produce adequate environmental plans and strategies but there are not implemented/used | 1 |  |  |  |  |
|  | Adequate environmental plans and strategies are produced but there are only partially implemented because of funding constraints and/or other problems | 2 |  |  |  |  |
|  | The environmental planning and strategy development process is well coordinated by the lead environmental organizations and produces the required environmental plans and strategies; which are being implemented | 3 | 3 | There is an ELUP law detailing the processes to be fulfilled by ELUP strategies and is starting to be implemented at municipal level | Provide support to municipalities to develop local ELUP | 2 |
| Indicator 10: Existence of adequate environmental policy and regulatory frameworks | The environmental policy and regulatory frameworks are insufficient; they do not provide an enabling environment | 0 |  |  |  |  |
|  | Some relevant environmental policies and laws exist but few are implemented and enforced | 1 |  |  |  |  |
|  | Adequate environmental policy and legislation frameworks exist but there are problems in implementing and enforcing them | 2 | 2 | Regulatory frameworks exist at province and municipal levels but not implemented in the latter | Implementation of ELUP processes in municipalities of target landscapes and upscaling to the rest of the province | 2 |
|  | Adequate policy and legislation frameworks are implemented and provide an adequate enabling environment; a compliance and enforcement mechanism is established and functions | 3 |  |  |  |  |
| Indicator 11: Adequacy of the environmental information available for decision-making | The availability of environmental information for decision-making is lacking | 0 |  |  |  |  |
|  | Some environmental information exists but it is not sufficient to support environmental decision-making processes | 1 |  |  |  |  |
|  | Relevant environmental information is made available to environmental decision-makers but the process to update this information is not functioning properly | 2 | 2 | Channels to access and update information must be strengthened | Consolidation of disperse information and dissemination to key ELUP stakeholders |  |
|  | Political and administrative decision-makers obtain and use updated environmental information to make environmental decisions | 3 |  |  |  |  |
|  |  | 9 | 7 |  |  |  |
|  |  |  | 77.7% |  |  |  |
| CR 4: Capacities for Management and Implementation |  |  |  |  |  |  |
| Indicator 12: Existence and mobilization of resources | The environmental organizations don’t have adequate resources for their programmes and projects and the requirements have not been assessed | 0 |  |  |  |  |
|  | The resource requirements are known but are not being addressed | 1 |  |  |  |  |
|  | The funding sources for these resource requirements are partially identified and the resource requirements are partially addressed | 2 | 2 |  | Need to strengthen mechanisms for effective ELUP implementation |  |
|  | Adequate resources are mobilized and available for the functioning of the lead environmental organizations | 3 |  |  |  |  |
| Indicator 13: Availability of required technical skills and technology transfer | The necessary required skills and technology are not available and the needs are not identified | 0 |  |  |  |  |
|  | The required skills and technologies needs are identified as well as their sources | 1 |  |  |  |  |
|  | The required skills and technologies are obtained but their access depend on foreign sources | 2 |  |  |  |  |
|  | The required skills and technologies are available and there is a national-based mechanism for updating the required skills and for upgrading the technologies | 3 |  |  | Municipal level financing and capacity needs to be strengthened. Sustainability of mechanisms and transfers to municipalities. |  |
|  |  | 6 | 5 |  |  |  |
|  |  |  | 83.3% |  |  |  |
| CR 5: Capacities to Monitor and Evaluate |  |  |  |  |  |  |
| Indicator 14: Adequacy of the project/programme monitoring process | Irregular project monitoring is being done without an adequate monitoring framework detailing what and how to monitor the particular project or programme | 0 |  |  |  |  |
|  | An adequate resourced monitoring framework is in place but project monitoring is irregularly conducted | 1 |  |  |  |  |
|  | Regular participative monitoring of results in being conducted but this information is only partially used by the project/programme implementation team | 2 | 2 |  | Currently information is not used to update ELUP related data bases |  |
|  | Monitoring information is produced timely and accurately and is used by the implementation team to learn and possibly to change the course of action | 3 |  |  |  |  |
| Indicator 15: Adequacy of the project/programme evaluation process | None or ineffective evaluations are being conducted without an adequate evaluation plan; including the necessary resources | 0 |  |  |  |  |
|  | An adequate evaluation plan is in place but evaluation activities are irregularly conducted | 1 |  |  |  |  |
|  | Evaluations are being conducted as per an adequate evaluation plan but the evaluation results are only partially used by the project/programme implementation team | 2 | 2 | Results of evaluations are not incorporated into planning | Promote incorporation of results of evaluations into provincial and local planning |  |
|  | Effective evaluations are conducted timely and accurately and are used by the implementation team and the Agencies and GEF Staff to correct the course of action if needed and to learn for further planning activities | 3 |  |  |  |  |
|  |  | 6 | 4 |  |  |  |
|  |  |  | 66.6% |  |  |  |
| Total |  |  | 80% |  |  |  |

SGAyDS

| Capacity Result / Indicator | Staged Indicators | Rating | Score | Comments | Next Steps |  | Contribution to which outcome |
| --- | --- | --- | --- | --- | --- | --- | --- |
| CR 1: Capacities for Engagement |  |  |  |  |  |  |  |
| Indicator 1: Degree of legitimacy/mandate of lead environmental organizations | Organizational responsibilities for environmental management are not clearly defined | 0 |  |  |  |  |  |
|  | Organizational responsibilities for environmental management are identified | 1 |  |  |  |  |  |
|  | Authority and legitimacy of all lead organizations responsible for environmental management are partially recognized by stakeholders | 2 | 2 | SGAyDS is responsible for enforcement of the General Environment Law (GEL) and guarantees environmental protection. Although the SGAyDS is responsible for design and implementation of ELUP, land use planning is undertaken under a classical zoning view through the Planning Ministry | Recognize SGAyDS as leader in the ELUP process at national level |  | 1, 3 |
|  | Authority and legitimacy of all lead organizations responsible for environmental management recognized by stakeholders | 3 |  |  |  |  |  |
| Indicator 2: Existence of operational co-management mechanisms | Some co-management mechanisms are formally established through agreements, MOUs, etc. | 0 |  |  |  |  |  |
|  | Some co-management mechanisms are in place and operational | 1 |  |  |  |  |  |
|  | Some co-management mechanisms are formally established through agreements, MOUs, etc. | 2 | 2 |  | Coordination with institutions relevant to the development of dialogue platforms for ELUP at national level. Establishment of a multi-sector advisory committee. Establishment of a platform with actors working in ELUP with an integrated approach and building on work in progress |  | 1, 3 |
|  | Comprehensive co-management mechanisms are formally established and are operational/functional | 3 |  |  |  |  |  |
| Indicator 3: Existence of cooperation with stakeholder groups | Identification of stakeholders and their participation/involvement in decision-making is poor | 0 |  |  |  |  |  |
|  | Stakeholders are identified but their participation in decision-making is limited | 1 | 1 |  | Promote dialogue spaces where participation will transcend the usual basic consultation processes and involve stakeholders in decision making. |  | 1, 3 |
|  | Stakeholders are identified and regular consultations mechanisms are established | 2 |  |  |  |  |  |
|  | Stakeholders are identified and they actively contribute to established participative decision making processes | 3 |  |  |  |  |  |
| Scoring CR 1 |  | 9 | 5 |  |  |  |  |
|  |  |  | 55,5% |  |  |  |  |
| CR 2: Capacities to Generate, Access and Use Information and Knowledge |  |  |  |  |  |  |  |
| Indicator 4: Degree of environmental awareness of stakeholders | Stakeholders are not aware about global environmental issues and their related possible solutions (MEAs) | 0 |  |  |  |  |  |
|  | Stakeholders are aware about global environmental issues but not about the possible solutions (MEAs) | 1 | 1 | Some national level institutions have the knowledge but do not know possible solutions from an ELUP approach (there are sector based perspectives) | SGAyDS and INTA have been working for some time in these issues, but not all institutions are aware. Training and awareness raising tools will be developed for ELUP. ELUP mainstreaming, open discussions on possible solutions with other national institutions and organizations |  |  |
|  | Stakeholders are aware about global environmental issues and the possible solutions but do not know how to participate | 2 |  |  |  |  |  |
|  | Stakeholders are aware about global environmental issues and are actively participating in the implementation of related solutions | 3 |  |  |  |  |  |
| Indicator 5: Access and sharing of environmental information by stakeholders | The environmental information needs are not identified and the information management infrastructure is inadequate | 0 |  |  |  |  |  |
|  | The environmental information needs are identified but the information management infrastructure is inadequate | 1 |  |  |  |  |  |
|  | The environmental information is partially available and shared among stakeholders but is not covering all focal areas and/or the information management infrastructure to manage and give information access to the public is limited | 2 | 2 | Information is available and is shared through adequate systems but there is overlapping of information and mostly dispersed. Offer of information should be greater. There is a significant volume of information but coordination and sharing needs to be strengthened among stakeholders. | Identification and systematization of existing disperse and repeated information and making it available to the general public in accessible formats |  |  |
|  | Comprehensive environmental information is available and shared through an adequate information management infrastructure | 3 |  |  |  |  |  |
| Indicator 6: Existence of environmental education programmes | No environmental education programmes are in place | 0 |  |  |  |  |  |
|  | Environmental education programmes are partially developed and partially delivered | 1 | 1 | There is environmental information on ELUP, partially developed and accessible | Development of training programs on ELUP and other subjects related to participation and indigenous peoples |  |  |
|  | Environmental education programmes are fully developed but partially delivered | 2 |  |  |  |  |  |
|  | Comprehensive environmental education programmes exist and are being delivered | 3 |  |  |  |  |  |
| Indicator 7: Extent of the linkage between environmental research/science and policy development | No linkage exist between environmental policy development and science/research strategies and programmes | 0 |  |  |  |  |  |
|  | Research needs for environmental policy development are identified but are not translated into relevant research strategies and programmes | 1 | 1 | There are several initiatives that are partially oriented to existing and sector based scientific-political interfaces (CONADIBIO, ONDTyD, Climate Change Roundtable). Existing initiatives do not have integrated approaches | The advisory committee and the dialogue spaces at national level will promote incorporation of the scientific and academic sectors in discussion and generation of alternatives for ELUP |  |  |
|  | Relevant research strategies and programmes for environmental policy development exist but the research information is not responding fully to the policy research needs | 2 |  |  |  |  |  |
|  | Relevant research results are available for environmental policy development | 3 |  |  |  |  |  |
| Indicator 8: Extent of inclusion/use of traditional knowledge in Environmental decision-making | Traditional knowledge is ignored and not taken into account into relevant participative decision-making processes | 0 |  |  |  |  |  |
|  | Traditional knowledge is identified and recognized as important but is not collected and used in relevant participative decision-making processes | 1 | 1 | There are national policies addressing traditional knowledge and practices. Nevertheless mainstreaming of this knowledge in public policies or decision making processes is very low. There is little knowledge of these aspects related to traditional knowledge and potential impact on environmental public policies or decision making. | Coordination with state and non-state actors for identification of traditional knowledge and capacity building. Participation of indigenous peoples in dialogue spaces will help to improve this situation |  |  |
|  | Traditional knowledge is collected but is not used systematically into relevant participative decision making processes | 2 |  |  |  |  |  |
|  | Traditional knowledge is collected, used and shared for effective participative decision-making processes | 3 |  |  |  |  |  |
| Scoring CR 2 |  | 15 | 6 |  |  |  |  |
|  |  |  | 40% |  |  |  |  |
| CR 3: Capacities for Strategy, Policy and Legislation Development |  |  |  |  |  |  |  |
| Indicator 9: Extent of the environmental planning and strategy development process | The environmental planning and strategy development process is not coordinated and does not produce adequate environmental plans and strategies | 0 |  |  |  |  |  |
|  | The environmental planning and strategy development process does produce adequate environmental plans and strategies but there are not implemented/used | 1 |  |  |  |  |  |
|  | Adequate environmental plans and strategies are produced but there are only partially implemented because of funding constraints and/or other problems | 2 | 2 | There are sector based processes (Native Forests, Glaciers) | ELUP will provide a comprehensive framework to set guidelines for implementation of ELUP at national, provincial and local levels. |  |  |
|  | The environmental planning and strategy development process is well coordinated by the lead environmental organizations and produces the required environmental plans and strategies; which are being implemented | 3 |  |  |  |  |  |
| Indicator 10: Existence of adequate environmental policy and regulatory frameworks | The environmental policy and regulatory frameworks are insufficient; they do not provide an enabling environment | 0 |  |  |  |  |  |
|  | Some relevant environmental policies and laws exist but few are implemented and enforced | 1 | 1 | There are a few sectoral regulatory frameworks (Native Forests, Glaciers) | Development of instruments, policies, tools for ELUP implementation at national, provincial and municipal levels. |  |  |
|  | Adequate environmental policy and legislation frameworks exist but there are problems in implementing and enforcing them | 2 |  |  |  |  |  |
|  | Adequate policy and legislation frameworks are implemented and provide an adequate enabling environment; a compliance and enforcement mechanism is established and functions | 3 |  |  |  |  |  |
| Indicator 11: Adequacy of the environmental information available for decision-making | The availability of environmental information for decision-making is lacking | 0 |  |  |  |  |  |
|  | Some environmental information exists but it is not sufficient to support environmental decision-making processes | 1 | 1 | There are initiatives that need to be strengthened | Definition of criteria to determine relevance of information in accordance with the proposed national level strategy |  |  |
|  | Relevant environmental information is made available to environmental decision-makers but the process to update this information is not functioning properly | 2 |  |  |  |  |  |
|  | Political and administrative decision-makers obtain and use updated environmental information to make environmental decisions | 3 |  |  |  |  |  |
| Scoring CR 3 |  | 9 | 4 |  |  |  |  |
|  |  |  | 44,4% |  |  |  |  |
| CR 4: Capacities for Management and Implementation |  |  |  |  |  |  |  |
| Indicator 12: Existence and mobilization of resources | The environmental organizations don’t have adequate resources for their programmes and projects and the requirements have not been assessed | 0 |  |  |  |  |  |
|  | The resource requirements are known but are not being addressed | 1 |  |  |  |  |  |
|  | The funding sources for these resource requirements are partially identified and the resource requirements are partially addressed | 2 | 2 | There are necessary resources that have been identified for ELUP development, which need to be strengthened | Project will strengthen the resources needed for ELUP |  |  |
|  | Adequate resources are mobilized and available for the functioning of the lead environmental organizations | 3 |  |  |  |  |  |
| Indicator 13: Availability of required technical skills and technology transfer | The necessary required skills and technology are not available and the needs are not identified | 0 |  |  |  |  |  |
|  | The required skills and technologies needs are identified as well as their sources | 1 |  |  |  |  |  |
|  | The required skills and technologies are obtained but their access depend on foreign sources | 2 | 2 | There is technical capacity at national level that should be updated in relation to policies. Specifically for ELUP there is dependence on foreign sources | Exchange of information; improve progress toward ELUP in the territory; capacity building |  |  |
|  | The required skills and technologies are available and there is a national-based mechanism for updating the required skills and for upgrading the technologies | 3 |  |  |  |  |  |
| Scoring CR 4 |  | 6 | 4 |  |  |  |  |
|  |  |  | 66,6% |  |  |  |  |
| CR 5: Capacities to Monitor and Evaluate |  |  |  |  |  |  |  |
| Indicator 14: Adequacy of the project/programme monitoring process | Irregular project monitoring is being done without an adequate monitoring framework detailing what and how to monitor the particular project or programme | 0 |  |  |  |  |  |
|  | An adequate resourced monitoring framework is in place but project monitoring is irregularly conducted | 1 | 1 | There are monitoring frameworks but are irregularly conducted. No participation in monitoring | Development of monitoring system with participation of key stakeholders |  |  |
|  | Regular participative monitoring of results in being conducted but this information is only partially used by the project/programme implementation team | 2 |  |  |  |  |  |
|  | Monitoring information is produced timely and accurately and is used by the implementation team to learn and possibly to change the course of action | 3 |  |  |  |  |  |
| Indicator 15: Adequacy of the project/programme evaluation process | None or ineffective evaluations are being conducted without an adequate evaluation plan; including the necessary resources | 0 |  |  |  |  |  |
|  | An adequate evaluation plan is in place but evaluation activities are irregularly conducted | 1 | 1 | There are evaluation plans but are irregularly conducted. No dissemination of results | Development of a systematic evaluation system for ELUP implementation with stakeholder participation |  |  |
|  | Evaluations are being conducted as per an adequate evaluation plan but the evaluation results are only partially used by the project/programme implementation team | 2 |  |  |  |  |  |
|  | Effective evaluations are conducted timely and accurately and are used by the implementation team and the Agencies and GEF Staff to correct the course of action if needed and to learn for further planning activities | 3 |  |  |  |  |  |
| Scoring CR 5 |  | 6 | 2 |  |  |  |  |
|  |  |  | 33.3% |  |  |  |  |
| Total Score |  | 45 | 21 |  |  |  |  |
|  |  |  | 46.6% |  |  |  |  |

## Annex J:  Letter of Agreement with the Government of Argentina and Description of UNDP Country Office Support Services (Signed version will be included by ProDoc Signature)

LETTER OF AGREEMENT BETWEEN UNDP AND THE SECRETARIAT OF THE ENVORONMENT AND SUSTAINABLE DEVELOPMENT (SAyDS) OF ARGENTINA FOR THE IMPLEMENTATION OF THE PROJECT “MAINSTREAMING BIODIVERSITY CONSERVATION AND SUSTAONABLE LAND USE MANAGEMENT (SLM) INTO DEVELOPING PLANNING: MAKING ENVIRONMENTAL LAND USE PLANNING (ELUP) OPERATIONAL IN ARGENTINA” AWARD 00114826, PROJECT 00112703 WITHIN THE CONTEXT OF THE NATIONAL IMPLEMENTATION MODALITY.

Secretariat of the Government of Environment and Sustainable Development,

1.	Reference is made to consultations between officials of the Government of Argentina (hereinafter referred to as “the Government”) and officials of UNDP with respect to the provision of support services by the UNDP country office for nationally managed programmes and projects.  UNDP and the Government hereby agree that the UNDP country office may provide such support services at the request of the Government through its institution designated in the relevant programme support document or project document, as described below.

2.	The UNDP country office may provide support services for assistance with reporting requirements and direct payment.  In providing such support services, the UNDP country office shall ensure that the capacity of the Government-designated institution is strengthened to enable it to carry out such activities directly.  The costs incurred by the UNDP country office in providing such support services shall be recovered from the administrative budget of the office.

3.	The UNDP country office may provide, at the request of the designated institution, the following support services for the activities of the programme/project:

- Identification and/or recruitment of project and programme personnel;

- Identification and facilitation of training activities;

- Procurement of goods and services;

4.	The procurement of goods and services and the recruitment of project and programme personnel by the UNDP country office shall be in accordance with the UNDP regulations, rules, policies and procedures.  Support services described in paragraph 3 above shall be detailed in an annex to the programme support document or project document, in the form provided in the Attachment hereto.  If the requirements for support services by the country office change during the life of a programme or project

the annex to the programme support document or project document is revised with the mutual agreement of the UNDP resident representative and the designated institution.

5.	The relevant provisions of the Standard Basic Assistance Agreement signed on February 26, 1985 and approved by Law Nº23396 of October 10, 1986 between UNDP and the Government of Argentina, and the Country Programme (the “SBAA”), including the provisions on liability and privileges and immunities, shall apply to the provision of such support services. The Government shall retain overall responsibility for the nationally managed programme or project through its designated institution.  The responsibility of the UNDP country office for the provision of the support services described herein shall be limited to the provision of such support services detailed in the annex to the programme support document or project document.

6.	Any claim or dispute arising under or in connection with the provision of support services by the UNDP country office in accordance with this letter shall be handled pursuant to the relevant provisions of the SBAA.

7.	The manner and method of cost-recovery by the UNDP country office in providing the support services described in paragraph 3 above shall be specified in the annex to the programme support document or project document.

8.	The UNDP country office shall submit progress reports on the support services provided and shall report on the costs reimbursed in providing such services, as may be required.

9.	Any modification of the present arrangements shall be effected by mutual written agreement of the parties hereto.

10.	If you are in agreement with the provisions set forth above, please sign and return to this office two signed copies of this letter.  Upon your signature, this letter shall constitute an agreement between your Government and UNDP on the terms and conditions for the provision of support services by the UNDP country office for nationally managed programmes and projects.

Yours sincerely,

________________________

Signed on behalf of UNDP

_____________________

Signed on behalf of SAyDS

Attachment

# DESCRIPTION OF UNDP COUNTRY OFFICE SUPPORT SERVICES

1.	Reference is made to consultations between Secretariat of the Environment and Sustainable Development (SAyDS), the institution designated by the Government of Argentina and officials of UNDP with respect to the provision of support services by the UNDP country office for the nationally managed project “Mainstreaming Biodiversity Conservation And Sustainable Land Use Management (SLM) into Developing Planning: Making Environmental Land Use Planning (ELUP) Operational In Argentina” Award 00114826, Project 00112703 within the context of the National Implementation Modality.

2.	According with the present letter, the UNDP Country office will provide support services in compliance with the table below.

3.	Support services to be provided*

| Support services | Schedule for the support services provision | UNDP Cost for providing support services (when necessary) | Quantity and UNDP reimbursement method (when necessary) |
| --- | --- | --- | --- |
| - Payments, disbursements and other financial transactions | During the Project implementation | Universal Price List | Support services |
| - Staff, technical team and consultant recruitment. | During the Project implementation | Universal Price List | Support services |
| - Equipment and services recruitment, and inventory discharge. | During the Project implementation | Universal Price List | Support services |
| - Training activities, workshops and conference organization. | During the Project implementation | Universal Price List | Support services |
| - Trip authorization, security clearance, tickets and travel arrangements. | During the Project implementation | Universal Price List | Support services |
| - Delivery, sending, custom clearance, vehicles registry and accreditation. | During the Project implementation | Universal Price List | Support services |

*  Please refer to the enclosed table with the services breakdown per year.

Estimated Direct Project Costs/UNDP Country Office:

|  | Amount Year 1 USD | Amount Year 2 USD | Amount Year 3 USD | Amount Year 4 USD | Amount Year 5 USD | Amount Year 6 USD | TOTAL |
| --- | --- | --- | --- | --- | --- | --- | --- |
| UNDP Recovery Cost Charges | 49,729 | 49,729 | 49,733 | 49,735 | 49,736 | 49,736 | 298,398 |
| Payments, disbursements and other financial transactions | 12,206 | 8,206 | 11,206 | 11,206 | 11,206 | 12,206 | 66,236 |
| Staff, technical team and consultant recruitment. | 8,300 | 10,300 | 5,300 | 7,300 | 8,300 | 8,300 | 47,800 |
| Equipment and services recruitment, and inventory discharge. | 9,300 | 6,300 | 5,304 | 8,306 | 7,306 | 6,306 | 42,822 |
| Training activities, workshops and conference organization. | 7,306 | 7,306 | 11,306 | 5,306 | 5,306 | 8,306 | 44,836 |
| Trip authorization, security clearance, tickets and travel arrangements. | 8,306 | 8,306 | 9,306 | 9,306 | 7,306 | 5,306 | 47,836 |
| Delivery, sending, custom clearance, vehicles registry and accreditation. | 4,311 | 9,311 | 7,311 | 8,311 | 10,312 | 9,312 | 48,868 |
|  | 49,729 | 49,729 | 49,733 | 49,735 | 49,736 | 49,736 | 298,398 |

4.         The roles and responsibilities of the parties involved:

Please refer to Section VIII. Governance and Management Arrangements of the ProDoc for a complete description of the roles and responsibilities of the parties involved.

## Annex K :  UNDP Project Quality Assurance Report

(to be completed in UNDP online corporate planning system by UNDP Country Office, does not need to be attached as separate document)

## Annex L :  Target Landscapes Profiles and Maps

PROVINCE OF BUENOS AIRES

1. Parana River Delta

Area: 6,300 hectares

Ecoregions covered: Delta and islands of the Parana River

Municipalities involved: Campana and San Fernando.

Demographic and Socio-economic Description: The insular territories, the islands, as the mosaic of wetlands that make up the region is generally called, under the jurisdictions of the Provinces of Entre Ríos, Buenos Aires and Santa Fe, were and are a place of residence and work of family groups, in small numbers and with very low density that are dedicated to different fluvial and rural activities, mainly fishing, hunting, beekeeping, fruit growing and livestock, with the objectives of subsistence and provision of agricultural products or services to the urban sites in the mainland. Most of the inhabitants living in the Delta and working in the productive activities of the region, do so in precarious living conditions and with poor services infrastructure. Local communities are organized in territorial and water defense associations (assemblies or neighborhood associations), although national-level organizations that work with a focus on wetland protection have been identified, such as the Fundación Humedales. Likewise, the Delta Council of Producers (CONPRODEL) can be mentioned in this regard.

Environmental Description: The Paraná Delta is an immense wetland. As such, in addition to containing a rich biological diversity, it fulfills multiple and essential roles such as aquifer recharge and discharge, flood control, retention of sediments and nutrients, stabilization of coasts, protection against erosion, nursery for fish, regulation of the climate and an extensive list of goods and services for mankind. The geographical location grants the PD a particular importance, as it is adjacent to the most consolidated corridor of development and anthropic intervention in the country: the La Plata / Rosario axis. On the other hand, it is close to the mouth of the Paraná / Plata system, which gives it a particular morphological dynamism emphasized by the Parana-Paraguay Hidrovia, an increasingly important flow channel, which continuous dredging and maintenance offers a hydraulic filling material that is randomly made available and according to particular and changing interests.

The Delta stands out for the intrinsic value of biodiversity and the aesthetic value of the landscape, capacity for flood control, sediment retention and nutrient retention and export. Numerous species of fauna can fully or partially fulfill their life cycle. Many others, coming from neighboring continental areas, move towards it when conditions become unfavorable, turning it into a refuge in times of drought or lack of food. Some of the values ​​of the wetlands are: fishing resources (especially important for the local population), wildlife, fodder, forestry, transport and tourism, as well as an important supply of freshwater

Problems and Threats to BD and LD: Unfortunately, the Paraná Delta (DP) has not been an exception in terms of vulnerability to anthropic impacts and a clear example of such actions are the fires originated from the burning of grasslands. They impact on the wetland in direct function to the structure and virulence (intensity and extent) of the fire and its recurrence, insofar as it directly affects the resilience or buffer capacity of the ecosystem.

In addition to the productive activities and ways of appropriation developed by the locals, there are new imported practices being carried out in the terrestrial ecosystems that threaten the ecosystem´s ecological integrity, such as the integration of exotic flora and fauna species , the construction of flood "defense" slopes, the alteration of the natural height due to filling up, modification and creation of water bodies and building of closed urbanizations, among others.

OAT processes: OPDS is carrying out the project "Elaboration of the Province of Buenos Aires Wetland Inventory 2018/2019". It is worth mentioning the work and background of the Draft Law: "Conservation and environmental management of the Delta territory of the Province of Buenos Aires" prepared by the Directorate of Territorial Environmental Management of this Agency, from which guidelines can be drawn for the formulation of future actions to implement.

2. Riverine Forests, Eastern “Talares” and Samborombon Bay.

Area: 275,000 hectares

Ecoregions covered: Pampas

Municipalities involved: Magdalena, Punta Indio, Chascomús, Lezama and Castelli.

Demographic and Socio-economic Description:  Attention must be paid to the rural landowners in the fields located between the peri-urban and agricultural interface, since their land contains the largest area with this type of vegetation. In this area, it is important to work jointly with the Félix de Azara Foundation, which has extensive experience working on the subject, besides articulating with the provincial and grassroots stakeholders.

Environmental Description / Problems and threats to BD and LD: The pilot site includes tala forests (Celtis tala) that are distributed in the southeast of the province along the coast following the shell cordons and the forest formations of the soils with wavy relief entering the continent (eastern talares).

This area was selected not only because it is a strategic ecosystem due to its biodiversity, but also because of the provision of fresh water contained in the shell cordons of the Samborombón Bay wetland. This ecosystem good has diminished since extraction started at the beginning of the 20th century to such an extent that it affects the water supply sustainability of the area. The size of the removed water reserves (0.68 hm3) is significant for the environmental conditions of the region; taking into account that for a consumption of 200 L / inhabitant / day, it would have been enough to supply  a population of over 9000 inhabitants for 1 year (Tejada et al., 2011).

In addition, it is considered to be of strategic ecological value due to the interaction between the tala forests and wetlands, given that a synergy between them takes place. Some authors refer to this as: "joint productions" that are inseparable in most processes of nature (Turner et al., 2003). The forests that settle on the shell cordons perform a role of immobilization of the substrate and preservation of forms of the relief that are added to other ecosystem services (Morello J., 2006) regulation of hydrological systems, cycling of nutrients and climate. Shell mining activities, the proliferation of exotic species (plants and animals) and the substitution of talares to give rise to pastures and crop agriculture, with secondary or associated effects; as well as the harmful application of agrochemicals on the tala forests and the exploitation of firewood are some threats on the tala forests (Merida and ot., 2006).

The tala forest is most related to the urban progress of the province of Buenos Aires, with  the talares of ravine being the most fragmented; however, the talares of packsaddle are increasingly threatened by the extraction of shells. These native forested formations, where Celtis tala predominates, associated with different plant species, serve as habitat for numerous species and, together with their associated habitats (wetlands), make up the area with the greatest diversity in the province (Athor et al., 2004).

3. Southwestern Buenos Aires

Area: 180,400 hectares

Ecoregions covered: Espinal

Municipalities involved: Villarino and Carmen de Patagones.

Demographic and Socio-economic Description: This site covers the municipalities of Villarino with 31,162 inhabitants of which 15,818 are men and 15,344 are women and Carmen de Patagones with 30,446 inhabitants of which 15,179 are men and 15,267 are women. It is an essentially agricultural region. These two municipalities have approximately 1500 farming facilities, according to the national agricultural census of 2008, which represent an amount of 1,730,129 hectares. The area is characterized by an agrarian social structure historically dominated by family units. In terms of agricultural production, the region is an important producer of winter cereals. Wheat is absolutely the main crop in the region. However, this area is essentially suited for livestock and agriculture is carried out on marginal lands, which are highly vulnerable to wind erosion and drought, where the agricultural risk grows from north to south and from east to west. There are clear signs that there is a significant reduction in the number of agricultural activities in the area, by around 5% per year, as a result of the aforementioned vicious circle of degradation and decapitalization that leads to abandonment and rural exodus. An important deterioration of rural life has taken place in these lands, with consequent migratory flows that show an expulsion of the population of the area, where there is a significant number of people that are disappearing, are stagnating or have already disappeared.

Environmental Description / Problems and threats to BD and LD: The zone covers a transition between ecological systems of semi-arid and humid climates including the Espinal ecoregion. In terms of ecological significance, the original vegetation of the “calden” (Prosopis caldenia) district has suffered a considerable loss of its forest area and a strong fragmentation process. On the other hand, the destruction of immense wooded areas that form this region has had a strong environmental impact causing erosion, salinization, loss of structure and soil organic matter, decrease in productivity and rise of water tables, loss of water regulation capacity, clogged lagoons, etc.

The southwestern region of the province of Buenos Aires has its own climatic and edaphic characteristics that restrict primary activities compared to the rest of the province. The process of desertification is the result of the degradation of vegetation cover due to overgrazing, clearing due to the extension of the agricultural frontier, overexploitation of forest resources, uncontrolled fires and agricultural practices that are not appropriate for the region (Abraham et al., 2016).

The southwest region of Buenos Aires is one of the areas most threatened by wind erosion in Argentina. This process, together with the recurrent droughts in recent decades and the poor management of productive practices have generated desertification. The pilot site corresponds to areas of ecological fragility that are defined by their intrinsic vulnerability to the impact of anthropogenic activities. Soil types and their limitations, vegetation cover, water flows, among others, are biophysical characteristics, which help to define ecosystems´ fragility and therefore the threat they represent for the population and the economy when innapropriate interventions take place.

The irrigated lands are dedicated to agricultural production, while the non-irrigated lands have a mixed production system (beef cattle-wheat). The average annual rainfall between the years 1940 and 2014 was 407 mm. In 60% of the years of the specified period, it was lower than the average. Desertification in the area is a consequence of drought and poor management (Abraham et al., 2016).

Figure 1 – Map of target landscapes of Buenos Aires

Southwestern Buenos Aires (Espinal)

Southwestern Buenos Aires (Espinal)

Riverine Forests, Talares and Samborombon Bay (Pampas)

Riverine Forests, Talares and Samborombon Bay (Pampas)

Parana River Delta (Flooded Savanna)

Parana River Delta (Flooded Savanna)

PROVINCE OF JUJUY

1. Hornocal-Valle Grande

Area: 86,974 hectares

Ecoregions covered: Puna, Yungas Forest, High Monte

Demographic and Socio-economic Description: It has an approximate population of 14,255 inhabitants (2010 census), and its most important localities are Humahuaca, Huacalera, Valle Grande, Uquía, San Francisco, Santa Ana, Yacoraite, Caspalá, Valle Colorado, Palca de Aparzo, Coctaca, Pampichuela, Palca de Varas, Cianzo, Aparzo.

The pilot site is inhabited mainly by indigenous communities and the presence of small producers and other key stakeholders to be considered, especially in the Humahuaca area. According to the 2010 census and information available from the Secretariat of Indigenous Peoples, approximately 26 indigenous communities are present, 8 of which have community property deeds, six have been surveyed and another twelve have geo-referenced information. All these stakeholders have different degrees of organization and a great potential for implementing the activities identified for the project. These populations belong mostly to two peoples: the Omaguaca People and the Kolla People. The southern zone is mainly inhabited by Kolla communities, while in the central and northern zone, Omaguaca communities are concentrated. In these communities there is a rural subsistence economy, and the possibility of tourism development between regions with great contrasts, with traditional customs entrenched by its inhabitants. Valle Colorado is the link with the ravine, and the antiquity of this relationship is reflected in the old Inca road that links them. Valle Grande (1,600 masl) is located on a steep slope between 1600 and 1800 masl. on the left bank of the river with the same name, at the foot of the Ovejería hill. San Francisco (1500 masl) is the main town of the community-based tourism network of Jujuy. This small town with around one hundred families offers the necessary basic services for the tourists who access the Yungas. Some of these localities produce sweets and cheeses for sale in informal markets, although some communities also participate in projects to develop certified products.

Environmental Description: From the biophysical point of view, this landscape represents great ecosystemic variability since ecotones and transition zones exist between the different ecoregions throughout the zone, representing immense biological wealth. The existing vegetation is variable depending on the ecoregion, the jungle of the yungas is represented with its altitudinal floors, grasslands, montane forest, forests of queñoas and churquis, cardonal, and scrub steppe of the Puna, among others.

Wetlands such as rivers, lakes, lagoons and vegas are the main providers of ecosystem services. The Grande River is the main river in the area, around which agricultural activity is concentrated.  Agriculture is mainly for subsistence or for local and / or regional sale. Other minor activities are beekeeping, breeding of goats, sheep, camelids and the elaboration of artisanal products (textile products, potters, food preserves, among others).

The most important mining group in the province is in the Eastern zone of the Site, Mina Aguilar, where silver, lead and zinc have been extracted for more than 75 years. At a landscape level, the Site combines historical, cultural, natural and archaeological elements and their relationship with the inhabitants of the territory is truly valuable. It is part of the Quebrada de Humahuaca and the Qapac Ñam, both declared World Heritage Sites, as well as the Laguna de Leandro Provincial Natural Monument and a portion of the Biosphere Reserve of the Yungas. It is important to note that in the vicinity of the area where the Qapac Ñam is located, a vehicular road linking the towns of Santa Ana and Valle Colorado is being constructed. As the site is a tourist resource in potential development, ELUP is necessary in order to avoid land speculation.

2. Susques-Jama-Catua-Olaroz

Area: 32,354 hectares

Ecoregions covered: Puna, High Andes

Demographic and Socio-economic description: Within the framework of the Puna and the High Andes of Jujuy, it involves an approximate population of 2,331 inhabitants (2010 Census), with the main towns being Susques, Catua, Olaroz Chico, Jama and Mina Providencia. In this site, there are 10 communities of the Atacama people: El Toro, Huancar, Portico de los Andes, Olaroz Chico, San Juan de Quillaques, Puesto Sey, Los Manantiales de Pastos Chicos, Catua, Coranzuli, Paso de Jama. 5 of these have deeds, 4 were surveyed and one was georeferenced.

The population of the Puna has some mobility, but has a return circuit, since it goes out in search of work but it returns, both in different periods of the year and at some point in its life cycle. The most important activities, due to their impact on both the level of employment and the generation of income, are mining, livestock, commerce and public administration. Agriculture, tourism and handicraft production, although they still have a low level of development, have an important growth potential. Currently, in the region there is small-scale livestock entrepreneurship for subsistence or eventual informal sale in urban centers. This activity generates the minimum income to cover the basic survival needs of the family group. The agriculture carried out is also for subsistence purposes.

Susques, one of the most important population centers, located at 3,675 m above sea level and 120 kilometers to the west of Purmamarca and 155 kilometers to the east of the border with Chile by the passage of Jama and that makes it an obligatory passage of this interoceanic axis. It is the capital of the Susques Department and headquarters of the Municipal Commission. Susques also has special relevance as a community territory, since about 100 domestic units with their herds of cattle are deployed around the urban nucleus. This collective space is established by the sum of the territories of the different pastoral domestic units from Susques, locally known as “pastoreos” or grazing lands. Most families have livestock, mainly sheep, llamas and goats. During winter they move the cattle to lower and warmer areas, and in the summer they go up to the summits, to the plains. They also work in the salt deposits and make crafts generally for domestic use. Sometimes they sell salt and artisanal fabrics at regional fairs.

In addition to the original communities, there are key stakeholders to be considered in the territory, such as Sales de Jujuy S.A. that drives the Salar de Olaroz project, tour operators in the region and regional technicians of national programs such as IPAF or SAF that have a territorial presence.

Environmental Description: From a biophysical point of view, the Site has very specific characteristics associated with the climatic and topographic components that make living conditions difficult. At heights ranging from 3500 to 6000 masl, relevant ecological processes occur that translate into ecosystem services, allowing the existing population to survive even under extreme conditions.

The existing vegetation is shrubby and squat and the population uses it mainly for firewood. Some species serve as pasture for cattle or for medicinal use. Agriculture and livestock in this area are basically for subsistence.

In an area where water is scarce, wetlands such as rivers, lakes, lagoons, salt flats and plains are the main providers of ecosystem services, since they are the places where the greatest biodiversity and primary production are concentrated, as well as regulating the water system of the region. Historically, they have been affected by livestock use and are currently exposed to two types of possible growing risks that would mainly affect hydrology: climate change and more developed uses of the territory, such as mining and tourism (Izquierdo et.al., 2016).

The dynamics associated with the endorheic basins and the particular geology of the area have allowed the formation of important minerals that are currently being exploited, with prospection expected to continue increasing. Another resource that the zone has is the large number of hours of solar energy, being close to the area of one of the largest solar ventures in Latin America, the Olaroz-Cauchari solar park.

At the landscape level, the site has imposing places associated with geological, geomorphological, volcanic and salt formations, which make this place an unexploited attraction. Currently, there are limitations due to basic infrastructure deficits (road network, communications, sanitary and health services, tourism, etc.), very important for its articulation with the Andean circuit in Chile and regional trade.

Figure 2 – Map of Jujuy target landscapes and ecoregions covered

PROVINCE OF MENDOZA

1. Andean Piedmont of the Metropolitan Area of Mendoza (AMM)

Area: 25,711 hectares

Ecoregions covered: High Andes, Low Monte, High Monte

Main locations: Las Heras- Capital- Godoy Cruz- Luján

Demographic and Socio-economic Description: It comprises an approximate population of 30,000 inhabitants. Because of the territorial characteristics, most of them are individuals who have private property and with whom a dialogue must be established to incorporate environmental notions and ecosystem services in the management of their properties.

Another objective is working with stakeholders in the tourism sector and the areas involved in the Divisadero Largo Reserve. Among the local activities to be considered is the raising of pigs, which, although of small scale, includes some local producers. It is also important to articulate with private actors, such as tour operators or other social organizations.

Environmental Description: This area is a transition unit between the mountainous region and the plain, composed of loose and eroded pleistocene materials, with variants according to the type of mountainous relief they come from. In the aforementioned case, it is the Precordillera foothill, closely related to the Mendoza Metropolitan Area which starts at around 1,500 masl. and it has a variable extension towards the plain that differs between 10 and 20 km.

The dominant plant characteristic of this site is the so-called Larrea shrub steppe. This "jarillal" is formed by Larrea cuneifolia and Larrea divaricata as dominant species and others such as llaullin (Lyciumtenui spinosum), and thyme (Acantholoppia seriphioides), leaf grass (Trichloris crinita) and numerous cacti.

Conservation Efforts: The Divisadero Largo Reserve is located within this pilot site, spanning the foothills of the Sierra de Uspallata between 900 and 1350 meters above sea level, in the departments of Capital and Las Heras. The area covers ​​492 hectares (Law 4.902). It is approximately 10 km in length and 0.9 km in its middle sector.

The vegetation provides a good vegetation cover on an environment of slopes and loose substrate of gravel and sand. Its key function is to avoid water erosion, increase infiltration and reduce the impact of drops during rains. All these processes contribute to reduce the chance of large alluvions that periodically affect the city of Mendoza, located downstream (Manzur et al., 2007).

It is a transition area, called «ecotone», that is to say that plant and animal species of different regions coexist simultaneously, which are typical forms of mountain and plain. This gives the foothill a unique importance in terms of biodiversity conservation (Cali and Güller, 2006). Regarding archaeological studies, fragments of ceramics corresponding to the groups typologically attached to the period 500-1000 years AD (Agrelo Culture) and the period 1300-1600 years AD (Viluco Culture) have been recovered in the area.

Problems and Threats to BD and LD: The most relevant degradation process of this site is the vegetation cover impoverishment. In this sense, it is worth mentioning the great pressure to which the foothills of the Precordillera are subject, especially due to the unplanned urban expansion of the Gran Mendoza.

In this site, the expansion of agriculture and urbanization in the foothills affect fragile ecosystems and biological corridors with the consequent increase in alluvial fan risk. Among the main causes are the following: a) The urbanization of large sectors of Piedmont Front Range in the area of ​​influence of the metropolitan area, due to the environmental values ​​that it presents at a climatic level; b) The development of productive and / or housing units without considering Piedmont environmental and hydrological functions and control and mitigation of its effects; c) Government regulation and control instruments are inadequate to address the problem; and d) The expansion of the productive areas towards the Cordillera Frontal sector in the Uco Valley and the right margin of the Mendoza River due to the availability of water and climate considered suitable for wine production.

This site is the object of anthropic intervention processes on the natural environment which increasingly and steadily affect the biodiversity, soil, and the landscape: a) Public policy directed or centralized in the oasis for socio-productive development without considering systemic strategies in the entire territory; b) Loss and degradation of heritage due to the abusive and unsustainable use of resources (i.e., firewood), habitat reduction and competition with exotic species; c) Urban development towards the Precordillera foothill in the Gran Mendoza area of ​​influence and productive development towards the Cordillera Frontal foothill; d) Deficiencies in knowledge, planning, control and monitoring of the different uses of natural resources; e) Inadequate cultural patterns of the population, particularly hunting, high consumption of firewood, waste management, burning, etc., f) productive activities that use firewood as a primary input, such as for brickyards; g) Extensive areas affected by extractive activities such as hydrocarbons, aggregates, etc. h) Absence of biological corridors under effective conservation strategies; i) Detrimental processes on rainfed vegetation, such as overgrazing, associated on the one hand with the low carrying capacity of the systems and on the other hand with inadequate livestock management; j) Destruction of vegas and mallines in mountainous areas through overgrazing, infrastructure, use of peat for mining; k) Institutional weakness linked to the integral management process of protected natural areas, without management tools, on the one hand budget and on the other the development of co-management models with the local inhabitants for effective management, setting the establishment of models of sustainable use of natural resources, favoring degradation; l) protected natural areas are not always designated in areas where protection is most critical; m) Provincial public policy that has not prioritized landscape valuation as an important and essential aspect to preserve the quality of life and economic development; n) Development of public works without adequate environmental assessment and management measures; ñ) Extraction of building materials in inappropriate sectors from the landscape point of view; o) Scarce infrastructure and strategies of public use of natural sites according to their category; p) Deterioration of natural and cultural systems such as hydrological systems, wetlands, native or implanted vegetation, heritage areas, q) Lack of building criteria according to the sitesʹ socio-cultural and environmental characteristics; r) Insufficient management of solid waste, effluents.

The analysis of trends shows a significant advance in the clearing of areas, especially in the foothill areas, increasing the loss of biodiversity, and a significant decrease in the system's hydrological services and increasing downstream alluvial impact.

Processes of ELUP on the Site: Regarding the legal framework affecting this site, two basic laws that legislate on the foothills of the AMM can be mentioned: Law 4886/83 that demarcates, zones and allocates uses of the sector and Law 5804 / 91 (with its regulatory decree No. 1077/95), which declares it of public interest and utility, establishes land use or the creation of natural reserves bounded by an area located in the west of Gran Mendoza.

2. Piedmont of the Uco Valley

Area: 28,525 hectares

Ecoregions covered: High Andes, Low Monte, Patagonian Steppe

Main locations: Tunuyán, San Carlos, Tupungato

Demographic and Socio-economic Description: The population density is low in this territory, which is why it is known as the "field without people". In this pilot site, we find the presence of large agricultural ventures, and especially winegrowing, with the use of ground and surface water. Likewise, oil and mining activities are carried out, as well as extensive livestock farming, as in other foothill areas of the province.

State stakeholders at the provincial and municipal levels interact mainly with wine entrepreneurs, such as the Civil Association for the Wine Development of Valle de Uco or Bodegas Argentinas A.C. which will become relevant stakeholders for the work that will be carried out in the area. INTA, Irrigation or the Municipalities are the institutions that interact the most with these private stakeholders. The producers in this territory, generally with a business mindset, are open to technological innovation and integration for certain purposes. The need to organize themselves is not as critical as in the rest of the oasis, essentially due to scale and vertical integration issues. This is also associated with these producers´ greater negotiating power with the other stakeholders of the respective chains, and likewise, as a rule, they can easily access private financing. Only some producers are located in the territory and the population's roots in rural areas are very scarce ("fields without people"). Therefore, the difficulty to mobilize a labour force is critical in this territory, and we try to solve it by bringing people in from the outside, from the most important urban centers of the oasis. The agricultural activity in the Uco High Valley is aimed both at the international market and to the local market. There is a growing positive perception of this region, nationally and internationally, largely promoted by changes and the internationalization of the wine industry. The rural tourism here is a progressive development activity, but not locally based but mobilized mainly by companies located outside the territory.

Environmental Description: This area is a transition unit between the mountainous region and the plain, composed of loose and eroded pleistocene materials, with variants according to the type of mountainous relief they come from. In the aforementioned case, it is the Cordillera Frontal foothills, which starts around 2,000 masl, extending up to approximately 50 km to the east in the so-called Valle de Uco area.

The dominant plant characteristic of this site is the so-called shrub steppe of Larrea. This "jarillal" is formed by Larrea cuneifolia and Larrea divaricata as dominant species and others as llaullin (Lyciumtenui spinosum), and thyme (Acantholoppia seriphioides), leaf grass (Trichloris crinita) and numerous cacti.

In the foothill plains of the analyzed site, the erosion factor is rain and it is enhanced by the slope and poor cohesion of surface materials. The rainfall regime, concentrated in very short periods and small sectors of the basins, causes strong water erosion.

Conservation efforts: Within the aforementioned site, the Manzano Histórico Natural and Cultural Reserve, and the Manzano Histórico locality can be found, where recreational activities, fish production, gastronomy, tourism, etc. take place.

Problems and Threats to the BD and LD: In this pilot site, we find the presence of large agricultural ventures, and especially winegrowing, with the use of ground and surface water. Likewise, oil and mining activities are carried out, as well as extensive livestock farming, as in other foothill areas of the province.

The enlargement of agrarian borders and urbanization in the foothills affect fragile ecosystems and biological corridors with the consequent alluvial risk increment. Among the main causes are the following: a) The urbanization of large sectors of Front Range Piedmont in the area of ​​influence of the metropolitan area, due to the environmental values ​​that it presents at a climatic level; b) The development of productive and / or housing units without considering Piedmontʹs environmental and hydrological functions and control and mitigation of its effects; c) government regulation and control instruments are inadequate to address the problem; d) The expansion of the productive areas towards the Cordillera Frontal sector in the Uco Valley and the right margin of the Mendoza River due to the availability of water and climate considered suitable for wine production.

The analysis of trends shows  a significant advance in the clearing of areas, especially in foothill areas, increasing the loss of biodiversity, and a significant decrease in the system's hydrological services and increasing downstream alluvial impact.

3.  Llancanelo Lagoon –Malargüe River Basin

Area: 42,884 hectares

Ecoregions covered: High Andes, Patagonian Steppe

Demographic and Socio-economic Description: According to the 2010 census, the population is approximately 27660 people, 14,109 men and 13,551 women (2010 census at departmental level). This site includes the implementation of activities linked to 25 Mapuche communities inhabiting the territory. There is no available indigenous population data by department in the national population census. The interviews conducted with community leaders show 150 indigenous families and approximately 600 people who are recognized in these communities. Since this information was obtained from interviews and cannot be contrasted with census data, information pertinent to the communities must be collected when staring activities in the pilot sites, for this and other pilot sites cases. In the interviews it was also reported that most of the communities do not have individual or community deeds, although this has not been an obstacle for their participation in the different dialogue processes and actions related to territorial management.

Its economic activity is focused on subsistence, working in livestock, breeding of goats, sheep, horses and cattle. The traditional economic activity of the department is the extensive breeding of goats. Malargüe is famous for its goat meat, which is sold to other departments and other provinces. Mining activity had its boom period in the 40s until the 70s. Beginning in the 70s the boom in oil activity began, which, although it has had important ups and downs, today still represents the main income of the department. Malargüe is the main oil producer in the province. Above all, since the 90s, tourism has become one of the most dynamic activities.

Environmental Description: The salty lagoon of Llancanelo is the base level of a closed system or endorheic basin, whose main surface supply is the Malargüe river, which has developed a wide alluvial fan and flows into estuaries and marshes. The Llancanelo Basin, the oasis and the city of Malargüe are part of the described natural scenario located 450 km south of the City of Mendoza.

The oasis of Malargüe is the smallest in the province, shaped by the Malargüe river, with an annual spill of 305 hm3 and without any storage reservoir. At the exit of the mountain range, the Malargüe diversion dam is located, from which a 90 km long network of channels is born, which is not waterproofed. With the waters from this river and the extracted ones from the Malargüe underground reservoir through 800 wells, the city of Malargüe and the adjacent cultivated area are supplied, characterized by potato seed crops. Groundwater is exploited in order to supplement surface deliveries or to supply drinking water, industrial and agricultural water. The Malargüe underground reservoir covers an area of ​​7,000 km2 and stores a volume of water of 70,000 hm3, which highlights its importance as a safe source of water supply (Torres et al., 2008).

Conservation efforts: Llancanelo has been declared a "Natural Protected Area" by Law 7824 of 2007, and it is a Ramsar Site. Llancanelo is a mirror of water of very small depth, with approximately 88,000 ha, which is found at approximately 1,330 masl. and it feeds on melting waters coming from the mountain range. There is a series of volcanoes next the lagoon, among which the Trapal, Coral and Carapacho stand out.

Regarding the biodiversity of species, the Llancanelo Wetland is located within the Patagonian ecoregion and protects more than 150 species of birds (residents and migrants). The population of flamingos is considered the most important on the planet and they nest in this place, as well as several species of ducks, such as the coscoroba swan and the black-necked swan. Other aquatic species also inhabit this area, such as the coypu and the medium rodent. In the coastal environment that surrounds the lagoon you can see vizcachas, cuy, snakes, red and gray foxes, rheas, among others. In the areas of low dunes and salt flats an endemic rodent in danger of extinction lives: the vizcacha rat of the salt flats, which feeds on halophytic plants. Regarding flora, there is a predominance of tall, open bushes, together with low-lying herbaceous steppes. Among the halophytic vegetation the stained glass, the jume, the vinagrilla and salty pastures stand out where there is a higher concentration of salts, while on the surface of the low-lying dunes, zampas, llaullines and chirriaderas emerge. Underwater and underwater plants grow in the most humid sectors, such as reeds, cortaderas and totoras.

Problems and Threats to BD and LD: The decrease in the flow of the Malargüe River due to overexploitation for agricultural purposes in the upper river sections affects the water supply for  “puesteros” (traditional ranchers and pastoralists who live in the plains and range up in the Andes) and Mapuche indigenous self-determined communities (around 60 families) and the natural regime of the lagoon. These are dedicated to the breeding of goats for self-supply and marketing, and to a lesser extent to sale or services for tourism.

This site suffers from the impact of anthropic intervention processes on the natural environment which increasingly and steadily affect the biodiversity, soil, and the landscape: a) Public policy directed or centralized in the oasis for socio-productive development without considering systemic strategies in the entire territory; b) Loss and degradation of heritage due to the abusive and unsustainable use of resources (i.e., firewood), habitat reduction and competition with exotic species; c) Urban development towards the Precordillera foothill in the Gran Mendoza area of ​​influence and productive development towards the Cordillera Frontal foothill; d) Deficiencies in knowledge, planning, control and monitoring of the different uses of natural resources; e) Inadequate cultural patterns of the population, particularly hunting, high consumption of firewood, waste management, burning, etc., f) productive activities that use firewood as a primary input, such as for brickyards; g) Extensive areas affected by extractive activities such as hydrocarbons, aggregates, etc. h) Absence of biological corridors under effective conservation strategies; i) Detrimental processes on rainfed vegetation, such as overgrazing, associated on the one hand with the low carrying capacity of the systems and on the other hand with inadequate livestock management; j) Destruction of vegas and mallines in mountainous areas through overgrazing, infrastructure, use of peat for mining; k) Institutional weaknesses linked to the integral management process of the protected natural areas, without management tools. On the one hand budget and on the other the development of co-management models with the local inhabitants for effective management, limit the establishment of models of sustainable use of natural resources, favoring degradation; l) protected natural areas are not always designated in areas where protection is most critical m) Provincial public policy that has not prioritized landscape valuation as an important and essential aspect to preserve the quality of life and economic development; n) Development of public works without adequate environmental assessment and management measures; ñ) Extraction of building materials in inappropriate sectors from the landscape point of view; o) Scarce infrastructure and strategies of public use of natural sites according to their category; p) Deterioration of natural and cultural systems such as hydrological systems, wetlands, native or implanted vegetation, heritage areas, q) Lack of building criteria according to the sitesʹ socio-cultural and environmental characteristics; r) Insufficient management of solid waste, effluents.

In terms of trends, the province is becoming impoverished in biodiversity which is progressively decreasing its wealth, productivity and resilience. The soils of non-irrigated areas present severe degradation processes that significantly impact on ecosystem and productive processes. The natural landscape, especially in sectors of tourist corridors is partially deteriorated in one or more of its components which affects its functionality and valuation.

4. Northern Oasis – Green Belt

Area: 63,650 hectares

Ecoregions covered:  Low Monte

Main locations: Guaymallén, Lavalle (part), Maipú

Demographic and Socio-economic Description: The territory is occupied by family and commercial vegetable gardens that surround the cities and where vegetables are produced to supply the urban population. Approximately 25,000 people live on the site. This space is characterized as producing most of the vegetables as fresh and industrialized agro food consumed in Mendoza and in a relevant number of Argentine provinces and according to the opportunities of other countries, contributing to food security.

The predominant land tenure regime in the green belt is private property in 80% of cases, with leasing or sharecropping following in importance with 15%. In terms of the producers, the participation of the Bolivian community and its descendants is notorious in this horticultural activity, with social and cultural characteristics different from the traditional wine growing, fruit and horticultural producers of Creole origin and / or descendants of Spaniards and Italians. In general, they are farmers with high productive specialization, little diversification, with a very low or zero level of organization both horizontally and vertically and with little development of more efficient marketing methods.

The labor force of this territory is clearly similar to most other rural territories of the province, formed on the one hand by an aging population, which leads to an extreme situation in some districts, in the form of an inverted pyramid. On the other hand, there is an exodus of young people with a higher level of education to the nearby population centers in search of greater job opportunities, remaining in the green belt those young people with incomplete primary or secondary education. This leads to a complicated scenario for the agricultural sector, since the producers lack sufficient manpower to carry out activities.

Environmental Description: It is a large area in the shape of a croissant surrounding the urban conglomerate called "Gran Mendoza" to the east, reaching the urban peripheries of the cities of Maipú, Guaymallén and Lavalle. The main contributions of this site to the region are: its optimal agroecological soil, water or climate conditions; social, cultural and technological capital, diversity of horticultural species, as well as fruits, olive trees and grapes; the possibility of consuming food without excessive transfer times; infrastructure of roads, irrigation network and electric power that allow this production; input suppliers; among others.

Problems and Threats to the BD and LD: The site is a segment of the North Oasis of Mendoza; it includes most of the agricultural area of ​​the department of Guaymallén and a fraction of the departments of Lavalle and Maipú. It constitutes a quite heterogeneous agroecosystem characterized by the presence - although not exclusively - of horticultural farms that coexist with vineyards, olive groves and fruit trees. The proximity to the Mendoza Metropolitan Area, a regional metropolis with more than one million inhabitants, imposes an urbanization gradient on this area that threatens the sustainability of the productive system. Given the complexity and diversity of the problem and its challenges, the urban advance on agricultural land will be addressed as a central theme.

Among the main problems of the territory the following can be listed: disorganized advance of urban land over rural land; consequent loss of fertile land suitable for agricultural uses; costly investments in the generation of new crop lands; increasing pollution of the rural and peri-urban environment; contamination of irrigation and drainage channels by residential and industrial waste; low agricultural productivity with little adoption of sustainable productive practices (BPA); low level of agricultural employment; high degree of economic informality; little added value of horticultural production; large fluctuations and gaps between the prices received per producer and those paid by consumers; rural population with producers of a high average age; exodus of qualified rural youth from rural areas to cities in search of job opportunities; poor horizontal organization; fragmentation of the landscape and segmentation of the social fabric; among others.

The selected area shows diverse environmental problems: a) Irrational use of agrochemicals, both phytopharmaceuticals and fertilizers. This practice leads to environmental consequences, such as the contamination of the soil, water resources, air, and biome alteration; b) Presence of degraded soils and increase of the edaphic salinization process; c) Contamination of the surface irrigation network with urban solid waste; d) Increasing presence of plastic waste from protected crops; e) Increasing presence of open air dumps; f) Urban advance on agricultural lands in various modalities. The irreversible and direct consequences of this process include the loss of productive capacity of the agroecosystem as well as other ecosystem services in the landscape, the obsolescence of agricultural infrastructure such as the irrigation distribution network, alterations in the biome and rural-urban conflicts.

Figure 3 – Map of Mendoza target landscapes and ecoregions covered

Argentina spans the latitudes 21º 46' SL up to 55º 03' SL; is the 8th country in land area (2,791,810 km2) and 4th in the Americas. Its marine territory covers 4,8 million km2, an additional 1.7 million km2 of continental shelf was recently recognized under UN Convention on the Law of the Sea.

Spanish equivalents: Altos Andes; Puna; Monte de Sierras y Bolsones, Selva de las Yungas; Chaco Seco; Chaco Húmedo; Selva Paranaense Esteros del Iberá; Campos y Malezales; Valle y Delta del Paraná; Espinal; Pampas; Monte de Llanuras y Mesetas; Estepa Patagónica; Bosques Patagónicos; Islas del Atlántico Sur, Mar Argentino y la Antártida

Zuloaga et al. Flora Vascular de la Republica Argentina. 2015.

Ojeda et al. Libro Rojo de Mamiferos Amenazados de la Argentina. 2012

Lopez Lanues et al. Categorización de Aves de la Argentina. 2008

Vaira et al. Categorización del Estado de Conservación de anfibios de la República Argentina. 2012

Abadala et al. Categorización de los Reptiles. 2012

Giraudo et al. Categorización del Estado de las Serpientes de la Republica Argentina. 2012

Prado et al. Categorización del Estado de las Tortugas de la Republica Argentina. 2012

Claps et al. Biodiversidad de Artrópodos Argentinos 2008

INDEC Population Census. 2010

SGAyDS.2015

IBAs include globally threatened bird populations (red list species), restricted-range species (Endemic Bird Areas EBAs), species confined to South America and congregatory bird species. 99% of Argentina’s IBAs are important for globally threatened species, 70% for endemic species in EBAs, 81% South America and 8% congregatory bird species. All the most relevant bird species for conservation purposes pertain to one or two IBAs.

According to Ravelo, Andres C. et al. 2008. CDE/WOCAT, FAO/LADA, ISRIC the degrees of degradation are defined as: a) light: there are some indications of degradation but the process is still in an initial stage; it can be easily halted and the damage may be repaired with a minor effort; b) moderate: degradation is obvious but control and complete rehabilitation of the land is still possible with considerable effort; c) strong: evident signs of degradation; changes in the properties of the land are significant and difficult to restore within a reasonable time limit; and d) extreme: degradation is beyond restoration.

Project Identification Form

This Bill was passed February 2016 by the Senate; it is waiting enactment by the Lower House; wetlands account for almost 21.5% of the country.

The PIF had identified a fourth province: San Luis. During the PPG phase, the Province of San Luis was invited to participate in the Project Formulation Workshop in order to be a part of the PPG phase, but the Ministry of Environment of the Province did not assist nor answer emails and phone calls.

Endorheic basins are land locked drainage networks where water does not drain into large water bodies, such as rivers connected to oceans. Considering natural water cycle processes only, endorheic basins and lakes experience water losses through water percolation underground and evapotranspiration. The level of evapotranspiration and plant transpiration is generally higher than precipitation in arid and semi-arid areas, where most of these basins and lakes are located. They can be highly sensitive to variations in climate and adverse anthropogenic activities, such as overexploitation of water resources.

The Sustainable Livelihoods Framework measures progress in five capitals: social capital, productive capital, human capital, physical capital and natural capital. The process is participatory and the methodology of capital analysis assigns point values to each capital ranging typically between 0 and 20 and possible results are: unsustainable (0-4), limited sustainability (4.0-8), sustainable (8.0-12), progressively sustainable (12-16) and abundant (16-20). http://www.latinamerica.undp.org/content/dam/rblac/docs/Research%20and%20Publications/Poverty%20Reduction/UNDP_RBLAC_Livelihoods%20Guidance%20Note_EN-210July2017.pdf

The ONDTyD is a national system to monitor and evaluate land degradation at different scales (national, regional and pilot sites) based on an integrated, interdisciplinary and participatory approach. It is supported by a network of institutions that provide data and knowledge and are at the same time users of the information; and comprises a Board of Directors in charge of management and coordination, a Technical/Scientific Advisory Committee to support functioning and to provide data, and Pilot Sites to generate local field data that may be extrapolated at regional level. Information is made available online through interactive maps, publications and geospatial data. http://www.desertificacion.gob.ar.

Federal: IDE Ambiente of the MAyDS http://mapas.ambiente.gob.ar, GeoINTA of INTA http://visor.geointa.inta.gob.ar, Biodiversity Information System of the National Parks Administration https://sib.gob.ar/#!/, Data Argentina of the Ministry of Modernization http://datos.gob.ar. Jujuy: Provincial Directorate for Environment and Land Use Planning http://www.ambientejujuy.gob.ar, IDE Jujuy http://idej.jujuy.gob.ar/visualizadores/, Provincial Directorate of Statistics and Census http://www.dipec.jujuy.gov.ar. Mendoza: IDE Mendoza http://www.idem.mendoza.gov.ar,Territorial and Environmental Information System (SIAT) http://www.siat.mendoza.gov.ar, IDE Irrigation http://ide.irrigacion.gov.ar. Buenos Aires: Territorial and Environmental Analysis System (SATA) http://sata.opds.gba.gov.ar/institucional.php, UrBASIG of the Ministry of Public Works http://www.urbasig.minfra.gba.gov.ar/urbasig/, GIS-ADA of the Water Authority of the Province of Buenos Aires http://www.ada.gba.gov.ar.

IDERA is a national and federal level geospatial information community with the objective of disseminating publication of data, products and services to facilitate information produced by the State and different stakeholders and to support decision making in the different activities of the public, private, academic, non-governmental and civil society sectors.  Data, products and services produced by the different institutions linked to the IDERA platform are published in the Internet under defined standards and norms thus ensuring their inter-operability and use, as well as the property of the information by the institutions that publish and update them. http://www.idera.gob.ar

ECOSER: “Collaborative protocol for assessing and mapping ecosystem services and socio-ecological vulnerability for land use planning is a tool developed by INTA to support decision making on land uses. It includes the bio-physical evaluation of ecosystem services but not their economic valuation.  The protocol comprises a number of procedures to assess and map ecosystem services and estimate the socio-ecological vulnerability in the face of loss of such services.

TSA is an analytical approach developed by UNDP that captures and presents the value of ecosystem services within decision making, to help make the business case for sustainable policy and investment choices. The product of a TSA is a balanced presentation of evidence for a decision maker that weighs up the pros and cons of continuing with business as usual (BAU) or following a sustainable development path in which ecosystems are more effectively managed.

INTA has used multi-criteria analysis and GIS to evaluate water resources. The methodology consisted of classifying landscapes according to criteria related to the buffering capacity of water. It is a biophysical approach and the selection and weight of criteria was based on expert opinion. The biophysical approach allows for decision making on the ground and is the basis to undertake an economic analysis.

The SGAyDS does not have a species inventory but issues an annual publication on the conservation status of certain taxonomic groups: birds, mammals and herpetofauna. Data is updated, but there is no field collection. Preparation of the first red list of plants is currently underway. IUCN criteria will be used to define conservation status of BD categories. Activities are undertaken with the participation of NGOs relevant to the taxonomic group under study.

The scheme consists of a fund to pay for water services for conservation of the Ramon Stream. The fund will be initiated with seed money from public and private institutions and then will receive contributions form users of drinking water services through their water bills. Suppliers of ES upstream will be the beneficiaries receiving payments for avoiding agricultural and livestock practices that may damage the stream.

A native forest conservation status indicator, guides for preparing management plans and a guide for best management practices were developed and included in forest management plans to define payments. The conservation status indicator is monitored annually and must be increased or at least maintained for the landowner to receive payments. Payments are initially directed to forest areas with lower conservation status to promote their improvement.

The scheme consists of tax deductions for implementation of best practices in agricultural and mixed agricultural-livestock systems to mitigate and reduce soil erosion, loss of water, and degradation of natural resources.

The law states that the jurisdictions will apply 70% of the financial resources from the Native Forest Fund to compensate landowners for conserving native forests according to the conservation categories established in the law.  The compensation consists of a non-reimbursable amount to be paid per hectare per year. To receive payments, landowners must have native forest management and conservation plans approved by the application authority of each jurisdiction.  Law Nº 27431 creates a Fiduciary Fund for Environmental Protection of Native Forests (FOBOSQUE) administered by the SGAyDS.

Environment General Law Nº25 675, Native Forest Law Nº26 331, Glacier Law Nº 26 639, National Parks Law Nº 22 351; Wildlife Conservation Law Nº 22 421; Law Nº 24 375 ratifying the Convention on Biological Diversity; Law Nº 23 919 ratifying the RAMSAR Convention; Law Nº 24 701 ratifying the United Nations Convention to Combat Desertification; Environmental Management of Water Law Nº 25 688; and Law Nº 27 037 National System of Marine Protected Areas; Law Nº 22211 Agricultural Promotion for Low Productivity Rural Lands; Law Nº 26737 Rural Lands; Law Nº 22428 Promotion of Soil Conservation; Law Nº20247 Seeds and Phyto-genetic Creations; National Tourism Law Nº25997; Law Nº 1919 Mining Code; Decree Nº420/2010 Establishment of the Federal Planning and Land Use Planning Council; Law Nº 25916 Domestic Solid Waste Management; Law Nº 27279 of Minimum Standards for Environmental Protection for Management of Empty Phytosanitary Containers; and Law Nº 26815 establishing the Federal Fire Management System.

Argentina’s Constitution states that natural resources are owned by the provinces. The National Government is in charge of enacting the laws on “minimum standards” for protecting the environment, its ecosystems, biodiversity and all other natural resources; these establish the common principles and minimum levels provinces must have in place for protecting the environment; provincial governments shall enact laws to supplement national provisions. Within this framework, provinces are charged with implementing ELUP but the national government can establish minimum standards for ELUP and its implementation.

Public funding programs: Native Forest Law Fund; Forest Plantations Investment Fund; Sheep Recovery Fund; Inclusive Rural Development Program (PRODERI); Rural Area Development Program (PRODEAR); Argentine Technology Fund (FONTAR); Social Actors Demand Council Program (PROCODAS); Seed Fund; Tourism Fund; Provincial Agricultural Services Program (PROSAP). Private sector financial institutions: Banco Galicia; Argentine National Bank.

The Fund provides fiscal benefits (national, provincial and municipal fiscal stability, reserve valuation and early amortization) and non-reimbursable grants for afforestation, enrichment of native forests and forest management.

Under the law, non-reimbursable funds are granted to family producers who do not have conditions to access and return loans, to finance projects addressing recovery of sheep production.

Provides reimbursable and/or non-reimbursable funding for: preparing investment projects and baseline studies; implementing plans or projects; technical assistance; training costs; grants to cover interest rates of bank loans; undertake market studies and market access activities; socio-organizational development.

Banco Galicia has signed agreements with the International Financial Corporation to grant credits with favorable conditions to finance projects in the fields of energy efficiency, renewable energy (solar and biomass), water use efficiency, forest conservation. The bank also has credit lines to finance sustainable projects with high social and environmental impact. It grants annual prizes to research initiatives addressing environmental conservation and sustainable development.

Strategic Environmental Assessment (SEA) is defined as the process by which environmental considerations are required to be fully integrated into the preparation of plans and programs prior to their final adoption. The objectives of SEA are to provide for a high level of protection of the environment and to promote sustainable development.  During the PPG the SGAyDS decided that for ELUP it would be more appropriate to develop SEA instruments instead of sector-based EIAs as foreseen in the PIF. Given its strategic nature it is better adapted for ELUP as a planning instrument.

Federal level forum comprising the environmental authorities of the provinces. Key objectives are: to coordinate environmental strategies and programs at national and regional levels through promoting agreements among the relevant government sectors involved in resolving environmental problems; to formulate sustainable use policies to favor conservation of environmental resources; and promoting planning of economic growth and development with social equality and in harmony with the environment.

Inter-institutional coordination committee to promote consensus building on biodiversity related policies and action plans. It comprises representatives of national and provincial governments, civil society, representatives of indigenous peoples and scientific organizations.

Federal forum coordinated by the Ministry of Interior, Public Works and Housing for sectoral planning, coordinating and harmonizing land use planning and zoning policies.

Federal forum comprising representatives of the Environment Committees of the provincial congresses and the City of Buenos Aires to promote common legislative policies in regard to the environment from a federal perspective; updating and adapting provincial legislation to international environmental treaties ratified by Argentina.

The Government of Argentina established in 2016 a National Climate Change Cabinet comprised by 12 ministries which meets regularly to design public policies that include strategies to mitigate greenhouse gas emissions and to provide coordinated responses to the impacts of climate change.  The workplans and results are validated in roundtables with civil society representatives. The roundtables are convened by the Secretariat of Environment and Sustainable Development.

Law Nº 11723 has the objective of protecting, conserving, improving and restoring the natural resources and the environment in general of the Province of Buenos Aires to preserve life in its broadest sense, ensuring environmental quality and biological diversity for present and future generations. Articles 7 and 8 refer to planning and land use instruments. Article 7 establishes the general conditions to consider when making use of natural resources, locating productive activities and/or human settlements: nature and characteristics of each biome; aptitude of each zone or region according to its resources, population distribution and geo-economic characteristics; and existing alterations of biomes due to anthropogenic activities or natural phenomena. Article 8 establishes a list of activities to which the previous article applies: public works; construction and operation of industrial, commercial or services plants; land use permits for agricultural, forest and livestock production; financing of the previous activities; granting concessions or permits for use of water resources and wildlife; establishment of new settlements; government programs related to infrastructure, urban equipment and housing.

An observatory is a network of scientific and technical institutions/experts that collect, analyze and generate information to support decision making by different stakeholders related to development of the territory as well as making adjustments to correct undesired trends and/or dynamics.

In alignment with the Federal Native Forest Law, this provincial land use plan for forests has the objective of providing incentives for conservation and sustainable management of native forests and the ecosystem services they provide. Under the plan, landowners must prepare land use plans as a pre-requisite for presenting land use change plans, sustainable management plans or conservation plans in accordance with the zoning categories established for native forests.

Law Nº 5063 has the overarching goal of guaranteeing protection, preservation, conservation, defense and improvement of the environment, promoting a sustainable development policy that is compatible with such ends, and ensuring an optimum quality of life for the present and future generations in the Province of Jujuy. Article 51 states that the province must establish financial mechanisms for environmentally friendly investments. For this purpose, it establishes the Provincial Environmental Fund.

The objectives of Law Nº6080 are: to promote ecotourism; to promote sustainable development initiatives in those protected areas where such initiatives may be undertaken to improve the livelihoods of their historical dwellers; and develop a financing strategy for the protected area system. The law establishes the Provincial Protected Area Fund to provide grants or benefits to landowners located inside protected areas.

Law Nº5954 establishes the Urban Solid Waste Management Plan; its objectives being among others to implement the Urban Solid Waste Management System; promote waste segregation at origin, reuse and recycling; establish a collection, treatment and final disposal system; procure equipment and human resources; raise awareness on solid waste issues; incorporate environmentally friendly technologies and processes; and eliminate dumps.

Law Nº8051 establishes land use planning as the political and administrative procedure of the provincial government and municipalities, and as the basic instrument for economic, social and environmental development pursuing balanced and efficient ways to occupy the territory. It establishes several instruments, among them the provincial land use plan, municipal land use plans and land use plans for special areas.

Law Nº 5048 declares of public interest and use an area of land located to the West of the Mendoza Metropolitan Area and subject to expropriation, adjustment of land use or establishment of natural reserves.

The CIOUT´s objective is to elaborate regulatory, procedural and technological instruments to optimize and improve the Provincial Land Use Planning System and coordination with municipalities. Members include OPDS, INTA, Ministry of Agro-industry, Buenos Aires Revenue Agency, Water Authority, Ministry of Government, Ministry of Infrastructure and Provincial Directorate for Risk Management and Emergencies. http://www.gob.gba.gov.ar/legislacion/legislacion/08-1496.html.

The CPOT is a consultative and advisory body on land use planning. It is convened by the Environment Secretariat of Mendoza and includes representatives of provincial and municipal institutions and CSOs. Its objectives are to provide recommendations and proposals for the territorial organization of the province; to issue opinions and statements on the planning procedures established in the provincial Land Use Planning and Land Use Law. http://www.ambiente.mendoza.gov.ar/organismos/cpot/mision-cpot/.

The unit has the role of coordinating and implementing actions to forward research, conservation and preservation, community participation and sustainable development of archaeological roads and sites and communities as part of the Qhapac Ñam (Inca Road) Andean Road System.

The Provincial Native Forest Law was issued in 2016 and establishes the measures for conservation and sustainable use of native forests in alignment with the federal Native Forest Law. This allows for allocation and transfer of federal funds from the Native Forest Law to the province. OPDS and the Ministry of Agro-industry of Buenos Aires (MAIBA) are the application authorities of the provincial law.  An agreement between the OPDS and MAIBA establishing their respective roles and responsibilities must be signed as a pre-requisite for the province to start receiving funds.

The Seed Funds have the objective of providing technical and financial assistance to individuals who want to start projects or strengthen ongoing projects with innovative components that mainstream gender equality and have the potential to generate economic and social impact at local, national or regional level. Modalities are technical cooperation (incubators) and financial assistance (soft credits with 0% interest rates).

ArgenINTA provides credits at low interest rates with own funds and third party funds; toolkits for associations and individuals and has experience in designing financial instruments and revolving funds for family farmers. It implements several programs: Sustainable Territorial Innovation (INTERRIS), Productive Credits and Small Contributions to Projects (PROFEDER) and ProHuerta.

The Ministry of Tourism implements several funding options: a) Emprender Turismo with the objective of promoting entrepreneurial culture and converting ideas into sustainable tourism enterprises and employment generation; b) Fondetur provides resources through calls for proposals to projects that strengthen development of tourism within the framework of national programs; and c) international cooperation projects.

BAPRO has a business unit for micro and small producers granting them credits with minimum requirements. https://www.provinciamicrocreditos.com/

BNA has microcredit lines for micro and small producers.

The Provincial Emergency Law Nº10390 establishes a number of measures in support of producers affected by natural disasters and during the declaration of emergency, among them: deferral of payments and/or renegotiation of credits; special credits for recovery; temporary suspension of collection judgements; renewal of credit return schedules; tax deferrals; total or partial tax exemptions; allocation of funds for public works in the affected areas; supply of seeds and inputs for agricultural operations.

Prospective is a systematic and participatory process to collect knowledge related to the future and construct medium to long term visions with the objective of guiding the decisions that need to be taken today and mobilizing actions to address the desired future.  The methodology provides information on facts, ideas and trends to adjust the needs of society and economic activities to the environmental characteristics of the territory; it provides guidance on “what”, “what for” and “how” to plan the territory following the desired scenario.

Law Nº8999/2017 approves the Provincial Land Use Plan, which has the overarching goal of setting the foundations for a sustainable development model of the province, with three of its specific objectives being: a) to reduce environmental degradation and natural and anthropogenic risks, promote adaptation to climate change, and conserve BD and the natural and cultural heritage; b) promote sustainable production and trade; and c) promote integrated water resources management. The plan calls for developing regulations for economic instruments, namely: a) property tax; b) minimum sustainable economic unit; c) capital gain; d) promotion; and e) compensation for ES.

Law Nº6045 establishes the provincial Protected Areas System with the objective of conserving and promoting the province´s natural heritage in a manner compatible with production and tourism in accordance with sustainable development standards and integrated into the Provincial Land Use Planning Plan. The law establishes a Permanent Protected Areas Fund which may be funded through several sources, e.g., provincial budget, fines, donations, fees.

The provincial government currently does not request the private sector to present an EIA since there are no soil management criteria to undertake an assessment.

Under the law, non-reimbursable funds are granted to family producers who do not have conditions to access and return loans, to finance projects addressing recovery of sheep production.

PRODECCA benefits farmer and indigenous families whose main income relies on goat production. Objectives include promoting inclusion of family farmers, indigenous communities, women and youth; improving integration of goat producers in value chains; and promoting and facilitating dialogue between productive stakeholders.

A participatory land use planning exercise was undertaken by INTA in the Santa Rita stream basin in the Yungas ecoregion that comprised land zoning according to potentialities, limitations and characteristics, and the population´s development objectives and expectations. Participatory planning was undertaken through local roundtables with a high level of citizen participation.

Law Nº5428 objectives are: a) to promote, organize and develop tourism activities and services; b) promote organized and sustainable growth of tourism; c) promote and stimulate private sector initiatives in developing tourism infrastructure and services; d) establish basic conditions to promote investment in infrastructure; e) conserve, protect and develop natural and cultural heritage; f) train human resources of the receptive tour operators; g) incentivize inner tourism in the province.  It includes several incentives.

Law Nº 5428 establishes a fund administered by the Tourism and Culture Secretariat of Jujuy. Its objective is to provide financial resources to the tourism sector to finance: a) funding (reimbursable or not) to cover interest rates of commercial loans for infrastructure investments; b) programs for tourism promotion; c) caring and preserving the cultural and natural heritage of the province; and d) training programs.

Jujuy is implementing Land Use Plans since 2011 to provide access to compensation for forest conservation by landowners. However, there are several problems: compensation amounts are too low to cover the investments for forest conservation (e.g., fencing around forest reserves); weak capacities of landowners to prepare financial reports; delays in transfer of funds; small landowners lack financial capacity to hire a specialist to prepare a plan.

The plan's objective is to contribute within the framework of the Native Forest Law to the sustainable use of native forests as an alternative to land-use change. This inter-agency initiative (MAGyP and SAyDS) suggests that livestock activities in areas of native forests can be incorporated into the productive matrix fulfilling ecological, economic and social sustainability criteria.

PROCODAS provides financing of projects addressing technologies for social inclusion in the areas of: social economy; family agriculture; habitat; and disabilities.

PRODERI´s objectives are to support Family Agriculture and family farmers to incorporate technology and increase production, participate in markets and value chains; promote partnerships between economic actors for better market access; finance investments and working capital; generate employment opportunities and improve income of women, youth and rural employees; and strengthen cooperatives and organizations.

PRODEAR aims at contributing to social and productive cohesion and inclusion of the rural sector and creating conditions for the sustainable development of rural areas. Specific objectives include territorial development through social and gender equality; incorporating youth into productive activities; preserving the environment; and support to indigenous peoples respecting their culture.

In September 2017 Jujuy issued its first green bond in the international stock market (USD 210 million) to finance the construction of the Cauchari solar energy park. Green bonds are securities that raise capital for specific climate or environmental sustainability purposes issued by public or private organizations to invest in projects that reduce carbon emissions.

See http://www.undp.org/content/undp/en/home/operations/transparency/information_disclosurepolicy/

See https://www.thegef.org/gef/policies_guidelines

See https://www.thegef.org/gef/policies_guidelines

See https://www.thegef.org/gef/gef_agencies

See guidance here:  https://info.undp.org/global/popp/frm/pages/financial-management-and-execution-modalities.aspx

Excluding project team staff time and UNDP staff time and travel expenses.

The costs of UNDP Country Office and UNDP-GEF Unit’s participation and time are charged to the GEF Agency Fee.

Includes fees and travel costs

Includes fees and travel costs

see  https://info.undp.org/global/popp/ppm/Pages/Closing-a-Project.aspx

See https://popp.undp.org/_layouts/15/WopiFrame.aspx?sourcedoc=/UNDP_POPP_DOCUMENT_LIBRARY/Public/PPM_Project%20Management_Closing.docx&action=default.

Prohibited grounds of discrimination include race, ethnicity, gender, age, language, disability, sexual orientation, religion, political or other opinion, national or social or geographical origin, property, birth or other status including as an indigenous person or as a member of a minority. References to “women and men” or similar is understood to include women and men, boys and girls, and other groups discriminated against based on their gender identities, such as transgender people and transsexuals.

In regards to CO2, ‘significant emissions’ corresponds generally to more than 25,000 tons per year (from both direct and indirect sources). [The Guidance Note on Climate Change Mitigation and Adaptation provides additional information on GHG emissions.]

Forced evictions include acts and/or omissions involving the coerced or involuntary displacement of individuals, groups, or communities from homes and/or lands and common property resources that were occupied or depended upon, thus eliminating the ability of an individual, group, or community to reside or work in a particular dwelling, residence, or location without the provision of, and access to, appropriate forms of legal or other protections.

Argentine Legislation: Support to Aboriginal Communities Law No. 23,302, creating the National Indigenous Peoples Institute (1985) – ILO’s Indigenous and Tribal Peoples Convention (1989). Law No. 24071/92, as ratified in 2001 – Biological Diversity Convention (Article 8(j)) (1992) – Law No. 24,375/94 Granting Constitutional Status (Argentine Constitution Article 75 (17)) (1994) – Law No. 26,160 (2006) providing for a survey of indigenous territories.

Argentine Ministry of Justice and Human Rights. Derechos de los pueblos indígenas en la Argentina, una compilación (Rights of Indigenous Peoples of Argentina, a compilation), Sebastián Demicheli Calcagno, Viviana Canet, Leticia Virosta (eds.) – 1st edition. Autonomous City of Buenos Aires: Ministry of Justice and Human Rights. Human Rights Secretariat, 2015.

See http://www.un.org/esa/socdev/unpfii/documents/DRIPS_es.pdf

In other communities, formal protocols are in place currently in the Province of Jujuy, namely: “Consultation Protocol of the Departmental Council of Cochinoca Communities, Kolla People”, “Kachi Yupi. Procedure for Consultation and Free, Prior and Informed Consent for the Indigenous Communities of Cuenca De Salinas Grandes and Laguna De Guayatayoc” and the prior consultation procedure for land-use planning of Native Forests in Pueblo Ocloya.

Based on UNDP’s project level Grievance Response Mechanisms guidance, available at https://info.undp.org/sites/bpps/SES_Toolkit/SES%20Document%20Library/Uploaded%20October%202016/Supplemental%20Guidance_Grievance%20Redress%20Mechanisms.pdf

Argentine Legislation: Support to Aboriginal Communities Law No. 23,302, creating the National Indigenous Peoples Institute (1985) – ILO’s Indigenous and Tribal Peoples Convention (1989). Law No. 24071/92, as ratified in 2001 – Biological Diversity Convention (Article 8(j)) (1992) – Law No. 24,375/94 Granting Constitutional Status (Argentine Constitution Article 75 (17)) (1994) – Law No. 26,160 (2006) providing for a survey of indigenous territories.

Argentine Ministry of Justice and Human Rights. Derechos de los pueblos indígenas en la Argentina, una compilación (Rights of Indigenous Peoples of Argentina, a compilation), Sebastián Demicheli Calcagno, Viviana Canet, Leticia Virosta (eds.) – 1st edition. Autonomous City of Buenos Aires: Ministry of Justice and Human Rights. Human Rights Secretariat, 2015.

See http://www.un.org/esa/socdev/unpfii/documents/DRIPS_es.pdf

In other communities, formal protocols are in place currently in the Province of Jujuy, namely: “Consultation Protocol of the Departmental Council of Cochinoca Communities, Kolla People”, “Kachi Yupi. Procedure for Consultation and Free, Prior and Informed Consent for the Indigenous Communities of Cuenca De Salinas Grandes and Laguna De Guayatayoc” and the prior consultation procedure for land-use planning of Native Forests in Pueblo Ocloya.

The Government of Argentina established in 2016 a National Climate Change Cabinet comprised by 12 ministries which meets regularly to design public policies that include strategies to mitigate greenhouse gas emissions and to provide coordinated responses to the impacts of climate change.  The workplans and results are validated in roundtables with civil society representatives. The roundtables are convened by the Secretariat of Environment and Sustainable Development.